National Grid | RANDOLPH | 638792 | 02368 | 5.85 | Solar | 05_09_909W3 | 09/09/2024 | 10/21/2024 | 1 | 0 | 1 | 10/22/2024 | 10/22/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 09/09/2024 | 12/3/2025 | Y | EXP | 365 | 01/04/2025 | 02/11/2025 | 39 | 0 | 39 |  |  | 3/6/2025 | Connected |  | N
National Grid | NORWELL | 452283 | 02061 | 100 | Solar | 05_05_314W3 | 09/01/2022 | 09/19/2022 | 11 | 2 | 9 | 09/20/2022 | 09/20/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 | 09/01/2022 | 4/15/2024 | Y | EXP | 119 | 09/15/2023 | 02/08/2024 | 146 | 145 | 1 |  |  | 4/9/2024 | Connected |  | N
National Grid | BELCHERTOWN | 390299 | 01007 | 43.2 | Solar | 05_07_797W1 | 10/26/2021 | 01/06/2022 | 18 | 13 | 5 | 11/23/2021 | 11/23/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2021 |  | 6/28/2023 | N | EXP | 55 |  |  | 0 | 0 | 0 |  |  | 6/27/2023 | Connected |  | N
National Grid | MILFORD | 494670 | 01757 | 750 | Solar | 05_05_8L3 | 07/05/2023 | 10/30/2023 | 80 | 71 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 01/03/2024 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GOSHEN | 177601 | 01032 | 57.6 | Solar | 04_04_101L7 | 07/19/2017 | 07/19/2017 | 18 | 17 | 1 | 08/14/2017 | 08/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 7/24/2018 | N | EXP | 343 |  |  | 0 | 0 | 0 | 12/8/2017 | 12/8/2017 | 12/21/2017 | Connected |  | N
National Grid | WESTBOROUGH | 438767 | 01581 | 7.6 | Solar | 05_09_1109W3 | 06/20/2022 | 06/24/2022 | 5 | 2 | 3 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2022 | Connected |  | N
National Grid | BRIDGEWATER | 176914 | 02324 | 11.4 | Solar | 05_07_97W2 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 | 05/04/2016 | 5/10/2017 | Y | EXP | 348 | 11/07/2016 | 11/26/2016 | 13 | 0 | 13 | 12/5/2016 | 12/5/2016 | 12/5/2016 | Connected |  | N
National Grid | ATTLEBORO | 175929 | 02703 | 20 | Solar | 05_07_915W35 | 08/05/2015 | 08/05/2015 | 3 | 3 | 0 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2015 |  | 8/11/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 10/20/2015 | 10/20/2015 | 11/4/2015 | Connected |  | N
National Grid | NANTUCKET | 459286 | 02554 | 167.3 | Solar | 05_09_523L2 | 09/23/2022 | 11/04/2022 | 29 | 21 | 8 |  |  | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 09/23/2022 | 4/21/2025 | Y | STD | 5 | 11/16/2024 | 11/15/2024 | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 207501 | 01266 | 7.6 | Solar | 05_05_336W3 | 02/11/2019 | 02/20/2019 | 5 | 0 | 5 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 | 02/11/2019 | 7/22/2020 | Y | EXP | 365 | 11/01/2019 | 01/15/2020 | 75 | 0 | 75 |  |  | 4/22/2020 | Connected |  | N
National Grid | RANDOLPH | 641184 | 02368 | 15.2 | Solar | 05_09_909W3 | 09/18/2024 | 09/20/2024 | 3 | 1 | 2 | 09/23/2024 | 09/23/2024 | 16 | 0 | 16 | 11/20/2024 | 12/29/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 12/29/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 1/6/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | NORWELL | 648892 | 02061 | 10 | Solar | 05_05_314W3 | 11/01/2024 | 01/08/2025 | 38 | 34 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | PALMER | 467978 | 01009 | 28.8 | Solar | 05_07_797W1 | 10/19/2022 | 10/21/2022 | 2 | 1 | 1 | 10/24/2022 | 10/24/2022 | 25 | 7 | 18 | 07/21/2023 | 09/18/2023 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  | 09/18/2023 | 41 | 0 | 41 |  |  | 0 | 0 | 0 | 9/21/2023 |  | 11/30/2025 | N | EXP | 525 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 581441 | 01757 | 0 | Solar | 05_05_8L3 | 01/04/2024 | 01/05/2024 | 1 | 0 | 1 | 01/08/2024 | 01/08/2024 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 4/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2024 | Connected |  | N
National Grid | NORTHAMPTON | 197532 | 01060 | 9.92 | Solar | 04_04_101L7 | 10/02/2018 | 10/22/2018 | 9 | 9 | 0 | 10/23/2018 | 10/23/2018 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 454957 | 01581 | 9.86 | Solar | 05_09_1109W3 | 08/29/2022 | 09/01/2022 | 3 | 0 | 3 | 09/02/2022 | 09/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2022 |  | 11/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | N
National Grid | EAST BRIDGEWATER | 177471 | 02333 | 3.8 | Solar | 05_07_97W2 | 03/02/2017 | 03/02/2017 | 10 | 9 | 1 | 03/17/2017 | 03/17/2017 | 258 | 0 | 258 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 |  | 3/8/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 177196 | 02766 | 46 | Solar | 05_07_915W35 | 11/01/2016 | 11/01/2016 | 7 | 7 | 0 | 11/10/2016 | 11/10/2016 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2016 |  | 11/6/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 460033 | 02554 | 34.6 | Solar | 05_09_523L2 | 09/23/2022 | 11/03/2022 | 28 | 17 | 11 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 09/23/2022 | 1/19/2025 | Y | STD | 45 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | Y
National Grid | GREAT BARRINGTON | 240285 | 01230 | 7.6 | Solar | 05_05_336W3 | 07/24/2019 | 07/25/2019 | 0 | 0 | 0 | 07/26/2019 | 07/26/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2019 |  | 10/4/2019 | N | EXP | 59 |  |  | 0 | 0 | 0 |  |  | 9/26/2019 | Connected |  | N
National Grid | RANDOLPH | 644899 | 02368 | 16.53 | Solar | 05_09_909W3 | 10/03/2024 | 10/16/2024 | 8 | 6 | 2 | 10/17/2024 | 10/17/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 11/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | NORWELL | 654182 | 02061 | 5.76 | Solar | 05_05_314W3 | 11/18/2024 | 12/20/2024 | 3 | 0 | 3 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/18/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 473567 | 01069 | 15.925 | Solar | 05_07_797W1 | 11/03/2022 | 11/07/2022 | 2 | 0 | 2 | 11/08/2022 | 11/08/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 |  | 12/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | MILFORD | 581408 | 01757 | 0 | Solar | 05_05_8L3 | 01/04/2024 | 01/23/2024 | 13 | 12 | 1 | 01/24/2024 | 01/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 4/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2024 | Connected |  | N
National Grid | WILLIAMSBURG | 315235 | 01096 | 11.4 | Solar | 04_04_101L7 | 10/05/2020 | 10/12/2020 | 4 | 2 | 2 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2021 | Connected |  | N
National Grid | WESTBOROUGH | 458936 | 01581 | 0 | Solar | 05_09_1109W3 | 09/16/2022 | 09/21/2022 | 3 | 3 | 0 | 09/22/2022 | 09/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 09/16/2022 | 11/1/2023 | Y | EXP | 365 | 01/28/2023 | 03/04/2023 | 36 | 0 | 36 |  |  | 4/27/2023 | Connected |  | N
National Grid | BRIDGEWATER | 177961 | 02324 | 8.96 | Solar | 05_07_97W2 | 10/24/2017 | 10/24/2017 | 12 | 11 | 1 | 11/21/2017 | 11/21/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 10/31/2018 | N | EXP | 338 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | ATTLEBORO | 177613 | 02703 | 15.2 | Solar | 05_07_915W35 | 09/22/2017 | 09/22/2017 | 24 | 24 | 0 | 10/27/2017 | 10/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2017 |  | 9/27/2018 | N | EXP | 33 |  |  | 0 | 0 | 0 | 2/28/2018 | 2/28/2018 | 3/6/2018 | Connected |  | N
National Grid | NANTUCKET | 459650 | 02554 | 100 | Solar | 05_09_523L2 | 09/26/2022 | 11/07/2022 | 29 | 20 | 9 |  |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 09/26/2022 | 2/13/2025 | Y | STD | 45 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 361359 | 01230 | 7.6 | Solar | 05_05_336W3 | 06/22/2021 | 06/28/2021 | 4 | 0 | 4 | 06/29/2021 | 06/29/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2021 |  | 6/22/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 645387 | 02368 | 10.725 | Solar | 05_09_909W3 | 10/08/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/08/2024 | 12/8/2025 | Y | EXP | 365 | 02/13/2025 | 02/25/2025 | 13 | 0 | 13 |  |  | 2/28/2025 | Connected |  | N
National Grid | SCITUATE | 597594 | 02066 | 120 | Solar | 05_05_314W4 | 03/18/2024 | 04/22/2024 | 24 | 16 | 8 |  |  | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | PALMER | 482811 | 01069 | 10 | Solar | 05_07_797W1 | 12/12/2022 | 12/13/2022 | 1 | 0 | 1 | 12/14/2022 | 12/14/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 |  | 4/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2023 | Connected |  | N
National Grid | MILFORD | 622204 | 01757 | 6.72 | Solar | 05_05_8L3 | 07/02/2024 | 07/05/2024 | 4 | 0 | 4 | 09/27/2024 | 09/27/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2024 | 07/02/2024 | 11/13/2025 | Y | EXP | 365 | 12/19/2024 | 01/16/2025 | 29 | 0 | 29 |  |  | 1/29/2025 | Connected |  | N
National Grid | NORTHAMPTON | 324332 | 01053 | 19 | Solar | 04_04_101L7 | 11/10/2020 | 11/17/2020 | 3 | 0 | 3 | 11/18/2020 | 11/18/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2021 | Connected |  | N
National Grid | WESTBOROUGH | 461068 | 01581 | 30 | Solar | 05_09_1109W3 | 01/31/2023 | 02/08/2023 | 6 | 5 | 1 | 02/09/2023 | 02/09/2023 | 69 | 48 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2023 |  | 7/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | BRIDGEWATER | 187799 | 02324 | 15.2 | Solar | 05_07_97W2 | 06/12/2018 | 06/12/2018 | 12 | 0 | 12 | 06/22/2018 | 06/22/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 203337 | 02766 | 0 | Solar | 05_07_915W35 | 12/12/2018 | 12/24/2018 | 7 | 0 | 7 | 12/26/2018 | 12/26/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2019 | Connected |  | N
National Grid | NANTUCKET | 561289 | 02554 | 10 | Solar | 05_09_523L2 | 12/05/2023 | 12/06/2023 | 1 | 0 | 1 | 12/07/2023 | 12/07/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 361006 | 01230 | 7.6 | Solar | 05_05_336W3 | 07/15/2021 | 07/15/2021 | 0 | 0 | 0 | 07/16/2021 | 07/16/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 |  | 8/15/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2021 | Connected |  | N
National Grid | RANDOLPH | 645594 | 02368 | 10 | Solar | 05_09_909W3 | 10/08/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 597738 | 02066 | 120 | Solar | 05_05_314W4 | 04/18/2024 | 05/03/2024 | 12 | 3 | 9 |  |  | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | PALMER | 485014 | 01009 | 16 | Solar | 05_07_797W1 | 12/13/2022 | 12/27/2022 | 9 | 8 | 1 | 12/28/2022 | 12/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2023 | Connected |  | N
National Grid | MILFORD | 625421 | 01757 | 9.86 | Solar | 05_05_8L3 | 07/17/2024 | 07/22/2024 | 4 | 2 | 2 | 07/23/2024 | 07/23/2024 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 |  | 9/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2024 | Connected |  | Y
National Grid | GOSHEN | 331118 | 01032 | 19.72 | Solar | 04_04_101L7 | 01/15/2021 | 01/25/2021 | 4 | 0 | 4 | 01/26/2021 | 01/26/2021 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2021 | Connected |  | N
National Grid | WESTBOROUGH | 465317 | 01581 | 10 | Solar | 05_09_1109W3 | 10/24/2022 | 10/26/2022 | 2 | 0 | 2 | 10/27/2022 | 10/27/2022 | 260 | 247 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 194982 | 02324 | 7.6 | Solar | 05_07_97W2 | 09/04/2018 | 10/08/2018 | 17 | 17 | 0 | 10/09/2018 | 10/09/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 | 09/04/2018 | 5/21/2019 | Y | EXP | 222 | 11/09/2018 | 02/27/2019 | 110 | 0 | 110 |  |  | 4/18/2019 | Connected |  | N
National Grid | ATTLEBORO | 438286 | 02703 | 15.2 | Solar | 05_07_915W35 | 06/23/2022 | 07/26/2022 | 22 | 19 | 3 | 07/27/2022 | 07/27/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2022 |  | 11/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | Y
National Grid | NANTUCKET | 628785 | 02554 | 10 | Solar | 05_09_523L2 | 07/30/2024 | 08/14/2024 | 4 | 0 | 4 | 08/15/2024 | 08/15/2024 | 23 | 18 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 373774 | 01230 | 9.6 | Solar | 05_05_336W3 | 09/07/2021 | 01/10/2022 | 4 | 0 | 4 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 | 09/07/2021 | 6/2/2023 | Y | EXP | 365 | 02/01/2022 | 04/22/2022 | 81 | 0 | 81 |  |  | 6/7/2022 | Connected |  | N
National Grid | RANDOLPH | 650879 | 02368 | 23 | Solar | 05_09_909W3 | 10/30/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 10/30/2024 | 1/31/2026 | Y | EXP | 365 | 05/15/2025 | 06/16/2025 | 33 | 0 | 33 |  |  | 6/17/2025 | Connected |  | N
National Grid | NORWELL | 702409 | 02061 | 5.76 | Solar | 05_05_314W4 | 07/02/2025 | 10/14/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 1/29/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PALMER | 486457 | 01069 | 7.6 | Solar | 05_07_797W1 | 12/19/2022 | 01/03/2023 | 9 | 7 | 2 |  |  | 168 | 148 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 629128 | 01757 | 11.5 | Solar | 05_05_8L3 | 08/02/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2024 | Connected |  | N
National Grid | WILLIAMSBURG | 371953 | 01096 | 100 | Solar | 04_04_101L7 | 07/26/2021 | 08/17/2021 | 16 | 6 | 10 | 08/18/2021 | 08/18/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 | 07/26/2021 | 7/14/2023 | Y | EXP | 98 |  |  | 0 | 0 | 0 |  |  | 7/21/2023 | Connected |  | N
National Grid | WESTBOROUGH | 469401 | 01581 | 7.6 | Solar | 05_09_1109W3 | 10/18/2022 | 10/20/2022 | 2 | 0 | 2 | 10/21/2022 | 10/21/2022 | 202 | 107 | 95 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 192557 | 02324 | 15.2 | Solar | 05_07_97W2 | 08/02/2018 | 08/15/2018 | 7 | 0 | 7 | 08/16/2018 | 08/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 542075 | 02703 | 2000 | Solar | 05_07_915W35 | 09/29/2023 | 11/16/2023 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 01/05/2024 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 648336 | 02554 | 9.92 | Solar | 05_09_523L2 | 10/18/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/18/2024 | 12/22/2025 | Y | EXP | 365 | 01/18/2025 | 02/11/2025 | 25 | 0 | 25 |  |  | 2/26/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 430119 | 01266 | 6 | Solar | 05_05_336W3 | 05/23/2022 | 05/24/2022 | 1 | 0 | 1 | 05/25/2022 | 05/25/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 12/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2023 | Connected |  | N
National Grid | RANDOLPH | 659585 | 02368 | 11.2 | Solar | 05_09_909W3 | 12/10/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | NORWELL | 174880 | 02061 | 250.8 | Solar | 05_05_314W4 | 02/14/2013 | 02/14/2013 | 7 | 2 | 5 | 02/27/2013 | 02/27/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2013 | 02/14/2013 | 10/1/2013 | Y | EXP | 7 | 11/19/2013 | 03/15/2014 | 79 | 0 | 79 | 11/20/2014 | 11/20/2014 | 12/2/2014 | Connected |  | N
National Grid | PALMER | 578968 | 01009 | 10 | Solar | 05_07_797W1 | 01/18/2024 | 01/23/2024 | 3 | 0 | 3 | 01/24/2024 | 01/24/2024 | 50 | 33 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 01/18/2024 | 5/29/2025 | Y | EXP | 365 | 07/17/2024 | 07/16/2024 | 0 | 0 | 0 |  |  | 8/8/2024 | Connected |  | N
National Grid | MILFORD | 667705 | 01757 | 10 | Solar | 05_05_8L3 | 01/24/2025 | 02/11/2025 | 6 | 2 | 4 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N
National Grid | WILLIAMSBURG | 404158 | 01039 | 60 | Solar | 04_04_101L7 | 12/30/2021 | 02/04/2022 | 25 | 18 | 7 | 02/07/2022 | 02/07/2022 | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2022 |  | 9/16/2023 | N | EXP | 386 |  |  | 0 | 0 | 0 |  |  | 10/21/2022 | Connected |  | N
National Grid | WESTBOROUGH | 471659 | 01581 | 16.34 | Solar | 05_09_1109W3 | 10/27/2022 | 11/07/2022 | 8 | 7 | 1 | 11/08/2022 | 11/08/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2023 | Connected |  | N
National Grid | BRIDGEWATER | 201002 | 02324 | 15.2 | Solar | 05_07_97W2 | 11/12/2018 | 11/16/2018 | 2 | 0 | 2 | 11/19/2018 | 11/19/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2019 | 11/12/2018 | 7/22/2020 | Y | EXP | 365 | 01/30/2020 | 02/20/2020 | 21 | 0 | 21 |  |  | 7/14/2020 | Connected |  | N
National Grid | ATTLEBORO | 661282 | 02703 | 10 | Solar | 05_07_915W35 | 12/17/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/17/2024 | 2/26/2026 | Y | EXP | 365 | 07/16/2025 | 10/29/2025 | 106 | 0 | 106 |  |  | 11/13/2025 | Connected |  | N
National Grid | NANTUCKET | 659910 | 02554 | 7.6 | Solar | 05_09_523L2 | 12/11/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 12/11/2024 | 2/13/2026 | Y | EXP | 365 | 05/16/2025 | 10/03/2025 | 141 | 0 | 141 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 431440 | 01230 | 7.54 | Solar | 05_05_336W3 | 05/19/2022 | 05/25/2022 | 3 | 2 | 1 | 05/26/2022 | 05/26/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2022 | 05/19/2022 | 12/21/2023 | Y | EXP | 365 | 10/18/2022 | 12/21/2022 | 65 | 0 | 65 |  |  | 1/11/2023 | Connected |  | N
National Grid | RANDOLPH | 663177 | 02368 | 11.5 | Solar | 05_09_909W3 | 12/31/2024 | 01/27/2025 | 2 | 0 | 2 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 12/31/2024 | 4/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | NORWELL | 176836 | 02061 | 3.75 | Solar | 05_05_314W4 | 02/29/2016 | 02/29/2016 | 5 | 5 | 0 | 03/08/2016 | 03/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2016 |  | 3/6/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 5/10/2016 | 5/10/2016 | 5/12/2016 | Connected |  | N
National Grid | BELCHERTOWN | 592007 | 01007 | 8.99 | Solar | 05_07_797W1 | 02/27/2024 | 03/05/2024 | 5 | 3 | 2 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/27/2024 | 3/25/2025 | Y | EXP | 365 | 04/23/2024 | 04/23/2024 | 1 | 0 | 1 |  |  | 5/8/2024 | Connected |  | N
National Grid | MILFORD | 690901 | 01757 | 11.5 | Solar | 05_05_8L3 | 05/09/2025 | 06/18/2025 | 3 | 0 | 3 | 07/09/2025 | 07/09/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 485414 | 01062 | 100 | Solar | 04_04_101L7 | 01/06/2023 | 02/06/2023 | 21 | 11 | 10 | 02/07/2023 | 02/07/2023 | 25 | 0 | 25 | 04/04/2023 | 05/16/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 05/16/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 5/30/2023 |  | 12/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 515132 | 01532 | 10 | Solar | 05_09_1109W3 | 03/30/2023 | 04/03/2023 | 2 | 0 | 2 | 04/04/2023 | 04/04/2023 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2023 |  | 9/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2023 | Connected |  | N
National Grid | BRIDGEWATER | 223131 | 02333 | 199.8 | Solar | 05_07_97W2 | 04/27/2019 | 05/21/2019 | 16 | 11 | 5 | 05/22/2019 | 05/22/2019 | 13 | 3 | 10 | 07/19/2019 | 07/30/2020 | 260 | 151 | 109 |  |  | 0 | 0 | 0 |  | 07/30/2020 | 260 | 151 | 109 |  |  | 0 | 0 | 0 | 9/4/2020 | 04/27/2019 | 10/11/2022 | Y | EXP | 245 | 05/11/2021 | 01/04/2022 | 239 | 226 | 13 |  |  | 9/15/2022 | Connected |  | N
National Grid | NORTON | 667801 | 02766 | 4990 | Solar | 05_07_915W35 | 03/18/2025 | 04/09/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/10/2025 | 05/06/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 690691 | 02554 | 15.2 | Solar | 05_09_523L2 | 05/14/2025 | 05/23/2025 | 6 | 3 | 3 | 05/27/2025 | 05/27/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 521681 | 01266 | 10 | Solar | 05_05_336W3 | 05/17/2023 | 05/18/2023 | 1 | 0 | 1 | 05/19/2023 | 05/19/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 7/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 669864 | 02368 | 10 | Solar | 05_09_909W3 | 02/13/2025 | 02/19/2025 | 3 | 0 | 3 | 02/20/2025 | 02/20/2025 | 60 | 37 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 | 02/13/2025 | 5/28/2026 | Y | EXP | 365 | 06/18/2025 | 06/30/2025 | 13 | 0 | 13 |  |  | 9/2/2025 | Connected |  | N
National Grid | NORWELL | 176933 | 02061 | 72 | Solar | 05_05_314W4 | 01/28/2016 | 01/28/2016 | 4 | 4 | 0 | 02/03/2016 | 02/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 2/2/2017 | N | EXP | 345 |  |  | 0 | 0 | 0 | 11/7/2016 | 11/7/2016 | 8/12/2016 | Connected |  | N
National Grid | BELCHERTOWN | 600324 | 01007 | 12 | Solar | 05_07_797W1 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2024 |  | 5/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | MILFORD | 695236 | 01757 | 15.76 | Solar | 05_05_8L3 | 05/30/2025 | 06/03/2025 | 2 | 0 | 2 | 06/04/2025 | 06/04/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | NORTHAMPTON | 492630 | 01053 | 21.638 | Solar | 04_04_101L7 | 01/16/2023 | 01/18/2023 | 2 | 0 | 2 | 01/19/2023 | 01/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2023 |  | 3/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N
National Grid | WESTBOROUGH | 559483 | 01581 | 10 | Solar | 05_09_1109W3 | 11/10/2023 | 12/08/2023 | 19 | 18 | 1 | 12/11/2023 | 12/11/2023 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/10/2023 | 3/25/2025 | Y | EXP | 365 | 04/23/2024 | 05/01/2024 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 228709 | 02324 | 7.6 | Solar | 05_07_97W2 | 07/24/2019 | 07/30/2019 | 3 | 0 | 3 | 07/31/2019 | 07/31/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 678529 | 02766 | 7.6 | Solar | 05_07_915W35 | 03/17/2025 | 03/25/2025 | 10 | 6 | 4 | 04/10/2025 | 04/10/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 695597 | 02554 | 11.4 | Solar | 05_09_523L2 | 06/02/2025 | 06/24/2025 | 15 | 12 | 3 | 06/25/2025 | 06/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 556931 | 01230 | 10 | Solar | 05_05_336W3 | 09/27/2023 | 09/28/2023 | 1 | 0 | 1 | 09/29/2023 | 09/29/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2023 |  | 11/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2023 | Connected |  | N
National Grid | RANDOLPH | 676776 | 02368 | 20 | Solar | 05_09_909W3 | 03/10/2025 | 04/14/2025 | 26 | 20 | 6 | 04/15/2025 | 04/15/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 176928 | 02066 | 32.4 | Solar | 05_05_314W4 | 11/20/2015 | 11/20/2015 | 16 | 16 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2015 |  | 11/25/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 | 1/3/2017 | 1/3/2017 | 1/11/2017 | Connected |  | N
National Grid | PALMER | 656387 | 01009 | 6.67 | Solar | 05_07_797W1 | 11/24/2024 | 12/11/2024 | 9 | 5 | 4 | 12/12/2024 | 12/12/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/24/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | MILFORD | 704830 | 01757 | 480 | Solar | 05_05_8L3 | 08/28/2025 |  | 32 | 24 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 526775 | 01096 | 16.24 | Solar | 04_04_101L7 | 05/23/2023 | 07/03/2023 | 28 | 26 | 2 | 07/05/2023 | 07/05/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 |  | 8/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2023 | Connected |  | Y
National Grid | NORTHBOROUGH | 528486 | 01532 | 14.79 | Solar | 05_09_1109W3 | 06/23/2023 | 07/07/2023 | 10 | 6 | 4 | 07/10/2023 | 07/10/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2024 | Connected |  | N
National Grid | BRIDGEWATER | 230807 | 02324 | 13.6 | Solar | 05_07_97W2 | 06/26/2019 | 07/05/2019 | 5 | 5 | 0 | 07/08/2019 | 07/08/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2019 | 06/26/2019 | 6/1/2020 | Y | EXP | 365 | 01/24/2020 | 02/05/2020 | 12 | 0 | 12 |  |  | 2/6/2020 | Connected |  | N
National Grid | ATTLEBORO | 683341 | 02703 | 7.6 | Solar | 05_07_915W35 | 04/07/2025 | 05/02/2025 | 1 | 0 | 1 | 05/09/2025 | 05/09/2025 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 04/07/2025 | 6/27/2026 | Y | EXP | 365 | 08/13/2025 | 09/16/2025 | 35 | 0 | 35 |  |  | 9/25/2025 | Connected |  | N
National Grid | NANTUCKET | 698128 | 02554 | 12.54 | Solar | 05_09_523L2 | 06/13/2025 | 09/15/2025 | 64 | 62 | 2 | 09/16/2025 | 09/16/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 540445 | 01230 | 6 | Solar | 05_05_336W3 | 07/17/2023 | 07/18/2023 | 1 | 0 | 1 | 07/19/2023 | 07/19/2023 | 17 | 0 | 17 | 08/24/2023 | 09/25/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 09/25/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | N
National Grid | RANDOLPH | 676558 | 02368 | 23 | Solar | 05_09_909W3 | 03/07/2025 |  | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 177970 | 02061 | 414 | Solar | 05_05_314W4 | 04/25/2017 | 04/25/2017 | 28 | 26 | 2 | 06/06/2017 | 06/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2017 | 04/25/2017 | 5/1/2017 | Y | EXP | 73 | 09/22/2017 | 10/13/2017 | 14 | 0 | 14 | 11/27/2017 | 11/27/2017 | 11/27/2017 | Connected |  | N
National Grid | BELCHERTOWN | 658952 | 01007 | 8.41 | Solar | 05_07_797W1 | 12/06/2024 | 04/14/2025 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 12/06/2024 | 5/29/2026 | Y | EXP | 365 | 07/24/2025 | 10/01/2025 | 70 | 0 | 70 |  |  | 10/16/2025 | Connected |  | N
National Grid | MILFORD | 720017 | 01757 | 19 | Solar | 05_05_8L3 | 09/18/2025 | 10/23/2025 | 24 | 20 | 4 | 10/24/2025 | 10/24/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 11/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | WILLIAMSBURG | 551854 | 01096 | 19 | Solar | 04_04_101L7 | 08/29/2023 | 09/14/2023 | 12 | 11 | 1 | 09/15/2023 | 09/15/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2023 |  | 11/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | WESTBOROUGH | 544313 | 01581 | 22.8 | Solar | 05_09_1109W3 | 07/31/2023 | 08/01/2023 | 1 | 0 | 1 | 08/02/2023 | 08/02/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 8/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2023 | Connected |  | N
National Grid | BRIDGEWATER | 265635 | 02333 | 4.55 | Solar | 05_07_97W2 | 11/21/2019 |  | 83 | 80 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 174513 | 02766 | 1500 | Solar | 05_07_915W36 | 05/23/2011 | 05/23/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 05/23/2011 | 10/31/2012 | Y | STD | 42 | 01/02/2013 | 09/12/2013 | 166 | 0 | 166 | 9/10/2013 | 9/10/2013 | 9/23/2013 | Connected |  | N
National Grid | NANTUCKET | 743963 | 02554 | 5.76 | Solar | 05_09_523L2 | 01/07/2026 | 01/12/2026 | 3 | 0 | 3 | 01/13/2026 | 01/13/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2026 | Connected |  | N
National Grid | STOCKBRIDGE | 552467 | 01266 | 10 | Solar | 05_05_336W3 | 08/31/2023 | 09/05/2023 | 2 | 0 | 2 | 09/06/2023 | 09/06/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 |  | 11/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2024 | Connected |  | N
National Grid | RANDOLPH | 679096 | 02368 | 10 | Solar | 05_09_909W3 | 03/19/2025 | 04/16/2025 | 5 | 0 | 5 | 04/30/2025 | 04/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 03/19/2025 | 6/5/2026 | Y | EXP | 365 | 09/16/2025 | 09/15/2025 | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | SCITUATE | 194780 | 02066 | 7.6 | Solar | 05_05_314W4 | 11/27/2018 | 12/05/2018 | 6 | 0 | 6 | 12/06/2018 | 12/06/2018 | 160 | 0 | 160 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 662678 | 01007 | 7.6 | Solar | 05_07_797W1 | 01/02/2025 | 01/29/2025 | 10 | 6 | 4 | 01/30/2025 | 01/30/2025 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2025 | Connected |  | N
National Grid | MILFORD | 720592 | 01757 | 15.76 | Solar | 05_05_8L3 | 09/19/2025 | 09/26/2025 | 5 | 0 | 5 | 09/29/2025 | 09/29/2025 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2026 | Connected |  | N
National Grid | NORTHAMPTON | 590905 | 01062 | 0 | Other | 04_04_101L7 | 03/14/2024 | 03/27/2024 | 9 | 7 | 2 | 03/28/2024 | 03/28/2024 | 98 | 74 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 547421 | 01581 | 5 | Solar | 05_09_1109W3 | 08/10/2023 | 08/15/2023 | 4 | 3 | 1 | 08/16/2023 | 08/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 10/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2023 | Connected |  | N
National Grid | EAST BRIDGEWATER | 287352 | 02333 | 7.6 | Solar | 05_07_97W2 | 06/10/2020 | 06/15/2020 | 2 | 0 | 2 | 06/16/2020 | 06/16/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/10/2020 | 6/30/2021 | Y | EXP | 365 | 01/29/2021 | 03/11/2021 | 41 | 0 | 41 |  |  | 6/6/2021 | Connected |  | N
National Grid | ATTLEBORO | 174512 | 02703 | 1500 | Solar | 05_07_915W36 | 05/23/2011 | 05/23/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 05/23/2011 | 10/31/2012 | Y | STD | 42 | 01/02/2013 | 09/12/2013 | 166 | 0 | 166 | 9/10/2013 | 9/10/2013 | 9/23/2013 | Connected |  | N
National Grid | NANTUCKET | 676977 | 02554 | 750 | Solar | 05_09_523L4 | 04/08/2025 | 06/27/2025 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2025 | 07/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | STOCKBRIDGE | 592714 | 01236 | 14.175 | Solar | 05_05_336W3 | 03/08/2024 | 03/14/2024 | 4 | 1 | 3 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 | 03/08/2024 | 5/31/2025 | Y | EXP | 365 | 07/02/2024 | 08/06/2024 | 36 | 0 | 36 |  |  | 8/20/2024 | Connected |  | N
National Grid | RANDOLPH | 691016 | 02368 | 25 | Other | 05_09_909W3 | 08/07/2025 |  | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 208290 | 02066 | 3 | Solar | 05_05_314W4 | 02/13/2019 | 02/25/2019 | 6 | 1 | 5 | 02/26/2019 | 02/26/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 3/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2019 | Connected |  | N
National Grid | BELCHERTOWN | 667190 | 01007 | 10 | Solar | 05_07_797W1 | 01/22/2025 | 01/28/2025 | 4 | 0 | 4 | 01/29/2025 | 01/29/2025 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2025 | 01/22/2025 | 3/26/2026 | Y | EXP | 365 | 05/21/2025 | 06/10/2025 | 21 | 0 | 21 |  |  | 7/22/2025 | Connected |  | N
National Grid | MILFORD | 286728 | 01757 | 0 | Solar | 05_05_8L4 | 04/28/2020 | 04/30/2020 | 1 | 0 | 1 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2020 | Terminated |  | N
National Grid | NORTHAMPTON | 660023 | 01062 | 5 | Solar | 04_04_101L7 | 12/11/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | WESTBOROUGH | 583485 | 01581 | 3.8 | Solar | 05_09_1109W3 | 03/14/2024 | 03/19/2024 | 3 | 0 | 3 | 03/20/2024 | 03/20/2024 | 2 | 0 | 2 | 04/03/2024 | 05/16/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  | 05/16/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 5/22/2024 |  | 7/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | BRIDGEWATER | 310071 | 02324 | 5 | Solar | 05_07_97W2 | 01/11/2021 | 01/15/2021 | 3 | 0 | 3 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  | 4/26/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 174605 | 02766 | 1500 | Wind | 05_07_915W36 | 02/22/2010 | 02/22/2010 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2010 | 02/22/2010 | 3/29/2012 | Y | STD | 52 | 10/18/2011 | 03/15/2012 | 100 | 0 | 100 | 8/3/2012 | 8/3/2012 | 3/29/2012 | Connected |  | N
National Grid | NANTUCKET | 705630 | 02554 | 5.76 | Solar | 05_09_523L4 | 07/17/2025 | 09/15/2025 | 4 | 0 | 4 | 09/16/2025 | 09/16/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | EGREMONT | 603626 | 01230 | 2.32 | Solar | 05_05_336W3 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2024 | Connected |  | N
National Grid | RANDOLPH | 692583 | 02368 | 6.08 | Solar | 05_09_909W3 | 05/19/2025 | 06/18/2025 | 1 | 0 | 1 | 06/23/2025 | 06/23/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  | 8/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | SCITUATE | 246090 | 02066 | 0 | Solar | 05_05_314W4 | 07/30/2019 | 07/31/2019 | 0 | 0 | 0 | 08/01/2019 | 08/01/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2019 |  | 11/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 174196 | 01007 | 1500 | Solar | 05_07_797W19 | 03/20/2012 | 03/20/2012 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2013 |  | 11/1/2012 | N | STD | 111 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 660850 | 01757 | 10 | Solar | 05_05_8L4 | 12/16/2024 | 01/21/2025 | 6 | 1 | 5 | 01/22/2025 | 01/22/2025 | 54 | 35 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 12/16/2024 | 4/21/2026 | Y | EXP | 365 | 05/21/2025 | 05/20/2025 | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WILLIAMSBURG | 688005 | 01096 | 25 | Solar | 04_04_101L7 | 04/28/2025 | 05/15/2025 | 12 | 9 | 3 | 05/16/2025 | 05/16/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2025 | Connected |  | N
National Grid | WESTBOROUGH | 589495 | 01581 | 15.66 | Solar | 05_09_1109W3 | 02/12/2024 | 03/08/2024 | 19 | 16 | 3 | 03/11/2024 | 03/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | BRIDGEWATER | 319113 | 02324 | 5 | Solar | 05_07_97W2 | 11/22/2020 | 11/24/2020 | 1 | 0 | 1 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 11/22/2020 |  | Y | EXP | 365 | 04/27/2021 | 05/21/2021 | 24 | 0 | 24 |  |  | 6/22/2021 | Connected |  | N
National Grid | ATTLEBORO | 177758 | 02703 | 360 | Solar | 05_07_915W36 | 08/02/2017 | 08/02/2017 | 48 | 48 | 0 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 |  | 12/1/2020 | N | STD | 874 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 735075 | 02554 | 7.6 | Solar | 05_09_523L4 | 11/20/2025 | 11/21/2025 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GREAT BARRINGTON | 606160 | 01230 | 3.8 | Solar | 05_05_336W3 | 04/23/2024 | 05/03/2024 | 5 | 0 | 5 | 05/06/2024 | 05/06/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/23/2024 | 6/3/2025 | Y | EXP | 365 | 07/30/2024 | 08/26/2024 | 28 | 0 | 28 |  |  | 8/29/2024 | Connected |  | N
National Grid | RANDOLPH | 701270 | 02368 | 7.6 | Solar | 05_09_909W3 | 06/26/2025 | 07/11/2025 | 3 | 0 | 3 | 07/22/2025 | 07/22/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/26/2025 | 8/21/2026 | Y | EXP | 365 | 09/19/2025 | 09/18/2025 | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | SCITUATE | 318365 | 02066 | 10 | Solar | 05_05_314W4 | 10/09/2020 | 10/12/2020 | 0 | 0 | 0 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 10/09/2020 | 4/30/2021 | Y | EXP | 365 | 01/28/2021 | 02/17/2021 | 20 | 0 | 20 |  |  | 3/4/2021 | Connected |  | N
National Grid | WARE | 174480 | 01082 | 1500 | Solar | 05_07_797W19 | 04/19/2011 | 04/19/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2011 | 06/20/2011 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2012 | 04/19/2011 | 10/31/2012 | Y | STD | 282 | 05/27/2013 | 07/27/2013 | 42 | 0 | 42 | 7/26/2013 | 7/26/2013 | 8/15/2013 | Connected |  | N
National Grid | MILFORD | 694188 | 01757 | 7.25 | Solar | 05_05_8L4 | 06/05/2025 | 06/11/2025 | 4 | 0 | 4 | 06/12/2025 | 06/12/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GOSHEN | 702575 | 01032 | 25.08 | Solar | 04_04_101L7 | 07/07/2025 | 07/11/2025 | 3 | 1 | 2 | 07/14/2025 | 07/14/2025 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | WESTBOROUGH | 603142 | 01581 | 20 | Solar | 05_09_1109W3 | 04/10/2024 | 04/16/2024 | 3 | 1 | 2 | 04/17/2024 | 04/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2024 | Connected |  | N
National Grid | BRIDGEWATER | 325552 | 02324 | 7.68 | Solar | 05_07_97W2 | 12/28/2020 | 01/12/2021 | 9 | 9 | 0 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 | 12/28/2020 | 5/25/2022 | Y | EXP | 365 | 04/27/2021 | 05/19/2021 | 22 | 0 | 22 |  |  | 10/4/2021 | Connected |  | N
National Grid | REHOBOTH | 206251 | 02769 | 0 | Solar | 05_07_915W36 | 02/01/2019 | 02/12/2019 | 6 | 0 | 6 | 02/13/2019 | 02/13/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | NANTUCKET | 744636 | 02554 | 11.5 | Solar | 05_09_523L4 | 01/12/2026 | 01/13/2026 | 2 | 0 | 2 | 01/21/2026 | 01/21/2026 | 30 | 16 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STOCKBRIDGE | 617495 | 01266 | 11.5 | Solar | 05_05_336W3 | 06/18/2024 | 06/21/2024 | 2 | 0 | 2 | 06/24/2024 | 06/24/2024 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2024 |  | 8/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2024 | Connected |  | N
National Grid | RANDOLPH | 706628 | 02368 | 0 | Solar | 05_09_909W3 | 07/23/2025 | 07/28/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | SCITUATE | 343155 | 02066 | 0 | Solar | 05_05_314W4 | 02/19/2021 | 02/24/2021 | 3 | 2 | 1 | 02/25/2021 | 02/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2021 |  | 2/24/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 174898 | 01069 | 1800 | Solar | 05_07_797W19 | 03/20/2012 | 03/20/2012 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2012 | 07/18/2012 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2013 |  | 12/3/2012 | N | STD | 79 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 710661 | 01757 | 11.5 | Solar | 05_05_8L4 | 08/08/2025 | 10/21/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 40 | 20 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 682333 | 01053 | 22.8 | Solar | 05_01_10J323 | 04/07/2025 | 04/21/2025 | 9 | 5 | 4 | 04/22/2025 | 04/22/2025 | 24 | 10 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 7/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | NORTHBOROUGH | 613110 | 01532 | 7.6 | Solar | 05_09_1109W3 | 05/23/2024 | 06/07/2024 | 7 | 5 | 2 | 06/10/2024 | 06/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 05/23/2024 | 6/26/2025 | Y | EXP | 365 | 07/26/2024 | 08/21/2024 | 27 | 0 | 27 |  |  | 8/24/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 332457 | 02379 | 3.8 | Solar | 05_07_97W2 | 01/07/2021 | 01/15/2021 | 6 | 6 | 0 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 |  | 1/14/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 337902 | 02703 | 7.6 | Solar | 05_07_915W36 | 01/21/2021 | 02/09/2021 | 13 | 12 | 1 | 02/10/2021 | 02/10/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  | 11/26/2022 | N | EXP | 55 |  |  | 0 | 0 | 0 |  |  | 10/28/2022 | Connected |  | N
National Grid | NANTUCKET | 752329 | 02554 | 10 | Solar | 05_09_523L4 | 02/20/2026 | 02/26/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | GREAT BARRINGTON | 624049 | 01230 | 0 | Solar | 05_05_336W3 | 07/11/2024 | 07/17/2024 | 4 | 0 | 4 | 07/18/2024 | 07/18/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 07/11/2024 | 8/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2024 | Connected |  | N
National Grid | RANDOLPH | 727168 | 02368 | 249 | Solar | 05_09_909W3 | 10/17/2025 | 11/10/2025 | 15 | 8 | 7 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 415123 | 02066 | 15.2 | Solar | 05_05_314W4 | 03/02/2022 | 03/03/2022 | 1 | 0 | 1 | 03/04/2022 | 03/04/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 176793 | 01082 | 11.4 | Solar | 05_07_797W19 | 02/24/2016 | 02/24/2016 | 5 | 5 | 0 | 03/03/2016 | 03/03/2016 | 238 | 0 | 238 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2016 |  | 3/1/2017 | N | EXP | 317 |  |  | 0 | 0 | 0 | 4/18/2016 | 4/18/2016 |  | Withdrawn |  | Y
National Grid | MILFORD | 721493 | 01757 | 10 | Solar | 05_05_8L4 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 | 10/09/2025 | 11/24/2026 | Y | EXP | 365 | 01/17/2026 | 02/10/2026 | 25 | 0 | 25 |  |  |  | Completion Documents |  | N
National Grid | GOSHEN | 174809 | 01032 | 145 | Solar | 05_01_10J323 | 01/24/2013 | 01/24/2013 | 7 | 0 | 7 | 02/05/2013 | 02/05/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2013 |  | 5/15/2013 | N | EXP | 33 | 05/22/2013 | 07/17/2013 | 37 | 0 | 37 | 7/29/2013 | 7/29/2013 | 8/20/2013 | Connected |  | N
National Grid | WESTBOROUGH | 613078 | 01581 | 999 | Solar | 05_09_1109W3 | 12/16/2024 | 03/05/2025 | 54 | 45 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2025 | 04/02/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 337718 | 02379 | 4.08 | Solar | 05_07_97W2 | 02/05/2021 | 04/26/2021 | 54 | 53 | 1 | 04/27/2021 | 04/27/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 4/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2021 | Connected |  | N
National Grid | REHOBOTH | 600721 | 02769 | 0 | Solar | 05_07_915W36 | 03/31/2024 | 04/02/2024 | 2 | 0 | 2 | 04/03/2024 | 04/03/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 174243 | 02554 | 2000 | Solar | 05_09_523L4 | 02/21/2012 | 02/21/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2012 | 05/24/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 629702 | 01230 | 10 | Solar | 05_05_336W3 | 08/02/2024 | 08/30/2024 | 12 | 7 | 5 | 09/03/2024 | 09/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 642779 | 02368 | 45 | Solar | 05_09_909W4 | 09/25/2024 | 11/04/2024 | 28 | 19 | 9 | 11/05/2024 | 11/05/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SCITUATE | 472757 | 02066 | 11.31 | Solar | 05_05_314W4 | 11/11/2022 | 11/18/2022 | 6 | 2 | 4 | 11/21/2022 | 11/21/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2022 | 11/11/2022 | 4/24/2024 | Y | EXP | 365 | 02/07/2023 | 04/25/2023 | 78 | 0 | 78 |  |  | 12/1/2023 | Connected |  | N
National Grid | WARE | 177635 | 01082 | 8 | Solar | 05_07_797W19 | 07/19/2017 | 07/19/2017 | 23 | 18 | 5 | 08/22/2017 | 08/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 | 07/19/2017 | 7/25/2018 | Y | EXP | 331 | 12/20/2017 | 12/30/2017 | 7 | 0 | 7 | 2/27/2018 | 2/27/2018 | 3/6/2018 | Connected |  | N
National Grid | MILFORD | 734048 | 01757 | 13.36 | Solar | 05_05_8L4 | 11/17/2025 | 11/18/2025 | 2 | 0 | 2 | 12/23/2025 | 12/23/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | GOSHEN | 578609 | 01032 | 6.96 | Solar | 05_01_10J323 | 01/08/2024 | 01/10/2024 | 2 | 0 | 2 | 01/11/2024 | 01/11/2024 | 172 | 25 | 147 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 616894 | 01532 | 50 | Solar | 05_09_1109W3 | 06/10/2024 | 06/20/2024 | 7 | 3 | 4 | 06/21/2024 | 06/21/2024 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 399692 | 02379 | 9.8 | Solar | 05_07_97W2 | 12/21/2021 | 12/22/2021 | 1 | 0 | 1 | 12/23/2021 | 12/23/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2022 | 12/21/2021 | 8/2/2023 | Y | EXP | 365 | 07/12/2022 | 08/01/2022 | 21 | 0 | 21 |  |  | 8/25/2022 | Connected |  | N
National Grid | ATTLEBORO | 634979 | 02703 | 240 | Solar | 05_07_915W36 | 08/28/2024 | 01/03/2025 | 85 | 78 | 7 | 01/06/2025 | 01/06/2025 | 57 | 24 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 174292 | 01604 | 950 | Solar | 05_09_523L4 | 12/09/2011 | 12/09/2011 | 40 | 0 | 40 | 02/08/2012 | 02/08/2012 | 485 | 163 | 322 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOCKBRIDGE | 630813 | 01266 | 22.42 | Solar | 05_05_336W3 | 08/07/2024 | 08/08/2024 | 1 | 0 | 1 | 08/09/2024 | 08/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 |  | 8/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | RANDOLPH | 714304 | 02368 | 7.6 | Solar | 05_09_909W4 | 08/25/2025 | 09/12/2025 | 6 | 0 | 6 | 09/25/2025 | 09/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 | 08/25/2025 | 11/14/2026 | Y | EXP | 365 | 01/13/2026 |  | 53 | 0 | 53 |  |  |  | Construction |  | N
National Grid | SCITUATE | 495314 | 02066 | 11.136 | Solar | 05_05_314W4 | 04/10/2023 | 05/02/2023 | 15 | 13 | 2 | 05/03/2023 | 05/03/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2023 |  | 7/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | PALMER | 178556 | 01079 | 133.2 | Solar | 05_07_797W19 | 03/12/2018 | 03/12/2018 | 1 | 0 | 1 | 03/30/2018 | 03/30/2018 | 4 | 0 | 4 | 04/06/2018 | 05/16/2018 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  | 05/16/2018 | 28 | 8 | 20 |  |  | 0 | 0 | 0 | 5/30/2018 | 03/12/2018 | 1/10/2022 | Y | EXP | 611 | 02/12/2021 | 12/17/2021 | 309 | 6 | 303 |  |  | 12/30/2021 | Connected |  | N
National Grid | MILFORD | 736729 | 01757 | 5.76 | Solar | 05_05_8L4 | 11/26/2025 | 12/02/2025 | 3 | 0 | 3 | 12/03/2025 | 12/03/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 |  | 1/16/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WILLIAMSBURG | 401106 | 01096 | 0 | Other | 05_01_10J366 | 01/24/2022 | 01/31/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 03/01/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 634705 | 01532 | 11.5 | Solar | 05_09_1109W3 | 08/22/2024 | 09/04/2024 | 8 | 6 | 2 | 09/05/2024 | 09/05/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 9/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 412389 | 02379 | 3 | Solar | 05_07_97W2 | 03/24/2022 | 03/28/2022 | 2 | 0 | 2 | 03/29/2022 | 03/29/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 659410 | 02769 | 0 | Battery Add-On | 05_07_915W36 | 12/09/2024 | 12/26/2024 | 12 | 8 | 4 | 12/27/2024 | 12/27/2024 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | WORCESTER | 174291 | 01604 | 950 | Solar | 05_09_523L4 | 12/09/2011 | 12/09/2011 | 40 | 0 | 40 | 02/08/2012 | 02/08/2012 | 483 | 0 | 483 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 643421 | 01230 | 10 | Solar | 05_05_336W3 | 09/27/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 | 09/27/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | RANDOLPH | 723531 | 02368 | 10 | Solar | 05_09_909W4 | 10/02/2025 | 10/09/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 1/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SCITUATE | 544895 | 02066 | 15.2 | Solar | 05_05_314W4 | 08/01/2023 | 08/07/2023 | 4 | 0 | 4 | 08/08/2023 | 08/08/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 |  | 10/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2023 | Connected |  | N
National Grid | WARE | 191685 | 01082 | 136 | Solar | 05_07_797W19 | 12/05/2018 | 12/12/2018 | 4 | 0 | 4 | 12/13/2018 | 12/13/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 740725 | 01757 | 13.96 | Solar | 05_05_8L4 | 12/17/2025 | 01/06/2026 | 7 | 2 | 5 | 01/28/2026 | 01/28/2026 | 15 | 4 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTHAMPTON | 622728 | 01062 | 10 | Solar | 05_01_10J366 | 07/27/2024 | 08/28/2024 | 23 | 20 | 3 | 08/29/2024 | 08/29/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2024 |  | 11/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 644061 | 01532 | 10 | Solar | 05_09_1109W3 | 10/01/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 59 | 35 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 416744 | 02379 | 5.51 | Solar | 05_07_97W2 | 04/07/2022 | 04/11/2022 | 2 | 0 | 2 | 04/12/2022 | 04/12/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2022 | 04/07/2022 | 12/13/2023 | Y | EXP | 365 | 11/04/2022 | 12/12/2022 | 39 | 0 | 39 |  |  | 1/7/2023 | Connected |  | N
National Grid | REHOBOTH | 667216 | 02769 | 16.96 | Solar | 05_07_915W36 | 03/14/2025 | 03/20/2025 | 4 | 0 | 4 | 03/21/2025 | 03/21/2025 | 175 | 157 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 174290 | 01604 | 950 | Solar | 05_09_523L4 | 12/09/2011 | 12/09/2011 | 40 | 0 | 40 | 02/08/2012 | 02/08/2012 | 485 | 0 | 485 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 645301 | 01230 | 7.6 | Solar | 05_05_336W3 | 10/07/2024 | 10/30/2024 | 2 | 0 | 2 | 10/31/2024 | 10/31/2024 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/07/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | RANDOLPH | 737787 | 02368 | 7.6 | Solar | 05_09_909W4 | 12/03/2025 | 12/04/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 16 | 1 | 15 | 02/03/2026 | 03/02/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 03/02/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 3/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SCITUATE | 548633 | 02066 | 5.985 | Solar | 05_05_314W4 | 08/22/2023 | 08/25/2023 | 3 | 1 | 2 | 08/28/2023 | 08/28/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 |  | 11/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2024 | Connected |  | N
National Grid | PALMER | 223130 | 01069 | 133.2 | Solar | 05_07_797W19 | 04/27/2019 | 05/21/2019 | 16 | 13 | 3 | 05/22/2019 | 05/22/2019 | 26 | 16 | 10 | 07/26/2019 | 09/04/2020 | 61 | 58 | 3 |  |  | 0 | 0 | 0 |  | 09/04/2020 | 61 | 58 | 3 |  |  | 0 | 0 | 0 | 9/28/2020 |  | 1/3/2023 | N | EXP | 365 | 02/25/2021 | 12/08/2021 | 286 | 67 | 219 |  |  | 3/7/2022 | Connected |  | N
National Grid | MILFORD | 742489 | 01757 | 23 | Solar | 05_05_8L4 | 12/29/2025 | 01/06/2026 | 5 | 0 | 5 | 01/07/2026 | 01/07/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 659756 | 01062 | 7.68 | Solar | 05_01_10J366 | 12/11/2024 | 01/13/2025 | 16 | 11 | 5 | 01/14/2025 | 01/14/2025 | 126 | 103 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 650232 | 01532 | 10 | Solar | 05_09_1109W3 | 10/28/2024 | 11/11/2024 | 5 | 0 | 5 | 11/12/2024 | 11/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/28/2024 | 1/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 429334 | 02301 | 15.2 | Solar | 05_07_97W2 | 05/09/2022 | 05/13/2022 | 3 | 3 | 0 | 05/16/2022 | 05/16/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 |  | 6/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2022 | Connected |  | N
National Grid | REHOBOTH | 668974 | 02769 | 0 | Battery Add-On | 05_07_915W36 | 01/30/2025 | 02/03/2025 | 2 | 0 | 2 | 02/04/2025 | 02/04/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | WORCESTER | 174289 | 01604 | 950 | Solar | 05_09_523L4 | 12/08/2011 | 12/08/2011 | 40 | 0 | 40 | 02/08/2012 | 02/08/2012 | 485 | 0 | 485 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 649472 | 01230 | 10 | Solar | 05_05_336W3 | 11/07/2024 | 11/21/2024 | 2 | 0 | 2 | 11/22/2024 | 11/22/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/07/2024 | 1/2/2026 | Y | EXP | 365 | 01/23/2025 | 02/13/2025 | 22 | 0 | 22 |  |  | 3/11/2025 | Connected |  | N
National Grid | RANDOLPH | 740691 | 02368 | 10 | Solar | 05_09_909W4 | 12/16/2025 | 12/17/2025 | 4 | 0 | 4 | 01/22/2026 | 01/22/2026 | 20 | 6 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SCITUATE | 553642 | 02066 | 120 | Solar | 05_05_314W4 | 09/11/2023 | 09/29/2023 | 14 | 5 | 9 | 10/02/2023 | 10/02/2023 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 | 09/11/2023 | 10/14/2025 | Y | EXP | 217 | 01/30/2025 | 01/20/2025 | 0 | 0 | 0 |  |  | 5/9/2025 | Connected |  | N
National Grid | PALMER | 234850 | 01069 | 7.6 | Solar | 05_07_797W19 | 04/29/2020 | 06/09/2020 | 27 | 26 | 1 | 06/10/2020 | 06/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 6/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 747606 | 01757 | 7.6 | Solar | 05_05_8L4 | 01/27/2026 | 01/29/2026 | 2 | 0 | 2 | 01/30/2026 | 01/30/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 661738 | 01062 | 7.68 | Solar | 05_01_10J366 | 12/20/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 650987 | 01532 | 5 | Solar | 05_09_1109W3 | 10/30/2024 | 11/11/2024 | 4 | 0 | 4 | 11/12/2024 | 11/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/30/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | BROCKTON | 438829 | 02301 | 6 | Solar | 05_07_97W2 | 06/27/2022 | 06/29/2022 | 2 | 0 | 2 | 06/30/2022 | 06/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/27/2022 | 6/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2025 | Connected |  | N
National Grid | REHOBOTH | 694473 | 02769 | 5.76 | Solar | 05_07_915W36 | 07/10/2025 | 08/15/2025 | 26 | 24 | 2 | 08/18/2025 | 08/18/2025 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | WORCESTER | 174288 | 01605 | 950 | Solar | 05_09_523L4 | 12/09/2011 | 12/09/2011 | 40 | 0 | 40 | 02/08/2012 | 02/08/2012 | 541 | 0 | 541 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 650647 | 01252 | 10 | Solar | 05_05_336W3 | 10/31/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2025 | Connected |  | N
National Grid | RANDOLPH | 742723 | 02368 | 120 | Solar | 05_09_909W4 | 12/31/2025 | 02/20/2026 | 33 | 23 | 10 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SCITUATE | 567577 | 02066 | 240 | Solar | 05_05_314W4 | 10/31/2023 |  | 97 | 27 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 245587 | 01069 | 7.6 | Solar | 05_07_797W19 | 07/31/2019 | 08/07/2019 | 4 | 4 | 0 | 08/08/2019 | 08/08/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 | 07/31/2019 | 12/31/2020 | Y | EXP | 365 | 09/02/2020 | 09/18/2020 | 16 | 0 | 16 |  |  | 10/17/2020 | Connected |  | N
National Grid | MILFORD | 747010 | 01757 | 10 | Solar | 05_05_8L4 | 01/23/2026 | 01/27/2026 | 2 | 0 | 2 | 01/28/2026 | 01/28/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTHAMPTON | 175212 | 01062 | 0 | Natural Gas | 05_01_10J383 | 12/07/2012 | 12/07/2012 | 12 | 7 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2012 | 02/20/2013 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2013 |  | 8/30/2013 | N | STD | 55 |  |  | 0 | 0 | 0 | 10/24/2013 | 10/24/2013 | 10/24/2013 | Terminated |  | N
National Grid | NORTHBOROUGH | 661710 | 01532 | 11.52 | Solar | 05_09_1109W3 | 12/19/2024 | 01/02/2025 | 9 | 5 | 4 | 01/03/2025 | 01/03/2025 | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | BROCKTON | 447515 | 02301 | 10 | Solar | 05_07_97W2 | 08/03/2022 | 08/09/2022 | 4 | 0 | 4 | 08/10/2022 | 08/10/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 |  | 9/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2022 | Connected |  | N
National Grid | ATTLEBORO | 698491 | 02703 | 20 | Solar | 05_07_915W36 | 06/13/2025 | 06/26/2025 | 6 | 4 | 2 | 06/27/2025 | 06/27/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | WORCESTER | 174652 | 01605 | 260 | Solar | 05_09_523L4 | 08/21/2012 | 08/21/2012 | 8 | 0 | 8 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2012 |  | 11/1/2012 | N | EXP | 4 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | N
National Grid | GREAT BARRINGTON | 657455 | 01230 | 3.8 | Solar | 05_05_336W3 | 11/27/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 745251 | 02368 | 10 | Solar | 05_09_909W4 | 01/14/2026 | 01/15/2026 | 3 | 1 | 2 | 01/29/2026 | 01/29/2026 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SCITUATE | 593596 | 02066 | 6.282 | Solar | 05_05_314W4 | 03/08/2024 | 03/13/2024 | 3 | 0 | 3 | 03/14/2024 | 03/14/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2024 | Connected |  | N
National Grid | PALMER | 246245 | 01069 | 100 | Solar | 05_07_797W19 | 07/31/2019 | 08/07/2019 | 4 | 1 | 3 | 08/08/2019 | 08/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 |  | 9/23/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 748264 | 01757 | 13.36 | Solar | 05_05_8L4 | 01/29/2026 | 02/02/2026 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTHAMPTON | 688095 | 01062 | 3.2 | Solar | 05_01_10J383 | 06/26/2025 | 07/11/2025 | 2 | 0 | 2 | 07/18/2025 | 07/18/2025 | 30 | 18 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2025 | 06/26/2025 | 9/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTHBOROUGH | 676888 | 01532 | 23 | Solar | 05_09_1109W3 | 03/21/2025 | 03/25/2025 | 2 | 0 | 2 | 03/26/2025 | 03/26/2025 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | BROCKTON | 468022 | 02301 | 6 | Solar | 05_07_97W2 | 12/05/2022 | 12/07/2022 | 2 | 0 | 2 | 12/08/2022 | 12/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 | 12/05/2022 | 4/13/2024 | Y | EXP | 365 | 04/12/2023 | 04/11/2023 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 710488 | 02769 | 0 | Battery Add-On | 05_07_915W36 | 10/06/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | WORCESTER | 175486 | 01605 | 4880 | Solar | 05_09_523L4 | 07/14/2014 | 07/14/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/24/2014 | 08/19/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 01/27/2015 | 03/04/2015 | 25 | 0 | 25 | 3/12/2015 | 07/14/2014 | 6/1/2016 | Y | STD | 447 |  |  | 0 | 0 | 0 | 12/21/2015 | 12/21/2015 | 12/22/2015 | Connected |  | N
National Grid | GREAT BARRINGTON | 664785 | 01230 | 11.5 | Solar | 05_05_336W3 | 01/09/2025 | 01/10/2025 | 1 | 0 | 1 | 01/13/2025 | 01/13/2025 | 113 | 33 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 174670 | 02368 | 200 | Natural Gas | 05_09_909W4 | 06/06/2013 | 06/06/2013 | 23 | 22 | 1 | 07/12/2013 | 07/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2013 |  | 11/29/2013 | N | EXP | 121 |  |  | 0 | 0 | 0 | 11/24/2015 | 11/24/2015 | 11/24/2015 | Connected |  | N
National Grid | SCITUATE | 621808 | 02066 | 11.5 | Solar | 05_05_314W4 | 07/01/2024 | 08/19/2024 | 9 | 4 | 5 | 08/20/2024 | 08/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 9/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | PALMER | 254306 | 01069 | 0 | Solar | 05_07_797W19 | 09/17/2019 | 09/17/2019 | 0 | 0 | 0 | 09/18/2019 | 09/18/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 | 09/17/2019 | 6/22/2020 | Y | EXP | 365 | 12/19/2019 | 01/14/2020 | 26 | 0 | 26 |  |  | 4/3/2020 | Connected |  | N
National Grid | MILFORD | 174866 | 01757 | 2000 | Solar | 05_05_8L4 | 08/02/2012 | 08/02/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2012 | 10/15/2012 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2013 | 08/02/2012 | 7/1/2013 | Y | STD | 42 | 10/17/2013 | 12/19/2013 | 43 | 0 | 43 | 12/16/2013 | 12/16/2013 | 12/23/2013 | Connected |  | N
National Grid | NORTHAMPTON | 718163 | 01062 | 10.88 | Solar | 05_01_10J383 | 09/13/2025 | 09/29/2025 | 32 | 26 | 6 | 12/23/2025 | 12/23/2025 | 47 | 31 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 677189 | 01581 | 7.6 | Solar | 05_09_1109W3 | 03/11/2025 | 03/19/2025 | 7 | 3 | 4 | 03/20/2025 | 03/20/2025 | 74 | 54 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 467533 | 02379 | 7.6 | Solar | 05_07_97W2 | 11/16/2022 | 11/18/2022 | 2 | 0 | 2 | 11/21/2022 | 11/21/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2022 |  | 2/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | REHOBOTH | 727094 | 02769 | 0 | Battery Add-On | 05_07_915W36 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 10/23/2025 | 10/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 11/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2026 | Connected |  | N
National Grid | WORCESTER | 175802 | 01604 | 4400 | Solar | 05_09_523L4 | 03/03/2015 | 03/03/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/08/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 | 03/03/2015 | 12/31/2016 | Y | STD | 446 | 09/02/2016 | 02/23/2017 | 116 | 0 | 116 |  |  | 12/30/2016 | Connected |  | N
National Grid | EGREMONT | 682310 | 01252 | 23 | Solar | 05_05_336W3 | 04/04/2025 | 04/11/2025 | 5 | 0 | 5 | 04/14/2025 | 04/14/2025 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 175909 | 02368 | 20 | Solar | 05_09_909W4 | 03/10/2015 | 03/10/2015 | 4 | 0 | 4 | 03/18/2015 | 03/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2015 |  | 7/31/2015 | N | EXP | 134 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 7/23/2015 | Connected |  | N
National Grid | SCITUATE | 657569 | 02066 | 5.76 | Solar | 05_05_314W4 | 11/28/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/28/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | WARE | 290955 | 01082 | 57.6 | Solar | 05_07_797W19 | 08/03/2020 | 08/13/2020 | 7 | 3 | 4 | 08/14/2020 | 08/14/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 3/7/2022 | N | EXP | 545 |  |  | 0 | 0 | 0 |  |  | 3/4/2022 | Connected |  | N
National Grid | MILFORD | 175839 | 01757 | 17.4 | Solar | 05_05_8L4 | 03/04/2015 | 03/04/2015 | 5 | 1 | 4 | 03/12/2015 | 03/12/2015 | 351 | 0 | 351 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2015 |  | 7/31/2015 | N | EXP | 14 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 733762 | 01062 | 7.6 | Solar | 05_01_10J383 | 11/13/2025 | 12/11/2025 | 10 | 9 | 1 | 01/12/2026 | 01/12/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 684139 | 01532 | 50 | Solar | 05_09_1109W3 | 04/09/2025 | 05/28/2025 | 32 | 22 | 10 | 05/29/2025 | 05/29/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | BROCKTON | 490321 | 02301 | 6 | Solar | 05_07_97W2 | 01/24/2023 | 01/27/2023 | 3 | 0 | 3 | 01/30/2023 | 01/30/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 | 01/24/2023 | 9/7/2024 | Y | EXP | 365 | 08/17/2023 | 09/01/2023 | 16 | 0 | 16 |  |  | 9/18/2023 | Connected |  | N
National Grid | ATTLEBORO | 676491 | 02703 | 24.99 | Solar | 05_07_915W37 | 05/06/2025 | 06/09/2025 | 23 | 20 | 3 | 06/10/2025 | 06/10/2025 | 124 | 110 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 176032 | 01604 | 499 | Solar | 05_09_523L4 | 06/19/2015 | 06/19/2015 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/02/2015 | 07/30/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/19/2015 | 6/24/2016 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 692666 | 01230 | 15.2 | Solar | 05_05_336W3 | 05/27/2025 | 06/24/2025 | 18 | 14 | 4 | 06/25/2025 | 06/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | RANDOLPH | 176099 | 02368 | 300 | Solar | 05_09_909W4 | 04/10/2015 | 04/10/2015 | 3 | 3 | 0 | 04/16/2015 | 04/16/2015 | 317 | 0 | 317 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 |  | 9/11/2015 | N | EXP | 143 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 663565 | 02066 | 10 | Solar | 05_05_314W4 | 01/03/2025 | 01/29/2025 | 12 | 8 | 4 | 01/30/2025 | 01/30/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 345964 | 01069 | 500 | Solar | 05_07_797W19 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 |  |  | 174 | 126 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 176040 | 01757 | 10 | Solar | 05_05_8L4 | 08/13/2015 | 08/13/2015 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/19/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 174271 | 01053 | 517 | Solar | 05_01_10J383 | 12/26/2011 | 12/26/2011 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 04/12/2012 | 06/22/2012 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  | 06/22/2012 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 5/16/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 697991 | 01532 | 22.8 | Solar | 05_09_1109W3 | 06/11/2025 | 06/13/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 25 | 7 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 | 06/11/2025 | 8/12/2026 | Y | EXP | 365 | 08/26/2025 | 09/23/2025 | 29 | 0 | 29 |  |  | 10/29/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 492308 | 02379 | 6 | Solar | 05_07_97W2 | 01/26/2023 | 01/27/2023 | 1 | 0 | 1 | 01/30/2023 | 01/30/2023 | 263 | 25 | 238 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 744191 | 02769 | 7.6 | Solar | 05_07_915W37 | 01/09/2026 | 01/13/2026 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 |  | 3/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 177148 | 01604 | 4 | Solar | 05_09_523L4 | 08/08/2016 | 08/08/2016 | 22 | 22 | 0 | 09/12/2016 | 09/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2016 | 08/08/2016 | 8/15/2017 | Y | EXP | 33 | 04/11/2017 | 05/11/2017 | 21 | 0 | 21 | 5/15/2017 | 5/15/2017 | 5/18/2017 | Connected |  | N
National Grid | STOCKBRIDGE | 693605 | 01266 | 15.2 | Solar | 05_05_336W3 | 05/29/2025 | 06/03/2025 | 3 | 0 | 3 | 06/04/2025 | 06/04/2025 | 35 | 22 | 13 | 08/12/2025 | 10/08/2025 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  | 10/08/2025 | 41 | 0 | 41 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 11/18/2026 | N | EXP | 365 | 12/30/2025 | 01/27/2026 | 29 | 0 | 29 |  |  | 2/21/2026 | Connected |  | N
National Grid | RANDOLPH | 176611 | 02368 | 488 | Solar | 05_09_909W4 | 02/12/2016 | 02/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2016 | 03/11/2016 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/20/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 695567 | 02066 | 15.2 | Solar | 05_05_314W4 | 06/04/2025 | 06/11/2025 | 4 | 1 | 3 | 06/12/2025 | 06/12/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | PALMER | 389732 | 01069 | 0 | Other | 05_07_797W19 | 11/10/2021 | 01/26/2022 | 51 | 42 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2022 | 02/02/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 176062 | 01568 | 28.8 | Solar | 05_05_8L4 | 03/31/2015 | 03/31/2015 | 4 | 1 | 3 | 04/07/2015 | 04/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2015 |  | 7/31/2015 | N | EXP | 114 |  |  | 0 | 0 | 0 | 9/23/2015 | 9/23/2015 | 9/28/2015 | Connected |  | N
National Grid | NORTHAMPTON | 176344 | 01062 | 8.39 | Solar | 05_01_10J383 | 02/25/2015 | 02/25/2015 | 9 | 5 | 4 | 03/11/2015 | 03/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2015 |  | 7/31/2015 | N | EXP | 141 |  |  | 0 | 0 | 0 | 3/12/2015 | 3/12/2015 | 1/13/2016 | Connected |  | N
National Grid | WESTBOROUGH | 707189 | 01581 | 15.2 | Solar | 05_09_1109W3 | 07/24/2025 | 07/30/2025 | 4 | 0 | 4 | 07/31/2025 | 07/31/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | BROCKTON | 519279 | 02301 | 9.984 | Solar | 05_07_97W2 | 06/16/2023 | 06/21/2023 | 2 | 1 | 1 | 06/22/2023 | 06/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 | 06/16/2023 | 12/6/2024 | Y | EXP | 365 | 10/26/2023 | 12/04/2023 | 40 | 0 | 40 |  |  | 12/29/2023 | Connected |  | N
National Grid | REHOBOTH | 174958 | 02769 | 85 | Solar | 05_07_915W37 | 02/28/2013 | 02/28/2013 | 3 | 0 | 3 | 03/11/2013 | 03/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2013 |  | 7/31/2013 | N | EXP | 58 |  |  | 0 | 0 | 0 | 12/12/2013 | 12/12/2013 | 12/27/2013 | Connected |  | N
National Grid | WORCESTER | 177311 | 01604 | 3468 | Solar | 05_09_523L4 | 02/09/2017 | 02/15/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2017 | 02/22/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2017 | 02/09/2017 | 10/1/2019 | Y | STD | 666 | 12/06/2018 | 02/21/2019 | 77 | 0 | 77 |  |  | 9/17/2019 | Connected |  | N
National Grid | EGREMONT | 695290 | 01252 | 5.76 | Solar | 05_05_336W3 | 05/30/2025 | 06/20/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | RANDOLPH | 176610 | 02368 | 2355 | Solar | 05_09_909W4 | 02/12/2016 | 02/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2016 | 03/11/2016 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2016 | 02/12/2016 | 10/31/2017 | Y | STD | 419 | 08/23/2017 | 10/12/2017 | 34 | 0 | 34 | 10/26/2017 | 10/26/2017 | 11/9/2017 | Connected |  | N
National Grid | COHASSET | 724347 | 02025 | 11.4 | Solar | 05_05_314W4 | 10/06/2025 | 10/14/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 1/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2026 | Connected |  | N
National Grid | PALMER | 412220 | 01079 | 0 | Battery Add-On | 05_07_797W19 | 03/04/2022 | 04/28/2022 | 38 | 29 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2022 | 05/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 176455 | 01568 | 7.6 | Solar | 05_05_8L4 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 | 12/08/2015 | 12/14/2016 | Y | EXP | 356 | 10/05/2016 | 10/11/2016 | 3 | 0 | 3 | 11/1/2016 | 11/1/2016 | 11/8/2016 | Connected |  | N
National Grid | NORTHAMPTON | 176587 | 01062 | 6 | Solar | 05_01_10J383 | 04/08/2016 | 04/08/2016 | 2 | 2 | 0 | 04/13/2016 | 04/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/08/2016 | 4/16/2017 | Y | EXP | 355 | 09/14/2016 | 10/03/2016 | 13 | 0 | 13 | 10/19/2016 | 10/19/2016 | 10/19/2016 | Connected |  | N
National Grid | NORTHBOROUGH | 719256 | 01532 | 22.8 | Solar | 05_09_1109W3 | 09/15/2025 | 09/19/2025 | 4 | 0 | 4 | 09/22/2025 | 09/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 10/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N
National Grid | BROCKTON | 517602 | 02301 | 3.8 | Solar | 05_07_97W2 | 04/24/2023 | 04/26/2023 | 2 | 0 | 2 | 04/27/2023 | 04/27/2023 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 04/24/2023 | 8/22/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2023 | Connected |  | N
National Grid | NORTON | 175771 | 02766 | 196 | Solar | 05_07_915W37 | 08/15/2014 | 08/15/2014 | 6 | 1 | 5 | 08/26/2014 | 08/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2014 |  | 12/31/2014 | N | EXP | 16 |  |  | 0 | 0 | 0 | 12/19/2014 | 12/19/2014 | 12/19/2014 | Connected |  | N
National Grid | WORCESTER | 177604 | 01604 | 7.6 | Solar | 05_09_523L4 | 07/19/2017 | 07/19/2017 | 6 | 0 | 6 | 07/28/2017 | 07/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2017 |  | 7/25/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 | 3/28/2018 | 3/28/2018 | 3/28/2018 | Connected |  | N
National Grid | STOCKBRIDGE | 697246 | 01266 | 11.4 | Solar | 05_05_336W3 | 06/09/2025 | 07/02/2025 | 11 | 6 | 5 | 08/04/2025 | 08/04/2025 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 | 06/09/2025 | 9/25/2026 | Y | EXP | 365 | 11/18/2025 | 01/17/2026 | 61 | 0 | 61 |  |  | 2/3/2026 | Connected |  | N
National Grid | RANDOLPH | 176633 | 02368 | 528 | Solar | 05_09_909W4 | 10/16/2015 | 10/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2015 | 11/13/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 175947 | 02025 | 336 | Solar | 05_05_314W5 | 03/17/2015 | 03/17/2015 | 2 | 1 | 1 | 03/20/2015 | 03/20/2015 | 410 | 13 | 397 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2015 |  | 8/17/2015 | N | EXP | 11 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 443983 | 01069 | 0 | Other | 05_07_797W19 | 11/09/2022 |  | 121 | 113 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 176625 | 01757 | 10 | Solar | 05_05_8L4 | 04/15/2016 | 04/15/2016 | 1 | 1 | 0 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2016 |  | 4/24/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 10/18/2016 | 10/18/2016 | 10/21/2016 | Connected |  | N
National Grid | NORTHAMPTON | 177001 | 01062 | 52.25 | Solar | 05_01_10J383 | 07/21/2016 | 07/21/2016 | 4 | 4 | 0 | 07/26/2016 | 07/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2016 | 07/21/2016 | 7/26/2017 | Y | EXP | 32 | 04/05/2017 | 04/19/2017 | 9 | 0 | 9 | 6/8/2017 | 6/8/2017 | 6/8/2017 | Connected |  | N
National Grid | NORTHBOROUGH | 693485 | 01532 | 240 | Solar | 05_09_139L1 | 05/23/2025 | 07/30/2025 | 45 | 35 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROCKTON | 559566 | 02301 | 6 | Solar | 05_07_97W2 | 10/25/2023 | 10/26/2023 | 1 | 0 | 1 | 10/27/2023 | 10/27/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 10/25/2023 | 1/22/2025 | Y | EXP | 365 | 03/14/2024 | 05/09/2024 | 57 | 0 | 57 |  |  | 6/8/2024 | Connected |  | N
National Grid | REHOBOTH | 310912 | 02769 | 6.67 | Solar | 05_07_915W37 | 09/15/2020 | 10/02/2020 | 13 | 13 | 0 | 10/05/2020 | 10/05/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 11/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2020 | Connected |  | N
National Grid | WORCESTER | 177956 | 01604 | 1980 | Solar | 05_09_523L4 | 10/23/2017 | 10/23/2017 | 104 | 100 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 699782 | 01252 | 23 | Solar | 05_05_336W3 | 06/23/2025 | 07/11/2025 | 1 | 0 | 1 | 07/17/2025 | 07/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 | 06/23/2025 | 8/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2026 | Connected |  | N
National Grid | RANDOLPH | 178174 | 02368 | 7.6 | Solar | 05_09_909W4 | 03/23/2018 | 03/23/2018 | 5 | 0 | 5 | 04/02/2018 | 04/02/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2018 |  | 3/31/2019 | N | EXP | 327 |  |  | 0 | 0 | 0 |  |  | 10/30/2019 | Connected |  | N
National Grid | SCITUATE | 176866 | 02066 | 1232 | Solar | 05_05_314W5 | 01/22/2016 | 01/22/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/26/2016 | 02/17/2016 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/27/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 443981 | 01069 | 0 | Other | 05_07_797W19 | 11/09/2022 | 01/31/2023 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2023 | 03/02/2023 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 177068 | 01757 | 15.2 | Solar | 05_05_8L4 | 03/21/2017 | 03/21/2017 | 7 | 6 | 1 | 03/30/2017 | 03/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2017 |  | 3/26/2018 | N | EXP | 36 |  |  | 0 | 0 | 0 | 9/21/2017 | 9/21/2017 | 9/26/2017 | Connected |  | N
National Grid | NORTHAMPTON | 177437 | 01062 | 8.6 | Solar | 05_01_10J383 | 06/30/2016 | 06/30/2016 | 2 | 2 | 0 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2016 | 06/30/2016 | 7/6/2017 | Y | EXP | 353 | 11/10/2016 | 12/02/2016 | 14 | 0 | 14 | 12/20/2016 | 12/20/2016 | 12/20/2016 | Connected |  | N
National Grid | NORTHBOROUGH | 717006 | 01532 | 5.76 | Solar | 05_09_139L1 | 09/05/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 09/05/2025 | 12/17/2026 | Y | EXP | 365 | 02/06/2026 | 02/12/2026 | 7 | 0 | 7 |  |  |  | Completion Documents |  | N
National Grid | WEST BRIDGEWATER | 550162 | 02379 | 10 | Solar | 05_07_97W2 | 08/29/2023 | 08/30/2023 | 1 | 0 | 1 | 08/31/2023 | 08/31/2023 | 41 | 16 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 08/29/2023 | 11/23/2024 | Y | EXP | 365 | 12/07/2023 | 02/17/2024 | 73 | 3 | 70 |  |  | 3/18/2024 | Connected |  | N
National Grid | REHOBOTH | 329626 | 02769 | 22.8 | Solar | 05_07_915W37 | 12/04/2020 | 12/10/2020 | 3 | 0 | 3 | 12/11/2020 | 12/11/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 | 12/04/2020 | 12/6/2021 | Y | EXP | 365 | 02/11/2021 | 03/17/2021 | 34 | 0 | 34 |  |  | 5/19/2021 | Connected |  | N
National Grid | WORCESTER | 178136 | 01604 | 15.2 | Solar | 05_09_523L4 | 03/22/2018 | 03/29/2018 | 4 | 4 | 0 | 03/29/2018 | 03/29/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2018 |  | 3/28/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 12/6/2019 | Connected |  | N
National Grid | EGREMONT | 699425 | 01258 | 17.4 | Solar | 05_05_336W3 | 06/24/2025 | 07/08/2025 | 3 | 0 | 3 | 07/09/2025 | 07/09/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 178385 | 02368 | 3.8 | Solar | 05_09_909W4 | 01/15/2018 | 01/15/2018 | 27 | 27 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 |  | 1/21/2019 | N | EXP | 214 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 196392 | 02066 | 496 | Solar | 05_05_314W5 | 09/19/2018 | 10/01/2018 | 5 | 2 | 3 |  |  | 73 | 51 | 22 |  |  | 0 | 0 | 0 | 10/02/2018 | 02/26/2019 | 97 | 57 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 479635 | 01082 | 8.064 | Solar | 05_07_797W19 | 03/07/2023 | 03/07/2023 | 0 | 0 | 0 | 03/08/2023 | 03/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 177099 | 01757 | 10 | Solar | 05_05_8L4 | 05/24/2016 | 05/24/2016 | 2 | 2 | 0 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/24/2016 | 5/30/2017 | Y | EXP | 358 | 08/24/2016 | 09/06/2016 | 8 | 0 | 8 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | NORTHAMPTON | 177683 | 01062 | 488 | Solar | 05_01_10J383 | 09/29/2017 | 09/29/2017 | 36 | 30 | 6 | 11/30/2017 | 11/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2018 |  | 10/23/2020 | N | EXP | 952 | 01/29/2020 | 04/16/2020 | 78 | 0 | 78 |  |  | 10/23/2020 | Connected |  | N
National Grid | WESTBOROUGH | 738830 | 01582 | 10 | Solar | 05_09_139L1 | 12/08/2025 | 12/10/2025 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEST BRIDGEWATER | 555021 | 02379 | 10 | Solar | 05_07_97W2 | 09/15/2023 | 09/18/2023 | 1 | 0 | 1 | 09/19/2023 | 09/19/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 338336 | 02769 | 466.6 | Solar | 05_07_915W37 | 02/08/2021 | 02/17/2021 | 5 | 0 | 5 | 02/18/2021 | 02/18/2021 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178373 | 01604 | 7.6 | Solar | 05_09_523L4 | 11/20/2017 | 11/20/2017 | 92 | 87 | 5 | 07/10/2018 | 07/10/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2018 |  | 11/26/2018 | N | EXP | 14 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 713903 | 01057 | 20 | Solar | 05_05_336W3 | 08/21/2025 | 08/22/2025 | 1 | 0 | 1 | 08/25/2025 | 08/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 10/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | RANDOLPH | 178658 | 02368 | 3564 | Solar | 05_09_909W4 | 02/05/2018 | 02/05/2018 | 21 | 21 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/08/2018 | 04/11/2018 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2018 | 02/05/2018 | 12/31/2020 | Y | STD | 773 | 05/08/2020 | 11/18/2020 | 195 | 5 | 190 | 11/20/2020 | 12/24/2020 | 12/31/2020 | Connected |  | N
National Grid | COHASSET | 201712 | 02025 | 7.6 | Solar | 05_05_314W5 | 11/20/2018 | 12/14/2018 | 4 | 0 | 4 | 12/17/2018 | 12/17/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2019 | 11/20/2018 | 4/14/2020 | Y | EXP | 467 | 11/13/2019 | 11/27/2019 | 14 | 0 | 14 |  |  | 1/14/2020 | Connected |  | N
National Grid | PALMER | 494818 | 01069 | 19 | Solar | 05_07_797W19 | 01/25/2023 | 01/31/2023 | 5 | 3 | 2 | 02/01/2023 | 02/01/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2023 |  | 3/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 177458 | 01568 | 15.2 | Solar | 05_05_8L4 | 12/07/2016 | 12/07/2016 | 1 | 1 | 0 | 12/12/2016 | 12/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2016 |  | 12/14/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 9/21/2017 | 9/21/2017 | 9/26/2017 | Connected |  | N
National Grid | NORTHAMPTON | 177950 | 01062 | 3.8 | Solar | 05_01_10J383 | 08/23/2017 | 08/23/2017 | 9 | 9 | 0 | 09/07/2017 | 09/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2017 |  | 8/24/2018 | N | EXP | 347 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/14/2017 | Connected |  | N
National Grid | WESTBOROUGH | 747782 | 01582 | 11.5 | Solar | 05_09_139L1 | 02/03/2026 | 02/10/2026 | 3 | 0 | 3 | 02/11/2026 | 02/11/2026 | 15 | 4 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BRIDGEWATER | 560567 | 02379 | 6.144 | Solar | 05_07_97W2 | 10/06/2023 | 10/12/2023 | 10 | 6 | 4 | 10/24/2023 | 10/24/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2023 | 10/06/2023 | 12/28/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2024 | Connected |  | N
National Grid | REHOBOTH | 343630 | 02769 | 499 | Solar | 05_07_915W37 | 05/13/2021 | 06/28/2021 | 31 | 20 | 11 |  |  | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 717214 | 01604 | 7.6 | Solar | 05_05_336W3 | 09/10/2025 | 09/25/2025 | 2 | 0 | 2 | 10/07/2025 | 10/07/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 178700 | 01036 | 4320 | Solar | 05_09_909W4 | 02/08/2018 | 04/09/2018 | 42 | 37 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2018 | 05/02/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 | 02/08/2018 | 12/17/2019 | Y | STD | 294 | 09/11/2019 | 11/19/2019 | 69 | 0 | 69 |  |  | 12/20/2019 | Connected |  | N
National Grid | RANDOLPH | 205806 | 02368 | 7.6 | Solar | 05_05_314W5 | 04/15/2019 | 06/12/2019 | 39 | 32 | 7 | 06/13/2019 | 06/13/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 | 04/15/2019 | 3/6/2020 | Y | EXP | 262 |  |  | 0 | 0 | 0 |  |  | 11/21/2019 | Connected |  | N
National Grid | COHASSET | 534311 | 02025 | 10 | Solar | 05_07_797W19 | 07/11/2023 | 07/12/2023 | 1 | 0 | 1 | 07/13/2023 | 07/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 9/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 177565 | 01079 | 7.6 | Solar | 05_05_8L4 | 07/14/2017 | 07/14/2017 | 2 | 2 | 0 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/22/2018 | N | EXP | 367 |  |  | 0 | 0 | 0 | 11/7/2017 | 11/7/2017 | 11/7/2017 | Connected |  | N
National Grid | MILFORD | 495040 | 01757 | 3.8 | Solar | 05_01_10J383 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2023 | Connected |  | N
National Grid | NORTHAMPTON | 175021 | 01062 | 3500 | Solar | 05_09_139L1 | 10/08/2012 | 10/08/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2012 | 12/03/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2014 | 10/08/2012 | 6/3/2013 | Y | STD | 231 |  |  | 0 | 0 | 0 | 7/24/2015 | 7/24/2015 | 7/31/2015 | Connected |  | N
National Grid | WESTBOROUGH | 562983 | 01582 | 9.765 | Solar | 05_07_97W2 | 12/04/2023 | 12/27/2023 | 16 | 13 | 3 | 12/28/2023 | 12/28/2023 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 | 12/04/2023 | 2/20/2025 | Y | EXP | 365 | 05/11/2024 | 05/14/2024 | 4 | 0 | 4 |  |  | 5/30/2024 | Connected |  | N
National Grid | BROCKTON | 343627 | 02301 | 500 | Solar | 05_07_915W37 | 05/13/2021 | 06/28/2021 | 31 | 20 | 11 |  |  | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 178491 | 02766 | 4000 | Solar | 05_09_523L4 | 12/01/2017 | 12/01/2017 | 41 | 40 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2018 | 02/28/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/9/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 676974 | 01604 | 999.9 | Solar | 05_05_336W4 | 04/08/2025 | 06/10/2025 | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LONGMEADOW | 187299 | 01028 | 10 | Solar | 05_09_909W4 | 06/06/2018 | 06/06/2018 | 3 | 3 | 0 | 09/19/2018 | 09/19/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2018 | 06/06/2018 | 4/17/2019 | Y | EXP | 25 |  |  | 0 | 0 | 0 |  |  | 11/21/2018 | Connected |  | N
National Grid | RANDOLPH | 650005 | 02368 | 0 | Other | 05_05_317W1 | 05/02/2025 | 07/11/2025 | 46 | 38 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 12/18/2025 | 110 | 92 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | COHASSET | 546935 | 02025 | 0 | Other | 05_07_797W19 | 03/21/2024 | 06/12/2024 | 57 | 47 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2024 | 07/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 177644 | 01082 | 4268 | Solar | 05_05_8L4 | 09/22/2017 | 09/22/2017 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2017 | 12/14/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 | 09/22/2017 | 12/11/2020 | Y | STD | 67 | 09/24/2019 | 11/19/2020 | 422 | 5 | 417 |  |  | 12/28/2020 | Connected |  | N
National Grid | MILFORD | 517558 | 01757 | 10 | Solar | 05_01_10J383 | 06/22/2023 | 04/26/2023 | 3 | 0 | 3 | 06/28/2023 | 06/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 176634 | 01060 | 527 | Solar | 05_09_139L1 | 10/16/2015 | 10/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2015 | 11/13/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 570882 | 01581 | 10 | Solar | 05_07_97W2 | 12/01/2023 | 12/06/2023 | 3 | 0 | 3 | 12/07/2023 | 12/07/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 12/01/2023 | 1/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2024 | Connected |  | Y
National Grid | BROCKTON | 440798 | 02301 | 9.86 | Solar | 05_07_915W37 | 07/19/2022 | 07/21/2022 | 2 | 0 | 2 | 07/22/2022 | 07/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2022 |  | 8/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2023 | Connected |  | N
National Grid | REHOBOTH | 192365 | 02769 | 7999 | Solar | 05_09_523L4 | 10/15/2018 | 11/09/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 | 01/08/2019 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 749435 | 01604 | 180 | Solar | 05_05_336W4 | 02/17/2026 |  | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | HAMPDEN | 201270 | 01036 | 3 | Solar | 05_09_909W4 | 11/15/2018 | 12/19/2018 | 7 | 0 | 7 | 12/20/2018 | 12/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2019 | 11/15/2018 | 1/13/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2019 | Connected |  | N
National Grid | RANDOLPH | 175356 | 02368 | 1200 | Bio Gas | 05_05_317W1 | 09/05/2014 | 09/05/2014 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/19/2014 | 10/20/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2014 |  | 12/31/2016 | N | STD | 738 |  |  | 0 | 0 | 0 | 12/22/2015 | 12/22/2015 | 12/22/2015 | Connected |  | N
National Grid | COHASSET | 564779 | 02025 | 6 | Solar | 05_07_797W19 | 11/01/2023 | 11/06/2023 | 3 | 0 | 3 | 11/07/2023 | 11/07/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  | 12/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2024 | Connected |  | N
National Grid | WARE | 177788 | 01082 | 7.6 | Solar | 05_05_8L4 | 06/02/2017 | 06/02/2017 | 13 | 13 | 0 | 06/21/2017 | 06/21/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2017 | 06/02/2017 | 6/7/2018 | Y | EXP | 349 | 08/24/2017 | 09/19/2017 | 17 | 0 | 17 | 9/19/2017 | 9/19/2017 | 9/27/2017 | Connected |  | N
National Grid | MILFORD | 520774 | 01757 | 6 | Solar | 05_01_10J383 | 05/03/2023 | 05/05/2023 | 2 | 0 | 2 | 05/08/2023 | 05/08/2023 | 108 | 25 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 177651 | 01062 | 2000 | Solar | 05_09_139L1 | 09/28/2017 | 09/28/2017 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 | 11/14/2017 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2017 | 09/28/2017 | 3/31/2021 | Y | STD | 15 |  |  | 0 | 0 | 0 | 11/20/2020 | 3/8/2021 | 3/30/2021 | Connected |  | N
National Grid | WESTBOROUGH | 576442 | 01581 | 10 | Solar | 05_07_97W2 | 12/08/2023 | 12/29/2023 | 15 | 12 | 3 | 01/02/2024 | 01/02/2024 | 36 | 14 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2024 | Connected |  | N
National Grid | BROCKTON | 461808 | 02301 | 230 | Solar | 05_07_915W37 | 10/14/2022 | 11/03/2022 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/04/2022 | 11/30/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 192328 | 02766 | 7.6 | Solar | 05_09_523L4 | 07/31/2018 | 11/07/2018 | 29 | 26 | 3 | 11/08/2018 | 11/08/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 | 07/31/2018 | 8/28/2019 | Y | EXP | 252 | 04/19/2019 | 04/18/2019 | 0 | 0 | 0 |  |  | 5/25/2019 | Connected |  | N
National Grid | WORCESTER | 174659 | 01604 | 250 | Solar | 05_05_336W4 | 12/03/2012 | 12/03/2012 | 12 | 4 | 8 | 12/21/2012 | 12/21/2012 | 309 | 0 | 309 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 |  | 5/1/2013 | N | EXP | 48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 203430 | 01036 | 0 | Battery Add-On | 05_09_909W4 | 12/17/2018 | 01/19/2019 | 22 | 14 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2019 | 02/18/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2019 | 12/17/2018 | 12/31/2020 | Y | STD | 365 | 05/08/2020 | 10/21/2020 | 167 | 5 | 162 |  |  | 12/23/2020 | Connected |  | N
National Grid | RANDOLPH | 176480 | 02368 | 75 | Solar | 05_05_317W1 | 05/19/2016 | 05/19/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2016 |  | 5/31/2019 | N | EXP | 129 |  |  | 0 | 0 | 0 |  |  | 7/2/2019 | Connected |  | N
National Grid | COHASSET | 561847 | 02025 | 7.6 | Solar | 05_07_797W19 | 10/24/2023 | 10/27/2023 | 3 | 1 | 2 | 10/30/2023 | 10/30/2023 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2023 |  | 12/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2024 | Connected |  | N
National Grid | PALMER | 189870 | 01069 | 10 | Solar | 05_05_8L4 | 07/05/2018 | 07/05/2018 | 8 | 8 | 0 | 08/14/2018 | 08/14/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  | 8/26/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2019 | Connected |  | N
National Grid | MILFORD | 551311 | 01757 | 4.93 | Solar | 05_01_10J383 | 08/28/2023 | 08/30/2023 | 3 | 2 | 1 | 08/31/2023 | 08/31/2023 | 42 | 20 | 22 | 11/07/2023 | 01/05/2024 | 40 | 3 | 37 |  |  | 0 | 0 | 0 |  | 01/05/2024 | 40 | 3 | 37 |  |  | 0 | 0 | 0 | 1/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 177854 | 01062 | 250 | Solar | 05_09_139L1 | 04/10/2017 | 04/10/2017 | 200 | 198 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/16/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 580555 | 01772 | 4.64 | Solar | 05_07_97W2 | 01/12/2024 | 01/18/2024 | 3 | 0 | 3 | 01/19/2024 | 01/19/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 471856 | 02379 | 13.34 | Solar | 05_07_915W37 | 03/20/2023 | 01/16/2024 | 205 | 195 | 10 | 01/17/2024 | 01/17/2024 | 37 | 16 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 | 03/20/2023 | 3/26/2025 | Y | EXP | 365 | 04/19/2024 | 04/22/2024 | 4 | 0 | 4 |  |  | 10/3/2024 | Connected |  | N
National Grid | ATTLEBORO | 214399 | 02703 | 15.2 | Solar | 05_09_523L4 | 03/19/2019 | 03/28/2019 | 6 | 0 | 6 | 03/29/2019 | 03/29/2019 | 66 | 38 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175322 | 01604 | 301.6 | Solar | 05_05_336W4 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 12/23/2014 | 12/23/2014 | 12/31/2014 | Connected |  | N
National Grid | LONGMEADOW | 205909 | 01028 | 9.71 | Solar | 05_09_909W4 | 02/01/2019 | 02/13/2019 | 8 | 7 | 1 | 02/14/2019 | 02/14/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 176631 | 02368 | 75 | Solar | 05_05_317W1 | 10/16/2015 | 10/16/2015 | 3 | 3 | 0 | 10/23/2015 | 10/23/2015 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 625688 | 02025 | 3.8 | Solar | 05_07_797W19 | 07/17/2024 | 07/29/2024 | 0 | 0 | 0 | 07/30/2024 | 07/30/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2024 | Connected |  | N
National Grid | PALMER | 195799 | 01069 | 6 | Solar | 05_05_8L4 | 11/10/2018 | 11/16/2018 | 3 | 3 | 0 | 11/19/2018 | 11/19/2018 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 | 11/10/2018 | 5/23/2019 | Y | EXP | 156 | 03/20/2019 | 03/19/2019 | 0 | 0 | 0 |  |  | 3/29/2019 | Connected |  | N
National Grid | MILFORD | 553055 | 01757 | 10 | Solar | 05_01_10J383 | 09/07/2023 | 09/20/2023 | 9 | 7 | 2 | 09/21/2023 | 09/21/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 177853 | 01062 | 250 | Solar | 05_09_139L1 | 04/10/2017 | 04/10/2017 | 200 | 198 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/16/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 581836 | 01752 | 5.51 | Solar | 05_07_97W2 | 01/19/2024 | 01/22/2024 | 1 | 0 | 1 | 01/23/2024 | 01/23/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 488438 | 02301 | 0 | Solar | 05_07_915W37 | 01/03/2023 | 01/05/2023 | 2 | 0 | 2 | 01/06/2023 | 01/06/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2023 |  | 9/30/2024 | N | EXP | 47 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 217150 | 02769 | 7.6 | Solar | 05_09_523L4 | 04/03/2019 |  | 321 | 25 | 296 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/6/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176441 | 01604 | 206 | Solar | 05_05_336W4 | 05/10/2016 | 05/10/2016 | 1 | 1 | 0 | 05/13/2016 | 05/13/2016 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/17/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 234095 | 01036 | 10 | Solar | 05_09_909W4 | 07/01/2019 | 07/02/2019 | 0 | 0 | 0 | 07/03/2019 | 07/03/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2019 |  | 11/15/2019 | N | EXP | 129 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N
National Grid | RANDOLPH | 176857 | 02368 | 75 | Solar | 05_05_317W1 | 01/19/2016 | 01/19/2016 | 0 | 0 | 0 | 01/19/2016 | 01/19/2016 | 166 | 0 | 166 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/24/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 640558 | 02066 | 7.22 | Solar | 05_07_797W19 | 09/16/2024 | 10/04/2024 | 4 | 1 | 3 | 10/07/2024 | 10/07/2024 | 59 | 38 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2025 | Connected |  | N
National Grid | PALMER | 192159 | 01069 | 10 | Solar | 05_05_8L4 | 07/30/2018 | 09/05/2018 | 19 | 16 | 3 | 09/06/2018 | 09/06/2018 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 |  | 11/1/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2019 | Connected |  | N
National Grid | MILFORD | 569102 | 01757 | 10 | Solar | 05_01_10J383 | 11/14/2023 | 11/16/2023 | 2 | 0 | 2 | 11/17/2023 | 11/17/2023 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 177852 | 01062 | 250 | Solar | 05_09_139L1 | 04/10/2017 | 04/10/2017 | 200 | 198 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/16/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 586650 | 01752 | 8.7 | Solar | 05_07_97W2 | 02/07/2024 | 02/09/2024 | 2 | 0 | 2 | 02/12/2024 | 02/12/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/07/2024 | 3/1/2025 | Y | EXP | 365 | 03/30/2024 | 04/17/2024 | 19 | 0 | 19 |  |  | 5/14/2024 | Connected |  | N
National Grid | BROCKTON | 645050 | 02301 | 9.1 | Solar | 05_07_915W37 | 10/05/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2025 | Connected |  | N
National Grid | ATTLEBORO | 271476 | 02703 | 6.72 | Solar | 05_09_523L4 | 01/02/2020 | 02/24/2020 | 37 | 36 | 1 | 02/25/2020 | 02/25/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2020 |  | 1/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2020 | Connected |  | N
National Grid | WORCESTER | 176734 | 01604 | 206 | Solar | 05_05_336W4 | 04/26/2016 | 04/26/2016 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/2/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 260373 | 01057 | 8.41 | Solar | 05_09_909W4 | 10/29/2019 | 11/05/2019 | 4 | 0 | 4 | 11/06/2019 | 11/06/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 | 10/29/2019 | 10/29/2020 | Y | EXP | 365 | 05/16/2020 | 05/15/2020 | 0 | 0 | 0 |  |  | 5/21/2020 | Connected |  | N
National Grid | RANDOLPH | 177517 | 02368 | 75 | Solar | 05_05_317W1 | 06/23/2016 | 06/23/2016 | 5 | 0 | 5 | 06/30/2016 | 06/30/2016 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 642255 | 02025 | 5.76 | Solar | 05_07_797W19 | 09/23/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/23/2024 | 12/3/2025 | Y | EXP | 365 | 02/26/2025 | 05/16/2025 | 80 | 0 | 80 |  |  | 6/5/2025 | Connected |  | N
National Grid | PALMER | 196777 | 01079 | 4998 | Solar | 05_05_8L4 | 11/06/2018 | 11/21/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2018 | 01/09/2019 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 607592 | 01757 | 4.225 | Solar | 05_01_10J383 | 05/08/2024 | 05/31/2024 | 6 | 5 | 1 | 06/03/2024 | 06/03/2024 | 51 | 38 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | NORTHAMPTON | 177851 | 01062 | 250 | Solar | 05_09_139L1 | 04/10/2017 | 04/10/2017 | 200 | 198 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/16/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 586576 | 01752 | 7.25 | Solar | 05_07_97W2 | 02/07/2024 | 02/14/2024 | 5 | 0 | 5 | 02/15/2024 | 02/15/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/07/2024 | 3/15/2025 | Y | EXP | 365 | 08/29/2024 | 09/30/2024 | 33 | 0 | 33 |  |  | 10/10/2024 | Connected |  | N
National Grid | BRIDGEWATER | 723924 | 02379 | 15.76 | Solar | 05_07_915W37 | 10/03/2025 | 10/09/2025 | 4 | 0 | 4 | 10/10/2025 | 10/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2026 | Connected |  | N
National Grid | ATTLEBORO | 317367 | 02703 | 187.5 | Solar | 05_09_523L4 | 10/07/2020 | 11/19/2020 | 28 | 24 | 4 | 11/20/2020 | 11/20/2020 | 63 | 43 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177077 | 01604 | 206 | Solar | 05_05_336W4 | 05/10/2016 | 05/10/2016 | 1 | 0 | 1 | 05/13/2016 | 05/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2016 | 05/10/2016 | 12/30/2016 | Y | EXP | 137 | 11/10/2016 | 12/28/2016 | 31 | 0 | 31 | 12/28/2016 | 12/28/2016 | 1/10/2017 | Connected |  | N
National Grid | MONSON | 265140 | 01057 | 0 | Solar | 05_09_909W4 | 11/24/2019 | 12/03/2019 | 5 | 0 | 5 | 12/04/2019 | 12/04/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2020 |  | 11/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2020 | Connected |  | N
National Grid | RANDOLPH | 178234 | 02368 | 1200 | Landfill Gas | 05_05_317W1 | 01/08/2018 | 01/08/2018 | 36 | 3 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/01/2018 | 04/13/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/13/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 656078 | 02066 | 4.55 | Solar | 05_07_797W19 | 11/21/2024 | 12/09/2024 | 5 | 0 | 5 | 12/10/2024 | 12/10/2024 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | PALMER | 205992 | 01079 | 7.6 | Solar | 05_05_8L4 | 01/15/2019 | 01/30/2019 | 9 | 0 | 9 | 01/31/2019 | 01/31/2019 | 178 | 0 | 178 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 607705 | 01757 | 3.19 | Solar | 05_01_10J383 | 04/30/2024 | 05/06/2024 | 1 | 0 | 1 | 05/07/2024 | 05/07/2024 | 86 | 71 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 177878 | 01062 | 250 | Solar | 05_09_139L1 | 10/17/2017 | 10/17/2017 | 15 | 0 | 15 | 11/09/2017 | 11/09/2017 | 19 | 0 | 19 | 02/22/2018 | 03/22/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 03/22/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 6/27/2018 | 10/17/2017 | 9/11/2020 | Y | EXP | 492 | 07/26/2019 | 08/03/2020 | 372 | 0 | 372 |  |  | 9/10/2020 | Connected |  | N
National Grid | MARLBOROUGH | 587494 | 01752 | 7.6 | Solar | 05_07_97W2 | 02/12/2024 | 02/15/2024 | 3 | 0 | 3 | 02/16/2024 | 02/16/2024 | 5 | 0 | 5 | 03/22/2024 | 02/12/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 02/12/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 5/3/2024 |  | 5/22/2025 | N | EXP | 365 | 06/13/2024 | 10/09/2024 | 119 | 0 | 119 |  |  | 11/7/2024 | Connected |  | N
National Grid | BROCKTON | 177080 | 02301 | 312 | Solar | 05_07_915W82 | 10/18/2016 | 10/18/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2016 | 01/23/2017 | 59 | 43 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2018 | 10/18/2016 | 11/8/2021 | Y | STD | 225 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 322772 | 02703 | 10 | Solar | 05_09_523L4 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/10/2020 | 3/20/2022 | Y | EXP | 365 | 07/02/2021 | 09/10/2021 | 68 | 3 | 65 |  |  | 10/15/2021 | Connected |  | Y
National Grid | WORCESTER | 177935 | 01604 | 34.2 | Solar | 05_05_336W4 | 06/20/2017 | 06/20/2017 | 143 | 143 | 0 | 01/24/2018 | 01/24/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2018 |  | 6/25/2018 | N | EXP | 152 |  |  | 0 | 0 | 0 |  |  | 4/27/2018 | Connected |  | N
National Grid | MONSON | 284382 | 01057 | 10 | Solar | 05_09_909W4 | 03/26/2020 | 04/08/2020 | 8 | 8 | 0 | 04/09/2020 | 04/09/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2020 |  | 4/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2020 | Connected |  | N
National Grid | RANDOLPH | 178387 | 02368 | 10 | Solar | 05_05_317W1 | 01/16/2018 | 01/16/2018 | 16 | 0 | 16 | 02/08/2018 | 02/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 |  | 1/22/2019 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  | 6/1/2018 | Connected |  | N
National Grid | SCITUATE | 673546 | 02066 | 3.8 | Solar | 05_07_797W19 | 03/07/2025 | 03/12/2025 | 3 | 0 | 3 | 03/13/2025 | 03/13/2025 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 209085 | 01082 | 3.8 | Solar | 05_05_8L4 | 03/12/2019 | 03/21/2019 | 6 | 0 | 6 | 03/22/2019 | 03/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 631126 | 01757 | 5.76 | Solar | 05_01_10J383 | 08/08/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 53 | 25 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 177979 | 01062 | 7.6 | Solar | 05_09_139L1 | 06/28/2017 | 06/28/2017 | 5 | 5 | 0 | 07/06/2017 | 07/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2017 |  | 7/3/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | MARLBOROUGH | 590155 | 01752 | 7.6 | Solar | 05_07_97W2 | 02/23/2024 | 04/11/2024 | 34 | 25 | 9 | 04/12/2024 | 04/12/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 | 02/23/2024 | 5/3/2025 | Y | EXP | 365 | 10/05/2024 | 11/22/2024 | 49 | 0 | 49 |  |  | 12/3/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 215949 | 02379 | 0 | Solar | 05_07_915W82 | 03/29/2019 | 04/05/2019 | 4 | 0 | 4 | 04/08/2019 | 04/08/2019 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2019 | Connected |  | N
National Grid | REHOBOTH | 348872 | 02769 | 0 | Other | 05_09_523L4 | 04/23/2021 | 05/09/2021 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2021 | 06/08/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 273779 | 01604 | 60 | Solar | 05_05_336W4 | 01/23/2020 | 02/06/2020 | 9 | 5 | 4 | 02/07/2020 | 02/07/2020 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2020 |  | 6/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 287922 | 01057 | 2.4 | Solar | 05_09_909W4 | 05/29/2020 | 06/01/2020 | 0 | 0 | 0 | 06/02/2020 | 06/02/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/29/2020 | 6/1/2021 | Y | EXP | 365 | 10/08/2020 | 10/21/2020 | 13 | 0 | 13 |  |  | 11/10/2020 | Connected |  | N
National Grid | RANDOLPH | 193382 | 02368 | 3.8 | Solar | 05_05_317W1 | 08/14/2018 | 08/31/2018 | 2 | 2 | 0 | 09/04/2018 | 09/04/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 692435 | 02025 | 3.8 | Solar | 05_07_797W19 | 05/23/2025 | 06/27/2025 | 2 | 0 | 2 | 06/30/2025 | 06/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 304219 | 01069 | 6.96 | Solar | 05_05_8L4 | 07/30/2020 | 08/12/2020 | 8 | 8 | 0 | 08/13/2020 | 08/13/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 |  | 8/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2020 | Connected |  | N
National Grid | MILFORD | 641898 | 01757 | 5.76 | Solar | 05_01_10J383 | 11/06/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 40 | 17 | 23 | 01/30/2025 | 03/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 03/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/06/2024 | 4/12/2026 | Y | EXP | 365 | 04/03/2025 | 07/25/2025 | 114 | 0 | 114 |  |  | 9/10/2025 | Connected |  | Y
National Grid | NORTHAMPTON | 178122 | 01062 | 3480 | Solar | 05_09_139L1 | 05/12/2017 | 05/12/2017 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2017 | 08/03/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2018 |  | 7/5/2019 | N | STD | 449 | 04/13/2019 | 10/15/2019 | 185 | 0 | 185 |  |  | 11/27/2019 | Connected |  | N
National Grid | MARLBOROUGH | 589671 | 01752 | 9.57 | Solar | 05_07_97W2 | 02/27/2024 | 02/28/2024 | 1 | 0 | 1 | 02/29/2024 | 02/29/2024 | 94 | 25 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 260128 | 02379 | 9.86 | Solar | 05_07_915W82 | 10/18/2019 | 10/27/2019 | 5 | 0 | 5 | 10/28/2019 | 10/28/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 |  | 10/18/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2020 | Connected |  | N
National Grid | REHOBOTH | 348867 | 02769 | 0 | Other | 05_09_523L4 | 04/23/2021 | 05/09/2021 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2021 | 06/08/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 340729 | 01604 | 466.6 | Solar | 05_05_336W4 | 02/19/2021 | 03/05/2021 | 10 | 0 | 10 |  |  | 93 | 66 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 02/19/2021 | 7/29/2025 | Y | STD | 38 | 01/28/2025 | 03/03/2025 | 35 | 0 | 35 |  |  | 7/3/2025 | Connected |  | N
National Grid | MONSON | 303203 | 01057 | 9.12 | Solar | 05_09_909W4 | 08/05/2020 | 08/11/2020 | 3 | 0 | 3 | 08/12/2020 | 08/12/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/05/2020 | 5/3/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2021 | Connected |  | N
National Grid | RANDOLPH | 421420 | 02368 | 0 | Solar | 05_05_317W1 | 12/07/2022 | 12/19/2022 | 8 | 7 | 1 | 12/20/2022 | 12/20/2022 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  | 3/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2023 | Connected |  | N
National Grid | SCITUATE | 521068 | 02066 | 495.7 | Solar | 05_07_797W20 | 11/02/2023 | 01/19/2024 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2024 | 02/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 325845 | 01082 | 15.2 | Solar | 05_05_8L4 | 11/13/2020 | 11/18/2020 | 2 | 0 | 2 | 11/19/2020 | 11/19/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 11/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2021 | Connected |  | N
National Grid | MILFORD | 648562 | 01757 | 5.76 | Solar | 05_01_10J383 | 10/21/2024 | 11/12/2024 | 4 | 0 | 4 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/21/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 178328 | 01062 | 8980 | Solar | 05_09_139L1 | 03/30/2018 | 03/30/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/19/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/4/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 591319 | 01772 | 7.6 | Solar | 05_07_97W2 | 03/06/2024 | 04/17/2024 | 27 | 25 | 2 | 04/18/2024 | 04/18/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 291812 | 02301 | 11.4 | Solar | 05_07_915W82 | 05/13/2020 | 06/16/2020 | 22 | 17 | 5 | 06/17/2020 | 06/17/2020 | 148 | 130 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2021 |  | 3/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2022 | Connected |  | N
National Grid | ATTLEBORO | 357047 | 02703 | 10 | Solar | 05_09_523L4 | 05/07/2021 | 05/19/2021 | 7 | 7 | 0 | 05/20/2021 | 05/20/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2021 |  | 7/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2021 | Connected |  | N
National Grid | WORCESTER | 340727 | 01604 | 466.6 | Solar | 05_05_336W4 | 02/19/2021 | 03/05/2021 | 9 | 0 | 9 |  |  | 93 | 70 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 325868 | 01057 | 15.2 | Solar | 05_09_909W4 | 11/13/2020 | 11/17/2020 | 1 | 0 | 1 | 11/18/2020 | 11/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/13/2020 | 12/12/2022 | Y | EXP | 365 | 03/06/2021 | 04/06/2021 | 31 | 0 | 31 |  |  | 3/8/2022 | Connected |  | N
National Grid | RANDOLPH | 610366 | 02368 | 10.15 | Solar | 05_05_317W1 | 05/20/2024 | 06/24/2024 | 5 | 2 | 3 | 06/25/2024 | 06/25/2024 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  | 10/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2024 | Connected |  | N
National Grid | SCITUATE | 581189 | 02066 | 240 | Solar | 05_07_797W20 | 01/09/2024 | 01/16/2024 | 4 | 0 | 4 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | PALMER | 385414 | 01069 | 9.8 | Solar | 05_05_8L4 | 11/02/2021 | 12/15/2021 | 1 | 0 | 1 | 11/04/2021 | 11/04/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 688082 | 01757 | 7.475 | Solar | 05_01_10J383 | 04/28/2025 | 05/13/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2025 | Connected |  | Y
National Grid | NORTHAMPTON | 178461 | 01062 | 3875 | Solar | 05_09_139L1 | 01/19/2018 | 01/19/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2018 | 04/20/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2019 | 01/19/2018 | 11/30/2022 | Y | STD | 252 | 01/14/2022 | 11/21/2022 | 312 | 0 | 312 |  |  | 11/30/2022 | Connected |  | N
National Grid | WESTBOROUGH | 595756 | 01581 | 10 | Solar | 05_07_97W2 | 03/14/2024 | 03/15/2024 | 1 | 0 | 1 | 03/18/2024 | 03/18/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 | 03/14/2024 | 3/25/2025 | Y | EXP | 365 | 10/03/2024 | 11/01/2024 | 30 | 0 | 30 |  |  | 11/9/2024 | Connected |  | N
National Grid | BROCKTON | 317813 | 02301 | 15.2 | Solar | 05_07_915W82 | 10/07/2020 | 10/09/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 10/07/2020 | 2/27/2022 | Y | EXP | 365 | 01/14/2021 | 01/27/2021 | 13 | 0 | 13 |  |  | 12/20/2021 | Connected |  | N
National Grid | REHOBOTH | 358673 | 02769 | 10 | Solar | 05_09_523L4 | 06/15/2021 | 12/03/2021 | 12 | 4 | 8 | 07/02/2021 | 07/02/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2021 |  | 9/30/2022 | N | EXP | 365 | 09/17/2021 | 09/29/2021 | 13 | 0 | 13 |  |  | 1/19/2022 | Connected |  | Y
National Grid | WORCESTER | 343062 | 01604 | 233.2 | Solar | 05_05_336W4 | 02/19/2021 | 03/05/2021 | 10 | 0 | 10 |  |  | 93 | 70 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 02/19/2021 | 6/6/2025 | Y | STD | 38 | 04/03/2025 | 04/21/2025 | 19 | 0 | 19 |  |  | 7/16/2025 | Connected |  | N
National Grid | HAMPDEN | 330696 | 01036 | 7.6 | Solar | 05_09_909W4 | 12/09/2020 | 12/17/2020 | 5 | 0 | 5 | 12/18/2020 | 12/18/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 |  | 3/6/2022 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 660358 | 02368 | 16.8 | Solar | 05_05_317W1 | 01/22/2025 | 01/27/2025 | 3 | 0 | 3 | 01/28/2025 | 01/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 01/22/2025 | 3/14/2026 | Y | EXP | 365 | 12/05/2025 | 12/04/2025 | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | SCITUATE | 676982 | 02066 | 750 | Solar | 05_07_797W20 | 04/08/2025 | 06/27/2025 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2025 | 07/23/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PALMER | 391863 | 01069 | 15.2 | Solar | 05_05_8L4 | 11/01/2021 | 11/09/2021 | 6 | 5 | 1 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 722399 | 01757 | 13.3 | Solar | 05_01_11J330 | 09/26/2025 | 10/15/2025 | 1 | 0 | 1 | 10/17/2025 | 10/17/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | NORTHAMPTON | 178597 | 01062 | 2500 | Solar | 05_09_139L1 | 04/06/2018 | 04/06/2018 | 9 | 8 | 1 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  | 9/30/2020 | N | STD | 595 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 601570 | 01772 | 7.6 | Solar | 05_07_97W2 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 341765 | 02379 | 15.2 | Solar | 05_07_915W82 | 02/11/2021 | 03/05/2021 | 14 | 13 | 1 | 03/08/2021 | 03/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 428299 | 02769 | 15.2 | Solar | 05_09_523L4 | 05/04/2022 | 05/12/2022 | 6 | 6 | 0 | 05/13/2022 | 05/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2022 |  | 6/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2023 | Connected |  | N
National Grid | WORCESTER | 391850 | 01604 | 0 | Other | 05_05_336W4 | 12/16/2021 | 01/05/2022 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 11/22/2022 | 221 | 213 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 354333 | 01036 | 10 | Solar | 05_09_909W4 | 04/23/2021 | 04/26/2021 | 0 | 0 | 0 | 04/27/2021 | 04/27/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2021 | Connected |  | N
National Grid | RANDOLPH | 174312 | 02368 | 333 | Solar | 05_05_317W2 | 12/21/2011 | 12/21/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2012 | 03/26/2012 | 0 | 0 | 0 | 4/2/2012 |  | 6/8/2012 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/12/2012 | 9/12/2012 | 9/17/2012 | Connected |  | N
National Grid | SCITUATE | 683042 | 02066 | 10 | Solar | 05_07_797W20 | 04/07/2025 | 04/30/2025 | 1 | 0 | 1 | 05/01/2025 | 05/01/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WARE | 416885 | 01082 | 15.2 | Solar | 05_05_8L4 | 03/10/2022 | 03/11/2022 | 1 | 0 | 1 | 03/14/2022 | 03/14/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 |  | 3/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2022 | Connected |  | N
National Grid | MILFORD | 177844 | 01757 | 17.6 | Solar | 05_01_11J330 | 10/17/2017 | 10/17/2017 | 53 | 53 | 0 | 01/17/2018 | 01/17/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2018 |  | 10/24/2018 | N | EXP | 279 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 178664 | 01062 | 3818 | Solar | 05_09_139L1 | 03/16/2018 | 04/16/2018 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/11/2018 | 40 | 20 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2018 | 03/16/2018 | 12/31/2024 | Y | STD | 675 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | WESTBOROUGH | 607477 | 01581 | 10 | Solar | 05_07_97W2 | 05/01/2024 | 07/15/2024 | 45 | 42 | 3 | 07/16/2024 | 07/16/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 344708 | 02333 | 7.68 | Solar | 05_07_915W82 | 03/02/2021 | 03/08/2021 | 3 | 0 | 3 | 03/09/2021 | 03/09/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 489441 | 02703 | 3.8 | Solar | 05_09_523L4 | 03/09/2023 | 03/16/2023 | 5 | 0 | 5 | 03/17/2023 | 03/17/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2023 |  | 4/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2023 | Connected |  | N
National Grid | WORCESTER | 401110 | 01604 | 0 | Other | 05_05_336W4 | 01/05/2022 | 02/04/2022 | 21 | 13 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2022 | 11/22/2022 | 199 | 199 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 378064 | 01036 | 3.8 | Solar | 05_09_909W4 | 09/09/2021 | 09/14/2021 | 3 | 0 | 3 | 09/15/2021 | 09/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 175038 | 02368 | 100 | Solar | 05_05_317W2 | 09/22/2013 | 09/22/2013 | 7 | 0 | 7 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2013 |  | 12/31/2013 | N | EXP | 6 |  |  | 0 | 0 | 0 | 11/8/2013 | 11/8/2013 | 1/8/2014 | Connected |  | N
National Grid | SCITUATE | 695308 | 02066 | 9.772 | Solar | 05_07_797W20 | 02/02/2026 | 02/20/2026 | 13 | 11 | 2 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PALMER | 424932 | 01069 | 7.6 | Solar | 05_05_8L4 | 04/19/2022 |  | 86 | 69 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 646198 | 01757 | 3.8 | Solar | 05_01_11J330 | 10/10/2024 | 02/17/2025 | 83 | 83 | 0 | 02/18/2025 | 02/18/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 184311 | 01062 | 7.6 | Solar | 05_09_139L1 | 07/15/2018 | 08/14/2018 | 21 | 0 | 21 | 08/15/2018 | 08/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 615043 | 01772 | 3.8 | Solar | 05_07_97W2 | 06/04/2024 | 06/12/2024 | 1 | 0 | 1 | 06/13/2024 | 06/13/2024 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 | 06/04/2024 | 8/28/2025 | Y | EXP | 365 | 09/05/2024 | 09/06/2024 | 2 | 0 | 2 |  |  | 11/6/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 358914 | 02379 | 9.8 | Solar | 05_07_915W82 | 05/18/2021 | 05/20/2021 | 1 | 1 | 0 | 05/21/2021 | 05/21/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2021 |  | 5/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2021 | Connected |  | N
National Grid | NORTON | 614250 | 02766 | 2.32 | Solar | 05_09_523L4 | 05/30/2024 | 06/06/2024 | 1 | 0 | 1 | 06/07/2024 | 06/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 05/30/2024 | 7/1/2025 | Y | EXP | 365 | 08/01/2024 | 08/28/2024 | 28 | 0 | 28 |  |  | 9/27/2024 | Connected |  | N
National Grid | WORCESTER | 422048 | 01605 | 0 | Battery Add-On | 05_05_336W4 | 07/28/2022 | 08/10/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 379683 | 01036 | 0 | Other | 05_09_909W4 | 09/02/2021 |  | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 189707 | 02368 | 472.5 | Natural Gas | 05_05_317W2 | 07/03/2018 | 07/03/2018 | 33 | 24 | 9 |  |  | 24 | 0 | 24 | 10/19/2018 | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 10/30/2019 |  | 12/31/2019 | N | STD | 41 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N
National Grid | SCITUATE | 735664 | 02066 | 5.76 | Solar | 05_07_797W20 | 11/21/2025 | 11/24/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | PALMER | 440304 | 01069 | 15.2 | Solar | 05_05_8L4 | 06/27/2022 | 06/29/2022 | 2 | 0 | 2 | 06/30/2022 | 06/30/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 |  | 9/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2022 | Connected |  | N
National Grid | MILFORD | 652361 | 01757 | 9.12 | Solar | 05_01_11J330 | 11/05/2024 | 11/25/2024 | 7 | 5 | 2 | 11/26/2024 | 11/26/2024 | 71 | 47 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 11/05/2024 | 4/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2025 | Connected |  | N
National Grid | NORTHAMPTON | 199336 | 01062 | 7.6 | Solar | 05_09_139L1 | 11/07/2018 | 03/18/2019 | 88 | 84 | 4 | 03/19/2019 | 03/19/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2019 |  | 11/8/2019 | N | EXP | 228 |  |  | 0 | 0 | 0 |  |  | 10/11/2019 | Connected |  | N
National Grid | MARLBOROUGH | 618878 | 01752 | 7.6 | Solar | 05_07_97W2 | 06/18/2024 | 07/03/2024 | 1 | 0 | 1 | 07/05/2024 | 07/05/2024 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2024 | 06/18/2024 | 8/6/2025 | Y | EXP | 365 | 12/12/2024 | 03/14/2025 | 93 | 0 | 93 |  |  | 4/8/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 375299 | 02379 | 21.17 | Solar | 05_07_915W82 | 08/11/2021 | 08/13/2021 | 3 | 2 | 1 | 08/16/2021 | 08/16/2021 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2021 | Connected |  | N
National Grid | REHOBOTH | 660815 | 02769 | 3.8 | Solar | 05_09_523L4 | 12/16/2024 | 01/10/2025 | 5 | 0 | 5 | 01/13/2025 | 01/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | WORCESTER | 522693 | 01605 | 100 | Solar | 05_05_336W4 | 04/29/2023 | 01/06/2024 | 171 | 162 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMPDEN | 382307 | 01036 | 7.6 | Solar | 05_09_909W4 | 10/01/2021 | 01/04/2022 | 1 | 0 | 1 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 | 10/01/2021 | 1/20/2023 | Y | EXP | 365 | 01/05/2022 | 01/04/2022 | 0 | 0 | 0 |  |  | 1/27/2022 | Connected |  | N
National Grid | RANDOLPH | 549586 | 02368 | 200 | Solar | 05_05_317W2 | 09/25/2023 | 03/07/2024 | 111 | 102 | 9 | 03/08/2024 | 03/08/2024 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 |  | 5/27/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | SCITUATE | 752108 | 02066 | 13.12 | Solar | 05_07_797W20 | 02/19/2026 | 03/02/2026 | 6 | 3 | 3 | 03/03/2026 | 03/03/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WARE | 562760 | 01082 | 9.984 | Solar | 05_05_8L4 | 11/27/2023 | 12/21/2023 | 18 | 16 | 2 | 12/22/2023 | 12/22/2023 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  | 2/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2024 | Connected |  | N
National Grid | MILFORD | 655535 | 01757 | 7.6 | Solar | 05_01_11J330 | 11/19/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 201377 | 01062 | 7.6 | Solar | 05_09_139L1 | 11/16/2018 | 12/19/2018 | 21 | 21 | 0 | 12/20/2018 | 12/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 620708 | 01752 | 6 | Solar | 05_07_97W2 | 06/26/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 48 | 34 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 392732 | 02379 | 5.76 | Solar | 05_07_915W82 | 11/15/2021 | 01/04/2022 | 25 | 20 | 5 | 11/19/2021 | 11/19/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/15/2021 | 5/24/2023 | Y | EXP | 365 | 04/01/2022 | 05/20/2022 | 50 | 0 | 50 |  |  | 6/30/2022 | Connected |  | N
National Grid | REHOBOTH | 667028 | 02769 | 20 | Solar | 05_09_523L4 | 02/03/2025 | 02/05/2025 | 2 | 0 | 2 | 02/06/2025 | 02/06/2025 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 02/03/2025 | 4/3/2026 | Y | EXP | 365 | 11/07/2025 | 12/18/2025 | 42 | 0 | 42 |  |  | 11/24/2025 | Connected |  | N
National Grid | WORCESTER | 698208 | 01605 | 150 | Solar | 05_05_336W4 | 07/07/2025 |  | 56 | 49 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMPDEN | 395501 | 01036 | 10 | Solar | 05_09_909W4 | 03/07/2022 | 03/08/2022 | 2 | 1 | 1 | 03/09/2022 | 03/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2022 | 03/07/2022 | 6/13/2023 | Y | EXP | 365 | 05/19/2022 | 05/31/2022 | 13 | 0 | 13 |  |  | 8/12/2022 | Connected |  | N
National Grid | RANDOLPH | 625569 | 02368 | 499 | Solar | 05_05_317W2 | 09/25/2024 |  | 73 | 66 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 177426 | 02066 | 7.6 | Solar | 05_07_797W20 | 02/27/2017 | 02/27/2017 | 6 | 6 | 0 | 03/08/2017 | 03/08/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2017 |  | 3/5/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 10/4/2018 | Connected |  | N
National Grid | PALMER | 594903 | 01079 | 34.5 | Solar | 05_05_8L4 | 03/06/2024 | 03/08/2024 | 2 | 0 | 2 | 03/11/2024 | 03/11/2024 | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 175077 | 01757 | 35 | Solar | 05_01_11J331 | 09/24/2013 | 09/24/2013 | 4 | 0 | 4 | 10/02/2013 | 10/02/2013 | 818 | 0 | 818 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2013 | 09/24/2013 | 7/31/2016 | Y | EXP | 991 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 284615 | 01062 | 10 | Solar | 05_09_139L1 | 03/20/2020 | 03/31/2020 | 7 | 7 | 0 | 04/01/2020 | 04/01/2020 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2020 |  | 3/31/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2020 | Connected |  | N
National Grid | MARLBOROUGH | 629620 | 01752 | 6.72 | Solar | 05_07_97W2 | 08/02/2024 | 08/13/2024 | 5 | 0 | 5 | 08/14/2024 | 08/14/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/02/2024 | 9/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 403664 | 02379 | 0 | Solar | 05_07_915W82 | 12/29/2021 | 01/18/2022 | 12 | 9 | 3 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2022 | Connected |  | N
National Grid | NORTON | 668004 | 02766 | 9.5 | Solar | 05_09_523L4 | 01/27/2025 | 02/07/2025 | 4 | 0 | 4 | 02/10/2025 | 02/10/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | WORCESTER | 175467 | 01605 | 7.6 | Solar | 05_05_341W1 | 09/24/2014 | 09/24/2014 | 7 | 0 | 7 | 10/06/2014 | 10/06/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 410687 | 01036 | 0 | Solar | 05_09_909W4 | 02/07/2022 | 02/23/2022 | 12 | 11 | 1 | 02/24/2022 | 02/24/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  | 4/26/2023 | N | EXP | 39 |  |  | 0 | 0 | 0 |  |  | 3/7/2023 | Connected |  | N
National Grid | RANDOLPH | 650004 | 02368 | 0 | Other | 05_05_317W3 | 05/02/2025 | 07/11/2025 | 46 | 38 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 12/18/2025 | 109 | 92 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SCITUATE | 177657 | 02066 | 1000 | Solar | 05_07_797W20 | 11/10/2017 | 11/10/2017 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2017 | 01/12/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 11/19/2018 | N | STD | 159 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 632119 | 01082 | 0 | Battery Add-On | 05_05_8L4 | 09/03/2024 | 09/11/2024 | 6 | 4 | 2 | 09/12/2024 | 09/12/2024 | 24 | 19 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2024 |  | 11/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2024 | Connected |  | N
National Grid | MILFORD | 587958 | 01757 | 825 | Natural Gas | 05_01_11J331 | 03/07/2024 |  | 179 | 170 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 333791 | 01062 | 15.2 | Solar | 05_09_139L1 | 12/23/2020 | 12/29/2020 | 3 | 2 | 1 | 12/30/2020 | 12/30/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/23/2020 | 6/8/2022 | Y | EXP | 365 | 04/14/2021 | 05/12/2021 | 28 | 0 | 28 |  |  | 12/14/2021 | Connected |  | N
National Grid | MARLBOROUGH | 630217 | 01752 | 3.8 | Solar | 05_07_97W2 | 08/05/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 415760 | 02379 | 0 | Solar | 05_07_915W82 | 03/12/2022 | 03/14/2022 | 2 | 1 | 1 | 03/15/2022 | 03/15/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 |  | 5/15/2023 | N | EXP | 39 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 703736 | 02703 | 20 | Solar | 05_09_523L4 | 07/09/2025 | 07/24/2025 | 4 | 0 | 4 | 11/12/2025 | 11/12/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | WORCESTER | 175894 | 01605 | 6 | Solar | 05_05_341W1 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/10/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 12/3/2015 | Connected |  | N
National Grid | MONSON | 418652 | 01057 | 15.2 | Solar | 05_09_909W4 | 03/18/2022 | 03/24/2022 | 5 | 4 | 1 | 03/25/2022 | 03/25/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2022 |  | 4/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2022 | Connected |  | N
National Grid | RANDOLPH | 177488 | 02368 | 7.6 | Solar | 05_05_317W3 | 09/23/2016 | 09/23/2016 | 3 | 3 | 0 | 09/29/2016 | 09/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 | 09/23/2016 | 10/1/2017 | Y | EXP | 361 | 08/22/2017 | 09/12/2017 | 14 | 0 | 14 | 9/25/2017 | 9/25/2017 | 9/28/2017 | Connected |  | N
National Grid | SCITUATE | 189857 | 02066 | 999 | Solar | 05_07_797W20 | 07/16/2018 | 08/27/2018 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2018 | 03/09/2020 | 186 | 4 | 182 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2019 |  | 4/29/2021 | N | STD | 658 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 641921 | 01069 | 6 | Solar | 05_05_8L4 | 09/23/2024 | 09/30/2024 | 4 | 0 | 4 | 10/01/2024 | 10/01/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 657838 | 01757 | 7.6 | Solar | 05_01_11J334 | 12/05/2024 | 01/22/2025 | 23 | 19 | 4 | 01/23/2025 | 01/23/2025 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | NORTHAMPTON | 338188 | 01062 | 7.6 | Solar | 05_09_139L1 | 01/22/2021 | 01/27/2021 | 2 | 0 | 2 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/22/2021 | 9/14/2022 | Y | EXP | 365 | 09/10/2021 | 10/12/2021 | 22 | 0 | 22 |  |  | 12/15/2021 | Connected |  | Y
National Grid | MARLBOROUGH | 633443 | 01752 | 9.57 | Solar | 05_07_97W2 | 08/22/2024 | 10/03/2024 | 26 | 24 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  | 11/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N
National Grid | BRIDGEWATER | 491908 | 02333 | 0 | Solar | 05_07_915W82 | 01/12/2023 | 01/18/2023 | 4 | 1 | 3 | 01/19/2023 | 01/19/2023 | 43 | 23 | 20 | 05/03/2024 | 07/23/2024 | 56 | 9 | 47 |  |  | 0 | 0 | 0 |  | 07/23/2024 | 56 | 9 | 47 |  |  | 0 | 0 | 0 | 7/23/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 465731 | 02769 | 0 | Other | 05_09_527L1 | 12/22/2022 | 01/10/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2023 | 02/09/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 177163 | 01609 | 3.8 | Solar | 05_05_341W1 | 01/24/2017 | 01/24/2017 | 3 | 2 | 1 | 01/27/2017 | 01/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2017 | 01/24/2017 | 1/29/2018 | Y | EXP | 364 |  |  | 0 | 0 | 0 | 9/21/2017 | 9/21/2017 | 9/21/2017 | Connected |  | N
National Grid | LONGMEADOW | 458403 | 01028 | 10 | Solar | 05_09_909W4 | 01/30/2023 | 02/14/2023 | 11 | 9 | 2 | 02/15/2023 | 02/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 01/30/2023 | 10/25/2024 | Y | EXP | 365 | 10/10/2023 | 10/16/2023 | 7 | 0 | 7 |  |  | 11/16/2023 | Connected |  | Y
National Grid | RANDOLPH | 289768 | 02368 | 166.6 | Solar | 05_05_317W3 | 06/10/2020 | 07/06/2020 | 18 | 13 | 5 | 07/07/2020 | 07/07/2020 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2020 |  | 7/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2021 | Connected |  | N
National Grid | SCITUATE | 198658 | 02066 | 433.3 | Solar | 05_07_797W20 | 11/01/2018 | 11/07/2018 | 3 | 0 | 3 | 11/08/2018 | 11/08/2018 | 37 | 23 | 14 | 01/10/2019 | 03/11/2019 | 40 | 21 | 19 |  |  | 0 | 0 | 0 |  | 03/11/2019 | 40 | 21 | 19 |  |  | 0 | 0 | 0 | 3/25/2019 |  | 1/2/2021 | N | EXP | 649 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 645330 | 01082 | 7.6 | Solar | 05_05_8L4 | 10/07/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 | 10/07/2024 | 2/26/2026 | Y | EXP | 365 | 04/15/2025 | 05/20/2025 | 36 | 0 | 36 |  |  | 6/5/2025 | Connected |  | N
National Grid | FRANKLIN | 689607 | 02038 | 5.76 | Solar | 05_01_11J334 | 05/05/2025 | 05/20/2025 | 3 | 0 | 3 | 06/02/2025 | 06/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2026 | Connected |  | N
National Grid | NORTHAMPTON | 340383 | 01062 | 15.36 | Solar | 05_09_139L1 | 02/03/2021 | 02/05/2021 | 1 | 0 | 1 | 02/08/2021 | 02/08/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2021 |  | 2/4/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 639713 | 01772 | 2.32 | Solar | 05_07_97W2 | 09/12/2024 | 09/25/2024 | 1 | 0 | 1 | 09/26/2024 | 09/26/2024 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 521120 | 02379 | 15 | Solar | 05_07_915W82 | 07/27/2023 | 08/09/2023 | 9 | 7 | 2 | 08/10/2023 | 08/10/2023 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  | 12/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2024 | Connected |  | N
National Grid | REHOBOTH | 458825 | 02769 | 4980 | Solar | 05_09_527L1 | 10/28/2022 | 11/29/2022 | 21 | 15 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 11/30/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 177340 | 01609 | 480 | Solar | 05_05_341W1 | 11/11/2016 | 11/11/2016 | 4 | 4 | 0 | 11/28/2016 | 11/28/2016 | 205 | 14 | 191 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/26/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 487983 | 01057 | 10 | Solar | 05_09_909W4 | 01/24/2023 | 01/26/2023 | 2 | 0 | 2 | 01/27/2023 | 01/27/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 | 01/24/2023 | 8/23/2024 | Y | EXP | 365 | 07/28/2023 | 07/27/2023 | 0 | 0 | 0 |  |  | 8/31/2023 | Connected |  | N
National Grid | RANDOLPH | 324464 | 02368 | 16 | Solar | 05_05_317W3 | 11/07/2020 | 11/10/2020 | 1 | 0 | 1 | 11/12/2020 | 11/12/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 11/10/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 292016 | 02066 | 7.83 | Solar | 05_07_797W20 | 05/27/2020 | 06/03/2020 | 4 | 0 | 4 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2021 | Connected |  | N
National Grid | PALMER | 657168 | 01069 | 5.76 | Solar | 05_05_8L4 | 11/26/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 4/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | FRANKLIN | 653116 | 02038 | 5.76 | Solar | 05_01_11J346 | 11/08/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | NORTHAMPTON | 422881 | 01062 | 0 | Solar | 05_09_139L1 | 04/08/2022 | 04/11/2022 | 1 | 0 | 1 | 04/12/2022 | 04/12/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2022 |  | 5/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2022 | Connected |  | N
National Grid | SOUTHBOROUGH | 641021 | 01772 | 7.6 | Solar | 05_07_97W2 | 10/07/2024 | 11/12/2024 | 15 | 10 | 5 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/07/2024 | 3/12/2026 | Y | EXP | 365 | 04/15/2025 | 04/29/2025 | 15 | 0 | 15 |  |  | 9/16/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 534667 | 02379 | 50 | Solar | 05_07_915W82 | 06/29/2023 | 08/24/2023 | 39 | 30 | 9 | 08/25/2023 | 08/25/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2024 |  | 4/3/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | ATTLEBORO | 442707 | 02703 | 3000 | Solar | 05_09_527L1 | 09/30/2022 | 10/25/2022 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2022 | 11/16/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 177968 | 01605 | 10 | Solar | 05_05_341W1 | 04/24/2017 | 04/24/2017 | 26 | 26 | 0 | 05/31/2017 | 05/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 | 04/24/2017 | 4/29/2018 | Y | EXP | 332 | 08/29/2017 | 09/08/2017 | 7 | 0 | 7 | 10/24/2017 | 10/24/2017 | 10/24/2017 | Connected |  | N
National Grid | LONGMEADOW | 505781 | 01028 | 10.47 | Solar | 05_09_909W4 | 03/06/2023 | 03/08/2023 | 2 | 0 | 2 | 03/09/2023 | 03/09/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 |  | 4/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2023 | Connected |  | N
National Grid | RANDOLPH | 422790 | 02368 | 17.6 | Solar | 05_05_317W3 | 04/08/2022 | 05/05/2022 | 19 | 17 | 2 | 05/06/2022 | 05/06/2022 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2022 | 04/08/2022 | 3/8/2024 | Y | EXP | 365 | 08/11/2022 | 01/11/2023 | 154 | 0 | 154 |  |  | 8/23/2023 | Connected |  | N
National Grid | SCITUATE | 337504 | 02066 | 150 | Solar | 05_07_797W20 | 01/26/2021 | 02/03/2021 | 5 | 0 | 5 | 02/04/2021 | 02/04/2021 | 22 | 0 | 22 | 04/12/2021 | 07/13/2021 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  | 07/13/2021 | 48 | 0 | 48 |  |  | 0 | 0 | 0 | 7/6/2021 | 01/26/2021 | 11/25/2022 | Y | EXP | 273 | 02/05/2022 | 07/11/2022 | 158 | 119 | 39 |  |  | 12/6/2022 | Connected |  | N
National Grid | GRANBY | 657032 | 01033 | 10 | Solar | 05_05_8L4 | 11/26/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 711185 | 02038 | 7.6 | Solar | 05_01_11J347 | 08/11/2025 | 09/22/2025 | 2 | 0 | 2 | 10/20/2025 | 10/20/2025 | 10 | 1 | 9 | 11/13/2025 | 12/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 12/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 12/19/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 456718 | 01062 | 15.2 | Solar | 05_09_139L1 | 09/06/2022 | 09/07/2022 | 1 | 0 | 1 | 09/08/2022 | 09/08/2022 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 | 09/06/2022 | 10/10/2023 | Y | EXP | 365 | 01/07/2023 | 01/14/2023 | 8 | 0 | 8 |  |  | 3/2/2023 | Connected |  | N
National Grid | SOUTHBOROUGH | 646523 | 01772 | 10 | Solar | 05_07_97W2 | 10/18/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 546343 | 02379 | 10.64 | Solar | 05_07_915W82 | 08/18/2023 | 08/28/2023 | 7 | 6 | 1 | 08/29/2023 | 08/29/2023 | 66 | 45 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  | 12/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | ATTLEBORO | 645502 | 02703 | 0 | Other | 05_09_527L1 | 03/07/2025 | 05/01/2025 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2025 | 06/02/2025 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 266941 | 01605 | 10 | Solar | 05_05_341W1 | 11/22/2019 | 01/28/2020 | 45 | 44 | 1 | 01/29/2020 | 01/29/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2020 |  | 11/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2020 | Connected |  | N
National Grid | HAMPDEN | 528675 | 01036 | 7.6 | Solar | 05_09_909W4 | 05/26/2023 | 06/01/2023 | 3 | 0 | 3 | 06/02/2023 | 06/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2023 | 05/26/2023 | 7/6/2024 | Y | EXP | 365 | 08/01/2023 | 08/04/2023 | 4 | 0 | 4 |  |  | 8/12/2023 | Connected |  | N
National Grid | RANDOLPH | 439477 | 02368 | 7.6 | Solar | 05_05_317W3 | 07/28/2022 | 08/01/2022 | 2 | 0 | 2 | 08/02/2022 | 08/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 | 07/28/2022 | 1/5/2024 | Y | EXP | 365 | 10/11/2022 | 01/24/2023 | 106 | 0 | 106 |  |  | 1/14/2023 | Connected |  | N
National Grid | SCITUATE | 378348 | 02066 | 0 | Solar | 05_07_797W20 | 08/26/2021 | 08/27/2021 | 1 | 0 | 1 | 08/30/2021 | 08/30/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 3/6/2023 | N | EXP | 45 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 668697 | 01033 | 10 | Solar | 05_05_8L4 | 01/29/2025 | 03/11/2025 | 3 | 0 | 3 | 03/12/2025 | 03/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 5/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | FRANKLIN | 723563 | 02038 | 5.76 | Solar | 05_01_11J347 | 10/02/2025 | 10/09/2025 | 5 | 0 | 5 | 11/13/2025 | 11/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 10/02/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTHAMPTON | 462569 | 01062 | 19 | Solar | 05_09_139L1 | 09/26/2022 | 09/27/2022 | 2 | 1 | 1 | 09/28/2022 | 09/28/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2022 |  | 9/6/2024 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 654919 | 01772 | 11.5 | Solar | 05_07_97W2 | 11/19/2024 | 11/25/2024 | 2 | 0 | 2 | 02/06/2025 | 02/06/2025 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 594641 | 02379 | 23 | Solar | 05_07_915W82 | 03/05/2024 | 03/07/2024 | 2 | 0 | 2 | 03/08/2024 | 03/08/2024 | 27 | 23 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 5/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | REHOBOTH | 681440 | 02769 | 6.67 | Solar | 05_09_527L1 | 08/28/2025 | 09/17/2025 | 9 | 7 | 2 | 12/18/2025 | 12/18/2025 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 | 08/28/2025 | 2/19/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 656447 | 01602 | 23 | Battery Add-On | 05_05_341W1 | 12/17/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 53 | 30 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | MONSON | 529594 | 01057 | 3.8 | Solar | 05_09_909W4 | 06/02/2023 | 06/06/2023 | 2 | 0 | 2 | 06/07/2023 | 06/07/2023 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 456585 | 02368 | 10 | Solar | 05_05_317W3 | 09/05/2022 | 09/06/2022 | 1 | 0 | 1 | 09/07/2022 | 09/07/2022 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 10/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | N
National Grid | SCITUATE | 389737 | 02066 | 0 | Other | 05_07_797W20 | 11/10/2021 | 01/04/2022 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 680570 | 01033 | 15.58 | Solar | 05_05_8L4 | 03/26/2025 | 04/03/2025 | 7 | 3 | 4 | 04/04/2025 | 04/04/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N
National Grid | FRANKLIN | 731780 | 02038 | 10 | Solar | 05_01_11J347 | 11/06/2025 | 11/06/2025 | 2 | 0 | 2 | 11/17/2025 | 11/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTHAMPTON | 494712 | 01062 | 240 | Solar | 05_09_139L1 | 01/28/2023 | 06/02/2023 | 0 | 0 | 0 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 669810 | 01772 | 2.03 | Solar | 05_07_97W2 | 02/04/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 601761 | 02379 | 0 | Solar | 05_07_915W82 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 689634 | 02703 | 499 | Solar | 05_09_527L1 | 06/12/2025 | 07/30/2025 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2025 | 08/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 678310 | 01605 | 10 | Solar | 05_05_341W1 | 03/19/2025 | 03/24/2025 | 3 | 0 | 3 | 03/25/2025 | 03/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | HAMPDEN | 547130 | 01036 | 15.2 | Solar | 05_09_909W4 | 08/09/2023 | 08/15/2023 | 4 | 0 | 4 | 08/16/2023 | 08/16/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 7/24/2025 | N | EXP | 465 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 507198 | 02368 | 19.72 | Solar | 05_05_317W3 | 03/09/2023 | 03/10/2023 | 1 | 0 | 1 | 03/13/2023 | 03/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2023 |  | 4/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2023 | Connected |  | N
National Grid | SCITUATE | 486251 | 02066 | 10 | Solar | 05_07_797W20 | 12/27/2022 | 01/03/2023 | 4 | 0 | 4 | 01/04/2023 | 01/04/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 | 12/27/2022 | 3/26/2024 | Y | EXP | 365 | 03/28/2023 | 03/27/2023 | 0 | 0 | 0 |  |  | 7/24/2023 | Connected |  | N
National Grid | GRANBY | 683213 | 01033 | 5.76 | Solar | 05_05_8L4 | 04/14/2025 | 04/24/2025 | 7 | 4 | 3 | 04/25/2025 | 04/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | FRANKLIN | 652966 | 02038 | 8.7 | Solar | 05_01_11J347 | 11/21/2024 | 12/30/2024 | 6 | 1 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 11/21/2024 | 4/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | NORTHAMPTON | 498078 | 01062 | 0 | Battery Add-On | 05_09_139L1 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2023 |  | 8/3/2024 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 674265 | 01772 | 11.4 | Solar | 05_07_97W2 | 02/26/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | BRIDGEWATER | 670840 | 02324 | 7.6 | Solar | 05_07_915W82 | 02/07/2025 | 03/17/2025 | 3 | 0 | 3 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | ATTLEBORO | 688733 | 02703 | 22.8 | Solar | 05_09_527L1 | 05/07/2025 | 05/12/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 715096 | 01605 | 23 | Solar | 05_05_341W1 | 08/28/2025 | 09/03/2025 | 3 | 1 | 2 | 09/04/2025 | 09/04/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | MONSON | 548485 | 01057 | 6 | Solar | 05_09_909W4 | 08/23/2023 | 08/29/2023 | 4 | 0 | 4 | 08/30/2023 | 08/30/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 511745 | 02368 | 15.2 | Solar | 05_05_317W3 | 03/16/2023 | 03/17/2023 | 1 | 0 | 1 | 03/20/2023 | 03/20/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2023 | 03/16/2023 | 4/27/2024 | Y | EXP | 365 | 05/06/2023 | 12/06/2023 | 215 | 0 | 215 |  |  | 12/14/2023 | Connected |  | N
National Grid | SCITUATE | 591477 | 02066 | 15.2 | Solar | 05_07_797W20 | 02/20/2024 | 02/22/2024 | 2 | 0 | 2 | 02/23/2024 | 02/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 684218 | 01033 | 11.5 | Solar | 05_05_8L4 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | FRANKLIN | 654510 | 02038 | 7.6 | Solar | 05_01_11J347 | 11/14/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 65 | 41 | 24 | 03/18/2025 | 05/14/2025 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  | 05/14/2025 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 519840 | 01062 | 15.2 | Solar | 05_09_139L1 | 04/18/2023 | 04/24/2023 | 4 | 0 | 4 | 04/25/2023 | 04/25/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2023 |  | 6/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 697060 | 01772 | 7.6 | Solar | 05_07_97W2 | 07/10/2025 | 07/16/2025 | 4 | 0 | 4 | 07/17/2025 | 07/17/2025 | 67 | 55 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 682654 | 02379 | 22.8 | Solar | 05_07_915W82 | 04/21/2025 | 05/08/2025 | 12 | 8 | 4 | 05/09/2025 | 05/09/2025 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | REHOBOTH | 692853 | 02769 | 4980 | Solar | 05_09_527L1 | 06/06/2025 | 08/26/2025 | 53 | 43 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2025 | 09/23/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 738905 | 01605 | 0 | Battery Add-On | 05_05_341W2 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MONSON | 552016 | 01057 | 0 | Solar | 05_09_909W4 | 10/05/2023 | 10/09/2023 | 2 | 0 | 2 | 10/10/2023 | 10/10/2023 | 93 | 50 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 554254 | 02368 | 0 | Solar | 05_05_317W3 | 09/08/2023 | 09/12/2023 | 2 | 0 | 2 | 09/13/2023 | 09/13/2023 | 29 | 7 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 | 09/08/2023 | 12/7/2024 | Y | EXP | 365 | 11/21/2023 | 11/21/2023 | 1 | 0 | 1 |  |  | 2/12/2024 | Connected |  | N
National Grid | SCITUATE | 625438 | 02066 | 9.86 | Solar | 05_07_797W20 | 07/17/2024 | 07/24/2024 | 3 | 1 | 2 | 07/25/2024 | 07/25/2024 | 17 | 6 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/17/2024 | 8/23/2025 | Y | EXP | 365 | 10/29/2024 | 11/13/2024 | 16 | 0 | 16 |  |  | 11/15/2024 | Connected |  | N
National Grid | GRANBY | 687034 | 01033 | 10 | Solar | 05_05_8L4 | 04/23/2025 | 04/29/2025 | 4 | 0 | 4 | 04/30/2025 | 04/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2025 | Connected |  | N
National Grid | FRANKLIN | 669413 | 02038 | 7.6 | Solar | 05_01_11J347 | 02/03/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 40 | 20 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N
National Grid | NORTHAMPTON | 522193 | 01062 | 10 | Solar | 05_09_139L1 | 06/05/2023 | 06/12/2023 | 6 | 5 | 1 | 06/13/2023 | 06/13/2023 | 20 | 0 | 20 | 08/09/2023 | 09/14/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 09/14/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 9/11/2023 |  | 11/1/2024 | N | EXP | 365 | 10/25/2023 | 10/30/2023 | 6 | 0 | 6 |  |  | 2/14/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 710397 | 01772 | 10 | Solar | 05_07_97W2 | 08/07/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 51 | 25 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 740453 | 02379 | 11.5 | Battery Add-On | 05_07_915W82 | 12/16/2025 | 12/17/2025 | 1 | 0 | 1 | 12/18/2025 | 12/18/2025 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2026 | Connected |  | N
National Grid | REHOBOTH | 692847 | 02769 | 4980 | Solar | 05_09_527L1 | 06/12/2025 | 08/19/2025 | 45 | 37 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2025 | 09/10/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 174314 | 01605 | 20.5 | Solar | 05_05_341W2 | 01/16/2012 | 01/16/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/15/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 553933 | 01036 | 22.8 | Solar | 05_09_909W4 | 09/12/2023 | 09/18/2023 | 4 | 0 | 4 | 09/19/2023 | 09/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 |  | 11/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2024 | Connected |  | N
National Grid | RANDOLPH | 645386 | 02368 | 10 | Solar | 05_05_317W3 | 10/18/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 | 10/18/2024 | 1/3/2026 | Y | EXP | 365 | 01/16/2025 | 02/19/2025 | 34 | 0 | 34 |  |  | 4/22/2025 | Connected |  | N
National Grid | SCITUATE | 634657 | 02066 | 9.86 | Solar | 05_07_797W20 | 08/22/2024 | 09/03/2024 | 4 | 0 | 4 | 09/04/2024 | 09/04/2024 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 | 08/22/2024 | 11/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | GRANBY | 694429 | 01033 | 13.36 | Solar | 05_05_8L4 | 05/28/2025 | 07/15/2025 | 2 | 0 | 2 | 07/22/2025 | 07/22/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 745416 | 02038 | 11.4 | Solar | 05_01_11J351 | 01/14/2026 | 01/20/2026 | 1 | 0 | 1 | 01/27/2026 | 01/27/2026 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 526470 | 01062 | 10 | Solar | 05_09_139L1 | 06/07/2023 | 07/05/2023 | 19 | 16 | 3 | 07/06/2023 | 07/06/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2023 |  | 9/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 712286 | 01772 | 3.8 | Solar | 05_07_97W2 | 08/14/2025 | 09/05/2025 | 2 | 0 | 2 | 09/11/2025 | 09/11/2025 | 43 | 29 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 646496 | 02379 | 3.8 | Solar | 05_07_91W40 | 12/17/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 3/18/2026 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REHOBOTH | 716877 | 02769 | 11.02 | Solar | 05_09_527L1 | 09/04/2025 | 09/22/2025 | 9 | 5 | 4 | 10/09/2025 | 10/09/2025 | 37 | 18 | 19 | 12/10/2025 | 01/05/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 01/05/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 1/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WORCESTER | 175726 | 01605 | 140 | Solar | 05_05_341W2 | 05/30/2014 | 05/30/2014 | 14 | 9 | 5 | 06/23/2014 | 06/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2014 | 05/30/2014 | 10/15/2014 | Y | EXP | 85 | 10/16/2014 | 12/04/2014 | 33 | 0 | 33 | 7/16/2014 | 7/16/2014 | 12/30/2014 | Connected |  | N
National Grid | HAMPDEN | 564752 | 01036 | 5 | Solar | 05_09_909W4 | 11/22/2023 | 12/07/2023 | 11 | 9 | 2 | 12/08/2023 | 12/08/2023 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 11/22/2023 | 3/6/2025 | Y | EXP | 365 | 03/30/2024 | 04/09/2024 | 11 | 0 | 11 |  |  | 4/11/2024 | Connected |  | N
National Grid | RANDOLPH | 649999 | 02368 | 16.72 | Solar | 05_05_317W3 | 10/25/2024 | 10/30/2024 | 3 | 0 | 3 | 10/31/2024 | 10/31/2024 | 51 | 27 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | SCITUATE | 637313 | 02066 | 34.5 | Solar | 05_07_797W20 | 09/03/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 47 | 38 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | GRANBY | 696851 | 01033 | 11.5 | Solar | 05_05_8L4 | 06/06/2025 | 08/22/2025 | 1 | 0 | 1 | 08/25/2025 | 08/25/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 376329 | 02038 | 7.6 | Solar | 05_01_11J351 | 09/21/2021 | 01/07/2022 | 51 | 50 | 1 | 12/07/2021 | 12/07/2021 | 22 | 0 | 22 | 04/05/2022 | 12/14/2023 | 422 | 0 | 422 |  |  | 0 | 0 | 0 |  | 12/14/2023 | 422 | 0 | 422 |  |  | 0 | 0 | 0 | 3/30/2022 |  | 8/20/2024 | N | EXP | 365 | 09/09/2023 | 12/14/2023 | 97 | 0 | 97 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 537341 | 01062 | 3.8 | Solar | 05_09_139L1 | 07/05/2023 | 07/19/2023 | 11 | 10 | 1 | 07/20/2023 | 07/20/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2023 | 07/05/2023 | 11/17/2024 | Y | EXP | 365 | 01/20/2024 | 01/19/2024 | 0 | 0 | 0 |  |  | 1/23/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 715435 | 01772 | 10.15 | Solar | 05_07_97W2 | 08/28/2025 | 09/26/2025 | 3 | 0 | 3 | 09/29/2025 | 09/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 | 08/28/2025 | 11/3/2026 | Y | EXP | 365 | 12/24/2025 | 01/06/2026 | 14 | 0 | 14 |  |  | 1/8/2026 | Connected |  | N
National Grid | WEST BRIDGEWATER | 699180 | 02379 | 7.6 | Solar | 05_07_91W40 | 10/01/2025 | 10/13/2025 | 5 | 0 | 5 | 11/04/2025 | 11/04/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATTLEBORO | 729569 | 02703 | 12.76 | Solar | 05_09_527L1 | 10/29/2025 | 12/11/2025 | 28 | 24 | 4 | 12/12/2025 | 12/12/2025 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 393614 | 01605 | 15.2 | Solar | 05_05_341W2 | 11/05/2021 | 11/09/2021 | 2 | 0 | 2 | 11/10/2021 | 11/10/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 596291 | 01057 | 0 | Solar | 05_09_909W4 | 03/12/2024 | 03/15/2024 | 3 | 1 | 2 | 03/18/2024 | 03/18/2024 | 54 | 54 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 177389 | 02368 | 15.2 | Solar | 05_05_317W4 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2017 |  | 2/21/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 6/8/2017 | 6/8/2017 | 6/13/2017 | Connected |  | N
National Grid | SCITUATE | 647055 | 02066 | 10 | Solar | 05_07_797W20 | 10/24/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/24/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 701732 | 01033 | 15.96 | Solar | 05_05_8L4 | 06/27/2025 | 07/02/2025 | 3 | 0 | 3 | 07/03/2025 | 07/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 |  | 8/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | FRANKLIN | 620163 | 02038 | 5.76 | Solar | 05_01_11J351 | 06/24/2024 | 07/08/2024 | 2 | 0 | 2 | 07/09/2024 | 07/09/2024 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 9/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | NORTHAMPTON | 564573 | 01062 | 0 | Solar | 05_09_139L1 | 10/19/2023 | 10/26/2023 | 6 | 5 | 1 | 10/27/2023 | 10/27/2023 | 56 | 43 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2024 |  | 2/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 714211 | 01772 | 5.76 | Solar | 05_07_97W3 | 08/22/2025 | 10/03/2025 | 3 | 0 | 3 | 10/28/2025 | 10/28/2025 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEST BRIDGEWATER | 711584 | 02379 | 5.76 | Solar | 05_07_91W40 | 08/12/2025 | 10/29/2025 | 25 | 22 | 3 | 01/22/2026 | 01/22/2026 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | REHOBOTH | 732333 | 02769 | 20 | Solar | 05_09_527L1 | 11/12/2025 | 11/14/2025 | 2 | 0 | 2 | 11/17/2025 | 11/17/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 423130 | 01609 | 7.6 | Solar | 05_05_341W2 | 04/11/2022 | 05/27/2022 | 34 | 33 | 1 | 05/31/2022 | 05/31/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2022 |  | 7/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2022 | Connected |  | N
National Grid | HAMPDEN | 600071 | 01036 | 5 | Solar | 05_09_909W4 | 04/02/2024 | 04/03/2024 | 1 | 0 | 1 | 04/04/2024 | 04/04/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 | 04/02/2024 | 4/23/2025 | Y | EXP | 365 | 05/24/2024 | 08/15/2024 | 84 | 0 | 84 |  |  | 9/5/2024 | Connected |  | N
National Grid | RANDOLPH | 255931 | 02368 | 10 | Solar | 05_05_317W4 | 09/23/2019 | 09/25/2019 | 2 | 2 | 0 | 09/26/2019 | 09/26/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2019 |  | 9/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N
National Grid | BROCKTON | 654486 | 02302 | 10 | Solar | 05_07_797W20 | 11/18/2024 | 12/18/2024 | 1 | 0 | 1 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/18/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | GRANBY | 706851 | 01033 | 15.76 | Solar | 05_05_8L4 | 08/06/2025 | 08/11/2025 | 3 | 0 | 3 | 08/12/2025 | 08/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2025 | Connected |  | N
National Grid | FRANKLIN | 661688 | 02038 | 0 | Solar | 05_01_11J351 | 01/21/2025 | 02/14/2025 | 19 | 14 | 5 | 02/18/2025 | 02/18/2025 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | NORTHAMPTON | 575689 | 01062 | 11.4 | Solar | 05_09_139L1 | 12/05/2023 | 12/06/2023 | 1 | 0 | 1 | 12/07/2023 | 12/07/2023 | 80 | 56 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 715083 | 01772 | 7.6 | Solar | 05_07_97W3 | 08/28/2025 | 09/23/2025 | 1 | 0 | 1 | 10/02/2025 | 10/02/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 08/28/2025 | 2/7/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WEST BRIDGEWATER | 734999 | 02379 | 250 | Solar | 05_07_91W40 | 02/19/2026 |  | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | REHOBOTH | 737659 | 02769 | 5.76 | Solar | 05_09_527L1 | 12/02/2025 | 12/03/2025 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 476346 | 01609 | 0 | Other | 05_05_341W2 | 02/21/2023 |  | 99 | 56 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMPDEN | 612200 | 01036 | 7.6 | Solar | 05_09_909W4 | 05/20/2024 | 05/28/2024 | 3 | 0 | 3 | 05/29/2024 | 05/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 299834 | 02368 | 10 | Solar | 05_05_317W4 | 07/06/2020 | 07/29/2020 | 16 | 14 | 2 | 07/30/2020 | 07/30/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 10/16/2021 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 657495 | 02302 | 11.5 | Solar | 05_07_797W20 | 11/27/2024 | 12/11/2024 | 9 | 7 | 2 | 12/12/2024 | 12/12/2024 | 82 | 59 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/19/2025 | Connected |  | N
National Grid | GRANBY | 709735 | 01033 | 10 | Solar | 05_05_8L4 | 08/05/2025 | 08/25/2025 | 4 | 0 | 4 | 09/25/2025 | 09/25/2025 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 08/05/2025 | 11/17/2026 | Y | EXP | 365 | 01/13/2026 | 02/12/2026 | 31 | 0 | 31 |  |  | 2/17/2026 | Connected |  | N
National Grid | FRANKLIN | 513744 | 02038 | 7.6 | Solar | 05_01_11J354 | 03/24/2023 | 03/27/2023 | 1 | 0 | 1 | 03/28/2023 | 03/28/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2023 |  | 6/25/2024 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  | 5/16/2024 | Connected |  | N
National Grid | NORTHAMPTON | 589118 | 01062 | 6 | Solar | 05_09_139L1 | 04/16/2024 | 04/17/2024 | 1 | 0 | 1 | 04/18/2024 | 04/18/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 | 04/16/2024 | 5/7/2025 | Y | EXP | 365 | 10/30/2024 | 10/29/2024 | 0 | 0 | 0 |  |  | 11/6/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 725687 | 01772 | 18.56 | Solar | 05_07_97W3 | 10/10/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEST BRIDGEWATER | 176888 | 02379 | 0 | Solar | 05_07_91W40 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 251 | 0 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2015 |  | 11/18/2016 | N | EXP | 35 |  |  | 0 | 0 | 0 | 12/4/2015 | 12/4/2015 |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 738822 | 02703 | 3.8 | Solar | 05_09_527L1 | 12/08/2025 | 01/15/2026 | 1 | 0 | 1 | 02/02/2026 | 02/02/2026 | 24 | 12 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 507457 | 01609 | 8.448 | Solar | 05_05_341W2 | 03/16/2023 | 04/25/2023 | 28 | 27 | 1 | 04/26/2023 | 04/26/2023 | 105 | 82 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2023 |  | 10/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2023 | Connected |  | N
National Grid | HAMPDEN | 622038 | 01036 | 11.5 | Solar | 05_09_909W4 | 07/02/2024 | 07/31/2024 | 1 | 0 | 1 | 08/01/2024 | 08/01/2024 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 10/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2024 | Connected |  | N
National Grid | HOLBROOK | 428460 | 02343 | 7.6 | Solar | 05_05_317W4 | 05/04/2022 | 05/12/2022 | 7 | 6 | 1 | 05/13/2022 | 05/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2022 |  | 8/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2022 | Connected |  | N
National Grid | BROCKTON | 665671 | 02302 | 0 | Solar | 05_07_797W20 | 01/15/2025 | 01/23/2025 | 5 | 2 | 3 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 | 01/15/2025 | 4/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2025 | Connected |  | N
National Grid | GRANBY | 726585 | 01033 | 0 | Solar | 05_05_8L4 | 11/05/2025 | 11/10/2025 | 3 | 1 | 2 | 11/12/2025 | 11/12/2025 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 538092 | 02038 | 10 | Solar | 05_01_11J354 | 07/05/2023 | 07/06/2023 | 2 | 1 | 1 | 07/07/2023 | 07/07/2023 | 90 | 50 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 620374 | 01062 | 10 | Solar | 05_09_139L1 | 06/25/2024 | 07/28/2024 | 4 | 0 | 4 | 07/29/2024 | 07/29/2024 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2024 | 06/25/2024 | 11/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 728113 | 01772 | 10 | Solar | 05_07_97W3 | 10/21/2025 | 12/04/2025 | 6 | 1 | 5 | 01/07/2026 | 01/07/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WEST BRIDGEWATER | 178279 | 02379 | 7.6 | Solar | 05_07_91W40 | 02/23/2018 | 02/23/2018 | 5 | 5 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 9/16/2020 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 7/18/2020 | Connected |  | N
National Grid | ATTLEBORO | 741731 | 02703 | 33.853 | Solar | 05_09_527L1 | 12/22/2025 | 12/29/2025 | 3 | 0 | 3 | 12/30/2025 | 12/30/2025 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 568963 | 01609 | 0 | Battery Add-On | 05_05_341W2 | 11/06/2023 | 12/07/2023 | 21 | 19 | 2 | 12/08/2023 | 12/08/2023 | 87 | 59 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 5/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | HAMPDEN | 627934 | 01036 | 10 | Solar | 05_09_909W4 | 09/23/2024 | 10/08/2024 | 12 | 8 | 4 | 10/09/2024 | 10/09/2024 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | RANDOLPH | 497172 | 02368 | 15.356 | Solar | 05_05_317W4 | 03/03/2023 | 03/06/2023 | 1 | 0 | 1 | 03/07/2023 | 03/07/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 03/03/2023 | 10/31/2024 | Y | EXP | 365 | 06/14/2023 | 11/01/2023 | 141 | 0 | 141 |  |  | 11/11/2023 | Connected |  | N
National Grid | BROCKTON | 671083 | 02302 | 15.2 | Solar | 05_07_797W20 | 02/10/2025 | 02/19/2025 | 4 | 0 | 4 | 07/18/2025 | 07/18/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 10/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | GRANBY | 728165 | 01033 | 13.36 | Solar | 05_05_8L4 | 10/25/2025 | 10/27/2025 | 5 | 0 | 5 | 11/13/2025 | 11/13/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 560507 | 02038 | 3.8 | Solar | 05_01_11J354 | 10/18/2023 | 10/20/2023 | 3 | 2 | 1 | 10/23/2023 | 10/23/2023 | 72 | 25 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 629307 | 01062 | 100 | Solar | 05_09_139L1 | 08/01/2024 |  | 58 | 49 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 731036 | 01772 | 7.6 | Solar | 05_07_97W3 | 11/03/2025 | 11/04/2025 | 3 | 0 | 3 | 12/09/2025 | 12/09/2025 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEST BRIDGEWATER | 196383 | 02379 | 7.6 | Solar | 05_07_91W40 | 09/19/2018 | 11/20/2018 | 23 | 23 | 0 | 11/21/2018 | 11/21/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 746291 | 02703 | 11.5 | Solar | 05_09_527L1 | 01/20/2026 | 01/23/2026 | 6 | 3 | 3 | 02/11/2026 | 02/11/2026 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 178768 | 01605 | 11 | Solar | 05_05_3422W1 | 02/15/2013 | 02/15/2013 | 5 | 0 | 5 | 02/28/2013 | 02/28/2013 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2013 |  | 12/31/2016 | N | EXP | 1354 |  |  | 0 | 0 | 0 | 4/17/2013 | 4/17/2013 | 1/1/2014 | Connected |  | N
National Grid | HAMPDEN | 631183 | 01036 | 10 | Solar | 05_09_909W4 | 08/20/2024 | 08/21/2024 | 1 | 0 | 1 | 08/22/2024 | 08/22/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 625861 | 02343 | 15.2 | Solar | 05_05_317W4 | 07/18/2024 | 07/24/2024 | 5 | 3 | 2 | 07/25/2024 | 07/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | BROCKTON | 674770 | 02302 | 5.76 | Solar | 05_07_797W20 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N
National Grid | GRANBY | 713326 | 01033 | 2280 | Solar | 05_05_8U | 01/08/2026 |  | 39 | 29 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | FRANKLIN | 564727 | 02038 | 8.12 | Solar | 05_01_11J354 | 10/25/2023 | 11/20/2023 | 17 | 15 | 2 | 11/21/2023 | 11/21/2023 | 149 | 29 | 120 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 634462 | 01062 | 16 | Solar | 05_09_139L1 | 08/21/2024 | 08/23/2024 | 3 | 1 | 2 | 08/26/2024 | 08/26/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 9/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 739909 | 01772 | 11.5 | Solar | 05_07_97W3 | 12/12/2025 | 01/22/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BRIDGEWATER | 248607 | 02379 | 7.6 | Solar | 05_07_91W40 | 08/13/2019 | 09/04/2019 | 3 | 0 | 3 | 09/05/2019 | 09/05/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 | 08/13/2019 | 9/30/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2020 | Connected |  | N
National Grid | ATTLEBORO | 749832 | 02703 | 7.6 | Solar | 05_09_527L1 | 02/12/2026 | 02/18/2026 | 3 | 0 | 3 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 178760 | 01605 | 300 | Solar | 05_05_3422W1 | 12/22/2011 | 12/22/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 647226 | 01057 | 7.6 | Solar | 05_09_909W4 | 10/15/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/15/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2025 | Connected |  | N
National Grid | RANDOLPH | 660095 | 02368 | 23 | Solar | 05_05_317W4 | 12/11/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | BROCKTON | 688918 | 02302 | 9.425 | Solar | 05_07_797W20 | 05/01/2025 | 09/15/2025 | 93 | 91 | 2 | 09/16/2025 | 09/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 732310 | 01033 | 17.6 | Solar | 05_05_9L1 | 01/22/2026 | 01/28/2026 | 3 | 1 | 2 | 01/29/2026 | 01/29/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FRANKLIN | 590880 | 02038 | 1.74 | Solar | 05_01_11J354 | 02/23/2024 | 02/26/2024 | 1 | 0 | 1 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2024 | Connected |  | N
National Grid | NORTHAMPTON | 647319 | 01060 | 11.5 | Solar | 05_09_139L1 | 10/15/2024 | 11/19/2024 | 10 | 6 | 4 | 11/20/2024 | 11/20/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/15/2024 | 3/24/2026 | Y | EXP | 365 | 05/14/2025 | 05/13/2025 | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 745422 | 01772 | 16.34 | Solar | 05_07_97W3 | 01/14/2026 | 01/21/2026 | 4 | 0 | 4 | 01/22/2026 | 01/22/2026 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BRIDGEWATER | 281490 | 02333 | 6 | Solar | 05_07_91W40 | 05/22/2020 | 05/27/2020 | 1 | 0 | 1 | 05/28/2020 | 05/28/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/22/2020 | 5/12/2022 | Y | EXP | 365 | 08/12/2021 | 08/28/2021 | 15 | 3 | 12 |  |  | 9/13/2021 | Connected |  | N
National Grid | REHOBOTH | 173510 | 02769 | 3.8 | Solar | 05_09_527L1 | 04/12/2018 | 04/12/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 6/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2019 | Connected |  | N
National Grid | WORCESTER | 178770 | 01605 | 10 | Solar | 05_05_3422W1 | 10/02/2012 | 10/02/2012 | 6 | 0 | 6 | 10/12/2012 | 10/12/2012 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/5/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 647872 | 01036 | 20 | Solar | 05_09_909W4 | 10/24/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 |  | 1/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2025 | Connected |  | N
National Grid | HOLBROOK | 454160 | 02343 | 133.2 | Solar | 05_05_317W6 | 10/06/2022 | 01/24/2023 | 72 | 62 | 10 | 01/25/2023 | 01/25/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 | 10/06/2022 | 9/18/2026 | Y | EXP | 245 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BROCKTON | 697453 | 02302 | 15.2 | Solar | 05_07_797W20 | 06/12/2025 | 06/25/2025 | 8 | 6 | 2 | 06/26/2025 | 06/26/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/2/2026 | Connected |  | N
National Grid | GRANBY | 738070 | 01033 | 3.8 | Solar | 05_05_9L1 | 12/04/2025 | 12/17/2025 | 3 | 0 | 3 | 01/06/2026 | 01/06/2026 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2026 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 634170 | 01605 | 7.6 | Solar | 05_01_11J354 | 08/20/2024 | 09/17/2024 | 4 | 0 | 4 | 09/18/2024 | 09/18/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 647277 | 01062 | 7.6 | Solar | 05_09_139L1 | 10/15/2024 | 04/23/2025 | 11 | 8 | 3 | 05/22/2025 | 05/22/2025 | 86 | 74 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 754577 | 01772 | 10 | Solar | 05_07_97W3 | 03/04/2026 | 03/06/2026 | 2 | 0 | 2 | 03/09/2026 | 03/09/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BRIDGEWATER | 315002 | 02379 | 7.6 | Solar | 05_07_91W40 | 10/26/2020 | 10/27/2020 | 0 | 0 | 0 | 10/28/2020 | 10/28/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 | 10/26/2020 |  | Y | EXP | 365 | 02/18/2021 | 02/24/2021 | 5 | 0 | 5 |  |  | 3/10/2021 | Connected |  | N
National Grid | MILFORD | 174163 | 01757 | 11.39 | Solar | 05_09_527L1 | 04/23/2012 | 04/23/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2012 |  | 6/22/2012 | N | EXP | 52 |  |  | 0 | 0 | 0 | 8/13/2012 | 8/13/2012 | 1/14/2013 | Connected |  | N
National Grid | WORCESTER | 178769 | 01605 | 12 | Solar | 05_05_3422W1 | 09/18/2012 | 09/18/2012 | 7 | 0 | 7 | 09/28/2012 | 09/28/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2013 |  | 11/20/2012 | N | EXP | 55 |  |  | 0 | 0 | 0 | 1/14/2013 | 1/14/2013 | 4/1/2013 | Connected |  | N
National Grid | HAMPDEN | 652175 | 01036 | 10 | Solar | 05_09_909W4 | 11/11/2024 | 12/04/2024 | 4 | 0 | 4 | 12/05/2024 | 12/05/2024 | 117 | 99 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 347804 | 02368 | 216 | Solar | 05_05_317W6 | 03/19/2021 | 04/05/2021 | 9 | 0 | 9 | 04/06/2021 | 04/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2021 |  | 6/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2021 | Connected |  | N
National Grid | BROCKTON | 718781 | 02302 | 12.16 | Solar | 05_07_797W20 | 09/12/2025 | 11/04/2025 | 1 | 0 | 1 | 11/05/2025 | 11/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 742985 | 01033 | 7.6 | Solar | 05_05_9L1 | 12/31/2025 | 01/06/2026 | 2 | 0 | 2 | 03/05/2026 | 03/05/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FRANKLIN | 636139 | 02038 | 7.6 | Solar | 05_01_11J354 | 08/28/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 31 | 24 | 7 | 11/20/2024 | 01/14/2025 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  | 01/14/2025 | 36 | 0 | 36 |  |  | 0 | 0 | 0 | 1/22/2025 |  | 2/21/2026 | N | EXP | 365 | 06/26/2025 | 07/23/2025 | 28 | 0 | 28 |  |  | 8/21/2025 | Connected |  | N
National Grid | NORTHAMPTON | 648573 | 01062 | 5.76 | Solar | 05_09_139L1 | 11/01/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 176628 | 01772 | 10 | Solar | 05_07_97W3 | 10/15/2015 | 10/15/2015 | 4 | 4 | 0 | 10/21/2015 | 10/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 |  | 10/20/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 8/18/2016 | Connected |  | N
National Grid | WEST BRIDGEWATER | 392439 | 02379 | 7.6 | Solar | 05_07_91W40 | 11/23/2021 | 01/03/2022 | 9 | 3 | 6 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  | 6/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2022 | Connected |  | N
National Grid | ATTLEBORO | 174198 | 02703 | 3300 | Solar | 05_09_527L1 | 03/20/2012 | 03/20/2012 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/15/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 178793 | 01605 | 133.2 | Solar | 05_05_3422W1 | 02/23/2017 | 02/23/2017 | 2 | 0 | 2 | 02/27/2017 | 02/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2017 |  | 2/28/2018 | N | EXP | 328 |  |  | 0 | 0 | 0 | 10/3/2017 | 10/3/2017 | 10/16/2017 | Connected |  | N
National Grid | MONSON | 653490 | 01057 | 11.5 | Solar | 05_09_909W4 | 11/11/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | HOLBROOK | 348992 | 02343 | 100 | Solar | 05_05_317W6 | 03/26/2021 | 05/03/2021 | 24 | 15 | 9 | 05/04/2021 | 05/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2021 |  | 6/26/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 649258 | 02302 | 499 | Solar | 05_07_797W23 | 02/14/2025 | 03/12/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2025 | 04/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GRANBY | 750215 | 01033 | 7.6 | Solar | 05_05_9L1 | 02/11/2026 | 02/13/2026 | 2 | 0 | 2 | 02/17/2026 | 02/17/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 638685 | 01605 | 7.6 | Solar | 05_01_11J354 | 09/09/2024 | 09/20/2024 | 3 | 0 | 3 | 09/23/2024 | 09/23/2024 | 126 | 118 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 653870 | 01062 | 7.6 | Solar | 05_09_139L1 | 11/14/2024 | 12/03/2024 | 1 | 0 | 1 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | MARLBOROUGH | 176647 | 01752 | 1260 | Solar | 05_07_97W3 | 02/17/2016 | 02/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/18/2016 | 03/08/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/23/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 413365 | 02379 | 23.4 | Solar | 05_07_91W40 | 03/24/2022 |  | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 174435 | 02703 | 13.8 | Solar | 05_09_527L1 | 06/28/2012 | 06/28/2012 | 6 | 0 | 6 | 07/11/2012 | 07/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 | 06/28/2012 | 10/26/2012 | Y | EXP | 24 | 07/23/2012 | 10/18/2012 | 61 | 0 | 61 | 10/2/2012 | 10/2/2012 | 11/28/2012 | Connected |  | N
National Grid | WORCESTER | 178792 | 01605 | 28.8 | Solar | 05_05_3422W1 | 02/23/2017 | 02/23/2017 | 2 | 0 | 2 | 02/27/2017 | 02/27/2017 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/28/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMPDEN | 655258 | 01036 | 5.76 | Solar | 05_09_909W4 | 11/20/2024 | 12/20/2024 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | RANDOLPH | 494891 | 02368 | 24.94 | Solar | 05_05_317W6 | 02/15/2023 | 03/20/2023 | 23 | 22 | 1 | 03/21/2023 | 03/21/2023 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2023 |  | 7/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2023 | Connected |  | N
National Grid | BROCKTON | 656709 | 02302 | 4800 | Solar | 05_07_797W23 | 01/07/2025 | 09/15/2025 | 171 | 162 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2025 | 10/13/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BELCHERTOWN | 176386 | 01007 | 10 | Solar | 05_05_9L1 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2016 |  | 2/6/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/22/2016 | 11/28/2016 | Connected |  | N
National Grid | WORCESTER | 641165 | 01605 | 4.537 | Solar | 05_01_11J354 | 09/19/2024 | 10/08/2024 | 10 | 7 | 3 | 10/09/2024 | 10/09/2024 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/19/2024 | 11/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | NORTHAMPTON | 696231 | 01062 | 15.2 | Solar | 05_09_139L1 | 06/04/2025 | 06/11/2025 | 1 | 0 | 1 | 06/12/2025 | 06/12/2025 | 33 | 11 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 176646 | 01752 | 1988 | Solar | 05_07_97W3 | 02/17/2016 | 02/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/18/2016 | 03/08/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/23/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 174676 | 02379 | 3000 | Solar | 05_09_527L1 | 12/30/2013 | 12/30/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2014 | 01/28/2014 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2014 |  | 12/31/2016 | N | STD | 848 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 178785 | 02703 | 480 | Solar | 05_05_3422W1 | 08/18/2015 | 08/18/2015 | 2 | 2 | 0 | 08/20/2015 | 08/20/2015 | 268 | 0 | 268 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/23/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 661925 | 01605 | 13.125 | Solar | 05_09_909W4 | 12/20/2024 | 01/06/2025 | 3 | 0 | 3 | 01/07/2025 | 01/07/2025 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | HAMPDEN | 597028 | 01036 | 46.5 | Solar | 05_05_317W6 | 03/22/2024 | 05/17/2024 | 26 | 19 | 7 | 05/20/2024 | 05/20/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2024 | Connected |  | N
National Grid | HOLBROOK | 717436 | 02343 | 34.2 | Solar | 05_07_797W23 | 09/08/2025 | 09/22/2025 | 9 | 6 | 3 | 09/23/2025 | 09/23/2025 | 110 | 91 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 176410 | 02302 | 10 | Solar | 05_05_9L1 | 05/09/2016 | 05/09/2016 | 1 | 1 | 0 | 05/12/2016 | 05/12/2016 | 182 | 0 | 182 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 |  | 5/16/2017 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 648897 | 01033 | 3.8 | Solar | 05_01_11J354 | 11/18/2024 | 01/21/2025 | 4 | 0 | 4 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | HAMPDEN | 704049 | 01036 | 23.04 | Solar | 05_09_139L1 | 07/14/2025 | 07/21/2025 | 5 | 0 | 5 | 07/22/2025 | 07/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  | 8/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | NORTHAMPTON | 176652 | 01062 | 6 | Solar | 05_07_97W3 | 02/17/2016 | 02/17/2016 | 2 | 2 | 0 | 02/22/2016 | 02/22/2016 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2016 | 02/17/2016 | 9/26/2019 | Y | EXP | 1274 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 485572 | 01752 |  | Other | 05_07_91W40 | 01/19/2023 | 02/03/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2023 | 08/03/2023 | 124 | 105 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 174808 | 02333 | 16 | Solar | 05_09_527L1 | 01/24/2013 | 01/24/2013 | 6 | 0 | 6 | 02/04/2013 | 02/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2013 |  | 4/30/2013 | N | EXP | 46 |  |  | 0 | 0 | 0 | 4/10/2013 | 4/10/2013 | 5/2/2013 | Connected |  | N
National Grid | ATTLEBORO | 178803 | 02703 | 15.2 | Solar | 05_05_3422W1 | 02/01/2018 | 02/01/2018 | 32 | 0 | 32 | 04/26/2018 | 04/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2018 |  | 2/7/2019 | N | EXP | 287 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | Connected |  | N
National Grid | WORCESTER | 670769 | 01605 | 23 | Solar | 05_09_909W4 | 02/07/2025 | 02/13/2025 | 4 | 0 | 4 | 02/14/2025 | 02/14/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | HAMPDEN | 430828 | 01036 | 237.5 | Solar | 05_05_317W7 | 05/25/2022 | 06/24/2022 | 20 | 14 | 6 | 06/27/2022 | 06/27/2022 | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2022 | 05/25/2022 | 6/11/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HOLBROOK | 735422 | 02343 | 5.76 | Solar | 05_07_797W23 | 11/20/2025 | 12/12/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 45 | 30 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 176612 | 02301 | 250 | Solar | 05_05_9L1 | 02/12/2016 | 02/12/2016 | 10 | 10 | 0 | 03/01/2016 | 03/01/2016 | 0 | 0 | 0 | 08/24/2016 | 09/21/2016 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  | 09/21/2016 | 19 | 1 | 18 |  |  | 0 | 0 | 0 | 11/14/2016 |  | 5/12/2017 | N | EXP | 179 |  |  | 0 | 0 | 0 | 5/2/2017 | 5/2/2017 | 5/12/2017 | Connected |  | N
National Grid | GRANBY | 653802 | 01033 | 11.5 | Solar | 05_01_11J354 | 11/18/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 98 | 74 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | WILBRAHAM | 742643 | 01095 | 0 | Battery Add-On | 05_09_139L3 | 01/05/2026 | 01/07/2026 | 2 | 0 | 2 | 01/08/2026 | 01/08/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 176991 | 01062 | 3.8 | Solar | 05_07_97W3 | 03/13/2017 | 03/13/2017 | 9 | 7 | 2 | 03/28/2017 | 03/28/2017 | 251 | 0 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 |  | 3/20/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 493283 | 01752 | 5 | Solar | 05_07_91W40 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2023 | 02/03/2023 | 11/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2023 | Connected |  | N
National Grid | EAST BRIDGEWATER | 175429 | 02333 | 499 | Solar | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/29/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 | 09/18/2014 | 3/15/2016 | Y | STD | 168 |  |  | 0 | 0 | 0 | 12/27/2016 | 12/27/2016 | 12/27/2016 | Connected |  | N
National Grid | ATTLEBORO | 185160 | 02703 | 10.56 | Solar | 05_05_3422W1 | 06/08/2018 | 06/08/2018 | 18 | 7 | 11 | 06/13/2018 | 06/13/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 |  | 7/22/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2018 | Connected |  | N
National Grid | WORCESTER | 686119 | 01605 | 10 | Solar | 05_09_909W4 | 04/25/2025 | 04/28/2025 | 1 | 0 | 1 | 04/29/2025 | 04/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | LONGMEADOW | 175489 | 01028 | 16.8 | Solar | 05_05_317W7 | 07/23/2014 | 07/23/2014 | 7 | 7 | 0 | 08/04/2014 | 08/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2014 |  | 10/31/2014 | N | EXP | 53 |  |  | 0 | 0 | 0 | 9/8/2014 | 9/8/2014 | 12/11/2015 | Connected |  | N
National Grid | HOLBROOK | 745718 | 02343 | 13.8 | Solar | 05_07_797W23 | 01/15/2026 | 01/21/2026 | 1 | 0 | 1 | 01/29/2026 | 01/29/2026 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 177494 | 02301 | 3.8 | Solar | 05_05_9L1 | 12/13/2016 | 12/13/2016 | 4 | 4 | 0 | 12/20/2016 | 12/20/2016 | 270 | 0 | 270 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 |  | 12/19/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/25/2018 | 1/25/2018 |  | Withdrawn |  | N
National Grid | GRANBY | 657179 | 01033 | 7.6 | Solar | 05_01_11J354 | 11/26/2024 | 12/19/2024 | 4 | 0 | 4 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | PLAINVILLE | 175297 | 02762 | 499 | Solar | 05_09_139L3 | 01/15/2015 | 01/15/2015 | 4 | 0 | 4 | 01/23/2015 | 01/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2015 | 01/15/2015 | 3/10/2016 | Y | EXP | 373 | 11/04/2015 | 12/23/2015 | 33 | 0 | 33 | 1/25/2016 | 1/25/2016 | 1/25/2016 | Connected |  | N
National Grid | NORTHAMPTON | 177328 | 01062 | 15.2 | Solar | 05_07_97W3 | 06/20/2016 | 06/20/2016 | 2 | 2 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/26/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 10/12/2016 | 10/12/2016 | 10/17/2016 | Connected |  | N
National Grid | MARLBOROUGH | 557710 | 01752 | 3.84 | Solar | 05_07_91W40 | 09/29/2023 | 10/02/2023 | 1 | 0 | 1 | 10/03/2023 | 10/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 09/29/2023 | 12/8/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 175428 | 02333 | 499 | Solar | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 | 09/18/2014 | 2/14/2017 | Y | STD | 54 |  |  | 0 | 0 | 0 | 12/27/2016 | 12/27/2016 | 12/27/2016 | Connected |  | N
National Grid | ATTLEBORO | 185621 | 02703 | 996 | Solar | 05_05_3422W1 | 05/24/2018 | 05/24/2018 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/28/2018 | 08/02/2018 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 | 05/24/2018 | 3/24/2023 | Y | STD | 575 | 10/23/2021 | 01/27/2023 | 461 | 4 | 457 |  |  | 3/14/2023 | Connected |  | N
National Grid | WORCESTER | 691058 | 01605 | 9.5 | Solar | 05_09_909W4 | 05/12/2025 | 06/16/2025 | 1 | 0 | 1 | 06/18/2025 | 06/18/2025 | 44 | 31 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | HAMPDEN | 714695 | 01036 | 7.6 | Solar | 05_05_317W8 | 08/26/2025 | 09/16/2025 | 5 | 2 | 3 | 11/25/2025 | 11/25/2025 | 36 | 22 | 14 | 02/13/2026 | 03/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 03/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | RANDOLPH | 745482 | 02368 | 11.78 | Solar | 05_07_797W23 | 01/15/2026 | 01/16/2026 | 4 | 1 | 3 | 01/29/2026 | 01/29/2026 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 177875 | 02302 | 120 | Solar | 05_05_9L1 | 08/15/2017 | 08/15/2017 | 12 | 12 | 0 | 08/31/2017 | 08/31/2017 | 142 | 3 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2017 |  | 8/20/2018 | N | EXP | 325 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 658161 | 01033 | 3.8 | Solar | 05_01_11J354 | 12/03/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 139 | 116 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 176704 | 01036 | 499 | Solar | 05_09_139L3 | 10/28/2015 | 10/28/2015 | 0 | 0 | 0 | 10/28/2015 | 10/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 | 10/28/2015 | 11/2/2016 | Y | EXP | 314 | 12/30/2016 | 02/14/2017 | 30 | 0 | 30 | 3/21/2017 | 3/21/2017 | 3/30/2017 | Connected |  | N
National Grid | NORTHAMPTON | 177626 | 01062 | 10 | Solar | 05_07_97W3 | 05/23/2017 | 05/23/2017 | 3 | 3 | 0 | 05/30/2017 | 05/30/2017 | 208 | 0 | 208 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 |  | 5/29/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 548907 | 01752 | 600 | Natural Gas | 05_07_91W40 | 10/03/2023 | 02/05/2024 | 82 | 73 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2024 | 02/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 175427 | 02333 | 392 | Solar | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 188212 | 02703 | 172.8 | Solar | 05_05_3422W1 | 06/15/2018 | 06/15/2018 | 19 | 2 | 17 |  |  | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 705420 | 01605 | 5.76 | Solar | 05_09_909W4 | 07/16/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 717150 | 01095 | 12.92 | Solar | 05_05_317W8 | 09/05/2025 | 09/23/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 | 09/05/2025 | 1/20/2027 | Y | EXP | 365 | 02/07/2026 | 02/13/2026 | 7 | 0 | 7 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 175228 | 02368 | 17.6 | Solar | 05_07_797W23 | 01/06/2015 | 01/06/2015 | 9 | 4 | 5 | 01/17/2015 | 01/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 10/6/2015 | 10/6/2015 | 6/17/2016 | Connected |  | N
National Grid | BROCKTON | 184255 | 02302 | 7.6 | Solar | 05_05_9L1 | 06/11/2018 | 06/11/2018 | 13 | 3 | 10 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 |  | 7/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | GRANBY | 666118 | 01033 | 5.76 | Solar | 05_01_11J354 | 01/16/2025 | 01/29/2025 | 4 | 0 | 4 | 01/30/2025 | 01/30/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 178644 | 01095 | 1000 | Solar | 05_09_139L3 | 12/15/2017 | 01/05/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2018 | 02/06/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2018 | 12/15/2017 | 12/31/2020 | Y | STD | 687 | 04/24/2020 | 10/27/2020 | 187 | 5 | 182 | 12/9/2020 | 12/8/2020 | 12/22/2020 | Connected |  | N
National Grid | NORTHAMPTON | 177813 | 01062 | 7.6 | Solar | 05_07_97W3 | 03/31/2017 | 03/31/2017 | 5 | 2 | 3 | 04/07/2017 | 04/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 4/5/2018 | N | EXP | 36 |  |  | 0 | 0 | 0 | 12/15/2017 | 12/15/2017 | 12/15/2017 | Connected |  | N
National Grid | MARLBOROUGH | 548794 | 01752 | 6 | Solar | 05_07_91W40 | 08/25/2023 | 08/28/2023 | 1 | 0 | 1 | 08/29/2023 | 08/29/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 | 08/25/2023 | 11/24/2024 | Y | EXP | 365 | 01/30/2024 | 02/06/2024 | 8 | 0 | 8 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 175426 | 02333 | 280 | Solar | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/29/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 188150 | 02703 | 172.8 | Solar | 05_05_3422W1 | 06/15/2018 | 06/15/2018 | 18 | 1 | 17 |  |  | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 714408 | 01605 | 7.6 | Solar | 05_09_909W4 | 08/25/2025 | 10/21/2025 | 3 | 0 | 3 | 10/22/2025 | 10/22/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | HAMPDEN | 728722 | 01036 | 11.5 | Solar | 05_05_317W8 | 10/23/2025 | 10/27/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 175295 | 02368 | 21.2 | Solar | 05_07_797W23 | 01/14/2015 | 01/14/2015 | 4 | 1 | 3 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2015 | 01/14/2015 | 12/31/2016 | Y | EXP | 683 | 11/04/2016 | 11/15/2016 | 6 | 0 | 6 | 1/12/2017 | 1/12/2017 | 1/24/2017 | Connected |  | N
National Grid | BROCKTON | 189370 | 02302 | 5 | Solar | 05_05_9L1 | 07/05/2018 | 07/05/2018 | 6 | 0 | 6 | 08/13/2018 | 08/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2018 |  | 8/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2018 | Connected |  | N
National Grid | GRANBY | 669755 | 01033 | 5.76 | Solar | 05_01_11J354 | 02/04/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 186355 | 02038 | 21 | Solar | 05_09_139L3 | 05/25/2018 | 05/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 178683 | 01062 | 149.4 | Solar | 05_07_97W3 | 12/18/2017 | 12/18/2017 | 49 | 41 | 8 | 03/12/2018 | 03/12/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2018 |  | 6/30/2020 | N | EXP | 285 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 554168 | 01752 | 10 | Solar | 05_07_91W40 | 09/25/2023 | 09/29/2023 | 4 | 0 | 4 | 10/02/2023 | 10/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 | 09/25/2023 | 11/22/2024 | Y | EXP | 365 | 01/30/2024 | 01/31/2024 | 2 | 0 | 2 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 175425 | 02324 | 499 | Solar | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 | 09/18/2014 | 3/15/2016 | Y | STD | 168 |  |  | 0 | 0 | 0 | 12/27/2016 | 12/27/2016 | 12/27/2016 | Connected |  | N
National Grid | ATTLEBORO | 188144 | 02703 | 345.6 | Solar | 05_05_3422W1 | 06/15/2018 | 06/15/2018 | 11 | 11 | 0 |  |  | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 223132 | 01605 | 133.2 | Solar | 05_12_10C2 | 04/27/2019 | 05/21/2019 | 17 | 15 | 2 | 05/22/2019 | 05/22/2019 | 16 | 5 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  | 3/31/2021 | N | EXP | 72 |  |  | 0 | 0 | 0 |  |  | 5/20/2021 | Connected |  | N
National Grid | HAMPDEN | 176029 | 01036 | 23.75 | Solar | 05_05_317W8 | 06/16/2015 | 06/16/2015 | 22 | 22 | 0 | 07/21/2015 | 07/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 |  | 6/22/2016 | N | EXP | 33 |  |  | 0 | 0 | 0 | 12/10/2015 | 12/10/2015 | 12/10/2015 | Connected |  | N
National Grid | RANDOLPH | 176549 | 02368 | 9.6 | Solar | 05_07_797W23 | 04/05/2016 | 04/05/2016 | 1 | 1 | 0 | 04/06/2016 | 04/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 | 04/05/2016 | 4/10/2017 | Y | EXP | 356 | 11/10/2016 | 11/21/2016 | 6 | 0 | 6 | 11/28/2016 | 11/28/2016 | 11/30/2016 | Connected |  | N
National Grid | BROCKTON | 245118 | 02302 | 0 | Solar | 05_05_9L1 | 07/24/2019 | 07/30/2019 | 3 | 0 | 3 | 07/31/2019 | 07/31/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 737631 | 01033 | 4.56 | Solar | 05_01_11J357 | 12/02/2025 | 12/12/2025 | 1 | 0 | 1 | 12/23/2025 | 12/23/2025 | 49 | 34 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WILBRAHAM | 195698 | 01095 | 0 | Solar | 05_09_139L3 | 06/25/2019 |  | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 193636 | 01062 | 10 | Solar | 05_07_97W3 | 08/15/2018 | 10/08/2018 | 46 | 22 | 24 | 11/02/2018 | 11/02/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2019 | 08/15/2018 | 10/8/2020 | Y | EXP | 365 | 10/23/2019 | 11/13/2019 | 21 | 0 | 21 |  |  | 1/3/2020 | Connected |  | N
National Grid | MARLBOROUGH | 583557 | 01752 | 4.35 | Solar | 05_07_91W40 | 02/08/2024 | 02/12/2024 | 2 | 0 | 2 | 02/13/2024 | 02/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 175424 | 02333 | 499 | Solar | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 | 09/18/2014 | 2/14/2017 | Y | STD | 54 |  |  | 0 | 0 | 0 | 12/27/2016 | 12/27/2016 | 12/27/2016 | Connected |  | N
National Grid | ATTLEBORO | 188139 | 02703 | 259.2 | Solar | 05_05_3422W1 | 06/14/2018 | 06/14/2018 | 10 | 10 | 0 |  |  | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176945 | 01605 | 43.2 | Solar | 05_12_10J5 | 12/20/2016 | 12/20/2016 | 9 | 8 | 1 | 01/05/2017 | 01/05/2017 | 107 | 0 | 107 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2017 |  | 12/26/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 343536 | 01095 | 100 | Solar | 05_05_317W8 | 02/26/2021 | 03/15/2021 | 10 | 0 | 10 | 03/16/2021 | 03/16/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2021 |  | 7/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2022 | Connected |  | N
National Grid | RANDOLPH | 176822 | 02368 | 10 | Solar | 05_07_797W23 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 1/20/2017 | N | EXP | 346 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 11/21/2016 | Connected |  | N
National Grid | BROCKTON | 319753 | 02302 | 2.4 | Solar | 05_05_9L1 | 11/06/2020 | 11/12/2020 | 2 | 0 | 2 | 11/13/2020 | 11/13/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/06/2020 | 5/7/2022 | Y | EXP | 52 | 09/17/2021 | 10/15/2021 | 29 | 0 | 29 |  |  | 5/6/2022 | Connected |  | N
National Grid | GRANBY | 651292 | 01033 | 6.46 | Solar | 05_01_11J357 | 11/01/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | HAMPDEN | 460717 | 01036 | 17.98 | Solar | 05_09_139L3 | 10/04/2022 | 10/10/2022 | 4 | 1 | 3 | 10/11/2022 | 10/11/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2022 |  | 1/13/2024 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 247656 | 01062 | 5 | Solar | 05_07_97W3 | 09/25/2019 | 09/30/2019 | 2 | 0 | 2 | 10/01/2019 | 10/01/2019 | 19 | 16 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2019 | 09/25/2019 | 9/25/2020 | Y | EXP | 365 | 03/04/2020 | 05/08/2020 | 65 | 0 | 65 |  |  | 6/18/2020 | Connected |  | N
National Grid | MARLBOROUGH | 609945 | 01752 | 6 | Solar | 05_07_91W40 | 05/09/2024 | 06/06/2024 | 2 | 0 | 2 | 06/07/2024 | 06/07/2024 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 | 05/09/2024 | 9/30/2025 | Y | EXP | 365 | 03/08/2025 | 04/10/2025 | 34 | 0 | 34 |  |  | 4/23/2025 | Connected |  | N
National Grid | BRIDGEWATER | 175430 | 02333 | 499 | Solar | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 | 09/18/2014 | 2/14/2017 | Y | STD | 54 |  |  | 0 | 0 | 0 | 12/27/2016 | 12/27/2016 | 12/27/2016 | Connected |  | N
National Grid | ATTLEBORO | 188306 | 02760 | 259.2 | Solar | 05_05_3422W1 | 06/18/2018 | 06/18/2018 | 11 | 11 | 0 |  |  | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174223 | 01605 | 500 |  | 05_12_10J6 | 02/09/2012 | 02/09/2012 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/26/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 625321 | 01095 | 0 | Other | 05_05_318W1 | 01/16/2025 | 05/01/2025 | 72 | 63 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2025 | 05/30/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RANDOLPH | 177199 | 02368 | 3.8 | Solar | 05_07_797W23 | 02/01/2017 | 02/01/2017 | 2 | 2 | 0 | 02/03/2017 | 02/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2017 |  | 2/6/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/21/2017 | 8/21/2017 | 8/21/2017 | Connected |  | N
National Grid | BROCKTON | 324117 | 02302 | 133.2 | Solar | 05_05_9L1 | 11/12/2020 | 12/08/2020 | 16 | 12 | 4 | 12/09/2020 | 12/09/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2021 |  | 11/19/2022 | N | EXP | 386 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 657184 | 01033 | 5.76 | Solar | 05_01_11J357 | 11/26/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/26/2024 | 2/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 506045 | 01095 | 10 | Solar | 05_09_139L3 | 03/16/2023 | 03/22/2023 | 5 | 2 | 3 | 03/23/2023 | 03/23/2023 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 03/16/2023 | 6/4/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2023 | Connected |  | N
National Grid | EVERETT | 271946 | 02149 | 15.2 | Solar | 05_07_97W3 | 01/06/2020 | 01/17/2020 | 6 | 6 | 0 | 01/21/2020 | 01/21/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2020 |  | 1/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2020 | Connected |  | N
National Grid | MARLBOROUGH | 616891 | 01752 | 3.8 | Solar | 05_07_91W40 | 06/10/2024 | 06/17/2024 | 1 | 0 | 1 | 06/18/2024 | 06/18/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | BRIDGEWATER | 175588 | 02333 | 2000 | Solar | 05_09_527L1 | 04/21/2014 | 04/21/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2014 | 05/29/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 |  | 12/31/2016 | N | STD | 722 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 188304 | 02703 | 302.4 | Solar | 05_05_3422W1 | 06/18/2018 | 06/18/2018 | 13 | 13 | 0 |  |  | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174222 | 01605 | 500 |  | 05_12_10J6 | 02/07/2012 | 02/07/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 174933 | 01095 | 371.2 | Solar | 05_05_318W1 | 08/29/2013 | 08/29/2013 | 7 | 0 | 7 | 09/11/2013 | 09/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2014 | 08/29/2013 | 10/30/2014 | Y | EXP | 29 | 04/02/2015 | 04/10/2015 | 6 | 0 | 6 | 5/22/2015 | 5/22/2015 | 5/22/2015 | Connected |  | N
National Grid | RANDOLPH | 177198 | 02368 | 7.6 | Solar | 05_07_797W23 | 02/01/2017 | 02/01/2017 | 2 | 2 | 0 | 02/03/2017 | 02/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2017 |  | 2/6/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/23/2017 | 10/23/2017 | 10/23/2017 | Connected |  | N
National Grid | BROCKTON | 353933 | 02302 | 200 | Solar | 05_05_9L1 | 07/14/2021 | 08/10/2021 | 19 | 10 | 9 | 08/11/2021 | 08/11/2021 | 27 | 3 | 24 | 12/09/2021 | 09/15/2023 | 443 | 40 | 403 |  |  | 0 | 0 | 0 |  | 09/15/2023 | 443 | 40 | 403 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 669842 | 01033 | 3.8 | Solar | 05_01_11J357 | 02/04/2025 | 02/27/2025 | 2 | 0 | 2 | 02/28/2025 | 02/28/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/04/2025 | 5/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 682735 | 01095 | 11.4 | Solar | 05_09_139L3 | 04/03/2025 | 05/13/2025 | 4 | 0 | 4 | 05/14/2025 | 05/14/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 318107 | 02149 | 9.57 | Solar | 05_07_97W3 | 10/08/2020 | 10/19/2020 | 6 | 6 | 0 | 10/20/2020 | 10/20/2020 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 10/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | Y
National Grid | MARLBOROUGH | 621865 | 01752 | 3.8 | Solar | 05_07_91W40 | 07/01/2024 | 07/10/2024 | 2 | 0 | 2 | 07/11/2024 | 07/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  | 7/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2024 | Connected |  | N
National Grid | BRIDGEWATER | 175644 | 02333 | 3.23 | Solar | 05_09_527L1 | 12/16/2014 | 12/16/2014 | 8 | 7 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2015 |  | 12/31/2016 | N | EXP | 71 |  |  | 0 | 0 | 0 | 7/20/2015 | 7/20/2015 | 1/8/2016 | Connected |  | N
National Grid | ATTLEBORO | 188303 | 02703 | 172.8 | Solar | 05_05_3422W1 | 06/18/2018 | 06/18/2018 | 6 | 5 | 1 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176188 | 01605 | 500 |  | 05_12_10J6 | 09/01/2015 | 09/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2015 | 09/29/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/8/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 177383 | 01036 | 366.3 | Solar | 05_05_318W1 | 11/28/2016 | 11/28/2016 | 0 | 0 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 |  | 12/4/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 | 6/22/2017 | 6/22/2017 | 6/27/2017 | Connected |  | N
National Grid | RANDOLPH | 177515 | 02368 | 143.2 | Solar | 05_07_797W23 | 07/14/2016 | 07/14/2016 | 1 | 1 | 0 | 07/15/2016 | 07/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2016 | 07/14/2016 | 7/19/2017 | Y | EXP | 33 | 12/05/2016 | 01/05/2017 | 21 | 0 | 21 | 2/15/2017 | 2/15/2017 | 2/23/2017 | Connected |  | N
National Grid | BROCKTON | 357046 | 02302 | 283.3 | Solar | 05_05_9L1 | 07/30/2021 | 01/27/2022 | 123 | 113 | 10 |  |  | 123 | 99 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LUDLOW | 175482 | 01056 | 47.3 | Solar | 05_01_12J376 | 03/21/2014 | 03/21/2014 | 5 | 1 | 4 | 04/01/2014 | 04/01/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2014 |  | 5/30/2014 | N | EXP | 51 |  |  | 0 | 0 | 0 | 4/14/2014 | 4/14/2014 | 7/11/2014 | Connected |  | N
National Grid | HAMPDEN | 683586 | 01036 | 10 | Solar | 05_09_139L3 | 04/08/2025 | 04/30/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 |  | 6/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 318700 | 02149 | 6 | Solar | 05_07_97W3 | 11/23/2020 | 12/10/2020 | 11 | 9 | 2 | 12/11/2020 | 12/11/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2021 | Connected |  | N
National Grid | MARLBOROUGH | 625778 | 01752 | 7.6 | Solar | 05_07_91W40 | 07/18/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/16/2024 | Connected |  | N
National Grid | BRIDGEWATER | 175908 | 02333 | 374 | Solar | 05_09_527L1 | 09/30/2015 | 09/30/2015 | 8 | 8 | 0 | 10/16/2015 | 10/16/2015 | 0 | 0 | 0 | 01/06/2016 | 04/08/2016 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  | 04/08/2016 | 64 | 0 | 64 |  |  | 0 | 0 | 0 | 2/9/2018 |  | 12/14/2018 | N | EXP | 38 |  |  | 0 | 0 | 0 | 2/9/2018 | 2/9/2018 | 2/9/2018 | Connected |  | N
National Grid | ATTLEBORO | 188301 | 02703 | 302.4 | Solar | 05_05_3422W1 | 06/18/2018 | 06/18/2018 | 10 | 10 | 0 |  |  | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 683221 | 01605 | 15.2 | Solar | 05_12_11J1 | 04/08/2025 | 04/10/2025 | 2 | 0 | 2 | 04/11/2025 | 04/11/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2025 | Connected |  | N
National Grid | WILBRAHAM | 178048 | 01095 | 750 | Solar | 05_05_318W1 | 05/05/2017 | 05/05/2017 | 15 | 13 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2017 | 06/15/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 01/16/2018 | 10/25/2019 | 449 | 20 | 429 | 12/21/2018 | 05/05/2017 | 2/19/2021 | Y | STD | 5 | 01/04/2020 | 12/16/2020 | 347 | 5 | 342 |  |  | 2/12/2021 | Connected |  | N
National Grid | HOLBROOK | 177931 | 02343 | 7.6 | Solar | 05_07_797W23 | 04/20/2017 | 04/20/2017 | 7 | 7 | 0 | 05/01/2017 | 05/01/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2017 |  | 4/25/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 | 9/5/2017 | 9/5/2017 | 9/5/2017 | Connected |  | N
National Grid | BROCKTON | 356799 | 02302 | 375 | Solar | 05_05_9L1 | 07/14/2021 | 08/12/2021 | 21 | 11 | 10 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 | 07/14/2021 | 1/10/2024 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 651009 | 01033 | 5.76 | Solar | 05_01_12J376 | 11/12/2024 | 12/04/2024 | 4 | 0 | 4 | 12/05/2024 | 12/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | WILBRAHAM | 683852 | 01095 | 16.24 | Solar | 05_09_139L3 | 04/09/2025 | 04/15/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | EVERETT | 333373 | 02149 | 9.36 | Solar | 05_07_97W3 | 01/23/2021 | 01/27/2021 | 2 | 0 | 2 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/23/2021 | 4/20/2022 | Y | EXP | 365 | 03/03/2022 | 03/07/2022 | 5 | 0 | 5 |  |  | 3/15/2022 | Connected |  | N
National Grid | MARLBOROUGH | 626535 | 01752 | 7.6 | Solar | 05_07_91W40 | 07/22/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 31 | 22 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 07/22/2024 | 11/22/2025 | Y | EXP | 365 | 02/11/2025 | 02/10/2025 | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | BRIDGEWATER | 175997 | 02333 | 10 | Solar | 05_09_527L1 | 06/11/2015 | 06/11/2015 | 2 | 2 | 0 | 06/16/2015 | 06/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2015 |  | 6/17/2016 | N | EXP | 347 |  |  | 0 | 0 | 0 | 7/6/2015 | 7/6/2015 | 1/12/2016 | Connected |  | N
National Grid | ATTLEBORO | 193188 | 02703 | 1500 | Solar | 05_05_3422W1 | 08/30/2018 | 10/17/2018 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2018 | 11/15/2018 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 704611 | 01605 | 249 | Solar | 05_12_11J13 | 10/17/2025 | 10/31/2025 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2025 |  | 83 | 65 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WILBRAHAM | 178327 | 01095 | 1300 | Solar | 05_05_318W1 | 03/30/2018 | 03/30/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 06/18/2018 | 54 | 32 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/4/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 178409 | 02343 | 10000 | Other | 05_07_797W23 | 11/22/2017 | 11/22/2017 | 89 | 82 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/2/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 422661 | 02302 | 0 | Other | 05_05_9L1 | 08/18/2022 | 09/19/2022 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2022 | 10/18/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 685935 | 01007 | 7.6 | Solar | 05_01_12J377 | 04/17/2025 | 05/08/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | E LONGMEADOW | 742844 | 01028 | 7.6 | Solar | 05_09_139L5 | 01/12/2026 | 01/13/2026 | 1 | 0 | 1 | 01/30/2026 | 01/30/2026 | 25 | 14 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | EVERETT | 336483 | 02149 | 10 | Solar | 05_07_97W3 | 01/12/2021 | 01/15/2021 | 2 | 0 | 2 | 01/19/2021 | 01/19/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 632647 | 01752 | 4.06 | Solar | 05_07_91W40 | 08/14/2024 | 08/22/2024 | 3 | 0 | 3 | 08/23/2024 | 08/23/2024 | 16 | 10 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/14/2024 | 10/28/2025 | Y | EXP | 365 | 03/08/2025 | 03/19/2025 | 12 | 0 | 12 |  |  | 3/25/2025 | Connected |  | N
National Grid | BRIDGEWATER | 175993 | 02333 | 4.95 | Solar | 05_09_527L1 | 06/10/2015 | 06/10/2015 | 6 | 6 | 0 | 06/22/2015 | 06/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2015 |  | 6/16/2016 | N | EXP | 336 |  |  | 0 | 0 | 0 | 4/13/2016 | 4/13/2016 | 4/19/2016 | Connected |  | N
National Grid | ATTLEBORO | 223811 | 02703 | 0 | Solar | 05_05_3422W1 | 04/30/2019 | 05/01/2019 | 0 | 0 | 0 | 05/02/2019 | 05/02/2019 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2019 |  | 7/8/2019 | N | EXP | 62 |  |  | 0 | 0 | 0 |  |  | 7/1/2019 | Connected |  | N
National Grid | WORCESTER | 177474 | 01605 | 7.5 | Solar | 05_12_11J13 | 07/06/2016 | 07/06/2016 | 26 | 26 | 0 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2016 | 07/06/2016 | 7/12/2017 | Y | EXP | 328 |  |  | 0 | 0 | 0 | 1/27/2017 | 1/27/2017 | 1/27/2017 | Connected |  | N
National Grid | HAMPDEN | 482180 | 01036 | 1800 | Solar | 05_05_318W3 | 07/06/2023 | 10/25/2023 | 78 | 68 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 | 11/16/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HOLBROOK | 178602 | 02343 | 500 | Solar | 05_07_797W23 | 04/06/2018 | 04/06/2018 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/07/2018 | 07/11/2018 | 50 | 11 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 442263 | 02302 | 11.6 | Solar | 05_05_9L1 | 08/03/2022 | 08/31/2022 | 21 | 20 | 1 | 09/01/2022 | 09/01/2022 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2022 |  | 10/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2022 | Connected |  | N
National Grid | BELCHERTOWN | 670626 | 01007 | 3.8 | Solar | 05_01_12J377 | 02/06/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | E LONGMEADOW | 748915 | 01028 | 7.6 | Solar | 05_09_139L5 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MEDFORD | 354572 | 02155 | 3.8 | Solar | 05_07_97W3 | 05/27/2021 | 12/11/2021 | 1 | 0 | 1 | 06/02/2021 | 06/02/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2021 | 05/27/2021 | 12/11/2022 | Y | EXP | 365 | 12/07/2021 | 12/09/2021 | 3 | 0 | 3 |  |  | 3/17/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 639571 | 01532 | 6 | Solar | 05_07_91W40 | 09/12/2024 | 09/27/2024 | 7 | 6 | 1 | 09/30/2024 | 09/30/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 | 09/12/2024 | 12/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | BRIDGEWATER | 176077 | 02333 | 0 | Solar | 05_09_527L1 | 08/20/2015 | 08/20/2015 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/31/2015 | 09/29/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/30/2015 |  | 599 | 0 | 599 |  |  | 4/15/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 243834 | 02703 | 0 | Solar | 05_05_3422W1 | 07/16/2019 | 07/23/2019 | 4 | 0 | 4 | 07/24/2019 | 07/24/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2019 | Connected |  | N
National Grid | WORCESTER | 178131 | 01605 | 7.6 | Solar | 05_12_11J13 | 07/12/2017 | 07/12/2017 | 3 | 0 | 3 | 07/17/2017 | 07/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2017 |  | 7/17/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 10/17/2017 | 10/17/2017 | 10/17/2017 | Connected |  | N
National Grid | WILBRAHAM | 619605 | 01095 | 4980 | Solar | 05_05_318W3 | 07/17/2024 | 08/21/2024 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2024 | 08/29/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RANDOLPH | 178599 | 02368 | 72 | Solar | 05_07_797W23 | 04/06/2018 | 04/06/2018 | 1 | 0 | 1 | 04/10/2018 | 04/10/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2018 |  | 4/14/2019 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 12/18/2018 | Connected |  | N
National Grid | BROCKTON | 453607 | 02302 | 5 | Solar | 05_05_9L1 | 09/12/2022 | 09/12/2022 | 0 | 0 | 0 | 09/13/2022 | 09/13/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 | 09/12/2022 | 10/26/2023 | Y | EXP | 365 | 01/07/2023 | 01/06/2023 | 0 | 0 | 0 |  |  | 1/10/2023 | Connected |  | N
National Grid | GRANBY | 177106 | 01033 | 120 | Solar | 05_01_12J391 | 05/27/2016 | 05/27/2016 | 3 | 3 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2016 |  | 6/5/2017 | N | EXP | 34 |  |  | 0 | 0 | 0 | 12/6/2016 | 12/6/2016 | 12/6/2016 | Connected |  | N
National Grid | E LONGMEADOW | 754518 | 01028 | 210.3 | Solar | 05_09_139L5 | 03/06/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MEDFORD | 534192 | 02155 | 5.76 | Solar | 05_07_97W3 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 22 | 0 | 22 | 08/29/2023 | 10/02/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 10/02/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 10/6/2023 |  | 10/22/2024 | N | EXP | 365 | 12/21/2023 | 02/08/2024 | 49 | 1 | 48 |  |  | 4/15/2024 | Connected |  | N
National Grid | MARLBOROUGH | 641061 | 01752 | 10 | Solar | 05_07_91W40 | 09/17/2024 | 10/02/2024 | 9 | 6 | 3 | 10/03/2024 | 10/03/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  | 11/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 176332 | 02333 | 7.6 | Solar | 05_09_527L1 | 09/15/2015 | 09/15/2015 | 4 | 4 | 0 | 09/22/2015 | 09/22/2015 | 345 | 0 | 345 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 |  | 9/21/2016 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 295996 | 02703 | 5 | Solar | 05_05_3422W1 | 06/12/2020 | 06/16/2020 | 1 | 0 | 1 | 06/17/2020 | 06/17/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2020 | 06/12/2020 | 6/14/2021 | Y | EXP | 365 | 12/04/2020 | 01/19/2021 | 46 | 0 | 46 |  |  | 5/19/2021 | Connected |  | N
National Grid | WORCESTER | 195807 | 01606 | 496 | Solar | 05_12_11J13 | 09/13/2018 | 09/21/2018 | 6 | 4 | 2 | 09/24/2018 | 09/24/2018 | 5 | 0 | 5 | 12/03/2018 | 01/17/2019 | 32 | 5 | 27 |  |  | 0 | 0 | 0 |  | 01/17/2019 | 32 | 5 | 27 |  |  | 0 | 0 | 0 | 3/28/2019 | 09/13/2018 | 10/16/2020 | Y | EXP | 551 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LONGMEADOW | 692505 | 01028 | 3.8 | Solar | 05_05_318W3 | 05/18/2025 | 11/26/2025 | 1 | 0 | 1 | 02/09/2026 | 02/09/2026 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 186356 | 02368 | 15.2 | Solar | 05_07_797W23 | 08/22/2018 | 10/11/2018 | 9 | 9 | 0 | 10/12/2018 | 10/12/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 08/22/2018 | 8/20/2019 | Y | EXP | 38 | 05/10/2019 | 06/05/2019 | 26 | 0 | 26 |  |  | 8/8/2019 | Connected |  | N
National Grid | BROCKTON | 471193 | 02302 | 120 | Solar | 05_05_9L1 | 11/01/2022 | 11/10/2022 | 8 | 1 | 7 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 650869 | 01007 | 5.235 | Solar | 05_01_13J350 | 10/30/2024 | 11/18/2024 | 6 | 2 | 4 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | E LONGMEADOW | 176488 | 01028 | 7.6 | Solar | 05_09_139L5 | 12/09/2015 | 12/09/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2015 |  | 12/14/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/11/2016 | 8/11/2016 | 8/11/2016 | Connected |  | N
National Grid | MEDFORD | 535946 | 02155 | 5.76 | Solar | 05_07_97W3 | 07/05/2023 | 07/06/2023 | 2 | 1 | 1 | 07/07/2023 | 07/07/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2023 | 07/05/2023 | 8/9/2024 | Y | EXP | 365 | 10/19/2023 | 10/20/2023 | 2 | 0 | 2 |  |  | 10/23/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 647766 | 01532 | 6.09 | Solar | 05_07_91W40 | 10/17/2024 | 11/12/2024 | 12 | 9 | 3 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/17/2024 | 12/31/2025 | Y | EXP | 365 | 04/15/2025 | 05/16/2025 | 32 | 0 | 32 |  |  | 5/19/2025 | Connected |  | N
National Grid | BRIDGEWATER | 176449 | 02333 | 17.4 | Solar | 05_09_527L1 | 05/18/2016 | 05/18/2016 | 0 | 0 | 0 | 05/18/2016 | 05/18/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2016 |  | 5/23/2017 | N | EXP | 344 |  |  | 0 | 0 | 0 | 7/13/2016 | 7/13/2016 | 7/13/2016 | Connected |  | N
National Grid | ATTLEBORO | 318964 | 02703 | 19.25 | Solar | 05_05_3422W1 | 10/13/2020 | 10/14/2020 | 1 | 1 | 0 | 10/15/2020 | 10/15/2020 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2021 | Connected |  | N
National Grid | WORCESTER | 294723 | 01605 | 8 | Solar | 05_12_11J13 | 06/03/2020 | 06/29/2020 | 17 | 14 | 3 | 06/30/2020 | 06/30/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2020 | 06/03/2020 | 9/9/2021 | Y | EXP | 365 | 12/11/2020 | 02/05/2021 | 56 | 0 | 56 |  |  | 2/19/2021 | Connected |  | N
National Grid | LONGMEADOW | 709064 | 01028 | 5.76 | Solar | 05_05_318W3 | 08/04/2025 | 08/07/2025 | 3 | 0 | 3 | 08/08/2025 | 08/08/2025 | 80 | 60 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 08/04/2025 | 12/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | RANDOLPH | 273621 | 02368 | 7.6 | Solar | 05_07_797W23 | 01/28/2020 | 02/04/2020 | 5 | 5 | 0 | 02/05/2020 | 02/05/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2020 |  | 1/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2020 | Connected |  | N
National Grid | BROCKTON | 485614 | 02302 | 15.2 | Solar | 05_05_9L1 | 12/15/2022 | 12/27/2022 | 7 | 4 | 3 | 12/28/2022 | 12/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 |  | 2/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2023 | Connected |  | N
National Grid | GRANBY | 261693 | 01033 | 4900 | Natural Gas | 05_01_13J358 | 06/26/2020 | 07/09/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 08/19/2020 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2021 | 06/26/2020 | 11/1/2022 | Y | STD | 532 | 06/08/2022 | 10/19/2022 | 134 | 0 | 134 |  |  | 10/26/2022 | Connected |  | N
National Grid | E LONGMEADOW | 184049 | 01028 | 10.32 | Solar | 05_09_139L5 | 07/02/2018 | 07/02/2018 | 18 | 5 | 13 | 07/27/2018 | 07/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  |  | N | EXP | 476 |  |  | 0 | 0 | 0 |  |  | 11/22/2019 | Connected |  | N
National Grid | MEDFORD | 546998 | 02155 | 11.34 | Solar | 05_07_97W3 | 08/28/2023 | 09/05/2023 | 6 | 5 | 1 | 09/06/2023 | 09/06/2023 | 24 | 0 | 24 | 11/21/2023 | 01/05/2024 | 31 | 3 | 28 |  |  | 0 | 0 | 0 |  | 01/05/2024 | 31 | 3 | 28 |  |  | 0 | 0 | 0 | 1/10/2024 |  | 2/11/2025 | N | EXP | 365 | 05/02/2024 | 06/01/2024 | 31 | 0 | 31 |  |  | 6/6/2024 | Connected |  | N
National Grid | BERLIN | 655817 | 01503 | 5.76 | Solar | 05_07_91W40 | 11/20/2024 | 01/15/2025 | 19 | 13 | 6 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 176653 | 02333 | 10 | Solar | 05_09_527L1 | 02/17/2016 | 02/17/2016 | 3 | 3 | 0 | 02/23/2016 | 02/23/2016 | 234 | 0 | 234 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2016 |  | 2/23/2017 | N | EXP | 332 |  |  | 0 | 0 | 0 | 3/28/2016 | 3/28/2016 |  | Withdrawn |  | N
National Grid | ATTLEBORO | 326235 | 02703 | 9.8 | Solar | 05_05_3422W1 | 12/22/2020 | 12/30/2020 | 4 | 0 | 4 | 12/31/2020 | 12/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/22/2020 | 3/8/2022 | Y | EXP | 365 | 09/04/2021 | 10/12/2021 | 13 | 0 | 13 |  |  | 2/3/2022 | Connected |  | N
National Grid | WORCESTER | 682764 | 01606 | 7.6 | Solar | 05_12_11J13 | 04/03/2025 | 04/16/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | LONGMEADOW | 742068 | 01028 | 45.6 | Solar | 05_05_318W3 | 12/31/2025 | 01/21/2026 | 13 | 11 | 2 | 01/22/2026 | 01/22/2026 | 31 | 19 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HOLBROOK | 300143 | 02343 | 9.8 | Solar | 05_07_797W23 | 09/16/2020 | 09/21/2020 | 2 | 0 | 2 | 09/22/2020 | 09/22/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 | 09/16/2020 | 1/13/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2021 | Connected |  | N
National Grid | BROCKTON | 556357 | 02302 | 199.8 | Solar | 05_05_9L1 | 01/08/2024 | 06/11/2024 | 107 | 97 | 10 |  |  | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 | 01/08/2024 | 1/5/2026 | Y | STD | 224 | 05/09/2025 | 05/14/2025 | 6 | 0 | 6 |  |  | 12/10/2025 | Connected |  | N
National Grid | GRANBY | 684614 | 01033 | 15.2 | Solar | 05_01_13J358 | 04/12/2025 | 04/14/2025 | 1 | 0 | 1 | 04/15/2025 | 04/15/2025 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | E LONGMEADOW | 186850 | 01028 | 7.6 | Solar | 05_09_139L5 | 06/15/2018 | 06/15/2018 | 20 | 17 | 3 | 07/17/2018 | 07/17/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 548813 | 02155 | 10 | Solar | 05_07_97W3 | 08/30/2023 | 09/12/2023 | 9 | 8 | 1 | 09/13/2023 | 09/13/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 | 08/30/2023 | 11/5/2024 | Y | EXP | 365 | 01/04/2024 | 02/08/2024 | 36 | 0 | 36 |  |  | 2/29/2024 | Connected |  | Y
National Grid | BOLTON | 660096 | 01740 | 7.6 | Solar | 05_07_91W40 | 12/11/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 177036 | 02333 | 1980 | Solar | 05_09_527L1 | 07/26/2016 | 07/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2016 | 08/24/2016 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 330825 | 02703 | 11.52 | Solar | 05_05_3422W1 | 12/10/2020 | 01/28/2021 | 31 | 26 | 5 | 01/29/2021 | 01/29/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2021 |  | 1/28/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 553658 | 01606 | 10 | Solar | 05_12_11J2 | 09/11/2023 | 09/12/2023 | 1 | 0 | 1 | 09/13/2023 | 09/13/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 | 09/11/2023 | 10/26/2024 | Y | EXP | 365 | 02/09/2024 | 05/18/2024 | 100 | 0 | 100 |  |  | 5/21/2024 | Connected |  | N
National Grid | LONGMEADOW | 174857 | 01028 | 750 | Solar | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | RANDOLPH | 330658 | 02368 | 10 | Solar | 05_07_797W23 | 12/09/2020 | 01/07/2021 | 19 | 14 | 5 | 01/08/2021 | 01/08/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 1/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2021 | Connected |  | N
National Grid | BROCKTON | 645296 | 02302 | 10 | Solar | 05_05_9L1 | 10/07/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/07/2024 | 12/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | GRANBY | 503254 | 01033 | 6.09 | Solar | 05_01_14J367 | 03/29/2023 | 03/31/2023 | 2 | 0 | 2 | 04/03/2023 | 04/03/2023 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2023 | 03/29/2023 | 11/28/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N
National Grid | E LONGMEADOW | 188147 | 01028 | 7.6 | Solar | 05_09_139L5 | 06/14/2018 | 06/14/2018 | 3 | 3 | 0 | 09/14/2018 | 09/14/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 551665 | 02155 | 7.6 | Solar | 05_07_97W3 | 10/11/2023 | 10/16/2023 | 3 | 0 | 3 | 10/17/2023 | 10/17/2023 | 49 | 28 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 | 10/11/2023 | 1/29/2025 | Y | EXP | 365 | 04/25/2024 | 08/14/2024 | 112 | 0 | 112 |  |  | 8/23/2024 | Connected |  | N
National Grid | BERLIN | 425562 | 01503 | 999 | Solar | 05_07_91W41 | 08/15/2022 | 09/06/2022 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/07/2022 | 09/28/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/15/2022 | 1/4/2027 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | EAST BRIDGEWATER | 177035 | 02333 | 990 | Solar | 05_09_527L1 | 07/26/2016 | 07/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2016 | 08/24/2016 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 387717 | 02703 | 2000 | Solar | 05_05_3422W1 | 10/27/2021 | 12/16/2021 | 35 | 25 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 646492 | 01606 | 7.6 | Solar | 05_12_11J2 | 10/11/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/11/2024 | 1/3/2026 | Y | EXP | 365 | 03/15/2025 | 03/21/2025 | 7 | 0 | 7 |  |  | 4/17/2025 | Connected |  | N
National Grid | LONGMEADOW | 174856 | 01028 | 750 | Solar | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | HOLBROOK | 340873 | 02343 | 15.2 | Solar | 05_07_797W23 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2021 | 02/05/2021 | 8/9/2023 | Y | EXP | 365 | 06/03/2022 | 06/28/2022 | 25 | 0 | 25 |  |  | 9/30/2022 | Connected |  | N
National Grid | BROCKTON | 645348 | 02302 | 5.76 | Solar | 05_05_9L1 | 10/07/2024 | 11/12/2024 | 11 | 7 | 4 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/07/2024 | 12/31/2025 | Y | EXP | 365 | 02/13/2025 | 02/19/2025 | 7 | 0 | 7 |  |  | 2/26/2025 | Connected |  | N
National Grid | GRANBY | 589307 | 01033 | 7.6 | Solar | 05_01_14J367 | 03/01/2024 | 03/05/2024 | 2 | 0 | 2 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 03/01/2024 | 3/22/2025 | Y | EXP | 365 | 05/15/2024 | 06/26/2024 | 43 | 0 | 43 |  |  | 6/27/2024 | Connected |  | N
National Grid | E LONGMEADOW | 188034 | 01028 | 3.8 | Solar | 05_09_139L5 | 06/15/2018 | 06/15/2018 | 2 | 0 | 2 | 07/03/2018 | 07/03/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2018 | 06/15/2018 | 3/4/2020 | Y | EXP | 572 | 10/17/2019 | 10/30/2019 | 13 | 0 | 13 |  |  | 10/31/2019 | Connected |  | N
National Grid | MEDFORD | 587439 | 02155 | 7.25 | Solar | 05_07_97W3 | 02/09/2024 | 03/07/2024 | 19 | 16 | 3 | 03/08/2024 | 03/08/2024 | 5 | 0 | 5 | 04/29/2024 | 05/02/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 05/02/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 5/3/2024 |  | 6/1/2025 | N | EXP | 365 | 06/13/2024 | 08/30/2024 | 79 | 0 | 79 |  |  | 10/2/2024 | Connected |  | N
National Grid | BERLIN | 651586 | 01053 | 5.76 | Solar | 05_07_91W41 | 11/13/2024 | 12/08/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/13/2024 | 1/29/2026 | Y | EXP | 365 | 05/07/2025 | 06/02/2025 | 27 | 0 | 27 |  |  |  | Completion Documents |  | N
National Grid | BRIDGEWATER | 177034 | 02333 | 3960 | Solar | 05_09_527L1 | 07/26/2016 | 07/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2016 | 08/24/2016 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 405839 | 02703 | 0 | Battery Add-On | 05_05_3422W1 | 01/23/2022 | 01/31/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 02/04/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 350691 | 01606 | 57.6 | Solar | 05_12_11J4 | 04/05/2021 | 12/20/2021 | 6 | 0 | 6 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2021 | 04/05/2021 | 1/2/2023 | Y | EXP | 365 | 08/06/2021 | 09/20/2021 | 24 | 3 | 21 |  |  | 1/27/2022 | Connected |  | N
National Grid | LONGMEADOW | 174855 | 01028 | 750 | Solar | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | RANDOLPH | 485389 | 02368 | 7.6 | Solar | 05_07_797W23 | 12/29/2022 | 01/03/2023 | 2 | 0 | 2 | 01/04/2023 | 01/04/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 649789 | 02302 | 8.7 | Solar | 05_05_9L1 | 10/25/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 647285 | 01033 | 3.8 | Solar | 05_01_14J367 | 10/21/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/21/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | E LONGMEADOW | 190514 | 01028 | 9.6 | Solar | 05_09_139L5 | 07/11/2018 | 08/29/2018 | 10 | 0 | 10 | 08/30/2018 | 08/30/2018 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2018 | 07/11/2018 | 10/29/2019 | Y | EXP | 37 | 05/11/2019 | 05/28/2019 | 17 | 0 | 17 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 608653 | 02148 | 10 | Solar | 05_07_97W3 | 05/03/2024 | 05/14/2024 | 3 | 0 | 3 | 05/15/2024 | 05/15/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2024 | Connected |  | N
National Grid | BERLIN | 736127 | 01503 | 11.168 | Solar | 05_07_91W41 | 01/06/2026 | 01/07/2026 | 1 | 0 | 1 | 01/15/2026 | 01/15/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BRIDGEWATER | 177166 | 02333 | 3000 | Solar | 05_09_527L1 | 01/25/2017 | 01/27/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2017 | 03/01/2017 | 22 | 14 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 | 01/25/2017 | 8/16/2021 | Y | STD | 21 | 06/02/2020 | 01/11/2021 | 224 | 5 | 219 | 7/22/2021 | 7/29/2021 | 7/29/2021 | Connected |  | N
National Grid | ATTLEBORO | 515278 | 02703 | 8.99 | Solar | 05_05_3422W1 | 05/25/2023 | 05/26/2023 | 1 | 0 | 1 | 05/30/2023 | 05/30/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2023 |  | 10/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | WORCESTER | 664189 | 01606 | 7.6 | Solar | 05_12_11J4 | 01/07/2025 | 01/27/2025 | 11 | 7 | 4 | 01/28/2025 | 01/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LONGMEADOW | 174894 | 01028 | 666 | Solar | 05_05_318W3 | 08/20/2013 | 08/20/2013 | 52 | 43 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2013 | 09/16/2014 | 213 | 0 | 213 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 491623 | 02343 | 7.6 | Solar | 05_07_797W23 | 05/01/2023 | 05/02/2023 | 1 | 0 | 1 | 05/03/2023 | 05/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | BROCKTON | 657139 | 02302 | 5.76 | Solar | 05_05_9L1 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 657562 | 01033 | 5.76 | Solar | 05_01_14J367 | 11/28/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | E LONGMEADOW | 218868 | 01028 | 10 | Solar | 05_09_139L5 | 04/11/2019 | 04/11/2019 | 0 | 0 | 0 | 04/12/2019 | 04/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2019 |  | 8/12/2019 | N | EXP | 116 |  |  | 0 | 0 | 0 |  |  | 7/31/2019 | Connected |  | N
National Grid | MALDEN | 608570 | 02148 | 6.93 | Solar | 05_07_97W3 | 05/03/2024 | 05/09/2024 | 2 | 0 | 2 | 05/10/2024 | 05/10/2024 | 85 | 75 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 748972 | 01503 | 10 | Solar | 05_07_91W41 | 02/03/2026 | 02/06/2026 | 3 | 0 | 3 | 02/24/2026 | 02/24/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BRIDGEWATER | 177200 | 02333 | 2.4 | Solar | 05_09_527L1 | 02/01/2017 | 02/01/2017 | 1 | 0 | 1 | 02/03/2017 | 02/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2017 |  | 2/7/2018 | N | EXP | 366 |  |  | 0 | 0 | 0 | 8/29/2017 | 8/29/2017 | 8/28/2017 | Connected |  | N
National Grid | ATTLEBORO | 601598 | 02703 | 0 | Other | 05_05_3422W1 | 04/25/2024 | 07/18/2024 | 56 | 48 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2024 | 08/12/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 438522 | 01606 | 50 | Solar | 05_12_12J3 | 07/22/2022 | 09/13/2022 | 36 | 26 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 6/9/2025 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | LONGMEADOW | 174960 | 01028 | 750 | Solar | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | RANDOLPH | 563367 | 02368 | 4980 | Solar | 05_07_797W23 | 02/28/2024 | 04/11/2024 | 32 | 22 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2024 | 04/24/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 672006 | 02302 | 5.76 | Solar | 05_05_9L1 | 02/13/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 704048 | 01033 | 7.6 | Solar | 05_01_14J367 | 07/11/2025 | 07/24/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 | 07/11/2025 | 9/9/2026 | Y | EXP | 365 | 02/03/2026 | 02/05/2026 | 3 | 0 | 3 |  |  | 2/17/2026 | Connected |  | N
National Grid | E LONGMEADOW | 224421 | 01028 | 5 | Solar | 05_09_139L5 | 05/07/2019 | 05/15/2019 | 6 | 6 | 0 | 05/16/2019 | 05/16/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 | 05/07/2019 | 2/28/2020 | Y | EXP | 269 | 10/25/2019 | 10/30/2019 | 5 | 0 | 5 |  |  | 11/7/2019 | Connected |  | N
National Grid | MEDFORD | 622060 | 02155 | 7.6 | Solar | 05_07_97W3 | 07/23/2024 | 09/06/2024 | 9 | 8 | 1 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 175573 | 01503 | 3720 | Solar | 05_07_91W41 | 10/15/2014 | 10/15/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2014 | 11/12/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2015 | 10/15/2014 | 9/30/2017 | Y | STD | 843 | 06/16/2017 | 08/08/2017 | 36 | 0 | 36 | 8/9/2017 | 8/9/2017 | 8/24/2017 | Connected |  | N
National Grid | EAST BRIDGEWATER | 177258 | 02333 | 10 | Solar | 05_09_527L1 | 08/18/2016 | 08/18/2016 | 1 | 1 | 0 | 08/22/2016 | 08/22/2016 | 99 | 0 | 99 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2016 |  | 8/24/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 609575 | 02703 | 10 | Solar | 05_05_3422W1 | 05/08/2024 | 05/16/2024 | 2 | 0 | 2 | 05/17/2024 | 05/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/08/2024 | 12/31/2025 | Y | EXP | 365 | 07/23/2024 | 09/03/2024 | 43 | 0 | 43 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 178448 | 01606 | 33.3 | Solar | 05_12_12J4 | 11/29/2017 | 11/29/2017 | 4 | 4 | 0 | 01/08/2018 | 01/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 | 11/29/2017 | 12/5/2018 | Y | EXP | 331 | 03/16/2018 | 03/16/2018 | 4 | 4 | 0 |  |  | 8/14/2018 | Connected |  | N
National Grid | LONGMEADOW | 177688 | 01028 | 4950 | Solar | 05_05_318W3 | 10/03/2017 | 10/24/2017 | 15 | 12 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2017 | 11/27/2017 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 | 10/03/2017 | 8/5/2021 | Y | STD | 16 | 03/14/2021 | 07/30/2021 | 138 | 0 | 138 | 6/18/2021 | 7/30/2021 | 7/30/2021 | Connected |  | N
National Grid | HOLBROOK | 572096 | 02343 | 13.05 | Solar | 05_07_797W23 | 01/22/2024 | 01/29/2024 | 6 | 4 | 2 | 01/30/2024 | 01/30/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 711687 | 02333 | 19.893 | Solar | 05_05_9L1 | 08/25/2025 | 09/05/2025 | 8 | 3 | 5 | 09/08/2025 | 09/08/2025 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 175455 | 01033 | 252 | Solar | 05_01_14J368 | 07/17/2014 | 07/17/2014 | 3 | 0 | 3 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 11/28/2014 | N | EXP | 53 |  |  | 0 | 0 | 0 | 12/15/2014 | 12/15/2014 | 3/23/2016 | Connected |  | N
National Grid | E LONGMEADOW | 223863 | 01028 | 8.74 | Solar | 05_09_139L5 | 06/21/2019 | 06/28/2019 | 4 | 0 | 4 | 07/01/2019 | 07/01/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2019 |  | 6/21/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2020 | Connected |  | N
National Grid | MALDEN | 630075 | 02148 | 3.15 | Solar | 05_07_97W3 | 08/05/2024 | 08/15/2024 | 3 | 0 | 3 | 08/16/2024 | 08/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/05/2024 | 9/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 176245 | 01532 | 5100 | Solar | 05_07_91W41 | 04/30/2015 | 04/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2015 | 05/08/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 177254 | 02333 | 6 | Solar | 05_09_527L1 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/20/2016 | 06/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/20/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 | 10/27/2016 | 10/27/2016 | 10/27/2016 | Connected |  | N
National Grid | ATTLEBORO | 616100 | 02703 | 3.8 | Solar | 05_05_3422W1 | 06/06/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 60 | 46 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 1/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | WORCESTER | 262490 | 01606 | 0 | Solar | 05_12_12J5 | 10/28/2019 | 10/29/2019 | 0 | 0 | 0 | 10/30/2019 | 10/30/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 |  | 10/27/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2020 | Connected |  | N
National Grid | LONGMEADOW | 184729 | 01028 | 16.64 | Solar | 05_05_318W3 | 05/07/2018 | 05/07/2018 | 9 | 0 | 9 | 07/13/2018 | 07/13/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 586841 | 02368 | 15.2 | Solar | 05_07_797W23 | 01/31/2024 | 02/26/2024 | 17 | 15 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  | 3/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2024 | Connected |  | N
National Grid | BROCKTON | 713209 | 02302 | 5.76 | Solar | 05_05_9L1 | 08/19/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 31 | 19 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2026 | Connected |  | N
National Grid | GRANBY | 407000 | 01033 | 15.37 | Solar | 05_01_14J368 | 03/13/2022 | 03/15/2022 | 2 | 0 | 2 | 03/16/2022 | 03/16/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 |  | 3/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2022 | Connected |  | N
National Grid | HAMPDEN | 272367 | 01036 | 9.89 | Solar | 05_09_139L5 | 05/07/2020 | 05/28/2020 | 14 | 14 | 0 | 05/29/2020 | 05/29/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/07/2020 | 5/28/2021 | Y | EXP | 365 | 11/14/2020 | 12/10/2020 | 26 | 0 | 26 |  |  | 12/12/2020 | Connected |  | N
National Grid | BEVERLY | 639504 | 01915 | 10 | Solar | 05_07_97W3 | 09/11/2024 | 12/04/2024 | 46 | 45 | 1 | 12/05/2024 | 12/05/2024 | 51 | 25 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 176315 | 01503 | 2610 | Solar | 05_07_91W41 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/12/2015 | 06/04/2015 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 | 05/08/2015 | 10/10/2017 | Y | STD | 656 | 05/05/2017 | 11/08/2017 | 124 | 0 | 124 | 11/8/2017 | 11/8/2017 | 11/15/2017 | Connected |  | N
National Grid | EAST BRIDGEWATER | 177665 | 02333 | 7.6 | Solar | 05_09_527L1 | 05/24/2017 | 05/24/2017 | 5 | 5 | 0 | 06/02/2017 | 06/02/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2017 | 05/24/2017 | 8/31/2018 | Y | EXP | 452 | 01/30/2018 | 02/12/2018 | 9 | 0 | 9 |  |  | 6/11/2018 | Connected |  | N
National Grid | ATTLEBORO | 616598 | 02703 | 0 | Solar | 05_05_3422W1 | 06/14/2024 | 07/22/2024 | 24 | 22 | 2 | 07/23/2024 | 07/23/2024 | 30 | 22 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2024 | Connected |  | N
National Grid | WORCESTER | 586184 | 01606 | 25 | Solar | 05_12_12J5 | 01/30/2024 | 02/07/2024 | 7 | 5 | 2 | 02/08/2024 | 02/08/2024 | 10 | 0 | 10 | 02/27/2024 | 04/03/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 04/03/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 4/3/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2024 | Connected |  | N
National Grid | LONGMEADOW | 195130 | 01028 | 479.904 | Solar | 05_05_318W3 | 09/06/2018 | 09/21/2018 | 4 | 0 | 4 | 09/24/2018 | 09/24/2018 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2018 |  | 5/31/2020 | N | EXP | 389 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | HOLBROOK | 594128 | 02343 | 12.915 | Solar | 05_07_797W23 | 03/21/2024 | 03/27/2024 | 4 | 2 | 2 | 03/28/2024 | 03/28/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | BROCKTON | 720985 | 02302 | 3.8 | Solar | 05_05_9L1 | 09/22/2025 | 11/24/2025 | 23 | 20 | 3 | 11/25/2025 | 11/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 |  | 12/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2026 | Connected |  | N
National Grid | GRANBY | 639399 | 01033 | 7.6 | Solar | 05_01_14J368 | 10/02/2024 | 02/26/2025 | 97 | 96 | 1 | 02/27/2025 | 02/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | HAMPDEN | 273953 | 01036 | 3984 | Solar | 05_09_139L5 | 10/27/2020 | 01/12/2021 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/13/2021 | 02/09/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 643251 | 01915 | 4.8 | Solar | 05_07_97W3 | 09/27/2024 | 10/07/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 226520 | 01503 | 4061 | Solar | 05_07_91W41 | 06/11/2019 | 07/02/2019 | 15 | 9 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2019 | 07/30/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 177734 | 02333 | 10 | Solar | 05_09_527L1 | 03/22/2017 | 03/22/2017 | 4 | 4 | 0 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 | 03/22/2017 | 3/27/2018 | Y | EXP | 363 |  |  | 0 | 0 | 0 | 1/5/2018 | 1/5/2018 | 1/8/2018 | Connected |  | N
National Grid | ATTLEBORO | 637593 | 02703 | 0 | Solar | 05_05_3422W1 | 09/04/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | WORCESTER | 606036 | 01606 | 5.7 | Solar | 05_12_12J5 | 04/24/2024 | 05/07/2024 | 6 | 5 | 1 | 05/08/2024 | 05/08/2024 | 81 | 75 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 202568 | 01028 | 15.2 | Solar | 05_05_318W3 | 12/10/2018 | 12/21/2018 | 6 | 0 | 6 | 12/24/2018 | 12/24/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2019 | 12/10/2018 | 9/23/2021 | Y | EXP | 365 | 04/07/2021 | 04/14/2021 | 7 | 0 | 7 |  |  | 4/23/2021 | Connected |  | N
National Grid | RANDOLPH | 597731 | 02368 | 10.44 | Solar | 05_07_797W23 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | BRIDGEWATER | 732094 | 02333 | 10 | Solar | 05_05_9L1 | 11/06/2025 | 11/07/2025 | 3 | 0 | 3 | 11/17/2025 | 11/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 749657 | 01033 | 15.2 | Solar | 05_01_15J392 | 02/05/2026 | 02/06/2026 | 1 | 0 | 1 | 02/09/2026 | 02/09/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | E LONGMEADOW | 281671 | 01028 | 9.84 | Solar | 05_09_139L5 | 05/20/2020 | 05/22/2020 | 1 | 0 | 1 | 05/26/2020 | 05/26/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2020 |  | 5/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2020 | Connected |  | N
National Grid | BEVERLY | 644166 | 01915 | 10 | Solar | 05_07_97W3 | 10/02/2024 | 10/17/2024 | 2 | 0 | 2 | 10/18/2024 | 10/18/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 328433 | 01503 | 9.8 | Solar | 05_07_91W41 | 01/07/2021 | 01/11/2021 | 1 | 0 | 1 | 01/12/2021 | 01/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2021 | 01/07/2021 | 6/25/2022 | Y | EXP | 365 | 06/18/2021 | 06/28/2021 | 11 | 0 | 11 |  |  | 3/29/2022 | Connected |  | N
National Grid | BRIDGEWATER | 177779 | 02333 | 4150 | Solar | 05_09_527L1 | 03/30/2017 | 03/30/2017 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2017 | 05/11/2017 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/4/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 664060 | 02703 | 5.76 | Solar | 05_05_3422W1 | 01/10/2025 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N
National Grid | WORCESTER | 671333 | 01606 | 4.35 | Solar | 05_12_12J5 | 02/24/2025 | 02/26/2025 | 2 | 0 | 2 | 02/27/2025 | 02/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | HAMPDEN | 202205 | 01036 | 20 | Solar | 05_05_318W3 | 11/27/2018 | 12/05/2018 | 5 | 0 | 5 | 12/06/2018 | 12/06/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 598158 | 02343 | 10 | Solar | 05_07_797W23 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2024 | Connected |  | N
National Grid | BRIDGEWATER | 174134 | 02333 | 36 | Solar | 05_05_9L2 | 05/04/2012 | 05/04/2012 | 9 | 0 | 9 | 05/21/2012 | 05/21/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2012 |  | 5/19/2012 | N | EXP | 14 |  |  | 0 | 0 | 0 | 8/31/2012 | 8/31/2012 | 10/24/2012 | Connected |  | N
National Grid | GRANBY | 175282 | 01033 | 42.57 | Solar | 05_01_15J392 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/5/2015 | Connected |  | N
National Grid | E LONGMEADOW | 327143 | 01028 | 11.4 | Solar | 05_09_139L5 | 11/19/2020 | 11/30/2020 | 5 | 1 | 4 | 12/01/2020 | 12/01/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2020 |  | 2/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2022 | Connected |  | N
National Grid | BEVERLY | 646249 | 01915 | 7.6 | Solar | 05_07_97W3 | 10/17/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 | 10/17/2024 | 1/28/2026 | Y | EXP | 365 | 04/30/2025 | 06/18/2025 | 50 | 0 | 50 |  |  | 7/7/2025 | Connected |  | N
National Grid | HUDSON | 404665 | 01749 | 0 | Solar | 05_07_91W41 | 01/04/2022 | 01/10/2022 | 4 | 2 | 2 | 01/11/2022 | 01/11/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  | 1/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2022 | Connected |  | N
National Grid | BRIDGEWATER | 178120 | 02333 | 3960 | Solar | 05_09_527L1 | 05/11/2017 | 05/11/2017 | 219 | 218 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/17/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 683812 | 02703 | 13.12 | Solar | 05_05_3422W1 | 04/08/2025 | 05/06/2025 | 0 | 0 | 0 | 05/07/2025 | 05/07/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/08/2025 | 7/7/2026 | Y | EXP | 365 | 10/07/2025 | 10/16/2025 | 10 | 0 | 10 |  |  | 11/3/2025 | Connected |  | N
National Grid | WORCESTER | 175881 | 01606 | 40 | Solar | 05_12_12J6 | 03/09/2015 | 03/09/2015 | 1 | 0 | 1 | 03/16/2015 | 03/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2015 |  | 8/17/2015 | N | EXP | 152 |  |  | 0 | 0 | 0 | 4/1/2015 | 4/1/2015 | 7/2/2015 | Connected |  | N
National Grid | HAMPDEN | 241787 | 01036 | 9.28 | Solar | 05_05_318W3 | 09/30/2019 | 10/07/2019 | 4 | 1 | 3 | 10/08/2019 | 10/08/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2019 |  | 9/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2020 | Connected |  | N
National Grid | RANDOLPH | 616189 | 02368 | 5.76 | Solar | 05_07_797W23 | 06/06/2024 | 06/25/2024 | 3 | 0 | 3 | 06/26/2024 | 06/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 | 06/06/2024 | 8/1/2025 | Y | EXP | 365 | 09/03/2024 | 02/28/2025 | 179 | 0 | 179 |  |  | 2/28/2025 | Connected |  | N
National Grid | BROCKTON | 175394 | 02302 | 131 | Solar | 05_05_9L2 | 09/16/2014 | 09/16/2014 | 7 | 0 | 7 | 09/26/2014 | 09/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2014 |  | 12/31/2014 | N | EXP | 82 |  |  | 0 | 0 | 0 | 1/15/2015 | 1/15/2015 | 2/5/2015 | Connected |  | N
National Grid | GRANBY | 405854 | 01033 | 0 | Other | 05_01_15J392 | 05/20/2022 | 06/09/2022 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2022 | 06/21/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | E LONGMEADOW | 335442 | 01028 | 7.875 | Solar | 05_09_139L5 | 01/19/2021 | 01/25/2021 | 3 | 1 | 2 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/19/2021 | 1/24/2022 | Y | EXP | 365 | 05/08/2021 | 05/25/2021 | 17 | 0 | 17 |  |  | 7/13/2021 | Connected |  | N
National Grid | BEVERLY | 656845 | 01915 | 5.76 | Solar | 05_07_97W3 | 11/26/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 429020 | 01503 | 499 | Solar | 05_07_91W41 | 06/03/2022 | 07/01/2022 | 18 | 12 | 6 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 178462 | 02333 | 8300 | Solar | 05_09_527L1 | 01/22/2018 | 02/27/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2018 | 04/03/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 699705 | 02703 | 15.2 | Solar | 05_05_3422W1 | 06/19/2025 | 06/30/2025 | 6 | 2 | 4 | 07/01/2025 | 07/01/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | WORCESTER | 174453 | 01605 | 75 | Diesel | 05_12_12J7 | 07/12/2012 | 07/12/2012 | 6 | 0 | 6 | 07/24/2012 | 07/24/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 12/24/2012 | 12/24/2012 | 3/29/2013 | Connected |  | N
National Grid | LONGMEADOW | 346401 | 01028 | 250 | Solar | 05_05_318W3 | 04/07/2021 | 04/23/2021 | 11 | 0 | 11 |  |  | 171 | 98 | 73 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 | 04/07/2021 | 7/20/2024 | Y | STD | 437 | 08/16/2023 | 10/27/2023 | 73 | 0 | 73 |  |  | 5/22/2024 | Connected |  | N
National Grid | RANDOLPH | 626085 | 02368 | 10 | Solar | 05_07_797W23 | 07/23/2024 | 08/07/2024 | 1 | 0 | 1 | 08/08/2024 | 08/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 8/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2024 | Connected |  | N
National Grid | BROCKTON | 175657 | 02302 | 60 | Solar | 05_05_9L2 | 05/13/2014 | 05/13/2014 | 7 | 0 | 7 | 05/23/2014 | 05/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2014 | 05/13/2014 | 9/30/2014 | Y | EXP | 16 | 11/05/2014 | 11/20/2014 | 10 | 0 | 10 | 12/12/2014 | 12/12/2014 | 12/16/2014 | Connected |  | N
National Grid | GRANBY | 664954 | 01033 | 0 | Battery Add-On | 05_01_15J392 | 01/10/2025 | 01/14/2025 | 2 | 0 | 2 | 01/15/2025 | 01/15/2025 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | E LONGMEADOW | 344559 | 01028 | 6.93 | Solar | 05_09_139L5 | 03/26/2021 | 04/06/2021 | 7 | 7 | 0 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2021 |  | 4/5/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2021 | Connected |  | N
National Grid | BEVERLY | 661823 | 01915 | 7.6 | Solar | 05_07_97W3 | 12/24/2024 | 01/17/2025 | 5 | 0 | 5 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/24/2024 | 4/5/2026 | Y | EXP | 365 | 05/07/2025 | 11/05/2025 | 183 | 0 | 183 |  |  | 1/6/2026 | Connected |  | N
National Grid | BERLIN | 490718 | 01503 | 0 | Solar | 05_07_91W41 | 01/09/2023 | 01/10/2023 | 2 | 1 | 1 | 01/11/2023 | 01/11/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2023 |  | 2/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2023 | Connected |  | N
National Grid | BRIDGEWATER | 178677 | 02333 | 7.6 | Solar | 05_09_527L1 | 04/11/2018 | 04/11/2018 | 53 | 29 | 24 | 05/22/2018 | 05/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2018 |  | 4/17/2019 | N | EXP | 27 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 655156 | 02703 | 7.22 | Solar | 05_05_3422W2 | 11/19/2024 | 12/04/2024 | 3 | 0 | 3 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 175147 | 01605 | 34.2 | Solar | 05_12_12J7 | 10/24/2013 | 10/24/2013 | 8 | 1 | 7 | 11/06/2013 | 11/06/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2013 |  | 12/31/2013 | N | EXP | 53 |  |  | 0 | 0 | 0 | 2/28/2014 | 2/28/2014 | 3/24/2014 | Connected |  | N
National Grid | LONGMEADOW | 355955 | 01028 | 7.83 | Solar | 05_05_318W3 | 05/03/2021 | 05/06/2021 | 3 | 1 | 2 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2021 | Connected |  | N
National Grid | RANDOLPH | 648326 | 02368 | 3.8 | Solar | 05_07_797W23 | 10/21/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | WHITMAN | 175655 | 02382 | 684 | Solar | 05_05_9L2 | 05/09/2014 | 05/09/2014 | 8 | 0 | 8 | 05/22/2014 | 05/22/2014 | 0 | 0 | 0 | 07/30/2014 | 08/29/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 08/29/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 1/28/2015 | 05/09/2014 | 12/31/2016 | Y | EXP | 73 | 05/04/2016 | 08/23/2016 | 76 | 0 | 76 | 8/31/2016 | 8/31/2016 | 8/31/2016 | Connected |  | N
National Grid | BELCHERTOWN | 441629 | 01007 | 16.82 | Solar | 05_01_16J1 | 07/04/2022 |  | 50 | 47 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | E LONGMEADOW | 430108 | 01028 | 9.86 | Solar | 05_09_139L5 | 10/21/2022 | 05/20/2022 | 2 | 0 | 2 | 10/26/2022 | 10/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 |  | 11/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2023 | Connected |  | N
National Grid | BEVERLY | 667503 | 01915 | 8.99 | Solar | 05_07_97W3 | 01/28/2025 | 02/25/2025 | 8 | 4 | 4 | 02/26/2025 | 02/26/2025 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 5/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | BOLTON | 559477 | 01740 | 7.56 | Solar | 05_07_91W41 | 10/27/2023 | 10/30/2023 | 1 | 0 | 1 | 10/31/2023 | 10/31/2023 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2023 | 10/27/2023 | 2/6/2025 | Y | EXP | 365 | 02/27/2024 | 04/19/2024 | 53 | 0 | 53 |  |  | 5/6/2024 | Connected |  | N
National Grid | BRIDGEWATER | 178698 | 02333 | 4400 | Solar | 05_09_527L1 | 02/07/2018 | 04/02/2018 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2018 | 04/27/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 703901 | 02703 | 0 | Solar | 05_05_3422W2 | 07/10/2025 | 07/21/2025 | 7 | 4 | 3 | 07/22/2025 | 07/22/2025 | 98 | 82 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 244606 | 01605 | 146 | Solar | 05_12_12J7 | 07/22/2019 | 08/16/2019 | 17 | 14 | 3 |  |  | 0 | 0 | 0 | 11/01/2019 | 11/01/2019 | 1 | 1 | 0 | 08/19/2019 | 10/01/2019 | 30 | 17 | 13 |  | 11/01/2019 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 | 07/22/2019 | 1/18/2023 | Y | STD | 365 | 03/25/2023 | 03/24/2023 | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | LONGMEADOW | 366496 | 01028 | 8.7 | Solar | 05_05_318W3 | 09/07/2021 | 09/13/2021 | 4 | 0 | 4 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 | 09/07/2021 | 12/21/2023 | Y | EXP | 365 | 04/13/2022 | 12/21/2022 | 253 | 0 | 253 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 648691 | 02343 | 10 | Solar | 05_07_797W23 | 11/04/2024 | 12/04/2024 | 16 | 11 | 5 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 175957 | 02333 | 997 | Solar | 05_05_9L2 | 06/02/2015 | 06/02/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2015 | 07/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2015 | 06/02/2015 | 6/30/2016 | Y | STD | 29 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 457672 | 01033 | 16.82 | Solar | 05_01_16J1 | 09/09/2022 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | E LONGMEADOW | 460692 | 01028 | 14.79 | Solar | 05_09_139L5 | 10/06/2022 | 10/10/2022 | 2 | 0 | 2 | 10/11/2022 | 10/11/2022 | 52 | 37 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 |  | 5/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2023 | Connected |  | N
National Grid | BEVERLY | 680640 | 01915 | 10 | Solar | 05_07_97W3 | 03/26/2025 | 04/10/2025 | 20 | 19 | 1 | 06/02/2025 | 06/02/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 | 03/26/2025 | 7/9/2026 | Y | EXP | 365 | 08/29/2025 | 11/21/2025 | 85 | 0 | 85 |  |  | 11/25/2025 | Connected |  | N
National Grid | BERLIN | 544773 | 01503 | 15.2 | Solar | 05_07_91W41 | 07/31/2023 | 08/03/2023 | 3 | 0 | 3 | 08/04/2023 | 08/04/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 9/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2024 | Connected |  | N
National Grid | EAST BRIDGEWATER | 178731 | 02333 | 4400 | Solar | 05_09_527L1 | 02/12/2018 | 04/02/2018 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2018 | 04/27/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 188239 | 02703 | 259.2 | Solar | 05_05_3422W2 | 06/15/2018 | 06/15/2018 | 11 | 11 | 0 |  |  | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 268435 | 01605 | 175 | Solar | 05_12_12J7 | 12/05/2019 | 12/10/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2019 | 01/03/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 01/03/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 5/18/2020 | 12/05/2019 | 1/31/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2023 | Connected |  | N
National Grid | LONGMEADOW | 372931 | 01028 | 7.6 | Solar | 05_05_318W3 | 08/31/2021 | 09/08/2021 | 4 | 4 | 0 | 09/09/2021 | 09/09/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 |  | 5/14/2023 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 650281 | 02368 | 10 | Solar | 05_07_797W23 | 10/30/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | BRIDGEWATER | 177007 | 02333 | 997 | Solar | 05_05_9L2 | 10/13/2016 | 10/13/2016 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 | 11/01/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/18/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 674114 | 01033 | 0 | Battery Add-On | 05_01_16J1 | 02/25/2025 | 03/26/2025 | 12 | 8 | 4 | 03/27/2025 | 03/27/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | E LONGMEADOW | 486713 | 01028 | 7.83 | Solar | 05_09_139L5 | 12/28/2022 | 01/03/2023 | 3 | 1 | 2 | 01/04/2023 | 01/04/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/28/2022 | 7/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2023 | Connected |  | N
National Grid | BEVERLY | 684881 | 01915 | 10 | Solar | 05_07_97W3 | 04/14/2025 | 05/08/2025 | 1 | 0 | 1 | 05/09/2025 | 05/09/2025 | 14 | 0 | 14 | 06/05/2025 | 06/04/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/04/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 | 04/14/2025 | 6/16/2026 | Y | EXP | 365 | 11/04/2025 | 12/01/2025 | 28 | 0 | 28 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 606032 | 01740 | 5.76 | Solar | 05_07_91W41 | 04/23/2024 | 05/07/2024 | 9 | 6 | 3 | 05/08/2024 | 05/08/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 184743 | 02333 | 630 | Solar | 05_09_527L1 | 07/03/2018 | 07/03/2018 | 124 | 25 | 99 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 188233 | 02703 | 302.4 | Solar | 05_05_3422W2 | 06/15/2018 | 06/15/2018 | 10 | 10 | 0 |  |  | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 446332 | 01602 | 50 | Solar | 05_12_12J7 | 07/22/2022 | 09/16/2022 | 39 | 29 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 6/9/2025 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N
National Grid | LONGMEADOW | 384559 | 01028 | 7.6 | Solar | 05_05_318W3 | 09/27/2021 | 09/28/2021 | 1 | 0 | 1 | 09/29/2021 | 09/29/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  | 5/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2022 | Connected |  | N
National Grid | RANDOLPH | 655063 | 02368 | 10 | Solar | 05_07_797W23 | 11/18/2024 | 12/09/2024 | 2 | 0 | 2 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/18/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | BROCKTON | 177239 | 02302 | 1080 | Solar | 05_05_9L2 | 02/03/2017 | 03/07/2017 | 22 | 21 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2017 | 05/15/2017 | 50 | 37 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2017 | 02/03/2017 | 4/2/2023 | Y | STD | 2 | 10/11/2021 | 03/01/2022 | 142 | 4 | 138 |  |  | 3/31/2023 | Connected |  | N
National Grid | GRANBY | 742647 | 01033 | 20 | Solar | 05_01_16J2 | 01/30/2026 | 02/03/2026 | 2 | 0 | 2 | 02/04/2026 | 02/04/2026 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | E LONGMEADOW | 502131 | 01028 | 0 | Solar | 05_09_139L5 | 02/27/2023 | 03/01/2023 | 3 | 2 | 1 | 03/02/2023 | 03/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 |  | 4/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2023 | Connected |  | N
National Grid | BEVERLY | 686545 | 01915 | 10 | Solar | 05_07_97W3 | 04/21/2025 | 05/13/2025 | 4 | 0 | 4 | 06/04/2025 | 06/04/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 04/21/2025 | 9/2/2026 | Y | EXP | 365 | 11/26/2025 | 01/15/2026 | 51 | 0 | 51 |  |  | 2/5/2026 | Connected |  | N
National Grid | BOLTON | 256585 | 01740 | 7.6 | Solar | 05_07_91W42 | 10/17/2019 | 10/21/2019 | 2 | 1 | 1 | 10/22/2019 | 10/22/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2019 | 10/17/2019 | 6/9/2021 | Y | EXP | 365 | 01/14/2020 | 01/13/2020 | 0 | 0 | 0 |  |  | 11/13/2020 | Connected |  | N
National Grid | BRIDGEWATER | 188688 | 02333 | 456 | Solar | 05_09_527L1 | 06/21/2018 | 06/21/2018 | 63 | 44 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 188112 | 02703 | 302.4 | Solar | 05_05_3422W2 | 06/14/2018 | 06/14/2018 | 10 | 10 | 0 |  |  | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 727434 | 01602 | 8 | Solar | 05_12_12J902 | 10/17/2025 | 10/23/2025 | 1 | 0 | 1 | 10/31/2025 | 10/31/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 10/17/2025 | 12/1/2026 | Y | EXP | 365 | 01/13/2026 |  | 53 | 0 | 53 |  |  |  | Construction |  | N
National Grid | LONGMEADOW | 388680 | 01028 | 9.86 | Solar | 05_05_318W3 | 10/14/2021 | 10/19/2021 | 3 | 3 | 0 | 10/20/2021 | 10/20/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 |  | 1/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N
National Grid | HOLBROOK | 677765 | 02343 | 11.5 | Solar | 05_07_797W23 | 03/13/2025 | 03/18/2025 | 3 | 0 | 3 | 03/19/2025 | 03/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  | 6/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2025 | Connected |  | N
National Grid | EAST BRIDGEWATER | 177427 | 02333 | 997 | Solar | 05_05_9L2 | 02/28/2017 | 02/28/2017 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2017 | 03/24/2017 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 175762 | 01033 | 17 | Solar | 05_01_16J2 | 06/05/2014 | 06/05/2014 | 6 | 0 | 6 | 06/16/2014 | 06/16/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2014 |  | 8/29/2014 | N | EXP | 49 |  |  | 0 | 0 | 0 | 7/11/2014 | 7/11/2014 | 10/9/2014 | Connected |  | N
National Grid | E LONGMEADOW | 514196 | 01028 | 0 | Solar | 05_09_139L5 | 03/27/2023 | 03/31/2023 | 5 | 4 | 1 | 04/03/2023 | 04/03/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 701953 | 01915 | 7.6 | Solar | 05_07_97W3 | 07/02/2025 | 07/23/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 | 07/02/2025 | 10/6/2026 | Y | EXP | 365 | 11/08/2025 | 01/21/2026 | 75 | 0 | 75 |  |  | 1/23/2026 | Connected |  | N
National Grid | BOLTON | 371375 | 01740 | 7.6 | Solar | 05_07_91W42 | 08/13/2021 | 08/18/2021 | 3 | 0 | 3 | 08/19/2021 | 08/19/2021 | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2021 | 08/13/2021 | 9/25/2023 | Y | EXP | 365 | 02/15/2022 | 04/25/2022 | 70 | 0 | 70 |  |  | 11/3/2022 | Connected |  | N
National Grid | BRIDGEWATER | 188676 | 02333 | 470 | Solar | 05_09_527L1 | 06/21/2018 | 06/21/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/07/2018 | 11/08/2018 | 43 | 3 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 188300 | 02703 | 259.2 | Solar | 05_05_3422W2 | 06/18/2018 | 06/18/2018 | 11 | 11 | 0 |  |  | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 738984 | 01602 | 7.6 | Solar | 05_12_12J902 | 12/09/2025 | 12/10/2025 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 418047 | 01028 | 15.2 | Solar | 05_05_318W3 | 03/16/2022 | 03/18/2022 | 3 | 2 | 1 | 03/21/2022 | 03/21/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 684009 | 02368 | 19.76 | Solar | 05_07_797W23 | 04/09/2025 | 04/15/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | BROCKTON | 178090 | 02302 | 100 | Solar | 05_05_9L2 | 07/07/2017 | 07/07/2017 | 32 | 32 | 0 | 08/22/2017 | 08/22/2017 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2017 |  | 7/12/2018 | N | EXP | 317 |  |  | 0 | 0 | 0 |  |  | 8/21/2018 | Connected |  | N
National Grid | AYER | 593407 | 01432 | 10 | Solar | 05_01_16J2 | 02/29/2024 | 03/12/2024 | 8 | 5 | 3 | 03/13/2024 | 03/13/2024 | 10 | 7 | 3 | 04/01/2024 | 04/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 04/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 4/29/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | E LONGMEADOW | 567007 | 01028 | 10 | Solar | 05_09_139L5 | 11/08/2023 |  | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 705472 | 01915 | 5.76 | Solar | 05_07_97W3 | 07/17/2025 | 08/01/2025 | 4 | 0 | 4 | 08/13/2025 | 08/13/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 402619 | 01740 | 3.84 | Solar | 05_07_91W42 | 01/24/2022 | 02/02/2022 | 7 | 0 | 7 | 02/03/2022 | 02/03/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2022 |  | 3/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2022 | Connected |  | N
National Grid | BRIDGEWATER | 188660 | 02333 | 240 | Solar | 05_09_527L1 | 06/21/2018 | 06/21/2018 | 60 | 31 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 11/08/2018 | 77 | 26 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 188280 | 02703 | 259.2 | Solar | 05_05_3422W2 | 06/15/2018 | 06/15/2018 | 10 | 10 | 0 |  |  | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 687004 | 01609 | 7.83 | Solar | 05_12_12J903 | 04/23/2025 | 05/12/2025 | 4 | 0 | 4 | 05/30/2025 | 05/30/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 04/23/2025 | 7/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | LONGMEADOW | 429894 | 01028 | 15.2 | Solar | 05_05_318W3 | 05/11/2022 | 05/12/2022 | 1 | 0 | 1 | 05/13/2022 | 05/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2022 |  | 8/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2022 | Connected |  | N
National Grid | RANDOLPH | 709116 | 02368 | 3.8 | Solar | 05_07_797W23 | 08/11/2025 | 09/02/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | BROCKTON | 433514 | 02302 | 10 | Solar | 05_05_9L2 | 06/22/2022 | 06/24/2022 | 2 | 0 | 2 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/22/2022 | 1/7/2024 | Y | EXP | 365 | 01/07/2023 | 01/06/2023 | 0 | 0 | 0 |  |  | 2/3/2023 | Connected |  | N
National Grid | GRANBY | 672266 | 01033 | 7.6 | Solar | 05_01_16J2 | 02/19/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 02/19/2025 | 4/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | E LONGMEADOW | 582369 | 01028 | 15.2 | Solar | 05_09_139L5 | 01/09/2024 | 01/29/2024 | 14 | 12 | 2 | 01/30/2024 | 01/30/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  | 3/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | LYNN | 712872 | 01902 | 10 | Solar | 05_07_97W3 | 08/18/2025 | 09/11/2025 | 6 | 2 | 4 | 09/25/2025 | 09/25/2025 | 20 | 4 | 16 | 10/30/2025 | 12/09/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 12/09/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | BERLIN | 565340 | 01503 | 10 | Solar | 05_07_91W42 | 11/27/2023 | 11/30/2023 | 3 | 0 | 3 | 12/01/2023 | 12/01/2023 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/27/2023 | 2/19/2025 | Y | EXP | 365 | 04/25/2024 | 05/03/2024 | 9 | 0 | 9 |  |  | 5/13/2024 | Connected |  | N
National Grid | BRIDGEWATER | 188659 | 02333 | 2376 | Solar | 05_09_527L1 | 06/21/2018 | 06/21/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 11/08/2018 | 78 | 27 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 217708 | 02703 | 25 | Solar | 05_05_3422W2 | 04/24/2019 | 05/06/2019 | 7 | 0 | 7 | 05/07/2019 | 05/07/2019 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 |  | 5/6/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2019 | Connected |  | N
National Grid | WORCESTER | 716171 | 01609 | 3.8 | Solar | 05_12_12J903 | 09/10/2025 | 09/25/2025 | 2 | 0 | 2 | 10/07/2025 | 10/07/2025 | 54 | 36 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 | 09/10/2025 | 12/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LONGMEADOW | 434493 | 01028 | 15.2 | Solar | 05_05_318W3 | 06/01/2022 | 06/03/2022 | 2 | 0 | 2 | 06/06/2022 | 06/06/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2022 |  | 7/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2023 | Connected |  | N
National Grid | HOLBROOK | 719830 | 02343 | 10 | Solar | 05_07_797W23 | 09/18/2025 | 09/22/2025 | 2 | 0 | 2 | 09/23/2025 | 09/23/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 456501 | 02302 | 19.14 | Solar | 05_05_9L2 | 09/03/2022 | 09/07/2022 | 3 | 2 | 1 | 09/08/2022 | 09/08/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 11/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2023 | Connected |  | N
National Grid | GRANBY | 174464 | 01033 | 170 | Natural Gas | 05_01_16J3 | 08/09/2011 | 08/09/2011 | 40 | 0 | 40 | 10/10/2011 | 10/10/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2011 |  | 10/31/2012 | N | EXP | 329 |  |  | 0 | 0 | 0 | 6/29/2012 | 6/29/2012 | 1/29/2013 | Connected |  | N
National Grid | E LONGMEADOW | 601540 | 01028 | 7.6 | Solar | 05_09_139L5 | 04/05/2024 | 04/09/2024 | 2 | 0 | 2 | 04/10/2024 | 04/10/2024 | 16 | 10 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2024 | 04/05/2024 | 5/14/2025 | Y | EXP | 365 | 08/09/2024 | 08/20/2024 | 12 | 0 | 12 |  |  | 10/4/2024 | Connected |  | N
National Grid | LYNN | 665647 | 01902 | 7.6 | Solar | 05_07_97W4 | 01/16/2025 | 03/05/2025 | 3 | 0 | 3 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 01/16/2025 | 10/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | BERLIN | 589554 | 01503 | 9.8 | Solar | 05_07_91W42 | 02/21/2024 | 03/29/2024 | 27 | 24 | 3 | 04/01/2024 | 04/01/2024 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 02/21/2024 | 12/13/2025 | Y | EXP | 365 | 06/27/2024 | 07/25/2024 | 29 | 0 | 29 |  |  | 3/17/2025 | Connected |  | N
National Grid | EAST BRIDGEWATER | 249752 | 02333 | 3.8 | Solar | 05_05_3422W2 | 08/20/2019 | 09/09/2019 | 12 | 6 | 6 | 09/10/2019 | 09/10/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2019 |  | 8/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2020 | Connected |  | N
National Grid | ATTLEBORO | 423857 | 02703 | 3 | Solar | 05_12_12J903 | 05/04/2022 | 06/24/2022 | 24 | 22 | 2 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 462578 | 01609 | 60 | Solar | 05_05_318W3 | 10/06/2022 | 11/07/2022 | 22 | 12 | 10 | 11/08/2022 | 11/08/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2023 | 10/06/2022 | 6/25/2024 | Y | EXP | 133 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N
National Grid | LONGMEADOW | 651763 | 01028 | 3.8 | Solar | 05_07_797W24 | 11/13/2024 | 02/19/2025 | 2 | 0 | 2 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | RANDOLPH | 598260 | 02368 | 10 | Solar | 05_05_9L2 | 03/29/2024 | 04/16/2024 | 12 | 10 | 2 | 04/17/2024 | 04/17/2024 | 10 | 6 | 4 | 05/14/2024 | 06/26/2024 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 06/26/2024 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 5/16/2024 |  | 5/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 648172 | 02302 | 5.76 | Solar | 05_01_18J394 | 10/30/2024 | 03/06/2025 | 77 | 73 | 4 | 03/07/2025 | 03/07/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GRANBY | 625890 | 01033 | 9.765 | Solar | 05_09_139L5 | 08/14/2024 | 08/21/2024 | 6 | 3 | 3 | 08/22/2024 | 08/22/2024 | 58 | 35 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | RANDOLPH | 725062 | 02368 | 5.76 | Solar | 05_07_97W4 | 10/08/2025 | 10/27/2025 | 11 | 10 | 1 | 10/28/2025 | 10/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 602878 | 01904 | 4.06 | Solar | 05_07_91W42 | 04/09/2024 | 05/10/2024 | 3 | 2 | 1 | 05/13/2024 | 05/13/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2024 | 04/09/2024 | 1/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | BERLIN | 190067 | 01503 | 5000 | Solar | 05_09_527L1 | 07/18/2018 | 08/01/2018 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2018 | 08/24/2018 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 319784 | 02333 | 15 | Solar | 05_05_3422W2 | 11/10/2020 | 11/17/2020 | 4 | 2 | 2 | 11/18/2020 | 11/18/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 |  | 11/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N
National Grid | ATTLEBORO | 472733 | 02703 | 10 | Solar | 05_12_12J903 | 12/07/2022 |  | 150 | 25 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 478862 | 01609 | 16.82 | Solar | 05_05_318W3 | 11/18/2022 | 11/23/2022 | 3 | 0 | 3 | 11/25/2022 | 11/25/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 |  | 5/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2023 | Connected |  | N
National Grid | LONGMEADOW | 680245 | 01028 | 11.5 | Solar | 05_07_797W24 | 03/25/2025 | 06/16/2025 | 15 | 11 | 4 | 06/17/2025 | 06/17/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 609619 | 02368 | 12.6 | Solar | 05_05_9L2 | 05/09/2024 | 05/31/2024 | 1 | 0 | 1 | 06/03/2024 | 06/03/2024 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2024 |  | 7/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2024 | Connected |  | N
National Grid | BROCKTON | 671686 | 02302 | 3.8 | Solar | 05_01_18J394 | 02/12/2025 | 07/28/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GRANBY | 627240 | 01033 | 0 | Solar | 05_09_139L5 | 07/24/2024 | 07/26/2024 | 2 | 0 | 2 | 07/29/2024 | 07/29/2024 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 9/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2024 | Connected |  | N
National Grid | RANDOLPH | 747168 | 02368 | 7.6 | Solar | 05_07_97W4 | 01/23/2026 | 01/28/2026 | 2 | 0 | 2 | 03/03/2026 | 03/03/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 606767 | 01902 | 5.76 | Solar | 05_07_91W42 | 04/25/2024 | 04/29/2024 | 1 | 0 | 1 | 04/30/2024 | 04/30/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 6/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | BERLIN | 190691 | 01503 | 4400 | Solar | 05_09_527L1 | 07/16/2018 | 08/08/2018 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2018 | 10/09/2018 | 44 | 15 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 341243 | 02333 | 0 | Solar | 05_05_3422W2 | 02/09/2021 | 02/10/2021 | 0 | 0 | 0 | 02/11/2021 | 02/11/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2021 |  | 7/13/2022 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  | 6/27/2022 | Connected |  | N
National Grid | ATTLEBORO | 591993 | 02703 | 7.6 | Solar | 05_12_12J903 | 03/26/2024 | 03/27/2024 | 1 | 0 | 1 | 03/28/2024 | 03/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 482613 | 01609 | 0 | Solar | 05_05_318W3 | 12/13/2022 | 01/03/2023 | 13 | 8 | 5 | 01/04/2023 | 01/04/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 1/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2024 | Connected |  | N
National Grid | LONGMEADOW | 703140 | 01028 | 400 | Solar | 05_07_797W24 | 07/26/2025 | 09/03/2025 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/04/2025 | 09/24/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RANDOLPH | 647209 | 02368 | 7.6 | Solar | 05_05_9L2 | 10/15/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 101 | 75 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 736837 | 02302 | 5.76 | Solar | 05_01_18J394 | 11/27/2025 | 12/31/2025 | 2 | 0 | 2 | 01/27/2026 | 01/27/2026 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GRANBY | 631614 | 01033 | 5.76 | Solar | 05_09_139L5 | 08/09/2024 | 09/09/2024 | 3 | 0 | 3 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/09/2024 | 10/11/2025 | Y | EXP | 365 | 02/12/2025 | 02/26/2025 | 15 | 0 | 15 |  |  | 3/11/2025 | Connected |  | Y
National Grid | RANDOLPH | 178045 | 02368 | 51.75 | Solar | 05_07_97W4 | 05/05/2017 | 05/05/2017 | 14 | 13 | 1 | 05/25/2017 | 05/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2017 |  | 5/10/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 | 9/29/2017 | 9/29/2017 | 10/4/2017 | Connected |  | N
National Grid | LYNN | 651638 | 01902 | 7.6 | Solar | 05_07_91W42 | 11/13/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | BERLIN | 193939 | 01503 | 2500 | Solar | 05_09_527L1 | 08/20/2018 | 09/17/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 01/26/2019 | 136 | 52 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 383113 | 02341 | 13800 | Other | 05_05_3422W2 | 11/11/2021 | 12/30/2021 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2021 | 01/19/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 603517 | 02703 | 10 | Solar | 05_12_12J903 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 20 | 0 | 20 | 06/17/2024 | 07/24/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 07/24/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 7/1/2024 |  | 8/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | WORCESTER | 484982 | 01604 | 7.6 | Solar | 05_05_318W3 | 01/04/2023 | 01/05/2023 | 1 | 0 | 1 | 01/06/2023 | 01/06/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 2/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2023 | Connected |  | Y
National Grid | LONGMEADOW | 724039 | 01028 | 15.2 | Solar | 05_07_797W24 | 10/07/2025 | 11/04/2025 | 19 | 17 | 2 | 11/05/2025 | 11/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 | 10/07/2025 | 1/6/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | RANDOLPH | 657108 | 02368 | 5.76 | Solar | 05_05_9L2 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/26/2024 | 2/11/2026 | Y | EXP | 365 | 03/04/2025 | 04/17/2025 | 45 | 0 | 45 |  |  | 5/16/2025 | Connected |  | N
National Grid | BROCKTON | 742928 | 02302 | 5.76 | Solar | 05_01_18J394 | 01/02/2026 | 01/12/2026 | 5 | 0 | 5 | 01/28/2026 | 01/28/2026 | 27 | 16 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GRANBY | 637722 | 01033 | 3000 | Solar | 05_09_139L5 | 02/13/2025 |  | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 285089 | 02368 | 7.68 | Solar | 05_07_97W4 | 03/25/2020 | 04/01/2020 | 4 | 0 | 4 | 04/02/2020 | 04/02/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2020 | 03/25/2020 | 10/21/2021 | Y | EXP | 365 | 01/29/2021 | 03/12/2021 | 42 | 0 | 42 |  |  | 4/13/2021 | Connected |  | N
National Grid | LYNN | 681001 | 01902 | 4.56 | Solar | 05_07_91W42 | 03/27/2025 | 04/24/2025 | 3 | 0 | 3 | 04/25/2025 | 04/25/2025 | 47 | 33 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 192330 | 01503 | 11.4 | Solar | 05_09_527L1 | 07/31/2018 | 09/04/2018 | 12 | 0 | 12 | 09/05/2018 | 09/05/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  | 9/14/2020 | N | EXP | 45 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N
National Grid | PEMBROKE | 405831 | 02359 | 0 | Battery Add-On | 05_05_3422W2 | 01/24/2022 | 02/03/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2022 | 02/04/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 649321 | 02703 | 12.54 | Solar | 05_12_12J903 | 10/24/2024 | 11/13/2024 | 14 | 11 | 3 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | WORCESTER | 488595 | 01604 | 15.95 | Solar | 05_05_318W3 | 01/11/2023 | 01/27/2023 | 12 | 11 | 1 | 01/30/2023 | 01/30/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 4/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2023 | Connected |  | N
National Grid | LONGMEADOW | 753420 | 01028 | 15.2 | Solar | 05_07_797W24 | 02/26/2026 | 03/02/2026 | 2 | 0 | 2 | 03/03/2026 | 03/03/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 662700 | 02368 | 10 | Solar | 05_05_9L2 | 12/26/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/26/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | BROCKTON | 174124 | 02302 | 1000 |  | 05_01_18J394 | 04/05/2012 | 04/05/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 640515 | 01033 | 4.93 | Solar | 05_09_139L5 | 09/16/2024 | 11/19/2024 | 38 | 34 | 4 | 11/20/2024 | 11/20/2024 | 70 | 48 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 09/16/2024 | 4/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | RANDOLPH | 342233 | 02368 | 10 | Solar | 05_07_97W4 | 05/04/2021 | 05/05/2021 | 0 | 0 | 0 | 05/06/2021 | 05/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 | 05/04/2021 | 9/25/2022 | Y | EXP | 365 | 08/11/2021 | 09/23/2021 | 43 | 3 | 40 |  |  | 5/5/2022 | Connected |  | N
National Grid | LYNN | 692993 | 01902 | 3.8 | Solar | 05_07_91W42 | 05/23/2025 | 07/15/2025 | 3 | 0 | 3 | 08/04/2025 | 08/04/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 197086 | 01503 | 13.8 | Solar | 05_09_527L1 | 09/27/2018 | 10/30/2018 | 0 | 0 | 0 | 10/31/2018 | 10/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  | 8/30/2019 | N | EXP | 282 |  |  | 0 | 0 | 0 |  |  | 8/12/2019 | Connected |  | N
National Grid | HANSON | 408895 | 02341 | 9.6 | Solar | 05_05_3422W2 | 03/22/2022 | 03/28/2022 | 4 | 0 | 4 | 03/29/2022 | 03/29/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2022 | 03/22/2022 | 9/14/2023 | Y | EXP | 365 | 08/25/2022 | 09/08/2022 | 15 | 0 | 15 |  |  | 1/6/2023 | Connected |  | N
National Grid | ATTLEBORO | 660578 | 02703 | 5.76 | Solar | 05_12_12J903 | 12/13/2024 | 01/09/2025 | 5 | 0 | 5 | 01/10/2025 | 01/10/2025 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | WORCESTER | 502268 | 01604 | 7.6 | Solar | 05_05_318W3 | 03/09/2023 | 03/31/2023 | 17 | 16 | 1 | 04/03/2023 | 04/03/2023 | 66 | 46 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 8/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2023 | Connected |  | N
National Grid | LONGMEADOW | 174858 | 01028 | 10 | Solar | 05_07_797W24 | 08/08/2013 | 08/08/2013 | 6 | 0 | 6 | 08/19/2013 | 08/19/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2013 |  | 12/31/2016 | N | EXP | 1219 |  |  | 0 | 0 | 0 | 3/16/2015 | 3/16/2015 | 2/9/2017 | Connected |  | N
National Grid | RANDOLPH | 670414 | 02368 | 30.6 | Solar | 05_05_9L2 | 02/06/2025 | 03/05/2025 | 19 | 16 | 3 | 03/06/2025 | 03/06/2025 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 232530 | 02302 | 7.6 | Solar | 05_01_18J394 | 09/03/2019 | 09/24/2019 | 14 | 10 | 4 | 09/25/2019 | 09/25/2019 | 13 | 7 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 | 09/03/2019 | 10/20/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2020 | Connected |  | N
National Grid | GRANBY | 651816 | 01033 | 1.45 | Solar | 05_09_139L5 | 11/04/2024 | 11/25/2024 | 6 | 1 | 5 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/14/2026 | Y | EXP | 365 | 02/12/2025 | 02/15/2025 | 4 | 0 | 4 |  |  | 4/3/2025 | Connected |  | N
National Grid | RANDOLPH | 351290 | 02368 | 10 | Solar | 05_07_97W4 | 04/23/2021 | 04/28/2021 | 2 | 0 | 2 | 04/29/2021 | 04/29/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 | 04/23/2021 | 11/9/2022 | Y | EXP | 365 | 10/19/2021 | 10/19/2021 | 1 | 0 | 1 |  |  | 12/15/2021 | Connected |  | Y
National Grid | LYNN | 701723 | 01902 | 9.5 | Solar | 05_07_91W42 | 06/27/2025 | 07/11/2025 | 8 | 3 | 5 | 07/31/2025 | 07/31/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/27/2025 | 9/15/2026 | Y | EXP | 365 | 10/28/2025 | 11/12/2025 | 16 | 0 | 16 |  |  | 11/12/2025 | Connected |  | N
National Grid | BERLIN | 198592 | 01503 | 5000 | Solar | 05_09_527L1 | 12/06/2018 | 12/22/2018 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 | 01/22/2019 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HALIFAX | 606714 | 02338 | 15.3 | Solar | 05_05_3422W2 | 04/25/2024 | 04/26/2024 | 1 | 0 | 1 | 04/29/2024 | 04/29/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | ATTLEBORO | 730763 | 02703 | 7.6 | Solar | 05_12_12J903 | 11/02/2025 | 11/03/2025 | 2 | 1 | 1 | 11/14/2025 | 11/14/2025 | 64 | 25 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 554413 | 01604 | 0 | Battery Add-On | 05_05_318W3 | 09/22/2023 | 09/26/2023 | 2 | 0 | 2 | 09/27/2023 | 09/27/2023 | 81 | 60 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | LONGMEADOW | 175261 | 01028 | 22.8 | Solar | 05_07_797W24 | 01/09/2015 | 01/09/2015 | 5 | 2 | 3 | 01/19/2015 | 01/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2015 |  | 5/31/2015 | N | EXP | 89 |  |  | 0 | 0 | 0 | 3/3/2015 | 3/3/2015 | 8/28/2015 | Connected |  | N
National Grid | RANDOLPH | 687241 | 02368 | 7.25 | Solar | 05_05_9L2 | 05/02/2025 | 05/20/2025 | 2 | 0 | 2 | 06/03/2025 | 06/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | BROCKTON | 265291 | 02302 | 7.6 | Solar | 05_01_18J394 | 12/12/2019 | 01/02/2020 | 12 | 3 | 9 | 01/03/2020 | 01/03/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/12/2019 | 4/1/2021 | Y | EXP | 365 | 01/20/2021 | 01/22/2021 | 2 | 0 | 2 |  |  | 2/23/2021 | Connected |  | Y
National Grid | GRANBY | 653444 | 01033 | 10 | Solar | 05_09_139L5 | 11/11/2024 | 12/19/2024 | 13 | 12 | 1 | 12/20/2024 | 12/20/2024 | 59 | 37 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 | 11/11/2024 | 4/3/2026 | Y | EXP | 365 | 10/04/2025 | 10/16/2025 | 13 | 0 | 13 |  |  | 10/30/2025 | Connected |  | N
National Grid | RANDOLPH | 413313 | 02368 | 125 | Solar | 05_07_97W4 | 03/14/2022 | 08/01/2022 | 96 | 87 | 9 | 08/02/2022 | 08/02/2022 | 50 | 28 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 | 03/14/2022 | 8/5/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2024 | Connected |  | N
National Grid | LYNN | 632735 | 01902 | 7.6 | Solar | 05_07_91W43 | 10/01/2024 | 04/23/2025 | 23 | 21 | 2 | 04/24/2025 | 04/24/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 | 10/01/2024 | 7/2/2026 | Y | EXP | 365 | 10/01/2025 | 10/09/2025 | 9 | 0 | 9 |  |  |  | Completion Documents |  | N
National Grid | BOLTON | 201380 | 01740 | 3000 | Solar | 05_09_527L1 | 12/07/2018 | 01/29/2019 | 100 | 26 | 74 |  |  | 43 | 26 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 317765 | 02341 | 200 | Solar | 05_05_3422W3 | 10/22/2020 | 11/24/2020 | 22 | 15 | 7 | 11/25/2020 | 11/25/2020 | 173 | 69 | 104 | 05/11/2021 | 12/28/2023 | 659 | 33 | 626 |  |  | 0 | 0 | 0 |  | 12/28/2023 | 659 | 33 | 626 |  |  | 0 | 0 | 0 | 1/31/2024 |  | 6/5/2026 | N | EXP | 231 | 03/29/2025 |  | 343 | 289 | 54 |  |  |  | Construction |  | N
National Grid | ATTLEBORO | 692379 | 02703 | 13.36 | Solar | 05_12_12J904 | 05/22/2025 | 06/04/2025 | 4 | 1 | 3 | 06/25/2025 | 06/25/2025 | 28 | 13 | 15 | 08/12/2025 | 10/02/2025 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  | 10/02/2025 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | WORCESTER | 566220 | 01604 | 7.6 | Solar | 05_05_318W3 | 10/25/2023 | 10/26/2023 | 1 | 0 | 1 | 10/27/2023 | 10/27/2023 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2023 | Connected |  | N
National Grid | LONGMEADOW | 175305 | 01028 | 16 | Solar | 05_07_797W24 | 06/25/2014 | 06/25/2014 | 19 | 13 | 6 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2014 |  | 9/30/2014 | N | EXP | 47 |  |  | 0 | 0 | 0 | 9/3/2014 | 9/3/2014 | 11/14/2014 | Connected |  | N
National Grid | RANDOLPH | 700980 | 02368 | 7.6 | Solar | 05_05_9L2 | 06/25/2025 | 07/10/2025 | 2 | 0 | 2 | 07/18/2025 | 07/18/2025 | 13 | 0 | 13 | 08/22/2025 | 08/21/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/21/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 | 06/25/2025 | 9/10/2026 | Y | EXP | 365 | 11/04/2025 | 11/24/2025 | 21 | 0 | 21 |  |  | 12/5/2025 | Connected |  | N
National Grid | BROCKTON | 602751 | 02302 | 5 | Solar | 05_01_18J394 | 04/16/2024 | 04/18/2024 | 2 | 0 | 2 | 04/19/2024 | 04/19/2024 | 62 | 50 | 12 | 08/23/2024 | 09/17/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 09/17/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 9/20/2024 |  | 9/30/2025 | N | EXP | 365 | 10/24/2024 | 11/12/2024 | 20 | 0 | 20 |  |  | 1/22/2025 | Connected |  | N
National Grid | GRANBY | 653283 | 01033 | 2.03 | Solar | 05_09_139L5 | 11/08/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/08/2024 | 1/22/2026 | Y | EXP | 365 | 02/13/2025 | 02/20/2025 | 8 | 0 | 8 |  |  | 3/11/2025 | Connected |  | N
National Grid | RANDOLPH | 576970 | 02368 | 3.8 | Solar | 05_07_97W4 | 12/27/2023 | 01/02/2024 | 3 | 0 | 3 | 01/03/2024 | 01/03/2024 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 | 12/27/2023 | 2/20/2025 | Y | EXP | 365 | 09/12/2024 | 11/05/2024 | 55 | 0 | 55 |  |  | 1/29/2025 | Connected |  | N
National Grid | LYNN | 643789 | 01904 | 75 | Solar | 05_07_91W43 | 12/03/2024 | 02/19/2025 | 52 | 43 | 9 | 02/20/2025 | 02/20/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BERLIN | 201291 | 01503 | 3000 | Solar | 05_09_527L1 | 12/12/2018 | 02/22/2019 | 84 | 63 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/25/2019 | 03/20/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HALIFAX | 660617 | 02338 | 10 | Solar | 05_05_3422W3 | 12/13/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ATTLEBORO | 487065 | 02703 | 19 | Solar | 05_12_12J904 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2023 | Connected |  | N
National Grid | WORCESTER | 612829 | 01604 | 10 | Solar | 05_05_318W3 | 05/22/2024 | 05/24/2024 | 3 | 2 | 1 | 05/28/2024 | 05/28/2024 | 34 | 22 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2024 | Connected |  | N
National Grid | LONGMEADOW | 175616 | 01028 | 23.4 | Solar | 05_07_797W24 | 12/16/2014 | 12/16/2014 | 8 | 7 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2015 | 12/16/2014 | 12/31/2016 | Y | EXP | 71 | 11/02/2015 | 11/10/2015 | 6 | 0 | 6 | 1/22/2015 | 1/22/2015 | 6/17/2016 | Connected |  | N
National Grid | RANDOLPH | 202263 | 02368 | 7.6 | Solar | 05_05_9L3 | 12/19/2018 | 01/03/2019 | 8 | 1 | 7 | 01/28/2019 | 01/28/2019 | 146 | 0 | 146 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 675673 | 02302 | 7.6 | Solar | 05_01_18J394 | 03/04/2025 | 03/18/2025 | 1 | 0 | 1 | 03/19/2025 | 03/19/2025 | 55 | 34 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | Y
National Grid | GRANBY | 653585 | 01033 | 15.2 | Solar | 05_09_139L5 | 11/26/2024 | 11/27/2024 | 1 | 0 | 1 | 12/02/2024 | 12/02/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | RANDOLPH | 614076 | 02368 | 3.8 | Solar | 05_07_97W4 | 05/29/2024 | 06/10/2024 | 2 | 0 | 2 | 06/11/2024 | 06/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | LYNN | 660767 | 01902 | 6 | Solar | 05_07_91W43 | 12/16/2024 | 03/25/2025 | 4 | 0 | 4 | 03/26/2025 | 03/26/2025 | 24 | 0 | 24 | 05/27/2025 | 06/18/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 06/18/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 12/19/2026 | N | EXP | 365 | 10/04/2025 | 10/09/2025 | 6 | 0 | 6 |  |  |  | Completion Documents |  | N
National Grid | BERLIN | 676978 | 01503 | 750 | Solar | 05_05_3422W3 | 04/08/2025 | 06/10/2025 | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BRIDGEWATER | 503337 | 02333 | 3.8 | Solar | 05_12_12J904 | 02/23/2023 | 03/22/2023 | 19 | 17 | 2 | 03/23/2023 | 03/23/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2023 | 02/23/2023 | 1/23/2025 | Y | EXP | 365 | 09/06/2023 | 12/08/2023 | 94 | 0 | 94 |  |  | 2/22/2024 | Connected |  | N
National Grid | ATTLEBORO | 637222 | 02703 | 6.08 | Solar | 05_05_318W3 | 09/03/2024 | 09/16/2024 | 3 | 1 | 2 | 09/17/2024 | 09/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | WORCESTER | 175940 | 01604 | 19 | Solar | 05_07_797W24 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 | 01/29/2015 | 01/29/2015 | 556 | 0 | 556 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 |  | 5/31/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 205771 | 01028 | 10 | Solar | 05_05_9L3 | 02/13/2019 | 03/05/2019 | 12 | 12 | 0 | 03/06/2019 | 03/06/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2019 | 02/13/2019 | 3/13/2020 | Y | EXP | 365 | 11/15/2019 | 01/08/2020 | 48 | 0 | 48 |  |  | 1/17/2020 | Connected |  | N
National Grid | RANDOLPH | 175076 | 02368 | 100 | Solar | 05_01_1J363 | 09/23/2013 | 09/23/2013 | 6 | 0 | 6 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2013 |  | 2/1/2016 | N | EXP | 829 |  |  | 0 | 0 | 0 | 2/29/2016 | 2/29/2016 | 4/5/2016 | Connected |  | N
National Grid | BROCKTON | 655652 | 02301 | 5.8 | Solar | 05_09_139L5 | 11/20/2024 | 02/04/2025 | 15 | 10 | 5 | 02/05/2025 | 02/05/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | GRANBY | 651128 | 01033 | 10 | Solar | 05_07_97W4 | 11/12/2024 | 12/02/2024 | 2 | 0 | 2 | 12/03/2024 | 12/03/2024 | 60 | 36 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 11/12/2024 | 9/14/2026 | Y | EXP | 365 | 10/04/2025 | 02/13/2026 | 133 | 65 | 68 |  |  | 2/13/2026 | Connected |  | Y
National Grid | FOXBOROUGH | 721378 | 02035 | 5.76 | Solar | 05_07_91W43 | 10/01/2025 | 10/08/2025 | 2 | 0 | 2 | 11/25/2025 | 11/25/2025 | 26 | 8 | 18 | 01/23/2026 | 02/04/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 02/04/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 2/9/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 219076 | 01902 | 2.88 | Solar | 05_09_527L1 | 07/15/2019 | 07/30/2019 | 10 | 3 | 7 | 07/31/2019 | 07/31/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 2/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 742850 | 01740 | 19 | Solar | 05_05_3422W3 | 01/02/2026 | 01/05/2026 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BRIDGEWATER | 608562 | 02333 | 10 | Solar | 05_12_12J904 | 05/06/2024 | 05/23/2024 | 1 | 0 | 1 | 05/24/2024 | 05/24/2024 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 05/06/2024 | 9/4/2025 | Y | EXP | 365 | 08/20/2024 | 01/17/2025 | 151 | 0 | 151 |  |  | 3/28/2025 | Connected |  | N
National Grid | ATTLEBORO | 640073 | 02703 | 0 | Battery Add-On | 05_05_318W3 | 09/13/2024 | 09/17/2024 | 2 | 0 | 2 | 09/18/2024 | 09/18/2024 | 14 | 6 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2024 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | WORCESTER | 175952 | 01604 | 17.6 | Solar | 05_07_797W24 | 03/19/2015 | 03/19/2015 | 10 | 9 | 1 | 04/03/2015 | 04/03/2015 | 454 | 0 | 454 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2015 |  | 7/17/2015 | N | EXP | 12 |  |  | 0 | 0 | 0 | 4/24/2015 | 4/24/2015 |  | Withdrawn |  | N
National Grid | LONGMEADOW | 222415 | 01028 | 5 | Solar | 05_05_9L3 | 05/02/2019 | 05/09/2019 | 3 | 3 | 0 | 05/10/2019 | 05/10/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2019 | 05/02/2019 | 11/15/2019 | Y | EXP | 169 |  |  | 0 | 0 | 0 |  |  | 10/9/2019 | Connected |  | N
National Grid | RANDOLPH | 424441 | 02368 | 7.6 | Solar | 05_01_1J363 | 05/11/2022 | 05/16/2022 | 3 | 0 | 3 | 05/17/2022 | 05/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2022 |  | 12/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2023 | Connected |  | N
National Grid | BROCKTON | 656598 | 02301 | 10 | Solar | 05_09_139L5 | 11/25/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2025 | Connected |  | N
National Grid | GRANBY | 656239 | 01033 | 5.76 | Solar | 05_07_97W4 | 11/22/2024 | 01/22/2025 | 22 | 18 | 4 | 01/23/2025 | 01/23/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 11/22/2024 | 3/11/2026 | Y | EXP | 365 | 07/30/2025 | 10/24/2025 | 87 | 0 | 87 |  |  | 12/15/2025 | Connected |  | N
National Grid | PLAINVILLE | 187893 | 02762 | 11.4 | Solar | 05_07_91W43 | 06/25/2018 | 06/25/2018 | 3 | 0 | 3 | 07/02/2018 | 07/02/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2018 |  | 1/27/2020 | N | EXP | 55 |  |  | 0 | 0 | 0 |  |  | 1/3/2020 | Connected |  | N
National Grid | LYNN | 218290 | 01902 | 0 | Solar | 05_09_527L1 | 04/09/2019 | 05/13/2019 | 23 | 16 | 7 | 05/14/2019 | 05/14/2019 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2019 | Connected |  | N
National Grid | BERLIN | 178763 | 01503 | 142 | Solar | 05_05_3422W3 | 04/14/2011 | 04/14/2011 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 6/3/2014 | 6/3/2014 | 9/7/2012 | Connected |  | N
National Grid | HALIFAX | 635914 | 02338 | 3.8 | Solar | 05_12_12J904 | 08/28/2024 | 09/05/2024 | 1 | 0 | 1 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 |  | 10/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | ATTLEBORO | 682747 | 02703 | 15.2 | Solar | 05_05_318W3 | 04/04/2025 | 04/10/2025 | 4 | 0 | 4 | 04/11/2025 | 04/11/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 04/04/2025 | 5/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | WORCESTER | 177047 | 01610 | 876 | Solar | 05_07_797W24 | 10/17/2016 | 10/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2016 | 01/20/2017 | 58 | 43 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 | 10/17/2016 | 12/15/2021 | Y | STD | 741 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 299443 | 01028 | 7.44 | Solar | 05_05_9L3 | 07/02/2020 | 07/08/2020 | 3 | 1 | 2 | 07/09/2020 | 07/09/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 | 07/02/2020 | 7/5/2021 | Y | EXP | 365 | 10/06/2020 | 10/26/2020 | 20 | 0 | 20 |  |  | 11/4/2020 | Connected |  | N
National Grid | RANDOLPH | 458817 | 02368 | 0 | Solar | 05_01_1J363 | 09/14/2022 | 09/23/2022 | 7 | 7 | 0 | 09/26/2022 | 09/26/2022 | 124 | 37 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 663991 | 02302 | 3.8 | Solar | 05_09_139L5 | 01/06/2025 | 02/25/2025 | 27 | 22 | 5 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | GRANBY | 670368 | 01033 | 10 | Solar | 05_07_97W4 | 02/10/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | PLAINVILLE | 191213 | 02762 | 0 | Solar | 05_07_91W43 | 08/28/2018 | 09/14/2018 | 12 | 2 | 10 | 09/17/2018 | 09/17/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 258757 | 01904 | 7.6 | Solar | 05_09_527L1 | 10/07/2019 | 10/11/2019 | 3 | 0 | 3 | 10/15/2019 | 10/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 | 10/07/2019 | 10/7/2020 | Y | EXP | 365 | 06/02/2020 | 06/03/2020 | 1 | 0 | 1 |  |  | 7/23/2020 | Connected |  | N
National Grid | BERLIN | 178762 | 01503 | 102.6 | Solar | 05_05_3422W3 | 08/29/2011 | 08/29/2011 | 181 | 0 | 181 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2013 | 08/29/2011 | 6/23/2012 | Y | EXP | 229 | 10/11/2012 | 12/19/2012 | 32 | 0 | 32 | 2/7/2013 | 2/7/2013 | 3/12/2013 | Connected |  | N
National Grid | HALIFAX | 644745 | 02338 | 3.8 | Solar | 05_12_12J904 | 10/03/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 | 10/03/2024 | 12/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 685270 | 02703 | 15.2 | Solar | 05_05_318W3 | 04/15/2025 | 04/23/2025 | 5 | 0 | 5 | 04/24/2025 | 04/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177302 | 01602 | 532.8 | Solar | 05_07_797W24 | 11/15/2016 | 11/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 03/06/2017 | 74 | 59 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 |  | 12/1/2018 | N | STD | 27 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 335835 | 01036 | 9.12 | Solar | 05_05_9L3 | 04/15/2021 | 05/14/2021 | 20 | 20 | 0 | 05/17/2021 | 05/17/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  | 5/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2021 | Connected |  | N
National Grid | RANDOLPH | 547657 | 02368 | 3.8 | Solar | 05_01_1J363 | 08/21/2023 | 08/22/2023 | 1 | 0 | 1 | 08/23/2023 | 08/23/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 669722 | 02301 | 10 | Solar | 05_09_139L5 | 02/03/2025 | 02/20/2025 | 4 | 0 | 4 | 02/21/2025 | 02/21/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | GRANBY | 740392 | 01033 | 5.76 | Solar | 05_07_97W5 | 12/15/2025 | 12/16/2025 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 17 | 5 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PLAINVILLE | 288315 | 02762 | 0 | Other | 05_07_91W43 | 05/07/2020 | 08/26/2020 | 77 | 70 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2020 | 04/29/2021 | 166 | 26 | 140 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 291194 | 01902 | 1.92 | Solar | 05_09_527L1 | 07/31/2020 | 08/03/2020 | 0 | 0 | 0 | 08/04/2020 | 08/04/2020 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 178772 | 01503 | 300 | Solar | 05_05_3422W3 | 08/16/2012 | 08/16/2012 | 5 | 1 | 4 | 08/24/2012 | 08/24/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2012 |  | 11/27/2012 | N | EXP | 39 |  |  | 0 | 0 | 0 | 1/3/2013 | 1/3/2013 | 1/17/2013 | Connected |  | N
National Grid | BRIDGEWATER | 653929 | 02333 | 5.76 | Solar | 05_12_12J904 | 11/27/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 712988 | 02703 | 19.1 | Solar | 05_05_318W3 | 10/01/2025 | 10/27/2025 | 16 | 14 | 2 | 10/28/2025 | 10/28/2025 | 47 | 28 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 |  | 1/8/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2026 | Connected |  | N
National Grid | WORCESTER | 183820 | 01602 | 0 | Solar | 05_07_797W24 | 05/25/2018 | 05/25/2018 | 5 | 0 | 5 | 06/06/2018 | 06/06/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 356770 | 01036 | 300 | Solar | 05_05_9L3 | 07/14/2021 | 08/10/2021 | 19 | 9 | 10 |  |  | 48 | 20 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2022 | 07/14/2021 | 10/19/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 649168 | 02368 | 3.8 | Solar | 05_01_1J363 | 11/04/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/04/2024 | 3/2/2026 | Y | EXP | 365 | 01/23/2025 | 06/16/2025 | 145 | 0 | 145 |  |  | 8/18/2025 | Connected |  | N
National Grid | BROCKTON | 687653 | 02302 | 12.6 | Solar | 05_09_139L5 | 04/25/2025 | 05/22/2025 | 2 | 0 | 2 | 06/02/2025 | 06/02/2025 | 65 | 54 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 176559 | 01033 | 2052 | Solar | 05_07_97W5 | 10/08/2015 | 10/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2015 | 11/06/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 02/03/2016 | 08/09/2017 | 378 | 89 | 289 | 8/25/2016 |  | 10/14/2016 | N | STD | 5 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 311151 | 02762 | 10 | Solar | 05_07_91W43 | 10/01/2020 | 10/06/2020 | 1 | 0 | 1 | 10/07/2020 | 10/07/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2020 | 10/01/2020 | 8/18/2022 | Y | EXP | 365 | 08/10/2021 | 10/12/2021 | 42 | 3 | 39 |  |  | 12/20/2021 | Connected |  | N
National Grid | LYNN | 293669 | 01904 | 0 | Other | 05_09_527L1 | 01/05/2021 |  | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 178791 | 01503 | 86.6 | Solar | 05_05_3422W3 | 02/03/2017 | 02/03/2017 | 2 | 2 | 0 | 02/07/2017 | 02/07/2017 | 199 | 66 | 133 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2017 |  | 2/8/2018 | N | EXP | 254 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 727173 | 02341 | 15.2 | Solar | 05_12_12L2 | 10/16/2025 | 11/03/2025 | 11 | 7 | 4 | 11/04/2025 | 11/04/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATTLEBORO | 723459 | 02703 | 3.8 | Solar | 05_05_318W3 | 10/02/2025 | 10/07/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | WORCESTER | 290756 | 01602 | 7.68 | Solar | 05_07_797W24 | 05/06/2020 | 05/11/2020 | 2 | 0 | 2 | 05/12/2020 | 05/12/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2022 | Connected |  | N
National Grid | LONGMEADOW | 398708 | 01028 | 7.6 | Solar | 05_05_9L3 | 12/02/2021 | 12/07/2021 | 3 | 0 | 3 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  | 2/22/2023 | N | EXP | 45 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 654216 | 02368 | 7.6 | Solar | 05_01_1J363 | 11/15/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 701116 | 02301 | 7.6 | Solar | 05_09_139L5 | 06/25/2025 | 07/11/2025 | 2 | 0 | 2 | 07/18/2025 | 07/18/2025 | 14 | 2 | 12 | 08/20/2025 | 09/26/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 09/26/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 176979 | 01033 | 5.2 | Solar | 05_07_97W5 | 12/28/2016 | 12/28/2016 | 4 | 4 | 0 | 01/05/2017 | 01/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2017 | 12/28/2016 | 1/3/2018 | Y | EXP | 362 | 07/24/2017 | 08/10/2017 | 13 | 0 | 13 | 9/5/2017 | 9/5/2017 | 9/7/2017 | Connected |  | N
National Grid | FOXBOROUGH | 315789 | 02035 | 9.8 | Solar | 05_07_91W43 | 11/03/2020 | 11/05/2020 | 1 | 0 | 1 | 11/06/2020 | 11/06/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/03/2020 | 12/22/2024 | Y | EXP | 365 | 07/24/2021 | 07/26/2021 | 3 | 0 | 3 |  |  | 1/31/2025 | Connected |  | N
National Grid | LYNN | 300661 | 01902 | 6.72 | Solar | 05_09_527L1 | 07/10/2020 | 10/22/2020 | 72 | 27 | 45 | 10/23/2020 | 10/23/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2020 |  | 2/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2021 | Connected |  | N
National Grid | BERLIN | 178786 | 01503 | 19.4 | Solar | 05_05_3422W3 | 04/27/2015 | 04/27/2015 | 0 | 0 | 0 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2015 |  | 9/30/2015 | N | EXP | 153 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 7/1/2016 | Connected |  | N
National Grid | HANSON | 737918 | 02341 | 5.76 | Solar | 05_12_12L2 | 12/03/2025 | 12/05/2025 | 1 | 0 | 1 | 01/13/2026 | 01/13/2026 | 36 | 22 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ATTLEBORO | 661572 | 02703 | 11.5 | Solar | 05_05_318W5 | 12/23/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 3/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | WORCESTER | 299346 | 01602 | 10 | Solar | 05_07_797W24 | 07/01/2020 | 07/08/2020 | 4 | 0 | 4 | 07/09/2020 | 07/09/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 418617 | 01028 | 0 | Battery Add-On | 05_05_9L3 | 03/21/2022 | 04/05/2022 | 11 | 10 | 1 | 04/06/2022 | 04/06/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 660183 | 02322 | 5.76 | Solar | 05_01_1J363 | 12/12/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 702745 | 02301 | 5.76 | Solar | 05_09_139L5 | 07/09/2025 |  | 18 | 14 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 177321 | 01033 | 7.6 | Solar | 05_07_97W5 | 06/17/2016 | 06/17/2016 | 1 | 1 | 0 | 06/21/2016 | 06/21/2016 | 149 | 0 | 149 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/25/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 321262 | 02035 | 9.8 | Solar | 05_07_91W43 | 12/03/2020 | 12/08/2020 | 2 | 0 | 2 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  | 3/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2022 | Connected |  | N
National Grid | LYNN | 307066 | 01902 | 150 | Solar | 05_09_527L1 | 08/18/2020 | 09/16/2020 | 19 | 12 | 7 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 178784 | 01740 | 1000 | Solar | 05_05_3422W3 | 01/23/2015 | 01/23/2015 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 03/31/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HALIFAX | 740671 | 02338 | 11.5 | Solar | 05_12_12L2 | 12/16/2025 | 01/08/2026 | 3 | 0 | 3 | 02/03/2026 | 02/03/2026 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ATTLEBORO | 716128 | 02703 | 11.4 | Solar | 05_05_320W1 | 09/02/2025 | 10/02/2025 | 20 | 16 | 4 | 11/04/2025 | 11/04/2025 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 326952 | 01602 | 9.36 | Solar | 05_07_797W24 | 12/09/2020 | 01/08/2021 | 20 | 15 | 5 | 01/11/2021 | 01/11/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 1/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2021 | Connected |  | N
National Grid | LONGMEADOW | 444120 | 01028 | 9.86 | Solar | 05_05_9L3 | 09/09/2022 | 09/13/2022 | 2 | 0 | 2 | 09/14/2022 | 09/14/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 |  | 10/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2023 | Connected |  | N
National Grid | AVON | 720993 | 02322 | 18 | Solar | 05_01_1J369 | 10/06/2025 | 10/22/2025 | 1 | 0 | 1 | 11/05/2025 | 11/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROCKTON | 714478 | 02301 | 0 | Solar | 05_09_139L5 | 08/27/2025 | 08/29/2025 | 2 | 0 | 2 | 09/02/2025 | 09/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | GRANBY | 189432 | 01033 | 7.6 | Solar | 05_07_97W5 | 06/27/2018 | 06/27/2018 | 9 | 0 | 9 | 07/20/2018 | 07/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 06/27/2018 | 8/12/2020 | Y | EXP | 675 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 348390 | 02035 | 7.6 | Solar | 05_07_91W43 | 04/22/2021 | 04/28/2021 | 3 | 0 | 3 | 04/29/2021 | 04/29/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2021 |  | 8/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 311886 | 01915 | 8.4 | Solar | 05_09_527L1 | 10/20/2020 | 11/03/2020 | 1 | 0 | 1 | 11/04/2020 | 11/04/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 10/20/2020 | 6/4/2022 | Y | EXP | 365 | 06/25/2021 | 08/02/2021 | 38 | 0 | 38 |  |  | 12/20/2021 | Connected |  | N
National Grid | BOLTON | 178783 | 01740 | 1000 | Solar | 05_05_3422W3 | 01/23/2015 | 01/23/2015 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 03/31/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 746385 | 02341 |  | Battery Add-On | 05_12_12L2 | 01/20/2026 | 01/27/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ATTLEBORO | 726974 | 02703 | 15.2 | Solar | 05_05_320W1 | 10/16/2025 | 10/21/2025 | 3 | 0 | 3 | 10/22/2025 | 10/22/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 339190 | 01602 | 57.2 | Solar | 05_07_797W24 | 03/30/2021 | 12/09/2021 | 34 | 24 | 10 | 06/03/2021 | 06/03/2021 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2021 |  | 8/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2022 | Connected |  | N
National Grid | LONGMEADOW | 604389 | 01028 | 10 | Solar | 05_05_9L3 | 04/16/2024 | 04/24/2024 | 1 | 0 | 1 | 04/25/2024 | 04/25/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2024 | Connected |  | N
National Grid | RANDOLPH | 750966 | 02368 | 7.6 | Solar | 05_01_1J369 | 02/12/2026 | 02/16/2026 | 4 | 0 | 4 | 02/27/2026 | 02/27/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 177777 | 02301 | 3960 | Solar | 05_09_501L1 | 03/28/2017 | 04/18/2017 | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2017 | 05/11/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 | 03/28/2017 | 10/17/2027 | Y | STD | 14 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | GRANBY | 194453 | 01033 | 3.8 | Solar | 05_07_97W5 | 09/04/2018 | 10/05/2018 | 6 | 6 | 0 | 10/08/2018 | 10/08/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2018 | 09/04/2018 | 3/5/2019 | Y | EXP | 147 |  |  | 0 | 0 | 0 |  |  | 12/14/2018 | Connected |  | N
National Grid | FOXBOROUGH | 355333 | 02035 | 480 | Natural Gas | 05_07_91W43 | 06/14/2021 | 09/14/2021 | 64 | 52 | 12 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 322287 | 01915 | 5 | Solar | 05_09_527L1 | 11/19/2020 | 11/24/2020 | 2 | 0 | 2 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 212066 | 01532 | 17.6 | Solar | 05_05_3422W3 | 03/04/2019 | 03/14/2019 | 7 | 7 | 0 | 03/15/2019 | 03/15/2019 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2019 |  | 4/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HALIFAX | 754022 | 02338 | 5.76 | Solar | 05_12_12L2 | 03/03/2026 | 03/05/2026 | 2 | 0 | 2 | 03/06/2026 | 03/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ATTLEBORO | 728545 | 02703 | 0 | Battery Add-On | 05_05_320W1 | 10/23/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 | 10/23/2025 | 12/9/2026 | Y | EXP | 365 | 01/08/2026 | 02/04/2026 | 28 | 0 | 28 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 439549 | 01602 | 0 | Solar | 05_07_797W24 | 07/06/2022 | 07/08/2022 | 3 | 2 | 1 | 07/11/2022 | 07/11/2022 | 54 | 34 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 |  | 11/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2022 | Connected |  | N
National Grid | LONGMEADOW | 615713 | 01028 | 9.8 | Solar | 05_05_9L3 | 06/05/2024 | 07/15/2024 | 24 | 18 | 6 | 07/16/2024 | 07/16/2024 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 264740 | 02368 | 8.64 | Solar | 05_01_1J369 | 12/31/2019 | 02/19/2020 | 31 | 26 | 5 | 02/20/2020 | 02/20/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2020 | 12/31/2019 | 2/22/2021 | Y | EXP | 365 | 09/23/2020 | 01/25/2021 | 124 | 0 | 124 |  |  | 2/2/2021 | Connected |  | N
National Grid | BROCKTON | 177639 | 02302 | 2700 | Solar | 05_09_501L1 | 07/20/2017 | 01/11/2018 | 114 | 104 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2018 | 01/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 | 07/20/2017 | 10/17/2027 | Y | STD | 784 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | GRANBY | 195014 | 01033 | 7.6 | Solar | 05_07_97W5 | 09/06/2018 | 09/24/2018 | 3 | 3 | 0 | 09/25/2018 | 09/25/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2018 | 09/06/2018 | 3/5/2019 | Y | EXP | 162 |  |  | 0 | 0 | 0 |  |  | 1/16/2019 | Connected |  | N
National Grid | PLAINVILLE | 450999 | 02762 | 3.8 | Solar | 05_07_91W43 | 09/15/2022 | 09/19/2022 | 2 | 0 | 2 | 09/20/2022 | 09/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 09/15/2022 | 3/31/2024 | Y | EXP | 365 | 03/29/2023 | 03/31/2023 | 3 | 0 | 3 |  |  | 4/28/2023 | Connected |  | N
National Grid | BEVERLY | 323927 | 01915 | 7.6 | Solar | 05_09_527L1 | 11/05/2020 | 11/24/2020 | 12 | 10 | 2 | 11/25/2020 | 11/25/2020 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 |  | 11/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2021 | Connected |  | N
National Grid | NORTHBRIDGE | 259189 | 01534 | 12 | Solar | 05_05_3422W3 | 10/28/2019 | 11/04/2019 | 4 | 0 | 4 | 11/05/2019 | 11/05/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 |  | 10/28/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2020 | Connected |  | N
National Grid | EAST BRIDGEWATER | 174621 | 02333 | 190 | Solar | 05_12_12L2 | 04/06/2011 | 04/06/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2011 |  | 8/11/2012 | N | EXP | 38 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 1/18/2012 | Connected |  | N
National Grid | ATTLEBORO | 733037 | 02703 | 15.2 | Solar | 05_05_320W1 | 11/11/2025 | 11/19/2025 | 5 | 2 | 3 | 11/20/2025 | 11/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 463055 | 01602 | 2550 | Solar | 05_07_797W24 | 11/03/2022 |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 617491 | 01028 | 7.6 | Solar | 05_05_9L3 | 06/14/2024 | 07/02/2024 | 8 | 3 | 5 | 07/03/2024 | 07/03/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 539352 | 02368 | 6 | Solar | 05_01_1J369 | 02/12/2024 | 07/19/2023 | 9 | 9 | 0 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | BROCKTON | 735375 | 02301 | 100 | Solar | 05_09_501L1 | 12/01/2025 | 01/26/2026 | 36 | 28 | 8 | 01/27/2026 | 01/27/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BELCHERTOWN | 316225 | 01007 | 7.6 | Solar | 05_07_97W5 | 11/02/2020 | 11/09/2020 | 4 | 0 | 4 | 11/10/2020 | 11/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 381633 | 02762 | 5 | Solar | 05_07_91W43 | 10/04/2021 | 12/16/2021 | 26 | 16 | 10 | 11/04/2021 | 11/04/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 10/04/2021 | 4/14/2023 | Y | EXP | 365 | 02/22/2022 | 04/14/2022 | 51 | 0 | 51 |  |  | 5/13/2022 | Connected |  | N
National Grid | BEVERLY | 364394 | 01915 | 19 | Solar | 05_09_527L1 | 06/16/2021 | 06/17/2021 | 2 | 1 | 1 | 06/18/2021 | 06/18/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2021 |  | 8/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2021 | Connected |  | N
National Grid | WHITINSVILLE | 291839 | 01588 | 10 | Solar | 05_05_3422W3 | 05/14/2020 | 06/02/2020 | 11 | 7 | 4 | 06/03/2020 | 06/03/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2020 | Connected |  | N
National Grid | HANSON | 174782 | 02341 | 7.31 | Solar | 05_12_12L2 | 07/11/2013 | 07/11/2013 | 7 | 0 | 7 | 07/23/2013 | 07/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2013 |  | 10/31/2013 | N | EXP | 97 |  |  | 0 | 0 | 0 | 11/4/2013 | 11/4/2013 | 11/4/2013 | Connected |  | N
National Grid | ATTLEBORO | 174792 | 02703 | 225 | Solar | 05_05_320W1 | 06/20/2011 | 06/20/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2011 |  | 3/16/2012 | N | EXP | 185 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 3/16/2012 | Connected |  | N
National Grid | WORCESTER | 490153 | 01602 | 20 | Solar | 05_07_797W24 | 01/05/2023 | 01/06/2023 | 1 | 0 | 1 | 01/09/2023 | 01/09/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 |  | 3/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/25/2023 | Connected |  | N
National Grid | WEST BROOKFIELD | 643142 | 01585 | 10 | Solar | 05_05_9L3 | 09/26/2024 | 11/15/2024 | 18 | 16 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 09/26/2024 | 1/17/2026 | Y | EXP | 365 | 02/19/2025 | 02/18/2025 | 0 | 0 | 0 |  |  | 4/24/2025 | Connected |  | N
National Grid | RANDOLPH | 571562 | 02368 | 10 | Solar | 05_01_1J369 | 12/07/2023 | 12/12/2023 | 4 | 1 | 3 | 12/13/2023 | 12/13/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 | 12/07/2023 | 2/14/2025 | Y | EXP | 365 | 04/16/2024 | 08/28/2024 | 135 | 0 | 135 |  |  | 10/2/2024 | Connected |  | N
National Grid | BROCKTON | 737146 | 02302 | 20 | Solar | 05_09_501L1 | 12/02/2025 | 01/08/2026 | 25 | 24 | 1 | 01/09/2026 | 01/09/2026 | 39 | 27 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GRANBY | 466954 | 01033 | 3.77 | Solar | 05_07_97W5 | 02/23/2023 | 04/12/2023 | 34 | 28 | 6 | 04/13/2023 | 04/13/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2023 | 02/23/2023 | 7/23/2024 | Y | EXP | 365 | 10/21/2023 | 11/07/2023 | 18 | 0 | 18 |  |  | 11/9/2023 | Connected |  | Y
National Grid | PLAINVILLE | 409189 | 02762 | 4.8 | Solar | 05_07_91W43 | 02/11/2022 | 02/22/2022 | 6 | 0 | 6 | 02/23/2022 | 02/23/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 |  | 3/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2022 | Connected |  | N
National Grid | BEVERLY | 369951 | 01915 | 996 | Solar | 05_09_527L1 | 08/25/2021 |  | 53 | 30 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 347002 | 01568 | 999 | Solar | 05_05_3422W3 | 04/29/2021 | 05/16/2021 | 11 | 3 | 8 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 174863 | 02341 | 60 | Solar | 05_12_12L2 | 10/18/2011 | 10/18/2011 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2012 | 10/18/2011 | 7/13/2012 | Y | EXP | 127 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 7/13/2012 | Connected |  | N
National Grid | ATTLEBORO | 174791 | 02703 | 120 | Solar | 05_05_320W1 | 06/20/2011 | 06/20/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2011 |  | 3/12/2012 | N | EXP | 181 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 3/12/2012 | Connected |  | N
National Grid | WORCESTER | 499293 | 01602 | 19 | Solar | 05_07_797W24 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 6/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | WARREN | 645897 | 01585 | 15.2 | Solar | 05_05_9L3 | 10/11/2024 | 10/21/2024 | 5 | 4 | 1 | 10/22/2024 | 10/22/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 12/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | N
National Grid | RANDOLPH | 742072 | 02368 | 15.2 | Solar | 05_01_1J369 | 12/23/2025 | 12/26/2025 | 2 | 0 | 2 | 12/29/2025 | 12/29/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 175848 | 02302 | 224 | Solar | 05_09_501L1 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 | 05/25/2015 | 05/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 10/30/2015 | N | EXP | 121 |  |  | 0 | 0 | 0 | 7/1/2015 | 7/1/2015 | 12/15/2015 | Connected |  | N
National Grid | GRANBY | 572536 | 01033 | 9.6 | Solar | 05_07_97W5 | 11/27/2023 | 12/11/2023 | 10 | 7 | 3 | 12/12/2023 | 12/12/2023 | 26 | 3 | 23 | 02/15/2024 | 03/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 03/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 2/27/2024 | 11/27/2023 | 3/5/2025 | Y | EXP | 365 | 03/16/2024 | 04/19/2024 | 35 | 0 | 35 |  |  | 5/17/2024 | Connected |  | N
National Grid | FOXBOROUGH | 418384 | 02035 | 16.24 | Solar | 05_07_91W43 | 03/18/2022 | 03/28/2022 | 6 | 5 | 1 | 03/29/2022 | 03/29/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2022 |  | 11/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | BEVERLY | 398685 | 01915 | 9.84 | Solar | 05_09_527L1 | 12/01/2021 | 12/02/2021 | 1 | 0 | 1 | 12/03/2021 | 12/03/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 12/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2022 | Connected |  | N
National Grid | NORTHBRIDGE | 380603 | 01534 | 9.6 | Solar | 05_05_3422W3 | 09/22/2021 | 09/23/2021 | 2 | 1 | 1 | 09/24/2021 | 09/24/2021 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2021 |  | 11/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2021 | Connected |  | N
National Grid | HANSON | 175049 | 02341 | 85 | Solar | 05_12_12L2 | 10/18/2011 | 10/18/2011 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2012 | 10/18/2011 | 8/19/2012 | Y | EXP | 164 |  |  | 0 | 0 | 0 | 8/14/2012 | 8/14/2012 | 7/13/2012 | Connected |  | N
National Grid | ATTLEBORO | 175581 | 02703 | 13.6 | Solar | 05_05_320W1 | 12/12/2014 | 12/12/2014 | 38 | 38 | 0 | 02/10/2015 | 02/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2015 |  | 4/30/2015 | N | EXP | 78 |  |  | 0 | 0 | 0 | 2/5/2016 | 2/5/2016 | 2/5/2016 | Connected |  | N
National Grid | WORCESTER | 516332 | 01602 | 10 | Solar | 05_07_797W24 | 06/09/2023 | 07/12/2023 | 22 | 21 | 1 | 07/13/2023 | 07/13/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 06/09/2023 | 8/16/2024 | Y | EXP | 365 | 09/13/2023 | 09/13/2023 | 1 | 0 | 1 |  |  | 9/18/2023 | Connected |  | N
National Grid | WARE | 647336 | 01082 | 0 | Solar | 05_05_9L3 | 12/12/2024 | 12/18/2024 | 1 | 0 | 1 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/12/2024 | 2/4/2026 | Y | EXP | 365 | 03/18/2025 | 04/07/2025 | 21 | 0 | 21 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 625582 | 02368 | 10 | Solar | 05_01_1J370 | 07/17/2024 | 07/26/2024 | 2 | 0 | 2 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 07/17/2024 | 8/20/2025 | Y | EXP | 365 | 12/05/2024 | 03/07/2025 | 93 | 0 | 93 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175847 | 02302 | 70 | Solar | 05_09_501L1 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 | 05/25/2015 | 05/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 10/30/2015 | N | EXP | 121 |  |  | 0 | 0 | 0 | 7/1/2015 | 7/1/2015 | 12/15/2015 | Connected |  | N
National Grid | GRANBY | 579463 | 01033 | 10 | Solar | 05_07_97W5 | 01/10/2024 | 01/16/2024 | 3 | 0 | 3 | 01/17/2024 | 01/17/2024 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 01/10/2024 | 3/6/2025 | Y | EXP | 365 | 05/24/2024 | 09/11/2024 | 111 | 0 | 111 |  |  | 9/17/2024 | Connected |  | N
National Grid | FOXBOROUGH | 438914 | 02035 | 6 | Solar | 05_07_91W43 | 07/05/2022 | 08/11/2022 | 27 | 24 | 3 | 08/12/2022 | 08/12/2022 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2022 | 07/05/2022 | 5/22/2024 | Y | EXP | 365 | 05/13/2023 | 05/19/2023 | 7 | 0 | 7 |  |  | 7/24/2023 | Connected |  | N
National Grid | BEVERLY | 448872 | 01915 | 10 | Solar | 05_09_527L1 | 08/31/2022 | 09/01/2022 | 1 | 0 | 1 | 09/02/2022 | 09/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 |  | 10/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2022 | Connected |  | N
National Grid | WHITINSVILLE | 396690 | 01588 | 15.2 | Solar | 05_05_3422W3 | 11/19/2021 | 11/23/2021 | 1 | 0 | 1 | 11/24/2021 | 11/24/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2021 |  | 1/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2022 | Connected |  | N
National Grid | HALIFAX | 175316 | 02338 | 6.45 | Solar | 05_12_12L2 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2014 |  | 11/28/2014 | N | EXP | 52 |  |  | 0 | 0 | 0 | 10/7/2014 | 10/7/2014 | 4/27/2015 | Connected |  | N
National Grid | ATTLEBORO | 175862 | 02703 | 5 | Solar | 05_05_320W1 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/10/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 5/5/2016 | Connected |  | N
National Grid | WORCESTER | 518671 | 01602 | 9.86 | Solar | 05_07_797W24 | 05/01/2023 | 05/09/2023 | 6 | 5 | 1 | 05/10/2023 | 05/10/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 6/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2023 | Connected |  | N
National Grid | WARE | 685298 | 01082 | 16.34 | Solar | 05_05_9L3 | 04/16/2025 | 04/24/2025 | 5 | 0 | 5 | 04/25/2025 | 04/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2025 | Connected |  | N
National Grid | RANDOLPH | 633683 | 02368 | 3.8 | Solar | 05_01_1J370 | 08/19/2024 | 08/28/2024 | 3 | 0 | 3 | 08/29/2024 | 08/29/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2024 |  | 9/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | BROCKTON | 176279 | 02302 | 75 | Solar | 05_09_501L1 | 05/06/2015 | 05/06/2015 | 1 | 1 | 0 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2015 |  | 10/30/2015 | N | EXP | 149 |  |  | 0 | 0 | 0 | 6/10/2015 | 6/10/2015 | 11/23/2016 | Connected |  | N
National Grid | GRANBY | 625881 | 01033 | 5.76 | Solar | 05_07_97W5 | 07/18/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | BROCKTON | 492594 | 02302 | 6 | Solar | 05_07_91W43 | 02/01/2023 | 02/03/2023 | 2 | 0 | 2 | 02/06/2023 | 02/06/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  | 9/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 471040 | 01915 | 3.8 | Solar | 05_09_527L1 | 12/06/2022 | 12/09/2022 | 3 | 0 | 3 | 12/12/2022 | 12/12/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 | 12/06/2022 | 4/11/2024 | Y | EXP | 365 | 03/10/2023 | 04/12/2023 | 34 | 0 | 34 |  |  | 4/18/2023 | Connected |  | Y
National Grid | WHITINSVILLE | 400659 | 01588 | 19.72 | Solar | 05_05_3422W3 | 02/16/2022 | 03/09/2022 | 14 | 13 | 1 | 03/10/2022 | 03/10/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2022 |  | 4/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2022 | Connected |  | N
National Grid | HALIFAX | 175647 | 02338 | 3.66 | Solar | 05_12_12L2 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2015 |  | 2/16/2015 | N | EXP | 41 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 9/29/2015 | Connected |  | N
National Grid | ATTLEBORO | 175949 | 02703 | 15.2 | Solar | 05_05_320W1 | 03/13/2015 | 03/13/2015 | 7 | 4 | 3 | 03/26/2015 | 03/26/2015 | 468 | 0 | 468 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 7/31/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 4/14/2015 | 4/14/2015 |  | Withdrawn |  | N
National Grid | WORCESTER | 601957 | 01602 | 10 | Solar | 05_07_797W24 | 04/11/2024 | 04/12/2024 | 1 | 0 | 1 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 04/11/2024 | 5/16/2025 | Y | EXP | 365 | 05/23/2024 | 07/15/2024 | 54 | 0 | 54 |  |  | 10/16/2024 | Connected |  | N
National Grid | WARE | 697764 | 01082 | 15.2 | Solar | 05_05_9L3 | 06/11/2025 | 06/16/2025 | 3 | 0 | 3 | 06/17/2025 | 06/17/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 06/11/2025 | 8/14/2026 | Y | EXP | 365 | 10/02/2025 | 10/01/2025 | 0 | 0 | 0 |  |  | 10/11/2025 | Connected |  | N
National Grid | RANDOLPH | 649792 | 02368 | 7.6 | Solar | 05_01_1J370 | 11/06/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/06/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | BROCKTON | 176295 | 02302 | 1000 | Solar | 05_09_501L1 | 09/09/2015 | 09/09/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/15/2015 | 10/20/2015 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/16/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 642842 | 01033 | 10 | Solar | 05_07_97W5 | 09/30/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 | 09/30/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | PLAINVILLE | 540461 | 02762 | 10 | Solar | 05_07_91W43 | 07/17/2023 | 07/18/2023 | 1 | 0 | 1 | 07/19/2023 | 07/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2023 | 07/17/2023 | 9/16/2024 | Y | EXP | 365 | 10/28/2023 | 11/14/2023 | 18 | 0 | 18 |  |  | 1/26/2024 | Connected |  | N
National Grid | BEVERLY | 501268 | 01915 | 2.03 | Solar | 05_09_527L1 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 149 | 134 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2023 |  | 1/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2024 | Connected |  | N
National Grid | UPTON | 405128 | 01568 | 100 | Solar | 05_05_3422W3 | 01/06/2022 |  | 207 | 200 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANSON | 176390 | 02341 | 7.6 | Solar | 05_12_12L2 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 251 | 0 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 |  | 2/6/2017 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 176133 | 02703 | 10 | Solar | 05_05_320W1 | 04/15/2015 | 04/15/2015 | 1 | 1 | 0 | 04/17/2015 | 04/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 | 04/15/2015 | 12/31/2016 | Y | EXP | 614 | 02/19/2016 | 02/29/2016 | 6 | 0 | 6 | 4/27/2015 | 4/27/2015 | 8/8/2016 | Connected |  | N
National Grid | WORCESTER | 646911 | 01602 | 7.6 | Solar | 05_07_797W24 | 10/24/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | WARE | 701607 | 01082 | 0 | Battery Add-On | 05_05_9L3 | 06/27/2025 | 07/01/2025 | 2 | 0 | 2 | 07/02/2025 | 07/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 |  | 8/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid | RANDOLPH | 291231 | 02368 | 7.6 | Solar | 05_01_1J390 | 06/26/2020 | 07/08/2020 | 7 | 6 | 1 | 07/09/2020 | 07/09/2020 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 176368 | 02301 | 499 | Solar | 05_09_501L1 | 05/06/2016 | 05/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2016 | 06/07/2016 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/11/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 650545 | 01007 | 7.6 | Solar | 05_07_97W5 | 10/29/2024 | 11/07/2024 | 6 | 4 | 2 | 11/08/2024 | 11/08/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 |  | 12/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | FOXBOROUGH | 564420 | 02035 | 9.765 | Solar | 05_07_91W43 | 01/24/2024 | 01/25/2024 | 2 | 1 | 1 | 01/26/2024 | 01/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 01/24/2024 | 3/8/2025 | Y | EXP | 365 | 04/10/2024 | 05/08/2024 | 29 | 0 | 29 |  |  | 5/9/2024 | Connected |  | N
National Grid | BEVERLY | 522509 | 01915 | 12.18 | Solar | 05_09_527L1 | 05/04/2023 | 05/08/2023 | 2 | 0 | 2 | 05/09/2023 | 05/09/2023 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 433335 | 01568 | 300 | Solar | 05_05_3422W3 | 07/12/2022 | 12/22/2022 | 111 | 101 | 10 |  |  | 209 | 185 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 176572 | 02341 | 68 | Solar | 05_12_12L2 | 02/11/2016 | 02/11/2016 | 3 | 3 | 0 | 02/17/2016 | 02/17/2016 | 162 | 0 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/16/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/29/2016 | 9/29/2016 |  | Withdrawn |  | N
National Grid | ATTLEBORO | 176293 | 02703 | 7.6 | Solar | 05_05_320W1 | 07/10/2015 | 07/10/2015 | 15 | 15 | 0 | 08/03/2015 | 08/03/2015 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/18/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 651648 | 01602 | 7.6 | Solar | 05_07_797W24 | 11/04/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/04/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 718105 | 01082 | 11.4 | Solar | 05_05_9L3 | 09/10/2025 | 09/26/2025 | 2 | 0 | 2 | 10/27/2025 | 10/27/2025 | 51 | 27 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 1/29/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2026 | Connected |  | N
National Grid | RANDOLPH | 174831 | 02368 | 2500 | Solar | 05_01_201W1 | 08/01/2012 | 08/01/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2012 | 11/24/2012 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 176472 | 02302 | 375 | Hydro | 05_09_501L1 | 03/21/2016 | 03/21/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2016 | 05/13/2016 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 658229 | 01033 | 5.76 | Solar | 05_07_97W5 | 12/03/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 562243 | 02762 | 6 | Solar | 05_07_91W43 | 10/25/2023 |  | 81 | 25 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 540230 | 01915 | 5 | Solar | 05_09_527L1 | 07/24/2023 | 07/26/2023 | 2 | 0 | 2 | 07/27/2023 | 07/27/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 | 07/24/2023 | 12/2/2024 | Y | EXP | 365 | 11/17/2023 | 12/14/2023 | 28 | 0 | 28 |  |  | 2/17/2024 | Connected |  | N
National Grid | NORTHBRIDGE | 493072 | 01534 | 0 | Other | 05_05_3422W3 | 05/01/2023 | 06/29/2023 | 40 | 30 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2023 | 12/07/2023 | 110 | 96 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 177208 | 02341 | 7 | Solar | 05_12_12L2 | 06/06/2016 | 06/06/2016 | 3 | 3 | 0 | 06/10/2016 | 06/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 | 06/06/2016 | 6/12/2017 | Y | EXP | 357 | 08/22/2016 | 10/07/2016 | 33 | 0 | 33 | 11/2/2016 | 11/2/2016 | 11/7/2016 | Connected |  | N
National Grid | ATTLEBORO | 176431 | 02703 | 6 | Solar | 05_05_320W1 | 03/11/2016 | 03/11/2016 | 3 | 3 | 0 | 03/17/2016 | 03/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 |  | 3/19/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 10/28/2016 | 10/28/2016 | 11/1/2016 | Connected |  | N
National Grid | WORCESTER | 654121 | 01602 | 5.7 | Solar | 05_07_797W24 | 11/18/2024 | 12/12/2024 | 6 | 2 | 4 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/18/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | WARE | 265289 | 01082 | 600 | Natural Gas | 05_05_9L4 | 12/02/2020 | 01/05/2021 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2021 | 02/24/2021 | 34 | 13 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2023 | 12/02/2020 | 6/15/2026 | Y | STD | 69 | 06/15/2024 |  | 630 | 422 | 208 |  |  |  | Construction |  | N
National Grid | RANDOLPH | 174830 | 02368 | 500 | Solar | 05_01_201W1 | 08/01/2012 | 08/01/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2012 | 10/09/2012 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 177641 | 02302 | 3200 | Solar | 05_09_501L1 | 07/20/2017 | 01/11/2018 | 113 | 104 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2018 | 01/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 737857 | 01033 | 5.76 | Solar | 05_07_97W5 | 12/09/2025 | 01/08/2026 | 19 | 19 | 0 | 01/09/2026 | 01/09/2026 | 21 | 9 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 568122 | 02762 | 22.8 | Solar | 05_07_91W43 | 11/22/2023 | 12/18/2023 | 17 | 14 | 3 | 12/19/2023 | 12/19/2023 | 288 | 263 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | BEVERLY | 547979 | 01915 | 10 | Solar | 05_09_527L1 | 08/28/2023 | 08/29/2023 | 2 | 1 | 1 | 08/30/2023 | 08/30/2023 | 26 | 1 | 25 | 11/02/2023 | 12/11/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 12/11/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 11/29/2023 |  | 12/21/2024 | N | EXP | 365 | 01/18/2024 | 01/31/2024 | 14 | 0 | 14 |  |  | 2/22/2024 | Connected |  | N
National Grid | NORTHBRIDGE | 495226 | 01534 | 15.2 | Solar | 05_05_3422W3 | 01/26/2023 | 04/14/2023 | 55 | 55 | 0 | 04/18/2023 | 04/18/2023 | 78 | 57 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2023 |  | 11/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2024 | Connected |  | N
National Grid | HANSON | 177385 | 02341 | 7.6 | Solar | 05_12_12L2 | 11/28/2016 | 11/28/2016 | 1 | 1 | 0 | 12/01/2016 | 12/01/2016 | 130 | 0 | 130 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2016 |  | 12/5/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 176467 | 02703 | 27 | Solar | 05_05_320W1 | 02/05/2016 | 02/05/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2016 |  | 2/13/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 11/18/2016 | 11/18/2016 | 12/5/2016 | Connected |  | N
National Grid | WORCESTER | 693651 | 01602 | 17.6 | Solar | 05_07_797W24 | 06/02/2025 | 06/06/2025 | 4 | 0 | 4 | 06/09/2025 | 06/09/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2025 | Connected |  | N
National Grid | WARE | 358156 | 01082 | 875 | Solar | 05_05_9L4 | 07/26/2021 | 11/04/2021 | 71 | 61 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2021 | 02/03/2022 | 62 | 15 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | RANDOLPH | 174859 | 02368 | 500 | Solar | 05_01_201W1 | 08/01/2012 | 08/01/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2012 | 11/24/2012 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 177640 | 02302 | 2980 | Solar | 05_09_501L1 | 07/20/2017 | 01/11/2018 | 113 | 104 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2018 | 01/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 704381 | 01033 | 3.8 | Solar | 05_07_98W10 | 07/11/2025 | 02/24/2026 | 2 | 0 | 2 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PLAINVILLE | 571413 | 02762 | 75 | Solar | 05_07_91W43 | 11/22/2023 |  | 110 | 26 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 563791 | 01915 | 6 | Solar | 05_09_527L1 | 10/24/2023 | 10/26/2023 | 2 | 1 | 1 | 10/27/2023 | 10/27/2023 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 1/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2024 | Connected |  | N
National Grid | NORTHBRIDGE | 601533 | 01534 | 7.6 | Solar | 05_05_3422W3 | 04/04/2024 | 04/17/2024 | 9 | 5 | 4 | 04/18/2024 | 04/18/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  | 4/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2024 | Connected |  | N
National Grid | HANSON | 178243 | 02341 | 15.04 | Solar | 05_12_12L2 | 02/20/2018 | 02/20/2018 | 31 | 31 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/26/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 176739 | 02703 | 3 | Solar | 05_05_320W1 | 10/29/2015 | 10/29/2015 | 2 | 2 | 0 | 11/04/2015 | 11/04/2015 | 275 | 0 | 275 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2015 |  | 11/7/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 11/17/2015 | 11/17/2015 |  | Withdrawn |  | N
National Grid | SHIRLEY | 479187 | 01464 | 4990 | Solar | 05_07_797W29 | 05/30/2023 | 07/13/2023 | 29 | 19 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2023 | 08/17/2023 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 736512 | 01082 | 18.85 | Solar | 05_05_9L4 | 12/05/2025 | 01/30/2026 | 5 | 3 | 2 | 02/02/2026 | 02/02/2026 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | RANDOLPH | 175452 | 02368 | 2000 | Solar | 05_01_201W1 | 07/16/2014 | 07/16/2014 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2014 | 08/20/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 07/16/2014 | 2/1/2016 | Y | STD | 41 | 04/20/2016 | 08/10/2016 | 77 | 0 | 77 | 8/12/2016 | 8/12/2016 | 8/12/2016 | Connected |  | N
National Grid | BROCKTON | 177638 | 02301 | 4282 | Solar | 05_09_501L1 | 07/20/2017 | 01/11/2018 | 114 | 104 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2018 | 01/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 | 07/20/2017 |  | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 750444 | 01033 | 11.5 | Solar | 05_07_98W10 | 02/10/2026 | 02/17/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BROCKTON | 576220 | 02302 | 2.32 | Solar | 05_07_91W43 | 12/20/2023 | 12/22/2023 | 1 | 1 | 0 | 12/26/2023 | 12/26/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 570155 | 01915 | 10 | Solar | 05_09_527L1 | 11/27/2023 | 11/28/2023 | 1 | 0 | 1 | 11/29/2023 | 11/29/2023 | 29 | 9 | 20 | 01/22/2024 | 01/24/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  | 01/24/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 2/7/2024 |  | 2/19/2025 | N | EXP | 365 | 02/28/2024 | 04/03/2024 | 36 | 0 | 36 |  |  | 4/9/2024 | Connected |  | N
National Grid | UPTON | 637353 | 01568 | 11.5 | Solar | 05_05_3422W3 | 09/03/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 32 | 18 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 |  | 1/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | HANSON | 178383 | 02341 | 15.2 | Solar | 05_12_12L2 | 01/15/2018 | 01/15/2018 | 38 | 13 | 25 | 03/27/2018 | 03/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2018 |  | 1/21/2019 | N | EXP | 299 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 176840 | 02703 | 7 | Solar | 05_05_320W1 | 05/02/2016 | 05/02/2016 | 5 | 5 | 0 | 05/09/2016 | 05/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2016 | 05/02/2016 | 5/7/2017 | Y | EXP | 347 | 08/01/2016 | 10/19/2016 | 55 | 0 | 55 | 10/26/2016 | 10/26/2016 | 10/26/2016 | Connected |  | N
National Grid | SHIRLEY | 681042 | 01464 | 1826 | Solar | 05_07_797W29 | 04/07/2025 | 04/25/2025 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/28/2025 | 06/06/2025 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARREN | 741152 | 01083 | 9.12 | Solar | 05_05_9L4 | 12/18/2025 | 12/19/2025 | 11 | 8 | 3 | 01/15/2026 | 01/15/2026 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 | 12/18/2025 | 2/17/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | RANDOLPH | 175557 | 02368 | 996 | Solar | 05_01_201W1 | 07/30/2014 | 07/30/2014 | 6 | 1 | 5 |  |  | 0 | 0 | 0 | 10/01/2014 | 10/13/2014 | 8 | 0 | 8 | 08/08/2014 | 09/10/2014 | 22 | 1 | 21 |  | 10/13/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 8/25/2015 | 07/30/2014 | 12/10/2016 | Y | STD | 473 | 07/07/2016 | 12/20/2016 | 114 | 0 | 114 | 12/7/2016 | 12/7/2016 | 12/21/2016 | Connected |  | N
National Grid | BROCKTON | 177778 | 02301 | 8200 | Solar | 05_09_501L1 | 03/28/2017 | 04/18/2017 | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2017 | 05/11/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 | 03/28/2017 |  | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 177139 | 01033 | 7.6 | Solar | 05_07_98W10 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 |  | 6/6/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 578958 | 02035 | 7.6 | Solar | 05_07_91W43 | 01/31/2024 | 02/01/2024 | 1 | 0 | 1 | 02/02/2024 | 02/02/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 3/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2024 | Connected |  | N
National Grid | BEVERLY | 583851 | 01915 | 15.66 | Solar | 05_09_527L1 | 01/16/2024 | 01/18/2024 | 2 | 0 | 2 | 01/19/2024 | 01/19/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | WHITINSVILLE | 644099 | 01588 | 7.6 | Solar | 05_05_3422W3 | 10/01/2024 | 11/12/2024 | 14 | 12 | 2 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HALIFAX | 186214 | 02338 | 9.92 | Solar | 05_12_12L2 | 05/24/2018 | 05/24/2018 | 2 | 0 | 2 | 06/25/2018 | 06/25/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 |  |  | N | EXP | 53 |  |  | 0 | 0 | 0 |  |  | 11/12/2019 | Connected |  | N
National Grid | ATTLEBORO | 177348 | 02703 | 7.6 | Solar | 05_05_320W1 | 11/23/2016 | 11/23/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2016 |  | 11/28/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 750514 | 01464 |  | Battery Add-On | 05_05_9L4 | 02/11/2026 | 02/18/2026 | 4 | 0 | 4 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BROOKFIELD | 175925 | 01585 | 750 | Solar | 05_01_201W1 | 05/29/2015 | 06/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2015 | 07/01/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 09/30/2016 | 06/15/2016 | 0 | 0 | 0 | 12/5/2018 | 05/29/2015 | 12/31/2022 | Y | STD | 324 | 04/16/2022 | 06/18/2022 | 64 | 0 | 64 |  |  | 12/29/2022 | Connected |  | N
National Grid | BROCKTON | 177877 | 02301 | 900 | Solar | 05_09_501L1 | 10/17/2017 | 11/29/2017 | 22 | 21 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 201105 | 02301 | 496 | Solar | 05_07_98W10 | 11/15/2018 | 12/06/2018 | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 580600 | 01033 | 9.765 | Solar | 05_07_91W43 | 01/23/2024 | 01/24/2024 | 1 | 0 | 1 | 01/25/2024 | 01/25/2024 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 | 01/23/2024 | 3/4/2025 | Y | EXP | 365 | 03/26/2024 | 04/22/2024 | 28 | 0 | 28 |  |  | 4/26/2024 | Connected |  | N
National Grid | FOXBOROUGH | 595501 | 02035 | 10 | Solar | 05_09_527L1 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 65 | 51 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2024 | 03/27/2024 | 7/28/2025 | Y | EXP | 365 | 08/22/2024 | 08/29/2024 | 8 | 0 | 8 |  |  | 12/12/2024 | Connected |  | N
National Grid | BEVERLY | 651087 | 01915 | 5.76 | Solar | 05_05_3422W3 | 11/12/2024 | 12/06/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/12/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | Y
National Grid | UPTON | 187345 | 01568 | 3.8 | Solar | 05_12_12L2 | 06/06/2018 | 06/06/2018 | 0 | 0 | 0 | 06/25/2018 | 06/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2018 | 06/06/2018 | 6/24/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2019 | Connected |  | N
National Grid | HANSON | 177890 | 02341 | 15.2 | Solar | 05_05_320W1 | 04/12/2017 | 04/12/2017 | 4 | 3 | 1 | 04/20/2017 | 04/20/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2017 |  | 4/18/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/29/2017 | 8/29/2017 | 9/5/2017 | Connected |  | N
National Grid | ATTLEBORO | 716184 | 02703 | 8 | Solar | 05_07_797W29 | 09/02/2025 | 02/11/2026 | 39 | 38 | 1 | 02/12/2026 | 02/12/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SHIRLEY | 750117 | 01464 | 0 | Battery Add-On | 05_05_9L4 | 02/09/2026 |  | 18 | 17 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WEST BROOKFIELD | 176075 | 01585 | 920 | Solar | 05_01_201W1 | 08/18/2015 | 08/18/2015 | 7 | 7 | 0 | 08/31/2015 | 08/31/2015 | 0 | 0 | 0 | 11/06/2015 | 12/02/2015 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 12/02/2015 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 3/23/2016 | 08/18/2015 | 8/25/2016 | Y | EXP | 155 |  |  | 0 | 0 | 0 | 3/8/2017 | 3/8/2017 | 3/8/2017 | Connected |  | N
National Grid | BROCKTON | 177876 | 02301 | 900 | Solar | 05_09_501L1 | 10/17/2017 | 11/29/2017 | 22 | 21 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 292050 | 02302 | 499 | Solar | 05_07_98W10 | 05/14/2020 | 05/29/2020 | 10 | 3 | 7 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2020 | 05/14/2020 | 3/29/2026 | Y | STD | 484 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 591245 | 01033 | 3.78 | Solar | 05_07_91W43 | 03/06/2024 | 03/11/2024 | 3 | 0 | 3 | 03/12/2024 | 03/12/2024 | 4 | 1 | 3 | 04/08/2024 | 05/02/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 05/02/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 5/3/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 598591 | 02762 | 10 | Solar | 05_09_527L1 | 03/27/2024 | 04/23/2024 | 19 | 16 | 3 | 04/24/2024 | 04/24/2024 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 | 03/27/2024 | 7/4/2025 | Y | EXP | 365 | 08/08/2024 | 08/13/2024 | 6 | 0 | 6 |  |  | 9/18/2024 | Connected |  | N
National Grid | BEVERLY | 660959 | 01915 | 10 | Solar | 05_05_3422W3 | 12/16/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 12/16/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | UPTON | 187972 | 01568 | 15.2 | Solar | 05_12_12L2 | 06/13/2018 | 06/13/2018 | 10 | 2 | 8 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 178493 | 02333 | 4980 | Solar | 05_05_320W1 | 12/01/2017 | 12/01/2017 | 45 | 43 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2018 | 03/26/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2018 | 12/01/2017 | 3/31/2021 | Y | STD | 434 | 01/14/2021 | 03/31/2021 | 76 | 0 | 76 |  |  | 3/31/2021 | Connected |  | N
National Grid | ATTLEBORO | 751083 | 02703 | 13.611 | Solar | 05_07_797W29 | 02/13/2026 | 02/19/2026 | 3 | 1 | 2 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AYER | 174147 | 01432 | 9.99 | Solar | 05_05_9L4 | 04/10/2012 | 04/10/2012 | 14 | 0 | 14 | 05/03/2012 | 05/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2012 | 04/10/2012 | 6/1/2012 | Y | EXP | 2 | 01/21/2013 | 02/25/2013 | 19 | 0 | 19 | 3/4/2013 | 3/4/2013 | 3/15/2013 | Connected |  | N
National Grid | WARREN | 176238 | 01083 | 1000 | Solar | 05_01_201W1 | 04/27/2015 | 04/27/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2015 | 06/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 08/26/2016 | 06/24/2016 | 0 | 0 | 0 | 8/4/2016 | 04/27/2015 | 7/31/2018 | Y | STD | 726 | 11/28/2017 | 05/30/2018 | 183 | 0 | 183 | 1/25/2018 | 1/25/2018 | 6/29/2018 | Connected |  | N
National Grid | BROCKTON | 178701 | 02301 | 5000 | Solar | 05_09_501L1 | 02/08/2018 | 02/08/2018 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2018 | 05/04/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/14/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 368085 | 02301 | 7.6 | Solar | 05_07_98W10 | 07/19/2021 | 07/22/2021 | 3 | 0 | 3 | 07/23/2021 | 07/23/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2021 | 07/19/2021 | 10/30/2024 | Y | EXP | 365 | 03/01/2022 | 03/02/2022 | 2 | 0 | 2 |  |  | 11/15/2023 | Connected |  | N
National Grid | BELCHERTOWN | 590937 | 01007 | 10 | Solar | 05_07_91W43 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 602089 | 02762 | 6 | Solar | 05_09_527L1 | 04/11/2024 | 04/16/2024 | 2 | 0 | 2 | 04/17/2024 | 04/17/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 | 04/11/2024 | 6/6/2025 | Y | EXP | 365 | 08/22/2024 | 08/21/2024 | 0 | 0 | 0 |  |  | 8/24/2024 | Connected |  | N
National Grid | BEVERLY | 669146 | 01915 | 10 | Solar | 05_05_3422W3 | 01/31/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N
National Grid | UPTON | 188503 | 01568 | 8.32 | Solar | 05_12_12L2 | 07/23/2018 | 07/30/2018 | 5 | 3 | 2 | 07/31/2018 | 07/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 |  | 8/8/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2018 | Connected |  | N
National Grid | EAST BRIDGEWATER | 178492 | 02333 | 4980 | Solar | 05_05_320W1 | 12/01/2017 | 12/01/2017 | 45 | 43 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2018 | 03/26/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2018 | 12/01/2017 | 3/31/2021 | Y | STD | 434 | 12/19/2020 | 03/24/2021 | 95 | 0 | 95 |  |  | 3/31/2021 | Connected |  | N
National Grid | ATTLEBORO | 751328 | 02703 | 11.5 | Solar | 05_07_797W29 | 02/16/2026 | 03/04/2026 | 12 | 10 | 2 | 03/05/2026 | 03/05/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AYER | 174146 | 01432 | 9.99 | Solar | 05_05_9L4 | 04/10/2012 | 04/10/2012 | 14 | 0 | 14 | 05/03/2012 | 05/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2012 | 04/10/2012 | 6/1/2012 | Y | EXP | 2 | 01/21/2013 | 02/25/2013 | 19 | 0 | 19 | 3/4/2013 | 3/4/2013 | 3/15/2013 | Connected |  | N
National Grid | WARE | 176239 | 01082 | 1000 | Solar | 05_01_201W1 | 04/27/2015 | 04/27/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2015 | 06/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 03/15/2016 | 06/24/2016 | 69 | 0 | 69 | 8/4/2016 | 04/27/2015 | 7/31/2018 | Y | STD | 726 | 11/28/2017 | 05/30/2018 | 183 | 0 | 183 | 1/9/2018 | 1/9/2018 | 6/29/2018 | Connected |  | N
National Grid | BROCKTON | 328673 | 02301 | 0 | Solar | 05_09_501L1 | 12/01/2020 | 12/08/2020 | 4 | 0 | 4 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 1/12/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2021 | Connected |  | N
National Grid | BROCKTON | 389731 | 02302 | 0 | Other | 05_07_98W10 | 11/10/2021 | 01/04/2022 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 607506 | 01033 | 3.8 | Solar | 05_07_91W43 | 04/29/2024 | 05/14/2024 | 3 | 0 | 3 | 05/15/2024 | 05/15/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 625323 | 02762 | 17.6 | Solar | 05_09_527L1 | 07/23/2024 | 07/25/2024 | 2 | 0 | 2 | 07/26/2024 | 07/26/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 07/23/2024 | 8/19/2025 | Y | EXP | 365 | 10/02/2024 | 10/01/2024 | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | N
National Grid | BEVERLY | 710748 | 01915 | 20 | Solar | 05_05_3422W3 | 08/21/2025 | 08/22/2025 | 1 | 0 | 1 | 08/25/2025 | 08/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | UPTON | 189636 | 01568 | 11.4 | Solar | 05_12_12L2 | 06/29/2018 | 06/29/2018 | 3 | 3 | 0 | 10/10/2018 | 10/10/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 186263 | 02333 | 17.6 | Solar | 05_05_320W1 | 06/13/2018 | 06/13/2018 | 12 | 6 | 6 | 07/02/2018 | 07/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 7/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2018 | Connected |  | N
National Grid | ATTLEBORO | 174821 | 02703 | 180 | Solar | 05_07_797W29 | 08/02/2013 | 08/02/2013 | 7 | 0 | 7 | 08/14/2013 | 08/14/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2013 | 08/02/2013 | 11/1/2014 | Y | EXP | 432 |  |  | 0 | 0 | 0 | 2/13/2015 | 2/13/2015 | 2/13/2015 | Connected |  | N
National Grid | SHIRLEY | 174145 | 01464 | 9.99 | Solar | 05_05_9L4 | 04/10/2012 | 04/10/2012 | 13 | 0 | 13 | 05/02/2012 | 05/02/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2012 | 04/10/2012 | 6/1/2012 | Y | EXP | 2 | 01/21/2013 | 02/25/2013 | 19 | 0 | 19 | 3/4/2013 | 3/4/2013 | 3/15/2013 | Connected |  | N
National Grid | WARE | 176320 | 01082 | 997.6 | Solar | 05_01_201W1 | 05/11/2015 | 05/11/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2015 | 06/15/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/28/2016 | 10/28/2016 | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 361080 | 02301 | 9.8 | Solar | 05_09_501L1 | 06/01/2021 | 06/02/2021 | 0 | 0 | 0 | 06/03/2021 | 06/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2021 | 06/01/2021 | 12/17/2022 | Y | EXP | 365 | 09/11/2021 | 10/01/2021 | 21 | 0 | 21 |  |  | 8/8/2022 | Connected |  | N
National Grid | BROCKTON | 431649 | 02301 | 0 | Battery Add-On | 05_07_98W10 | 07/06/2022 | 08/10/2022 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 631090 | 01033 | 5.76 | Solar | 05_07_91W43 | 08/08/2024 | 09/10/2024 | 18 | 16 | 2 | 09/11/2024 | 09/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 |  | 11/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2025 | Connected |  | N
National Grid | PLAINVILLE | 630437 | 02762 | 10 | Solar | 05_09_527L1 | 08/06/2024 | 08/16/2024 | 1 | 0 | 1 | 08/19/2024 | 08/19/2024 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 08/06/2024 | 11/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2025 | Connected |  | N
National Grid | BEVERLY | 744511 | 01915 | 15.2 | Solar | 05_05_3422W4 | 01/20/2026 | 01/23/2026 | 3 | 0 | 3 | 01/26/2026 | 01/26/2026 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBRIDGE | 194242 | 01534 | 10 | Solar | 05_12_12L2 | 08/22/2018 | 08/23/2018 | 7 | 6 | 1 | 09/12/2018 | 09/12/2018 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2018 | 08/22/2018 | 5/10/2019 | Y | EXP | 233 | 11/30/2018 | 04/12/2019 | 133 | 0 | 133 |  |  | 4/19/2019 | Connected |  | N
National Grid | BRIDGEWATER | 198326 | 02333 | 10 | Solar | 05_05_320W1 | 11/02/2018 | 11/13/2018 | 1 | 1 | 0 | 11/14/2018 | 11/14/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 175280 | 02703 | 42.57 | Solar | 05_07_797W29 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/4/2015 | Connected |  | N
National Grid | SHIRLEY | 175606 | 01464 | 644 | Solar | 05_05_9L4 | 10/21/2014 | 10/21/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2014 | 11/25/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 176319 | 01082 | 904.8 | Solar | 05_01_201W1 | 05/11/2015 | 05/11/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2015 | 06/15/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/28/2016 | 10/28/2016 | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 361060 | 02301 | 11.52 | Solar | 05_09_501L1 | 07/21/2021 | 07/22/2021 | 1 | 0 | 1 | 07/23/2021 | 07/23/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 437699 | 02301 | 0 | Battery Add-On | 05_07_98W10 | 08/02/2022 | 08/12/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/15/2022 | 09/07/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 632654 | 01033 | 7.6 | Solar | 05_07_91W43 | 08/14/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2024 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2025 | Connected |  | N
National Grid | FOXBOROUGH | 640697 | 02035 | 15.36 | Solar | 05_09_527L1 | 09/17/2024 | 11/05/2024 | 34 | 30 | 4 | 11/06/2024 | 11/06/2024 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 178747 | 01915 | 0 | Solar | 05_05_3422W4 | 12/14/2011 | 12/14/2011 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2012 | 12/14/2011 | 6/8/2012 | Y | STD | 12 | 01/16/2013 | 02/24/2013 | 22 | 0 | 22 | 2/22/2013 | 2/22/2013 | 3/5/2013 | Connected |  | N
National Grid | NORTHBRIDGE | 200315 | 01534 | 3.8 | Solar | 05_12_12L2 | 11/05/2018 | 01/28/2019 | 57 | 55 | 2 | 01/29/2019 | 01/29/2019 | 159 | 0 | 159 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 294823 | 02333 | 10 | Solar | 05_05_320W1 | 06/16/2020 | 06/29/2020 | 8 | 4 | 4 | 06/30/2020 | 06/30/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 177803 | 02703 | 499.5 | Solar | 05_07_797W29 | 10/11/2017 | 10/11/2017 | 103 | 96 | 7 | 03/23/2018 | 03/23/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2018 | 10/11/2017 | 2/12/2021 | Y | EXP | 573 | 07/19/2019 | 08/04/2020 | 382 | 0 | 382 |  |  | 2/9/2021 | Connected |  | N
National Grid | SHIRLEY | 175718 | 01464 | 475 | Solar | 05_05_9L4 | 12/30/2014 | 12/30/2014 | 6 | 1 | 5 | 01/08/2015 | 01/08/2015 | 140 | 0 | 140 | 03/03/2015 | 08/03/2015 | 104 | 0 | 104 |  |  | 0 | 0 | 0 |  | 08/03/2015 | 104 | 0 | 104 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 177928 | 01082 | 750 | Solar | 05_01_201W1 | 04/18/2017 | 04/18/2017 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2017 | 08/01/2017 | 63 | 47 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2018 | 04/18/2017 | 6/10/2020 | Y | STD | 79 | 12/06/2019 | 01/16/2020 | 41 | 0 | 41 |  |  | 6/16/2020 | Connected |  | N
National Grid | BROCKTON | 435977 | 02301 | 6 | Solar | 05_09_501L1 | 06/13/2022 | 06/14/2022 | 1 | 0 | 1 | 06/15/2022 | 06/15/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2022 | Connected |  | N
National Grid | BROCKTON | 597159 | 02301 | 6 | Solar | 05_07_98W10 | 04/05/2024 | 04/23/2024 | 11 | 8 | 3 | 04/24/2024 | 04/24/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 640968 | 01007 | 5 | Solar | 05_07_91W43 | 09/19/2024 | 10/17/2024 | 13 | 11 | 2 | 10/18/2024 | 10/18/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | FOXBOROUGH | 655098 | 02035 | 5.76 | Solar | 05_09_527L1 | 11/19/2024 | 01/08/2025 | 12 | 7 | 5 | 01/09/2025 | 01/09/2025 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 11/19/2024 | 5/9/2026 | Y | EXP | 365 | 07/10/2025 | 07/23/2025 | 14 | 0 | 14 |  |  | 7/31/2025 | Connected |  | N
National Grid | BEVERLY | 178761 | 01915 | 625 | Natural Gas | 05_05_3422W4 | 01/05/2012 | 01/05/2012 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2012 |  | 2/18/2012 | N | STD | 213 |  |  | 0 | 0 | 0 | 12/18/2012 | 12/18/2012 | 12/19/2012 | Connected |  | N
National Grid | UPTON | 201091 | 01568 | 3.8 | Solar | 05_12_12L2 | 11/14/2018 | 12/10/2018 | 7 | 2 | 5 | 12/11/2018 | 12/11/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 335875 | 02333 | 9.6 | Solar | 05_05_320W1 | 01/08/2021 | 01/20/2021 | 6 | 5 | 1 | 01/21/2021 | 01/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2021 |  | 1/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2021 | Connected |  | N
National Grid | ATTLEBORO | 177856 | 02703 | 3.8 | Solar | 05_07_797W29 | 04/11/2017 | 04/11/2017 | 3 | 2 | 1 | 04/14/2017 | 04/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2017 | 04/11/2017 | 4/16/2018 | Y | EXP | 362 | 06/28/2017 | 07/17/2017 | 12 | 0 | 12 | 10/16/2017 | 10/16/2017 | 10/16/2017 | Connected |  | N
National Grid | SHIRLEY | 176321 | 01464 | 140 | Solar | 05_05_9L4 | 05/13/2015 | 05/13/2015 | 2 | 2 | 0 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 | 05/13/2015 | 12/31/2016 | Y | EXP | 478 | 03/28/2016 | 05/16/2016 | 34 | 0 | 34 | 7/11/2016 | 7/11/2016 | 7/14/2016 | Connected |  | N
National Grid | WARE | 208607 | 01082 | 500 | Solar | 05_01_201W1 | 03/22/2019 | 04/23/2019 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/24/2019 | 05/23/2019 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 505468 | 02301 | 17.6 | Solar | 05_09_501L1 | 03/01/2023 | 03/15/2023 | 11 | 10 | 1 | 03/16/2023 | 03/16/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 |  | 4/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2023 | Connected |  | N
National Grid | BROCKTON | 646596 | 02302 | 10 | Solar | 05_07_98W10 | 10/25/2024 | 11/07/2024 | 1 | 0 | 1 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/25/2024 | 12/28/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | GRANBY | 647475 | 01033 | 7.6 | Solar | 05_07_91W43 | 10/29/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | GRANBY | 660307 | 01033 | 17.16 | Solar | 05_09_527L1 | 12/12/2024 | 12/18/2024 | 4 | 1 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | BEVERLY | 178755 | 01915 | 500 | Solar | 05_05_3422W4 | 12/14/2011 | 12/14/2011 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/22/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 201284 | 01568 | 180 | Solar | 05_12_12L2 | 11/27/2018 | 11/27/2018 | 0 | 0 | 0 | 11/28/2018 | 11/28/2018 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2019 | Connected |  | N
National Grid | WHITMAN | 390487 | 02382 | 9.765 | Solar | 05_05_320W1 | 11/12/2021 | 01/05/2022 | 2 | 0 | 2 | 11/16/2021 | 11/16/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/12/2021 | 4/3/2023 | Y | EXP | 365 | 02/08/2022 | 03/31/2022 | 52 | 0 | 52 |  |  | 5/11/2022 | Connected |  | N
National Grid | ATTLEBORO | 177855 | 02703 | 3.8 | Solar | 05_07_797W29 | 04/11/2017 | 04/11/2017 | 3 | 3 | 0 | 04/14/2017 | 04/14/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2017 | 04/11/2017 | 7/30/2020 | Y | EXP | 942 | 06/28/2017 | 07/17/2017 | 12 | 0 | 12 |  |  | 6/1/2020 | Connected |  | N
National Grid | SHIRLEY | 177560 | 01464 | 594 | Solar | 05_05_9L4 | 07/13/2017 | 07/13/2017 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2017 | 09/06/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 326607 | 01082 | 8 | Solar | 05_01_201W1 | 11/17/2020 | 11/20/2020 | 2 | 0 | 2 | 11/23/2020 | 11/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/17/2020 | 5/3/2022 | Y | EXP | 365 | 03/12/2021 | 04/12/2021 | 31 | 0 | 31 |  |  | 9/14/2021 | Connected |  | N
National Grid | BROCKTON | 516139 | 02301 | 20 | Solar | 05_09_501L1 | 03/31/2023 | 04/03/2023 | 1 | 0 | 1 | 04/04/2023 | 04/04/2023 | 132 | 113 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 659860 | 02301 | 7.6 | Solar | 05_07_98W10 | 12/11/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/11/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | GRANBY | 650602 | 01033 | 5.2 | Solar | 05_07_91W43 | 11/04/2024 | 11/19/2024 | 5 | 1 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/04/2024 | 1/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2025 | Connected |  | N
National Grid | GRANBY | 667309 | 01033 | 7.6 | Solar | 05_09_527L1 | 01/22/2025 | 01/28/2025 | 4 | 0 | 4 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 208008 | 01915 | 7.6 | Solar | 05_05_3422W4 | 02/04/2019 | 02/07/2019 | 3 | 3 | 0 | 02/08/2019 | 02/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  | 2/19/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | Connected |  | N
National Grid | NORTHBRIDGE | 203722 | 01534 | 10 | Solar | 05_12_12L2 | 01/01/2019 | 01/10/2019 | 6 | 0 | 6 | 01/11/2019 | 01/11/2019 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 | 01/01/2019 | 2/18/2020 | Y | EXP | 365 | 05/15/2019 | 05/14/2019 | 0 | 0 | 0 |  |  | 6/6/2019 | Connected |  | N
National Grid | BRIDGEWATER | 415301 | 02333 | 30 | Solar | 05_05_320W1 | 03/03/2022 | 03/04/2022 | 1 | 0 | 1 | 03/07/2022 | 03/07/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2022 | Connected |  | N
National Grid | ATTLEBORO | 178510 | 02703 | 6 | Solar | 05_07_797W29 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 | 03/15/2018 | 03/15/2018 | 270 | 0 | 270 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 | 03/08/2018 | 3/13/2019 | Y | EXP | 36 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N
National Grid | AYER | 184801 | 01432 | 990 | Solar | 05_05_9L4 | 07/09/2018 | 06/12/2018 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/25/2018 | 10/22/2018 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2019 |  | 1/2/2021 | N | STD | 589 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 456437 | 01082 | 4.64 | Solar | 05_01_201W1 | 10/27/2022 | 10/31/2022 | 2 | 0 | 2 | 11/22/2022 | 11/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 635553 | 02301 | 5.76 | Solar | 05_09_501L1 | 08/26/2024 | 09/18/2024 | 1 | 0 | 1 | 09/19/2024 | 09/19/2024 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 08/26/2024 | 12/5/2025 | Y | EXP | 365 | 03/05/2025 | 04/30/2025 | 57 | 0 | 57 |  |  | 5/7/2025 | Connected |  | N
National Grid | BROCKTON | 674682 | 02301 | 5.76 | Solar | 05_07_98W10 | 02/27/2025 | 05/22/2025 | 2 | 0 | 2 | 06/06/2025 | 06/06/2025 | 85 | 75 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 650743 | 01033 | 6 | Solar | 05_07_91W43 | 10/30/2024 | 11/18/2024 | 4 | 0 | 4 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 692427 | 01033 | 17.6 | Solar | 05_09_527L1 | 05/27/2025 | 05/28/2025 | 1 | 0 | 1 | 05/29/2025 | 05/29/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 279731 | 01915 | 0 | Solar | 05_05_3422W4 | 02/18/2020 | 02/26/2020 | 6 | 6 | 0 | 02/27/2020 | 02/27/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2020 |  | 3/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 223495 | 01534 | 11.4 | Solar | 05_12_12L2 | 04/29/2019 | 09/20/2019 | 102 | 101 | 1 | 09/23/2019 | 09/23/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2019 |  | 11/29/2019 | N | EXP | 63 |  |  | 0 | 0 | 0 |  |  | 10/31/2019 | Connected |  | N
National Grid | BRIDGEWATER | 526206 | 02333 | 15.2 | Solar | 05_05_320W1 | 08/27/2023 | 08/28/2023 | 1 | 0 | 1 | 08/29/2023 | 08/29/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 194877 | 02703 | 3.8 | Solar | 05_07_797W29 | 08/31/2018 | 10/01/2018 | 4 | 4 | 0 | 10/02/2018 | 10/02/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2018 |  | 10/18/2019 | N | EXP | 38 |  |  | 0 | 0 | 0 |  |  | 9/9/2019 | Connected |  | N
National Grid | AYER | 200411 | 01432 | 492 | Solar | 05_05_9L4 | 11/19/2018 | 12/19/2018 | 11 | 5 | 6 |  |  | 32 | 17 | 15 | 04/02/2019 | 05/02/2019 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 05/02/2019 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 12/19/2019 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 647481 | 01082 | 7.6 | Solar | 05_09_501L1 | 10/24/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/24/2024 | 1/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 684073 | 02301 | 5.76 | Solar | 05_07_98W10 | 04/09/2025 | 08/12/2025 | 4 | 0 | 4 | 08/13/2025 | 08/13/2025 | 24 | 6 | 18 | 10/06/2025 | 10/27/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 10/27/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 654702 | 02301 | 5.76 | Solar | 05_07_91W43 | 11/19/2024 | 12/17/2024 | 7 | 0 | 7 | 12/18/2024 | 12/18/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | GRANBY | 718085 | 01033 | 16 | Solar | 05_09_527L1 | 10/21/2025 | 10/24/2025 | 3 | 0 | 3 | 10/27/2025 | 10/27/2025 | 39 | 19 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 1/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2026 | Connected |  | N
National Grid | WRENTHAM | 374918 | 02093 | 468 | Solar | 05_05_3422W4 | 10/19/2021 | 11/24/2021 | 25 | 15 | 10 | 11/25/2021 | 11/25/2021 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2023 | Connected |  | N
National Grid | BEVERLY | 573240 | 01915 | 50 | Solar | 05_05_320W1 | 12/18/2023 |  | 47 | 38 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 194734 | 01568 | 10 | Solar | 05_07_797W29 | 11/19/2018 | 10/23/2018 | 0 | 0 | 0 | 11/20/2018 | 11/20/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 | 11/19/2018 | 3/27/2020 | Y | EXP | 472 | 11/15/2019 | 12/12/2019 | 27 | 0 | 27 |  |  | 12/12/2019 | Connected |  | N
National Grid | BRIDGEWATER | 325226 | 02333 | 10 | Solar | 05_05_9L4 | 12/11/2020 | 12/18/2020 | 4 | 0 | 4 | 12/21/2020 | 12/21/2020 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/11/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2021 | Connected |  | N
National Grid | ATTLEBORO | 489990 | 02703 | 11.31 | Solar | 05_01_201W1 | 01/06/2023 | 01/06/2023 | 0 | 0 | 0 | 01/09/2023 | 01/09/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 701029 | 01432 | 5.8 | Solar | 05_09_501L1 | 06/25/2025 | 07/09/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 | 06/25/2025 | 8/8/2026 | Y | EXP | 365 | 10/02/2025 | 10/22/2025 | 21 | 0 | 21 |  |  | 12/2/2025 | Connected |  | N
National Grid | WARE | 719822 | 01082 | 15.2 | Solar | 05_07_98W10 | 09/23/2025 | 09/29/2025 | 3 | 1 | 2 | 09/30/2025 | 09/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 657585 | 02301 | 5.76 | Solar | 05_07_91W43 | 11/29/2024 | 12/13/2024 | 3 | 0 | 3 | 12/16/2024 | 12/16/2024 | 31 | 9 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 392878 | 02301 | 999 | Solar | 05_09_527L2 | 04/12/2022 | 06/02/2022 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/03/2022 | 07/07/2022 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GRANBY | 385688 | 01033 | 15.2 | Solar | 05_05_3422W4 | 09/30/2021 | 10/01/2021 | 1 | 0 | 1 | 10/04/2021 | 10/04/2021 | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  | 11/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2022 | Connected |  | N
National Grid | BEVERLY | 262763 | 01915 | 10 | Solar | 05_12_12L2 | 10/29/2019 | 11/05/2019 | 4 | 0 | 4 | 11/06/2019 | 11/06/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 | 10/29/2019 | 10/21/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | BEVERLY | 586651 | 01915 | 10 | Solar | 05_05_320W1 | 02/16/2024 | 03/18/2024 | 21 | 17 | 4 | 03/19/2024 | 03/19/2024 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITINSVILLE | 193184 | 01588 | 780 | Solar | 05_07_797W29 | 09/11/2018 | 09/25/2018 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2018 | 11/06/2018 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2019 | 09/11/2018 | 11/10/2021 | Y | STD | 484 | 06/11/2021 | 09/27/2021 | 90 | 3 | 87 | 10/1/2021 | 9/30/2021 | 10/7/2021 | Connected |  | N
National Grid | WHITMAN | 331536 | 02382 | 7.6 | Solar | 05_05_9L4 | 01/07/2021 | 01/12/2021 | 2 | 0 | 2 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 562170 | 02703 | 0 | Battery Add-On | 05_01_201W1 | 10/11/2023 | 10/12/2023 | 1 | 0 | 1 | 10/13/2023 | 10/13/2023 | 93 | 75 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 5/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2024 | Connected |  | N
National Grid | AYER | 368904 | 01432 | 0 | Other | 05_09_501L2 | 01/24/2022 | 05/02/2022 | 68 | 59 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2022 | 07/11/2022 | 47 | 28 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 441919 | 01082 | 999 | Solar | 05_07_98W19 | 09/07/2022 | 10/11/2022 | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2022 | 11/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/07/2022 | 1/4/2027 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 662984 | 02301 | 10 | Solar | 05_07_91W43 | 12/30/2024 | 01/27/2025 | 5 | 0 | 5 | 01/28/2025 | 01/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | BROCKTON | 738903 | 02301 | 5.76 | Solar | 05_09_527L2 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 29 | 16 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2026 |  | 3/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GRANBY | 393455 | 01033 | 10 | Solar | 05_05_3422W4 | 02/12/2023 | 01/14/2022 | 2 | 1 | 1 | 02/14/2023 | 02/14/2023 | 26 | 3 | 23 | 04/06/2023 | 05/08/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 05/08/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 1/14/2022 |  | 8/2/2024 | N | EXP | 365 | 07/13/2023 | 07/26/2023 | 14 | 0 | 14 |  |  | 8/30/2023 | Connected |  | N
National Grid | BEVERLY | 281100 | 01915 | 7.6 | Solar | 05_12_12L2 | 03/04/2020 | 03/12/2020 | 6 | 6 | 0 | 03/13/2020 | 03/13/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2020 | 03/04/2020 | 3/12/2021 | Y | EXP | 365 | 09/18/2020 | 09/28/2020 | 10 | 0 | 10 |  |  | 11/4/2020 | Connected |  | N
National Grid | BEVERLY | 610138 | 01915 | 15.2 | Solar | 05_05_320W1 | 05/14/2024 | 05/16/2024 | 2 | 0 | 2 | 05/17/2024 | 05/17/2024 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 05/14/2024 | 7/19/2025 | Y | EXP | 365 | 08/07/2024 | 08/26/2024 | 20 | 0 | 20 |  |  | 9/24/2024 | Connected |  | N
National Grid | UPTON | 211156 | 01568 | 210 | Natural Gas | 05_07_797W29 | 09/13/2019 | 11/05/2019 | 36 | 27 | 9 | 11/06/2019 | 11/06/2019 | 13 | 4 | 9 | 12/30/2019 | 04/01/2020 | 65 | 46 | 19 |  |  | 0 | 0 | 0 |  | 04/01/2020 | 65 | 46 | 19 |  |  | 0 | 0 | 0 | 4/1/2020 |  | 9/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2020 | Connected |  | N
National Grid | BRIDGEWATER | 357402 | 02333 | 300 | Solar | 05_05_9L4 | 07/14/2021 | 08/11/2021 | 20 | 10 | 10 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 | 07/14/2021 | 1/6/2024 | Y | STD | 36 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 628975 | 02703 | 9.28 | Solar | 05_01_201W1 | 10/15/2024 | 11/05/2024 | 8 | 4 | 4 | 11/06/2024 | 11/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/15/2024 | 12/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | AYER | 588156 | 01432 | 4980 | Solar | 05_09_501L2 | 04/12/2024 | 12/30/2024 | 176 | 166 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 12/29/2025 | 248 | 229 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 544370 | 01082 | 4999 | Solar | 05_07_98W19 | 08/29/2023 | 01/09/2024 | 89 | 83 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2024 | 02/06/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/29/2023 | 1/4/2027 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 672475 | 02301 | 3.8 | Solar | 05_07_91W43 | 02/17/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 741953 | 02301 | 19 | Solar | 05_09_527L2 | 12/23/2025 |  | 49 | 46 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | GRANBY | 397405 | 01033 | 5.76 | Solar | 05_05_3422W4 | 11/23/2021 | 12/15/2021 | 5 | 4 | 1 | 12/16/2021 | 12/16/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2022 |  | 7/23/2023 | N | EXP | 55 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 295936 | 01915 | 3.8 | Solar | 05_12_12L2 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/19/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 615196 | 01915 | 7.6 | Solar | 05_05_320W1 | 06/05/2024 | 06/20/2024 | 3 | 0 | 3 | 06/21/2024 | 06/21/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/05/2024 | 7/30/2025 | Y | EXP | 365 | 08/21/2024 | 09/12/2024 | 23 | 0 | 23 |  |  | 10/7/2024 | Connected |  | N
National Grid | NORTHBRIDGE | 260147 | 01534 | 0 | Solar | 05_07_797W29 | 10/15/2019 | 10/16/2019 | 0 | 0 | 0 | 10/17/2019 | 10/17/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2019 |  | 10/14/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2020 | Connected |  | N
National Grid | BRIDGEWATER | 357809 | 02333 | 499.5 | Solar | 05_05_9L4 | 07/30/2021 | 11/11/2021 | 71 | 60 | 11 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 655615 | 02703 | 7.83 | Solar | 05_01_201W1 | 11/20/2024 | 12/04/2024 | 4 | 2 | 2 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/20/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2025 | Connected |  | N
National Grid | SHIRLEY | 602603 | 01464 | 11.4 | Solar | 05_09_501L2 | 04/08/2024 | 06/21/2024 | 38 | 36 | 2 | 07/24/2025 | 07/24/2025 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 04/08/2024 | 11/7/2026 | Y | EXP | 365 | 01/08/2026 | 01/15/2026 | 8 | 0 | 8 |  |  |  | Completion Documents |  | N
National Grid | WARE | 176978 | 01082 | 112 | Solar | 05_07_98W19 | 12/27/2016 | 12/27/2016 | 2 | 1 | 1 | 12/30/2016 | 12/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2017 |  | 1/2/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 5/5/2017 | 5/5/2017 | 5/5/2017 | Connected |  | N
National Grid | BROCKTON | 673026 | 02301 | 7.6 | Solar | 05_07_91W43 | 02/24/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 02/24/2025 | 4/24/2026 | Y | EXP | 365 | 07/15/2025 | 10/22/2025 | 100 | 0 | 100 |  |  | 12/16/2025 | Connected |  | N
National Grid | BROCKTON | 174593 | 02302 | 14 | Solar | 05_09_527L2 | 10/28/2011 | 10/28/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2011 |  | 1/6/2012 | N | EXP | 24 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 1/6/2012 | Connected |  | N
National Grid | GRANBY | 446350 | 01033 | 6.96 | Solar | 05_05_3422W4 | 08/01/2022 | 08/04/2022 | 3 | 0 | 3 | 08/05/2022 | 08/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 | 08/01/2022 | 2/3/2024 | Y | EXP | 365 | 10/27/2022 | 02/01/2023 | 98 | 0 | 98 |  |  | 2/14/2023 | Connected |  | N
National Grid | BEVERLY | 324809 | 01915 | 8.64 | Solar | 05_12_12L2 | 12/21/2020 | 01/06/2021 | 10 | 10 | 0 | 01/07/2021 | 01/07/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/21/2020 | 1/5/2022 | Y | EXP | 365 | 07/09/2021 | 07/15/2021 | 7 | 0 | 7 |  |  | 8/5/2021 | Connected |  | N
National Grid | BEVERLY | 618849 | 01915 | 34.6 | Solar | 05_05_320W1 | 08/12/2024 | 08/15/2024 | 4 | 3 | 1 | 08/16/2024 | 08/16/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 |  | 10/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2025 | Connected |  | N
National Grid | UPTON | 306629 | 01568 | 3.8 | Solar | 05_07_797W29 | 09/14/2020 | 10/02/2020 | 14 | 14 | 0 | 10/05/2020 | 10/05/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2020 | 09/14/2020 | 11/5/2021 | Y | EXP | 365 | 02/18/2021 | 04/07/2021 | 48 | 0 | 48 |  |  | 4/13/2021 | Connected |  | N
National Grid | EAST BRIDGEWATER | 357632 | 02333 | 283.2 | Solar | 05_05_9L4 | 07/14/2021 | 10/01/2021 | 56 | 46 | 10 |  |  | 32 | 4 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 665952 | 02703 | 0 | Other | 05_01_201W2 | 02/25/2025 | 03/28/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/31/2025 | 04/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | AYER | 676477 | 01432 | 249 | Solar | 05_09_501L2 | 03/27/2025 | 09/08/2025 | 67 | 57 | 10 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HARDWICK | 176969 | 01031 | 540 | Solar | 05_07_98W19 | 10/04/2016 | 10/04/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2016 | 11/07/2016 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2017 | 10/04/2016 | 6/26/2018 | Y | STD | 446 | 12/01/2017 | 06/12/2018 | 193 | 0 | 193 | 4/5/2018 | 4/5/2018 | 6/22/2018 | Connected |  | N
National Grid | BROCKTON | 696136 | 02301 | 11.52 | Solar | 05_07_91W43 | 06/05/2025 | 06/10/2025 | 3 | 0 | 3 | 06/11/2025 | 06/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 177695 | 02301 | 11.4 | Solar | 05_09_527L2 | 03/21/2017 | 03/21/2017 | 7 | 7 | 0 | 03/30/2017 | 03/30/2017 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2017 |  | 3/26/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 453555 | 01033 | 0 | Battery Add-On | 05_05_3422W4 | 10/17/2022 | 10/27/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2022 | 11/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 330235 | 01915 | 7.6 | Solar | 05_12_12L2 | 12/07/2020 | 02/05/2021 | 40 | 38 | 2 | 02/08/2021 | 02/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 619888 | 01915 | 7.6 | Solar | 05_05_320W1 | 06/24/2024 | 07/01/2024 | 3 | 0 | 3 | 07/02/2024 | 07/02/2024 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 06/24/2024 | 12/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | N
National Grid | UPTON | 328155 | 01568 | 10 | Solar | 05_07_797W29 | 01/08/2021 | 01/12/2021 | 1 | 0 | 1 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/08/2021 |  | Y | EXP | 365 | 07/20/2021 | 08/17/2021 | 25 | 0 | 25 |  |  | 9/2/2021 | Connected |  | N
National Grid | WHITMAN | 357619 | 02382 | 466.6 | Solar | 05_05_9L4 | 07/14/2021 | 08/11/2021 | 20 | 10 | 10 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 749370 | 02703 | 11.4 | Solar | 05_01_201W2 | 02/04/2026 | 02/11/2026 | 4 | 2 | 2 | 02/12/2026 | 02/12/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AYER | 676470 | 01432 | 249 | Solar | 05_09_501L2 | 03/26/2025 | 09/05/2025 | 60 | 50 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 447289 | 01082 | 6 | Solar | 05_07_98W19 | 01/29/2024 | 08/16/2022 | 8 | 4 | 4 | 02/09/2024 | 02/09/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 702055 | 02379 | 5.76 | Solar | 05_07_91W43 | 07/08/2025 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 177693 | 02301 | 7.6 | Solar | 05_09_527L2 | 03/21/2017 | 03/21/2017 | 5 | 5 | 0 | 03/28/2017 | 03/28/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 |  | 3/28/2019 | N | EXP | 729 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 566683 | 01033 | 46 | Solar | 05_05_3422W4 | 10/27/2023 | 11/13/2023 | 10 | 8 | 2 | 11/14/2023 | 11/14/2023 | 95 | 79 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 4/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2024 | Connected |  | N
National Grid | BEVERLY | 358932 | 01915 | 10 | Solar | 05_12_12L2 | 05/18/2021 | 05/24/2021 | 3 | 3 | 0 | 05/25/2021 | 05/25/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2021 |  | 7/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2021 | Connected |  | N
National Grid | BEVERLY | 622626 | 01915 | 10 | Solar | 05_05_320W1 | 07/11/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/11/2024 | 11/30/2025 | Y | EXP | 365 | 10/03/2024 | 10/02/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBRIDGE | 345490 | 01534 | 500 | Solar | 05_07_797W29 | 04/07/2021 | 04/23/2021 | 11 | 0 | 11 |  |  | 107 | 82 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 370328 | 02339 | 480 | Solar | 05_05_9L4 | 11/16/2021 | 12/14/2021 | 19 | 11 | 8 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 | 11/16/2021 | 12/16/2025 | Y | STD | 36 | 09/08/2023 | 12/09/2025 | 822 | 582 | 240 |  |  | 12/24/2025 | Connected |  | N
National Grid | ATTLEBORO | 174148 | 02703 | 30 | Solar | 05_01_201W2 | 04/18/2012 | 04/18/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 04/18/2012 | 8/1/2012 | Y | EXP | 133 | 01/10/2013 | 02/27/2013 | 28 | 0 | 28 | 2/20/2013 | 2/20/2013 | 3/11/2013 | Connected |  | N
National Grid | AYER | 690066 | 01432 | 996 | Solar | 05_09_501L2 | 06/03/2025 | 07/14/2025 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2025 | 08/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HARDWICK | 571236 | 01031 | 9.984 | Solar | 05_07_98W19 | 11/14/2023 | 11/20/2023 | 4 | 3 | 1 | 11/21/2023 | 11/21/2023 | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 11/14/2023 | 3/7/2025 | Y | EXP | 365 | 04/23/2024 | 05/14/2024 | 22 | 0 | 22 |  |  | 5/23/2024 | Connected |  | N
National Grid | BROCKTON | 672350 | 02301 | 7.54 | Solar | 05_07_91W46 | 02/17/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 88 | 67 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 | 02/17/2025 | 7/25/2026 | Y | EXP | 365 | 10/02/2025 | 11/18/2025 | 48 | 0 | 48 |  |  |  | Completion Documents |  | Y
National Grid | BROCKTON | 177784 | 02301 | 3.8 | Solar | 05_09_527L2 | 06/01/2017 | 06/01/2017 | 6 | 6 | 0 | 06/12/2017 | 06/12/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 |  | 6/7/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 686036 | 01033 | 7.6 | Solar | 05_05_3422W4 | 04/18/2025 | 05/06/2025 | 4 | 0 | 4 | 06/10/2025 | 06/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2025 | 04/18/2025 | 7/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2026 | Connected |  | N
National Grid | BEVERLY | 361035 | 01915 | 3.8 | Solar | 05_12_12L2 | 06/11/2021 | 06/16/2021 | 3 | 0 | 3 | 06/17/2021 | 06/17/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 645388 | 01915 | 5.76 | Solar | 05_05_320W1 | 10/07/2024 | 11/04/2024 | 4 | 0 | 4 | 11/05/2024 | 11/05/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/07/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 394890 | 01534 | 996 | Solar | 05_07_797W29 | 01/29/2022 | 03/01/2022 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2022 | 03/02/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITMAN | 374717 | 02382 | 11.4 | Solar | 05_05_9L4 | 08/09/2021 |  | 33 | 26 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 174259 | 02703 | 217 | Solar | 05_01_201W2 | 02/28/2012 | 02/28/2012 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 690063 | 01432 | 996 | Solar | 05_09_501L2 | 06/03/2025 | 07/14/2025 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2025 | 08/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 637880 | 01082 | 5.76 | Solar | 05_07_98W19 | 09/05/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 | 09/05/2024 | 1/10/2026 | Y | EXP | 365 | 12/03/2024 | 02/15/2025 | 74 | 0 | 74 |  |  | 9/11/2025 | Connected |  | N
National Grid | BROCKTON | 711480 | 02301 | 20 | Solar | 05_07_91W46 | 08/19/2025 | 08/28/2025 | 6 | 2 | 4 | 08/29/2025 | 08/29/2025 | 41 | 22 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 178133 | 02302 | 9980 | Solar | 05_09_527L2 | 07/12/2017 | 08/28/2017 | 32 | 32 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2017 | 09/19/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2018 |  | 12/21/2022 | N | STD | 128 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 659602 | 01007 | 480 | Solar | 05_05_3424W1 | 05/20/2025 | 07/29/2025 | 47 | 37 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2025 | 09/25/2025 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FOXBOROUGH | 378053 | 02035 | 15.2 | Solar | 05_12_12L2 | 08/25/2021 | 08/26/2021 | 1 | 0 | 1 | 08/27/2021 | 08/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2021 |  | 12/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2022 | Connected |  | N
National Grid | BEVERLY | 660931 | 01915 | 7.6 | Solar | 05_05_320W1 | 12/16/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 57 | 35 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 12/16/2024 | 4/14/2026 | Y | EXP | 365 | 06/24/2025 | 07/16/2025 | 23 | 0 | 23 |  |  | 8/19/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 460265 | 01534 | 15.2 | Solar | 05_07_797W29 | 09/20/2022 |  | 78 | 57 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 374279 | 02333 | 7.6 | Solar | 05_05_9L4 | 08/05/2021 | 08/17/2021 | 9 | 8 | 1 | 08/18/2021 | 08/18/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 8/17/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 174643 | 02703 | 90 | Solar | 05_01_201W2 | 12/11/2013 | 12/11/2013 | 4 | 0 | 4 | 12/18/2013 | 12/18/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2014 |  | 1/31/2014 | N | EXP | 24 |  |  | 0 | 0 | 0 | 1/8/2014 | 1/8/2014 | 4/7/2014 | Connected |  | N
National Grid | HARVARD | 690058 | 01451 | 996 | Solar | 05_09_501L2 | 06/03/2025 | 07/14/2025 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2025 | 08/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 641187 | 01082 | 10 | Solar | 05_07_98W19 | 09/27/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175465 | 02301 | 490 | Solar | 05_07_91W46 | 09/24/2014 | 09/24/2014 | 7 | 0 | 7 | 10/06/2014 | 10/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2014 |  | 1/30/2015 | N | EXP | 93 |  |  | 0 | 0 | 0 | 2/17/2016 | 2/17/2016 | 2/17/2016 | Connected |  | N
National Grid | BROCKTON | 201376 | 02301 | 10 | Solar | 05_09_527L2 | 11/16/2018 | 12/28/2018 | 25 | 24 | 1 | 12/31/2018 | 12/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 1/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2019 | Connected |  | N
National Grid | GRANBY | 733950 | 01033 | 249 | Solar | 05_05_3424W1 | 01/13/2026 | 01/26/2026 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BEVERLY | 378580 | 01915 | 9.8 | Solar | 05_12_12L2 | 08/30/2021 | 09/10/2021 | 9 | 8 | 1 | 09/13/2021 | 09/13/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2021 |  | 11/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2022 | Connected |  | N
National Grid | BEVERLY | 661979 | 01915 | 3.8 | Solar | 05_05_320W1 | 12/20/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | UPTON | 494260 | 01568 | 10 | Solar | 05_07_797W29 | 03/28/2023 | 03/30/2023 | 2 | 0 | 2 | 03/31/2023 | 03/31/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 |  | 5/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2023 | Connected |  | N
National Grid | EAST BRIDGEWATER | 384112 | 02333 | 10 | Solar | 05_05_9L4 | 10/14/2021 | 12/23/2021 | 4 | 2 | 2 | 10/21/2021 | 10/21/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 |  | 1/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2022 | Connected |  | N
National Grid | ATTLEBORO | 174833 | 02703 | 210 | Solar | 05_01_201W2 | 08/30/2012 | 08/30/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/12/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 697860 | 01451 | 5000 | Solar | 05_09_501L2 | 09/17/2025 | 12/08/2025 | 54 | 44 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/09/2025 | 01/02/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HARDWICK | 174410 | 01031 | 1750 | Solar | 05_07_98W44 | 06/19/2012 | 06/19/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2012 | 10/04/2012 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2013 | 06/19/2012 | 11/1/2012 | Y | STD | 112 | 01/11/2013 | 04/16/2013 | 56 | 0 | 56 | 11/20/2013 | 11/20/2013 | 12/6/2013 | Connected |  | N
National Grid | BROCKTON | 184909 | 02301 | 125 | Natural Gas | 05_07_91W46 | 06/21/2018 | 06/21/2018 | 15 | 12 | 3 | 07/20/2018 | 07/20/2018 | 39 | 17 | 22 | 10/12/2018 | 11/21/2018 | 28 | 21 | 7 |  |  | 0 | 0 | 0 |  | 11/21/2018 | 28 | 21 | 7 |  |  | 0 | 0 | 0 | 12/6/2018 |  | 6/7/2019 | N | EXP | 183 |  |  | 0 | 0 | 0 |  |  | 7/17/2019 | Connected |  | N
National Grid | BROCKTON | 369533 | 02302 | 7.68 | Solar | 05_09_527L2 | 07/27/2021 | 08/03/2021 | 5 | 0 | 5 | 08/04/2021 | 08/04/2021 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 178751 | 01007 | 125 | Solar | 05_05_3424W1 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 | 03/30/2012 | 03/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 | 02/15/2012 | 7/1/2012 | Y | EXP | 2 |  |  | 0 | 0 | 0 | 12/13/2012 | 12/13/2012 | 12/19/2012 | Connected |  | N
National Grid | BEVERLY | 378451 | 01915 | 11.4 | Solar | 05_12_12L2 | 08/27/2021 | 08/31/2021 | 2 | 0 | 2 | 09/01/2021 | 09/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2021 |  | 3/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2022 | Connected |  | N
National Grid | BEVERLY | 668717 | 01915 | 1.9 | Solar | 05_05_320W1 | 01/29/2025 | 02/03/2025 | 3 | 0 | 3 | 02/04/2025 | 02/04/2025 | 49 | 28 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | WHITINSVILLE | 517489 | 01588 | 5.22 | Solar | 05_07_797W29 | 11/01/2023 | 04/17/2023 | 20 | 19 | 1 | 12/01/2023 | 12/01/2023 | 74 | 51 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | EAST BRIDGEWATER | 421701 | 02333 | 15.2 | Solar | 05_05_9L4 | 06/15/2022 | 06/24/2022 | 6 | 4 | 2 | 06/27/2022 | 06/27/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  | 10/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2023 | Connected |  | N
National Grid | ATTLEBORO | 174832 | 02703 | 260 | Solar | 05_01_201W2 | 08/30/2012 | 08/30/2012 | 6 | 0 | 6 | 09/11/2012 | 09/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2013 | 08/30/2012 | 6/27/2014 | Y | EXP | 333 | 05/28/2014 | 07/21/2014 | 36 | 0 | 36 | 6/13/2014 | 6/13/2014 | 6/26/2014 | Connected |  | N
National Grid | HARVARD | 697477 | 01451 | 996 | Solar | 05_09_501L2 | 07/07/2025 | 07/30/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2025 | 08/22/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HARDWICK | 175515 | 01031 | 250 | Solar | 05_07_98W44 | 03/28/2014 | 03/28/2014 | 6 | 0 | 6 | 04/08/2014 | 04/08/2014 | 548 | 3 | 545 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2014 |  | 12/31/2016 | N | EXP | 982 |  |  | 0 | 0 | 0 | 6/29/2015 | 6/29/2015 |  | Withdrawn |  | Y
National Grid | BROCKTON | 199415 | 02301 | 430 | Solar | 05_07_91W46 | 10/25/2018 | 11/13/2018 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 | 12/27/2018 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 421045 | 02302 | 10 | Solar | 05_09_527L2 | 03/31/2022 | 04/07/2022 | 6 | 5 | 1 | 04/08/2022 | 04/08/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2022 |  | 6/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2022 | Connected |  | N
National Grid | BELCHERTOWN | 178750 | 01007 | 495 | Solar | 05_05_3424W1 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 | 03/30/2012 | 03/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 | 02/15/2012 | 7/1/2012 | Y | EXP | 2 |  |  | 0 | 0 | 0 | 12/19/2012 | 12/19/2012 | 12/19/2012 | Connected |  | N
National Grid | FOXBOROUGH | 382439 | 02035 | 10 | Solar | 05_12_12L2 | 09/17/2021 | 11/17/2021 | 42 | 40 | 2 | 11/18/2021 | 11/18/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 1/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | N
National Grid | BEVERLY | 678749 | 01915 | 10 | Solar | 05_05_320W1 | 03/19/2025 | 03/24/2025 | 3 | 0 | 3 | 03/25/2025 | 03/25/2025 | 66 | 45 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 527426 | 01534 | 6.96 | Solar | 05_07_797W29 | 05/18/2023 | 05/22/2023 | 2 | 0 | 2 | 05/23/2023 | 05/23/2023 | 70 | 49 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 9/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2023 | Connected |  | N
National Grid | WHITMAN | 427776 | 02382 | 8.064 | Solar | 05_05_9L4 | 05/05/2022 | 05/16/2022 | 8 | 7 | 1 | 05/17/2022 | 05/17/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 | 05/05/2022 | 9/6/2023 | Y | EXP | 365 | 08/06/2022 | 09/03/2022 | 29 | 0 | 29 |  |  | 1/10/2023 | Connected |  | N
National Grid | ATTLEBORO | 175355 | 02703 | 200 | Solar | 05_01_201W2 | 09/05/2014 | 09/05/2014 | 7 | 0 | 7 | 09/17/2014 | 09/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2014 |  | 12/31/2014 | N | EXP | 7 |  |  | 0 | 0 | 0 | 12/17/2014 | 12/17/2014 | 12/18/2014 | Connected |  | N
National Grid | AYER | 697433 | 01432 | 996 | Solar | 05_09_501L2 | 07/07/2025 | 08/01/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/04/2025 | 08/28/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HARDWICK | 175587 | 01031 | 496 | Solar | 05_07_98W44 | 04/28/2014 | 04/28/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2014 | 05/27/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 | 04/28/2014 | 9/13/2018 | Y | STD | 17 | 02/16/2018 | 08/28/2018 | 193 | 0 | 193 |  |  | 9/7/2018 | Connected |  | N
National Grid | BROCKTON | 204748 | 02301 | 1380 | Solar | 05_07_91W46 | 12/27/2018 | 01/16/2019 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/17/2019 | 02/28/2019 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2020 | 12/27/2018 | 3/10/2025 | Y | STD | 86 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | BROCKTON | 488737 | 02302 | 10 | Solar | 05_09_527L2 | 03/16/2023 | 03/21/2023 | 3 | 1 | 2 | 03/22/2023 | 03/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2023 | 03/16/2023 | 6/25/2024 | Y | EXP | 365 | 06/09/2023 | 06/23/2023 | 15 | 0 | 15 |  |  | 6/29/2023 | Connected |  | N
National Grid | GRANBY | 178749 | 01033 | 75 | Solar | 05_05_3424W1 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 7/1/2012 | N | EXP | 164 |  |  | 0 | 0 | 0 | 12/19/2012 | 12/19/2012 | 12/19/2012 | Connected |  | N
National Grid | BEVERLY | 422071 | 01915 | 0 | Battery Add-On | 05_12_12L2 | 05/19/2022 | 08/11/2022 | 56 | 48 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2022 | 09/09/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 736897 | 01915 | 11.52 | Solar | 05_05_320W1 | 11/28/2025 | 12/01/2025 | 1 | 0 | 1 | 12/02/2025 | 12/02/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | WHITINSVILLE | 528895 | 01588 | 7.6 | Solar | 05_07_797W29 | 06/21/2023 | 06/22/2023 | 1 | 0 | 1 | 06/23/2023 | 06/23/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 10/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2023 | Connected |  | N
National Grid | HANSON | 431477 | 02341 | 5.8 | Solar | 05_05_9L4 | 06/03/2022 | 06/06/2022 | 1 | 0 | 1 | 06/07/2022 | 06/07/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2022 |  | 8/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | Connected |  | N
National Grid | ATTLEBORO | 175365 | 02703 | 79.2 | Solar | 05_01_201W2 | 11/17/2014 | 11/17/2014 | 4 | 0 | 4 | 11/24/2014 | 11/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2014 |  | 4/30/2015 | N | EXP | 15 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 | 12/9/2015 | Connected |  | N
National Grid | HARVARD | 697414 | 01451 | 4980 | Solar | 05_09_501L2 | 07/08/2025 | 07/30/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2025 | 08/22/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 176127 | 01082 | 1656 | Solar | 05_07_98W44 | 02/03/2015 | 02/03/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2015 | 03/10/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 09/10/2015 | 07/06/2016 | 202 | 191 | 11 | 7/6/2016 | 02/03/2015 | 7/31/2015 | Y | STD | 341 | 12/07/2016 | 06/19/2017 | 132 | 0 | 132 | 7/6/2017 | 7/6/2017 | 7/6/2017 | Connected |  | N
National Grid | WEST BRIDGEWATER | 213914 | 02379 | 100 | Solar | 05_07_91W46 | 03/14/2019 | 03/19/2019 | 2 | 0 | 2 | 03/20/2019 | 03/20/2019 | 7 | 0 | 7 | 04/05/2019 | 06/03/2019 | 41 | 15 | 26 |  |  | 0 | 0 | 0 |  | 06/03/2019 | 41 | 15 | 26 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 528945 | 02302 | 15.08 | Solar | 05_09_527L2 | 09/25/2023 | 06/02/2023 | 5 | 2 | 3 | 10/03/2023 | 10/03/2023 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 10/10/2023 | Connected |  | N
National Grid | BELCHERTOWN | 178766 | 01007 | 375 | Solar | 05_05_3424W1 | 07/27/2012 | 07/27/2012 | 242 | 233 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 464712 | 02035 | 7.6 | Solar | 05_12_12L2 | 10/03/2022 | 10/06/2022 | 3 | 0 | 3 | 10/07/2022 | 10/07/2022 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/03/2022 | 5/3/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2023 | Connected |  | N
National Grid | BEVERLY | 710539 | 01915 | 21.66 | Solar | 05_05_320W2 | 08/14/2025 | 08/25/2025 | 6 | 3 | 3 | 08/26/2025 | 08/26/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | NORTHBRIDGE | 528712 | 01534 | 3.84 | Solar | 05_07_797W29 | 05/30/2023 | 06/16/2023 | 14 | 13 | 1 | 06/20/2023 | 06/20/2023 | 39 | 18 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2023 | 05/30/2023 | 4/28/2025 | Y | EXP | 365 | 03/19/2024 | 05/14/2024 | 57 | 0 | 57 |  |  | 12/24/2024 | Connected |  | N
National Grid | EAST BRIDGEWATER | 559140 | 02333 | 0 | Battery Add-On | 05_05_9L4 | 09/28/2023 | 10/02/2023 | 2 | 0 | 2 | 10/03/2023 | 10/03/2023 | 104 | 84 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 176157 | 02703 | 230 | Solar | 05_01_201W2 | 02/04/2015 | 02/04/2015 | 3 | 1 | 2 | 02/11/2015 | 02/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2015 |  | 7/31/2015 | N | EXP | 15 |  |  | 0 | 0 | 0 | 7/23/2015 | 7/23/2015 | 8/6/2015 | Connected |  | N
National Grid | HARVARD | 700559 | 01451 | 249 | Solar | 05_09_501L2 | 07/03/2025 | 08/08/2025 | 25 | 17 | 8 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HARDWICK | 176125 | 01031 | 1660 | Solar | 05_07_98W44 | 02/03/2015 | 02/03/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2015 | 03/10/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 09/10/2015 | 07/06/2016 | 202 | 191 | 11 | 7/6/2016 |  | 7/31/2015 | N | STD | 341 | 12/07/2016 | 06/19/2017 | 132 | 0 | 132 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 330313 | 02379 | 7.6 | Solar | 05_07_91W46 | 12/21/2020 | 12/22/2020 | 0 | 0 | 0 | 12/23/2020 | 12/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2021 | 12/21/2020 |  | Y | EXP | 365 | 04/20/2021 | 04/19/2021 | 0 | 0 | 0 |  |  | 9/3/2021 | Connected |  | N
National Grid | BROCKTON | 541261 | 02302 | 0 | Battery Add-On | 05_09_527L2 | 07/17/2023 | 07/19/2023 | 2 | 0 | 2 | 07/20/2023 | 07/20/2023 | 98 | 77 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 |  | 7/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2025 | Connected |  | N
National Grid | GRANBY | 178776 | 01033 | 255 | Solar | 05_05_3424W1 | 04/02/2014 | 04/02/2014 | 5 | 0 | 5 | 04/11/2014 | 04/11/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2014 | 04/02/2014 | 6/30/2014 | Y | EXP | 67 |  |  | 0 | 0 | 0 | 8/13/2015 | 8/13/2015 | 8/13/2015 | Connected |  | N
National Grid | FOXBOROUGH | 466433 | 02035 | 6 | Solar | 05_12_12L2 | 10/12/2022 | 10/13/2022 | 1 | 0 | 1 | 10/14/2022 | 10/14/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 742639 | 01915 | 3.8 | Solar | 05_05_320W2 | 12/30/2025 | 12/31/2025 | 3 | 0 | 3 | 01/15/2026 | 01/15/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 | 12/30/2025 | 2/20/2027 | Y | EXP | 365 | 02/28/2026 |  | 7 | 0 | 7 |  |  |  | Construction |  | N
National Grid | UPTON | 531257 | 01568 | 14.4 | Solar | 05_07_797W29 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2023 |  | 8/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2023 | Connected |  | N
National Grid | EAST BRIDGEWATER | 560385 | 02333 | 18.85 | Solar | 05_05_9L4 | 06/14/2024 |  | 79 | 55 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 176412 | 02703 | 949.2 | Solar | 05_01_201W2 | 05/10/2016 | 05/10/2016 | 15 | 15 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/01/2016 | 06/15/2016 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/16/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 709806 | 01451 | 996 | Solar | 05_09_501L2 | 09/18/2025 | 09/29/2025 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/30/2025 | 10/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HARDWICK | 176382 | 01031 | 496 | Solar | 05_07_98W44 | 11/25/2015 | 11/25/2015 | 3 | 3 | 0 | 12/01/2015 | 12/01/2015 | 247 | 0 | 247 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 331606 | 02379 | 200 | Solar | 05_07_91W46 | 02/02/2021 | 02/17/2021 | 9 | 0 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 550526 | 02302 | 0 | Solar | 05_09_527L2 | 08/31/2023 | 09/12/2023 | 8 | 6 | 2 | 09/13/2023 | 09/13/2023 | 59 | 40 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2024 | Connected |  | N
National Grid | BELCHERTOWN | 178775 | 01007 | 170 | Solar | 05_05_3424W1 | 08/27/2014 | 08/27/2014 | 7 | 0 | 7 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2014 |  | 11/28/2014 | N | EXP | 57 |  |  | 0 | 0 | 0 | 1/2/2015 | 1/2/2015 | 2/22/2016 | Connected |  | N
National Grid | FOXBOROUGH | 479722 | 02035 | 6 | Solar | 05_12_12L2 | 12/10/2022 | 12/14/2022 | 13 | 9 | 4 | 12/30/2022 | 12/30/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2023 |  | 6/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2023 | Connected |  | Y
National Grid | BEVERLY | 749864 | 01915 | 15.2 | Solar | 05_05_320W2 | 02/11/2026 | 02/20/2026 | 5 | 2 | 3 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHBRIDGE | 546743 | 01534 | 10 | Solar | 05_07_797W29 | 08/21/2023 | 08/22/2023 | 1 | 0 | 1 | 08/23/2023 | 08/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2023 |  | 10/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2023 | Connected |  | N
National Grid | BRIDGEWATER | 538767 | 02333 | 15.2 | Solar | 05_05_9L4 | 07/05/2023 | 07/06/2023 | 1 | 0 | 1 | 07/07/2023 | 07/07/2023 | 54 | 26 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 176517 | 02703 | 80 | Solar | 05_01_201W2 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 | 10/06/2015 | 10/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2015 |  | 10/11/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 12/29/2015 | 12/29/2015 | 12/29/2015 | Connected |  | N
National Grid | AYER | 724261 | 01432 | 22.8 | Solar | 05_09_501L2 | 10/06/2025 | 10/28/2025 | 1 | 0 | 1 | 10/29/2025 | 10/29/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HARDWICK | 176718 | 01031 | 259.2 | Solar | 05_07_98W44 | 01/11/2016 | 01/11/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2016 | 01/27/2016 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2016 | 01/11/2016 | 12/5/2017 | Y | STD | 495 | 10/12/2017 | 11/06/2017 | 12 | 0 | 12 | 11/2/2017 | 11/2/2017 | 12/5/2017 | Connected |  | N
National Grid | WEST BRIDGEWATER | 527992 | 02379 | 20.01 | Solar | 05_07_91W46 | 05/20/2023 | 07/12/2023 | 35 | 33 | 2 | 07/13/2023 | 07/13/2023 | 40 | 23 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 |  | 1/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2024 | Connected |  | N
National Grid | BROCKTON | 601385 | 02302 | 6 | Solar | 05_09_527L2 | 04/15/2024 | 04/16/2024 | 1 | 0 | 1 | 04/17/2024 | 04/17/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 | 04/15/2024 | 5/24/2025 | Y | EXP | 365 | 08/20/2024 | 10/01/2024 | 43 | 0 | 43 |  |  | 10/8/2024 | Connected |  | N
National Grid | GRANBY | 178799 | 01033 | 432.9 | Solar | 05_05_3424W1 | 02/16/2018 | 02/16/2018 | 0 | 0 | 0 |  |  | 33 | 8 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2018 | 02/16/2018 | 9/11/2020 | Y | STD | 417 | 01/10/2020 | 05/08/2020 | 119 | 0 | 119 |  |  | 9/3/2020 | Connected |  | N
National Grid | FOXBOROUGH | 492383 | 02035 | 3.84 | Solar | 05_12_12L2 | 04/19/2023 | 04/24/2023 | 3 | 0 | 3 | 04/25/2023 | 04/25/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 174450 | 01915 | 2000 | Solar | 05_05_320W2 | 10/07/2011 | 10/07/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 10/07/2011 | 5/1/2012 | Y | STD | 225 | 10/09/2012 | 01/09/2013 | 47 | 0 | 47 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | N
National Grid | DOUGLAS | 566962 | 01516 | 3.84 | Solar | 05_07_797W29 | 10/27/2023 | 05/23/2024 | 1 | 0 | 1 | 05/24/2024 | 05/24/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2024 |  | 6/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/5/2024 | Connected |  | N
National Grid | WHITMAN | 543889 | 02382 | 3 | Solar | 05_05_9L4 | 07/26/2023 | 08/04/2023 | 7 | 5 | 2 | 08/07/2023 | 08/07/2023 | 47 | 29 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 11/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2023 | Connected |  | N
National Grid | ATTLEBORO | 176553 | 02703 | 6 | Solar | 05_01_201W2 | 10/05/2015 | 10/05/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2015 |  | 10/13/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 6/3/2016 | Connected |  | N
National Grid | AYER | 740154 | 01434 | 17.6 | Solar | 05_09_501L2 | 12/15/2025 | 12/18/2025 | 3 | 0 | 3 | 12/19/2025 | 12/19/2025 | 41 | 27 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WARE | 176992 | 01082 | 7.6 | Solar | 05_07_98W44 | 03/15/2017 | 03/15/2017 | 9 | 7 | 2 | 03/28/2017 | 03/28/2017 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2017 |  | 3/20/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 622917 | 02379 | 6 | Solar | 05_07_91W46 | 07/05/2024 | 08/01/2024 | 11 | 10 | 1 | 08/02/2024 | 08/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | BROCKTON | 610562 | 02302 | 8.99 | Solar | 05_09_527L2 | 05/13/2024 | 06/07/2024 | 2 | 0 | 2 | 06/10/2024 | 06/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 05/13/2024 | 7/8/2025 | Y | EXP | 365 | 07/26/2024 | 07/31/2024 | 6 | 0 | 6 |  |  | 8/7/2024 | Connected |  | N
National Grid | BELCHERTOWN | 189459 | 01007 | 7.6 | Solar | 05_05_3424W1 | 06/27/2018 | 06/27/2018 | 44 | 24 | 20 | 08/30/2018 | 08/30/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  | 9/10/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2019 | Connected |  | N
National Grid | FOXBOROUGH | 654225 | 02035 | 10 | Solar | 05_12_12L2 | 11/15/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/15/2024 | 2/19/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | BEVERLY | 174445 | 01915 | 60 | Solar | 05_05_320W2 | 07/09/2012 | 07/09/2012 | 6 | 0 | 6 | 07/19/2012 | 07/19/2012 | 0 | 0 | 0 | 02/11/2013 | 02/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2013 | 07/09/2012 | 11/30/2012 | Y | EXP | 73 | 06/18/2013 | 07/31/2013 | 30 | 0 | 30 | 2/11/2013 | 2/11/2013 | 8/12/2013 | Connected |  | N
National Grid | DOUGLAS | 597629 | 01516 | 10 | Solar | 05_07_797W29 | 05/07/2024 | 06/07/2024 | 23 | 22 | 1 | 06/10/2024 | 06/10/2024 | 41 | 26 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 549717 | 02333 | 11.4 | Solar | 05_05_9L4 | 08/24/2023 | 09/13/2023 | 14 | 13 | 1 | 09/14/2023 | 09/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 | 08/24/2023 | 11/22/2024 | Y | EXP | 365 | 06/05/2024 | 06/06/2024 | 2 | 0 | 2 |  |  | 6/18/2024 | Connected |  | N
National Grid | ATTLEBORO | 176586 | 02703 | 236 | Solar | 05_01_201W2 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2017 | 10/19/2016 | 4/16/2017 | Y | EXP | 1 |  |  | 0 | 0 | 0 | 1/10/2017 | 1/10/2017 | 1/4/2018 | Connected |  | N
National Grid | AYER | 746599 | 01432 | 23 | Battery Add-On | 05_09_501L2 | 01/22/2026 | 01/27/2026 | 3 | 0 | 3 | 01/28/2026 | 01/28/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HARDWICK | 178509 | 01031 | 60 | Solar | 05_07_98W44 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 | 03/19/2018 | 03/19/2018 | 55 | 41 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2018 |  | 3/13/2019 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  | 5/30/2019 | Connected |  | N
National Grid | WEST BRIDGEWATER | 650518 | 02379 | 7.6 | Solar | 05_07_91W46 | 11/11/2024 | 01/06/2025 | 5 | 0 | 5 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 11/11/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | BROCKTON | 653885 | 02382 | 7.6 | Solar | 05_09_527L2 | 11/15/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/15/2024 | 8/10/2026 | Y | EXP | 365 | 11/14/2025 |  | 113 | 0 | 113 |  |  | 3/5/2026 | Connected |  | N
National Grid | GRANBY | 290810 | 01033 | 400 | Solar | 05_05_3424W1 | 05/29/2020 | 07/31/2020 | 38 | 21 | 17 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 658638 | 01915 | 5.76 | Solar | 05_12_12L2 | 12/05/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 | 12/05/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | BEVERLY | 174722 | 01915 | 14 | Solar | 05_05_320W2 | 08/03/2010 | 08/03/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2010 |  | 12/31/2012 | N | EXP | 881 |  |  | 0 | 0 | 0 | 11/29/2012 | 11/29/2012 | 8/3/2010 | Connected |  | N
National Grid | DOUGLAS | 603730 | 01516 | 16.128 | Solar | 05_07_797W29 | 04/17/2024 | 07/18/2024 | 32 | 29 | 3 | 07/19/2024 | 07/19/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 9/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2024 | Connected |  | N
National Grid | WHITMAN | 552428 | 02382 | 6 | Solar | 05_05_9L4 | 09/22/2023 | 09/25/2023 | 2 | 1 | 1 | 09/26/2023 | 09/26/2023 | 43 | 18 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2023 |  | 1/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2024 | Connected |  | N
National Grid | ATTLEBORO | 206095 | 02703 | 10 | Solar | 05_01_201W2 | 02/04/2019 | 02/07/2019 | 2 | 2 | 0 | 02/08/2019 | 02/08/2019 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 |  | 7/19/2019 | N | EXP | 14 |  |  | 0 | 0 | 0 |  |  | 7/10/2019 | Connected |  | N
National Grid | AYER | 174162 | 01432 | 276.8 | Solar | 05_09_501L2 | 04/23/2012 | 04/23/2012 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 06/25/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 09/10/2013 | 10/22/2013 | 29 | 0 | 29 | 12/31/2013 | 04/23/2012 |  | Y | STD | 365 | 06/29/2015 | 07/29/2015 | 21 | 0 | 21 | 7/29/2015 | 7/29/2015 | 7/31/2015 | Connected |  | N
National Grid | HARDWICK | 188061 | 01037 | 1400 | Solar | 05_07_98W44 | 06/14/2018 | 06/14/2018 | 10 | 9 | 1 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 | 06/14/2018 | 11/29/2022 | Y | STD | 29 | 06/05/2021 | 09/23/2021 | 111 | 3 | 108 |  |  | 10/18/2022 | Connected |  | N
National Grid | BROCKTON | 653234 | 02301 | 3.8 | Solar | 05_07_91W46 | 11/08/2024 | 11/26/2024 | 3 | 0 | 3 | 11/27/2024 | 11/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 661566 | 02302 | 23 | Battery Add-On | 05_09_527L2 | 12/18/2024 | 12/30/2024 | 8 | 5 | 3 | 12/31/2024 | 12/31/2024 | 85 | 25 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 345466 | 01007 | 500 | Solar | 05_05_3424W1 | 04/07/2021 | 07/01/2021 | 59 | 50 | 9 |  |  | 67 | 27 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2022 | 04/07/2021 | 6/20/2024 | Y | STD | 322 | 02/28/2023 | 11/15/2023 | 261 | 190 | 71 |  |  | 6/20/2024 | Connected |  | N
National Grid | FOXBOROUGH | 688843 | 02035 | 15.2 | Solar | 05_12_12L2 | 05/01/2025 | 05/12/2025 | 6 | 2 | 4 | 05/13/2025 | 05/13/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 | 05/01/2025 | 6/12/2026 | Y | EXP | 365 | 10/17/2025 | 11/24/2025 | 39 | 0 | 39 |  |  | 11/25/2025 | Connected |  | N
National Grid | BEVERLY | 174903 | 01915 | 1000 | Solar | 05_05_320W2 | 08/10/2012 | 08/10/2012 | 244 | 241 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 634802 | 01516 | 10 | Solar | 05_07_797W29 | 08/22/2024 | 09/17/2024 | 11 | 9 | 2 | 09/18/2024 | 09/18/2024 | 15 | 7 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2024 | 08/22/2024 | 12/18/2025 | Y | EXP | 365 | 12/19/2024 | 01/10/2025 | 23 | 0 | 23 |  |  | 3/15/2025 | Connected |  | N
National Grid | BRIDGEWATER | 564312 | 02333 | 15.2 | Solar | 05_05_9L4 | 10/18/2023 | 10/20/2023 | 2 | 0 | 2 | 10/23/2023 | 10/23/2023 | 80 | 64 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 3/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | ATTLEBORO | 207974 | 02703 | 9.8 | Solar | 05_01_201W2 | 08/20/2019 | 10/30/2019 | 49 | 47 | 2 | 10/31/2019 | 10/31/2019 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 | 08/20/2019 | 11/18/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2020 | Connected |  | N
National Grid | AYER | 174161 | 01432 | 1825.6 | Solar | 05_09_501L2 | 04/20/2012 | 04/20/2012 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 06/25/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 09/10/2013 | 10/22/2013 | 29 | 0 | 29 | 12/31/2013 | 04/20/2012 | 12/31/2014 | Y | STD | 365 | 06/29/2015 | 07/29/2015 | 21 | 0 | 21 | 7/29/2015 | 7/29/2015 | 7/31/2015 | Connected |  | N
National Grid | WARE | 204836 | 01082 | 300 | Solar | 05_07_98W44 | 12/27/2018 | 01/10/2019 | 9 | 5 | 4 | 01/11/2019 | 01/11/2019 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2019 |  | 9/3/2023 | N | EXP | 448 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 653207 | 02379 | 3.8 | Solar | 05_07_91W46 | 11/08/2024 | 11/27/2024 | 4 | 0 | 4 | 12/02/2024 | 12/02/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 669000 | 02302 | 7.36 | Solar | 05_09_527L2 | 01/30/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | GRANBY | 412230 | 01033 | 0 | Battery Add-On | 05_05_3424W1 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/25/2022 | 25 | 7 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 694351 | 02035 | 5.76 | Solar | 05_12_12L2 | 05/28/2025 | 11/07/2025 | 1 | 0 | 1 | 11/14/2025 | 11/14/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 175936 | 01915 | 22.8 | Solar | 05_05_320W2 | 01/20/2015 | 01/20/2015 | 5 | 1 | 4 | 01/28/2015 | 01/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2015 |  | 6/30/2015 | N | EXP | 13 |  |  | 0 | 0 | 0 | 3/11/2015 | 3/11/2015 | 9/28/2015 | Connected |  | N
National Grid | DOUGLAS | 646690 | 01516 | 5.76 | Solar | 05_07_797W29 | 10/25/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/25/2024 | 1/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | EAST BRIDGEWATER | 583657 | 02333 | 8.12 | Solar | 05_05_9L4 | 02/06/2024 | 02/20/2024 | 10 | 7 | 3 | 02/21/2024 | 02/21/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2024 | Connected |  | N
National Grid | ATTLEBORO | 243831 | 02703 | 6.38 | Solar | 05_01_201W2 | 07/31/2019 | 08/01/2019 | 0 | 0 | 0 | 08/02/2019 | 08/02/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2019 | 07/31/2019 | 11/15/2019 | Y | EXP | 94 | 09/25/2019 | 10/02/2019 | 7 | 0 | 7 |  |  | 10/25/2019 | Connected |  | N
National Grid | AYER | 175215 | 01432 | 480 | Solar | 05_09_501L2 | 11/03/2014 | 11/03/2014 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2014 | 12/18/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 05/10/2016 | 06/27/2016 | 32 | 0 | 32 | 12/21/2015 | 11/03/2014 | 3/31/2017 | Y | STD | 466 | 10/28/2016 | 03/23/2017 | 98 | 0 | 98 | 3/27/2017 | 3/27/2017 | 4/3/2017 | Connected |  | N
National Grid | WARE | 389735 | 01082 | 0 | Other | 05_07_98W44 | 11/10/2021 | 01/04/2022 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 658949 | 02301 | 3.8 | Solar | 05_07_91W46 | 12/09/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 | 02/07/2025 | 03/18/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 03/18/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 669322 | 02302 | 0 | Battery Add-On | 05_09_527L2 | 01/31/2025 | 02/03/2025 | 1 | 0 | 1 | 02/04/2025 | 02/04/2025 | 61 | 46 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2025 | Connected |  | N
National Grid | HADLEY | 493291 | 01075 | 19 | Solar | 05_05_3424W1 | 01/18/2023 | 01/19/2023 | 1 | 0 | 1 | 01/20/2023 | 01/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 2/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2023 | Connected |  | N
National Grid | FOXBOROUGH | 380771 | 02035 | 360 | Solar | 05_12_12L4 | 09/09/2021 | 10/11/2021 | 21 | 14 | 7 |  |  | 45 | 5 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 | 09/09/2021 | 7/7/2026 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BEVERLY | 177725 | 01915 | 4982 | Solar | 05_05_320W2 | 10/04/2017 | 10/04/2017 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 | 12/07/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2018 |  | 4/5/2019 | N | STD | 332 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 670573 | 01516 | 10 | Solar | 05_07_797W29 | 02/06/2025 | 03/10/2025 | 14 | 11 | 3 | 03/11/2025 | 03/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | EAST BRIDGEWATER | 613496 | 02333 | 5.8 | Solar | 05_05_9L4 | 06/05/2024 | 06/11/2024 | 4 | 3 | 1 | 06/12/2024 | 06/12/2024 | 35 | 21 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 247186 | 02703 | 15.2 | Solar | 05_01_201W2 | 08/06/2019 | 08/07/2019 | 0 | 0 | 0 | 08/08/2019 | 08/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2019 | 08/06/2019 | 5/1/2020 | Y | EXP | 259 | 10/29/2019 | 11/07/2019 | 9 | 0 | 9 |  |  | 1/14/2020 | Connected |  | N
National Grid | HARVARD | 175216 | 01451 | 480 | Solar | 05_09_501L2 | 11/03/2014 | 11/03/2014 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2014 | 12/18/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 05/10/2016 | 06/27/2016 | 32 | 0 | 32 | 12/21/2015 | 11/03/2014 | 3/31/2017 | Y | STD | 466 | 10/10/2016 | 03/23/2017 | 111 | 0 | 111 | 3/27/2017 | 3/27/2017 | 4/3/2017 | Connected |  | N
National Grid | HARDWICK | 401391 | 01031 | 9.8 | Solar | 05_07_98W44 | 03/02/2022 | 03/08/2022 | 4 | 2 | 2 | 03/09/2022 | 03/09/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2022 | 03/02/2022 | 7/27/2023 | Y | EXP | 365 | 07/13/2022 | 07/21/2022 | 9 | 0 | 9 |  |  | 1/31/2023 | Connected |  | N
National Grid | WEST BRIDGEWATER | 745914 | 02379 | 3.8 | Solar | 05_07_91W47 | 01/16/2026 | 01/21/2026 | 4 | 0 | 4 | 02/11/2026 | 02/11/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 686247 | 02302 | 11.5 | Solar | 05_09_527L2 | 05/06/2025 | 05/08/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 8/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | GRANBY | 583853 | 01033 | 11.5 | Solar | 05_05_3424W1 | 02/01/2024 | 02/08/2024 | 5 | 3 | 2 | 02/09/2024 | 02/09/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 |  | 4/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2024 | Connected |  | N
National Grid | FOXBOROUGH | 697519 | 02035 | 24.96 | Solar | 05_12_12L4 | 06/26/2025 | 07/14/2025 | 10 | 8 | 2 | 07/15/2025 | 07/15/2025 | 14 | 2 | 12 | 08/11/2025 | 12/18/2025 | 90 | 49 | 41 |  |  | 0 | 0 | 0 |  | 12/18/2025 | 90 | 49 | 41 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 1/14/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BEVERLY | 178465 | 01915 | 1750 | Solar | 05_05_320W2 | 01/22/2018 | 01/22/2018 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/12/2018 | 05/05/2018 | 40 | 19 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/28/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 697510 | 01516 | 14.06 | Solar | 05_07_797W29 | 06/10/2025 | 06/26/2025 | 4 | 0 | 4 | 07/31/2025 | 07/31/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | BRIDGEWATER | 627851 | 02333 | 5.76 | Solar | 05_05_9L4 | 07/25/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2024 | Connected |  | N
National Grid | ATTLEBORO | 279637 | 02703 | 10.44 | Solar | 05_01_201W2 | 02/14/2020 | 03/06/2020 | 14 | 14 | 0 | 03/09/2020 | 03/09/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2020 |  | 3/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2020 | Connected |  | N
National Grid | HARVARD | 175476 | 01451 | 1000 | Solar | 05_09_501L2 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/12/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2015 |  | 3/1/2017 | N | STD | 622 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 552189 | 01031 | 4.095 | Solar | 05_07_98W44 | 08/31/2023 | 09/05/2023 | 2 | 0 | 2 | 09/06/2023 | 09/06/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  | 11/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2023 | Connected |  | N
National Grid | BROCKTON | 174594 | 02302 | 36.4 | Solar | 05_07_91W47 | 10/20/2011 | 10/20/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2012 |  | 3/2/2012 | N | EXP | 24 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 3/2/2012 | Connected |  | N
National Grid | BROCKTON | 713614 | 02302 | 11.4 | Solar | 05_09_604W1 | 08/28/2025 | 09/23/2025 | 4 | 0 | 4 | 10/07/2025 | 10/07/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 08/28/2025 | 12/30/2026 | Y | EXP | 365 | 02/19/2026 |  | 16 | 0 | 16 |  |  |  | Construction |  | N
National Grid | GRANBY | 636407 | 01033 | 15.2 | Solar | 05_05_3424W1 | 08/30/2024 | 09/04/2024 | 2 | 0 | 2 | 09/05/2024 | 09/05/2024 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 10/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2024 | Connected |  | N
National Grid | FOXBOROUGH | 705356 | 02035 | 249 | Solar | 05_12_12L4 | 07/17/2025 | 08/18/2025 | 21 | 13 | 8 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BEVERLY | 178564 | 01915 | 4998 | Solar | 05_05_320W2 | 04/05/2018 | 04/05/2018 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2018 | 09/06/2018 | 74 | 66 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2019 |  | 4/11/2020 | N | STD | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 712520 | 01516 | 0 | Battery Add-On | 05_07_797W29 | 08/15/2025 | 08/19/2025 | 2 | 0 | 2 | 08/20/2025 | 08/20/2025 | 53 | 33 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N
National Grid | WHITMAN | 628004 | 02382 | 18.85 | Solar | 05_05_9L4 | 08/01/2024 | 08/22/2024 | 12 | 10 | 2 | 08/23/2024 | 08/23/2024 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 282114 | 02703 | 66.6 | Solar | 05_01_201W2 | 07/21/2020 | 08/12/2020 | 15 | 9 | 6 | 08/13/2020 | 08/13/2020 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 | 07/21/2020 | 4/29/2022 | Y | EXP | 336 |  |  | 0 | 0 | 0 |  |  | 4/29/2022 | Connected |  | N
National Grid | HARVARD | 175475 | 01451 | 1000 | Solar | 05_09_501L2 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/12/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2015 |  | 3/1/2017 | N | STD | 622 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 564164 | 01037 | 499 | Solar | 05_07_98W44 | 07/03/2024 | 03/14/2025 | 172 | 162 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2025 | 04/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 175275 | 02379 | 42.57 | Solar | 05_07_91W47 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2014 |  | 11/28/2014 | N | EXP | 7 |  |  | 0 | 0 | 0 | 9/19/2014 | 9/19/2014 | 4/30/2015 | Connected |  | N
National Grid | BROCKTON | 174176 | 02302 | 500 | Solar | 05_09_604W1 | 03/04/2012 | 03/04/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 330982 | 01033 | 2738 | Solar | 05_05_3424W3 | 02/25/2021 | 03/08/2021 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2021 | 04/06/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2022 | 02/25/2021 | 11/26/2026 | Y | STD | 364 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | FOXBOROUGH | 174129 | 02035 | 224 | Solar | 05_12_12L4 | 04/30/2012 | 04/30/2012 | 11 | 0 | 11 | 05/17/2012 | 05/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2012 |  | 9/28/2012 | N | EXP | 39 |  |  | 0 | 0 | 0 | 1/30/2013 | 1/30/2013 | 1/8/2013 | Connected |  | N
National Grid | BEVERLY | 178647 | 01915 | 1750 | Solar | 05_05_320W2 | 12/15/2017 | 12/15/2017 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 644742 | 01516 | 1996 | Solar | 05_07_797W42 | 10/03/2024 | 02/13/2026 | 98 | 95 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2026 |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WHITMAN | 634091 | 02382 | 5.76 | Solar | 05_05_9L4 | 08/20/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 283144 | 02703 | 7.6 | Solar | 05_01_201W2 | 03/11/2020 | 04/30/2020 | 34 | 26 | 8 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 3/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2020 | Connected |  | N
National Grid | HARVARD | 176023 | 01451 | 180 | Solar | 05_09_501L2 | 03/25/2015 | 03/25/2015 | 7 | 4 | 3 | 04/06/2015 | 04/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2015 |  | 8/31/2015 | N | EXP | 147 |  |  | 0 | 0 | 0 | 7/10/2017 | 7/10/2017 | 7/31/2017 | Connected |  | N
National Grid | HARDWICK | 627633 | 01037 | 10.725 | Solar | 05_07_98W44 | 07/30/2024 | 08/15/2024 | 3 | 0 | 3 | 08/16/2024 | 08/16/2024 | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 07/30/2024 | 9/25/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 176108 | 02379 | 476 | Solar | 05_07_91W47 | 06/26/2015 | 06/26/2015 | 2 | 2 | 0 | 06/30/2015 | 06/30/2015 | 451 | 0 | 451 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2015 | 06/26/2015 | 7/1/2016 | Y | EXP | 33 |  |  | 0 | 0 | 0 | 8/6/2015 | 8/6/2015 |  | Withdrawn |  | N
National Grid | WHITMAN | 174175 | 02382 | 500 | Solar | 05_09_604W1 | 03/04/2012 | 03/04/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 178764 | 01033 | 499 | Solar | 05_05_3424W3 | 06/05/2013 | 06/05/2013 | 7 | 0 | 7 | 06/17/2013 | 06/17/2013 | 1077 | 0 | 1077 | 07/08/2014 | 10/17/2017 | 816 | 0 | 816 |  |  | 0 | 0 | 0 |  | 10/17/2017 | 816 | 0 | 816 |  |  | 0 | 0 | 0 | 7/22/2014 |  | 9/30/2018 | N | EXP | 1531 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 174128 | 02035 | 224 | Solar | 05_12_12L4 | 04/30/2012 | 04/30/2012 | 11 | 0 | 11 | 05/17/2012 | 05/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2012 |  | 9/28/2012 | N | EXP | 39 |  |  | 0 | 0 | 0 | 1/30/2013 | 1/30/2013 | 1/8/2013 | Connected |  | N
National Grid | BEVERLY | 178717 | 01915 | 1000 | Solar | 05_05_320W2 | 04/11/2018 | 04/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2018 | 05/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 693546 | 01516 | 15.2 | Solar | 05_07_797W42 | 05/28/2025 | 06/03/2025 | 4 | 0 | 4 | 06/04/2025 | 06/04/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HANSON | 637461 | 02341 | 10 | Solar | 05_05_9L4 | 09/04/2024 | 09/16/2024 | 1 | 0 | 1 | 09/17/2024 | 09/17/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 292576 | 02703 | 3.8 | Solar | 05_01_201W2 | 07/09/2020 | 07/17/2020 | 5 | 0 | 5 | 07/20/2020 | 07/20/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 176205 | 01451 | 495 | Solar | 05_09_501L2 | 04/24/2015 | 04/24/2015 | 6 | 6 | 0 | 05/05/2015 | 05/05/2015 | 246 | 0 | 246 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 683588 | 01037 | 6 | Solar | 05_07_98W44 | 04/08/2025 | 04/28/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 | 04/08/2025 | 7/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 177267 | 02379 | 10 | Solar | 05_07_91W47 | 11/08/2016 | 11/08/2016 | 1 | 1 | 0 | 11/10/2016 | 11/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2016 |  | 11/14/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 10/10/2017 | 10/10/2017 | 10/10/2017 | Connected |  | N
National Grid | BROCKTON | 174191 | 02302 | 1750 | Solar | 05_09_604W1 | 03/15/2012 | 03/15/2012 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PETERSHAM | 178804 | 01366 | 400 | Natural Gas | 05_05_3424W3 | 03/21/2018 | 03/21/2018 | 10 | 9 | 1 |  |  | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 |  | 9/6/2019 | N | STD | 214 | 09/06/2019 | 09/05/2019 | 0 | 0 | 0 | 9/6/2019 | 9/5/2019 | 9/5/2019 | Connected |  | N
National Grid | FOXBOROUGH | 174663 | 02035 | 50 | Solar | 05_12_12L4 | 12/13/2012 | 12/13/2012 | 8 | 0 | 8 | 12/27/2012 | 12/27/2012 | 0 | 0 | 0 | 03/12/2013 | 03/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2013 | 12/13/2012 | 4/30/2013 | Y | EXP | 55 |  |  | 0 | 0 | 0 | 8/7/2013 | 8/7/2013 | 8/28/2013 | Connected |  | N
National Grid | BEVERLY | 178716 | 01915 | 250 | Solar | 05_05_320W2 | 04/11/2018 | 04/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2018 | 05/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 745088 | 01516 | 20 | Solar | 05_07_797W42 | 01/13/2026 | 01/16/2026 | 3 | 1 | 2 | 01/20/2026 | 01/20/2026 | 33 | 21 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WHITMAN | 641014 | 02382 | 7.6 | Solar | 05_05_9L4 | 09/17/2024 | 10/07/2024 | 4 | 0 | 4 | 10/08/2024 | 10/08/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  | 12/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 293316 | 02703 | 7.6 | Solar | 05_01_201W2 | 05/27/2020 | 06/03/2020 | 4 | 0 | 4 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2020 | Connected |  | N
National Grid | AYER | 176263 | 01432 | 20 | Solar | 05_09_501L2 | 09/08/2015 | 09/08/2015 | 4 | 4 | 0 | 09/14/2015 | 09/14/2015 | 338 | 0 | 338 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2015 |  | 9/13/2016 | N | EXP | 348 |  |  | 0 | 0 | 0 | 4/11/2016 | 4/11/2016 |  | Withdrawn |  | Y
National Grid | HARDWICK | 707304 | 01037 | 7.6 | Solar | 05_07_98W46 | 07/24/2025 | 08/25/2025 | 4 | 0 | 4 | 08/26/2025 | 08/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEST BRIDGEWATER | 204844 | 02379 | 180 | Solar | 05_07_91W47 | 12/28/2018 | 01/09/2019 | 7 | 4 | 3 | 01/10/2019 | 01/10/2019 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 |  | 3/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174324 | 02302 | 0 | Solar | 05_09_604W1 | 01/13/2012 | 01/13/2012 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2013 | 01/13/2012 | 12/31/2012 | Y | STD | 158 |  |  | 0 | 0 | 0 | 5/28/2014 | 5/28/2014 | 5/29/2014 | Connected |  | N
National Grid | PETERSHAM | 197444 | 01366 | 2085 | Natural Gas | 05_05_3424W3 | 03/08/2019 | 04/05/2019 | 20 | 12 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/08/2019 | 04/17/2019 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2019 | 03/08/2019 | 12/31/2019 | Y | STD | 25 |  |  | 0 | 0 | 0 |  |  | 12/23/2019 | Connected |  | N
National Grid | BEVERLY | 175051 | 01915 | 190 | Solar | 05_12_12L4 | 10/18/2011 | 10/18/2011 | 76 | 0 | 76 | 02/09/2012 | 02/09/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2012 | 10/18/2011 | 11/30/2012 | Y | EXP | 267 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 8/23/2012 | Connected |  | N
National Grid | BEVERLY | 178715 | 01915 | 1000 | Solar | 05_05_320W2 | 04/11/2018 | 04/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2018 | 05/10/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 754474 | 01516 | 10.819 | Solar | 05_07_797W42 | 03/04/2026 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BRIDGEWATER | 643239 | 02333 | 3.8 | Solar | 05_05_9L4 | 09/26/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 09/26/2024 | 3/21/2026 | Y | EXP | 365 | 02/22/2025 | 02/21/2025 | 0 | 0 | 0 |  |  | 4/24/2025 | Connected |  | N
National Grid | ATTLEBORO | 298159 | 02703 | 10 | Solar | 05_01_201W2 | 06/26/2020 | 07/07/2020 | 6 | 1 | 5 | 07/08/2020 | 07/08/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2020 | Connected |  | N
National Grid | HARVARD | 176561 | 01451 | 250 | Solar | 05_09_501L2 | 12/18/2015 | 12/22/2015 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2015 | 01/22/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/25/2016 | 59 | 0 | 59 | 1/15/2019 | 12/18/2015 |  | Y | STD | 259 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 731035 | 01037 | 11.5 | Solar | 05_07_98W46 | 11/03/2025 | 11/25/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 | 11/03/2025 | 1/30/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WEST BRIDGEWATER | 284129 | 02379 | 999 | Solar | 05_07_91W47 | 03/23/2020 | 04/10/2020 | 14 | 9 | 5 |  |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 | 03/23/2020 | 9/27/2022 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174911 | 02302 | 3000 | Solar | 05_09_604W1 | 09/17/2012 | 09/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PETERSHAM | 412238 | 01366 | 0 | Battery Add-On | 05_05_3424W3 | 07/28/2022 | 08/11/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2022 | 09/09/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 175852 | 01915 | 1104 | Solar | 05_12_12L4 | 05/21/2015 | 05/21/2015 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/18/2015 | 07/16/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2016 |  | 10/30/2015 | N | STD | 77 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 178714 | 01915 | 500 | Solar | 05_05_320W2 | 04/11/2018 | 04/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2018 | 05/25/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 174559 | 01516 | 2000 | Solar | 05_07_797W42 | 09/02/2011 | 09/02/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2011 | 12/09/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2012 | 09/02/2011 | 10/31/2012 | Y | STD | 9 | 04/01/2013 | 05/28/2013 | 39 | 0 | 39 | 5/9/2013 | 5/9/2013 | 6/7/2013 | Connected |  | N
National Grid | BRIDGEWATER | 648652 | 02333 | 10 | Solar | 05_05_9L4 | 10/21/2024 | 11/06/2024 | 7 | 4 | 3 | 11/07/2024 | 11/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/21/2024 | 12/18/2025 | Y | EXP | 365 | 01/07/2025 | 01/06/2025 | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | N
National Grid | ATTLEBORO | 311609 | 02703 | 10 | Solar | 05_01_201W2 | 09/09/2020 | 09/10/2020 | 0 | 0 | 0 | 09/11/2020 | 09/11/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2020 |  | 9/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | N
National Grid | AYER | 176560 | 01432 | 972 | Solar | 05_09_501L2 | 12/17/2015 | 12/18/2015 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2015 | 01/15/2016 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 10/18/2016 | 10/25/2016 | 5 | 0 | 5 | 2/4/2019 | 12/17/2015 | 10/9/2020 | Y | STD | 441 | 02/28/2020 | 04/01/2020 | 33 | 0 | 33 |  |  | 10/8/2020 | Connected |  | N
National Grid | HARDWICK | 745954 | 01031 | 11.5 | Solar | 05_07_98W46 | 01/16/2026 | 01/21/2026 | 2 | 0 | 2 | 01/29/2026 | 01/29/2026 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BRIDGEWATER | 334165 | 02379 | 9.8 | Solar | 05_07_91W47 | 01/11/2021 |  | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 175234 | 02382 | 480 | Solar | 05_09_604W1 | 06/17/2014 | 06/17/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/22/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2014 | 06/17/2014 | 12/31/2016 | Y | STD | 74 | 09/03/2015 | 12/02/2015 | 60 | 0 | 60 | 11/30/2015 | 11/30/2015 | 12/22/2015 | Connected |  | N
National Grid | PETERSHAM | 607373 | 01366 | 100 | Solar | 05_05_3424W5 | 04/29/2024 | 07/16/2024 | 53 | 45 | 8 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 3/20/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | N
National Grid | FOXBOROUGH | 175876 | 02035 | 50 | Solar | 05_12_12L4 | 03/09/2015 | 03/09/2015 | 4 | 0 | 4 | 03/16/2015 | 03/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 |  | 8/13/2015 | N | EXP | 149 |  |  | 0 | 0 | 0 | 5/13/2015 | 5/13/2015 | 7/7/2015 | Connected |  | N
National Grid | BEVERLY | 178713 | 01915 | 1000 | Solar | 05_05_320W2 | 04/11/2018 | 04/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2018 | 05/25/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 175092 | 01516 | 12 | Solar | 05_07_797W42 | 10/23/2012 | 10/23/2012 | 2 | 0 | 2 | 11/06/2012 | 11/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2013 |  | 1/15/2013 | N | EXP | 3 |  |  | 0 | 0 | 0 | 2/3/2014 | 2/3/2014 | 2/10/2014 | Connected |  | N
National Grid | EAST BRIDGEWATER | 651200 | 02333 | 5 | Solar | 05_05_9L4 | 11/01/2024 | 12/20/2024 | 15 | 12 | 3 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2025 | Connected |  | N
National Grid | ATTLEBORO | 329550 | 02703 | 10 | Solar | 05_01_201W2 | 12/10/2020 | 12/14/2020 | 1 | 0 | 1 | 12/15/2020 | 12/15/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2021 | Connected |  | N
National Grid | AYER | 177024 | 01432 | 15.2 | Solar | 05_09_501L2 | 03/16/2017 | 03/16/2017 | 8 | 7 | 1 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 |  | 3/21/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 | 9/19/2017 | 9/19/2017 | 9/19/2017 | Connected |  | N
National Grid | HARDWICK | 754993 | 01037 | 15.58 | Solar | 05_07_98W46 | 03/06/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BROCKTON | 392417 | 02301 | 6 | Solar | 05_07_91W47 | 02/17/2022 | 02/23/2022 | 3 | 0 | 3 | 02/24/2022 | 02/24/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175233 | 02302 | 480 | Solar | 05_09_604W1 | 06/17/2014 | 06/17/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/22/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2014 | 06/17/2014 | 12/31/2016 | Y | STD | 74 | 09/03/2015 | 12/02/2015 | 60 | 0 | 60 | 11/30/2015 | 11/30/2015 | 12/22/2015 | Connected |  | N
National Grid | BARRE | 607351 | 01005 | 50 | Solar | 05_05_3424W5 | 04/29/2024 | 07/16/2024 | 53 | 44 | 9 | 07/17/2024 | 07/17/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 3/18/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | FOXBOROUGH | 176984 | 02035 | 1104 | Solar | 05_12_12L4 | 03/07/2017 | 03/07/2017 | 229 | 225 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/13/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 178712 | 01915 | 4998 | Solar | 05_05_320W2 | 04/12/2018 | 04/12/2018 | 14 | 1 | 13 |  |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 | 04/12/2018 | 1/26/2022 | Y | STD | 455 | 06/09/2021 | 12/28/2021 | 203 | 7 | 196 |  |  | 1/24/2022 | Connected |  | N
National Grid | DOUGLAS | 176134 | 01516 | 1000 | Solar | 05_07_797W42 | 04/16/2015 | 04/16/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/17/2015 | 05/18/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 652294 | 02333 | 5.76 | Solar | 05_05_9L4 | 11/06/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 37 | 22 | 15 | 01/27/2025 | 02/11/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 02/11/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/28/2026 | N | EXP | 365 | 03/12/2025 | 04/14/2025 | 34 | 0 | 34 |  |  | 4/21/2025 | Connected |  | N
National Grid | ATTLEBORO | 341611 | 02703 | 7.6 | Solar | 05_01_201W2 | 02/10/2021 | 02/11/2021 | 0 | 0 | 0 | 02/12/2021 | 02/12/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2021 |  | 2/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2021 | Connected |  | N
National Grid | HARVARD | 177674 | 01451 | 4980 | Solar | 05_09_501L2 | 07/20/2017 | 08/11/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2017 | 09/06/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 12/31/2019 | N | STD | 588 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 174197 | 01082 | 2000 | Solar | 05_07_98W46 | 03/20/2012 | 03/20/2012 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2012 | 09/04/2012 | 96 | 0 | 96 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2013 | 03/20/2012 | 6/1/2014 | Y | STD | 319 | 06/05/2014 | 07/11/2014 | 24 | 0 | 24 | 7/25/2014 | 7/25/2014 | 7/31/2014 | Connected |  | N
National Grid | BROCKTON | 541611 | 02301 | 90 | Solar | 05_07_91W47 | 08/07/2023 | 10/05/2023 | 43 | 33 | 10 |  |  | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175232 | 02302 | 480 | Solar | 05_09_604W1 | 06/17/2014 | 06/17/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/22/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2014 | 06/17/2014 | 12/31/2016 | Y | STD | 74 | 09/03/2015 | 12/02/2015 | 60 | 0 | 60 | 11/30/2015 | 11/30/2015 | 12/30/2015 | Connected |  | N
National Grid | NEW SALEM | 683373 | 01355 | 4998 | Other | 05_05_3424W5 | 10/16/2025 | 01/06/2026 | 54 | 45 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2026 | 01/30/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FOXBOROUGH | 178374 | 02035 | 57.5 | Solar | 05_12_12L4 | 11/21/2017 | 11/21/2017 | 10 | 0 | 10 | 12/08/2017 | 12/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2018 |  | 11/27/2018 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  | 7/25/2018 | Connected |  | N
National Grid | BEVERLY | 178711 | 01915 | 250 | Solar | 05_05_320W2 | 04/11/2018 | 05/23/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 176312 | 01516 | 5.16 | Solar | 05_07_797W42 | 02/25/2015 | 02/25/2015 | 9 | 6 | 3 | 03/11/2015 | 03/11/2015 | 439 | 0 | 439 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 |  | 12/31/2016 | N | EXP | 655 |  |  | 0 | 0 | 0 | 3/17/2015 | 3/17/2015 |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 655290 | 02333 | 10 | Solar | 05_05_9L4 | 11/19/2024 | 12/11/2024 | 5 | 3 | 2 | 12/12/2024 | 12/12/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/19/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | ATTLEBORO | 348883 | 02703 | 7.68 | Solar | 05_01_201W2 | 03/26/2021 | 03/29/2021 | 0 | 0 | 0 | 03/30/2021 | 03/30/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2021 | Connected |  | N
National Grid | HARVARD | 177782 | 01451 | 1320 | Solar | 05_09_501L2 | 05/31/2017 | 06/21/2017 | 14 | 12 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/21/2017 | 07/11/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2017 | 05/31/2017 | 12/16/2021 | Y | STD | 63 | 11/27/2019 | 03/03/2021 | 463 | 6 | 457 | 11/17/2021 | 12/6/2021 | 12/10/2021 | Connected |  | N
National Grid | WARE | 175118 | 01082 | 50 | Solar | 05_07_98W46 | 10/18/2013 | 10/18/2013 | 5 | 0 | 5 | 10/28/2013 | 10/28/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2013 |  | 12/31/2013 | N | EXP | 42 |  |  | 0 | 0 | 0 | 1/27/2014 | 1/27/2014 | 2/6/2014 | Connected |  | N
National Grid | BROCKTON | 545337 | 02301 | 7.56 | Solar | 05_07_91W47 | 09/22/2023 | 09/25/2023 | 2 | 1 | 1 | 09/26/2023 | 09/26/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 09/22/2023 | 11/2/2024 | Y | EXP | 365 | 12/02/2023 | 01/19/2024 | 49 | 3 | 46 |  |  | 1/25/2024 | Connected |  | N
National Grid | WHITMAN | 175451 | 02382 | 480 | Solar | 05_09_604W1 | 07/21/2014 | 07/21/2014 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2014 | 08/01/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2014 | 07/21/2014 | 12/31/2016 | Y | STD | 74 |  |  | 0 | 0 | 0 | 11/30/2015 | 11/30/2015 | 12/22/2015 | Connected |  | N
National Grid | BARRE | 729320 | 01005 | 100 | Solar | 05_05_3424W5 | 12/29/2025 | 01/14/2026 | 12 | 3 | 9 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | FOXBOROUGH | 193913 | 02035 | 112.5 | Solar | 05_12_12L4 | 08/21/2018 | 08/29/2018 | 6 | 5 | 1 | 08/30/2018 | 08/30/2018 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2019 |  | 11/15/2019 | N | EXP | 256 |  |  | 0 | 0 | 0 |  |  | 12/17/2019 | Connected |  | N
National Grid | BEVERLY | 185136 | 01915 | 4980 | Solar | 05_05_320W2 | 05/21/2018 | 05/21/2018 | 34 | 29 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/11/2018 | 09/12/2018 | 45 | 15 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2019 | 05/21/2018 | 1/8/2024 | Y | STD | 71 | 08/12/2022 | 07/19/2023 | 342 | 174 | 168 |  |  | 12/14/2023 | Connected |  | N
National Grid | DOUGLAS | 176544 | 01516 | 10 | Solar | 05_07_797W42 | 03/31/2016 | 03/31/2016 | 2 | 2 | 0 | 04/05/2016 | 04/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 |  | 4/6/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/29/2016 | 9/29/2016 | 10/3/2016 | Connected |  | N
National Grid | BRIDGEWATER | 671376 | 02333 | 18.85 | Solar | 05_05_9L4 | 02/20/2025 | 04/23/2025 | 43 | 25 | 18 | 04/24/2025 | 04/24/2025 | 102 | 25 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 397143 | 02703 | 0 | Solar | 05_01_201W2 | 01/10/2022 | 01/13/2022 | 3 | 2 | 1 | 01/14/2022 | 01/14/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2022 |  | 5/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2023 | Connected |  | N
National Grid | AYER | 177768 | 01432 | 5000 | Solar | 05_09_501L2 | 10/06/2017 | 01/31/2018 | 77 | 70 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2018 | 02/22/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 175950 | 01082 | 2166 | Solar | 05_07_98W46 | 03/16/2015 | 03/16/2015 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 04/27/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2016 | 03/16/2015 | 8/31/2017 | Y | STD | 575 | 03/06/2017 | 08/15/2017 | 113 | 0 | 113 | 8/16/2017 | 8/16/2017 | 9/6/2017 | Connected |  | N
National Grid | BROCKTON | 566719 | 02301 | 7.6 | Solar | 05_07_91W47 | 11/09/2023 | 11/16/2023 | 4 | 1 | 3 | 11/17/2023 | 11/17/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2023 |  | 1/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2024 | Connected |  | N
National Grid | WHITMAN | 175580 | 02382 | 984 | Solar | 05_09_604W1 | 12/10/2014 | 12/10/2014 | 12 | 10 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2014 | 01/23/2015 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 741647 | 01005 | 11.5 | Solar | 05_05_3424W5 | 12/22/2025 | 12/26/2025 | 3 | 0 | 3 | 01/28/2026 | 01/28/2026 | 28 | 14 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FOXBOROUGH | 204469 | 02035 | 20 | Solar | 05_12_12L4 | 02/06/2019 | 03/18/2019 | 27 | 22 | 5 | 03/19/2019 | 03/19/2019 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2019 |  | 9/30/2019 | N | EXP | 171 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | BEVERLY | 185462 | 01915 | 15.2 | Solar | 05_05_320W2 | 05/22/2018 | 05/22/2018 | 11 | 8 | 3 | 06/14/2018 | 06/14/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 7/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2019 | Connected |  | N
National Grid | DOUGLAS | 176989 | 01516 | 7.6 | Solar | 05_07_797W42 | 03/10/2017 | 03/10/2017 | 5 | 3 | 2 | 03/17/2017 | 03/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 | 03/10/2017 | 3/15/2018 | Y | EXP | 359 | 08/22/2017 | 08/31/2017 | 7 | 0 | 7 | 1/29/2018 | 1/29/2018 | 2/7/2018 | Connected |  | N
National Grid | BRIDGEWATER | 673851 | 02324 | 3.19 | Solar | 05_05_9L4 | 02/24/2025 | 05/12/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 | 02/24/2025 | 7/24/2026 | Y | EXP | 365 | 08/02/2025 | 08/14/2025 | 13 | 0 | 13 |  |  | 9/4/2025 | Connected |  | N
National Grid | ATTLEBORO | 456305 | 02703 | 10 | Solar | 05_01_201W2 | 09/22/2022 | 09/30/2022 | 7 | 5 | 2 | 10/03/2022 | 10/03/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 |  | 1/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2023 | Connected |  | N
National Grid | AYER | 177973 | 01432 | 1500 | Solar | 05_09_501L2 | 06/27/2017 | 06/27/2017 | 152 | 151 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 176348 | 01037 | 225 | Solar | 05_07_98W46 | 02/26/2015 | 02/26/2015 | 5 | 0 | 5 | 03/09/2015 | 03/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2015 |  | 9/30/2015 | N | EXP | 184 |  |  | 0 | 0 | 0 | 4/1/2016 | 4/1/2016 | 4/1/2016 | Connected |  | N
National Grid | EASTON | 654977 | 02356 | 3.8 | Solar | 05_07_91W47 | 11/19/2024 | 01/03/2025 | 10 | 7 | 3 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 11/19/2024 | 3/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | WHITMAN | 175610 | 02382 | 480 | Solar | 05_09_604W1 | 12/15/2014 | 12/15/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 | 01/23/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 178777 | 01005 | 17.6 | Solar | 05_05_3424W5 | 12/09/2014 | 12/09/2014 | 4 | 2 | 2 | 12/16/2014 | 12/16/2014 | 409 | 0 | 409 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2014 |  | 2/28/2015 | N | EXP | 74 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 243349 | 02035 | 2000 | Solar | 05_12_12L4 | 07/29/2019 | 09/09/2019 | 29 | 24 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/10/2019 | 10/08/2019 | 21 | 17 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2021 | 07/29/2019 | 6/1/2023 | Y | STD | 367 | 09/28/2022 | 01/19/2023 | 114 | 0 | 114 |  |  | 5/31/2023 | Connected |  | N
National Grid | BEVERLY | 296412 | 01915 | 10 | Solar | 05_05_320W2 | 06/16/2020 | 06/18/2020 | 1 | 1 | 0 | 06/19/2020 | 06/19/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2020 | 06/16/2020 | 6/16/2021 | Y | EXP | 365 | 08/20/2020 | 09/15/2020 | 26 | 0 | 26 |  |  | 1/29/2021 | Connected |  | N
National Grid | DOUGLAS | 186427 | 01516 | 7.6 | Solar | 05_07_797W42 | 05/25/2018 | 05/25/2018 | 24 | 19 | 5 | 06/15/2018 | 06/15/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 669674 | 02333 | 0 | Other | 05_05_9L5 | 07/22/2025 | 08/26/2025 | 24 | 13 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2025 | 11/01/2025 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 472052 | 02703 | 18.816 | Solar | 05_01_201W2 | 10/27/2022 | 11/16/2022 | 14 | 13 | 1 | 11/17/2022 | 11/17/2022 | 27 | 15 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 | 10/27/2022 | 1/11/2024 | Y | EXP | 365 | 06/09/2023 | 08/10/2023 | 63 | 0 | 63 |  |  | 8/11/2023 | Connected |  | N
National Grid | HARVARD | 177997 | 01451 | 1610 | Solar | 05_09_501L2 | 10/25/2017 | 10/25/2017 | 51 | 51 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2018 | 02/14/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 176676 | 01082 | 5 | Solar | 05_07_98W46 | 01/04/2016 | 01/04/2016 | 1 | 1 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 | 01/04/2016 | 1/10/2017 | Y | EXP | 347 | 04/23/2017 | 05/05/2017 | 9 | 0 | 9 | 5/8/2017 | 5/8/2017 | 5/10/2017 | Connected |  | N
National Grid | EASTON | 659627 | 02356 | 6.175 | Solar | 05_07_91W47 | 12/10/2024 | 12/19/2024 | 5 | 0 | 5 | 12/20/2024 | 12/20/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | WHITMAN | 176782 | 02382 | 2000 | Solar | 05_09_604W1 | 11/05/2015 | 11/05/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/10/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 178787 | 01005 | 325 | Solar | 05_05_3424W5 | 11/24/2015 | 11/24/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2015 | 12/17/2015 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/29/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 243338 | 02035 | 842 | Solar | 05_12_12L4 | 09/13/2019 | 10/14/2019 | 20 | 16 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 | 10/29/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 | 09/13/2019 | 4/26/2023 | Y | STD | 26 | 02/17/2023 | 02/16/2023 | 0 | 0 | 0 | 4/4/2023 | 4/3/2023 | 5/23/2023 | Connected |  | N
National Grid | BEVERLY | 371684 | 01915 | 1000 | Solar | 05_05_320W2 | 10/15/2021 | 01/04/2022 | 55 | 46 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 11/22/2022 | 220 | 211 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 195864 | 01516 | 7.6 | Solar | 05_07_797W42 | 11/02/2018 | 11/14/2018 | 6 | 0 | 6 | 11/15/2018 | 11/15/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  | 11/13/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2020 | Connected |  | N
National Grid | BRIDGEWATER | 733030 | 02333 | 25.38 | Solar | 05_05_9L5 | 11/11/2025 | 11/12/2025 | 1 | 0 | 1 | 11/13/2025 | 11/13/2025 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATTLEBORO | 505820 | 02703 | 12.18 | Solar | 05_01_201W2 | 05/16/2023 | 05/18/2023 | 3 | 2 | 1 | 05/19/2023 | 05/19/2023 | 98 | 79 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2023 |  | 10/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2023 | Connected |  | N
National Grid | AYER | 177996 | 01432 | 1610 | Solar | 05_09_501L2 | 10/25/2017 | 10/25/2017 | 51 | 51 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2018 | 02/14/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 177764 | 01031 | 9.92 | Solar | 05_07_98W46 | 10/05/2017 | 10/05/2017 | 25 | 25 | 0 | 11/21/2017 | 11/21/2017 | 92 | 0 | 92 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 10/11/2018 | N | EXP | 318 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N
National Grid | EASTON | 487773 | 02356 | 1680 | Solar | 05_07_91W48 | 02/28/2023 | 03/14/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/15/2023 | 04/11/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/28/2023 | 12/2/2026 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WHITMAN | 176886 | 02382 | 17.25 | Solar | 05_09_604W1 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 286 | 0 | 286 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2015 |  | 11/18/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 328991 | 01005 | 7.6 | Solar | 05_05_3424W5 | 01/08/2021 | 01/14/2021 | 4 | 4 | 0 | 01/15/2021 | 01/15/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2021 |  | 1/14/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 257220 | 01915 | 33.3 | Solar | 05_12_12L4 | 10/02/2019 | 10/17/2019 | 9 | 5 | 4 | 10/18/2019 | 10/18/2019 | 7 | 0 | 7 | 11/08/2019 | 08/18/2020 | 185 | 58 | 127 |  |  | 0 | 0 | 0 |  | 08/18/2020 | 185 | 58 | 127 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 398313 | 01915 | 9.772 | Solar | 05_05_320W2 | 12/03/2021 | 12/07/2021 | 3 | 1 | 2 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  | 1/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2022 | Connected |  | N
National Grid | DOUGLAS | 192138 | 01516 | 4975 | Solar | 05_07_797W42 | 09/20/2018 | 10/01/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 11/08/2018 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2020 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 174239 | 02333 | 500 | Solar | 05_05_9L5 | 02/17/2012 | 02/17/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 537240 | 02703 | 7.25 | Solar | 05_01_201W2 | 06/29/2023 | 07/05/2023 | 4 | 3 | 1 | 07/06/2023 | 07/06/2023 | 110 | 97 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2023 |  | 12/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | HARVARD | 178030 | 01451 | 4998 | Solar | 05_09_501L2 | 09/01/2017 | 09/01/2017 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2017 | 10/12/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/9/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 178505 | 01037 | 9.92 | Solar | 05_07_98W46 | 01/24/2018 | 01/24/2018 | 20 | 10 | 10 | 02/23/2018 | 02/23/2018 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2018 | 01/24/2018 | 10/31/2019 | Y | EXP | 577 |  |  | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | EASTON | 693870 | 02356 | 7.6 | Solar | 05_07_91W48 | 09/12/2025 | 09/29/2025 | 3 | 0 | 3 | 10/21/2025 | 10/21/2025 | 36 | 20 | 16 | 01/06/2026 | 02/04/2026 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  | 02/04/2026 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 2/9/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WHITMAN | 177809 | 02382 | 50 | Solar | 05_09_604W1 | 10/12/2017 | 10/12/2017 | 10 | 0 | 10 | 10/27/2017 | 10/27/2017 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2018 |  | 10/18/2018 | N | EXP | 255 |  |  | 0 | 0 | 0 |  |  | 8/27/2018 | Connected |  | N
National Grid | BARRE | 421144 | 01005 | 0 | Solar | 05_05_3424W5 | 03/31/2022 | 04/04/2022 | 2 | 0 | 2 | 04/05/2022 | 04/05/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 298302 | 02035 | 390 | Solar | 05_12_12L4 | 07/17/2020 | 10/16/2020 | 63 | 25 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2020 | 10/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 470299 | 01915 | 8.12 | Solar | 05_05_320W2 | 11/10/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 |  | 12/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | DOUGLAS | 191425 | 01516 | 10 | Solar | 05_07_797W42 | 08/01/2018 | 09/18/2018 | 24 | 13 | 11 | 09/19/2018 | 09/19/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 | 08/01/2018 | 9/27/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2019 | Connected |  | N
National Grid | BRIDGEWATER | 175148 | 02333 | 50 | Solar | 05_05_9L5 | 10/25/2013 | 10/25/2013 | 6 | 0 | 6 | 11/04/2013 | 11/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2013 |  | 12/31/2013 | N | EXP | 48 |  |  | 0 | 0 | 0 | 1/24/2014 | 1/24/2014 | 1/24/2014 | Connected |  | N
National Grid | SEEKONK | 564591 | 02771 | 44.6 | Solar | 05_01_201W2 | 10/24/2023 | 10/25/2023 | 1 | 0 | 1 | 10/26/2023 | 10/26/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 10/24/2023 |  | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | AYER | 178050 | 01432 | 6740 | Solar | 05_09_501L2 | 06/29/2017 | 08/09/2017 | 27 | 27 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2017 | 09/01/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2018 |  | 7/5/2018 | N | STD | 54 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 234807 | 01037 | 10 | Solar | 05_07_98W46 | 07/30/2019 | 07/31/2019 | 0 | 0 | 0 | 08/01/2019 | 08/01/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 | 07/30/2019 | 7/19/2023 | Y | EXP | 365 | 01/12/2021 | 01/25/2021 | 13 | 0 | 13 |  |  | 1/7/2023 | Connected |  | N
National Grid | BROCKTON | 717839 | 02301 | 21.66 | Solar | 05_07_91W48 | 09/25/2025 | 10/20/2025 | 16 | 12 | 4 | 10/21/2025 | 10/21/2025 | 85 | 76 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WHITMAN | 178292 | 02382 | 14.2 | Solar | 05_09_604W1 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 | 05/23/2018 | 05/23/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  | 11/19/2018 | N | EXP | 69 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 447463 | 01005 | 7.6 | Solar | 05_05_3424W5 | 08/04/2022 | 08/09/2022 | 3 | 0 | 3 | 08/10/2022 | 08/10/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 |  | 10/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2023 | Connected |  | Y
National Grid | FOXBOROUGH | 316425 | 02035 | 0 | Other | 05_12_12L4 | 10/07/2020 | 10/19/2020 | 6 | 0 | 6 | 10/20/2020 | 10/20/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | Connected |  | N
National Grid | BEVERLY | 475577 | 01915 | 15.2 | Solar | 05_05_320W2 | 11/08/2022 | 11/09/2022 | 1 | 0 | 1 | 11/10/2022 | 11/10/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 1/16/2024 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 201018 | 01516 | 7.6 | Solar | 05_07_797W42 | 11/12/2018 | 11/16/2018 | 3 | 1 | 2 | 11/19/2018 | 11/19/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 |  | 11/29/2019 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N
National Grid | EAST BRIDGEWATER | 175210 | 02333 | 285 | Solar | 05_05_9L5 | 12/05/2012 | 12/05/2012 | 6 | 0 | 6 | 12/17/2012 | 12/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2013 | 12/05/2012 | 5/15/2013 | Y | EXP | 9 | 06/07/2013 | 07/31/2013 | 36 | 0 | 36 | 2/15/2013 | 2/15/2013 | 9/23/2013 | Connected |  | N
National Grid | REHOBOTH | 567774 | 02769 | 23 | Solar | 05_01_201W2 | 11/01/2023 | 05/10/2024 | 131 | 128 | 3 | 05/13/2024 | 05/13/2024 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 11/01/2023 | 6/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | HARVARD | 178059 | 01451 | 3000 | Solar | 05_09_501L2 | 09/01/2017 | 09/22/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2017 | 10/17/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2018 | 09/01/2017 | 7/8/2021 | Y | STD | 839 | 05/29/2020 | 03/29/2021 | 304 | 88 | 216 |  |  | 7/8/2021 | Connected |  | N
National Grid | HARDWICK | 251819 | 01037 | 7.6 | Solar | 05_07_98W46 | 10/14/2019 | 10/21/2019 | 4 | 0 | 4 | 10/22/2019 | 10/22/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 | 10/14/2019 | 3/29/2021 | Y | EXP | 365 | 08/10/2021 | 08/10/2021 | 0 | 0 | 0 |  |  | 2/7/2022 | Connected |  | N
National Grid | BROCKTON | 174784 | 02301 | 180 | Solar | 05_07_91W48 | 07/17/2013 | 07/17/2013 | 5 | 0 | 5 | 07/25/2013 | 07/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2013 | 07/17/2013 | 7/30/2014 | Y | EXP | 355 | 04/23/2014 | 06/26/2014 | 44 | 0 | 44 | 7/17/2014 | 7/17/2014 | 7/23/2014 | Connected |  | N
National Grid | BROCKTON | 178434 | 02301 | 636 | Solar | 05_09_604W1 | 03/05/2018 | 03/05/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 654103 | 01005 | 4.8 | Solar | 05_05_3424W5 | 11/13/2024 | 11/25/2024 | 4 | 0 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 11/13/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | FOXBOROUGH | 325853 | 02035 | 33.3 | Solar | 05_12_12L4 | 11/19/2020 | 12/05/2020 | 10 | 8 | 2 | 12/07/2020 | 12/07/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/27/2021 | Connected |  | N
National Grid | BEVERLY | 568589 | 01915 | 46 | Solar | 05_05_320W2 | 11/03/2023 | 11/14/2023 | 7 | 5 | 2 | 11/15/2023 | 11/15/2023 | 104 | 87 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 5/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | DOUGLAS | 206156 | 01516 | 3.8 | Solar | 05_07_797W42 | 04/17/2019 | 06/18/2019 | 42 | 40 | 2 | 06/19/2019 | 06/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 175554 | 02333 | 750 | Solar | 05_05_9L5 | 04/16/2014 | 04/16/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 06/17/2014 | 07/31/2014 | 30 | 0 | 30 | 04/25/2014 | 05/22/2014 | 19 | 0 | 19 |  | 07/31/2014 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 10/27/2014 |  | 12/31/2014 | N | STD | 65 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 4/3/2015 | Connected |  | N
National Grid | SEEKONK | 581647 | 02771 | 7.83 | Solar | 05_01_201W2 | 01/09/2024 | 01/16/2024 | 5 | 1 | 4 | 01/17/2024 | 01/17/2024 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | HARVARD | 178170 | 01451 | 1746 | Solar | 05_09_501L2 | 03/23/2018 | 04/18/2018 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/09/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 293451 | 01082 | 1.92 | Solar | 05_07_98W46 | 06/01/2020 | 06/04/2020 | 2 | 0 | 2 | 06/05/2020 | 06/05/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 175498 | 02301 | 990 | Solar | 05_07_91W48 | 09/26/2014 | 09/26/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2014 | 10/31/2014 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 178746 | 02302 | 990 | Solar | 05_09_604W1 | 08/02/2018 | 08/10/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/13/2018 | 09/05/2018 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/24/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PETERSHAM | 698435 | 01366 | 10 | Solar | 05_05_3424W5 | 06/13/2025 | 07/23/2025 | 3 | 0 | 3 | 08/08/2025 | 08/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2025 | Connected |  | N
National Grid | FOXBOROUGH | 411748 | 02035 | 0 | Battery Add-On | 05_12_12L4 | 03/14/2022 | 03/28/2022 | 10 | 0 | 10 | 03/29/2022 | 03/29/2022 | 39 | 19 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2022 |  | 11/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2023 | Connected |  | N
National Grid | BEVERLY | 604715 | 01915 | 8.376 | Solar | 05_05_320W2 | 04/17/2024 | 05/06/2024 | 1 | 0 | 1 | 05/07/2024 | 05/07/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 |  | 5/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | DOUGLAS | 210891 | 01516 | 10 | Solar | 05_07_797W42 | 02/21/2019 | 03/05/2019 | 7 | 0 | 7 | 03/06/2019 | 03/06/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  | 4/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2019 | Connected |  | N
National Grid | BRIDGEWATER | 175800 | 02333 | 990 | Solar | 05_05_9L5 | 02/27/2015 | 02/27/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/08/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 593191 | 02703 | 15.2 | Solar | 05_01_201W2 | 02/29/2024 | 03/06/2024 | 4 | 0 | 4 | 03/07/2024 | 03/07/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 |  | 7/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | HARVARD | 178396 | 01451 | 19.2 | Solar | 05_09_501L2 | 03/04/2018 | 03/04/2018 | 1 | 1 | 0 | 03/20/2018 | 03/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2018 |  | 3/11/2019 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 7/27/2018 | Connected |  | N
National Grid | BARRE | 308244 | 01005 | 1.92 | Solar | 05_07_98W46 | 09/15/2020 | 09/21/2020 | 3 | 0 | 3 | 09/22/2020 | 09/22/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 |  | 9/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 177759 | 02301 | 648 | Solar | 05_07_91W48 | 08/02/2017 | 08/02/2017 | 69 | 69 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/01/2017 | 12/18/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 08/02/2017 | 2/1/2020 | Y | STD | 523 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 235906 | 02302 | 17.28 | Solar | 05_09_604W1 | 06/12/2019 | 06/21/2019 | 6 | 2 | 4 | 06/27/2019 | 06/27/2019 | 20 | 12 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 |  | 7/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2019 | Connected |  | N
National Grid | PETERSHAM | 721653 | 01366 | 498 | Solar | 05_05_3431W1 | 11/12/2025 | 12/08/2025 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/09/2025 | 01/07/2026 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FOXBOROUGH | 513872 | 02035 |  | Other | 05_12_12L4 | 07/13/2023 | 10/02/2023 | 57 | 47 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2023 | 11/28/2023 | 38 | 15 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 620732 | 01915 | 7.68 | Solar | 05_05_320W2 | 06/26/2024 | 07/12/2024 | 1 | 0 | 1 | 07/15/2024 | 07/15/2024 | 28 | 14 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | DOUGLAS | 290149 | 01516 | 996 | Solar | 05_07_797W42 | 05/18/2020 | 06/23/2020 | 24 | 17 | 7 |  |  | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 175883 | 02333 | 150 | Solar | 05_05_9L5 | 05/22/2015 | 05/22/2015 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2015 | 06/30/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2015 | 05/22/2015 | 10/30/2016 | Y | STD | 334 | 08/11/2016 | 10/19/2016 | 47 | 0 | 47 | 10/31/2016 | 10/31/2016 | 11/8/2016 | Connected |  | N
National Grid | ATTLEBORO | 597435 | 02703 | 23 | Solar | 05_01_201W2 | 03/18/2024 | 03/27/2024 | 8 | 6 | 2 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 5/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | HARVARD | 178619 | 01451 | 7.6 | Solar | 05_09_501L2 | 01/31/2018 | 03/07/2018 | 20 | 0 | 20 | 03/07/2018 | 03/07/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2018 | 01/31/2018 | 6/17/2019 | Y | EXP | 466 | 03/07/2019 | 03/06/2019 | 0 | 0 | 0 |  |  | 5/17/2019 | Connected |  | N
National Grid | WARE | 325302 | 01082 | 7.6 | Solar | 05_07_98W46 | 12/08/2020 | 12/13/2020 | 3 | 0 | 3 | 12/14/2020 | 12/14/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 |  | 5/23/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 177826 | 02301 | 60 | Solar | 05_07_91W48 | 06/08/2017 | 06/08/2017 | 3 | 3 | 0 | 06/13/2017 | 06/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2017 |  | 6/13/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/25/2017 | 8/25/2017 | 9/8/2017 | Connected |  | N
National Grid | BROCKTON | 291503 | 02301 | 20 | Solar | 05_09_604W1 | 05/18/2020 | 06/02/2020 | 9 | 9 | 0 | 06/03/2020 | 06/03/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/18/2020 | 5/4/2022 | Y | EXP | 4 | 03/13/2021 | 03/24/2021 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Y
National Grid | PETERSHAM | 178788 | 01366 | 32.8 | Solar | 05_05_3431W1 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 | 05/11/2016 | 05/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2016 | 05/10/2016 | 5/16/2017 | Y | EXP | 35 | 12/05/2016 | 01/05/2017 | 21 | 0 | 21 | 2/14/2017 | 2/14/2017 | 2/14/2017 | Connected |  | N
National Grid | FOXBOROUGH | 590972 | 02035 | 75 | Solar | 05_12_12L4 | 02/19/2024 |  | 59 | 51 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 630622 | 01915 | 8.12 | Solar | 05_05_320W2 | 08/07/2024 | 08/15/2024 | 2 | 1 | 1 | 08/16/2024 | 08/16/2024 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/07/2024 | 9/4/2025 | Y | EXP | 365 | 02/28/2025 | 03/04/2025 | 5 | 0 | 5 |  |  | 3/6/2025 | Connected |  | N
National Grid | DOUGLAS | 353508 | 01516 | 498 | Solar | 05_07_797W42 | 06/23/2021 | 09/08/2021 | 53 | 44 | 9 |  |  | 60 | 17 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 177549 | 02333 | 7.6 | Solar | 05_05_9L5 | 05/15/2017 | 05/15/2017 | 6 | 5 | 1 | 05/24/2017 | 05/24/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2017 |  | 5/21/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 2/15/2018 | 2/15/2018 | 2/15/2018 | Connected |  | N
National Grid | ATTLEBORO | 630200 | 02703 | 22.8 | Solar | 05_01_201W2 | 08/05/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 25 | 7 | 18 | 12/12/2024 | 04/28/2025 | 93 | 16 | 77 |  |  | 0 | 0 | 0 |  | 04/28/2025 | 93 | 16 | 77 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 1/21/2027 | N | EXP | 365 | 11/07/2025 | 12/22/2025 | 46 | 0 | 46 |  |  | 12/9/2025 | Connected |  | N
National Grid | AYER | 178606 | 01432 | 10 | Solar | 05_09_501L2 | 12/12/2017 | 12/13/2017 | 77 | 61 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/18/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 333382 | 01082 | 9.6 | Solar | 05_07_98W46 | 05/06/2021 | 05/06/2021 | 0 | 0 | 0 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2021 |  | 7/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2022 | Connected |  | N
National Grid | BROCKTON | 244132 | 02301 | 999 | Solar | 05_07_91W48 | 09/17/2019 | 10/04/2019 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2019 | 01/15/2020 | 68 | 49 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2021 | 09/17/2019 | 2/24/2023 | Y | STD | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 298629 | 02301 | 9.36 | Solar | 05_09_604W1 | 07/31/2020 | 08/03/2020 | 0 | 0 | 0 | 08/04/2020 | 08/04/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 |  | 8/2/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PETERSHAM | 285186 | 01366 | 9.57 | Solar | 05_05_3431W1 | 03/25/2020 | 03/26/2020 | 1 | 1 | 0 | 03/27/2020 | 03/27/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2020 |  | 3/25/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | FOXBOROUGH | 608526 | 02035 | 2.9 | Solar | 05_12_12L4 | 05/03/2024 | 05/28/2024 | 11 | 10 | 1 | 05/29/2024 | 05/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/03/2024 | 6/24/2025 | Y | EXP | 365 | 08/20/2024 | 09/07/2024 | 19 | 0 | 19 |  |  | 9/10/2024 | Connected |  | N
National Grid | BEVERLY | 632483 | 01915 | 10 | Solar | 05_05_320W2 | 08/13/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 | 08/13/2024 | 9/20/2025 | Y | EXP | 365 | 11/13/2024 | 12/05/2024 | 22 | 0 | 22 |  |  | 12/20/2024 | Connected |  | N
National Grid | DOUGLAS | 358173 | 01516 | 9.6 | Solar | 05_07_797W42 | 05/14/2021 | 05/19/2021 | 3 | 3 | 0 | 05/20/2021 | 05/20/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2021 |  | 1/11/2023 | N | EXP | 534 |  |  | 0 | 0 | 0 |  |  | 1/19/2023 | Connected |  | N
National Grid | BRIDGEWATER | 177769 | 02333 | 10 | Solar | 05_05_9L5 | 10/09/2017 | 10/09/2017 | 14 | 14 | 0 | 10/31/2017 | 10/31/2017 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2017 |  | 10/15/2018 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 650502 | 02769 | 0 | Solar | 05_01_201W2 | 10/29/2024 | 10/31/2024 | 2 | 0 | 2 | 11/01/2024 | 11/01/2024 | 71 | 47 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2025 | Connected |  | N
National Grid | HARVARD | 188725 | 01451 | 15.2 | Solar | 05_09_501L2 | 06/20/2018 | 06/20/2018 | 4 | 0 | 4 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 |  | 9/20/2019 | N | EXP | 38 |  |  | 0 | 0 | 0 |  |  | 9/3/2019 | Connected |  | N
National Grid | WARE | 342718 | 01082 | 10 | Solar | 05_07_98W46 | 05/27/2021 | 06/03/2021 | 3 | 0 | 3 | 06/04/2021 | 06/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 246170 | 02301 | 10 | Solar | 05_07_91W48 | 09/12/2019 | 11/12/2019 | 40 | 40 | 0 | 11/13/2019 | 11/13/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2019 | 09/12/2019 | 9/12/2020 | Y | EXP | 365 | 02/14/2020 | 03/02/2020 | 17 | 0 | 17 |  |  | 8/11/2020 | Connected |  | N
National Grid | BROCKTON | 330336 | 02302 | 7.6 | Solar | 05_09_604W1 | 01/18/2021 | 01/28/2021 | 8 | 5 | 3 | 01/29/2021 | 01/29/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/18/2021 | 1/27/2022 | Y | EXP | 365 | 04/21/2021 | 05/12/2021 | 21 | 0 | 21 |  |  | 5/13/2021 | Connected |  | N
National Grid | PETERSHAM | 337152 | 01366 | 250 | Solar | 05_05_3431W1 | 01/28/2021 | 02/03/2021 | 3 | 0 | 3 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 621340 | 02035 | 90 | Solar | 05_12_12L4 | 06/28/2024 | 08/15/2024 | 33 | 24 | 9 | 08/16/2024 | 08/16/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 4/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | BEVERLY | 663343 | 01915 | 10 | Solar | 05_05_320W2 | 01/02/2025 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N
National Grid | DOUGLAS | 473695 | 01516 | 6 | Solar | 05_07_797W42 | 02/17/2023 | 02/21/2023 | 1 | 0 | 1 | 02/22/2023 | 02/22/2023 | 33 | 10 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 | 02/17/2023 | 9/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2024 | Connected |  | N
National Grid | EAST BRIDGEWATER | 177791 | 02333 | 612 | Solar | 05_05_9L5 | 08/02/2017 | 08/02/2017 | 126 | 126 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/8/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 653155 | 02771 | 9.75 | Solar | 05_01_201W2 | 11/08/2024 | 12/03/2024 | 1 | 0 | 1 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 11/08/2024 | 1/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 191405 | 01451 | 1746 | Solar | 05_09_501L2 | 12/14/2018 | 01/30/2019 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2019 | 02/26/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 352007 | 01082 | 10 | Solar | 05_07_98W46 | 04/29/2021 | 05/06/2021 | 4 | 0 | 4 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  | 1/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2021 | Connected |  | N
National Grid | BROCKTON | 451320 | 02301 | 3.8 | Solar | 05_07_91W48 | 08/26/2022 |  | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 370720 | 02302 | 7.68 | Solar | 05_09_604W1 | 07/19/2021 | 07/21/2021 | 3 | 2 | 1 | 07/22/2021 | 07/22/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2021 | 07/19/2021 | 5/7/2023 | Y | EXP | 365 | 12/02/2021 | 04/29/2022 | 149 | 0 | 149 |  |  | 5/16/2022 | Connected |  | N
National Grid | BARRE | 405822 | 01005 | 0 | Battery Add-On | 05_05_3431W1 | 01/24/2022 | 01/31/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 02/04/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 644325 | 02035 | 10 | Solar | 05_12_12L4 | 10/02/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/02/2024 | 12/12/2025 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 668016 | 01915 | 15.2 | Solar | 05_05_320W2 | 01/27/2025 | 02/19/2025 | 1 | 0 | 1 | 03/28/2025 | 03/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | DOUGLAS | 515597 | 01516 | 10 | Solar | 05_07_797W42 | 04/04/2023 | 04/21/2023 | 13 | 12 | 1 | 04/24/2023 | 04/24/2023 | 158 | 137 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2024 |  | 9/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | EAST BRIDGEWATER | 177821 | 02333 | 300 | Natural Gas | 05_05_9L5 | 06/05/2017 | 06/05/2017 | 6 | 6 | 0 | 06/15/2017 | 06/15/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2017 |  | 2/28/2018 | N | EXP | 233 |  |  | 0 | 0 | 0 | 3/22/2018 | 3/22/2018 | 3/29/2018 | Connected |  | N
National Grid | SEEKONK | 656060 | 02771 | 9.423 | Solar | 05_01_201W2 | 11/21/2024 | 01/13/2025 | 4 | 0 | 4 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | HARVARD | 191403 | 01451 | 2200 | Solar | 05_09_501L2 | 12/14/2018 | 01/30/2019 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2019 | 02/25/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 378903 | 01082 | 9.8 | Solar | 05_07_98W46 | 09/15/2021 | 09/16/2021 | 1 | 0 | 1 | 09/17/2021 | 09/17/2021 | 33 | 10 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2021 |  | 9/16/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 475340 | 02301 | 250 | Solar | 05_07_91W48 | 10/31/2023 |  | 92 | 27 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 436738 | 02302 | 1.74 | Solar | 05_09_604W1 | 07/01/2022 | 07/12/2022 | 6 | 3 | 3 | 07/13/2022 | 07/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 | 07/01/2022 | 8/8/2024 | Y | EXP | 365 | 03/07/2023 | 08/02/2023 | 149 | 0 | 149 |  |  | 7/17/2024 | Connected |  | N
National Grid | PETERSHAM | 439470 | 01366 | 240 | Solar | 05_05_3431W1 | 08/01/2022 | 08/16/2022 | 12 | 3 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 674470 | 02035 | 50 | Solar | 05_12_12L4 | 03/03/2025 | 03/13/2025 | 8 | 4 | 4 | 03/14/2025 | 03/14/2025 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2026 | Connected |  | Y
National Grid | BEVERLY | 673567 | 01915 | 0 | Battery Add-On | 05_05_320W2 | 02/21/2025 | 03/10/2025 | 12 | 7 | 5 | 03/11/2025 | 03/11/2025 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 9/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2026 | Connected |  | N
National Grid | DOUGLAS | 536248 | 01516 | 15.2 | Solar | 05_07_797W42 | 06/26/2023 | 06/27/2023 | 2 | 1 | 1 | 06/28/2023 | 06/28/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2023 | Connected |  | N
National Grid | BRIDGEWATER | 178187 | 02333 | 15.2 | Solar | 05_05_9L5 | 04/13/2018 | 04/13/2018 | 13 | 0 | 13 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 |  | 4/21/2019 | N | EXP | 333 |  |  | 0 | 0 | 0 |  |  | 8/14/2019 | Connected |  | N
National Grid | SEEKONK | 671328 | 02771 | 0 | Battery Add-On | 05_01_201W2 | 02/11/2025 | 02/14/2025 | 3 | 0 | 3 | 02/18/2025 | 02/18/2025 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  | 6/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | AYER | 191401 | 01432 | 1371 | Solar | 05_09_501L2 | 01/09/2019 | 01/28/2019 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2019 | 02/20/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 381609 | 01082 | 9.8 | Solar | 05_07_98W46 | 09/23/2021 | 12/29/2021 | 4 | 0 | 4 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 | 09/23/2021 |  | Y | EXP |  | 04/23/2022 | 04/25/2022 | 3 | 0 | 3 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 476961 | 02301 | 10 | Solar | 05_07_91W48 | 01/26/2023 | 01/30/2023 | 2 | 0 | 2 | 01/31/2023 | 01/31/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2023 | 01/26/2023 | 6/23/2024 | Y | EXP | 365 | 06/22/2023 | 06/21/2023 | 0 | 0 | 0 |  |  | 7/17/2024 | Connected |  | N
National Grid | BROCKTON | 466768 | 02302 | 3.8 | Solar | 05_09_604W1 | 10/17/2022 | 10/18/2022 | 1 | 0 | 1 | 10/19/2022 | 10/19/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2022 |  | 11/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2022 | Connected |  | N
National Grid | PETERSHAM | 586635 | 01366 | 1500 | Solar | 05_05_3431W1 | 09/05/2024 |  | 68 | 58 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 174665 | 02035 | 230 | Solar | 05_12_12L6 | 12/12/2012 | 12/12/2012 | 8 | 0 | 8 | 12/27/2012 | 12/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2013 | 12/12/2012 | 4/30/2013 | Y | EXP | 55 |  |  | 0 | 0 | 0 | 8/7/2013 | 8/7/2013 | 8/15/2013 | Connected |  | N
National Grid | BEVERLY | 685525 | 01915 | 3.8 | Solar | 05_05_320W2 | 04/16/2025 | 06/06/2025 | 34 | 24 | 10 | 06/09/2025 | 06/09/2025 | 35 | 22 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | DOUGLAS | 567311 | 01516 | 10 | Solar | 05_07_797W42 | 11/16/2023 | 11/17/2023 | 1 | 0 | 1 | 11/20/2023 | 11/20/2023 | 29 | 6 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2024 | 11/16/2023 | 1/18/2025 | Y | EXP | 365 | 03/29/2024 | 04/30/2024 | 33 | 0 | 33 |  |  | 5/3/2024 | Connected |  | N
National Grid | BROCKTON | 178321 | 02302 | 612 | Solar | 05_05_9L5 | 08/02/2017 | 08/02/2017 | 126 | 0 | 126 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2018 | 03/29/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/3/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 674076 | 02703 | 6.84 | Solar | 05_01_201W2 | 02/28/2025 | 03/10/2025 | 6 | 2 | 4 | 03/11/2025 | 03/11/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | HARVARD | 191399 | 01451 | 996 | Solar | 05_09_501L2 | 01/04/2019 | 01/29/2019 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/30/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 386273 | 01082 | 15.2 | Solar | 05_07_98W46 | 04/05/2022 | 04/20/2022 | 11 | 10 | 1 | 04/21/2022 | 04/21/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2022 |  | 5/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2022 | Connected |  | N
National Grid | BROCKTON | 558519 | 02301 | 5.67 | Solar | 05_07_91W48 | 09/26/2023 | 10/06/2023 | 8 | 5 | 3 | 05/29/2024 | 05/29/2024 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 | 09/26/2023 | 10/26/2025 | Y | EXP | 365 | 12/19/2024 | 03/31/2025 | 102 | 0 | 102 |  |  | 5/29/2025 | Connected |  | N
National Grid | BROCKTON | 498809 | 02301 | 7.6 | Solar | 05_09_604W1 | 02/21/2023 | 02/23/2023 | 2 | 0 | 2 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 | 02/21/2023 | 7/5/2024 | Y | EXP | 365 | 08/16/2023 | 11/01/2023 | 78 | 0 | 78 |  |  | 11/23/2023 | Connected |  | N
National Grid | BARRE | 638486 | 01005 | 11.4 | Solar | 05_05_3431W1 | 09/10/2024 | 09/16/2024 | 4 | 2 | 2 | 09/17/2024 | 09/17/2024 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 174664 | 02035 | 110 | Solar | 05_12_12L6 | 12/12/2012 | 12/12/2012 | 8 | 0 | 8 | 12/27/2012 | 12/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2013 | 12/12/2012 | 4/30/2013 | Y | EXP | 55 |  |  | 0 | 0 | 0 | 8/7/2013 | 8/7/2013 | 8/15/2013 | Connected |  | N
National Grid | BEVERLY | 690252 | 01915 | 15.2 | Solar | 05_05_320W2 | 05/07/2025 | 05/14/2025 | 5 | 1 | 4 | 05/15/2025 | 05/15/2025 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | DOUGLAS | 598236 | 01516 | 10 | Solar | 05_07_797W42 | 04/15/2024 | 04/19/2024 | 4 | 0 | 4 | 04/22/2024 | 04/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 |  | 5/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2024 | Connected |  | N
National Grid | BROCKTON | 292469 | 02302 | 0 | Solar | 05_05_9L5 | 05/20/2020 | 12/23/2021 | 2 | 0 | 2 | 05/27/2020 | 05/27/2020 | 69 | 50 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2020 | 05/20/2020 | 10/12/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 685431 | 02703 | 9.423 | Solar | 05_01_201W2 | 04/23/2025 | 04/30/2025 | 5 | 1 | 4 | 05/01/2025 | 05/01/2025 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | HARVARD | 197527 | 01451 | 4998 | Solar | 05_09_501L2 | 11/13/2018 | 11/30/2018 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 12/28/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 402370 | 01082 | 9.8 | Solar | 05_07_98W46 | 12/23/2021 | 12/29/2021 | 4 | 0 | 4 | 12/30/2021 | 12/30/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 | 12/23/2021 | 4/12/2023 | Y | EXP | 365 | 03/19/2022 | 04/11/2022 | 24 | 0 | 24 |  |  | 8/9/2022 | Connected |  | N
National Grid | BROCKTON | 536961 | 02301 | 10 | Solar | 05_07_91W48 | 06/27/2023 | 07/10/2023 | 2 | 0 | 2 | 07/11/2023 | 07/11/2023 | 77 | 59 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 06/27/2023 | 12/6/2024 | Y | EXP | 365 | 02/02/2024 | 02/12/2024 | 11 | 0 | 11 |  |  | 6/26/2024 | Connected |  | N
National Grid | BROCKTON | 565348 | 02301 | 1999.2 | Solar | 05_09_604W1 | 10/30/2023 | 01/30/2024 | 61 | 53 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2024 | 02/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 |  | 6/3/2025 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | PETERSHAM | 686861 | 01366 | 15.96 | Solar | 05_05_3431W1 | 04/23/2025 | 05/09/2025 | 6 | 1 | 5 | 09/26/2025 | 09/26/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2025 | Connected |  | N
National Grid | FOXBOROUGH | 177018 | 02035 | 60 | Solar | 05_12_12L6 | 01/09/2017 | 01/09/2017 | 4 | 4 | 0 | 01/13/2017 | 01/13/2017 | 37 | 37 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2017 |  | 8/1/2018 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 706306 | 01915 | 11.5 | Solar | 05_05_320W2 | 07/21/2025 | 09/25/2025 | 2 | 0 | 2 | 09/26/2025 | 09/26/2025 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2026 | Connected |  | N
National Grid | DOUGLAS | 600629 | 01516 | 9.8 | Solar | 05_07_797W42 | 04/12/2024 | 05/20/2024 | 0 | 0 | 0 | 07/16/2024 | 07/16/2024 | 145 | 45 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 372331 | 02333 | 11.02 | Solar | 05_05_9L5 | 08/04/2021 | 08/09/2021 | 10 | 6 | 4 | 08/19/2021 | 08/19/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  | 10/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 692599 | 02771 | 7.678 | Solar | 05_01_201W2 | 05/19/2025 | 05/22/2025 | 3 | 0 | 3 | 05/23/2025 | 05/23/2025 | 34 | 13 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 200896 | 01432 | 4998 | Solar | 05_09_501L2 | 11/12/2018 | 11/30/2018 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 12/29/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 436238 | 01082 | 10 | Solar | 05_07_98W46 | 06/14/2022 | 06/15/2022 | 2 | 1 | 1 | 06/16/2022 | 06/16/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 |  | 7/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2022 | Connected |  | N
National Grid | BROCKTON | 550852 | 02301 | 8.99 | Solar | 05_07_91W48 | 08/25/2023 | 08/29/2023 | 2 | 0 | 2 | 08/30/2023 | 08/30/2023 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 599337 | 02301 | 14.8 | Solar | 05_09_604W1 | 04/17/2024 | 04/22/2024 | 4 | 1 | 3 | 04/23/2024 | 04/23/2024 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 | 04/17/2024 | 6/10/2025 | Y | EXP | 365 | 09/27/2024 | 10/29/2024 | 33 | 0 | 33 |  |  | 10/31/2024 | Connected |  | N
National Grid | PETERSHAM | 178802 | 01366 | 4680 | Solar | 05_05_3432W1 | 01/15/2018 | 01/15/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2018 | 03/09/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2018 |  | 8/10/2020 | N | STD | 665 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 177117 | 02035 | 360 | Solar | 05_12_12L6 | 10/19/2016 | 10/19/2016 | 4 | 4 | 0 | 10/26/2016 | 10/26/2016 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 707731 | 01915 | 10 | Solar | 05_05_320W2 | 07/28/2025 | 08/13/2025 | 11 | 8 | 3 | 08/14/2025 | 08/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2025 | Connected |  | N
National Grid | DOUGLAS | 680697 | 01516 | 10 | Solar | 05_07_797W42 | 03/26/2025 | 04/04/2025 | 2 | 0 | 2 | 04/14/2025 | 04/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 | 03/26/2025 | 6/2/2026 | Y | EXP | 365 | 09/13/2025 | 09/12/2025 | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | BROCKTON | 392829 | 02302 | 10 | Solar | 05_05_9L5 | 12/09/2021 | 01/07/2022 | 5 | 1 | 4 | 12/17/2021 | 12/17/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 | 12/09/2021 | 5/9/2023 | Y | EXP | 365 | 05/03/2022 | 05/06/2022 | 4 | 0 | 4 |  |  | 6/8/2022 | Connected |  | N
National Grid | ATTLEBORO | 693842 | 02703 | 10 | Solar | 05_01_201W2 | 05/23/2025 | 05/27/2025 | 1 | 0 | 1 | 05/28/2025 | 05/28/2025 | 107 | 84 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 200895 | 01451 | 1660 | Solar | 05_09_501L2 | 11/12/2018 | 11/30/2018 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 01/30/2019 | 56 | 21 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 457764 | 01082 | 0 | Solar | 05_07_98W46 | 09/16/2022 | 09/19/2022 | 0 | 0 | 0 | 09/20/2022 | 09/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 554224 | 02301 | 6 | Solar | 05_07_91W48 | 09/26/2023 | 10/03/2023 | 5 | 0 | 5 | 10/04/2023 | 10/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2023 | 09/26/2023 | 1/31/2025 | Y | EXP | 365 | 02/27/2024 | 03/18/2024 | 21 | 0 | 21 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 643807 | 02301 | 10 | Solar | 05_09_604W1 | 10/08/2024 | 11/18/2024 | 4 | 0 | 4 | 11/19/2024 | 11/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/08/2024 | 2/10/2026 | Y | EXP | 365 | 05/16/2025 | 09/23/2025 | 131 | 0 | 131 |  |  | 10/7/2025 | Connected |  | N
National Grid | BARRE | 268549 | 01005 | 10 | Solar | 05_05_3432W1 | 12/09/2019 | 12/10/2019 | 0 | 0 | 0 | 12/11/2019 | 12/11/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 |  | 12/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2020 | Connected |  | N
National Grid | FOXBOROUGH | 244619 | 02035 | 115.2 | Solar | 05_12_12L6 | 07/22/2019 | 08/21/2019 | 20 | 14 | 6 | 08/22/2019 | 08/22/2019 | 26 | 17 | 9 | 01/22/2020 | 05/05/2020 | 64 | 54 | 10 |  |  | 0 | 0 | 0 |  | 05/05/2020 | 64 | 54 | 10 |  |  | 0 | 0 | 0 | 5/27/2020 |  | 5/2/2022 | N | EXP | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 716359 | 01915 | 14.658 | Solar | 05_05_320W2 | 09/03/2025 | 09/09/2025 | 3 | 1 | 2 | 09/10/2025 | 09/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | DOUGLAS | 733746 | 01516 | 12.54 | Solar | 05_07_797W42 | 11/13/2025 | 11/14/2025 | 1 | 0 | 1 | 11/17/2025 | 11/17/2025 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2026 | Connected |  | N
National Grid | BRIDGEWATER | 403290 | 02333 | 250 | Solar | 05_05_9L5 | 01/19/2022 | 01/28/2022 | 7 | 1 | 6 | 01/31/2022 | 01/31/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2022 | 01/19/2022 | 5/13/2024 | Y | EXP | 386 | 04/15/2024 | 04/14/2024 | 0 | 0 | 0 |  |  | 4/29/2024 | Connected |  | N
National Grid | SEEKONK | 711870 | 02771 | 6.282 | Solar | 05_01_201W2 | 08/13/2025 | 08/19/2025 | 4 | 0 | 4 | 08/20/2025 | 08/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | HARVARD | 205168 | 01451 | 3500 | Solar | 05_09_501L2 | 03/19/2019 | 04/23/2019 | 25 | 17 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/24/2019 | 05/18/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 465211 | 01082 | 15.2 | Solar | 05_07_98W46 | 10/02/2022 | 10/10/2022 | 6 | 3 | 3 | 10/11/2022 | 10/11/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2022 | 10/02/2022 | 8/1/2024 | Y | EXP | 5 | 06/09/2023 | 04/16/2024 | 313 | 3 | 310 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 554752 | 02301 | 6 | Solar | 05_07_91W48 | 10/04/2023 | 10/10/2023 | 3 | 0 | 3 | 10/11/2023 | 10/11/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2024 | Connected |  | N
National Grid | BROCKTON | 665912 | 02302 | 7.6 | Solar | 05_09_604W1 | 01/15/2025 | 01/30/2025 | 2 | 0 | 2 | 01/31/2025 | 01/31/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 401844 | 01005 | 15.2 | Solar | 05_05_3432W1 | 12/17/2021 | 12/27/2021 | 6 | 3 | 3 | 12/28/2021 | 12/28/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  | 11/26/2023 | N | EXP | 575 |  |  | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N
National Grid | FOXBOROUGH | 593565 | 02035 | 67.3 | Solar | 05_12_1381 | 02/29/2024 | 04/01/2024 | 23 | 13 | 10 | 04/02/2024 | 04/02/2024 | 32 | 20 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 701275 | 01915 | 10 | Solar | 05_05_320W3 | 06/26/2025 | 09/03/2025 | 12 | 8 | 4 | 09/29/2025 | 09/29/2025 | 48 | 35 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DOUGLAS | 176388 | 01516 | 3.8 | Solar | 05_07_8W1 | 01/29/2016 | 01/29/2016 | 3 | 3 | 0 | 02/04/2016 | 02/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 2/6/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 12/1/2016 | 12/1/2016 | 12/5/2016 | Connected |  | N
National Grid | BROCKTON | 411356 | 02302 | 4999.2 | Battery Add-On | 05_05_9L5 | 05/11/2022 | 07/07/2022 | 38 | 29 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2022 | 08/04/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 730160 | 02771 | 11.78 | Solar | 05_01_201W2 | 10/30/2025 | 11/10/2025 | 6 | 4 | 2 | 11/12/2025 | 11/12/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 225183 | 01451 | 0 | Solar | 05_09_501L2 | 05/03/2019 | 05/08/2019 | 2 | 0 | 2 | 05/09/2019 | 05/09/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2019 | Connected |  | N
National Grid | HARDWICK | 495450 | 01037 | 3.8 | Solar | 05_07_98W46 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 562420 | 02301 | 3.8 | Solar | 05_07_91W48 | 10/24/2023 | 10/26/2023 | 2 | 1 | 1 | 10/27/2023 | 10/27/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 | 10/24/2023 | 12/7/2024 | Y | EXP | 365 | 05/07/2024 | 05/15/2024 | 9 | 0 | 9 |  |  | 5/22/2024 | Connected |  | N
National Grid | BROCKTON | 666716 | 02301 | 13.3 | Solar | 05_09_604W1 | 01/20/2025 | 02/03/2025 | 5 | 1 | 4 | 02/04/2025 | 02/04/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 | 01/20/2025 | 3/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | ATHOL | 544841 | 01331 | 6 | Solar | 05_05_3432W1 | 08/22/2023 | 08/25/2023 | 4 | 2 | 2 | 08/28/2023 | 08/28/2023 | 100 | 75 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2024 |  | 2/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2024 | Connected |  | N
National Grid | FOXBOROUGH | 587964 | 02035 | 250 | Natural Gas | 05_12_1383 | 03/07/2024 | 08/06/2024 | 104 | 95 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2024 | 08/14/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 711249 | 01915 | 250 | Solar | 05_05_320W3 | 09/09/2025 | 11/26/2025 | 53 | 43 | 10 |  |  | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DOUGLAS | 177454 | 01516 | 7.6 | Solar | 05_07_8W1 | 12/06/2016 | 12/06/2016 | 2 | 2 | 0 | 12/09/2016 | 12/09/2016 | 277 | 0 | 277 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2016 |  | 2/14/2018 | N | EXP | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 506779 | 02302 | 11.02 | Solar | 05_05_9L5 | 03/17/2023 | 03/21/2023 | 2 | 0 | 2 | 03/22/2023 | 03/22/2023 | 150 | 130 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  | 12/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | SEEKONK | 728331 | 02771 | 8.36 | Solar | 05_01_201W2 | 10/22/2025 | 10/27/2025 | 3 | 0 | 3 | 10/28/2025 | 10/28/2025 | 76 | 25 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 288610 | 01451 | 3.8 | Solar | 05_09_501L2 | 05/28/2020 |  | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 500083 | 01037 | 0 | Solar | 05_07_98W46 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 124 | 102 | 22 | 12/06/2023 | 01/17/2024 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  | 01/17/2024 | 19 | 3 | 16 |  |  | 0 | 0 | 0 | 1/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 626242 | 02301 | 5.76 | Solar | 05_07_91W48 | 07/19/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/19/2024 | 9/16/2025 | Y | EXP | 365 | 12/11/2024 | 01/29/2025 | 50 | 0 | 50 |  |  | 2/10/2025 | Connected |  | N
National Grid | BROCKTON | 674451 | 02301 | 8.64 | Solar | 05_09_604W1 | 02/26/2025 | 03/14/2025 | 2 | 0 | 2 | 03/27/2025 | 03/27/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2026 | Connected |  | N
National Grid | PETERSHAM | 593998 | 01366 | 6 | Solar | 05_05_3432W1 | 03/11/2024 | 03/12/2024 | 1 | 0 | 1 | 03/13/2024 | 03/13/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 175090 | 02035 | 15 | Solar | 05_12_1385 | 07/29/2011 | 07/29/2011 | 322 | 65 | 257 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 713976 | 01915 | 10 | Solar | 05_05_320W3 | 08/22/2025 | 09/24/2025 | 5 | 0 | 5 | 10/02/2025 | 10/02/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | DOUGLAS | 198035 | 01516 | 9 | Solar | 05_07_8W1 | 10/16/2018 | 12/27/2018 | 10 | 10 | 0 | 12/28/2018 | 12/28/2018 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 | 10/16/2018 | 10/22/2019 | Y | EXP | 279 | 04/24/2019 | 05/31/2019 | 37 | 0 | 37 |  |  | 8/1/2019 | Connected |  | N
National Grid | BRIDGEWATER | 579428 | 02333 | 6.09 | Solar | 05_05_9L5 | 12/26/2023 | 01/02/2024 | 4 | 0 | 4 | 01/03/2024 | 01/03/2024 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 | 12/26/2023 | 2/26/2025 | Y | EXP | 365 | 06/04/2024 | 07/09/2024 | 36 | 0 | 36 |  |  | 7/17/2024 | Connected |  | N
National Grid | ATTLEBORO | 443314 | 02703 | 240 | Solar | 05_01_201W3 | 07/15/2022 | 07/28/2022 | 9 | 0 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/26/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HARVARD | 291680 | 01451 | 0 | Other | 05_09_501L2 | 08/31/2020 | 09/16/2020 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/17/2020 | 10/08/2020 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 520042 | 01082 | 7.83 | Solar | 05_07_98W46 | 04/27/2023 | 05/15/2023 | 12 | 9 | 3 | 05/16/2023 | 05/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 7/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | BROCKTON | 635533 | 02301 | 6 | Solar | 05_07_91W48 | 08/26/2024 | 08/30/2024 | 2 | 0 | 2 | 09/03/2024 | 09/03/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 681343 | 02301 | 11.4 | Solar | 05_09_604W1 | 05/14/2025 | 05/20/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | PETERSHAM | 603943 | 01366 | 11.4 | Solar | 05_05_3432W1 | 04/17/2024 | 04/23/2024 | 4 | 3 | 1 | 04/24/2024 | 04/24/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 5/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2024 | Connected |  | N
National Grid | FOXBOROUGH | 176864 | 02035 | 26.75 | Solar | 05_12_1385 | 01/21/2016 | 01/21/2016 | 4 | 4 | 0 | 01/27/2016 | 01/27/2016 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/26/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 722246 | 01902 | 14.44 | Solar | 05_05_320W3 | 09/30/2025 | 10/20/2025 | 4 | 0 | 4 | 11/06/2025 | 11/06/2025 | 78 | 60 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | NORTHBRIDGE | 428516 | 01534 | 7.6 | Solar | 05_07_8W1 | 05/05/2022 | 05/26/2022 | 15 | 14 | 1 | 05/27/2022 | 05/27/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 603824 | 02190 | 15.2 | Solar | 05_05_9L5 | 04/15/2024 | 04/17/2024 | 2 | 1 | 1 | 04/18/2024 | 04/18/2024 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 |  | 5/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 729148 | 02703 | 4995 | Other | 05_01_201W3 | 12/09/2025 |  | 58 | 25 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | HARVARD | 315000 | 01451 | 5 | Solar | 05_09_501L2 | 10/06/2020 |  | 70 | 48 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 534910 | 01082 | 5.76 | Solar | 05_07_98W46 | 06/22/2023 | 06/26/2023 | 2 | 0 | 2 | 06/27/2023 | 06/27/2023 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2023 | 06/22/2023 | 10/22/2024 | Y | EXP | 365 | 10/04/2023 | 10/20/2023 | 17 | 0 | 17 |  |  | 10/26/2023 | Connected |  | N
National Grid | BROCKTON | 646456 | 02301 | 3.8 | Solar | 05_07_91W48 | 10/29/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 696615 | 02301 | 23.725 | Solar | 05_09_604W1 | 06/20/2025 | 06/25/2025 | 3 | 1 | 2 | 06/26/2025 | 06/26/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 620650 | 01005 | 7.678 | Solar | 05_05_3432W1 | 06/26/2024 | 08/01/2024 | 24 | 22 | 2 | 08/02/2024 | 08/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 | 06/26/2024 | 8/28/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2024 | Connected |  | N
National Grid | FOXBOROUGH | 683610 | 02035 | 20 | Solar | 05_12_1385 | 04/09/2025 | 04/30/2025 | 4 | 0 | 4 | 05/01/2025 | 05/01/2025 | 89 | 75 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 735262 | 01901 | 3.8 | Solar | 05_05_320W3 | 11/20/2025 | 12/18/2025 | 15 | 11 | 4 | 12/19/2025 | 12/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/21/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WHITINSVILLE | 456387 | 01588 | 7.6 | Solar | 05_07_8W1 | 11/28/2022 | 12/01/2022 | 3 | 2 | 1 | 12/02/2022 | 12/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 | 11/28/2022 | 6/10/2024 | Y | EXP | 365 | 05/12/2023 | 06/09/2023 | 29 | 0 | 29 |  |  | 6/23/2023 | Connected |  | N
National Grid | WEYMOUTH | 619110 | 02190 | 6.84 | Solar | 05_05_9L5 | 06/19/2024 | 07/03/2024 | 4 | 2 | 2 | 07/05/2024 | 07/05/2024 | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | SEEKONK | 174968 | 02771 | 27 | Solar | 05_01_201W3 | 09/06/2013 | 09/06/2013 | 7 | 0 | 7 | 09/18/2013 | 09/18/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2013 |  | 11/29/2013 | N | EXP | 38 |  |  | 0 | 0 | 0 | 11/27/2013 | 11/27/2013 | 12/27/2013 | Connected |  | N
National Grid | HARVARD | 318585 | 01451 | 0 | Other | 05_09_501L2 | 11/06/2020 |  | 24 | 17 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 554912 | 01082 | 5 | Solar | 05_07_98W46 | 09/15/2023 | 10/24/2023 | 43 | 26 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 646825 | 02301 | 6.38 | Solar | 05_07_91W48 | 10/14/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | BROCKTON | 712329 | 02302 | 8.376 | Solar | 05_09_604W1 | 08/21/2025 | 09/11/2025 | 2 | 0 | 2 | 09/16/2025 | 09/16/2025 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 | 08/21/2025 | 10/16/2026 | Y | EXP | 365 | 11/21/2025 | 11/25/2025 | 5 | 0 | 5 |  |  | 12/2/2025 | Connected |  | N
National Grid | PETERSHAM | 639342 | 01366 | 7.6 | Solar | 05_05_3432W1 | 09/11/2024 | 10/04/2024 | 2 | 0 | 2 | 10/07/2024 | 10/07/2024 | 116 | 101 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 529508 | 02035 | 10 | Solar | 05_12_1388 | 06/07/2023 |  | 46 | 35 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 736065 | 01901 | 11.4 | Solar | 05_05_320W3 | 11/25/2025 | 11/26/2025 | 4 | 0 | 4 | 12/16/2025 | 12/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 |  | 1/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBRIDGE | 520468 | 01534 | 0 | Solar | 05_07_8W1 | 04/20/2023 | 04/24/2023 | 2 | 0 | 2 | 04/25/2023 | 04/25/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2023 |  | 8/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | WEYMOUTH | 632018 | 02190 | 5.12 | Solar | 05_05_9L5 | 08/16/2024 | 08/20/2024 | 2 | 1 | 1 | 08/21/2024 | 08/21/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 175010 | 02771 | 1500 | Solar | 05_01_201W3 | 09/02/2011 | 09/02/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 |  | 11/30/2012 | N | STD | 154 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 327466 | 01432 | 6.24 | Solar | 05_09_501L2 | 12/01/2020 | 01/05/2021 | 22 | 18 | 4 | 01/06/2021 | 01/06/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2021 |  | 1/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2021 | Connected |  | N
National Grid | WARE | 587841 | 01082 | 0 | Solar | 05_07_98W46 | 02/14/2024 | 03/01/2024 | 12 | 10 | 2 | 03/04/2024 | 03/04/2024 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 4/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | BROCKTON | 652303 | 02301 | 7.6 | Solar | 05_07_91W48 | 11/14/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | BROCKTON | 714578 | 02301 | 24.32 | Solar | 05_09_604W1 | 08/25/2025 | 08/28/2025 | 2 | 0 | 2 | 08/29/2025 | 08/29/2025 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PETERSHAM | 678259 | 01366 | 15.2 | Solar | 05_05_3432W1 | 03/19/2025 | 04/10/2025 | 17 | 14 | 3 | 04/11/2025 | 04/11/2025 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | FOXBOROUGH | 535794 | 02035 | 8.8 | Solar | 05_12_1388 | 08/10/2023 | 08/16/2023 | 5 | 2 | 3 | 08/17/2023 | 08/17/2023 | 106 | 43 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 753170 | 01901 | 15.2 | Solar | 05_05_320W3 | 02/25/2026 | 03/02/2026 | 3 | 0 | 3 | 03/03/2026 | 03/03/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GRAFTON | 579417 | 01519 | 16 | Solar | 05_07_8W1 | 12/26/2023 | 12/28/2023 | 2 | 0 | 2 | 12/29/2023 | 12/29/2023 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 646163 | 02190 | 6 | Solar | 05_05_9L5 | 10/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/04/2024 | 12/04/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 12/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2025 | Connected |  | N
National Grid | SEEKONK | 176175 | 02771 | 35 | Solar | 05_01_201W3 | 07/02/2015 | 07/02/2015 | 4 | 4 | 0 | 07/09/2015 | 07/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2015 |  | 7/7/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 12/21/2015 | Connected |  | N
National Grid | AYER | 329493 | 01432 | 0 | Battery Add-On | 05_09_501L2 | 12/15/2020 | 01/11/2021 | 17 | 13 | 4 | 01/12/2021 | 01/12/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2021 | 12/15/2020 | 5/23/2022 | Y | EXP | 365 | 05/07/2021 | 05/18/2021 | 11 | 0 | 11 |  |  | 11/3/2021 | Connected |  | N
National Grid | WARE | 587972 | 01082 | 6.67 | Solar | 05_07_98W46 | 03/19/2024 | 03/25/2024 | 4 | 0 | 4 | 03/26/2024 | 03/26/2024 | 30 | 23 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 658143 | 02301 | 7.6 | Solar | 05_07_91W48 | 12/03/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/03/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 467839 | 02302 | 1900 | Solar | 05_09_604W2 | 02/27/2023 | 05/09/2023 | 49 | 39 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2023 | 06/27/2023 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PETERSHAM | 178748 | 01366 | 0 | Solar | 05_05_3432W2 | 03/19/2012 | 03/19/2012 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2012 |  | 6/1/2012 | N | EXP | 7 |  |  | 0 | 0 | 0 | 6/11/2012 | 6/11/2012 | 8/27/2012 | Terminated |  | N
National Grid | FOXBOROUGH | 639873 | 02035 | 5.76 | Solar | 05_12_1389 | 09/13/2024 | 10/01/2024 | 3 | 0 | 3 | 10/02/2024 | 10/02/2024 | 69 | 45 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | LYNN | 174553 | 01901 | 1910 | Solar | 05_05_320W3 | 10/28/2011 | 10/28/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 | 10/28/2011 | 10/31/2012 | Y | STD | 19 | 05/30/2013 | 07/26/2013 | 39 | 0 | 39 | 7/17/2013 | 7/17/2013 | 9/9/2013 | Connected |  | N
National Grid | GRAFTON | 642780 | 01560 | 7.6 | Solar | 05_07_8W1 | 09/25/2024 | 10/17/2024 | 1 | 0 | 1 | 10/18/2024 | 10/18/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 09/25/2024 | 12/20/2025 | Y | EXP | 365 | 05/30/2025 | 08/19/2025 | 82 | 0 | 82 |  |  | 8/22/2025 | Connected |  | N
National Grid | WEYMOUTH | 657113 | 02190 | 6.96 | Solar | 05_05_9L5 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/26/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | SEEKONK | 382980 | 02771 | 3.8 | Solar | 05_01_201W3 | 09/19/2021 | 10/18/2021 | 20 | 19 | 1 | 10/19/2021 | 10/19/2021 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2021 |  | 10/17/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 339048 | 01432 | 5 | Solar | 05_09_501L2 | 02/05/2021 | 04/14/2021 | 48 | 48 | 0 | 04/15/2021 | 04/15/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 |  | 4/14/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARDWICK | 604595 | 01031 | 7.6 | Solar | 05_07_98W46 | 04/17/2024 | 04/30/2024 | 2 | 0 | 2 | 05/01/2024 | 05/01/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 | 04/17/2024 | 7/30/2025 | Y | EXP | 365 | 08/02/2024 | 10/01/2024 | 61 | 0 | 61 |  |  | 4/10/2025 | Connected |  | N
National Grid | BROCKTON | 662628 | 02301 | 7.475 | Solar | 05_07_91W48 | 12/26/2024 | 02/26/2025 | 36 | 25 | 11 | 02/27/2025 | 02/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 702793 | 02301 | 450 | Solar | 05_09_604W2 | 02/10/2026 |  | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | PETERSHAM | 367911 | 01366 | 266.6 | Solar | 05_05_3432W2 | 08/02/2021 | 08/17/2021 | 12 | 3 | 9 | 08/18/2021 | 08/18/2021 | 15 | 3 | 12 | 12/01/2021 | 12/21/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 12/21/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 3/18/2022 | 08/02/2021 | 9/18/2026 | Y | EXP | 28 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | FOXBOROUGH | 205221 | 02035 | 33.3 | Solar | 05_12_1391 | 01/04/2019 | 01/07/2019 | 1 | 1 | 0 | 01/08/2019 | 01/08/2019 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 |  | 1/25/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2021 | Connected |  | N
National Grid | LYNN | 174712 | 01902 | 19.35 | Solar | 05_05_320W3 | 06/23/2013 | 06/23/2013 | 7 | 0 | 7 | 07/03/2013 | 07/03/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2013 |  | 12/2/2013 | N | EXP | 143 |  |  | 0 | 0 | 0 | 8/29/2013 | 8/29/2013 | 11/12/2013 | Connected |  | N
National Grid | GRAFTON | 657360 | 01560 | 3.8 | Solar | 05_07_8W1 | 11/27/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | WEYMOUTH | 673203 | 02190 | 17.28 | Solar | 05_05_9L5 | 02/25/2025 | 03/03/2025 | 5 | 1 | 4 | 03/04/2025 | 03/04/2025 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | ATTLEBORO | 396935 | 02703 | 7.6 | Solar | 05_01_201W3 | 11/22/2021 | 01/06/2022 | 31 | 23 | 8 | 01/07/2022 | 01/07/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 434992 | 01432 | 8.99 | Solar | 05_09_501L2 | 06/29/2022 | 06/30/2022 | 1 | 0 | 1 | 07/01/2022 | 07/01/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2022 | Connected |  | N
National Grid | HARDWICK | 610691 | 01037 | 0 | Solar | 05_07_98W46 | 05/13/2024 | 05/21/2024 | 6 | 3 | 3 | 05/22/2024 | 05/22/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 | 05/13/2024 | 6/14/2025 | Y | EXP | 365 | 08/21/2024 | 10/02/2024 | 43 | 0 | 43 |  |  | 12/10/2024 | Connected |  | N
National Grid | BROCKTON | 669861 | 02301 | 3.8 | Solar | 05_07_91W48 | 02/10/2025 | 03/14/2025 | 12 | 10 | 2 | 03/17/2025 | 03/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 6/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2025 | Connected |  | Y
National Grid | BROCKTON | 723717 | 02302 | 15.96 | Solar | 05_09_604W2 | 10/02/2025 | 10/08/2025 | 4 | 0 | 4 | 10/09/2025 | 10/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | PETERSHAM | 367906 | 01366 | 57.6 | Solar | 05_05_3432W2 | 07/09/2021 | 08/02/2021 | 16 | 8 | 8 | 08/03/2021 | 08/03/2021 | 27 | 3 | 24 | 12/01/2021 | 12/21/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 12/21/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 3/18/2022 | 07/09/2021 | 12/9/2026 | Y | EXP | 278 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | FOXBOROUGH | 175112 | 02035 | 100 | Solar | 05_12_1393 | 10/09/2013 | 10/09/2013 | 8 | 2 | 6 | 10/23/2013 | 10/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2013 |  | 9/1/2014 | N | EXP | 285 |  |  | 0 | 0 | 0 | 2/28/2014 | 2/28/2014 | 7/25/2014 | Connected |  | N
National Grid | LYNN | 175435 | 01902 | 28 | Solar | 05_05_320W3 | 11/24/2014 | 11/24/2014 | 5 | 3 | 2 | 12/03/2014 | 12/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2014 |  | 3/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 1/16/2015 | 1/16/2015 | 6/23/2015 | Connected |  | N
National Grid | NORTHBRIDGE | 727211 | 01534 | 11.5 | Solar | 05_07_910W25 | 10/16/2025 | 10/24/2025 | 5 | 3 | 2 | 10/27/2025 | 10/27/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WEYMOUTH | 678782 | 02190 | 5.76 | Solar | 05_05_9L5 | 03/19/2025 | 03/26/2025 | 5 | 0 | 5 | 03/27/2025 | 03/27/2025 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 405997 | 02703 | 0 | Battery Add-On | 05_01_201W3 | 02/01/2022 | 02/07/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2022 | 05/10/2023 | 313 | 304 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 491099 | 01432 | 11.02 | Solar | 05_09_501L2 | 01/26/2023 | 02/24/2023 | 21 | 20 | 1 | 02/27/2023 | 02/27/2023 | 72 | 49 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 9/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2024 | Connected |  | N
National Grid | WARE | 620821 | 01082 | 5 | Solar | 05_07_98W46 | 06/28/2024 | 07/10/2024 | 6 | 5 | 1 | 07/11/2024 | 07/11/2024 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 06/28/2024 | 8/30/2025 | Y | EXP | 365 | 09/10/2024 | 11/20/2024 | 72 | 0 | 72 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 671662 | 02301 | 8.99 | Solar | 05_07_91W48 | 02/12/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 02/12/2025 | 10/1/2026 | Y | EXP | 365 | 12/12/2025 | 01/21/2026 | 41 | 0 | 41 |  |  | 1/23/2026 | Connected |  | N
National Grid | BROCKTON | 729932 | 02302 | 10 | Solar | 05_09_604W2 | 11/14/2025 | 11/17/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BARRE | 419331 | 01005 | 500 | Solar | 05_05_3432W2 | 05/26/2022 | 06/27/2022 | 20 | 16 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/28/2022 | 07/26/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2025 | 05/26/2022 | 9/1/2027 | Y | STD | 679 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | FOXBOROUGH | 175379 | 02035 | 75 | Natural Gas | 05_12_1393 | 07/08/2014 | 07/08/2014 | 6 | 6 | 0 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2014 |  | 11/28/2014 | N | EXP | 98 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 1/5/2015 | Connected |  | N
National Grid | LYNN | 176462 | 01902 | 10 | Solar | 05_05_320W3 | 02/04/2016 | 02/04/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/13/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 5/16/2016 | 5/16/2016 | 5/18/2016 | Connected |  | N
National Grid | GRAFTON | 728034 | 01560 | 15 | Solar | 05_07_910W25 | 10/21/2025 | 10/27/2025 | 4 | 0 | 4 | 10/28/2025 | 10/28/2025 | 87 | 64 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEYMOUTH | 681353 | 02190 | 15.2 | Solar | 05_05_9L5 | 03/28/2025 | 04/02/2025 | 3 | 0 | 3 | 04/03/2025 | 04/03/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | SEEKONK | 410227 | 02771 | 3.8 | Solar | 05_01_201W3 | 02/03/2022 | 02/08/2022 | 4 | 3 | 1 | 02/09/2022 | 02/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 519111 | 01432 | 7.6 | Solar | 05_09_501L2 | 04/28/2023 | 05/08/2023 | 6 | 4 | 2 | 05/09/2023 | 05/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 621695 | 01082 | 10 | Solar | 05_07_98W46 | 07/01/2024 | 08/07/2024 | 24 | 21 | 3 | 08/08/2024 | 08/08/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 | 07/01/2024 | 11/7/2025 | Y | EXP | 365 | 12/18/2024 | 02/22/2025 | 67 | 0 | 67 |  |  | 7/16/2025 | Connected |  | N
National Grid | BROCKTON | 685885 | 02301 | 7.6 | Solar | 05_07_91W48 | 04/17/2025 | 04/25/2025 | 5 | 1 | 4 | 04/28/2025 | 04/28/2025 | 38 | 23 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 | 04/17/2025 | 7/11/2026 | Y | EXP | 365 | 11/18/2025 | 11/24/2025 | 7 | 0 | 7 |  |  | 12/19/2025 | Connected |  | N
National Grid | BROCKTON | 734018 | 02302 | 11.5 | Solar | 05_09_604W2 | 11/14/2025 | 11/18/2025 | 2 | 0 | 2 | 11/19/2025 | 11/19/2025 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2026 |  | 1/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BARRE | 408090 | 01005 | 999 | Solar | 05_05_3432W2 | 06/01/2022 | 07/13/2022 | 28 | 20 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2022 | 08/08/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2025 | 06/01/2022 | 10/16/2026 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | FOXBOROUGH | 177082 | 02035 | 750 | Solar | 05_12_1393 | 10/18/2016 | 10/18/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/13/2017 | 53 | 42 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 176681 | 01901 | 7.74 | Solar | 05_05_320W3 | 01/04/2016 | 01/04/2016 | 2 | 2 | 0 | 01/08/2016 | 01/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2016 |  | 1/11/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 | 3/11/2016 | 3/11/2016 | 3/17/2016 | Connected |  | N
National Grid | WHITINSVILLE | 736328 | 01588 | 25.7 | Solar | 05_07_910W25 | 11/25/2025 | 12/08/2025 | 8 | 5 | 3 | 12/09/2025 | 12/09/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 |  | 1/8/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEYMOUTH | 704378 | 02190 | 34.2 | Solar | 05_05_9L5 | 08/14/2025 | 08/21/2025 | 4 | 3 | 1 | 08/22/2025 | 08/22/2025 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | N
National Grid | SEEKONK | 424633 | 02771 | 15.2 | Solar | 05_01_201W3 | 05/04/2022 | 05/12/2022 | 6 | 5 | 1 | 05/13/2022 | 05/13/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 |  | 6/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2023 | Connected |  | N
National Grid | AYER | 544083 | 01432 | 7.6 | Solar | 05_09_501L2 | 08/18/2023 | 08/22/2023 | 2 | 0 | 2 | 08/23/2023 | 08/23/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 637460 | 01082 | 7.6 | Solar | 05_07_98W46 | 09/03/2024 | 09/17/2024 | 1 | 0 | 1 | 09/18/2024 | 09/18/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 |  | 12/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2024 | Connected |  | N
National Grid | BROCKTON | 687718 | 02301 | 10.64 | Solar | 05_07_91W48 | 04/29/2025 | 05/30/2025 | 2 | 0 | 2 | 06/05/2025 | 06/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 733815 | 02301 | 0 | Battery Add-On | 05_09_604W2 | 11/18/2025 | 11/20/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | OAKHAM | 538944 | 01068 | 240 | Solar | 05_05_3432W2 | 07/14/2023 | 08/07/2023 | 16 | 8 | 8 |  |  | 85 | 64 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  | 3/18/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FOXBOROUGH | 193190 | 02035 | 5 | Solar | 05_12_1394 | 08/09/2018 | 10/22/2018 | 27 | 26 | 1 | 10/23/2018 | 10/23/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 176758 | 01901 | 6 | Solar | 05_05_320W3 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/29/2016 | 03/02/2016 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 3/1/2017 | N | STD | 364 |  |  | 0 | 0 | 0 | 5/13/2016 | 5/13/2016 | 5/18/2016 | Connected |  | N
National Grid | NORTHBRIDGE | 738566 | 01534 | 11.4 | Solar | 05_07_910W25 | 12/08/2025 | 12/18/2025 | 3 | 0 | 3 | 01/15/2026 | 01/15/2026 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PEMBROKE | 721787 | 02359 | 3.8 | Solar | 05_05_9L5 | 09/29/2025 | 10/03/2025 | 3 | 0 | 3 | 10/06/2025 | 10/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2026 | Connected |  | N
National Grid | SEEKONK | 437610 | 02771 | 3.8 | Solar | 05_01_201W3 | 06/14/2022 | 06/15/2022 | 1 | 0 | 1 | 06/16/2022 | 06/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2022 | 06/14/2022 | 8/25/2023 | Y | EXP | 365 | 09/14/2022 | 09/28/2022 | 15 | 0 | 15 |  |  | 10/5/2022 | Connected |  | N
National Grid | AYER | 573208 | 01432 | 7.6 | Solar | 05_09_501L2 | 12/12/2023 | 12/13/2023 | 1 | 0 | 1 | 12/14/2023 | 12/14/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2024 | 12/12/2023 | 3/8/2025 | Y | EXP | 365 | 06/13/2024 | 07/08/2024 | 26 | 0 | 26 |  |  | 7/9/2024 | Connected |  | Y
National Grid | WARE | 639218 | 01082 | 5.76 | Solar | 05_07_98W46 | 09/10/2024 | 09/24/2024 | 3 | 0 | 3 | 09/25/2024 | 09/25/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | BROCKTON | 536401 | 02301 | 100 | Solar | 05_07_91W49 | 07/18/2023 | 09/06/2023 | 35 | 27 | 8 |  |  | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 | 07/18/2023 | 9/27/2026 | Y | STD | 28 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | BROCKTON | 735466 | 02302 | 11.4 | Solar | 05_09_604W2 | 11/21/2025 | 12/04/2025 | 7 | 6 | 1 | 12/05/2025 | 12/05/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2026 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BARRE | 178782 | 01005 | 2700 | Solar | 05_05_3432W2 | 09/22/2015 | 09/22/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/23/2015 | 11/13/2015 | 35 | 14 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 340811 | 02035 | 9.8 | Solar | 05_12_13J2 | 03/26/2021 | 03/31/2021 | 2 | 0 | 2 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 |  | 5/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 176786 | 01902 | 0 | Solar | 05_05_320W3 | 01/14/2016 | 01/14/2016 | 0 | 0 | 0 | 01/15/2016 | 01/15/2016 | 228 | 0 | 228 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/20/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 738354 | 01519 | 5.76 | Solar | 05_07_910W25 | 12/05/2025 | 12/10/2025 | 3 | 0 | 3 | 12/11/2025 | 12/11/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  | 1/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEMBROKE | 702226 | 02359 | 11.4 | Solar | 05_05_9L6 | 07/02/2025 | 07/09/2025 | 2 | 0 | 2 | 12/16/2025 | 12/16/2025 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SEEKONK | 669239 | 02771 | 5.76 | Solar | 05_01_201W3 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 576642 | 01432 | 7.6 | Solar | 05_09_501L2 | 01/08/2024 | 01/16/2024 | 6 | 3 | 3 | 01/17/2024 | 01/17/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2024 | Connected |  | N
National Grid | WARE | 640647 | 01082 | 7.6 | Solar | 05_07_98W46 | 09/18/2024 | 10/03/2024 | 3 | 0 | 3 | 10/04/2024 | 10/04/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 651307 | 02301 | 5.76 | Solar | 05_07_91W49 | 11/12/2024 | 12/04/2024 | 4 | 0 | 4 | 12/05/2024 | 12/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 174442 | 02302 | 1000 | Solar | 05_09_604W2 | 07/03/2012 | 07/03/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2012 | 08/22/2012 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OAKHAM | 178781 | 01068 | 1200 | Solar | 05_05_3432W2 | 06/10/2014 | 06/10/2014 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2014 | 07/21/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2015 | 06/10/2014 | 7/31/2017 | Y | STD | 96 | 10/22/2015 | 07/14/2017 | 429 | 0 | 429 | 7/19/2017 | 7/19/2017 | 7/25/2017 | Connected |  | N
National Grid | FOXBOROUGH | 646670 | 02035 | 7.6 | Solar | 05_12_13J2 | 10/25/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/25/2024 | 12/27/2025 | Y | EXP | 365 | 09/11/2025 | 09/10/2025 | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | LYNN | 176832 | 01905 | 10 | Solar | 05_05_320W3 | 02/26/2016 | 02/26/2016 | 6 | 6 | 0 | 03/08/2016 | 03/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2016 |  | 3/5/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 | 6/1/2016 | 6/1/2016 | 6/17/2016 | Connected |  | N
National Grid | NORTHBRIDGE | 740489 | 01534 | 7.6 | Solar | 05_07_910W25 | 12/16/2025 | 12/18/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEMBROKE | 177097 | 02359 | 5 | Solar | 05_05_9L6 | 05/24/2016 | 05/24/2016 | 2 | 2 | 0 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/24/2016 | 5/30/2017 | Y | EXP | 358 | 11/03/2016 | 11/14/2016 | 6 | 0 | 6 | 1/5/2017 | 1/5/2017 | 1/5/2017 | Connected |  | N
National Grid | SEEKONK | 671932 | 02771 | 5.76 | Solar | 05_01_201W4 | 02/13/2025 | 06/27/2025 | 54 | 53 | 1 | 08/26/2025 | 08/26/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 | 02/13/2025 | 10/1/2026 | Y | EXP | 365 | 02/03/2026 |  | 32 | 0 | 32 |  |  |  | Construction |  | N
National Grid | AYER | 585404 | 01432 | 11.4 | Solar | 05_09_501L2 | 01/26/2024 | 03/27/2024 | 42 | 41 | 1 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 01/26/2024 | 4/4/2025 | Y | EXP | 365 | 07/03/2024 | 07/05/2024 | 3 | 0 | 3 |  |  | 7/8/2024 | Connected |  | Y
National Grid | WARE | 642925 | 01082 | 6.67 | Solar | 05_07_98W46 | 09/25/2024 | 11/01/2024 | 18 | 13 | 5 | 11/04/2024 | 11/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 09/25/2024 | 12/2/2025 | Y | EXP | 365 | 02/26/2025 | 03/26/2025 | 29 | 0 | 29 |  |  | 3/31/2025 | Connected |  | N
National Grid | BROCKTON | 656536 | 02301 | 6.96 | Solar | 05_07_91W49 | 11/26/2024 | 03/10/2025 | 29 | 25 | 4 | 03/11/2025 | 03/11/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 174611 | 02302 | 1000 | Solar | 05_09_604W2 | 10/28/2010 | 10/28/2010 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2011 |  | 8/8/2012 | N | STD | 335 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 8/3/2012 | Connected |  | N
National Grid | OAKHAM | 178774 | 01068 | 2000 | Solar | 05_05_3432W2 | 06/10/2014 | 06/10/2014 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2014 | 07/21/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2015 | 06/10/2014 | 10/15/2017 | Y | STD | 982 | 08/16/2017 | 10/04/2017 | 34 | 0 | 34 | 10/11/2017 | 10/11/2017 | 10/11/2017 | Connected |  | N
National Grid | FOXBOROUGH | 173305 | 02035 | 3.8 | Solar | 05_12_13J3 | 06/26/2018 | 06/26/2018 | 12 | 8 | 4 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 176917 | 01902 | 10 | Solar | 05_05_320W3 | 05/05/2016 | 05/05/2016 | 1 | 1 | 0 | 05/09/2016 | 05/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2016 |  | 5/11/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N
National Grid | GRAFTON | 746747 | 01560 | 10 | Solar | 05_07_910W25 | 01/22/2026 | 01/26/2026 | 2 | 0 | 2 | 01/27/2026 | 01/27/2026 | 28 | 17 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PEMBROKE | 178043 | 02359 | 1382 | Solar | 05_05_9L6 | 05/03/2017 | 05/03/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2017 | 05/30/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2017 |  | 2/15/2019 | N | STD | 443 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 175712 | 02771 | 5600 | Natural Gas | 05_01_201W4 | 10/23/2014 | 10/23/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2014 | 11/14/2014 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 | 10/23/2014 | 12/31/2016 | Y | STD | 614 | 07/09/2015 | 08/13/2015 | 25 | 0 | 25 | 12/2/2015 | 12/2/2015 | 12/9/2015 | Connected |  | N
National Grid | AYER | 595171 | 01432 | 7.6 | Solar | 05_09_501L2 | 03/13/2024 | 04/03/2024 | 16 | 12 | 4 | 04/04/2024 | 04/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 644508 | 01082 | 7.6 | Solar | 05_07_98W46 | 10/03/2024 | 10/17/2024 | 3 | 0 | 3 | 10/18/2024 | 10/18/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/03/2024 | 12/18/2025 | Y | EXP | 365 | 04/24/2025 | 05/29/2025 | 36 | 0 | 36 |  |  | 6/27/2025 | Connected |  | N
National Grid | BROCKTON | 731422 | 02301 | 8.74 | Solar | 05_07_91W49 | 11/04/2025 | 11/05/2025 | 6 | 3 | 3 | 11/19/2025 | 11/19/2025 | 30 | 10 | 20 | 01/15/2026 | 03/02/2026 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  | 03/02/2026 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 3/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROCKTON | 174609 | 02301 | 1000 | Solar | 05_09_604W2 | 10/19/2010 | 10/19/2010 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2011 | 10/19/2010 | 3/2/2012 | Y | STD | 176 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 4/2/2012 | Connected |  | N
National Grid | OAKHAM | 178794 | 01068 | 57.6 | Solar | 05_05_3432W2 | 03/06/2017 | 03/06/2017 | 2 | 0 | 2 | 03/08/2017 | 03/08/2017 | 265 | 0 | 265 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2017 |  | 3/11/2018 | N | EXP | 367 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 178358 | 02035 | 11.4 | Solar | 05_12_13J3 | 03/01/2018 | 03/01/2018 | 10 | 0 | 10 | 03/16/2018 | 03/16/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2018 |  | 3/23/2020 | N | EXP | 683 |  |  | 0 | 0 | 0 |  |  | 1/17/2020 | Connected |  | N
National Grid | SAUGUS | 177179 | 01906 | 9 | Solar | 05_05_320W3 | 06/06/2016 | 06/06/2016 | 1 | 1 | 0 | 06/08/2016 | 06/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 |  | 6/12/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/22/2016 | 11/28/2016 | Connected |  | N
National Grid | GRAFTON | 748089 | 01560 | 10 | Solar | 05_07_910W25 | 01/29/2026 | 03/02/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | PEMBROKE | 203529 | 02359 | 3.8 | Solar | 05_05_9L6 | 01/30/2019 | 02/12/2019 | 8 | 0 | 8 | 02/13/2019 | 02/13/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 175959 | 02703 | 989 | Solar | 05_01_201W4 | 06/03/2015 | 06/03/2015 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/16/2015 | 07/01/2015 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 03/15/2016 | 06/15/2016 | 63 | 18 | 45 | 4/18/2016 | 06/03/2015 | 6/30/2016 | Y | STD | 326 |  |  | 0 | 0 | 0 | 10/26/2017 | 10/26/2017 | 10/26/2017 | Connected |  | N
National Grid | AYER | 599874 | 01432 | 10 | Solar | 05_09_501L2 | 05/29/2024 | 05/31/2024 | 2 | 1 | 1 | 06/03/2024 | 06/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/29/2024 | 7/1/2025 | Y | EXP | 365 | 08/01/2024 | 07/31/2024 | 0 | 0 | 0 |  |  | 9/13/2024 | Connected |  | N
National Grid | WARE | 650253 | 01082 | 10 | Solar | 05_07_98W46 | 11/07/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 737460 | 02301 | 0 | Battery Add-On | 05_07_91W49 | 12/10/2025 | 12/15/2025 | 3 | 0 | 3 | 12/16/2025 | 12/16/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 1/15/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 174680 | 02301 | 19.99 | Solar | 05_09_604W2 | 01/06/2014 | 01/06/2014 | 5 | 0 | 5 | 01/14/2014 | 01/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2014 | 01/06/2014 | 3/31/2014 | Y | EXP | 52 | 01/22/2015 | 04/08/2014 | 0 | 0 | 0 | 6/12/2014 | 6/12/2014 | 7/8/2014 | Connected |  | N
National Grid | BARRE | 196782 | 01005 | 464 | Solar | 05_05_3432W2 | 10/29/2018 | 12/10/2018 | 27 | 18 | 9 | 12/11/2018 | 12/11/2018 | 13 | 1 | 12 | 02/13/2019 | 04/30/2019 | 54 | 34 | 20 |  |  | 0 | 0 | 0 |  | 04/30/2019 | 54 | 34 | 20 |  |  | 0 | 0 | 0 | 6/27/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 188535 | 02035 | 3.8 | Solar | 05_12_13J3 | 06/19/2018 | 06/19/2018 | 1 | 0 | 1 | 06/22/2018 | 06/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2018 |  | 9/22/2021 | N | EXP | 6 |  |  | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | SAUGUS | 177472 | 01906 | 15.2 | Solar | 05_05_320W3 | 03/02/2017 | 03/02/2017 | 239 | 238 | 1 | 02/12/2018 | 02/12/2018 | 77 | 76 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2018 |  | 6/30/2020 | N | EXP | 92 |  |  | 0 | 0 | 0 |  |  | 6/2/2020 | Connected |  | N
National Grid | WHITINSVILLE | 747627 | 01588 | 10 | Solar | 05_07_910W25 | 01/27/2026 | 01/30/2026 | 3 | 0 | 3 | 02/02/2026 | 02/02/2026 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | PEMBROKE | 205070 | 02359 | 0 | Solar | 05_05_9L6 | 01/03/2019 | 01/11/2019 | 5 | 0 | 5 | 01/14/2019 | 01/14/2019 | 21 | 13 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2019 |  | 3/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | ATTLEBORO | 310063 | 02703 | 10 | Solar | 05_01_201W4 | 09/01/2020 | 09/02/2020 | 0 | 0 | 0 | 09/03/2020 | 09/03/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2020 | Connected |  | N
National Grid | AYER | 602802 | 01432 | 6 | Solar | 05_09_501L2 | 04/13/2024 | 04/15/2024 | 0 | 0 | 0 | 04/16/2024 | 04/16/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2024 | Connected |  | N
National Grid | WARE | 651868 | 01082 | 10 | Solar | 05_07_98W46 | 11/13/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | BROCKTON | 736855 | 02301 | 7.6 | Solar | 05_07_91W49 | 12/22/2025 | 12/26/2025 | 1 | 0 | 1 | 01/07/2026 | 01/07/2026 | 26 | 13 | 13 | 03/03/2026 |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | BROCKTON | 174818 | 02301 | 749 | Solar | 05_09_604W2 | 07/29/2013 | 07/29/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2013 | 11/18/2013 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 410297 | 01005 | 0 | Battery Add-On | 05_05_3432W2 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 199773 | 02035 | 7.6 | Solar | 05_12_13J3 | 10/30/2018 | 11/08/2018 | 6 | 0 | 6 | 11/09/2018 | 11/09/2018 | 75 | 60 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 177840 | 01906 | 4980 | Solar | 05_05_320W3 | 10/17/2017 | 10/17/2017 | 17 | 12 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 | 11/30/2017 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 | 10/17/2017 | 12/31/2021 | Y | STD | 47 | 09/04/2021 | 12/30/2021 | 118 | 4 | 114 |  |  | 12/28/2021 | Connected |  | N
National Grid | GRAFTON | 751306 | 01519 | 3.42 | Solar | 05_07_910W25 | 02/16/2026 | 02/19/2026 | 7 | 3 | 4 | 02/27/2026 | 02/27/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PEMBROKE | 210655 | 02359 | 20 | Solar | 05_05_9L6 | 03/22/2019 | 04/02/2019 | 6 | 1 | 5 | 04/03/2019 | 04/03/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2019 | 03/22/2019 | 4/15/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2019 | Connected |  | N
National Grid | ATTLEBORO | 317230 | 02703 | 10 | Solar | 05_01_201W4 | 12/18/2020 | 12/30/2020 | 6 | 0 | 6 | 12/31/2020 | 12/31/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 |  | 8/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GROTON | 602792 | 01472 | 3 | Solar | 05_09_501L2 | 04/26/2024 | 05/01/2024 | 3 | 0 | 3 | 05/02/2024 | 05/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 04/26/2024 | 6/3/2025 | Y | EXP | 365 | 08/17/2024 | 09/10/2024 | 25 | 0 | 25 |  |  | 11/22/2024 | Connected |  | N
National Grid | WARE | 660550 | 01082 | 5.76 | Solar | 05_07_98W46 | 12/13/2024 | 12/19/2024 | 4 | 0 | 4 | 02/11/2025 | 02/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | Y
National Grid | BROCKTON | 738165 | 02301 | 19.38 | Solar | 05_07_91W49 | 12/04/2025 |  | 62 | 59 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BROCKTON | 175058 | 02301 | 2000 | Solar | 05_09_604W2 | 10/17/2012 | 10/17/2012 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2012 | 02/04/2013 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 513658 | 01005 | 487.5 | Solar | 05_05_3432W2 | 05/15/2023 | 07/21/2023 | 47 | 37 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/24/2023 | 08/18/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 209880 | 02035 | 7.6 | Solar | 05_12_13J3 | 02/28/2019 | 03/11/2019 | 6 | 0 | 6 | 03/12/2019 | 03/12/2019 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 178280 | 01906 | 2930 | Solar | 05_05_320W3 | 02/23/2018 | 02/28/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2018 | 03/27/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2018 | 02/23/2018 | 11/22/2024 | Y | STD | 393 | 05/21/2022 | 05/14/2024 | 724 | 625 | 99 |  |  | 10/29/2024 | Connected |  | N
National Grid | GRAFTON | 175854 | 01560 | 10 | Solar | 05_07_910W25 | 08/03/2015 | 08/03/2015 | 3 | 3 | 0 | 08/07/2015 | 08/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/9/2016 | N | EXP | 354 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 12/18/2015 | Connected |  | N
National Grid | PEMBROKE | 292596 | 02359 | 5 | Solar | 05_05_9L6 | 05/19/2020 | 05/20/2020 | 0 | 0 | 0 | 05/21/2020 | 05/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/19/2020 | 6/16/2021 | Y | EXP | 365 | 03/05/2021 | 04/20/2021 | 46 | 0 | 46 |  |  | 5/25/2021 | Connected |  | N
National Grid | ATTLEBORO | 392812 | 02703 | 15.2 | Solar | 05_01_201W4 | 11/02/2021 |  | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 611141 | 01432 | 9.28 | Solar | 05_09_501L2 | 05/15/2024 | 06/21/2024 | 18 | 17 | 1 | 06/24/2024 | 06/24/2024 | 81 | 37 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 679036 | 01082 | 11.4 | Solar | 05_07_98W46 | 03/19/2025 | 05/14/2025 | 11 | 7 | 4 | 05/15/2025 | 05/15/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 | 03/19/2025 | 6/9/2026 | Y | EXP | 365 | 09/24/2025 | 10/09/2025 | 16 | 0 | 16 |  |  | 10/14/2025 | Connected |  | N
National Grid | BROCKTON | 740616 | 02301 | 13.68 | Solar | 05_07_91W49 | 12/16/2025 | 12/17/2025 | 2 | 0 | 2 | 12/24/2025 | 12/24/2025 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 176071 | 02301 | 10 | Solar | 05_09_604W2 | 06/19/2015 | 06/19/2015 | 12 | 12 | 0 | 07/10/2015 | 07/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 |  | 6/28/2016 | N | EXP | 336 |  |  | 0 | 0 | 0 | 7/28/2015 | 7/28/2015 | 6/30/2016 | Connected |  | N
National Grid | OAKHAM | 689875 | 01068 | 5.76 | Solar | 05_05_3432W2 | 05/06/2025 | 05/08/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2025 | Connected |  | N
National Grid | FOXBOROUGH | 231877 | 02035 | 3.8 | Solar | 05_12_13J3 | 08/15/2019 | 08/26/2019 | 6 | 1 | 5 | 08/27/2019 | 08/27/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2019 |  | 8/26/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2020 | Connected |  | N
National Grid | SAUGUS | 178583 | 01906 | 225 | Solar | 05_05_320W3 | 01/31/2018 | 01/31/2018 | 0 | 0 | 0 | 02/16/2018 | 02/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2018 | 01/31/2018 | 2/6/2019 | Y | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 2/20/2019 | Connected |  | N
National Grid | NORTHBRIDGE | 176147 | 01534 | 2400 | Solar | 05_07_910W25 | 08/24/2015 | 08/24/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/31/2015 | 09/28/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 03/23/2016 | 03/23/2016 | 0 | 0 | 0 | 5/11/2016 | 08/24/2015 | 12/18/2017 | Y | STD | 586 | 08/03/2017 | 12/18/2017 | 88 | 0 | 88 | 12/5/2017 | 12/5/2017 | 12/18/2017 | Connected |  | N
National Grid | PEMBROKE | 355741 | 02359 | 10 | Solar | 05_05_9L6 | 05/25/2021 | 05/27/2021 | 46 | 36 | 10 | 05/28/2021 | 05/28/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2021 | 05/25/2021 | 11/3/2022 | Y | EXP | 365 | 08/19/2021 | 10/12/2021 | 23 | 3 | 20 |  |  | 11/22/2021 | Connected |  | N
National Grid | ATTLEBORO | 477550 | 02703 | 7.83 | Solar | 05_01_201W4 | 01/25/2023 | 02/09/2023 | 12 | 10 | 2 | 02/10/2023 | 02/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 637293 | 01464 | 15.2 | Solar | 05_09_501L2 | 09/11/2024 | 09/19/2024 | 7 | 5 | 2 | 09/20/2024 | 09/20/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | HARDWICK | 740038 | 01094 |  | Battery Add-On | 05_07_98W48 | 12/12/2025 | 12/18/2025 | 4 | 0 | 4 | 12/19/2025 | 12/19/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 741324 | 02301 | 4.8 | Solar | 05_07_91W49 | 12/19/2025 | 12/26/2025 | 39 | 38 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BROCKTON | 176349 | 02301 | 2000 | Solar | 05_09_604W2 | 02/25/2015 | 03/09/2015 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 12/22/2016 | 02/17/2017 | 38 | 11 | 27 | 3/30/2017 | 02/25/2015 | 4/21/2021 | Y | STD | 125 | 01/11/2020 | 02/12/2021 | 397 | 180 | 217 |  |  | 4/20/2021 | Connected |  | N
National Grid | NORTH BROOKFIELD | 695890 | 01535 | 11.4 | Solar | 05_05_3432W2 | 06/09/2025 | 06/20/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 30 | 15 | 15 | 09/09/2025 | 09/17/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 09/17/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/13/2026 | N | EXP | 365 | 11/20/2025 | 12/09/2025 | 20 | 0 | 20 |  |  | 12/31/2025 | Connected |  | N
National Grid | FOXBOROUGH | 256490 | 02035 | 10 | Solar | 05_12_13J3 | 10/04/2019 | 10/19/2019 | 9 | 9 | 0 | 10/21/2019 | 10/21/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 | 10/04/2019 | 10/4/2020 | Y | EXP | 365 | 04/08/2020 | 05/15/2020 | 37 | 0 | 37 |  |  | 5/28/2020 | Connected |  | Y
National Grid | SAUGUS | 178624 | 01906 | 5 | Solar | 05_05_320W3 | 03/15/2018 | 03/15/2018 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2018 |  | 3/20/2019 | N | EXP | 323 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | NORTHBRIDGE | 178143 | 01534 | 4998 | Solar | 05_07_910W25 | 03/23/2018 | 03/30/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2018 | 04/25/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2018 | 03/23/2018 | 6/2/2020 | Y | STD | 635 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 469711 | 02359 | 16.53 | Solar | 05_05_9L6 | 10/19/2022 | 01/06/2023 | 53 | 51 | 2 | 01/09/2023 | 01/09/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2023 | 10/19/2022 | 5/7/2024 | Y | EXP | 365 | 07/20/2023 | 09/14/2023 | 57 | 0 | 57 |  |  | 9/19/2023 | Connected |  | N
National Grid | ATTLEBORO | 548714 | 02703 | 7.6 | Solar | 05_01_201W4 | 08/28/2023 | 08/30/2023 | 2 | 0 | 2 | 08/31/2023 | 08/31/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 | 08/28/2023 | 11/3/2024 | Y | EXP | 365 | 05/29/2024 | 06/04/2024 | 7 | 0 | 7 |  |  | 6/18/2024 | Connected |  | N
National Grid | AYER | 643780 | 01432 | 10 | Solar | 05_09_501L2 | 10/01/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 | 10/01/2024 | 1/2/2026 | Y | EXP | 365 | 02/13/2025 | 02/12/2025 | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | WARE | 174210 | 01082 | 100 | Solar | 05_07_98W48 | 02/01/2012 | 02/01/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 2/18/2012 | N | EXP | 298 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 750127 | 02301 | 23 | Solar | 05_07_91W49 | 02/09/2026 | 02/10/2026 | 1 | 0 | 1 | 02/11/2026 | 02/11/2026 | 17 | 8 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 176715 | 02301 | 16.4 | Solar | 05_09_604W2 | 01/08/2016 | 01/08/2016 | 3 | 3 | 0 | 01/13/2016 | 01/13/2016 | 269 | 0 | 269 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2016 |  | 1/27/2017 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OAKHAM | 488486 | 01068 | 240 | Solar | 05_05_344W1 | 02/24/2023 | 05/23/2023 | 61 | 52 | 9 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2025 | 02/24/2023 | 6/3/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | FOXBOROUGH | 668811 | 02035 | 7.6 | Solar | 05_12_13J3 | 02/05/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 40 | 22 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 185495 | 01906 | 250 | Solar | 05_05_320W3 | 05/16/2018 | 05/16/2018 | 14 | 0 | 14 | 06/08/2018 | 06/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 |  | 7/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2019 | Connected |  | N
National Grid | NORTHBRIDGE | 178167 | 01534 | 11.4 | Solar | 05_07_910W25 | 02/14/2018 | 02/14/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2018 |  | 2/20/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 9/30/2019 | Connected |  | N
National Grid | PEMBROKE | 472474 | 02359 | 13.6 | Solar | 05_05_9L6 | 12/01/2022 | 12/07/2022 | 4 | 0 | 4 | 12/08/2022 | 12/08/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 565211 | 02703 | 0 | Solar | 05_01_201W4 | 10/23/2023 | 10/24/2023 | 1 | 0 | 1 | 10/25/2023 | 10/25/2023 | 50 | 29 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 2/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | AYER | 656486 | 01432 | 10 | Solar | 05_09_501L2 | 11/26/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 177165 | 01082 | 99.9 | Solar | 05_07_98W48 | 01/24/2017 | 01/24/2017 | 14 | 12 | 2 | 02/14/2017 | 02/14/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2017 |  | 1/30/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 9/12/2018 | Connected |  | N
National Grid | BROCKTON | 749931 | 02301 | 7.6 | Solar | 05_07_91W49 | 02/06/2026 | 02/10/2026 | 3 | 0 | 3 | 02/20/2026 | 02/20/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 176993 | 02301 | 16 | Solar | 05_09_604W2 | 03/15/2017 | 03/15/2017 | 10 | 10 | 0 | 03/31/2017 | 03/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 |  | 3/20/2018 | N | EXP | 35 |  |  | 0 | 0 | 0 | 12/13/2017 | 12/13/2017 | 12/13/2017 | Connected |  | N
National Grid | NORTH BROOKFIELD | 657127 | 01535 | 19 | Solar | 05_05_344W1 | 01/09/2025 | 01/14/2025 | 3 | 2 | 1 | 01/15/2025 | 01/15/2025 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FOXBOROUGH | 697587 | 02035 | 6.84 | Solar | 05_12_16J1 | 06/17/2025 | 07/01/2025 | 7 | 5 | 2 | 07/17/2025 | 07/17/2025 | 59 | 46 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  | 1/14/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | N
National Grid | SAUGUS | 191709 | 01906 | 8 | Solar | 05_05_320W3 | 07/24/2018 | 08/10/2018 | 5 | 0 | 5 | 08/13/2018 | 08/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 178285 | 01560 | 3200 | Solar | 05_07_910W25 | 03/29/2018 | 03/29/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2018 | 04/27/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 | 03/29/2018 | 12/30/2022 | Y | STD | 532 | 12/15/2021 | 07/25/2022 | 223 | 141 | 82 |  |  | 12/28/2022 | Connected |  | N
National Grid | PEMBROKE | 532360 | 02359 | 10 | Solar | 05_05_9L6 | 07/24/2023 | 07/25/2023 | 1 | 0 | 1 | 07/26/2023 | 07/26/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 | 07/24/2023 | 10/25/2024 | Y | EXP | 365 | 10/25/2023 | 12/14/2023 | 51 | 0 | 51 |  |  | 1/9/2024 | Connected |  | N
National Grid | ATTLEBORO | 662637 | 02703 | 11.5 | Solar | 05_01_201W4 | 12/26/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | AYER | 667431 | 01432 | 7.6 | Solar | 05_09_501L2 | 01/27/2025 | 02/18/2025 | 8 | 3 | 5 | 02/19/2025 | 02/19/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 | 01/27/2025 | 3/25/2026 | Y | EXP | 365 | 05/02/2025 | 05/08/2025 | 7 | 0 | 7 |  |  | 12/18/2025 | Connected |  | N
National Grid | WARE | 177287 | 01082 | 240 | Solar | 05_07_98W48 | 06/16/2016 | 06/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/17/2016 | 07/21/2016 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2016 |  | 2/22/2017 | N | STD | 15 |  |  | 0 | 0 | 0 | 12/15/2016 | 12/15/2016 | 3/6/2017 | Connected |  | N
National Grid | BROCKTON | 175743 | 02301 | 684 | Solar | 05_07_91W49 | 10/28/2014 | 10/28/2014 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2014 | 12/05/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/18/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 177180 | 02301 | 12.75 | Solar | 05_09_604W2 | 06/06/2016 | 06/06/2016 | 3 | 3 | 0 | 06/10/2016 | 06/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 |  | 6/12/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 | 10/4/2016 | 10/4/2016 | 10/6/2016 | Connected |  | N
National Grid | OAKHAM | 704909 | 01068 | 999 | Other | 05_05_344W1 | 09/05/2025 | 11/14/2025 | 47 | 39 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2025 | 12/11/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FOXBOROUGH | 426175 | 02035 | 7.6 | Solar | 05_12_16J1 | 04/25/2022 | 04/25/2022 | 0 | 0 | 0 | 04/26/2022 | 04/26/2022 | 70 | 52 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 199879 | 01906 | 6 | Solar | 05_05_320W3 | 11/06/2018 | 12/20/2018 | 28 | 28 | 0 | 12/21/2018 | 12/21/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 249662 | 01560 | 3200 | Solar | 05_07_910W25 | 09/05/2019 | 11/19/2019 | 48 | 46 | 2 |  |  | 2 | 2 | 0 |  |  | 0 | 0 | 0 | 11/20/2019 | 05/07/2020 | 116 | 94 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 666094 | 02359 | 5.76 | Solar | 05_05_9L6 | 01/16/2025 | 04/08/2025 | 18 | 16 | 2 | 04/09/2025 | 04/09/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 705319 | 02703 | 50 | Solar | 05_01_201W4 | 07/21/2025 | 08/29/2025 | 26 | 24 | 2 | 09/02/2025 | 09/02/2025 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | N
National Grid | AYER | 674945 | 01432 | 15.7 | Solar | 05_09_501L2 | 03/03/2025 | 03/11/2025 | 6 | 1 | 5 | 03/12/2025 | 03/12/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 | 03/03/2025 | 6/5/2026 | Y | EXP | 365 | 07/25/2025 | 10/02/2025 | 70 | 0 | 70 |  |  | 10/6/2025 | Connected |  | N
National Grid | WARE | 192458 | 01082 | 710 | Solar | 05_07_98W48 | 09/14/2018 | 10/01/2018 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 12/03/2018 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2019 |  | 5/18/2021 | N | STD | 61 |  |  | 0 | 0 | 0 |  |  | 5/12/2021 | Connected |  | N
National Grid | EASTON | 176620 | 02375 | 10 | Solar | 05_07_91W49 | 04/12/2016 | 04/12/2016 | 1 | 1 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/12/2016 | 4/18/2017 | Y | EXP | 357 | 07/18/2016 | 07/25/2016 | 5 | 0 | 5 | 1/23/2017 | 1/23/2017 | 3/9/2017 | Connected |  | N
National Grid | BROCKTON | 177331 | 02301 | 990 | Solar | 05_09_604W2 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2016 | 12/15/2016 | 73 | 57 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/4/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OAKHAM | 750908 | 01068 |  | Battery Add-On | 05_05_344W1 | 02/12/2026 | 02/17/2026 | 2 | 0 | 2 | 02/18/2026 | 02/18/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FRANKLIN | 532542 | 02038 | 5 | Solar | 05_12_16J1 | 06/29/2023 | 07/06/2023 | 5 | 4 | 1 | 07/07/2023 | 07/07/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 06/29/2023 | 10/25/2024 | Y | EXP | 365 | 06/22/2024 | 07/09/2024 | 18 | 0 | 18 |  |  | 7/22/2024 | Connected |  | N
National Grid | SAUGUS | 216239 | 01906 | 3.8 | Solar | 05_05_320W3 | 04/04/2019 | 04/12/2019 | 5 | 0 | 5 | 04/15/2019 | 04/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 303299 | 01560 | 0 | Solar | 05_07_910W25 | 07/27/2020 | 07/28/2020 | 0 | 0 | 0 | 07/29/2020 | 07/29/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2020 |  | 8/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 676821 | 02359 | 3.8 | Solar | 05_05_9L6 | 03/10/2025 | 03/22/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 437404 | 02703 | 0 | Other | 05_01_207W1 | 09/26/2022 | 10/27/2022 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2022 | 11/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | AYER | 678319 | 01432 | 7.6 | Solar | 05_09_501L2 | 03/26/2025 | 04/22/2025 | 19 | 15 | 4 | 04/23/2025 | 04/23/2025 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 389742 | 01082 | 0 | Other | 05_07_98W48 | 11/10/2021 | 01/04/2022 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 309629 | 02375 | 7.6 | Solar | 05_07_91W49 | 09/29/2020 | 10/02/2020 | 2 | 0 | 2 | 10/05/2020 | 10/05/2020 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 09/29/2020 | 1/24/2022 | Y | EXP | 365 | 08/21/2021 | 08/30/2021 | 3 | 0 | 3 |  |  | 10/19/2021 | Connected |  | N
National Grid | BROCKTON | 177421 | 02301 | 17.6 | Solar | 05_09_604W2 | 12/05/2016 | 12/05/2016 | 2 | 2 | 0 | 12/08/2016 | 12/08/2016 | 231 | 0 | 231 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2016 |  | 12/11/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OAKHAM | 174733 | 01068 | 13.97 | Solar | 05_05_344W1 | 01/08/2013 | 01/08/2013 | 7 | 0 | 7 | 01/18/2013 | 01/18/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2013 |  | 3/29/2013 | N | EXP | 4 |  |  | 0 | 0 | 0 | 10/7/2013 | 10/7/2013 | 12/3/2013 | Connected |  | N
National Grid | FRANKLIN | 188941 | 02038 | 499.5 | Solar | 05_12_16J2 | 09/17/2018 | 09/21/2018 | 3 | 0 | 3 | 09/24/2018 | 09/24/2018 | 165 | 1 | 164 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 222039 | 02148 | 240 | Solar | 05_05_320W3 | 04/24/2019 | 06/03/2019 | 14 | 11 | 3 |  |  | 14 | 4 | 10 | 08/06/2019 | 08/28/2019 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  | 08/28/2019 | 17 | 1 | 16 |  |  | 0 | 0 | 0 | 4/27/2020 | 04/24/2019 | 1/28/2022 | Y | STD | 44 |  |  | 0 | 0 | 0 | 12/3/2021 | 1/14/2022 | 1/24/2022 | Connected |  | N
National Grid | NORTHBRIDGE | 365824 | 01534 | 7.6 | Solar | 05_07_910W25 | 06/24/2021 | 01/06/2022 | 2 | 0 | 2 | 06/29/2021 | 06/29/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2021 |  | 7/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2022 | Connected |  | N
National Grid | PEMBROKE | 697153 | 02359 | 5.76 | Solar | 05_05_9L6 | 06/09/2025 | 06/24/2025 | 2 | 0 | 2 | 07/09/2025 | 07/09/2025 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | ATTLEBORO | 730853 | 02703 | 10.26 | Solar | 05_01_207W1 | 11/03/2025 | 11/07/2025 | 3 | 2 | 1 | 02/03/2026 | 02/03/2026 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | SHIRLEY | 687185 | 01464 | 15.2 | Solar | 05_09_501L2 | 04/24/2025 | 04/29/2025 | 3 | 0 | 3 | 04/30/2025 | 04/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 | 04/24/2025 | 6/15/2026 | Y | EXP | 365 | 06/18/2025 | 09/06/2025 | 81 | 0 | 81 |  |  | 9/23/2025 | Connected |  | N
National Grid | WARE | 391844 | 01082 | 0 | Other | 05_07_98W48 | 11/11/2021 | 01/04/2022 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 311832 | 02375 | 10.32 | Solar | 05_07_91W49 | 10/23/2020 | 10/26/2020 | 0 | 0 | 0 | 10/27/2020 | 10/27/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 | 10/23/2020 | 7/26/2023 | Y | EXP | 9 | 12/18/2020 | 01/26/2021 | 39 | 0 | 39 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 178336 | 02301 | 1000 | Solar | 05_09_604W2 | 11/17/2017 | 11/17/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/06/2017 | 12/27/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/25/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OAKHAM | 176858 | 01068 | 10 | Solar | 05_05_344W1 | 01/19/2016 | 01/19/2016 | 3 | 3 | 0 | 01/22/2016 | 01/22/2016 | 243 | 0 | 243 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2016 |  | 1/24/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 188939 | 02038 | 499.5 | Solar | 05_12_16J2 | 09/19/2018 | 09/21/2018 | 1 | 0 | 1 | 09/24/2018 | 09/24/2018 | 165 | 1 | 164 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 232606 | 02148 | 6.72 | Solar | 05_05_320W3 | 06/20/2019 | 06/28/2019 | 5 | 0 | 5 | 07/01/2019 | 07/01/2019 | 24 | 23 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2019 | 06/20/2019 | 9/30/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2020 | Connected |  | N
National Grid | WHITINSVILLE | 373135 | 01588 | 498 | Solar | 05_07_910W25 | 09/08/2021 | 10/13/2021 | 24 | 16 | 8 |  |  | 37 | 25 | 12 |  |  | 0 | 0 | 0 | 10/14/2021 | 10/15/2021 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 698096 | 02359 | 5.76 | Solar | 05_05_9L6 | 06/12/2025 | 06/27/2025 | 2 | 0 | 2 | 07/03/2025 | 07/03/2025 | 38 | 24 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/26/2025 | Connected |  | N
National Grid | ATTLEBORO | 743282 | 02703 | 11.4 | Solar | 05_01_207W1 | 01/05/2026 | 01/27/2026 | 2 | 0 | 2 | 02/05/2026 | 02/05/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 | 01/05/2026 | 3/2/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | AYER | 699285 | 01432 | 15.58 | Solar | 05_09_501L2 | 06/17/2025 | 06/20/2025 | 2 | 0 | 2 | 06/23/2025 | 06/23/2025 | 77 | 25 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 430304 | 01082 | 100 | Solar | 05_07_98W48 | 05/27/2022 | 08/18/2022 | 56 | 49 | 7 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2023 | 05/27/2022 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | EASTON | 313208 | 02375 | 7.6 | Solar | 05_07_91W49 | 10/01/2020 | 10/06/2020 | 2 | 0 | 2 | 10/07/2020 | 10/07/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 | 10/01/2020 | 5/20/2024 | Y | EXP | 365 | 01/08/2021 | 01/21/2021 | 13 | 0 | 13 |  |  | 8/7/2023 | Connected |  | N
National Grid | BROCKTON | 186270 | 02301 | 4998 | Solar | 05_09_604W2 | 05/29/2018 | 05/29/2018 | 50 | 49 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2018 | 10/12/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 178645 | 01535 | 10 | Solar | 05_05_344W1 | 12/14/2017 | 12/14/2017 | 1 | 0 | 1 | 05/17/2018 | 05/17/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  | 12/20/2018 | N | EXP | 174 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 689238 | 02038 | 120 | Solar | 05_12_16J4 | 10/17/2025 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | MALDEN | 257134 | 02148 | 2930 | Battery Add-On | 05_05_320W3 | 10/21/2019 | 11/07/2019 | 13 | 9 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2019 | 01/10/2020 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 391653 | 01560 | 7.6 | Solar | 05_07_910W25 | 11/02/2021 | 12/21/2021 | 6 | 0 | 6 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 | 11/02/2021 | 4/7/2023 | Y | EXP | 365 | 03/16/2022 | 04/04/2022 | 20 | 0 | 20 |  |  | 4/29/2022 | Connected |  | N
National Grid | PEMBROKE | 728131 | 02359 | 940 | Solar | 05_07_10W1 | 12/22/2025 | 01/27/2026 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/28/2026 | 02/23/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | ATTLEBORO | 198460 | 02703 | 7.6 | Solar | 05_01_207W1 | 10/12/2018 | 11/20/2018 | 22 | 21 | 1 | 11/21/2018 | 11/21/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 699771 | 01453 | 6 | Solar | 05_09_501L2 | 07/09/2025 | 07/22/2025 | 2 | 0 | 2 | 07/30/2025 | 07/30/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 | 07/09/2025 | 8/18/2026 | Y | EXP | 365 | 10/02/2025 | 01/27/2026 | 118 | 0 | 118 |  |  | 12/11/2025 | Connected |  | N
National Grid | HARDWICK | 598992 | 01031 | 25 | Solar | 05_07_98W48 | 03/22/2024 | 04/09/2024 | 12 | 9 | 3 | 04/10/2024 | 04/10/2024 | 32 | 26 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 377483 | 02375 | 10 | Solar | 05_07_91W49 | 08/26/2021 | 08/31/2021 | 4 | 1 | 3 | 09/01/2021 | 09/01/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 | 08/26/2021 | 5/5/2023 | Y | EXP | 365 | 03/09/2022 | 03/31/2022 | 23 | 0 | 23 |  |  | 11/22/2022 | Connected |  | Y
National Grid | BROCKTON | 198424 | 02301 | 2000 | Battery Add-On | 05_09_604W2 | 12/06/2018 | 01/19/2019 | 29 | 20 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2019 | 03/13/2019 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2023 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 194876 | 01535 | 9.92 | Solar | 05_05_344W1 | 08/31/2018 | 10/12/2018 | 8 | 7 | 1 | 10/15/2018 | 10/15/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 |  | 11/1/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2019 | Connected |  | N
National Grid | FRANKLIN | 707537 | 02038 | 11.5 | Solar | 05_12_16J4 | 07/25/2025 | 09/03/2025 | 3 | 0 | 3 | 09/17/2025 | 09/17/2025 | 20 | 4 | 16 | 10/30/2025 | 11/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 11/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 11/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 291554 | 01905 | 11.4 | Solar | 05_05_320W3 | 05/12/2020 | 05/14/2020 | 1 | 0 | 1 | 05/15/2020 | 05/15/2020 | 53 | 32 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  | 5/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2022 | Connected |  | Y
National Grid | GRAFTON | 393258 | 01560 | 15.2 | Solar | 05_07_910W25 | 11/05/2021 | 01/05/2022 | 32 | 26 | 6 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2022 |  | 3/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2022 | Connected |  | N
National Grid | PEMBROKE | 738237 | 02359 | 7.6 | Solar | 05_07_10W1 | 12/04/2025 | 12/05/2025 | 5 | 0 | 5 | 01/06/2026 | 01/06/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 | 12/04/2025 | 2/3/2027 | Y | EXP | 365 | 03/04/2026 | 03/03/2026 | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATTLEBORO | 240618 | 02703 | 3.8 | Solar | 05_01_207W1 | 10/10/2019 | 10/14/2019 | 1 | 0 | 1 | 10/15/2019 | 10/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2019 | 10/10/2019 | 7/7/2020 | Y | EXP | 365 | 02/12/2020 | 02/22/2020 | 10 | 0 | 10 |  |  | 4/21/2020 | Connected |  | N
National Grid | LEOMINSTER | 707554 | 01463 | 11.52 | Solar | 05_09_501L2 | 07/25/2025 | 09/08/2025 | 5 | 0 | 5 | 09/09/2025 | 09/09/2025 | 58 | 44 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARDWICK | 660345 | 01037 | 120 | Solar | 05_07_98W48 | 12/24/2024 | 01/10/2025 | 11 | 3 | 8 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 438769 | 02375 | 0 | Solar | 05_07_91W49 | 06/20/2022 | 06/21/2022 | 1 | 0 | 1 | 06/22/2022 | 06/22/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 | 06/20/2022 | 5/3/2024 | Y | EXP | 365 | 04/13/2023 | 05/03/2023 | 21 | 0 | 21 |  |  | 5/24/2023 | Connected |  | N
National Grid | BROCKTON | 363219 | 02301 | 6 | Solar | 05_09_604W2 | 06/25/2021 | 06/30/2021 | 4 | 2 | 2 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2021 |  | 9/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/5/2022 | Connected |  | N
National Grid | OAKHAM | 195928 | 01068 | 0 | Solar | 05_05_344W1 | 09/17/2018 | 10/01/2018 | 9 | 2 | 7 | 10/02/2018 | 10/02/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2019 | 09/17/2018 | 8/31/2019 | Y | EXP | 219 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | FRANKLIN | 175889 | 02038 | 56 | Solar | 05_12_16J4 | 05/27/2015 | 05/27/2015 | 1 | 1 | 0 | 05/29/2015 | 05/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2015 |  | 10/30/2015 | N | EXP | 129 |  |  | 0 | 0 | 0 | 6/30/2015 | 6/30/2015 | 1/25/2016 | Connected |  | N
National Grid | MALDEN | 328163 | 02148 | 7.6 | Solar | 05_05_320W3 | 11/24/2020 | 12/13/2021 | 4 | 0 | 4 | 12/03/2020 | 12/03/2020 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  | 5/27/2022 | N | EXP | 435 |  |  | 0 | 0 | 0 |  |  | 4/22/2022 | Connected |  | N
National Grid | GRAFTON | 431674 | 01560 | 0 | Battery Add-On | 05_07_910W25 | 07/06/2022 | 08/10/2022 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 740608 | 02359 | 11.5 | Solar | 05_07_10W1 | 12/16/2025 | 01/20/2026 | 3 | 0 | 3 | 02/05/2026 | 02/05/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ATTLEBORO | 406210 | 02703 | 7.6 | Solar | 05_01_207W1 | 05/06/2024 | 01/17/2022 | 0 | 0 | 0 | 05/07/2024 | 05/07/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 327667 | 01453 | 0 | Other | 05_09_503L1 | 04/06/2021 | 04/30/2021 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 670860 | 01082 | 7.6 | Solar | 05_07_98W49 | 02/07/2025 | 03/14/2025 | 5 | 0 | 5 | 03/25/2025 | 03/25/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 | 02/07/2025 | 5/5/2026 | Y | EXP | 365 | 05/16/2025 | 07/31/2025 | 77 | 0 | 77 |  |  |  | Completion Documents |  | N
National Grid | EASTON | 486521 | 02375 | 7.6 | Solar | 05_07_91W49 | 01/03/2023 | 01/27/2023 | 17 | 15 | 2 | 01/30/2023 | 01/30/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 3/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N
National Grid | BROCKTON | 539539 | 02301 | 0 | Battery Add-On | 05_09_604W2 | 07/13/2023 | 07/17/2023 | 2 | 0 | 2 | 07/18/2023 | 07/18/2023 | 129 | 104 | 25 | 02/16/2024 | 02/15/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/15/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 07/13/2023 | 3/21/2025 | Y | EXP | 365 | 05/29/2024 | 12/18/2024 | 204 | 0 | 204 |  |  | 8/12/2024 | Connected |  | N
National Grid | OAKHAM | 309857 | 01068 | 7.6 | Solar | 05_05_344W1 | 08/31/2020 | 09/01/2020 | 0 | 0 | 0 | 09/02/2020 | 09/02/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2020 | Connected |  | N
National Grid | FRANKLIN | 176667 | 02038 | 268.8 | Solar | 05_12_16J4 | 10/20/2015 | 10/20/2015 | 2 | 2 | 0 | 10/23/2015 | 10/23/2015 | 332 | 26 | 306 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2016 |  | 10/26/2016 | N | EXP | 274 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 382030 | 02148 | 19 | Solar | 05_05_320W3 | 09/14/2021 | 09/21/2021 | 6 | 5 | 1 | 09/22/2021 | 09/22/2021 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 9/20/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBRIDGE | 439708 | 01534 | 15.2 | Solar | 05_07_910W25 | 06/23/2022 | 06/27/2022 | 2 | 0 | 2 | 06/28/2022 | 06/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2022 | Connected |  | N
National Grid | PEMBROKE | 176695 | 02359 | 10 | Solar | 05_07_10W1 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 | 04/25/2016 | 04/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2016 |  | 4/30/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/25/2016 | 8/25/2016 | 8/29/2016 | Connected |  | N
National Grid | HOLBROOK | 412235 | 02343 | 0 | Battery Add-On | 05_01_207W1 | 07/22/2022 | 08/04/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2022 | 09/01/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 327663 | 01453 | 0 | Other | 05_09_503L1 | 04/06/2021 | 04/30/2021 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 686134 | 01082 | 5.76 | Solar | 05_07_98W49 | 04/18/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 04/18/2025 | 6/24/2026 | Y | EXP | 365 | 07/30/2025 | 08/28/2025 | 30 | 0 | 30 |  |  |  | Completion Documents |  | N
National Grid | EASTON | 487499 | 02375 | 15.2 | Solar | 05_07_91W49 | 12/27/2022 | 01/03/2023 | 4 | 2 | 2 | 01/04/2023 | 01/04/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 5/23/2024 | N | EXP | 39 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 611134 | 02301 | 9.88 | Solar | 05_09_604W2 | 05/15/2024 | 05/17/2024 | 2 | 1 | 1 | 05/20/2024 | 05/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OAKHAM | 330469 | 01068 | 10 | Solar | 05_05_344W1 | 12/08/2020 | 12/16/2020 | 5 | 0 | 5 | 12/17/2020 | 12/17/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/9/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 178608 | 02038 | 15.2 | Solar | 05_12_16J4 | 12/12/2017 | 12/12/2017 | 0 | 0 | 0 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 3/22/2019 | N | EXP | 443 |  |  | 0 | 0 | 0 |  |  | 6/6/2019 | Connected |  | N
National Grid | MALDEN | 411110 | 02148 | 19 | Solar | 05_05_320W3 | 02/09/2022 | 02/10/2022 | 1 | 0 | 1 | 02/11/2022 | 02/11/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBRIDGE | 464697 | 01534 | 9.984 | Solar | 05_07_910W25 | 09/30/2022 | 10/25/2022 | 16 | 16 | 0 | 10/26/2022 | 10/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  | 11/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2023 | Connected |  | N
National Grid | PEMBROKE | 176934 | 02359 | 180 | Solar | 05_07_10W1 | 01/28/2016 | 01/28/2016 | 4 | 4 | 0 | 02/03/2016 | 02/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 2/2/2017 | N | EXP | 345 |  |  | 0 | 0 | 0 | 11/29/2016 | 11/29/2016 | 12/5/2016 | Connected |  | N
National Grid | HOLBROOK | 437434 | 02343 | 0 | Other | 05_01_207W1 | 09/19/2022 | 10/20/2022 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2022 | 11/17/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 421650 | 01453 | 240 | Solar | 05_09_503L1 | 05/26/2022 | 06/14/2022 | 12 | 5 | 7 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 175497 | 01082 | 1889 | Solar | 05_07_98W49 | 09/26/2014 | 09/26/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2014 | 10/31/2014 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 489910 | 02375 | 10 | Solar | 05_07_91W49 | 04/25/2023 | 05/22/2023 | 20 | 19 | 1 | 05/23/2023 | 05/23/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 | 04/25/2023 | 8/1/2025 | Y | EXP | 365 | 10/18/2023 | 11/03/2023 | 17 | 0 | 17 |  |  | 10/15/2024 | Connected |  | N
National Grid | BROCKTON | 614764 | 02301 | 5 | Solar | 05_09_604W2 | 06/20/2024 | 06/24/2024 | 2 | 0 | 2 | 06/25/2024 | 06/25/2024 | 49 | 41 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2024 | Connected |  | N
National Grid | NEW BRAINTREE | 339026 | 01531 | 9.8 | Solar | 05_05_344W1 | 01/27/2021 | 02/03/2021 | 4 | 3 | 1 | 02/04/2021 | 02/04/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2021 |  | 2/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2021 | Connected |  | N
National Grid | FRANKLIN | 188285 | 02038 | 6 | Solar | 05_12_16J4 | 08/29/2018 | 06/15/2018 | 41 | 30 | 11 | 09/26/2018 | 09/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 |  | 10/15/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2019 | Connected |  | N
National Grid | MALDEN | 425276 | 02148 | 0 | Solar | 05_05_320W3 | 04/21/2022 | 04/29/2022 | 7 | 6 | 1 | 05/02/2022 | 05/02/2022 | 36 | 22 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 04/21/2022 | 1/11/2024 | Y | EXP | 5 | 12/29/2023 | 01/05/2024 | 8 | 0 | 8 |  |  | 1/5/2024 | Connected |  | N
National Grid | GRAFTON | 553060 | 01560 | 10 | Solar | 05_07_910W25 | 10/02/2023 | 10/05/2023 | 3 | 0 | 3 | 10/06/2023 | 10/06/2023 | 91 | 74 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 10/02/2023 | 2/26/2025 | Y | EXP | 365 | 03/14/2024 | 04/26/2024 | 44 | 0 | 44 |  |  | 7/10/2024 | Connected |  | N
National Grid | PEMBROKE | 177597 | 02359 | 324 | Solar | 05_07_10W1 | 07/18/2017 | 07/18/2017 | 43 | 43 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2017 | 11/27/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 | 07/18/2017 | 8/20/2021 | Y | STD | 57 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 477027 | 02343 | 6 | Solar | 05_01_207W1 | 03/07/2023 | 03/09/2023 | 2 | 1 | 1 | 03/10/2023 | 03/10/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2023 | 03/07/2023 | 6/8/2024 | Y | EXP | 365 | 06/09/2023 | 05/31/2023 | 64 | 0 | 64 |  |  | 8/7/2023 | Connected |  | N
National Grid | LEOMINSTER | 634442 | 01453 | 4980 | Solar | 05_09_503L1 | 12/04/2024 | 01/09/2025 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2025 | 02/10/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PALMER | 196581 | 01069 | 3.8 | Solar | 05_07_98W49 | 09/20/2018 | 10/12/2018 | 5 | 5 | 0 | 10/15/2018 | 10/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 9/9/2019 | Connected |  | N
National Grid | BROCKTON | 511260 | 02301 | 7.6 | Solar | 05_07_91W49 | 03/28/2023 |  | 215 | 209 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 631321 | 02302 | 7.6 | Solar | 05_09_604W2 | 08/08/2024 | 08/26/2024 | 3 | 0 | 3 | 08/27/2024 | 08/27/2024 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 | 08/08/2024 | 9/25/2025 | Y | EXP | 365 | 11/15/2024 | 06/23/2025 | 221 | 0 | 221 |  |  | 6/28/2025 | Connected |  | N
National Grid | OAKHAM | 339784 | 01068 | 10 | Solar | 05_05_344W1 | 02/01/2021 | 02/04/2021 | 2 | 0 | 2 | 02/05/2021 | 02/05/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 546731 | 02038 | 25 | Solar | 05_12_16J4 | 10/27/2023 | 11/07/2023 | 8 | 5 | 3 | 11/08/2023 | 11/08/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | N
National Grid | MALDEN | 427162 | 02148 | 9.8 | Solar | 05_05_320W3 | 06/29/2022 | 06/30/2022 | 1 | 0 | 1 | 07/01/2022 | 07/01/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2022 | Connected |  | N
National Grid | GRAFTON | 645357 | 01560 | 10 | Solar | 05_07_910W25 | 10/07/2024 | 10/18/2024 | 2 | 0 | 2 | 10/21/2024 | 10/21/2024 | 22 | 0 | 22 | 01/10/2025 | 02/07/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 02/07/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 2/19/2025 | 10/07/2024 | 3/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | PEMBROKE | 215628 | 02359 | 7.6 | Solar | 05_07_10W1 | 04/02/2019 | 04/10/2019 | 6 | 6 | 0 | 04/11/2019 | 04/11/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2019 | 04/02/2019 | 5/27/2020 | Y | EXP |  | 01/30/2020 | 02/19/2020 | 20 | 0 | 20 |  |  | 3/24/2020 | Connected |  | N
National Grid | HOLBROOK | 610626 | 02343 | 3.8 | Solar | 05_01_207W1 | 05/14/2024 | 05/23/2024 | 3 | 0 | 3 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 | 05/14/2024 | 12/31/2025 | Y | EXP | 365 | 05/06/2025 | 05/05/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 723341 | 01453 | 15.2 | Solar | 05_09_503L1 | 10/01/2025 | 10/07/2025 | 4 | 0 | 4 | 10/08/2025 | 10/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PALMER | 357829 | 01069 | 9.8 | Solar | 05_07_98W49 | 07/15/2021 | 07/16/2021 | 1 | 1 | 0 | 07/19/2021 | 07/19/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 |  | 7/15/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 515507 | 02301 | 12.16 | Solar | 05_07_91W49 | 04/18/2024 | 05/01/2024 | 10 | 8 | 2 | 05/02/2024 | 05/02/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 634131 | 02301 | 7.475 | Solar | 05_09_604W2 | 08/23/2024 | 10/14/2024 | 15 | 11 | 4 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 | 08/23/2024 | 11/18/2025 | Y | EXP | 365 | 12/31/2024 | 01/21/2025 | 22 | 0 | 22 |  |  | 1/24/2025 | Connected |  | N
National Grid | OAKHAM | 440655 | 01068 | 22.8 | Solar | 05_05_344W1 | 07/05/2022 | 07/08/2022 | 4 | 3 | 1 | 07/11/2022 | 07/11/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 12/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 546706 | 02038 | 25 | Solar | 05_12_16J4 | 11/07/2023 | 11/09/2023 | 2 | 0 | 2 | 11/10/2023 | 11/10/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | MALDEN | 487761 | 02148 | 15.2 | Solar | 05_05_320W3 | 12/22/2022 | 12/27/2022 | 2 | 0 | 2 | 12/28/2022 | 12/28/2022 | 73 | 50 | 23 | 05/03/2023 | 12/14/2023 | 154 | 25 | 129 |  |  | 0 | 0 | 0 |  | 12/14/2023 | 154 | 25 | 129 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 646996 | 01560 | 5.7 | Solar | 05_07_910W25 | 10/14/2024 | 11/01/2024 | 4 | 0 | 4 | 11/04/2024 | 11/04/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/14/2024 | 2/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | PEMBROKE | 297040 | 02359 | 10 | Solar | 05_07_10W1 | 09/25/2020 | 10/01/2020 | 3 | 0 | 3 | 10/02/2020 | 10/02/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 | 09/25/2020 | 9/1/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2021 | Connected |  | N
National Grid | HOLBROOK | 661867 | 02343 | 3.8 | Solar | 05_01_207W1 | 12/19/2024 |  | 79 | 75 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 175380 | 01453 | 499 | Solar | 05_09_503L1 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2014 | 08/14/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2015 | 07/09/2014 | 1/15/2016 | Y | STD | 39 | 08/03/2016 | 10/11/2016 | 47 | 0 | 47 | 3/17/2017 | 3/17/2017 | 10/17/2016 | Connected |  | N
National Grid | PALMER | 413113 | 01069 | 6 | Solar | 05_07_98W49 | 02/25/2022 | 03/01/2022 | 2 | 0 | 2 | 03/02/2022 | 03/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2022 | 02/25/2022 | 5/3/2023 | Y | EXP | 365 | 04/07/2022 | 05/02/2022 | 26 | 0 | 26 |  |  | 5/6/2022 | Connected |  | N
National Grid | BROCKTON | 522930 | 02301 | 6.38 | Solar | 05_07_91W49 | 05/18/2023 | 06/14/2023 | 18 | 17 | 1 | 06/15/2023 | 06/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 642285 | 02301 | 15.2 | Solar | 05_09_604W2 | 09/23/2024 | 09/25/2024 | 2 | 0 | 2 | 09/26/2024 | 09/26/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 |  | 11/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 456412 | 01535 | 16.24 | Solar | 05_05_344W1 | 11/08/2022 |  | 169 | 25 | 144 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 546570 | 02038 | 25 | Solar | 05_12_16J4 | 10/27/2023 | 10/30/2023 | 1 | 0 | 1 | 10/31/2023 | 10/31/2023 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2023 |  | 12/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | N
National Grid | MALDEN | 515069 | 02148 | 15.2 | Solar | 05_05_320W3 | 03/28/2023 | 03/29/2023 | 1 | 0 | 1 |  |  | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 651669 | 01519 | 9.92 | Solar | 05_07_910W25 | 11/01/2024 | 12/02/2024 | 5 | 0 | 5 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | PEMBROKE | 389949 | 02359 | 6 | Solar | 05_07_10W1 | 11/16/2021 | 01/06/2022 | 20 | 15 | 5 | 11/19/2021 | 11/19/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 652757 | 02343 | 17.6 | Solar | 05_01_207W2 | 11/14/2024 | 11/19/2024 | 1 | 0 | 1 | 04/17/2025 | 04/17/2025 | 46 | 26 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 |  | 7/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 175916 | 01453 | 252 | Solar | 05_09_503L1 | 03/12/2015 | 03/12/2015 | 8 | 6 | 2 | 03/26/2015 | 03/26/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2015 |  | 8/12/2015 | N | EXP | 134 |  |  | 0 | 0 | 0 | 4/10/2015 | 4/10/2015 | 11/19/2015 | Connected |  | N
National Grid | PALMER | 597382 | 01069 | 6 | Solar | 05_07_98W49 | 03/29/2024 | 04/03/2024 | 3 | 0 | 3 | 04/04/2024 | 04/04/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 03/29/2024 | 5/15/2025 | Y | EXP | 365 | 07/23/2024 | 08/09/2024 | 18 | 0 | 18 |  |  | 1/10/2025 | Connected |  | N
National Grid | BROCKTON | 559160 | 02301 | 7.875 | Solar | 05_07_91W49 | 10/12/2023 | 10/16/2023 | 3 | 1 | 2 | 10/17/2023 | 10/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 12/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2024 | Connected |  | N
National Grid | BROCKTON | 658509 | 02301 | 5.76 | Solar | 05_09_604W2 | 12/04/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | BARRE | 469770 | 01005 | 15.2 | Solar | 05_05_344W1 | 10/19/2022 | 10/21/2022 | 2 | 0 | 2 | 10/24/2022 | 10/24/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  | 12/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2023 | Connected |  | N
National Grid | FRANKLIN | 646234 | 02038 | 10 | Solar | 05_12_16J4 | 10/15/2024 | 10/16/2024 | 1 | 0 | 1 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 | 10/15/2024 | 2/5/2026 | Y | EXP | 365 | 04/16/2025 | 08/18/2025 | 125 | 0 | 125 |  |  | 10/3/2025 | Connected |  | N
National Grid | MALDEN | 520350 | 02148 | 9.86 | Solar | 05_05_320W3 | 04/27/2023 | 05/08/2023 | 7 | 4 | 3 | 05/09/2023 | 05/09/2023 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2023 |  | 8/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2023 | Connected |  | Y
National Grid | NORTHBRIDGE | 652723 | 01534 | 2000 | Other | 05_07_910W25 | 05/07/2025 | 06/17/2025 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/18/2025 | 07/17/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 424886 | 02359 | 100 | Solar | 05_07_10W1 | 05/31/2022 | 09/19/2022 | 76 | 68 | 8 | 09/20/2022 | 09/20/2022 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2022 |  | 7/30/2024 | N | EXP | 455 |  |  | 0 | 0 | 0 |  |  | 8/12/2024 | Connected |  | N
National Grid | HOLBROOK | 651785 | 02343 | 3.8 | Solar | 05_01_207W2 | 01/02/2025 | 02/12/2025 | 25 | 22 | 3 | 02/13/2025 | 02/13/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 176892 | 01453 | 2000 | Solar | 05_09_503L1 | 11/16/2015 | 11/16/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2015 | 12/21/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/21/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 606381 | 01069 | 7.6 | Solar | 05_07_98W49 | 04/24/2024 | 04/29/2024 | 1 | 0 | 1 | 04/30/2024 | 04/30/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 |  | 5/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 543562 | 02301 | 10 | Solar | 05_07_91W49 | 07/28/2023 | 08/01/2023 | 2 | 0 | 2 | 08/02/2023 | 08/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 664958 | 02301 | 15.2 | Solar | 05_09_604W2 | 01/10/2025 | 01/14/2025 | 2 | 0 | 2 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 01/10/2025 | 3/18/2026 | Y | EXP | 365 | 09/03/2025 | 09/02/2025 | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | BARRE | 515324 | 01005 | 14.5 | Solar | 05_05_344W1 | 04/18/2024 | 07/25/2024 | 66 | 61 | 5 | 07/26/2024 | 07/26/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2024 |  | 8/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2025 | Connected |  | N
National Grid | FRANKLIN | 530618 | 02038 | 0 | Solar | 05_12_16J5 | 06/01/2023 | 06/02/2023 | 1 | 0 | 1 | 06/05/2023 | 06/05/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2023 |  | 9/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | MALDEN | 559289 | 02148 | 7.25 | Solar | 05_05_320W3 | 11/09/2023 | 11/16/2023 | 4 | 1 | 3 | 11/17/2023 | 11/17/2023 | 69 | 48 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2024 | Connected |  | N
National Grid | GRAFTON | 676202 | 01560 | 4990 | Solar | 05_07_910W25 | 04/29/2025 | 05/27/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2025 | 07/02/2025 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 434918 | 02359 | 0 | Solar | 05_07_10W1 | 07/28/2022 | 08/02/2022 | 4 | 3 | 1 | 08/03/2022 | 08/03/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2022 |  | 1/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2023 | Connected |  | N
National Grid | HOLBROOK | 724260 | 02343 | 12.47 | Solar | 05_01_207W2 | 10/08/2025 | 12/01/2025 | 3 | 1 | 2 | 12/18/2025 | 12/18/2025 | 52 | 37 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 177313 | 01453 | 4290 | Solar | 05_09_503L1 | 02/10/2017 | 02/22/2017 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2017 | 02/23/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2018 | 02/10/2017 | 8/21/2020 | Y | STD | 526 | 07/16/2019 | 10/15/2019 | 91 | 0 | 91 |  |  | 8/20/2020 | Connected |  | N
National Grid | PALMER | 609927 | 01069 | 10 | Solar | 05_07_98W49 | 05/17/2024 |  | 41 | 40 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 543423 | 02301 | 3.8 | Solar | 05_07_91W49 | 07/27/2023 | 07/31/2023 | 2 | 0 | 2 | 08/01/2023 | 08/01/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 8/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | BROCKTON | 664799 | 02301 | 6.38 | Solar | 05_09_604W2 | 01/09/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 576378 | 01005 | 0 | Battery Add-On | 05_05_344W1 | 12/07/2023 | 12/12/2023 | 4 | 3 | 1 | 12/13/2023 | 12/13/2023 | 55 | 31 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 |  | 4/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | FRANKLIN | 658179 | 02038 | 5.76 | Solar | 05_12_16J5 | 12/04/2024 | 01/03/2025 | 4 | 2 | 2 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/04/2024 | 2/20/2026 | Y | EXP | 365 | 04/15/2025 | 04/30/2025 | 16 | 0 | 16 |  |  | 5/19/2025 | Connected |  | N
National Grid | MALDEN | 600585 | 02148 | 10 | Solar | 05_05_320W3 | 04/04/2024 | 04/10/2024 | 4 | 0 | 4 | 04/11/2024 | 04/11/2024 | 10 | 6 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 677102 | 01560 | 40 | Solar | 05_07_910W25 | 03/24/2025 | 03/27/2025 | 3 | 0 | 3 | 03/28/2025 | 03/28/2025 | 24 | 6 | 18 | 05/12/2025 | 05/20/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 05/20/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 5/27/2025 |  | 6/17/2026 | N | EXP | 365 | 07/30/2025 | 09/30/2025 | 63 | 0 | 63 |  |  | 1/22/2026 | Connected |  | N
National Grid | PEMBROKE | 473793 | 02359 | 11.4 | Solar | 05_07_10W1 | 12/07/2022 | 12/14/2022 | 6 | 4 | 2 | 12/15/2022 | 12/15/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 176161 | 02343 | 11 | Solar | 05_01_207W2 | 02/05/2015 | 02/05/2015 | 4 | 1 | 3 | 02/12/2015 | 02/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 6/24/2016 | N | EXP | 483 |  |  | 0 | 0 | 0 | 2/27/2015 | 2/27/2015 | 3/18/2016 | Connected |  | N
National Grid | LEOMINSTER | 177678 | 01453 | 72 | Solar | 05_09_503L1 | 07/21/2017 | 08/04/2017 | 9 | 6 | 3 | 08/04/2017 | 08/04/2017 | 161 | 0 | 161 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 7/29/2018 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 619247 | 01069 | 8.7 | Solar | 05_07_98W49 | 06/20/2024 | 06/28/2024 | 4 | 0 | 4 | 07/01/2024 | 07/01/2024 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2024 | Connected |  | N
National Grid | BROCKTON | 543283 | 02301 | 3.8 | Solar | 05_07_91W49 | 07/27/2023 | 07/28/2023 | 1 | 0 | 1 | 07/31/2023 | 07/31/2023 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2023 | 07/27/2023 | 10/15/2024 | Y | EXP | 365 | 03/15/2024 | 05/20/2024 | 67 | 0 | 67 |  |  | 6/10/2024 | Connected |  | N
National Grid | BROCKTON | 668996 | 02301 | 5.76 | Solar | 05_09_604W2 | 01/30/2025 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 | 01/30/2025 | 3/28/2026 | Y | EXP | 365 | 06/14/2025 | 11/21/2025 | 161 | 0 | 161 |  |  | 11/25/2025 | Connected |  | N
National Grid | OAKHAM | 651904 | 01068 | 5.7 | Solar | 05_05_344W1 | 11/09/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/09/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2025 | Connected |  | N
National Grid | FRANKLIN | 676531 | 02038 | 3.8 | Solar | 05_12_16J5 | 03/07/2025 | 03/26/2025 | 1 | 0 | 1 | 04/04/2025 | 04/04/2025 | 136 | 125 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 623382 | 02148 | 11.5 | Solar | 05_05_320W3 | 07/09/2024 | 07/12/2024 | 3 | 0 | 3 | 07/15/2024 | 07/15/2024 | 45 | 31 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 684020 | 01588 | 22.8 | Solar | 05_07_910W25 | 04/12/2025 | 04/16/2025 | 3 | 0 | 3 | 04/17/2025 | 04/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | PEMBROKE | 485772 | 02359 | 7.6 | Solar | 05_07_10W1 | 12/27/2022 | 12/29/2022 | 2 | 0 | 2 | 12/30/2022 | 12/30/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 12/27/2022 | 5/13/2024 | Y | EXP | 365 | 09/28/2023 | 10/26/2023 | 29 | 0 | 29 |  |  | 11/27/2023 | Connected |  | N
National Grid | HOLBROOK | 178351 | 02343 | 5 | Solar | 05_01_207W2 | 01/12/2018 | 01/12/2018 | 9 | 9 | 0 | 03/27/2018 | 03/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2018 | 01/12/2018 | 5/17/2019 | Y | EXP | 415 |  |  | 0 | 0 | 0 |  |  | 5/9/2019 | Connected |  | N
National Grid | LEOMINSTER | 177765 | 01453 | 3014 | Solar | 05_09_503L1 | 10/05/2017 | 10/05/2017 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2017 | 11/27/2017 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/11/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 639502 | 01069 | 10 | Solar | 05_07_98W49 | 10/10/2024 | 10/14/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/10/2024 | 2/4/2026 | Y | EXP | 365 | 04/18/2025 | 06/05/2025 | 49 | 0 | 49 |  |  | 6/11/2025 | Connected |  | N
National Grid | BROCKTON | 551871 | 02301 | 6 | Solar | 05_07_91W49 | 09/19/2023 | 10/03/2023 | 11 | 8 | 3 | 10/04/2023 | 10/04/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 2/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2024 | Connected |  | N
National Grid | BROCKTON | 685631 | 02301 | 5.76 | Solar | 05_09_604W2 | 04/16/2025 | 05/05/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 | 04/16/2025 | 6/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | OAKHAM | 707851 | 01068 | 0 | Solar | 05_05_344W1 | 07/28/2025 | 08/20/2025 | 14 | 10 | 4 | 08/21/2025 | 08/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2026 | Connected |  | N
National Grid | FRANKLIN | 175037 | 02038 | 300 | Solar | 05_12_16J6 | 09/20/2013 | 09/20/2013 | 12 | 5 | 7 | 10/09/2013 | 10/09/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2013 |  | 12/31/2013 | N | EXP | 64 |  |  | 0 | 0 | 0 | 12/23/2013 | 12/23/2013 | 12/27/2013 | Connected |  | N
National Grid | MALDEN | 626485 | 02148 | 10 | Solar | 05_05_320W3 | 07/22/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 | 07/22/2024 | 8/27/2025 | Y | EXP | 365 | 10/04/2024 | 10/22/2024 | 19 | 0 | 19 |  |  | 10/30/2024 | Connected |  | N
National Grid | GRAFTON | 701465 | 01560 | 5.76 | Solar | 05_07_910W25 | 06/26/2025 | 07/30/2025 | 3 | 0 | 3 | 07/31/2025 | 07/31/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 06/26/2025 | 10/1/2026 | Y | EXP | 365 | 11/05/2025 | 11/28/2025 | 24 | 0 | 24 |  |  | 12/4/2025 | Connected |  | N
National Grid | PEMBROKE | 487663 | 02359 | 960 | Solar | 05_07_10W1 | 01/27/2023 | 02/22/2023 | 17 | 8 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2023 | 03/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2023 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 178704 | 02343 | 10 | Solar | 05_01_207W2 | 03/20/2018 | 03/20/2018 | 22 | 20 | 2 | 09/24/2018 | 09/24/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 3/26/2019 | N | EXP | 182 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 178051 | 01453 | 4950 | Solar | 05_09_503L1 | 06/29/2017 | 08/10/2017 | 28 | 27 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/10/2017 | 08/31/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2018 | 06/29/2017 | 10/8/2020 | Y | STD | 643 | 08/06/2019 | 10/16/2019 | 71 | 0 | 71 | 7/30/2020 | 8/20/2020 | 10/7/2020 | Connected |  | N
National Grid | PALMER | 692715 | 01069 | 4.537 | Solar | 05_07_98W49 | 05/21/2025 | 06/12/2025 | 2 | 0 | 2 | 07/14/2025 | 07/14/2025 | 64 | 52 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 552507 | 02301 | 5.985 | Solar | 05_07_91W49 | 09/11/2023 | 09/12/2023 | 2 | 1 | 1 | 09/13/2023 | 09/13/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 700297 | 02302 | 120 | Hydro | 05_09_604W2 | 07/22/2025 | 07/25/2025 | 3 | 2 | 1 | 07/28/2025 | 07/28/2025 | 28 | 17 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 252380 | 01535 | 999 | Solar | 05_05_344W2 | 11/19/2019 | 12/19/2019 | 21 | 20 | 1 |  |  | 43 | 17 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2021 | 11/19/2019 | 2/17/2026 | Y | STD | 518 | 07/23/2024 |  | 592 | 260 | 332 |  |  |  | Construction |  | N
National Grid | FRANKLIN | 223160 | 02038 | 133.2 | Solar | 05_12_16J6 | 04/29/2019 | 05/16/2019 | 12 | 7 | 5 | 05/17/2019 | 05/17/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2019 |  | 6/21/2021 | N | EXP | 72 |  |  | 0 | 0 | 0 |  |  | 5/27/2021 | Connected |  | N
National Grid | MALDEN | 629924 | 02148 | 11.4 | Solar | 05_05_320W3 | 08/14/2024 | 08/19/2024 | 3 | 0 | 3 | 08/20/2024 | 08/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 11/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | WHITINSVILLE | 747871 | 01588 | 15.2 | Solar | 05_07_910W25 | 01/28/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 523316 | 02359 | 10 | Solar | 05_07_10W1 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  | 11/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2023 | Connected |  | N
National Grid | HOLBROOK | 187189 | 02343 | 200 | Solar | 05_01_207W2 | 07/02/2018 | 07/02/2018 | 15 | 1 | 14 | 07/26/2018 | 07/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2018 |  | 12/31/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2019 | Connected |  | N
National Grid | LEOMINSTER | 178061 | 01453 | 2640 | Solar | 05_09_503L1 | 09/01/2017 | 09/26/2017 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2017 | 11/07/2017 | 28 | 15 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 |  | 9/14/2020 | N | STD | 689 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 632686 | 01069 | 0 | Solar | 05_07_99W32 | 08/14/2024 | 10/07/2024 | 28 | 24 | 4 | 10/08/2024 | 10/08/2024 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2025 | Terminated |  | N
National Grid | BROCKTON | 555644 | 02301 | 5 | Solar | 05_07_91W49 | 10/11/2023 | 10/16/2023 | 3 | 0 | 3 | 10/17/2023 | 10/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2023 |  | 12/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2024 | Connected |  | N
National Grid | BROCKTON | 702660 | 02301 | 13.8 | Solar | 05_09_604W2 | 07/03/2025 | 08/26/2025 | 4 | 0 | 4 | 09/17/2025 | 09/17/2025 | 62 | 50 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OAKHAM | 199270 | 01068 | 250 | Solar | 05_05_344W2 | 01/04/2019 | 01/08/2019 | 1 | 0 | 1 | 01/09/2019 | 01/09/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 291626 | 02038 | 24.36 | Solar | 05_12_16J6 | 05/12/2020 | 05/14/2020 | 1 | 0 | 1 | 05/15/2020 | 05/15/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2020 |  | 5/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2020 | Connected |  | N
National Grid | MALDEN | 650597 | 02148 | 7.6 | Solar | 05_05_320W3 | 10/30/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/30/2024 | 1/26/2026 | Y | EXP | 365 | 01/16/2025 | 02/27/2025 | 43 | 0 | 43 |  |  | 7/31/2025 | Connected |  | N
National Grid | GRAFTON | 391839 | 01560 | 0 | Other | 05_07_910W26 | 11/11/2021 | 01/05/2022 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 03/02/2022 | 38 | 4 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 529626 | 02359 | 6 | Solar | 05_07_10W1 | 06/01/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2023 | 06/01/2023 | 7/19/2024 | Y | EXP | 365 | 01/13/2024 | 03/04/2024 | 52 | 0 | 52 |  |  | 3/9/2024 | Connected |  | N
National Grid | HOLBROOK | 196330 | 02343 | 7.6 | Solar | 05_01_207W2 | 11/29/2018 | 12/19/2018 | 13 | 6 | 7 | 12/20/2018 | 12/20/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 11/29/2018 | 1/27/2021 | Y | EXP | 365 | 05/26/2021 | 06/24/2021 | 29 | 0 | 29 |  |  | 10/12/2021 | Connected |  | N
National Grid | LEOMINSTER | 178238 | 01453 | 6 | Solar | 05_09_503L1 | 02/20/2018 | 02/20/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2018 |  | 2/25/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 8/7/2018 | Connected |  | N
National Grid | PALMER | 175890 | 01069 | 56 | Solar | 05_07_99W32 | 05/27/2015 | 05/27/2015 | 1 | 1 | 0 | 05/29/2015 | 05/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2015 |  | 10/30/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 12/15/2015 | Connected |  | N
National Grid | BROCKTON | 566403 | 02301 | 6 | Solar | 05_07_91W49 | 11/16/2023 | 11/27/2023 | 6 | 0 | 6 | 11/28/2023 | 11/28/2023 | 89 | 68 | 21 | 05/01/2024 | 06/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 06/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 6/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 309808 | 02301 | 960 | Solar | 05_09_604W3 | 08/17/2021 | 01/18/2022 | 104 | 96 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2022 | 11/21/2022 | 212 | 205 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTH BROOKFIELD | 206339 | 01535 | 499.5 | Solar | 05_05_344W2 | 02/06/2020 | 02/21/2020 | 10 | 6 | 4 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 | 02/06/2020 | 10/5/2023 | Y | STD | 442 | 04/30/2023 | 04/30/2023 | 1 | 1 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | FRANKLIN | 669885 | 02038 | 7.54 | Solar | 05_12_16J6 | 02/06/2025 | 03/18/2025 | 12 | 7 | 5 | 03/19/2025 | 03/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | MALDEN | 679652 | 02148 | 7.6 | Solar | 05_05_320W3 | 03/24/2025 | 04/25/2025 | 24 | 20 | 4 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 676968 | 01534 | 750 | Solar | 05_07_910W51 | 04/11/2025 | 06/27/2025 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2025 | 07/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PEMBROKE | 534907 | 02359 | 7.6 | Solar | 05_07_10W1 | 06/28/2023 | 06/29/2023 | 2 | 1 | 1 | 06/30/2023 | 06/30/2023 | 52 | 25 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 198844 | 02343 | 10 | Solar | 05_01_207W2 | 11/08/2018 | 11/20/2018 | 5 | 0 | 5 | 11/21/2018 | 11/21/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  | 12/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | Connected |  | N
National Grid | LEOMINSTER | 178758 | 01453 | 1000 | Solar | 05_09_503L1 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD |  | 10/13/2016 | 03/20/2017 | 106 | 0 | 106 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 177255 | 01069 | 35 | Solar | 05_07_99W32 | 08/17/2016 | 08/17/2016 | 282 | 282 | 0 | 10/03/2017 | 10/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2017 |  | 2/28/2018 | N | EXP | 147 |  |  | 0 | 0 | 0 | 1/22/2018 | 1/22/2018 | 1/19/2018 | Connected |  | N
National Grid | BROCKTON | 561903 | 02301 | 15.2 | Solar | 05_07_91W49 | 10/10/2023 | 10/20/2023 | 8 | 6 | 2 | 10/23/2023 | 10/23/2023 | 28 | 16 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 336793 | 02301 | 0 | Solar | 05_09_604W3 | 04/06/2021 | 04/30/2021 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/02/2021 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BARRE | 346796 | 01005 | 250 | Solar | 05_05_344W2 | 06/01/2021 | 07/28/2021 | 40 | 32 | 8 |  |  | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2022 | 06/01/2021 | 10/17/2024 | Y | STD | 386 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 732515 | 02038 | 7.678 | Solar | 05_12_16W1 | 11/09/2025 | 12/02/2025 | 14 | 10 | 4 | 12/03/2025 | 12/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MALDEN | 680520 | 02148 | 3.8 | Solar | 05_05_320W3 | 03/25/2025 | 04/15/2025 | 7 | 2 | 5 | 04/16/2025 | 04/16/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 175661 | 01534 | 70 | Solar | 05_07_910W51 | 05/23/2014 | 05/23/2014 | 5 | 2 | 3 | 06/03/2014 | 06/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2014 |  | 8/29/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 7/2/2014 | 7/2/2014 | 11/19/2014 | Connected |  | N
National Grid | PEMBROKE | 631154 | 02359 | 7.6 | Solar | 05_07_10W1 | 08/08/2024 | 08/15/2024 | 1 | 0 | 1 | 08/16/2024 | 08/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 08/08/2024 | 8/30/2025 | Y | EXP | 365 | 10/03/2024 | 11/06/2024 | 35 | 0 | 35 |  |  | 2/25/2025 | Connected |  | N
National Grid | HOLBROOK | 204913 | 02343 | 3.8 | Solar | 05_01_207W2 | 01/30/2019 | 02/12/2019 | 8 | 0 | 8 | 02/13/2019 | 02/13/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 178757 | 01453 | 1000 | Solar | 05_09_503L1 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD |  | 10/13/2016 | 03/20/2017 | 106 | 0 | 106 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 177306 | 01069 | 936 | Solar | 05_07_99W32 | 11/16/2016 | 11/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/01/2017 | 12/18/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2018 | 11/16/2016 | 8/11/2021 | Y | STD | 197 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 568459 | 02190 | 15.2 | Solar | 05_07_91W49 | 11/22/2023 | 12/18/2023 | 17 | 14 | 3 | 12/19/2023 | 12/19/2023 | 83 | 28 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 319692 | 02301 | 250 | Solar | 05_09_604W3 | 10/20/2020 | 12/07/2020 | 31 | 25 | 6 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | OAKHAM | 346790 | 01068 | 300 | Solar | 05_05_344W2 | 06/01/2021 | 07/28/2021 | 40 | 32 | 8 |  |  | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2022 | 06/01/2021 | 5/6/2025 | Y | STD | 386 | 02/28/2025 | 03/24/2025 | 25 | 25 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | FRANKLIN | 188457 | 02038 | 9.92 | Solar | 05_12_16W1 | 06/18/2018 | 06/18/2018 | 21 | 21 | 0 | 08/22/2018 | 08/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 |  | 11/15/2019 | N | EXP | 45 |  |  | 0 | 0 | 0 |  |  | 10/6/2019 | Connected |  | N
National Grid | MALDEN | 684546 | 02148 | 3.48 | Solar | 05_05_320W3 | 04/11/2025 | 05/05/2025 | 1 | 0 | 1 | 05/06/2025 | 05/06/2025 | 42 | 26 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 175884 | 01534 | 15.2 | Solar | 05_07_910W51 | 05/20/2015 | 05/20/2015 | 1 | 1 | 0 | 05/27/2015 | 05/27/2015 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2015 |  | 10/30/2015 | N | EXP | 134 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 642755 | 02339 | 7.6 | Solar | 05_07_10W1 | 09/25/2024 | 10/01/2024 | 4 | 0 | 4 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | HOLBROOK | 205332 | 02343 | 9.6 | Solar | 05_01_207W2 | 01/07/2019 | 02/05/2019 | 10 | 1 | 9 | 02/06/2019 | 02/06/2019 | 301 | 0 | 301 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 | 01/07/2019 | 7/22/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 178756 | 01453 | 2550 | Solar | 05_09_503L1 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2012 | 05/16/2012 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2014 | 12/27/2011 | 4/30/2016 | Y | STD | 65 | 10/13/2016 | 03/20/2017 | 106 | 0 | 106 | 7/13/2017 | 7/13/2017 | 3/31/2017 | Connected |  | N
National Grid | PALMER | 177326 | 01069 | 828 | Solar | 05_07_99W32 | 06/20/2016 | 06/20/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/24/2016 | 08/03/2016 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 568062 | 02351 | 6 | Solar | 05_07_91W49 | 11/16/2023 |  | 73 | 27 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 433961 | 02301 | 996 | Other | 05_09_604W3 | 08/18/2022 | 10/03/2022 | 32 | 22 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/04/2022 | 10/27/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NEW BRAINTREE | 346755 | 01531 | 297 | Solar | 05_05_344W2 | 06/01/2021 | 07/28/2021 | 40 | 32 | 8 |  |  | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2022 | 06/01/2021 | 4/19/2025 | Y | STD | 386 | 03/08/2025 | 04/03/2025 | 27 | 17 | 10 |  |  | 4/28/2025 | Connected |  | N
National Grid | FRANKLIN | 199644 | 02038 | 11.4 | Solar | 05_12_16W1 | 12/03/2018 | 12/17/2018 | 9 | 0 | 9 | 12/18/2018 | 12/18/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2019 | 12/03/2018 | 12/3/2020 | Y | EXP | 365 | 01/29/2020 | 02/05/2020 | 7 | 0 | 7 |  |  | 4/15/2020 | Connected |  | N
National Grid | MALDEN | 685316 | 02148 | 7.6 | Solar | 05_05_320W3 | 04/15/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 | 04/15/2025 | 7/2/2026 | Y | EXP | 365 | 09/16/2025 | 12/02/2025 | 78 | 0 | 78 |  |  | 2/17/2026 | Connected |  | N
National Grid | WHITINSVILLE | 176278 | 01588 | 98 | Solar | 05_07_910W51 | 05/05/2015 | 05/05/2015 | 1 | 1 | 0 | 05/08/2015 | 05/08/2015 | 418 | 0 | 418 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2015 | 05/05/2015 | 10/30/2015 | Y | EXP | 17 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 643090 | 02359 | 10 | Solar | 05_07_10W1 | 11/07/2024 | 11/20/2024 | 3 | 0 | 3 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | HOLBROOK | 317534 | 02343 | 50 | Solar | 05_01_207W2 | 10/06/2020 | 10/15/2020 | 5 | 0 | 5 | 10/16/2020 | 10/16/2020 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2021 | Connected |  | N
National Grid | LEOMINSTER | 195621 | 01453 | 4885 | Solar | 05_09_503L1 | 10/17/2018 | 11/06/2018 | 10 | 0 | 10 |  |  | 30 | 28 | 2 |  |  | 0 | 0 | 0 | 11/07/2018 | 12/15/2018 | 30 | 28 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 178091 | 01069 | 3.8 | Solar | 05_07_99W32 | 07/07/2017 | 07/07/2017 | 7 | 6 | 1 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/15/2018 | N | EXP | 36 |  |  | 0 | 0 | 0 | 1/5/2018 | 1/5/2018 | 1/5/2018 | Connected |  | N
National Grid | WEYMOUTH | 570456 | 02190 | 0 | Solar | 05_07_91W49 | 11/10/2023 | 11/16/2023 | 5 | 3 | 2 | 11/17/2023 | 11/17/2023 | 104 | 91 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2024 | Connected |  | N
National Grid | BROCKTON | 531613 | 02301 | 4999 | Other | 05_09_604W3 | 06/29/2023 | 07/26/2023 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2023 | 08/29/2023 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NEW BRAINTREE | 401364 | 01531 | 0 | Battery Add-On | 05_05_344W2 | 03/08/2022 | 03/22/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2022 | 03/25/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 207669 | 02038 | 10 | Solar | 05_12_16W1 | 02/01/2019 | 02/22/2019 | 2 | 1 | 1 | 02/25/2019 | 02/25/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2019 |  | 11/15/2019 | N | EXP | 256 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | MALDEN | 708476 | 02148 | 15.2 | Solar | 05_05_320W3 | 07/30/2025 | 08/05/2025 | 4 | 0 | 4 | 08/06/2025 | 08/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2025 | Connected |  | N
National Grid | GRAFTON | 184731 | 01560 | 25 | Solar | 05_07_910W51 | 05/15/2018 | 05/15/2018 | 40 | 20 | 20 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 7/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2018 | Connected |  | N
National Grid | PEMBROKE | 654829 | 02359 | 5.76 | Solar | 05_07_10W1 | 11/19/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 331470 | 02343 | 3.36 | Solar | 05_01_207W2 | 02/13/2021 | 02/16/2021 | 0 | 0 | 0 | 02/17/2021 | 02/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/15/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 197020 | 01453 | 3840 | Solar | 05_09_503L1 | 09/27/2018 | 10/30/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2018 | 11/28/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 194141 | 01069 | 660 | Solar | 05_07_99W32 | 10/09/2018 | 10/30/2018 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2018 | 11/30/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 577152 | 02188 | 8.7 | Solar | 05_07_91W49 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 12/27/2023 | 4/20/2025 | Y | EXP | 365 | 06/27/2024 | 07/17/2024 | 21 | 0 | 21 |  |  | 9/11/2024 | Connected |  | N
National Grid | BROCKTON | 570272 | 02301 | 1500 | Solar | 05_09_604W3 | 12/05/2023 | 02/28/2024 | 57 | 48 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/29/2024 | 02/29/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 | 12/05/2023 | 6/10/2026 | Y | STD | 112 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEW BRAINTREE | 434015 | 01531 | 0 | Battery Add-On | 05_05_344W2 | 07/06/2022 | 08/01/2022 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2022 | 08/29/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 291578 | 02038 | 7.6 | Solar | 05_12_16W1 | 05/20/2020 | 05/27/2020 | 3 | 0 | 3 | 05/28/2020 | 05/28/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/20/2020 | 9/9/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2021 | Connected |  | N
National Grid | MALDEN | 716907 | 02148 | 7.68 | Solar | 05_05_320W3 | 09/04/2025 | 10/15/2025 | 3 | 0 | 3 | 10/30/2025 | 10/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 186391 | 01560 | 249.8 | Solar | 05_07_910W51 | 07/05/2018 | 07/05/2018 | 9 | 0 | 9 | 07/20/2018 | 07/20/2018 | 26 | 4 | 22 | 08/31/2018 | 09/11/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  | 09/11/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 679789 | 02339 | 5.76 | Solar | 05_07_10W1 | 03/26/2025 | 07/03/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 58 | 40 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/26/2025 | Connected |  | N
National Grid | HOLBROOK | 340616 | 02343 | 57.6 | Solar | 05_01_207W2 | 03/30/2021 | 12/09/2021 | 9 | 0 | 9 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  | 6/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2021 | Connected |  | N
National Grid | LEOMINSTER | 201424 | 01453 | 4290 | Solar | 05_09_503L1 | 12/07/2018 | 01/09/2019 | 20 | 12 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2019 | 02/06/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 205175 | 01069 | 0 | Solar | 05_07_99W32 | 01/07/2019 | 01/17/2019 | 7 | 0 | 7 | 01/22/2019 | 01/22/2019 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 3/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2019 | Connected |  | N
National Grid | WEYMOUTH | 578264 | 02188 | 10 | Solar | 05_07_91W49 | 02/14/2024 | 02/16/2024 | 2 | 0 | 2 | 02/20/2024 | 02/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 660297 | 02301 | 225 | Solar | 05_09_604W3 | 12/12/2024 | 01/14/2025 | 22 | 12 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BARRE | 175069 | 01005 | 0 | Solar | 05_05_344W3 | 04/03/2013 | 04/03/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/15/2013 | 06/24/2013 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2014 | 04/03/2013 | 6/30/2014 | Y | STD | 88 | 09/22/2014 | 03/30/2015 | 127 | 0 | 127 | 5/11/2015 | 5/11/2015 | 5/22/2015 | Terminated |  | N
National Grid | FRANKLIN | 346151 | 02038 | 19.893 | Solar | 05_12_16W1 | 03/10/2021 | 03/17/2021 | 4 | 4 | 0 | 03/18/2021 | 03/18/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 |  | 3/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2021 | Connected |  | N
National Grid | SAUGUS | 177459 | 01906 | 3000 | Solar | 05_05_320W5 | 12/09/2016 | 12/09/2016 | 43 | 43 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/14/2017 | 05/10/2017 | 59 | 45 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/17/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Terminated |  | N
National Grid | WHITINSVILLE | 207469 | 01588 | 10 | Solar | 05_07_910W51 | 02/01/2019 | 02/07/2019 | 4 | 4 | 0 | 02/08/2019 | 02/08/2019 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 | 02/01/2019 | 10/22/2019 | Y | EXP | 242 | 05/11/2019 | 05/28/2019 | 17 | 0 | 17 |  |  | 6/11/2019 | Connected |  | N
National Grid | HANOVER | 681924 | 02339 | 3.8 | Solar | 05_07_10W1 | 04/01/2025 | 04/16/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2025 | Connected |  | N
National Grid | HOLBROOK | 350603 | 02343 | 9.86 | Solar | 05_01_207W2 | 04/02/2021 | 04/22/2021 | 13 | 13 | 0 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 4/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2021 | Connected |  | N
National Grid | LEOMINSTER | 329775 | 01453 | 15.2 | Solar | 05_09_503L1 | 12/04/2020 | 12/08/2020 | 1 | 0 | 1 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 223586 | 01069 | 100 | Solar | 05_07_99W32 | 04/29/2019 | 05/21/2019 | 16 | 14 | 2 | 05/22/2019 | 05/22/2019 | 13 | 3 | 10 | 07/17/2019 | 08/20/2020 | 277 | 240 | 37 |  |  | 0 | 0 | 0 |  | 08/20/2020 | 277 | 240 | 37 |  |  | 0 | 0 | 0 | 9/9/2020 |  | 6/23/2022 | N | EXP | 365 | 03/02/2021 | 06/10/2021 | 100 | 0 | 100 |  |  | 12/27/2021 | Connected |  | N
National Grid | WEYMOUTH | 584131 | 02190 | 10 | Solar | 05_07_91W49 | 01/24/2024 | 03/05/2024 | 28 | 26 | 2 | 03/06/2024 | 03/06/2024 | 14 | 12 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 | 01/24/2024 | 4/15/2025 | Y | EXP | 365 | 05/15/2024 | 05/17/2024 | 3 | 0 | 3 |  |  | 6/12/2024 | Connected |  | N
National Grid | BROCKTON | 666567 | 02301 | 4980 | Solar | 05_09_604W3 | 02/07/2025 | 03/07/2025 | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2025 | 04/29/2025 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BARRE | 734238 | 01005 | 720 | Solar | 05_05_344W3 | 12/11/2025 |  | 27 | 24 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | FRANKLIN | 362215 | 02038 | 7.6 | Solar | 05_12_16W1 | 07/19/2021 | 12/29/2021 | 1 | 0 | 1 | 07/21/2021 | 07/21/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2021 | 07/19/2021 | 1/28/2023 | Y | EXP | 365 | 01/29/2022 | 01/28/2022 | 0 | 0 | 0 |  |  | 3/16/2022 | Connected |  | N
National Grid | SAUGUS | 657149 | 01906 | 7.6 | Solar | 05_05_320W5 | 11/26/2024 | 03/24/2025 | 48 | 43 | 5 | 03/25/2025 | 03/25/2025 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBRIDGE | 211159 | 01534 | 262.5 | Natural Gas | 05_07_910W51 | 09/13/2019 | 11/05/2019 | 36 | 27 | 9 | 11/06/2019 | 11/06/2019 | 8 | 0 | 8 | 12/26/2019 | 04/27/2020 | 84 | 46 | 38 |  |  | 0 | 0 | 0 |  | 04/27/2020 | 84 | 46 | 38 |  |  | 0 | 0 | 0 | 5/22/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 693001 | 02339 | 5.76 | Solar | 05_07_10W1 | 05/26/2025 | 07/01/2025 | 4 | 0 | 4 | 07/02/2025 | 07/02/2025 | 68 | 50 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 369937 | 02343 | 28.8 | Solar | 05_01_207W2 | 08/09/2021 | 01/05/2022 | 1 | 0 | 1 | 08/11/2021 | 08/11/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2021 |  | 9/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2022 | Connected |  | N
National Grid | LEOMINSTER | 342869 | 01453 | 10 | Solar | 05_09_503L1 | 03/19/2021 | 03/26/2021 | 4 | 1 | 3 | 03/29/2021 | 03/29/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 248006 | 01069 | 7.6 | Solar | 05_07_99W32 | 10/01/2019 | 10/03/2019 | 1 | 0 | 1 | 10/04/2019 | 10/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  | 10/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 586610 | 02351 | 7.6 | Solar | 05_07_91W49 | 02/09/2024 | 03/05/2024 | 16 | 13 | 3 | 03/06/2024 | 03/06/2024 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 | 02/09/2024 | 4/11/2025 | Y | EXP | 365 | 08/27/2024 | 10/03/2024 | 38 | 0 | 38 |  |  | 1/16/2025 | Connected |  | N
National Grid | BROCKTON | 690051 | 02301 | 996 | Solar | 05_09_604W3 | 06/03/2025 | 07/14/2025 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2025 | 08/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BARRE | 174285 | 01005 | 30 | Solar | 05_05_344W3 | 11/15/2011 | 11/15/2011 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2012 |  | 1/23/2012 | N | EXP | 88 |  |  | 0 | 0 | 0 | 7/5/2012 | 7/5/2012 | 7/24/2012 | Connected |  | N
National Grid | FRANKLIN | 389679 | 02038 | 8.027 | Solar | 05_12_16W1 | 10/25/2021 | 01/03/2022 | 3 | 3 | 0 | 10/27/2021 | 10/27/2021 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 | 10/25/2021 | 12/29/2022 | Y | EXP | 365 | 01/13/2022 | 01/26/2022 | 14 | 0 | 14 |  |  | 8/23/2022 | Connected |  | N
National Grid | MALDEN | 677259 | 02148 | 100 | Solar | 05_05_320W5 | 03/24/2025 | 05/19/2025 | 39 | 30 | 9 |  |  | 40 | 15 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | GRAFTON | 265163 | 01560 | 250 | Solar | 05_07_910W51 | 01/08/2020 | 01/27/2020 | 11 | 11 | 0 | 01/28/2020 | 01/28/2020 | 25 | 12 | 13 | 04/10/2020 | 05/05/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 05/05/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 7/13/2020 | 01/08/2020 | 6/12/2023 | Y | EXP | 533 | 06/28/2021 | 06/22/2022 | 360 | 160 | 200 |  |  | 4/11/2023 | Connected |  | N
National Grid | PEMBROKE | 735843 | 02359 | 200 | Solar | 05_07_11W1 | 11/25/2025 | 01/06/2026 | 27 | 21 | 6 | 01/07/2026 | 01/07/2026 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HOLBROOK | 390483 | 02343 | 4.8 | Solar | 05_01_207W2 | 11/09/2021 | 01/10/2022 | 4 | 2 | 2 | 11/17/2021 | 11/17/2021 | 41 | 26 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 | 11/09/2021 | 9/21/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/18/2023 | Connected |  | N
National Grid | LEOMINSTER | 390310 | 01453 | 15.2 | Solar | 05_09_503L1 | 11/01/2021 | 11/03/2021 | 2 | 0 | 2 | 11/04/2021 | 11/04/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 11/2/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 279479 | 01069 | 7.6 | Solar | 05_07_99W32 | 02/13/2020 | 02/18/2020 | 1 | 0 | 1 | 02/19/2020 | 02/19/2020 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2020 | Connected |  | N
National Grid | WEYMOUTH | 588333 | 02190 | 6.96 | Solar | 05_07_91W49 | 02/14/2024 | 02/20/2024 | 3 | 0 | 3 | 02/21/2024 | 02/21/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 690043 | 02301 | 996 | Solar | 05_09_604W3 | 06/03/2025 | 07/17/2025 | 30 | 20 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2025 | 08/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NEW BRAINTREE | 174278 | 01531 | 1725 | Solar | 05_05_344W3 | 12/30/2011 | 12/30/2011 | 25 | 0 | 25 | 02/07/2012 | 02/07/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2013 | 12/30/2011 | 7/2/2012 | Y | EXP | 185 | 04/19/2013 | 06/14/2013 | 39 | 0 | 39 | 7/1/2013 | 7/1/2013 | 7/3/2013 | Connected |  | N
National Grid | FRANKLIN | 422479 | 02038 | 9.57 | Solar | 05_12_16W1 | 04/20/2022 | 04/21/2022 | 1 | 0 | 1 | 04/22/2022 | 04/22/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2022 | 04/20/2022 | 10/20/2023 | Y | EXP | 365 | 09/14/2022 | 10/14/2022 | 31 | 0 | 31 |  |  | 2/15/2023 | Connected |  | N
National Grid | SAUGUS | 710740 | 01906 | 10 | Solar | 05_05_320W5 | 08/08/2025 | 10/10/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 35 | 17 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SUTTON | 270336 | 01590 | 400 | Solar | 05_07_910W51 | 12/26/2019 | 01/15/2020 | 13 | 12 | 1 |  |  | 7 | 2 | 5 |  |  | 0 | 0 | 0 | 01/16/2020 | 02/05/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 | 12/26/2019 | 1/2/2023 | Y | STD | 533 | 01/27/2022 | 06/08/2022 | 133 | 0 | 133 |  |  | 9/20/2022 | Connected |  | N
National Grid | HANOVER | 175450 | 02339 | 45 | Solar | 05_07_11W1 | 07/15/2014 | 07/15/2014 | 5 | 2 | 3 | 07/23/2014 | 07/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2014 |  | 10/31/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 10/1/2014 | 10/1/2014 | 6/25/2015 | Connected |  | N
National Grid | HOLBROOK | 475067 | 02343 | 5.22 | Solar | 05_01_207W2 | 02/13/2023 | 02/17/2023 | 5 | 3 | 2 | 02/21/2023 | 02/21/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 | 02/13/2023 | 11/15/2024 | Y | EXP | 365 | 12/14/2023 | 12/22/2023 | 9 | 3 | 6 |  |  | 12/29/2023 | Connected |  | N
National Grid | LEOMINSTER | 440288 | 01453 | 18.85 | Solar | 05_09_503L1 | 06/27/2022 | 06/30/2022 | 4 | 1 | 3 | 09/09/2022 | 09/09/2022 | 14 | 14 | 0 | 10/05/2022 | 11/09/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 11/09/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 11/17/2022 |  | 3/5/2024 | N | EXP | 365 | 01/07/2023 | 03/06/2023 | 59 | 0 | 59 |  |  | 3/9/2023 | Connected |  | N
National Grid | PALMER | 303572 | 01069 | 8 | Solar | 05_07_99W32 | 07/28/2020 | 07/31/2020 | 3 | 3 | 0 | 08/03/2020 | 08/03/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 588823 | 02190 | 6 | Solar | 05_07_91W49 | 02/14/2024 | 02/20/2024 | 3 | 0 | 3 | 02/21/2024 | 02/21/2024 | 12 | 6 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 689991 | 02301 | 4980 | Solar | 05_09_604W3 | 06/03/2025 | 07/09/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 07/29/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BARRE | 174458 | 01005 | 82 | Solar | 05_05_344W3 | 10/06/2011 | 10/06/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 1/8/2014 | 1/8/2014 | 1/13/2014 | Connected |  | N
National Grid | FRANKLIN | 468441 | 02038 | 7.6 | Solar | 05_12_16W1 | 10/21/2022 | 10/26/2022 | 3 | 0 | 3 | 10/27/2022 | 10/27/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/21/2022 | 7/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2023 | Connected |  | N
National Grid | SAUGUS | 730431 | 01906 | 10 | Solar | 05_05_320W5 | 11/03/2025 | 11/10/2025 | 5 | 0 | 5 | 11/12/2025 | 11/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SUTTON | 287125 | 01590 | 43.2 | Solar | 05_07_910W51 | 04/13/2020 | 04/22/2020 | 6 | 3 | 3 |  |  | 30 | 7 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/13/2020 | 12/4/2023 | Y | STD | 631 |  |  | 0 | 0 | 0 |  |  | 5/26/2023 | Connected |  | N
National Grid | PEMBROKE | 202010 | 02359 | 6.4 | Solar | 05_07_11W1 | 11/26/2018 | 12/20/2018 | 14 | 14 | 0 | 12/21/2018 | 12/21/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 1/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2019 | Connected |  | N
National Grid | HOLBROOK | 484968 | 02343 | 8.99 | Solar | 05_01_207W2 | 12/15/2022 | 12/26/2022 | 7 | 1 | 6 | 12/27/2022 | 12/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 | 12/15/2022 | 10/25/2024 | Y | EXP | 365 | 07/18/2023 | 10/20/2023 | 95 | 0 | 95 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 465144 | 01453 | 50 | Solar | 05_09_503L1 | 10/03/2022 | 10/28/2022 | 19 | 9 | 10 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 319983 | 01069 | 35 | Natural Gas | 05_07_99W32 | 10/20/2020 |  | 308 | 116 | 192 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 595125 | 02190 | 7.6 | Solar | 05_07_91W49 | 04/10/2024 | 04/17/2024 | 4 | 1 | 3 | 04/18/2024 | 04/18/2024 | 26 | 13 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  | 5/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2024 | Connected |  | N
National Grid | BROCKTON | 730587 | 02301 | 11.5 | Solar | 05_09_604W3 | 10/31/2025 | 11/13/2025 | 2 | 0 | 2 | 12/04/2025 | 12/04/2025 | 63 | 42 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BARRE | 175789 | 01005 | 46 | Solar | 05_05_344W3 | 09/17/2015 | 09/17/2015 | 0 | 0 | 0 | 09/18/2015 | 09/18/2015 | 364 | 48 | 316 | 11/03/2015 | 12/02/2015 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  | 12/02/2015 | 19 | 1 | 18 |  |  | 0 | 0 | 0 | 2/24/2016 |  | 3/31/2017 | N | EXP | 41 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 471967 | 02038 | 3.8 | Solar | 05_12_16W1 | 12/13/2022 | 12/20/2022 | 5 | 0 | 5 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 2/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2023 | Connected |  | N
National Grid | SAUGUS | 738203 | 01906 | 11.52 | Solar | 05_05_320W5 | 12/04/2025 | 12/08/2025 | 2 | 0 | 2 | 12/09/2025 | 12/09/2025 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SUTTON | 286961 | 01590 | 366.6 | Solar | 05_07_910W51 | 05/04/2020 | 05/12/2020 | 6 | 2 | 4 |  |  | 15 | 7 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 05/04/2020 | 5/8/2025 | Y | STD | 13 | 10/14/2024 | 10/11/2024 | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | PEMBROKE | 475207 | 02359 | 15.2 | Solar | 05_07_11W1 | 11/07/2022 | 11/08/2022 | 1 | 0 | 1 | 11/09/2022 | 11/09/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 12/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/3/2023 | Connected |  | N
National Grid | QUINCY | 514450 | 02171 | 7.6 | Solar | 05_01_207W2 | 04/06/2023 | 04/17/2023 | 7 | 5 | 2 | 04/18/2023 | 04/18/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2023 | 04/06/2023 | 7/26/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/11/2024 | Connected |  | N
National Grid | LEOMINSTER | 540050 | 01453 | 0 | Solar | 05_09_503L1 | 07/13/2023 | 07/14/2023 | 1 | 0 | 1 | 07/17/2023 | 07/17/2023 | 135 | 115 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2024 |  | 2/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | PALMER | 319549 | 01069 | 7.6 | Solar | 05_07_99W32 | 11/17/2020 | 11/23/2020 | 3 | 0 | 3 | 11/24/2020 | 11/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 603357 | 02190 | 7.6 | Solar | 05_07_91W49 | 04/16/2024 | 04/18/2024 | 2 | 0 | 2 | 04/19/2024 | 04/19/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 | 04/16/2024 | 7/14/2025 | Y | EXP | 365 | 08/03/2024 | 09/12/2024 | 41 | 0 | 41 |  |  | 12/24/2024 | Connected |  | N
National Grid | BROCKTON | 736432 | 02301 | 11.5 | Solar | 05_09_604W3 | 11/25/2025 | 12/18/2025 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BARRE | 178472 | 01005 | 905.8 | Solar | 05_05_344W3 | 03/07/2018 | 03/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2018 | 05/03/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2019 | 03/07/2018 | 11/28/2022 | Y | STD | 126 | 06/13/2020 | 01/28/2022 | 595 | 182 | 413 |  |  | 11/28/2022 | Connected |  | N
National Grid | FRANKLIN | 537674 | 02038 | 7.6 | Solar | 05_12_16W1 | 02/16/2024 | 07/07/2023 | 4 | 0 | 4 | 02/26/2024 | 02/26/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 | 02/16/2024 | 3/13/2025 | Y | EXP | 365 | 06/05/2024 | 06/04/2024 | 0 | 0 | 0 |  |  | 6/9/2024 | Connected |  | N
National Grid | SAUGUS | 742575 | 01906 | 10 | Solar | 05_05_320W5 | 12/29/2025 | 01/05/2026 | 3 | 0 | 3 | 01/27/2026 | 01/27/2026 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WHITINSVILLE | 286960 | 01588 | 100.8 | Solar | 05_07_910W51 | 04/11/2020 | 04/22/2020 | 7 | 3 | 4 |  |  | 30 | 7 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/11/2020 | 4/22/2025 | Y | STD | 13 | 10/11/2024 | 10/11/2024 | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | PEMBROKE | 649272 | 02359 | 10 | Solar | 05_07_11W1 | 10/26/2024 | 11/06/2024 | 2 | 0 | 2 | 11/07/2024 | 11/07/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/26/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | QUINCY | 523383 | 02171 | 6 | Solar | 05_01_207W2 | 05/12/2023 | 05/16/2023 | 2 | 0 | 2 | 05/17/2023 | 05/17/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 | 05/12/2023 | 7/23/2024 | Y | EXP | 365 | 09/21/2023 | 10/24/2023 | 34 | 0 | 34 |  |  | 11/9/2023 | Connected |  | N
National Grid | LEOMINSTER | 555915 | 01453 | 10 | Solar | 05_09_503L1 | 10/23/2023 | 10/24/2023 | 1 | 0 | 1 | 10/25/2023 | 10/25/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 10/23/2023 | 1/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | PALMER | 329977 | 01069 | 10 | Solar | 05_07_99W32 | 12/07/2020 | 12/10/2020 | 2 | 0 | 2 | 12/11/2020 | 12/11/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | Connected |  | N
National Grid | WEYMOUTH | 607442 | 02190 | 5.355 | Solar | 05_07_91W49 | 04/29/2024 | 06/06/2024 | 7 | 2 | 5 | 06/07/2024 | 06/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2024 | Connected |  | N
National Grid | BROCKTON | 750307 | 02301 |  | Battery Add-On | 05_09_604W3 | 02/10/2026 | 02/12/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BARRE | 346314 | 01005 | 240 | Solar | 05_05_344W3 | 03/11/2021 | 01/10/2022 | 9 | 0 | 9 | 03/26/2021 | 03/26/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2021 | 03/11/2021 | 1/12/2024 | Y | EXP | 36 | 08/26/2023 | 12/15/2023 | 112 | 22 | 90 |  |  | 12/29/2023 | Connected |  | N
National Grid | FRANKLIN | 551251 | 02038 | 3.8 | Solar | 05_12_16W1 | 09/01/2023 | 09/05/2023 | 1 | 0 | 1 | 09/06/2023 | 09/06/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2023 | 09/01/2023 | 10/19/2024 | Y | EXP | 365 | 02/09/2024 | 02/26/2024 | 18 | 0 | 18 |  |  | 3/4/2024 | Connected |  | N
National Grid | SAUGUS | 174284 | 01906 | 2000 | Solar | 05_05_320W5 | 12/17/2011 | 12/17/2011 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 287784 | 01590 | 72 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 5 | 4 | 1 |  |  | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/30/2020 | 12/4/2023 | Y | STD | 631 |  |  | 0 | 0 | 0 |  |  | 8/14/2023 | Connected |  | N
National Grid | PEMBROKE | 653435 | 02359 | 5.76 | Solar | 05_07_11W1 | 11/11/2024 | 11/21/2024 | 4 | 0 | 4 | 11/22/2024 | 11/22/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 | 11/11/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2025 | Connected |  | N
National Grid | QUINCY | 532600 | 02171 | 6 | Solar | 05_01_207W2 | 06/13/2023 | 06/14/2023 | 1 | 0 | 1 | 06/15/2023 | 06/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 |  | 8/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | LEOMINSTER | 579915 | 01453 | 7.6 | Solar | 05_09_503L1 | 01/18/2024 | 01/23/2024 | 3 | 0 | 3 | 01/24/2024 | 01/24/2024 | 71 | 56 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 341855 | 01069 | 7.6 | Solar | 05_07_99W32 | 02/11/2021 | 02/17/2021 | 2 | 0 | 2 | 02/18/2021 | 02/18/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 |  | 12/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2021 | Connected |  | N
National Grid | WEYMOUTH | 606963 | 02190 | 10 | Solar | 05_07_91W49 | 04/26/2024 | 05/07/2024 | 1 | 0 | 1 | 05/08/2024 | 05/08/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 174381 | 02301 | 1000 | Solar | 05_09_604W3 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 09/18/2012 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/15/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 412237 | 01535 | 0 | Battery Add-On | 05_05_344W3 | 07/06/2022 | 08/01/2022 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2022 | 08/29/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 555760 | 02038 | 2.9 | Solar | 05_12_16W1 | 10/11/2023 | 10/23/2023 | 8 | 4 | 4 | 10/24/2023 | 10/24/2023 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2023 |  | 2/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2024 | Connected |  | N
National Grid | SAUGUS | 174283 | 01906 | 2000 | Solar | 05_05_320W5 | 12/17/2011 | 12/17/2011 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 09/08/2014 | 89 | 0 | 89 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 287776 | 01526 | 144 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 5 | 4 | 1 |  |  | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/30/2020 | 4/22/2025 | Y | STD | 13 | 10/11/2024 | 10/11/2024 | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | PEMBROKE | 663052 | 02359 | 3.8 | Solar | 05_07_11W1 | 12/30/2024 | 01/28/2025 | 6 | 1 | 5 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 | 12/30/2024 | 7/24/2026 | Y | EXP | 365 | 09/09/2025 | 12/18/2025 | 101 | 0 | 101 |  |  | 11/24/2025 | Connected |  | N
National Grid | QUINCY | 546090 | 02171 | 26 | Solar | 05_01_207W2 | 08/04/2023 | 08/08/2023 | 2 | 0 | 2 | 08/09/2023 | 08/09/2023 | 214 | 29 | 185 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 588858 | 01453 | 7.6 | Solar | 05_09_503L1 | 03/18/2024 | 03/19/2024 | 1 | 0 | 1 | 03/20/2024 | 03/20/2024 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 | 03/18/2024 | 4/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 416071 | 01069 | 15.2 | Solar | 05_07_99W32 | 03/07/2022 | 03/08/2022 | 1 | 0 | 1 | 03/09/2022 | 03/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2022 |  | 5/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/18/2023 | Connected |  | N
National Grid | WEYMOUTH | 618180 | 02190 | 5.76 | Solar | 05_07_91W49 | 06/14/2024 | 06/18/2024 | 6 | 2 | 4 | 08/08/2024 | 08/08/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 |  | 11/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174380 | 02302 | 1000 | Solar | 05_09_604W3 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 09/18/2012 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/15/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 640224 | 01005 | 7.6 | Solar | 05_05_344W3 | 09/16/2024 | 09/30/2024 | 1 | 0 | 1 | 10/01/2024 | 10/01/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 578271 | 02038 | 11.4 | Solar | 05_12_16W1 | 12/21/2023 | 12/29/2023 | 5 | 0 | 5 | 01/02/2024 | 01/02/2024 | 20 | 0 | 20 | 04/11/2024 | 02/12/2025 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  | 02/12/2025 | 76 | 0 | 76 |  |  | 0 | 0 | 0 | 8/6/2024 |  | 8/30/2025 | N | EXP | 365 | 08/31/2024 | 09/20/2024 | 21 | 0 | 21 |  |  | 12/18/2024 | Connected |  | N
National Grid | REVERE | 174336 | 02151 | 42 | Solar | 05_05_320W5 | 01/26/2012 | 01/26/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2012 |  | 3/9/2012 | N | EXP | 35 |  |  | 0 | 0 | 0 | 4/27/2012 | 4/27/2012 | 5/4/2012 | Connected |  | N
National Grid | WHITINSVILLE | 287773 | 01588 | 57.6 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 6 | 5 | 1 |  |  | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/30/2020 | 12/5/2023 | Y | STD | 631 | 01/28/2023 | 01/27/2023 | 0 | 0 | 0 |  |  | 5/26/2023 | Connected |  | N
National Grid | PEMBROKE | 211163 | 02359 | 262.5 | Natural Gas | 05_07_11W2 | 09/13/2019 | 11/05/2019 | 37 | 32 | 5 | 11/06/2019 | 11/06/2019 | 20 | 11 | 9 | 01/03/2020 | 04/16/2020 | 73 | 38 | 35 |  |  | 0 | 0 | 0 |  | 04/16/2020 | 73 | 38 | 35 |  |  | 0 | 0 | 0 | 4/24/2020 |  | 12/7/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 12/17/2020 | Connected |  | N
National Grid | QUINCY | 551656 | 02171 | 3.8 | Solar | 05_01_207W2 | 08/30/2023 | 09/01/2023 | 2 | 0 | 2 | 09/05/2023 | 09/05/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 | 08/30/2023 | 11/10/2024 | Y | EXP | 365 | 02/22/2024 | 03/13/2024 | 21 | 0 | 21 |  |  | 4/18/2024 | Connected |  | N
National Grid | LEOMINSTER | 624145 | 01453 | 4.55 | Solar | 05_09_503L1 | 07/24/2024 | 09/20/2024 | 3 | 1 | 2 | 09/23/2024 | 09/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2024 | 07/24/2024 | 11/11/2025 | Y | EXP | 365 | 06/10/2025 | 08/04/2025 | 56 | 0 | 56 |  |  | 8/21/2025 | Connected |  | N
National Grid | PALMER | 525126 | 01069 | 7.6 | Solar | 05_07_99W32 | 06/27/2023 | 08/03/2023 | 27 | 25 | 2 | 08/04/2023 | 08/04/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 9/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2023 | Connected |  | N
National Grid | WEYMOUTH | 630079 | 02190 | 3.8 | Solar | 05_07_91W49 | 08/05/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 |  | 9/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2024 | Connected |  | N
National Grid | BROCKTON | 174379 | 02301 | 3000 | Solar | 05_09_604W3 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 09/18/2012 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2015 |  | 2/13/2013 | N | STD | 751 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 650355 | 01005 | 7.6 | Solar | 05_05_344W4 | 11/07/2024 | 01/29/2025 | 48 | 46 | 2 | 01/30/2025 | 01/30/2025 | 46 | 23 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FRANKLIN | 595219 | 02038 | 5 | Solar | 05_12_16W1 | 03/26/2024 | 03/28/2024 | 2 | 0 | 2 | 03/29/2024 | 03/29/2024 | 31 | 25 | 6 | 06/21/2024 | 07/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 07/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/19/2025 | N | EXP | 365 | 08/03/2024 | 11/12/2024 | 102 | 0 | 102 |  |  | 11/13/2024 | Connected |  | N
National Grid | SAUGUS | 174613 | 01906 | 1000 | Solar | 05_05_320W5 | 11/16/2010 | 11/16/2010 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2011 | 11/16/2010 | 2/28/2012 | Y | STD | 277 | 10/14/2011 | 02/22/2012 | 86 | 0 | 86 | 8/3/2012 | 8/3/2012 | 2/28/2012 | Connected |  | N
National Grid | SUTTON | 287707 | 01590 | 72 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 5 | 4 | 1 |  |  | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/30/2020 | 12/4/2023 | Y | STD | 631 |  |  | 0 | 0 | 0 |  |  | 8/15/2023 | Connected |  | N
National Grid | PEMBROKE | 641046 | 02359 | 7.68 | Solar | 05_07_11W2 | 09/17/2024 | 10/18/2024 | 2 | 0 | 2 | 10/21/2024 | 10/21/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/17/2024 | 11/26/2025 | Y | EXP | 365 | 02/13/2025 | 03/21/2025 | 37 | 0 | 37 |  |  | 5/19/2025 | Connected |  | N
National Grid | QUINCY | 565145 | 02171 | 6.3 | Solar | 05_01_207W2 | 10/27/2023 | 10/30/2023 | 1 | 0 | 1 | 10/31/2023 | 10/31/2023 | 29 | 6 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  | 12/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2024 | Connected |  | N
National Grid | LEOMINSTER | 632606 | 01453 | 11.5 | Solar | 05_09_503L1 | 08/27/2024 | 08/28/2024 | 1 | 0 | 1 | 08/29/2024 | 08/29/2024 | 12 | 6 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 | 08/27/2024 | 9/26/2025 | Y | EXP | 365 | 10/29/2024 | 11/07/2024 | 10 | 0 | 10 |  |  | 5/1/2025 | Connected |  | N
National Grid | PALMER | 559009 | 01069 | 15.2 | Solar | 05_07_99W32 | 09/28/2023 | 10/03/2023 | 3 | 0 | 3 | 10/04/2023 | 10/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2023 |  | 3/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2024 | Connected |  | N
National Grid | WEYMOUTH | 632887 | 02190 | 5.8 | Solar | 05_07_91W49 | 08/20/2024 | 09/05/2024 | 5 | 3 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 |  | 9/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2024 | Connected |  | N
National Grid | BROCKTON | 174656 | 02301 | 800 | Solar | 05_09_604W3 | 04/11/2011 | 04/11/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 299 |  |  | 0 | 0 | 0 | 12/3/2012 | 12/3/2012 | 12/4/2012 | Connected |  | N
National Grid | NEW BRAINTREE | 685927 | 01531 | 7.6 | Solar | 05_05_344W4 | 04/17/2025 | 10/01/2025 | 114 | 112 | 2 | 10/02/2025 | 10/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 11/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FRANKLIN | 594652 | 02038 | 7.6 | Solar | 05_12_16W1 | 03/08/2024 | 03/12/2024 | 2 | 0 | 2 | 03/13/2024 | 03/13/2024 | 7 | 0 | 7 | 04/08/2024 | 07/16/2024 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  | 07/16/2024 | 67 | 0 | 67 |  |  | 0 | 0 | 0 | 6/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 174612 | 01906 | 1000 | Solar | 05_05_320W5 | 11/16/2010 | 11/16/2010 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2011 | 11/16/2010 | 2/2/2012 | Y | STD | 251 | 10/14/2011 | 01/20/2012 | 64 | 0 | 64 | 8/3/2012 | 8/3/2012 | 2/2/2012 | Connected |  | N
National Grid | SUTTON | 287680 | 01590 | 72 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 5 | 4 | 1 |  |  | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/30/2020 | 12/4/2023 | Y | STD | 631 |  |  | 0 | 0 | 0 |  |  | 6/7/2023 | Connected |  | N
National Grid | PEMBROKE | 660805 | 02359 | 5.76 | Solar | 05_07_11W2 | 12/16/2024 | 01/08/2025 | 1 | 0 | 1 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 12/16/2024 | 2/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | QUINCY | 573630 | 02171 | 10 | Solar | 05_01_207W2 | 12/12/2023 | 12/19/2023 | 5 | 1 | 4 | 12/20/2023 | 12/20/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 | 12/12/2023 | 2/12/2025 | Y | EXP | 365 | 05/11/2024 | 06/05/2024 | 26 | 0 | 26 |  |  | 6/15/2024 | Connected |  | N
National Grid | LEOMINSTER | 647261 | 01453 | 10 | Solar | 05_09_503L1 | 10/24/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2025 | Connected |  | N
National Grid | PALMER | 552140 | 01069 | 0 | Solar | 05_07_99W32 | 08/30/2023 | 10/03/2023 | 24 | 23 | 1 | 10/04/2023 | 10/04/2023 | 45 | 22 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  | 3/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | WEYMOUTH | 632819 | 02190 | 11.5 | Solar | 05_07_91W49 | 08/19/2024 | 09/03/2024 | 1 | 0 | 1 | 09/04/2024 | 09/04/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 174689 | 02301 | 800 | Solar | 05_09_604W3 | 04/11/2011 | 04/11/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 299 | 07/17/2012 | 12/12/2012 | 87 | 0 | 87 | 12/3/2012 | 12/3/2012 | 12/4/2012 | Connected |  | N
National Grid | NEW BRAINTREE | 713324 | 01531 | 1680 | Solar | 05_05_344W4 | 01/08/2026 |  | 39 | 29 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | FRANKLIN | 629646 | 02038 | 5.76 | Solar | 05_12_16W1 | 08/02/2024 | 08/21/2024 | 5 | 0 | 5 | 08/22/2024 | 08/22/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2024 | Connected |  | N
National Grid | SAUGUS | 174645 | 01906 | 44.4 | Solar | 05_05_320W5 | 12/20/2013 | 12/20/2013 | 6 | 0 | 6 | 01/02/2014 | 01/02/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2014 | 12/20/2013 | 2/28/2014 | Y | EXP | 32 | 06/09/2014 | 06/09/2014 | 0 | 0 | 0 | 7/15/2014 | 7/15/2014 | 7/16/2014 | Connected |  | N
National Grid | SUTTON | 287677 | 01590 | 95.4 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 6 | 5 | 1 |  |  | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/30/2020 | 5/8/2025 | Y | STD | 13 | 10/11/2024 | 10/11/2024 | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | PEMBROKE | 673592 | 02359 | 1500 | Other | 05_07_11W3 | 05/02/2025 | 08/20/2025 | 75 | 66 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2025 | 09/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | QUINCY | 576114 | 02170 | 34.5 | Solar | 05_01_207W2 | 12/06/2023 | 02/01/2024 | 38 | 26 | 12 | 02/02/2024 | 02/02/2024 | 144 | 25 | 119 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 654380 | 01453 | 10 | Solar | 05_09_503L1 | 11/14/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 5/18/2026 | Y | EXP | 365 | 05/21/2025 | 05/20/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 552899 | 01069 | 7.6 | Solar | 05_07_99W32 | 09/01/2023 | 09/07/2023 | 3 | 0 | 3 | 09/08/2023 | 09/08/2023 | 72 | 25 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 636465 | 02190 | 9.88 | Solar | 05_07_91W49 | 08/29/2024 | 09/10/2024 | 1 | 0 | 1 | 09/11/2024 | 09/11/2024 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 08/29/2024 | 6/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 175003 | 02301 | 4000 | Solar | 05_09_604W3 | 09/16/2013 | 09/16/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2013 | 10/25/2013 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 |  | 8/29/2014 | N | STD | 48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 726096 | 01531 | 7.6 | Solar | 05_05_344W4 | 10/13/2025 | 11/20/2025 | 2 | 0 | 2 | 12/24/2025 | 12/24/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 | 10/13/2025 | 1/30/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | BELLINGHAM | 635855 | 02019 | 4.93 | Solar | 05_12_16W1 | 08/28/2024 | 09/17/2024 | 10 | 7 | 3 | 09/18/2024 | 09/18/2024 | 8 | 0 | 8 | 12/13/2024 | 12/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 12/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 1/6/2025 |  | 1/25/2026 | N | EXP | 365 | 03/18/2025 | 05/07/2025 | 51 | 12 | 39 |  |  | 4/29/2025 | Connected |  | N
National Grid | MALDEN | 174655 | 02148 | 375 | Solar | 05_05_320W5 | 08/21/2012 | 08/21/2012 | 8 | 0 | 8 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2012 |  | 11/1/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | N
National Grid | NORTHBRIDGE | 288164 | 01534 | 52.2 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 5 | 4 | 1 |  |  | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/30/2020 | 5/8/2025 | Y | STD | 13 | 10/11/2024 | 10/11/2024 | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | PEMBROKE | 174468 | 02359 | 1100 | Solar | 05_07_11W3 | 07/14/2011 | 07/14/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2012 | 07/14/2011 | 7/25/2012 | Y | STD | 111 | 10/10/2012 | 03/04/2013 | 78 | 0 | 78 | 11/26/2012 | 11/26/2012 | 12/4/2012 | Connected |  | N
National Grid | QUINCY | 592388 | 02170 | 7.6 | Solar | 05_01_207W2 | 03/11/2024 | 03/14/2024 | 3 | 0 | 3 | 03/15/2024 | 03/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 | 03/11/2024 | 4/24/2025 | Y | EXP | 365 | 05/30/2024 | 06/04/2024 | 6 | 0 | 6 |  |  | 6/11/2024 | Connected |  | N
National Grid | LEOMINSTER | 685358 | 01453 | 4980 | Solar | 05_09_503L1 | 06/03/2025 | 07/09/2025 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 07/29/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 568632 | 01069 | 7.6 | Solar | 05_07_99W32 | 11/03/2023 | 02/01/2024 | 59 | 55 | 4 | 02/02/2024 | 02/02/2024 | 21 | 10 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2024 | Connected |  | N
National Grid | WEYMOUTH | 638145 | 02190 | 11.5 | Battery Add-On | 05_07_91W49 | 09/25/2024 | 09/26/2024 | 1 | 0 | 1 | 09/27/2024 | 09/27/2024 | 73 | 50 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | BROCKTON | 175016 | 02301 | 0 | Solar | 05_09_604W3 | 09/16/2011 | 09/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2011 | 12/12/2011 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2013 | 09/16/2011 | 11/30/2012 | Y | STD | 189 |  |  | 0 | 0 | 0 | 4/11/2014 | 4/11/2014 | 4/28/2014 | Connected |  | N
National Grid | BARRE | 733287 | 01005 | 5.76 | Solar | 05_05_344W4 | 11/12/2025 | 11/25/2025 | 1 | 0 | 1 | 12/18/2025 | 12/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BELLINGHAM | 644192 | 02019 | 7.6 | Solar | 05_12_16W1 | 10/01/2024 | 11/27/2024 | 6 | 0 | 6 | 12/02/2024 | 12/02/2024 | 25 | 0 | 25 | 01/22/2025 | 03/07/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  | 03/07/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/28/2025 | Connected |  | Y
National Grid | SAUGUS | 175519 | 01906 | 1950 | Solar | 05_05_320W5 | 04/08/2014 | 04/08/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2014 | 04/28/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 04/08/2014 | 12/31/2016 | Y | STD | 722 |  |  | 0 | 0 | 0 | 11/30/2016 | 11/30/2016 | 11/30/2016 | Connected |  | N
National Grid | NORTHBRIDGE | 288162 | 01534 | 72 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 5 | 4 | 1 |  |  | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/30/2020 | 12/4/2023 | Y | STD | 631 | 05/16/2023 | 05/30/2023 | 14 | 0 | 14 |  |  | 6/12/2023 | Connected |  | N
National Grid | PEMBROKE | 175422 | 02359 | 225 | Solar | 05_07_11W3 | 07/14/2014 | 07/14/2014 | 0 | 0 | 0 | 07/23/2014 | 07/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2014 |  | 10/31/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 10/1/2014 | 10/1/2014 | 3/13/2015 | Connected |  | N
National Grid | QUINCY | 593162 | 02170 | 3.77 | Solar | 05_01_207W2 | 03/03/2024 | 03/06/2024 | 3 | 0 | 3 | 03/07/2024 | 03/07/2024 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 | 03/03/2024 | 4/25/2025 | Y | EXP | 365 | 07/10/2024 | 07/16/2024 | 7 | 0 | 7 |  |  | 8/6/2024 | Connected |  | N
National Grid | LEOMINSTER | 696490 | 01453 | 24.7 | Solar | 05_09_503L2 | 06/05/2025 | 06/25/2025 | 12 | 9 | 3 | 06/26/2025 | 06/26/2025 | 56 | 41 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PALMER | 577766 | 01069 | 0 | Other | 05_07_99W32 | 12/21/2023 | 02/21/2024 | 41 | 32 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2024 | 02/28/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 639225 | 02190 | 7.6 | Solar | 05_07_91W49 | 09/10/2024 | 09/23/2024 | 1 | 0 | 1 | 09/24/2024 | 09/24/2024 | 72 | 50 | 22 | 01/22/2025 | 02/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 02/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/10/2026 | N | EXP | 365 | 05/16/2025 | 07/03/2025 | 49 | 0 | 49 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 175218 | 02301 | 750 | Solar | 05_09_604W3 | 11/03/2014 | 11/03/2014 | 12 | 10 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2014 | 12/19/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 734412 | 01005 | 23 | Solar | 05_05_344W4 | 11/21/2025 | 12/17/2025 | 3 | 0 | 3 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BELLINGHAM | 645489 | 02019 | 6.175 | Solar | 05_12_16W1 | 10/07/2024 | 10/11/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  | 12/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2025 | Connected |  | Y
National Grid | SAUGUS | 176067 | 01906 | 10 | Solar | 05_05_320W5 | 06/19/2015 | 06/19/2015 | 6 | 6 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2015 |  | 6/27/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 5/10/2016 | Connected |  | N
National Grid | SUTTON | 287871 | 01526 | 144 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 6 | 5 | 1 |  |  | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/30/2020 | 5/5/2025 | Y | STD | 13 | 10/11/2024 | 10/11/2024 | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | PEMBROKE | 176643 | 02359 | 528 | Solar | 05_07_11W3 | 12/31/2015 | 12/31/2015 | 12 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2016 | 02/04/2016 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/15/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 605055 | 02171 | 3.8 | Solar | 05_01_207W2 | 04/18/2024 | 05/01/2024 | 5 | 0 | 5 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/18/2024 | 5/29/2025 | Y | EXP | 365 | 08/23/2024 | 09/16/2024 | 25 | 0 | 25 |  |  | 9/20/2024 | Connected |  | N
National Grid | LEOMINSTER | 732307 | 01453 | 11.5 | Solar | 05_09_503L2 | 11/07/2025 | 01/07/2026 | 3 | 0 | 3 | 01/21/2026 | 01/21/2026 | 31 | 17 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PALMER | 606662 | 01069 | 23 | Solar | 05_07_99W32 | 04/25/2024 | 04/29/2024 | 2 | 0 | 2 | 04/30/2024 | 04/30/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 643766 | 02190 | 15.2 | Solar | 05_07_91W49 | 12/03/2024 | 12/05/2024 | 3 | 2 | 1 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2026 | Connected |  | N
National Grid | BROCKTON | 175238 | 02301 | 480 | Solar | 05_09_604W3 | 08/20/2014 | 08/20/2014 | 7 | 0 | 7 | 09/02/2014 | 09/02/2014 | 0 | 0 | 0 | 10/21/2014 | 11/24/2014 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  | 11/24/2014 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 12/24/2014 | 08/20/2014 | 11/15/2015 | Y | EXP | 326 | 09/08/2015 | 11/12/2015 | 45 | 0 | 45 | 11/6/2015 | 11/6/2015 | 11/16/2015 | Connected |  | N
National Grid | HARDWICK | 174743 | 01037 | 3108 | Solar | 05_05_344W4 | 07/01/2013 | 07/01/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/11/2013 | 08/02/2013 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2014 | 07/01/2013 | 3/15/2016 | Y | STD | 728 | 11/02/2015 | 01/03/2017 | 289 | 0 | 289 | 12/21/2016 | 12/21/2016 | 12/23/2016 | Connected |  | N
National Grid | BELLINGHAM | 646803 | 02019 | 5.8 | Solar | 05_12_16W1 | 10/14/2024 | 10/22/2024 | 4 | 0 | 4 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/14/2024 | 11/25/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | SAUGUS | 177280 | 01906 | 2800 | Solar | 05_05_320W5 | 02/08/2017 | 02/08/2017 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/14/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 287869 | 01534 | 115.2 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 5 | 4 | 1 |  |  | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 186049 | 02359 | 1005.6 | Solar | 05_07_11W3 | 08/02/2018 | 10/04/2018 | 44 | 38 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2018 | 12/28/2018 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 629800 | 02171 | 5.76 | Solar | 05_01_207W2 | 08/02/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 | 08/02/2024 | 10/2/2025 | Y | EXP | 365 | 12/13/2024 | 12/12/2024 | 0 | 0 | 0 |  |  | 1/21/2025 | Connected |  | N
National Grid | LEOMINSTER | 742272 | 01453 | 7.6 | Solar | 05_09_503L2 | 12/26/2025 | 01/27/2026 | 2 | 0 | 2 | 02/18/2026 | 02/18/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PALMER | 633824 | 01069 | 15.2 | Solar | 05_07_99W32 | 08/19/2024 | 09/09/2024 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | WEYMOUTH | 652480 | 02190 | 10 | Solar | 05_07_91W49 | 11/14/2024 | 12/08/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 96 | 74 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 5/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | BROCKTON | 175304 | 02301 | 499 | Solar | 05_09_604W3 | 06/25/2014 | 06/25/2014 | 6 | 0 | 6 | 07/07/2014 | 07/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2014 | 06/25/2014 | 11/18/2016 | Y | EXP | 826 | 12/02/2016 | 03/29/2017 | 79 | 0 | 79 | 4/12/2017 | 4/12/2017 | 4/12/2017 | Connected |  | N
National Grid | BARRE | 174915 | 01005 | 12.9 | Solar | 05_05_344W4 | 02/21/2013 | 02/21/2013 | 6 | 0 | 6 | 03/05/2013 | 03/05/2013 | 329 | 0 | 329 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2013 |  | 5/31/2013 | N | EXP | 52 |  |  | 0 | 0 | 0 | 4/9/2013 | 4/9/2013 |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 649182 | 02019 | 10 | Solar | 05_12_16W1 | 10/23/2024 | 12/03/2024 | 21 | 19 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | SAUGUS | 178078 | 01906 | 3220 | Solar | 05_05_320W5 | 05/05/2017 | 05/25/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/25/2017 | 06/15/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 10/8/2021 | N | STD | 449 |  |  | 0 | 0 | 0 |  |  | 12/30/2021 | Connected |  | N
National Grid | SUTTON | 287867 | 01590 | 72 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 5 | 4 | 1 |  |  | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/30/2020 | 12/4/2023 | Y | STD | 631 |  |  | 0 | 0 | 0 |  |  | 8/15/2023 | Connected |  | N
National Grid | PEMBROKE | 365947 | 02359 | 700 | Solar | 05_07_11W3 | 03/28/2022 | 06/30/2022 | 65 | 57 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/01/2022 | 07/29/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 632334 | 02171 | 7.6 | Solar | 05_01_207W2 | 08/21/2024 | 08/26/2024 | 3 | 0 | 3 | 08/27/2024 | 08/27/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 | 08/21/2024 | 9/16/2025 | Y | EXP | 365 | 01/09/2025 | 01/08/2025 | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | LEOMINSTER | 175162 | 01453 | 3000 | Solar | 05_09_503L2 | 07/18/2011 | 07/18/2011 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/10/2011 | 09/30/2011 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2012 | 07/18/2011 | 12/31/2012 | Y | STD | 194 | 01/09/2014 | 10/07/2014 | 185 | 0 | 185 | 8/25/2014 | 8/25/2014 | 8/25/2014 | Connected |  | N
National Grid | WALES | 664153 | 01081 | 10.4 | Solar | 05_07_99W32 | 01/07/2025 | 01/16/2025 | 3 | 1 | 2 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 01/07/2025 | 3/10/2026 | Y | EXP | 365 | 05/10/2025 | 06/20/2025 | 42 | 0 | 42 |  |  | 6/28/2025 | Connected |  | Y
National Grid | ABINGTON | 653043 | 02351 | 7.6 | Solar | 05_07_91W49 | 11/14/2024 | 12/11/2024 | 7 | 6 | 1 | 12/12/2024 | 12/12/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/14/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 175688 | 02301 | 480 | Solar | 05_09_604W3 | 05/22/2014 | 05/22/2014 | 6 | 0 | 6 | 06/03/2014 | 06/03/2014 | 0 | 0 | 0 | 07/30/2014 | 08/29/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 08/29/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 10/6/2014 | 05/22/2014 | 11/13/2015 | Y | EXP | 43 | 10/06/2015 | 10/21/2015 | 10 | 0 | 10 | 11/5/2015 | 11/5/2015 | 11/16/2015 | Connected |  | N
National Grid | NEW BRAINTREE | 175608 | 01531 | 998 | Solar | 05_05_344W4 | 10/17/2014 | 10/17/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2014 | 11/25/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 654913 | 02019 | 3.8 | Solar | 05_12_16W1 | 11/19/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 178674 | 01906 | 1000 | Solar | 05_05_320W5 | 04/10/2018 | 04/16/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/18/2018 | 08/14/2018 | 61 | 43 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2019 | 04/10/2018 | 12/16/2020 | Y | STD | 375 | 01/29/2020 | 10/26/2020 | 272 | 5 | 267 | 11/10/2020 | 11/10/2020 | 12/4/2020 | Connected |  | N
National Grid | WHITINSVILLE | 289948 | 01588 | 233.3 | Solar | 05_07_910W51 | 05/11/2020 | 05/13/2020 | 1 | 0 | 1 |  |  | 14 | 7 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 05/11/2020 | 2/4/2025 | Y | STD | 13 | 10/11/2024 | 10/11/2024 | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | PEMBROKE | 690710 | 02359 | 0 | Solar | 05_07_11W4 | 05/08/2025 | 06/17/2025 | 24 | 20 | 4 | 06/18/2025 | 06/18/2025 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2025 |  | 9/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | QUINCY | 635778 | 02171 | 6 | Solar | 05_01_207W2 | 08/27/2024 | 08/30/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/27/2024 | 1/7/2026 | Y | EXP | 365 | 02/12/2025 | 03/03/2025 | 20 | 0 | 20 |  |  | 3/18/2025 | Connected |  | N
National Grid | LEOMINSTER | 175738 | 01453 | 4280 | Solar | 05_09_503L2 | 08/11/2014 | 08/11/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2014 | 09/23/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 08/11/2014 | 12/31/2017 | Y | STD | 15 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 684372 | 01057 | 10 | Solar | 05_07_99W32 | 04/10/2025 | 05/12/2025 | 4 | 0 | 4 | 05/13/2025 | 05/13/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2025 | Connected |  | N
National Grid | WEYMOUTH | 657177 | 02190 | 7.6 | Solar | 05_07_91W49 | 11/26/2024 | 12/16/2024 | 6 | 0 | 6 | 12/17/2024 | 12/17/2024 | 59 | 34 | 25 | 04/04/2025 | 05/01/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 05/01/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 5/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175779 | 02301 | 40 | Solar | 05_09_604W3 | 07/21/2015 | 07/21/2015 | 3 | 3 | 0 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2015 | 07/21/2015 | 8/27/2017 | Y | EXP | 745 | 04/27/2017 | 05/11/2017 | 10 | 0 | 10 | 8/13/2015 | 8/13/2015 | 6/19/2017 | Connected |  | N
National Grid | BARRE | 175941 | 01005 | 15.2 | Solar | 05_05_344W4 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 | 01/29/2015 | 01/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 |  | 5/31/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 11/19/2015 | 11/19/2015 | 11/19/2015 | Connected |  | N
National Grid | BELLINGHAM | 659125 | 02019 | 10 | Solar | 05_12_16W1 | 12/10/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 178805 | 02151 | 0 | Solar | 05_05_320W5 | 12/17/2011 | 12/17/2011 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 288988 | 01590 | 28.8 | Solar | 05_07_910W51 | 04/30/2020 | 05/08/2020 | 6 | 5 | 1 |  |  | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 04/30/2020 | 12/5/2023 | Y | STD | 631 | 01/28/2023 | 01/27/2023 | 0 | 0 | 0 |  |  | 5/26/2023 | Connected |  | N
National Grid | PEMBROKE | 175732 | 02359 | 1161 | Solar | 05_07_11W4 | 06/02/2014 | 06/02/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2014 | 07/28/2014 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 639505 | 02171 | 3.8 | Solar | 05_01_207W2 | 09/11/2024 | 10/08/2024 | 3 | 0 | 3 | 10/09/2024 | 10/09/2024 | 40 | 19 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 09/11/2024 | 12/18/2025 | Y | EXP | 365 | 01/30/2025 | 02/12/2025 | 14 | 0 | 14 |  |  | 2/20/2025 | Connected |  | N
National Grid | LEOMINSTER | 175838 | 01453 | 2000 | Solar | 05_09_503L2 | 03/04/2015 | 03/04/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/11/2015 | 04/09/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2015 | 03/04/2015 | 8/14/2017 | Y | STD | 671 | 03/08/2017 | 07/21/2017 | 94 | 0 | 94 | 8/18/2017 | 8/18/2017 | 8/18/2017 | Connected |  | N
National Grid | MONSON | 706368 | 01057 | 8.725 | Solar | 05_07_99W32 | 07/22/2025 | 07/25/2025 | 3 | 0 | 3 | 07/28/2025 | 07/28/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | ABINGTON | 658066 | 02351 | 3.8 | Solar | 05_07_91W49 | 12/03/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | BROCKTON | 175954 | 02301 | 990 | Solar | 05_09_604W3 | 03/12/2015 | 03/12/2015 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 04/24/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 176011 | 01531 | 11 | Solar | 05_05_344W4 | 01/23/2015 | 01/23/2015 | 6 | 2 | 4 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2015 | 01/23/2015 | 7/19/2016 | Y | EXP | 512 | 11/05/2015 | 11/16/2015 | 6 | 0 | 6 | 3/28/2016 | 3/28/2016 | 3/28/2016 | Connected |  | N
National Grid | FRANKLIN | 634128 | 02038 | 6.38 | Solar | 05_12_16W2 | 08/21/2024 | 10/01/2024 | 24 | 21 | 3 | 10/02/2024 | 10/02/2024 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 08/21/2024 | 10/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | REVERE | 184565 | 02151 | 264 | Solar | 05_05_320W5 | 07/17/2018 | 08/28/2018 | 6 | 0 | 6 |  |  | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2019 |  | 8/3/2020 | N | STD | 479 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 288984 | 01534 | 300 | Solar | 05_07_910W51 | 05/04/2020 | 05/11/2020 | 5 | 2 | 3 |  |  | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 05/04/2020 | 1/21/2025 | Y | STD | 13 | 10/15/2024 | 10/14/2024 | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | PEMBROKE | 178119 | 02359 | 300 | Natural Gas | 05_07_11W4 | 05/11/2017 | 05/11/2017 | 35 | 31 | 4 | 06/30/2017 | 06/30/2017 | 101 | 42 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2017 |  | 5/16/2018 | N | EXP | 233 |  |  | 0 | 0 | 0 |  |  | 9/14/2018 | Connected |  | N
National Grid | QUINCY | 645900 | 02171 | 7.6 | Solar | 05_01_207W2 | 10/09/2024 | 10/24/2024 | 9 | 6 | 3 | 10/25/2024 | 10/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | LEOMINSTER | 176457 | 01453 | 7.6 | Solar | 05_09_503L2 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 |  | 12/14/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 6/10/2016 | 6/10/2016 | 6/21/2016 | Connected |  | N
National Grid | MONSON | 456001 | 01057 | 200 | Solar | 05_07_99W61 | 09/02/2022 | 09/19/2022 | 10 | 0 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2025 |  | 7/30/2026 | N | STD | 147 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WEYMOUTH | 662015 | 02190 | 8.45 | Solar | 05_07_91W49 | 12/20/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 175951 | 02301 | 990 | Solar | 05_09_604W3 | 03/12/2015 | 03/12/2015 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 04/24/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 176082 | 01535 | 50 | Solar | 05_05_344W4 | 01/30/2015 | 01/30/2015 | 15 | 15 | 0 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 6/27/2015 | N | EXP | 12 |  |  | 0 | 0 | 0 | 4/1/2015 | 4/1/2015 | 5/10/2016 | Connected |  | N
National Grid | BELLINGHAM | 659695 | 02019 | 11.4 | Solar | 05_12_16W2 | 12/10/2024 | 01/03/2025 | 14 | 10 | 4 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/10/2024 | 9/30/2026 | Y | EXP | 365 | 01/14/2026 |  | 52 | 0 | 52 |  |  |  | Construction |  | Y
National Grid | SAUGUS | 190183 | 01906 | 250 | Solar | 05_05_320W5 | 07/10/2018 | 07/20/2018 | 1 | 0 | 1 | 07/23/2018 | 07/23/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  | 7/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2019 | Connected |  | N
National Grid | SUTTON | 290029 | 01590 | 233.3 | Solar | 05_07_910W51 | 05/11/2020 | 05/13/2020 | 1 | 0 | 1 |  |  | 14 | 7 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 05/11/2020 | 5/8/2025 | Y | STD | 13 | 10/11/2024 | 10/11/2024 | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | PEMBROKE | 336065 | 02359 | 7.6 | Solar | 05_07_11W4 | 01/11/2021 | 01/13/2021 | 8 | 6 | 2 | 01/04/2023 | 01/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2021 |  | 2/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | N
National Grid | QUINCY | 648296 | 02171 | 10 | Solar | 05_01_207W2 | 10/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | LEOMINSTER | 176601 | 01453 | 2000 | Solar | 05_09_503L2 | 12/29/2015 | 01/05/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/15/2016 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 06/24/2016 | 09/27/2016 | 65 | 12 | 53 | 9/30/2016 | 12/29/2015 | 2/28/2019 | Y | STD | 881 | 09/19/2018 | 11/09/2018 | 51 | 0 | 51 |  |  | 2/28/2019 | Connected |  | N
National Grid | MONSON | 689730 | 01057 | 6.96 | Solar | 05_07_99W61 | 05/05/2025 | 07/11/2025 | 3 | 0 | 3 | 07/14/2025 | 07/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEYMOUTH | 670801 | 02190 | 11.4 | Solar | 05_07_91W49 | 02/12/2025 | 02/24/2025 | 8 | 4 | 4 | 02/25/2025 | 02/25/2025 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 | 02/12/2025 | 6/14/2026 | Y | EXP | 365 | 09/03/2025 | 10/17/2025 | 45 | 0 | 45 |  |  | 10/28/2025 | Connected |  | N
National Grid | BROCKTON | 176322 | 02302 | 15.2 | Solar | 05_09_604W3 | 07/14/2015 | 07/14/2015 | 8 | 8 | 0 | 07/27/2015 | 07/27/2015 | 313 | 0 | 313 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2015 |  | 7/20/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 176401 | 01531 | 3.8 | Solar | 05_05_344W4 | 03/11/2016 | 03/11/2016 | 3 | 3 | 0 | 03/17/2016 | 03/17/2016 | 228 | 0 | 228 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 |  | 3/19/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 742326 | 02019 | 3.8 | Solar | 05_12_16W2 | 12/26/2025 | 12/30/2025 | 2 | 0 | 2 | 12/31/2025 | 12/31/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  | 2/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 193521 | 01906 | 2000 | Solar | 05_05_320W5 | 08/14/2018 | 08/27/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2018 | 10/31/2018 | 46 | 27 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2020 | 08/14/2018 | 4/27/2025 | Y | STD | 28 | 07/12/2023 | 01/07/2025 | 547 | 365 | 182 |  |  | 4/18/2025 | Connected |  | N
National Grid | SUTTON | 349785 | 01590 | 200 | Solar | 05_07_910W51 | 04/07/2021 | 04/27/2021 | 13 | 3 | 10 | 04/28/2021 | 04/28/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 | 04/07/2021 | 5/15/2025 | Y | EXP | 491 | 02/18/2022 | 04/26/2024 | 799 | 737 | 62 |  |  | 4/26/2024 | Connected |  | N
National Grid | PEMBROKE | 463424 | 02359 | 10 | Solar | 05_07_11W4 | 12/09/2022 | 10/05/2022 | 1 | 0 | 1 | 12/13/2022 | 12/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2023 | 12/09/2022 | 5/2/2024 | Y | EXP | 365 | 04/06/2023 | 05/01/2023 | 26 | 0 | 26 |  |  | 5/31/2023 | Connected |  | Y
National Grid | QUINCY | 649022 | 02171 | 3.8 | Solar | 05_01_207W2 | 11/05/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 176850 | 01453 | 972 | Solar | 05_09_503L2 | 11/09/2015 | 11/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/11/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/1/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 708790 | 01057 | 240 | Solar | 05_07_99W61 | 08/05/2025 | 09/16/2025 | 28 | 18 | 10 |  |  | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WEYMOUTH | 674182 | 02190 | 5.76 | Solar | 05_07_91W49 | 02/27/2025 | 04/08/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 176411 | 02301 | 34.2 | Solar | 05_09_604W3 | 05/10/2016 | 05/10/2016 | 2 | 2 | 0 | 05/13/2016 | 05/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/10/2016 | 5/16/2017 | Y | EXP | 344 | 02/27/2017 | 03/22/2017 | 17 | 0 | 17 | 3/23/2017 | 3/23/2017 | 3/29/2017 | Connected |  | N
National Grid | BARRE | 176753 | 01005 | 7.6 | Solar | 05_05_344W4 | 01/12/2016 | 01/12/2016 | 8 | 8 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2016 |  | 1/18/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 6/30/2016 | Connected |  | N
National Grid | BELLINGHAM | 177868 | 02019 | 3.8 | Solar | 05_12_16W2 | 08/09/2017 | 08/09/2017 | 4 | 4 | 0 | 08/16/2017 | 08/16/2017 | 116 | 0 | 116 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/15/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 208111 | 02149 | 3.8 | Solar | 05_05_320W5 | 02/25/2019 | 03/06/2019 | 6 | 0 | 6 | 03/07/2019 | 03/07/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 401688 | 01590 | 9.57 | Solar | 05_07_910W51 | 12/15/2021 | 01/24/2022 | 26 | 25 | 1 | 01/25/2022 | 01/25/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2022 |  | 3/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2022 | Connected |  | N
National Grid | PEMBROKE | 529304 | 02359 | 6 | Solar | 05_07_11W4 | 06/01/2023 | 06/02/2023 | 1 | 0 | 1 | 06/05/2023 | 06/05/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 | 06/01/2023 | 7/13/2024 | Y | EXP | 365 | 08/05/2023 | 10/27/2023 | 84 | 0 | 84 |  |  | 10/30/2023 | Connected |  | N
National Grid | QUINCY | 649640 | 02169 | 3.8 | Solar | 05_01_207W2 | 11/06/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/06/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | LEOMINSTER | 178214 | 01453 | 4980 | Solar | 05_09_503L2 | 03/23/2018 | 03/23/2018 | 12 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2018 | 05/04/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/1/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 177379 | 01057 | 1000 | Solar | 05_07_99W61 | 11/23/2016 | 11/23/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/3/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 699730 | 02370 | 5.76 | Solar | 05_07_91W49 | 06/24/2025 | 07/21/2025 | 4 | 0 | 4 | 07/28/2025 | 07/28/2025 | 28 | 15 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 | 06/24/2025 | 10/7/2026 | Y | EXP | 365 | 11/18/2025 | 12/05/2025 | 18 | 0 | 18 |  |  | 12/11/2025 | Connected |  | N
National Grid | BROCKTON | 176783 | 02301 | 2000 | Solar | 05_09_604W3 | 11/05/2015 | 11/05/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/09/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 176820 | 01005 | 6 | Solar | 05_05_344W4 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2016 |  | 1/20/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 12/16/2016 | Connected |  | N
National Grid | BELLINGHAM | 340353 | 02019 | 7.6 | Solar | 05_12_16W2 | 02/03/2021 | 02/11/2021 | 5 | 3 | 2 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 3/23/2023 | N | EXP | 7 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 266587 | 02149 | 15.2 | Solar | 05_05_320W5 | 11/21/2019 | 11/22/2019 | 0 | 0 | 0 | 11/25/2019 | 11/25/2019 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2020 | 11/21/2019 | 11/21/2020 | Y | EXP | 365 | 04/01/2020 | 04/07/2020 | 6 | 0 | 6 |  |  | 7/17/2020 | Connected |  | N
National Grid | SUTTON | 417115 | 01590 | 262.5 | Natural Gas | 05_07_910W51 | 05/16/2022 | 05/24/2022 | 6 | 0 | 6 |  |  | 56 | 33 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 574216 | 02359 | 7.6 | Solar | 05_07_11W4 | 01/03/2024 | 01/05/2024 | 2 | 0 | 2 | 01/08/2024 | 01/08/2024 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | QUINCY | 654350 | 02170 | 6.175 | Solar | 05_01_207W2 | 11/14/2024 | 12/17/2024 | 12 | 7 | 5 | 12/18/2024 | 12/18/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | LEOMINSTER | 184321 | 01453 | 11.4 | Solar | 05_09_503L2 | 07/15/2018 | 08/09/2018 | 18 | 0 | 18 | 08/10/2018 | 08/10/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 196387 | 01057 | 100 | Solar | 05_07_99W61 | 09/19/2018 | 10/05/2018 | 7 | 0 | 7 | 10/08/2018 | 10/08/2018 | 25 | 4 | 21 | 11/29/2018 | 12/19/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 12/19/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 1/24/2019 | 09/19/2018 | 6/1/2020 | Y | EXP | 494 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 708868 | 02370 | 0 | Battery Add-On | 05_07_91W49 | 07/31/2025 | 08/04/2025 | 2 | 0 | 2 | 08/05/2025 | 08/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 07/31/2025 | 9/16/2026 | Y | EXP | 365 | 10/31/2025 | 11/28/2025 | 29 | 0 | 29 |  |  | 2/21/2026 | Connected |  | N
National Grid | BROCKTON | 176812 | 02301 | 1000 | Solar | 05_09_604W3 | 11/05/2015 | 11/05/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/10/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 176807 | 01005 | 6 | Solar | 05_05_344W4 | 04/27/2016 | 04/27/2016 | 8 | 8 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2016 |  | 5/3/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 | 9/16/2016 | 9/16/2016 | 11/22/2016 | Connected |  | N
National Grid | BELLINGHAM | 354177 | 02019 | 16.82 | Solar | 05_12_16W2 | 04/22/2021 | 04/23/2021 | 0 | 0 | 0 | 04/26/2021 | 04/26/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2021 | Connected |  | Y
National Grid | EVERETT | 329362 | 02149 | 10 | Solar | 05_05_320W5 | 01/18/2021 | 02/12/2021 | 19 | 16 | 3 | 02/16/2021 | 02/16/2021 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/11/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 419321 | 01516 | 499 | Solar | 05_07_910W51 | 04/13/2022 |  | 89 | 26 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 615186 | 02359 | 6.175 | Solar | 05_07_11W4 | 06/04/2024 | 06/14/2024 | 2 | 1 | 1 | 06/17/2024 | 06/17/2024 | 17 | 3 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 | 06/04/2024 | 8/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2024 | Connected |  | N
National Grid | QUINCY | 661571 | 02171 | 5.76 | Solar | 05_01_207W2 | 12/18/2024 | 01/10/2025 | 5 | 0 | 5 | 01/13/2025 | 01/13/2025 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 12/18/2024 | 3/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | LEOMINSTER | 185765 | 01453 | 4990 | Solar | 05_09_503L2 | 05/25/2018 | 05/25/2018 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2019 | 03/11/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 218741 | 01057 | 7.6 | Solar | 05_07_99W61 | 04/10/2019 | 04/22/2019 | 7 | 0 | 7 | 04/23/2019 | 04/23/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2019 |  | 12/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 714619 | 02370 | 7.6 | Solar | 05_07_91W49 | 08/26/2025 | 09/16/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 88 | 73 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 177092 | 02301 | 40.25 | Solar | 05_09_604W3 | 01/19/2017 | 01/19/2017 | 0 | 0 | 0 | 01/19/2017 | 01/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2017 |  | 1/24/2018 | N | EXP | 366 |  |  | 0 | 0 | 0 | 5/15/2017 | 5/15/2017 | 5/15/2017 | Connected |  | N
National Grid | NEW BRAINTREE | 176806 | 01531 | 6 | Solar | 05_05_344W4 | 04/27/2016 | 04/27/2016 | 8 | 8 | 0 | 05/10/2016 | 05/10/2016 | 177 | 0 | 177 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2016 |  | 5/3/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 415927 | 02019 | 3.8 | Solar | 05_12_16W2 | 03/14/2022 | 03/15/2022 | 1 | 0 | 1 | 03/16/2022 | 03/16/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2022 | 03/14/2022 | 4/14/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | EVERETT | 337942 | 02149 | 0 | Other | 05_05_320W5 | 04/07/2021 | 04/30/2021 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/02/2021 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITINSVILLE | 429786 | 01588 | 7.6 | Solar | 05_07_910W51 | 05/10/2022 | 05/11/2022 | 1 | 0 | 1 | 05/12/2022 | 05/12/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  | 6/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | N
National Grid | HANOVER | 656127 | 02339 | 5.76 | Solar | 05_07_11W4 | 11/25/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/25/2024 | 2/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | QUINCY | 661778 | 02171 | 10 | Solar | 05_01_207W2 | 12/19/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | LEOMINSTER | 185764 | 01453 | 4990 | Solar | 05_09_503L2 | 06/18/2018 | 06/18/2018 | 13 | 13 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2019 | 03/23/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 392758 | 01057 | 100 | Solar | 05_07_99W61 | 11/05/2021 | 12/02/2021 | 17 | 9 | 8 | 12/03/2021 | 12/03/2021 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2022 |  | 6/27/2024 | N | EXP | 9 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | ROCKLAND | 580004 | 02370 | 220 | Solar | 05_07_92W43 | 12/29/2023 | 01/18/2024 | 12 | 7 | 5 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  | 7/22/2026 | N | STD | 36 |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | BROCKTON | 177316 | 02301 | 1000 | Solar | 05_09_604W3 | 02/10/2017 | 02/15/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2017 | 02/22/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 | 02/10/2017 | 12/21/2024 | Y | STD | 15 | 02/08/2023 | 03/07/2023 | 28 | 0 | 28 |  |  | 12/23/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 176842 | 01535 | 10 | Solar | 05_05_344W4 | 05/02/2016 | 05/02/2016 | 34 | 34 | 0 | 06/21/2016 | 06/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2016 |  | 5/7/2017 | N | EXP | 312 |  |  | 0 | 0 | 0 | 1/17/2017 | 1/17/2017 | 1/20/2017 | Connected |  | N
National Grid | BELLINGHAM | 418839 | 02019 | 11.5 | Solar | 05_12_16W2 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2023 | 02/14/2023 | 7/16/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 450732 | 02149 | 19.195 | Solar | 05_05_320W5 | 08/11/2022 | 08/18/2022 | 6 | 4 | 2 | 08/19/2022 | 08/19/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2022 | 08/11/2022 | 10/17/2023 | Y | EXP | 365 | 12/16/2022 | 01/18/2023 | 34 | 0 | 34 |  |  | 1/23/2023 | Connected |  | N
National Grid | SUTTON | 445451 | 01590 | 1500 | Solar | 05_07_910W51 | 07/27/2022 | 08/12/2022 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/15/2022 | 09/13/2022 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 661143 | 02359 | 3.8 | Solar | 05_07_11W4 | 12/17/2024 | 02/12/2025 | 3 | 0 | 3 | 02/13/2025 | 02/13/2025 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2025 | Connected |  | N
National Grid | QUINCY | 663213 | 02171 | 7.6 | Solar | 05_01_207W2 | 12/31/2024 | 01/03/2025 | 13 | 9 | 4 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 12/31/2024 | 4/4/2026 | Y | EXP | 365 | 09/30/2025 | 10/13/2025 | 14 | 0 | 14 |  |  | 10/17/2025 | Connected |  | N
National Grid | LEOMINSTER | 190886 | 01453 | 3.8 | Solar | 05_09_503L2 | 07/17/2018 | 12/20/2018 | 8 | 0 | 8 | 10/04/2018 | 10/04/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 396029 | 01057 | 6 | Solar | 05_07_99W61 | 12/07/2021 | 01/07/2022 | 22 | 20 | 2 | 01/10/2022 | 01/10/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2022 | 12/07/2021 | 11/20/2023 | Y | EXP | 365 | 06/15/2022 | 10/11/2022 | 118 | 0 | 118 |  |  | 6/1/2023 | Connected |  | N
National Grid | ROCKLAND | 749132 | 02370 | 11.52 | Solar | 05_07_92W43 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 177315 | 02301 | 1800 | Solar | 05_09_604W3 | 02/10/2017 | 03/10/2017 | 18 | 16 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2017 | 03/24/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 | 02/10/2017 | 12/9/2024 | Y | STD | 15 | 09/13/2024 | 09/12/2024 | 0 | 0 | 0 |  |  | 12/23/2024 | Connected |  | N
National Grid | BARRE | 176883 | 01005 | 10 | Solar | 05_05_344W4 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2016 |  | 5/10/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 | 9/8/2016 | 9/8/2016 | 9/14/2016 | Connected |  | N
National Grid | BELLINGHAM | 502664 | 02019 | 6 | Solar | 05_12_16W2 | 02/22/2023 | 02/24/2023 | 2 | 0 | 2 | 02/27/2023 | 02/27/2023 | 179 | 160 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 377003 | 02149 | 20.8 | Solar | 05_05_320W5 | 08/26/2021 |  | 186 | 167 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITINSVILLE | 469930 | 01588 | 0 | Other | 05_07_910W51 | 01/06/2023 | 03/02/2023 | 37 | 27 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2023 | 05/04/2023 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 681259 | 02359 | 10 | Solar | 05_07_11W4 | 03/28/2025 | 05/05/2025 | 27 | 23 | 4 | 06/17/2025 | 06/17/2025 | 41 | 19 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 | 03/28/2025 | 9/10/2026 | Y | EXP | 365 | 10/15/2025 | 12/01/2025 | 48 | 0 | 48 |  |  | 12/3/2025 | Connected |  | N
National Grid | QUINCY | 665465 | 02169 | 10 | Solar | 05_01_207W2 | 01/13/2025 | 03/12/2025 | 17 | 13 | 4 | 03/13/2025 | 03/13/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 194853 | 01453 | 10 | Solar | 05_09_503L2 | 09/16/2018 | 10/29/2018 | 13 | 13 | 0 | 10/30/2018 | 10/30/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 419309 | 01057 | 240 | Solar | 05_07_99W61 | 05/26/2022 | 07/17/2022 | 33 | 26 | 7 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 175290 | 02370 | 189 | Solar | 05_07_92W43 | 11/06/2014 | 11/06/2014 | 5 | 1 | 4 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2014 | 11/06/2014 | 12/31/2016 | Y | EXP | 743 | 09/29/2016 | 10/31/2016 | 21 | 0 | 21 | 2/5/2015 | 2/5/2015 | 2/23/2017 | Connected |  | N
National Grid | BROCKTON | 177314 | 02301 | 1650 | Solar | 05_09_604W3 | 02/10/2017 | 02/15/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2017 | 02/22/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2017 | 02/10/2017 | 12/8/2023 | Y | STD | 83 | 08/04/2022 | 01/31/2023 | 181 | 0 | 181 | 2/1/2023 | 10/26/2023 | 11/21/2023 | Connected |  | N
National Grid | BARRE | 177422 | 01005 | 7.6 | Solar | 05_05_344W4 | 12/05/2016 | 12/05/2016 | 2 | 2 | 0 | 12/08/2016 | 12/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2016 |  | 12/11/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 7/5/2017 | 7/5/2017 | 7/5/2017 | Connected |  | N
National Grid | BELLINGHAM | 570390 | 02019 | 11.4 | Solar | 05_12_16W2 | 11/09/2023 | 11/16/2023 | 2 | 0 | 2 | 08/20/2024 | 08/20/2024 | 52 | 45 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 394432 | 02149 | 15.36 | Solar | 05_05_320W5 | 12/16/2021 | 12/28/2021 | 1 | 0 | 1 | 12/20/2021 | 12/20/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 |  | 5/27/2023 | N | EXP | 387 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 541461 | 01590 | 10 | Solar | 05_07_910W51 | 07/21/2023 | 12/12/2023 | 99 | 99 | 0 | 12/13/2023 | 12/13/2023 | 138 | 134 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 |  | 7/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | PEMBROKE | 704591 | 02359 | 900 | Solar | 05_07_12W1 | 10/16/2025 | 10/31/2025 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2025 | 02/12/2026 | 69 | 50 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | QUINCY | 668536 | 02171 | 7.6 | Solar | 05_01_207W2 | 01/29/2025 | 02/25/2025 | 4 | 0 | 4 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 5/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | LEOMINSTER | 204943 | 01453 | 7.6 | Solar | 05_09_503L2 | 02/06/2019 | 02/15/2019 | 6 | 0 | 6 | 02/19/2019 | 02/19/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 | 02/06/2019 | 9/16/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/19/2020 | Connected |  | N
National Grid | MONSON | 668646 | 01057 | 15.2 | Solar | 05_07_99W61 | 01/29/2025 | 02/07/2025 | 3 | 0 | 3 | 04/10/2025 | 04/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | ROCKLAND | 175289 | 02370 | 370 | Solar | 05_07_92W43 | 11/06/2014 | 11/06/2014 | 5 | 1 | 4 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2014 | 11/06/2014 | 12/31/2016 | Y | EXP | 743 | 09/29/2016 | 11/21/2016 | 35 | 0 | 35 | 2/7/2017 | 2/7/2017 | 2/16/2017 | Connected |  | N
National Grid | EASTON | 177323 | 02356 | 7.6 | Solar | 05_09_604W3 | 06/16/2016 | 06/16/2016 | 0 | 0 | 0 | 06/21/2016 | 06/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/26/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 10/6/2016 | 10/6/2016 | 10/6/2016 | Connected |  | N
National Grid | NEW BRAINTREE | 177567 | 01531 | 7.6 | Solar | 05_05_344W4 | 09/14/2017 | 09/14/2017 | 9 | 9 | 0 | 09/27/2017 | 09/27/2017 | 124 | 0 | 124 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/19/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 580198 | 02038 | 7.25 | Solar | 05_12_16W2 | 01/09/2024 |  | 40 | 40 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 406978 | 02149 | 10 | Solar | 05_05_320W5 | 02/21/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/21/2022 | 8/3/2023 | Y | EXP | 365 | 06/23/2022 | 07/15/2022 | 23 | 0 | 23 |  |  | 8/13/2022 | Connected |  | N
National Grid | NORTHBRIDGE | 636087 | 01534 | 0 | Other | 05_07_910W51 | 11/08/2024 | 12/09/2024 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/10/2025 | 210 | 191 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 725168 | 02359 | 249.49 | Solar | 05_07_12W1 | 10/13/2025 | 12/02/2025 | 34 | 27 | 7 | 12/03/2025 | 12/03/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2026 | 10/13/2025 | 8/20/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | QUINCY | 670642 | 02170 | 10 | Solar | 05_01_207W2 | 02/06/2025 | 04/11/2025 | 28 | 25 | 3 | 04/14/2025 | 04/14/2025 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 211308 | 01453 | 15 | Solar | 05_09_503L2 | 03/12/2019 | 03/15/2019 | 2 | 1 | 1 | 03/18/2019 | 03/18/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 | 03/12/2019 | 11/22/2019 | Y | EXP | 245 | 08/06/2019 | 08/14/2019 | 8 | 0 | 8 |  |  | 8/21/2019 | Connected |  | N
National Grid | MONSON | 707767 | 01057 | 13.8 | Solar | 05_07_99W61 | 07/30/2025 | 08/06/2025 | 4 | 0 | 4 | 08/07/2025 | 08/07/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2026 | Connected |  | N
National Grid | ROCKLAND | 177236 | 02370 | 5.86 | Solar | 05_07_92W43 | 11/07/2016 | 11/07/2016 | 28 | 28 | 0 | 12/19/2016 | 12/19/2016 | 18 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/13/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 177354 | 02356 | 499 | Solar | 05_09_604W3 | 02/15/2017 | 04/26/2017 | 47 | 47 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2017 | 04/26/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 |  | 2/26/2021 | N | STD | 995 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 177816 | 01531 | 7.6 | Solar | 05_05_344W4 | 04/04/2017 | 04/04/2017 | 5 | 1 | 4 | 04/11/2017 | 04/11/2017 | 241 | 0 | 241 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2017 |  | 4/9/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 586800 | 02019 | 6.38 | Solar | 05_12_16W2 | 02/19/2024 | 02/21/2024 | 2 | 0 | 2 | 02/22/2024 | 02/22/2024 | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 533804 | 02149 | 15.36 | Solar | 05_05_320W5 | 06/26/2023 | 08/07/2023 | 30 | 28 | 2 |  |  | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBRIDGE | 645804 | 01534 | 0 | Other | 05_07_910W51 | 01/17/2025 | 04/22/2025 | 65 | 55 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/23/2025 | 05/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 174444 | 02339 | 45 | Solar | 05_07_12W1 | 07/09/2012 | 07/09/2012 | 6 | 0 | 6 | 07/19/2012 | 07/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 9/28/2012 | 9/28/2012 | 3/6/2013 | Connected |  | N
National Grid | QUINCY | 670824 | 02169 | 3.9 | Solar | 05_01_207W2 | 02/07/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2025 | Connected |  | N
National Grid | LEOMINSTER | 325183 | 01453 | 7.6 | Solar | 05_09_503L2 | 11/11/2020 | 11/17/2020 | 3 | 0 | 3 | 11/18/2020 | 11/18/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 |  | 11/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2021 | Connected |  | N
National Grid | MONSON | 424099 | 01057 | 187.5 | Solar | 05_07_99W62 | 06/02/2022 | 06/24/2022 | 15 | 9 | 6 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 06/02/2022 | 3/9/2026 | Y | STD | 28 | 09/23/2025 |  | 165 | 46 | 119 |  |  |  | Construction |  | Y
National Grid | ROCKLAND | 295460 | 02370 | 7.6 | Solar | 05_07_92W43 | 06/09/2020 | 06/15/2020 | 3 | 3 | 0 | 06/16/2020 | 06/16/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2020 |  | 6/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 177436 | 02356 | 10 | Solar | 05_09_604W3 | 06/30/2016 | 06/30/2016 | 2 | 2 | 0 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2016 | 06/30/2016 | 7/6/2017 | Y | EXP | 353 | 10/12/2016 | 10/12/2016 | 0 | 0 | 0 | 11/21/2016 | 11/21/2016 | 11/21/2016 | Connected |  | N
National Grid | NEW BRAINTREE | 178016 | 01531 | 15.2 | Solar | 05_05_344W4 | 06/29/2017 | 06/29/2017 | 4 | 3 | 1 | 07/06/2017 | 07/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 | 06/29/2017 | 7/4/2018 | Y | EXP | 362 | 12/26/2017 | 12/20/2017 | 0 | 0 | 0 | 1/16/2018 | 1/16/2018 | 1/22/2018 | Connected |  | N
National Grid | BELLINGHAM | 600537 | 02019 | 7.6 | Solar | 05_12_16W2 | 04/16/2024 | 06/04/2024 | 34 | 30 | 4 | 06/05/2024 | 06/05/2024 | 29 | 17 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 04/16/2024 | 11/30/2025 | Y | EXP | 365 | 03/04/2025 | 10/13/2025 | 224 | 0 | 224 |  |  | 10/22/2025 | Connected |  | N
National Grid | EVERETT | 542382 | 02149 | 1000 | Solar | 05_05_320W5 | 01/10/2024 |  | 69 | 61 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 657507 | 01590 | 7.6 | Solar | 05_07_910W51 | 11/27/2024 | 12/19/2024 | 5 | 0 | 5 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | HANOVER | 177063 | 02339 | 360 | Solar | 05_07_12W1 | 03/20/2017 | 03/20/2017 | 110 | 108 | 2 | 08/24/2017 | 08/24/2017 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/25/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 671919 | 02188 | 10 | Solar | 05_01_207W2 | 02/13/2025 | 03/06/2025 | 3 | 0 | 3 | 03/07/2025 | 03/07/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2025 | Connected |  | N
National Grid | LEOMINSTER | 340846 | 01453 | 9.8 | Solar | 05_09_503L2 | 03/30/2021 | 04/06/2021 | 4 | 0 | 4 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2021 | 03/30/2021 | 6/7/2023 | Y | EXP | 365 | 09/11/2021 | 11/16/2021 | 67 | 4 | 63 |  |  | 6/8/2023 | Connected |  | Y
National Grid | MONSON | 672406 | 01057 | 15.2 | Solar | 05_07_99W62 | 02/26/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ROCKLAND | 331116 | 02370 | 187.5 | Solar | 05_07_92W43 | 12/14/2020 | 12/21/2020 | 4 | 0 | 4 | 12/22/2020 | 12/22/2020 | 109 | 91 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2021 |  | 8/1/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 177428 | 02356 | 997 | Solar | 05_09_604W3 | 02/28/2017 | 04/07/2017 | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2017 | 04/26/2017 | 12 | 7 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2017 | 02/28/2017 | 5/3/2023 | Y | STD | 541 | 11/18/2022 | 04/18/2023 | 153 | 43 | 110 |  |  | 4/26/2023 | Connected |  | N
National Grid | BARRE | 178065 | 01005 | 15.2 | Solar | 05_05_344W4 | 09/05/2017 | 09/05/2017 | 10 | 9 | 1 | 09/19/2017 | 09/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2017 |  | 9/10/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 | 11/13/2017 | 11/13/2017 | 11/28/2017 | Connected |  | N
National Grid | BELLINGHAM | 620312 | 02019 | 10 | Solar | 05_12_16W2 | 06/25/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 06/25/2024 | 8/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | EVERETT | 545580 | 02149 | 7.6 | Solar | 05_05_320W5 | 08/21/2023 | 09/01/2023 | 10 | 9 | 1 | 09/05/2023 | 09/05/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 08/21/2023 | 11/15/2024 | Y | EXP | 365 | 01/19/2024 | 04/03/2024 | 76 | 0 | 76 |  |  | 4/5/2024 | Connected |  | N
National Grid | SUTTON | 657506 | 01590 | 6 | Solar | 05_07_910W51 | 11/27/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/27/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | HANOVER | 177062 | 02339 | 420 | Solar | 05_07_12W1 | 03/20/2017 | 03/20/2017 | 110 | 108 | 2 | 08/24/2017 | 08/24/2017 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/25/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 695112 | 02188 | 15.58 | Solar | 05_01_207W2 | 06/11/2025 | 06/18/2025 | 3 | 0 | 3 | 09/12/2025 | 09/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2025 | Connected |  | Y
National Grid | LEOMINSTER | 397572 | 01453 | 9.45 | Solar | 05_09_503L2 | 11/30/2021 | 12/14/2021 | 10 | 9 | 1 | 12/15/2021 | 12/15/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2022 |  | 2/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2022 | Connected |  | Y
National Grid | WALES | 738840 | 01081 | 17.6 | Solar | 05_07_99W62 | 12/10/2025 | 12/30/2025 | 13 | 12 | 1 | 12/31/2025 | 12/31/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  | 2/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ROCKLAND | 394644 | 02370 | 9.86 | Solar | 05_07_92W43 | 11/15/2021 | 11/16/2021 | 1 | 0 | 1 | 11/17/2021 | 11/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 12/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2022 | Connected |  | N
National Grid | EASTON | 177724 | 02356 | 4800 | Solar | 05_09_604W3 | 10/04/2017 | 10/18/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2017 | 11/08/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 | 6/14/2018 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 178693 | 01531 | 10 | Solar | 05_05_344W4 | 02/09/2018 | 02/06/2018 | 70 | 0 | 70 | 05/21/2018 | 05/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2018 |  | 2/12/2019 | N | EXP | 251 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 641458 | 02019 | 7.98 | Solar | 05_12_16W2 | 09/19/2024 | 09/27/2024 | 4 | 0 | 4 | 09/30/2024 | 09/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/19/2024 | 11/13/2025 | Y | EXP | 365 | 02/28/2025 | 02/27/2025 | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | EVERETT | 620478 | 02149 | 15.2 | Solar | 05_05_320W5 | 06/27/2024 | 07/01/2024 | 2 | 0 | 2 | 07/02/2024 | 07/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/27/2024 | 7/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | SUTTON | 675216 | 01590 | 0 | Other | 05_07_910W51 | 06/25/2025 | 08/26/2025 | 42 | 32 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2025 | 09/23/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 177061 | 02339 | 300 | Solar | 05_07_12W1 | 03/20/2017 | 03/20/2017 | 90 | 88 | 2 | 07/27/2017 | 07/27/2017 | 51 | 18 | 33 | 08/31/2017 | 10/10/2017 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 10/10/2017 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 3/25/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 499837 | 02188 | 240 | Solar | 05_01_207W3 | 02/20/2023 | 03/24/2023 | 24 | 14 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEOMINSTER | 409183 | 01453 | 0 | Solar | 05_09_503L2 | 01/28/2022 | 02/25/2022 | 20 | 19 | 1 | 02/28/2022 | 02/28/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 |  | 4/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2022 | Connected |  | N
National Grid | MONSON | 747413 | 01057 | 11.4 | Solar | 05_07_99W62 | 01/26/2026 | 01/27/2026 | 1 | 0 | 1 | 01/28/2026 | 01/28/2026 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ABINGTON | 654218 | 02351 | 5.76 | Solar | 05_07_92W43 | 11/15/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/15/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 178305 | 02356 | 1855 | Solar | 05_09_604W3 | 01/09/2018 | 03/09/2018 | 41 | 21 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/07/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/15/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 186502 | 01531 | 10 | Solar | 05_05_344W4 | 06/13/2018 | 06/13/2018 | 7 | 0 | 7 | 06/26/2018 | 06/26/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 676976 | 02019 | 999.9 | Solar | 05_12_16W3 | 04/08/2025 | 06/10/2025 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | EVERETT | 626980 | 02149 | 7.6 | Solar | 05_05_320W5 | 07/23/2024 | 07/28/2024 | 4 | 0 | 4 | 07/29/2024 | 07/29/2024 | 39 | 25 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 07/23/2024 | 12/18/2025 | Y | EXP | 365 | 05/23/2025 | 05/22/2025 | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | SUTTON | 687539 | 01590 | 10 | Solar | 05_07_910W51 | 04/24/2025 | 04/30/2025 | 4 | 0 | 4 | 05/01/2025 | 05/01/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | PEMBROKE | 177060 | 02359 | 480 | Solar | 05_07_12W1 | 03/20/2017 | 03/20/2017 | 85 | 83 | 2 | 07/20/2017 | 07/20/2017 | 56 | 24 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/25/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 620051 | 02188 | 9000 | Solar | 05_01_207W3 | 08/12/2024 | 11/20/2024 | 69 | 60 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2024 | 06/30/2025 | 149 | 130 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEOMINSTER | 419511 | 01453 | 15.2 | Solar | 05_09_503L2 | 03/23/2022 | 03/29/2022 | 5 | 4 | 1 | 03/30/2022 | 03/30/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2022 |  | 5/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | N
National Grid | MONSON | 177595 | 01057 | 323 | Solar | 05_07_99W62 | 07/17/2017 | 07/17/2017 | 10 | 10 | 0 | 07/31/2017 | 07/31/2017 | 165 | 3 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 |  | 7/22/2018 | N | EXP | 326 |  |  | 0 | 0 | 0 |  |  | 6/12/2018 | Connected |  | N
National Grid | ABINGTON | 724358 | 02351 | 15.2 | Solar | 05_07_92W43 | 10/06/2025 | 10/09/2025 | 3 | 0 | 3 | 10/10/2025 | 10/10/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 12/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2026 | Connected |  | N
National Grid | EASTON | 193356 | 02356 | 4998 | Solar | 05_09_604W3 | 10/01/2018 | 10/15/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 12/20/2018 | 45 | 26 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 187250 | 01531 | 11.4 | Solar | 05_05_344W4 | 07/10/2018 | 07/27/2018 | 11 | 7 | 4 | 07/30/2018 | 07/30/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 461 |  |  | 0 | 0 | 0 |  |  | 11/7/2019 | Connected |  | N
National Grid | BELLINGHAM | 705094 | 02019 | 300 | Solar | 05_12_16W3 | 08/18/2025 | 11/10/2025 | 58 | 51 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 01/05/2026 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | EVERETT | 626948 | 02149 | 7.6 | Solar | 05_05_320W5 | 07/24/2024 | 07/31/2024 | 2 | 1 | 1 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 | 07/24/2024 | 8/15/2025 | Y | EXP | 365 | 11/14/2024 | 12/02/2024 | 19 | 0 | 19 |  |  | 2/5/2025 | Connected |  | Y
National Grid | WHITINSVILLE | 174931 | 01588 | 180 | Solar | 05_07_910W52 | 08/26/2013 | 08/26/2013 | 8 | 1 | 7 | 09/10/2013 | 09/10/2013 | 725 | 398 | 327 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2015 |  | 2/18/2016 | N | EXP | 212 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 195005 | 02359 | 720 | Solar | 05_07_12W1 | 09/27/2018 | 10/25/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 | 05/09/2019 | 93 | 8 | 85 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 754766 | 02188 | 19.76 | Solar | 05_01_207W3 | 03/05/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LEOMINSTER | 425011 | 01453 | 10 | Solar | 05_09_503L2 | 05/23/2022 | 05/25/2022 | 2 | 1 | 1 | 05/26/2022 | 05/26/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2022 |  | 7/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2023 | Connected |  | Y
National Grid | WALES | 345576 | 01081 | 9.6 | Solar | 05_07_99W62 | 03/08/2021 | 03/10/2021 | 1 | 0 | 1 | 03/11/2021 | 03/11/2021 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2021 |  | 11/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2021 | Connected |  | N
National Grid | ABINGTON | 723650 | 02351 | 17.799 | Solar | 05_07_92W43 | 10/02/2025 | 10/08/2025 | 4 | 2 | 2 | 10/09/2025 | 10/09/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 297453 | 02356 | 420 | Solar | 05_09_604W3 | 07/28/2020 | 09/28/2020 | 43 | 36 | 7 | 09/29/2020 | 09/29/2020 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEW BRAINTREE | 187518 | 01531 | 3.8 | Solar | 05_05_344W4 | 06/25/2018 | 06/25/2018 | 1 | 0 | 1 | 07/02/2018 | 07/02/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 720512 | 02019 | 11.4 | Solar | 05_12_16W3 | 01/12/2026 | 01/13/2026 | 25 | 22 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | EVERETT | 639198 | 02149 | 7.6 | Solar | 05_05_320W5 | 09/10/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/10/2024 | 12/10/2025 | Y | EXP | 365 | 02/13/2025 | 02/24/2025 | 12 | 0 | 12 |  |  | 4/1/2025 | Connected |  | N
National Grid | WHITINSVILLE | 177770 | 01588 | 15.2 | Solar | 05_07_910W52 | 10/09/2017 | 10/09/2017 | 14 | 14 | 0 | 10/31/2017 | 10/31/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2017 |  | 10/15/2018 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 223125 | 02359 | 60 | Solar | 05_07_12W1 | 04/27/2019 | 05/21/2019 | 16 | 12 | 4 | 05/22/2019 | 05/22/2019 | 268 | 153 | 115 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 174258 | 02188 | 111 | Solar | 05_01_207W3 | 02/29/2012 | 02/29/2012 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 8/6/2012 | N | EXP | 128 |  |  | 0 | 0 | 0 | 8/16/2012 | 8/16/2012 | 3/2/2013 | Connected |  | N
National Grid | LEOMINSTER | 530542 | 01453 | 3.8 | Solar | 05_09_503L2 | 06/12/2023 | 06/13/2023 | 1 | 0 | 1 | 06/14/2023 | 06/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 |  | 9/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2023 | Connected |  | N
National Grid | MONSON | 412225 | 01057 | 0 | Battery Add-On | 05_07_99W62 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 443464 | 02351 | 999 | Solar | 05_07_92W44 | 11/15/2022 | 12/01/2022 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/02/2022 | 12/27/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11/15/2022 | 1/4/2027 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | EASTON | 385046 | 02375 | 2660 | Solar | 05_09_604W3 | 10/26/2021 | 01/11/2022 | 53 | 44 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/12/2022 | 11/21/2022 | 216 | 211 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 189314 | 01535 | 10 | Solar | 05_05_344W4 | 06/27/2018 | 06/27/2018 | 16 | 11 | 5 | 11/21/2018 | 11/21/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 176460 | 02019 | 56 | Solar | 05_12_16W3 | 02/04/2016 | 02/04/2016 | 1 | 1 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2016 |  | 2/13/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/22/2016 | 11/22/2016 | Connected |  | N
National Grid | SAUGUS | 647702 | 01906 | 10 | Solar | 05_05_320W5 | 10/28/2024 | 11/19/2024 | 8 | 5 | 3 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2025 | Connected |  | N
National Grid | SUTTON | 194677 | 01590 | 400 | Solar | 05_07_910W52 | 08/29/2018 | 09/10/2018 | 6 | 0 | 6 | 09/11/2018 | 09/11/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | HANOVER | 295847 | 02339 | 10 | Solar | 05_07_12W1 | 06/10/2020 | 06/19/2020 | 7 | 5 | 2 | 06/22/2020 | 06/22/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 6/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2021 | Connected |  | N
National Grid | WEYMOUTH | 175337 | 02188 | 100 | Solar | 05_01_207W3 | 01/19/2015 | 01/19/2015 | 4 | 1 | 3 | 01/26/2015 | 01/26/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2015 |  | 6/30/2015 | N | EXP | 138 |  |  | 0 | 0 | 0 | 2/12/2015 | 2/12/2015 | 6/11/2015 | Connected |  | N
National Grid | LEOMINSTER | 554489 | 01453 | 3.8 | Solar | 05_09_503L2 | 09/12/2023 | 09/13/2023 | 1 | 0 | 1 | 09/14/2023 | 09/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 | 09/12/2023 | 11/11/2024 | Y | EXP | 365 | 12/27/2023 | 01/18/2024 | 23 | 0 | 23 |  |  | 3/8/2024 | Connected |  | N
National Grid | MONSON | 553916 | 01057 | 10 | Solar | 05_07_99W62 | 04/03/2024 | 09/15/2023 | 3 | 0 | 3 | 04/09/2024 | 04/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 574910 | 02351 | 90 | Solar | 05_07_92W44 | 01/09/2024 | 04/11/2024 | 65 | 56 | 9 | 04/12/2024 | 04/12/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | EASTON | 454366 | 02356 | 10 | Solar | 05_09_604W3 | 09/06/2022 | 09/12/2022 | 4 | 1 | 3 | 09/13/2022 | 09/13/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 |  | 9/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2023 | Connected |  | N
National Grid | NEW BRAINTREE | 190511 | 01531 | 10 | Solar | 05_05_344W4 | 07/11/2018 | 10/29/2018 | 10 | 7 | 3 | 10/30/2018 | 10/30/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 | 07/11/2018 | 11/12/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | BELLINGHAM | 178582 | 02019 | 37.8 | Solar | 05_12_16W3 | 01/31/2018 | 01/31/2018 | 20 | 0 | 20 | 04/13/2018 | 04/13/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 2/6/2019 | N | EXP | 28 |  |  | 0 | 0 | 0 |  |  | 9/5/2018 | Connected |  | N
National Grid | MALDEN | 653727 | 02148 | 10 | Solar | 05_05_320W5 | 11/18/2024 | 12/19/2024 | 4 | 0 | 4 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 3/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | WHITINSVILLE | 191825 | 01588 | 249.8 | Solar | 05_07_910W52 | 08/27/2018 | 09/10/2018 | 8 | 0 | 8 | 09/11/2018 | 09/11/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 |  | 12/31/2020 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  | 12/30/2020 | Connected |  | N
National Grid | PEMBROKE | 306140 | 02359 | 120 | Solar | 05_07_12W1 | 12/11/2020 | 12/21/2020 | 5 | 0 | 5 | 12/22/2020 | 12/22/2020 | 71 | 47 | 24 | 05/13/2021 | 07/08/2021 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  | 07/08/2021 | 22 | 2 | 20 |  |  | 0 | 0 | 0 | 6/25/2021 |  | 2/15/2026 | N | EXP | 271 | 07/30/2021 | 03/21/2025 | 1331 | 1289 | 42 |  |  | 12/31/2025 | Connected |  | N
National Grid | WEYMOUTH | 176599 | 02188 | 75 | Solar | 05_01_207W3 | 12/29/2015 | 12/29/2015 | 0 | 0 | 0 | 12/30/2015 | 12/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2016 |  | 1/4/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 11/15/2016 | 11/15/2016 | 11/15/2016 | Connected |  | N
National Grid | LANCASTER | 648797 | 01523 | 5.76 | Solar | 05_09_503L2 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 577753 | 01057 | 0 | Other | 05_07_99W62 | 01/04/2024 | 02/21/2024 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2024 | 02/28/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 729000 | 02351 | 3.8 | Solar | 05_07_92W44 | 10/24/2025 | 10/27/2025 | 1 | 0 | 1 | 10/28/2025 | 10/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | EASTON | 480402 | 02356 | 7.6 | Solar | 05_09_604W3 | 11/28/2022 | 12/05/2022 | 6 | 5 | 1 | 12/06/2022 | 12/06/2022 | 58 | 38 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  | 3/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 192457 | 01535 | 3.8 | Solar | 05_05_344W4 | 08/01/2018 | 08/27/2018 | 5 | 4 | 1 | 08/28/2018 | 08/28/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  | 10/30/2019 | N | EXP | 414 |  |  | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | BELLINGHAM | 215396 | 02019 | 5 | Solar | 05_12_16W3 | 04/02/2019 | 04/09/2019 | 4 | 0 | 4 | 04/10/2019 | 04/10/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2019 | 04/02/2019 | 2/17/2020 | Y | EXP | 365 | 01/30/2020 | 01/29/2020 | 0 | 0 | 0 |  |  | 2/19/2020 | Connected |  | N
National Grid | MALDEN | 664108 | 02148 | 10 | Solar | 05_05_320W5 | 01/07/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | WHITINSVILLE | 207842 | 01588 | 7.6 | Solar | 05_07_910W52 | 02/05/2019 | 02/13/2019 | 5 | 0 | 5 | 02/14/2019 | 02/14/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 399003 | 02359 | 499.5 | Solar | 05_07_12W1 | 12/14/2021 | 01/18/2022 | 24 | 16 | 8 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2022 | 12/14/2021 | 12/15/2023 | Y | STD | 565 |  |  | 0 | 0 | 0 |  |  | 12/12/2023 | Connected |  | N
National Grid | WEYMOUTH | 176930 | 02188 | 360 | Solar | 05_01_207W3 | 01/27/2016 | 01/27/2016 | 2 | 2 | 0 | 02/01/2016 | 02/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2016 | 01/27/2016 | 4/14/2017 | Y | EXP | 35 | 12/08/2016 | 03/21/2017 | 69 | 0 | 69 | 4/7/2017 | 4/7/2017 | 4/12/2017 | Connected |  | N
National Grid | LEOMINSTER | 655987 | 01453 | 7.6 | Solar | 05_09_503L2 | 11/21/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | MONSON | 655138 | 01057 | 3.8 | Solar | 05_07_99W62 | 11/19/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | ABINGTON | 174704 | 02351 | 75 | Solar | 05_07_92W44 | 06/14/2013 | 06/14/2013 | 6 | 0 | 6 | 06/26/2013 | 06/26/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2013 |  | 8/16/2013 | N | EXP | 38 |  |  | 0 | 0 | 0 | 12/6/2013 | 12/6/2013 | 12/12/2013 | Connected |  | N
National Grid | EASTON | 479620 | 02375 | 10 | Solar | 05_09_604W3 | 12/08/2022 | 12/12/2022 | 2 | 0 | 2 | 12/13/2022 | 12/13/2022 | 63 | 38 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 192331 | 01005 | 3.8 | Solar | 05_05_344W4 | 07/31/2018 | 08/24/2018 | 3 | 3 | 0 | 08/27/2018 | 08/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 07/31/2018 | 5/14/2020 | Y | EXP | 626 | 11/06/2019 | 12/17/2019 | 41 | 0 | 41 |  |  | 1/28/2020 | Connected |  | N
National Grid | BELLINGHAM | 217215 | 02019 | 3 | Solar | 05_12_16W3 | 04/09/2019 | 04/17/2019 | 5 | 0 | 5 | 04/18/2019 | 04/18/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2019 | 04/09/2019 | 4/2/2020 | Y | EXP | 365 | 02/19/2020 | 02/26/2020 | 7 | 0 | 7 |  |  | 3/12/2020 | Connected |  | N
National Grid | MALDEN | 669902 | 02148 | 4.35 | Solar | 05_05_320W5 | 02/10/2025 | 09/15/2025 | 64 | 64 | 0 | 09/16/2025 | 09/16/2025 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2025 | Connected |  | N
National Grid | DOUGLAS | 209527 | 01516 | 3.8 | Solar | 05_07_910W52 | 02/12/2019 | 02/22/2019 | 6 | 0 | 6 | 02/25/2019 | 02/25/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  | 7/23/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 408117 | 02339 | 80 | Solar | 05_07_12W1 | 01/27/2022 | 02/15/2022 | 14 | 10 | 4 | 02/16/2022 | 02/16/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2022 | 01/27/2022 | 10/31/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2022 | Connected |  | N
National Grid | WEYMOUTH | 177185 | 02188 | 225 | Solar | 05_01_207W3 | 08/12/2016 | 08/12/2016 | 2 | 2 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2016 |  | 11/20/2017 | N | EXP | 433 |  |  | 0 | 0 | 0 | 9/13/2017 | 9/13/2017 | 9/13/2017 | Connected |  | N
National Grid | LEOMINSTER | 661116 | 01453 | 11.5 | Solar | 05_09_503L2 | 12/17/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 5/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | MONSON | 656847 | 01057 | 5.76 | Solar | 05_07_99W62 | 11/26/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | ABINGTON | 175117 | 02351 | 84 | Solar | 05_07_92W44 | 10/18/2013 | 10/18/2013 | 5 | 0 | 5 | 10/28/2013 | 10/28/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2013 |  | 12/31/2013 | N | EXP | 57 |  |  | 0 | 0 | 0 | 2/11/2014 | 2/11/2014 | 2/25/2014 | Connected |  | N
National Grid | EASTON | 492334 | 02356 | 2000 | Solar | 05_09_604W3 | 03/08/2023 | 03/22/2023 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2023 | 05/16/2023 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 198992 | 01531 | 250 | Solar | 05_05_344W4 | 10/19/2018 | 11/14/2018 | 15 | 3 | 12 | 11/15/2018 | 11/15/2018 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 |  | 1/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 218392 | 02019 | 5 | Solar | 05_12_16W3 | 04/18/2019 | 04/26/2019 | 6 | 5 | 1 | 04/29/2019 | 04/29/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2019 | 04/18/2019 | 4/24/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2020 | Connected |  | N
National Grid | MALDEN | 673581 | 02148 | 5.76 | Solar | 05_05_320W5 | 02/25/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 | 02/25/2025 | 5/1/2026 | Y | EXP | 365 | 08/07/2025 | 10/09/2025 | 64 | 0 | 64 |  |  | 11/20/2025 | Connected |  | N
National Grid | SUTTON | 255341 | 01590 | 57.6 | Solar | 05_07_910W52 | 09/20/2019 | 10/01/2019 | 7 | 2 | 5 | 10/02/2019 | 10/02/2019 | 24 | 11 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2019 |  | 1/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2020 | Connected |  | N
National Grid | HANOVER | 657808 | 02339 | 11.4 | Solar | 05_07_12W1 | 12/10/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | WEYMOUTH | 178359 | 02189 | 17.28 | Solar | 05_01_207W3 | 03/01/2018 | 03/01/2018 | 10 | 0 | 10 | 04/27/2018 | 04/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 3/7/2019 | N | EXP | 234 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 667744 | 01453 | 7.6 | Solar | 05_09_503L2 | 01/24/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | MONSON | 424573 | 01057 | 480 | Solar | 05_07_99W63 | 06/03/2022 | 07/13/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2022 | 08/09/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 7/3/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ABINGTON | 177184 | 02351 | 270 | Solar | 05_07_92W44 | 08/15/2016 | 08/15/2016 | 0 | 0 | 0 | 08/15/2016 | 08/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2016 | 08/15/2016 | 8/20/2017 | Y | EXP | 353 | 02/22/2017 | 06/20/2017 | 82 | 0 | 82 | 8/9/2017 | 8/9/2017 | 8/14/2017 | Connected |  | N
National Grid | EASTON | 670324 | 02375 | 17.225 | Solar | 05_09_604W3 | 03/11/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 200884 | 01535 | 500 | Solar | 05_05_344W4 | 02/25/2019 | 03/18/2019 | 15 | 9 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2019 | 04/09/2019 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2019 | 02/25/2019 | 4/7/2021 | Y | STD | 321 | 09/30/2020 | 12/22/2020 | 83 | 0 | 83 | 3/30/2021 | 3/29/2021 | 4/7/2021 | Connected |  | N
National Grid | BELLINGHAM | 233774 | 02019 | 3.8 | Solar | 05_12_16W3 | 06/19/2019 | 07/09/2019 | 13 | 13 | 0 | 07/10/2019 | 07/10/2019 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2019 |  | 6/19/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 685167 | 01906 | 9.6 | Solar | 05_05_320W5 | 04/15/2025 | 05/22/2025 | 3 | 0 | 3 | 05/23/2025 | 05/23/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITINSVILLE | 268709 | 01588 | 7.6 | Solar | 05_07_910W52 | 12/06/2019 | 12/16/2019 | 6 | 6 | 0 | 12/17/2019 | 12/17/2019 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 |  | 2/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2021 | Connected |  | N
National Grid | PEMBROKE | 747238 | 02359 | 10 | Solar | 05_07_12W2 | 01/23/2026 | 01/28/2026 | 3 | 0 | 3 | 01/29/2026 | 01/29/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEYMOUTH | 185527 | 02188 | 4950 | Solar | 05_01_207W3 | 05/21/2018 | 06/19/2018 | 6 | 0 | 6 |  |  | 30 | 5 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2019 | 05/21/2018 | 4/30/2021 | Y | STD | 726 |  |  | 0 | 0 | 0 |  |  | 4/7/2021 | Connected |  | N
National Grid | LEOMINSTER | 671245 | 01453 | 10 | Solar | 05_09_503L2 | 02/10/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 581885 | 01057 | 100 | Solar | 05_07_99W63 | 02/22/2024 | 03/06/2024 | 9 | 0 | 9 |  |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | ABINGTON | 177366 | 02351 | 20 | Solar | 05_07_92W44 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2016 |  | 7/3/2017 | N | EXP | 36 |  |  | 0 | 0 | 0 | 11/2/2016 | 11/2/2016 | 11/2/2016 | Connected |  | N
National Grid | EASTON | 669890 | 02375 | 5.76 | Solar | 05_09_604W3 | 02/04/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N
National Grid | NEW BRAINTREE | 239323 | 01531 | 10 | Solar | 05_05_344W4 | 02/05/2020 | 02/11/2020 | 3 | 0 | 3 | 02/12/2020 | 02/12/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 | 02/05/2020 | 2/9/2022 | Y | EXP | 365 | 07/15/2020 | 07/28/2020 | 13 | 0 | 13 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 306220 | 02019 | 10 | Solar | 05_12_16W3 | 08/11/2020 | 08/13/2020 | 1 | 0 | 1 | 08/14/2020 | 08/14/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2020 | Connected |  | N
National Grid | SAUGUS | 686786 | 01906 | 15.2 | Solar | 05_05_320W5 | 04/22/2025 | 04/25/2025 | 3 | 0 | 3 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 04/22/2025 | 6/11/2026 | Y | EXP | 365 | 08/06/2025 | 12/31/2025 | 148 | 0 | 148 |  |  | 1/9/2026 | Connected |  | N
National Grid | SUTTON | 291004 | 01590 | 499 | Solar | 05_07_910W52 | 05/08/2020 | 06/16/2020 | 26 | 21 | 5 | 06/17/2020 | 06/17/2020 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 174264 | 02359 | 16.83 | Solar | 05_07_12W2 | 12/28/2011 | 12/28/2011 | 8 | 0 | 8 | 01/19/2012 | 01/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2012 |  | 4/1/2012 | N | EXP | 3 |  |  | 0 | 0 | 0 | 3/30/2012 | 3/30/2012 | 4/12/2012 | Connected |  | N
National Grid | WEYMOUTH | 195313 | 02188 | 995 | Solar | 05_01_207W3 | 05/22/2020 | 06/16/2020 | 15 | 11 | 4 |  |  | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 683451 | 01453 | 3.8 | Solar | 05_09_503L2 | 04/15/2025 |  | 113 | 25 | 88 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 177849 | 01057 | 166.5 | Solar | 05_07_99W63 | 04/06/2017 | 04/06/2017 | 7 | 7 | 0 | 04/19/2017 | 04/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2017 | 04/06/2017 | 4/12/2018 | Y | EXP | 324 | 05/24/2017 | 06/21/2017 | 19 | 0 | 19 | 12/15/2017 | 12/15/2017 | 12/21/2017 | Connected |  | N
National Grid | ABINGTON | 178108 | 02351 | 48 | Solar | 05_07_92W44 | 11/06/2017 | 11/06/2017 | 16 | 16 | 0 | 11/30/2017 | 11/30/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2017 |  | 11/11/2018 | N | EXP | 345 |  |  | 0 | 0 | 0 | 3/26/2018 | 3/26/2018 | 7/23/2018 | Connected |  | N
National Grid | EASTON | 694159 | 02356 | 20 | Solar | 05_09_604W3 | 05/29/2025 | 06/04/2025 | 4 | 0 | 4 | 06/05/2025 | 06/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2025 | 05/29/2025 | 7/11/2026 | Y | EXP | 365 | 11/14/2025 | 12/02/2025 | 19 | 0 | 19 |  |  | 12/27/2025 | Connected |  | N
National Grid | NEW BRAINTREE | 251916 | 01531 | 7.6 | Solar | 05_05_344W4 | 10/07/2019 | 10/30/2019 | 15 | 15 | 0 | 10/31/2019 | 10/31/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 |  | 12/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 405846 | 02038 | 0 | Battery Add-On | 05_12_16W3 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 03/04/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 313859 | 01906 | 800 | Solar | 05_05_321W1 | 01/27/2021 | 02/21/2021 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2021 | 05/20/2021 | 63 | 41 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 01/27/2021 | 6/19/2026 | Y | STD | 252 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | SUTTON | 358406 | 01590 | 9.8 | Solar | 05_07_910W52 | 06/10/2021 | 06/15/2021 | 3 | 0 | 3 | 06/16/2021 | 06/16/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2021 |  | 8/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 174363 | 02359 | 95 | Solar | 05_07_12W2 | 08/30/2011 | 08/30/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2012 |  | 5/30/2012 | N | EXP | 26 |  |  | 0 | 0 | 0 | 8/2/2012 | 8/2/2012 | 8/9/2012 | Connected |  | N
National Grid | WEYMOUTH | 203373 | 02188 | 19.52 | Solar | 05_01_207W3 | 12/10/2018 | 12/31/2018 | 13 | 5 | 8 | 01/02/2019 | 01/02/2019 | 28 | 23 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 699724 | 01453 | 19 | Solar | 05_09_503L2 | 06/19/2025 | 06/23/2025 | 2 | 0 | 2 | 06/24/2025 | 06/24/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N
National Grid | MONSON | 178160 | 01057 | 230 | Solar | 05_07_99W63 | 12/26/2017 | 12/26/2017 | 13 | 10 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/16/2018 | 01/30/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 | 12/26/2017 | 7/10/2019 | Y | STD | 384 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 201301 | 02370 | 250 | Solar | 05_07_92W44 | 11/16/2018 | 11/19/2018 | 0 | 0 | 0 | 11/20/2018 | 11/20/2018 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2018 |  | 12/31/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2019 | Connected |  | N
National Grid | EASTON | 699206 | 02375 | 11.4 | Solar | 05_09_604W3 | 06/19/2025 | 07/08/2025 | 13 | 12 | 1 | 07/31/2025 | 07/31/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 268733 | 01535 | 7.6 | Solar | 05_05_344W4 | 01/02/2020 | 01/10/2020 | 5 | 0 | 5 | 01/13/2020 | 01/13/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2020 | 01/02/2020 | 9/22/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2021 | Connected |  | N
National Grid | BELLINGHAM | 434702 | 02019 | 0 | Other | 05_12_16W3 | 07/12/2022 | 07/12/2022 | 67 | 58 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/12/2023 | 02/24/2023 | 30 | 10 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 634878 | 01906 | 996 | Solar | 05_05_321W1 | 12/10/2024 | 01/16/2025 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/17/2025 | 02/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SUTTON | 363041 | 01526 | 7.6 | Solar | 05_07_910W52 | 09/16/2021 | 09/17/2021 | 1 | 0 | 1 | 09/20/2021 | 09/20/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 |  | 10/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 175277 | 02359 | 42.57 | Solar | 05_07_12W2 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2014 |  | 11/28/2014 | N | EXP | 7 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/1/2015 | Connected |  | N
National Grid | WEYMOUTH | 330998 | 02188 | 10 | Solar | 05_01_207W3 | 12/10/2020 | 12/14/2020 | 1 | 0 | 1 | 12/15/2020 | 12/15/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 745113 | 01523 | 13.36 | Solar | 05_09_503L4 | 01/13/2026 | 01/26/2026 | 4 | 0 | 4 | 02/18/2026 | 02/18/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MONSON | 178648 | 01057 | 244 | Solar | 05_07_99W63 | 12/15/2017 | 12/15/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/02/2018 | 01/30/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 | 12/15/2017 | 8/6/2021 | Y | STD | 596 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 320150 | 02370 | 8.64 | Solar | 05_07_92W44 | 11/03/2020 | 11/19/2020 | 10 | 9 | 1 | 11/20/2020 | 11/20/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 11/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2021 | Connected |  | N
National Grid | EASTON | 334194 | 02375 | 0 | Other | 05_09_604W4 | 04/06/2021 | 04/30/2021 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BARRE | 281369 | 01005 | 7.6 | Solar | 05_05_344W4 | 04/14/2020 | 04/20/2020 | 3 | 0 | 3 | 04/21/2020 | 04/21/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2020 | 04/14/2020 | 3/31/2021 | Y | EXP | 365 | 12/23/2020 | 01/08/2021 | 16 | 0 | 16 |  |  | 2/18/2021 | Connected |  | N
National Grid | BELLINGHAM | 735668 | 02019 | 3.8 | Solar | 05_05_321W1 | 11/21/2025 | 12/24/2025 | 2 | 0 | 2 | 01/27/2026 | 01/27/2026 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MALDEN | 366907 | 02148 | 7.6 | Solar | 05_07_910W52 | 08/18/2021 |  | 31 | 26 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITINSVILLE | 176723 | 01588 | 10 | Solar | 05_07_12W2 | 02/22/2016 | 02/22/2016 | 4 | 4 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2016 |  | 2/28/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 6/14/2016 | 6/14/2016 | 6/15/2016 | Connected |  | N
National Grid | PEMBROKE | 348269 | 02359 | 400 | Solar | 05_01_207W3 | 05/14/2021 |  | 373 | 363 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 174449 | 02189 | 1000 | Solar | 05_09_503L4 | 07/11/2012 | 07/11/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/24/2012 | 10/16/2012 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 386079 | 01453 | 100 | Solar | 05_07_99W63 | 11/01/2021 | 12/09/2021 | 26 | 17 | 9 | 12/10/2021 | 12/10/2021 | 127 | 105 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 364216 | 01057 | 199.8 | Solar | 05_07_92W44 | 06/18/2021 | 07/07/2021 | 13 | 3 | 10 | 07/08/2021 | 07/08/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2021 |  | 12/10/2022 | N | EXP | 48 |  |  | 0 | 0 | 0 |  |  | 11/28/2022 | Connected |  | N
National Grid | ROCKLAND | 667804 | 02370 | 996 | Solar | 05_09_604W4 | 02/20/2025 | 03/25/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2025 | 04/24/2025 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 284138 | 02301 | 15.2 | Solar | 05_05_344W4 | 03/17/2020 | 04/13/2020 | 19 | 19 | 0 | 04/14/2020 | 04/14/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2020 | 03/17/2020 | 4/13/2021 | Y | EXP | 365 | 07/15/2020 | 12/05/2020 | 143 | 5 | 138 |  |  | 12/16/2020 | Connected |  | N
National Grid | NORTH BROOKFIELD | 437637 | 01535 | 350 | Solar | 05_12_16W3 | 09/01/2022 | 09/23/2022 | 15 | 5 | 10 |  |  | 68 | 47 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 09/01/2022 | 8/3/2025 | Y | STD | 133 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 749744 | 02019 | 15.2 | Solar | 05_05_321W1 | 02/06/2026 | 02/10/2026 | 2 | 0 | 2 | 02/11/2026 | 02/11/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MALDEN | 421190 | 02148 | 7.6 | Solar | 05_07_910W52 | 04/08/2022 | 06/10/2022 | 44 | 43 | 1 | 06/13/2022 | 06/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 176874 | 01569 | 10 | Solar | 05_07_12W2 | 03/02/2016 | 03/02/2016 | 4 | 4 | 0 | 03/08/2016 | 03/08/2016 | 212 | 0 | 212 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2016 |  | 3/7/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 426071 | 02359 | 15.2 | Solar | 05_01_207W3 | 04/26/2022 | 04/27/2022 | 1 | 0 | 1 | 04/28/2022 | 04/28/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2022 | 04/26/2022 | 10/20/2023 | Y | EXP | 365 | 09/30/2022 | 10/18/2022 | 19 | 0 | 19 |  |  | 5/4/2023 | Connected |  | Y
National Grid | WEYMOUTH | 174448 | 02189 | 1000 | Solar | 05_09_503L4 | 07/11/2012 | 07/11/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/24/2012 | 10/16/2012 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 408872 | 01453 | 0 | Battery Add-On | 05_07_99W63 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 03/02/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 389740 | 01057 | 0 | Other | 05_07_92W44 | 11/10/2021 | 01/04/2022 | 36 | 28 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/27/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 669274 | 02370 | 4316 | Solar | 05_09_604W4 | 02/21/2025 | 03/17/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2025 | 04/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | EASTON | 293030 | 02375 | 0 | Solar | 05_05_344W4 | 05/21/2020 | 06/12/2020 | 14 | 14 | 0 | 06/15/2020 | 06/15/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2020 | Connected |  | N
National Grid | NORTH BROOKFIELD | 576689 | 01535 | 0 | Battery Add-On | 05_12_16W3 | 12/08/2023 | 12/19/2023 | 7 | 6 | 1 | 12/20/2023 | 12/20/2023 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | BELLINGHAM | 177834 | 02019 | 3000 | Solar | 05_05_321W1 | 08/09/2017 | 08/09/2017 | 12 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2017 | 09/20/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2018 |  | 7/1/2019 | N | STD | 459 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 482498 | 01906 | 10 | Solar | 05_07_910W52 | 12/21/2022 | 12/26/2022 | 3 | 0 | 3 | 12/27/2022 | 12/27/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 177133 | 01569 | 99.9 | Solar | 05_07_12W2 | 01/23/2017 | 01/23/2017 | 4 | 4 | 0 | 01/27/2017 | 01/27/2017 | 206 | 82 | 124 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 | 01/23/2017 | 1/29/2018 | Y | EXP | 242 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 435106 | 02359 | 0 | Other | 05_01_207W3 | 07/01/2022 | 10/24/2022 | 78 | 68 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2022 | 11/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 174447 | 02188 | 1000 | Solar | 05_09_503L4 | 07/11/2012 | 07/11/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/24/2012 | 10/16/2012 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 422057 | 01453 | 4999.2 | Battery Add-On | 05_07_99W63 | 05/17/2022 |  | 188 | 26 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 389734 | 01010 | 0 | Other | 05_07_92W44 | 11/10/2021 | 01/04/2022 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 715130 | 02370 | 5.76 | Solar | 05_09_604W4 | 08/27/2025 | 09/23/2025 | 3 | 0 | 3 | 11/04/2025 | 11/04/2025 | 44 | 24 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 | 08/27/2025 | 1/20/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | EASTON | 307866 | 02375 | 7.6 | Solar | 05_05_344W4 | 09/03/2020 | 09/08/2020 | 1 | 0 | 1 | 09/09/2020 | 09/09/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2020 |  | 9/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 673208 | 01005 | 500 | Solar | 05_12_16W4 | 05/27/2025 | 06/26/2025 | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2025 | 07/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BELLINGHAM | 177833 | 02019 | 1980 | Solar | 05_05_321W1 | 08/09/2017 | 08/09/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2017 | 09/20/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2018 |  | 7/1/2019 | N | STD | 459 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 577710 | 01906 | 0 | Other | 05_07_910W52 | 01/04/2024 | 02/21/2024 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2024 | 02/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 183596 | 01569 | 0 | Solar | 05_07_12W2 | 06/04/2018 | 06/04/2018 | 0 | 0 | 0 | 06/06/2018 | 06/06/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 7/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2019 | Connected |  | N
National Grid | PEMBROKE | 439256 | 02359 | 4.64 | Solar | 05_01_207W3 | 06/26/2022 | 07/21/2022 | 18 | 17 | 1 | 07/22/2022 | 07/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 | 06/26/2022 | 8/19/2023 | Y | EXP | 365 | 09/21/2022 | 10/11/2022 | 21 | 0 | 21 |  |  | 5/5/2023 | Connected |  | N
National Grid | WEYMOUTH | 174483 | 02188 | 1000 | Solar | 05_09_503L4 | 02/01/2011 | 02/01/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/24/2011 | 05/06/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2012 | 02/01/2011 | 10/31/2012 | Y | STD | 21 | 05/31/2013 | 08/21/2013 | 56 | 0 | 56 | 8/20/2013 | 8/20/2013 | 9/13/2013 | Connected |  | N
National Grid | LEOMINSTER | 431370 | 01453 | 450 | Solar | 05_07_99W63 | 05/26/2022 | 06/13/2022 | 11 | 3 | 8 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 454234 | 01010 | 9.984 | Solar | 05_07_92W44 | 09/07/2022 | 09/06/2022 | 5 | 4 | 1 | 09/15/2022 | 09/15/2022 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2022 | 09/07/2022 | 12/13/2023 | Y | EXP | 4 | 12/06/2022 | 12/19/2022 | 14 | 0 | 14 |  |  | 11/2/2023 | Connected |  | N
National Grid | ROCKLAND | 740862 | 02370 | 5.76 | Solar | 05_09_604W4 | 12/17/2025 | 12/22/2025 | 3 | 0 | 3 | 12/23/2025 | 12/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 313308 | 02301 | 25 | Solar | 05_05_344W4 | 09/17/2020 | 09/23/2020 | 3 | 0 | 3 | 09/24/2020 | 09/24/2020 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2020 | 09/17/2020 | 10/22/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2021 | Connected |  | N
National Grid | BARRE | 729210 | 01005 | 200 | Solar | 05_12_16W4 | 10/30/2025 | 12/04/2025 | 23 | 17 | 6 | 12/05/2025 | 12/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BELLINGHAM | 178494 | 02019 | 0 | Solar | 05_05_321W1 | 12/01/2017 | 12/01/2017 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2018 | 03/26/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/9/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 601823 | 02148 | 6 | Solar | 05_07_910W52 | 04/15/2024 | 04/18/2024 | 4 | 1 | 3 | 04/19/2024 | 04/19/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 351129 | 01569 | 7.6 | Solar | 05_07_12W2 | 04/22/2021 | 04/27/2021 | 2 | 0 | 2 | 04/28/2021 | 04/28/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2021 |  | 4/27/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 519207 | 02359 | 10 | Solar | 05_01_207W3 | 05/03/2023 | 05/04/2023 | 1 | 0 | 1 | 05/05/2023 | 05/05/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 | 05/03/2023 | 6/15/2024 | Y | EXP | 365 | 08/26/2023 | 10/19/2023 | 55 | 0 | 55 |  |  | 10/28/2023 | Connected |  | N
National Grid | WEYMOUTH | 174698 | 02188 | 2000 | Solar | 05_09_503L4 | 01/01/2013 | 01/01/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 577761 | 01453 | 0 | Other | 05_07_99W63 | 01/04/2024 | 02/21/2024 | 31 | 28 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2024 | 02/28/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 460236 | 01010 | 9.984 | Solar | 05_07_92W44 | 09/21/2022 | 10/04/2022 | 10 | 9 | 1 | 10/05/2022 | 10/05/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 |  | 11/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2023 | Connected |  | N
National Grid | ROCKLAND | 745132 | 02370 | 5.76 | Solar | 05_09_604W4 | 01/13/2026 | 01/15/2026 | 3 | 0 | 3 | 02/03/2026 | 02/03/2026 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | EASTON | 343803 | 02375 | 0 | Solar | 05_05_344W4 | 02/26/2021 | 03/01/2021 | 1 | 1 | 0 | 03/02/2021 | 03/02/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2021 |  | 7/1/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 4/29/2022 | Connected |  | N
National Grid | BARRE | 175479 | 01005 | 240.8 | Solar | 05_12_16W4 | 03/13/2014 | 03/13/2014 | 10 | 5 | 5 | 03/31/2014 | 03/31/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2014 | 03/13/2014 | 8/29/2014 | Y | EXP | 128 | 08/26/2014 | 08/26/2014 | 0 | 0 | 0 | 12/12/2014 | 12/12/2014 | 1/2/2015 | Connected |  | N
National Grid | FRANKLIN | 193087 | 02038 | 4280 | Solar | 05_05_321W1 | 08/29/2018 | 09/19/2018 | 13 | 13 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2018 | 10/19/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 615040 | 02148 | 5.8 | Solar | 05_07_910W52 | 06/03/2024 | 06/10/2024 | 3 | 0 | 3 | 06/11/2024 | 06/11/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2024 | 06/03/2024 | 7/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 426693 | 01516 | 15.2 | Solar | 05_07_12W2 | 05/05/2022 | 05/06/2022 | 1 | 0 | 1 | 05/09/2022 | 05/09/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2022 |  | 8/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2023 | Connected |  | N
National Grid | PEMBROKE | 543114 | 02359 | 7.6 | Solar | 05_01_207W3 | 08/01/2023 | 08/02/2023 | 1 | 0 | 1 | 08/03/2023 | 08/03/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2023 |  | 9/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2023 | Connected |  | N
National Grid | WEYMOUTH | 175088 | 02189 | 1000 | Solar | 05_09_503L4 | 08/14/2012 | 08/14/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/23/2012 | 11/24/2012 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 691739 | 01453 | 7.6 | Solar | 05_07_99W63 | 05/26/2025 | 07/01/2025 | 4 | 0 | 4 | 07/02/2025 | 07/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIMFIELD | 601812 | 01010 | 15 | Solar | 05_07_92W44 | 04/16/2024 | 04/29/2024 | 10 | 8 | 2 | 04/30/2024 | 04/30/2024 | 12 | 6 | 6 | 05/23/2024 | 07/09/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 07/09/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 6/11/2024 |  | 10/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2025 | Connected |  | N
National Grid | HINGHAM | 174209 | 02043 | 500 | Solar | 05_09_604W4 | 02/27/2012 | 02/27/2012 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 376456 | 02375 | 7.6 | Solar | 05_05_344W4 | 08/17/2021 | 09/20/2021 | 23 | 23 | 0 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 9/19/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 175930 | 01005 | 10 | Solar | 05_12_16W4 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 8/2/2016 | Connected |  | N
National Grid | BELLINGHAM | 247851 | 02019 | 4966.6 | Solar | 05_05_321W1 | 11/08/2019 | 11/22/2019 | 9 | 6 | 3 |  |  | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 | 11/08/2019 | 1/3/2024 | Y | STD | 392 | 02/09/2023 | 07/18/2023 | 160 | 0 | 160 |  |  | 12/18/2023 | Connected |  | N
National Grid | MALDEN | 635888 | 02148 | 10 | Solar | 05_07_910W52 | 08/27/2024 | 09/13/2024 | 1 | 0 | 1 | 09/16/2024 | 09/16/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 549988 | 01516 | 0 | Other | 05_07_12W2 | 11/08/2023 | 12/21/2023 | 29 | 22 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2023 | 04/01/2024 | 68 | 49 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 568532 | 02339 | 6.96 | Solar | 05_01_207W3 | 11/15/2023 | 11/21/2023 | 5 | 3 | 2 | 11/22/2023 | 11/22/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 | 11/15/2023 | 6/30/2025 | Y | EXP | 365 | 01/30/2024 | 02/16/2024 | 18 | 0 | 18 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 175087 | 02188 | 1000 | Solar | 05_09_503L4 | 08/14/2012 | 08/14/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/23/2012 | 11/24/2012 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 693329 | 01453 | 200 | Solar | 05_07_99W63 | 05/29/2025 | 08/25/2025 | 58 | 48 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 609995 | 01069 | 0 | Solar | 05_07_92W44 | 05/17/2024 | 06/21/2024 | 23 | 21 | 2 | 06/24/2024 | 06/24/2024 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 | 05/17/2024 | 7/18/2025 | Y | EXP | 365 | 08/21/2024 | 08/20/2024 | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | ROCKLAND | 174323 | 02370 | 1000 | Solar | 05_09_604W4 | 01/13/2012 | 01/13/2012 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/8/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 391859 | 02375 | 0 | Other | 05_05_344W4 | 01/04/2022 | 01/20/2022 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2022 | 01/27/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 176915 | 01005 | 14.19 | Solar | 05_12_16W4 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 | 05/04/2016 | 5/10/2017 | Y | EXP | 348 |  |  | 0 | 0 | 0 | 12/6/2016 | 12/6/2016 | 11/15/2016 | Connected |  | N
National Grid | BELLINGHAM | 452462 | 02019 | 15.2 | Solar | 05_05_321W1 | 09/02/2022 | 09/13/2022 | 7 | 5 | 2 | 09/14/2022 | 09/14/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 1/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | Y
National Grid | REVERE | 640786 | 02151 | 17.6 | Solar | 05_07_910W52 | 09/17/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 118 | 97 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 690858 | 01534 | 11.5 | Solar | 05_07_12W2 | 05/13/2025 | 05/21/2025 | 5 | 2 | 3 | 05/22/2025 | 05/22/2025 | 29 | 6 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 605468 | 02359 | 11.4 | Solar | 05_01_207W3 | 04/24/2024 | 04/30/2024 | 2 | 0 | 2 | 05/01/2024 | 05/01/2024 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 175086 | 02188 | 2000 | Solar | 05_09_503L4 | 08/14/2012 | 08/14/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/23/2012 | 11/24/2012 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 721206 | 01453 | 0 | Solar | 05_07_9W1 | 09/25/2025 | 10/07/2025 | 8 | 6 | 2 | 10/08/2025 | 10/08/2025 | 53 | 32 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 1/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BRIMFIELD | 621684 | 01010 | 10 | Solar | 05_07_92W44 | 07/01/2024 | 07/12/2024 | 1 | 0 | 1 | 07/15/2024 | 07/15/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 | 07/01/2024 | 8/5/2025 | Y | EXP | 365 | 02/28/2025 | 03/27/2025 | 28 | 0 | 28 |  |  | 4/4/2025 | Connected |  | N
National Grid | ROCKLAND | 174603 | 02370 | 15 | Solar | 05_09_604W4 | 09/07/2011 | 09/07/2011 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2012 |  | 4/19/2012 | N | EXP | 48 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 4/19/2012 | Connected |  | N
National Grid | EASTON | 425595 | 02375 | 996 | Solar | 05_05_344W4 | 08/31/2022 | 09/20/2022 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2022 | 10/19/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 177140 | 01005 | 6 | Solar | 05_12_16W4 | 05/27/2016 | 05/27/2016 | 9 | 9 | 0 | 06/14/2016 | 06/14/2016 | 153 | 0 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 |  | 6/6/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 408286 | 02019 | 15.2 | Solar | 05_05_321W1 | 01/24/2022 | 01/26/2022 | 3 | 2 | 1 | 01/27/2022 | 01/27/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 |  | 3/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2022 | Connected |  | N
National Grid | REVERE | 686163 | 02151 | 11.5 | Solar | 05_07_910W52 | 04/18/2025 | 05/12/2025 | 14 | 10 | 4 | 05/13/2025 | 05/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | UXBRIDGE | 174876 | 01569 | 95 | Solar | 05_07_12W3 | 09/11/2012 | 09/11/2012 | 7 | 7 | 0 | 09/21/2012 | 09/21/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2012 |  | 12/17/2012 | N | EXP | 3 |  |  | 0 | 0 | 0 | 12/20/2012 | 12/20/2012 | 2/8/2013 | Connected |  | N
National Grid | PEMBROKE | 620474 | 02359 | 3.8 | Solar | 05_01_207W3 | 06/25/2024 | 07/19/2024 | 5 | 4 | 1 | 07/22/2024 | 07/22/2024 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 06/25/2024 | 10/4/2025 | Y | EXP | 365 | 12/20/2024 | 01/15/2025 | 27 | 0 | 27 |  |  | 2/4/2025 | Connected |  | N
National Grid | WEYMOUTH | 175402 | 02189 | 1080 | Solar | 05_09_503L4 | 11/21/2014 | 11/21/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/02/2014 | 12/19/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 | 11/21/2014 | 5/1/2016 | Y | STD | 276 | 01/10/2017 | 02/17/2017 | 27 | 0 | 27 |  |  | 3/10/2017 | Connected |  | N
National Grid | LEOMINSTER | 725210 | 01453 | 18.24 | Solar | 05_07_9W1 | 12/09/2025 | 12/29/2025 | 12 | 11 | 1 | 12/30/2025 | 12/30/2025 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2026 |  | 3/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BRIMFIELD | 653830 | 01010 | 9.57 | Solar | 05_07_92W44 | 11/12/2024 | 12/02/2024 | 6 | 2 | 4 | 12/03/2024 | 12/03/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | N
National Grid | ROCKLAND | 175214 | 02370 | 960 | Solar | 05_09_604W4 | 11/03/2014 | 11/03/2014 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2014 | 12/08/2014 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 03/18/2017 | 02/14/2017 | 0 | 0 | 0 | 5/9/2017 | 11/03/2014 | 9/27/2018 | Y | STD | 56 |  |  | 0 | 0 | 0 |  |  | 9/17/2018 | Connected |  | N
National Grid | EASTON | 442113 | 02375 | 240 | Solar | 05_05_344W4 | 07/08/2022 | 07/26/2022 | 12 | 3 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 1/7/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  | 2/24/2026 | Connected |  | N
National Grid | HUBBARDSTON | 177358 | 01452 | 7.6 | Solar | 05_12_16W4 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2017 |  | 2/21/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 10/10/2017 | 10/10/2017 | 8/31/2017 | Connected |  | N
National Grid | BELLINGHAM | 474060 | 02019 | 5100 | Solar | 05_05_321W1 | 06/02/2023 | 09/14/2023 | 71 | 61 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/15/2023 | 10/09/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 697216 | 02151 | 15.2 | Solar | 05_07_910W52 | 06/16/2025 | 06/17/2025 | 1 | 0 | 1 | 06/18/2025 | 06/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | UXBRIDGE | 176532 | 01569 | 428 | Solar | 05_07_12W3 | 12/17/2015 | 12/17/2015 | 0 | 0 | 0 | 12/18/2015 | 12/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2016 | 12/17/2015 | 12/23/2016 | Y | EXP | 354 | 06/08/2016 | 04/24/2017 | 217 | 0 | 217 | 5/12/2017 | 5/12/2017 | 5/12/2017 | Connected |  | N
National Grid | PEMBROKE | 644944 | 02359 | 3.8 | Solar | 05_01_207W3 | 10/03/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/03/2024 | 3/20/2026 | Y | EXP | 365 | 02/28/2025 | 12/02/2025 | 278 | 111 | 167 |  |  | 12/3/2025 | Connected |  | N
National Grid | WEYMOUTH | 176554 | 02188 | 7.6 | Solar | 05_09_503L4 | 10/05/2015 | 10/05/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2015 |  | 10/13/2016 | N | EXP | 353 |  |  | 0 | 0 | 0 | 5/9/2016 | 5/9/2016 | 5/12/2016 | Connected |  | N
National Grid | LEOMINSTER | 751369 | 01453 | 15.2 | Solar | 05_07_9W1 | 02/23/2026 |  | 9 | 6 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BRIMFIELD | 679979 | 01010 | 22.75 | Solar | 05_07_92W44 | 03/27/2025 | 04/28/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2025 | Connected |  | N
National Grid | ROCKLAND | 175217 | 02370 | 480 | Solar | 05_09_604W4 | 11/03/2014 | 11/03/2014 | 8 | 5 | 3 | 11/17/2014 | 11/17/2014 | 131 | 0 | 131 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 472217 | 02375 | 10 | Solar | 05_05_344W4 | 12/21/2022 | 12/22/2022 | 1 | 0 | 1 | 12/23/2022 | 12/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/21/2022 | 12/27/2024 | Y | EXP | 365 | 07/28/2023 | 02/13/2024 | 200 | 3 | 197 |  |  | 4/24/2024 | Connected |  | N
National Grid | HUBBARDSTON | 189147 | 01452 | 10 | Solar | 05_12_16W4 | 06/26/2018 | 06/26/2018 | 6 | 1 | 5 | 09/14/2018 | 09/14/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 |  | 10/10/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2018 | Connected |  | N
National Grid | BELLINGHAM | 474054 | 02019 | 5100 | Solar | 05_05_321W1 | 06/02/2023 | 09/13/2023 | 70 | 60 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2023 | 10/09/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 716010 | 02151 | 17.6 | Solar | 05_07_910W52 | 09/02/2025 | 09/24/2025 | 15 | 10 | 5 | 09/25/2025 | 09/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | UXBRIDGE | 176721 | 01569 | 10 | Solar | 05_07_12W3 | 02/22/2016 | 02/22/2016 | 73 | 73 | 0 | 06/08/2016 | 06/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 |  | 2/28/2017 | N | EXP | 259 |  |  | 0 | 0 | 0 | 11/17/2016 | 11/17/2016 | 11/17/2016 | Connected |  | N
National Grid | PEMBROKE | 652489 | 02359 | 0 | Solar | 05_01_207W3 | 11/06/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 50 | 26 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | WEYMOUTH | 176591 | 02188 | 496 | Solar | 05_09_503L4 | 10/08/2015 | 10/08/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 | 12/02/2015 | 03/01/2016 | 60 | 7 | 53 | 10/14/2015 | 11/10/2015 | 19 | 0 | 19 |  | 03/01/2016 | 60 | 7 | 53 |  |  | 0 | 0 | 0 |  |  | 10/14/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 614112 | 01453 | 11.5 | Battery Add-On | 05_07_9W1 | 05/29/2024 | 06/04/2024 | 5 | 4 | 1 | 06/05/2024 | 06/05/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2024 | 05/29/2024 | 7/2/2025 | Y | EXP | 365 | 07/24/2024 | 07/24/2024 | 1 | 0 | 1 |  |  | 8/28/2024 | Connected |  | N
National Grid | BRIMFIELD | 680303 | 01010 | 10 | Solar | 05_07_92W44 | 04/04/2025 |  | 74 | 72 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 175544 | 02189 | 1000 | Solar | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2015 | 12/05/2014 | 3/31/2018 | Y | STD | 83 | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 | 2/21/2018 | 2/21/2018 | 3/6/2018 | Connected |  | N
National Grid | EASTON | 478736 | 02356 | 10 | Solar | 05_05_344W4 | 12/08/2022 | 12/12/2022 | 2 | 0 | 2 | 12/13/2022 | 12/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2023 | 12/08/2022 | 7/12/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2023 | Connected |  | N
National Grid | BARRE | 189054 | 01005 | 10 | Solar | 05_12_16W4 | 06/26/2018 | 06/26/2018 | 3 | 1 | 2 | 08/06/2018 | 08/06/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 06/26/2018 | 6/26/2020 | Y | EXP | 65 | 05/07/2020 | 05/18/2020 | 9 | 0 | 9 |  |  | 6/3/2020 | Connected |  | N
National Grid | FRANKLIN | 657082 | 02038 | 10 | Solar | 05_05_321W1 | 11/26/2024 | 12/02/2024 | 2 | 0 | 2 | 12/03/2024 | 12/03/2024 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | REVERE | 727065 | 02151 | 23 | Solar | 05_07_910W52 | 10/24/2025 | 10/28/2025 | 2 | 0 | 2 | 10/29/2025 | 10/29/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2026 | Connected |  | N
National Grid | UXBRIDGE | 236381 | 01569 | 150 | Solar | 05_07_12W3 | 06/12/2019 | 06/29/2019 | 11 | 8 | 3 | 07/01/2019 | 07/01/2019 | 32 | 26 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2019 | 06/12/2019 | 10/30/2020 | Y | EXP | 365 | 08/08/2020 | 08/14/2020 | 6 | 0 | 6 |  |  | 10/21/2020 | Connected |  | N
National Grid | PEMBROKE | 653697 | 02359 | 7.6 | Solar | 05_01_207W3 | 11/15/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/15/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | WEYMOUTH | 176817 | 02189 | 990 | Solar | 05_09_503L4 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/06/2015 | 12/08/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/11/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 620078 | 01453 | 7.6 | Solar | 05_07_9W1 | 06/25/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 | 06/25/2024 | 8/15/2025 | Y | EXP | 365 | 02/07/2025 | 02/06/2025 | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | PALMER | 346959 | 01069 | 499 | Solar | 05_07_92W54 | 07/13/2021 | 08/04/2021 | 16 | 13 | 3 |  |  | 74 | 37 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 07/13/2021 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WEYMOUTH | 175543 | 02189 | 557 | Solar | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2015 | N | STD |  | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 508761 | 02375 | 5.8 | Solar | 05_05_344W4 | 03/14/2023 | 03/14/2023 | 0 | 0 | 0 | 03/15/2023 | 03/15/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2023 | 03/14/2023 | 9/10/2024 | Y | EXP | 365 | 06/30/2023 | 09/08/2023 | 71 | 0 | 71 |  |  | 9/14/2023 | Connected |  | N
National Grid | BARRE | 195285 | 01005 | 10 | Solar | 05_12_16W4 | 10/16/2018 | 11/15/2018 | 14 | 9 | 5 | 11/16/2018 | 11/16/2018 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 | 10/16/2018 | 12/27/2019 | Y | EXP | 365 | 07/09/2019 | 07/15/2019 | 6 | 0 | 6 |  |  | 8/20/2019 | Connected |  | N
National Grid | BELLINGHAM | 660886 | 02019 | 6.825 | Solar | 05_05_321W1 | 12/16/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | REVERE | 594698 | 02151 | 10 | Solar | 05_07_911W13 | 03/05/2024 | 04/25/2024 | 2 | 0 | 2 | 04/26/2024 | 04/26/2024 | 24 | 15 | 9 | 06/26/2024 | 08/23/2024 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  | 08/23/2024 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 8/26/2024 |  | 3/31/2026 | N | EXP | 365 | 11/08/2024 | 01/28/2026 | 446 | 202 | 244 |  |  |  | Completion Documents |  | N
National Grid | UXBRIDGE | 341344 | 01516 | 15.2 | Solar | 05_07_12W3 | 02/09/2021 | 02/10/2021 | 0 | 0 | 0 | 02/11/2021 | 02/11/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2021 |  | 2/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2021 | Connected |  | N
National Grid | PEMBROKE | 676801 | 02359 | 7.6 | Solar | 05_01_207W3 | 03/10/2025 | 04/28/2025 | 18 | 14 | 4 | 04/29/2025 | 04/29/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | WEYMOUTH | 178083 | 02189 | 5000 | Solar | 05_09_503L4 | 05/09/2017 | 05/09/2017 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2017 | 06/30/2017 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/14/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 681906 | 01453 | 7.6 | Solar | 05_07_9W1 | 09/22/2025 | 09/26/2025 | 4 | 1 | 3 | 09/29/2025 | 09/29/2025 | 47 | 32 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/2/2026 | Connected |  | N
National Grid | PALMER | 695285 | 01069 | 750 | Solar | 05_07_92W54 | 11/07/2025 | 01/07/2026 | 39 | 34 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2026 | 02/05/2026 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WEYMOUTH | 175542 | 02189 | 540 | Solar | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2015 | 12/05/2014 | 3/31/2018 | Y | STD | 83 | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 | 2/21/2018 | 2/21/2018 | 3/6/2018 | Connected |  | N
National Grid | EASTON | 516130 | 02356 | 5 | Solar | 05_05_344W4 | 04/19/2023 | 04/25/2023 | 5 | 2 | 3 | 04/26/2023 | 04/26/2023 | 65 | 42 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 04/19/2023 | 9/21/2024 | Y | EXP | 365 | 02/29/2024 | 03/26/2024 | 27 | 0 | 27 |  |  | 3/28/2024 | Connected |  | N
National Grid | BARRE | 195873 | 01005 | 10 | Solar | 05_12_16W4 | 09/27/2019 | 10/01/2019 | 1 | 0 | 1 | 10/02/2019 | 10/02/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 673801 | 02019 | 0 | Battery Add-On | 05_05_321W1 | 02/24/2025 | 02/25/2025 | 1 | 0 | 1 | 02/26/2025 | 02/26/2025 | 61 | 41 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 654832 | 02151 | 7.6 | Solar | 05_07_911W13 | 11/18/2024 | 12/09/2024 | 7 | 3 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 | 11/18/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | UXBRIDGE | 455605 | 01569 | 15.2 | Solar | 05_07_12W3 | 09/16/2022 | 09/22/2022 | 4 | 4 | 0 | 09/23/2022 | 09/23/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2022 |  | 12/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 686521 | 02359 | 5.76 | Solar | 05_01_207W3 | 04/21/2025 | 05/14/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 178495 | 02190 | 3000 | Solar | 05_09_503L4 | 12/04/2017 | 02/01/2018 | 42 | 41 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2018 | 03/03/2018 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 174592 | 01453 | 15 | Solar | 05_07_9W2 | 11/16/2011 | 11/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2012 |  | 1/31/2012 | N | EXP | 21 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 2/10/2012 | Connected |  | N
National Grid | BRIMFIELD | 722879 | 01010 | 11.5 | Solar | 05_07_92W54 | 09/30/2025 | 11/10/2025 | 27 | 22 | 5 | 11/12/2025 | 11/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEYMOUTH | 175541 | 02189 | 380 | Solar | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/09/2016 | 05/09/2016 | 0 | 0 | 0 | 12/22/2015 | 12/05/2014 | 3/31/2018 | Y | STD | 83 | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 | 2/21/2018 | 2/21/2018 | 3/6/2018 | Connected |  | N
National Grid | EASTON | 516573 | 02375 | 6 | Solar | 05_05_344W4 | 04/20/2023 | 04/21/2023 | 1 | 0 | 1 | 04/24/2023 | 04/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 203604 | 01005 | 3.8 | Solar | 05_12_16W4 | 01/24/2019 | 01/30/2019 | 4 | 4 | 0 | 01/31/2019 | 01/31/2019 | 228 | 0 | 228 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 175913 | 02019 | 500 | Natural Gas | 05_05_321W10 | 03/11/2015 | 03/11/2015 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2015 | 04/15/2015 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2017 | 03/11/2015 | 6/1/2018 | Y | STD | 441 | 07/12/2017 | 07/28/2017 | 12 | 0 | 12 | 1/26/2018 | 1/26/2018 | 4/27/2018 | Connected |  | N
National Grid | REVERE | 175364 | 02151 | 20 | Solar | 05_07_911W13 | 11/13/2014 | 11/13/2014 | 5 | 1 | 4 | 11/21/2014 | 11/21/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2014 |  | 1/31/2015 | N | EXP | 53 |  |  | 0 | 0 | 0 | 4/24/2015 | 4/24/2015 | 6/26/2015 | Connected |  | N
National Grid | UXBRIDGE | 485756 | 01569 | 17.11 | Solar | 05_07_12W3 | 12/15/2022 | 12/20/2022 | 4 | 1 | 3 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2023 |  | 2/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2023 | Connected |  | N
National Grid | PEMBROKE | 714915 | 02359 | 6.08 | Solar | 05_01_207W3 | 08/26/2025 | 10/22/2025 | 14 | 11 | 3 | 10/23/2025 | 10/23/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 184096 | 02189 | 1875 | Solar | 05_09_503L4 | 05/08/2018 | 05/08/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/09/2019 | 07/13/2020 | 380 | 357 | 23 | 8/4/2020 | 05/08/2018 | 2/1/2022 | Y | CMPX | 46 | 08/06/2021 | 12/01/2021 | 118 | 7 | 111 |  |  | 12/29/2021 | Connected |  | N
National Grid | LEOMINSTER | 177792 | 01453 | 468 | Solar | 05_07_9W2 | 08/02/2017 | 08/02/2017 | 68 | 68 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2017 | 12/18/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 | 08/02/2017 | 10/19/2021 | Y | STD | 197 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 174114 | 01069 | 1500 | Solar | 05_07_92W54 | 03/30/2012 | 03/30/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/17/2012 | 06/25/2012 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2012 | 03/30/2012 | 10/31/2012 | Y | STD | 35 | 07/31/2013 | 09/27/2013 | 41 | 0 | 41 | 9/25/2013 | 9/25/2013 | 10/24/2013 | Connected |  | N
National Grid | WEYMOUTH | 175752 | 02189 | 480 | Solar | 05_09_604W4 | 10/31/2014 | 10/31/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 12/08/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 521532 | 02356 | 7.6 | Solar | 05_05_344W4 | 05/02/2023 | 05/04/2023 | 2 | 0 | 2 | 05/05/2023 | 05/05/2023 | 104 | 76 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 223563 | 01005 | 106.6 | Solar | 05_12_16W4 | 04/29/2019 | 05/16/2019 | 12 | 7 | 5 | 05/17/2019 | 05/17/2019 | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2019 | 04/29/2019 | 8/6/2021 | Y | EXP | 72 | 11/04/2020 | 04/07/2021 | 154 | 0 | 154 |  |  | 8/5/2021 | Connected |  | N
National Grid | BELLINGHAM | 438621 | 02019 | 10 | Solar | 05_05_321W10 | 10/27/2022 | 06/30/2022 | 2 | 0 | 2 | 11/01/2022 | 11/01/2022 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2022 | 10/27/2022 | 7/20/2024 | Y | EXP | 365 | 06/09/2023 | 06/21/2023 | 13 | 0 | 13 |  |  | 8/2/2023 | Connected |  | N
National Grid | REVERE | 177162 | 02151 | 79 | Solar | 05_07_911W13 | 10/28/2016 | 10/28/2016 | 0 | 0 | 0 | 11/01/2016 | 11/01/2016 | 303 | 2 | 301 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2016 |  | 2/6/2018 | N | EXP | 449 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 521091 | 01569 | 23 | Solar | 05_07_12W3 | 05/02/2023 | 05/04/2023 | 2 | 0 | 2 | 05/05/2023 | 05/05/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2023 |  | 6/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2024 | Connected |  | N
National Grid | BROCKTON | 405711 | 02301 | 0 | Other | 05_01_207W4 | 02/23/2022 | 04/01/2022 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2022 | 04/05/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 02/23/2022 |  | Y | STD | 116 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WEYMOUTH | 190328 | 02190 | 2820 | Solar | 05_09_503L4 | 08/14/2018 | 08/20/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2018 | 10/09/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 261964 | 01453 | 0 | Natural Gas | 05_07_9W2 | 04/17/2020 | 04/20/2020 | 0 | 0 | 0 |  |  | 147 | 135 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2021 |  | 1/20/2023 | N | STD | 78 |  |  | 0 | 0 | 0 |  |  | 12/23/2022 | Connected |  | N
National Grid | PALMER | 174939 | 01069 | 83.8 | Solar | 05_07_92W54 | 10/31/2011 | 10/31/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 175977 | 02189 | 760 | Solar | 05_09_604W4 | 05/07/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2016 | 08/11/2016 | 50 | 0 | 50 | 12/9/2015 | 05/07/2015 | 6/30/2016 | Y | STD | 24 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 556593 | 02375 | 6 | Solar | 05_05_344W4 | 01/05/2024 | 01/16/2024 | 6 | 5 | 1 | 01/17/2024 | 01/17/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2024 | 01/05/2024 | 2/14/2025 | Y | EXP | 365 | 06/12/2024 | 07/17/2024 | 36 | 0 | 36 |  |  | 8/20/2024 | Connected |  | N
National Grid | BARRE | 257961 | 01005 | 5 | Solar | 05_12_16W4 | 11/13/2019 | 11/20/2019 | 6 | 6 | 0 | 11/21/2019 | 11/21/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2019 | 11/13/2019 | 11/13/2020 | Y | EXP | 365 | 03/25/2020 | 04/07/2020 | 13 | 0 | 13 |  |  | 5/22/2020 | Connected |  | N
National Grid | BELLINGHAM | 753399 | 02019 | 10 | Solar | 05_05_321W2 | 02/26/2026 | 03/03/2026 | 3 | 0 | 3 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 190934 | 02151 | 3.8 | Solar | 05_07_911W13 | 07/17/2018 | 10/24/2018 | 5 | 5 | 0 | 10/25/2018 | 10/25/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 |  | 7/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 660352 | 01569 | 7.6 | Solar | 05_07_12W3 | 12/12/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | BROCKTON | 439851 | 02301 | 990 | Solar | 05_01_207W4 | 08/12/2022 | 11/16/2022 | 64 | 54 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 12/13/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | WEYMOUTH | 194417 | 02190 | 3000 | Solar | 05_09_503L4 | 10/09/2018 | 10/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 | 01/29/2019 | 61 | 42 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 475879 | 01453 | 7.6 | Solar | 05_07_9W2 | 12/06/2022 | 12/09/2022 | 3 | 0 | 3 | 12/12/2022 | 12/12/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 | 12/06/2022 | 7/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2023 | Connected |  | N
National Grid | BRIMFIELD | 175768 | 01010 | 1000 | Solar | 05_07_92W54 | 06/06/2014 | 06/06/2014 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/25/2014 | 10/03/2014 | 70 | 68 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 175975 | 02189 | 990 | Solar | 05_09_604W4 | 05/07/2015 | 05/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 558058 | 02375 | 6 | Solar | 05_05_344W4 | 09/29/2023 | 10/05/2023 | 4 | 0 | 4 | 10/06/2023 | 10/06/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2023 |  | 11/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | BARRE | 263607 | 01005 | 10 | Solar | 05_12_16W4 | 11/12/2019 | 11/20/2019 | 6 | 6 | 0 | 11/21/2019 | 11/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 174622 | 02019 | 2000 | Solar | 05_05_321W2 | 04/14/2011 | 04/14/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2011 | 04/14/2011 | 6/1/2012 | Y | STD | 182 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 6/1/2012 | Connected |  | N
National Grid | REVERE | 194001 | 02151 | 15.2 | Solar | 05_07_911W13 | 08/20/2018 | 08/23/2018 | 3 | 2 | 1 | 08/24/2018 | 08/24/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2018 |  | 10/30/2019 | N | EXP | 432 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | NORTHBRIDGE | 743058 | 01534 | 11.5 | Solar | 05_07_12W4 | 01/02/2026 | 01/05/2026 | 2 | 0 | 2 | 01/23/2026 | 01/23/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROCKTON | 657558 | 02301 | 10 | Solar | 05_01_207W4 | 12/16/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/16/2024 | 3/14/2026 | Y | EXP | 365 | 06/12/2025 |  | 268 | 0 | 268 |  |  |  | Completion Documents |  | N
National Grid | WEYMOUTH | 229566 | 02190 | 15.2 | Solar | 05_09_503L4 | 05/20/2019 | 05/30/2019 | 6 | 0 | 6 | 05/31/2019 | 05/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 6/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2019 | Connected |  | N
National Grid | LEOMINSTER | 540130 | 01453 | 7.6 | Solar | 05_07_9W2 | 11/05/2023 | 08/11/2023 | 1 | 0 | 1 | 11/07/2023 | 11/07/2023 | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 11/05/2023 | 3/11/2025 | Y | EXP | 365 | 03/28/2024 | 04/03/2024 | 7 | 0 | 7 |  |  | 4/17/2024 | Connected |  | N
National Grid | BRIMFIELD | 176155 | 01010 | 490 | Solar | 05_07_92W54 | 02/02/2015 | 02/02/2015 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/19/2015 | 03/27/2015 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 177057 | 02189 | 4900.5 | Solar | 05_09_604W4 | 01/16/2017 | 01/19/2017 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/03/2017 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 | 01/16/2017 | 9/24/2021 | Y | STD | 996 | 02/28/2019 | 10/27/2020 | 608 | 5 | 603 | 6/4/2021 | 9/23/2021 | 9/24/2021 | Connected |  | N
National Grid | EASTON | 557516 | 02375 | 10 | Solar | 05_05_344W4 | 09/29/2023 | 10/12/2023 | 8 | 6 | 2 | 10/13/2023 | 10/13/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 | 09/29/2023 | 11/17/2024 | Y | EXP | 365 | 01/30/2024 | 04/23/2024 | 85 | 0 | 85 |  |  | 5/1/2024 | Connected |  | N
National Grid | BARRE | 341284 | 01005 | 5 | Solar | 05_12_16W4 | 02/12/2021 | 02/17/2021 | 1 | 0 | 1 | 02/18/2021 | 02/18/2021 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 | 02/12/2021 | 5/3/2022 | Y | EXP | 365 | 06/16/2021 | 07/26/2021 | 41 | 0 | 41 |  |  | 1/13/2022 | Connected |  | N
National Grid | BELLINGHAM | 175163 | 02019 | 1000 | Solar | 05_05_321W2 | 06/02/2011 | 06/02/2011 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 195391 | 02151 | 7.6 | Solar | 05_07_911W13 | 09/07/2018 | 10/17/2018 | 14 | 8 | 6 | 10/18/2018 | 10/18/2018 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2019 |  | 5/7/2019 | N | EXP | 12 |  |  | 0 | 0 | 0 |  |  | 5/4/2019 | Connected |  | N
National Grid | UXBRIDGE | 748187 | 01569 | 11.5 | Solar | 05_07_12W4 | 01/29/2026 | 02/02/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 725213 | 02301 | 100 | Solar | 05_01_207W4 | 10/08/2025 | 10/29/2025 | 14 | 7 | 7 |  |  | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WEYMOUTH | 306870 | 02190 | 17.6 | Solar | 05_09_503L4 | 01/22/2021 | 01/27/2021 | 3 | 2 | 1 | 01/28/2021 | 01/28/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 567935 | 01453 | 10 | Solar | 05_07_9W2 | 11/14/2023 | 11/16/2023 | 2 | 0 | 2 | 11/17/2023 | 11/17/2023 | 39 | 17 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/14/2023 | 2/1/2025 | Y | EXP | 365 | 04/25/2024 | 05/15/2024 | 21 | 0 | 21 |  |  | 5/30/2024 | Connected |  | N
National Grid | BRIMFIELD | 176272 | 01010 | 3084 | Solar | 05_07_92W54 | 02/19/2015 | 02/19/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2015 | 03/30/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 | 02/19/2015 | 12/14/2017 | Y | STD | 794 | 05/24/2017 | 02/20/2018 | 179 | 0 | 179 | 11/20/2017 | 11/20/2017 | 12/14/2017 | Connected |  | N
National Grid | WEYMOUTH | 177955 | 02188 | 3300 | Solar | 05_09_604W4 | 10/23/2017 | 12/21/2017 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 | 01/02/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  | 10/31/2018 | N | STD | 92 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 558155 | 02375 | 7.6 | Solar | 05_05_344W4 | 10/18/2023 | 10/23/2023 | 4 | 1 | 3 | 10/24/2023 | 10/24/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 10/18/2023 | 12/21/2024 | Y | EXP | 365 | 02/06/2024 | 05/14/2024 | 99 | 0 | 99 |  |  | 5/31/2024 | Connected |  | N
National Grid | BARRE | 346961 | 01005 | 7.6 | Solar | 05_12_16W4 | 03/30/2021 | 03/31/2021 | 0 | 0 | 0 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  | 5/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2022 | Connected |  | N
National Grid | BELLINGHAM | 175241 | 02019 | 20 | Solar | 05_05_321W2 | 08/22/2014 | 08/22/2014 | 5 | 0 | 5 | 09/02/2014 | 09/02/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 11/28/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 4/24/2015 | Connected |  | N
National Grid | REVERE | 294957 | 02151 | 10 | Solar | 05_07_911W13 | 07/30/2020 | 08/03/2020 | 1 | 0 | 1 | 08/04/2020 | 08/04/2020 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 | 07/30/2020 | 8/2/2021 | Y | EXP | 365 | 11/04/2020 | 12/10/2020 | 36 | 0 | 36 |  |  | 12/29/2020 | Connected |  | N
National Grid | UXBRIDGE | 178066 | 01569 | 240 | Solar | 05_07_12W4 | 09/05/2017 | 09/05/2017 | 45 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/13/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2018 | 09/05/2017 | 4/15/2021 | Y | STD | 598 | 09/16/2020 | 03/24/2021 | 189 | 0 | 189 |  |  | 4/15/2021 | Connected |  | N
National Grid | BROCKTON | 174277 | 02301 | 25.6 | Solar | 05_01_207W4 | 12/14/2011 | 12/14/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 03/13/2012 | 03/14/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  | 03/14/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 3/14/2012 |  | 4/14/2012 | N | EXP | 31 |  |  | 0 | 0 | 0 | 4/2/2012 | 4/2/2012 | 4/24/2012 | Connected |  | N
National Grid | WEYMOUTH | 311431 | 02188 | 20 | Solar | 05_09_503L4 | 09/08/2020 | 09/10/2020 | 1 | 0 | 1 | 09/11/2020 | 09/11/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2021 | Connected |  | N
National Grid | LEOMINSTER | 603792 | 01453 | 5.76 | Solar | 05_07_9W2 | 04/13/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 04/13/2024 | 12/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | BRIMFIELD | 177631 | 01010 | 296 | Solar | 05_07_92W54 | 05/24/2017 | 05/24/2017 | 22 | 22 | 0 | 06/29/2017 | 06/29/2017 | 186 | 8 | 178 | 08/07/2017 | 08/29/2017 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  | 08/29/2017 | 16 | 1 | 15 |  |  | 0 | 0 | 0 | 9/20/2017 | 05/24/2017 | 8/30/2018 | Y | EXP | 344 | 02/21/2018 | 04/17/2018 | 27 | 0 | 27 |  |  | 8/16/2018 | Connected |  | N
National Grid | WEYMOUTH | 178496 | 02189 | 10 | Solar | 05_09_604W4 | 12/04/2017 | 02/12/2018 | 46 | 46 | 0 | 02/12/2018 | 02/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2018 |  | 12/10/2018 | N | EXP | 31 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 541092 | 02375 | 25 | Solar | 05_05_344W4 | 07/14/2023 | 08/03/2023 | 14 | 13 | 1 | 08/04/2023 | 08/04/2023 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 408870 | 01005 | 0 | Battery Add-On | 05_12_16W4 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 03/04/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 175390 | 02019 | 728 | Solar | 05_05_321W2 | 09/11/2014 | 09/11/2014 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/23/2014 | 10/20/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 | 09/11/2014 | 1/26/2016 | Y | STD | 39 |  |  | 0 | 0 | 0 | 7/19/2016 | 7/19/2016 | 6/17/2016 | Connected |  | N
National Grid | REVERE | 306595 | 02151 | 7.6 | Solar | 05_07_911W13 | 08/13/2020 | 08/14/2020 | 0 | 0 | 0 | 08/17/2020 | 08/17/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 |  | 8/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2020 | Connected |  | N
National Grid | UXBRIDGE | 178099 | 01569 | 492 | Solar | 05_07_12W4 | 09/05/2017 | 09/05/2017 | 45 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/13/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2018 | 09/05/2017 | 4/15/2021 | Y | STD | 598 | 09/16/2020 | 03/24/2021 | 189 | 0 | 189 |  |  | 4/13/2021 | Connected |  | N
National Grid | BROCKTON | 245424 | 02301 | 0 | Solar | 05_01_207W4 | 07/25/2019 | 07/30/2019 | 2 | 0 | 2 | 07/31/2019 | 07/31/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2019 | Connected |  | N
National Grid | WEYMOUTH | 506481 | 02190 | 16.896 | Solar | 05_09_503L4 | 03/07/2023 | 06/22/2023 | 73 | 72 | 1 | 06/23/2023 | 06/23/2023 | 111 | 68 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 644014 | 01453 | 5.76 | Solar | 05_07_9W2 | 10/01/2024 | 11/13/2024 | 14 | 11 | 3 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2025 | Connected |  | N
National Grid | BRIMFIELD | 178053 | 01010 | 1128 | Solar | 05_07_92W54 | 06/30/2017 | 06/30/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2017 | 10/26/2017 | 72 | 57 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2018 | 06/30/2017 | 2/12/2021 | Y | STD | 422 | 06/30/2020 | 11/13/2020 | 136 | 5 | 131 | 1/28/2021 | 1/27/2021 | 2/12/2021 | Connected |  | N
National Grid | WEYMOUTH | 189429 | 02189 | 3000 | Solar | 05_09_604W4 | 06/28/2018 | 06/28/2018 | 7 | 7 | 0 |  |  | 10 | 6 | 4 |  |  | 0 | 0 | 0 | 07/25/2018 | 09/13/2018 | 36 | 9 | 27 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 544470 | 02375 | 10 | Solar | 05_05_344W4 | 08/22/2023 | 08/23/2023 | 1 | 0 | 1 | 08/24/2023 | 08/24/2023 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 |  | 11/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | Y
National Grid | HUBBARDSTON | 534356 | 01452 | 3.8 | Solar | 05_12_16W4 | 06/26/2023 | 06/28/2023 | 2 | 0 | 2 | 06/29/2023 | 06/29/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 175463 | 02019 | 450 | Solar | 05_05_321W2 | 09/19/2014 | 09/19/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2014 | 10/20/2014 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 | 09/19/2014 | 12/31/2016 | Y | STD | 649 | 10/01/2015 | 06/23/2016 | 179 | 0 | 179 | 7/19/2016 | 7/19/2016 | 6/17/2016 | Connected |  | N
National Grid | REVERE | 332855 | 02151 | 7.6 | Solar | 05_07_911W13 | 01/27/2021 |  | 101 | 26 | 75 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 204176 | 01569 | 99.9 | Solar | 05_07_12W4 | 12/18/2018 | 01/09/2019 | 14 | 9 | 5 | 01/10/2019 | 01/10/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 377022 | 02301 | 250 | Solar | 05_01_207W4 | 01/21/2022 | 02/01/2022 | 7 | 1 | 6 |  |  | 30 | 7 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 531883 | 02190 | 15 | Solar | 05_09_503L4 | 06/07/2023 | 06/08/2023 | 1 | 0 | 1 | 06/09/2023 | 06/09/2023 | 30 | 10 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  | 8/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2023 | Connected |  | N
National Grid | LEOMINSTER | 648723 | 01453 | 7.83 | Solar | 05_07_9W2 | 11/06/2024 | 12/19/2024 | 16 | 12 | 4 | 12/20/2024 | 12/20/2024 | 120 | 98 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIMFIELD | 178573 | 01010 | 415 | Solar | 05_07_92W54 | 12/11/2017 | 12/11/2017 | 77 | 57 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/18/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 190867 | 02189 | 4998 | Solar | 05_09_604W4 | 11/14/2018 | 11/30/2018 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 01/25/2019 | 56 | 20 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 550304 | 02379 | 7.6 | Solar | 05_05_344W4 | 09/08/2023 |  | 145 | 52 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 535671 | 01452 | 5 | Solar | 05_12_16W4 | 01/02/2024 |  | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 175462 | 02019 | 950 | Solar | 05_05_321W2 | 09/19/2014 | 09/19/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2014 | 10/20/2014 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 | 09/19/2014 | 2/10/2016 | Y | STD | 324 | 10/01/2015 | 06/23/2016 | 179 | 0 | 179 | 7/19/2016 | 7/19/2016 | 6/17/2016 | Connected |  | N
National Grid | REVERE | 391841 | 02151 | 0 | Other | 05_07_911W13 | 11/11/2021 | 01/05/2022 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 01/26/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 244318 | 01569 | 10 | Solar | 05_07_12W4 | 07/23/2019 | 07/25/2019 | 2 | 2 | 0 | 07/26/2019 | 07/26/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2019 |  | 8/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 429394 | 02301 | 0 | Other | 05_01_207W4 | 09/16/2022 | 10/21/2022 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2022 | 11/09/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 573402 | 02188 | 9.765 | Solar | 05_09_503L4 | 12/27/2023 | 01/04/2024 | 6 | 5 | 1 | 01/05/2024 | 01/05/2024 | 112 | 92 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2024 | Connected |  | N
National Grid | LEOMINSTER | 657167 | 01453 | 7.6 | Solar | 05_07_9W2 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/26/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | BRIMFIELD | 185614 | 01010 | 294 | Solar | 05_07_92W54 | 05/17/2018 | 05/17/2018 | 49 | 35 | 14 | 07/30/2018 | 07/30/2018 | 49 | 25 | 24 | 10/09/2018 | 11/29/2018 | 35 | 17 | 18 |  |  | 0 | 0 | 0 |  | 11/29/2018 | 35 | 17 | 18 |  |  | 0 | 0 | 0 | 1/2/2019 | 05/17/2018 | 4/19/2021 | Y | EXP | 197 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 194815 | 02189 | 250 | Solar | 05_09_604W4 | 11/21/2018 | 12/19/2018 | 17 | 10 | 7 | 12/20/2018 | 12/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 552896 | 02375 | 7.6 | Solar | 05_05_344W4 | 09/01/2023 | 09/14/2023 | 1 | 0 | 1 | 09/15/2023 | 09/15/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | BARRE | 550822 | 01005 | 3.8 | Solar | 05_12_16W4 | 08/28/2023 | 09/01/2023 | 4 | 2 | 2 | 09/05/2023 | 09/05/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 175493 | 02019 | 1000 | Solar | 05_05_321W2 | 07/25/2014 | 07/25/2014 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2014 | 09/05/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2015 | 07/25/2014 | 6/30/2017 | Y | STD | 781 | 03/03/2016 | 03/13/2017 | 254 | 0 | 254 | 5/17/2017 | 5/17/2017 | 7/18/2017 | Connected |  | N
National Grid | REVERE | 443641 | 02151 | 5 | Solar | 05_07_911W13 | 09/07/2022 | 09/12/2022 | 3 | 0 | 3 | 09/13/2022 | 09/13/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2022 |  | 10/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2022 | Connected |  | N
National Grid | UXBRIDGE | 610973 | 01569 | 5.76 | Solar | 05_07_12W4 | 05/14/2024 | 05/21/2024 | 1 | 0 | 1 | 05/22/2024 | 05/22/2024 | 22 | 9 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 | 05/14/2024 | 7/1/2025 | Y | EXP | 365 | 08/06/2024 | 08/05/2024 | 0 | 0 | 0 |  |  | 8/9/2024 | Connected |  | N
National Grid | BROCKTON | 437417 | 02301 | 0 | Other | 05_01_207W4 | 09/26/2022 | 10/26/2022 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 | 11/17/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 670741 | 02188 | 5.76 | Solar | 05_09_503L4 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | LEOMINSTER | 670230 | 01453 | 7.25 | Solar | 05_07_9W2 | 02/05/2025 | 03/03/2025 | 4 | 1 | 3 | 03/04/2025 | 03/04/2025 | 46 | 29 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N
National Grid | PALMER | 185461 | 01069 | 422 | Solar | 05_07_92W54 | 05/17/2018 | 05/17/2018 | 49 | 30 | 19 | 07/30/2018 | 07/30/2018 | 60 | 25 | 35 | 11/06/2018 | 12/14/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 12/14/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 1/2/2019 | 05/17/2018 | 5/2/2021 | Y | EXP | 197 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 192362 | 02189 | 2400 | Solar | 05_09_604W4 | 10/01/2018 | 10/25/2018 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 | 11/27/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 565970 | 02379 | 10 | Solar | 05_05_344W4 | 11/01/2023 | 11/07/2023 | 5 | 2 | 3 | 11/08/2023 | 11/08/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 | 11/01/2023 | 1/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2024 | Connected |  | N
National Grid | HUBBARDSTON | 581875 | 01452 | 100 | Solar | 05_12_16W4 | 01/19/2024 | 02/08/2024 | 13 | 3 | 10 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 175502 | 02019 | 1000 | Solar | 05_05_321W2 | 09/29/2014 | 09/29/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2014 | 10/31/2014 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 | 09/29/2014 | 1/21/2016 | Y | STD | 34 | 06/09/2016 | 09/14/2016 | 66 | 0 | 66 | 12/22/2016 | 12/22/2016 | 12/22/2016 | Connected |  | N
National Grid | REVERE | 467668 | 02151 | 6 | Solar | 05_07_911W13 | 11/29/2022 | 12/06/2022 | 5 | 0 | 5 | 12/07/2022 | 12/07/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 |  | 8/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 626580 | 01569 | 10 | Solar | 05_07_12W4 | 07/22/2024 | 09/03/2024 | 4 | 0 | 4 | 09/04/2024 | 09/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 10/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | BROCKTON | 445310 | 02301 | 100 | Solar | 05_01_207W4 | 07/26/2022 | 08/29/2022 | 24 | 15 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 650830 | 02189 | 11.4 | Solar | 05_09_507L1 | 10/30/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/30/2024 | 3/17/2027 | Y | EXP | 45 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | LEOMINSTER | 559874 | 01453 | 225 | Solar | 05_09_1001W1 | 10/10/2023 | 11/30/2023 | 35 | 26 | 9 | 12/01/2023 | 12/01/2023 | 83 | 59 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 | 10/10/2023 | 4/5/2026 | Y | EXP | 133 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | PALMER | 186104 | 01069 | 500 | Solar | 05_07_92W54 | 08/29/2018 | 09/28/2018 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2018 | 10/26/2018 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2019 |  | 5/15/2020 | N | STD | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 202897 | 02189 | 20 | Solar | 05_09_604W4 | 02/18/2019 | 12/21/2018 | 0 | 0 | 0 | 02/21/2019 | 02/21/2019 | 19 | 11 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2019 |  | 2/24/2020 | N | EXP | 34 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 570649 | 02375 | 5.51 | Solar | 05_05_344W4 | 12/27/2023 | 01/05/2024 | 6 | 2 | 4 | 01/08/2024 | 01/08/2024 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 600326 | 01331 | 6 | Solar | 05_12_16W4 | 04/05/2024 |  | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 175583 | 02019 | 15.265 | Solar | 05_05_321W2 | 04/16/2014 | 04/16/2014 | 6 | 0 | 6 | 04/28/2014 | 04/28/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2014 |  | 8/29/2014 | N | EXP | 11 |  |  | 0 | 0 | 0 | 5/20/2014 | 5/20/2014 | 8/15/2014 | Connected |  | N
National Grid | REVERE | 468616 | 02151 | 4.35 | Solar | 05_07_911W13 | 03/07/2024 | 03/25/2024 | 13 | 10 | 3 | 03/26/2024 | 03/26/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 | 03/07/2024 | 4/10/2025 | Y | EXP | 365 | 06/05/2024 | 06/06/2024 | 2 | 0 | 2 |  |  | 6/26/2024 | Connected |  | N
National Grid | UXBRIDGE | 643964 | 01569 | 10 | Solar | 05_07_12W4 | 10/01/2024 | 10/09/2024 | 5 | 0 | 5 | 10/10/2024 | 10/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/01/2024 | 11/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 485045 | 02301 | 0 | Other | 05_01_207W4 | 02/27/2023 | 03/09/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2023 | 03/24/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 697152 | 02190 | 19 | Solar | 05_09_507L1 | 06/09/2025 | 06/11/2025 | 2 | 0 | 2 | 06/12/2025 | 06/12/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 594606 | 01453 | 50 | Solar | 05_09_1001W1 | 04/30/2024 | 05/16/2024 | 12 | 7 | 5 | 05/17/2024 | 05/17/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2024 |  | 3/3/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PALMER | 204400 | 01069 | 480 | Solar | 05_07_92W54 | 12/26/2018 | 01/17/2019 | 14 | 5 | 9 | 01/18/2019 | 01/18/2019 | 19 | 2 | 17 | 04/09/2019 | 04/29/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 04/29/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 5/9/2019 | 12/26/2018 | 2/19/2021 | Y | EXP | 398 | 12/22/2020 | 12/21/2020 | 0 | 0 | 0 |  |  | 2/17/2021 | Connected |  | N
National Grid | WEYMOUTH | 260756 | 02189 | 10 | Solar | 05_09_604W4 | 10/17/2019 | 10/25/2019 | 5 | 3 | 2 | 10/28/2019 | 10/28/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 |  | 10/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2020 | Connected |  | N
National Grid | EASTON | 573961 | 02375 | 10 | Solar | 05_05_344W4 | 12/06/2023 | 12/07/2023 | 1 | 0 | 1 | 12/08/2023 | 12/08/2023 | 57 | 36 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 612100 | 01005 | 7.6 | Solar | 05_12_16W4 | 05/21/2024 | 06/03/2024 | 2 | 0 | 2 | 06/04/2024 | 06/04/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | BELLINGHAM | 176528 | 02019 | 10 | Solar | 05_05_321W2 | 12/15/2015 | 12/15/2015 | 16 | 16 | 0 | 01/08/2016 | 01/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2016 |  | 12/20/2016 | N | EXP | 336 |  |  | 0 | 0 | 0 | 1/20/2016 | 1/20/2016 | 3/7/2016 | Connected |  | N
National Grid | REVERE | 507289 | 02151 | 12.76 | Solar | 05_07_911W13 | 03/08/2023 | 04/19/2023 | 29 | 27 | 2 | 04/20/2023 | 04/20/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2023 |  | 7/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N
National Grid | UXBRIDGE | 650035 | 01569 | 10 | Solar | 05_07_12W4 | 10/25/2024 | 12/13/2024 | 29 | 24 | 5 | 12/16/2024 | 12/16/2024 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | BROCKTON | 579807 | 02301 | 6.38 | Solar | 05_01_207W4 | 02/13/2024 | 03/27/2024 | 30 | 27 | 3 | 03/28/2024 | 03/28/2024 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 |  | 4/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2024 | Connected |  | N
National Grid | WEYMOUTH | 709861 | 02190 | 18.34 | Solar | 05_09_507L1 | 08/05/2025 | 08/28/2025 | 2 | 0 | 2 | 11/20/2025 | 11/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 611495 | 01453 | 100 | Solar | 05_09_1001W1 | 05/31/2024 | 06/18/2024 | 12 | 4 | 8 | 06/20/2024 | 06/20/2024 | 71 | 53 | 18 | 10/15/2024 | 07/23/2025 | 191 | 45 | 146 |  |  | 0 | 0 | 0 |  | 07/23/2025 | 191 | 45 | 146 |  |  | 0 | 0 | 0 | 11/12/2025 | 05/31/2024 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | PALMER | 346957 | 01069 | 499 | Solar | 05_07_92W54 | 07/14/2021 | 08/05/2021 | 16 | 9 | 7 |  |  | 73 | 37 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 07/14/2021 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 296858 | 02189 | 12.285 | Solar | 05_09_604W4 | 08/12/2020 | 08/18/2020 | 3 | 2 | 1 | 08/19/2020 | 08/19/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 | 08/12/2020 | 8/1/2021 | Y | EXP | 365 | 01/20/2021 | 02/11/2021 | 22 | 0 | 22 |  |  | 2/17/2021 | Connected |  | Y
National Grid | EASTON | 589418 | 02375 | 0 | Solar | 05_05_344W4 | 02/12/2024 | 03/11/2024 | 20 | 18 | 2 | 03/12/2024 | 03/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 613303 | 01005 | 34.6 | Solar | 05_12_16W4 | 06/05/2024 | 06/07/2024 | 2 | 0 | 2 | 06/10/2024 | 06/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  | 7/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | BELLINGHAM | 176607 | 02019 | 1000 | Solar | 05_05_321W2 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/12/2016 | 5 | 1 | 4 |  |  | 0 | 0 | 0 | 05/06/2016 | 07/19/2016 | 49 | 0 | 49 | 7/19/2016 | 12/29/2015 | 10/20/2017 | Y | STD | 458 | 07/20/2017 | 01/11/2018 | 114 | 0 | 114 | 12/20/2017 | 12/20/2017 | 12/22/2017 | Connected |  | N
National Grid | REVERE | 512252 | 02151 | 3.84 | Solar | 05_07_911W13 | 03/23/2023 | 03/28/2023 | 3 | 0 | 3 | 03/29/2023 | 03/29/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/23/2023 | 5/16/2024 | Y | EXP | 365 | 07/20/2023 | 07/20/2023 | 1 | 0 | 1 |  |  | 8/3/2023 | Connected |  | N
National Grid | UXBRIDGE | 660139 | 01569 | 10.44 | Solar | 05_07_12W4 | 12/13/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/13/2024 | 2/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | BROCKTON | 587583 | 02301 | 7.25 | Solar | 05_01_207W4 | 02/13/2024 | 03/06/2024 | 15 | 12 | 3 | 03/07/2024 | 03/07/2024 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 | 02/13/2024 | 4/4/2025 | Y | EXP | 365 | 06/28/2024 | 08/07/2024 | 41 | 0 | 41 |  |  | 8/16/2024 | Connected |  | N
National Grid | WEYMOUTH | 717426 | 02190 | 4950 | Solar | 05_09_507L1 | 12/16/2025 | 01/21/2026 | 22 | 13 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2026 | 02/12/2026 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LEOMINSTER | 673600 | 01453 | 957 | Other | 05_09_1001W1 | 07/14/2025 | 08/26/2025 | 30 | 20 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2025 | 09/19/2025 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WILBRAHAM | 351232 | 01095 | 8.7 | Solar | 05_07_92W54 | 04/07/2021 | 04/22/2021 | 9 | 7 | 2 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 4/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2021 | Connected |  | N
National Grid | WILLIAMSTOWN | 297555 | 01267 | 84 | Solar | 05_09_604W4 | 06/22/2020 | 06/26/2020 | 4 | 4 | 0 | 06/29/2020 | 06/29/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 626766 | 02375 | 10 | Solar | 05_05_344W4 | 07/22/2024 | 07/23/2024 | 24 | 17 | 7 | 12/09/2024 | 12/09/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | BARRE | 643354 | 01005 | 10 | Solar | 05_12_16W4 | 09/27/2024 | 01/03/2025 | 3 | 0 | 3 | 01/06/2025 | 01/06/2025 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 176636 | 02019 | 2000 | Solar | 05_05_321W2 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/12/2016 | 5 | 1 | 4 |  |  | 0 | 0 | 0 | 05/06/2016 | 07/19/2016 | 49 | 0 | 49 | 7/19/2016 | 12/29/2015 | 10/20/2017 | Y | STD | 458 | 07/20/2017 | 01/11/2018 | 114 | 0 | 114 | 12/20/2017 | 12/20/2017 | 12/22/2017 | Connected |  | N
National Grid | REVERE | 521575 | 02151 | 2.61 | Solar | 05_07_911W13 | 08/14/2023 | 08/17/2023 | 3 | 0 | 3 | 08/18/2023 | 08/18/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 7/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2024 | Connected |  | N
National Grid | UXBRIDGE | 675883 | 01569 | 7.6 | Solar | 05_07_12W4 | 03/05/2025 | 05/14/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 7/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | BROCKTON | 590751 | 02301 | 10 | Solar | 05_01_207W4 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 | 02/22/2024 | 3/23/2025 | Y | EXP | 365 | 05/18/2024 | 05/30/2024 | 13 | 0 | 13 |  |  | 6/21/2024 | Connected |  | N
National Grid | WEYMOUTH | 725101 | 02190 | 14.44 | Solar | 05_09_507L1 | 10/09/2025 | 10/21/2025 | 8 | 6 | 2 | 10/22/2025 | 10/22/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LEOMINSTER | 730458 | 01453 |  | Solar | 05_09_1001W1 | 11/06/2025 |  | 78 | 65 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WILBRAHAM | 394878 | 01095 | 9.28 | Solar | 05_07_92W54 | 11/19/2021 | 12/21/2021 | 22 | 19 | 3 | 12/22/2021 | 12/22/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  | 2/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2022 | Connected |  | N
National Grid | NORTH ADAMS | 297418 | 01247 | 150 | Solar | 05_09_604W4 | 06/19/2020 | 06/26/2020 | 5 | 5 | 0 | 06/29/2020 | 06/29/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 643781 | 02379 | 10 | Solar | 05_12_16W4 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/01/2024 | 1/6/2026 | Y | EXP | 365 | 07/30/2025 | 10/29/2025 | 92 | 0 | 92 |  |  | 12/3/2025 | Connected |  | N
National Grid | BARRE | 178259 | 01005 | 4990 | Solar | 05_05_321W2 | 04/17/2018 | 04/17/2018 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2018 | 06/21/2018 | 22 | 21 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/22/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 524386 | 02019 | 6 | Solar | 05_07_911W13 | 05/12/2023 |  | 107 | 91 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 683797 | 02151 | 4998 | Other | 05_07_15J1 | 10/16/2025 | 12/04/2025 | 31 | 23 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2025 | 12/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MILLVILLE | 598939 | 01529 | 5 | Solar | 05_01_207W4 | 03/28/2024 | 04/01/2024 | 2 | 0 | 2 | 04/02/2024 | 04/02/2024 | 82 | 80 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 741880 | 02301 | 11.4 | Solar | 05_09_507L1 | 12/22/2025 | 12/29/2025 | 3 | 0 | 3 | 01/21/2026 | 01/21/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEYMOUTH | 744509 | 02190 | 11.5 | Solar | 05_09_1001W1 | 01/10/2026 | 01/14/2026 | 3 | 0 | 3 | 01/15/2026 | 01/15/2026 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 471914 | 01453 | 10 | Solar | 05_07_92W54 | 11/21/2022 | 12/01/2022 | 8 | 6 | 2 | 12/02/2022 | 12/02/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 | 11/21/2022 | 4/18/2024 | Y | EXP | 365 | 03/29/2023 | 03/28/2023 | 0 | 0 | 0 |  |  | 8/19/2023 | Connected |  | Y
National Grid | WILBRAHAM | 303281 | 01095 | 15.2 | Solar | 05_09_604W4 | 04/12/2021 | 04/19/2021 | 4 | 0 | 4 | 04/20/2021 | 04/20/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2021 | 04/12/2021 | 8/15/2022 | Y | EXP | 365 | 10/21/2022 | 01/06/2023 | 78 | 0 | 78 |  |  | 1/19/2024 | Connected |  | Y
National Grid | NORTH ADAMS | 638849 | 01247 | 6 | Solar | 05_05_344W4 | 09/09/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 | 09/09/2024 | 10/31/2025 | Y | EXP | 365 | 12/19/2024 | 12/31/2024 | 13 | 0 | 13 |  |  | 1/15/2025 | Connected |  | N
National Grid | EASTON | 673809 | 02356 | 5.76 | Solar | 05_12_16W4 | 02/24/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 558668 | 01452 | 2.61 | Solar | 05_07_911W13 | 10/04/2023 | 10/12/2023 | 6 | 3 | 3 | 10/13/2023 | 10/13/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 2/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2024 | Connected |  | N
National Grid | BELLINGHAM | 717385 | 02019 | 7.6 | Solar | 05_07_15J1 | 09/18/2025 | 09/25/2025 | 2 | 0 | 2 | 10/23/2025 | 10/23/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 09/18/2025 | 12/5/2026 | Y | EXP | 365 | 01/21/2026 | 02/20/2026 | 31 | 0 | 31 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 651575 | 02151 | 5.76 | Solar | 05_01_207W4 | 11/04/2024 | 11/26/2024 | 10 | 0 | 10 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 174389 | 01569 | 17.2 | Solar | 05_09_507L1 | 06/06/2012 | 06/06/2012 | 6 | 0 | 6 | 06/18/2012 | 06/18/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 8/31/2012 | N | EXP | 13 |  |  | 0 | 0 | 0 | 9/7/2012 | 9/7/2012 | 1/4/2013 | Connected |  | N
National Grid | BROCKTON | 748671 | 02301 | 0 | Solar | 05_09_1001W1 | 02/03/2026 | 02/09/2026 | 3 | 0 | 3 | 02/10/2026 | 02/10/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2026 |  | 3/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEYMOUTH | 485460 | 02190 | 0 | Solar | 05_07_92W54 | 12/14/2022 |  | 112 | 71 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 307522 | 01453 | 25 | Solar | 05_09_604W4 | 08/19/2020 | 08/31/2020 | 8 | 0 | 8 | 09/01/2020 | 09/01/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/19/2020 | 11/29/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 640557 | 01095 | 10 | Solar | 05_05_344W4 | 09/16/2024 | 09/25/2024 | 1 | 0 | 1 | 09/26/2024 | 09/26/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 | 09/16/2024 | 10/31/2025 | Y | EXP | 365 | 11/27/2024 | 01/07/2025 | 42 | 0 | 42 |  |  | 3/26/2025 | Connected |  | N
National Grid | NORTH ADAMS | 677613 | 01247 | 250 | Solar | 05_12_16W5 | 06/13/2025 | 07/07/2025 | 14 | 5 | 9 | 07/08/2025 | 07/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 6/28/2026 | N | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | EASTON | 178350 | 02375 | 24.94 | Solar | 05_05_321W2 | 01/12/2018 | 01/12/2018 | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2018 |  | 1/17/2019 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 7/18/2018 | Connected |  | N
National Grid | HUBBARDSTON | 558405 | 01452 | 3.8 | Solar | 05_07_911W13 | 09/29/2023 | 10/03/2023 | 3 | 1 | 2 | 10/04/2023 | 10/04/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2023 |  | 1/12/2025 | N | EXP | 42 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 353056 | 02019 | 0 | Solar | 05_07_15J1 | 04/16/2021 | 04/22/2021 | 2 | 0 | 2 | 04/23/2021 | 04/23/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 5/16/2023 | N | EXP | 6 |  |  | 0 | 0 | 0 |  |  | 4/5/2023 | Connected |  | N
National Grid | REVERE | 653516 | 02151 | 10.075 | Solar | 05_01_207W4 | 11/20/2024 | 03/04/2025 | 13 | 9 | 4 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 | 11/20/2024 | 4/14/2026 | Y | EXP | 365 | 09/20/2025 | 09/23/2025 | 4 | 0 | 4 |  |  | 10/8/2025 | Connected |  | N
National Grid | UXBRIDGE | 174386 | 01569 | 14 | Solar | 05_09_507L1 | 06/01/2012 | 06/01/2012 | 28 | 0 | 28 | 07/17/2012 | 07/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 9/28/2012 | N | EXP | 75 |  |  | 0 | 0 | 0 | 9/14/2012 | 9/14/2012 | 2/22/2013 | Connected |  | N
National Grid | BROCKTON | 748339 | 02301 | 3.8 | Solar | 05_09_1001W1 | 01/30/2026 | 02/04/2026 | 1 | 0 | 1 | 02/10/2026 | 02/10/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEYMOUTH | 487262 | 02190 | 15.2 | Solar | 05_07_92W54 | 12/28/2022 | 01/04/2023 | 5 | 1 | 4 | 01/05/2023 | 01/05/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2023 |  | 2/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2023 | Connected |  | N
National Grid | LEOMINSTER | 307520 | 01453 | 25 | Solar | 05_09_604W4 | 08/19/2020 | 08/31/2020 | 7 | 0 | 7 | 09/01/2020 | 09/01/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2020 | 08/19/2020 | 4/9/2023 | Y | EXP | 565 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 645363 | 01095 | 10 | Solar | 05_05_344W4 | 10/07/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/07/2024 | 3/11/2026 | Y | EXP | 365 | 07/02/2025 | 07/25/2025 | 24 | 0 | 24 |  |  | 8/13/2025 | Connected |  | N
National Grid | NORTH ADAMS | 692294 | 01247 | 3.839 | Solar | 05_12_16W5 | 05/16/2025 | 06/05/2025 | 1 | 0 | 1 | 06/10/2025 | 06/10/2025 | 97 | 85 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 | 05/16/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | EASTON | 178349 | 02356 | 49.88 | Solar | 05_05_321W2 | 01/12/2018 | 01/12/2018 | 14 | 4 | 10 | 02/02/2018 | 02/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2018 |  | 1/17/2019 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 7/18/2018 | Connected |  | N
National Grid | HUBBARDSTON | 558206 | 01452 | 6 | Solar | 05_07_911W13 | 10/09/2023 | 10/12/2023 | 3 | 0 | 3 | 10/13/2023 | 10/13/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 10/09/2023 | 12/1/2025 | Y | EXP | 73 | 03/14/2024 | 03/21/2024 | 8 | 0 | 8 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 384763 | 02019 | 15.2 | Solar | 05_07_15J1 | 09/27/2021 |  | 58 | 49 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 684320 | 02151 | 7.6 | Solar | 05_01_207W4 | 04/10/2025 | 05/13/2025 | 2 | 0 | 2 | 06/02/2025 | 06/02/2025 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2025 |  | 9/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | BLACKSTONE | 176364 | 01504 | 10 | Solar | 05_09_507L1 | 03/08/2016 | 03/08/2016 | 3 | 3 | 0 | 03/15/2016 | 03/15/2016 | 230 | 0 | 230 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2016 |  | 3/15/2017 | N | EXP | 35 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 174233 | 02301 | 1000 | Solar | 05_09_1001W1 | 02/01/2012 | 02/01/2012 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2012 | 05/10/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 494331 | 02066 | 25 | Solar | 05_07_92W54 | 01/23/2023 | 01/24/2023 | 1 | 0 | 1 | 01/25/2023 | 01/25/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2023 | Connected |  | N
National Grid | LEOMINSTER | 319066 | 01453 | 4999 | Solar | 05_09_604W4 | 11/20/2020 | 12/30/2020 | 26 | 20 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2021 | 02/10/2021 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 656039 | 01095 | 10 | Solar | 05_05_344W4 | 11/21/2024 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | NORTH ADAMS | 730134 | 01247 | 10 | Solar | 05_12_16W5 | 11/03/2025 | 11/04/2025 | 4 | 0 | 4 | 12/10/2025 | 12/10/2025 | 25 | 13 | 12 | 02/13/2026 | 03/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 03/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | EASTON | 178541 | 02375 | 6 | Solar | 05_05_321W2 | 01/29/2018 | 01/29/2018 | 6 | 0 | 6 | 02/06/2018 | 02/06/2018 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2018 |  | 2/3/2019 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 529271 | 01452 | 7.6 | Solar | 05_07_911W13 | 05/30/2023 | 06/01/2023 | 2 | 0 | 2 | 06/02/2023 | 06/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 | 05/30/2023 | 11/5/2024 | Y | EXP | 365 | 10/11/2023 | 11/02/2023 | 23 | 0 | 23 |  |  | 2/2/2024 | Connected |  | N
National Grid | BELLINGHAM | 411314 | 02019 | 15.2 | Solar | 05_07_15J1 | 02/09/2022 | 02/10/2022 | 1 | 0 | 1 | 02/11/2022 | 02/11/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2022 |  | 3/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2022 | Connected |  | N
National Grid | REVERE | 645834 | 02151 | 4950 | Other | 05_01_207W6 | 01/29/2025 | 04/23/2025 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/24/2025 | 05/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BLACKSTONE | 177107 | 01504 | 1600 | Solar | 05_09_507L1 | 08/04/2016 | 08/04/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2016 | 09/14/2016 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/10/2019 | N | STD | 66 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174511 | 02301 | 177 | Solar | 05_09_1001W1 | 08/22/2011 | 08/22/2011 | 26 | 0 | 26 | 09/28/2011 | 09/28/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2011 |  | 10/31/2012 | N | EXP | 345 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 4/23/2013 | Connected |  | N
National Grid | SCITUATE | 525072 | 02066 | 10 | Solar | 05_07_92W54 | 05/09/2023 | 05/11/2023 | 2 | 0 | 2 | 05/12/2023 | 05/12/2023 | 49 | 27 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 11/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2023 | Connected |  | N
National Grid | LEOMINSTER | 319065 | 01453 | 4999 | Solar | 05_09_604W4 | 11/19/2020 | 12/17/2020 | 18 | 12 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2020 | 01/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 671532 | 01095 | 19 | Solar | 05_05_344W4 | 02/13/2025 | 02/24/2025 | 2 | 0 | 2 | 05/28/2025 | 05/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2025 | Connected |  | N
National Grid | WILLIAMSTOWN | 176347 | 01267 | 140 | Solar | 05_12_16W5 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 | 03/09/2015 | 03/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 |  | 9/30/2015 | N | EXP | 191 |  |  | 0 | 0 | 0 | 3/25/2015 | 3/25/2015 | 11/18/2015 | Connected |  | N
National Grid | EASTON | 184500 | 02375 | 1666 | Solar | 05_05_321W2 | 05/04/2018 | 05/04/2018 | 18 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/01/2018 | 06/28/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 550946 | 01452 | 3.8 | Solar | 05_07_911W13 | 09/06/2023 | 09/08/2023 | 2 | 1 | 1 | 09/11/2023 | 09/11/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 637597 | 02019 | 8.74 | Solar | 05_07_15J1 | 09/09/2024 | 09/25/2024 | 1 | 0 | 1 | 09/26/2024 | 09/26/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 698849 | 02148 | 14.82 | Solar | 05_01_207W6 | 07/01/2025 | 08/20/2025 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | UXBRIDGE | 177201 | 01569 | 7.6 | Solar | 05_09_507L1 | 02/01/2017 | 02/01/2017 | 1 | 0 | 1 | 02/03/2017 | 02/03/2017 | 200 | 0 | 200 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2017 |  | 2/7/2018 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174510 | 02301 | 225 | Solar | 05_09_1001W1 | 08/22/2011 | 08/22/2011 | 21 | 0 | 21 | 09/28/2011 | 09/28/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2011 |  | 10/31/2012 | N | EXP | 345 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 4/23/2013 | Connected |  | N
National Grid | SCITUATE | 590129 | 02066 | 10 | Solar | 05_07_92W54 | 02/15/2024 | 02/20/2024 | 2 | 0 | 2 | 02/21/2024 | 02/21/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/15/2024 | 3/8/2025 | Y | EXP | 365 | 07/17/2024 | 09/04/2024 | 50 | 0 | 50 |  |  | 9/11/2024 | Connected |  | N
National Grid | LEOMINSTER | 400502 | 01453 | 10 | Solar | 05_09_604W4 | 12/10/2021 | 12/14/2021 | 2 | 0 | 2 | 12/15/2021 | 12/15/2021 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2022 |  | 2/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2022 | Connected |  | N
National Grid | WILBRAHAM | 672886 | 01095 | 10 | Solar | 05_05_344W4 | 02/19/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 22 | 0 | 22 | 04/24/2025 | 04/23/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 04/23/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 5/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | WILLIAMSTOWN | 176784 | 01267 | 432 | Solar | 05_12_16W5 | 01/13/2016 | 01/13/2016 | 9 | 9 | 0 | 01/27/2016 | 01/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2016 |  | 7/1/2017 | N | EXP | 249 |  |  | 0 | 0 | 0 | 1/12/2017 | 1/12/2017 | 6/30/2017 | Connected |  | N
National Grid | EASTON | 184499 | 02375 | 1666 | Solar | 05_05_321W2 | 04/30/2018 | 04/30/2018 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2018 | 06/27/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 550688 | 01452 | 5 | Solar | 05_07_911W13 | 09/11/2023 | 09/18/2023 | 5 | 0 | 5 | 09/19/2023 | 09/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 640601 | 02019 | 23 | Battery Add-On | 05_07_15J1 | 09/16/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 54 | 40 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 09/16/2024 | 1/13/2026 | Y | EXP | 365 | 03/21/2025 | 03/27/2025 | 7 | 0 | 7 |  |  | 5/14/2025 | Connected |  | N
National Grid | EVERETT | 175882 | 02149 | 984 | Solar | 05_01_207W6 | 05/21/2015 | 05/21/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/27/2015 | 06/25/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2016 | 05/21/2015 | 10/31/2017 | Y | STD | 487 | 09/14/2017 | 01/05/2018 | 71 | 0 | 71 | 12/28/2017 | 12/28/2017 | 1/4/2018 | Connected |  | N
National Grid | UXBRIDGE | 177240 | 01569 | 4000 | Solar | 05_09_507L1 | 02/03/2017 | 02/03/2017 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2017 | 02/22/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 | 02/03/2017 | 12/31/2020 | Y | STD | 946 | 08/24/2019 | 10/27/2020 | 431 | 11 | 420 | 11/13/2020 | 12/3/2020 | 12/23/2020 | Connected |  | N
National Grid | BROCKTON | 174589 | 02301 | 60 | Solar | 05_09_1001W1 | 08/22/2011 | 08/22/2011 | 26 | 0 | 26 | 09/28/2011 | 09/28/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2011 |  | 8/4/2012 | N | EXP | 257 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 4/26/2013 | Connected |  | N
National Grid | SCITUATE | 606070 | 02066 | 10 | Solar | 05_07_92W54 | 04/23/2024 | 05/07/2024 | 8 | 6 | 2 | 05/08/2024 | 05/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 | 04/23/2024 | 9/28/2025 | Y | EXP | 365 | 08/01/2024 | 09/11/2024 | 42 | 0 | 42 |  |  | 1/29/2025 | Connected |  | N
National Grid | LEOMINSTER | 439587 | 01453 | 15.2 | Solar | 05_09_604W4 | 06/23/2022 | 07/06/2022 | 9 | 5 | 4 | 07/07/2022 | 07/07/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 | 06/23/2022 | 9/19/2023 | Y | EXP | 365 | 09/07/2022 | 09/19/2022 | 13 | 0 | 13 |  |  | 12/13/2022 | Connected |  | N
National Grid | MONSON | 685846 | 01057 | 23 | Solar | 05_05_344W4 | 06/18/2025 |  | 24 | 21 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 323866 | 01247 | 6 | Solar | 05_12_16W5 | 11/23/2020 | 11/25/2020 | 1 | 0 | 1 | 11/27/2020 | 11/27/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 | 11/23/2020 | 6/16/2022 | Y | EXP | 365 | 10/15/2021 | 12/07/2021 | 54 | 4 | 50 |  |  | 12/13/2021 | Connected |  | Y
National Grid | EASTON | 184491 | 02375 | 1800 | Solar | 05_05_321W2 | 04/28/2018 | 04/28/2018 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2018 | 06/27/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 554323 | 01005 | 3.8 | Solar | 05_07_911W13 | 09/12/2023 | 10/23/2023 | 28 | 25 | 3 | 10/24/2023 | 10/24/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 |  | 11/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 657499 | 02019 | 0 | Battery Add-On | 05_07_15J1 | 11/27/2024 | 12/12/2024 | 9 | 7 | 2 | 12/13/2024 | 12/13/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | EVERETT | 176471 | 02149 | 7.6 | Solar | 05_01_207W6 | 03/20/2016 | 03/20/2016 | 3 | 3 | 0 | 03/24/2016 | 03/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/20/2016 | 3/26/2017 | Y | EXP | 348 | 11/08/2016 | 11/29/2016 | 13 | 0 | 13 | 1/19/2017 | 1/19/2017 | 1/19/2017 | Connected |  | N
National Grid | UXBRIDGE | 177656 | 01569 | 15.2 | Solar | 05_09_507L1 | 11/10/2017 | 11/10/2017 | 15 | 0 | 15 | 12/05/2017 | 12/05/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2017 |  | 11/15/2018 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 12/21/2018 | Connected |  | N
National Grid | BROCKTON | 174752 | 02301 | 19.99 | Solar | 05_09_1001W1 | 01/22/2014 | 01/22/2014 | 7 | 0 | 7 | 02/03/2014 | 02/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2014 |  | 8/15/2014 | N | EXP | 123 |  |  | 0 | 0 | 0 | 4/15/2014 | 4/15/2014 | 8/1/2014 | Connected |  | N
National Grid | SCITUATE | 606788 | 02066 | 0 | Battery Add-On | 05_07_92W54 | 04/25/2024 | 04/30/2024 | 3 | 0 | 3 | 05/01/2024 | 05/01/2024 | 37 | 23 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2024 |  | 7/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | LEOMINSTER | 516473 | 01453 | 10 | Solar | 05_09_604W4 | 04/06/2023 | 04/24/2023 | 203 | 133 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 687956 | 01095 | 22.8 | Solar | 05_05_344W4 | 05/01/2025 | 06/17/2025 | 26 | 24 | 2 | 06/18/2025 | 06/18/2025 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 | 05/01/2025 | 7/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | NORTH ADAMS | 326220 | 01247 | 7.6 | Solar | 05_12_16W5 | 11/25/2020 | 12/01/2020 | 2 | 0 | 2 | 12/02/2020 | 12/02/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 11/25/2020 | 9/13/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2021 | Connected |  | N
National Grid | EASTON | 252243 | 02375 | 0 | Solar | 05_05_321W2 | 09/05/2019 | 09/17/2019 | 8 | 8 | 0 | 09/18/2019 | 09/18/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 9/4/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2020 | Connected |  | N
National Grid | BARRE | 554975 | 01005 | 6 | Solar | 05_07_911W13 | 09/29/2023 | 10/03/2023 | 2 | 0 | 2 | 10/04/2023 | 10/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 |  | 11/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2024 | Connected |  | N
National Grid | BELLINGHAM | 302775 | 02019 | 7.6 | Solar | 05_07_17J1 | 07/23/2020 | 08/14/2020 | 15 | 15 | 0 | 08/17/2020 | 08/17/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 |  | 8/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2021 | Connected |  | N
National Grid | MALDEN | 176557 | 02148 | 6 | Solar | 05_01_207W6 | 10/07/2015 | 10/07/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 |  | 10/13/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 3/31/2016 | 3/31/2016 | 4/6/2016 | Connected |  | N
National Grid | UXBRIDGE | 177879 | 01569 | 7.6 | Solar | 05_09_507L1 | 10/18/2017 | 10/18/2017 | 10 | 10 | 0 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 |  | 10/24/2018 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 8/24/2018 | Connected |  | N
National Grid | BROCKTON | 175089 | 02301 | 1000 | Solar | 05_09_1001W1 | 08/10/2011 | 08/10/2011 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2011 | 12/19/2011 | 78 | 0 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2014 |  | 12/31/2016 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 618835 | 02066 | 7.6 | Solar | 05_07_92W54 | 06/18/2024 | 07/03/2024 | 1 | 0 | 1 | 07/05/2024 | 07/05/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2024 | Connected |  | N
National Grid | LEOMINSTER | 532813 | 01453 | 10 | Solar | 05_09_604W4 | 06/09/2023 | 06/13/2023 | 2 | 1 | 1 | 06/14/2023 | 06/14/2023 | 52 | 33 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 689421 | 01095 | 14.82 | Solar | 05_05_344W4 | 05/02/2025 | 05/16/2025 | 3 | 0 | 3 | 05/27/2025 | 05/27/2025 | 44 | 32 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | NORTH ADAMS | 419637 | 01247 | 85 | Solar | 05_12_16W5 | 04/13/2022 | 07/26/2022 | 70 | 62 | 8 | 07/27/2022 | 07/27/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 | 04/13/2022 | 1/18/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2023 | Connected |  | N
National Grid | EASTON | 266700 | 02356 | 0 | Other | 05_05_321W2 | 09/15/2020 | 10/01/2020 | 12 | 7 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2020 | 10/27/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 | 09/15/2020 | 7/12/2027 | Y | STD | 553 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 566755 | 01452 | 7.6 | Solar | 05_07_911W13 | 11/10/2023 | 11/20/2023 | 7 | 4 | 3 | 11/21/2023 | 11/21/2023 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 662497 | 02019 | 7.8 | Solar | 05_07_17J1 | 12/24/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | MALDEN | 176657 | 02148 | 3.8 | Solar | 05_01_207W6 | 04/19/2016 | 04/19/2016 | 13 | 13 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2016 |  | 4/26/2017 | N | EXP | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 178451 | 01569 | 15.2 | Solar | 05_09_507L1 | 11/29/2017 | 11/29/2017 | 32 | 32 | 0 | 01/23/2018 | 01/23/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2018 |  | 7/15/2020 | N | EXP | 314 |  |  | 0 | 0 | 0 |  |  | 6/5/2020 | Connected |  | N
National Grid | BROCKTON | 175370 | 02301 | 41.92 | Solar | 05_09_1001W1 | 02/14/2014 | 02/14/2014 | 9 | 4 | 5 | 03/03/2014 | 03/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2014 |  | 9/30/2014 | N | EXP | 22 |  |  | 0 | 0 | 0 | 8/1/2014 | 8/1/2014 | 9/19/2014 | Connected |  | N
National Grid | SCITUATE | 626173 | 02066 | 1772 | Solar | 05_07_92W54 | 12/20/2024 | 02/18/2025 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/19/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 596912 | 01453 | 7.6 | Solar | 05_09_604W4 | 03/22/2024 | 03/27/2024 | 3 | 0 | 3 | 03/28/2024 | 03/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/22/2024 | 4/9/2025 | Y | EXP | 365 | 04/26/2024 | 05/01/2024 | 6 | 0 | 6 |  |  | 1/9/2025 | Connected |  | N
National Grid | WILBRAHAM | 693098 | 01095 | 17.86 | Solar | 05_05_344W4 | 05/23/2025 | 05/29/2025 | 3 | 0 | 3 | 05/30/2025 | 05/30/2025 | 28 | 12 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | NORTH ADAMS | 642291 | 01247 | 11.4 | Solar | 05_12_16W5 | 09/25/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 285198 | 02375 | 10 | Solar | 05_05_321W2 | 03/25/2020 | 03/30/2020 | 2 | 2 | 0 | 03/31/2020 | 03/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2020 |  | 3/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N
National Grid | BARRE | 563286 | 01005 | 7.6 | Solar | 05_07_911W13 | 11/07/2023 | 11/09/2023 | 2 | 0 | 2 | 11/13/2023 | 11/13/2023 | 31 | 8 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 | 11/07/2023 | 1/29/2025 | Y | EXP | 365 | 04/23/2024 | 05/09/2024 | 17 | 0 | 17 |  |  | 5/30/2024 | Connected |  | N
National Grid | BELLINGHAM | 176459 | 02019 | 10 | Solar | 05_07_18J1 | 02/04/2016 | 02/04/2016 | 0 | 0 | 0 | 02/05/2016 | 02/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2016 |  | 2/10/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 5/13/2016 | 5/13/2016 | 5/16/2016 | Connected |  | N
National Grid | MALDEN | 176656 | 02148 | 10 | Solar | 05_01_207W6 | 04/20/2016 | 04/20/2016 | 1 | 1 | 0 | 04/21/2016 | 04/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 | 04/20/2016 | 4/25/2017 | Y | EXP | 357 | 08/30/2016 | 09/09/2016 | 7 | 0 | 7 | 12/2/2016 | 12/2/2016 | 12/2/2016 | Connected |  | N
National Grid | UXBRIDGE | 185238 | 01569 | 5000 | Solar | 05_09_507L1 | 05/22/2018 | 05/22/2018 | 272 | 0 | 272 |  |  | 257 | 0 | 257 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 178205 | 02301 | 2.76 | Solar | 05_09_1001W1 | 02/19/2018 | 02/19/2018 | 8 | 8 | 0 | 03/08/2018 | 03/08/2018 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2018 |  | 2/25/2019 | N | EXP | 35 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 632417 | 02066 | 10 | Solar | 05_07_92W54 | 08/13/2024 | 08/15/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 | 08/13/2024 | 1/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2025 | Connected |  | Y
National Grid | LEOMINSTER | 608016 | 01453 | 10 | Solar | 05_09_604W4 | 05/03/2024 | 05/09/2024 | 4 | 3 | 1 | 05/10/2024 | 05/10/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 05/03/2024 | 6/28/2025 | Y | EXP | 365 | 09/05/2024 | 09/28/2024 | 24 | 0 | 24 |  |  | 10/16/2024 | Connected |  | N
National Grid | WILBRAHAM | 696573 | 01095 | 5.7 | Solar | 05_05_344W4 | 06/05/2025 | 06/11/2025 | 4 | 0 | 4 | 06/12/2025 | 06/12/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSTOWN | 655553 | 01267 | 3.8 | Solar | 05_12_16W5 | 11/20/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 340617 | 02375 | 10 | Solar | 05_05_321W2 | 02/04/2021 | 03/26/2021 | 35 | 34 | 1 | 03/29/2021 | 03/29/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  | 3/25/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 571870 | 01452 | 6 | Solar | 05_07_911W13 | 11/29/2023 | 12/05/2023 | 4 | 3 | 1 | 12/06/2023 | 12/06/2023 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 |  | 4/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2024 | Connected |  | N
National Grid | BELLINGHAM | 177907 | 02019 | 43.2 | Solar | 05_07_18J1 | 08/16/2017 | 08/16/2017 | 13 | 13 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 8/21/2018 | N | EXP | 347 |  |  | 0 | 0 | 0 | 10/27/2017 | 10/27/2017 | 11/13/2017 | Connected |  | N
National Grid | MALDEN | 176795 | 02148 | 10 | Solar | 05_01_207W6 | 02/25/2016 | 02/25/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2016 | 02/25/2016 | 3/1/2017 | Y | EXP | 328 | 07/18/2016 | 08/01/2016 | 10 | 0 | 10 | 4/7/2016 | 4/7/2016 | 8/3/2016 | Connected |  | N
National Grid | UXBRIDGE | 197167 | 01569 | 15.2 | Solar | 05_09_507L1 | 09/28/2018 | 10/02/2018 | 2 | 2 | 0 | 10/03/2018 | 10/03/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2018 | 09/28/2018 | 9/20/2019 | Y | EXP | 352 | 01/15/2019 | 02/04/2019 | 20 | 0 | 20 |  |  | 9/3/2019 | Connected |  | N
National Grid | BROCKTON | 178596 | 02301 | 4999 | Solar | 05_09_1001W1 | 04/03/2018 | 04/03/2018 | 10 | 10 | 0 |  |  | 79 | 65 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 642648 | 02066 | 3.8 | Solar | 05_07_92W54 | 09/24/2024 | 10/29/2024 | 6 | 4 | 2 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 654668 | 01453 | 9.56 | Solar | 05_09_604W4 | 11/15/2024 | 12/09/2024 | 4 | 2 | 2 | 12/10/2024 | 12/10/2024 | 97 | 72 | 25 | 05/12/2025 | 05/09/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 05/09/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | WILBRAHAM | 706186 | 01095 | 20 | Solar | 05_05_344W4 | 07/21/2025 | 07/25/2025 | 4 | 0 | 4 | 07/28/2025 | 07/28/2025 | 53 | 25 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 588206 | 01247 | 6 | Solar | 05_12_16W6 | 05/06/2024 | 09/17/2024 | 52 | 50 | 2 | 09/18/2024 | 09/18/2024 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2024 | 05/06/2024 | 2/18/2026 | Y | EXP | 45 | 03/27/2025 | 07/11/2025 | 107 | 0 | 107 |  |  |  | Completion Documents |  | N
National Grid | EASTON | 342437 | 02356 | 0 | Solar | 05_05_321W2 | 02/26/2021 | 03/01/2021 | 1 | 1 | 0 | 03/02/2021 | 03/02/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2021 |  | 5/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2022 | Connected |  | N
National Grid | BARRE | 582426 | 01005 | 10 | Solar | 05_07_911W13 | 02/01/2024 | 03/07/2024 | 25 | 24 | 1 | 03/08/2024 | 03/08/2024 | 48 | 42 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 317141 | 02019 | 7.6 | Solar | 05_07_18J1 | 10/05/2020 | 11/02/2020 | 18 | 16 | 2 | 11/03/2020 | 11/03/2020 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2021 | Connected |  | N
National Grid | EVERETT | 177137 | 02149 | 7.6 | Solar | 05_01_207W6 | 05/27/2016 | 05/27/2016 | 1 | 1 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 | 05/27/2016 | 6/5/2017 | Y | EXP | 356 | 11/01/2016 | 11/14/2016 | 8 | 0 | 8 | 12/7/2016 | 12/7/2016 | 12/12/2016 | Connected |  | N
National Grid | UXBRIDGE | 203478 | 01569 | 10 | Solar | 05_09_507L1 | 12/17/2018 | 12/31/2018 | 8 | 0 | 8 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 257042 | 02301 | 0 | Solar | 05_09_1001W1 | 09/27/2019 | 10/01/2019 | 1 | 0 | 1 | 10/02/2019 | 10/02/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2019 |  | 9/28/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2020 | Connected |  | N
National Grid | SCITUATE | 658372 | 02066 | 2423 | Solar | 05_07_92W54 | 03/04/2025 | 03/26/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2025 | 04/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 661929 | 01453 | 3.8 | Solar | 05_09_604W4 | 12/20/2024 | 01/14/2025 | 5 | 0 | 5 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 12/20/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | WILBRAHAM | 713501 | 01095 | 13.36 | Solar | 05_05_344W4 | 08/20/2025 | 09/17/2025 | 4 | 0 | 4 | 11/28/2025 | 11/28/2025 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 |  | 1/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2026 | Connected |  | N
National Grid | WILLIAMSTOWN | 174267 | 01267 | 75 | Solar | 05_12_16W6 | 01/03/2012 | 01/03/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2012 |  | 4/2/2012 | N | EXP | 18 |  |  | 0 | 0 | 0 | 6/26/2012 | 6/26/2012 | 7/5/2012 | Connected |  | N
National Grid | WEST BRIDGEWATER | 402695 | 02379 | 0 | Solar | 05_05_321W2 | 12/21/2021 | 01/12/2022 | 16 | 15 | 1 | 01/13/2022 | 01/13/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  | 2/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2022 | Connected |  | N
National Grid | BARRE | 602397 | 01005 | 6 | Solar | 05_07_911W13 | 04/10/2024 | 04/22/2024 | 8 | 5 | 3 | 04/23/2024 | 04/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/10/2024 | 6/11/2025 | Y | EXP | 365 | 08/21/2024 | 09/25/2024 | 36 | 0 | 36 |  |  | 10/3/2024 | Connected |  | N
National Grid | BELLINGHAM | 429558 | 02019 | 15.2 | Solar | 05_07_18J1 | 05/18/2022 | 05/20/2022 | 2 | 0 | 2 | 05/23/2022 | 05/23/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2022 |  | 10/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 177219 | 02149 | 36 | Solar | 05_01_207W6 | 08/15/2016 | 08/15/2016 | 1 | 1 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2016 |  | 1/21/2018 | N | EXP | 486 |  |  | 0 | 0 | 0 | 12/13/2017 | 12/13/2017 | 12/13/2017 | Connected |  | N
National Grid | UXBRIDGE | 322211 | 01569 | 9.8 | Solar | 05_09_507L1 | 11/12/2020 | 11/17/2020 | 2 | 0 | 2 | 11/18/2020 | 11/18/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2020 | 11/12/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2021 | Connected |  | N
National Grid | BROCKTON | 279879 | 02301 | 20 | Solar | 05_09_1001W1 | 03/02/2020 | 03/02/2020 | 0 | 0 | 0 | 03/03/2020 | 03/03/2020 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2020 |  | 3/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2020 | Connected |  | N
National Grid | COHASSET | 679507 | 02025 | 15.2 | Solar | 05_07_92W54 | 03/25/2025 | 03/26/2025 | 1 | 0 | 1 | 03/27/2025 | 03/27/2025 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 | 03/25/2025 | 5/20/2026 | Y | EXP | 365 | 09/09/2025 | 09/23/2025 | 15 | 0 | 15 |  |  | 9/23/2025 | Connected |  | N
National Grid | LEOMINSTER | 674960 | 01453 | 16.34 | Solar | 05_09_604W4 | 02/28/2025 | 03/05/2025 | 4 | 1 | 3 | 03/06/2025 | 03/06/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 720062 | 01095 | 15.2 | Solar | 05_05_344W4 | 09/18/2025 | 09/22/2025 | 2 | 0 | 2 | 09/23/2025 | 09/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | WILLIAMSTOWN | 177687 | 01267 | 6.54 | Solar | 05_12_16W6 | 09/29/2017 | 09/29/2017 | 5 | 5 | 0 | 10/06/2017 | 10/06/2017 | 80 | 12 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2017 |  | 10/7/2018 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 408025 | 02375 | 7.6 | Solar | 05_05_321W2 | 01/25/2022 | 02/01/2022 | 4 | 4 | 0 | 02/02/2022 | 02/02/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  | 3/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2022 | Connected |  | N
National Grid | HUBBARDSTON | 602146 | 01452 | 3.8 | Solar | 05_07_911W13 | 04/05/2024 | 04/25/2024 | 1 | 0 | 1 | 04/26/2024 | 04/26/2024 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 201688 | 02019 | 66.6 | Solar | 05_07_1J11 | 12/04/2018 | 12/20/2018 | 11 | 6 | 5 | 03/06/2019 | 03/06/2019 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 178182 | 02149 | 3.8 | Solar | 05_01_207W6 | 04/13/2018 | 04/13/2018 | 7 | 0 | 7 | 05/02/2018 | 05/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2018 |  | 4/21/2019 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 330777 | 01569 | 7.6 | Solar | 05_09_507L1 | 01/11/2021 | 01/19/2021 | 4 | 4 | 0 | 01/20/2021 | 01/20/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2021 | 01/11/2021 | 1/18/2022 | Y | EXP | 365 | 06/02/2021 | 06/15/2021 | 13 | 0 | 13 |  |  | 7/3/2021 | Connected |  | N
National Grid | BROCKTON | 293844 | 02301 | 10 | Solar | 05_09_1001W1 | 06/26/2020 | 07/10/2020 | 10 | 5 | 5 | 07/13/2020 | 07/13/2020 | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 | 06/26/2020 | 7/9/2021 | Y | EXP | 365 | 12/12/2020 | 05/26/2021 | 165 | 0 | 165 |  |  | 5/27/2021 | Connected |  | N
National Grid | COHASSET | 701340 | 02025 | 15.2 | Solar | 05_07_92W54 | 06/26/2025 | 06/30/2025 | 2 | 0 | 2 | 07/01/2025 | 07/01/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 7/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | LEOMINSTER | 676035 | 01453 | 11.5 | Solar | 05_09_604W4 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | WILBRAHAM | 724250 | 01095 | 10 | Solar | 05_05_344W4 | 10/09/2025 |  | 72 | 68 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 177718 | 01247 | 3.8 | Solar | 05_12_16W6 | 07/27/2017 | 07/27/2017 | 9 | 9 | 0 | 08/09/2017 | 08/09/2017 | 121 | 0 | 121 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2017 |  | 8/1/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 425379 | 02356 | 10 | Solar | 05_05_321W2 | 04/21/2022 | 05/31/2022 | 3 | 0 | 3 | 06/01/2022 | 06/01/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2022 | 04/21/2022 | 11/2/2023 | Y | EXP | 365 | 09/27/2022 | 10/27/2022 | 31 | 0 | 31 |  |  | 11/30/2022 | Connected |  | N
National Grid | BARRE | 604736 | 01005 | 3.84 | Solar | 05_07_911W13 | 04/17/2024 | 05/01/2024 | 3 | 0 | 3 | 05/02/2024 | 05/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 |  | 5/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | BELLINGHAM | 676376 | 02019 | 360 | Solar | 05_07_1J6 | 08/01/2025 | 09/23/2025 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/24/2025 | 10/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MELROSE | 178446 | 02176 | 7.6 | Solar | 05_01_207W6 | 04/03/2018 | 04/03/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2018 |  | 4/9/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2018 | Connected |  | N
National Grid | UXBRIDGE | 354101 | 01569 | 2500 | Solar | 05_09_507L1 | 05/28/2021 | 07/09/2021 | 28 | 16 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/12/2021 | 08/04/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2022 | 05/28/2021 | 5/26/2025 | Y | STD | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 309752 | 02301 | 15.2 | Solar | 05_09_1001W1 | 08/31/2020 | 09/01/2020 | 0 | 0 | 0 | 09/02/2020 | 09/02/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2021 | Connected |  | N
National Grid | COHASSET | 750520 | 02025 | 23 | Solar | 05_07_92W54 | 02/11/2026 | 02/18/2026 | 4 | 0 | 4 | 02/19/2026 | 02/19/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 689688 | 01453 | 13.8 | Solar | 05_09_604W4 | 05/05/2025 | 05/27/2025 | 3 | 0 | 3 | 06/04/2025 | 06/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 | 05/05/2025 | 7/16/2026 | Y | EXP | 365 | 10/03/2025 | 10/09/2025 | 7 | 0 | 7 |  |  | 10/11/2025 | Connected |  | N
National Grid | WILBRAHAM | 174237 | 01095 | 15.69 | Solar | 05_05_344W5 | 02/13/2012 | 02/13/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2012 |  | 3/11/2012 | N | EXP | 53 |  |  | 0 | 0 | 0 | 6/7/2012 | 6/7/2012 | 6/19/2012 | Connected |  | N
National Grid | NORTH ADAMS | 177754 | 01247 | 6 | Solar | 05_12_16W6 | 07/31/2017 | 07/31/2017 | 8 | 8 | 0 | 08/11/2017 | 08/11/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 8/6/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 6/12/2018 | Connected |  | N
National Grid | WEST BRIDGEWATER | 475763 | 02379 | 6.96 | Solar | 05_05_321W2 | 11/29/2022 | 12/06/2022 | 5 | 0 | 5 | 12/07/2022 | 12/07/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 |  | 2/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2023 | Connected |  | Y
National Grid | BARRE | 619935 | 01005 | 20 | Solar | 05_07_911W13 | 06/24/2024 | 06/26/2024 | 2 | 0 | 2 | 06/27/2024 | 06/27/2024 | 109 | 88 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2025 | Connected |  | N
National Grid | FRANKLIN | 712885 | 02038 | 360 | Solar | 05_07_1J6 | 09/24/2025 | 11/04/2025 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2025 | 12/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MELROSE | 187836 | 02176 | 9.84 | Solar | 05_01_207W6 | 06/13/2018 | 06/12/2018 | 10 | 5 | 5 | 06/28/2018 | 06/28/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2018 | 06/13/2018 | 8/30/2019 | Y | EXP | 394 | 03/09/2019 | 03/08/2019 | 0 | 0 | 0 |  |  | 8/10/2019 | Connected |  | N
National Grid | UXBRIDGE | 460064 | 01569 | 15.2 | Solar | 05_09_507L1 | 09/19/2022 | 09/20/2022 | 1 | 0 | 1 | 09/21/2022 | 09/21/2022 | 203 | 25 | 178 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 339003 | 02301 | 10 | Solar | 05_09_1001W1 | 01/27/2021 | 01/29/2021 | 1 | 0 | 1 | 02/01/2021 | 02/01/2021 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 735708 | 02025 | 15.76 | Solar | 05_07_92W78 | 11/21/2025 | 11/24/2025 | 1 | 0 | 1 | 01/12/2026 | 01/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LEOMINSTER | 707812 | 01453 | 4980 | Solar | 05_09_701J1 | 08/14/2025 | 08/29/2025 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/02/2025 | 09/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MONSON | 175989 | 01057 | 15 | Solar | 05_05_344W5 | 03/18/2015 | 03/18/2015 | 4 | 0 | 4 | 03/25/2015 | 03/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2015 |  | 7/20/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 4/15/2015 | 4/15/2015 | 3/18/2016 | Connected |  | N
National Grid | WILLIAMSTOWN | 178263 | 01267 | 16.32 | Solar | 05_12_16W6 | 04/17/2018 | 04/17/2018 | 3 | 3 | 0 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2018 |  | 4/23/2019 | N | EXP | 34 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 490668 | 02375 | 22.8 | Solar | 05_05_321W2 | 01/12/2023 | 01/19/2023 | 4 | 2 | 2 | 01/20/2023 | 01/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 2/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2023 | Connected |  | N
National Grid | BARRE | 641173 | 01005 | 11.4 | Solar | 05_07_911W13 | 09/18/2024 | 10/09/2024 | 1 | 0 | 1 | 10/10/2024 | 10/10/2024 | 74 | 60 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 619741 | 02019 | 86 | Solar | 05_07_1J6 | 07/25/2024 | 08/07/2024 | 9 | 4 | 5 | 08/08/2024 | 08/08/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 |  | 4/5/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | MELROSE | 189869 | 02176 | 4999 | Solar | 05_01_207W6 | 09/10/2018 | 09/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2018 | 11/19/2018 | 46 | 20 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2021 |  | 9/30/2022 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 517155 | 01569 | 15.36 | Solar | 05_09_507L1 | 04/05/2023 | 05/04/2023 | 20 | 18 | 2 | 05/05/2023 | 05/05/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 6/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2023 | Connected |  | N
National Grid | BROCKTON | 378678 | 02301 | 3.8 | Solar | 05_09_1001W1 | 10/21/2021 | 12/29/2021 | 7 | 4 | 3 | 11/02/2021 | 11/02/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 10/21/2021 |  | Y | EXP | 365 | 03/01/2022 | 03/11/2022 | 11 | 0 | 11 |  |  | 4/7/2022 | Connected |  | N
National Grid | QUINCY | 737552 | 02169 | 0 | Battery Add-On | 05_07_92W78 | 12/03/2025 | 12/08/2025 | 3 | 0 | 3 | 12/09/2025 | 12/09/2025 | 40 | 23 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LEOMINSTER | 707788 | 01453 | 2988 | Solar | 05_09_701J1 | 08/14/2025 | 08/29/2025 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/02/2025 | 09/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WILBRAHAM | 176844 | 01095 | 9 | Solar | 05_05_344W5 | 05/02/2016 | 05/02/2016 | 3 | 3 | 0 | 05/06/2016 | 05/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2016 |  | 5/8/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 8/23/2016 | 8/23/2016 | 8/29/2016 | Connected |  | N
National Grid | WILLIAMSTOWN | 185547 | 01267 | 17.85 | Solar | 05_12_16W6 | 05/16/2018 | 05/16/2018 | 35 | 25 | 10 | 06/22/2018 | 06/22/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 534936 | 02375 | 7.6 | Solar | 05_05_321W2 | 06/19/2023 | 06/26/2023 | 5 | 2 | 3 | 06/27/2023 | 06/27/2023 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2023 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2024 | Connected |  | N
National Grid | BARRE | 651633 | 01005 | 3.8 | Solar | 05_07_911W13 | 11/13/2024 | 12/02/2024 | 3 | 0 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/13/2024 | 2/5/2026 | Y | EXP | 365 | 04/15/2025 | 04/16/2025 | 2 | 0 | 2 |  |  | 7/18/2025 | Connected |  | N
National Grid | BELLINGHAM | 673520 | 02019 | 200 | Solar | 05_07_1J6 | 08/04/2025 |  | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 241465 | 02176 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 8/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | UXBRIDGE | 526173 | 01569 | 14.79 | Solar | 05_09_507L1 | 05/12/2023 | 06/05/2023 | 15 | 14 | 1 | 06/06/2023 | 06/06/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 |  | 7/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2023 | Connected |  | N
National Grid | BROCKTON | 577992 | 02301 | 7.6 | Solar | 05_09_1001W1 | 01/09/2024 | 01/19/2024 | 7 | 4 | 3 | 01/22/2024 | 01/22/2024 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 | 01/09/2024 | 2/20/2025 | Y | EXP | 365 | 04/17/2024 | 04/23/2024 | 7 | 0 | 7 |  |  | 1/7/2025 | Connected |  | N
National Grid | QUINCY | 175643 | 02169 | 18 | Solar | 05_07_92W78 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 |  | 2/6/2015 | N | EXP | 88 |  |  | 0 | 0 | 0 | 2/26/2015 | 2/26/2015 | 9/24/2015 | Connected |  | N
National Grid | LEOMINSTER | 716025 | 01453 | 2988 | Solar | 05_09_701J1 | 09/26/2025 | 10/27/2025 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 12/31/2025 | 44 | 24 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HAMPDEN | 177055 | 01036 | 1000 | Solar | 05_05_344W5 | 01/12/2017 | 01/12/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/17/2017 | 01/31/2017 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2017 |  | 4/16/2019 | N | STD | 685 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSTOWN | 237449 | 01267 | 7.6 | Solar | 05_12_16W6 | 07/15/2019 | 08/06/2019 | 16 | 16 | 0 | 08/07/2019 | 08/07/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 | 07/15/2019 | 3/10/2020 | Y | EXP | 365 | 10/11/2019 | 01/07/2020 | 88 | 0 | 88 |  |  | 1/12/2020 | Connected |  | N
National Grid | EASTON | 540266 | 02375 | 5 | Solar | 05_05_321W2 | 08/01/2023 | 08/02/2023 | 1 | 0 | 1 | 08/03/2023 | 08/03/2023 | 23 | 0 | 23 | 10/17/2023 | 10/31/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 10/31/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 12/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2024 | Connected |  | N
National Grid | BARRE | 651979 | 01005 | 3.8 | Solar | 05_07_911W13 | 11/08/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 688257 | 02038 | 75 | Solar | 05_07_1W1 | 11/14/2025 |  | 75 | 67 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MALDEN | 241464 | 02148 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | DOUGLAS | 587977 | 01516 | 14.79 | Solar | 05_09_507L1 | 02/14/2024 | 07/01/2024 | 26 | 22 | 4 | 07/02/2024 | 07/02/2024 | 35 | 25 | 10 | 08/23/2024 | 10/21/2024 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  | 10/21/2024 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 10/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 578098 | 02301 | 9.57 | Solar | 05_09_1001W1 | 01/03/2024 | 01/10/2024 | 5 | 0 | 5 | 01/11/2024 | 01/11/2024 | 86 | 64 | 22 | 06/18/2024 | 09/11/2024 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  | 09/11/2024 | 59 | 0 | 59 |  |  | 0 | 0 | 0 | 9/16/2024 | 01/03/2024 | 11/13/2025 | Y | EXP | 365 | 12/19/2024 | 02/04/2025 | 48 | 0 | 48 |  |  | 4/14/2025 | Connected |  | N
National Grid | QUINCY | 177881 | 02169 | 19.6 | Solar | 05_07_92W78 | 10/18/2017 | 10/18/2017 | 8 | 2 | 6 | 11/07/2017 | 11/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 10/24/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 | 3/7/2018 | 3/7/2018 | 3/19/2018 | Connected |  | N
National Grid | LEOMINSTER | 751184 | 01453 | 0 | Solar | 05_09_701J1 | 02/16/2026 | 02/24/2026 | 5 | 2 | 3 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WILBRAHAM | 187783 | 01095 | 180 | Solar | 05_05_344W5 | 06/17/2018 | 06/17/2018 | 5 | 0 | 5 | 06/29/2018 | 06/29/2018 | 289 | 70 | 219 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 310897 | 01267 | 10 | Solar | 05_12_16W6 | 11/10/2020 | 11/17/2020 | 3 | 0 | 3 | 11/18/2020 | 11/18/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/10/2020 | 1/4/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2021 | Connected |  | N
National Grid | EASTON | 561628 | 02356 | 19.845 | Solar | 05_05_321W2 | 10/13/2023 | 10/16/2023 | 1 | 0 | 1 | 10/17/2023 | 10/17/2023 | 69 | 49 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2024 |  | 2/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2024 | Connected |  | N
National Grid | ROYALSTON | 652437 | 01368 | 5.51 | Solar | 05_07_911W13 | 11/06/2024 | 12/06/2024 | 11 | 5 | 6 | 12/09/2024 | 12/09/2024 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/06/2024 | 2/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | FRANKLIN | 174561 | 02038 | 150 | Solar | 05_07_1W1 | 10/24/2011 | 10/24/2011 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 241463 | 02148 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | UXBRIDGE | 621584 | 01569 | 5 | Solar | 05_09_507L1 | 07/01/2024 | 07/03/2024 | 1 | 0 | 1 | 07/05/2024 | 07/05/2024 | 53 | 38 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 | 07/01/2024 | 12/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | BROCKTON | 655675 | 02301 | 7.6 | Solar | 05_09_1001W1 | 12/05/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 | 12/05/2024 | 3/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | QUINCY | 178257 | 02169 | 15 | Solar | 05_07_92W78 | 04/17/2018 | 04/17/2018 | 31 | 29 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2019 |  | 4/22/2019 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 178159 | 01453 | 3420 | Solar | 05_09_701J1 | 12/26/2017 | 02/12/2018 | 32 | 24 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2018 | 03/14/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 03/03/2020 | 06/05/2020 | 66 | 0 | 66 | 8/16/2018 | 12/26/2017 | 4/26/2022 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 204783 | 01095 | 10 | Solar | 05_05_344W5 | 12/27/2018 | 01/04/2019 | 4 | 0 | 4 | 01/04/2019 | 01/04/2019 | 274 | 269 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2020 |  | 12/27/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 343246 | 01267 | 10 | Solar | 05_12_16W6 | 03/16/2021 | 04/01/2021 | 11 | 6 | 5 | 04/02/2021 | 04/02/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2021 | Connected |  | N
National Grid | EASTON | 574593 | 02356 | 6 | Solar | 05_05_321W2 | 12/27/2023 | 01/29/2024 | 22 | 19 | 3 | 01/30/2024 | 01/30/2024 | 28 | 15 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 12/27/2023 | 4/22/2025 | Y | EXP | 365 | 08/13/2024 | 09/10/2024 | 29 | 0 | 29 |  |  | 9/24/2024 | Connected |  | N
National Grid | ROYALSTON | 654077 | 01368 | 7.6 | Solar | 05_07_911W13 | 11/15/2024 | 12/04/2024 | 2 | 0 | 2 | 12/05/2024 | 12/05/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/15/2024 | 2/13/2026 | Y | EXP | 365 | 07/16/2025 | 08/25/2025 | 41 | 0 | 41 |  |  | 9/10/2025 | Connected |  | N
National Grid | FRANKLIN | 174802 | 02038 | 155 | Solar | 05_07_1W1 | 08/29/2012 | 08/29/2012 | 6 | 0 | 6 | 09/11/2012 | 09/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2013 |  | 12/17/2012 | N | EXP | 29 |  |  | 0 | 0 | 0 | 1/15/2013 | 1/15/2013 | 4/9/2013 | Connected |  | N
National Grid | MALDEN | 241462 | 02148 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | UXBRIDGE | 627518 | 01569 | 7.6 | Solar | 05_09_507L1 | 07/24/2024 | 08/28/2024 | 3 | 0 | 3 | 08/29/2024 | 08/29/2024 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 |  | 10/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 666152 | 02301 | 10 | Solar | 05_09_1001W1 | 01/21/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | QUINCY | 196083 | 02169 | 366.6 | Solar | 05_07_92W78 | 09/17/2018 | 10/01/2018 | 8 | 5 | 3 | 10/02/2018 | 10/02/2018 | 29 | 7 | 22 | 11/29/2018 | 01/10/2019 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  | 01/10/2019 | 28 | 8 | 20 |  |  | 0 | 0 | 0 | 2/22/2019 |  | 8/24/2020 | N | EXP | 549 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 178669 | 01453 | 4990 | Solar | 05_09_701J1 | 03/16/2018 | 04/02/2018 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/24/2018 | 05/31/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 302923 | 01095 | 11.4 | Solar | 05_05_344W5 | 07/24/2020 | 07/30/2020 | 3 | 0 | 3 | 07/31/2020 | 07/31/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2020 | Connected |  | N
National Grid | WILLIAMSTOWN | 369366 | 01267 | 12.98 | Solar | 05_12_16W6 | 08/06/2021 | 08/31/2021 | 18 | 16 | 2 | 09/01/2021 | 09/01/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 |  | 10/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/11/2022 | Connected |  | Y
National Grid | EASTON | 594814 | 02356 | 6 | Solar | 05_05_321W2 | 03/12/2024 | 03/13/2024 | 1 | 0 | 1 | 03/14/2024 | 03/14/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROYALSTON | 655768 | 01368 | 5.12 | Solar | 05_07_911W13 | 12/17/2024 | 12/30/2024 | 3 | 0 | 3 | 12/31/2024 | 12/31/2024 | 45 | 21 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | FRANKLIN | 176826 | 02038 | 54 | Solar | 05_07_1W1 | 01/18/2016 | 01/18/2016 | 2 | 2 | 0 | 01/21/2016 | 01/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2016 | 01/18/2016 | 1/24/2017 | Y | EXP | 347 |  |  | 0 | 0 | 0 | 10/12/2016 | 10/12/2016 | 10/25/2016 | Connected |  | N
National Grid | MALDEN | 241461 | 02148 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | UXBRIDGE | 634668 | 01569 | 7.6 | Solar | 05_09_507L1 | 08/23/2024 | 09/30/2024 | 11 | 8 | 3 | 10/01/2024 | 10/01/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  | 12/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | BROCKTON | 671131 | 02301 | 3.8 | Solar | 05_09_1001W1 | 02/10/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 191163 | 02169 | 50 | Solar | 05_07_92W78 | 07/19/2018 | 08/08/2018 | 4 | 0 | 4 | 08/09/2018 | 08/09/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2018 |  | 8/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2019 | Connected |  | N
National Grid | LEOMINSTER | 195813 | 01453 | 7999 | Solar | 05_09_701J1 | 09/14/2018 | 09/21/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2018 | 11/21/2018 | 34 | 26 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 310834 | 01095 | 11.4 | Solar | 05_05_344W5 | 09/03/2020 | 09/08/2020 | 1 | 0 | 1 | 09/09/2020 | 09/09/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2020 |  | 9/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2021 | Connected |  | N
National Grid | WILLIAMSTOWN | 418205 | 01267 | 7.68 | Solar | 05_12_16W6 | 04/06/2022 | 04/18/2022 | 8 | 7 | 1 | 04/19/2022 | 04/19/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2022 | 04/06/2022 | 7/17/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 609981 | 02356 | 20 | Solar | 05_05_321W2 | 05/09/2024 | 05/10/2024 | 1 | 0 | 1 | 05/13/2024 | 05/13/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | ATHOL | 656212 | 01368 | 6 | Solar | 05_07_911W13 | 11/22/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 398156 | 02038 | 500 | Solar | 05_07_1W1 | 03/03/2022 | 04/06/2022 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2022 | 05/05/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 241466 | 02148 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | MILLVILLE | 639071 | 01529 | 24.32 | Solar | 05_09_507L1 | 09/10/2024 | 09/12/2024 | 3 | 1 | 2 | 09/13/2024 | 09/13/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2024 |  | 10/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | BROCKTON | 693622 | 02301 | 3.8 | Solar | 05_09_1001W1 | 05/22/2025 | 06/06/2025 | 5 | 1 | 4 | 06/17/2025 | 06/17/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/22/2025 | 9/5/2026 | Y | EXP | 365 | 11/14/2025 | 01/12/2026 | 60 | 0 | 60 |  |  | 12/3/2025 | Connected |  | N
National Grid | QUINCY | 208014 | 02169 | 0 | Solar | 05_07_92W78 | 02/02/2019 | 02/12/2019 | 6 | 0 | 6 | 02/13/2019 | 02/13/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 02/02/2019 | 1/6/2023 | Y | EXP | 365 | 04/16/2022 | 12/20/2022 | 249 | 0 | 249 |  |  | 1/5/2023 | Connected |  | N
National Grid | LEOMINSTER | 196252 | 01453 | 250 | Solar | 05_09_701J1 | 10/31/2018 | 12/03/2018 | 10 | 5 | 5 | 12/04/2018 | 12/04/2018 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 314915 | 01095 | 7.6 | Solar | 05_05_344W5 | 09/24/2020 | 09/25/2020 | 0 | 0 | 0 | 09/28/2020 | 09/28/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 |  | 10/26/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 475615 | 01247 | 67.3 | Solar | 05_12_16W6 | 11/10/2022 | 11/23/2022 | 8 | 0 | 8 | 11/25/2022 | 11/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2023 |  | 10/27/2024 | N | EXP | 2 |  |  | 0 | 0 | 0 |  |  | 7/22/2024 | Connected |  | N
National Grid | EASTON | 691998 | 02356 | 7.6 | Solar | 05_05_321W2 | 05/29/2025 | 06/04/2025 | 4 | 0 | 4 | 06/05/2025 | 06/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 | 05/29/2025 | 8/2/2026 | Y | EXP | 365 | 09/03/2025 | 09/02/2025 | 0 | 0 | 0 |  |  | 10/6/2025 | Connected |  | N
National Grid | ROYALSTON | 659918 | 01368 | 3.9 | Solar | 05_07_911W13 | 12/11/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 12/11/2024 | 3/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | FRANKLIN | 618129 | 02038 | 200 | Solar | 05_07_1W1 | 08/05/2024 | 10/25/2024 | 57 | 48 | 9 | 10/28/2024 | 10/28/2024 | 128 | 104 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 9/5/2025 | N | EXP | 21 |  |  | 0 | 0 | 0 |  |  | 8/18/2025 | Connected |  | N
National Grid | MALDEN | 294443 | 02148 | 15.2 | Solar | 05_01_207W6 | 06/02/2020 | 06/04/2020 | 1 | 0 | 1 | 06/05/2020 | 06/05/2020 | 73 | 55 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 | 06/02/2020 | 6/4/2021 | Y | EXP | 365 | 01/20/2021 | 01/26/2021 | 6 | 0 | 6 |  |  | 4/29/2021 | Connected |  | N
National Grid | DOUGLAS | 648176 | 01516 | 20 | Solar | 05_09_507L1 | 10/18/2024 | 11/13/2024 | 17 | 13 | 4 | 11/14/2024 | 11/14/2024 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 695798 | 02301 | 17.1 | Solar | 05_09_1001W1 | 06/18/2025 | 07/02/2025 | 9 | 8 | 1 | 07/03/2025 | 07/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2025 | Connected |  | N
National Grid | QUINCY | 255776 | 02169 | 24.885 | Solar | 05_07_92W78 | 10/15/2019 | 11/08/2019 | 17 | 13 | 4 | 11/12/2019 | 11/12/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2019 |  | 10/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2020 | Connected |  | N
National Grid | LEOMINSTER | 198058 | 01453 | 2400 | Solar | 05_09_701J1 | 10/16/2018 | 11/26/2018 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 01/14/2019 | 56 | 14 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 329798 | 01057 | 15.2 | Solar | 05_05_344W5 | 12/04/2020 | 12/08/2020 | 1 | 0 | 1 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2021 | Connected |  | N
National Grid | NORTH ADAMS | 582518 | 01247 | 10 | Solar | 05_12_16W6 | 01/12/2024 | 02/07/2024 | 17 | 14 | 3 | 02/08/2024 | 02/08/2024 | 23 | 14 | 9 | 03/29/2024 | 04/26/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 04/26/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 4/26/2024 |  | 4/29/2025 | N | EXP | 365 | 06/05/2024 | 06/14/2024 | 10 | 0 | 10 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 721320 | 02356 | 14.309 | Solar | 05_05_321W2 | 09/25/2025 | 10/01/2025 | 4 | 0 | 4 | 10/02/2025 | 10/02/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2026 | Connected |  | N
National Grid | ROYALSTON | 661530 | 01368 | 3.8 | Solar | 05_07_911W13 | 12/30/2024 | 01/21/2025 | 7 | 5 | 2 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 655839 | 02038 | 9.88 | Solar | 05_07_1W1 | 11/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 295621 | 02176 | 9.8 | Solar | 05_01_207W6 | 07/30/2020 | 08/03/2020 | 1 | 0 | 1 | 08/04/2020 | 08/04/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 | 07/30/2020 | 8/2/2021 | Y | EXP | 365 | 05/04/2021 | 05/05/2021 | 1 | 0 | 1 |  |  | 5/24/2021 | Connected |  | N
National Grid | MILLVILLE | 675817 | 01529 | 17.98 | Solar | 05_09_507L1 | 03/10/2025 | 03/13/2025 | 4 | 1 | 3 | 03/14/2025 | 03/14/2025 | 55 | 24 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 177336 | 02301 | 775.1 | Solar | 05_09_1003W1 | 08/31/2016 | 08/31/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/01/2016 | 10/25/2016 | 36 | 23 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2017 | 08/31/2016 | 3/14/2029 | Y | STD | 18 | 11/03/2016 | 01/26/2017 | 55 | 0 | 55 |  |  |  | Completion Documents |  | N
National Grid | QUINCY | 324369 | 02169 | 0 | Solar | 05_07_92W78 | 11/16/2020 | 11/18/2020 | 1 | 0 | 1 | 11/19/2020 | 11/19/2020 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2021 |  | 6/5/2022 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 287445 | 01453 | 10 | Solar | 05_09_701J1 | 04/10/2020 | 04/28/2020 | 13 | 12 | 1 | 04/29/2020 | 04/29/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 |  | 4/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2020 | Connected |  | N
National Grid | WILBRAHAM | 362971 | 01095 | 11.4 | Solar | 05_05_344W5 | 06/09/2021 | 08/19/2021 | 44 | 41 | 3 | 08/20/2021 | 08/20/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 |  | 8/18/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 587105 | 01267 | 7.68 | Solar | 05_12_16W6 | 02/23/2024 | 03/13/2024 | 13 | 9 | 4 | 03/14/2024 | 03/14/2024 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2024 |  | 4/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 621748 | 02356 | 0 | Solar | 05_05_321W4 | 09/13/2024 | 03/03/2025 | 112 | 103 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ROYALSTON | 661583 | 01368 | 10 | Solar | 05_07_911W13 | 12/18/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 | 12/18/2024 | 4/2/2026 | Y | EXP | 365 | 05/24/2025 | 06/10/2025 | 18 | 0 | 18 |  |  | 10/22/2025 | Connected |  | N
National Grid | FRANKLIN | 664597 | 02038 | 5.76 | Solar | 05_07_1W1 | 01/08/2025 | 01/24/2025 | 6 | 1 | 5 | 01/27/2025 | 01/27/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | MELROSE | 326200 | 02176 | 11.4 | Solar | 05_01_207W6 | 11/19/2020 | 11/25/2020 | 4 | 2 | 2 | 11/27/2020 | 11/27/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 |  | 11/24/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | UXBRIDGE | 685667 | 01569 | 11.52 | Solar | 05_09_507L1 | 04/16/2025 | 04/24/2025 | 5 | 0 | 5 | 04/25/2025 | 04/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 5/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2025 | Connected |  | N
National Grid | BROCKTON | 562368 | 02301 | 100 | Solar | 05_09_1003W1 | 10/13/2023 | 10/30/2023 | 11 | 0 | 11 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2024 |  | 10/17/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | QUINCY | 328800 | 02169 | 15.2 | Solar | 05_07_92W78 | 11/30/2020 | 12/08/2020 | 5 | 0 | 5 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 11/30/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 291614 | 01453 | 500 | Solar | 05_09_701J1 | 05/18/2020 | 06/24/2020 | 25 | 16 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 380647 | 01095 | 360 | Solar | 05_05_344W5 | 10/29/2021 | 12/14/2021 | 30 | 20 | 10 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 588827 | 01267 | 6 | Solar | 05_12_16W6 | 03/04/2024 | 03/07/2024 | 3 | 0 | 3 | 03/08/2024 | 03/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 | 03/04/2024 | 4/21/2025 | Y | EXP | 365 | 05/16/2024 | 08/21/2024 | 98 | 0 | 98 |  |  | 9/11/2024 | Connected |  | N
National Grid | EASTON | 737930 | 02356 | 5.76 | Solar | 05_05_321W4 | 12/03/2025 | 12/23/2025 | 12 | 9 | 3 | 02/03/2026 | 02/03/2026 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ATHOL | 663556 | 01331 | 5.76 | Solar | 05_07_911W13 | 01/03/2025 | 01/13/2025 | 3 | 0 | 3 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 01/03/2025 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/8/2025 | Connected |  | N
National Grid | FRANKLIN | 175342 | 02038 | 144 | Solar | 05_07_1W2 | 07/02/2014 | 07/02/2014 | 3 | 0 | 3 | 07/09/2014 | 07/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2014 |  | 11/28/2014 | N | EXP | 113 |  |  | 0 | 0 | 0 | 8/7/2014 | 8/7/2014 | 3/16/2015 | Connected |  | N
National Grid | MELROSE | 325515 | 02176 | 7.6 | Solar | 05_01_207W6 | 11/30/2020 | 12/08/2020 | 5 | 0 | 5 | 12/09/2020 | 12/09/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 11/30/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 705670 | 01569 | 6.96 | Solar | 05_09_507L1 | 07/17/2025 | 07/22/2025 | 3 | 0 | 3 | 07/23/2025 | 07/23/2025 | 81 | 67 | 14 | 11/26/2025 | 12/22/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 12/22/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 12/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 746161 | 02301 | 23 | Solar | 05_09_1003W1 | 01/23/2026 | 01/27/2026 | 2 | 0 | 2 | 01/28/2026 | 01/28/2026 | 27 | 15 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | QUINCY | 374531 | 02169 | 11.4 | Solar | 05_07_92W78 | 08/09/2021 | 08/25/2021 | 13 | 12 | 1 | 08/26/2021 | 08/26/2021 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 10/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2022 | Connected |  | N
National Grid | LEOMINSTER | 318176 | 01453 | 5000 | Solar | 05_09_701J1 | 11/30/2020 | 01/05/2021 | 23 | 21 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2021 | 01/26/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 401360 | 01095 | 0 | Other | 05_05_344W5 | 01/06/2022 | 01/18/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2022 | 01/26/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSTOWN | 600609 | 01267 | 6 | Solar | 05_12_16W6 | 04/04/2024 | 04/10/2024 | 4 | 0 | 4 | 04/11/2024 | 04/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/04/2024 | 5/14/2026 | Y | EXP | 73 | 08/21/2024 | 10/02/2024 | 43 | 0 | 43 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 174184 | 02356 | 1000 | Solar | 05_05_321W4 | 03/13/2012 | 03/13/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROYALSTON | 672811 | 01368 | 10 | Solar | 05_07_911W13 | 02/19/2025 | 03/28/2025 | 18 | 13 | 5 | 03/31/2025 | 03/31/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 175453 | 02038 | 120 | Solar | 05_07_1W2 | 07/15/2014 | 07/15/2014 | 5 | 0 | 5 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2014 |  | 10/31/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 10/1/2014 | 10/1/2014 | 11/23/2015 | Connected |  | N
National Grid | MELROSE | 401899 | 02176 | 6 | Solar | 05_01_207W6 | 01/26/2022 | 01/27/2022 | 0 | 0 | 0 | 01/28/2022 | 01/28/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 |  | 4/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2022 | Connected |  | N
National Grid | MILLVILLE | 715109 | 01529 | 15.36 | Solar | 05_09_507L1 | 08/29/2025 | 09/02/2025 | 1 | 0 | 1 | 09/03/2025 | 09/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2026 | Connected |  | N
National Grid | BROCKTON | 174286 | 02301 | 24.4 | Solar | 05_09_1003W1 | 11/07/2011 | 11/07/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2012 |  | 12/30/2011 | N | EXP | 116 |  |  | 0 | 0 | 0 | 7/24/2012 | 7/24/2012 | 7/24/2012 | Connected |  | N
National Grid | QUINCY | 378621 | 02169 | 7.6 | Solar | 05_07_92W78 | 08/29/2021 | 09/24/2021 | 20 | 19 | 1 | 09/27/2021 | 09/27/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  | 9/23/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 494175 | 01453 | 7.6 | Solar | 05_09_701J1 | 03/08/2023 | 03/13/2023 | 4 | 3 | 1 | 03/14/2023 | 03/14/2023 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 |  | 6/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2023 | Connected |  | N
National Grid | WILBRAHAM | 427984 | 01095 | 15.2 | Solar | 05_05_344W5 | 05/03/2022 | 05/04/2022 | 1 | 1 | 0 | 05/05/2022 | 05/05/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 |  | 9/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2022 | Connected |  | N
National Grid | WILLIAMSTOWN | 616847 | 01267 | 7.6 | Solar | 05_12_16W6 | 06/10/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | EASTON | 175347 | 02356 | 42 | Solar | 05_05_321W4 | 07/03/2014 | 07/03/2014 | 3 | 0 | 3 | 07/10/2014 | 07/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2014 |  | 12/31/2016 | N | EXP | 879 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 1/22/2016 | Connected |  | N
National Grid | ROYALSTON | 674919 | 01368 | 15.76 | Solar | 05_07_911W13 | 02/28/2025 | 03/12/2025 | 8 | 4 | 4 | 03/13/2025 | 03/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 178325 | 02038 | 6 | Solar | 05_07_1W2 | 03/30/2018 | 03/30/2018 | 7 | 0 | 7 | 04/10/2018 | 04/10/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2018 | 03/30/2018 | 4/4/2019 | Y | EXP | 323 |  |  | 0 | 0 | 0 |  |  | 10/29/2018 | Connected |  | N
National Grid | MELROSE | 409760 | 02176 | 12 | Solar | 05_01_207W6 | 05/12/2022 | 05/17/2022 | 3 | 1 | 2 | 05/18/2022 | 05/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2022 |  | 10/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2022 | Connected |  | N
National Grid | UXBRIDGE | 717200 | 01569 | 11.5 | Solar | 05_09_507L1 | 09/05/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174675 | 02301 | 500 | Solar | 05_09_1003W1 | 06/03/2013 | 06/03/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 421426 | 02169 | 15.2 | Solar | 05_07_92W78 | 04/01/2022 | 06/06/2022 | 44 | 41 | 3 | 06/07/2022 | 06/07/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2022 |  | 7/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2022 | Connected |  | N
National Grid | LEOMINSTER | 665005 | 01453 | 10 | Solar | 05_09_701J1 | 01/10/2025 | 02/18/2025 | 23 | 18 | 5 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N
National Grid | WILBRAHAM | 472534 | 01095 | 15.2 | Solar | 05_05_344W5 | 10/31/2022 | 11/01/2022 | 1 | 0 | 1 | 11/02/2022 | 11/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2022 |  | 12/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2023 | Connected |  | N
National Grid | WILLIAMSTOWN | 628444 | 01267 | 15.2 | Solar | 05_12_16W6 | 07/29/2024 | 08/01/2024 | 1 | 0 | 1 | 12/04/2024 | 12/04/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2024 |  | 1/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | EASTON | 175346 | 02356 | 265 | Solar | 05_05_321W4 | 07/03/2014 | 07/03/2014 | 3 | 0 | 3 | 07/10/2014 | 07/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2014 |  | 11/28/2014 | N | EXP | 129 |  |  | 0 | 0 | 0 | 7/22/2014 | 7/22/2014 | 3/2/2016 | Connected |  | N
National Grid | ATHOL | 678401 | 01331 | 4.06 | Solar | 05_07_911W13 | 03/17/2025 | 03/27/2025 | 4 | 0 | 4 | 04/08/2025 | 04/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 178365 | 02038 | 7.6 | Solar | 05_07_1W2 | 03/30/2018 | 03/30/2018 | 4 | 0 | 4 | 04/06/2018 | 04/06/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 |  | 4/7/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 416852 | 02176 | 9.86 | Solar | 05_01_207W6 | 03/11/2022 | 04/04/2022 | 16 | 13 | 3 | 04/05/2022 | 04/05/2022 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2022 | 03/11/2022 | 7/26/2023 | Y | EXP | 365 | 06/30/2022 | 07/20/2022 | 21 | 0 | 21 |  |  | 8/24/2022 | Connected |  | Y
National Grid | DOUGLAS | 713765 | 01516 | 10 | Solar | 05_09_507L2 | 08/21/2025 | 09/18/2025 | 3 | 0 | 3 | 09/26/2025 | 09/26/2025 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 | 08/21/2025 | 11/12/2026 | Y | EXP | 365 | 01/15/2026 | 02/13/2026 | 30 | 0 | 30 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 174785 | 02301 | 500 | Solar | 05_09_1003W1 | 06/03/2013 | 06/03/2013 | 7 | 0 | 7 | 06/13/2013 | 06/13/2013 | 235 | 41 | 194 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2013 | 06/03/2013 | 12/31/2013 | Y | EXP | 6 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 422073 | 02169 | 0 | Battery Add-On | 05_07_92W78 | 07/27/2022 | 08/11/2022 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2022 | 09/09/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 697634 | 01453 | 11.4 | Solar | 05_09_701J1 | 06/10/2025 | 06/30/2025 | 5 | 0 | 5 | 09/11/2025 | 09/11/2025 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | HAMPDEN | 478730 | 01036 | 15.2 | Solar | 05_05_344W5 | 11/18/2022 | 12/05/2022 | 10 | 8 | 2 | 12/06/2022 | 12/06/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 |  | 1/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2023 | Connected |  | N
National Grid | WILLIAMSTOWN | 648715 | 01267 | 5.76 | Solar | 05_12_16W6 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 175864 | 02356 | 10 | Solar | 05_05_321W4 | 09/22/2015 | 09/22/2015 | 3 | 3 | 0 | 09/28/2015 | 09/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2015 |  | 9/28/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 9/22/2015 | 9/22/2015 | 3/14/2016 | Connected |  | N
National Grid | ROYALSTON | 679982 | 01368 | 11.02 | Solar | 05_07_911W13 | 03/24/2025 | 04/14/2025 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 03/24/2025 | 6/9/2026 | Y | EXP | 365 | 09/09/2025 | 12/02/2025 | 85 | 0 | 85 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 195989 | 02038 | 10 | Solar | 05_07_1W2 | 11/02/2018 | 02/01/2019 | 59 | 54 | 5 | 02/04/2019 | 02/04/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2019 | 11/02/2018 | 10/8/2019 | Y | EXP | 365 | 04/10/2019 | 05/31/2019 | 51 | 0 | 51 |  |  | 10/8/2019 | Connected |  | N
National Grid | MELROSE | 427452 | 02176 | 19 | Solar | 05_01_207W6 | 05/03/2022 | 06/28/2022 | 38 | 35 | 3 | 06/29/2022 | 06/29/2022 | 343 | 325 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 735593 | 01516 | 7.6 | Solar | 05_09_507L2 | 11/21/2025 | 11/24/2025 | 4 | 0 | 4 | 12/30/2025 | 12/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROCKTON | 175460 | 02301 | 414 | Solar | 05_09_1003W1 | 09/19/2014 | 09/19/2014 | 7 | 0 | 7 | 10/01/2014 | 10/01/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2014 | 09/19/2014 | 1/30/2015 | Y | EXP | 84 | 04/02/2015 | 05/19/2015 | 32 | 0 | 32 | 6/9/2015 | 6/9/2015 | 6/9/2015 | Connected |  | N
National Grid | QUINCY | 428918 | 02169 | 7.6 | Solar | 05_07_92W78 | 08/19/2022 | 08/22/2022 | 1 | 0 | 1 | 08/23/2022 | 08/23/2022 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2022 | 08/19/2022 | 9/23/2023 | Y | EXP | 365 | 10/27/2022 | 12/07/2022 | 42 | 0 | 42 |  |  | 1/18/2023 | Connected |  | N
National Grid | LEOMINSTER | 701325 | 01453 | 11.5 | Solar | 05_09_701J1 | 06/27/2025 | 07/15/2025 | 10 | 6 | 4 | 07/16/2025 | 07/16/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 | 06/27/2025 | 9/25/2026 | Y | EXP | 365 | 12/31/2025 | 01/12/2026 | 13 | 0 | 13 |  |  | 1/13/2026 | Connected |  | N
National Grid | MONSON | 519911 | 01057 | 15.2 | Solar | 05_05_344W5 | 04/20/2023 | 06/14/2023 | 38 | 37 | 1 | 06/15/2023 | 06/15/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2023 |  | 7/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2023 | Connected |  | N
National Grid | WILLIAMSTOWN | 650399 | 01267 | 9.88 | Solar | 05_12_16W6 | 11/01/2024 | 11/18/2024 | 4 | 0 | 4 | 11/19/2024 | 11/19/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 11/01/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N
National Grid | EASTON | 175948 | 02356 | 630 | Solar | 05_05_321W4 | 03/16/2015 | 03/16/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/20/2015 | 04/17/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROYALSTON | 702430 | 01368 | 3.8 | Solar | 05_07_911W13 | 07/07/2025 | 07/18/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 199529 | 02038 | 7.6 | Solar | 05_07_1W2 | 11/05/2018 | 11/20/2018 | 9 | 7 | 2 | 11/21/2018 | 11/21/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2018 | 11/05/2018 | 11/15/2019 | Y | EXP | 333 |  |  | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | MALDEN | 471046 | 02148 | 6 | Solar | 05_01_207W6 | 11/20/2023 | 11/01/2022 | 1 | 0 | 1 | 11/22/2023 | 11/22/2023 | 40 | 19 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2022 | 11/20/2023 | 2/20/2025 | Y | EXP | 365 | 05/03/2024 | 05/29/2024 | 27 | 0 | 27 |  |  | 7/6/2024 | Connected |  | N
National Grid | UXBRIDGE | 752922 | 01569 | 11.4 | Solar | 05_09_507L2 | 02/24/2026 | 02/27/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BROCKTON | 175552 | 02301 | 2000 | Solar | 05_09_1003W1 | 04/16/2014 | 04/16/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/25/2014 | 05/16/2014 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 448291 | 02169 | 15.2 | Solar | 05_07_92W78 | 08/01/2022 | 08/02/2022 | 1 | 0 | 1 | 08/03/2022 | 08/03/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2022 |  | 9/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 712920 | 01453 | 7.25 | Solar | 05_09_701J1 | 08/18/2025 | 09/22/2025 | 2 | 0 | 2 | 09/23/2025 | 09/23/2025 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2025 | Connected |  | N
National Grid | WILBRAHAM | 526935 | 01095 | 7.6 | Solar | 05_05_344W5 | 07/26/2023 | 07/31/2023 | 4 | 1 | 3 | 08/01/2023 | 08/01/2023 | 78 | 26 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 651613 | 01267 | 3.8 | Solar | 05_12_16W6 | 11/20/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 187429 | 02356 | 1250 | Solar | 05_05_321W4 | 08/08/2018 | 08/23/2018 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2018 | 12/14/2018 | 76 | 35 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROYALSTON | 710544 | 01368 | 15.96 | Solar | 05_07_911W13 | 08/07/2025 | 08/11/2025 | 2 | 0 | 2 | 08/12/2025 | 08/12/2025 | 51 | 39 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 254182 | 02038 | 7.6 | Solar | 05_07_1W2 | 09/23/2019 | 10/01/2019 | 5 | 4 | 1 | 10/02/2019 | 10/02/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2019 | 09/23/2019 | 11/6/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2020 | Connected |  | N
National Grid | MALDEN | 487948 | 02148 | 10 | Solar | 05_01_207W6 | 02/06/2023 | 02/08/2023 | 2 | 0 | 2 | 02/09/2023 | 02/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/06/2023 | 9/19/2024 | Y | EXP | 365 | 10/18/2023 | 11/14/2023 | 28 | 0 | 28 |  |  | 1/31/2024 | Connected |  | Y
National Grid | UXBRIDGE | 175375 | 01569 | 3000 | Solar | 05_09_507L2 | 02/26/2014 | 02/26/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/17/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2014 | N | STD |  | 10/13/2016 | 12/02/2016 | 34 | 0 | 34 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 175618 | 02301 | 18 | Solar | 05_09_1003W1 | 04/30/2014 | 04/30/2014 | 6 | 0 | 6 | 05/09/2014 | 05/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2014 |  | 8/15/2014 | N | EXP | 73 |  |  | 0 | 0 | 0 | 6/3/2014 | 6/3/2014 | 7/23/2014 | Connected |  | N
National Grid | QUINCY | 479467 | 02169 | 17.28 | Solar | 05_07_92W78 | 11/22/2022 | 02/06/2023 | 50 | 46 | 4 | 02/07/2023 | 02/07/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 687139 | 01453 | 4980 | Solar | 05_09_702W1 | 06/03/2025 | 07/09/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 07/28/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WILBRAHAM | 531442 | 01095 | 14.79 | Solar | 05_05_344W5 | 06/05/2023 | 06/16/2023 | 10 | 9 | 1 | 06/20/2023 | 06/20/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 658379 | 01267 | 7.6 | Solar | 05_12_16W6 | 12/10/2024 | 01/07/2025 | 14 | 10 | 4 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | EASTON | 288134 | 02356 | 0 | Other | 05_05_321W4 | 01/14/2021 | 02/17/2021 | 22 | 17 | 5 |  |  | 39 | 21 | 18 |  |  | 0 | 0 | 0 | 03/19/2021 | 04/14/2021 | 18 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROYALSTON | 719427 | 01368 | 10 | Solar | 05_07_911W13 | 09/18/2025 | 09/23/2025 | 3 | 1 | 2 | 09/24/2025 | 09/24/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 |  | 10/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | FRANKLIN | 309572 | 02038 | 6.96 | Solar | 05_07_1W2 | 09/28/2020 | 10/05/2020 | 5 | 3 | 2 | 10/06/2020 | 10/06/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 | 09/28/2020 | 11/3/2021 | Y | EXP | 365 | 01/13/2021 | 02/24/2021 | 41 | 0 | 41 |  |  | 3/10/2021 | Connected |  | N
National Grid | MALDEN | 491121 | 02148 | 9.86 | Solar | 05_01_207W6 | 02/02/2023 | 02/06/2023 | 2 | 0 | 2 | 02/07/2023 | 02/07/2023 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2023 | 02/02/2023 | 5/31/2024 | Y | EXP | 365 | 06/01/2023 | 05/31/2023 | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | UXBRIDGE | 175577 | 01569 | 15.2 | Solar | 05_09_507L2 | 12/09/2014 | 12/09/2014 | 4 | 2 | 2 | 12/16/2014 | 12/16/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2014 |  | 2/28/2015 | N | EXP | 74 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 9/30/2015 | Connected |  | N
National Grid | BROCKTON | 175723 | 02301 | 1187 | Natural Gas | 05_09_1003W1 | 01/05/2015 | 01/05/2015 | 12 | 10 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2015 | 02/04/2015 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2015 |  | 12/31/2016 | N | STD | 394 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 479458 | 02169 | 7.6 | Solar | 05_07_92W78 | 11/22/2022 | 11/29/2022 | 4 | 0 | 4 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2023 |  | 1/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 692776 | 01453 | 7.6 | Solar | 05_09_702W1 | 05/20/2025 | 05/28/2025 | 4 | 0 | 4 | 06/25/2025 | 06/25/2025 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 05/20/2025 | 9/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | WILBRAHAM | 567611 | 01095 | 7.6 | Solar | 05_05_344W5 | 12/05/2023 | 12/11/2023 | 5 | 2 | 3 | 12/12/2023 | 12/12/2023 | 51 | 28 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 663005 | 01267 | 7.6 | Solar | 05_12_16W6 | 12/30/2024 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2025 | Connected |  | N
National Grid | EASTON | 474056 | 02356 | 5100 | Solar | 05_05_321W4 | 06/02/2023 | 09/14/2023 | 72 | 62 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/15/2023 | 10/09/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROYALSTON | 616921 | 01368 | 300 | Solar | 05_07_911W25 | 09/16/2024 | 03/05/2025 | 114 | 104 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2025 | 04/02/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FRANKLIN | 317594 | 02038 | 10 | Solar | 05_07_1W2 | 10/06/2020 | 10/09/2020 | 2 | 0 | 2 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2021 | Connected |  | N
National Grid | MELROSE | 556880 | 02176 | 9.86 | Solar | 05_01_207W6 | 10/18/2023 | 11/08/2023 | 16 | 14 | 2 | 11/09/2023 | 11/09/2023 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 |  | 1/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 175590 | 01569 | 496 | Solar | 05_09_507L2 | 04/22/2014 | 04/22/2014 | 9 | 4 | 5 | 05/06/2014 | 05/06/2014 | 0 | 0 | 0 | 08/06/2014 | 08/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2014 | 04/22/2014 | 6/30/2016 | Y | EXP | 694 | 10/13/2016 | 12/02/2016 | 34 | 0 | 34 | 12/8/2016 | 12/8/2016 | 12/8/2016 | Connected |  | N
National Grid | BROCKTON | 175910 | 02301 | 130 | Solar | 05_09_1003W1 | 03/09/2015 | 03/09/2015 | 5 | 0 | 5 | 03/18/2015 | 03/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2015 |  | 7/31/2015 | N | EXP | 115 |  |  | 0 | 0 | 0 | 7/30/2015 | 7/30/2015 | 7/30/2015 | Connected |  | N
National Grid | QUINCY | 489931 | 02169 | 13 | Solar | 05_07_92W78 | 01/10/2023 | 01/17/2023 | 5 | 4 | 1 | 01/18/2023 | 01/18/2023 | 50 | 30 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 | 01/10/2023 | 7/17/2024 | Y | EXP | 365 | 08/10/2023 | 09/08/2023 | 30 | 0 | 30 |  |  | 9/15/2023 | Connected |  | N
National Grid | LEOMINSTER | 716803 | 01453 | 5.76 | Solar | 05_09_702W1 | 09/04/2025 | 10/20/2025 | 3 | 0 | 3 | 12/03/2025 | 12/03/2025 | 38 | 25 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WILBRAHAM | 606726 | 01095 | 0 | Solar | 05_05_344W5 | 12/23/2024 | 01/31/2025 | 15 | 11 | 4 | 02/03/2025 | 02/03/2025 | 30 | 9 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | WILLIAMSTOWN | 675526 | 01267 | 15.2 | Solar | 05_12_16W6 | 03/04/2025 | 04/09/2025 | 27 | 22 | 5 | 04/10/2025 | 04/10/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N
National Grid | EASTON | 648550 | 02334 | 5.76 | Solar | 05_05_321W4 | 11/01/2024 | 12/04/2024 | 14 | 9 | 5 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2025 | 11/01/2024 | 2/24/2026 | Y | EXP | 365 | 04/03/2025 | 05/05/2025 | 33 | 0 | 33 |  |  | 5/9/2025 | Connected |  | N
National Grid | ROYALSTON | 175385 | 01368 | 92 | Solar | 05_07_911W25 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2014 |  | 11/28/2014 | N | EXP | 12 |  |  | 0 | 0 | 0 | 8/7/2014 | 8/7/2014 | 3/17/2015 | Connected |  | N
National Grid | FRANKLIN | 405421 | 02038 | 4.64 | Solar | 05_07_1W2 | 03/01/2022 | 03/02/2022 | 1 | 0 | 1 | 03/03/2022 | 03/03/2022 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 571006 | 02176 | 7.6 | Solar | 05_01_207W6 | 11/27/2023 | 11/29/2023 | 3 | 2 | 1 | 11/30/2023 | 11/30/2023 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 | 11/27/2023 | 6/30/2025 | Y | EXP | 365 | 02/17/2024 | 02/16/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 175965 | 01569 | 8.39 | Solar | 05_09_507L2 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 |  | 8/15/2016 | N | EXP | 342 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 4/14/2016 | Connected |  | N
National Grid | BROCKTON | 176138 | 02301 | 1500 | Solar | 05_09_1003W1 | 06/26/2015 | 06/26/2015 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/01/2015 | 07/29/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 | 06/26/2015 | 10/18/2017 | Y | STD | 56 |  |  | 0 | 0 | 0 | 10/20/2017 | 10/20/2017 | 11/17/2017 | Connected |  | N
National Grid | QUINCY | 502360 | 02169 | 13.3 | Solar | 05_07_92W78 | 02/15/2023 | 02/17/2023 | 3 | 2 | 1 | 02/21/2023 | 02/21/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 | 02/15/2023 | 5/4/2024 | Y | EXP | 365 | 07/07/2023 | 07/26/2023 | 20 | 0 | 20 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 724125 | 01453 | 20 | Solar | 05_09_702W1 | 10/05/2025 | 10/07/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WILBRAHAM | 606999 | 01095 | 0 | Battery Add-On | 05_05_344W5 | 04/26/2024 | 04/30/2024 | 2 | 0 | 2 | 05/01/2024 | 05/01/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 | 04/26/2024 | 5/13/2025 | Y | EXP | 365 | 05/23/2024 | 05/22/2024 | 0 | 0 | 0 |  |  | 10/4/2024 | Connected |  | N
National Grid | WILLIAMSTOWN | 679311 | 01267 | 11.5 | Solar | 05_12_16W6 | 03/20/2025 | 04/07/2025 | 1 | 0 | 1 | 07/16/2025 | 07/16/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2025 | Connected |  | N
National Grid | EASTON | 661004 | 02356 | 5.51 | Solar | 05_05_321W4 | 12/20/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/20/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | ATHOL | 176824 | 01037 | 7.6 | Solar | 05_07_911W25 | 01/15/2016 | 01/15/2016 | 0 | 0 | 0 | 01/15/2016 | 01/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 | 01/15/2016 | 1/20/2017 | Y | EXP | 346 | 08/12/2016 | 09/02/2016 | 15 | 0 | 15 | 10/6/2016 | 10/6/2016 | 10/11/2016 | Connected |  | N
National Grid | FRANKLIN | 422902 | 02038 | 0 | Solar | 05_07_1W2 | 04/08/2022 | 04/11/2022 | 1 | 0 | 1 | 04/12/2022 | 04/12/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2022 |  | 6/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2023 | Connected |  | N
National Grid | MALDEN | 573946 | 02148 | 0 | Battery Add-On | 05_01_207W6 | 11/28/2023 | 11/30/2023 | 2 | 0 | 2 | 12/01/2023 | 12/01/2023 | 66 | 49 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2024 | Connected |  | N
National Grid | DOUGLAS | 176402 | 01516 | 6 | Solar | 05_09_507L2 | 03/11/2016 | 03/11/2016 | 3 | 3 | 0 | 03/17/2016 | 03/17/2016 | 225 | 0 | 225 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2016 |  | 3/19/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 176523 | 02301 | 80.5 | Solar | 05_09_1003W1 | 12/11/2015 | 12/11/2015 | 4 | 4 | 0 | 12/17/2015 | 12/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2016 |  | 12/16/2016 | N | EXP | 326 |  |  | 0 | 0 | 0 | 8/19/2016 | 8/19/2016 | 8/24/2016 | Connected |  | N
National Grid | QUINCY | 521894 | 02169 | 14.97 | Solar | 05_07_92W78 | 04/26/2023 | 05/01/2023 | 4 | 2 | 2 | 05/02/2023 | 05/02/2023 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2023 | Connected |  | N
National Grid | LEOMINSTER | 725118 | 01453 | 8.7 | Solar | 05_09_702W1 | 10/08/2025 | 10/09/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  | 12/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WILBRAHAM | 625699 | 01095 | 5.76 | Solar | 05_05_344W5 | 07/17/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 07/17/2024 | 10/3/2025 | Y | EXP | 365 | 11/20/2024 | 11/19/2024 | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | WILLIAMSTOWN | 693560 | 01267 | 7.6 | Solar | 05_12_16W6 | 05/22/2025 | 06/18/2025 | 7 | 1 | 6 | 06/20/2025 | 06/20/2025 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N
National Grid | EASTON | 370747 | 02334 | 455 | Solar | 05_05_321W5 | 09/07/2021 | 06/22/2022 | 198 | 189 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2022 | 11/21/2022 | 104 | 85 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | ATHOL | 177205 | 01331 | 153.2 | Solar | 05_07_911W25 | 02/01/2017 | 02/01/2017 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 468425 | 02038 | 9.8 | Solar | 05_07_1W2 | 10/20/2022 | 10/24/2022 | 2 | 0 | 2 | 10/25/2022 | 10/25/2022 | 180 | 25 | 155 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 575385 | 02176 | 2.32 | Solar | 05_01_207W6 | 01/15/2024 | 01/24/2024 | 8 | 5 | 3 | 01/25/2024 | 01/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 01/15/2024 | 3/6/2025 | Y | EXP | 365 | 05/30/2024 | 07/01/2024 | 33 | 0 | 33 |  |  | 7/3/2024 | Connected |  | N
National Grid | UXBRIDGE | 177227 | 01516 | 10 | Solar | 05_09_507L2 | 11/01/2016 | 11/01/2016 | 3 | 3 | 0 | 11/07/2016 | 11/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 11/01/2016 | 11/7/2017 | Y | EXP | 357 | 02/08/2017 | 02/25/2017 | 12 | 0 | 12 | 3/30/2017 | 3/30/2017 | 4/5/2017 | Connected |  | N
National Grid | BROCKTON | 176733 | 02302 | 160 | Solar | 05_09_1003W1 | 04/26/2016 | 04/26/2016 | 2 | 2 | 0 | 04/29/2016 | 04/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 |  | 5/2/2017 | N | EXP | 341 |  |  | 0 | 0 | 0 | 4/26/2017 | 4/26/2017 | 4/26/2017 | Connected |  | N
National Grid | QUINCY | 532740 | 02169 | 10 | Solar | 05_07_92W78 | 06/09/2023 | 07/20/2023 | 27 | 25 | 2 | 07/21/2023 | 07/21/2023 | 70 | 49 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 |  | 1/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | LEOMINSTER | 728611 | 01453 | 3.8 | Solar | 05_09_702W1 | 10/23/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 55 | 35 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/28/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WILBRAHAM | 645585 | 01095 | 10 | Solar | 05_05_344W5 | 10/23/2024 | 12/04/2024 | 10 | 8 | 2 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 10/23/2024 | 1/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | WILLIAMSTOWN | 726424 | 01267 | 3.8 | Solar | 05_12_16W6 | 10/14/2025 | 11/17/2025 | 3 | 0 | 3 | 12/23/2025 | 12/23/2025 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 419350 | 02356 | 240 | Solar | 05_05_321W5 | 05/26/2022 | 06/13/2022 | 11 | 6 | 5 | 06/14/2022 | 06/14/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 |  | 6/19/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATHOL | 177400 | 01331 | 480 | Solar | 05_07_911W25 | 06/29/2016 | 06/29/2016 | 0 | 0 | 0 | 06/30/2016 | 06/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2016 |  | 7/5/2017 | N | EXP | 315 |  |  | 0 | 0 | 0 | 5/30/2017 | 5/30/2017 | 6/1/2017 | Connected |  | N
National Grid | FRANKLIN | 477496 | 02038 | 2.792 | Solar | 05_07_1W2 | 11/18/2022 | 11/23/2022 | 3 | 0 | 3 | 11/25/2022 | 11/25/2022 | 241 | 222 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 607929 | 02148 | 10 | Solar | 05_01_207W6 | 05/01/2024 | 05/23/2024 | 9 | 3 | 6 | 05/24/2024 | 05/24/2024 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 | 05/01/2024 | 7/11/2025 | Y | EXP | 365 | 10/03/2024 | 10/22/2024 | 20 | 0 | 20 |  |  | 11/9/2024 | Connected |  | N
National Grid | UXBRIDGE | 177811 | 01569 | 15.2 | Solar | 05_09_507L2 | 03/31/2017 | 03/31/2017 | 5 | 2 | 3 | 04/07/2017 | 04/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 11/30/2018 | N | EXP | 599 |  |  | 0 | 0 | 0 | 1/24/2018 | 1/24/2018 | 1/24/2018 | Connected |  | N
National Grid | BROCKTON | 178161 | 02301 | 233.1 | Solar | 05_09_1003W1 | 02/12/2018 | 02/12/2018 | 10 | 0 | 10 | 04/17/2018 | 04/17/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2018 |  | 2/18/2019 | N | EXP | 144 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 204168 | 02169 | 173.2 | Solar | 05_07_911W25 | 12/18/2018 | 01/10/2019 | 14 | 12 | 2 | 01/11/2019 | 01/11/2019 | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 489308 | 01453 | 4.35 | Solar | 05_07_1W2 | 02/21/2023 | 02/21/2023 | 8 | 0 | 8 | 02/22/2023 | 02/22/2023 | 239 | 213 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 650816 | 01095 | 10 | Solar | 05_01_207W6 | 10/30/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 10/30/2024 | 12/30/2025 | Y | EXP | 365 | 03/13/2025 | 03/28/2025 | 16 | 0 | 16 |  |  | 4/5/2025 | Connected |  | N
National Grid | WILLIAMSTOWN | 178129 | 01267 | 3.23 | Solar | 05_09_507L2 | 07/12/2017 | 07/12/2017 | 5 | 0 | 5 | 07/19/2017 | 07/19/2017 | 149 | 16 | 133 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2017 |  | 7/17/2018 | N | EXP | 337 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 191459 | 02356 | 35.4 | Solar | 05_09_1003W1 | 08/20/2018 | 08/22/2018 | 0 | 0 | 0 | 08/23/2018 | 08/23/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2018 |  | 8/27/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2019 | Connected |  | N
National Grid | ATHOL | 279970 | 01331 | 10 | Solar | 05_07_911W25 | 03/25/2020 | 05/26/2020 | 44 | 43 | 1 | 05/27/2020 | 05/27/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 | 03/25/2020 | 5/25/2021 | Y | EXP | 365 | 09/03/2020 | 09/24/2020 | 21 | 0 | 21 |  |  | 1/19/2021 | Connected |  | N
National Grid | FRANKLIN | 493396 | 02038 | 7.6 | Solar | 05_07_1W2 | 01/23/2023 | 01/25/2023 | 2 | 0 | 2 | 01/26/2023 | 01/26/2023 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 | 01/23/2023 | 7/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2023 | Connected |  | N
National Grid | MELROSE | 659044 | 02176 | 7.6 | Solar | 05_01_207W6 | 12/06/2024 | 12/23/2024 | 8 | 3 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 189780 | 01569 | 746 | Solar | 05_09_507L2 | 07/03/2018 | 07/03/2018 | 61 | 46 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 200515 | 02301 | 53.3 | Solar | 05_09_1003W1 | 11/09/2018 | 01/29/2019 | 51 | 42 | 9 | 01/30/2019 | 01/30/2019 | 47 | 26 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2019 |  | 2/26/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2021 | Connected |  | N
National Grid | QUINCY | 306208 | 02169 | 166.6 | Solar | 05_07_911W25 | 02/03/2021 | 02/17/2021 | 8 | 0 | 8 | 02/18/2021 | 02/18/2021 | 23 | 0 | 23 | 04/22/2021 | 05/10/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 05/10/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 5/24/2021 | 02/03/2021 | 8/24/2022 | Y | EXP | 245 | 10/22/2021 | 09/02/2022 | 315 | 203 | 112 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 504369 | 01453 | 4.64 | Solar | 05_07_1W2 | 03/16/2023 | 03/22/2023 | 5 | 2 | 3 | 03/23/2023 | 03/23/2023 | 22 | 0 | 22 | 06/02/2023 | 07/12/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 07/12/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 6/29/2023 |  | 9/6/2024 | N | EXP | 365 | 07/06/2023 | 09/01/2023 | 58 | 0 | 58 |  |  | 9/22/2023 | Connected |  | N
National Grid | WILBRAHAM | 666673 | 01095 | 7.6 | Solar | 05_01_207W6 | 01/20/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 | 01/20/2025 | 4/10/2026 | Y | EXP | 365 | 06/12/2025 | 06/24/2025 | 13 | 0 | 13 |  |  | 8/22/2025 | Connected |  | N
National Grid | WILLIAMSTOWN | 194350 | 01267 | 3110 | Solar | 05_09_507L2 | 10/26/2018 | 11/26/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 12/24/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 242042 | 02334 | 6.72 | Solar | 05_09_1003W1 | 07/08/2019 | 07/15/2019 | 4 | 0 | 4 | 07/16/2019 | 07/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 | 07/08/2019 | 7/8/2020 | Y | EXP | 365 | 04/10/2020 | 06/03/2020 | 52 | 0 | 52 |  |  | 6/15/2020 | Connected |  | N
National Grid | ATHOL | 309398 | 01331 | 10 | Solar | 05_07_911W25 | 09/24/2020 | 09/28/2020 | 1 | 0 | 1 | 09/29/2020 | 09/29/2020 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2020 |  | 9/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 559804 | 02038 | 3.8 | Solar | 05_07_1W2 | 10/26/2023 |  | 15 | 13 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 666989 | 02148 | 3.8 | Solar | 05_01_207W6 | 01/21/2025 | 03/11/2025 | 21 | 16 | 5 | 03/12/2025 | 03/12/2025 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 5/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | UXBRIDGE | 200996 | 01569 | 7.6 | Solar | 05_09_507L2 | 11/12/2018 | 11/16/2018 | 2 | 0 | 2 | 11/19/2018 | 11/19/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 |  | 3/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2020 | Connected |  | N
National Grid | BROCKTON | 299450 | 02301 | 6 | Solar | 05_09_1003W1 | 08/03/2020 | 08/05/2020 | 1 | 0 | 1 | 08/06/2020 | 08/06/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 348431 | 02169 | 7.6 | Solar | 05_07_911W25 | 04/20/2021 | 12/09/2021 | 3 | 0 | 3 | 04/27/2021 | 04/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 571106 | 01453 | 3.8 | Solar | 05_07_1W2 | 12/01/2023 | 02/27/2024 | 58 | 58 | 0 | 02/28/2024 | 02/28/2024 | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 722918 | 01095 | 3.8 | Solar | 05_01_207W6 | 10/22/2025 | 10/27/2025 | 2 | 0 | 2 | 11/13/2025 | 11/13/2025 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSTOWN | 300267 | 01267 | 9.84 | Solar | 05_09_507L2 | 07/14/2020 | 07/15/2020 | 0 | 0 | 0 | 07/16/2020 | 07/16/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 |  | 7/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2020 | Connected |  | N
National Grid | EASTON | 399989 | 02356 | 20 | Solar | 05_09_1003W1 | 02/10/2022 | 02/11/2022 | 1 | 0 | 1 | 02/14/2022 | 02/14/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2022 |  | 4/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2022 | Connected |  | N
National Grid | ATHOL | 471429 | 01331 | 166.6 | Solar | 05_07_911W25 | 02/01/2023 | 08/11/2023 | 131 | 121 | 10 | 08/14/2023 | 08/14/2023 | 286 | 268 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 586029 | 02038 | 3.19 | Solar | 05_07_1W2 | 02/06/2024 | 02/09/2024 | 3 | 0 | 3 | 02/12/2024 | 02/12/2024 | 171 | 148 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 729074 | 02148 | 7.6 | Solar | 05_01_207W6 | 11/04/2025 | 11/07/2025 | 3 | 0 | 3 | 11/10/2025 | 11/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITINSVILLE | 320388 | 01588 | 3.8 | Solar | 05_09_507L2 | 12/15/2020 | 12/18/2020 | 2 | 0 | 2 | 12/21/2020 | 12/21/2020 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2021 | 12/15/2020 | 10/6/2022 | Y | EXP | 365 | 07/29/2021 | 09/10/2021 | 42 | 3 | 39 |  |  | 9/28/2021 | Connected |  | N
National Grid | BROCKTON | 473079 | 02301 | 10 | Solar | 05_09_1003W1 | 11/07/2022 | 11/10/2022 | 3 | 0 | 3 | 11/14/2022 | 11/14/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2022 | 11/07/2022 | 2/15/2024 | Y | EXP | 365 | 02/02/2023 | 02/14/2023 | 13 | 0 | 13 |  |  | 6/28/2023 | Connected |  | Y
National Grid | QUINCY | 476015 | 02169 | 6 | Solar | 05_07_911W25 | 01/13/2023 | 01/17/2023 | 1 | 0 | 1 | 01/18/2023 | 01/18/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 | 01/13/2023 | 11/17/2024 | Y | EXP | 365 | 09/12/2023 | 10/11/2023 | 30 | 0 | 30 |  |  | 1/30/2024 | Connected |  | N
National Grid | LEOMINSTER | 637734 | 01453 | 2.32 | Solar | 05_07_1W2 | 10/09/2024 | 10/31/2024 | 6 | 2 | 4 | 11/01/2024 | 11/01/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/09/2024 | 1/7/2026 | Y | EXP | 365 | 04/15/2025 | 10/10/2025 | 179 | 0 | 179 |  |  | 10/17/2025 | Connected |  | N
National Grid | WILBRAHAM | 741523 | 01095 | 3.8 | Solar | 05_01_210L1 | 12/20/2025 | 12/24/2025 | 2 | 0 | 2 | 01/15/2026 | 01/15/2026 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WILLIAMSTOWN | 415891 | 01267 | 15.2 | Solar | 05_09_507L2 | 03/07/2022 | 03/08/2022 | 1 | 0 | 1 | 03/09/2022 | 03/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2022 |  | 4/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2022 | Connected |  | N
National Grid | BROCKTON | 528161 | 02301 | 0 | Solar | 05_09_1003W1 | 05/22/2023 | 05/24/2023 | 2 | 0 | 2 | 05/25/2023 | 05/25/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 494765 | 02169 | 10 | Solar | 05_07_911W25 | 02/10/2023 | 02/13/2023 | 1 | 0 | 1 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 02/10/2023 | 5/23/2024 | Y | EXP | 365 | 05/12/2023 | 05/23/2023 | 12 | 0 | 12 |  |  | 6/10/2023 | Connected |  | N
National Grid | LEOMINSTER | 639649 | 01453 | 5.76 | Solar | 05_07_1W2 | 09/12/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 | 09/12/2024 | 10/8/2025 | Y | EXP | 365 | 11/21/2024 | 01/20/2025 | 61 | 0 | 61 |  |  | 1/23/2025 | Connected |  | N
National Grid | WILBRAHAM | 742750 | 01095 | 5.584 | Solar | 05_01_210L1 | 01/08/2026 | 01/15/2026 | 4 | 2 | 2 | 01/16/2026 | 01/16/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WILLIAMSTOWN | 465488 | 01267 | 6.96 | Solar | 05_09_507L2 | 10/11/2022 | 10/13/2022 | 2 | 0 | 2 | 10/14/2022 | 10/14/2022 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/11/2022 | 2/9/2024 | Y | EXP | 365 | 02/03/2023 | 02/08/2023 | 6 | 0 | 6 |  |  | 2/14/2023 | Connected |  | N
National Grid | BROCKTON | 602572 | 02301 | 10 | Solar | 05_09_1003W1 | 04/08/2024 | 05/09/2024 | 23 | 19 | 4 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 |  | 6/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2024 | Connected |  | N
National Grid | QUINCY | 527571 | 02169 | 6 | Solar | 05_07_911W25 | 06/08/2023 | 06/26/2023 | 11 | 8 | 3 | 06/27/2023 | 06/27/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 655173 | 01453 | 7.6 | Solar | 05_07_1W2 | 11/19/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | WILBRAHAM | 754901 | 01095 | 19 | Solar | 05_01_210L1 | 03/05/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WILLIAMSTOWN | 511047 | 01267 | 6 | Solar | 05_09_507L2 | 04/04/2023 | 04/10/2023 | 5 | 1 | 4 | 04/11/2023 | 04/11/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2023 | 04/04/2023 | 6/29/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2024 | Connected |  | Y
National Grid | BROCKTON | 609933 | 02301 | 25 | Solar | 05_09_1003W1 | 05/09/2024 | 05/24/2024 | 11 | 9 | 2 | 05/28/2024 | 05/28/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N
National Grid | QUINCY | 576593 | 02169 | 2.32 | Solar | 05_07_911W25 | 12/19/2023 | 12/27/2023 | 4 | 2 | 2 | 12/28/2023 | 12/28/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2024 |  | 2/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | LEOMINSTER | 655168 | 01453 | 5.76 | Solar | 05_07_1W2 | 11/19/2024 | 02/11/2025 | 36 | 33 | 3 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 754832 | 01095 | 15.2 | Solar | 05_01_210L1 | 03/05/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WILLIAMSTOWN | 513503 | 01267 | 10 | Solar | 05_09_507L2 | 04/03/2023 |  | 135 | 119 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 649031 | 02301 | 3.48 | Solar | 05_09_1003W1 | 10/29/2024 | 11/19/2024 | 9 | 5 | 4 | 11/20/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 | 10/29/2024 | 1/8/2026 | Y | EXP | 365 | 04/15/2025 | 10/10/2025 | 179 | 0 | 179 |  |  | 12/31/2025 | Connected |  | N
National Grid | QUINCY | 582938 | 02169 | 5.8 | Solar | 05_07_911W25 | 02/01/2024 | 02/06/2024 | 3 | 0 | 3 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/01/2024 | 4/19/2025 | Y | EXP | 365 | 06/22/2024 | 07/09/2024 | 18 | 0 | 18 |  |  | 7/13/2024 | Connected |  | N
National Grid | LEOMINSTER | 657457 | 01453 | 11.4 | Solar | 05_07_1W2 | 12/03/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | WILBRAHAM | 174640 | 01095 | 1720 | Solar | 05_01_210L1 | 12/03/2013 | 12/03/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2013 | 01/03/2014 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2015 | 12/03/2013 | 12/31/2016 | Y | STD | 477 | 11/30/2016 | 01/09/2017 | 26 | 0 | 26 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | WILLIAMSTOWN | 520047 | 01267 | 12.025 | Solar | 05_09_507L2 | 04/18/2023 |  | 17 | 13 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 692485 | 02301 | 7.8 | Solar | 05_09_1003W1 | 05/18/2025 | 05/23/2025 | 5 | 1 | 4 | 05/27/2025 | 05/27/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | QUINCY | 598320 | 02169 | 10 | Solar | 05_07_911W25 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 13 | 11 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 03/26/2024 | 5/23/2025 | Y | EXP | 365 | 08/08/2024 | 08/26/2024 | 19 | 0 | 19 |  |  | 12/18/2024 | Connected |  | N
National Grid | LEOMINSTER | 716123 | 01453 | 7.98 | Solar | 05_07_1W2 | 09/08/2025 | 09/11/2025 | 2 | 0 | 2 | 09/12/2025 | 09/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | HAMPDEN | 175466 | 01036 | 150 | Solar | 05_01_210L1 | 09/24/2014 | 09/24/2014 | 7 | 0 | 7 | 10/06/2014 | 10/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2014 |  | 1/30/2015 | N | EXP | 15 |  |  | 0 | 0 | 0 | 1/30/2015 | 1/30/2015 | 2/25/2015 | Connected |  | N
National Grid | WILLIAMSTOWN | 587628 | 01267 | 8.19 | Solar | 05_09_507L2 | 02/13/2024 | 02/16/2024 | 3 | 1 | 2 | 02/20/2024 | 02/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 703233 | 02301 | 13.36 | Solar | 05_09_1003W1 | 07/11/2025 | 08/19/2025 | 3 | 1 | 2 | 08/29/2025 | 08/29/2025 | 41 | 27 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | QUINCY | 606725 | 02189 | 1275 | Solar | 05_07_911W25 | 06/17/2024 | 09/06/2024 | 55 | 51 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/09/2024 | 10/04/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 723086 | 01453 | 17.6 | Solar | 05_07_1W2 | 09/30/2025 | 10/08/2025 | 5 | 0 | 5 | 10/09/2025 | 10/09/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | WILBRAHAM | 175821 | 01095 | 5 | Solar | 05_01_210L1 | 07/31/2015 | 07/31/2015 | 2 | 2 | 0 | 08/05/2015 | 08/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2015 | 07/31/2015 | 8/8/2016 | Y | EXP | 356 |  |  | 0 | 0 | 0 | 8/18/2015 | 8/18/2015 | 6/17/2016 | Connected |  | N
National Grid | WILLIAMSTOWN | 600823 | 01267 | 6.96 | Solar | 05_09_507L2 | 04/05/2024 | 04/12/2024 | 6 | 4 | 2 | 04/16/2024 | 04/16/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  | 5/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | BROCKTON | 177195 | 02301 | 4000 | Diesel | 05_09_1003W2 | 11/01/2016 | 11/01/2016 | 28 | 28 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2016 | 01/25/2017 | 28 | 16 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2017 | 11/01/2016 | 3/6/2027 | Y | STD | 1 | 07/13/2019 | 03/27/2020 | 257 | 0 | 257 |  |  |  | Completion Documents |  | N
National Grid | QUINCY | 608967 | 02169 | 9.765 | Solar | 05_07_911W25 | 05/06/2024 | 08/13/2024 | 52 | 52 | 0 | 08/14/2024 | 08/14/2024 | 112 | 25 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 175310 | 01463 | 129 | Solar | 05_07_1W3 | 06/27/2014 | 06/27/2014 | 6 | 1 | 5 | 07/09/2014 | 07/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2014 |  | 11/28/2014 | N | EXP | 115 |  |  | 0 | 0 | 0 | 1/23/2015 | 1/23/2015 | 1/29/2015 | Connected |  | N
National Grid | WILBRAHAM | 176061 | 01095 | 900 | Solar | 05_01_210L1 | 03/27/2015 | 03/27/2015 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2015 | 05/05/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2016 | 03/27/2015 | 8/8/2015 | Y | STD | 156 | 11/30/2016 | 01/09/2017 | 26 | 0 | 26 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | WILLIAMSTOWN | 636009 | 01267 | 3.8 | Solar | 05_09_507L2 | 08/28/2024 | 09/23/2024 | 4 | 0 | 4 | 09/24/2024 | 09/24/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 | 08/28/2024 | 11/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2025 | Connected |  | N
National Grid | BROCKTON | 726594 | 02301 | 249 | Solar | 05_09_1003W2 | 10/16/2025 | 11/12/2025 | 15 | 6 | 9 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | QUINCY | 650417 | 02169 | 5.76 | Solar | 05_07_911W25 | 10/30/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 564935 | 01827 | 6 | Solar | 05_07_1W3 | 10/24/2023 | 10/26/2023 | 2 | 1 | 1 | 10/27/2023 | 10/27/2023 | 34 | 21 | 13 | 01/18/2024 | 02/21/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 02/21/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 1/24/2024 |  | 2/7/2025 | N | EXP | 365 | 02/15/2024 | 03/11/2024 | 26 | 0 | 26 |  |  | 4/1/2024 | Connected |  | N
National Grid | WILBRAHAM | 176231 | 01095 | 24 | Solar | 05_01_210L1 | 02/13/2015 | 02/13/2015 | 4 | 0 | 4 | 02/23/2015 | 02/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2015 |  | 6/30/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 3/10/2015 | 3/10/2015 | 8/19/2015 | Connected |  | N
National Grid | WILLIAMSTOWN | 650884 | 01267 | 22.8 | Solar | 05_09_507L2 | 11/08/2024 | 11/20/2024 | 7 | 5 | 2 | 11/21/2024 | 11/21/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2025 | Connected |  | N
National Grid | BROCKTON | 174636 | 02301 | 4500 | Solar | 05_09_1003W2 | 05/13/2013 | 05/13/2013 | 219 | 211 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 653228 | 02169 | 10 | Solar | 05_07_911W25 | 11/08/2024 | 11/25/2024 | 8 | 5 | 3 | 11/26/2024 | 11/26/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | DUNSTABLE | 617593 | 01827 | 2.9 | Solar | 05_07_1W3 | 06/13/2024 | 07/23/2024 | 18 | 15 | 3 | 07/24/2024 | 07/24/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 06/13/2024 | 8/8/2025 | Y | EXP | 365 | 10/11/2024 | 10/23/2024 | 13 | 0 | 13 |  |  |  | Withdrawn |  | Y
National Grid | HAMPDEN | 176229 | 01036 | 17.6 | Solar | 05_01_210L1 | 02/11/2015 | 02/11/2015 | 4 | 2 | 2 | 02/19/2015 | 02/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2015 |  | 6/30/2015 | N | EXP | 13 |  |  | 0 | 0 | 0 | 10/1/2015 | 10/1/2015 | 4/12/2016 | Connected |  | N
National Grid | WILLIAMSTOWN | 665643 | 01267 | 10 | Solar | 05_09_507L2 | 01/14/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 01/14/2025 | 4/11/2026 | Y | EXP | 365 | 06/19/2025 | 02/13/2026 | 240 | 0 | 240 |  |  | 11/24/2025 | Connected |  | N
National Grid | BROCKTON | 174841 | 02301 | 3000 | Solar | 05_09_1003W2 | 10/07/2011 | 10/07/2011 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2011 | 02/24/2012 | 49 | 0 | 49 |  |  | 0 | 0 | 0 | 04/30/2014 | 02/06/2015 | 192 | 0 | 192 |  |  | 7/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 654969 | 02169 | 3.8 | Solar | 05_07_911W25 | 11/20/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/20/2024 | 2/19/2026 | Y | EXP | 365 | 04/24/2025 | 05/29/2025 | 36 | 0 | 36 |  |  | 6/12/2025 | Connected |  | N
National Grid | PEPPERELL | 174868 | 01463 | 420 | Solar | 05_07_1W4 | 09/06/2012 | 09/06/2012 | 7 | 0 | 7 | 09/18/2012 | 09/18/2012 | 351 | 0 | 351 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2013 |  | 12/11/2012 | N | EXP | 48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 176277 | 01095 | 20 | Solar | 05_01_210L1 | 05/05/2015 | 05/05/2015 | 50 | 50 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSTOWN | 688265 | 01267 | 10 | Solar | 05_09_507L2 | 04/29/2025 | 06/24/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 8/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175055 | 02301 | 2000 | Wind | 05_09_1003W2 | 10/10/2012 | 10/10/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/3/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 657633 | 02169 | 10 | Solar | 05_07_911W25 | 11/29/2024 | 02/06/2025 | 13 | 8 | 5 | 02/07/2025 | 02/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 176985 | 01879 | 466.2 | Solar | 05_07_1W4 | 03/09/2017 | 03/09/2017 | 12 | 12 | 0 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2017 |  | 3/15/2018 | N | EXP | 346 |  |  | 0 | 0 | 0 | 12/7/2017 | 12/7/2017 | 12/12/2017 | Connected |  | N
National Grid | WILBRAHAM | 176299 | 01095 | 300 | Solar | 05_01_210L1 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 | 09/14/2015 | 09/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 | 09/11/2015 | 9/19/2016 | Y | EXP | 299 |  |  | 0 | 0 | 0 | 11/25/2015 | 11/25/2015 | 5/2/2016 | Connected |  | N
National Grid | WILLIAMSTOWN | 752954 | 01267 | 11.5 | Solar | 05_09_507L2 | 02/24/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 175549 | 02301 | 16.125 | Solar | 05_09_1003W2 | 04/11/2014 | 04/11/2014 | 5 | 0 | 5 | 04/22/2014 | 04/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2014 |  | 9/30/2014 | N | EXP | 132 |  |  | 0 | 0 | 0 | 7/30/2014 | 7/30/2014 | 9/8/2014 | Connected |  | N
National Grid | QUINCY | 696488 | 02169 | 13.3 | Solar | 05_07_911W25 | 06/09/2025 | 07/28/2025 | 3 | 0 | 3 | 08/01/2025 | 08/01/2025 | 90 | 77 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 328052 | 01879 | 13.8 | Solar | 05_07_1W4 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2021 | Connected |  | N
National Grid | WILBRAHAM | 176396 | 01095 | 10 | Solar | 05_01_210L1 | 03/10/2016 | 03/10/2016 | 5 | 5 | 0 | 03/17/2016 | 03/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2016 | 03/10/2016 | 3/15/2017 | Y | EXP | 348 | 09/23/2016 | 11/08/2016 | 31 | 0 | 31 | 6/30/2016 | 6/30/2016 | 7/11/2016 | Connected |  | N
National Grid | WILLIAMSTOWN | 630493 | 01267 | 120 | Solar | 05_09_507L3 | 08/16/2024 | 09/25/2024 | 27 | 19 | 8 | 09/26/2024 | 09/26/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  | 5/9/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BROCKTON | 175835 | 02301 | 28 | Solar | 05_09_1003W2 | 03/03/2015 | 03/03/2015 | 4 | 0 | 4 | 03/10/2015 | 03/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2015 |  | 7/15/2015 | N | EXP | 99 |  |  | 0 | 0 | 0 | 4/24/2015 | 4/24/2015 | 10/4/2016 | Connected |  | N
National Grid | QUINCY | 710760 | 02169 | 7.6 | Solar | 05_07_911W25 | 08/08/2025 | 08/12/2025 | 2 | 0 | 2 | 08/13/2025 | 08/13/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 531634 | 01827 | 10 | Solar | 05_07_1W4 | 07/18/2023 | 07/19/2023 | 1 | 0 | 1 | 07/20/2023 | 07/20/2023 | 19 | 0 | 19 | 09/06/2023 | 09/22/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 09/22/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 9/21/2023 |  | 11/26/2024 | N | EXP | 365 | 11/02/2023 | 12/08/2023 | 37 | 0 | 37 |  |  | 12/18/2023 | Connected |  | N
National Grid | HAMPDEN | 176728 | 01036 | 40 | Solar | 05_01_210L1 | 04/25/2016 | 04/25/2016 | 3 | 3 | 0 | 04/29/2016 | 04/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2016 | 04/25/2016 | 5/1/2017 | Y | EXP | 361 | 07/19/2016 | 09/12/2016 | 38 | 0 | 38 | 1/5/2017 | 1/5/2017 | 1/5/2017 | Connected |  | N
National Grid | WILLIAMSTOWN | 670350 | 01267 | 180 | Solar | 05_09_507L3 | 04/14/2025 | 07/17/2025 | 64 | 54 | 10 | 07/18/2025 | 07/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BROCKTON | 176918 | 02301 | 316 | Solar | 05_09_1003W2 | 05/05/2016 | 05/05/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 470 | 470 | 0 | 06/24/2016 | 07/28/2016 | 24 | 24 | 0 |  |  | 0 | 0 | 0 |  | 07/28/2016 | 24 | 24 | 0 |  |  | 0 | 0 | 0 |  |  | 6/11/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 654666 | 02169 | 3.8 | Solar | 05_07_911W56 | 11/19/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 11/19/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TYNGSBORO | 690107 | 01879 | 17.6 | Solar | 05_07_1W4 | 05/12/2025 | 05/19/2025 | 5 | 0 | 5 | 05/20/2025 | 05/20/2025 | 40 | 20 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/12/2025 | 8/4/2026 | Y | EXP | 365 | 09/06/2025 | 11/21/2025 | 77 | 0 | 77 |  |  | 11/24/2025 | Connected |  | N
National Grid | WILBRAHAM | 176797 | 01095 | 6 | Solar | 05_01_210L1 | 02/25/2016 | 02/25/2016 | 1 | 1 | 0 | 02/29/2016 | 02/29/2016 | 291 | 0 | 291 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/25/2016 | 5/31/2017 | Y | EXP | 422 | 03/16/2017 | 05/08/2017 | 36 | 0 | 36 | 4/4/2016 | 4/4/2016 |  | Withdrawn |  | N
National Grid | LANESBOROUGH | 731801 | 01237 | 3.8 | Solar | 05_09_507L3 | 11/05/2025 | 11/06/2025 | 1 | 0 | 1 | 12/03/2025 | 12/03/2025 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 177948 | 02301 | 33.3 | Solar | 05_09_1003W2 | 08/21/2017 | 08/21/2017 | 59 | 58 | 1 | 11/27/2017 | 11/27/2017 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 8/28/2018 | N | EXP | 274 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 712382 | 02169 | 15.2 | Solar | 05_07_911W56 | 08/15/2025 | 08/18/2025 | 1 | 0 | 1 | 08/19/2025 | 08/19/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DUNSTABLE | 587954 | 01827 | 325 | Natural Gas | 05_07_1W5 | 02/26/2024 | 08/06/2024 | 112 | 104 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2024 | 08/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 | 02/26/2024 | 8/30/2026 | Y | STD | 194 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WILBRAHAM | 177009 | 01095 | 18 | Solar | 05_01_210L1 | 10/13/2016 | 10/13/2016 | 1 | 1 | 0 | 10/17/2016 | 10/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2016 |  | 10/19/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 1/5/2017 | 1/5/2017 | 1/5/2017 | Connected |  | N
National Grid | LANESBOROUGH | 177110 | 01237 | 1120 | Solar | 05_09_507L3 | 08/03/2016 | 08/03/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2016 | 09/14/2016 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/10/2019 | N | STD | 66 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 178121 | 02301 | 2058 | Solar | 05_09_1003W2 | 05/12/2017 | 05/12/2017 | 168 | 167 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/17/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 715099 | 02169 | 10 | Solar | 05_07_911W56 | 08/27/2025 | 10/28/2025 | 2 | 0 | 2 | 10/29/2025 | 10/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DUNSTABLE | 175421 | 01827 | 96 | Solar | 05_07_1W5 | 07/14/2014 | 07/14/2014 | 6 | 3 | 3 | 07/23/2014 | 07/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2014 |  | 10/31/2014 | N | EXP | 77 |  |  | 0 | 0 | 0 | 9/16/2014 | 9/16/2014 | 3/18/2016 | Connected |  | N
National Grid | WILBRAHAM | 177032 | 01095 | 10 | Solar | 05_01_210L1 | 07/26/2016 | 07/26/2016 | 3 | 3 | 0 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2016 | 07/26/2016 | 7/31/2017 | Y | EXP | 36 | 12/29/2016 | 01/05/2017 | 4 | 0 | 4 | 2/16/2017 | 2/16/2017 | 2/16/2017 | Connected |  | N
National Grid | LANESBOROUGH | 177109 | 01237 | 640 | Solar | 05_09_507L3 | 08/03/2016 | 08/03/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2016 | 09/14/2016 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/10/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 178140 | 02301 | 17.6 | Solar | 05_09_1003W2 | 03/22/2018 | 03/22/2018 | 15 | 0 | 15 | 04/13/2018 | 04/13/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2018 |  | 4/15/2020 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  | 5/6/2020 | Connected |  | N
National Grid | QUINCY | 723885 | 02169 | 10 | Solar | 05_07_911W56 | 10/03/2025 | 12/03/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 31 | 17 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | DUNSTABLE | 178017 | 01827 | 15.2 | Solar | 05_07_1W5 | 06/29/2017 | 06/29/2017 | 4 | 3 | 1 | 07/06/2017 | 07/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2017 |  | 7/4/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 3/6/2018 | 3/6/2018 | 3/23/2018 | Connected |  | N
National Grid | WILBRAHAM | 177416 | 01095 | 995 | Landfill Gas | 05_01_210L1 | 09/15/2016 | 09/15/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2016 | 10/19/2016 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/20/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSTOWN | 177108 | 01267 | 1600 | Solar | 05_09_507L3 | 08/03/2016 | 08/03/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2016 | 09/14/2016 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/10/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 178248 | 02301 | 21.44 | Solar | 05_09_1003W2 | 03/27/2018 | 03/27/2018 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/2/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 736731 | 02169 | 7.6 | Solar | 05_07_911W56 | 11/26/2025 | 11/28/2025 | 2 | 0 | 2 | 01/22/2026 | 01/22/2026 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | TYNGSBORO | 248196 | 01879 | 7.6 | Solar | 05_07_1W5 | 08/12/2019 | 08/12/2019 | 0 | 0 | 0 | 08/13/2019 | 08/13/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2019 | 08/12/2019 | 4/24/2020 | Y | EXP | 247 | 10/23/2019 | 11/09/2019 | 16 | 0 | 16 |  |  | 11/14/2019 | Connected |  | N
National Grid | WILBRAHAM | 177490 | 01095 | 3.8 | Solar | 05_01_210L1 | 09/23/2016 | 09/23/2016 | 3 | 3 | 0 | 09/29/2016 | 09/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 | 09/23/2016 | 10/1/2017 | Y | EXP | 361 | 04/10/2017 | 04/25/2017 | 10 | 0 | 10 | 5/17/2017 | 5/17/2017 | 5/17/2017 | Connected |  | N
National Grid | WILLIAMSTOWN | 177105 | 01267 | 225 | Solar | 05_09_507L3 | 05/27/2016 | 05/27/2016 | 3 | 3 | 0 | 06/03/2016 | 06/03/2016 | 397 | 0 | 397 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2016 |  | 6/5/2017 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 178738 | 02301 | 50 | Solar | 05_09_1003W2 | 02/12/2018 | 02/12/2018 | 10 | 0 | 10 | 03/27/2018 | 03/27/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2019 |  | 2/18/2019 | N | EXP | 24 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 741113 | 02169 | 21.28 | Solar | 05_07_911W56 | 12/18/2025 | 01/12/2026 | 15 | 13 | 2 | 01/13/2026 | 01/13/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DUNSTABLE | 311801 | 01827 | 7.6 | Solar | 05_07_1W5 | 09/10/2020 | 09/11/2020 | 0 | 0 | 0 | 09/14/2020 | 09/14/2020 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2020 |  | 10/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2020 | Connected |  | N
National Grid | WILBRAHAM | 177812 | 01095 | 15.2 | Solar | 05_01_210L1 | 03/31/2017 | 03/31/2017 | 5 | 2 | 3 | 04/07/2017 | 04/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 4/5/2018 | N | EXP | 36 |  |  | 0 | 0 | 0 | 8/22/2017 | 8/22/2017 | 8/22/2017 | Connected |  | N
National Grid | WILLIAMSTOWN | 177679 | 01267 | 300 | Natural Gas | 05_09_507L3 | 07/24/2017 | 07/24/2017 | 13 | 13 | 0 | 08/15/2017 | 08/15/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2017 |  | 7/30/2018 | N | EXP | 332 |  |  | 0 | 0 | 0 |  |  | 10/10/2018 | Connected |  | N
National Grid | BROCKTON | 200518 | 02301 | 60 | Solar | 05_09_1003W2 | 11/09/2018 |  | 42 | 33 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 743373 | 02169 |  | Battery Add-On | 05_07_911W56 | 01/05/2026 | 01/06/2026 | 3 | 0 | 3 | 01/22/2026 | 01/22/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | DUNSTABLE | 313212 | 01827 | 10 | Solar | 05_07_1W5 | 09/16/2020 | 09/17/2020 | 0 | 0 | 0 | 09/18/2020 | 09/18/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 177964 | 01095 | 6 | Solar | 05_01_210L1 | 02/25/2016 | 02/25/2016 | 0 | 0 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/25/2016 | 4/26/2018 | Y | EXP | 752 | 03/16/2017 | 05/08/2017 | 36 | 0 | 36 | 4/21/2017 | 4/21/2017 | 6/20/2017 | Connected |  | N
National Grid | WILLIAMSTOWN | 178566 | 01267 | 15.2 | Solar | 05_09_507L3 | 12/07/2017 | 12/07/2017 | 0 | 0 | 0 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 12/13/2018 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 11/12/2019 | Connected |  | N
National Grid | BROCKTON | 200510 | 02302 | 18 | Solar | 05_09_1003W2 | 11/09/2018 | 03/14/2019 | 2 | 2 | 0 | 03/15/2019 | 03/15/2019 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2019 |  | 10/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2021 | Connected |  | N
National Grid | QUINCY | 749466 | 02169 | 11.5 | Solar | 05_07_911W56 | 02/05/2026 | 02/06/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | TYNGSBORO | 350545 | 01879 | 9.86 | Solar | 05_07_1W5 | 04/14/2021 | 04/15/2021 | 1 | 1 | 0 | 04/16/2021 | 04/16/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 |  | 4/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2021 | Connected |  | N
National Grid | WILBRAHAM | 178622 | 01095 | 7.6 | Solar | 05_01_210L1 | 02/01/2018 | 02/01/2018 | 19 | 0 | 19 | 03/02/2018 | 03/02/2018 | 189 | 0 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2018 |  | 2/7/2019 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSTOWN | 190105 | 01267 | 7.6 | Solar | 05_09_507L3 | 07/06/2018 | 08/28/2018 | 21 | 0 | 21 | 08/29/2018 | 08/29/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2018 |  | 10/21/2019 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  | 9/17/2019 | Connected |  | N
National Grid | BROCKTON | 208997 | 02302 | 57.64 | Solar | 05_09_1003W2 | 02/08/2019 | 03/25/2019 | 30 | 25 | 5 | 03/26/2019 | 03/26/2019 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2019 |  | 2/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2021 | Connected |  | N
National Grid | QUINCY | 175260 | 02169 | 8 | Solar | 05_07_911W56 | 01/09/2015 | 01/09/2015 | 13 | 11 | 2 | 01/30/2015 | 01/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2015 |  | 5/31/2015 | N | EXP | 19 |  |  | 0 | 0 | 0 | 3/5/2015 | 3/5/2015 | 6/1/2015 | Connected |  | N
National Grid | DUNSTABLE | 419001 | 01827 | 10 | Solar | 05_07_1W5 | 06/02/2022 | 07/06/2022 | 21 | 20 | 1 | 07/07/2022 | 07/07/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2022 | 06/02/2022 | 9/16/2023 | Y | EXP | 365 | 08/27/2022 | 09/14/2022 | 19 | 0 | 19 |  |  | 1/19/2023 | Connected |  | N
National Grid | WILBRAHAM | 184039 | 01095 | 4500 | Solar | 05_01_210L1 | 04/28/2018 | 04/28/2018 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2018 | 07/16/2018 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2019 | 04/28/2018 | 12/31/2020 | Y | STD | 415 | 02/19/2020 | 08/01/2020 | 163 | 0 | 163 |  |  | 12/31/2020 | Connected |  | N
National Grid | LANESBOROUGH | 301119 | 01237 | 7.6 | Solar | 05_09_507L3 | 07/14/2020 | 07/22/2020 | 5 | 0 | 5 | 07/23/2020 | 07/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 |  | 8/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2020 | Connected |  | N
National Grid | BROCKTON | 232178 | 02302 | 0 | Solar | 05_09_1003W2 | 05/30/2019 | 05/31/2019 | 0 | 0 | 0 | 06/03/2019 | 06/03/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2019 |  | 5/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2020 | Connected |  | N
National Grid | QUINCY | 175973 | 02169 | 250 | Solar | 05_07_911W56 | 08/10/2015 | 08/10/2015 | 3 | 3 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2015 |  | 8/18/2016 | N | EXP | 339 |  |  | 0 | 0 | 0 | 10/6/2015 | 10/6/2015 | 12/11/2015 | Connected |  | N
National Grid | PEPPERELL | 528713 | 01463 | 20 | Solar | 05_07_1W5 | 05/24/2023 | 05/25/2023 | 1 | 0 | 1 | 05/26/2023 | 05/26/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 |  | 9/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2023 | Connected |  | N
National Grid | WILBRAHAM | 190303 | 01095 | 3.8 | Solar | 05_01_210L1 | 07/10/2018 | 09/11/2018 | 14 | 14 | 0 | 09/12/2018 | 09/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSTOWN | 335397 | 01267 | 7.6 | Solar | 05_09_507L3 | 01/11/2021 | 01/15/2021 | 3 | 0 | 3 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/11/2021 |  | Y | EXP | 365 | 06/25/2021 | 08/06/2021 | 41 | 0 | 41 |  |  | 9/9/2021 | Connected |  | N
National Grid | BROCKTON | 266810 | 02302 | 0 | Other | 05_09_1003W2 | 03/11/2020 |  | 104 | 104 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 176588 | 02169 | 3 | Solar | 05_07_911W56 | 04/11/2016 | 04/11/2016 | 2 | 2 | 0 | 04/13/2016 | 04/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/11/2016 | 4/16/2017 | Y | EXP | 355 |  |  | 0 | 0 | 0 | 9/23/2016 | 9/23/2016 | 9/28/2016 | Connected |  | N
National Grid | DUNSTABLE | 573913 | 01827 | 7.25 | Solar | 05_07_1W5 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 222601 | 01095 | 0 | Solar | 05_01_210L1 | 04/25/2019 | 05/06/2019 | 6 | 0 | 6 | 05/07/2019 | 05/07/2019 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 |  | 8/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSTOWN | 345779 | 01267 | 140 | Solar | 05_09_507L3 | 03/09/2021 | 03/23/2021 | 9 | 0 | 9 | 03/24/2021 | 03/24/2021 | 53 | 28 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2021 |  | 9/22/2023 | N | EXP | 8 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 268691 | 02302 | 0 | Battery Add-On | 05_09_1003W2 | 02/12/2021 | 12/19/2019 | 0 | 0 | 0 | 02/16/2021 | 02/16/2021 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2019 |  | 8/1/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 176666 | 02169 | 15.48 | Solar | 05_07_911W56 | 10/19/2015 | 10/19/2015 | 2 | 2 | 0 | 10/23/2015 | 10/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2015 |  | 10/26/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/27/2016 | 7/27/2016 | 8/1/2016 | Connected |  | N
National Grid | DUNSTABLE | 576061 | 01827 | 8.41 | Solar | 05_07_1W5 | 12/06/2023 | 01/16/2024 | 26 | 24 | 2 | 01/17/2024 | 01/17/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 274504 | 01095 | 6.38 | Solar | 05_01_210L1 | 03/12/2020 | 03/13/2020 | 1 | 1 | 0 | 03/16/2020 | 03/16/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2020 | 03/12/2020 | 3/12/2021 | Y | EXP | 365 | 06/30/2020 | 07/16/2020 | 16 | 0 | 16 |  |  | 7/20/2020 | Connected |  | N
National Grid | WILLIAMSTOWN | 353082 | 01267 | 433.3 | Solar | 05_09_507L3 | 06/08/2021 | 08/04/2021 | 40 | 30 | 10 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 292650 | 02302 | 0 | Solar | 05_09_1003W2 | 05/21/2020 | 05/22/2020 | 0 | 0 | 0 | 05/26/2020 | 05/26/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 176679 | 02169 | 10 | Solar | 05_07_911W56 | 01/04/2016 | 01/04/2016 | 0 | 0 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 |  | 1/11/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 | 7/25/2016 | 7/25/2016 | 7/26/2016 | Connected |  | N
National Grid | DUNSTABLE | 590352 | 01827 | 7.6 | Solar | 05_07_1W5 | 02/15/2024 | 02/20/2024 | 2 | 0 | 2 | 02/21/2024 | 02/21/2024 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 5/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2024 | Connected |  | N
National Grid | WILBRAHAM | 308268 | 01095 | 15.36 | Solar | 05_01_210L1 | 08/22/2020 | 08/24/2020 | 0 | 0 | 0 | 08/25/2020 | 08/25/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 | 08/22/2020 | 9/10/2021 | Y | EXP | 365 | 05/05/2021 | 05/24/2021 | 19 | 0 | 19 |  |  | 8/30/2021 | Connected |  | N
National Grid | WILLIAMSTOWN | 386258 | 01267 | 7.6 | Solar | 05_09_507L3 | 10/04/2021 | 11/09/2021 | 25 | 18 | 7 | 11/10/2021 | 11/10/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 | 10/04/2021 | 6/5/2023 | Y | EXP | 365 | 04/15/2022 | 04/19/2022 | 5 | 0 | 5 |  |  | 6/29/2022 | Connected |  | N
National Grid | BROCKTON | 386281 | 02302 | 0 | Solar | 05_09_1003W2 | 01/11/2022 | 01/31/2022 | 14 | 13 | 1 | 02/01/2022 | 02/01/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 |  | 11/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2022 | Connected |  | N
National Grid | QUINCY | 176774 | 02169 | 6 | Solar | 05_07_911W56 | 11/03/2015 | 11/03/2015 | 0 | 0 | 0 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2015 |  | 11/9/2016 | N | EXP | 37 |  |  | 0 | 0 | 0 | 5/6/2016 | 5/6/2016 | 5/12/2016 | Connected |  | N
National Grid | TYNGSBORO | 616166 | 01879 | 10 | Solar | 05_07_1W5 | 11/04/2024 | 11/20/2024 | 11 | 9 | 2 | 11/21/2024 | 11/21/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | WILBRAHAM | 342970 | 01095 | 11.4 | Solar | 05_01_210L1 | 02/19/2021 | 03/10/2021 | 12 | 12 | 0 | 03/11/2021 | 03/11/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2021 |  | 1/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2022 | Connected |  | N
National Grid | WILLIAMSTOWN | 386581 | 01267 | 10 | Solar | 05_09_507L3 | 11/22/2021 | 11/23/2021 | 1 | 0 | 1 | 11/24/2021 | 11/24/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/22/2021 | 10/3/2023 | Y | EXP | 365 | 07/01/2022 | 09/15/2022 | 77 | 0 | 77 |  |  | 12/22/2022 | Connected |  | N
National Grid | BROCKTON | 401601 | 02302 | 0 | Solar | 05_09_1003W2 | 02/04/2022 | 04/01/2022 | 39 | 38 | 1 | 04/04/2022 | 04/04/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2022 |  | 4/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N
National Grid | QUINCY | 176798 | 02169 | 10 | Solar | 05_07_911W56 | 02/25/2016 | 02/25/2016 | 1 | 1 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2016 | 02/25/2016 | 3/2/2017 | Y | EXP | 329 | 07/26/2016 | 08/05/2016 | 8 | 0 | 8 | 4/7/2016 | 4/7/2016 | 2/8/2017 | Connected |  | N
National Grid | DUNSTABLE | 667016 | 01827 | 10 | Solar | 05_07_1W5 | 01/31/2025 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 16 | 0 | 16 | 03/11/2025 | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 354941 | 01095 | 9.6 | Solar | 05_01_210L1 | 04/28/2021 | 04/29/2021 | 1 | 1 | 0 | 05/04/2021 | 05/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 4/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2021 | Connected |  | N
National Grid | WILLIAMSTOWN | 411592 | 01267 | 15.2 | Solar | 05_09_507L3 | 02/10/2022 | 02/14/2022 | 2 | 0 | 2 | 02/15/2022 | 02/15/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  | 7/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2022 | Connected |  | N
National Grid | BROCKTON | 406530 | 02302 | 10 | Solar | 05_09_1003W2 | 01/13/2022 | 01/24/2022 | 7 | 6 | 1 | 01/25/2022 | 01/25/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2022 |  | 2/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2022 | Connected |  | N
National Grid | QUINCY | 177250 | 02169 | 10 | Solar | 05_07_911W56 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/17/2016 | 06/17/2016 | 150 | 0 | 150 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/20/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 672397 | 01827 | 8.376 | Solar | 05_07_1W5 | 02/20/2025 | 03/13/2025 | 4 | 3 | 1 | 04/04/2025 | 04/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 | 02/20/2025 | 5/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | WILBRAHAM | 368575 | 01095 | 80 | Solar | 05_01_210L1 | 07/09/2021 | 07/23/2021 | 9 | 3 | 6 | 07/26/2021 | 07/26/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2021 |  | 10/5/2022 | N | EXP | 365 | 05/10/2022 | 05/09/2022 | 0 | 0 | 0 |  |  | 8/17/2022 | Connected |  | N
National Grid | WILLIAMSTOWN | 418321 | 01267 | 7.6 | Solar | 05_09_507L3 | 04/12/2022 | 04/13/2022 | 2 | 1 | 1 | 04/14/2022 | 04/14/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 04/12/2022 | 8/28/2023 | Y | EXP | 365 | 07/29/2022 | 08/04/2022 | 7 | 0 | 7 |  |  | 9/1/2022 | Connected |  | N
National Grid | BROCKTON | 446211 | 02302 | 5.8 | Solar | 05_09_1003W2 | 08/25/2022 | 08/29/2022 | 2 | 0 | 2 | 08/30/2022 | 08/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 | 08/25/2022 | 9/30/2024 | Y | EXP | 6 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 177555 | 02169 | 10 | Solar | 05_07_911W56 | 05/16/2017 | 05/16/2017 | 1 | 1 | 0 | 05/18/2017 | 05/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 | 05/16/2017 | 5/22/2018 | Y | EXP | 365 | 08/28/2017 | 09/09/2017 | 9 | 0 | 9 | 11/8/2017 | 11/8/2017 | 11/28/2017 | Connected |  | N
National Grid | PEPPERELL | 704480 | 01463 | 4.18 | Solar | 05_07_1W5 | 07/15/2025 | 08/26/2025 | 5 | 0 | 5 | 08/27/2025 | 08/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | WILBRAHAM | 373203 | 01095 | 15.4 | Solar | 05_01_210L1 | 07/31/2021 | 08/02/2021 | 1 | 0 | 1 | 08/03/2021 | 08/03/2021 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2021 |  | 8/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2021 | Connected |  | Y
National Grid | WILLIAMSTOWN | 434053 | 01267 | 3.8 | Solar | 05_09_507L3 | 06/13/2022 | 06/28/2022 | 10 | 8 | 2 | 06/29/2022 | 06/29/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 461061 | 02302 | 10 | Solar | 05_09_1003W2 | 10/28/2022 | 11/09/2022 | 8 | 5 | 3 | 11/10/2022 | 11/10/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2022 |  | 2/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2023 | Connected |  | N
National Grid | QUINCY | 177661 | 02169 | 16 | Solar | 05_07_911W56 | 11/13/2017 | 11/13/2017 | 64 | 64 | 0 | 02/16/2018 | 02/16/2018 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2018 |  | 11/19/2018 | N | EXP | 15 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 552146 | 01827 | 360 | Solar | 05_07_1W6 | 02/16/2024 | 05/21/2024 | 65 | 57 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2024 | 06/04/2024 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2024 | 02/16/2024 | 9/1/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | WILBRAHAM | 376595 | 01095 | 7.6 | Solar | 05_01_210L1 | 08/18/2021 | 08/24/2021 | 4 | 4 | 0 | 08/25/2021 | 08/25/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 |  | 8/23/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 446236 | 01267 | 15.2 | Solar | 05_09_507L3 | 07/22/2022 | 07/22/2022 | 0 | 0 | 0 | 07/25/2022 | 07/25/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 |  | 8/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2022 | Connected |  | N
National Grid | BROCKTON | 481070 | 02302 | 11.4 | Solar | 05_09_1003W2 | 11/29/2022 | 12/02/2022 | 3 | 1 | 2 | 12/05/2022 | 12/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2023 | 11/29/2022 | 2/15/2024 | Y | EXP | 365 | 02/02/2023 | 02/14/2023 | 13 | 0 | 13 |  |  | 3/1/2023 | Connected |  | N
National Grid | QUINCY | 177761 | 02169 | 360 | Solar | 05_07_911W56 | 08/02/2017 | 08/02/2017 | 69 | 69 | 0 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 | 08/02/2017 | 6/25/2021 | Y | STD | 57 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 731355 | 01462 | 5.76 | Solar | 05_07_1W6 | 11/04/2025 | 12/02/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WILBRAHAM | 375882 | 01095 | 9.86 | Solar | 05_01_210L1 | 08/19/2021 | 08/24/2021 | 3 | 3 | 0 | 08/25/2021 | 08/25/2021 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 |  | 10/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2021 | Connected |  | N
National Grid | WILLIAMSTOWN | 476868 | 01267 | 7.6 | Solar | 05_09_507L3 | 01/30/2023 | 02/09/2023 | 8 | 6 | 2 | 02/10/2023 | 02/10/2023 | 75 | 53 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 622797 | 02302 | 50 | Solar | 05_09_1003W2 | 07/10/2024 | 07/15/2024 | 3 | 0 | 3 | 07/16/2024 | 07/16/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2024 |  | 10/23/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 10/16/2025 | Connected |  | N
National Grid | QUINCY | 178377 | 02169 | 7.6 | Solar | 05_07_911W56 | 11/21/2017 | 11/21/2017 | 16 | 6 | 10 | 12/15/2017 | 12/15/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2017 |  | 11/27/2018 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  | 6/26/2018 | Connected |  | N
National Grid | DUNSTABLE | 738024 | 01827 | 10 | Solar | 05_07_1W6 | 12/05/2025 | 12/09/2025 | 2 | 0 | 2 | 12/10/2025 | 12/10/2025 | 55 | 35 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WILBRAHAM | 384470 | 01095 | 7.6 | Solar | 05_01_210L1 | 09/26/2021 |  | 34 | 26 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 486553 | 01267 | 15.2 | Solar | 05_09_507L3 | 12/21/2022 | 12/22/2022 | 1 | 0 | 1 | 12/23/2022 | 12/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2023 |  | 2/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2023 | Connected |  | N
National Grid | BROCKTON | 623206 | 02302 | 40 | Solar | 05_09_1003W2 | 07/11/2024 | 07/15/2024 | 2 | 0 | 2 | 07/16/2024 | 07/16/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2024 |  | 10/30/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 10/16/2025 | Connected |  | N
National Grid | QUINCY | 186717 | 02169 | 7.6 | Solar | 05_07_911W56 | 08/16/2018 | 10/01/2018 | 28 | 18 | 10 | 10/02/2018 | 10/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 08/16/2018 | 9/23/2020 | Y | EXP | 5 | 10/22/2019 | 10/30/2019 | 8 | 0 | 8 |  |  | 6/11/2020 | Connected |  | N
National Grid | PEPPERELL | 174683 | 01463 | 30 | Solar | 05_07_1W6 | 01/09/2014 | 01/09/2014 | 5 | 0 | 5 | 01/17/2014 | 01/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2014 |  | 3/31/2014 | N | EXP | 66 |  |  | 0 | 0 | 0 | 4/11/2014 | 4/11/2014 | 4/11/2014 | Connected |  | N
National Grid | WILBRAHAM | 392140 | 01095 | 240 | Solar | 05_01_210L1 | 11/02/2021 | 11/17/2021 | 10 | 0 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2022 | 11/02/2021 | 5/15/2023 | Y | STD | 9 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N
National Grid | WILLIAMSTOWN | 485815 | 01267 | 9.86 | Solar | 05_09_507L3 | 12/29/2022 | 01/03/2023 | 2 | 0 | 2 | 01/04/2023 | 01/04/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/29/2022 | 5/15/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2023 | Connected |  | N
National Grid | BROCKTON | 632270 | 02302 | 20.88 | Solar | 05_09_1003W2 | 08/13/2024 | 08/20/2024 | 5 | 3 | 2 | 08/21/2024 | 08/21/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 |  | 9/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2024 | Connected |  | N
National Grid | QUINCY | 186523 | 02169 | 10 | Solar | 05_07_911W56 | 05/29/2018 | 05/29/2018 | 8 | 0 | 8 | 08/10/2018 | 08/10/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 174682 | 01827 | 40 | Solar | 05_07_1W6 | 01/09/2014 | 01/09/2014 | 5 | 0 | 5 | 01/17/2014 | 01/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2014 |  | 3/31/2014 | N | EXP | 68 |  |  | 0 | 0 | 0 | 4/22/2014 | 4/22/2014 | 4/25/2014 | Connected |  | N
National Grid | WILBRAHAM | 397552 | 01095 | 15.2 | Solar | 05_01_210L1 | 01/04/2022 | 01/05/2022 | 1 | 0 | 1 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 491959 | 01267 | 8.7 | Solar | 05_09_507L3 | 02/02/2023 | 02/03/2023 | 1 | 0 | 1 | 02/06/2023 | 02/06/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/02/2023 | 10/23/2024 | Y | EXP | 365 | 01/31/2024 | 05/14/2024 | 105 | 0 | 105 |  |  | 5/31/2024 | Connected |  | N
National Grid | BROCKTON | 658707 | 02302 | 23 | Solar | 05_09_1003W2 | 12/09/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 | 12/09/2024 | 2/5/2026 | Y | EXP | 365 | 04/30/2025 | 06/20/2025 | 52 | 0 | 52 |  |  | 7/17/2025 | Connected |  | N
National Grid | QUINCY | 201443 | 02169 | 8.96 | Solar | 05_07_911W56 | 12/12/2018 | 02/08/2019 | 36 | 32 | 4 | 02/11/2019 | 02/11/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 | 12/12/2018 | 8/30/2019 | Y | EXP | 192 | 04/09/2019 | 05/01/2019 | 22 | 0 | 22 |  |  | 8/16/2019 | Connected |  | N
National Grid | TYNGSBORO | 175343 | 01879 | 42 | Solar | 05_07_1W6 | 07/02/2014 | 07/02/2014 | 3 | 0 | 3 | 07/09/2014 | 07/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2014 |  | 11/28/2014 | N | EXP | 115 |  |  | 0 | 0 | 0 | 1/21/2015 | 1/21/2015 | 1/30/2015 | Connected |  | N
National Grid | WILBRAHAM | 399903 | 01095 | 0 | Solar | 05_01_210L1 | 12/13/2021 | 12/20/2021 | 6 | 4 | 2 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 | 12/13/2021 | 6/8/2023 | Y | EXP | 365 | 05/26/2022 | 06/08/2022 | 14 | 0 | 14 |  |  | 7/21/2022 | Connected |  | N
National Grid | WILLIAMSTOWN | 511786 | 01267 | 15.2 | Solar | 05_09_507L3 | 03/16/2023 | 03/17/2023 | 1 | 0 | 1 | 03/20/2023 | 03/20/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2023 |  | 4/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2023 | Connected |  | N
National Grid | BROCKTON | 667018 | 02302 | 23 | Solar | 05_09_1003W2 | 01/30/2025 | 02/05/2025 | 5 | 2 | 3 | 02/06/2025 | 02/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2025 | Connected |  | N
National Grid | QUINCY | 208398 | 02169 | 7.6 | Solar | 05_07_911W56 | 02/19/2019 | 02/20/2019 | 0 | 0 | 0 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 175423 | 01827 | 195 | Solar | 05_07_1W6 | 07/14/2014 | 07/14/2014 | 6 | 2 | 4 | 07/23/2014 | 07/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2014 |  | 10/31/2014 | N | EXP | 74 |  |  | 0 | 0 | 0 | 8/29/2014 | 8/29/2014 | 1/30/2015 | Connected |  | N
National Grid | WILBRAHAM | 407710 | 01095 | 7.678 | Solar | 05_01_210L1 | 05/10/2022 | 06/21/2022 | 28 | 25 | 3 | 06/22/2022 | 06/22/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2022 | Connected |  | N
National Grid | WILLIAMSTOWN | 517065 | 01267 | 20 | Solar | 05_09_507L3 | 04/07/2023 | 04/10/2023 | 1 | 0 | 1 | 04/11/2023 | 04/11/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2023 |  | 6/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2023 | Connected |  | N
National Grid | BROCKTON | 683701 | 02302 | 0 | Battery Add-On | 05_09_1003W2 | 04/08/2025 | 04/21/2025 | 8 | 4 | 4 | 04/22/2025 | 04/22/2025 | 84 | 69 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | QUINCY | 210009 | 02169 | 6 | Solar | 05_07_911W56 | 02/15/2019 | 03/21/2019 | 8 | 0 | 8 | 03/22/2019 | 03/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2019 | 02/15/2019 | 3/30/2020 | Y | EXP | 365 | 07/27/2019 | 08/13/2019 | 17 | 0 | 17 |  |  | 9/6/2019 | Connected |  | N
National Grid | DUNSTABLE | 175633 | 01827 | 120 | Solar | 05_07_1W6 | 08/06/2014 | 08/06/2014 | 36 | 31 | 5 | 09/29/2014 | 09/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2014 |  | 12/31/2014 | N | EXP | 84 |  |  | 0 | 0 | 0 | 1/20/2015 | 1/20/2015 | 1/29/2015 | Connected |  | N
National Grid | WILBRAHAM | 410230 | 01095 | 8.64 | Solar | 05_01_210L1 | 02/23/2022 | 02/28/2022 | 3 | 0 | 3 | 03/01/2022 | 03/01/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/23/2022 | 7/28/2023 | Y | EXP | 365 | 06/04/2022 | 06/28/2022 | 24 | 0 | 24 |  |  | 1/14/2023 | Connected |  | N
National Grid | WILLIAMSTOWN | 522940 | 01267 |  | Other | 05_09_507L3 | 07/19/2023 | 10/06/2023 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2023 | 11/03/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 709928 | 02302 | 17.225 | Solar | 05_09_1003W2 | 08/06/2025 | 08/11/2025 | 3 | 0 | 3 | 08/12/2025 | 08/12/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2025 | Connected |  | N
National Grid | QUINCY | 209355 | 02170 | 12 | Solar | 05_07_911W56 | 03/21/2019 | 04/19/2019 | 21 | 21 | 0 | 04/22/2019 | 04/22/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2019 | 03/21/2019 | 11/25/2019 | Y | EXP | 215 | 09/22/2019 | 10/08/2019 | 16 | 0 | 16 |  |  | 10/29/2019 | Connected |  | N
National Grid | TYNGSBORO | 178001 | 01879 | 86.4 | Solar | 05_07_1W6 | 04/26/2017 | 04/26/2017 | 1 | 1 | 0 | 04/28/2017 | 04/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2017 | 04/26/2017 | 5/2/2018 | Y | EXP | 366 | 01/29/2018 | 02/07/2018 | 7 | 0 | 7 | 4/4/2018 | 4/4/2018 | 4/10/2018 | Connected |  | N
National Grid | WILBRAHAM | 465180 | 01095 | 15.95 | Solar | 05_01_210L1 | 10/10/2022 | 10/11/2022 | 1 | 0 | 1 | 10/12/2022 | 10/12/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2022 |  | 11/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | Y
National Grid | WILLIAMSTOWN | 523750 | 01267 | 0 | Other | 05_09_507L3 | 06/02/2023 |  | 131 | 35 | 96 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 717176 | 02302 | 5.8 | Solar | 05_09_1003W2 | 09/10/2025 | 09/16/2025 | 4 | 0 | 4 | 09/17/2025 | 09/17/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | QUINCY | 220789 | 02169 | 6 | Solar | 05_07_911W56 | 04/24/2019 | 04/29/2019 | 4 | 4 | 0 | 04/30/2019 | 04/30/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2019 | 04/24/2019 | 4/14/2020 | Y | EXP | 348 | 10/02/2019 | 10/15/2019 | 13 | 0 | 13 |  |  | 10/22/2019 | Connected |  | N
National Grid | DUNSTABLE | 650648 | 01827 | 3.19 | Solar | 05_07_1W6 | 10/29/2024 | 11/06/2024 | 3 | 0 | 3 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/29/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | WILBRAHAM | 477387 | 01095 | 7.6 | Solar | 05_01_210L1 | 11/15/2022 | 11/18/2022 | 3 | 0 | 3 | 11/21/2022 | 11/21/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  | 2/29/2024 | N | EXP | 41 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 543374 | 01267 | 15.2 | Solar | 05_09_507L3 | 07/25/2023 | 07/26/2023 | 1 | 0 | 1 | 07/27/2023 | 07/27/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 1/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2024 | Connected |  | N
National Grid | BROCKTON | 719924 | 02302 | 19.2 | Solar | 05_09_1003W2 | 09/18/2025 | 09/26/2025 | 5 | 0 | 5 | 09/29/2025 | 09/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | QUINCY | 215043 | 02170 | 3.8 | Solar | 05_07_911W56 | 07/23/2019 |  | 52 | 26 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 663115 | 01879 | 7.25 | Solar | 05_07_1W6 | 12/30/2024 | 01/07/2025 | 3 | 1 | 2 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | WILBRAHAM | 480125 | 01095 | 16.9 | Solar | 05_01_210L1 | 11/28/2022 | 11/30/2022 | 2 | 0 | 2 | 12/01/2022 | 12/01/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 | 11/28/2022 | 3/6/2024 | Y | EXP | 365 | 02/24/2023 | 03/06/2023 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 550020 | 01267 | 15.2 | Solar | 05_09_507L3 | 08/22/2023 | 08/24/2023 | 2 | 0 | 2 | 08/25/2023 | 08/25/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2023 |  | 10/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2023 | Connected |  | N
National Grid | BROCKTON | 744322 | 02302 | 10 | Solar | 05_09_1007G1 | 01/09/2026 | 01/13/2026 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 17 | 8 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | QUINCY | 222923 | 02170 | 7.6 | Solar | 05_07_911W56 | 06/24/2019 | 06/25/2019 | 0 | 0 | 0 | 06/26/2019 | 06/26/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 | 06/24/2019 | 11/20/2020 | Y | EXP | 365 | 07/10/2020 | 07/22/2020 | 12 | 0 | 12 |  |  | 10/30/2020 | Connected |  | N
National Grid | DUNSTABLE | 676729 | 01827 | 16.754 | Solar | 05_07_1W6 | 03/24/2025 | 03/28/2025 | 4 | 0 | 4 | 03/31/2025 | 03/31/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | WILBRAHAM | 486759 | 01095 | 13.92 | Solar | 05_01_210L1 | 06/14/2023 | 08/11/2023 | 41 | 40 | 1 | 08/14/2023 | 08/14/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 10/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2024 | Connected |  | N
National Grid | WILLIAMSTOWN | 572302 | 01267 | 6.67 | Solar | 05_09_507L3 | 12/11/2023 | 12/14/2023 | 3 | 2 | 1 | 12/15/2023 | 12/15/2023 | 31 | 9 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 | 12/11/2023 | 3/4/2025 | Y | EXP | 365 | 06/01/2024 | 06/05/2024 | 5 | 0 | 5 |  |  | 6/13/2024 | Connected |  | N
National Grid | BROCKTON | 175440 | 02302 | 499 | Solar | 05_09_1007G1 | 11/24/2014 | 11/24/2014 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2014 | 01/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/15/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 228923 | 02170 | 15 | Solar | 05_07_911W56 | 06/13/2019 | 06/18/2019 | 3 | 1 | 2 | 06/19/2019 | 06/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2019 |  | 11/8/2019 | N | EXP | 141 |  |  | 0 | 0 | 0 |  |  | 10/22/2019 | Connected |  | N
National Grid | TYNGSBORO | 584110 | 01879 | 0 | Other | 05_07_1W8 | 02/28/2024 | 05/23/2024 | 60 | 50 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/24/2024 | 09/03/2024 | 69 | 63 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WILBRAHAM | 551822 | 01095 | 15.2 | Solar | 05_01_210L1 | 08/29/2023 | 09/08/2023 | 8 | 6 | 2 | 09/11/2023 | 09/11/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 |  | 10/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2023 | Connected |  | N
National Grid | WILLIAMSTOWN | 609525 | 01267 | 23 | Solar | 05_09_507L3 | 05/08/2024 | 06/04/2024 | 18 | 16 | 2 | 06/05/2024 | 06/05/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 176461 | 02302 | 7.6 | Solar | 05_09_1007G1 | 02/04/2016 | 02/04/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/13/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/24/2016 | 8/24/2016 | 8/24/2016 | Connected |  | N
National Grid | QUINCY | 245629 | 02170 | 0 | Solar | 05_07_911W56 | 07/31/2019 | 08/07/2019 | 4 | 0 | 4 | 08/08/2019 | 08/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 7/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2020 | Connected |  | N
National Grid | TYNGSBORO | 174684 | 01879 | 50 | Solar | 05_07_1W8 | 01/09/2014 | 01/09/2014 | 5 | 0 | 5 | 01/17/2014 | 01/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2014 |  | 3/31/2014 | N | EXP | 66 |  |  | 0 | 0 | 0 | 4/7/2014 | 4/7/2014 | 4/24/2014 | Connected |  | N
National Grid | WILBRAHAM | 585368 | 01095 | 10 | Solar | 05_01_210L1 | 02/15/2024 | 02/28/2024 | 8 | 4 | 4 | 02/29/2024 | 02/29/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSTOWN | 626055 | 01267 | 0 | Solar | 05_09_507L3 | 07/18/2024 | 08/06/2024 | 14 | 10 | 4 | 08/07/2024 | 08/07/2024 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 10/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2024 | Connected |  | N
National Grid | BROCKTON | 417651 | 02302 | 0 | Solar | 05_09_1007G1 | 12/22/2022 | 12/27/2022 | 2 | 0 | 2 | 12/28/2022 | 12/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/22/2022 | 2/3/2024 | Y | EXP | 365 | 04/25/2023 | 08/24/2023 | 122 | 0 | 122 |  |  | 11/6/2023 | Connected |  | N
National Grid | QUINCY | 292552 | 02169 | 10 | Solar | 05_07_911W56 | 06/22/2020 |  | 148 | 18 | 130 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/10/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 174713 | 01827 | 85 | Solar | 05_07_1W8 | 01/09/2014 | 01/09/2014 | 5 | 0 | 5 | 01/17/2014 | 01/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2014 |  | 3/31/2014 | N | EXP | 32 |  |  | 0 | 0 | 0 | 4/7/2014 | 4/7/2014 | 4/24/2014 | Connected |  | N
National Grid | WILBRAHAM | 588595 | 01095 | 9.86 | Solar | 05_01_210L1 | 03/11/2024 | 03/13/2024 | 2 | 0 | 2 | 03/14/2024 | 03/14/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 | 03/11/2024 | 3/29/2025 | Y | EXP | 365 | 05/08/2024 | 06/21/2024 | 45 | 0 | 45 |  |  | 6/29/2024 | Connected |  | N
National Grid | WILLIAMSTOWN | 633834 | 01267 | 7.6 | Solar | 05_09_507L3 | 08/19/2024 | 09/03/2024 | 4 | 1 | 3 | 09/04/2024 | 09/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 08/19/2024 | 9/18/2025 | Y | EXP | 365 | 12/13/2024 | 12/12/2024 | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | BROCKTON | 597080 | 02302 | 22.8 | Solar | 05_09_1007G1 | 05/20/2024 |  | 82 | 81 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 304482 | 02169 | 10 | Solar | 05_07_911W56 | 12/08/2020 | 12/13/2020 | 3 | 0 | 3 | 12/14/2020 | 12/14/2020 | 30 | 9 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2021 | Connected |  | N
National Grid | DUNSTABLE | 175415 | 01827 | 52 | Solar | 05_07_1W8 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2014 |  | 11/28/2014 | N | EXP | 12 |  |  | 0 | 0 | 0 | 8/11/2014 | 8/11/2014 | 1/8/2015 | Connected |  | N
National Grid | WILBRAHAM | 594891 | 01095 | 20 | Solar | 05_01_210L1 | 03/06/2024 | 03/12/2024 | 4 | 1 | 3 | 03/13/2024 | 03/13/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | WILLIAMSTOWN | 640425 | 01267 | 3.8 | Solar | 05_09_507L3 | 09/16/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 57 | 33 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | BROCKTON | 675280 | 02302 | 17.6 | Solar | 05_09_1007G1 | 03/03/2025 | 03/06/2025 | 3 | 0 | 3 | 03/07/2025 | 03/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | QUINCY | 305161 | 02170 | 5.22 | Solar | 05_07_911W56 | 08/05/2020 | 09/15/2020 | 28 | 28 | 0 | 09/16/2020 | 09/16/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 | 08/05/2020 | 9/15/2021 | Y | EXP | 365 | 12/22/2020 | 01/08/2021 | 17 | 0 | 17 |  |  | 7/7/2021 | Connected |  | N
National Grid | DUNSTABLE | 175599 | 01827 | 72 | Solar | 05_07_1W8 | 08/01/2014 | 08/01/2014 | 6 | 0 | 6 | 08/12/2014 | 08/12/2014 | 616 | 0 | 616 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2014 |  | 11/28/2014 | N | EXP | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 613674 | 01095 | 19.1 | Solar | 05_01_210L1 | 05/28/2024 | 05/30/2024 | 2 | 0 | 2 | 05/31/2024 | 05/31/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | WILLIAMSTOWN | 657347 | 01267 | 10 | Solar | 05_09_507L3 | 11/27/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/19/2025 | Connected |  | N
National Grid | BROCKTON | 175376 | 02302 | 5000 | Solar | 05_09_1009W1 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/03/2014 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 319559 | 02170 | 7.6 | Solar | 05_07_911W56 | 11/11/2020 | 11/17/2020 | 3 | 0 | 3 | 11/18/2020 | 11/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 11/11/2020 |  | Y | EXP | 365 | 02/16/2021 | 03/12/2021 | 24 | 0 | 24 |  |  | 5/6/2021 | Connected |  | N
National Grid | DUNSTABLE | 175594 | 01827 | 63 | Solar | 05_07_1W8 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2014 |  | 10/31/2014 | N | EXP | 63 |  |  | 0 | 0 | 0 | 3/14/2016 | 3/14/2016 | 3/14/2016 | Connected |  | N
National Grid | SPRINGFIELD | 617302 | 01095 | 19.195 | Solar | 05_01_210L1 | 06/26/2024 | 07/03/2024 | 5 | 2 | 3 | 07/05/2024 | 07/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2024 | Connected |  | N
National Grid | CHARLEMONT | 665090 | 01339 | 10 | Solar | 05_09_507L3 | 01/10/2025 | 01/28/2025 | 2 | 0 | 2 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 01/10/2025 | 3/17/2026 | Y | EXP | 365 | 07/24/2025 | 11/12/2025 | 112 | 0 | 112 |  |  | 12/17/2025 | Connected |  | N
National Grid | BROCKTON | 175448 | 02302 | 5000 | Solar | 05_09_1009W1 | 03/12/2014 | 03/12/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/24/2014 | 04/03/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 333806 | 02169 | 6.72 | Solar | 05_07_911W56 | 03/19/2021 | 03/22/2021 | 0 | 0 | 0 | 03/23/2021 | 03/23/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 03/19/2021 | 1/23/2023 | Y | EXP | 365 | 06/10/2021 | 06/12/2021 | 3 | 0 | 3 |  |  | 7/8/2022 | Connected |  | N
National Grid | DUNSTABLE | 369405 | 01827 | 9.57 | Solar | 05_07_1W8 | 09/17/2021 | 09/21/2021 | 2 | 0 | 2 | 09/22/2021 | 09/22/2021 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2021 |  | 6/26/2023 | N | EXP | 6 |  |  | 0 | 0 | 0 |  |  | 6/28/2023 | Connected |  | N
National Grid | WILBRAHAM | 652470 | 01095 | 7.6 | Solar | 05_01_210L1 | 11/06/2024 | 12/18/2024 | 28 | 25 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | CHARLEMONT | 684855 | 01339 | 3.8 | Solar | 05_09_507L3 | 04/14/2025 | 09/15/2025 | 103 | 100 | 3 | 09/16/2025 | 09/16/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 585259 | 02302 | 25 | Solar | 05_09_1015W1 | 02/22/2024 | 03/21/2024 | 20 | 15 | 5 | 03/22/2024 | 03/22/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 340045 | 02171 | 7.6 | Solar | 05_07_911W56 | 02/17/2021 | 02/25/2021 | 5 | 0 | 5 | 02/26/2021 | 02/26/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 414118 | 01827 | 7.6 | Solar | 05_07_1W8 | 02/24/2022 | 02/28/2022 | 2 | 0 | 2 | 03/01/2022 | 03/01/2022 | 60 | 44 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2022 |  | 6/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 656820 | 01095 | 6.175 | Solar | 05_01_210L1 | 11/26/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  | 2/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | CHARLEMONT | 698150 | 01339 | 15.2 | Solar | 05_09_507L3 | 06/13/2025 | 06/27/2025 | 9 | 5 | 4 | 06/30/2025 | 06/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2025 |  | 8/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | BROCKTON | 592046 | 02302 | 25 | Solar | 05_09_1015W1 | 02/22/2024 | 02/28/2024 | 17 | 17 | 0 | 02/29/2024 | 02/29/2024 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 341380 | 02170 | 7.6 | Solar | 05_07_911W56 | 02/09/2021 | 02/11/2021 | 1 | 0 | 1 | 02/12/2021 | 02/12/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 444420 | 01827 | 0 | Other | 05_07_1W8 | 03/14/2023 | 07/14/2023 | 84 | 74 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2023 | 08/08/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 661863 | 01095 | 6 | Solar | 05_01_210L1 | 12/19/2024 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | CHARLEMONT | 717879 | 01339 | 0 | Battery Add-On | 05_09_507L3 | 09/09/2025 | 09/10/2025 | 1 | 0 | 1 | 09/11/2025 | 09/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 592039 | 02302 | 22.8 | Solar | 05_09_1015W1 | 02/22/2024 | 03/21/2024 | 20 | 15 | 5 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 342713 | 02170 | 7.6 | Solar | 05_07_911W56 | 03/09/2021 | 03/16/2021 | 4 | 0 | 4 | 03/17/2021 | 03/17/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2021 |  | 5/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2021 | Connected |  | N
National Grid | DUNSTABLE | 531854 | 01827 | 5 | Solar | 05_07_1W8 | 07/25/2023 | 10/17/2023 | 58 | 52 | 6 | 10/18/2023 | 10/18/2023 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 07/25/2023 | 11/27/2024 | Y | EXP | 365 | 01/10/2024 | 01/09/2024 | 0 | 0 | 0 |  |  | 1/26/2024 | Connected |  | N
National Grid | WILBRAHAM | 666043 | 01095 | 5.76 | Solar | 05_01_210L1 | 01/15/2025 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | CHARLEMONT | 753169 | 01339 | 7.6 | Solar | 05_09_508L1 | 02/25/2026 | 02/27/2026 | 2 | 0 | 2 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 592033 | 02302 | 22.8 | Solar | 05_09_1015W1 | 02/22/2024 | 03/21/2024 | 20 | 15 | 5 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 345930 | 02170 | 7.6 | Solar | 05_07_911W56 | 04/10/2021 | 04/12/2021 | 0 | 0 | 0 | 04/13/2021 | 04/13/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 652949 | 01827 | 3.8 | Solar | 05_07_1W8 | 11/07/2024 | 11/25/2024 | 4 | 0 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | WILBRAHAM | 675295 | 01095 | 7.6 | Solar | 05_01_210L1 | 03/03/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 71 | 56 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 6/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2025 | Connected |  | N
National Grid | CHARLEMONT | 177284 | 01339 | 73.3 | Solar | 05_09_508L1 | 06/15/2016 | 06/15/2016 | 7 | 7 | 0 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 | 06/15/2016 | 6/21/2017 | Y | EXP | 321 | 02/07/2017 | 03/06/2017 | 18 | 0 | 18 | 3/23/2017 | 3/23/2017 | 3/27/2017 | Connected |  | N
National Grid | BROCKTON | 592026 | 02302 | 22.8 | Solar | 05_09_1015W1 | 02/22/2024 | 03/21/2024 | 20 | 15 | 5 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 350043 | 02169 | 7.6 | Solar | 05_07_911W56 | 05/19/2021 | 12/26/2021 | 1 | 0 | 1 | 05/24/2021 | 05/24/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2021 | 05/19/2021 | 8/26/2022 | Y | EXP | 365 | 04/08/2022 | 04/22/2022 | 15 | 0 | 15 |  |  | 6/1/2022 | Connected |  | N
National Grid | DUNSTABLE | 708135 | 01827 | 7.678 | Solar | 05_07_1W8 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 34 | 22 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | WILBRAHAM | 685252 | 01095 | 14.44 | Solar | 05_01_210L1 | 04/15/2025 | 05/20/2025 | 23 | 17 | 6 | 05/21/2025 | 05/21/2025 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2025 |  | 8/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | MONROE | 177319 | 01350 | 10 | Solar | 05_09_508L1 | 02/14/2017 | 02/14/2017 | 5 | 3 | 2 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2017 |  | 6/29/2018 | N | EXP | 491 |  |  | 0 | 0 | 0 |  |  | 4/29/2018 | Connected |  | N
National Grid | BROCKTON | 592018 | 02302 | 22.8 | Solar | 05_09_1015W1 | 02/22/2024 | 03/21/2024 | 20 | 15 | 5 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 449542 | 02171 | 6 | Solar | 05_07_911W56 | 08/12/2022 | 09/06/2022 | 16 | 15 | 1 | 09/07/2022 | 09/07/2022 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2022 | 08/12/2022 | 7/28/2024 | Y | EXP | 4 | 04/13/2023 | 04/27/2023 | 15 | 0 | 15 |  |  | 10/11/2024 | Connected |  | Y
National Grid | DUNSTABLE | 591013 | 01827 | 34.6 | Solar | 05_07_20W10 | 02/19/2024 |  | 12 | 9 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 287338 | 01095 | 3200 | Hydro | 05_01_216W1 | 09/24/2021 | 04/27/2022 | 137 | 127 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/28/2022 | 05/23/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MONROE | 177507 | 01350 | 11.4 | Solar | 05_09_508L1 | 03/06/2017 | 03/06/2017 | 8 | 7 | 1 | 03/17/2017 | 03/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 | 03/06/2017 | 3/12/2018 | Y | EXP | 356 | 06/23/2017 | 06/26/2017 | 1 | 0 | 1 | 9/13/2017 | 9/13/2017 | 9/13/2017 | Connected |  | N
National Grid | BROCKTON | 592011 | 02302 | 25 | Solar | 05_09_1015W1 | 02/22/2024 | 03/21/2024 | 20 | 15 | 5 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 |  | 5/21/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 386414 | 02170 | 10 | Solar | 05_07_911W56 | 11/09/2021 | 11/10/2021 | 1 | 1 | 0 | 11/12/2021 | 11/12/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/09/2021 | 4/14/2023 | Y | EXP | 365 | 03/19/2022 | 04/11/2022 | 24 | 0 | 24 |  |  | 4/22/2022 | Connected |  | N
National Grid | DUNSTABLE | 192789 | 01827 | 10 | Solar | 05_07_20W13 | 08/06/2018 | 09/10/2018 | 7 | 6 | 1 | 09/10/2018 | 09/10/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 | 08/06/2018 | 10/30/2019 | Y | EXP | 399 | 04/26/2019 | 05/17/2019 | 21 | 0 | 21 |  |  | 10/7/2019 | Connected |  | N
National Grid | WILBRAHAM | 178032 | 01095 | 299 | Solar | 05_01_216W1 | 10/26/2017 | 10/26/2017 | 17 | 17 | 0 | 11/30/2017 | 11/30/2017 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2018 |  | 11/1/2019 | N | EXP | 666 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 177506 | 01247 |  | Solar | 05_09_508L1 | 03/06/2017 | 03/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/12/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 592001 | 02302 | 25 | Solar | 05_09_1015W1 | 02/22/2024 | 03/21/2024 | 20 | 15 | 5 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 388182 | 02170 | 6 | Solar | 05_07_911W56 | 10/26/2021 | 01/06/2022 | 31 | 25 | 6 | 12/10/2021 | 12/10/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 406009 | 01827 | 5.52 | Solar | 05_07_20W13 | 06/30/2022 |  | 156 | 17 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 299739 | 01095 | 7.6 | Solar | 05_01_216W1 | 08/03/2020 | 08/05/2020 | 1 | 0 | 1 | 08/06/2020 | 08/06/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2020 | 08/03/2020 | 6/8/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2021 | Connected |  | N
National Grid | NORTH ADAMS | 177727 | 01247 | 16 | Solar | 05_09_508L1 | 10/04/2017 | 10/04/2017 | 10 | 0 | 10 | 02/05/2018 | 02/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2018 | 10/04/2017 | 8/22/2019 | Y | EXP | 562 |  |  | 0 | 0 | 0 |  |  | 5/31/2019 | Connected |  | N
National Grid | BROCKTON | 591983 | 02302 | 20 | Solar | 05_09_1015W1 | 02/22/2024 | 02/28/2024 | 15 | 14 | 1 | 02/29/2024 | 02/29/2024 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 400248 | 02171 | 3.84 | Solar | 05_07_911W56 | 01/04/2022 | 01/07/2022 | 3 | 0 | 3 | 01/10/2022 | 01/10/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2022 | 01/04/2022 | 5/6/2023 | Y | EXP | 365 | 04/07/2022 | 05/02/2022 | 26 | 0 | 26 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 408727 | 01463 | 57.6 | Solar | 05_07_20W7 | 01/31/2022 | 02/17/2022 | 13 | 8 | 5 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 321965 | 01095 | 5315 | Solar | 05_01_216W1 | 01/08/2021 | 03/22/2021 | 77 | 68 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2021 | 06/02/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 185731 | 01247 | 500 | Solar | 05_09_508L1 | 05/18/2018 | 05/18/2018 | 6 | 0 | 6 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 591947 | 02302 | 20 | Solar | 05_09_1015W1 | 02/22/2024 | 02/28/2024 | 15 | 14 | 1 | 02/29/2024 | 02/29/2024 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 414713 | 02170 | 10 | Solar | 05_07_911W56 | 03/31/2022 | 04/04/2022 | 2 | 0 | 2 | 04/05/2022 | 04/05/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 515523 | 01879 | 0 | Natural Gas | 05_07_20W9 | 08/17/2023 |  | 151 | 83 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LONGMEADOW | 393819 | 01028 | 8.7 | Solar | 05_01_216W1 | 11/06/2021 | 12/29/2021 | 4 | 2 | 2 | 11/12/2021 | 11/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 |  | 2/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2023 | Connected |  | N
National Grid | NORTH ADAMS | 187656 | 01247 | 7.6 | Solar | 05_09_508L1 | 06/11/2018 | 06/11/2018 | 0 | 0 | 0 | 07/13/2018 | 07/13/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 590327 | 02302 | 20 | Solar | 05_09_1015W1 | 02/22/2024 | 03/21/2024 | 20 | 15 | 5 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 421229 | 02170 | 4999.2 | Battery Add-On | 05_07_911W56 | 11/07/2022 | 07/20/2023 | 173 | 163 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2023 | 10/17/2023 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 736785 | 01827 | 10 | Solar | 05_07_2W1 | 11/26/2025 | 12/01/2025 | 2 | 0 | 2 | 12/02/2025 | 12/02/2025 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2026 |  | 2/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LONGMEADOW | 402759 | 01028 | 980 | Solar | 05_01_216W1 | 02/22/2022 | 04/11/2022 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2022 | 04/14/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 187558 | 01247 | 15.2 | Solar | 05_09_508L1 | 06/08/2018 | 06/08/2018 | 18 | 10 | 8 | 07/06/2018 | 07/06/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 590284 | 02302 | 20 | Solar | 05_09_1015W1 | 02/22/2024 | 03/21/2024 | 20 | 15 | 5 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | QUINCY | 431099 | 02170 | 9.8 | Solar | 05_07_911W56 | 06/08/2022 | 06/09/2022 | 1 | 0 | 1 | 06/10/2022 | 06/10/2022 | 24 | 2 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 9/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2023 | Connected |  | N
National Grid | DUNSTABLE | 744023 | 01827 | 13.3 | Solar | 05_07_2W1 | 01/07/2026 | 01/08/2026 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 21 | 9 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LONGMEADOW | 527951 | 01028 | 6 | Solar | 05_01_216W1 | 05/30/2023 | 06/01/2023 | 2 | 0 | 2 | 06/02/2023 | 06/02/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 | 05/30/2023 | 8/3/2024 | Y | EXP | 365 | 05/16/2024 | 06/10/2024 | 26 | 0 | 26 |  |  | 6/18/2024 | Connected |  | N
National Grid | NORTH ADAMS | 189273 | 01247 | 19 | Solar | 05_09_508L1 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 |  | 9/27/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | BROCKTON | 590179 | 02302 | 22.8 | Solar | 05_09_1015W1 | 02/22/2024 | 03/21/2024 | 20 | 15 | 5 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BROCKTON | 433454 | 02301 | 3.8 | Solar | 05_07_911W56 | 06/03/2022 | 06/07/2022 | 2 | 0 | 2 | 06/08/2022 | 06/08/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2022 |  | 7/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | N
National Grid | CLINTON | 749270 | 01510 | 13.36 | Solar | 05_07_2W1 | 02/04/2026 | 02/06/2026 | 4 | 2 | 2 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LONGMEADOW | 546329 | 01028 | 15.2 | Solar | 05_01_216W1 | 08/14/2023 | 08/15/2023 | 1 | 0 | 1 | 08/16/2023 | 08/16/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2024 | Connected |  | N
National Grid | NORTH ADAMS | 190139 | 01247 | 3.8 | Solar | 05_09_508L1 | 07/06/2018 | 08/28/2018 | 4 | 0 | 4 | 08/29/2018 | 08/29/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 | 07/06/2018 | 12/31/2020 | Y | EXP | 5 |  |  | 0 | 0 | 0 |  |  | 10/22/2020 | Connected |  | N
National Grid | BROCKTON | 590175 | 02302 | 20 | Solar | 05_09_1015W1 | 02/22/2024 | 03/21/2024 | 20 | 15 | 5 | 03/22/2024 | 03/22/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 |  | 4/24/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BROCKTON | 438734 | 02301 | 10 | Solar | 05_07_911W56 | 07/06/2022 | 07/12/2022 | 4 | 1 | 3 | 07/13/2022 | 07/13/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 174807 | 01510 | 20 | Solar | 05_07_2W1 | 01/22/2013 | 01/22/2013 | 7 | 0 | 7 | 02/01/2013 | 02/01/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2013 |  | 4/30/2013 | N | EXP | 36 |  |  | 0 | 0 | 0 | 3/25/2013 | 3/25/2013 | 4/29/2013 | Connected |  | N
National Grid | LONGMEADOW | 577614 | 01028 | 7.6 | Solar | 05_01_216W1 | 12/28/2023 | 01/04/2024 | 4 | 0 | 4 | 01/05/2024 | 01/05/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2024 |  | 2/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | NORTH ADAMS | 207492 | 01247 | 6 | Solar | 05_09_508L1 | 01/30/2019 | 02/04/2019 | 3 | 3 | 0 | 02/05/2019 | 02/05/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2019 | 01/30/2019 | 8/30/2019 | Y | EXP | 25 | 06/01/2019 | 07/02/2019 | 31 | 0 | 31 |  |  | 8/12/2019 | Connected |  | N
National Grid | BROCKTON | 657379 | 02302 | 5000 | Solar | 05_09_1015W1 | 04/14/2025 | 01/09/2026 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/12/2026 | 02/17/2026 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BROCKTON | 443774 | 02301 | 7.6 | Solar | 05_07_911W56 | 08/31/2022 | 09/01/2022 | 1 | 0 | 1 | 09/02/2022 | 09/02/2022 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 08/31/2022 | 6/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2023 | Connected |  | N
National Grid | CLINTON | 175276 | 01510 | 42.57 | Solar | 05_07_2W1 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2014 |  | 11/28/2014 | N | EXP | 66 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/5/2015 | Connected |  | N
National Grid | LONGMEADOW | 598936 | 01028 | 7.6 | Solar | 05_01_216W1 | 04/11/2024 | 04/15/2024 | 2 | 0 | 2 | 04/16/2024 | 04/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  | 7/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | NORTH ADAMS | 237300 | 01247 | 9.6 | Solar | 05_09_508L1 | 03/03/2020 | 05/14/2020 | 51 | 43 | 8 | 05/15/2020 | 05/15/2020 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 | 03/03/2020 | 4/14/2021 | Y | EXP | 365 | 01/23/2021 | 02/04/2021 | 12 | 0 | 12 |  |  | 2/19/2021 | Connected |  | N
National Grid | BROCKTON | 741777 | 02302 | 11.5 | Solar | 05_09_1015W1 | 12/23/2025 | 12/26/2025 | 1 | 0 | 1 | 12/29/2025 | 12/29/2025 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 445947 | 02301 | 6 | Solar | 05_07_911W56 | 07/27/2022 | 07/29/2022 | 2 | 0 | 2 | 08/01/2022 | 08/01/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 176098 | 01510 | 16.77 | Solar | 05_07_2W1 | 04/07/2015 | 04/07/2015 | 4 | 1 | 3 | 04/14/2015 | 04/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2015 |  | 8/10/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 4/27/2015 | 4/27/2015 | 7/25/2016 | Connected |  | N
National Grid | LONGMEADOW | 651311 | 01028 | 3.8 | Solar | 05_01_216W1 | 11/12/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/12/2024 | 3/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | NORTH ADAMS | 235072 | 01247 | 7.6 | Solar | 05_09_508L1 | 06/18/2019 | 06/24/2019 | 3 | 0 | 3 | 06/25/2019 | 06/25/2019 | 10 | 5 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 06/18/2019 | 9/16/2020 | Y | EXP | 365 | 05/14/2020 | 05/27/2020 | 13 | 0 | 13 |  |  | 7/28/2020 | Connected |  | N
National Grid | BROCKTON | 744911 | 02302 | 7.6 | Solar | 05_09_1015W1 | 01/13/2026 | 01/29/2026 | 11 | 10 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | BROCKTON | 444881 | 02301 | 6 | Solar | 05_07_911W56 | 08/10/2022 | 08/12/2022 | 2 | 0 | 2 | 08/15/2022 | 08/15/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2022 | 08/10/2022 | 6/22/2024 | Y | EXP | 365 | 05/03/2023 | 06/13/2023 | 42 | 0 | 42 |  |  | 7/7/2023 | Connected |  | N
National Grid | CLINTON | 176759 | 01510 | 5 | Solar | 05_07_2W1 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2016 | 02/24/2016 | 3/1/2017 | Y | EXP | 327 | 01/11/2017 | 01/17/2017 | 3 | 0 | 3 | 4/8/2016 | 4/8/2016 | 1/30/2017 | Connected |  | N
National Grid | LONGMEADOW | 660341 | 01028 | 3.8 | Solar | 05_01_216W1 | 12/12/2024 | 02/05/2025 | 27 | 22 | 5 | 02/06/2025 | 02/06/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 3/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | NORTH ADAMS | 250508 | 01247 | 7.6 | Solar | 05_09_508L1 | 11/07/2019 | 11/13/2019 | 2 | 1 | 1 | 11/14/2019 | 11/14/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 |  | 11/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2020 | Connected |  | N
National Grid | BROCKTON | 174295 | 02302 | 2250 | Solar | 05_09_1015W1 | 12/16/2011 | 12/16/2011 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2012 | 04/25/2012 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2014 | 12/16/2011 | 8/30/2013 | Y | STD | 31 | 03/24/2015 | 08/12/2015 | 97 | 0 | 97 | 7/16/2015 | 7/16/2015 | 7/16/2015 | Connected |  | N
National Grid | HOLBROOK | 473250 | 02343 | 10 | Solar | 05_07_911W56 | 11/28/2022 | 12/02/2022 | 4 | 0 | 4 | 12/05/2022 | 12/05/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 | 11/28/2022 | 11/29/2024 | Y | EXP | 365 | 10/04/2024 | 10/03/2024 | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | CLINTON | 177622 | 01510 | 7.6 | Solar | 05_07_2W1 | 11/09/2017 | 11/09/2017 | 15 | 14 | 1 | 12/05/2017 | 12/05/2017 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2017 |  | 11/15/2018 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LONGMEADOW | 690813 | 01028 | 5.76 | Solar | 05_01_216W1 | 05/09/2025 | 05/21/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 | 05/09/2025 | 7/16/2026 | Y | EXP | 365 | 11/07/2025 | 12/18/2025 | 42 | 0 | 42 |  |  | 11/26/2025 | Connected |  | N
National Grid | NORTH ADAMS | 307802 | 01247 | 7.6 | Solar | 05_09_508L1 | 08/19/2020 | 08/20/2020 | 0 | 0 | 0 | 08/21/2020 | 08/21/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2020 | 08/19/2020 | 8/19/2021 | Y | EXP | 365 | 02/04/2021 | 02/03/2021 | 0 | 0 | 0 |  |  | 3/18/2021 | Connected |  | N
National Grid | BROCKTON | 174465 | 02302 | 200 | Solar | 05_09_1015W1 | 08/03/2011 | 08/03/2011 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 472498 | 02343 | 7.6 | Solar | 05_07_911W56 | 11/28/2022 | 12/11/2022 | 10 | 6 | 4 | 12/12/2022 | 12/12/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 | 11/28/2022 | 12/1/2025 | Y | EXP | 73 | 08/30/2023 | 09/19/2024 | 387 | 3 | 384 |  |  | 12/5/2024 | Connected |  | N
National Grid | CLINTON | 177793 | 01510 | 10 | Solar | 05_07_2W1 | 08/02/2017 | 08/02/2017 | 8 | 8 | 0 | 08/15/2017 | 08/15/2017 | 154 | 0 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2017 | 08/02/2017 | 9/7/2018 | Y | EXP | 387 | 02/02/2018 | 02/06/2018 | 2 | 0 | 2 |  |  | 8/21/2018 | Connected |  | N
National Grid | LONGMEADOW | 486664 | 01028 | 4999 | Solar | 05_01_216W2 | 05/08/2023 | 05/22/2023 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2023 | 05/23/2023 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTH ADAMS | 313267 | 01247 | 4.8 | Solar | 05_09_508L1 | 10/13/2020 | 10/20/2020 | 4 | 0 | 4 | 10/21/2020 | 10/21/2020 | 58 | 41 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2021 | Connected |  | N
National Grid | BROCKTON | 174599 | 02302 | 41 | Solar | 05_09_1015W1 | 10/04/2011 | 10/04/2011 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2011 |  | 2/22/2012 | N | EXP | 68 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 2/22/2012 | Connected |  | N
National Grid | HOLBROOK | 474867 | 02343 | 3.8 | Solar | 05_07_911W56 | 11/16/2022 | 11/18/2022 | 2 | 0 | 2 | 11/21/2022 | 11/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/25/2022 | 11/16/2022 | 5/10/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | CLINTON | 177921 | 01510 | 10 | Solar | 05_07_2W1 | 10/23/2017 | 10/23/2017 | 2 | 0 | 2 | 11/06/2017 | 11/06/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 10/31/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | LONGMEADOW | 682136 | 01028 | 2000 | Solar | 05_01_216W2 | 11/25/2025 | 12/18/2025 | 15 | 6 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 | 01/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTH ADAMS | 316243 | 01247 | 9.8 | Solar | 05_09_508L1 | 10/21/2020 | 10/22/2020 | 0 | 0 | 0 | 10/23/2020 | 10/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2020 |  | 10/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2021 | Connected |  | N
National Grid | BROCKTON | 175434 | 02302 | 984 | Solar | 05_09_1015W1 | 11/24/2014 | 11/24/2014 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2014 | 01/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 484350 | 02343 | 10 | Solar | 05_07_911W56 | 12/30/2022 | 01/04/2023 | 2 | 0 | 2 | 01/05/2023 | 01/05/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 | 12/30/2022 | 5/15/2024 | Y | EXP | 365 | 04/07/2023 | 05/15/2023 | 39 | 0 | 39 |  |  | 7/11/2023 | Connected |  | N
National Grid | CLINTON | 542282 | 01510 | 0 | Solar | 05_07_92W78 | 07/21/2023 | 07/24/2023 | 1 | 0 | 1 | 07/25/2023 | 07/25/2023 | 113 | 94 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2024 | Connected |  | N
National Grid | LONGMEADOW | 694872 | 01028 | 400 | Solar | 05_01_216W2 | 09/09/2025 | 10/09/2025 | 21 | 13 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2025 | 01/09/2026 | 61 | 44 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FLORIDA | 349187 | 01247 | 240 | Solar | 05_09_508L1 | 04/06/2021 | 01/07/2022 | 8 | 0 | 8 | 04/20/2021 | 04/20/2021 | 28 | 4 | 24 | 07/20/2021 | 11/12/2021 | 81 | 7 | 74 |  |  | 0 | 0 | 0 |  | 11/12/2021 | 81 | 7 | 74 |  |  | 0 | 0 | 0 | 12/2/2021 |  | 11/1/2023 | N | EXP | 651 | 01/10/2023 | 08/03/2023 | 206 | 0 | 206 |  |  | 10/31/2023 | Connected |  | N
National Grid | BROCKTON | 175490 | 02302 | 480 | Solar | 05_09_1015W1 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 | 08/06/2014 | 08/06/2014 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/1/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 504970 | 02343 | 10 | Solar | 05_07_911W56 | 03/31/2023 | 04/04/2023 | 2 | 0 | 2 | 04/05/2023 | 04/05/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 | 03/31/2023 | 5/25/2024 | Y | EXP | 365 | 07/21/2023 | 08/02/2023 | 13 | 0 | 13 |  |  | 10/5/2023 | Connected |  | N
National Grid | CLINTON | 632317 | 01510 | 9.88 | Solar | 05_07_92W78 | 08/30/2024 | 09/04/2024 | 2 | 0 | 2 | 09/05/2024 | 09/05/2024 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 | 08/30/2024 | 10/31/2025 | Y | EXP | 365 | 01/23/2025 | 03/27/2025 | 51 | 0 | 51 |  |  | 3/6/2025 | Connected |  | N
National Grid | LONGMEADOW | 176314 | 01028 | 183 | Solar | 05_01_216W2 | 05/11/2015 | 05/11/2015 | 4 | 4 | 0 | 05/15/2015 | 05/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2015 | 05/11/2015 | 12/31/2016 | Y | EXP | 561 | 06/21/2016 | 07/27/2016 | 25 | 0 | 25 | 12/11/2015 | 12/11/2015 | 8/4/2016 | Connected |  | N
National Grid | FLORIDA | 428276 | 01247 | 7.6 | Solar | 05_09_508L1 | 05/04/2022 | 05/05/2022 | 1 | 0 | 1 | 05/06/2022 | 05/06/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2022 |  | 5/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2022 | Connected |  | N
National Grid | BROCKTON | 175528 | 02302 | 480 | Solar | 05_09_1015W1 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 08/29/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 509862 | 02343 | 6 | Solar | 05_07_911W56 | 05/26/2023 | 05/30/2023 | 1 | 0 | 1 | 05/31/2023 | 05/31/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 647788 | 01510 | 4.64 | Solar | 05_07_92W78 | 10/17/2024 | 11/13/2024 | 3 | 1 | 2 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | LONGMEADOW | 177307 | 01028 | 15.2 | Solar | 05_01_216W2 | 11/16/2016 | 11/16/2016 | 3 | 3 | 0 | 11/22/2016 | 11/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 |  | 11/22/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 6/8/2017 | 6/8/2017 | 6/8/2017 | Connected |  | N
National Grid | FLORIDA | 489544 | 01247 | 7.6 | Solar | 05_09_508L1 | 01/04/2023 | 01/09/2023 | 3 | 0 | 3 | 01/10/2023 | 01/10/2023 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2023 |  | 4/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2023 | Connected |  | Y
National Grid | BROCKTON | 175572 | 02302 | 480 | Solar | 05_09_1015W1 | 10/13/2014 | 10/13/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2014 | 11/20/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 512233 | 02343 | 7.6 | Solar | 05_07_911W56 | 05/17/2023 | 05/18/2023 | 1 | 0 | 1 | 05/19/2023 | 05/19/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2023 | 05/17/2023 | 9/14/2024 | Y | EXP | 365 | 09/06/2023 | 09/15/2023 | 10 | 0 | 10 |  |  | 10/28/2023 | Connected |  | N
National Grid | CLINTON | 653471 | 01510 | 10 | Solar | 05_07_92W78 | 11/11/2024 | 12/12/2024 | 12 | 9 | 3 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/11/2024 | 2/24/2026 | Y | EXP | 365 | 06/11/2025 | 06/10/2025 | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | LONGMEADOW | 178033 | 01028 | 296 | Solar | 05_01_216W2 | 10/26/2017 | 10/26/2017 | 17 | 17 | 0 | 11/30/2017 | 11/30/2017 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2018 |  | 11/1/2019 | N | EXP | 666 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 515456 | 01247 | 7.6 | Solar | 05_09_508L1 | 04/28/2023 | 05/01/2023 | 1 | 0 | 1 | 05/02/2023 | 05/02/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  | 6/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2023 | Connected |  | N
National Grid | BROCKTON | 175918 | 02302 | 197 | Natural Gas | 05_09_1015W1 | 05/28/2015 | 05/28/2015 | 201 | 201 | 0 | 03/22/2016 | 03/22/2016 | 80 | 30 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2016 |  | 9/30/2019 | N | EXP | 1216 |  |  | 0 | 0 | 0 | 2/15/2018 | 2/15/2018 | 11/21/2019 | Connected |  | N
National Grid | HOLBROOK | 735694 | 02343 | 7.6 | Solar | 05_09_702W1 | 12/01/2025 | 12/05/2025 | 4 | 0 | 4 | 12/08/2025 | 12/08/2025 | 61 | 45 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CLINTON | 671495 | 01510 | 5.76 | Solar | 05_07_92W78 | 02/11/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | LONGMEADOW | 187526 | 01028 | 149.9 | Solar | 05_01_216W2 | 06/08/2018 | 09/03/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 519747 | 01247 | 10 | Solar | 05_09_508L1 | 05/01/2023 | 05/03/2023 | 2 | 0 | 2 | 05/04/2023 | 05/04/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 176100 | 02302 | 996 | Solar | 05_09_1015W1 | 04/13/2015 | 04/13/2015 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/14/2015 | 05/12/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2017 | 04/13/2015 | 11/1/2017 | Y | STD | 177 | 06/13/2017 | 10/06/2017 | 81 | 0 | 81 | 9/26/2017 | 9/26/2017 | 10/10/2017 | Connected |  | N
National Grid | HOLBROOK | 740243 | 02343 | 11.5 | Solar | 05_09_702W1 | 12/15/2025 | 01/06/2026 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CLINTON | 678603 | 01510 | 13.8 | Solar | 05_07_92W78 | 03/19/2025 | 03/26/2025 | 5 | 2 | 3 | 03/27/2025 | 03/27/2025 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | Y
National Grid | LONGMEADOW | 208503 | 01028 | 86.6 | Solar | 05_01_216W2 | 02/07/2019 | 03/19/2019 | 24 | 17 | 7 | 03/20/2019 | 03/20/2019 | 93 | 88 | 5 | 08/08/2019 | 08/25/2020 | 264 | 182 | 82 |  |  | 0 | 0 | 0 |  | 08/25/2020 | 264 | 182 | 82 |  |  | 0 | 0 | 0 | 9/4/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 547682 | 01247 | 5 | Solar | 05_09_508L1 | 09/15/2023 | 09/19/2023 | 2 | 0 | 2 | 09/20/2023 | 09/20/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 184798 | 02302 | 4648 | Solar | 05_09_1015W1 | 05/31/2018 | 05/31/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/25/2018 | 07/27/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 749319 | 02343 |  | Battery Add-On | 05_09_702W1 | 02/04/2026 | 02/05/2026 | 1 | 0 | 1 | 02/06/2026 | 02/06/2026 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CLINTON | 706156 | 01510 | 15.2 | Solar | 05_07_92W78 | 07/21/2025 | 07/25/2025 | 4 | 0 | 4 | 07/28/2025 | 07/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | LONGMEADOW | 470890 | 01028 | 15.2 | Solar | 05_01_216W2 | 10/24/2022 | 10/26/2022 | 2 | 0 | 2 | 10/27/2022 | 10/27/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 |  | 11/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2023 | Connected |  | N
National Grid | FLORIDA | 549132 | 01247 | 3.8 | Solar | 05_09_508L1 | 08/18/2023 | 08/22/2023 | 3 | 2 | 1 | 08/23/2023 | 08/23/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2023 | 08/18/2023 | 10/28/2024 | Y | EXP | 365 | 02/15/2024 | 03/07/2024 | 22 | 0 | 22 |  |  | 4/8/2024 | Connected |  | N
National Grid | BROCKTON | 186395 | 02302 | 4625 | Solar | 05_09_1015W1 | 06/22/2018 | 06/22/2018 | 60 | 41 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 10/10/2018 | 16 | 10 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 174649 | 02356 | 1000 | Solar | 05_09_702W1 | 04/04/2011 | 04/04/2011 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2011 | 09/08/2011 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2012 | 04/04/2011 | 12/31/2012 | Y | STD | 278 | 05/24/2013 | 10/17/2013 | 99 | 0 | 99 | 10/14/2013 | 10/14/2013 | 10/25/2013 | Connected |  | N
National Grid | CLINTON | 714426 | 01510 | 11.4 | Solar | 05_07_92W78 | 08/25/2025 | 09/03/2025 | 5 | 2 | 3 | 09/04/2025 | 09/04/2025 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | LONGMEADOW | 589386 | 01028 | 7.6 | Solar | 05_01_216W2 | 02/23/2024 | 03/04/2024 | 6 | 0 | 6 | 03/05/2024 | 03/05/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 | 02/23/2024 | 3/21/2025 | Y | EXP | 365 | 05/24/2024 | 05/23/2024 | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | NORTH ADAMS | 567652 | 01247 | 10 | Solar | 05_09_508L1 | 12/27/2023 | 01/05/2024 | 6 | 2 | 4 | 01/08/2024 | 01/08/2024 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 4/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2024 | Connected |  | N
National Grid | BROCKTON | 189359 | 02302 | 4000 | Solar | 05_09_1015W1 | 09/12/2018 | 10/05/2018 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/08/2018 | 11/08/2018 | 94 | 42 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 174984 | 02356 | 1000 | Solar | 05_09_702W1 | 11/10/2011 | 11/10/2011 | 623 | 51 | 572 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 738757 | 01510 | 0 | Battery Add-On | 05_07_92W79 | 12/08/2025 | 12/10/2025 | 2 | 0 | 2 | 12/11/2025 | 12/11/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2026 |  | 1/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LONGMEADOW | 601702 | 01028 | 7.6 | Solar | 05_01_216W2 | 04/10/2024 | 04/16/2024 | 3 | 0 | 3 | 04/17/2024 | 04/17/2024 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 | 04/10/2024 | 5/30/2025 | Y | EXP | 365 | 08/21/2024 | 10/17/2024 | 58 | 0 | 58 |  |  | 11/15/2024 | Connected |  | N
National Grid | NORTH ADAMS | 581722 | 01247 | 3.8 | Solar | 05_09_508L1 | 01/24/2024 | 01/30/2024 | 4 | 0 | 4 | 01/31/2024 | 01/31/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 | 01/24/2024 | 2/28/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  | 5/24/2024 | Connected |  | N
National Grid | BROCKTON | 647371 | 02302 | 6 | Solar | 05_05_344W5 | 11/11/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/11/2024 | 3/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2025 | Connected |  | N
National Grid | EASTON | 175200 | 02356 | 1000 | Solar | 05_09_702W1 | 04/11/2011 | 04/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2011 | 09/08/2011 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 278 | 05/24/2013 | 10/17/2013 | 99 | 0 | 99 | 10/14/2013 | 10/14/2013 | 10/25/2013 | Connected |  | N
National Grid | CLINTON | 746180 | 01510 | 0 | Battery Add-On | 05_07_92W79 | 01/20/2026 | 01/26/2026 | 3 | 0 | 3 | 01/27/2026 | 01/27/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LONGMEADOW | 715423 | 01028 | 3320 | Solar | 05_01_216W3 | 10/28/2025 | 12/09/2025 | 28 | 20 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 01/08/2026 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FLORIDA | 652722 | 01247 | 5.7 | Solar | 05_09_508L1 | 11/06/2024 | 12/05/2024 | 8 | 4 | 4 | 12/06/2024 | 12/06/2024 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 | 11/06/2024 | 2/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | BROCKTON | 673788 | 02302 | 11.5 | Solar | 05_05_344W5 | 02/24/2025 | 03/24/2025 | 21 | 18 | 3 | 03/25/2025 | 03/25/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2025 | Connected |  | N
National Grid | EASTON | 175201 | 02356 | 1000 | Solar | 05_09_702W1 | 04/11/2011 | 04/11/2011 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2011 | 09/08/2011 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 278 |  |  | 0 | 0 | 0 | 10/14/2013 | 10/14/2013 | 10/25/2013 | Connected |  | N
National Grid | CLINTON | 174695 | 01510 | 900 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2015 |  | 12/31/2015 | N | STD | 238 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 174358 | 01028 | 10.53 | Solar | 05_01_216W3 | 05/16/2012 | 05/16/2012 | 7 | 0 | 7 | 05/30/2012 | 05/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 7/31/2012 | N | EXP | 134 |  |  | 0 | 0 | 0 | 9/6/2012 | 9/6/2012 | 5/30/2013 | Connected |  | N
National Grid | NORTH ADAMS | 653570 | 01247 | 7.04 | Solar | 05_09_508L1 | 11/12/2024 | 11/22/2024 | 4 | 0 | 4 | 11/25/2024 | 11/25/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 688241 | 01331 | 11.5 | Solar | 05_05_344W5 | 05/26/2025 | 07/22/2025 | 38 | 35 | 3 | 07/23/2025 | 07/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | EASTON | 175979 | 02356 | 990 | Solar | 05_09_702W1 | 01/22/2015 | 01/22/2015 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/03/2015 | 03/05/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 06/24/2016 | 08/01/2016 | 25 | 0 | 25 | 6/24/2016 | 01/22/2015 | 6/30/2015 | Y | STD | 36 | 12/20/2016 | 05/02/2017 | 90 | 0 | 90 | 7/6/2017 | 7/6/2017 | 7/6/2017 | Connected |  | N
National Grid | CLINTON | 174694 | 01510 | 500 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 01/15/2014 | 04/03/2014 | 53 | 0 | 53 | 12/31/2013 | 12/21/2012 | 12/31/2016 | Y | STD | 196 |  |  | 0 | 0 | 0 | 12/25/2012 | 12/25/2012 | 2/23/2016 | Connected |  | N
National Grid | LONGMEADOW | 174374 | 01028 | 1000 | Solar | 05_01_216W3 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 08/17/2012 | 47 | 0 | 47 |  |  | 0 | 0 | 0 | 09/24/2013 | 09/24/2013 | 0 | 0 | 0 | 3/14/2013 | 05/29/2012 | 3/2/2018 | Y | STD | 1814 | 11/30/2017 | 02/21/2018 | 55 | 0 | 55 | 3/1/2018 | 3/1/2018 | 3/1/2018 | Connected |  | N
National Grid | NORTH ADAMS | 660756 | 01247 | 15.2 | Solar | 05_09_508L1 | 12/16/2024 | 12/20/2024 | 5 | 3 | 2 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | ATHOL | 695866 | 01331 | 0 | Solar | 05_05_344W5 | 06/03/2025 | 06/09/2025 | 4 | 0 | 4 | 06/10/2025 | 06/10/2025 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2025 | Connected |  | N
National Grid | EASTON | 176330 | 02356 | 16 | Solar | 05_09_702W1 | 07/21/2015 | 07/21/2015 | 3 | 3 | 0 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 |  | 7/27/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 6/22/2016 | 6/22/2016 | 6/22/2016 | Connected |  | N
National Grid | CLINTON | 175004 | 01510 | 500 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 01/15/2014 | 04/03/2014 | 53 | 0 | 53 | 12/31/2013 | 12/21/2012 | 12/31/2016 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  | 2/23/2016 | Connected |  | N
National Grid | LONGMEADOW | 176889 | 01028 | 6.45 | Solar | 05_01_216W3 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2015 |  | 11/18/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 7/26/2016 | 7/26/2016 | 7/26/2016 | Connected |  | N
National Grid | FLORIDA | 708590 | 01247 | 10.24 | Solar | 05_09_508L1 | 08/01/2025 | 10/03/2025 | 8 | 4 | 4 | 10/06/2025 | 10/06/2025 | 75 | 57 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 695799 | 01331 | 11.7 | Solar | 05_05_344W5 | 06/03/2025 | 06/11/2025 | 6 | 2 | 4 | 06/12/2025 | 06/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/03/2025 | 10/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | N
National Grid | EASTON | 176337 | 02356 | 972 | Solar | 05_09_702W1 | 09/16/2015 | 09/16/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2015 | 10/20/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 01/27/2016 | 04/04/2016 | 46 | 0 | 46 | 9/20/2016 | 09/16/2015 | 9/22/2016 | Y | STD | 2 |  |  | 0 | 0 | 0 | 10/23/2017 | 10/23/2017 | 10/23/2017 | Connected |  | N
National Grid | CLINTON | 175006 | 01510 | 750 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 01/15/2014 | 04/03/2014 | 53 | 0 | 53 | 12/31/2013 | 12/21/2012 | 12/31/2016 | Y | STD | 196 |  |  | 0 | 0 | 0 | 9/18/2013 | 9/18/2013 | 2/23/2016 | Connected |  | N
National Grid | LONGMEADOW | 177806 | 01028 | 15 | Solar | 05_01_216W3 | 10/12/2017 | 10/12/2017 | 8 | 0 | 8 | 10/25/2017 | 10/25/2017 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2017 | 10/12/2017 | 9/26/2019 | Y | EXP | 7 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FLORIDA | 705429 | 01247 | 10 | Solar | 05_12_16W7 | 07/16/2025 | 08/06/2025 | 4 | 0 | 4 | 09/03/2025 | 09/03/2025 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 | 07/16/2025 | 11/12/2026 | Y | EXP | 365 | 12/13/2025 | 01/02/2026 | 21 | 0 | 21 |  |  |  | Completion Documents |  | N
National Grid | ATHOL | 712481 | 01331 | 7.6 | Solar | 05_05_344W5 | 08/18/2025 | 09/05/2025 | 5 | 0 | 5 | 09/25/2025 | 09/25/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 12/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 176673 | 02356 | 7.6 | Solar | 05_09_702W1 | 01/04/2016 | 01/04/2016 | 59 | 59 | 0 | 03/30/2016 | 03/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 |  | 1/9/2017 | N | EXP | 272 |  |  | 0 | 0 | 0 | 10/28/2016 | 10/28/2016 | 10/28/2016 | Connected |  | N
National Grid | CLINTON | 175005 | 01510 | 750 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 01/15/2014 | 04/03/2014 | 53 | 0 | 53 | 12/31/2013 | 12/21/2012 | 12/31/2016 | Y | STD | 196 |  |  | 0 | 0 | 0 | 9/18/2013 | 9/18/2013 | 2/23/2016 | Connected |  | N
National Grid | LONGMEADOW | 194838 | 01028 | 3.8 | Solar | 05_01_216W3 | 08/30/2018 | 10/29/2018 | 21 | 21 | 0 | 10/30/2018 | 10/30/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FLORIDA | 734529 | 01247 | 15.58 | Solar | 05_12_16W7 | 11/20/2025 | 11/24/2025 | 2 | 0 | 2 | 11/25/2025 | 11/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATHOL | 746427 | 01331 | 11.7 | Solar | 05_05_344W5 | 01/20/2026 | 01/27/2026 | 5 | 0 | 5 | 01/28/2026 | 01/28/2026 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2026 | Connected |  | N
National Grid | EASTON | 176898 | 02375 | 10 | Solar | 05_09_702W1 | 01/25/2016 | 01/25/2016 | 1 | 1 | 0 | 01/27/2016 | 01/27/2016 | 252 | 0 | 252 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2016 |  | 1/31/2017 | N | EXP | 321 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 175321 | 01510 | 440.8 | Solar | 05_07_92W79 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 299 | 0 | 299 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LONGMEADOW | 197325 | 01028 | 7.6 | Solar | 05_01_216W3 | 10/01/2018 | 10/22/2018 | 3 | 3 | 0 | 10/23/2018 | 10/23/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 174063 | 02038 | 3.8 | Solar | 05_12_16W7 | 09/27/2018 | 11/05/2018 | 24 | 20 | 4 | 11/06/2018 | 11/06/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 11/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  | 10/9/2019 | Connected |  | N
National Grid | ATHOL | 494444 | 01331 | 937.5 | Solar | 05_05_344W6 | 03/01/2023 | 08/03/2023 | 107 | 98 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/04/2023 | 08/28/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 6/25/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | EASTON | 176757 | 02375 | 17.6 | Solar | 05_12_16W7 | 02/24/2016 | 02/24/2016 | 1 | 1 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2016 |  | 3/1/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 8/8/2016 | 8/8/2016 | 8/8/2016 | Connected |  | N
National Grid | LANCASTER | 704632 | 01523 | 480 | Solar | 05_05_344W6 | 10/17/2025 | 10/30/2025 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 | 11/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LONGMEADOW | 177951 | 01028 | 3.8 | Solar | 05_12_16W7 | 08/24/2017 | 08/24/2017 | 9 | 9 | 0 | 09/07/2017 | 09/07/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2017 |  | 8/29/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  | 5/3/2018 | Connected |  | N
National Grid | FRANKLIN | 174754 | 02038 | 56 | Solar | 05_05_344W6 | 01/28/2014 | 01/28/2014 | 7 | 0 | 7 | 02/07/2014 | 02/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2014 |  | 4/30/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 12/8/2014 | 12/8/2014 | 1/9/2015 | Connected |  | N
National Grid | ATHOL | 183731 | 01331 | 11.4 | Solar | 05_12_16W7 | 04/25/2018 | 04/25/2018 | 3 | 0 | 3 | 07/27/2018 | 07/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 | 04/25/2018 | 11/25/2019 | Y | EXP | 482 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 11/1/2019 | Connected |  | N
National Grid | NORTON | 175786 | 02766 | 42 | Solar | 05_05_344W6 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2015 |  | 8/1/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 2/2/2016 | 2/2/2016 | 2/12/2016 | Connected |  | N
National Grid | CLINTON | 207027 | 01510 | 7.6 | Solar | 05_12_16W7 | 02/14/2019 | 02/21/2019 | 3 | 3 | 0 | 02/22/2019 | 02/22/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2019 | 02/14/2019 | 10/11/2019 | Y | EXP | 226 | 08/21/2019 | 08/29/2019 | 8 | 0 | 8 |  |  | 9/20/2019 | Connected |  | N
National Grid | LONGMEADOW | 177485 | 01028 | 128 | Solar | 05_05_344W6 | 09/22/2016 | 09/22/2016 | 5 | 5 | 0 | 10/03/2016 | 10/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2016 |  | 10/1/2017 | N | EXP | 338 |  |  | 0 | 0 | 0 | 12/4/2017 | 12/4/2017 | 12/18/2017 | Connected |  | N
National Grid | FRANKLIN | 220757 | 02038 | 7.6 | Solar | 05_12_16W7 | 08/22/2019 |  | 44 | 39 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 177757 | 01331 | 612 | Solar | 05_05_344W6 | 08/01/2017 | 08/01/2017 | 69 | 69 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/01/2017 | 12/20/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 | 08/01/2017 | 11/30/2021 | Y | STD | 597 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 214054 | 02766 | 10 | Solar | 05_12_16W7 | 03/25/2019 | 04/15/2019 | 15 | 14 | 1 | 04/16/2019 | 04/16/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2019 | 03/25/2019 | 12/16/2019 | Y | EXP | 241 | 06/27/2019 | 08/21/2019 | 55 | 0 | 55 |  |  | 8/24/2019 | Connected |  | N
National Grid | CLINTON | 177797 | 01510 | 636 | Solar | 05_05_344W6 | 08/03/2017 | 08/03/2017 | 48 | 48 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2017 | 12/20/2017 | 35 | 21 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 | 08/03/2017 | 11/30/2021 | Y | STD | 597 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 229044 | 01028 | 7.245 | Solar | 05_12_16W7 | 06/24/2019 | 06/24/2019 | 0 | 0 | 0 | 06/25/2019 | 06/25/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 194820 | 02038 | 600 | Solar | 05_05_344W6 | 09/19/2018 | 10/01/2018 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 01/22/2019 | 73 | 9 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 269654 | 01331 | 7.6 | Solar | 05_12_16W7 | 05/19/2020 | 07/01/2020 | 29 | 26 | 3 | 07/02/2020 | 07/02/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 | 05/19/2020 | 7/28/2021 | Y | EXP | 365 | 12/05/2020 | 01/04/2021 | 30 | 0 | 30 |  |  | 6/3/2021 | Connected |  | N
National Grid | NORTON | 191137 | 02766 | 250 | Solar | 05_05_344W6 | 07/19/2018 | 08/28/2018 | 22 | 14 | 8 |  |  | 58 | 25 | 33 | 01/08/2019 | 02/05/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 02/05/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 298842 | 01510 | 7.6 | Solar | 05_12_16W7 | 06/29/2020 | 08/24/2020 | 39 | 38 | 1 | 08/25/2020 | 08/25/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 548490 | 01028 | 462.5 | Solar | 05_05_344W6 | 08/23/2023 | 10/18/2023 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2023 | 03/08/2024 | 97 | 79 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 310462 | 02038 | 10 | Solar | 05_12_16W7 | 10/02/2020 | 10/06/2020 | 1 | 0 | 1 | 10/07/2020 | 10/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2021 | Connected |  | Y
National Grid | ATHOL | 177446 | 01331 | 311 | Solar | 05_09_702W1 | 09/16/2016 | 09/16/2016 | 0 | 0 | 0 | 09/16/2016 | 09/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2016 | 09/16/2016 | 9/21/2017 | Y | EXP | 337 | 10/16/2017 | 12/06/2017 | 30 | 0 | 30 | 12/13/2017 | 12/13/2017 | 12/13/2017 | Connected |  | N
National Grid | NORTON | 316112 | 02766 | 10 | Solar | 05_12_16W7 | 12/18/2020 | 12/30/2020 | 6 | 0 | 6 | 12/31/2020 | 12/31/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/18/2020 | 6/15/2022 | Y | EXP | 365 | 08/02/2021 | 08/27/2021 | 23 | 1 | 22 |  |  | 9/13/2021 | Connected |  | N
National Grid | LANCASTER | 177619 | 01523 | 2200 | Solar | 05_09_702W1 | 11/08/2017 | 11/08/2017 | 55 | 30 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2018 | 04/11/2018 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/14/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 327499 | 02148 | 7.6 | Solar | 05_12_16W7 | 12/09/2020 | 12/13/2020 | 2 | 0 | 2 | 12/14/2020 | 12/14/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 178106 | 02038 | 3230 | Solar | 05_09_702W1 | 09/08/2017 | 10/31/2017 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2017 | 11/15/2017 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/16/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 328785 | 01331 | 10 | Solar | 05_12_16W7 | 12/15/2020 | 12/18/2020 | 2 | 0 | 2 | 12/21/2020 | 12/21/2020 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/15/2020 | 5/19/2022 | Y | EXP | 365 | 04/21/2021 | 05/11/2021 | 20 | 0 | 20 |  |  | 9/20/2021 | Connected |  | Y
National Grid | NORTON | 178105 | 02766 | 8730 | Solar | 05_09_702W1 | 09/08/2017 | 10/24/2017 | 30 | 20 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2017 | 11/15/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/16/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 336201 | 01510 | 7.6 | Solar | 05_12_16W7 | 01/15/2021 | 01/25/2021 | 4 | 0 | 4 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2021 | 01/15/2021 | 4/9/2022 | Y | EXP | 365 | 08/06/2021 | 12/21/2021 | 137 | 7 | 130 |  |  | 2/26/2022 | Connected |  | N
National Grid | MALDEN | 178458 | 02148 | 10 | Solar | 05_09_702W1 | 01/18/2018 | 01/18/2018 | 10 | 2 | 8 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2018 |  | 1/23/2019 | N | EXP | 32 |  |  | 0 | 0 | 0 |  |  | 7/26/2018 | Connected |  | N
National Grid | FRANKLIN | 343326 | 02038 | 6 | Solar | 05_12_16W7 | 03/31/2021 | 04/07/2021 | 4 | 0 | 4 | 04/08/2021 | 04/08/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2021 |  | 5/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2021 | Connected |  | N
National Grid | ATHOL | 185392 | 01331 | 4998 | Solar | 05_09_702W1 | 06/29/2018 | 06/29/2018 | 32 | 28 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2018 | 10/12/2018 | 62 | 39 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 345364 | 02375 | 3.8 | Solar | 05_12_16W7 | 03/19/2021 | 03/29/2021 | 6 | 6 | 0 | 03/30/2021 | 03/30/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 03/19/2021 | 7/30/2022 | Y | EXP | 365 | 06/05/2021 | 06/18/2021 | 14 | 0 | 14 |  |  | 9/16/2021 | Connected |  | N
National Grid | CLINTON | 188028 | 01510 | 5000 | Solar | 05_09_702W1 | 06/13/2018 | 06/13/2018 | 21 | 21 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/16/2018 | 08/15/2018 | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 378586 | 02149 | 7.6 | Solar | 05_12_16W7 | 09/13/2021 | 01/10/2022 | 2 | 0 | 2 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2021 | 09/13/2021 | 8/30/2023 | Y | EXP | 365 | 02/22/2022 | 04/06/2022 | 43 | 0 | 43 |  |  | 9/3/2022 | Connected |  | N
National Grid | FRANKLIN | 200891 | 02038 | 0 | Solar | 05_09_702W1 | 11/13/2018 | 12/04/2018 | 7 | 0 | 7 | 12/05/2018 | 12/05/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | REVERE | 397076 | 02151 | 6 | Solar | 05_12_16W7 | 01/26/2022 | 02/02/2022 | 5 | 0 | 5 | 02/03/2022 | 02/03/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2022 | 01/26/2022 | 5/26/2024 | Y | EXP | 365 | 10/05/2022 | 01/30/2023 | 118 | 0 | 118 |  |  | 9/18/2023 | Connected |  | N
National Grid | FRANKLIN | 222507 | 02038 | 7.6 | Solar | 05_09_702W1 | 05/07/2019 | 05/09/2019 | 2 | 2 | 0 | 05/10/2019 | 05/10/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2019 | 05/07/2019 | 1/22/2020 | Y | EXP | 236 | 08/21/2019 | 10/10/2019 | 50 | 0 | 50 |  |  | 10/29/2019 | Connected |  | N
National Grid | EVERETT | 478025 | 02149 | 15.2 | Solar | 05_12_16W7 | 11/16/2022 | 11/17/2022 | 1 | 0 | 1 | 11/18/2022 | 11/18/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  | 12/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | FRANKLIN | 238129 | 02038 | 25 | Solar | 05_09_702W1 | 06/18/2019 | 07/10/2019 | 15 | 15 | 0 | 07/11/2019 | 07/11/2019 | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2019 |  | 8/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 485036 | 02149 | 7.6 | Solar | 05_12_16W7 | 01/04/2023 | 03/06/2023 | 41 | 35 | 6 | 03/07/2023 | 03/07/2023 | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2023 |  | 9/16/2024 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 280094 | 02038 | 3.8 | Solar | 05_09_702W1 | 05/27/2020 | 05/28/2020 | 1 | 1 | 0 | 05/29/2020 | 05/29/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2020 |  | 5/27/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 530667 | 02148 | 10 | Solar | 05_12_16W7 | 06/09/2023 | 06/13/2023 | 2 | 0 | 2 | 06/14/2023 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 297385 | 02038 | 4950 | Other | 05_09_702W1 | 08/17/2020 | 09/24/2020 | 25 | 20 | 5 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 551574 | 02151 | 10 | Solar | 05_12_16W7 | 09/13/2023 | 10/02/2023 | 14 | 12 | 2 | 10/03/2023 | 10/03/2023 | 22 | 0 | 22 | 11/16/2023 | 02/21/2024 | 65 | 3 | 62 |  |  | 0 | 0 | 0 |  | 02/21/2024 | 65 | 3 | 62 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 4/11/2025 | N | EXP | 365 | 05/21/2024 | 11/05/2024 | 169 | 0 | 169 |  |  | 8/4/2024 | Connected |  | N
National Grid | FRANKLIN | 305628 | 02038 | 9.8 | Solar | 05_09_702W1 | 08/07/2020 | 08/10/2020 | 0 | 0 | 0 | 08/11/2020 | 08/11/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 |  | 2/26/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2021 | Connected |  | N
National Grid | REVERE | 569775 | 02151 | 6 | Solar | 05_12_16W7 | 11/22/2023 | 12/05/2023 | 8 | 4 | 4 | 12/06/2023 | 12/06/2023 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 | 11/22/2023 | 4/23/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2024 | Connected |  | N
National Grid | FRANKLIN | 352917 | 02038 | 10 | Solar | 05_09_702W1 | 04/29/2021 | 04/30/2021 | 1 | 1 | 0 | 05/03/2021 | 05/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 | 04/29/2021 | 10/4/2022 | Y | EXP | 365 | 08/11/2021 | 10/04/2021 | 53 | 3 | 50 |  |  | 10/5/2021 | Connected |  | N
National Grid | REVERE | 570139 | 02151 | 6 | Solar | 05_12_16W7 | 11/20/2023 | 11/30/2023 | 7 | 2 | 5 | 12/01/2023 | 12/01/2023 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 360037 | 02038 | 11.4 | Solar | 05_09_702W1 | 05/24/2021 | 06/02/2021 | 6 | 6 | 0 | 06/03/2021 | 06/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2021 |  | 7/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2022 | Connected |  | N
National Grid | REVERE | 589342 | 02151 | 6 | Solar | 05_12_16W7 | 02/29/2024 | 03/04/2024 | 2 | 0 | 2 | 03/05/2024 | 03/05/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/29/2024 | 3/12/2025 | Y | EXP | 365 | 03/20/2024 | 05/02/2024 | 44 | 0 | 44 |  |  | 5/12/2024 | Connected |  | N
National Grid | FRANKLIN | 363344 | 02038 | 10 | Solar | 05_09_702W1 | 06/24/2021 | 06/29/2021 | 3 | 0 | 3 | 06/30/2021 | 06/30/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2021 | 06/24/2021 | 11/9/2022 | Y | EXP | 365 | 09/24/2021 | 11/04/2021 | 42 | 4 | 38 |  |  | 11/10/2021 | Connected |  | N
National Grid | EVERETT | 590680 | 02149 | 6 | Solar | 05_12_16W7 | 02/20/2024 | 03/15/2024 | 19 | 18 | 1 | 03/18/2024 | 03/18/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 11/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 375005 | 02038 | 17.28 | Solar | 05_09_702W1 | 08/19/2021 | 09/10/2021 | 15 | 13 | 2 | 09/13/2021 | 09/13/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 11/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2022 | Connected |  | N
National Grid | EVERETT | 591953 | 02149 | 12 | Solar | 05_12_16W7 | 02/22/2024 | 04/29/2024 | 46 | 26 | 20 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  | 5/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 483184 | 01331 | 6 | Solar | 05_09_702W1 | 12/07/2022 | 12/12/2022 | 4 | 3 | 1 | 12/13/2022 | 12/13/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2023 |  | 8/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N
National Grid | REVERE | 596663 | 02151 | 5 | Solar | 05_12_16W7 | 04/12/2024 | 04/23/2024 | 7 | 5 | 2 | 04/24/2024 | 04/24/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 | 04/12/2024 | 5/17/2025 | Y | EXP | 365 | 08/22/2024 | 09/06/2024 | 16 | 0 | 16 |  |  | 9/27/2024 | Connected |  | N
National Grid | ATHOL | 490479 | 01331 | 15.08 | Solar | 05_09_702W1 | 01/06/2023 | 01/09/2023 | 1 | 0 | 1 | 01/10/2023 | 01/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2023 |  | 3/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | Y
National Grid | REVERE | 610885 | 02151 | 6 | Solar | 05_12_16W7 | 05/14/2024 | 06/07/2024 | 3 | 0 | 3 | 06/10/2024 | 06/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | ATHOL | 506129 | 01331 | 10 | Solar | 05_09_702W1 | 05/08/2023 | 05/09/2023 | 1 | 0 | 1 | 05/10/2023 | 05/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2023 | 05/08/2023 | 7/12/2024 | Y | EXP | 365 | 09/07/2023 | 10/25/2023 | 49 | 0 | 49 |  |  | 10/27/2023 | Connected |  | N
National Grid | REVERE | 652410 | 02151 | 5.76 | Solar | 05_12_16W7 | 11/14/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | ATHOL | 522009 | 01331 | 10 | Solar | 05_09_702W1 | 05/18/2023 |  | 255 | 24 | 231 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 655522 | 02149 | 3.8 | Solar | 05_12_16W7 | 11/20/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2025 | Connected |  | N
National Grid | ATHOL | 526873 | 01331 | 6 | Solar | 05_09_702W1 | 05/16/2023 | 06/21/2023 | 14 | 12 | 2 | 06/22/2023 | 06/22/2023 | 110 | 89 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 |  | 12/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N
National Grid | EVERETT | 669837 | 02149 | 10 | Solar | 05_12_16W7 | 02/04/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2025 | Connected |  | N
National Grid | ATHOL | 557213 | 01331 | 10 | Solar | 05_09_702W1 | 10/25/2023 | 11/14/2023 | 14 | 13 | 1 | 11/15/2023 | 11/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2023 |  | 1/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2024 | Connected |  | N
National Grid | EVERETT | 173494 | 02149 | 10 | Solar | 05_12_16W8 | 04/24/2018 | 04/24/2018 | 1 | 0 | 1 | 05/08/2018 | 05/08/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2018 |  | 5/25/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2019 | Connected |  | N
National Grid | ATHOL | 530162 | 01331 | 10 | Solar | 05_09_702W1 | 06/08/2023 | 06/13/2023 | 4 | 3 | 1 | 06/14/2023 | 06/14/2023 | 67 | 48 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2023 |  | 10/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2024 | Connected |  | N
National Grid | EVERETT | 173375 | 02149 | 10 | Solar | 05_12_16W8 | 04/11/2018 | 04/11/2018 | 0 | 0 | 0 | 05/10/2018 | 05/10/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 544256 | 01331 | 10 | Solar | 05_09_702W1 | 07/28/2023 | 07/31/2023 | 1 | 0 | 1 | 08/01/2023 | 08/01/2023 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 |  | 10/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | REVERE | 176303 | 02151 | 4.3 | Solar | 05_12_16W8 | 09/15/2015 | 09/15/2015 | 4 | 4 | 0 | 09/22/2015 | 09/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 | 09/15/2015 | 9/21/2016 | Y | EXP | 348 | 09/01/2016 | 08/31/2016 | 0 | 0 | 0 | 9/12/2016 | 9/12/2016 | 9/12/2016 | Connected |  | N
National Grid | ATHOL | 577497 | 01331 | 7.6 | Solar | 05_09_702W1 | 01/31/2024 | 02/07/2024 | 5 | 3 | 2 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2024 | Connected |  | N
National Grid | EVERETT | 176787 | 02149 | 6 | Solar | 05_12_16W8 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 267 | 0 | 267 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 1/20/2017 | N | EXP | 332 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 618189 | 01331 | 7.6 | Solar | 05_09_702W1 | 06/14/2024 | 07/09/2024 | 4 | 0 | 4 | 07/10/2024 | 07/10/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 06/14/2024 | 8/14/2025 | Y | EXP | 365 | 10/03/2024 | 11/18/2024 | 47 | 0 | 47 |  |  | 12/18/2024 | Connected |  | N
National Grid | MALDEN | 177801 | 02148 | 15.2 | Solar | 05_12_16W8 | 10/09/2017 | 10/09/2017 | 13 | 10 | 3 | 10/25/2017 | 10/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2017 |  | 10/16/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 | 12/13/2017 | 12/13/2017 | 12/13/2017 | Connected |  | N
National Grid | ATHOL | 627710 | 01331 | 12.18 | Solar | 05_09_702W1 | 08/29/2024 | 10/25/2024 | 3 | 1 | 2 | 10/28/2024 | 10/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2024 | 08/29/2024 | 12/16/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | MALDEN | 194567 | 02148 | 7.6 | Solar | 05_12_16W8 | 08/29/2018 | 09/10/2018 | 0 | 0 | 0 | 09/11/2018 | 09/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 | 08/29/2018 | 5/28/2019 | Y | EXP | 259 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | ATHOL | 634477 | 01331 | 3.8 | Solar | 05_09_702W1 | 08/21/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 08/21/2024 | 9/24/2025 | Y | EXP | 365 | 01/08/2025 | 03/05/2025 | 57 | 0 | 57 |  |  | 3/21/2025 | Connected |  | N
National Grid | MALDEN | 195927 | 02148 | 7.6 | Solar | 05_12_16W8 | 09/13/2018 | 10/23/2018 | 0 | 0 | 0 | 10/24/2018 | 10/24/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 635856 | 01331 | 0 | Battery Add-On | 05_09_702W1 | 08/27/2024 | 08/29/2024 | 2 | 0 | 2 | 08/30/2024 | 08/30/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 203538 | 02149 | 3.8 | Solar | 05_12_16W8 | 12/27/2018 | 01/25/2019 | 19 | 19 | 0 | 01/28/2019 | 01/28/2019 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 642396 | 01366 | 10 | Solar | 05_09_702W1 | 09/24/2024 | 10/25/2024 | 4 | 1 | 3 | 10/28/2024 | 10/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 09/24/2024 | 1/6/2026 | Y | EXP | 365 | 09/04/2025 | 09/29/2025 | 26 | 0 | 26 |  |  | 11/11/2025 | Connected |  | N
National Grid | MALDEN | 256448 | 02148 | 10 | Solar | 05_12_16W8 | 10/02/2019 | 10/07/2019 | 2 | 0 | 2 | 10/08/2019 | 10/08/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 | 10/02/2019 | 10/13/2021 | Y | EXP | 365 | 07/02/2020 | 03/29/2021 | 271 | 5 | 266 |  |  | 6/15/2021 | Connected |  | N
National Grid | ATHOL | 642630 | 01331 | 3.8 | Solar | 05_09_702W1 | 09/24/2024 | 01/06/2025 | 20 | 15 | 5 | 01/07/2025 | 01/07/2025 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | EVERETT | 269219 | 02149 | 3.8 | Solar | 05_12_16W8 | 12/18/2019 |  | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/18/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 651707 | 01331 | 7.6 | Solar | 05_09_702W1 | 11/03/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | MALDEN | 277078 | 02148 | 3.8 | Solar | 05_12_16W8 | 02/06/2020 | 02/18/2020 | 6 | 2 | 4 | 02/19/2020 | 02/19/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2020 | 02/06/2020 | 3/31/2021 | Y | EXP | 365 | 06/24/2020 | 01/11/2021 | 202 | 5 | 197 |  |  | 3/20/2021 | Connected |  | N
National Grid | ATHOL | 652705 | 01331 | 5.76 | Solar | 05_09_702W1 | 11/14/2024 | 11/20/2024 | 5 | 0 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 11/14/2024 | 4/8/2026 | Y | EXP | 365 | 06/04/2025 | 11/21/2025 | 171 | 0 | 171 |  |  | 12/11/2025 | Connected |  | N
National Grid | EVERETT | 279550 | 02149 | 7.6 | Solar | 05_12_16W8 | 04/13/2020 | 04/27/2020 | 8 | 8 | 0 | 04/28/2020 | 04/28/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 | 04/13/2020 | 4/26/2021 | Y | EXP | 365 | 08/18/2020 | 12/12/2020 | 116 | 0 | 116 |  |  | 12/16/2020 | Connected |  | N
National Grid | ATHOL | 673827 | 01331 | 5.76 | Solar | 05_09_702W1 | 02/24/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 299562 | 02148 | 6 | Solar | 05_12_16W8 | 08/18/2020 | 08/20/2020 | 1 | 0 | 1 | 08/21/2020 | 08/21/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 | 08/18/2020 | 6/24/2022 | Y | EXP | 365 | 02/09/2021 | 04/10/2021 | 60 | 0 | 60 |  |  | 5/4/2022 | Connected |  | N
National Grid | ATHOL | 675149 | 01331 | 5.76 | Solar | 05_09_702W1 | 03/05/2025 | 03/11/2025 | 4 | 0 | 4 | 03/12/2025 | 03/12/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | MALDEN | 471406 | 02148 | 14.976 | Solar | 05_12_16W8 | 11/16/2022 | 11/28/2022 | 8 | 7 | 1 | 11/29/2022 | 11/29/2022 | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 | 11/16/2022 | 7/23/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 715910 | 01331 | 7.6 | Solar | 05_09_702W1 | 09/12/2025 | 10/28/2025 | 2 | 0 | 2 | 10/29/2025 | 10/29/2025 | 75 | 25 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 483382 | 02149 | 8.7 | Solar | 05_12_16W8 | 02/22/2023 | 03/01/2023 | 5 | 4 | 1 | 03/02/2023 | 03/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 665917 | 01331 | 996 | Solar | 05_09_702W2 | 04/17/2025 | 05/13/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/14/2025 | 06/11/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MALDEN | 539835 | 02148 | 5.76 | Solar | 05_12_16W8 | 07/10/2023 | 07/17/2023 | 3 | 0 | 3 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2023 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | ATHOL | 685853 | 01331 | 3.8 | Solar | 05_09_702W2 | 04/17/2025 | 05/19/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 99 | 83 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 1/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | EVERETT | 538307 | 02149 | 3.8 | Solar | 05_12_16W8 | 07/04/2023 | 07/06/2023 | 2 | 0 | 2 | 07/07/2023 | 07/07/2023 | 63 | 42 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 07/04/2023 | 10/14/2024 | Y | EXP | 365 | 07/09/2024 | 07/30/2024 | 22 | 0 | 22 |  |  | 8/5/2024 | Connected |  | N
National Grid | ATHOL | 737148 | 01331 | 15.2 | Solar | 05_09_702W2 | 12/01/2025 | 12/02/2025 | 1 | 0 | 1 | 12/03/2025 | 12/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 542060 | 02151 | 3.8 | Solar | 05_12_16W8 | 07/19/2023 | 07/29/2023 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2023 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | ATHOL | 744824 | 01331 | 7.6 | Solar | 05_09_702W2 | 01/14/2026 | 01/20/2026 | 1 | 0 | 1 | 02/06/2026 | 02/06/2026 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | REVERE | 572705 | 02151 | 7.83 | Solar | 05_12_16W8 | 11/28/2023 | 12/21/2023 | 18 | 16 | 2 | 12/22/2023 | 12/22/2023 | 104 | 84 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 747023 | 01331 | 160 | Solar | 05_09_702W2 | 02/03/2026 |  | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | REVERE | 575019 | 02151 | 9.86 | Solar | 05_12_16W8 | 12/14/2023 | 12/19/2023 | 3 | 1 | 2 | 12/20/2023 | 12/20/2023 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 12/14/2023 | 3/20/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2024 | Connected |  | N
National Grid | ATHOL | 751317 | 01331 | 7.6 | Solar | 05_09_702W2 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 587620 | 02151 | 11 | Solar | 05_12_16W8 | 02/09/2024 | 02/28/2024 | 13 | 11 | 2 | 02/29/2024 | 02/29/2024 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  | 5/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2024 | Connected |  | N
National Grid | ATHOL | 174977 | 01331 | 950 | Solar | 05_09_702W2 | 09/16/2011 | 09/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 588803 | 02151 | 7.6 | Solar | 05_12_16W8 | 04/09/2024 | 04/15/2024 | 4 | 0 | 4 | 04/16/2024 | 04/16/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2024 | Connected |  | N
National Grid | ATHOL | 175047 | 01331 | 1000 | Solar | 05_09_702W2 | 06/08/2011 | 06/08/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2012 | 06/08/2011 | 8/19/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/14/2012 | 8/14/2012 | 7/6/2012 | Connected |  | N
National Grid | REVERE | 602201 | 02151 | 6 | Solar | 05_12_16W8 | 04/22/2024 | 04/23/2024 | 1 | 0 | 1 | 04/24/2024 | 04/24/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2024 | 04/22/2024 | 11/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | ATHOL | 175046 | 01331 | 1000 | Solar | 05_09_702W2 | 06/08/2011 | 06/08/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2012 | 06/08/2011 | 8/19/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/14/2012 | 8/14/2012 | 7/6/2012 | Connected |  | N
National Grid | REVERE | 602855 | 02151 | 3.8 | Solar | 05_12_16W8 | 04/17/2024 | 04/18/2024 | 1 | 0 | 1 | 04/19/2024 | 04/19/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PETERSHAM | 175048 | 01366 | 750 | Solar | 05_09_702W2 | 06/08/2011 | 06/08/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2012 | 06/08/2011 | 8/19/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/14/2012 | 8/14/2012 | 7/6/2012 | Connected |  | N
National Grid | REVERE | 618248 | 02151 | 7.25 | Solar | 05_12_16W8 | 06/17/2024 | 07/15/2024 | 12 | 9 | 3 | 07/16/2024 | 07/16/2024 | 30 | 17 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 06/17/2024 | 9/30/2025 | Y | EXP | 365 | 11/13/2024 | 03/06/2025 | 114 | 0 | 114 |  |  | 3/18/2025 | Connected |  | N
National Grid | ATHOL | 176742 | 01331 | 1100 | Solar | 05_09_702W2 | 11/03/2015 | 11/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2015 | 12/04/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/8/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 642469 | 02151 | 3.84 | Solar | 05_12_16W8 | 09/24/2024 | 10/18/2024 | 4 | 0 | 4 | 10/21/2024 | 10/21/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | ATHOL | 176781 | 01331 | 2000 | Solar | 05_09_702W2 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2015 | 12/04/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 642393 | 02151 | 7.6 | Solar | 05_12_16W8 | 09/24/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/24/2024 | 12/17/2025 | Y | EXP | 365 | 06/18/2025 | 10/20/2025 | 125 | 0 | 125 |  |  | 10/31/2025 | Connected |  | N
National Grid | ATHOL | 177445 | 01331 | 336 | Solar | 05_09_702W2 | 09/16/2016 | 09/16/2016 | 0 | 0 | 0 | 09/16/2016 | 09/16/2016 | 381 | 0 | 381 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 |  | 1/31/2019 | N | EXP | 842 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 644001 | 02151 | 7.6 | Solar | 05_12_16W8 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 |  | 12/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 178025 | 01331 | 4980 | Solar | 05_09_702W2 | 08/31/2017 | 10/03/2017 | 23 | 22 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2017 | 10/30/2017 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 653527 | 02151 | 3.8 | Solar | 05_12_16W8 | 11/15/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/15/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | ATHOL | 178250 | 01331 | 2000 | Solar | 05_09_702W2 | 03/27/2018 | 03/27/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2018 | 06/13/2018 | 44 | 31 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/2/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 655554 | 02151 | 7.6 | Solar | 05_12_16W8 | 12/16/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2025 | Connected |  | N
National Grid | ATHOL | 178311 | 01331 | 1625 | Solar | 05_09_702W2 | 02/26/2018 | 02/26/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2018 | 07/24/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/3/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 656727 | 02151 | 7.6 | Solar | 05_12_16W8 | 11/25/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/25/2024 | 5/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | ATHOL | 178397 | 01331 | 3332 | Solar | 05_09_702W2 | 03/05/2018 | 03/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2018 | 04/17/2018 | 20 | 7 | 13 |  |  | 0 | 0 | 0 | 01/09/2019 | 01/06/2020 | 249 | 42 | 207 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 658086 | 02151 | 8.7 | Solar | 05_12_16W8 | 12/10/2024 | 01/03/2025 | 4 | 1 | 3 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | ORANGE | 178482 | 01364 | 1350 | Solar | 05_09_702W2 | 04/03/2018 | 04/05/2018 | 11 | 11 | 0 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 665567 | 02151 | 7.6 | Solar | 05_12_16W8 | 01/14/2025 | 01/29/2025 | 8 | 6 | 2 | 01/30/2025 | 01/30/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | ATHOL | 178671 | 01331 | 8300 | Solar | 05_09_702W2 | 03/19/2018 |  | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/25/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 671008 | 02151 | 3.8 | Solar | 05_12_16W8 | 04/18/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 186829 | 01364 | 250 | Solar | 05_09_702W2 | 06/07/2018 | 06/07/2018 | 17 | 16 | 1 | 07/10/2018 | 07/10/2018 | 14 | 13 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 671761 | 02151 | 5.76 | Solar | 05_12_16W8 | 02/17/2025 | 03/20/2025 | 9 | 4 | 5 | 03/21/2025 | 03/21/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2025 | Connected |  | N
National Grid | ATHOL | 671747 | 01331 | 7.6 | Solar | 05_12_16W8 | 02/17/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | REVERE | 187787 | 02151 | 15.2 | Solar | 05_09_702W2 | 06/12/2018 | 06/12/2018 | 54 | 51 | 3 | 08/28/2018 | 08/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 |  | 10/18/2019 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 9/13/2019 | Connected |  | N
National Grid | ATHOL | 681063 | 01331 | 7.6 | Solar | 05_12_16W8 | 03/28/2025 | 04/10/2025 | 2 | 0 | 2 | 04/18/2025 | 04/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 188362 | 02151 | 8300 | Solar | 05_09_702W2 | 06/18/2018 | 06/18/2018 | 30 | 30 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/01/2018 | 08/17/2018 | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 730402 | 01331 | 2.56 | Solar | 05_12_16W8 | 10/30/2025 | 11/19/2025 | 13 | 12 | 1 | 11/20/2025 | 11/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 190726 | 02151 | 4940 | Solar | 05_09_702W2 | 07/26/2018 | 08/23/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2018 | 08/28/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 654022 | 01331 | 6.46 | Solar | 05_12_17J1 | 11/13/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | REVERE | 252830 | 02151 | 10 | Solar | 05_09_702W2 | 09/24/2019 | 09/30/2019 | 3 | 0 | 3 | 10/01/2019 | 10/01/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 213815 | 01364 | 0 | Solar | 05_12_17J2 | 03/14/2019 | 03/15/2019 | 2 | 0 | 2 | 09/12/2019 | 09/12/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2019 |  | 3/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2020 | Connected |  | N
National Grid | REVERE | 265840 | 02151 | 0 | Solar | 05_09_702W2 | 11/16/2019 | 11/21/2019 | 3 | 0 | 3 | 11/22/2019 | 11/22/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 | 11/16/2019 | 8/31/2022 | Y | EXP | 44 | 07/31/2020 | 08/17/2020 | 17 | 0 | 17 |  |  | 8/18/2022 | Connected |  | N
National Grid | ORANGE | 635834 | 01364 | 9.074 | Solar | 05_12_17J2 | 08/27/2024 | 10/18/2024 | 2 | 0 | 2 | 10/21/2024 | 10/21/2024 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 273962 | 02151 | 2500 | Solar | 05_09_702W2 | 10/27/2020 | 02/05/2021 | 67 | 58 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2021 | 03/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 646255 | 01364 | 7.22 | Solar | 05_12_17J2 | 10/10/2024 | 11/22/2024 | 26 | 22 | 4 | 11/25/2024 | 11/25/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 | 10/10/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | REVERE | 285646 | 02151 | 10 | Solar | 05_09_702W2 | 04/29/2020 | 05/04/2020 | 2 | 2 | 0 | 05/05/2020 | 05/05/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2020 | Connected |  | N
National Grid | ATHOL | 750365 | 01331 | 0 | Battery Add-On | 05_12_17J3 | 02/10/2026 | 02/17/2026 | 4 | 0 | 4 | 02/18/2026 | 02/18/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 302401 | 02151 | 10 | Solar | 05_09_702W2 | 09/25/2020 | 10/01/2020 | 3 | 0 | 3 | 10/02/2020 | 10/02/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2020 | 09/25/2020 | 11/2/2021 | Y | EXP | 365 | 01/27/2021 | 02/12/2021 | 15 | 0 | 15 |  |  | 3/31/2021 | Connected |  | N
National Grid | ATHOL | 268101 | 01331 | 7.6 | Solar | 05_12_17J3 | 12/03/2019 | 12/10/2019 | 5 | 4 | 1 | 12/11/2019 | 12/11/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 302982 | 02151 | 9.36 | Solar | 05_09_702W2 | 07/24/2020 | 07/27/2020 | 0 | 0 | 0 | 07/28/2020 | 07/28/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2020 |  | 7/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2020 | Connected |  | N
National Grid | ATHOL | 322458 | 01331 | 7.6 | Solar | 05_12_17J3 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 339524 | 02151 | 0 | Solar | 05_09_702W2 | 02/03/2021 | 02/10/2021 | 4 | 3 | 1 | 02/11/2021 | 02/11/2021 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 | 02/03/2021 | 4/18/2022 | Y | EXP | 365 | 04/07/2021 | 04/13/2021 | 6 | 0 | 6 |  |  | 2/23/2022 | Connected |  | N
National Grid | ATHOL | 387786 | 01331 | 9.28 | Solar | 05_12_17J3 | 11/01/2021 | 12/23/2021 | 7 | 4 | 3 | 11/12/2021 | 11/12/2021 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  | 8/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2022 | Connected |  | Y
National Grid | REVERE | 372949 | 02151 | 14.07 | Solar | 05_09_702W2 | 08/19/2021 | 03/02/2022 | 133 | 124 | 9 | 03/03/2022 | 03/03/2022 | 59 | 42 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROYALSTON | 598869 | 01368 | 6.08 | Solar | 05_12_17J4 | 03/29/2024 | 05/01/2024 | 22 | 20 | 2 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 374024 | 02151 | 0 | Solar | 05_09_702W2 | 08/12/2021 | 12/22/2021 | 22 | 21 | 1 | 09/14/2021 | 09/14/2021 | 92 | 66 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 561621 | 01368 | 0 | Solar | 05_12_17J5 | 10/12/2023 | 10/19/2023 | 6 | 4 | 2 | 10/20/2023 | 10/20/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 435569 | 02151 | 9.86 | Solar | 05_09_702W2 | 06/23/2022 | 06/24/2022 | 1 | 0 | 1 | 06/27/2022 | 06/27/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/23/2022 | 11/13/2023 | Y | EXP | 365 | 10/06/2022 | 11/10/2022 | 36 | 0 | 36 |  |  | 4/27/2023 | Connected |  | N
National Grid | ATHOL | 649388 | 01331 | 6 | Solar | 05_12_17J5 | 10/24/2024 | 11/15/2024 | 7 | 3 | 4 | 11/18/2024 | 11/18/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 479424 | 02151 | 25 | Solar | 05_09_702W2 | 11/28/2022 | 12/05/2022 | 5 | 4 | 1 | 12/06/2022 | 12/06/2022 | 73 | 53 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  | 4/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2023 | Connected |  | N
National Grid | ORANGE | 738090 | 01364 | 44.6 | Solar | 05_12_17J6 | 01/07/2026 | 01/08/2026 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 480601 | 02151 | 18.56 | Solar | 05_09_702W2 | 11/28/2022 | 12/05/2022 | 5 | 4 | 1 | 12/06/2022 | 12/06/2022 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 | 11/28/2022 | 10/19/2024 | Y | EXP | 365 | 05/02/2023 | 10/19/2023 | 171 | 0 | 171 |  |  | 10/24/2023 | Connected |  | N
National Grid | ATHOL | 175209 | 01331 | 12 | Solar | 05_12_17J6 | 12/05/2012 | 12/05/2012 | 10 | 5 | 5 | 12/21/2012 | 12/21/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2013 |  | 2/28/2013 | N | EXP | 13 |  |  | 0 | 0 | 0 | 2/15/2013 | 2/15/2013 | 3/14/2013 | Connected |  | N
National Grid | REVERE | 517086 | 02151 | 6 | Solar | 05_09_702W2 | 06/09/2023 | 06/15/2023 | 5 | 4 | 1 | 06/16/2023 | 06/16/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 | 06/09/2023 | 8/20/2024 | Y | EXP | 365 | 11/10/2023 | 01/12/2024 | 64 | 3 | 61 |  |  | 1/18/2024 | Connected |  | N
National Grid | ATHOL | 328772 | 01331 | 7.6 | Solar | 05_12_17J6 | 11/30/2020 | 12/08/2020 | 5 | 0 | 5 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 11/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2021 | Connected |  | N
National Grid | REVERE | 520344 | 02151 | 14.79 | Solar | 05_09_702W2 | 04/19/2023 | 05/03/2023 | 10 | 7 | 3 | 05/04/2023 | 05/04/2023 | 112 | 97 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 |  | 1/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/18/2024 | Connected |  | N
National Grid | ATHOL | 421359 | 01331 | 0 | Solar | 05_12_17J6 | 04/01/2022 | 04/04/2022 | 1 | 0 | 1 | 04/05/2022 | 04/05/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2022 |  | 5/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2022 | Connected |  | N
National Grid | REVERE | 526584 | 02151 | 3.8 | Solar | 05_09_702W2 | 06/13/2023 | 06/14/2023 | 1 | 0 | 1 | 06/15/2023 | 06/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2023 | 06/13/2023 | 7/31/2024 | Y | EXP | 365 | 08/24/2023 | 12/26/2023 | 125 | 3 | 122 |  |  | 1/4/2024 | Connected |  | Y
National Grid | ORANGE | 521915 | 01364 | 10 | Solar | 05_12_17J6 | 05/09/2023 | 05/11/2023 | 2 | 0 | 2 | 05/12/2023 | 05/12/2023 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2023 | 05/09/2023 | 1/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 556896 | 02151 | 8.99 | Solar | 05_09_702W2 | 11/15/2023 | 09/22/2023 | 3 | 1 | 2 | 11/20/2023 | 11/20/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 |  | 12/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2024 | Connected |  | N
National Grid | ATHOL | 612896 | 01331 | 5.76 | Solar | 05_12_17J6 | 05/22/2024 | 05/29/2024 | 2 | 0 | 2 | 05/30/2024 | 05/30/2024 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/22/2024 | 7/5/2025 | Y | EXP | 365 | 03/05/2025 | 03/04/2025 | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | REVERE | 556457 | 02151 | 25 | Solar | 05_09_702W2 | 09/28/2023 | 10/02/2023 | 2 | 0 | 2 | 10/03/2023 | 10/03/2023 | 63 | 42 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | ATHOL | 175514 | 01331 | 500 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 550490 | 02155 | 25 | Solar | 05_09_702W2 | 08/25/2023 | 09/12/2023 | 11 | 9 | 2 | 09/13/2023 | 09/13/2023 | 139 | 122 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 |  | 6/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2024 | Connected |  | N
National Grid | ROYALSTON | 175692 | 01368 | 15.8 | Solar | 05_07_92W79 | 05/23/2014 | 05/23/2014 | 5 | 0 | 5 | 06/03/2014 | 06/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2014 |  | 8/29/2014 | N | EXP | 58 |  |  | 0 | 0 | 0 | 7/2/2014 | 7/2/2014 | 9/25/2015 | Connected |  | N
National Grid | MEDFORD | 550568 | 02155 | 15 | Solar | 05_09_702W2 | 09/25/2023 | 10/02/2023 | 5 | 1 | 4 | 10/03/2023 | 10/03/2023 | 43 | 18 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 | 09/25/2023 | 12/20/2024 | Y | EXP | 365 | 01/30/2024 | 03/18/2024 | 49 | 0 | 49 |  |  | 3/20/2024 | Connected |  | N
National Grid | ATHOL | 176849 | 01331 | 996 | Solar | 05_07_92W79 | 11/09/2015 | 11/09/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2015 | 12/14/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/15/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 567606 | 02155 | 10 | Solar | 05_09_702W2 | 11/30/2023 | 12/19/2023 | 13 | 11 | 2 | 12/20/2023 | 12/20/2023 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 | 11/30/2023 | 3/4/2025 | Y | EXP | 365 | 06/12/2024 | 07/17/2024 | 36 | 0 | 36 |  |  | 7/23/2024 | Connected |  | N
National Grid | ATHOL | 178008 | 01331 | 990 | Solar | 05_07_92W79 | 04/28/2017 | 04/28/2017 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2017 | 06/27/2017 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 | 04/28/2017 | 12/31/2019 | Y | STD | 499 | 01/24/2019 | 02/06/2019 | 13 | 0 | 13 | 9/3/2019 | 9/3/2019 | 12/31/2019 | Connected |  | N
National Grid | MEDFORD | 577357 | 02155 | 0 | Battery Add-On | 05_09_702W2 | 12/12/2023 | 01/02/2024 | 13 | 11 | 2 | 01/03/2024 | 01/03/2024 | 57 | 32 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 |  | 4/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2024 | Connected |  | N
National Grid | ATHOL | 185564 | 01331 | 2000 | Solar | 05_07_92W79 | 05/17/2018 | 05/17/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/19/2018 | 07/27/2018 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 | 05/17/2018 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 594763 | 02155 | 4.64 | Solar | 05_09_702W2 | 03/12/2024 | 03/13/2024 | 1 | 0 | 1 | 03/14/2024 | 03/14/2024 | 16 | 15 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 185512 | 01331 | 2000 | Solar | 05_07_92W79 | 05/15/2018 | 05/15/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/19/2018 | 07/27/2018 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 | 05/15/2018 | 4/14/2026 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 624205 | 02155 | 0 | Solar | 05_09_702W2 | 07/11/2024 | 07/15/2024 | 2 | 0 | 2 | 07/16/2024 | 07/16/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/11/2024 | 8/12/2025 | Y | EXP | 365 | 10/02/2024 | 10/09/2024 | 8 | 0 | 8 |  |  | 1/24/2025 | Connected |  | N
National Grid | ORANGE | 192507 | 01364 | 15.2 | Solar | 05_07_92W79 | 08/01/2018 | 08/15/2018 | 8 | 0 | 8 | 08/16/2018 | 08/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 644621 | 02155 | 5.76 | Solar | 05_09_702W2 | 10/03/2024 | 10/31/2024 | 4 | 0 | 4 | 11/01/2024 | 11/01/2024 | 64 | 42 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 10/03/2024 | 3/25/2026 | Y | EXP | 365 | 08/28/2025 | 09/12/2025 | 16 | 0 | 16 |  |  | 9/25/2025 | Connected |  | N
National Grid | ROYALSTON | 291859 | 01368 | 43.2 | Solar | 05_07_92W79 | 05/13/2020 | 05/18/2020 | 2 | 1 | 1 | 05/19/2020 | 05/19/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2020 | Connected |  | N
National Grid | MEDFORD | 651793 | 02155 | 3.8 | Solar | 05_09_702W2 | 11/13/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | ORANGE | 346956 | 01364 | 499 | Solar | 05_07_92W79 | 07/14/2021 | 08/23/2021 | 28 | 19 | 9 |  |  | 58 | 32 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 651668 | 02155 | 3.8 | Solar | 05_09_702W2 | 11/13/2024 | 12/16/2024 | 7 | 0 | 7 | 12/17/2024 | 12/17/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 346955 | 01331 | 499 | Solar | 05_07_92W79 | 07/14/2021 | 08/04/2021 | 15 | 6 | 9 |  |  | 71 | 45 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 665670 | 02155 | 19.1 | Solar | 05_09_702W2 | 01/14/2025 | 02/11/2025 | 16 | 10 | 6 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | ROYALSTON | 479156 | 01331 | 7.6 | Solar | 05_07_92W79 | 11/21/2022 | 11/28/2022 | 4 | 0 | 4 | 11/29/2022 | 11/29/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 |  | 1/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | MEDFORD | 693902 | 02155 | 15.2 | Solar | 05_09_702W2 | 05/23/2025 | 05/29/2025 | 3 | 0 | 3 | 05/30/2025 | 05/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | ATHOL | 481017 | 01331 | 15.2 | Solar | 05_07_92W79 | 11/29/2022 | 12/12/2022 | 10 | 8 | 2 | 12/13/2022 | 12/13/2022 | 28 | 5 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 | 11/29/2022 | 6/15/2024 | Y | EXP | 365 | 06/15/2023 | 06/16/2023 | 2 | 0 | 2 |  |  | 7/3/2023 | Connected |  | N
National Grid | MEDFORD | 711382 | 02155 | 15.2 | Solar | 05_09_702W2 | 08/14/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 484048 | 01331 | 20 | Solar | 05_07_92W79 | 01/26/2023 | 01/31/2023 | 4 | 3 | 1 | 02/01/2023 | 02/01/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  | 3/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2023 | Connected |  | N
National Grid | MEDFORD | 715697 | 02155 | 5.51 | Solar | 05_09_702W2 | 08/29/2025 | 10/03/2025 | 4 | 0 | 4 | 10/06/2025 | 10/06/2025 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2026 | Connected |  | N
National Grid | ATHOL | 585541 | 01331 | 0 | Solar | 05_07_92W79 | 01/31/2024 | 02/16/2024 | 12 | 10 | 2 | 02/20/2024 | 02/20/2024 | 46 | 41 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 651942 | 02155 | 20 | Solar | 05_07_92W79 | 11/11/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | ATHOL | 174311 | 01331 | 2000 | Solar | 05_07_93W40 | 01/12/2012 | 01/12/2012 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2012 | 05/03/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2012 | 01/12/2012 | 10/1/2012 | Y | STD | 1 | 09/13/2013 | 12/28/2013 | 72 | 0 | 72 | 12/27/2013 | 12/27/2013 | 12/27/2013 | Connected |  | N
National Grid | MEDFORD | 178473 | 02155 | 10 | Solar | 05_07_93W40 | 03/07/2018 | 03/07/2018 | 6 | 0 | 6 | 03/15/2018 | 03/15/2018 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 | 03/07/2018 | 3/12/2019 | Y | EXP | 35 |  |  | 0 | 0 | 0 |  |  | 12/14/2018 | Connected |  | N
National Grid | ROYALSTON | 187879 | 01368 | 1850 | Solar | 05_07_93W40 | 07/05/2018 | 07/05/2018 | 20 | 7 | 13 |  |  | 95 | 27 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 383891 | 02155 | 8.7 | Solar | 05_07_93W40 | 09/22/2021 | 12/14/2021 | 2 | 0 | 2 | 09/27/2021 | 09/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 |  | 2/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2022 | Connected |  | N
National Grid | ORANGE | 404082 | 01364 | 240 | Solar | 05_07_93W40 | 08/01/2022 | 08/29/2022 | 21 | 11 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 412222 | 02155 | 0 | Battery Add-On | 05_07_93W40 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 421780 | 01364 | 9.45 | Solar | 05_07_93W40 | 05/05/2022 | 05/09/2022 | 1 | 1 | 0 | 05/10/2022 | 05/10/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2022 |  | 7/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2023 | Connected |  | N
National Grid | NORTON | 547930 | 02766 | 18.048 | Solar | 05_07_93W40 | 08/14/2023 | 08/17/2023 | 4 | 2 | 2 | 08/18/2023 | 08/18/2023 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 563028 | 01331 | 7.25 | Solar | 05_07_93W40 | 10/17/2023 | 10/20/2023 | 4 | 1 | 3 | 10/23/2023 | 10/23/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 577762 | 02375 | 0 | Other | 05_07_93W40 | 12/21/2023 | 02/21/2024 | 39 | 30 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2024 | 02/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 581852 | 01331 | 3.8 | Solar | 05_07_93W40 | 02/12/2024 | 02/15/2024 | 4 | 1 | 3 | 02/16/2024 | 02/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/12/2024 | 5/16/2025 | Y | EXP | 365 | 06/12/2024 | 07/03/2024 | 22 | 0 | 22 |  |  | 8/8/2024 | Connected |  | N
National Grid | EASTON | 648554 | 02375 | 5.76 | Solar | 05_07_93W40 | 11/01/2024 | 12/04/2024 | 14 | 9 | 5 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 651299 | 01331 | 5.76 | Solar | 05_07_93W40 | 11/12/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 4/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | EASTON | 651115 | 02375 | 5.7 | Solar | 05_07_93W40 | 11/01/2024 | 11/25/2024 | 8 | 4 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 11/01/2024 | 3/29/2026 | Y | EXP | 365 | 06/13/2025 | 06/17/2025 | 5 | 0 | 5 |  |  | 6/24/2025 | Connected |  | N
National Grid | ORANGE | 653385 | 01364 | 8.41 | Solar | 05_07_93W40 | 11/12/2024 | 01/24/2025 | 34 | 31 | 3 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 663118 | 02760 | 5.12 | Solar | 05_07_93W40 | 12/30/2024 | 01/29/2025 | 4 | 0 | 4 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 | 12/30/2024 | 4/8/2026 | Y | EXP | 365 | 06/26/2025 | 11/21/2025 | 149 | 0 | 149 |  |  | 12/15/2025 | Connected |  | N
National Grid | ATHOL | 672326 | 01331 | 9.75 | Solar | 05_07_93W40 | 02/19/2025 | 03/03/2025 | 6 | 3 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | NORTON | 680985 | 02766 | 7.6 | Solar | 05_07_93W40 | 03/27/2025 | 04/18/2025 | 4 | 0 | 4 | 04/30/2025 | 04/30/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 175317 | 01364 | 417.6 | Solar | 05_07_93W41 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 12/24/2014 | 12/24/2014 | 12/31/2014 | Connected |  | N
National Grid | EASTON | 176195 | 02375 | 800 | Solar | 05_07_93W41 | 02/04/2015 | 02/04/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2015 | 03/12/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 176194 | 01331 | 990 | Solar | 05_07_93W41 | 02/04/2015 | 02/04/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2015 | 03/12/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 609078 | 02375 | 3.8 | Solar | 05_07_93W41 | 05/06/2024 | 06/11/2024 | 6 | 4 | 2 | 06/12/2024 | 06/12/2024 | 38 | 22 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 676983 | 01331 | 750 | Solar | 05_07_93W42 | 04/08/2025 | 06/25/2025 | 53 | 43 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2025 | 07/23/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | EASTON | 741952 | 02375 | 11.52 | Solar | 05_07_93W42 | 12/23/2025 | 01/20/2026 | 17 | 17 | 0 | 01/21/2026 | 01/21/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ATHOL | 174654 | 01331 | 266 | Solar | 05_07_93W42 | 08/21/2012 | 08/21/2012 | 8 | 0 | 8 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2012 |  | 11/1/2012 | N | EXP | 4 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | N
National Grid | EASTON | 174941 | 02375 | 34.2 | Solar | 05_07_93W42 | 10/13/2011 | 10/13/2011 | 0 | 0 | 0 | 11/09/2011 | 11/09/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2012 |  | 11/30/2012 | N | EXP | 4 |  |  | 0 | 0 | 0 | 7/1/2013 | 7/1/2013 | 12/16/2014 | Connected |  | N
National Grid | ATHOL | 174940 | 01331 | 60 | Solar | 05_07_93W42 | 10/13/2011 | 10/13/2011 | 0 | 0 | 0 | 11/09/2011 | 11/09/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 12/10/2014 | 12/10/2014 | 12/16/2014 | Connected |  | N
National Grid | EASTON | 175561 | 02375 | 996 | Solar | 05_07_93W42 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2014 | 09/09/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 175560 | 01364 | 996 | Solar | 05_07_93W42 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 106 | 0 | 106 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 175707 | 02766 | 996 | Solar | 05_07_93W42 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 11/26/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 |  | 12/31/2016 | N | STD | 62 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 175705 | 01331 | 996 | Solar | 05_07_93W42 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 11/26/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 |  | 12/31/2016 | N | STD | 62 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 176336 | 02375 | 996 | Solar | 05_07_93W42 | 09/17/2015 | 09/17/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/17/2015 | 10/15/2015 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2016 | 09/17/2015 | 9/22/2016 | Y | STD | 176 | 09/19/2016 | 12/19/2016 | 62 | 0 | 62 | 12/30/2016 | 12/30/2016 | 12/30/2016 | Connected |  | N
National Grid | ATHOL | 177048 | 01331 | 1320 | Solar | 05_07_93W42 | 10/17/2016 | 10/17/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/23/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 177339 | 02375 | 36 | Solar | 05_07_93W42 | 09/01/2016 | 09/01/2016 | 2 | 2 | 0 | 09/06/2016 | 09/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2016 | 09/01/2016 | 9/6/2017 | Y | EXP | 363 | 10/14/2016 | 10/26/2016 | 8 | 0 | 8 | 7/24/2017 | 7/24/2017 | 7/26/2017 | Connected |  | N
National Grid | EASTON | 178089 | 02375 | 756 | Solar | 05_07_93W42 | 07/06/2017 | 07/06/2017 | 81 | 81 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 |  | 1/13/2020 | N | CMPX | 549 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 292499 | 02370 | 0 | Solar | 05_07_93W42 | 05/19/2020 | 05/20/2020 | 1 | 1 | 0 | 05/21/2020 | 05/21/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2020 |  | 5/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2020 | Connected |  | N
National Grid | ROCKLAND | 316919 | 02370 | 0 | Battery Add-On | 05_07_93W42 | 10/05/2020 | 10/08/2020 | 3 | 1 | 2 | 10/09/2020 | 10/09/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 7/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2022 | Connected |  | N
National Grid | ROCKLAND | 396664 | 02370 | 0 | Other | 05_07_93W42 | 01/14/2022 | 01/28/2022 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 03/02/2022 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 401109 | 02370 | 0 | Other | 05_07_93W42 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 03/02/2022 | 31 | 3 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 443989 | 02370 | 0 | Other | 05_07_93W42 | 11/09/2022 |  | 121 | 113 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 483153 | 02370 | 13.63 | Solar | 05_07_93W42 | 01/11/2023 | 01/12/2023 | 1 | 0 | 1 | 01/13/2023 | 01/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 3/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2023 | Connected |  | N
National Grid | ROCKLAND | 504529 | 02370 | 10.44 | Solar | 05_07_93W42 | 03/15/2023 | 03/20/2023 | 4 | 1 | 3 | 03/21/2023 | 03/21/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2023 | 03/15/2023 | 6/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2023 | Connected |  | N
National Grid | ROCKLAND | 531761 | 02370 | 247.3 | Solar | 05_07_93W42 | 07/19/2023 | 09/05/2023 | 33 | 24 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 577755 | 02370 | 0 | Other | 05_07_93W42 | 12/21/2023 | 02/21/2024 | 39 | 30 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2024 | 02/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKLAND | 596183 | 02370 | 7.6 | Solar | 05_07_93W42 | 04/03/2024 | 04/04/2024 | 1 | 0 | 1 | 04/05/2024 | 04/05/2024 | 134 | 25 | 109 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKLAND | 606147 | 02370 | 7.6 | Solar | 05_07_93W42 | 04/23/2024 | 06/05/2024 | 0 | 0 | 0 | 06/06/2024 | 06/06/2024 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2024 | 04/23/2024 | 6/28/2025 | Y | EXP | 365 | 08/27/2024 | 10/15/2024 | 50 | 0 | 50 |  |  | 10/24/2024 | Connected |  | N
National Grid | ROCKLAND | 621950 | 02370 | 9.28 | Solar | 05_07_93W42 | 07/02/2024 | 07/22/2024 | 13 | 11 | 2 | 07/23/2024 | 07/23/2024 | 24 | 11 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 624545 | 02370 | 7.6 | Solar | 05_07_93W42 | 07/12/2024 | 07/24/2024 | 3 | 0 | 3 | 07/25/2024 | 07/25/2024 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 | 07/12/2024 | 10/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | ROCKLAND | 637008 | 02370 | 10 | Solar | 05_07_93W42 | 09/05/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 39 | 25 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKLAND | 653517 | 02370 | 10 | Solar | 05_07_93W42 | 11/15/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/15/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 217500 | 02370 | 3.8 | Solar | 05_01_216W3 | 06/18/2019 | 10/23/2019 | 87 | 83 | 4 | 10/24/2019 | 10/24/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 242400 | 02339 | 9.92 | Solar | 05_01_216W3 | 07/16/2019 | 07/23/2019 | 4 | 0 | 4 | 07/24/2019 | 07/24/2019 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 | 07/16/2019 | 7/16/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2020 | Connected |  | N
National Grid | ROCKLAND | 287761 | 02370 | 11.52 | Solar | 05_01_216W3 | 04/14/2020 | 04/20/2020 | 3 | 0 | 3 | 04/21/2020 | 04/21/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2020 |  | 9/24/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2021 | Connected |  | N
National Grid | ABINGTON | 320293 | 02351 | 7.6 | Solar | 05_01_216W3 | 10/29/2020 | 11/02/2020 | 1 | 0 | 1 | 11/03/2020 | 11/03/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 | 10/29/2020 | 10/29/2021 | Y | EXP | 365 | 05/06/2021 | 05/07/2021 | 1 | 0 | 1 |  |  | 9/3/2021 | Connected |  | N
National Grid | ABINGTON | 396737 | 02351 | 1744 | Other | 05_01_216W3 | 05/25/2022 | 06/04/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/06/2022 | 07/11/2022 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 425604 | 02351 | 15.2 | Solar | 05_01_216W3 | 04/22/2022 | 04/26/2022 | 3 | 2 | 1 | 04/27/2022 | 04/27/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2022 |  | 6/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2022 | Connected |  | N
National Grid | ABINGTON | 435349 | 02351 | 0 | Other | 05_01_216W3 | 07/27/2022 | 08/23/2022 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2022 | 09/16/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 588934 | 02351 | 6 | Solar | 05_01_216W3 | 02/28/2024 | 03/04/2024 | 3 | 0 | 3 | 03/05/2024 | 03/05/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/28/2024 | 12/31/2025 | Y | EXP | 365 | 06/05/2024 | 08/28/2024 | 85 | 0 | 85 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 613402 | 02351 | 3.8 | Solar | 05_01_216W3 | 05/29/2024 | 05/31/2024 | 1 | 0 | 1 | 06/03/2024 | 06/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 |  | 6/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/5/2024 | Connected |  | N
National Grid | ABINGTON | 618307 | 02351 | 10 | Solar | 05_01_216W3 | 06/17/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 | 06/17/2024 | 8/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2024 | Connected |  | N
National Grid | WHITMAN | 620430 | 02382 | 6.09 | Solar | 05_01_216W3 | 06/28/2024 | 03/03/2025 | 36 | 32 | 4 | 03/04/2025 | 03/04/2025 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | WHITMAN | 630507 | 02382 | 3.8 | Solar | 05_01_216W3 | 08/06/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 637107 | 02351 | 10 | Solar | 05_01_216W3 | 09/02/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/02/2024 | 12/3/2025 | Y | EXP | 365 | 03/05/2025 | 03/11/2025 | 7 | 0 | 7 |  |  | 3/25/2025 | Connected |  | N
National Grid | ABINGTON | 639366 | 02351 | 3.8 | Solar | 05_01_216W3 | 09/11/2024 | 10/10/2024 | 11 | 8 | 3 | 10/11/2024 | 10/11/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/11/2024 | 1/26/2026 | Y | EXP | 365 | 01/16/2025 | 03/13/2025 | 57 | 0 | 57 |  |  | 6/3/2025 | Connected |  | N
National Grid | ABINGTON | 643765 | 02351 | 3.8 | Solar | 05_01_216W3 | 10/01/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/01/2024 | 12/11/2025 | Y | EXP | 365 | 03/15/2025 | 03/21/2025 | 7 | 0 | 7 |  |  | 4/10/2025 | Connected |  | N
National Grid | ABINGTON | 646190 | 02351 | 10.26 | Solar | 05_01_216W3 | 10/10/2024 | 10/21/2024 | 4 | 2 | 2 | 10/22/2024 | 10/22/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/10/2024 | 11/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | ABINGTON | 649756 | 02351 | 3.8 | Solar | 05_01_216W3 | 11/05/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 11/05/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | ABINGTON | 665491 | 02351 | 5.76 | Solar | 05_01_216W3 | 01/14/2025 | 01/29/2025 | 5 | 0 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | ABINGTON | 641164 | 02351 | 300 | Solar | 05_07_913W43 | 11/20/2024 | 03/10/2025 | 73 | 64 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/11/2025 | 04/07/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ABINGTON | 717898 | 02351 | 7.6 | Solar | 05_07_913W43 | 09/09/2025 | 10/16/2025 | 1 | 0 | 1 | 11/05/2025 | 11/05/2025 | 24 | 6 | 18 | 01/12/2026 | 03/02/2026 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  | 03/02/2026 | 34 | 0 | 34 |  |  | 0 | 0 | 0 | 3/5/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ABINGTON | 727503 | 02351 | 3.8 | Solar | 05_07_913W43 | 10/17/2025 | 12/09/2025 | 5 | 0 | 5 | 01/07/2026 | 01/07/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ABINGTON | 737466 | 02351 | 15.2 | Solar | 05_07_913W43 | 12/02/2025 | 12/05/2025 | 3 | 0 | 3 | 12/08/2025 | 12/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ABINGTON | 736782 | 02351 | 10 | Solar | 05_07_913W43 | 11/26/2025 | 01/12/2026 | 2 | 0 | 2 | 02/04/2026 | 02/04/2026 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ABINGTON | 740976 | 02351 | 6.46 | Solar | 05_07_913W43 | 12/17/2025 | 12/23/2025 | 1 | 0 | 1 | 01/12/2026 | 01/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ABINGTON | 747644 | 02351 | 11.5 | Solar | 05_07_913W43 | 01/27/2026 | 01/29/2026 | 2 | 0 | 2 | 01/30/2026 | 01/30/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WHITMAN | 174938 | 02382 | 68.4 | Solar | 05_07_913W43 | 10/13/2011 | 10/13/2011 | 0 | 0 | 0 | 11/09/2011 | 11/09/2011 | 555 | 0 | 555 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2012 |  | 11/30/2012 | N | EXP | 58 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 176878 | 02351 | 28.8 | Solar | 05_07_913W43 | 05/04/2016 | 05/04/2016 | 2 | 2 | 0 | 05/06/2016 | 05/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2016 |  | 5/9/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 1/9/2017 | 1/9/2017 | 1/9/2017 | Connected |  | N
National Grid | ABINGTON | 177310 | 02351 | 22.8 | Solar | 05_07_913W43 | 11/17/2016 | 11/17/2016 | 2 | 2 | 0 | 11/22/2016 | 11/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 |  | 11/23/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 6/27/2017 | 6/27/2017 | 6/30/2017 | Connected |  | N
National Grid | ABINGTON | 178335 | 02351 | 60.8 | Solar | 05_07_913W43 | 11/17/2017 | 11/17/2017 | 69 | 69 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/25/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 178651 | 02351 | 10 | Solar | 05_07_913W43 | 12/18/2017 | 12/18/2017 | 0 | 0 | 0 | 07/11/2018 | 07/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2018 |  | 12/23/2018 | N | EXP | 166 |  |  | 0 | 0 | 0 |  |  | 5/14/2019 | Connected |  | N
National Grid | WHITMAN | 212974 | 02382 | 6 | Solar | 05_07_913W43 | 03/20/2019 | 03/28/2019 | 5 | 0 | 5 | 03/29/2019 | 03/29/2019 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2019 |  | 4/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2019 | Connected |  | N
National Grid | ABINGTON | 273993 | 02351 | 10 | Solar | 05_07_913W43 | 04/17/2020 | 05/28/2020 | 27 | 27 | 0 | 05/29/2020 | 05/29/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 5/28/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 310322 | 02302 | 249 | Solar | 05_07_913W43 | 10/13/2020 | 10/29/2020 | 12 | 4 | 8 | 10/30/2020 | 10/30/2020 | 22 | 0 | 22 | 04/30/2021 | 04/21/2022 | 244 | 33 | 211 |  |  | 0 | 0 | 0 |  | 04/21/2022 | 244 | 33 | 211 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITMAN | 328974 | 02382 | 7.6 | Solar | 05_07_913W43 | 12/01/2020 | 12/03/2020 | 1 | 0 | 1 | 12/04/2020 | 12/04/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 7/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/3/2022 | Connected |  | N
National Grid | ABINGTON | 331347 | 02351 | 10 | Solar | 05_07_913W43 | 01/21/2021 | 01/27/2021 | 3 | 2 | 1 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/21/2021 | 10/16/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2021 | Connected |  | N
National Grid | CLINTON | 331261 | 01510 | 8.88 | Solar | 05_07_913W43 | 12/11/2020 | 01/08/2021 | 18 | 14 | 4 | 01/11/2021 | 01/11/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/11/2020 | 5/15/2023 | Y | EXP | 365 | 11/25/2021 | 02/12/2022 | 80 | 0 | 80 |  |  | 4/5/2023 | Connected |  | N
National Grid | CLINTON | 340789 | 01510 | 15.2 | Solar | 05_07_913W43 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 375475 | 01523 | 15.2 | Solar | 05_07_913W43 | 08/12/2021 | 01/09/2022 | 4 | 0 | 4 | 08/19/2021 | 08/19/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  | 9/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2022 | Connected |  | N
National Grid | CLINTON | 414774 | 01510 | 0 | Solar | 05_07_913W43 | 04/22/2022 | 04/26/2022 | 3 | 1 | 2 | 04/27/2022 | 04/27/2022 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  | 8/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | CLINTON | 420576 | 01510 | 15.2 | Solar | 05_07_913W43 | 04/21/2022 | 04/22/2022 | 1 | 0 | 1 | 04/25/2022 | 04/25/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2022 |  | 9/30/2024 | N | EXP | 65 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 474223 | 01523 | 5.8 | Solar | 05_07_913W43 | 12/15/2022 | 01/03/2023 | 11 | 7 | 4 | 01/04/2023 | 01/04/2023 | 49 | 30 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2023 |  | 11/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2024 | Connected |  | N
National Grid | CLINTON | 477659 | 01510 | 16.53 | Solar | 05_07_913W43 | 11/17/2022 | 11/22/2022 | 3 | 0 | 3 | 11/23/2022 | 11/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2022 |  | 5/20/2024 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 483858 | 01510 | 0 | Solar | 05_07_913W43 | 12/08/2022 | 12/12/2022 | 2 | 0 | 2 | 12/13/2022 | 12/13/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2023 |  | 9/12/2024 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 540995 | 01510 | 6 | Solar | 05_07_913W43 | 08/22/2023 | 09/19/2023 | 19 | 16 | 3 | 09/20/2023 | 09/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 541916 | 01523 | 0 | Solar | 05_07_913W43 | 07/19/2023 | 07/26/2023 | 5 | 4 | 1 | 07/27/2023 | 07/27/2023 | 132 | 107 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2024 | Connected |  | N
National Grid | CLINTON | 597061 | 01510 | 7.6 | Solar | 05_07_913W43 | 03/21/2024 | 04/08/2024 | 13 | 11 | 2 | 04/09/2024 | 04/09/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  | 4/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2024 | Connected |  | N
National Grid | CLINTON | 619530 | 01510 | 7.6 | Solar | 05_07_913W43 | 06/21/2024 | 07/02/2024 | 4 | 1 | 3 | 07/03/2024 | 07/03/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | CLINTON | 625260 | 01510 | 4.18 | Solar | 05_07_913W43 | 07/16/2024 | 08/06/2024 | 12 | 9 | 3 | 08/07/2024 | 08/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/16/2024 | 8/30/2025 | Y | EXP | 365 | 04/08/2025 | 04/07/2025 | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | CLINTON | 625803 | 01510 | 1.74 | Solar | 05_07_913W43 | 07/18/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 66 | 47 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 630486 | 01510 | 3.8 | Solar | 05_07_913W43 | 08/06/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 08/06/2024 | 9/6/2025 | Y | EXP | 365 | 12/13/2024 | 12/12/2024 | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | CLINTON | 637012 | 01510 | 0 | Battery Add-On | 05_07_913W43 | 09/03/2024 | 09/18/2024 | 11 | 9 | 2 | 09/19/2024 | 09/19/2024 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2024 |  | 11/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2024 | Connected |  | N
National Grid | CLINTON | 655783 | 01510 | 5.76 | Solar | 05_07_913W43 | 11/20/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | CLINTON | 656137 | 01510 | 4.94 | Solar | 05_07_913W43 | 11/22/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2025 | Connected |  | N
National Grid | STOUGHTON | 657653 | 02072 | 5.76 | Solar | 05_07_913W43 | 11/29/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | STOUGHTON | 658168 | 02072 | 10 | Solar | 05_07_913W43 | 12/03/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 675761 | 02072 | 5.76 | Solar | 05_07_913W43 | 03/05/2025 | 03/18/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 680634 | 02072 | 5.76 | Solar | 05_07_913W43 | 03/26/2025 | 04/29/2025 | 23 | 18 | 5 | 04/30/2025 | 04/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2025 | Connected |  | N
National Grid | STOUGHTON | 681967 | 02072 | 5 | Solar | 05_07_913W43 | 04/01/2025 | 04/22/2025 | 4 | 0 | 4 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | STOUGHTON | 683413 | 02072 | 15.2 | Solar | 05_07_913W43 | 04/09/2025 | 04/14/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 691658 | 02072 | 10 | Solar | 05_07_913W43 | 05/26/2025 | 06/27/2025 | 2 | 0 | 2 | 07/14/2025 | 07/14/2025 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 | 05/26/2025 | 9/9/2026 | Y | EXP | 365 | 11/26/2025 | 01/08/2026 | 44 | 0 | 44 |  |  | 1/12/2026 | Connected |  | N
National Grid | STOUGHTON | 709025 | 02072 | 10 | Solar | 05_07_913W43 | 08/01/2025 | 09/15/2025 | 29 | 24 | 5 | 09/16/2025 | 09/16/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 722755 | 02072 | 3.8 | Solar | 05_07_913W43 | 09/30/2025 | 10/07/2025 | 5 | 1 | 4 | 10/08/2025 | 10/08/2025 | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2026 | Connected |  | N
National Grid | STOUGHTON | 668229 | 02072 | 10 | Solar | 05_01_304W1 | 01/28/2025 | 03/08/2025 | 22 | 18 | 4 | 03/10/2025 | 03/10/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | STOUGHTON | 718080 | 02072 | 5.76 | Solar | 05_01_304W1 | 09/10/2025 | 09/17/2025 | 4 | 2 | 2 | 09/18/2025 | 09/18/2025 | 114 | 101 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STOUGHTON | 726510 | 02072 | 10 | Solar | 05_01_304W1 | 10/14/2025 | 11/20/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 | 10/14/2025 | 1/13/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | STOUGHTON | 738884 | 02072 | 5.76 | Solar | 05_01_304W1 | 12/09/2025 | 01/02/2026 | 2 | 0 | 2 | 01/23/2026 | 01/23/2026 | 30 | 18 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STOUGHTON | 744806 | 02072 | 15.2 | Solar | 05_01_304W1 | 01/13/2026 | 01/20/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | STOUGHTON | 174133 | 02072 | 24.94 | Solar | 05_01_304W1 | 05/03/2012 | 05/03/2012 | 17 | 0 | 17 | 05/31/2012 | 05/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2012 |  | 8/10/2012 | N | EXP | 54 |  |  | 0 | 0 | 0 | 12/26/2013 | 12/26/2013 | 12/26/2013 | Connected |  | N
National Grid | STOUGHTON | 174945 | 02072 | 45 | Solar | 05_01_304W1 | 09/21/2012 | 09/21/2012 | 9 | 0 | 9 | 10/04/2012 | 10/04/2012 | 0 | 0 | 0 | 03/28/2013 | 04/30/2013 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 04/30/2013 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 5/6/2013 |  | 2/1/2013 | N | EXP | 94 |  |  | 0 | 0 | 0 | 5/23/2013 | 5/23/2013 | 10/30/2013 | Connected |  | N
National Grid | STOUGHTON | 175007 | 02072 | 2700 | Solar | 05_01_304W1 | 09/18/2013 | 09/18/2013 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2013 | 10/23/2013 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2014 | 09/18/2013 | 5/14/2016 | Y | STD | 74 | 03/18/2016 | 12/20/2016 | 189 | 0 | 189 |  |  | 10/28/2016 | Connected |  | N
National Grid | STOUGHTON | 175206 | 02072 | 2000 | Solar | 05_01_304W1 | 12/04/2012 | 12/04/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2012 | 01/15/2013 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 01/15/2013 | 01/15/2013 | 0 | 0 | 0 | 8/9/2013 | 12/04/2012 | 12/31/2014 | Y | STD | 59 | 08/11/2014 | 03/29/2016 | 404 | 0 | 404 | 3/15/2015 | 3/15/2015 | 3/16/2015 | Connected |  | N
National Grid | STOUGHTON | 175625 | 02072 | 672 | Solar | 05_01_304W1 | 05/05/2014 | 05/05/2014 | 7 | 4 | 3 |  |  | 0 | 0 | 0 | 06/13/2014 | 06/13/2014 | 0 | 0 | 0 | 05/15/2014 | 09/12/2014 | 82 | 12 | 70 |  | 06/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 | 05/05/2014 | 12/1/2016 | Y | STD | 419 | 04/19/2016 | 12/21/2016 | 169 | 0 | 169 | 12/9/2016 | 12/9/2016 | 12/21/2016 | Connected |  | N
National Grid | STOUGHTON | 175713 | 02072 | 5 | Solar | 05_01_304W1 | 10/27/2014 | 10/27/2014 | 6 | 1 | 5 | 11/05/2014 | 11/05/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 |  | 1/28/2015 | N | EXP | 64 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 8/7/2015 | Connected |  | N
National Grid | STOUGHTON | 175982 | 02072 | 990 | Solar | 05_01_304W1 | 01/23/2015 | 01/23/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/03/2015 | 03/05/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 09/16/2015 | 10/02/2015 | 12 | 0 | 12 | 12/8/2015 | 01/23/2015 | 6/30/2015 | Y | STD | 161 | 09/21/2017 | 11/27/2017 | 39 | 0 | 39 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | SHARON | 176017 | 02067 | 21.4 | Solar | 05_01_304W1 | 01/26/2015 | 01/26/2015 | 4 | 0 | 4 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2015 |  | 5/31/2015 | N | EXP | 114 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 12/11/2015 | Connected |  | N
National Grid | STOUGHTON | 176102 | 02072 | 6.45 | Solar | 05_01_304W1 | 06/19/2015 | 06/19/2015 | 5 | 5 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/28/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 11/13/2015 | Connected |  | N
National Grid | STOUGHTON | 176508 | 02072 | 5 | Solar | 05_01_304W1 | 03/24/2016 | 03/24/2016 | 3 | 3 | 0 | 03/30/2016 | 03/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 |  | 3/30/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 | 10/5/2016 | 10/5/2016 | 10/11/2016 | Connected |  | N
National Grid | STOUGHTON | 176555 | 02072 | 10 | Solar | 05_01_304W1 | 10/05/2015 | 10/05/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 336 | 0 | 336 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2015 |  | 10/13/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 176683 | 02072 | 4.73 | Solar | 05_01_304W1 | 02/18/2016 | 02/18/2016 | 35 | 35 | 0 | 04/08/2016 | 04/08/2016 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2016 |  | 2/23/2017 | N | EXP | 316 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 177835 | 02072 | 1760 | Solar | 05_01_304W1 | 08/09/2017 | 08/09/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2017 | 09/20/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2018 | 08/09/2017 | 7/16/2022 | Y | STD | 434 | 11/25/2021 | 03/14/2022 | 110 | 0 | 110 |  |  | 3/21/2022 | Connected |  | N
National Grid | STOUGHTON | 178296 | 02072 | 10 | Solar | 05_01_304W1 | 11/15/2017 | 11/15/2017 | 63 | 49 | 14 | 02/20/2018 | 02/20/2018 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2018 |  | 11/21/2018 | N | EXP | 273 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 185050 | 02072 | 240 | Solar | 05_01_304W1 | 05/10/2018 | 05/10/2018 | 17 | 0 | 17 |  |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 | 05/10/2018 | 10/27/2022 | Y | STD | 773 | 10/22/2019 | 07/29/2020 | 282 | 247 | 35 |  |  | 4/15/2022 | Connected |  | N
National Grid | STOUGHTON | 193678 | 02072 | 250 | Solar | 05_01_304W1 | 08/17/2018 | 08/27/2018 | 4 | 0 | 4 | 08/28/2018 | 08/28/2018 | 0 | 0 | 0 | 09/27/2019 | 11/26/2019 | 40 | 20 | 20 |  |  | 0 | 0 | 0 |  | 11/26/2019 | 40 | 20 | 20 |  |  | 0 | 0 | 0 | 12/12/2019 | 08/17/2018 | 5/17/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2021 | Connected |  | N
National Grid | STOUGHTON | 195088 | 02072 | 10 | Solar | 05_01_304W1 | 09/10/2018 | 10/31/2018 | 9 | 8 | 1 | 11/01/2018 | 11/01/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 12/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2019 | Connected |  | N
National Grid | STOUGHTON | 193132 | 02072 | 4000 | Solar | 05_01_304W1 | 10/24/2018 | 11/08/2018 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/21/2021 | 05/01/2023 | 486 | 322 | 164 | 3/11/2021 | 10/24/2018 | 2/7/2025 | Y | CMPX | 399 |  |  | 0 | 0 | 0 |  |  | 6/28/2024 | Connected |  | N
National Grid | STOUGHTON | 196967 | 02072 | 6 | Solar | 05_01_304W1 | 09/26/2018 | 10/18/2018 | 2 | 2 | 0 | 10/19/2018 | 10/19/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 12/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2019 | Connected |  | N
National Grid | STOUGHTON | 199009 | 02072 | 10 | Solar | 05_01_304W1 | 01/16/2019 | 01/30/2019 | 8 | 0 | 8 | 01/31/2019 | 01/31/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 | 01/16/2019 | 2/12/2020 | Y | EXP | 365 | 06/22/2019 | 06/21/2019 | 0 | 0 | 0 |  |  | 7/25/2019 | Connected |  | N
National Grid | STOUGHTON | 204685 | 02072 | 0 | Solar | 05_01_304W1 | 01/17/2019 | 02/01/2019 | 9 | 0 | 9 | 02/04/2019 | 02/04/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2019 | Connected |  | N
National Grid | STOUGHTON | 211835 | 02072 | 1760 | Solar | 05_01_304W1 | 02/27/2019 | 04/04/2019 | 25 | 17 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2019 | 07/08/2019 | 65 | 49 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 213993 | 02072 | 7.6 | Solar | 05_01_304W1 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  | 4/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2019 | Connected |  | N
National Grid | STOUGHTON | 222250 | 02072 | 10 | Solar | 05_01_304W1 | 05/13/2019 | 05/24/2019 | 8 | 1 | 7 | 05/28/2019 | 05/28/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 6/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2019 | Connected |  | N
National Grid | STOUGHTON | 248216 | 02072 | 7.6 | Solar | 05_01_304W1 | 09/19/2019 | 10/04/2019 | 10 | 10 | 0 | 10/07/2019 | 10/07/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2019 | 09/19/2019 | 6/8/2020 | Y | EXP | 365 | 01/16/2020 | 01/31/2020 | 15 | 0 | 15 |  |  | 2/13/2020 | Connected |  | N
National Grid | STOUGHTON | 266020 | 02072 | 7.6 | Solar | 05_01_304W1 | 11/21/2019 | 12/10/2019 | 12 | 12 | 0 | 12/11/2019 | 12/11/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 |  | 12/21/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 265476 | 02072 | 0 | Solar | 05_01_304W1 | 11/14/2019 | 11/20/2019 | 3 | 0 | 3 | 11/21/2019 | 11/21/2019 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2020 | 11/14/2019 | 11/14/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2020 | Connected |  | N
National Grid | STOUGHTON | 291144 | 02072 | 9.996 | Solar | 05_01_304W1 | 05/08/2020 | 05/13/2020 | 2 | 0 | 2 | 05/14/2020 | 05/14/2020 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2020 | 05/08/2020 | 4/23/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2021 | Connected |  | N
National Grid | STOUGHTON | 290832 | 02072 | 1.68 | Solar | 05_01_304W1 | 05/07/2020 | 05/21/2020 | 10 | 5 | 5 | 05/22/2020 | 05/22/2020 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 |  | 6/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2022 | Connected |  | N
National Grid | STOUGHTON | 301597 | 02072 | 10 | Solar | 05_01_304W1 | 07/30/2020 | 08/12/2020 | 8 | 6 | 2 | 08/13/2020 | 08/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 | 07/30/2020 | 8/5/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2021 | Connected |  | N
National Grid | GRAFTON | 306191 | 01519 | 15.2 | Solar | 05_01_304W1 | 08/11/2020 | 08/13/2020 | 1 | 0 | 1 | 08/14/2020 | 08/14/2020 | 88 | 64 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/12/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 322960 | 01560 | 5.584 | Solar | 05_01_304W1 | 12/14/2020 | 12/30/2020 | 10 | 6 | 4 | 12/31/2020 | 12/31/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/14/2020 | 2/3/2022 | Y | EXP | 365 | 09/04/2021 | 11/08/2021 | 66 | 4 | 62 |  |  | 1/12/2022 | Connected |  | N
National Grid | MILLBURY | 339077 | 01527 | 7.6 | Solar | 05_01_304W1 | 01/27/2021 | 01/28/2021 | 0 | 0 | 0 | 01/29/2021 | 01/29/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2021 | Connected |  | N
National Grid | GRAFTON | 338606 | 01519 | 8.725 | Solar | 05_01_304W1 | 02/02/2021 | 02/12/2021 | 8 | 8 | 0 | 02/16/2021 | 02/16/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 | 02/02/2021 | 7/19/2022 | Y | EXP | 365 | 06/25/2021 | 07/15/2021 | 21 | 0 | 21 |  |  | 9/16/2021 | Connected |  | N
National Grid | GRAFTON | 339113 | 01519 | 9.8 | Solar | 05_01_304W1 | 01/27/2021 | 01/28/2021 | 0 | 0 | 0 | 01/29/2021 | 01/29/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2021 | Connected |  | N
National Grid | GRAFTON | 358023 | 01519 | 0 | Solar | 05_01_304W1 | 05/13/2021 | 05/14/2021 | 0 | 0 | 0 | 05/17/2021 | 05/17/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2021 | 05/13/2021 | 4/24/2023 | Y | EXP | 55 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 449309 | 01519 | 15.2 | Solar | 05_01_304W1 | 08/04/2022 | 08/10/2022 | 4 | 3 | 1 | 08/11/2022 | 08/11/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2022 |  | 1/19/2024 | N | EXP | 474 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 375886 | 01519 | 15.2 | Solar | 05_01_304W1 | 09/01/2021 | 09/09/2021 | 5 | 3 | 2 | 09/10/2021 | 09/10/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2021 |  | 11/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2022 | Connected |  | Y
National Grid | GRAFTON | 381612 | 01519 | 20.3 | Solar | 05_01_304W1 | 01/25/2022 |  | 27 | 26 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 388111 | 01519 | 15.2 | Solar | 05_01_304W1 | 10/17/2021 | 12/16/2021 | 42 | 40 | 2 | 12/17/2021 | 12/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 414504 | 01527 | 15.2 | Solar | 05_01_304W1 | 02/28/2022 | 03/02/2022 | 2 | 0 | 2 | 09/13/2022 | 09/13/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2022 |  | 10/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2022 | Connected |  | N
National Grid | GRAFTON | 414386 | 01519 | 15.2 | Solar | 05_01_304W1 | 02/25/2022 | 02/28/2022 | 1 | 0 | 1 | 03/01/2022 | 03/01/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 415260 | 01519 | 20.3 | Solar | 05_01_304W1 | 03/03/2022 | 03/04/2022 | 1 | 0 | 1 | 03/07/2022 | 03/07/2022 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2022 |  | 7/6/2023 | N | EXP | 42 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 434574 | 01527 | 10 | Solar | 05_01_304W1 | 06/13/2022 | 06/14/2022 | 1 | 0 | 1 | 06/15/2022 | 06/15/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 441932 | 01536 | 8.41 | Solar | 05_01_304W1 | 08/11/2022 | 09/01/2022 | 15 | 13 | 2 | 09/02/2022 | 09/02/2022 | 14 | 0 | 14 | 10/05/2022 | 10/19/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 10/19/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 5/16/2024 | N | EXP | 365 | 04/20/2023 | 05/16/2023 | 27 | 0 | 27 |  |  | 5/19/2023 | Connected |  | N
National Grid | GRAFTON | 444127 | 01519 | 0 | Solar | 05_01_304W1 | 07/14/2022 | 07/15/2022 | 1 | 1 | 0 | 07/18/2022 | 07/18/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 |  | 8/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2023 | Connected |  | N
National Grid | MILLBURY | 445236 | 01527 | 15.2 | Solar | 05_01_304W1 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 |  | 9/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2023 | Connected |  | N
National Grid | GRAFTON | 447696 | 01519 | 9.86 | Solar | 05_01_304W1 | 08/05/2022 | 08/09/2022 | 2 | 0 | 2 | 08/10/2022 | 08/10/2022 | 49 | 26 | 23 | 01/06/2023 | 01/11/2023 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 01/11/2023 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 1/11/2023 |  | 1/13/2024 | N | EXP | 365 | 04/08/2023 | 04/21/2023 | 14 | 0 | 14 |  |  | 4/25/2023 | Connected |  | N
National Grid | GRAFTON | 482228 | 01519 | 20 | Solar | 05_01_304W1 | 12/02/2022 | 12/13/2022 | 8 | 7 | 1 | 12/14/2022 | 12/14/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2023 |  | 1/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2023 | Connected |  | N
National Grid | GRAFTON | 533787 | 01519 | 15 | Solar | 05_01_304W1 | 06/15/2023 | 06/21/2023 | 4 | 2 | 2 | 06/22/2023 | 06/22/2023 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 12/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2024 | Connected |  | N
National Grid | GRAFTON | 562326 | 01519 | 10 | Solar | 05_01_304W1 | 11/01/2023 | 11/02/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 52 | 28 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 586889 | 01536 | 15.2 | Solar | 05_01_304W1 | 02/02/2024 | 02/16/2024 | 11 | 10 | 1 | 02/20/2024 | 02/20/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 |  | 3/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 594840 | 01519 | 10 | Solar | 05_01_304W1 | 03/06/2024 | 03/11/2024 | 3 | 0 | 3 | 03/12/2024 | 03/12/2024 | 42 | 35 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 6/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2024 | Connected |  | N
National Grid | GRAFTON | 609002 | 01536 | 34.5 | Solar | 05_01_304W1 | 05/06/2024 | 05/24/2024 | 15 | 14 | 1 | 05/28/2024 | 05/28/2024 | 30 | 20 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2024 |  | 7/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2024 | Connected |  | N
National Grid | GRAFTON | 613635 | 01519 | 10 | Solar | 05_01_304W1 | 05/28/2024 | 07/31/2024 | 1 | 0 | 1 | 08/01/2024 | 08/01/2024 | 116 | 25 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 648662 | 01536 | 9.92 | Solar | 05_01_304W1 | 10/22/2024 | 12/04/2024 | 17 | 15 | 2 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | GRAFTON | 656253 | 01519 | 7.6 | Solar | 05_01_304W1 | 11/22/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/22/2024 | 2/14/2026 | Y | EXP | 365 | 10/04/2025 | 12/18/2025 | 76 | 0 | 76 |  |  | 1/21/2026 | Connected |  | N
National Grid | GRAFTON | 658212 | 01536 | 6.84 | Solar | 05_01_304W1 | 12/03/2024 | 12/30/2024 | 6 | 1 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | GRAFTON | 663779 | 01519 | 7.6 | Solar | 05_01_304W1 | 01/05/2025 | 01/17/2025 | 6 | 0 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | MILLBURY | 669841 | 01527 | 5.76 | Solar | 05_01_304W1 | 02/05/2025 | 03/18/2025 | 12 | 7 | 5 | 03/19/2025 | 03/19/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 4/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N
National Grid | GRAFTON | 691717 | 01536 | 13.975 | Solar | 05_01_304W1 | 05/14/2025 | 06/25/2025 | 8 | 5 | 3 | 06/26/2025 | 06/26/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 | 05/14/2025 | 7/25/2026 | Y | EXP | 365 | 10/29/2025 | 11/21/2025 | 24 | 0 | 24 |  |  | 12/1/2025 | Connected |  | N
National Grid | GRAFTON | 730026 | 01519 | 15.2 | Solar | 05_01_304W1 | 10/30/2025 | 11/12/2025 | 7 | 3 | 4 | 11/13/2025 | 11/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 1/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2026 | Connected |  | N
National Grid | GRAFTON | 176286 | 01519 | 130 | Solar | 05_01_HT14 | 07/10/2015 | 07/10/2015 | 209 | 209 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/15/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 640228 | 01527 | 720 | Solar | 05_01_HT3 | 11/13/2024 | 03/10/2025 | 77 | 68 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/11/2025 | 05/06/2025 | 40 | 21 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MILLBURY | 177804 | 01527 | 584 | Solar | 05_01_HT3 | 10/11/2017 | 10/11/2017 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 | 11/28/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/17/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 176805 | 01519 | 225 | Solar | 05_05_115W43 | 04/27/2016 | 04/27/2016 | 19 | 19 | 0 | 05/24/2016 | 05/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 |  | 3/15/2017 | N | EXP | 28 |  |  | 0 | 0 | 0 | 8/22/2017 | 8/22/2017 | 8/24/2017 | Connected |  | N
National Grid | GRAFTON | 199674 | 01519 | 133.2 | Solar | 05_05_115W43 | 11/06/2018 | 11/26/2018 | 10 | 2 | 8 | 11/27/2018 | 11/27/2018 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 |  | 12/31/2020 | N | EXP | 525 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 337141 | 01519 | 497.5 | Solar | 05_05_115W43 | 05/14/2021 | 11/09/2021 | 123 | 110 | 13 |  |  | 50 | 27 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 504309 | 01527 | 7.6 | Solar | 05_05_115W43 | 06/01/2023 | 06/15/2023 | 11 | 10 | 1 | 06/16/2023 | 06/16/2023 | 102 | 84 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 593434 | 01519 | 7.6 | Solar | 05_05_115W43 | 03/29/2024 | 04/04/2024 | 4 | 0 | 4 | 04/05/2024 | 04/05/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 | 03/29/2024 | 5/16/2025 | Y | EXP | 365 | 07/17/2024 | 08/28/2024 | 43 | 0 | 43 |  |  | 11/9/2024 | Connected |  | N
National Grid | GRAFTON | 174462 | 01519 | 548 | Solar | 05_09_S100 | 08/25/2011 | 08/25/2011 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/15/2011 | 11/14/2011 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2012 |  | 6/30/2014 | N | STD | 811 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 12/23/2013 | Connected |  | N
National Grid | GRAFTON | 174724 | 01519 | 3500 | Natural Gas | 05_09_S100 | 03/23/2010 | 03/23/2010 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 03/23/2010 | 12/31/2012 | Y | STD | 19 |  |  | 0 | 0 | 0 | 8/28/2013 | 8/28/2013 | 12/16/2013 | Connected |  | N
National Grid | GRAFTON | 174805 | 01536 | 300 | Solar | 05_12_11J3 | 01/23/2013 | 01/23/2013 | 6 | 0 | 6 | 02/01/2013 | 02/01/2013 | 346 | 0 | 346 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2013 |  | 6/28/2013 | N | EXP | 87 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 175175 | 01519 | 200 | Solar | 05_12_11J3 | 11/27/2012 | 11/27/2012 | 8 | 0 | 8 | 12/10/2012 | 12/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2013 |  | 2/28/2013 | N | EXP | 6 |  |  | 0 | 0 | 0 | 6/18/2013 | 6/18/2013 | 10/9/2013 | Connected |  | N
National Grid | GRAFTON | 252575 | 01519 | 150 | Solar | 05_12_11J3 | 09/06/2019 | 09/10/2019 | 0 | 0 | 0 | 09/11/2019 | 09/11/2019 | 12 | 1 | 11 | 10/22/2019 | 11/25/2019 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  | 11/25/2019 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 12/10/2019 | 09/06/2019 | 9/29/2020 | Y | EXP | 365 | 07/29/2020 | 08/25/2020 | 27 | 0 | 27 |  |  | 9/28/2020 | Connected |  | N
National Grid | GRAFTON | 419319 | 01519 | 240 | Solar | 05_12_11J3 | 05/26/2022 | 06/13/2022 | 11 | 4 | 7 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2022 | 05/26/2022 | 12/21/2024 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2024 | Connected |  | N
National Grid | GRAFTON | 457068 | 01519 | 15.2 | Solar | 05_12_11J3 | 09/07/2022 | 09/09/2022 | 2 | 0 | 2 | 09/12/2022 | 09/12/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 |  | 10/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2022 | Connected |  | N
National Grid | GRAFTON | 484436 | 01519 | 15.2 | Solar | 05_12_11J3 | 12/09/2022 | 12/15/2022 | 5 | 4 | 1 | 12/16/2022 | 12/16/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2023 |  | 2/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2023 | Connected |  | N
National Grid | MILLBURY | 688885 | 01527 | 3.8 | Solar | 05_12_11J3 | 05/01/2025 | 06/17/2025 | 4 | 0 | 4 | 06/18/2025 | 06/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 | 05/01/2025 | 7/25/2026 | Y | EXP | 365 | 11/15/2025 | 11/14/2025 | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | MILLBURY | 176016 | 01527 | 1000 | Solar | 05_01_601W1 | 01/23/2015 | 01/23/2015 | 26 | 23 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/03/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 176015 | 01519 | 1000 | Solar | 05_01_601W1 | 01/23/2015 | 01/23/2015 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/03/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 176014 | 01519 | 1000 | Solar | 05_01_601W1 | 01/23/2015 | 01/23/2015 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/03/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 638822 | 01519 | 7.6 | Solar | 05_01_601W1 | 09/12/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 09/12/2024 | 2/12/2026 | Y | EXP | 365 | 06/11/2025 | 07/14/2025 | 34 | 0 | 34 |  |  | 7/30/2025 | Connected |  | N
National Grid | GRAFTON | 650682 | 01519 | 5.76 | Solar | 05_01_601W1 | 11/11/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/11/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | GRAFTON | 193346 | 01519 | 2040 | Solar | 05_01_601W4 | 10/18/2018 |  | 17 | 16 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 714226 | 01527 | 60 | Solar | 05_05_28W42 | 08/23/2025 | 11/06/2025 | 50 | 41 | 9 | 11/07/2025 | 11/07/2025 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GRAFTON | 211048 | 01519 | 492 | Solar | 05_05_28W42 | 04/17/2019 | 04/25/2019 | 5 | 0 | 5 | 04/26/2019 | 04/26/2019 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 476578 | 01519 | 180 | Solar | 05_05_28W42 | 11/10/2022 | 12/22/2022 | 28 | 18 | 10 | 12/23/2022 | 12/23/2022 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 647467 | 01519 | 5.76 | Solar | 49_56_33F1 | 10/21/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 10/21/2024 | 1/27/2026 | Y | EXP | 365 | 03/19/2025 | 05/15/2025 | 58 | 0 | 58 |  |  | 6/4/2025 | Connected |  | N
National Grid | GRAFTON | 746413 | 01519 | 17.6 | Solar | 49_56_33F4 | 01/20/2026 | 01/22/2026 | 2 | 0 | 2 | 01/23/2026 | 01/23/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GRAFTON | 174310 | 01519 | 12 | Solar | 49_56_33F4 | 09/20/2011 | 09/20/2011 | 159 | 0 | 159 | 09/19/2012 | 09/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/20/2011 | 12/31/2011 | Y | EXP | 347 | 02/03/2014 | 02/14/2014 | 9 | 0 | 9 | 4/5/2012 | 4/5/2012 | 1/31/2014 | Connected |  | N
National Grid | GRAFTON | 314962 | 01519 | 0 | Solar | 49_56_33F4 | 10/07/2020 | 10/09/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 |  | 10/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2021 | Connected |  | N
National Grid | GRAFTON | 175197 | 01519 | 1000 | Solar | 05_01_0012 | 05/05/2011 | 05/05/2011 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/13/2011 | 06/23/2011 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2012 | 05/05/2011 | 12/31/2012 | Y | STD | 168 | 08/21/2013 | 12/12/2013 | 77 | 0 | 77 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N
National Grid | MILLBURY | 175195 | 01527 | 1000 | Solar | 05_01_0012 | 05/05/2011 | 05/05/2011 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/13/2011 | 06/23/2011 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2012 | 05/05/2011 | 12/31/2012 | Y | STD | 168 | 08/21/2013 | 12/12/2013 | 77 | 0 | 77 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N
National Grid | GRAFTON | 178087 | 01519 | 4300 | Solar | 05_01_0012 | 05/09/2017 | 05/09/2017 | 18 | 16 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/06/2017 | 08/28/2017 | 58 | 49 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 | 05/09/2017 | 1/10/2022 | Y | STD | 35 | 06/17/2020 | 10/11/2021 | 380 | 5 | 375 | 11/16/2021 | 11/15/2021 | 12/30/2021 | Connected |  | N
National Grid | GRAFTON | 178116 | 01519 | 1500 | Solar | 05_01_0012 | 05/09/2017 | 05/09/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2017 | 08/28/2017 | 60 | 49 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 | 05/09/2017 | 10/16/2021 | Y | STD | 35 |  |  | 0 | 0 | 0 |  |  | 10/4/2021 | Connected |  | N
National Grid | GRAFTON | 176232 | 01519 | 60 | Natural Gas | 05_01_HT40 | 02/13/2015 | 02/13/2015 | 10 | 7 | 3 | 03/02/2015 | 03/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2015 |  | 7/31/2015 | N | EXP | 149 |  |  | 0 | 0 | 0 | 2/19/2016 | 2/19/2016 | 2/18/2016 | Connected |  | N
National Grid | WORCESTER | 174853 | 01602 | 990 | Solar | 05_05_2248 | 04/16/2013 | 04/16/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2013 | 07/16/2013 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2016 | 04/16/2013 | 8/19/2020 | Y | STD | 1358 | 04/14/2020 | 04/13/2020 | 0 | 0 | 0 | 5/15/2020 | 5/14/2020 | 8/19/2020 | Connected |  | N
National Grid | WORCESTER | 174852 | 01604 | 0 | Solar | 05_05_2248 | 04/16/2013 | 04/16/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2013 | 07/16/2013 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2016 |  | 9/23/2019 | N | STD | 1274 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175104 | 01604 | 3960 | Solar | 05_05_2248 | 04/16/2013 | 04/16/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2013 | 07/16/2013 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2016 | 04/16/2013 | 8/19/2020 | Y | STD | 1358 | 04/14/2020 | 04/13/2020 | 0 | 0 | 0 | 5/15/2020 | 5/14/2020 | 8/19/2020 | Connected |  | N
National Grid | FALL RIVER | 175082 | 02721 | 75 | Solar | 05_05_2248 | 10/08/2013 | 10/08/2013 | 3 | 0 | 3 | 10/15/2013 | 10/15/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2013 |  | 12/31/2013 | N | EXP | 43 |  |  | 0 | 0 | 0 | 1/8/2014 | 1/8/2014 | 3/20/2014 | Connected |  | N
National Grid | FALL RIVER | 177702 | 02723 | 3469 | Solar | 05_05_2274 | 05/25/2017 | 05/25/2017 | 54 | 53 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2017 | 09/01/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2018 | 05/25/2017 | 12/31/2020 | Y | STD | 444 |  |  | 0 | 0 | 0 |  |  | 12/31/2020 | Connected |  | N
National Grid | FALL RIVER | 174298 | 02721 | 2000 | Solar | 05_05_2284 | 12/22/2011 | 12/22/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2013 | 12/22/2011 | 3/1/2012 | Y | STD | 328 | 01/07/2014 | 03/25/2014 | 52 | 0 | 52 | 12/26/2013 | 12/26/2013 | 12/26/2013 | Connected |  | N
National Grid | FALL RIVER | 174437 | 02721 | 1000 | Solar | 05_05_2284 | 06/29/2012 | 06/29/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2012 | 08/22/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/12/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 174957 | 02721 | 3334 | Solar | 05_05_2284 | 03/01/2013 | 03/01/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 03/21/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 7/16/2015 | 7/16/2015 | 7/21/2015 | Connected |  | N
National Grid | NORTHAMPTON | 175137 | 01060 | 5000 | Solar | 05_05_2284 | 11/12/2012 | 11/12/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2012 | 01/04/2013 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 178759 | 01060 | 3000 | Solar | 05_05_2284 | 12/22/2011 | 12/22/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2012 | 12/22/2011 | 3/1/2012 | Y | STD | 25 | 07/02/2013 | 10/04/2013 | 66 | 0 | 66 | 9/19/2013 | 9/19/2013 | 11/18/2013 | Connected |  | N
National Grid | MEDFORD | 397260 | 02155 | 2250 | Solar | 05_05_2284 | 03/15/2022 |  | 165 | 157 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 397258 | 02155 | 1500 | Solar | 05_05_2284 | 03/15/2022 |  | 166 | 158 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 214604 | 02155 | 150 | Solar | 05_05_2285 | 03/28/2019 | 04/17/2019 | 12 | 6 | 6 | 04/18/2019 | 04/18/2019 | 33 | 7 | 26 | 08/07/2019 | 10/18/2019 | 51 | 13 | 38 |  |  | 0 | 0 | 0 |  | 10/18/2019 | 51 | 13 | 38 |  |  | 0 | 0 | 0 | 10/30/2019 | 03/28/2019 | 3/28/2022 | Y | EXP | 28 | 10/05/2021 | 03/17/2022 | 164 | 4 | 160 |  |  | 3/25/2022 | Connected |  | N
National Grid | MEDFORD | 176317 | 02155 | 4890 | Solar | 05_05_2286 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/12/2015 | 06/09/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 | 05/08/2015 | 7/7/2017 | Y | STD | 561 | 06/21/2017 | 08/02/2017 | 29 | 0 | 29 | 8/24/2017 | 8/24/2017 | 8/25/2017 | Connected |  | N
National Grid | MEDFORD | 176520 | 02155 | 768 | Solar | 05_07_1104 | 10/05/2015 | 10/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2016 | 02/10/2016 | 22 | 4 | 18 | 10/06/2015 | 11/04/2015 | 20 | 0 | 20 |  | 02/10/2016 | 22 | 4 | 18 |  |  | 0 | 0 | 0 | 10/5/2017 |  | 12/1/2017 | N | STD | 57 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 342873 | 02155 | 2575 | Solar | 05_07_1104 | 06/09/2021 | 07/16/2021 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2021 | 08/20/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 06/09/2021 | 10/30/2023 | Y | STD | 49 | 06/14/2023 | 06/13/2023 | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N
National Grid | MEDFORD | 175399 | 02155 | 1850 | Natural Gas | 05_07_1202 | 11/17/2014 | 11/17/2014 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2014 | 12/23/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2015 |  | 12/31/2016 | N | STD | 495 |  |  | 0 | 0 | 0 | 12/14/2015 | 12/14/2015 | 12/14/2015 | Connected |  | N
National Grid | GARDNER | 174160 | 01440 | 2000 | Solar | 05_09_0504 | 04/16/2012 | 04/16/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 06/26/2012 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/15/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 174159 | 01440 | 3000 | Solar | 05_09_0504 | 04/16/2012 | 04/16/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 06/26/2012 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/15/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 174158 | 01440 | 3800 | Solar | 05_09_0504 | 04/16/2012 | 04/16/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 06/26/2012 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 08/17/2013 | 10/15/2013 | 39 | 0 | 39 | 8/9/2013 | 04/16/2012 | 12/31/2016 | Y | STD | 124 |  |  | 0 | 0 | 0 | 2/23/2016 | 2/23/2016 | 2/23/2016 | Connected |  | N
National Grid | NORTH BROOKFIELD | 175737 | 01535 | 5350 | Solar | 05_09_0504 | 08/11/2014 | 08/11/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2014 | 09/23/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 |  | 12/31/2016 | N | STD | 64 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 176198 | 01440 | 144 | Solar | 05_09_0504 | 02/16/2015 | 02/16/2015 | 4 | 0 | 4 | 02/23/2015 | 02/23/2015 | 206 | 29 | 177 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2015 |  | 6/30/2015 | N | EXP | 69 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 178102 | 01440 | 4980 | Solar | 05_09_0504 | 09/08/2017 | 09/14/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2017 | 10/09/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 | 09/08/2017 | 12/29/2023 | Y | STD | 481 | 01/31/2023 | 09/12/2023 | 225 | 121 | 104 |  |  | 12/29/2023 | Connected |  | N
National Grid | FALL RIVER | 178162 | 02720 | 2490 | Solar | 05_09_0504 | 02/12/2018 | 02/12/2018 | 31 | 2 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2018 | 04/17/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 192369 | 02720 | 410 | Solar | 05_09_0504 | 09/14/2018 | 11/29/2018 | 127 | 26 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2018 | 03/22/2019 | 77 | 26 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 178039 | 02720 | 2490 | Solar | 05_09_0507 | 10/27/2017 | 11/14/2017 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 | 12/11/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 2/26/2021 | N | STD | 885 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 185520 | 02721 | 1000 | Solar | 05_09_1003 | 05/25/2018 | 05/25/2018 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2018 | 08/10/2018 | 26 | 21 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTPORT | 175649 | 02790 | 5.38 | Solar | 05_12_1384 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/16/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 176329 | 02790 | 3.8 | Solar | 05_12_1384 | 07/20/2015 | 07/20/2015 | 4 | 4 | 0 | 07/27/2015 | 07/27/2015 | 198 | 88 | 110 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2016 |  | 7/26/2016 | N | EXP | 169 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTPORT | 176389 | 02790 | 6 | Solar | 05_12_1384 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/6/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 176486 | 01535 | 5 | Solar | 05_12_1384 | 12/09/2015 | 12/09/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/14/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 177075 | 01535 | 10 | Solar | 05_12_1384 | 08/03/2016 | 08/03/2016 | 1 | 1 | 0 | 08/05/2016 | 08/05/2016 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/9/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 177827 | 01535 | 10 | Solar | 05_12_1384 | 06/09/2017 | 06/09/2017 | 7 | 0 | 7 | 06/20/2017 | 06/20/2017 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/14/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 192763 | 01535 | 8 | Solar | 05_12_1384 | 11/07/2018 |  | 59 | 26 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 525248 | 01602 | 3.84 | Solar | 05_12_1384 | 05/22/2023 | 05/23/2023 | 1 | 0 | 1 | 05/24/2023 | 05/24/2023 | 175 | 149 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 661725 | 02771 | 15.2 | Solar | 05_12_1384 | 01/09/2025 | 01/24/2025 | 11 | 7 | 4 | 01/27/2025 | 01/27/2025 | 68 | 50 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 685356 | 02771 | 10 | Solar | 05_12_1384 | 04/15/2025 | 05/05/2025 | 1 | 0 | 1 | 05/09/2025 | 05/09/2025 | 51 | 39 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  | 7/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/18/2025 | Connected |  | N
National Grid | SEEKONK | 696793 | 02771 | 9.28 | Solar | 05_12_1384 | 06/06/2025 | 06/27/2025 | 5 | 1 | 4 | 06/30/2025 | 06/30/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 174485 | 02703 | 3 | Solar | 05_12_2302E | 12/29/2010 | 12/29/2010 | 12 | 0 | 12 | 01/21/2011 | 01/21/2011 | 1449 | 0 | 1449 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2011 |  | 12/31/2016 | N | EXP | 2132 |  |  | 0 | 0 | 0 | 1/18/2013 | 1/18/2013 |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 174562 | 02763 | 600 | Wind | 05_12_2305 | 09/30/2011 | 09/30/2011 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2011 | 12/09/2011 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2013 |  | 10/31/2012 | N | STD | 292 |  |  | 0 | 0 | 0 | 1/7/2014 | 1/7/2014 | 1/22/2014 | Connected |  | N
National Grid | FRANKLIN | 661151 | 02038 | 2000 | Other | 05_12_2306 | 08/11/2025 |  | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 175063 | 02769 | 2880 | Solar | 05_12_2307 | 10/23/2012 | 10/23/2012 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/06/2012 | 12/27/2012 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2014 |  | 7/1/2013 | N | STD | 255 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 174252 | 02769 | 450 | Solar | 05_12_2327 | 02/27/2012 | 02/27/2012 | 27 | 0 | 27 | 04/10/2012 | 04/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2012 |  | 6/15/2012 | N | EXP | 181 |  |  | 0 | 0 | 0 | 12/31/2012 | 12/31/2012 | 12/31/2012 | Connected |  | N
National Grid | MELROSE | 174956 | 02176 | 260 | Solar | 05_12_2335 | 02/28/2013 | 02/28/2013 | 3 | 0 | 3 | 03/11/2013 | 03/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2013 |  | 7/31/2013 | N | EXP | 54 |  |  | 0 | 0 | 0 | 12/19/2013 | 12/19/2013 | 12/19/2013 | Connected |  | N
National Grid | FRANKLIN | 435099 | 02038 | 0 | Other | 05_12_2335 | 07/05/2022 | 10/28/2022 | 81 | 71 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2022 | 11/30/2022 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 177936 | 02038 | 300 | Natural Gas | 05_12_2338 | 06/20/2017 | 06/20/2017 | 4 | 0 | 4 | 06/26/2017 | 06/26/2017 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2017 |  | 7/27/2018 | N | EXP | 338 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 194606 | 02149 | 336 | Solar | 05_12_2338 | 10/08/2018 | 10/15/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2018 |  | 8/30/2021 | N | EXP | 385 |  |  | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | METHUEN | 175156 | 01844 | 82.8 | Solar | 05_12_2344 | 11/12/2013 | 11/12/2013 | 6 | 0 | 6 | 11/21/2013 | 11/21/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2013 |  | 12/31/2013 | N | EXP | 28 |  |  | 0 | 0 | 0 | 4/24/2014 | 4/24/2014 | 4/24/2014 | Connected |  | N
National Grid | PLAINVILLE | 176235 | 02762 | 4000 | Natural Gas | 05_12_2344 | 02/17/2015 | 02/17/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/24/2015 | 03/25/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 | 02/17/2015 | 6/15/2017 | Y | STD | 237 | 09/25/2017 | 09/25/2017 | 0 | 0 | 0 | 9/29/2017 | 9/29/2017 | 9/29/2017 | Connected |  | N
National Grid | QUINCY | 190186 | 02171 | 50 | Solar | 05_12_2344 | 07/09/2018 | 07/13/2018 | 2 | 0 | 2 | 07/16/2018 | 07/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2018 |  | 12/30/2019 | N | EXP | 53 |  |  | 0 | 0 | 0 |  |  | 12/30/2019 | Connected |  | N
National Grid | QUINCY | 195969 | 02171 | 240 | Solar | 05_12_2344 | 10/04/2018 | 10/26/2018 | 15 | 15 | 0 | 10/29/2018 | 10/29/2018 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2019 |  | 12/16/2019 | N | EXP | 265 |  |  | 0 | 0 | 0 |  |  | 12/30/2019 | Connected |  | N
National Grid | QUINCY | 191794 | 02169 | 66.6 | Solar | 05_12_2344 | 07/25/2018 | 07/26/2018 | 0 | 0 | 0 | 07/27/2018 | 07/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  | 12/16/2019 | N | EXP | 53 |  |  | 0 | 0 | 0 |  |  | 12/30/2019 | Connected |  | N
National Grid | PALMER | 281295 | 01069 | 0 | Other | 05_12_2344 | 03/04/2020 | 03/11/2020 | 5 | 2 | 3 |  |  | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 03/04/2020 | 2/10/2024 | Y | STD | 7 |  |  | 0 | 0 | 0 |  |  | 12/29/2023 | Connected |  | N
National Grid | PALMER | 355956 | 01069 | 240 | Solar | 05_12_2344 | 07/23/2021 | 05/11/2022 | 201 | 191 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 07/23/2021 | 9/2/2026 | Y | EXP | 514 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 175311 | 01069 | 1560 | Natural Gas | 05_12_2349 | 06/27/2014 | 06/27/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/07/2014 | 08/08/2014 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2015 | 06/27/2014 | 11/22/2019 | Y | STD | 1581 | 08/06/2019 | 08/05/2019 | 0 | 0 | 0 |  |  | 11/22/2019 | Connected |  | N
National Grid | MONSON | 409260 | 01057 | 480 | Solar | 05_12_2364 | 06/15/2022 | 07/13/2022 | 17 | 8 | 9 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | PALMER | 434644 | 01069 | 240 | Solar | 05_12_2364 | 06/06/2022 | 06/30/2022 | 17 | 10 | 7 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | PALMER | 434942 | 01069 | 240 | Solar | 05_12_2364 | 09/23/2022 | 10/05/2022 | 8 | 0 | 8 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | PALMER | 174567 | 01069 | 2000 | Wind | 05_12_2364 | 07/13/2011 | 07/13/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/28/2011 | 09/13/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2012 | 07/13/2011 | 10/31/2012 | Y | STD | 91 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/31/2012 | Connected |  | N
National Grid | PALMER | 174566 | 01069 | 2000 | Wind | 05_12_2364 | 07/13/2011 | 07/13/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2012 | 07/13/2011 | 8/1/2012 | Y | STD |  |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/31/2012 | Connected |  | N
National Grid | MONSON | 174899 | 01057 | 2500 | Wind | 05_12_2364 | 10/28/2011 | 10/28/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 02/06/2012 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 10/28/2011 | 11/30/2012 | Y | STD | 12 | 11/20/2012 | 11/26/2012 | 3 | 0 | 3 | 12/10/2012 | 12/10/2012 | 12/14/2012 | Connected |  | N
National Grid | ADAMS | 174823 | 01220 | 2000 | Solar | 05_12_2365 | 07/30/2012 | 07/30/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2012 | 10/19/2012 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2013 | 07/30/2012 | 4/1/2014 | Y | STD | 336 |  |  | 0 | 0 | 0 | 5/1/2014 | 5/1/2014 | 5/8/2014 | Connected |  | N
National Grid | LYNN | 396930 | 01902 | 1000 | Solar | 05_12_2365 | 04/27/2022 |  | 144 | 136 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 621831 | 01902 | 120 | Solar | 05_12_2370 | 07/08/2024 | 12/20/2024 | 114 | 103 | 11 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 186728 | 01902 | 88 | Solar | 05_12_2370 | 05/30/2018 | 05/30/2018 | 0 | 0 | 0 | 06/04/2018 | 06/04/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2018 |  | 5/26/2020 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  | 8/11/2020 | Connected |  | N
National Grid | LYNN | 174486 | 01902 | 500 | Diesel | 05_12_2401 | 12/09/2010 | 12/09/2010 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2011 | 02/23/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2011 |  | 10/31/2012 | N | STD | 55 |  |  | 0 | 0 | 0 | 9/19/2012 | 9/19/2012 | 9/24/2012 | Connected |  | N
National Grid | LYNN | 177102 | 01902 | 1332 | Solar | 05_12_2401 | 05/26/2016 | 05/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/27/2016 | 07/07/2016 | 26 | 9 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2016 | 05/26/2016 | 9/29/2017 | Y | STD | 32 | 09/22/2017 | 02/14/2018 | 92 | 0 | 92 | 9/18/2017 | 9/18/2017 | 9/22/2017 | Connected |  | N
National Grid | LYNN | 318011 | 01902 | 250 | Solar | 05_12_2401 | 10/13/2020 | 10/23/2020 | 8 | 1 | 7 |  |  | 44 | 21 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2021 | 10/13/2020 | 11/13/2023 | Y | STD | 64 | 01/18/2023 | 10/31/2023 | 287 | 0 | 287 |  |  | 11/16/2023 | Connected |  | N
National Grid | LYNN | 433145 | 01902 | 0 | Other | 05_12_2401 | 07/06/2022 | 10/28/2022 | 80 | 72 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2022 | 11/22/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2024 | 07/06/2022 | 6/21/2026 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 215897 | 01902 | 400 | Solar | 05_14_1314 | 04/01/2019 | 04/05/2019 | 19 | 7 | 12 | 04/08/2019 | 04/08/2019 | 13 | 0 | 13 | 07/10/2019 | 07/09/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 07/09/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2019 |  | 12/16/2019 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  | 12/20/2019 | Connected |  | N
National Grid | LYNN | 178156 | 01902 | 176 | Solar | 05_14_1319 | 12/22/2017 | 12/22/2017 | 33 | 29 | 4 | 02/13/2018 | 02/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2018 |  | 1/31/2019 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  | 1/30/2019 | Connected |  | N
National Grid | LYNN | 587976 | 01902 | 950 | Natural Gas | 05_14_1321 | 03/07/2024 | 07/31/2024 | 100 | 90 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/01/2024 | 09/25/2024 | 39 | 19 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LYNN | 174275 | 01902 | 380 | Solar | 05_14_1321 | 12/20/2011 | 12/20/2011 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2012 |  | 4/1/2012 | N | EXP | 31 |  |  | 0 | 0 | 0 | 6/15/2012 | 6/15/2012 | 7/6/2012 | Connected |  | N
National Grid | SALEM | 174459 | 01970 | 250 | Solar | 05_14_1321 | 09/21/2011 | 09/21/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2012 |  | 10/31/2012 | N | EXP | 295 |  |  | 0 | 0 | 0 | 9/26/2012 | 9/26/2012 | 10/2/2012 | Connected |  | N
National Grid | LYNN | 603306 | 01905 | 50 | Solar | 05_14_1324 | 04/22/2024 | 07/31/2024 | 69 | 60 | 9 | 08/01/2024 | 08/01/2024 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 8/27/2026 | N | EXP | 28 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | AYER | 603274 | 01432 | 40 | Solar | 05_14_1324 | 04/17/2024 | 08/28/2024 | 92 | 84 | 8 | 08/29/2024 | 08/29/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 8/12/2026 | N | EXP | 28 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | REVERE | 378285 | 02151 | 60 | Solar | 05_14_1324 | 01/24/2022 | 03/29/2022 | 45 | 36 | 9 | 03/30/2022 | 03/30/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2022 | 01/24/2022 | 2/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2024 | Connected |  | N
National Grid | GLOUCESTER | 686652 | 01930 | 110 | Solar | 05_14_1324 | 05/05/2025 | 06/20/2025 | 32 | 22 | 10 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 423252 | 02176 | 160 | Solar | 05_14_1325 | 04/11/2022 | 05/06/2022 | 18 | 8 | 10 | 05/09/2022 | 05/09/2022 | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 | 04/11/2022 | 1/30/2025 | Y | EXP | 45 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 446168 | 02176 | 50 | Solar | 05_14_1325 | 07/22/2022 | 08/10/2022 | 13 | 4 | 9 | 08/11/2022 | 08/11/2022 | 30 | 10 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2022 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 176223 | 02149 | 232 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 | 08/18/2015 | 9/9/2016 | Y | EXP | 34 |  |  | 0 | 0 | 0 | 9/6/2017 | 9/6/2017 | 9/6/2017 | Connected |  | N
National Grid | EVERETT | 176222 | 02149 | 158 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 558 | 59 | 499 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 | 08/18/2015 | 9/9/2016 | Y | EXP | 34 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 176221 | 02155 | 122 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 |  | 9/9/2016 | N | EXP | 34 |  |  | 0 | 0 | 0 | 10/4/2017 | 10/4/2017 | 10/4/2017 | Connected |  | N
National Grid | MEDFORD | 176220 | 02155 | 349 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 185 | 160 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2016 | 08/18/2015 | 10/3/2018 | Y | EXP | 789 |  |  | 0 | 0 | 0 |  |  | 10/29/2018 | Connected |  | N
National Grid | MEDFORD | 176326 | 02155 | 3200 | Natural Gas | 05_14_2326 | 07/17/2015 | 07/17/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2015 | 08/18/2015 | 21 | 21 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 | 07/17/2015 | 8/20/2019 | Y | STD | 124 | 05/31/2017 | 10/30/2017 | 105 | 0 | 105 |  |  | 8/16/2019 | Connected |  | N
National Grid | MEDFORD | 176448 | 02155 | 140 | Solar | 05_14_2326 | 05/17/2016 | 05/17/2016 | 0 | 0 | 0 | 05/18/2016 | 05/18/2016 | 0 | 0 | 0 | 06/16/2016 | 08/10/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  | 08/10/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 8/25/2016 |  | 5/23/2017 | N | EXP | 271 |  |  | 0 | 0 | 0 | 5/23/2017 | 5/23/2017 | 5/23/2017 | Connected |  | N
National Grid | MEDFORD | 176445 | 02155 | 140 | Solar | 05_14_2326 | 05/16/2016 | 05/16/2016 | 0 | 0 | 0 | 05/16/2016 | 05/16/2016 | 0 | 0 | 0 | 08/19/2016 | 08/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2016 |  | 9/21/2017 | N | EXP | 392 |  |  | 0 | 0 | 0 | 7/19/2017 | 7/19/2017 | 7/19/2017 | Connected |  | N
National Grid | MEDFORD | 176444 | 02155 | 108 | Solar | 05_14_2326 | 05/06/2016 | 05/06/2016 | 0 | 0 | 0 | 05/16/2016 | 05/16/2016 | 435 | 0 | 435 | 06/16/2016 | 08/10/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  | 08/10/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 8/25/2016 |  | 2/28/2018 | N | EXP | 552 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 178093 | 02155 | 232 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 | 08/18/2015 | 7/15/2018 | Y | EXP | 114 |  |  | 0 | 0 | 0 |  |  | 6/11/2018 | Connected |  | N
National Grid | SALEM | 178092 | 01970 | 122 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 | 08/18/2015 | 10/17/2018 | Y | EXP | 118 |  |  | 0 | 0 | 0 |  |  | 10/4/2017 | Connected |  | N
National Grid | GLOUCESTER | 202326 | 01930 | 450 | Solar | 05_14_2326 | 11/28/2018 | 02/14/2019 | 43 | 38 | 5 | 02/15/2019 | 02/15/2019 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 206881 | 01930 | 278 | Solar | 05_14_2326 | 01/23/2019 | 03/11/2019 | 29 | 23 | 6 | 03/12/2019 | 03/12/2019 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 379254 | 01930 | 200 | Solar | 05_14_2326 | 09/14/2021 | 09/24/2021 | 8 | 0 | 8 |  |  | 44 | 4 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 178314 | 01930 | 2800 | Solar | 05_14_2329 | 02/26/2018 | 02/26/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2018 | 04/11/2018 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2018 |  | 3/31/2021 | N | STD | 543 | 01/17/2020 | 01/04/2021 | 353 | 5 | 348 |  |  | 3/11/2021 | Connected |  | N
National Grid | GLOUCESTER | 426199 | 01930 | 100 | Solar | 05_14_2355 | 08/29/2022 | 11/29/2022 | 62 | 54 | 8 |  |  | 33 | 7 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 | 08/29/2022 | 1/14/2026 | Y | STD | 343 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | GLOUCESTER | 186222 | 01930 | 100.8 | Solar | 05_14_2355 | 05/31/2018 | 05/31/2018 | 0 | 0 | 0 | 06/04/2018 | 06/04/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2018 |  | 3/11/2020 | N | EXP | 535 |  |  | 0 | 0 | 0 |  |  | 3/5/2020 | Connected |  | N
National Grid | BEVERLY | 348816 | 01915 | 499 | Solar | 05_14_2355 | 12/21/2021 |  | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 348813 | 01915 | 750 | Solar | 05_14_2355 | 09/21/2021 | 01/20/2022 | 563 | 554 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2022 | 03/03/2022 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 174119 | 01970 | 4968 | Solar | 05_14_2356 | 04/05/2012 | 04/19/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2014 | 04/05/2012 | 12/29/2017 | Y | STD | 1327 | 02/15/2017 | 08/21/2017 | 129 | 0 | 129 | 12/19/2017 | 12/19/2017 | 4/3/2017 | Connected |  | N
National Grid | SALEM | 177224 | 01970 | 995 | Landfill Gas | 05_14_2356 | 08/16/2016 | 08/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/16/2016 | 08/26/2016 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2017 | 08/16/2016 | 11/30/2020 | Y | STD | 177 | 03/11/2020 | 07/06/2020 | 117 | 0 | 117 | 11/4/2020 | 11/3/2020 | 11/12/2020 | Connected |  | N
National Grid | EVERETT | 175612 | 02149 | 2000 | Solar | 05_14_2358 | 12/16/2014 | 12/16/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 | 01/23/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2015 | N | STD |  | 12/16/2016 | 08/31/2017 | 177 | 0 | 177 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 175611 | 02149 | 3384 | Solar | 05_14_2358 | 12/16/2014 | 12/16/2014 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 | 12/02/2015 | 233 | 232 | 1 |  |  | 0 | 0 | 0 | 12/07/2015 | 12/07/2015 | 0 | 0 | 0 | 5/1/2016 | 12/16/2014 | 4/1/2023 | Y | STD | 546 | 12/16/2016 | 12/16/2016 | 0 | 0 | 0 | 4/11/2017 | 4/11/2017 | 4/3/2023 | Connected |  | N
National Grid | EVERETT | 178779 | 02149 | 2000 | Solar | 05_14_2358 | 12/16/2014 | 12/16/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 | 01/23/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2015 |  | 12/31/2016 | N | STD | 458 | 12/16/2016 | 02/14/2018 | 284 | 0 | 284 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 178778 | 02149 | 2000 | Solar | 05_14_2358 | 12/16/2014 | 12/16/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 | 01/23/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2015 |  | 12/31/2016 | N | STD | 458 | 12/16/2016 | 01/26/2018 | 271 | 0 | 271 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 524407 | 01843 | 500 | Solar | 05_14_2358 | 02/15/2024 | 08/01/2024 | 114 | 106 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2024 | 08/30/2024 | 21 | 14 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 619480 | 01843 | 500 | Solar | 05_14_2358 | 06/22/2024 | 08/26/2024 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2024 | 08/30/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 619478 | 01840 | 500 | Solar | 05_14_2358 | 06/22/2024 | 08/26/2024 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2024 | 08/30/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 619466 | 01841 | 500 | Solar | 05_14_2358 | 06/22/2024 | 08/26/2024 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2024 | 08/30/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174552 | 01840 | 420 | Landfill Gas | 05_14_2371 | 11/07/2011 | 11/07/2011 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174590 | 01840 | 1000 | Solar | 05_14_2376 | 07/20/2011 | 07/20/2011 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | STD | 12 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 174520 | 01840 | 1000 | Solar | 05_14_2377N | 10/07/2010 | 10/07/2010 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2011 | 10/07/2010 | 10/31/2012 | Y | STD | 53 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 8/3/2012 | Connected |  | N
National Grid | LAWRENCE | 174519 | 01840 | 1000 | Solar | 05_14_2377N | 10/07/2010 | 10/07/2010 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2011 | 10/07/2010 | 10/31/2012 | Y | STD | 53 |  |  | 0 | 0 | 0 | 1/18/2013 | 1/18/2013 | 8/3/2012 | Connected |  | N
National Grid | LAWRENCE | 174523 | 01840 | 1000 | Solar | 05_14_2377N | 10/07/2010 | 10/07/2010 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2011 | 10/07/2010 | 10/31/2012 | Y | STD | 53 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 8/3/2012 | Connected |  | N
National Grid | LAWRENCE | 174522 | 01840 | 1000 | Solar | 05_14_2377N | 10/07/2010 | 10/07/2010 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2011 | 10/07/2010 | 10/31/2012 | Y | STD | 53 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 8/3/2012 | Connected |  | N
National Grid | LAWRENCE | 174521 | 01840 | 750 | Solar | 05_14_2377N | 10/07/2010 | 10/07/2010 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2011 | 10/07/2010 | 10/31/2012 | Y | STD | 53 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 8/3/2012 | Connected |  | N
National Grid | LAWRENCE | 175030 | 01843 | 50 | Solar | 05_14_2377N | 03/21/2013 | 03/21/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 175029 | 01843 | 300 | Solar | 05_14_2377N | 03/21/2013 | 03/21/2013 | 6 | 0 | 6 | 04/02/2013 | 04/02/2013 | 0 | 0 | 0 | 06/11/2013 | 06/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2013 |  | 8/30/2013 | N | EXP | 79 |  |  | 0 | 0 | 0 | 8/23/2013 | 8/23/2013 | 9/19/2013 | Connected |  | N
National Grid | LAWRENCE | 174350 | 01843 | 675 | Solar | 05_14_2381 | 05/08/2012 | 05/08/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2012 | 07/03/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 177799 | 01843 | 266.4 | Solar | 05_14_2381 | 08/03/2017 | 08/03/2017 | 14 | 14 | 0 | 08/18/2017 | 08/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2017 |  | 8/9/2018 | N | EXP | 323 | 01/15/2018 | 01/15/2018 | 0 | 0 | 0 | 1/8/2018 | 1/8/2018 | 1/8/2018 | Connected |  | N
National Grid | ANDOVER | 225135 | 01845 | 486 | Solar | 05_14_2381 | 05/07/2019 | 06/06/2019 | 21 | 20 | 1 | 06/07/2019 | 06/07/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 732305 | 01845 | 470 | Solar | 05_14_2384 | 01/30/2026 | 02/23/2026 | 14 | 7 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/24/2026 |  | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 184585 | 01845 | 1920 | Solar | 05_14_2384 | 08/07/2018 | 08/22/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/23/2018 | 11/27/2018 | 58 | 38 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2019 | 08/07/2018 | 1/6/2022 | Y | STD | 329 |  |  | 0 | 0 | 0 |  |  | 12/30/2021 | Connected |  | N
National Grid | ANDOVER | 243763 | 01845 | 600 | Natural Gas | 05_14_2384 | 10/27/2020 | 12/03/2020 | 25 | 19 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2020 | 01/14/2021 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2021 | 10/27/2020 | 10/28/2022 | Y | STD | 399 | 09/22/2022 | 09/21/2022 | 0 | 0 | 0 |  |  | 10/5/2022 | Connected |  | N
National Grid | LAWRENCE | 174373 | 01843 | 260 | Solar | 05_14_2385 | 05/29/2012 | 05/29/2012 | 11 | 0 | 11 | 06/18/2012 | 06/18/2012 | 0 | 0 | 0 | 12/17/2012 | 01/30/2013 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  | 01/30/2013 | 29 | 0 | 29 |  |  | 0 | 0 | 0 | 1/30/2013 | 05/29/2012 | 10/31/2014 | Y | EXP | 639 | 07/28/2014 | 08/19/2016 | 513 | 0 | 513 | 5/14/2015 | 5/14/2015 | 12/3/2014 | Connected |  | N
National Grid | LAWRENCE | 175120 | 01843 | 2850 | Solar | 05_14_2385 | 10/18/2013 | 10/18/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2013 | 12/11/2013 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2015 | 10/18/2013 | 12/31/2016 | Y | STD | 725 | 06/23/2016 | 04/07/2017 | 197 | 0 | 197 | 12/21/2016 | 12/21/2016 | 12/28/2016 | Connected |  | N
National Grid | LAWRENCE | 175685 | 01843 | 4999 | Solar | 05_14_2385 | 12/23/2014 | 12/23/2014 | 16 | 15 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2015 | 01/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 | 12/23/2014 | 5/31/2017 | Y | STD | 671 | 01/16/2017 | 07/27/2017 | 133 | 0 | 133 | 6/5/2017 | 6/5/2017 | 6/7/2017 | Connected |  | N
National Grid | LAWRENCE | 176502 | 01843 | 499.5 | Solar | 05_14_2385 | 02/08/2016 | 02/08/2016 | 3 | 3 | 0 | 02/16/2016 | 02/16/2016 | 493 | 0 | 493 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/15/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 174303 | 01845 | 500 | Solar | 05_14_2387 | 12/29/2011 | 12/29/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 174583 | 01830 | 1000 | Solar | 05_14_2387 | 12/16/2009 | 12/16/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2011 | 12/16/2009 | 10/31/2012 | Y | STD | 454 |  |  | 0 | 0 | 0 | 9/17/2013 | 9/17/2013 | 9/17/2012 | Connected |  | N
National Grid | LAWRENCE | 174608 | 01841 | 1000 | Solar | 05_14_2387 | 12/16/2009 | 12/16/2009 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2011 | 12/16/2009 | 4/5/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 4/5/2012 | Connected |  | N
National Grid | LAWRENCE | 174607 | 01841 | 1000 | Solar | 05_14_2387 | 12/16/2009 | 12/16/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2011 | 12/16/2009 | 4/5/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 4/5/2012 | Connected |  | N
National Grid | METHUEN | 174606 | 01844 | 1000 | Solar | 05_14_2387 | 12/16/2009 | 12/16/2009 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2011 | 12/16/2009 | 4/5/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 4/5/2012 | Connected |  | N
National Grid | LAWRENCE | 174144 | 01841 | 999 | Solar | 05_14_2389 | 04/17/2012 | 04/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2012 |  | 12/3/2012 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176089 | 01830 | 990 | Solar | 05_14_2396N | 01/30/2015 | 01/30/2015 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/09/2015 | 11/04/2015 | 17 | 17 | 0 | 1/12/2016 |  | 8/31/2015 | N | STD | 134 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176088 | 01835 | 990 | Solar | 05_14_2396N | 01/30/2015 | 01/30/2015 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/09/2015 | 11/04/2015 | 17 | 17 | 0 | 1/12/2016 |  | 8/31/2015 | N | STD | 134 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 176087 | 01845 | 990 | Solar | 05_14_2396N | 01/30/2015 | 01/30/2015 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/09/2015 | 11/04/2015 | 17 | 17 | 0 | 1/12/2016 |  | 8/31/2015 | N | STD | 134 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 176122 | 01845 | 990 | Solar | 05_14_2396N | 01/30/2015 | 01/30/2015 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/09/2015 | 11/04/2015 | 17 | 17 | 0 | 4/15/2015 |  | 8/31/2015 | N | STD | 138 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 176121 | 01845 | 990 | Solar | 05_14_2396N | 01/30/2015 | 01/30/2015 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/09/2015 | 11/04/2015 | 17 | 17 | 0 | 1/12/2016 |  | 8/31/2015 | N | STD | 134 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 175619 | 01845 | 2000 | Hydro | 05_14_2399 | 04/30/2014 | 04/30/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/05/2014 | 08/12/2014 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 405845 | 01845 | 0 | Battery Add-On | 05_14_2399 | 01/25/2022 | 02/03/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2022 | 03/02/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 419852 | 01845 | 0 | Other | 05_14_2405 | 06/14/2022 | 08/01/2022 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2022 | 08/24/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ANDOVER | 725383 | 01845 | 500 | Solar | 05_14_2405 | 12/30/2025 |  | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | ANDOVER | 174669 | 01845 | 1980 | Solar | 05_14_2405 | 06/05/2013 | 06/05/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/17/2013 | 07/15/2013 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2014 | 06/05/2013 | 12/21/2023 | Y | STD | 15 | 10/11/2023 | 12/06/2023 | 57 | 0 | 57 |  |  | 12/29/2023 | Connected |  | N
National Grid | HAVERHILL | 176642 | 01835 | 375 | Solar | 05_14_2405 | 12/31/2015 | 12/31/2015 | 1 | 1 | 0 | 01/05/2016 | 01/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 1/9/2017 | N | EXP | 339 |  |  | 0 | 0 | 0 | 12/30/2016 | 12/30/2016 | 12/30/2016 | Connected |  | N
National Grid | METHUEN | 396685 | 01844 | 0 | Other | 05_14_2405 | 01/14/2022 | 01/28/2022 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 03/04/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 422863 | 01952 | 0 | Other | 05_14_2405 | 08/25/2022 | 09/26/2022 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2022 | 01/03/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 213621 | 01952 | 266.4 | Solar | 05_14_301 | 08/30/2019 | 10/24/2019 | 37 | 32 | 5 | 10/25/2019 | 10/25/2019 | 8 | 0 | 8 | 11/15/2019 | 02/18/2020 | 63 | 34 | 29 |  |  | 0 | 0 | 0 |  | 02/18/2020 | 63 | 34 | 29 |  |  | 0 | 0 | 0 | 2/24/2020 |  | 9/22/2023 | N | EXP | 3 |  |  | 0 | 0 | 0 |  |  | 6/27/2023 | Connected |  | N
National Grid | SALISBURY | 647606 | 01952 | 0 | Hydro | 05_14_304 | 02/04/2025 | 03/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SALISBURY | 174580 | 01952 | 275 | Solar | 05_14_304 | 09/28/2011 | 09/28/2011 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2011 | 09/28/2011 | 10/31/2012 | Y | EXP | 334 |  |  | 0 | 0 | 0 | 1/24/2013 | 1/24/2013 | 8/3/2012 | Connected |  | N
National Grid | SALISBURY | 679224 | 01952 | 250 | Solar | 05_14_306 | 04/16/2025 | 05/13/2025 | 18 | 8 | 10 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | AMESBURY | 556404 | 01913 | 250 | Solar | 05_14_306 | 11/22/2023 | 12/05/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/06/2023 | 01/11/2024 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2024 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 587969 | 01913 | 325 | Natural Gas | 05_14_306 | 02/26/2024 | 08/01/2024 | 109 | 99 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2024 | 08/27/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 673515 | 01852 | 200 | Solar | 05_14_315 | 02/24/2025 |  | 257 | 67 | 190 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | Y
National Grid | LOWELL | 204310 | 01852 | 2649 | Natural Gas | 05_14_319 | 01/14/2019 | 02/19/2019 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/20/2019 | 02/10/2020 | 245 | 221 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2020 | 01/14/2019 | 7/20/2022 | Y | STD | 575 | 04/23/2021 | 10/12/2021 | 62 | 0 | 62 |  |  | 5/3/2022 | Connected |  | N
National Grid | LOWELL | 274261 | 01852 | 100 | Solar | HVDC Converter to Sandy Pond | 01/22/2020 | 02/10/2020 | 13 | 7 | 6 | 02/11/2020 | 02/11/2020 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2020 |  | 10/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2020 | Connected |  | N
National Grid | CHELMSFORD | 178439 | 01824 | 132 | Solar | 05_07_68J1 | 04/02/2018 | 04/02/2018 | 12 | 3 | 9 | 04/20/2018 | 04/20/2018 | 60 | 36 | 24 | 09/05/2018 | 10/17/2018 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  | 10/17/2018 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 4/8/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 177862 | 01824 | 4990 | Solar | 05_01_601W3 | 06/13/2017 | 06/21/2017 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/21/2017 | 07/19/2017 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2019 | 06/13/2017 | 6/12/2020 | Y | STD | 587 | 09/13/2019 | 11/14/2019 | 62 | 0 | 62 |  |  | 6/16/2020 | Connected |  | N
National Grid | CHELMSFORD | 195202 | 01824 | 2310 | Solar | 05_01_601W3 | 09/28/2018 | 10/22/2018 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 | 12/18/2018 | 38 | 19 | 19 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 314893 | 01876 | 25 | Solar | 05_01_601W3 | 09/25/2020 | 09/29/2020 | 1 | 0 | 1 | 09/30/2020 | 09/30/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 09/25/2020 | 2/28/2023 | Y | EXP | 455 | 09/10/2021 | 09/09/2021 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 399116 | 01862 | 234.6 | Solar | 05_05_3431W2 | 12/07/2021 | 02/26/2022 | 56 | 50 | 6 |  |  | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 | 12/07/2021 | 8/17/2026 | Y | STD | 28 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BILLERICA | 531270 | 01862 | 380 | Solar | 05_05_3431W2 | 07/20/2023 | 08/04/2023 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2023 | 09/05/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 | 07/20/2023 | 6/24/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | BILLERICA | 750606 | 01862 | 0 | Battery Add-On | 05_05_3431W2 | 02/11/2026 | 02/20/2026 | 6 | 4 | 2 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTFORD | 178801 | 01886 | 275 | Solar | 05_05_3431W2 | 02/27/2018 | 02/27/2018 | 10 | 10 | 0 | 03/29/2018 | 03/29/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2018 |  | 3/5/2019 | N | EXP | 337 |  |  | 0 | 0 | 0 |  |  | 10/12/2018 | Connected |  | N
National Grid | WESTFORD | 178789 | 01886 | 1775 | Solar | 05_05_3431W2 | 03/04/2016 | 03/04/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2016 | 04/21/2016 | 31 | 17 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/9/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 184044 | 01886 | 292 | Natural Gas | 05_05_3431W2 | 06/07/2018 | 06/07/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2018 | 08/13/2018 | 37 | 29 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 |  | 3/31/2020 | N | STD | 291 |  |  | 0 | 0 | 0 | 3/31/2020 | 3/30/2020 | 3/30/2020 | Connected |  | N
National Grid | WESTFORD | 491954 | 01886 | 6.96 | Solar | 05_05_3431W2 | 02/07/2023 | 02/08/2023 | 1 | 0 | 1 | 02/09/2023 | 02/09/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 |  | 12/15/2024 | N | EXP | 465 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | WESTFORD | 529749 | 01886 | 6 | Solar | 05_05_3431W2 | 09/06/2023 | 06/04/2023 | 1 | 0 | 1 | 09/08/2023 | 09/08/2023 | 85 | 63 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2023 |  | 1/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | BILLERICA | 637086 | 01821 | 7.6 | Solar | 05_05_3431W2 | 09/02/2024 | 09/18/2024 | 3 | 0 | 3 | 09/19/2024 | 09/19/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2024 |  | 10/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2025 | Connected |  | Y
National Grid | SALISBURY | 662546 | 01952 | 3.8 | Solar | 05_05_3431W2 | 12/24/2024 | 01/13/2025 | 4 | 0 | 4 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | SALISBURY | 722327 | 01952 | 15.36 | Solar | 05_05_3431W2 | 09/26/2025 |  | 32 | 28 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 174515 | 01952 | 1000 | Solar | 05_09_524L1 | 07/20/2012 | 07/20/2012 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2012 | 08/23/2012 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/28/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 174514 | 01952 | 2000 | Solar | 05_09_524L1 | 07/20/2012 | 07/20/2012 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2012 | 08/23/2012 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/28/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 175022 | 01952 | 2000 | Solar | 05_09_524L1 | 10/08/2012 | 10/08/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2012 | 11/24/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 175146 | 01879 | 3500 | Solar | 05_09_524L1 | 04/29/2013 | 04/29/2013 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2013 | 08/11/2014 | 310 | 0 | 310 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 175138 | 01879 | 1000 | Solar | 05_09_524L1 | 11/12/2012 | 11/12/2012 | 14 | 9 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2012 | 01/16/2013 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 174121 | 01950 | 2000 | Solar | 05_14_43L7 | 03/29/2012 | 03/29/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/29/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 174120 | 01950 | 2000 | Solar | 05_14_43L7 | 03/29/2012 | 03/29/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/29/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 175384 | 01952 | 52 | Solar | 05_14_43L7 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2014 |  | 11/28/2014 | N | EXP | 12 |  |  | 0 | 0 | 0 | 8/7/2014 | 8/7/2014 | 1/15/2015 | Connected |  | N
National Grid | NEWBURY | 177537 | 01950 | 300 | Solar | 05_14_43L7 | 09/14/2017 | 09/14/2017 | 18 | 18 | 0 | 10/11/2017 | 10/11/2017 | 0 | 0 | 0 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2018 |  | 9/19/2018 | N | EXP | 226 |  |  | 0 | 0 | 0 |  |  | 5/11/2018 | Connected |  | N
National Grid | NEWBURY | 327460 | 01951 | 10 | Solar | 05_14_43L7 | 12/09/2020 | 12/17/2020 | 5 | 3 | 2 | 12/18/2020 | 12/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2021 | 12/09/2020 |  | Y | EXP | 365 | 04/14/2021 | 04/26/2021 | 12 | 0 | 12 |  |  | 5/7/2021 | Connected |  | N
National Grid | NEWBURY | 367917 | 01922 | 900 | Solar | 05_14_43L7 | 09/08/2021 | 10/06/2021 | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2021 | 12/14/2021 | 46 | 21 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2022 | 09/08/2021 | 7/8/2024 | Y | STD | 38 | 07/12/2023 | 04/10/2024 | 272 | 184 | 88 |  |  | 9/5/2024 | Connected |  | N
National Grid | LOWELL | 422534 | 01852 | 3.8 | Solar | 05_14_43L7 | 04/07/2022 | 04/08/2022 | 1 | 0 | 1 | 04/11/2022 | 04/11/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2022 |  | 4/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2022 | Connected |  | N
National Grid | LOWELL | 532991 | 01852 | 0 | Solar | 05_14_43L7 | 06/12/2023 | 06/13/2023 | 1 | 0 | 1 | 06/14/2023 | 06/14/2023 | 30 | 10 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  | 8/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | LOWELL | 565734 | 01852 | 14.3 | Solar | 05_14_43L7 | 11/01/2023 | 11/17/2023 | 11 | 8 | 3 | 11/20/2023 | 11/20/2023 | 52 | 38 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  | 2/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2024 | Connected |  | N
National Grid | LOWELL | 567193 | 01852 | 0 | Battery Add-On | 05_14_43L7 | 11/02/2023 | 11/15/2023 | 8 | 5 | 3 | 11/16/2023 | 11/16/2023 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2024 | Connected |  | N
National Grid | LOWELL | 650475 | 01852 | 5.76 | Solar | 05_14_43L7 | 10/31/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2025 | Connected |  | N
National Grid | LOWELL | 673471 | 01852 | 7.25 | Solar | 05_14_43L7 | 02/21/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | LOWELL | 674186 | 01852 | 3.8 | Solar | 05_14_43L7 | 02/26/2025 | 03/27/2025 | 12 | 8 | 4 | 03/28/2025 | 03/28/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 | 02/26/2025 | 7/24/2026 | Y | EXP | 365 | 08/21/2025 | 12/22/2025 | 124 | 0 | 124 |  |  | 12/3/2025 | Connected |  | N
National Grid | LOWELL | 694259 | 01851 | 15.2 | Solar | 05_14_43L7 | 06/02/2025 | 06/04/2025 | 2 | 0 | 2 | 06/05/2025 | 06/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  | 7/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 174844 | 01432 | 2000 | Solar | 05_14_2396 | 11/04/2011 | 11/04/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2011 | 12/28/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/5/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 174843 | 02322 | 2000 | Solar | 05_14_2396 | 11/04/2011 | 11/04/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2011 | 12/28/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 174842 | 01473 | 2000 | Solar | 05_14_2396 | 11/04/2011 | 11/04/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2011 | 12/28/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 175064 | 01473 | 4016 | Solar | 05_09_501L4 | 10/23/2012 | 10/23/2012 | 13 | 11 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2012 | 02/05/2013 | 41 | 0 | 41 |  |  | 0 | 0 | 0 | 04/23/2014 | 06/11/2014 | 34 | 0 | 34 | 6/11/2014 | 10/23/2012 | 7/1/2016 | Y | STD | 751 | 09/09/2016 | 06/20/2017 | 193 | 0 | 193 | 6/28/2017 | 6/28/2017 | 6/28/2017 | Connected |  | N
National Grid | GARDNER | 175065 | 01440 | 936 | Solar | 05_09_501L4 | 03/28/2013 | 03/28/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2013 | 06/14/2013 | 46 | 0 | 46 |  |  | 0 | 0 | 0 | 04/23/2014 | 06/11/2014 | 34 | 0 | 34 | 6/11/2014 |  | 7/1/2016 | N | STD | 751 |  |  | 0 | 0 | 0 | 7/12/2017 | 7/12/2017 | 8/4/2017 | Connected |  | N
National Grid | FOXBOROUGH | 677862 | 02035 | 240 | Solar | 05_05_3451W3 | 03/17/2025 | 04/07/2025 | 16 | 6 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FOXBOROUGH | 731605 | 02035 | 13.8 | Solar | 05_05_3451W3 | 11/06/2025 | 11/25/2025 | 4 | 1 | 3 | 11/26/2025 | 11/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FOXBOROUGH | 740765 | 02035 | 11.4 | Solar | 05_05_3451W3 | 12/17/2025 | 12/18/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FOXBOROUGH | 178767 | 02035 | 225 | Solar | 05_05_3451W3 | 07/31/2012 | 07/31/2012 | 8 | 2 | 6 | 08/14/2012 | 08/14/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 12/18/2012 | 12/18/2012 | 12/31/2012 | Connected |  | N
National Grid | FOXBOROUGH | 178780 | 02035 | 19.995 | Solar | 05_05_3451W3 | 08/08/2014 | 08/08/2014 | 7 | 1 | 6 | 08/20/2014 | 08/20/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2014 |  | 11/28/2014 | N | EXP | 85 |  |  | 0 | 0 | 0 | 9/4/2014 | 9/4/2014 | 11/6/2014 | Connected |  | N
National Grid | FOXBOROUGH | 178797 | 02035 | 2310 | Solar | 05_05_3451W3 | 10/23/2017 | 10/23/2017 | 31 | 29 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 | 01/04/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2018 |  | 10/31/2018 | N | STD | 77 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 178795 | 02035 | 4950 | Solar | 05_05_3451W3 | 03/06/2017 | 03/06/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2017 | 03/28/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2017 | 03/06/2017 | 12/31/2019 | Y | STD | 753 | 03/08/2019 | 03/08/2019 | 0 | 0 | 0 | 10/16/2019 | 12/16/2019 | 12/30/2019 | Connected |  | N
National Grid | FOXBOROUGH | 178790 | 02035 | 10 | Solar | 05_05_3451W3 | 10/31/2016 | 10/31/2016 | 4 | 4 | 0 | 11/07/2016 | 11/07/2016 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/6/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 259106 | 02035 | 10 | Solar | 05_05_3451W3 | 10/10/2019 | 10/21/2019 | 5 | 0 | 5 | 10/22/2019 | 10/22/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 |  | 10/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2020 | Connected |  | N
National Grid | FOXBOROUGH | 278143 | 02035 | 4107 | Solar | 05_05_3451W3 | 03/05/2020 | 03/18/2020 | 9 | 7 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2020 | 04/10/2020 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2021 | 03/05/2020 | 2/22/2024 | Y | STD | 49 | 09/26/2023 | 01/02/2024 | 99 | 3 | 96 |  |  | 6/26/2024 | Connected |  | N
National Grid | FOXBOROUGH | 290815 | 02035 | 7.6 | Solar | 05_05_3451W3 | 05/06/2020 | 05/11/2020 | 2 | 0 | 2 | 05/12/2020 | 05/12/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2020 |  | 11/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2022 | Connected |  | N
National Grid | HAMPDEN | 313374 | 01036 | 8.64 | Solar | 05_05_3451W3 | 09/17/2020 | 09/18/2020 | 0 | 0 | 0 | 09/21/2020 | 09/21/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/17/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2021 | Connected |  | N
National Grid | HAMPDEN | 329828 | 01036 | 15.2 | Solar | 05_05_3451W3 | 12/05/2020 | 12/08/2020 | 1 | 0 | 1 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 3/31/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 2/23/2022 | Connected |  | Y
National Grid | HAMPDEN | 412928 | 01036 | 11.4 | Solar | 05_05_3451W3 | 02/17/2022 | 02/23/2022 | 3 | 0 | 3 | 02/24/2022 | 02/24/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  | 7/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2023 | Connected |  | N
National Grid | HAMPDEN | 490027 | 01036 | 15.2 | Solar | 05_05_3451W3 | 01/23/2023 | 01/25/2023 | 3 | 2 | 1 | 01/26/2023 | 01/26/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  | 8/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2023 | Connected |  | N
National Grid | HAMPDEN | 588469 | 01036 | 6 | Solar | 05_05_3451W3 | 02/15/2024 | 02/16/2024 | 1 | 0 | 1 | 02/20/2024 | 02/20/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2024 | Connected |  | N
National Grid | HAVERHILL | 664435 | 01830 | 11.5 | Solar | 05_05_3451W3 | 01/09/2025 | 01/16/2025 | 1 | 0 | 1 | 01/17/2025 | 01/17/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 3/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | HAVERHILL | 469559 | 01830 | 22.8 | Solar | 05_07_1W10 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 | 11/29/2022 | 1/25/2024 | Y | EXP | 365 | 03/09/2023 | 05/26/2023 | 79 | 0 | 79 |  |  | 6/13/2023 | Connected |  | N
National Grid | ANDOVER | 662446 | 01845 | 8.45 | Solar | 05_07_1W9 | 12/24/2024 | 02/07/2025 | 4 | 0 | 4 | 02/10/2025 | 02/10/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 752339 | 01845 | 17.6 | Solar | 05_07_1W9 | 03/03/2026 | 03/05/2026 | 2 | 0 | 2 | 03/06/2026 | 03/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BOXFORD | 754311 | 01921 | 7.6 | Solar | 05_07_1W9 | 03/03/2026 | 03/05/2026 | 2 | 0 | 2 | 03/06/2026 | 03/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 321557 | 01845 | 21.46 | Solar | 05_07_1W9 | 10/30/2020 | 11/19/2020 | 12 | 9 | 3 | 11/20/2020 | 11/20/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 1/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 379796 | 01921 | 0 | Solar | 05_07_1W9 | 10/21/2021 | 12/17/2021 | 39 | 30 | 9 | 12/20/2021 | 12/20/2021 | 46 | 22 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 714507 | 01921 | 11.4 | Solar | 05_12_8W1 | 08/26/2025 | 09/16/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOXFORD | 633465 | 01921 | 15.2 | Solar | 05_12_8W1 | 08/26/2024 | 08/29/2024 | 3 | 0 | 3 | 08/30/2024 | 08/30/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 9/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | BOXFORD | 669645 | 01921 | 3.8 | Solar | 05_12_8W1 | 02/03/2025 | 02/27/2025 | 6 | 3 | 3 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 | 02/03/2025 | 4/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | HAVERHILL | 498286 | 01835 | 480 | Solar | 05_05_348W7 | 06/23/2023 | 09/18/2023 | 60 | 50 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/19/2023 | 10/10/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/23/2023 | 9/23/2027 | Y | STD | 651 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HAVERHILL | 497564 | 01835 | 480 | Solar | 05_05_348W7 | 06/23/2023 | 09/18/2023 | 60 | 50 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/19/2023 | 10/10/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/23/2023 | 9/23/2027 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HAVERHILL | 591460 | 01835 | 1000 | Solar | 05_05_348W7 | 07/12/2024 | 08/28/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2024 | 09/04/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | ANDOVER | 673792 | 01845 | 7.6 | Solar | 05_05_348W7 | 02/28/2025 | 03/26/2025 | 18 | 13 | 5 | 03/27/2025 | 03/27/2025 | 118 | 98 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALISBURY | 686212 | 01952 | 500 | Solar | 05_05_348W7 | 05/28/2025 | 09/30/2025 | 85 | 76 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2025 |  | 106 | 25 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALISBURY | 713322 | 01952 | 500 | Solar | 05_05_348W7 | 01/23/2026 |  | 29 | 20 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SALISBURY | 713187 | 01952 | 500 | Solar | 05_05_348W7 | 01/02/2026 |  | 42 | 35 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WARE | 174333 | 01082 | 231 | Solar | 05_05_348W7 | 01/24/2012 | 01/24/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2012 |  | 2/13/2012 | N | EXP | 94 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 9/28/2012 | Connected |  | N
National Grid | WARE | 175213 | 01082 | 266 | Solar | 05_05_348W7 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2014 | 07/31/2014 | 1/30/2015 | Y | EXP | 164 |  |  | 0 | 0 | 0 | 12/5/2014 | 12/5/2014 | 12/15/2014 | Connected |  | N
National Grid | PLAINVILLE | 175503 | 02762 | 490 | Solar | 05_05_348W7 | 10/01/2014 | 10/01/2014 | 3 | 0 | 3 | 10/07/2014 | 10/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 10/01/2014 | 1/30/2015 | Y | EXP | 81 | 03/10/2015 | 03/17/2015 | 5 | 0 | 5 | 2/6/2015 | 2/6/2015 | 3/19/2015 | Connected |  | N
National Grid | PLAINVILLE | 175592 | 02762 | 266 | Solar | 05_05_348W7 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2014 |  | 10/31/2014 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 177561 | 02762 | 10 | Solar | 05_05_348W7 | 07/13/2017 | 07/13/2017 | 11 | 11 | 0 | 07/31/2017 | 07/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2017 | 07/13/2017 | 7/19/2018 | Y | EXP | 352 |  |  | 0 | 0 | 0 | 1/12/2018 | 1/12/2018 | 1/19/2018 | Connected |  | N
National Grid | PLAINVILLE | 177864 | 02762 | 60 | Solar | 05_05_348W7 | 06/14/2017 | 06/14/2017 | 18 | 17 | 1 | 07/11/2017 | 07/11/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2017 |  | 6/19/2018 | N | EXP | 337 |  |  | 0 | 0 | 0 | 9/7/2017 | 9/7/2017 | 9/14/2017 | Connected |  | N
National Grid | PLAINVILLE | 184559 | 02762 | 990 | Solar | 05_05_348W7 | 05/09/2018 | 05/09/2018 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2018 | 07/27/2018 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  | 9/4/2020 | N | STD | 56 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 184555 | 02762 | 990 | Solar | 05_05_348W7 | 05/09/2018 | 05/09/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2018 | 07/27/2018 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  | 9/4/2020 | N | STD | 56 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 185866 | 02762 | 4990 | Solar | 05_05_348W7 | 05/24/2018 | 05/24/2018 | 21 | 17 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2018 | 07/23/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2019 | 05/24/2018 | 12/2/2023 | Y | STD | 547 | 08/12/2022 | 12/16/2022 | 127 | 1 | 126 |  |  | 12/29/2023 | Connected |  | N
National Grid | PLAINVILLE | 202003 | 02762 | 7490 | Solar | 05_05_348W7 | 12/28/2018 | 08/26/2019 | 166 | 26 | 140 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2019 | 10/14/2019 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 246153 | 02762 | 20 | Solar | 05_05_348W7 | 08/05/2019 | 08/09/2019 | 3 | 0 | 3 | 08/12/2019 | 08/12/2019 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 9/16/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | PLAINVILLE | 273152 | 02762 | 27.6 | Solar | 05_05_348W7 | 01/14/2020 | 01/17/2020 | 3 | 3 | 0 | 01/21/2020 | 01/21/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2020 |  | 1/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2020 | Connected |  | N
National Grid | PLAINVILLE | 286629 | 02762 | 7.6 | Solar | 05_05_348W7 | 04/06/2020 | 04/09/2020 | 2 | 0 | 2 | 04/10/2020 | 04/10/2020 | 28 | 16 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 | 04/06/2020 | 4/3/2021 | Y | EXP | 365 | 07/28/2020 | 01/09/2021 | 165 | 5 | 160 |  |  | 1/14/2021 | Connected |  | N
National Grid | PLAINVILLE | 301858 | 02762 | 10 | Solar | 05_05_348W7 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2020 |  | 7/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2020 | Connected |  | N
National Grid | FRANKLIN | 311913 | 02038 | 10 | Solar | 05_05_348W7 | 09/29/2020 | 10/02/2020 | 2 | 0 | 2 | 10/05/2020 | 10/05/2020 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 09/29/2020 | 3/10/2022 | Y | EXP | 365 | 06/09/2021 | 09/10/2021 | 92 | 3 | 89 |  |  | 12/1/2021 | Connected |  | N
National Grid | FRANKLIN | 320922 | 02038 | 499.9 | Solar | 05_05_348W7 | 01/06/2021 | 02/19/2021 | 30 | 23 | 7 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 320921 | 02762 | 499.9 | Solar | 05_05_348W7 | 01/06/2021 | 02/19/2021 | 30 | 23 | 7 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 322917 | 02762 | 10 | Solar | 05_05_348W7 | 11/03/2020 | 11/05/2020 | 1 | 0 | 1 | 11/06/2020 | 11/06/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  | 11/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2021 | Connected |  | N
National Grid | PLAINVILLE | 451936 | 02762 | 9.57 | Solar | 05_05_348W7 | 08/18/2022 | 08/22/2022 | 2 | 0 | 2 | 08/23/2022 | 08/23/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2022 | 08/18/2022 | 1/18/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2023 | Connected |  | N
National Grid | QUINCY | 396718 | 02169 | 996 | Solar | 05_05_348W7 | 01/29/2022 | 03/08/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2022 | 03/09/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 411046 | 02169 | 0 | Other | 05_05_348W7 | 03/30/2022 | 04/13/2022 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/14/2022 | 05/12/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 540635 | 02169 | 10.44 | Solar | 05_05_348W7 | 08/07/2023 | 08/30/2023 | 18 | 17 | 1 | 08/31/2023 | 08/31/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 | 08/07/2023 | 10/17/2024 | Y | EXP | 365 | 11/02/2023 | 11/29/2023 | 28 | 0 | 28 |  |  | 4/26/2024 | Connected |  | N
National Grid | QUINCY | 624449 | 02169 | 13.53 | Solar | 05_05_348W7 | 11/27/2024 | 01/09/2025 | 27 | 25 | 2 | 01/10/2025 | 01/10/2025 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | QUINCY | 634679 | 02169 | 0 | Solar | 05_05_348W7 | 08/23/2024 |  | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 676078 | 02169 | 3.8 | Solar | 05_05_348W7 | 03/06/2025 | 03/18/2025 | 8 | 4 | 4 | 03/19/2025 | 03/19/2025 | 29 | 7 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | EVERETT | 177671 | 02149 | 2000 | Solar | 05_01_2236W3 | 05/25/2017 | 06/02/2017 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2017 | 06/29/2017 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 177885 | 02149 | 4950 | Solar | 05_01_2236W3 | 10/20/2017 | 10/26/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2017 | 11/28/2017 | 16 | 5 | 11 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 59 | 3 | 56 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 285112 | 02149 | 0 | Other | 05_01_2236W3 | 05/06/2020 | 05/12/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2020 | 10/20/2020 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178527 | 02038 | 2800 | Solar | 05_01_2236W5 | 12/04/2017 | 01/12/2018 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/12/2018 | 02/06/2018 | 16 | 1 | 15 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178592 | 02038 | 5000 | Solar | 05_01_2236W5 | 03/14/2018 | 03/15/2018 | 17 | 0 | 17 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 418278 | 02038 | 2000 | Solar | 05_01_2236W2 | 02/17/2023 | 07/13/2023 | 98 | 88 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2023 | 08/07/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BELLINGHAM | 187430 | 02019 | 4998 | Solar | 05_01_2236W2 | 06/11/2018 | 06/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2018 | 07/18/2018 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 255867 | 02038 | 2000 | Solar | 05_01_2236W2 | 11/21/2019 | 11/27/2019 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2019 | 12/09/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178076 | 02038 | 4750 | Solar | 05_01_2236W4 | 11/03/2017 | 12/12/2017 | 24 | 19 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/09/2018 | 18 | 7 | 11 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FRANKLIN | 184672 | 02038 | 2000 | Solar | 05_09_1193W1 | 05/09/2018 | 05/09/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/05/2018 | 08/09/2018 | 49 | 45 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 185368 | 02038 | 4998 | Solar | 05_09_1193W3 | 05/31/2018 | 05/31/2018 | 24 | 21 | 3 |  |  | 69 | 26 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 177541 | 02038 | 4400 | Solar | 05_09_1194T1 | 11/06/2017 | 12/07/2017 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/07/2017 | 02/20/2018 | 49 | 32 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 177540 | 02038 | 4400 | Solar | 05_09_1194T1 | 11/06/2017 | 01/03/2018 | 37 | 36 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/03/2018 | 02/20/2018 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178235 | 02038 | 2500 | Solar | 05_09_1194T1 | 02/19/2018 | 02/28/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2018 | 04/28/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 178579 | 02019 | 2500 | Solar | 05_09_1194T1 | 01/31/2018 | 03/14/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2018 | 04/10/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178610 | 02038 | 4950 | Solar | 05_09_1194T1 | 12/14/2017 | 01/26/2018 | 32 | 3 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/26/2018 | 02/20/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178673 | 02038 | 4990 | Solar | 05_09_1194T1 | 04/10/2018 | 04/16/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 07/05/2018 | 57 | 42 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178368 | 02038 | 4950 | Solar | 05_09_1194T3 | 04/02/2018 | 04/05/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2018 | 05/24/2018 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178367 | 02038 | 1500 | Solar | 05_09_1194T3 | 04/02/2018 | 04/05/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2018 | 05/24/2018 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178399 | 02038 | 4900 | Solar | 05_09_1194T3 | 04/02/2018 | 04/02/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2018 | 05/24/2018 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178398 | 02038 | 5300 | Solar | 05_09_1194T3 | 04/02/2018 | 04/05/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2018 | 05/24/2018 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178405 | 02038 | 4900 | Solar | 05_09_1194T3 | 04/02/2018 | 04/06/2018 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 05/24/2018 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178404 | 02038 | 3400 | Solar | 05_09_1194T3 | 04/02/2018 | 04/06/2018 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 05/24/2018 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178403 | 02038 | 3900 | Solar | 05_09_1194T3 | 04/02/2018 | 04/06/2018 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 05/24/2018 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178402 | 02038 | 2900 | Solar | 05_09_1194T3 | 04/02/2018 | 04/06/2018 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 05/24/2018 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 177999 | 02038 | 2904 | Solar | 05_01_612T2 | 10/25/2017 | 12/12/2017 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/10/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178668 | 02038 | 4990 | Solar | 05_01_612T2 | 03/16/2018 | 03/21/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2018 | 05/31/2018 | 84 | 33 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178115 | 02038 | 4990 | Solar | 05_01_607W7 | 11/06/2017 | 12/12/2017 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/10/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 178114 | 02019 | 4990 | Solar | 05_01_607W7 | 11/06/2017 | 12/12/2017 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/10/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 370269 | 02038 | 2000 | Solar | 05_01_607W6 | 11/12/2021 | 01/21/2022 | 47 | 37 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/24/2022 | 11/21/2022 | 209 | 201 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FRANKLIN | 177539 | 02038 | 4990 | Solar | 05_01_607W6 | 11/06/2017 | 12/12/2017 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/10/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 178112 | 02019 | 4990 | Solar | 05_01_607W6 | 11/06/2017 | 12/12/2017 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/10/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178614 | 02038 | 2000 | Solar | 05_01_607W6 | 12/14/2017 | 01/29/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2018 | 02/20/2018 | 15 | 1 | 14 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/01/2020 | 59 | 3 | 56 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 178540 | 02038 | 4940 | Solar | 05_01_552L2 | 01/26/2018 | 02/28/2018 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2018 | 03/28/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2018 | 01/26/2018 | 12/31/2020 | Y | STD | 833 | 07/11/2020 | 11/25/2020 | 138 | 5 | 133 | 12/4/2020 | 12/8/2020 | 12/30/2020 | Connected |  | N
National Grid | FRANKLIN | 178595 | 02038 | 3000 | Solar | 05_01_552L2 | 03/15/2018 | 03/20/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/20/2018 | 04/12/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2018 | 03/15/2018 | 12/31/2020 | Y | STD | 912 | 07/11/2020 | 11/25/2020 | 138 | 5 | 133 | 12/4/2020 | 12/10/2020 | 12/30/2020 | Connected |  | N
National Grid | SPENCER | 557789 | 01562 | 10 | Solar | 05_01_552L2 | 09/25/2023 | 10/04/2023 | 8 | 4 | 4 | 10/05/2023 | 10/05/2023 | 94 | 76 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 371682 | 01524 | 1000 | Solar | 05_01_552L4 | 10/15/2021 | 01/03/2022 | 53 | 44 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/04/2022 | 08/02/2023 | 394 | 379 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEICESTER | 178171 | 01524 | 4400 | Solar | 05_01_552L4 | 03/23/2018 | 04/18/2018 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/09/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 59 | 3 | 56 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 178568 | 01501 | 6995 | Solar | 05_01_406L5 | 12/07/2017 | 02/07/2018 | 40 | 21 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2018 | 03/07/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 348877 | 01501 | 0 | Other | 05_09_523L3 | 04/26/2021 | 05/09/2021 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2021 | 06/08/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SPENCER | 348875 | 01562 | 0 | Other | 05_09_523L3 | 04/23/2021 | 05/09/2021 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2021 | 06/08/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEICESTER | 178600 | 01524 | 2500 | Solar | 05_01_612W4 | 04/06/2018 | 04/09/2018 | 9 | 9 | 0 |  |  | 55 | 55 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 59 | 3 | 56 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 315366 | 01524 | 0 | Other | 05_01_612W2 | 11/05/2020 | 11/12/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 | 11/30/2020 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 596713 | 01501 | 247 | Solar | 04_04_101L8 | 05/17/2024 | 07/12/2024 | 37 | 31 | 6 | 07/15/2024 | 07/15/2024 | 53 | 33 | 20 | 10/10/2024 | 02/28/2025 | 94 | 2 | 92 |  |  | 0 | 0 | 0 |  | 02/28/2025 | 94 | 2 | 92 |  |  | 0 | 0 | 0 | 3/14/2025 | 05/17/2024 | 4/5/2026 | Y | EXP | 23 | 10/08/2025 | 01/25/2026 | 110 | 0 | 110 |  |  |  | Completion Documents |  | N
National Grid | ATHOL | 714200 | 01331 | 11.5 | Solar | 04_04_101L8 | 08/22/2025 | 09/17/2025 | 17 | 15 | 2 | 09/18/2025 | 09/18/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATHOL | 175824 | 01331 | 25 | Solar | 04_04_101L8 | 08/03/2015 | 08/03/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/9/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OAKHAM | 175853 | 01068 | 25 | Solar | 04_04_101L8 | 08/03/2015 | 08/03/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/8/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OAKHAM | 175856 | 01068 | 25 | Solar | 04_04_101L8 | 08/04/2015 | 08/04/2015 | 1 | 1 | 0 | 08/05/2015 | 08/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2015 |  | 8/9/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 10/1/2015 | 10/1/2015 | 3/25/2016 | Connected |  | N
National Grid | NEW BRAINTREE | 176867 | 01531 | 21.75 | Solar | 04_04_101L8 | 03/01/2016 | 03/01/2016 | 2 | 2 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 |  | 3/6/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 5/23/2016 | 5/23/2016 | 8/8/2016 | Connected |  | N
National Grid | OAKHAM | 177972 | 01068 | 18 | Solar | 04_04_101L8 | 06/26/2017 | 06/26/2017 | 12 | 11 | 1 | 07/14/2017 | 07/14/2017 | 176 | 0 | 176 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2017 |  | 7/2/2018 | N | EXP | 35 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OAKHAM | 202585 | 01068 | 25 | Solar | 04_04_101L8 | 12/13/2018 | 12/21/2018 | 5 | 1 | 4 | 12/24/2018 | 12/24/2018 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 |  | 2/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | OAKHAM | 295382 | 01068 | 249.98 | Solar | 04_04_101L8 | 07/14/2020 | 09/03/2020 | 35 | 27 | 8 | 09/04/2020 | 09/04/2020 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 310959 | 01543 | 7.6 | Solar | 04_04_101L8 | 09/17/2020 | 09/21/2020 | 1 | 1 | 0 | 09/22/2020 | 09/22/2020 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2020 |  | 9/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N
National Grid | RUTLAND | 374111 | 01543 | 20 | Solar | 04_04_101L8 | 08/06/2021 | 08/09/2021 | 1 | 0 | 1 | 08/10/2021 | 08/10/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2022 | Connected |  | N
National Grid | RUTLAND | 434333 | 01543 | 20 | Solar | 04_04_101L8 | 06/02/2022 | 06/08/2022 | 4 | 2 | 2 | 06/09/2022 | 06/09/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2022 |  | 7/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2022 | Connected |  | N
National Grid | RUTLAND | 619120 | 01543 | 50 | Solar | 04_04_101L8 | 06/21/2024 | 07/22/2024 | 21 | 14 | 7 | 07/23/2024 | 07/23/2024 | 27 | 14 | 13 | 10/08/2024 | 10/09/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  | 10/09/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 | 10/11/2024 |  | 10/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | RUTLAND | 649444 | 01543 | 12.5 | Solar | 04_04_101L8 | 10/24/2024 | 10/29/2024 | 2 | 0 | 2 | 10/30/2024 | 10/30/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 12/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2025 | Connected |  | N
National Grid | RUTLAND | 658428 | 01543 | 120 | Solar | 04_04_101L8 | 12/04/2024 | 01/30/2025 | 38 | 29 | 9 | 01/31/2025 | 01/31/2025 | 25 | 0 | 25 | 03/13/2025 | 04/09/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 04/09/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 4/23/2025 |  | 9/24/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 8/25/2025 | Connected |  | N
National Grid | RUTLAND | 661195 | 01543 | 10 | Solar | 04_04_101L8 | 12/17/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2025 | 12/17/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | RUTLAND | 682274 | 01543 | 7.6 | Solar | 04_04_101L8 | 04/04/2025 |  | 21 | 16 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 728879 | 01475 | 10 | Solar | 05_14_20L1 | 10/29/2025 | 11/04/2025 | 4 | 0 | 4 | 11/05/2025 | 11/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 10/29/2025 | 12/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WINCHENDON | 270035 | 01475 | 9.84 | Solar | 05_14_20L1 | 12/17/2019 | 12/17/2019 | 0 | 0 | 0 | 12/18/2019 | 12/18/2019 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2020 |  | 12/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2020 | Connected |  | N
National Grid | GARDNER | 308551 | 01440 | 933.3 | Solar | 05_14_20L1 | 10/22/2020 | 11/02/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2020 | 12/21/2020 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2022 | 10/22/2020 | 2/24/2024 | Y | STD | 393 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 646986 | 01440 | 5.76 | Solar | 05_14_20L1 | 10/29/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/29/2024 | 2/4/2026 | Y | EXP | 365 | 12/19/2024 | 02/11/2025 | 55 | 0 | 55 |  |  | 5/8/2025 | Connected |  | N
National Grid | GARDNER | 648940 | 01440 | 7.6 | Solar | 05_14_20L1 | 11/01/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 718758 | 01440 | 22.8 | Solar | 05_14_20L1 | 09/12/2025 | 10/21/2025 | 3 | 1 | 2 | 10/22/2025 | 10/22/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2026 | Connected |  | N
National Grid | GARDNER | 175829 | 01440 | 7.6 | Solar | 05_01_607W5 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 |  | 9/27/2016 | N | EXP | 354 |  |  | 0 | 0 | 0 | 5/12/2016 | 5/12/2016 | 5/16/2016 | Connected |  | N
National Grid | GARDNER | 176104 | 01440 | 10 | Solar | 05_01_607W5 | 06/19/2015 | 06/19/2015 | 5 | 5 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 6/28/2016 | N | EXP | 334 |  |  | 0 | 0 | 0 | 7/30/2015 | 7/30/2015 | 3/1/2016 | Connected |  | N
National Grid | SPENCER | 176605 | 01562 | 10 | Solar | 05_01_607W5 | 12/30/2015 | 12/30/2015 | 0 | 0 | 0 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2016 | 12/30/2015 | 1/5/2017 | Y | EXP | 246 | 10/04/2016 | 10/11/2016 | 4 | 0 | 4 | 3/21/2017 | 3/21/2017 | 3/21/2017 | Connected |  | N
National Grid | SPENCER | 176746 | 01562 | 10 | Solar | 05_01_607W5 | 11/02/2015 | 11/02/2015 | 3 | 3 | 0 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 | 11/02/2015 | 11/8/2016 | Y | EXP | 349 | 06/06/2016 | 06/21/2016 | 10 | 0 | 10 | 11/25/2015 | 11/25/2015 | 9/28/2016 | Connected |  | N
National Grid | SPENCER | 177089 | 01562 | 4950 | Solar | 05_01_607W5 | 01/17/2017 | 01/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/10/2017 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 | 01/17/2017 | 4/22/2019 | Y | STD | 7 | 09/26/2018 | 06/11/2019 | 257 | 0 | 257 | 8/1/2019 | 10/21/2019 | 10/29/2019 | Connected |  | N
National Grid | SPENCER | 177159 | 01562 | 10 | Solar | 05_01_607W5 | 10/27/2016 | 10/27/2016 | 2 | 2 | 0 | 11/01/2016 | 11/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2016 | 10/27/2016 | 3/2/2018 | Y | EXP | 484 | 07/17/2017 | 08/29/2017 | 31 | 0 | 31 | 1/25/2018 | 1/25/2018 | 1/25/2018 | Connected |  | N
National Grid | SPENCER | 177501 | 01562 | 9 | Solar | 05_01_607W5 | 03/03/2017 | 03/03/2017 | 4 | 3 | 1 | 03/10/2017 | 03/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2017 | 03/03/2017 | 3/11/2018 | Y | EXP | 356 | 05/01/2017 | 07/10/2017 | 48 | 0 | 48 | 7/25/2017 | 7/25/2017 | 7/24/2017 | Connected |  | N
National Grid | OXFORD | 177593 | 01540 | 4990 | Solar | 05_01_607W5 | 05/22/2017 | 06/15/2017 | 16 | 15 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/15/2017 | 07/24/2017 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2018 | 05/22/2017 | 12/31/2020 | Y | STD | 825 | 07/11/2020 | 12/01/2020 | 173 | 5 | 168 |  |  | 12/31/2020 | Connected |  | N
National Grid | PALMER | 178796 | 01069 | 2500 | Solar | 05_01_607W5 | 03/30/2017 | 04/07/2017 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2017 | 05/08/2017 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2017 | 03/30/2017 | 7/30/2019 | Y | STD | 66 | 09/26/2018 | 07/15/2019 | 291 | 0 | 291 | 8/1/2019 | 8/20/2019 | 9/19/2019 | Connected |  | N
National Grid | PALMER | 195106 | 01069 | 10 | Solar | 05_01_607W5 | 09/05/2018 | 12/31/2018 | 20 | 13 | 7 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2019 | 09/05/2018 | 12/31/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2020 | Connected |  | N
National Grid | WINCHENDON | 195930 | 01475 | 7.6 | Solar | 05_01_607W5 | 09/13/2018 | 09/18/2018 | 3 | 3 | 0 | 09/19/2018 | 09/19/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2018 | 09/13/2018 | 1/6/2022 | Y | EXP | 365 | 07/24/2021 | 09/01/2021 | 38 | 3 | 35 |  |  | 9/1/2021 | Connected |  | N
National Grid | WINCHENDON | 247451 | 01475 | 6.24 | Solar | 05_01_607W5 | 09/13/2019 | 10/22/2019 | 26 | 23 | 3 | 10/23/2019 | 10/23/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 | 09/13/2019 | 2/5/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2021 | Connected |  | N
National Grid | NANTUCKET | 250818 | 02554 | 0 | Solar | 05_01_607W5 | 09/04/2019 | 09/10/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 | 09/04/2019 | 5/15/2023 | Y | STD |  | 01/28/2022 | 01/23/2023 | 359 | 0 | 359 |  |  | 5/4/2023 | Connected |  | N
National Grid | NANTUCKET | 251773 | 02564 | 12.76 | Solar | 05_01_607W5 | 09/04/2019 | 09/06/2019 | 1 | 0 | 1 | 09/09/2019 | 09/09/2019 | 13 | 8 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2019 | 09/04/2019 | 9/4/2020 | Y | EXP | 365 | 02/05/2020 | 02/21/2020 | 16 | 0 | 16 |  |  | 3/12/2020 | Connected |  | N
National Grid | NANTUCKET | 268678 | 02554 | 5 | Solar | 05_01_607W5 | 03/10/2020 | 04/03/2020 | 18 | 18 | 0 | 04/06/2020 | 04/06/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 | 03/10/2020 | 4/2/2021 | Y | EXP | 365 | 09/03/2020 | 09/29/2020 | 26 | 0 | 26 |  |  | 12/8/2020 | Connected |  | N
National Grid | NANTUCKET | 312149 | 02554 | 7.6 | Solar | 05_01_607W5 | 10/14/2020 | 10/20/2020 | 3 | 0 | 3 | 10/21/2020 | 10/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 320803 | 02554 | 3.8 | Solar | 05_01_607W5 | 11/06/2020 | 11/12/2020 | 2 | 0 | 2 | 11/13/2020 | 11/13/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 5/26/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2021 | Connected |  | N
National Grid | NANTUCKET | 347438 | 02554 | 7.6 | Solar | 05_01_607W5 | 04/20/2021 | 04/22/2021 | 1 | 0 | 1 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 4/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2021 | Connected |  | N
National Grid | NANTUCKET | 373636 | 02554 | 3 | Solar | 05_01_607W5 | 08/09/2021 | 08/12/2021 | 3 | 0 | 3 | 08/13/2021 | 08/13/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 |  | 9/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2021 | Connected |  | Y
National Grid | NANTUCKET | 410542 | 02554 | 7.6 | Solar | 05_01_607W5 | 02/11/2022 | 02/16/2022 | 3 | 0 | 3 | 02/17/2022 | 02/17/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 | 02/11/2022 | 6/7/2023 | Y | EXP | 365 | 05/18/2022 | 05/24/2022 | 7 | 0 | 7 |  |  | 7/8/2022 | Connected |  | N
National Grid | NANTUCKET | 438200 | 02554 | 7.25 | Solar | 05_01_607W5 | 06/26/2022 | 07/06/2022 | 8 | 6 | 2 | 07/07/2022 | 07/07/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 06/26/2022 | 2/18/2024 | Y | EXP | 365 | 02/07/2023 | 02/16/2023 | 10 | 0 | 10 |  |  | 3/6/2023 | Connected |  | N
National Grid | NANTUCKET | 467785 | 02564 | 8.7 | Solar | 05_01_607W5 | 11/18/2022 | 12/13/2022 | 17 | 15 | 2 | 12/14/2022 | 12/14/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2023 |  | 4/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2023 | Connected |  | N
National Grid | NANTUCKET | 522487 | 02554 | 4.06 | Solar | 05_01_607W5 | 05/26/2023 | 05/30/2023 | 1 | 0 | 1 | 05/31/2023 | 05/31/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 551596 | 02564 | 4.93 | Solar | 05_01_607W5 | 09/05/2023 | 11/27/2023 | 56 | 56 | 0 | 11/28/2023 | 11/28/2023 | 86 | 29 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 567040 | 02554 | 10 | Solar | 05_01_607W5 | 11/15/2023 | 11/17/2023 | 2 | 0 | 2 | 11/20/2023 | 11/20/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 | 11/15/2023 | 1/28/2025 | Y | EXP | 365 | 03/08/2024 | 03/07/2024 | 0 | 0 | 0 |  |  | 3/30/2024 | Connected |  | N
National Grid | NANTUCKET | 570537 | 02564 | 21.4 | Solar | 05_01_607W5 | 11/10/2023 |  | 86 | 52 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 570460 | 02554 | 0 | Solar | 05_01_607W5 | 11/10/2023 | 11/30/2023 | 14 | 12 | 2 | 12/01/2023 | 12/01/2023 | 33 | 10 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2024 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2024 | Connected |  | N
National Grid | NANTUCKET | 575195 | 02554 | 5 | Solar | 05_01_607W5 | 12/14/2023 | 12/20/2023 | 4 | 2 | 2 | 12/21/2023 | 12/21/2023 | 65 | 41 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 597945 | 02564 | 20 | Solar | 05_01_607W5 | 04/11/2024 | 04/17/2024 | 3 | 0 | 3 | 04/18/2024 | 04/18/2024 | 13 | 9 | 4 | 06/06/2024 | 07/09/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  | 07/09/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 7/12/2025 | N | EXP | 365 | 08/21/2024 | 08/22/2024 | 2 | 0 | 2 |  |  | 9/10/2024 | Connected |  | N
National Grid | TEWKSBURY | 609902 | 01876 | 7.6 | Solar | 05_01_607W5 | 05/09/2024 | 05/16/2024 | 2 | 0 | 2 | 05/17/2024 | 05/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/09/2024 | 6/5/2025 | Y | EXP | 365 | 09/06/2024 | 09/16/2024 | 11 | 0 | 11 |  |  | 10/11/2024 | Connected |  | N
National Grid | TEWKSBURY | 663672 | 01876 | 5.76 | Solar | 05_01_607W5 | 01/03/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 | 01/03/2025 | 3/14/2026 | Y | EXP | 365 | 05/24/2025 | 11/21/2025 | 182 | 0 | 182 |  |  | 11/26/2025 | Connected |  | N
National Grid | TEWKSBURY | 586964 | 01876 | 0 | Other | 05_01_328W2 | 02/05/2024 | 12/18/2024 | 216 | 207 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | TEWKSBURY | 735691 | 01876 | 10 | Solar | 05_01_328W2 | 11/21/2025 | 12/03/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 | 11/21/2025 | 1/27/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | TEWKSBURY | 747565 | 01876 | 7.6 | Solar | 05_01_328W2 | 01/26/2026 | 01/27/2026 | 1 | 0 | 1 | 01/28/2026 | 01/28/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | TEWKSBURY | 174827 | 01876 | 250 | Solar | 05_01_328W2 | 08/22/2011 | 08/22/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2011 | 08/22/2011 | 1/3/2012 | Y | EXP | 71 | 12/14/2011 | 12/22/2011 | 6 | 0 | 6 | 8/8/2012 | 8/8/2012 | 1/3/2012 | Connected |  | N
National Grid | GARDNER | 175739 | 01440 | 100 | Solar | 05_01_328W2 | 08/14/2014 | 08/14/2014 | 7 | 1 | 6 | 08/26/2014 | 08/26/2014 | 118 | 32 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2015 |  | 12/31/2014 | N | EXP | 14 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 175953 | 01440 | 20.21 | Solar | 05_01_328W2 | 03/19/2015 | 03/19/2015 | 3 | 0 | 3 | 03/25/2015 | 03/25/2015 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2015 |  | 7/31/2015 | N | EXP | 113 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 176141 | 01440 | 11.4 | Solar | 05_01_328W2 | 06/26/2015 | 06/26/2015 | 0 | 0 | 0 | 07/01/2015 | 07/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 | 06/26/2015 | 7/6/2016 | Y | EXP | 355 | 06/07/2016 | 06/23/2016 | 11 | 0 | 11 | 5/11/2016 | 5/11/2016 | 7/1/2016 | Connected |  | N
National Grid | GARDNER | 176233 | 01440 | 100 | Solar | 05_01_328W2 | 02/14/2015 | 02/14/2015 | 4 | 0 | 4 | 02/23/2015 | 02/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2015 | 02/14/2015 | 12/31/2016 | Y | EXP | 662 | 11/05/2015 | 03/04/2016 | 80 | 0 | 80 | 4/4/2016 | 4/4/2016 | 4/4/2016 | Connected |  | N
National Grid | WINCHENDON | 193597 | 01475 | 3.8 | Solar | 05_01_328W2 | 08/15/2018 | 09/10/2018 | 7 | 7 | 0 | 09/10/2018 | 09/10/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 193486 | 01440 | 3.8 | Solar | 05_01_328W2 | 08/14/2018 | 09/12/2018 | 13 | 2 | 11 | 09/13/2018 | 09/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 280278 | 01440 | 10 | Solar | 05_01_328W2 | 02/20/2020 | 02/21/2020 | 0 | 0 | 0 | 02/24/2020 | 02/24/2020 | 25 | 17 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2020 |  | 2/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2020 | Connected |  | N
National Grid | GARDNER | 322909 | 01440 | 3.8 | Solar | 05_01_328W2 | 11/12/2020 | 11/20/2020 | 5 | 2 | 3 | 11/23/2020 | 11/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/12/2020 | 11/19/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2021 | Connected |  | N
National Grid | GARDNER | 366738 | 01440 | 7.44 | Solar | 05_01_328W2 | 07/07/2021 | 08/02/2021 | 19 | 18 | 1 | 08/03/2021 | 08/03/2021 | 56 | 31 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 |  | 11/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 380180 | 01440 | 15.2 | Solar | 05_01_328W2 | 09/06/2021 | 09/30/2021 | 19 | 18 | 1 | 10/01/2021 | 10/01/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2021 |  | 9/29/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 417754 | 01440 | 7.6 | Solar | 05_01_328W2 | 04/06/2022 | 05/05/2022 | 20 | 17 | 3 | 05/06/2022 | 05/06/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2022 | 04/06/2022 | 9/21/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2022 | Connected |  | N
National Grid | GARDNER | 561102 | 01440 | 15.2 | Solar | 05_01_328W2 | 10/06/2023 | 10/09/2023 | 0 | 0 | 0 | 10/10/2023 | 10/10/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2023 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2024 | Connected |  | N
National Grid | WINCHENDON | 567264 | 01475 | 11.6 | Solar | 05_01_328W2 | 11/20/2023 | 11/22/2023 | 3 | 2 | 1 | 11/24/2023 | 11/24/2023 | 71 | 38 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 646137 | 01440 | 3.8 | Solar | 05_01_328W2 | 10/22/2024 | 11/12/2024 | 2 | 0 | 2 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 1/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | WINCHENDON | 651870 | 01475 | 7.6 | Solar | 05_01_328W2 | 11/13/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/13/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | GARDNER | 660218 | 01440 | 2.03 | Solar | 05_01_328W2 | 12/16/2024 | 01/02/2025 | 4 | 2 | 2 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2025 | Connected |  | N
National Grid | GARDNER | 613726 | 01440 | 499 | Solar | 05_01_328W3 | 07/11/2024 | 08/23/2024 | 31 | 22 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/26/2024 | 09/17/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | GARDNER | 658673 | 01440 | 498 | Solar | 05_01_328W3 | 02/04/2025 | 03/04/2025 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/05/2025 | 04/01/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | GARDNER | 724927 | 01440 | 15.007 | Solar | 05_01_328W3 | 10/08/2025 | 10/15/2025 | 2 | 0 | 2 | 10/29/2025 | 10/29/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GARDNER | 746199 | 01440 | 17.6 | Solar | 05_01_328W3 | 01/29/2026 | 02/02/2026 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GARDNER | 174845 | 01440 | 2000 | Solar | 05_01_328W3 | 01/29/2013 | 01/29/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2013 | 04/01/2013 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2013 | 01/29/2013 | 8/1/2017 | Y | STD | 1331 |  |  | 0 | 0 | 0 | 7/12/2017 | 7/12/2017 | 7/31/2017 | Connected |  | N
National Grid | WINCHENDON | 176126 | 01475 | 15 | Solar | 05_01_328W3 | 02/03/2015 | 02/03/2015 | 5 | 2 | 3 | 02/11/2015 | 02/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2015 |  | 7/31/2015 | N | EXP | 169 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 6/3/2015 | Connected |  | N
National Grid | GARDNER | 177574 | 01440 | 120.75 | Solar | 05_01_328W3 | 09/18/2017 | 09/18/2017 | 36 | 29 | 7 | 11/17/2017 | 11/17/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 9/24/2018 | N | EXP | 31 |  |  | 0 | 0 | 0 |  |  | 9/11/2018 | Connected |  | N
National Grid | GARDNER | 178558 | 01440 | 9.92 | Solar | 05_01_328W3 | 04/05/2018 | 04/05/2018 | 4 | 4 | 0 | 04/12/2018 | 04/12/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 4/11/2019 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 8/2/2018 | Connected |  | N
National Grid | WINCHENDON | 178730 | 01475 | 11.4 | Solar | 05_01_328W3 | 02/09/2018 | 02/09/2018 | 38 | 24 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/14/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 191356 | 01440 | 250 | Solar | 05_01_328W3 | 07/20/2018 | 07/26/2018 | 2 | 0 | 2 | 07/27/2018 | 07/27/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  | 3/19/2020 | N | EXP | 419 |  |  | 0 | 0 | 0 |  |  | 3/20/2020 | Connected |  | N
National Grid | GARDNER | 205004 | 01440 | 0 | Solar | 05_01_328W3 | 01/03/2019 | 01/15/2019 | 7 | 0 | 7 | 01/16/2019 | 01/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 01/03/2019 | 12/18/2020 | Y | EXP | 365 | 01/07/2020 | 02/28/2020 | 52 | 0 | 52 |  |  | 11/16/2020 | Connected |  | N
National Grid | GARDNER | 330733 | 01440 | 10 | Solar | 05_01_328W3 | 12/09/2020 | 12/17/2020 | 5 | 0 | 5 | 12/18/2020 | 12/18/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 |  | 12/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2021 | Connected |  | N
National Grid | GARDNER | 374462 | 01440 | 10 | Solar | 05_01_328W3 | 08/23/2021 | 12/14/2021 | 5 | 2 | 3 | 09/01/2021 | 09/01/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 377991 | 01475 | 0 | Solar | 05_01_328W3 | 08/25/2021 | 10/04/2021 | 27 | 26 | 1 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  | 5/22/2024 | N | EXP | 858 |  |  | 0 | 0 | 0 |  |  | 5/20/2024 | Connected |  | N
National Grid | GARDNER | 454266 | 01440 | 11.866 | Solar | 05_01_328W3 | 09/09/2022 | 09/13/2022 | 2 | 0 | 2 | 09/14/2022 | 09/14/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 | 09/09/2022 | 2/15/2024 | Y | EXP | 365 | 02/16/2023 | 07/28/2023 | 163 | 0 | 163 |  |  | 7/20/2023 | Connected |  | N
National Grid | GRAFTON | 469374 | 01536 | 17.69 | Solar | 05_01_328W3 | 11/15/2022 | 01/23/2023 | 44 | 34 | 10 | 01/24/2023 | 01/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 |  | 3/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2023 | Connected |  | N
National Grid | MILLBURY | 470975 | 01527 | 20.352 | Solar | 05_01_328W3 | 10/28/2022 | 11/03/2022 | 5 | 4 | 1 | 11/04/2022 | 11/04/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  | 1/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2023 | Connected |  | N
National Grid | MILLBURY | 486978 | 01527 | 16.82 | Solar | 05_01_328W3 | 01/03/2023 | 01/04/2023 | 1 | 0 | 1 | 01/05/2023 | 01/05/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2023 |  | 2/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2023 | Connected |  | N
National Grid | GRAFTON | 601604 | 01519 | 1992 | Solar | 05_01_328W3 | 06/03/2024 | 07/30/2024 | 39 | 31 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2024 | 08/07/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 623420 | 01527 | 10 | Solar | 05_01_328W3 | 08/05/2024 | 08/27/2024 | 16 | 12 | 4 | 08/28/2024 | 08/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 |  | 9/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2024 | Connected |  | N
National Grid | GRAFTON | 647346 | 01536 | 5.76 | Solar | 05_01_328W3 | 10/16/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 649690 | 01536 | 6.84 | Solar | 05_01_328W3 | 10/31/2024 | 11/14/2024 | 2 | 0 | 2 | 11/15/2024 | 11/15/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  | 12/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2025 | Connected |  | N
National Grid | MILLBURY | 696776 | 01527 | 5.76 | Solar | 05_01_328W3 | 06/06/2025 | 07/25/2025 | 29 | 24 | 5 | 07/28/2025 | 07/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | GRAFTON | 699671 | 01536 | 0 | Battery Add-On | 05_01_328W3 | 06/19/2025 | 07/25/2025 | 24 | 21 | 3 | 07/28/2025 | 07/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2025 | Connected |  | N
National Grid | GRAFTON | 726244 | 01536 | 17.799 | Solar | 05_01_328W3 | 10/14/2025 | 10/20/2025 | 4 | 0 | 4 | 10/21/2025 | 10/21/2025 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | MILLBURY | 175027 | 01527 | 1000 | Solar | 05_01_328W1 | 03/20/2013 | 03/20/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2013 | 05/15/2013 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2014 | 03/20/2013 | 2/16/2016 | Y | STD | 699 | 06/24/2016 | 01/06/2017 | 133 | 0 | 133 |  |  | 2/10/2017 | Connected |  | N
National Grid | GRAFTON | 175537 | 01536 | 499 | Solar | 05_01_328W1 | 10/09/2014 | 10/09/2014 | 1 | 1 | 0 | 10/14/2014 | 10/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2015 | 10/09/2014 | 1/15/2016 | Y | EXP | 366 | 04/08/2017 | 04/13/2017 | 3 | 0 | 3 | 3/27/2015 | 3/27/2015 | 8/23/2017 | Connected |  | N
National Grid | MILLBURY | 205913 | 01527 | 1380 | Natural Gas | 05_01_328W1 | 10/04/2019 | 10/25/2019 | 14 | 9 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2019 | 04/29/2021 | 376 | 122 | 254 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 669010 | 01527 | 15.2 | Solar | 05_01_328W1 | 01/30/2025 | 02/05/2025 | 4 | 0 | 4 | 02/06/2025 | 02/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | MILLBURY | 702825 | 01527 | 15.2 | Solar | 05_01_328W1 | 07/03/2025 | 07/08/2025 | 2 | 0 | 2 | 07/09/2025 | 07/09/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2025 | Connected |  | N
National Grid | GRAFTON | 175154 | 01536 | 50 | Solar | 05_01_413L8 | 11/05/2013 | 11/05/2013 | 5 | 0 | 5 | 11/13/2013 | 11/13/2013 | 681 | 0 | 681 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2014 |  | 12/31/2016 | N | EXP | 14 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 177747 | 01536 | 2500 | Solar | 05_01_413L8 | 05/26/2017 | 06/09/2017 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2017 | 07/07/2017 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2018 | 05/26/2017 | 12/31/2020 | Y | STD | 1174 | 07/15/2020 | 12/02/2020 | 141 | 5 | 136 | 12/14/2020 | 12/22/2020 | 12/30/2020 | Connected |  | N
National Grid | GRAFTON | 177858 | 01536 | 2000 | Solar | 05_01_413L8 | 06/09/2017 | 06/21/2017 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/21/2017 | 07/12/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2018 | 06/09/2017 | 12/31/2020 | Y | STD | 1174 | 03/17/2020 | 12/02/2020 | 261 | 5 | 256 | 12/11/2020 | 12/22/2020 | 12/30/2020 | Connected |  | N
National Grid | MILLBURY | 178615 | 01527 | 2800 | Solar | 05_01_413L8 | 01/31/2018 | 03/15/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/15/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 | 01/31/2018 | 12/31/2020 | Y | STD | 1114 | 04/03/2020 | 12/02/2020 | 244 | 5 | 239 | 12/3/2020 | 12/15/2020 | 12/30/2020 | Connected |  | N
National Grid | GRAFTON | 178653 | 01536 | 4300 | Solar | 05_01_413L8 | 02/02/2018 | 03/15/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/15/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 | 02/02/2018 | 12/31/2020 | Y | STD | 1117 | 03/17/2020 | 12/02/2020 | 261 | 5 | 256 | 12/3/2020 | 12/14/2020 | 12/24/2020 | Connected |  | N
National Grid | GRAFTON | 282511 | 01519 | 0 | Other | 05_01_413L8 | 05/06/2020 | 05/12/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/13/2020 | 06/26/2020 | 32 | 1 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 05/06/2020 |  | Y | STD | 77 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 325163 | 01536 | 0 | Other | 05_01_413L8 | 12/04/2020 | 01/05/2021 | 20 | 13 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2021 | 02/08/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 12/04/2020 | 4/9/2025 | Y | STD | 77 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 177573 | 01536 | 8800 | Solar | 05_09_604W5 | 09/18/2017 | 10/13/2017 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2017 | 11/14/2017 | 16 | 5 | 11 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GRAFTON | 316407 | 01536 | 0 | Other | 05_09_604W5 | 11/05/2020 | 12/10/2020 | 23 | 20 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2020 | 01/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 609336 | 01536 | 7.6 | Solar | 05_07_12W5 | 05/08/2024 | 05/24/2024 | 1 | 0 | 1 | 05/28/2024 | 05/28/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 |  | 6/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 645029 | 01519 | 5.76 | Solar | 05_07_12W5 | 10/04/2024 | 11/06/2024 | 5 | 0 | 5 | 11/07/2024 | 11/07/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 | 10/04/2024 | 1/19/2026 | Y | EXP | 365 | 02/26/2025 | 03/21/2025 | 24 | 0 | 24 |  |  | 4/30/2025 | Connected |  | N
National Grid | GRAFTON | 646888 | 01519 | 7.6 | Solar | 05_07_12W5 | 10/29/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2025 | Connected |  | N
National Grid | GRAFTON | 178100 | 01536 | 240 | Solar | 05_07_12W6 | 09/05/2017 | 09/05/2017 | 45 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/13/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2018 | 09/05/2017 | 4/15/2021 | Y | STD | 598 | 09/29/2020 | 03/24/2021 | 175 | 0 | 175 |  |  | 4/15/2021 | Connected |  | N
National Grid | GRAFTON | 520939 | 01536 | 67.3 | Solar | 05_07_12W6 | 04/24/2023 | 06/12/2023 | 34 | 26 | 8 | 06/13/2023 | 06/13/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 593497 | 01519 | 155 | Natural Gas | 05_07_12W6 | 05/01/2024 | 07/02/2024 | 42 | 33 | 9 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2025 |  | 11/18/2025 | N | STD | 49 |  |  | 0 | 0 | 0 |  |  | 9/30/2025 | Connected |  | N
National Grid | GRAFTON | 621436 | 01536 | 0 | Other | 05_07_12W6 | 08/01/2024 | 10/31/2024 | 63 | 53 | 10 | 11/01/2024 | 11/01/2024 | 25 | 0 | 25 | 01/30/2025 | 04/03/2025 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  | 04/03/2025 | 45 | 25 | 20 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 8/18/2025 | N | EXP | 147 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | GRAFTON | 629807 | 01536 | 7.22 | Solar | 05_07_12W6 | 08/02/2024 | 08/15/2024 | 3 | 0 | 3 | 08/16/2024 | 08/16/2024 | 7 | 0 | 7 | 10/01/2024 | 11/14/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  | 11/14/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 11/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 329621 | 01519 | 0 | Other | 05_05_320W4 | 04/13/2021 | 04/29/2021 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2021 | 05/28/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 04/13/2021 | 9/29/2026 | Y | STD | 35 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | GRAFTON | 654689 | 01536 | 10 | Solar | 05_05_320W4 | 11/20/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 | 11/20/2024 | 3/13/2026 | Y | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | GRAFTON | 739364 | 01519 | 10 | Solar | 05_05_320W4 | 12/10/2025 | 01/12/2026 | 2 | 0 | 2 | 01/21/2026 | 01/21/2026 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  | 3/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GRAFTON | 174183 | 01536 | 3000 | Solar | 05_05_320W4 | 03/13/2012 | 03/13/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2012 | 05/24/2012 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2013 | 03/13/2012 | 8/1/2012 | Y | STD | 163 | 07/03/2013 | 09/27/2013 | 60 | 0 | 60 | 10/4/2013 | 10/4/2013 | 10/4/2013 | Connected |  | N
National Grid | GRAFTON | 174558 | 01536 | 950 | Solar | 05_05_320W4 | 09/16/2011 | 09/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/16/2011 | 10/31/2012 | Y | STD | 42 | 02/05/2013 | 10/02/2013 | 157 | 0 | 157 | 8/9/2013 | 8/9/2013 | 8/13/2013 | Connected |  | N
National Grid | GRAFTON | 174557 | 01536 | 950 | Solar | 05_05_320W4 | 09/16/2011 | 09/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/16/2011 | 10/31/2012 | Y | STD | 42 | 02/05/2013 | 10/02/2013 | 157 | 0 | 157 | 8/9/2013 | 8/9/2013 | 8/13/2013 | Connected |  | N
National Grid | GRAFTON | 174556 | 01536 | 950 | Solar | 05_05_320W4 | 09/16/2011 | 09/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/16/2011 | 10/31/2012 | Y | STD | 42 | 02/05/2013 | 10/02/2013 | 157 | 0 | 157 | 8/9/2013 | 8/9/2013 | 8/13/2013 | Connected |  | N
National Grid | GRAFTON | 174734 | 01519 | 13.115 | Solar | 05_05_320W4 | 01/08/2013 | 01/08/2013 | 7 | 0 | 7 | 01/18/2013 | 01/18/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2013 |  | 3/29/2013 | N | EXP | 18 |  |  | 0 | 0 | 0 | 5/31/2013 | 5/31/2013 | 6/11/2013 | Connected |  | N
National Grid | GRAFTON | 175564 | 01519 | 16 | Solar | 05_05_320W4 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2014 |  | 10/31/2014 | N | EXP | 74 |  |  | 0 | 0 | 0 | 9/4/2014 | 9/4/2014 | 2/23/2015 | Connected |  | N
National Grid | GRAFTON | 369766 | 01536 | 5 | Solar | 05_05_320W4 | 09/30/2021 | 01/06/2022 | 2 | 0 | 2 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 |  | 4/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2022 | Connected |  | N
National Grid | GRAFTON | 397254 | 01519 | 1500 | Solar | 05_05_320W4 | 03/15/2022 |  | 165 | 157 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 397070 | 01519 | 2500 | Solar | 05_05_320W4 | 03/15/2022 |  | 165 | 157 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 479285 | 01536 | 10 | Solar | 05_05_320W4 | 12/06/2022 | 12/27/2022 | 14 | 12 | 2 | 12/28/2022 | 12/28/2022 | 24 | 2 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2023 | 12/06/2022 | 2/25/2024 | Y | EXP | 365 | 04/04/2023 | 04/26/2023 | 23 | 0 | 23 |  |  | 9/19/2023 | Connected |  | N
National Grid | GRAFTON | 576750 | 01519 | 10 | Solar | 05_05_320W4 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2024 | 12/27/2023 | 2/26/2025 | Y | EXP | 365 | 03/14/2024 | 04/03/2024 | 21 | 0 | 21 |  |  | 5/30/2024 | Connected |  | N
National Grid | MILLBURY | 622100 | 01527 | 6 | Solar | 05_05_320W4 | 07/02/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 12/31/2025 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 664155 | 01519 | 10 | Solar | 05_05_320W4 | 01/07/2025 | 01/15/2025 | 1 | 0 | 1 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 671473 | 01536 | 3.8 | Solar | 05_05_320W4 | 02/11/2025 | 03/18/2025 | 2 | 0 | 2 | 03/19/2025 | 03/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 671325 | 01536 | 10 | Solar | 05_05_320W4 | 02/11/2025 | 02/28/2025 | 2 | 0 | 2 | 04/01/2025 | 04/01/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N
National Grid | RUTLAND | 678976 | 01543 | 24.32 | Solar | 05_05_320W4 | 03/19/2025 | 03/25/2025 | 4 | 1 | 3 | 03/26/2025 | 03/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 687020 | 01550 | 20 | Solar | 05_05_320W4 | 04/23/2025 | 04/29/2025 | 4 | 0 | 4 | 04/30/2025 | 04/30/2025 | 23 | 9 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2025 | 04/23/2025 | 7/15/2026 | Y | EXP | 365 | 07/19/2025 | 09/17/2025 | 61 | 0 | 61 |  |  | 10/29/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 720848 | 01550 | 11.4 | Solar | 05_05_320W4 | 09/24/2025 | 09/30/2025 | 4 | 0 | 4 | 10/01/2025 | 10/01/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 12/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 177373 | 01550 | 57.6 | Solar | 05_14_16L6 | 09/08/2016 | 09/08/2016 | 2 | 2 | 0 | 09/12/2016 | 09/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2016 |  | 9/13/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 1/5/2017 | 1/5/2017 | 1/5/2017 | Connected |  | N
National Grid | SOUTHBRIDGE | 434017 | 01550 | 0 | Battery Add-On | 05_14_16L6 | 07/12/2022 | 08/19/2022 | 28 | 19 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2022 | 09/19/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 639549 | 01550 | 3.8 | Solar | 05_14_16L6 | 09/11/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 09/11/2024 | 1/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 660833 | 01550 | 5.76 | Solar | 05_14_16L6 | 12/16/2024 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARDWICK | 558173 | 01037 | 240 | Solar | 05_14_20L2 | 10/02/2023 | 02/21/2024 | 96 | 87 | 9 | 02/22/2024 | 02/22/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/20/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | HARDWICK | 724308 | 01037 | 23 | Solar | 05_14_20L2 | 10/06/2025 | 10/13/2025 | 4 | 2 | 2 | 10/14/2025 | 10/14/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEYMOUTH | 176340 | 02188 | 268 | Solar | 05_14_20L2 | 09/17/2015 | 09/17/2015 | 3 | 3 | 0 | 09/22/2015 | 09/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2015 |  | 9/22/2016 | N | EXP | 323 |  |  | 0 | 0 | 0 | 11/12/2015 | 11/12/2015 | 1/27/2016 | Connected |  | N
National Grid | WEYMOUTH | 594235 | 02190 | 23 | Solar | 05_14_20L2 | 03/04/2024 | 03/06/2024 | 2 | 0 | 2 | 03/07/2024 | 03/07/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2024 |  | 3/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | WEYMOUTH | 682856 | 02188 | 5.76 | Solar | 05_14_20L2 | 04/04/2025 | 05/02/2025 | 4 | 0 | 4 | 05/20/2025 | 05/20/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 | 04/04/2025 | 7/1/2026 | Y | EXP | 365 | 10/01/2025 | 12/01/2025 | 62 | 0 | 62 |  |  | 12/12/2025 | Connected |  | N
National Grid | WEYMOUTH | 580543 | 02188 | 240 | Solar | 05_14_20L3 | 01/16/2024 | 02/16/2024 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/20/2024 | 03/25/2024 | 25 | 22 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEYMOUTH | 690863 | 02189 | 499 | Other | 05_14_20L3 | 08/29/2025 | 09/17/2025 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WEYMOUTH | 717753 | 02188 | 4995 | Other | 05_14_20L3 | 09/29/2025 | 10/30/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 | 12/01/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WEYMOUTH | 740754 | 02189 | 21.28 | Solar | 05_14_20L3 | 12/17/2025 | 01/30/2026 | 2 | 0 | 2 | 02/02/2026 | 02/02/2026 | 23 | 9 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEYMOUTH | 177217 | 02189 | 72 | Solar | 05_14_20L3 | 08/15/2016 | 08/15/2016 | 1 | 1 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2016 |  | 1/21/2018 | N | EXP | 521 |  |  | 0 | 0 | 0 | 11/28/2017 | 11/28/2017 | 11/28/2017 | Connected |  | N
National Grid | UXBRIDGE | 189667 | 01569 | 249.8 | Solar | 05_14_20L3 | 06/29/2018 | 06/29/2018 | 2 | 0 | 2 | 07/11/2018 | 07/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 7/31/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 8/3/2020 | Connected |  | N
National Grid | UXBRIDGE | 280389 | 01569 | 250 | Solar | 05_14_20L3 | 02/21/2020 | 03/02/2020 | 4 | 0 | 4 | 03/03/2020 | 03/03/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2020 |  | 4/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 651308 | 01569 | 7.6 | Solar | 05_14_20L3 | 11/12/2024 | 12/02/2024 | 2 | 0 | 2 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/12/2024 | 1/22/2026 | Y | EXP | 365 | 07/30/2025 | 10/10/2025 | 73 | 0 | 73 |  |  | 11/6/2025 | Connected |  | N
National Grid | DOUGLAS | 309756 | 01516 | 13.6 | Solar | 05_14_20L4 | 08/31/2020 | 09/02/2020 | 2 | 2 | 0 | 09/03/2020 | 09/03/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2020 | Connected |  | N
National Grid | UXBRIDGE | 174098 | 01569 | 3.8 | Solar | 05_14_20L5 | 04/21/2018 | 04/21/2018 | 1 | 0 | 1 | 05/29/2018 | 05/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 184053 | 01569 | 3.8 | Solar | 05_14_20L5 | 07/15/2018 | 07/18/2018 | 2 | 0 | 2 | 07/19/2018 | 07/19/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 660953 | 01569 | 5.76 | Solar | 05_14_20L5 | 12/16/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 733679 | 01569 |  | Other |  | 11/13/2025 | 11/13/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | UXBRIDGE | 174110 | 01569 | 2000 | Solar |  | 03/27/2012 | 03/27/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2012 | 05/31/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 174109 | 01569 | 1000 | Solar |  | 03/27/2012 | 03/27/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2012 | 05/31/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 174202 | 01516 | 1000 | Solar |  | 02/29/2012 | 02/29/2012 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 174247 | 01569 | 1000 | Solar |  | 02/23/2012 | 02/23/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/6/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 174242 | 01569 | 2500 | Solar |  | 02/21/2012 | 02/21/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 174221 | 01569 | 500 | Solar |  | 02/07/2012 | 02/07/2012 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 174302 | 01569 | 1000 | Solar |  | 11/22/2011 | 11/22/2011 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 174301 | 01569 | 1000 | Solar |  | 11/22/2011 | 11/22/2011 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 174300 | 01569 | 1000 | Solar |  | 11/22/2011 | 11/22/2011 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 05/16/2014 | 12 | 0 | 12 | 5/16/2014 |  | 7/1/2012 | N | STD | 684 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 174320 | 01569 | 1000 | Solar |  | 01/17/2012 | 01/17/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2012 | 05/30/2012 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/25/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 174319 | 01569 | 5000 | Solar |  | 01/17/2012 | 01/17/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2012 | 05/30/2012 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/25/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 174318 | 01516 | 1000 | Solar |  | 01/17/2012 | 01/17/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2012 | 05/30/2012 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/25/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 174317 | 01569 | 1000 | Solar |  | 01/07/2012 | 01/07/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2012 | 05/30/2012 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174316 | 01852 | 2000 | Solar |  | 01/17/2012 | 01/17/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2012 | 05/30/2012 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/25/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174416 | 01852 | 750 | Solar |  | 12/14/2011 | 12/14/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/30/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174433 | 01852 | 2000 | Solar |  | 06/27/2012 | 06/27/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2012 | 10/09/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174432 | 01852 | 2000 | Solar |  | 06/27/2012 | 06/27/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2012 | 10/09/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174429 | 01876 | 2000 | Solar |  | 11/18/2011 | 11/18/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 |  | 10/31/2012 | N | STD | 134 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174419 | 01876 | 1791 | Solar |  | 06/24/2012 | 06/24/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2012 | 08/21/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 04/30/2014 | 09/08/2014 | 89 | 0 | 89 |  |  | 4/20/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174660 | 01876 | 3000 | Solar |  | 12/11/2012 | 12/11/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2012 | 01/29/2013 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174738 | 01876 | 6000 | Solar |  | 08/03/2011 | 08/03/2011 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2011 | 10/26/2011 | 44 | 0 | 44 |  |  | 0 | 0 | 0 | 04/30/2014 | 08/05/2016 | 563 | 0 | 563 | 5/29/2013 | 08/03/2011 | 12/31/2016 | Y | STD | 1312 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174777 | 01876 | 3000 | Solar |  | 01/21/2013 | 01/21/2013 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2013 | 09/08/2014 | 388 | 0 | 388 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174989 | 01852 | 1000 | Solar |  | 09/26/2011 | 09/26/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174988 | 01876 | 1000 | Solar |  | 09/26/2011 | 09/26/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174987 | 01852 | 1000 | Solar |  | 09/26/2011 | 09/26/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174985 | 01852 | 1000 | Solar |  | 11/03/2011 | 11/03/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2011 | 02/16/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2013 |  | 12/31/2012 | N | STD | 23 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174983 | 01876 | 950 | Solar |  | 09/16/2011 | 09/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174982 | 01852 | 950 | Solar |  | 09/16/2011 | 09/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174981 | 01852 | 950 | Solar |  | 09/16/2011 | 09/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/10/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 175017 | 01852 | 1000 | Solar |  | 09/26/2011 | 09/26/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 175131 | 01879 | 4000 | Solar |  | 11/04/2012 | 11/04/2012 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2012 | 01/04/2013 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2013 |  | 12/31/2016 | N | STD | 1226 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 175177 | 01876 | 2000 | Solar |  | 04/29/2013 | 04/29/2013 | 21 | 14 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2013 | 07/12/2013 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/1/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 175404 | 01876 |  |  |  | 11/25/2014 | 11/25/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/17/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 175761 | 01876 | 364 | Solar |  | 05/29/2014 | 05/29/2014 | 57 | 51 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PRINCETON | 175958 | 01541 | 989 | Solar |  | 06/03/2015 | 06/03/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/9/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 176172 | 01069 | 2000 | Solar |  | 04/23/2015 | 04/23/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/28/2015 | 05/27/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/23/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 176579 | 01069 |  |  |  | 02/12/2016 | 02/12/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/17/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LENOX | 176608 | 01240 |  |  |  | 02/12/2016 | 02/12/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/17/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 176964 | 01562 | 10 | Solar |  | 07/19/2016 | 07/19/2016 | 4 | 4 | 0 | 07/25/2016 | 07/25/2016 | 251 | 0 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2016 |  | 7/24/2017 | N | EXP | 35 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 177684 | 01082 | 4990 | Solar |  | 09/29/2017 | 09/29/2017 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2017 | 11/08/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/4/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 177691 | 02072 | 1620 | Solar |  | 10/03/2017 | 10/03/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 | 11/01/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 178742 | 01569 | 990 | Solar |  | 05/16/2018 | 04/19/2018 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/24/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 184488 | 01569 | 66.6 | Solar |  | 05/23/2018 | 05/23/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 184437 | 01569 | 0 | Solar |  | 05/04/2018 | 05/04/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 184659 | 01069 | 5120 | Solar |  | 05/09/2018 | 05/09/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 184647 | 01069 | 990 | Solar |  | 05/10/2018 | 05/10/2018 | 1 | 0 | 1 |  |  | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 184777 | 01069 | 4980 | Solar |  | 05/09/2018 | 05/09/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 184741 | 01069 | 530 | Solar |  | 07/03/2018 | 07/03/2018 | 124 | 25 | 99 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 185024 | 01069 | 499 | Solar |  | 05/16/2018 | 05/16/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 185571 | 01569 | 2000 | Solar |  | 05/17/2018 | 05/17/2018 | 31 | 5 | 26 |  |  | 69 | 21 | 48 |  |  | 0 | 0 | 0 | 09/04/2018 | 10/10/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 185413 | 01543 | 0 | Solar |  | 05/31/2018 | 05/31/2018 | 738 | 37 | 701 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 186387 | 01543 | 250 | Solar |  | 07/19/2018 |  | 703 | 20 | 683 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 186220 | 01524 | 250 | Solar |  | 06/01/2018 | 06/01/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 187511 | 02703 | 15.2 | Solar |  | 06/08/2018 | 06/08/2018 | 4 | 0 | 4 | 06/18/2018 | 06/18/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2018 |  | 6/8/2020 | N | EXP | 6 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 186877 | 01010 | 0 | Solar |  | 05/31/2018 | 05/31/2018 | 739 | 54 | 685 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 186861 | 01515 | 0 | Solar |  | 05/31/2018 | 05/31/2018 | 49 | 49 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 187549 | 01010 | 2500 | Solar |  | 06/10/2018 | 06/10/2018 | 37 | 0 | 37 |  |  | 300 | 0 | 300 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 188842 | 01543 | 2280 | Solar |  | 07/06/2018 | 07/26/2018 | 14 | 13 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2018 | 08/21/2018 | 17 | 16 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 194460 | 01543 | 720 | Solar |  | 01/15/2019 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 196296 | 01543 | 794 | Solar |  | 12/05/2018 | 12/22/2018 | 12 | 3 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 12/24/2018 | 01/25/2019 | 44 | 2 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 449533 | 01452 | 10 | Solar |  | 08/04/2022 | 08/05/2022 | 1 | 0 | 1 | 08/08/2022 | 08/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 669544 | 01331 | 16 | Solar |  | 02/03/2025 | 02/03/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 633062 | 01331 |  | Solar | 05_07_98W46 | 03/20/2012 | 03/20/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/20/2012 |  | Y | STD | 365 | 10/06/2025 | 01/29/2026 | 116 | 0 | 116 |  |  |  | Completion Documents |  | N
National Grid | ATHOL | 352979 | 01331 | 9.8 | Solar | 05_14_78L9 | 04/23/2021 | 05/18/2021 | 0 | 0 | 0 | 05/19/2021 | 05/19/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 04/23/2021 |  | Y | EXP | 365 | 11/05/2021 | 12/03/2021 | 29 | 0 | 29 |  |  | 1/27/2022 | Connected |  | N
National Grid | RUTLAND | 164405 | 01543 | 500 | Solar | 05_14_73L1 | 04/05/2010 | 04/05/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2010 | Connected |  | N
National Grid | SPENCER | 163782 | 01562 | 75 | Natural Gas | 05_05_311W1 | 01/22/2009 | 01/22/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2009 | Connected |  | N
National Grid | BRIMFIELD | 163916 | 01010 | 60 | Natural Gas | 05_14_31J6 | 10/27/2009 | 10/27/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2011 | Connected |  | N
National Grid | WEST BROOKFIELD | 163718 | 01585 | 142 | Solar | 05_14_92L3 | 07/14/2009 | 07/14/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2009 | Connected |  | N
National Grid | SHEFFIELD | 164071 | 01257 | 300 | Natural Gas | 05_01_412L3 | 07/08/2010 | 07/08/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2011 | Connected |  | N
National Grid | AYER | 164331 | 01432 | 82 | Solar | 05_01_24W4 | 03/07/2011 | 03/07/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2011 | Connected |  | N
National Grid | BERLIN | 164174 | 01503 | 120 | Solar | 05_01_24W4 | 08/05/2010 | 08/05/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2010 | Connected |  | N
National Grid | NORTHAMPTON | 163655 | 01062 | 95 | Solar | 05_14_36L2 | 05/07/2009 | 05/07/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2009 | Connected |  | N
National Grid | NORTHAMPTON | 163654 | 01062 | 392 | Solar | 05_14_36L2 | 05/07/2009 | 05/07/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2009 | Connected |  | N
National Grid | GRAFTON | 164306 | 01536 | 0 | Natural Gas | 05_05_311W6 | 03/01/2010 | 03/01/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2010 | Terminated |  | N
National Grid | LANCASTER | 164015 | 01523 | 60 | Solar | 05_01_216W5 | 11/18/2009 | 11/18/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2010 | Connected |  | N
National Grid | FALL RIVER | 163681 | 02720 | 0 | Landfill Gas | 05_01_607W1 | 06/03/2009 | 06/03/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2010 | Terminated |  | N
National Grid | ORANGE | 163813 | 01364 | 52.7 | Solar | 05_14_3L5 | 05/19/2010 | 05/19/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 1/18/2011 | Connected |  | N
National Grid | NORTHAMPTON | 163814 | 01060 | 0 | Solar | 05_01_412L6 | 05/21/2010 | 05/21/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2010 | Terminated |  | N
National Grid | WARREN | 163887 | 01083 | 190 | Solar | 05_05_312W2 | 11/23/2010 | 11/23/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2011 | Connected |  | N
National Grid | BARRE | 163819 | 01005 | 79.8 | Solar | 05_01_607W3 | 05/26/2010 | 05/26/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2010 | Connected |  | N
National Grid | WILLIAMSBURG | 163642 | 01096 | 95 | Solar | 05_01_607W3 | 04/22/2009 | 04/22/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2009 | Connected |  | N
National Grid | WILBRAHAM | 164070 | 01095 | 266 | Solar | 05_05_312W3 | 07/12/2010 | 07/12/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2011 | Connected |  | N
National Grid | AYER | 163641 | 01432 | 3300 | Wind | 05_01_607W3 | 01/14/2010 | 01/14/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2011 | Connected |  | N
National Grid | GOSHEN | 164514 | 01032 | 60 | Solar | 05_05_115W53 | 04/28/2010 | 04/28/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2011 | Connected |  | N
National Grid | WARE | 164529 | 01082 | 148 | Solar | 05_01_27W4 | 11/02/2010 | 11/02/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2011 | Connected |  | N
National Grid | GRAFTON | 165000 | 01560 | 135 | Solar | 05_05_115W55 | 09/01/2011 | 09/01/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2011 | Connected |  | N
National Grid | WEST BROOKFIELD | 164304 | 01585 | 82 | Solar | 05_05_11W81 | 02/26/2010 | 02/26/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2011 | Connected |  | N
National Grid | DUDLEY | 164255 | 01571 | 250 | Solar | 05_01_219W4 | 02/22/2010 | 02/22/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2010 | Connected |  | N
National Grid | BELLINGHAM | 164356 | 02019 | 1600 | Landfill Gas | 05_01_413L4 | 07/01/2011 | 07/01/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2011 | Connected |  | N
National Grid | ATHOL | 164410 | 01331 | 82 | Solar | 05_14_43L8 | 04/12/2010 | 04/12/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2010 | Connected |  | N
National Grid | WINCHENDON | 163698 | 01475 | 1000 | Solar | 05_12_7W4 | 06/12/2009 | 06/12/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2011 | Connected |  | N
National Grid | DOUGLAS | 163986 | 01516 | 100 | Solar | 05_01_21W2 | 12/14/2010 | 12/14/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2011 | Connected |  | N
National Grid | LEICESTER | 163985 | 01524 | 175 | Solar | 05_01_21W2 | 12/14/2010 | 12/14/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2011 | Connected |  | N
National Grid | SAUGUS | 163984 | 01906 | 100 | Solar | 05_01_21W2 | 12/14/2010 | 12/14/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2011 | Connected |  | N
National Grid | NORTHBOROUGH | 164086 | 01532 | 120 | Solar | 05_14_13L1 | 01/04/2011 | 01/04/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2011 | Connected |  | N
National Grid | ROCKPORT | 557102 | 01966 | 6 | Solar | 05_01_6W1 | 01/03/2024 | 09/29/2023 | 0 | 0 | 0 | 02/16/2024 | 02/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2024 | Connected |  | N
National Grid | MALDEN | 163703 | 02149 | 1000 | Solar | 05_14_48L2 | 06/12/2009 | 06/12/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2011 | Connected |  | N
National Grid | PLAINVILLE | 164068 | 02762 | 500 | Solar | 05_05_317W1 | 07/09/2010 | 07/09/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2011 | Connected |  | N
National Grid | HOLBROOK | 163722 | 02343 | 326 | Solar | 05_12_2W2 | 07/14/2009 | 07/14/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2010 | Connected |  | N
National Grid | ABINGTON | 164273 | 02351 | 177 | Solar | 05_01_304W6 | 08/19/2010 | 08/19/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2011 | Connected |  | N
National Grid | NORTH ADAMS | 164348 | 01247 | 75 | Natural Gas | 05_01_4J324 | 08/11/2009 | 08/11/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2010 | Withdrawn |  | N
National Grid | MEDFORD | 164163 | 02155 | 60 | Natural Gas | 05_01_3J373 | 01/27/2010 | 01/27/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2011 | Connected |  | N
National Grid | NORTHBRIDGE | 164572 | 01534 | 100 | Solar | 05_14_77L1 | 05/19/2010 | 05/19/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2010 | Connected |  | N
National Grid | ORANGE | 163818 | 01364 | 95 | Solar | 05_01_525L2 | 05/25/2010 | 05/25/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 163990 | 01028 | 95 | Solar | 05_01_525L2 | 11/22/2010 | 11/22/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2011 | Connected |  | N
National Grid | BROCKTON | 163988 | 02302 | 100 | Solar | 05_14_211L1 | 12/15/2010 | 12/15/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2011 | Connected |  | N
National Grid | CLINTON | 163877 | 01510 | 100 | Solar | 05_14_211L1 | 06/04/2010 | 06/04/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2010 | Connected |  | N
National Grid | FRANKLIN | 164165 | 02038 | 85 | Natural Gas | 05_14_53J3 | 02/04/2010 | 02/04/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2011 | Connected |  | N
National Grid | HOLBROOK | 164166 | 02343 | 150 | Natural Gas | 05_05_318W5 | 07/29/2010 | 07/29/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2011 | Connected |  | N
National Grid | HANSON | 164423 | 02341 | 123 | Solar | 05_05_318W5 | 10/07/2010 | 10/07/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2011 | Connected |  | N
National Grid | NORTH ADAMS | 164182 | 01247 | 500 | Solar | 05_05_320W1 | 01/28/2011 | 01/28/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2011 | Connected |  | N
National Grid | BEVERLY | 164557 | 01915 | 86 | Solar | 05_01_9J310 | 10/01/2009 | 10/01/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2010 | Connected |  | N
National Grid | UXBRIDGE | 163247 | 01525 | 75 | Solar | 05_05_28W40 | 12/08/2009 | 12/08/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2010 | Connected |  | N
National Grid | ORANGE | 163611 | 01364 | 60 | Solar | 05_12_37W7 | 07/16/2009 | 07/16/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2010 | Connected |  | N
National Grid | LONGMEADOW | 163610 | 01028 | 60 | Solar | 05_12_37W7 | 07/16/2009 | 07/16/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2010 | Connected |  | N
National Grid | BROCKTON | 164335 | 02302 | 0 | Solar | 05_12_37W9 | 03/08/2011 | 03/08/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2011 | Terminated |  | N
National Grid | CLINTON | 163917 | 01510 | 82 | Solar | 05_05_28W41 | 10/27/2009 | 10/27/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2010 | Connected |  | N
National Grid | FRANKLIN | 164183 | 02038 | 83 | Solar | 05_14_55L1 | 01/31/2011 | 01/31/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2011 | Connected |  | N
National Grid | HOLBROOK | 164351 | 02343 | 75 | Natural Gas | 05_01_HT20 | 08/11/2009 | 08/11/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2010 | Withdrawn |  | N
National Grid | WHITMAN | 164173 | 02382 | 100 | Solar | 05_05_28W50 | 08/05/2010 | 08/05/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2010 | Connected |  | N
National Grid | NORTH ADAMS | 164999 | 01247 | 75 | Solar | 05_05_28W50 | 09/01/2011 | 09/01/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2011 | Connected |  | N
National Grid | BEVERLY | 164536 | 01915 | 95 | Solar | 05_05_28W50 | 04/27/2011 | 04/27/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/16/2011 | Connected |  | N
National Grid | BLACKSTONE | 164087 | 01504 | 60 | Solar | 05_14_21L2 | 01/04/2011 | 01/04/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2011 | Connected |  | N
National Grid | ATHOL | 164229 | 01331 | 150 | Natural Gas | 05_01_HT39 | 02/02/2011 | 02/02/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2011 | Connected |  | N
National Grid | LONGMEADOW | 164352 | 01028 | 75 | Natural Gas | 05_01_HT41 | 08/11/2009 | 08/11/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2010 | Withdrawn |  | N
National Grid | BROCKTON | 164527 | 02302 | 82 | Solar | 05_01_HT48 | 11/01/2010 | 11/01/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2011 | Connected |  | N
National Grid | CLINTON | 566803 | 01510 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | FOXBOROUGH | 566738 | 02035 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | HOLBROOK | 566786 | 02343 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | WHITMAN | 576553 | 02382 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | NORTH ADAMS | 576270 | 01247 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2024 | Connected |  | N
National Grid | BEVERLY | 576257 | 01915 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | MENDON | 164284 | 01756 | 60 | Solar | 05_05_106W44 | 02/23/2011 | 02/23/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2011 | Connected |  | N
National Grid | ATHOL | 580298 | 01331 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | LONGMEADOW | 580347 | 01028 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | BROCKTON | 580288 | 02302 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | CLINTON | 580284 | 01510 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | REHOBOTH | 580282 | 02769 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | HOLBROOK | 580271 | 02343 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | BROCKTON | 164079 | 02301 | 0 | Solar | 05_01_227W3 | 07/20/2010 | 07/20/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2011 | Connected |  | N
National Grid | LANESBOROUGH | 580262 | 01237 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | WENHAM | 164066 | 01984 | 95 | Solar | 05_01_227W3 | 12/02/2009 | 12/02/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2010 | Connected |  | N
National Grid | UXBRIDGE | 580274 | 01569 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | ATHOL | 164065 | 01331 | 95 | Solar | 05_01_227W3 | 12/02/2009 | 12/02/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2010 | Connected |  | N
National Grid | LONGMEADOW | 580264 | 01028 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | BROCKTON | 164064 | 02302 | 95 | Solar | 05_01_227W3 | 12/02/2009 | 12/02/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2010 | Connected |  | N
National Grid | CLINTON | 580253 | 01510 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | REHOBOTH | 163876 | 02769 | 95 | Solar | 05_01_227W3 | 06/04/2010 | 06/04/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2010 | Connected |  | N
National Grid | WEYMOUTH | 164216 | 02190 | 300 | Bio Gas | 05_01_55W1 | 02/23/2010 | 02/23/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2011 | Connected |  | N
National Grid | BROCKTON | 580245 | 02301 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | CHARLEMONT | 164562 | 01339 | 95 | Solar | 05_01_227W3 | 05/14/2010 | 05/14/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2010 | Connected |  | N
National Grid | WENHAM | 580242 | 01984 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2024 | Connected |  | N
National Grid | UXBRIDGE | 580235 | 01569 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | NEW SALEM | 580229 | 01355 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | LONGMEADOW | 580435 | 01028 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | BROCKTON | 163704 | 02302 | 1000 | Solar | 05_05_320W5 | 06/12/2009 | 06/12/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2010 | Connected |  | N
National Grid | STOUGHTON | 580432 | 02072 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | SEEKONK | 580430 | 02771 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | QUINCY | 580426 | 02169 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | BROCKTON | 580423 | 02301 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | CHARLEMONT | 580410 | 01339 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | WENHAM | 580408 | 01984 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | UXBRIDGE | 580402 | 01569 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | ATHOL | 580393 | 01331 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | LONGMEADOW | 580387 | 01028 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | BROCKTON | 580366 | 02302 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | STOUGHTON | 580361 | 02072 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | NORTON | 580359 | 02766 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | QUINCY | 580358 | 02171 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | BROCKTON | 580349 | 02301 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | CHARLEMONT | 580341 | 01339 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | WENHAM | 580326 | 01984 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | BLACKSTONE | 580320 | 01504 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2024 | Connected |  | N
National Grid | SHUTESBURY | 580300 | 01072 | 25 | Solar | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | LONGMEADOW | 165087 | 01028 | 100 | Solar | 05_05_106W82 | 09/26/2011 | 09/26/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2011 | Connected |  | N
National Grid | BROCKTON | 164998 | 02302 | 200 | Solar | 05_05_106W82 | 09/01/2011 | 09/01/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2011 | Connected |  | N
National Grid | STOUGHTON | 620448 | 02072 | 15.36 | Solar | 05_05_320W5 | 06/25/2024 | 06/26/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2025 | Connected |  | N
National Grid | NORTON | 163398 | 02766 | 95 | Solar | 05_05_2J3 | 10/12/2009 | 10/12/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2010 | Connected |  | N
National Grid | QUINCY | 164457 | 02170 | 60 | Solar | 05_01_23W2 | 04/19/2010 | 04/19/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2011 | Connected |  | N
National Grid | BROCKTON | 164128 | 02301 | 343 | Solar | 05_07_3W3 | 01/07/2011 | 01/07/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2011 | Connected |  | N
National Grid | ADAMS | 164561 | 01220 | 95 | Solar | 05_12_18L1 | 05/11/2010 | 05/11/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2011 | Connected |  | N
National Grid | WENHAM | 164454 | 01984 | 95 | Solar | 05_09_702W3 | 09/17/2009 | 09/17/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2010 | Connected |  | N
National Grid | MENDON | 164453 | 01756 | 95 | Solar | 05_09_702W3 | 09/17/2009 | 09/17/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2010 | Connected |  | N
National Grid | SHUTESBURY | 164088 | 01072 | 82 | Solar | 05_14_2L3 | 01/04/2011 | 01/04/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2011 | Connected |  | N
National Grid | LONGMEADOW | 164403 | 01028 | 95 | Solar | 05_14_58L2 | 09/10/2009 | 09/10/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2010 | Connected |  | N
National Grid | BROCKTON | 163935 | 02302 | 75 | Solar | 05_07_95W1 | 11/29/2010 | 11/29/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2011 | Connected |  | N
National Grid | STOUGHTON | 163699 | 02072 | 900 | Wind | 05_09_1019W1 | 06/17/2009 | 06/17/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2011 | Connected |  | N
National Grid | NORTON | 164000 | 02766 | 225 | Solar | 05_12_19W2 | 06/13/2011 | 06/13/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2011 | Connected |  | N
National Grid | RANDOLPH | 164258 | 02368 | 400 | Solar | 05_05_348W6 | 02/23/2010 | 02/23/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2010 | Connected |  | N
National Grid | BROCKTON | 165127 | 02301 | 100 | Solar | 05_05_349W1 | 12/07/2009 | 12/07/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2010 | Connected |  | N
National Grid | ADAMS | 164369 | 01220 | 95 | Solar | 05_14_59L1 | 09/21/2010 | 09/21/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2011 | Connected |  | N
National Grid | HAMILTON | 165126 | 01982 | 75 | Solar | 05_05_349W1 | 12/07/2009 | 12/07/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2010 | Connected |  | N
National Grid | UXBRIDGE | 164368 | 01569 | 82 | Solar | 05_14_59L1 | 09/22/2010 | 09/22/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2011 | Connected |  | N
National Grid | SHUTESBURY | 165124 | 01072 | 75 | Solar | 05_05_349W1 | 12/07/2009 | 12/07/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2010 | Connected |  | N
National Grid | LONGMEADOW | 165123 | 01028 | 100 | Solar | 05_05_349W1 | 12/07/2009 | 12/07/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2010 | Connected |  | N
National Grid | BROCKTON | 164515 | 02302 | 142 | Solar | 05_09_705W3 | 05/05/2010 | 05/05/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2011 | Connected |  | N
National Grid | GRAFTON | 164105 | 01519 | 57 | Solar | 05_09_1021W2 | 12/07/2009 | 12/07/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2010 | Connected |  | N
National Grid | NORTON | 165169 | 02766 | 0 | Solar | 05_07_912W55 | 06/18/2009 | 06/18/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2010 | Connected |  | N
National Grid | RANDOLPH | 163794 | 02368 | 225 | Solar | 05_09_509L1 | 05/17/2011 | 05/17/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2011 | Connected |  | N
National Grid | BROCKTON | 163662 | 02301 | 325 | Bio Gas | 05_12_21J27 | 05/15/2009 | 05/15/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2009 | Connected |  | N
National Grid | ADAMS | 164472 | 01220 | 95 | Solar | 05_07_912W73 | 10/15/2010 | 10/15/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2011 | Connected |  | N
National Grid | SAUGUS | 164906 | 01906 | 96 | Solar | 05_07_912W73 | 08/19/2011 | 08/19/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2011 | Connected |  | N
National Grid | MENDON | 164492 | 01756 | 210 | Solar | 05_09_901W3 | 04/21/2011 | 04/21/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2011 | Connected |  | N
National Grid | SHUTESBURY | 164281 | 01072 | 75 | Natural Gas | 05_12_22W2 | 02/16/2011 | 02/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2011 | Connected |  | N
National Grid | LONGMEADOW | 164011 | 01028 | 100 | Solar | 05_05_7L1 | 11/16/2009 | 11/16/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2010 | Connected |  | N
National Grid | BROCKTON | 164172 | 02302 | 78 | Solar | 05_14_5J11 | 05/20/2011 | 05/20/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2011 | Connected |  | N
National Grid | GRAFTON | 163825 | 01519 | 1750 | Solar | 05_09_1108W1 | 11/15/2010 | 11/15/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2011 | Connected |  | N
National Grid | NORTON | 163873 | 02766 | 280 | Bio Gas | 05_09_1108W2 | 06/02/2010 | 06/02/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2011 | Connected |  | N
National Grid | RANDOLPH | 165170 | 02368 | 425 | Natural Gas | 05_09_909W1 | 06/25/2009 | 06/25/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2010 | Connected |  | N
National Grid | STOUGHTON | 164114 | 02072 | 82 | Solar | 05_09_1109W1 | 12/29/2009 | 12/29/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2010 | Connected |  | N
National Grid | ADAMS | 164544 | 01220 | 95 | Solar | 05_09_909W2 | 05/05/2011 | 05/05/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2011 | Connected |  | N
National Grid | LYNN | 163937 | 01905 | 86 | Solar | 05_07_75W7 | 12/02/2010 | 12/02/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2011 | Connected |  | N
National Grid | MENDON | 163817 | 01756 | 95 | Solar | 05_09_516L3 | 05/25/2010 | 05/25/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHUTESBURY | 163816 | 01072 | 95 | Solar | 05_09_516L3 | 05/25/2010 | 05/25/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 163992 | 01028 | 95 | Solar | 05_09_516L3 | 11/22/2010 | 11/22/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2011 | Connected |  | N
National Grid | BROCKTON | 163991 | 02302 | 95 | Solar | 05_09_516L3 | 11/22/2010 | 11/22/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2011 | Connected |  | N
National Grid | GRAFTON | 519323 | 01519 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTON | 670156 | 02766 | 7.6 | Solar | 05_07_97W1 | 02/05/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | RANDOLPH | 519319 | 02368 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | STOUGHTON | 519304 | 02072 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHESHIRE | 163981 | 01225 | 120 | Solar | 05_14_60L3 | 06/09/2010 | 06/09/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2010 | Connected |  | N
National Grid | LYNN | 164518 | 01905 | 100 | Wind | 04_04_101L4 | 05/07/2010 | 05/07/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2010 | Connected |  | N
National Grid | UXBRIDGE | 164113 | 01569 | 60 | Solar | 05_09_1109W3 | 12/29/2009 | 12/29/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2010 | Connected |  | N
National Grid | SHUTESBURY | 164484 | 01072 | 375 | Solar | 05_05_336W4 | 04/15/2011 | 04/15/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2011 | Connected |  | N
National Grid | BELCHERTOWN | 163702 | 01007 | 500 | Solar | 05_12_10J6 | 06/12/2009 | 06/12/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2010 | Connected |  | N
National Grid | BROCKTON | 164155 | 02302 | 60 | Natural Gas | 05_07_91W41 | 01/11/2010 | 01/11/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2011 | Connected |  | N
National Grid | GRAFTON | 163836 | 01519 | 357 | Solar | 05_07_91W41 | 11/19/2010 | 11/19/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2011 | Connected |  | N
National Grid | NORTON | 164991 | 02766 | 1000 | Solar | 05_07_797W42 | 09/02/2011 | 09/02/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 165125 | 02368 | 100 | Solar | 05_05_3424W1 | 12/07/2009 | 12/07/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2010 | Connected |  | N
National Grid | STOUGHTON | 164578 | 02072 | 95 | Solar | 05_07_98W44 | 11/08/2010 | 11/08/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2011 | Connected |  | N
National Grid | ADAMS | 165128 | 01220 | 75 | Solar | 05_05_3424W3 | 12/07/2009 | 12/07/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2010 | Connected |  | N
National Grid | LYNN | 164310 | 01905 | 200 | Solar | 05_01_201W2 | 03/12/2010 | 03/12/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2010 | Connected |  | N
National Grid | UXBRIDGE | 164209 | 01569 | 82 | Solar | 05_01_201W2 | 02/17/2010 | 02/17/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2010 | Connected |  | N
National Grid | WENDELL | 164208 | 01379 | 60 | Solar | 05_01_201W2 | 02/17/2010 | 02/17/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2010 | Connected |  | N
National Grid | BELCHERTOWN | 164238 | 01007 | 82 | Solar | 05_12_12L4 | 02/10/2011 | 02/10/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2011 | Connected |  | N
National Grid | BROCKTON | 164433 | 02302 | 100 | Solar | 05_07_910W51 | 03/29/2011 | 03/29/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2011 | Connected |  | N
National Grid | GRAFTON | 164254 | 01519 | 300 | Solar | 05_05_9L3 | 02/22/2010 | 02/22/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2010 | Connected |  | N
National Grid | NORTON | 165168 | 02766 | 62.5 | Solar | 05_12_1388 | 04/06/2009 | 04/06/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2009 | Connected |  | N
National Grid | RANDOLPH | 164371 | 02368 | 142 | Solar | 05_12_1394 | 09/27/2010 | 09/27/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2011 | Connected |  | N
National Grid | BROCKTON | 163792 | 02301 | 215 | Solar | 05_05_344W2 | 05/16/2011 | 05/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2011 | Connected |  | N
National Grid | ADAMS | 163663 | 01220 | 325 | Bio Gas | 05_05_344W2 | 05/15/2009 | 05/15/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2009 | Connected |  | N
National Grid | SAUGUS | 164517 | 01906 | 95 | Solar | 05_01_201W3 | 05/05/2010 | 05/05/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 163851 | 01756 | 95 | Solar | 05_14_63L2 | 10/12/2009 | 10/12/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2010 | Connected |  | N
National Grid | WENDELL | 164305 | 01379 | 60 | Solar | 05_07_92W44 | 03/01/2010 | 03/01/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2010 | Connected |  | N
National Grid | BELCHERTOWN | 163772 | 01007 | 250 | Natural Gas | 05_07_92W54 | 01/20/2009 | 01/20/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2009 | Connected |  | N
National Grid | BROCKTON | 164473 | 02302 | 113 | Solar | 05_01_207W3 | 10/19/2010 | 10/19/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2011 | Connected |  | N
National Grid | GRAFTON | 163631 | 01519 | 95 | Solar | 05_14_70L1 | 04/13/2009 | 04/13/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2009 | Connected |  | N
National Grid | NORTON | 188889 | 02766 | 10 | Solar | 05_07_911W56 | 08/06/2018 | 08/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2019 | Connected |  | N
National Grid | RANDOLPH | 164421 | 02368 | 62 | Solar | 05_01_207W6 | 10/07/2010 | 10/07/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2011 | Connected |  | N
National Grid | STOUGHTON | 164257 | 02072 | 135 | Solar | 05_14_70L5 | 02/23/2010 | 02/23/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2010 | Connected |  | N
National Grid | CHESHIRE | 164262 | 01225 | 75 | Solar | 05_14_70L6 | 02/25/2010 | 02/25/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2010 | Connected |  | N
National Grid | SAUGUS | 164340 | 01906 | 63 | Solar | 05_07_1W6 | 03/14/2011 | 03/14/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2011 | Connected |  | N
National Grid | MENDON | 163823 | 01756 | 60 | Natural Gas | 05_01_HT40 | 05/19/2010 | 05/19/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2011 | Connected |  | N
National Grid | ERVING | 163581 | 01344 | 100 | Solar | 05_01_HT40 | 02/06/2009 | 02/06/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2009 | Connected |  | N
National Grid | BELCHERTOWN | 163579 | 01007 | 75 | Solar | 05_12_2310 | 02/05/2009 | 02/05/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2009 | Connected |  | N
National Grid | BROCKTON | 163253 | 02302 | 68.04 | Solar | 05_12_2370 | 07/22/2009 | 07/22/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2009 | Connected |  | N
National Grid | GRAFTON | 164358 | 01519 | 60 | Solar | 05_14_2326 | 03/22/2010 | 03/22/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2011 | Connected |  | N
National Grid | NORTON | 164357 | 02766 | 328 | Solar | 05_14_2358 | 03/22/2010 | 03/22/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2011 | Connected |  | N
National Grid | RANDOLPH | 164440 | 02368 | 190 | Solar | 05_14_312 | 04/11/2011 | 04/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2011 | Connected |  | N
National Grid | STOUGHTON | 164290 | 02072 | 260 | Solar | 05_05_348W7 | 03/01/2011 | 03/01/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2011 | Connected |  | N
National Grid | NORTH ADAMS | 164570 | 01247 | 135 | Solar | 05_14_20L3 | 05/19/2010 | 05/19/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2010 | Connected |  | N
National Grid | SAUGUS | 274206 | 01906 | 0 | Solar | 05_01_406L1 | 02/08/2017 | 03/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/23/2020 | 02/14/2020 | 17 | 1 | 16 |  | 02/08/2017 |  | Y | STD |  |  |  | 0 | 0 | 0 |  |  | 8/18/2021 | Connected |  | N
National Grid | MENDON | 408868 | 01756 | 0 | Battery Add-On | 05_05_336W1 | 02/11/2022 | 02/14/2022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2022 | 11/22/2022 | 193 | 192 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHUTESBURY | 195142 | 01072 | 4500 | Solar | 05_01_415L1 | 10/11/2018 | 10/19/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2018 | 12/20/2018 | 40 | 21 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 670477 | 01007 | 11.05 | Solar | 05_05_311W6 | 02/07/2025 | 03/10/2025 | 0 | 0 | 0 | 03/11/2025 | 03/11/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 205907 | 02302 | 10 | Solar | 05_09_523L2 | 01/14/2019 | 01/16/2019 | 0 | 0 | 0 | 06/18/2019 | 06/18/2019 | 20 | 18 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 528884 | 01519 | 10 | Solar | 05_09_527L1 | 08/22/2023 | 08/01/2023 | 0 | 0 | 0 | 08/24/2023 | 08/24/2023 | 42 | 17 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 189036 | 02766 | 57.6 | Solar | 05_01_8W1 | 08/01/2018 | 08/01/2018 | 0 | 0 | 0 | 08/02/2018 | 08/02/2018 | 134 | 26 | 108 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 2/19/2019 | Connected |  | N
National Grid | RANDOLPH | 206476 | 02368 | 120 | Solar | 05_01_8W1 | 03/26/2019 | 05/21/2019 | 0 | 0 | 0 | 05/22/2019 | 05/22/2019 | 13 | 3 | 10 | 10/16/2019 | 01/23/2020 | 67 | 50 | 17 |  |  | 0 | 0 | 0 |  | 01/23/2020 | 67 | 50 | 17 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 193105 | 02301 | 130 | Solar | 05_14_66L1 | 08/22/2018 | 08/29/2018 | 0 | 0 | 0 | 08/30/2018 | 08/30/2018 | 100 | 0 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 697467 | 01247 | 3.8 | Solar | 05_12_19W1 | 06/12/2025 | 06/27/2025 | 0 | 0 | 0 | 07/22/2025 | 07/22/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 195692 | 01906 | 0 | Solar | 05_05_318W3 | 09/12/2018 | 04/28/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
NSTAR | Sandwich | 557 | 2542 | 1500 | Wind | 4-81A-81A | 2009-01-12 | 2009-01-12 | 0 | 8 | 0 | 2009-02-18 |  | -28474 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-24 | 2009-06-24 |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2009-12-22 | Online | Private | N
NSTAR | Cambridge | 582 | 2139 | 21500 | Natural Gas | 811-36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | N
NSTAR | Woburn | 593 | 1801 | 75 | Capacitor | 211-H7XY |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2007-05-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | N
NSTAR | Plymouth | 658 | 2360 | 4500 | Wind | 3-89-926 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | N
NSTAR | Allston | 677 | 2134 | 4300 | Natural Gas | 341-82 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2007-11-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | N
NSTAR | Cambridge | 743 | 2138 | 8 | PV | 819-1NE6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Retired |  | N
NSTAR | Falmouth | 744 | 2540 | 1545 | Wind | 4-98A-98A | 2009-01-15 | 2009-01-15 | 0 |  | 0 | 2009-01-15 | 2009-03-13 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2009-04-29 | [7 empty] | 0 |  | 0 |  |  | 2010-03-23 | Online |  | Y
NSTAR | Edgartown | 863 | 2539 | 68 | Wind | 4-75-75 | 2009-01-05 | 2009-05-14 | 93 | 70 | 23 | 2009-05-14 | 2009-06-16 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-18 |  | 2008-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-08-14 |  | 2009-08-13 | Online | Private | Y
NSTAR | Woburn | 945 | 1801 | 95 | PV | 375-H11 | 2009-10-15 | 2009-10-15 | 0 |  | 0 | 2008-10-15 | 2008-10-30 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2008-11-13 | [7 empty] | 0 |  | 0 | 2009-02-11 |  | 2009-02-11 | Online |  | Y
NSTAR | Woods Hole | 990 | 2543 | 10 | Wind | 4-91-434 | 2009-02-17 | 2009-02-17 | 0 |  | 0 | 2009-02-17 | 2009-03-24 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2009-03-03 | [7 empty] | 0 |  | 0 | 2009-04-30 |  | 2009-05-07 | Online |  | Y
NSTAR | Canton | 1083 | 2021 | 39 | PV | 470-H7 | 2009-01-06 | 2009-01-13 | 5 | 4 | 1 | 2009-01-13 | 2009-01-29 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-01-12 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Waltham | 1084 | 2454 | 1200 | Diesel | 386-1356 | 2009-01-28 | 2009-02-25 | 20 | 19 | 1 | 2009-02-25 | 2009-04-01 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2009-07-07 |  | 2009-07-07 | Online | Private | N
NSTAR | Waltham | 1144 | 2451 | 235 | PV | 450-H7 | 2009-02-09 | 2009-02-19 | 8 | 7 | 1 | 2009-02-19 | 2009-03-26 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-03-30 |  | 2009-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-04-23 |  | 2009-04-09 | Online |  | N
NSTAR | Sharon | 1167 | 2067 | 20 | PV | 146-H7 | 2009-02-10 | 2010-07-08 | 367 | 366 | 1 | 2010-07-08 | 2010-08-02 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-17 |  | 2009-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online | Gov't | Y
NSTAR | Chelsea | 1171 | 2150 | 44 | PV | 488-H3 | 2009-02-11 | 2009-04-29 | 55 | 54 | 1 | 2009-04-29 | 2009-05-22 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-27 |  | 2009-03-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-07-02 |  | 2009-07-02 | Online | Private | Y
NSTAR | West Tisbury | 1172 | 2575 | 5 | Wind | 4-97-222 | 2009-02-17 | 2009-03-16 | 19 |  | 19 | 2017-10-17 |  | -30699 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2009-05-27 | 2009-05-27 | [6 empty] | 0 |  | 0 |  |  | 2009-07-08 | Online
NSTAR | Orleans | 1176 | 2662 | 10 | Wind | 4-95B-600 | 2009-02-17 | 2010-05-12 | 321 | 320 | 1 | 2010-05-12 | 2010-06-22 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-22 |  | 2009-06-30 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Brewster | 1177 | 2631 | 10 | Wind | 4-89B-89B | 2009-02-25 | 2009-02-26 | 1 | 0 | 1 | 2009-02-26 | 2009-04-14 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-16 |  | 2009-03-13 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-07-09 |  | 2009-07-09 | Online | Private | N
NSTAR | Hyannis | 1187 | 2601 | 105 | Natural Gas | 4-80B-80B | 2009-02-25 | 2009-02-26 | 1 | 0 | 1 | 2009-03-04 | 2009-04-13 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-30 |  | 2009-07-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2010-07-21 | Online | Private | N
NSTAR | Falmouth | 1189 | 2536 | 1650 | Wind | 4-98A-98A | 2009-03-10 | 2009-03-10 | 0 | 0 | 0 | 2009-03-10 | 2009-04-10 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-04-16 |  | 2009-03-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-07-21 | Online | Private | N
NSTAR | Roxbury | 1198 | 2109 | 35 | PV | 323-05 | 2009-03-15 | 2009-04-02 | 14 | 11 | 3 | 2017-11-03 | 2009-05-05 | -2186 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-05 |  | 2009-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-07-20 | Online | Gov't | Y
NSTAR | Somerville | 1203 | 2143 | 48 | PV | 250-1N81H1 | 2009-03-15 | 2009-03-18 | 3 | 0 | 3 | 2009-03-19 |  | -28495 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-10-31 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Winthrop | 1204 | 2152 | 1200 | Wind | TRM-PTC | 2009-03-20 | 2009-03-23 | 1 | 0 | 1 | 2009-03-24 | 2009-04-17 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-06 |  | 2009-05-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-06-18 |  | 2009-06-18 | Online | Gov't | N
NSTAR | Norfolk | 1219 | 2056 | 95 | PV | 146-H2 | 2009-03-24 | 2009-03-30 | 4 | 3 | 1 | 2009-03-30 | 2009-04-30 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-10-28 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-23 |  | 2010-06-23 | Online | Private | Y
NSTAR | Somerville | 1226 | 2144 | 85 | Natural Gas | 250-1N81H1 | 2009-03-30 | 2009-11-02 | 155 | 152 | 3 | 2009-11-02 | 2009-11-19 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-16 |  | 2010-07-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-06-08 | Online | Private | N
NSTAR | Weston | 1234 | 2493 | 95 | PV | 282-H10 | 2009-04-06 | 2009-05-05 | 21 | 20 | 1 | 2009-05-05 | 2009-06-08 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-23 |  | 2009-09-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-11-20 | Online | Private | N
NSTAR | Plymouth | 1240 | 2360 | 1670 | Wind | 3-71-71 | 2009-04-08 | 2009-04-16 | 6 | 4 | 2 | 2009-04-16 | 2009-05-07 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-18 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-09-03 |  | 2012-11-08 | Online | Private | N
NSTAR | Woburn | 1245 | 1801 | 26 | PV | 375-H6 | 2009-04-08 | 2009-04-16 | 6 | 4 | 2 | 2009-04-16 | 2009-05-19 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-26 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-09-03 |  | 2009-09-03 | Online | Private | Y
NSTAR | Woburn | 1246 | 1801 | 30 | PV | 375-H6 | 2009-04-13 | 2009-04-17 | 4 | 1 | 3 | 2009-04-22 | 2009-06-02 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-04 |  | 2009-07-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-22 |  | 2009-12-22 | Online | Gov't | N
NSTAR | Walpole | 1248 | 2081 | 75 | PV | 146-H4 | 2009-04-10 | 2009-05-05 | 17 | 10 | 7 | 2009-05-05 | 2009-06-08 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-09-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 1252 | 2360 | 750 | Wind | 3-71-937 | 2009-04-17 | 2009-04-22 | 3 | 0 | 3 | 2009-04-22 | 2009-05-15 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-05-18 |  | 2009-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-08-05 |  | 2009-08-05 | Online | Private | Y
NSTAR | Osterville | 1253 | 2655 | 52 | PV | 4-80A-490 | 2009-04-21 | 2009-04-29 | 6 | 4 | 2 | 2009-04-30 | 2009-05-27 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-05 |  | 2009-05-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2008-07-30 |  | 2009-07-30 | Online | Gov't | N
NSTAR | Chelsea | 1265 | 2150 | 60 | PV | 488-H6 | 2009-04-29 | 2009-06-09 | 29 | 27 | 2 | 2009-06-15 | 2009-07-20 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-11-30 | N/A | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | N
NSTAR | West Barnstable | 1272 | 2668 | 600 | Wind | 4-82-516 | 2009-05-07 | 2009-06-08 | 22 | 22 | 0 | 2009-06-08 | 2009-07-10 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-14 |  |  | No | STD |  |  |  | 0 | 0 | 0 | 2011-02-15 |  | 2011-02-16 | Online | Gov't | N
NSTAR | Milton | 1277 | 2186 | 75 | Natural Gas | 496-H2 | 2009-05-14 | 2009-06-18 | 25 | 24 | 1 | 2009-06-18 | 2009-07-09 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-09 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-15 | Online | Private | Y
NSTAR | Dorchester | 1283 | 2124 | 45 | PV | 496-H8 | 2009-05-21 | 2009-05-28 | 5 | 1 | 4 | 2009-05-29 | 2009-06-24 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-01 |  | 2009-09-04 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-30 |  | 2009-12-30 | Online | Private | N
NSTAR | Cambridge | 1289 | 2139 | 75 | PV | 817-02 | 2009-05-19 | 2009-06-04 | 12 | 5 | 7 | 2009-06-05 | 2011-10-22 | 620 | 0 | 620 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-24 |  | 2009-12-31 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 1290 | 2360 | 750 | Wind | 3-14-911 | 2009-05-26 | 2009-06-02 | 5 | 2 | 3 | 2009-06-02 | 2009-06-23 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-06-29 |  | 2009-07-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-09-17 | Online | Private | N
NSTAR | Marshfield | 1293 | 2050 | 135 | PV | 3-25-908 | 2009-05-28 | 2009-06-01 | 2 | 1 | 1 | 2009-06-02 | 2009-06-29 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-01 |  | 2009-07-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-08-06 |  | 2009-08-06 | Online | Private | Y
NSTAR | Hyannis | 1294 | 2601 | 27 | PV | 4-63-521 | 2009-05-29 | 2009-06-02 | 2 | 0 | 2 | 2009-06-03 | 2009-06-30 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-08 |  | 2009-10-08 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-04 |  | 2010-02-04 | Online | Private | N
NSTAR | Framingham | 1297 | 1701 | 100 | PV | 433-H4 | 2009-06-10 | 2009-06-11 | 1 | 1 | 0 | 2009-06-11 | 2009-07-01 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-07-08 |  | 2009-08-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-03 | Online | Private | Y
NSTAR | New Bedford | 1303 | 2740 | 44 | PV | 2-103-103 | 2009-06-18 | 2009-09-10 | 60 | 60 | 0 | 2009-09-10 | 2009-10-02 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-10-15 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-31 |  | 2009-12-31 | Online | Gov't | N
NSTAR | Framingham | 1316 | 1701 | 75 | PV | 274-H4 | 2009-06-23 | 2009-07-01 | 6 | 6 | 0 | 2009-07-02 |  | -28570 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-06-23 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Jamaica Plain | 1330 | 2130 | 150 | Natural Gas | 284-1360H2 | 2009-06-23 | 2009-06-25 | 2 | 2 | 0 | 2009-06-25 | 2009-07-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-16 |  | 2009-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-11-24 | Online | Private | Y
NSTAR | Edgartown | 1335 | 2539 | 5 | Wind | 4-75-75 | 2009-06-22 |  | -28562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Hopkinton | 1337 | 1748 | 2000 | Other | 126-H1 | 2009-06-29 | 2009-06-30 | 1 | 1 | 0 | 2009-06-30 | 2009-07-16 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-05 |  | 2009-10-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-10 | Online | Private | Y
NSTAR | Bellingham | 1344 | 2019 | 75 | PV | 65-H4 | 2009-06-30 | 2009-07-01 | 1 | 1 | 0 | 2009-07-01 | 2009-07-29 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-08 |  | 2009-08-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-10-15 |  | 2009-10-15 | Online | Private | N
NSTAR | Hopkinton | 1346 | 1748 | 177 | PV | 65-H7 | 2009-06-30 | 2009-06-30 | 0 | 0 | 0 | 2009-07-01 | 2009-08-03 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-13 |  | 2009-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-10-08 | Online | Private | N
NSTAR | Hopkinton | 1347 | 1748 | 82 | PV | 65-H7 | 2009-07-03 | 2009-07-07 | 2 | 0 | 2 | 2009-07-08 | 2009-08-05 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-16 |  | 2009-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-09-23 |  | 2009-09-23 | Online | Private | N
NSTAR | Bedford | 1353 | 1730 | 142 | PV | 512-1399H | 2009-07-22 | 2009-07-22 | 0 | 0 | 0 | 2009-07-30 | 2009-09-03 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-21 |  | 2009-01-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-03 | Online | Private | Y
NSTAR | Arlington | 1380 | 2474 | 52 | PV | 320-H7 | 2009-07-24 | 2009-07-30 | 4 | 3 | 1 | 2009-07-30 | 2009-08-20 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-26 |  | 2009-10-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Brighton | 1383 | 2135 | 58 | PV | 329-H5 | 2009-07-24 | 2009-07-30 | 4 | 3 | 1 | 2009-07-30 | 2009-08-20 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2009-10-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Brighton | 1384 | 2135 | 16 | PV | 329-H5 | 2009-07-23 | 2009-07-29 | 4 | 0 | 4 | 2009-07-29 | 2009-08-14 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-08-18 |  | 2009-07-23 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Roslindale | 1386 | 2131 | 30 | PV | 496-H3 | 2009-07-14 | 2009-08-13 | 22 | 10 | 12 | 2009-08-13 | 2009-09-15 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-16 |  |  | No | STD |  |  |  | 0 | 0 | 0 | 2010-01-07 |  | 2010-01-07 | Online | Private | N
NSTAR | Dedham | 1388 | 2026 | 400 | Natural Gas | 20-H5 | 2009-07-13 | 2009-08-06 | 18 | 4 | 14 | 2009-08-06 | 2009-09-10 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-02 |  | 2009-10-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-10 | Online | Private | N
NSTAR | Dedham | 1390 | 2026 | 75 | PV | 20-H5 | 2009-06-19 | 2009-08-03 | 31 | 0 | 31 | 2009-08-03 | 2009-09-09 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-02-28 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 1393 | 2360 | 1670 | Wind | 3-89-926 | 2009-08-07 | 2009-12-17 | 94 | 93 | 1 | 2009-12-18 | 2010-09-21 | 197 | 0 | 197 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-04 |  | 2011-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-10 |  |  | Withdrawn | Gov't | N
NSTAR | Weston | 1400 | 2493 | 200 | Hydro | 282-H8 | 2009-08-07 | 2010-01-15 | 115 | 114 | 1 | 2010-01-15 |  | -28711 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-05-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Milton | 1401 | 2186 | 2000 | Wind | 496-H7 | 2009-08-10 | 2009-10-14 | 47 | 47 | 0 | 2009-10-14 | 2009-11-04 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-05 |  | 2009-12-04 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-02 |  | 2010-03-02 | Online | Private | Y
NSTAR | Orleans | 1402 | 2653 | 85 | PV | 4-94A-632 | 2009-08-17 | 2009-08-24 | 5 | 3 | 2 | 2009-08-25 | 2009-09-16 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-09-21 |  | 2009-08-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-17 |  | 2009-12-17 | Online | Private | Y
NSTAR | Oak Bluffs | 1413 | 2557 | 39 | PV | 4-99-221 | 2009-08-25 | 2010-03-30 | 155 | 153 | 2 | 2010-03-30 | 2011-03-09 | 246 | 0 | 246 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-15 |  | 2009-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-12 |  | 2011-04-15 | Online | Private | Y
NSTAR | Bedford | 1426 | 1730 | 75 | Natural Gas | 533-H7 | 2009-09-08 | 2009-09-16 | 6 | 5 | 1 | 2009-09-16 | 2009-12-09 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-09 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-12-23 | Online | Private | N
NSTAR | Watertown | 1435 | 2472 | 500 | PV | 467-H9 | 2009-09-08 | 2009-10-30 | 38 | 37 | 1 | 2009-10-30 | 2009-12-08 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-18 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting App Fee and/or Further Info | Private | N
NSTAR | Newton | 1436 | 2467 | 400 | Natural Gas | 467-H14 | 2009-09-08 | 2010-03-01 | 124 | 123 | 1 | 2010-03-01 | 2010-04-01 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-01 |  | 2009-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-26 |  | 2010-05-26 | Online | Gov't | Y
NSTAR | Cambridge | 1437 | 2139 | 30 | PV | 814-14 | 2009-09-15 | 2009-09-28 | 9 | 9 | 0 | 2009-09-28 | 2010-10-26 | 281 | 0 | 281 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-12 |  | 2010-03-31 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-26 | Online | Private | N
NSTAR | Dorchester | 1440 | 2122 | 1240 | PV | 466-1482H1 | 2009-09-25 | 2009-09-30 | 3 | 2 | 1 | 2009-09-30 | 2009-10-16 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-10-23 |  | 2009-09-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2009-12-22 |  | 2012-01-17 | Online |  | N
NSTAR | Bourne | 1450 | 2534 | 100 | PV | 4-78-409 | 2009-10-06 | 2009-10-09 | 3 | 0 | 3 | 2009-10-09 | 2009-10-29 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-18 |  | 2010-07-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-09 |  | 2010-11-09 | Online | Gov't | Y
NSTAR | Acton | 1464 | 1720 | 95 | PV | 416-H2 | 2009-10-06 | 2009-10-09 | 3 | 0 | 3 | 2009-10-09 | 2009-12-10 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-15 |  | 2009-06-22 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-25 |  | 2010-02-25 | Online | Private | Y
NSTAR | Falmouth | 1465 | 2536 | 67 | PV | 4-80B-523 | 2009-10-06 | 2009-10-23 | 13 | 10 | 3 | 2009-10-23 | 2009-11-10 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-21 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-04 |  | 2010-03-04 | Online | Gov't | N
NSTAR | Acton | 1466 | 1720 | 190 | PV | 416-H2 | 2009-10-09 | 2009-10-15 | 4 | 2 | 2 | 2009-10-15 | 2009-11-19 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-10 |  | 2009-11-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-01-14 |  | 2010-01-14 | Online | Private | Y
NSTAR | Woburn | 1468 | 1801 | 101 | PV | 375-H11 | 2009-10-09 | 2009-10-23 | 10 | 7 | 3 | 2009-10-23 | 2009-11-13 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-11-18 |  | 2009-10-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2009-12-16 | Online | Private | Y
NSTAR | Framingham | 1469 | 1702 | 20 | PV | 2404 | 2009-10-13 | 2009-10-23 | 8 | 7 | 1 | 2009-10-23 | 2009-12-16 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-17 |  | 2009-11-24 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-02 |  | 2010-06-02 | Online | Private | N
NSTAR | Dartmouth | 1470 | 2747 | 95 | PV | 2-532-532 | 2009-10-16 | 2009-10-23 | 5 | 1 | 4 | 2009-10-23 | 2009-11-30 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-03 |  | 2009-11-05 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-20 |  | 2010-06-02 | Online | Private | Y
NSTAR | Woburn | 1483 | 1801 | 45 | PV | 375-H6 | 2009-10-21 | 2009-10-27 | 4 | 3 | 1 | 2009-10-27 | 2009-12-01 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-24 |  | 2010-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-01-11 |  | 2012-02-06 | Online | Gov't | Y
NSTAR | Boston | 1484 | 2110 | 30 | PV | 528-129H | 2009-10-21 | 2009-11-09 | 13 | 11 | 2 | 2009-11-10 | 2009-12-14 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-13 |  | 2009-11-06 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-18 |  | 2010-02-18 | Online | Private | Y
NSTAR | Dennisport | 1485 | 2639 | 33 | PV | 4-92B-583 | 2009-10-29 | 2009-11-03 | 3 | 3 | 0 | 2009-11-03 | 2009-11-13 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-15 |  | 2011-04-30 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Bourne | 1491 | 2532 | 600 | Wind | 4-86-402 | 2009-10-30 | 2009-12-04 | 25 | 24 | 1 | 2009-12-07 | 2010-11-30 | 256 | 0 | 256 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-31 |  |  | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Private | N | 2011-01-31
NSTAR | Boston | 1494 | 2127 | 7200 | Natural Gas | 515-193H | 2009-11-03 | 2009-11-10 | 5 | 5 | 0 | 2009-11-10 | 2009-11-25 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-04 |  | 2009-12-04 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-02 |  | 2010-02-02 | Online | Private | N
NSTAR | Lexington | 1495 | 2421 | 150 | Natural Gas | 3401 | 2009-11-05 | 2009-11-17 | 8 | 8 | 0 | 2009-11-17 |  | -28668 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-01-31 | n/a | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Boston | 1498 | 2118 | 6600 | Natural Gas | 376-90 | 2009-11-09 |  | -28662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Plymouth | 1500 | 2360 | 1650 | Wind | 3-89-926 | 2009-11-10 | 2009-11-12 | 2 | 2 | 0 | 2009-11-12 | 2009-12-23 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-11-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-01-21 |  |  | Withdrawn | Private | N
NSTAR | Cambridge | 1503 | 2138 | 66 | PV | 827-31 | 2009-11-13 | 2009-11-20 | 5 | 4 | 1 | 2009-11-20 | 2010-01-04 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-05 |  | 2010-01-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-16 | Online | Private | N
NSTAR | Somerville | 1505 | 2143 | 75 | Natural Gas | 250-1N81H1 | 2009-11-13 | 2009-11-17 | 2 | 1 | 1 | 2009-11-17 | 2009-12-21 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-05 |  | 2009-11-13 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-11 |  | 2010-02-11 | Online | Private | Y
NSTAR | East Falmouth | 1506 | 2536 | 40 | PV | 4-98A-98A | 2009-11-16 | 2009-11-17 | 1 | 0 | 1 | 2009-11-17 | 2009-12-23 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-16 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-07-07 |  | 2010-07-07 | Online | Private | N
NSTAR | Waltham | 1507 | 2154 | 60 | Natural Gas | 33-H2 | 2009-11-16 | 2009-11-19 | 3 | 2 | 1 | 2009-11-19 | 2009-12-23 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-04 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-23 |  | 2010-02-23 | Online | Gov't | Y
NSTAR | Eastham | 1508 | 2642 | 80 | PV | 4-94B-646 | 2009-11-13 | 2009-11-17 | 2 | 0 | 2 | 2009-12-03 | 2009-12-21 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-24 |  | 2010-02-24 | Online | Private | Y
NSTAR | Waltham | 1509 | 2453 | 272 | PV | 282-H8 | 2009-10-16 | 2009-11-17 | 22 | 0 | 22 | 2009-11-24 | 2009-12-22 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-26 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-10 |  | 2010-11-10 | Online | Private | N
NSTAR | Jamaica Plain | 1510 | 2130 | 75 | Natural Gas | 350-H2 | 2009-10-16 | 2009-11-18 | 23 | 0 | 23 | 2009-11-19 | 2009-12-23 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-05 |  | 2009-12-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-02-01 | Online | Private | Y
NSTAR | Newton | 1511 | 2459 | 36 | PV | 467-H5 | 2009-10-18 | 2009-11-18 | 23 | 0 | 23 | 2009-12-03 | 2010-01-08 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-27 |  | 2009-12-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-06 |  | 2010-05-06 | Online | Private | Y
NSTAR | Somerville | 1512 | 2145 | 198 | PV | 250-1N81H1 | 2009-11-17 | 2009-11-23 | 4 | 2 | 2 | 2009-11-24 | 2009-12-24 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-14 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-10 |  | 2010-11-10 | Online | Private | N
NSTAR | Needham | 1513 | 1730 | 75 | Natural Gas | 148-H1 | 2009-11-19 | 2009-11-19 | 0 | 0 | 0 | 2009-11-20 | 2009-12-22 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2009-12-23 |  | 2009-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-01-28 |  | 2010-01-28 | Online | Private | Y
NSTAR | Westport | 1514 | 2790 | 34 | PV | 2-523-523 | 2009-11-20 | 2009-12-03 | 9 | 9 | 0 | 2009-12-03 | 2010-01-28 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-02 |  | 2009-12-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-13 |  | 2010-05-13 | Online | Private | Y
NSTAR | Dedham | 1516 | 2026 | 167 | PV | 13-H1 | 2009-11-25 | 2009-11-27 | 2 | 0 | 2 | 2009-12-03 | 2010-01-08 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-13 |  | 2009-12-31 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2010-07-22 |  | 2010-07-22 | Online | Gov't | Y
NSTAR | Brewster | 1520 | 2631 | 101 | PV | 4-89B-573 | 2009-11-25 | 2009-11-27 | 2 | 0 | 2 | 2009-12-03 | 2009-12-23 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-28 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-02-23 |  | 2010-02-23 | Online | Gov't | Y
NSTAR | Eastham | 1521 | 2642 | 101 | PV | 4-94A-648 | 2009-11-25 | 2009-11-27 | 2 | 0 | 2 | 2009-12-03 | 2010-01-28 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-01-28 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-07-16 |  | 2010-07-16 | Online | Gov't | Y
NSTAR | Brewster | 1522 | 2631 | 101 | PV | 4-89B-573 | 2009-12-03 | 2009-12-03 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | East Falmouth | 1526 | 2540 | 20 | PV | 4-98A-98A | 2009-12-02 | 2009-12-15 | 9 | 9 | 0 | 2009-12-16 |  | -28689 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-01-01 | N/A | N/A |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Wellfleet | 1527 | 2667 | 1650 | Wind | 4-94B-653 | 2009-11-30 | 2009-12-17 | 13 | 6 | 7 | 2009-12-18 | 2010-01-25 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-05 |  | 2010-06-30 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Kingston | 1531 | 2364 | 100 | Wind | 3-17-913 | 2009-12-16 | 2010-01-18 | 23 | 22 | 1 | 2010-01-18 | 2010-02-12 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-22 |  | 2009-12-11 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-07 |  | 2010-04-07 | Online | Private | Y
NSTAR | Framingham | 1534 | 1702 | 63 | PV | 240-H4 | 2009-12-16 | 2009-12-22 | 4 | 2 | 2 | 2009-12-23 | 2010-01-04 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-04 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-11 |  | 2010-03-11 | Online | Private | Y
NSTAR | Dartmouth | 1535 | 2748 | 32 | PV | 2-532-532 | 2009-12-17 | 2010-01-12 | 18 | 16 | 2 | 2010-01-12 | 2010-02-11 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-12 |  | 2010-02-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-25 |  | 2010-03-25 | Online | Gov't | N
NSTAR | Medway | 1536 | 2053 | 134 | PV | 65-H5 | 2009-12-17 | 2010-01-05 | 13 | 11 | 2 | 2010-01-05 | 2010-01-25 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-08 |  | 2009-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-08 |  | 2010-04-08 | Online | Private | Y
NSTAR | Plymouth | 1537 | 2360 | 30 | PV | 3-73-938 | 2009-12-22 | 2010-10-19 | 215 | 215 | 0 | 2010-10-19 | 2010-10-20 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-10-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | N
NSTAR | South Dartmouth | 1541 | 2748 | 750 | Wind | 2-528-528 | 2010-01-04 | 2010-01-07 | 3 | 1 | 2 | 2010-01-07 | 2010-02-10 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-02-16 |  | 2010-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-01 |  | 2010-04-01 | Online | Private | Y
NSTAR | Cambridge | 1544 | 2141 | 29 | PV | 811-37 | 2010-01-05 | 2010-06-30 | 126 | 123 | 3 | 2010-06-30 | 2010-09-10 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-06 |  | 2010-01-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2011-06-01 |  | 2011-06-01 | Online | Gov't | N
NSTAR | Hyannis | 1545 | 2601 | 200 | Wind | 4-80B-523 | 2010-01-05 | 2010-01-12 | 5 | 2 | 3 | 2010-01-12 | 2010-02-16 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-10 |  | 2010-03-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-26 |  | 2011-04-28 | Online | Private | N
NSTAR | Dorchester | 1546 | 2125 | 75 | Natural Gas | 483-08 | 2010-01-06 | 2010-01-27 | 15 | 12 | 3 | 2010-01-27 | 2010-04-14 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-20 |  | 2010-04-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-30 |  | 2012-04-09 | Online | Private | N
NSTAR | Plymouth | 1547 | 2360 | 250 | PV | 3-13-943 | 2010-01-06 | 2010-03-03 | 40 | 37 | 3 | 2010-03-03 | 2010-03-25 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-26 |  | 2010-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-22 |  | 2012-03-30 | Online | Private | Y
NSTAR | New Bedford | 1548 | 2740 | 39 | PV | 2-38-38 | 2010-01-08 | 2010-02-01 | 16 | 12 | 4 | 2010-02-01 | 2010-03-03 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-04 |  | 2010-02-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-04-21 |  | 2010-04-21 | Online | Private | Y
NSTAR | Bourne | 1550 | 2532 | 27 | PV | 4-81A-81A | 2010-01-11 | 2010-01-27 | 12 | 9 | 3 | 2010-01-27 | 2010-03-01 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-02 |  | 2010-02-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-05-05 |  | 2010-05-05 | Online | Private | N
NSTAR | Boston | 1554 | 2122 | 170 | PV | 106-H4 | 2010-01-08 | 2010-01-28 | 14 | 12 | 2 | 2010-01-28 | 2010-03-09 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-03-31 |  | 2010-03-31 | Online | Gov't | N
NSTAR | Bourne | 1555 | 2532 | 28 | PV | 3-88-923 | 2010-01-15 | 2010-06-10 | 104 | 103 | 1 | 2010-06-18 | 2010-07-14 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-01-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | South Dartmouth | 1559 | 2748 | 3340 | Wind | 2-531-531 | 2010-01-19 |  | -28713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2010-01-22 | Online | Private | Y
NSTAR | Bourne | 1562 | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-19 |  | -28713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Bourne | 1563 | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-19 |  | -28713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Bourne | 1564 | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-19 |  | -28713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Bourne | 1565 | 2452 | 1500 | Wind | 4-81A-81A | 2010-01-29 | 2010-02-02 | 2 | 0 | 2 | 2010-02-02 | 2010-03-25 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-25 |  | 2010-02-22 | N/A | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Dennis | 1569 | 2660 | 150 | PV | 4-92B-92B | 2010-02-01 | 2010-02-04 | 3 | 1 | 2 | 2010-02-04 | 2010-03-03 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-04 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-07-15 |  | 2010-07-15 | Online | Gov't | Y
NSTAR | Harwich | 1571 | 2645 | 104 | PV | 4-95A-95A | 2010-02-01 | 2010-02-04 | 3 | 1 | 2 | 2010-02-04 | 2010-03-12 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-22 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-06-14 | Online | Gov't | Y
NSTAR | Bourne | 1572 | 2532 | 143 | PV | 4-86-402 | 2010-02-04 | 2010-02-12 | 6 | 6 | 0 | 2010-02-16 | 2010-03-29 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-29 |  | 2010-04-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-12 |  | 2010-08-12 | Online | Private | Y
NSTAR | Canton | 1573 | 2021 | 155 | PV | 470-H10 | 2010-02-04 | 2010-02-25 | 15 | 15 | 0 | 2010-02-25 | 2010-03-30 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-14 |  | 2010-11-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Response and/or Cost Estimates from Eng | Private | Y | 2011-05-09
NSTAR | Charlestown | 1574 | 2129 | 555 | Diesel | 10-H1 | 2010-02-16 | 2010-02-17 | 1 | 1 | 0 | 2010-02-17 | 2010-03-05 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-08 |  | 2010-04-12 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-23 |  | 2010-08-23 | Online | Gov't | Y
NSTAR | Ashland | 1580 | 1721 | 21 | PV | 274-1429H1 | 2010-02-11 | 2010-02-24 | 9 | 5 | 4 | 2010-02-25 | 2010-03-25 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-26 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-07 | Online | Gov't | N
NSTAR | Boston | 1581 | 2128 | 200 | PV | 592-70H | 2010-02-18 | 2010-02-23 | 3 | 3 | 0 | 2010-02-24 | 2010-04-20 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-21 |  | 2010-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-12 |  | 2010-08-12 | Online | Gov't | Y
NSTAR | Watertown | 1582 | 2472 | 28 | PV | 467-H8 | 2010-02-08 |  | -28727 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Bourne | 1583 | 2532 | 1500 | Wind | 3-88-923 | 2010-03-01 | 2010-03-02 | 1 | 1 | 0 | 2010-03-03 | 2010-03-05 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-03-08 |  | 2010-05-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-29 |  |  | Withdrawn | Gov't | Y
NSTAR | Fairhaven | 1585 | 2719 | 85 | PV | 2-221-221 | 2010-03-01 | 2010-03-08 | 5 | 4 | 1 | 2010-08-02 | 2010-08-30 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-09-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Wareham | 1587 | 2571 | 4398 | PV | 3-83-83 | 2010-03-03 | 2010-03-08 | 3 | 3 | 0 | 2010-03-08 | 2011-04-15 | 289 | 0 | 289 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-20 |  | 2010-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-28 |  | 2011-01-28 | Withdrawn | Private | Y
NSTAR | Framingham | 1588 | 1702 | 60 | Natural Gas | 2401 | 2010-03-12 | 2010-03-24 | 8 | 8 | 0 | 2010-03-25 | 2010-04-07 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-08 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-10 |  | 2010-06-10 | Online | Private | Y
NSTAR | Walpole | 1589 | 2081 | 104 | PV | 146-H6 | 2010-03-12 | 2010-03-26 | 10 | 10 | 0 | 2010-03-26 | 2010-04-20 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-20 |  | 2010-04-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-07-14 | Online | Private | Y
NSTAR | Woburn | 1590 | 1801 | 30 | PV | 375-H9 | 2010-03-19 | 2010-03-23 | 2 | 2 | 0 | 2010-03-24 | 2010-04-07 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-27 |  | 2010-05-03 | No | STD |  |  |  | 0 | 0 | 0 | 2010-08-05 |  | 2010-08-05 | Online | Private | Y
NSTAR | Hyannis | 1591 | 2601 | 259 | PV | 4-84B-524 | 2010-03-22 | 2010-03-24 | 2 | 2 | 0 | 2010-07-30 | 2010-10-08 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-06 |  | 2010-07-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2011-03-09 |  | 2010-08-05 | Online | Private | Y
NSTAR | New Bedford | 1592 | 2740 | 1600 | PV | 4-107-107 | 2010-03-22 | 2010-03-31 | 7 | 7 | 0 | 2010-03-31 | 2010-07-02 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-04-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | North Dartmouth | 1593 | 2747 | 1500 | PV | 2-541-541 | 2010-03-23 | 2010-03-26 | 3 | 3 | 0 | 2010-03-26 | 2010-05-10 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-10 |  | 2010-03-26 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-06-09 |  |  |  | Private | Y
NSTAR | Falmouth | 1594 | 2536 | 50 | PV | 4-76-437 | 2010-03-25 | 2010-04-01 | 5 | 5 | 0 | 2010-04-01 | 2010-05-07 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-23 |  | 2010-05-30 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-02-14 |  | 2012-02-14 | Online | Gov't | Y
NSTAR | Falmouth | 1595 | 2540 | 1650 | Wind | 4-98A-98A | 2010-03-29 | 2010-04-01 | 3 | 3 | 0 | 2010-04-01 | 2010-04-20 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-14 |  | 2010-03-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-15 |  | 2012-02-14 | Online | Private | N
NSTAR | Needham | 1596 | 2494 | 78 | PV | 292-H10 | 2010-03-31 | 2010-04-01 | 1 | 1 | 0 | 2010-04-01 | 2010-05-11 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-12 |  | 2010-05-21 | No | STD |  |  |  | 0 | 0 | 0 | 2010-10-15 |  | 2010-10-15 | Online | Private | Y
NSTAR | Mashpee | 1597 | 2649 | 141 | PV | 4-88-453 | 2010-04-02 | 2010-04-09 | 5 | 5 | 0 | 2010-04-09 | 2010-04-20 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-04-30 |  | 2010-04-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2010-07-21 |  | 2010-07-21 | Online | Private | Y
NSTAR | Sandwich | 1598 | 2537 | 29 | PV | 4-87A-471 | 2010-04-09 | 2010-04-16 | 5 | 5 | 0 | 2010-04-20 | 2010-05-26 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-05-27 |  | 2010-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-16 |  | 2010-12-16 | Online | Gov't | N
NSTAR | Milton | 1600 | 2186 | 60 | PV | 362-02 | 2010-04-21 |  | -28779 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Hyannis | 1601 | 2601 | 48 | PV | 4-80B-80B | 2010-04-21 | 2010-04-21 | 0 | 0 | 0 | 2010-05-18 | 2010-06-15 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-07 |  | 2010-10-07 | Online | Private | Y
NSTAR | Hyannis | 1602 | 2601 | 60 | PV | 4-80B-80B | 2010-04-21 | 2010-05-18 | 19 | 19 | 0 | 2010-05-18 | 2010-06-16 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-17 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-11 |  | 2010-08-11 | Online | Private | Y
NSTAR | Hyannis | 1603 | 2601 | 40 | PV | 4-84B-524 | 2010-04-21 | 2010-05-05 | 10 | 10 | 0 | 2010-05-05 | 2010-06-10 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-25 |  | 2010-08-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-01-13 | Online | Private | N
NSTAR | Somerville | 1604 | 2144 | 85 | Natural Gas | 59-1393H1 | 2010-04-21 | 2010-05-05 | 10 | 10 | 0 | 2010-05-05 | 2010-06-29 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-30 |  | 2010-08-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-01-13 | Online | Private | N
NSTAR | Somerville | 1605 | 2144 | 85 | Natural Gas | 59-1393H1 | 2010-04-21 | 2010-05-05 | 10 | 10 | 0 | 2010-05-05 | 2010-06-25 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-25 |  | 2010-08-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-01-13 | Online | Private | N
NSTAR | Somerville | 1606 | 2144 | 85 | Natural Gas | 59-1393H1 | 2010-04-21 | 2010-06-07 | 33 | 33 | 0 | 2010-06-07 | 2010-07-13 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-13 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-09-29 | Online | Gov't | N
NSTAR | Dorchester | 1608 | 2121 | 36 | PV | 143-151H1 | 2010-04-21 | 2010-06-07 | 33 | 33 | 0 | 2010-06-07 | 2010-07-13 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-11 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-09-29 | Online | Gov't | Y
NSTAR | Dorchester | 1609 | 2122 | 45 | PV | 466-1481H1 | 2010-04-23 | 2010-05-17 | 16 | 16 | 0 | 2010-05-18 | 2010-06-14 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-09 |  | 2010-08-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-10 | Online | Gov't | Y
NSTAR | Watertown | 1610 | 2472 | 34 | PV | 467-H9 | 2010-04-23 | 2010-05-24 | 21 | 21 | 0 | 2010-05-25 | 2010-07-09 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-13 |  | 2010-03-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-09 |  | 2010-08-09 | Online | Gov't | Y
NSTAR | Newton | 1611 | 2460 | 30 | PV | 17-H1 | 2010-04-23 | 2010-05-10 | 11 | 11 | 0 | 2010-08-26 | 2010-09-21 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-14 |  | 2010-05-24 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-20 |  | 2010-10-22 | Online | Private | Y
NSTAR | Hopkinton | 1612 | 1748 | 29 | PV | 126-H1 | 2010-04-26 | 2010-05-11 | 11 | 11 | 0 | 2010-05-12 | 2010-06-14 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-15 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-22 | Online | Private | Y
NSTAR | Mashpee | 1613 | 2649 | 192 | PV | 4-88-453 | 2010-04-28 | 2010-05-03 | 3 | 3 | 0 | 2010-05-03 | 2010-06-30 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-01 |  | 2010-07-16 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-08 |  | 2011-03-08 | Online | Gov't | N
NSTAR | Freetown | 1614 | 2717 | 82 | PV | 2-102-102 | 2010-04-28 | 2010-05-03 | 3 | 3 | 0 | 2010-05-03 | 2010-07-08 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-13 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-22 |  | 2011-03-25 | Online | Gov't | Y
NSTAR | Bourne | 1615 | 2532 | 50 | Wind | 4-79-79 | 2010-04-29 | 2010-05-10 | 7 | 7 | 0 | 2010-05-12 | 2010-06-14 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-15 |  | 2010-05-17 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-29 |  | 2010-09-29 | Online | Gov't | Y
NSTAR | Boston | 1616 | 2126 | 11 | PV | 496-H8 | 2010-04-30 | 2010-05-12 | 8 | 8 | 0 | 2010-05-12 | 2010-06-14 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-17 |  | 2010-05-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-26 |  | 2011-05-09 | Online | Gov't | Y
NSTAR | Hyannis | 1617 | 2601 | 14 | PV | 4-63-905 | 2010-05-03 | 2010-05-12 | 7 | 7 | 0 | 2010-05-12 | 2010-06-11 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-30 | No | STD |  |  |  | 0 | 0 | 0 | 2010-08-23 |  | 2010-08-23 | Online | Gov't | Y
NSTAR | Barnstable | 1618 | 2601 | 131 | PV | 4-80B-514 | 2010-05-04 | 2010-06-08 | 25 | 25 | 0 | 2010-06-08 | 2010-08-18 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-08 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online | Private | Y
NSTAR | Westport | 1619 | 2790 | 11 | Wind | 2-523-523 | 2010-05-04 | 2010-06-08 | 25 | 25 | 0 | 2010-06-08 | 2010-08-18 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-08 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online | Private | Y
NSTAR | Westport | 1620 | 2790 | 11 | Wind | 2-523-523 | 2010-05-04 | 2010-06-08 | 25 | 25 | 0 | 2010-06-08 | 2010-08-18 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-08 |  | 2010-06-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-16 |  | 2010-09-16 | Online | Private | Y
NSTAR | Westport | 1621 | 2790 | 10 | Wind | 2-523-523 | 2010-05-07 | 2011-10-03 | 366 | 366 | 0 | 2011-10-03 | 2011-11-09 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-11 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-08-28 | 2013-08-28 | 2013-09-19 | Online | Gov't | N
NSTAR | Dartmouth | 1622 | 2747 | 2150 | Natural Gas | 2-525-525 | 2010-05-07 | 2010-05-11 | 2 | 2 | 0 | 2010-05-12 | 2010-06-22 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-22 |  | 2010-07-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-23 |  | 2010-11-23 | Online | Gov't | N
NSTAR | Boston | 1623 | 2119 | 242 | PV | 106-H4 | 2010-05-12 | 2010-05-25 | 9 | 9 | 0 | 2010-05-25 | 2010-06-22 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-23 |  | 2010-05-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-09-09 |  | 2010-09-09 | Online | Private | Y
NSTAR | Holliston | 1624 | 1746 | 50 | PV | 274-H3 | 2010-05-17 | 2010-05-26 | 7 | 7 | 0 | 2010-05-26 | 2010-06-15 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-06-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-24 |  | 2011-02-24 | Online | Private | Y
NSTAR | Hyannis | 1625 | 2601 | 25 | PV | 4-80B-523 | 2010-05-18 | 2010-05-25 | 5 | 5 | 0 | 2010-05-25 | 2010-06-24 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-25 |  | 2010-07-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-08-11 |  | 2010-08-11 | Online | Private | Y
NSTAR | West Roxbury | 1626 | 2132 | 37 | PV | 374-04 | 2010-05-21 | 2010-05-25 | 2 | 2 | 0 | 2010-05-25 | 2010-06-10 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-06-16 |  | 2010-07-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2010-08-13 |  | 2010-08-13 | Online | Private | Y
NSTAR | Yarmouth | 1627 | 2664 | 183 | PV | 4-64-558 | 2010-05-24 | 2010-05-26 | 2 | 2 | 0 | 2010-05-27 | 2010-06-30 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-01 |  | 2010-10-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-22 |  | 2011-05-04 | Online | Private | N
NSTAR | Boston | 1628 | 2118 | 177 | PV | 323-02 | 2010-05-27 | 2010-06-01 | 3 | 3 | 0 | 2010-06-01 | 2010-07-06 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-07 |  | 2010-08-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-03 | Online | Private | Y
NSTAR | Cambridge | 1629 | 2142 | 75 | Natural Gas | 875-1N35B | 2010-05-27 | 2010-06-02 | 4 | 4 | 0 | 2010-06-02 | 2010-07-06 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-08 |  | 2010-09-02 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-18 |  | 2010-11-18 | Online | Private | Y
NSTAR | Brighton | 1630 | 2135 | 75 | Natural Gas | 329-H7 | 2010-06-01 | 2010-06-03 | 2 | 2 | 0 | 2010-06-03 | 2010-07-07 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-09 |  | 2010-08-27 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-21 |  | 2011-06-21 | Online | Private | Y
NSTAR | Cambridge | 1631 | 2142 | 85 | Natural Gas | 875-1N39A | 2010-06-01 | 2010-06-04 | 3 | 3 | 0 | 2010-06-04 | 2010-07-29 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-04-07 | Online | Private | Y
NSTAR | New Bedford | 1632 | 2744 | 177 | PV | 2-6-17 | 2010-06-04 | 2010-07-26 | 36 | 36 | 0 | 2010-08-26 | 2010-10-15 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-01 |  | 2011-03-01 | Online | Gov't | Y
NSTAR | Cambridge | 1633 | 2140 | 41 | PV | 826-28 | 2010-06-09 | 2010-06-18 | 7 | 6 | 1 | 2010-06-18 | 2010-07-28 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-30 |  | 2010-08-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-14 |  | 2010-12-14 | Online | Gov't | Y
NSTAR | Acton | 1634 | 1720 | 60 | PV | 416-H4 | 2010-06-09 | 2010-06-10 | 1 | 0 | 1 | 2010-06-10 | 2010-07-14 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-11-30 | N/A | N/A |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Brewster | 1635 | 2631 | 1800 | Wind | 4-95B-600 | 2010-06-16 | 2010-08-13 | 42 | 42 | 0 | 2010-08-19 | 2011-01-28 | 116 | 0 | 116 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-28 |  |  | No | STD |  |  |  | 0 | 0 | 0 | 2011-02-17 |  | 2011-02-17 | Online | Private | N
NSTAR | Framingham | 1636 | 1701 | 2000 | Diesel | Sta 175 | 2010-06-16 | 2010-06-18 | 2 | 2 | 0 | 2010-06-18 | 2010-07-21 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-07-26 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-08 |  | 2010-11-10 | Online | Private | Y
NSTAR | Framingham | 1637 | 2030 | 110 | PV | 2410 | 2010-06-17 | 2010-06-25 | 6 | 6 | 0 | 2010-07-01 | 2010-08-18 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-13 |  | 2010-10-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-10-14 |  | 2011-10-14 | Online | Private | Y
NSTAR | Charlestown | 1638 | 2129 | 1500 | Wind | 387-148H1 | 2010-06-28 | 2010-07-02 | 4 | 4 | 0 | 2010-07-07 | 2010-08-20 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-23 |  | 2010-10-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-09 |  | 2011-11-01 | Online | Gov't | Y
NSTAR | Wellfleet | 1639 | 2667 | 52 | PV | 4-94B-653 | 2010-06-22 | 2010-07-16 | 18 | 19 | -1 | 2010-07-16 | 2010-08-30 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-09-01 | N/A | N/A |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Brewster | 1640 | 2631 | 1800 | Wind | 4-95B-600 | 2010-06-29 | 2010-07-06 | 5 | 5 | 0 | 2010-07-06 | 2010-08-10 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-13 |  | 2010-07-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-14 |  | 2010-10-14 | Online | Gov't | N
NSTAR | Dorchester | 1641 | 2125 | 197 | PV | 483-01 | 2010-06-29 | 2010-07-02 | 3 | 3 | 0 | 2010-10-01 |  | -28896 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-10-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Plymouth | 1642 | 2532 | 10000 | Wind | 221 | 2010-06-29 | 2010-07-02 | 3 | 3 | 0 | 2010-10-01 |  | -28896 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-10-01 | N/A | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Bourne | 1643 | 2532 | 15000 | Wind | 4-81A-81A | 2010-07-07 |  | -28834 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Boston | 1644 | 2116 | 195 | Natural Gas | 71-1N35 | 2010-07-09 | 2010-07-13 | 2 | 2 | 0 | 2010-07-13 | 2010-10-04 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-08 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-05 | Online | Private | Y
NSTAR | Mattapan | 1645 | 2126 | 38 | PV | 311-05 | 2010-07-09 | 2010-07-14 | 3 | 3 | 0 | 2010-07-14 | 2010-08-24 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-06 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-05 | Online | Private | Y
NSTAR | Mattapan | 1646 | 2126 | 14 | PV | 311-05 | 2010-07-09 | 2010-07-14 | 3 | 3 | 0 | 2010-07-14 | 2010-08-24 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-08 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-05 | Online | Private | Y
NSTAR | Mattapan | 1647 | 2126 | 15 | PV | 311-05 | 2010-07-13 | 2010-07-22 | 7 | 7 | 0 | 2010-07-22 | 2010-09-10 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-06 |  | 2010-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-01-31 |  | 2012-01-31 | Online | Gov't | N
NSTAR | Hyannis | 1648 | 2601 | 766 | PV | 4-80B-523 | 2010-07-14 | 2010-07-28 | 10 | 10 | 0 | 2010-08-02 | 2010-09-10 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-24 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-19 |  | 2012-01-31 | Online | Gov't | Y
NSTAR | Dennis | 1649 | 2660 | 30 | PV | 4-92B-92B | 2010-07-14 | 2010-07-29 | 11 | 11 | 0 | 2010-07-30 | 2010-10-12 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-09-24 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-19 |  | 2011-01-21 | Online | Private | Y
NSTAR | Dennis | 1650 | 2660 | 82 | PV | 4-92B-92B | 2010-07-15 | 2010-08-05 | 15 | 14 | 1 | 2010-08-05 | 2010-10-14 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-14 |  | 2010-09-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2010-12-06 |  | 2010-12-06 | Online | Private | Y
NSTAR | North Dartmouth | 1651 | 2747 | 1650 | Wind | 2-53-65 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  | Y
NSTAR | Chelsea | 1652 | 2150 | 175 | PV | 488-H2 | 2010-07-19 | 2010-08-30 | 30 | 30 | 0 | 2010-08-31 | 2010-12-14 | 75 | 0 | 75 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-16 |  | 2010-07-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2011-02-08 | Online | Gov't | Y
NSTAR | Norfolk | 1653 | 2056 | 82 | PV | 146-H9 | 2010-07-19 | 2010-08-06 | 14 | 14 | 0 | 2010-08-09 | 2010-09-16 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-03 |  | 2010-07-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-06-12 |  | 2011-07-14 | Online | Gov't | N
NSTAR | Walpole | 1654 | 2081 | 95 | PV | 146-H4 | 2010-07-19 | 2010-08-06 | 14 | 14 | 0 | 2010-08-09 | 2010-10-04 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-22 |  | 2010-07-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-16 |  | 2011-03-21 | Online | Gov't | Y
NSTAR | Norfolk | 1655 | 2056 | 142 | PV | 146-H2 | 2010-07-23 | 2010-08-13 | 15 | 15 | 0 | 2010-08-18 | 2010-09-23 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-22 |  | 2010-11-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-02-08 |  | 2012-02-08 | Online | Gov't | Y
NSTAR | Kingston | 1656 | 2364 | 6000 | Wind | 3-17-913 | 2010-07-27 | 2010-08-17 | 15 | 14 | 1 | 2010-08-17 | 2010-10-01 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-05 |  | 2010-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-10-28 | Online | Gov't | Y
NSTAR | Wellfleet | 1657 | 2667 | 28 | PV | 4-96-677 | 2010-07-29 | 2010-08-17 | 13 | 13 | 0 | 2010-08-17 | 2010-10-14 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-19 |  | 2010-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-02-18 |  | 2011-02-18 | Online | Private | Y
NSTAR | Walpole | 1658 | 2081 | 28 | PV | 2-105-105 | 2010-07-30 | 2010-08-17 | 12 | 12 | 0 | 2010-08-17 | 2010-10-01 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-05 |  | 2010-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-10-29 | Online | Private | Y
NSTAR | New Bedford | 1659 | 2745 | 16 | PV | 2-105-105 | 2010-08-02 | 2010-08-16 | 10 | 10 | 0 | 2010-08-16 | 2010-10-06 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-08 |  | 2010-08-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-02 | Online | Private | Y
NSTAR | Westport | 1660 | 2791 | 7 | PV | 2-523-523 | 2010-08-01 | 2010-08-13 | 10 | 7 | 3 | 2010-08-16 | 2010-10-06 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-08-16 |  | 2010-08-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-11-16 | Online | Private | Y
NSTAR | Edgartown | 1661 | 2539 | 42 | PV | 4-99-223 | 2010-08-03 | 2010-08-12 | 7 | 5 | 2 | 2010-08-18 | 2010-10-06 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-13 |  | 2010-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-12-01 | Online | Gov't | Y
NSTAR | South Dennis | 1662 | 2660 | 100 | Wind | 4-92B-92B | 2010-08-06 | 2010-08-19 | 9 | 5 | 4 | 2010-08-19 | 2010-09-21 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-14 |  | 2010-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-05-01 |  | 2012-05-01 | Online | Gov't | N
NSTAR | Fairhaven | 1663 | 2719 | 1500 | Wind | 2-220-220 | 2010-08-06 | 2010-08-13 | 5 | 1 | 4 | 2010-08-18 | 2010-09-21 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-14 |  | 2010-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-05-03 |  | 2012-05-01 | Online | Gov't | N
NSTAR | Fairhaven | 1664 | 2719 | 1500 | Wind | 2-220-220 | 2010-08-17 | 2010-08-25 | 6 | 5 | 1 | 2010-08-26 | 2010-10-27 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-31 |  | 2012-05-03 | Online | Gov't | Y
NSTAR | Hopkinton | 1665 | 1748 | 36 | PV | 65-H7 | 2010-08-18 | 2010-08-27 | 7 | 6 | 1 | 2010-08-27 | 2010-10-01 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-16 |  | 2010-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-05 |  | 2011-01-19 | Online | Private | Y
NSTAR | Woburn | 1666 | 1801 | 60 | PV | 375-H11 | 2010-08-20 | 2010-09-01 | 8 | 8 | 0 | 2010-09-01 | 2010-10-06 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-13 |  | 2010-10-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-04-27 | Online | Private | Y
NSTAR | Jamaica Plain | 1667 | 2130 | 75 | PV | 350-H2 | 2010-08-23 | 2011-08-01 | 245 | 245 | 0 | 2011-08-01 | 2011-09-06 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-07 |  | 2010-08-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-02-24 | Online | Gov't | Y
NSTAR | Cambridge | 1668 | 2139 | 30 | PV | 819-1NB2 | 2010-08-20 | 2010-09-15 | 18 | 17 | 1 | 2010-09-15 | 2010-10-14 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2012-12-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Bourne | 1669 | 2532 | 2000 | Wind | 4-81A-81A | 2010-08-24 | 2010-08-30 | 4 | 4 | 0 | 2010-09-01 | 2010-10-21 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-22 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-24 |  | 2011-03-25 | Online | Private | Y
NSTAR | Mattapoisett | 1670 | 2739 | 164 | PV | 2-304-304 | 2010-08-24 | 2010-08-26 | 2 | 2 | 0 | 2010-08-26 | 2010-10-01 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-05 |  | 2010-08-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-10-21 | Online | Private | Y
NSTAR | Fairhaven | 1671 | 2719 | 100 | PV | 2-220-201 | 2010-08-24 | 2010-08-26 | 2 | 2 | 0 | 2010-08-26 | 2010-10-06 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-02 |  | 2010-11-01 | No | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-05-29 | Online | Private | N
NSTAR | Dartmouth | 1672 | 2747 | 1000 | PV | 2-532-532 | 2010-08-26 | 2010-09-02 | 5 | 4 | 1 | 2010-09-02 | 2010-11-29 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-30 |  | 2010-10-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-29 |  | 2012-05-25 | Online | Private | Y
NSTAR | Cambridge | 1673 | 2138 | 75 | PV | 828-1104H1 | 2010-09-09 | 2010-09-17 | 6 | 5 | 1 | 2010-09-17 | 2010-10-21 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-25 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-03-10 | Online | Gov't | Y
NSTAR | Edgartown | 1674 | 2539 | 15 | PV | 4-99-99 | 2010-09-13 | 2010-09-22 | 7 | 7 | 0 | 2011-01-24 | 2011-03-25 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-25 |  | 2010-03-28 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-05-19 | Online | Private | Y
NSTAR | Vineyard Haven | 1675 | 2568 | 72 | PV | 4-91-222 | 2010-09-10 |  | -28881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Wareham | 1676 | 2571 | 11500 | Wind | 3-83-966 | 2010-09-10 |  | -28881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Wareham | 1677 | 2571 | 4600 | Wind | 3-85-928 | 2010-09-10 |  | -28881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Wareham | 1678 | 2571 | 2300 | Wind | 3-83-966 | 2010-09-15 | 2010-09-20 | 3 | 2 | 1 | 2010-09-20 | 2010-10-20 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-22 |  | 2010-11-03 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-23 |  | 2010-12-23 | Online | Private | Y
NSTAR | Hopkinton | 1679 | 1748 | 20 | PV | 126-H1 | 2010-09-15 | 2010-09-22 | 5 | 4 | 1 | 2010-09-22 | 2010-10-14 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-19 |  | 2010-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-15 |  | 2010-12-15 | Online | Gov't | Y
NSTAR | Watertown | 1680 | 2742 | 50 | PV | 467-H4 | 2010-09-21 | 2010-09-28 | 5 | 4 | 1 | 2010-10-04 | 2010-11-10 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-19 |  | 2010-09-08 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-11-30 |  | 2010-11-30 | Online | Private | Y
NSTAR | Falmouth | 1681 | 2540 | 75 | PV | 4-72-72 | 2010-09-21 | 2010-09-28 | 5 | 4 | 1 | 2010-10-04 | 2010-11-15 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-16 |  | 2010-09-08 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-02 |  | 2010-12-02 | Online | Gov't | Y
NSTAR | Acusnet | 1682 | 2743 | 20 | PV | 2-241-237 | 2010-09-21 | 2010-09-28 | 5 | 3 | 2 | 2010-10-04 | 2010-11-22 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-22 |  | 2010-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2010-12-08 | Online | Private | Y
NSTAR | North Falmouth | 1683 | 2556 | 43 | PV | 4-78-420 | 2010-09-20 | 2010-09-30 | 8 | 2 | 6 | 2010-10-01 | 2010-11-05 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-09 |  | 2010-10-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-25 |  | 2011-02-02 | Online | Private | Y
NSTAR | Dartmouth | 1684 | 2748 | 95 | PV | 2-524-524 | 2010-09-27 | 2010-10-14 | 13 | 9 | 4 | 2010-10-14 | 2010-12-03 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-15 |  | 2010-10-25 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-03-10 |  | 2011-03-10 | Online | Private | Y
NSTAR | Dartmouth | 1685 | 2790 | 70 | PV | 2-523-523 | 2010-09-22 | 2010-10-01 | 7 | 2 | 5 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online | Private | Y
NSTAR | South Dartmouth | 1686 | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | 7 | 2 | 5 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online | Private | Y
NSTAR | South Dartmouth | 1687 | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | 7 | 2 | 5 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online | Private | Y
NSTAR | South Dartmouth | 1689 | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | 7 | 2 | 5 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online | Private | Y
NSTAR | South Dartmouth | 1690 | 2748 | 14 | PV | 2-53-65 | 2010-09-22 | 2010-10-01 | 7 | 2 | 5 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online | Private | Y
NSTAR | South Dartmouth | 1691 | 2748 | 14 | PV | 2-53-65 | 2010-09-24 | 2010-11-02 | 27 | 23 | 4 | 2010-11-02 | 2010-12-16 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-29 |  | 2011-11-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-11-08 |  | 2011-11-08 | Online | Gov't | N
NSTAR | Bourne | 1692 | 2542 | 3000 | Wind | 3-88-923 | 2010-09-28 | 2010-10-01 | 3 | 0 | 3 | 2010-10-25 | 2010-12-02 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-03 |  | 2010-09-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-12-21 |  | 2010-12-21 | Online | Gov't | Y
NSTAR | South Dartmouth | 1693 | 2748 | 17 | PV | 2-53-65 | 2010-09-27 | 2010-10-14 | 13 | 9 | 4 | 2010-10-15 | 2010-11-22 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-08 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-01-04 |  | 2011-01-04 | Online | Private | Y
NSTAR | Needham | 1694 | 2492 | 15 | PV | 148-H1 | 2010-10-01 | 2010-10-19 | 12 | 11 | 1 | 2010-10-20 | 2010-12-08 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-09 |  | 2011-01-30 | Yes | STD |  |  |  | 0 | 0 | 0 | 2011-08-22 |  | 2011-09-08 | Online | Private | Y
NSTAR | Canton | 1695 | 2021 | 261.45 | PV | 470-H4 | 2010-10-01 | 2010-10-18 | 11 | 10 | 1 | 2010-10-20 | 2011-01-04 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-04 |  | 2010-10-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-03-10 |  | 2011-09-01 | Online | Private | Y
NSTAR | Plymouth | 1696 | 2360 | 95 | PV | 3-14-911 | 2010-10-07 | 2010-10-20 | 9 | 4 | 5 | 2010-10-20 | 2010-12-23 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-23 |  | 2010-10-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-07 |  | 2011-04-08 | Online | Private | Y
NSTAR | Falmouth | 1697 | 2536 | 95 | PV | 4-98A-98A | 2010-10-01 | 2010-10-22 | 15 | 13 | 2 | 2010-10-22 | 2011-02-22 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-11-29 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Hopkinton | 1698 | 1748 | 2250 | Natural Gas | 455-H3 | 2010-09-01 | 2010-11-12 | 52 | 26 | 26 | 2010-11-18 | 2010-12-23 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-11-02 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dorchester | 1700 | 2122 | 65 | Natural Gas | 466-1482H1 | 2009-10-01 | 2010-11-09 | 288 | 19 | 269 | 2010-11-09 | 2010-12-08 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-13 |  | 2010-11-01 | No | STD |  |  |  | 0 | 0 | 0 | 2011-03-04 |  | 2011-03-07 | Online | Gov't | N
NSTAR | Boston | 1701 | 2222 | 28 | PV | 2-1N43 | 2010-10-18 | 2010-10-19 | 1 | 1 | 0 | 2010-10-19 | 2010-10-29 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-10-25 |  | 2010-10-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2010-10-21 |  | 2010-10-25 | Online | Private | Y
NSTAR | Fairhaven | 1702 | 2719 | 30 | PV | 2-220-201 | 2010-10-15 | 2010-10-25 | 6 | 4 | 2 | 2010-10-26 | 2010-12-22 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2010-12-01 | Yes | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Milton | 1703 | 2186 | 2000 | Wind | 362-02 | 2010-10-07 |  | -28900 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Cambridge | 1705 | 2139 | 1500 | Natural Gas | 813-36 | 2010-10-18 | 2011-04-04 | 120 | 118 | 2 | 2011-04-04 | 2011-05-11 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-07 | Online | Gov't | Y
NSTAR | East Boston | 1706 | 2128 | 82 | PV | 592-72XY | 2010-10-20 | 2010-11-04 | 11 | 9 | 2 | 2010-11-08 | 2010-12-16 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-20 |  | 2010-11-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-02-14 | Online | Private | Y
NSTAR | Dartmouth | 1707 | 2747 | 33 | PV | 2-543-543 | 2010-10-24 | 2010-11-16 | 17 | 16 | 1 | 2010-11-16 | 2010-11-29 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-22 |  | 2010-11-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-06-28 | Online | Private | Y
NSTAR | Framingham | 1708 | 1701 | 500 | PV | 433-H4 | 2010-10-26 | 2010-10-28 | 2 | 0 | 2 | 2010-11-08 | 2010-11-24 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-11-29 |  | 2010-10-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Charlestown | 1709 | 2129 | 30 | Wind | 287-148H1 | 2010-10-27 | 2010-11-23 | 19 | 17 | 2 | 2010-11-23 | 2011-01-21 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-31 |  | 2010-11-25 | No | STD |  |  |  | 0 | 0 | 0 | 2011-09-22 |  | 2011-09-30 | Online | Gov't | N
NSTAR | Boston | 1710 | 2108 | 16 | PV | 2-1N45 | 2010-10-27 | 2010-11-09 | 9 | 5 | 4 | 2010-11-09 | 2010-12-07 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2010-12-09 |  | 2011-01-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-15 |  | 2011-06-15 | Online | Private | Y
NSTAR | Cambridge | 1711 | 2138 | 250 | PV | 828-1104H1 | 2010-11-02 | 2010-11-10 | 6 | 5 | 1 | 2010-11-18 | 2010-12-16 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 |  | 2011-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2011-06-16 | Online | Gov't | N
NSTAR | Dennis | 1712 | 2660 | 1250 | PV | 4-92B-92B | 2010-11-08 | 2010-11-19 | 9 | 8 | 1 | 2010-11-23 | 2011-01-14 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-20 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-05-25 |  | 2011-05-25 | Online | Gov't | Y
NSTAR | Chilmark | 1713 | 2535 | 88 | PV | 4-97-226 | 2010-11-10 | 2010-11-16 | 4 | 1 | 3 | 2010-11-19 | 2010-12-20 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2010-11-26 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-03-21 |  | 2013-03-21 | Online | Gov't | N
NSTAR | Fairhaven | 1714 | 2719 | 577.28 | PV | 2-222-222 | 2010-11-12 | 2010-12-02 | 14 | 13 | 1 | 2010-12-03 | 2011-02-03 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-21 | Online | Private | N
NSTAR | Boston | 1715 | 2134 | 75 | Natural Gas | 329-H1 | 2010-11-10 | 2010-11-19 | 7 | 4 | 3 | 2010-11-23 | 2010-12-23 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-19 | 2011-04-19 | 2011-04-21 | Online | Private | Y
NSTAR | Framingham | 1716 | 1701 | 50 | PV | 342-H4 | 2010-11-15 | 2010-11-22 | 5 | 2 | 3 | 2010-11-24 | 2010-12-16 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-05 |  | 2010-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Weston | 1717 | 2493 | 300 | PV | 282-H3 | 2010-11-16 | 2010-11-24 | 6 | 3 | 3 | 2010-11-30 | 2011-01-21 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-28 |  | 2011-01-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-19 |  |  | Withdrawn | Private | Y
NSTAR | Boston | 1718 | 2210 | 125 | PV | 385-H10 | 2010-11-16 | 2010-11-24 | 6 | 3 | 3 | 2010-11-30 | 2010-12-23 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-28 |  | 2011-01-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-19 |  | 2012-03-21 | Decommissioned | Private | Y | 2021-12-29
NSTAR | Boston | 1719 | 2210 | 200 | PV | 385-H5 | 2010-11-16 | 2010-11-24 | 6 | 2 | 4 | 2010-11-30 | 2011-01-03 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-04 |  | 2011-01-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-19 |  | 2012-03-21 | Decommissioned | Private | Y | 2021-12-29
NSTAR | Boston | 1720 | 2210 | 200 | PV | 385-H15 | 2010-11-18 | 2010-12-06 | 12 | 10 | 2 | 2010-12-07 | 2010-12-28 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-26 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-06-08 | Decommissioned | Private | Y | 2021-12-29
NSTAR | Brewster | 1721 | 2170 | 10 | Wind | 4-89B-576 | 2010-11-19 | 2010-12-03 | 10 | 9 | 1 | 2010-12-03 | 2011-02-04 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-07 |  | 2010-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-03-21 | Online | Private | Y
NSTAR | Hyannis | 1722 | 2601 | 43 | PV | 4-80B-80B | 2010-12-01 | 2010-12-13 | 8 | 7 | 1 | 2010-12-13 | 2011-01-12 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-14 |  | 2010-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-27 |  | 2011-05-27 | Online | Private | Y
NSTAR | Cambridge | 1723 | 2141 | 28 | PV | 820-15 | 2010-12-07 | 2010-12-15 | 6 | 3 | 3 | 2010-12-16 | 2011-02-10 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-16 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-20 |  | 2011-05-04 | Online | Private | Y
NSTAR | Dorchester | 1724 | 2122 | 100 | PV | 466-1482H1 | 2010-12-03 | 2010-12-15 | 8 | 3 | 5 | 2010-12-16 | 2011-02-02 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Milton | 1725 | 2186 | 26 | PV | 496-H7 | 2010-12-13 | 2010-12-21 | 6 | 5 | 1 | 2010-12-22 | 2011-04-23 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-08-03 |  | 2012-08-03 | Online | Gov't | N
NSTAR | Canton | 1726 | 2021 | 950 | PV | 470-H8 | 2010-12-13 | 2010-12-21 | 6 | 5 | 1 | 2010-12-22 | 2011-04-23 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online | Gov't | N
NSTAR | Canton | 1727 | 2021 | 950 | PV | 470-H8 | 2010-12-13 | 2010-12-21 | 6 | 5 | 1 | 2010-12-22 | 2011-04-23 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online | Gov't | N
NSTAR | Canton | 1728 | 2021 | 950 | PV | 470-H4 | 2010-12-13 | 2010-12-21 | 6 | 5 | 1 | 2010-12-22 | 2011-04-23 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online | Gov't | N
NSTAR | Canton | 1729 | 2021 | 950 | PV | 470-H4 | 2010-12-13 | 2010-12-21 | 6 | 5 | 1 | 2010-12-22 | 2011-04-23 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  | 2010-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-03 | Online | Gov't | N
NSTAR | Canton | 1730 | 2021 | 950 | PV | 470-H4 | 2010-12-15 | 2011-01-06 | 16 | 16 | 0 | 2011-01-07 | 2011-02-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2012-08-03 | Online | Gov't | N
NSTAR | Dartmouth | 1731 | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | 16 | 16 | 0 | 2011-01-07 | 2011-02-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online | Gov't | N
NSTAR | Dartmouth | 1732 | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | 16 | 16 | 0 | 2011-01-07 | 2011-02-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online | Gov't | N
NSTAR | Dartmouth | 1733 | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | 16 | 16 | 0 | 2011-01-07 | 2011-02-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online | Gov't | N
NSTAR | Dartmouth | 1734 | 2747 | 60 | PV | 2-525-525 | 2010-12-15 | 2011-01-06 | 16 | 16 | 0 | 2011-01-07 | 2011-02-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-02 |  | 2010-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-14 |  | 2011-09-06 | Online | Gov't | N
NSTAR | Dartmouth | 1735 | 2747 | 82 | PV | 2-525-525 | 2010-12-15 | 2010-12-21 | 4 | 1 | 3 | 2010-12-21 | 2011-01-25 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-28 |  | 2011-03-11 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-17 |  | 2011-08-18 | Online | Private | N
NSTAR | Ashland | 1736 | 1721 | 500 | PV | 274-H1 | 2010-12-20 | 2011-01-05 | 12 | 11 | 1 | 2011-01-05 | 2011-02-18 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-08-30 | Online | Gov't | Y
NSTAR | Framingham | 1737 | 1701 | 82 | PV | 455-H5 | 2010-12-20 | 2011-01-05 | 12 | 11 | 1 | 2011-01-05 | 2011-02-02 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-02-08 |  | 2010-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-08-30 | Online | Gov't | Y
NSTAR | Framingham | 1738 | 1701 | 26 | PV | 455-H5 | 2010-12-20 | 2011-01-26 | 27 | 25 | 2 | 2011-01-26 | 2011-03-01 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-03 |  | 2011-04-21 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-12-29 |  | 2011-12-29 | Online | Private | Y
NSTAR | Chilmark | 1739 | 2535 | 68 | Wind | 4-97-226 | 2010-12-21 | 2011-01-04 | 10 | 6 | 4 | 2011-01-04 | 2011-02-28 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-01 |  | 2011-01-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-06-09 |  | 2011-06-09 | Online | Gov't | Y
NSTAR | Yarmouth | 1740 | 2664 | 266 | PV | 4-92B-563 | 2010-12-29 | 2011-01-13 | 11 | 9 | 2 | 2011-01-13 | 2011-03-25 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-29 |  | 2011-02-25 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-07-18 |  |  |  | Private | Y
NSTAR | East Falmouth | 1741 | 2536 | 97 | PV | 4-98A-98A | 2011-01-03 | 2011-01-04 | 1 | 1 | 0 | 2011-01-04 | 2011-01-11 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-01-13 |  | 2011-03-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-10 |  | 2013-01-03 | Online | Gov't | Y
NSTAR | Orleans | 1742 | 2653 | 16 | PV | 4-94A-633 | 2011-01-05 | 2011-01-13 | 6 | 4 | 2 | 2011-01-13 | 2011-02-28 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-01 |  | 2011-02-25 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-05-11 |  | 2011-05-11 | Online | Private | Y
NSTAR | Mattapoisett | 1743 | 2739 | 60 | PV | 2-301-301 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-17 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online | Gov't | Y
NSTAR | New Bedford | 1744 | 2740 | 88 | PV | 2-38-38 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online | Gov't | Y
NSTAR | New Bedford | 1745 | 2740 | 14 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online | Gov't | Y
NSTAR | New Bedford | 1746 | 2740 | 42 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online | Gov't | Y
NSTAR | New Bedford | 1747 | 2740 | 28 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online | Gov't | Y
NSTAR | New Bedford | 1748 | 2740 | 28 | PV | 2-6-10 | 2010-12-27 | 2011-03-08 | 51 | 42 | 9 | 2011-03-09 | 2011-04-27 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-27 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online | Gov't | Y
NSTAR | New Bedford | 1749 | 2740 | 56 | PV | 2-6-10 | 2011-01-07 | 2011-03-01 | 37 | 36 | 1 | 2011-03-01 | 2011-03-02 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-29 |  | 2011-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-12 |  | 2011-05-12 | Online | Private | Y
NSTAR | Roxbury | 1750 | 2119 | 75 | PV | 483-H3 | 2011-01-07 | 2011-03-22 | 52 | 51 | 1 | 2011-03-22 | 2011-04-06 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-07 |  | 2011-03-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-24 |  | 2012-05-24 | Online | Private | Y
NSTAR | Plymouth | 1751 | 2360 | 49 | PV | 3-13-936 | 2011-01-17 | 2011-01-28 | 9 | 8 | 1 | 2011-01-28 | 2011-03-15 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-18 |  | 2011-02-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-07-22 | Online | Private | Y
NSTAR | Brighton | 1752 | 2135 | 14 | PV | 315-H5 | 2011-01-14 |  | -28971 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 1753 | 2747 | 600 | Wind | 2-525-525 | 2011-01-20 | 2011-02-01 | 8 | 7 | 1 | 2011-02-01 | 2011-03-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-18 |  | 2011-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2011-08-02 | Online | Gov't | Y
NSTAR | Dedham | 1754 | 2026 | 26 | PV | 20-H1 | 2011-01-21 | 2011-01-25 | 2 | 1 | 1 | 2011-01-25 | 2011-04-01 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-05-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2011-08-02 | Online | Gov't | N
NSTAR | Dedham | 1755 | 2026 | 120 | PV | 20-H5 | 2011-01-21 | 2011-02-08 | 12 | 8 | 4 | 2011-02-08 | 2011-03-14 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-18 |  | 2011-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-30 |  | 2012-05-30 | Online | Private | N
NSTAR | Cambridge | 1756 | 2139 | 150 | Natural Gas | 831-1324 | 2011-01-24 | 2011-02-01 | 6 | 3 | 3 | 2011-02-01 | 2011-04-14 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-15 |  | 2011-02-20 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-05-31 |  | 2011-05-31 | Online | Private | Y
NSTAR | Hyannis | 1757 | 2601 | 82 | PV | 4-63-521 | 2011-01-31 | 2011-08-16 | 141 | 140 | 1 | 2011-08-16 | 2011-11-18 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-21 |  | 2011-03-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2012-06-27 | Online | Private | Y
NSTAR | Roslindale | 1759 | 2131 | 26 | PV | 13-H1 | 2011-02-01 | 2011-02-11 | 8 | 6 | 2 | 2011-02-11 | 2011-04-05 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-06 |  | 2011-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-03 |  | 2011-08-04 | Online | Private | Y
NSTAR | Assonett | 1760 | 2702 | 11 | PV | 2-605-605 | 2011-02-03 | 2011-03-16 | 29 | 29 | 0 | 2011-03-16 | 2011-03-25 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-30 |  | 2011-04-30 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-11-16 | Online | Private | N
NSTAR | Edgartown | 1761 | 2539 | 55 | Wind | 4-97-97 | 2011-02-03 | 2011-02-07 | 2 | 1 | 1 | 2011-02-07 | 2011-03-31 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-01 |  | 2011-04-29 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-04-28 |  | 2011-05-04 | Online | Private | Y
NSTAR | Chelsea | 1762 | 2150 | 39 | PV | 488-H2 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 343 | 0 | 343 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-04-30 | Online | Gov't | N
NSTAR | Dartmouth | 1763 | 2747 | 4560 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 343 | 0 | 343 |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Dartmouth | 1764 | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 343 | 0 | 343 |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Dartmouth | 1765 | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 343 | 0 | 343 |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Dartmouth | 1766 | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 343 | 0 | 343 |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Dartmouth | 1767 | 2747 | 1000 | PV | 2-525-525 | 2011-02-10 | 2011-02-14 | 2 | 0 | 2 | 2011-02-14 | 2011-04-28 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-26 | 2012-07-25 | 343 | 0 | 343 |  |  | 0 | 0 | 0 |  |  | 2012-05-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Dartmouth | 1768 | 2747 | 1000 | PV | 2-525-525 | 2011-02-11 | 2011-02-28 | 11 | 10 | 1 | 2011-02-28 | 2011-04-07 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-06-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-12-28 |  |  | Withdrawn | Gov't | Y
NSTAR | Cambridge | 1769 | 2139 | 82 | PV | 831-1324 | 2011-02-14 | 2011-03-07 | 15 | 14 | 1 | 2011-03-07 | 2011-04-20 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-09 |  | 2011-05-21 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2013-01-24 | Online | Private | Y
NSTAR | Milton | 1770 | 2186 | 200 | PV | 4306 | 2011-02-11 | 2011-02-28 | 11 | 9 | 2 | 2011-02-28 | 2011-03-25 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-04-30 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-05-17 |  | 2011-06-07 | Online | Private | Y
NSTAR | Jamaica Plain | 1771 | 2130 | 30 | PV | 396-01 | 2011-02-17 | 2011-04-22 | 46 | 45 | 1 | 2011-04-22 | 2011-06-22 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-14 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-31 |  | 2012-07-31 | Online | Private | Y
NSTAR | Wareham | 1772 | 2571 | 875 | PV | 3-86-966 | 2011-02-24 | 2011-03-16 | 14 | 13 | 1 | 2011-03-16 | 2011-04-20 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-22 |  | 2011-03-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-20 |  | 2012-07-31 | Online | Private | Y
NSTAR | Brewster | 1773 | 2631 | 15 | PV | 4-89B-577 | 2011-02-24 |  | -29000 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Brewster | 1774 | 2631 | 2 | PV | 4-89B-577 | 2011-02-24 | 2011-03-16 | 14 | 13 | 1 | 2011-03-16 | 2011-03-28 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-03-31 |  | 2011-03-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-20 |  | 2011-05-20 | Online | Private | Y
NSTAR | Brewster | 1775 | 2631 | 21 | PV | 4-89B-577 | 2011-03-03 | 2011-03-07 | 2 | 1 | 1 | 2011-03-07 | 2011-05-24 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Kingston | 1776 | 2364 | 1000 | PV | 3-17-913 | 2011-03-07 | 2011-03-07 | 0 | 0 | 0 | 2011-03-07 | 2011-04-28 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-31 |  | 2011-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-02-06 |  |  | Withdrawn | Gov't | N
NSTAR | Dartmouth | 1777 | 2748 | 1000 | PV | 2-528-528 | 2011-03-08 | 2011-04-15 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Chatham | 1778 | 2633 | 31 | PV | 4-95A-608 | 2011-03-10 | 2011-04-15 | 26 | 25 | 1 | 2011-04-15 | 2011-06-14 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-02 |  | 2011-06-03 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-06 |  | 2012-07-06 | Online | Private | Y
NSTAR | Stoneham | 1779 | 2180 | 72 | PV | 375-H7 | 2011-03-10 | 2011-05-12 | 45 | 44 | 1 | 2011-05-13 | 2011-07-08 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-11 |  | 2011-05-21 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-01-28 |  | 2013-01-28 | Online | Private | Y
NSTAR | Somerville | 1780 | 2143 | 120 | PV | 250-1N39H1 | 2011-03-10 | 2011-04-28 | 35 | 34 | 1 | 2011-04-28 | 2011-06-16 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-21 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-19 |  | 2012-06-19 | Online | Private | Y
NSTAR | Ashland | 1781 | 1721 | 30 | PV | 519-175H1 | 2011-03-15 | 2011-09-26 | 139 | 139 | 0 | 2011-09-26 | 2011-10-28 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-28 |  | 2011-07-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Bedford | 1782 | 1730 | 51 | PV | 592-70H | 2011-03-15 | 2011-03-18 | 3 | 2 | 1 | 2011-03-18 | 2011-04-29 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-06 |  | 2011-12-08 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-08-02 |  | 2012-08-02 | Online | Gov't | N
NSTAR | Dartmouth | 1783 | 2747 | 600 | Wind | 2-525-525 | 2011-03-21 | 2011-03-21 | 0 | 0 | 0 | 2011-03-21 | 2011-03-30 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-04-05 |  | 2011-04-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-07-01 | Online | Private | Y
NSTAR | West Dennis | 1784 | 2670 | 30 | PV | 4-92B-571 | 2011-03-28 | 2011-04-06 | 7 | 5 | 2 | 2011-04-06 | 2011-06-03 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-10 |  | 2011-05-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-09-13 |  | 2011-09-16 | Online | Private | N
NSTAR | Medway | 1785 | 2053 | 350 | PV | 65-H3 | 2011-03-30 | 2011-04-29 | 22 | 20 | 2 | 2011-04-29 | 2011-06-16 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-22 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-29 |  | 2011-09-13 | Online | Gov't | Y
NSTAR | Acton | 1787 | 1720 | 24 | PV | 416-H2 | 2011-04-01 | 2011-04-12 | 7 | 5 | 2 | 2011-04-12 | 2011-05-11 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2011-12-27 | Online | Private | Y
NSTAR | Acton | 1788 | 1720 | 142 | PV | 416-H5 | 2011-04-01 | 2011-04-08 | 5 | 3 | 2 | 2011-04-08 | 2011-05-17 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-17 |  | 2011-04-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-05-18 |  | 2011-09-07 | Online | Gov't | Y
NSTAR | Milton | 1789 | 2186 | 60 | PV | 362-05 | 2011-04-05 | 2011-05-06 | 23 | 23 | 0 | 2011-05-09 | 2011-06-29 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-06 |  | 2011-05-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-07-22 | Online | Private | Y
NSTAR | Canton | 1790 | 2021 | 100 | PV | 470-H7 | 2011-04-08 | 2011-04-12 | 2 | 1 | 1 | 2011-04-12 | 2011-05-16 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-12 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-07 | Online | Gov't | Y
NSTAR | East Boston | 1791 | 2128 | 345 | PV | 592-72XY | 2011-04-08 | 2011-10-27 | 144 | 142 | 2 | 2011-10-28 | 2011-12-06 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-07 |  | 2011-10-10 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-12 |  |  |  | Private | Y
NSTAR | Jamaica Plain | 1792 | 2130 | 30 | PV | 284-1360H2 | 2011-04-12 | 2011-04-15 | 3 | 2 | 1 | 2011-04-15 | 2011-05-18 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-23 |  | 2011-06-17 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-08-25 |  | 2011-08-25 | Online | Private | Y
NSTAR | Sherborn | 1793 | 1770 | 16 | PV | 240-H1 | 2011-04-20 | 2011-08-24 | 90 | 89 | 1 | 2011-08-24 | 2012-03-12 | 141 | 0 | 141 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-03 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Private | N | 2011-10-03
NSTAR | Charlestown | 1794 | 2129 | 250 | Natural Gas | 250-H3 | 2011-04-25 | 2011-04-27 | 2 | 1 | 1 | 2011-05-02 | 2011-06-03 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-15 |  | 2011-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-11-17 | Online | Private | Y
NSTAR | Brookline | 1796 | 2446 | 75 | Natural Gas | 350-H12 | 2011-04-27 | 2011-05-19 | 16 | 15 | 1 | 2011-05-19 | 2011-07-13 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-08 |  | 2011-09-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-08-03 |  | 2012-08-08 | Online | Gov't | N
NSTAR | Fairhaven | 1797 | 2719 | 100 | Conditioned Digester Gas | 2-221-221 | 2011-04-25 | 2011-05-31 | 26 | 23 | 3 | 2011-05-31 | 2011-07-11 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-12 |  | 2011-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-23 | Online | Gov't | Y
NSTAR | Mashpee | 1798 | 2649 | 270 | PV | 4-77A-454 | 2011-04-27 | 2011-05-13 | 12 | 10 | 2 | 2011-05-13 | 2011-06-29 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-23 |  | 2012-05-23 | Online | Private | Y
NSTAR | Dedham | 1799 | 2026 | 100 | PV | 344-07 | 2011-04-27 | 2011-05-12 | 11 | 9 | 2 | 2011-05-13 | 2011-06-29 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-26 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-29 | Online | Private | Y
NSTAR | Jamaica Plain | 1800 | 2130 | 100 | PV | 496-H4 | 2011-04-29 | 2011-05-12 | 9 | 8 | 1 | 2011-05-13 | 2011-09-28 | 98 | 0 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-17 |  | 2011-05-21 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-01-18 |  | 2013-01-18 | Online | Private | Y
NSTAR | Dedham | 1802 | 2026 | 250 | PV | 20-H8 | 2011-04-29 | 2011-05-12 | 9 | 7 | 2 | 2011-05-13 | 2011-06-29 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-05-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Marshfield | 1803 | 2050 | 100 | PV | 3-24-915 | 2011-05-03 | 2011-05-10 | 5 | 2 | 3 | 2011-05-10 | 2011-06-13 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-13 |  | 2011-06-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-11-29 | Online | Private | Y
NSTAR | Dorchester | 1804 | 2125 | 250 | PV | 106-H2 | 2011-05-03 | 2011-05-09 | 4 | 1 | 3 | 2011-05-09 | 2011-05-10 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-05-16 |  | 2011-09-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-27 | Online | Gov't | Y
NSTAR | Waltham | 1805 | 2452 | 182 | PV | 3316 | 2011-05-05 | 2011-10-20 | 120 | 118 | 2 | 2011-10-21 | 2011-12-19 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-19 |  | 2011-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-28 |  | 2012-04-06 | Online | Gov't | Y
NSTAR | Canton | 1806 | 2021 | 50 | PV | 470-H8 | 2011-05-09 |  | -29052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Fairhaven | 1807 | 2719 | 100 | Conditioned Digester Gas | 2-221-221 | 2011-05-09 | 2011-05-11 | 2 | 1 | 1 | 2011-05-11 | 2011-06-27 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-28 |  | 2011-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-10-12 |  | 2011-10-12 | Online | Private | Y
NSTAR | Harwich | 1808 | 2645 | 32 | PV | 4-95A-599 | 2011-05-13 | 2011-06-03 | 15 | 13 | 2 | 2011-06-03 | 2011-06-15 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2012-07-14 | 29355 | 0 | 29355 |  |  | 0 | 0 | 0 | 2012-12-19 |  |  | TBD | STD |  |  |  | 0 | 0 | 0 | 2013-02-06 |  | 2013-02-06 | Online | Private | N
NSTAR | Acusnet | 1809 | 2743 | 1142.68 | PV | 2-241-238 | 2011-05-16 | 2011-06-01 | 12 | 11 | 1 | 2011-06-01 | 2011-07-25 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2013-02-06 | Online | Gov't | Y
NSTAR | Milton | 1810 | 2186 | 75 | PV | 311-04 | 2011-05-16 | 2011-06-01 | 12 | 11 | 1 | 2011-06-01 | 2011-07-18 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-25 |  | 2011-07-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-31 | Online | Gov't | N
NSTAR | Milton | 1811 | 2186 | 100 | PV | 496-H7 | 2011-05-16 | 2011-06-01 | 12 | 11 | 1 | 2011-06-01 | 2011-09-13 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-07-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-27 | Online | Gov't | N
NSTAR | Milton | 1812 | 2186 | 400 | PV | 496-H7 | 2011-05-16 | 2011-05-31 | 11 | 9 | 2 | 2011-06-01 | 2011-07-20 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-21 |  | 2011-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-24 | Online | Gov't | N
NSTAR | Milton | 1813 | 2186 | 200 | PV | 4303 | 2011-05-17 | 2011-06-06 | 14 | 13 | 1 | 2011-06-06 | 2011-07-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-15 |  | 2011-12-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-01-25 | Online | Private | Y
NSTAR | Boston | 1814 | 2127 | 50 | PV | 385-H1 | 2011-05-17 | 2011-06-06 | 14 | 12 | 2 | 2011-06-06 | 2011-07-11 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-11 |  | 2011-12-14 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-22 |  | 2011-12-22 | Online | Private | Y
NSTAR | Boston | 1815 | 2127 | 28 | PV | 385-H1 | 2011-05-17 | 2011-06-06 | 14 | 10 | 4 | 2011-06-06 | 2011-07-07 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-08 |  | 2011-12-14 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-22 |  | 2012-01-09 | Online | Private | Y
NSTAR | Boston | 1816 | 2127 | 28 | PV | 385-H1 | 2011-05-26 | 2011-05-26 | 0 | 0 | 0 | 2011-05-26 | 2011-07-08 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-11 |  | 2011-07-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-09-30 |  | 2011-10-04 | Online | Private | Y
NSTAR | Chatham | 1817 | 2633 | 21 | PV | 4-95B-941 | 2011-05-25 | 2011-06-06 | 8 | 7 | 1 | 2011-06-06 | 2011-06-16 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-06-22 |  | 2011-06-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-12-28 | Online | Gov't | Y
NSTAR | Natick | 1818 | 1760 | 175 | PV | 433-H12 | 2011-05-23 | 2011-05-31 | 6 | 3 | 3 | 2011-05-31 | 2011-07-23 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-25 |  | 2012-05-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-24 | Online | Private | Y
NSTAR | Carver | 1819 | 2330 | 833 | PV | 3-10-930 | 2011-05-25 | 2011-08-22 | 63 | 58 | 5 | 2011-08-22 | 2011-10-24 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-15 |  | 2012-01-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | East Falmouth | 1820 | 2536 | 225 | Wind | 4-98A-98A | 2011-05-26 | 2011-06-02 | 5 | 0 | 5 | 2011-06-02 | 2011-07-15 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  |  | Withdrawn | Private | N
NSTAR | Wareham | 1821 | 2576 | 1000 | PV | 3-86-86 | 2011-05-26 | 2011-06-02 | 5 | 0 | 5 | 2011-06-02 | 2011-07-15 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  | 2012-07-12 | Online | Private | N
NSTAR | Wareham | 1822 | 2576 | 1000 | PV | 3-86-86 | 2011-05-26 | 2011-06-02 | 5 | 0 | 5 | 2011-06-02 | 2011-07-15 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  | 2012-07-12 | Online | Private | N
NSTAR | Wareham | 1823 | 2576 | 1000 | PV | 3-86-86 | 2011-05-26 | 2011-06-02 | 5 | 0 | 5 | 2011-06-02 | 2011-07-15 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 |  | 2012-02-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-07-17 |  | 2012-07-12 | Online | Private | N
NSTAR | Wareham | 1824 | 2576 | 500 | PV | 3-86-86 | 2011-06-01 | 2011-06-08 | 5 | 3 | 2 | 2011-06-08 | 2011-06-16 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-17 | Online | Private | Y
NSTAR | Hopkinton | 1825 | 1748 | 69 | PV | 65-1325H3 | 2011-05-31 | 2011-06-14 | 10 | 6 | 4 | 2011-06-14 | 2011-09-14 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-09 |  | 2011-07-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-06 |  | 2011-12-06 | Online | Private | Y
NSTAR | Dedham | 1826 | 2026 | 150 | PV | 344-07 | 2011-06-01 | 2011-07-06 | 25 | 21 | 4 | 2011-07-06 | 2011-08-10 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-21 |  | 2011-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-01-22 |  | 2013-01-22 | Online | Private | Y
NSTAR | Freetown | 1827 | 2717 | 1304.16 | PV | 2-102-604 | 2011-06-07 | 2011-06-15 | 6 | 6 | 0 | 2011-06-15 | 2011-08-05 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-08-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-11-29 |  | 2013-01-22 | Online | Private | N
NSTAR | Westwood | 1828 | 2090 | 150 | Natural Gas | 148-H3 | 2011-06-13 | 2011-06-27 | 10 | 10 | 0 | 2011-06-27 | 2011-08-15 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-15 |  | 2011-07-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-07 | Online | Private | Y
NSTAR | New Bedford | 1829 | 2745 | 26 | PV | 2-106-160 | 2011-05-31 | 2011-06-14 | 10 | 1 | 9 | 2011-06-14 | 2011-08-08 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-07-15 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2011-12-06 |  | 2012-01-11 | Online | Private | Y
NSTAR | Roxbury | 1830 | 2119 | 150 | PV | 52-1487H1 | 2011-06-13 | 2011-06-24 | 9 | 9 | 0 | 2011-06-24 | 2011-07-01 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-07-31 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | New Bedford | 1831 | 2740 | 200 | PV | 2-220-9 | 2011-06-13 | 2011-07-29 | 34 | 30 | 4 | 2011-07-29 | 2011-08-05 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-17 |  | 2011-08-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-09-16 | Online | Private | Y
NSTAR | Mattapoisett | 1832 | 2739 | 82 | PV | 2-304-304 | 2011-06-20 | 2011-06-30 | 8 | 7 | 1 | 2011-06-30 | 2011-08-01 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-08 |  | 2011-08-01 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-05-11 |  | 2012-05-11 | Online | Gov't | N
NSTAR | Kingston | 1833 | 2364 | 2100 | Wind | 3-17-913 | 2011-06-21 | 2011-06-24 | 3 | 3 | 0 | 2011-06-24 | 2011-09-16 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2011-12-21 | Online | Gov't | Y
NSTAR | Waltham | 1834 | 2452 | 395 | PV | 450-H1 | 2011-06-21 | 2011-06-24 | 3 | 3 | 0 | 2011-06-24 | 2011-07-25 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-26 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online | Gov't | Y
NSTAR | Waltham | 1835 | 2451 | 130 | PV | 450-H1 | 2011-06-21 | 2011-06-24 | 3 | 3 | 0 | 2011-06-24 | 2011-07-25 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-26 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online | Gov't | Y
NSTAR | Waltham | 1836 | 2452 | 75 | PV | 282-H2 | 2011-06-21 | 2011-06-24 | 3 | 3 | 0 | 2011-06-24 | 2011-07-28 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-07-29 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-02-09 | Online | Gov't | Y
NSTAR | Waltham | 1837 | 2453 | 75 | PV | 467-H5 | 2011-06-23 | 2011-08-05 | 31 | 31 | 0 | 2011-08-05 | 2011-08-23 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-06 |  | 2012-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-09 | Online | Private | Y
NSTAR | Natick | 1838 | 1760 | 332 | Natural Gas | 433-H7 | 2011-06-24 | 2011-06-28 | 2 | 2 | 0 | 2011-06-28 | 2011-08-15 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-11-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Holliston | 1839 | 1746 | 1750 | PV | 274-H2 | 2011-06-24 | 2011-07-29 | 25 | 23 | 2 | 2011-07-29 | 2011-09-16 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 1842 | 2748 | 50 | PV | 2-524-524 | 2011-07-01 | 2011-07-18 | 11 | 11 | 0 | 2011-07-18 | 2011-07-25 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-04 | 2012-12-10 | 45 | 0 | 45 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 | 2013-12-18 | Online | Gov't | Y
NSTAR | East Freetown | 1843 | 2717 | 1723 | PV | 2-102-102 | 2011-07-01 | 2011-07-18 | 11 | 11 | 0 | 2011-07-18 | 2011-07-25 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-04 | 2012-12-10 | 45 | 0 | 45 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 | 2013-12-18 | Online | Gov't | Y
NSTAR | East Freetown | 1844 | 2717 | 2000 | PV | 2-102-102 | 2011-07-01 | 2011-07-08 | 5 | 3 | 2 | 2011-07-08 | 2011-08-05 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-07-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-11-15 | Online | Gov't | Y
NSTAR | New Bedford | 1845 | 2746 | 177 | PV | 2-84-15 | 2011-07-04 | 2011-07-05 | 1 | 0 | 1 | 2011-07-05 | 2011-08-09 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-01 |  | 2011-10-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online | Private | Y
NSTAR | Norfolk | 1846 | 2056 | 1375 | PV | 65-H1 | 2011-07-06 | 2011-07-07 | 1 | 0 | 1 | 2011-07-07 | 2011-08-25 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-25 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online | Gov't | N
NSTAR | Boston | 1847 | 2125 | 82 | PV | 511-1497H | 2011-07-11 | 2011-07-20 | 7 | 7 | 0 | 2011-07-20 | 2011-09-09 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-09 |  | 2011-09-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-03-30 | Online | Gov't | Y
NSTAR | Sharon | 1848 | 2067 | 30 | PV | 470-H12 | 2011-07-13 | 2011-08-02 | 14 | 14 | 0 | 2011-08-02 | 2011-09-12 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2013-09-19 | 430 | 0 | 430 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2012-03-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-23 | Online | Gov't | N
NSTAR | Freetown | 1849 | 2717 | 4200 | PV | 2-102-102 | 2011-07-13 | 2011-08-02 | 14 | 14 | 0 | 2011-08-02 | 2011-09-12 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 |  | -29223 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Freetown | 1850 | 2717 | 2000 | PV | 2-102-102 | 2011-07-07 | 2011-09-09 | 46 | 42 | 4 | 2011-09-09 | 2011-10-24 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-29 | 2012-07-13 | 94 | 0 | 94 |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Acusnet | 1851 | 2116 | 1000 | PV | 2-241-241 | 2011-07-07 | 2011-09-09 | 46 | 42 | 4 | 2011-09-09 | 2011-10-24 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-29 | 2012-07-13 | 94 | 0 | 94 |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Acusnet | 1852 | 2116 | 1000 | PV | 2-241-241 | 2011-07-14 | 2011-07-20 | 4 | 4 | 0 | 2011-07-20 | 2011-08-25 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-07 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Acton | 1853 | 1720 | 128 | PV | 416-H9 | 2011-07-20 | 2011-07-27 | 5 | 5 | 0 | 2011-07-27 | 2011-09-16 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-09-05 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-05 |  | 2011-12-15 | Online | Private | Y
NSTAR | New Bedford | 1854 | 2745 | 250 | PV | 2-82-82 | 2011-07-20 | 2011-08-02 | 9 | 8 | 1 | 2011-08-02 | 2011-09-12 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | 111 | 0 | 111 |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Freetown | 1855 | 2717 | 2000 | PV | 2-102-102 | 2011-07-21 | 2011-09-20 | 43 | 43 | 0 | 2011-09-20 | 2011-10-29 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-31 |  | 2011-08-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-02-07 |  | 2012-02-13 | Online | Private | Y
NSTAR | Plymouth | 1856 | 2360 | 190 | PV | 3-12-12 | 2011-07-22 | 2011-07-28 | 4 | 4 | 0 | 2011-07-28 | 2011-08-05 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online | Gov't | N
NSTAR | New Bedford | 1857 | 2745 | 110 | PV | 2-105-105 | 2011-07-22 | 2011-07-28 | 4 | 3 | 1 | 2011-07-28 | 2011-08-05 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online | Gov't | N
NSTAR | New Bedford | 1858 | 2740 | 50 | PV | 2-73-16 | 2011-07-22 | 2011-07-28 | 4 | 3 | 1 | 2011-07-28 | 2011-08-05 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online | Gov't | N
NSTAR | New Bedford | 1859 | 2745 | 50 | PV | 2-79-79 | 2011-07-22 | 2011-07-28 | 4 | 3 | 1 | 2011-07-28 | 2011-09-16 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Gov't | Y | 2011-09-19
NSTAR | New Bedford | 1860 | 2744 | 110 | PV | 2-7-34 | 2011-07-22 | 2011-07-28 | 4 | 3 | 1 | 2011-07-28 | 2011-08-31 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-31 |  | 2011-10-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2011-12-15 | Online | Gov't | Y
NSTAR | New Bedford | 1861 | 2746 | 50 | PV | 2-83-403 | 2011-07-25 | 2011-07-28 | 3 | 2 | 1 | 2011-07-29 | 2011-09-09 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-26 |  | 2011-10-01 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-07-05 |  | 2012-07-05 | Online | Private | Y
NSTAR | Dartmouth | 1862 | 2747 | 2000 | PV | 2-541-541 | 2011-07-26 | 2011-07-28 | 2 | 2 | 0 | 2011-07-29 | 2011-08-05 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-08 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-13 |  | 2012-07-05 | Online | Gov't | N
NSTAR | New Bedford | 1863 | 2740 | 108 | PV | 2-71-71 | 2011-07-26 | 2011-07-28 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Impact Study Fee & Agreement | Private | Y | 2011-08-31
NSTAR | New Bedford | 1864 | 2745 | 625 | PV | 2-59-59 | 2011-07-27 | 2011-08-02 | 4 | 4 | 0 | 2011-08-04 | 2011-09-09 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | 209 | 0 | 209 |  |  | 0 | 0 | 0 | 2013-04-26 |  | 2012-06-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  |  | Private | Y
NSTAR | Marshfield | 1865 | 1845 | 3000 | PV | 3-21-34J1 | 2011-07-27 | 2011-08-02 | 4 | 4 | 0 | 2011-08-04 | 2011-09-13 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | 209 | 0 | 209 |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Marshfield | 1866 | 1845 | 1000 | PV | 3-21-976 | 2011-07-27 | 2011-08-02 | 4 | 4 | 0 | 2011-08-04 | 2011-09-09 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | 209 | 0 | 209 |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Marshfield | 1867 | 1845 | 1000 | PV | 3-21-976 | 2011-07-27 | 2011-08-02 | 4 | 4 | 0 | 2011-08-04 | 2011-09-09 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-27 | 2012-08-22 | 209 | 0 | 209 |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Marshfield | 1868 | 1845 | 1000 | PV | 3-21-976 | 2011-07-27 | 2011-07-28 | 1 | 0 | 1 | 2011-07-28 | 2011-09-07 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-09 |  | 2011-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-05 |  |  | Withdrawn | Private | Y
NSTAR | Wareham | 1869 | 2671 | 30 | PV | 3-86-966 | 2011-07-28 | 2011-07-28 | 0 | 0 | 0 | 2011-07-28 | 2011-09-07 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-09 |  | 2011-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2011-12-27 | Online | Private | Y
NSTAR | Sherborn | 1870 | 1770 | 60 | PV | 240-H6 | 2011-07-28 | 2011-08-01 | 2 | 1 | 1 | 2011-08-01 | 2011-09-01 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-08-29 |  | 2011-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-02-03 |  | 2012-02-03 | Online | Private | Y
NSTAR | Brewster | 1871 | 2631 | 310 | PV | 4-95B-600 | 2011-08-02 | 2011-08-04 | 2 | 2 | 0 | 2011-08-04 | 2011-09-08 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-13 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-29 |  |  |  | Gov't | N
NSTAR | Waltham | 1872 | 2452 | 310 | PV | 450-H6 | 2011-08-02 | 2011-08-09 | 5 | 4 | 1 | 2011-08-09 | 2011-09-26 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-26 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-12-29 | Online | Private | Y
NSTAR | Framingham | 1873 | 1701 | 225 | PV | 433-H8 | 2011-08-03 | 2012-09-10 | 282 | 287 | -5 | 2012-09-10 |  | -29396 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | New Bedford | 1874 | 2744 | 310 | PV | 12457 | 2011-08-04 | 2011-09-28 | 39 | 39 | 0 | 2011-09-28 | 2011-11-02 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-02 | 2012-10-15 | 219 | 0 | 219 |  |  | 0 | 0 | 0 | 2012-02-28 |  | 2011-12-01 | TBD | STD |  |  |  | 0 | 0 | 0 | 2012-09-27 | 2012-10-02 |  |  | Private | Y
NSTAR | Hyannis | 1875 | 2601 | 1238 | PV | 4-80B-80-B | 2011-08-04 | 2011-08-09 | 3 | 2 | 1 | 2011-08-09 | 2011-09-16 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-19 |  | 2011-08-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-27 | Online | Private | Y
NSTAR | Waltham | 1876 | 2453 | 30 | PV | 467-H5 | 2011-08-08 | 2011-08-09 | 1 | 0 | 1 | 2011-08-10 | 2011-09-23 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-09 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-08-07 | 2012-08-07 | 2012-08-07 | Online | Private | N
NSTAR | Hopkinton | 1877 | 1748 | 1000 | Natural Gas | 455-H3 | 2011-08-09 | 2011-08-10 | 1 | 1 | 0 | 2011-08-10 | 2011-09-14 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-09-15 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-04-04 |  | 2012-04-11 | Online | Private | Y
NSTAR | West Tisbury | 1879 | 2575 | 5 | Wind | 4-97-97 | 2011-08-09 | 2011-08-11 | 2 | 1 | 1 | 2011-08-12 | 2011-10-24 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Bourne | 1880 | 2532 | 2000 | Wind | 3-88-923 | 2011-08-09 | 2011-08-11 | 2 | 1 | 1 | 2011-08-12 | 2011-10-24 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Bourne | 1881 | 2532 | 2000 | Wind | 3-88-923 | 2011-08-09 | 2011-08-11 | 2 | 1 | 1 | 2011-08-12 | 2011-10-24 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Bourne | 1882 | 2532 | 2000 | Wind | 3-88-923 | 2011-08-16 | 2011-08-30 | 10 | 10 | 0 | 2011-08-30 | 2011-10-24 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 |  | -29223 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-07-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | N
NSTAR | East Freetown | 1883 | 2717 | 1000 | PV | 604 | 2011-08-18 | 2011-08-25 | 5 | 5 | 0 | 2011-08-26 | 2011-10-01 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-28 |  | 2011-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-08 |  | 2012-03-08 | Online | Private | Y
NSTAR | Boston | 1884 | 2119 | 75 | PV | 323-05 | 2011-08-18 | 2011-08-25 | 5 | 5 | 0 | 2011-08-26 | 2011-10-04 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-04 |  | 2011-10-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-27 |  | 2012-07-06 | Online | Private | Y
NSTAR | Boston | 1885 | 2128 | 75 | PV | 108-196H1 | 2011-08-17 | 2011-08-22 | 3 | 1 | 2 | 2011-08-22 | 2011-09-12 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-09 | 2012-05-15 | 88 | 0 | 88 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2014-06-09 | 2014-06-09 | 2014-06-16 | Online | Gov't | Y
NSTAR | Edgartown | 1886 | 2539 | 1083 | PV | 4-97-227 | 2011-08-22 | 2011-08-22 | 0 | 0 | 0 | 2011-08-23 | 2011-09-12 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-06-20 | 147 | 0 | 147 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-06-16 | Online | Gov't | Y
NSTAR | Edgartown | 1887 | 2539 | 1083 | PV | 4-97-97 | 2011-08-22 | 2011-08-25 | 3 | 2 | 1 | 2011-08-25 | 2011-10-24 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-10-15 | 227 | 0 | 227 |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online | Gov't | Y
NSTAR | Dartmouth | 1888 | 2747 | 1146 | PV | 2-107-107 | 2011-08-22 | 2011-08-25 | 3 | 2 | 1 | 2011-08-25 | 2011-10-24 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-10-15 | 227 | 0 | 227 |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online | Private | Y
NSTAR | Dartmouth | 1889 | 2747 | 1000 | PV | 2-107-107 | 2011-08-22 | 2011-08-25 | 3 | 2 | 1 | 2011-08-25 | 2011-10-24 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 | 2012-10-15 | 227 | 0 | 227 |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online | Private | Y
NSTAR | Dartmouth | 1890 | 2747 | 1146 | PV | 2-107-107 | 2011-08-23 | 2011-08-29 | 4 | 4 | 0 | 2011-08-29 | 2011-10-17 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-11-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-12-14 |  | 2013-03-27 | Online | Private | Y
NSTAR | Harwich | 1891 | 2645 | 36 | PV | 4-89A-556 | 2011-08-26 | 2011-08-30 | 2 | 1 | 1 | 2011-08-30 | 2011-10-19 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-03-05 | Online | Gov't | Y
NSTAR | Natick | 1892 | 1760 | 100 | PV | 240-H5 | 2011-08-26 | 2011-08-30 | 2 | 1 | 1 | 2011-08-30 | 2011-10-19 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online | Gov't | N
NSTAR | Natick | 1893 | 1760 | 90 | PV | 433-H5 | 2011-08-26 | 2011-08-30 | 2 | 1 | 1 | 2011-08-30 | 2011-10-24 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | 111 | 0 | 111 |  |  | 0 | 0 | 0 |  |  | 2013-07-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | East Freetown | 1894 | 2717 | 1000 | PV | 604 | 2011-08-26 | 2011-08-30 | 2 | 1 | 1 | 2011-08-30 | 2011-10-24 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | 111 | 0 | 111 |  |  | 0 | 0 | 0 | 2013-06-07 |  | 2013-07-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-23 | Online | Private | Y
NSTAR | East Freetown | 1895 | 2717 | 2984 | PV | 2-108-108 | 2011-08-26 | 2011-08-30 | 2 | 1 | 1 | 2011-08-30 | 2011-10-24 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-06-12 | 111 | 0 | 111 |  |  | 0 | 0 | 0 | 2013-06-07 |  | 2013-07-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-20 | Online | Gov't | Y
NSTAR | East Freetown | 1896 | 2717 | 1000 | PV | 2-102-604 | 2011-08-25 | 2011-08-29 | 2 | 0 | 2 | 2011-08-29 | 2011-10-17 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-20 |  | 2011-11-15 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2011-12-14 |  | 2015-03-20 | Online | Private | Y
NSTAR | Harwich | 1897 | 2645 | 36 | PV | 4-89A-556 | 2011-08-29 | 2011-08-30 | 1 | 1 | 0 | 2011-08-30 | 2011-11-09 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-14 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-21 |  | 2011-12-21 | Online | Gov't | N
NSTAR | Natick | 1898 | 1760 | 260 | PV | 433-H5 | 2011-08-30 | 2011-10-05 | 26 | 25 | 1 | 2011-10-05 | 2011-12-02 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-02 |  | 2011-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-03 |  | 2012-07-03 | Online | Private | Y
NSTAR | Canton | 1899 | 2021 | 46 | PV | 269-1321H2 | 2011-08-31 | 2011-09-02 | 2 | 2 | 0 | 2011-09-02 | 2011-10-07 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-03 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2011-12-05 |  | 2011-12-05 | Online | Private | Y
NSTAR | North Dartmouth | 1900 | 2747 | 17 | PV | 2-72-501 | 2011-09-01 | 2011-09-08 | 5 | 5 | 0 | 2011-09-08 | 2011-11-22 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Roslindale | 1901 | 2131 | 50 | PV | 1308 | 2011-09-01 | 2011-09-08 | 5 | 5 | 0 | 2011-09-08 | 2011-11-17 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-17 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Roslindale | 1902 | 2131 | 35 | PV | 1308 | 2011-09-01 | 2011-09-08 | 5 | 5 | 0 | 2011-09-08 | 2011-11-22 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Roslindale | 1903 | 2131 | 50 | PV | 1308 | 2011-09-01 | 2011-09-08 | 5 | 5 | 0 | 2011-09-08 | 2011-11-17 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-17 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Roslindale | 1904 | 2131 | 35 | PV | 1308 | 2011-09-01 | 2011-09-06 | 3 | 3 | 0 | 2011-09-06 | 2011-11-29 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-30 |  | 2011-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-04-03 |  | 2012-04-03 | Online | Private | Y
NSTAR | Wayland | 1906 | 1778 | 12 | PV | 342-H1 | 2011-09-01 | 2011-09-08 | 5 | 4 | 1 | 2011-09-08 | 2011-11-15 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-15 |  | 2011-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Roslindale | 1907 | 2131 | 35 | PV | 1310 | 2011-09-02 | 2011-10-25 | 37 | 35 | 2 | 2011-10-25 | 2012-05-10 | 139 | 0 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-11 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-14 | Online | Gov't | Y
NSTAR | Chatham | 1908 | 2633 | 50 | PV | 4-95A-606 | 2011-09-09 | 2011-09-15 | 4 | 3 | 1 | 2011-09-15 | 2011-10-26 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-06-21 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Bellingham | 1909 | 2019 | 600 | PV | 65-H4 | 2011-09-09 | 2011-09-15 | 4 | 3 | 1 | 2011-09-15 | 2011-10-26 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-06-21 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Medway | 1910 | 2053 | 600 | PV | 65-H2 | 2011-09-12 | 2011-09-20 | 6 | 6 | 0 | 2011-09-20 | 2011-10-24 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-03 | 2012-06-20 | 95 | 0 | 95 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Chatham | 1911 | 2633 | 1500 | PV | 4-95B-606 | 2011-09-12 | 2011-10-21 | 29 | 29 | 0 | 2011-10-24 | 2012-01-27 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-09 | 2012-06-20 | 71 | 0 | 71 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-29 | Online | Gov't | Y
NSTAR | Brewster | 1912 | 2631 | 1083 | PV | 4-89A-553 | 2011-09-09 | 2011-09-20 | 7 | 6 | 1 | 2011-09-20 | 2011-10-18 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-09 | 2012-07-18 | 132 | 0 | 132 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-08-05 | Online | Gov't | Y
NSTAR | Harwich | 1913 | 2645 | 2000 | PV | 4-89A-89A | 2011-09-09 | 2011-09-20 | 7 | 6 | 1 | 2011-09-20 | 2011-10-18 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-09 | 2012-07-18 | 132 | 0 | 132 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Harwich | 1914 | 2645 | 2000 | PV | 4-89A-89A | 2011-09-09 | 2012-02-21 | 115 | 116 | -1 | 2012-02-21 | 2012-04-02 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Eastham | 1915 | 2642 | 500 | PV | 4-94B-646 | 2011-09-15 | 2011-09-21 | 4 | 4 | 0 | 2011-09-21 | 2011-10-14 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-17 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-02-16 |  | 2012-02-16 | Online | Private | Y
NSTAR | Wayland | 1916 | 1778 | 60 | PV | 342-H3 | 2011-09-17 |  | -29146 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Edgartown | 1917 | 2539 | 1500 | PV | 4-97-97 | 2011-09-15 | 2011-09-20 | 3 | 1 | 2 | 2011-09-21 | 2011-11-07 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-08 |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Cambridge | 1918 | 2141 | 38 | Natural Gas | 812-16 | 2011-09-20 | 2011-09-21 | 1 | 0 | 1 | 2011-09-21 | 2012-01-30 | 92 | 0 | 92 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-21 |  | 2011-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-01 |  | 2012-05-04 | Online | Private | Y
NSTAR | Hyde Park | 1919 | 2136 | 177 | PV | 496-H2 | 2011-09-21 | 2011-09-26 | 3 | 3 | 0 | 2011-09-26 | 2011-11-07 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-09 |  | 2011-12-27 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-02-23 | Online | Private | Y
NSTAR | Sudbury | 1920 | 1776 | 95 | PV | 342-H5 | 2011-05-23 | 2011-05-31 | 6 | 3 | 3 | 2011-05-31 | 2011-07-23 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-06 |  | 2012-05-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Carver | 1921 | 2346 | 1000 | PV | 930 | 2011-09-22 | 2011-09-28 | 4 | 1 | 3 | 2011-09-28 | 2011-10-28 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-10-28 |  | 2011-07-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Carlisle | 1922 | 1741 | 11 | PV | 512-1399H1 | 2011-09-29 | 2011-10-21 | 16 | 15 | 1 | 2011-10-24 | 2012-01-30 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 | 2012-05-25 | 68 | 0 | 68 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-08-05 | Online | Gov't | Y
NSTAR | Tisbury | 1923 | 2568 | 1083 | PV | 4-91-91 | 2011-09-30 | 2011-10-04 | 2 | 2 | 0 | 2011-10-04 | 2011-12-20 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-23 | 2012-05-09 | 75 | 0 | 75 |  |  | 0 | 0 | 0 | 2013-11-19 |  | 2012-08-01 | Yes | TBD |  |  |  | 0 | 0 | 0 |  |  | 2014-07-25 | Online | Gov't | Y
NSTAR | Dartmouth | 1924 | 2747 | 2750 | PV | 2-541-541 | 2011-09-30 | 2011-10-04 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2014-03-24 | Online | Gov't | Y
NSTAR | Dartmouth | 1925 | 2747 | 4000 | PV | 2-532-532 | 2011-09-30 | 2011-10-04 | 2 | 2 | 0 | 2011-10-04 | 2011-12-20 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-23 |  | -29236 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | Withdrawn | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Dartmouth | 1926 | 2747 | 2000 | PV | 2-532-532 | 2011-09-30 | 2011-10-04 | 2 | 2 | 0 | 2011-10-04 | 2011-12-20 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-23 |  | -29236 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | Withdrawn | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Dartmouth | 1927 | 2747 | 2000 | PV | 2-532-532 | 2011-10-03 | 2011-10-04 | 1 | 1 | 0 | 2011-10-04 | 2011-11-23 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-22 |  | 2011-11-07 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Winchester | 1928 | 1890 | 17 | PV | 211-H4 | 2011-09-30 | 2012-04-06 | 133 |  | 133 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Private | N | 2012-05-29
NSTAR | Cambridge | 1929 | 2142 | 5750 | Natural Gas | 831-1301 | 2011-10-03 | 2011-10-04 | 1 | 1 | 0 | 2011-10-04 | 2011-11-08 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-09 |  | 2011-12-15 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-06 |  | 2012-06-27 | Online | Gov't | N
NSTAR | Waltham | 1930 | 2452 | 666 | PV | 450-H1 | 2011-10-03 | 2011-10-05 | 2 | 2 | 0 | 2011-10-05 | 2011-11-29 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-30 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-20 |  | 2012-06-06 | Online | Private | Y
NSTAR | Acton | 1931 | 1720 | 42 | PV | 416-H9 | 2011-10-04 | 2011-10-04 | 0 | 0 | 0 | 2011-10-05 | 2012-01-05 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-06 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-15 | Online | Private | Y
NSTAR | Hopkinton | 1932 | 1748 | 200 | PV | 519-175H1 | 2011-10-06 |  | -29160 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Bellingham | 1933 | 2019 | 5800 | PV | 65-H4 | 2011-10-06 | 2011-10-12 | 4 | 3 | 1 | 2011-10-12 | 2011-11-14 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-12-14 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-02-28 |  | 2012-02-28 | Withdrawn | Private | Y
NSTAR | Chilmark | 1934 | 2535 | 62 | PV | 4-97-220 | 2011-10-10 | 2011-10-12 | 2 | 1 | 1 | 2011-10-20 | 2012-01-20 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2012-02-28 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-08 |  | 2012-11-08 | Online | Private | Y
NSTAR | Hyannis | 1935 | 2601 | 35 | PV | 4-84B-524 | 2011-10-10 | 2011-10-12 | 2 | 1 | 1 | 2011-10-20 | 2012-01-20 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2012-02-28 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-08 |  | 2012-11-08 | Online | Private | Y
NSTAR | Hyannis | 1936 | 2601 | 50 | PV | 4-84B-524 | 2011-10-07 | 2011-10-12 | 3 | 1 | 2 | 2011-10-13 | 2011-11-19 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-21 |  | 2011-12-31 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-04-17 |  | 2012-04-19 | Online | Private | Y
NSTAR | Mattapoisett | 1937 | 2739 | 82 | PV | 2-304-304 | 2011-10-12 | 2011-10-12 | 0 | 0 | 0 | 2011-10-12 | 2011-11-29 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-15 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-02-15 | Online | Private | Y
NSTAR | Hopkinton | 1938 | 1748 | 30 | PV | 65-H6 | 2011-10-13 | 2011-10-19 | 4 | 3 | 1 | 2011-10-20 | 2012-01-30 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-06 | 2012-07-27 | 77 | 0 | 77 |  |  | 0 | 0 | 0 | 2013-08-12 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-08-29 | Online | Private | Y
NSTAR | New Bedford | 1939 | 2740 | 1500 | PV | 2-70-502 | 2011-10-12 | 2011-10-21 | 7 | 4 | 3 | 2011-10-24 | 2012-01-26 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Acusnet | 1940 | 2743 | 2000 | PV | 2-241-241 | 2011-10-12 | 2011-10-21 | 7 | 4 | 3 | 2011-10-24 | 2012-01-26 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Acusnet | 1941 | 2743 | 2000 | PV | 2-240-240 | 2011-10-12 | 2011-10-21 | 7 | 4 | 3 | 2011-10-24 | 2012-01-26 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Acusnet | 1942 | 2743 | 2000 | PV | 2-242-242 | 2011-10-17 | 2011-10-24 | 5 | 5 | 0 | 2011-10-24 | 2012-01-23 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Framingham | 1943 | 1702 | 750 | PV | 274-H1 | 2011-10-17 | 2011-10-24 | 5 | 5 | 0 | 2011-10-24 | 2012-01-23 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Framingham | 1944 | 1702 | 875 | PV | 274-H1 | 2011-10-17 | 2011-10-24 | 5 | 5 | 0 | 2011-10-24 | 2012-01-23 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Framingham | 1945 | 1702 | 875 | PV | 274-H1 | 2011-10-20 | 2011-10-21 | 1 | 1 | 0 | 2011-10-21 | 2012-01-19 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2011-06-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-07-13 |  |  | Withdrawn | Private | Y
NSTAR | Hyannis | 1946 | 2601 | 475.2 | PV | 4-80B-80B | 2011-10-20 | 2011-10-20 | 0 | 0 | 0 | 2011-10-21 | 2011-12-22 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-23 |  | 2011-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-01-18 |  | 2012-07-13 | Online | Private | Y
NSTAR | Marion | 1947 | 2378 | 39 | PV | 3-85-957 | 2011-10-20 | 2011-10-28 | 6 | 6 | 0 | 2011-10-31 | 2012-01-30 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-03 | 2012-07-11 | 131 | 0 | 131 |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Freetown | 1948 | 2717 | 1785 | PV | 2-102-604 | 2011-10-07 | 2011-11-21 | 31 | 21 | 10 | 2011-11-21 | 2012-02-28 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-07 |  | 2011-12-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Private | Y | 2012-05-07
NSTAR | Boston | 1949 | 2215 | 225 | PV | 329-H4 | 2011-10-27 | 2011-10-28 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2014-07-10 | Online | Private | Y
NSTAR | Brewster | 1950 | 2631 | 1785 | PV | 4-95B-600 | 2011-10-24 | 2011-10-25 | 1 | 0 | 1 | 2011-10-25 | 2011-11-30 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-01 |  | 2011-12-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-15 |  | 2012-03-15 | Online | Private | Y
NSTAR | Carver | 1951 | 2330 | 150 | PV | 3-10-917 | 2011-10-24 |  | -29172 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Bellingham | 1952 | 2019 | 5800 | PV | 65-H4 | 2011-10-27 | 2011-11-01 | 3 | 1 | 2 | 2011-11-02 | 2011-12-19 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-20 |  | 2011-11-04 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-02-10 | Withdrawn | Private | Y
NSTAR | Edgartown | 1953 | 2539 | 12 | PV | 4-75-227 | 2011-10-28 | 2011-11-01 | 2 | 1 | 1 | 2011-11-01 | 2011-11-29 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2011-11-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | New Bedford | 1954 | 2740 | 50 | PV | 2-5-5 | 2011-10-31 | 2011-11-01 | 1 | 1 | 0 | 2011-11-01 | 2012-01-26 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2011-12-31 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-08-24 |  | 2012-08-24 | Online | Private | Y
NSTAR | Carver | 1955 | 2330 | 225 | PV | 3-10-917 | 2011-10-31 | 2011-11-01 | 1 | 1 | 0 | 2011-11-01 | 2011-12-12 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2011-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-05 | Online | Private | N
NSTAR | Cambridge | 1956 | 2142 | 75 | Natural Gas | 875-1N25A | 2011-10-31 | 2011-11-01 | 1 | 1 | 0 | 2011-11-01 | 2011-11-30 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-11-30 |  | 2011-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-05 | Online | Private | N
NSTAR | Roxbury | 1957 | 2119 | 75 | Natural Gas | 106-1N18H1 | 2011-11-01 | 2011-11-28 | 19 | 18 | 1 | 2011-11-28 | 2012-01-23 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-25 |  | 2011-12-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-02-21 | Online | Private | Y
NSTAR | North Dartmouth | 1958 | 2747 | 125 | PV | 2-541-541 | 2011-11-04 | 2011-11-04 | 0 | 0 | 0 | 2011-11-04 | 2011-12-19 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2011-12-19 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-03 |  | 2012-07-03 | Online | Private | Y
NSTAR | Carver | 1959 | 2330 | 21 | PV | 3-11-11 | 2011-11-04 | 2011-11-14 | 6 | 5 | 1 | 2011-11-14 | 2012-01-31 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-01 |  | 2012-06-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Fairhaven | 1960 | 2719 | 1000 | PV | 2-220-220 | 2011-11-04 | 2011-11-08 | 2 | 1 | 1 | 2011-11-08 | 2012-01-30 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-01 |  | 2012-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Maynard | 1961 | 1754 | 1000 | PV | 416-H6 | 2011-11-09 | 2011-11-15 | 4 | 3 | 1 | 2011-11-21 | 2012-01-03 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-01-30 | N/A | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Yarmouth | 1962 | 2675 | 75 | PV | 4-92A-92A | 2011-11-09 | 2011-11-15 | 4 | 3 | 1 | 2011-11-15 | 2012-02-14 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-27 |  | 2012-03-27 | Online | Private | Y
NSTAR | Barnstable | 1963 | 2630 | 14 | PV | 4-82-518 | 2011-11-10 | 2011-11-18 | 6 | 4 | 2 | 2011-11-22 | 2012-01-31 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 | 2012-09-04 | 137 | 0 | 137 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online | Gov't | Y
NSTAR | Barnstable | 1964 | 2655 | 2000 | PV | 4-80A-80A | 2011-11-10 | 2011-11-18 | 6 | 4 | 2 | 2011-11-22 | 2012-01-31 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 | 2012-09-04 | 137 | 0 | 137 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online | Gov't | Y
NSTAR | Barnstable | 1965 | 2648 | 1681 | PV | 4-88-88 | 2011-11-14 | 2011-11-21 | 5 | 4 | 1 | 2011-11-23 | 2012-02-29 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 |  | 2012-04-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2012-11-21 |  | 2014-09-02 | Online | Gov't | N
NSTAR | Framingham | 1966 | 1702 | 725 | PV | 2408 | 2011-11-17 | 2011-12-01 | 10 | 9 | 1 | 2011-12-01 | 2012-01-31 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-10 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  | 2012-11-20 | Online | Gov't | Y
NSTAR | Edgartown | 1967 | 2539 | 250 | PV | 4-97-97 | 2011-11-17 | 2011-12-01 | 10 | 9 | 1 | 2011-12-01 | 2012-01-31 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-10 |  |  | yes | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  | 2012-11-20 | Online | Private | Y
NSTAR | Edgartown | 1968 | 2539 | 250 | PV | 4-97-97 | 2011-11-17 | 2011-12-01 | 10 | 9 | 1 | 2011-12-01 | 2012-02-01 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  | 2012-11-20 | Online | Private | Y
NSTAR | West Tisbury | 1969 | 2575 | 250 | PV | 4-91-91 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Ashland | 1970 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Ashland | 1971 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Ashland | 1972 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Ashland | 1973 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Ashland | 1974 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 5 | 0 | 2011-11-28 | 2012-02-01 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Ashland | 1975 | 1721 | 875 | PV | 274-H1 | 2011-11-21 | 2011-11-28 | 5 | 4 | 1 | 2011-11-28 | 2012-01-23 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Framingham | 1976 | 1702 | 750 | PV | 240-H4 | 2011-11-21 | 2011-11-28 | 5 | 4 | 1 | 2011-11-28 | 2012-01-23 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Framingham | 1977 | 1702 | 750 | PV | 240-H4 | 2011-11-21 | 2011-11-22 | 1 | 0 | 1 | 2011-11-23 | 2012-01-03 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-11-20 |  |  | Withdrawn | Private | Y
NSTAR | Dover | 1978 | 2030 | 16 | PV | 456-H5 | 2011-11-23 | 2011-12-01 | 6 | 4 | 2 | 2011-12-01 | 2012-02-04 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-12 |  | 2012-02-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-29 |  | 2012-06-29 | Online | Private | Y
NSTAR | Bedford | 1979 | 1730 | 500 | PV | 533-H8 | 2011-11-23 | 2011-12-06 | 9 | 7 | 2 | 2011-12-08 | 2012-01-26 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-27 |  | 2010-08-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-16 |  | 2012-06-29 | Online | Private | Y
NSTAR | New Bedford | 1980 | 2745 | 30 | PV | 2-79-79 | 2011-11-30 | 2011-12-01 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private | Y
NSTAR | Dartmouth | 1981 | 2747 | 4400 | PV | 2-533-533 | 2011-11-30 | 2011-12-01 | 1 | 1 | 0 | 2011-12-01 | 2012-03-12 | 70 | 0 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-30 |  | -29742 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 1982 | 2747 | 2000 | PV | 2-533-533 | 2011-11-30 | 2011-12-01 | 1 | 1 | 0 | 2011-12-01 | 2012-03-12 | 70 | 0 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-30 |  | -29742 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-08-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 1983 | 2747 | 1000 | PV | 2-533-533 | 2011-11-30 | 2011-12-15 | 11 | 9 | 2 | 2011-12-15 | 2012-03-07 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-07 |  | 2011-12-24 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-15 |  |  | Withdrawn | Private | Y
NSTAR | Hyannis | 1984 | 2601 | 46 | PV | 4-84B-524 | 2011-11-30 | 2012-02-22 | 58 | 58 | 0 | 2012-02-29 | 2012-05-26 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Bellingham | 1985 | 2019 | 2000 | PV | 65-H4 | 2011-11-30 | 2012-02-22 | 58 | 58 | 0 | 2012-02-29 | 2012-05-26 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Bellingham | 1986 | 2019 | 2000 | PV | 65-H4 | 2011-11-30 |  | -29199 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Bellingham | 1987 | 2019 | 2000 | PV | 65-H4 | 2011-12-01 | 2011-12-07 | 4 | 3 | 1 | 2011-12-07 | 2012-02-09 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-23 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-16 |  |  | Withdrawn | Private | Y
NSTAR | Norfolk | 1988 | 2056 | 270 | PV | 146-H3 | 2011-12-01 | 2011-12-09 | 6 | 4 | 2 | 2011-12-15 | 2012-02-10 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-15 |  | 2012-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Medway | 1989 | 2053 | 2000 | Other | 65-H2 | 2011-12-06 | 2011-12-12 | 4 | 2 | 2 | 2011-12-13 | 2012-02-14 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-16 |  | 2012-04-23 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Watertown | 1990 | 2472 | 120 | PV | 467-H6 | 2011-12-08 | 2011-12-13 | 3 | 3 | 0 | 2011-12-15 | 2012-01-04 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-05 |  | 2012-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-16 |  | 2013-01-16 | Online | Private | Y
NSTAR | Fairhaven | 1991 | 2719 | 82 | PV | 2-220-201 | 2011-12-05 | 2011-12-09 | 4 | 0 | 4 | 2012-11-13 | 2013-04-09 | 100 | 0 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  | 2011-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage | Private | N
NSTAR | Plymouth | 1992 | 2360 | 2000 | Wind | 3-89-925 | 2011-12-08 | 2011-12-13 | 3 | 0 | 3 | 2011-12-15 | 2012-01-03 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-04 |  | 2011-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-16 |  | 2016-08-10 | Online | Gov't | Y
NSTAR | Fairhaven | 1993 | 2719 | 120 | PV | 2-220-201 | 2011-12-08 | 2011-12-13 | 3 | 0 | 3 | 2011-12-15 | 2012-01-04 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-05 |  | 2012-02-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-16 |  | 2013-01-16 | Online | Private | Y
NSTAR | Fairhaven | 1994 | 2719 | 60 | PV | 2-220-201 | 2011-12-13 | 2011-12-14 | 1 | 0 | 1 | 2011-12-15 | 2012-01-16 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-01-20 |  | 2012-02-15 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-05 | Online | Private | N
NSTAR | Brighton | 1995 | 2135 | 75 | Natural Gas | 329-H3 | 2011-12-13 | 2011-12-16 | 3 | 2 | 1 | 2011-12-20 | 2012-02-02 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-07 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-03-16 |  | 2012-03-16 | Online | Private | Y
NSTAR | New Bedford | 1996 | 2745 | 135 | PV | 2-104-104 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-02-04 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 91 | 0 | 91 |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online | Private | Y
NSTAR | Carver | 1997 | 2355 | 1154 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-02-04 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 91 | 0 | 91 |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online | Private | Y
NSTAR | Carver | 1998 | 2355 | 1154 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-02-04 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 91 | 0 | 91 |  |  | 0 | 0 | 0 | 2011-12-27 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online | Private | Y
NSTAR | Carver | 1999 | 2355 | 1154 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-02-04 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 91 | 0 | 91 |  |  | 0 | 0 | 0 | 2013-09-06 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online | Private | Y
NSTAR | Carver | 2000 | 2355 | 1000 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-02-04 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 91 | 0 | 91 |  |  | 0 | 0 | 0 | 2012-09-06 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-20 | Online | Private | Y
NSTAR | Carver | 2001 | 2355 | 1000 | PV | 3-10-10 | 2011-12-14 | 2011-12-23 | 7 | 5 | 2 | 2011-12-27 | 2012-03-12 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 | 2012-07-11 | 91 | 0 | 91 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Carver | 2002 | 2355 | 200 | PV | 3-10-10 | 2011-12-16 | 2011-12-20 | 2 | 0 | 2 | 2011-12-27 | 2012-03-01 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 |  | 2012-02-24 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Cambridge | 2003 | 2140 | 85 | Natural Gas | 825-20 | 2011-12-16 | 2011-12-20 | 2 | 0 | 2 | 2011-12-27 | 2012-03-01 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-01 |  | 2012-02-24 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-23 | Online | Private | N
NSTAR | Cambridge | 2004 | 2140 | 85 | Natural Gas | 825-20 | 2011-12-20 | 2011-12-23 | 3 | 1 | 2 | 2011-12-27 | 2012-03-01 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-03 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-10-10 |  | 2012-10-10 | Online | Private | Y
NSTAR | New Bedford | 2005 | 2746 | 287.35 | PV | 2-24-182 | 2011-12-20 | 2011-12-22 | 2 | 0 | 2 | 2011-12-22 | 2012-01-11 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-02 |  | 2015-02-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-10-10 | Online | Private | Y
NSTAR | North Truro | 2006 | 2652 | 39 | PV | 4-96-674 | 2011-12-21 | 2011-12-22 | 1 | 0 | 1 | 2012-04-09 | 2012-05-18 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-21 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-20 | Online | Private | Y
NSTAR | Norfolk | 2007 | 2056 | 45 | PV | 146-H3 | 2011-12-28 | 2012-01-03 | 4 | 0 | 4 | 2012-01-03 | 2012-02-06 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-07 |  | 2012-02-28 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-11 |  | 2012-05-11 | Online | Private | Y
NSTAR | Bourne | 2008 | 2532 | 14 | PV | 3-84-961 | 2011-12-28 | 2012-01-12 | 11 | 7 | 4 | 2012-01-16 | 2012-05-09 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-15 |  | 2012-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-08-06 |  | 2013-08-09 | Online | Gov't | Y
NSTAR | Canton | 2009 | 2021 | 360 | PV | 470-H6 | 2012-01-03 | 2012-01-11 | 6 | 5 | 1 | 2012-01-12 | 2012-02-16 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-17 |  | 2012-03-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-05 |  | 2013-08-13 | Online | Gov't | Y
NSTAR | Woburn | 2010 | 1801 | 50 | PV | 211-H8 | 2011-12-28 |  | -29219 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Edgartown | 2011 | 2539 | 1250 | PV | 4-97-97 | 2011-12-15 | 2012-01-09 | 17 | 0 | 17 | 2012-01-10 |  | -29228 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Canton | 2012 | 2021 | 14 | PV | 269-1320H1 | 2012-01-05 | 2012-01-17 | 7 | 5 | 2 | 2012-01-24 | 2012-04-26 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-30 |  | 2012-04-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-08-06 |  | 2013-08-09 | Online | Gov't | Y
NSTAR | Canton | 2013 | 2021 | 225 | PV | 269-1321H2 | 2012-01-05 | 2012-01-17 | 7 | 5 | 2 | 2012-01-27 | 2012-03-19 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-04-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Canton | 2014 | 2021 | 120 | PV | 470-H10 | 2012-01-05 | 2012-02-02 | 19 | 17 | 2 | 2012-02-02 | 2012-03-20 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-22 |  | 2012-03-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-04-20 |  | 2012-05-04 | Online | Private | Y
NSTAR | Kingston | 2015 | 2364 | 60 | PV | 3-17-913 | 2012-01-02 | 2012-02-01 | 21 | 16 | 5 | 2012-02-01 | 2012-03-02 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-05 |  | 2012-02-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-03 | Online | Private | Y
NSTAR | Brewster | 2016 | 2631 | 11 | PV | 4-89B-576 | 2012-01-06 | 2012-01-11 | 3 | 0 | 3 | 2012-01-11 | 2012-02-06 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-27 |  | 2012-03-10 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online | Private | Y
NSTAR | Bourne | 2017 | 2532 | 250 | PV | 4-86-86 | 2011-11-08 | 2012-02-08 | 65 | 20 | 45 | 2012-02-08 | 2012-03-19 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-29 |  | 2012-05-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-06-29 | Online | Gov't | Y
NSTAR | Waltham | 2018 | 2453 | 30 | PV | 3311 | 2012-01-10 | 2012-01-18 | 5 | 4 | 1 | 2012-01-18 | 2012-02-24 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2011-12-23 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-04-23 | Online | Private | Y
NSTAR | Orleans | 2019 | 2653 | 11 | PV | 4-95B-600 | 2012-01-13 | 2012-01-18 | 2 | 2 | 0 | 2012-01-24 | 2012-03-29 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-29 |  | 2012-05-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-07-13 |  | 2012-07-13 | Online | Private | Y
NSTAR | Falmouth | 2020 | 2536 | 750 | PV | 4-98A-98A | 2012-01-16 | 2012-02-27 | 29 | 30 | -1 | 2012-02-27 | 2012-04-30 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-03 |  | 2012-03-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-12-11 |  | 2012-07-13 | Online | Private | Y
NSTAR | Hyde Park | 2021 | 2136 | 975 | PV | 344-07 | 2012-01-16 | 2012-01-24 | 6 | 5 | 1 | 2012-01-27 | 2012-04-06 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-09-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Sharon | 2022 | 2067 | 999 | PV | 146-H1 | 2012-01-17 | 2012-03-20 | 44 | 44 | 0 | 2012-03-20 | 2012-04-11 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-11 |  | 2012-07-03 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-09 | Withdrawn | Gov't | Y
NSTAR | Woburn | 2023 | 1801 | 90 | PV | 375-H4 | 2012-01-18 | 2012-01-24 | 4 | 3 | 1 | 2012-01-24 | 2012-02-22 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-04-05 |  | 2012-04-11 | Online | Private | Y
NSTAR | South Wellfleet | 2024 | 2663 | 60 | PV | 4-94B-653 | 2012-01-19 | 2012-02-06 | 12 | 12 | 0 | 2012-02-06 | 2012-03-19 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 |  | 2012-05-25 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-26 |  | 2012-06-26 | Online | Private | Y
NSTAR | Provincetown | 2025 | 2657 | 34 | PV | 4-96-675 | 2012-01-18 | 2012-01-23 | 3 | 0 | 3 | 2012-01-30 | 2012-02-22 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-04-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-09-06 |  | 2012-09-06 | Online | Private | Y
NSTAR | Fairhaven | 2026 | 2719 | 66 | PV | 2-240-240 | 2012-01-18 | 2012-02-21 | 23 | 21 | 2 | 2012-02-21 | 2012-03-20 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 2027 | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | 23 | 21 | 2 | 2012-02-21 | 2012-03-20 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 2028 | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | 23 | 21 | 2 | 2012-02-21 | 2012-03-20 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 2029 | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | 23 | 21 | 2 | 2012-02-21 | 2012-03-20 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 2030 | 2714 | 1000 | PV | 2-541-541 | 2012-01-18 | 2012-02-21 | 23 | 21 | 2 | 2012-02-21 | 2012-03-20 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 2031 | 2714 | 1000 | PV | 2-541-541 | 2012-01-19 | 2012-02-02 | 10 | 8 | 2 | 2012-02-02 | 2012-03-02 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-02 |  | 2012-06-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-12-27 | Online | Private | Y
NSTAR | Eastham | 2032 | 2642 | 210 | PV | 4-94B-94B | 2012-01-19 | 2012-02-02 | 10 | 8 | 2 | 2012-02-02 | 2012-03-02 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-02 |  | 2012-06-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2012-08-09 | Online | Private | Y
NSTAR | Eastham | 2033 | 2642 | 220 | PV | 4-94B-94B | 2012-01-23 | 2012-01-26 | 3 | 2 | 1 | 2012-01-26 | 2012-02-22 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-23 |  | 2011-12-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-20 | Online | Private | Y
NSTAR | Bedford | 2034 | 1703 | 13 | PV | 533-H8 | 2012-01-16 | 2012-02-02 | 13 | 5 | 8 | 2012-02-02 | 2012-03-16 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-23 | 2013-07-25 | 126 | 0 | 126 |  |  | 0 | 0 | 0 | 2014-07-18 |  | 2012-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage | Gov't | N | 2013-05-28
NSTAR | Plymouth | 2035 | 2360 | 2000 | PV | 3-89-89 | 2012-01-16 | 2012-02-02 | 13 | 5 | 8 | 2012-02-02 | 2012-03-16 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-23 | 2013-07-25 | 126 | 0 | 126 |  |  | 0 | 0 | 0 | 2014-04-18 |  | 2012-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage | Gov't | Y | 2013-05-28
NSTAR | Plymouth | 2036 | 2360 | 500 | PV | 3-89-89 | 2012-01-27 | 2012-02-07 | 7 | 7 | 0 | 2012-02-07 | 2012-04-20 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-23 |  | 2012-12-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-05-17 | Online | Private | Y
NSTAR | Cotuit | 2037 | 2635 | 12 | PV | 4-88-485 | 2012-01-23 | 2012-01-30 | 5 | 1 | 4 | 2012-01-30 | 2012-02-23 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-02-24 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-26 |  | 2012-06-26 | Online | Private | Y
NSTAR | South Yarmouth | 2038 | 2664 | 100 | PV | 4-90-90 | 2012-01-31 | 2012-02-03 | 3 | 3 | 0 | 2012-02-03 | 2012-04-28 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 | 2012-08-09 | 64 | 0 | 64 |  |  | 0 | 0 | 0 | 2012-08-16 |  | 2012-06-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online | Private | N
NSTAR | Ashland | 2039 | 1721 | 1000 | PV | 274-H1 | 2012-01-31 | 2012-02-03 | 3 | 3 | 0 | 2012-02-03 | 2012-04-28 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 | 2012-08-09 | 64 | 0 | 64 |  |  | 0 | 0 | 0 | 2012-08-16 |  | 2012-06-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-02-03 | Online | Private | N
NSTAR | Ashland | 2040 | 1721 | 1000 | PV | 274-H1 | 2012-01-31 | 2012-02-03 | 3 | 3 | 0 | 2012-02-03 | 2012-04-28 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 |  | -29311 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-06-01 | Withdrawn | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Ashland | 2041 | 1721 | 500 | PV | 274-H1 | 2012-01-31 | 2012-02-17 | 13 | 12 | 1 | 2012-02-17 | 2012-03-21 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-07 |  | 2012-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-21 |  | 2012-12-21 | Online | Private | Y
NSTAR | Jamaica Plain | 2042 | 2130 | 100 | PV | 284-1300H1 | 2012-02-01 | 2012-02-13 | 8 | 7 | 1 | 2012-02-13 | 2012-03-20 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 | 2012-06-22 | 65 | 0 | 65 |  |  | 0 | 0 | 0 | 2013-03-30 |  | 2012-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-05-23 | Online | Gov't | N
NSTAR | Sandwich | 2043 | 2563 | 3500 | PV | 4-81B-443 | 2012-02-01 | 2012-02-13 | 8 | 7 | 1 | 2012-02-13 | 2012-03-20 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 | 2012-06-22 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 2012-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Sandwich | 2044 | 2563 | 1500 | PV | 4-81B-443 | 2012-02-03 | 2012-02-21 | 11 | 11 | 0 | 2012-02-21 | 2012-03-16 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-13 | 2012-06-27 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 2012-06-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2045 | 2330 | 2000 | PV | 3-10-10 | 2012-01-25 | 2012-03-01 | 25 | 16 | 9 | 2012-03-01 | 2012-04-25 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-25 |  | 2012-01-27 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-06 |  |  | Withdrawn | Private | Y
NSTAR | Sudbury | 2046 | 1776 | 18 | PV | 342-H2 | 2012-01-24 | 2012-02-22 | 20 | 9 | 11 | 2012-02-22 | 2012-03-19 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-20 |  | 2012-04-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-28 | Online | Private | Y
NSTAR | Roxbury Crossing | 2047 | 2021 | 96 | PV | 483-H6 | 2011-11-15 | 2012-03-08 | 80 | 20 | 60 | 2012-03-08 | 2012-04-09 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-02 |  | 2011-11-15 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-06-12 |  | 2012-06-12 | Online | Private | Y
NSTAR | Plymouth | 2048 | 2360 | 11 | PV | 3-89-925 | 2012-01-02 | 2012-03-26 | 58 | 31 | 27 | 2012-03-26 | 2012-04-26 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 | 2013-01-17 | 106 | 0 | 106 |  |  | 0 | 0 | 0 | 2013-01-24 |  | 2012-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online | Gov't | Y
NSTAR | Mashpee | 2049 | 2649 | 1500 | PV | 4-88-455 | 2012-02-06 | 2012-02-15 | 7 | 3 | 4 | 2012-02-16 | 2012-03-16 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 |  | 2012-06-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-09-26 | Online | Gov't | Y
NSTAR | Vineyard Haven | 2050 | 2568 | 135 | PV | 4-75-75 | 2012-02-10 | 2012-02-22 | 7 | 7 | 0 | 2012-02-22 | 2012-03-30 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-30 |  | 2012-04-10 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-09 | Online | Private | Y
NSTAR | Medfield | 2051 | 2052 | 20 | PV | 456-H3 | 2012-02-09 | 2012-03-27 | 32 | 31 | 1 | 2012-03-28 | 2012-05-04 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-07 |  | 2012-04-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-06-25 |  | 2012-06-26 | Online | Private | Y
NSTAR | Boston | 2052 | 2119 | 18 | PV | 106-1N18H1 | 2012-02-12 |  | -29250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Dennis | 2053 | 2638 | 1250 | PV | 4-92B-92B | 2012-02-12 |  | -29250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Dennis | 2054 | 2638 | 1250 | PV | 4-92B-92B | 2012-02-13 | 2012-02-24 | 8 | 5 | 3 | 2012-08-23 | 2012-09-21 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-01 |  | 2012-07-15 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2012-10-11 |  |  | Withdrawn | Private | Y
NSTAR | West Barnstable | 2055 | 2668 | 581 | PV | 4-82-516 | 2012-02-17 | 2012-02-23 | 3 | 4 | -1 | 2012-02-23 | 2012-05-08 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-11 | 2012-09-19 | 70 | 0 | 70 |  |  | 0 | 0 | 0 | 2012-10-04 |  | 2012-10-31 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-12-23 | 2013-12-23 | 2012-10-11 | Online | Gov't | Y
NSTAR | Acton | 2056 | 1720 | 1500 | PV | 416-H4 | 2012-02-21 | 2012-03-05 | 9 | 7 | 2 | 2012-03-05 | 2012-04-09 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-09 |  | 2012-03-15 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-18 | Online | Gov't | Y
NSTAR | Westport | 2057 | 2790 | 20 | PV | 2-524-524 | 2012-02-21 | 2012-03-01 | 7 | 5 | 2 | 2012-03-01 | 2012-05-21 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-21 |  | 2012-03-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-11-08 |  | 2012-11-08 | Online | Private | Y
NSTAR | Hyannis | 2058 | 2601 | 26 | PV | 4-84A-520 | 2012-02-23 | 2012-02-27 | 2 | 1 | 1 | 2012-02-28 | 2012-03-19 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-03-21 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-07-05 |  | 2012-07-05 | Online | Private | Y
NSTAR | Marion | 2059 | 2738 | 18 | PV | 3-85-969 | 2012-02-24 | 2012-03-13 | 12 | 12 | 0 | 2012-03-13 | 2012-04-23 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-24 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-31 |  | 2012-06-26 | Online | Private | Y
NSTAR | Chelsea | 2060 | 2150 | 30 | PV | 488-H2 | 2012-02-24 | 2012-06-26 | 85 | 86 | -1 | 2012-06-26 | 2012-07-31 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-01 |  | 2012-04-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-24 | Online | Private | Y
NSTAR | Acton | 2061 | 1720 | 12 | PV | 416-H8 | 2012-02-27 | 2012-02-29 | 2 | 2 | 0 | 2012-02-29 | 2012-03-19 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-08 | 2013-08-24 | 303 | 0 | 303 |  |  | 0 | 0 | 0 | 2013-04-08 |  | 2012-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 | 2013-10-02 | 2013-10-02 | 2013-10-04 | Online | Gov't | Y
NSTAR | Plympton | 2062 | 2367 | 4000 | PV | 3-51-901 | 2012-02-27 | 2012-02-29 | 2 | 2 | 0 | 2012-02-29 | 2012-03-19 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-09-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plympton | 2063 | 2367 | 2000 | PV | 3-51-901 | 2012-02-29 | 2012-03-05 | 3 | 3 | 0 | 2012-03-05 | 2012-04-09 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-05-08 |  |  | Withdrawn | Private | Y
NSTAR | West Wareham | 2064 | 2756 | 30 | PV | 3-86-966 | 2012-03-01 | 2012-03-08 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Private | Y | 2012-03-28
NSTAR | New Bedford | 2065 | 2740 | 60 | PV | 2-5-5 | 2010-11-02 | 2010-11-10 | 6 | 5 | 1 | 2010-11-18 | 2010-12-16 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 |  | 2012-08-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Dennis | 2066 | 2660 | 1250 | PV | 4-92B-92B | 2012-03-02 | 2012-03-23 | 15 | 14 | 1 | 2012-03-23 | 2012-05-25 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-25 |  | 2012-05-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-22 | Online | Private | Y
NSTAR | Falmouth | 2067 | 2540 | 70 | PV | 4-98A-461 | 2012-03-06 | 2012-03-08 | 2 | 2 | 0 | 2012-03-08 | 2012-04-09 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-09 |  | 2012-05-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-10 | Online | Private | Y
NSTAR | Oak Bluffs | 2068 | 2575 | 13 | PV | 4-99-99 | 2012-03-01 | 2012-03-06 | 3 | 0 | 3 | 2012-03-07 | 2012-04-09 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-05-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | West Tisbury | 2069 | 2568 | 31 | PV | 4-97-97 | 2012-03-05 | 2012-04-03 | 21 | 19 | 2 | 2012-04-03 | 2012-06-26 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Norfolk | 2070 | 2056 | 5000 | PV | 65-H1 | 2012-03-09 | 2012-03-15 | 4 | 3 | 1 | 2012-03-15 | 2012-04-21 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-16 | 2013-03-25 | 173 | 0 | 173 |  |  | 0 | 0 | 0 |  |  | 2012-11-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Bourne | 2071 | 2532 | 1785 | PV | 4-86-402 | 2012-03-12 | 2012-03-23 | 9 | 9 | 0 | 2012-03-23 | 2012-05-10 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-18 |  | 2012-08-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Milton | 2072 | 2186 | 190 | PV | 362-05 | 2012-03-13 | 2012-03-20 | 5 | 5 | 0 | 2012-03-20 | 2012-04-26 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-04-27 |  | 2012-04-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Private | Y | 2012-04-27
NSTAR | Dartmouth | 2073 | 2747 | 16 | PV | 2-543-543 | 2012-03-14 | 2012-04-09 | 18 | 16 | 2 | 2012-04-09 | 2012-06-11 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-22 |  | -29342 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-09-30 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Wareham | 2074 | 2576 | 1000 | PV | 3-83-83 | 2012-03-19 | 2012-04-19 | 22 | 21 | 1 | 2012-04-19 | 2012-05-23 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-24 |  | 2012-04-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Norfolk | 2075 | 2056 | 82 | PV | 146-H9 | 2012-03-22 | 2012-04-26 | 24 | 22 | 2 | 2012-04-26 | 2012-06-04 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Sandwich | 2076 | 2537 | 6000 | PV | 4-81B-443 | 2012-03-26 | 2012-04-25 | 21 | 21 | 0 | 2012-04-25 | 2012-06-04 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-07 |  | 2012-05-31 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-09-12 |  | 2012-09-12 | Online | Gov't | Y
NSTAR | West Roxbury | 2077 | 2132 | 100 | PV | 468-01 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  | 2012-09-13 | Online | Private | Y
NSTAR | Plymouth | 2078 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2079 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2080 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2081 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2082 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2083 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2084 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2085 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2086 | 2360 | 1000 | PV | 3-89-925 | 2012-03-27 | 2012-04-03 | 5 | 3 | 2 | 2012-04-03 | 2012-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2087 | 2360 | 1000 | PV | 3-89-925 | 2012-03-30 | 2012-04-05 | 4 | 4 | 0 | 2012-07-03 | 2012-08-14 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-30 |  | 2012-03-30 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Hyannis | 2088 | 2601 | 110 | PV | 4-80B-514 | 2012-03-29 | 2012-05-02 | 23 | 23 | 0 | 2012-05-02 | 2012-06-13 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-14 |  | 2012-03-30 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-24 | Online | Private | Y
NSTAR | Canton | 2089 | 2021 | 14 | PV | 269-1320H1 | 2012-03-29 | 2012-04-03 | 3 | 1 | 2 | 2012-04-05 | 2012-06-12 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-15 |  | 2012-06-15 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-07 | Online | Gov't | Y
NSTAR | Falmouth | 2090 | 2540 | 26 | PV | 4-107-830 | 2012-03-30 | 2012-04-05 | 4 | 2 | 2 | 2012-04-05 | 2012-05-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-03-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Natick | 2091 | 1760 | 14 | PV | 240-H1 | 2012-03-30 | 2012-04-03 | 2 | 0 | 2 | 2012-04-13 | 2012-05-23 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-24 |  | 2012-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Assonett | 2092 | 2702 | 12 | PV | 2-605-605 | 2012-04-04 | 2012-04-05 | 1 | 0 | 1 | 2012-04-09 | 2012-05-22 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-23 |  | 2012-09-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Medfield | 2093 | 2081 | 41 | PV | 146-H6 | 2012-04-03 | 2012-04-10 | 5 | 3 | 2 | 2012-04-10 | 2012-05-09 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-09 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-21 | Online | Private | Y
NSTAR | Marshfield | 2094 | 2050 | 334 | PV | 3-25-908 | 2012-04-04 | 2012-04-06 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Private | Y | 2012-05-04
NSTAR | Brookline | 2095 | 2467 | 51 | PV | 369-07 | 2012-04-04 | 2012-04-06 | 2 | 0 | 2 | 2012-04-06 | 2012-05-10 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-29 |  | 2012-08-17 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Private | Y | 2012-06-29
NSTAR | Brookline | 2096 | 2467 | 111 | PV | 369-07 | 2012-04-10 | 2012-05-24 | 31 | 31 | 0 | 2012-05-24 | 2012-07-18 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-18 |  | 2012-05-17 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-07-24 | Online | Private | Y
NSTAR | Kingston | 2097 | 2364 | 11 | PV | 3-909-909 | 2012-04-11 | 2012-04-12 | 1 | 1 | 0 | 2012-04-12 | 2012-05-04 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-05-04 |  |  | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-09-05 | Online | Private | Y
NSTAR | West Tisbury | 2098 | 2575 | 13 | PV | 4-97-226 | 2012-04-12 | 2012-06-27 | 52 | 54 | -2 | 2012-06-27 | 2012-08-07 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-16 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-06 | Online | Private | Y
NSTAR | West Roxbury | 2099 | 1746 | 60 | PV | 468-01 | 2012-04-13 | 2012-08-29 | 95 | 96 | -1 | 2012-08-29 | 2012-10-04 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-07-03 | Online | Private | Y
NSTAR | Dorchester | 2100 | 2124 | 60 | Natural Gas | 511-1495H | 2012-04-13 | 2012-08-29 | 95 | 96 | -1 | 2012-08-29 | 2012-10-09 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-11 | Online | Private | Y
NSTAR | East Boston | 2101 | 2128 | 60 | Natural Gas | MC-8 | 2012-04-17 | 2012-04-17 | 0 | 0 | 0 | 2012-11-13 | 2013-04-09 | 100 | 0 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage | Private | Y
NSTAR | Plymouth | 2102 | 2360 | 2000 | Wind | 3-89-925 | 2012-04-17 | 2012-04-17 | 0 | 0 | 0 | 2012-11-13 | 2013-04-09 | 100 | 0 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2016-08-10 | Online | Private | Y
NSTAR | Plymouth | 2103 | 2360 | 4000 | Wind | 3-89-925 | 2012-04-17 | 2012-04-17 | 0 | 0 | 0 | 2012-11-13 | 2013-04-09 | 100 | 0 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2016-08-10 | Online | Private | Y
NSTAR | Plymouth | 2104 | 2360 | 1500 | Wind | 3-89-925 | 2012-04-18 | 2012-04-20 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-08-10 | Online | Private | Y | 2013-07-24
NSTAR | Carver | 2105 | 2330 | 833 | PV | 3-10-929 | 2012-04-17 | 2012-04-19 | 2 | 1 | 1 | 2012-04-19 | 2012-05-30 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-22 | 2013-04-12 | 202 | 0 | 202 |  |  | 0 | 0 | 0 | 2013-11-15 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2016-07-01 | Online | Private | Y
NSTAR | Plymouth | 2106 | 2360 | 500 | PV | 3-11-11 | 2012-04-18 | 2012-04-25 | 5 | 4 | 1 | 2012-04-25 | 2012-07-09 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-10 |  | 2012-06-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-06-12 | Online | Private | Y
NSTAR | Assonett | 2107 | 2702 | 13 | PV | 2-605-605 | 2012-04-19 | 2012-04-20 | 1 | 0 | 1 | 2012-04-24 | 2012-06-04 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-06 |  | 2012-07-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-03-01 |  | 2012-09-21 | Online | Private | Y
NSTAR | South Boston | 2108 | 2127 | 75 | Natural Gas | 106-H3 | 2012-04-19 | 2012-04-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | 2013-01-22 |  | 2013-01-22 | Online | Private | Y
NSTAR | Freetown | 2109 | 2717 | 648.98 | PV | 2-102-604 | 2012-04-21 | 2012-05-01 | 7 | 5 | 2 | 2012-05-01 | 2012-06-26 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-29 |  | 2012-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-22 | Online | Gov't | Y
NSTAR | Natick | 2110 | 1760 | 260 | PV | 240-H1 | 2012-04-23 | 2012-04-27 | 4 | 2 | 2 | 2012-04-27 | 2012-06-25 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-26 |  | 2012-09-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-06 | Online | Gov't | Y
NSTAR | Natick | 2111 | 1760 | 50 | PV | 240-H2 | 2012-04-23 | 2012-06-11 | 34 | 33 | 1 | 2012-06-11 | 2012-07-06 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-11 |  | 2012-05-19 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-10 | Online | Private | Y
NSTAR | Holliston | 2112 | 1746 | 18 | PV | 65-H5 | 2012-04-23 | 2012-05-24 | 23 | 21 | 2 | 2012-05-24 | 2012-06-23 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-11 |  | 2012-05-17 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-09 | Online | Private | Y
NSTAR | Vineyard Haven | 2113 | 2568 | 19 | PV | 4-75-75 | 2012-04-23 | 2012-05-01 | 6 | 4 | 2 | 2012-05-01 | 2012-06-05 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-06-12 |  | 2012-08-01 | TBD | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-28 | Online | Gov't | Y
NSTAR | Aquinnah | 2114 | 2575 | 54 | PV | 4-97-126 | 2012-04-21 | 2012-04-30 | 6 | 3 | 3 | 2012-04-30 | 2012-06-11 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-24 | 2013-09-19 | 226 | 0 | 226 |  |  | 0 | 0 | 0 | 2013-04-22 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-12 | Online | Gov't | Y
NSTAR | Dennis | 2115 | 2660 | 2500 | PV | 4-92B-92B | 2012-04-21 | 2012-04-30 | 6 | 3 | 3 | 2012-04-30 | 2012-06-11 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-24 |  | -29427 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Dennis | 2116 | 2660 | 1250 | PV | 4-92B-92B | 2012-04-25 | 2012-05-01 | 4 | 3 | 1 | 2012-05-01 | 2012-06-05 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-12 |  | 2012-07-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage | Private | Y | 2013-01-07
NSTAR | Marion | 2117 | 2740 | 1000 | PV | 3-85-85 | 2012-04-27 | 2012-05-01 | 2 | 2 | 0 | 2012-05-03 | 2012-06-06 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Plymouth | 2118 | 2360 | 1000 | PV | 3311 | 2012-04-27 | 2012-05-01 | 2 | 2 | 0 | 2012-05-03 | 2012-06-12 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Plymouth | 2119 | 2360 | 2000 | PV | 3-89-926 | 2012-05-01 | 2012-05-07 | 4 | 3 | 1 | 2012-05-08 | 2012-07-27 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-13 |  | 2013-08-29 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Walpole | 2120 | 2071 | 1000 | PV | 146-H9 | 2012-05-01 | 2012-05-07 | 4 | 3 | 1 | 2012-05-08 | 2012-07-27 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-13 |  | 2013-08-29 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-02-03 | Online | Private | Y
NSTAR | Walpole | 2121 | 2071 | 1398.22 | PV | 146-H9 | 2012-05-02 | 2012-05-04 | 2 | 2 | 0 | 2012-05-04 | 2012-07-09 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-12 |  | 2012-05-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-08-10 |  | 2015-02-03 | Online | Gov't | Y
NSTAR | Carver | 2122 | 2330 | 95 | PV | 3-10-930 | 2012-05-04 | 2012-05-16 | 8 | 8 | 0 | 2012-05-22 | 2012-08-03 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-22 |  | 2012-10-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Private | Y | 2012-08-22
NSTAR | Woburn | 2123 | 1801 | 288 | PV | 375-H1 | 2012-05-04 | 2012-05-07 | 1 | 1 | 0 | 2012-05-08 | 2012-06-15 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plympton | 2124 | 2367 | 1500 | PV | 3-51-43J1 | 2012-05-04 | 2012-05-07 | 1 | 1 | 0 | 2012-05-08 | 2012-06-15 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plympton | 2125 | 2367 | 1000 | PV | 3-51-43J1 | 2012-05-04 | 2012-05-07 | 1 | 1 | 0 | 2012-05-08 | 2012-06-15 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plympton | 2126 | 2367 | 1000 | PV | 3-51-43J1 | 2012-05-04 | 2012-05-07 | 1 | 1 | 0 | 2012-05-08 | 2012-06-15 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plympton | 2127 | 2367 | 1000 | PV | 3-51-43J1 | 2012-05-08 | 2012-05-15 | 5 | 5 | 0 | 2012-05-15 | 2012-07-03 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-24 | 2013-02-11 | 74 | 0 | 74 |  |  | 0 | 0 | 0 | 2013-05-10 |  | 2012-11-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Wareham | 2128 | 2571 | 583 | PV | 4-83-83 | 2012-05-10 | 2012-06-11 | 21 | 22 | -1 | 2012-06-11 | 2012-07-23 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-27 |  | 2012-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-27 | Online | Private | Y
NSTAR | Wayland | 2129 | 1778 | 150 | PV | 342-H1 | 2012-05-11 |  | -29313 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2012-11-16 | Online | Gov't | Y
NSTAR | Wareham | 2130 | 2571 | 583 | PV | 3-83-83 | 2012-05-11 | 2012-05-14 | 1 | 0 | 1 | 2012-05-14 | 2012-07-09 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-12 |  | 2012-07-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Newton | 2131 | 2465 | 11 | PV | 1707 | 2012-05-15 | 2012-05-25 | 8 | 8 | 0 | 2012-05-29 | 2012-07-13 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-06 |  | 2012-07-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-14 | Online | Private | Y
NSTAR | Norfolk | 2132 | 2056 | 14 | PV | 146-H3 | 2012-05-16 | 2012-06-27 | 29 | 30 | -1 | 2012-06-27 | 2012-07-31 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-02 |  | 2012-06-18 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-07 |  | 2012-12-07 | Online | Gov't | Y
NSTAR | Boston | 2133 | 2218 | 102 | PV | 574-70H | 2012-05-14 | 2012-06-01 | 13 | 12 | 1 | 2012-06-01 | 2012-07-13 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-19 |  | 2012-06-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-08-24 | Online | Private | Y
NSTAR | Dover | 2134 | 2030 | 13 | PV | 456-H3 | 2012-05-16 | 2012-06-01 | 11 | 12 | -1 | 2012-06-01 | 2012-07-06 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-18 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Private | Y | 2012-07-18
NSTAR | Lincoln | 2135 | 1733 | 11 | PV | 282-H1 | 2012-05-17 | 2012-05-17 | 0 | 0 | 0 | 2012-05-22 | 2012-06-15 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-20 |  | 2012-10-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-27 | Online | Private | Y
NSTAR | Dartmouth | 2136 | 2747 | 276 | PV | 2-543-543 | 2012-05-21 | 2012-05-21 | 0 | 0 | 0 | 2012-05-22 | 2012-08-02 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | East Walpole | 2137 | 2032 | 360 | PV | 135-1319H1 | 2012-05-21 | 2012-11-26 | 130 |  | 130 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Design Stage | Private | Y
NSTAR | Boston | 2138 | 2114 | 555 | Natural Gas | 2-1N11 | 2012-05-22 |  | -29320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Boston | 2140 | 2118 | 60 | Natural Gas | 528-129H | 2012-05-23 | 2012-09-19 | 82 | 84 | -2 | 2012-09-19 | 2013-01-07 | 74 | 25 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-14 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-06-11 | Online | Gov't | Y
NSTAR | Buzzards Bay | 2141 | 2532 | 96 | PV | 3-84-965 | 2012-05-22 | 2012-06-29 | 27 | 26 | 1 | 2012-06-29 | 2012-08-06 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-15 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-12-10 | Online | Private | Y
NSTAR | Wayland | 2142 | 1778 | 19 | PV | 278-H2 | 2012-05-30 | 2012-06-20 | 15 | 13 | 2 | 2012-06-20 | 2012-07-09 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-09 |  | 2012-12-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-23 | Online | Gov't | Y
NSTAR | Duxbury | 2143 | 2331 | 500 | PV | 3-26-903 | 2012-06-04 | 2012-06-19 | 11 | 10 | 1 | 2012-06-19 | 2012-11-30 | 114 | 0 | 114 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-30 |  | 2012-10-02 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-12-26 |  | 2014-06-23 | Online | Gov't | Y
NSTAR | Framingham | 2144 | 1702 | 500 | PV | 455-H6 | 2012-06-01 | 2012-06-14 | 9 | 7 | 2 | 2012-06-14 | 2012-07-19 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-07-23 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-26 | Online | Private | Y
NSTAR | West Tisbury | 2145 | 2568 | 13 | PV | 4-97-220 | 2012-05-23 | 2012-09-27 | 88 | 82 | 6 | 2012-09-27 | 2012-10-04 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-04 | 2013-01-29 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 2013-06-10 |  | 2012-10-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | New Bedford | 2146 | 2745 | 1750 | PV | 2-102-102 | 2012-06-01 | 2012-08-07 | 46 | 45 | 1 | 2013-03-12 | 2013-04-09 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2012-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Private | Y | 2013-04-13
NSTAR | Canton | 2147 | 2021 | 260 | PV | 470-H11 | 2012-06-01 | 2012-08-06 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2013-08-06 | Eng Stage: Awaiting Customer's Response/Docs | Private | Y | 2012-09-24
NSTAR | Canton | 2148 | 2021 | 200 | PV | 470-H11 | 2012-06-05 | 2012-06-08 | 3 | 0 | 3 | 2012-06-08 | 2012-08-30 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-30 |  | 2012-09-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-05 |  | 2012-12-05 | Online | Private | Y
NSTAR | New Bedford | 2149 | 2745 | 100 | PV | 2-103-103 | 2012-06-06 | 2012-06-08 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Design Stage | Private | N
NSTAR | Cambridge | 2150 | 2142 | 1966 | Natural Gas | 814-17 | 2012-06-11 | 2012-07-26 | 32 | 30 | 2 | 2012-07-27 | 2012-08-31 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-09-04 |  | 2012-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-29 | Online | Gov't | Y
NSTAR | Millis | 2151 | 2054 | 135 | PV | 146-H10 | 2012-06-07 | 2012-09-27 | 78 | 75 | 3 | 2012-09-27 | 2012-10-04 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-10-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | New Bedford | 2152 | 2745 | 1750 | PV | 2-102-102 | 2012-06-18 | 2012-10-23 | 88 | 89 | -1 | 2012-10-23 | 2012-11-27 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-22 |  | 2012-08-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-17 | Online | Private | Y
NSTAR | Weston | 2153 | 2493 | 60 | PV | 450-H7 | 2012-06-18 | 2012-07-20 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Private | Y | 2012-08-29
NSTAR | Marshfield | 2154 | 2500 | 14 | PV | 3-25-25 | 2012-06-20 | 2012-08-16 | 40 | 33 | 7 | 2012-08-16 | 2012-12-14 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-15 | 2012-12-14 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 2013-06-05 |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-06-06 | Online | Gov't | Y
NSTAR | West Wareham | 2156 | 2576 | 60 | PV | 3-86-966 | 2012-06-20 | 2012-08-16 | 40 | 33 | 7 | 2012-08-16 | 2012-09-21 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Plymouth | 2157 | 2360 | 2000 | PV | 3-89-89 | 2012-06-20 | 2012-08-16 | 40 | 33 | 7 | 2012-08-16 | 2012-09-21 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Plymouth | 2158 | 2360 | 2000 | PV | 3-89-89 | 2012-06-27 | 2012-08-16 | 35 | 29 | 6 | 2012-08-16 | 2012-09-17 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-09-18 |  | 2012-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  |  | Private | Y
NSTAR | Hyannis | 2159 | 2601 | 60 | PV | 4-63-905 | 2012-06-28 | 2012-07-24 | 17 | 12 | 5 | 2012-07-24 | 2012-08-28 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-31 |  | 2012-08-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-08 | Online | Private | Y
NSTAR | Newton Center | 2160 | 2459 | 11 | PV | 467-H12 | 2012-07-02 | 2012-08-15 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Gov't | Y | 2013-04-29
NSTAR | Burlington | 2161 | 1805 | 3000 | Natural Gas | 541-1377H | 2012-07-13 | 2012-07-25 | 8 | 7 | 1 | 2012-07-25 | 2012-11-06 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-23 |  | 2012-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2162 | 2360 | 142 | PV | 3-13-936 | 2012-07-10 | 2012-07-18 | 6 | 1 | 5 | 2012-07-18 | 2012-08-24 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-19 |  | 2012-12-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Private | Y | 2012-08-28
NSTAR | Boston | 2163 | 2210 | 250 | Natural Gas | 385-H5 | 2012-07-10 | 2012-08-10 | 23 | 17 | 6 | 2012-08-10 | 2012-10-01 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-11 | 2013-12-11 | 125 | 0 | 125 |  |  | 0 | 0 | 0 |  |  | 2013-06-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Acusnet | 2164 | 2743 | 2000 | PV | 2-241-327 | 2012-07-10 | 2012-08-10 | 23 | 17 | 6 | 2012-08-10 | 2012-10-01 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Acusnet | 2165 | 2743 | 1000 | PV | 2-241-327 | 2012-07-10 | 2012-08-10 | 23 | 17 | 6 | 2012-08-10 | 2012-10-01 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-30 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Acusnet | 2166 | 2743 | 2000 | PV | 2-241-327 | 2012-07-18 | 2012-07-25 | 5 | 3 | 2 | 2012-07-27 | 2012-11-18 | 78 | 0 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-19 |  | 2012-12-31 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | South Dennis | 2167 | 2660 | 500 | PV | 4-89A-553 | 2012-07-18 | 2012-07-27 | 7 | 5 | 2 | 2012-07-27 | 2012-12-18 | 99 | 8 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-01 | 2013-09-11 | 133 | 0 | 133 |  |  | 0 | 0 | 0 | 2013-08-08 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-11-19 | Online | Gov't | Y
NSTAR | West Yarmouth | 2168 | 2673 | 750 | PV | 4-92A-92A | 2012-07-18 | 2012-07-27 | 7 | 5 | 2 | 2012-07-27 | 2013-01-10 | 114 | 0 | 114 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-06 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-02-27 | Online | Gov't | Y
NSTAR | West Yarmouth | 2169 | 2673 | 200 | PV | 4-92A-92A | 2012-07-20 | 2012-07-26 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Private | Y | 2012-09-14
NSTAR | Woburn | 2170 | 1801 | 485 | PV | 375-H4 | 2012-07-20 | 2012-07-31 | 7 | 5 | 2 | 2012-08-01 | 2012-09-17 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-11 |  | 2012-08-24 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2012-11-15 |  |  | Withdrawn | Private | Y
NSTAR | Marshfield | 2171 | 2050 | 82 | PV | 3-24A-24A | 2012-07-24 | 2012-10-22 | 62 | 64 | -2 | 2012-10-22 | 2013-02-10 | 75 | 0 | 75 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-01 |  | -29514 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-08 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | West Yarmouth | 2172 | 2673 | 750 | PV | 4-92A-92A | 2012-07-25 | 2012-11-30 | 89 | 92 | -3 | 2012-11-30 | 2013-02-07 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-22 | 2013-03-20 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 2013-06-19 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | South Yarmouth | 2173 | 2664 | 500 | PV | 4-92B-560 | 2012-07-25 | 2012-10-31 | 68 | 70 | -2 | 2012-10-31 | 2013-03-08 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-14 | Online | Gov't | Y
NSTAR | West Dennis | 2174 | 2122 | 75 | PV | 4-92B-92B | 2012-07-25 | 2012-11-30 | 89 | 92 | -3 | 2012-11-30 | 2012-12-20 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-22 | 2013-03-20 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 2013-05-05 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-03-05 | Online | Gov't | Y
NSTAR | South Yarmouth | 2175 | 2664 | 500 | PV | 4-92B-560 | 2012-07-25 | 2012-08-06 | 8 | 8 | 0 | 2012-08-06 | 2012-09-11 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-08-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-10-24 | 2013-10-24 | 2015-03-05 | Online | Gov't | Y
NSTAR | Sudbury | 2176 | 1776 | 1333 | PV | 342-H3 | 2012-07-26 | 2012-08-15 | 14 | 14 | 0 | 2012-08-16 | 2012-09-28 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-14 |  | 2012-08-06 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-18 | Online | Gov't | Y
NSTAR | Wayland | 2177 | 1778 | 12 | PV | 278-H2 | 2012-07-30 |  | -29367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Buzzards Bay | 2178 | 2532 | 50 | PV | 3-88-88 | 2012-07-30 |  | -29367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Buzzards Bay | 2179 | 2532 | 21 | PV | 3-89-925 | 2012-07-30 | 2012-10-22 | 58 | 59 | -1 | 2012-12-18 | 2013-01-22 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-31 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Gov't | Y | 2013-01-31
NSTAR | Bourne | 2180 | 2532 | 425 | PV | 4-86-402 | 2013-05-01 | 2013-05-03 | 2 | 0 | 2 | 2013-05-03 | 2013-06-18 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 | 2013-09-19 | 61 | 0 | 61 |  |  | 0 | 0 | 0 | 2013-12-30 |  | 2013-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-04-15 | Online | Gov't | Y
NSTAR | Hyannis | 2181 | 2601 | 4500 | PV | 4-84B-524 | 2012-07-30 |  | -29367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Forestdale | 2182 | 2644 | 100 | PV | 4-81B-443 | 2012-07-30 | 2012-11-06 | 69 | 70 | -1 | 2012-11-06 | 2012-12-20 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-08 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-15 | Online | Gov't | Y
NSTAR | Provincetown | 2183 | 2657 | 135 | PV | 4-96-675 | 2012-07-30 |  | -29367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | East Sandwich | 2184 | 2537 | 200 | PV | 4-81B-443 | 2012-07-30 | 2012-08-22 | 17 | 16 | 1 | 2012-08-22 | 2012-09-24 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-29 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Hyannis | 2185 | 2601 | 500 | PV | 4-80B-514 | 2012-07-30 | 2012-08-22 | 17 | 16 | 1 | 2012-08-22 | 2012-11-16 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-30 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-20 | Online | Gov't | Y
NSTAR | Marston Mills | 2186 | 2648 | 61 | PV | 4-88-88 | 2012-07-30 | 2012-10-16 | 54 |  | 54 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Impact Study Fee & Agreement | Gov't | Y | 2013-01-15
NSTAR | Chatham | 2188 | 2633 | 868 | PV | 4-95B-95B | 2012-07-30 | 2012-10-23 | 59 | 59 | 0 | 2012-10-23 | 2012-12-20 | 41 | 2 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-06 | 2013-03-20 | 29 | 0 | 29 |  |  | 0 | 0 | 0 | 2013-07-30 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-12-31 | Online | Gov't | Y
NSTAR | West Tisbury | 2189 | 2568 | 850 | PV | 4-91-220 | 2012-07-30 | 2012-10-23 | 59 | 59 | 0 | 2013-04-08 | 2013-05-03 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-08 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Vineyard Haven | 2190 | 2568 | 50 | PV | 4-97-228 | 2012-07-30 | 2012-08-21 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-07-17 | Online | Gov't | N
NSTAR | Assonett | 2191 | 2702 | 1500 | PV | 2-606-605 | 2012-07-30 | 2012-12-17 | 97 |  | 97 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | Gov't | Y
NSTAR | Barnstable | 2192 | 2601 | 1250 | PV | 4-80B-80B | 2012-07-30 | 2012-12-17 | 97 |  | 97 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Barnstable | 2193 | 2601 | 1750 | PV | 4-80B-80B | 2012-07-30 |  | -29367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | East Sandwich | 2194 | 2537 | 200 | PV | 4-81B-443 | 2012-07-30 | 2012-10-23 | 59 | 59 | 0 | 2012-10-23 | 2013-01-03 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-30 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Buzzards Bay | 2195 | 2532 | 35 | PV | 3-88-88 | 2012-08-02 | 2012-08-06 | 2 | 2 | 0 | 2012-08-08 | 2012-09-11 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-09-12 |  | 2012-08-13 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-25 | Online | Private | Y
NSTAR | Needham | 2196 | 2492 | 14 | PV | 148-01 | 2012-08-02 | 2012-08-13 | 7 | 7 | 0 | 2012-08-14 | 2012-10-18 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-25 |  | 2012-09-13 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-01-10 | Online | Private | Y
NSTAR | Natick | 2197 | 1760 | 14 | PV | 433-H5 | 2012-08-01 | 2012-08-23 | 16 | 14 | 2 | 2012-08-23 | 2012-11-19 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-04 |  | 2012-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2012-12-29 | Online | Gov't | Y
NSTAR | West Tisbury | 2198 | 2575 | 34 | PV | 4-97-97 | 2012-08-03 | 2012-09-13 | 28 | 29 | -1 | 2012-09-13 | 2012-12-20 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-08 |  | 2012-12-31 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Gov't | Y | 2013-01-08
NSTAR | Eastham | 2199 | 2642 | 500 | PV | 4-94B-646 | 2012-08-03 |  | -29371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Oak Bluffs | 2200 | 2557 | 100 | PV | 4-75-75 | 2012-08-03 |  | -29371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Provincetown | 2201 | 2657 | 50 | PV | 4-96-675 | 2012-08-06 | 2012-08-23 | 13 | 13 | 0 | 2012-08-23 | 2012-10-04 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Hyannis | 2202 | 2601 | 2000 | PV | 4-92-92 | 2012-08-06 | 2012-08-23 | 13 | 13 | 0 | 2012-08-23 | 2012-10-04 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Hyannis | 2203 | 2601 | 1000 | PV | 4-92-92 | 2012-08-06 | 2012-08-23 | 13 | 13 | 0 | 2012-08-23 | 2012-10-04 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Hyannis | 2204 | 2601 | 2000 | PV | 4-92-92 | 2012-08-06 | 2012-12-27 | 99 | 103 | -4 | 2012-12-27 | 2013-01-29 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-10 |  | -29646 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-18 |  | 2012-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Brewster | 2205 | 2631 | 750 | PV | 4-89B-576 | 2012-08-06 | 2012-12-14 | 91 | 94 | -3 | 2012-12-21 | 2013-01-29 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-10 |  | -29646 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-18 |  | 2012-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Brewster | 2206 | 2631 | 3000 | PV | 4-95B-600 | 2012-08-07 |  | -29373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Brewster | 2207 | 2631 | 1000 | PV | 4-95B-600 | 2012-08-07 |  | -29373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 2208 | 2747 | 500 | PV | 2-543-543 | 2012-08-06 | 2012-11-07 | 65 | 66 | -1 | 2012-11-07 | 2013-01-22 | 50 | 13 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-04 | 2013-07-25 | 76 | 0 | 76 |  |  | 0 | 0 | 0 | 2013-08-05 |  | 2013-10-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Dartmouth | 2209 | 2747 | 3500 | PV | 2-532-532 | 2012-08-07 |  | -29373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 2210 | 2747 | 1000 | PV | 2-543-543 | 2012-08-07 |  | -29373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dartmouth | 2211 | 2747 | 1000 | PV | 2-532-532 | 2012-08-08 | 2012-08-21 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Dartmouth | 2212 | 2747 | 1000 | PV | 2-532-532 | 2012-08-08 | 2012-08-21 | 9 | 9 | 0 | 2012-08-23 | 2012-10-01 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Dartmouth | 2213 | 2747 | 1000 | PV | 2-532-532 | 2012-08-08 | 2012-10-12 | 45 | 47 | -2 | 2012-10-12 | 2012-11-30 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-04 | 2013-09-11 | 171 | 0 | 171 |  |  | 0 | 0 | 0 |  |  | 2012-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Westport | 2214 | 2790 | 500 | PV | 2-523-523 | 2012-08-09 |  | -29375 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Freetown | 2215 | 2717 | 1500 | PV | 2-102-102 | 2012-08-13 | 2012-08-13 | 0 | 0 | 0 | 2012-08-13 | 2012-09-18 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | North Dartmouth | 2216 | 2747 | 100 | PV | 2-543-543 | 2012-08-10 | 2012-08-15 | 3 | 2 | 1 | 2012-08-15 | 2012-09-20 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-06 |  | 2012-12-31 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-02-21 | Online | Gov't | Y
NSTAR | Orleans | 2217 | 2653 | 500 | PV | 4-95B-95B | 2012-08-10 | 2012-09-25 | 31 | 30 | 1 | 2012-09-25 | 2012-10-25 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-03-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Boston | 2218 | 2210 | 500 | PV | 385-H12 | 2012-08-14 |  | -29378 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Freetown | 2219 | 2717 | 1500 | PV | 2-102-102 | 2012-08-14 |  | -29378 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Freetown | 2220 | 2717 | 1500 | PV | 2-102-102 | 2012-08-16 | 2012-08-21 | 3 | 3 | 0 | 2012-08-22 | 2012-10-19 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-30 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-06-12 | 2013-06-12 |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2221 | 2360 | 649.74 | PV | 3-13-13 | 2012-08-15 | 2012-08-17 | 2 | 1 | 1 | 2012-08-17 | 2012-09-20 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-15 |  | 2012-09-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-12 | Online | Private | Y
NSTAR | Vineyard Haven | 2222 | 2568 | 12 | PV | 4-91-122 | 2012-08-07 | 2012-08-27 | 14 | 7 | 7 | 2012-08-27 | 2012-10-15 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-09-09 | Online | Private | Y
NSTAR | Sagamore Beach | 2223 | 2562 | 250 | PV | 3-89-925 | 2012-07-17 | 2012-08-21 | 25 | 3 | 22 | 2012-08-21 | 2012-09-24 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-16 |  | 2012-10-03 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-04 |  | 2014-09-09 | Online | Private | Y
NSTAR | Rochester | 2224 | 2770 | 17 | PV | 3-702-702 | 2012-08-16 | 2012-08-17 | 1 | 1 | 0 | 2012-10-12 | 2013-01-15 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Allston | 2225 | 2134 | 354 | PV | 467-H11 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-11-19 | 64 | 21 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-14 |  | 2013-08-29 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs and NSTARwork completion | Gov't | Y
NSTAR | Wareham | 2226 | 2538 | 4000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-10-03 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Wareham | 2227 | 2538 | 1000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-10-03 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Wareham | 2228 | 2538 | 1000 | PV | 3-83-83 | 2012-08-16 | 2012-08-17 | 1 | 0 | 1 | 2012-08-17 | 2012-10-03 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Wareham | 2229 | 2538 | 1000 | PV | 3-83-83 | 2012-08-20 | 2012-08-27 | 5 | 5 | 0 | 2012-08-27 | 2012-10-09 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-15 |  | 2012-09-25 | No | EXP |  |  |  | 0 | 0 | 0 |  | 2013-03-11 |  |  | Private | Y
NSTAR | Dover | 2230 | 2030 | 23 | PV | 456-H5 | 2012-08-24 |  | -29386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Westport | 2231 | 2790 | 500 | PV | 2-523-523 | 2012-08-24 | 2012-09-06 | 8 | 8 | 0 | 2012-09-06 | 2012-11-26 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-04 |  | 2012-09-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Lincoln | 2232 | 1733 | 13 | PV | 320-H6 | 2012-08-24 | 2012-08-30 | 4 | 3 | 1 | 2012-08-30 | 2013-06-26 | 204 | 0 | 204 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2014-06-24 |  |  | Awaiting Witness test | Gov't | Y
NSTAR | Newton | 2233 | 2460 | 260 | PV | 17-H1 | 2012-08-24 | 2012-08-30 | 4 | 3 | 1 | 2012-08-30 | 2012-11-25 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-24 | Online | Gov't | Y
NSTAR | Newton | 2234 | 2461 | 100 | PV | 433-02 | 2012-08-24 | 2012-08-30 | 4 | 3 | 1 | 2012-08-30 | 2012-09-27 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-05 | 2012-09-01 | -126 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-27 |  | 2012-09-01 | No | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-26 | Online | Gov't | Y
NSTAR | Newton | 2235 | 2459 | 200 | PV | 292-H8 | 2012-08-27 | 2012-08-30 | 3 | 3 | 0 | 2013-09-06 | 2013-10-10 | 24 | 228 | -204 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-26 | Online | Gov't | Y
NSTAR | Lexington | 2236 | 2421 | 260 | PV | 533-H2 | 2012-08-29 |  | -29389 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Barnstable | 2237 | 2360 | 11 | PV | 4-82-518 | 2012-08-29 | 2012-10-16 | 32 | 34 | -2 | 2012-10-16 | 2013-01-30 | 72 | 65 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2238 | 2360 | 95 | PV | 3-12-12 | 2012-08-29 | 2012-09-05 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Private | Y | 2012-09-21
NSTAR | West Yarmouth | 2239 | 2673 | 150 | PV | 4-92A-536 | 2012-08-30 | 2012-10-03 | 23 | 24 | -1 | 2012-10-03 | 2013-03-18 | 112 | 0 | 112 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dorchester | 2240 | 2122 | 95 | PV | 511-1498H1 | 2012-08-28 | 2012-09-12 | 10 | 3 | 7 | 2012-09-12 | 2013-04-29 | 156 | 0 | 156 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2012-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-01-06 | Online | Private | Y
NSTAR | New Bedford | 2241 | 2740 | 190 | PV | 2-81-94 | 2012-08-21 | 2012-09-07 | 12 | 6 | 6 | 2012-09-07 | 2012-09-11 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-31 |  | 2012-10-30 | Yes | EXP |  |  |  | 0 | 0 | 0 | 2013-09-11 | 2013-09-11 | 2013-10-11 | Online | Private | Y
NSTAR | New Bedford | 2242 | 2740 | 225 | PV | 2-84-84 | 2012-08-22 | 2012-09-07 | 11 | 5 | 6 | 2012-09-07 | 2012-11-16 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-12 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-10-11 | Online | Private | Y
NSTAR | East Falmouth | 2243 | 2536 | 11 | PV | 4-98B-449 | 2012-08-31 | 2012-09-06 | 3 | 4 | -1 | 2012-09-06 | 2012-10-05 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-11-13 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-30 | 2013-01-30 | 2013-01-30 | Online | Gov't | Y
NSTAR | Lexington | 2244 | 2421 | 56 | PV | 320-H5XY | 2012-08-30 | 2012-09-11 | 7 | 5 | 2 | 2012-09-11 | 2013-01-07 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-13 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-04-23 | 2013-04-23 | 2013-04-23 | Online | Gov't | Y
NSTAR | Harwich | 2245 | 2661 | 20 | PV | 320-H5XY | 2012-09-05 | 2012-12-05 | 63 | 65 | -2 | 2012-12-05 | 2013-02-01 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-05 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-02-21 | 2013-02-21 | 2013-02-21 | Online | Private | Y
NSTAR | Walpole | 2246 | 2081 | 300 | PV | 4-85-592 | 2012-09-05 | 2012-09-26 | 15 | 15 | 0 | 2012-09-26 | 2012-12-18 | 57 | 46 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-10 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-21 | Online | Private | Y
NSTAR | Canton | 2247 | 2021 | 237 | PV | 135-1319H1 | 2012-09-05 | 2012-09-10 | 3 | 3 | 0 | 2012-09-10 | 2012-11-25 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-10-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-04 | Online | Private | Y
NSTAR | Woburn | 2248 | 1801 | 12 | PV | 211-H5 | 2012-09-04 | 2012-09-11 | 5 | 3 | 2 | 2012-09-11 | 2012-11-14 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-15 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Newton | 2250 | 2461 | 50 | PV | 292-H11 | 2012-09-06 | 2013-05-10 | 169 | 175 | -6 | 2013-05-10 | 2013-06-18 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | N
NSTAR | Assonett | 2251 | 2702 | 500 | PV | 2-605-605 | 2012-09-14 | 2012-09-24 | 6 | 6 | 0 | 2012-09-24 | 2012-12-12 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  | 2012-11-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Newton | 2252 | 2460 | 20 | PV | 282-H9 | 2012-09-17 | 2012-09-18 | 1 | 1 | 0 | 2012-09-18 | 2012-10-10 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-10-26 |  | 2012-10-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2012-12-05 |  | 2012-12-05 | Online | Private | Y
NSTAR | Lexington | 2253 | 2420 | 18 | PV | 391-H3 | 2012-09-17 | 2012-09-19 | 2 | 1 | 1 | 2012-10-04 | 2013-03-18 | 111 | 0 | 111 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-12-13 | 2013-12-13 | 2013-12-20 | Online | Private | Y
NSTAR | Plymouth | 2254 | 2360 | 361 | PV | 3-14-911 | 2012-09-17 | 2012-09-20 | 3 | 2 | 1 | 2012-09-20 | 2012-10-05 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-10 | 2013-09-19 | 90 | 0 | 90 | 2013-09-26 |  | -29658 | 0 | 0 | 2013-12-09 |  | 2013-01-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-12-19 | Online | Private | N
NSTAR | Acusnet | 2255 | 2745 | 750 | PV | 221 | 2012-09-18 | 2012-12-27 | 69 | 70 | -1 | 2013-11-13 |  | -29690 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-29 |  | -29781 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-17 |  | 2013-07-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Impact Study Stage | Gov't | Y
NSTAR | New Bedford | 2256 | 2745 | 5000 | PV | 2-102-604 | 2012-09-19 |  | -29403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Harwich | 2257 | 2645 | 4000 | PV | 4-89A-89A | 2012-09-21 | 2012-09-26 | 3 | 3 | 0 | 2012-09-26 | 2013-01-17 | 77 | 0 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | West Harwich | 2258 | 2671 | 11 | PV | 4-85-925 | 2012-09-21 | 2012-09-26 | 3 | 3 | 0 | 2012-09-26 | 2013-01-17 | 77 | 0 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | West Harwich | 2259 | 2671 | 11 | PV | 4-85-925 | 2012-09-26 | 2012-10-12 | 11 | 12 | -1 | 2012-10-16 | 2013-01-30 | 72 | 36 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-08-13 | 90 | 0 | 90 | 2013-09-26 |  | -29658 | 0 | 0 | 2013-11-27 |  | 2013-10-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-19 | Online | Gov't | Y
NSTAR | Mattapoisett | 2260 | 2739 | 750 | PV | 2-301-301 | 2012-09-26 | 2012-10-12 | 11 | 12 | -1 | 2012-10-16 | 2013-01-30 | 72 | 36 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-08-13 | 90 | 0 | 90 | 2013-09-26 |  | -29658 | 0 | 0 | 2013-11-27 |  | 2013-10-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Design Stage | Gov't | N
NSTAR | Mattapoisett | 2261 | 2739 | 750 | PV | 2-301-301 | 2012-09-26 | 2012-11-27 | 42 | 44 | -2 | 2012-11-27 | 2013-02-06 | 48 | 11 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 | 2013-05-14 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 2014-02-25 |  | 2013-10-15 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-09-18 | Online | Private | Y
NSTAR | Holliston | 2262 | 1746 | 3000 | PV | 3-88-2J2 | 2012-09-28 | 2012-09-28 | 0 | 0 | 0 | 2012-10-17 | 2012-12-05 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-10-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-11 | Online | Gov't | Y
NSTAR | Wayland | 2263 | 1778 | 13 | PV | 342-H1 | 2012-09-29 | 2012-10-17 | 12 | 12 | 0 | 2012-10-17 | 2012-12-05 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online | Private | Y
NSTAR | Sudbury | 2264 | 1776 | 12 | PV | 342-H8 | 2012-09-29 | 2012-11-07 | 27 | 27 | 0 | 2012-11-07 | 2012-12-26 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-11 |  | 2012-11-07 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-21 | Online | Private | Y
NSTAR | Sudbury | 2265 | 1776 | 12 | PV | 342-H2 | 2012-09-29 | 2012-10-17 | 12 | 12 | 0 | 2012-10-17 | 2012-12-05 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Wayland | 2266 | 1778 | 12 | PV | 342-H9 | 2012-10-01 | 2012-11-28 | 40 | 41 | -1 | 2012-11-28 | 2013-01-03 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-09 |  | 2012-10-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-16 | Online | Private | Y
NSTAR | Plymouth | 2267 | 2360 | 12 | PV | 3-11-11 | 2012-10-01 | 2012-11-28 | 40 | 41 | -1 | 2012-11-28 | 2013-01-15 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-28 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-28 | Online | Private | Y
NSTAR | Wayland | 2268 | 1778 | 10 | PV | 342-H1 | 2012-10-01 | 2012-10-24 | 16 | 16 | 0 | 2012-10-24 | 2013-01-15 | 56 | 26 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-03 |  | 2012-10-22 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-16 | Online | Private | Y
NSTAR | Brewster | 2269 | 2631 | 16 | PV | 4-89B-89B | 2012-10-02 | 2012-10-24 | 15 | 16 | -1 | 2012-10-24 | 2012-12-12 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-13 |  | 2012-10-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-05 | Online | Private | Y
NSTAR | Wayland | 2270 | 1778 | 17 | PV | 342-H1 | 2012-10-02 | 2012-11-07 | 25 | 26 | -1 | 2012-11-14 | 2012-12-20 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-31 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-14 | Online | Private | Y
NSTAR | Lincoln | 2271 | 1773 | 14 | PV | 282-H1 | 2012-10-02 | 2012-10-24 | 15 | 16 | -1 | 2012-10-24 | 2012-12-04 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-28 | Online | Private | Y
NSTAR | Lincoln | 2272 | 1773 | 12 | PV | 320-H6 | 2012-10-02 | 2012-11-13 | 29 | 30 | -1 | 2012-11-13 | 2012-12-26 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-14 |  | 2012-10-25 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-09 | Online | Private | Y
NSTAR | Wayland | 2273 | 1778 | 14 | PV | 278-H2 | 2012-10-02 | 2012-11-21 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Private | Y | 2013-03-19
NSTAR | Bellingham | 2274 | 2019 | 1000 | PV | 65-H4 | 2012-10-02 | 2012-11-06 | 24 | 23 | 1 | 2012-11-06 | 2013-01-17 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-31 |  | 2012-11-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-04-01 | 2013-04-01 |  |  | Private | Y
NSTAR | Brewster | 2275 | 2631 | 25 | PV | 4-89B-945 | 2012-10-02 |  | -29412 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Bellingham | 2276 | 2019 | 1000 | PV | 65-H4 | 2012-10-03 | 2012-10-12 | 6 | 6 | 0 | 2012-10-12 | 2012-12-04 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-10 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2013-01-31 |  |  |  | Private | Y
NSTAR | Waltham | 2277 | 2452 | 12 | PV | 33-H2 | 2012-10-03 | 2012-10-12 | 6 | 6 | 0 | 2012-10-12 | 2013-01-15 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-03-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-01 | Online | Private | Y
NSTAR | Harwich | 2278 | 2645 | 13 | PV | 4-95A-597 | 2012-10-04 | 2012-10-31 | 18 | 18 | 0 | 2012-10-31 | 2012-12-11 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-19 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online | Private | Y
NSTAR | Holliston | 2279 | 1746 | 15 | PV | 65-H5 | 2012-10-15 | 2012-11-08 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-12-23 | Online | Private | Y
NSTAR | Cambridge | 2280 | 2139 | 7500 | Natural Gas | 817-48 | 2012-10-17 | 2012-10-25 | 6 | 5 | 1 | 2012-10-26 | 2013-02-06 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  | 2012-11-05 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | Online | Private | Y
NSTAR | Sudbury | 2281 | 1776 | 12 | PV | 342-H8 | 2012-10-18 | 2012-11-29 | 29 | 30 | -1 | 2012-11-29 |  | -29452 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2012-11-07 | Withdrawn | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Wayland | 2282 | 1778 | 11 | PV | 342-H1 | 2012-10-22 | 2012-11-07 | 12 | 12 | 0 | 2012-11-07 | 2012-12-14 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-06 | 2013-06-26 | 96 | 0 | 96 |  |  | 0 | 0 | 0 | 2013-08-14 |  | 2012-12-15 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-07-22 | Online | Gov't | Y
NSTAR | Plymouth | 2283 | 2360 | 4260 | PV | 3-71-71 | 2012-10-23 | 2012-10-25 | 2 | 2 | 0 | 2012-10-26 | 2012-12-18 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-25 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-07-22 | Online | Gov't | Y
NSTAR | Plymouth | 2284 | 2360 | 75 | PV | 3-14-911 | 2012-10-19 |  | -29424 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2285 | 2360 | 75 | PV | 3-14-911 | 2012-10-25 | 2012-11-06 | 8 | 8 | 0 | 2012-11-06 | 2013-01-30 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  | 2012-11-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-03-29 | 2013-03-29 | 2013-03-29 | Online | Private | Y
NSTAR | Carlisle | 2286 | 1741 | 14 | PV | 512-1399H1 | 2012-10-25 | 2012-11-01 | 5 | 4 | 1 | 2012-11-01 | 2012-12-04 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-14 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-02-25 | Online | Private | Y
NSTAR | West Tisbury | 2287 | 2575 | 26 | PV | 4-97-220 | 2012-10-25 | 2012-10-31 | 4 | 3 | 1 | 2012-10-31 | 2013-02-10 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-14 |  | 2012-12-12 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-22 | Online | Private | Y
NSTAR | Framingham | 2288 | 1701 | 25 | PV | 433-H4 | 2012-10-25 | 2012-10-31 | 4 | 3 | 1 | 2012-10-31 | 2013-02-10 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2012-11-26 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-24 | Online | Private | Y
NSTAR | Framingham | 2289 | 1702 | 20 | PV | 278-H1 | 2012-10-26 | 2012-11-29 | 23 | 24 | -1 | 2012-11-29 | 2013-02-06 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-29 | Online | Private | Y
NSTAR | Cambridge | 2290 | 2139 | 14 | PV | 817-03 | 2012-10-26 | 2013-01-07 | 48 | 51 | -3 | 2013-01-11 | 2013-02-10 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2012-12-27 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Framingham | 2291 | 1702 | 20 | PV | 455-H5 | 2012-10-31 | 2012-11-27 | 18 | 19 | -1 | 2012-11-27 | 2012-12-20 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-13 | Online | Private | Y
NSTAR | Lincoln | 2292 | 1773 | 12 | PV | 320-H8 | 2012-10-31 | 2012-11-30 | 21 | 22 | -1 | 2012-11-30 | 2013-01-15 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Lincoln | 2293 | 1773 | 11 | PV | 320-H1 | 2012-10-31 | 2012-11-27 | 18 | 19 | -1 | 2012-11-27 | 2013-01-15 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-21 |  | 2012-11-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-17 | Online | Private | Y
NSTAR | Lincoln | 2294 | 1773 | 13 | PV | 320-H8 | 2012-10-31 | 2012-11-01 | 1 | 1 | 0 | 2013-04-22 | 2013-04-26 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-06 |  | 2012-11-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-05 | Online | Private | Y
NSTAR | Lincoln | 2295 | 1773 | 13 | PV | 320-H8 | 2012-10-31 | 2012-11-01 | 1 | 1 | 0 | 2012-11-01 | 2012-12-18 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-07 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-25 | Online | Private | Y
NSTAR | Wayland | 2296 | 1778 | 12 | PV | 342-H1 | 2012-10-31 | 2012-11-01 | 1 | 1 | 0 | 2012-11-01 | 2013-02-06 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-11-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-23 | Online | Private | Y
NSTAR | Wayland | 2297 | 1778 | 11 | PV | 342-H1 | 2012-11-02 | 2012-11-07 | 3 | 3 | 0 | 2012-11-27 | 2013-01-22 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2012-11-14 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2013-08-26 | Online | Private | Y
NSTAR | Acusnet | 2298 | 2745 | 425 | PV | 2-86-86 | 2012-11-06 | 2012-11-08 | 2 | 2 | 0 | 2012-11-08 | 2013-03-18 | 87 | 0 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-13 |  | 2012-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-26 | Online | Private | Y
NSTAR | Plymouth | 2299 | 2360 | 132 | PV | 3-89-925 | 2012-11-06 | 2012-11-27 | 14 | 15 | -1 | 2012-11-27 | 2013-03-18 | 75 | 0 | 75 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-30 |  | 2012-12-27 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-24 | Online | Private | Y
NSTAR | North Dartmouth | 2300 | 2747 | 20 | PV | 2-528-528 | 2012-10-31 | 2012-11-14 | 10 | 0 | 10 | 2012-11-14 | 2013-01-04 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-13 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-06 | Online | Gov't | Y
NSTAR | West Roxbury | 2301 | 2132 | 60 | PV | 468-01 | 2012-11-09 | 2012-11-16 | 5 | 2 | 3 | 2012-11-16 | 2013-03-18 | 81 | 0 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-01-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Framingham | 2302 | 1702 | 4400 | PV | 274-H4 | 2012-11-13 | 2012-11-19 | 4 | 3 | 1 | 2012-11-19 | 2013-02-06 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-11-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-13 | Withdrawn | Private | Y
NSTAR | Lexington | 2303 | 2421 | 11 | PV | 3409 | 2012-11-04 | 2012-11-20 | 12 | 4 | 8 | 2012-11-20 | 2012-12-20 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-01-28 |  | 2012-04-01 | TBD | EXP |  |  |  | 0 | 0 | 0 | 2013-03-27 | 2013-03-27 | 2013-03-27 | Online | Gov't | Y
NSTAR | Somerville | 2304 | 2145 | 42 | PV | 250-1N90H2 | 2012-11-19 | 2012-11-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Lexington | 2305 | 2421 | 10 | PV | 320-H5XY | 2012-11-21 | 2012-11-28 | 4 | 5 | -1 | 2012-11-28 | 2012-12-20 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-12-27 |  |  | No | EXP |  |  |  | 0 | 0 | 0 | 2013-03-29 | 2013-03-29 | 2013-03-29 | Online | Private | Y
NSTAR | Dover | 2306 | 2030 | 12 | PV | 456-H5 | 2012-11-26 | 2012-12-05 | 7 | 3 | 4 | 2012-12-05 | 2013-02-06 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2013-01-07 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-23 | Online | Private | Y
NSTAR | Lincoln | 2307 | 1773 | 12 | PV | 320-H8 | 2012-11-27 | 2012-12-04 | 5 | 5 | 0 | 2012-12-04 | 2013-02-12 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-02-26 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-02 | Online | Private | Y
NSTAR | West Barnstable | 2308 | 2668 | 40 | PV | 4-87B-473 | 2012-11-28 | 2012-12-11 | 9 | 9 | 0 | 2012-12-11 | 2013-01-30 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-07 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-23 | Online | Private | Y
NSTAR | Woburn | 2309 | 1801 | 60 | PV | 375-H6 | 2012-11-28 | 2012-12-27 | 20 | 19 | 1 | 2012-12-27 | 2013-02-25 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-06 |  | 2013-01-02 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-30 | Online | Private | Y
NSTAR | North Dartmouth | 2310 | 2747 | 13 | PV | 2-524-524 | 2012-12-03 | 2012-12-27 | 17 | 16 | 1 | 2012-12-27 | 2013-02-12 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-07 |  | 2013-02-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-20 | Online | Private | Y
NSTAR | Lincoln | 2311 | 1773 | 10 | PV | 320-H6 | 2012-12-03 | 2012-12-13 | 8 | 6 | 2 | 2012-12-27 | 2013-02-12 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-02-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-13 | Online | Private | Y
NSTAR | Wayland | 2312 | 1778 | 18 | PV | 342-H3 | 2012-12-04 | 2012-12-11 | 5 | 1 | 4 | 2012-12-11 | 2013-02-12 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-24 | Online | Gov't | Y
NSTAR | Plymouth | 2313 | 2360 | 333 | PV | 3-13-943 | 2012-12-05 | 2012-12-13 | 6 | 1 | 5 | 2012-12-13 | 2013-02-12 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-26 |  | 2013-04-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-10-14 | Online | Gov't | Y
NSTAR | Sandwich | 2314 | 2537 | 28 | PV | 4-87B-473 | 2012-12-12 | 2012-12-17 | 3 | 2 | 1 | 2012-12-17 | 2013-02-06 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-11 |  | 2013-01-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-04-22 | Online | Private | Y
NSTAR | Plympton | 2315 | 2367 | 12 | PV | 3-51-901 | 2012-12-12 | 2012-12-20 | 6 | 4 | 2 | 2012-12-20 | 2013-02-12 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  | 2013-03-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-01 | Online | Private | Y
NSTAR | New Bedford | 2316 | 2745 | 100 | PV | 2-103-103 | 2012-12-13 | 2012-12-21 | 6 | 5 | 1 | 2012-12-21 | 2013-02-06 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-19 |  | 2012-12-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-03-28 | Online | Private | Y
NSTAR | Needham | 2317 | 2492 | 12 | PV | 148-03 | 2012-12-14 |  | -29463 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Plymouth | 2318 | 2360 | 333 | PV | 3-13-943 | 2012-12-14 | 2012-12-27 | 8 | 9 | -1 | 2012-12-27 | 2013-01-29 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-04 |  | 2013-01-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Wayland | 2319 | 1778 | 11 | PV | 342-H1 | 2012-12-14 |  | -29463 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | New Bedford | 2320 | 2745 | 100 | PV | 2-103-103 | 2012-12-17 | 2013-01-24 | 25 | 26 | -1 | 2013-01-24 | 2013-03-18 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-22 |  | 2012-12-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Private | Y | 2013-03-25
NSTAR | Bedford | 2321 | 1730 | 24 | PV | 533-H8 | 2012-12-18 | 2012-12-20 | 2 | 1 | 1 | 2013-03-26 | 2013-04-16 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-24 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-06 | Online | Private | Y
NSTAR | Hopkinton | 2322 | 1748 | 190 | PV | 126-H1 | 2012-12-19 | 2012-12-21 | 2 | 1 | 1 | 2013-04-08 | 2013-04-24 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-19 |  | 2012-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-24 | Online | Private | Y
NSTAR | Brewster | 2323 | 2631 | 16 | PV | 4-89B-946 | 2012-12-26 | 2012-12-27 | 1 | 1 | 0 | 2012-12-27 | 2013-02-10 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-21 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Private | Y | 2013-02-21
NSTAR | Newton | 2324 | 2458 | 13 | PV | 277-05 | 2012-12-28 | 2013-01-24 | 17 | 19 | -2 | 2013-01-24 | 2013-04-17 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-26 |  | 2012-12-20 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-05-02 | 2013-05-02 | 2013-05-02 | Online | Private | Y
NSTAR | Mashpee | 2325 | 2649 | 18 | PV | 4-71-455 | 2013-01-02 | 2013-01-09 | 5 | 3 | 2 | 2013-01-10 | 2013-04-29 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-02 |  | 2013-05-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-16 | Online | Private | Y
NSTAR | North Dartmouth | 2326 | 2747 | 134 | PV | 2-533-503 | 2013-01-04 | 2013-01-04 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Stability Study Stage | Gov't | Y
NSTAR | Carver | 2327 | 2330 | 2000 | PV | 433-H8 | 2013-01-08 | 2013-01-11 | 3 | 3 | 0 | 2013-01-16 | 2013-02-12 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-02-20 |  | 2013-01-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-06-13 | 2013-06-13 | 2016-10-04 | Online | Private | Y
NSTAR | New Bedford | 2328 | 2745 | 345 | PV | 240-H3 | 2013-01-15 | 2013-01-22 | 4 | 1 | 3 | 2013-01-28 | 2013-03-08 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-03-14 |  | 2013-03-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-13 | Online | Private | Y
NSTAR | Lincoln | 2329 | 1773 | 11 | PV | 320-H6 | 2013-01-21 | 2013-01-28 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Gov't | Y | 2013-05-07
NSTAR | West Yarmouth | 2330 | 2673 | 1000 | PV | 2-92A-92A | 2013-01-21 |  | -29486 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | West Yarmouth | 2331 | 2673 | 1000 | PV | 2-92A-92A | 2013-01-23 | 2013-01-28 | 3 | 0 | 3 | 2013-04-22 | 2013-05-28 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | South Sandwich | 2332 | 2653 | 2250 | PV | 2-87A-475 | 2013-01-21 | 2013-01-30 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Waiting for the Study of a Nearby System | Gov't | Y | 2013-05-09
NSTAR | West Yarmouth | 2333 | 2673 | 500 | PV | 2-92A-92A | 2013-01-21 | 2013-02-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Impact Study Fee & Agreement | Gov't | Y | 2013-06-03
NSTAR | Tisbury | 2334 | 2568 | 500 | PV | 4-91-91 | 2013-01-24 |  | -29489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | East Falmouth | 2335 | 2536 | 54 | PV | 4-98A-98A | 2013-01-25 | 2013-02-01 | 5 | 4 | 1 | 2013-02-27 | 2013-08-26 | 124 | 0 | 124 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-07 |  | -29560 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-04 |  | 2013-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online | Gov't | Y
NSTAR | Bourne | 2336 | 2532 | 1680 | Wind | 4-81A-81A | 2013-01-25 | 2013-02-06 | 8 | 7 | 1 | 2013-03-01 | 2013-08-26 | 122 | 0 | 122 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online | Gov't | N
NSTAR | Framingham | 2337 | 1702 | 150 | PV | 433-H8 | 2013-01-25 | 2013-02-06 | 8 | 7 | 1 | 2013-02-27 | 2013-04-08 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-05 | Online | Private | Y
NSTAR | Framingham | 2338 | 1702 | 190 | PV | 240-H3 | 2013-01-28 | 2013-01-29 | 1 | 0 | 1 | 2013-01-29 | 2013-02-11 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-11 |  | 2013-02-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-05-21 | Online | Private | Y
NSTAR | Lincoln | 2339 | 1773 | 9 | PV | 320-H8 | 2013-01-28 | 2013-03-12 | 30 | 30 | 0 | 2013-03-13 | 2013-04-29 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-17 |  | 2013-02-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-08-12 | 2013-08-12 | 2013-08-16 | Online | Private | N
NSTAR | Woburn | 2340 | 1801 | 336 | Natural Gas | 301-1386H | 2013-01-29 | 2013-02-06 | 6 | 4 | 2 | 2013-02-13 | 2013-04-24 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-29 |  | 2013-02-14 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-12 | Online | Private | Y
NSTAR | Sudbury | 2341 | 1776 | 12 | PV | 342-H8 | 2013-01-31 | 2013-02-06 | 4 | 3 | 1 | 2013-02-27 | 2013-04-09 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-12-15 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plympton | 2342 | 2367 | 1000 | PV | 3-10-930 | 2013-01-31 |  | -29494 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Chilmark | 2343 | 2535 | 12 | PV | 4-97-226 | 2013-02-01 | 2013-02-07 | 4 | 1 | 3 | 2013-03-06 | 2013-04-09 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-22 |  | -29736 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Millis | 2344 | 2052 | 1000 | PV | 65-H1 | 2013-02-05 | 2013-03-06 | 20 | 19 | 1 | 2013-03-21 | 2013-04-24 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-06 |  | 2013-05-21 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Boston | 2345 | 2118 | 60 | PV | 323-02 | 2013-02-04 | 2013-04-01 | 39 | 36 | 3 | 2013-04-02 | 2013-05-13 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-27 |  | 2013-03-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-08-07 | Online | Private | Y
NSTAR | Sudbury | 2346 | 1776 | 41 | PV | 342-H7 | 2013-03-26 | 2013-04-01 | 4 | 0 | 4 | 2013-04-01 | 2013-05-06 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-23 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online | Private | Y
NSTAR | Burlington | 2347 | 1803 | 351 | PV | 391-H12 | 2013-02-08 | 2013-05-14 | 65 | 50 | 15 | 2013-06-24 | 2013-07-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-11 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online | Private | Y
NSTAR | Kingston | 2348 | 2364 | 33 | PV | 3-26-902 | 2013-02-08 | 2013-03-06 | 17 | 18 | -1 | 2013-03-11 | 2013-05-10 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-15 |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  | 2013-11-08 | Online | Private | Y
NSTAR | Waltham | 2349 | 2451 | 120 | PV | 282-H5 | 2013-02-11 | 2013-02-14 | 3 | 0 | 3 | 2013-02-27 | 2013-04-09 | 29 | 2 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-10 |  | 2013-08-29 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  | 2014-05-16 | Online | Private | Y
NSTAR | Wareham | 2350 | 2571 | 1000 | PV | 3-83-83 | 2013-02-22 | 2013-02-27 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Waiting for Customer's Response / Revised Docs | Private | Y | 2013-06-17
NSTAR | Boston | 2351 | 2115 | 5750 | Natural Gas | 335-1141 | 2013-02-21 | 2013-02-27 | 4 | 3 | 1 | 2013-02-28 | 2013-04-24 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Norfolk | 2352 | 2056 | 82 | PV | 65-H1 | 2013-02-22 | 2013-03-06 | 8 | 5 | 3 | 2013-03-07 | 2013-04-09 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-13 |  | 2013-05-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-08 | Online | Private | Y
NSTAR | Assonett | 2353 | 2702 | 142 | PV | 2-605-605 | 2013-02-26 | 2013-03-28 | 22 | 20 | 2 | 2013-04-01 | 2013-04-24 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-31 |  | 2013-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-19 | Online | Private | Y
NSTAR | Plymouth | 2354 | 2360 | 85 | PV | 3-73-927 | 2013-03-04 | 2013-05-30 | 61 | 62 | -1 | 2013-05-30 | 2013-07-02 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-26 |  | 2013-06-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-08-11 | Online | Gov't | Y
NSTAR | Carver | 2355 | 2330 | 250 | PV | 3-51-901 | 2013-03-06 | 2013-03-06 | 0 | 0 | 0 | 2013-03-08 |  | -29519 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-05-15 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Wayland | 2356 | 1778 | 10 | PV | 278-H2 | 2013-03-06 | 2013-03-13 | 5 | 2 | 3 | 2013-03-15 | 2013-04-24 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-27 |  | 2013-05-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-07-18 | Online | Private | Y
NSTAR | New Bedford | 2357 | 2746 | 50 | PV | 2-82-82 | 2013-03-07 |  | -29518 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Winchester | 2358 | 1890 | 11 | PV | 211-H7XY | 2013-03-15 | 2013-10-09 | 143 | 146 | -3 | 2013-10-10 |  | -29668 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-04 |  | 2013-04-11 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | Private | Y
NSTAR | Oak Bluffs | 2359 | 2557 | 260 | PV | 4-75-75 | 2013-03-18 | 2013-03-25 | 5 | 0 | 5 | 2013-03-25 | 2013-04-24 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-27 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | Private | Y
NSTAR | South Boston | 2360 | 2127 | 142 | PV | 106-H1 | 2013-03-21 | 2013-04-12 | 16 | 14 | 2 | 2013-04-17 | 2013-05-28 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-11-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | New Bedford | 2361 | 2745 | 2000 | PV | 4-??-103 | 2013-01-29 | 2013-03-25 | 38 | 0 | 38 | 2013-03-25 | 2013-04-24 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-05 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Westwood | 2362 | 2090 | 17 | PV | 148-H3 | 2013-03-25 | 2013-03-29 | 4 | 2 | 2 | 2013-04-02 | 2013-04-24 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-04-30 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-06-26 | Online | Private | Y
NSTAR | Weston | 2363 | 2493 | 20 | PV | 342-H1 | 2013-02-04 |  | -29496 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | Private | Y | 2013-03-27
NSTAR | Dartmouth | 2364 | 2747 | 17 | PV | 2-543-543 | 2013-03-27 | 2013-04-01 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Detailed Study Stage | Private | Y | 2013-08-16
NSTAR | Edgartown | 2365 | 2539 | 266 | PV | 4-97-97 | 2013-03-26 | 2013-10-03 | 132 | 133 | -1 | 2013-10-04 |  | -29664 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-04-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-12 | Online | Private | Y
NSTAR | Edgartown | 2366 | 2539 | 18 | PV | 4-75-123 | 2013-03-28 | 2013-04-09 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private | Y | 2013-07-22
NSTAR | Millis | 2367 | 2054 | 500 | PV | 146-H10 | 2013-03-21 | 2013-04-10 | 14 | 5 | 9 | 2013-04-10 | 2013-04-24 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-18 |  | 2013-06-30 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 |  | Withdrawn | Private | Y
NSTAR | North Dartmouth | 2368 | 2747 | 225 | PV | 2-543-543 | 2013-04-03 | 2013-04-26 | 16 | 14 | 2 | 2013-05-01 | 2013-06-18 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-01 | No | EXP |  |  |  | 0 | 0 | 0 | 2013-12-18 | 2013-12-18 | 2013-12-18 | Online | Private | Y
NSTAR | New Bedford | 2369 | 2740 | 500 | PV | 2-59-59 | 2013-03-26 | 2013-04-08 | 9 | 0 | 9 | 2013-04-12 | 2013-04-24 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-10-02 | Online | Private | Y
NSTAR | Westport | 2370 | 2767 | 82 | PV | 2-522-522 | 2013-04-12 | 2013-04-17 | 2 | 1 | 1 | 2013-04-25 | 2013-06-18 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-24 |  | 2013-06-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-13 | Online | Private | Y
NSTAR | Dartmouth | 2371 | 2747 | 19 | PV | 2-533-533 | 2013-04-10 | 2013-04-30 | 13 | 10 | 3 | 2013-04-30 |  | -29555 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-07-01 | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Freetown | 2372 | 2702 | 4999 | PV | 2-102-102 | 2013-04-12 | 2013-06-14 | 43 | 43 | 0 | 2013-06-17 | 2013-07-26 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-11 | 2013-11-27 | 53 | 11 | 42 |  |  | 0 | 0 | 0 | 2014-03-13 |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Dedham | 2373 | 2136 | 2000 | PV | 344-1413H1 | 2013-04-19 | 2013-04-29 | 6 | 3 | 3 | 2013-04-30 | 2013-06-18 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-11 | Online | Private | Y
NSTAR | West Tisbury | 2374 | 2575 | 15 | PV | 4-97-97 | 2013-04-24 | 2013-05-01 | 5 | 3 | 2 | 2013-05-01 | 2013-06-27 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Hopkinton | 2375 | 1748 | 4000 | PV | 126-H1 | 2013-04-30 | 2013-04-30 | 0 | 0 | 0 | 2013-04-30 | 2013-06-18 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Cambridge | 2376 | 2140 | 28 | PV | 825-26 | 2013-04-30 | 2013-06-19 | 34 | 36 | -2 | 2013-06-20 | 2013-07-10 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  | 2013-07-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-10-08 | Online | Private | Y
NSTAR | Arlington | 2377 | 2476 | 34 | PV | 5905 | 2013-04-30 | 2013-04-30 | 0 | 0 | 0 | 2013-04-30 | 2013-06-18 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-09-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-23 | Online | Private | Y
NSTAR | Cambridge | 2378 | 2140 | 35 | PV | 825-26 | 2013-04-30 | 2013-05-06 | 4 | 4 | 0 | 2013-05-20 | 2013-06-26 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-09-16 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-24 | Online | Private | Y
NSTAR | Jamaica Plain | 2379 | 2130 | 60 | PV | 396 | 2013-05-01 | 2013-05-14 | 9 | 9 | 0 | 2013-05-16 | 2013-06-27 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-05 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-11 | Online | Gov't | N
NSTAR | Boston | 2380 | 2129 | 75 | Natural Gas | 530-178 | 2013-05-01 | 2013-05-06 | 3 | 3 | 0 | 2013-05-06 | 2013-06-18 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-24 |  | 2013-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-11-27 | Online | Private | Y
NSTAR | Chilmark | 2381 | 2535 | 27 | PV | 4-97-126 | 2013-04-17 | 2013-05-08 | 15 | 5 | 10 | 2013-05-17 | 2013-06-26 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-06-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Mashpee | 2382 | 2649 | 5000 | PV | 4-88-453 | 2013-05-02 | 2013-05-31 | 20 | 19 | 1 | 2013-06-01 | 2013-07-10 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-06-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | North Dartmouth | 2383 | 2747 | 75 | PV | 2-532-532 | 2013-05-07 | 2013-05-16 | 7 | 6 | 1 | 2013-05-17 | 2013-06-26 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-07-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-25 | Online | Private | Y
NSTAR | Chelsea | 2384 | 2150 | 50 | PV | 488-H7 | 2013-05-08 | 2013-05-16 | 6 | 5 | 1 | 2013-05-21 | 2013-09-05 | 73 | 0 | 73 | 2013-09-13 | 2013-09-16 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-17 |  | 2013-08-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Boston | 2385 | 2109 | 35 | PV | 3009 | 2013-05-10 | 2013-05-21 | 7 | 3 | 4 | 2013-05-23 | 2013-06-26 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | Private | N
NSTAR | Boston | 2386 | 2210 | 75 | Natural Gas | 385-H4 | 2013-05-17 | 2013-06-10 | 15 | 15 | 0 | 2013-06-10 | 2013-07-16 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-21 |  | 2013-07-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-30 | Online | Private | Y
NSTAR | Roxbury | 2387 | 2492 | 32 | PV | 483-H6 | 2013-05-20 | 2013-05-31 | 8 | 9 | -1 | 2013-05-31 | 2013-06-26 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  | 2013-08-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | West Tisbury | 2388 | 2575 | 15 | PV | 4-97-97 | 2013-05-17 | 2013-05-24 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-07-09 | Online | Private | Y
NSTAR | Holliston | 2389 | 1746 | 1000 | PV | 65-1325H | 2013-05-20 | 2013-07-02 | 29 | 30 | -1 | 2013-07-02 | 2013-07-10 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  | 2013-06-07 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-07-09 | Online | Private | Y
NSTAR | Edgartown | 2390 | 2539 | 26 | PV | 4-75-75 | 2013-05-21 | 2013-05-28 | 4 | 5 | -1 | 2013-05-28 | 2013-07-01 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-08 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-09-27 | Online | Private | Y
NSTAR | Falmouth | 2391 | 2540 | 60 | PV | 4-76-437 | 2013-04-16 | 2013-05-22 | 26 | 23 | 3 | 2013-05-22 | 2013-06-26 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-06-28 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-08-13 | Online | Private | Y
NSTAR | Chilmark | 2392 | 2535 | 23 | PV | 4-97-226 | 2013-05-24 |  | -29573 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | New Bedford | 2393 | 2746 | 1000 | PV | 2-7-34 | 2013-05-28 | 2013-06-18 | 14 | 13 | 1 | 2013-06-19 | 2013-10-29 | 91 | 1 | 90 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-30 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Falmouth | 2394 | 2540 | 25 | PV | 4-107-830 | 2013-05-31 | 2013-06-26 | 17 | 18 | -1 | 2013-07-01 | 2013-08-26 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-26 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-10 | Online | Private | Y
NSTAR | Bedford | 2395 | 1730 | 500 | PV | 391-H10 | 2013-06-04 |  | -29579 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Norfolk | 2396 | 2056 | 1000 | PV | 146-H3 | 2013-06-05 | 2013-06-10 | 3 | 3 | 0 | 2013-10-01 | 2013-10-23 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-29 |  | 2013-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Medway | 2397 | 2053 | 103 | PV | 65-H3 | 2013-06-05 | 2013-06-07 | 2 | 2 | 0 | 2013-10-10 | 2013-10-23 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-29 |  | 2013-09-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-06 | Online | Private | Y
NSTAR | Medway | 2398 | 2053 | 50 | PV | 65-H2 | 2013-06-10 |  | -29583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | Private | Y | 2013-06-10
NSTAR | Acusnet | 2399 | 2743 | 750 | PV | 2-231-231 | 2013-06-10 | 2013-06-20 | 7 | 7 | 0 | 2013-06-26 | 2013-07-23 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-25 |  | 2013-07-20 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Walpole | 2400 | 2081 | 49 | PV | 146-H3 | 2013-06-12 | 2013-07-30 | 32 | 33 | -1 | 2013-07-30 |  | -29617 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-05-01 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plympton | 2401 | 2364 | 4000 | PV | 3-15-901 | 2013-06-12 | 2013-08-20 | 47 | 48 | -1 | 2013-08-21 |  | -29633 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-11 | 2013-11-23 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 2014-05-09 |  | 2013-12-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Norfolk | 2402 | 2056 | 1000 | PV | 146-H3 | 2013-06-07 | 2013-07-10 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Response and/or Cost Estimates from Eng | Gov't | Y | 2013-08-26
NSTAR | Acusnet | 2403 | 2743 | 500 | PV | 2-240-240 | 2013-06-17 | 2013-06-20 | 3 | 2 | 1 | 2013-06-24 | 2013-07-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-19 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2017-01-06 | Online | Private | Y
NSTAR | Framingham | 2404 | 1702 | 18 | PV | 433-H12 | 2013-06-17 | 2013-06-19 | 2 | 1 | 1 | 2013-06-19 | 2013-08-13 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-15 |  | 2013-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-17 | Online | Private | Y
NSTAR | New Bedford | 2405 | 2740 | 100 | PV | 2-38-38 | 2013-06-18 | 2013-06-24 | 4 | 3 | 1 | 2013-06-26 | 2013-07-10 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-07-15 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-11-04 | Online | Private | Y
NSTAR | Cambridge | 2406 | 2140 | 40 | PV | 824-25 | 2013-06-18 | 2013-06-24 | 4 | 2 | 2 | 2013-06-24 | 2013-08-26 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-01 |  | -29661 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-09 |  | 2013-12-15 | No | STD |  |  |  | 0 | 0 | 0 |  |  |  | Impact Study Stage C&P | Gov't | Y
NSTAR | Mattapoisett | 2407 | 2739 | 4500 | PV | 2-302-302 | 2013-06-19 | 2013-07-01 | 8 | 7 | 1 | 2013-07-03 | 2013-08-07 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-24 |  | 2013-08-15 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  |  | Private | Y
NSTAR | Framingham | 2408 | 1701 | 46 | PV | 455-H5 | 2013-06-20 | 2013-08-20 | 42 | 41 | 1 | 2013-08-20 |  | -29632 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-03 |  | 2013-09-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-30 | Online | Private | Y
NSTAR | Boston | 2409 | 2121 | 60 | PV | 323-02 | 2013-06-25 | 2013-06-27 | 2 | 2 | 0 | 2013-06-27 | 2013-08-26 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-05 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-08-08 | Online | Private | Y
NSTAR | Waltham | 2410 | 2451 | 750 | PV | 320-H3 | 2013-06-24 | 2013-07-01 | 5 | 2 | 3 | 2013-07-01 | 2013-08-26 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-08-07 | Online | Private | Y
NSTAR | Dorchester | 2411 | 2122 | 85 | PV | 511-1498H1 | 2013-06-26 | 2013-06-28 | 2 | 1 | 1 | 2013-07-02 | 2013-08-26 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2013-08-29 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Holliston | 2412 | 1746 | 2000 | PV | 130-H1 | 2013-01-25 | 2013-02-01 | 5 | 4 | 1 | 2013-02-27 | 2013-08-26 | 124 | 0 | 124 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-05-07 |  | -29560 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-04 |  | 2013-09-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Bourne | 2413 | 2532 | 1680 | Wind | 4-81A-81A | 2013-07-08 | 2013-10-29 | 79 |  | 79 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Private | Y | 2013-11-18
NSTAR | Newton | 2414 | 2458 | 57 | PV | 467-H5 | 2013-07-08 | 2013-10-29 | 79 | 80 | -1 | 2013-11-05 |  | -29685 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | TBD | TBD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Newton | 2415 | 2458 | 62 | PV | 467-H3 | 2013-07-08 | 2013-07-22 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Stage: Awaiting Customer's Response/Docs | Private | Y | 2013-09-16
NSTAR | Framingham | 2416 | 1702 | 1000 | PV | 455-H6 | 2013-07-09 | 2013-07-22 | 9 | 7 | 2 | 2013-07-25 |  | -29614 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-25 |  | -29657 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-21 |  | 2013-11-30 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Sudbury | 2417 | 1776 | 980 | PV | 416-H4 | 2013-07-03 | 2013-08-20 | 33 | 28 | 5 | 2013-08-20 |  | -29632 | 0 | 0 | 2013-09-16 |  | -29650 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-16 |  | 2013-09-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-05-19 | Online | Private | Y
NSTAR | Boston | 2418 | 2119 | 36 | PV | 385-H1 | 2013-07-03 | 2013-08-20 | 33 | 28 | 5 | 2013-08-20 |  | -29632 | 0 | 0 | 2013-09-16 |  | -29650 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-16 |  | 2013-09-09 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-24 | Online | Private | Y
NSTAR | Boston | 2419 | 2119 | 50 | PV | 385-H19 | 2013-07-09 | 2013-07-12 | 3 | 1 | 2 | 2013-07-12 | 2013-08-26 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-15 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-09 | Online | Private | Y
NSTAR | Falmouth | 2420 | 2540 | 40 | PV | 4-76-76 | 2013-07-09 | 2013-10-02 | 60 | 58 | 2 | 2013-10-08 | 2013-12-11 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-10 |  | 2013-10-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-03 | Online | Private | Y
NSTAR | New Bedford | 2421 | 2740 | 75 | Natural Gas | 2-67-14 | 2013-07-11 | 2013-07-23 | 8 | 6 | 2 | 2013-07-24 | 2013-08-26 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-08-29 |  | 2013-09-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-11-18 | Online | Private | Y
NSTAR | Chilmark | 2422 | 2535 | 17 | PV | 4-97-126 | 2013-07-15 | 2013-08-12 | 20 | 18 | 2 | 2013-08-12 | 2013-09-11 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-25 |  | -29657 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-30 |  | 2013-12-31 | TBD | STD |  |  |  | 0 | 0 | 0 |  |  | 2015-04-21 | Online | Gov't | Y
NSTAR | Hyannis | 2423 | 2601 | 750 | PV | 4-84B-510 | 2013-07-22 | 2013-07-25 | 3 | 2 | 1 | 2013-07-26 |  | -29615 | 0 | 0 | 2013-09-11 | 2013-10-08 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-10 |  | 2013-10-01 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-21 | Online | Gov't | Y
NSTAR | Needham | 2424 | 2494 | 30 | PV | 148-H7 | 2013-07-25 |  | -29614 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Norfolk | 2425 | 2056 | 266 | PV | 146-H3 | 2013-07-29 | 2013-08-02 | 4 | 3 | 1 | 2013-08-05 |  | -29621 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-13 |  | 2013-08-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Chilmark | 2426 | 2535 | 17 | PV | 4-97-226 | 2013-08-06 |  | -29622 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Stability Study Stage | Gov't | Y
NSTAR | Carver | 2427 | 2330 | 5000 | PV | 3-10-930 | 2013-08-13 | 2013-08-22 | 7 | 6 | 1 | 2013-08-22 |  | -29634 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-03 |  | 2013-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Private | Y | 2013-09-03
NSTAR | Somerville | 2428 | 2143 | 85 | PV | 250-1N35H2 | 2013-08-13 | 2013-08-26 | 9 | 7 | 2 | 2013-08-26 |  | -29636 | 0 | 0 | 2013-09-24 |  | -29656 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Wayland | 2429 | 1778 | 325 | PV | 433-H6 | 2013-08-13 | 2013-08-26 | 9 | 7 | 2 | 2013-08-26 |  | -29636 | 0 | 0 | 2013-09-24 | 2013-10-28 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Gov't | Y | 2013-12-02
NSTAR | Natick | 2430 | 1778 | 225 | PV | 433-H6 | 2013-08-13 | 2013-08-26 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Construction Stage | Gov't | Y
NSTAR | Framingham | 2431 | 1701 | 250 | PV | 433-H4 | 2013-08-13 | 2013-08-30 | 13 | 11 | 2 | 2013-08-30 |  | -29640 | 0 | 0 | 2013-11-07 | 2013-11-25 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Gov't | Y
NSTAR | Framingham | 2432 | 1702 | 1364 | PV | 278-H2 | 2013-08-21 | 2013-08-30 | 7 | 6 | 1 | 2013-08-30 |  | -29640 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-15 |  | 2013-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Plymouth | 2433 | 2360 | 75 | PV | 3-13-943 | 2013-08-22 | 2013-08-27 | 3 | 0 | 3 | 2013-08-27 |  | -29637 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-23 |  | 2013-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-23 | Online | Private | Y
NSTAR | Walpole | 2434 | 2081 | 24 | PV | 456-H1 | 2013-09-03 | 2013-09-11 | 6 | 5 | 1 | 2013-09-11 |  | -29647 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-09-28 |  | 2014-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-23 | Online | Private | Y
NSTAR | Burlington | 2435 | 1803 | 232 | PV | 391-H5 | 2013-09-03 | 2013-11-22 | 56 | 57 | -1 | 2013-11-22 |  | -29697 | 60 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-12 | 2014-12-04 | 2014-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-04 | Online | Private | Y
NSTAR | Natick | 2436 | 1760 | 550 | PV | 433-H10 | 2013-09-10 | 2013-09-13 | 3 | 3 | 0 | 2013-09-13 |  | -29649 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  | 2013-10-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-06 | Online | Private | Y
NSTAR | Lexington | 2437 | 2420 | 32 | PV | 391-H11 | 2013-09-10 | 2013-09-11 | 1 | 0 | 1 | 2013-09-11 |  | -29647 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-16 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-07-18 | Online | Private | Y
NSTAR | Sharon | 2438 | 2067 | 185 | PV | 146-H1 | 2013-09-12 | 2013-10-30 | 33 | 33 | 0 | 2013-10-30 |  | -29681 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-02 |  | 2013-11-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-19 | Online | Private | Y
NSTAR | Framingham | 2439 | 1702 | 40 | PV | 433-H8 | 2013-09-16 | 2013-10-02 | 12 | 12 | 0 | 2013-10-02 |  | -29662 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-10-21 | Awaiting Completion Docs | Private | Y | 2013-12-09
NSTAR | Cotuit | 2440 | 2635 | 30 | PV | 4-71-455 | 2013-09-18 | 2013-09-20 | 2 | 2 | 0 | 2013-09-20 |  | -29654 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-28 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-13 | Online | Private | Y
NSTAR | Waltham | 2441 | 2451 | 60 | PV | 282-H1 | 2013-09-16 | 2013-09-20 | 4 | 1 | 3 | 2013-09-20 |  | -29654 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-18 |  | 2013-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-17 | Online | Private | Y
NSTAR | Lexington | 2442 | 2421 | 46 | PV | 3402 | 2013-09-19 | 2013-10-24 | 24 | 24 | 0 | 2013-10-24 |  | -29677 | 31 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-07 |  | 2013-12-15 | No | EXP |  |  |  | 0 | 0 | 0 | 2014-04-08 | 2014-04-08 | 2014-04-08 | Online | Private | Y
NSTAR | Framingham | 2443 | 1701 | 75 | Natural Gas | 342-H4 | 2013-09-20 | 2013-09-30 | 6 | 4 | 2 | 2013-10-01 |  | -29661 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-29 | Online | Private | Y
NSTAR | Brookline | 2444 | 2446 | 46 | PV | 329-H7 | 2013-09-23 | 2013-10-01 | 6 | 5 | 1 | 2013-10-04 |  | -29664 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-10 | Online | Private | Y
NSTAR | Sherborn | 2445 | 1770 | 19 | PV | 130-H2 | 2013-09-23 | 2013-09-30 | 5 | 2 | 3 | 2013-10-04 |  | -29664 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2014-06-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-07 | Online | Private | Y
NSTAR | North Dartmouth | 2446 | 2747 | 383 | PV | 2-531-530 | 2013-09-23 | 2013-09-27 | 4 | 1 | 3 | 2013-10-01 |  | -29661 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-04 |  | 2013-10-10 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2015-04-07 | Online | Private | Y
NSTAR | Assonett | 2447 | 2702 | 10 | PV | 2-605-605 | 2013-10-02 | 2013-10-07 | 3 | 0 | 3 | 2013-10-10 |  | -29668 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-06 |  | 2013-10-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-19 | Online | Private | Y
NSTAR | Plympton | 2448 | 2367 | 24 | PV | 3-51-901 | 2013-10-04 | 2013-10-10 | 4 | 2 | 2 | 2013-10-11 |  | -29669 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-01 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Westwood | 2449 | 2090 | 20 | PV | 456-H1 | 2013-10-09 | 2013-10-15 | 3 | 2 | 1 | 2013-10-17 |  | -29672 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-06 |  | 2013-11-22 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-12 | Online | Private | Y
NSTAR | Woburn | 2450 | 1801 | 50 | PV | 211-H2 | 2013-10-09 | 2013-10-16 | 4 | 3 | 1 | 2013-10-18 |  | -29673 | 0 | 0 | 2013-12-02 |  | -29702 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-13 |  | 2013-11-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-04-04 | Online | Private | Y
NSTAR | Cambridge | 2451 | 2138 | 70 | PV | 827-31 | 2013-10-15 | 2013-10-23 | 6 | 5 | 1 | 2013-10-23 |  | -29676 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  | 2013-11-29 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-11 | Online | Private | Y
NSTAR | Dover | 2452 | 2030 | 20 | PV | 456-H3 | 2013-10-15 | 2013-10-21 | 4 | 3 | 1 | 2013-10-21 |  | -29674 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-10-28 |  | 2013-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | Private | Y
NSTAR | Westport | 2453 | 2790 | 100 | PV | 2-532-532 | 2013-10-16 | 2013-10-18 | 2 | 0 | 2 | 2013-10-21 |  | -29674 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-25 |  | 2013-12-15 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-14 | Online | Private | Y
NSTAR | North Dartmouth | 2454 | 2747 | 25 | PV | 2-531-531 | 2013-10-18 | 2013-11-01 | 10 | 10 | 0 | 2013-11-01 |  | -29683 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2013-12-31 | Online | Private | Y
NSTAR | East Falmouth | 2455 | 2536 | 85 | PV | 4-77A-450 | 2013-10-17 |  | -29672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | Private | Y | 2013-10-18
NSTAR | East Falmouth | 2456 | 2536 | 90 | PV | 4-98A-98A | 2013-10-18 | 2013-10-24 | 4 | 3 | 1 | 2013-12-16 |  | -29712 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-25 |  | 2013-11-30 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | Private | Y
NSTAR | Kingston | 2457 | 2364 | 19 | PV | 3-17-910 | 2013-10-18 | 2013-10-28 | 6 | 5 | 1 | 2013-10-28 |  | -29679 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-09 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-01-31 | Online | Private | Y
NSTAR | Hopkinton | 2458 | 1748 | 85 | PV | 126-H1 | 2013-10-18 | 2013-10-28 | 6 | 5 | 1 | 2013-10-28 |  | -29679 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-11-27 |  |  | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-03-19 | Online | Private | Y
NSTAR | Hopkinton | 2459 | 1748 | 18 | PV | 126-H1 | 2013-10-21 | 2013-11-01 | 9 | 9 | 0 | 2013-11-01 |  | -29683 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-04 |  | 2013-12-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Awaiting Completion Docs | Private | Y | 2013-12-04
NSTAR | Canton | 2460 | 2021 | 60 | PV | 269-1320H1 | 2013-10-24 |  | -29677 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | Private | Y | 2013-10-24
NSTAR | Sudbury | 2461 | 1778 | 225 | PV | 342-H3 | 2013-10-28 | 2013-11-13 | 11 | 12 | -1 | 2013-11-13 |  | -29690 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-05-14 | 41 | 0 | 41 |  |  | 0 | 0 | 0 | 2014-06-09 |  | 2014-04-01 | Yes | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dedham | 2462 | 2026 | 1750 | PV | 20-H2, 20-H3 | 2013-10-25 | 2014-03-05 | 87 |  | 87 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Mattapoisett | 2463 | 2739 | 4000 | PV | 2-302-302 | 2013-10-25 | 2014-03-05 | 87 |  | 87 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Review Stage | Private | Y
NSTAR | Mattapoisett | 2464 | 2739 | 1000 | PV | 2-302-302 | 2013-10-25 | 2014-03-05 | 87 |  | 87 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Review Stage | Private | Y
NSTAR | Mattapoisett | 2465 | 2739 | 1000 | PV | 2-302-302 | 2013-10-30 | 2013-11-22 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | Private | Y
NSTAR | Dorchester | 2466 | 2121 | 27 | PV | 483-H3 | 2013-10-29 | 2013-11-18 | 13 | 12 | 1 | 2013-11-19 |  | -29694 | 0 | 0 | 2013-12-05 | 2014-01-10 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-28 |  | 2013-12-23 | Yes | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-06-25 | Online | Private | Y
NSTAR | Charlestown | 2467 | 2129 | 11 | PV | 10-H2 | 2013-11-08 | 2013-11-14 | 3 | 1 | 2 | 2013-11-15 |  | -29692 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-19 |  | 2013-12-25 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-02-14 | Online | Private | Y
NSTAR | Chilmark | 2468 | 2535 | 42 | PV | 4-91-220 | 2014-11-18 | 2015-01-02 | 31 | 0 | 31 | 2015-01-02 | 2015-01-08 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-19 | 2016-03-11 | 2015-06-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 1972361 | 2571 | 5000 | PV | 3-83-83 | 2013-11-25 | 2013-12-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2015-12-29 | 2016-04-19 | Online | Gov't
NSTAR | Carver | 1972386 | 2330 | 5000 | PV | 3-83-83 | 2013-12-02 | 2013-12-03 | 1 | 0 | 1 | 2013-12-05 | 2013-12-27 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-30 |  | 2014-07-10 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wayland | 1973375 | 1778 | 200 | PV | 342-H3 | 2013-12-10 | 2013-12-10 | 0 | 0 | 0 | 2013-12-11 | 2013-12-19 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2013-12-27 | 2013-12-31 | 2014-07-18 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2013-12-27 |  | Withdrawn | Private
NSTAR | East Boston | 1976430 | 2128 | 100 | PV | 488-H4 | 2013-12-11 | 2013-12-12 | 1 | 0 | 1 | 2013-12-17 | 2015-03-10 | 306 | 3 | 303 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-07-21 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Gov't
NSTAR | Woburn | 1976701 | 1801 | 1000 | PV | 375-H14 | 2013-12-16 | 2013-12-16 | 0 | 0 | 0 | 2013-12-18 | 2014-10-15 | 204 | 297 | -93 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-03 | 2015-05-20 | 2015-09-27 | No | EXP | 30 | 2014-10-14 | 2014-10-14 | 0 |  | 0 |  | 2015-10-20 |  | Withdrawn | Gov't
NSTAR | Plymouth | 1977739 | 2360 | 600 | PV | 3-13-943 | 2013-12-16 | 2013-12-16 | 0 | 0 | 0 | 2013-12-18 | 2014-01-15 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-01-22 |  | 2014-07-24 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-01-02 | 2015-10-21 | Online | GOV'T
NSTAR | Burlington | 1977755 | 1803 | 500 | PV | 391-H12 | 2013-12-19 | 2013-12-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't
NSTAR | Provincetown | 1978458 | 2657 | 20 | PV | 4-96-676 | 2013-12-23 | 2013-12-24 | 1 | 0 | 1 | 2013-12-31 | 2016-06-08 | 623 | 604 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-12-31 | TBD | COMP | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Mattapoisett | 1978822 | 2739 | 750 | PV | 2-301-301 | 2014-01-02 | 2014-01-02 | 0 | 106 | 0 | 2014-01-03 | 2015-01-07 | 251 | 139 | 112 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2014-08-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Waltham | 1980806 | 2451 | 1000 | PV | 526-1361H | 2014-01-03 | 2014-01-03 | 0 | 0 | 0 | 2014-02-04 | 2014-02-04 | 0 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-31 | 2014-06-05 | 2014-09-30 | No | EXP | 30 | 2014-09-04 | 2014-09-04 | 0 |  | 0 |  | 2014-09-25 |  | Withdrawn | Gov't
NSTAR | Chilmark | 1981127 | 2535 | 95 | PV | 4-97-126 | 2014-01-08 | 2014-01-08 | 0 | 0 | 0 | 2014-01-14 | 2014-02-05 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-10 |  | 2014-08-14 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-02-19 | 2015-02-19 | Online | Private
NSTAR | Hatchville | 1982667 | 2536 | 48 | PV | 4-98B-448 | 2014-01-09 | 2014-01-09 | 0 | 0 | 0 | 2014-01-15 | 2014-02-05 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-16 |  | 2014-09-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-05-16 | 2014-05-16 | Online | Private
NSTAR | Brighton | 1982906 | 2135 | 75 | Natural Gas | 467-H13 | 2014-01-16 | 2014-01-16 | 0 | 0 | 0 | 2014-01-24 | 2014-02-07 | 10 | 0 | 10 | 2014-02-20 | 2014-03-24 | 21 | 0 | 21 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-27 | 2014-04-17 | 2014-08-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Marshfield | 1984064 | 2050 | 18.5 | PV | 3-25-976 | 2014-01-20 | 2014-01-21 | 1 | 0 | 1 | 2014-01-20 | 2014-01-24 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-11 |  | 2014-08-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wayland | 1984570 | 1778 | 225 | PV | 342-H3 | 2014-01-21 | 2014-04-30 | 68 | 0 | 68 | 2014-01-24 | 2014-02-14 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-05 | 2014-05-13 | 2014-08-26 | TBD | EXP | 30 | 2014-05-16 | 2014-05-16 | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Acusnet | 1984711 | 2743 | 40 | PV | 2-241-241 | 2014-01-27 | 2014-05-06 | 68 | 0 | 68 | 2014-06-25 | 2014-08-22 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-26 |  | 2014-09-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-26 | Online | Private
NSTAR | Falmouth | 1985442 | 2536 | 90 | PV | 4-98A-98A | 2014-01-28 | 2014-01-30 | 2 | 0 | 2 | 2014-01-30 | 2014-02-05 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-02-11 |  | 2014-09-03 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Framingham | 1985681 | 1702 | 27.6 | PV | 240-H4 | 2014-01-30 | 2014-01-30 | 0 | 0 | 0 | 2014-02-05 | 2014-02-26 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-20 | 2014-08-25 | 2014-09-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-08-22 | 2014-08-22 | Online | Private
NSTAR | Dartmouth | 1986041 | 2748 | 21 | PV | 2-524-524 | 2014-02-10 | 2014-05-16 | 66 |  | 66 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2015-08-19 | Online | Private
NSTAR | Harwich | 1987679 | 2671 | 23 | PV | 4-92B-572 | 2014-02-10 | 2014-02-11 | 1 | 0 | 1 | 2014-02-11 | 2014-02-28 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-13 | 2014-04-15 | 2014-09-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-29 | Online | Private | Y
NSTAR | Bellingham | 1987709 | 2019 | 52.5 | PV | 65-H4 | 2014-02-12 | 2014-02-14 | 2 | 0 | 2 | 2014-02-14 | 2014-03-06 | 13 | 28 | -15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-29 |  | 2014-09-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-07-18 | Online | Private
NSTAR | Plymouth | 1988060 | 2360 | 38 | PV | 3-12-41J1 | 2014-02-18 | 2014-07-10 | 97 | 0 | 97 | 2014-02-19 | 2014-04-07 | 32 | 1 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-04 | 2016-01-05 | 2016-10-07 | Yes | EXP | 30 | 2016-07-22 |  | -30377 |  | 0 |  |  |  | Awaiting Completion Docs | Private | N
NSTAR | Plympton | 1988677 | 2367 | 840 | PV | 3-15-906 | 2014-01-30 | 2014-02-20 | 14 | 0 | 14 | 2014-03-07 | 2014-03-12 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-04-15 | 2014-09-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-12-19 | Online | Private
NSTAR | Ashland | 1988954 | 1721 | 80 | PV | 274-1429H1 | 2014-02-05 | 2014-02-24 | 12 | 0 | 12 | 2014-02-28 | 2014-02-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-11 |  | 2014-09-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-09-11 | Online | Private | N
NSTAR | Lexington | 1989453 | 2421 | 25.9 | PV | 533-H1 | 2014-02-11 | 2014-02-26 | 10 | 0 | 10 | 2014-03-14 | 2014-03-20 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-04-11 | 2014-08-07 | 80 | 7 | 73 | 2015-05-04 | 2015-05-07 | 3 | 0 | 3 | 2014-08-04 | 2015-05-11 | 2015-11-30 | No | STD | 60 | 2015-09-30 | 2015-09-30 | 0 |  | 0 |  | 2016-03-01 | 2016-03-01 | Online | Private | N
NSTAR | Needham | 1989732 | 2492 | 3120 | PV | 148-H1 | 2014-02-14 | 2014-02-28 | 9 | 0 | 9 | 2014-03-04 | 2014-03-12 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-03-14 | 2014-04-15 | 2014-10-03 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-23 | Online | Gov't | Y
NSTAR | Wayland | 1989963 | 1778 | 20 | PV | 342-H1 | 2014-02-28 | 2014-09-20 | 139 | 0 | 139 | 2014-03-05 | 2014-04-03 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-11-03 | 2015-06-05 | 151 | 9 | 142 | 2015-11-16 | 2015-11-25 | 7 | 0 | 7 | 2015-03-04 | 2016-04-20 | 2016-11-01 | No | STD | 60 | 2016-05-27 |  | -30337 |  | 0 |  |  |  | Online | PRIVATE | N
NSTAR | Hyde Park | 1990011 | 2136 | 3190 | PV | 496-H2 | 2014-02-28 | 2014-03-06 | 4 | 0 | 4 | 2014-03-10 | 2014-04-29 | 34 | 22 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-05 |  | 2014-10-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-28 | Online | Gov't | Y
NSTAR | Wareham | 1991204 | 2538 | 100 | PV | 3-84-961 | 2014-03-14 | 2014-03-14 | 0 | 0 | 0 | 2014-03-20 | 2014-03-31 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-28 | 2014-05-05 | 2015-01-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-05-01 | 2015-05-01 | Online | Private
NSTAR | Roxbury | 1992441 | 2120 | 75 | Natural Gas | 5201 | 2014-03-18 | 2014-10-08 | 141 |  | 141 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2015-05-20
NSTAR | Mattapoisett | 1992844 | 2739 | 2000 | PV | 2-301-301 | 2014-03-18 | 2014-10-10 | 143 |  | 143 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-12-27 | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2015-03-12
NSTAR | Mattapoisett | 1992854 | 2739 | 2000 | PV | 2-306-306 | 2014-03-18 | 2014-11-07 | 162 |  | 162 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2015-05-20
NSTAR | Mattapoisett | 1992858 | 2739 | 1000 | PV | 2-306-306 | 2014-03-25 |  | -29778 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Jamaica Plain | 1994005 | 2130 | 34.2 | PV | 284-1300H1 | 2014-03-26 | 2014-04-01 | 4 | 0 | 4 | 2014-04-01 | 2014-04-23 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-15 | 2014-11-03 | 2014-10-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-11-18 | 2014-11-18 | Online | Private | N
NSTAR | Cambridge | 1994170 | 2142 | 75 | Natural Gas | 875-1328 | 2014-01-22 | 2014-03-27 | 44 | 0 | 44 | 2014-03-31 | 2014-04-02 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-04-15 | 2014-09-03 | 2014-10-31 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-11-18 | 2014-11-18 | Online | Private
NSTAR | Waltham | 1994357 | 2453 | 75 | Natural Gas | 33-H1 | 2014-04-20 | 2014-04-22 | 1 | 0 | 1 | 2014-05-12 | 2014-05-23 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-29 |  | 2014-11-28 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-02-18 |  | Withdrawn | Gov't
NSTAR | Natick | 1998808 | 1760 | 150 | Natural Gas | 23-1339H1 | 2014-04-29 | 2014-04-30 | 1 | 0 | 1 | 2014-05-13 | 2014-08-20 | 68 | 64 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-19 | 2016-03-11 | 2014-12-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Newton | 2000080 | 2458 | 100 | PV | 467-H3 | 2014-03-20 | 2014-03-27 | 5 | 0 | 5 | 2014-05-06 | 2014-05-08 | 2 | 0 | 2 | 2014-05-13 | 2014-05-28 | 10 | 0 | 10 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 |  | 2017-10-31 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Walpole | 2000815 | 2071 | 3450 | PV | 146-H3 | 2014-03-13 | 2014-03-13 | 0 |  | 0 | 2014-03-13 |  | -29771 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-01 | 2015-09-01 | [6 empty] | 0 |  | 0 |  |  | 2017-08-10 | Online
NSTAR | Natick | 2001305 | 1760 | 580 | PV | 433-H10 | 2014-05-05 | 2014-05-06 | 1 | 0 | 1 | 2014-05-07 | 2014-09-23 | 95 | 131 | -36 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-29 | 2014-12-11 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-06-03 | Online | Private
NSTAR | Natick | 2001314 | 1760 | 620 | PV | 433-H9 | 2014-03-24 | 2014-05-05 | 29 | 0 | 29 | 2014-05-07 | 2014-11-26 | 139 | 132 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-30 | 2014-12-11 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-12-28 | 2016-06-03 | Online | Private
NSTAR | Natick | 2001342 | 1760 | 520 | PV | 433-H10 | 2014-01-30 | 2014-03-27 | 38 | 0 | 38 | 2014-05-14 | 2014-06-25 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-09 |  | 2014-12-17 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-10-24 | 2015-12-28 | Online | Private | Y
NSTAR | Pocasset | 2002111 | 2559 | 248.4 | PV | 4-86-86 | 2014-02-05 | 2014-04-22 | 51 | 0 | 51 | 2014-05-16 | 2014-05-16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-05-20 | 2014-08-14 | 2014-12-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-10-23 | Online | Private
NSTAR | Marshfield | 2002502 | 2050 | 9 | PV | 3-24B-915 | 2014-02-14 | 2014-05-02 | 52 | 0 | 52 | 2014-05-19 | 2014-05-28 | 6 | 7 | -1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-30 |  | 2014-12-19 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | Private
NSTAR | West Tisbury | 2002682 | 2575 | 204 | PV | 4-97-220 | 2014-05-14 | 2014-05-15 | 1 | 0 | 1 | 2014-06-18 | 2015-06-15 | 252 | 243 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-05-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Gov't
NSTAR | Cambridge | 2002879 | 2139 | 802 | PV | 817-05 | 2014-05-15 | 2014-05-16 | 1 | 0 | 1 | 2014-05-19 | 2014-06-10 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-07-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | New Bedford | 2003173 | 2745 | 810 | Natural Gas | 2-107-107 | 2014-03-10 | 2014-05-12 | 43 | 0 | 43 | 2014-06-06 | 2014-06-17 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-19 | 2014-08-11 | 2015-01-05 | TBD | EXP | 30 | 2014-10-01 | 2014-10-01 | 0 |  | 0 |  |  | 2014-10-10 | Online | Private
NSTAR | Chatham | 2004834 | 2659 | 44 | PV | 4-95A-95A | 2014-03-20 | 2014-05-13 | 37 | 0 | 37 | 2014-06-03 | 2014-06-09 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-10 | 2014-11-19 | 2015-06-30 | TBD | EXP | 30 | 2015-07-17 | 2015-07-17 | 0 |  | 0 |  |  | 2015-07-28 | Online | Private
NSTAR | Edgartown | 2005414 | 2539 | 80 | PV | 4-75-123 | 2014-05-30 | 2015-05-07 | 237 | 0 | 237 | 2014-06-05 | 2014-12-29 | 140 | 148 | -8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-28 |  | 2015-01-08 | No | STD | 60 |  |  | 0 |  | 0 |  | 2016-06-23 | 2016-06-30 | Online | Private | N
NSTAR | Jamaica Plain | 2005440 | 2130 | 1640 | Natural Gas | 496-H4 | 2014-05-30 | 2015-05-16 | 243 | 0 | 243 | 2014-06-05 | 2015-01-19 | 155 | 148 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-01-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-06-30 | Online
NSTAR | New Bedford | 2005461 | 2745 | 2000 | Natural Gas | 2-101-101 | 2014-05-14 | 2014-06-03 | 13 | 0 | 13 | 2014-06-06 | 2014-06-10 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-02 | 2014-09-12 | 2015-01-12 | TBD | EXP | 30 | 2014-10-09 | 2014-10-09 | 0 |  | 0 |  | 2014-11-05 | 2014-11-18 | Withdrawn | Private
NSTAR | Framingham | 2006363 | 1702 | 120 | PV | 274-H4 | 2014-05-16 | 2014-06-03 | 11 | 0 | 11 | 2014-06-06 | 2014-07-01 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-02 |  | 2015-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-11-21 | Online | Private
NSTAR | Boston | 2006387 | 2109 | 45 | PV | 3009 | 2014-05-19 | 2014-06-05 | 12 | 0 | 12 | 2014-06-12 | 2014-10-23 | 91 | 45 | 46 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-15 |  | 2015-01-14 | No | EXP | 30 | 2015-01-12 | 2015-01-12 | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | East Boston | 2006940 | 2128 | 750 | PV | 108-196H1 | 2014-06-06 | 2014-06-09 | 1 | 0 | 1 | 2014-06-11 | 2014-06-30 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-01 |  | 2015-01-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Dover | 2007317 | 2030 | 20.2 | PV | 456-H5 | 2014-06-03 | 2014-06-09 | 4 | 0 | 4 | 2014-06-11 | 2014-06-23 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-25 | 2014-10-01 | 2015-01-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-02-19 | 2015-02-19 | Online | Private
NSTAR | Chatham | 2007346 | 2659 | 50 | PV | 4-95A-95A | 2014-06-06 | 2014-06-11 | 3 | 0 | 3 | 2014-06-13 | 2014-06-17 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-06-18 | 2014-10-01 | 2015-01-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-02 | Online | Private
NSTAR | Edgartown | 2007907 | 2539 | 18.7 | PV | 4-75-123 | 2014-06-06 | 2014-06-11 | 3 | 0 | 3 | 2014-06-13 | 2014-10-07 | 79 | 46 | 33 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-10-24 | 2015-01-14 | 55 | 0 | 55 | 2015-08-31 | 2015-10-13 | 31 | 0 | 31 | 2015-01-12 | 2016-02-09 | 2016-08-16 | No | STD | 60 | 2016-02-02 | 2016-02-02 | 0 |  | 0 |  | 2016-07-19 | 2016-07-19 | Online | Private | N
NSTAR | Canton | 2007950 | 2021 | 980 | PV | 470-H7 | 2014-06-11 | 2014-06-11 | 0 | 0 | 0 | 2014-06-13 | 2014-10-07 | 79 | 46 | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2014-10-24 | 2015-01-14 | 55 | 0 | 55 | 2015-08-31 | 2015-10-13 | 31 | 0 | 31 | 2015-01-12 | 2016-02-09 | 2016-08-16 | No | STD | 60 | 2016-02-02 | 2016-02-02 | 0 |  | 0 |  | 2016-07-19 | 2016-07-19 | Online | Private | N
NSTAR | Holliston | 2008170 | 1746 | 17 | PV | 274-H5 | 2014-06-11 | 2014-06-12 | 1 | 0 | 1 | 2014-06-16 | 2014-07-07 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-09 | 2014-09-22 | 2014-09-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Stoneham | 2008179 | 2180 | 15.9 | PV | 375-H8 | 2014-06-11 | 2014-06-17 | 3 | 0 | 3 | 2014-06-20 | 2014-09-10 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-11 | 2014-09-11 | 2015-01-26 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-11 | Online | Private | N
NSTAR | Plymouth | 2009028 | 2360 | 20 | PV | 3-89-926 | 2014-06-13 | 2014-06-17 | 1 | 0 | 1 | 2014-06-20 | 2014-08-15 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-26 |  | 2015-01-26 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-10-09 | 2014-11-17 | Online | Private
NSTAR | Wareham | 2009038 | 2576 | 18 | PV | 3-85-85 | 2014-06-13 | 2014-06-18 | 2 | 0 | 2 | 2014-06-27 | 2014-07-01 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-01 | 2014-09-03 | 2015-01-27 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-02-04 | 2016-02-04 | Online | Private
NSTAR | Boston | 2009215 | 2118 | 75 | Natural Gas | 385-H17 | 2014-06-16 | 2014-06-20 | 3 | 0 | 3 | 2014-06-26 | 2014-07-08 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 |  | 2015-01-29 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-31 | 2014-12-31 | Online | Gov't
NSTAR | Lexington | 2009595 | 2421 | 388 | PV | 320-H5XY | 2014-06-16 | 2014-06-20 | 3 | 0 | 3 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-31 | Online | Gov't | N
NSTAR | Lexington | 2009605 | 2420 | 135 | PV | 391-H11 | 2014-06-20 | 2014-06-20 | 0 | 0 | 0 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-31 | 2014-12-31 | Online | Gov't
NSTAR | Lexington | 2009611 | 2420 | 135 | PV | 533-H3 | 2014-06-20 | 2014-06-20 | 0 | 0 | 0 | 2014-06-27 | 2014-06-30 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-02 | 2014-12-10 | Online | Private
NSTAR | Lexington | 2009615 | 2421 | 79 | PV | 320-H5XY | 2014-06-20 | 2014-06-27 | 5 | 0 | 5 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-16 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-31 | Online | Private
NSTAR | Lexington | 2009625 | 2421 | 171 | PV | 320-H5XY | 2014-06-20 | 2014-06-26 | 4 | 0 | 4 | 2014-06-26 | 2014-06-30 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 | 2014-07-15 | 2015-01-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-23 | Online | Private
NSTAR | Lexington | 2009631 | 2420 | 40 | PV | 3403 | 2014-06-23 | 2014-06-26 | 3 | 0 | 3 | 2014-06-27 | 2014-07-02 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-03 | 2014-10-01 | 2015-01-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-02-19 | Online | Private
NSTAR | Chatham | 2009828 | 2659 | 60 | PV | 4-95A-95A | 2014-06-23 | 2014-06-26 | 3 | 0 | 3 | 2014-06-27 | 2014-07-23 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-24 |  | 2015-01-30 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-31 | 2015-04-08 | Online | Private
NSTAR | Waltham | 2009878 | 2451 | 675 | PV | 531-1359H | 2014-06-24 | 2014-06-24 | 0 | 0 | 0 | 2014-07-01 | 2014-07-29 | 19 | 308 | -289 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-04 |  | 2015-02-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | East Boston | 2010040 | 2128 | 552 | PV | 108-196H1 | 2014-06-26 | 2014-07-01 | 3 | 0 | 3 | 2014-07-03 | 2014-07-08 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-08 | 2014-10-06 | 2015-02-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2011256 | 2576 | 42 | PV | 3-86-966 | 2014-06-26 | 2014-07-03 | 5 | 0 | 5 | 2014-08-04 | 2014-10-06 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-20 | 2015-02-05 | 2015-10-01 | TBD | EXP | 30 | 2015-01-30 |  | -29992 |  | 0 |  | 2015-09-23 |  | Withdrawn | Gov't
NSTAR | Framingham | 2012062 | 1701 | 500 | PV | 278-H2 | 2014-07-09 | 2014-07-10 | 1 | 0 | 1 | 2014-07-11 | 2014-08-22 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-06 | 2015-03-02 | 2015-02-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-02 | 2015-09-21 | Online | Gov't
NSTAR | Falmouth | 2012720 | 2540 | 47.8 | PV | 4-107-830 | 2014-07-09 | 2014-07-10 | 1 | 0 | 1 | 2014-07-11 | 2014-08-22 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-07-16 |  | 2015-02-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Hyannis | 2012789 | 2601 | 252 | PV | 4-84B-524 | 2014-07-03 | 2014-07-10 | 4 | 0 | 4 | 2014-07-16 | 2014-08-25 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-04 | 2014-09-03 | 2015-02-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-31 |  | Withdrawn | Private
NSTAR | Allston | 2012919 | 2134 | 90 | PV | 548-92H3 | 2014-07-15 | 2014-07-22 | 5 | 0 | 5 | 2014-08-04 | 2014-07-29 | -6 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-17 | 2014-10-27 | 2015-02-23 | No | EXP | 30 | 2014-11-14 | 2014-11-14 | 0 |  | 0 |  | 2014-12-19 | 2015-01-02 | Online | Private | N
NSTAR | Acton | 2013623 | 1720 | 126 | PV | 416-H9 | 2014-07-18 | 2014-07-22 | 2 | 0 | 2 | 2014-07-28 | 2014-07-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-04 |  | 2015-02-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-10 | Online | Private
NSTAR | Acton | 2014462 | 1720 | 81 | PV | 416-H1 | 2014-07-23 | 2014-07-28 | 3 | 0 | 3 | 2014-08-19 | 2014-10-01 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-20 |  | 2015-10-01 | TBD | EXP | 30 | 2014-11-14 | 2014-11-14 | 0 |  | 0 |  | 2015-09-17 | 2015-09-17 | Online | Gov't
NSTAR | Framingham | 2015313 | 1701 | 500 | PV | 433-H11 | 2014-07-22 | 2014-07-23 | 1 | 0 | 1 | 2014-07-25 | 2014-08-05 | 7 | 73 | -66 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-28 | 2015-01-27 | 2015-06-19 | No | EXP | 30 | 2015-05-27 | 2015-05-27 | 0 |  | 0 |  | 2015-06-16 | 2015-07-08 | Online | Private
NSTAR | Holliston | 2015374 | 1746 | 300 | PV | 65-H7 | 2014-07-24 | 2014-08-19 | 18 | 0 | 18 | 2014-08-04 | 2014-08-11 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-17 | 2014-11-03 | 2015-03-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-07-08 | Online | Private
NSTAR | Dorchester | 2015660 | 2122 | 89 | PV | 6702 | 2014-07-30 | 2014-08-01 | 2 | 0 | 2 | 2014-08-05 | 2014-08-22 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2014-09-29 | 2015-04-17 | 140 | 0 | 140 |  |  | 0 | 0 | 0 |  |  | 2015-03-10 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Rochester | 2016902 | 2770 | 2000 | PV | 3-703-703 | 2014-08-04 | 2014-08-04 | 0 | 0 | 0 | 2014-08-11 | 2014-12-02 | 77 | 60 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-17 | 2015-09-08 | 2016-03-15 | No | EXP | 30 | 2016-01-28 | 2016-01-28 | 0 |  | 0 |  | 2016-04-14 |  | Withdrawn | Private | N
NSTAR | Charlestown | 2017443 | 2129 | 391 | PV | 10-H1 | 2014-08-05 | 2014-08-11 | 4 | 0 | 4 | 2014-08-15 | 2014-11-21 | 67 | 34 | 33 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2016-04-11 | 2016-04-14 | 3 | 0 | 3 | 2015-03-26 | 2016-07-28 | 2016-12-15 | No | STD | 60 |  |  | 0 |  | 0 |  |  |  | Field Com | Private | N
NSTAR | Hopkinton | 2017615 | 1748 | 342 | PV | 126-H4 | 2014-08-06 | 2014-08-15 | 7 | 0 | 7 | 2014-09-24 |  | -29904 |  | 0 |  |  | 0 | 0 | 0 | 2014-08-15 | 2014-10-04 | 34 | 11 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-23 |  | 2015-03-17 | No | TBD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | New Bedford | 2017870 | 2745 | 2000 | Natural Gas | 2-101-101 | 2014-08-07 | 2014-08-15 | 6 | 0 | 6 | 2014-09-24 | 2014-09-24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-30 | 2014-10-06 | 2015-03-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-02 | Online | Private | N
NSTAR | Kingston | 2018246 | 2364 | 142.5 | PV | 3-15-15 | 2014-08-11 | 2014-08-15 | 4 | 0 | 4 | 2014-09-24 | 2014-10-02 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-10 |  | 2015-03-20 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-08-17 | 2015-08-18 | Online | PRIVATE
NSTAR | East Walpole | 2018681 | 2032 | 325.6 | PV | 135-1301 | 2014-08-12 | 2014-08-15 | 3 | 0 | 3 | 2014-08-15 | 2014-08-28 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-04 |  | 2015-03-23 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-13 | Online | Private | N
NSTAR | South Walpole | 2018960 | 2071 | 85 | PV | 146-H3 | 2014-08-12 | 2014-08-15 | 3 | 0 | 3 | 2014-08-19 | 2014-09-09 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-03 |  | 2015-03-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-20 | Online | Private
NSTAR | Plymouth | 2018969 | 2360 | 50 | PV | 4-81A-406 | 2014-08-19 | 2014-08-19 | 0 | 0 | 0 | 2014-08-21 | 2014-09-08 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-16 | 2015-03-02 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2015-03-30 | Online | Private
NSTAR | Dover | 2019996 | 2030 | 21.2 | PV | 456-H5 | 2014-08-19 | 2014-08-20 | 1 | 0 | 1 | 2014-08-20 | 2014-09-26 | 26 | 9 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-28 | 2016-08-18 | 2015-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Fee | Gov't
NSTAR | Truro | 2020127 | 2666 | 1000 | PV | 4-96-96 | 2014-08-20 | 2014-08-25 | 3 | 0 | 3 | 2014-08-25 |  | -29883 |  | 0 |  |  | 0 | 0 | 0 | 2014-10-21 | 2015-01-09 | 55 | 120 | -65 | 2015-07-02 | 2015-07-10 | 6 | 3 | 3 | 2016-03-10 | 2016-03-31 | 15 | 0 | 15 | 2015-07-08 | 2016-04-25 | 2016-12-02 | No | TBD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Kingston | 2020238 | 2364 | 668 | PV | 3-909-909 | 2014-08-21 | 2014-08-25 | 2 | 0 | 2 | 2014-08-25 | 2014-09-15 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-18 | 2015-07-15 | 2015-04-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-08 | Online | Private
NSTAR | Plymouth | 2020496 | 2360 | 92.8 | PV | 3-14-911 | 2014-08-25 | 2014-08-28 | 3 | 0 | 3 | 2014-08-28 | 2014-11-10 | 50 | 16 | 34 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-17 |  | 2015-04-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-17 | 2015-01-02 | Online | Private
NSTAR | Dartmouth | 2020964 | 2747 | 232 | PV | 2-532-532 | 2014-08-26 | 2014-08-28 | 2 | 0 | 2 | 2014-08-28 | 2014-09-17 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-25 | 2014-10-31 | 2014-12-15 | TBD | EXP | 30 | 2014-12-12 | 2014-12-12 | 0 |  | 0 |  |  | 2014-12-17 | Online | Private
NSTAR | Holliston | 2021069 | 1746 | 185 | PV | 65-H2 | 2014-08-26 | 2014-08-28 | 2 | 0 | 2 | 2014-08-28 | 2014-10-15 | 32 | 22 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 | 2014-12-05 | 2014-12-31 | No | EXP | 30 | 2015-02-06 | 2015-02-06 | 0 |  | 0 |  | 2015-02-18 | 2015-02-27 | Online | Private
NSTAR | Holliston | 2021094 | 1746 | 500 | PV | 65-H2 | 2014-08-27 | 2014-08-28 | 1 | 0 | 1 | 2014-09-04 | 2014-10-09 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 |  | 2017-01-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-02-27 | Online | Private
NSTAR | Plymouth | 2021322 | 2360 | 500 | PV | 3-12-12 | 2014-09-02 | 2014-09-03 | 1 | 0 | 1 | 2014-09-04 | 2015-01-30 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-05 |  | 2015-04-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wianno | 2022522 | 2655 | 32.8 | PV | 4-80A-892 | 2014-09-04 | 2014-09-04 | 0 | 0 | 0 | 2015-02-13 | 2015-04-01 | 33 | 107 | -74 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 |  | 2015-04-14 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-10-06 |  | Withdrawn | Private
NSTAR | Canton | 2022843 | 2021 | 300 | PV | 470-H7 | 2014-09-03 | 2014-09-04 | 1 | 0 | 1 | 2014-09-09 | 2014-09-22 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 | 2014-10-02 | 2015-04-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-06 | Online | Private
NSTAR | Canton | 2022875 | 2021 | 170 | PV | 470-H8 | 2014-09-02 | 2014-09-03 | 1 | 0 | 1 | 2014-09-09 | 2014-09-15 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-26 | 2014-09-29 | 2015-04-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-19 | Online | Private
NSTAR | Dennis | 2022973 | 2660 | 75 | PV | 4-92B-92B | 2014-09-03 | 2014-09-04 | 1 | 0 | 1 | 2014-09-09 | 2014-09-29 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-29 | 2014-10-06 | 2015-04-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-20 | Online | Private
NSTAR | Kingston | 2023232 | 2364 | 21.5 | PV | 3-15-15 | 2014-09-18 |  | -29900 | 0 | 0 | 2014-09-10 | 2014-10-01 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-09-18 |  | 2015-04-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-23 | 2014-12-31 | Online | Private
NSTAR | Wareham | 2023726 | 2571 | 324.8 | PV | 3-86-966 | 2014-09-10 | 2014-09-10 | 0 | 0 | 0 | 2014-09-18 | 2014-10-10 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-08 |  | 2015-04-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2014-12-17 | 2014-12-23 | Online | Private
NSTAR | Dartmouth | 2024047 | 2747 | 301.6 | PV | 2-531-531 | 2014-09-11 | 2014-09-12 | 1 | 0 | 1 | 2014-09-19 | 2015-01-16 | 81 | 53 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-04-22 | TBD | STD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2024196 | 2571 | 2000 | PV | 3-84-84 | 2014-08-13 | 2014-09-16 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Hatchville | 2024739 | 2536 | 3000 | PV | 4-98A-98A | 2014-09-16 |  | -29898 | 0 | 0 | 2014-09-18 | 2014-10-01 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 |  | 2015-04-27 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-21 | 2017-04-06 | Online | Gov't
NSTAR | Natick | 2024912 | 1760 | 264 | PV | 433-H9 | 2014-08-27 | 2014-09-15 | 12 | 0 | 12 | 2014-09-23 | 2014-09-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 | 2014-10-02 | 2015-04-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-21 | Online | Private
NSTAR | Dorchester | 2025617 | 2122 | 56 | PV | 466-1482H1 | 2014-09-18 | 2014-09-18 | 0 | 0 | 0 | 2014-09-22 | 2014-10-09 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-16 | 2014-10-17 | 2015-04-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-02-27 | Online | Private
NSTAR | Canton | 2025700 | 2021 | 85 | PV | 470-H11 | 2014-09-19 | 2014-09-20 | -1 | 0 | 0 | 2014-09-22 | 2014-10-20 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-20 |  | 2015-04-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Bourne | 2025848 | 2532 | 499 | PV | 3-89-925 | 2014-09-22 | 2014-09-22 | 0 | 0 | 0 | 2014-09-30 | 2014-11-10 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-11 |  | 2015-05-01 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-30 |  | Withdrawn | Private
NSTAR | Burlington | 2026226 | 1803 | 500 | PV | 391-H9 | 2014-09-25 | 2014-09-25 | 0 | 0 | 0 | 2014-09-29 | 2015-07-21 | 207 | 195 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 | 2015-11-18 | 2016-06-16 | No | EXP | 30 | 2016-05-16 | 2016-05-16 | 0 |  | 0 |  |  |  | Online | Private | N
NSTAR | Norfolk | 2026963 | 2056 | 499 | PV | 146-H3 | 2014-09-25 | 2014-09-26 | 1 | 0 | 1 | 2014-10-01 | 2014-10-01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 | 2014-12-30 | 2015-05-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-28 | Online | Private
NSTAR | Lexington | 2027027 | 2420 | 15 | PV | 391-H3 | 2014-09-26 | 2014-09-27 | -1 | 0 | 0 | 2014-09-30 | 2014-10-21 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 |  | 2015-05-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Somerville | 2027112 | 2145 | 50 | PV | 14N26 | 2014-09-29 | 2014-09-29 | 0 | 0 | 0 | 2014-10-01 | 2014-11-21 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-21 |  | 2015-05-08 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2014-11-21 | 2014-12-24 | Online | Private
NSTAR | Woburn | 2027532 | 1801 | 278.4 | PV | 375-H9 | 2014-09-30 | 2014-10-02 | 2 | 0 | 2 | 2014-10-03 | 2014-10-06 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-14 |  | 2015-05-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2014-12-22 | Online | Private
NSTAR | Holliston | 2027916 | 1746 | 42 | PV | 274-H3 | 2014-10-01 | 2014-12-09 | 46 | 0 | 46 | 2014-12-09 | 2014-12-15 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 |  | 2015-03-01 | TBD | EXP | 30 | 2015-03-02 | 2015-03-02 | 0 |  | 0 |  |  | 2015-07-28 | Online | Private
NSTAR | Norfolk | 2028128 | 2056 | 22 | PV | 146-H3 | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | 2014-10-14 | 2014-11-06 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-05-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-08 | Online | Private
NSTAR | Pocasset | 2029122 | 2559 | 55.2 | PV | 4-81A-406 | 2014-10-06 | 2014-10-06 | 0 | 0 | 0 | 2014-10-08 | 2014-11-12 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-09 | 2015-01-15 | 2015-04-30 | No | EXP | 30 | 2015-03-09 | 2015-03-09 | 0 |  | 0 |  | 2015-04-27 | 2015-04-27 | Online | Private | N
NSTAR | Marion | 2029145 | 2738 | 783 | PV | 3-85-85 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-16 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-27 | 2014-10-27 | 2015-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-27 | Online | Private
NSTAR | Framingham | 2029290 | 1702 | 42.5 | PV | 240-H4 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-17 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-10-31 |  | 2015-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-27 | Online | Private
NSTAR | Plymouth | 2029298 | 2360 | 30.9 | PV | 3-89-926 | 2014-10-07 | 2014-10-07 | 0 | 0 | 0 | 2014-10-09 | 2014-10-31 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-08 | Online | Private
NSTAR | Pocasset | 2029376 | 2559 | 34.2 | PV | 4-81A-406 | 2014-10-09 | 2014-10-09 | 0 | 0 | 0 | 2014-10-17 | 2015-05-20 | 150 | 115 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-03 |  | 2015-05-20 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-03-02 | 2016-03-02 | Online | Gov't | N
NSTAR | Plymouth | 2029874 | 2360 | 225 | Natural Gas | 3-13-943 | 2014-10-09 | 2014-10-10 | 1 | 0 | 1 | 2014-10-27 | 2014-11-20 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-10 |  | 2015-05-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2029884 | 2571 | 60 | PV | 3-86-966 | 2014-10-21 | 2014-10-21 | 0 | 0 | 0 | 2014-10-23 | 2014-12-22 | 40 | 39 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-23 | 2015-06-01 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-03-12 | 2015-04-22 | Online | Private
NSTAR | Dennis | 2031577 | 2641 | 16.1 | PV | 4-89A-552 | 2014-10-22 | 2014-10-23 | 1 | 0 | 1 | 2014-10-27 | 2014-10-28 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Dennisport | 2031909 | 2639 | 72 | PV | 4-92B-583 | 2014-10-23 | 2014-10-23 | 0 | 0 | 0 | 2014-10-27 | 2014-10-28 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Yarmouth | 2032033 | 2664 | 42 | PV | 4-92A-562 | 2014-10-23 | 2014-10-23 | 0 | 0 | 0 | 2014-10-27 | 2014-11-14 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-09 | 2015-02-18 | 2015-06-15 | TBD | EXP | 30 | 2015-05-21 | 2015-05-21 | 0 |  | 0 |  | 2015-07-08 | 2015-07-13 | Online | Private
NSTAR | Marion | 2032055 | 2738 | 250 | PV | 3-304-304 | 2014-10-27 | 2014-11-05 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | Private | N
NSTAR | Bellingham | 2032500 | 2019 | 480 | PV | 65-H4 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | 2014-10-31 | 2014-11-03 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-05 | 2014-11-21 | 2015-06-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-26 | Online | Private
NSTAR | Hopkinton | 2033025 | 1748 | 15.2 | PV | 65-H6 | 2014-10-29 | 2014-10-29 | 0 | 0 | 0 | 2014-10-31 | 2014-11-06 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-11-13 |  | 2015-06-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-01-12 | Online | Private
NSTAR | Westport | 2033167 | 2790 | 30 | PV | 2-532-532 | 2014-10-30 | 2014-12-18 | 33 | 0 | 33 | 2014-12-29 | 2015-01-12 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-06-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights | Private
NSTAR | Chilmark | 2033372 | 2535 | 195.2 | PV | 4-97-126 | 2014-11-03 | 2014-11-03 | 0 | 0 | 0 | 2014-11-06 | 2014-11-24 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-11 |  | 2015-06-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Buzzards Bay | 2034325 | 2532 | 104 | PV | 3-88-2J4 | 2014-11-04 | 2014-11-04 | 0 | 0 | 0 | 2014-11-07 | 2014-11-12 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-02 | 2014-12-30 | 2015-06-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Newton | 2034511 | 2459 | 36 | PV | 292-H3 | 2014-11-05 | 2015-01-20 | 51 | 0 | 51 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-21 |  | 2015-06-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-28 | Online | Private
NSTAR | New Bedford | 2034765 | 2740 | 30.9 | PV | 2-89-14 | 2014-11-05 | 2014-11-06 | 1 | 0 | 1 | 2014-11-10 | 2014-12-10 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-15 |  | 2015-06-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-05-12 | 2015-05-12 | Online | Private
NSTAR | New Bedford | 2034871 | 2746 | 600 | PV | 2-83-403 | 2014-11-06 | 2014-11-07 | 1 | 0 | 1 | 2014-12-12 | 2015-03-30 | 75 | 65 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-06-17 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-12 | Online | Private
NSTAR | Dedham | 2034950 | 2026 | 794 | PV | 20-H5 | 2014-11-10 | 2014-11-10 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Ashland | 2035449 | 1721 | 3756 | PV | 274-1429H1 | 2014-11-10 | 2014-11-18 | 5 | 61 | -56 | 2014-11-14 | 2015-01-09 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-12-01 | 2015-12-14 | 9 | 0 | 9 | 2015-05-13 | 2016-02-29 | 2016-08-12 | No | STD | 60 | 2016-05-18 | 2016-05-18 | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Wareham | 2035472 | 2571 | 999 | PV | 3-85-955 | 2014-11-12 | 2014-11-13 | 1 | 0 | 1 | 2014-11-14 | 2015-01-12 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 | 2016-12-29 | 2015-06-22 | TBD | STD | 60 |  |  | 0 |  | 0 |  |  | 2016-08-29 | Online | Private
NSTAR | Plymouth | 2035699 | 2360 | 993.6 | PV | 3-89-926 | 2014-11-12 | 2014-11-12 | 0 | 0 | 0 | 2014-11-18 | 2014-11-19 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-05 |  | 2015-06-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Acusnet | 2035823 | 2743 | 43.6 | PV | 2-106-160 | 2014-11-13 | 2014-11-13 | 0 | 0 | 0 | 2014-12-24 | 2015-02-24 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-06-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-04-21 | 2015-04-24 | Online | Private
NSTAR | Dedham | 2035957 | 2026 | 150 | Natural Gas | 13-H1 | 2014-11-14 | 2014-11-14 | 0 | 0 | 0 | 2015-02-10 | 2015-09-01 | 145 | 112 | 33 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-06-24 | No | COMP | 160 |  |  | 0 |  | 0 |  |  |  | Screening | Private
NSTAR | Plymouth | 2036219 | 2360 | 4000 | PV | 3-14-934 | 2014-11-18 | 2014-12-16 | 19 | 0 | 19 | 2014-12-16 | 2015-02-23 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-11 | 2015-08-25 | 2015-06-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Lexington | 2036677 | 2421 | 15.75 | PV | TBD | 2014-11-17 |  | -29940 | 0 | 0 | 2015-01-02 | 2015-01-08 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-14 |  | 2015-06-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Walpole | 2036754 | 2081 | 138 | PV | 146-H3 | 2015-08-04 | 2015-08-07 | 3 | 0 | 3 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-08-11 |  | -30129 | 172 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 |  | 2016-03-14 | No | TBD | 60 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | Private
NSTAR | Plymouth | 2036912 | 2360 | 960 | PV | 3-12-12 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | 2014-11-27 | 2014-12-23 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 |  | 2015-06-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-07-01 |  | Withdrawn | Private
NSTAR | Yarmouth | 2036990 | 2664 | - | PV | TBD | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | 2014-12-12 | 2014-12-16 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 | 2015-01-27 | 2015-06-29 | No | EXP | 30 | 2015-02-23 | 2015-02-23 | 0 |  | 0 |  | 2015-03-06 | 2015-03-06 | Online | Gov't
NSTAR | New Bedford | 2037115 | 2745 | 300 | PV | 2-104-104 | 2014-11-19 | 2014-11-19 | 0 | 0 | 0 | 2014-11-27 | 2015-02-23 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-23 | 2015-06-02 | 2015-06-29 | No | EXP | 30 | 2015-07-06 | 2015-07-06 | 0 |  | 0 |  | 2015-07-14 | 2015-07-17 | Online | Private
NSTAR | New Bedford | 2037121 | 2745 | 266 | PV | 2-104-104 | 2014-11-20 | 2014-11-24 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Hopkinton | 2037342 | 1748 | 3000 | PV | 65-H6 | 2014-11-21 | 2015-02-10 | 55 | 0 | 55 | 2014-11-24 | 2015-04-01 | 90 | 0 | 90 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-22 |  | 2016-05-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online | Private
NSTAR | Bellingham | 2037441 | 2019 | 480 | PV | 65-H4 | 2014-11-21 | 2015-02-10 | 55 | 0 | 55 | 2014-11-24 | 2015-03-26 | 86 | 0 | 86 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-22 |  | 2016-05-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private | N
NSTAR | Bellingham | 2037449 | 2019 | 480 | PV | 65-H4 | 2014-11-25 | 2014-12-08 | 8 | 0 | 8 | 2014-12-02 | 2015-02-14 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-04-21 |  | -30311 | 1 | 0 |  |  | 0 | 0 | 0 | 2015-07-31 |  | 2015-07-03 | TBD | COMP | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Rochester | 2037775 | 2770 | 1500 | PV | 3-702-702 | 2014-11-28 | 2014-12-23 | 17 | 0 | 17 | 2014-12-23 | 2014-12-24 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-31 | 2015-07-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Yarmouth | 2038201 | 2664 | 40 | PV | 4-92A-562 | 2014-12-02 | 2014-12-23 | 15 | 0 | 15 | 2014-12-23 | 2015-02-26 | 46 | 35 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-07-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-19 | Online | Private
NSTAR | Wayland | 2038683 | 1778 | 131 | PV | 342-H1 | 2014-12-02 | 2015-01-02 | 22 | 0 | 22 | 2015-01-02 | 2015-12-02 | 238 | 215 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 25 | 0 | 2016-02-09 | 2016-03-11 | 2016-08-15 | No | EXP | 30 | 2016-03-24 |  | -30291 |  | 0 |  |  | 2016-04-14 | Online | Private
NSTAR | Ashland | 2038832 | 1721 | 200 | PV | 274-1429H1 | 2014-12-03 | 2015-01-02 | 21 | 0 | 21 | 2015-01-02 | 2015-12-02 | 238 | 215 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 25 | 0 | 2016-02-09 |  | 2015-07-10 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-21 | Online | Private
NSTAR | Ashland | 2039760 | 1721 | 200 | PV | 274-1429H1 | 2014-12-04 | 2015-01-23 | 35 | 0 | 35 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-29 |  | 2015-07-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-21 | Online | Private
NSTAR | New Bedford | 2041158 | 2746 | 18 | PV | 2-84-133 | 2014-12-04 | 2015-01-13 | 27 | 0 | 27 | 2015-01-13 | 2015-02-21 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2015-02-23 | 2015-06-29 | 90 | 0 | 90 |  |  | 0 | 0 | 0 | 2015-04-29 |  | 2015-07-13 | TBD | STD | 60 |  |  | 0 |  | 0 |  | 2015-12-17 | 2015-12-17 | Online | PRIVATE
NSTAR | East Freetown | 2041172 | 2717 | 1137 | Natural Gas | 2-606-606 | 2014-12-08 | 2015-01-02 | 18 | 0 | 18 | 2015-01-02 | 2015-01-23 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-26 |  | 2015-07-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Cambridge | 2041620 | 2139 | 22.8 | PV | 815-10 | 2014-12-08 | 2015-01-02 | 18 | 0 | 18 | 2015-01-02 | 2015-02-25 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-03 |  | 2015-07-15 | TBD | EXP | 30 | 2015-02-06 | 2015-02-06 | 0 |  | 0 |  |  | 2015-06-12 | Online | Private
NSTAR | Cambridge | 2041623 | 2139 | 22.8 | PV | 814-12 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2015-01-05 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-06 |  | 2015-07-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-05 | Online | Private | N
NSTAR | Dartmouth | 2042098 | 2747 | 17.5 | PV | 2-533-533 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2014-12-22 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 |  | 2015-07-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-02-04 | Online | Private
NSTAR | Sherborn | 2042113 | 1770 | 29 | PV | 240-H1 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2014-12-18 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-15 | 2015-01-14 | 2015-05-22 | No | EXP | 30 | 2015-05-08 | 2015-05-08 | 0 |  | 0 |  |  | 2015-05-29 | Online | Private
NSTAR | Newton | 2042189 | 2466 | 16.4 | PV | 292-H12 | 2014-12-11 | 2014-12-11 | 0 | 0 | 0 | 2014-12-17 | 2015-02-17 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-07-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-04 | Online | Private
NSTAR | Mashpee | 2042191 | 2649 | 11.4 | PV | 4-77A-454 | 2014-12-16 | 2014-12-17 | 1 | 0 | 1 | 2014-12-19 | 2015-03-30 | 70 | 36 | 34 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-16 | 2015-05-27 | 2015-07-23 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Natick | 2043228 | 1760 | 211 | PV | 23-H1 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 | 2014-12-22 | 2015-03-18 | 61 | 27 | 34 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-18 |  | 2015-07-23 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-15 | 2016-01-15 | Online | Private
NSTAR | Framingham | 2043236 | 1701 | 524 | PV | 433-H3 | 2014-12-16 | 2014-12-16 | 0 | 0 | 0 | 2014-12-19 | 2015-03-05 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 | 2015-09-14 | 2016-01-15 | No | EXP | 30 | 2015-10-30 | 2015-10-30 | 0 |  | 0 |  | 2016-02-03 | 2016-01-15 | Online | Private
NSTAR | Bourne | 2043278 | 2532 | 650 | PV | 4-86-402 | 2014-12-17 | 2014-12-17 | 0 | 0 | 0 | 2014-12-17 | 2015-01-05 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-06 | 2015-02-02 | 2015-03-01 | No | EXP | 30 | 2015-03-26 | 2015-03-26 | 0 |  | 0 |  |  | 2015-12-31 | Online | Private
NSTAR | Somerville | 2043499 | 2145 | 50 | PV | 585-114H4 | 2014-12-17 | 2014-12-17 | 0 | 0 | 0 | 2014-12-22 | 2014-12-24 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-12-31 | 2014-12-31 | 2015-07-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-23 | Online | Private
NSTAR | Brewster | 2043623 | 2631 | 132 | PV | 4-89A-553 | 2014-12-22 | 2014-12-24 | 2 | 0 | 2 | 2014-12-29 | 2015-01-06 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-19 | 2015-02-05 | 2015-04-01 | TBD | EXP | 30 | 2015-03-10 | 2015-03-10 | 0 |  | 0 |  |  | 2015-04-07 | Online | Private
NSTAR | Yarmouthport | 2044156 | 2675 | 57 | PV | 4-92A-92A | 2014-12-23 | 2014-12-24 | 1 | 0 | 1 | 2014-12-29 | 2015-01-16 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-30 | 2015-01-29 | 2015-06-19 | No | EXP | 30 | 2015-05-20 | 2015-05-20 | 0 |  | 0 |  |  | 2015-06-17 | Online | Private
NSTAR | Canton | 2044274 | 2021 | 18.9 | PV | 269-1320H1 | 2014-12-26 | 2014-12-26 | 0 | 0 | 0 | 2015-01-01 | 2015-01-08 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-09 |  | 2015-08-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-03-26 | Online | Private
NSTAR | Holliston | 2044550 | 1746 | 15.2 | PV | 65-H2 | 2014-12-26 | 2014-12-26 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Gov't
NSTAR | Boston | 2044564 | 2118 | 2000 | Natural Gas | 4910 | 2014-12-31 | 2014-12-31 | 0 | 0 | 0 | 2015-01-06 | 2015-01-07 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-08 | 2015-01-08 | 2015-08-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-09 | Online | Private | N
NSTAR | Truro | 2045149 | 2652 | 16 | PV | 4-96-674 | 2014-12-31 | 2015-01-02 | 2 | 0 | 2 | 2015-01-02 | 2015-01-09 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-01-12 | 2015-01-12 | 2015-08-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-11 | Online | Private
NSTAR | Dennisport | 2045155 | 2639 | 72 | PV | 4-92B-583 | 2015-01-06 | 2015-01-08 | 2 | 0 | 2 | 2015-01-12 | 2015-01-29 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-25 | Online | Private
NSTAR | Millis | 2048757 | 2054 | 131 | PV | 146-H10 | 2015-01-07 | 2015-01-08 | 1 | 0 | 1 | 2015-01-12 | 2015-03-31 | 56 | 2 | 54 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-14 | 2015-04-14 | 2015-08-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-12-18 | 2015-12-18 | Online | Private
NSTAR | Boston | 2048937 | 2118 | 85 | Natural Gas | 318-10 | 2015-01-08 | 2015-01-08 | 0 | 0 | 0 | 2015-01-13 | 2015-01-29 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-29 | Online | Private
NSTAR | Millis | 2049131 | 2054 | 42 | PV | 146-H10 | 2015-01-09 | 2015-01-12 | 1 | 0 | 1 | 2015-01-15 | 2015-03-26 | 50 | 15 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 | 2015-03-31 | 2015-07-23 | No | EXP | 30 | 2015-06-15 |  | -30088 |  | 0 |  | 2015-09-11 | 2015-09-11 | Online | Private
NSTAR | Millis | 2049284 | 2054 | 300 | PV | 146-H10 | 2015-01-12 | 2015-01-13 | 1 | 0 | 1 | 2015-01-15 | 2015-01-30 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-11 | Online | Private
NSTAR | Millis | 2049734 | 2054 | 75 | PV | 146-H10 | 2015-01-12 | 2015-01-13 | 1 | 0 | 1 | 2015-01-15 | 2015-03-31 | 53 | 40 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-07 | 2015-06-02 | 2015-09-30 | TBD | EXP | 30 | 2015-07-15 | 2015-07-15 | 0 |  | 0 |  | 2015-09-28 | 2015-09-28 | Online | Private
NSTAR | New Bedford | 2049774 | 2745 | 200 | PV | 2-104-104 | 2015-01-13 | 2015-01-13 | 0 | 0 | 0 | 2015-01-21 | 2015-01-26 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-02 |  | 2015-08-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-01 | Online | Private
NSTAR | Dartmouth | 2049963 | 2748 | 17.8 | PV | 2-2-505 | 2015-01-13 | 2015-01-13 | 0 | 0 | 0 | 2015-01-21 | 2015-02-06 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-08-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Sharon | 2049971 | 2067 | 15.8 | PV | 470-H3 | 2015-01-16 | 2015-01-16 | 0 | 0 | 0 | 2015-01-21 | 2015-01-23 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-04 |  | 2015-08-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-07-22 | Withdrawn | Private
NSTAR | Wayland | 2050518 | 1778 | 113 | PV | 433-H6 | 2015-01-16 | 2015-01-19 | 1 | 0 | 1 | 2015-01-21 | 2015-02-09 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 |  | 2015-08-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-03 | Online | Private
NSTAR | Canton | 2050531 | 2021 | 95 | PV | 470-H4 | 2015-01-16 | 2015-01-16 | 0 | 0 | 0 | 2015-01-21 | 2015-01-26 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 | 2015-07-07 | 2015-07-31 | TBD | EXP | 30 | 2015-07-28 | 2015-07-28 | 0 |  | 0 |  |  | 2015-08-18 | Online | Private
NSTAR | Wareham | 2050542 | 2576 | 23.6 | PV | 3-85-928 | 2015-01-20 | 2015-01-20 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study | Private | N
NSTAR | Acusnet | 2051046 | 2743 | 1904 | PV | 2-241-238 | 2015-01-20 | 2015-01-21 | 1 | 0 | 1 | 2015-01-27 | 2015-09-03 | 157 | 152 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-08-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2020-04-29 | Online | Private
NSTAR | Holliston | 2051070 | 1746 | 2000 | PV | 130-H1 | 2015-01-21 | 2015-01-21 | 0 | 64 | 0 | 2015-01-23 | 2016-01-19 | 257 | 66 | 191 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-06 |  | 2016-12-31 | No | COMP | 160 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn | Private
NSTAR | Carver | 2051273 | 2330 | 1500 | PV | 3-10-930 | 2015-01-21 | 2015-01-23 | 2 | 0 | 2 | 2015-01-23 |  | -29987 | 395 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2017-01-25 |  | -30510 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-02 | 2015-05-14 | 2015-08-26 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  | 2017-05-09 | Online | Private |  | 2015-01-27
NSTAR | Acusnet | 2051285 | 2743 | 4000 | PV | 2-241-238 | 2015-01-21 | 2015-01-23 | 2 | 0 | 2 | 2015-01-27 | 2015-02-05 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2015-05-19 |  | -30069 | 0 | 0 |  |  | 0 |  | 0 | 2015-10-02 |  |  |  | STD |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Hopkinton | 2051301 | 1748 | 31 | PV | 65-H2 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-03-09 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-11 | 2015-04-20 | 2015-08-26 | TBD | EXP | 30 | 2015-05-18 | 2015-05-18 | 0 |  | 0 |  |  | 2015-09-04 | Online | Private
NSTAR | Falmouth | 2051319 | 2536 | 56 | PV | 4-76-436 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-06 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-17 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online | Private
NSTAR | Maynard | 2051324 | 1754 | 15.2 | PV | 355-05 | 2015-01-21 | 2015-01-22 | 1 | 0 | 1 | 2015-01-23 | 2015-02-25 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-05 | 2015-09-24 | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dartmouth | 2051325 | 2747 | 360 | PV | 2-532-532 | 2015-01-21 | 2015-01-21 | 0 |  | 0 | 2015-01-27 |  | -29989 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-03 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2051336 | 2571 | 150 | PV | 3-86-966 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-20 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 | 2015-02-24 | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Witness Test Awaiting Cust Response/Doc | Gov't
NSTAR | Cambridge | 2051340 | 2139 | 60 | Natural Gas | 814-12 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-01-30 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-04 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-04-07 | Online | Private
NSTAR | Wareham | 2051382 | 2571 | 56 | PV | 3-86-966 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-06 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-18 | 2015-02-18 | 2015-08-26 | TBD | EXP | 30 | 2015-03-19 | 2015-03-19 | 0 |  | 0 |  |  | 2015-03-27 | Online | Private
NSTAR | Framingham | 2051390 | 1701 | 17.6 | PV | 433-H4 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-20 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Cambridge | 2051393 | 2139 | 60 | Natural Gas | 814-12 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-01-29 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-02 |  | 2015-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-24 | Online | Private
NSTAR | Westport | 2051411 | 2790 | 16.3 | PV | 2-523-523 | 2015-01-21 | 2015-01-21 | 0 | 0 | 0 | 2015-01-27 | 2015-02-10 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-11 |  | 2015-08-26 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private | N
NSTAR | Roxbury | 2051417 | 2119 | 42 | PV | 323-05 | 2015-01-22 | 2015-01-22 | 0 | 0 | 0 | 2015-01-29 | 2015-03-30 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-08-25 | 2015-09-09 | 11 | 0 | 11 | 2015-03-25 | 2015-09-24 | 2016-04-01 | No | COMP | 160 | 2015-11-19 | 2015-11-19 | 0 |  | 0 |  | 2016-05-23 | 2016-09-28 | Online | Private
NSTAR | Wareham | 2051455 | 2538 | 2000 | PV | 3-84-961 | 2015-01-22 | 2015-01-22 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online | Private
NSTAR | Mattapoisett | 2051477 | 2739 | 2250 | PV | 2-304-304 | 2015-01-22 | 2015-01-23 | 1 | 0 | 1 | 2015-02-19 | 2015-03-26 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-08-27 | TBD | COMP | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Mattapoisett | 2051498 | 2739 | 2500 | PV | 2-304-304 | 2015-01-26 | 2015-01-29 | 3 | 0 | 3 | 2015-02-02 | 2015-02-04 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-06 |  | 2015-08-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Assonett | 2051972 | 2702 | 24.1 | PV | 2-605-605 | 2015-01-26 | 2015-01-29 | 3 | 0 | 3 | 2015-02-02 | 2015-02-18 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-25 |  | 2015-08-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-07-24 | Online | Private
NSTAR | Wayland | 2052009 | 1778 | 42 | PV | 433-H6 | 2015-01-28 | 2015-01-28 | 0 | 0 | 0 | 2015-02-02 | 2015-02-18 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-25 |  | 2015-09-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-05-06 | Online | Private
NSTAR | Framingham | 2052167 | 1702 | 15.2 | PV | 455-H3 | 2015-01-29 | 2015-01-29 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | Private | N
NSTAR | Ashland | 2052252 | 1721 | 2413 | PV | 274-H1 | 2015-01-30 | 2015-01-30 | 0 | 0 | 0 | 2015-02-04 | 2015-02-04 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-09 |  | 2015-09-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online | Private
NSTAR | East Freetown | 2052538 | 2717 | 17.4 | PV | 2-102-102 | 2014-11-05 | 2014-11-12 | 4 |  | 4 | 2015-02-03 |  | -29994 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-02-09 | 2015-02-12 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2016-02-12 | Online | Private | N
NSTAR | Lexington | 2052550 | 2421 | 2964 | PV | 533-H2 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-16 | 2016-12-04 | 2015-09-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-15 | Online | Gov't
NSTAR | Arlington | 2053824 | 2476 | 102 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-18 | Online | Gov't
NSTAR | Arlington | 2053835 | 2476 | 176 | PV | 211-H3 | 2015-02-03 | 2015-02-04 | 1 | 0 | 1 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Gov't
NSTAR | Arlington | 2053837 | 2474 | 74 | PV | 59-1383H1 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-03-09 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-11 |  | 2015-09-09 | TBD | EXP | 30 | 2015-03-05 | 2015-03-05 | 0 |  | 0 |  |  | 2015-11-18 | Online | Gov't
NSTAR | Arlington | 2053847 | 2476 | 74 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 | 0 | 0 | 2015-02-13 | 2015-02-20 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-27 |  | 2015-09-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-19 | Online | Gov't
NSTAR | Arlington | 2053868 | 2474 | 102 | PV | 211-H14 | 2015-02-03 | 2015-02-03 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Impact Study Fee/ Agreement | Private
NSTAR | Acusnet | 2053880 | 2743 | 1995 | PV | 2-241-238 | 2015-02-04 | 2017-03-15 | 550 |  | 550 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | impact study | Private
NSTAR | Plymouth | 2053997 | 2360 | 112 | PV | 3-13-936 | 2015-02-05 | 2015-02-05 | 0 | 0 | 0 | 2015-02-10 | 2015-03-26 | 32 | 2 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-02 |  | 2015-09-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2015-07-09 | 2016-03-29 | Online | Private
NSTAR | Framingham | 2054091 | 1701 | 322 | PV | 433-H3 | 2015-02-06 | 2015-02-06 | 0 | 0 | 0 | 2015-02-11 |  | -30000 | 145 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-09-14 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  | 2017-07-23 | Online | Private
NSTAR | Plymouth | 2054256 | 2360 | 1000 | PV | 3-11-11 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-12 | 2015-02-13 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-19 |  | 2015-09-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-10-03 | Online | Private
NSTAR | Lexington | 2054352 | 2421 | 15.9 | PV | 320-H2 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-11 |  | -30000 | 115 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-05 |  | 2015-09-15 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | Private
NSTAR | Plymouth | 2054376 | 2360 | 500 | PV | 3-11-11 | 2015-02-09 | 2015-02-09 | 0 | 0 | 0 | 2015-02-12 | 2015-02-13 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-19 | 2015-02-19 | 2015-09-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | hold - cluster | Private
NSTAR | Harwichport | 2054472 | 2646 | 15.2 | PV | 4-95A-95A | 2015-02-10 | 2015-02-11 | 1 | 0 | 1 | 2015-02-13 | 2015-02-19 | 4 | 47 | -43 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-09-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Ashland | 2054585 | 1721 | 21.2 | PV | 519-175H1 | 2015-02-12 | 2015-02-13 | 1 | 0 | 1 | 2015-02-17 | 2015-03-30 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-31 |  | 2016-04-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dartmouth | 2054857 | 2747 | 800 | PV | 2-533-530 | 2015-02-13 | 2015-02-13 | 0 | 0 | 0 | 2015-02-20 | 2015-02-23 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-26 | 2015-02-25 | 2015-09-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dennis | 2055020 | 2660 | 56 | PV | 4-92B-92B | 2015-02-13 | 2015-02-13 | 0 | 0 | 0 | 2015-02-20 | 2015-02-23 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-02-26 | 2015-02-25 | 2015-09-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-05 | Online | Private
NSTAR | Dennis | 2055023 | 2660 | 70 | PV | 4-92B-92B | 2015-02-18 | 2015-02-19 | 1 | 0 | 1 | 2015-02-23 | 2015-02-24 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-02 |  | 2015-09-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-05 | Online | Gov't
NSTAR | Arlington | 2055516 | 2476 | 56 | PV | 320-H7 | 2015-02-23 | 2015-02-23 | 0 | 0 | 0 | 2015-02-27 | 2015-03-04 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-05 | 2015-03-05 | 2015-09-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online | Private
NSTAR | Dennis | 2055761 | 2660 | 15.2 | PV | 4-92B-572 | 2015-02-23 | 2015-02-23 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-04-15 |  | Construction | Private | N
NSTAR | Weston | 2055868 | 2493 | 1795 | PV | 450-H7 | 2015-02-24 | 2015-03-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-04-15 | Online | Private | Y
NSTAR | Oak Bluffs | 2055949 | 2557 | 2000 | PV | 4-75-75 | 2015-02-24 | 2015-02-25 | 1 | 0 | 1 | 2015-02-27 | 2015-04-27 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-09-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Forestdale | 2055988 | 2644 | 15.8 | PV | 4-81B-443 | 2015-02-25 | 2015-02-25 | 0 | 0 | 0 | 2015-03-02 | 2015-03-05 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 |  | 2015-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-29 | Online | Private
NSTAR | Plymouth | 2056169 | 2360 | 100 | PV | 3-14-911 | 2015-02-26 | 2015-02-26 | 0 | 0 | 0 | 2015-03-04 | 2015-03-10 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-27 |  | 2015-12-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private
NSTAR | East Freetown | 2056337 | 2717 | 52 | PV | 2-102-602 | 2015-02-27 | 2015-02-27 | 0 | 0 | 0 | 2015-03-04 | 2015-03-30 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-13 |  | 2015-10-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-30 | Online | Private
NSTAR | Chelsea | 2056434 | 2150 | 394.4 | PV | 488-H2 | 2015-02-27 | 2015-02-27 | 0 | 62 | 0 | 2015-03-05 | 2015-07-02 | 85 | 0 | 85 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-28 |  | 2016-09-30 | TBD | EXP | 30 | 2016-03-02 |  | -30275 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Chelsea | 2056439 | 2150 | 185.6 | PV | 488-H2 | 2015-02-03 | 2015-02-03 | 0 |  | 0 | 2015-03-21 |  | -30027 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-15 | 2015-04-27 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2056449 | 2770 | 840 | PV | 3-702-702 | 2015-03-03 | 2015-03-03 | 0 | 0 | 0 | 2015-03-06 | 2015-03-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-03-09 |  | 2015-10-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-06 | Online | Private
NSTAR | Rochester | 2056499 | 2770 | 2500 | PV | 3-703-703 | 2015-02-27 | 2015-02-27 | 0 | 62 | 0 | 2015-03-05 | 2015-07-02 | 85 | 0 | 85 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2015-07-28 | 2016-09-12 | 2016-12-16 | TBD | EXP | 30 | 2016-03-02 | 2016-03-02 | 0 |  | 0 |  | 2017-01-13 | 2017-01-13 | Online | Private
NSTAR | Acusnet | 2057145 | 2743 | 18 | PV | 2-241-237 | 2015-03-04 | 2015-03-09 | 3 | 49 | -46 | 2015-06-03 | 2015-07-13 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-07 |  | 2015-10-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | Private
NSTAR | Hopkinton | 2057252 | 1748 | 308 | PV | 126-H2 | 2015-03-21 | 2015-05-06 | 33 | 5 | 28 | 2015-05-12 |  | -30064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-07 | [7 empty] | 0 |  | 0 |  |  | 2017-07-18 | Online | Private
NSTAR | Millis | 2057504 | 2054 | 296 | PV | 65-H3 | 2015-03-10 | 2015-03-10 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2015-03-13
NSTAR | Marion | 2057875 | 2738 | 482 | PV | 2-304-304 | 2015-03-12 | 2015-03-12 | 0 | 0 | 0 | 2015-03-17 | 2015-04-03 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-07 |  | 2015-10-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dartmouth | 2058198 | 2747 | 17 | PV | 2-532-532 | 2015-03-16 | 2015-03-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2015-03-24
NSTAR | Acusnet | 2058670 | 2743 | 1000 | PV | 2-241-241 | 2015-03-17 | 2015-03-17 | 0 | 0 | 0 | 2015-03-24 | 2015-04-10 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-17 | 2019-08-21 | 2015-10-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  |  | Private
NSTAR | Westwood | 2059020 | 2090 | 40 | PV | 456-H1 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-04-14 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-01 | 2016-06-06 | 2015-10-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Wayland | 2059369 | 1778 | 176 | PV | 342-H1 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-05-18 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2015-10-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-30 | Online | Private
NSTAR | Wayland | 2059403 | 1778 | 207 | PV | 342-H3 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-25 | 2015-06-22 | 63 | 25 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-18 | 2016-01-11 | 2016-07-29 | TBD | EXP | 30 | 2016-04-29 |  | -30317 |  | 0 |  |  | 2016-12-30 | Online | Gov't
NSTAR | Wayland | 2059432 | 1778 | 500 | PV | 278-H2 | 2015-03-19 | 2015-03-19 | 0 | 0 | 0 | 2015-03-23 | 2015-05-19 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2015-10-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Wayland | 2059441 | 1778 | 217 | PV | 433-H6 | 2015-03-19 | 2015-03-20 | 1 | 0 | 1 | 2015-07-23 | 2015-07-30 | 5 | 85 | -80 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-22 | 2016-06-30 | 2015-10-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-29 | Online | Private
NSTAR | Natick | 2059455 | 1760 | 240 | PV | 433-H7 | 2015-03-23 | 2015-03-23 | 0 | 0 | 0 | 2015-03-31 | 2015-04-22 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-15 |  | 2015-10-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Woburn | 2059849 | 1801 | 65 | PV | 211-H2 | 2015-03-24 | 2015-03-24 | 0 | 0 | 0 | 2015-03-27 | 2015-06-04 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-14 | 2016-02-05 | 2015-10-28 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private | N
NSTAR | Plymouth | 2059927 | 2360 | 500 | PV | 3-12-12 | 2015-03-24 | 2015-03-24 | 0 | 0 | 0 | 2015-03-27 | 2015-04-21 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 |  | 2015-10-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Westport | 2059968 | 2790 | 21 | PV | 2-523-523 | 2015-03-25 | 2015-03-25 | 0 | 0 | 0 | 2015-04-09 | 2015-05-01 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-08 | 2015-05-08 | 2015-10-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-26 | Online | Private
NSTAR | Medfield | 2060105 | 2052 | 196 | PV | 456-H2 | 2015-03-31 | 2015-04-01 | 1 | 0 | 1 | 2015-04-03 | 2015-09-21 | 121 | 117 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-11-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Natick | 2060976 | 1760 | 500 | PV | 408-1433 | 2015-03-31 | 2015-03-31 | 0 | 0 | 0 | 2015-04-03 | 2015-04-23 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-30 |  | 2015-11-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Holliston | 2061089 | 1746 | 28 | PV | 65-H5 | 2015-03-31 | 2015-04-07 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review | Private
NSTAR | Westport | 2061122 | 2790 | 2000 | PV | 2-532-532 | 2015-04-01 | 2015-04-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-09-27 | Online | Private
NSTAR | Walpole | 2061451 | 2081 | 2280 | PV | 146-H6 | 2015-04-02 | 2015-04-03 | 1 | 0 | 1 |  |  | 0 | 76 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-12 | 2016-02-29 | 2015-11-06 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-06-26 | Online | Private | N
NSTAR | Bellingham | 2061830 | 2019 | 1976 | PV | 65-H4 | 2015-04-03 | 2015-04-17 | 10 | 0 | 10 | 2015-04-20 | 2015-05-04 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-11 | 2015-09-07 | 2015-11-09 | TBD | EXP | 30 | 2015-10-16 | 2015-10-16 | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Falmouth | 2062098 | 2540 | 56 | PV | 4-76-436 | 2015-04-03 | 2015-04-17 | 10 | 0 | 10 | 2015-04-22 | 2015-04-23 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-24 | 2015-04-23 | 2015-11-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-04 | Online | Private
NSTAR | Provincetown | 2062144 | 2657 | 27 | PV | 4-96-675 | 2015-04-06 | 2015-04-13 | 5 | 0 | 5 | 2015-04-16 | 2015-04-23 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-24 |  | 2015-11-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-06-08 | Online | Private
NSTAR | Wareham | 2062402 | 2571 | 17 | PV | 3-84-84 | 2015-04-06 | 2015-04-16 | 8 | 0 | 8 | 2015-04-20 | 2015-04-21 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-22 | 2015-04-22 | 2015-11-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Meter | Private
NSTAR | Edgartown | 2062416 | 2539 | 56 | PV | 4-97-97 | 2015-04-07 | 2015-04-07 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-07-21 | 2016-08-29 | Online | Private | N
NSTAR | Marion | 2062768 | 2738 | 882 | PV | 3-85-85 | 2015-04-08 | 2015-04-22 | 10 | 3 | 7 | 2015-04-24 | 2015-05-01 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-06 |  | 2015-11-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-07-20 | Online | Private
NSTAR | Boston | 2062878 | 2118 | 100 | PV | 2-543-543 | 2015-04-08 | 2015-04-21 | 9 | 0 | 9 | 2015-04-23 | 2015-07-17 | 61 | 59 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-22 |  | 2015-11-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-02-25 | Online | Private
NSTAR | New Bedford | 2062901 | 2745 | 40 | PV | 2-88-18 | 2015-04-09 | 2015-04-15 | 4 | 0 | 4 | 2015-04-16 | 2015-07-07 | 58 | 23 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-08 |  | 2015-11-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Dedham | 2063144 | 2026 | 210 | PV | 469-H4 | 2015-04-09 | 2015-04-16 | 5 | 0 | 5 | 2015-04-20 | 2015-04-22 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 | 2015-04-22 | 2015-11-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Orleans | 2063168 | 2653 | 100 | PV | 4-89B-618 | 2015-04-13 | 2015-04-14 | 1 | 0 | 1 | 2015-04-16 | 2015-04-22 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-04-23 | 2015-04-22 | 2015-11-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-09-15 | Online | Private
NSTAR | Harwichport | 2063694 | 2646 | 40 | PV | 4-85-592 | 2015-04-14 | 2015-04-14 | 0 | 0 | 0 | 2015-04-14 | 2015-05-16 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-22 |  | 2016-06-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | East Boston | 2063933 | 2128 | 499 | PV | 108-196H1 | 2015-04-14 | 2015-04-14 | 0 | 0 | 0 | 2015-04-14 | 2015-07-07 | 60 | 28 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-07 |  | 2016-11-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | East Boston | 2063964 | 2128 | 499 | PV | 108-196H1 | 2015-04-16 | 2015-04-16 | 0 | 0 | 0 | 2015-05-01 | 2015-05-28 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-25 |  | 2015-11-23 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-12-29 | 2017-04-06 | Online | Private | N
NSTAR | Waltham | 2064568 | 2451 | 500 | PV | 363-1369 | 2015-04-17 | 2015-04-17 | 0 | 37 | 0 | 2015-04-24 | 2015-07-01 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-02 |  | 2015-11-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Dartmouth | 2064782 | 2748 | 20 | PV | 2-528-528 | 2015-04-17 | 2015-04-23 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-11-28 | Online | Private
NSTAR | Woburn | 2064809 | 1801 | 2640 | PV | 375-H6 | 2015-04-21 | 2015-04-28 | 5 | 49 | -44 | 2015-05-05 | 2015-07-10 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-12 | 2015-09-15 | 2015-11-25 | No | EXP | 30 | 2015-12-11 | 2015-12-11 | 0 |  | 0 |  | 2015-12-22 | 2017-06-15 | Online | Private
NSTAR | Dartmouth | 2065135 | 2747 | 239.4 | PV | 2-532-532 | 2015-04-21 | 2015-04-22 | 1 | 0 | 1 | 2015-04-24 | 2015-06-15 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-14 | 2015-08-26 | 2015-11-25 | No | EXP | 30 | 2015-09-16 | 2015-09-16 | 0 |  | 0 |  | 2015-12-22 | 2016-02-28 | Online | Private
NSTAR | Dartmouth | 2065189 | 2747 | 360 | PV | 2-532-532 | 2015-04-22 | 2015-07-28 | 69 | 60 | 9 | 2015-08-03 | 2016-08-01 | 260 | 63 | 197 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-07 |  | 2015-11-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Fee | Private | N
NSTAR | Plympton | 2065453 | 2367 | 5000 | PV | 3-51-DSS | 2015-04-23 | 2015-04-24 | 1 | 0 | 1 | 2015-05-04 | 2016-05-24 | 276 | 256 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-11-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Millis | 2065662 | 2054 | 2000 | PV | 65-H1 | 2015-04-24 | 2015-04-29 | 3 | 0 | 3 | 2015-04-30 | 2015-05-11 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-04 |  | 2015-12-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Cambridge | 2065777 | 2140 | 36 | PV | 826-20 | 2015-04-24 | 2015-04-25 | -1 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Centerville | 2065805 | 2632 | 17.4 | PV | 4-82-508 | 2015-04-27 | 2015-05-04 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | Private |  | 2015-07-27
NSTAR | Boston | 2066237 | 2118 | 96 | PV | 528-129H | 2015-04-28 | 2015-04-29 | 1 | 0 | 1 | 2015-04-29 | 2015-06-30 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-21 |  | 2016-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-03-10 |  | Withdrawn | Gov't
NSTAR | Cambridge | 2066481 | 2139 | 568 | PV | 817-05 | 2015-04-28 | 2015-05-05 | 5 | 0 | 5 | 2015-05-07 | 2015-05-27 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-27 |  | 2015-12-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-24 | Withdrawn | Private
NSTAR | Boston | 2066533 | 2118 | 48 | PV | 385-H15 | 2015-04-28 | 2015-05-19 | 15 | 11 | 4 | 2015-05-20 | 2015-06-23 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-24 | 2015-06-24 | 2015-12-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-07-12 | 2016-07-22 | Online | Private
NSTAR | Provincetown | 2066548 | 2657 | 30 | PV | 4-96-676 | 2015-05-05 | 2015-05-13 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review | Private
NSTAR | Bellingham | 2068158 | 2019 | 497 | PV | 65-H4 | 2015-05-06 | 2015-05-07 | 1 | 0 | 1 | 2015-07-01 | 2015-07-07 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-09 | 2016-09-12 |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-12-18 | ISA Received/Signed | Private
NSTAR | Waltham | 2068489 | 2451 | 96 | PV | 450-H8 | 2015-05-07 | 2015-05-11 | 2 | 0 | 2 | 2015-05-14 | 2015-06-22 | 27 | 1 | 26 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-01 |  | 2015-12-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-22 | 2016-01-25 | Online | Private
NSTAR | Woburn | 2068626 | 1801 | 300 | PV | 375-H11 | 2015-05-07 | 2015-05-12 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private | N
NSTAR | Westport | 2068650 | 2790 | 2550 | PV | 2-522-522 | 2015-05-08 | 2015-05-12 | 2 | 0 | 2 | 2015-05-15 | 2015-05-19 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-05 |  | 2015-12-15 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-01 | Online | Private | Y
NSTAR | Lexington | 2068862 | 2420 | 19 | PV | 391-H11 | 2015-05-08 | 2015-05-12 | 2 | 0 | 2 | 2015-05-15 | 2015-05-26 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-05-29 | 2015-05-29 | 2015-12-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-08-05 | Online | Private
NSTAR | Natick | 2068895 | 1760 | 19 | PV | 240-H5 | 2015-05-11 | 2015-05-13 | 2 | 0 | 2 | 2015-05-15 | 2015-05-27 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-01 |  | 2015-12-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-12-14 | Online | Private
NSTAR | Duxbury | 2069125 | 2332 | 16 | PV | 3-23-981 | 2015-05-11 | 2015-05-13 | 2 | 0 | 2 | 2015-05-15 | 2015-07-09 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-06 |  | 2015-12-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  | 2016-01-20 | 2016-01-25 | Online | Private
NSTAR | Lexington | 2069155 | 2421 | 319 | PV | 320-H5XY | 2015-05-15 | 2015-05-16 | -1 | 47 | 0 | 2015-05-18 | 2015-08-11 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2015-12-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-19 | Online | Private
NSTAR | Norfolk | 2070139 | 2056 | 475 | PV | 146-H3 | 2015-05-19 | 2015-05-21 | 2 | 0 | 2 | 2015-05-25 | 2015-08-03 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2015-12-24 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | Private
NSTAR | Woburn | 2070813 | 1801 | 662 | PV | 211-H5 | 2015-05-19 | 2015-05-27 | 6 | 0 | 6 | 2015-05-28 | 2015-06-01 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2015-06-25 | 2015-12-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Watertown | 2070884 | 2472 | 156 | PV | 467-H9 | 2015-05-20 | 2015-05-26 | 4 | 45 | -41 | 2015-05-28 | 2015-07-22 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 |  | 2015-12-28 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Ashland | 2071026 | 1721 | 498 | PV | 519-175H1 | 2015-05-20 | 2015-05-22 | 2 | 0 | 2 | 2015-05-27 | 2015-06-05 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-10 | 2015-07-09 | 2015-12-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online | Private
NSTAR | Ashland | 2071030 | 1721 | 186 | PV | 274-1429H1 | 2015-05-20 | 2015-05-26 | 4 | 0 | 4 | 2015-05-28 | 2015-07-10 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-11 | 2016-02-29 | 2016-12-27 | No | EXP | 30 | 2016-02-23 |  | -30269 | 0 | 0 |  |  | 2017-02-23 | Online | Private
NSTAR | Ashland | 2071039 | 1721 | 728 | PV | 455-H3 | 2015-05-21 | 2015-06-10 | 14 | 0 | 14 | 2015-06-11 | 2015-08-26 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 | 2015-08-26 | 2015-12-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | Private
NSTAR | Hyannis | 2071355 | 2601 | 144 | PV | 4-80B-523 | 2015-05-21 | 2015-06-25 | 25 | 0 | 25 | 2015-07-01 | 2015-08-26 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 | 2015-08-26 | 2015-12-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-12 | Online | Private
NSTAR | Hyannis | 2071356 | 2601 | 120 | PV | 4-84B-524 | 2015-05-26 | 2015-06-02 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | Private | N | 2015-06-23
NSTAR | Wareham | 2071689 | 2576 | 1800 | PV | 3-85-85 | 2015-05-27 | 2015-05-28 | 1 | 0 | 1 | 2015-05-28 | 2015-06-09 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-10 |  | 2016-01-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-01-17 | Online | Private
NSTAR | Natick | 2071934 | 1760 | 148 | PV | 240-H5 | 2015-05-28 | 2015-06-01 | 2 | 0 | 2 | 2015-06-03 | 2015-06-24 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-06-25 |  | 2016-01-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-12 | Online | Private
NSTAR | Plymouth | 2072210 | 2360 | 112 | PV | 3-12-12 | 2015-05-28 | 2015-06-01 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | Private
NSTAR | Framingham | 2072250 | 1702 | 4279 | PV | 274-H4 | 2015-05-29 | 2015-05-30 | -1 | 0 | 0 | 2015-06-05 | 2016-01-27 | 168 | 158 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-23 | 2016-01-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-18 | Online | Private
NSTAR | Woburn | 2072460 | 1801 | 225 | PV | 375-H6 | 2015-06-01 | 2015-06-04 | 3 | 0 | 3 | 2015-06-08 | 2015-07-01 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-29 | 2015-10-23 | 2016-03-17 | TBD | EXP | 30 | 2016-01-15 | 2016-01-15 | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dartmouth | 2072760 | 2748 | 100 | PV | 2-528-528 | 2015-06-01 | 2015-06-05 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Impct Stdy:Awaiting Customers Response/Doc | Private |  | 2016-06-14
NSTAR | Millis | 2072811 | 2054 | 1002 | PV | 65-H3 | 2015-06-02 | 2015-06-03 | 1 | 0 | 1 | 2015-06-05 | 2015-07-06 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-24 | 2015-12-10 | 2016-01-08 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-11-01 | Online | Private
NSTAR | Woburn | 2073317 | 1801 | 100 | PV | 211-H8 | 2015-06-03 | 2016-03-02 | 195 |  | 195 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-03-02 | Online | Private
NSTAR | Arlington | 2073733 | 2474 | 92 | PV | 59-1383H1 | 2015-06-03 | 2015-10-28 | 105 | 87 | 18 | 2015-10-28 | 2015-10-28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 | 2015-11-02 | 2016-01-11 | No | EXP | 30 |  |  | 0 |  | 0 |  | 2015-10-28 | 2015-12-08 | Online | Private | N
NSTAR | Arlington | 2073753 | 2476 | 69 | PV | 351-1385H1 | 2015-06-04 | 2015-06-08 | 2 | 0 | 2 | 2015-06-09 | 2015-07-30 | 37 | 34 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2016-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-26 | Online | Private | N
NSTAR | Lincoln | 2073947 | 1773 | 84 | PV | 320-H8 | 2015-06-04 | 2015-06-08 | 2 | 0 | 2 | 2015-06-10 | 2015-07-17 | 27 | 26 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-30 |  | 2016-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-05-18 | Online | Private | N
NSTAR | Lincoln | 2073959 | 1773 | 112 | PV | 320-H8 | 2015-06-09 | 2015-06-11 | 2 | 0 | 2 | 2015-06-15 | 2015-06-25 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-10 | 2015-12-18 | 2016-01-20 | TBD | EXP | 30 | 2015-12-28 | 2015-12-28 | 0 |  | 0 |  |  | 2016-01-29 | Online | Private
NSTAR | Holliston | 2074665 | 1746 | 20 | PV | 274-H5 | 2015-06-10 | 2015-06-12 | 2 | 0 | 2 | 2015-06-17 | 2015-08-26 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-26 |  | 2016-01-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-02-19 | Online | Private | N
NSTAR | Wianno | 2074867 | 2655 | 44 | PV | 4-80A-892 | 2015-06-19 | 2015-06-25 | 4 | 0 | 4 | 2015-06-24 |  | -30095 | 290 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-01-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2015-06-26
NSTAR | Dartmouth | 2076812 | 2747 | 4500 | PV | 2-532-532 | 2015-06-23 | 2015-06-29 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2015-07-03
NSTAR | Acusnet | 2077489 | 2743 | 1080 | PV | 2-241-241 | 2015-06-25 | 2015-06-30 | 3 | 0 | 3 | 2015-07-02 | 2015-07-30 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-08-21 |  | 2016-02-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  |  | Private
NSTAR | Wareham | 2077939 | 2571 | 200 | PV | 3-84-961 | 2015-06-30 | 2015-07-06 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Rights/Customer Cost | Private
NSTAR | Ashland | 2078781 | 1721 | 183.287 | PV | 274-1429H1 | 2015-07-02 | 2015-07-06 | 2 | 0 | 2 | 2015-07-08 | 2015-07-29 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-17 | 2015-09-30 | 2015-11-06 | No | EXP | 30 | 2015-10-20 | 2015-10-20 | 0 |  | 0 |  |  | 2017-07-07 | Online | Private | N
NSTAR | Walpole | 2079372 | 2081 | 153 | PV | 146-H3 | 2015-07-02 | 2015-07-09 | 5 | 0 | 5 | 2015-07-10 | 2015-07-13 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-07-16 |  | 2016-02-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-13 | Online | Private
NSTAR | Assonett | 2079393 | 2702 | 20 | PV | 2-605-605 | 2015-07-09 | 2015-07-16 | 5 | 0 | 5 | 2015-07-20 | 2015-08-06 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-14 | 2016-02-12 | 2016-06-30 | No | EXP | 30 | 2016-08-10 |  | -30390 |  | 0 |  |  |  | Construction | Private
NSTAR | Woburn | 2080949 | 1801 | 696 | PV | 375-H4 | 2015-07-16 | 2015-07-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private | N
NSTAR | Bellingham | 2082060 | 2019 | 990 | PV | 65-H4 | 2015-07-17 | 2015-07-20 | 1 | 0 | 1 | 2015-07-23 | 2015-08-25 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-28 |  | 2016-02-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Plymouth | 2082435 | 2360 | 79 | PV | 3-12-12 | 2015-07-17 | 2015-07-21 | 2 | 0 | 2 | 2015-07-23 | 2016-02-10 | 144 | 50 | 94 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-01 | 2016-05-25 | 2016-10-14 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-08 | Online | Private
NSTAR | Plympton | 2082491 | 2367 | 990 | PV | 3-51-901 | 2015-07-17 | 2015-07-21 | 2 | 0 | 2 | 2015-07-23 | 2015-08-06 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-19 | 2016-02-10 | 2016-02-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-09 | Online | Private
NSTAR | Woburn | 2082549 | 1801 | 495 | PV | 375-H3 | 2015-07-21 | 2015-07-22 | 1 | 0 | 1 | 2015-07-24 | 2015-09-04 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-29 | 2016-05-30 | 2016-02-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2019-03-29 | Online | Private
NSTAR | Woburn | 2083212 | 1801 | 263 | PV | 325-03 | 2015-07-21 | 2015-07-22 | 1 | 3 | -2 | 2015-07-24 | 2015-09-02 | 28 | 194 | -166 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-16 | 2016-01-06 | 2016-02-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-28 | Online | Gov't | Y
NSTAR | Woburn | 2083239 | 1801 | 454 | PV | 211-H5 | 2015-07-22 | 2015-07-23 | 1 | 0 | 1 | 2015-07-27 | 2015-09-05 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-25 |  | 2016-03-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | Private
NSTAR | Woburn | 2083306 | 1801 | 265 | PV | 211-H10 | 2015-07-22 | 2015-07-23 | 1 | 0 | 1 | 2015-07-27 | 2015-08-12 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 |  | 2016-03-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Jamaica Plain | 2083371 | 2130 | 28 | PV | 496-H4 | 2015-07-23 | 2015-07-24 | 1 | 0 | 1 | 2015-07-28 | 2015-08-07 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-18 | 2016-03-15 | 2016-08-25 | TBD | EXP | 30 | 2016-08-04 | 2016-08-04 | 0 |  | 0 |  |  |  | Online | Private
NSTAR | Rochester | 2083435 | 2770 | 20.52 | PV | 3-702-702 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2083555 | 2739 | 60 | PV | 2-304-304 | 2015-07-27 | 2015-07-29 | 2 | 0 | 2 | 2015-07-30 | 2015-07-30 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-04 |  | 2016-03-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-05-05 | Online | Private
NSTAR | Somerville | 2084293 | 2145 | 54 | PV | 250-1N81H1 | 2015-07-27 | 2015-07-28 | 1 | 0 | 1 | 2015-07-31 | 2015-08-19 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-19 |  | 2016-03-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-11-10 | Online | Private
NSTAR | Roxbury | 2084347 | 2119 | 27 | PV | 323-05 | 2015-07-27 | 2015-07-31 | 4 | 0 | 4 | 2015-08-04 | 2015-08-11 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-20 | 2015-08-19 | 2016-03-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-10-20 | Online | Private
NSTAR | Needham | 2084378 | 2494 | 40 | PV | 148-H7 | 2015-07-28 | 2015-08-05 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2015-08-13
NSTAR | Acton | 2084724 | 1720 | 2000 | PV | 416-H2 | 2015-07-29 | 2015-08-03 | 3 | 0 | 3 | 2015-08-05 | 2016-01-20 | 120 | 108 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-04-22 | No | EXP | 30 | 2016-05-11 |  | -30325 |  | 0 |  | 2016-06-08 |  | Withdrawn | Private | N
NSTAR | Natick | 2085006 | 1760 | 492 | PV | 433-H9 | 2015-07-30 | 2015-08-01 | 1 | 0 | 1 | 2015-08-04 | 2015-09-30 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-05-19 | Online | Private
NSTAR | Woburn | 2085086 | 1801 | 336 | PV | 258-1394H2 | 2015-07-30 | 2015-08-01 | 1 | 0 | 1 | 2015-08-04 | 2015-09-30 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-09 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Woburn | 2085091 | 1801 | 377 | PV | 258-1394H2 | 2015-07-30 | 2015-08-04 | 3 | 0 | 3 | 2015-08-06 | 2016-01-26 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-26 |  | 2017-02-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Woburn | 2085252 | 1801 | 624 | PV | 375-H12 | 2015-07-31 | 2015-08-01 | -1 | 0 | 0 | 2015-08-07 | 2016-03-23 | 163 | 142 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Westport | 2085492 | 2790 | 2000 | PV | 2-524-524 | 2015-07-31 | 2015-08-04 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Gov't |  | 2015-08-17
NSTAR | Dorchester | 2085514 | 2125 | 4600 | Natural Gas | 511-1497H | 2015-08-04 | 2015-08-07 | 3 | 0 | 3 | 2015-08-11 | 2015-09-15 | 25 | 13 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | East Freetown | 2086294 | 2717 | 1440 | PV | 2-102-604 | 2015-08-06 | 2015-08-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2015-09-28
NSTAR | Wareham | 2086312 | 2576 | 1440 | PV | 3-85-928 | 2015-08-05 | 2015-08-07 | 2 | 0 | 2 | 2015-08-11 | 2015-09-15 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Assonett | 2086459 | 2702 | 1440 | PV | 2-605-605 | 2013-11-25 | 2013-12-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  | 2016-04-20 |  | Withdrawn
NSTAR | Acusnet | 2086742 | 2743 | 1990 | PV | 2-241-241 | 2015-08-07 | 2015-08-17 | 6 | 0 | 6 | 2015-09-28 |  | -30163 | 81 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-08-21 |  | 2016-03-17 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2016-04-27
NSTAR | Acusnet | 2086776 | 2743 | 1000 | PV | 2-241-241 | 2015-08-11 | 2015-08-18 | 5 | 0 | 5 | 2015-08-20 | 2016-01-13 | 104 | 0 | 104 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 | 2019-08-21 | 2016-03-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval | Private | N
NSTAR | Woburn | 2087191 | 1801 | 29 | PV | 211-H2 | 2015-08-11 | 2015-08-18 | 5 | 0 | 5 | 2015-08-18 | 2015-10-09 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 | 2017-01-05 | 2016-03-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-06 | Online | PRIVATE | N
NSTAR | Cambridge | 2087199 | 2138 | 171.1 | PV | 828-1105 | 2015-08-11 | 2015-08-18 | 5 | 0 | 5 | 2015-08-20 | 2015-08-24 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-27 | 2015-08-26 | 2016-03-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-26 | Online | Private
NSTAR | Brewster | 2087387 | 2631 | 111 | PV | 4-95A-597 | 2015-08-14 | 2015-08-15 | -1 | 0 | 0 | 2015-08-21 | 2015-12-15 | 82 | 53 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-03-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Acusnet | 2088074 | 2743 | 4000 | PV | 2-241-238 | 2015-08-19 | 2015-08-20 | 1 | 0 | 1 | 2015-08-25 | 2015-09-17 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 |  | 2016-03-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Roxbury | 2088902 | 2120 | 75 | Natural Gas | 106-H8 | 2015-08-19 | 2015-08-20 | 1 | 0 | 1 | 2015-08-25 | 2015-09-20 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-17 | 2015-10-09 | 2016-03-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-20 | Online | Private
NSTAR | Boston | 2088913 | 2118 | 75 | Natural Gas | 106-H4 | 2015-08-19 | 2015-08-21 | 2 | 0 | 2 | 2015-08-25 | 2015-12-15 | 80 | 72 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-21 | 2015-10-09 | 2016-03-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-20 | Online | Private
NSTAR | Waltham | 2088991 | 2451 | 175 | PV | 282-H6 | 2015-08-20 | 2015-08-21 | 1 | 98 | -97 | 2015-08-25 | 2016-04-05 | 160 | 0 | 160 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-15 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-03-17 | Online | Private
NSTAR | Boston | 2089121 | 2115 | 128 | PV | 492-1N14S | 2015-08-20 | 2015-08-20 | 0 | 0 | 0 | 2015-08-20 | 2015-08-25 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-10 |  | 2016-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2015-12-14 | Online | Private
NSTAR | Waltham | 2089144 | 2451 | 96 | PV | 450-H8 | 2015-08-21 | 2015-08-24 | 1 | 0 | 1 | 2015-08-26 | 2015-09-22 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-23 |  | 2016-03-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-01-05 | Online | Private
NSTAR | Mashpee | 2089388 | 2649 | 90 | PV | 4-88-455 | 2015-08-24 | 2015-08-26 | 2 | 0 | 2 | 2015-08-28 | 2015-10-26 | 41 | 11 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-04 |  | 2016-04-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | Private
NSTAR | Dover | 2089416 | 2030 | 27.75 | PV | 456-H3 | 2015-07-31 | 2015-08-11 | 7 |  | 7 | 2015-08-24 |  | -30138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-14 | 2016-06-15 | [6 empty] | 0 |  | 0 |  |  | 2016-09-15 | Online
NSTAR | East Freetown | 2089453 | 2717 | 22.8 | PV | 2-102-102 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2089685 | 1741 | 216 | PV | 512-1399H1 | 2015-08-24 | 2015-08-27 | 3 | 0 | 3 | 2015-08-31 | 2015-09-23 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-09-24 |  | 2016-04-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Roxbury | 2089776 | 2119 | 33 | PV | 106-H5 | 2015-08-26 | 2015-08-27 | 1 | 44 | -43 | 2015-08-31 | 2015-12-21 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Arlington | 2090065 | 2476 | 118 | PV | 320-H7 | 2015-08-26 | 2015-08-27 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Plymouth | 2090094 | 2360 | 4999 | PV | 3-012-012 | 2015-08-26 | 2015-08-28 | 2 | 0 | 2 | 2015-08-31 | 2015-10-14 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-03 |  | 2016-11-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | New Bedford | 2090242 | 2744 | 843 | PV | 2-7-95 | 2015-08-26 | 2015-08-28 | 2 | 0 | 2 | 2015-09-02 | 2015-10-27 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-04-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-04 | Online | Private
NSTAR | Rochester | 2090360 | 2770 | 1000 | PV | 3-702-702 | 2015-08-27 | 2015-08-28 | 1 | 0 | 1 | 2015-08-31 | 2015-11-23 | 60 | 53 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-22 |  | 2016-04-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-12-14 | Customer Cost | Private
NSTAR | Chatham | 2090556 | 2650 | 296 | PV | 4-95A-608 | 2015-08-28 | 2015-09-01 | 2 | 0 | 2 | 2015-09-02 |  | -30145 | 241 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-07 | TBD | TBD | 160 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Gov't |  | 2015-09-03
NSTAR | Acton | 2090728 | 1720 | 420 | PV | 416-H4 | 2015-08-14 | 2015-09-01 | 12 | 0 | 12 | 2015-09-01 | 2015-09-01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-04-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | ISA sent | Private
NSTAR | Dartmouth | 2090751 | 2748 | 18 | PV | 2-524-524 | 2015-09-01 | 2015-09-02 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | Private | N
NSTAR | Sandwich | 2091380 | 2563 | 1476 | PV | 4-81A-439 | 2015-09-02 | 2015-09-03 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-08 | Online | Private |  | 2015-09-28
NSTAR | Acusnet | 2092115 | 2743 | 2000 | PV | 2-241-238 | 2015-09-02 | 2015-09-03 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-29 | [7 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2015-09-28
NSTAR | Acusnet | 2092123 | 2743 | 2000 | PV | 2-241-238 | 2015-09-03 | 2015-09-04 | 1 | 0 | 1 | 2015-09-11 | 2015-11-09 | 41 | 29 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-09-29 |  |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Rochester | 2092354 | 2770 | 2000 | PV | 3-702-702 | 2015-09-03 | 2015-09-04 | 1 | 0 | 1 | 2015-09-11 | 2016-04-06 | 148 | 130 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Rochester | 2092534 | 2770 | 1000 | PV | 3-702-702 | 2015-09-08 | 2015-09-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-06-17
NSTAR | Wareham | 2092960 | 2571 | 5500 | PV | 3-82-82 | 2015-09-08 | 2015-09-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-01-11 | Online | Private |  | 2016-04-25
NSTAR | Wareham | 2093002 | 2571 | 4000 | PV | 3-83-83 | 2015-09-08 | 2015-09-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Canton | 2093030 | 2021 | 990 | PV | 470-H7 | 2015-09-09 | 2015-09-10 | 1 | 0 | 1 | 2015-09-14 | 2015-10-13 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-17 | 2016-03-09 | 2016-05-27 | No | EXP | 30 | 2016-02-24 |  | -30270 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Holliston | 2093131 | 1746 | 990 | PV | 65-H2 | 2015-09-09 | 2015-09-10 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-09 | Online | Private
NSTAR | Fairhaven | 2093189 | 2719 | 2000 | PV | 2-221-221 | 2015-09-09 | 2015-09-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-05 | Online | Private
NSTAR | Carver | 2093250 | 2330 | 990 | PV | 3-10-929 | 2015-09-09 | 2015-09-10 | 1 | 0 | 1 | 2015-09-14 | 2016-03-19 | 134 | 37 | 97 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-04 |  | 2016-04-19 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2019-01-23 | Online | Private
NSTAR | Somerville | 2093280 | 2145 | 999 | PV | 250-H3 | 2015-09-10 | 2015-09-11 | 1 | 0 | 1 | 2015-09-10 |  | -30151 |  | 0 |  |  | 0 | 0 | 0 | 2015-09-15 | 2015-10-16 | 23 | 2 | 21 | 2016-02-19 |  | -30267 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-04 | 2016-02-04 | [6 empty] | 0 |  | 0 |  |  | 2017-05-02 | Online | Private | N
NSTAR | Acton | 2093456 | 1720 | 750 | PV | 416-H1 | 2015-09-10 | 2015-09-14 | 2 | 0 | 2 | 2015-09-15 | 2016-01-26 | 95 | 54 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-08 |  | 2016-07-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | New Bedford | 2093470 | 2746 | 990 | PV | 2-38-38 | 2015-09-10 | 2015-09-11 | 1 | 0 | 1 | 2015-09-15 | 2015-10-14 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-28 | 2017-05-17 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Milton | 2093526 | 2186 | 512 | PV | 496-H1XY | 2015-09-11 | 2015-09-15 | 2 | 0 | 2 | 2015-09-18 | 2015-10-26 | 26 | 205 | -179 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-04-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2015-10-27
NSTAR | Waltham | 2093779 | 2451 | 1000 | PV | 450-H3 | 2015-09-14 | 2015-09-15 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Acton | 2093910 | 1720 | 1940 | PV | 416-H1 | 2015-09-14 | 2015-09-15 | 1 | 0 | 1 | 2015-09-18 | 2015-10-08 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-04 |  | 2016-04-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Falmouth | 2093955 | 2540 | 19 | PV | 4-76-436 | 2015-09-14 | 2015-09-15 | 1 | 0 | 1 | 2015-09-16 | 2015-09-28 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-20 | 2015-10-30 | 2016-01-20 | TBD | EXP | 30 | 2016-01-04 | 2016-01-04 | 0 |  | 0 |  | 2016-01-26 |  | Withdrawn | Private
NSTAR | Dennis | 2094068 | 2660 | 300 | PV | 4-92B-92B | 2015-09-14 | 2015-09-15 | 1 | 0 | 1 | 2015-09-18 | 2015-10-26 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-09 | 2016-06-06 | 2016-11-18 | No | EXP | 30 | 2016-06-06 |  | -30343 |  | 0 |  | 2016-06-06 | 2016-01-26 | Online | Private
NSTAR | Lexington | 2094085 | 2421 | 815 | PV | 320-H2 | 2015-08-20 | 2015-08-26 | 4 |  | 4 | 2015-09-15 |  | -30154 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-11-17 | 2015-11-18 | [6 empty] | 0 |  | 0 |  |  | 2016-06-08 | Online
NSTAR | Waltham | 2094179 | 2451 | 1200 | Natural Gas | 373-1358 | 2015-09-16 | 2015-09-22 | 4 | 0 | 4 | 2015-09-24 | 2015-09-28 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-27 | 2016-02-25 | 2016-03-30 | TBD | EXP | 30 | 2016-02-25 | 2016-02-25 | 0 |  | 0 |  |  | 2016-04-14 | Online | Private
NSTAR | Harwich | 2094563 | 2671 | 72 | PV | 4-85-592 | 2015-09-16 | 2015-09-17 | 1 | 0 | 1 | 2015-09-22 | 2015-10-15 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-15 |  | 2016-04-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Somerville | 2094631 | 2145 | 24 | PV | 250-H4XY | 2015-09-16 | 2015-09-22 | 4 | 0 | 4 | 2015-09-24 | 2015-10-01 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-14 |  | 2016-04-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-30 | Online | Private
NSTAR | Natick | 2094705 | 1760 | 75 | PV | 433-H11 | 2015-09-16 | 2015-09-21 | 3 | 0 | 3 | 2015-09-23 | 2015-10-07 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-06 |  | 2016-04-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-25 | Online | Private
NSTAR | Burlington | 2094742 | 1803 | 100 | PV | 211-H13 | 2015-09-17 | 2015-09-21 | 2 | 0 | 2 | 2015-09-23 | 2016-01-19 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-09 | 2016-04-07 | 2016-06-24 | No | EXP | 30 | 2016-05-18 |  | -30330 |  | 0 |  | 2015-10-14 |  | Awaiting Completion Docs | Private | N
NSTAR | Monument Beach | 2094911 | 2553 | 496 | PV | 4-86-408 | 2015-09-22 | 2015-09-23 | 1 | 0 | 1 | 2015-09-23 | 2016-04-12 | 144 | 0 | 144 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-09 | 2016-02-09 | 2016-05-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-30 | Online | Private
NSTAR | Mashpee | 2095832 | 2649 | 264 | PV | 4-88-455 | 2015-09-22 | 2015-09-23 | 1 | 0 | 1 | 2015-09-28 | 2015-10-16 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-16 | 2015-12-02 | 2016-01-29 | TBD | EXP | 30 | 2015-12-30 | 2015-12-30 | 0 |  | 0 |  |  |  |  | Private
NSTAR | Brookline | 2095914 | 2467 | 32 | PV | 496-H4 | 2015-09-24 | 2015-09-25 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review Desn1 Stage | Private
NSTAR | Woburn | 2096036 | 1801 | 499.8 | PV | 375-H12 | 2015-09-04 | 2015-09-09 | 3 |  | 3 | 2015-09-24 |  | -30161 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-11-25 | 2015-11-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-10 | Online | PRIVATE
NSTAR | Plymouth | 2096227 | 2360 | 4000 | PV | 3-88-924 | 2015-09-25 | 2015-09-26 | -1 | 0 | 0 | 2015-09-30 | 2016-04-28 | 151 | 130 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Holliston | 2096409 | 1746 | 476 | PV | 274-H1 | 2015-09-25 | 2015-09-28 | 1 | 0 | 1 | 2015-09-30 | 2015-11-20 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-14 | 2016-01-21 | 2016-06-30 | No | EXP | 30 | 2016-04-07 | 2016-04-07 | 0 |  | 0 |  | 2016-06-24 |  | Withdrawn | Private
NSTAR | Mashpee | 2096431 | 2649 | 371 | PV | 4-77A-454 | 2015-09-25 | 2015-09-28 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review | Private
NSTAR | Bellingham | 2096445 | 2019 | 984 | PV | 65-H4 | 2015-09-28 | 2015-09-30 | 2 | 2 | 0 | 2015-10-06 | 2015-10-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-12 | 2016-10-11 | 2016-05-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Hopkinton | 2096675 | 1748 | 170 | PV | 126-H1 | 2015-09-28 | 2015-09-30 | 2 | 0 | 2 | 2015-10-05 | 2015-10-05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-05 |  | 2016-05-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-29 | Online | Private
NSTAR | New Bedford | 2096734 | 2746 | 157 | PV | 2-87-135 | 2015-10-01 | 2015-10-02 | 1 | 8 | -7 | 2015-10-16 | 2015-11-02 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-05 | 2016-10-09 |  | No | EXP | 30 |  |  | 0 |  | 0 |  | 2016-03-10 | 2016-04-29 | Online | Private | Y
NSTAR | Natick | 2097431 | 1760 | 207 | PV | 433-H7 | 2015-10-01 | 2015-10-02 | 1 | 0 | 1 | 2015-10-05 | 2015-10-27 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 |  | 2016-05-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Westport | 2097455 | 2790 | 32.85 | PV | 2-523-523 | 2015-09-22 | 2015-09-24 | 2 |  | 2 | 2015-10-02 |  | -30167 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-10-29 | 2015-11-30 | [6 empty] | 0 |  | 0 |  |  | 2016-09-09 | Online | Private | Y
NSTAR | New Bedford | 2097474 | 2746 | 360 | PV | 2-134-134 | 2015-10-02 | 2015-10-05 | 1 | 0 | 1 | 2015-10-07 | 2015-10-29 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 | 2015-10-30 | 2016-05-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-03 | Online | Private
NSTAR | Somerville | 2097809 | 2144 | 20 | PV | 227-51H2 | 2015-10-05 | 2015-10-06 | 1 | 0 | 1 | 2015-10-12 | 2016-03-17 | 113 | 0 | 113 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-13 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Bourne | 2098326 | 2532 | 4800 | Natural Gas | 4-81A-81A | 2015-10-05 | 2015-10-09 | 4 | 0 | 4 | 2015-10-14 | 2015-10-20 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-27 | 2015-11-11 | 2016-06-15 | TBD | EXP | 30 | 2016-05-18 | 2016-05-18 | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Mattapoisett | 2098384 | 2739 | 25 | WIND | 2-301-301 | 2015-10-05 | 2015-10-09 | 4 | 73 | -69 | 2015-10-14 | 2016-06-14 | 174 | 0 | 174 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-26 |  | 2016-05-13 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private
NSTAR | Woburn | 2098750 | 1801 | 252 | PV | 211-H5 | 2015-10-06 | 2015-10-08 | 2 | 0 | 2 | 2015-10-12 | 2016-02-18 | 93 | 18 | 75 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-06 | 2016-05-13 | 2016-11-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-12 | Online | Private
NSTAR | Dedham | 2099070 | 2026 | 765 | PV | 20-H2 | 2015-10-07 | 2015-10-08 | 1 | 0 | 1 | 2015-10-14 | 2016-05-02 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-04 | Online | Private
NSTAR | Plymouth | 2099348 | 2360 | 420 | PV | 3-12-12 | 2015-10-08 | 2015-10-09 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Plympton | 2099482 | 2367 | 880 | PV | 3-51-901 | 2015-10-08 | 2015-10-21 | 9 | 0 | 9 | 2015-10-27 | 2015-11-17 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-01 |  | 2016-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Sudbury | 2099532 | 1776 | 42 | PV | 342-H2 | 2015-10-08 | 2015-10-13 | 3 | 0 | 3 | 2015-10-14 | 2015-11-16 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 |  | 2016-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Woburn | 2099592 | 1801 | 84 | PV | 211-01 | 2015-10-08 | 2015-10-13 | 3 | 0 | 3 | 2015-10-14 | 2016-01-25 | 73 | 57 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-14 |  | 2016-05-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Burlington | 2099699 | 1803 | 360 | PV | 391-H15 | 2015-10-08 | 2015-10-14 | 4 | 1 | 3 | 2015-10-16 | 2016-08-01 | 206 | 0 | 206 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-18 |  | 2016-05-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Plymouth | 2099704 | 2360 | 996 | PV | 31313 | 2015-10-13 | 2015-10-14 | 1 | 14 | -13 | 2015-10-16 | 2016-02-19 | 90 | 0 | 90 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-05-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-09-06 | Online | Private
NSTAR | Woburn | 2100110 | 1801 | 360 | PV | 258-1394H2 | 2015-10-13 | 2015-10-14 | 1 | 14 | -13 | 2015-10-16 | 2016-02-12 | 85 | 0 | 85 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-05-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Woburn | 2100120 | 1801 | 480 | PV | 258-1394H2 | 2015-10-14 | 2015-10-15 | 1 | 0 | 1 | 2015-10-19 | 2016-01-08 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-13 |  | 2016-05-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Woburn | 2100528 | 1801 | 40 | PV | 258-1394H4 | 2015-10-16 | 2015-10-19 | 1 | 0 | 1 | 2015-10-21 | 2016-01-25 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-22 |  | 2016-05-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private
NSTAR | Bourne | 2101008 | 2532 | 468 | PV | 4-86-402 | 2015-10-16 | 2015-10-19 | 1 | 0 | 1 | 2015-10-20 | 2015-10-20 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-20 |  | 2016-05-25 | TBD | EXP | 30 |  |  | 0 |  | 0 | 2017-04-03 |  | 2017-04-11 | Online | Private
NSTAR | Westport | 2101010 | 2790 | 19 | PV | 2-523-523 | 2015-10-16 | 2015-10-19 | 1 | 0 | 1 | 2015-10-21 | 2015-11-23 | 23 | 9 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-11 | 2016-01-11 | 2016-04-15 | No | EXP | 30 | 2016-03-11 |  | -30282 |  | 0 |  |  | 2016-12-07 | Online | Private | N
NSTAR | Waltham | 2101013 | 2453 | 126 | PV | 467-H8 | 2015-10-20 | 2015-10-21 | 1 | 0 | 1 | 2015-10-27 | 2016-03-31 | 112 | 102 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-05-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-16 | Online | PRIVATE
NSTAR | Medway | 2101737 | 2053 | 504 | PV | 65-H2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lincoln | 2102041 | 1773 | 20 | PV | 320-H1 | 2015-10-21 | 2015-10-22 | 1 | 0 | 1 | 2015-10-23 | 2015-10-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-10-28 |  | 2016-05-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Dartmouth | 2102045 | 2747 | 98 | PV | 2-543-543 | 2015-10-23 | 2015-10-24 | -1 | 0 | 0 | 2015-11-03 | 2016-06-27 | 169 | 157 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Acton | 2102432 | 1720 | 830 | PV | 416-H1 | 2015-10-23 | 2015-11-04 | 8 | 0 | 8 | 2015-10-27 | 2016-08-01 | 199 | 26 | 173 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-19 |  | 2016-06-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting App Fee and/or Further Info | Private
NSTAR | Wareham | 2102456 | 2576 | 600 | PV | 3-85-85 | 2015-10-23 | 2015-11-04 | 8 | 0 | 8 | 2015-10-28 | 2016-01-29 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-29 | 2016-03-08 | 2017-01-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-16 | Online
NSTAR | New Bedford | 2102526 | 2745 | 928 | PV | 2-88-88 | 2015-10-23 | 2015-10-26 | 1 | 0 | 1 | 2015-10-28 | 2016-02-10 | 75 | 57 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-06-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Chatham | 2102528 | 2650 | 88 | PV | 4-95A-608 | 2015-10-23 | 2015-10-24 | -1 | 0 | 0 | 2015-10-27 | 2016-04-19 | 125 | 112 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Assonett | 2102530 | 2702 | 1992 | PV | 2-605-605 | 2015-10-23 | 2015-10-24 | -1 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Falmouth | 2102531 | 2536 | 48 | PV | 4-98A-98A | 2015-10-26 | 2015-10-29 | 3 | 0 | 3 | 2015-10-29 | 2016-02-12 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-06-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-07-14 | Online | Private
NSTAR | Pocasset | 2102746 | 2559 | 27 | PV | 4-81A-81A | 2015-10-27 | 2015-10-29 | 2 | 0 | 2 | 2015-11-02 | 2015-12-29 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-15 | 2016-02-10 | 2016-07-15 | TBD | EXP | 30 | 2016-06-09 | 2016-06-09 | 0 |  | 0 |  |  | 2016-07-22 | Online | Private
NSTAR | Canton | 2102821 | 2021 | 324.6 | PV | 470-H8 | 2015-10-09 | 2016-10-16 | 265 |  | 265 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-25 | 2016-05-20 | [6 empty] | 0 |  | 0 |  |  | 2017-03-20 | Online | PRIVATE
NSTAR | Jamaica Plain | 2103067 | 2130 | 17 | PV | 554-79H1 | 2015-10-28 | 2015-10-29 | 1 | 0 | 1 | 2015-11-04 | 2016-04-13 | 115 | 0 | 115 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Gov't
NSTAR | Plymouth | 2103303 | 2360 | 5976 | PV | 3-73-73 | 2015-10-28 | 2015-10-29 | 1 | 0 | 1 | 2015-11-04 | 2016-04-05 | 109 | 15 | 94 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Assonett | 2103346 | 2702 | 984 | PV | 2-605-605 | 2015-10-29 | 2015-11-04 | 4 | 0 | 4 | 2015-11-03 |  | -30189 | 199 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-08 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2015-11-04
NSTAR | West Tisbury | 2103349 | 2575 | 233.1 | PV | 4-97-220 | 2015-10-15 | 2015-10-23 | 6 |  | 6 | 2015-10-29 |  | -30186 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-12-07 | [7 empty] | 0 |  | 0 | 2017-03-23 | 2017-03-23 | 2017-04-10 | Online | PRIVATE
NSTAR | Rochester | 2103573 | 2770 | 2000 | PV | 3-703-703 | 2015-10-29 | 2015-11-04 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2015-11-04
NSTAR | Rochester | 2103577 | 2770 | 3000 | PV | 3-702-702 | 2015-11-03 | 2015-11-03 | 0 | 0 | 0 | 2015-11-09 | 2015-11-17 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-31 |  | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Natick | 2104785 | 1760 | 36 | PV | 433-H11 | 2015-11-03 | 2015-11-04 | 1 | 0 | 1 | 2015-11-09 | 2015-11-18 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 | 2015-11-18 | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-25 | Online | Private
NSTAR | Provincetown | 2104938 | 2657 | 168 | PV | 4-96-674 | 2015-11-03 | 2015-11-04 | 1 | 0 | 1 | 2015-11-09 | 2016-04-18 | 115 | 46 | 69 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-29 |  | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review Desn1 Stage | Private
NSTAR | Somerville | 2104944 | 2143 | 996 | PV | 387-148H2 | 2015-11-03 | 2015-11-04 | 1 | 0 | 1 | 2015-11-09 | 2015-11-18 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-11-20 | 2015-11-18 | 2016-06-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  |  | Private
NSTAR | Provincetown | 2104946 | 2657 | 124 | PV | 4-96-674 | 2015-11-05 | 2015-11-06 | 1 | 0 | 1 | 2015-11-11 | 2015-12-07 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-08 | 2015-12-07 | 2016-06-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-21 | Online | Private
NSTAR | Hyannis | 2105424 | 2601 | 96 | PV | 4-84A-520 | 2015-11-05 | 2015-11-06 | 1 | 0 | 1 | 2015-11-11 | 2015-11-27 | 12 | 5 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-04 | 2016-02-12 | 2016-03-31 | TBD | EXP | 30 | 2016-03-31 | 2016-03-31 | 0 |  | 0 |  |  | 2016-04-26 | Online | Private
NSTAR | Provincetown | 2105431 | 2657 | 100 | PV | 4-96-676 | 2015-11-05 | 2015-11-06 | 1 | 0 | 1 | 2015-11-11 | 2016-02-18 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-14 |  | 2016-06-15 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | Private
NSTAR | Canton | 2105434 | 2021 | 630 | PV | 269-1320H1 | 2015-11-05 | 2015-11-09 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Engineering Screen Review | Private
NSTAR | South Boston | 2105436 | 2210 | 2280 | PV | 106-H1 | 2015-11-10 | 2015-11-11 | 1 | 0 | 1 | 2015-11-18 | 2016-04-19 | 109 | 24 | 85 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-09 | Online | Private
NSTAR | Assonett | 2106271 | 2702 | 1992 | PV | 2-605-605 | 2015-11-12 | 2015-11-17 | 3 | 0 | 3 | 2015-11-18 | 2015-12-02 | 10 | 0 | 10 |  |  | 0 | 4 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-03 |  | 2016-06-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Plymouth | 2106576 | 2360 | 21.07 | PV | 3-14-931 | 2015-10-27 | 2015-10-28 | 1 |  | 1 | 2015-11-17 |  | -30199 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-20 | 2016-01-29 | [6 empty] | 0 |  | 0 |  |  | 2016-03-10 | Online
NSTAR | Carver | 2106584 | 2330 | 28 | PV | 3-10-929 | 2015-11-12 | 2015-11-17 | 3 | 0 | 3 | 2015-11-18 | 2015-12-09 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-09 |  | 2016-06-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-04-29 | Online | Private | N
NSTAR | Woburn | 2106588 | 1801 | 85 | PV | 375-H3 | 2015-11-13 | 2015-11-17 | 2 | 0 | 2 | 2015-11-18 | 2016-03-25 | 92 | 34 | 58 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-27 |  | 2016-06-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private
NSTAR | Norfolk | 2106809 | 2056 | 186.5 | PV | 146-H3 | 2015-11-17 | 2015-11-19 | 2 | 0 | 2 | 2015-11-23 | 2015-12-16 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-24 |  | 2016-06-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-14 | Online | Private
NSTAR | Westport | 2107466 | 2790 | 36 | PV | 2-523-523 | 2015-11-17 | 2015-11-19 | 2 | 0 | 2 | 2015-11-23 | 2015-11-30 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-03 |  | 2016-06-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-08-02 | Online | Private
NSTAR | Dartmouth | 2107468 | 2747 | 72 | PV | 2-543-543 | 2015-11-17 | 2015-11-19 | 2 | 0 | 2 | 2015-11-23 | 2015-12-03 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-12-08 |  | 2016-06-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-08-02 | Online | Gov't
NSTAR | Hopkinton | 2107469 | 1748 | 87 | PV | 65-H7 | 2015-11-18 | 2015-11-19 | 1 | 0 | 1 | 2015-11-20 |  | -30202 | 187 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-06-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2015-11-23
NSTAR | Carver | 2107748 | 2330 | 5966 | PV & Battery | 3-83-83 | 2015-11-19 | 2015-11-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online | Private |  | 2015-11-25
NSTAR | East Freetown | 2108032 | 2717 | 4000 | PV | 2-102-102 | 2015-11-23 | 2015-11-25 | 2 | 0 | 2 | 2015-11-26 | 2015-12-08 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-11 | 2016-02-23 | 2016-06-24 | No | EXP | 30 | 2016-04-08 | 2016-04-08 | 0 |  | 0 |  |  |  | Meter | Private | N
NSTAR | Wellfleet | 2108544 | 2663 | 50 | PV | 4-94B-653 | 2015-11-23 | 2015-11-25 | 2 | 0 | 2 | 2015-11-26 | 2015-11-27 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-11 | 2016-02-03 | 2016-06-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-26 | Online | Gov't
NSTAR | Truro | 2108546 | 2652 | 30 | PV | 4-96-674 | 2015-11-25 | 2015-11-26 | 1 | 0 | 1 | 2015-12-03 | 2015-12-07 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-05 | 2017-11-28 | 2016-07-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-01-10 | Online | Private
NSTAR | Hyannis | 2108876 | 2601 | 120 | PV | 4-84B-524 | 2015-12-03 | 2015-12-04 | 1 | 18 | -17 | 2015-12-08 | 2016-01-25 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Plymouth | 2108966 | 2360 | 23.75 | PV | 3-89-926 | 2015-11-24 | 2015-11-24 | 0 |  | 0 | 2015-12-01 |  | -30209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-07-26 | Online
NSTAR | West Tisbury | 2109230 | 2575 | 213.2 | PV | 4-97-220 | 2015-11-17 | 2015-11-30 | 9 |  | 9 | 2015-12-01 |  | -30209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-05 | 2016-01-06 | [6 empty] | 0 |  | 0 |  |  | 2016-11-30 | Online
NSTAR | Cambridge | 2109233 | 2138 | 26.6 | PV | 821-05 | 2015-11-10 | 2015-11-10 | 0 |  | 0 | 2015-12-01 |  | -30209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-11 | 2016-01-19 | [6 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online
NSTAR | Milton | 2109234 | 2186 | 32.4 | PV | 496-H7 | 2015-11-06 | 2015-11-30 | 16 |  | 16 | 2015-12-11 |  | -30217 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-05 | 2016-01-06 | [6 empty] | 0 |  | 0 |  |  | 2016-06-10 | Online
NSTAR | Plymouth | 2110218 | 2360 | 394.8 | PV | 3-14-931 | 2015-11-17 | 2015-11-17 | 0 |  | 0 | 2016-01-11 |  | -30238 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | 2016-08-10 | [6 empty] | 0 |  | 0 |  |  | 2016-11-08 | Online | PRIVATE
NSTAR | Hyde Park | 2110822 | 2136 | 1200 | PV | 344-07 | 2015-12-03 | 2015-12-04 | 1 | 0 | 1 | 2015-12-08 | 2016-07-18 | 159 | 86 | 73 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Westport | 2110823 | 2790 | 1000 | PV | 2-523-523 | 2015-12-07 | 2015-12-08 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2015-12-16
NSTAR | East Freetown | 2113074 | 2717 | 2000 | PV | 2-102-604 | 2015-12-09 | 2015-12-11 | 2 |  | 2 | 2015-12-14 | 2016-01-05 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-08 |  | 2016-07-18 | TBD | EXP | 30 |  |  | 0 |  | 0 | 2018-12-12 | 2018-12-13 | 2018-12-13 | Online | Private
NSTAR | Sudbury | 2114162 | 1776 | 15.5 | PV | 342-H7 | 2015-10-19 | 2015-10-20 | 1 |  | 1 | 2015-12-11 |  | -30217 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-01-15 | [6 empty] | 0 |  | 0 |  |  | 2016-04-04 | Online
NSTAR | Acton | 2114164 | 1720 | 17 | PV | 416-H8 | 2015-12-09 | 2015-12-11 | 2 | 0 | 2 | 2015-12-14 | 2016-01-05 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-08 |  | 2016-07-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Ashland | 2114171 | 1721 | 17 | PV | 519-175H1 | 2015-12-14 | 2015-12-15 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Carver | 2114406 | 2330 | 17.5 | PV | 3-83-950 | 2015-11-19 | 2016-01-05 | 33 |  | 33 | 2016-02-11 |  | -30261 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-10-19 | Online | PRIVATE
NSTAR | Carver | 2114902 | 2330 | 499 | PV | 3-10-929 | 2015-12-14 | 2015-12-22 | 6 | 0 | 6 | 2015-12-23 | 2015-12-23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-10 | 2016-07-04 | 2016-07-21 | TBD | EXP | 30 | 2016-07-06 | 2016-07-06 | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Plymouth | 2114928 | 2360 | 57 | PV | 3-89-922 | 2015-12-14 | 2015-12-15 | 1 | 0 | 1 | 2015-12-16 | 2016-04-26 | 94 | 74 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 |  | 2016-07-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | Private
NSTAR | Rochester | 2114929 | 2770 | 392 | PV | 3-702-702 | 2015-12-15 | 2015-12-15 | 0 | 1 | 0 | 2015-12-18 | 2016-01-06 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 | 2016-05-25 | 2016-07-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online | Private
NSTAR | Holliston | 2115036 | 1746 | 21 | PV | 274-H1 | 2015-12-16 | 2015-12-18 | 2 | 0 | 2 | 2015-12-22 | 2016-01-14 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-20 |  | 2016-07-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-03-25 | Online | Private
NSTAR | Dover | 2115395 | 2030 | 20 | PV | 456-H5 | 2015-12-16 | 2015-12-18 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study | Private | N
NSTAR | Canton | 2115399 | 2021 | 432 | PV | 470-H11 | 2015-12-17 | 2015-12-18 | 1 | 21 | -20 | 2015-12-22 | 2016-02-03 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 | 2016-05-04 |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-19 | Online | Private
NSTAR | Boston | 2115948 | 2110 | 75 | Natural Gas | 12-1N82N | 2015-12-17 | 2015-12-17 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2016-02-01
NSTAR | Cambridge | 2115956 | 2139 | 1000 | Natural Gas | 875-1N35B | 2015-12-18 | 2015-12-19 | -1 | 0 | 0 | 2015-12-24 | 2016-01-18 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Canton | 2116306 | 2021 | 396 | PV | 470-H4 | 2015-12-18 | 2015-12-22 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study | Private
NSTAR | Carver | 2116312 | 2330 | 2000 | PV | 3-10-929 | 2015-12-18 | 2015-12-22 | 2 | 0 | 2 | 2015-12-30 |  | -30230 | 155 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2019-02-28 | Online | Private |  | 2016-01-11
NSTAR | Wareham | 2116332 | 2538 | 7450 | PV | 3-84-961 | 2015-12-22 | 2016-01-15 | 18 | 0 | 18 | 2016-01-15 | 2016-04-16 | 65 | 54 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Brewster | 2116973 | 2631 | 82 | PV | 4-89A-553 | 2015-12-22 | 2015-12-23 | 1 | 0 | 1 | 2015-12-29 | 2015-12-30 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-05 |  | 2016-07-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-21 | Online | Private
NSTAR | Lexington | 2116975 | 2421 | 20.35 | PV | 320-H5XY | 2015-12-11 | 2015-12-15 | 2 |  | 2 | 2015-12-23 |  | -30225 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-27 | 2016-04-19 | [6 empty] | 0 |  | 0 |  |  | 2016-08-31 | Online | PRIVATE
NSTAR | Acusnet | 2116976 | 2743 | 16 | PV | 2-241-237 | 2015-12-23 | 2015-12-24 | 1 | 0 | 1 | 2016-01-05 | 2016-02-17 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-24 |  | 2016-08-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private
NSTAR | North Dartmouth | 2117201 | 2747 | 19.3 | PV | 2-107-107 | 2015-12-11 | 2015-12-15 | 2 |  | 2 | 2015-12-24 |  | -30226 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-22 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2016-01-03 | Online | PRIVATE
NSTAR | Duxbury | 2117204 | 2332 | 360 | PV | 3-27-970 | 2015-12-23 | 2015-12-24 | 1 | 0 | 1 | 2016-01-05 | 2016-02-17 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-08-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private | N
NSTAR | Duxbury | 2117207 | 2332 | 480 | PV | 3-26-903 | 2015-12-24 | 2015-12-29 | 3 | 13 | -10 | 2016-01-05 |  | -30234 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-25 |  | 2016-08-02 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | Private
NSTAR | Kingston | 2117310 | 2364 | 600 | PV | 3-26-902 | 2015-12-29 | 2015-12-30 | 1 | 2 | -1 | 2016-01-05 | 2016-07-19 | 140 | 0 | 140 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 |  | 2016-12-31 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-19 | Online | Private
NSTAR | Plymouth | 2117742 | 2360 | 21.4 | PV | 3-73-27J2 | 2015-12-09 | 2016-12-10 | 262 |  | 262 | 2016-01-04 |  | -30233 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-08 | 2016-01-12 | [6 empty] | 0 |  | 0 |  |  | 2016-03-17 | Online
NSTAR | Woburn | 2117752 | 1810 | 42.3 | PV | 211-H2 | 2015-12-01 | 2015-12-28 | 19 |  | 19 | 2016-01-05 |  | -30234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-22 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Yarmouth | 2117763 | 2664 | 19.3 | PV | 4-90-90 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dover | 2117764 | 2030 | 1000 | PV | 456-H4 | 2015-12-30 | 2016-01-01 | 2 | 0 | 2 | 2016-01-06 | 2016-05-31 | 104 | 0 | 104 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-14 |  | 2016-08-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Boston | 2117954 | 2118 | 587 | PV | 528-169H |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2117955 | 2118 | 471 | PV | 528-169H |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Stoneham | 2119971 | 2180 | 16.95 | PV | 375H8 | 2016-12-17 | 2016-12-22 | 4 |  | 4 | 2016-01-05 |  | -30234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-06-27 | Online
NSTAR | New Bedford | 2119973 | 2740 | 248.88 | PV | 2-137-139 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2119974 | 2746 | 280 | PV | 2-80-80 | 2016-01-05 | 2016-01-08 | 3 | 5 | -2 | 2016-01-11 | 2016-02-09 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-23 | 2016-03-28 | 2016-08-10 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-19 | Online | Private
NSTAR | Natick | 2120155 | 1760 | 457 | PV | 240-H1 | 2016-01-05 | 2016-01-08 | 3 | 0 | 3 | 2016-01-11 | 2016-01-11 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-01-21 |  | 2016-08-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-06 | Online | Gov't
NSTAR | Natick | 2120191 | 1760 | 24.8 | PV | 2302 | 2016-12-22 | 2016-12-26 | 2 |  | 2 | 2016-01-08 |  | -30237 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-28 | 2016-01-28 | [6 empty] | 0 |  | 0
NSTAR | Natick | 2120194 | 1760 | 120 | PV | 23-H1 | 2016-01-06 | 2016-01-08 | 2 | 0 | 2 | 2016-01-11 | 2016-02-10 | 22 | 19 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-11 | 2016-02-11 | 2016-08-11 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online | Private
NSTAR | Edgartown | 2120504 | 2539 | 36 | PV | 4-97-97 | 2016-01-11 | 2016-01-26 | 11 | 0 | 11 | 2016-01-26 | 2016-01-27 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-12 | 2016-02-29 | 2016-06-25 | TBD | EXP | 30 | 2016-05-24 | 2016-05-24 | 0 |  | 0 |  |  | 2016-06-08 | Online | Private
NSTAR | Woburn | 2120505 | 1801 | 16.7 | PV | 375-H11 | 2015-11-05 | 2015-11-08 | 1 |  | 1 | 2016-01-08 |  | -30237 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-23 | 2016-05-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online | PRIVATE
NSTAR | Wareham | 2122405 | 2576 | 16.5 | PV | 3-86-966 | 2015-12-04 | 2016-01-07 | 24 |  | 24 | 2016-01-11 |  | -30238 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-26 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-03-11 | Online
NSTAR | Sharon | 2122406 | 2067 | 17.5 | PV | 470-h12 | 2015-12-02 | 2016-01-07 | 26 |  | 26 | 2016-01-11 |  | -30238 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-12 | 2016-03-23 | [6 empty] | 0 |  | 0 |  |  | 2016-04-29 | Online
NSTAR | Maynard | 2122407 | 1754 | 32.85 | PV | 416-H6 | 2016-12-21 | 2017-01-05 | 11 |  | 11 | 2017-01-11 |  | -30500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-20 | 2016-02-01 | [6 empty] | 0 |  | 0 |  |  | 2016-10-21 | Online
NSTAR | Framingham | 2122694 | 1701 | 328.75 | CHP | 433-H1 | 2016-01-04 | 2016-03-16 | 52 |  | 52 | 2016-01-12 |  | -30239 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-14 | 2016-10-19 | [6 empty] | 0 |  | 0 |  |  | 2017-04-04 | Online | NO EXPORT
NSTAR | Plympton | 2122696 | 2367 | 24 | PV | 3-51-901 | 2016-01-13 | 2016-01-15 | 2 | 0 | 2 | 2016-01-18 | 2016-02-16 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-23 |  | 2016-08-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval | Private
NSTAR | Brewster | 2122697 | 2631 | 73.2 | PV | 4-89B-89B | 2016-01-05 | 2016-01-08 | 3 |  | 3 | 2016-01-27 |  | -30250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-17 | 2016-02-25 | [6 empty] | 0 |  | 0 |  |  | 2016-07-11 | Online
NSTAR | Acton | 2123114 | 2747 | 17.6 | PV | 416-H4 | 2016-01-04 | 2016-01-05 | 1 |  | 1 | 2016-01-13 |  | -30240 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-01-26 | 2016-03-03 | [6 empty] | 0 |  | 0 |  |  | 2016-03-24 | Online
NSTAR | Marshfield | 2123118 | 2050 | 19.35 | PV | 3-25-42J2 | 2016-12-23 | 2017-01-11 | 13 |  | 13 | 2017-01-15 |  | -30502 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-10 | 2016-02-11 | [6 empty] | 0 |  | 0
NSTAR | Charlestown | 2123364 | 2129 | 30 | PV | 250-H5 | 2016-01-14 | 2016-01-19 | 3 | 0 | 3 | 2016-01-21 | 2016-01-27 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-01 | 2016-08-19 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Edgartown | 2123548 | 2539 | 36 | PV | 4-97-97 | 2016-01-14 | 2016-01-19 | 3 | 0 | 3 | 2016-01-21 | 2016-03-14 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-03 | 2016-02-12 | 2016-08-19 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online | Private
NSTAR | Lexington | 2123559 | 2421 | 720 | PV | 2-1N11 | 2016-01-15 | 2016-01-19 | 2 | 7 | -5 | 2016-01-21 | 2016-03-21 | 42 | 9 | 33 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-06 |  | 2016-08-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private | N
NSTAR | Marston Mills | 2123807 | 2648 | 19.3 | PV | 4-88-478 | 2012-01-11 | 2016-01-15 | 1013 |  | 1013 | 2016-01-19 |  | -30244 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-10 | 2016-03-15 | [6 empty] | 0 |  | 0
NSTAR | Burlington | 2123809 | 1803 | 672 | PV | 391-H16 | 2016-01-20 | 2016-01-22 | 2 | 0 | 2 | 2016-01-27 |  | -30250 | 41 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-08-25 | No | TBD | 160 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review
NSTAR | West Tisbury | 2124323 | 2575 | 33.9 | PV | 4-97-97 | 2016-01-13 | 2016-01-15 | 2 |  | 2 | 2016-01-20 |  | -30245 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-03 | 2016-02-17 | [6 empty] | 0 |  | 0 |  |  | 2016-08-05 | Online
NSTAR | Cambridge | 2124635 | 2139 | 4400 | Natural Gas | 831-1110 | 2016-01-06 | 2016-01-07 | 1 | 0 | 1 | 2016-01-27 |  | -30250 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-06-07 | 2017-08-11 |  | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2020-12-14 | Online | Private
NSTAR | Hatchville | 2124636 | 2536 | 1500 | PV | 4-98A-98A | 2016-01-21 | 2016-01-22 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-02-16
NSTAR | Dedham | 2124992 | 2026 | 1740 | PV | 344-1413H1 | 2016-01-21 | 2016-01-25 | 2 | 0 | 2 | 2016-01-27 | 2016-01-28 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 |  |  | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-11-16 | Online | Private
NSTAR | Sagamore Beach | 2124995 | 2562 | 150 | PV | 3-89-925 | 2016-01-22 | 2016-01-26 | 2 | 0 | 2 | 2016-01-28 | 2016-03-22 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-09 | 2016-02-17 | 2016-08-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-12 | Online | Private | N
NSTAR | Chelsea | 2125197 | 2150 | 491 | PV | 488-H2 | 2016-01-22 | 2016-01-26 | 2 | 0 | 2 | 2016-01-28 | 2016-02-19 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-24 |  | 2016-08-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-04-28 | Online | Private
NSTAR | Ashland | 2125198 | 1721 | 90 | PV | 519-175H1 | 2016-01-25 | 2016-01-26 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-11-10 | Online | Private
NSTAR | Holliston | 2125460 | 1746 | 432 | PV | 274-H1 | 2016-01-25 | 2016-01-26 | 1 | 0 | 1 | 2016-01-28 | 2016-03-30 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-30 |  | 2016-08-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Dorchester | 2125462 | 2124 | 300 | PV | 311-07 | 2016-01-27 | 2016-01-28 | 1 | 0 | 1 | 2016-02-01 | 2016-02-19 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-11 |  | 2016-09-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-19 | Online | Private
NSTAR | Bedford | 2125698 | 1730 | 16.7 | PV | 533-H8 | 2016-12-31 | 2017-01-06 | 5 |  | 5 | 2017-01-27 |  | -30512 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-11 | 2016-03-14 | [6 empty] | 0 |  | 0 |  |  | 2016-09-06 | Online | PRIVATE
NSTAR | Falmouth | 2125878 | 2540 | 250 | PV | 10494/020 | 2016-01-28 | 2016-01-29 | 1 | 0 | 1 | 2016-02-01 | 2016-06-06 | 90 | 0 | 90 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-20 |  | 2016-09-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Needham | 2126109 | 2494 | 828 | PV | 148-H6 | 2016-01-29 | 2016-02-01 | 1 | 0 | 1 | 2016-02-04 | 2016-02-22 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-02 |  | 2016-09-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-12-18 |  | Private
NSTAR | Hyde Park | 2126261 | 2136 | 5 | PV | 6006 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 2126313 | 1748 | 6 | PV | 65-H6 | 2016-02-01 | 2016-02-02 | 1 | 0 | 1 | 2016-02-05 | 2016-03-30 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-06 |  | 2016-09-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Woburn | 2126828 | 1801 | 168 | PV | 375-H3 | 2016-02-01 | 2016-02-02 | 1 | 0 | 1 | 2016-02-05 | 2016-03-09 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 | 2017-04-18 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-02-16 | Online | Private
NSTAR | Hyde Park | 2126908 | 2136 | 168 | PV | 344-1411H2 | 2016-02-01 | 2016-02-03 | 2 | 0 | 2 | 2016-02-09 | 2016-03-29 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 | 2016-03-18 | 2016-09-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-02 | Online | Private
NSTAR | Hyde Park | 2126921 | 2136 | 192 | PV | 344-1411H2 | 2016-02-01 | 2016-02-03 | 2 | 0 | 2 | 2016-02-09 | 2016-03-29 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-29 | 2017-04-18 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-02-06 | Online | Private
NSTAR | Hyde Park | 2126922 | 2136 | 288 | PV | 344-1411H2 | 2016-02-01 | 2016-02-02 | 1 | 0 | 1 | 2016-02-05 | 2016-05-19 | 74 | 31 | 43 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-12 | 2017-04-18 |  | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2018-02-06 | Online | Private
NSTAR | Woburn | 2126923 | 1801 | 726 | PV | 375-H14 | 2016-02-02 | 2016-02-02 | 0 | 0 | 0 | 2016-02-08 | 2016-05-06 | 64 | 35 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 |  | 2016-09-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Bedford | 2127134 | 1730 | 370 | PV | 322-1397H1 | 2016-02-02 | 2016-02-03 | 1 | 0 | 1 | 2016-02-09 | 2016-07-20 | 116 | 0 | 116 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Gov't
NSTAR | Bourne | 2127227 | 2532 | 1000 | PV | 4-98A-98A | 2016-02-02 | 2016-02-03 | 1 | 0 | 1 | 2016-02-09 | 2016-04-04 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 |  | 2016-09-08 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Burlington | 2127236 | 1803 | 170 | PV | 211-H13 | 2016-02-04 | 2016-02-05 | 1 | 0 | 1 | 2016-02-15 | 2016-07-11 | 105 | 91 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Millis | 2127532 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127571 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127590 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127594 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127596 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Millis | 2127597 | 2054 | 58.4 | PV | 146-H10 | 2015-11-23 | 2016-02-04 | 53 |  | 53 | 2016-02-04 |  | -30256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-19 | 2016-02-22 | [6 empty] | 0 |  | 0 |  |  | 2016-07-14 | Online
NSTAR | Oak Bluffs | 2127808 | 2568 | 566.1 | PV | 4-75-75 | 2016-01-14 | 2016-01-20 | 4 |  | 4 | 2016-02-08 |  | -30258 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-06-07 | [6 empty] | 0 |  | 0
NSTAR | Maynard | 2127819 | 1754 | 750 | PV | STA207 | 2016-02-04 | 2016-02-04 | 0 | 0 | 0 | 2016-03-17 | 2016-04-07 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-09-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | West Roxbury | 2127824 | 2132 | 40 | PV | 468-01 | 2016-02-05 | 2016-02-08 | 1 | 0 | 1 | 2016-02-10 | 2016-03-01 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-09-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Falmouth | 2128032 | 2536 | 16.7 | PV | 4-98B-845 | 2016-02-09 | 2016-02-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-03-09
NSTAR | New Bedford | 2128034 | 2740 | 17.45 | PV | 2.3.96 | 2016-01-27 | 2016-02-01 | 3 |  | 3 | 2016-02-08 |  | -30258 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-26 | 2016-03-07 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Duxbury | 2128036 | 2332 | 20.25 | PV | 3-27-970 | 2016-01-27 | 2016-02-01 | 3 |  | 3 | 2016-02-08 |  | -30258 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-11 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  | 2016-06-13 | Online
NSTAR | Hyde Park | 2128422 | 2136 | 540 | PV | 344-1413H1 | 2016-02-09 | 2016-02-10 | 1 | 0 | 1 | 2016-02-12 | 2016-02-22 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-11 | 2016-06-06 | 2016-09-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dennisport | 2128423 | 2639 | 72 | PV | 4-92B-572 | 2016-02-10 | 2016-02-11 | 1 | 0 | 1 | 2016-02-15 | 2016-02-16 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-17 | 2016-02-17 | 2016-09-16 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-23 | Online | Private
NSTAR | Edgartown | 2128645 | 2539 | 72 | PV | 4-97-97 | 2016-02-11 | 2016-02-12 | 1 | 0 | 1 | 2016-02-18 | 2016-03-31 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 |  | 2016-09-19 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-09-22 | Online | Private
NSTAR | Woburn | 2128688 | 1801 | 53 | PV | 211-H6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2128797 | 2021 | 19 | PV | 470-H9 | 2016-02-11 | 2016-02-12 | 1 | 0 | 1 | 2016-02-18 | 2016-03-09 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-07-12 | 2016-09-19 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-07 | Online | Private
NSTAR | Brighton | 2128801 | 2135 | 111 | PV | 329-H9 | 2016-02-11 | 2016-02-12 | 1 | 0 | 1 | 2016-02-18 |  | -30266 | 129 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-19 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2016-10-12 | Online | Private |  | 2016-02-18
NSTAR | Wareham | 2128802 | 2571 | 1992 | PV | 3-83-966 | 2016-02-12 | 2016-02-16 | 2 | 0 | 2 | 2016-02-23 | 2016-03-08 | 10 | 6 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-09 |  | 2016-09-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westport | 2129051 | 2790 | 25 | PV | 2-532-532 | 2016-02-12 | 2016-02-17 | 3 | 0 | 3 | 2016-02-23 | 2016-05-26 | 67 | 63 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-27 |  | 2016-09-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Gov't
NSTAR | Newton | 2129052 | 2459 | 104 | PV | 292-H8 | 2016-02-12 | 2016-02-13 | -1 | 0 | 0 | 2016-02-23 | 2016-05-27 | 68 | 63 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-29 | 2016-05-31 | 2016-09-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-09 | Online | Private
NSTAR | Acusnet | 2129053 | 2743 | 168 | PV | 2-231-231 | 2016-02-16 | 2016-02-17 | 1 | 0 | 1 | 2016-02-18 |  | -30266 | 74 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-18 |  | 2016-09-21 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | Private
NSTAR | Plymouth | 2129459 | 2360 | 840 | PV | 3-12-12 | 2016-02-16 | 2016-02-17 | 1 | 0 | 1 | 2016-02-18 | 2016-05-18 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-08 | 2016-08-02 | 2016-09-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Plymouth | 2129461 | 2360 | 308 | PV | 3-71-71 | 2016-02-17 | 2016-02-18 | 1 | 0 | 1 | 2016-02-18 | 2016-02-18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-02-25 |  | 2016-09-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | Private
NSTAR | Assonett | 2129465 | 2702 | 16.95 | PV | 2-605-605 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Arlington | 2129730 | 2476 | 115 | PV | 320-H7 | 2016-02-17 | 2016-02-19 | 2 | 0 | 2 | 2016-02-25 | 2016-04-26 | 43 | 27 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-02 |  | 2016-09-22 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | New Bedford | 2129733 | 2745 | 496 | PV | 2-103-103 | 2016-02-18 | 2016-03-15 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-03-17
NSTAR | Marston Mills | 2129905 | 2648 | 4400 | PV | 4-88-478 | 2016-02-18 | 2016-02-19 | 1 | 73 | -72 | 2016-02-22 | 2016-03-21 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-04-15 |  | -30307 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-02 | 2016-10-03 | 2016-12-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-05-09
NSTAR | Framingham | 2129908 | 1701 | 1250 | PV | 203-1348H3 | 2016-02-01 | 2016-02-04 | 3 |  | 3 | 2016-02-19 |  | -30267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-11 | 2016-04-12 | [6 empty] | 0 |  | 0 |  |  | 2017-12-18 | Online
NSTAR | Watertown | 2130080 | 2472 | 216 | PV | 467-H6 | 2016-02-19 | 2016-02-22 | 1 | 0 | 1 | 2016-02-25 | 2016-03-01 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-02 | 2016-03-02 | 2016-09-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-30 | Online | Private
NSTAR | Edgartown | 2130081 | 2539 | 170 | PV | 4-97-97 | 2016-02-22 | 2016-02-23 | 1 | 0 | 1 | 2016-03-03 | 2016-03-22 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-25 |  | 2016-09-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-10-26 | Online | Private
NSTAR | Canton | 2130083 | 2021 | 495.72 | PV | 470-H11 | 2016-01-12 | 2016-01-24 | 8 |  | 8 | 2016-02-23 |  | -30269 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2016-06-10 | 30346 |  | 30346 |  |  | 0 |  | 0 | 2017-07-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Fairhaven | 2130412 | 2719 | 16.4 | PV | 2-221-221 | 2016-02-02 | 2016-02-02 | 0 |  | 0 | 2016-02-23 |  | -30269 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-07 | 2016-03-18 | [6 empty] | 0 |  | 0 |  |  | 2016-07-01 | Online
NSTAR | Cambridge | 2130419 | 2140 | 36 | PV | 824-26 | 2016-02-23 | 2016-02-26 | 3 | 0 | 3 | 2016-03-03 | 2016-03-15 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-16 |  | 2016-09-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-05-23 | Online | Private
NSTAR | Cambridge | 2130635 | 2139 | 27 | PV | 815-10 | 2016-02-23 | 2016-03-09 | 11 | 0 | 11 | 2016-03-15 | 2016-06-23 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-15 |  | 2016-09-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights/Customer Cost | Private
NSTAR | Woburn | 2130638 | 1801 | 50 | PV | 375-H4 | 2016-02-24 | 2016-04-08 | 32 | 0 | 32 | 2016-04-25 | 2016-05-04 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-04 | 2016-07-25 | 2016-09-29 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-04-18 | Online | Private
NSTAR | Stoneham | 2130639 | 2180 | 30.3 | PV | 301-03 | 2016-02-05 | 2016-02-10 | 3 |  | 3 | 2016-02-25 |  | -30271 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-06-01 | [6 empty] | 0 |  | 0 |  |  | 2016-12-14 | Online | PRIVATE
NSTAR | New Bedford | 2130836 | 2744 | 144 | PV | 2-69-69 | 2016-02-24 | 2016-02-29 | 3 | 0 | 3 | 2016-03-15 | 2016-03-23 | 6 | 3 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-11 |  | 2016-09-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Hyannis | 2130872 | 2601 | 21.045 | PV | 4-63-521 | 2016-02-09 | 2016-02-12 | 3 |  | 3 | 2016-02-24 |  | -30270 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-06 | 2016-04-27 | [6 empty] | 0 |  | 0 |  |  | 2016-07-28 | Online
NSTAR | Newton | 2130935 | 2468 | 36 | PV | 292-H12 | 2016-02-25 | 2016-02-26 | 1 | 0 | 1 | 2016-03-03 | 2016-06-06 | 67 | 58 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-19 | Online | Private
NSTAR | Newton | 2130936 | 2461 | 57.5 | PV | 369-01 | 2016-02-08 | 2016-02-10 | 2 |  | 2 | 2016-02-29 |  | -30273 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-11 | 2016-04-14 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online
NSTAR | Dover | 2130937 | 2030 | 16.7 | PV | 456-H5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2131133 | 2360 | 22.575 | PV | 3-71-71 | 2016-02-01 | 2016-02-01 | 0 |  | 0 | 2016-02-29 |  | -30273 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-29 | 2016-03-30 | [6 empty] | 0 |  | 0 |  |  | 2016-10-26 | Online
NSTAR | Canton | 2131137 | 2021 | 496 | PV | 470-H8 | 2016-02-25 | 2016-02-29 | 2 | 0 | 2 | 2016-03-03 | 2016-03-18 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-03-18 |  | 2016-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Framingham | 2131138 | 1702 | 60 | WIND | 240-H4 | 2016-02-26 | 2016-02-29 | 1 | 0 | 1 | 2016-03-03 | 2016-04-07 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-07 |  | 2016-10-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Rochester | 2131315 | 2770 | 15.2 | PV | 3-702-702 | 2016-02-04 | 2016-02-12 | 6 |  | 6 | 2016-02-29 |  | -30273 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-20 | 2016-07-11 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2131316 | 2537 | 15.2 | PV | 4-81B-443 | 2016-02-08 | 2016-02-12 | 4 |  | 4 | 2016-02-29 |  | -30273 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-28 | 2016-04-25 | [6 empty] | 0 |  | 0 |  |  | 2016-11-01 | Online | PRIVATE
NSTAR | Somerville | 2131317 | 2145 | 56 | PV | 227-51H2 | 2016-02-29 |  | -30273 | 0 | 0 | 2016-03-03 | 2016-05-27 | 61 | 48 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Watertown | 2131752 | 2472 | 125 | PV | 467-H2 | 2016-02-29 | 2016-03-02 | 2 | 0 | 2 | 2016-03-03 | 2016-05-10 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-11 |  | 2016-10-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | Private
NSTAR | Newton | 2131753 | 2461 | 492 | PV | 292-H2 | 2016-03-01 | 2016-03-29 | 20 | 0 | 20 | 2016-03-29 | 2016-05-12 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-11 | 2016-05-12 | 2016-10-05 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online | Private
NSTAR | Plymouth | 2132061 | 2360 | 2000 | PV | 3-89-925 | 2016-03-02 | 2016-03-03 | 1 | 0 | 1 | 2016-03-09 | 2016-06-02 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-03 |  | 2016-10-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online | Private
NSTAR | Somerville | 2132326 | 2145 | 84 | PV | 227-52H3 | 2016-03-02 | 2016-03-03 | 1 | 0 | 1 | 2016-03-09 | 2016-05-14 | 47 | 32 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-31 | 2016-06-03 | 2016-10-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-14 | Online | Private
NSTAR | Dennisport | 2132327 | 2639 | 65.7 | PV | 4-92B-583 | 2016-02-16 | 2016-02-18 | 2 |  | 2 | 2016-03-03 |  | -30276 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-31 | 2016-10-24 | [6 empty] | 0 |  | 0 |  |  | 2017-03-23 | Online | PRIVATE
NSTAR | Dennisport | 2132335 | 2639 | 40 | PV | 4-92B-583 | 2016-03-02 | 2016-03-03 | 1 | 22 | -21 | 2016-04-25 | 2016-05-13 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Falmouth | 2132336 | 2536 | 185 | PV | 4-92B-583 | 2016-03-03 | 2016-07-14 | 95 | 0 | 95 | 2016-07-14 | 2016-07-18 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-20 | 2016-10-24 | 2016-10-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2132937 | 2571 | 150 | PV | 3-84-84 | 2016-03-04 | 2016-03-08 | 2 | 0 | 2 | 2016-03-15 | 2016-03-22 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 | 2016-09-01 | 2016-10-11 | No | EXP | 30 | 2016-05-24 | 2016-05-24 | 0 |  | 0 |  |  |  | ISA Received/Signed | Private
NSTAR | Plymouth | 2132938 | 2360 | 18.92 | PV | 3-71-38J1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2133263 | 1741 | 22 | PV | 533-H8 | 2016-03-04 | 2016-03-07 | 1 | 0 | 1 | 2016-03-15 | 2016-05-17 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 |  | 2016-10-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private
NSTAR | Sandwich | 2133264 | 2563 | 109.2 | PV | 4-81B-443 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2133265 | 2360 | 66 | PV | 3-12-12 | 2016-03-07 | 2016-03-10 | 3 | 0 | 3 | 2016-03-15 | 2016-04-25 | 29 | 24 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-03 | 2016-07-25 | 2016-10-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-03 | Online | Private
NSTAR | Bedford | 2133471 | 1730 | 312 | PV | 487-1376H1 | 2016-03-07 | 2016-03-09 | 2 | 0 | 2 | 2016-03-15 |  | -30284 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-12 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | Private
NSTAR | Buzzards Bay | 2133572 | 2532 | 66 | PV | 3-90-10J2 | 2016-03-07 | 2016-03-09 | 2 | 0 | 2 | 2016-03-15 | 2016-06-07 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-12 | 2016-12-19 | 2016-10-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-07 | Online | Private
NSTAR | Arlington | 2133574 | 2476 | 40.32 | PV | 211-H3 | 2016-02-19 | 2016-02-19 | 0 |  | 0 | 2016-03-09 |  | -30280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-15 | 2016-07-12 | [6 empty] | 0 |  | 0 |  |  | 2017-03-31 | Online | PRIVATE
NSTAR | Ashland | 2133577 | 1721 | 756.4 | PV | 274-H5 | 2016-02-07 | 2016-02-22 | 11 |  | 11 | 2016-03-10 |  | -30281 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-06-16 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
NSTAR | Brighton | 2133578 | 2135 | 48 | PV | 329-H7 | 2016-03-09 | 2016-03-11 | 2 | 0 | 2 | 2016-03-21 | 2016-04-11 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-13 |  | 2016-10-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Newton | 2133801 | 2461 | 47.52 | PV | 1701 | 2016-02-19 | 2016-04-07 | 34 |  | 34 | 2016-03-10 |  | -30281 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-07 | 2016-04-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2133803 | 2461 | 41.76 | PV | 467-H3 | 2016-02-19 | 2016-02-19 | 0 |  | 0 | 2016-03-10 |  | -30281 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-23 | 2016-05-23 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Somerville | 2133805 | 2143 | 23.04 | PV | 250-1N90H2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2134025 | 2601 | 72 | PV | 4-84B-524 | 2016-03-09 | 2016-03-11 | 2 | 0 | 2 | 2016-03-21 | 2016-04-11 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-11 |  | 2016-10-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | West Tisbury | 2134027 | 2575 | 95.4 | PV | 4-97-97 | 2016-02-17 | 2016-02-23 | 4 |  | 4 | 2016-03-11 |  | -30282 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-06 | 2016-05-10 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online | PRIVATE | Y
NSTAR | Sudbury | 2134028 | 1776 | 112 | PV | 342-H2 | 2016-03-09 | 2016-03-10 | 1 | 0 | 1 | 2016-03-21 | 2016-04-06 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Newton | 2134029 | 2462 | 15.2 | PV | 292-H7 | 2016-02-24 | 2016-02-24 | 0 |  | 0 | 2016-03-16 |  | -30285 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-04 | 2016-05-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-19 | Online | PRIVATE
NSTAR | Newton | 2134030 | 2459 | 159 | PV | 292-H2 | 2016-03-10 | 2016-03-14 | 2 | 0 | 2 | 2016-03-17 | 2016-04-07 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-14 |  | 2016-10-17 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | South Walpole | 2134146 | 2071 | - |  | TBD | 2016-03-10 | 2016-03-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-17 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Sudbury | 2134239 | 1776 | 600 | PV | 342-H2 | 2016-03-10 | 2016-03-11 | 1 | 0 | 1 | 2016-03-21 | 2016-04-05 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-04-08 | 2016-10-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Carlisle | 2134241 | 1741 | 39 | PV | 512-1399H1 | 2016-03-11 | 2016-03-12 | -1 | 0 | 0 | 2016-03-22 | 2016-06-16 | 62 | 40 | 22 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-08 | 2016-04-08 | 2016-10-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-16 | Online | Private | Y
NSTAR | Woburn | 2134403 | 1801 | 200 | PV | 375-H6 | 2016-03-11 | 2016-03-16 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2016-03-21
NSTAR | Waltham | 2134404 | 2453 | 16.15 | PV | 3311 | 2016-03-10 | 2016-03-11 | 1 |  | 1 | 2016-03-16 |  | -30285 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-08 | 2016-04-22 | [6 empty] | 0 |  | 0 |  |  | 2016-08-02 | Online
NSTAR | Acton | 2134405 | 1720 | 990 | PV | 416-H4 | 2016-03-15 | 2016-04-20 | 26 | 39 | -13 | 2016-03-22 | 2016-05-13 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-13 |  | 2016-10-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Sandwich | 2135023 | 2537 | 984 | PV | 4-87A-471 | 2016-03-15 | 2016-03-16 | 1 | 0 | 1 | 2016-03-23 | 2016-05-16 | 38 | 1 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-08 | 2016-06-17 | 2016-10-20 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Rights | Private
NSTAR | Woburn | 2135024 | 1801 | 378 | PV | 375-H4 | 2016-03-15 | 2016-03-18 | 3 | 0 | 3 | 2016-03-28 | 2016-05-16 | 35 | 28 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-07 | 2016-06-08 | 2016-10-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-09 | Online | Private
NSTAR | Needham | 2135025 | 2494 | 150 | PV | 148-H1 | 2016-03-16 | 2016-03-17 | 1 | 11 | -10 | 2016-04-04 | 2016-06-14 | 51 | 5 | 46 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Cambridge | 2135260 | 2138 | 405 | PV | 819-1NB3 | 2016-03-16 | 2016-03-17 | 1 | 0 | 1 | 2016-03-22 | 2016-04-20 | 21 | 16 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Plymouth | 2135261 | 2360 | 2000 | PV | 3-89-922 | 2016-03-16 | 2016-03-31 | 11 | 0 | 11 | 2016-04-07 |  | -30301 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-21 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Rochester | 2135262 | 2770 | 260 | PV | 3-702-702 | 2016-03-16 | 2016-03-22 | 4 | 0 | 4 | 2016-03-22 |  | -30289 | 97 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-26 | 2017-01-24 | 2016-10-21 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-03-08 | Online | Private | N
NSTAR | Carver | 2135263 | 2330 | 490 | PV | 3-81-950 | 2016-03-17 | 2016-03-18 | 1 | 0 | 1 | 2016-03-28 | 2016-04-18 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-06 |  | 2016-10-24 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | ISA sent | Private
NSTAR | Dedham | 2135559 | 2026 | 112 | PV | 20-H5 | 2016-03-18 | 2016-03-21 | 1 | 0 | 1 | 2016-03-28 | 2016-05-24 | 41 | 28 | 13 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-26 |  | 2016-10-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | Private
NSTAR | Waltham | 2135867 | 2451 | 270 | PV | 450-H8 | 2016-05-24 | 2016-05-24 | 0 | 0 | 0 | 2016-05-24 | 2016-08-10 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 | 2016-08-29 | 2016-10-25 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dedham | 2135868 | 2026 | 84 | PV | 20-H1 | 2016-03-18 | 2016-03-30 | 8 | 0 | 8 | 2016-03-30 |  | -30295 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-25 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Engineering Screen Review | Private | N
NSTAR | Cambridge | 2135869 | 2140 | 270 | PV | 828-1NA9 | 2016-03-21 | 2016-03-29 | 6 | 0 | 6 | 2016-04-04 | 2016-04-06 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-05-22 | [7 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Carver | 2135870 | 2330 | 34.2 | PV | 3-10-930 | 2016-02-24 | 2016-02-29 | 3 |  | 3 | 2016-03-21 |  | -30288 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-09 | 2016-05-12 | [6 empty] | 0 |  | 0 |  |  | 2017-01-20 | Online
NSTAR | Carlisle | 2136139 | 1741 | 17 | PV | 512-1399H1 | 2016-03-21 | 2016-03-25 | 4 | 0 | 4 | 2016-03-31 | 2016-06-14 | 53 | 22 | 31 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-21 | 2016-09-08 | 2016-10-26 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-18 | Online | Private
NSTAR | Somerville | 2136141 | 2145 | 499.5 | PV | 250-H4XY | 2016-03-21 | 2016-03-23 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2016-03-31
NSTAR | Hopkinton | 2136142 | 1748 | 2000 | PV | 126-H1 | 2016-03-23 | 2016-05-12 | 36 | 0 | 36 | 2016-03-31 |  | -30296 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-28 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Chestnut Hill | 2136357 | 2467 | 324.8 | PV | 292-H6 | 2016-02-08 | 2016-03-01 | 16 |  | 16 | 2016-03-23 |  | -30290 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-03 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online | Private | Y
NSTAR | Chestnut Hill | 2136359 | 2467 | 196.24 | PV | 292-H6 | 2016-02-08 | 2016-03-01 | 16 |  | 16 | 2016-03-23 |  | -30290 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-31 | 2016-06-16 | [6 empty] | 0 |  | 0 |  |  | 2017-04-24 | Online | Private | Y
NSTAR | Hyannis | 2136574 | 2601 | 465 | PV | 4-84B-524 | 2016-02-09 | 2016-02-17 | 6 |  | 6 | 2016-03-24 |  | -30291 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2016-11-01 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online
NSTAR | Hyannis | 2136578 | 2601 | 364 | PV | 4-84B-524 | 2016-02-09 | 2016-02-17 | 6 |  | 6 | 2016-03-24 |  | -30291 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2016-11-01 | [6 empty] | 0 |  | 0 |  |  | 2017-05-03 | Online
NSTAR | Newton | 2136579 | 2459 | 240 | PV | 292-H8 | 2016-03-24 | 2016-04-04 | 7 | 0 | 7 | 2016-04-04 | 2016-04-04 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-06 | 2016-04-05 | 2016-10-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-01-24 | Online | Private
NSTAR | Hatchville | 2136806 | 2536 | 15.4 | PV | 4-98A-98A | 2016-03-25 | 2016-03-28 | 1 | 0 | 1 | 2016-03-29 | 2016-04-04 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-05 | 2016-06-16 | 2016-11-01 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-06 | Online | Private
NSTAR | Dennis | 2136807 | 2660 | 21.75 | PV | 4-92B-92B | 2016-03-01 | 2016-03-02 | 1 |  | 1 | 2016-03-25 |  | -30292 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-19 | 2016-06-22 | [6 empty] | 0 |  | 0
NSTAR | Newton | 2136808 | 2468 | 109.25 | PV | 292-H12 | 2016-02-25 | 2016-03-02 | 4 |  | 4 | 2016-03-25 |  | -30292 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-06 | 2016-07-25 | 2016-07-25 | [5 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2136975 | 2740 | 468 | PV | 2-110-110 | 2016-03-25 | 2016-03-28 | 1 | 0 | 1 | 2016-03-31 |  | -30296 | 86 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-01 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2016-12-19 | Online | Private |  | 2016-04-20
NSTAR | Acton | 2136976 | 1720 | 990 | PV | 416-H4 | 2016-03-28 | 2016-03-29 | 1 | 0 | 1 | 2016-03-29 |  | -30294 | 81 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-02 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-04-27
NSTAR | Dartmouth | 2137247 | 2747 | 1000 | PV | 2-532-532 | 2016-03-28 | 2016-03-28 | 0 | 0 | 0 | 2016-03-29 | 2016-04-28 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Plympton | 2137254 | 2367 | 972 | PV | 3-51-901 | 2016-03-29 | 2016-03-30 | 1 | 0 | 1 | 2016-04-07 | 2016-05-18 | 29 | 17 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 |  | 2016-11-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Design Approval | Private
NSTAR | Jamaica Plain | 2137255 | 2130 | 21.9 | PV | 496-H4 | 2016-02-24 | 2016-02-29 | 3 |  | 3 | 2016-03-29 |  | -30294 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-30 | 2016-04-08 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online | PRIVATE
NSTAR | Carver | 2137495 | 2330 | 1860 | PV | 3-51-980 | 2016-03-08 | 2016-03-08 | 0 |  | 0 | 2016-03-29 |  | -30294 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-15 | 2016-08-18 | [6 empty] | 0 |  | 0 |  |  | 2017-02-24 | Online
NSTAR | Dorchester | 2137497 | 2121 | 57.6 | PV | 106-H2 | 2016-02-15 | 2016-02-26 | 9 |  | 9 | 2016-04-01 |  | -30297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2137498 | 2451 | 290 | PV | 450-H3 | 2016-03-30 | 2016-03-31 | 1 | 0 | 1 | 2016-04-07 |  | -30301 | 86 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 | 2016-08-29 | 2016-11-04 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-06-06
NSTAR | Lexington | 2137830 | 2421 | 360 | PV | 320-H4 | 2016-03-30 | 2016-04-01 | 2 | 0 | 2 | 2016-04-07 | 2016-05-31 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-30 |  | 2016-11-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Framingham | 2137840 | 1702 | 219 | PV | 455-H5 | 2016-03-31 | 2016-04-01 | 1 | 0 | 1 | 2016-04-07 | 2016-04-11 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-04-12 |  | 2016-11-07 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dartmouth | 2138143 | 2747 | 18 | PV | 2-532-532 | 2016-04-01 | 2016-04-05 | 2 | 0 | 2 | 2016-04-11 | 2016-06-22 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-29 |  | 2016-11-08 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | Private | N
NSTAR | Mashpee | 2138475 | 2649 | 53.8 | PV | 4-88-455 | 2016-03-28 | 2016-03-30 | 2 |  | 2 | 2016-04-06 |  | -30300 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-05-31 | [6 empty] | 0 |  | 0 |  |  | 2019-01-10 | Online
NSTAR | Dover | 2138477 | 2030 | 282 | PV | 456-H5 | 2016-04-06 | 2016-04-07 | 1 | 0 | 1 | 2016-04-25 | 2016-06-13 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Kingston | 2138478 | 2364 | 16.69 | PV | 3-17-916 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Freetown | 2139202 | 2717 | 24.32 | PV | 2-102-602 | 2016-03-23 | 2016-04-06 | 10 |  | 10 | 2016-04-06 |  | -30300 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-09 | 2016-06-10 | [6 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online | PRIVATE
NSTAR | Bedford | 2139203 | 1730 | 21.9 | PV | 322-05 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2139413 | 1760 | 16.2 | PV | 240-H1 | 2016-03-20 | 2016-03-28 | 6 |  | 6 | 2016-04-07 |  | -30301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-04-22 | 2016-07-11 | [6 empty] | 0 |  | 0
NSTAR | Weston | 2139664 | 2493 | 20.16 | PV | 282-H2 | 2016-03-28 | 2016-03-28 | 0 |  | 0 | 2016-04-07 |  | -30301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-26 | 2016-06-28 | [6 empty] | 0 |  | 0 |  |  | 2016-11-01 | Online | PRIVATE
NSTAR | Canton | 2139666 | 2021 | 192 | PV | 470-H7 | 2016-04-07 | 2016-04-11 | 2 | 0 | 2 | 2016-04-20 | 2016-06-20 | 43 | 6 | 37 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-28 | 2016-08-24 | 2016-11-15 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Customer Cost | Private
NSTAR | Newton | 2139847 | 2468 | 982 | PV | 292-H2 | 2016-04-08 | 2016-04-09 | -1 | 0 | 0 | 2016-04-19 | 2016-05-04 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-25 |  | 2016-11-16 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | ISA sent | Private
NSTAR | Duxbury | 2139848 | 2332 | 24.32 | PV | 3-26-903 | 2016-03-17 | 2016-03-28 | 7 |  | 7 | 2016-05-26 |  | -30336 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-26 | 2016-06-09 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online | private
NSTAR | Charlestown | 2140031 | 2129 | 288 | PV | 10-H1 | 2016-04-11 | 2016-04-12 | 1 | 0 | 1 | 2016-04-25 | 2016-05-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-13 |  | 2016-11-17 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Mashpee | 2140032 | 2649 | 21.9 | PV | 4-88-483 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2140033 | 1776 | 15.75 | PV | 342-H2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | 2140338 | 2364 | 50 | PV | 3-17-17 | 2016-04-11 | 2016-04-12 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-09-28 | Online | Private
NSTAR | Woburn | 2140339 | 1801 | 480 | PV | 375-H6 | 2016-04-11 | 2016-04-25 | 10 | 0 | 10 | 2016-04-28 | 2016-07-13 | 54 | 49 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 |  | 2016-11-17 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval | Private
NSTAR | Plymouth | 2140340 | 2360 | 364.3 | PV | 3-89-922 | 2016-04-12 | 2016-04-13 | 1 | 0 | 1 | 2016-04-18 | 2016-05-02 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-12-13 | 2016-12-22 | 2016-11-18 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-24 | Online | Private
NSTAR | Weston | 2140569 | 2493 | 246 | PV | 433-H6 | 2016-04-14 | 2016-04-20 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng Screen Review: Awaiting Customer's Response/Docs | Private |  | 2016-04-27
NSTAR | Burlington | 2140576 | 1803 | 16.72 | PV | 391-H6 | 2016-03-29 | 2016-04-05 | 5 |  | 5 | 2016-04-14 |  | -30306 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-12 | 2016-06-29 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2140849 | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2140850 | 2121 | 43.2 | PV | 483-H7 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2140851 | 2121 | 43.2 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2141085 | 2021 | 252 | PV | 470-H11 | 2016-04-14 | 2016-04-20 | 4 | 0 | 4 | 2016-04-27 | 2016-06-15 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-06-10 | 2016-06-10 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-11-02 | 2016-11-17 | 2016-11-22 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-16 | Online | Private
NSTAR | Dorchester | 2141087 | 2121 | 57 | PV | 106-H2 | 2016-04-15 | 2016-04-27 | 8 | 0 | 8 | 2016-04-27 | 2016-05-13 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-16 |  | 2016-11-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Somerville | 2141311 | 2145 | 18 | PV | 250-H4XY | 2016-04-18 | 2016-04-20 | 2 | 0 | 2 | 2016-04-27 | 2016-06-15 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-15 |  | 2016-11-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting ISA Receipt/Approval | Private
NSTAR | Dorchester | 2141870 | 2121 | 48 | PV | 106-H2 | 2016-04-21 | 2016-04-22 | 1 | 0 | 1 | 2016-05-12 | 2016-06-06 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-11-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dorchester | 2141880 | 2121 | 30.4 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2141881 | 2121 | 25.8 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142397 | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142398 | 2121 | 25.8 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142654 | 2121 | 26.6 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2142655 | 2121 | 28.8 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Sudbury | 2142844 | 1776 | 21.6 | PV | 342-h8 | 2016-04-11 | 2016-04-19 | 6 |  | 6 | 2016-04-25 |  | -30313 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-13 | 2016-08-10 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2142845 | 2121 | 45.6 | PV | 483-H7 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2142846 | 2124 | 57 | PV | 106-H2 | 2016-03-31 | 2016-04-05 | 3 |  | 3 | 2016-04-28 | 2016-05-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dorchester | 2143232 | 2121 | 30.4 | PV | 106-H2 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2143233 | 2121 | 26.6 | PV | 143-109H4 | 2016-03-04 | 2016-03-04 | 0 |  | 0 | 2016-04-27 |  | -30315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-20 | 2016-09-28 | [6 empty] | 0 |  | 0
NSTAR | Harwich | 2143454 | 2645 | 16.77 | PV | 4-95A-599 | 2016-03-31 | 2016-04-05 | 3 |  | 3 | 2016-04-28 |  | -30316 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-13 | 2016-08-24 | [6 empty] | 0 |  | 0 |  |  | 2017-01-25 | Online | PRIVATE
NSTAR | Kingston | 2143458 | 2364 | 48 | PV | 3-17-910 | 2016-04-26 | 2016-04-28 | 2 | 0 | 2 | 2016-05-02 | 2016-05-06 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-16 | 2016-09-08 | 2016-12-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online | Private
NSTAR | Woburn | 2143665 | 1801 | 140 | PV | 211-H5 | 2016-04-27 | 2016-04-29 | 2 | 0 | 2 | 2016-04-29 | 2016-06-17 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-17 |  | 2016-12-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-11-09 | Online | Private
NSTAR | Woburn | 2143667 | 1801 | 112 | PV | 211-H5 | 2016-04-27 | 2016-05-20 | 17 | 0 | 17 | 2016-05-26 | 2016-08-17 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-09-23 | 2016-12-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-04-05 | Online | Private | Y
NSTAR | Natick | 2143668 | 1760 | 16.25 | PV | 433-H5 | 2016-04-05 | 2016-04-11 | 4 |  | 4 | 2016-04-29 |  | -30317 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-16 | 2010-06-03 | [6 empty] | 0 |  | 0 |  |  | 2016-09-19 | Online | PRIVATE
NSTAR | Carlisle | 2143902 | 1741 | 17.4 | PV | 512-1399h1 | 2016-04-10 | 2016-04-11 | 1 |  | 1 | 2016-05-02 |  | -30318 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-27 | 2016-06-20 | [6 empty] | 0 |  | 0 |  |  | 2016-08-23 | Online
NSTAR | Jamaica Plain | 2143903 | 2130 | 30 | PV | 284-07 | 2016-04-28 | 2016-05-03 | 3 | 0 | 3 | 2016-05-13 | 2016-05-16 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-26 | 2016-06-02 | 2016-12-06 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-02 | Online | Private
NSTAR | Milton | 2144091 | 2186 | 25.05 | PV | 496-H7 | 2016-03-11 | 2016-04-01 | 15 |  | 15 | 2016-05-02 |  | -30318 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-05-06 | 2016-06-30 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2144430 | 1720 | 18 | PV | 416-H4 | 2016-05-02 | 2016-05-03 | 1 | 0 | 1 | 2016-05-13 | 2016-05-27 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-01 |  | 2016-12-08 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-08-31 | Online | Private
NSTAR | Weston | 2145203 | 2493 | 20 | PV | 282-H10 | 2016-05-04 | 2016-05-05 | 1 | 0 | 1 | 2016-05-11 | 2016-05-24 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-07 |  | 2016-12-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-07-13 | Online | Private
NSTAR | Canton | 2145484 | 2021 | 780 | PV | 269-1320H1 | 2016-05-05 | 2016-05-11 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Eng. Impact Study | Private
NSTAR | West Roxbury | 2145690 | 2132 | 684 | PV | 374-04 | 2016-05-06 | 2016-05-11 | 3 | 0 | 3 | 2016-05-16 |  | -30328 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-05-25 | 2016-05-25 | 2016-12-14 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Mashpee | 2145692 | 2649 | 58.9 | PV | 4-88-453 | 2016-02-10 | 2016-04-27 | 55 |  | 55 | 2016-05-11 |  | -30325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-27 | 2016-09-26 | [6 empty] | 0 |  | 0 |  |  | 2016-12-05 | Online | PRIVATE
NSTAR | Woburn | 2145950 | 1801 | 43.009 | PV | 211-H5 | 2016-04-20 | 2016-05-02 | 8 |  | 8 | 2016-05-12 |  | -30326 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-31 | 2016-09-06 | 2016-09-06 | [5 empty] | 0 |  | 0 |  |  | 2017-01-27 | Online | PRIVATE
NSTAR | West Newton | 2145951 | 2465 | 21.681 | PV | 282-H9 | 2016-04-26 | 2016-04-29 | 3 |  | 3 | 2016-05-12 |  | -30326 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-11 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2017-01-27 | Online | PRIVATE | Y
NSTAR | Woburn | 2146188 | 1801 | 15.2 | PV | 211-H6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2146368 | 2360 | 99.9 | PV | 3-88-924 | 2016-05-05 | 2016-05-05 | 0 |  | 0 | 2016-05-10 |  | -30324 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | 2016-08-15 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Duxbury | 2146377 | 2332 | 28.8 | PV | 3-26-903 | 2016-03-24 | 2016-05-02 | 27 |  | 27 | 2016-05-10 |  | -30324 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | PRIVATE
NSTAR | Dennisport | 2146378 | 2639 | 34.77 | PV | 4-85-592 | 2016-05-05 | 2016-05-05 | 0 |  | 0 | 2016-05-10 |  | -30324 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-01 | 2016-06-24 | [6 empty] | 0 |  | 0 |  |  | 2016-08-11 | Online
NSTAR | Sherborn | 2146567 | 1770 | 19 | PV | 274-H2 | 2016-05-12 | 2016-05-18 | 4 | 0 | 4 | 2016-05-26 | 2016-06-10 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-17 |  | 2016-12-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-08 | Online | Private
NSTAR | New Bedford | 2146760 | 2744 | 499.5 | PV | 2-69-52 | 2016-05-08 | 2016-05-09 | 1 |  | 1 | 2016-05-22 |  | -30332 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-27 | 2016-06-30 | [6 empty] | 0 |  | 0 |  |  | 2016-12-28 | Online
NSTAR | Waltham | 2147316 | 2452 | 16.15 | PV | 33-H2 | 2016-05-13 | 2016-05-16 | 1 |  | 1 | 2016-05-23 |  | -30333 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-17 | 2016-06-29 | [6 empty] | 0 |  | 0 |  |  | 2016-08-23 | Online | PRIVATE
NSTAR | Ashland | 2147605 | 1721 | 728 | PV | 3-10-929 | 2016-05-18 | 2016-05-19 | 1 | 0 | 1 | 2016-07-14 | 2016-07-29 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2015-08-11 | 2015-08-18 | 2016-12-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Field Com | Private
NSTAR | Carver | 2147609 | 2330 | 20 | PV | 3-10-929 | 2016-05-18 | 2016-05-23 | 3 | 0 | 3 | 2016-05-26 | 2016-08-19 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-22 | 2017-01-19 | 2016-12-27 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-28 | Online | Private | N
NSTAR | Boston | 2147800 | 2118 | 336 | PV | 106-H4 | 2016-05-19 | 2016-05-20 | 1 | 0 | 1 | 2016-05-23 | 2016-08-10 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-14 | 2016-09-15 | 2016-12-28 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | ISA Received/Signed | Private
NSTAR | Assonett | 2148246 | 2702 | 432 | PV | 2-605-605 | 2016-05-23 | 2016-05-24 | 1 | 0 | 1 | 2016-05-24 |  | -30334 | 58 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-12-14 |  | 2016-12-30 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-10-23 | Online | Private |  | 2016-05-30
NSTAR | Natick | 2148247 | 1760 | 280 | PV | 433-H7 | 2016-05-23 | 2016-05-24 | 1 | 0 | 1 | 2016-05-30 | 2016-07-25 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 | 2016-08-24 | 2016-12-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-06 | Online | Private
NSTAR | Newton | 2148462 | 2466 | 1800 | PV | 33-H3 | 2016-05-24 | 2016-05-25 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-07-07 | Online | Private |  | 2016-06-06
NSTAR | Roxbury | 2148650 | 2120 | 936 | PV | 483-H6 | 2016-05-25 | 2016-05-31 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Online | Gov't
NSTAR | Sherborn | 2148838 | 1770 | 23.1 | PV | 274-H3 | 2016-05-03 | 2016-05-18 | 11 |  | 11 | 2016-06-02 |  | -30341 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-07 | [7 empty] | 0 |  | 0 |  |  | 2016-09-09 | Online | PRIVATE
NSTAR | Lexington | 2149011 | 2421 | 15.4 | PV | 3408 | 2016-05-16 | 2016-05-18 | 2 |  | 2 | 2016-06-02 |  | -30341 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-06-17 | 2016-06-20 | [6 empty] | 0 |  | 0 |  |  | 2016-08-31 | Online | PRIVATE
NSTAR | Stoneham | 2150045 | 2180 | 15.98 | PV | 375-H8 | 2016-05-13 | 2016-05-18 | 3 |  | 3 | 2016-06-02 |  | -30341 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-05 | 2016-08-10 | [6 empty] | 0 |  | 0 |  |  |  |  | PRIVATE
NSTAR | Hyannis | 2151036 | 2601 | 38 | PV | 4-63-63 | 2016-06-02 | 2016-06-08 | 4 | 0 | 4 | 2016-06-14 | 2016-06-30 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-14 |  | 2017-01-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  |  | Private
NSTAR | Bedford | 2151037 | 1730 | 288 | PV | 391-H8 | 2016-05-23 | 2016-05-31 | 6 |  | 6 | 2016-06-07 |  | -30344 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-12 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2017-05-01 | Online | Private
NSTAR | Hyannis | 2151406 | 2601 | 136.5 | PV | 4-63-521 | 2016-05-12 | 2016-05-31 | 13 |  | 13 | 2016-06-09 |  | -30346 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-15 | 2016-08-08 | [6 empty] | 0 |  | 0 |  |  | 2017-06-13 | Online
NSTAR | Boston | 2151408 | 2215 | 367 | PV | 350-H5 | 2016-06-03 | 2016-06-04 | -1 | 0 | 0 | 2016-06-09 | 2016-06-21 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-01-12 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Natick | 2151948 | 1760 | 75 | Natural Gas | 433-H7 | 2016-06-07 | 2016-06-09 | 2 | 38 | -36 | 2016-06-14 |  | -30349 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-29 | 2016-01-03 | 2017-01-17 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-02-23 | Online | Private |  | 2016-06-28
NSTAR | Cotuit | 2152205 | 2635 | 1992 | PV | 4-88-880 | 2016-06-08 | 2016-06-13 | 3 | 0 | 3 | 2016-06-14 |  | -30349 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-09-26 |  | -30423 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-28 |  | 2017-01-18 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-06-17
NSTAR | Bourne | 2152371 | 2532 | 566.1 | PV | 3-89-925 | 2016-03-04 | 2016-05-18 | 53 |  | 53 | 2016-06-10 |  | -30347 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-30 | 2016-09-01 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Falmouth | 2152612 | 2536 | 16.15 | PV | 4-98A-462 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Eastham | 2152613 | 2642 | 15.4 | PV | 4-94A-648 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2152922 | 1801 | 49.14 | PV | 533-H7 | 2016-05-10 | 2016-06-02 | 17 |  | 17 | 2016-06-15 |  | -30350 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2016-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online | PRIVATE
NSTAR | Orleans | 2152923 | 2653 | 300 | PV | 4-83-952 | 2016-06-13 | 2016-06-15 | 2 | 0 | 2 | 2016-06-20 | 2016-06-24 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-06-27 |  | 2017-01-23 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-07-18 | Online | Private
NSTAR | Cotuit | 2153294 | 2635 | 1992 | PV | 4-88-880 | 2016-06-15 | 2016-06-16 | 1 | 0 | 1 | 2016-06-27 |  | -30358 | 37 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 2016-09-26 |  | -30423 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-26 | 2016-09-28 | 2017-01-25 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-06-29
NSTAR | Newton | 2154090 | 2460 | 75 | PV | 467-H5 | 2016-06-20 | 2016-06-21 | 1 | 0 | 1 | 2016-06-27 | 2016-06-29 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-27 |  | 2017-01-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private
NSTAR | Watertown | 2154091 | 2472 | 432 | PV | 467-H6 | 2016-06-20 | 2016-06-21 | 1 | 0 | 1 | 2016-06-28 | 2016-08-03 | 26 | 22 | 4 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-08-24 | 2017-01-30 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-06-23 | Online | Private
NSTAR | Framingham | 2154503 | 1701 | 105 | PV | 433-H3 | 2016-06-22 | 2016-06-23 | 1 | 2 | -1 | 2016-06-28 | 2016-07-05 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-05 |  | 2017-02-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Framingham | 2154699 | 1701 | 105 | PV | 433-H3 | 2016-06-23 | 2016-06-24 | 1 | 2 | -1 | 2016-07-05 | 2016-07-05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-05 |  | 2017-02-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Dedham | 2154886 | 2026 | 189.2 | PV | 20-H5 | 2016-06-24 | 2016-06-27 | 1 | 0 | 1 | 2016-07-04 | 2016-07-26 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-03 | 2016-08-03 | 2017-02-03 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-30 | Online | Private
NSTAR | Sandwich | 2155321 | 2537 | 468 | PV | 4-81B-81B | 2016-06-28 | 2016-06-29 | 1 | 0 | 1 | 2016-07-04 |  | -30363 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 2016-09-08 | 30410 | 0 | 30410 |  |  | 0 | 0 | 0 | 2016-12-19 |  | 2017-02-07 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Sent ISA | Private
NSTAR | Brighton | 2155327 | 2135 | 75 | PV | 315-H11 | 2016-06-28 | 2016-06-29 | 1 | 0 | 1 | 2016-07-04 | 2016-07-25 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 |  | 2017-02-07 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-07 | Online | Private
NSTAR | Dennis | 2155620 | 2638 | 89.9 | PV | 4-92B-92B | 2016-05-13 | 2016-06-08 | 18 |  | 18 | 2016-06-30 |  | -30361 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-28 | 2016-10-03 | [6 empty] | 0 |  | 0 |  |  |  | isa received/signed
NSTAR | Sandwich | 2155836 | 2563 | 109.2 | PV | 4-81B-443 | 2016-06-09 | 2016-06-22 | 9 |  | 9 | 2016-07-01 |  | -30362 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2156003 | 2122 | 170 | PV | 496-H1XY | 2016-07-01 | 2016-07-05 | 2 | 0 | 2 | 2016-07-06 | 2016-07-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-07-25 | 2016-07-26 | 2016-09-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-02-01 | Online | Private
NSTAR | Chatham | 2156004 | 2650 | 21.44 | PV | 4-95B-612 | 2016-06-10 | 2016-06-13 | 1 |  | 1 | 2016-07-05 |  | -30364 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-07-13 | 2016-07-25 | [6 empty] | 0 |  | 0 |  |  | 2016-10-19 | Online | PRIVATE
NSTAR | Needham | 2156671 | 2494 | 90 | PV | 148-H7 | 2016-07-05 | 2016-07-06 | 1 | 0 | 1 | 2016-07-14 | 2016-08-05 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-23 | 2016-08-25 | 2017-02-13 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-03-07 | Online | Private
NSTAR | North Dartmouth | 2157001 | 2747 | 16.25 | PV | 2-541-541 | 2016-06-01 | 2016-06-20 | 13 |  | 13 | 2016-07-07 |  | -30366 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-05 | 2016-09-12 | [6 empty] | 0 |  | 0 |  |  | 2016-09-26 | Online | PRIVATE
NSTAR | Waltham | 2157007 | 2453 | 180 | PV | 33-H3 | 2016-07-06 | 2016-07-07 | 1 | 0 | 1 | 2016-07-14 |  | -30371 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 | 2016-10-21 | 2017-02-14 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Online | Private |  | 2016-08-04
NSTAR | Dartmouth | 2157191 | 2747 | 150 | Natural Gas | 2-541-542 | 2016-07-07 | 2016-07-11 | 2 | 0 | 2 | 2016-07-14 |  | -30371 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-14 | 2016-09-22 | 2017-02-15 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-01-31 | Online | Gov't
NSTAR | Dover | 2157192 | 2030 | 21 | PV | 456-H5 | 2016-07-07 | 2016-07-11 | 2 | 0 | 2 | 2016-07-15 | 2016-08-04 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-10 |  | 2017-02-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2016-12-02 | Online | Private
NSTAR | Woburn | 2157251 | 1801 | 499 | PV | 375-H3 | 2016-07-08 | 2016-07-11 | 1 | 0 | 1 | 2016-07-13 |  | -30370 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-16 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  |  | Private
NSTAR | South Boston | 2157900 | 2210 | 456 | PV | 385-H18 | 2016-06-09 | 2016-06-22 | 9 | 0 | 9 | 2016-07-14 |  | -30371 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-22 | 2016-09-23 | 2017-02-21 | No | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-07-20 | Online | Private
NSTAR | Acusnet | 2157905 | 2743 | 144.4 | PV | 2-231-231 | 2016-05-27 | 2016-06-27 | 21 |  | 21 | 2016-07-14 |  | -30371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2158112 | 2648 | 50.4 | PV | 4-88-478 | 2016-05-24 | 2016-06-28 | 25 |  | 25 | 2016-07-14 |  | -30371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-26 | [7 empty] | 0 |  | 0 |  |  |  | isa sent | PRIVATE
NSTAR | South Boston | 2158329 | 2127 | 486.2 | PV | 385-H17 | 2016-05-11 | 2016-05-16 | 3 |  | 3 | 2016-06-08 |  | -30345 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-08-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2158504 | 2330 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-24 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | South Boston | 2158505 | 2127 | 500 | PV | 106-H1 | 2016-07-15 | 2016-07-25 | 6 | 0 | 6 | 2016-07-25 |  | -30378 | 16 | 0 | 2016-08-31 |  | -30405 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-10-18 | 2016-10-21 | 2017-02-24 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | South Boston | 2158507 | 2127 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-24 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Carver | 2158976 | 2330 | - | PV | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  | 2018-04-30 | 2018-04-30 | Online | Private
NSTAR | Acton | 2158995 | 1720 | 294 | PV | 416-H4 | 2016-07-18 | 2016-07-25 | 5 | 0 | 5 | 2016-07-28 |  | -30381 | 14 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-02-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-08-02
NSTAR | Milton | 2158997 | 2186 | 30 | PV | 362-1209H1 | 2016-07-18 | 2016-07-20 | 2 | 0 | 2 | 2016-07-28 | 2016-08-09 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-15 |  | 2017-02-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Awaiting Completion Docs | Private
NSTAR | Weston | 2159240 | 2493 | 20 | PV | 282-H1 | 2016-07-19 | 2016-07-20 | 1 | 0 | 1 | 2016-07-28 |  | -30381 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-01-30 |  | 2017-02-28 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-08-10
NSTAR | Framingham | 2159493 | 2472 | 166.5 | PV | 467-H2 | 2016-06-29 | 2016-07-12 | 9 |  | 9 | 2016-07-25 |  | -30378 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plympton | 2159738 | 2367 | 1000 | PV | TBD | 2016-07-21 |  | -30376 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-03-02 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | West Roxbury | 2160263 | 2132 | 250 | Natural Gas | 374-2215 | 2016-07-25 | 2016-07-27 | 2 | 0 | 2 | 2016-08-01 |  | -30383 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-18 | 2016-09-09 | 2017-03-06 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | ISA Received/Signed | Gov't
NSTAR | Westwood | 2160448 | 2090 | 126.5 | PV | 456-h1 | 2016-07-14 | 2016-07-18 | 2 |  | 2 | 2016-07-27 |  | -30380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-02 | 2016-09-14 | [6 empty] | 0 |  | 0 |  |  | 2017-04-27 | Online
NSTAR | Mattapoisett | 2160656 | 2739 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-07-27 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Hatchville | 2160717 | 2536 | 98 | PV | 4-98A-98A | 2016-07-27 | 2016-08-30 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Maynard | 2160866 | 1754 | 576 | PV | 416-H3 | 2016-07-28 | 2016-08-01 | 2 | 0 | 2 | 2016-08-05 |  | -30387 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-03-09 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-08-11
NSTAR | Westwood | 2161143 | 2090 | 161 | PV | 469-H2 | 2016-07-29 | 2016-08-01 | 1 | 0 | 1 | 2016-08-05 |  | -30387 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-16 | 2016-09-23 | 2017-03-10 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-04-27 | Online | Private
NSTAR | Hopkinton | 2161144 | 1748 | 252 | PV | 126-H1 | 2016-07-29 | 2016-08-02 | 2 | 0 | 2 | 2016-08-05 | 2016-08-19 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-24 | 2016-09-12 | 2017-03-10 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-02-08 | Online | Private |  | 2016-08-22
NSTAR | Westwood | 2161690 | 2090 | 164 | PV | 456-H4 | 2016-07-16 | 2016-08-09 | 17 | 0 | 17 | 2016-08-03 |  | -30385 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-02 | 2016-09-14 | 2017-03-14 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-01-30 | Online | Private
NSTAR | Waltham | 2162221 | 2452 | 380 | PV | 277-1367 | 2016-08-03 | 2016-08-09 | 4 | 0 | 4 | 2016-08-11 |  | -30391 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-19 | 2016-09-29 | 2017-03-15 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private |  | 2016-08-12
NSTAR | East Boston | 2162392 | 2128 | 72 | PV | 488-H8 | 2016-08-04 | 2016-08-09 | 3 | 0 | 3 | 2016-08-11 |  | -30391 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-08-16 |  | 2017-03-16 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Ashland | 2162591 | 1721 | 148.9 | PV | 274-H1 | 2016-07-18 | 2016-07-25 | 5 |  | 5 | 2016-08-09 |  | -30389 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-08 | [7 empty] | 0 |  | 0
NSTAR | Bellingham | 2164625 | 2019 | 497.5 | PV | 65-H4 | 2016-06-10 | 2016-07-25 | 31 |  | 31 | 2016-08-22 |  | -30398 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-01-12 | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-19 | 2018-07-28 | [6 empty] | 0 |  | 0 |  |  | 2018-12-18
NSTAR | Mattapoisett | 2164627 | 2739 | 16.92 | PV | 2-301-301 | 2016-07-05 | 2016-07-27 | 16 |  | 16 | 2016-08-22 |  | -30398 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | New Bedford | 2164917 | 2745 | 272 | PV | 2-103-103 | 2016-07-22 | 2016-07-27 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online | Private
NSTAR | Westwood | 2165129 | 2090 | 138 | PV | 456-H4 | 2016-07-14 | 2016-07-28 | 10 | 0 | 10 | 2016-08-22 |  | -30398 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2016-09-22 | 2016-09-29 | 2017-03-31 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  | 2017-04-25 | Online | Gov't
NSTAR | Roxbury | 2165132 | 2119 | 57.6 | PV | 106-H5 | 2016-07-11 | 2016-07-28 | 13 |  | 13 | 2016-08-22 |  | -30398 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Roxbury | 2165395 | 2119 | 115.2 | PV | 106-H4 | 2016-07-13 | 2016-08-01 | 13 |  | 13 | 2016-08-24 |  | -30400 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-09 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2165396 | 2648 | 19.6 | PV | 4-88-485 | 2016-07-26 | 2016-08-01 | 4 |  | 4 | 2016-08-24 |  | -30400 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | [7 empty] | 0 |  | 0 |  |  | 2017-01-17 | Online | PRIVATE
NSTAR | Falmouth | 2165668 | 2536 | 90 | PV | 4-98A-98A | 2016-07-29 | 2016-08-09 | 7 |  | 7 | 2016-08-24 |  | -30400 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | 2016-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-02-08 | Online | PRIVATE | Y
NSTAR | Framingham | 2165880 | 1701 | 30 | PV | 4-98A-98A | 2016-07-22 | 2016-08-09 | 12 |  | 12 | 2016-08-29 |  | -30403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-13 | [7 empty] | 0 |  | 0 |  |  | 2017-01-25 | Online | PRIVATE
NSTAR | Westwood | 2165893 | 2090 | 266.4 | PV | 456-H1 | 2016-08-05 | 2016-08-12 | 5 |  | 5 | 2016-08-26 |  | -30402 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-19 | 2017-10-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-21 | Online | PRIVATE | Y
NSTAR | Hyannis | 2166109 | 2601 | 20 | PV | 4-63-63 | 2016-07-13 | 2016-08-15 | 23 |  | 23 | 2016-08-29 |  | -30403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-26 | [7 empty] | 0 |  | 0 |  |  |  | isa sent | PRIVATE
NSTAR | Falmouth | 2166111 | 2536 | 100.8 | PV | 4-98A-98A | 2016-07-26 | 2016-08-29 | 24 |  | 24 | 2016-08-29 |  | -30403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | 2017-11-28 | [6 empty] | 0 |  | 0 |  |  | 2017-04-28 | Online
NSTAR | Waltham | 2166275 | 2453 | 60 | PV | 282-H4 | 2016-08-09 | 2016-08-15 | 4 |  | 4 | 2016-08-30 |  | -30404 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-26 | 2016-09-26 | [6 empty] | 0 |  | 0 |  |  | 2017-05-19 | Online | PRIVATE
NSTAR | Waltham | 2166276 | 2453 | 50 | PV | 282-H9 | 2016-08-09 | 2016-08-16 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-06-16 | Online | PRIVATE
NSTAR | Dedham | 2166557 | 2026 | 525 | PV | 344-1413H1 | 2016-07-20 | 2016-08-22 | 23 |  | 23 | 2016-08-30 |  | -30404 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-20 |  | -30441 |  | 0 |  |  | 0 |  | 0 | 2016-12-29 | [7 empty] | 0 |  | 0 |  |  |  | isa sent
NSTAR | Dorchester | 2166559 | 2124 | 20 | PV | 511-1497H3 | 2016-08-11 | 2016-08-22 | 7 |  | 7 | 2016-08-22 |  | -30398 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-22 | 2016-09-23 | [6 empty] | 0 |  | 0 |  |  | 2017-06-02 | Online | PRIVATE
NSTAR | Cambridge | 2166793 | 2140 | 22.8 | PV | 825-27 | 2016-08-03 | 2016-08-04 | 1 |  | 1 | 2016-09-01 |  | -30406 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-11-21 | [6 empty] | 0 |  | 0 |  |  | 2017-01-03 | Online | PRIVATE
NSTAR | Newton | 2166797 | 2458 | 150 | PV | 467-H14 | 2016-08-12 | 2016-08-22 | 6 |  | 6 | 2016-09-02 |  | -30407 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2016-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-03-29 | Online | PRIVATE
NSTAR | Newton | 2166988 | 2466 | 57.5 | PV | 292-H7 | 2016-08-18 | 2016-08-22 | 2 |  | 2 | 2016-09-02 |  | -30407 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-20 | 2017-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-03-01 | Online | PRIVATE
NSTAR | Cambridge | 2166994 | 2140 | 115.2 | PV | 825-26 | 2016-08-16 | 2016-08-24 | 6 |  | 6 | 2016-09-02 |  | -30407 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2167216 | 2453 | 73.3 | PV | 33-H1 | 2016-08-09 | 2016-08-16 | 5 |  | 5 | 2016-09-02 |  | -30407 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-21 | 2016-11-03 | [6 empty] | 0 |  | 0 |  |  | 2017-05-19 | Online
NSTAR | Allston | 2168053 | 2134 | 60 | PV | 329-H7 | 2016-08-17 | 2016-08-22 | 3 |  | 3 | 2016-09-07 |  | -30410 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-27 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-02 | Online | PRIVATE
NSTAR | Boston | 2168059 | 2118 | 75 | PV | 323-06 | 2016-08-12 | 2016-08-22 | 6 |  | 6 | 2016-09-07 |  | -30410 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | 2017-02-09 | [6 empty] | 0 |  | 0 |  |  | 2017-08-30 | Online
NSTAR | Bedford | 2168512 | 1731 | 2805 | PV | 320-H6 | 2016-09-01 | 2016-09-07 | 4 |  | 4 | 2016-09-12 |  | -30413 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2168736 | 1760 | 21.9 | PV | 240-H2 | 2016-08-11 | 2016-08-22 | 7 |  | 7 | 2016-09-12 |  | -30413 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-13 | 2016-09-14 | [6 empty] | 0 |  | 0 |  |  | 2016-11-29 | Online | PRIVATE | Y
NSTAR | Sudbury | 2168989 | 1776 | 20 | PV | 342-H7 | 2016-08-16 | 2016-08-24 | 6 |  | 6 | 2016-09-13 |  | -30414 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | [7 empty] | 0 |  | 0 |  |  | 2017-01-04 | Online | PRIVATE
NSTAR | North Dartmouth | 2168995 | 2747 | 40 | PV | 2-541-542 | 2016-07-28 | 2016-08-29 | 22 |  | 22 | 2016-09-13 |  | -30414 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-09-30 | 2016-10-03 | [6 empty] | 0 |  | 0 |  |  | 2017-04-14 | Online | PRIVATE | Y
NSTAR | Brewster | 2169301 | 2631 | 19.25 | PV | 4-89B-576 | 2016-08-18 | 2016-08-24 | 4 |  | 4 | 2016-09-14 |  | -30415 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Somerville | 2169544 | 2143 | 45 | PV | 286-1322H1 | 2016-07-21 | 2016-09-09 | 36 |  | 36 | 2016-09-15 |  | -30416 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | [7 empty] | 0 |  | 0 |  |  | 2019-02-05 | isa sent | PRIVATE
NSTAR | Somerville | 2169546 | 2143 | 105 | PV | 286-1322H1 | 2016-07-21 | 2016-09-09 | 36 |  | 36 | 2016-09-15 |  | -30416 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-09 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-18 | Online
NSTAR | Cambridge | 2169551 | 2139 | 57.6 | PV | 814-13 | 2016-09-02 | 2016-09-07 | 3 |  | 3 | 2016-09-15 |  | -30416 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-10-13 | [6 empty] | 0 |  | 0 |  |  | 2017-02-06 | Online | PRIVATE
NSTAR | Boston | 2169723 | 2188 | 72 | PV | 106-H4 | 2016-08-17 | 2016-08-26 | 7 |  | 7 | 2016-09-16 |  | -30417 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2017-11-18 | [6 empty] | 0 |  | 0 |  |  | 2017-11-09 | Online
NSTAR | Brighton | 2169751 | 2135 | 64 | PV | 467-H12 | 2016-08-17 | 2016-08-26 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2169753 | 2128 | 167 | PV | 108-196H1 | 2016-08-17 | 2016-08-26 | 7 |  | 7 | 2016-09-16 |  | -30417 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | [7 empty] | 0 |  | 0 |  |  | 2017-09-26 | Online
NSTAR | Stoneham | 2170420 | 2180 | 84 | PV | 375-H7 | 2016-08-17 | 2016-08-26 | 7 |  | 7 | 2016-09-20 |  | -30419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-23 | 2017-12-06 | [6 empty] | 0 |  | 0 |  |  | 2017-09-14 | Online
NSTAR | Hopkinton | 2170421 | 1748 | 22.7 | PV | 126-H1 | 2016-08-29 | 2016-08-31 | 2 |  | 2 | 2016-09-20 |  | -30419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-01-05 | Online | PRIVATE
NSTAR | Rochester | 2170422 | 2770 | 21.9 | PV | 5-702-702 | 2016-08-25 | 2016-08-29 | 2 |  | 2 | 2016-09-20 |  | -30419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Plymouth | 2170423 | 2360 | 188.42 | PV | 3-14-911 | 2016-08-19 | 2016-08-30 | 7 |  | 7 | 2016-09-20 |  | -30419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-03 | [7 empty] | 0 |  | 0 |  |  | 2017-06-28 | Online
NSTAR | Hyannis | 2170678 | 2601 | 306.07 | PV | 4-84B-524 | 2016-08-19 | 2016-08-30 | 7 |  | 7 | 2016-09-21 |  | -30420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | [7 empty] | 0 |  | 0 |  |  | 2017-03-28 | Online | PRIVATE
NSTAR | Kingston | 2170680 | 2364 | 80 | PV | 3-26-902 | 2016-08-23 | 2016-09-01 | 7 |  | 7 | 2016-09-21 |  | -30420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-02-28 | Online | PRIVATE
NSTAR | Acton | 2170908 | 1720 | 21.9 | PV | 416-H4 | 2016-08-25 | 2016-09-01 | 5 |  | 5 | 2016-07-22 |  | -30377 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-21 | [7 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online | PRIVATE
NSTAR | Arlington | 2170910 | 2475 | 396 | PV | 211-H11 | 2016-08-22 | 2016-09-14 | 17 |  | 17 | 2016-09-22 |  | -30421 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-23 | 2016-12-02 | 7 |  | 7 |  |  | 0 |  | 0 | 2017-02-24 | [7 empty] | 0 |  | 0 |  |  | 2017-08-04 | Online | PRIVATE
NSTAR | West Wareham | 2170912 | 2576 | 24.5 | PV | 3-85-85 | 2016-08-30 | 2016-09-06 | 5 |  | 5 | 2016-09-22 |  | -30421 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Framingham | 2171111 | 1701 | 1760 | PV | 455-H7 | 2016-07-29 | 2016-09-07 | 28 |  | 28 | 2016-09-23 |  | -30422 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-22 | 2017-02-13 | [6 empty] | 0 |  | 0 |  |  | 2018-04-30 | Online
NSTAR | Acton | 2171112 | 1720 | 39.1 | PV | 416-H5 | 2016-08-22 | 2016-09-06 | 11 |  | 11 | 2016-09-23 |  | -30422 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Marion | 2171654 | 2738 | 15.2 | PV | 3-85-85 | 2016-09-01 | 2016-09-07 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-12-28 | Online | PRIVATE
NSTAR | Woburn | 2171655 | 1888 | 466.2 | PV | 375-H3 | 2016-06-01 | 2016-09-07 | 70 |  | 70 | 2016-09-28 |  | -30425 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-15 |  | -30545 |  | 0 |  |  | 0 |  | 0 | 2017-08-18 | 2017-08-23 | [6 empty] | 0 |  | 0 |  |  | 2018-02-26 | Online
NSTAR | Hopkinton | 2171656 | 1748 | 433 | PV | 126-H1 | 2016-09-01 | 2016-09-06 | 3 |  | 3 | 2016-09-29 |  | -30426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-17 | 2016-11-17 | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-17 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  |  | WO Request
NSTAR | Acton | 2171989 | 1720 | 40 | PV | 416-H4 | 2016-09-07 | 2016-09-07 | 0 |  | 0 | 2016-09-29 |  | -30426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Acton | 2171992 | 1720 | 52.9 | PV | 416-H4 | 2016-09-07 | 2016-09-07 | 0 |  | 0 | 2016-09-29 |  | -30426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Truro | 2172198 | 2666 | 18.9 | PV | 4-96-674 | 2016-09-07 | 2016-09-09 | 2 |  | 2 | 2016-09-29 |  | -30426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-12 | 2016-11-03 | [6 empty] | 0 |  | 0 |  |  | 2017-01-11 | Online | PRIVATE
NSTAR | East Falmouth | 2172199 | 2536 | 48 | PV | 4-98A-98A | 2016-07-15 | 2016-09-14 | 43 |  | 43 | 2016-09-29 |  | -30426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Acton | 2172398 | 1720 | 101 | PV | 416-H9 | 2016-08-18 | 2016-09-07 | 14 |  | 14 | 2016-10-03 |  | -30428 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Cambridge | 2172403 | 2140 | 66.6 | PV | 824-28 | 2016-09-09 | 2016-09-14 | 3 |  | 3 | 2016-10-03 |  | -30428 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-02 | 2016-11-07 | [6 empty] | 0 |  | 0 |  |  | 2017-06-26 | Online
NSTAR | Orleans | 2172699 | 2653 | 33.5 | PV | 4-83-952 | 2016-09-06 | 2016-09-14 | 6 |  | 6 | 2016-10-30 |  | -30447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-17 | [7 empty] | 0 |  | 0 |  |  | 2017-05-18 | Online | PRIVATE
NSTAR | East Boston | 2173575 | 2128 | 75 | CHP | 488-H8 | 2016-09-12 | 2016-10-04 | 16 |  | 16 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | 2016-12-06 | [6 empty] | 0 |  | 0 |  |  | 2017-02-10 | Online | NO EXPORT
NSTAR | Buzzards Bay | 2173585 | 2532 | 100 | PV | 3-88-2J4 | 2016-09-08 | 2016-09-14 | 4 |  | 4 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Barnstable | 2173782 | 2630 | 50 | PV | 4-84B-524 | 2016-08-29 | 2016-09-09 | 9 |  | 9 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-03 | 2017-01-04 | [6 empty] | 0 |  | 0 |  |  | 2017-03-10 | Online | PRIVATE
NSTAR | Arlington | 2173991 | 2476 | 34.5 | PV | 211-H3 | 2016-08-25 | 2016-09-14 | 14 |  | 14 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Natick | 2173993 | 1760 | 126 | PV | 240-H2 | 2016-09-09 | 2016-09-14 | 3 |  | 3 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-24 | [7 empty] | 0 |  | 0 |  |  |  | ISA SENT
NSTAR | West Tisbury | 2173995 | 2575 | 22.8 | PV | 4-97-97 | 2016-09-12 | 2016-09-15 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-12-16 | Online | PRIVATE
NSTAR | West Tisbury | 2173999 | 2575 | 22.8 | PV | 4-97-226 | 2016-09-12 | 2016-09-15 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-11 | Online | PRIVATE
NSTAR | Framingham | 2174568 | 1701 | 165 | PV | 433-H3 | 2016-09-09 | 2016-09-15 | 4 |  | 4 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-27 | [7 empty] | 0 |  | 0 |  |  | 2017-06-28 | Online
NSTAR | Walpole | 2174571 | 2081 | 135 | PV | 2611 | 2016-09-08 | 2016-09-14 | 4 |  | 4 | 2016-10-12 |  | -30435 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2016-11-18 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marion | 2174858 | 2738 | 27.72 | PV | 2-304-304 | 2016-09-08 | 2016-09-15 | 5 |  | 5 | 2016-10-14 |  | -30437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-04-11 | Online | PRIVATE
NSTAR | Framingham | 2175097 | 1702 | 180 | PV | 240-H4 | 2016-09-28 | 2016-10-03 | 3 |  | 3 | 2016-10-14 |  | -30437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2175313 | 2452 | 18.4 | PV | 282-H7 | 2016-09-15 | 2016-09-19 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Assonett | 2175318 | 2702 | 16.7 | PV | 2-605-605 | 2016-09-13 | 2016-09-17 | 3 |  | 3 | 2016-10-17 |  | -30438 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | New Bedford | 2175669 | 2746 | 180 | PV | 2-24-11 | 2016-09-16 | 2016-09-19 | 1 |  | 1 | 2016-10-18 |  | -30439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-10-25 | 2017-03-21 | [6 empty] | 0 |  | 0 |  |  | 2017-04-11 | Online
NSTAR | Acusnet | 2176279 | 2743 | 15.36 | PV | 2-241-241 | 2016-09-20 | 2016-09-20 | 0 |  | 0 | 2016-10-21 |  | -30442 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-08 | 2016-12-09 | [6 empty] | 0 |  | 0 |  |  | 2017-03-31 | Online | PRIVATE
NSTAR | Stoneham | 2176517 | 2180 | - | PV | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2016-10-20 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Holliston | 2176549 | 1746 | 36 | PV | 274-H3 | 2016-09-09 | 2016-09-23 | 10 |  | 10 | 2016-10-21 |  | -30442 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | [7 empty] | 0 |  | 0 |  |  | 2017-05-16 | Online | PRIVATE
NSTAR | Harwich | 2176727 | 2645 | 30 | PV | 4-89A-556 | 2016-09-19 | 2016-09-21 | 2 |  | 2 | 2016-10-24 |  | -30443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-01 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-09-08 | Online | PRIVATE
NSTAR | Needham | 2176734 | 2494 | 866 | PV | 148-H6 | 2016-07-13 | 2016-09-23 | 52 |  | 52 | 2016-10-24 |  | -30443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Somerville | 2177085 | 2145 | 210 | PV | 210-1N81H1 | 2016-08-19 | 2016-09-23 | 25 |  | 25 | 2016-10-25 |  | -30444 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2177087 | 2360 | 32.35 | PV | 3-13-936 | 2016-09-20 | 2016-09-26 | 4 |  | 4 | 2016-10-25 |  | -30444 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-15 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-04-05 | Online | Private | Y
NSTAR | Brookline | 2177319 | 2446 | 16.5 | PV | 350-H12 | 2016-09-15 | 2016-09-26 | 7 |  | 7 | 2016-10-26 |  | -30445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-06 | 2016-12-07 | [6 empty] | 0 |  | 0 |  |  | 2017-04-19 | Online | PRIVATE
NSTAR | Lexington | 2177534 | 2420 | 79.2 | PV | 391-H11 | 2016-09-21 | 2016-09-28 | 5 |  | 5 | 2016-10-27 |  | -30446 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Oak Bluffs | 2177535 | 2557 | 21.15 | PV | 4-99-224 | 2016-08-25 | 2016-10-19 | 39 |  | 39 | 2016-11-02 |  | -30450 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2016-11-18 | [6 empty] | 0 |  | 0 |  |  | 2017-02-03 | Online | PRIVATE
NSTAR | Medway | 2177856 | 2053 | 180 | PV | 65-H3 | 2016-09-30 | 2016-10-26 | 18 |  | 18 | 2016-10-28 |  | -30447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Edgartown | 2178416 | 2539 | 21.38 | PV | 4-75-75 | 2016-06-15 | 2016-10-19 | 90 |  | 90 | 2016-11-02 |  | -30450 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-16 | 2016-11-28 | [6 empty] | 0 |  | 0 |  |  | 2017-01-24 | Online | PRIVATE
NSTAR | North Dartmouth | 2178419 | 2747 | 499.5 | PV | 2-533-530 | 2016-09-30 | 2016-10-04 | 2 |  | 2 | 2016-11-01 |  | -30449 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-29 | 2016-12-02 | [6 empty] | 0 |  | 0 |  |  | 2017-05-17 | Online
NSTAR | Natick | 2178429 | 1760 | 458 | PV | TBD | 2016-10-31 |  | -30448 | 0 | 0 | 2016-11-04 | 2017-08-17 | 204 | 188 | 16 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-06-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Gov't
NSTAR | Somerville | 2178439 | 2143 | 30.24 | PV | 250-1N90H2 | 2016-09-20 | 2016-09-29 | 7 |  | 7 | 2016-11-01 |  | -30449 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-05-17 | Online | PRIVATE | Y
NSTAR | Yarmouth | 2178449 | 2664 | 127.8 | PV | 4-92a-562 | 2016-09-26 | 2016-10-03 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Teaticket | 2178798 | 2536 | 228 | PV | 4-76-437 | 2016-09-26 | 2016-10-03 | 5 |  | 5 | 2016-11-02 |  | -30450 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-01 | [7 empty] | 0 |  | 0 |  |  | 2017-12-01 | Online
NSTAR | New Bedford | 2179799 | 2745 | 208 | PV | 2-82-82 | 2016-10-09 | 2016-10-12 | 3 |  | 3 | 2016-11-03 |  | -30451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-01 | 2016-12-22 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online | Private
NSTAR | Falmouth | 2179819 | 2540 | 32.4 | PV | 4-72-433 | 2016-09-26 | 2016-10-03 | 5 |  | 5 | 2016-11-03 |  | -30451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Falmouth | 2180040 | 2540 | 16 | PV | 4-72-433 | 2016-09-27 | 2016-10-03 | 4 |  | 4 | 2016-11-07 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-03 | 2017-01-05 | [6 empty] | 0 |  | 0 |  |  | 2017-03-07 | Online | PRIVATE
NSTAR | Waltham | 2180042 | 2453 | 30 | PV | 467-H5 | 2016-09-30 | 2016-10-04 | 2 |  | 2 | 2016-11-07 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-28 | 2016-12-13 | [6 empty] | 0 |  | 0 |  |  | 2017-09-08 | Online | PRIVATE
NSTAR | Bourne | 2180239 | 2542 | 7950 | PV | 4-98A-98A | 2016-10-04 | 2016-10-12 | 6 |  | 6 | 2016-11-07 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-05-11 | -46 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2180242 | 1760 | 252 | PV | 240-H1 | 2016-09-29 | 2016-10-04 | 3 |  | 3 | 2016-11-07 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-03 | 2017-04-19 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2180244 | 1730 | 5198 | CHP | 319-1377 | 2016-09-29 | 2016-10-04 | 3 |  | 3 | 2016-11-07 |  | -30453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medfield | 2180484 | 2052 | 70 | PV | 146-H2 | 2016-11-07 | 2016-11-07 | 0 |  | 0 | 2016-11-09 |  | -30455 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-01-19 | Online | GOV'T
NSTAR | North Dartmouth | 2180485 | 2748 | 39.6 | PV | 2-524-524 | 2016-09-22 | 2016-10-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-08 | Waiting for ISA | PRIVATE
NSTAR | Framingham | 2180488 | 1702 | 50 | PV | 2408 | 2016-09-19 | 2016-10-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-01-17 | [6 empty] | 0 |  | 0 |  |  | 2017-03-20 | Online | PRIVATE
NSTAR | Brookline | 2180952 | 2455 | 60 | PV | 506-07 | 2016-09-30 | 2016-10-12 | 8 |  | 8 | 2016-11-30 |  | -30470 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-16 | 2016-01-03 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Walpole | 2180956 | 2081 | 28.8 | PV | 146-H3 | 2016-10-05 | 2016-10-17 | 8 |  | 8 | 2016-11-10 |  | -30456 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2017-12-22 | [6 empty] | 0 |  | 0 |  |  | 2017-02-24 | Online | PRIVATE
NSTAR | Framingham | 2181138 | 1702 | 51 | PV | 278-H1 | 2016-09-19 | 2016-10-12 | 17 |  | 17 | 2016-11-14 |  | -30458 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-04-10 | [6 empty] | 0 |  | 0 |  |  | 2017-09-20 | Online | PRIVATE
NSTAR | Holliston | 2181140 | 1746 | 42 | PV | 274-H3 | 2016-10-13 | 2016-10-21 | 6 | 7 | -1 | 2016-11-14 |  | -30458 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-09 | [7 empty] | 0 |  | 0 |  |  | 2017-08-10 | Online | PRIVATE
NSTAR | Bedford | 2181646 | 1731 | 430 | PV | 319-1378 | 2016-10-11 | 2016-10-18 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-22 | Online
NSTAR | Holliston | 2181649 | 1746 | 32.5 | PV | 130-H1 | 2016-10-06 | 2016-10-19 | 9 |  | 9 | 2016-11-16 |  | -30460 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-11-29 | 2016-12-07 | [6 empty] | 0 |  | 0 |  |  | 2017-03-13 | Online | PRIVATE
NSTAR | Dedham | 2181650 | 2026 | 150 | CHP | 20-H5 | 2016-10-14 | 2016-10-19 | 3 |  | 3 | 2016-11-16 |  | -30460 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-07-18 | Online
NSTAR | South Dartmouth | 2181937 | 2748 | 57.6 | PV | 2-2-505 | 2016-10-04 | 2016-10-20 | 12 |  | 12 | 2016-11-17 |  | -30461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-06 | 2016-12-08 | [6 empty] | 0 |  | 0 |  |  | 2017-02-21 | Online | PRIVATE
NSTAR | Needham | 2181939 | 2494 | 64.8 | PV | 148-H1 | 2016-10-17 | 2016-10-21 | 4 |  | 4 | 2016-11-17 |  | -30461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-07 | 2016-12-15 | [6 empty] | 0 |  | 0
NSTAR | Brookline | 2181940 | 2445 | 89 | PV | 369-07 | 2016-10-20 | 2016-10-25 | 3 |  | 3 | 2016-11-17 |  | -30461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sherborn | 2181941 | 1770 | 35.6 | PV | 274-H2 | 2016-10-11 | 2016-10-17 | 4 |  | 4 | 2016-11-17 |  | -30461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Weston | 2182191 | 2493 | 18 | PV | 433-H6 | 2016-10-12 | 2016-10-18 | 4 |  | 4 | 2016-11-18 |  | -30462 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-11 | [6 empty] | 0 |  | 0 |  |  | 2017-04-24 | Online | PRIVATE
NSTAR | Hyannis | 2182194 | 2601 | 19 | PV | 4-63-905 | 2016-10-12 | 2016-10-18 | 4 |  | 4 | 2016-11-18 |  | -30462 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Westwood | 2182386 | 2090 | 480 | PV | 469-H3 | 2016-09-15 | 2016-10-18 | 23 |  | 23 | 2016-11-21 |  | -30463 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | [7 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
NSTAR | Lexington | 2182387 | 2420 | 20 | PV | 391-H11 | 2016-05-23 | 2016-10-18 | 106 |  | 106 | 2016-11-21 |  | -30463 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-15 | [6 empty] | 0 |  | 0 |  |  |  | isa sent | PRIVATE
NSTAR | Canton | 2182736 | 2021 | 980 | PV | 470-H7 | 2014-06-17 | 2014-06-17 | 0 |  | 0 | 2017-06-30 |  | -30622 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2014-10-20 | 2014-10-14 | -6 |  | 0 |  |  | 0 |  | 0 | 2016-09-09 | 2016-09-09 | [6 empty] | 0 |  | 0
NSTAR | Brookline | 2182805 | 2445 | 28 | PV | 350-H8 | 2016-10-21 | 2016-10-24 | 1 |  | 1 | 2016-11-22 |  | -30464 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-01-31 | [6 empty] | 0 |  | 0 |  |  | 2017-03-22 | Online | PRIVATE | Y
NSTAR | Framingham | 2182806 | 1702 | 648 | PV | 240-H6 | 2016-10-03 | 2016-11-18 | 34 |  | 34 | 2016-11-22 |  | -30464 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-02 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Arlington | 2182807 | 2474 | 18 | PV | 5905 | 2016-10-18 | 2016-10-24 | 4 |  | 4 | 2016-11-22 |  | -30464 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-01-06 | Online | PRIVATE
NSTAR | Acton | 2182998 | 1720 | 288 | PV | 416-H4 | 2016-10-21 | 2016-10-24 | 1 |  | 1 | 2016-11-23 |  | -30465 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-11 | [7 empty] | 0 |  | 0
NSTAR | Edgartown | 2183002 | 2539 | 21.75 | PV | 4-97-97 | 2016-10-21 | 2016-10-27 | 4 |  | 4 | 2016-11-28 |  | -30468 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-02 | 2016-12-16 | [6 empty] | 0 |  | 0 |  |  | 2017-01-04 | Online | PRIVATE
NSTAR | Natick | 2183182 | 1760 | 94.52 | PV | 240-H5 | 2016-10-18 | 2016-10-27 | 7 |  | 7 | 2016-11-28 |  | -30468 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-05-16 | Online
NSTAR | Framingham | 2183183 | 1702 | 220 | Battery | 455-H5 | 2016-10-28 | 2016-11-14 | 11 |  | 11 | 2016-11-28 |  | -30468 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2183910 | 1760 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-07-10 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | North Dartmouth | 2184042 | 2747 | 22 | PV | 2-523-523 | 2016-07-21 | 2016-10-28 | 71 |  | 71 | 2016-12-01 |  | -30471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-13 | 2017-02-21 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online | PRIVATE
NSTAR | Westwood | 2184045 | 2090 | 2310 | PV | 344-1412H1 | 2016-10-21 | 2016-10-31 | 6 |  | 6 | 2016-12-01 |  | -30471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-20 | 2017-05-18 | 20 |  | 20 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | 2184047 | 1776 | 17.4 | PV | 342-H7 | 2016-10-25 | 2016-10-31 | 4 |  | 4 | 2016-12-01 |  | -30471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  |  | isa sent | PRIVATE
NSTAR | Westwood | 2184048 | 2090 | 30.14 | PV | 148-H3 | 2016-10-24 | 2016-11-15 | 16 |  | 16 | 2016-12-01 |  | -30471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Canton | 2184049 | 2021 | 660 | PV | TBD | 2016-11-30 |  | -30470 | 0 | 0 | 2016-12-08 | 2016-12-23 | 11 | 8 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-07-10 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Natick | 2184402 | 1760 | 720 | PV | 433-H12 | 2016-10-17 | 2016-10-31 | 10 |  | 10 | 2016-12-02 |  | -30472 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-20 | [6 empty] | 0 |  | 0
NSTAR | Cambridge | 2184403 | 2140 | 2442 | PV | 828-1375 | 2016-10-24 | 2017-10-31 | 266 |  | 266 | 2016-12-02 |  | -30472 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 |  | -30559 |  | 0 |  |  | 0 |  | 0 | 2017-08-16 | 2017-09-14 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyde Park | 2184405 | 2136 | 510 | PV | TBD | 2016-12-01 |  | -30471 | 0 | 0 | 2016-12-06 | 2016-12-23 | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-07-11 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Newton | 2184406 | 2468 | 480 | PV | 292-H12 | 2016-10-24 | 2016-10-31 | 5 |  | 5 | 2016-12-02 |  | -30472 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-19 | 2017-06-19 |  |  |  | 87 |  |  | 0 |  | 0 |  |  | 2022-05-13 | Online
NSTAR | Dedham | 2184658 | 2026 | 66.6 | PV | 374-04 | 2016-10-31 | 2016-11-01 | 1 |  | 1 | 2016-12-05 |  | -30473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | [7 empty] | 0 |  | 0 |  |  | 2017-06-13 | Online
NSTAR | East Falmouth | 2187033 | 2536 | 16.7 | PV | 4-98A-98A | 2016-10-27 | 2016-11-02 | 4 |  | 4 | 2016-12-06 |  | -30474 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-12 | 2016-12-15 | [6 empty] | 0 |  | 0 |  |  | 2017-05-05 | Online | PRIVATE
NSTAR | Woburn | 2187229 | 1801 | 180 | PV | TBD | 2016-12-06 |  | -30474 | 0 | 0 | 2016-12-09 | 2017-03-03 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-06 |  | 2017-07-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Gov't
NSTAR | Hopkinton | 2187300 | 1748 | 2820 | PV | 455=H3 | 2016-11-18 | 2016-11-18 | 0 |  | 0 | 2016-12-07 |  | -30475 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Cambridge | 2187307 | 2138 | 23.4 | PV | 821-05 | 2016-11-21 | 2016-11-28 | 5 |  | 5 | 2016-12-07 |  | -30475 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-09 | 2017-02-07 | [6 empty] | 0 |  | 0 |  |  | 2017-07-20 | Online | PRIVATE
NSTAR | Eastham | 2187463 | 2642 | 23.04 | PV | 4-94B-956 | 2016-11-15 | 2016-11-17 | 2 |  | 2 | 2016-12-08 |  | -30476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-18 | [6 empty] | 0 |  | 0 |  |  | 2017-05-01 | Online | PRIVATE
NSTAR | Cambridge | 2187497 | 2139 | 60 | CHP | 831-1NC7 | 2016-10-31 | 2016-11-05 | 4 |  | 4 | 2016-12-08 |  | -30476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-26 | ISA Received | PRIVATE
NSTAR | Winchester | 2187499 | 1890 | 60 | PV | 211-H4 | 2016-11-07 | 2016-11-09 | 2 |  | 2 | 2016-12-08 |  | -30476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Weston | 2187501 | 2493 | 16.7 | PV | 450-H7 | 2016-11-10 | 2016-11-15 | 3 |  | 3 | 2016-12-08 |  | -30476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Woburn | 2187695 | 1801 | 15.875 | PV | 211-H8 | 2016-11-10 | 2016-11-15 | 3 |  | 3 | 2016-12-09 |  | -30477 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-29 | 2017-04-19 | [6 empty] | 0 |  | 0 |  |  | 2017-12-28 | Online | PRIVATE
NSTAR | Mashpee | 2187699 | 2649 | 496 | PV | 4-88-455 | 2016-11-14 | 2016-11-16 | 2 |  | 2 | 2016-12-09 |  | -30477 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-20 | [6 empty] | 0 |  | 0
NSTAR | Edgartown | 2187701 | 2539 | 21.9 | PV | 4-75-75 | 2016-11-14 | 2016-11-16 | 2 |  | 2 | 2016-12-09 |  | -30477 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | [7 empty] | 0 |  | 0 |  |  | 2017-08-03 | Online | PRIVATE
NSTAR | Sandwich | 2187704 | 2542 | 4700 | Micro Grid | 4-98A-98A | 2016-12-07 | 2016-12-21 | 10 |  | 10 | 2016-12-09 |  | -30477 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-20 | [7 empty] | 0 |  | 0 |  |  | 2019-10-17 | Online
NSTAR | Wareham | 2188254 | 2571 | 77.6 | PV | 3-84-968 | 2016-09-28 | 2016-12-09 | 52 |  | 52 | 2016-12-14 |  | -30480 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-29 | 2017-01-03 | [6 empty] | 0 |  | 0 |  |  | 2017-02-08 | Online | PRIVATE
NSTAR | Edgartown | 2188255 | 2539 | 21.9 | PV | 4-75-75 | 2016-11-14 | 2016-11-16 | 2 |  | 2 | 2016-12-14 |  | -30480 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-12-27 | 2017-01-04 | [6 empty] | 0 |  | 0 |  |  | 2017-08-23 | Online | PRIVATE
NSTAR | Assonett | 2188539 | 2702 | 16.7 | PV | 2-605-605 | 2016-11-17 | 2016-11-21 | 2 |  | 2 | 2016-12-15 |  | -30481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Wareham | 2188540 | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2019-01-11
NSTAR | Wareham | 2188541 | 2571 | 2000 | PV | 3-83-83 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2188542 | 2571 | 1500 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-12-20 | Online
NSTAR | Wareham | 2188543 | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-12-20
NSTAR | Wareham | 2188544 | 2571 | 2000 | PV | 3-82-82 | 2015-08-12 | 2015-08-12 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2019-01-11 | Online
NSTAR | Hopkinton | 2188716 | 1748 | 990 | PV | 126-H1 | 2016-11-15 | 2016-11-21 | 4 |  | 4 | 2016-12-16 |  | -30482 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-04 | 2017-04-04 | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2188717 | 2717 | 4950 | PV | 2-102-102 | 2016-11-15 | 2016-11-21 | 4 |  | 4 | 2016-12-16 |  | -30482 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2188718 | 2740 | 27 | PV | 2-73-47 | 2016-08-29 | 2016-10-28 | 44 |  | 44 | 2016-12-16 |  | -30482 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-03 | [6 empty] | 0 |  | 0 |  |  | 2017-02-23 | Online | NO EXPORT | N
NSTAR | Wayland | 2189506 | 1778 | 93.275 | PV | 342-H3 | 2016-11-09 | 2016-11-22 | 9 |  | 9 | 2016-12-28 |  | -30490 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-26 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online
NSTAR | Rochester | 2189508 | 2770 | 3300 | PV | 3-702-702 | 2016-11-15 | 2016-11-21 | 4 |  | 4 | 2016-12-28 |  | -30490 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-04 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 2189509 | 1748 | 2120 | PV | 126-H2 | 2016-11-17 | 2016-11-23 | 4 |  | 4 | 2016-12-27 |  | -30489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-04-18 | Online
NSTAR | Weston | 2190095 | 2493 | 115 | PV | 282-H1 | 2016-11-17 | 2016-11-23 | 4 |  | 4 | 2016-12-27 |  | -30489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-27 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-07-06 | Online
NSTAR | Bellingham | 2190097 | 2019 | 16.09 | PV | 65-H4 | 2016-11-22 | 2016-11-30 | 6 |  | 6 | 2016-12-27 |  | -30489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-28 | [7 empty] | 0 |  | 0 |  |  | 2017-09-18 | Online | PRIVATE
NSTAR | Westport | 2190239 | 2790 | 16.7 | PV | 2-523-523 | 2016-11-23 | 2016-11-30 | 5 |  | 5 | 2016-12-27 |  | -30489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-17 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  | 2017-12-14 | Online | PRIVATE
NSTAR | Westport | 2190240 | 2790 | 16.7 | PV | 2-523-523 | 2016-11-23 | 2016-11-30 | 5 |  | 5 | 2016-12-27 |  | -30489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-02-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Chilmark | 2191358 | 2535 | 65.2 | PV | 4-91-226 | 2016-11-22 | 2016-11-30 | 6 |  | 6 | 2016-12-29 |  | -30491 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-04 | 2017-01-11 | [6 empty] | 0 |  | 0
NSTAR | Woburn | 2191380 | 1801 | 86.4 | PV | 325-01 | 2016-11-29 | 2016-12-05 | 4 |  | 4 | 2016-12-29 |  | -30491 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-30 | 2017-04-06 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2017-09-08 | Online | PRIVATE
NSTAR | Hopkinton | 2191381 | 1748 | 28.8 | PV | 65-H6 | 2016-11-28 | 2016-12-05 | 5 |  | 5 | 2016-12-29 |  | -30491 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-12 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  | 2017-06-21 | Online | PRIVATE
NSTAR | Natick | 2191567 | 1760 | 20 | PV | 240-H5 | 2016-11-28 | 2016-12-05 | 5 |  | 5 | 2016-12-30 |  | -30492 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-25 | 2017-02-03 | [6 empty] | 0 |  | 0 |  |  | 2017-06-27 | Online | PRIVATE
NSTAR | Holliston | 2191568 | 1746 | 47.7 | PV | 65-H2 | 2016-12-02 | 2016-12-05 | 1 |  | 1 | 2016-12-30 |  | -30492 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-13 | 2017-02-22 | [6 empty] | 0 |  | 0 |  |  | 2017-07-07 | Online | PRIVATE
NSTAR | North Dartmouth | 2193439 | 2747 | 15.34 | PV | 2-541-541 | 2016-11-30 | 2016-12-05 | 3 |  | 3 | 2016-01-04 |  | -30233 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | 2017-04-25 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | North Dartmouth | 2193440 | 2747 | 15.2 | PV | 2-107-107 | 2016-11-29 | 2016-12-05 | 4 |  | 4 | 2016-01-04 |  | -30233 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Burlington | 2193629 | 1803 | 19.75 | PV | 391-H6 | 2016-12-06 | 2016-12-08 | 2 |  | 2 | 2016-01-05 |  | -30234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-08 | 2017-03-29 | [6 empty] | 0 |  | 0 |  |  | 2017-11-29 | Online | PRIVATE
NSTAR | West Roxbury | 2193924 | 2132 | 300 | CHP | 496-H6 | 2016-12-06 | 2016-12-08 | 2 |  | 2 | 2017-01-06 |  | -30497 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-27 | 2017-09-08 | [6 empty] | 0 |  | 0 |  |  | 2018-01-24 | Online
NSTAR | Canton | 2195719 | 2021 | 128 | PV | 470-H4 | 2016-12-09 | 2016-12-13 | 2 |  | 2 | 2017-01-09 |  | -30498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-16 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2018-02-20
NSTAR | Milton | 2195721 | 2186 | 17.4 | PV | 60-1409H1 | 2016-11-28 | 2016-12-13 | 11 |  | 11 | 2017-01-09 |  | -30498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-17 | 2017-02-21 | [6 empty] | 0 |  | 0 |  |  | 2017-05-05 | Online | PRIVATE
NSTAR | Cambridge | 2195978 | 2138 | 42 | PV | 828-1NC8 | 2016-12-08 | 2016-12-15 | 5 |  | 5 | 2017-01-11 |  | -30500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-30 | 2017-02-09 | [6 empty] | 0 |  | 0 |  |  | 2017-05-04 | Online | PRIVATE
NSTAR | Cambridge | 2195981 | 2138 | 214.2 | PV | 821-05 | 2016-12-08 | 2016-12-15 | 5 |  | 5 | 2017-01-11 |  | -30500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-09 | 2017-02-13 | [6 empty] | 0 |  | 0 |  |  | 2017-05-04 | Online
NSTAR | Boston | 2196194 | 2163 | 32 | PV | 817-03 | 2016-12-22 | 2016-12-29 | 5 |  | 5 | 2017-01-11 |  | -30500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-16 | 2017-02-28 | [6 empty] | 0 |  | 0 |  |  |  |  | PRIVATE
NSTAR | Woburn | 2196195 | 1801 | 119.9 | PV | 375-H3 | 2016-12-16 | 2016-12-27 | 7 |  | 7 | 2017-01-11 |  | -30500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-05-16 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  |  | PRIVATE | Y
NSTAR | Rochester | 2196392 | 2770 | 3180 | PV | 3-702-702 | 2016-12-12 | 2016-12-15 | 3 |  | 3 | 2017-01-12 |  | -30501 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-26 | 2017-06-22 | -265 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | [7 empty] | 0 |  | 0 | [5 empty] | Y
NSTAR | Sherborn | 2196661 | 1770 | 75 | PV | 240-H1 | 2016-12-16 | 2016-12-28 | 8 |  | 8 | 2017-01-13 |  | -30502 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-17 | 2017-01-19 | [6 empty] | 0 |  | 0 |  |  | 2017-05-24 | Online
NSTAR | New Bedford | 2196803 | 2745 | 296 | PV | 2-101-101 | 2016-12-28 | 2016-12-30 | 2 |  | 2 | 2016-01-17 |  | -30242 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-25 | 2017-02-17 | [6 empty] | 0 |  | 0 |  |  | 2017-05-09
NSTAR | New Bedford | 2197507 | 2745 | 496 | PV | 2-152-152 | 2016-12-21 | 2016-12-30 | 7 |  | 7 | 2017-01-19 |  | -30506 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-09 | 2017-03-15 | [6 empty] | 0 |  | 0 |  |  | 2017-06-19 | Online
NSTAR | Ashland | 2197716 | 1721 | 728 | PV |  | 2017-01-19 |  | -30506 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 2017-09-29 | 2018-05-30 | TBD |  | 30 | 2018-04-05 | 2018-04-05 | 0 |  | 0 |  | 2018-06-14 | 2018-06-15 | Online | Private
NSTAR | Natick | 2197718 | 1760 | 737 | PV | 339-1345H | 2016-12-21 | 2017-01-05 | 11 |  | 11 | 2017-01-20 |  | -30507 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-16 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2197892 | 2360 | 21.6 | PV | 3-89-926 | 2016-11-16 | 2017-01-05 | 36 |  | 36 | 2017-01-24 |  | -30509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-03-08 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Hyannis | 2198079 | 2601 | 38 | PV | 4-63-63 | 2017-01-09 | 2017-01-11 | 2 |  | 2 | 2017-01-24 |  | -30509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-08 | 2017-02-16 | [6 empty] | 0 |  | 0 |  |  | 2017-08-01 | Online | PRIVATE
NSTAR | Holliston | 2198478 | 1746 | 110 | Battery | 274-H3 | 2016-12-01 | 2017-01-12 | 30 |  | 30 | 2017-01-27 |  | -30512 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-22 | 2017-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-04-20 | Online | N/A | N
NSTAR | Natick | 2199089 | 1760 | 16.78 | PV | 433-H5 | 2017-01-11 | 2017-01-18 | 5 |  | 5 | 2017-01-31 |  | -30514 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-22 | 2017-03-06 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online | PRIVATE
NSTAR | Woburn | 2199093 | 1801 | 8.35 | PV | 211-H2 | 2017-01-17 | 2017-01-20 | 3 |  | 3 | 2017-01-31 |  | -30514 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Canton | 2199637 | 2021 | 16.7 | PV | 470-H11 | 2017-01-11 | 2017-01-20 | 7 |  | 7 | 2017-02-01 |  | -30515 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-02-24 | [7 empty] | 0 |  | 0 |  |  |  |  | PRIVATE
NSTAR | Burlington | 2199843 | 1803 | 182.65 | PV | 391-H15 | 2017-01-11 | 2017-01-18 | 5 |  | 5 | 2017-02-02 |  | -30516 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-21 | 2017-06-07 | [6 empty] | 0 |  | 0 |  |  | 2017-07-24 | Online
NSTAR | Walpole | 2200165 | 2081 | 16.7 | PV | 146-H9 | 2017-01-11 | 2017-01-20 | 7 |  | 7 | 2017-02-08 |  | -30520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-04-24 | [6 empty] | 0 |  | 0 |  |  | 2017-11-06 | Online | PRIVATE
NSTAR | Westport | 2200167 | 2790 | 15.2 | PV | 2-523-523 | 2017-01-11 | 2017-01-20 | 7 |  | 7 | 2017-02-08 |  | -30520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-23 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Sudbury | 2200633 | 1776 | 96 | PV | 342-H2 | 2017-02-09 | 2017-02-09 | 0 |  | 0 | 2017-02-10 |  | -30522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-31 | 2017-04-03 | [6 empty] | 0 |  | 0 |  |  | 2017-05-25 | Online | P2 | N
NSTAR | Dedham | 2200785 | 2026 | 153.2 | PV | 20-H1 | 2017-01-24 | 2017-01-25 | 1 |  | 1 | 2017-02-09 |  | -30521 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Stoneham | 2200960 | 1776 | 16.2 | PV | 375-H2 | 2017-01-24 | 2017-01-27 | 3 |  | 3 | 2017-02-10 |  | -30522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | East Freetown | 2200961 | 2717 | - |  | TBD | 2017-02-09 |  | -30521 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-09-15 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Fairhaven | 2201063 | 2719 | 2000 | PV | 2-221-221 | 2017-01-31 | 2017-01-31 | 0 |  | 0 | 2017-02-13 |  | -30523 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-17 | 2017-02-27 | -16 |  | 0 |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-30 | [6 empty] | 0 |  | 0 |  |  | 2021-08-10 | Online
NSTAR | Sudbury | 2201274 | 1776 | 21.4 | PV | 342-H5 | 2017-02-03 | 2017-02-08 | 3 |  | 3 | 2017-02-14 |  | -30524 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-15 | 2017-03-20 | [6 empty] | 0 |  | 0 |  |  | 2017-06-06 | Online | PRIVATE
NSTAR | Vineyard Haven | 2201898 | 2568 | 166.5 | PV | 4-75-75 | 2017-01-30 | 2017-02-13 | 10 |  | 10 | 2017-02-16 |  | -30526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-18 | 2017-06-28 | [6 empty] | 0 |  | 0 |  |  | 2018-04-18 | Online
NSTAR | Plymouth | 2202211 | 2367 | 18.6 | PV | 3-51-43J1 | 2017-02-09 | 2017-02-13 | 2 |  | 2 | 2017-02-27 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-03-10 | [6 empty] | 0 |  | 0 |  |  | 2017-08-09 | Online | PRIVATE
NSTAR | Needham | 2202454 | 2492 | 69 | PV | 342-H5 | 2017-02-13 | 2017-02-13 | 0 |  | 0 | 2017-02-27 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-04-28 |  | YES | EXP |  |  |  | 0 |  | 0 |  |  | 2017-10-10 | Online | PRIVATE | Y
NSTAR | East Falmouth | 2202817 | 2536 | 109.25 | PV | 4-98A-98A | 2017-01-27 | 2017-02-13 | 11 |  | 11 | 2017-02-27 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-07 | 2017-05-03 | [6 empty] | 0 |  | 0 |  |  | 2017-08-17 | Online | Private
NSTAR | Fairhaven | 2202964 | 2719 | 184 | PV | 2-240-209 | 2017-02-15 | 2017-02-15 | 0 |  | 0 | 2017-02-27 |  | -30533 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-07 | 2017-03-16 | [6 empty] | 0 |  | 0 |  |  | 2017-08-30 | Online
NSTAR | Acusnet | 2203266 | 2743 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2017-10-02 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Plymouth | 2203287 | 2360 | 208 | PV | 3-14-911 | 2017-01-31 | 2017-02-03 | 3 |  | 3 | 2017-02-28 |  | -30534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-04-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online | PRIVATE | Y
NSTAR | New Bedford | 2203288 | 2740 | 496 | PV | TBD | 2017-02-27 |  | -30533 | 0 | 0 | 2017-03-01 | 2017-04-07 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-03-29 |  | 2017-10-02 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Hopkinton | 2203698 | 1748 | 1980 | PV | 126-H4 | 2015-08-14 | 2015-08-14 | 0 |  | 0 | 2015-08-26 |  | -30140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-03-26 | [7 empty] | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Woburn | 2204382 | 1801 | 17.4 | PV | 211-H10 | 2017-02-17 | 2017-02-23 | 4 |  | 4 | 2017-03-06 |  | -30538 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Kingston | 2204685 | 2364 | 366.4 | PV | 3-26-902 | 2017-02-03 | 2017-02-09 | 4 |  | 4 | 2017-03-08 |  | -30540 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2205487 | 1801 | 17.4 | PV | 211-H5 | 2017-02-17 | 2017-02-23 | 4 |  | 4 | 2017-03-16 |  | -30546 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-27 | 2017-03-28 | [6 empty] | 0 |  | 0 |  |  | 2017-11-15 | Online | PRIVATE
NSTAR | West Roxbury | 2205777 | 2132 | 300 | Fuel Cell & Battery | 496-H3 | 2017-02-09 | 2017-02-27 | 12 |  | 12 | 2017-03-16 |  | -30546 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-27 | 2017-11-03 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Arlington | 2206239 | 2474 | 16.45 | PV | 211-H11 | 2017-03-01 | 2017-03-03 | 2 |  | 2 | 2017-03-17 |  | -30547 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Westwood | 2206500 | 2090 | 20 | PV | 148-H3 | 2017-02-28 | 2017-03-06 | 4 |  | 4 | 2017-03-20 |  | -30548 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-25 | 2017-04-26 | [6 empty] | 0 |  | 0 |  |  | 2017-06-19 | Online | PRIVATE
NSTAR | Boston | 2206844 | 2130 | 75 | CHP | 536-76H2 | 2016-12-08 | 2017-03-08 | 64 |  | 64 | 2017-04-11 |  | -30564 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-24 | Online
NSTAR | Woburn | 2207029 | 1801 | 576 | PV | 258-1394H2 | 2017-03-09 | 2017-03-10 | 1 |  | 1 | 2017-03-23 |  | -30551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-11-17 | [6 empty] | 0 |  | 0 |  |  | 2018-06-14 | Online
NSTAR | Cambridge | 2207242 | 2139 | 75 | CHP | 817-03 | 2017-03-08 | 2017-03-20 | 8 |  | 8 | 2017-03-23 |  | -30551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-21 | 2017-06-21 | [6 empty] | 0 |  | 0 |  |  | 2018-12-26
NSTAR | Cambridge | 2207411 | 2142 | 35 | CHP | 875-1328 | 2017-03-10 | 2017-03-20 | 6 |  | 6 | 2017-03-28 |  | -30554 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-06-15 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-09-07 | Online | PRIVATE | Y
NSTAR | Cambridge | 2207804 | 2142 | 35 | CHP | 875-1343 | 2017-03-10 | 2017-03-20 | 6 |  | 6 | 2017-03-28 |  | -30554 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-05 | 2017-06-15 |  | NO | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-26 |  | PRIVATE
NSTAR | Canton | 2207988 | 2021 | 19.8 | PV | 269-1320H1 | 2017-03-06 | 2017-03-20 | 10 |  | 10 | 2017-03-30 |  | -30556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | New Bedford | 2208391 | 2740 | 36 | PV | 2-59-96 | 2017-02-20 | 2017-03-20 | 20 |  | 20 | 2017-04-03 |  | -30558 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-02 | 2017-05-22 | [6 empty] | 0 |  | 0 |  |  | 2017-07-20 | Online | PRIVATE
NSTAR | Natick | 2208547 | 1760 | 449.5 | PV | 433-H5 | 2017-02-10 | 2017-03-23 | 29 |  | 29 | 2017-04-06 |  | -30561 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE | N
NSTAR | Natick | 2209451 | 1760 | 466.2 | PV | 433-H12 | 2017-02-10 | 2017-03-23 | 29 |  | 29 | 2017-04-06 |  | -30561 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE | N
NSTAR | Wareham | 2209835 | 2571 | - |  | TBD | 2017-04-06 |  | -30561 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2018-05-01 | 2018-03-31 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dartmouth | 2210401 | 2747 | 20.35 | PV | 274-H3 | 2017-03-22 | 2017-03-28 | 4 |  | 4 | 2017-04-12 |  | -30565 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-16 | 2017-06-30 | 2017-06-30 | [5 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Onset | 2210632 | 2558 | 19.5 | PV | 3-84-17J1 | 2017-03-22 | 2017-03-28 | 4 |  | 4 | 2017-04-13 |  | -30566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-04-19 | [7 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online | PRIVATE
NSTAR | Plympton | 2211077 | 2367 | 4950 | PV & Battery | 3-15-901 | 2017-03-30 | 2017-04-05 | 4 |  | 4 | 2017-04-17 |  | -30568 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-11 | 2017-05-11 | -89 |  | 0 | 2017-09-01 | 2017-08-10 | -18 |  | 0 | 2017-07-28 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Charlestown | 2211409 | 2129 | 403.2 | PV & Battery | 5-208H/22-208 | 2017-03-16 | 2017-04-01 | 11 |  | 11 | 2017-04-18 |  | -30569 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-06 | 2017-07-14 | [6 empty] | 0 |  | 0 |  |  | 2018-02-13 | Online
NSTAR | Woburn | 2211603 | 1801 | 20.35 | PV | 211-H8 | 2017-03-30 | 2017-04-10 | 7 |  | 7 | 2017-04-24 |  | -30573 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | PRIVATE
NSTAR | Millis | 2211983 | 2054 | 350.4 | PV | 146-H10 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-21 |  | -30572 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Millis | 2211985 | 2054 | 175.2 | PV | 146-H10 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-21 |  | -30572 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westwood | 2212591 | 2090 | 858 | PV | 469-H6 | 2017-03-30 | 2017-04-05 | 4 |  | 4 | 2017-04-26 |  | -30575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-01 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2212756 | 2021 | 330 | PV | 470-H1 | 2017-03-30 | 2017-04-05 | 4 |  | 4 | 2017-04-28 |  | -30577 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-11 | 2017-08-10 | -46 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-02-26 | Online
NSTAR | Wayland | 2212763 | 1778 | 15.2 | PV | 342-H1 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-27 |  | -30576 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-16 | 2017-06-28 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
NSTAR | Woburn | 2212768 | 1801 | 16.7 | PV | 211-H13 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-27 |  | -30576 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-01 | 2017-05-02 | [6 empty] | 0 |  | 0 |  |  | 2018-02-20 | Online
NSTAR | Burlington | 2212942 | 1803 | 16.95 | PV | 391-H7 | 2017-03-31 | 2017-04-10 | 6 |  | 6 | 2017-04-28 |  | -30577 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-27 | 2017-07-13 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Burlington | 2213109 | 1803 | 176.4 | PV | 211-H13 | 2017-03-10 | 2017-04-11 | 22 |  | 22 | 2017-05-01 |  | -30578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2213428 | 2360 | 210 | PV & Battery | 3-13-943 | 2017-04-07 | 2017-04-11 | 2 |  | 2 | 2017-05-02 |  | -30579 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-20 | 2017-07-18 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Cambridge | 2214153 | 2412 | 47.5 | PV | 875-1N38A | 2017-03-01 | 2017-04-13 | 31 |  | 31 | 2017-05-05 |  | -30582 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-02 | 2017-08-30 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Barnstable | 2214303 | 2630 | 373 | PV | 4-84B-524 | 2017-04-12 | 2017-04-18 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-25 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2018-04-09 | Online
NSTAR | Lincoln | 2214304 | 1773 | 24 | PV | 320-H8 | 2017-04-12 | 2017-04-18 | 4 |  | 4 | 2017-05-05 |  | -30582 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-07 | 2017-06-20 | [6 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online
NSTAR | Canton | 2214562 | 2021 | 462 | PV | 470-H11 | 2017-04-13 | 2017-04-14 | 1 |  | 1 | 2017-05-08 |  | -30583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-11 | 2017-08-10 | -46 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 | 2018-12-27 |  | 2018-12-28 | Online
NSTAR | Cambridge | 2214784 | 2139 | 14.4 | PV | 831-1NC7 | 2017-03-31 | 2017-04-11 | 7 |  | 7 | 2017-05-09 |  | -30584 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-25 | 2018-03-01 | [6 empty] | 0 |  | 0 |  |  | 2018-09-07 | Online
NSTAR | Chatham | 2214785 | 2659 | 47 | PV | 4-95A-95A | 2017-04-11 | 2017-04-18 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-05-09
NSTAR | Carver | 2214971 | 2330 | 30 | PV | 3-81-950 | 2017-04-13 | 2017-04-21 | 6 |  | 6 | 2017-05-16 |  | -30589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-05 | 2017-07-14 | [6 empty] | 0 |  | 0
NSTAR | Walpole | 2215756 | 2081 | 19.15 | PV | 146-H3 | 2017-04-14 | 2017-04-24 | 6 |  | 6 | 2017-05-16 |  | -30589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Stoneham | 2215757 | 2180 | 16.7 | PV | 375-H8 | 2017-04-14 | 2017-04-24 | 6 |  | 6 | 2017-05-16 |  | -30589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-25 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2216193 | 2571 | 17.575 | PV | 3-84-963 | 2017-04-14 | 2017-04-24 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-10-27 | Online
NSTAR | Osterville | 2216608 | 2655 | 18.91 | PV | 4-80A-490 | 2017-04-19 | 2017-04-26 | 5 |  | 5 | 2017-05-22 |  | -30593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 | 2017-09-12 | [6 empty] | 0 |  | 0 |  |  | 2017-11-03
NSTAR | Chelsea | 2217046 | 2150 | 996 | PV | 14-113H1 | 2017-04-20 | 2017-04-27 | 5 |  | 5 | 2017-05-24 |  | -30595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-11 | 2017-07-12 | [6 empty] | 0 |  | 0 | 2018-12-28
NSTAR | Burlington | 2217047 | 1803 | 180 | PV | 346-1395H1 | 2017-04-21 | 2017-05-01 | 6 |  | 6 | 2017-05-24 |  | -30595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-14 | 2017-08-10 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Dartmouth | 2217262 | 2747 | 210 | Fuel Cell | 2-531-531 | 2017-05-02 | 2017-05-02 | 0 |  | 0 | 2017-05-25 |  | -30596 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-30 | 2017-06-07 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Woburn | 2217434 | 1801 | 224.25 | PV | 375-H4 | 2017-05-01 | 2017-05-02 | 1 |  | 1 | 2017-05-26 |  | -30597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-21 | 2017-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-02-22 | Online
NSTAR | Cambridge | 2217599 | 2141 | 153.2 | PV | 875-1N36B | 2017-04-25 | 2017-05-03 | 6 |  | 6 | 2017-05-30 |  | -30599 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-25 | 2017-08-15 | [6 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Yarmouth | 2217600 | 2673 | 1560 | PV | 4-92A-92A | 2017-05-08 | 2017-06-13 | 26 |  | 26 | 2017-06-13 |  | -30609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2217818 | 2740 | 1070 | PV | 2-151-151 | 2017-05-08 | 2017-06-13 | 26 |  | 26 | 2017-06-16 | 2017-06-16 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2017-08-16 | -19 |  | 0 |  |  | 0 |  | 0 | 2018-01-22 | [7 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
NSTAR | Westwood | 2218004 | 2090 | 302 | PV | 469-H6 | 2017-05-09 | 2017-05-16 | 5 |  | 5 | 2017-06-16 |  | -30612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-04 | 30646 |  | 30646 |  |  | 0 |  | 0 | 2018-03-29 | 2018-04-02 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2018-10-29 | Online | Private
NSTAR | Plymouth | 2218005 | 2360 | 1176 | PV | 3-12-12 | 2017-05-08 | 2017-06-13 | 26 |  | 26 | 2017-06-16 | 2017-08-10 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-10 | 2017-09-08 | [6 empty] | 0 |  | 0 |  |  | 2018-06-22 | Online
NSTAR | Sandwich | 2218204 | 2563 | 70 | PV | 4-81B-443 | 2017-05-11 | 2017-05-17 | 4 |  | 4 | 2017-06-02 |  | -30602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-06 | [6 empty] | 0 |  | 0 |  |  | 2018-04-19 | Online
NSTAR | Wareham | 2218205 | 2571 | 210 | Fuel Cell | 3-84-961 | 2017-05-11 | 2017-05-17 | 4 |  | 4 | 2017-06-02 |  | -30602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 | 1900-04-05 | 2017-06-20 | [5 empty] | 0 |  | 0 |  |  | 2018-05-02 | Online
NSTAR | Norfolk | 2218206 | 2056 | 72 | PV | 146-H3 | 2017-05-01 | 2017-05-19 | 14 |  | 14 | 2017-06-02 |  | -30602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-10-06 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 2218766 | 1748 | 16.7 | PV | 65-H6 | 2017-05-15 | 2017-05-22 | 5 |  | 5 | 2017-06-05 |  | -30603 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2219177 | 2747 | 2300 | PV | 2-543-543 | 2017-05-01 | 2017-05-19 | 14 |  | 14 | 2017-06-06 |  | -30604 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-07-27 | 30640 |  | 30640 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-29 | Online
NSTAR | Roxbury | 2219411 | 2119 | 24 | PV | 483-H6 | 2017-05-13 | 2017-05-22 | 6 |  | 6 | 2017-06-07 |  | -30605 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-17 | 2017-09-20 | [6 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
NSTAR | New Bedford | 2219644 | 2745 | 336 | PV | 2-88-18 | 2017-05-19 | 2017-05-22 | 1 |  | 1 | 2017-06-08 |  | -30606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-08 | 2017-06-26 | [6 empty] | 0 |  | 0 |  |  | 2017-12-29 | Online
NSTAR | Falmouth | 2219873 | 2540 | 54.88 | PV | 4-72-433 | 2017-05-23 | 2017-05-25 | 2 |  | 2 | 2017-06-13 |  | -30609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2220027 | 2453 | 72 | PV | 282-H8 | 2017-05-01 | 2017-05-23 | 16 |  | 16 | 2017-06-13 |  | -30609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-14 | 2017-09-18 | [6 empty] | 0 |  | 0
NSTAR | Wareham | 2220029 | 2576 | 18 | PV | 3-85-85 | 2017-05-24 | 2017-05-30 | 4 |  | 4 | 2017-06-13 |  | -30609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-06-16 | 2017-07-14 | [6 empty] | 0 |  | 0 |  |  | 2017-11-29 | Online
NSTAR | Dorchester | 2220311 | 2124 | 45.15 | PV | 483-H7 | 2017-03-22 | 2017-03-28 | 4 |  | 4 | 2017-06-13 |  | -30609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-12 | 2017-07-24 | [6 empty] | 0 |  | 0 |  |  | 2018-01-23 | Online | PRIVATE
NSTAR | Ashland | 2220527 | 1721 | 4450 | PV | 274-1429H1 | 2017-05-16 | 2017-05-22 | 4 |  | 4 | 2017-06-15 |  | -30611 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-29 | 2017-09-21 | -8 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2221535 | 2330 | 2000 | PV | 3-10-10 | 2017-05-19 | 2017-05-30 | 7 |  | 7 | 2017-06-21 |  | -30615 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-08-16 | -17 |  | 0 |  |  | 0 |  | 0 | 2017-11-20 | 2017-11-20 | [6 empty] | 0 |  | 0 |  |  | 2019-05-17 | Online
NSTAR | North Dartmouth | 2223159 | 2747 | 100.8 | PV | 2-532-532 | 2017-05-22 | 2017-05-31 | 7 |  | 7 | 2017-06-30 |  | -30622 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-10 | [6 empty] | 0 |  | 0 |  |  | 2018-04-12 | Online
NSTAR | Newton | 2223207 | 2465 | 17.75 | PV | 292-H12 | 2017-05-22 | 2017-06-02 | 9 |  | 9 | 2017-07-06 |  | -30626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-24 | 2017-09-13 | [6 empty] | 0 |  | 0 |  |  | 2017-12-14 | Online
NSTAR | Dedham | 2223211 | 2026 | 135 | CHP | 20-H6 | 2017-05-26 | 2017-06-05 | 6 |  | 6 | 2017-07-06 |  | -30626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-16 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2223213 | 2053 | 20 | PV | 65-H5 | 2017-05-16 | 2017-06-05 | 14 |  | 14 | 2017-07-06 |  | -30626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-04 | 2017-08-09 | [6 empty] | 0 |  | 0 |  |  | 2017-10-02 | Online
NSTAR | Woburn | 2223988 | 2116 | 602 | PV | 375-H9 | 2017-06-05 | 2017-06-07 | 2 |  | 2 | 2017-07-06 |  | -30626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | 30654 |  | 30654 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2223989 | 2739 | 43.17 | PV | 2-301-301 | 2017-06-02 | 2017-06-08 | 4 |  | 4 | 2017-07-06 |  | -30626 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-26 | 2017-08-17 | [6 empty] | 0 |  | 0
NSTAR | Acton | 2223990 | 1720 | 167 | PV | 416-H4 | 2017-06-07 | 2017-06-15 | 6 |  | 6 | 2017-07-07 |  | -30627 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-08-16 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Millis | 2224177 | 2054 | 17.1 | PV | 65-H1 | 2017-06-01 | 2017-06-19 | 12 |  | 12 | 2017-07-10 |  | -30628 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-08 | 2017-10-04 | [6 empty] | 0 |  | 0 |  |  | 2018-01-03 | Online
NSTAR | West Roxbury | 2224405 | 2132 | 498 | PV | 496-H3 | 2017-06-09 | 2017-06-19 | 6 |  | 6 | 2017-07-10 |  | -30628 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2224625 | 2452 | 499.5 | PV | 277-1367XYH | 2017-06-28 | 2017-07-03 | 3 |  | 3 | 2017-07-11 |  | -30629 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-31 | 2017-08-03 | [6 empty] | 0 |  | 0 |  |  | 2017-12-21 | Online
NSTAR | Fairhaven | 2224661 | 2702 | 4900 | PV | 2-605-605 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | -30630 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | 30654 |  | 30654 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2224664 | 2571 | 3300 | PV | 3-85-928 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | -30630 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | 2017-08-16 | -19 |  | 0 |  |  | 0 |  | 0 | 2017-12-06 | 2017-12-26 | [6 empty] | 0 |  | 0 |  |  | 2018-12-12 | Online
NSTAR | Freetown | 2224890 | 2702 | 4900 | PV | 2-102-102 | 2017-06-20 | 2017-06-20 | 0 |  | 0 | 2017-07-12 |  | -30630 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-08-16 | 30654 |  | 30654 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2225509 | 2125 | 210 | Fuel Cell | 106-H4 | 2017-06-15 | 2017-06-19 | 2 |  | 2 | 2017-07-17 |  | -30633 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-18 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2019-04-04 | Online
NSTAR | Kingston | 2225512 | 2364 | 20.4 | PV | 3-18-36J1 | 2017-06-08 | 2017-06-20 | 8 |  | 8 | 2017-07-17 |  | -30633 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-20 | 2017-07-21 | [6 empty] | 0 |  | 0 |  |  | 2017-09-05 | Online
NSTAR | Waltham | 2226333 | 2453 | 180 | PV | 282-H8 | 2017-06-01 | 2017-06-20 | 13 |  | 13 | 2017-07-21 |  | -30637 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
NSTAR | Dorchester | 2226367 | 2021 | 56.35 | PV | 143-109H4 | 2017-06-12 | 2017-06-28 | 12 |  | 12 | 2017-07-20 |  | -30636 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | West Newton | 2226368 | 2465 | 15.95 | PV | 282-H9 | 2017-06-15 | 2017-06-28 | 9 |  | 9 | 2017-07-20 |  | -30636 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-29 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-11-17 | Online
NSTAR | Brewster | 2226549 | 2631 | 19.2 | PV | 4-89B-576 | 2017-06-23 | 2017-06-28 | 3 |  | 3 | 2017-07-24 |  | -30638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-01 | 2017-08-03 | [6 empty] | 0 |  | 0 |  |  | 2017-12-28 | Online
NSTAR | Framingham | 2226553 | 1702 | 120 | PV | 240-H4 | 2017-06-26 | 2017-06-28 | 2 |  | 2 | 2017-07-24 |  | -30638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
NSTAR | Natick | 2226744 | 1760 | 497 | PV | 240-H1 | 2017-06-26 | 2017-06-28 | 2 |  | 2 | 2017-07-24 |  | -30638 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-13 | 2018-05-01 | [6 empty] | 0 |  | 0
NSTAR | Lexington | 2226745 | 2421 | 860.6 | PV | 450-H5 | 2017-06-27 | 2017-07-24 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
NSTAR | New Bedford | 2227188 | 2745 | 499.05 | PV | 2-107-107 | 2017-06-16 | 2017-07-10 | 16 |  | 16 | 2017-07-26 |  | -30640 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-04 | 2017-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
NSTAR | New Bedford | 2227197 | 2740 | 700 | PV | 2-152-152 | 2017-06-15 | 2017-06-29 | 10 |  | 10 | 2017-07-26 |  | -30640 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-08 | [7 empty] | 0 |  | 0 | 2018-12-21 |  | 2018-12-21
NSTAR | Maynard | 2227357 | 1754 | 3516 | PV | 416-H6 | 2017-06-22 | 2017-07-06 | 10 |  | 10 | 2017-07-27 |  | -30641 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-19 | 2018-02-20 | -21 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-12-18 | [6 empty] | 0 |  | 0
NSTAR | Orleans | 2227358 | 2653 | 58.6 | PV | 4-83-952 | 2017-06-05 | 2017-06-15 | 8 |  | 8 | 2017-07-27 |  | -30641 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 | 2018-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-18
NSTAR | Plymouth | 2227360 | 2360 | 18 | PV | 3-89-926 | 2017-06-27 | 2017-07-06 | 7 |  | 7 | 2017-07-27 |  | -30641 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-07-31 | 2017-08-02 | [6 empty] | 0 |  | 0 |  |  | 2017-12-11 | Online
NSTAR | Westport | 2227530 | 2790 | 480 | PV | 2-523-523 | 2017-05-09 | 2017-06-28 | 36 |  | 36 | 2017-07-31 |  | -30643 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2019-08-12 | Online
NSTAR | New Bedford | 2227939 | 2745 | 632.7 | PV | 2-83-83 | 2017-06-30 | 2017-07-07 | 5 |  | 5 | 2017-08-01 |  | -30644 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-11-15 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2227941 | 1702 | 1095.78 | PV | 240-H6 | 2017-06-26 | 2017-07-06 | 8 |  | 8 | 2017-08-01 |  | -30644 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2017-12-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-16 | Online
NSTAR | Weston | 2228145 | 2493 | 24.82 | PV | 282-H1 | 2017-06-27 | 2017-07-11 | 10 |  | 10 | 2017-08-02 |  | -30645 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-21 | 2017-08-25 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
NSTAR | Westport | 2228336 | 2790 | 2000 | PV | 2-524-524 | 2017-07-03 | 2017-07-11 | 6 |  | 6 | 2017-08-03 |  | -30646 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-28 |  | -30663 |  | 0 |  |  | 0 |  | 0 | 2017-12-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2228337 | 2601 | 997.965 | PV | 4-80B-80B | 2017-06-13 | 2017-07-12 | 21 |  | 21 | 2017-08-03 |  | -30646 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-04 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-12-19
NSTAR | West Yarmouth | 2228338 | 2673 | 39 | PV | 4-64-536 | 2017-06-26 | 2017-07-12 | 12 |  | 12 | 2017-08-03 |  | -30646 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-26 | 2017-11-10 | [6 empty] | 0 |  | 0 |  |  | 2017-12-20 | Online
NSTAR | Falmouth | 2228808 | 2536 | 7190 | PV | 4-98A-429 | 2017-06-30 | 2017-07-12 | 8 |  | 8 | 2017-08-04 |  | -30647 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-01-23 | 2018-01-17 | 257 |  | 257 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-06 | Online
NSTAR | Mattapoisett | 2229139 | 2739 | - |  | TBD | 2017-08-07 |  | -30648 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-03-16 | No | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private | N
NSTAR | Dorchester | 2229211 | 2121 | 40.7 | PV | 483-H2 | 2017-07-10 | 2017-07-17 | 5 |  | 5 | 2017-08-08 |  | -30649 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dover | 2229213 | 2030 | 28 | PV | 456-H3 | 2017-07-07 | 2017-07-19 | 8 |  | 8 | 2017-08-08 |  | -30649 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-13 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2229434 | 1746 | 44 | PV | 130-H1 | 2017-07-18 | 2017-07-21 | 3 |  | 3 | 2017-08-09 |  | -30650 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-23 | 2017-08-29 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
NSTAR | Norfolk | 2229611 | 2056 | 34.5 | PV | 146-H3 | 2017-07-11 | 2017-07-19 | 6 |  | 6 | 2017-08-10 |  | -30651 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-14 | [6 empty] | 0 |  | 0 |  |  | 2018-01-11 | Online
NSTAR | Holliston | 2229612 | 1746 | 15.2 | PV | 130-H1 | 2017-06-16 | 2017-07-19 | 23 |  | 23 | 2017-08-10 |  | -30651 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-06 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-02-01 | Online
NSTAR | Acton | 2229787 | 1720 | 22.8 | PV | 416-H4 | 2017-07-10 | 2017-07-24 | 10 |  | 10 | 2017-08-11 |  | -30652 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-18 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dorchester | 2229788 | 2121 | 36 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | 8 |  | 8 | 2017-08-11 |  | -30652 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-15 | 2017-08-16 | [6 empty] | 0 |  | 0 |  |  | 2017-09-26 | Online
NSTAR | Natick | 2229922 | 1760 | 466.2 | PV | 433-H10 | 2017-07-18 | 2017-07-20 | 2 |  | 2 | 2017-08-14 |  | -30653 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-04 | 2018-01-19 | [6 empty] | 0 |  | 0 |  |  | 2018-10-11 | Online | Private
NSTAR | Natick | 2229933 | 1760 | 466.2 | PV | 433-H14 | 2017-07-18 | 2017-07-20 | 2 |  | 2 | 2017-08-14 |  | -30653 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-02 | 2017-01-08 | -281 |  | 0 |  |  | 0 |  | 0 | 2018-05-04 | 2018-11-29 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2019-11-20 | Online
NSTAR | Dorchester | 2229935 | 2124 | 24 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | 8 |  | 8 | 2017-08-14 |  | -30653 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-30 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-10-20 | Online
NSTAR | Wareham | 2230372 | 2576 | 24.5 | PV | 3-85-85 | 2017-07-14 | 2017-07-25 | 7 |  | 7 | 2017-08-16 |  | -30655 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-06 | 2017-09-08 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2230376 | 1748 | 3960 | PV | 126-H2 | 2017-07-21 | 2017-07-25 | 2 |  | 2 | 2017-08-16 |  | -30655 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 2230557 | 2121 | 36 | PV | 143-109H4 | 2017-07-13 | 2017-07-25 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Walpole | 2230560 | 2081 | 590 | PV | 146-H1 | 2017-07-21 | 2017-07-25 | 2 |  | 2 | 2017-08-17 |  | -30656 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Dorchester | 2230829 | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-18 |  | -30657 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dorchester | 2231017 | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-21 |  | -30658 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-01 | 2017-09-05 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
NSTAR | Dorchester | 2231474 | 2121 | 32.85 | PV | 143-109H4 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-23 |  | -30660 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-06 | 2017-11-08 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Dorchester | 2231481 | 2124 | 30 | PV | 143-109H4 | 2017-07-18 | 2017-07-26 | 6 |  | 6 | 2017-08-23 |  | -30660 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-25 | 2017-08-29 | [6 empty] | 0 |  | 0 |  |  | 2017-10-25 | Online
NSTAR | Dorchester | 2231678 | 2121 | 36 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-25 |  | -30662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2017-12-04 | Online
NSTAR | Dorchester | 2231683 | 2121 | 32.85 | PV | 483-H3 | 2017-07-17 | 2017-07-26 | 7 |  | 7 | 2017-08-25 |  | -30662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-09-19 | [6 empty] | 0 |  | 0 |  |  | 2017-11-30 | Online
NSTAR | Walpole | 2231849 | 2081 | 402 | PV | 146-H1 | 2017-07-21 | 2017-07-27 | 4 |  | 4 | 2017-08-25 |  | -30662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Walpole | 2231851 | 2081 | 362 | PV | 146-H1 | 2017-07-21 | 2017-07-27 | 4 |  | 4 | 2017-08-25 |  | -30662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Lexington | 2231852 | 2420 | 25 | PV | 533-H3 | 2017-07-07 | 2017-07-27 | 14 |  | 14 | 2017-08-25 |  | -30662 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-03 | 2017-10-13 | [6 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
NSTAR | Sandwich | 2232261 | 2563 | 66.6 | PV | 4-81B-81B | 2017-07-23 | 2017-07-31 | 6 |  | 6 | 2017-08-29 |  | -30664 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2018-01-02 | [6 empty] | 0 |  | 0 |  |  | 2018-04-16 | Online
NSTAR | Dorchester | 2232263 | 2124 | 48 | PV | 483-H7 | 2017-07-27 | 2017-07-31 | 2 |  | 2 | 2017-08-29 |  | -30664 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-09-19 | [6 empty] | 0 |  | 0 |  |  | 2017-11-30 | Online
NSTAR | Bourne | 2232421 | 2532 | 36 | PV | 3-89-925 | 2017-07-25 | 2017-07-31 | 4 |  | 4 | 2017-08-30 |  | -30665 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-13 | 2017-11-20 | [6 empty] | 0 |  | 0 |  |  | 2018-02-06 | Online
NSTAR | Dorchester | 2232422 | 2124 | 43.2 | PV | 483-H5 | 2017-07-27 | 2017-08-01 | 3 |  | 3 | 2017-08-30 |  | -30665 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-08-31 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  | 2017-11-06 | Online
NSTAR | Dorchester | 2232784 | 2124 | 72 | PV | 483-H4 | 2017-07-27 | 2017-08-01 | 3 |  | 3 | 2017-09-05 |  | -30669 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-22 | 2017-09-22 | [6 empty] | 0 |  | 0 |  |  | 2017-11-03 | Online
NSTAR | Walpole | 2233507 | 2081 | 336 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | 2 |  | 2 | 2017-09-06 |  | -30670 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Walpole | 2233722 | 2081 | 368 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | 2 |  | 2 | 2017-09-08 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | 2019-06-29 | [7 empty] | 0 |  | 0 |  |  | 2019-07-03 | Online
NSTAR | Walpole | 2233726 | 2081 | 662 | PV | 146-H1 | 2017-07-28 | 2017-08-01 | 2 |  | 2 | 2017-09-08 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Wareham | 2233733 | 2576 | 2000 | PV | 3-85-85 | 2017-07-31 | 2017-08-01 | 1 |  | 1 | 2017-09-08 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-26 | 2018-01-23 | -5 |  | 0 |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0
NSTAR | Woods Hole | 2233739 | 2540 | 86.4 | PV | 4-72-433 | 2017-08-03 | 2017-08-03 | 0 |  | 0 | 2017-09-08 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2018-01-23 | [6 empty] | 0 |  | 0 |  |  | 2018-06-08 | Online
NSTAR | Falmouth | 2233941 | 2540 | 33.3 | PV | 4-72-433 | 2017-08-08 | 2017-08-08 | 0 |  | 0 | 2017-09-08 |  | -30672 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2018-01-23 | [6 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
NSTAR | West Tisbury | 2233942 | 2575 | 48 | PV | 4-97-220 | 2017-08-02 | 2017-08-08 | 4 |  | 4 | 2017-09-11 |  | -30673 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-03 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 2234087 | 2081 | 24 | PV | 456-H1 | 2017-08-01 | 2017-08-15 | 10 |  | 10 | 2017-09-12 |  | -30674 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-17 | 2017-10-17 | [6 empty] | 0 |  | 0 |  |  | 2017-12-27 | Online
NSTAR | Walpole | 2234091 | 2081 | 782 | PV | 146-H1 | 2017-08-08 | 2017-08-08 | 0 |  | 0 | 2017-09-12 |  | -30674 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Walpole | 2234593 | 2081 | 132 | PV | 146-H1 | 2017-07-21 | 2017-07-25 | 2 |  | 2 | 2017-09-13 |  | -30675 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-01 | 2017-10-27 | -5 |  | 0 |  |  | 0 |  | 0 | 2018-06-29 | [7 empty] | 0 |  | 0 |  |  | 2019-06-21 | Online
NSTAR | Dartmouth | 2234626 | 2747 | 594 | PV | 2-532-532 | 2017-08-08 | 2017-08-11 | 3 |  | 3 | 2017-09-13 |  | -30675 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-11-15 | 30719 |  | 30719 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2234823 | 1721 | 1080 | PV | 274-1429H1 | 2017-08-02 | 2017-08-15 | 9 |  | 9 | 2017-09-14 |  | -30676 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2234830 | 2330 | 21.9 | PV | 3-10-929 | 2017-08-10 | 2017-08-15 | 3 | 0 | 3 | 2017-09-13 |  | -30675 | 6 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-24 | 2017-12-06 | [6 empty] | 0 |  | 0 |  |  | 2018-01-22 | Online
NSTAR | Woburn | 2234836 | 1801 | 16.7 | PV | 375-H12 | 2017-08-09 | 2017-08-15 | 4 |  | 4 | 2017-09-14 |  | -30676 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | 2017-12-05 | [6 empty] | 0 |  | 0
NSTAR | Woburn | 2234838 | 1801 | 16.7 | PV | 375-H14 | 2017-08-09 | 2017-08-15 | 4 |  | 4 | 2017-09-14 |  | -30676 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2235080 | 2131 | 180 | PV | 385-H15 | 2017-07-06 | 2017-08-15 | 28 |  | 28 | 2017-09-18 |  | -30678 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-27 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 2235082 | 1748 | 59 | PV | 126-H2 | 2017-08-01 | 2017-08-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-23 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-04-11 | Online
NSTAR | Barnstable | 2235087 | 2090 | 3720 | PV | 4-88-453 | 2017-08-17 | 2017-08-18 | 1 |  | 1 | 2017-09-18 |  | -30678 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-06 | 2018-02-26 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2235287 | 1802 | 42 | PV | 240-H3 | 2017-08-16 | 2017-08-22 | 4 |  | 4 | 2017-09-18 |  | -30678 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | 2017-11-10 | [6 empty] | 0 |  | 0 |  |  | 2018-05-29 | Online
NSTAR | Barnstable | 2235688 | 2571 | 472 | PV | 4-80B-80B | 2017-07-24 | 2017-10-17 | 61 |  | 61 | 2017-11-06 |  | -30713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2235692 | 2134 | 133.2 | PV | 250-1N39H1 | 2017-08-22 | 2017-08-28 | 4 |  | 4 | 2017-10-19 |  | -30701 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-16 | 2017-10-19 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Hyannis | 2235860 | 2601 | 28.8 | PV | 4-84B-524 | 2017-08-25 | 2017-08-29 | 2 |  | 2 | 2017-09-20 |  | -30680 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-05 | 2018-01-12 | [6 empty] | 0 |  | 0 |  |  | 2018-02-08 | Online
NSTAR | Wareham | 2236093 | 2571 | 46.8 | PV | 3-85-964 | 2017-08-07 | 2017-08-29 | 16 |  | 16 | 2017-09-21 |  | -30681 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-27 | 2017-09-27 | [6 empty] | 0 |  | 0 |  |  | 2018-01-11 | Online
NSTAR | Natick | 2236094 | 1760 | 51.75 | PV | 433-H9 | 2017-08-29 | 2017-08-30 | 1 |  | 1 | 2017-09-21 |  | -30681 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-06 | 2017-10-25 | [6 empty] | 0 |  | 0 |  |  | 2018-03-23 | Online
NSTAR | Canton | 2236306 | 2021 | 208 | PV | 470-H11 | 2017-08-24 | 2017-08-30 | 4 |  | 4 | 2017-09-22 |  | -30682 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapan | 2236312 | 2126 | 30.5 | PV | 311-12 | 2017-08-31 | 2017-08-31 | 0 |  | 0 | 2017-09-22 |  | -30682 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-09-26 | [7 empty] | 0 |  | 0 |  |  | 2018-02-21 | Online
NSTAR | Ashland | 2236318 | 1721 | 92 | PV | 274-1429H1 | 2017-08-31 | 2017-09-01 | 1 |  | 1 | 2017-09-22 |  | -30682 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dedham | 2236710 | 2026 | 170 | PV | 20-H6 | 2017-08-31 | 2017-09-05 | 3 |  | 3 | 2017-09-26 |  | -30684 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-07 | 2017-12-15 | [6 empty] | 0 |  | 0 |  |  | 2019-06-25 | Online
NSTAR | Boston | 2236712 | 2115 | 15.2 | PV | 2-1N45 | 2017-08-31 | 2017-09-05 | 3 |  | 3 | 2017-09-26 |  | -30684 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-18 | 2017-12-19 | [6 empty] | 0 |  | 0 |  |  | 2018-04-24 | Online
NSTAR | Boston | 2236713 | 2215 | 21.9 | PV | 350-H10 | 2017-08-31 | 2017-09-05 | 3 |  | 3 | 2017-09-26 |  | -30684 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-16 | 2017-12-08 | [6 empty] | 0 |  | 0 |  |  | 2018-04-18 | Online
NSTAR | Yarmouth | 2236910 | 2675 | 23.2 | PV | 4-90-541 | 2017-09-01 | 2017-09-06 | 3 |  | 3 | 2017-09-27 |  | -30685 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-14 | 2017-12-26 | [6 empty] | 0 |  | 0
NSTAR | Burlington | 2236911 | 1803 | 27.9 | PV | 346-1395H1 | 2017-09-01 | 2017-09-06 | 3 |  | 3 | 2017-09-27 |  | -30685 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-20 | [7 empty] | 0 |  | 0
NSTAR | East Falmouth | 2237110 | 2536 | 159.9 | PV | 4-98B-449 | 2017-09-06 | 2017-09-08 | 2 |  | 2 | 2017-09-28 |  | -30686 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-02-21 | [6 empty] | 0 |  | 0 |  |  | 2018-06-28 | Online
NSTAR | Wellfleet | 2237326 | 2667 | 17.92 | PV | 4-96-960 | 2017-09-07 | 2017-09-14 | 5 |  | 5 | 2017-09-29 | 2017-10-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-10-24 | [6 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
NSTAR | Westport | 2237335 | 2790 | 268 | PV | 2-532-532 | 2017-09-06 | 2017-09-14 | 6 |  | 6 | 2017-09-29 | 2017-10-16 | 11 | 0 | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-12-27 | [6 empty] | 0 |  | 0
NSTAR | Wareham | 2237797 | 2571 | 294 | PV | 3-86-966 | 2017-09-06 | 2017-09-11 | 3 |  | 3 | 2017-10-03 | 2017-10-17 | 10 | 0 | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marshfield | 2237799 | 2050 | 27.5 | PV | 3-25-42J2 | 2017-08-22 | 2017-09-13 | 16 |  | 16 | 2017-10-03 |  | -30689 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-11 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
NSTAR | Plymouth | 2238366 | 2360 | 499.5 | PV | 3-14-911 | 2017-05-15 | 2017-09-13 | 87 |  | 87 | 2017-10-04 | 2017-10-17 | 9 | 0 | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-18 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2019-02-11
NSTAR | Hopkinton | 2238660 | 1748 | 7520 | PV | 126-H2 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-05 |  | -30691 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2238661 | 2717 | 1156 | PV & Battery |  | 2017-10-04 | 2017-10-06 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-10-11 | 2019-05-16 | 416 | 333 | 83 |  |  | 0 |  | 0 | 2019-06-25 | 2019-07-10 | 11 | 0 | 11 | 2019-02-25 | 2019-08-01 | 2020-03-01 | No |  | 60 | 2020-01-30 |  | -31296 |  | 0 |  |  |  | In Queue | Private | N
NSTAR | Cambridge | 2238845 | 2139 | 1330 | PV | 875-1312 | 2017-06-02 | 2017-10-05 | 89 |  | 89 | 2017-10-06 |  | -30692 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-09 | 2018-01-05 | -4 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online | Public
NSTAR | Buzzards Bay | 2239274 | 2532 | 119.9 | PV | 3-88-2J4 | 2017-09-12 | 2017-09-13 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-21 | Online
NSTAR | Plympton | 2239531 | 2367 | 4695 | PV & Battery | TBD | 2017-09-17 | 2017-09-17 | 0 |  | 0 | 2017-09-17 |  | -30677 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-21 | Online
NSTAR | Brighton | 2239744 | 2134 | 7500 | CHP |  | 2017-10-04 | 2017-10-04 | 0 |  | 0 | 2017-10-13 |  | -30697 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-26 | [7 empty] | 0 |  | 0 |  |  | 2019-12-11 | Online
NSTAR | Dartmouth | 2239746 | 2747 | 997.7 | PV | 2-543-543 | 2017-09-11 | 2017-09-21 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2239974 | 1801 | 57.5 | PV | 4W5-H1 | 2017-09-07 | 2017-09-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-26 | [6 empty] | 0 |  | 0 |  |  | 2018-07-20 | Online
NSTAR | Roslindale | 2240297 | 2131 | 338 | PV | 496-H4 | 2017-09-12 | 2017-09-27 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Waltham | 2240718 | 2452 | 266.4 | PV | 450-H4 | 2017-09-21 | 2017-09-27 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-03 | 2017-11-07 | [6 empty] | 0 |  | 0 |  |  | 2018-07-06 | Online
NSTAR | Plymouth | 2240998 | 2360 | - |  | TBD | 2017-10-18 |  | -30700 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-05-25 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Sharon | 2241001 | 2067 | 272 | PV | 146-H1 | 2017-10-04 | 2017-10-04 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-28 | 2018-08-30 | [6 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online | Private
NSTAR | Acton | 2241211 | 1720 | 22.8 | PV | 416-H8 | 2017-09-22 | 2017-09-27 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-28 | 2017-12-05 | [6 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
NSTAR | Kingston | 2241214 | 2364 | 33.3 | PV | 3-17-17 | 2017-09-27 | 2017-10-03 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-01-22 | Online
NSTAR | Milton | 2241676 | 2186 | 21.9 | PV | 362-02 | 2017-10-03 | 2017-10-03 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-10 | 2017-11-13 | [6 empty] | 0 |  | 0 |  |  | 2018-08-21 | Online
NSTAR | South Yarmouth | 2241680 | 2664 | 124.47 | PV | 4-92A-562 | 2017-09-27 | 2017-10-03 | 4 |  | 4 | 2017-10-10 |  | -30694 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-21 | [6 empty] | 0 |  | 0 |  |  | 2018-08-09 | Online
NSTAR | Plympton | 2241681 | 2367 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-05-31 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dartmouth | 2241682 | 2748 | 22.8 | PV | 2-528-528 | 2017-10-02 | 2017-10-10 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-09 | Online
NSTAR | Framingham | 2242066 | 1702 | 20 | PV | 455-H5 | 2017-08-30 | 2017-10-11 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2242067 | 1748 | 299.7 | PV | 126-H1 | 2017-09-29 | 2017-10-10 | 7 |  | 7 | 2017-11-02 |  | -30711 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private | Y
NSTAR | Waltham | 2242293 | 2451 | 210 | PV | 450-H1 | 2017-10-10 | 2017-10-31 | 15 |  | 15 | 2017-11-02 |  | -30711 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-19 | 2018-05-17 | [6 empty] | 0 |  | 0 |  |  | 2019-12-16 | Online
NSTAR | Plymouth | 2242294 | 2360 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-06-05 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Roxbury | 2242468 | 2119 | 15.5 | PV | 52-148H1 | 2017-09-13 | 2017-10-17 | 24 |  | 24 | 2017-11-03 |  | -30712 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-11-29 | 2017-12-07 | [6 empty] | 0 |  | 0 |  |  | 2018-06-14 | Online
NSTAR | Framingham | 2243010 | 1702 | 256 | PV | 455-H4 | 2017-10-04 | 2017-10-18 | 10 |  | 10 | 2017-11-03 |  | -30712 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-08-06 | Online
NSTAR | Barnstable | 2243747 | 2668 | 33.6 | PV | 4-82-516 | 2017-10-10 | 2017-10-18 | 6 |  | 6 | 2017-11-03 |  | -30712 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-19 | 2017-12-21 | [6 empty] | 0 |  | 0 |  |  | 2018-09-17 | Online
NSTAR | Vineyard Haven | 2243750 | 2658 | 22 | PV | 4-91-228 | 2017-10-16 | 2017-10-18 | 2 |  | 2 | 2017-11-03 |  | -30712 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-20 | 2018-08-09 | [6 empty] | 0 |  | 0 |  |  |  | Revised ISA/WO (2287709)
NSTAR | Westport | 2243995 | 2790 | 2400 | PV | 2-532-532 | 2017-10-04 | 2017-10-13 | 7 |  | 7 | 2017-11-06 |  | -30713 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2018-04-12 | 30825 |  | 30825 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-10-14 | Online
NSTAR | Oak Bluffs | 2244459 | 2557 | 20.5 | PV | 4-99-224 | 2017-10-16 | 2017-10-18 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Oak Bluffs | 2244463 | 2557 | 27.5 | PV | 4-99-224 | 2017-10-16 | 2017-10-18 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2244680 | 2139 | 33.3 | PV | 814-13 | 2017-10-17 | 2017-10-19 | 2 |  | 2 | 2017-11-13 |  | -30718 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Roxbury | 2244684 | 2132 | 35 | CHP | 468-01 | 2017-10-18 | 2017-10-19 | 1 |  | 1 | 2017-11-13 |  | -30718 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
NSTAR | West Roxbury | 2244833 | 2132 | 35 | CHP | 468-01 | 2017-10-18 | 2017-10-19 | 1 |  | 1 | 2017-11-13 |  | -30718 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-31 | Online
NSTAR | Waltham | 2245190 | 2451 | 599 | PV | TBD | 2017-11-13 |  | -30718 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-06-21 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Waltham | 2245192 | 2451 | 599 | PV | 450-H2 | 2017-10-10 | 2017-10-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-13 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2245194 | 2451 | 632.7 | PV | 282-H5 | 2017-08-15 | 2017-10-27 | 53 |  | 53 | 2017-11-21 |  | -30724 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Edgartown | 2245195 | 2539 | 74.4 | PV | 4-97-97 | 2017-10-18 | 2017-10-23 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-04 | Online
NSTAR | Plymouth | 2245196 | 2360 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-06-21 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | South Carver | 2245475 | 2366 | 88 | PV | 3-81-81 | 2017-10-23 | 2017-10-23 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-02-06 | Online
NSTAR | Ashland | 2245647 | 1721 | 773.6 | PV | 274-H1 | 2017-11-02 | 2017-11-02 | 0 |  | 0 | 2017-11-16 |  | -30721 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lincoln | 2245650 | 1773 | 199.8 | PV | 320-H6 | 2017-09-26 | 2017-11-02 | 27 |  | 27 | 2018-11-16 |  | -30982 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-03 | 2018-02-15 | [6 empty] | 0 |  | 0 |  |  | 2018-10-04 | Online
NSTAR | Plymouth | 2245961 | 2360 | 48 | PV | 3-13-936 | 2017-10-19 | 2017-10-26 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-14 | 2017-12-15 | [6 empty] | 0 |  | 0 |  |  | 2018-05-30 | Online
NSTAR | Allston | 2246186 | 2134 | 66.6 | PV | 3614 | 2017-10-19 | 2017-10-26 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-27 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-06-27 | Online
NSTAR | Canton | 2246191 | 2021 | 24 | PV | 470-H9 | 2017-10-10 | 2017-10-23 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westport | 2246192 | 2790 | 21.95 | PV | 2-532-532 | 2017-10-11 | 2017-10-23 | 8 |  | 8 | 2017-11-20 |  | -30723 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Boston | 2246431 | 2128 | 978 | PV | 108-195H1 | 2017-10-31 | 2017-11-03 | 3 |  | 3 | 2017-11-21 |  | -30724 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-01 | 2018-03-02 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2246432 | 1748 | 15.2 | PV | 65-H6 | 2017-10-16 | 2017-10-26 | 8 |  | 8 | 2017-11-21 |  | -30724 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-05-02 | [6 empty] | 0 |  | 0
NSTAR | Waltham | 2246565 | 2451 | 366.3 | PV | 282-H5 | 2017-08-11 | 2017-10-27 | 55 |  | 55 | 2017-11-29 |  | -30730 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Falmouth | 2246979 | 2536 | 1500 | PV | 4-98A-98A | 2017-10-12 | 2017-11-07 | 18 |  | 18 | 2017-11-29 |  | -30730 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-22 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2246980 | 2770 | 1000 | PV | 3-85-85 | 2017-10-27 | 2017-11-07 | 7 |  | 7 | 2017-11-29 | 2018-11-06 | 244 |  | 244 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-06 |  |  |  | STD |  |  |  | 0 |  | 0 |  |  |  |  | Private
NSTAR | Wareham | 2247147 | 2571 | 26.35 | PV | 3-85-85 | 2017-10-20 | 2017-10-26 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 2247148 | 2121 | 57.6 | PV | 483-H3 | 2017-10-20 | 2017-10-27 | 5 |  | 5 | 2017-11-29 |  | -30730 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | 2018-01-16 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2247317 | 2421 | 840 | PV | TBD | 2017-11-29 | 2017-11-30 | 1 | 0 | 1 | 2017-12-05 | 2018-02-09 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2017-12-28 |  | 2018-07-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2017-12-29 | Withdrawn
NSTAR | Fairhaven | 2247327 | 2719 | 53.3 | PV | 2-240-240 | 2017-10-24 | 2017-11-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-03-29 | Online
NSTAR | Kingston | 2247506 | 2364 | 23 | PV | 3-18-36J1 | 2017-10-10 | 2017-11-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-01-09 | Online
NSTAR | Edgartown | 2247507 | 2539 | 133.2 | PV | 4-97-97 | 2017-10-23 | 2017-11-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-01 | Online
NSTAR | Wareham | 2247812 | 2571 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-07-11 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Carver | 2247816 | 2330 | 1500 | PV | 3-10-10 | 2017-10-27 | 2017-11-08 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-19 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2247819 | 2571 | 8300 | PV & Battery | 3-83-83 | 2017-11-09 | 2017-11-23 | 10 |  | 10 | 2017-12-06 |  | -30735 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-12-16 | Online
NSTAR | Hopkinton | 2249982 | 1748 | 84 | PV | 126-H4 | 2017-10-19 | 2017-10-19 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-08 | Online
NSTAR | Canton | 2250080 | 2021 | 964 | PV | 470-H10 | 2017-10-18 | 2017-11-15 | 20 |  | 20 | 2017-12-06 |  | -30735 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-18 | [7 empty] | 0 |  | 0 |  |  | 2020-07-23 | Online
NSTAR | Burlington | 2250081 | 1803 | 34.8 | PV | 391-H2 | 2017-11-09 | 2017-11-14 | 3 |  | 3 | 2017-12-06 |  | -30735 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | 2018-03-22 | [6 empty] | 0 |  | 0 |  |  | 2018-06-07 | Online
NSTAR | Carver | 2250250 | 2330 | 8300 | PV & Battery | 3-81-81 | 2017-11-14 | 2017-11-14 | 0 |  | 0 | 2017-12-06 |  | -30735 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Somerville | 2250465 | 2144 | 100.8 | PV | 1604 | 2017-11-14 | 2017-11-29 | 11 |  | 11 | 2017-12-07 |  | -30736 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-02 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Assonett | 2250466 | 2702 | 15.2 | PV | 2-605-605 | 2017-11-14 | 2017-11-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-12 | Online
NSTAR | Somerville | 2250669 | 2143 | 150 | PV | 387-148H2 | 2017-11-10 | 2017-11-14 | 2 |  | 2 | 2017-12-08 |  | -30737 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-26 | 2018-03-12 | [6 empty] | 0 |  | 0
NSTAR | Acton | 2250671 | 1720 | 66 | PV | 416-H4 | 2017-11-08 | 2017-11-17 | 7 |  | 7 | 2017-12-08 |  | -30737 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-07 | 2018-02-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-30 | Online
NSTAR | Duxbury | 2251155 | 2332 | 300 | PV | 3-26-903 | 2017-11-17 | 2017-11-17 | 0 |  | 0 | 2017-12-12 |  | -30739 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2251157 | 2421 | 21.11 | PV | 320-H5XY | 2017-11-13 | 2017-11-17 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-25 | Online
NSTAR | Kingston | 2251317 | 2364 | 232 | PV | 3-17-17 | 2017-10-15 | 2017-11-21 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-16 | Online
NSTAR | Hyannis | 2251318 | 2601 | 250 | PV | 4-63-63 | 2017-11-10 | 2017-11-21 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-08 | Online
NSTAR | Plymouth | 2251494 | 2360 | 20 | PV | 40613 | 2017-11-15 | 2017-11-21 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-20 | Online
NSTAR | Orleans | 2251495 | 2653 | 64 | PV | 4-94A-633 | 2017-10-15 | 2017-11-17 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-12-21 | 2018-01-11 | [6 empty] | 0 |  | 0 |  |  | 2018-04-20 | Online
NSTAR | Natick | 2252677 | 1760 | 1700 | CHP | 23-1339H2 | 2017-12-01 | 2017-12-19 | 12 |  | 12 | 2017-12-20 |  | -30745 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 2252869 | 2536 | 19.3 | PV | 4-98B-449 | 2017-11-10 | 2017-11-30 | 14 |  | 14 | 2017-12-21 |  | -30746 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 | 2018-02-01 | [6 empty] | 0 |  | 0 |  |  | 2018-10-05 | Online
NSTAR | Millis | 2253053 | 2054 | 46 | PV | 146-H10 | 2017-11-22 | 2017-11-28 | 4 |  | 4 | 2017-12-22 |  | -30747 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-21 | 2018-03-27 | [6 empty] | 0 |  | 0
NSTAR | Millis | 2253054 | 2054 | 40.25 | PV | 146-H10 | 2017-11-22 | 2017-11-28 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2253056 | 2021 | 432.9 | PV | 470-H4 | 2017-11-24 | 2017-12-05 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-12-05 | Online
NSTAR | Newton | 2253263 | 2465 | 24.95 | PV | 282-H9 | 2017-10-30 | 2017-12-05 | 26 |  | 26 | 2018-12-27 |  | -31011 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-12 | [7 empty] | 0 |  | 0 |  |  | 2018-12-11
NSTAR | Somerville | 2253264 | 2144 | 52.2 | PV | 1604 | 2017-11-10 | 2017-12-12 | 22 |  | 22 | 2017-12-28 |  | -30751 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | [7 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Wareham | 2253372 | 2576 | 4320 | PV & Battery | 3-83-83 | 2017-11-10 | 2017-12-07 | 19 |  | 19 | 2017-12-28 |  | -30751 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2253373 | 2144 | 72 | PV | 1604 | 2017-11-10 | 2017-12-07 | 19 |  | 19 | 2017-12-28 |  | -30751 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-11-07 | Online
NSTAR | Somerville | 2253374 | 2144 | 50.4 | PV | 1604 | 2017-11-10 | 2017-12-12 | 22 |  | 22 | 2017-12-28 |  | -30751 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | [7 empty] | 0 |  | 0 |  |  |  | Online
NSTAR | Hopkinton | 2255236 | 1748 | 18 | PV | 126-H1 | 2017-11-30 | 2017-12-07 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-04-03 | Online
NSTAR | Norfolk | 2255237 | 2056 | 152 | PV | 146-H3 | 2017-12-08 | 2017-12-18 | 6 |  | 6 | 2018-01-03 |  | -30755 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-08-15 | Online
NSTAR | Bedford | 2255723 | 1730 | 138 | PV | 533-H7 | 2017-12-01 | 2017-12-12 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2255727 | 2330 | 5980 | PV & Battery | 3-83-83 | 2017-11-20 | 2017-12-11 | 15 |  | 15 | 2018-01-08 |  | -30758 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Fairhaven | 2255728 | 2719 | 3750 | PV | 2-221-221 | 2017-12-04 | 2017-12-11 | 5 |  | 5 | 2018-01-08 |  | -30758 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-24 | 2018-04-23 | -3 |  | 0 |  |  | 0 |  | 0 | 2018-09-26 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2021-09-15 | Online
NSTAR | Plymouth | 2257795 | 2360 | 480 | PV | 3-13-943 | 2017-12-12 | 2017-12-18 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-07-30 | Online
NSTAR | Stoneham | 2257799 | 2180 | 15.95 | PV | 375-H8 | 2017-12-05 | 2017-12-11 | 4 |  | 4 | 2018-01-09 | 2018-11-01 | 212 |  | 212 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-01 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2258018 | 2571 | 15.2 | PV | 3-84-968 | 2017-12-12 | 2017-12-15 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | 2258119 | 2136 | 19.6 | PV | 60-1409H1 | 2017-12-13 | 2017-12-18 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | 2258239 | 2081 | 218.5 | PV | 146-H1 | 2017-10-31 | 2017-12-18 | 34 |  | 34 | 2018-01-11 |  | -30761 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-11 |  | -30761 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Stoneham | 2258388 | 2180 | 17.575 | PV | 375-H8 | 2017-12-18 | 2017-12-21 | 3 |  | 3 | 2018-01-12 |  | -30762 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2258392 | 2458 | 199.8 | PV | 467-H3 | 2017-12-15 | 2017-12-22 | 5 |  | 5 | 2018-01-12 |  | -30762 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-14 | 2018-03-16 | [6 empty] | 0 |  | 0 |  |  | 2019-01-28 | Online
NSTAR | Boston | 2258582 | 2136 | 992 | PV | 344-1413H1 | 2017-12-22 | 2018-01-03 | 8 |  | 8 | 2018-01-17 |  | -30765 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-23 | Online
NSTAR | Rochester | 2258583 | 2770 | 7415 | PV |  | 2018-01-12 | 2018-01-17 | 3 | 0 | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-17 | 2020-01-07 | 514 | 234 | 280 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-05-17 |  | 2019-06-28 | No |  | 60 |  |  | 0 |  | 0 |  |  | 2023-01-19 | Online | Private | N
NSTAR | Assonett | 2258821 | 2702 | 16.7 | PV | 2-605-605 | 2017-12-18 | 2017-12-28 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 2258823 | 2130 | 23 | PV | 284-02 | 2017-12-21 | 2017-12-28 | 5 |  | 5 | 2018-01-17 |  | -30765 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Dennis | 2259134 | 2660 | 149.5 | PV | 4-92B-92B | 2017-10-23 | 2017-12-28 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-03-12
NSTAR | Allston | 2259136 | 2134 | 99.9 | PV | 456-H3 | 2017-12-02 | 2017-12-14 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-06 | 2018-02-22 | [6 empty] | 0 |  | 0 |  |  | 2018-07-23 | Online
NSTAR | Rochester | 2259340 | 2770 | 3320 | PV | TBD | 2018-01-18 |  | -30766 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-01-23 | 2019-09-30 | 439 | 160 | 279 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-05-07 |  | 2019-06-30 | No | TBD | 60 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Cambridge | 2259341 | 2138 | 13.6 | PV & Battery | 821-22 | 2017-12-14 | 2018-01-03 | 14 |  | 14 | 2018-01-22 |  | -30768 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-05-03 | [6 empty] | 0 |  | 0
NSTAR | Vineyard Haven | 2259526 | 2658 | 20 | PV | 4-91-228 | 2017-10-16 | 2018-01-04 | 58 |  | 58 | 2018-01-25 |  | -30771 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Cambridge | 2259745 | 2139 | 76.6 | PV | 814-13 | 2017-12-14 | 2018-01-03 | 14 |  | 14 | 2018-01-23 |  | -30769 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-03-05 | [6 empty] | 0 |  | 0
NSTAR | Dorchester | 2259746 | 2122 | 51.75 | PV | 466-1481H1 | 2017-12-12 | 2018-01-03 | 16 |  | 16 | 2018-01-23 |  | -30769 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-14 | 2018-03-28 | [6 empty] | 0 |  | 0 |  |  | 2018-08-02 | Online
NSTAR | Cambridge | 2259916 | 2138 | 53.3 | PV | 830-11 | 2017-12-14 | 2018-01-03 | 14 |  | 14 | 2018-01-24 |  | -30770 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-04-19 | [6 empty] | 0 |  | 0
NSTAR | Lincoln | 2260143 | 1773 | 43.8 | PV | 320-H1 | 2017-10-16 | 2018-01-03 | 57 |  | 57 | 2018-01-25 |  | -30771 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-27 | 2018-03-05 | [6 empty] | 0 |  | 0 |  |  | 2018-09-18 | Online
NSTAR | Wareham | 2260144 | 2571 | 7310 | PV & Battery | 3-83-83 | 2017-11-16 | 2018-01-11 | 40 |  | 40 | 2018-01-25 |  | -30771 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2260285 | 1760 | 40.25 | PV | 433-H5 | 2017-12-28 | 2017-12-28 | 0 |  | 0 | 2018-01-26 |  | -30772 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-13 | 2018-04-18 | [6 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
NSTAR | Woburn | 2260286 | 1801 | 23.4 | PV | 325-03 | 2017-12-26 | 2018-01-05 | 8 |  | 8 | 2018-01-26 |  | -30772 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bourne | 2260502 | 2559 | 32 | PV | 4-86-86 | 2017-12-28 | 2018-01-08 | 7 |  | 7 | 2018-01-29 |  | -30773 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-27 | 2018-04-02 | [6 empty] | 0 |  | 0 |  |  | 2018-05-15 | Online
NSTAR | Hopkinton | 2260503 | 1748 | 4000 | PV | 126-H4 | 2017-12-19 | 2018-01-09 | 15 |  | 15 | 2018-01-29 |  | -30773 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-03 |  | -30907 |  | 0 |  |  | 0 |  | 0 | 2017-07-28 | 2017-08-31 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2260699 | 2571 | 8300 | PV & Battery | 3-83-83 | 2018-01-09 | 2018-01-09 | 0 |  | 0 | 2018-01-30 |  | -30774 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2260702 | 2770 | 540 | PV | TBD | 2018-01-29 |  | -30773 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-09-04 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Rochester | 2260703 | 2770 | 2540 | PV |  | 2018-01-29 | 2018-01-31 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-01-31 |  | -30775 | 394 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-03-20 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Carver | 2260848 | 2330 | 6415 | PV | 3-10-917 | 2017-12-11 | 2018-01-02 | 16 |  | 16 | 2018-01-31 |  | -30775 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2261351 | 1801 | 15.2 | PV | 375-H12 | 2018-01-03 | 2018-01-29 | 18 |  | 18 | 2018-02-01 |  | -30776 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-11 | [7 empty] | 0 |  | 0 |  |  | 2019-09-27 | Online
NSTAR | Canton | 2261355 | 2021 | 288 | PV | 269-1321H2 | 2018-01-09 | 2018-01-17 | 6 |  | 6 | 2018-02-01 | 2018-11-20 | 208 |  | 208 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-21 | [6 empty] | 0 |  | 0 |  |  | 2019-05-30 | Online | Private
NSTAR | Acton | 2261525 | 1720 | 143.2 | PV | 416-H4 | 2017-06-07 | 2018-01-11 | 156 |  | 156 | 2018-01-11 |  | -30761 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-28 | [7 empty] | 0 |  | 0 |  |  |  | Online
NSTAR | Sudbury | 2261526 | 1776 | 29.58 | PV | 342-H7 | 2017-12-04 | 2018-01-19 | 34 |  | 34 | 2018-02-02 |  | -30777 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-05-23 | [6 empty] | 0 |  | 0 |  |  | 2018-07-24 | Online
NSTAR | Wayland | 2261527 | 1778 | 15.2 | PV | 433-H6 | 2017-12-12 | 2018-01-19 | 28 |  | 28 | 2018-02-02 |  | -30777 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-05-22 | [6 empty] | 0 |  | 0 |  |  | 2018-07-23 | Online
NSTAR | Medway | 2261707 | 2053 | 22.95 | PV | 65-H5 | 2017-12-14 | 2018-01-19 | 26 |  | 26 | 2018-02-06 |  | -30779 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Osterville | 2262127 | 2665 | 36 | PV | 4-80A-892 | 2018-01-09 | 2018-01-17 | 6 |  | 6 | 2018-02-08 |  | -30781 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2018-08-08 | Online
NSTAR | Millis | 2262130 | 2054 | 97.75 | PV | 146-H10 | 2017-12-01 | 2018-01-23 | 37 |  | 37 | 2018-02-07 |  | -30780 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-29 | 2018-04-09 | [6 empty] | 0 |  | 0 |  |  | 2018-09-12 | Online
NSTAR | East Freetown | 2262266 | 2717 | 15.95 | PV | 2-107-107 | 2018-01-16 | 2018-01-23 | 5 |  | 5 | 2018-02-08 |  | -30781 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-28 | 2018-04-02 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2262268 | 1754 | 133.2 | PV | 416-H6 | 2018-01-22 | 2018-01-24 | 2 |  | 2 | 2018-02-08 |  | -30781 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-05-11 | [6 empty] | 0 |  | 0 |  |  | 2018-08-14 | Online
NSTAR | Maynard | 2262282 | 1754 | 133.2 | PV | 416-H6 | 2018-01-22 | 2018-01-24 | 2 |  | 2 | 2018-02-08 |  | -30781 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 2262431 | 2492 | 18.56 | PV | 148-01 | 2017-12-22 | 2018-01-25 | 24 |  | 24 | 2018-02-09 |  | -30782 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-15 | 2018-05-22 | [6 empty] | 0 |  | 0 |  |  | 2018-08-07 | Online
NSTAR | Waltham | 2262433 | 2465 | 80.5 | PV | 282-H9 | 2018-01-02 | 2018-01-26 | 18 |  | 18 | 2018-02-09 |  | -30782 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-15 | 2018-05-17 | [6 empty] | 0 |  | 0 |  |  | 2018-08-09 | Online
NSTAR | Brookline | 2262436 | 2445 | 21.9 | PV | 496-H4 | 2017-10-09 | 2018-01-29 | 80 |  | 80 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-02 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2019-01-03 | Online
NSTAR | Natick | 2262597 | 1760 | 37.5 | PV | 433-H12 | 2018-01-16 | 2018-01-29 | 9 |  | 9 | 2018-02-12 |  | -30783 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | 2018-05-11 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
NSTAR | Oak Bluffs | 2262599 | 2557 | 90 | PV | 4-99-99 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-12-06
NSTAR | Provincetown | 2262605 | 2657 | 276.6 | PV | 4-96-675 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-25 | 2018-05-02 | [6 empty] | 0 |  | 0 |  |  | 2020-04-29 | Online
NSTAR | Truro | 2262805 | 2666 | 80 | PV | 4-96-674 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-11-04 | Online
NSTAR | Eastham | 2262807 | 2642 | 109.8 | PV | 4-94A-648 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-16 | Online
NSTAR | Chatham | 2262808 | 2633 | 86.4 | PV | 4-95B-940 | 2018-01-24 | 2018-01-30 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-22 | 2018-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-10-31
NSTAR | Sherborn | 2262993 | 1770 | 110 | PV | 274-H4 | 2017-11-17 | 2018-02-01 | 54 |  | 54 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2015-04-25 | 2018-06-29 | [6 empty] | 0 |  | 0 |  |  | 2018-04-25
NSTAR | Eastham | 2262994 | 2642 | 83 | PV | 4-94b-646 | 2018-01-13 | 2018-02-16 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-05-23 | Online
NSTAR | Plympton | 2262995 | 2367 | 2310 | PV & Battery |  | 2018-02-13 | 2018-02-27 | 10 | 0 | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-05 | 2018-08-24 | 124 | 96 | 28 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-08-28 |  | 2020-03-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Wareham | 2263854 | 2532 | 4875 | PV | 3-85-928 | 2018-01-26 | 2018-02-02 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 2263856 | 2675 | 104.4 | PV | 4-92A-536 | 2018-01-24 | 2018-02-02 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-06-27 | [6 empty] | 0 |  | 0 |  |  | 2019-11-08 | Online
NSTAR | West Roxbury | 2263857 | 2132 | 588 | PV | 496-H3 | 2018-02-01 | 2018-02-05 | 2 |  | 2 | 2018-02-05 |  | -30778 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Framingham | 2264047 | 1702 | 125 | PV | 2410 | 2018-01-16 | 2018-02-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-04 | [7 empty] | 0 |  | 0 |  |  | 2019-04-22 | Online
NSTAR | Boston | 2264049 | 2118 | 109.25 | PV | 318-10 | 2018-02-02 | 2018-02-08 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-05-18 | [6 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2264227 | 2664 | 33.6 | PV | 4-92A-562 | 2018-02-07 | 2018-02-12 | 3 |  | 3 | 2018-02-23 |  | -30792 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-06-21 | [6 empty] | 0 |  | 0
NSTAR | Dartmouth | 2264231 | 2747 | 178 | PV | 2-532-532 | 2018-01-29 | 2018-02-14 | 12 |  | 12 | 2018-02-23 |  | -30792 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-12 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2018-06-19 | Online
NSTAR | Dartmouth | 2264232 | 2747 | 178 | PV | 2-532-532 | 2018-01-29 | 2018-02-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-06-04
NSTAR | Cambridge | 2264395 | 2140 | 466.2 | PV | 828-1382 | 2018-02-02 | 2018-02-15 | 9 |  | 9 | 2018-02-26 | 2018-03-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-23 | 2018-06-14 |  |  | EXP |  |  |  | 0 |  | 0 | 2018-11-19 | 2018-11-19 | 2018-11-20 | Online
NSTAR | Canton | 2264634 | 2021 | 700 | PV | 470-H7 | 2014-06-12 | 2014-06-12 | 0 | 0 | 0 | 2014-06-16 | 2014-06-24 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2014-08-21 |  | 2015-01-21 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2019-12-23 | Online | Private
NSTAR | Dartmouth | 2264640 | 2747 | 1500 | PV | 2-107-107 | 2018-02-26 | 2018-02-27 | 1 | 0 | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-28 | 2020-05-04 | 568 | 122 | 446 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-10-12 |  | 2019-06-14 | TBD |  | 60 |  |  | 0 |  | 0 |  | 2019-06-11 | 2019-06-11 | Online | Private
NSTAR | Woburn | 2264643 | 1801 | 50 | PV | 211-H6 | 2018-01-26 | 2018-02-15 | 14 |  | 14 | 2018-02-27 |  | -30794 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-11 | 2018-05-18 | [6 empty] | 0 |  | 0 |  |  | 2018-10-19
NSTAR | Yarmouth | 2264855 | 2664 | 52.2 | PV | 4-92a-562 | 2018-01-24 | 2018-02-15 | 16 |  | 16 | 2018-02-28 |  | -30795 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-15 | [6 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
NSTAR | Rochester | 2264857 | 2770 | 4650 | PV |  | 2018-02-27 | 2018-03-01 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-03-05 |  | -30798 | 660 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2018-05-11
NSTAR | Walpole | 2265026 | 2032 | 2370 | PV | 146-H6 | 2018-02-16 | 2018-04-03 | 32 |  | 32 | 2018-03-01 |  | -30796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2018-03-01 | 30795 |  | 30795 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2265032 | 2118 | 30 | PV | 323-175H | 2018-02-02 | 2018-08-23 | 144 |  | 144 | 2018-08-23 |  | -30921 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-25 | [7 empty] | 0 |  | 0
NSTAR | Milton | 2265246 | 2186 | 15.2 | PV | 362-02 | 2018-02-09 | 2018-02-16 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2265247 | 2576 | 201.6 | PV | 3-83-83 | 2018-02-05 | 2018-02-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-09 | [6 empty] | 0 |  | 0 |  |  | 2020-03-17 | Online
NSTAR | Cambridge | 2267013 | 2138 | 100.8 | PV | 829-19 | 2018-01-09 | 2018-02-20 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-11-05 | Online
NSTAR | Cambridge | 2267217 | 2138 | 66.6 | PV | 814-13 | 2018-02-08 | 2018-02-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-12 | [7 empty] | 0 |  | 0 |  |  | 2018-12-05 | Online
NSTAR | Plymouth | 2267338 | 2360 | 272 | PV | 3-71-937 | 2017-11-30 | 2018-02-07 | 49 |  | 49 | 2018-03-23 |  | -30812 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-18 | 2018-04-30 | [6 empty] | 0 |  | 0 |  |  | 2018-08-17 | Online
NSTAR | Boston | 2267381 | 2135 | 75 | Gas Turbine | 548-193 | 2017-12-21 | 2018-02-21 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-08-27 | Online
NSTAR | Somerville | 2267712 | 2143 | 42 | PV | 250-1N81H1 | 2018-02-14 | 2018-02-28 | 10 |  | 10 | 2018-03-23 |  | -30812 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-30 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2019-07-17 | Online
NSTAR | Dorchester | 2267902 | 2121 | 43.2 | PV | 483-H5 | 2018-02-28 | 2018-02-28 | 0 |  | 0 | 2018-03-26 |  | -30813 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-19
NSTAR | Westport | 2268194 | 2748 | 5000 | PV & Battery | 2-523-523 | 2018-02-15 | 2018-02-23 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0
NSTAR | Norfolk | 2268196 | 2056 | 66.6 | PV | 146-H3 | 2018-02-21 | 2018-02-28 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-02-08 | 2018-05-03 | [6 empty] | 0 |  | 0 |  |  | 2018-12-04 | Online
NSTAR | New Bedford | 2268420 | 2745 | 120 | PV | 2-104-104 | 2018-02-21 | 2018-03-15 | 16 |  | 16 | 2018-03-28 |  | -30815 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online | Private
NSTAR | New Bedford | 2268649 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268650 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268651 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268866 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2268869 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | New Bedford | 2269021 | 2745 | 120 | PV | 2-102-102 | 2018-02-21 | 2018-03-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-26 | 2018-05-08 | [6 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Rochester | 2269022 | 2770 | 1250 | PV | TBD | 2018-03-30 |  | -30817 | 0 | 0 | 2018-04-02 | 2020-07-20 | 600 | 572 | 28 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Sudbury | 2269609 | 1776 | 240 | PV | 342-H5 | 2018-02-21 | 2018-03-16 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-25 | 2018-05-10 | [6 empty] | 0 |  | 0 |  |  | 2019-10-25 | Online
NSTAR | Dartmouth | 2269612 | 2747 | 1000 | PV | 2-532-532 | 2018-02-02 | 2018-03-05 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-31 | [7 empty] | 0 |  | 0
NSTAR | Dover | 2269886 | 2030 | 25 | PV | 456-H5 | 2018-02-23 | 2018-03-06 | 7 |  | 7 | 2018-04-04 |  | -30820 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-05-15 | [6 empty] | 0 |  | 0 |  |  | 2018-07-19 | Online
NSTAR | Dartmouth | 2269896 | 2747 | 8300 | PV & Battery | 2-532-532 | 2018-02-02 | 2018-03-06 | 22 |  | 22 | 2018-04-05 |  | -30821 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2270084 | 2747 | 8300 | PV & Battery | 2-532-532 | 2018-02-02 | 2018-03-06 | 22 |  | 22 | 2018-04-05 |  | -30821 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Dartmouth | 2270087 | 2747 | 520 | PV & Battery | 2-525-525 | 2018-02-27 | 2018-03-12 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-31 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2270295 | 2364 | 150 | PV | 3-26-902 | 2018-02-22 | 2018-03-07 | 9 |  | 9 | 2018-04-09 |  | -30823 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-09 | 2018-05-16 | [6 empty] | 0 |  | 0
NSTAR | Marion | 2270301 | 2738 | 17.6 | PV | 2-304-304 | 2018-03-08 | 2018-03-09 | 1 |  | 1 | 2018-04-09 |  | -30823 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-23 | 2018-06-25 | [6 empty] | 0 |  | 0 |  |  | 2018-08-02 | Online
NSTAR | New Bedford | 2270504 | 2744 | 599.4 | PV | 2-54-54 | 2018-01-22 | 2018-03-14 | 37 |  | 37 | 2018-04-09 |  | -30823 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-15 | 2018-06-22 | [6 empty] | 0 |  | 0 |  |  | 2019-07-19 | Online
NSTAR | Fairhaven | 2270747 | 2719 | 8300 | PV & Battery | 2-241-241 | 2018-03-01 | 2018-03-14 | 9 |  | 9 | 2018-04-11 |  | -30825 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2270749 | 2743 | 5000 | PV |  | 2018-04-09 | 2018-04-11 | 2 | 0 | 2 | 2018-04-11 |  | -30825 | 681 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2018-04-12
NSTAR | Millis | 2270750 | 2054 | 199.8 | PV | 65-H1 | 2018-02-23 | 2018-03-16 | 15 |  | 15 | 2018-04-11 |  | -30825 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-06-14 | [6 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Framingham | 2270751 | 1702 | 528 | PV | 519-175H1 | 2018-01-31 | 2018-03-21 | 35 |  | 35 | 2018-04-11 | 2018-11-29 | 166 |  | 166 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-11-29 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2021-06-28 | Online | Private
NSTAR | Acton | 2271183 | 1720 | 5040 | PV & Battery | 416-H9 | 2018-03-01 | 2018-03-21 | 14 |  | 14 | 2018-04-12 |  | -30826 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0 |  |  | 2022-06-16 | Online
NSTAR | Chilmark | 2271199 | 2535 | 40.35 | PV | 4-97-226 | 2018-02-06 | 2018-03-21 | 31 |  | 31 | 2018-04-12 |  | -30826 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-05-24 | [6 empty] | 0 |  | 0
NSTAR | Brewster | 2271201 | 2631 | 250 | PV | 4-89B-576 | 2018-03-01 | 2018-03-22 | 15 |  | 15 | 2018-04-12 |  | -30826 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-10 | 2018-07-16 | [6 empty] | 0 |  | 0 |  |  | 2019-05-16 | Online
NSTAR | Wellfleet | 2271202 | 2663 | 48.56 | PV | 4-96-960 | 2018-02-26 | 2018-03-23 | 19 |  | 19 | 2018-04-12 |  | -30826 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-25 | [6 empty] | 0 |  | 0
NSTAR | Brewster | 2271377 | 2631 | 250 | PV | 4-89B-576 | 2018-03-01 | 2018-03-26 | 17 |  | 17 | 2018-04-13 |  | -30827 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-10 | [6 empty] | 2018-07-16 | 30892 |  | 30892 |  |  | 2019-05-16 | Online
NSTAR | Walpole | 2271379 | 2081 | 480 | PV | 146-H6 | 2018-03-16 | 2018-03-26 | 6 |  | 6 | 2018-04-13 |  | -30827 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2271383 | 2360 | 4986 | PV | 3-89-922 | 2018-03-12 | 2018-03-27 | 11 |  | 11 | 2018-04-13 |  | -30827 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 2271557 | 2743 | 9878 | PV & Battery | 2-106-160 | 2018-03-19 | 2018-03-28 | 7 |  | 7 | 2018-04-16 |  | -30828 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Boston | 2271561 | 2163 | 56 | PV | 821-05 | 2018-03-21 | 2018-03-29 | 6 |  | 6 | 2018-04-16 |  | -30828 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0
NSTAR | Cambridge | 2272015 | 2138 | 16 | PV | 821-05 | 2018-03-21 | 2018-03-29 | 6 |  | 6 | 2018-04-17 |  | -30829 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-04 | [6 empty] | 0 |  | 0 |  |  | 2018-12-26
NSTAR | Cambridge | 2272017 | 2138 | 32 | PV | 821-05 | 2018-03-21 | 2018-03-29 | 6 |  | 6 | 2018-04-17 |  | -30829 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-01 | 2018-06-04 | [6 empty] | 0 |  | 0 |  |  | 2018-12-27
NSTAR | Orleans | 2272019 | 2653 | 23.1 | PV | 4-83-952 | 2018-03-26 | 2018-03-29 | 3 |  | 3 | 2018-04-17 |  | -30829 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-08 | 2018-06-11 | [6 empty] | 0 |  | 0 |  |  | 2018-08-20 | Online
NSTAR | Watertown | 2272442 | 2472 | 166.5 | PV | 467-H6 | 2018-03-16 | 2018-03-29 | 9 |  | 9 | 2018-03-29 |  | -30816 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0 |  |  | 2018-12-11
NSTAR | Acton | 2272445 | 1720 | 2100 | PV & Battery | 416-H2 | 2018-03-23 | 2018-04-04 | 8 |  | 8 | 2018-04-19 |  | -30831 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-25 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Hopkinton | 2272446 | 1748 | 19 | PV | 130-H1 | 2018-03-01 | 2018-04-03 | 23 |  | 23 | 2018-04-19 |  | -30831 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-05 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  | 2020-04-07 | Online
NSTAR | Carver | 2272654 | 2330 | 104.4 | PV | 3-81-81 | 2018-03-16 | 2018-04-03 | 12 |  | 12 | 2018-04-20 |  | -30832 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-30 | 2018-06-18 | [6 empty] | 0 |  | 0 |  |  | 2021-06-18 | Online
NSTAR | Holliston | 2272656 | 1746 | 7.6 | PV | 274-H3 | 2018-04-04 | 2018-04-09 | 3 |  | 3 | 2018-04-20 |  | -30832 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-04 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online
NSTAR | Carver | 2272658 | 2330 | 2980 | PV & Battery | 3-10-10 | 2018-03-27 | 2018-04-05 | 7 |  | 7 | 2018-04-20 |  | -30832 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 2272821 | 1748 | 86.25 | PV | 4-92A-558 | 2018-03-29 | 2018-04-09 | 7 |  | 7 | 2018-04-23 |  | -30833 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-07-16 | [6 empty] | 0 |  | 0 |  |  | 2018-12-14
NSTAR | Hopkinton | 2272822 | 1748 | 86.25 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-23 |  | -30833 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-21 | 2018-07-17 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2273069 | 1748 | 51.75 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-24 |  | -30834 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 2273079 | 1748 | 51.75 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-24 |  | -30834 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-06-25 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2273089 | 1748 | 25 | PV | 65-H6 | 2018-03-30 | 2018-04-09 | 6 |  | 6 | 2018-04-24 |  | -30834 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-06-25 | [6 empty] | 0 |  | 0
NSTAR | New Bedford | 2273298 | 2745 | 1384 | PV |  | 2018-04-24 | 2018-04-25 | 1 | 0 | 1 | 2018-05-04 | 2018-10-03 | 108 | 0 | 108 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-07-10 | 2019-04-30 | 2020-02-28 | TBD | EXP | 30 | 2020-02-27 |  | -31316 |  | 0 |  |  |  | In Queue | Private
NSTAR | Dartmouth | 2273508 | 2747 | 4999 | PV | 2-107-107 | 2018-04-04 | 2018-04-11 | 5 |  | 5 | 2018-04-26 |  | -30836 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-22 | 2018-12-18 | [6 empty] | 0 |  | 0
NSTAR | Canton | 2273509 | 2021 | 240 | PV | 269-1321H2 | 2018-02-20 | 2018-04-12 | 37 |  | 37 | 2018-04-26 | 2018-04-26 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-12-13 | [6 empty] | 0 |  | 0
NSTAR | Chelsea | 2273722 | 2150 | 153.2 | PV | 488-H6 | 2018-03-22 | 2018-04-12 | 15 |  | 15 | 2018-04-27 |  | -30837 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chelsea | 2273723 | 2150 | 196.6 | PV | 488-H7 | 2018-03-22 | 2018-04-12 | 15 |  | 15 | 2018-04-27 | 2018-11-20 | 147 |  | 147 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-27 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-03-26 | Online
NSTAR | Hopkinton | 2273879 | 1748 | 74 | PV | 65-H6 | 2018-03-30 | 2018-04-11 | 8 |  | 8 | 2018-05-01 |  | -30839 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-21 | 2018-07-17 | [6 empty] | 0 |  | 0
NSTAR | Canton | 2273880 | 2021 | 610 | PV | 470-H1 | 2018-04-05 | 2018-04-12 | 5 |  | 5 | 2018-05-01 |  | -30839 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-11 | [7 empty] | 0 |  | 0 |  |  | 2020-03-12 | Online
NSTAR | Woburn | 2274149 | 1801 | 180 | PV | 375-H10 | 2016-10-26 | 2016-11-02 | 5 |  | 5 | 2016-12-06 |  | -30474 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-06 | 2017-03-15 | [6 empty] | 0 |  | 0 |  |  | 2018-08-23 | Online
NSTAR | Framingham | 2274154 | 1702 | 198 | PV | 2411 | 2018-04-13 | 2018-04-17 | 2 |  | 2 | 2018-05-01 |  | -30839 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-08 | [7 empty] | 0 |  | 0 |  |  | 2018-11-13 | Online
NSTAR | Westport | 2274155 | 2790 | 4500 | PV | 2-532-532 | 2018-03-02 | 2018-04-15 | 30 |  | 30 | 2018-05-01 |  | -30839 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 2274401 | 2743 | 4990 | PV & Battery | 2-241-241 | 2018-04-04 | 2018-04-16 | 8 |  | 8 | 2018-05-02 |  | -30840 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2274408 | 2770 | 1000 | PV | 3-703-703 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-02 |  | -30840 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Westport | 2274649 | 2790 | 8300 | PV & Battery | 2-523-523 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-04 |  | -30842 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | Freetown | 2274652 | 2702 | 8300 | PV & Battery | 2-605-605 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-04 |  | -30842 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2274654 | 2360 | 3750 | PV & Battery | 3-89-89 | 2018-04-11 | 2018-04-17 | 4 |  | 4 | 2018-05-04 |  | -30842 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-04-27 | Online
NSTAR | Vineyard Haven | 2275151 | 2568 | 5666.1 | PV & Battery | 4-75-75 | 2016-01-19 | 2016-02-08 | 14 |  | 14 | 2016-02-08 |  | -30258 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-05-31 | 2017-05-31 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2018-12-14
NSTAR | Wayland | 2275155 | 1778 | 16.32 | PV | 342-H1 | 2018-04-17 | 2018-04-24 | 5 |  | 5 | 2018-05-04 |  | -30842 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-06 | 2018-07-11 | [6 empty] | 0 |  | 0 |  |  | 2018-09-18 | Online
NSTAR | Dorchester | 2275333 | 2122 | 64 | PV | 466-1481H1 | 2018-04-12 | 2018-04-27 | 11 |  | 11 | 2018-05-07 |  | -30843 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-05-16 | Online
NSTAR | Norfolk | 2275667 | 2056 | 15.2 | PV | 146-H3 | 2018-04-09 | 2018-04-24 | 11 |  | 11 | 2018-05-08 |  | -30844 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Somerville | 2276155 | 2143 | 3000 | PV & Battery | 30-179XYH | 2018-04-11 | 2018-05-03 | 16 |  | 16 | 2018-05-10 |  | -30846 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-10 |  | -30955 |  | 0 |  |  | 0 |  | 0 | 2019-04-12 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2276157 | 2143 | 3000 | PV & Battery | 30-179XYH | 2018-04-11 | 2018-05-03 | 16 |  | 16 | 2018-05-10 |  | -30846 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-10 |  | -30955 |  | 0 |  |  | 0 |  | 0 | 2019-04-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2276786 | 1701 | 15.8 | PV | 433-H8 | 2018-03-01 | 2018-04-27 | 41 |  | 41 | 2018-05-15 |  | -30849 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lincoln | 2276951 | 1773 | 250 | PV | 320-H1 | 2018-04-26 | 2018-05-01 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-31 | [7 empty] | 0 |  | 0
NSTAR | Westport | 2277112 | 2790 | 8300 | PV & Battery | 2-522-522 | 2018-04-27 | 2018-05-04 | 5 |  | 5 | 2018-05-17 |  | -30851 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Freetown | 2277113 | 2702 | 8300 | PV & Battery | 2-605-605 | 2018-04-27 | 2018-05-04 | 5 |  | 5 | 2018-05-17 |  | -30851 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2277114 | 2702 | 5000 | PV & Battery | 532 | 2018-04-27 | 2018-05-04 | 5 |  | 5 | 2018-05-17 |  | -30851 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westport | 2277378 | 2790 | 4875 | PV & Battery |  | 2018-05-17 | 2018-05-22 | 3 | 0 | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-22 | 2018-12-26 | 156 | 148 | 8 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2018-10-22 |  | 2020-12-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Acusnet | 2277380 | 2743 | 8980 | PV & Battery | 2-241-241 | 2018-04-11 | 2018-05-04 | 17 |  | 17 | 2018-05-22 |  | -30854 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2277381 | 2330 | 8980 | PV & Battery | 3-81-81 | 2018-04-06 | 2018-05-04 | 20 |  | 20 | 2018-05-22 |  | -30854 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2277865 | 2576 | 3300 | PV & Battery | 3-86-966 | 2018-04-25 | 2018-05-08 | 9 |  | 9 | 2018-05-22 |  | -30854 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-31 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Woburn | 2277867 | 1801 | 130 | PV | 258-1394-H1 | 2018-03-07 | 2018-05-10 | 46 |  | 46 | 2018-05-22 |  | -30854 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-09 | 2018-08-22 | [6 empty] | 0 |  | 0 |  |  | 2018-09-24 | Online
NSTAR | Wareham | 2278333 | 2576 | 201.6 | PV | 3-86-966 | 2018-05-01 | 2018-05-11 | 8 |  | 8 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-05 | 2018-09-17 | [6 empty] | 0 |  | 0
NSTAR | Waltham | 2278335 | 2451 | 210 | Fuel Cell | 450-H2 | 2018-04-05 | 2018-05-15 | 28 |  | 28 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-14 | 2018-07-06 | [6 empty] | 0 |  | 0
NSTAR | Rochester | 2278508 | 2770 | 3345 | PV & Battery | 3-702-702 | 2018-05-14 | 2018-05-15 | 1 |  | 1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Tisbury | 2279017 | 2575 | 22.8 | PV | 4-97-222 | 2018-05-03 | 2018-05-16 | 9 |  | 9 | 2018-05-30 |  | -30860 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-08 | 2018-06-14 | [6 empty] | 0 |  | 0 |  |  | 2018-08-16 | Online
NSTAR | Medway | 2279222 | 2053 | 27.72 | PV | 65-H5 | 2018-04-26 | 2018-05-16 | 14 |  | 14 | 2018-05-31 |  | -30861 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2279224 | 1776 | 249.8 | PV | 342-H2 | 2018-05-11 | 2018-05-16 | 3 |  | 3 | 2018-05-31 |  | -30861 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0
NSTAR | Medfield | 2279225 | 2052 | 264 | PV | 456-H2 | 2018-05-07 | 2018-05-11 | 4 |  | 4 | 2018-06-05 |  | -30864 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-15 | [7 empty] | 0 |  | 0 |  |  | 2019-06-05 | Online
NSTAR | Wayland | 2279425 | 1778 | 21.9 | PV | 342-H1 | 2018-05-04 | 2018-05-16 | 8 |  | 8 | 2018-06-01 |  | -30862 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-07 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2019-03-11
NSTAR | Plympton | 2279426 | 2367 | 2500 | PV & Battery | 3-15-906 | 2018-04-25 | 2018-05-11 | 12 |  | 12 | 2018-06-01 | 2018-11-08 | 114 |  | 114 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-08 | 2018-12-07 |  |  | STD |  |  |  | 0 |  | 0 |  |  | 2023-02-06 | Online | Private
NSTAR | Plympton | 2279636 | 2367 | 4998 | PV & Battery | 3-51-43J1 | 2018-05-04 | 2018-05-17 | 9 |  | 9 | 2018-06-04 |  | -30863 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-06 | [7 empty] | 0 |  | 0 |  |  | 2022-12-29 | Online
NSTAR | Barnstable | 2279638 | 2648 | 4998 | PV & Battery | 4-88-478 | 2018-05-16 | 2018-05-22 | 4 |  | 4 | 2018-06-04 | 2018-11-08 | 113 |  | 113 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-08 | 2018-12-07 | [6 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online | Private
NSTAR | Cambridge | 2280401 | 2142 | 35 | CHP | 875-1399 | 2018-05-15 | 2018-05-22 | 5 |  | 5 | 2018-06-05 |  | -30864 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-20 | 2018-07-18 | [6 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Waltham | 2280855 | 2453 | 780 | PV & Battery | 386-1356 | 2018-05-03 | 2018-05-22 | 13 |  | 13 | 2018-06-07 |  | -30866 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | [7 empty] | 0 |  | 0 |  |  | 2019-10-01 | Online | Private
NSTAR | Acton | 2280862 | 1720 | 1496 | PV & Battery | 416-H1 | 2018-03-01 | 2018-05-23 | 59 |  | 59 | 2018-06-07 |  | -30866 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Wellfleet | 2281067 | 2667 | 700 | PV | 4-96-677 | 2018-05-18 | 2018-05-23 | 3 |  | 3 | 2018-06-08 |  | -30867 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0 |  |  | 2021-12-08 | Online
NSTAR | Westport | 2281069 | 2790 | 995 | Gas Turbine | 2-523-523 | 2018-05-16 | 2018-05-30 | 10 |  | 10 | 2018-06-08 |  | -30867 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2281481 | 2330 | 2000 | PV & Battery |  | 2018-06-11 | 2018-06-12 | 1 | 0 | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-06-13 |  | -30870 | 135 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-05-20 |  | 2019-06-28 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Carver | 2281482 | 2330 | 1000 | PV & Battery | 3-81-950 | 2018-05-18 | 2018-05-30 | 8 |  | 8 | 2018-06-12 |  | -30869 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0
NSTAR | Edgartown | 2282055 | 2539 | 466.6 | PV & Battery | 4-97-97 | 2018-05-29 | 2018-05-31 | 2 |  | 2 | 2018-06-15 |  | -30872 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Framingham | 2282056 | 1707 | 66.6 | PV | 2408 | 2018-05-23 | 2018-05-31 | 6 |  | 6 | 2018-06-15 |  | -30872 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Cambridge | 2282057 | 2138 | 28.8 | PV | 825-18 | 2018-05-29 | 2018-06-01 | 3 |  | 3 | 2018-06-15 |  | -30872 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-24 | [7 empty] | 0 |  | 0 |  |  | 2019-02-04 |  | Private
NSTAR | Barnstable | 2282058 | 2668 | 44.5 | PV | 4-87B-473 | 2018-05-15 | 2018-06-01 | 13 |  | 13 | 2018-06-15 |  | -30872 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-03 | 2018-08-03 | [6 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2282066 | 1707 | 66.6 | PV | 2408 | 2018-05-23 | 2018-05-31 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2282256 | 2576 | 1497 | PV | TBD | 2018-06-15 |  | -30872 | 0 | 0 | 2018-09-22 | 2018-09-28 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-01-25 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Medfield | 2282637 | 2052 | 240 | PV | 456-H2 | 2018-05-30 | 2018-06-04 | 3 |  | 3 | 2018-06-19 |  | -30874 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-15 | 2018-08-23 | [6 empty] | 0 |  | 0 |  |  | 2019-06-10 | Online
NSTAR | Ashland | 2282638 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-19 |  | -30874 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 2282639 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-08 | 2018-06-13 | 3 |  | 3 | 2018-06-28 |  | -30881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0
NSTAR | Ashland | 2282640 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-19 |  | -30874 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 2282847 | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-19 |  | -30874 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2283031 | 2130 | 38 | PV | 350-H11 | 2018-06-04 | 2018-06-06 | 2 |  | 2 | 2018-06-21 |  | -30876 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-01 | [7 empty] | 0 |  | 0 |  |  | 2019-01-22 | Online
NSTAR | Westport | 2283036 | 2790 | 2000 | PV | 2-523-523 | 2018-05-23 | 2018-06-13 | 15 |  | 15 | 2018-06-21 |  | -30876 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | 2283230 | 2081 | 486.6 | PV | 146-H1 | 2018-06-05 | 2018-06-13 | 6 |  | 6 | 2018-06-26 |  | -30879 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Walpole | 2283639 | 2081 | 7499 | PV & Battery | 456-H1 | 2018-06-01 | 2018-06-13 | 8 |  | 8 | 2018-06-26 |  | -30879 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 2283640 | 2664 | 15.2 | PV | 4-90-90 | 2018-05-16 | 2018-06-13 | 20 |  | 20 | 2018-06-26 |  | -30879 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-02 | 2018-07-17 | [6 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
NSTAR | Wareham | 2284066 | 2571 | 15.13 | PV | 3-84-963 | 2018-04-23 | 2018-06-13 | 37 |  | 37 | 2018-06-25 |  | -30878 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-19 | 2018-08-01 | [6 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online
NSTAR | Ashland | 2284070 | 1721 | 100 | PV | 274-1429H1 | 2018-06-08 | 2018-06-13 | 3 |  | 3 | 2018-06-28 |  | -30881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2284071 | 2563 | 133.2 | PV | 4-81B-443 | 2018-06-04 | 2018-06-14 | 8 |  | 8 | 2018-06-28 |  | -30881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-12 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online | Private
NSTAR | Acton | 2284261 | 1720 | - |  | TBD | 2018-06-28 |  | -30881 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2018-11-23 | TBD | TBD |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | New Bedford | 2284288 | 2740 | 250 | PV | 110-110 | 2018-05-29 | 2018-06-14 | 12 |  | 12 | 2018-06-29 |  | -30882 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2284555 | 1776 | 25 | PV | 342-H7 | 2018-05-31 | 2018-06-15 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-11-13 | Online
NSTAR | Plymouth | 2284556 | 2360 | 250 | PV | 3-13-943 | 2018-06-11 | 2018-06-18 | 5 |  | 5 | 2018-07-02 |  | -30883 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2285552 | 2743 | 2000 | PV |  | 2018-07-05 | 2018-07-06 | 1 | 0 | 1 | 2018-07-06 |  | -30887 | 619 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2018-07-11
NSTAR | Mattapoisett | 2285553 | 2739 | 3560 | PV | 2-302-302 | 2018-06-08 | 2018-06-20 | 8 |  | 8 | 2018-07-06 |  | -30887 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2285554 | 2739 | 4980 | PV & Battery | 2-301-301 | 2018-06-08 | 2018-06-20 | 8 |  | 8 | 2018-07-06 |  | -30887 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Vineyard Haven | 2285555 | 2568 | 29.75 | PV | 4-97-222 | 2018-06-12 | 2018-06-19 | 5 |  | 5 | 2018-07-06 |  | -30887 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-07 | [7 empty] | 0 |  | 0 |  |  | 2018-11-08 | Online
NSTAR | Westport | 2285715 | 2790 | 2200 | PV & Battery | 33-H3 | 2018-06-08 | 2018-06-20 | 8 |  | 8 | 2018-07-09 |  | -30888 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2285721 | 2446 | 86 | PV | 33-H3 | 2018-06-12 | 2018-06-20 | 6 |  | 6 | 2018-07-09 |  | -30888 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2285991 | 2458 | 50 | PV | 292-H1 | 2018-05-31 | 2018-06-26 | 18 |  | 18 | 2018-07-09 |  | -30888 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-10-05 | [6 empty] | 0 |  | 0
NSTAR | Hopkinton | 2286172 | 1748 | 100 | PV | TBD | 2018-07-10 | 2018-07-11 | 1 | 0 | 1 | 2018-07-13 | 2018-07-18 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-19 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Medway | 2286612 | 2053 | 180 | PV | 65-H3 | 2018-07-12 |  | -30891 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-21 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2019-07-30 | Online | Private
NSTAR | Bedford | 2286613 | 1730 | 52.2 | PV | 533-H7 | 2018-06-21 | 2018-06-27 | 4 |  | 4 | 2018-07-13 |  | -30892 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-10 | [7 empty] | 0 |  | 0 |  |  | 2019-08-02 | Online
NSTAR | Hopkinton | 2286965 | 1748 | 100 | PV | 3-86-966 | 2018-05-23 | 2018-06-27 | 25 |  | 25 | 2018-07-11 | 2018-12-10 | 108 |  | 108 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-10 | 2018-12-11 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-10-16 | Online | Private
NSTAR | New Bedford | 2286967 | 2740 | 28 | PV | TBD | 2018-07-16 | 2018-07-24 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-25 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2286968 | 2576 | 2660 | PV & Battery | 3-81-81 | 2018-06-13 | 2018-06-29 | 12 |  | 12 | 2018-07-17 |  | -30894 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2286970 | 1701 | 21.68 | PV | 342-H4 | 2018-05-15 | 2018-06-29 | 33 |  | 33 | 2018-07-17 |  | -30894 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | [7 empty] | 0 |  | 0 |  |  |  | Online
NSTAR | Wayland | 2286971 | 1778 | 208 | PV | 433-H6 | 2018-06-29 | 2018-06-29 | 0 |  | 0 | 2018-07-17 |  | -30894 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-23 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2287284 | 1701 | 249.8 | PV | 278-H1 | 2018-06-06 | 2018-06-29 | 17 |  | 17 | 2018-07-18 |  | -30895 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-09-21 | [6 empty] | 0 |  | 0 |  |  | 2019-08-02 | Online
NSTAR | Boston | 2287285 | 2125 | 288 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | 10 |  | 10 | 2018-07-18 |  | -30895 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-02 | Online
NSTAR | Woburn | 2287543 | 1801 | 1310 | PV | 375-H1 | 2018-07-02 | 2018-07-03 | 1 |  | 1 | 2018-07-19 |  | -30896 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-23 | Online
NSTAR | Boston | 2287544 | 2125 | 288 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | 10 |  | 10 | 2018-07-18 |  | -30895 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Vineyard Haven | 2287709 | 2658 | 19.78 | PV | 4-91-228 | 2017-11-03 | 2017-11-03 | 0 |  | 0 | 2017-11-03 | 2018-07-20 | 185 |  | 185 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-20 | [7 empty] | 0 |  | 0 |  |  | 2018-10-10 | Online | Private
NSTAR | Plymouth | 2287723 | 2360 | 780 | PV | TBD | 2018-07-19 |  | -30896 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-02-28 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2287856 | 2576 | 3992 | PV | TBD | 2018-07-20 |  | -30897 | 0 | 0 | 2018-09-22 | 2018-09-28 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-03-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Westport | 2287931 | 2790 | 4950 | PV | 2-522-522 | 2018-06-29 | 2018-07-03 | 2 |  | 2 | 2018-07-23 |  | -30898 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2288242 | 1801 | 942 | PV | 146-H1 | 2018-07-10 | 2018-07-10 | 0 |  | 0 | 2018-07-24 |  | -30899 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-18 | [7 empty] | 0 |  | 0
NSTAR | Tisbury | 2288244 | 2575 | 18 | PV | 4-97-222 | 2018-05-25 | 2018-07-10 | 32 |  | 32 | 2018-07-24 |  | -30899 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-11 | [7 empty] | 0 |  | 0 |  |  | 2018-11-16 | Online
NSTAR | Stoneham | 2288415 | 2180 | 17.17 | PV | 375-H8 | 2018-07-10 | 2018-07-24 | 10 |  | 10 | 2018-07-25 |  | -30900 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-28 | [7 empty] | 0 |  | 0 |  |  | 2020-01-24 | Online
NSTAR | Hyannis | 2288599 | 2601 | 1500 | PV | 4-84B-524 | 2018-05-31 | 2018-07-11 | 29 |  | 29 | 2018-07-26 |  | -30901 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-13 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2288600 | 2360 | 780 | PV | 3-73-73 | 2018-07-03 | 2018-07-11 | 6 |  | 6 | 2018-07-26 |  | -30901 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-24 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 2288772 | 1803 | 17.49 | PV | 391-H6 | 2018-07-03 | 2018-07-11 | 6 |  | 6 | 2018-07-27 |  | -30902 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-20 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2288774 | 1720 | 999 | PV | 416-H4 | 2018-06-20 | 2018-07-12 | 16 |  | 16 | 2018-07-27 |  | -30902 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  | 2020-09-30
NSTAR | Carver | 2288775 | 2330 | 5000 | PV & Battery | 3-83-83 | 2018-07-06 | 2018-07-12 | 4 |  | 4 | 2018-07-27 |  | -30902 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Norfolk | 2288776 | 2056 | 250 | PV | 146-H3 | 2018-06-07 | 2018-07-12 | 25 |  | 25 | 2018-07-27 |  | -30902 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-09-07 | Online
NSTAR | Holliston | 2288918 | 1746 | 66.6 | PV | 65-H9 | 2018-07-13 | 2018-07-16 | 1 |  | 1 | 2018-07-30 |  | -30903 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-05 | 2018-09-06 | [6 empty] | 0 |  | 0 |  |  | 2019-11-14 | Online
NSTAR | Holliston | 2289154 | 1746 | 17.28 | PV | 274-H3 | 2018-04-10 | 2018-07-17 | 70 |  | 70 | 2018-08-02 |  | -30906 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2020-05-11 | Online
NSTAR | Woburn | 2289155 | 1801 | 15.34 | PV | 211-H10 | 2018-07-03 | 2018-07-17 | 10 |  | 10 | 2018-08-02 |  | -30906 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Burlington | 2289156 | 1803 | 15.2 | PV | 391-H7 | 2018-07-03 | 2018-07-17 | 10 |  | 10 | 2018-08-02 |  | -30906 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | [7 empty] | 0 |  | 0 |  |  | 2019-11-25 | Online
NSTAR | Wareham | 2289380 | 2571 | 996 | PV & Battery | 3-84-961 | 2018-06-27 | 2018-07-18 | 15 |  | 15 | 2018-08-02 |  | -30906 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bourne | 2289611 | 2532 | 115.2 | PV | 4-86-402 | 2018-07-10 | 2018-07-18 | 6 |  | 6 | 2018-08-02 |  | -30906 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  | 2020-02-21 | Online
NSTAR | Brookline | 2289821 | 2445 | 17.28 | PV | 350-H3 | 2018-07-18 | 2018-07-19 | 1 |  | 1 | 2018-08-03 |  | -30907 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-21 | [7 empty] | 0 |  | 0 |  |  | 2019-03-19 | Online
NSTAR | Cambridge | 2289823 | 2138 | 510 | Fuel Cell | 819-1NC3 | 2018-06-12 | 2018-07-20 | 28 |  | 28 | 2018-08-03 |  | -30907 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-01 | [7 empty] | 0 |  | 0 | 2018-12-20 |  | 2018-12-21
NSTAR | Westport | 2289828 | 2770 | 4498 | PV & Battery | 2-532-532 | 2018-04-30 | 2018-07-20 | 59 |  | 59 | 2018-08-15 |  | -30915 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2290339 | 1720 | 300 | PV | 416-H4 | 2018-07-10 | 2018-07-20 | 8 |  | 8 | 2018-08-07 |  | -30909 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2290347 | 1720 | 360 | PV | 416-H9 | 2018-07-10 | 2018-07-20 | 8 |  | 8 | 2018-08-07 |  | -30909 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2290688 | 1801 | 16.42 | PV | 211-H8 | 2018-07-03 | 2018-07-17 | 10 |  | 10 | 2018-08-07 |  | -30909 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2290690 | 2770 | 4000 | PV | 3-702-702 | 2018-07-18 | 2018-07-23 | 3 |  | 3 | 2018-08-07 |  | -30909 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2290691 | 2748 | 18 | PV | 2-528-528 | 2018-07-17 | 2018-07-23 | 4 |  | 4 | 2018-08-07 |  | -30909 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-06 | 2018-09-19 | [6 empty] | 0 |  | 0 |  |  | 2018-10-11 | Online | Private
NSTAR | Bedford | 2290881 | 1731 | 1645 | PV & Battery | 320-H6 | 2018-07-19 | 2018-07-24 | 3 |  | 3 | 2018-08-08 |  | -30910 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-21 | [7 empty] | 0 |  | 0
NSTAR | Acton | 2290885 | 1720 | 15.2 | PV | 416-H1 | 2018-05-23 | 2018-07-24 | 44 |  | 44 | 2018-08-08 |  | -30910 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-12 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2020-02-11 | Online
NSTAR | Edgartown | 2291054 | 2539 | 19.6 | PV | 4-99-99 | 2018-05-31 | 2018-07-25 | 39 |  | 39 | 2018-08-09 |  | -30911 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-22 | [7 empty] | 0 |  | 0
NSTAR | Chelsea | 2291056 | 2150 | 33.3 | PV | 488-H7 | 2018-07-20 | 2018-07-25 | 3 |  | 3 | 2018-08-09 |  | -30911 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-24 | 2018-10-03 | [6 empty] | 0 |  | 0 |  |  | 2019-11-07 | Online
NSTAR | Woburn | 2291058 | 1801 | 15.2 | PV | 391-H11 | 2018-07-18 | 2018-07-26 | 6 |  | 6 | 2018-08-09 |  | -30911 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-18 | 2018-10-24 | [6 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Norfolk | 2291293 | 2056 | 996 | PV | 146-H3 | 2018-07-24 | 2018-07-26 | 2 |  | 2 | 2018-08-10 |  | -30912 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-16 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2291296 | 1801 | 16.56 | PV | 375-H14 | 2018-05-22 | 2018-07-26 | 47 |  | 47 | 2018-08-10 | 2018-12-10 | 86 |  | 86 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-10 | 2018-12-11 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2291297 | 2644 | 15.2 | PV | 4-81B-443 | 2018-07-18 | 2018-07-26 | 6 |  | 6 | 2018-08-10 |  | -30912 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | 2018-10-24 | [6 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Westport | 2291742 | 2790 | 500 | PV | 2-522-522 | 2018-07-23 | 2018-07-27 | 4 |  | 4 | 2018-08-14 |  | -30914 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapan | 2291743 | 2124 | 86 | PV | 311-12 | 2018-07-27 | 2018-08-02 | 4 |  | 4 | 2018-08-15 |  | -30915 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | [7 empty] | 0 |  | 0 |  |  | 2019-06-19 | Online | Private
NSTAR | New Bedford | 2291744 | 2740 | 36 | PV | 2-69-69 | 2018-06-25 | 2018-08-03 | 29 |  | 29 | 2018-08-15 |  | -30915 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-19 | 2018-10-09 | [6 empty] | 0 |  | 0 |  |  | 2018-10-24 | Online | Private
NSTAR | Harwich | 2291972 | 2645 | 30 | PV | 4-92B-92B | 2018-08-02 | 2018-08-07 | 3 |  | 3 | 2018-08-15 | 2018-11-06 | 59 |  | 59 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-06 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Bellingham | 2292179 | 2019 | 6310 | PV & Battery | 65-H4 | 2018-08-03 | 2018-08-07 | 2 |  | 2 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2021-11-30 | Online
NSTAR | Carver | 2292181 | 2330 | 2468 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | 4 |  | 4 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Osterville | 2292182 | 2655 | 23.04 | PV | 4-80A-892 | 2018-07-20 | 2018-08-08 | 13 |  | 13 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Rochester | 2292307 | 2770 | 16.7 | PV | 3-702-702 | 2018-08-08 | 2018-08-15 | 5 |  | 5 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-08-21 | 2018-08-29 | [6 empty] | 0 |  | 0 |  |  | 2018-08-21 | Online | Private
NSTAR | Newton | 2292310 | 2460 | 90 | PV | 467-H3 | 2018-07-20 | 2018-08-08 | 13 |  | 13 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | [7 empty] | 0 |  | 0
NSTAR | Acton | 2293955 | 1720 | 17.56 | PV | 416-H4 | 2018-07-20 | 2018-08-10 | 15 |  | 15 | 2018-08-29 |  | -30925 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-23 | 2018-10-24 | [6 empty] | 0 |  | 0 |  |  | 2019-04-05 | Online | Private
NSTAR | Allston | 2294148 | 2134 | 70 | PV | 548-92H3 | 2018-08-09 | 2018-08-10 | 1 |  | 1 | 2018-08-30 | 2018-10-31 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-31 | 2018-11-16 | [6 empty] | 0 |  | 0
NSTAR | Plymouth | 2294151 | 2362 | 133.2 | PV | 3-14-911 | 2018-08-09 | 2018-08-10 | 1 |  | 1 | 2018-08-30 | 2018-11-05 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-05 | 2018-12-05 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-08-18 | Online | Private
NSTAR | Barnstable | 2294153 | 1801 | 22.8 | PV | 4-81B-443 | 2018-07-24 | 2018-08-15 | 16 |  | 16 | 2018-08-30 | 2018-11-02 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 | 2018-12-17 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-06-04 | Online | Private
NSTAR | Brewster | 2294155 | 2631 | 15.2 | PV | 4-89A-553 | 2018-08-02 | 2018-08-15 | 9 |  | 9 | 2018-08-30 |  | -30926 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-09-11 | [7 empty] | 0 |  | 0 |  |  | 2019-12-04 | Online
NSTAR | Waltham | 2294156 | 2451 | 496 | PV | 320-H3 | 2018-06-05 | 2018-08-15 | 51 |  | 51 | 2018-08-30 | 2018-10-31 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-02 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-05-21 |  | Private
NSTAR | Mattapoisett | 2295025 | 2739 | 960 | PV | 2-302-302 | 2018-08-14 | 2018-08-17 | 3 |  | 3 | 2018-09-05 |  | -30930 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-17 | Online
NSTAR | Natick | 2295244 | 1760 | 180 | PV | 433-H12 | 2018-08-09 | 2018-08-17 | 6 |  | 6 | 2018-09-06 |  | -30931 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2295246 | 2740 | 86.4 | PV | 2-49-49 | 2018-08-14 | 2018-08-20 | 4 |  | 4 | 2018-09-06 |  | -30931 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-08 | [7 empty] | 0 |  | 0 |  |  | 2019-08-22 | Online
NSTAR | Boston | 2295249 | 2163 | 46 | PV | STATION890 | 2018-07-26 | 2018-08-20 | 17 |  | 17 | 2018-09-06 |  | -30931 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-11 | 2018-10-16 | [6 empty] | 0 |  | 0 |  |  | 2018-10-24 | Online | Private
NSTAR | Cambridge | 2295384 | 2138 | 80.5 | PV | 821-05 | 2018-07-31 | 2018-08-20 | 14 |  | 14 | 2018-09-07 | 2018-11-09 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-09 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-26
NSTAR | New Bedford | 2295385 | 2744 | 233.1 | PV | 2-41-41 | 2018-08-06 | 2018-09-04 | 21 |  | 21 | 2018-09-07 | 2018-11-20 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-21 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-11-27
NSTAR | Wareham | 2295386 | 2738 | 2925 | PV | 3-85-85 | 2018-08-07 | 2018-08-22 | 11 |  | 11 | 2018-09-07 |  | -30932 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2295579 | 2740 | 150 | PV | 2-70-70 | 2018-08-07 | 2018-08-22 | 11 |  | 11 | 2018-09-11 | 2018-10-24 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-24 | 2018-10-30 | [6 empty] | 0 |  | 0 |  |  | 2019-12-19 | Online | Private
NSTAR | Oak Bluffs | 2295584 | 2557 | 280 | PV & Battery | 4-75-75 | 2018-08-20 | 2018-08-22 | 2 |  | 2 | 2018-09-11 |  | -30934 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-05-05 | Online
NSTAR | Rochester | 2295586 | 2738 | 996 | PV | 3-85-85 | 2018-08-20 | 2018-08-23 | 3 |  | 3 | 2018-09-11 |  | -30934 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 2295850 | 1721 | 22.95 | PV | 455-H3 | 2018-08-23 | 2018-08-23 | 0 |  | 0 | 2018-09-12 | 2018-11-05 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-05 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2295852 | 2576 | 3000 | PV & Battery | 3-81-81 | 2018-08-16 | 2018-08-23 | 5 |  | 5 | 2018-09-11 |  | -30934 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2295857 | 2453 | 73.3 | PV | 33-H2 | 2018-08-08 | 2018-08-23 | 11 |  | 11 | 2018-09-11 |  | -30934 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-29 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2296072 | 2364 | 3510 | PV | 3/14-14 | 2018-08-22 | 2018-08-24 | 2 |  | 2 | 2018-09-12 |  | -30935 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2021-03-24 | Online
NSTAR | Carver | 2296366 | 2330 | 4650 | PV |  | 2018-09-12 | 2018-09-18 | 4 | 0 | 4 | 2018-09-18 |  | -30939 | 569 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2018-09-20
NSTAR | Westport | 2296371 | 2790 | 2000 | PV | 2-532-532 | 2018-08-22 | 2018-08-24 | 2 |  | 2 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2296372 | 2770 | 4998 | PV & Battery | 3-703-703 | 2018-08-14 | 2018-08-24 | 8 |  | 8 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2296373 | 2571 | 4890 | PV | 3-82-82 | 2018-08-09 | 2018-08-28 | 13 |  | 13 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Dartmouth | 2296559 | 2747 | 4990 | PV | 2-103-103 | 2018-08-09 | 2018-08-28 | 13 |  | 13 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-11 | [7 empty] | 0 |  | 0 |  |  | 2021-03-03 | Online
NSTAR | Framingham | 2296563 | 1702 | 15.2 | PV | 274-H1 | 2018-08-02 | 2018-08-29 | 19 |  | 19 | 2018-09-18 | 2018-11-15 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-15 | 2018-11-16 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Sandwich | 2296564 | 2563 | 4890 | PV & Battery | 4-81B-443 | 2018-07-24 | 2018-08-29 | 26 |  | 26 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-15 | [7 empty] | 0 |  | 0
NSTAR | Ashland | 2296607 | 1721 | 4450 | PV |  | 2018-09-14 |  | -30937 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-31 | TBD |  | 30 | 2019-10-30 | 2019-10-30 | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Wareham | 2296718 | 2538 | 199.8 | PV | 3-81-81 | 2018-08-23 | 2018-08-29 | 4 |  | 4 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2296720 | 2330 | 3500 | PV | 3-10-10 | 2018-08-27 | 2018-08-29 | 2 |  | 2 | 2018-09-18 |  | -30939 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2296721 | 2120 | 27 | PV | 5203 | 2018-06-25 | 2018-08-30 | 48 |  | 48 | 2018-09-18 | 2018-11-02 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-04-09 | Online | Private
NSTAR | Rochester | 2296978 | 2770 | - |  | TBD | 2018-09-17 |  | -30938 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-04-26 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Needham | 2297073 | 2494 | 99.9 | PV | 148-H4 | 2018-08-30 | 2018-08-31 | 1 |  | 1 | 2018-09-19 | 2018-11-14 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-15 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-31 | Online | Private
NSTAR | Westport | 2297080 | 2790 | 1000 | PV | 2-532-532 | 2018-08-20 | 2018-08-31 | 9 |  | 9 | 2018-09-19 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2297083 | 2576 | 4075 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | 1 |  | 1 | 2018-09-19 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2297267 | 2576 | 500 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | 1 |  | 1 | 2018-09-19 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2297500 | 2571 | 4890 | PV | 8-83-83 | 2018-08-09 | 2018-09-19 | 29 |  | 29 | 2018-09-20 |  | -30941 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dennisport | 2297501 | 2639 | 40 | PV | 4-92B-583 | 2018-08-03 | 2018-08-18 | 10 |  | 10 | 2018-09-19 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-02-05
NSTAR | Wareham | 2297503 | 2576 | 250 | PV & Battery | 3-85-85 | 2018-09-04 | 2018-09-05 | 1 |  | 1 | 2018-09-19 |  | -30940 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2297504 | 2210 | 75 | PV | 323-06 | 2018-08-09 | 2018-09-05 | 19 |  | 19 | 2018-09-20 | 2018-11-02 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 | 2018-11-07 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-12-27 |  | Private
NSTAR | Freetown | 2297681 | 2717 | 4500 | PV & Battery | 2-108-108 | 2018-08-28 | 2018-09-06 | 7 |  | 7 | 2018-09-21 |  | -30942 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marion | 2297682 | 2738 | 3500 | PV & Battery | 3-85-85 | 2018-08-14 | 2018-09-06 | 17 |  | 17 | 2018-09-21 |  | -30942 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2298087 | 1754 | 462 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2298090 | 1754 | 396 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Maynard | 2298091 | 1754 | 396 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Maynard | 2298092 | 1754 | 1254 | PV | 416-H6 | 2018-08-03 | 2018-09-04 | 22 |  | 22 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 2298285 | 1720 | 490 | PV | 416-H4 | 2018-07-10 | 2018-09-06 | 42 |  | 42 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2298289 | 1730 | 72 | PV | 533-H5 | 2018-08-28 | 2018-09-06 | 7 |  | 7 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-06 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2298290 | 1801 | 924 | PV | 258-1394-H1 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-26 |  | -30945 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-29 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | Woburn | 2298553 | 1801 | 490 | PV | 258-1394H8 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-27 |  | -30946 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-29 | [7 empty] | 0 |  | 0 |  |  | 2022-11-22 | Online
NSTAR | Burlington | 2298565 | 1803 | 990 | PV | 391-H16 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-27 | 2018-11-29 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-12-05 |  |  | EXP |  |  |  | 0 |  | 0
NSTAR | Burlington | 2298567 | 1803 | 990 | PV | 391-H9 | 2018-08-24 | 2018-09-07 | 10 |  | 10 | 2018-09-27 | 2018-11-29 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-12-05 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Barnstable | 2298568 | 2648 | 4990 | PV | 4-88-453 | 2018-09-04 | 2018-09-07 | 3 |  | 3 | 2018-09-27 |  | -30946 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2298768 | 2770 | 1782 | PV | 3-702-702 | 2018-08-28 | 2018-09-07 | 8 |  | 8 | 2018-09-28 |  | -30947 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2298783 | 1746 | 31 | PV | 130-H1 | 2018-08-30 | 2018-09-07 | 6 |  | 6 | 2018-09-28 | 2018-12-06 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-06 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-03-06
NSTAR | New Bedford | 2298790 | 2745 | 1220 | PV | 2-107-107 | 2018-09-04 | 2018-09-07 | 3 |  | 3 | 2018-09-28 |  | -30947 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2298981 | 2747 | 185 | PV & Battery | 2-525-525 | 2018-08-31 | 2018-09-10 | 6 |  | 6 | 2018-10-01 |  | -30948 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-23 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2299343 | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-06 | 2018-09-11 | 3 |  | 3 | 2018-10-02 |  | -30949 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2299346 | 2330 | 8300 | PV & Battery | 3-51-901 | 2018-09-07 | 2018-09-11 | 2 |  | 2 | 2018-10-02 |  | -30949 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2299348 | 2360 | 924 | PV | 3-12-41J1 | 2018-08-17 | 2018-09-12 | 18 |  | 18 | 2018-10-02 |  | -30949 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2022-12-21 | Online
NSTAR | Rochester | 2299350 | 2770 | 1250 | PV & Battery | 5-702-702 | 2018-09-06 | 2018-09-12 | 4 |  | 4 | 2018-10-02 |  | -30949 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chatham | 2299602 | 2659 | 78.2 | PV | 4-95A-95A | 2018-09-12 | 2018-09-19 | 5 |  | 5 | 2018-10-03 |  | -30950 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-17 | 2018-10-24 | [6 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Acusnet | 2299606 | 2743 | 4950 | PV & Battery | 2-241-241 | 2018-09-07 | 2018-09-20 | 9 |  | 9 | 2018-10-03 |  | -30950 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2300058 | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | 3 |  | 3 | 2018-10-04 |  | -30951 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2300060 | 2770 | 3060 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | 3 |  | 3 | 2018-10-04 |  | -30951 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2300709 | 2770 | 5000 | PV & Battery | 3-703-703 | 2018-09-17 | 2018-09-20 | 3 |  | 3 | 2018-10-10 |  | -30955 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2300908 | 2576 | 4180 | PV & Battery | 3-81-81 | 2018-09-04 | 2018-09-21 | 13 |  | 13 | 2018-10-11 |  | -30956 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Woburn | 2300919 | 1801 | 15.2 | PV | 211-H13 | 2018-09-07 | 2018-09-25 | 12 |  | 12 | 2018-10-11 |  | -30956 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  | 2020-03-24 | Online | Private
NSTAR | Watertown | 2300922 | 2472 | 475.2 | PV | 467-H4 | 2018-09-18 | 2018-09-25 | 5 |  | 5 | 2018-10-11 |  | -30956 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | [7 empty] | 0 |  | 0 |  |  | 2019-11-15 | Online | Private
NSTAR | Sandwich | 2301106 | 2563 | 133.2 | PV | 4-81B-443 | 2018-09-19 | 2018-09-26 | 5 |  | 5 | 2018-10-12 |  | -30957 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Cambridge | 2301108 | 2142 | 63.3 | PV | 831-1336XY | 2018-09-24 | 2018-09-27 | 3 |  | 3 | 2018-10-12 | 2018-11-14 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-28 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-12-22 | Online | Private
NSTAR | East Freetown | 2301315 | 2717 | 220 | PV | 604 | 2018-09-24 | 2018-09-27 | 3 |  | 3 | 2018-10-16 |  | -30959 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-22 | [7 empty] | 0 |  | 0 |  |  | 2020-10-19 | Online | Private
NSTAR | Acusnet | 2301808 | 2743 | 5000 | PV |  | 2018-10-16 | 2018-10-17 | 1 | 0 | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-10-18 | 2019-12-18 | 304 | 41 | 263 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-06-13 |  | 2020-06-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  | 2021-09-23 | Online | Private
NSTAR | Acusnet | 2301817 | 2743 | 5000 | PV | 2-241-241 | 2018-09-26 | 2018-09-28 | 2 |  | 2 | 2018-10-17 |  | -30960 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Chelsea | 2302133 | 2150 | 66.6 | PV | 488-H2 | 2018-09-26 | 2018-10-01 | 3 |  | 3 | 2018-10-18 |  | -30961 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-20 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Rochester | 2302146 | 2770 | 1000 | PV & Battery | 3-702-702 | 2018-09-20 | 2018-09-21 | 1 |  | 1 | 2018-10-18 |  | -30961 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Plymouth | 2302150 | 2360 | 133.2 | PV | 3-13-943 | 2018-09-25 | 2018-10-02 | 5 |  | 5 | 2018-10-18 | 2018-11-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-02 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2302380 | 2571 | 100 | PV | 8-83-83 | 2018-09-25 | 2018-10-02 | 5 |  | 5 | 2018-10-19 | 2018-11-20 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 | 2018-11-20 |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Milton | 2302387 | 2186 | 38 | PV | 362-03 | 2018-09-26 | 2018-10-02 | 4 |  | 4 | 2018-10-19 |  | -30962 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-04 | [7 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Canton | 2302390 | 2021 | 3992 | PV | 269-1321H | 2018-09-28 | 2018-10-03 | 3 |  | 3 | 2018-10-19 |  | -30962 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-06-09 | Online | Private
NSTAR | Barnstable | 2302867 | 2632 | 66.6 | PV | 4-88-88 | 2018-10-05 | 2018-10-05 | 0 |  | 0 | 2018-10-23 |  | -30964 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Plymouth | 2303219 | 2360 | 199.8 | PV | 3-10-10 | 2018-10-01 | 2018-10-05 | 4 |  | 4 | 2018-10-25 |  | -30966 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | New Bedford | 2303220 | 2746 | 86.4 | PV | 2-24-182 | 2018-10-03 | 2018-10-10 | 5 |  | 5 | 2018-10-25 | 2018-11-14 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-21 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2021-05-10 | Online | Private
NSTAR | New Bedford | 2303221 | 2746 | 57.6 | PV | 2-24-182 | 2018-10-03 | 2018-10-10 | 5 |  | 5 | 2018-10-25 | 2018-11-29 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-29 | 2018-11-30 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2021-08-23 | Online | Public
NSTAR | Natick | 2303427 | 1760 | 100 | PV & Battery | 240-H3 | 2018-10-11 | 2018-10-18 | 5 |  | 5 |  | 2018-11-26 | 30987 |  | 30987 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | 2018-11-27 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-04-22 | Online | Private
NSTAR | Plymouth | 2303429 | 2360 | 144 | PV | 3-13-943 | 2018-10-11 | 2018-10-18 | 5 |  | 5 | 2018-10-31 | 2018-11-20 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-20 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-04-21 | Online | Private
NSTAR | Vineyard Haven | 2303430 | 2568 | 23.36 | PV | 3-24B-95 | 2018-10-05 | 2018-10-11 | 4 |  | 4 | 2018-10-31 | 2018-12-11 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Hyannis | 2303431 | 2601 | 40 | PV | 4-80B-514 | 2018-10-15 | 2018-10-19 | 4 |  | 4 | 2018-10-11 |  | -30956 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | [7 empty] | 0 |  | 0 |  |  | 2019-09-06 | Online | Private
NSTAR | Natick | 2303432 | 1760 | 366.6 | PV | 433-H9 | 2018-10-05 | 2018-10-11 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Falmouth | 2303631 | 2536 | 3300 | PV & Battery | 4-98A-98A | 2018-10-08 | 2018-10-12 | 4 |  | 4 | 2018-11-02 |  | -30972 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-04 | [7 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Woburn | 2304049 | 1801 | 15.2 | PV | 375-H14 | 2018-10-09 | 2018-10-12 | 3 |  | 3 | 2018-10-31 |  | -30970 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Canton | 2304052 | 2021 | 496.2 | PV | 269-1321H | 2018-10-12 | 2018-10-12 | 0 |  | 0 | 2018-10-31 |  | -30970 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-08 | [7 empty] | 0 |  | 0 |  |  | 2020-12-08 | Online | Private
NSTAR | Plymouth | 2304254 | 2360 | 366.6 | PV | 3-13-943 | 2019-04-04 | 2019-04-12 | 6 |  | 6 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Canton | 2304257 | 2021 | 350 | PV | 470-h7 | 2018-10-10 | 2018-10-18 | 6 |  | 6 | 2018-11-01 |  | -30971 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Westport | 2304259 | 2790 | 5000 | PV & Battery | 2-523-523 | 2018-10-02 | 2018-10-18 | 12 |  | 12 | 2018-11-01 |  | -30971 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Acusnet | 2304486 | 2743 | 3060 | PV & Battery | 2-241-238 | 2018-10-15 | 2018-10-18 | 3 |  | 3 | 2018-11-02 |  | -30972 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Newton | 2304489 | 2468 | 75.6 | PV | 292-H12 | 2018-10-18 | 2018-11-02 | 11 |  | 11 | 2018-11-02 |  | -30972 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-19 | [7 empty] | 0 |  | 0 |  |  | 2019-09-05 | Online | Private
NSTAR | Framingham | 2304490 | 1701 | 43.2 | PV | 433-H2 | 2018-10-15 | 2018-10-19 | 4 |  | 4 | 2018-11-02 |  | -30972 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-02 | [7 empty] | 0 |  | 0 |  |  | 2020-03-06 | Online | Private
NSTAR | New Bedford | 2305081 | 2740 | 199.4 | PV | 2-38-38 | 2018-10-18 | 2018-10-19 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online | Public
NSTAR | Marion | 2305082 | 2738 | 20.88 | PV | 3-85-969 | 2018-10-19 | 2018-10-19 | 0 |  | 0 | 2018-11-05 | 2018-11-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 | 2018-11-29 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2018-01-09 | Online | Private
NSTAR | New Bedford | 2305084 | 2746 | 428 | PV | 2-80-401 | 2018-10-18 | 2018-10-19 | 1 |  | 1 | 2018-11-05 |  | -30973 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online | Public
NSTAR | Winchester | 2305372 | 2890 | 50 | PV | 211-H10 | 2018-10-19 | 2018-10-23 | 2 |  | 2 | 2018-11-06 |  | -30974 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online | Private
NSTAR | Winchester | 2305374 | 1890 | 60 | PV | 211-H1 | 2018-10-19 | 2018-10-23 | 2 |  | 2 | 2018-11-06 |  | -30974 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 |  |  | 2019-11-14 | Online | Private
NSTAR | Roslindale | 2305544 | 2131 | 336 | PV & Battery | 496-H4 | 2018-10-24 | 2018-11-07 | 10 |  | 10 | 2018-11-07 | 2018-11-14 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-14 | 2018-11-14 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-12-04 | Online | Private
NSTAR | Jamaica Plain | 2305731 | 2130 | 60 | PV | 284-02 | 2018-10-19 | 2018-11-08 | 14 |  | 14 | 2018-11-08 | 2018-11-15 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-15 | 2018-12-14 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-02-26 | Online | Private
NSTAR | Burlington | 2305732 | 1803 | 400 | PV | 391-H5 | 2018-11-06 | 2018-11-08 | 2 |  | 2 | 2018-11-08 |  | -30976 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Burlington | 2305734 | 1803 | 800 | PV | 391-H5 | 2018-10-25 | 2018-11-08 | 10 |  | 10 | 2018-11-08 |  | -30976 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Dartmouth | 2305846 | 2747 | 999 | PV & Battery | 2-541-542 | 2018-10-23 | 2018-10-25 | 2 |  | 2 | 2018-11-09 |  | -30977 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Dartmouth | 2305925 | 2747 | 999 | PV & Battery | 2-541-542 | 2018-10-23 | 2018-10-25 | 2 |  | 2 | 2018-11-09 |  | -30977 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-06-14 | Online | Private
NSTAR | Holliston | 2306412 | 1746 | 490 | PV | 274-H3 | 2018-10-29 | 2018-11-14 | 12 |  | 12 | 2018-11-14 |  | -30980 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Carver | 2306416 | 2330 | 1625 | PV | 3-10-929 | 2018-10-29 | 2018-11-14 | 12 |  | 12 | 2018-11-14 |  | -30980 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Rochester | 2306598 | 2770 | 1750 | PV | 3-703-703 | 2018-10-31 | 2018-11-15 | 11 |  | 11 | 2018-11-15 |  | -30981 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Wareham | 2306600 | 2571 | 4999 | PV & Battery | 3-82-82 | 2018-11-01 | 2018-11-15 | 10 |  | 10 | 2018-11-15 |  | -30981 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Norfolk | 2306602 | 2056 | 15.2 | PV | 146-H9 | 2018-11-01 | 2018-11-15 | 10 |  | 10 | 2018-11-15 |  | -30981 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Lincoln | 2306816 | 1773 | 86.4 | PV | 320-H1 | 2018-11-01 | 2018-11-16 | 11 |  | 11 | 2018-11-16 |  | -30982 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-09-23 | Online | Private
NSTAR | Edgartown | 2306817 | 2539 | 22.4 | PV | 4-99-99 | 2018-11-01 | 2018-11-16 | 11 |  | 11 | 2018-11-16 | 2018-11-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-11-26 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2306818 | 2571 | 240 | PV | 3-85-955 | 2018-11-01 | 2018-11-16 | 11 |  | 11 | 2018-11-16 |  | -30982 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-08 | [7 empty] | 0 |  | 0 |  |  |  |  | Public
NSTAR | Framingham | 2307344 | 1702 | 57.6 | PV | 24-H1 | 2018-11-05 | 2018-11-20 | 11 |  | 11 | 2018-11-20 |  | -30984 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-27 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-12-13 | Online | Private
NSTAR | Framingham | 2307346 | 1701 | 81 | PV | 278-H1 | 2018-11-05 | 2018-11-20 | 11 |  | 11 | 2018-11-20 |  | -30984 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Chestnut Hill | 2307511 | 2467 | 496.2 | PV | 292-H6 | 2018-11-06 | 2018-11-21 | 11 |  | 11 | 2018-11-21 |  | -30985 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Chestnut Hill | 2307513 | 2467 | 499.8 | PV | 292-H6 | 2018-11-06 | 2018-11-21 | 11 |  | 11 | 2018-11-21 |  | -30985 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Rochester | 2307638 | 2770 | 5000 | PV & Battery | 3-703-703 | 2018-11-06 | 2018-11-23 | 13 |  | 13 | 2018-11-23 |  | -30987 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Westport | 2307639 | 2790 | 1500 | PV | 2-532-532 | 2018-11-06 | 2018-11-23 | 13 |  | 13 | 2018-11-23 |  | -30987 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Somerville | 2307640 | 2145 | 250 | PV & Battery | 250-H4XY | 2018-11-08 | 2018-11-23 | 11 |  | 11 | 2018-11-23 |  | -30987 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-10 | [7 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Westport | 2307641 | 2790 | 4998 | PV & Battery | 2-532-532 | 2018-11-06 | 2018-11-23 | 13 |  | 13 | 2018-11-23 |  | -30987 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Woburn | 2307642 | 1801 | 208.3 | PV | 211-H2 | 2018-11-09 | 2018-11-27 | 12 |  | 12 | 2018-11-27 |  | -30989 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-07 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online | Private
NSTAR | Woburn | 2308000 | 1801 | 333.3 | PV | 211-H2 | 2018-11-09 | 2018-11-27 | 12 |  | 12 | 2018-11-27 |  | -30989 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Westport | 2308001 | 2790 | 37.8 | PV | 2-532-532 | 2018-11-07 | 2018-11-27 | 14 |  | 14 | 2018-11-27 |  | -30989 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0 |  |  | 2019-12-20 | Online
NSTAR | New Bedford | 2308002 | 2740 | 43.2 | PV | 2-24-182 | 2018-11-07 | 2018-11-27 | 14 |  | 14 | 2018-11-27 | 2018-12-04 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-04 | 2018-12-21 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-12-20 | Online | Private
NSTAR | West Tisbury | 2308167 | 2575 | 22.33 | PV & Battery | 3-24B-95 | 2018-11-07 | 2018-11-28 | 15 |  | 15 | 2018-11-28 | 2018-12-07 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-07 | 2018-12-07 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-09-06 | Online | Private
NSTAR | Boston | 2308171 | 2114 | 50 | CHP | 274-H3 | 2018-11-07 | 2018-11-28 | 15 |  | 15 | 2018-11-28 |  | -30990 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-04-09 | Online | Private
NSTAR | Dennis | 2308172 | 2638 | 17.4 | PV | 4-92B-92B | 2018-11-07 | 2018-11-28 | 15 |  | 15 | 2018-11-28 |  | -30990 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-18 | [7 empty] | 0 |  | 0 |  |  | 2019-04-30 | Online | Private
NSTAR | Boston | 2308328 | 2115 | 1600 | PV & Battery | 528-169H | 2018-11-27 |  | -30989 |  | 0 | 2018-12-26 |  | -31010 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-06 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
NSTAR | Plymouth | 2308333 | 2360 | 500 | PV | 3-13-943 | 2018-11-13 | 2018-11-29 | 12 |  | 12 | 2018-11-29 |  | -30991 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Hopkinton | 2308334 | 1748 | 2000 | PV & Battery | 126-H4 | 2018-11-14 | 2018-11-29 | 11 |  | 11 | 2018-11-29 |  | -30991 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dartmouth | 2308512 | 2748 | 17.4 | PV | 2-528-528 | 2018-11-14 | 2018-11-30 | 12 |  | 12 | 2018-11-30 | 2018-12-11 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 | 2018-12-12 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2019-04-30 | Online | Private
NSTAR | Carver | 2308513 | 2330 | 4980 | PV & Battery | 3-81-950 | 2018-11-15 | 2018-11-30 | 11 |  | 11 | 2018-11-30 |  | -30992 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Somerville | 2308642 | 2145 | 600 | Fuel Cell | 250-H4XY | 2018-11-15 | 2018-12-03 | 12 |  | 12 | 2018-12-03 |  | -30993 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2020-03-06 | Online | Private
NSTAR | North Dartmouth | 2308643 | 2747 | 18.15 | PV | 2-532-532 | 2018-11-16 | 2018-12-03 | 11 |  | 11 | 2018-12-03 | 2018-12-06 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-06 | 2018-12-11 |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2020-12-24 | Online | Private
NSTAR | Kingston | 2311123 | 2364 | 1531.8 | PV | 3/14-14 | 2018-11-16 | 2018-12-05 | 13 |  | 13 | 2018-12-05 |  | -30995 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Marshfield | 2311127 | 2050 | 2112 | PV | 3-24A-24A | 2018-11-16 | 2018-12-05 | 13 |  | 13 | 2018-12-05 |  | -30995 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2022-12-06 | Online | Private
NSTAR | Framingham | 2311128 | 1702 | 492 | PV | 455-H2 | 2018-12-05 | 2018-12-05 | 0 |  | 0 | 2018-12-05 |  | -30995 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Canton | 2311297 | 2021 | 225 | PV | 470-H7 | 2018-11-14 | 2018-11-21 | 5 |  | 5 | 2018-12-06 |  | -30996 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2021-02-04 | Online
NSTAR | Plymouth | 2311298 | 2360 | 233.1 | PV | 3-13-13 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-06 |  | -30996 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | 2311303 | 2535 | 83.52 | PV | 4-91-126 | 2018-11-21 | 2018-12-06 | 11 |  | 11 | 2018-12-06 |  | -30996 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-26 | 2018-12-27 | [6 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Woburn | 2311476 | 1801 | 249.8 | PV | 211-H2 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 |  | -30997 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-08 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online | Private
NSTAR | Plympton | 2311480 | 2367 | 2000 | PV & Battery | 3-51-901 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 |  | -30997 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Natick | 2311483 | 1760 | 180 | PV | 433-H10 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 |  | -30997 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-05 | [7 empty] | 0 |  | 0 |  |  | 2020-02-14 | Online | Private
NSTAR | Rochester | 2311484 | 2770 | 19 | PV | 3-703-703 | 2018-11-21 | 2018-12-07 | 12 |  | 12 | 2018-12-07 | 2018-12-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-11 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Cotuit | 2311617 | 2635 | 17.93 | PV & Battery | 4-88-880 | 2018-11-26 | 2018-12-10 | 10 |  | 10 | 2018-12-10 |  | -30998 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-15 | [7 empty] | 0 |  | 0 |  |  | 2019-10-21 | Online | Private
NSTAR | Lexington | 2311846 | 2421 | 1149 | PV & Battery | 533-H1 | 2018-11-27 | 2018-12-11 | 10 |  | 10 | 2018-12-11 |  | -30999 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-10 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 2311847 | 2050 | 115.44 | PV | 3-24A-24A | 2018-11-28 | 2018-12-11 | 9 |  | 9 | 2018-12-11 |  | -30999 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-18 | [7 empty] | 0 |  | 0 |  |  | 2020-04-07 | Online
NSTAR | Oak Bluffs | 2311848 | 2557 | 249.8 | PV | 4-75-75 | 2018-11-29 | 2018-12-11 | 8 |  | 8 | 2018-12-11 |  | -30999 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2312220 | 2459 | 200 | PV | 292-H3 | 2018-11-28 | 2018-11-29 | 1 |  | 1 | 2018-12-13 |  | -31001 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-01 |  |  |  | EXP |  |  |  | 0 |  | 0
NSTAR | Stoneham | 2312221 | 2180 | 15.98 | PV | 375-H8 | 2018-11-07 | 2018-11-29 | 16 |  | 16 | 2018-12-13 |  | -31001 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-01 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2312223 | 2067 | 660 | PV & Battery | 146-H7 | 2018-10-25 | 2018-12-03 | 27 |  | 27 | 2018-12-13 |  | -31001 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn |  |  | 2020-09-30
NSTAR | Roxbury | 2312379 | 2119 | 199.8 | PV | 106-H4 | 2018-12-03 | 2018-12-03 | 0 |  | 0 | 2018-12-14 |  | -31002 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2020-06-02 | Online
NSTAR | Bourne | 2312381 | 2532 | 999 | PV | 3-88-88 | 2018-11-21 | 2018-12-03 | 8 |  | 8 | 2018-12-14 |  | -31002 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-12-23 | Online
NSTAR | Falmouth | 2313194 | 2540 | 24.84 | PV | 4-98A-98A | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-18 |  | -31004 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0 |  |  | 2019-05-02 | Online
NSTAR | Roxbury | 2313198 | 2119 | 36 | PV | 106-H5 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-18 |  | -31004 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  | 2019-12-11 | Online
NSTAR | Westport | 2313433 | 2790 | 4998 | PV & Battery | 2-532-532 | 2018-11-29 | 2018-12-04 | 3 |  | 3 | 2018-12-19 |  | -31005 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Truro | 2313435 | 2655 | 4998 | PV & Battery | 4-96-674 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-19 |  | -31005 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2313788 | 2770 | 496.6 | PV | 3-85-85 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-21 |  | -31007 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0 |  |  | 2020-07-06 | Online
NSTAR | Boston | 2313793 | 2128 | 250 | PV | 488-H5 | 2018-12-04 | 2018-12-04 | 0 |  | 0 | 2018-12-21 |  | -31007 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Canton | 2313802 | 2021 | 100 | PV | 269-1320H1 | 2018-12-04 | 2018-12-06 | 2 |  | 2 | 2018-12-21 |  | -31007 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-16 | Online
NSTAR | Hyde Park | 2313809 | 2136 | 15.2 | PV | 441-06 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-21 |  | -31007 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2313811 | 1749 | 31.7 | PV | 386-1356 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-21 |  | -31007 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Tisbury | 2313933 | 2575 | 92.4 | PV | 4-97-97 | 2018-12-06 | 2018-12-06 | 0 |  | 0 | 2018-12-24 |  | -31008 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-17 | [7 empty] | 0 |  | 0
NSTAR | East Boston | 2314366 | 2128 | 79.2 | PV | 592-72XY |  | 2018-12-07 | 30996 |  | 30996 | 2018-12-28 |  | -31012 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-22 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Cotuit | 2314367 | 2635 | 15.2 | PV | 4-88-880 | 2018-12-07 | 2018-12-07 | 0 |  | 0 | 2018-12-28 |  | -31012 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Harwich | 2314368 | 2645 | 20 | PV | 4-92B-92B | 2018-12-07 | 2018-12-07 | 0 |  | 0 | 2018-12-28 |  | -31012 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-09 | [7 empty] | 0 |  | 0 |  |  | 2019-05-21 | Online
NSTAR | Carver | 2314369 | 2330 | 3500 | PV | 3-81-950 | 2018-11-27 | 2018-12-10 | 9 |  | 9 | 2018-12-28 |  | -31012 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2314370 | 2451 | 40 | PV | 282-H8 | 2018-12-11 |  | -30999 |  | 0 | 2018-12-28 |  | -31012 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2314371 | 2745 | 100 | PV | 2-137-139 | 2018-12-12 | 2018-12-12 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-28 | [7 empty] | 0 |  | 0 |  |  | 2019-10-08
NSTAR | East Freetown | 2314499 | 2717 | 3300 | PV & Battery | 2-102-604 | 2018-10-19 | 2018-12-14 | 40 |  | 40 | 2018-12-31 |  | -31013 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2018-07-10 | Online
NSTAR | Stoneham | 2314500 | 2180 | 72 | PV | 375-H7 | 2018-12-13 | 2018-12-17 | 2 |  | 2 | 2018-12-31 |  | -31013 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 |  |  | 2019-08-07 | Online
NSTAR | Stoneham | 2314501 | 2180 | 150 | PV | 375-H8 | 2018-12-13 | 2018-12-17 | 2 |  | 2 | 2018-12-31 |  | -31013 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-25 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2316352 | 2180 | 50 | PV | 375-H8 | 2018-12-13 | 2018-12-17 | 2 |  | 2 | 2019-01-03 |  | -31016 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-03 | [7 empty] | 0 |  | 0 |  |  | 2019-07-30 | Online
NSTAR | Plympton | 2316354 | 2364 | 4999 | PV & Battery | 3-15-15 | 2018-12-12 | 2018-12-18 | 4 |  | 4 | 2019-01-03 |  | -31016 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2316355 | 1748 | 6310 | PV & Battery | 533-H7 | 2018-12-20 | 2018-12-20 | 0 |  | 0 | 2019-01-03 |  | -31016 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-13 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2316959 | 2601 | 500 | PV | 4-63-63 | 2018-11-21 | 2018-12-12 | 15 |  | 15 | 2019-01-04 |  | -31017 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Falmouth | 2316966 | 2536 | 4500 | PV | 4-98A-98A | 2018-12-11 | 2018-12-17 | 4 |  | 4 | 2019-01-04 |  | -31017 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online
NSTAR | East Falmouth | 2317177 | 2536 | 4000 | PV | 4-98A-98A | 2018-12-12 | 2018-12-17 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-12-14 | Online
NSTAR | Sudbury | 2317182 | 1766 | 499.99 | PV | 342-H2 | 2018-12-10 | 2018-12-10 | 0 |  | 0 | 2019-01-07 |  | -31018 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Falmouth | 2317183 | 2540 | 1000 | PV | 4-98A-98A | 2018-12-10 | 2018-12-10 | 0 |  | 0 | 2019-01-07 |  | -31018 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Freetown | 2319218 | 2717 | 8360 | PV & Battery | 2-605-605 | 2018-12-07 | 2018-12-18 | 7 |  | 7 | 2019-01-08 |  | -31019 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2319219 | 2460 | 206 | PV | 17-H2 | 2018-12-17 | 2018-12-20 | 3 |  | 3 | 2019-01-08 |  | -31019 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2319220 | 2460 | 66.66 | PV | 467-H3 | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-08 |  | -31019 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2319393 | 2360 | 999 | PV & Battery | 3-73-73 | 2018-12-18 | 2018-12-18 | 0 |  | 0 | 2018-01-09 |  | -30759 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2319563 | 2460 | 233 | PV | 17-1354H1 | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-10 |  | -31021 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2319566 | 2460 | 66.66 | PV | 17-1354H1 | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-10 |  | -31021 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-16 | [7 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Holliston | 2319567 | 1746 | 1640 | PV | 274-H3 | 2018-12-17 | 2018-12-19 | 2 |  | 2 | 2019-01-10 |  | -31021 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-10-15 | Online
NSTAR | Vineyard Haven | 2319568 | 2568 | 43.2 | PV | 4-75-75 | 2018-12-13 | 2018-12-20 | 5 |  | 5 | 2019-01-10 |  | -31021 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-04 | [7 empty] | 0 |  | 0 |  |  | 2019-10-29
NSTAR | Marshfield | 2319796 | 2050 | 15.2 | PV | 3-25-42J2 | 2018-12-11 | 2018-12-21 | 8 |  | 8 | 2019-01-11 |  | -31022 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-27 | [7 empty] | 0 |  | 0 |  |  | 2022-08-17 | Online
NSTAR | Waltham | 2319797 | 2451 | 106.6 | PV | 3-25-42J2 | 2018-12-19 | 2018-12-21 | 2 |  | 2 | 2019-01-11 |  | -31022 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-01-30 | [7 empty] | 0 |  | 0 |  |  | 2019-12-30 | Online
NSTAR | Westport | 2319812 | 2790 | 22.1 | PV | 2-532-532 | 2018-12-19 | 2018-12-21 | 2 |  | 2 | 2019-01-11 |  | -31022 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Kingston | 2319914 | 2364 | 406.5 | PV | 3-26-902 | 2018-12-19 | 2019-01-02 | 10 |  | 10 | 2019-01-11 |  | -31022 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-27 | [7 empty] | 0 |  | 0 |  |  | 2021-09-09 | Online
NSTAR | Newton | 2320273 | 2468 | 133.3 | PV | 17-H2 | 2019-01-07 | 2019-01-07 | 0 |  | 0 | 2019-01-14 |  | -31023 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-11 | [7 empty] | 0 |  | 0 |  |  | 2020-05-04 | Online
NSTAR | Dover | 2320293 | 2030 | 19.8 | PV | 456-H1 | 2018-12-26 | 2019-01-07 | 8 |  | 8 | 2019-01-14 |  | -31023 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-05 | [7 empty] | 0 |  | 0 |  |  | 2019-07-22 | Online
NSTAR | Wareham | 2320442 | 2571 | 5000 | PV | 8-83-83 | 2018-12-12 | 2018-12-21 | 7 |  | 7 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2320444 | 2330 | 4980 | PV & Battery | 3-81-950 | 2018-12-16 | 2018-12-19 | 3 |  | 3 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2320445 | 2021 | 3240 | PV | 269-1320H1 | 2018-12-19 | 2018-12-26 | 5 |  | 5 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2320446 | 2770 | 2900 | PV | 3-703-703 | 2018-12-21 | 2018-12-26 | 3 |  | 3 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2320561 | 2563 | 500 | PV | 4-87A-471 | 2019-01-02 | 2019-01-02 | 0 |  | 0 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-09 | [7 empty] | 0 |  | 0
NSTAR | Freetown | 2320621 | 2702 | 4875 | PV | 2-605-605 | 2018-12-26 | 2018-12-27 | 1 |  | 1 | 2019-01-16 |  | -31025 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2320623 | 2770 | 4890 | PV & Battery | 3-703-703 | 2018-12-26 | 2018-12-27 | 1 |  | 1 | 2019-01-16 |  | -31025 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2320809 | 2360 | 4999 | PV & Battery | 3-73-73 | 2019-01-08 | 2019-01-08 | 0 |  | 0 | 2019-01-17 |  | -31026 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 2320829 | 2026 | 399.6 | PV | 20-H6 | 2018-12-19 | 2018-12-27 | 6 |  | 6 | 2019-01-17 |  | -31026 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-11 | [7 empty] | 0 |  | 0 |  |  | 2022-02-17 | Online
NSTAR | Acusnet | 2320833 | 2743 | 21.34 | PV & Battery | 2-241-241 | 2018-04-06 | 2018-12-26 | 188 |  | 188 | 2019-01-17 |  | -31026 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-10-01 | Online
NSTAR | West Yarmouth | 2320835 | 2673 | 498 | PV | 4-92A-534 | 2018-12-20 | 2018-12-26 | 4 |  | 4 | 2019-01-17 |  | -31026 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Lincoln | 2321103 | 1773 | 20 | PV & Battery | 320-H6 | 2018-12-20 | 2019-01-08 | 13 |  | 13 | 2019-01-29 |  | -31034 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-01 | [7 empty] | 0 |  | 0 |  |  | 2019-09-03 | Online
NSTAR | Watertown | 2321147 | 2472 | 100 | PV | 467-H4 | 2018-12-26 | 2018-12-27 | 1 |  | 1 | 2019-01-18 |  | -31027 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-24 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | Dedham | 2321149 | 2026 | 199.8 | PV | 20-H6 | 2018-12-19 | 2018-12-27 | 6 |  | 6 | 2019-01-18 |  | -31027 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-11-07 | Online
NSTAR | Dedham | 2321151 | 2026 | 119 | PV | 20-H6 | 2018-12-19 | 2018-12-28 | 7 |  | 7 | 2019-01-18 |  | -31027 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-27 | [7 empty] | 0 |  | 0 |  |  | 2021-07-07 | Online
NSTAR | Natick | 2321334 | 1760 | 32.4 | PV | TBD | 2019-01-18 |  | -31027 | 0 | 0 | 2019-01-22 | 2019-03-05 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-08-26 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Carver | 2321677 | 2330 | 6500 | PV | 3-10-930 | 2019-01-07 | 2019-01-08 | 1 |  | 1 | 2019-01-23 |  | -31030 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2321814 | 2021 | 132 | PV | 269-1320H1 | 2018-12-18 | 2019-01-09 | 16 |  | 16 | 2019-01-23 |  | -31030 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-29 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2321912 | 1760 | 72 | PV | 433-H10 | 2019-01-15 | 2019-01-15 | 0 |  | 0 | 2019-01-23 |  | -31030 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Wareham | 2322036 | 2571 | 2250 | PV | 8-83-83 | 2019-01-04 | 2019-01-07 | 1 |  | 1 | 2019-01-25 |  | -31032 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bourne | 2322113 | 2532 | 1390 | PV | 4-86-402 | 2019-01-07 | 2019-01-16 | 7 |  | 7 | 2019-01-25 |  | -31032 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2322158 | 1721 | 346.2 | PV | 455-H3 | 2018-12-19 | 2019-01-16 | 20 |  | 20 | 2019-01-25 |  | -31032 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-23 | [7 empty] | 0 |  | 0 |  |  | 2021-08-03 | Online
NSTAR | Woburn | 2322181 | 1801 | 15.2 | PV | 375-H12 | 2018-12-28 | 2019-01-16 | 13 |  | 13 | 2019-01-25 |  | -31032 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-19 | [7 empty] | 0 |  | 0 |  |  | 2020-02-27 | Online
NSTAR | Watertown | 2322219 | 2472 | 249.9 | PV | 467-H4 | 2019-01-15 | 2019-01-17 | 2 |  | 2 | 2019-01-28 |  | -31033 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dedham | 2322394 | 2026 | 499.5 | PV | 20-H5 | 2018-12-19 | 2019-01-17 | 21 |  | 21 | 2019-01-28 |  | -31033 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Online
NSTAR | Mattapoisett | 2322525 | 2739 | 115.2 | PV | 2-302-302 | 2019-01-15 | 2019-01-17 | 2 |  | 2 | 2019-01-29 |  | -31034 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2020-01-10 | Online
NSTAR | North Dartmouth | 2322528 | 2747 | 720 | PV | 2-541-541 | 2018-12-19 | 2019-01-17 | 21 |  | 21 | 2019-01-29 |  | -31034 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 2322577 | 2136 | 60 | PV | 344-08 | 2019-01-18 | 2019-01-18 | 0 |  | 0 | 2019-01-29 |  | -31034 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2019-12-11 | Online
NSTAR | Falmouth | 2322598 | 2536 | 3300 | PV & Battery | 4-98A-98A | 2019-01-17 |  | -31026 |  | 0 | 2019-01-29 |  | -31034 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2322632 | 1720 | 242 | PV | 416-H4 | 2019-01-18 |  | -31027 |  | 0 | 2019-01-30 |  | -31035 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-25 | [7 empty] | 0 |  | 0
NSTAR | Allston | 2322689 | 2134 | 57.6 | PV | 456-H3 | 2019-01-04 | 2019-01-09 | 3 |  | 3 | 2019-01-30 |  | -31035 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online
NSTAR | Needham | 2322796 | 2492 | 28.8 | PV | 148-H1 | 2019-01-18 | 2019-01-25 | 5 |  | 5 | 2019-01-30 |  | -31035 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0 |  |  | 2019-08-22 | Online
NSTAR | Barnstable | 2322818 | 2668 | 17.92 | PV | 4-87B-473 | 2019-01-30 | 2019-01-30 | 0 | 0 | 0 | 2019-02-01 | 2019-02-26 | 17 | 0 | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-02-26 | 2019-03-01 | 2019-09-05 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2019-07-16 | Online | Private
NSTAR | Dorchester | 2322890 | 2122 | 260 | PV & Battery | 483-H7 | 2019-01-02 |  | -31015 |  | 0 | 2019-01-31 |  | -31036 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-07 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23 | Online
NSTAR | South Dennis | 2323237 | 2660 | 4951 | PV | tbd | 2019-01-24 | 2019-01-28 | 2 |  | 2 | 2019-01-31 |  | -31036 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2323317 | 2360 | 26.55 | PV | 3-13-943 | 2019-01-23 |  | -31030 |  | 0 | 2019-02-01 |  | -31037 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-25 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2323381 | 2459 | 1000 | PV | 282-H8 | 2019-01-24 |  | -31031 |  | 0 | 2019-02-01 |  | -31037 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2323400 | 2451 | 480 | PV | 450-H7 | 2019-01-25 |  | -31032 |  | 0 | 2019-02-01 |  | -31037 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-17 | [7 empty] | 0 |  | 0 |  |  | 2021-09-22 | Online
NSTAR | Dorchester | 2323443 | 2124 | 15.2 | PV | 483-H2 | 2019-01-07 | 2019-01-14 | 5 |  | 5 | 2019-02-01 |  | -31037 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-26 | [7 empty] | 0 |  | 0 |  |  | 2020-11-24 | Online
NSTAR | Sandwich | 2323654 | 2563 | 2660 | PV | 4-81B-443 | 2019-01-23 | 2019-01-29 | 4 |  | 4 | 2019-02-04 |  | -31038 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Westport | 2323699 | 2790 | 72 | PV | 2-532-532 | 2019-01-22 | 2019-01-31 | 7 |  | 7 | 2019-02-05 |  | -31039 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-03 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2323714 | 2360 | 700 | PV | 3-71-937 | 2019-01-25 | 2019-01-29 | 2 |  | 2 | 2019-02-06 |  | -31040 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-05-21 | Online
NSTAR | Ashland | 2323862 | 1721 | 500 | PV | 455-H3 | 2019-01-07 | 2019-01-11 | 4 |  | 4 | 2019-02-05 |  | -31039 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2323875 | 2747 | 699.3 | PV | 2-528-528 | 2019-01-17 | 2019-01-22 | 3 |  | 3 | 2019-02-08 |  | -31042 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2323953 | 2571 | 2000 | PV | 3-82-82 | 2019-02-06 |  | -31040 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-01-24 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Carver | 2324188 | 2330 | 2350 | PV | 3-10-930 | 2019-01-18 | 2019-01-23 | 3 |  | 3 | 2019-02-08 |  | -31042 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Boston | 2324396 | 2128 | 115.2 | PV | 488-H5 | 2019-01-18 | 2019-01-23 | 3 |  | 3 | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-21 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Canton | 2324409 | 2021 | 299.7 | PV | 269-1320H1 | 2019-01-17 |  | -31026 |  | 0 | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-14 | [7 empty] | 0 |  | 0
NSTAR | Freetown | 2324659 | 1701 | 4980 | PV & Battery | 2-605-605 | 2018-12-27 | 2019-02-01 | 26 |  | 26 | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Brewster | 2324673 | 2631 | 25 | PV | 4-95A-597 | 2019-01-28 | 2019-02-01 | 4 |  | 4 | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-13 | [7 empty] | 0 |  | 0 |  |  | 2019-07-01 | Online
NSTAR | South Dennis | 2324745 | 2660 | 133.3 | PV | 4-92B-92B | 2019-02-01 | 2019-02-01 | 0 |  | 0 | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-25 | [7 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Cambridge | 2324814 | 2139 | 44000 | CHP | 831-1314 | 2019-02-12 | 2019-02-19 | 5 | 0 | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-19 | 2019-03-04 | 9 | 0 | 9 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-06-30 | No |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Woburn | 2325016 | 1801 | 243.1 | PV | 375-H3 | 2018-12-26 | 2019-02-07 | 31 |  | 31 | 2019-02-13 |  | -31045 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-16 | [7 empty] | 0 |  | 0 |  |  | 2021-08-25 | Online
NSTAR | Acton | 2325167 | 1720 | 43.2 | PV | 416-H2 | 2019-02-07 | 2019-02-07 | 0 |  | 0 | 2019-02-14 |  | -31046 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2020-09-25 | Online
NSTAR | Framingham | 2325422 | 1702 | 240 | PV | 433-H8 | 2019-01-14 | 2019-01-14 | 0 |  | 0 | 2019-02-15 |  | -31047 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-02 | Online
NSTAR | Weston | 2325546 | 2493 | 200 | PV | 342-H1 | 2019-02-08 |  | -31042 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | Brewster | 2325660 | 2631 | 24.99 | PV | 4-95B-600 | 2019-02-05 | 2019-02-08 | 3 |  | 3 | 2019-02-15 |  | -31047 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-02-26 | [7 empty] | 0 |  | 0 |  |  | 2019-07-15 | Online
NSTAR | Framingham | 2325768 | 1702 | 996 | PV | 240-H6 | 2019-02-06 | 2019-02-08 | 2 |  | 2 | 2019-02-19 |  | -31049 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2325785 | 1801 | 216 | PV | 375-H14 | 2019-02-05 | 2019-02-08 | 3 |  | 3 | 2019-02-19 |  | -31049 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | Woburn | 2325824 | 1801 | 250 | PV | 211-H6 | 2019-02-06 | 2019-02-08 | 2 |  | 2 | 2019-02-19 |  | -31049 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-07-02 | Online
NSTAR | Rochester | 2325833 | 2770 | 20 | PV | 3-703-703 | 2019-02-06 | 2019-02-11 | 3 |  | 3 | 2019-02-20 |  | -31050 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-19 | [7 empty] | 0 |  | 0 |  |  | 2019-05-30 | Online
NSTAR | East Walpole | 2326033 | 2032 | 2370 | PV | 2-102-604 | 2019-01-29 | 2019-02-11 | 9 |  | 9 | 2019-02-20 |  | -31050 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-07-20 | Online
NSTAR | Boston | 2326176 | 2130 | 37.8 | PV | 528-169H | 2019-01-23 | 2019-02-04 | 8 |  | 8 | 2019-02-22 |  | -31052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  | 2021-05-13 | Online
NSTAR | Dorchester | 2326311 | 2125 | 1516 | PV | 466-1481H1 | 2019-01-28 |  | -31033 |  | 0 | 2019-02-22 |  | -31052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 2326325 | 2494 | 194 | PV | 148-H4 | 2019-02-04 |  | -31038 |  | 0 | 2019-02-22 |  | -31052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2019-09-10 | Online
NSTAR | Dorchester | 2326537 | 2122 | 52.2 | PV | 466-1482H1 | 2019-02-07 |  | -31041 |  | 0 | 2019-02-22 |  | -31052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-28 | [7 empty] | 0 |  | 0 |  |  | 2021-03-08 | Online
NSTAR | Carver | 2326793 | 2330 | 2000 | PV | 3-10-917 | 2019-02-11 | 2019-02-12 | 1 |  | 1 | 2019-02-25 |  | -31053 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2326814 | 1801 | 233.1 | PV | 211-H6 | 2019-02-12 | 2019-02-12 | 0 |  | 0 | 2019-02-25 |  | -31053 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Hopkinton | 2326836 | 1748 | 206 | PV | 126-H2 | 2019-02-13 | 2019-02-13 | 0 |  | 0 | 2019-02-25 |  | -31053 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-29 | [7 empty] | 0 |  | 0 |  |  | 2020-03-31 | Online
NSTAR | Stoneham | 2326872 | 2180 | 200 | PV | 375-H7 | 2019-02-13 | 2019-02-13 | 0 |  | 0 | 2019-02-26 |  | -31054 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | Chatham | 2326896 | 2633 | 117.12 | PV & Battery | 4-95A-95A | 2019-01-23 | 2019-02-04 | 8 |  | 8 | 2019-02-26 |  | -31054 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-15 | [7 empty] | 0 |  | 0 |  |  | 2020-07-01 | Online
NSTAR | Burlington | 2327102 | 1805 | 5274.6 | PV & Battery | 541-1377H | 2019-01-22 | 2019-02-15 | 18 |  | 18 | 2019-02-27 |  | -31055 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0
NSTAR | Falmouth | 2327130 | 2540 | 4980 | PV & Battery | 4-98B-448 | 2019-02-01 | 2019-02-15 | 10 |  | 10 | 2019-02-27 |  | -31055 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2327251 | 2138 | 86.4 | PV | 831-1336XY | 2019-02-14 | 2019-02-22 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2021-01-21 | Online
NSTAR | Chilmark | 2327284 | 2535 | 25 | PV | 4-91-126 | 2019-02-20 | 2019-02-22 | 2 |  | 2 | 2019-02-28 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-06 | [7 empty] | 0 |  | 0 |  |  | 2019-10-02 | Online
NSTAR | Plympton | 2327303 | 2367 | 2000 | PV | 3-10-930 | 2019-02-11 | 2019-02-12 | 1 |  | 1 | 2019-02-28 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2327320 | 2739 | 2000 | PV | 2-302-302 | 2019-02-12 | 2019-02-14 | 2 |  | 2 | 2019-02-28 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2327357 | 2114 | 50 | PV | 528-169H | 2019-02-14 | 2019-02-14 | 0 |  | 0 | 2019-02-28 |  | -31056 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-22 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | Chilmark | 2327379 | 2535 | 16.24 | PV | 4-97-220 | 2019-02-20 | 2019-02-20 | 0 |  | 0 | 2019-03-01 |  | -31057 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-08 | [7 empty] | 0 |  | 0
NSTAR | Westwood | 2327596 | 2090 | - |  | TBD | 2019-03-01 |  | -31057 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-10-04 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Rochester | 2328012 | 2770 | 15000 | PV | 3-85-85 | 2018-12-12 | 2018-12-18 | 4 |  | 4 | 2019-03-04 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2328021 | 2330 | 499 | PV |  | 2019-03-04 | 2019-03-07 | 3 | 0 | 3 | 2019-03-07 | 2019-03-20 | 9 | 0 | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 2019-04-17 | 2020-10-16 | No | EXP | 30 | 2020-10-14 |  | -31480 |  | 0 |  |  |  | In Queue | Private
NSTAR | Plymouth | 2328025 | 2360 | 630 | PV & Battery | 3-71-937 | 2019-02-19 | 2019-02-19 | 0 |  | 0 | 2019-03-04 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2328085 | 2717 | 27.42 | PV | 2-102-102 | 2019-02-20 | 2019-02-21 | 1 |  | 1 | 2019-03-05 |  | -31059 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-04 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | Plymouth | 2328095 | 2360 | 500 | PV & Battery | 3-89-89 | 2019-02-22 | 2019-02-22 | 0 |  | 0 | 2019-03-05 |  | -31059 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2328177 | 1760 | 32.4 | PV | 433-H10 | 2019-01-07 | 2019-01-07 | 0 |  | 0 | 2019-03-04 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-05 | [7 empty] | 0 |  | 0 |  |  | 2019-12-27 | Online
NSTAR | Framingham | 2328190 | 1701 | 57 | PV |  | 2019-03-05 | 2019-11-25 | 189 | 182 | 7 | 2019-11-25 | 2019-12-10 | 11 | 0 | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-12-20 |  | 2019-10-06 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2022-11-21 | Online | Private | N
NSTAR | Boston | 2328228 | 2134 | 180 | PV | 350-H4 | 2019-02-21 | 2019-02-25 | 2 |  | 2 | 2019-03-05 |  | -31059 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-08 | [7 empty] | 0 |  | 0 |  |  | 2020-10-19 | Online
NSTAR | Roxbury Crossing | 2328268 | 2120 | 72 | PV | 350-H4 | 2019-02-21 | 2019-02-25 | 2 |  | 2 | 2019-03-06 |  | -31060 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Newton | 2328535 | 2460 | 220 | PV | 17-H1 | 2019-01-17 | 2019-02-26 | 28 |  | 28 | 2019-03-07 |  | -31061 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-09-15 | Online
NSTAR | Norfolk | 2328724 | 2056 | 195 | PV | 146-H9 | 2019-02-14 | 2019-02-19 | 3 |  | 3 | 2019-03-08 |  | -31062 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2328863 | 2601 | 100 | PV | 4-63-63 | 2019-02-21 | 2019-02-25 | 2 |  | 2 | 2019-03-12 |  | -31064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-09-18 | Online
NSTAR | Waltham | 2329018 | 2451 | 924 | PV | 450-H7 | 2019-02-21 | 2019-03-04 | 7 |  | 7 | 2019-03-11 |  | -31063 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-21 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2329096 | 2021 | 1100 | PV | 269-1320H1 | 2019-02-06 | 2019-02-28 | 16 |  | 16 | 2019-03-12 |  | -31064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2329126 | 2131 | 20.7 | PV | 468-02 | 2019-01-04 | 2019-02-27 | 38 |  | 38 | 2019-03-12 |  | -31064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-17 | [7 empty] | 0 |  | 0 |  |  | 2019-08-05 | Online
NSTAR | Hyannis | 2329185 | 2601 | 43.6 | PV | 4-63-63 | 2019-02-25 | 2019-02-28 | 3 |  | 3 | 2019-03-12 |  | -31064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-09-23 | Online
NSTAR | Sherborn | 2329192 | 1770 | 34.78 | PV | 240-H1 | 2019-02-15 | 2019-02-26 | 7 |  | 7 | 2019-03-12 |  | -31064 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
NSTAR | Brewster | 2329348 | 2631 | 20 | PV | 4-89B-576 | 2019-02-28 | 2019-03-05 | 3 |  | 3 | 2019-03-13 |  | -31065 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-03-26 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2329391 | 2739 | 4600 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-02-28 | 6 |  | 6 | 2019-03-14 |  | -31066 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2329466 | 2743 | 4980 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-02-28 | 6 |  | 6 | 2019-03-15 |  | -31067 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2330206 | 2739 | 2600 | PV & Battery | 2-302-302 | 2019-02-20 | 2019-03-06 | 10 |  | 10 | 2019-03-18 |  | -31068 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2330259 | 1801 | 233.2 | PV | 375-H3 | 2019-03-05 | 2019-03-08 | 3 |  | 3 | 2019-03-18 |  | -31068 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-10 | [7 empty] | 0 |  | 0 |  |  | 2019-11-12 | Online
NSTAR | Sandwich | 2330325 | 2644 | 5000 | PV & Battery | 4-81B-443 | 2019-02-22 | 2019-02-27 | 3 |  | 3 | 2019-03-19 |  | -31069 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2330355 | 2459 | 266 | PV | 17-H2 | 2019-03-11 | 2019-03-11 | 0 |  | 0 | 2019-03-19 |  | -31069 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-07 | [7 empty] | 0 |  | 0 |  |  | 2021-09-08 | Online
NSTAR | Sandwich | 2330360 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330392 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | 5 |  | 5 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 2330416 | 2492 | 23.3 | PV | 148-H4 | 2019-02-12 | 2019-03-07 | 17 |  | 17 | 2019-03-19 |  | -31069 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-08-21
NSTAR | South Yarmouth | 2330447 | 2664 | 233.64 | PV | 4-90-90 | 2019-02-28 | 2019-03-06 | 4 |  | 4 | 2019-03-19 |  | -31069 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2330458 | 2601 | 699.9 | PV | 4-63-63 | 2019-03-04 | 2019-03-12 | 6 |  | 6 | 2019-03-20 |  | -31070 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-08 | [7 empty] | 0 |  | 0 |  |  | 2022-12-31 | Online
NSTAR | Assonett | 2330491 | 2702 | 4890 | PV & Battery |  | 2019-03-19 | 2019-03-20 | 1 | 0 | 1 | 2019-03-26 |  | -31074 | 439 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2019-04-02
NSTAR | Winchester | 2330512 | 1890 | 37.8 | PV | 211-H1 | 2019-03-01 | 2019-03-11 | 6 |  | 6 | 2019-03-22 |  | -31072 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2020-09-09 | Online
NSTAR | Sandwich | 2330718 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | 5 |  | 5 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330720 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-08 | 2019-03-15 | 5 |  | 5 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapoisett | 2330775 | 2739 | 4980 | PV & Battery | 2-302-302 | 2019-02-21 | 2019-03-06 | 9 |  | 9 | 2019-03-29 |  | -31077 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-01 | Withdrawn
NSTAR | Roslindale | 2330819 | 2131 | 42.8 | PV | 1312 | 2019-02-21 | 2019-03-04 | 7 |  | 7 | 2019-03-22 |  | -31072 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-09-05
NSTAR | Sandwich | 2330875 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330882 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330923 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2330926 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-07 | 2019-03-15 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | 2330941 | 2081 | 250 | PV | 146-H1 | 2019-03-08 | 2019-03-13 | 3 |  | 3 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 2331027 | 2653 | 133.3 | PV | TBD | 2019-03-22 |  | -31072 | 0 | 0 | 2019-04-17 | 2019-05-04 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-04-15 | 2019-11-21 | 2019-10-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Sandwich | 2331148 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331153 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2331280 | 2744 | 250 | PV | 2-241-241 | 2019-03-04 | 2019-03-13 | 7 |  | 7 | 2019-03-26 |  | -31074 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2331299 | 2743 | 250 | PV | 2-241-241 | 2019-03-04 | 2019-03-13 | 7 |  | 7 | 2019-03-26 |  | -31074 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331348 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331371 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2331457 | 2118 | 1000 | PV & Battery | 4912 | 2019-02-11 | 2019-03-14 | 23 |  | 23 | 2019-03-26 |  | -31074 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2331587 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-03-11 | 2019-03-15 | 4 |  | 4 | 2019-03-25 |  | -31073 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2331592 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-01-02 | 2019-02-26 | 39 |  | 39 | 2019-01-15 |  | -31024 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2331739 | 2142 | 75 | PV | 875-1N35B | 2019-02-14 | 2019-03-15 | 21 |  | 21 | 2019-03-28 |  | -31076 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0 |  |  | 2019-10-25 | Online
NSTAR | Walpole | 2331931 | 2081 | 407 | PV | 146-H1 | 2019-01-11 | 2019-03-15 | 45 |  | 45 | 2019-03-29 |  | -31077 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 2332061 | 2649 | 254.29 | PV | 4-88-483 | 2019-03-13 | 2019-03-15 | 2 |  | 2 | 2019-03-29 |  | -31077 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-09 | [7 empty] | 0 |  | 0 |  |  | 2020-02-03 | Online
NSTAR | Ashland | 2333111 | 1721 | 250 | PV & Battery | 455-H3 | 2019-03-05 | 2019-03-18 | 9 |  | 9 | 2019-04-04 |  | -31081 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2333220 | 1721 | 250 | PV | 455-H3 | 2019-01-11 | 2019-03-18 | 46 |  | 46 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2333229 | 1760 | 407 | PV & Battery | 433-H10 | 2019-01-17 | 2019-03-18 | 42 |  | 42 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2333242 | 2601 | 254.29 | PV | 4-63-63 | 2019-03-14 | 2019-03-19 | 3 |  | 3 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-23 | [7 empty] | 0 |  | 0 |  |  | 2020-01-09 | Online
NSTAR | Dorchester | 2333256 | 2124 | 240 | PV | 466-1481H1 | 2019-03-08 | 2019-03-19 | 7 |  | 7 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2333267 | 2421 | - |  | TBD | 2019-04-04 |  | -31081 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-11-08 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Duxbury | 2333489 | 2332 | 20 | PV | 3-26-903 | 2019-03-07 | 2019-03-22 | 11 |  | 11 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2333508 | 2740 | 346.5 | PV | 2-137-139 | 2019-03-18 | 2019-03-22 | 4 |  | 4 | 2019-04-09 |  | -31084 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2333666 | 2745 | 22.8 | PV | 2-87-135 | 2019-03-13 | 2019-03-25 | 8 |  | 8 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2022-01-06 | Online
NSTAR | Newton | 2333672 | 2460 | 360 | PV | 282-H8 | 2019-03-22 | 2019-03-25 | 1 |  | 1 | 2019-04-08 |  | -31083 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-11 | [7 empty] | 0 |  | 0 |  |  | 2021-08-24 | Online
NSTAR | Wareham | 2333726 | 2571 | 4500 | PV | 8-83-83 | 2019-03-22 | 2019-03-25 | 1 |  | 1 | 2019-04-09 |  | -31084 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2333746 | 2571 | 4500 | PV |  | 2019-04-08 | 2019-04-09 | 1 | 0 | 1 | 2019-04-10 |  | -31085 | 427 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 2020-06-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2019-04-18
NSTAR | South Boston | 2333766 | 2127 | 172.8 | PV | 106-H3 | 2019-03-05 | 2019-03-25 | 14 |  | 14 | 2019-04-09 |  | -31084 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-09 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21 | Online
NSTAR | Walpole | 2333782 | 2081 | 34.2 | PV | 146-H4 | 2019-04-08 | 2019-04-12 | 4 | 0 | 4 | 2019-04-19 | 2019-05-30 | 29 | 0 | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | South Dennis | 2333807 | 2660 | 699.7 | PV | 4-92B-92B | 2019-03-04 | 2019-03-25 | 15 |  | 15 | 2019-04-09 |  | -31084 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2020-10-23 | Online
NSTAR | Edgartown | 2333814 | 2539 | 24 | PV | TBD | 2019-02-26 | 2019-03-20 | 16 |  | 16 | 2019-04-09 |  | -31084 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-15 | [7 empty] | 0 |  | 0 |  |  | 2020-02-11 | Online
NSTAR | Walpole | 2334013 | 2081 | 400 | PV |  | 2019-04-10 | 2019-04-12 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-19 | 2020-06-03 | 293 | 0 | 293 |  |  | 0 |  | 0 | 2020-11-17 | 2020-11-20 | 3 | 0 | 3 | 2020-02-21 | 2020-12-29 | 2021-01-15 | No |  | 60 | 2020-02-10 |  | -31303 |  | 0 |  |  | 2021-05-24 | Online | Private | N
NSTAR | Walpole | 2334039 | 2081 | 131.4 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | 4 | 0 | 4 | 2019-04-19 | 2019-06-15 | 40 | 0 | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | 2020-06-09 | 2020-10-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Forestdale | 2334165 | 2644 | 4990 | PV | 4-81B-443 | 2019-03-14 | 2019-03-26 | 8 |  | 8 | 2019-04-11 |  | -31086 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2334186 | 2360 | 144 | PV | 3-89-89 | 2019-03-20 | 2019-03-26 | 4 |  | 4 | 2019-04-11 |  | -31086 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-11-18 | Online
NSTAR | Walpole | 2334212 | 2081 | 37.8 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | 4 | 0 | 4 | 2019-04-18 | 2019-05-31 | 31 | 0 | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-04 | 2019-06-18 | 2020-06-04 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private | N
NSTAR | Walpole | 2334218 | 2081 | 32.4 | PV | 146-H4 | 2019-04-10 | 2019-04-16 | 4 | 0 | 4 | 2019-04-19 | 2019-05-30 | 29 | 0 | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2021-02-04 | Online | Private
NSTAR | Walpole | 2334252 | 2081 | 90 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | 3 | 0 | 3 | 2019-04-19 | 2019-05-30 | 29 | 0 | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2021-02-04 | Online | Gov't
NSTAR | Walpole | 2334255 | 2081 | 90 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | 3 | 0 | 3 | 2019-04-19 | 2019-05-30 | 29 | 0 | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2021-02-04 | Online | Gov't
NSTAR | Mattapoisett | 2334358 | 2739 | 3300 | PV & Battery | 2-302-302 | 2019-02-21 | 2019-03-27 | 24 |  | 24 | 2019-04-11 |  | -31086 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-01 | Withdrawn
NSTAR | New Bedford | 2334371 | 2744 | 180 | PV | 2-137-139 | 2019-01-31 | 2019-03-27 | 39 |  | 39 | 2019-04-11 |  | -31086 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2021-07-29 | Online
NSTAR | Sandwich | 2334390 | 2563 | 250 | PV & Battery | 4-81B-443 | 2019-03-27 | 2019-03-27 | 0 |  | 0 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0
NSTAR | Bedford | 2334399 | 1730 | 200 | PV | 322-05 | 2019-03-25 | 2019-03-28 | 3 |  | 3 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Walpole | 2334411 | 2081 | 142 | PV | 146-H4 | 2019-04-11 | 2019-04-16 | 3 | 0 | 3 | 2019-04-18 | 2019-05-30 | 30 | 0 | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | 2019-06-18 | 2020-06-04 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2021-02-09 | Online | Gov't
NSTAR | Walpole | 2334415 | 2081 | 129.6 | PV | TBD | 2019-04-11 |  | -31086 | 0 | 0 | 2019-04-19 | 2019-05-30 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-06-04 | 2020-01-08 | 2019-11-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Gov't
NSTAR | Sandwich | 2334444 | 2563 | 77.5 | PV | 4-81B-443 | 2019-02-19 | 2019-03-28 | 27 |  | 27 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-10-20 | Online
NSTAR | East Dennis | 2334447 | 2641 | 36 | PV | 4-89A-552 | 2019-03-25 | 2019-03-28 | 3 |  | 3 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 | [7 empty] | 0 |  | 0 |  |  | 2019-08-12 | Online
NSTAR | Sudbury | 2334450 | 1776 | 15.2 | PV & Battery | 342-H5 | 2019-03-29 | 2019-04-12 | 10 |  | 10 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-15 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Walpole | 2334456 | 2081 | 1000 | PV & Battery | 146-H1 | 2019-03-15 | 2019-03-28 | 9 |  | 9 | 2019-04-15 |  | -31088 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2334473 | 2745 | 496 | PV |  | 2019-04-12 | 2019-04-16 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-18 | 2020-09-08 | 363 | 319 | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-05 |  | 2020-06-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2019-09-20
NSTAR | Lexington | 2334511 | 2421 | 1500 | PV & Battery | 533-H1 | 2019-03-15 | 2019-03-20 | 3 |  | 3 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2334531 | 2747 | 1000 | PV | 2-528-528 | 2019-03-08 | 2019-03-19 | 7 |  | 7 | 2019-04-12 |  | -31087 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2334854 | 2745 | 199.8 | PV | 2-137-139 | 2019-04-15 | 2019-04-16 | 1 | 0 | 1 | 2019-04-18 |  | -31091 | 379 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-05 |  | 2020-06-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2019-06-26
NSTAR | Milton | 2335039 | 2186 | 61.2 | PV | 496-H2 | 2019-03-28 | 2019-04-01 | 2 |  | 2 | 2019-04-16 |  | -31089 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | [7 empty] | 0 |  | 0 |  |  | 2020-03-17 | Online
NSTAR | Plymouth | 2335156 | 2360 | - |  | TBD | 2019-04-16 |  | -31089 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-11-21 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Norfolk | 2335261 | 2056 | 50 | PV | 146-H9 | 2019-04-01 | 2019-04-01 | 0 |  | 0 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-05 | [7 empty] | 0 |  | 0 |  |  | 2020-03-03 | Online
NSTAR | Jamaica Plain | 2335383 | 2130 | 432.9 | PV | 496-H4 | 2019-04-02 | 2019-04-02 | 0 |  | 0 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-01 | [7 empty] | 0 |  | 0 |  |  | 2021-07-07 | Online
NSTAR | Natick | 2335440 | 1760 | 150 | CHP | 433-H7 | 2019-03-26 | 2019-04-02 | 5 |  | 5 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2020-02-18 | Online
NSTAR | South Dennis | 2335447 | 2660 | 133.2 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | 2 |  | 2 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | South Dennis | 2335454 | 2660 | 166.6 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | 2 |  | 2 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Dennis | 2335459 | 2660 | 166.6 | PV | 4-92B-92B | 2019-04-01 | 2019-04-03 | 2 |  | 2 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2335506 | 2770 | 25 | PV | 3-702-702 | 2019-03-20 | 2019-04-02 | 9 |  | 9 | 2019-05-03 |  | -31102 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2335814 | 2360 | 1800 | PV | 3-89-89 | 2019-03-20 | 2019-04-04 | 11 |  | 11 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2335827 | 2330 | 2000 | PV & Battery | 3-81-950 | 2019-03-28 | 2019-04-04 | 5 |  | 5 | 2019-04-22 |  | -31093 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2336013 | 2021 | 200.4 | PV | 269-1320H1 | 2019-04-05 | 2019-04-08 | 1 |  | 1 | 2019-04-23 |  | -31094 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2019-12-20 | Online
NSTAR | Plymouth | 2336042 | 2360 | 366 | PV |  | 2019-04-23 | 2019-04-23 | 0 | 0 | 0 | 2019-04-23 | 2019-05-22 | 21 | 0 | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-23 | 2020-09-02 | 2019-11-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2023-03-28 | Online | Private
NSTAR | Cambridge | 2336049 | 2142 | 35 | CHP | 875-1N25A | 2019-03-12 | 2019-04-08 | 19 |  | 19 | 2019-04-23 |  | -31094 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-02 | [7 empty] | 0 |  | 0
NSTAR | Norfolk | 2336071 | 2056 | 4990 | PV & Battery | 146-H9 | 2019-04-05 | 2019-04-08 | 1 |  | 1 | 2019-04-23 |  | -31094 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | 2336099 | 2719 | 5000 | PV |  | 2019-04-23 | 2019-04-25 | 2 | 0 | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-04-25 |  | -31096 | 256 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 |  | 2020-06-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2020-04-18
NSTAR | West Wareham | 2336183 | 2576 | 57.6 | PV | 3-86-86 | 2019-04-10 | 2019-04-10 | 0 |  | 0 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-16 | Online
NSTAR | Rochester | 2336283 | 2770 | 17.52 | PV | 3-85-85 | 2019-04-09 | 2019-04-11 | 2 |  | 2 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-28 | [7 empty] | 0 |  | 0 |  |  | 2019-10-11 | Online
NSTAR | Falmouth | 2336292 | 2556 | 26 | PV | 4-98B-448 | 2019-04-04 | 2019-04-11 | 5 |  | 5 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-24 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Natick | 2336317 | 1760 | 366.6 | PV | 433-H5 | 2019-04-04 | 2019-04-12 | 6 |  | 6 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Waltham | 2336372 | 2451 | 166.6 | PV | 450-H7 | 2019-04-04 | 2019-04-12 | 6 |  | 6 | 2019-04-25 |  | -31096 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2336465 | 1741 | 496 | PV | 512-1399h1 | 2019-04-10 | 2019-04-15 | 3 |  | 3 | 2019-04-26 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2337102 | 1741 | 484 | PV | 512-1399h1 | 2019-04-10 | 2019-04-15 | 3 |  | 3 | 2019-04-30 |  | -31099 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-26 | [7 empty] | 0 |  | 0 |  |  | 2021-09-30 | Online
NSTAR | Freetown | 2337126 | 2702 | 4890 | PV & Battery | 2-605-605 | 2019-04-12 | 2019-04-15 | 1 |  | 1 | 2019-05-01 |  | -31100 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2337174 | 2717 | 4890 | PV & Battery | 2-605-605 | 2019-04-16 | 2019-04-17 | 1 |  | 1 | 2019-05-01 |  | -31100 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2337311 | 2360 | 195 | PV | 3-89-89 | 2019-03-26 | 2019-04-01 | 4 |  | 4 | 2019-05-02 |  | -31101 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-20 | [7 empty] | 0 |  | 0
NSTAR | Brighton | 2337320 | 2135 | 250 | PV | 467-H12 | 2019-03-29 | 2019-04-03 | 3 |  | 3 | 2019-05-02 |  | -31101 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-21 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2337333 | 2021 | 133.6 | PV | 269-1320H1 | 2019-02-11 | 2019-04-08 | 40 |  | 40 | 2019-05-02 |  | -31101 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-06 | [7 empty] | 0 |  | 0 |  |  | 2020-11-17 | Online
NSTAR | Hatchville | 2337408 | 2536 | 28.5 | PV | 4-98A-98A | 2019-02-26 | 2019-04-12 | 33 |  | 33 | 2019-05-02 |  | -31101 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-17 | [7 empty] | 0 |  | 0
NSTAR | Bedford | 2337464 | 1730 | 35 | CHP | 322-05 | 2019-04-01 | 2019-04-22 | 15 |  | 15 | 2019-05-03 |  | -31102 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | Brighton | 2337496 | 2135 | 86.6 | PV | 329-H2 | 2019-04-18 | 2019-04-22 | 2 |  | 2 | 2019-05-03 |  | -31102 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-30 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Somerville | 2338222 | 2145 | 99.9 | PV | 250-H4XY | 2019-04-18 | 2019-04-22 | 2 |  | 2 | 2019-05-06 |  | -31103 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  | 2021-01-26 | Online
NSTAR | Ashland | 2338277 | 1721 | 19 | PV | 519-175H1 | 2019-04-17 | 2019-04-18 | 1 |  | 1 | 2019-05-08 |  | -31105 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-13 | [7 empty] | 0 |  | 0 |  |  | 2019-12-27 | Online
NSTAR | Carver | 2338333 | 2330 | - |  | TBD | 2019-05-06 |  | -31103 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-12 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Carver | 2338339 | 2330 | 9500 | PV & Battery | 3-81-950 | 2019-04-08 | 2019-04-30 | 16 |  | 16 | 2019-05-07 |  | -31104 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marion | 2338418 | 2738 | 99.9 | PV | 3-304-304 | 2019-04-18 | 2019-04-18 | 0 |  | 0 | 2019-05-08 |  | -31105 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-22 | [7 empty] | 0 |  | 0 |  |  | 2019-10-16 | Online
NSTAR | East Boston | 2338574 | 2128 | 43.2 | PV | 488-H5 | 2019-04-22 | 2019-04-23 | 1 |  | 1 | 2019-05-08 |  | -31105 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-25 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | East Boston | 2338586 | 2128 | 28.8 | PV | 592-72XY | 2019-04-22 | 2019-04-23 | 1 |  | 1 | 2019-05-08 |  | -31105 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 1900-01-03 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Waltham | 2338649 | 2453 | 99.9 | PV | 33-H3 | 2019-04-17 | 2019-04-23 | 4 |  | 4 | 2019-05-09 |  | -31106 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Framingham | 2338764 | 1702 | 15.2 | PV | 455-H5 | 2019-01-04 | 2019-04-19 | 75 |  | 75 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-21 | [7 empty] | 0 |  | 0 |  |  | 2019-12-30 | Online
NSTAR | Plymouth | 2338789 | 2360 | 756 | PV | 3-89-89 | 2019-04-09 | 2019-04-25 | 12 |  | 12 | 2019-05-09 |  | -31106 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Assonett | 2339086 | 2702 | 4498 | PV |  | 2019-05-10 | 2019-05-10 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-14 |  | -31109 | 409 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2019-12-18 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2019-05-14
NSTAR | New Bedford | 2339142 | 2746 | 355 | PV |  | 2019-05-10 | 2019-05-17 | 5 | 0 | 5 | 2019-05-27 |  | -31118 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 |  | 2020-03-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Gov't
NSTAR | New Bedford | 2339509 | 2744 | 113 | PV |  | 2019-05-13 | 2019-05-17 | 4 | 0 | 4 | 2019-05-27 | 2020-06-16 | 276 | 0 | 276 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | 2020-12-15 | 2020-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Sharon | 2339541 | 2067 | 57.6 | PV | 146-H7 | 2019-04-23 | 2019-04-25 | 2 |  | 2 | 2019-05-14 |  | -31109 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-29 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | New Bedford | 2339571 | 2745 | 129.6 | PV |  | 2019-05-13 | 2019-05-22 | 7 | 0 | 7 | 2019-05-27 | 2020-09-17 | 343 | 0 | 343 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | 2020-12-15 | 2020-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Gov't
NSTAR | New Bedford | 2339580 | 2745 | - |  | TBD | 2019-05-13 |  | -31108 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-19 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | New Bedford | 2339584 | 2746 | 369.6 | PV | 2-89-181 | 2019-05-13 | 2019-05-21 | 6 | 0 | 6 | 2019-05-27 | 2019-11-13 | 122 | 0 | 122 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-03-20 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Gov't
NSTAR | Woburn | 2339665 | 1801 | 66.6 | PV | 375-H1 | 2019-04-18 | 2019-04-29 | 7 |  | 7 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | Hyde Park | 2339703 | 2136 | 40 | PV | 311-13 | 2019-04-19 | 2019-04-29 | 6 |  | 6 | 2019-05-14 |  | -31109 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Westwood | 2339939 | 2090 | 60 | PV | 20-H3 | 2019-04-18 | 2019-04-29 | 7 |  | 7 | 2019-05-16 |  | -31111 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Newton | 2340114 | 2459 | 57.6 | PV | 1708 | 2019-05-01 | 2019-05-02 | 1 |  | 1 | 2019-05-17 |  | -31112 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | North Dartmouth | 2340119 | 2747 | 999 | PV & Battery | 2-541-541 | 2019-03-21 | 2019-05-07 | 33 |  | 33 | 2019-05-17 |  | -31112 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2340125 | 2745 | 200 | PV | 2-137-139 | 2019-04-18 | 2019-05-08 | 14 |  | 14 | 2019-05-20 |  | -31113 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0 |  |  | 2021-10-19 | Online
NSTAR | Boston | 2340373 | 2118 | 60 | PV | 323-78H1 | 2019-04-19 | 2019-04-30 | 7 |  | 7 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Waltham | 2340378 | 2136 | - |  | TBD | 2019-05-17 |  | -31112 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-12-26 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Acusnet | 2340380 | 2743 | 2999 | PV & Battery | 2-241-241 | 2019-04-12 | 2019-04-30 | 12 |  | 12 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2340383 | 2453 | 40 | PV | 311-13 | 2019-04-17 | 2019-04-29 | 8 |  | 8 | 2019-05-28 |  | -31119 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Newton | 2340567 | 2460 | 72 | PV | 282-H8 | 2019-04-26 | 2019-05-01 | 3 |  | 3 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-24 | Online
NSTAR | Lincoln | 2340569 | 1773 | 38 | PV | 320-H8 | 2019-04-22 | 2019-05-01 | 7 |  | 7 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2019-12-12 | Online
NSTAR | Kingston | 2340663 | 2364 | 1800 | PV | 3-17-17 | 2019-04-25 | 2019-05-02 | 5 |  | 5 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-03-30 | Online
NSTAR | Walpole | 2340703 | 2071 | 99.9 | PV | 146-H1 | 2019-05-01 | 2019-05-03 | 2 |  | 2 | 2019-05-23 |  | -31116 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dennisport | 2340718 | 2637 | 250 | PV | 4-92B-583 | 2019-04-25 | 2019-04-30 | 3 |  | 3 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  | 2020-11-12 | Online
NSTAR | Dover | 2340724 | 2030 | 20.2 | PV | 456-H5 | 2019-04-11 | 2019-05-06 | 17 |  | 17 | 2019-05-21 |  | -31114 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2019-12-05 | Online
NSTAR | Dedham | 2340807 | 2026 | 20 | PV | 148-H3 | 2019-05-13 | 2019-05-13 | 0 |  | 0 | 2019-05-22 |  | -31115 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2019-03-27 | Online
NSTAR | Brewster | 2340839 | 2631 | 20.01 | PV | 4-89B-618 | 2019-04-12 | 2019-05-14 | 22 |  | 22 | 2019-05-22 |  | -31115 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0
NSTAR | Cambridge | 2340888 | 2138 | 66.6 | PV | 819-1NE4 | 2019-05-21 | 2019-05-22 | 1 | 0 | 1 | 2019-05-23 | 2019-06-18 | 18 | 0 | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 |  | 2019-12-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2020-12-16 | Online | Private
NSTAR | Woburn | 2340946 | 1801 | 480 | PV | TBD | 2019-05-08 | 2019-05-14 | 4 |  | 4 | 2019-05-22 |  | -31115 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-20 | [7 empty] | 0 |  | 0 |  |  | 2021-02-18 | Online
NSTAR | Cambridge | 2341088 | 2138 | 20.4 | PV | 831-1336XY | 2019-04-17 | 2019-05-15 | 20 |  | 20 | 2019-05-23 |  | -31116 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Woburn | 2341172 | 1801 | 166.5 | PV | 211-H6 | 2019-04-26 | 2019-05-15 | 13 |  | 13 | 2019-05-24 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-08 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2341237 | 1801 | 249.8 | PV | 211-H6 | 2019-04-26 | 2019-05-15 | 13 |  | 13 | 2019-05-24 |  | -31117 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dartmouth | 2341375 | 2748 | 200 | PV | 2-528-528 | 2019-05-09 | 2019-05-16 | 5 |  | 5 | 2019-05-28 |  | -31119 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2341496 | 2747 | 1000 | PV & Battery | 2-528-528 | 2019-02-25 | 2019-05-16 | 58 |  | 58 | 2019-05-28 |  | -31119 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sagamore Beach | 2341513 | 2562 | 20 | PV | 3-89-925 | 2019-05-16 | 2019-05-17 | 1 |  | 1 | 2019-05-28 |  | -31119 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-11 | [7 empty] | 0 |  | 0 |  |  | 2019-12-17 | Online
NSTAR | East Freetown | 2341535 | 2717 | 25 | PV | 2-102-102 | 2019-05-16 | 2019-05-17 | 1 |  | 1 | 2019-05-29 |  | -31120 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-01 | [7 empty] | 0 |  | 0 |  |  | 2020-10-22 | Online
NSTAR | Sharon | 2341555 | 2067 | 20.35 | PV | 470-H12 | 2019-04-22 | 2019-05-17 | 19 |  | 19 | 2019-05-29 |  | -31120 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-13 | [7 empty] | 0 |  | 0 |  |  | 2020-06-04 | Online
NSTAR | Norfolk | 2341849 | 2056 | 1000 | PV | 146-H9 | 2019-05-16 | 2019-05-20 | 2 |  | 2 | 2019-05-30 |  | -31121 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-11 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2341861 | 2360 | 114 | PV | 3-89-89 | 2019-05-20 | 2019-05-21 | 1 |  | 1 | 2019-05-30 |  | -31121 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | 2341981 | 2050 | 31.5 | PV & Battery | 3-25-42J2 | 2019-04-18 | 2019-05-21 | 23 |  | 23 | 2019-06-04 |  | -31124 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 2342846 | 2743 | 2640 | PV & Battery | 2-241-241 | 2019-04-10 | 2019-05-31 | 37 |  | 37 | 2019-06-04 |  | -31124 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2342972 | 1741 | 18.7 | PV | 512-1399h1 | 2019-05-16 | 2019-05-24 | 6 |  | 6 | 2019-06-04 |  | -31124 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-12 | [7 empty] | 0 |  | 0 |  |  | 2020-03-03 | Online
NSTAR | Dartmouth | 2342977 | 2747 | - | PV | TBD | 2019-06-03 |  | -31123 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-01-10 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Needham | 2342982 | 2494 | 43.2 | PV | 148-H1 | 2019-05-16 | 2019-05-22 | 4 |  | 4 | 2019-06-13 |  | -31131 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2020-02-06 | Online
NSTAR | Plymouth | 2343065 | 2360 | 250 | PV & Battery | 3-71-937 | 2019-05-21 | 2019-05-24 | 3 |  | 3 | 2019-06-04 |  | -31124 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2343104 | 1748 | 8485 | PV & Battery | 533-H7 | 2019-05-16 | 2019-05-24 | 6 |  | 6 | 2019-06-05 |  | -31125 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-16 | [7 empty] | 0 |  | 0
NSTAR | East Falmouth | 2343408 | 2536 | 36 | PV | 4-98A-98A | 2019-05-29 | 2019-05-29 | 0 |  | 0 | 2019-06-05 |  | -31125 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-17 | [7 empty] | 0 |  | 0 |  |  | 2020-03-05 | Online
NSTAR | Wareham | 2343539 | 2571 | 5000 | PV & Battery | 8-83-83 | 2019-05-21 | 2019-05-29 | 6 |  | 6 | 2019-06-06 |  | -31126 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | 2343563 | 2747 | 6000 | PV | 2-528-528 | 2019-05-06 | 2019-05-29 | 17 |  | 17 | 2019-06-06 |  | -31126 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2343564 | 1801 | 50 | PV | 211-H2 | 2019-05-14 | 2019-05-22 | 6 |  | 6 | 2019-06-13 |  | -31131 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-16 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21
NSTAR | Cambridge | 2343568 | 2140 | 32.4 | PV | 824-26 | 2019-05-13 | 2019-05-22 | 7 |  | 7 | 2019-06-13 |  | -31131 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2343632 | 1801 | 66.6 | PV | 211-H6 | 2019-05-28 | 2019-05-28 | 0 |  | 0 | 2019-06-06 |  | -31126 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-18 | [7 empty] | 0 |  | 0 |  |  | 2021-01-20 | Online
NSTAR | Cambridge | 2343786 | 2138 | 924 | PV | 831-1336XY | 2019-05-21 | 2019-05-30 | 7 |  | 7 | 2019-06-07 |  | -31127 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Falmouth | 2343832 | 2536 | 72 | PV | 4-98B-449 | 2019-05-28 | 2019-05-28 | 0 |  | 0 | 2019-06-07 |  | -31127 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-17 | [7 empty] | 0 |  | 0 |  |  | 2020-02-14 | Online
NSTAR | West Yarmouth | 2343868 | 2673 | 174 | PV & Battery | 4-92A-536 | 2019-05-21 | 2019-05-28 | 5 |  | 5 | 2019-06-10 |  | -31128 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-26 | [7 empty] | 0 |  | 0 |  |  | 2020-08-26 | Online
NSTAR | Wareham | 2344136 | 2571 | 5000 | PV & Battery | 8-83-83 | 2019-05-24 | 2019-05-30 | 4 |  | 4 | 2019-06-10 |  | -31128 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2344165 | 2460 | 216 | PV | 282-H8 | 2019-05-20 | 2019-05-30 | 8 |  | 8 | 2019-06-10 |  | -31128 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344421 | 2468 | 86 | PV | 292-H12 | 2019-04-25 | 2019-05-30 | 25 |  | 25 | 2019-06-12 |  | -31130 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344584 | 2460 | 109 | PV | TBD | 2019-05-08 | 2019-05-30 | 16 |  | 16 | 2019-06-14 |  | -31132 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2344713 | 2460 | 133 | PV | TBD | 2019-05-08 | 2019-05-30 | 16 |  | 16 | 2019-06-14 | 2019-05-30 | -13 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344729 | 2460 | 60 | PV | TBD | 2019-05-08 | 2019-05-30 | 16 |  | 16 | 2019-06-14 |  | -31132 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2344792 | 2459 | 136 | PV | 292-H8 | 2019-04-25 | 2019-05-30 | 25 |  | 25 | 2019-06-14 |  | -31132 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-01 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344807 | 2460 | 109 | PV | 467-H14 | 2019-05-20 | 2019-05-30 | 8 |  | 8 | 2019-06-14 |  | -31132 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2344839 | 2459 | 146 | PV | TBD | 2019-05-20 | 2019-05-30 | 8 |  | 8 | 2019-06-14 |  | -31132 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0
NSTAR | Roxbury | 2344916 | 2119 | 52.2 | PV | TBD | 2019-05-16 | 2019-05-31 | 11 |  | 11 | 2019-06-19 |  | -31135 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-12-29 | Online
NSTAR | New Bedford | 2345033 | 2746 | 496 | PV | 2-83-403 | 2017-02-01 | 2017-02-17 | 12 |  | 12 | 2017-02-28 |  | -30534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2017-03-29 | 2017-04-25 | [6 empty] | 0 |  | 0 |  |  | 2019-12-31
NSTAR | Cambridge | 2345372 | 2138 | 330 | PV | TBD | 2019-05-21 | 2019-06-03 | 9 |  | 9 | 2019-06-18 |  | -31134 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2345373 | 2421 | 22.95 | PV & Battery | 320-H2 | 2019-05-28 | 2019-06-04 | 5 |  | 5 | 2019-06-18 |  | -31134 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Newton | 2345601 | 2459 | 100 | PV | TBD | 2019-04-25 | 2020-06-04 | 290 |  | 290 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2345649 | 2664 | 249.9 | PV | TBD | 2019-05-29 | 2019-06-05 | 5 |  | 5 | 2019-06-19 |  | -31135 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-19 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Canton | 2345712 | 2021 | 688 | PV & Battery | 269-1320H1 | 2019-04-26 | 2019-06-06 | 29 |  | 29 | 2019-06-20 |  | -31136 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 2345953 | 2021 | 250 | PV | TBD | 2019-05-30 | 2019-06-07 | 6 |  | 6 | 2019-06-20 |  | -31136 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2021-03-02 | Online
NSTAR | Newton | 2346031 | 2461 | 145.1 | PV | 292-H1 | 2019-05-29 | 2019-06-07 | 7 |  | 7 | 2019-06-24 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-17 | [7 empty] | 0 |  | 0 |  |  | 2021-03-05 | Online
NSTAR | Chelsea | 2346218 | 2150 | 1736 | CHP | TBD | 2019-03-20 | 2019-06-03 | 53 |  | 53 | 2019-06-24 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-28 | [7 empty] | 0 |  | 0 |  |  | 2023-04-27 | Online
NSTAR | Canton | 2346246 | 2021 | 100 | PV | TBD | 2019-06-06 | 2019-06-10 | 2 |  | 2 | 2019-06-24 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Roxbury | 2346323 | 2119 | 37.8 | PV | TBD | 2019-06-06 | 2019-06-10 | 2 |  | 2 | 2019-06-24 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2021-01-26 | Online
NSTAR | Watertown | 2346407 | 2472 | 133.2 | PV | TBD | 2019-06-06 | 2019-06-10 | 2 |  | 2 | 2019-06-25 |  | -31139 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  | 2020-11-12 | Online
NSTAR | Westport | 2346438 | 2790 | 20 | PV | TBD | 2019-05-29 | 2019-06-10 | 8 |  | 8 | 2019-06-25 |  | -31139 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-09 | [7 empty] | 0 |  | 0 |  |  | 2019-11-04 | Online
NSTAR | Boston | 2346459 | 2125 | 133.2 | PV | 321-02 | 2019-06-07 | 2019-06-11 | 2 |  | 2 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-05 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Wareham | 2346531 | 2576 | 4980 | PV | TBD | 2019-06-24 | 2019-06-26 | 2 | 0 | 2 | 2019-06-27 |  | -31141 | 371 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-02-03 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2019-07-09
NSTAR | Boston | 2346677 | 2163 | 43.2 | PV | TBD | 2019-05-31 | 2019-06-12 | 8 |  | 8 | 2019-06-26 |  | -31140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-11 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Hopkinton | 2346774 | 1748 | 480 | PV | TBD | 2019-05-23 | 2019-06-13 | 15 |  | 15 | 2019-06-26 |  | -31140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0
NSTAR | Roxbury | 2346835 | 2120 | 57.6 | PV | TBD | 2019-06-10 | 2019-06-13 | 3 |  | 3 | 2019-06-26 |  | -31140 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Sharon | 2346951 | 2067 | 50 | PV | 470-H3 | 2019-05-07 | 2019-06-14 | 28 |  | 28 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2023-03-21 | Online
NSTAR | Duxbury | 2346979 | 2332 | 200 | PV | 3-27-970 | 2019-06-19 | 2019-06-19 | 0 |  | 0 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-23 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | Needham | 2347063 | 2492 | 57.6 | PV | 148-H4 | 2019-06-13 | 2019-06-17 | 2 |  | 2 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-15 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Boston | 2347214 | 2115 | 57.6 | PV | TBD | 2019-06-12 | 2019-06-14 | 2 |  | 2 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lincoln | 2347229 | 1773 | 17.4 | PV | 320-H6 | 2019-05-31 | 2019-06-14 | 10 |  | 10 | 2019-06-27 |  | -31141 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-02 | [7 empty] | 0 |  | 0 |  |  | 2020-03-31 | Online
NSTAR | Acton | 2347245 | 1720 | 60 | PV | 416-H8 | 2019-06-06 | 2019-06-17 | 7 |  | 7 | 2019-06-28 |  | -31142 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-10 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Assonett | 2347725 | 2702 | 3000 | PV & Battery | TBD | 2019-06-17 | 2019-06-20 | 3 |  | 3 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Brewster | 2347755 | 2631 | 1490 | PV & Battery | TBD | 2019-05-31 | 2019-06-21 | 15 |  | 15 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22
NSTAR | Walpole | 2348516 | 2081 | 17.5 | PV | TBD | 2019-06-17 | 2019-06-21 | 4 |  | 4 | 2019-07-08 |  | -31148 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-07 | [7 empty] | 0 |  | 0 |  |  | 2019-12-27 | Online
NSTAR | Brewster | 2348521 | 2631 | 480 | PV | TBD | 2019-05-30 | 2019-06-21 | 16 |  | 16 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-05 | [7 empty] | 0 |  | 0 |  |  | 2021-08-12 | Online
NSTAR | South Yarmouth | 2348526 | 2664 | 1560 | PV & Battery | 4-92A-563 | 2019-05-30 | 2019-06-26 | 19 |  | 19 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 2348529 | 2645 | 166.5 | PV | 4-95A-95A | 2019-05-31 | 2019-06-26 | 18 |  | 18 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-09 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | Newton | 2348530 | 2465 | 20 | PV & Battery | 282-H9 | 2019-05-31 | 2019-06-20 | 14 |  | 14 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-18 | [7 empty] | 0 |  | 0 |  |  | 2020-01-22 | Online
NSTAR | Ashland | 2348725 | 1721 | 129.6 | PV | TBD | 2019-06-17 | 2019-06-24 | 5 |  | 5 | 2019-07-10 |  | -31150 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-12 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | Ashland | 2348729 | 1721 | 144 | PV | TBD | 2019-06-17 | 2019-06-24 | 5 |  | 5 | 2019-07-10 |  | -31150 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2021-05-04 | Online
NSTAR | Woburn | 2349171 | 1801 | 333 | PV | TBD | 2019-06-21 | 2019-06-24 | 1 |  | 1 | 2019-07-15 |  | -31153 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-05 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2349180 | 2461 | 133.2 | PV | TBD | 2019-06-17 | 2019-06-25 | 6 |  | 6 | 2019-07-10 |  | -31150 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-04 | [7 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Ashland | 2349389 | 1721 | 129.6 | PV | TBD | 2019-06-17 | 2019-06-24 | 5 |  | 5 | 2019-07-11 |  | -31151 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | East Freetown | 2349398 | 2717 | 1750 | PV | TBD | 2019-05-09 | 2019-06-24 | 32 |  | 32 | 2019-07-11 |  | -31151 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2349404 | 1890 | 108 | PV | 211-H4 | 2019-06-21 | 2019-06-26 | 3 |  | 3 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Fairhaven | 2349408 | 2719 | 2000 | PV & Battery | TBD | 2019-05-28 | 2019-06-26 | 21 |  | 21 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2349571 | 2717 | 1000 | PV | TBD | 2019-06-21 | 2019-06-26 | 3 |  | 3 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Sandwich | 2349576 | 2537 | 849.5 | PV & Battery | 4-87A-471 | 2019-05-31 | 2019-06-26 | 18 |  | 18 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Sandwich | 2349579 | 2537 | 3510 | PV & Battery | 4-87A-471 | 2019-05-30 | 2019-06-26 | 19 |  | 19 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2349583 | 2644 | 849.5 | PV & Battery | 4-81B-443 | 2019-05-30 | 2019-06-26 | 19 |  | 19 | 2019-07-12 |  | -31152 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | 2349777 | 1701 | 57.6 | PV | TBD | 2019-06-27 | 2019-06-27 | 0 |  | 0 | 2019-07-15 |  | -31153 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-07-17 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Roxbury | 2349780 | 2119 | 37.8 | PV | tbd | 2019-06-27 | 2019-06-27 | 0 |  | 0 | 2019-07-15 |  | -31153 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Wareham | 2349786 | 2571 | 5500 | PV & Battery | TBD | 2019-06-21 | 2019-06-28 | 5 |  | 5 | 2019-07-15 |  | -31153 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Tisbury | 2349997 | 2573 | 19.17 | PV | TBD | 2019-06-26 | 2019-06-28 | 2 |  | 2 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-07 | [7 empty] | 0 |  | 0 |  |  | 2019-12-06
NSTAR | Framingham | 2350003 | 1701 | 72 | PV | 433-H8 | 2019-06-24 | 2019-07-08 | 10 |  | 10 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-13 | [7 empty] | 0 |  | 0
NSTAR | Lincoln | 2350004 | 1773 | 107.84 | PV & Battery | 320-H8 | 2019-02-11 | 2019-07-10 | 107 |  | 107 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-27 | [7 empty] | 0 |  | 0
NSTAR | Lincoln | 2350022 | 1773 | 17.6 | PV | 320-H6 | 2019-05-31 | 2019-07-03 | 23 |  | 23 | 2019-07-16 |  | -31154 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 2350124 | 1720 | 999 | PV | TBD | 2019-07-02 | 2019-07-09 | 5 |  | 5 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2350166 | 2770 | 1000 | PV & Battery | 3-702-702 | 2019-07-03 | 2019-07-10 | 5 |  | 5 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Roxbury | 2350185 | 2119 | 25 | PV | 106-1N31H4 | 2019-06-27 | 2019-06-27 | 0 |  | 0 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-05 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Natick | 2350187 | 1760 | 466.6 | PV | TBD | 2019-07-01 | 2019-07-01 | 0 |  | 0 | 2019-07-22 |  | -31158 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-05 | [7 empty] | 0 |  | 0
NSTAR | West Tisbury | 2350188 | 2568 | 20 | PV | TBD | 2019-05-23 | 2019-07-02 | 28 |  | 28 | 2019-07-17 |  | -31155 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-27 | [7 empty] | 0 |  | 0 |  |  | 2020-03-11 | Online
NSTAR | Hyannis | 2350400 | 2601 | 112.5 | PV | TBD | 2019-06-25 | 2019-07-11 | 12 |  | 12 | 2019-07-18 |  | -31156 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-06 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Plymouth | 2350447 | 2360 | 250 | CHP | 3-73-927 | 2019-06-27 | 2019-07-02 | 3 |  | 3 | 2019-07-22 |  | -31158 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2350448 | 2452 | 133.2 | PV | TBD | 2019-07-09 | 2019-07-12 | 3 |  | 3 | 2019-07-19 |  | -31157 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2020-08-24 | Online
NSTAR | Bass River | 2350641 | 2664 | 180 | PV | TBD | 2019-07-18 |  | -31156 | 0 | 0 | 2019-07-23 | 2019-08-17 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2019-09-05 |  | 2020-02-27 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Yarmouth | 2350705 | 2664 | 187.5 | PV |  | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 2019-07-23 | 2019-09-06 | 33 | 22 | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | 2019-10-10 | 2020-02-28 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Provincetown | 2350711 | 2657 | 53.76 | PV | TBD | 2019-06-26 | 2019-07-12 | 12 |  | 12 | 2019-07-19 |  | -31157 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Dennis | 2350752 | 2368 | 333 | PV | TBD | 2019-06-24 | 2019-07-01 | 5 |  | 5 | 2019-07-19 |  | -31157 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-29 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | West Newton | 2350781 | 2465 | 100 | PV | 467-H5 | 2019-07-01 | 2019-07-01 | 0 |  | 0 | 2019-07-19 |  | -31157 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23
NSTAR | Plymouth | 2350809 | 2360 | 49.59 | PV | 3-10-10 | 2019-07-01 | 2019-07-01 | 0 |  | 0 | 2019-07-22 |  | -31158 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-03 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 2351221 | 1803 | 999 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-07-25 |  | -31161 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-23 | [7 empty] | 0 |  | 0 |  |  | 2021-08-25 | Online
NSTAR | New Bedford | 2351223 | 2745 | 499.5 | PV | TBD | 2019-07-01 | 2019-07-08 | 5 |  | 5 | 2019-07-23 |  | -31159 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-19 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Lexington | 2351263 | 2421 | 110 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-07-25 |  | -31161 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2351363 | 2420 | 491 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-07-25 |  | -31161 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 2351364 | 1746 | 4999 | PV & Battery | TBD | 2019-07-05 | 2019-07-10 | 3 |  | 3 | 2019-07-23 |  | -31159 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-14 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 2351423 | 2026 | 22.8 | PV | 20-H7 | 2019-07-08 | 2019-07-10 | 2 |  | 2 | 2019-07-24 |  | -31160 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-09 | [7 empty] | 0 |  | 0 |  |  | 2020-02-27 | Online
NSTAR | New Bedford | 2351619 | 2740 | 236 | PV | TBD | 2019-07-10 | 2019-07-11 | 1 |  | 1 | 2019-07-26 |  | -31162 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2020-07-30 | Online
NSTAR | Boston | 2351637 | 2115 | 43.2 | PV | TBD | 2019-06-27 | 2019-07-11 | 10 |  | 10 | 2019-07-26 |  | -31162 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2351638 | 2745 | 466.6 | PV | TBD | 2019-07-08 | 2019-07-11 | 3 |  | 3 | 2019-07-26 |  | -31162 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Dartmouth | 2351639 | 2747 | 150 | PV | TBD | 2019-07-12 | 2019-07-12 | 0 |  | 0 | 2019-07-26 |  | -31162 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2020-10-16 | Online
NSTAR | Medfield | 2351919 | 2052 | 1280 | PV & Battery | TBD | 2019-07-11 | 2019-07-16 | 3 |  | 3 | 2019-07-29 |  | -31163 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-10 | [7 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2351939 | 2664 | 92.16 | PV | TBD | 2019-07-12 | 2019-07-15 | 1 |  | 1 | 2019-07-29 |  | -31163 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-27 | [7 empty] | 0 |  | 0 |  |  | 2020-10-16 | Online
NSTAR | Sandwich | 2351960 | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 | 46 |  | 46 | 2019-07-29 |  | -31163 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2351984 | 2330 | 4999 | PV & Battery | TBD | 2019-07-11 | 2019-07-15 | 2 |  | 2 | 2019-07-29 |  | -31163 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2352055 | 2420 | 220 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-07-29 |  | -31163 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Lexington | 2352056 | 2421 | 220 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-07-30 |  | -31164 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Provincetown | 2352065 | 2657 | 325 | PV | TBD | 2019-07-12 |  | -31152 |  | 0 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-29 | [7 empty] | 0 |  | 0 |  |  | 2021-01-19 | Online
NSTAR | Lexington | 2352139 | 2421 | 180 | PV | TBD | 2019-07-10 | 2019-07-17 | 5 |  | 5 | 2019-07-30 |  | -31164 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-28 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 2352175 | 2743 | 84 | PV | TBD | 2019-07-18 | 2019-07-18 | 0 |  | 0 | 2019-07-30 |  | -31164 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-21 | [7 empty] | 0 |  | 0
NSTAR | Cambridge | 2352275 | 2139 | 694 | PV & Battery | 831-1118 | 2019-06-19 | 2019-07-19 | 22 |  | 22 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2352285 | 2421 | 905 | PV & Battery | TBD | 2019-07-11 | 2019-07-15 | 2 |  | 2 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-09 | [7 empty] | 0 |  | 0 |  |  | 2023-02-02 | Online
NSTAR | Medfield | 2352302 | 2052 | 766.6 | PV & Battery | TBD | 2019-07-11 | 2019-07-16 | 3 |  | 3 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-10 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2352308 | 2053 | 250 | PV | TBD | 2019-06-26 | 2019-07-16 | 14 |  | 14 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-05 | [7 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | Cambridge | 2352522 | 2139 | 460 | PV & Battery | 831-1304 | 2019-06-19 | 2019-07-19 | 22 |  | 22 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2352540 | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 | 46 |  | 46 | 2019-07-31 |  | -31165 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2352572 | 2421 | 247 | PV & Battery | TBD | 2019-07-11 | 2019-07-17 | 4 |  | 4 | 2019-08-01 |  | -31166 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Dorchester | 2352639 | 2124 | 199.8 | PV | TBD | 2019-07-01 | 2019-07-17 | 12 |  | 12 | 2019-08-01 |  | -31166 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Sandwich | 2352680 | 2644 | 496 | PV & Battery | TBD | 2019-05-14 | 2019-07-17 | 46 |  | 46 | 2019-08-01 |  | -31166 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2352731 | 2747 | 516 | PV | TBD | 2019-06-24 | 2019-07-19 | 19 |  | 19 | 2019-08-02 |  | -31167 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2352774 | 1801 | 100 | PV | 211-H6 | 2019-07-18 | 2019-07-19 | 1 |  | 1 | 2019-08-02 |  | -31167 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Stoneham | 2352776 | 2180 | 166.6 | PV | TBD | 2019-06-21 | 2019-07-17 | 18 |  | 18 | 2019-08-02 |  | -31167 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-08 | Online
NSTAR | Lexington | 2352782 | 2421 | 330 | PV | TBD | 2019-08-01 |  | -31166 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-03-12 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Lexington | 2352860 | 2421 | 297 | PV | TBD | 2019-07-10 | 2019-07-15 | 3 |  | 3 | 2019-08-02 |  | -31167 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online
NSTAR | Medfield | 2352954 | 2052 | 150 | PV | TBD | 2019-07-18 | 2019-07-22 | 2 |  | 2 | 2019-08-05 |  | -31168 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  | 2022-09-13 | Online
NSTAR | Carver | 2352975 | 2330 | 1250 | PV & Battery | TBD | 2019-07-12 | 2019-07-19 | 5 |  | 5 | 2019-08-05 |  | -31168 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2353430 | 2571 | 5000 | PV & Battery | tbd | 2019-06-04 | 2019-07-23 | 35 |  | 35 | 2019-08-05 |  | -31168 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2353437 | 1760 | 496 | PV | 240-H1 | 2017-06-28 | 2017-06-28 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-04-03 | [7 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Roxbury | 2353454 | 2120 | 66.6 | PV | TBD | 2019-07-24 | 2019-07-24 | 0 |  | 0 | 2019-08-06 |  | -31169 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-16 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Milton | 2353541 | 2186 | 25.2 | PV | 496-H7 | 2019-06-05 | 2019-07-26 | 37 |  | 37 | 2019-08-06 |  | -31169 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-22 | [7 empty] | 0 |  | 0 |  |  | 2022-03-07 | Online
NSTAR | Mattapoisett | 2353656 | 2739 | 4999 | PV & Battery | TBD | 2019-07-16 | 2019-07-19 | 3 |  | 3 | 2019-08-07 |  | -31170 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2353669 | 2139 | 133.2 | PV | TBD | 2019-06-19 | 2019-07-19 | 22 |  | 22 | 2019-08-06 |  | -31169 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-25 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2353792 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | 2353830 | 1803 | 43.2 | PV | TBD | 2019-07-16 | 2019-07-19 | 3 |  | 3 | 2019-08-08 |  | -31171 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | South Yarmouth | 2353833 | 2664 | 756 | PV | TBD | 2019-06-24 | 2019-07-19 | 19 |  | 19 | 2019-08-08 |  | -31171 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2353838 | 2717 | 500 | PV & Battery | TBD | 2019-05-29 | 2019-07-22 | 38 |  | 38 | 2019-08-08 |  | -31171 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2354057 | 2120 | 43.2 | PV | TBD | 2019-07-09 | 2019-07-24 | 11 |  | 11 | 2019-08-09 |  | -31172 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-26 | [7 empty] | 0 |  | 0 |  |  | 2020-03-30
NSTAR | Sandwich | 2354118 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2354162 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2354172 | 2563 | 3250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-12 |  | -31173 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Roxbury | 2354364 | 2120 | 22.8 | PV | 52-1499H2 | 2019-07-24 | 2019-07-24 | 0 |  | 0 | 2019-08-12 |  | -31173 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-16 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | East Wareham | 2354403 | 2538 | 15.2 | PV | 3-84-960 | 2019-04-19 | 2019-07-25 | 69 |  | 69 | 2019-08-13 |  | -31174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-19 | [7 empty] | 0 |  | 0 |  |  | 2020-08-26 | Online
NSTAR | Freetown | 2354457 | 2717 | 5000 | PV & Battery | TBD | 2019-06-03 | 2019-07-30 | 41 |  | 41 | 2019-08-13 |  | -31174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 2354467 | 2645 | 3750 | PV | TBD | 2019-07-24 | 2019-08-01 | 6 |  | 6 | 2019-08-14 |  | -31175 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Sandwich | 2354511 | 2537 | 900 | PV | TBD | 2019-06-24 | 2019-07-19 | 19 |  | 19 | 2019-08-13 |  | -31174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chatham | 2354558 | 2659 | 1560 | PV | TBD | 2019-06-24 |  | -31138 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 2354628 | 2139 | 594.6 | PV & Battery | 831-1301 | 2019-06-18 | 2019-07-19 | 23 |  | 23 | 2019-08-14 |  | -31175 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 2354633 | 1801 | 100 | PV | 375-H14 | 2019-07-18 | 2019-07-19 | 1 |  | 1 | 2019-08-14 |  | -31175 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-04 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Chatham | 2354636 | 2650 | 24.64 | PV | TBD | 2019-07-16 | 2019-07-22 | 4 |  | 4 | 2019-08-14 |  | -31175 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  | 2020-02-06 | Online
NSTAR | Boston | 2354844 | 2120 | 43.2 | PV | TBD | 2019-07-10 | 2019-07-24 | 10 |  | 10 | 2019-08-15 |  | -31176 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-08-29 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 2354849 | 2747 | 5000 | PV & Battery | TBD | 2019-05-09 | 2019-07-26 | 56 |  | 56 | 2019-08-15 |  | -31176 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2355009 | 2571 | 500 | PV & Battery | 3-84-968 | 2019-07-18 | 2019-07-29 | 7 |  | 7 | 2019-08-16 |  | -31177 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-15 | [7 empty] | 0 |  | 0
NSTAR | Chatham | 2355012 | 2659 | 2500 | PV & Battery | TBD | 2019-07-25 | 2019-07-25 | 0 |  | 0 | 2019-08-16 |  | -31177 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-29 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2355014 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2355015 | 2563 | 250 | PV & Battery | TBD | 2019-07-29 | 2019-07-29 | 0 |  | 0 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2355016 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2355017 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 2355098 | 2163 | 166.6 | PV | TBD | 2019-07-19 | 2019-08-05 | 11 |  | 11 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-21 | [7 empty] | 0 |  | 0 |  |  | 2021-05-24 | Online
NSTAR | Sandwich | 2355143 | 2563 | 250 | PV & Battery | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2355146 | 2743 | 4995 | PV & Battery | TBD | 2019-07-24 | 2019-08-01 | 6 |  | 6 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Yarmouth | 2355147 | 2664 | 264 | PV | TBD | 2019-07-22 | 2019-08-02 | 9 |  | 9 | 2019-08-19 |  | -31178 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-11 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Boston | 2355397 | 2127 | 275 | PV & Battery | 293-09 | 2019-07-12 | 2019-08-05 | 16 |  | 16 | 2019-08-20 |  | -31179 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-24 | [7 empty] | 0 |  | 0 |  |  | 2020-12-14 | Online
NSTAR | Dorchester | 2355449 | 2125 | 366.3 | PV | TBD | 2019-08-19 |  | -31178 | 0 | 0 | 2019-08-22 | 2019-11-01 | 51 | 40 | 11 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-03-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Boston | 2355531 | 2163 | 66.6 | PV | TBD | 2019-07-29 | 2019-08-05 | 5 |  | 5 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2021-03-23 | Online
NSTAR | Bourne | 2355532 | 2532 | 499 | PV | TBD | 2019-07-29 | 2019-08-06 | 6 |  | 6 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2355569 | 2601 | 62.5 | PV | TBD | 2019-08-01 | 2019-08-07 | 4 |  | 4 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-29 | Online
NSTAR | Falmouth | 2355581 | 2540 | 46.08 | PV | TBD | 2019-08-01 | 2019-08-07 | 4 |  | 4 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-02-24 | Online
NSTAR | Boston | 2355610 | 2115 | 100 | PV | 493-1411H | 2019-08-07 | 2019-08-08 | 1 |  | 1 | 2019-08-21 |  | -31180 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-29 | Online
NSTAR | Bellingham | 2355844 | 2019 | 250 | PV | TBD | 2019-07-15 | 2019-08-06 | 16 |  | 16 | 2019-08-22 |  | -31181 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-19 | [7 empty] | 0 |  | 0
NSTAR | Acton | 2355854 | 1720 | 750 | PV | tbd | 2019-07-30 | 2019-08-05 | 4 |  | 4 | 2019-08-23 |  | -31182 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-12 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Fairhaven | 2355860 | 2719 | 100 | PV | TBD | 2019-08-05 | 2019-08-05 | 0 |  | 0 | 2019-08-23 |  | -31182 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-11 | [7 empty] | 0 |  | 0 |  |  | 2021-03-12 | Online
NSTAR | Burlington | 2355861 | 1821 | 1000 | PV & Battery | TBD | 2019-07-30 | 2019-08-01 | 2 |  | 2 | 2019-08-22 |  | -31181 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2355862 | 2420 | 22.8 | PV | TBD | 2019-07-25 | 2019-08-06 | 8 |  | 8 | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Sudbury | 2355864 | 1776 | 15.2 | PV | TBD | 2019-07-31 | 2019-08-06 | 4 |  | 4 | 2019-08-22 |  | -31181 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-12 | [7 empty] | 0 |  | 0 |  |  | 2019-12-13 | Online
NSTAR | Boston | 2355992 | 2119 | 43.2 | PV | TBD | 2019-07-10 | 2019-08-09 | 22 |  | 22 | 2019-08-26 |  | -31183 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-25 | [7 empty] | 0 |  | 0 |  |  | 2020-05-13 | Online
NSTAR | South Yarmouth | 2356024 | 2664 | 100 | PV | TBD | 2019-08-07 | 2019-08-07 | 0 |  | 0 | 2019-08-23 |  | -31182 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-03-10 | Online
NSTAR | Buzzards Bay | 2356276 | 2532 | 4975 | PV & Battery | TBD | 2019-08-05 | 2019-08-09 | 4 |  | 4 | 2019-08-26 |  | -31183 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2356386 | 2601 | 62.5 | PV | TBD | 2019-08-01 | 2019-08-07 | 4 |  | 4 | 2019-08-27 |  | -31184 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-29 | Online
NSTAR | Medway | 2356387 | 2053 | 500 | PV | TBD | 2019-08-08 | 2019-08-15 | 5 |  | 5 | 2019-08-28 |  | -31185 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-24 | [7 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Burlington | 2356435 | 1803 | 130 | PV | 391-H2 | 2019-08-01 | 2019-08-07 | 4 |  | 4 | 2019-08-27 |  | -31184 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Stoneham | 2356835 | 1757 | 86.4 | PV | TBD | 2019-08-14 | 2019-08-19 | 3 |  | 3 | 2019-08-29 |  | -31186 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-04 | [7 empty] | 0 |  | 0 |  |  | 2020-04-21 | Online
NSTAR | Stoneham | 2357040 | 2180 | 72 | PV | TBD | 2019-08-14 | 2019-08-16 | 2 |  | 2 | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  | 2020-04-02 | Online
NSTAR | Hopkinton | 2357587 | 1748 | 2770 | PV & Battery | 126-H2 | 2019-08-15 | 2020-08-16 | 261 |  | 261 | 2020-09-06 |  | -31452 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-24 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2357591 | 2180 | 72 | PV | TBD | 2019-08-14 | 2019-08-19 | 3 |  | 3 | 2019-09-04 |  | -31190 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-08 | [7 empty] | 0 |  | 0 |  |  | 2020-09-16 | Online
NSTAR | Norfolk | 2357740 | 2056 | 100.8 | PV | TBD | 2019-08-20 | 2019-08-20 | 0 |  | 0 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-16 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2357988 | 2360 | 150 | PV | 3-12-12 | 2019-08-13 | 2019-08-13 | 0 |  | 0 | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-20 | [7 empty] | 0 |  | 0 |  |  | 2020-05-18 | Online
NSTAR | Provincetown | 2357992 | 2657 | 30.39 | PV | 4-96-974 | 2019-08-06 | 2019-08-08 | 2 |  | 2 | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0
NSTAR | South Dennis | 2357995 | 2638 | 100 | PV | TBD | 2019-08-01 | 2019-08-09 | 6 |  | 6 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-08 | [7 empty] | 0 |  | 0 |  |  | 2020-09-09
NSTAR | Wareham | 2358028 | 2571 | 300 | PV | 3-86-966 | 2019-08-20 | 2019-08-22 | 2 |  | 2 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-25 | [7 empty] | 0 |  | 0 |  |  | 2020-11-18 | Online
NSTAR | Sherborn | 2358191 | 1770 | 17.6 | PV & Battery | TBD | 2019-08-07 | 2019-08-13 | 4 |  | 4 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-24 | [7 empty] | 0 |  | 0 |  |  | 2020-02-25 | Online
NSTAR | Boston | 2358194 | 2121 | 20 | PV | TBD | 2019-07-10 | 2019-08-09 | 22 |  | 22 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-05 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | Acusnet | 2358231 | 2743 | 22 | PV | 2-231-231 | 2019-08-22 | 2019-08-26 | 2 |  | 2 | 2019-09-06 |  | -31192 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-21 | [7 empty] | 0 |  | 0 |  |  | 2021-10-14 | Online
NSTAR | Hopkinton | 2358327 | 1748 | 2770 | PV | TBD | 2019-09-06 |  | -31192 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-04-16 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Framingham | 2358332 | 1749 | 216 | PV | TBD | 2019-08-19 | 2019-08-21 | 2 |  | 2 | 2019-09-09 |  | -31193 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Dorchester | 2358592 | 2124 | 45.4 | PV | 511-1498H1 | 2019-08-26 | 2019-08-26 | 0 |  | 0 | 2019-09-11 |  | -31195 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Osterville | 2358595 | 2655 | 240 | PV | 4-88-491 | 2019-08-14 | 2019-08-27 | 9 |  | 9 | 2019-09-11 |  | -31195 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Provincetown | 2358697 | 2657 | - |  | TBD | 2019-09-10 |  | -31194 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-04-20 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2358992 | 2571 | 16.59 | PV | 3-83-83 | 2018-04-25 | 2018-06-13 | 35 |  | 35 | 2018-06-28 |  | -30881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-07-24 | 2018-08-14 | [6 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Orleans | 2358998 | 2653 | 86 | PV | 4-83-951 | 2019-08-20 | 2019-08-27 | 5 |  | 5 | 2019-09-13 |  | -31197 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-31 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2359000 | 2143 | 2400 | CHP | 30-179XYH | 2019-08-06 | 2019-08-29 | 17 |  | 17 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2020-09-30 | Online
NSTAR | Somerville | 2359001 | 2143 | 600 | CHP | 30-179XYH | 2019-08-06 | 2019-08-29 | 17 |  | 17 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Wareham | 2359588 | 2571 | 5000 | PV |  | 2019-09-16 | 2019-09-18 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-04-24 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Harwich | 2359695 | 2645 | 5000 | PV & Battery | TBD | 2019-08-26 | 2019-08-29 | 3 |  | 3 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | 2359696 | 2364 | 250 | PV | TBD | 2019-08-23 | 2019-09-03 | 7 |  | 7 | 2019-09-17 |  | -31199 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-09 | [7 empty] | 0 |  | 0 |  |  | 2020-02-28 | Online
NSTAR | Framingham | 2359697 | 1701 | 43.2 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-17 |  | -31199 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2359768 | 2601 | 17.6 | PV | 4-80B-514 | 2019-05-06 | 2019-09-03 | 86 |  | 86 | 2019-09-17 |  | -31199 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acton | 2359934 | 1720 | 100 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-27 | [7 empty] | 0 |  | 0
NSTAR | Assonett | 2359951 | 2702 | 250 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-18 |  | -31200 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-16 | [7 empty] | 0 |  | 0
NSTAR | East Sandwich | 2360131 | 2537 | 4600 | PV | TBD | 2019-08-28 | 2019-09-04 | 5 |  | 5 | 2019-10-01 |  | -31209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | 2360135 | 2143 | 1200 | CHP | TBD | 2019-08-06 | 2019-08-29 | 17 |  | 17 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | North Dartmouth | 2360141 | 2747 | 200 | PV | TBD | 2019-09-03 | 2019-09-03 | 0 |  | 0 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-16 | [7 empty] | 0 |  | 0 |  |  | 2021-05-12 | Online
NSTAR | Woburn | 2360146 | 1801 | 240 | PV | TBD | 2019-08-29 | 2019-09-04 | 4 |  | 4 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-10-29 | Online
NSTAR | Cambridge | 2360150 | 2141 | 125 | CHP | TBD | 2019-08-05 | 2019-09-05 | 23 |  | 23 | 2019-09-19 |  | -31201 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2360179 | 2381 | 19 | PV | TBD | 2019-07-25 | 2019-09-05 | 30 |  | 30 | 2019-09-20 |  | -31202 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Edgartown | 2360354 | 2539 | 286 | PV & Battery | TBD | 2019-08-16 | 2019-09-05 | 14 |  | 14 | 2019-09-23 |  | -31203 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Falmouth | 2360385 | 2536 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 | 2 |  | 2 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Marston Mills | 2360391 | 2635 | 210 | Fuel Cell | 4-88-485 | 2019-09-05 | 2019-09-06 | 1 |  | 1 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-16 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | East Wareham | 2360402 | 2538 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 | 2 |  | 2 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-14 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Hyannis | 2360467 | 2601 | 262.5 | Fuel Cell | 4-84A-520 | 2019-09-04 | 2019-09-06 | 2 |  | 2 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-17 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Sandwich | 2360491 | 2563 | 262.5 | Fuel Cell | TBD | 2019-09-04 | 2019-09-06 | 2 |  | 2 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-14 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Mashpee | 2360533 | 2649 | 210 | Fuel Cell | TBD | 2019-09-05 | 2019-09-06 | 1 |  | 1 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Harwich | 2360563 | 2645 | 262.5 | Fuel Cell | TBD | 2019-09-05 | 2019-09-06 | 1 |  | 1 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2020-06-25 | Online
NSTAR | Freetown | 2360807 | 2717 | 1125 | PV & Battery | TBD | 2019-09-05 | 2019-09-09 | 2 |  | 2 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medway | 2360809 | 2053 | 500 | PV | 65-H2 | 2019-08-22 | 2019-09-09 | 12 |  | 12 | 2019-09-25 |  | -31205 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-31 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2361120 | 2571 | - |  | TBD | 2019-09-25 |  | -31205 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-05 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Carver | 2361242 | 2330 | 4999 | PV & Battery | TBD | 2019-09-04 | 2019-09-11 | 5 |  | 5 | 2019-09-27 |  | -31207 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2361243 | 2330 | 2000 | PV & Battery | TBD | 2019-09-05 | 2019-09-13 | 6 |  | 6 | 2019-10-01 |  | -31209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2361417 | 2601 | 24.78 | PV | 4-63-63 | 2019-09-05 | 2019-09-09 | 2 |  | 2 | 2019-09-27 |  | -31207 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-18 | [7 empty] | 0 |  | 0 |  |  | 2020-05-19 | Online
NSTAR | Carver | 2361424 | 2330 | 2000 | PV & Battery | TBD | 2019-09-05 | 2019-09-09 | 2 |  | 2 | 2019-09-27 |  | -31207 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2361428 | 2330 | 2000 | PV & Battery | TBD | 2019-09-06 | 2019-09-13 | 5 |  | 5 | 2019-10-01 |  | -31209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Freetown | 2361432 | 2717 | 4000 | PV |  | 2019-09-26 | 2019-10-02 | 4 | 0 | 4 | 2019-10-07 |  | -31213 | 298 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-05-06 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2019-10-22
NSTAR | Hopkinton | 2361481 | 1748 | 333.3 | PV | TBD | 2019-09-03 | 2019-09-12 | 7 |  | 7 | 2019-10-01 |  | -31209 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2361879 | 1890 | 25.2 | PV & Battery | 211-H3 | 2019-09-03 | 2019-09-17 | 10 |  | 10 | 2019-10-02 |  | -31210 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-14 | [7 empty] | 0 |  | 0 |  |  | 2020-04-29 | Online
NSTAR | Carver | 2361931 | 2330 | - |  | TBD | 2019-10-01 |  | -31209 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-11 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Carver | 2361932 | 2330 | 2000 | PV & Battery | TBD | 2019-10-01 |  | -31209 | 0 | 0 | 2019-10-10 | 2019-10-24 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-11 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Lexington | 2361940 | 2421 | 250 | PV | TBD | 2019-09-03 | 2019-09-09 | 4 |  | 4 | 2019-10-02 |  | -31210 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-18 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Foxboro | 2362818 | 2035 | 3900 | PV | TBD | 2019-09-18 | 2019-09-23 | 3 |  | 3 | 2019-10-08 |  | -31214 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2363245 | 2746 | 83.3 | PV | TBD | 2019-09-23 | 2019-09-25 | 2 |  | 2 | 2019-10-22 |  | -31224 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2363249 | 2746 | 83.3 | PV | TBD | 2019-09-23 | 2019-09-25 | 2 |  | 2 | 2019-10-22 |  | -31224 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2363427 | 2770 | 3500 | PV & Battery | TBD | 2019-09-19 | 2019-09-24 | 3 |  | 3 | 2019-10-09 |  | -31215 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 2363669 | 2645 | 210 | PV | 4-95A-597 | 2019-09-13 | 2019-09-19 | 4 |  | 4 | 2019-10-09 |  | -31215 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  | 2021-07-21 | Online
NSTAR | New Bedford | 2363671 | 2746 | 200 | PV | TBD | 2019-09-23 | 2019-09-25 | 2 |  | 2 | 2019-10-22 |  | -31224 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0
NSTAR | Dover | 2363676 | 2030 | 17.6 | PV & Battery | TBD | 2019-09-20 | 2019-09-26 | 4 |  | 4 | 2019-10-10 |  | -31216 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-28 | [7 empty] | 0 |  | 0 |  |  | 2019-01-08 | Online
NSTAR | Brewster | 2363697 | 2631 | 2500 | PV | TBD | 2019-09-06 | 2019-09-25 | 13 |  | 13 | 2019-10-10 |  | -31216 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2363855 | 2601 | 112.1 | PV | TBD | 2019-09-05 | 2019-09-09 | 2 |  | 2 | 2019-10-15 |  | -31219 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-08-19 | Online
NSTAR | Natick | 2363856 | 1760 | 66 | PV & Battery | 433-H9 | 2019-08-22 | 2019-09-30 | 27 |  | 27 | 2019-10-15 |  | -31219 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-27 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | Holliston | 2364171 | 1746 | - |  | TBD | 2019-10-15 |  | -31219 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-05-22 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Holliston | 2364172 | 1746 | 240 | PV | TBD | 2019-09-09 | 2019-09-26 | 13 |  | 13 | 2019-10-16 |  | -31220 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Newton | 2364472 | 2459 | 15.2 | PV | TBD | 2019-09-27 | 2019-10-03 | 4 |  | 4 | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  | 2020-04-07 | Online
NSTAR | Dedham | 2364473 | 2026 | 125 | PV & Battery | 20-H8 | 2019-07-30 | 2019-10-03 | 47 |  | 47 | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Acusnet | 2364982 | 2743 | 500 | PV & Battery |  | 2019-10-21 | 2019-10-22 | 1 | 0 | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-25 |  | -31227 | 86 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 |  | 2020-12-31 | TBD |  | 60 |  |  | 0 |  | 0 |  |  | 2022-02-09 | Online | Private
NSTAR | Weston | 2365270 | 2493 | 57.6 | PV | 282-H1 | 2019-10-01 | 2019-10-03 | 2 |  | 2 | 2019-10-24 |  | -31226 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2019-12-11 | [6 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Framingham | 2365418 | 1701 | 199.8 | PV | TBD | 2019-09-27 | 2019-10-09 | 8 |  | 8 | 2019-10-24 |  | -31226 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2365634 | 2360 | 17.6 | PV | TBD | 2019-04-18 | 2019-10-10 | 125 |  | 125 | 2019-10-28 |  | -31228 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-05 | [7 empty] | 0 |  | 0 |  |  | 2020-02-28 | Online
NSTAR | Lincoln | 2365635 | 1773 | 1831.4 | PV & Battery | 320-H8 | 2019-09-13 | 2019-10-28 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0
NSTAR | North Harwich | 2365636 | 2645 | 23.2 | PV | 4-92B-92B | 2019-10-07 | 2019-10-10 | 3 |  | 3 | 2019-10-28 |  | -31228 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-05 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Wareham | 2366043 | 2571 | 499 | Fuel Cell | TBD | 2019-10-15 | 2019-10-15 | 0 |  | 0 | 2019-10-29 |  | -31229 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2366044 | 1760 | 43.2 | PV | TBD | 2019-10-11 | 2019-10-15 | 2 |  | 2 | 2019-10-29 |  | -31229 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2366164 | 2114 | 66 | PV | TBD | 2019-08-23 | 2019-10-10 | 34 |  | 34 | 2019-10-29 |  | -31229 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2366298 | 2745 | 200 | PV | 2-79-404 | 2019-09-25 | 2019-10-09 | 10 |  | 10 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | East Falmouth | 2366343 | 2536 | 39.83 | PV | TBD | 2019-09-27 | 2019-10-09 | 8 |  | 8 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2020-03-13
NSTAR | Watertown | 2366357 | 2472 | 480 | PV | TBD | 2019-09-30 | 2019-10-10 | 8 |  | 8 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Watertown | 2366405 | 2472 | 99.9 | PV | TBD | 2019-09-30 | 2019-10-10 | 8 |  | 8 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Watertown | 2366415 | 2472 | 353 | PV | TBD | 2019-09-30 | 2019-10-10 | 8 |  | 8 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Orleans | 2366434 | 2653 | 20 | PV | 4-89B-89B | 2019-09-20 | 2019-10-09 | 13 |  | 13 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-25 | [7 empty] | 0 |  | 0 |  |  | 2020-04-08 | Online
NSTAR | Natick | 2366438 | 1760 | 100 | PV | TBD | 2019-10-15 | 2019-10-15 | 0 |  | 0 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-20 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2366447 | 2740 | 1400 | Fuel Cell | TBD | 2019-10-11 | 2019-10-15 | 2 |  | 2 | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Falmouth | 2366459 | 2556 | 15.2 | PV | TBD | 2019-08-01 | 2019-10-16 | 54 |  | 54 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2020-05-18 | Online
NSTAR | Marshfield | 2366460 | 2050 | 250 | PV | TBD | 2019-10-11 | 2019-10-16 | 3 |  | 3 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Freetown | 2366461 | 2717 | 2000 | PV | TBD | 2019-08-14 | 2019-10-16 | 45 |  | 45 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2366478 | 1760 | 250 | PV | TBD | 2019-10-31 |  | -31231 | 0 | 0 | 2019-11-05 | 2020-07-01 | 171 | 13 | 158 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-06-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Milton | 2366661 | 2186 | 18.2 | PV | TBD | 2019-09-23 | 2019-10-21 | 20 |  | 20 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-18 | [7 empty] | 0 |  | 0 |  |  | 2020-03-17 | Online
NSTAR | Kingston | 2366662 | 2364 | 15.3 | PV | 3-15-15 | 2019-09-19 | 2019-10-22 | 23 |  | 23 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 2366684 | 2186 | 15.2 | PV | 311-11 | 2019-08-29 |  | -31186 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-16 | [7 empty] | 0 |  | 0 |  |  | 2021-02-17 | Online
NSTAR | Woburn | 2366729 | 1801 | 250 | PV | TBD | 2019-10-11 | 2019-10-16 | 3 |  | 3 | 2019-11-05 |  | -31234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-17 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online
NSTAR | Newton | 2366803 | 2465 | 21.4 | PV | 1713 | 2019-09-25 | 2019-10-22 | 19 |  | 19 | 2019-11-05 |  | -31234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-20 | [7 empty] | 0 |  | 0 |  |  | 2020-08-26 | Online
NSTAR | Waltham | 2367388 | 2453 | 480 | PV | TBD | 2019-09-25 | 2019-10-16 | 15 |  | 15 | 2019-11-05 |  | -31234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2367405 | 1890 | 15.2 | PV | 211-H10 | 2019-08-28 | 2019-10-16 | 35 |  | 35 | 2019-11-05 |  | -31234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Boston | 2367475 | 2116 | 1150 | CHP | TBD | 2019-09-25 | 2019-10-18 | 17 |  | 17 | 2019-11-05 |  | -31234 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Brighton | 2367836 | 2135 | 456 | PV | TBD | 2019-10-07 | 2019-10-22 | 11 |  | 11 | 2019-11-07 |  | -31236 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Sherborn | 2367897 | 1770 | 22.8 | PV | 240-H1 | 2019-10-18 | 2019-10-24 | 4 |  | 4 | 2019-11-07 |  | -31236 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-11-29 | [7 empty] | 0 |  | 0 |  |  | 2021-06-01 | Online
NSTAR | East Falmouth | 2367955 | 2536 | 134 | PV | TBD | 2019-10-18 | 2019-10-23 | 3 |  | 3 | 2019-11-07 |  | -31236 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-11 | [7 empty] | 0 |  | 0 |  |  | 2021-03-05 | Online
NSTAR | Newton | 2367956 | 2459 | 436 | PV | TBD | 2019-07-16 | 2019-10-25 | 73 |  | 73 | 2019-11-07 |  | -31236 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-26 | [7 empty] | 0 |  | 0
NSTAR | Lincoln | 2368084 | 1773 | 129.6 | PV | TBD | 2019-10-28 | 2019-10-28 | 0 |  | 0 | 2019-12-04 |  | -31255 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Brewster | 2368090 | 2631 | 199.8 | PV | 4-95A-597 | 2018-09-12 | 2018-09-20 | 6 |  | 6 | 2018-10-10 |  | -30955 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-12-14 | [7 empty] | 0 |  | 0 |  |  | 2020-11-10 | Online
NSTAR | Lincoln | 2368534 | 1773 | 23.7 | PV | 282-H1 | 2019-08-05 | 2019-10-28 | 60 |  | 60 | 2019-11-13 |  | -31240 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-30 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Hatchville | 2368537 | 2536 | 20 | PV | TBD | 2019-10-18 | 2019-10-28 | 6 |  | 6 | 2019-11-13 |  | -31240 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2368538 | 2739 | 15.2 | PV | 2-301-301 | 2019-09-10 | 2019-10-28 | 34 |  | 34 | 2019-11-13 |  | -31240 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2368571 | 2067 | 499 | PV & Battery | TBD | 2019-10-24 | 2019-10-29 | 3 |  | 3 | 2019-11-14 |  | -31241 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-03 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2368605 | 2067 | 999 | PV | TBD | 2019-09-05 | 2019-10-29 | 38 |  | 38 | 2019-11-14 |  | -31241 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0
NSTAR | Winchester | 2368750 | 1890 | 35.2 | PV | TBD | 2019-10-18 | 2019-10-29 | 7 |  | 7 | 2019-11-14 |  | -31241 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-02 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | Hyannis | 2368753 | 2601 | 200 | PV | TBD | 2019-10-29 | 2019-10-31 | 2 |  | 2 | 2019-11-14 |  | -31241 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-19 | Online
NSTAR | Charlestown | 2368889 | 2129 | 250 | PV | TBD | 2019-10-22 | 2019-10-25 | 3 |  | 3 | 2019-11-18 |  | -31243 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2368913 | 2459 | 220 | PV | TBD | 2019-09-20 | 2019-11-01 | 30 |  | 30 | 2019-11-18 |  | -31243 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0
NSTAR | Assonett | 2368944 | 2702 | 15.2 | PV | 2-605-605 | 2019-09-13 | 2019-11-01 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Watertown | 2369438 | 2472 | 700 | PV & Battery | TBD | 2019-10-10 | 2019-11-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Rochester | 2369465 | 2770 | 25 | PV | TBD | 2019-11-05 | 2019-11-07 | 2 |  | 2 | 2019-11-20 |  | -31245 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Yarmouth | 2369488 | 2661 | 17.23 | PV | 4-92A-562 | 2019-10-16 | 2019-11-04 | 13 |  | 13 | 2019-11-20 |  | -31245 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-03 | [7 empty] | 0 |  | 0 |  |  | 2020-02-21 | Online
NSTAR | Rochester | 2369675 | 2770 | 25 | PV | TBD | 2019-11-05 | 2019-11-07 | 2 |  | 2 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2369838 | 2601 | 975 | PV |  | 2019-11-20 | 2019-11-27 | 5 | 0 | 5 | 2019-11-28 |  | -31251 | 264 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-06-29 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2019-12-10
NSTAR | Dorchester | 2369846 | 2122 | 66.6 | PV | TBD | 2019-11-05 | 2019-11-07 | 2 |  | 2 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sherborn | 2369848 | 1770 | 187.5 | PV | TBD | 2019-11-08 | 2019-11-12 | 2 |  | 2 | 2019-11-22 |  | -31247 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Orleans | 2369981 | 2653 | 133.7 | PV | 4-83-952 | 2019-03-04 | 2019-03-12 | 6 |  | 6 | 2019-04-15 |  | -31088 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-04 | Online
NSTAR | Canton | 2370020 | 2021 | 133.2 | PV | TBD | 2019-11-07 | 2019-11-08 | 1 |  | 1 | 2019-11-25 |  | -31248 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2370022 | 2458 | 200 | PV | TBD | 2019-08-29 | 2020-09-16 | 274 |  | 274 | 2020-11-22 |  | -31507 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0 |  |  | 2021-05-12 | Online
NSTAR | Wayland | 2370024 | 1778 | 80 | PV | TBD | 2019-10-28 | 2019-11-08 | 9 |  | 9 | 2019-11-22 |  | -31247 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-03 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online
NSTAR | New Bedford | 2370116 | 2745 | 100 | PV | TBD | 2019-11-22 | 2019-11-22 | 0 |  | 0 | 2019-11-25 |  | -31248 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2370417 | 1746 | 437.5 | PV | TBD | 2019-11-08 | 2019-11-12 | 2 |  | 2 | 2019-11-26 |  | -31249 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2370419 | 2458 | 100 | PV | TBD | 2019-11-05 | 2019-11-12 | 5 |  | 5 | 2019-11-26 |  | -31249 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Charlestown | 2370420 | 2129 | 100 | PV | TBD | 2019-11-04 | 2019-11-12 | 6 |  | 6 | 2019-11-26 |  | -31249 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2370421 | 2458 | 62.5 | PV | TBD | 2019-11-04 | 2019-11-12 | 6 |  | 6 | 2019-12-04 |  | -31255 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chatham | 2370503 | 2633 | 133.3 | PV | TBD | 2019-11-08 | 2019-11-12 | 2 |  | 2 | 2019-11-27 |  | -31250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-21 | [7 empty] | 0 |  | 0 |  |  | 2021-09-20 | Online
NSTAR | Marshfield | 2370516 | 2050 | 187.5 | PV | TBD | 2019-11-08 | 2019-11-12 | 2 |  | 2 | 2019-11-27 |  | -31250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2370546 | 2021 | 495.8 | PV | TBD | 2019-11-04 | 2019-11-12 | 6 |  | 6 | 2019-11-27 |  | -31250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-13 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2370560 | 1746 | 499 | PV | TBD | 2019-11-04 | 2019-11-12 | 6 |  | 6 | 2019-11-27 |  | -31250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-27 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 2370575 | 2081 | 312.5 | PV | TBD | 2019-11-04 | 2019-11-12 | 6 |  | 6 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2370582 | 2607 | 370 | PV | TBD | 2019-10-07 | 2019-11-12 | 26 |  | 26 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-02 | [7 empty] | 0 |  | 0
NSTAR | Ashland | 2370583 | 1721 | 125 | PV | TBD | 2019-10-31 | 2019-11-12 | 8 |  | 8 | 2019-11-27 |  | -31250 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 2370630 | 2607 | 660 | PV | TBD | 2019-10-07 | 2019-11-12 | 26 |  | 26 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2370666 | 2607 | 5000 | PV & Battery | TBD | 2019-10-07 | 2019-11-13 | 27 |  | 27 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0
NSTAR | Westport | 2370690 | 2721 | 3375 | PV | TBD | 2019-10-29 | 2019-11-14 | 12 |  | 12 | 2019-11-29 |  | -31252 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Arlington | 2370768 | 2474 | 19.86 | PV & Battery | 59-1383H1 | 2019-10-31 | 2019-11-19 | 13 |  | 13 | 2019-12-02 |  | -31253 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Sandwich | 2370777 | 2563 | 250 | PV & Battery | TBD | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-02 |  | -31253 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2370785 | 2744 | 150 | PV | TBD | 2019-11-07 | 2019-11-19 | 8 |  | 8 | 2019-12-02 |  | -31253 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2021-05-18 | Online
NSTAR | Plympton | 2370996 | 2367 | 1560 | PV | 3-51-980 | 2019-10-24 | 2019-11-07 | 10 |  | 10 | 2019-12-03 |  | -31254 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2371039 | 2576 | 100 | PV | TBD | 2019-11-08 | 2019-11-15 | 5 |  | 5 | 2019-12-03 |  | -31254 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2371521 | 2601 | 250 | PV | TBD | 2019-09-30 | 2019-10-28 | 20 |  | 20 | 2019-12-04 |  | -31255 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-13 | [7 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Canton | 2371598 | 2021 | 325 | Natural Gas | 269-1321H2 | 2019-11-14 | 2019-11-14 | 0 |  | 0 | 2019-12-04 |  | -31255 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0
NSTAR | Wareham | 2371602 | 2571 | 166.6 | PV | TBD | 2019-11-08 | 2019-11-15 | 5 |  | 5 | 2019-12-04 |  | -31255 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2372155 | 2563 | 250 | PV & Battery | 4-81B-81B | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Eastham | 2372185 | 2642 | 37.7 | PV | TBD | 2019-11-13 | 2019-11-20 | 5 |  | 5 | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0 |  |  | 2020-07-30 | Online
NSTAR | Framingham | 2372222 | 1702 | 250 | PV | TBD | 2019-10-11 | 2019-10-15 | 2 |  | 2 | 2019-11-01 |  | -31232 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2372246 | 2421 | 3000 | CHP | 2-1N11 | 2019-11-18 | 2019-11-19 | 1 |  | 1 | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | 2372255 | 2535 | - |  | TBD | 2019-12-04 |  | -31255 | 0 | 0 | 2019-12-19 | 2020-01-27 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-02-20 | 2020-10-01 | 2020-07-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Dedham | 2372263 | 2026 | 15.2 | PV | TBD | 2019-11-06 | 2019-11-18 | 8 |  | 8 | 2019-12-06 |  | -31257 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online
NSTAR | South Yarmouth | 2372266 | 2664 | 160 | PV & Battery | TBD | 2019-06-14 | 2019-07-02 | 12 |  | 12 | 2019-07-19 |  | -31157 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0
NSTAR | Sandwich | 2372267 | 2563 | 250 | PV & Battery | TBD | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-06 |  | -31257 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2373333 | 2451 | 144 | PV | 450-H7 | 2019-11-14 | 2019-11-08 | -6 |  | 0 | 2019-11-25 |  | -31248 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-27 | [7 empty] | 0 |  | 0
NSTAR | East Freetown | 2373342 | 2717 | 17.6 | PV & Battery | 2-102-602 | 2019-11-07 | 2019-11-22 | 11 |  | 11 | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Sandwich | 2373431 | 2563 | 112.5 | PV | TBD | 2019-11-19 | 2019-11-19 | 0 |  | 0 | 2019-12-06 |  | -31257 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Sandwich | 2373432 | 2644 | 2500 | PV & Battery | TBD | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 2373744 | 1748 | 15.2 | PV | 126-H1 | 2019-11-18 | 2019-11-21 | 3 |  | 3 | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2373797 | 2362 | 60 | PV | 3-13-13 | 2019-11-11 | 2019-11-25 | 10 |  | 10 | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 2373810 | 2653 | 89.39 | PV | TBD | 2019-05-28 | 2019-06-20 | 17 |  | 17 | 2019-07-05 |  | -31147 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-10-07 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Centerville | 2373813 | 2632 | 747 | PV & Battery | tbd | 2019-11-15 | 2019-11-20 | 3 |  | 3 | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 2373814 | 2144 | 133.2 | PV | TBD | 2019-11-18 | 2019-11-27 | 7 |  | 7 | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-18 | [7 empty] | 0 |  | 0 |  |  | 2022-02-09 | Online
NSTAR | Chelsea | 2373967 | 2150 | 275 | PV & Battery | 488-H2 | 2019-11-08 | 2019-11-26 | 12 |  | 12 | 2019-12-12 |  | -31261 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-29 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | Sandwich | 2374039 | 2563 | 249 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 | 3 |  | 3 | 2019-12-12 |  | -31261 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2374058 | 2067 | 200 | PV | 146-H1 | 2019-11-27 | 2019-11-27 | 0 |  | 0 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-06 | [7 empty] | 0 |  | 0 |  |  | 2021-04-20 | Online
NSTAR | Waltham | 2374169 | 2451 | 250 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 | 3 |  | 3 | 2019-12-12 |  | -31261 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Fairhaven | 2374177 | 2719 | 200 | PV | 2-220-206 | 2019-11-27 | 2019-11-27 | 0 |  | 0 | 2019-12-12 |  | -31261 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Medfield | 2374353 | 2052 | 17.6 | PV & Battery | TBD | 2019-11-21 | 2019-12-02 | 7 |  | 7 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-13 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | West Harwich | 2374665 | 2671 | 25.6 | PV & Battery | 4-85-592 | 2019-11-22 | 2019-12-02 | 6 |  | 6 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0
NSTAR | Roxbury | 2374769 | 2120 | 55.8 | PV | TBD | 2019-12-02 | 2019-12-02 | 0 |  | 0 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-03 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Chatham | 2374770 | 2659 | 25 | PV & Battery | 4-95A-606 | 2019-11-15 | 2019-12-02 | 11 |  | 11 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-21 | [7 empty] | 0 |  | 0 |  |  | 2020-12-07 | Online
NSTAR | Mattapoisett | 2374771 | 2739 | - | PV & Battery | TBD | 2019-11-27 | 2019-12-03 | 4 |  | 4 | 2019-12-17 |  | -31264 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 2375330 | 2739 | 28.7 | PV & Battery | 2-301-301 | 2019-11-27 | 2019-12-03 | 4 |  | 4 | 2019-12-20 |  | -31267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Arlington | 2375571 | 2476 | 275 | PV & Battery | TBD | 2019-11-27 | 2019-12-05 | 6 |  | 6 | 2019-12-20 |  | -31267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-28 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Lexington | 2375572 | 2420 | 15.2 | PV | TBD | 2019-11-27 | 2019-12-03 | 4 |  | 4 | 2019-12-20 |  | -31267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-11-13 | Online
NSTAR | Woburn | 2375623 | 1801 | 150 | PV | TBD | 2019-12-02 | 2019-12-05 | 3 |  | 3 | 2019-12-20 |  | -31267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-28 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 2375708 | 2476 | 15.2 | PV | TBD | 2019-12-03 | 2019-12-10 | 5 |  | 5 | 2019-12-20 |  | -31267 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2020-08-11 | Online
NSTAR | Plymouth | 2375823 | 2360 | 173.46 | PV | TBD | 2019-12-11 | 2019-12-11 | 0 |  | 0 | 2019-12-26 |  | -31271 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | Falmouth | 2376010 | 2540 | 133.2 | PV | TBD | 2019-12-09 | 2019-12-12 | 3 |  | 3 | 2019-12-26 |  | -31271 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-15 | [7 empty] | 0 |  | 0 |  |  | 2020-08-11 | Online
NSTAR | Carlisle | 2376068 | 1741 | 17.6 | PV | 512-1399H1 | 2019-10-22 | 2019-12-11 | 36 |  | 36 | 2019-12-26 |  | -31271 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-21 | [7 empty] | 0 |  | 0
NSTAR | Cotuit | 2376383 | 2635 | 200 | PV | TBD | 2019-12-12 | 2019-12-16 | 2 |  | 2 | 2019-12-31 |  | -31274 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-06-27 | Online
NSTAR | Bedford | 2376385 | 1730 | 25 | PV & Battery | 533-H8 | 2019-12-11 | 2019-12-19 | 6 |  | 6 | 2019-12-31 |  | -31274 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Burlington | 2377387 | 1803 | 19.57 | PV & Battery | TBD | 2019-11-22 | 2019-11-26 | 2 |  | 2 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | 2377419 | 2136 | - |  | TBD | 2020-01-02 |  | -31276 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-08-06 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wayland | 2377433 | 1778 | 20 | PV & Battery | 342-H1 | 2019-11-07 | 2019-11-22 | 11 |  | 11 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2377476 | 2125 | 72 | PV | TBD | 2019-10-18 | 2019-11-22 | 25 |  | 25 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-29 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2377493 | 2453 | 80 | PV | TBD | 2019-12-13 | 2019-12-20 | 5 |  | 5 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-03-01 | Online
NSTAR | Centerville | 2377494 | 2632 | 15.2 | PV | TBD | 2019-11-25 | 2019-12-20 | 19 |  | 19 | 2020-01-03 |  | -31277 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Harwich | 2378433 | 2645 | 3150 | PV & Battery | TBD | 2019-11-22 | 2019-11-22 | 0 |  | 0 | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | 2378459 | 2364 | 320 | PV | 3-17-916 | 2019-11-13 | 2019-11-25 | 8 |  | 8 | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-28 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2378471 | 1702 | 15.2 | PV | 274-H1 | 2019-12-02 | 2019-12-12 | 8 |  | 8 | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Medway | 2378489 | 2053 | 230 | PV | TBD | 2019-11-20 | 2019-12-13 | 17 |  | 17 | 2020-01-23 |  | -31291 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-11 | [7 empty] | 0 |  | 0 |  |  | 2020-09-21 | Online
NSTAR | South Dennis | 2378744 | 2660 | 30.72 | PV | TBD | 2019-11-20 | 2019-11-26 | 4 |  | 4 | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2378798 | 2563 | 490 | PV & Battery | TBD | 2019-11-22 | 2019-11-27 | 3 |  | 3 | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Roxbury | 2378813 | 2132 | 43.2 | PV | TBD | 2019-12-11 | 2019-12-19 | 6 |  | 6 | 2020-01-08 |  | -31280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  | 2021-02-08 | Online
NSTAR | Carver | 2378857 | 2330 | 2500 | PV & Battery | TBD | 2019-11-19 | 2019-12-23 | 24 |  | 24 | 2020-01-07 |  | -31279 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bourne | 2378858 | 2532 | 5000 | PV & Battery | TBD | 2019-11-21 | 2019-12-23 | 22 |  | 22 | 2020-01-07 |  | -31279 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 2380743 | 2719 | 200 | PV | 2-221-221 | 2019-11-27 | 2019-11-27 | 0 |  | 0 | 2020-01-08 |  | -31280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-20 | [7 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Waltham | 2380747 | 2451 | 16 | Battery | 450-H3 | 2019-11-27 | 2019-12-02 | 3 |  | 3 | 2020-01-08 |  | -31280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2380929 | 2421 | 133.3 | PV | 533-H1 | 2019-12-02 | 2019-12-05 | 3 |  | 3 | 2020-01-09 |  | -31281 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 2380935 | 1748 | 250 | PV |  | 2020-01-08 | 2020-01-09 | 1 | 0 | 1 | 2020-01-10 | 2020-05-08 | 85 | 4 | 81 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-27 |  | 2020-08-12 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Onset | 2381115 | 2558 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-08-13 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Marshfield | 2381120 | 2048 | 4600 | PV & Battery | TBD | 2019-12-18 | 2019-12-26 | 6 |  | 6 | 2020-01-10 |  | -31282 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2381326 | 2180 | 20 | PV & Battery | 375-H8 | 2019-11-18 | 2019-12-26 | 28 |  | 28 | 2020-01-13 |  | -31283 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Westport | 2381437 | 2790 | 4000 | PV & Battery | TBD | 2019-11-19 | 2019-12-30 | 29 |  | 29 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Watertown | 2381519 | 2472 | 100 | PV | 467-H5 | 2019-12-20 | 2019-12-20 | 0 |  | 0 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-03 | [7 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Lexington | 2381543 | 2421 | 130 | PV | 533-H1 | 2019-12-10 | 2019-12-13 | 3 |  | 3 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-03 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2381555 | 2453 | 748 | PV | TBD | 2019-12-09 | 2019-12-12 | 3 |  | 3 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 2381556 | 2136 | 19 | PV | 60-1409H1 | 2019-10-31 | 2019-12-02 | 22 |  | 22 | 2020-01-15 |  | -31285 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-30 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Walpole | 2381558 | 2032 | 23.8 | PV | TBD | 2019-12-11 | 2019-12-16 | 3 |  | 3 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Woburn | 2381571 | 1801 | 3623 | PV | TBD | 2019-12-05 | 2019-12-09 | 2 |  | 2 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-24 | [7 empty] | 0 |  | 0
NSTAR | Bourne | 2381610 | 2532 | 5000 | PV & Battery | TBD | 2019-12-13 | 2019-12-23 | 6 |  | 6 | 2020-01-16 |  | -31286 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 2381700 | 2770 | 21.4 | PV | TBD | 2019-11-06 | 2019-12-30 | 38 |  | 38 | 2020-01-16 |  | -31286 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2381703 | 2360 | 249.9 | PV & Battery | TBD | 2019-12-30 | 2019-12-30 | 0 |  | 0 | 2020-01-16 |  | -31286 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2381861 | 2648 | 40 | PV | TBD | 2019-12-19 | 2020-01-02 | 10 |  | 10 | 2020-01-16 |  | -31286 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Carver | 2382007 | 2330 | 50 | PV | TBD | 2019-12-26 | 2020-01-06 | 7 |  | 7 | 2020-01-17 |  | -31287 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-07 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | Needham | 2382008 | 2494 | 17 | PV & Battery | 148-08 | 2019-12-05 | 2020-01-06 | 22 |  | 22 | 2020-01-17 |  | -31287 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | Lexington | 2382228 | 2421 | 22.72 | PV | 320-H2 | 2019-12-20 | 2020-01-02 | 9 |  | 9 | 2020-01-21 |  | -31289 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Needham | 2382255 | 2494 | 17.25 | PV | 148-H4 | 2019-12-09 | 2020-01-02 | 18 |  | 18 | 2020-01-21 |  | -31289 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-08 | [7 empty] | 0 |  | 0 |  |  | 2020-11-23 | Online
NSTAR | East Freetown | 2382455 | 2717 | 25 | PV & Battery | TBD | 2020-01-06 | 2020-01-06 | 0 |  | 0 | 2020-01-21 |  | -31289 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-01-31 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2382474 | 2571 | 66.6 | PV | 3-84-960 | 2019-12-19 | 2020-01-06 | 12 |  | 12 | 2020-01-30 |  | -31296 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2383462 | 2053 | 15.2 | PV | 130-H2 | 2019-12-18 | 2019-12-20 | 2 |  | 2 | 2020-01-30 |  | -31296 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0
NSTAR | Carlisle | 2383471 | 1741 | 17.6 | PV & Battery | 512-1399H1 | 2019-12-13 | 2020-01-13 | 21 |  | 21 | 2020-01-31 |  | -31297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Hyde Park | 2383520 | 2136 | 333.2 | PV | TBD | 2020-01-02 | 2020-01-13 | 7 |  | 7 | 2020-01-30 |  | -31296 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | Dennis | 2383632 | 2670 | 20 | PV & Battery | 4-92B-571 | 2020-01-04 | 2020-01-13 | 6 |  | 6 | 2020-01-31 |  | -31297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0 |  |  | 2020-05-21
NSTAR | South Dennis | 2383634 | 2660 | 37.6 | PV | TBD | 2020-01-06 | 2020-01-13 | 5 |  | 5 | 2020-01-31 |  | -31297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2020-05-29 | Online
NSTAR | North Falmouth | 2383638 | 2556 | 15.2 | PV | 4-78-78 | 2020-01-08 | 2020-01-15 | 5 |  | 5 | 2020-01-31 |  | -31297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-13 | [7 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Watertown | 2383645 | 2472 | 52.2 | PV | TBD | 2020-01-06 | 2020-01-07 | 1 |  | 1 | 2020-01-31 |  | -31297 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online
NSTAR | Westport | 2383646 | 2790 | 4000 | PV & Battery | TBD | 2019-12-20 | 2020-01-08 | 13 |  | 13 | 2020-02-04 |  | -31299 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Eastham | 2384268 | 2642 | 10 | PV & Battery | 4-94A-633 | 2019-11-22 | 2020-01-16 | 39 |  | 39 | 2020-02-04 |  | -31299 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 2384357 | 2453 | 40 | PV | TBD | 2019-06-14 | 2020-01-21 | 157 |  | 157 | 2020-02-04 |  | -31299 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Marshfield | 2384377 | 2050 | 16.2 | PV | 3-24A-971 | 2019-09-18 | 2019-12-11 | 60 |  | 60 | 2020-02-04 |  | -31299 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-21 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Brookline | 2384381 | 2446 | 38.5 | PV | TBD | 2020-01-16 | 2020-01-17 | 1 |  | 1 | 2020-02-04 |  | -31299 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2384383 | 2420 | 17 | PV & Battery | 320-H5XY | 2020-01-15 | 2020-01-22 | 5 |  | 5 | 2020-02-07 |  | -31302 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | New Bedford | 2384474 | 2746 | 133 | PV |  | 2020-02-04 | 2020-02-07 | 3 | 0 | 3 | 2020-02-13 | 2020-02-28 | 11 | 0 | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 |  | 2020-09-08 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Woburn | 2384521 | 1801 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-09-08 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Provincetown | 2384542 | 2657 | 70 | PV | 4-96-675 | 2020-01-15 | 2020-01-22 | 5 |  | 5 | 2020-02-06 |  | -31301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Hopkinton | 2384545 | 1748 | 111.5 | PV & Battery | 126-H2 | 2019-12-10 | 2020-01-02 | 17 |  | 17 | 2020-02-07 |  | -31302 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0 |  |  | 2021-03-31
NSTAR | Wareham | 2384553 | 2538 | 4995 | PV & Battery | TBD | 2019-12-30 | 2020-01-06 | 5 |  | 5 | 2020-02-06 |  | -31301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | 2384624 | 1702 | 440 | PV | TBD | 2020-01-21 | 2020-01-23 | 2 |  | 2 | 2020-02-06 |  | -31301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-12 | [7 empty] | 0 |  | 0 |  |  | 2021-08-03 | Online
NSTAR | Freetown | 2384761 | 2717 | 2000 | PV & Battery | TBD | 2020-01-07 | 2020-01-08 | 1 |  | 1 | 2020-02-06 |  | -31301 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2384826 | 2451 | 166.6 | PV | TBD | 2019-12-30 | 2020-01-08 | 7 |  | 7 | 2020-02-07 |  | -31302 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Orleans | 2384945 | 2653 | 60 | PV |  | 2020-02-06 | 2020-02-11 | 3 | 0 | 3 | 2020-02-11 | 2020-02-12 | 1 | 0 | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | 2020-03-02 | 2020-09-10 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2020-10-06 | Online | Private
NSTAR | South Yarmouth | 2384954 | 2664 | 437.5 | PV | TBD | 2019-12-19 | 2020-01-06 | 12 |  | 12 | 2020-02-07 |  | -31302 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Online
NSTAR | Walpole | 2384980 | 2081 | 30.2 | PV & Battery | 146-H4 | 2020-01-10 | 2020-01-26 | 10 |  | 10 | 2020-02-07 |  | -31302 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-04 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21 | Online
NSTAR | Dorchester | 2384991 | 2122 | 100 | PV & Battery | 6702 | 2020-01-22 | 2020-01-28 | 4 |  | 4 | 2020-02-11 |  | -31304 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-02 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | Burlington | 2385267 | 1803 | 19.76 | PV | 346-1395H1 | 2020-01-17 | 2020-01-27 | 6 |  | 6 | 2020-02-11 |  | -31304 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-09-09
NSTAR | West Tisbury | 2385299 | 2575 | 25 | PV | TBD | 2020-01-22 | 2020-01-28 | 4 |  | 4 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-18 | Online
NSTAR | Watertown | 2385313 | 2472 | 43.2 | PV | 282-H8 | 2020-01-22 | 2020-01-28 | 4 |  | 4 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2020-12-24 | Online
NSTAR | Westwood | 2385414 | 2090 | 25 | PV & Battery | 469-H2 | 2020-01-21 | 2020-01-28 | 5 |  | 5 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-03 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Acton | 2385734 | 1720 | 200 | PV | TBD | 2019-12-12 | 2020-01-31 | 36 |  | 36 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 2385800 | 1702 | 187.5 | PV | TBD | 2020-01-30 | 2020-01-30 | 0 |  | 0 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-12 | Online
NSTAR | Needham | 2385802 | 2494 | 460 | PV | TBD | 2019-12-09 | 2020-01-30 | 38 |  | 38 | 2020-02-14 |  | -31307 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2023-04-28 | Online
NSTAR | Falmouth | 2386189 | 2540 | 34.6 | PV & Battery | 4-78-420 | 2020-01-22 | 2020-02-03 | 8 |  | 8 | 2020-02-19 |  | -31310 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0
NSTAR | Provincetown | 2386275 | 2657 | 28.8 | PV | TBD | 2020-01-30 | 2020-02-03 | 2 |  | 2 | 2020-02-19 |  | -31310 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-02 | [7 empty] | 0 |  | 0
NSTAR | Duxbury | 2386320 | 2332 | 66.6 | PV | TBD | 2020-02-03 | 2020-02-03 | 0 |  | 0 | 2020-02-19 |  | -31310 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-04 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Barnstable | 2386368 | 2630 | 240 | PV | 4-84B-510 | 2020-02-03 | 2020-02-03 | 0 |  | 0 | 2020-02-20 |  | -31311 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2386391 | 2745 | 30 | PV | 2-137-137 | 2019-12-03 | 2020-02-04 | 45 |  | 45 | 2020-02-25 |  | -31314 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-24 | [7 empty] | 0 |  | 0 |  |  | 2020-09-25 | Online
NSTAR | Ashland | 2386559 | 1721 | 10 | PV & Battery | 274-H1 | 2020-01-23 | 2020-02-04 | 8 |  | 8 | 2020-02-20 |  | -31311 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Wareham | 2386584 | 2538 | 30 | PV | 3-84-960 | 2019-12-03 | 2020-02-04 | 45 |  | 45 | 2020-02-24 |  | -31313 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-16 | [7 empty] | 0 |  | 0 |  |  | 2020-10-06 | Online
NSTAR | Dedham | 2386594 | 2026 | 10 | PV & Battery | 20-H7 | 2020-01-29 | 2020-02-04 | 4 |  | 4 | 2020-02-24 |  | -31313 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2387342 | 1746 | 4999 | PV & Battery | TBD | 2019-12-26 | 2020-02-06 | 30 |  | 30 | 2020-02-25 |  | -31314 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-12-05 | Online
NSTAR | Marshfield | 2387378 | 2050 | 15.1 | PV | 3-24B-24B | 2019-12-23 | 2020-02-06 | 33 |  | 33 | 2020-02-25 |  | -31314 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-06 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Bourne | 2387476 | 2532 | 43.2 | PV | 4-86-402 | 2020-02-10 | 2020-02-13 | 3 |  | 3 | 2020-02-26 |  | -31315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-20 | [7 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Winchester | 2387543 | 1890 | 20 | PV | 211-H10 | 2020-04-14 | 2020-02-21 | -39 |  | 0 | 2020-03-02 |  | -31318 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-17 | Online
NSTAR | Needham | 2387570 | 2494 | 7 | PV & Battery | 148-H4 | 2020-01-06 | 2020-01-16 | 8 |  | 8 | 2020-02-27 |  | -31316 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0 |  |  | 2020-07-21 | Online
NSTAR | Boston | 2387593 | 2210 | 233.3 | PV | TBD | 2019-12-19 | 2020-02-14 | 41 |  | 41 | 2020-02-27 |  | -31316 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hyannis | 2387744 | 2601 | 115.05 | PV | TBD | 2020-02-10 | 2020-02-13 | 3 |  | 3 | 2020-03-02 |  | -31318 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23 | Online
NSTAR | Brookline | 2387929 | 2467 | 20 | PV & Battery | 496-H5 | 2020-01-16 | 2020-02-14 | 21 |  | 21 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2020-03-26 | Online
NSTAR | East Freetown | 2387969 | 2717 | 15.2 | PV | 2-107-107 | 2020-01-22 | 2020-02-18 | 19 |  | 19 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 2387970 | 2649 | 499.73 | PV | TBD | 2020-02-10 | 2020-02-13 | 3 |  | 3 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-17 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 2387981 | 2420 | 20 | PV & Battery | 533-H3 | 2019-12-02 | 2020-02-14 | 54 |  | 54 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-11 | [7 empty] | 0 |  | 0 |  |  | 2020-07-28 | Online
NSTAR | Walpole | 2388024 | 2021 | 20 | PV | TBD | 2020-02-06 | 2020-02-14 | 6 |  | 6 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0 |  |  | 2020-10-28 | Online
NSTAR | Mattapoisett | 2388535 | 2739 | 800 | PV | TBD | 2020-01-30 | 2020-02-18 | 13 |  | 13 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | 2388537 | 2364 | 2760 | PV | TBD | 2020-01-22 | 2020-02-18 | 19 |  | 19 | 2020-03-04 |  | -31320 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 2388583 | 2125 | 366.3 | PV | TBD | 2020-02-18 | 2020-02-18 | 0 |  | 0 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | 2388590 | 2364 | 66.6 | PV | TBD | 2020-02-14 | 2020-02-18 | 2 |  | 2 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-04-16 | Online
NSTAR | Winchester | 2388617 | 1890 | 17.6 | PV & Battery | TBD | 2020-01-16 | 2020-02-19 | 24 |  | 24 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 | [7 empty] | 0 |  | 0 |  |  | 2020-06-12 | Online
NSTAR | Needham | 2388633 | 2492 | 18.8 | PV | 148-06 | 2019-12-02 | 2020-02-19 | 57 |  | 57 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0
NSTAR | Dorchester | 2388772 | 2125 | 121.22 | PV | TBD | 2020-02-10 | 2020-02-19 | 7 |  | 7 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Plympton | 2388822 | 2367 | 15.2 | PV | TBD | 2020-02-10 | 2020-02-21 | 9 |  | 9 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-05-12 | Online
NSTAR | Framingham | 2388879 | 1702 | 400 | PV | TBD | 2020-01-21 | 2020-02-24 | 24 |  | 24 | 2020-03-06 |  | -31322 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-30 | [7 empty] | 0 |  | 0 |  |  | 2021-12-31 | Online
NSTAR | Newton | 2388945 | 2378 | 2400 | CHP | TBD | 2019-12-20 | 2020-02-20 | 44 |  | 44 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Osterville | 2389165 | 2655 | 23.3 | PV & Battery | 4-80A-490 | 2019-11-04 | 2020-02-21 | 79 |  | 79 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Duxbury | 2389174 | 2332 | 16.7 | PV | TBD | 2020-02-18 | 2020-02-21 | 3 |  | 3 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Falmouth | 2389176 | 2540 | 21.58 | PV & Battery | 4-72-433 | 2019-12-18 | 2020-02-24 | 48 |  | 48 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0
NSTAR | Falmouth | 2389199 | 2540 | 958 | PV & Battery | TBD | 2020-02-18 | 2020-02-24 | 4 |  | 4 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2389233 | 1776 | 20 | PV & Battery | TBD | 2020-02-07 | 2020-02-24 | 11 |  | 11 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  | 2020-10-08 | Online
NSTAR | Ashland | 2389241 | 1721 | 20 | Battery | 519-175H1 | 2020-01-15 | 2020-02-24 | 28 |  | 28 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Lexington | 2389247 | 2420 | 10 | PV & Battery | TBD | 2020-01-15 | 2020-02-24 | 28 |  | 28 | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-02-17 | Online
NSTAR | Wayland | 2389401 | 1778 | 20 | PV | TBD | 2020-02-20 | 2020-02-25 | 3 |  | 3 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-09-27 | Online
NSTAR | Boston | 2389473 | 2135 | 1150 | PV & Battery | TBD | 2020-01-29 | 2020-02-25 | 19 |  | 19 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online
NSTAR | Natick | 2389477 | 1760 | 133.2 | PV | TBD | 2020-03-03 | 2020-03-04 | 1 |  | 1 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-31 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Online
NSTAR | Barnstable | 2389479 | 2630 | 66.6 | PV | TBD | 2020-02-24 | 2020-02-25 | 1 |  | 1 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Winchester | 2389481 | 1890 | 17.6 | PV & Battery | 211-H1 | 2020-02-20 | 2020-02-25 | 3 |  | 3 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-07-27 | Online
NSTAR | Edgartown | 2389485 | 2539 | 22.8 | PV | TBD | 2019-12-26 | 2020-02-25 | 43 |  | 43 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-19 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Acton | 2389509 | 1720 | 27 | Battery | 416-H4 | 2020-02-21 | 2020-02-25 | 2 |  | 2 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 2389511 | 2067 | 480 | PV | TBD | 2020-02-24 | 2020-02-25 | 1 |  | 1 | 2020-03-11 |  | -31325 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-07-20 | Online
NSTAR | Lexington | 2389932 | 2420 | 25 | PV & Battery | TBD | 2020-02-20 | 2020-02-27 | 5 |  | 5 | 2020-03-19 |  | -31331 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-03-25 | [7 empty] | 0 |  | 0 |  |  | 2020-10-20 | Online
NSTAR | Chatham | 2390124 | 2633 | 18.7 | PV & Battery | TBD | 2020-02-28 | 2020-03-03 | 2 |  | 2 | 2020-03-19 |  | -31331 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0 |  |  | 2020-07-16 | Online
NSTAR | Boston | 2390327 | 2118 | 557.5 | PV & Battery | 4912 | 2020-02-10 | 2020-03-06 | 19 |  | 19 | 2020-03-19 |  | -31331 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-12 | [7 empty] | 0 |  | 0 |  |  | 2023-02-02 | Online
NSTAR | Bellingham | 2390335 | 2019 | 15.2 | PV | 65-H4 | 2020-03-05 | 2020-03-09 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2390546 | 1702 | 100 | PV | TBD | 2020-03-02 | 2020-03-04 | 2 |  | 2 | 2020-03-19 |  | -31331 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wayland | 2390669 | 1778 | 17.6 | PV & Battery | 342-H1 | 2020-02-25 | 2020-03-05 | 7 |  | 7 | 2020-03-23 |  | -31333 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Dennis | 2390776 | 2670 | 233.3 | PV | TBD | 2020-03-06 | 2020-03-06 | 0 |  | 0 | 2020-03-23 |  | -31333 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westwood | 2390944 | 2090 | 10 | PV & Battery | 148-H3 | 2020-02-18 | 2020-03-10 | 15 |  | 15 | 2020-03-23 |  | -31333 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | North Dartmouth | 2390961 | 2747 | 150 | PV | TBD | 2020-03-09 | 2020-03-09 | 0 |  | 0 | 2020-03-23 |  | -31333 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0 |  |  | 2021-07-19 | Online
NSTAR | Weston | 2391087 | 2493 | 25 | PV & Battery | TBD | 2020-02-25 | 2020-03-09 | 9 |  | 9 | 2020-03-25 |  | -31335 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2020-07-08 | Online
NSTAR | Falmouth | 2391172 | 2536 | 4990 | PV & Battery | TBD | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Harwich | 2391210 | 2645 | 23 | PV |  | 2020-03-24 |  | -31334 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-10-27 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Harwich | 2391216 | 2645 | 23 | PV | TBD | 2020-03-06 | 2020-03-12 | 4 |  | 4 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-07-28 | Online
NSTAR | East Falmouth | 2391234 | 2536 | 3000 | PV & Battery | TBD | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2391270 | 2601 | 133.2 | PV | TBD | 2019-07-26 | 2019-07-29 | 1 |  | 1 | 2019-08-16 |  | -31177 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-06-09 | Online
NSTAR | Cataumet | 2391363 | 2534 | 29.23 | PV & Battery | 4-78-410 | 2020-02-21 | 2020-03-11 | 13 |  | 13 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-14 | [7 empty] | 0 |  | 0 |  |  | 2020-06-30 | Online
NSTAR | Newton | 2391435 | 2459 | - | Battery | 292-H8 | 2020-01-15 | 2020-03-12 | 41 |  | 41 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Falmouth | 2391457 | 2540 | 15.2 | PV | 4-72-72 | 2020-03-10 | 2020-03-12 | 2 |  | 2 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2391467 | 1746 | 20 | PV & Battery | TBD | 2020-03-09 | 2020-03-12 | 3 |  | 3 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-04 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chelsea | 2391483 | 2150 | 199.8 | PV | TBD | 2020-03-10 | 2020-03-12 | 2 |  | 2 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2391527 | 1776 | 17.6 | PV & Battery | 342-H7 | 2020-03-09 | 2020-03-12 | 3 |  | 3 | 2020-03-27 |  | -31337 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-06 | [7 empty] | 0 |  | 0 |  |  | 2020-10-23 | Online
NSTAR | Falmouth | 2391570 | 2540 | 24.6 | PV & Battery | 4-107-832 | 2020-03-05 | 2020-03-12 | 5 |  | 5 | 2020-03-30 |  | -31338 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Holliston | 2391752 | 1746 | 200 | PV | TBD | 2020-02-27 | 2020-03-16 | 12 |  | 12 | 2020-03-30 |  | -31338 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 2391763 | 1730 | 15.2 | PV | TBD | 2020-01-15 | 2020-03-16 | 43 |  | 43 | 2020-03-30 |  | -31338 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Burlington | 2391862 | 1803 | 19.12 | PV & Battery | TBD | 2020-03-09 | 2020-03-16 | 5 |  | 5 | 2020-04-01 |  | -31340 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-28 | [7 empty] | 0 |  | 0 |  |  | 2020-11-06 | Online
NSTAR | East Freetown | 2391908 | 2717 | 25 | PV | TBD | 2020-03-16 | 2020-03-16 | 0 |  | 0 | 2020-03-31 |  | -31339 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-07 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Wareham | 2391934 | 2571 | 28.8 | PV | TBD | 2020-03-16 | 2020-03-18 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-16 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | South Chatham | 2392011 | 2659 | 24.92 | PV & Battery | 4-95A-606 | 2020-03-09 | 2020-03-12 | 3 |  | 3 | 2020-04-01 |  | -31340 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0
NSTAR | Oak Bluffs | 2392014 | 2557 | 1500 | PV |  | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 2020-04-08 |  | -31345 | 179 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-03 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2020-04-17
NSTAR | Sandwich | 2392033 | 2563 | 250 | PV | TBD | 2020-02-27 | 2020-03-16 | 12 |  | 12 | 2020-04-01 |  | -31340 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 2392113 | 2743 | 4000 | PV & Battery | TBD | 2020-03-12 | 2020-03-18 | 4 |  | 4 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Millis | 2392127 | 2054 | 250 | PV | TBD | 2020-03-18 | 2020-03-18 | 0 |  | 0 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0
NSTAR | Bedford | 2392184 | 1730 | 20 | PV | 533-H8 | 2020-03-17 | 2020-03-18 | 1 |  | 1 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-22 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Roxbury | 2392188 | 2132 | 344.8 | PV & Battery | TBD | 2020-03-05 | 2020-03-18 | 9 |  | 9 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2021-10-15 | Online
NSTAR | Walpole | 2392586 | 2081 | 2000 | PV & Battery | TBD | 2020-03-06 | 2020-03-20 | 10 |  | 10 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2392595 | 1760 | 456 | PV & Battery | TBD | 2020-03-05 | 2020-03-20 | 11 |  | 11 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-29 | [7 empty] | 0 |  | 0 |  |  | 2023-01-13 | Online
NSTAR | Marshfield | 2392617 | 2050 | 500 | PV | TBD | 2020-03-18 | 2020-03-20 | 2 |  | 2 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | 2392719 | 2050 | 250 | PV | TBD | 2020-03-18 | 2020-03-20 | 2 |  | 2 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-03 | [7 empty] | 0 |  | 0 |  |  | 2022-06-08 | Online
NSTAR | Natick | 2392730 | 1760 | 180 | PV | TBD | 2020-03-02 | 2020-03-20 | 14 |  | 14 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-29 | [7 empty] | 0 |  | 0 |  |  | 2023-01-13 | Online
NSTAR | Arlington | 2392742 | 2474 | 17.6 | PV & Battery | TBD | 2020-02-20 | 2020-03-18 | 19 |  | 19 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-06 | [7 empty] | 0 |  | 0 |  |  | 2020-09-11 | Online
NSTAR | Harwich | 2392746 | 2645 | 4990 | PV & Battery | TBD | 2020-03-16 | 2020-03-20 | 4 |  | 4 | 2020-04-03 |  | -31342 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | 2392870 | 2576 | 133.2 | PV | TBD | 2020-03-18 | 2020-03-20 | 2 |  | 2 | 2020-04-08 |  | -31345 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0
NSTAR | Allston | 2392879 | 2134 | 36 | CHP | TBD | 2020-03-18 | 2020-03-20 | 2 |  | 2 | 2020-04-07 |  | -31344 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-17 | [7 empty] | 0 |  | 0 |  |  | 2020-09-25 | Online
NSTAR | Duxbury | 2392885 | 2332 | 4000 | PV & Battery | TBD | 2020-03-20 | 2020-03-23 | 1 |  | 1 | 2020-04-07 |  | -31344 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2392889 | 2601 | 72 | PV | TBD | 2020-03-17 | 2020-03-20 | 3 |  | 3 | 2020-04-08 |  | -31345 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 2392993 | 2360 | 144 | PV | TBD | 2020-03-20 | 2020-03-23 | 1 |  | 1 | 2020-04-08 |  | -31345 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-03-05 | Online
NSTAR | Mashpee | 2393455 | 2649 | 5000 | PV & Battery | TBD | 2020-02-20 | 2020-03-27 | 26 |  | 26 | 2020-04-14 |  | -31349 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | 2393720 | 2770 | - |  | TBD |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-11-17 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Wareham | 2393736 | 2571 | 8500 | PV |  | 2020-04-13 | 2020-12-21 | 180 | 0 | 180 | 2020-12-21 |  | -31528 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2022-05-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Wareham | 2393742 | 2571 | 8500 | PV |  | 2020-04-13 |  | -31348 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2022-03-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Stoneham | 2393943 | 2180 | 486 | PV | TBD | 2020-03-25 | 2020-03-31 | 4 |  | 4 | 2020-04-15 |  | -31350 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 2393958 | 2719 | 245 | PV | TBD | 2020-03-18 | 2020-03-31 | 9 |  | 9 | 2020-04-15 |  | -31350 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carlisle | 2394000 | 1741 | 19.5 | PV | TBD | 2020-01-17 | 2020-03-31 | 52 |  | 52 | 2020-04-16 |  | -31351 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-21 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Charlestown | 2394014 | 2129 | 4990 | PV | TBD | 2020-03-27 | 2020-03-31 | 2 |  | 2 | 2020-04-15 |  | -31350 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Walpole | 2394160 | 2081 | 1000 | PV | TBD | 2020-03-27 | 2020-04-01 | 3 |  | 3 | 2020-04-20 |  | -31353 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-29 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2394184 | 2740 | 100 | PV | TBD | 2020-03-18 | 2020-03-31 | 9 |  | 9 | 2020-04-16 |  | -31351 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 2394211 | 2740 | 250 | PV | TBD | 2020-03-20 | 2020-03-31 | 7 |  | 7 | 2020-04-16 |  | -31351 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 2394461 | 2743 | 100 | PV | TBD | 2020-03-18 | 2020-03-31 | 9 |  | 9 | 2020-04-20 |  | -31353 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-17 | [7 empty] | 0 |  | 0 |  |  | 2022-05-17 | Online
NSTAR | New Bedford | 2394463 | 2745 | 133.3 | PV | TBD | 2020-03-18 | 2020-03-31 | 9 |  | 9 | 2020-04-20 |  | -31353 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0 |  |  | 2022-02-28 | Online
NSTAR | Boston | 2394534 | 2109 | 750 | CHP | TBD | 2020-04-06 | 2020-04-06 | 0 |  | 0 | 2020-04-20 |  | -31353 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2394648 | 2458 | 25 | PV & Battery | TBD | 2020-03-20 | 2020-03-31 | 7 |  | 7 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-28 | [7 empty] | 0 |  | 0 |  |  | 2020-07-06 | Online
NSTAR | Plympton | 2394682 | 2367 | 4975 | PV |  | 2020-04-20 |  | -31353 | 0 | 0 | 2020-04-25 |  | -31357 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-24 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | New Bedford | 2394787 | 2745 | 100 | PV | TBD | 2020-04-06 | 2020-04-08 | 2 |  | 2 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Falmouth | 2394862 | 2536 | 3500 | PV & Battery | TBD | 2020-03-27 | 2020-04-08 | 8 |  | 8 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 2394867 | 2536 | 3500 | PV |  | 2020-04-21 |  | -31354 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-25 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | South Dennis | 2395010 | 2368 | 112.5 | PV | TBD | 2020-04-30 | 2020-04-30 | 0 |  | 0 | 2020-04-30 |  | -31361 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | East Freetown | 2395036 | 2717 | 149.3 | PV | TBD | 2020-03-26 | 2020-04-06 | 7 |  | 7 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-07-12 | Online
NSTAR | Wareham | 2395041 | 2571 | 216 | PV | TBD | 2020-03-27 | 2020-04-13 | 11 |  | 11 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-28 | Online
NSTAR | Provincetown | 2395067 | 2657 | 495.8 | PV | TBD | 2020-04-08 | 2020-04-08 | 0 |  | 0 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 2395093 | 2462 | 17.6 | PV & Battery | TBD | 2020-04-06 | 2020-04-09 | 3 |  | 3 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2020-12-15 | Online
NSTAR | Boston | 2395099 | 2134 | 40 | PV | TBD | 2020-04-06 | 2020-04-09 | 3 |  | 3 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-07-14 | Online
NSTAR | Canton | 2395122 | 2021 | 15.2 | PV | TBD | 2020-03-18 | 2020-04-09 | 16 |  | 16 | 2020-04-23 |  | -31356 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0 |  |  | 2021-02-04 | Online
NSTAR | Rochester | 2395209 | 2770 | 999 | PV |  | 2020-04-23 | 2020-04-27 | 2 | 0 | 2 | 2020-04-28 |  | -31359 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-11-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Dennis | 2395295 | 2638 | 16.6 | PV & Battery | 4-90-90 | 2020-03-27 | 2020-04-15 | 13 |  | 13 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-06-19 | Online
NSTAR | Acton | 2395297 | 1720 | 240 | PV | TBD | 2020-04-08 | 2020-04-15 | 5 |  | 5 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online
NSTAR | Wareham | 2395408 | 2576 | 470 | PV | TBD | 2020-04-06 | 2020-04-09 | 3 |  | 3 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Marston Mills | 2395414 | 2648 | 16.38 | PV | TBD | 2020-04-01 | 2020-04-09 | 6 |  | 6 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-12-09 | Online
NSTAR | Boston | 2395480 | 2136 | 99.9 | PV | TBD | 2020-04-06 | 2020-04-13 | 5 |  | 5 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 2395483 | 2717 | 149.3 | PV | TBD | 2020-03-09 | 2020-04-10 | 24 |  | 24 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Hyannis | 2395561 | 2601 | 50 | PV | 4-80B-80B | 2020-04-08 |  | -31345 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0
NSTAR | Dorchester | 2395617 | 2118 | 484 | PV | TBD | 2020-04-09 |  | -31346 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2395659 | 1701 | 57.6 | PV | TBD | 2020-04-20 | 2020-04-20 | 0 |  | 0 | 2020-05-04 |  | -31363 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Milton | 2395800 | 2186 | 57.6 | PV | TBD | 2020-02-13 |  | -31306 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2020-10-16 | Online
NSTAR | Brewster | 2395844 | 2631 | 16.28 | PV & Battery | 4-89A-553 | 2020-03-27 | 2020-04-15 | 13 |  | 13 | 2020-04-30 |  | -31361 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-04 | [7 empty] | 0 |  | 0 |  |  | 2020-06-04 | Online
NSTAR | Falmouth | 2395855 | 2536 | 4990 | PV |  | 2020-04-29 | 2020-04-30 | 1 | 0 | 1 | 2020-04-30 |  | -31361 | 169 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-04 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2020-05-01
NSTAR | Plymouth | 2395947 | 2360 | 5466 | PV & Battery | TBD | 2020-03-27 | 2020-04-15 | 13 |  | 13 | 2020-05-04 |  | -31363 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hatchville | 2395965 | 2536 | 3300 | PV |  | 2020-04-30 | 2020-04-30 | 0 | 0 | 0 | 2020-04-30 |  | -31361 | 169 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-07 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2020-05-01
NSTAR | Falmouth | 2395998 | 2536 | 3000 | PV |  | 2020-04-30 | 2020-05-01 | 1 | 0 | 1 |  |  | 0 | 169 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-07 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2020-05-01
NSTAR | Falmouth | 2396002 | 2540 | 958 | PV |  | 2020-04-30 |  | -31361 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-07 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | East Boston | 2396083 | 2128 | 1700 | Steam Turbine |  | 2020-05-01 |  | -31362 | 0 | 0 | 2020-05-01 |  | -31362 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-08 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Gov't
NSTAR | Framingham | 2396140 | 1702 | 400 | PV | TBD | 2020-04-09 |  | -31346 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chilmark | 2396188 | 2535 | 20.95 | PV | TBD | 2020-04-06 | 2020-04-27 | 15 |  | 15 | 2020-05-04 |  | -31363 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0 |  |  | 2021-03-12 | Online
NSTAR | Plymouth | 2396211 | 2360 | 1000 | PV & Battery | TBD | 2020-04-15 | 2020-04-16 | 1 |  | 1 | 2020-05-04 |  | -31363 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Brewster | 2396597 | 2631 | 86.4 | PV | TBD | 2020-05-04 |  | -31363 | 0 | 0 | 2020-05-06 | 2020-05-06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-05-13 | 2020-05-12 | 2020-12-09 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Gov't
NSTAR | Brewster | 2396639 | 2631 | 66.6 | PV | TBD | 2020-03-13 | 2020-04-20 | 26 |  | 26 | 2020-05-06 |  | -31365 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2396686 | 1746 | 14 | Battery | 274-H5 | 2020-02-18 | 2020-04-20 | 44 |  | 44 | 2020-05-06 |  | -31365 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2396845 | 2563 | 133.3 | PV | TBD | 2020-03-17 | 2020-04-20 | 24 |  | 24 | 2020-05-06 |  | -31365 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-21 | [7 empty] | 0 |  | 0
NSTAR | East Falmouth | 2397127 | 2536 | 18.85 | PV | TBD | 2020-04-23 | 2020-04-27 | 2 |  | 2 | 2020-05-11 |  | -31368 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-02 | [7 empty] | 0 |  | 0 |  |  | 2021-03-26 | Online
NSTAR | Oak Bluffs | 2397130 | 2557 | 300 | PV | 4-99-224 | 2020-03-18 | 2020-04-22 | 25 |  | 25 | 2020-05-11 |  | -31368 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-16 | [7 empty] | 0 |  | 0 |  |  | 2022-06-07 | Online
NSTAR | Hopkinton | 2397168 | 1748 | 3900 | PV & Battery | TBD | 2020-02-10 | 2020-04-23 | 53 |  | 53 | 2020-05-08 |  | -31367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Truro | 2397176 | 2652 | 35 | PV | TBD | 2020-05-07 |  | -31366 | 0 | 0 | 2020-06-25 | 2020-06-26 | 1 | 15 | -14 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-07-15 |  | 2020-12-14 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Natick | 2397214 | 1760 | 13.92 | PV | 240-H1 | 2020-03-09 | 2020-04-22 | 32 |  | 32 | 2020-05-08 |  | -31367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-27 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Waltham | 2397225 | 2453 | 80 | PV | TBD | 2020-03-20 | 2020-04-23 | 24 |  | 24 | 2020-05-14 |  | -31371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-16 | [7 empty] | 0 |  | 0 |  |  | 2023-03-14 | Online
NSTAR | Stoneham | 2397255 | 2180 | 15.2 | PV | TBD | 2020-03-17 | 2020-03-27 | 8 |  | 8 | 2020-05-08 |  | -31367 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dover | 2397442 | 2030 | 17.7 | PV | 456-H3 | 2020-04-30 | 2020-04-30 | 0 |  | 0 | 2020-05-11 |  | -31368 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-09-14 | Online
NSTAR | Waltham | 2397603 | 2453 | 46 | PV | TBD | 2020-04-16 | 2020-04-27 | 7 |  | 7 | 2020-05-14 |  | -31371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0
NSTAR | Provincetown | 2397610 | 2657 | 54 | PV | TBD | 2020-04-06 | 2020-04-23 | 13 |  | 13 | 2020-05-14 |  | -31371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2020-11-23 | Online
NSTAR | Framingham | 2397729 | 1702 | 240 | PV | TBD | 2020-04-23 | 2020-04-27 | 2 |  | 2 | 2020-05-14 |  | -31371 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 2397818 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2397824 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2397836 | 1760 | 330 | PV |  | 2020-05-12 |  | -31369 | 0 | 0 | 2020-05-18 |  | -31373 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-17 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2022-04-25 | Online | Private
NSTAR | Holliston | 2397865 | 1746 | 200 | PV |  | 2020-05-13 | 2020-05-13 | 0 | 0 | 0 | 2020-05-13 | 2020-05-13 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-13 |  | 2020-12-18 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2021-03-19 | Online | Private
NSTAR | Canton | 2397898 | 2021 | 499 | PV & Battery | TBD | 2020-04-29 | 2020-04-30 | 1 |  | 1 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2398079 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Harwich | 2398156 | 2645 | 22.2 | PV | 4-95A-95A | 2020-04-27 | 2020-04-29 | 2 |  | 2 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2398168 | 2747 | 15.2 | PV | 2-532-532 | 2020-03-16 | 2020-04-30 | 33 |  | 33 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-05-28 | [7 empty] | 0 |  | 0 |  |  | 2021-05-21 | Online
NSTAR | Natick | 2398175 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2398227 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-04-29 |  | -31360 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | East Falmouth | 2398257 | 2536 | 500 | PV | TBD | 2020-04-27 | 2020-04-30 | 3 |  | 3 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2398274 | 1748 | 24.28 | PV | TBD | 2020-04-09 | 2020-04-29 | 14 |  | 14 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Cambridge | 2398561 | 2138 | 200 | PV | TBD | 2020-03-27 | 2020-04-30 | 24 |  | 24 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Brewster | 2398609 | 2631 | 4999 | PV & Battery | TBD | 2020-04-30 | 2020-04-30 | 0 |  | 0 | 2020-05-18 |  | -31373 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lincoln | 2398639 | 1773 | 43.2 | PV | 240-H1 | 2020-04-15 | 2020-05-04 | 13 |  | 13 | 2020-05-20 |  | -31375 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2022-09-27 | Online
NSTAR | Somerville | 2398711 | 2143 | 211 | PV | TBD | 2020-05-05 | 2020-05-08 | 3 |  | 3 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-03-11 | Online
NSTAR | Lincoln | 2398773 | 1773 | 86.4 | PV | TBD | 2020-04-15 | 2020-05-04 | 13 |  | 13 | 2020-05-20 |  | -31375 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2022-09-27 | Online
NSTAR | South Dartmouth | 2398833 | 2748 | 20.8 | PV & Battery | 2-53-65 | 2020-04-30 | 2020-05-05 | 3 |  | 3 | 2020-05-20 |  | -31375 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2398880 | 2360 | 7.6 | PV & Battery | TBD | 2020-04-29 | 2020-04-29 | 0 |  | 0 | 2020-04-29 |  | -31360 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-23 | [7 empty] | 0 |  | 0 |  |  | 2020-09-14 | Online
NSTAR | Framingham | 2398893 | 1701 | - |  | TBD | 2020-05-20 |  | -31375 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-28 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Holliston | 2399007 | 1746 | 300 | PV | TBD | 2020-04-20 | 2020-05-13 | 17 |  | 17 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Freetown | 2399041 | 2717 | 25 | PV | TBD | 2020-05-07 | 2020-05-07 | 0 |  | 0 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 2399048 | 2744 | 15.2 | PV | TBD | 2020-05-05 | 2020-05-13 | 6 |  | 6 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-02-09 | Online
NSTAR | Framingham | 2399085 | 1702 | 22 | PV | TBD | 2020-05-21 |  | -31376 | 0 | 0 | 2020-05-26 | 2020-06-24 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-29 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Duxbury | 2399108 | 2332 | 25 | PV & Battery | TBD | 2020-04-29 | 2020-05-08 | 7 |  | 7 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 2399178 | 2601 | 460 | PV | 4-80B-80B | 2020-04-16 | 2020-04-20 | 2 |  | 2 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0
NSTAR | Brewster | 2399192 | 2631 | 4999 | PV & Battery | TBD | 2020-05-05 | 2020-05-08 | 3 |  | 3 | 2020-05-27 |  | -31380 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Dennis | 2399437 | 2660 | 15.2 | PV | TBD | 2020-04-01 | 2020-05-18 | 33 |  | 33 | 2020-06-16 |  | -31394 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Natick | 2399566 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Natick | 2399596 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Harwich | 2399599 | 2645 | 240 | PV | TBD | 2020-04-29 | 2020-05-13 | 10 |  | 10 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-21 | [7 empty] | 0 |  | 0
NSTAR | Natick | 2399607 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Hyannis | 2399725 | 2601 | 73.3 | PV | TBD | 2020-04-06 | 2020-05-13 | 27 |  | 27 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Hyannis | 2399742 | 2601 | 60 | PV | TBD | 2020-04-08 | 2020-05-13 | 25 |  | 25 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2022-02-28 | Online
NSTAR | Plymouth | 2399743 | 2360 | 17.6 | PV | 3-72-940 | 2020-05-08 | 2020-05-13 | 3 |  | 3 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-23 | [7 empty] | 0 |  | 0 |  |  | 2020-11-04 | Online
NSTAR | Cambridge | 2399827 | 2141 | 60 | CHP | TBD | 2020-02-04 | 2020-05-13 | 71 |  | 71 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-08 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online
NSTAR | Acusnet | 2399839 | 2743 | 5000 | PV | TBD | 2019-09-13 | 2020-05-13 | 173 |  | 173 | 2020-05-29 |  | -31382 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | 2399904 | 2030 | 35.2 | PV | TBD | 2020-05-05 | 2020-05-13 | 6 |  | 6 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-19 | [7 empty] | 0 |  | 0 |  |  | 2021-03-09 | Online
NSTAR | Sandwich | 2400107 | 2653 | 150 | PV | TBD | 2020-05-08 | 2020-05-18 | 6 |  | 6 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-24 | [7 empty] | 0 |  | 0 |  |  | 2021-03-10 | Online
NSTAR | Freetown | 2400205 | 2717 | 4990 | PV & Battery | TBD | 2020-04-30 | 2020-05-20 | 14 |  | 14 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mashpee | 2400260 | 2649 | 1490 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | 10 |  | 10 | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plympton | 2400919 | 2367 | 149.3 | PV | TBD | 2020-05-20 | 2020-05-20 | 0 |  | 0 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 2400943 | 2653 | 499 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | 10 |  | 10 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Online
NSTAR | Natick | 2400946 | 1760 | 100.8 | PV | TBD | 2020-04-22 | 2020-04-29 | 5 |  | 5 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-15 | Online
NSTAR | Mashpee | 2400979 | 2649 | 2075 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | 10 |  | 10 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Orleans | 2401009 | 2653 | 200 | PV | TBD | 2020-04-30 | 2020-05-18 | 12 |  | 12 | 2020-06-04 |  | -31386 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-21 | [7 empty] | 0 |  | 0
NSTAR | West Roxbury | 2401149 | 2132 | 149.8 | PV | TBD | 2020-04-27 | 2020-05-26 | 21 |  | 21 | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-14 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 2401235 | 2649 | 730 | PV & Battery | TBD | 2020-05-04 | 2020-05-18 | 10 |  | 10 | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marion | 2401247 | 2738 | 700 | PV & Battery | TBD | 2020-04-30 | 2020-05-18 | 12 |  | 12 | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Sandwich | 2401361 | 2537 | 499 | PV | TBD | 2020-05-04 | 2020-05-20 | 12 |  | 12 | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2401405 | 2717 | 4990 | PV & Battery | TBD | 2020-04-30 | 2020-05-20 | 14 |  | 14 | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2401687 | 2746 | 499 | PV | TBD | 2020-05-18 | 2020-05-20 | 2 |  | 2 | 2020-06-10 |  | -31390 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-05 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 2401948 | 1746 | 216 | PV | TBD | 2020-05-15 | 2020-05-26 | 7 |  | 7 | 2020-06-10 |  | -31390 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2021-04-01 | Online
NSTAR | Lincoln | 2401979 | 1773 | 22.6 | PV & Battery | TBD | 2020-05-18 | 2020-05-28 | 8 |  | 8 | 2020-06-12 |  | -31392 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Chatham | 2402094 | 2633 | 22.32 | PV | TBD | 2020-05-26 | 2020-05-28 | 2 |  | 2 | 2020-06-11 |  | -31391 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-06 | [7 empty] | 0 |  | 0 |  |  | 2020-09-10 | Online
NSTAR | Falmouth | 2402100 | 2540 | 133 | PV |  | 2020-06-11 | 2020-06-15 | 2 | 0 | 2 | 2020-06-15 | 2020-06-15 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-15 | 2020-07-06 | 2020-12-15 | No | EXP | 30 |  |  | 0 |  | 0 |  |  | 2020-08-19 | Online | Private
NSTAR | Waltham | 2402126 | 2451 | 375 | PV | TBD | 2020-05-28 | 2020-05-28 | 0 |  | 0 | 2020-06-12 |  | -31392 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-29 | [7 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2402135 | 2747 | 149.3 | PV | TBD | 2020-05-28 | 2020-05-28 | 0 |  | 0 | 2020-06-12 |  | -31392 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-23 | [7 empty] | 0 |  | 0
NSTAR | West Roxbury | 2402181 | 2132 | 226.9 | PV | TBD | 2020-04-27 | 2020-05-26 | 21 |  | 21 | 2020-06-16 |  | -31394 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 2402255 | 1721 | 10 | PV & Battery | TBD | 2020-05-26 | 2020-06-01 | 4 |  | 4 | 2020-06-16 |  | -31394 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  | 2020-10-15 | Online
NSTAR | Kingston | 2402374 | 2364 | 499 | PV |  | 2020-06-15 | 2020-06-16 | 1 | 0 | 1 | 2020-06-30 |  | -31404 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-20 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Centerville | 2402410 | 2632 | 7.6 | PV | 4-82-508 | 2020-05-18 | 2020-06-03 | 12 |  | 12 | 2020-06-16 |  | -31394 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-24 | [7 empty] | 0 |  | 0 |  |  | 2021-04-21
NSTAR | Carver | 2402730 | 2330 | 200 | PV | TBD | 2020-05-15 | 2020-06-03 | 13 |  | 13 | 2020-06-16 |  | -31394 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 2402767 | 2649 | 10 | PV & Battery | 4-452-452 | 2020-05-15 | 2020-06-03 | 13 |  | 13 | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2020-08-05 | Online
NSTAR | New Bedford | 2402897 | 2746 | 499 | PV | TBD | 2020-05-28 | 2020-06-01 | 2 |  | 2 | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 2402933 | 2130 | 1489 | PV |  | 2020-06-17 | 2020-06-19 | 2 | 0 | 2 | 2020-06-29 |  | -31403 | 128 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-15 | No |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2020-06-30
NSTAR | West Wareham | 2402967 | 2576 | 10 | PV & Battery | 3-85-85 | 2020-05-28 | 2020-06-03 | 4 |  | 4 | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Sandwich | 2403120 | 2563 | 90 | PV & Battery | TBD | 2020-05-28 | 2020-06-03 | 4 |  | 4 | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0
NSTAR | Woburn | 2403255 | 1801 | 63.3 | PV | TBD | 2020-06-01 | 2020-06-04 | 3 |  | 3 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 2403259 | 2421 | 25.5 | PV & Battery | TBD | 2020-06-03 | 2020-06-05 | 2 |  | 2 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  | 2021-01-08 | Online
NSTAR | Fairhaven | 2403269 | 2719 | 469.8 | PV | TBD | 2020-03-16 | 2020-06-05 | 59 |  | 59 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-29 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Newton | 2403398 | 2459 | 19.84 | PV & Battery | 443-02 | 2020-06-05 | 2020-06-05 | 0 |  | 0 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-06-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Jamaica Plain | 2403403 | 2130 | 10 | PV & Battery | 284-1300H1 | 2020-05-20 | 2020-06-08 | 13 |  | 13 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 2403438 | 2673 | 232 | PV | TBD | 2020-05-18 | 2020-06-08 | 15 |  | 15 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Bedford | 2403475 | 1730 | 31 | PV & Battery | TBD | 2020-06-01 | 2020-06-08 | 5 |  | 5 | 2020-06-23 |  | -31399 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-09-20 | Online
NSTAR | Wareham | 2403535 | 2571 | 149.3 | PV | TBD | 2020-06-10 | 2020-06-10 | 0 |  | 0 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-07-21 | Online
NSTAR | Centerville | 2403564 | 2632 | 15.2 | PV | TBD | 2020-04-20 | 2020-06-18 | 43 |  | 43 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-07 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | West Wareham | 2403572 | 2576 | 25 | PV | TBD | 2020-06-10 | 2020-06-10 | 0 |  | 0 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 2403584 | 2714 | 2958 | PV & Battery | 2-543-543 | 2020-02-20 | 2020-06-08 | 77 |  | 77 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2403624 | 2451 | 144 | PV | TBD | 2020-04-15 | 2020-05-26 | 29 |  | 29 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-01-21 | Online
NSTAR | Provincetown | 2403670 | 2567 | 22.89 | PV & Battery | 4-96-675 | 2020-06-03 | 2020-06-10 | 5 |  | 5 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-13 | [7 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online
NSTAR | Forestdale | 2403701 | 2644 | - |  | TBD | 2020-06-24 |  | -31400 | 0 | 0 | 2020-06-30 | 2020-07-13 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-08-12 | 2020-09-14 | 2020-12-02 | No | EXP | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Medway | 2403742 | 2053 | 25.75 | PV | TBD | 2019-10-09 | 2020-06-10 | 175 |  | 175 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sudbury | 2403835 | 1776 | 200 | PV | TBD | 2020-04-16 | 2020-06-10 | 39 |  | 39 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2022-05-13 | Online
NSTAR | Plymouth | 2403991 | 2360 | 180 | PV | TBD | 2020-05-18 | 2020-06-11 | 18 |  | 18 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0
NSTAR | Dennis | 2404237 | 2660 | 3176 | PV | TBD | 2020-04-01 | 2020-06-11 | 51 |  | 51 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Barnstable | 2404275 | 2630 | 3146 | PV & Battery | TBD | 2019-05-26 | 2020-06-15 | 276 |  | 276 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Orleans | 2404297 | 2643 | 10 | PV & Battery | 4-95B-628 | 2020-05-28 | 2020-06-15 | 12 |  | 12 | 2020-06-29 |  | -31403 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-13 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | Boston | 2404393 | 2126 | 129.6 | PV | TBD | 2020-06-08 | 2020-06-15 | 5 |  | 5 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-08 | [7 empty] | 0 |  | 0
NSTAR | Millis | 2404399 | 2054 | 2500 | PV & Battery | TBD | 2020-06-03 | 2020-06-15 | 8 |  | 8 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0
NSTAR | Brewster | 2404421 | 2631 | 10 | PV & Battery | 4-95A-597 | 2020-06-15 | 2020-06-29 | 10 |  | 10 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-23 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | Wayland | 2404425 | 1778 | 10 | PV & Battery | TBD | 2020-06-15 | 2020-06-29 | 10 |  | 10 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2404430 | 1748 | 15.2 | PV | 126-H1 | 2020-06-02 | 2020-06-29 | 19 |  | 19 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-21 | [7 empty] | 0 |  | 0 |  |  | 2021-05-27 | Online
NSTAR | Framingham | 2404459 | 1702 | 61.2 | PV | TBD | 2020-04-30 | 2020-06-10 | 29 |  | 29 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-09 | [7 empty] | 0 |  | 0 |  |  | 2021-09-27 | Online
NSTAR | Needham | 2404602 | 2492 | 19.84 | PV | 148-H2 | 2020-06-22 | 2020-06-22 | 0 |  | 0 | 2020-07-06 |  | -31408 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2404607 | 1746 | 21 | PV & Battery | 274-H5 | 2020-06-10 | 2020-06-23 | 9 |  | 9 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  | 2021-05-07 | Online
NSTAR | Hyannis | 2404659 | 2601 | 999 | PV & Battery | TBD | 2020-02-07 | 2020-06-11 | 89 |  | 89 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | 2404678 | 2576 | 25 | PV | TBD | 2020-06-10 | 2020-06-11 | 1 |  | 1 | 2020-07-01 |  | -31405 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-03 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 2404735 | 2476 | 17.6 | PV & Battery | TBD | 2020-06-10 | 2020-06-15 | 3 |  | 3 | 2020-07-06 |  | -31408 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0 |  |  | 2020-12-11 | Online
NSTAR | Jamaica Plain | 2404933 | 2130 | 1360 | PV | TBD | 2020-04-16 | 2020-06-02 | 33 |  | 33 | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | 2404942 | 2143 | 22.8 | PV | TBD | 2020-06-15 | 2020-06-22 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-15 | [7 empty] | 0 |  | 0 |  |  | 2021-06-16 | Online
NSTAR | Cambridge | 2405400 | 2139 | 16 | PV & Battery | 817-03 | 2020-06-15 | 2020-06-22 | 5 |  | 5 | 2020-07-06 |  | -31408 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2405461 | 1701 | 365 | PV | TBD | 2020-06-01 | 2020-07-06 | 25 |  | 25 | 2020-07-06 |  | -31408 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-09 | [7 empty] | 0 |  | 0
NSTAR | Truro | 2405858 | 2652 | 4107 | PV & Battery | TBD | 2020-06-23 | 2020-06-23 | 0 |  | 0 | 2020-07-13 |  | -31413 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 2406412 | 1748 | 250 | PV | TBD | 2020-07-01 | 2020-07-01 | 0 |  | 0 | 2020-07-15 |  | -31415 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 2406453 | 2492 | 25 | PV & Battery | TBD | 2020-06-15 | 2020-07-07 | 16 |  | 16 | 2020-07-14 |  | -31414 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2020-12-16 | Online
NSTAR | Waban | 2406455 | 2468 | 19.84 | PV & Battery | 292-H12 | 2020-06-23 | 2020-06-23 | 0 |  | 0 | 2020-07-14 |  | -31414 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 2406457 | 2186 | 21.67 | PV & Battery | 4303 | 2020-06-10 | 2020-06-23 | 9 |  | 9 | 2020-07-14 |  | -31414 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-07 | [7 empty] | 0 |  | 0
NSTAR | Sudbury | 2406653 | 1776 | 25 | PV & Battery | TBD | 2020-06-15 | 2020-06-29 | 10 |  | 10 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2406660 | 1701 | 17.6 | PV & Battery | TBD | 2020-06-15 | 2020-06-15 | 0 |  | 0 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2021-07-01 | Online
NSTAR | Bedford | 2406661 | 1730 | 21 | PV & Battery | 322-1397H1 | 2020-06-23 | 2020-06-29 | 4 |  | 4 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Westport | 2406662 | 2790 | 19 | PV | 2-523-523 | 2020-06-09 | 2020-06-29 | 14 |  | 14 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-27 | [7 empty] | 0 |  | 0 |  |  | 2021-04-05 | Online
NSTAR | Waltham | 2406861 | 2452 | 25 | PV & Battery | TBD | 2020-06-11 | 2020-06-29 | 12 |  | 12 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  | 2020-11-23 | Online
NSTAR | Somerville | 2406866 | 2145 | 23 | PV |  | 2020-07-15 | 2020-07-20 | 3 | 0 | 3 | 2020-08-04 | 2020-08-21 | 13 | 0 | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-25 | 2020-09-10 | 2020-12-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Buzzards Bay | 2407059 | 2532 | 133.2 | PV | TBD | 2020-04-20 | 2020-06-30 | 51 |  | 51 | 2020-07-20 |  | -31418 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Sandwich | 2407070 | 2563 | 499 | PV |  | 2020-07-16 | 2020-07-20 | 2 | 0 | 2 | 2020-08-04 |  | -31429 | 100 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-15 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2020-08-10
NSTAR | Hopkinton | 2407210 | 1748 | 480 | PV |  | 2020-07-17 | 2020-07-20 | 1 | 0 | 1 | 2020-07-22 |  | -31420 | 104 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 |  | 2020-12-15 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2020-08-04
NSTAR | Lexington | 2407464 | 2421 | 19.86 | PV & Battery | 320-H2 | 2020-07-03 | 2020-07-03 | 0 |  | 0 | 2020-07-21 |  | -31419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wellfleet | 2407474 | 2667 | 2000 | PV & Battery | TBD | 2020-07-01 | 2020-07-02 | 1 |  | 1 | 2020-07-21 |  | -31419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0
NSTAR | Oak Bluffs | 2407481 | 2557 | 22 | PV & Battery | TBD | 2020-06-29 | 2020-07-01 | 2 |  | 2 | 2020-07-21 |  | -31419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-28 | [7 empty] | 0 |  | 0
NSTAR | Medway | 2407609 | 2053 | 1476 | PV & Battery | TBD | 2020-07-06 | 2020-07-09 | 3 |  | 3 | 2020-07-21 |  | -31419 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sherborn | 2407667 | 1770 | 17.4 | PV | TBD | 2020-07-10 | 2020-07-10 | 0 |  | 0 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-09 | [7 empty] | 0 |  | 0 |  |  | 2020-11-12 | Online
NSTAR | Acton | 2407706 | 1720 | 15 | PV & Battery | 416-H4 | 2020-07-21 |  | -31419 | 0 | 0 | 2020-08-06 | 2020-11-12 | 70 | 0 | 70 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-21 |  | 2020-12-30 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | New Bedford | 2407717 | 2745 | 500 | PV & Battery | TBD | 2020-06-01 | 2020-07-13 | 30 |  | 30 | 2020-07-22 |  | -31420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-11 | [7 empty] | 0 |  | 0
NSTAR | Newton | 2407737 | 2460 | 115.2 | PV | TBD | 2020-07-06 | 2020-07-07 | 1 |  | 1 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Online
NSTAR | Newton | 2407743 | 2459 | 20 | PV & Battery | TBD | 2020-06-23 | 2020-07-01 | 6 |  | 6 | 2020-07-22 |  | -31420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-21 | [7 empty] | 0 |  | 0 |  |  | 2021-02-10 | Online
NSTAR | Mattapoisett | 2407746 | 2739 | 15.2 | PV | TBD | 2020-07-01 | 2020-07-01 | 0 |  | 0 | 2020-07-22 |  | -31420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-03 | [7 empty] | 0 |  | 0 |  |  | 2021-01-19 | Online
NSTAR | Hyannis | 2407747 | 2601 | 24.07 | PV | TBD | 2020-07-06 | 2020-07-07 | 1 |  | 1 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Somerville | 2407835 | 2143 | 22.8 | PV | TBD | 2020-06-02 | 2020-07-07 | 25 |  | 25 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-07-29 | [7 empty] | 0 |  | 0 |  |  | 2021-08-04 | Online
NSTAR | Holliston | 2407949 | 2532 | 15.2 | PV | TBD | 2020-07-14 | 2020-07-14 | 0 |  | 0 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chestnut Hill | 2407979 | 2467 | 36 | PV & Battery | 467-H12 | 2020-07-01 | 2020-07-02 | 1 |  | 1 | 2020-07-28 |  | -31424 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-30 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 2408018 | 1701 | 22 | PV & Battery | TBD | 2020-07-01 | 2020-07-03 | 2 |  | 2 | 2020-07-27 |  | -31423 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2022-01-06 | Online
NSTAR | Fairhaven | 2408049 | 2719 | 99 | PV |  | 2020-07-23 | 2020-07-27 | 2 | 0 | 2 | 2020-08-04 | 2020-08-19 | 11 | 0 | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 |  | 2020-10-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Wayland | 2408090 | 1778 | 17.6 | PV & Battery | TBD | 2020-07-14 | 2020-07-14 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-28 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Framingham | 2408258 | 1701 | 245 | PV & Battery | TBD | 2020-07-15 | 2020-07-17 | 2 |  | 2 | 2020-07-28 |  | -31424 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-10 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 2408289 | 2719 | 99.09 | PV | TBD | 2020-07-10 | 2020-07-14 | 2 |  | 2 | 2020-07-28 |  | -31424 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Wellfleet | 2408369 | 2667 | - |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 2408400 | 1746 | 499 | PV | TBD | 2020-07-21 | 2020-07-21 | 0 |  | 0 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 2408483 | 2360 | 1000 | PV & Battery | TBD | 2020-06-30 | 2020-07-02 | 2 |  | 2 | 2020-07-28 |  | -31424 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 2408542 | 1730 | 25 | PV & Battery | 533-H5 | 2020-07-22 | 2020-07-22 | 0 |  | 0 | 2020-08-07 |  | -31432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Needham | 2408568 | 2492 | 17 | PV & Battery | TBD | 2020-07-06 | 2020-07-07 | 1 |  | 1 | 2020-07-30 |  | -31426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2021-02-02 | Online
NSTAR | Ashland | 2408580 | 1721 | 7 | PV & Battery | 519-175H1 | 2020-06-05 | 2020-07-13 | 26 |  | 26 | 2020-07-30 |  | -31426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Natick | 2408582 | 1760 | 43.2 | PV | TBD | 2020-05-28 | 2020-07-07 | 28 |  | 28 | 2020-07-30 |  | -31426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Rochester | 2408783 | 2770 | 4999 | PV & Battery | TBD | 2020-07-07 | 2020-07-13 | 4 |  | 4 | 2020-07-30 |  | -31426 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Newton | 2408881 | 2459 | 10 | PV | 1709 | 2020-07-30 | 2020-09-10 | 30 | 0 | 30 | 2020-09-10 |  | -31456 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 |  | 2020-12-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  | 2022-02-15 | Online | Private
NSTAR | Marshfield | 2409029 | 2050 | 7.6 | PV | 3-24B-915 | 2020-05-26 | 2020-07-07 | 30 |  | 30 | 2020-08-03 |  | -31428 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-12 | [7 empty] | 0 |  | 0 |  |  | 2021-10-25 | Online
NSTAR | Acton | 2409041 | 1702 | 15.6 | PV & Battery | 416-H5 | 2020-07-11 | 2020-07-15 | 3 |  | 3 | 2020-08-03 |  | -31428 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | North Cambridge | 2409461 | 2140 | 14 | PV & Battery | 825-27 | 2020-06-11 | 2020-07-16 | 25 |  | 25 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-11-17 | Online
NSTAR | West Wareham | 2409477 | 2576 | 7.6 | PV | TBD | 2020-07-01 | 2020-07-16 | 11 |  | 11 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-02-22 | Online
NSTAR | Orleans | 2409513 | 2145 | 245 | PV | TBD | 2020-07-15 | 2020-07-16 | 1 |  | 1 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Holliston | 2409582 | 1746 | 250 | PV | TBD | 2020-07-08 | 2020-07-14 | 4 |  | 4 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2409588 | 2115 | 180 | PV |  | 2020-08-03 | 2020-08-04 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-31 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Canton | 2409650 | 2021 | 21.4 | PV & Battery | TBD | 2020-07-20 | 2020-07-20 | 0 |  | 0 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-07-26 | Online
NSTAR | Plymouth | 2409661 | 2360 | 10 | PV & Battery | 3-14-934 | 2020-07-15 | 2020-07-15 | 0 |  | 0 | 2020-08-04 |  | -31429 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-01-23 | Online
NSTAR | Hopkinton | 2409830 | 1748 | 5000 | PV & Battery | TBD | 2020-07-15 | 2020-07-15 | 0 |  | 0 | 2020-08-07 |  | -31432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | 2409880 | 1803 | 95.5 | PV | TBD | 2020-07-22 | 2020-07-23 | 1 |  | 1 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 2409915 | 2649 | 245 | PV & Battery | TBD | 2020-08-07 |  | -31432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-05 | [7 empty] | 0 |  | 0
NSTAR | Boston | 2409919 | 2128 | 57.6 | PV | TBD | 2020-08-07 |  | -31432 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2021-03-22 | Online
NSTAR | Burlington | 2409940 | 1803 | 20.4 | PV & Battery | 346-1395H1 | 2020-06-29 | 2020-07-28 | 21 |  | 21 | 2020-08-11 |  | -31434 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Winchester | 2409982 | 1890 | 18 | PV & Battery |  | 2020-08-07 | 2020-08-10 | 1 | 0 | 1 | 2020-08-13 | 2020-08-13 | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-25 | 2020-08-31 | 2020-12-15 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  | 2022-02-03 | Online | Private
NSTAR | Lexington | 2409998 | 2420 | 20 | PV & Battery | TBD | 2020-07-15 | 2020-07-20 | 3 |  | 3 | 2020-08-10 |  | -31433 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  | 2020-12-30 | Online
NSTAR | Fairhaven | 2410005 | 2719 | 750 | PV | TBD | 2020-07-22 | 2020-07-22 | 0 |  | 0 | 2020-08-10 |  | -31433 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | 2410106 | 2563 | 7.6 | PV | 4-81B-443 | 2020-06-23 | 2020-07-28 | 25 |  | 25 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Boston | 2410160 | 2115 | 180 | PV | TBD | 2020-07-28 | 2020-07-29 | 1 |  | 1 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 2410254 | 2649 | 499 | PV & Battery | TBD | 2020-07-27 | 2020-08-03 | 5 |  | 5 | 2020-08-18 |  | -31439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2410310 | 2364 | 133.2 | PV | TBD | 2020-07-29 | 2020-08-03 | 3 |  | 3 | 2020-08-18 |  | -31439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Online
NSTAR | Mattapoisett | 2410489 | 2739 | 5000 | PV & Battery | TBD | 2020-07-29 | 2020-08-04 | 4 |  | 4 | 2020-08-17 |  | -31438 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 2410632 | 2536 | 4998 | PV & Battery | TBD | 2020-07-06 | 2020-07-13 | 5 |  | 5 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 2410727 | 2021 | 249.8 | PV | 470-H7 | 2020-07-29 | 2020-07-29 | 0 |  | 0 | 2020-07-29 |  | -31425 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-08 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Natick | 2410746 | 1760 | 10 | PV | TBD | 2020-07-21 | 2020-07-21 | 0 |  | 0 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 2410747 | 2494 | 19.57 | PV & Battery | 292-H4 | 2020-07-22 | 2020-07-22 | 0 |  | 0 | 2020-08-14 |  | -31437 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 2410763 | 2452 | 7.6 | PV | 450-H6 | 2020-08-04 | 2020-08-06 | 2 |  | 2 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0 |  |  | 2021-10-20 | Online
NSTAR | Wareham | 2410816 | 2576 | - |  | TBD | 2020-08-14 |  | -31437 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2030-12-20 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | Withdrawn | Private
NSTAR | Brookline | 2410954 | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 | 7 |  | 7 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | 2410982 | 1760 | 497 | PV | 240-H1 | 2020-08-17 | 2020-09-29 | 31 | 0 | 31 | 2020-09-29 | 2020-10-07 | 6 | 0 | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-01 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Woburn | 2411000 | 1801 | 15.2 | PV | TBD | 2020-06-08 | 2020-07-28 | 36 |  | 36 | 2020-08-17 |  | -31438 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-08-20 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 2411056 | 1803 | 500 | PV |  | 2020-08-17 | 2020-08-17 | 0 | 0 | 0 | 2020-08-25 |  | -31444 | 65 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-30 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2020-09-30
NSTAR | Falmouth | 2411073 | 2540 | 15.2 | PV | 4-76-436 | 2020-06-15 | 2020-07-28 | 31 |  | 31 | 2020-08-18 |  | -31439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 2411107 | 2536 | 4998 | PV & Battery | TBD | 2020-07-06 | 2020-07-30 | 18 |  | 18 | 2020-08-18 |  | -31439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 2411131 | 1730 | 25 | PV & Battery | TBD | 2020-07-22 | 2020-08-03 | 8 |  | 8 | 2020-08-18 |  | -31439 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2020-12-24 | Online
NSTAR | Brookline | 2411200 | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 | 7 |  | 7 | 2020-08-26 |  | -31445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Stoneham | 2411309 | 2180 | 10 | PV & Battery | 375-H8 | 2020-07-22 | 2020-08-03 | 8 |  | 8 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-09 | [7 empty] | 0 |  | 0 |  |  | 2021-02-08 | Online
NSTAR | Framingham | 2411344 | 1702 | 573 | PV |  | 2020-08-18 | 2020-09-09 | 16 | 0 | 16 | 2020-09-14 |  | -31458 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 |  | 2020-12-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Gov't
NSTAR | Hyannis | 2411466 | 2601 | 186 | PV | TBD | 2020-08-06 | 2020-08-06 | 0 |  | 0 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-22 | [7 empty] | 0 |  | 0
NSTAR | Falmouth | 2411491 | 2536 | - | PV & Battery | TBD | 2020-07-06 | 2020-07-03 | -3 |  | 0 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 2411492 | 2421 | 361.5 | PV | TBD | 2020-07-29 | 2020-08-04 | 4 |  | 4 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-23 | [7 empty] | 0 |  | 0 |  |  | 2022-01-19 | Online
NSTAR | Falmouth | 2411634 | 2540 | 66.6 | PV | TBD | 2020-08-03 | 2020-08-07 | 4 |  | 4 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2021-03-18 | Online
NSTAR | Falmouth | 2411656 | 2540 | 18.7 | PV & Battery | TBD | 2020-07-15 | 2020-08-03 | 13 |  | 13 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0 |  |  | 2020-10-23 | Online
NSTAR | Wayland | 2411668 | 1778 | 23.01 | PV | TBD | 2020-07-22 | 2020-08-07 | 12 |  | 12 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-08-06 | Online
NSTAR | North Falmouth | 2411670 | 2556 | 18 | PV & Battery | TBD | 2020-08-04 | 2020-08-10 | 4 |  | 4 | 2020-08-24 |  | -31443 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-02 | [7 empty] | 0 |  | 0
NSTAR | Brewster | 2411939 | 2631 | 57.6 | PV | TBD | 2020-07-22 | 2020-08-06 | 11 |  | 11 | 2020-08-26 |  | -31445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Brookline | 2411957 | 2445 | 75 | CHP | TBD | 2020-07-28 | 2020-08-06 | 7 |  | 7 | 2020-08-26 |  | -31445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online
NSTAR | Mashpee | 2411961 | 2649 | 750 | PV & Battery | TBD | 2020-07-27 | 2020-08-06 | 8 |  | 8 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 2412130 | 2747 | 15.2 | PV | TBD | 2020-07-27 | 2020-08-07 | 9 |  | 9 | 2020-08-26 |  | -31445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 2412133 | 2050 | 15.2 | PV | TBD | 2020-08-06 | 2020-08-07 | 1 |  | 1 | 2020-08-26 |  | -31445 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0
NSTAR | Westwood | 2412211 | 2090 | 3104.5 | PV & Battery | TBD | 2020-08-07 | 2020-08-11 | 2 |  | 2 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 2412218 | 2125 | 19 | PV & Battery | 483-01 | 2020-07-29 | 2020-08-11 | 9 |  | 9 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-14 | [7 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Onset | 2412247 | 2558 | 17.6 | PV | TBD | 2020-06-23 | 2020-08-13 | 37 |  | 37 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0 |  |  | 2021-04-05 | Online
NSTAR | Fairhaven | 2412322 | 2719 | 66.6 | PV | TBD | 2020-08-10 | 2020-08-10 | 0 |  | 0 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2021-07-28 | Online
NSTAR | Holliston | 2412335 | 1746 | 20 | PV | TBD | 2020-08-26 | 2020-08-31 | 3 | 0 | 3 | 2020-09-14 |  | -31458 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-12-01 | TBD | TBD | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Falmouth | 2412337 | 2540 | 122 | PV | TBD | 2020-08-06 | 2020-08-11 | 3 |  | 3 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2022-09-15 | Online
NSTAR | Pocasset | 2412341 | 2559 | 999 | PV & Battery | TBD | 2020-08-12 | 2020-08-12 | 0 |  | 0 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 2412477 | 2601 | 250 | PV | TBD | 2020-08-12 | 2020-08-12 | 0 |  | 0 | 2020-08-28 |  | -31447 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-13 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 2412478 | 2421 | 133.3 | PV | TBD | 2020-05-05 | 2020-08-13 | 72 |  | 72 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-30 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 2412543 | 2180 | 15.2 | PV | TBD | 2020-07-22 | 2020-08-14 | 17 |  | 17 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-03 | [7 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Lexington | 2412545 | 2421 | 15.2 | PV | TBD | 2020-08-12 | 2020-08-14 | 2 |  | 2 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0
NSTAR | Canton | 2412573 | 2021 | 2660 | PV & Battery | TBD | 2020-07-29 | 2020-08-17 | 13 |  | 13 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Cambridge | 2412636 | 2140 | 19.12 | PV | TBD | 2020-08-12 | 2020-08-17 | 3 |  | 3 | 2020-09-09 |  | -31455 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-11 | [7 empty] | 0 |  | 0 |  |  | 2021-09-08 | Online
NSTAR | New Bedford | 2412695 | 2746 | 250 | PV | TBD | 2019-12-30 | 2020-01-21 | 16 |  | 16 | 2020-09-07 |  | -31453 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-28 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 2412699 | 2026 | 4990 | PV |  | 2020-08-31 | 2020-09-09 | 7 | 0 | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-14 |  | -31458 | 62 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-30 | TBD |  | 60 |  |  | 0 |  | 0 |  |  |  | In Queue | Private |  | 2020-10-05
NSTAR | Plymouth | 2412755 | 2360 | 17.6 | PV & Battery | TBD | 2020-07-28 | 2020-08-14 | 13 |  | 13 | 2020-09-14 |  | -31458 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-18 | [7 empty] | 0 |  | 0
NSTAR | Kingston | 2412838 | 2364 | 15.2 | PV | 3-51-980 | 2020-07-22 |  | -31420 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-21 | [7 empty] | 0 |  | 0 |  |  | 2021-05-13 | Online
NSTAR | Medfield | 2412922 | 2052 | 250 | PV | TBD | 2020-09-01 | 2020-09-03 | 2 | 0 | 2 | 2020-09-14 | 2020-11-25 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2020-12-14 |  | 2020-12-31 | TBD | EXP | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Norfolk | 2412929 | 2056 | 5000 | PV & Battery | TBD | 2020-08-06 |  | -31431 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 2413383 | 1746 | 5000 | PV & Battery | TBD | 2020-08-06 |  | -31431 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 2413389 | 1720 | 5000 | PV & Battery | TBD | 2020-08-06 |  | -31431 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 2413390 | 2360 | 21.4 | PV & Battery | TBD | 2020-08-11 |  | -31434 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Carlisle | 2413532 | 1741 | 17.6 | PV & Battery | TBD | 2020-08-12 | 2020-08-18 | 4 |  | 4 | 2020-09-09 |  | -31455 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0 |  |  | 2021-06-01 | Online
NSTAR | Waltham | 2413861 | 2451 | 487.5 | PV | TBD | 2020-06-22 | 2020-08-25 | 46 |  | 46 | 2020-09-11 |  | -31457 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0
NSTAR | Brookline | 2413980 | 2445 | 133.2 | PV | TBD | 2020-08-27 | 2020-08-27 | 0 |  | 0 | 2020-09-11 |  | -31457 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Hyde Park | 2414035 | 2136 | 15.2 | PV | TBD | 2020-08-04 | 2020-08-18 | 10 |  | 10 | 2020-09-09 |  | -31455 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-16 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Brookline | 2414048 | 2446 | 200 | PV | TBD | 2020-08-27 | 2020-08-27 | 0 |  | 0 | 2020-09-11 |  | -31457 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-09-24 | [7 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Acusnet | 2414312 | 2743 | 1220 | PV & Battery | 2-241-241 | 2020-08-19 | 2020-08-27 | 6 |  | 6 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | 2414387 | 2743 | 610 | PV & Battery | 2-241-241 | 2020-08-19 | 2020-08-27 | 6 |  | 6 | 2020-09-14 |  | -31458 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 4253275 | 2130 | 15.2 | PV | TBD | 2020-08-07 | 2020-08-27 | 14 |  | 14 | 2020-09-17 |  | -31461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chatham | 4257166 | 2633 | 86.6 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 | 9 |  | 9 | 2020-09-17 |  | -31461 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 4258230 | 2136 | 15.2 | PV | TBD | 2020-08-07 | 2020-08-27 | 14 |  | 14 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-27 | Online
NSTAR | Yarmouth | 4263458 | 2673 | 158.4 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 | 9 |  | 9 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0
NSTAR | Truro | 4280601 | 2652 | 35 | PV | TBD | 2020-09-03 | 2020-09-03 | 0 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-01-28 | Online
NSTAR | Burlington | 4280698 | 1803 | 30.2 | PV & Battery | TBD | 2020-07-22 | 2020-08-18 | 19 |  | 19 | 2020-09-25 |  | -31467 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0 |  |  | 2021-06-11 | Online
NSTAR | Aquinnah | 4281091 | 2635 | 54.2 | PV & Battery | TBD | 2020-08-19 | 2020-09-01 | 9 |  | 9 | 2020-09-23 |  | -31465 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0
NSTAR | Orleans | 4284906 | 2653 | 51.62 | PV | TBD | 2020-08-27 | 2020-09-01 | 3 |  | 3 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-03-01 | Online
NSTAR | Acusnet | 4287867 | 2743 | 610 | PV & Battery | TBD | 2020-09-01 | 2020-09-03 | 2 |  | 2 | 2020-09-24 |  | -31466 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | 4288338 | 2536 | 33.3 | PV | TBD | 2020-09-01 | 2020-09-03 | 2 |  | 2 | 2020-09-25 |  | -31467 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2021-03-12 | Online
NSTAR | Lexington | 4289037 | 2421 | 21.4 | PV & Battery | TBD | 2020-09-04 | 2020-09-04 | 0 |  | 0 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-05-18 | Online
NSTAR | East Falmouth | 4290987 | 2536 | 17.04 | PV | 4-77A-77A | 2020-08-27 | 2020-09-02 | 4 |  | 4 | 2020-09-25 |  | -31467 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-01 | [7 empty] | 0 |  | 0 |  |  | 2021-01-21 | Online
NSTAR | Dover | 4296074 | 2030 | 200 | PV | TBD | 2020-09-04 | 2020-09-04 | 0 |  | 0 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Wellfleet | 4304369 | 2667 | 28.7 | PV & Battery | TBD | 2020-08-04 | 2020-09-08 | 25 |  | 25 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0 |  |  | 2021-02-23 | Online
NSTAR | East Falmouth | 4304824 | 2536 | 20 | PV & Battery | TBD | 2020-09-03 | 2020-09-09 | 4 |  | 4 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-08 | [7 empty] | 0 |  | 0 |  |  | 2021-02-12 | Online
NSTAR | Hyannis | 4305225 | 2601 | 86.4 | PV | TBD | 2020-08-27 | 2020-09-03 | 5 |  | 5 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Woburn | 4305278 | 1801 | 111.5 | PV & Battery | TBD | 2020-09-08 | 2020-09-11 | 3 |  | 3 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Online
NSTAR | West Tisbury | 4307156 | 2658 | 48 | PV | TBD | 2020-09-04 | 2020-09-14 | 6 |  | 6 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  | 2021-06-30 | Online
NSTAR | Sudbury | 4307664 | 1776 | 25 | PV & Battery | TBD | 2020-06-11 | 2020-09-15 | 68 |  | 68 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0
NSTAR | Brookline | 4307751 | 2445 | 100 | PV | TBD | 2020-08-27 | 2020-08-27 | 0 |  | 0 | 2020-09-29 |  | -31469 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2022-12-08 | Online
NSTAR | East Dennis | 4308158 | 2641 | 10 | PV & Battery | 4-89A-552 | 2020-09-15 | 2020-09-15 | 0 |  | 0 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Chilmark | 4310270 | 2535 | 166.9 | PV | 4-97-226 | 2020-09-16 | 2020-09-16 | 0 |  | 0 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-20 | [7 empty] | 0 |  | 0 |  |  | 2020-12-22 | Online
NSTAR | West Yarmouth | 4311398 | 2673 | 370 | PV | TBD | 2020-08-18 | 2020-09-03 | 12 |  | 12 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Truro | 4311559 | 2666 | 15.2 | PV | TBD | 2020-08-07 | 2020-09-03 | 19 |  | 19 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-04-09 | Online
NSTAR | Acton | 4312709 | 1720 | 15.2 | PV | TBD | 2020-08-27 | 2020-09-03 | 5 |  | 5 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 4314087 | 1721 | 27.6 | PV & Battery | TBD | 2020-09-04 | 2020-09-04 | 0 |  | 0 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0
NSTAR | Carlisle | 4318460 | 1741 | 30.2 | PV & Battery | TBD | 2020-09-01 | 2020-09-10 | 7 |  | 7 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Needham | 4318615 | 2494 | 1300 | PV & Battery | TBD | 2020-08-27 | 2020-09-10 | 10 |  | 10 | 2020-10-01 |  | -31471 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 4323415 | 2571 | 200 | PV | TBD | 2020-08-06 | 2020-09-10 | 25 |  | 25 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Needham | 4324124 | 2492 | 144 | PV | TBD | 2020-09-03 | 2020-09-11 | 6 |  | 6 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4325211 | 2030 | 20 | PV | 456-H5 | 2020-09-11 | 2020-09-18 | 5 |  | 5 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 4325236 | 2179 | 300 | PV | TBD | 2020-09-08 | 2020-09-14 | 4 |  | 4 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wayland | 4336889 | 1778 | 20 | PV & Battery | TBD | 2020-09-15 | 2020-09-15 | 0 |  | 0 | 2020-10-05 |  | -31473 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Oak Bluffs | 4340257 | 2557 | 233.1 | PV | TBD | 2020-05-26 | 2020-09-15 | 80 |  | 80 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | Watertown | 4340848 | 2472 | 430.3 | PV | TBD | 2020-09-08 | 2020-09-16 | 6 |  | 6 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-24 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Online
NSTAR | Millis | 4345313 | 2054 | 19 | PV | TBD | 2020-09-14 | 2020-09-18 | 4 |  | 4 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Wareham | 4350518 | 2576 | 266.3 | PV | TBD | 2020-09-18 | 2020-09-22 | 2 |  | 2 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2022-03-30 | Online
NSTAR | Canton | 4350632 | 2021 | 35.2 | PV & Battery | TBD | 2020-09-08 | 2020-09-22 | 10 |  | 10 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4351141 | 2030 | 20.22 | PV & Battery | 456-H5 | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-08 |  | -31476 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-05-14 | Online
NSTAR | Bedford | 4352135 | 1730 | 100.8 | PV | TBD | 2020-09-10 | 2020-09-24 | 10 |  | 10 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-17 | [7 empty] | 0 |  | 0 |  |  | 2022-04-12 | Online
NSTAR | Sudbury | 4352193 | 2453 | 17.86 | PV & Battery | TBD | 2020-09-18 | 2020-09-24 | 4 |  | 4 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-21 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Boston | 4352975 | 2215 | 75 | CHP | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-02 | [7 empty] | 0 |  | 0 |  |  | 2021-08-19 | Online
NSTAR | East Freetown | 4355122 | 2717 | 61.6 | PV | TBD | 2020-09-25 | 2020-09-25 | 0 |  | 0 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-11-02 | Online
NSTAR | Allston | 4367936 | 2134 | 125 | PV & Battery | TBD | 2020-09-18 | 2020-09-25 | 5 |  | 5 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-05 | [7 empty] | 0 |  | 0
NSTAR | Wayland | 4371445 | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Wayland | 4372220 | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Wayland | 4372438 | 1778 | 43.2 | PV | TBD | 2020-09-24 | 2020-09-24 | 0 |  | 0 | 2020-10-15 |  | -31481 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-19 | [7 empty] | 0 |  | 0
NSTAR | Carver | 4377469 | 2330 | 200 | PV | TBD | 2020-09-18 | 2020-09-30 | 8 |  | 8 | 2020-10-21 |  | -31485 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-25 | [7 empty] | 0 |  | 0
NSTAR | Milton | 4380220 | 2186 | 17.6 | PV & Battery | TBD | 2020-09-22 | 2020-10-05 | 9 |  | 9 | 2020-10-21 |  | -31485 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0
NSTAR | Duxbury | 4389990 | 2332 | 16.24 | PV & Battery | 3-26-903 | 2020-09-30 | 2020-10-05 | 3 |  | 3 | 2020-10-21 |  | -31485 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0
NSTAR | Natick | 4397054 | 1760 | 100 | PV | TBD | 2020-10-05 | 2020-10-05 | 0 |  | 0 | 2020-10-22 |  | -31486 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-15 | Withdrawn
NSTAR | Waltham | 4399358 | 2453 | 75 | chp | TBD | 2020-10-05 | 2020-10-05 | 0 |  | 0 | 2020-10-22 |  | -31486 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-08-10 | Online
NSTAR | Forestdale | 4399952 | 2644 | 15.2 | PV | 4-81B-443 | 2020-09-18 | 2020-09-18 | 0 |  | 0 | 2020-09-18 |  | -31462 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Watertown | 4403448 | 2472 | 583.3 | PV & Battery | TBD | 2020-09-22 | 2020-09-30 | 6 |  | 6 | 2020-10-22 |  | -31486 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-02 | [7 empty] | 0 |  | 0
NSTAR | Watertown | 4404039 | 2472 | 320.8 | PV | TBD | 2020-09-22 | 2020-09-30 | 6 |  | 6 | 2020-10-22 |  | -31486 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-02 | [7 empty] | 0 |  | 0
NSTAR | Fairhaven | 4404592 | 2719 | 2000 | PV & Battery | TBD | 2020-09-24 | 2020-09-25 | 1 |  | 1 | 2020-10-28 |  | -31490 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 4406125 | 2139 | 77.8 | PV | TBD | 2020-09-30 | 2020-09-30 | 0 |  | 0 | 2020-10-23 |  | -31487 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-09 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Sherborn | 4425381 | 1770 | 20 | PV & Battery | TBD | 2020-10-07 | 2020-10-07 | 0 |  | 0 | 2020-10-28 |  | -31490 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0
NSTAR | West Roxbury | 4425492 | 2132 | 15.2 | PV | TBD | 2020-09-24 | 2020-10-07 | 9 |  | 9 | 2020-10-28 |  | -31490 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Natick | 4427690 | 1760 | 25 | PV & Battery | TBD | 2020-10-07 | 2020-10-07 | 0 |  | 0 | 2020-11-04 |  | -31495 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-09-30 | Online
NSTAR | Vineyard Haven | 4429285 | 2568 | 19.68 | PV | TBD | 2020-08-27 | 2020-10-07 | 29 |  | 29 | 2020-11-04 |  | -31495 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-13 | [7 empty] | 0 |  | 0 |  |  | 2021-03-18 | Online
NSTAR | East Falmouth | 4430372 | 2536 | 198 | PV | TBD | 2020-09-30 | 2020-10-08 | 6 |  | 6 | 2020-11-04 |  | -31495 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4433447 | 2360 | 66.6 | PV | TBD | 2020-10-06 | 2020-10-07 | 1 |  | 1 | 2020-11-09 |  | -31498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0 |  |  | 2021-04-05 | Online
NSTAR | Somerville | 4467249 | 2143 | 250 | PV | TBD | 2020-10-19 | 2020-10-19 | 0 |  | 0 | 2020-11-09 |  | -31498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-13 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 4468058 | 2067 | 19 | PV | TBD | 2020-10-07 | 2020-10-15 | 6 |  | 6 | 2020-11-09 |  | -31498 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0
NSTAR | Wellfleet | 4469232 | 2667 | 23.2 | PV | 4-96-677 | 2020-09-18 | 2020-10-08 | 14 |  | 14 | 2020-11-12 |  | -31501 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-30 | [7 empty] | 0 |  | 0 |  |  | 2021-06-04
NSTAR | Newton | 4469731 | 2458 | 19.75 | PV & Battery | 277-05 | 2020-09-18 | 2020-10-05 | 11 |  | 11 | 2020-11-12 |  | -31501 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-04-20 | Online
NSTAR | Medway | 4470535 | 2053 | 20 | PV & Battery | TBD | 2020-10-07 | 2020-10-19 | 8 |  | 8 | 2020-11-12 |  | -31501 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-06-08 | Online
NSTAR | Canton | 4470982 | 2021 | 245 | PV | TBD | 2020-10-08 | 2020-10-19 | 7 |  | 7 | 2020-11-12 |  | -31501 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0
NSTAR | North Falmouth | 4479289 | 2649 | 25.81 | PV & Battery | TBD | 2020-10-15 | 2020-10-19 | 2 |  | 2 | 2020-11-13 |  | -31502 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0 |  |  | 2021-04-09 | Online
NSTAR | Somerville | 4487617 | 2145 | 250 | PV | TBD | 2020-10-15 | 2020-10-15 | 0 |  | 0 | 2020-11-17 |  | -31504 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2022-02-09 | Online
NSTAR | Sharon | 4488554 | 2067 | 18.75 | PV | TBD | 2020-10-16 | 2020-10-21 | 3 |  | 3 | 2020-11-17 |  | -31504 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-17 | [7 empty] | 0 |  | 0 |  |  | 2021-06-03 | Online
NSTAR | Rochester | 4489081 | 2770 | 22 | PV | TBD | 2020-10-15 | 2020-10-19 | 2 |  | 2 | 2020-11-17 |  | -31504 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-25 | [7 empty] | 0 |  | 0 |  |  | 2021-02-09 | Online
NSTAR | Jamaica Plain | 4489427 | 2130 | 400 | PV | TBD | 2020-10-16 | 2020-10-21 | 3 |  | 3 | 2020-11-17 |  | -31504 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Lexington | 4490263 | 2421 | 24 | PV & Battery | 3401 | 2020-10-15 | 2020-10-21 | 4 |  | 4 | 2020-11-17 |  | -31504 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-01-14 | Online
NSTAR | Wareham | 4490547 | 2576 | 233.2 | PV | TBD | 2020-10-16 | 2020-10-21 | 3 |  | 3 | 2020-11-18 |  | -31505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapoisett | 4490762 | 2739 | 5000 | PV & Battery | TBD | 2020-10-16 | 2020-10-21 | 3 |  | 3 | 2020-11-18 |  | -31505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | 4492827 | 2030 | 36 | PV & Battery | TBD | 2020-10-15 | 2020-10-21 | 4 |  | 4 | 2020-11-18 |  | -31505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-02 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 4493355 | 2050 | 19.6 | PV & Battery | 3-25-25 | 2020-10-21 | 2020-10-22 | 1 |  | 1 | 2020-11-18 |  | -31505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0
NSTAR | Assonett | 4494158 | 2702 | 18.85 | PV | TBD | 2020-10-22 | 2020-10-22 | 0 |  | 0 | 2020-12-03 |  | -31516 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-05-05 | Online
NSTAR | Newton | 4495812 | 2459 | 18 | PV & Battery | TBD | 2020-10-16 | 2020-10-22 | 4 |  | 4 | 2020-11-19 |  | -31506 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | 4500410 | 2121 | 16.8 | PV | TBD | 2020-10-07 | 2020-10-27 | 14 |  | 14 | 2020-11-23 |  | -31508 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0
NSTAR | Canton | 4503033 | 2021 | 200 | PV | TBD | 2020-10-21 | 2020-10-22 | 1 |  | 1 | 2020-11-23 |  | -31508 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-12 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4506135 | 2360 | 1000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 | 6 |  | 6 | 2020-11-24 |  | -31509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | 4506942 | 2143 | 53.6 | PV & Battery | TBD | 2020-10-19 | 2020-10-27 | 6 |  | 6 | 2020-11-23 |  | -31508 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-25 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Online
NSTAR | Carver | 4507889 | 2330 | 1000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 | 6 |  | 6 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 4518746 | 2330 | 5000 | PV & Battery | TBD | 2020-10-21 | 2020-10-29 | 6 |  | 6 | 2020-11-24 |  | -31509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Arlington | 4519305 | 2476 | 17.6 | PV & Battery | TBD | 2020-10-05 | 2020-10-15 | 8 |  | 8 | 2020-11-24 |  | -31509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-11-30 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Walpole | 4519566 | 2081 | 15.2 | PV | TBD | 2020-09-14 | 2020-10-15 | 23 |  | 23 | 2020-11-24 |  | -31509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Plympton | 4519678 | 2367 | 15.2 | PV | TBD | 2020-10-08 | 2020-10-16 | 6 |  | 6 | 2020-11-24 |  | -31509 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-08 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 4529021 | 2021 | 166.5 | PV | 269-1321H2 | 2020-09-28 | 2020-09-28 | 0 |  | 0 | 2020-09-28 |  | -31468 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 |  |  |  | EXP |  |  |  | 0 |  | 0 |  |  | 2021-11-15 | Online | Private
NSTAR | Framingham | 4532766 | 1701 | 16.4 | PV | TBD | 2020-09-30 | 2020-11-02 | 23 |  | 23 | 2020-11-25 |  | -31510 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-10-20 | Online
NSTAR | Westwood | 4533474 | 2090 | 20 | PV & Battery | TBD | 2020-11-16 | 2020-11-18 | 2 |  | 2 | 2020-11-25 |  | -31510 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-12 | [7 empty] | 0 |  | 0
NSTAR | Bellingham | 4534965 | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 | 23 |  | 23 | 2020-12-01 |  | -31514 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bellingham | 4535505 | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 | 23 |  | 23 | 2020-12-01 |  | -31514 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | 4550665 | 2120 | 66.6 | PV | TBD | 2020-11-16 | 2020-11-16 | 0 |  | 0 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0
NSTAR | Boston | 4550829 | 2120 | 66.6 | PV | TBD | 2020-11-16 | 2020-11-16 | 0 |  | 0 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 4551603 | 2120 | 43.2 | PV | TBD | 2020-11-02 | 2020-11-02 | 0 |  | 0 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-06-11 | Online
NSTAR | Assonett | 4556815 | 2702 | 15.2 | PV | TBD | 2020-10-15 | 2020-11-04 | 14 |  | 14 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Lincoln | 4556854 | 1773 | 20 | PV & Battery | TBD | 2020-11-02 | 2020-11-04 | 2 |  | 2 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-05 | Online
NSTAR | Acusnet | 4556908 | 2743 | 500 | PV & Battery | TBD | 2020-11-02 | 2020-11-02 | 0 |  | 0 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-04-20 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 4556981 | 2740 | 999 | PV & Battery | TBD | 2020-10-27 | 2020-11-02 | 4 |  | 4 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-17
NSTAR | Woburn | 4557000 | 1801 | 57.6 | PV | TBD | 2020-10-27 | 2020-11-04 | 6 |  | 6 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2022-02-16 | Online
NSTAR | Sherborn | 4557126 | 1770 | 18.6 | PV & Battery | TBD | 2020-11-02 | 2020-11-04 | 2 |  | 2 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 4562972 | 2130 | 75 | CHP | TBD | 2020-11-02 | 2020-11-04 | 2 |  | 2 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-29 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online
NSTAR | Dedham | 4575161 | 2026 | 4990 | PV & Battery | TBD | 2020-05-07 |  | -31366 |  | 0 | 2020-09-11 |  | -31457 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Norfolk | 4578744 | 2056 | 15.2 | PV | TBD | 2020-10-27 | 2020-11-09 | 9 |  | 9 | 2020-12-08 |  | -31519 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-08-03 | Online
NSTAR | New Bedford | 4579621 | 2746 | 93.45 | PV | TBD | 2020-10-29 | 2020-11-10 | 8 |  | 8 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-09-13 | Online
NSTAR | Medfield | 4581063 | 2052 | 17.6 | PV | 456-H5 | 2020-09-18 | 2020-11-04 | 33 |  | 33 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-09-14 | Online
NSTAR | Bellingham | 4581275 | 2019 | 4999 | PV & Battery | TBD | 2020-09-30 | 2020-11-02 | 23 |  | 23 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 4581293 | 2067 | 15.2 | PV | TBD | 2020-11-06 | 2020-11-09 | 1 |  | 1 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-29 | Online
NSTAR | Dartmouth | 4581517 | 2747 | 200 | PV | TBD | 2020-11-04 | 2020-11-06 | 2 |  | 2 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online
NSTAR | Newton | 4581647 | 2464 | 25 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | 7 |  | 7 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | South Walpole | 4581720 | 2071 | 20 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | 7 |  | 7 | 2020-12-04 |  | -31517 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0 |  |  | 2021-06-25 | Online
NSTAR | Westwood | 4581827 | 2090 | 20 | PV & Battery | TBD | 2020-11-13 | 2020-11-13 | 0 |  | 0 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 4582227 | 2451 | 7.6 | PV | TBD | 2020-10-29 | 2020-11-06 | 6 |  | 6 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-08-04 | Online
NSTAR | New Bedford | 4582294 | 2745 | 17.6 | PV & Battery | 2-104-104 | 2020-10-21 | 2020-11-09 | 13 |  | 13 | 2020-12-09 |  | -31520 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-15 | [7 empty] | 0 |  | 0 |  |  | 2021-04-06 | Online
NSTAR | Medfield | 4589421 | 2052 | 200 | PV | TBD | 2020-10-27 | 2020-11-09 | 9 |  | 9 | 2020-12-11 |  | -31522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | New Bedford | 4590471 | 2740 | 20 | PV | TBD | 2020-11-09 | 2020-11-16 | 5 |  | 5 | 2020-12-11 |  | -31522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-05-14 | Online
NSTAR | Walpole | 4590656 | 2081 | 10 | PV & Battery | 146-H3 | 2020-11-06 | 2020-11-13 | 5 |  | 5 | 2020-12-11 |  | -31522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-28 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 4590784 | 2770 | 20 | PV | TBD | 2020-11-06 | 2020-11-13 | 5 |  | 5 | 2020-12-11 |  | -31522 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-24 | [7 empty] | 0 |  | 0 |  |  | 2021-06-11 | Online
NSTAR | Needham | 4590881 | 2494 | 17.36 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | 7 |  | 7 | 2020-12-22 |  | -31529 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-07 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 4590902 | 2743 | 61.6 | PV | TBD | 2020-11-16 | 2020-11-16 | 0 |  | 0 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0 |  |  | 2021-08-24 | Online
NSTAR | Newton | 4590939 | 2461 | 10 | PV & Battery | 292-01 | 2020-11-13 | 2020-11-16 | 1 |  | 1 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bedford | 4606031 | 1730 | 20 | PV & Battery | TBD | 2020-11-18 | 2020-11-24 | 4 |  | 4 | 2020-12-15 |  | -31524 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 4606031 | [7 empty] | 0 |  | 0 |  |  | 2021-02-10 | Online
NSTAR | New Bedford | 4607301 | 2745 | 2125 | PV | TBD | 2020-11-18 | 2020-12-01 | 9 |  | 9 | 2020-12-17 |  | -31526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 4607939 | 1748 | 19.72 | PV | TBD | 2020-11-24 | 2020-12-01 | 5 |  | 5 | 2020-12-17 |  | -31526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-19 | Online
NSTAR | West Newton | 4610357 | 2465 | 17.6 | PV & Battery | TBD | 2020-11-13 | 2020-11-13 | 0 |  | 0 | 2020-12-17 |  | -31526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-18 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Online
NSTAR | Maynard | 4614920 | 1754 | 86.4 | PV | TBD | 2020-11-13 | 2020-11-16 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29
NSTAR | Burlington | 4615024 | 1803 | 58.2 | PV | TBD | 2020-11-02 | 2020-11-18 | 12 |  | 12 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-07-26 | Online
NSTAR | Holliston | 4615055 | 1746 | 19.8 | PV & Battery | TBD | 2020-11-18 | 2020-11-19 | 1 |  | 1 | 2020-12-21 |  | -31528 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-26 | [7 empty] | 0 |  | 0 |  |  | 2021-04-01 | Online
NSTAR | Dorchester | 4615111 | 2124 | 15.2 | PV | TBD | 2020-12-01 | 2020-12-07 | 4 |  | 4 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Arlington | 4615145 | 2476 | 15.2 | PV | TBD | 2020-10-27 | 2020-11-09 | 9 |  | 9 | 2020-12-22 |  | -31529 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2022-02-03 | Online
NSTAR | North Dartmouth | 4615175 | 2747 | 35.2 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | 7 |  | 7 | 2020-12-22 |  | -31529 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2022-06-17 | Online
NSTAR | Sudbury | 4619003 | 1776 | 5 | Battery | 342-H4 | 2020-11-06 | 2020-11-24 | 12 |  | 12 | 2020-12-21 |  | -31528 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 4619474 | 1701 | 17.6 | PV & Battery | 278-H1 | 2020-11-09 | 2020-11-24 | 11 |  | 11 | 2020-12-21 |  | -31528 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-20 | [7 empty] | 0 |  | 0 |  |  | 2021-03-18 | Online
NSTAR | Framingham | 4619506 | 1702 | 205 | PV | TBD | 2020-11-18 | 2020-11-24 | 4 |  | 4 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-03 | [7 empty] | 0 |  | 0
NSTAR | Winchester | 4619563 | 1890 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-24 | 7 |  | 7 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Mattapoisett | 4619595 | 2739 | 2250 | PV & Battery | TBD | 2020-11-06 | 2020-11-25 | 13 |  | 13 | 2020-12-21 |  | -31528 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 4619617 | 2067 | 20 | PV & Battery | TBD | 2020-10-29 | 2020-11-25 | 19 |  | 19 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0 |  |  | 2021-11-19 | Online
NSTAR | Sudbury | 4619695 | 1776 | 23.8 | PV & Battery | TBD | 2020-11-06 | 2020-11-24 | 12 |  | 12 | 2020-12-22 |  | -31529 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-06 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4619716 | 2360 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-25 | 8 |  | 8 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-30 | [7 empty] | 0 |  | 0
NSTAR | Truro | 4621310 | 2666 | 62.93 | PV | TBD | 2020-12-01 | 2020-12-07 | 4 |  | 4 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-01 | [7 empty] | 0 |  | 0 |  |  | 2022-01-18 | Online
NSTAR | Lexington | 4621352 | 2420 | 17.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-16 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online
NSTAR | Mashpee | 4632820 | 2649 | 13.8 | PV & Battery | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2023-01-23 | Online
NSTAR | South Dartmouth | 4632856 | 2748 | 43.92 | PV | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-15 | Online
NSTAR | Medfield | 4635189 | 2052 | 25 | PV & Battery | TBD | 2020-11-25 | 2020-12-14 | 13 |  | 13 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0 |  |  | 2022-05-13 | Online
NSTAR | Stoneham | 4635296 | 2180 | 180 | PV | TBD | 2020-12-01 | 2020-12-01 | 0 |  | 0 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Westwood | 4635371 | 2090 | 20 | PV & Battery | TBD | 2020-12-01 | 2020-12-01 | 0 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | Westwood | 4636581 | 2090 | 25.2 | PV & Battery | TBD | 2020-11-25 | 2020-12-07 | 8 |  | 8 | 2020-12-23 |  | -31530 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-05 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online
NSTAR | Needham | 4637344 | 2494 | 22.6 | PV & Battery | TBD | 2020-11-04 | 2020-11-13 | 7 |  | 7 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-03 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online
NSTAR | Sharon | 4637394 | 2067 | 18.5 | PV | TBD | 2020-11-13 | 2020-11-18 | 3 |  | 3 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Manomet | 4637511 | 2345 | 17.4 | PV | TBD | 2020-11-13 | 2020-11-18 | 3 |  | 3 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Marshfield | 4637609 | 2050 | 13.8 | PV & Battery | 3-22-973 | 2020-10-29 |  | -31491 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2021-05-21 | Online
NSTAR | Cambridge | 4637828 | 2140 | 75 | CHP | TBD | 2020-11-18 |  | -31505 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-08 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15
NSTAR | Boston | 4637851 | 2135 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-11-25 | 8 |  | 8 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 4637906 | 1701 | 250 | PV | TBD | 2020-11-25 | 2020-11-25 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4642133 | 2421 | 5 | PV & Battery | TBD | 2020-11-13 | 2020-12-01 | 12 |  | 12 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online
NSTAR | North Cambridge | 4642185 | 2140 | 19.57 | PV & Battery | TBD | 2020-11-06 | 2020-12-01 | 17 |  | 17 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  | 2021-05-21 | Online
NSTAR | West Roxbury | 4642220 | 2132 | 15.2 | PV | TBD | 2020-11-25 | 2020-12-01 | 4 |  | 4 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-06 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 4642283 | 2459 | 28.8 | PV & Battery | 292-H6 | 2020-11-18 | 2020-12-07 | 13 |  | 13 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-03-03 | Online
NSTAR | Somerville | 4642301 | 2145 | 201.6 | PV | TBD | 2020-12-01 | 2020-12-07 | 4 |  | 4 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0
NSTAR | Millis | 4642384 | 2054 | 15.2 | PV | TBD | 2020-12-07 | 2020-12-07 | 0 |  | 0 | 2020-12-29 |  | -31534 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-13 | [7 empty] | 0 |  | 0 |  |  | 2021-08-06 | Online
NSTAR | Newton | 4658683 | 2459 | 15 | PV & Battery | 292-H11 | 2020-11-13 | 2020-11-24 | 7 |  | 7 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2023-01-06 | Online
NSTAR | Truro | 4658780 | 2666 | 249.8 | PV | TBD | 2020-11-24 | 2020-11-24 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0
NSTAR | Westwood | 4659394 | 2090 | 95.8 | PV | TBD | 2020-11-06 | 2020-12-14 | 26 |  | 26 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Wareham | 4659423 | 2571 | 4980 | PV & Battery | TBD | 2020-12-07 | 2020-12-14 | 5 |  | 5 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-23 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 4659441 | 1803 | 23.49 | PV | TBD | 2020-12-07 | 2020-12-14 | 5 |  | 5 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-07 | Online
NSTAR | Watertown | 4659469 | 2122 | 57.6 | PV | TBD | 2020-12-07 | 2020-12-14 | 5 |  | 5 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-28 | [7 empty] | 0 |  | 0 |  |  | 2021-08-30 | Online
NSTAR | Acton | 4659513 | 1720 | 4980 | PV & Battery | TBD | 2020-11-25 | 2020-12-15 | 14 |  | 14 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | 4661337 | 2030 | 20 | PV | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Weston | 4663199 | 2493 | 35.2 | PV & Battery | TBD | 2020-12-16 | 2020-12-16 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-02-22 | Online
NSTAR | Holliston | 4664449 | 1746 | 10 | Battery | TBD | 2020-11-16 | 2020-12-14 | 20 |  | 20 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-23 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4664554 | 2030 | 19.84 | PV & Battery | 456-H5 | 2020-12-14 | 2020-12-14 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-02 | [7 empty] | 0 |  | 0
NSTAR | Acton | 4665887 | 1720 | 17.6 | PV & Battery | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2022-03-28 | Online
NSTAR | Acton | 4668063 | 1720 | 25.2 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-03-16 | Online
NSTAR | Winchester | 4668160 | 1890 | 25 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Marion | 4668251 | 2738 | 22.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-11 | [7 empty] | 0 |  | 0 |  |  | 2021-06-30 | Online
NSTAR | Marshfield | 4668327 | 2050 | 18 | PV | TBD | 2020-12-17 | 2020-12-17 | 0 |  | 0 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 4669412 | 2770 | 149.3 | PV | TBD | 2020-12-01 | 2020-12-14 | 9 |  | 9 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | 4675384 | 2364 | 499 | PV & Battery | TBD | 2020-12-14 | 2020-12-14 | 0 |  | 0 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-01 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 4676006 | 2180 | 150 | PV | TBD | 2020-12-14 | 2020-12-14 | 0 |  | 0 | 2021-01-08 |  | -31542 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0 |  |  | 2022-03-11 | Online
NSTAR | Wayland | 4676256 | 1778 | 20 | PV | TBD | 2020-11-25 | 2020-12-14 | 13 |  | 13 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0
NSTAR | Roslindale | 4677350 | 2131 | 18 | PV & Battery | 496-H8 | 2020-12-16 | 2020-12-16 | 0 |  | 0 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Dorchester | 4680348 | 2124 | 15.2 | PV | TBD | 2020-10-29 | 2020-12-22 | 38 |  | 38 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0 |  |  | 2021-09-24 | Online
NSTAR | Stoneham | 4680468 | 2180 | 15.2 | PV | TBD | 2020-10-29 | 2020-12-22 | 38 |  | 38 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 4680531 | 1748 | 35.2 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Milton | 4680587 | 2186 | 16 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Sherborn | 4680617 | 1770 | 17.6 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-02 | [7 empty] | 0 |  | 0 |  |  | 2022-05-18 | Online
NSTAR | Hopkinton | 4683322 | 1748 | 20 | PV & Battery | TBD | 2020-12-07 | 2020-12-22 | 11 |  | 11 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | Waltham | 4683376 | 2451 | 166 | PV | TBD | 2020-12-14 | 2020-12-22 | 6 |  | 6 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-04-11 | Online
NSTAR | Mattapan | 4683605 | 2126 | 7.6 | PV | TBD | 2020-12-14 | 2020-12-22 | 6 |  | 6 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-22 | [7 empty] | 0 |  | 0
NSTAR | Acton | 4685975 | 1720 | 34.2 | PV | TBD | 2020-11-25 | 2020-12-22 | 19 |  | 19 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0
NSTAR | East Freetown | 4686146 | 2717 | 149.3 | PV | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Waltham | 4686399 | 2451 | 233 | PV | TBD | 2020-12-14 | 2020-12-22 | 6 |  | 6 | 2021-01-11 |  | -31543 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mattapoisett | 4696273 | 2793 | 2500 | PV & Battery | TBD | 2020-11-04 | 2020-11-25 | 15 |  | 15 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 4698222 | 1720 | 34.2 | PV | TBD | 2020-11-25 | 2020-12-29 | 24 |  | 24 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0
NSTAR | South Dartmouth | 4698354 | 2748 | 15.2 | PV | TBD | 2020-12-14 | 2020-12-29 | 11 |  | 11 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Natick | 4698431 | 1760 | 7.6 | PV | 240-H3 | 2020-12-14 | 2020-12-29 | 11 |  | 11 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 4698540 | 2081 | 495 | PV | TBD | 2020-11-13 | 2020-12-29 | 32 |  | 32 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0
NSTAR | Dover | 4701003 | 2030 | 20.92 | PV | 456-H5 | 2020-12-14 | 2020-12-29 | 11 |  | 11 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Acusnet | 4702589 | 2743 | 4990 | PV & Battery | TBD | 2020-12-17 | 2020-12-29 | 8 |  | 8 | 2021-01-13 |  | -31545 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 4706363 | 2330 | 248 | PV | TBD | 2020-12-30 | 2020-12-30 | 0 |  | 0 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dedham | 4707682 | 2026 | 66.6 | PV | 20-H1 | 2020-12-01 | 2020-12-30 | 21 |  | 21 | 2021-01-21 |  | -31551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-10-20 | Online
NSTAR | Newton | 4708433 | 2459 | 66.6 | PV | TBD | 2020-12-30 | 2020-12-30 | 0 |  | 0 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plympton | 4708506 | 2367 | 19 | PV | TBD | 2020-12-29 | 2020-12-30 | 1 |  | 1 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4708532 | 2421 | 17.44 | PV & Battery | TBD | 2020-12-30 | 2020-12-30 | 0 |  | 0 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0
NSTAR | Acton | 4708871 | 1720 | 2495 | Battery | TBD | 2020-12-29 | 2020-12-29 | 0 |  | 0 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | 4713423 | 2139 | 75 | CHP | 831-1394 | 2020-12-31 | 2020-12-31 | 0 |  | 0 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-04 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Holliston | 4713490 | 1746 | 20 | PV & Battery | TBD | 2020-07-29 | 2020-08-10 | 8 |  | 8 | 2020-08-31 |  | -31448 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online
NSTAR | Lincoln | 4713513 | 1773 | 14 | Battery | 320-H8 | 2020-12-31 | 2020-12-31 | 0 |  | 0 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-04-30 | Online
NSTAR | Medfield | 4714661 | 2052 | 250 | PV | TBD | 2020-08-14 |  | -31437 |  | 0 | 2020-09-03 |  | -31451 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-14 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4717011 | 2420 | 40 | PV & Battery | TBD | 2020-12-30 | 2020-12-31 | 1 |  | 1 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-18 | [7 empty] | 0 |  | 0
NSTAR | Mattapoisett | 4717656 | 2739 | 2496 | Battery | TBD | 2020-12-22 | 2020-12-22 | 0 |  | 0 | 2021-01-19 |  | -31549 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 4832256 | 2492 | 16 | PV | TBD | 2020-12-22 | 2020-12-23 | 1 |  | 1 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  | 2021-08-30 | Online
NSTAR | Walpole | 4833200 | 2081 | 15.2 | PV | TBD | 2020-12-23 | 2020-12-23 | 0 |  | 0 | 2021-01-21 |  | -31551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Stoneham | 4841015 | 2180 | 15.2 | PV | 375-H8 | 2020-12-29 | 2021-01-11 | 9 |  | 9 | 2021-01-21 |  | -31551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0 |  |  | 2021-05-17 | Online
NSTAR | Stoneham | 4841178 | 2180 | 19 | PV | TBD | 2020-12-29 | 2021-01-06 | 6 |  | 6 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-01 | [7 empty] | 0 |  | 0 |  |  | 2021-08-19 | Online
NSTAR | Canton | 4849001 | 2021 | 53.2 | PV | TBD | 2021-01-04 | 2021-01-07 | 3 |  | 3 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-09-01 | Online
NSTAR | Carver | 4849634 | 2330 | 72 | PV | TBD | 2020-12-30 | 2021-01-06 | 5 |  | 5 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-04 | [7 empty] | 0 |  | 0 |  |  | 2021-06-09 | Online
NSTAR | Milton | 4850213 | 2186 | 23.78 | PV | TBD | 2021-01-07 | 2021-01-07 | 0 |  | 0 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Sudbury | 4850477 | 1776 | 35.2 | PV & Battery | TBD | 2020-12-24 | 2020-12-24 | 0 |  | 0 | 2021-01-25 |  | -31553 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Dartmouth | 4869494 | 2747 | 18.6 | PV | TBD | 2021-01-07 | 2021-01-11 | 2 |  | 2 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-28 | Online
NSTAR | Freetown | 4869709 | 2702 | 4999 | PV & Battery | TBD | 2020-12-30 | 2021-01-11 | 8 |  | 8 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 4869810 | 2492 | 17.04 | PV | TBD | 2020-12-31 | 2021-01-11 | 7 |  | 7 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0 |  |  | 2021-08-06 | Online
NSTAR | Rochester | 4869940 | 2770 | 250 | PV | TBD | 2020-12-31 | 2021-01-11 | 7 |  | 7 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 4869990 | 2360 | 110 | PV | TBD | 2020-12-31 | 2021-01-11 | 7 |  | 7 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  | 2022-02-07 | Online
NSTAR | South Dartmouth | 4870032 | 2748 | 18 | PV & Battery | TBD | 2020-12-17 | 2021-01-11 | 17 |  | 17 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 4874091 | 2420 | 25.2 | PV & Battery | TBD | 2020-12-17 | 2021-01-11 | 17 |  | 17 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-01-26 | Online
NSTAR | Carver | 4876930 | 2330 | 15.2 | PV | TBD | 2020-12-16 | 2021-01-11 | 18 |  | 18 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-08-24 | Online
NSTAR | East Wareham | 4877705 | 2538 | 17.6 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | 20 |  | 20 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-10-07 | Online
NSTAR | Acton | 4878009 | 1720 | 20 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | 20 |  | 20 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-08-23 | Online
NSTAR | West Somerville | 4878069 | 2144 | 17.6 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | 20 |  | 20 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0
NSTAR | Weston | 4878172 | 2493 | 18 | PV & Battery | TBD | 2020-12-14 | 2021-01-11 | 20 |  | 20 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0
NSTAR | Weston | 4878244 | 2393 | 21.4 | PV & Battery | TBD | 2020-12-28 | 2020-12-28 | 0 |  | 0 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-07-08 | Online
NSTAR | Newton | 4878336 | 2468 | 35.2 | PV & Battery | TBD | 2020-12-01 | 2021-01-11 | 29 |  | 29 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-23 | [7 empty] | 0 |  | 0 |  |  | 2021-10-25 | Online
NSTAR | Sudbury | 4878402 | 1776 | 20 | PV & Battery | TBD | 2021-01-11 | 2021-01-11 | 0 |  | 0 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Burlington | 4878461 | 1803 | 20 | PV & Battery | 391-H7 | 2020-12-14 | 2021-01-11 | 20 |  | 20 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-01-29 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | North Acton | 4886788 | 1720 | 57.6 | PV | TBD | 2021-01-12 | 2021-01-12 | 0 |  | 0 | 2021-01-28 |  | -31556 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2022-02-28 | Online
NSTAR | Hyannis | 4886864 | 2601 | 7.6 | PV | 4-84A-520 | 2020-12-14 | 2021-01-12 | 21 |  | 21 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-08-25 | Online
NSTAR | East Walpole | 4886981 | 2032 | 15.2 | PV | TBD | 2020-12-14 | 2021-01-12 | 21 |  | 21 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-07-27 | Online
NSTAR | Westwood | 4887029 | 2090 | 20 | PV & Battery | TBD | 2020-12-29 | 2021-01-12 | 10 |  | 10 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0
NSTAR | Westport | 4887097 | 2790 | 23.8 | PV & Battery | TBD | 2020-12-29 | 2021-01-12 | 10 |  | 10 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0
NSTAR | Mashpee | 4887205 | 2649 | 52.78 | PV | TBD | 2021-01-12 | 2021-01-12 | 0 |  | 0 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-10 | [7 empty] | 0 |  | 0 |  |  | 2021-05-27 | Online
NSTAR | Plymouth | 4887324 | 2360 | 17.6 | PV & Battery | TBD | 2020-11-25 | 2021-01-12 | 34 |  | 34 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Online
NSTAR | Waltham | 4887381 | 2451 | 466 | PV | TBD | 2020-12-31 | 2021-01-25 | 17 |  | 17 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0 |  |  | 2022-12-30 | Online
NSTAR | Wayland | 4894418 | 1778 | 16.78 | PV & Battery | TBD | 2020-12-28 | 2020-12-28 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2022-05-16 | Online
NSTAR | Bedford | 4896010 | 1730 | 15.2 | PV | TBD | 2021-01-12 | 2021-01-14 | 2 |  | 2 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-11-19 | Online
NSTAR | East Freetown | 4896804 | 2717 | 25 | PV & Battery | TBD | 2021-01-12 | 2021-01-14 | 2 |  | 2 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 4907766 | 2743 | 149.3 | PV | TBD | 2021-01-14 | 2021-01-14 | 0 |  | 0 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 4907809 | 2743 | 149.3 | PV | TBD | 2021-01-14 | 2021-01-14 | 0 |  | 0 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 4907860 | 2673 | 21.75 | PV & Battery | TBD | 2021-01-12 | 2021-01-14 | 2 |  | 2 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2022-02-16 | Online
NSTAR | Medway | 4920759 | 2053 | 29.5 | PV | TBD | 2020-12-30 | 2021-01-19 | 14 |  | 14 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-20 | [7 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Medway | 4920922 | 2053 | 19.75 | PV | TBD | 2020-12-30 | 2021-01-19 | 14 |  | 14 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Milton | 4921183 | 2186 | 15.2 | PV | 311-04 | 2021-01-12 | 2021-01-19 | 5 |  | 5 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0
NSTAR | Rochester | 4921323 | 2770 | 25.2 | PV & Battery | TBD | 2020-12-14 | 2021-01-20 | 27 |  | 27 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 4921387 | 2476 | 20 | PV & Battery | TBD | 2020-12-29 | 2021-01-19 | 15 |  | 15 | 2021-02-02 |  | -31559 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-09 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Online
NSTAR | Sharon | 4921508 | 2067 | 13.8 | PV & Battery | TBD | 2020-12-14 |  | -31523 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2021-11-04 | Online
NSTAR | Hyannis | 4936393 | 2601 | 69.25 | PV | TBD | 2021-01-21 |  | -31551 |  | 0 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0
NSTAR | Brighton | 4936614 | 2134 | 43.2 | PV | TBD | 2021-01-21 | 2021-01-21 | 0 |  | 0 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 4937121 | 1703 | 21.83 | PV | TBD | 2021-01-21 | 2021-01-21 | 0 |  | 0 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online
NSTAR | Hyannis | 4945477 | 2601 | 86.6 | PV | TBD | 2021-01-21 | 2021-01-21 | 0 |  | 0 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2022-09-22 | Online
NSTAR | Hyannis | 4945583 | 2601 | 120 | PV | TBD | 2021-01-12 | 2021-01-21 | 7 |  | 7 | 2021-02-05 |  | -31562 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-18 | [7 empty] | 0 |  | 0 |  |  | 2021-12-23 | Online
NSTAR | Mashpee | 4962795 | 2649 | 495 | PV | TBD | 2021-01-21 | 2021-01-26 | 3 |  | 3 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0
NSTAR | Truro | 4963253 | 2666 | 17.68 | battery | TBD | 2021-01-21 | 2021-01-27 | 4 |  | 4 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Duxbury | 4963456 | 2332 | 25.2 | PV | TBD | 2021-01-21 | 2021-01-27 | 4 |  | 4 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Sherborn | 4963535 | 1770 | 15.2 | PV & Battery | TBD | 2020-11-24 | 2021-01-27 | 46 |  | 46 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Plymouth | 4963768 | 2360 | 20 | PV & Battery | TBD | 2020-12-01 | 2021-01-27 | 41 |  | 41 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-12 | Online
NSTAR | Walpole | 4963817 | 2081 | 10 | PV & Battery | TBD | 2020-12-14 | 2021-01-27 | 32 |  | 32 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0 |  |  | 2021-08-18 | Online
NSTAR | Marston Mills | 4971708 | 2648 | 11.6 | Battery | TBD | 2021-01-21 | 2021-01-27 | 4 |  | 4 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wayland | 4972029 | 1778 | 10 | Battery | TBD | 2021-01-27 | 2021-01-28 | 1 |  | 1 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2022-06-16 | Online
NSTAR | Acton | 4972089 | 1720 | 20 | PV & Battery | TBD | 2020-12-07 | 2021-01-27 | 37 |  | 37 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 4972223 | 2747 | 200 | PV | TBD | 2021-03-02 | 2021-03-02 | 0 |  | 0 | 2021-03-02 |  | -31579 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | 4983194 | 2601 | 51.9 | PV | TBD | 2021-01-20 | 2021-01-20 | 0 |  | 0 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0
NSTAR | Milton | 4983372 | 2186 | 15.8 | PV & Battery | TBD | 2020-12-29 | 2021-01-20 | 16 |  | 16 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-05 | [7 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | Hyannis | 4983604 | 2601 | 90 | PV | TBD | 2021-01-20 | 2021-01-20 | 0 |  | 0 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-11-09 | Online
NSTAR | Sudbury | 4983699 | 1776 | 15.2 | PV | TBD | 2020-12-14 | 2021-01-20 | 27 |  | 27 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | 4983727 | 2067 | 16.48 | PV & Battery | TBD | 2020-12-29 | 2021-01-20 | 16 |  | 16 | 2021-02-11 |  | -31566 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-12 | [7 empty] | 0 |  | 0 |  |  | 2022-02-07 | Online
NSTAR | Bourne | 4991635 | 2532 | 19.9 | PV | TBD | 2021-01-21 | 2021-01-26 | 3 |  | 3 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-02-19 | [7 empty] | 0 |  | 0 |  |  | 2021-06-24 | Online
NSTAR | New Bedford | 4991678 | 2740 | 15.2 | PV | TBD | 2021-01-06 | 2021-01-26 | 14 |  | 14 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Harwich | 4999717 | 2645 | 213.2 | PV | TBD | 2021-01-12 | 2021-01-20 | 6 |  | 6 | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-04-11 | Online
NSTAR | Kingston | 5000850 | 2364 | 250 | PV | TBD | 2021-01-14 | 2021-01-20 | 4 |  | 4 | 2021-02-16 |  | -31569 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0
NSTAR | Carver | 5001002 | 2330 | 1992 | PV | TBD | 2021-01-20 | 2021-01-20 | 0 |  | 0 | 2021-02-16 |  | -31569 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Carver | 5016871 | 2366 | 23.8 | PV & Battery | TBD | 2021-01-25 | 2021-02-05 | 9 |  | 9 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 5017076 | 2474 | 19 | Battery | TBD | 2021-01-21 | 2021-02-05 | 11 |  | 11 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online
NSTAR | Carlisle | 5017153 | 1741 | 35.2 | PV & Battery | TBD | 2021-01-26 | 2021-02-05 | 8 |  | 8 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | 5018578 | 2601 | 120 | PV | TBD | 2021-01-21 | 2021-02-05 | 11 |  | 11 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-15 | Online
NSTAR | Holliston | 5025553 | 1746 | 120 | PV | TBD | 2020-12-31 | 2021-02-05 | 26 |  | 26 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0 |  |  | 2022-08-04 | Online
NSTAR | Canton | 5057342 | 2021 | 7.6 | PV | TBD | 2021-01-27 | 2021-02-05 | 7 |  | 7 | 2021-02-24 |  | -31575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Yarmouth | 5057452 | 2673 | 188 | PV | TBD | 2021-01-27 | 2021-02-05 | 7 |  | 7 | 2021-02-24 |  | -31575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-15 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5057606 | 2420 | 20 | PV & Battery | TBD | 2021-01-26 | 2021-02-05 | 8 |  | 8 | 2021-02-24 |  | -31575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-08-10 | Online
NSTAR | Lexington | 5058397 | 2421 | 20 | PV & Battery | TBD | 2020-11-06 | 2021-02-05 | 65 |  | 65 | 2021-02-24 |  | -31575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-08 | Online
NSTAR | West Barnstable | 5058535 | 2668 | 20.88 | PV | TBD | 2021-02-05 | 2021-02-05 | 0 |  | 0 | 2021-02-24 |  | -31575 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-06-21 | Online
NSTAR | Kingston | 5077570 | 2364 | 22.8 | PV & Battery | TBD | 2021-01-21 | 2021-02-08 | 12 |  | 12 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 | [7 empty] | 0 |  | 0
NSTAR | Needham | 5077813 | 2492 | 10 | Battery | TBD | 2021-02-05 | 2021-02-08 | 1 |  | 1 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 5077946 | 1722 | 466.6 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5077981 | 1722 | 233.2 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5078034 | 1722 | 200 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5078087 | 1722 | 100 | PV | TBD | 2021-02-08 | 2021-02-08 | 0 |  | 0 | 2021-03-01 |  | -31578 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5087787 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5087888 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5087946 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088024 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088121 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088220 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088274 | 1720 | 500 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5088314 | 1720 | 500 | PV | TBD | 2020-12-17 |  | -31526 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5097801 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5097909 | 1720 | 1000 | PV & Battery | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | 5099394 | 1801 | 19.6 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-12 | [7 empty] | 0 |  | 0 |  |  | 2022-07-27 | Online
NSTAR | Hopkinton | 5099581 | 1848 | 19.6 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online
NSTAR | Westwood | 5099732 | 2090 | 15.2 | PV | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0
NSTAR | Pocasset | 5099887 | 2559 | 20 | PV & Battery | TBD | 2021-02-12 | 2021-02-12 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0
NSTAR | Acton | 5103412 | 1720 | 250 | PV | TBD | 2020-12-17 | 2021-02-12 | 41 |  | 41 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 5112763 | 1748 | 166.6 | PV | TBD | 2021-02-10 | 2021-02-10 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-17 | [7 empty] | 0 |  | 0 |  |  | 2022-06-27 | Online
NSTAR | Marston Mills | 5113061 | 2648 | 433 | PV | TBD | 2021-01-06 | 2021-02-10 | 25 |  | 25 | 2021-03-12 |  | -31587 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marston Mills | 5113167 | 2648 | 500 | PV | TBD | 2021-01-06 | 2021-02-10 | 25 |  | 25 | 2021-03-12 |  | -31587 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-03 | [7 empty] | 0 |  | 0
NSTAR | Acusnet | 5113369 | 2743 | 17.6 | PV & Battery | TBD | 2020-12-17 | 2021-02-16 | 43 |  | 43 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-06-07 | Online
NSTAR | Winchester | 5113444 | 1890 | 18 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Weston | 5113544 | 2493 | 33.8 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Framingham | 5113610 | 1701 | 35.2 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-23 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Ashland | 5113674 | 1721 | 22.6 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-08 | [7 empty] | 0 |  | 0 |  |  | 2022-03-03 | Online
NSTAR | Wayland | 5113728 | 1778 | 17.6 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 | 7 |  | 7 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Canton | 5113853 | 2021 | 18 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 | 7 |  | 7 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2021-04-20 | [6 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Carver | 5114629 | 2330 | 5000 | PV & Battery | TBD | 2020-11-25 | 2021-01-25 | 43 |  | 43 | 2021-03-12 |  | -31587 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5122500 | 2420 | 30.2 | PV & Battery | TBD | 2021-02-05 | 2021-02-16 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-03 | [7 empty] | 0 |  | 0 |  |  | 2021-10-14 | Online
NSTAR | Ashland | 5122724 | 1721 | 250 | PV | TBD | 2021-02-08 | 2021-02-16 | 6 |  | 6 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5122828 | 1746 | 499 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 5123008 | 2330 | 499 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | 5123184 | 2050 | 2000 | PV & Battery | TBD | 2021-01-27 | 2021-02-16 | 14 |  | 14 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medway | 5123430 | 2054 | 5000 | PV & Battery | TBD | 2020-12-31 | 2021-01-25 | 17 |  | 17 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | 5123449 | 1748 | 100 | PV | TBD | 2021-01-19 | 2021-01-20 | 1 |  | 1 | 2021-03-12 |  | -31587 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-11-19 | Online
NSTAR | Holliston | 5131879 | 1746 | 150 | PV | TBD | 2021-02-17 | 2021-02-17 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | 5131937 | 1721 | 200 | PV | TBD | 2021-02-17 | 2021-02-17 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5132026 | 1746 | 466.6 | PV | TBD | 2021-02-17 | 2021-02-17 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 5132026 | [7 empty] | 0 |  | 0 |  |  | 2022-08-03 | Online
NSTAR | East Wareham | 5132131 | 2538 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 | 15 |  | 15 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | 5132174 | 2719 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 | 15 |  | 15 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | 5132265 | 2452 | 499.9 | PV | TBD | 2021-01-27 | 2021-02-17 | 15 |  | 15 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | 5132388 | 2645 | 20 | Battery | TBD | 2021-02-08 | 2021-02-17 | 7 |  | 7 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2021-10-07 | Online
NSTAR | Carver | 5132501 | 2330 | 3000 | PV & Battery | 3-81-81 | 2018-10-04 | 2018-10-11 | 5 |  | 5 | 2018-10-31 |  | -30970 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Sharon | 5132549 | 2067 | 30 | PV & Battery | TBD | 2020-10-15 | 2021-02-17 | 89 |  | 89 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-18 | [7 empty] | 0 |  | 0
NSTAR | Holliston | 5140433 | 1746 | 100 | PV | TBD | 2021-02-18 | 2021-02-18 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5140517 | 1746 | 133.2 | PV | TBD | 2021-02-18 |  | -31571 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | 5140889 | 1746 | 150 | PV | TBD | 2021-02-18 | 2021-02-18 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5141509 | 1720 | 1125 | PV & Battery | TBD | 2020-12-31 | 2021-02-05 | 26 |  | 26 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 5141690 | 2717 | 25 | PV | TBD | 2020-12-30 | 2021-02-10 | 30 |  | 30 | 2021-03-03 |  | -31580 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  | 2021-08-27 | Online
NSTAR | Brewster | 5149756 | 2601 | 13.6 | PV & Battery | TBD | 2021-02-05 | 2021-02-08 | 1 |  | 1 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-20 | [7 empty] | 0 |  | 0 |  |  | 2021-06-16 | Online
NSTAR | Acton | 5149891 | 1720 | 84 | PV | TBD | 2021-02-10 | 2021-02-19 | 7 |  | 7 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-03-25 | [7 empty] | 0 |  | 0 |  |  | 2021-08-05 | Online
NSTAR | Lexington | 5149929 | 2421 | 19.86 | battery | TBD | 2021-02-19 | 2021-02-19 | 0 |  | 0 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Online
NSTAR | Natick | 5158094 | 1760 | 26.4 | PV & Battery | TBD | 2021-02-19 | 2021-03-01 | 6 |  | 6 | 2021-03-08 |  | -31583 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-12 | [7 empty] | 0 |  | 0 |  |  | 2022-07-14 | Online
NSTAR | Watertown | 5164450 | 2472 | 66.6 | PV | TBD | 2021-02-17 | 2021-02-22 | 3 |  | 3 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-03 | [7 empty] | 0 |  | 0 |  |  | 2021-10-01 | Online
NSTAR | Wayland | 5164657 | 1778 | 17.6 | PV & Battery | TBD | 2021-02-08 | 2021-02-22 | 10 |  | 10 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Sudbury | 5164789 | 1776 | 36 | PV & Battery | TBD | 2021-02-08 | 2021-02-22 | 10 |  | 10 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | 5164886 | 2492 | 19.84 | battery | TBD | 2021-02-18 | 2021-02-23 | 3 |  | 3 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-10-26 | Online
NSTAR | Ashland | 5174138 | 1721 | 199.8 | PV | TBD | 2021-02-23 |  | -31574 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-06 | [7 empty] | 0 |  | 0 |  |  | 2022-06-27 | Online
NSTAR | Marshfield | 5174339 | 2050 | 172 | PV | TBD | 2021-02-17 | 2021-02-23 | 4 |  | 4 | 2021-03-11 |  | -31586 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01
NSTAR | Orleans | 5174743 | 2653 | 18.32 | PV & Battery | TBD | 2021-02-18 | 2021-02-23 | 3 |  | 3 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | North Chatham | 5174898 | 2650 | 17.6 | battery | TBD | 2021-02-23 | 2021-02-25 | 2 |  | 2 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0 |  |  | 2021-10-15 | Online
NSTAR | East Falmouth | 5184793 | 2536 | 22.32 | PV & Battery | TBD | 2021-02-19 | 2021-02-25 | 4 |  | 4 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0
NSTAR | Plympton | 5184938 | 2367 | 233.2 | PV | TBD | 2021-02-25 | 2021-02-25 | 0 |  | 0 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-22 | [7 empty] | 0 |  | 0
NSTAR | Duxbury | 5193836 | 2332 | 19.5 | PV & Battery | TBD | 2021-02-19 | 2021-02-25 | 4 |  | 4 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2021-05-17 | Online
NSTAR | Mattapoisett | 5193909 | 2739 | 148.92 | PV | TBD | 2021-02-25 | 2021-02-25 | 0 |  | 0 | 2021-03-18 |  | -31591 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Orleans | 5202637 | 2653 | 262.5 | Fuel Cell | TBD | 2021-02-26 | 2021-02-26 | 0 |  | 0 | 2021-03-16 |  | -31589 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-07-21 | Online
NSTAR | Sharon | 5215247 | 2067 | 30.2 | PV & Battery | TBD | 2020-12-14 |  | -31523 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Harwich | 5233905 | 2645 | 72 | Wind | TBD | 2020-01-22 | 2021-03-02 | 289 |  | 289 | 2021-03-30 |  | -31599 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 5233972 | 2673 | 187.5 | PV & Battery | TBD | 2021-02-25 |  | -31576 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 5243395 | 2664 | 5325 | PV & Battery | TBD | 2021-02-17 | 2021-03-02 | 9 |  | 9 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 5243558 | 2360 | 1519.1 | PV & Battery | TBD | 2021-02-23 | 2021-03-02 | 5 |  | 5 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 5243871 | 2021 | 499 | PV & Battery | TBD | 2020-12-30 | 2021-03-02 | 44 |  | 44 | 2021-03-22 |  | -31593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0
NSTAR | Maynard | 5244434 | 1754 | 495.3 | PV | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-22 |  | -31593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | West Dennis | 5247195 | 2670 | 5 | battery | TBD | 2021-02-17 | 2021-03-05 | 12 |  | 12 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Natick | 5247213 | 1760 | 17.6 | PV & Battery | TBD | 2021-02-19 | 2021-03-05 | 10 |  | 10 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-01 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online
NSTAR | Weston | 5247231 | 2493 | 35.2 | PV | TBD | 2021-03-05 | 2021-03-05 | 0 |  | 0 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 5247359 | 2673 | 17.6 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-04 | Online
NSTAR | New Bedford | 5256352 | 2745 | 445 | PV | TBD | 2021-02-18 | 2021-03-05 | 11 |  | 11 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-21 | [7 empty] | 0 |  | 0
NSTAR | Harwich | 5256465 | 2645 | 255 | PV | TBD | 2021-02-18 | 2021-03-05 | 11 |  | 11 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-08 | [7 empty] | 0 |  | 0
NSTAR | Maynard | 5256556 | 1754 | 774.3 | PV | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Maynard | 5256604 | 1754 | 1400.5 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-24 |  | -31595 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | East Walpole | 5256722 | 2032 | 15.2 | PV | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-09 | [7 empty] | 0 |  | 0 |  |  | 2021-08-04 | Online
NSTAR | Marion | 5256768 | 2738 | 25.2 | PV & Battery | TBD | 2021-02-25 | 2021-03-05 | 6 |  | 6 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-14 | [7 empty] | 0 |  | 0
NSTAR | Brighton | 5256844 | 2135 | 43.2 | PV | TBD | 2021-02-03 | 2021-03-05 | 22 |  | 22 | 2021-03-22 |  | -31593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2022-02-07 | Online
NSTAR | Natick | 5273003 | 1760 | 19.86 | Battery | TBD | 2021-03-08 | 2021-03-08 | 0 |  | 0 | 2021-03-23 |  | -31594 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0 |  |  | 2022-01-19 | Online
NSTAR | Orleans | 5273198 | 2643 | 17.4 | PV | TBD | 2021-03-08 | 2021-03-08 | 0 |  | 0 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-06-16 | Online
NSTAR | Acton | 5273453 | 1720 | 30.2 | PV & Battery | TBD | 2021-03-08 | 2021-03-08 | 0 |  | 0 | 2021-03-23 |  | -31594 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | 5273636 | 2021 | 20 | PV & Battery | TBD | 2021-03-02 | 2021-03-08 | 4 |  | 4 | 2021-03-23 |  | -31594 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0 |  |  | 2021-09-17 | Online
NSTAR | Lincoln | 5273781 | 2748 | 15.2 | PV | TBD | 2021-03-09 | 2021-03-09 | 0 |  | 0 | 2021-03-23 |  | -31594 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-06 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Dartmouth | 5273833 | 2748 | 15 | PV & Battery | TBD | 2021-02-19 | 2021-03-05 | 10 |  | 10 | 2021-03-23 |  | -31594 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-14 | [7 empty] | 0 |  | 0 |  |  | 2021-09-08 | Online
NSTAR | Sharon | 5286859 | 2067 | 15.2 | PV | TBD | 2020-10-15 | 2021-03-02 | 98 |  | 98 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-05 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Jamaica Plain | 5287061 | 2130 | 18 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 | 9 |  | 9 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Truro | 5287511 | 2366 | 19.6 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 | 9 |  | 9 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Somerville | 5287647 | 2144 | 85.2 | PV | TBD | 2021-03-02 | 2021-03-10 | 6 |  | 6 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Arlington | 5298461 | 2474 | 17.68 | Battery | TBD | 2021-03-02 | 2021-03-10 | 6 |  | 6 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-10-24 | Online
NSTAR | Wellfleet | 5298773 | 2663 | 18.16 | PV & Battery | TBD | 2021-02-25 | 2021-03-10 | 9 |  | 9 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | East Wareham | 5299014 | 2538 | 19 | PV | TBD | 2021-02-19 | 2021-03-10 | 13 |  | 13 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2021-11-12 | Online
NSTAR | West Tisbury | 5299167 | 2575 | 16.225 | PV | TBD | 2021-03-02 | 2021-03-10 | 6 |  | 6 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-27 | [7 empty] | 0 |  | 0 |  |  | 2022-01-26 | Online
NSTAR | New Bedford | 5299345 | 2740 | 120 | PV | TBD | 2021-02-25 | 2021-03-10 | 9 |  | 9 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-14 | [7 empty] | 0 |  | 0 |  |  | 2021-09-30 | Online
NSTAR | Onset | 5308165 | 2053 | 33.3 | PV | TBD | 2021-02-12 | 2021-02-24 | 8 |  | 8 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-13 | [7 empty] | 0 |  | 0 |  |  | 2021-12-13 | Online
NSTAR | Arlington | 5308545 | 2474 | 4.93 | PV | TBD | 2021-02-23 | 2021-02-23 | 0 |  | 0 | 2021-03-26 |  | -31597 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 5317803 | 1803 | 35.2 | PV & Battery | TBD | 2020-12-14 | 2021-03-12 | 64 |  | 64 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-12 | [7 empty] | 0 |  | 0
NSTAR | Chestnut Hill | 5333163 | 2467 | 100.8 | PV | TBD | 2021-03-15 | 2021-03-15 | 0 |  | 0 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0 |  |  | 2022-04-20 | Online
NSTAR | West Barnstable | 5333489 | 2668 | 450 | PV | TBD | 2021-03-15 | 2021-03-15 | 0 |  | 0 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-19 | [7 empty] | 0 |  | 0
NSTAR | Needham | 5333657 | 2494 | 86.4 | PV | TBD | 2021-01-27 | 2021-03-15 | 33 |  | 33 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2022-03-31 | Online
NSTAR | Chestnut Hill | 5333799 | 2467 | 86.4 | PV | TBD | 2021-03-15 | 2021-03-15 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-01 | [7 empty] | 0 |  | 0
NSTAR | Yarmouth | 5333868 | 2673 | 999 | PV & Battery | TBD | 2021-03-02 | 2021-03-15 | 9 |  | 9 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | 5343412 | 1776 | 400 | PV | TBD | 2021-03-16 | 2021-03-15 | -3 |  | 0 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-08 | [7 empty] | 0 |  | 0
NSTAR | Milton | 5343599 | 2364 | 125 | PV | TBD | 2021-02-25 | 2021-03-16 | 13 |  | 13 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-09-15 | Online
NSTAR | Natick | 5343911 | 1760 | 10 | Battery | TBD | 2021-03-12 | 2021-03-16 | 2 |  | 2 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0 |  |  | 2023-03-09 | Online
NSTAR | Hatchville | 5344212 | 2536 | 44.98 | PV | TBD | 2021-03-15 | 2021-03-17 | 2 |  | 2 | 2021-03-31 |  | -31600 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-06 | [7 empty] | 0 |  | 0 |  |  | 2022-01-26 | Online
NSTAR | Needham | 5354359 | 2492 | 20 | PV & Battery | TBD | 2021-03-15 | 2021-03-17 | 2 |  | 2 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-01 | [7 empty] | 0 |  | 0
NSTAR | Natick | 5354616 | 1860 | 17.6 | PV & Battery | TBD | 2021-03-15 | 2021-03-17 | 2 |  | 2 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online
NSTAR | Hopkinton | 5354874 | 1748 | 240 | PV | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-14 | [7 empty] | 0 |  | 0
NSTAR | Hopkinton | 5354925 | 1748 | 233.2 | PV | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Online
NSTAR | Marston Mills | 5355181 | 2648 | 19.84 | Battery | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online
NSTAR | Needham | 5355247 | 2492 | 24.86 | Battery | TBD | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | New Bedford | 5355312 | 2744 | 480 | PV | 2-7-7 | 2021-03-17 | 2021-03-17 | 0 |  | 0 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | 2018-10-10 | [6 empty] | 0 |  | 0 |  |  |  |  | Private
NSTAR | Acton | 5367340 | 1720 | 199.8 | PV | TBD | 2021-03-02 | 2021-03-19 | 13 |  | 13 | 2021-04-02 |  | -31602 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5377708 | 1720 | 249.8 | PV | TBD | 2021-03-02 | 2021-03-19 | 13 |  | 13 | 2021-04-07 |  | -31605 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | 5377796 | 1720 | 249.8 | PV | TBD | 2021-03-02 | 2021-03-19 | 13 |  | 13 | 2021-04-06 |  | -31604 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | South Dartmouth | 5392200 | 2748 | 21.4 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Mashpee | 5392364 | 2649 | 17.6 | PV & Battery | TBD | 2021-03-12 | 2021-03-22 | 6 |  | 6 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-28 | [7 empty] | 0 |  | 0
NSTAR | Hyde Park | 5392588 | 2136 | 16 | PV | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0
NSTAR | Dorchester | 5392648 | 2125 | 15.2 | PV | TBD | 2021-02-12 | 2021-03-22 | 26 |  | 26 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-10 | [7 empty] | 0 |  | 0
NSTAR | Sharon | 5392760 | 2067 | 250 | PV | TBD | 2021-03-16 | 2021-03-22 | 4 |  | 4 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0
NSTAR | Dedham | 5392843 | 2026 | 250 | PV | TBD | 2021-03-17 | 2021-03-22 | 3 |  | 3 | 2021-05-04 |  | -31624 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-04 | [7 empty] | 0 |  | 0
NSTAR | Newton | 5392881 | 2459 | 19.84 | PV & Battery | TBD | 2021-03-17 | 2021-03-22 | 3 |  | 3 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online
NSTAR | Vineyard Haven | 5392988 | 2568 | 16.26 | PV & Battery | TBD | 2021-03-15 | 2021-03-22 | 5 |  | 5 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-01 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online
NSTAR | Framingham | 5393050 | 1701 | 10 | Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | 5393125 | 2360 | 499 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 5393165 | 2050 | 249 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-02 | [7 empty] | 0 |  | 0
NSTAR | Marshfield | 5393188 | 2050 | 249 | PV & Battery | TBD | 2021-03-22 | 2021-03-22 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5402282 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-01 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5403022 | 2420 | 250 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5403190 | 2420 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-01 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5403580 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0
NSTAR | Lexington | 5403662 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | 5403782 | 2421 | 125 | battery | TBD | 2021-03-12 | 2021-03-23 | 7 |  | 7 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | 5403892 | 1803 | 52.2 | PV | TBD | 2021-03-23 | 2021-03-23 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Newton | 5404047 | 2461 | 158.4 | PV | TBD | 2021-03-23 | 2021-03-23 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2022-06-20 | Online
NSTAR | Newton | 5404188 | 2461 | 86.4 | PV | TBD | 2021-03-23 | 2021-03-23 | 0 |  | 0 | 2021-04-08 |  | -31606 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0
NSTAR | Plymouth | 5414087 | 2360 | 1366.4 | PV & Battery | TBD | 2021-02-23 | 2021-03-02 | 5 |  | 5 | 2021-04-09 |  | -31607 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Freetown | 5415234 | 2717 | 1000 | PV & Battery | 2-102-608 | 2016-12-14 | 2016-12-27 | 9 |  | 9 | 2017-01-19 |  | -30506 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 2017-05-22 | 30592 |  | 30592 |  |  | 0 |  | 0 | 2018-08-22 | [7 empty] | 0 |  | 0 |  |  | 2022-12-28 | Online
NSTAR | Marston Mills | 5447070 | 2648 | 15.2 | PV | TBD | 2021-03-17 | 2021-03-29 | 8 |  | 8 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0
NSTAR | Natick | 5447224 | 1760 | 16.24 | PV | TBD | 2021-03-29 | 2021-03-29 | 0 |  | 0 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-19 | [7 empty] | 0 |  | 0
NSTAR | Burlington | 5447287 | 1803 | 17.6 | Battery | TBD | 2021-03-17 | 2021-03-29 | 8 |  | 8 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0
NSTAR | Dartmouth | 5447348 | 2748 | 27.28 | PV & Battery | TBD | 2021-03-17 |  | -31590 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-10-14 | Online
NSTAR | Plymouth | 5447376 | 2360 | 747 | PV & Battery | TBD | 2021-03-05 | 2021-03-29 | 16 |  | 16 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-10 | [7 empty] | 0 |  | 0
NSTAR | Centerville | 5447504 | 2632 | 15.68 | Battery | TBD | 2021-03-29 | 2021-03-29 | 0 |  | 0 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-22 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online
NSTAR | Brookline | 5447826 | 2445 | 25 | PV & Battery | TBD | 2020-12-16 | 2021-03-29 | 73 |  | 73 | 2021-04-13 |  | -31609 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-15 | [7 empty] | 0 |  | 0
NSTAR | East Walpole | 5483759 | 2032 | 26.4 | PV & Battery | TBD | 2021-03-29 | 2021-04-01 | 3 |  | 3 | 2021-04-16 |  | -31612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-13 | [7 empty] | 0 |  | 0 |  |  | 2021-12-01 | Online
NSTAR | East Wareham | 5483849 | 2538 | 21.4 | PV | TBD | 2021-03-29 | 2021-04-01 | 3 |  | 3 | 2021-04-16 |  | -31612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-21 | [7 empty] | 0 |  | 0 |  |  | 2021-10-21 | Online
NSTAR | Hyannis | 5483911 | 2601 | 400 | PV | TBD | 2021-03-16 | 2021-04-01 | 12 |  | 12 | 2021-04-16 |  | -31612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0
NSTAR | West Yarmouth | 5483954 | 2673 | 160 | PV | TBD | 2021-03-16 | 2021-04-01 | 12 |  | 12 | 2021-04-16 |  | -31612 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-04-30 | [7 empty] | 0 |  | 0 |  |  | 2021-06-15 | Online
NSTAR | Hyannisport | 5518451 | 2678 | 28 | Battery | TBD | 2021-04-09 | 2021-04-09 | 0 |  | 0 | 2021-04-21 |  | -31615 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0 |  |  | 2022-05-18 | Online
NSTAR | Plymouth | 5518643 | 2360 | 25 | PV & Battery | TBD | 2021-03-05 | 2021-03-05 | 0 |  | 0 | 2021-04-21 |  | -31615 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-06 | [7 empty] | 0 |  | 0 |  |  | 2022-02-16 | Online
NSTAR | Falmouth | 5518931 | 2540 | 27.6 | PV & Battery | TBD | 2021-01-26 | 2021-03-19 | 38 |  | 38 | 2021-04-21 |  | -31615 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Jamaica Plain | 5530688 | 2130 | 199.8 | PV | TBD | 2020-07-01 | 2021-04-06 | 199 |  | 199 | 2021-04-29 |  | -31621 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-24 | [7 empty] | 0 |  | 0 |  |  | 2022-08-24 | Online
NSTAR | Somerville | 5540752 | 2144 | 85.2 | PV | TBD | 2021-03-02 | 2021-03-15 | 9 |  | 9 | 2021-04-29 |  | -31621 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-12 | [7 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Hopkinton | 5566155 | 1748 | 1000 | PV | TBD | 2021-03-17 | 2021-04-13 | 19 |  | 19 | 2021-04-29 |  | -31621 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dedham | 5577223 | 2026 | 86.4 | PV | TBD | 2021-02-25 | 2021-04-12 | 32 |  | 32 | 2021-04-29 |  | -31621 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online
NSTAR | Framingham | 5587228 | 1702 | 167.32 | PV | TBD | 2021-04-13 | 2021-04-14 | 1 |  | 1 | 2021-04-29 |  | -31621 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 1932-09-13 | [7 empty] | 0 |  | 0
NSTAR | Walpole | 5608635 | 2081 | 15.2 | PV | TBD | 2020-09-08 | 2021-04-16 | 158 |  | 158 | 2021-05-05 |  | -31625 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0
NSTAR | South Dennis | 5758561 | 2660 | 20 | PV & Battery | TBD | 2020-12-07 | 2021-05-04 | 106 |  | 106 | 2021-05-19 |  | -31635 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-01 | [7 empty] | 0 |  | 0
NSTAR | Plympton | 5758591 | 2367 | 742 | PV & Battery | TBD | 2021-02-25 | 2021-05-04 | 48 |  | 48 | 2021-05-19 |  | -31635 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-15 | [7 empty] | 0 |  | 0
NSTAR | Chatham | 5813985 | 2633 | 100.8 | PV & Battery | TBD | 2020-08-19 | 2021-05-14 | 192 |  | 192 | 2021-05-27 |  | -31641 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-08 | [7 empty] | 0 |  | 0
NSTAR | Arlington | 5913979 | 2476 | 16 | Battery | TBD | 2020-09-14 |  | -31458 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0
NSTAR | Hatchville | 9568068 | 2536 | 4000 | PV & Battery |  | 2020-08-19 | 2020-08-24 | 3 | 0 | 3 | 2020-09-16 |  | -31460 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2020-12-01 | TBD |  | 30 |  |  | 0 |  | 0 |  |  |  | In Queue | Private
NSTAR | Kingston | 23815557 | 2364 | 19.27 | PV | 3-17-910 | 2019-12-05 | 2019-12-10 | 3 |  | 3 | 2020-01-15 |  | -31285 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-02-12 | [7 empty] | 0 |  | 0
NSTAR | Plympton | 2065453a | 2367 | 1000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | 2 |  | 2 | 2015-07-31 |  | -30122 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online | Private
NSTAR | Plympton | 2065453b | 2367 | 2000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | 2 |  | 2 | 2015-07-31 |  | -30122 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online | Private
NSTAR | Plympton | 2065453c | 2367 | 2000 | PV | 3-51-DSS | 2015-04-17 | 2015-04-21 | 2 |  | 2 | 2015-07-31 |  | -30122 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-03-17 | 2016-03-22 | [6 empty] | 0 |  | 0 |  |  | 2017-09-06 | Online | Private
NSTAR | Canton | 2093030b | 2021 | 990 | PV | 470-H7 | 2015-08-31 | 2015-09-04 | 4 |  | 4 | 2015-09-09 |  | -30150 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2016-02-23 | 2016-04-12 | [6 empty] | 0 |  | 0 |  |  |  | Cust Docs
NSTAR | Plymouth | 2155/2249 | 2360 | 4750 | PV | 3-89-89 | 2012-06-20 | 2012-07-09 | 12 | 4 | 8 | 2012-07-18 | 2012-08-27 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2012-08-28 |  | 2012-06-01 | No | EXP |  |  |  | 0 | 0 | 0 |  |  | 2014-12-02 | Online | Gov't | Y
NSTAR | Freetown | 2238661 - A | 2717 | 4090 | PV | 2-102-102 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-06 |  | -30692 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | 2238661 - B | 2717 | 4990 | PV | 2-102-102 | 2017-09-19 | 2017-09-19 | 0 |  | 0 | 2017-10-06 |  | -30692 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-12-31 | Online
NSTAR | Rochester | 2260703 - A | 2770 | 2000 | PV | 3-703-703 | 2018-01-08 | 2018-01-12 | 4 |  | 4 | 2018-01-31 |  | -30775 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-04-30
NSTAR | Rochester | 2260703 - B | 2770 | 540 | PV | 3-703-703 | 2018-01-08 | 2018-01-12 | 4 |  | 4 | 2018-01-31 |  | -30775 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2282256-A | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 | 2018-07-20 |  | -30897 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2282256-B | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 | 2018-07-20 |  | -30897 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2282256-C | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 | 2018-07-20 |  | -30897 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Boston | 2287285-B | 2125 | 500 | PV & Battery | 511-1497H | 2018-06-18 | 2018-07-02 | 10 |  | 10 | 2018-07-19 |  | -30896 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | 2287856-A | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-B | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-C | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-D | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-E | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-F | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-G | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Wareham | 2287856-H | 2576 | 499 | PV | 3-85-85 | 2018-05-10 | 2018-06-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Carver | 2292181 - A | 2330 | 2000 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | 4 |  | 4 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | 2292181 - B | 2330 | 466 | PV | 3-10-930 | 2018-08-02 | 2018-08-08 | 4 |  | 4 | 2018-08-16 |  | -30916 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | 2334473 & 2334854 | 2745 | 695.6 | PV | TBD | 2019-03-25 | 2020-03-29 | 264 |  | 264 | 2020-04-16 |  | -31351 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-10-05 | [7 empty] | 0 |  | 0
NSTAR | Winchester | 24-9982 | 1701 | 22 | PV & Battery | TBD | 2020-07-21 | 2020-07-21 | 0 |  | 0 | 2020-08-10 |  | -31433 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | ISO NE | 2770 | 15000 | PV & Battery | 3-703-703 | 2018-12-18 | 2018-12-18 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | MULTIPLE WOS | 2081 | 2167.6 | PV | 146-H4 | 2019-01-14 | 2019-03-28 | 53 |  | 53 | 2019-04-15 |  | -31088 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-05-31 | [7 empty] | 0 |  | 0
NSTAR | Rochester | pp02295853 | 2770 | 2000 | PV & Battery | 3-85-85 | 2021-01-17 | 2021-01-17 | 0 |  | 0 | 2021-03-22 |  | -31593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | PP02407747 | 2601 | 19.92 | PV | TBD | 2020-10-15 | 2020-11-12 | 20 |  | 20 | 2021-01-05 |  | -31539 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2020-12-06 | [7 empty] | 0 |  | 0 |  |  | 2021-07-28 | Online
NSTAR | Provincetown | TBD | 2657 | 28.13 | PV | TBD | 2019-08-06 | 2019-08-08 | 2 |  | 2 | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-09-20 | [7 empty] | 0 |  | 0 |  |  | 2019-01-06 | Online
NSTAR | Ashland | TBD | 1721 | 4450 | PV | TBD | 2017-05-08 | 2017-05-25 | 13 |  | 13 | 2017-06-15 |  | -30611 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2018-05-04 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Dedham | TBD | 2026 | 20 | PV | TBD | 2019-05-13 | 2019-05-13 | 0 |  | 0 | 2019-05-22 |  | -31115 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-06-12 | [7 empty] | 0 |  | 0 |  |  | 2019-12-31 | Online
NSTAR | Wareham | TBD | 2571 | 1750 | PV & Battery | 416-H1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-02-12 | Withdrawn
NSTAR | Somerville | TBD | 2145 | 22.8 | PV | TBD | 2020-06-02 |  | -31384 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2021-04-22 | Online
NSTAR | Lincoln | TBD | 1773 | 109.6 | PV & Battery | 416-H1 | 2018-01-10 |  | -30760 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2744 | 599.4 | PV | 2-54-54 | 2018-01-16 | 2018-03-14 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2744 | 599.4 | PV | 2-54-54 | 2018-01-23 | 2018-03-14 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | TBD | 2565 | 27.48 | PV & Battery | 416-H1 | 2018-02-21 |  | -30790 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Falmouth | TBD | 2565 | 15 | PV & Battery | 416-H1 | 2018-02-21 |  | -30790 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Weston | TBD | 2493 | 21.6 | PV & Battery | 416-H1 | 2018-02-21 |  | -30790 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Provincetown | TBD | 2657 | 10 | PV & Battery | 4-96-675 | 2018-02-22 |  | -30791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rcohester | TBD | 2770 | 22.6 | PV & Battery | 3-702-702 | 2018-02-22 |  | -30791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | TBD | 2576 | 18.35 | PV & Battery | 416-H1 | 2018-02-22 |  | -30791 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Darmouth | TBD | 2747 | 520 | PV & Battery | 2-525-525 | 2018-02-27 | 2018-03-12 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | TBD | 2743 | 8300 | PV & Battery | 416-H1 | 2018-03-01 | 2018-03-14 | 9 |  | 9 | 2018-04-11 |  | -30825 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lincoln | TBD | 1773 | 17.6 | PV & Battery | 416-H1 | 2018-03-16 |  | -30807 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chelsea | TBD | 2150 | 153.2 | PV | 416-H1 | 2018-03-22 | 2018-04-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chelsea | TBD | 2150 | 196.6 | PV | 416-H1 | 2018-03-22 | 2018-04-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Watertown | TBD | 2472 | 166.5 | PV | 467-H6 | 2018-03-29 | 2018-03-29 | 0 |  | 0 | 2018-04-19 |  | -30831 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | TBD | 2743 | 10 | PV & Battery | 2-241-241 | 2018-04-04 |  | -30820 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 9878 | PV & Battery | 416-H1 | 2018-04-06 |  | -30822 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dorchester | TBD | 2122 | 64 | PV | 416-H1 | 2018-04-12 | 2018-04-27 | 11 |  | 11 | 2018-05-07 |  | -30843 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2538 | 7.6 | PV | 416-H1 | 2018-04-19 |  | -30831 |  | 0 | 2018-04-18 |  | -30830 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1701 | 5 | PV | 342-H4 | 2018-04-26 |  | -30836 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Westport | TBD | 2770 | 4200 | PV & Battery | 4-80B-514 | 2018-04-30 | 2018-07-20 | 59 |  | 59 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Yarmouth | TBD | 2664 | 15.2 | PV | 4-90-90 | 2018-05-16 | 2018-06-13 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 2000 | PV | 416-H1 | 2018-05-18 | 2018-05-30 | 8 |  | 8 | 2018-06-12 |  | -30869 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 15.2 | PV | 416-H1 | 2018-05-23 | 2018-07-24 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | TBD | 2451 | 995 | PV & Battery | 416-H1 | 2018-05-29 |  | -30859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Ashland | TBD | 1721 | 57.6 | PV | 274-1429H1 | 2018-06-04 | 2018-06-06 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 300 | PV | 4-80B-514 | 2018-07-10 | 2018-07-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 660 | PV | 4-80B-514 | 2018-07-10 | 2018-07-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 360 | PV | 4-80B-514 | 2018-07-10 | 2018-07-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | TBD | 2748 | 18 | PV | 2-528-528 | 2018-07-17 | 2018-07-23 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 4000 | PV | 4-80B-514 | 2018-07-18 | 2018-07-23 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2744 | 685 | PV | 2-41-41 | 2018-08-06 | 2018-08-09 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | TBD | 2142 | 63.3 | PV | 416-H1 | 2018-09-24 | 2018-09-27 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Wareham | TBD | 2576 | 143.2 | PV | TBD | 2019-01-24 |  | -31031 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dennis | TBD | 2660 | 4951 | PV | TBD | 2019-01-25 |  | -31032 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acton | TBD | 1720 | 43.2 | PV | TBD | 2019-02-07 |  | -31041 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2717 | 4980 | PV & Battery | TBD | 2019-02-11 |  | -31043 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | TBD | 2492 | 23.5 | PV | TBD | 2019-02-12 |  | -31044 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1701 | 81 | PV | TBD | 2019-02-22 | 2019-02-22 | 0 |  | 0 | 2019-02-22 |  | -31052 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2019-12-20 | [7 empty] | 0 |  | 0
NSTAR | Hyannis | TBD | 2601 | 699.9 | PV | TBD | 2019-03-04 |  | -31058 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2571 | 15.485 | PV | TBD | 2019-03-13 |  | -31065 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mattapoisett | TBD | 2739 | 5000 | PV | TBD | 2019-03-13 |  | -31065 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2702 | 4500 | PV & Battery | tbd | 2019-04-10 |  | -31085 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2745 | 5000 | PV | TBD | 2019-04-26 |  | -31097 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Cambridge | TBD | 2138 | 66.6 | PV | TBD | 2019-05-09 |  | -31106 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | West Newton | TBD | 2465 | 20 | PV & Battery | TBD | 2019-05-31 |  | -31122 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Milton | TBD | 2186 | 25.2 | PV & Battery | TBD | 2019-06-05 |  | -31125 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Burlington | TBD | 1803 | 15.2 | PV | TBD | 2019-08-01 |  | -31166 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | TBD | 2710 | 100 | PV | TBD | 2019-08-05 |  | -31168 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Duxbury | TBD | 2332 | 25.2 | PV | TBD | 2019-08-07 |  | -31170 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Truro | TBD | 2666 | 16.4 | PV | TBD | 2019-08-28 |  | -31185 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 2000 | PV & Battery | TBD | 2019-09-05 |  | -31191 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2717 | 4000 | PV & Battery | TBD | 2019-09-11 |  | -31195 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyannis | TBD | 2601 | 998 | PV | TBD | 2019-10-11 |  | -31217 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | TBD | 2050 | 15.2 | PV | TBD | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | TBD | 1760 | 15.2 | PV | TBD | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | TBD | 2364 | 15.2 | PV | TBD | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sharon | TBD | 2067 | 15.2 | PV | TBD | 2019-10-18 |  | -31222 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 15.2 | PV | TBD | 2019-10-21 |  | -31223 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2571 | 15.2 | PV | TBD | 2019-10-24 |  | -31226 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | TBD | 2136 | 19 | PV | TBD | 2019-10-31 |  | -31231 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | TBD | 2535 | 180.96 | PV | TBD | 2019-11-04 |  | -31233 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Onset | TBD | 2558 | 25 | PV & Battery | TBD | 2019-11-21 |  | -31246 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Oaks Bluff | TBD | 2557 | 2000 | PV & Battery | TBD | 2019-12-02 |  | -31253 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Kingston | TBD | 2364 | 19.27 | PV | TBD | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | TBD | 2136 | 330 | PV | TBD | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Needham | TBD | 2494 | 3623 | PV | TBD | 2019-12-05 |  | -31256 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Woburn | TBD | 2453 | 748 | PV | TBD | 2019-12-09 |  | -31258 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1702 | 15.2 | PV | TBD | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Lexington | TBD | 2421 | 130 | PV | TBD | 2019-12-10 |  | -31259 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | East Walpole | TBD | 2032 | 23.8 | PV | TBD | 2019-12-11 |  | -31260 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | TBD | 2360 | 865.8 | PV | TBD | 2019-12-18 |  | -31265 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | TBD | 2360 | 865.8 | PV | TBD | 2019-12-18 | 2019-12-23 | 3 |  | 3 | 2020-01-14 |  | -31284 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | TBD | 2130 | 37.8 | PV | TBD | 2020-01-06 |  | -31278 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Boston | TBD | 2120 | 200 | PV | TBD | 2020-01-08 |  | -31280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | North Falmouth | TBD | 2556 | 15.2 | PV | TBD | 2020-01-08 |  | -31280 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Oaks Bluff | TBD | 2557 | 1500 | PV & Battery | TBD | 2020-01-23 |  | -31291 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 6 | PV | TBD | 2020-01-28 |  | -31294 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | TBD | 2050 | 20 | Battery | TBD | 2020-01-28 |  | -31294 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | TBD | 2748 | 14 | Battery | TBD | 2020-01-29 |  | -31295 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Walpole | TBD | 2081 | 16 | PV | TBD | 2020-02-13 |  | -31306 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dartmouth | TBD | 2714 | 2958 | Battery | TBD | 2020-02-20 |  | -31311 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wayland | TBD | 1778 | 29 | Battery | TBD | 2020-02-21 |  | -31312 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Plymouth | TBD | 2360 | 15.2 | PV | TBD | 2020-02-24 |  | -31313 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Mashpee | TBD | 2649 | 153.85 | PV | TBD | 2020-03-03 |  | -31319 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dedham | TBD | 2026 | 108.375 | PV | TBD | 2020-03-03 |  | -31319 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sagamore Beach | TBD | 2561 | 150.45 | PV | TBD | 2020-03-05 |  | -31321 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Natick | TBD | 1760 | - | PV | TBD | 2020-03-09 |  | -31323 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | TBD | 2451 | 8.5 | PV | TBD | 2020-03-20 |  | -31332 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Harwich | TBD | 2645 | 175.9 | PV | TBD | 2020-03-25 | 2020-05-15 | 37 |  | 37 | 2020-06-10 |  | -31390 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 9999 | PV & Battery | TBD | 2020-04-09 | 2020-04-15 | 4 |  | 4 | 2020-04-27 |  | -31358 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1702 | 400 | PV | TBD | 2020-04-09 | 2020-04-17 | 6 |  | 6 | 2020-05-04 |  | -31363 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 999 | PV & Battery | TBD | 2020-04-09 |  | -31346 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Duxbury | TBD | 2332 | 15.2 | PV | TBD | 2020-05-28 |  | -31381 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | TBD | 2563 | 90 | Battery | TBD | 2020-05-28 |  | -31381 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Waltham | TBD | 2451 | 15.2 | PV | TBD | 2020-05-28 |  | -31381 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Freetown | TBD | 2717 | 5000 | PV & Battery | TBD | 2020-05-28 |  | -31381 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Bellingham | TBD | 2019 | 4990 | PV & Battery | TBD | 2020-06-08 |  | -31388 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | TBD | 2145 | 22.8 | PV | TBD | 2020-06-15 |  | -31393 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sandwich | TBD | 2563 | 499 | PV & Battery | TBD | 2020-06-19 |  | -31397 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Dover | TBD | 2030 | 15.2 | PV | TBD | 2020-07-22 |  | -31420 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1702 | 573 | PV & Battery | TBD | 2020-07-29 |  | -31425 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Acusnet | TBD | 2743 | 610 | Battery | TBD | 2020-08-19 |  | -31440 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Aquinnah | TBD | 2635 | 144.8 | PV & Battery | TBD | 2020-08-19 |  | -31440 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sherborn | TBD | 1770 | 39 | PV & Battery | TBD | 2020-08-25 |  | -31444 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | TBD | 1748 | 4000 | PV & Battery | TBD | 2020-09-02 |  | -31450 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 2875 | PV | TBD | 2020-09-18 |  | -31462 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | New Bedford | TBD | 2740 | 250 | PV | TBD | 2020-09-22 |  | -31464 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medfield | TBD | 2052 | 200 | PV | TBD | 2020-10-27 |  | -31489 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 5 | battery | TBD | 2020-11-06 |  | -31497 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Chilmark | TBD | 2535 | 20.5 | Battery | TBD | 2020-11-13 |  | -31502 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 16.19 | PV | TBD | 2020-11-25 |  | -31510 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 149.3 | PV | TBD | 2020-12-07 |  | -31518 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Framingham | TBD | 1701 | 17.6 | PV & Battery | TBD | 2020-12-07 |  | -31518 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Milton | TBD | 2186 | 15.2 | PV | TBD | 2020-12-31 |  | -31536 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Holliston | TBD | 1757 | 180 | PV | TBD | 2021-01-20 |  | -31550 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hopkinton | TBD | 1748 | 18.5 | PV | TBD | 2021-01-21 |  | -31551 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Carver | TBD | 2330 | 3000 | PV & Battery | TBD | 2021-01-27 |  | -31555 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Medfield | TBD | 2052 | 15 | PV | TBD | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Canton | TBD | 2021 | 16 | PV | TBD | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Rochester | TBD | 2770 | 2000 | PV | TBD | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Wareham | TBD | 2571 | 4990 | PV & Battery | TBD | 2021-02-17 |  | -31570 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Somerville | TBD | 2144 | 170.4 | PV | TBD | 2021-02-18 |  | -31571 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Arlington | TBD | 2474 | 15.2 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Kingston | TBD | 2364 | 1 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Withdrawn
NSTAR | Centerville | TBD | 2632 | 15.2 | PV | TBD | 2021-02-25 |  | -31576 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Hyde Park | TBD | 2136 | 15 | PV | TBD | 2021-03-02 |  | -31579 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Auburndale | TBD | 2466 | 10 | Battery | TBD | 2021-03-22 |  | -31593 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Sudbury | TBD | 1776 | 500 | PV | TBD | 2021-03-19 |  | -31592 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Marshfield | TBD | 2050 | 1500 | PV | TBD | 2021-03-29 |  | -31598 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0
NSTAR | Fairhaven | ESMAEX-00027 | 02719 | 300 | Battery | 2-221-221 | 2021-04-02 | 2021-05-21 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2024-06-11 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_654 Arsene
NSTAR | Fairhaven | ESMAEX-00028 | 02719 | 223 | Battery | 2-220-206 | 2021-04-02 | 2021-05-20 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-03 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_654 Arsene
NSTAR | Newton Highlands | ESMAEX-00002 | 02461 | 7.68 | Battery | 292-H14 | 2021-03-29 | 2021-04-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-26 | [7 empty] | 0 |  | 0 |  |  | 2021-08-11 | Online | [7 empty] | 20
NSTAR | Brewster | ESMAEX-00097 | 02631 | 57.6 | Solar | 4-89B-946 | 2021-05-03 | 2021-06-11 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2023-07-17 | Online | [8 empty] | STA_975 Orleans
NSTAR | Canton | ESMAEX-00034 | 02021 | 250 | Solar | 470-H11 | 2021-04-07 | 2021-05-03 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-29 | [7 empty] | 0 |  | 0 |  |  | 2023-06-26 | Online | [8 empty] | STA_470 Canton
NSTAR | Lexington | ESMAEX-00010 | 02421 | 420 | Solar | 320-H5XY | 2021-03-30 | 2021-04-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-12 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Online | [8 empty] | STA_320 Lexington
NSTAR | New Bedford | ESMAEX-00009 | 02745 | 73.3 | Solar | 2-104-104 | 2021-03-30 | 2021-04-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-08 | [7 empty] | 0 |  | 0 |  |  | 2021-09-22 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Marion | ESMAEX-00063 | 02738 | 21.21 | Solar & Battery | 3-85-85 | 2021-04-21 | 2021-05-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-27 | [7 empty] | 0 |  | 0 |  |  | 2021-11-04 | Online |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | Plymouth | ESMAEX-00166 | 02360 | 8.7 | Solar | 3-89-89 | 2021-06-04 | 2021-07-06 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-08 | [7 empty] | 0 |  | 0 |  |  | 2022-01-26 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | South Sandwich | ESMAEX-00143 | 02563 | 10 | Battery | 4-455-455 | 2021-05-20 | 2021-06-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-27 | [7 empty] | 0 |  | 0 |  |  | 2023-12-11 | Online |  |  |  | Cape |  |  |  |  | STA_946 Mashpee
NSTAR | Newton Highlands | ESMAEX-00023 | 02461 | 18.88 | Solar & Battery | 292-H5 | 2021-04-02 | 2021-04-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-26 | [7 empty] | 0 |  | 0 |  |  | 2022-01-04 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Walpole | ESMAEX-00020 | 02081 | 20 | Solar & Battery | 146-H4 | 2021-04-01 | 2021-04-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-09 | [7 empty] | 0 |  | 0 |  |  | 2022-11-22 | Online | [8 empty] | STA_146 Walpole
NSTAR | Mattapoisett | ESMAEX-00425 | 02739 | 79.75 | Solar | 2-304-304 | 2021-09-20 | 2021-10-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-02-14 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Brighton | ESMAEX-00030 | 02135 | 150 | Internal Combustion Engine | 467-H12 | 2021-04-06 | 2021-05-04 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-15 | [7 empty] | 0 |  | 0 |  |  | 2021-12-28 | Online | [8 empty] | STA_467 Watertown
NSTAR | New Bedford | ESMAEX-00049 | 02745 | 166.6 | Solar | 2-82-82 | 2021-04-14 | 2021-05-12 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2022-04-19 | Online | [8 empty] | STA_612 Acushnet
NSTAR | Acton | ESMAEX-00032 | 01720 | 3800 | Solar & Battery | 416-H8 | 2021-04-07 | 2021-04-20 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study | [6 empty] | 2021 ASO Batch 1 |  | STA_416 Maynard
NSTAR | Needham | ESMAEX-00041 | 02494 | 250 | Solar | 148-H7 | 2021-04-13 | 2021-05-11 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-24 | Online | [8 empty] | STA_148 Needham
NSTAR | South Yarmouth | ESMAEX-00060 | 02664 | 250 | Battery |  | 2021-04-19 | 2021-05-04 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2024-06-18 | Online | [7 empty] | 250
NSTAR | Jamaica Plain | ESMAEX-00065 | 02130 | 30 | Solar | 396-1050H5 | 2021-04-21 | 2021-05-11 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-11-09 | Online
NSTAR | Holliston | ESMAEX-00058 | 01746 | 133.2 | Solar | 65-H2 | 2021-04-16 | 2021-05-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2022-12-07 | Online | [8 empty] | STA_065 Medway
NSTAR | New Bedford | ESMAEX-00053 | 02740 | 100 | Solar | 2-42-42 | 2021-04-14 | 2021-05-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-17 | [7 empty] | 0 |  | 0 |  |  | 2025-03-07 | Online | [8 empty] | STA_611 Pine Street
NSTAR | Bourne | ESMAEX-00059 | 02532 | 499 | Solar & Battery | 4-86-86 | 2021-04-16 | 2021-05-14 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_915 Otis
NSTAR | Waquoit | ESMAEX-00367 | 02536 | 20 | Solar & Battery | 4-77B-456 | 2021-08-27 | 2021-09-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-10 | [7 empty] | 0 |  | 0 |  |  | 2022-04-27 | Online
NSTAR | South Sandwich | ESMAEX-00055 | 02563 | 250 | Solar | 4-87A-87A | 2021-04-14 | 2021-05-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Online |  |  |  | Cape |  |  |  |  | STA_916 Sandwich
NSTAR | Brewster | ESMAEX-00096 | 02631 | 57.6 | Solar | 4-89B-946 | 2021-05-03 | 2021-06-11 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2023-07-17 | Online | [8 empty] | STA_975 Orleans
NSTAR | Eastham | ESMAEX-00073 | 02642 | 18.41 | Solar & Battery | 4-94A-94A | 2021-04-23 | 2021-06-04 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2021-11-02 | Online | [8 empty] | STA_975 Orleans
NSTAR | New Bedford | ESMAEX-00062 | 02740 | 16.57 | Solar & Battery | 2-531-531 | 2021-04-20 | 2021-05-18 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2021-11-10 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Acton | ESMAEX-00071 | 01720 | 16.23 | Solar | 416-H9 | 2021-04-23 | 2021-05-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online | [7 empty] | 10 | STA_416 Maynard
NSTAR | Chatham | ESMAEX-00070 | 02633 | 22 | Solar & Battery | 4-95B-941 | 2021-04-22 | 2021-06-02 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online | [7 empty] | 11.52 | STA_975 Orleans
NSTAR | Plympton | ESMAEX-00081 | 02367 | 999 | Solar & Battery | 3-15-15 | 2021-04-28 | 2021-06-01 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study
NSTAR | East Freetown | ESMAEX-00079 | 02717 | 69.2 | Solar | 2-102-102 | 2021-04-28 | 2021-05-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2023-03-28 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | East Freetown | ESMAEX-00080 | 02717 | 69.2 | Solar | 2-102-604 | 2021-04-28 | 2021-05-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Woburn | ESMAEX-00082 | 01801 | 17.4 | Solar | 533-H9 | 2021-04-28 | 2021-05-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-21 | [7 empty] | 0 |  | 0 |  |  | 2022-02-04 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Holliston | ESMAEX-00101 | 01746 | 140 | Solar | 65-H2 | 2021-05-05 | 2021-05-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-18 | [7 empty] | 0 |  | 0 |  |  | 2022-04-18 | Online | [8 empty] | STA_065 Medway
NSTAR | Eastham | ESMAEX-00276 | 02642 | 20 | Solar & Battery | 4-94A-94A | 2021-07-30 | 2021-08-16 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-25 | [7 empty] | 0 |  | 0 |  |  | 2022-03-10 | Online | [8 empty] | STA_975 Orleans
NSTAR | Falmouth | ESMAEX-00132 | 02540 | 5 | Solar | 4-76-436 | 2021-05-18 | 2021-06-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-12-08 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | West Falmouth | ESMAEX-00109 | 02574 | 17.772 | Solar & Battery | 4-98A-98A | 2021-05-07 | 2021-06-04 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2021-11-15 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Waltham | ESMAEX-00098 | 02451 | 1994 | Internal Combustion Engine | 526-1361H | 2021-05-03 | 2021-05-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2024-06-05 | Online | [6 empty] | 2021 ASO Batch 1 | 0 | STA_450 Trapelo Road
NSTAR | East Harwich | ESMAEX-00111 | 02645 | 20 | Battery | 4-95A-95A | 2021-05-10 | 2021-06-22 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2022-04-06 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | North Cambridge | ESMAEX-00182 | 02140 | 22.8 | Solar | 824-25 | 2021-06-13 | 2021-06-30 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-14 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online | [8 empty] | STA_828 Alewife
NSTAR | North Dartmouth | ESMAEX-00102 | 02747 | 86.4 | Solar | 2-533-503 | 2021-05-05 | 2021-05-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-10 | [7 empty] | 0 |  | 0 |  |  | 2022-02-03 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Westport | ESMAEX-00104 | 02790 | 20 | Solar | 2-532-532 | 2021-05-05 | 2021-06-04 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2021-09-24 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Needham | ESMAEX-00121 | 02492 | 18.56 | Solar | 148-H7 | 2021-05-13 | 2021-05-27 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2021-12-02 | Online | [8 empty] | STA_148 Needham
NSTAR | Framingham | ESMAEX-00105 | 01701 | 16 | Solar | 342-H4 | 2021-05-05 | 2021-05-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-03 | [7 empty] | 0 |  | 0 |  |  | 2021-08-04 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Natick | ESMAEX-00122 | 01760 | 251.3 | Solar | 433-H12 | 2021-05-13 | 2021-05-27 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-10 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Dorchester | ESMAEX-00108 | 02124 | 15.2 | Solar | 496-H8 | 2021-05-06 | 2021-05-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-04-15 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Waltham | ESMAEX-00113 | 02451 | 3012 | Internal Combustion Engine | 531-1359H | 2021-05-10 | 2021-06-18 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-11 | [7 empty] | 0 |  | 0 |  |  |  | Technical Review | [6 empty] | 2021 ASO Batch 1 |  | STA_450 Trapelo Road
NSTAR | Brighton | ESMAEX-00117 | 02135 | 100 | Solar | 329-H6 | 2021-05-11 | 2021-06-11 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-20 | [7 empty] | 0 |  | 0 |  |  | 2023-04-20 | Online | [8 empty] | STA_329 Brighton
NSTAR | South Boston | ESMAEX-00116 | 02127 | 100 | Solar | 385-H1 | 2021-05-11 | 2021-06-11 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2023-04-20 | Online | [8 empty] | STA_385D K Street
NSTAR | Waban | ESMAEX-00119 | 02468 | 10 | Battery | 292-H2 | 2021-05-13 | 2021-06-15 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-01 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Arlington | ESMAEX-00151 | 02476 | 20 | Solar | 320-H7 | 2021-05-27 | 2021-06-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-01-13 | Online | [8 empty] | STA_320 Lexington
NSTAR | Chatham | ESMAEX-00138 | 02633 | 10.15 | Solar | 4-95B-941 | 2021-05-19 | 2021-06-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-16 | [7 empty] | 0 |  | 0 |  |  | 2021-07-27 | Online | [8 empty] | STA_975 Orleans
NSTAR | Falmouth | ESMAEX-00124 | 02540 | 36.54 | Solar | 4-72-72 | 2021-05-15 | 2021-06-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-19 | [7 empty] | 0 |  | 0 |  |  | 2022-01-10 | Online | [8 empty] | STA_933 Falmouth
NSTAR | Weston | ESMAEX-00142 | 02493 | 20 | Solar & Battery | 282-H1 | 2021-05-20 | 2021-06-15 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-28 | [7 empty] | 0 |  | 0 |  |  | 2021-08-24 | Online | [8 empty] | STA_282 Waltham
NSTAR | Ashland | ESMAEX-00148 | 01721 | 75 | Solar | 274-H1 | 2021-05-24 | 2021-06-16 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2022-05-31 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Waban | ESMAEX-00139 | 02468 | 15 | Solar & Battery | 292-H7 | 2021-05-19 | 2021-05-20 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-22 | [7 empty] | 0 |  | 0 |  |  | 2021-10-08 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Woburn | ESMAEX-00141 | 01801 | 20 | Solar & Battery | 391-H11 | 2021-05-20 | 2021-06-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-27 | [7 empty] | 0 |  | 0 |  |  | 2021-12-07 | Online | [8 empty] | STA_391 Burlington
NSTAR | Forestdale | ESMAEX-00149 | 02644 | 20 | Solar & Battery | 4-81B-443 | 2021-05-25 | 2021-06-11 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online |  |  |  | Cape |  |  |  | 9.6 | STA_916 Sandwich
NSTAR | Hopkinton | ESMAEX-00145 | 01748 | 250 | Solar | 126-H1 | 2021-05-21 | 2021-05-26 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-06-17 | [7 empty] | 0 |  | 0 |  |  | 2022-06-03 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Woburn | ESMAEX-00380 | 01801 | 216 | Solar | 375-H6 | 2021-09-02 | 2021-09-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-29 | [7 empty] | 0 |  | 0 |  |  | 2022-05-19 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Burlington | ESMAEX-00175 | 01803 | 499.5 | Solar | 391-H12 | 2021-06-08 | 2021-06-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2025-01-14 | Online | [8 empty] | STA_391 Burlington
NSTAR | North Harwich | ESMAEX-00217 | 02645 | 10 | Battery | 4-89A-89A | 2021-06-28 | 2021-07-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-20 | [7 empty] | 0 |  | 0 |  |  | 2022-08-09 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Winchester | ESMAEX-00169 | 01890 | 2.03 | Solar | 211-H7XY | 2021-06-07 | 2021-06-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-10 | [7 empty] | 0 |  | 0 |  |  | 2021-12-17 | Online | [8 empty] | STA_211 Woburn
NSTAR | Mattapan | ESMAEX-00192 | 02126 | 78.8 | Solar | 496-H8 | 2021-06-18 | 2021-07-27 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-23 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Burlington | ESMAEX-00174 | 01803 | 233.1 | Solar | 391-H12 | 2021-06-08 | 2021-06-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2024-06-03 | Online | [8 empty] | STA_391 Burlington
NSTAR | Marstons Mills | ESMAEX-00172 | 02648 | 20.67 | Battery | 4-88-88 | 2021-06-08 | 2021-06-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-29 | Online |  |  |  | Cape |  |  |  |  | STA_946 Mashpee
NSTAR | Sudbury | ESMAEX-00171 | 01776 | 34.2 | Solar | 342-H8 | 2021-06-08 | 2021-06-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2022-01-13 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Burlington | ESMAEX-01605 | 01803 | 43.2 | Solar | 346-1395H1 | 2022-09-19 | 2022-10-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-24 | Online | [8 empty] | STA_391 Burlington
NSTAR | Carlisle | ESMAEX-00234 | 01741 | 15 | Battery | 533-H8 | 2021-07-12 | 2021-07-27 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2021-10-06 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Plymouth | ESMAEX-00822 | 02360 | 40.4 | Solar & Battery | 3-90-90 | 2022-02-08 | 2022-02-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Chestnut Hill | ESMAEX-00176 | 02467 | 16.57 | Solar & Battery | 467-H12 | 2021-06-09 | 2021-06-25 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-07 | [7 empty] | 0 |  | 0 |  |  | 2022-03-18 | Online | [7 empty] | 16.58 | STA_467 Watertown
NSTAR | Plympton | ESMAEX-00197 | 02367 | 499 | Solar | 3-15-15 | 2021-06-21 | 2021-07-27 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 499
NSTAR | Pocasset | ESMAEX-00188 | 02559 | 36.83 | Solar |  | 2021-06-15 | 2021-07-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Online
NSTAR | Medway | ESMAEX-00184 | 02053 | 22 | Solar & Battery | 65-H3 | 2021-06-14 | 2021-06-30 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-13 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online | [7 empty] | 12 | STA_065 Medway
NSTAR | Mattapoisett | ESMAEX-00189 | 02739 | 9 | Solar | 2-306-306 | 2021-06-16 | 2021-07-01 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2022-01-10 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Truro | ESMAEX-00190 | 02666 | 50 | Solar & Battery | 4-96-96 | 2021-06-16 | 2021-07-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-26 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online | [7 empty] | 30 | STA_976 Wellfleet
NSTAR | Oak Bluffs | ESMAEX-00193 | 02557 | 19.92 | Solar | 4-99-224 | 2021-06-19 | 2021-07-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-08 | [7 empty] | 0 |  | 0 |  |  | 2021-11-04 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Kingston | ESMAEX-00196 | 02364 | 7.6 | Solar & Battery | 3-18-18 | 2021-06-21 | 2021-07-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-15 | [7 empty] | 0 |  | 0 |  |  | 2021-09-17 | Online
NSTAR | Walpole | ESMAEX-00191 | 02081 | 15.2 | Solar | 456-H1 | 2021-06-17 | 2021-07-06 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-09 | [7 empty] | 0 |  | 0 |  |  | 2021-12-13 | Online | [8 empty] | STA_456 Dover
NSTAR | Assonett | ESMAEX-00195 | 02702 | 15.2 | Solar | 2-606-606 | 2021-06-21 | 2021-08-03 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2022-01-20 | Online | [8 empty] | STA_661 Bell Rock
NSTAR | Bedford | ESMAEX-00211 | 01730 | 17.6 | Solar | 322-1397H1 | 2021-06-24 | 2021-07-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-22 | [7 empty] | 0 |  | 0 |  |  | 2021-10-05 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Mattapoisett | ESMAEX-00200 | 02739 | 18.28 | Solar | 2-306-306 | 2021-06-22 | 2021-07-27 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-02 | [7 empty] | 0 |  | 0 |  |  | 2021-12-22 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Cambridge | ESMAEX-00251 | 02139 | 129.6 | Solar | 875-1328 | 2021-07-20 | 2021-09-24 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Online | [8 empty] | STA_875 East Cambridge
NSTAR | Hopkinton | ESMAEX-00228 | 01748 | 20 | Solar | 65-H7 | 2021-07-06 | 2021-07-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-09-13 | Online | [8 empty] | STA_065 Medway
NSTAR | Lincoln | ESMAEX-00206 | 01773 | 17.6 | Solar | 320-H8 | 2021-06-23 | 2021-07-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-07-22 | [7 empty] | 0 |  | 0 |  |  | 2022-03-29 | Online | [8 empty] | STA_320 Lexington
NSTAR | Lexington | ESMAEX-00235 | 02421 | 33.3 | Solar | 34-1352H1 | 2021-07-13 | 2021-08-03 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-12 | [7 empty] | 0 |  | 0 |  |  | 2022-06-20 | Online | [8 empty] | STA_320 Lexington
NSTAR | Lexington | ESMAEX-00210 | 02421 | 15.2 | Solar | 320-H5XY | 2021-06-24 | 2021-07-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2021-12-28 | Online | [8 empty] | STA_320 Lexington
NSTAR | Natick | ESMAEX-00213 | 01760 | 12.6 | Solar & Battery | 240-H6 | 2021-06-25 | 2021-07-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-14 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online | [8 empty] | STA_240 Framingham
NSTAR | East Falmouth | ESMAEX-00215 | 02536 | 15.2 | Solar | 4-98B-449 | 2021-06-25 | 2021-07-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-01 | [7 empty] | 0 |  | 0 |  |  | 2021-10-08 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Waban | ESMAEX-00218 | 02468 | 25 | Solar & Battery | 1701 | 2021-06-28 | 2021-07-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-09 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Dover | ESMAEX-00293 | 02030 | 3.8 | Solar | 456-H5 | 2021-08-09 | 2021-08-19 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-15 | [7 empty] | 0 |  | 0 |  |  | 2023-11-02 | Online | [8 empty] | STA_456 Dover
NSTAR | Sudbury | ESMAEX-00259 | 01776 | 20 | Solar | 342-H6 | 2021-07-22 | 2021-08-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2022-03-16 | Online | [8 empty] | STA_342 Sudbury
NSTAR | West Wareham | ESMAEX-00219 | 02576 | 15.2 | Solar | 3-85-85 | 2021-06-29 | 2021-07-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-05 | [7 empty] | 0 |  | 0 |  |  | 2021-10-22 | Online |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | Framingham | ESMAEX-00222 | 01701 | 9.8 | Solar & Battery | 342-H4 | 2021-07-01 | 2021-07-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Lincoln | ESMAEX-00226 | 01773 | 12.6 | Solar & Battery | 320-H6 | 2021-07-02 | 2021-07-21 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-03 | [7 empty] | 0 |  | 0 |  |  | 2022-03-15 | Online | [8 empty] | STA_320 Lexington
NSTAR | Dartmouth | ESMAEX-00238 | 02747 | 148.92 | Solar | 2-532-532 | 2021-07-13 | 2021-07-28 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2023-09-25 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Westwood | ESMAEX-00265 | 02090 | 76 | Solar | 148-H3 | 2021-07-26 | 2021-08-24 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Online | [8 empty] | STA_148 Needham
NSTAR | Arlington | ESMAEX-00304 | 02474 | 17.6 | Solar & Battery | 211-H3 | 2021-08-12 | 2021-09-15 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-27 | Online | [8 empty] | STA_211 Woburn
NSTAR | Maynard | ESMAEX-00232 | 01754 | 17.8 | Solar & Battery | 355-04 | 2021-07-12 | 2021-08-16 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-12-28 | Online | [8 empty] | STA_416 Maynard
NSTAR | Brookline | ESMAEX-00231 | 02445 | 200 | Solar | 350-H8 | 2021-07-09 | 2021-07-22 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-01-06 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Sandwich | ESMAEX-00305 | 02644 | 60.5 | Solar |  | 2021-08-12 | 2021-09-08 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-03 | [7 empty] | 0 |  | 0 |  |  | 2024-05-20 | Online
NSTAR | Needham | ESMAEX-00264 | 02492 | 23.4 | Solar | 148-04 | 2021-07-26 | 2021-08-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-23 | [7 empty] | 0 |  | 0 |  |  | 2021-11-29 | Online | [8 empty] | STA_148 Needham
NSTAR | Plymouth | ESMAEX-00570 | 02360 | 10 | Battery | 3-71-71 | 2021-11-05 | 2021-12-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-10-06 | Online |  |  |  | Plymouth |  |  |  |  | STA_721 Manomet
NSTAR | Framingham | ESMAEX-00236 | 01701 | 4999 | Battery | 433-H2 | 2021-08-31 | 2021-09-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-23 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [6 empty] | 2023 ASO Batch 1 | 4999 | STA_433 Speen Street
NSTAR | Wayland | ESMAEX-00252 | 01778 | 80 | Solar | 342-H3 | 2021-07-20 | 2021-08-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Waltham | ESMAEX-00240 | 02451 | 233.1 | Solar |  | 2021-07-14 | 2021-07-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-24 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online
NSTAR | Burlington | ESMAEX-00302 | 01803 | 19.825 | Solar | 375-H14 | 2021-08-11 | 2021-09-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-07 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Carlisle | ESMAEX-00267 | 01741 | 18.18 | Solar | 512-1399H1 | 2021-07-27 | 2021-08-12 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-19 | [7 empty] | 0 |  | 0 |  |  | 2022-03-08 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Dennis | ESMAEX-00336 | 02638 | 262.5 | Fuel Cell | 4-92B-92B | 2021-08-20 | 2021-09-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-05 | Online |  |  |  | Cape |  |  |  | 100 | STA_968 Harwich
NSTAR | Allston | ESMAEX-00263 | 02134 | 133.2 | Solar | 329-H5 | 2021-07-23 | 2021-08-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-01 | [7 empty] | 0 |  | 0 |  |  | 2022-09-27 | Online | [8 empty] | STA_329 Brighton
NSTAR | Sherborn | ESMAEX-00285 | 01770 | 19.7 | Solar | 130-H2 | 2021-08-04 | 2021-08-16 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-07-07 | Online | [8 empty] | STA_130 Holliston
NSTAR | Sherborn | ESMAEX-00248 | 01770 | 5.7 | Battery | 240-H1 | 2021-07-19 | 2021-08-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-04 | [7 empty] | 0 |  | 0 |  |  | 2022-02-18 | Online | [8 empty] | STA_240 Framingham
NSTAR | Maynard | ESMAEX-00247 | 01754 | 16.4 | Solar | 416-H1 | 2021-07-19 | 2021-08-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-02-02 | Online | [8 empty] | STA_416 Maynard
NSTAR | New Bedford | ESMAEX-00250 | 02745 | 15.2 | Solar | 2-106-160 | 2021-07-20 | 2021-08-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-11 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Burlington | ESMAEX-00337 | 01803 | 138.4 | Solar | 391-H9 | 2021-08-23 | 2021-09-21 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-01 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [8 empty] | STA_391 Burlington
NSTAR | Roslindale | ESMAEX-00257 | 02131 | 10 | Battery | 516-06 | 2021-07-21 | 2021-08-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-04 | Online | [8 empty] | STA_110 Baker Street
NSTAR | West Yarmouth | ESMAEX-00278 | 02673 | 170 | Internal Combustion Engine |  | 2021-08-02 | 2021-08-13 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2024-04-04 | Online | [7 empty] | 0
NSTAR | Lexington | ESMAEX-00282 | 02420 | 11.52 | Battery | 533-H9 | 2021-08-03 | 2021-08-26 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Mashpee | ESMAEX-00273 | 02649 | 80 | Solar | 4-452-452 | 2021-07-28 | 2021-08-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Online |  |  |  | Cape |  |  |  |  | STA_946 Mashpee
NSTAR | Westwood | ESMAEX-00274 | 02090 | 24 | Solar & Battery | 148-H3 | 2021-07-29 | 2021-09-17 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-09-15 | Online | [8 empty] | STA_148 Needham
NSTAR | Brookline | ESMAEX-00313 | 02445 | 7.68 | Solar & Battery | 23N30 | 2021-08-13 | 2021-09-08 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-31 | Online | [8 empty] | STA_329 Brighton
NSTAR | Brookline | ESMAEX-00299 | 02445 | 19.764 | Solar | 350-H8 | 2021-08-10 | 2021-08-24 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2021-11-18 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Marion | ESMAEX-00270 | 02738 | 22.8 | Solar | 3-85-85 | 2021-07-28 | 2021-08-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-03 | [7 empty] | 0 |  | 0 |  |  | 2022-06-17 | Online |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | Bellingham | ESMAEX-00298 | 02019 | 4947 | Battery | 65-H4 | 2021-08-10 | 2021-10-18 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Negotiated Timeframe |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [6 empty] | 2023 ASO Batch 1 |  | STA_065 Medway
NSTAR | Plymouth | ESMAEX-00271 | 02360 | 15 | Solar & Battery | 3-71-71 | 2021-07-28 | 2021-08-12 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-12 | [7 empty] | 0 |  | 0 |  |  | 2022-01-07 | Online |  |  |  | Plymouth |  |  |  |  | STA_721 Manomet
NSTAR | Chestnut Hill | ESMAEX-00272 | 02467 | 5.16 | Battery | 496-H5 | 2021-07-28 | 2021-08-12 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Orleans | ESMAEX-00303 | 02653 | 15.2 | Solar & Battery | 4-94A-94A | 2021-08-12 | 2021-09-09 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [8 empty] | STA_975 Orleans
NSTAR | Acton | ESMAEX-00320 | 01720 | 66.6 | Solar | 416-H9 | 2021-08-17 | 2021-09-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-05 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [8 empty] | STA_416 Maynard
NSTAR | Cummaquid | ESMAEX-00283 | 02637 | 18 | Solar | 4-92A-92A | 2021-08-03 | 2021-08-16 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-06-24 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Dedham | ESMAEX-00280 | 02026 | 86.4 | Solar | 148-H3 | 2021-08-02 | 2021-08-13 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2023-09-05 | Online | [8 empty] | STA_148 Needham
NSTAR | Marstons Mills | ESMAEX-00284 | 02648 | 6 | Solar | 4-87A-87A | 2021-08-03 | 2021-08-12 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-02-17 | Online |  |  |  | Cape |  |  |  |  | STA_916 Sandwich
NSTAR | New Bedford | ESMAEX-00322 | 02745 | 249.9 | Solar | 2-79-404 | 2021-08-17 | 2021-09-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-22 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_612 Acushnet
NSTAR | Duxbury | ESMAEX-00287 | 02332 | 15.2 | Solar | 3-26-26 | 2021-08-04 | 2021-08-16 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-08-24 | [7 empty] | 0 |  | 0 |  |  | 2021-12-06 | Online
NSTAR | Dover | ESMAEX-00288 | 02030 | 10 | Battery | 456-H5 | 2021-08-05 | 2021-08-16 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-21 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online | [8 empty] | STA_456 Dover
NSTAR | Kingston | ESMAEX-00297 | 02364 | 10 | Battery | 3-51-980 | 2021-08-10 | 2021-08-24 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-27 | [7 empty] | 0 |  | 0 |  |  | 2022-08-15 | Online |  |  |  | Plymouth |  |  |  |  | STA_727 Brook Street
NSTAR | Needham | ESMAEX-00393 | 02492 | 20 | Battery | 148-H4 | 2021-09-08 | 2021-09-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-12 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online | [8 empty] | STA_148 Needham
NSTAR | Norfolk | ESMAEX-00292 | 02056 | 15.29 | Solar & Battery | 65-H1 | 2021-08-09 | 2021-09-24 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0 |  |  | 2022-04-06 | Online | [8 empty] | STA_065 Medway
NSTAR | Hopkinton | ESMAEX-00317 | 01748 | 15.2 | Solar | 126-H2 | 2021-08-17 | 2021-09-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-23 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Waban | ESMAEX-00301 | 02468 | 7.67 | Solar & Battery | 292-H2 | 2021-08-11 | 2021-08-25 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-15 | [7 empty] | 0 |  | 0 |  |  | 2022-02-04 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Winchester | ESMAEX-00318 | 01890 | 17.58 | Solar & Battery | 211-07 | 2021-08-17 | 2021-10-15 | 43 |  | 43 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-23 | [7 empty] | 0 |  | 0 |  |  | 2022-01-14 | Online | [8 empty] | STA_211 Woburn
NSTAR | Sharon | ESMAEX-00315 | 02067 | 250 | Solar | 146-H1 | 2021-08-16 | 2021-09-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-01 | Online | [7 empty] | 250 | STA_146 Walpole
NSTAR | New Bedford | ESMAEX-00340 | 02745 | 50 | Solar | 2-103-103 | 2021-08-23 | 2021-09-09 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-13 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Online
NSTAR | Cambridge | ESMAEX-01118 | 02139 | 21.4 | Solar | 820-45 | 2022-04-26 | 2022-05-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2023-07-06 | Online | [8 empty] | STA_402 Newton Street
NSTAR | Acton | ESMAEX-00365 | 01720 | 110.8 | Solar | 416-H8 | 2021-08-27 | 2021-09-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-06-15 | Online | [8 empty] | STA_416 Maynard
NSTAR | Natick | ESMAEX-00473 | 01760 | 9.516 | Solar & Battery | 433-H12 | 2021-10-05 | 2021-10-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Dover | ESMAEX-00316 | 02030 | 12.685 | Solar & Battery | 456-H5 | 2021-08-16 | 2021-09-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-27 | [7 empty] | 0 |  | 0 |  |  | 2022-02-17 | Online | [8 empty] | STA_456 Dover
NSTAR | Plymouth | ESMAEX-00312 | 02360 | 7.6 | Solar & Battery | 3-14-934 | 2021-08-13 | 2021-08-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-17 | [7 empty] | 0 |  | 0 |  |  | 2022-01-27 | Online |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Marshfield | ESMAEX-00495 | 02050 | 5.51 | Solar & Battery | 3-22-33J2 | 2021-10-13 | 2021-11-24 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-09-19 | Online | [8 empty] | STA_739 Marshfield
NSTAR | Carlisle | ESMAEX-00310 | 01741 | 15.2 | Solar & Battery | 512-1399H1 | 2021-08-13 | 2021-08-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-19 | [7 empty] | 0 |  | 0 |  |  | 2022-11-29 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Milton | ESMAEX-00607 | 02186 | 19.8 | Battery | 496-H2 | 2021-11-18 | 2022-01-06 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Cambridge | ESMAEX-00308 | 02138 | 17.6 | Solar & Battery | 825-18 | 2021-08-13 | 2021-10-21 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-10 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online | [8 empty] | STA_828 Alewife
NSTAR | Wayland | ESMAEX-00424 | 01778 | 7.68 | Battery | 278-H2 | 2021-09-20 | 2021-11-09 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-05-26 | Online | [8 empty] | STA_278 Saxonville
NSTAR | Waltham | ESMAEX-00331 | 02451 | 100 | Solar | 450-H2 | 2021-08-19 | 2021-09-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online | [8 empty] | STA_450 Trapelo Road
NSTAR | East Falmouth | ESMAEX-00319 | 02536 | 310 | Solar |  | 2021-11-10 | 2021-12-14 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-19 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online
NSTAR | Hopkinton | ESMAEX-00321 | 01748 | 17.6 | Solar & Battery | 126-H2 | 2021-08-17 | 2022-06-01 | 206 |  | 206 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2022-09-26 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Sherborn | ESMAEX-00323 | 01770 | 20 | Solar & Battery | 240-H1 | 2021-08-17 | 2021-10-21 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-23 | Online | [7 empty] | 10 | STA_240 Framingham
NSTAR | Duxbury | ESMAEX-00326 | 02332 | 46.2 | Solar | 3-23-23 | 2021-08-18 | 2021-09-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-09 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Acton | ESMAEX-00328 | 01720 | 20 | Solar | 416-H8 | 2021-08-18 | 2021-09-22 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-01 | [7 empty] | 0 |  | 0 |  |  | 2022-06-17 | Online | [8 empty] | STA_416 Maynard
NSTAR | Millis | ESMAEX-00379 | 02054 | 27.13 | Battery | 146-H10 | 2021-09-02 | 2021-09-21 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-29 | [7 empty] | 0 |  | 0 |  |  | 2022-05-03 | Online | [8 empty] | STA_146 Walpole
NSTAR | Sherborn | ESMAEX-00335 | 01770 | 24.19 | Solar | 274-H2 | 2021-08-20 | 2021-09-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-08-17 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Brewster | ESMAEX-00334 | 02631 | 10 | Solar & Battery | 4-628-628 | 2021-08-20 | 2021-09-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0 |  |  | 2022-06-13 | Online | [8 empty] | STA_975 Orleans
NSTAR | Duxbury | ESMAEX-00346 | 02332 | 21.44 | Solar | 3-24B-24B | 2021-08-25 | 2021-09-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-30 | [7 empty] | 0 |  | 0 |  |  | 2022-04-05 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Medfield | ESMAEX-00339 | 02052 | 17.68 | Solar & Battery | 146-H2 | 2021-08-23 | 2021-09-09 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-02-16 | Online | [8 empty] | STA_146 Walpole
NSTAR | Lincoln | ESMAEX-00406 | 01773 | 21.65 | Solar & Battery | 320-H8 | 2021-09-13 | 2021-09-29 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-29 | [7 empty] | 0 |  | 0 |  |  | 2022-02-03 | Online | [8 empty] | STA_320 Lexington
NSTAR | Canton | ESMAEX-00422 | 02021 | 16 | Solar | 470-H11 | 2021-09-17 | 2022-02-01 | 97 |  | 97 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-16 | Online | [8 empty] | STA_470 Canton
NSTAR | Burlington | ESMAEX-00344 | 01803 | 17.6 | Solar & Battery | 346-1395H1 | 2021-08-24 | 2021-09-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-27 | Online | [8 empty] | STA_391 Burlington
NSTAR | Cambridge | ESMAEX-00350 | 02138 | 17.6 | Solar & Battery | 830-11 | 2021-08-26 | 2021-09-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-20 | [7 empty] | 0 |  | 0 |  |  | 2022-05-02 | Online | [8 empty] | STA_828 Alewife
NSTAR | Norfolk | ESMAEX-00345 | 02056 | 17.68 | Solar & Battery | 146-H3 | 2021-08-24 | 2021-09-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-14 | [7 empty] | 0 |  | 0 |  |  | 2022-09-22 | Online | [8 empty] | STA_146 Walpole
NSTAR | Sharon | ESMAEX-00352 | 02067 | 20.2 | Solar & Battery | 146-H7 | 2021-08-26 | 2021-09-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-21 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Online | [8 empty] | STA_146 Walpole
NSTAR | Acton | ESMAEX-00416 | 01720 | 19.79 | Battery | 416-H4 | 2021-09-16 | 2021-10-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2022-08-08 | Online | [8 empty] | STA_416 Maynard
NSTAR | Arlington | ESMAEX-00349 | 02474 | 12.6 | Solar & Battery | 211-H14 | 2021-08-25 | 2021-09-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-09-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Online | [8 empty] | STA_211 Woburn
NSTAR | Brookline | ESMAEX-00359 | 02446 | 15 | Battery | 4911 | 2021-08-26 | 2021-09-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-15 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Charlestown | ESMAEX-00488 | 02129 | 86.5 | Solar |  | 2021-10-12 | 2021-11-03 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-07 | [7 empty] | 0 |  | 0 |  |  | 2023-12-05 | Online
NSTAR | Acton | ESMAEX-00360 | 01720 | 17.6 | Solar & Battery | 416-H4 | 2021-08-26 | 2021-09-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-21 | [7 empty] | 0 |  | 0 |  |  | 2022-03-16 | Online | [8 empty] | STA_416 Maynard
NSTAR | Sharon | ESMAEX-00357 | 02067 | 498 | Solar | 146-H1 | 2021-10-02 | 2021-11-15 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-24 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [7 empty] | 498 | STA_146 Walpole
NSTAR | Medway | ESMAEX-00399 | 02053 | 28.8 | Solar | 65-H2 | 2021-09-09 | 2021-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Online | [8 empty] | STA_065 Medway
NSTAR | Medway | ESMAEX-00398 | 02053 | 43.2 | Solar | 65-H2 | 2021-09-09 | 2021-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-10 | Online | [8 empty] | STA_065 Medway
NSTAR | Bourne | ESMAEX-00461 | 02532 | 39.98 | Solar | 4-86-408 | 2021-09-30 | 2021-10-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online |  |  |  | Cape |  |  |  |  | STA_915 Otis
NSTAR | Acton | ESMAEX-00373 | 01720 | 21.4 | Solar & Battery | 416-H9 | 2021-08-31 | 2021-09-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-06-08 | Online | [8 empty] | STA_416 Maynard
NSTAR | Watertown | ESMAEX-00420 | 02472 | 325 | Solar & Battery | 240-H5 | 2021-09-17 | 2022-01-11 | 82 |  | 82 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2024-02-20 | Online |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Medway | ESMAEX-00400 | 02053 | 28.8 | Solar | 65-H2 | 2021-09-09 | 2021-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Online | [8 empty] | STA_065 Medway
NSTAR | Holliston | ESMAEX-00378 | 01746 | 19 | Solar | 130-H1 | 2021-09-01 | 2021-09-16 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-30 | [7 empty] | 0 |  | 0 |  |  | 2022-02-01 | Online | [8 empty] | STA_130 Holliston
NSTAR | East Sandwich | ESMAEX-00397 | 02537 | 10 | Solar & Battery | 4-87A-87A | 2021-09-09 | 2021-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-03 | [7 empty] | 0 |  | 0 |  |  | 2022-04-11 | Online |  |  |  | Cape |  |  |  |  | STA_916 Sandwich
NSTAR | West Newton | ESMAEX-00386 | 02465 | 17.6 | Solar & Battery | 282-H9 | 2021-09-06 | 2021-10-04 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-19 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Online | [8 empty] | STA_282 Waltham
NSTAR | Lincoln | ESMAEX-00376 | 01773 | 52.8 | Solar & Battery | 320-H8 | 2021-09-01 | 2021-09-16 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-20 | [7 empty] | 0 |  | 0 |  |  | 2022-07-19 | Online | [8 empty] | STA_320 Lexington
NSTAR | Waltham | ESMAEX-00389 | 02452 | 150 | Solar | 33-H2 | 2021-09-07 | 2021-11-22 | 54 |  | 54 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Online | [8 empty] | STA_282 Waltham
NSTAR | Waban | ESMAEX-00392 | 02468 | 25.2 | Solar & Battery | 292-H12 | 2021-09-08 | 2021-09-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-08 | [7 empty] | 0 |  | 0 |  |  | 2023-03-21 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Acton | ESMAEX-00388 | 01720 | 9.6 | Solar & Battery | 416-H2 | 2021-09-07 | 2021-09-21 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-08-10 | Online | [8 empty] | STA_416 Maynard
NSTAR | Westwood | ESMAEX-00440 | 02090 | 25.37 | Solar & Battery | 456-H1 | 2021-09-22 | 2021-12-07 | 54 |  | 54 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-19 | [7 empty] | 0 |  | 0 |  |  | 2022-08-19 | Online | [8 empty] | STA_456 Dover
NSTAR | East Boston | ESMAEX-00411 | 02128 | 75 | Internal Combustion Engine | 308-197H | 2021-09-14 | 2021-09-30 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Assonett | ESMAEX-00396 | 02702 | 149.76 | Solar | 2-102-604 | 2021-09-09 | 2021-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2024-11-26 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Norfolk | ESMAEX-00391 | 02056 | 13.15 | Battery | 146-H3 | 2021-09-08 | 2021-09-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-29 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Online | [8 empty] | STA_146 Walpole
NSTAR | Framingham | ESMAEX-00438 | 01702 | 21.28 | Solar & Battery | 455-H5 | 2021-09-21 | 2021-10-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-06 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online | [8 empty] | STA_455 West Framingham
NSTAR | North Falmouth | ESMAEX-00404 | 02556 | 25.075 | Solar | 4-78-861 | 2021-09-10 | 2021-09-29 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2022-08-30 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Brighton | ESMAEX-00405 | 02135 | 100 | Solar | 329-H2 | 2021-09-10 | 2021-09-29 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-26 | [7 empty] | 0 |  | 0 |  |  | 2024-12-17 | Online | [8 empty] | STA_329 Brighton
NSTAR | Boston | ESMAEX-00408 | 02118 | 100 | Solar | 106-H4 | 2021-09-13 | 2021-11-16 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2023-05-15 | Online | [8 empty] | STA_106 Andrew Square
NSTAR | Lexington | ESMAEX-00403 | 02421 | 21.43 | Solar & Battery | 3409 | 2021-09-10 | 2021-11-23 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-01-18 | Online
NSTAR | Westwood | ESMAEX-00414 | 02090 | 20 | Solar & Battery | 469-H2 | 2021-09-16 | 2021-10-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-08 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Online
NSTAR | Hopkinton | ESMAEX-00412 | 01748 | 27.6 | Solar & Battery | 126-H4 | 2021-09-14 | 2021-10-26 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | North Dartmouth | ESMAEX-00410 | 02747 | 15.2 | Solar | 2-531-531 | 2021-09-14 | 2021-11-16 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Chatham | ESMAEX-00415 | 02659 | 180 | Solar | 4-95A-95A | 2021-09-16 | 2022-01-19 | 89 |  | 89 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-01 | [7 empty] | 0 |  | 0 |  |  | 2024-12-09 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Kingston | ESMAEX-00445 | 02364 | 100 | Solar | 3-14-14 | 2021-09-23 | 2021-10-21 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-24 | [7 empty] | 0 |  | 0 |  |  | 2023-11-17 | Online
NSTAR | New Bedford | ESMAEX-00418 | 02740 | 50 | Solar | 2-73-73 | 2021-09-17 | 2021-10-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-08 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Online | [8 empty] | STA_611 Pine Street
NSTAR | Waltham | ESMAEX-00426 | 02453 | 7 | Solar & Battery | 282-H8 | 2021-09-20 | 2021-10-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Online | [8 empty] | STA_282 Waltham
NSTAR | Boston | ESMAEX-00460 | 02215 | 120.8 | Solar | 350-H12 | 2021-09-30 | 2021-10-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-09 | [7 empty] | 0 |  | 0 |  |  | 2022-08-08 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Framingham | ESMAEX-00419 | 01701 | 17.6 | Solar & Battery | 433-H8 | 2021-09-17 | 2021-10-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-26 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Online | [8 empty] | STA_433 Speen Street
NSTAR | North Falmouth | ESMAEX-00539 | 02556 | 12 | Battery | 4-78-420 | 2021-10-25 | 2021-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Rochester | ESMAEX-00421 | 02770 | 20 | Solar | 3-702-702 | 2021-09-17 | 2021-10-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-08 | [7 empty] | 0 |  | 0 |  |  | 2022-07-06 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_745 Rochester
NSTAR | Dover | ESMAEX-00428 | 02030 | 30 | Solar & Battery | 456-H5 | 2021-09-20 | 2021-10-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-14 | Online | [8 empty] | STA_456 Dover
NSTAR | Watertown | ESMAEX-00429 | 02472 | 492 | Solar |  | 2021-10-26 | 2021-12-01 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Online
NSTAR | West Tisbury | ESMAEX-00446 | 02575 | 12.98 | Solar | 4-97-97 | 2021-09-24 | 2021-11-09 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Falmouth | ESMAEX-00435 | 02540 | 16.82 | Solar | 4-76-76 | 2021-09-21 | 2021-11-09 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-19 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Newton | ESMAEX-00454 | 02458 | 200 | Solar | 467-H14 | 2021-09-28 | 2021-10-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2024-10-25 | Online | [8 empty] | STA_467 Watertown
NSTAR | New Bedford | ESMAEX-00436 | 02740 | 75 | Internal Combustion Engine | 2-67-28 | 2021-09-21 | 2021-10-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-27 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Online | [8 empty] | STA_611 Pine Street
NSTAR | New Bedford | ESMAEX-00437 | 02740 | 75 | Internal Combustion Engine | 2-4-51 | 2021-09-21 | 2021-10-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-27 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Online
NSTAR | Burlington | ESMAEX-00464 | 01803 | 15.2 | Solar & Battery | 391-H6 | 2021-10-01 | 2021-12-28 | 62 |  | 62 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-18 | [7 empty] | 0 |  | 0 |  |  | 2022-03-17 | Online | [8 empty] | STA_391 Burlington
NSTAR | North Dartmouth | ESMAEX-00480 | 02747 | 86.4 | Solar | 2-532-532 | 2021-10-07 | 2021-11-09 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Dartmouth | ESMAEX-00455 | 02747 | 100 | Solar | 2-541-541 | 2021-09-28 | 2022-02-03 | 92 |  | 92 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-20 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Online | [8 empty] | STA_651 Cross Road
NSTAR | Mattapoisett | ESMAEX-00450 | 02739 | 17.6 | Solar | 2-302-302 | 2021-09-27 | 2021-10-20 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-22 | [7 empty] | 0 |  | 0 |  |  | 2022-01-05 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Roxbury | ESMAEX-00513 | 02119 | 52.2 | Solar | 52-1499H4 | 2021-10-19 | 2021-11-15 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-15 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online
NSTAR | Sharon | ESMAEX-00457 | 02067 | 420 | Solar | 470-H12 | 2021-09-29 | 2021-10-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-14 | [7 empty] | 0 |  | 0 |  |  | 2025-03-25 | Online | [8 empty] | STA_470 Canton
NSTAR | West Tisbury | ESMAEX-00644 | 02575 | 25.568 | Solar & Battery |  | 2021-12-07 | 2021-12-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-03 | [7 empty] | 0 |  | 0 |  |  | 2022-11-04 | Online
NSTAR | Bedford | ESMAEX-00465 | 01730 | 12.6 | Solar & Battery | 533-H8 | 2021-10-03 | 2021-11-16 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Framingham | ESMAEX-00506 | 01702 | 316.6 | Solar | 24-H1 | 2021-10-15 | 2021-11-23 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2024-09-04 | Online | [8 empty] | STA_240 Framingham
NSTAR | Marion | ESMAEX-00658 | 02738 | 22.8 | Solar | 3-304-304 | 2021-12-14 | 2022-01-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Dedham | ESMAEX-00467 | 02026 | 17.6 | Solar & Battery | 20-H3 | 2021-10-04 | 2021-11-09 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Online | [8 empty] | STA_110 Baker Street
NSTAR | Harwich | ESMAEX-00466 | 02645 | 12.68 | Solar & Battery | 4-89B-576 | 2021-10-04 | 2021-10-21 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-10-21 | [7 empty] | 0 |  | 0 |  |  | 2022-05-04 | Online | [8 empty] | STA_975 Orleans
NSTAR | Natick | ESMAEX-00472 | 01760 | 10.248 | Solar & Battery | 240-H1 | 2021-10-05 | 2021-10-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-03 | [7 empty] | 0 |  | 0 |  |  | 2022-11-08 | Online | [8 empty] | STA_240 Framingham
NSTAR | Edgartown | ESMAEX-00682 | 02539 | 11.21 | Solar & Battery |  | 2021-12-21 | 2022-02-09 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-16 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online
NSTAR | Osterville | ESMAEX-00494 | 02655 | 28 | Solar & Battery | 4-80A-80A | 2021-10-13 | 2021-11-04 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-05-02 | Online | [8 empty] | STA_920 Oak Street
NSTAR | Hopkinton | ESMAEX-00478 | 01748 | 19.77 | Solar | 126-H1 | 2021-10-06 | 2021-11-18 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-12 | [7 empty] | 0 |  | 0 |  |  | 2022-03-10 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Wellfleet | ESMAEX-00505 | 02667 | 7.14 | Solar | 4-94B-656 | 2021-10-15 | 2021-11-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-04 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Woburn | ESMAEX-00486 | 01801 | 109.8 | Solar | 211-H2 | 2021-10-10 | 2021-11-03 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-06-09 | Online | [8 empty] | STA_211 Woburn
NSTAR | Chestnut Hill | ESMAEX-00548 | 02467 | 199.8 | Solar | 443-08 | 2021-10-27 | 2021-11-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-18 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Online | [8 empty] | STA_110 Baker Street
NSTAR | Walpole | ESMAEX-00498 | 02081 | 15.8 | Solar | 456-H1 | 2021-10-13 | 2021-11-16 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-07 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Online | [8 empty] | STA_456 Dover
NSTAR | Mattapoisett | ESMAEX-00485 | 02739 | 16.24 | Solar | 2-302-302 | 2021-10-09 | 2021-11-03 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-09 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Dover | ESMAEX-00500 | 02030 | 26 | Solar | 456-H5 | 2021-10-14 | 2021-11-04 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-19 | [7 empty] | 0 |  | 0 |  |  | 2022-06-07 | Online | [8 empty] | STA_456 Dover
NSTAR | East Freetown | ESMAEX-00508 | 02717 | 149.76 | Solar | 2-108-108 | 2021-10-18 | 2021-11-15 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-09 | [7 empty] | 0 |  | 0 |  |  | 2023-03-01 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | North Truro | ESMAEX-00507 | 02652 | 8 | Solar | 4-96-96 | 2021-10-18 | 2021-11-09 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-21 | [7 empty] | 0 |  | 0 |  |  | 2022-03-07 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Hyde Park | ESMAEX-00537 | 02136 | 30.45 | Solar | 60-1409H1 | 2021-10-21 | 2021-11-15 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2023-08-23 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Dover | ESMAEX-00547 | 02030 | 7.678 | Solar & Battery | 456-H5 | 2021-10-27 | 2021-11-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-10 | [7 empty] | 0 |  | 0 |  |  | 2022-07-06 | Online | [8 empty] | STA_456 Dover
NSTAR | Natick | ESMAEX-00514 | 01760 | 10.248 | Solar & Battery | 240-H3 | 2021-10-19 | 2022-01-25 | 70 |  | 70 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-05-20 | Online | [8 empty] | STA_240 Framingham
NSTAR | Dorchester | ESMAEX-00561 | 02125 | 43.2 | Solar | 106-1N31H1 | 2021-11-02 | 2021-11-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-09 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Online | [8 empty] | STA_106 Andrew Square
NSTAR | Waltham | ESMAEX-00516 | 02453 | 7 | Solar & Battery | 282-H8 | 2021-10-20 | 2021-11-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-19 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [8 empty] | STA_282 Waltham
NSTAR | East Sandwich | ESMAEX-00517 | 02537 | 9.12 | Solar & Battery | 4-87B-87B | 2021-10-20 | 2021-11-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-04-26 | Online |  |  |  | Cape |  |  |  |  | STA_920 Oak Street
NSTAR | South Chatham | ESMAEX-00522 | 02659 | 10 | Battery | 4-95A-606 | 2021-10-21 | 2021-11-15 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-22 | [7 empty] | 0 |  | 0 |  |  | 2022-10-04 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Wellfleet | ESMAEX-00664 | 02667 | 8 | Battery | 4-94B-94B | 2021-12-15 | 2022-01-14 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-05-23 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Hyannis | ESMAEX-00546 | 02601 | 150 | Solar | 4-63-531 | 2021-10-26 | 2021-12-15 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Hyannis Port | ESMAEX-00558 | 02672 | 10 | Battery | 4-80B-80B | 2021-11-01 | 2021-11-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Natick | ESMAEX-00563 | 01760 | 10.248 | Solar & Battery | 240-H3 | 2021-11-03 | 2021-11-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-03 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Online | [8 empty] | STA_240 Framingham
NSTAR | South Dartmouth | ESMAEX-00600 | 02748 | 48.03 | Solar & Battery | 2-524-524 | 2021-11-17 | 2022-01-05 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-10 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_657 Fisher Road
NSTAR | Wareham | ESMAEX-00540 | 02532 | 196 | Solar | 3-83-83 | 2021-10-25 | 2021-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-20 | [7 empty] | 0 |  | 0 |  |  | 2023-08-15 | Online |  |  |  | Plymouth |  |  |  |  | STA_714 Wareham
NSTAR | Ashland | ESMAEX-00557 | 01721 | 250 | Solar | 274-H5 | 2021-11-01 | 2021-11-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | STA_274 Sherborn
NSTAR | Chatham | ESMAEX-00542 | 02633 | 15.39 | Solar | 4-95B-95B | 2021-10-26 | 2021-11-19 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-23 | [7 empty] | 0 |  | 0 |  |  | 2022-02-08 | Online | [8 empty] | STA_975 Orleans
NSTAR | North Dartmouth | ESMAEX-00544 | 02747 | 57.6 | Solar | 2-532-532 | 2021-10-26 | 2021-11-16 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-22 | [7 empty] | 0 |  | 0 |  |  | 2022-08-16 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Chestnut Hill | ESMAEX-00545 | 02467 | 17.6 | Solar & Battery | 329-H6 | 2021-10-26 | 2021-11-16 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-11-16 | [7 empty] | 0 |  | 0 |  |  | 2022-03-21 | Online | [8 empty] | STA_329 Brighton
NSTAR | Newton Center | ESMAEX-00551 | 02459 | 1.5 | Solar & Battery | 292-H8 | 2021-10-28 | 2021-11-23 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-25 | [7 empty] | 0 |  | 0 |  |  | 2022-04-25 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Needham | ESMAEX-00830 | 02492 | 480 | Solar & Battery | 148-H1 | 2022-02-11 | 2022-03-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-02-03 | Compliance Documents | [8 empty] | STA_148 Needham
NSTAR | Needham | ESMAEX-00552 | 02494 | 750 | Solar & Battery | 148-H6 | 2021-12-23 | 2022-01-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-17 | [7 empty] | 0 |  | 0 |  |  | 2024-03-13 | Online | [7 empty] | 750 | STA_148 Needham
NSTAR | Burlington | ESMAEX-00554 | 01803 | 20 | Solar & Battery | 391-H7 | 2021-10-28 | 2021-11-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-10 | [7 empty] | 0 |  | 0 |  |  | 2022-01-21 | Online | [8 empty] | STA_391 Burlington
NSTAR | Needham | ESMAEX-00560 | 02494 | 11.4 | Battery | 292-H4 | 2021-11-02 | 2021-11-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-02 | [7 empty] | 0 |  | 0 |  |  | 2022-03-23 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Walpole | ESMAEX-00572 | 02081 | 400 | Solar | 146-H8 | 2021-11-08 | 2021-11-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-13 | [7 empty] | 0 |  | 0 |  |  | 2025-02-03 | Online | [8 empty] | STA_146 Walpole
NSTAR | Mashpee | ESMAEX-00565 | 02649 | 85.76 | Solar | 4-455-455 | 2021-11-04 | 2021-11-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-06-30 | Online | [8 empty] | STA_946 Mashpee
NSTAR | Canton | ESMAEX-00562 | 02021 | 8.56 | Solar & Battery | 470-H8 | 2021-11-02 | 2021-11-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-22 | [7 empty] | 0 |  | 0 |  |  | 2022-04-14 | Online | [8 empty] | STA_470 Canton
NSTAR | Newton Lower Falls | ESMAEX-00571 | 02462 | 9.75 | Solar & Battery | 292-H2 | 2021-11-08 | 2021-12-16 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-09 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Dover | ESMAEX-00566 | 02030 | 10 | Battery | 148-H2 | 2021-11-05 | 2021-11-23 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2023-01-03 | Online | [8 empty] | STA_148 Needham
NSTAR | North Dartmouth | ESMAEX-00589 | 02747 | 20 | Solar | 2-532-532 | 2021-11-15 | 2021-12-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0 |  |  | 2022-06-28 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Carlisle | ESMAEX-00596 | 01741 | 14 | Battery | 512-1399H1 | 2021-11-17 | 2021-12-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Online | [7 empty] | 14 | STA_533 Hartwell Avenue
NSTAR | Acusnet | ESMAEX-00573 | 02743 | 15.2 | Solar | 2-241-241 | 2021-11-09 | 2021-12-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-15 | [7 empty] | 0 |  | 0 |  |  | 2022-08-23 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_624 Wing Lane
NSTAR | Rochester | ESMAEX-00574 | 02770 | 10.03 | Solar | 3-703-703 | 2021-11-09 | 2021-11-23 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-03-03 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_745 Rochester
NSTAR | Dover | ESMAEX-00576 | 02030 | 16.225 | Solar | 456-H5 | 2021-11-10 | 2021-11-23 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Online | [8 empty] | STA_456 Dover
NSTAR | Needham | ESMAEX-00582 | 02492 | 11.4 | Battery | 148-H4 | 2021-11-11 | 2021-12-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-07 | [7 empty] | 0 |  | 0 |  |  | 2022-04-26 | Online | [8 empty] | STA_148 Needham
NSTAR | Chelsea | ESMAEX-00580 | 02150 | 43.2 | Solar | 488-H3 | 2021-11-10 | 2021-12-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Chelsea | ESMAEX-00581 | 02150 | 43.2 | Solar | 488-H7 | 2021-11-10 | 2021-12-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-19 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Chatham | ESMAEX-00586 | 02633 | 12 | Battery | 4-95B-95B | 2021-11-15 | 2021-12-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-13 | [7 empty] | 0 |  | 0 |  |  | 2022-03-24 | Online | [8 empty] | STA_975 Orleans
NSTAR | Marshfield | ESMAEX-00584 | 02050 | 9 | Battery | 3-27-27 | 2021-11-15 | 2021-12-17 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-23 | [7 empty] | 0 |  | 0 |  |  | 2022-10-17 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Carver | ESMAEX-02467 | 02330 | 4990 | Solar | 3-10-10 | 2023-06-26 | 2023-07-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study | 2024 SEMA/Cape ASO Study | 4990 | STA_737 West Pond
NSTAR | North Truro | ESMAEX-00585 | 02652 | 15.2 | Solar & Battery | 4-96-96 | 2021-11-15 | 2022-01-20 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2023-02-02 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Marion | ESMAEX-00590 | 02738 | 17.6 | Solar & Battery | 3-85-85 | 2021-11-16 | 2022-01-20 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-23 | [7 empty] | 0 |  | 0 |  |  | 2023-01-26 | Online |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | Newton Center | ESMAEX-00601 | 02459 | 15.2 | Solar | 443-02 | 2021-11-17 | 2022-01-06 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-25 | [7 empty] | 0 |  | 0 |  |  | 2022-11-30 | Online | [8 empty] | STA_110 Baker Street
NSTAR | Holliston | ESMAEX-00605 | 01746 | 80 | Solar | 274-H3 | 2021-11-18 | 2021-12-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-10 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Falmouth | ESMAEX-00604 | 02540 | 19 | Solar | 4-78-78 | 2021-11-18 | 2022-01-04 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-07 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Assonett | ESMAEX-00610 | 02702 | 17.25 | Solar | 2-605-605 | 2021-11-22 | 2021-12-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-02 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [8 empty] | STA_661 Bell Rock
NSTAR | Cambridge | ESMAEX-00597 | 02138 | 34.2 | Solar | 821-05 | 2021-11-17 | 2021-12-30 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-29 | [7 empty] | 0 |  | 0 |  |  | 2023-09-01 | Online | [8 empty] | STA_831 Putnam
NSTAR | South Chatham | ESMAEX-00602 | 02659 | 16 | Solar |  | 2021-11-17 | 2021-12-30 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online
NSTAR | Plymouth | ESMAEX-00603 | 02360 | 17.6 | Solar | 3-90-90 | 2021-11-17 | 2022-01-19 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-01 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Canton | ESMAEX-00606 | 02021 | 140 | Solar | 470-H4 | 2021-11-18 | 2022-01-13 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-01-06 | Online | [8 empty] | STA_470 Canton
NSTAR | Westport | ESMAEX-00630 | 02790 | 10 | Battery | 2-523-523 | 2021-11-30 | 2022-01-20 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-25 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_657 Fisher Road
NSTAR | South Dartmouth | ESMAEX-00890 | 02748 | 220 | Solar | 2-53-65 | 2022-03-08 | 2022-03-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-25 | [7 empty] | 0 |  | 0 |  |  | 2023-01-04 | Online | [8 empty] | STA_611 Pine Street
NSTAR | Cambridge | ESMAEX-00638 | 02139 | 14.79 | Solar | 817-46 | 2021-12-03 | 2022-01-03 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-27 | [7 empty] | 0 |  | 0 |  |  | 2022-11-02 | Online | [8 empty] | STA_831 Putnam
NSTAR | Lexington | ESMAEX-00637 | 02420 | 10.03 | Solar & Battery | 391-H11 | 2021-12-02 | 2021-12-28 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-20 | Online | [8 empty] | STA_391 Burlington
NSTAR | Silver Beach | ESMAEX-00636 | 02565 | 6.1 | Battery | 4-78-861 | 2021-12-02 | 2021-12-28 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-03-22 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Plymouth | ESMAEX-00635 | 02360 | 72 | Solar | 3-12-28J3 | 2021-12-01 | 2021-12-28 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Online |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Hopkinton | ESMAEX-00621 | 01748 | 20 | Solar & Battery | 126-H4 | 2021-11-24 | 2021-12-14 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-14 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Bedford | ESMAEX-00622 | 01730 | 17.4 | Solar | 533-H8 | 2021-11-24 | 2021-12-15 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-18 | [7 empty] | 0 |  | 0 |  |  | 2022-04-05 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Wellfleet | ESMAEX-00624 | 02667 | 23.78 | Solar | 4-94B-653 | 2021-11-27 | 2021-12-30 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2024-07-25 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Sharon | ESMAEX-00626 | 02067 | 7.6 | Solar & Battery | 470-H12 | 2021-11-28 | 2021-12-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-08 | [7 empty] | 0 |  | 0 |  |  | 2023-04-14 | Technical Review | [7 empty] | 3.8 | STA_470 Canton
NSTAR | Westwood | ESMAEX-00667 | 02090 | 18 | Solar & Battery | 456-H4 | 2021-12-16 | 2022-01-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online | [7 empty] | 5 | STA_456 Dover
NSTAR | Chelsea | ESMAEX-00672 | 02150 | 86.4 | Solar | 488-H7 | 2021-12-20 | 2022-01-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-17 | Online | [8 empty] | STA_488 Chelsea
NSTAR | East Brewster | ESMAEX-00650 | 02631 | 100 | Solar |  | 2021-12-09 | 2021-12-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online
NSTAR | Boston | ESMAEX-00733 | 02163 | 43.2 | Solar | 831-1107 | 2022-01-18 | 2022-02-14 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-08 | [7 empty] | 0 |  | 0 |  |  | 2022-08-01 | Online | [8 empty] | STA_831 Putnam
NSTAR | Hyannis | ESMAEX-00648 | 02601 | 220 | Solar | 4-63-521 | 2021-12-08 | 2021-12-30 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-05-16 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Sharon | ESMAEX-00641 | 02067 | 9.15 | Solar & Battery | 470-H12 | 2021-12-03 | 2021-12-28 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-12-29 | Online | [8 empty] | STA_470 Canton
NSTAR | West Barnstable | ESMAEX-00730 | 02668 | 15.36 | Solar | 4-87B-87B | 2022-01-16 | 2022-02-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-15 | [7 empty] | 0 |  | 0 |  |  | 2022-05-12 | Online |  |  |  | Cape |  |  |  |  | STA_920 Oak Street
NSTAR | Lexington | ESMAEX-00647 | 02421 | 8.85 | Solar | 320-H2 | 2021-12-08 | 2022-01-20 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Online | [8 empty] | STA_320 Lexington
NSTAR | Brookline | ESMAEX-00678 | 02445 | 14 | Battery | 350-H3 | 2021-12-20 | 2022-02-08 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-03-27 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | North Truro | ESMAEX-00740 | 02652 | 16.56 | Solar |  | 2022-01-19 | 2022-02-15 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-25 | [7 empty] | 0 |  | 0 |  |  | 2022-06-09 | Online
NSTAR | Duxbury | ESMAEX-00646 | 02332 | 10 | Solar | 3-26-26 | 2021-12-07 | 2021-12-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2021-12-30 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online
NSTAR | Hatchville | ESMAEX-00685 | 02536 | 10 | Solar | 4-98A-429 | 2021-12-21 | 2022-01-12 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-13 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Westwood | ESMAEX-00703 | 02090 | 16.054 | Solar | 148-H3 | 2022-01-03 | 2022-01-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-19 | Online | [8 empty] | STA_148 Needham
NSTAR | Needham | ESMAEX-00656 | 02492 | 15.707 | Solar & Battery | 148-08 | 2021-12-13 | 2021-12-30 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Online | [8 empty] | STA_148 Needham
NSTAR | Sudbury | ESMAEX-00651 | 01776 | 199.9 | Solar | 342-H2 | 2021-12-09 | 2021-12-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-10 | [7 empty] | 0 |  | 0 |  |  | 2025-04-28 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Boston | ESMAEX-00654 | 02125 | 98 | Solar | 483-H3 | 2021-12-10 | 2021-12-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-21 | [7 empty] | 0 |  | 0 |  |  | 2024-11-05 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Hyde Park | ESMAEX-00655 | 02136 | 3.8 | Solar | 441-02 | 2021-12-10 | 2021-12-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-29 | Online | [8 empty] | STA_441 Wilmont Street
NSTAR | Hopkinton | ESMAEX-00676 | 01748 | 7.6 | Solar & Battery | 126-H3 | 2021-12-20 | 2022-01-20 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2022-04-21 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Watertown | ESMAEX-00662 | 02472 | 10 | Battery | 467-H8 | 2021-12-15 | 2022-01-11 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-20 | [7 empty] | 0 |  | 0 |  |  | 2022-05-12 | Online | [8 empty] | STA_467 Watertown
NSTAR | Boston | ESMAEX-00666 | 02215 | 116 | Solar |  | 2021-12-15 | 2022-01-20 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-07-07 | Online
NSTAR | Marshfield | ESMAEX-00683 | 02050 | 17.7 | Solar | 3-24A-34J1 | 2021-12-21 | 2022-01-11 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2022-08-29 | Online | [8 empty] | STA_739 Marshfield
NSTAR | Canton | ESMAEX-00665 | 02021 | 15.2 | Solar | 470-H10 | 2021-12-15 | 2022-01-07 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2022-05-12 | Online | [8 empty] | STA_470 Canton
NSTAR | Boston | ESMAEX-00669 | 02124 | 130 | Solar | 496-H8 | 2021-12-17 | 2022-01-20 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-17 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Dover | ESMAEX-00704 | 02030 | 16.403 | Solar | 456-H5 | 2022-01-03 | 2022-01-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-05-24 | Online | [8 empty] | STA_456 Dover
NSTAR | Needham | ESMAEX-00693 | 02494 | 140 | Solar |  | 2021-12-23 | 2022-01-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-03 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Online
NSTAR | West Tisbury | ESMAEX-00673 | 02575 | 20 | Solar |  | 2021-12-20 | 2022-01-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-04-22 | Online
NSTAR | Falmouth | ESMAEX-00721 | 02540 | 10 | Battery | 4-76-436 | 2022-01-11 | 2022-02-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-10 | [7 empty] | 0 |  | 0 |  |  | 2023-07-21 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Canton | ESMAEX-00681 | 02021 | 4999.2 | Battery | 470-H4 | 2022-11-29 | 2022-12-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 4999.2 | STA_470 Canton
NSTAR | Edgartown | ESMAEX-00687 | 02539 | 8.12 | Solar & Battery | 4-75-123 | 2021-12-22 | 2022-01-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-07-27 | Online | [8 empty] | STA_933 Falmouth
NSTAR | Newton Center | ESMAEX-00688 | 02459 | 25.2 | Solar & Battery | 292-H6 | 2021-12-22 | 2022-02-22 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-04-11 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-00692 | 02420 | 22.8 | Solar & Battery | 533-H9 | 2021-12-23 | 2022-01-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2022-09-30 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Watertown | ESMAEX-00696 | 02472 | 400 | Solar | 315-H4 | 2022-01-20 | 2022-02-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Online | [8 empty] | STA_315 Electric Avenue
NSTAR | Framingham | ESMAEX-00697 | 01702 | 11.5 | Solar & Battery | 519-175H1 | 2021-12-28 | 2022-01-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-01 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Dover | ESMAEX-01930 | 02030 | 15.37 | Solar | 456-H3 | 2022-12-16 | 2023-01-10 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-11-16 | Online | [8 empty] | STA_456 Dover
NSTAR | Arlington | ESMAEX-00702 | 02474 | 17.6 | Solar & Battery | 211-H3 | 2022-01-03 | 2022-01-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-01-29 | [7 empty] | 0 |  | 0 |  |  | 2022-04-15 | Online | [8 empty] | STA_211 Woburn
NSTAR | Boston | ESMAEX-00722 | 02118 | 43.2 | Solar |  | 2022-01-11 | 2022-03-01 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2023-07-14 | Online
NSTAR | Westwood | ESMAEX-00709 | 02090 | 480 | Solar | 469-H6 | 2022-05-11 | 2022-07-21 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_469 Ellis Avenue
NSTAR | South Boston | ESMAEX-00753 | 02127 | 28.8 | Solar | 385-H19 | 2022-01-24 | 2022-02-28 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online | [8 empty] | STA_385D K Street
NSTAR | West Yarmouth | ESMAEX-00719 | 02673 | 20.2 | Solar & Battery | 4-64-64 | 2022-01-11 | 2022-02-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-04 | [7 empty] | 0 |  | 0 |  |  | 2022-12-05 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Centerville | ESMAEX-00711 | 02632 | 18.25 | Solar & Battery | 4-82-82 | 2022-01-05 | 2022-01-25 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-24 | [7 empty] | 0 |  | 0 |  |  | 2022-10-07 | Online |  |  |  | Cape |  |  |  |  | STA_920 Oak Street
NSTAR | Newton | ESMAEX-00716 | 02458 | 13.05 | Solar & Battery | 467-H12 | 2022-01-06 | 2022-01-26 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-20 | Online | [8 empty] | STA_467 Watertown
NSTAR | Hopkinton | ESMAEX-00809 | 01748 | 24.78 | Solar | 126-H4 | 2022-02-04 | 2022-03-18 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-30 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online | [7 empty] | 20 | STA_126 Hopkinton
NSTAR | West Newton | ESMAEX-00727 | 02465 | 15.51 | Solar & Battery | 316-03 | 2022-01-13 | 2022-02-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-24 | [7 empty] | 0 |  | 0 |  |  | 2022-04-13 | Online | [8 empty] | STA_282 Waltham
NSTAR | Marion | ESMAEX-00725 | 02738 | 10 | Solar & Battery | 3-304-304 | 2022-01-12 | 2022-02-24 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-28 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Plymouth | ESMAEX-00724 | 02360 | 43.2 | Solar | 3-89-922 | 2022-01-11 | 2022-02-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0 |  |  | 2022-08-24 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Needham | ESMAEX-00720 | 02492 | 10 | Battery | 148-07 | 2022-01-11 | 2022-02-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-11 | [7 empty] | 0 |  | 0 |  |  | 2022-07-08 | Online | [8 empty] | STA_148 Needham
NSTAR | Sudbury | ESMAEX-00723 | 01776 | 21.4 | Solar & Battery | 342-H8 | 2022-01-11 | 2022-02-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-17 | [7 empty] | 0 |  | 0 |  |  | 2022-03-14 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Watertown | ESMAEX-00726 | 02472 | 636 | Solar | 370-1323 | 2022-03-15 | 2022-04-11 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-07 | Online | [8 empty] | STA_315 Electric Avenue
NSTAR | Westwood | ESMAEX-00757 | 02090 | 15.2 | Solar & Battery | 456-H4 | 2022-01-25 | 2022-02-17 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-01-31 | Online | [8 empty] | STA_456 Dover
NSTAR | Weston | ESMAEX-00743 | 02493 | 18.148 | Solar | 282-H1 | 2022-01-20 | 2022-02-15 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Online | [8 empty] | STA_282 Waltham
NSTAR | Edgartown | ESMAEX-01133 | 02539 | 44.37 | Solar |  | 2022-05-02 | 2022-05-24 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-17 | [7 empty] | 0 |  | 0 |  |  | 2023-05-16 | Online
NSTAR | North Cambridge | ESMAEX-00732 | 02140 | 6.38 | Solar & Battery | 824-28 | 2022-01-18 | 2022-02-22 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-09 | [7 empty] | 0 |  | 0 |  |  | 2022-03-30 | Online | [8 empty] | STA_828 Alewife
NSTAR | Allston | ESMAEX-00729 | 02134 | 40 | Solar | 315-H8 | 2022-01-14 | 2022-02-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Online
NSTAR | East Harwich | ESMAEX-00737 | 02645 | 19.14 | Solar | 4-95A-95A | 2022-01-19 | 2022-02-15 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-16 | [7 empty] | 0 |  | 0 |  |  | 2022-10-26 | Technical Review |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Needham | ESMAEX-00736 | 02494 | 3.8 | Solar & Battery | 148-H4 | 2022-01-18 | 2022-06-20 | 109 |  | 109 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [8 empty] | STA_148 Needham
NSTAR | Lincoln | ESMAEX-00811 | 01773 | 7.68 | Battery | 320-H6 | 2022-02-04 | 2022-02-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-26 | [7 empty] | 0 |  | 0 |  |  | 2022-11-16 | Online | [8 empty] | STA_320 Lexington
NSTAR | Chelsea | ESMAEX-00744 | 02150 | 250 | Battery | 488-H1 | 2022-03-08 | 2022-03-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_488 Chelsea
NSTAR | Edgartown | ESMAEX-00891 | 02539 | 29 | Solar | 4-75-227 | 2022-03-09 | 2022-05-23 | 53 |  | 53 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Chelsea | ESMAEX-00745 | 02150 | 250 | Solar |  | 2022-03-08 | 2022-03-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Chelsea | ESMAEX-00747 | 02150 | 375 | Solar |  | 2022-03-08 | 2022-03-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2025-10-23 | Online
NSTAR | Cambridge | ESMAEX-00913 | 02139 | 9.15 | Solar & Battery | 816-02 | 2022-03-14 | 2022-04-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2022-11-25 | Online | [8 empty] | STA_831 Putnam
NSTAR | Waquoit | ESMAEX-00748 | 02536 | 11.52 | Solar & Battery | 4-77B-456 | 2022-01-20 | 2022-02-24 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2023-04-28 | Online
NSTAR | East Harwich | ESMAEX-00874 | 02645 | 11 | Solar & Battery | 4-95A-95A | 2022-03-03 | 2022-03-14 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2022-06-13 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Roxbury Crossing | ESMAEX-00802 | 02120 | 43.2 | Solar | 52-1499H4 | 2022-02-03 | 2022-03-16 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online
NSTAR | Chatham | ESMAEX-00820 | 02633 | 19.14 | Solar | 4-95A-606 | 2022-02-07 | 2022-04-07 | 43 |  | 43 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-05 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Sherborn | ESMAEX-00922 | 01770 | 15.705 | Solar | 274-H2 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-05 | [7 empty] | 0 |  | 0 |  |  | 2022-06-30 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Carlisle | ESMAEX-00767 | 01741 | 15.95 | Solar | 512-1399H1 | 2022-01-31 | 2022-02-22 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Falmouth | ESMAEX-00764 | 02540 | 9.6 | Solar & Battery | 4-72-72 | 2022-01-28 | 2022-02-17 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Chestnut Hill | ESMAEX-00907 | 02467 | 8 | Battery | 443-07 | 2022-03-11 | 2022-04-07 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [8 empty] | STA_110 Baker Street
NSTAR | Cambridge | ESMAEX-00758 | 02142 | 133.2 | Solar | 850-1310 | 2022-01-26 | 2022-04-19 | 59 |  | 59 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2025-06-27 | Online | [8 empty] | STA_875 East Cambridge
NSTAR | Waltham | ESMAEX-00761 | 02451 | 250 | Solar & Battery | 450-H8 | 2022-01-27 | 2022-02-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_450 Trapelo Road
NSTAR | Chelsea | ESMAEX-00888 | 02150 | 495.8 | Solar | 488-H6 | 2022-03-29 | 2022-04-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-05 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Watertown | ESMAEX-00762 | 02472 | 99.9 | Solar | 315-H4 | 2022-01-28 | 2022-03-02 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Online | [8 empty] | STA_315 Electric Avenue
NSTAR | South Dartmouth | ESMAEX-00785 | 02748 | 22.8 | Solar | 2-524-524 | 2022-02-01 | 2022-02-24 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-21 | [7 empty] | 0 |  | 0 |  |  | 2022-07-19 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_657 Fisher Road
NSTAR | Roxbury Crossing | ESMAEX-00768 | 02120 | 250 | Solar | 510-77H | 2022-03-04 | 2022-03-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-11-03 | Online | [8 empty] | STA_106 Andrew Square
NSTAR | Boston | ESMAEX-00770 | 02131 | 250 | Solar | 496-H8 | 2022-03-04 | 2022-03-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-21 | [7 empty] | 0 |  | 0 |  |  | 2025-09-19 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Boston | ESMAEX-00772 | 02124 | 480 | Solar | 483-H1 | 2022-03-14 | 2022-03-31 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2025-09-24 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Falmouth | ESMAEX-00776 | 02540 | 4999.2 | Battery | 4-76-76 | 2022-09-20 | 2022-10-13 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-16 |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Cape | Phase 2 - In Process | Cape Group Phase II | 2024 SEMA/Cape ASO Study |  | STA_933 Falmouth
NSTAR | Duxbury | ESMAEX-00807 | 02332 | 11.4 | Battery | 3-23-23 | 2022-02-04 | 2022-03-01 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-07 | [7 empty] | 0 |  | 0 |  |  | 2022-06-13 | Online
NSTAR | Woods Hole | ESMAEX-00827 | 02543 | 18.99 | Solar & Battery | 4-91-91 | 2022-02-10 | 2022-03-11 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-05 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Mattapan | ESMAEX-00796 | 02126 | 250 | Solar | 311-09 | 2022-08-04 | 2022-09-09 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Framingham | ESMAEX-00801 | 01701 | 20 | Solar | 455-H1 | 2022-02-03 | 2022-02-24 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-25 | [7 empty] | 0 |  | 0 |  |  | 2022-06-22 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Harwichport | ESMAEX-00821 | 02646 | 15.2 | Solar | 4-85-592 | 2022-02-08 | 2022-02-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-02-28 | [7 empty] | 0 |  | 0 |  |  | 2022-11-03 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Arlington | ESMAEX-00842 | 02476 | 166.5 | Solar | 211-H13 | 2022-02-18 | 2022-03-21 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-07 | [7 empty] | 0 |  | 0 |  |  | 2023-08-22 | Online | [8 empty] | STA_211 Woburn
NSTAR | Walpole | ESMAEX-00804 | 02081 | 133.3 | Solar | 146-H4 | 2022-02-03 | 2022-03-16 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-04-30 | Online | [8 empty] | STA_146 Walpole
NSTAR | East Walpole | ESMAEX-00805 | 02032 | 100 | Solar | 146-H8 | 2022-02-03 | 2022-03-16 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-04-30 | Online | [8 empty] | STA_146 Walpole
NSTAR | Hopkinton | ESMAEX-00841 | 01748 | 15.2 | Solar | 126-H4 | 2022-02-17 | 2022-03-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-10 | [7 empty] | 0 |  | 0 |  |  | 2022-06-07 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Westwood | ESMAEX-00808 | 02090 | 11 | Solar & Battery | 456-H4 | 2022-02-04 | 2022-02-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-24 | [7 empty] | 0 |  | 0 |  |  | 2022-08-19 | Online | [8 empty] | STA_456 Dover
NSTAR | East Falmouth | ESMAEX-00864 | 02536 | 15.93 | Solar | 4-76-437 | 2022-02-28 | 2022-04-12 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Edgartown | ESMAEX-00832 | 02539 | 2490 | Solar & Battery | 4-75-223 | 2022-02-14 | 2022-03-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Cape | Phase 2 - In Process | Cape Group Phase II | 2024 SEMA/Cape ASO Study |  | STA_933 Falmouth
NSTAR | Ashland | ESMAEX-01234 | 01721 | 120 | Solar | 274-1429H | 2022-05-27 | 2022-07-21 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Winchester | ESMAEX-00825 | 01890 | 19 | Solar | 211-H4 | 2022-02-09 | 2022-02-28 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0 |  |  | 2023-04-20 | Online | [8 empty] | STA_211 Woburn
NSTAR | Sherborn | ESMAEX-00824 | 01770 | 13.275 | Solar | 274-H2 | 2022-02-09 | 2022-03-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2022-07-21 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Westport | ESMAEX-00886 | 02790 | 5.12 | Battery | 2-523-523 | 2022-03-07 | 2022-07-01 | 84 |  | 84 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_657 Fisher Road
NSTAR | Hyannis | ESMAEX-00834 | 02601 | 75 | Solar | 4-63-521 | 2022-02-15 | 2022-04-15 | 43 |  | 43 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2024-06-26 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Vineyard Haven | ESMAEX-00831 | 02568 | 70 | Solar | 4-91-91 | 2022-02-12 | 2022-03-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-17 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Marshfield | ESMAEX-00838 | 02050 | 4999.2 | Battery | 3-22-973 | 2022-03-16 | 2022-05-23 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [6 empty] | 2024 SEMA/Cape ASO Study |  | STA_739 Marshfield
NSTAR | Lexington | ESMAEX-00860 | 02421 | 240 | Solar | 3402 | 2022-02-25 | 2022-03-10 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Online | [8 empty] | STA_320 Lexington
NSTAR | Lexington | ESMAEX-00861 | 02421 | 133.3 | Solar | 3402 | 2022-02-25 | 2022-03-10 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [8 empty] | STA_320 Lexington
NSTAR | Watertown | ESMAEX-00866 | 02472 | 160 | Solar |  | 2022-03-01 | 2022-03-14 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Online
NSTAR | Dennis | ESMAEX-00946 | 02638 | 17.6 | Solar & Battery | 4-89A-89A | 2022-03-18 | 2022-04-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Hopkinton | ESMAEX-00843 | 01748 | 15.2 | Solar | 126-H4 | 2022-02-21 | 2022-03-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-30 | [7 empty] | 0 |  | 0 |  |  | 2022-08-01 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Plymouth | ESMAEX-00844 | 02360 | 10.03 | Solar & Battery | 3-11-11 | 2022-02-21 | 2022-03-10 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-31 | [7 empty] | 0 |  | 0 |  |  | 2022-06-21 | Online
NSTAR | Orleans | ESMAEX-00851 | 02653 | 15.2 | Solar & Battery | 4-628-628 | 2022-02-22 | 2022-03-15 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Online | [8 empty] | STA_975 Orleans
NSTAR | Cambridge | ESMAEX-00918 | 02139 | 84.6 | Solar | 820-15 | 2022-03-15 | 2022-05-31 | 55 |  | 55 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2024-09-05 | Online | [8 empty] | STA_402 Newton Street
NSTAR | Mattapan | ESMAEX-00867 | 02126 | 60 | Solar | 311-1403H1 | 2022-03-01 | 2022-03-14 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-16 | [7 empty] | 0 |  | 0 |  |  | 2025-08-21 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Medway | ESMAEX-00859 | 02053 | 10.25 | Solar & Battery | 65-H3 | 2022-02-25 | 2022-03-11 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-25 | Online | [8 empty] | STA_065 Medway
NSTAR | South Dartmouth | ESMAEX-00863 | 02748 | 4.64 | Solar | 2-528-528 | 2022-02-28 | 2022-03-11 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-14 | [7 empty] | 0 |  | 0 |  |  | 2022-10-12 | Online
NSTAR | Newton Center | ESMAEX-00889 | 02459 | 480 | Solar | 292-H3 | 2022-04-07 | 2022-04-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-20 | [7 empty] | 0 |  | 0 |  |  | 2025-09-29 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Newton Center | ESMAEX-00984 | 02459 | 60 | Solar |  | 2022-03-29 | 2022-04-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-08-22 | Online
NSTAR | Sudbury | ESMAEX-00872 | 01776 | 15.2 | Solar & Battery | 342-H2 | 2022-03-02 | 2022-04-18 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Boston | ESMAEX-00885 | 02128 | 249.9 | Solar | 152-87H | 2022-03-07 | 2022-03-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2025-09-18 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Aquinnah | ESMAEX-00875 | 02535 | 8.7 | Solar & Battery | 4-97-97 | 2022-03-03 | 2022-03-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-23 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Newton Center | ESMAEX-00985 | 02459 | 240 | Solar | 292-H3 | 2022-03-29 | 2022-04-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-14 | [7 empty] | 0 |  | 0 |  |  | 2025-02-26 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Bedford | ESMAEX-00877 | 01730 | 16.104 | Solar | 533-H5 | 2022-03-04 | 2022-03-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-20 | [7 empty] | 0 |  | 0 |  |  | 2022-06-30 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Woburn | ESMAEX-00880 | 01801 | 15.2 | Solar | 325-03 | 2022-03-04 | 2022-03-29 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-20 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [8 empty] | STA_211 Woburn
NSTAR | Lincoln | ESMAEX-00912 | 01773 | 9.216 | Solar | 320-H6 | 2022-03-14 | 2022-03-31 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2022-09-26 | Online | [8 empty] | STA_320 Lexington
NSTAR | Medway | ESMAEX-00887 | 02053 | 6 | Solar | 65-H3 | 2022-03-07 | 2022-03-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-03-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Online | [8 empty] | STA_065 Medway
NSTAR | Chilmark | ESMAEX-01041 | 02535 | 15.2 | Solar & Battery | 4-97-97 | 2022-04-08 | 2022-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2022-10-17 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Framingham | ESMAEX-00951 | 01702 | 240 | Solar |  | 2022-03-21 | 2022-05-24 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Online
NSTAR | Milton | ESMAEX-00923 | 02186 | 15.2 | Solar & Battery | 362-1209H2 | 2022-03-15 | 2022-04-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-11 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Cambridge | ESMAEX-01252 | 02142 | 100 | Solar | 875-1N39A | 2022-06-02 | 2022-06-17 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0 |  |  | 2024-03-27 | Online | [8 empty] | STA_875 East Cambridge
NSTAR | Lincoln | ESMAEX-00917 | 01773 | 15.36 | Solar | 320-H6 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2022-10-14 | Online | [8 empty] | STA_320 Lexington
NSTAR | Natick | ESMAEX-00899 | 01760 | 86.5 | Solar | 433-H11 | 2022-03-11 | 2022-03-30 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2024-02-06 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Medway | ESMAEX-00895 | 02053 | 14.46 | Solar | 65-H5 | 2022-03-10 | 2022-03-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2022-08-22 | Online | [8 empty] | STA_065 Medway
NSTAR | Bellingham | ESMAEX-00901 | 02019 | 15.2 | Solar & Battery | 65-H4 | 2022-03-11 | 2022-03-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-10-22 | Online | [8 empty] | STA_065 Medway
NSTAR | Medway | ESMAEX-00902 | 02053 | 25.2 | Solar | 65-H3 | 2022-03-11 | 2022-03-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-03-21 | Online | [8 empty] | STA_065 Medway
NSTAR | New Bedford | ESMAEX-00900 | 02745 | 999 | Solar & Battery | 2-79-404 | 2022-04-06 | 2022-05-04 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 999 | STA_612 Acushnet
NSTAR | Wayland | ESMAEX-00903 | 01778 | 12.6 | Solar | 433-H2 | 2022-03-11 | 2022-03-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-06 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Needham | ESMAEX-01033 | 02492 | 15.2 | Solar & Battery | 148-06 | 2022-04-07 | 2022-04-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [8 empty] | STA_148 Needham
NSTAR | North Truro | ESMAEX-00908 | 02652 | 24.94 | Solar |  | 2022-03-11 | 2022-04-19 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-21 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online
NSTAR | Cotuit | ESMAEX-00929 | 02635 | 15.2 | Solar & Battery | 4-88-88 | 2022-03-16 | 2022-05-23 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-01-03 | Online |  |  |  | Cape |  |  |  |  | STA_946 Mashpee
NSTAR | Weston | ESMAEX-00949 | 02493 | 5 | Battery | 282-H1 | 2022-03-20 | 2022-06-20 | 66 |  | 66 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-05 | [7 empty] | 0 |  | 0 |  |  | 2023-08-03 | Online | [8 empty] | STA_282 Waltham
NSTAR | North Truro | ESMAEX-00919 | 02652 | 28.71 | Solar | 4-96-96 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Framingham | ESMAEX-00916 | 01702 | 3.8 | Solar | 455-H5 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Framingham | ESMAEX-00940 | 01702 | 10 | Solar & Battery | 455-H5 | 2022-03-17 | 2022-04-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2022-06-29 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Buzzards Bay | ESMAEX-00920 | 02532 | 11.4 | Solar | 3-88-88 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-11 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Newton Center | ESMAEX-00921 | 02459 | 3.5 | Solar | 1709 | 2022-03-15 | 2022-04-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2022-07-18 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Sudbury | ESMAEX-00945 | 01776 | 43.2 | Solar | 342-H2 | 2022-03-18 | 2022-04-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-24 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Needham | ESMAEX-00927 | 02494 | 15.2 | Solar & Battery | 292-H4 | 2022-03-16 | 2022-04-06 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-12 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Needham | ESMAEX-00931 | 02494 | 15.2 | Solar & Battery | 148-H4 | 2022-03-16 | 2022-04-06 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [8 empty] | STA_148 Needham
NSTAR | Holliston | ESMAEX-00936 | 01746 | 4.93 | Solar | 274-H3 | 2022-03-17 | 2022-04-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Waltham | ESMAEX-01801 | 02451 | 33.3 | Solar | 450-H7 | 2022-11-11 | 2022-12-13 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2024-09-11 | Online | [8 empty] | STA_450 Trapelo Road
NSTAR | Natick | ESMAEX-00935 | 01760 | 15.2 | Solar & Battery | 240-H1 | 2022-03-17 | 2022-04-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-28 | [7 empty] | 0 |  | 0 |  |  | 2022-06-02 | Online | [8 empty] | STA_240 Framingham
NSTAR | Fairhaven | ESMAEX-00938 | 02719 | 200 | Solar | 2-230-230 | 2022-06-22 | 2022-07-20 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-01 | [7 empty] | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_612 Acushnet
NSTAR | Boston | ESMAEX-00953 | 02118 | 51.9 | Solar | 218-80H1 | 2022-03-21 | 2022-04-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-08 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Online | [8 empty] | STA_250 Mystic
NSTAR | Canton | ESMAEX-00947 | 02021 | 7.6 | Solar & Battery | 470-H10 | 2022-03-19 | 2022-04-14 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Online | [8 empty] | STA_470 Canton
NSTAR | Newton Center | ESMAEX-00956 | 02459 | 15.2 | Solar & Battery | 292-H6 | 2022-03-22 | 2022-04-21 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-02-10 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Arlington | ESMAEX-01083 | 02476 | 13 | Solar & Battery | 320-H7 | 2022-04-15 | 2022-05-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-10-13 | Online | [8 empty] | STA_320 Lexington
NSTAR | Bourne | ESMAEX-00959 | 02532 | 18 | Solar | 4-86-408 | 2022-03-23 | 2022-04-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2023-01-26 | Online |  |  |  | Cape |  |  |  |  | STA_915 Otis
NSTAR | West Dennis | ESMAEX-00986 | 02670 | 3.8 | Solar & Battery | 4-92B-92B | 2022-03-29 | 2022-04-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Acton | ESMAEX-00962 | 01720 | 15.2 | Solar & Battery | 416-H1 | 2022-03-24 | 2022-04-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Online | [8 empty] | STA_416 Maynard
NSTAR | Waban | ESMAEX-00960 | 02468 | 23.424 | Solar | 292-H2 | 2022-03-23 | 2022-04-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-00967 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2022-03-25 | 2022-04-14 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-10-16 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | East Falmouth | ESMAEX-00963 | 02536 | 15.2 | Solar & Battery | 4-98B-449 | 2022-03-24 | 2022-04-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-01-17 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Plymouth | ESMAEX-00964 | 02360 | 15.2 | Solar & Battery | 3-89-925 | 2022-03-24 | 2022-04-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-04-10 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Canton | ESMAEX-00961 | 02021 | 250 | Solar | 269-1320H1 | 2022-06-06 | 2022-06-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-10 | Online | [8 empty] | STA_470 Canton
NSTAR | Allston | ESMAEX-00972 | 02134 | 34.6 | Solar | 315-H3 | 2022-03-28 | 2022-04-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-13 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [8 empty] | STA_315 Electric Avenue
NSTAR | Carlisle | ESMAEX-00987 | 01741 | 15.2 | Solar & Battery | 533-H8 | 2022-03-29 | 2022-05-02 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Falmouth | ESMAEX-00968 | 02540 | 15.2 | Solar & Battery | 4-72-72 | 2022-03-25 | 2022-04-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-06-01 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Marshfield | ESMAEX-00974 | 02050 | 7.6 | Solar & Battery | 3-24A-974 | 2022-03-28 | 2022-04-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-03-09 | Online | [8 empty] | STA_739 Marshfield
NSTAR | East Freetown | ESMAEX-00965 | 02717 | 15.2 | Solar | 2-108-108 | 2022-03-24 | 2022-04-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-15 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Lexington | ESMAEX-00970 | 02420 | 7.6 | Solar & Battery | 3406 | 2022-03-26 | 2022-04-14 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-18 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online
NSTAR | West Dennis | ESMAEX-00971 | 02670 | 15.2 | Solar & Battery | 4-92B-571 | 2022-03-27 | 2022-04-28 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-06 | Online | [8 empty] | STA_968 Harwich
NSTAR | Marion | ESMAEX-01255 | 02738 | 17.568 | Solar |  | 2022-06-03 | 2022-08-10 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online
NSTAR | New Bedford | ESMAEX-00976 | 02746 | 480 | Solar | 2-81-81 | 2022-06-08 | 2022-08-15 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-09 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_612 Acushnet
NSTAR | Edgartown | ESMAEX-01006 | 02539 | 132.48 | Solar | 4-75-75 | 2022-04-04 | 2022-04-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-03 | [7 empty] | 0 |  | 0 |  |  | 2024-08-30 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Vineyard Haven | ESMAEX-01005 | 02568 | 156.16 | Solar | 4-75-75 | 2022-04-04 | 2022-04-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Oak Bluffs | ESMAEX-00991 | 02557 | 20 | Solar | 4-99-225 | 2022-03-30 | 2022-04-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-04-18 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | New Bedford | ESMAEX-00996 | 02740 | 120 | Solar | 2-83-403 | 2022-03-31 | 2022-04-15 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2022-11-01 | Online | [8 empty] | STA_612 Acushnet
NSTAR | Boston | ESMAEX-00995 | 02118 | 250 | Solar |  | 2022-06-15 | 2022-08-01 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2024-06-05 | Online
NSTAR | Walpole | ESMAEX-00997 | 02081 | 10 | Solar | 146-H4 | 2022-03-31 | 2022-05-26 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-24 | Online | [8 empty] | STA_146 Walpole
NSTAR | Newton Center | ESMAEX-01398 | 02459 | 22.5 | Solar & Battery | 292-H6 | 2022-07-21 | 2022-08-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-15 | [7 empty] | 0 |  | 0 |  |  | 2023-09-11 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Chestnut Hill | ESMAEX-01000 | 02467 | 15.2 | Solar | 443-07 | 2022-04-01 | 2022-08-15 | 96 |  | 96 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Online | [8 empty] | STA_110 Baker Street
NSTAR | East Walpole | ESMAEX-01003 | 02032 | 17.6 | Solar & Battery | 146-H4 | 2022-04-04 | 2022-04-21 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [8 empty] | STA_146 Walpole
NSTAR | Winchester | ESMAEX-01017 | 01890 | 15.2 | Solar & Battery | 211-H10 | 2022-04-06 | 2022-04-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [8 empty] | STA_211 Woburn
NSTAR | Westwood | ESMAEX-01082 | 02090 | 20.2 | Solar & Battery | 148-H3 | 2022-04-15 | 2022-05-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-29 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Online | [8 empty] | STA_148 Needham
NSTAR | Newton Center | ESMAEX-01004 | 02459 | 492 | Solar | 292-H11 | 2022-04-27 | 2022-05-12 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-03 | [7 empty] | 0 |  | 0 |  |  | 2025-10-30 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Newton Center | ESMAEX-01094 | 02459 | 240 | Solar | 292-H3 | 2022-04-20 | 2022-06-14 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2025-12-22 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Stoneham | ESMAEX-01007 | 02180 | 15.2 | Solar | 375-H8 | 2022-04-04 | 2022-04-28 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-28 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Acton | ESMAEX-01055 | 01720 | 12.6 | Solar & Battery | 416-H9 | 2022-04-08 | 2022-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-08 | [7 empty] | 0 |  | 0 |  |  | 2023-02-28 | Online | [8 empty] | STA_416 Maynard
NSTAR | South Yarmouth | ESMAEX-01089 | 02664 | 18.56 | Solar | 4-92A-92A | 2022-04-18 | 2022-05-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Westwood | ESMAEX-01016 | 02090 | 15.2 | Solar | 148-H3 | 2022-04-06 | 2022-05-23 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online | [8 empty] | STA_148 Needham
NSTAR | Lexington | ESMAEX-01043 | 02420 | 9.3 | Solar | 533-H9 | 2022-04-08 | 2022-04-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-07-12 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Chestnut Hill | ESMAEX-01030 | 02467 | 25.2 | Solar & Battery | 443-08 | 2022-04-07 | 2022-04-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Online | [8 empty] | STA_110 Baker Street
NSTAR | Holliston | ESMAEX-01022 | 01746 | 15.2 | Solar & Battery | 65-H5 | 2022-04-06 | 2022-04-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-02-22 | Online | [8 empty] | STA_065 Medway
NSTAR | East Sandwich | ESMAEX-01023 | 02537 | 26.4 | Solar & Battery | 4-87A-87A | 2022-04-06 | 2022-04-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-05-17 | Online |  |  |  | Cape |  |  |  |  | STA_916 Sandwich
NSTAR | East Walpole | ESMAEX-01027 | 02032 | 15.2 | Solar & Battery | 146-H4 | 2022-04-06 | 2022-04-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Online | [8 empty] | STA_146 Walpole
NSTAR | East Falmouth | ESMAEX-01031 | 02536 | 15.2 | Solar & Battery | 4-77A-77A | 2022-04-07 | 2022-04-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-01-26 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | New Bedford | ESMAEX-01034 | 02745 | 15.2 | Solar & Battery | 2-106-161 | 2022-04-07 | 2022-04-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2023-05-11 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Boston | ESMAEX-01026 | 02210 | 300 | Solar | 385-H12 | 2022-06-17 | 2022-07-13 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-22 | [7 empty] | 0 |  | 0 |  |  | 2024-08-15 | Online | [8 empty] | STA_385D K Street
NSTAR | Sherborn | ESMAEX-01028 | 01770 | 30 | Solar | 240-H1 | 2022-04-07 | 2022-04-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-01-18 | Online | [8 empty] | STA_240 Framingham
NSTAR | Brewster | ESMAEX-01058 | 02631 | 25.2 | Solar & Battery | 4-89A-89A | 2022-04-08 | 2022-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2023-01-05 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Boston | ESMAEX-01105 | 02215 | 170 | Solar | 508-91 | 2022-04-24 | 2022-05-23 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-04-03 | Online | [8 empty] | STA_329 Brighton
NSTAR | Boston | ESMAEX-01104 | 02215 | 70 | Solar | 329-H9 | 2022-04-24 | 2022-05-23 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-04-03 | Online | [8 empty] | STA_329 Brighton
NSTAR | East Falmouth | ESMAEX-01299 | 02536 | 20 | Solar & Battery | 4-98B-449 | 2022-06-16 | 2022-07-13 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Natick | ESMAEX-01038 | 01760 | 15.2 | Solar & Battery | 240-H5 | 2022-04-07 | 2022-04-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Online | [8 empty] | STA_240 Framingham
NSTAR | Norfolk | ESMAEX-01039 | 02056 | 21 | Solar & Battery | 146-H10 | 2022-04-07 | 2022-04-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2022-10-19 | Online | [7 empty] | 15.2 | STA_146 Walpole
NSTAR | Canton | ESMAEX-01296 | 02021 | 20.2 | Solar & Battery | 470-H9 | 2022-06-15 | 2022-07-13 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-24 | [7 empty] | 0 |  | 0 |  |  | 2023-02-22 | Online | [8 empty] | STA_470 Canton
NSTAR | Stoneham | ESMAEX-01052 | 02180 | 15.2 | Solar & Battery | 375-H8 | 2022-04-08 | 2022-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-05-03 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Dorchester | ESMAEX-01137 | 02125 | 43.5 | Solar | 483-H3 | 2022-05-03 | 2022-05-26 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-12-27 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Dorchester | ESMAEX-01138 | 02125 | 31.7 | Solar | 6703 | 2022-05-03 | 2022-05-26 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2023-12-27 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Sharon | ESMAEX-01049 | 02067 | 15.2 | Solar & Battery | 470-H12 | 2022-04-08 | 2022-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-26 | [7 empty] | 0 |  | 0 |  |  | 2023-04-10 | Online | [8 empty] | STA_470 Canton
NSTAR | Carlisle | ESMAEX-01086 | 01741 | 17.9 | Solar | 512-1399H1 | 2022-04-16 | 2022-05-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2022-07-20 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Roxbury | ESMAEX-01062 | 02119 | 50 | Solar | 510-77H3 | 2022-04-11 | 2022-04-28 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-02 | [7 empty] | 0 |  | 0 |  |  | 2023-03-08 | Online | [8 empty] | STA_106 Andrew Square
NSTAR | Wellfleet | ESMAEX-01100 | 02667 | 21.83 | Solar | 4-96-96 | 2022-04-22 | 2022-05-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-07-21 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Allston | ESMAEX-01066 | 02134 | 480 | Solar | 508-91 | 2022-05-20 | 2022-06-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-24 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Online | [8 empty] | STA_329 Brighton
NSTAR | Hopkinton | ESMAEX-01067 | 01748 | 250 | Solar | 65-H7 | 2022-05-11 | 2022-06-22 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-19 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Online | [8 empty] | STA_065 Medway
NSTAR | Chilmark | ESMAEX-01069 | 02535 | 24.3 | Solar | 4-97-97 | 2022-04-11 | 2022-04-28 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-06 | [7 empty] | 0 |  | 0 |  |  | 2022-10-18 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Hopkinton | ESMAEX-01068 | 01748 | 120 | Solar | 126-H2 | 2022-05-11 | 2022-06-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Sharon | ESMAEX-01113 | 02067 | 8.85 | Solar & Battery | 146-H7 | 2022-04-26 | 2022-05-24 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-29 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online | [8 empty] | STA_146 Walpole
NSTAR | Boston | ESMAEX-01155 | 02119 | 30.16 | Solar | 396-1050H | 2022-05-06 | 2022-06-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Orleans | ESMAEX-01147 | 02653 | 10 | Battery | 4-89B-89B | 2022-05-05 | 2022-05-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2022-10-05 | Online | [8 empty] | STA_975 Orleans
NSTAR | Weston | ESMAEX-01079 | 02493 | 7.6 | Solar & Battery | 282-H8 | 2022-04-13 | 2022-05-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-05 | [7 empty] | 0 |  | 0 |  |  | 2023-01-30 | Online | [8 empty] | STA_282 Waltham
NSTAR | South Sandwich | ESMAEX-01088 | 02563 | 15.2 | Solar & Battery | 4-81B-81B | 2022-04-16 | 2022-05-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-11-21 | Online |  |  |  | Cape |  |  |  |  | STA_916 Sandwich
NSTAR | Holliston | ESMAEX-01080 | 01746 | 15.18 | Solar | 65-H5 | 2022-04-14 | 2022-05-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-02-10 | Online | [8 empty] | STA_065 Medway
NSTAR | Waltham | ESMAEX-01084 | 02451 | 17.6 | Solar & Battery | 282-H7 | 2022-04-15 | 2022-05-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [8 empty] | STA_282 Waltham
NSTAR | Kingston | ESMAEX-01095 | 02364 | 15.2 | Solar & Battery | 3-18-18 | 2022-04-20 | 2022-05-26 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-16 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Online
NSTAR | Bourne | ESMAEX-01091 | 02532 | 6 | Solar & Battery | 4-86-86 | 2022-04-19 | 2022-05-23 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-09 | Online |  |  |  | Cape |  |  |  |  | STA_915 Otis
NSTAR | Plymouth | ESMAEX-01125 | 02360 | 10 | Solar | 3-90-90 | 2022-04-29 | 2022-05-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-20 | [7 empty] | 0 |  | 0 |  |  | 2022-11-17 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Plymouth | ESMAEX-01098 | 02360 | 7 | Battery | 3-73-938 | 2022-04-21 | 2022-05-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-02-24 | Online |  |  |  | Plymouth |  |  |  |  | STA_721 Manomet
NSTAR | Westwood | ESMAEX-01786 | 02090 | 10 | Solar & Battery | 148-H3 | 2022-11-08 | 2022-12-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online | [8 empty] | STA_148 Needham
NSTAR | Burlington | ESMAEX-01115 | 01803 | 6.4 | Battery | 391-H7 | 2022-04-26 | 2022-05-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-20 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Online | [8 empty] | STA_391 Burlington
NSTAR | Plymouth | ESMAEX-01111 | 02360 | 10 | Battery | 3-89-922 | 2022-04-25 | 2022-07-21 | 63 |  | 63 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Natick | ESMAEX-01103 | 01760 | 18.29 | Solar | 433-H7 | 2022-04-22 | 2022-05-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-15 | [7 empty] | 0 |  | 0 |  |  | 2022-10-17 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Cambridge | ESMAEX-01099 | 02138 | 10 | Solar & Battery | 827-21 | 2022-04-21 | 2022-06-02 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [8 empty] | STA_828 Alewife
NSTAR | Acton | ESMAEX-01112 | 01720 | 17 | Solar & Battery | 416-H8 | 2022-04-25 | 2022-05-26 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [8 empty] | STA_416 Maynard
NSTAR | Framingham | ESMAEX-01108 | 01702 | 480 | Solar | 455-H5 | 2022-05-20 | 2022-06-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-07 | [7 empty] | 0 |  | 0 |  |  | 2025-12-16 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Vineyard Haven | ESMAEX-01162 | 02568 | 25 | Solar |  | 2022-05-10 | 2022-06-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2022-09-02 | Online
NSTAR | South Yarmouth | ESMAEX-01232 | 02664 | 20.2 | Solar & Battery | 4-92A-560 | 2022-05-27 | 2022-06-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Marion | ESMAEX-01896 | 02738 | 20.65 | Solar | 3-304-304 | 2022-12-06 | 2023-05-03 | 106 |  | 106 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-08-01 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Mattapan | ESMAEX-01121 | 02126 | 24.78 | Solar | 441-02 | 2022-04-27 | 2022-05-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-23 | [7 empty] | 0 |  | 0 |  |  | 2022-11-18 | Online | [8 empty] | STA_441 Wilmont Street
NSTAR | Hyannis | ESMAEX-01119 | 02601 | 7.6 | Solar & Battery |  | 2022-04-27 | 2022-05-17 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-05-31 | [7 empty] | 0 |  | 0 |  |  | 2022-08-12 | Online
NSTAR | North Falmouth | ESMAEX-01123 | 02556 | 15.29 | Battery | 4-78-420 | 2022-04-28 | 2022-05-18 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-20 | [7 empty] | 0 |  | 0 |  |  | 2022-08-26 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Wayland | ESMAEX-01143 | 01778 | 10.248 | Solar & Battery | 342-H1 | 2022-05-04 | 2022-05-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Holliston | ESMAEX-01124 | 01746 | 19.99 | Solar & Battery | 65-H2 | 2022-04-28 | 2022-05-18 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-27 | [7 empty] | 0 |  | 0 |  |  | 2024-02-13 | Online | [8 empty] | STA_065 Medway
NSTAR | Jamaica Plain | ESMAEX-01150 | 02130 | 50 | Solar | 284-1430H | 2022-05-05 | 2022-05-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-01 | [7 empty] | 0 |  | 0 |  |  | 2025-06-02 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Framingham | ESMAEX-01130 | 01702 | 67.3 | Solar | 455-H5 | 2022-04-29 | 2022-05-24 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-14 | [7 empty] | 0 |  | 0 |  |  | 2024-03-19 | Online | [8 empty] | STA_455 West Framingham
NSTAR | New Bedford | ESMAEX-01197 | 02740 | 100 | Solar | 2-55-47 | 2022-05-19 | 2022-06-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Online | [8 empty] | STA_611 Pine Street
NSTAR | Duxbury | ESMAEX-01131 | 02332 | 4990 | Battery | 3-25-25 | 2022-10-04 | 2022-11-30 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [6 empty] | 2024 SEMA/Cape ASO Study | 4990 | STA_738 Duxbury
NSTAR | Lincoln | ESMAEX-01144 | 01773 | 25.828 | Solar | 320-H6 | 2022-05-04 | 2022-05-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online | [8 empty] | STA_320 Lexington
NSTAR | Newton Center | ESMAEX-01145 | 02459 | 19.398 | Solar | 292-H12 | 2022-05-04 | 2022-05-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-28 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Edgartown | ESMAEX-01136 | 02539 | 34.2 | Solar | 4-75-75 | 2022-05-03 | 2022-05-31 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Lexington | ESMAEX-01142 | 02420 | 8.4 | Solar | 533-H4 | 2022-05-04 | 2022-05-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | East Brewster | ESMAEX-01151 | 02631 | 10 | Battery | 4-89B-577 | 2022-05-05 | 2022-05-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-02 | [7 empty] | 0 |  | 0 |  |  | 2022-09-09 | Online | [8 empty] | STA_975 Orleans
NSTAR | Hopkinton | ESMAEX-01154 | 01748 | 140 | Solar | 65-H7 | 2022-05-06 | 2022-06-14 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2023-06-20 | Online | [8 empty] | STA_065 Medway
NSTAR | Walpole | ESMAEX-01156 | 02081 | 250 | Solar | 146-H6 | 2022-05-06 | 2022-06-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_146 Walpole
NSTAR | Burlington | ESMAEX-01213 | 01803 | 15.2 | Solar & Battery | 391-H16 | 2022-05-24 | 2022-06-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-19 | [7 empty] | 0 |  | 0 |  |  | 2023-09-07 | Online | [8 empty] | STA_391 Burlington
NSTAR | East Boston | ESMAEX-01170 | 02128 | 43.5 | Solar | 108-196H1 | 2022-05-11 | 2022-06-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-06-16 | Online | [8 empty] | STA_488 Chelsea
NSTAR | East Walpole | ESMAEX-01149 | 02032 | 9.74 | Solar & Battery | 146-H4 | 2022-05-05 | 2022-05-25 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Online | [8 empty] | STA_146 Walpole
NSTAR | South Yarmouth | ESMAEX-01173 | 02664 | 79.8 | Solar | 4-92A-563 | 2022-05-11 | 2022-06-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2023-10-10 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Carlisle | ESMAEX-01172 | 01741 | 16.24 | Solar | 533-H8 | 2022-05-11 | 2022-06-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-18 | Online | [7 empty] | 7.68 | STA_533 Hartwell Avenue
NSTAR | Sudbury | ESMAEX-01152 | 01776 | 15.2 | Solar | 342-H2 | 2022-05-05 | 2022-06-29 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-01 | [7 empty] | 0 |  | 0 |  |  | 2023-08-14 | Online | [7 empty] | 15.2 | STA_342 Sudbury
NSTAR | Westwood | ESMAEX-01177 | 02090 | 15.045 | Solar | 456-H1 | 2022-05-12 | 2022-06-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-17 | Online | [8 empty] | STA_456 Dover
NSTAR | Woods Hole | ESMAEX-01153 | 02543 | 7.8 | Solar & Battery | 4-91-91 | 2022-05-06 | 2022-05-26 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2023-04-24 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Wayland | ESMAEX-01157 | 01778 | 24.192 | Solar | 342-H1 | 2022-05-09 | 2022-06-03 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online | [8 empty] | STA_342 Sudbury
NSTAR | East Boston | ESMAEX-01169 | 02128 | 43.5 | Solar | 108-196H1 | 2022-05-11 | 2022-06-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2023-06-16 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Natick | ESMAEX-01178 | 01760 | 160 | Solar | 23-H1 | 2022-05-13 | 2022-06-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0 |  |  | 2024-01-16 | Online | [8 empty] | STA_240 Framingham
NSTAR | Bedford | ESMAEX-01215 | 01730 | 15.2 | Solar & Battery | 533-H8 | 2022-05-24 | 2022-06-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2023-01-17 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Milton | ESMAEX-01160 | 02186 | 11.52 | Solar & Battery | 362-02 | 2022-05-09 | 2022-06-02 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2023-05-17 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Stoneham | ESMAEX-01174 | 02180 | 1500 | Solar & Battery | 375-H8 | 2022-06-03 | 2022-06-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [6 empty] | 2023 ASO Batch 1 |  | STA_375 Dragon Court
NSTAR | West Wareham | ESMAEX-01200 | 02576 | 15.045 | Solar | MID-702 | 2022-05-20 | 2022-06-23 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Online
NSTAR | Ashland | ESMAEX-01167 | 01721 | 29.5 | Solar & Battery | 274-H5 | 2022-05-11 | 2022-06-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-15 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Acusnet | ESMAEX-01310 | 02743 | 11.52 | Battery | 2-241-241 | 2022-06-20 | 2022-07-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2022-12-19 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_624 Wing Lane
NSTAR | Lexington | ESMAEX-01196 | 02420 | 34.6 | Solar | 533-H4 | 2022-05-19 | 2022-06-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | North Dartmouth | ESMAEX-01179 | 02747 | 10 | Solar & Battery | 2-541-541 | 2022-05-13 | 2022-06-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-07 | [7 empty] | 0 |  | 0 |  |  | 2022-11-09 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Boston | ESMAEX-01202 | 02128 | 100 | Solar | 108-195H4 | 2022-05-20 | 2022-06-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2024-04-15 | Online | [8 empty] | STA_488 Chelsea
NSTAR | East Boston | ESMAEX-01201 | 02128 | 100 | Solar | 108-195H1 | 2022-05-20 | 2022-06-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-05-21 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Canton | ESMAEX-01176 | 02021 | 15.2 | Solar & Battery | 470-H8 | 2022-05-12 | 2022-07-21 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2022-12-12 | Online | [8 empty] | STA_470 Canton
NSTAR | Lincoln | ESMAEX-01233 | 01773 | 24.78 | Solar | 320-H6 | 2022-05-27 | 2022-06-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-30 | [7 empty] | 0 |  | 0 |  |  | 2023-08-22 | Online | [8 empty] | STA_320 Lexington
NSTAR | Framingham | ESMAEX-01181 | 01701 | 16.512 | Solar | 278-H2 | 2022-05-15 | 2022-06-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Online | [8 empty] | STA_278 Saxonville
NSTAR | West Harwich | ESMAEX-01185 | 02671 | 17.2 | Solar & Battery | 4-85-925 | 2022-05-16 | 2022-07-26 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-12-29 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | South Dartmouth | ESMAEX-01228 | 02748 | 15.2 | Solar | 2-528-528 | 2022-05-26 | 2022-06-28 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-05 | [7 empty] | 0 |  | 0 |  |  | 2022-10-27 | Online
NSTAR | Hopkinton | ESMAEX-01184 | 01748 | 16.4 | Solar & Battery | 130-H1 | 2022-05-16 | 2022-06-06 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online | [8 empty] | STA_130 Holliston
NSTAR | Lexington | ESMAEX-01186 | 02421 | 15.3 | Solar | 320-H5XY | 2022-05-17 | 2022-06-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-07 | [7 empty] | 0 |  | 0 |  |  | 2023-03-06 | Online | [8 empty] | STA_320 Lexington
NSTAR | Dover | ESMAEX-01238 | 02030 | 19.8 | Solar & Battery | 456-H5 | 2022-06-01 | 2022-07-13 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-02 | Online | [8 empty] | STA_456 Dover
NSTAR | Westwood | ESMAEX-01194 | 02090 | 25 | Solar | 148-H3 | 2022-05-18 | 2022-06-13 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-13 | Online | [8 empty] | STA_148 Needham
NSTAR | Sudbury | ESMAEX-01193 | 01776 | 15.2 | Solar & Battery | 342-H4 | 2022-05-18 | 2022-06-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-09 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Jamaica Plain | ESMAEX-01195 | 02130 | 3.8 | Solar | 496-H4 | 2022-05-18 | 2022-06-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-13 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [7 empty] | 3.84 | STA_496 Hyde Park
NSTAR | Carlisle | ESMAEX-01198 | 01741 | 15.2 | Solar | 533-H8 | 2022-05-19 | 2022-06-17 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-18 | [7 empty] | 0 |  | 0 |  |  | 2023-01-30 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Sharon | ESMAEX-01212 | 02067 | 15.2 | Solar & Battery | 470-H12 | 2022-05-23 | 2022-06-17 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-03 | Online | [8 empty] | STA_470 Canton
NSTAR | Winchester | ESMAEX-01203 | 01890 | 9.984 | Solar & Battery | 211-H6 | 2022-05-20 | 2022-06-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-15 | Online | [8 empty] | STA_211 Woburn
NSTAR | Bellingham | ESMAEX-01253 | 02019 | 20 | Solar | 65-H4 | 2022-06-02 | 2022-06-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-27 | [7 empty] | 0 |  | 0 |  |  | 2022-11-01 | Online | [8 empty] | STA_065 Medway
NSTAR | Lexington | ESMAEX-01256 | 02421 | 19.175 | Solar | 320-H5XY | 2022-06-06 | 2022-06-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-06 | [7 empty] | 0 |  | 0 |  |  | 2022-10-28 | Online | [8 empty] | STA_320 Lexington
NSTAR | Holliston | ESMAEX-01204 | 01746 | 15.2 | Solar & Battery | 274-H3 | 2022-05-20 | 2022-06-17 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Burlington | ESMAEX-01211 | 01803 | 10.03 | Solar & Battery | 346-1395H1 | 2022-05-23 | 2022-06-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-19 | [7 empty] | 0 |  | 0 |  |  | 2023-11-07 | Online | [8 empty] | STA_391 Burlington
NSTAR | Fairhaven | ESMAEX-01216 | 02719 | 15.2 | Solar | 2-220-201 | 2022-05-24 | 2022-06-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-22 | [7 empty] | 0 |  | 0 |  |  | 2022-10-21 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_654 Arsene
NSTAR | Lincoln | ESMAEX-01217 | 01773 | 14.455 | Solar & Battery | 320-H8 | 2022-05-25 | 2022-06-23 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online | [8 empty] | STA_320 Lexington
NSTAR | Lexington | ESMAEX-01235 | 02420 | 22.85 | Solar & Battery | 391-H11 | 2022-05-30 | 2022-07-21 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online | [8 empty] | STA_391 Burlington
NSTAR | Wayland | ESMAEX-01225 | 01778 | 16 | Solar | 342-H1 | 2022-05-26 | 2022-06-15 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Dedham | ESMAEX-01226 | 02026 | 999 | Solar | 20-H1 | 2022-07-19 | 2022-08-02 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_110 Baker Street
NSTAR | Needham | ESMAEX-01227 | 02494 | 10 | Solar & Battery | 292-H4 | 2022-05-26 | 2022-06-28 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Natick | ESMAEX-01236 | 01760 | 6.6 | Solar & Battery | 433-H12 | 2022-05-31 | 2022-06-23 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-09 | [7 empty] | 0 |  | 0 |  |  | 2022-10-19 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Westwood | ESMAEX-01242 | 02090 | 486 | Solar | 456-H4 | 2022-12-05 | 2023-01-26 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-21 | [7 empty] | 0 |  | 0 |  |  | 2026-01-21 | Online | [7 empty] | 499 | STA_456 Dover
NSTAR | Hopkinton | ESMAEX-01231 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-05-27 | 2022-06-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-01 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Carlisle | ESMAEX-01237 | 01741 | 7.2 | Battery | 533-H8 | 2022-06-01 | 2022-06-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-08 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Online | [7 empty] | 7.68 | STA_533 Hartwell Avenue
NSTAR | Maynard | ESMAEX-01239 | 01754 | 430 | Solar | 416-H6 | 2023-01-04 | 2023-02-01 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2024-09-04 | Online | [8 empty] | STA_416 Maynard
NSTAR | West Tisbury | ESMAEX-01243 | 02575 | 17.6 | Solar & Battery | 4-97-97 | 2022-06-02 | 2022-06-17 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-26 | [7 empty] | 0 |  | 0 |  |  | 2022-12-01 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Dartmouth | ESMAEX-01244 | 02748 | 498 | Solar | 2-53-65 | 2022-10-04 | 2022-10-27 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-25 | [7 empty] | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_611 Pine Street
NSTAR | Osterville | ESMAEX-01248 | 02655 | 18.59 | Solar | 4-88-88 | 2022-06-02 | 2022-07-01 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Online |  |  |  | Cape |  |  |  |  | STA_946 Mashpee
NSTAR | Bedford | ESMAEX-01278 | 01730 | 7.08 | Solar & Battery |  | 2022-06-10 | 2022-07-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-12 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Online
NSTAR | Buzzards Bay | ESMAEX-01254 | 02532 | 6 | Battery | 3-88-2J3 | 2022-06-03 | 2022-06-21 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-06-23 | [7 empty] | 0 |  | 0 |  |  | 2023-07-28 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | West Somerville | ESMAEX-01294 | 02144 | 8.418 | Solar & Battery | 250-H6 | 2022-06-14 | 2022-07-13 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-19 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online | [8 empty] | STA_250 Mystic
NSTAR | Maynard | ESMAEX-01262 | 01754 | 62.5 | Solar | 342-H8 | 2022-06-07 | 2022-06-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Newton Center | ESMAEX-01338 | 02459 | 67.3 | Solar | 443-02 | 2022-06-30 | 2022-07-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-05-22 | Online | [8 empty] | STA_110 Baker Street
NSTAR | Waltham | ESMAEX-01259 | 02452 | 15.2 | Solar & Battery | 450-H4 | 2022-06-07 | 2022-06-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Online | [8 empty] | STA_450 Trapelo Road
NSTAR | Lexington | ESMAEX-01497 | 02421 | 15.2 | Solar & Battery | 3401 | 2022-08-23 | 2022-09-27 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2023-08-31 | Online | [7 empty] | 19.9 | STA_320 Lexington
NSTAR | Acton | ESMAEX-01260 | 01720 | 17.6 | Solar & Battery | 416-H9 | 2022-06-07 | 2022-06-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [8 empty] | STA_416 Maynard
NSTAR | Carver | ESMAEX-01387 | 02330 | 38 | Solar | 3-11-11 | 2022-07-19 | 2022-08-17 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-25 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online
NSTAR | Maynard | ESMAEX-01263 | 01754 | 125 | Solar | 342-H8 | 2022-06-07 | 2022-06-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-14 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Maynard | ESMAEX-01264 | 01754 | 33.3 | Solar | 342-H8 | 2022-06-07 | 2022-06-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Maynard | ESMAEX-01266 | 01754 | 125 | Solar | 416-H6 | 2022-06-07 | 2022-06-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [8 empty] | STA_416 Maynard
NSTAR | Maynard | ESMAEX-01267 | 01754 | 487.5 | Solar | 342-H8 | 2022-08-15 | 2022-09-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Boston | ESMAEX-01315 | 02134 | 200 | Solar | 329-H2 | 2022-06-21 | 2022-07-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2025-01-27 | Online | [8 empty] | STA_329 Brighton
NSTAR | Dorchester | ESMAEX-01305 | 02125 | 499 | Solar | 106-H2 | 2022-06-17 | 2022-07-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-08 | [7 empty] | 0 |  | 0 |  |  | 2024-01-02 | Online | [8 empty] | STA_106 Andrew Square
NSTAR | Carlisle | ESMAEX-01275 | 01741 | 21.4 | Solar | 512-1399H1 | 2022-06-09 | 2022-06-24 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-20 | [7 empty] | 0 |  | 0 |  |  | 2024-06-06 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Westwood | ESMAEX-01283 | 02090 | 16.5 | Solar | 456-H1 | 2022-06-10 | 2022-07-18 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2022-11-28 | Online | [8 empty] | STA_456 Dover
NSTAR | Lexington | ESMAEX-01312 | 02420 | 11.4 | Solar & Battery |  | 2022-06-20 | 2022-07-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-05-02 | Online
NSTAR | Sharon | ESMAEX-01683 | 02067 | 230 | Other | 146-H1 | 2022-10-14 | 2022-11-04 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-05 | [7 empty] | 0 |  | 0 |  |  | 2024-03-12 | Online | [7 empty] | 230 | STA_146 Walpole
NSTAR | Needham | ESMAEX-01285 | 02492 | 20 | Solar | 148-01 | 2022-06-13 | 2022-07-08 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-25 | [7 empty] | 0 |  | 0 |  |  | 2022-12-06 | Online | [8 empty] | STA_148 Needham
NSTAR | Eastham | ESMAEX-01290 | 02642 | 3.8 | Solar | 4-94A-94A | 2022-06-14 | 2022-08-23 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-03-28 | Online | [8 empty] | STA_975 Orleans
NSTAR | Natick | ESMAEX-01331 | 01760 | 15.2 | Solar | 433-H12 | 2022-06-28 | 2022-09-29 | 67 |  | 67 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Chilmark | ESMAEX-01416 | 02535 | 8.26 | Solar & Battery | 4-97-97 | 2022-07-28 | 2022-08-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Burlington | ESMAEX-01320 | 01803 | 15.3 | Solar | 391-H7 | 2022-06-24 | 2022-07-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-01-05 | Online | [8 empty] | STA_391 Burlington
NSTAR | Plymouth | ESMAEX-01309 | 02360 | 10 | Solar & Battery | 3-90-90 | 2022-06-18 | 2022-07-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-13 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Dover | ESMAEX-01313 | 02030 | 38.904 | Solar & Battery | 456-H5 | 2022-06-21 | 2022-10-25 | 90 |  | 90 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-31 | Online | [8 empty] | STA_456 Dover
NSTAR | Lexington | ESMAEX-01526 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2022-08-30 | 2022-09-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-26 | [7 empty] | 0 |  | 0 |  |  | 2023-10-04 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Green Harbor | ESMAEX-01300 | 02041 | 103.68 | Solar | 3-27-27 | 2024-01-09 | 2024-01-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-03 | [7 empty] | 0 |  | 0 |  |  | 2025-09-08 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Ashland | ESMAEX-01362 | 01721 | 15.2 | Solar & Battery | 274-H6 | 2022-07-11 | 2022-08-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online
NSTAR | Lincoln | ESMAEX-01394 | 01773 | 22.6 | Solar & Battery | 320-H8 | 2022-07-20 | 2022-08-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-12 | [7 empty] | 0 |  | 0 |  |  | 2023-02-23 | Online | [8 empty] | STA_320 Lexington
NSTAR | Lexington | ESMAEX-01355 | 02421 | 15.2 | Solar & Battery | 320-H2 | 2022-07-08 | 2022-09-14 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-26 | [7 empty] | 0 |  | 0 |  |  | 2023-03-07 | Online | [8 empty] | STA_320 Lexington
NSTAR | Arlington | ESMAEX-02499 | 02476 | 133.3 | Solar | 211-H3 | 2023-05-21 | 2023-08-24 | 69 |  | 69 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-01 | [7 empty] | 0 |  | 0 |  |  | 2025-12-05 | Compliance Documents | [8 empty] | STA_211 Woburn
NSTAR | Sharon | ESMAEX-01322 | 02067 | 15.2 | Solar & Battery | 470-H3 | 2022-06-24 | 2022-07-21 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [8 empty] | STA_470 Canton
NSTAR | Medway | ESMAEX-01321 | 02053 | 19.032 | Solar | 65-H2 | 2022-06-24 | 2022-07-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-25 | [7 empty] | 0 |  | 0 |  |  | 2023-05-02 | Online | [8 empty] | STA_065 Medway
NSTAR | Brighton | ESMAEX-01433 | 02135 | 100 | Solar | 315-H1 | 2022-08-04 | 2022-08-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [8 empty] | STA_315 Electric Avenue
NSTAR | Edgartown | ESMAEX-01415 | 02539 | 16.1 | Solar | 4-75-75 | 2022-07-28 | 2022-08-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2022-11-15 | Online | [8 empty] | STA_933 Falmouth
NSTAR | Newton | ESMAEX-01347 | 02458 | 50 | Solar | 467-H14 | 2022-07-06 | 2022-09-14 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-20 | [7 empty] | 0 |  | 0 |  |  | 2023-10-02 | Online | [8 empty] | STA_467 Watertown
NSTAR | Carver | ESMAEX-01327 | 02330 | 100 | Solar | 3-81-81 | 2022-06-27 | 2022-07-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Online |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | West Tisbury | ESMAEX-01340 | 02575 | 23.6 | Solar & Battery | 4-97-97 | 2022-07-01 | 2022-07-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-12-16 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Edgartown | ESMAEX-01348 | 02539 | 466.66 | Solar & Battery |  | 2022-07-06 | 2022-07-08 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2020-08-31 | Online | [7 empty] | 466.66
NSTAR | Weston | ESMAEX-01339 | 02493 | 17.6 | Solar | 282-H10 | 2022-06-30 | 2022-07-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [8 empty] | STA_282 Waltham
NSTAR | Acusnet | ESMAEX-01336 | 02743 | 9.3 | Solar & Battery | 2-241-241 | 2022-06-30 | 2022-07-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-07-20 | [7 empty] | 0 |  | 0 |  |  | 2023-05-05 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_624 Wing Lane
NSTAR | Ashland | ESMAEX-01359 | 01721 | 240 | Solar | 274-1429H1 | 2022-07-11 | 2022-07-26 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-06 | [7 empty] | 0 |  | 0 |  |  | 2023-06-21 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Dover | ESMAEX-01373 | 02030 | 150 | Solar | 456-H5 | 2022-07-13 | 2022-08-15 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2024-07-02 | Online | [8 empty] | STA_456 Dover
NSTAR | Lexington | ESMAEX-01365 | 02421 | 7 | Solar & Battery | 320-H5XY | 2022-07-12 | 2022-07-26 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Online | [8 empty] | STA_320 Lexington
NSTAR | Framingham | ESMAEX-01342 | 01701 | 6 | Solar | 278-H1 | 2022-07-01 | 2022-07-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2022-11-02 | Online | [7 empty] | 6 | STA_278 Saxonville
NSTAR | Charlestown | ESMAEX-01343 | 02129 | 4999 | Battery | 250-H3 | 2022-09-23 | 2022-10-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [6 empty] | 2023 ASO Batch 1 |  | STA_250 Mystic
NSTAR | Burlington | ESMAEX-01364 | 01803 | 15.2 | Solar & Battery | 391-H16 | 2022-07-12 | 2022-08-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-27 | Online | [8 empty] | STA_391 Burlington
NSTAR | Woburn | ESMAEX-01344 | 01801 | 7.38 | Solar & Battery | 211-H8 | 2022-07-05 | 2022-07-21 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online | [8 empty] | STA_211 Woburn
NSTAR | New Bedford | ESMAEX-01374 | 02745 | 17.57 | Solar | 2-102-608 | 2022-07-13 | 2022-08-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2023-07-26 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Oak Bluffs | ESMAEX-01389 | 02557 | 26.385 | Solar | 4-99-224 | 2022-07-20 | 2022-08-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-22 | [7 empty] | 0 |  | 0 |  |  | 2023-08-07 | Online | [8 empty] | STA_933 Falmouth
NSTAR | Natick | ESMAEX-01354 | 01760 | 17.6 | Solar | 433-H7 | 2022-07-08 | 2022-07-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2022-11-18 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Mashpee | ESMAEX-01363 | 02649 | 6 | Solar | 4-77A-77A | 2022-07-11 | 2022-07-26 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-24 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | North Truro | ESMAEX-01378 | 02652 | 10 | Battery | 4-96-96 | 2022-07-15 | 2022-08-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-10-14 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Milton | ESMAEX-01368 | 02186 | 17.6 | Solar | 4309 | 2022-07-12 | 2022-08-15 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Carlisle | ESMAEX-01437 | 01741 | 20.2 | Solar & Battery | 512-1399H1 | 2022-08-04 | 2022-08-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-07-10 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Harwichport | ESMAEX-01388 | 02646 | 10 | Battery | 4-85-592 | 2022-07-19 | 2022-08-01 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2022-09-26 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Westwood | ESMAEX-01503 | 02090 | 15.2 | Solar & Battery | 456-H1 | 2022-08-23 | 2022-09-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Online | [8 empty] | STA_456 Dover
NSTAR | Milton | ESMAEX-01508 | 02186 | 19 | Solar & Battery | 362-1209H2 | 2022-08-24 | 2022-09-22 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-03 | [7 empty] | 0 |  | 0 |  |  | 2023-05-03 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Framingham | ESMAEX-01377 | 01702 | 200 | Solar |  | 2022-08-04 | 2022-08-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-15 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [7 empty] | 200
NSTAR | Boston | ESMAEX-01603 | 02130 | 100 | Solar | 483-H6 | 2022-09-19 | 2022-10-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [8 empty] | STA_483 Dewar Street
NSTAR | Norfolk | ESMAEX-01417 | 02056 | 20.2 | Solar & Battery | 146-H10 | 2022-07-29 | 2022-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-06 | Online | [8 empty] | STA_146 Walpole
NSTAR | Boston | ESMAEX-01900 | 02125 | 34.6 | Solar | 106-1N31H1 | 2022-12-07 | 2023-01-04 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2024-04-22 | Online | [8 empty] | STA_106 Andrew Square
NSTAR | Boston | ESMAEX-01407 | 02119 | 120 | Solar | 106-1N31H6 | 2022-07-22 | 2022-08-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2024-04-30 | Online
NSTAR | Framingham | ESMAEX-01386 | 01702 | 200 | Solar | 455-H4 | 2022-08-08 | 2022-09-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-15 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Weston | ESMAEX-01390 | 02493 | 10 | Solar & Battery | 282-H1 | 2022-07-20 | 2022-08-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2022-12-08 | Online | [7 empty] | 10 | STA_282 Waltham
NSTAR | Bedford | ESMAEX-01393 | 01730 | 15.2 | Solar & Battery | 533-H8 | 2022-07-20 | 2022-09-29 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-06-27 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Wayland | ESMAEX-01659 | 01778 | 7.6 | Solar & Battery | 342-H1 | 2022-10-05 | 2022-11-10 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Online | [8 empty] | STA_342 Sudbury
NSTAR | North Dartmouth | ESMAEX-01395 | 02747 | 19 | Solar | 2-528-528 | 2022-07-21 | 2022-08-23 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-29 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online
NSTAR | Plymouth | ESMAEX-01399 | 02360 | 48 | Solar | 3-89-922 | 2022-07-21 | 2022-08-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-10 | [7 empty] | 0 |  | 0 |  |  | 2023-05-30 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Framingham | ESMAEX-01409 | 01702 | 200 | Solar | 455-H4 | 2022-08-15 | 2022-09-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Plymouth | ESMAEX-01411 | 02360 | 67.3 | Solar | 3-12-932 | 2022-07-25 | 2022-08-10 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-08-08 | Online |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Provincetown | ESMAEX-01414 | 02657 | 12.005 | Solar & Battery | 4-675-675 | 2022-07-27 | 2022-08-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-02-17 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Hatchville | ESMAEX-01412 | 02536 | 17.6 | Solar | 4-78-78 | 2022-07-27 | 2022-08-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-15 | [7 empty] | 0 |  | 0 |  |  | 2022-11-04 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Medfield | ESMAEX-01442 | 02052 | 19.8 | Solar | 456-H3 | 2022-08-08 | 2022-09-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-14 | [7 empty] | 0 |  | 0 |  |  | 2023-01-09 | Online | [8 empty] | STA_456 Dover
NSTAR | Watertown | ESMAEX-01443 | 02472 | 16.83 | Solar & Battery | 467-H4 | 2022-08-08 | 2022-09-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-21 | [7 empty] | 0 |  | 0 |  |  | 2023-02-21 | Online | [8 empty] | STA_467 Watertown
NSTAR | Dorchester | ESMAEX-01505 | 02125 | 72 | Solar | 483-H1 | 2022-08-24 | 2022-09-09 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-02 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Falmouth | ESMAEX-01418 | 02540 | 178.2 | Solar | 4-72-72 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-09 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Hopkinton | ESMAEX-01424 | 01748 | 15.2 | Solar & Battery | 126-H1 | 2022-08-02 | 2022-08-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Framingham | ESMAEX-01419 | 01702 | 200 | Solar | 455-H4 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  | 2023-10-30 | Online | [7 empty] | 200 | STA_455 West Framingham
NSTAR | Dover | ESMAEX-01420 | 02030 | 17.6 | Solar | 456-H5 | 2022-08-01 | 2022-08-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-23 | [7 empty] | 0 |  | 0 |  |  | 2022-12-08 | Online | [8 empty] | STA_456 Dover
NSTAR | Chilmark | ESMAEX-01423 | 02535 | 17.6 | Solar & Battery | 4-97-97 | 2022-08-02 | 2022-08-15 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Falmouth | ESMAEX-01422 | 02540 | 17.4 | Solar | 4-72-72 | 2022-08-02 | 2022-08-15 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-08-18 | [7 empty] | 0 |  | 0 |  |  | 2022-11-30 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Stoneham | ESMAEX-01425 | 02180 | 18.6 | Solar | 375-H8 | 2022-08-03 | 2022-08-17 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-01-24 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Framingham | ESMAEX-01432 | 01701 | 15.2 | Solar | 455-H1 | 2022-08-03 | 2022-09-27 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Kingston | ESMAEX-01431 | 02364 | 240 | Solar | 3-26-26 | 2022-08-03 | 2022-08-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-22 | [7 empty] | 0 |  | 0 |  |  | 2025-05-07 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Dedham | ESMAEX-01429 | 02026 | 270 | Solar | 13-H1 | 2022-08-03 | 2022-08-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-27 | [7 empty] | 0 |  | 0 |  |  | 2025-08-27 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Dedham | ESMAEX-01430 | 02026 | 150 | Solar | 20-H1 | 2022-08-03 | 2022-08-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-27 | [7 empty] | 0 |  | 0 |  |  | 2025-10-03 | Online | [8 empty] | STA_110 Baker Street
NSTAR | Westwood | ESMAEX-01541 | 02090 | 15.2 | Solar & Battery | 469-H2 | 2022-09-02 | 2022-10-11 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-03 | [7 empty] | 0 |  | 0 |  |  | 2023-01-20 | Online
NSTAR | Waban | ESMAEX-01446 | 02468 | 12.078 | Solar & Battery | 277-04 | 2022-08-08 | 2022-09-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-08-03 | Online | [8 empty] | STA_467 Watertown
NSTAR | Hopkinton | ESMAEX-01458 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-08-10 | 2022-09-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-20 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Plymouth | ESMAEX-01436 | 02360 | 15.2 | Solar | 3-90-10J2 | 2022-08-04 | 2022-08-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  | 2025-02-24 | Online |  |  |  | Plymouth |  |  |  | 15.2 | STA_715 Valley
NSTAR | Wayland | ESMAEX-01496 | 01778 | 22.8 | Solar & Battery | 342-H3 | 2022-08-22 | 2022-09-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-14 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Waltham | ESMAEX-01440 | 02452 | 15.2 | Solar | 282-H7 | 2022-08-05 | 2022-08-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Online | [7 empty] | 15.2 | STA_282 Waltham
NSTAR | Framingham | ESMAEX-01441 | 01702 | 250 | Solar | 455-H4 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [7 empty] | 250 | STA_455 West Framingham
NSTAR | Lexington | ESMAEX-01453 | 02420 | 6 | Solar | 391-H11 | 2022-08-09 | 2022-08-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [7 empty] | 6 | STA_391 Burlington
NSTAR | Needham | ESMAEX-01463 | 02492 | 20 | Solar | 148-H7 | 2022-08-11 | 2022-09-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-06 | Online | [8 empty] | STA_148 Needham
NSTAR | East Boston | ESMAEX-01610 | 02128 | 69.2 | Solar | 488-H8 | 2022-09-20 | 2022-10-13 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-19 | [7 empty] | 0 |  | 0 |  |  | 2024-04-30 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Medfield | ESMAEX-01452 | 02052 | 8.7 | Solar & Battery | 456-H2 | 2022-08-09 | 2022-08-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-25 | [7 empty] | 0 |  | 0 |  |  | 2023-03-08 | Online | [8 empty] | STA_456 Dover
NSTAR | Woburn | ESMAEX-01459 | 01801 | 6 | Solar | 375-H6 | 2022-08-10 | 2022-09-01 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-02-07 | Online | [7 empty] | 6 | STA_375 Dragon Court
NSTAR | Hopkinton | ESMAEX-01464 | 01748 | 250 | Solar | 126-H1 | 2022-09-09 | 2022-09-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-28 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-01467 | 01720 | 250 | Solar | 416-H9 | 2022-09-09 | 2022-09-27 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2024-03-01 | Online | [8 empty] | STA_416 Maynard
NSTAR | Framingham | ESMAEX-01470 | 01702 | 250 | Solar | 455-H4 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-26 | [7 empty] | 0 |  | 0 |  |  | 2023-11-08 | Online | [7 empty] | 250 | STA_455 West Framingham
NSTAR | Wayland | ESMAEX-01471 | 01778 | 16 | Solar | 278-H2 | 2022-08-15 | 2022-09-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-13 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online | [7 empty] | 16 | STA_278 Saxonville
NSTAR | Sharon | ESMAEX-01472 | 02067 | 19 | Solar | 470-H3 | 2022-08-15 | 2022-09-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-06-09 | Online | [8 empty] | STA_470 Canton
NSTAR | Hopkinton | ESMAEX-01487 | 01748 | 220 | Solar | 126-H1 | 2022-08-19 | 2022-09-01 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-18 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Weston | ESMAEX-01490 | 02493 | 15.3 | Solar & Battery | 282-H1 | 2022-08-19 | 2022-09-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-28 | [7 empty] | 0 |  | 0 |  |  | 2022-12-13 | Online | [8 empty] | STA_282 Waltham
NSTAR | Orleans | ESMAEX-01657 | 02653 | 29.76 | Solar & Battery | 4-628-628 | 2022-10-03 | 2022-10-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-06-06 | Online | [7 empty] | 15.36 | STA_975 Orleans
NSTAR | Woburn | ESMAEX-01491 | 01801 | 217.3 | Solar | 375-H3 | 2022-08-19 | 2022-09-27 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-30 | [7 empty] | 0 |  | 0 |  |  | 2025-03-18 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Eastham | ESMAEX-01481 | 02642 | 7.68 | Battery | 4-94A-94A | 2022-08-18 | 2022-08-18 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Online | [8 empty] | STA_975 Orleans
NSTAR | North Truro | ESMAEX-01485 | 02652 | 21.6 | Solar | 4-96-96 | 2022-08-18 | 2022-09-27 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-01-10 | Compliance Documents | [8 empty] | STA_976 Wellfleet
NSTAR | Woburn | ESMAEX-01493 | 01801 | 237.5 | Solar | 375-H3 | 2022-08-19 | 2022-09-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-30 | [7 empty] | 0 |  | 0 |  |  | 2024-09-30 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Wayland | ESMAEX-01531 | 01778 | 19.398 | Solar | 342-H1 | 2022-09-01 | 2022-10-25 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-31 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Watertown | ESMAEX-01498 | 02472 | 492 | Solar | 370-1327 | 2022-09-29 | 2022-10-25 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-05 | Online | [8 empty] | STA_467 Watertown
NSTAR | Watertown | ESMAEX-01499 | 02472 | 492 | Solar | 305-1422H2 | 2022-09-29 | 2022-10-27 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-12-21 | Online
NSTAR | Plympton | ESMAEX-01542 | 02367 | 15.2 | Solar & Battery | 3-50-50 | 2022-09-06 | 2022-09-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-04-13 | Online |  |  |  | Plymouth |  |  |  |  | STA_727 Brook Street
NSTAR | Waltham | ESMAEX-01516 | 02453 | 73.3 | Solar | 33-H2 | 2022-08-26 | 2022-09-22 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-01 | [7 empty] | 0 |  | 0 |  |  |  | Permission to Operate | [8 empty] | STA_282 Waltham
NSTAR | Newton Upper Falls | ESMAEX-01543 | 02464 | 15.2 | Solar & Battery | 292-H7 | 2022-09-06 | 2022-09-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-04 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Framingham | ESMAEX-01509 | 01701 | 17.1 | Solar | 455-H1 | 2022-08-25 | 2022-09-22 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-14 | [7 empty] | 0 |  | 0 |  |  | 2023-03-13 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Green Harbor | ESMAEX-01684 | 02041 | 20.2 | Solar & Battery | 3-27-27 | 2022-10-17 | 2022-11-23 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-15 | [7 empty] | 0 |  | 0 |  |  | 2024-01-10 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Sudbury | ESMAEX-01513 | 01776 | 17.6 | Solar | 342-H6 | 2022-08-25 | 2022-09-22 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-05-09 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Hopkinton | ESMAEX-01537 | 01748 | 250 | Solar | 65-H7 | 2022-09-02 | 2022-09-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-22 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Online | [8 empty] | STA_065 Medway
NSTAR | Wayland | ESMAEX-01521 | 01778 | 20.2 | Solar & Battery | 342-H3 | 2022-08-29 | 2022-09-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Needham | ESMAEX-01525 | 02492 | 15.2 | Solar | 148-H4 | 2022-08-30 | 2022-09-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-07 | [7 empty] | 0 |  | 0 |  |  | 2023-05-02 | Online | [8 empty] | STA_148 Needham
NSTAR | Burlington | ESMAEX-01528 | 01803 | 32.85 | Solar | 391-H2 | 2022-08-30 | 2022-09-22 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-09-28 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [8 empty] | STA_391 Burlington
NSTAR | Marshfield | ESMAEX-01540 | 02050 | 3.8 | Solar | 3-25-42J2 | 2022-09-02 | 2022-09-29 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-05 | [7 empty] | 0 |  | 0 |  |  | 2023-03-30 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Hopkinton | ESMAEX-01619 | 01748 | 16.2 | Solar | 126-H1 | 2022-09-22 | 2022-10-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-19 | [7 empty] | 0 |  | 0 |  |  | 2023-02-01 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Hopkinton | ESMAEX-01538 | 01748 | 250 | Solar | 126-H2 | 2022-09-02 | 2022-09-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-15 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-01534 | 01720 | 100 | Solar | 416-H4 | 2022-11-21 | 2023-01-30 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-06 | [7 empty] | 0 |  | 0 |  |  | 2024-02-15 | Online | [8 empty] | STA_416 Maynard
NSTAR | Waban | ESMAEX-01585 | 02468 | 15.2 | Solar & Battery | 292-H7 | 2022-09-14 | 2022-10-11 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-08-08 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Milton | ESMAEX-01545 | 02186 | 13.44 | Solar | 362-1209H2 | 2022-09-06 | 2022-10-07 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-14 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Natick | ESMAEX-01553 | 01760 | 19.8 | Solar | 240-H5 | 2022-09-08 | 2022-09-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-12 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Online | [8 empty] | STA_240 Framingham
NSTAR | Newton Highlands | ESMAEX-01549 | 02461 | 6.3 | Solar & Battery | 292-H12 | 2022-09-07 | 2022-11-30 | 60 |  | 60 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-28 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Woburn | ESMAEX-01562 | 01801 | 210 | Solar | 375-H9 | 2022-09-09 | 2022-09-27 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-15 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Winchester | ESMAEX-01673 | 01890 | 17.6 | Solar & Battery | 211-H1 | 2022-10-11 | 2022-11-10 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Online | [8 empty] | STA_211 Woburn
NSTAR | Bedford | ESMAEX-01548 | 01730 | 15.744 | Solar & Battery | 533-H7 | 2022-09-07 | 2022-10-27 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-11-02 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Westwood | ESMAEX-01560 | 02090 | 15.2 | Solar | 456-H4 | 2022-09-09 | 2022-09-27 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-31 | [7 empty] | 0 |  | 0 |  |  | 2023-07-26 | Online | [8 empty] | STA_456 Dover
NSTAR | Duxbury | ESMAEX-01633 | 02332 | 15.738 | Solar | 3-26-26 | 2022-09-27 | 2022-11-30 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-13 | [7 empty] | 0 |  | 0 |  |  | 2023-02-28 | Online
NSTAR | Plymouth | ESMAEX-01601 | 02360 | 22.8 | Solar & Battery | 3-71-38J1 | 2022-09-19 | 2022-10-27 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-03 | [7 empty] | 0 |  | 0 |  |  | 2023-09-08 | Online |  |  |  | Plymouth |  |  |  |  | STA_721 Manomet
NSTAR | Weston | ESMAEX-01636 | 02493 | 20.352 | Solar | 282-H10 | 2022-09-27 | 2022-10-27 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-08-31 | Online | [8 empty] | STA_282 Waltham
NSTAR | Lexington | ESMAEX-01804 | 02421 | 10 | Battery | 320-H2 | 2022-11-14 | 2022-12-08 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Online | [8 empty] | STA_320 Lexington
NSTAR | Hopkinton | ESMAEX-01692 | 01748 | 15.2 | Solar & Battery | 455-H8 | 2022-10-18 | 2022-11-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2023-05-15 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Norfolk | ESMAEX-01589 | 02056 | 15.2 | Solar & Battery | 146-H3 | 2022-09-14 | 2022-09-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Online | [8 empty] | STA_146 Walpole
NSTAR | Cambridge | ESMAEX-01911 | 02138 | 30 | Solar | 831-1111 | 2022-12-09 | 2023-01-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-10 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online | [8 empty] | STA_831 Putnam
NSTAR | Truro | ESMAEX-01579 | 02666 | 17.6 | Solar & Battery | 4-96-96 | 2022-09-13 | 2022-10-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-19 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Cambridge | ESMAEX-01703 | 02138 | 30 | Solar | 819-1NB2 | 2022-10-21 | 2022-11-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-05 | [7 empty] | 0 |  | 0 |  |  | 2024-06-20 | Online | [8 empty] | STA_402 Newton Street
NSTAR | Boston | ESMAEX-01604 | 02130 | 86.4 | Solar | 483-H6 | 2022-09-19 | 2022-10-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-24 | [7 empty] | 0 |  | 0 |  |  | 2026-01-14 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Weston | ESMAEX-01599 | 02493 | 25 | Solar & Battery | 282-H8 | 2022-09-16 | 2022-10-25 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-18 | Online | [8 empty] | STA_282 Waltham
NSTAR | Wellfleet | ESMAEX-01591 | 02667 | 18.816 | Solar | 4-94B-94B | 2022-09-15 | 2022-10-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-10 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Orleans | ESMAEX-01596 | 02653 | 15.2 | Solar & Battery | 4-628-628 | 2022-09-16 | 2022-10-11 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-20 | [7 empty] | 0 |  | 0 |  |  | 2023-06-09 | Online | [8 empty] | STA_975 Orleans
NSTAR | West Wareham | ESMAEX-01592 | 02576 | 19 | Solar | 3-85-85 | 2022-09-15 | 2022-10-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-11 | [7 empty] | 0 |  | 0 |  |  | 2023-03-27 | Online |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | Hopkinton | ESMAEX-01627 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-09-26 | 2022-10-27 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-01 | [7 empty] | 0 |  | 0 |  |  | 2023-02-15 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Lincoln | ESMAEX-01664 | 01773 | 19.845 | Solar | 320-H8 | 2022-10-06 | 2022-10-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-23 | [7 empty] | 0 |  | 0 |  |  | 2023-03-10 | Online | [8 empty] | STA_320 Lexington
NSTAR | Newton Lower Falls | ESMAEX-01607 | 02462 | 34 | Solar & Battery | 292-H2 | 2022-09-20 | 2022-10-13 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-01623 | 02421 | 15.2 | Solar & Battery | 320-H2 | 2022-09-23 | 2022-11-04 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Online | [8 empty] | STA_320 Lexington
NSTAR | Acton | ESMAEX-01611 | 01720 | 15.3 | Solar | 416-H5 | 2022-09-21 | 2022-12-29 | 71 |  | 71 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Online | [8 empty] | STA_416 Maynard
NSTAR | Cummaquid | ESMAEX-01616 | 02637 | 9 | Solar | 4-92A-92A | 2022-09-21 | 2022-10-25 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-06-05 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Natick | ESMAEX-01617 | 01760 | 250 | Solar | 433-H5 | 2022-10-14 | 2022-11-23 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-19 | [7 empty] | 0 |  | 0 |  |  | 2025-05-02 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Burlington | ESMAEX-01624 | 01803 | 18.9 | Solar | 391-H6 | 2022-09-23 | 2022-10-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [8 empty] | STA_391 Burlington
NSTAR | Framingham | ESMAEX-01634 | 01701 | 17.92 | Solar | 433-H3 | 2022-09-27 | 2022-10-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Walpole | ESMAEX-01628 | 02081 | 10 | Solar | 2607 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-04 | [7 empty] | 0 |  | 0 |  |  | 2023-03-13 | Online | [8 empty] | STA_146 Walpole
NSTAR | Needham | ESMAEX-01629 | 02494 | 17.6 | Solar | 292-H4 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-06-05 | Online | [7 empty] | 17.6 | STA_292 Newton Highlands
NSTAR | Wayland | ESMAEX-01825 | 01778 | 19.5 | Solar | 342-H1 | 2022-11-17 | 2023-01-04 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Dover | ESMAEX-01630 | 02030 | 9 | Solar | 456-H5 | 2022-09-26 | 2022-10-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-04-21 | Online | [8 empty] | STA_456 Dover
NSTAR | Plymouth | ESMAEX-01644 | 02360 | 25 | Solar | 3-10-10 | 2022-09-29 | 2022-10-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Online
NSTAR | Burlington | ESMAEX-01653 | 01803 | 15.2 | Solar & Battery | 346-1395H1 | 2022-10-03 | 2022-10-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-23 | [7 empty] | 0 |  | 0 |  |  | 2023-05-31 | Online | [8 empty] | STA_391 Burlington
NSTAR | Sherborn | ESMAEX-01663 | 01770 | 15.2 | Solar & Battery | 274-H2 | 2022-10-06 | 2022-10-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-28 | [7 empty] | 0 |  | 0 |  |  | 2023-04-10 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Hopkinton | ESMAEX-01646 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-09-29 | 2022-10-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-16 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-01648 | 01720 | 15.2 | Solar & Battery | 416-H5 | 2022-09-30 | 2022-10-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-21 | [7 empty] | 0 |  | 0 |  |  | 2023-04-03 | Online | [8 empty] | STA_416 Maynard
NSTAR | Onset | ESMAEX-01649 | 02558 | 10 | Battery | 3-88-17J1 | 2022-10-03 | 2022-12-07 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-08-07 | Online
NSTAR | Natick | ESMAEX-01796 | 01760 | 16.2 | Solar | 2304 | 2022-11-10 | 2022-12-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  | 2023-05-05 | Online | [8 empty] | STA_240 Framingham
NSTAR | Framingham | ESMAEX-01655 | 01702 | 15.2 | Solar | 24-H1 | 2022-10-03 | 2022-10-14 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-30 | Online | [7 empty] | 15.2 | STA_240 Framingham
NSTAR | Acton | ESMAEX-01714 | 01720 | 15.2 | Solar & Battery | 416-H5 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-04-26 | Online | [8 empty] | STA_416 Maynard
NSTAR | Sharon | ESMAEX-01661 | 02067 | 15.2 | Solar & Battery | 146-H1 | 2022-10-05 | 2022-11-29 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-13 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Online | [8 empty] | STA_146 Walpole
NSTAR | Fairhaven | ESMAEX-01787 | 02719 | 100 | Solar | 2-221-221 | 2022-11-09 | 2022-11-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-05 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_654 Arsene
NSTAR | Plymouth | ESMAEX-01665 | 02360 | 16 | Solar | 3-12-12 | 2022-10-06 | 2022-11-30 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-15 | [7 empty] | 0 |  | 0 |  |  | 2023-09-13 | Online
NSTAR | Bedford | ESMAEX-01779 | 01730 | 15.2 | Solar & Battery | 533-H7 | 2022-11-08 | 2022-12-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Edgartown | ESMAEX-01669 | 02539 | 37.6 | Solar | 4-75-75 | 2022-10-07 | 2022-10-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-13 | [7 empty] | 0 |  | 0 |  |  | 2025-12-17 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Westwood | ESMAEX-01668 | 02090 | 15.2 | Solar | 456-H1 | 2022-10-07 | 2022-10-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-10-31 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Online | [8 empty] | STA_456 Dover
NSTAR | Plympton | ESMAEX-01670 | 02367 | 17.6 | Solar | 3-50-50 | 2022-10-10 | 2022-11-22 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Online |  |  |  | Plymouth |  |  |  | 17.6 | STA_727 Brook Street
NSTAR | Maynard | ESMAEX-01675 | 02067 | 250 | Solar | 416-H6 | 2022-10-11 | 2022-11-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_416 Maynard
NSTAR | Natick | ESMAEX-01854 | 01760 | 19.8 | Solar | 240-H1 | 2022-11-28 | 2022-12-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-06-23 | Online | [8 empty] | STA_240 Framingham
NSTAR | Plymouth | ESMAEX-01680 | 02360 | 25 | Solar | 3-10-10 | 2022-10-12 | 2022-10-27 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-09-12 | Online
NSTAR | Needham | ESMAEX-01681 | 02492 | 15.2 | Solar & Battery | 148-01 | 2022-10-13 | 2022-12-07 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-12-20 | Online | [8 empty] | STA_148 Needham
NSTAR | Kingston | ESMAEX-01725 | 02364 | 7.6 | Solar & Battery | 3-18-18 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-31 | Online |  |  |  | Plymouth |  |  |  |  | STA_727 Brook Street
NSTAR | Wayland | ESMAEX-01892 | 01778 | 17.6 | Solar | 342-H1 | 2022-12-06 | 2022-12-29 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Ashland | ESMAEX-01685 | 01721 | 19.92 | Solar & Battery | 455-H3 | 2022-10-17 | 2022-11-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-08 | [7 empty] | 0 |  | 0 |  |  | 2023-07-05 | Online | [7 empty] | 19.92 | STA_455 West Framingham
NSTAR | Sharon | ESMAEX-01690 | 02067 | 16.47 | Solar | 470-H12 | 2022-10-17 | 2022-11-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-24 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online | [8 empty] | STA_470 Canton
NSTAR | Woburn | ESMAEX-01720 | 01801 | 15.2 | Solar & Battery | 375-H14 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | East Freetown | ESMAEX-01691 | 02717 | 2000 | Solar & Battery | 2-108-108 | 2022-11-17 | 2022-12-19 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Technical Review |  |  |  | New Bedford | Hold In Queue |  | 2024 SEMA/Cape ASO Study | 1500 | STA_636 Industrial Park
NSTAR | Lexington | ESMAEX-01807 | 02420 | 20.2 | Solar & Battery | 391-H11 | 2022-11-14 | 2022-12-08 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online | [8 empty] | STA_391 Burlington
NSTAR | Acton | ESMAEX-01716 | 01720 | 15.2 | Solar & Battery | 512-1399H1 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-08 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | North Eastham | ESMAEX-01694 | 02651 | 16 | Solar | 4-94B-646 | 2022-10-19 | 2022-11-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-07 | [7 empty] | 0 |  | 0 |  |  | 2023-03-23 | Online | [7 empty] | 15.36 | STA_976 Wellfleet
NSTAR | Boston | ESMAEX-01699 | 02132 | 483 | Solar |  | 2022-10-19 | 2022-11-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-28 | [7 empty] | 0 |  | 0 |  |  | 2024-04-23 | Online
NSTAR | Lexington | ESMAEX-01697 | 02421 | 22.8 | Solar & Battery | 320-H2 | 2022-10-19 | 2022-11-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-12 | [7 empty] | 0 |  | 0 |  |  | 2023-10-31 | Online | [8 empty] | STA_320 Lexington
NSTAR | Sudbury | ESMAEX-01711 | 01776 | 17.6 | Solar & Battery | 342-H7 | 2022-10-24 | 2022-11-16 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-05-08 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Carlisle | ESMAEX-01706 | 01741 | 10 | Battery | 512-1399H1 | 2022-10-21 | 2022-11-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-20 | [7 empty] | 0 |  | 0 |  |  | 2024-05-15 | Online | [7 empty] | 0 | STA_533 Hartwell Avenue
NSTAR | Plympton | ESMAEX-01740 | 02367 | 15.2 | Solar & Battery | 3-50-43J1 | 2022-10-31 | 2022-11-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Online
NSTAR | East Freetown | ESMAEX-01966 | 02717 | 10 | Battery | 2-108-108 | 2023-01-05 | 2023-01-23 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-28 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Lexington | ESMAEX-01717 | 02420 | 57 | Solar | 3406 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-09 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Online
NSTAR | Hopkinton | ESMAEX-01718 | 01748 | 15.2 | Solar | 126-H4 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-02-28 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Natick | ESMAEX-01929 | 01760 | 10 | Battery | 433-H10 | 2022-12-16 | 2023-01-10 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-12-18 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Hyannis | ESMAEX-01723 | 02601 | 166.6 | Solar | 4-64-64 | 2022-10-25 | 2022-12-16 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-19 | [7 empty] | 0 |  | 0 |  |  | 2025-09-09 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Walpole | ESMAEX-01722 | 02081 | 22.2 | Solar | 2606 | 2022-10-25 | 2022-11-16 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-27 | [7 empty] | 0 |  | 0 |  |  | 2023-06-16 | Online | [8 empty] | STA_146 Walpole
NSTAR | Duxbury | ESMAEX-01726 | 02332 | 9.9 | Solar & Battery | 3-26-26 | 2022-10-26 | 2022-11-16 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Online
NSTAR | Centerville | ESMAEX-01727 | 02632 | 20 | Solar | 4-82-82 | 2022-10-26 | 2022-11-16 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online |  |  |  | Cape |  |  |  |  | STA_920 Oak Street
NSTAR | Wellfleet | ESMAEX-01729 | 02667 | 18.9 | Solar | 4-96-96 | 2022-10-26 | 2022-11-16 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-06-08 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Dover | ESMAEX-01734 | 02030 | 20 | Solar | 456-H5 | 2022-10-27 | 2022-11-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-18 | Online | [7 empty] | 20 | STA_456 Dover
NSTAR | Stoneham | ESMAEX-01739 | 02180 | 7.6 | Solar & Battery | 211-H12 | 2022-10-31 | 2022-11-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Online | [8 empty] | STA_211 Woburn
NSTAR | Dedham | ESMAEX-01768 | 02026 | 15.2 | Solar & Battery | 456-H4 | 2022-11-04 | 2022-11-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-22 | [7 empty] | 0 |  | 0 |  |  | 2023-08-03 | Online | [8 empty] | STA_456 Dover
NSTAR | Hopkinton | ESMAEX-01757 | 01748 | 12.9 | Solar | 126-H2 | 2022-11-03 | 2022-12-05 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-09-19 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Burlington | ESMAEX-01736 | 01803 | 21.12 | Solar | 391-H6 | 2022-10-28 | 2023-03-22 | 103 |  | 103 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Online | [8 empty] | STA_391 Burlington
NSTAR | New Bedford | ESMAEX-01737 | 02745 | 10 | Solar | 2-105-105 | 2022-10-28 | 2022-12-13 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Needham | ESMAEX-01738 | 02494 | 20 | Solar & Battery | 148-H1 | 2022-10-28 | 2022-11-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Online | [7 empty] | 10 | STA_148 Needham
NSTAR | Dartmouth | ESMAEX-01745 | 02748 | 166 | Solar | 2-60-63 | 2022-11-01 | 2022-12-07 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_611 Pine Street
NSTAR | Dartmouth | ESMAEX-01746 | 02748 | 166 | Solar | 2-60-63 | 2022-11-01 | 2022-12-07 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_611 Pine Street
NSTAR | Dartmouth | ESMAEX-01747 | 02748 | 166 | Solar | 2-60-63 | 2022-11-01 | 2022-12-07 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_611 Pine Street
NSTAR | Sherborn | ESMAEX-01775 | 01770 | 9.7 | Solar | 130-H2 | 2022-11-08 | 2022-11-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-29 | [7 empty] | 0 |  | 0 |  |  | 2023-06-01 | Online | [8 empty] | STA_130 Holliston
NSTAR | North Dartmouth | ESMAEX-01771 | 02747 | 15.2 | Solar & Battery | 2-541-541 | 2022-11-04 | 2022-11-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-07 | [7 empty] | 0 |  | 0 |  |  | 2023-05-04 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Walpole | ESMAEX-01784 | 02081 | 15.2 | Solar | 146-H4 | 2022-11-08 | 2022-12-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-25 | Online | [8 empty] | STA_146 Walpole
NSTAR | Carver | ESMAEX-01753 | 02330 | 17.7 | Solar | 3-10-10 | 2022-11-02 | 2022-11-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2023-10-27 | Online
NSTAR | Westwood | ESMAEX-01974 | 02090 | 120 | Solar | 469-H4 | 2023-01-05 | 2023-02-23 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-28 | [7 empty] | 0 |  | 0 |  |  | 2024-10-23 | Online
NSTAR | Sudbury | ESMAEX-01756 | 01776 | 16 | Solar | 342-H8 | 2022-11-02 | 2022-11-16 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-02-17 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Weston | ESMAEX-01822 | 02493 | 15.2 | Solar & Battery | 342-H1 | 2022-11-16 | 2022-12-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2024-04-17 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Mashpee | ESMAEX-01765 | 02649 | 15.2 | Solar & Battery | 4-77B-454 | 2022-11-03 | 2022-11-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-25 | [7 empty] | 0 |  | 0 |  |  | 2023-05-04 | Online
NSTAR | West Somerville | ESMAEX-01788 | 02144 | 27.57 | Solar & Battery | 1603 | 2022-11-09 | 2022-12-05 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-31 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online | [7 empty] | 13.57 | STA_828 Alewife
NSTAR | Hyannis | ESMAEX-01970 | 02601 | 100 | Solar | 4-84B-524 | 2023-01-05 | 2023-01-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-11 | [7 empty] | 0 |  | 0 |  |  | 2025-03-31 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Hopkinton | ESMAEX-01843 | 01748 | 18 | Solar | 126-H3 | 2022-11-23 | 2023-02-03 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Orleans | ESMAEX-01973 | 02653 | 80 | Solar | 4-89B-89B | 2023-01-05 | 2023-02-01 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2024-07-11 | Online | [8 empty] | STA_975 Orleans
NSTAR | Canton | ESMAEX-01770 | 02021 | 35.2 | Solar & Battery | 470-H7 | 2022-11-04 | 2022-11-18 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-04-06 | Online | [8 empty] | STA_470 Canton
NSTAR | Carlisle | ESMAEX-01773 | 01741 | 15.2 | Solar | 533-H8 | 2022-11-07 | 2022-12-05 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-27 | [7 empty] | 0 |  | 0 |  |  | 2023-05-25 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Wareham | ESMAEX-01774 | 02571 | 66.6 | Solar | 3-86-966 | 2022-11-07 | 2022-11-16 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Online |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | Kingston | ESMAEX-01798 | 02364 | 180 | Solar | 3-17-17 | 2022-11-10 | 2022-12-07 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-08-16 | Online
NSTAR | South Dartmouth | ESMAEX-01780 | 02748 | 17.6 | Solar | 2-53-65 | 2022-11-08 | 2022-11-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-17 | [7 empty] | 0 |  | 0 |  |  | 2023-02-13 | Online | [7 empty] | 17.6 | STA_611 Pine Street
NSTAR | Norfolk | ESMAEX-01782 | 02056 | 12.6 | Solar & Battery | 65-H1 | 2022-11-08 | 2022-12-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Online | [8 empty] | STA_065 Medway
NSTAR | Milton | ESMAEX-01781 | 02186 | 15.2 | Solar | 362-1209H2 | 2022-11-08 | 2022-11-29 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-07 | [7 empty] | 0 |  | 0 |  |  | 2023-03-14 | Online | [7 empty] | 15.2 | STA_496 Hyde Park
NSTAR | Rochester | ESMAEX-01778 | 02770 | 15.2 | Solar | 3-702-702 | 2022-11-08 | 2022-11-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-11-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-16 | Online |  |  |  | Marion-Fairhaven |  |  |  | 15.2 | STA_745 Rochester
NSTAR | Hopkinton | ESMAEX-01884 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2022-12-02 | 2022-12-19 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-06-21 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Natick | ESMAEX-01785 | 01760 | 13.8 | Solar | 240-H1 | 2022-11-08 | 2022-12-08 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-01 | Online | [8 empty] | STA_240 Framingham
NSTAR | Hopkinton | ESMAEX-01910 | 01748 | 20 | Solar | 126-H2 | 2022-12-09 | 2023-01-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Lexington | ESMAEX-01795 | 02421 | 15.2 | Solar & Battery | 533-H4 | 2022-11-10 | 2022-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-27 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Freetown | ESMAEX-01812 | 02717 | 249 | Solar | 2-108-108 | 2022-11-15 | 2022-12-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-12 | [7 empty] | 0 |  | 0 |  |  | 2025-11-26 | Online | [7 empty] | 220 | STA_636 Industrial Park
NSTAR | Sherborn | ESMAEX-01944 | 01770 | 18.66 | Solar | 274-H2 | 2022-12-23 | 2023-01-10 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-07-12 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Burlington | ESMAEX-01805 | 01803 | 15.2 | Solar & Battery | 391-H7 | 2022-11-14 | 2022-12-08 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-04 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Online | [8 empty] | STA_391 Burlington
NSTAR | Hopkinton | ESMAEX-01885 | 01748 | 15.2 | Solar & Battery | 126-H2 | 2022-12-02 | 2023-01-12 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Stoneham | ESMAEX-01811 | 02180 | 10 | Solar & Battery | 375-H2 | 2022-11-15 | 2022-12-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-24 | [7 empty] | 0 |  | 0 |  |  | 2024-02-12 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Dover | ESMAEX-01827 | 02030 | 19.58 | Solar | 456-H3 | 2022-11-17 | 2022-12-19 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [8 empty] | STA_456 Dover
NSTAR | Roslindale | ESMAEX-01858 | 02131 | 6 | Solar & Battery | 496-H5 | 2022-11-29 | 2022-12-09 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-21 | [7 empty] | 0 |  | 0 |  |  | 2024-04-10 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | West Newton | ESMAEX-01831 | 02465 | 31.49 | Solar | 1713 | 2022-11-18 | 2022-12-16 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-05-08 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Walpole | ESMAEX-01829 | 02081 | 20.06 | Solar | 146-H4 | 2022-11-17 | 2022-12-19 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-04 | Online | [8 empty] | STA_146 Walpole
NSTAR | Chatham | ESMAEX-01842 | 02633 | 15.2 | Solar & Battery | 4-95B-95B | 2022-11-22 | 2022-12-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-13 | [7 empty] | 0 |  | 0 |  |  | 2024-10-17 | Online | [7 empty] | 10 | STA_975 Orleans
NSTAR | Sharon | ESMAEX-01863 | 02067 | 15.2 | Solar & Battery | 146-H7 | 2022-11-29 | 2022-12-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-08-08 | Online | [8 empty] | STA_146 Walpole
NSTAR | Holliston | ESMAEX-01856 | 01746 | 15.2 | Solar & Battery | 274-H3 | 2022-11-29 | 2022-12-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-21 | [7 empty] | 0 |  | 0 |  |  | 2023-03-20 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Mashpee | ESMAEX-01835 | 02649 | 17.58 | Solar | 4-452-452 | 2022-11-21 | 2022-12-13 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2022-12-15 | [7 empty] | 0 |  | 0 |  |  | 2023-04-04 | Online |  |  |  | Cape |  |  |  |  | STA_946 Mashpee
NSTAR | Framingham | ESMAEX-01837 | 01701 | 20.2 | Solar & Battery | 455-H1 | 2022-11-21 | 2022-12-13 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-06-13 | Online | [7 empty] | 15.36 | STA_455 West Framingham
NSTAR | Wareham | ESMAEX-01836 | 02571 | 12.9 | Solar | 3-83-83 | 2022-11-21 | 2022-12-13 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online |  |  |  | Plymouth |  |  |  |  | STA_714 Wareham
NSTAR | Sudbury | ESMAEX-01932 | 01776 | 17.568 | Solar | 342-H7 | 2022-12-16 | 2023-01-10 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Needham | ESMAEX-01838 | 02492 | 15.2 | Solar & Battery | 148-H4 | 2022-11-21 | 2022-12-16 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-06-21 | Online | [8 empty] | STA_148 Needham
NSTAR | Kingston | ESMAEX-01864 | 02364 | 15.2 | Solar & Battery | 3-15-15 | 2022-11-29 | 2022-12-29 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-03 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Online
NSTAR | Needham | ESMAEX-01871 | 02492 | 4.35 | Solar | 148-H6 | 2022-11-30 | 2022-12-08 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-12 | [7 empty] | 0 |  | 0 |  |  | 2023-07-07 | Online | [8 empty] | STA_148 Needham
NSTAR | Duxbury | ESMAEX-01845 | 02332 | 11.4 | Solar & Battery | 3-23-23 | 2022-11-23 | 2022-12-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-04-12 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Norfolk | ESMAEX-01848 | 02056 | 19.2 | Solar | 65-H1 | 2022-11-26 | 2022-12-19 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-05-19 | Online | [8 empty] | STA_065 Medway
NSTAR | Marshfield | ESMAEX-01850 | 02050 | 10 | Solar & Battery | 3-25-42J2 | 2022-11-28 | 2022-12-29 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Canton | ESMAEX-02179 | 02021 | 240 | Solar | 470-H10 | 2023-02-21 | 2023-03-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Online | [8 empty] | STA_470 Canton
NSTAR | Westwood | ESMAEX-01853 | 02090 | 15.2 | Solar | 456-H4 | 2022-11-28 | 2022-12-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-10-31 | Online | [8 empty] | STA_456 Dover
NSTAR | West Tisbury | ESMAEX-02077 | 02575 | 30.975 | Solar |  | 2023-01-27 | 2023-02-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2025-05-05 | Online |  |  |  | Cape
NSTAR | Carver | ESMAEX-01859 | 02330 | 15.2 | Solar | 3-14-934 | 2022-11-29 | 2023-01-11 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Online | [8 empty] | STA_737 West Pond
NSTAR | Holliston | ESMAEX-01868 | 01746 | 15.2 | Solar | 130-H1 | 2022-11-29 | 2022-12-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-01 | [7 empty] | 0 |  | 0 |  |  | 2023-07-12 | Online | [8 empty] | STA_130 Holliston
NSTAR | Hopkinton | ESMAEX-01908 | 01748 | 16 | Solar | 126-H2 | 2022-12-09 | 2023-01-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-30 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Burlington | ESMAEX-01870 | 01803 | 22.272 | Solar | 391-H6 | 2022-11-30 | 2023-02-06 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-02 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Online | [7 empty] | 22.272 | STA_391 Burlington
NSTAR | Framingham | ESMAEX-01939 | 01701 | 16.104 | Solar | 455-H1 | 2022-12-21 | 2023-01-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-23 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Framingham | ESMAEX-01876 | 01701 | 20 | Solar | 455-H4 | 2022-12-01 | 2022-12-29 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-11-13 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Sharon | ESMAEX-01922 | 02067 | 15.2 | Solar | 146-H7 | 2022-12-14 | 2023-01-12 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-02 | [7 empty] | 0 |  | 0 |  |  | 2023-11-09 | Online | [8 empty] | STA_146 Walpole
NSTAR | Walpole | ESMAEX-01947 | 02081 | 15.2 | Solar & Battery | 456-H1 | 2022-12-27 | 2023-01-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-15 | Online | [8 empty] | STA_456 Dover
NSTAR | Canton | ESMAEX-01889 | 02021 | 17.28 | Solar | 470-H8 | 2022-12-04 | 2022-12-29 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-03-22 | Online | [8 empty] | STA_470 Canton
NSTAR | Norfolk | ESMAEX-01898 | 02056 | 15.2 | Solar & Battery | 146-H3 | 2022-12-07 | 2022-12-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-05 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Online | [8 empty] | STA_146 Walpole
NSTAR | South Dartmouth | ESMAEX-02046 | 02748 | 10 | Battery | 2-528-528 | 2023-01-20 | 2023-02-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-23 | [7 empty] | 0 |  | 0 |  |  | 2023-06-22 | Online
NSTAR | Acton | ESMAEX-01948 | 01720 | 10 | Battery | 416-H5 | 2022-12-27 | 2023-01-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-03 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Online | [8 empty] | STA_416 Maynard
NSTAR | Medfield | ESMAEX-01891 | 02052 | 17.6 | Solar | 146-H6 | 2022-12-06 | 2022-12-29 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-06 | [7 empty] | 0 |  | 0 |  |  | 2023-07-12 | Online | [8 empty] | STA_146 Walpole
NSTAR | Duxbury | ESMAEX-01903 | 02332 | 10.5 | Solar & Battery | 3-26-26 | 2022-12-08 | 2022-12-29 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-04-13 | Online
NSTAR | Westwood | ESMAEX-01895 | 02090 | 15.2 | Solar | 148-H3 | 2022-12-06 | 2023-01-23 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Online | [8 empty] | STA_148 Needham
NSTAR | Acton | ESMAEX-01902 | 01720 | 16.5 | Solar | 416-H1 | 2022-12-07 | 2022-12-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-16 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Online | [8 empty] | STA_416 Maynard
NSTAR | East Wareham | ESMAEX-02002 | 02538 | 7.6 | Solar | 3-82-82 | 2023-01-11 | 2024-07-31 | 405 |  | 405 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-31 | Online |  |  |  | Plymouth |  |  |  |  | STA_714 Wareham
NSTAR | Wayland | ESMAEX-02352 | 01778 | 15 | Battery | 342-H1 | 2023-04-06 | 2023-05-09 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-16 | [7 empty] | 0 |  | 0 |  |  | 2024-05-17 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Mattapoisett | ESMAEX-01983 | 02739 | 19.5 | Solar | 2-301-305 | 2023-01-09 | 2023-02-01 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Carlisle | ESMAEX-01906 | 01741 | 17.6 | Solar & Battery | 533-H8 | 2022-12-08 | 2023-01-04 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Lexington | ESMAEX-02025 | 02421 | 15.2 | Solar & Battery | 320-H5XY | 2023-01-14 | 2023-02-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-04 | Online | [8 empty] | STA_320 Lexington
NSTAR | Hyannis | ESMAEX-01912 | 02601 | 100 | Solar | 4-80B-514 | 2022-12-09 | 2023-01-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-05-16 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Lexington | ESMAEX-01916 | 02421 | 15.372 | Solar | 320-H5XY | 2022-12-12 | 2023-01-10 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-10 | [7 empty] | 0 |  | 0 |  |  | 2023-07-06 | Online | [8 empty] | STA_320 Lexington
NSTAR | Natick | ESMAEX-01914 | 01760 | 15.2 | Solar & Battery | 240-H1 | 2022-12-09 | 2023-01-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-09 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Online | [8 empty] | STA_240 Framingham
NSTAR | Kingston | ESMAEX-01957 | 02364 | 10 | Battery | 3-18-18 | 2023-01-03 | 2023-01-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Online |  |  |  | Plymouth |  |  |  |  | STA_727 Brook Street
NSTAR | Woburn | ESMAEX-01993 | 01801 | 15.2 | Solar & Battery | 375-H14 | 2023-01-10 | 2023-01-31 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Fairhaven | ESMAEX-01927 | 02719 | 10 | Solar & Battery | 2-222-222 | 2022-12-14 | 2023-01-12 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_654 Arsene
NSTAR | Wayland | ESMAEX-01921 | 01778 | 15 | Battery | 278-H2 | 2022-12-13 | 2023-01-11 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-17 | [7 empty] | 0 |  | 0 |  |  | 2024-01-16 | Online | [8 empty] | STA_278 Saxonville
NSTAR | Duxbury | ESMAEX-01935 | 02332 | 15 | Solar & Battery | 3-23-23 | 2022-12-20 | 2023-01-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-23 | [7 empty] | 0 |  | 0 |  |  | 2023-08-31 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Newton Upper Falls | ESMAEX-01928 | 02464 | 19 | Solar | 292-H2 | 2022-12-14 | 2023-01-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-17 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Westwood | ESMAEX-01972 | 02090 | 200 | Solar | 456-H5 | 2023-01-05 | 2023-03-08 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-31 | Online | [8 empty] | STA_456 Dover
NSTAR | Westwood | ESMAEX-01971 | 02090 | 240 | Solar | 469-H4 | 2023-01-05 | 2023-02-09 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-09 | [7 empty] | 0 |  | 0 |  |  | 2024-10-31 | Online
NSTAR | Plymouth | ESMAEX-01931 | 02360 | 3.8 | Solar | 3-12-12 | 2022-12-16 | 2023-01-10 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-05-22 | Online
NSTAR | Harwichport | ESMAEX-01990 | 02646 | 39.6 | Solar | 4-85-592 | 2023-01-10 | 2023-02-01 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-27 | [7 empty] | 0 |  | 0 |  |  | 2025-07-01 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Marshfield | ESMAEX-02182 | 02050 | 15.2 | Solar | 3-25-25 | 2023-02-21 | 2023-03-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-03 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online
NSTAR | Plymouth | ESMAEX-01936 | 02360 | 7.6 | Solar | 3-14-934 | 2022-12-20 | 2023-01-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-18 | [7 empty] | 0 |  | 0 |  |  | 2023-03-24 | Online |  |  |  | Plymouth |  |  |  | 7.6 | STA_737 West Pond
NSTAR | Acton | ESMAEX-01956 | 01720 | 16.104 | Solar | 416-H8 | 2023-01-03 | 2023-01-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-03 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online | [8 empty] | STA_416 Maynard
NSTAR | West Newton | ESMAEX-01942 | 02465 | 25.62 | Solar | 1713 | 2022-12-22 | 2023-01-10 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2024-02-14 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Wareham | ESMAEX-01962 | 02571 | 7.6 | Solar & Battery | 3-84-84 | 2023-01-05 | 2023-01-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-01-30 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Online |  |  |  | Plymouth |  |  |  |  | STA_714 Wareham
NSTAR | Dedham | ESMAEX-01940 | 02026 | 15.2 | Solar | 344-1412H1 | 2022-12-21 | 2023-01-17 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-20 | [7 empty] | 0 |  | 0 |  |  | 2024-01-18 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Newton Center | ESMAEX-01943 | 02459 | 15.9 | Solar | 292-H11 | 2022-12-22 | 2023-01-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-09-18 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Walpole | ESMAEX-02060 | 02081 | 15.2 | Solar & Battery | 146-H6 | 2023-01-23 | 2023-02-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2024-02-13 | Online | [8 empty] | STA_146 Walpole
NSTAR | South Dartmouth | ESMAEX-02044 | 02748 | 6.59 | Solar & Battery | 2-2-505 | 2023-01-20 | 2023-02-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-25 | Online | [8 empty] | STA_611 Pine Street
NSTAR | Needham | ESMAEX-01961 | 02492 | 39.75 | Solar & Battery | 148-H6 | 2023-01-04 | 2023-01-26 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-14 | [7 empty] | 0 |  | 0 |  |  | 2023-09-20 | Online | [8 empty] | STA_148 Needham
NSTAR | Medfield | ESMAEX-02005 | 02052 | 17.934 | Solar | 146-H2 | 2023-01-11 | 2023-02-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2023-07-11 | Online | [8 empty] | STA_146 Walpole
NSTAR | Westport | ESMAEX-01953 | 02790 | 7.6 | Solar & Battery | 2-523-523 | 2023-01-03 | 2023-01-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2024-02-08 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_657 Fisher Road
NSTAR | Sharon | ESMAEX-01965 | 02067 | 19.845 | Solar | LINE48C | 2023-01-05 | 2023-01-23 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Online
NSTAR | Acton | ESMAEX-02092 | 01720 | 15.2 | Solar & Battery | 416-H8 | 2023-01-31 | 2023-02-10 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Online | [8 empty] | STA_416 Maynard
NSTAR | Needham | ESMAEX-01977 | 02492 | 16.836 | Solar | 148-H4 | 2023-01-06 | 2023-01-31 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-06-29 | Online | [8 empty] | STA_148 Needham
NSTAR | North Dartmouth | ESMAEX-01978 | 02747 | 250 | Solar | 2-70-502 | 2023-01-06 | 2023-02-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2024-05-21 | Online
NSTAR | Hopkinton | ESMAEX-02001 | 01748 | 15.2 | Solar | 126-H2 | 2023-01-11 | 2023-02-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-09 | [7 empty] | 0 |  | 0 |  |  | 2023-04-07 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Walpole | ESMAEX-02019 | 02081 | 15.3 | Solar | 146-H8 | 2023-01-13 | 2023-01-23 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Online | [8 empty] | STA_146 Walpole
NSTAR | Bedford | ESMAEX-02061 | 01730 | 15.2 | Solar & Battery | 533-H8 | 2023-01-23 | 2023-02-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-23 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Hopkinton | ESMAEX-01963 | 01748 | 15.2 | Solar | 126-H2 | 2023-01-05 | 2023-02-07 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-07-17 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Holliston | ESMAEX-01967 | 01746 | 15.2 | Solar | 274-H1 | 2023-01-05 | 2023-01-23 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-10 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Milton | ESMAEX-02890 | 02186 | 19.8 | Solar | 470-H9 | 2023-09-21 | 2023-09-20 | -3 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-27 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Online | [8 empty] | STA_470 Canton
NSTAR | Waltham | ESMAEX-03217 | 02451 | 20 | Solar | 282-H5 | 2023-12-04 | 2023-12-18 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Waltham | ESMAEX-03216 | 02451 | 20 | Solar | 282-H5 | 2023-12-04 | 2023-12-18 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Roslindale | ESMAEX-01975 | 02131 | 7.6 | Solar & Battery | 496-H6 | 2023-01-06 | 2023-02-03 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-14 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Stoneham | ESMAEX-01992 | 02180 | 15.2 | Solar & Battery | 375-H8 | 2023-01-10 | 2023-01-31 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Wayland | ESMAEX-02023 | 01778 | 15.2 | Solar | 342-H1 | 2023-01-13 | 2023-02-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-18 | [7 empty] | 0 |  | 0 |  |  | 2023-11-08 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Plymouth | ESMAEX-01998 | 02360 | 11.4 | Solar & Battery | 3-89-922 | 2023-01-11 | 2023-02-06 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2024-04-24 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Ashland | ESMAEX-02081 | 01721 | 87 | Solar | 455-H3 | 2023-01-27 | 2023-02-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-26 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Lexington | ESMAEX-02004 | 02420 | 15.2 | Solar & Battery | 391-H11 | 2023-01-11 |  | -32065 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Online | [8 empty] | STA_391 Burlington
NSTAR | Hatchville | ESMAEX-02000 | 02536 | 17.6 | Solar | 4-78-78 | 2023-01-11 | 2023-02-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2023-09-06 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Needham | ESMAEX-02007 | 02494 | 15.2 | Solar & Battery | 148-H4 | 2023-01-12 | 2023-02-09 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Online | [8 empty] | STA_148 Needham
NSTAR | Newton Center | ESMAEX-02047 | 02459 | 15.2 | Solar & Battery | 1708 | 2023-01-20 | 2023-02-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-17 | [7 empty] | 0 |  | 0 |  |  | 2024-02-29 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | North Truro | ESMAEX-02021 | 02652 | 15 | Battery | 4-96-96 | 2023-01-13 | 2023-02-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-07 | [7 empty] | 0 |  | 0 |  |  | 2023-04-13 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Hopkinton | ESMAEX-02110 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2023-02-03 | 2023-02-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2023-08-21 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | East Brewster | ESMAEX-02011 | 02631 | 18 | Solar | 4-89B-577 | 2023-01-12 | 2023-02-28 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2024-02-28 | Online | [8 empty] | STA_975 Orleans
NSTAR | East Wareham | ESMAEX-02014 | 02538 | 360 | Solar | 3-84-961 | 2023-02-24 | 2023-03-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  | 360 | STA_714 Wareham
NSTAR | Canton | ESMAEX-02029 | 02021 | 18.585 | Solar | 269-1320H1 | 2023-01-16 | 2023-02-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-09-14 | Online | [8 empty] | STA_470 Canton
NSTAR | Medfield | ESMAEX-02035 | 02052 | 15.2 | Solar & Battery | 146-H2 | 2023-01-17 | 2023-02-10 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Online | [8 empty] | STA_146 Walpole
NSTAR | Norfolk | ESMAEX-02026 | 02056 | 17.6 | Solar | 146-H3 | 2023-01-14 | 2023-02-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-11 | [7 empty] | 0 |  | 0 |  |  | 2023-09-26 | Online | [8 empty] | STA_146 Walpole
NSTAR | Natick | ESMAEX-02027 | 01760 | 16.4 | Solar | 240-H5 | 2023-01-14 | 2023-02-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-09 | [7 empty] | 0 |  | 0 |  |  | 2023-07-28 | Online | [8 empty] | STA_240 Framingham
NSTAR | Acusnet | ESMAEX-02031 | 02743 | 4999 | Solar & Battery | 2-241-241 | 2023-01-17 | 2023-02-21 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Marion-Fairhaven | Phase 2 - Executed ISA |  | 2024 SEMA/Cape ASO Study | 4999 | STA_624 Wing Lane
NSTAR | Medway | ESMAEX-02114 | 02053 | 10 | Battery | 65-H3 | 2023-02-04 | 2023-02-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Online | [8 empty] | STA_065 Medway
NSTAR | Sharon | ESMAEX-02057 | 02067 | 20.2 | Solar & Battery | 470-H3 | 2023-01-23 | 2023-02-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-08-17 | Online | [8 empty] | STA_470 Canton
NSTAR | Needham | ESMAEX-02068 | 02492 | 8.027 | Solar | 148-H1 | 2023-01-25 | 2023-02-10 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  | 2023-06-30 | Online | [8 empty] | STA_148 Needham
NSTAR | West Roxbury | ESMAEX-02076 | 02132 | 100 | Solar | 496-H3 | 2023-01-27 | 2023-02-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-30 | [7 empty] | 0 |  | 0 |  |  | 2024-03-08 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Arlington | ESMAEX-02049 | 02474 | 16.5 | Solar | 211-H11 | 2023-01-22 | 2023-02-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online | [8 empty] | STA_211 Woburn
NSTAR | Freetown | ESMAEX-02038 | 02717 | 4980 | Solar & Battery | 2-102-608 | 2023-05-16 | 2023-06-27 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | New Bedford | Hold In Queue |  | 2024 SEMA/Cape ASO Study |  | STA_636 Industrial Park
NSTAR | Walpole | ESMAEX-02041 | 02081 | 15.2 | Solar & Battery | 2601 | 2023-01-19 | 2023-02-10 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-28 | [7 empty] | 0 |  | 0 |  |  | 2023-08-14 | Online | [8 empty] | STA_146 Walpole
NSTAR | Woburn | ESMAEX-02100 | 01801 | 35.1 | Solar | 211-H5 | 2023-02-01 | 2023-02-16 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-21 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Online | [8 empty] | STA_211 Woburn
NSTAR | West Newton | ESMAEX-02048 | 02465 | 15.36 | Solar | 1703 | 2023-01-20 | 2023-02-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-14 | [7 empty] | 0 |  | 0 |  |  | 2023-07-19 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Natick | ESMAEX-02053 | 01760 | 19.84 | Solar | 433-H7 | 2023-01-23 | 2023-02-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-05-08 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Wayland | ESMAEX-02054 | 01778 | 15.2 | Solar | 278-H2 | 2023-01-23 | 2023-02-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-07 | Online | [8 empty] | STA_278 Saxonville
NSTAR | Allston | ESMAEX-02105 | 02134 | 66.6 | Solar | 315-H3 | 2023-02-02 | 2023-03-21 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-24 | [7 empty] | 0 |  | 0 |  |  | 2025-05-13 | Online | [8 empty] | STA_315 Electric Avenue
NSTAR | North Dartmouth | ESMAEX-02064 | 02747 | 10 | Battery | 2-541-541 | 2023-01-24 | 2023-02-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-23 | [7 empty] | 0 |  | 0 |  |  | 2024-03-26 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | New Bedford | ESMAEX-02066 | 02744 | 200 | Solar | 2-24-24 | 2023-03-15 | 2023-04-13 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  | 2025-11-14 | Permission to Operate | [8 empty] | STA_611 Pine Street
NSTAR | Acton | ESMAEX-02070 | 01720 | 15.2 | Solar & Battery | 416-H8 | 2023-01-25 | 2023-02-14 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-01 | [7 empty] | 0 |  | 0 |  |  | 2024-09-11 | Online | [7 empty] | 20 | STA_416 Maynard
NSTAR | East Freetown | ESMAEX-02075 | 02717 | 17.6 | Solar | 2-108-108 | 2023-01-26 | 2023-02-15 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-01 | [7 empty] | 0 |  | 0 |  |  | 2023-05-24 | Online |  |  |  | Cape |  |  |  | 17.6 | STA_636 Industrial Park
NSTAR | North Dartmouth | ESMAEX-02083 | 02747 | 312.5 | Solar | 2-543-543 | 2023-07-28 | 2023-08-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-06 | Online |  |  |  | Dartmouth-Westport |  |  |  | 25 | STA_651 Cross Road
NSTAR | Jamaica Plain | ESMAEX-02135 | 02130 | 10 | Battery | 284-1300H1 | 2023-02-07 | 2023-03-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-04-18 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Canton | ESMAEX-03358 | 02021 | 100 | Solar | 470-H7 | 2024-01-12 | 2024-01-31 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2025-12-02 | Billing | [8 empty] | STA_470 Canton
NSTAR | Milton | ESMAEX-02091 | 02186 | 16 | Solar | 470-H9 | 2023-01-30 | 2023-02-10 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-13 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Online | [7 empty] | 16 | STA_470 Canton
NSTAR | Sharon | ESMAEX-02117 | 02067 | 100 | Solar | 470-H12 | 2023-02-06 | 2023-02-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [8 empty] | STA_470 Canton
NSTAR | Boston | ESMAEX-02098 | 02115 | 15.2 | Solar & Battery | 5202 | 2023-02-01 | 2023-02-16 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-07 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Wayland | ESMAEX-02245 | 01778 | 7.6 | Solar & Battery | 342-H1 | 2023-03-08 | 2023-03-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-24 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Bedford | ESMAEX-02097 | 01730 | 19.96 | Solar | 533-H7 | 2023-02-01 | 2023-02-14 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-12 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Sharon | ESMAEX-02126 | 02067 | 60 | Solar | 470-H12 | 2023-02-06 | 2023-02-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [8 empty] | STA_470 Canton
NSTAR | Medfield | ESMAEX-02108 | 02052 | 15.2 | Solar & Battery | 456-H2 | 2023-02-02 | 2023-02-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-29 | Online | [8 empty] | STA_456 Dover
NSTAR | New Bedford | ESMAEX-02331 | 02744 | 10 | Solar & Battery | 2-25-25 | 2023-03-31 | 2023-04-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-15 | [7 empty] | 0 |  | 0 |  |  | 2024-07-12 | Online
NSTAR | Cambridge | ESMAEX-02373 | 02139 | 20.06 | Solar | 814-12 | 2023-04-13 | 2023-04-24 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-21 | [7 empty] | 0 |  | 0 |  |  | 2024-06-18 | Online | [8 empty] | STA_402 Newton Street
NSTAR | Cambridge | ESMAEX-02188 | 02138 | 9.6 | Battery | 823-21 | 2023-02-22 | 2023-03-21 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-17 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Online | [8 empty] | STA_828 Alewife
NSTAR | East Wareham | ESMAEX-02199 | 02538 | 120 | Solar | 3-84-961 | 2023-02-24 | 2023-03-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  | 120 | STA_714 Wareham
NSTAR | Walpole | ESMAEX-02431 | 02081 | 100 | Solar | 146-H8 | 2023-04-28 | 2023-05-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-30 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [8 empty] | STA_146 Walpole
NSTAR | Woburn | ESMAEX-02432 | 01801 | 75 | Solar | 375-H6 | 2023-04-29 | 2023-05-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-31 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Walpole | ESMAEX-02129 | 02081 | 19.52 | Solar | 146-H4 | 2023-02-07 | 2023-03-21 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-12 | [7 empty] | 0 |  | 0 |  |  | 2023-07-13 | Online | [8 empty] | STA_146 Walpole
NSTAR | Lexington | ESMAEX-02157 | 02420 | 19 | Solar | 320-H7 | 2023-02-14 | 2023-02-28 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-11-16 | Online | [8 empty] | STA_320 Lexington
NSTAR | Needham | ESMAEX-02177 | 02492 | 15.2 | Solar | 148-01 | 2023-02-17 | 2023-03-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2024-03-05 | Online | [8 empty] | STA_148 Needham
NSTAR | Onset | ESMAEX-02152 | 02558 | 1.28 | Battery | 3-88-17J1 | 2023-02-13 | 2023-03-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-07 | [7 empty] | 0 |  | 0 |  |  | 2023-11-15 | Online
NSTAR | Wayland | ESMAEX-02136 | 01778 | 16.2 | Solar | 278-H2 | 2023-02-07 | 2023-02-16 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-24 | [7 empty] | 0 |  | 0 |  |  | 2023-07-06 | Online | [8 empty] | STA_278 Saxonville
NSTAR | Sagamore Beach | ESMAEX-02140 | 02562 | 15.2 | Solar & Battery | 3-89-925 | 2023-02-08 | 2023-02-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-02-27 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Watertown | ESMAEX-02150 | 02472 | 120 | Solar | 470-H10 | 2023-02-13 | 2023-03-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-13 | [7 empty] | 0 |  | 0 |  |  | 2024-07-24 | Online | [8 empty] | STA_470 Canton
NSTAR | Winchester | ESMAEX-02166 | 01890 | 220 | Solar | 211-H13 | 2023-02-15 | 2023-03-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-12-22 | Online | [8 empty] | STA_211 Woburn
NSTAR | Cambridge | ESMAEX-02353 | 02139 | 19.18 | Solar | 817-03 | 2023-04-06 | 2023-04-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-06 | Online | [8 empty] | STA_831 Putnam
NSTAR | Sharon | ESMAEX-02167 | 02067 | 15.2 | Solar | 146-H1 | 2023-02-16 | 2023-03-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-13 | [7 empty] | 0 |  | 0 |  |  | 2023-06-15 | Online | [8 empty] | STA_146 Walpole
NSTAR | Needham | ESMAEX-02153 | 02494 | 7.6 | Solar | 148-H1 | 2023-02-13 | 2023-03-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-09-27 | Online | [8 empty] | STA_148 Needham
NSTAR | Dover | ESMAEX-02209 | 02030 | 25.2 | Solar | 456-H5 | 2023-02-27 | 2023-03-21 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-06-28 | Online | [8 empty] | STA_456 Dover
NSTAR | West Newton | ESMAEX-02154 | 02465 | 15.2 | Solar & Battery | 282-H9 | 2023-02-13 | 2023-03-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [8 empty] | STA_282 Waltham
NSTAR | Hopkinton | ESMAEX-02183 | 01748 | 15.2 | Solar | 455-H8 | 2023-02-21 | 2023-03-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-13 | [7 empty] | 0 |  | 0 |  |  | 2023-08-10 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Woburn | ESMAEX-02186 | 01801 | 150 | Solar | 211-H2 | 2023-02-22 | 2023-04-04 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2025-08-06 | Online | [8 empty] | STA_211 Woburn
NSTAR | North Truro | ESMAEX-02223 | 02652 | 10.25 | Solar & Battery | 4-96-96 | 2023-03-02 | 2023-03-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-29 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Westport | ESMAEX-02358 | 02790 | 1350 | Solar | 2-522-522 | 2023-04-08 | 2023-04-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-09-01 | Online | [7 empty] | 1350
NSTAR | Norfolk | ESMAEX-02208 | 02056 | 200 | Solar | 65-H1 | 2023-02-27 | 2023-03-21 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_065 Medway
NSTAR | Framingham | ESMAEX-02172 | 01702 | 15.2 | Solar & Battery | 240-H4 | 2023-02-17 | 2023-03-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-23 | [7 empty] | 0 |  | 0 |  |  | 2023-06-19 | Online | [8 empty] | STA_240 Framingham
NSTAR | Acton | ESMAEX-02180 | 01720 | 199.9 | Solar | 416-H8 | 2023-02-21 | 2023-03-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_416 Maynard
NSTAR | Acton | ESMAEX-02173 | 01720 | 960 | Solar | 416-H9 | 2023-03-31 | 2023-04-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_416 Maynard
NSTAR | Needham | ESMAEX-02181 | 02494 | 17.5698 | Solar | 148-H7 | 2023-02-21 | 2023-03-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-08-29 | Online | [8 empty] | STA_148 Needham
NSTAR | Westwood | ESMAEX-02213 | 02090 | 18.3 | Solar | 456-H1 | 2023-02-28 | 2023-03-21 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2023-07-14 | Online | [8 empty] | STA_456 Dover
NSTAR | Acton | ESMAEX-02187 | 01720 | 160 | Solar & Battery | 416-H5 | 2023-02-22 | 2023-03-30 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-14 | [7 empty] | 0 |  | 0 |  |  | 2024-01-19 | ISA Agreement | [8 empty] | STA_416 Maynard
NSTAR | Lexington | ESMAEX-02229 | 02421 | 10 | Battery | 320-H5XY | 2023-03-03 | 2023-03-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-09 | Online | [8 empty] | STA_320 Lexington
NSTAR | Woburn | ESMAEX-02195 | 01801 | 166.6 | Solar & Battery | 211-H2 | 2023-02-23 | 2023-03-02 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Online | [8 empty] | STA_211 Woburn
NSTAR | Holliston | ESMAEX-02203 | 01746 | 120 | Solar | 65-H2 | 2023-02-24 | 2023-03-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-31 | [7 empty] | 0 |  | 0 |  |  | 2024-07-23 | Online | [8 empty] | STA_065 Medway
NSTAR | Bellingham | ESMAEX-02191 | 02019 | 6 | Solar | 65-H4 | 2023-02-22 | 2023-03-21 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-07-24 | Online | [7 empty] | 6 | STA_065 Medway
NSTAR | Brewster | ESMAEX-02197 | 02631 | 16 | Solar & Battery | 4-89B-89B | 2023-02-23 | 2023-03-21 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-22 | [7 empty] | 0 |  | 0 |  |  | 2023-07-03 | Online | [7 empty] | 6 | STA_975 Orleans
NSTAR | Sharon | ESMAEX-02207 | 02067 | 19 | Solar | 470-H3 | 2023-02-27 | 2023-03-23 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-23 | [7 empty] | 0 |  | 0 |  |  | 2024-01-05 | Online | [8 empty] | STA_470 Canton
NSTAR | Brewster | ESMAEX-02212 | 02631 | 15.2 | Solar | 4-89B-576 | 2023-02-28 | 2023-03-23 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-28 | [7 empty] | 0 |  | 0 |  |  | 2024-01-17 | Online | [8 empty] | STA_975 Orleans
NSTAR | Needham | ESMAEX-02248 | 02494 | 15.2 | Solar & Battery | 292-H4 | 2023-03-08 | 2023-03-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-13 | [7 empty] | 0 |  | 0 |  |  | 2023-09-27 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Medfield | ESMAEX-02218 | 02052 | 100 | Solar | 456-H2 | 2023-03-23 | 2023-04-11 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [8 empty] | STA_456 Dover
NSTAR | Medfield | ESMAEX-02219 | 02052 | 480 | Solar | 456-H2 | 2023-03-24 | 2023-04-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-28 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_456 Dover
NSTAR | Medfield | ESMAEX-02220 | 02052 | 250 | Solar | 146-H2 | 2023-03-24 | 2023-04-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  | 2025-12-31 | Online | [8 empty] | STA_146 Walpole
NSTAR | Woburn | ESMAEX-02255 | 01801 | 117.3 | Solar | 375-H14 | 2023-03-09 | 2023-04-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | New Bedford | ESMAEX-02224 | 02746 | 996 | Solar & Battery | 2-83-403 | 2023-08-08 | 2023-09-20 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-15 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 999 | STA_612 Acushnet
NSTAR | North Dartmouth | ESMAEX-02225 | 02747 | 999 | Solar & Battery | 2-543-543 | 2023-08-08 | 2023-09-26 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Dartmouth-Westport |  |  |  | 999 | STA_651 Cross Road
NSTAR | Rochester | ESMAEX-03301 | 02770 | 4980 | Solar & Battery | 3-85-85 | 2023-12-20 | 2024-01-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study | 2024 SEMA/Cape ASO Study |  | STA_713 Tremont
NSTAR | Plymouth | ESMAEX-02240 | 02360 | 16.9 | Solar | 3-71-38J1 | 2023-03-08 | 2023-04-11 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-13 | [7 empty] | 0 |  | 0 |  |  | 2023-09-25 | Online |  |  |  | Plymouth |  |  |  |  | STA_721 Manomet
NSTAR | Medway | ESMAEX-02234 | 02053 | 16.4 | Solar & Battery | 65-H2 | 2023-03-05 | 2023-03-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-12 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online | [8 empty] | STA_065 Medway
NSTAR | Natick | ESMAEX-02242 | 01760 | 16.47 | Solar | 240-H1 | 2023-03-08 | 2023-03-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-06 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [8 empty] | STA_240 Framingham
NSTAR | Rochester | ESMAEX-02237 | 02770 | 4980 | Solar & Battery | 3-702-702 | 2023-06-02 | 2023-06-21 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Marion-Fairhaven | Phase 2 - Executed ISA |  | 2024 SEMA/Cape ASO Study |  | STA_745 ROCHESTER
NSTAR | South Orleans | ESMAEX-02239 | 02662 | 17.4 | Solar | 4-628-628 | 2023-03-07 | 2023-04-20 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-27 | [7 empty] | 0 |  | 0 |  |  | 2023-07-20 | Online | [8 empty] | STA_975 Orleans
NSTAR | Edgartown | ESMAEX-02243 | 02539 | 15 | Solar | 4-75-75 | 2023-03-08 | 2024-08-15 | 376 |  | 376 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2025-01-14 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Framingham | ESMAEX-02247 | 01701 | 15.3 | Solar | 342-H4 | 2023-03-08 | 2023-03-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-03-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-12 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Winchester | ESMAEX-02249 | 01890 | 8.4 | Solar | 211-H3 | 2023-03-08 | 2023-03-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-03 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [8 empty] | STA_211 Woburn
NSTAR | Cambridge | ESMAEX-02271 | 02139 | 7.6 | Solar | 817-01 | 2023-03-15 | 2023-04-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-12 | [7 empty] | 0 |  | 0 |  |  | 2024-09-23 | Online | [8 empty] | STA_831 Putnam
NSTAR | Stoneham | ESMAEX-02257 | 02180 | 9.6 | Battery | 375-H2 | 2023-03-10 | 2023-04-03 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-01-18 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Marstons Mills | ESMAEX-02419 | 02648 | 4.8 | Solar | 4-87A-87A | 2023-04-26 | 2023-05-22 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 | [7 empty] | 0 |  | 0 |  |  | 2025-11-21 | Online |  |  |  | Cape |  |  |  |  | STA_916 Sandwich
NSTAR | Plymouth | ESMAEX-02305 | 02360 | 16.5 | Solar | 3-14-931 | 2023-03-24 | 2023-04-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-13 | [7 empty] | 0 |  | 0 |  |  | 2024-12-20 | Online |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Boston | ESMAEX-02263 | 02127 | 34.6 | Solar | 385-H1 | 2023-03-14 | 2023-04-20 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-25 | [7 empty] | 0 |  | 0 |  |  | 2024-04-22 | Online | [8 empty] | STA_385D K Street
NSTAR | Acton | ESMAEX-02268 | 01720 | 15.2 | Solar & Battery | 416-H8 | 2023-03-14 | 2023-04-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-11 | [7 empty] | 0 |  | 0 |  |  | 2024-02-07 | Online | [8 empty] | STA_416 Maynard
NSTAR | Lexington | ESMAEX-02270 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2023-03-15 | 2023-04-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Barnstable | ESMAEX-02273 | 02630 | 8 | Battery | 4-84B-510 | 2023-03-15 | 2023-04-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-10 | [7 empty] | 0 |  | 0 |  |  | 2023-08-02 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Plympton | ESMAEX-02277 | 02367 | 5559.66 | Solar & Battery | 3-51-51 | 2023-03-17 | 2023-04-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study | 2024 SEMA/Cape ASO Study | 4999 | STA_727 Brook Street
NSTAR | Framingham | ESMAEX-02275 | 01701 | 15.2 | Solar | 455-H1 | 2023-03-16 | 2023-04-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-12 | [7 empty] | 0 |  | 0 |  |  | 2023-09-12 | Online | [7 empty] | 15.2 | STA_455 West Framingham
NSTAR | Arlington | ESMAEX-02286 | 02474 | 100 | Solar | 59-1393H1 | 2023-03-20 | 2023-04-06 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-03-22 | Online | [8 empty] | STA_211 Woburn
NSTAR | Westwood | ESMAEX-02297 | 02090 | 16.47 | Solar | 469-H2 | 2023-03-22 | 2023-04-03 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-07 | [7 empty] | 0 |  | 0 |  |  | 2023-07-14 | Online
NSTAR | Jamaica Plain | ESMAEX-02338 | 02130 | 19.47 | Solar | 350-H2 | 2023-04-03 | 2023-04-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-22 | [7 empty] | 0 |  | 0 |  |  | 2023-10-05 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Canton | ESMAEX-02281 | 02021 | 19 | Solar | 470-H9 | 2023-03-17 | 2023-04-25 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [8 empty] | STA_470 Canton
NSTAR | Sharon | ESMAEX-02282 | 02067 | 15.2 | Solar & Battery | 470-H3 | 2023-03-17 | 2023-04-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-19 | [7 empty] | 0 |  | 0 |  |  | 2023-11-30 | Online | [8 empty] | STA_470 Canton
NSTAR | Hopkinton | ESMAEX-02291 | 01748 | 15.2 | Solar | 455-H8 | 2023-03-21 | 2023-04-06 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-12 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Brookline | ESMAEX-02292 | 02445 | 20 | Solar | 25N30 | 2023-03-21 | 2023-05-03 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-09-10 | Online | [8 empty] | STA_329 Brighton
NSTAR | Canton | ESMAEX-02293 | 02021 | 19 | Solar | 470-H6 | 2023-03-21 | 2023-04-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-08 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Online | [8 empty] | STA_470 Canton
NSTAR | South Dartmouth | ESMAEX-02398 | 02748 | 34.6 | Solar | 2-60-63 | 2023-04-20 | 2023-05-08 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-15 | [7 empty] | 0 |  | 0 |  |  | 2023-07-27 | Technical Review | [8 empty] | STA_611 Pine Street
NSTAR | Canton | ESMAEX-02308 | 02021 | 100 | Solar | 470-H4 | 2023-03-24 | 2023-04-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-01-09 | Online | [8 empty] | STA_470 Canton
NSTAR | Canton | ESMAEX-02310 | 02021 | 70 | Solar | 470-H4 | 2023-03-24 | 2023-04-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-09 | [7 empty] | 0 |  | 0 |  |  | 2024-05-20 | Online | [8 empty] | STA_470 Canton
NSTAR | East Freetown | ESMAEX-02299 | 02717 | 20 | Solar & Battery | 2-108-108 | 2023-03-22 | 2023-04-13 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Lincoln | ESMAEX-02319 | 01773 | 10 | Battery | 320-H6 | 2023-03-29 | 2023-04-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-19 | [7 empty] | 0 |  | 0 |  |  | 2023-06-07 | Online | [8 empty] | STA_320 Lexington
NSTAR | Wayland | ESMAEX-02332 | 01778 | 18.3 | Solar | 342-H3 | 2023-04-01 | 2023-04-17 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Roxbury | ESMAEX-02371 | 02119 | 67.3 | Solar | 52-1487H1 | 2023-04-12 | 2023-05-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-08-28 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Westport | ESMAEX-02359 | 02790 | 1200 | Solar | 2-522-522 | 2023-04-08 | 2023-04-11 | 2 |  | 2 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2016-09-01 | Online | [7 empty] | 1200
NSTAR | Kingston | ESMAEX-02313 | 02364 | 180 | Solar | 3-14-14 | 2023-04-11 | 2023-05-08 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2025-11-14 | Online |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Holliston | ESMAEX-02318 | 01746 | 7.4 | Battery | 65-H2 | 2023-03-28 | 2023-04-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-04 | [7 empty] | 0 |  | 0 |  |  | 2023-08-15 | Online | [7 empty] | 7.4 | STA_065 Medway
NSTAR | Dorchester | ESMAEX-02420 | 02125 | 480 | Solar | 511-1495H1 | 2023-04-26 | 2023-05-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-20 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Weston | ESMAEX-02328 | 02493 | 100 | Solar | 450-H7 | 2023-03-31 | 2023-04-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2024-03-01 | Online | [8 empty] | STA_450 Trapelo Road
NSTAR | Truro | ESMAEX-02713 | 02652 | 50 | Solar | 4-96-96 | 2023-07-26 | 2023-08-24 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-25 | [7 empty] | 0 |  | 0 |  |  | 2024-09-05 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Woods Hole | ESMAEX-02335 | 02543 | 40 | Solar | 4-91-91 | 2023-04-03 | 2023-04-17 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-31 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Holliston | ESMAEX-02333 | 01746 | 20 | Solar & Battery | 130-H1 | 2023-04-03 | 2023-04-17 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [8 empty] | STA_130 Holliston
NSTAR | Westwood | ESMAEX-02337 | 02090 | 360 | Solar | 148-H3 | 2023-06-27 | 2023-08-22 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-17 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Online | [8 empty] | STA_148 Needham
NSTAR | Lincoln | ESMAEX-02346 | 01773 | 20 | Solar | 320-H8 | 2023-04-05 | 2023-04-25 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-30 | [7 empty] | 0 |  | 0 |  |  | 2023-08-07 | Online | [7 empty] | 20 | STA_320 Lexington
NSTAR | Marion | ESMAEX-02355 | 02738 | 15.2 | Solar & Battery | 3-702-702 | 2023-04-06 | 2023-04-27 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-01 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_745 Rochester
NSTAR | Lincoln | ESMAEX-02341 | 01773 | 11.52 | Solar | 342-H1 | 2023-04-04 | 2023-04-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-24 | [7 empty] | 0 |  | 0 |  |  | 2023-08-29 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Rochester | ESMAEX-02342 | 02770 | 14.5 | Solar | 3-702-702 | 2023-04-04 | 2023-04-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-21 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_745 Rochester
NSTAR | Sharon | ESMAEX-02345 | 02067 | 18.5 | Solar | LINE48C | 2023-04-05 | 2023-04-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-09-29 | Online
NSTAR | Canton | ESMAEX-02349 | 02021 | 15.3 | Solar | 269-1320H1 | 2023-04-05 | 2023-04-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-26 | [7 empty] | 0 |  | 0 |  |  | 2023-08-23 | Online | [8 empty] | STA_470 Canton
NSTAR | Maynard | ESMAEX-02347 | 01754 | 7.6 | Solar | 416-H6 | 2023-04-05 | 2023-04-25 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-05 | [7 empty] | 0 |  | 0 |  |  | 2023-12-08 | Online | [8 empty] | STA_416 Maynard
NSTAR | Ashland | ESMAEX-02538 | 01721 | 22.8 | Solar & Battery | 274-H5 | 2023-05-30 | 2023-06-21 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-25 | [7 empty] | 0 |  | 0 |  |  | 2024-02-08 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Hopkinton | ESMAEX-02356 | 01748 | 19.9 | Solar & Battery | 126-H4 | 2023-04-06 | 2023-04-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-25 | [7 empty] | 0 |  | 0 |  |  | 2023-08-21 | Online | [7 empty] | 19.9 | STA_126 Hopkinton
NSTAR | Needham | ESMAEX-02366 | 02492 | 15.2 | Solar & Battery | 148-07 | 2023-04-10 | 2023-05-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online | [8 empty] | STA_148 Needham
NSTAR | Hopkinton | ESMAEX-02363 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2023-04-10 | 2023-04-25 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-04-25 | [7 empty] | 0 |  | 0 |  |  | 2023-12-01 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-02364 | 01720 | 16.8 | Solar | 416-H5 | 2023-04-10 | 2023-05-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-10-02 | Online | [8 empty] | STA_416 Maynard
NSTAR | Rochester | ESMAEX-02368 | 02770 | 4999 | Solar & Battery | 3-703-703 | 2023-04-11 | 2023-09-20 | 116 |  | 116 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Marion-Fairhaven | Phase 2 - Executed ISA |  | 2024 SEMA/Cape ASO Study | 4999 | STA_745 ROCHESTER
NSTAR | Auburndale | ESMAEX-02380 | 02466 | 67.3 | Solar | 292-H7 | 2023-04-14 | 2023-05-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2025-05-02 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | West Roxbury | ESMAEX-02372 | 02132 | 15.3 | Solar | 468-06 | 2023-04-13 | 2023-05-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-09 | [7 empty] | 0 |  | 0 |  |  | 2023-08-28 | Online | [8 empty] | STA_110 Baker Street
NSTAR | West Newton | ESMAEX-02376 | 02465 | 15.2 | Solar & Battery | 33-H3 | 2023-04-13 | 2023-05-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-27 | [7 empty] | 0 |  | 0 |  |  | 2024-08-15 | Online | [8 empty] | STA_282 Waltham
NSTAR | Newton Center | ESMAEX-02381 | 02459 | 110 | Solar | 1709 | 2023-04-14 | 2023-05-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-14 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [7 empty] | 110 | STA_292 Newton Highlands
NSTAR | Dover | ESMAEX-02379 | 02030 | 17.6 | Solar | 148-H3 | 2023-04-14 | 2023-05-09 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-23 | [7 empty] | 0 |  | 0 |  |  | 2023-10-20 | Online | [7 empty] | 17.6 | STA_148 Needham
NSTAR | Lincoln | ESMAEX-02476 | 01773 | 15.2 | Solar & Battery | 320-H6 | 2023-05-15 | 2023-05-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-30 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Online | [8 empty] | STA_320 Lexington
NSTAR | Duxbury | ESMAEX-02401 | 02332 | 13.2 | Solar & Battery | 3-26-26 | 2023-04-21 | 2023-05-25 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-02 | [7 empty] | 0 |  | 0 |  |  | 2024-11-22 | Online
NSTAR | Plymouth | ESMAEX-02387 | 02360 | 16 | Solar | 3-10-10 | 2023-04-18 | 2023-05-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-11 | [7 empty] | 0 |  | 0 |  |  | 2024-03-25 | Online | [7 empty] | 16
NSTAR | Boston | ESMAEX-02427 | 02119 | 50 | Solar | 52-1487H1 | 2023-04-28 | 2023-05-24 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-30 | [7 empty] | 0 |  | 0 |  |  | 2024-08-07 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Wellfleet | ESMAEX-02389 | 02667 | 6.4 | Battery | 4-94B-94B | 2023-04-19 | 2023-05-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2023-05-18 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Wayland | ESMAEX-02392 | 01778 | 100 | Solar | 433-H2 | 2023-05-26 | 2023-06-19 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Cambridge | ESMAEX-02574 | 02139 | 28.8 | Solar | 819-1NE4 | 2023-06-12 | 2023-07-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-09-11 | Online | [8 empty] | STA_402 Newton Street
NSTAR | Natick | ESMAEX-02403 | 01760 | 15 | Battery | 433-H5 | 2023-04-21 | 2023-05-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-17 | [7 empty] | 0 |  | 0 |  |  | 2023-09-22 | Online | [7 empty] | 20 | STA_433 Speen Street
NSTAR | Waltham | ESMAEX-02400 | 02452 | 16 | Solar | 450-H4 | 2023-04-21 | 2023-05-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-24 | [7 empty] | 0 |  | 0 |  |  | 2023-09-11 | Online | [7 empty] | 16 | STA_450 Trapelo Road
NSTAR | Waltham | ESMAEX-02402 | 02451 | 15.2 | Solar | 450-H1 | 2023-04-21 | 2023-05-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-23 | [7 empty] | 0 |  | 0 |  |  | 2023-11-15 | Online | [8 empty] | STA_450 Trapelo Road
NSTAR | Kingston | ESMAEX-02406 | 02364 | 15.2 | Solar | 3-909-909 | 2023-04-21 | 2023-05-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-11 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Online |  |  |  | Plymouth |  |  |  |  | STA_735 Kingston
NSTAR | Norfolk | ESMAEX-02429 | 02056 | 15 | Battery | 65-H1 | 2023-04-28 | 2023-05-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-14 | [7 empty] | 0 |  | 0 |  |  | 2024-10-23 | Online | [8 empty] | STA_065 Medway
NSTAR | Somerville | ESMAEX-02814 | 02143 | 25.37 | Solar | 13N14 | 2023-08-15 | 2023-08-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-05 | [7 empty] | 0 |  | 0 |  |  | 2025-11-19 | Online | [8 empty] | STA_250 Mystic
NSTAR | Sharon | ESMAEX-02413 | 02067 | 250 | Solar | 470-H12 | 2023-05-17 | 2023-06-27 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-24 | [7 empty] | 0 |  | 0 |  |  | 2015-03-23 | Compliance Documents | [8 empty] | STA_470 Canton
NSTAR | Waban | ESMAEX-02444 | 02468 | 25.2 | Solar & Battery | 292-H2 | 2023-05-04 | 2023-05-24 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-17 | [7 empty] | 0 |  | 0 |  |  | 2024-02-20 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Medway | ESMAEX-02416 | 02053 | 15.2 | Solar | 65-H3 | 2023-04-26 | 2023-05-22 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-19 | [7 empty] | 0 |  | 0 |  |  | 2023-12-07 | Online | [8 empty] | STA_065 Medway
NSTAR | Framingham | ESMAEX-02417 | 01701 | 17.4 | Solar | 342-H2 | 2023-04-26 | 2023-05-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-26 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Chatham | ESMAEX-02424 | 02633 | 15.2 | Solar & Battery | 4-95B-95B | 2023-04-27 | 2023-05-16 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-16 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Online | [8 empty] | STA_975 Orleans
NSTAR | Arlington | ESMAEX-02426 | 02476 | 67.3 | Solar | 211-H3 | 2023-04-28 | 2023-05-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-18 | [7 empty] | 0 |  | 0 |  |  | 2024-03-07 | Online | [8 empty] | STA_211 Woburn
NSTAR | Brookline | ESMAEX-02460 | 02445 | 12.54 | Solar & Battery | 350-H8 | 2023-05-08 | 2023-05-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-01 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Sharon | ESMAEX-02433 | 02067 | 480 | Solar | 146-H1 | 2023-08-04 | 2023-08-24 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-13 | [7 empty] | 0 |  | 0 |  |  |  | Permission to Operate | [8 empty] | STA_146 Walpole
NSTAR | Lexington | ESMAEX-02439 | 02421 | 15.2 | Solar | 320-H2 | 2023-05-02 | 2023-05-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2023-07-31 | Online | [8 empty] | STA_320 Lexington
NSTAR | Natick | ESMAEX-02478 | 01760 | 4.4 | Solar & Battery | 23-H1 | 2023-05-15 | 2023-06-15 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online | [8 empty] | STA_240 Framingham
NSTAR | Holliston | ESMAEX-02449 | 01746 | 19.98 | Solar | 65-H5 | 2023-05-05 | 2023-05-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2023-10-25 | Online | [8 empty] | STA_065 Medway
NSTAR | Wareham | ESMAEX-02441 | 02738 | 2000 | Solar & Battery | 3-85-85 | 2023-08-08 | 2023-09-26 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study | 2024 SEMA/Cape ASO Study | 2000 | STA_713 Tremont
NSTAR | Ashland | ESMAEX-02440 | 01721 | 15.2 | Solar & Battery | 455-H3 | 2023-05-03 | 2023-05-18 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-05-22 | [7 empty] | 0 |  | 0 |  |  | 2023-12-01 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Newton Highlands | ESMAEX-02447 | 02461 | 17.9 | Solar | 292-H16 | 2023-05-05 | 2023-05-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-29 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Online
NSTAR | Norfolk | ESMAEX-02445 | 02056 | 15.2 | Solar | 65-H1 | 2023-05-04 | 2023-05-31 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Online | [7 empty] | 15.2 | STA_065 Medway
NSTAR | Westport | ESMAEX-02446 | 02790 | 199 | Solar & Battery | 2-523-523 | 2023-05-04 | 2023-05-25 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-18 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Dartmouth-Westport |  |  |  |  | STA_657 Fisher Road
NSTAR | Lexington | ESMAEX-02454 | 02421 | 15.2 | Solar | 533-H1 | 2023-05-05 | 2023-05-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-26 | [7 empty] | 0 |  | 0 |  |  | 2023-09-08 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Hopkinton | ESMAEX-02455 | 01748 | 15.2 | Solar | 455-H8 | 2023-05-06 | 2023-05-30 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-11 | [7 empty] | 0 |  | 0 |  |  | 2024-02-20 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Medfield | ESMAEX-02453 | 02052 | 19.584 | Solar | 456-H3 | 2023-05-05 | 2023-05-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-15 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [8 empty] | STA_456 Dover
NSTAR | Norfolk | ESMAEX-02461 | 02056 | 15.2 | Solar & Battery | 146-H9 | 2023-05-08 | 2023-06-06 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-16 | [7 empty] | 0 |  | 0 |  |  | 2024-01-17 | Online | [8 empty] | STA_146 Walpole
NSTAR | Framingham | ESMAEX-02481 | 01701 | 6.39 | Battery | 433-H4 | 2023-05-16 | 2023-05-31 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2023-08-11 | Online | [7 empty] | 6.39 | STA_433 Speen Street
NSTAR | Sherborn | ESMAEX-02464 | 01770 | 210 | Solar | 240-H1 | 2023-05-09 | 2023-05-31 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-06 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_240 Framingham
NSTAR | Sherborn | ESMAEX-02465 | 01770 | 15.2 | Solar | 274-H2 | 2023-05-09 | 2023-05-31 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [7 empty] | 15.2 | STA_274 Sherborn
NSTAR | Sherborn | ESMAEX-02468 | 01770 | 10 | Solar | 274-H2 | 2023-05-09 | 2023-06-06 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-18 | [7 empty] | 0 |  | 0 |  |  | 2024-11-26 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Hopkinton | ESMAEX-02469 | 01748 | 15.2 | Solar | 126-H1 | 2023-05-10 | 2023-05-24 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-01 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Framingham | ESMAEX-02474 | 01701 | 14.1 | Solar | 342-H4 | 2023-05-11 | 2023-05-25 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Online | [8 empty] | STA_342 Sudbury
NSTAR | South Truro | ESMAEX-02472 | 02666 | 17.82 | Solar | 4-96-669 | 2023-05-11 | 2023-06-09 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-09 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Marshfield | ESMAEX-02518 | 02050 | 20 | Solar & Battery | 3-25-42J2 | 2023-05-25 | 2023-06-06 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-19 | [7 empty] | 0 |  | 0 |  |  | 2023-09-13 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Carver | ESMAEX-02477 | 02330 | 14.976 | Solar | 3-51-980 | 2023-05-15 | 2023-06-02 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-08 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online |  |  |  | Plymouth |  |  |  |  | STA_727 Brook Street
NSTAR | Milton | ESMAEX-02654 | 02186 | 48 | Solar | 362-1209H2 | 2023-07-10 | 2023-08-14 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-21 | [7 empty] | 0 |  | 0 |  |  | 2024-10-21 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Duxbury | ESMAEX-02487 | 02332 | 15.2 | Solar | 3-26-26 | 2023-05-17 | 2023-05-31 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-05 | [7 empty] | 0 |  | 0 |  |  | 2023-09-27 | Online
NSTAR | Framingham | ESMAEX-02491 | 01701 | 17.1 | Solar | 342-H4 | 2023-05-18 | 2023-07-26 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-08 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Online | [8 empty] | STA_342 Sudbury
NSTAR | North Eastham | ESMAEX-02498 | 02651 | 82.01 | Solar | 4-94A-94A | 2023-05-19 | 2023-06-06 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-07 | [7 empty] | 0 |  | 0 |  |  | 2025-04-22 | Online | [8 empty] | STA_975 Orleans
NSTAR | Rochester | ESMAEX-02567 | 02770 | 15.3 | Solar | 3-703-703 | 2023-06-07 | 2023-07-11 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-31 | [7 empty] | 0 |  | 0 |  |  | 2024-09-12 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_745 Rochester
NSTAR | Medway | ESMAEX-02505 | 02053 | 17.6 | Solar | 65-H1 | 2023-05-22 | 2023-06-06 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-15 | Online | [7 empty] | 17.6 | STA_065 Medway
NSTAR | Bedford | ESMAEX-02555 | 01730 | 15.2 | Solar | 533-H8 | 2023-06-05 | 2023-06-30 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-07 | [7 empty] | 0 |  | 0 |  |  | 2024-01-12 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Acton | ESMAEX-02510 | 01720 | 17.1 | Solar | 416-H8 | 2023-05-23 | 2023-06-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-24 | [7 empty] | 0 |  | 0 |  |  | 2024-01-24 | Online | [8 empty] | STA_416 Maynard
NSTAR | Holliston | ESMAEX-02509 | 01746 | 15.36 | Solar | 274-H3 | 2023-05-23 | 2023-07-05 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-03 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Hopkinton | ESMAEX-02533 | 01748 | 15.2 | Solar & Battery | 126-H1 | 2023-05-26 | 2023-06-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-16 | [7 empty] | 0 |  | 0 |  |  | 2025-02-14 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Carver | ESMAEX-02592 | 02330 | 50 | Solar | 3-10-10 | 2023-06-16 | 2023-07-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2024-02-15 | Online |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Allston | ESMAEX-02602 | 02134 | 100 | Solar | 329-H5 | 2023-06-22 | 2023-07-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-03-19 | Online | [8 empty] | STA_329 Brighton
NSTAR | Medway | ESMAEX-02513 | 02053 | 18 | Solar | 65-H1 | 2023-05-24 | 2023-06-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-27 | [7 empty] | 0 |  | 0 |  |  | 2023-09-21 | Online | [7 empty] | 18 | STA_065 Medway
NSTAR | Acton | ESMAEX-02516 | 01720 | 15.2 | Solar & Battery | 416-H5 | 2023-05-24 | 2023-06-19 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-22 | [7 empty] | 0 |  | 0 |  |  | 2023-08-21 | Online | [8 empty] | STA_416 Maynard
NSTAR | Canton | ESMAEX-02587 | 02021 | 25.5 | Solar | 470-H9 | 2023-06-15 | 2023-07-11 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-22 | [7 empty] | 0 |  | 0 |  |  | 2024-09-25 | Online | [8 empty] | STA_470 Canton
NSTAR | Milton | ESMAEX-02558 | 02186 | 22.4 | Solar | 496-H7 | 2023-06-06 | 2023-06-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-29 | [7 empty] | 0 |  | 0 |  |  | 2023-10-03 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Canton | ESMAEX-02521 | 02021 | 15.2 | Solar | 470-H1 | 2023-05-25 | 2023-06-19 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-31 | [7 empty] | 0 |  | 0 |  |  | 2023-10-12 | Online | [7 empty] | 15.2 | STA_470 Canton
NSTAR | Dedham | ESMAEX-02526 | 02026 | 250 | Solar |  | 2023-07-06 | 2023-07-26 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | East Orleans | ESMAEX-02525 | 02643 | 6 | Solar | 4-628-628 | 2023-05-26 | 2023-06-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-14 | [7 empty] | 0 |  | 0 |  |  | 2023-09-20 | Online | [7 empty] | 6 | STA_975 Orleans
NSTAR | Dedham | ESMAEX-02527 | 02026 | 120 | Solar | 456-H4 | 2023-07-10 | 2023-07-25 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_456 Dover
NSTAR | Plymouth | ESMAEX-02612 | 02360 | 50 | Solar | 3-12-932 | 2023-06-23 | 2023-07-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-08-09 | Online |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Hopkinton | ESMAEX-02530 | 01748 | 22.8 | Solar & Battery | 126-H4 | 2023-05-26 | 2023-06-19 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-27 | [7 empty] | 0 |  | 0 |  |  | 2025-06-19 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Woburn | ESMAEX-02562 | 01801 | 200 | Solar | 211-H2 | 2023-06-06 | 2023-07-13 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-18 | [7 empty] | 0 |  | 0 |  |  | 2025-11-03 | Online | [8 empty] | STA_211 Woburn
NSTAR | Woburn | ESMAEX-02565 | 01801 | 150 | Solar | 211-H2 | 2023-06-07 | 2023-07-13 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-20 | [7 empty] | 0 |  | 0 |  |  | 2025-10-24 | Online | [8 empty] | STA_211 Woburn
NSTAR | Woburn | ESMAEX-02537 | 01801 | 10 | Battery | 211-H6 | 2023-05-30 | 2023-06-21 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2024-01-30 | Online | [7 empty] | 0 | STA_211 Woburn
NSTAR | Truro | ESMAEX-02539 | 02666 | 17.16 | Solar & Battery | 4-96-96 | 2023-05-30 | 2023-06-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-06-20 | [7 empty] | 0 |  | 0 |  |  | 2023-08-22 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Woburn | ESMAEX-02563 | 01801 | 240 | Solar | 211-H2 | 2023-06-06 | 2023-07-13 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  | 2025-10-24 | Online | [8 empty] | STA_211 Woburn
NSTAR | Woburn | ESMAEX-02564 | 01801 | 200 | Solar | 211-H2 | 2023-06-06 | 2023-07-13 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-20 | [7 empty] | 0 |  | 0 |  |  | 2025-12-04 | Online | [8 empty] | STA_211 Woburn
NSTAR | Medway | ESMAEX-02561 | 02053 | 200 | Solar | 65-H2 | 2023-06-06 | 2023-07-13 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-15 | [7 empty] | 0 |  | 0 |  |  | 2024-09-19 | Online | [8 empty] | STA_065 Medway
NSTAR | Canton | ESMAEX-02545 | 02021 | 16 | Solar | 470-H9 | 2023-06-01 | 2023-06-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2023-12-12 | Online | [8 empty] | STA_470 Canton
NSTAR | Lexington | ESMAEX-02544 | 02421 | 100 | Solar | 320-H5XY | 2023-07-07 | 2023-07-25 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-30 | [7 empty] | 0 |  | 0 |  |  | 2024-04-26 | Online | [8 empty] | STA_320 Lexington
NSTAR | Dedham | ESMAEX-02550 | 02026 | 200 | Solar | 20-H5 | 2023-06-02 | 2023-06-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-01 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_110 Baker Street
NSTAR | South Dartmouth | ESMAEX-02553 | 02748 | 20.1 | Solar | 2-528-528 | 2023-06-02 | 2023-07-11 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-31 | [7 empty] | 0 |  | 0 |  |  | 2023-10-19 | Online
NSTAR | Carlisle | ESMAEX-02569 | 01741 | 15.36 | Solar | 533-H8 | 2023-06-08 | 2023-07-21 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-15 | [7 empty] | 0 |  | 0 |  |  | 2023-10-16 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Dennisport | ESMAEX-02976 | 02639 | 18 | Solar | 4-92B-583 | 2023-09-28 | 2023-12-27 | 64 |  | 64 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-20 | [7 empty] | 0 |  | 0 |  |  | 2025-11-21 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Cambridge | ESMAEX-02674 | 02138 | 200 | Solar | 831-1332 | 2023-07-13 | 2023-08-04 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-07 | [7 empty] | 0 |  | 0 |  |  | 2026-02-13 | Online | [8 empty] | STA_831 Putnam
NSTAR | Stoneham | ESMAEX-02566 | 02180 | 20 | Solar | 375-H8 | 2023-06-07 | 2023-06-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2024-10-18 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Brighton | ESMAEX-02717 | 02135 | 200 | Solar | 467-H9 | 2023-07-26 | 2023-08-17 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2024-11-21 | Online | [8 empty] | STA_467 Watertown
NSTAR | Natick | ESMAEX-02581 | 01760 | 7.6 | Solar & Battery | 240-H3 | 2023-06-14 | 2023-07-07 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-13 | [7 empty] | 0 |  | 0 |  |  | 2024-04-23 | Online | [8 empty] | STA_240 Framingham
NSTAR | Dover | ESMAEX-02577 | 02030 | 7.6 | Solar & Battery | 456-H5 | 2023-06-12 | 2023-07-03 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-16 | Online | [8 empty] | STA_456 Dover
NSTAR | Burlington | ESMAEX-02572 | 01803 | 25.728 | Solar | 375-H6 | 2023-06-09 | 2023-07-11 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-05-08 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Rochester | ESMAEX-02576 | 02770 | 20 | Solar | 3-703-703 | 2023-06-12 | 2023-07-03 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-27 | [7 empty] | 0 |  | 0 |  |  | 2024-03-06 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_745 Rochester
NSTAR | Newton | ESMAEX-02600 | 02458 | 16 | Solar | 277-05 | 2023-06-21 | 2023-07-05 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-06 | Online | [8 empty] | STA_467 Watertown
NSTAR | Natick | ESMAEX-02579 | 01760 | 14 | Battery | 433-H5 | 2023-06-13 | 2023-07-13 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-17 | [7 empty] | 0 |  | 0 |  |  | 2024-05-20 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Marshfield | ESMAEX-02608 | 02050 | 10 | Battery | 3-25-25 | 2023-06-23 | 2023-07-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-19 | [7 empty] | 0 |  | 0 |  |  | 2024-06-07 | Online
NSTAR | Chestnut Hill | ESMAEX-02642 | 02467 | 100 | Solar | 292-H5 | 2023-07-06 | 2023-07-26 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-12 | [7 empty] | 0 |  | 0 |  |  |  | Permission to Operate | [8 empty] | STA_292 Newton Highlands
NSTAR | Chestnut Hill | ESMAEX-02646 | 02467 | 62.5 | Solar | 292-H5 | 2023-07-07 | 2023-07-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2025-12-31 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Chestnut Hill | ESMAEX-02586 | 02467 | 19 | Solar | 350-H7 | 2023-06-14 | 2023-07-07 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-11 | [7 empty] | 0 |  | 0 |  |  | 2023-10-17 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Needham | ESMAEX-02589 | 02494 | 15.2 | Solar | 148-H1 | 2023-06-16 | 2023-07-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Online | [8 empty] | STA_148 Needham
NSTAR | Westwood | ESMAEX-02676 | 02090 | 15.36 | Solar | 148-H3 | 2023-07-15 | 2023-08-22 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2023-11-08 | Online | [8 empty] | STA_148 Needham
NSTAR | Hopkinton | ESMAEX-02590 | 01748 | 19.968 | Solar | 126-H4 | 2023-06-16 | 2023-07-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-26 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Duxbury | ESMAEX-02595 | 02332 | 16.64 | Solar | 3-27-27 | 2023-06-20 | 2023-09-20 | 66 |  | 66 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_738 Duxbury
NSTAR | Marshfield | ESMAEX-02616 | 02050 | 19 | Solar | 3-24B-915 | 2023-06-26 | 2023-07-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-25 | [7 empty] | 0 |  | 0 |  |  | 2024-02-12 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Lexington | ESMAEX-02596 | 02420 | 25 | Solar | 533-H9 | 2023-06-20 | 2023-07-05 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-01 | [7 empty] | 0 |  | 0 |  |  | 2024-05-13 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Cambridge | ESMAEX-02718 | 02138 | 60 | Solar |  | 2023-07-26 | 2023-08-17 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-24 | [7 empty] | 0 |  | 0 |  |  | 2025-04-18 | Online
NSTAR | Boston | ESMAEX-02755 | 02115 | 120 | Solar | 452-1401 | 2023-08-04 | 2023-08-24 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-08 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Wayland | ESMAEX-02601 | 01778 | 20 | Solar | 342-H1 | 2023-06-22 | 2023-07-05 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-11 | Online | [8 empty] | STA_342 Sudbury
NSTAR | East Wareham | ESMAEX-02609 | 02538 | 10 | Battery | 3-82-82 | 2023-06-23 | 2023-07-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-21 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Online |  |  |  | Plymouth |  |  |  |  | STA_714 Wareham
NSTAR | Medfield | ESMAEX-02607 | 02052 | 30 | Solar | 456-H3 | 2023-06-23 | 2023-07-13 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-16 | [7 empty] | 0 |  | 0 |  |  | 2023-12-28 | Online | [8 empty] | STA_456 Dover
NSTAR | Hopkinton | ESMAEX-02615 | 01748 | 15.2 | Solar & Battery | 126-H2 | 2023-06-26 | 2023-07-20 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-20 | [7 empty] | 0 |  | 0 |  |  | 2023-10-18 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Sharon | ESMAEX-02618 | 02067 | 3.9 | Solar | 470-H12 | 2023-06-27 | 2023-08-09 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-20 | [7 empty] | 0 |  | 0 |  |  | 2024-03-25 | Online | [7 empty] | 0 | STA_470 Canton
NSTAR | West Wareham | ESMAEX-02629 | 02576 | 10 | Solar | 3-86-966 | 2023-06-29 | 2023-07-20 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-24 | [7 empty] | 0 |  | 0 |  |  | 2024-01-18 | Online |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | Cambridge | ESMAEX-02620 | 02139 | 7.6 | Solar | 817-01 | 2023-06-27 | 2023-06-27 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-07 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Online | [8 empty] | STA_831 Putnam
NSTAR | Holliston | ESMAEX-02636 | 01746 | 11.712 | Solar & Battery | 274-H3 | 2023-07-05 | 2023-07-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-18 | [7 empty] | 0 |  | 0 |  |  | 2024-02-02 | Online | [8 empty] | STA_274 Sherborn
NSTAR | South Chatham | ESMAEX-02644 | 02659 | 10 | Battery | 4-95A-95A | 2023-07-07 | 2023-07-25 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-29 | Online | [8 empty] | STA_968 Harwich
NSTAR | Weston | ESMAEX-02628 | 02493 | 19.72 | Solar | 282-H10 | 2023-06-29 | 2023-07-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-29 | [7 empty] | 0 |  | 0 |  |  | 2023-11-10 | Online | [8 empty] | STA_282 Waltham
NSTAR | Canton | ESMAEX-02627 | 02021 | 18.1 | Solar & Battery | 269-1320H1 | 2023-06-28 | 2023-07-18 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-28 | [7 empty] | 0 |  | 0 |  |  | 2023-09-28 | Online | [8 empty] | STA_470 Canton
NSTAR | Bedford | ESMAEX-02635 | 01730 | 196.99 | Solar | 533-H3 | 2023-06-30 | 2023-07-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-23 | [7 empty] | 0 |  | 0 |  |  | 2024-11-21 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Westwood | ESMAEX-02633 | 02090 | 13.056 | Solar | 456-H4 | 2023-06-30 | 2023-07-20 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-21 | Online | [8 empty] | STA_456 Dover
NSTAR | East Walpole | ESMAEX-02657 | 02032 | 15.2 | Solar | 146-H4 | 2023-07-10 | 2023-07-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-27 | [7 empty] | 0 |  | 0 |  |  | 2023-10-13 | Online | [8 empty] | STA_146 Walpole
NSTAR | Carlisle | ESMAEX-02745 | 01741 | 16 | Solar | 512-1399H1 | 2023-08-02 | 2023-08-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-20 | [7 empty] | 0 |  | 0 |  |  | 2024-01-12 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Rochester | ESMAEX-03936 | 02770 | 20 | Solar | 3-703-703 | 2024-07-30 | 2024-08-13 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-09-04 | Technical Review |  |  |  | Marion-Fairhaven |  |  |  |  | STA_745 Rochester
NSTAR | Lexington | ESMAEX-02875 | 02421 | 19.8 | Solar | 320-H2 | 2023-08-29 | 2023-10-16 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-05-10 | Online | [8 empty] | STA_320 Lexington
NSTAR | North Dartmouth | ESMAEX-02645 | 02747 | 200 | Solar | 2-541-541 | 2023-10-06 | 2023-10-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-14 | [7 empty] | 0 |  | 0 |  |  |  | Meter |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Framingham | ESMAEX-02648 | 01702 | 15.2 | Solar | 455-H3 | 2023-07-07 | 2023-07-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-07-28 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Mashpee | ESMAEX-02660 | 02649 | 50 | Solar | 4-77A-456 | 2023-07-11 | 2023-08-14 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-21 | [7 empty] | 0 |  | 0 |  |  | 2025-11-13 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Arlington | ESMAEX-02707 | 02476 | 150 | Solar |  | 2023-07-24 | 2023-08-23 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-12 | [7 empty] | 0 |  | 0 |  |  | 2025-11-24 | Online
NSTAR | Norfolk | ESMAEX-02658 | 02056 | 140 | Solar | 146-H3 | 2023-07-28 | 2023-08-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-27 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Online | [8 empty] | STA_146 Walpole
NSTAR | Mashpee | ESMAEX-02671 | 02649 | 50 | Solar | 4-77A-456 | 2023-07-13 | 2023-08-14 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  | 2025-09-22 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Arlington | ESMAEX-02664 | 02476 | 4.39 | Solar | 211-H11 | 2023-07-12 | 2023-07-25 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-07 | Online | [8 empty] | STA_211 Woburn
NSTAR | Winchester | ESMAEX-02667 | 01890 | 15.2 | Solar & Battery | 211-H11 | 2023-07-13 | 2023-07-26 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2025-04-23 | Online | [8 empty] | STA_211 Woburn
NSTAR | Brookline | ESMAEX-02678 | 02445 | 200 | Solar | 350-H7 | 2023-07-17 | 2023-08-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-22 | [7 empty] | 0 |  | 0 |  |  | 2024-06-20 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Arlington | ESMAEX-02686 | 02474 | 20 | Solar | 59-1383H1 | 2023-07-18 | 2023-08-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-07-26 | Online | [8 empty] | STA_211 Woburn
NSTAR | Stoneham | ESMAEX-02677 | 02180 | 180 | Solar | 375-H2 | 2023-07-17 | 2023-08-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_375 Dragon Court
NSTAR | Winchester | ESMAEX-02690 | 01890 | 15.2 | Solar & Battery | 211-H11 | 2023-07-19 | 2023-09-20 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-10 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Online | [8 empty] | STA_211 Woburn
NSTAR | Sandwich | ESMAEX-02681 | 02563 | 200 | Solar | 4-81A-81A | 2023-07-17 | 2023-08-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-08 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  | 200 | STA_915 Otis
NSTAR | Westwood | ESMAEX-02680 | 02090 | 17.28 | Solar | 456-H4 | 2023-07-17 | 2023-08-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online | [8 empty] | STA_456 Dover
NSTAR | Dorchester | ESMAEX-02751 | 02122 | 10 | Battery | 511-1498H1 | 2023-08-04 | 2023-08-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-31 | [7 empty] | 0 |  | 0 |  |  | 2024-01-04 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Wellfleet | ESMAEX-02803 | 02667 | 17.4 | Battery | 4-94B-94B | 2023-10-27 | 2023-09-06 | -39 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-29 | [7 empty] | 0 |  | 0 |  |  | 2025-01-09 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Lincoln | ESMAEX-02827 | 01773 | 25.8 | Solar & Battery | 320-H6 | 2023-08-17 | 2023-09-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-22 | [7 empty] | 0 |  | 0 |  |  | 2024-03-18 | Online | [8 empty] | STA_320 Lexington
NSTAR | Needham | ESMAEX-02783 | 02492 | 15.2 | Solar | 148-H4 | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-08-23 | Online | [8 empty] | STA_148 Needham
NSTAR | Burlington | ESMAEX-02687 | 01803 | 17.4 | Solar | 391-H6 | 2023-07-19 | 2023-08-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-14 | [7 empty] | 0 |  | 0 |  |  | 2023-12-11 | Online | [8 empty] | STA_391 Burlington
NSTAR | West Newton | ESMAEX-02688 | 02465 | 16 | Solar | 316-05 | 2023-07-19 | 2023-08-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Online | [7 empty] | 16 | STA_282 Waltham
NSTAR | Duxbury | ESMAEX-02693 | 02332 | 19 | Solar | 3-24B-24B | 2023-07-20 | 2023-08-04 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-10 | [7 empty] | 0 |  | 0 |  |  | 2024-03-21 | Online | [7 empty] | 19 | STA_738 Duxbury
NSTAR | Lexington | ESMAEX-02703 | 02420 | 15.2 | Solar | 533-H9 | 2023-07-21 | 2023-08-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-26 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Burlington | ESMAEX-03180 | 01803 | 240 | Solar | 391-H16 | 2023-11-20 | 2023-12-18 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Online | [8 empty] | STA_391 Burlington
NSTAR | Westwood | ESMAEX-02705 | 02090 | 15.2 | Solar | 148-H3 | 2023-07-24 | 2023-08-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-19 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Online | [8 empty] | STA_148 Needham
NSTAR | Medway | ESMAEX-02825 | 02341 | 27.3 | Solar | 65-H2 | 2023-08-16 | 2023-09-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-25 | [7 empty] | 0 |  | 0 |  |  | 2025-02-24 | Online | [8 empty] | STA_065 Medway
NSTAR | Boston | ESMAEX-03169 | 02119 | 67.3 | Solar | 396-1050H4 | 2023-11-17 | 2024-01-31 | 53 |  | 53 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-18 | [7 empty] | 0 |  | 0 |  |  |  | Permission to Operate | [8 empty] | STA_350 Colburn Street
NSTAR | Burlington | ESMAEX-02781 | 01803 | 15.68 | Solar | 346-1395H1 | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-10 | [7 empty] | 0 |  | 0 |  |  | 2023-12-04 | Online | [8 empty] | STA_391 Burlington
NSTAR | Medway | ESMAEX-02824 | 02053 | 50 | Solar | 65-H2 | 2023-08-16 | 2023-09-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-23 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [8 empty] | STA_065 Medway
NSTAR | Carlisle | ESMAEX-02813 | 01741 | 7.8 | Solar & Battery | 512-1399H1 | 2023-08-15 | 2023-09-25 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-06 | [7 empty] | 0 |  | 0 |  |  | 2024-06-24 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Kingston | ESMAEX-02711 | 02364 | 18.3 | Solar | 3-18-18 | 2023-07-26 | 2023-08-17 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth
NSTAR | Ashland | ESMAEX-02740 | 01721 | 200 | Solar | 274-H1 | 2023-08-01 | 2023-08-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-02 | [7 empty] | 0 |  | 0 |  |  | 2024-08-27 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Chatham | ESMAEX-02734 | 02633 | 19.14 | Solar | 4-95B-95B | 2023-08-01 | 2023-08-24 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-17 | [7 empty] | 0 |  | 0 |  |  | 2025-02-12 | Online | [8 empty] | STA_975 Orleans
NSTAR | Needham | ESMAEX-02722 | 02492 | 20.2 | Solar & Battery | 148-02 | 2023-07-28 | 2023-08-22 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-10 | [7 empty] | 0 |  | 0 |  |  | 2024-07-11 | Online | [8 empty] | STA_148 Needham
NSTAR | Winchester | ESMAEX-02730 | 01890 | 200 | Fuel Cell | 211-H1 | 2023-07-31 | 2023-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_211 Woburn
NSTAR | Burlington | ESMAEX-02733 | 01803 | 1500 | Fuel Cell | 391-H13 | 2023-07-31 | 2023-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_391 Burlington
NSTAR | Hyannis | ESMAEX-02732 | 02601 | 200 | Fuel Cell | 4-63-521 | 2023-07-31 | 2023-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-01 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Cambridge | ESMAEX-02731 | 02138 | 550 | Fuel Cell | 819-1NB5 | 2023-07-31 | 2023-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_402 Newton Street
NSTAR | Arlington | ESMAEX-02744 | 02474 | 13 | Solar & Battery | 211-H11 | 2023-08-01 | 2023-08-22 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-17 | [7 empty] | 0 |  | 0 |  |  | 2024-04-19 | Online | [8 empty] | STA_211 Woburn
NSTAR | Sharon | ESMAEX-02724 | 02067 | 15.2 | Solar | 146-H8 | 2023-07-28 | 2023-08-24 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-07 | [7 empty] | 0 |  | 0 |  |  | 2024-04-23 | Online | [8 empty] | STA_146 Walpole
NSTAR | Jamaica Plain | ESMAEX-02726 | 02130 | 10 | Battery | 284-07 | 2023-07-30 | 2023-08-17 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-08-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 0 | STA_350 Colburn Street
NSTAR | Dover | ESMAEX-02728 | 02030 | 10 | Battery | 456-H3 | 2023-07-31 | 2023-08-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-05 | [7 empty] | 0 |  | 0 |  |  | 2023-11-15 | Online | [7 empty] | 0 | STA_456 Dover
NSTAR | Lincoln | ESMAEX-02729 | 01773 | 699.3 | Solar | 320-H6 | 2023-11-01 | 2024-01-10 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-08 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_320 Lexington
NSTAR | Boston | ESMAEX-04016 | 02210 | 80 | Solar | 99-H2 | 2024-08-29 | 2024-10-10 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [8 empty] | STA_099 Seafood Way
NSTAR | Millis | ESMAEX-02772 | 02054 | 17.28 | Battery | 65-H1 | 2023-08-08 | 2023-08-31 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-06 | [7 empty] | 0 |  | 0 |  |  | 2024-02-06 | Online | [8 empty] | STA_065 Medway
NSTAR | Cambridge | ESMAEX-03392 | 02139 | 30 | Solar | 816-04 | 2024-01-29 | 2024-02-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-21 | [7 empty] | 0 |  | 0 |  |  | 2025-04-03 | Online | [8 empty] | STA_831 Putnam
NSTAR | Holliston | ESMAEX-02739 | 01746 | 480 | Solar | 274-H1 | 2023-09-01 | 2023-09-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Lincoln | ESMAEX-02747 | 01773 | 15.2 | Solar & Battery | 320-H8 | 2023-08-02 | 2023-08-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Online | [8 empty] | STA_320 Lexington
NSTAR | Sharon | ESMAEX-03046 | 02067 | 15.2 | Solar & Battery | 470-H12 | 2023-10-12 | 2023-10-31 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-01 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online | [8 empty] | STA_470 Canton
NSTAR | Framingham | ESMAEX-02919 | 01701 | 60 | Solar | 433-H4 | 2023-09-14 | 2023-09-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  | 2024-03-06 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Needham | ESMAEX-02779 | 02492 | 200 | Fuel Cell | 148-03 | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-17 | [7 empty] | 0 |  | 0 |  |  | 2025-07-02 | Online | [8 empty] | STA_148 Needham
NSTAR | Dover | ESMAEX-02746 | 02030 | 15.2 | Solar | 456-H5 | 2023-08-02 | 2023-08-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  | 2023-11-28 | Online | [8 empty] | STA_456 Dover
NSTAR | Newton Center | ESMAEX-02760 | 02459 | 8.7 | Solar & Battery | 369-06 | 2023-08-07 | 2023-08-30 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-26 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-02748 | 02420 | 19 | Solar | 351-01 | 2023-08-03 | 2023-08-28 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Technical Review | [8 empty] | STA_351 East Lexington
NSTAR | East Freetown | ESMAEX-02750 | 02717 | 15.744 | Solar | 2-108-108 | 2023-08-03 | 2023-08-28 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-02 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | East Cambridge | ESMAEX-02775 | 02141 | 1550 | Fuel Cell | 875-1N23B | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_875 East Cambridge
NSTAR | Burlington | ESMAEX-02777 | 01803 | 200 | Fuel Cell | 391-H6 | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  | 2025-12-17 | Online | [8 empty] | STA_391 Burlington
NSTAR | Newtonville | ESMAEX-02776 | 02460 | 200 | Fuel Cell | 467-H3 | 2023-08-09 | 2023-08-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_467 Watertown
NSTAR | Walpole | ESMAEX-02761 | 02081 | 15.2 | Solar & Battery | 146-H4 | 2023-08-07 | 2023-09-06 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-10 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [8 empty] | STA_146 Walpole
NSTAR | Hopkinton | ESMAEX-02857 | 01748 | 15.2 | Solar | 455-H8 | 2023-08-23 | 2023-09-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-21 | [7 empty] | 0 |  | 0 |  |  | 2024-07-31 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Acton | ESMAEX-02796 | 01720 | 19.39 | Solar | 416-H5 | 2023-08-11 | 2023-08-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2023-11-13 | Online | [8 empty] | STA_416 Maynard
NSTAR | Carlisle | ESMAEX-02762 | 01741 | 17.1 | Solar | 512-1399H1 | 2023-08-07 | 2023-09-20 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-09 | [7 empty] | 0 |  | 0 |  |  | 2024-03-18 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Brookline | ESMAEX-02771 | 02446 | 15.36 | Solar | 315-H8 | 2023-08-08 | 2023-09-08 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-11 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online
NSTAR | Newtonville | ESMAEX-02784 | 02460 | 200 | Fuel Cell | 467-H3 | 2023-08-10 | 2023-08-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_467 Watertown
NSTAR | Needham | ESMAEX-02807 | 02494 | 9.6 | Solar & Battery | 148-H4 | 2023-08-14 | 2023-09-08 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-03-13 | Online | [8 empty] | STA_148 Needham
NSTAR | Sherborn | ESMAEX-02805 | 01770 | 20 | Solar | 456-H5 | 2023-08-14 | 2023-09-08 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-12 | [7 empty] | 0 |  | 0 |  |  | 2024-01-29 | Technical Review | [8 empty] | STA_456 Dover
NSTAR | Holliston | ESMAEX-02786 | 01746 | 10 | Solar & Battery | 130-H1 | 2023-08-10 | 2023-08-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  | 2024-05-21 | Online | [8 empty] | STA_130 Holliston
NSTAR | Weston | ESMAEX-02793 | 02493 | 15.2 | Solar | 282-H10 | 2023-08-10 | 2023-08-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-05-06 | Online | [8 empty] | STA_282 Waltham
NSTAR | Hopkinton | ESMAEX-02800 | 01748 | 15.2 | Solar & Battery | 126-H4 | 2023-08-11 | 2023-08-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-04 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Lexington | ESMAEX-02879 | 02420 | 15.2 | Solar & Battery | 533-H9 | 2023-08-31 | 2023-09-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Framingham | ESMAEX-02801 | 01701 | 10 | Battery | 342-H9 | 2023-08-11 | 2023-08-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-13 | [7 empty] | 0 |  | 0 |  |  | 2024-03-22 | Online | [7 empty] | 0 | STA_342 Sudbury
NSTAR | Waltham | ESMAEX-02802 | 02451 | 5 | Battery | 450-H1 | 2023-08-11 | 2023-08-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Online | [7 empty] | 0 | STA_450 Trapelo Road
NSTAR | Sharon | ESMAEX-02810 | 02067 | 15.2 | Solar & Battery | 146-H1 | 2023-08-14 | 2023-09-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-05 | Online | [8 empty] | STA_146 Walpole
NSTAR | Norfolk | ESMAEX-02831 | 02056 | 15.2 | Solar | 146-H10 | 2023-08-17 | 2023-09-11 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-11 | [7 empty] | 0 |  | 0 |  |  | 2024-03-29 | Online | [8 empty] | STA_146 Walpole
NSTAR | Lincoln | ESMAEX-02816 | 01773 | 15 | Solar & Battery | 282-H1 | 2023-08-15 | 2023-08-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-11 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Online | [8 empty] | STA_282 Waltham
NSTAR | West Roxbury | ESMAEX-02817 | 02132 | 18.88 | Solar | 496-H6 | 2023-08-15 | 2023-08-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-06 | [7 empty] | 0 |  | 0 |  |  | 2024-02-18 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Canton | ESMAEX-02820 | 02021 | 10.368 | Solar | 269-1321H2 | 2023-08-16 | 2023-10-06 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-02 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Online | [8 empty] | STA_470 Canton
NSTAR | Hopkinton | ESMAEX-02832 | 01748 | 120 | Solar | 126-H2 | 2023-08-18 | 2023-09-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-02 | [7 empty] | 0 |  | 0 |  |  | 2024-09-17 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Weston | ESMAEX-02842 | 02493 | 19 | Solar | 342-H1 | 2023-08-18 | 2023-09-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-09-10 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Norfolk | ESMAEX-02844 | 02056 | 15.2 | Solar & Battery | 65-H1 | 2023-08-18 | 2023-09-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2024-10-17 | Online | [8 empty] | STA_065 Medway
NSTAR | Newton | ESMAEX-03544 | 02459 | 20 | Solar | 1701 | 2024-03-18 | 2024-04-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-30 | [7 empty] | 0 |  | 0 |  |  | 2025-12-31 | Permission to Operate | [7 empty] | 19.9 | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-02850 | 02420 | 15.2 | Solar | 533-H9 | 2023-08-21 | 2023-09-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-01-10 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Framingham | ESMAEX-02848 | 01701 | 7.6 | Solar | 433-H3 | 2023-08-21 | 2023-09-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-10 | [7 empty] | 0 |  | 0 |  |  | 2024-07-17 | Online | [7 empty] | 7.6 | STA_433 Speen Street
NSTAR | Burlington | ESMAEX-02851 | 01803 | 17.6 | Solar | 391-H7 | 2023-08-22 | 2023-09-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-24 | [7 empty] | 0 |  | 0 |  |  | 2024-02-21 | Online | [7 empty] | 20 | STA_391 Burlington
NSTAR | Auburndale | ESMAEX-02860 | 02466 | 5 | Battery | 292-H7 | 2023-08-23 | 2023-09-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-10 | [7 empty] | 0 |  | 0 |  |  | 2024-03-22 | Online | [7 empty] | 0 | STA_292 Newton Highlands
NSTAR | Dedham | ESMAEX-02865 | 02026 | 60 | Solar |  | 2023-08-25 | 2023-09-26 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2025-05-08 | Online
NSTAR | Wayland | ESMAEX-02868 | 01778 | 17.1 | Solar | 342-H1 | 2023-08-25 | 2023-09-12 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-01-31 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Carlisle | ESMAEX-02931 | 01741 | 19.8 | Solar | 512-1399H1 | 2023-09-18 | 2023-10-02 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-16 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | East Boston | ESMAEX-03210 | 02128 | 60 | Solar | 488-H8 | 2023-12-01 | 2023-12-27 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-28 | [7 empty] | 0 |  | 0 |  |  | 2024-10-29 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Natick | ESMAEX-02873 | 01760 | 13.05 | Solar | 240-H1 | 2023-08-28 | 2023-09-19 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-18 | Online | [8 empty] | STA_240 Framingham
NSTAR | Burlington | ESMAEX-02884 | 01803 | 16.8 | Solar | 346-1395H1 | 2023-09-01 | 2023-10-23 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-03-07 | Online | [8 empty] | STA_391 Burlington
NSTAR | Needham | ESMAEX-02980 | 02492 | 19.8 | Solar & Battery | 148-H1 | 2023-09-28 | 2023-10-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-14 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online | [7 empty] | 20 | STA_148 Needham
NSTAR | Framingham | ESMAEX-02877 | 01702 | 20 | Solar | 240-H6 | 2023-08-29 | 2023-09-20 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2024-05-16 | Online | [8 empty] | STA_240 Framingham
NSTAR | Framingham | ESMAEX-02932 | 01701 | 15.2 | Solar | 433-H8 | 2023-09-19 | 2023-10-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-10-20 | Online | [7 empty] | 13.62 | STA_433 Speen Street
NSTAR | Wayland | ESMAEX-02896 | 01778 | 15.2 | Solar | 342-H1 | 2023-09-07 | 2023-09-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-03 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Boston | ESMAEX-03020 | 02210 | 300 | Solar | 99-H2 | 2023-10-04 | 2023-12-07 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-26 | [7 empty] | 0 |  | 0 |  |  |  | Online | [8 empty] | STA_099 Seafood Way
NSTAR | East Walpole | ESMAEX-03053 | 02032 | 15.2 | Solar | 146-H4 | 2023-10-16 | 2023-11-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-10 | [7 empty] | 0 |  | 0 |  |  | 2024-10-20 | Online | [8 empty] | STA_146 Walpole
NSTAR | Acusnet | ESMAEX-02898 | 02743 | 1.5 | Solar & Battery | 2-230-230 | 2023-09-08 | 2023-09-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-09-28 | [7 empty] | 0 |  | 0 |  |  | 2024-02-01 | Online | [8 empty] | STA_612 Acushnet
NSTAR | Hopkinton | ESMAEX-02905 | 01748 | 199 | Solar | 126-H2 | 2023-09-11 | 2023-09-25 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-19 | [7 empty] | 0 |  | 0 |  |  |  | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Westwood | ESMAEX-03061 | 02090 | 10 | Battery | 148-H3 | 2023-10-17 | 2023-11-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-07 | [7 empty] | 0 |  | 0 |  |  | 2024-09-17 | Online | [8 empty] | STA_148 Needham
NSTAR | North Dartmouth | ESMAEX-02929 | 02747 | 15.2 | Solar | 2-70-502 | 2023-09-18 | 2023-10-02 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-06-13 | Online
NSTAR | Holliston | ESMAEX-02911 | 01746 | 20 | Solar & Battery | 130-H2 | 2023-09-12 | 2023-09-19 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Online | [8 empty] | STA_130 Holliston
NSTAR | East Walpole | ESMAEX-02934 | 02032 | 15.2 | Solar | 146-H4 | 2023-09-19 | 2023-10-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-13 | [7 empty] | 0 |  | 0 |  |  | 2024-07-12 | Online | [8 empty] | STA_146 Walpole
NSTAR | Milton | ESMAEX-02909 | 02186 | 16.53 | Solar & Battery | 496-H7 | 2023-09-12 | 2023-09-26 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-03-26 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Waltham | ESMAEX-02936 | 02452 | 15.2 | Solar | 450-H4 | 2023-09-19 | 2023-10-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-03-12 | Online | [8 empty] | STA_450 Trapelo Road
NSTAR | Falmouth | ESMAEX-02922 | 02540 | 15 | Battery | 4-72-72 | 2023-09-15 | 2023-09-26 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2025-06-20 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Framingham | ESMAEX-03028 | 01701 | 10 | Battery | 278-H2 | 2023-10-06 | 2023-10-30 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-19 | [7 empty] | 0 |  | 0 |  |  | 2024-01-26 | Online | [8 empty] | STA_278 Saxonville
NSTAR | Westwood | ESMAEX-02926 | 02090 | 10 | Battery | 469-H2 | 2023-09-15 | 2023-10-16 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-06-07 | Online
NSTAR | Sharon | ESMAEX-02920 | 02067 | 15.04 | Solar | 146-H7 | 2023-09-14 | 2023-10-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-06 | [7 empty] | 0 |  | 0 |  |  | 2024-01-30 | Online | [8 empty] | STA_146 Walpole
NSTAR | Dover | ESMAEX-02930 | 02030 | 5 | Battery | 456-H5 | 2023-09-18 | 2023-10-20 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-12 | [7 empty] | 0 |  | 0 |  |  | 2024-08-28 | Online | [8 empty] | STA_456 Dover
NSTAR | Duxbury | ESMAEX-03167 | 02332 | 30 | Solar | 3-23-23 | 2023-11-17 | 2023-12-04 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-10 | [7 empty] | 0 |  | 0 |  |  | 2024-04-30 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Walpole | ESMAEX-02955 | 02081 | 15.2 | Solar | 146-H6 | 2023-09-26 | 2023-10-12 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-14 | [7 empty] | 0 |  | 0 |  |  | 2024-03-26 | Online | [8 empty] | STA_146 Walpole
NSTAR | Cambridge | ESMAEX-03044 | 02140 | 300 | Solar | 828-1NC8 | 2023-11-08 | 2023-11-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-11 | [7 empty] | 0 |  | 0 |  |  | 2025-11-06 | Online | [8 empty] | STA_828 Alewife
NSTAR | Duxbury | ESMAEX-02921 | 02332 | 14 | Battery | 3-24B-24B | 2023-09-15 | 2023-12-04 | 56 |  | 56 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-06 | [7 empty] | 0 |  | 0 |  |  | 2024-11-27 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Fairhaven | ESMAEX-02923 | 02719 | 15 | Battery | 2-230-230 | 2023-09-15 | 2023-10-12 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2024-05-19 | Online | [8 empty] | STA_612 Acushnet
NSTAR | Hopkinton | ESMAEX-02925 | 01748 | 11.4 | Solar | 274-H5 | 2023-09-15 | 2023-09-26 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-25 | [7 empty] | 0 |  | 0 |  |  | 2024-04-26 | Online | [7 empty] | 11.4 | STA_274 Sherborn
NSTAR | Canton | ESMAEX-02959 | 02021 | 15.2 | Solar & Battery | 269-1321H2 | 2023-09-26 | 2023-10-30 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-30 | [7 empty] | 0 |  | 0 |  |  | 2024-10-30 | Online | [8 empty] | STA_470 Canton
NSTAR | Roxbury | ESMAEX-03017 | 02119 | 20 | Solar | 143-151H1 | 2023-10-04 | 2023-11-15 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-14 | [7 empty] | 0 |  | 0 |  |  | 2025-08-25 | Online | [7 empty] | 0 | STA_106 Andrew Square
NSTAR | Westwood | ESMAEX-02933 | 02090 | 19.968 | Solar | 148-H3 | 2023-09-19 | 2023-10-06 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-07 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Online | [8 empty] | STA_148 Needham
NSTAR | Plymouth | ESMAEX-02947 | 02360 | 77.3 | Solar | 3-13-943 | 2023-09-22 | 2024-08-15 | 234 |  | 234 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Dover | ESMAEX-03003 | 02030 | 16.2 | Solar | 456-H3 | 2023-10-03 | 2023-10-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-25 | [7 empty] | 0 |  | 0 |  |  | 2024-03-28 | Online | [8 empty] | STA_456 Dover
NSTAR | Charlestown | ESMAEX-02954 | 02129 | 80 | Solar | 218-80H | 2023-09-25 | 2023-10-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-16 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Online | [8 empty] | STA_250 Mystic
NSTAR | Natick | ESMAEX-02998 | 01760 | 15.2 | Solar | 433-H7 | 2023-10-02 | 2023-10-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Burlington | ESMAEX-02951 | 01803 | 66.6 | Solar | 375-H6 | 2023-09-22 | 2023-10-10 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-13 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Lincoln | ESMAEX-02995 | 01773 | 3.8 | Solar & Battery | 320-H6 | 2023-10-02 | 2023-10-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Online | [8 empty] | STA_320 Lexington
NSTAR | Walpole | ESMAEX-02997 | 02081 | 7.6 | Solar | 146-H4 | 2023-10-02 | 2023-10-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-02 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [8 empty] | STA_146 Walpole
NSTAR | Needham | ESMAEX-02991 | 02492 | 20.1 | Solar | 148-01 | 2023-09-29 | 2023-10-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-02-22 | Online | [8 empty] | STA_148 Needham
NSTAR | Waltham | ESMAEX-02956 | 02453 | 10 | Solar | 467-H5 | 2023-09-26 | 2023-10-12 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-06 | Online | [8 empty] | STA_467 Watertown
NSTAR | Edgartown | ESMAEX-03023 | 02539 | 400 | Battery | 4-75-75 | 2023-10-25 | 2024-01-03 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-07 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  | 400 | STA_933 Falmouth
NSTAR | Winchester | ESMAEX-03063 | 01890 | 72.2 | Solar | 211-H11 | 2023-10-18 | 2023-10-31 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-09 | [7 empty] | 0 |  | 0 |  |  | 2024-06-20 | Online | [8 empty] | STA_211 Woburn
NSTAR | Watertown | ESMAEX-02986 | 02472 | 16.47 | Solar | 467-H8 | 2023-09-29 | 2023-10-19 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-05-10 | Online | [8 empty] | STA_467 Watertown
NSTAR | Ashland | ESMAEX-02960 | 01721 | 10 | Solar | 519-175H1 | 2023-09-26 | 2023-10-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-26 | [7 empty] | 0 |  | 0 |  |  | 2025-10-27 | Online | [7 empty] | 10 | STA_274 Sherborn
NSTAR | Brookline | ESMAEX-02973 | 02467 | 35 | Internal Combustion Engine |  | 2023-09-27 | 2023-10-23 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Framingham | ESMAEX-02985 | 01702 | 250 | Solar | 240-H3 | 2023-10-27 | 2023-11-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2025-12-05 | Online | [7 empty] | 250 | STA_240 Framingham
NSTAR | Cambridge | ESMAEX-03070 | 02138 | 12.3 | Solar & Battery | 817-09 | 2023-10-19 | 2023-12-18 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Online | [8 empty] | STA_831 Putnam
NSTAR | Chelsea | ESMAEX-03001 | 02150 | 30.4 | Solar | 488-H6 | 2023-10-02 | 2023-11-13 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-06-05 | Online | [8 empty] | STA_488 Chelsea
NSTAR | East Freetown | ESMAEX-02989 | 02717 | 10 | Solar | 2-108-108 | 2023-09-29 | 2023-10-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-03 | [7 empty] | 0 |  | 0 |  |  | 2024-08-02 | Online |  |  |  | Cape |  |  |  | 10 | STA_636 Industrial Park
NSTAR | New Bedford | ESMAEX-02994 | 02745 | 999 | Solar & Battery | 2-151-151 | 2023-09-29 | 2023-10-17 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | New Bedford | Hold In Queue |  |  | 999 | STA_636 Industrial Park
NSTAR | Burlington | ESMAEX-02999 | 01803 | 15.8 | Solar | 391-H7 | 2023-10-02 | 2023-10-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-04-18 | Online | [7 empty] | 15.8 | STA_391 Burlington
NSTAR | Natick | ESMAEX-03007 | 01760 | 17.28 | Solar | 240-H1 | 2023-10-03 | 2023-10-24 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-30 | [7 empty] | 0 |  | 0 |  |  | 2024-02-23 | Online | [8 empty] | STA_240 Framingham
NSTAR | Boston | ESMAEX-03016 | 02210 | 999 | Solar & Battery | 151-140H | 2023-12-22 | 2024-01-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 999 | STA_385D K Street
NSTAR | Newtonville | ESMAEX-03021 | 02460 | 20 | Solar & Battery | 277-04 | 2023-10-04 | 2023-10-24 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Technical Review | [8 empty] | STA_467 Watertown
NSTAR | Jamaica Plain | ESMAEX-03407 | 02130 | 15 | Battery | 496-H4 | 2024-02-01 | 2024-02-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-01 | [7 empty] | 0 |  | 0 |  |  | 2024-11-04 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Sharon | ESMAEX-03027 | 02067 | 15.2 | Solar & Battery | 146-H7 | 2023-10-05 | 2023-10-25 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-10-26 | [7 empty] | 0 |  | 0 |  |  | 2024-03-15 | Online | [8 empty] | STA_146 Walpole
NSTAR | Cambridge | ESMAEX-03030 | 02139 | 487.5 | Solar | 828-1369 | 2023-10-06 | 2023-10-30 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  | 2026-01-28 | Online | [8 empty] | STA_828 Alewife
NSTAR | Cambridge | ESMAEX-03029 | 02139 | 375 | Solar | 828-1370 | 2023-10-06 | 2023-10-30 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  | 2026-01-28 | Online | [8 empty] | STA_828 Alewife
NSTAR | Arlington | ESMAEX-03265 | 02474 | 21.66 | Solar & Battery | 211-H11 | 2023-12-12 | 2024-01-29 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-22 | [7 empty] | 0 |  | 0 |  |  | 2024-06-07 | Online | [7 empty] | 10 | STA_211 Woburn
NSTAR | Maynard | ESMAEX-03032 | 01754 | 19.5 | Solar | 416-H6 | 2023-10-09 | 2023-11-27 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-04-10 | Online | [8 empty] | STA_416 Maynard
NSTAR | Natick | ESMAEX-03037 | 01760 | 20 | Solar | 240-H5 | 2023-10-11 | 2023-11-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-27 | [7 empty] | 0 |  | 0 |  |  | 2024-01-22 | Online | [7 empty] | 20 | STA_240 Framingham
NSTAR | Sharon | ESMAEX-03038 | 02067 | 23.36 | Solar | 470-H12 | 2023-10-11 | 2023-11-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-12 | [7 empty] | 0 |  | 0 |  |  | 2024-08-05 | Technical Review | [8 empty] | STA_470 Canton
NSTAR | Hopkinton | ESMAEX-03043 | 01748 | 18.816 | Solar | 126-H1 | 2023-10-12 | 2023-11-02 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-08 | [7 empty] | 0 |  | 0 |  |  | 2024-02-26 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Woburn | ESMAEX-03161 | 01801 | 20 | Battery | 211-H13 | 2023-11-15 | 2023-12-12 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-11-06 | Online | [8 empty] | STA_211 Woburn
NSTAR | Burlington | ESMAEX-03049 | 01803 | 20.8 | Solar | 391-H7 | 2023-10-13 | 2023-11-02 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-08 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [8 empty] | STA_391 Burlington
NSTAR | Hopkinton | ESMAEX-03055 | 01748 | 15.2 | Solar | 126-H2 | 2023-10-16 | 2023-11-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-28 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Carlisle | ESMAEX-03054 | 01741 | 17.6 | Battery | 533-H8 | 2023-10-16 | 2023-11-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Framingham | ESMAEX-03079 | 01701 | 18.9 | Solar | 342-H5 | 2023-10-23 | 2023-11-08 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-21 | [7 empty] | 0 |  | 0 |  |  | 2024-02-08 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Rochester | ESMAEX-03058 | 02770 | 4980 | Solar & Battery | 3-85-85 | 2023-12-20 | 2024-01-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study | 2024 SEMA/Cape ASO Study |  | STA_713 Tremont
NSTAR | Framingham | ESMAEX-03059 | 01701 | 20 | Solar | 342-H4 | 2023-10-17 | 2023-10-31 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Online | [7 empty] | 20 | STA_342 Sudbury
NSTAR | Canton | ESMAEX-03069 | 02021 | 5 | Solar & Battery | 269-1321H2 | 2023-10-19 | 2023-11-20 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-19 | Online | [8 empty] | STA_470 Canton
NSTAR | Framingham | ESMAEX-03071 | 01701 | 498 | Solar | 455-H1 | 2023-10-19 | 2024-01-31 | 74 |  | 74 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_455 West Framingham
NSTAR | Carlisle | ESMAEX-03073 | 01741 | 15.7 | Solar | 533-H8 | 2023-10-19 | 2023-11-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-04 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Weston | ESMAEX-03077 | 02493 | 16.25 | Solar | 282-H10 | 2023-10-22 | 2023-11-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Online | [8 empty] | STA_282 Waltham
NSTAR | Wayland | ESMAEX-03076 | 01778 | 1 | Battery | 342-H1 | 2023-10-20 | 2023-11-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-21 | [7 empty] | 0 |  | 0 |  |  | 2024-05-08 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Jamaica Plain | ESMAEX-03273 | 02130 | 16.8 | Solar | 496-H4 | 2023-12-13 | 2024-01-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-05-03 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Hopkinton | ESMAEX-03177 | 01748 | 15.2 | Solar | 126-H4 | 2023-11-20 | 2024-01-23 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-26 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-03078 | 01720 | 250 | Solar | 416-H8 | 2024-02-26 | 2024-03-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_416 Maynard
NSTAR | Hopkinton | ESMAEX-03178 | 01748 | 15.2 | Solar & Battery | 126-H2 | 2023-11-20 | 2024-01-23 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-26 | [7 empty] | 0 |  | 0 |  |  | 2024-09-16 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Westwood | ESMAEX-03084 | 02090 | 19 | Solar | 456-H1 | 2023-11-07 | 2023-11-20 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-22 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online | [8 empty] | STA_456 Dover
NSTAR | Burlington | ESMAEX-03155 | 01803 | 15.2 | Solar | 391-H7 | 2023-11-15 | 2023-12-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-18 | [7 empty] | 0 |  | 0 |  |  | 2024-07-10 | Online | [8 empty] | STA_391 Burlington
NSTAR | Sherborn | ESMAEX-03091 | 01770 | 5 | Battery | 130-H2 | 2023-10-26 | 2023-11-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-11 | [7 empty] | 0 |  | 0 |  |  | 2024-11-26 | Online | [8 empty] | STA_130 Holliston
NSTAR | Roxbury | ESMAEX-03130 | 02119 | 100 | Solar | 396-05 | 2023-11-08 | 2023-11-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-11 | [7 empty] | 0 |  | 0 |  |  | 2025-01-31 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Truro | ESMAEX-03089 | 02666 | 9.9 | Solar | 4-96-96 | 2023-10-25 | 2023-11-07 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-21 | [7 empty] | 0 |  | 0 |  |  | 2024-03-04 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Milton | ESMAEX-03133 | 02186 | 15.2 | Solar | 4303 | 2023-11-08 | 2023-12-06 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-30 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Sharon | ESMAEX-03110 | 02067 | 15 | Battery | 470-H12 | 2023-11-02 | 2023-11-20 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-18 | [7 empty] | 0 |  | 0 |  |  | 2024-09-27 | Online | [8 empty] | STA_470 Canton
NSTAR | Wayland | ESMAEX-03100 | 01778 | 50 | Solar | 342-H3 | 2023-10-31 |  | -32274 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-11-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-11 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Bedford | ESMAEX-03098 | 01730 | 15.2 | Solar & Battery | 533-H7 | 2023-10-30 | 2023-11-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-26 | [7 empty] | 0 |  | 0 |  |  | 2024-06-27 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Natick | ESMAEX-03149 | 01760 | 240 | Solar | 433-H11 | 2023-11-14 | 2023-12-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-12 | [7 empty] | 0 |  | 0 |  |  | 2025-12-19 | Online | [7 empty] | 240 | STA_433 Speen Street
NSTAR | Rochester | ESMAEX-03258 | 02770 | 56.14 | Solar | 3-702-702 | 2023-12-07 | 2023-12-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-09 | [7 empty] | 0 |  | 0 |  |  | 2024-11-05 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_745 ROCHESTER
NSTAR | Acton | ESMAEX-03154 | 01720 | 23 | Solar & Battery | 416-H5 | 2023-11-15 | 2023-12-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-19 | [7 empty] | 0 |  | 0 |  |  | 2024-11-01 | Online | [7 empty] | 4.8 | STA_416 Maynard
NSTAR | Framingham | ESMAEX-03102 | 01701 | 19.2 | Solar | 278-H2 | 2023-10-31 | 2023-11-16 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [8 empty] | STA_278 Saxonville
NSTAR | Acton | ESMAEX-03122 | 01720 | 14 | Battery | 416-H2 | 2023-11-07 | 2023-11-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-09 | [7 empty] | 0 |  | 0 |  |  | 2024-04-02 | Online | [8 empty] | STA_416 Maynard
NSTAR | West Newton | ESMAEX-03116 | 02465 | 20.125 | Battery | 282-H9 | 2023-11-03 | 2023-11-27 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-05 | [7 empty] | 0 |  | 0 |  |  | 2024-04-16 | Online | [7 empty] | 20 | STA_282 Waltham
NSTAR | Acton | ESMAEX-03134 | 01720 | 15.2 | Solar & Battery | 416-H1 | 2023-11-08 | 2023-11-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-08 | [7 empty] | 0 |  | 0 |  |  | 2024-03-20 | Online | [7 empty] | 19.92 | STA_416 Maynard
NSTAR | Hyannis | ESMAEX-03114 | 02601 | 499.5 | Solar | 4-84B-524 | 2023-12-06 | 2024-01-17 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  | 499.5 | STA_961 Hyannis Junction
NSTAR | Hyannis | ESMAEX-03148 | 02601 | 150 | Solar | 4-84B-524 | 2023-11-14 | 2023-12-12 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-05 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  | 150 | STA_961 Hyannis Junction
NSTAR | Arlington | ESMAEX-03117 | 02474 | 67.3 | Solar | 211-H3 | 2023-11-03 | 2023-11-27 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-06 | [7 empty] | 0 |  | 0 |  |  | 2026-02-06 | Online | [8 empty] | STA_211 Woburn
NSTAR | Boston | ESMAEX-03135 | 02111 | 24.4 | Solar | 514-1N25S | 2024-08-14 | 2023-12-18 | -174 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-18 | Online | [7 empty] | 0 | STA_514 Kingston Street
NSTAR | Cambridge | ESMAEX-03146 | 02139 | 30 | Solar | 831-1394 | 2023-11-14 | 2023-11-30 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-25 | Online | [8 empty] | STA_831 Putnam
NSTAR | Cambridge | ESMAEX-03147 | 02139 | 40 | Solar | 831-1303 | 2023-11-14 | 2023-11-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-25 | Online | [8 empty] | STA_831 Putnam
NSTAR | Newton | ESMAEX-03166 | 02458 | 2.24 | Solar | 277-05 | 2023-11-16 | 2023-12-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-17 | [7 empty] | 0 |  | 0 |  |  | 2024-04-29 | Online | [8 empty] | STA_467 Watertown
NSTAR | Dover | ESMAEX-03131 | 02030 | 5 | Battery | 456-H5 | 2023-11-08 | 2023-11-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-21 | [7 empty] | 0 |  | 0 |  |  | 2024-06-04 | Online | [8 empty] | STA_456 Dover
NSTAR | Westwood | ESMAEX-03140 | 02090 | 8.64 | Solar | 148-H3 | 2023-11-10 | 2023-11-29 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-02 | [7 empty] | 0 |  | 0 |  |  | 2024-04-12 | Online | [8 empty] | STA_148 Needham
NSTAR | Cambridge | ESMAEX-03393 | 02139 | 60 | Solar |  | 2024-01-29 | 2024-02-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online
NSTAR | Newton | ESMAEX-03165 | 02458 | 15.3 | Solar | 277-05 | 2023-11-16 | 2023-12-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-12 | [7 empty] | 0 |  | 0 |  |  | 2024-03-28 | Online | [8 empty] | STA_467 Watertown
NSTAR | Provincetown | ESMAEX-03138 | 02657 | 19.9 | Solar & Battery | 4-675-675 | 2023-11-10 | 2023-12-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-03 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Online | [7 empty] | 19.9 | STA_976 Wellfleet
NSTAR | Framingham | ESMAEX-03151 | 01702 | 20 | Solar | 240-H6 | 2023-11-14 | 2023-11-30 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-11 | [7 empty] | 0 |  | 0 |  |  | 2024-10-08 | Online | [8 empty] | STA_240 Framingham
NSTAR | Hopkinton | ESMAEX-03182 | 01748 | 10 | Battery | 126-H2 | 2023-11-21 | 2024-01-23 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-23 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Online | [7 empty] | 12.4 | STA_126 Hopkinton
NSTAR | Acton | ESMAEX-03143 | 01720 | 15.2 | Solar | 416-H5 | 2023-11-13 | 2023-11-30 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online | [7 empty] | 15.2 | STA_416 Maynard
NSTAR | Needham | ESMAEX-03183 | 02494 | 15.2 | Solar | 148-H4 | 2023-11-21 | 2024-01-23 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-06 | [7 empty] | 0 |  | 0 |  |  | 2024-07-16 | Online | [8 empty] | STA_148 Needham
NSTAR | Brighton | ESMAEX-03144 | 02135 | 15.3 | Solar | 315-H10 | 2023-11-13 | 2024-01-31 | 57 |  | 57 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [8 empty] | STA_315 Electric Avenue
NSTAR | Medway | ESMAEX-03159 | 02053 | 80 | Solar | 65-H3 | 2023-12-15 | 2024-01-09 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-13 | [7 empty] | 0 |  | 0 |  |  | 2024-09-19 | Online | [8 empty] | STA_065 Medway
NSTAR | Chatham | ESMAEX-03158 | 02633 | 15.2 | Solar | 4-95B-95B | 2023-11-15 | 2023-12-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-15 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Online | [7 empty] | 15.2 | STA_975 Orleans
NSTAR | Waltham | ESMAEX-03162 | 02451 | 100 | Solar | 282-H1 | 2023-11-15 | 2024-02-22 | 71 |  | 71 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-26 | [7 empty] | 0 |  | 0 |  |  | 2024-09-27 | Online | [8 empty] | STA_282 Waltham
NSTAR | Holliston | ESMAEX-03163 | 01746 | 20 | Battery | 65-H5 | 2023-11-16 | 2023-12-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-10 | [7 empty] | 0 |  | 0 |  |  | 2024-04-24 | Online | [8 empty] | STA_065 Medway
NSTAR | Newton Highlands | ESMAEX-03164 | 02461 | 15.2 | Solar | 292-H3 | 2023-11-16 | 2023-11-30 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-19 | [7 empty] | 0 |  | 0 |  |  | 2024-08-27 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Weston | ESMAEX-03175 | 02493 | 22.2 | Solar | 282-H8 | 2023-11-20 | 2024-01-10 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Online | [8 empty] | STA_282 Waltham
NSTAR | Weston | ESMAEX-03320 | 02493 | 15.6 | Solar | 282-H1 | 2023-12-29 | 2024-01-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-07-08 | Online | [8 empty] | STA_282 Waltham
NSTAR | Ashland | ESMAEX-03181 | 01721 | 10 | Battery | 455-H8 | 2023-11-21 | 2024-01-23 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-01 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [7 empty] | 20 | STA_455 West Framingham
NSTAR | Winchester | ESMAEX-03187 | 01890 | 490 | Solar | 211-07 | 2023-12-11 | 2024-01-09 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-02 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [7 empty] | 490 | STA_211 Woburn
NSTAR | Hopkinton | ESMAEX-03189 | 01748 | 15.744 | Solar | 126-H2 | 2023-11-22 | 2023-12-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2023-12-19 | [7 empty] | 0 |  | 0 |  |  | 2024-08-02 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Plymouth | ESMAEX-03195 | 02360 | 6 | Solar | 3-14-934 | 2023-11-27 | 2023-12-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-17 | [7 empty] | 0 |  | 0 |  |  | 2024-10-17 | Online |  |  |  | Plymouth |  |  |  | 6 | STA_737 West Pond
NSTAR | Waltham | ESMAEX-03202 | 02452 | 15.2 | Solar | 450-H6 | 2023-11-29 | 2023-12-27 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2024-08-12 | Online | [8 empty] | STA_450 Trapelo Road
NSTAR | New Bedford | ESMAEX-03339 | 02740 | 250 | Solar | 2-89-89 | 2024-01-08 | 2024-01-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-07 | [7 empty] | 0 |  | 0 |  |  | 2025-12-24 | Online | [8 empty] | STA_611 Pine Street
NSTAR | Milton | ESMAEX-03206 | 02186 | 20 | Solar | 311-04 | 2023-11-29 | 2023-12-27 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-02 | [7 empty] | 0 |  | 0 |  |  | 2024-03-07 | Online | [7 empty] | 20 | STA_496 Hyde Park
NSTAR | Billerica | ESMAEX-03207 | 01821 | 10 | Solar & Battery | 533-H7 | 2023-11-30 | 2023-12-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-17 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Wayland | ESMAEX-03281 | 01778 | 12.21 | Solar | 342-H1 | 2023-12-14 | 2024-02-22 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-18 | [7 empty] | 0 |  | 0 |  |  | 2024-05-07 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Sherborn | ESMAEX-03255 | 01770 | 18.56 | Solar | 240-H1 | 2023-12-06 | 2024-01-12 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-04-01 | Online | [8 empty] | STA_240 Framingham
NSTAR | Lexington | ESMAEX-03212 | 02420 | 23 | Solar & Battery | 3406 | 2023-12-01 | 2023-12-27 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-01 | [7 empty] | 0 |  | 0 |  |  | 2024-08-06 | Online | [7 empty] | 20
NSTAR | Burlington | ESMAEX-03261 | 01803 | 34.5 | Solar & Battery | 346-1395H1 | 2023-12-08 | 2024-01-09 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-07 | [7 empty] | 0 |  | 0 |  |  | 2025-06-18 | Online | [8 empty] | STA_391 Burlington
NSTAR | Arlington | ESMAEX-03209 | 02476 | 490 | Solar | 211-H3 | 2023-12-28 | 2024-01-23 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_211 Woburn
NSTAR | Westwood | ESMAEX-03307 | 02090 | 15.2 | Solar & Battery | 148-H3 | 2023-12-21 | 2024-03-04 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-09 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Online | [7 empty] | 20 | STA_148 Needham
NSTAR | Chilmark | ESMAEX-03230 | 02535 | 11.4 | Solar | 4-97-97 | 2023-12-05 | 2024-02-12 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-18 | [7 empty] | 0 |  | 0 |  |  | 2024-11-07 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | West Brewster | ESMAEX-03274 | 02631 | 20.44 | Solar | 4-89A-89A | 2023-12-13 | 2024-01-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  | 2025-03-17 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Lexington | ESMAEX-03260 | 02420 | 16.64 | Solar | 533-H9 | 2023-12-08 | 2023-12-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  | 2024-06-10 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Milton | ESMAEX-03335 | 02186 | 15.2 | Solar | 362-1209H2 | 2024-01-04 | 2024-01-31 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Newton Center | ESMAEX-03302 | 02459 | 20.2 | Solar & Battery | 292-H6 | 2023-12-20 | 2024-01-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-08 | [7 empty] | 0 |  | 0 |  |  | 2025-08-07 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Cambridge | ESMAEX-03395 | 02142 | 120 | Solar |  | 2024-01-29 | 2024-02-16 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-21 | [7 empty] | 0 |  | 0 |  |  |  | Online
NSTAR | Millis | ESMAEX-03263 | 02054 | 19 | Solar & Battery | 130-H2 | 2023-12-11 | 2024-01-09 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-09 | [7 empty] | 0 |  | 0 |  |  | 2025-02-27 | Online | [7 empty] | 19.9 | STA_130 Holliston
NSTAR | East Freetown | ESMAEX-03264 | 02717 | 15.36 | Solar | 2-108-108 | 2023-12-12 | 2024-01-09 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Westwood | ESMAEX-03269 | 02090 | 23 | Solar & Battery | 456-H1 | 2023-12-12 | 2024-01-09 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Online | [8 empty] | STA_456 Dover
NSTAR | Hopkinton | ESMAEX-03272 | 01748 | 15.2 | Solar | 126-H4 | 2023-12-13 | 2024-01-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-12 | [7 empty] | 0 |  | 0 |  |  | 2024-05-01 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Provincetown | ESMAEX-03277 | 02657 | 19.8 | Solar | 4-675-675 | 2023-12-14 | 2024-01-17 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-22 | [7 empty] | 0 |  | 0 |  |  | 2024-05-02 | Online | [7 empty] | 20 | STA_976 Wellfleet
NSTAR | Lexington | ESMAEX-03278 | 02420 | 15.2 | Solar | 351-02 | 2023-12-14 | 2024-01-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-03 | [7 empty] | 0 |  | 0 |  |  | 2024-09-05 | Online | [8 empty] | STA_211 Woburn
NSTAR | Acton | ESMAEX-03348 | 01720 | 50 | Solar | 416-H5 | 2024-01-09 | 2024-01-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-05 | [7 empty] | 0 |  | 0 |  |  | 2024-08-21 | Online | [8 empty] | STA_416 Maynard
NSTAR | Hopkinton | ESMAEX-03398 | 01748 | 20 | Solar & Battery | 126-H1 | 2024-01-30 | 2024-02-22 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-06 | Online | [7 empty] | 20 | STA_126 Hopkinton
NSTAR | Lexington | ESMAEX-03289 | 02421 | 17.6 | Solar & Battery | 450-H5 | 2023-12-19 | 2024-01-10 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-07-31 | Online | [8 empty] | STA_450 Trapelo Road
NSTAR | Marshfield | ESMAEX-03291 | 02050 | 999 | Solar & Battery | 3-24B-915 | 2024-06-12 | 2024-07-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 999 | STA_738 Duxbury
NSTAR | Lexington | ESMAEX-03387 | 02421 | 1836 | Solar & Battery | 391-H11 | 2024-06-06 | 2024-07-12 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_391 Burlington
NSTAR | Natick | ESMAEX-03384 | 01760 | 16.8 | Solar | 240-H5 | 2024-01-25 | 2024-02-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-27 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online | [8 empty] | STA_240 Framingham
NSTAR | Lexington | ESMAEX-03313 | 02420 | 15.2 | Solar | 391-H11 | 2023-12-27 | 2024-01-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-29 | [7 empty] | 0 |  | 0 |  |  | 2024-07-10 | Online | [8 empty] | STA_391 Burlington
NSTAR | Lexington | ESMAEX-03532 | 02421 | 17.6 | Solar & Battery | 3402 | 2024-03-12 | 2024-03-28 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-24 | Online | [8 empty] | STA_320 Lexington
NSTAR | Woods Hole | ESMAEX-03334 | 02543 | 10 | Battery | 4-91-91 | 2024-01-04 | 2024-08-15 | 160 |  | 160 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-05 | [7 empty] | 0 |  | 0 |  |  | 2025-10-07 | Online |  |  |  | Cape |  |  |  | 10 | STA_933 Falmouth
NSTAR | Sudbury | ESMAEX-03362 | 01776 | 43.01 | Solar & Battery | 416-H6 | 2024-01-16 | 2024-02-22 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-09 | [7 empty] | 0 |  | 0 |  |  | 2024-12-30 | Online | [8 empty] | STA_416 Maynard
NSTAR | Sharon | ESMAEX-03351 | 02067 | 12.6 | Solar & Battery | 470-H3 | 2024-01-10 | 2024-01-31 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-20 | [7 empty] | 0 |  | 0 |  |  | 2024-11-18 | Online | [8 empty] | STA_470 Canton
NSTAR | Medfield | ESMAEX-03324 | 02052 | 23 | Solar & Battery | 456-H2 | 2024-01-03 | 2024-01-31 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-11 | [7 empty] | 0 |  | 0 |  |  | 2024-12-30 | Online | [7 empty] | 7.33 | STA_456 Dover
NSTAR | Jamaica Plain | ESMAEX-03333 | 02130 | 50 | Solar | 496-H4 | 2024-01-04 | 2024-01-31 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-24 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Hopkinton | ESMAEX-03376 | 01748 | 4.8 | Solar & Battery | 126-H2 | 2024-01-22 | 2024-02-22 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-17 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Online | [7 empty] | 4.8 | STA_126 Hopkinton
NSTAR | Newton | ESMAEX-03366 | 02458 | 22.8 | Solar & Battery | 467-H3 | 2024-01-17 | 2024-02-22 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-07-15 | Online | [7 empty] | 22.8 | STA_467 Watertown
NSTAR | Stoneham | ESMAEX-03369 | 02180 | 10 | Battery | 375-H7 | 2024-01-18 | 2024-02-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-13 | Online | [7 empty] | 14.04 | STA_375 Dragon Court
NSTAR | East Walpole | ESMAEX-03354 | 02032 | 7.6 | Solar | 146-H4 | 2024-01-10 | 2024-01-31 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-01-31 | [7 empty] | 0 |  | 0 |  |  | 2025-09-04 | Online | [8 empty] | STA_146 Walpole
NSTAR | Cambridge | ESMAEX-03391 | 02139 | 160 | Solar |  | 2024-01-29 | 2024-02-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-15 | [7 empty] | 0 |  | 0 |  |  | 2025-06-17 | Online
NSTAR | Holliston | ESMAEX-03341 | 01746 | 7.6 | Solar | 65-H2 | 2024-01-09 | 2024-01-31 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-16 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Online | [7 empty] | 7.6 | STA_065 Medway
NSTAR | Wayland | ESMAEX-03353 | 01778 | 16 | Solar | 342-H1 | 2024-01-10 | 2024-01-31 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-07 | [7 empty] | 0 |  | 0 |  |  | 2024-04-25 | Online | [7 empty] | 16 | STA_342 Sudbury
NSTAR | Framingham | ESMAEX-03357 | 01701 | 30.66 | Solar & Battery | 455-H1 | 2024-01-12 | 2024-02-07 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_455 West Framingham
NSTAR | Cambridge | ESMAEX-03423 | 02139 | 20 | Solar | 814-12 | 2024-02-07 | 2024-02-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-27 | Online | [7 empty] | 20 | STA_402 Newton Street
NSTAR | Cambridge | ESMAEX-03422 | 02139 | 20 | Solar | 815-10 | 2024-02-07 | 2024-02-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-02-28 | [7 empty] | 0 |  | 0 |  |  | 2025-01-02 | Technical Review | [8 empty] | STA_831 Putnam
NSTAR | Somerville | ESMAEX-03421 | 02145 | 22.8 | Solar | 387-148H2 | 2024-02-07 | 2024-02-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-07 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 11 | STA_250 Mystic
NSTAR | Dover | ESMAEX-03546 | 02030 | 23.03 | Solar | 456-H3 | 2024-03-18 | 2024-04-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_456 Dover
NSTAR | East Freetown | ESMAEX-03512 | 02717 | 200 | Solar | 2-108-108 | 2024-03-06 | 2024-03-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Ashland | ESMAEX-03400 | 01721 | 15.29 | Solar | 274-H6 | 2024-01-30 | 2024-02-22 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-20 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Online | [7 empty] | 15.29
NSTAR | Holliston | ESMAEX-03401 | 01746 | 50 | Solar | 65-H2 | 2024-01-30 | 2024-02-26 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-30 | [7 empty] | 0 |  | 0 |  |  | 2024-09-16 | Online | [8 empty] | STA_065 Medway
NSTAR | Waban | ESMAEX-03429 | 02468 | 17.6 | Solar & Battery | 1701 | 2024-02-08 | 2024-02-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [7 empty] | 7.05 | STA_292 Newton Highlands
NSTAR | Acton | ESMAEX-03414 | 01720 | 40 | Solar | 416-H1 | 2024-02-05 | 2024-02-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-18 | [7 empty] | 0 |  | 0 |  |  | 2024-08-06 | Online | [8 empty] | STA_416 Maynard
NSTAR | South Wellfleet | ESMAEX-03501 | 02663 | 12.6 | Solar & Battery | 4-94B-653 | 2024-03-01 | 2024-03-22 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-13 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Newton Center | ESMAEX-03405 | 02459 | 10 | Battery | 292-H11 | 2024-02-01 | 2024-03-14 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-26 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Hopkinton | ESMAEX-03430 | 01748 | 23 | Battery | 126-H4 | 2024-02-09 | 2024-02-27 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Online | [7 empty] | 20 | STA_126 Hopkinton
NSTAR | Brighton | ESMAEX-03476 | 02135 | 34.6 | Solar | 329-1N51H2 | 2024-02-23 | 2024-03-05 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-11 | [7 empty] | 0 |  | 0 |  |  | 2025-09-16 | Online | [8 empty] | STA_329 Brighton
NSTAR | Cambridge | ESMAEX-03457 | 02138 | 225 | Solar | 827-31 | 2024-02-16 | 2024-03-05 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-29 | [7 empty] | 0 |  | 0 |  |  | 2025-09-15 | Online | [8 empty] | STA_828 Alewife
NSTAR | Carlisle | ESMAEX-03506 | 01741 | 10 | Battery | 533-H8 | 2024-03-05 | 2024-03-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Lexington | ESMAEX-03436 | 02420 | 5 | Battery | 533-H9 | 2024-02-14 | 2024-03-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-19 | [7 empty] | 0 |  | 0 |  |  | 2024-11-01 | Online | [7 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | Milton | ESMAEX-03424 | 02186 | 10 | Battery | 362-1209H2 | 2024-02-07 | 2024-02-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-12 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | STA_496 Hyde Park
NSTAR | Weston | ESMAEX-03452 | 02493 | 34.2 | Solar | 282-H10 | 2024-02-15 | 2024-03-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-08-06 | Online | [8 empty] | STA_282 Waltham
NSTAR | Acton | ESMAEX-03425 | 01720 | 10 | Battery | 512-1399H1 | 2024-02-07 | 2024-02-27 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-02 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [7 empty] | 12.4 | STA_533 Hartwell Avenue
NSTAR | Natick | ESMAEX-03426 | 01760 | 15.2 | Solar | 433-H10 | 2024-02-08 | 2024-02-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-04 | [7 empty] | 0 |  | 0 |  |  | 2024-04-18 | Online | [7 empty] | 15.2 | STA_433 Speen Street
NSTAR | Lexington | ESMAEX-03427 | 02421 | 16 | Solar | 3409 | 2024-02-08 | 2024-02-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-06-12 | Online | [7 empty] | 16
NSTAR | North Cambridge | ESMAEX-03439 | 02140 | 16.8 | Solar | 823-23 | 2024-02-14 | 2024-03-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-07 | [7 empty] | 0 |  | 0 |  |  | 2024-06-25 | Online | [8 empty] | STA_828 Alewife
NSTAR | Sudbury | ESMAEX-03428 | 01776 | 9.6 | Solar & Battery | 342-H2 | 2024-02-08 | 2024-03-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-21 | [7 empty] | 0 |  | 0 |  |  | 2025-10-06 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Natick | ESMAEX-03472 | 01760 | 200 | Fuel Cell | 2302 | 2024-02-22 | 2024-03-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  | 2025-06-27 | Online | [8 empty] | STA_240 Framingham
NSTAR | Lexington | ESMAEX-03433 | 02420 | 300 | Solar & Battery | 34-1378 | 2024-06-07 | 2024-08-06 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-31 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_211 Woburn
NSTAR | Duxbury | ESMAEX-03461 | 02332 | 15.36 | Solar & Battery | 3-26-26 | 2024-02-19 | 2024-03-05 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-12 | [7 empty] | 0 |  | 0 |  |  | 2024-06-14 | Online
NSTAR | Westwood | ESMAEX-03450 | 02090 | 10 | Solar & Battery | 148-H3 | 2024-02-14 | 2024-03-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-09 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Online | [7 empty] | 10 | STA_148 Needham
NSTAR | Weston | ESMAEX-03454 | 02493 | 20 | Solar & Battery | 433-H5 | 2024-02-15 | 2024-03-05 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-11-07 | Online | [7 empty] | 20 | STA_433 Speen Street
NSTAR | Lexington | ESMAEX-03460 | 02421 | 11.4 | Solar & Battery | 3409 | 2024-02-19 | 2024-03-05 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-10 | [7 empty] | 0 |  | 0 |  |  | 2024-07-31 | Online
NSTAR | Burlington | ESMAEX-03618 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-10 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_375 Dragon Court
NSTAR | Cataumet | ESMAEX-03462 | 02534 | 34.2 | Solar | 4-81A-81A | 2024-02-20 | 2024-03-05 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-02 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Online |  |  |  | Cape |  |  |  |  | STA_915 Otis
NSTAR | Boston | ESMAEX-03557 | 02119 | 20 | Solar | 483-H3 | 2024-03-20 | 2024-05-15 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-22 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Online | [8 empty] | STA_483 Dewar Street
NSTAR | Plymouth | ESMAEX-03475 | 02360 | 23.8 | Battery | 3-73-927 | 2024-02-23 | 2024-03-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-14 | [7 empty] | 0 |  | 0 |  |  | 2024-08-15 | Online | [7 empty] | 12.28 | STA_721 Manomet
NSTAR | Needham | ESMAEX-03469 | 02492 | 22.8 | Solar | 148-02 | 2024-02-22 | 2024-03-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-25 | [7 empty] | 0 |  | 0 |  |  | 2024-09-26 | Online | [8 empty] | STA_148 Needham
NSTAR | Winchester | ESMAEX-03466 | 01890 | 17.6 | Solar & Battery | 211-H6 | 2024-02-20 | 2024-03-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-24 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Online | [8 empty] | STA_211 Woburn
NSTAR | Mattapan | ESMAEX-03465 | 02126 | 7.6 | Solar | 311-02 | 2024-02-20 | 2024-03-04 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-29 | [7 empty] | 0 |  | 0 |  |  | 2024-10-15 | Online | [7 empty] | 7.6 | STA_496 Hyde Park
NSTAR | Walpole | ESMAEX-03497 | 02081 | 3.8 | Solar | 2601 | 2024-02-29 | 2024-03-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2024-08-01 | Online | [7 empty] | 3.8 | STA_146 Walpole
NSTAR | Westwood | ESMAEX-03477 | 02090 | 9.9 | Solar & Battery | 456-H1 | 2024-02-26 | 2024-04-03 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-24 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Online | [8 empty] | STA_456 Dover
NSTAR | Lincoln | ESMAEX-03470 | 01773 | 23.7 | Solar | 320-H6 | 2024-02-22 | 2024-03-19 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-01 | [7 empty] | 0 |  | 0 |  |  | 2024-11-06 | Online | [7 empty] | 9.99 | STA_320 Lexington
NSTAR | Brookline | ESMAEX-03509 | 02445 | 24.9 | Solar & Battery | 350-H8 | 2024-03-05 | 2024-03-18 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-17 | [7 empty] | 0 |  | 0 |  |  | 2024-12-20 | Online | [7 empty] | 19.48 | STA_350 Colburn Street
NSTAR | Arlington | ESMAEX-03508 | 02474 | 10 | Battery | 211-H11 | 2024-03-05 | 2024-03-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-23 | Online | [7 empty] | 11.34 | STA_211 Woburn
NSTAR | Dartmouth | ESMAEX-03486 | 02748 | 150 | Solar | 2-53-65 | 2024-02-28 | 2024-04-02 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-19 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Online | [8 empty] | STA_611 Pine Street
NSTAR | Wayland | ESMAEX-03496 | 01778 | 10 | Solar & Battery | 278-H2 | 2024-02-29 | 2024-04-03 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-30 | [7 empty] | 0 |  | 0 |  |  | 2024-08-08 | Online | [7 empty] | 20 | STA_278 Saxonville
NSTAR | Needham | ESMAEX-03484 | 02492 | 15.2 | Solar | 148-H7 | 2024-02-28 | 2024-03-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-28 | [7 empty] | 0 |  | 0 |  |  | 2024-10-20 | Online | [8 empty] | STA_148 Needham
NSTAR | Framingham | ESMAEX-03478 | 01701 | 21.6 | Solar | 455-H1 | 2024-02-26 | 2024-03-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-25 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [7 empty] | 20.88 | STA_455 West Framingham
NSTAR | Carlisle | ESMAEX-03480 | 01741 | 3 | Solar | 533-H8 | 2024-02-27 | 2024-03-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-18 | [7 empty] | 0 |  | 0 |  |  | 2024-07-10 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Acusnet | ESMAEX-03479 | 02743 | 15.2 | Solar | 2-241-241 | 2024-02-27 | 2024-03-22 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-29 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_624 Wing Lane
NSTAR | Framingham | ESMAEX-03494 | 01701 | 16 | Solar | 455-H1 | 2024-02-29 | 2024-03-19 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-03-26 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Online | [7 empty] | 16 | STA_455 West Framingham
NSTAR | Dover | ESMAEX-03491 | 02030 | 19.8 | Solar & Battery | 456-H5 | 2024-02-29 | 2024-03-14 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-05 | [7 empty] | 0 |  | 0 |  |  | 2024-09-24 | Online | [7 empty] | 19.8 | STA_456 Dover
NSTAR | Medway | ESMAEX-03487 | 02053 | 109 | Solar | 65-H3 | 2024-02-28 | 2024-04-02 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-09 | [7 empty] | 0 |  | 0 |  |  | 2025-05-07 | Online | [8 empty] | STA_065 Medway
NSTAR | Dorchester | ESMAEX-03535 | 02122 | 250 | Solar | 43-1490H3 | 2024-03-13 | 2024-04-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-14 | [7 empty] | 0 |  | 0 |  |  |  | Permission to Operate | [8 empty] | STA_483 Dewar Street
NSTAR | Sudbury | ESMAEX-03500 | 01776 | 800 | Solar | 342-H2 | 2024-03-01 | 2024-03-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 800 | STA_342 Sudbury
NSTAR | Arlington | ESMAEX-03505 | 02476 | 360 | Solar | 320-H7 | 2024-04-19 | 2024-05-20 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_320 Lexington
NSTAR | Dorchester | ESMAEX-03518 | 02121 | 22.8 | Solar | 483-H5 | 2024-03-08 | 2024-03-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-15 | [7 empty] | 0 |  | 0 |  |  | 2025-06-30 | Online | [7 empty] | 20 | STA_483 Dewar Street
NSTAR | Newton Center | ESMAEX-03515 | 02459 | 10 | Solar & Battery | 292-H11 | 2024-03-07 | 2024-03-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-21 | [7 empty] | 0 |  | 0 |  |  | 2024-11-12 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Duxbury | ESMAEX-03525 | 02332 | 166 | Solar | 3-24B-24B | 2024-06-04 | 2024-07-12 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_738 Duxbury
NSTAR | Sharon | ESMAEX-03527 | 02067 | 487.5 | Solar | 470-H3 | 2024-03-11 | 2024-03-26 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-03 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_470 Canton
NSTAR | Newton Center | ESMAEX-03529 | 02459 | 10 | Solar | 292-H5 | 2024-03-11 | 2024-03-26 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-08 | [7 empty] | 0 |  | 0 |  |  | 2024-10-11 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Westwood | ESMAEX-03538 | 02090 | 25 | Battery | 456-H1 | 2024-03-14 | 2024-04-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-28 | [7 empty] | 0 |  | 0 |  |  | 2025-10-07 | Online | [8 empty] | STA_456 Dover
NSTAR | Bellingham | ESMAEX-03534 | 02019 | 15.2 | Solar | 65-H4 | 2024-03-13 | 2024-03-28 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2025-03-04 | Online | [8 empty] | STA_065 Medway
NSTAR | North Cambridge | ESMAEX-03668 | 02140 | 108 | Solar | 828-1378 | 2024-04-15 | 2024-06-05 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  | 2025-12-30 | Online | [7 empty] | 0 | STA_828 Alewife
NSTAR | Dorchester | ESMAEX-03542 | 02124 | 60 | Solar | 496-H8 | 2024-03-15 | 2024-04-01 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-12 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_496 Hyde Park
NSTAR | Burlington | ESMAEX-03616 | 01803 | 20.1 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_375 Dragon Court
NSTAR | Burlington | ESMAEX-03615 | 01803 | 20.1 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_375 Dragon Court
NSTAR | Burlington | ESMAEX-03614 | 01803 | 17.3 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_375 Dragon Court
NSTAR | Roslindale | ESMAEX-03543 | 02131 | 60 | Solar | 1312 | 2024-03-15 | 2024-04-01 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-04-01 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_496 Hyde Park
NSTAR | Brighton | ESMAEX-03559 | 02135 | 133.2 | Solar | 329-H6 | 2024-03-21 | 2024-05-06 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Online | [8 empty] | STA_329 Brighton
NSTAR | Provincetown | ESMAEX-03685 | 02657 | 50 | Battery | 4-675-675 | 2024-04-18 | 2024-05-21 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-05 | [7 empty] | 0 |  | 0 |  |  | 2025-05-21 | Online | [7 empty] | 0 | STA_976 Wellfleet
NSTAR | Canton | ESMAEX-03680 | 02021 | 15.2 | Solar & Battery | 269-1320H1 | 2024-04-17 | 2024-05-10 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-05 | [7 empty] | 0 |  | 0 |  |  | 2024-11-19 | Online | [8 empty] | STA_470 Canton
NSTAR | Burlington | ESMAEX-03613 | 01803 | 20.1 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_375 Dragon Court
NSTAR | Bourne | ESMAEX-03619 | 02562 | 27.3 | Solar | 3-89-925 | 2024-04-02 | 2024-05-06 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-06 | [7 empty] | 0 |  | 0 |  |  | 2025-11-26 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Burlington | ESMAEX-03610 | 01803 | 17.3 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_375 Dragon Court
NSTAR | Burlington | ESMAEX-03609 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_375 Dragon Court
NSTAR | Westwood | ESMAEX-03549 | 02090 | 3.9 | Solar | 456-H4 | 2024-03-19 | 2024-04-01 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-21 | [7 empty] | 0 |  | 0 |  |  | 2024-07-24 | Online | [8 empty] | STA_456 Dover
NSTAR | Woburn | ESMAEX-03552 | 01801 | 48.38 | Solar | 375-H9 | 2024-03-19 | 2024-05-01 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-30 | [7 empty] | 0 |  | 0 |  |  | 2025-03-04 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Brookline | ESMAEX-03564 | 02446 | 29.58 | Solar | 350-H12 | 2024-03-21 | 2024-04-01 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-03-20 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Hatchville | ESMAEX-03554 | 02536 | 7.6 | Solar & Battery | 4-98A-98A | 2024-03-20 | 2024-03-28 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-26 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Burlington | ESMAEX-03606 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-07 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_375 Dragon Court
NSTAR | Burlington | ESMAEX-03605 | 01803 | 20 | Solar | 375-H6 | 2024-04-02 | 2024-05-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_375 Dragon Court
NSTAR | Orleans | ESMAEX-03556 | 02653 | 204.96 | Solar | 4-83-952 | 2024-03-20 | 2024-04-04 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-04 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_975 Orleans
NSTAR | Orleans | ESMAEX-03558 | 02653 | 249.9 | Solar | 4-83-952 | 2024-03-20 | 2024-04-04 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 250 | STA_975 Orleans
NSTAR | Wareham | ESMAEX-03560 | 02571 | 3 | Solar & Battery | 3-84-12J1 | 2024-03-21 | 2024-04-01 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-15 | [7 empty] | 0 |  | 0 |  |  | 2025-02-06 | Online
NSTAR | Millis | ESMAEX-03621 | 02054 | 20.2 | Solar | 65-H1 | 2024-04-03 | 2024-05-29 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-02 | Online | [7 empty] | 20 | STA_065 Medway
NSTAR | Needham | ESMAEX-03575 | 02492 | 18.048 | Solar | 148-06 | 2024-03-26 | 2024-04-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-08-13 | Online | [8 empty] | STA_148 Needham
NSTAR | South Wellfleet | ESMAEX-03774 | 02663 | 22.11 | Solar | 4-94B-656 | 2024-05-16 | 2024-06-17 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-13 | Technical Review | [8 empty] | STA_976 Wellfleet
NSTAR | Newton Lower Falls | ESMAEX-03674 | 02462 | 20 | Solar | 292-H2 | 2024-04-16 | 2024-05-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-18 | [7 empty] | 0 |  | 0 |  |  | 2025-01-03 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Chatham | ESMAEX-03577 | 02633 | 15.36 | Battery | 4-95B-95B | 2024-03-26 | 2024-04-12 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-22 | Online | [8 empty] | STA_975 Orleans
NSTAR | Chelsea | ESMAEX-03683 | 02150 | 67.3 | Solar | 14-113H2 | 2024-04-18 | 2024-05-23 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-06 | [7 empty] | 0 |  | 0 |  |  | 2025-12-11 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Framingham | ESMAEX-03580 | 01701 | 7.6 | Solar | 455-H1 | 2024-03-26 | 2024-04-25 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Online | [7 empty] | 7.6 | STA_455 West Framingham
NSTAR | West Newton | ESMAEX-03649 | 02465 | 60 | Solar | 292-H7 | 2024-04-09 | 2024-04-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-14 | [7 empty] | 0 |  | 0 |  |  | 2024-12-30 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Medway | ESMAEX-03582 | 02053 | 15.2 | Solar | 65-H3 | 2024-03-27 | 2024-04-12 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-15 | [7 empty] | 0 |  | 0 |  |  | 2024-12-11 | Online | [8 empty] | STA_065 Medway
NSTAR | Chatham | ESMAEX-03642 | 02633 | 150 | Solar | 4-95B-95B | 2024-04-09 | 2024-04-26 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_975 Orleans
NSTAR | Barnstable | ESMAEX-03860 | 02630 | 23.52 | Solar | 4-84A-84A | 2024-06-25 | 2024-09-05 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-19 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Online |  |  |  | Cape |  |  |  | 18.62 | STA_920 Oak Street
NSTAR | Waltham | ESMAEX-03594 | 02453 | 2000 | Battery | 386-1366 | 2024-05-22 | 2024-06-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 0 | STA_282 Waltham
NSTAR | Waltham | ESMAEX-03593 | 02453 | 1500 | Battery | 386-1356 | 2024-05-22 | 2024-06-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 0 | STA_282 Waltham
NSTAR | Eastham | ESMAEX-03679 | 02642 | 15.2 | Solar & Battery | 4-94A-94A | 2024-04-17 | 2024-06-21 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-15 | [7 empty] | 0 |  | 0 |  |  | 2025-02-28 | Online | [8 empty] | STA_975 Orleans
NSTAR | Weston | ESMAEX-03592 | 02493 | 15.2 | Solar | 282-H1 | 2024-03-29 | 2024-04-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-05 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Online | [7 empty] | 15.2 | STA_282 Waltham
NSTAR | Plympton | ESMAEX-03629 | 02367 | 4999 | Solar & Battery | 3-51-51 | 2024-04-04 | 2024-04-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4999 | STA_727 Brook Street
NSTAR | Kingston | ESMAEX-03636 | 02364 | 4999 | Solar & Battery | 3-50-50 | 2024-04-05 | 2024-04-18 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4999 | STA_727 Brook Street
NSTAR | Winchester | ESMAEX-03628 | 01890 | 23 | Solar & Battery | 211-H6 | 2024-04-04 | 2024-05-20 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-09-23 | Online | [7 empty] | 10 | STA_211 Woburn
NSTAR | Natick | ESMAEX-03622 | 01760 | 3.8 | Solar | 433-H5 | 2024-04-03 | 2024-04-24 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  | 2025-02-18 | Online | [7 empty] | 3.8 | STA_433 Speen Street
NSTAR | East Harwich | ESMAEX-03623 | 02645 | 17.6 | Solar & Battery | 4-89B-576 | 2024-04-03 | 2024-04-24 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [8 empty] | STA_975 Orleans
NSTAR | Framingham | ESMAEX-03627 | 01701 | 9.735 | Solar & Battery | 455-H1 | 2024-04-03 | 2024-04-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-15 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Needham | ESMAEX-03639 | 02494 | 24.96 | Solar | 292-H4 | 2024-04-08 | 2024-05-08 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-06 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Online | [7 empty] | 19.99 | STA_292 Newton Highlands
NSTAR | Norfolk | ESMAEX-03633 | 02056 | 19 | Solar | 146-H9 | 2024-04-05 | 2024-04-24 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Online | [8 empty] | STA_146 Walpole
NSTAR | Acton | ESMAEX-03645 | 01720 | 17.28 | Solar | 416-H8 | 2024-04-09 | 2024-05-06 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-05 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Online | [8 empty] | STA_416 Maynard
NSTAR | Lexington | ESMAEX-03673 | 02420 | 20 | Solar & Battery | 211-H10 | 2024-04-16 | 2024-06-05 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-06 | Online | [7 empty] | 20 | STA_211 Woburn
NSTAR | Framingham | ESMAEX-03641 | 01701 | 15.2 | Solar | 342-H9 | 2024-04-08 | 2024-04-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-13 | [7 empty] | 0 |  | 0 |  |  | 2025-02-24 | Online | [7 empty] | 15.2 | STA_342 Sudbury
NSTAR | Roslindale | ESMAEX-03646 | 02131 | 6.9 | Solar | 496-H5 | 2024-04-09 | 2024-04-30 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-03 | [7 empty] | 0 |  | 0 |  |  | 2024-08-20 | Technical Review | [8 empty] | STA_496 Hyde Park
NSTAR | Marshfield | ESMAEX-03643 | 02050 | 3.8 | Solar | 3-27-27 | 2024-04-09 | 2024-04-24 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-12 | [7 empty] | 0 |  | 0 |  |  | 2024-12-18 | Online | [8 empty] | STA_738 Duxbury
NSTAR | Brookline | ESMAEX-03651 | 02446 | 34.6 | Solar | 329-H10 | 2024-04-10 | 2024-04-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-06 | [7 empty] | 0 |  | 0 |  |  | 2025-09-30 | Online | [8 empty] | STA_329 Brighton
NSTAR | Bedford | ESMAEX-03656 | 01730 | 15.2 | Solar & Battery | 533-H3 | 2024-04-11 | 2024-05-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-17 | [7 empty] | 0 |  | 0 |  |  | 2024-09-27 | Online | [7 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | Carlisle | ESMAEX-03660 | 01741 | 10 | Battery | 533-H8 | 2024-07-25 | 2024-07-25 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Online | [7 empty] | 10 | STA_533 Hartwell Avenue
NSTAR | Chestnut Hill | ESMAEX-03658 | 02467 | 19.86 | Solar & Battery | 1706 | 2024-04-11 | 2024-05-20 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-22 | [7 empty] | 0 |  | 0 |  |  | 2024-10-01 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | New Bedford | ESMAEX-03661 | 02746 | 3.8 | Solar | 2-85-130 | 2024-04-12 | 2024-05-17 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-22 | [7 empty] | 0 |  | 0 |  |  | 2024-09-30 | Online
NSTAR | Sharon | ESMAEX-03666 | 02067 | 17.58 | Solar & Battery | 146-H1 | 2024-04-15 | 2024-05-06 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-01 | [7 empty] | 0 |  | 0 |  |  | 2024-11-25 | Online | [7 empty] | 11.45 | STA_146 Walpole
NSTAR | Cambridge | ESMAEX-03885 | 02139 | 40 | Solar & Battery | 817-01 | 2024-07-08 | 2024-07-31 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-28 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_831 Putnam
NSTAR | Dover | ESMAEX-03692 | 02030 | 67.3 | Solar | 456-H2 | 2024-04-22 | 2024-05-14 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-24 | [7 empty] | 0 |  | 0 |  |  | 2024-10-25 | Online | [8 empty] | STA_456 Dover
NSTAR | Boston | ESMAEX-03677 | 02119 | 27.3 | Solar | 510-77H3 | 2024-04-17 | 2024-06-21 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-21 | [7 empty] | 0 |  | 0 |  |  | 2025-03-20 | Online | [8 empty] | STA_106 Andrew Square
NSTAR | Waltham | ESMAEX-03734 | 02451 | 180 | Solar | 450-H2 | 2024-05-03 | 2024-05-23 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-17 | [7 empty] | 0 |  | 0 |  |  | 2025-08-28 | Online | [8 empty] | STA_450 Trapelo Road
NSTAR | Somerville | ESMAEX-03749 | 02144 | 100 | Solar | 59-1471 | 2024-05-10 | 2024-06-20 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-27 | [7 empty] | 0 |  | 0 |  |  | 2025-12-31 | Online | [8 empty] | STA_828 Alewife
NSTAR | Bellingham | ESMAEX-03684 | 02019 | 17.6 | Solar | 65-H4 | 2024-04-18 | 2024-05-21 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-27 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Online | [8 empty] | STA_065 Medway
NSTAR | Sharon | ESMAEX-03688 | 02067 | 15.2 | Solar | 146-H7 | 2024-04-19 | 2024-05-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2025-03-19 | Online | [8 empty] | STA_146 Walpole
NSTAR | Bellingham | ESMAEX-03689 | 02019 | 20 | Solar | 65-H4 | 2024-04-19 | 2024-08-07 | 78 |  | 78 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-27 | [7 empty] | 0 |  | 0 |  |  | 2025-03-19 | Online | [8 empty] | STA_065 Medway
NSTAR | Lincoln | ESMAEX-03690 | 01773 | 20 | Battery | 320-H6 | 2024-04-19 | 2024-05-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Online | [7 empty] | 20 | STA_320 Lexington
NSTAR | Watertown | ESMAEX-03714 | 02472 | 120 | Solar | 370-1327 | 2024-07-10 | 2024-08-06 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-29 | [7 empty] | 0 |  | 0 |  |  |  | Online | [8 empty] | STA_467 Watertown
NSTAR | Acton | ESMAEX-03717 | 01720 | 0 | Battery | 416-H1 | 2024-04-29 | 2024-05-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-29 | [7 empty] | 0 |  | 0 |  |  | 2025-04-24 | Online | [7 empty] | 20 | STA_416 Maynard
NSTAR | Arlington | ESMAEX-03703 | 02476 | 8.68 | Battery | 211-H14 | 2024-04-23 | 2024-05-21 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-19 | [7 empty] | 0 |  | 0 |  |  | 2024-11-19 | Online | [7 empty] | 8.68 | STA_211 Woburn
NSTAR | Cambridge | ESMAEX-03702 | 02138 | 23 | Solar & Battery | 823-30 | 2024-04-23 | 2024-05-10 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-20 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Online | [8 empty] | STA_828 Alewife
NSTAR | Lexington | ESMAEX-03705 | 02421 | 7.68 | Battery | 3409 | 2024-04-23 | 2024-05-21 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-31 | [7 empty] | 0 |  | 0 |  |  | 2024-11-18 | Online | [7 empty] | 7.68
NSTAR | Canton | ESMAEX-03791 | 02021 | 11.5 | Solar & Battery | 269-1320H1 | 2024-05-28 | 2024-07-12 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  | 2025-02-12 | Online | [8 empty] | STA_470 Canton
NSTAR | Brookline | ESMAEX-03719 | 02446 | 300 | Fuel Cell | 329-H8 | 2024-04-30 | 2024-05-23 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_329 Brighton
NSTAR | Framingham | ESMAEX-03706 | 01701 | 7.6 | Solar | 433-H8 | 2024-04-23 | 2024-05-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-16 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [7 empty] | 7.6 | STA_433 Speen Street
NSTAR | Bedford | ESMAEX-03852 | 01730 | 20 | Solar & Battery | 533-H7 | 2024-06-24 | 2024-07-24 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [7 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | Chatham | ESMAEX-03710 | 02633 | 36.9 | Solar & Battery | 4-95A-608 | 2024-04-24 | 2024-06-06 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-07 | [7 empty] | 0 |  | 0 |  |  | 2025-03-13 | Online |  |  |  | Cape |  |  |  | 19 | STA_968 Harwich
NSTAR | Milton | ESMAEX-03724 | 02186 | 240 | Solar | 496-H2 | 2024-05-01 | 2024-06-20 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [8 empty] | STA_496 Hyde Park
NSTAR | Milton | ESMAEX-03736 | 02186 | 240 | Solar | 60-1409H1 | 2024-05-06 | 2024-05-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-12 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [8 empty] | STA_496 Hyde Park
NSTAR | Burlington | ESMAEX-03716 | 01803 | 6.4 | Solar & Battery | 375-H6 | 2024-04-29 | 2024-05-14 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  | 2025-03-04 | Online | [7 empty] | 6.4 | STA_375 Dragon Court
NSTAR | Milton | ESMAEX-03735 | 02186 | 150 | Solar |  | 2024-05-06 | 2024-06-12 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-08 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Acton | ESMAEX-03776 | 01720 | 19 | Solar | 416-H5 | 2024-05-16 | 2024-06-12 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-03 | [7 empty] | 0 |  | 0 |  |  | 2024-10-31 | Online | [8 empty] | STA_416 Maynard
NSTAR | Acton | ESMAEX-03721 | 01720 | 7.6 | Solar | 416-H4 | 2024-05-01 | 2024-05-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-05-23 | [7 empty] | 0 |  | 0 |  |  | 2024-08-01 | Online | [7 empty] | 7.6 | STA_416 Maynard
NSTAR | Charlestown | ESMAEX-03722 | 02129 | 280 | Internal Combustion Engine | 225-184 | 2024-10-16 | 2024-11-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-24 | Online | [7 empty] | 0 | STA_250 Mystic
NSTAR | Framingham | ESMAEX-04059 | 01702 | 100 | Solar | 455-H4 | 2024-09-13 | 2024-10-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_455 West Framingham
NSTAR | Framingham | ESMAEX-04058 | 01702 | 150 | Solar | 455-H4 | 2024-09-13 | 2024-10-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-28 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_455 West Framingham
NSTAR | Chestnut Hill | ESMAEX-03777 | 02467 | 18.12 | Solar & Battery | 350-H7 | 2024-05-17 | 2024-06-13 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Carver | ESMAEX-03758 | 02330 | 4999 | Solar & Battery | 3-10-10 | 2024-05-13 | 2024-06-13 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4999 | STA_737 West Pond
NSTAR | Carver | ESMAEX-03767 | 02330 | 4999 | Solar & Battery | 3-10-10 | 2024-05-15 | 2024-05-23 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4999 | STA_737 West Pond
NSTAR | Acton | ESMAEX-03785 | 01720 | 7.6 | Solar | 416-H8 | 2024-10-17 | 2024-06-21 | -86 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-01 | [7 empty] | 0 |  | 0 |  |  | 2024-12-23 | Online | [7 empty] | 17.6 | STA_416 Maynard
NSTAR | Cambridge | ESMAEX-03813 | 02138 | 24.96 | Solar | 824-27 | 2024-06-05 | 2024-06-28 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-02 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [8 empty] | STA_828 Alewife
NSTAR | Weston | ESMAEX-03741 | 02493 | 17.99 | Solar | 282-H8 | 2024-05-08 | 2024-06-06 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  | 2024-12-02 | Technical Review | [8 empty] | STA_282 Waltham
NSTAR | Falmouth | ESMAEX-03752 | 02540 | 120 | Solar | 4-98A-98A | 2024-05-13 | 2024-07-24 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-09 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Acton | ESMAEX-03781 | 01720 | 22.34 | Solar & Battery | 416-H5 | 2024-05-21 | 2024-06-21 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-18 | Online | [7 empty] | 12.4 | STA_416 Maynard
NSTAR | North Dartmouth | ESMAEX-03845 | 02747 | 17.6 | Solar & Battery | 2-531-531 | 2024-06-17 | 2024-07-05 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  | 2025-05-16 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Stoneham | ESMAEX-03759 | 02180 | 8.77 | Battery | 211-H12 | 2024-05-14 | 2024-06-12 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  | 2025-03-03 | Online | [7 empty] | 8.77 | STA_211 Woburn
NSTAR | Provincetown | ESMAEX-03816 | 02657 | 11.6 | Battery | 4-675-675 | 2024-06-05 | 2024-06-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2024-11-19 | Online | [7 empty] | 10 | STA_976 Wellfleet
NSTAR | Hopkinton | ESMAEX-03773 | 01748 | 20 | Solar & Battery | 126-H1 | 2024-05-16 | 2024-06-12 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-12 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [7 empty] | 20 | STA_126 Hopkinton
NSTAR | Chelsea | ESMAEX-03762 | 02150 | 490 | Solar | 488-H7 | 2024-07-23 | 2024-08-16 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-11 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_488 Chelsea
NSTAR | Jamaica Plain | ESMAEX-03783 | 02130 | 20 | Solar | 284-01 | 2024-05-21 | 2024-06-13 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-28 | [7 empty] | 0 |  | 0 |  |  | 2025-09-22 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Boston | ESMAEX-03847 | 02127 | 50 | Solar | 385-H1 | 2024-06-18 | 2024-08-07 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Online | [8 empty] | STA_385D K Street
NSTAR | Sudbury | ESMAEX-03789 | 01776 | 20 | Solar | 342-H2 | 2024-05-23 | 2024-06-19 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Milton | ESMAEX-03796 | 02186 | 23 | Solar & Battery | 362-1207H1 | 2024-05-28 | 2024-06-24 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-16 | [7 empty] | 0 |  | 0 |  |  | 2024-11-14 | Online | [7 empty] | 19.92
NSTAR | Vineyard Haven | ESMAEX-03788 | 02568 | 16.8 | Solar | 4-91-91 | 2024-05-23 | 2024-06-06 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-28 | [7 empty] | 0 |  | 0 |  |  | 2025-04-04 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Waltham | ESMAEX-03794 | 02452 | 16.72 | Battery | 450-H6 | 2024-05-28 | 2024-06-14 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-10-10 | Online | [8 empty] | STA_450 Trapelo Road
NSTAR | Millis | ESMAEX-03790 | 02054 | 20 | Solar | 130-H2 | 2024-05-24 | 2024-06-06 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-06-25 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [7 empty] | 20 | STA_130 Holliston
NSTAR | Framingham | ESMAEX-03799 | 01701 | 46.08 | Solar | 455-H1 | 2024-05-29 | 2024-06-20 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-04 | [7 empty] | 0 |  | 0 |  |  | 2025-01-29 | Online | [7 empty] | 20 | STA_455 West Framingham
NSTAR | New Bedford | ESMAEX-03795 | 02744 | 480 | Solar | 2-69-69 | 2024-06-19 | 2024-07-12 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_611 Pine Street
NSTAR | Walpole | ESMAEX-03797 | 02081 | 20 | Solar | 146-H2 | 2024-05-29 | 2024-06-14 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-05 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Online | [8 empty] | STA_146 Walpole
NSTAR | Needham | ESMAEX-03801 | 02492 | 36.52 | Solar & Battery | 148-H2 | 2024-05-29 | 2024-10-16 | 100 |  | 100 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-12 | [7 empty] | 0 |  | 0 |  |  | 2025-05-20 | Online | [7 empty] | 20 | STA_148 Needham
NSTAR | Woburn | ESMAEX-03803 | 01801 | 10 | Solar | 375-H14 | 2024-05-29 | 2024-06-21 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-29 | [7 empty] | 0 |  | 0 |  |  | 2025-03-24 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Eastham | ESMAEX-03807 | 02642 | 249.6 | Solar | 4-94B-647 | 2024-05-31 | 2024-06-28 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-14 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_976 Wellfleet
NSTAR | Boston | ESMAEX-03848 | 02127 | 50 | Solar | 385-H1 | 2024-06-18 | 2024-08-07 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-08 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Online | [8 empty] | STA_385D K Street
NSTAR | Carlisle | ESMAEX-03810 | 01741 | 11.515 | Solar & Battery | 533-H8 | 2024-06-04 | 2024-07-05 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-13 | [7 empty] | 0 |  | 0 |  |  | 2025-03-14 | Online | [7 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | East Boston | ESMAEX-03814 | 02128 | 100 | Solar | 108-195H1 | 2024-06-05 | 2024-07-10 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-16 | [7 empty] | 0 |  | 0 |  |  | 2024-12-02 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Natick | ESMAEX-03826 | 01760 | 120 | Solar | 339-1345H | 2024-12-03 | 2025-01-22 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_433 Speen Street
NSTAR | Natick | ESMAEX-03863 | 01760 | 60.5 | Solar | 433-H9 | 2024-06-26 | 2024-07-24 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-29 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_433 Speen Street
NSTAR | Natick | ESMAEX-03864 | 01760 | 60.5 | Solar | 433-H9 | 2024-06-26 | 2024-07-24 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-30 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_433 Speen Street
NSTAR | Natick | ESMAEX-03865 | 01760 | 150 | Solar | 433-H9 | 2024-06-26 | 2024-07-24 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-25 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_433 Speen Street
NSTAR | Sherborn | ESMAEX-03818 | 01770 | 18.88 | Solar | 274-H2 | 2024-06-06 | 2024-06-28 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-10 | [7 empty] | 0 |  | 0 |  |  | 2024-10-16 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Hyannis | ESMAEX-03844 | 02601 | 100 | Solar | 4-84A-84A | 2024-06-14 | 2024-07-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-19 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Online |  |  |  | Cape |  |  |  |  | STA_920 Oak Street
NSTAR | Arlington | ESMAEX-03823 | 02476 | 15.2 | Solar | 211-H14 | 2024-06-11 | 2024-06-28 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-01 | [7 empty] | 0 |  | 0 |  |  | 2024-12-23 | Online | [8 empty] | STA_211 Woburn
NSTAR | Medway | ESMAEX-03873 | 02053 | 5 | Solar & Battery | 65-H5 | 2024-07-01 | 2024-07-31 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  | 2025-05-21 | Online | [7 empty] | 5 | STA_065 Medway
NSTAR | Chelsea | ESMAEX-03825 | 02150 | 34.6 | Solar | 488-H2 | 2024-06-11 | 2024-07-05 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-11 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_488 Chelsea
NSTAR | Winchester | ESMAEX-03840 | 01890 | 20 | Battery | 211-H7XY | 2024-06-14 | 2024-07-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-15 | Online | [7 empty] | 20 | STA_211 Woburn
NSTAR | Framingham | ESMAEX-03856 | 01702 | 100 | Solar | 2410 | 2024-06-24 | 2024-07-24 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-26 | [7 empty] | 0 |  | 0 |  |  | 2025-07-16 | Online | [8 empty] | STA_240 Framingham
NSTAR | Canton | ESMAEX-03850 | 02021 | 15.2 | Solar | 470-H4 | 2024-06-19 | 2024-07-11 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-31 | [7 empty] | 0 |  | 0 |  |  | 2024-09-25 | Online | [8 empty] | STA_470 Canton
NSTAR | Marshfield | ESMAEX-03851 | 02050 | 150 | Solar | 3-24A-24A | 2024-06-21 | 2024-07-31 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-13 | [7 empty] | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_739 Marshfield
NSTAR | Ashland | ESMAEX-03859 | 01721 | 15.2 | Solar | 455-H3 | 2024-06-25 | 2024-07-24 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-25 | [7 empty] | 0 |  | 0 |  |  | 2024-11-04 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Lexington | ESMAEX-03900 | 02421 | 9624.5 | Solar & Battery | 244-1362 | 2024-07-16 | 2024-08-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 4812.5 | STA_450 Trapelo Road
NSTAR | Medfield | ESMAEX-03858 | 02052 | 22.8 | Solar | 456-H3 | 2024-06-24 | 2024-07-11 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-07-31 | [7 empty] | 0 |  | 0 |  |  | 2025-03-21 | Online | [8 empty] | STA_456 Dover
NSTAR | Stoneham | ESMAEX-03868 | 02180 | 15.59 | Battery | 375-H2 | 2024-06-27 | 2024-07-31 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-13 | [7 empty] | 0 |  | 0 |  |  | 2025-01-10 | Online | [7 empty] | 15.59 | STA_375 Dragon Court
NSTAR | Sudbury | ESMAEX-03874 | 01776 | 20.46 | Solar | 342-H4 | 2024-07-01 | 2024-07-31 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-09 | [7 empty] | 0 |  | 0 |  |  | 2024-11-18 | Online | [8 empty] | STA_342 Sudbury
NSTAR | East Boston | ESMAEX-04153 | 02128 | 20 | Solar | 108-195H5 | 2024-10-08 | 2024-10-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  |  | Online | [8 empty] | STA_488 Chelsea
NSTAR | East Boston | ESMAEX-04152 | 02128 | 20 | Solar | 108-195H1 | 2024-10-08 | 2024-10-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  | 2025-12-29 | Online | [8 empty] | STA_488 Chelsea
NSTAR | East Boston | ESMAEX-04151 | 02128 | 20 | Solar | 108-195H1 | 2024-10-08 | 2024-10-16 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  | 2025-12-29 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Sudbury | ESMAEX-03889 | 01776 | 50 | Solar | 342-H5 | 2024-07-10 | 2024-08-09 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-09 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Stoneham | ESMAEX-03882 | 02180 | 5.7 | Solar | 375-H8 | 2024-07-02 | 2024-07-31 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  | 2025-03-03 | Online | [7 empty] | 20 | STA_375 Dragon Court
NSTAR | Canton | ESMAEX-03887 | 02021 | 120 | Solar | 470-H7 | 2024-07-09 | 2024-07-31 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-27 | [7 empty] | 0 |  | 0 |  |  | 2025-01-28 | Online | [8 empty] | STA_470 Canton
NSTAR | Maynard | ESMAEX-03886 | 01754 | 7.68 | Solar & Battery | 416-H6 | 2024-07-08 | 2024-08-07 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-05 | Online | [8 empty] | STA_416 Maynard
NSTAR | Sherborn | ESMAEX-03940 | 01770 | 15 | Solar | 240-H1 | 2024-07-31 | 2024-08-22 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-17 | [7 empty] | 0 |  | 0 |  |  | 2025-09-10 | Online | [7 empty] | 9.9 | STA_240 Framingham
NSTAR | Harwichport | ESMAEX-03912 | 02646 | 0 | Battery | 4-85-592 | 2024-07-18 | 2024-08-01 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 | [7 empty] | 0 |  | 0 |  |  | 2025-11-04 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Westwood | ESMAEX-04028 | 02090 | 20 | Battery | 148-H3 | 2024-09-04 | 2024-10-02 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  | 2025-12-24 | Online | [7 empty] | 20 | STA_148 Needham
NSTAR | Acton | ESMAEX-03911 | 01720 | 17.28 | Solar | 416-H5 | 2024-07-18 | 2024-09-18 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-09 | [7 empty] | 0 |  | 0 |  |  | 2025-02-27 | Online | [8 empty] | STA_416 Maynard
NSTAR | Walpole | ESMAEX-03903 | 02081 | 300 | Solar | 146-H4 | 2024-11-22 | 2025-01-08 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_146 Walpole
NSTAR | Stoneham | ESMAEX-03909 | 02180 | 10.62 | Solar & Battery | 375-H12 | 2024-07-17 | 2024-08-09 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-28 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Online | [7 empty] | 10.62 | STA_375 Dragon Court
NSTAR | Hopkinton | ESMAEX-03926 | 01748 | 16.8 | Solar | 126-H4 | 2024-07-26 | 2024-08-09 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-22 | [7 empty] | 0 |  | 0 |  |  | 2024-11-08 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Hopkinton | ESMAEX-03910 | 01748 | 7.6 | Solar | 126-H2 | 2024-07-18 | 2024-08-09 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-10 | [7 empty] | 0 |  | 0 |  |  | 2024-12-04 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Assonett | ESMAEX-03917 | 02702 | 15.2 | Solar | 2-605-605 | 2024-07-22 | 2024-08-07 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-12 | [7 empty] | 0 |  | 0 |  |  | 2024-11-14 | Online | [8 empty] | STA_661 Bell Rock
NSTAR | Carlisle | ESMAEX-03927 | 01741 | 19.99 | Solar | 512-1399H1 | 2024-07-26 | 2024-08-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-17 | [7 empty] | 0 |  | 0 |  |  | 2024-12-09 | Online | [7 empty] | 19.99 | STA_533 Hartwell Avenue
NSTAR | Hyannis | ESMAEX-04053 | 02601 | 150 | Solar | 4-63-63 | 2024-09-12 | 2024-12-06 | 61 |  | 61 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Woburn | ESMAEX-03923 | 01801 | 9.98 | Solar & Battery | 211-H5 | 2024-07-24 | 2024-08-09 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-26 | [7 empty] | 0 |  | 0 |  |  | 2025-01-10 | Online | [8 empty] | STA_211 Woburn
NSTAR | Hopkinton | ESMAEX-03958 | 01748 | 11.5 | Solar & Battery | 455-H8 | 2024-08-09 | 2024-08-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  | 2026-02-19 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Natick | ESMAEX-03959 | 01760 | 8.95 | Solar | 240-H5 | 2024-08-09 | 2024-08-29 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-21 | [7 empty] | 0 |  | 0 |  |  | 2025-07-21 | Online | [7 empty] | 8.95 | STA_240 Framingham
NSTAR | Hyde Park | ESMAEX-03944 | 02136 | 15.2 | Solar | 496-H7 | 2024-08-02 | 2024-08-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Natick | ESMAEX-03935 | 01760 | 20 | Solar & Battery | 433-H12 | 2024-07-30 | 2024-08-22 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-19 | [7 empty] | 0 |  | 0 |  |  | 2025-07-01 | Online | [7 empty] | 20 | STA_433 Speen Street
NSTAR | Newton Center | ESMAEX-03988 | 02459 | 50 | Solar | 292-H11 | 2024-08-22 | 2024-10-10 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 50 | STA_292 Newton Highlands
NSTAR | Newtonville | ESMAEX-03934 | 02460 | 31.2 | Solar & Battery | 1705 | 2024-07-30 | 2024-08-13 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-11 | [7 empty] | 0 |  | 0 |  |  | 2025-11-17 | Online | [7 empty] | 20 | STA_292 Newton Highlands
NSTAR | Bedford | ESMAEX-03946 | 01730 | 19.9 | Battery | 533-H3 | 2024-08-02 | 2024-08-22 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-01 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Online | [7 empty] | 19.9 | STA_533 Hartwell Avenue
NSTAR | Framingham | ESMAEX-03943 | 01701 | 20 | Solar | 455-H1 | 2024-08-02 | 2024-08-14 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-08-27 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Milton | ESMAEX-03969 | 02186 | 51.456 | Solar | 362-1209H2 | 2024-08-14 | 2024-08-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-18 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Somerville | ESMAEX-03945 | 02145 | 27.3 | Solar | 250-1N81H1 | 2024-08-02 | 2024-08-15 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-15 | Online | [8 empty] | STA_250 Mystic
NSTAR | Newtonville | ESMAEX-03948 | 02460 | 20 | Solar & Battery | 467-H5 | 2024-08-07 | 2024-08-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_467 Watertown
NSTAR | Natick | ESMAEX-03947 | 01760 | 17.202 | Solar | 23-H1 | 2024-08-06 | 2024-08-15 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  | 2024-11-27 | Online | [8 empty] | STA_240 Framingham
NSTAR | Newton | ESMAEX-03974 | 02458 | 10 | Battery | 277-05 | 2024-08-15 | 2024-08-29 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-22 | [7 empty] | 0 |  | 0 |  |  | 2025-01-02 | Online | [8 empty] | STA_467 Watertown
NSTAR | Winchester | ESMAEX-03949 | 01890 | 20 | Solar & Battery | 211-H7XY | 2024-08-08 | 2024-08-29 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-20 | [7 empty] | 0 |  | 0 |  |  | 2025-10-02 | Online | [7 empty] | 20 | STA_211 Woburn
NSTAR | Sharon | ESMAEX-03955 | 02067 | 12.4 | Battery | 146-H1 | 2024-08-08 | 2024-08-29 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  | 2025-04-18 | Online | [7 empty] | 12.4 | STA_146 Walpole
NSTAR | Natick | ESMAEX-03965 | 01760 | 10.1 | Battery | 240-H1 | 2024-08-14 | 2024-08-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-14 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [7 empty] | 10.1 | STA_240 Framingham
NSTAR | Acton | ESMAEX-03991 | 01720 | 5 | Battery | 416-H8 | 2024-08-23 | 2024-10-02 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-01 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [8 empty] | STA_416 Maynard
NSTAR | Arlington | ESMAEX-03976 | 02476 | 15.2 | Solar | 320-H7 | 2024-08-16 | 2024-10-09 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [7 empty] | 8.16 | STA_320 Lexington
NSTAR | Plymouth | ESMAEX-04000 | 02360 | 3997.8 | Solar & Battery | 3-11-11 | 2024-08-26 | 2024-09-18 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 3997.8 | STA_737 West Pond
NSTAR | Natick | ESMAEX-03996 | 01760 | 20 | Battery | 240-H1 | 2024-08-23 | 2024-09-18 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-31 | [7 empty] | 0 |  | 0 |  |  | 2025-06-03 | Online | [7 empty] | 20 | STA_240 Framingham
NSTAR | Woburn | ESMAEX-03995 | 01801 | 20 | Solar & Battery | 533-H9 | 2024-08-23 | 2024-09-23 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-31 | [7 empty] | 0 |  | 0 |  |  | 2025-03-05 | Online | [7 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | Newton | ESMAEX-03980 | 02135 | 130 | Solar | 467-H3 | 2024-08-20 | 2024-10-25 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-10 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [8 empty] | STA_467 Watertown
NSTAR | Carver | ESMAEX-03999 | 02330 | 3997.8 | Solar & Battery | 3-11-11 | 2024-08-26 | 2024-09-18 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 3997.8 | STA_737 West Pond
NSTAR | Roxbury | ESMAEX-03992 | 02119 | 120 | Solar | 465-129H1 | 2024-08-23 | 2024-09-18 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-20 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [8 empty] | STA_106 Andrew Square
NSTAR | Acton | ESMAEX-03993 | 01720 | 10 | Battery | 416-H1 | 2024-08-23 | 2024-09-18 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-09 | [7 empty] | 0 |  | 0 |  |  | 2025-09-12 | Online | [7 empty] | 0 | STA_416 Maynard
NSTAR | Carlisle | ESMAEX-04022 | 01741 | 18.88 | Solar | 512-1399H1 | 2024-08-30 | 2024-10-02 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  | 2025-01-08 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Waltham | ESMAEX-04003 | 02451 | 14.2 | Battery | 450-H4 | 2024-08-27 | 2024-09-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  | 2025-03-18 | Online | [7 empty] | 14.2 | STA_450 Trapelo Road
NSTAR | Sharon | ESMAEX-04004 | 02067 | 10 | Battery | 146-H1 | 2024-08-27 | 2024-09-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-22 | [7 empty] | 0 |  | 0 |  |  | 2025-02-07 | Online | [7 empty] | 10 | STA_146 Walpole
NSTAR | Canton | ESMAEX-04007 | 02021 | 990 | Solar | 269-1321H2 | 2024-09-24 | 2024-10-25 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 990 | STA_470 Canton
NSTAR | Canton | ESMAEX-04009 | 02021 | 320 | Solar | 470-H10 | 2024-09-23 | 2024-11-13 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2020-07-23 | Compliance Documents | [8 empty] | STA_470 Canton
NSTAR | West Roxbury | ESMAEX-04011 | 02132 | 17.6 | Solar & Battery | 496-H6 | 2024-08-27 | 2024-09-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-09 | [7 empty] | 0 |  | 0 |  |  | 2025-06-12 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Cotuit | ESMAEX-04012 | 02635 | 15.2 | Solar & Battery | 4-88-88 | 2024-08-27 | 2024-09-23 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  | 2025-06-18 | Online |  |  |  | Cape |  |  |  |  | STA_946 Mashpee
NSTAR | Cambridge | ESMAEX-04017 | 02139 | 50 | Solar | 814-12 | 2024-08-29 | 2025-01-13 | 97 |  | 97 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-27 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_402 Newton Street
NSTAR | Eastham | ESMAEX-04020 | 02642 | 11.5 | Battery | 4-94A-94A | 2024-08-30 | 2024-09-23 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-05-16 | Online | [8 empty] | STA_975 Orleans
NSTAR | Lexington | ESMAEX-04027 | 02421 | 27.3 | Solar | 533-H2 | 2024-09-04 | 2024-10-02 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  | 2025-10-17 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Sherborn | ESMAEX-04034 | 01770 | 16.104 | Solar | 240-H1 | 2024-09-05 | 2024-10-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2024-12-12 | Online | [8 empty] | STA_240 Framingham
NSTAR | Norfolk | ESMAEX-04031 | 02056 | 37 | Solar & Battery | 146-H10 | 2024-09-05 | 2024-11-13 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_146 Walpole
NSTAR | Westport | ESMAEX-04049 | 02790 | 25.242 | Solar & Battery | 2-523-523 | 2024-09-11 | 2024-10-10 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  | 2024-12-27 | Online |  |  |  | Dartmouth-Westport |  |  |  | 20 | STA_657 Fisher Road
NSTAR | Waltham | ESMAEX-04050 | 02451 | 140 | Solar | 282-H2 | 2024-09-11 | 2024-10-31 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-06 | [7 empty] | 0 |  | 0 |  |  | 2025-09-25 | Online | [8 empty] | STA_282 Waltham
NSTAR | West Barnstable | ESMAEX-04110 | 02668 | 22.09 | Solar | 4-84A-84A | 2024-09-26 | 2024-10-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-06 | [7 empty] | 0 |  | 0 |  |  | 2025-03-27 | Online | [8 empty] | STA_920 Oak Street
NSTAR | Newton | ESMAEX-04045 | 02460 | 27.3 | Solar | 467-H3 | 2024-09-09 | 2024-09-23 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_467 Watertown
EMA | Carver | ESMAEX-04072 | 02330 | 4980 | Solar & Battery | 3-10-929 | 2024-09-19 | 2024-10-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4980 | STA_737 West Pond
NSTAR | Carver | ESMAEX-04073 | 02330 | 4980 | Solar & Battery | 3-11-11 | 2024-09-19 | 2024-10-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth | Hold In Queue |  |  | 4980 | STA_737 West Pond
NSTAR | Framingham | ESMAEX-04048 | 01701 | 17.3 | Solar | 278-H1 | 2024-09-11 | 2024-09-23 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-09-30 | [7 empty] | 0 |  | 0 |  |  | 2025-01-16 | Online | [7 empty] | 3.8 | STA_278 Saxonville
NSTAR | Brookline | ESMAEX-04052 | 02445 | 7.67 | Solar & Battery | 315-H2 | 2024-09-11 | 2024-10-25 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Online | [7 empty] | 20
NSTAR | Sudbury | ESMAEX-04055 | 01776 | 15.2 | Solar & Battery | 342-H7 | 2024-09-13 | 2024-10-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-10 | [7 empty] | 0 |  | 0 |  |  | 2025-05-22 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Westwood | ESMAEX-04051 | 02090 | 7.5 | Solar | 148-H3 | 2024-09-11 | 2024-10-10 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-25 | [7 empty] | 0 |  | 0 |  |  | 2025-03-07 | Online | [8 empty] | STA_148 Needham
NSTAR | Watertown | ESMAEX-04116 | 02472 | 372 | Solar | 370-1327 | 2024-09-27 | 2024-10-15 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-29 | [7 empty] | 0 |  | 0 |  |  |  | Online | [8 empty] | STA_467 Watertown
NSTAR | Natick | ESMAEX-04070 | 01760 | 20 | Battery | 240-H6 | 2024-09-18 | 2024-10-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-03-06 | Online | [7 empty] | 20 | STA_240 Framingham
NSTAR | Wayland | ESMAEX-04080 | 01778 | 20 | Solar & Battery | 278-H2 | 2024-09-20 | 2024-10-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2025-03-13 | Online | [7 empty] | 20 | STA_278 Saxonville
NSTAR | Dover | ESMAEX-04060 | 02030 | 16.2 | Solar | 456-H5 | 2024-09-13 | 2024-10-21 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-20 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Online | [8 empty] | STA_456 Dover
NSTAR | Kingston | ESMAEX-04062 | 02364 | 498 | Solar | 3-15-15 | 2024-09-13 | 2024-10-10 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-21 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_735 Kingston
NSTAR | Falmouth | ESMAEX-04064 | 02540 | 17.644 | Solar & Battery | 4-72-72 | 2024-09-17 | 2024-10-04 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-23 | [7 empty] | 0 |  | 0 |  |  | 2025-05-15 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Wayland | ESMAEX-04066 | 01778 | 11.5 | Battery | 433-H2 | 2024-09-17 | 2024-10-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  | 2025-04-23 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Carver | ESMAEX-04077 | 02330 | 996 | Solar & Battery | 3-81-81 | 2024-09-19 | 2024-10-25 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process |  |  |  | STA_713 Tremont
NSTAR | Woburn | ESMAEX-04071 | 01801 | 15.744 | Solar | 325-03 | 2024-09-19 | 2024-10-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-31 | [7 empty] | 0 |  | 0 |  |  | 2025-03-05 | Online | [8 empty] | STA_211 Woburn
NSTAR | Lexington | ESMAEX-04078 | 02421 | 11.5 | Solar & Battery | 320-H2 | 2024-09-19 | 2024-10-02 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-05 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Online | [7 empty] | 7.2 | STA_320 Lexington
NSTAR | Canton | ESMAEX-04111 | 02021 | 13.8 | Battery | 470-H10 | 2024-09-26 | 2024-10-15 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-15 | [7 empty] | 0 |  | 0 |  |  | 2025-03-12 | Online | [7 empty] | 13.8 | STA_470 Canton
NSTAR | Canton | ESMAEX-04079 | 02021 | 20 | Solar & Battery | 269-1320H1 | 2024-09-19 | 2024-10-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-14 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Online | [7 empty] | 20 | STA_470 Canton
NSTAR | Holliston | ESMAEX-04083 | 01746 | 23 | Solar & Battery | 65-H5 | 2024-09-20 | 2024-12-03 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-09 | [7 empty] | 0 |  | 0 |  |  | 2025-06-20 | Online | [7 empty] | 20 | STA_065 Medway
NSTAR | Dover | ESMAEX-04137 | 02030 | 23 | Solar & Battery | 456-H3 | 2024-10-03 | 2024-10-15 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-29 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Online | [7 empty] | 20 | STA_456 Dover
NSTAR | Burlington | ESMAEX-04102 | 01803 | 20 | Battery | 346-1395H1 | 2024-09-25 | 2024-10-15 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-15 | [7 empty] | 0 |  | 0 |  |  | 2025-09-18 | Online | [7 empty] | 20 | STA_391 Burlington
NSTAR | Dover | ESMAEX-04089 | 02030 | 20.1 | Solar | 148-H3 | 2024-09-23 | 2024-10-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-10-23 | [7 empty] | 0 |  | 0 |  |  | 2025-07-24 | Online | [8 empty] | STA_148 Needham
NSTAR | Vineyard Haven | ESMAEX-04135 | 02568 | 50 | Solar |  | 2024-10-03 | 2024-10-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-22 | [7 empty] | 0 |  | 0 |  |  | 2025-05-15 | Online |  |  |  | Cape
NSTAR | North Dartmouth | ESMAEX-04101 | 02747 | 11.88 | Solar | 2-541-541 | 2024-09-24 | 2024-11-08 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-16 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Dartmouth-Westport |  |  |  | 19.99 | STA_651 Cross Road
NSTAR | Westwood | ESMAEX-04092 | 02090 | 20 | Solar | 456-H1 | 2024-09-24 | 2024-10-15 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-12 | [7 empty] | 0 |  | 0 |  |  | 2025-10-15 | Online | [7 empty] | 20 | STA_456 Dover
NSTAR | Needham | ESMAEX-04117 | 02492 | 5 | Battery | 148-02 | 2024-09-27 | 2024-11-12 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-04 | [7 empty] | 0 |  | 0 |  |  | 2025-04-15 | Online | [8 empty] | STA_148 Needham
NSTAR | Watertown | ESMAEX-04125 | 02472 | 920 | Solar & Battery | 467-H4 | 2024-12-19 | 2025-07-16 | 149 |  | 149 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 920 | STA_467 Watertown
NSTAR | Bass River | ESMAEX-04123 | 02664 | 7.6 | Solar & Battery | 4-92A-92A | 2024-09-27 | 2024-10-25 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-02-26 | Online |  |  |  | Cape |  |  |  | 7.6 | STA_961 Hyannis Junction
NSTAR | Kingston | ESMAEX-04140 | 02364 | 200 | Solar | 3-17-17 | 2024-10-04 | 2024-11-01 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_735 Kingston
NSTAR | Hopkinton | ESMAEX-04131 | 01748 | 7.65 | Battery | 126-H2 | 2024-10-01 | 2024-10-15 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-06 | [7 empty] | 0 |  | 0 |  |  | 2025-06-11 | Online | [7 empty] | 7.65 | STA_126 Hopkinton
NSTAR | Waltham | ESMAEX-04149 | 02451 | 13.3 | Solar | 282-H2 | 2024-10-07 | 2024-11-01 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-25 | [7 empty] | 0 |  | 0 |  |  | 2025-06-30 | Online | [8 empty] | STA_282 Waltham
NSTAR | Auburndale | ESMAEX-04178 | 02466 | 24.06 | Solar & Battery | 292-H7 | 2024-10-17 | 2024-11-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-03 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [7 empty] | 20 | STA_292 Newton Highlands
NSTAR | Lexington | ESMAEX-04134 | 02421 | 23.908 | Solar & Battery | 320-H2 | 2024-10-03 | 2024-10-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-04 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Online | [8 empty] | STA_320 Lexington
NSTAR | East Boston | ESMAEX-04159 | 02128 | 30 | Solar | 488-H5 | 2024-10-09 | 2024-11-01 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Eastham | ESMAEX-04142 | 02642 | 11.5 | Battery | 4-94A-94A | 2024-10-04 | 2024-11-01 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Online | [8 empty] | STA_975 Orleans
NSTAR | Sudbury | ESMAEX-04146 | 01776 | 25.73 | Solar & Battery | 342-H7 | 2024-10-07 | 2024-11-01 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_342 Sudbury
NSTAR | Dorchester | ESMAEX-04355 | 02122 | 180 | Solar |  | 2024-12-10 | 2025-01-27 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-13 | [7 empty] | 0 |  | 0 |  |  | 2025-09-09 | Online
NSTAR | Holliston | ESMAEX-04150 | 01746 | 14.98 | Solar | 65-H5 | 2024-10-08 | 2024-11-01 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-11 | [7 empty] | 0 |  | 0 |  |  | 2025-01-21 | Online | [8 empty] | STA_065 Medway
NSTAR | Edgartown | ESMAEX-04154 | 02539 | 17.6 | Solar |  | 2024-10-08 | 2024-10-25 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-18 | [7 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online |  |  |  | Cape
NSTAR | Chestnut Hill | ESMAEX-04158 | 02467 | 17.6 | Solar & Battery | 292-H6 | 2024-10-09 | 2024-11-01 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-07 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Online | [7 empty] | 17.6 | STA_292 Newton Highlands
NSTAR | Allston | ESMAEX-04308 | 02134 | 80 | Solar | 144-138 | 2024-11-26 | 2024-12-06 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-22 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_329 Brighton
NSTAR | Weston | ESMAEX-04204 | 02493 | 19.99 | Solar | 282-H1 | 2024-10-25 | 2024-11-01 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-15 | [7 empty] | 0 |  | 0 |  |  | 2025-10-17 | Online | [7 empty] | 19.99 | STA_282 Waltham
NSTAR | Carver | ESMAEX-04185 | 02330 | 4980 | Solar & Battery | 3-10-10 | 2024-10-17 | 2024-11-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4980 | STA_737 West Pond
NSTAR | Bedford | ESMAEX-04160 | 01730 | 49.7 | Solar | 533-H8 | 2024-10-10 | 2024-11-13 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-19 | [7 empty] | 0 |  | 0 |  |  | 2025-08-13 | Online | [7 empty] | 49.7 | STA_533 Hartwell Avenue
NSTAR | Roslindale | ESMAEX-04167 | 02131 | 11.5 | Battery | 496-H5 | 2024-10-11 | 2024-11-01 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-04 | [7 empty] | 0 |  | 0 |  |  | 2025-02-25 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Bedford | ESMAEX-04161 | 01730 | 82.9 | Solar |  | 2024-10-10 | 2024-11-13 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-02 | [7 empty] | 0 |  | 0 |  |  | 2025-07-29 | Online
NSTAR | Cambridge | ESMAEX-04195 | 02139 | 19.72 | Solar | 814-12 | 2024-10-18 | 2024-11-26 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-27 | [7 empty] | 0 |  | 0 |  |  |  | Meter | [8 empty] | STA_402 Newton Street
NSTAR | Acton | ESMAEX-04207 | 01720 | 15.2 | Solar | 416-H4 | 2024-10-25 | 2024-11-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-19 | [7 empty] | 0 |  | 0 |  |  | 2025-04-02 | Online | [8 empty] | STA_416 Maynard
NSTAR | Milton | ESMAEX-04175 | 02186 | 498 | Solar | 362-1209H2 | 2024-12-20 | 2025-01-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-10 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 498 | STA_496 Hyde Park
NSTAR | Sharon | ESMAEX-04170 | 02067 | 10 | Battery | 146-H7 | 2024-10-14 | 2024-11-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-15 | [7 empty] | 0 |  | 0 |  |  | 2025-04-23 | Online | [8 empty] | STA_146 Walpole
NSTAR | Milton | ESMAEX-04171 | 02186 | 10 | Solar & Battery | 362-1209H1 | 2024-10-14 | 2024-11-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-25 | Online | [7 empty] | 10 | STA_496 Hyde Park
NSTAR | Centerville | ESMAEX-04173 | 02632 | 17.26 | Solar | 4-82-82 | 2024-10-15 | 2024-11-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-25 | [7 empty] | 0 |  | 0 |  |  | 2025-07-11 | Online |  |  |  | Cape |  |  |  |  | STA_920 Oak Street
NSTAR | Westport | ESMAEX-04293 | 02790 | 10 | Battery | 2-523-523 | 2025-02-06 | 2024-12-27 | -31 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-05 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_657 Fisher Road
NSTAR | Carver | ESMAEX-04183 | 02330 | 996 | Solar & Battery | 3-81-950 | 2024-10-17 | 2024-11-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process |  |  |  | STA_713 Tremont
NSTAR | Carver | ESMAEX-04181 | 02330 | 4980 | Solar & Battery | 3-86-86 | 2024-10-17 | 2024-11-13 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4980 | STA_713 Tremont
NSTAR | Carver | ESMAEX-04182 | 01851 | 4980 | Solar & Battery | 3-86-86 | 2024-10-17 | 2024-11-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4980 | STA_713 Tremont
NSTAR | Waltham | ESMAEX-04179 | 02451 | 15.51 | Solar | 282-H2 | 2024-10-17 | 2024-11-01 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-25 | [7 empty] | 0 |  | 0 |  |  | 2025-11-28 | Online | [8 empty] | STA_282 Waltham
NSTAR | Norfolk | ESMAEX-04595 | 02056 | 66.6 | Solar | 146-H9 | 2025-03-05 | 2025-10-24 | 167 |  | 167 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_146 Walpole
NSTAR | Acton | ESMAEX-04198 | 01720 | 34.5 | Solar & Battery | 416-H8 | 2024-10-21 | 2024-11-12 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-21 | [7 empty] | 0 |  | 0 |  |  | 2025-06-12 | Online | [7 empty] | 20 | STA_416 Maynard
NSTAR | Weston | ESMAEX-04199 | 02493 | 17.6 | Solar | 282-H8 | 2024-10-21 | 2024-11-26 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-09 | [7 empty] | 0 |  | 0 |  |  | 2025-04-14 | Online | [7 empty] | 17.6 | STA_282 Waltham
NSTAR | Wareham | ESMAEX-04213 | 02571 | 999.45 | Solar & Battery | 3-84-84 | 2024-10-28 | 2024-12-03 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 999.45 | STA_714 Wareham
NSTAR | Carver | ESMAEX-04214 | 02330 | 4980 | Solar & Battery | 3-83-83 | 2024-10-28 | 2024-12-03 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4980 | STA_714 Wareham
NSTAR | Carver | ESMAEX-04215 | 02330 | 4980 | Solar & Battery | 3-83-83 | 2024-10-28 | 2024-12-03 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4980 | STA_714 Wareham
NSTAR | Carver | ESMAEX-04216 | 02330 | 4980 | Solar & Battery | 3-14-934 | 2024-10-28 | 2024-12-03 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Plymouth | In Queue |  |  | 4980 | STA_737 West Pond
NSTAR | Carver | ESMAEX-04219 | 02330 | 4980 | Solar & Battery | 3-14-934 | 2024-10-28 | 2024-12-04 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Hold In Queue |  |  | 4980 | STA_737 West Pond
NSTAR | Carver | ESMAEX-04218 | 02330 | 4980 | Solar & Battery | 3-10-10 | 2024-10-28 | 2024-12-04 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4980 | STA_737 West Pond
NSTAR | Carver | ESMAEX-04220 | 02330 | 4980 | Solar & Battery | 3-10-917 | 2024-10-28 | 2024-12-04 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4980 | STA_737 West Pond
NSTAR | Plympton | ESMAEX-04221 | 02367 | 4980 | Solar & Battery | 3-10-917 | 2024-10-29 | 2024-12-04 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Plymouth | Hold In Queue |  |  | 4980 | STA_737 West Pond
NSTAR | Wayland | ESMAEX-04281 | 01778 | 20 | Battery | 433-H2 | 2024-11-17 | 2024-12-05 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-20 | [7 empty] | 0 |  | 0 |  |  | 2025-10-24 | Online | [7 empty] | 20 | STA_433 Speen Street
NSTAR | West Newton | ESMAEX-04223 | 02465 | 110 | Solar | 292-H12 | 2024-10-29 | 2024-11-08 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-29 | [7 empty] | 0 |  | 0 |  |  |  | Permission to Operate | [8 empty] | STA_292 Newton Highlands
NSTAR | Acusnet | ESMAEX-04226 | 02743 | 149.76 | Solar | 2-241-241 | 2024-10-30 | 2024-11-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Marion-Fairhaven |  |  |  |  | STA_624 Wing Lane
NSTAR | Acusnet | ESMAEX-04227 | 02743 | 149.76 | Solar | 2-241-241 | 2024-10-30 | 2024-11-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Marion-Fairhaven |  |  |  |  | STA_624 Wing Lane
NSTAR | Medfield | ESMAEX-04225 | 02052 | 16.13 | Solar | 456-H5 | 2024-10-30 | 2024-11-08 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-11-22 | [7 empty] | 0 |  | 0 |  |  | 2025-03-17 | Online | [8 empty] | STA_456 Dover
NSTAR | Sudbury | ESMAEX-04232 | 01776 | 23 | Solar & Battery | 416-H7 | 2024-11-01 | 2024-12-04 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-11 | [7 empty] | 0 |  | 0 |  |  | 2025-05-21 | Online | [7 empty] | 20 | STA_416 Maynard
NSTAR | Wayland | ESMAEX-04229 | 01748 | 34.6 | Solar | 342-H1 | 2024-11-01 | 2024-11-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  | 2026-02-27 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Wayland | ESMAEX-04364 | 01778 | 11.74 | Solar | 342-H1 | 2024-12-11 | 2025-11-02 | 232 |  | 232 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-14 | [7 empty] | 0 |  | 0 |  |  | 2025-11-05 | Online | [7 empty] | 11.74 | STA_342 Sudbury
NSTAR | Oak Bluffs | ESMAEX-04236 | 02557 | 15.36 | Solar | 4-99-225 | 2024-11-01 | 2025-02-03 | 66 |  | 66 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  | 2026-01-26 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Carver | ESMAEX-04272 | 02330 | 4750 | Solar & Battery | 3-83-83 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Hold In Queue |  |  | 4750 | STA_714 Wareham
NSTAR | Carver | ESMAEX-04268 | 02330 | 990 | Solar | 3-10-10 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  |  | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04269 | 02360 | 990 | Solar | 3-11-11 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  |  | STA_737 West Pond
NSTAR | Carver | ESMAEX-04271 | 02330 | 4999 | Solar & Battery | 3-81-81 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Hold In Queue |  |  | 4999 | STA_713 Tremont
NSTAR | Carver | ESMAEX-04267 | 02330 | 990 | Solar | 3-10-929 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  |  | STA_737 West Pond
NSTAR | Carver | ESMAEX-04241 | 02330 | 4999 | Solar & Battery | 3-11-11 | 2024-11-06 | 2024-11-13 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4999 | STA_737 West Pond
NSTAR | West Yarmouth | ESMAEX-04247 | 02673 | 10 | Battery | 4-63-532 | 2024-11-07 | 2024-12-19 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-02 | [7 empty] | 0 |  | 0 |  |  | 2025-09-12 | Online |  |  |  | Cape |  |  |  | 10 | STA_961 Hyannis Junction
NSTAR | Hopkinton | ESMAEX-04244 | 01748 | 20.06 | Solar | 126-H2 | 2024-11-07 | 2025-01-08 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-11 | [7 empty] | 0 |  | 0 |  |  | 2025-06-03 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Newton Lower Falls | ESMAEX-04246 | 02462 | 1500 | Fuel Cell | 292-H2 | 2025-04-23 | 2025-05-29 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_292 Newton Highlands
NSTAR | Plymouth | ESMAEX-04253 | 02360 | 999 | Solar & Battery | 3-12-12 | 2024-11-11 | 2024-12-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 999 | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04256 | 02360 | 3500 | Solar & Battery | 3-90-90 | 2024-11-11 | 2024-11-25 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 3500 | STA_715 Valley
NSTAR | Waltham | ESMAEX-04262 | 02451 | 13.65 | Solar | 282-H2 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-22 | [7 empty] | 0 |  | 0 |  |  | 2025-08-26 | Online | [8 empty] | STA_282 Waltham
NSTAR | Sharon | ESMAEX-04250 | 02067 | 4950 | Other | 146-H1 | 2025-05-09 | 2025-07-15 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 4950 | STA_146 Walpole
NSTAR | Oak Bluffs | ESMAEX-04259 | 02557 | 17.6 | Solar | 4-99-224 | 2024-11-12 | 2024-11-26 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-24 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | East Freetown | ESMAEX-04294 | 02717 | 19 | Solar | 2-102-608 | 2024-11-22 | 2024-12-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-23 | [7 empty] | 0 |  | 0 |  |  | 2025-02-13 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Watertown | ESMAEX-04254 | 02472 | 16.2 | Solar | 467-H10 | 2024-11-11 | 2025-01-21 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-13 | [7 empty] | 0 |  | 0 |  |  | 2025-08-12 | Online | [8 empty] | STA_467 Watertown
NSTAR | Carver | ESMAEX-04255 | 02330 | 4999 | Solar & Battery | 3-81-950 | 2024-11-11 | 2024-11-21 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Phase 2 - In Process | Plymouth Phase 2 Distribution Group Study |  | 4999 | STA_713 Tremont
NSTAR | Carver | ESMAEX-04257 | 02330 | 225 | Solar | 3-11-11 | 2024-11-11 | 2024-11-19 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04258 | 02360 | 225 | Solar | 3-11-11 | 2024-11-11 | 2024-12-06 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-02 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Waltham | ESMAEX-04438 | 02453 | 33.1 | Solar | 282-H4 | 2025-01-16 | 2025-02-21 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-10 | [7 empty] | 0 |  | 0 |  |  | 2025-10-16 | Online | [8 empty] | STA_282 Waltham
NSTAR | Plymouth | ESMAEX-04273 | 02360 | 15.2 | Solar | 3-14-30J2 | 2024-11-12 | 2024-12-05 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2024-12-10 | [7 empty] | 0 |  | 0 |  |  | 2025-04-01 | Online |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Medfield | ESMAEX-04277 | 02052 | 18.705 | Solar | 146-H6 | 2024-11-14 | 2025-01-03 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-07 | [7 empty] | 0 |  | 0 |  |  | 2025-04-24 | Online | [8 empty] | STA_146 Walpole
NSTAR | Lexington | ESMAEX-04282 | 02421 | 20 | Solar & Battery | 320-H5XY | 2024-11-18 | 2024-12-05 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-23 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [7 empty] | 20 | STA_320 Lexington
NSTAR | Newton | ESMAEX-04486 | 02465 | 17.3 | Solar | 33-H3 | 2025-02-05 | 2025-02-19 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-07 | [7 empty] | 0 |  | 0 |  |  | 2025-09-12 | Online | [8 empty] | STA_282 Waltham
NSTAR | Jamaica Plain | ESMAEX-04567 | 02130 | 17.3 | Solar | 350-H2 | 2025-02-25 | 2025-03-11 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_350 Colburn Street
NSTAR | Needham | ESMAEX-04301 | 02492 | 21.5 | Solar & Battery | 148-06 | 2024-11-26 | 2025-01-15 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-05 | [7 empty] | 0 |  | 0 |  |  | 2025-06-10 | Online | [7 empty] | 20 | STA_148 Needham
NSTAR | Westwood | ESMAEX-04387 | 02090 | 150 | Solar | 469-H4 | 2024-12-17 | 2025-01-10 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_469 Ellis Avenue
NSTAR | Newton Center | ESMAEX-04315 | 02459 | 30 | Solar | 292-H3 | 2024-11-27 | 2025-01-08 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-25 | [7 empty] | 0 |  | 0 |  |  | 2025-08-15 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Medfield | ESMAEX-04317 | 02052 | 19.1 | Solar & Battery | 456-H2 | 2024-12-02 | 2025-01-31 | 44 |  | 44 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-03 | [7 empty] | 0 |  | 0 |  |  | 2025-08-21 | Online | [8 empty] | STA_456 Dover
NSTAR | Marshfield | ESMAEX-04585 | 02051 | 4998 | Other | 3-25-25 | 2025-02-28 | 2025-04-28 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | 4998 | STA_738 Duxbury
NSTAR | Westwood | ESMAEX-04345 | 02090 | 20 | Solar & Battery | 469-H2 | 2024-12-06 | 2024-12-19 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-24 | [7 empty] | 0 |  | 0 |  |  | 2025-05-20 | Online | [7 empty] | 20
NSTAR | Winchester | ESMAEX-04397 | 01890 | 31.02 | Solar | 211-H4 | 2024-12-20 | 2025-01-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-11 | [7 empty] | 0 |  | 0 |  |  | 2025-10-08 | Online | [7 empty] | 20 | STA_211 Woburn
NSTAR | Arlington | ESMAEX-04400 | 02476 | 7.59 | Solar | 211-H14 | 2024-12-20 | 2025-01-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-02 | [7 empty] | 0 |  | 0 |  |  | 2025-05-27 | Online | [8 empty] | STA_211 Woburn
NSTAR | Chelsea | ESMAEX-04326 | 02150 | 67.3 | Solar | 488-H5 | 2025-05-01 | 2025-05-26 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_488 Chelsea
NSTAR | New Bedford | ESMAEX-04327 | 02740 | 60 | Solar | 2-55-55 | 2025-08-13 | 2025-08-25 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_611 Pine Street
NSTAR | Freetown | ESMAEX-04331 | 02717 | 4980 | Solar & Battery | 2-102-102 | 2025-01-15 | 2025-01-27 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | New Bedford | Hold In Queue |  |  |  | STA_636 Industrial Park
NSTAR | Westwood | ESMAEX-04344 | 02090 | 20 | Battery | 148-H3 | 2024-12-06 | 2025-01-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-07 | [7 empty] | 0 |  | 0 |  |  | 2025-01-22 | Online | [7 empty] | 20 | STA_148 Needham
NSTAR | Yarmouthport | ESMAEX-04346 | 02675 | 7.6 | Solar | 4-90-90 | 2024-12-06 | 2025-01-08 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-07-23 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Dedham | ESMAEX-04347 | 02026 | 15.2 | Solar | 344-1412H1 | 2024-12-06 | 2025-01-03 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-23 | [7 empty] | 0 |  | 0 |  |  | 2025-09-11 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Vineyard Haven | ESMAEX-04518 | 02568 | 260 | Solar | 4-91-91 | 2025-05-06 | 2025-06-09 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Canton | ESMAEX-04383 | 02021 | 720 | Solar & Battery | 470-H7 | 2025-06-30 | 2025-08-18 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_470 Canton
NSTAR | Canton | ESMAEX-04350 | 02021 | 33 | Solar | 269-1320H1 | 2024-12-09 | 2025-01-03 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-14 | [7 empty] | 0 |  | 0 |  |  | 2025-03-26 | Online | [7 empty] | 20 | STA_470 Canton
NSTAR | Hyde Park | ESMAEX-04353 | 02136 | 200 | Solar | 344-07 | 2025-01-13 | 2025-01-27 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_496 Hyde Park
NSTAR | Dennis | ESMAEX-04354 | 02638 | 44.88 | Solar | 4-89A-552 | 2024-12-10 | 2025-01-02 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-18 | [7 empty] | 0 |  | 0 |  |  | 2025-08-12 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Weston | ESMAEX-04371 | 02493 | 80 | Solar | 282-H8 | 2024-12-23 | 2025-01-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-08 | [7 empty] | 0 |  | 0 |  |  | 2025-09-05 | Online | [8 empty] | STA_282 Waltham
NSTAR | Dedham | ESMAEX-04363 | 02026 | 17.26 | Solar | 344-1412H1 | 2024-12-11 | 2024-12-19 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-26 | [7 empty] | 0 |  | 0 |  |  | 2025-09-17 | Online | [7 empty] | 14 | STA_496 Hyde Park
NSTAR | Wayland | ESMAEX-04369 | 01778 | 22.8 | Solar | 342-H1 | 2024-12-13 |  | -32567 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_342 Sudbury
NSTAR | Burlington | ESMAEX-04441 | 01803 | 15.28 | Solar | 391-H7 | 2025-01-17 | 2025-03-03 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-18 | [7 empty] | 0 |  | 0 |  |  | 2025-07-07 | Online | [7 empty] | 15.2 | STA_391 Burlington
NSTAR | Framingham | ESMAEX-04386 | 01701 | 480 | Solar | 433-H10 | 2025-04-07 | 2025-04-28 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_433 Speen Street
NSTAR | Bourne | ESMAEX-04382 | 02532 | 450 | Solar | 4-71-455 | 2025-02-14 | 2025-03-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_946 Mashpee
NSTAR | Falmouth | ESMAEX-04421 | 02540 | 40 | Solar | 4-76-437 | 2025-01-08 | 2025-01-15 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-11 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Teaticket | ESMAEX-04396 | 02536 | 486 | Solar | 4-76-437 | 2025-06-03 | 2025-07-17 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | West Roxbury | ESMAEX-04411 | 02132 | 11.5 | Solar & Battery | 496-H6 | 2024-12-31 | 2025-01-10 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-01-10 | [7 empty] | 0 |  | 0 |  |  | 2025-06-23 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Stoneham | ESMAEX-04401 | 02180 | 15.36 | Solar & Battery | 211-H12 | 2024-12-21 | 2025-01-15 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-03 | [7 empty] | 0 |  | 0 |  |  | 2026-01-29 | Online | [8 empty] | STA_211 Woburn
NSTAR | Roxbury | ESMAEX-04402 | 02119 | 20 | Solar | 510-77H5 | 2024-12-23 | 2025-02-03 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-07 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_106 Andrew Square
NSTAR | Fairhaven | ESMAEX-04405 | 02719 | 240 | Solar | 2-230-230 | 2024-12-27 | 2025-04-23 | 83 |  | 83 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_612 Acushnet
NSTAR | New Bedford | ESMAEX-04420 | 02746 | 15.2 | Solar | 2-87-135 | 2025-01-07 | 2025-02-25 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-27 | [7 empty] | 0 |  | 0 |  |  | 2025-08-20 | Online | [8 empty] | STA_612 Acushnet
NSTAR | Dennis | ESMAEX-04408 | 02638 | 23 | Solar & Battery | 4-89A-89A | 2024-12-31 | 2025-01-15 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-17 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Falmouth | ESMAEX-04407 | 02540 | 11.5 | Battery | 4-72-72 | 2024-12-30 | 2025-03-03 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-12 | [7 empty] | 0 |  | 0 |  |  | 2025-12-10 | Online | [7 empty] | 0 | STA_933 Falmouth
NSTAR | West Tisbury | ESMAEX-04471 | 02575 | 90 | Solar & Battery | 4-97-97 | 2025-01-28 | 2025-02-25 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-03 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Weston | ESMAEX-04432 | 02493 | 20.352 | Solar | 282-H10 | 2025-01-14 | 2025-03-03 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-22 | [7 empty] | 0 |  | 0 |  |  | 2025-10-20 | Online | [7 empty] | 19.999 | STA_282 Waltham
NSTAR | Canton | ESMAEX-04417 | 02021 | 100 | Solar | 470-H4 | 2025-01-03 | 2025-01-27 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  | 2025-07-22 | Online | [8 empty] | STA_470 Canton
NSTAR | Lincoln | ESMAEX-04434 | 01773 | 15.5 | Other | 320-H6 | 2025-01-15 | 2025-01-31 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-03 | [7 empty] | 0 |  | 0 |  |  | 2025-09-04 | Online | [7 empty] | 15.5 | STA_320 Lexington
NSTAR | Bedford | ESMAEX-04430 | 01730 | 999 | Solar | 487-1378H | 2025-03-28 | 2025-04-10 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_391 Burlington
NSTAR | Hopkinton | ESMAEX-04426 | 01748 | 10 | Other | 126-H4 | 2025-01-10 | 2025-02-03 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-19 | [7 empty] | 0 |  | 0 |  |  | 2025-06-23 | Online | [7 empty] | 10 | STA_126 Hopkinton
NSTAR | West Newton | ESMAEX-04422 | 02465 | 15.2 | Solar & Battery | 316-01 | 2025-01-10 | 2025-02-03 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-04 | [7 empty] | 0 |  | 0 |  |  | 2025-06-17 | Online | [8 empty] | STA_282 Waltham
NSTAR | Acton | ESMAEX-04427 | 01720 | 19.58 | Solar & Battery | 416-H4 | 2025-01-10 | 2025-01-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-03 | [7 empty] | 0 |  | 0 |  |  | 2025-06-12 | Online | [8 empty] | STA_416 Maynard
NSTAR | Natick | ESMAEX-04534 | 01760 | 23 | Other | 23-H1 | 2025-02-18 | 2025-03-17 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-29 | [7 empty] | 0 |  | 0 |  |  | 2025-09-11 | Online | [7 empty] | 0 | STA_240 Framingham
NSTAR | Westwood | ESMAEX-04689 | 02090 | 17.48 | Solar | 148-H3 | 2025-03-26 |  | -32640 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-25 | Online | [8 empty] | STA_148 Needham
NSTAR | Burlington | ESMAEX-04477 | 01803 | 15.18 | Solar | 346-1395H1 | 2025-01-30 | 2025-02-12 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-06 | [7 empty] | 0 |  | 0 |  |  | 2025-12-23 | Online | [8 empty] | STA_391 Burlington
NSTAR | Sharon | ESMAEX-04435 | 02067 | 240 | Solar | 146-H7 | 2025-05-19 | 2025-06-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_146 Walpole
NSTAR | Milton | ESMAEX-04437 | 02186 | 17.6 | Solar & Battery | 496-H7 | 2025-01-15 | 2025-03-03 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-19 | [7 empty] | 0 |  | 0 |  |  | 2025-07-31 | Online | [7 empty] | 7.6 | STA_496 Hyde Park
NSTAR | Natick | ESMAEX-04481 | 01760 | 20 | Other | 240-H5 | 2025-02-03 | 2025-03-03 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  | 2025-11-07 | Online | [7 empty] | 20 | STA_240 Framingham
NSTAR | Lexington | ESMAEX-04440 | 02421 | 490 | Solar | 320-H2 | 2025-01-17 | 2025-02-18 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_320 Lexington
NSTAR | Edgartown | ESMAEX-04455 | 02539 | 60 | Solar | 4-97-97 | 2025-01-21 | 2025-02-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-29 | [7 empty] | 0 |  | 0 |  |  | 2026-01-21 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Walpole | ESMAEX-04454 | 02081 | 15.3 | Solar & Battery | 146-H4 | 2025-01-21 | 2025-02-07 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-02-10 | [7 empty] | 0 |  | 0 |  |  | 2025-09-09 | Online | [7 empty] | 15.3 | STA_146 Walpole
NSTAR | Carlisle | ESMAEX-04695 | 01741 | 60 | Solar & Battery | 512-1399H1 | 2025-03-26 | 2025-05-23 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-31 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 15 | STA_533 Hartwell Avenue
NSTAR | Plymouth | ESMAEX-04457 | 02360 | 15.36 | Solar | 3-72-940 | 2025-01-22 | 2025-03-14 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-08-12 | Online |  |  |  | Plymouth |  |  |  |  | STA_721 Manomet
NSTAR | Framingham | ESMAEX-04462 | 01702 | 23 | Solar & Battery | 455-H5 | 2025-01-23 | 2025-02-25 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  | 2025-11-26 | Online | [7 empty] | 19.9 | STA_455 West Framingham
NSTAR | Waltham | ESMAEX-04466 | 02451 | 4999 | Other | 450-H7 | 2025-04-09 | 2025-04-17 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 4999 | STA_450 Trapelo Road
NSTAR | Acton | ESMAEX-04469 | 01720 | 23 | Other | 416-H8 | 2025-01-28 | 2025-03-03 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 | [7 empty] | 0 |  | 0 |  |  | 2025-10-24 | Online | [7 empty] | 20 | STA_416 Maynard
NSTAR | Sandwich | ESMAEX-04472 | 02563 | 7.68 | Solar | 4-455-455 | 2025-01-28 | 2025-02-25 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-10-07 | Online |  |  |  | Cape |  |  |  |  | STA_946 Mashpee
NSTAR | Roxbury Crossing | ESMAEX-04674 | 02120 | 84.6 | Solar | 350-H6 | 2025-03-20 | 2025-05-28 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_350 Colburn Street
NSTAR | Bedford | ESMAEX-04555 | 01730 | 22.8 | Solar | 322-1397H1 | 2025-02-21 | 2025-03-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  | 2025-11-19 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Roxbury Crossing | ESMAEX-04684 | 02120 | 84.6 | Solar | 350-H6 | 2025-03-25 | 2025-05-28 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_350 Colburn Street
NSTAR | Sudbury | ESMAEX-04609 | 01776 | 15.76 | Solar | 342-H2 | 2025-03-10 | 2025-03-21 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-01 | Online | [7 empty] | 9.29 | STA_342 Sudbury
NSTAR | North Truro | ESMAEX-04490 | 02652 | 11.5 | Solar & Battery | 4-96-96 | 2025-02-06 | 2025-03-21 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 | [7 empty] | 0 |  | 0 |  |  | 2025-09-11 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Edgartown | ESMAEX-04537 | 02539 | 4.72 | Solar | 4-75-123 | 2025-02-19 | 2025-03-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-30 | [7 empty] | 0 |  | 0 |  |  | 2025-07-10 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Millis | ESMAEX-04479 | 02054 | 25 | Solar | 130-H2 | 2025-02-03 | 2025-02-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  | 2025-04-29 | Online | [7 empty] | 20 | STA_130 Holliston
NSTAR | North Eastham | ESMAEX-04488 | 02651 | 15.2 | Solar & Battery | 4-94B-956 | 2025-02-05 | 2025-03-04 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-07-21 | Online | [7 empty] | 7.6 | STA_976 Wellfleet
NSTAR | Marion | ESMAEX-04485 | 02738 | 15.2 | Solar | 3-85-85 | 2025-02-13 | 2025-03-19 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 | [7 empty] | 0 |  | 0 |  |  | 2025-05-14 | Online |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | Newton | ESMAEX-04493 | 02458 | 23 | Solar & Battery | 467-H12 | 2025-02-06 | 2025-03-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 | [7 empty] | 0 |  | 0 |  |  | 2025-09-19 | Online | [7 empty] | 19.9 | STA_467 Watertown
NSTAR | North Dartmouth | ESMAEX-04499 | 02747 | 15.2 | Solar | 2-533-503 | 2025-02-07 | 2025-03-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-10 | [7 empty] | 0 |  | 0 |  |  | 2025-05-09 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Acton | ESMAEX-04502 | 01720 | 23 | Solar & Battery | 416-H2 | 2025-02-07 | 2025-03-21 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-27 | [7 empty] | 0 |  | 0 |  |  | 2025-12-16 | Online | [7 empty] | 20 | STA_416 Maynard
NSTAR | Norfolk | ESMAEX-04491 | 02056 | 20 | Solar & Battery | 146-H3 | 2025-02-07 | 2025-02-24 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-03 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_146 Walpole
NSTAR | Canton | ESMAEX-04741 | 02021 | 20 | Solar & Battery | 269-1320H1 | 2025-04-05 | 2025-09-19 | 120 |  | 120 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 7.475 | STA_470 Canton
NSTAR | Woburn | ESMAEX-04492 | 01801 | 20.1 | Solar | 375-H6 | 2025-02-06 | 2025-03-07 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-12 | [7 empty] | 0 |  | 0 |  |  | 2025-07-28 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Woburn | ESMAEX-04512 | 01801 | 22.66 | Solar & Battery | 211-H8 | 2025-02-27 | 2025-03-11 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-19 | Online | [8 empty] | STA_211 Woburn
NSTAR | Sharon | ESMAEX-04496 | 02067 | 15.2 | Solar | 470-H12 | 2025-02-06 | 2025-03-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-14 | [7 empty] | 0 |  | 0 |  |  | 2025-04-16 | Online | [8 empty] | STA_470 Canton
NSTAR | South Walpole | ESMAEX-04522 | 02071 | 100 | Solar | 146-H3 | 2025-02-14 | 2025-03-14 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_146 Walpole
NSTAR | Sherborn | ESMAEX-04501 | 01770 | 23 | Solar & Battery | 274-H2 | 2025-02-07 | 2025-03-05 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-13 | [7 empty] | 0 |  | 0 |  |  | 2025-04-26 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Boston | ESMAEX-04500 | 02130 | 84.6 | Solar |  | 2025-02-07 |  | -32607 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | [8 empty] | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Walpole | ESMAEX-04525 | 02081 | 18.78 | Solar & Battery | 146-H4 | 2025-02-15 | 2025-03-04 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-21 | [7 empty] | 0 |  | 0 |  |  | 2025-08-11 | Online | [7 empty] | 18.78 | STA_146 Walpole
NSTAR | Rochester | ESMAEX-04503 | 02770 | 996 | Solar & Battery | 3-702-702 | 2025-03-17 | 2025-04-08 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-06 |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Marion-Fairhaven | Individual Study |  |  |  | STA_745 ROCHESTER
NSTAR | Newton | ESMAEX-04830 | 02456 | 15.58 | Solar | 316-01 | 2025-04-23 | 2025-05-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Carlisle | ESMAEX-04506 | 01741 | 15.2 | Solar | 533-H8 | 2025-02-10 | 2025-02-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  | 2025-06-04 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Burlington | ESMAEX-04579 | 01803 | 4.5 | Solar | 346-1395H1 | 2025-02-27 | 2025-04-10 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-31 | Online | [7 empty] | 4.5 | STA_391 Burlington
NSTAR | Needham | ESMAEX-04563 | 02494 | 50 | Solar | 292-H9 | 2025-02-25 | 2025-03-04 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_292 Newton Highlands
NSTAR | Lincoln | ESMAEX-04519 | 01773 | 17.16 | Solar | 320-H8 | 2025-02-14 | 2025-03-14 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 | [7 empty] | 0 |  | 0 |  |  | 2025-06-16 | Online | [7 empty] | 14.69 | STA_320 Lexington
NSTAR | Wayland | ESMAEX-04560 | 01778 | 18.4 | Solar & Battery | 278-H2 | 2025-02-24 | 2025-04-09 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-20 | Online | [8 empty] | STA_278 Saxonville
NSTAR | Vineyard Haven | ESMAEX-04529 | 02568 | 15.2 | Solar | 4-91-228 | 2025-02-17 | 2025-02-24 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 | [7 empty] | 0 |  | 0 |  |  | 2025-10-16 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Cambridge | ESMAEX-04531 | 02138 | 29.31 | Solar & Battery | 821-22 | 2025-02-18 | 2025-03-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-07 | [7 empty] | 0 |  | 0 |  |  | 2025-08-19 | Online | [7 empty] | 20 | STA_831 Putnam
NSTAR | Bedford | ESMAEX-04669 | 01730 | 32.256 | Solar & Battery | 533-H7 | 2025-03-19 | 2025-03-30 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-12 | Online | [7 empty] | 19.9 | STA_533 Hartwell Avenue
NSTAR | Canton | ESMAEX-04538 | 02021 | 250 | Solar | 470-H7 | 2025-03-31 | 2025-04-28 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_470 Canton
NSTAR | Acton | ESMAEX-04539 | 01720 | 7.6 | Solar | 512-1399H1 | 2025-02-19 | 2025-03-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-17 | [7 empty] | 0 |  | 0 |  |  | 2025-09-18 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Wayland | ESMAEX-04541 | 01778 | 15.2 | Solar | 433-H2 | 2025-02-19 | 2025-03-10 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-12 | [7 empty] | 0 |  | 0 |  |  | 2025-08-18 | Online | [8 empty] | STA_433 Speen Street
NSTAR | Needham | ESMAEX-04571 | 02492 | 16.89 | Solar | 148-07 | 2025-02-26 | 2025-03-11 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-18 | Online | [8 empty] | STA_148 Needham
NSTAR | East Freetown | ESMAEX-04551 | 02717 | 20 | Solar & Battery | 2-108-108 | 2025-02-20 | 2025-03-06 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-31 | [7 empty] | 0 |  | 0 |  |  | 2025-06-30 | Online |  |  |  | Cape |  |  |  | 20 | STA_636 Industrial Park
NSTAR | Dover | ESMAEX-04544 | 02030 | 19.58 | Solar & Battery | 456-H5 | 2025-02-20 | 2025-03-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-21 | [7 empty] | 0 |  | 0 |  |  | 2025-07-23 | Online | [8 empty] | STA_456 Dover
NSTAR | Lincoln | ESMAEX-04546 | 01773 | 18.43 | Solar | 320-H8 | 2025-02-20 | 2025-03-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 | [7 empty] | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_320 Lexington
NSTAR | Framingham | ESMAEX-04547 | 01701 | 7.6 | Solar | 342-H4 | 2025-02-20 | 2025-03-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 | [7 empty] | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | STA_342 Sudbury
NSTAR | New Bedford | ESMAEX-04597 | 02740 | 80 | Solar | 2-53-65 | 2025-03-05 | 2025-04-28 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_611 Pine Street
NSTAR | Westport | ESMAEX-04580 | 02790 | 13.8 | Solar & Battery | 2-522-522 | 2025-02-27 | 2025-06-18 | 79 |  | 79 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 11.9 | STA_657 Fisher Road
NSTAR | Newtonville | ESMAEX-04552 | 02460 | 15.2 | Solar | 467-H5 | 2025-02-24 | 2025-03-06 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-31 | Online | [8 empty] | STA_467 Watertown
NSTAR | Chatham | ESMAEX-04615 | 02633 | 23 | Other | 4-95B-95B | 2025-03-11 | 2025-07-24 | 97 |  | 97 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-29 | Online | [7 empty] | 19.9 | STA_975 Orleans
NSTAR | Roslindale | ESMAEX-04613 | 02131 | 110 | Solar | 1306 | 2025-03-11 | 2025-03-21 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-31 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Oak Bluffs | ESMAEX-04561 | 02557 | 15.36 | Solar | 4-75-75 | 2025-02-24 | 2025-03-04 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Centerville | ESMAEX-04574 | 02632 | 11.5 | Other | 4-82-82 | 2025-02-26 | 2025-03-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-29 | Online |  |  |  | Cape |  |  |  |  | STA_920 Oak Street
NSTAR | Sharon | ESMAEX-04575 | 02067 | 10 | Solar | 146-H1 | 2025-02-26 | 2025-03-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-14 | Online | [7 empty] | 10 | STA_146 Walpole
NSTAR | Hyannis | ESMAEX-04569 | 02601 | 36.16 | Solar | 4-63-532 | 2025-03-05 | 2025-04-25 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-23 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Lexington | ESMAEX-04572 | 02421 | 9 | Solar | 320-H2 | 2025-02-26 | 2025-03-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-27 | Online | [8 empty] | STA_320 Lexington
NSTAR | Watertown | ESMAEX-04581 | 02472 | 8.25 | Solar | 467-H9 | 2025-02-28 | 2025-03-06 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-09 | Online | [8 empty] | STA_467 Watertown
NSTAR | Kingston | ESMAEX-04582 | 02364 | 1800 | Solar & Battery | 3-17-17 | 2025-05-01 | 2025-05-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2023-03-30 | Online |  |  |  | Plymouth |  |  |  |  | STA_735 Kingston
NSTAR | Centerville | ESMAEX-04587 | 02632 | 19.1 | Solar & Battery | 4-82-82 | 2025-02-28 | 2025-03-17 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_920 Oak Street
NSTAR | Falmouth | ESMAEX-04621 | 02540 | 0 | Other | 4-76-436 | 2025-03-12 | 2025-05-07 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-27 | Online |  |  |  | Cape |  |  |  | 0 | STA_933 Falmouth
NSTAR | Dover | ESMAEX-04589 | 02030 | 23 | Solar & Battery | 456-H5 | 2025-03-03 | 2025-03-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-08 | Online | [7 empty] | 20 | STA_456 Dover
NSTAR | Ashland | ESMAEX-04591 | 01721 | 7.6 | Solar | 455-H8 | 2025-03-05 | 2025-04-25 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-05 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Osterville | ESMAEX-04658 | 02655 | 57.5 | Solar & Battery | 4-88-88 | 2025-03-18 | 2025-03-31 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-05-29 | Online |  |  |  | Cape |  |  |  | 19.9 | STA_946 Mashpee
NSTAR | Brighton | ESMAEX-04666 | 02135 | 19 | Solar |  | 2025-03-19 | 2025-03-28 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Hyde Park | ESMAEX-04903 | 02136 | 250 | Solar | 344-1411H | 2025-05-12 | 2025-07-02 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_496 Hyde Park
NSTAR | New Bedford | ESMAEX-04596 | 02745 | 15.2 | Solar | 2-105-105 | 2025-03-05 | 2025-05-01 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-09 | Online | [8 empty] | STA_636 Industrial Park
NSTAR | Norfolk | ESMAEX-04601 | 02056 | 18.81 | Solar | 65-H1 | 2025-03-05 | 2025-04-17 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-23 | Online | [8 empty] | STA_065 Medway
NSTAR | Provincetown | ESMAEX-04763 | 02657 | 17.3 | Solar | 4-675-675 | 2025-04-08 | 2025-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_976 Wellfleet
NSTAR | Provincetown | ESMAEX-04762 | 02657 | 27.3 | Solar | 4-675-675 | 2025-04-08 | 2025-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_976 Wellfleet
NSTAR | Rochester | ESMAEX-04606 | 02770 | 4999 | Solar | 3-703-703 | 2025-03-07 | 2025-04-30 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-03 |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Marion-Fairhaven | Individual Study |  |  |  | STA_745 ROCHESTER
NSTAR | Provincetown | ESMAEX-04761 | 02657 | 27.3 | Solar | 4-675-675 | 2025-04-08 | 2025-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_976 Wellfleet
NSTAR | Provincetown | ESMAEX-04759 | 02110 | 17.3 | Solar | 4-675-675 | 2025-04-08 | 2025-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_976 Wellfleet
NSTAR | Canton | ESMAEX-04610 | 02021 | 5.76 | Solar | 470-H1 | 2025-03-10 | 2025-03-17 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-17 | Online | [8 empty] | STA_470 Canton
NSTAR | Walpole | ESMAEX-04676 | 02081 | 980 | Solar | 146-H8 | 2025-11-06 | 2025-11-20 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_146 Walpole
NSTAR | Dartmouth | ESMAEX-04675 | 02747 | 980 | Solar | 2-532-532 | 2025-11-06 | 2025-11-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_651 Cross Road
NSTAR | Plymouth | ESMAEX-04673 | 02360 | 640 | Solar | 3-14-911 | 2025-11-06 | 2025-11-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_737 West Pond
NSTAR | Holliston | ESMAEX-04611 | 01746 | 15.36 | Solar | 65-H5 | 2025-03-11 | 2025-03-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-08 | Online | [8 empty] | STA_065 Medway
NSTAR | Carlisle | ESMAEX-04619 | 01741 | 9.9 | Solar | 512-1399H1 | 2025-03-12 | 2025-03-28 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-05-14 | Online | [7 empty] | 9.9 | STA_533 Hartwell Avenue
NSTAR | Waltham | ESMAEX-04625 | 02452 | 15.2 | Solar | 282-H7 | 2025-03-13 | 2025-03-25 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | West Falmouth | ESMAEX-04618 | 02574 | 30.72 | Other | 4-98A-98A | 2025-03-11 | 2025-03-27 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  | 6.5 | STA_933 Falmouth
NSTAR | Newton Center | ESMAEX-04690 | 02459 | 16.8 | Solar | 443-02 | 2025-03-26 |  | -32640 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-12 | Online | [8 empty] | STA_110 Baker Street
NSTAR | Cambridge | ESMAEX-04705 | 02139 | 90 | Solar | 814-12 | 2025-03-28 | 2025-04-28 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_402 Newton Street
NSTAR | Sharon | ESMAEX-04679 | 02067 | 8.784 | Solar | 146-H7 | 2025-03-24 | 2025-04-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-18 | Online | [7 empty] | 18.38 | STA_146 Walpole
NSTAR | Watertown | ESMAEX-04636 | 02472 | 11.5 | Other | 124-04 | 2025-03-14 | 2025-04-08 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_467 Watertown
NSTAR | West Wareham | ESMAEX-04713 | 02576 | 5 | Other | 3-85-85 | 2025-03-30 | 2025-04-18 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-07 | Online |  |  |  | Plymouth |  |  |  | 0 | STA_713 Tremont
NSTAR | Boston | ESMAEX-04728 | 02119 | 50 | Solar | 52-1487H | 2025-04-02 | 2025-05-06 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Brookline | ESMAEX-04714 | 02446 | 105 | Solar | 329-H8 | 2025-03-31 | 2025-09-24 | 127 |  | 127 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_329 Brighton
NSTAR | Plymouth | ESMAEX-04631 | 02360 | 425 | Solar | 3-13-936 | 2025-04-11 | 2025-05-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04634 | 02360 | 185 | Solar | 3-13-943 | 2025-04-11 | 2025-04-24 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04635 | 02360 | 195 | Solar | 3-13-943 | 2025-04-11 | 2025-05-23 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [8 empty] | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-04643 | 02360 | 499.9 | Solar | 3-13-936 | 2025-04-11 | 2025-05-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Impact Study | [7 empty] | 499.9 | STA_737 West Pond
NSTAR | Chilmark | ESMAEX-04641 | 02535 | 16.24 | Solar | 4-97-97 | 2025-03-14 | 2025-03-28 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-05-15 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Lexington | ESMAEX-04660 | 02420 | 9.57 | Solar | 391-H11 | 2025-03-18 | 2025-03-28 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-10 | Online | [8 empty] | STA_391 Burlington
NSTAR | Acton | ESMAEX-04646 | 01720 | 23.81 | Solar & Battery | 416-H5 | 2025-03-17 | 2025-03-31 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-17 | Online | [7 empty] | 20 | STA_416 Maynard
NSTAR | East Boston | ESMAEX-04647 | 02128 | 15.2 | Solar | 108-196H1 | 2025-03-17 | 2025-04-17 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-09 | Online | [8 empty] | STA_488 Chelsea
NSTAR | Bedford | ESMAEX-04652 | 01730 | 22.6 | Solar & Battery | 533-H7 | 2025-03-18 | 2025-05-20 | 45 |  | 45 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-19 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Brighton | ESMAEX-04649 | 02135 | 23.76 | Solar & Battery | 315-H7 | 2025-03-18 | 2025-03-31 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-30 | Online | [7 empty] | 11.54
NSTAR | Wareham | ESMAEX-04650 | 02571 | 990 | Solar | 3-85-928 | 2025-04-11 | 2025-04-22 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Hold In Queue |  |  |  | STA_713 Tremont
NSTAR | Woburn | ESMAEX-04653 | 01801 | 770 | Solar | 375-H6 | 2025-05-13 | 2025-06-30 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [8 empty] | STA_375 Dragon Court
NSTAR | Kingston | ESMAEX-04654 | 02364 | 990 | Solar | 3-17-17 | 2025-04-11 | 2025-04-28 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth |  |  |  |  | STA_735 Kingston
NSTAR | North Dartmouth | ESMAEX-04655 | 02747 | 990 | Solar | 2-533-533 | 2025-04-11 | 2025-04-28 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Dedham | ESMAEX-04656 | 02026 | 990 | Solar | 20-H1 | 2025-04-11 | 2025-04-22 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [8 empty] | STA_110 Baker Street
NSTAR | Winchester | ESMAEX-04720 | 01890 | 35.2 | Solar | 211-H11 | 2025-03-31 | 2025-04-14 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-25 | Online | [8 empty] | STA_211 Woburn
NSTAR | Brighton | ESMAEX-04665 | 02135 | 19 | Solar |  | 2025-03-19 | 2025-03-25 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Somerville | ESMAEX-04662 | 02143 | 499 | Solar | 387-148H2 | 2025-04-11 | 2025-05-23 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_250 Mystic
NSTAR | Fairhaven | ESMAEX-04668 | 02719 | 7.6 | Solar | 2-240-209 | 2025-03-19 | 2025-05-12 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage |  |  |  | Marion-Fairhaven |  |  |  |  | STA_624 Wing Lane
NSTAR | Somerville | ESMAEX-04671 | 02145 | 15.2 | Solar | 250-H4XY | 2025-03-20 | 2025-03-28 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-03-31 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_250 Mystic
NSTAR | Bedford | ESMAEX-05759 | 02128 | 149.1 | Solar | 488-H5 | 2025-11-19 | 2025-12-22 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_488 Chelsea
NSTAR | Arlington | ESMAEX-04715 | 02474 | 16.512 | Solar | 59-1393H1 | 2025-03-31 | 2025-06-09 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_211 Woburn
NSTAR | New Bedford | ESMAEX-04707 | 02744 | 690 | Solar | 2-2-2 | 2025-10-03 | 2025-11-13 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_611 Pine Street
NSTAR | Hopkinton | ESMAEX-04711 | 01748 | 4998 | Other | 126-H4 | 2025-03-28 | 2025-04-28 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 4980 | STA_126 Hopkinton
NSTAR | Boston | ESMAEX-04756 | 02128 | 40 | Solar |  | 2025-04-08 | 2025-04-22 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Plymouth | ESMAEX-04692 | 02360 | 23 | Solar & Battery |  | 2025-03-26 | 2025-04-25 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-16 | Online
NSTAR | Brewster | ESMAEX-04724 | 02631 | 14.73 | Solar | 4-89A-89A | 2025-04-01 | 2025-04-25 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 14.73 | STA_968 Harwich
NSTAR | Dorchester | ESMAEX-04718 | 02122 | 40 | Solar | 466-1481H1 | 2025-03-31 | 2025-04-14 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Burlington | ESMAEX-04694 | 01803 | 23 | Solar & Battery | 391-H6 | 2025-03-26 | 2025-04-28 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-23 | Online | [7 empty] | 11.1 | STA_391 Burlington
NSTAR | Lincoln | ESMAEX-04722 | 01773 | 9.6 | Solar | 282-H1 | 2025-04-01 | 2025-06-10 | 50 |  | 50 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-03 | Online | [8 empty] | STA_282 Waltham
NSTAR | Plymouth | ESMAEX-04702 | 02360 | 7.6 | Solar | 3-89-89 | 2025-03-27 | 2025-04-29 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-24 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Holliston | ESMAEX-04709 | 01746 | 5.76 | Solar | 65-H5 | 2025-03-28 | 2025-04-09 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_065 Medway
NSTAR | Wayland | ESMAEX-04717 | 01778 | 16.1 | Solar | 342-H1 | 2025-03-31 | 2025-04-04 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-25 | Online | [8 empty] | STA_342 Sudbury
NSTAR | South Dennis | ESMAEX-04729 | 02660 | 30.4 | Solar | 4-92B-92B | 2025-04-02 | 2025-04-29 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Wareham | ESMAEX-04732 | 02571 | 0 | Other | 3-84-84 | 2025-04-03 | 2025-05-07 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_714 Wareham
NSTAR | Roxbury Crossing | ESMAEX-04723 | 02120 | 100 | Solar | 299-1180H | 2025-04-01 | 2025-05-01 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_350 Colburn Street
NSTAR | Dover | ESMAEX-04721 | 02030 | 20.2 | Solar | 456-H5 | 2025-04-04 | 2025-04-14 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-13 | Online | [7 empty] | 20.2 | STA_456 Dover
NSTAR | Boston | ESMAEX-04730 | 02115 | 225 | Internal Combustion Engine | MC-9 | 2025-04-02 | 2025-04-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-19 | Online | [8 empty] | STA_350 Colburn Street
NSTAR | Sagamore Beach | ESMAEX-04727 | 02562 | 17.6 | Solar | 3-89-925 | 2025-04-02 | 2025-06-09 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-19 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Plymouth | ESMAEX-04731 | 02360 | 6 | Solar | 3-90-90 | 2025-04-03 | 2025-04-28 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-11 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Dorchester | ESMAEX-04735 | 02124 | 15.2 | Solar | 483-H5 | 2025-04-03 | 2025-04-10 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | STA_483 Dewar Street
NSTAR | Stoneham | ESMAEX-04737 | 02180 | 7.6 | Solar | 375-H8 | 2025-04-03 | 2025-05-05 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-24 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Holliston | ESMAEX-04739 | 01746 | 5.76 | Solar | 130-H1 | 2025-04-03 | 2025-05-05 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_130 Holliston
NSTAR | Newton Center | ESMAEX-04754 | 02459 | 19.968 | Solar | 292-H11 | 2025-04-29 | 2025-05-02 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-18 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | North Dartmouth | ESMAEX-04740 | 02747 | 23 | Solar & Battery | 2-522-522 | 2025-04-04 | 2025-05-05 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-11 | Online | [7 empty] | 20 | STA_657 Fisher Road
NSTAR | Bedford | ESMAEX-04745 | 01730 | 4950 | Other | 322-1397H1 | 2026-01-23 | 2026-02-12 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 4950 | STA_533 Hartwell Avenue
NSTAR | Edgartown | ESMAEX-04805 | 02539 | 25.74 | Solar | 4-75-75 | 2025-04-17 | 2025-05-08 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-08 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Lexington | ESMAEX-04777 | 02420 | 20.736 | Solar | 533-H3 | 2025-04-09 | 2025-04-18 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-04-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-06-05 | Online | [7 empty] | 19.9 | STA_533 Hartwell Avenue
NSTAR | Acton | ESMAEX-04820 | 01720 | 20 | Solar | 416-H8 | 2025-04-21 | 2025-04-28 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-17 | Online | [7 empty] | 20 | STA_416 Maynard
NSTAR | Plymouth | ESMAEX-04758 | 02360 | 7.6 | Solar | 3-14-934 | 2025-04-08 | 2025-04-28 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-13 | Online |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Allston | ESMAEX-04752 | 02134 | 50 | Solar | 315-H3 | 2025-04-08 | 2025-04-22 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_315 Electric Avenue
NSTAR | New Bedford | ESMAEX-04821 | 02740 | 156 | Solar |  | 2025-04-21 | 2025-05-20 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-10 | Online
NSTAR | Cataumet | ESMAEX-04846 | 02534 | 10.6 | Solar | 4-78-410 | 2025-04-27 | 2025-05-20 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-16 | Online |  |  |  | Cape |  |  |  | 10.6 | STA_936 Hatchville
NSTAR | Hopkinton | ESMAEX-04785 | 01748 | 5.7 | Solar | 126-H1 | 2025-04-10 | 2025-05-08 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-08 | Online | [8 empty] | STA_126 Hopkinton
NSTAR | Hyannis | ESMAEX-04772 | 02601 | 15.2 | Solar | 4-80B-80B | 2025-04-09 | 2025-05-07 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-20 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Framingham | ESMAEX-04778 | 01702 | 4999 | Other | 274-H4 | 2025-05-22 | 2025-06-11 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 4999 | STA_274 Sherborn
NSTAR | Kingston | ESMAEX-04780 | 02364 | 7.6 | Solar | 3-14-14 | 2025-04-09 | 2025-04-28 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-12 | Online |  |  |  | Plymouth
NSTAR | Natick | ESMAEX-04812 | 01760 | 17.66 | Solar | 240-H1 | 2025-04-18 | 2025-05-06 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-01 | Online | [8 empty] | STA_240 Framingham
NSTAR | Roxbury | ESMAEX-04783 | 02119 | 330 | Solar | 106-H4 | 2025-06-05 | 2025-06-13 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [7 empty] | 330 | STA_106 Andrew Square
NSTAR | East Orleans | ESMAEX-04822 | 02643 | 22.8 | Solar & Battery | 4-628-628 | 2025-04-22 | 2025-06-10 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-30 | Online | [8 empty] | STA_975 Orleans
NSTAR | Medway | ESMAEX-04788 | 02053 | 15.2 | Solar | 130-H2 | 2025-04-11 | 2025-05-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-17 | Online | [8 empty] | STA_130 Holliston
NSTAR | New Bedford | ESMAEX-04789 | 02740 | 30 | Solar | 2-59-38 | 2025-04-14 | 2025-04-21 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-14 | Online | [7 empty] | 20 | STA_611 Pine Street
NSTAR | Wayland | ESMAEX-04790 | 01778 | 5.76 | Solar | 342-H1 | 2025-04-14 | 2025-05-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-26 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Dedham | ESMAEX-04795 | 02026 | 20.76 | Solar & Battery | 2002 | 2025-04-15 | 2025-04-29 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-15 | Online | [7 empty] | 20.76 | STA_110 Baker Street
NSTAR | West Yarmouth | ESMAEX-04804 | 02673 | 7.6 | Solar | 4-64-557 | 2025-04-17 | 2025-07-24 | 70 |  | 70 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-12 | Online | [7 empty] | 19.92 | STA_961 Hyannis Junction
NSTAR | North Dartmouth | ESMAEX-04807 | 02747 | 10.2 | Solar | 2-107-107 | 2025-04-17 | 2025-04-29 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-31 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Lincoln | ESMAEX-04808 | 01773 | 6.14 | Solar | 320-H6 | 2025-04-17 | 2025-05-14 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-04 | Online | [7 empty] | 3.7 | STA_320 Lexington
NSTAR | East Falmouth | ESMAEX-04825 | 02536 | 11.5 | Solar & Battery | 4-77A-77A | 2025-04-22 | 2025-05-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-05 | Online | [8 empty] | STA_936 Hatchville
NSTAR | Duxbury | ESMAEX-04817 | 02332 | 498 | Solar | 3-26-26 | 2025-05-14 | 2025-06-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_738 Duxbury
NSTAR | Winchester | ESMAEX-04818 | 01890 | 990 | Solar | 211-H2 | 2025-05-29 | 2025-06-18 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 990 | STA_211 Woburn
NSTAR | Hyannis | ESMAEX-04819 | 02601 | 10 | Solar | 4-63-521 | 2025-04-18 | 2025-04-28 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-31 | Online |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Chestnut Hill | ESMAEX-04854 | 02467 | 43.056 | Solar & Battery | 496-H5 | 2025-04-30 | 2025-05-08 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-14 | Online | [7 empty] | 8.66 | STA_496 Hyde Park
NSTAR | Newton | ESMAEX-04838 | 02458 | 11.5 | Other | 467-H12 | 2025-04-23 | 2025-06-09 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_467 Watertown
NSTAR | Bedford | ESMAEX-04824 | 01730 | 23 | Solar & Battery | 533-H8 | 2025-04-22 | 2025-05-07 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-30 | Online | [7 empty] | 19.9 | STA_533 Hartwell Avenue
NSTAR | Walpole | ESMAEX-04840 | 02081 | 16.128 | Solar | 2601 | 2025-04-24 | 2025-05-07 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-20 | Online | [8 empty] | STA_146 Walpole
NSTAR | Harwich | ESMAEX-04826 | 02645 | 499 | Solar & Battery | 4-95A-95A | 2025-04-23 | 2025-05-06 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Cape |  |  |  | 499 | STA_968 Harwich
NSTAR | Plymouth | ESMAEX-04832 | 02360 | 11.5 | Other | 3-90-90 | 2025-04-23 | 2025-05-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Lincoln | ESMAEX-04827 | 01773 | 17.1 | Solar | 320-H6 | 2025-04-22 | 2025-04-28 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-03 | Online | [8 empty] | STA_320 Lexington
NSTAR | Dorchester | ESMAEX-05151 | 02125 | 49.7 | Solar |  | 2025-07-02 | 2025-08-05 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Lexington | ESMAEX-04836 | 02421 | 23 | Other | 533-H1 | 2025-04-23 | 2025-05-26 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-22 | Online | [7 empty] | 13.34 | STA_533 Hartwell Avenue
NSTAR | West Dennis | ESMAEX-04841 | 02670 | 5 | Other | 4-92B-571 | 2025-04-24 |  | -32661 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-18 | Online | [7 empty] | 0 | STA_968 Harwich
NSTAR | Plymouth | ESMAEX-04837 | 02360 | 15.2 | Solar | 3-88-923 | 2025-04-23 | 2025-05-20 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-22 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Edgartown | ESMAEX-04954 | 02539 | 34.6 | Solar | 4-75-75 | 2025-05-19 | 2025-06-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Cambridge | ESMAEX-04896 | 02138 | 50 | Solar | 828-1369 | 2025-05-07 | 2025-05-29 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_828 Alewife
NSTAR | Boston | ESMAEX-04839 | 02115 | 555 | Internal Combustion Engine | 350-H4 | 2025-11-14 |  | -32807 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_350 Colburn Street
NSTAR | Medfield | ESMAEX-04842 | 02052 | 6 | Solar | 146-H2 | 2025-04-24 | 2025-05-20 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-13 | Online | [8 empty] | STA_146 Walpole
NSTAR | Edgartown | ESMAEX-04955 | 02539 | 34.6 | Solar | 4-75-75 | 2025-05-19 | 2025-06-09 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Winchester | ESMAEX-04920 | 01890 | 5.84 | Solar | 211-H1 | 2025-05-14 | 2025-06-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-14 | Online | [8 empty] | STA_211 Woburn
NSTAR | North Dartmouth | ESMAEX-04849 | 02747 | 20 | Solar & Battery | 2-533-503 | 2025-04-28 | 2025-05-05 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-29 | Online |  |  |  | Dartmouth-Westport |  |  |  | 10 | STA_651 Cross Road
NSTAR | Hopkinton | ESMAEX-04847 | 01748 | 22.288 | Solar & Battery | 274-H5 | 2025-04-28 | 2025-09-05 | 94 |  | 94 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [7 empty] | 20 | STA_274 Sherborn
NSTAR | Chestnut Hill | ESMAEX-04848 | 02467 | 19.2 | Solar | 292-H5 | 2025-04-28 | 2025-05-07 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-18 | Online | [7 empty] | 19.2 | STA_292 Newton Highlands
NSTAR | Acton | ESMAEX-04933 | 01720 | 10 | Other | 416-H1 | 2025-05-15 | 2025-06-09 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-27 | Online | [7 empty] | 0 | STA_416 Maynard
NSTAR | Newton Center | ESMAEX-04853 | 02459 | 11.5 | Other | 292-H11 | 2025-04-29 | 2025-05-20 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-21 | Online | [7 empty] | 9.99 | STA_292 Newton Highlands
NSTAR | Mattapan | ESMAEX-04859 | 02126 | 24.58 | Solar | 496-H8 | 2025-04-30 | 2025-06-09 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | STA_496 Hyde Park
NSTAR | Weston | ESMAEX-04939 | 02493 | 9.24 | Solar | 282-H10 | 2025-05-15 | 2025-06-26 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-14 | Online | [7 empty] | 0 | STA_282 Waltham
NSTAR | East Sandwich | ESMAEX-04862 | 02537 | 21.88 | Solar | 4-87A-87A | 2025-05-01 | 2025-05-08 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-04 | Online |  |  |  | Cape |  |  |  |  | STA_916 Sandwich
NSTAR | Carver | ESMAEX-04864 | 02330 | 7.6 | Solar | 3-10-10 | 2025-05-01 | 2025-05-20 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-28 | Online |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | South Boston | ESMAEX-04869 | 02127 | 15.36 | Solar | 139-160H1 | 2025-05-02 | 2025-06-06 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-01 | Online
NSTAR | Mattapoisett | ESMAEX-04871 | 02739 | 10 | Solar | 2-302-302 | 2025-05-05 | 2025-05-16 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-09 | Online |  |  |  | Marion-Fairhaven |  |  |  | 20 | STA_646 Crystal Spring
NSTAR | Boston | ESMAEX-04914 | 02118 | 27.3 | Solar | 318-14 | 2025-05-14 | 2025-06-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_106 Andrew Square
NSTAR | Newton Center | ESMAEX-04981 | 02459 | 160 | Solar | 17-H2 | 2025-05-27 | 2025-06-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-31 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Plymouth | ESMAEX-04874 | 02360 | 910 | Solar | 3-14-911 | 2025-06-11 | 2025-10-09 | 86 |  | 86 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_737 West Pond
NSTAR | Hyannis | ESMAEX-05057 | 02601 | 80.5 | Solar | 4-84A-84A | 2025-06-13 | 2025-11-10 | 106 |  | 106 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Cape |  |  |  |  | STA_920 Oak Street
NSTAR | Hyannis | ESMAEX-05058 | 02601 | 84.6 | Solar | 4-84A-84A | 2025-06-13 | 2025-07-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_920 Oak Street
NSTAR | Boston | ESMAEX-04915 | 02118 | 34.6 | Solar | 318-12 | 2025-05-14 | 2025-05-28 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Online | [8 empty] | STA_106 Andrew Square
NSTAR | Lincoln | ESMAEX-05031 | 01773 | 13.71 | Solar | 320-H6 | 2025-06-09 | 2025-07-03 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_320 Lexington
NSTAR | Boston | ESMAEX-04916 | 02118 | 34.6 | Solar | 318-12 | 2025-05-14 | 2025-06-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-03 | Online | [8 empty] | STA_106 Andrew Square
NSTAR | Boston | ESMAEX-04918 | 02118 | 34.6 | Solar | 318-12 | 2025-05-14 | 2025-06-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Online | [8 empty] | STA_106 Andrew Square
NSTAR | Dorchester | ESMAEX-04875 | 02121 | 20 | Solar | 143-109H2 | 2025-11-18 | 2025-12-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_106 Andrew Square
NSTAR | Watertown | ESMAEX-04885 | 02472 | 66.5 | Solar | 124-02 | 2025-05-06 | 2025-05-22 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-05 | Online | [8 empty] | STA_467 Watertown
NSTAR | Sherborn | ESMAEX-04889 | 01770 | 12.6 | Solar | 130-H2 | 2025-05-06 | 2025-05-20 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-06 | Online | [8 empty] | STA_130 Holliston
NSTAR | Fairhaven | ESMAEX-04890 | 02719 | 15.76 | Solar | 2-222-222 | 2025-05-06 | 2025-05-20 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-31 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_654 Arsene
NSTAR | Sharon | ESMAEX-04952 | 02067 | 18.85 | Solar |  | 2025-05-19 | 2025-05-28 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage
NSTAR | Sharon | ESMAEX-04899 | 02067 | 2.065 | Solar | 470-H12 | 2025-05-07 | 2025-05-20 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-16 | Online | [8 empty] | STA_470 Canton
NSTAR | Lexington | ESMAEX-04894 | 02421 | 11.904 | Solar & Battery | 320-H2 | 2025-05-07 | 2025-07-17 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_320 Lexington
NSTAR | Chelsea | ESMAEX-04897 | 02150 | 0 | Other | 488-H6 | 2025-07-11 | 2025-09-09 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 499 | STA_488 Chelsea
NSTAR | Hopkinton | ESMAEX-04944 | 01748 | 11.5 | Solar & Battery | 126-H2 | 2025-05-16 | 2025-06-09 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-16 | Online | [7 empty] | 12.2 | STA_126 Hopkinton
NSTAR | East Falmouth | ESMAEX-04901 | 02536 | 5.76 | Solar | 4-77A-77A | 2025-05-08 | 2025-05-20 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-01 | Online |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Acton | ESMAEX-04924 | 01720 | 51.9 | Solar | 416-H2 | 2025-05-15 | 2025-05-20 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_416 Maynard
NSTAR | Cambridge | ESMAEX-04926 | 02139 | 20 | Solar | 820-45 | 2025-05-15 | 2025-05-28 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-05-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_402 Newton Street
NSTAR | Cambridge | ESMAEX-04927 | 02138 | 20 | Solar | 821-24 | 2025-05-15 | 2025-06-10 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_831 Putnam
NSTAR | East Cambridge | ESMAEX-04931 | 02141 | 17.6 | Solar | 812-16 | 2025-05-15 | 2025-06-10 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_875 East Cambridge
NSTAR | Acton | ESMAEX-04907 | 01720 | 20 | Other | 416-H2 | 2025-05-13 |  | -32674 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-16 | Online | [7 empty] | 20 | STA_416 Maynard
NSTAR | Mattapoisett | ESMAEX-04940 | 02739 | 19.1 | Solar & Battery | 2-302-302 | 2025-05-16 | 2025-05-28 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-16 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Carlisle | ESMAEX-05321 | 01741 | 38.4 | Solar | 512-1399H1 | 2025-08-14 | 2025-09-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_533 Hartwell Avenue
NSTAR | New Bedford | ESMAEX-04912 | 02740 | 15.2 | Solar | 2-89-89 | 2025-05-13 | 2025-05-29 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_611 Pine Street
NSTAR | Arlington | ESMAEX-04919 | 02476 | 14.592 | Solar & Battery | 320-H7 | 2025-05-14 | 2025-07-22 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 12.4 | STA_320 Lexington
NSTAR | Burlington | ESMAEX-04948 | 01803 | 23 | Other | 346-1395H1 | 2025-05-19 | 2025-06-10 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-18 | Online | [7 empty] | 19.99 | STA_391 Burlington
NSTAR | New Bedford | ESMAEX-04942 | 02746 | 10 | Other | 2-24-182 | 2025-05-16 | 2025-06-09 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_611 Pine Street
NSTAR | Newton Center | ESMAEX-04921 | 02459 | 15.2 | Solar | 443-02 | 2025-05-14 | 2025-05-20 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_110 Baker Street
NSTAR | Canton | ESMAEX-04922 | 02021 | 17.48 | Solar | 269-1320H1 | 2025-05-14 | 2025-06-13 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-18 | Online | [8 empty] | STA_470 Canton
NSTAR | Dover | ESMAEX-04971 | 02030 | 24.576 | Solar | 456-H3 | 2025-05-22 | 2025-06-09 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-17 | Online | [7 empty] | 19.99 | STA_456 Dover
NSTAR | North Truro | ESMAEX-04945 | 02652 | 11.5 | Other | 4-96-96 | 2025-05-17 | 2025-06-09 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-03 | Online | [8 empty] | STA_976 Wellfleet
NSTAR | Edgartown | ESMAEX-04956 | 02539 | 31.5 | Solar | 4-75-227 | 2025-05-19 | 2025-06-19 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-24 | Online |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Boston | ESMAEX-04949 | 02127 | 960 | Solar | 99-H7 | 2025-06-03 | 2025-06-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_099 Seafood Way
NSTAR | Framingham | ESMAEX-04951 | 01701 | 4999 | Other | 455-H7 | 2025-07-31 | 2025-08-13 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 4999 | STA_455 West Framingham
NSTAR | Duxbury | ESMAEX-04970 | 02332 | 46 | Solar & Battery | 3-26-26 | 2025-05-22 | 2025-06-13 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-11 | Online | [7 empty] | 9.9
NSTAR | North Dartmouth | ESMAEX-04961 | 02747 | 16.5 | Solar | 2-70-506 | 2025-05-19 | 2025-06-06 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-23 | Online
NSTAR | Falmouth | ESMAEX-05104 | 02540 | 200 | Solar | 4-76-436 | 2025-06-23 | 2025-07-07 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Natick | ESMAEX-05186 | 01760 | 15.2 | Solar | 23-H1 | 2025-07-09 | 2025-07-22 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-07 | Online | [7 empty] | 20 | STA_240 Framingham
NSTAR | Chelsea | ESMAEX-04979 | 02150 | 250 | Solar | 488-H7 | 2025-05-23 | 2025-06-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_488 Chelsea
NSTAR | East Boston | ESMAEX-04978 | 02128 | 50 | Solar | 488-H8 | 2025-05-23 | 2025-06-09 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_488 Chelsea
NSTAR | Boston | ESMAEX-05022 | 02124 | 100 | Solar | 511-1495H | 2025-06-06 | 2025-06-19 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Norfolk | ESMAEX-04967 | 02056 | 160 | Solar | 146-H9 | 2025-07-24 | 2025-08-05 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_146 Walpole
NSTAR | Waltham | ESMAEX-04968 | 02451 | 0 | Other | 450-H2 | 2025-08-12 | 2025-09-17 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 499 | STA_450 Trapelo Road
NSTAR | Natick | ESMAEX-04973 | 01760 | 499 | Other | 433-H9 | 2025-08-01 | 2025-09-09 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 350 | STA_433 Speen Street
NSTAR | Dorchester | ESMAEX-05039 | 02125 | 150 | Solar | 511-1498H | 2025-06-10 | 2025-07-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_483 Dewar Street
NSTAR | Kingston | ESMAEX-04975 | 02364 | 9.9 | Solar & Battery | 3-18-18 | 2025-05-23 | 2026-03-03 | 202 |  | 202 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 9.9
NSTAR | Dorchester | ESMAEX-05038 | 02125 | 200 | Solar | 511-1498H | 2025-06-10 | 2025-07-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_483 Dewar Street
NSTAR | Kingston | ESMAEX-04976 | 02364 | 28 | Solar & Battery | 3-17-17 | 2025-05-23 | 2025-06-13 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-15 | Online |  |  |  | Plymouth |  |  |  | 9.9
NSTAR | Framingham | ESMAEX-04992 | 01702 | 100 | Solar | 455-H4 | 2025-05-29 | 2025-07-24 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_455 West Framingham
NSTAR | Roxbury | ESMAEX-05035 | 02119 | 110 | Solar | 143-151H1 | 2025-06-10 | 2025-07-02 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_106 Andrew Square
NSTAR | Mattapoisett | ESMAEX-04982 | 02739 | 250 | Solar | 2-304-304 | 2025-06-16 | 2025-06-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Carlisle | ESMAEX-04996 | 01741 | 18.048 | Solar | 533-H8 | 2025-05-30 | 2025-07-03 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-24 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Canton | ESMAEX-04990 | 02021 | 15.2 | Solar | 470-H6 | 2025-05-29 | 2025-07-02 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-19 | Online | [8 empty] | STA_470 Canton
NSTAR | Sudbury | ESMAEX-04991 | 01776 | 15.2 | Solar | 342-H8 | 2025-05-29 | 2025-06-13 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-22 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Edgartown | ESMAEX-05002 | 02539 | 34.6 | Solar | 4-75-75 | 2025-06-02 | 2025-06-13 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | North Falmouth | ESMAEX-05017 | 02556 | 5 | Solar |  | 2025-06-05 | 2025-06-18 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape
NSTAR | Westport | ESMAEX-05055 | 02790 | 10 | Solar | 2-532-532 | 2025-06-13 | 2025-07-28 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-13 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Marshfield | ESMAEX-04999 | 02050 | 22.8 | Solar | 3-25-42J2 | 2025-05-30 | 2025-09-16 | 77 |  | 77 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19 | STA_738 Duxbury
NSTAR | Framingham | ESMAEX-05062 | 01701 | 10 | Solar | 278-H1 | 2025-06-13 |  | -32697 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_278 Saxonville
NSTAR | East Orleans | ESMAEX-05046 | 02643 | 23 | Other | 4-89B-89B | 2025-06-10 | 2025-07-24 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-05 | Online | [7 empty] | 19.9 | STA_975 Orleans
NSTAR | Millis | ESMAEX-05142 | 02054 | 20 | Solar & Battery | 65-H1 | 2025-06-28 | 2025-11-20 | 104 |  | 104 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_065 Medway
NSTAR | Lincoln | ESMAEX-05003 | 01773 | 9.6 | Solar & Battery | 320-H8 | 2025-06-02 | 2025-08-14 | 53 |  | 53 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-07 | Online | [7 empty] | 20 | STA_320 Lexington
NSTAR | Kingston | ESMAEX-05006 | 02364 | 17.6 | Solar | 3-15-15 | 2025-06-03 | 2025-06-19 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth
NSTAR | Teaticket | ESMAEX-05008 | 02536 | 400 | Solar | 4-76-437 | 2025-06-03 | 2025-06-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Dedham | ESMAEX-05009 | 02026 | 17.6 | Solar | 2007 | 2025-06-03 | 2025-06-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-20 | Online | [8 empty] | STA_110 Baker Street
NSTAR | Walpole | ESMAEX-05014 | 02081 | 15.2 | Solar | 2606 | 2025-06-04 | 2025-06-19 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-17 | Online | [8 empty] | STA_146 Walpole
NSTAR | Stoneham | ESMAEX-05686 | 02180 | 100 | Solar | 375-H7 | 2025-11-03 | 2025-11-11 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 100 | STA_375 Dragon Court
NSTAR | West Wareham | ESMAEX-05019 | 02576 | 15.2 | Solar | 3-85-928 | 2025-06-05 | 2025-07-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-12 | Permission to Operate |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | Newton | ESMAEX-05101 | 02459 | 130 | Solar | 292-H3 | 2025-06-23 | 2025-08-18 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_292 Newton Highlands
NSTAR | Stoneham | ESMAEX-05684 | 02180 | 100 | Solar | 375-H7 | 2025-11-03 | 2025-11-11 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 100 | STA_375 Dragon Court
NSTAR | Stoneham | ESMAEX-05685 | 02180 | 100 | Solar | 375-H7 | 2025-11-03 | 2025-11-11 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 100 | STA_375 Dragon Court
NSTAR | Boston | ESMAEX-05089 | 02119 | 40 | Solar | 510-77H | 2025-06-18 | 2025-06-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_106 Andrew Square
NSTAR | Duxbury | ESMAEX-05040 | 02332 | 20 | Solar | 3-23-23 | 2025-06-10 | 2025-07-17 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter
NSTAR | Duxbury | ESMAEX-05028 | 02332 | 23.8 | Solar | 3-17-17 | 2025-06-09 | 2025-07-02 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage |  |  |  | Plymouth
NSTAR | East Walpole | ESMAEX-05029 | 02032 | 5.7 | Solar | 146-H4 | 2025-06-09 | 2025-06-19 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-01 | Online | [8 empty] | STA_146 Walpole
NSTAR | Ashland | ESMAEX-05032 | 01721 | 5.76 | Solar | 274-H6 | 2025-06-09 | 2025-06-19 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-06-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-29 | Online
NSTAR | Canton | ESMAEX-05033 | 02021 | 720 | Solar | 470-H8 | 2025-08-14 | 2025-08-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_470 Canton
NSTAR | Medway | ESMAEX-05037 | 02053 | 19 | Solar | 65-H5 | 2025-06-10 | 2025-07-17 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_065 Medway
NSTAR | Duxbury | ESMAEX-05041 | 02332 | 20 | Solar | 3-23-23 | 2025-06-10 | 2025-07-17 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter
NSTAR | Newton Center | ESMAEX-05070 | 02459 | 40 | Solar | 292-H11 | 2025-06-16 | 2025-07-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_292 Newton Highlands
NSTAR | Sherborn | ESMAEX-05044 | 01770 | 15.2 | Solar | 274-H2 | 2025-06-10 | 2025-06-27 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-07-18 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Newton Center | ESMAEX-05071 | 02459 | 69 | Solar | 292-H11 | 2025-06-16 | 2025-07-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 69 | STA_292 Newton Highlands
NSTAR | Duxbury | ESMAEX-05049 | 02332 | 20 | Solar | 3-23-23 | 2025-06-11 | 2025-07-17 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter
NSTAR | Newton Center | ESMAEX-05073 | 02459 | 50 | Solar | 292-H11 | 2025-06-16 | 2025-07-03 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_292 Newton Highlands
NSTAR | Framingham | ESMAEX-05051 | 01702 | 390 | Other | 240-H3 | 2025-11-18 | 2026-01-26 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_240 Framingham
NSTAR | Falmouth | ESMAEX-05271 | 02540 | 99 | Solar | 4-76-436 | 2025-08-01 | 2025-08-07 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Winchester | ESMAEX-05054 | 01890 | 19.2 | Solar | 211-H10 | 2025-06-13 | 2025-08-01 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_211 Woburn
NSTAR | Needham | ESMAEX-05065 | 02492 | 16.4 | Solar | 148-01 | 2025-06-16 | 2025-06-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_148 Needham
NSTAR | Carver | ESMAEX-05064 | 02330 | 1999 | Solar & Battery | 3-10-917 | 2025-06-16 | 2025-06-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Impact Study |  |  |  | Plymouth | Hold In Queue |  |  | 1999 | STA_737 West Pond
NSTAR | Sherborn | ESMAEX-05077 | 01770 | 16.128 | Solar | 274-H2 | 2025-06-17 | 2025-06-26 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-30 | Online | [8 empty] | STA_274 Sherborn
NSTAR | Wellfleet | ESMAEX-05068 | 02667 | 34.8 | Solar & Battery | 4-94B-656 | 2025-06-16 | 2025-08-13 | 42 |  | 42 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-21 | Online | [7 empty] | 17.6 | STA_976 Wellfleet
NSTAR | Marshfield | ESMAEX-05092 | 02050 | 21.88 | Solar & Battery | 3-24A-974 | 2025-06-19 | 2025-06-26 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-29 | Online | [7 empty] | 21.7 | STA_739 Marshfield
NSTAR | Walpole | ESMAEX-05078 | 02081 | 15.2 | Solar | 146-H4 | 2025-06-17 | 2025-07-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-22 | Online | [8 empty] | STA_146 Walpole
NSTAR | Wayland | ESMAEX-05080 | 01778 | 6.588 | Solar | 278-H2 | 2025-06-17 | 2025-07-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-03 | Online | [8 empty] | STA_278 Saxonville
NSTAR | Medfield | ESMAEX-05091 | 02052 | 0 | Battery | 456-H3 | 2025-06-18 | 2025-07-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_456 Dover
NSTAR | Westwood | ESMAEX-05079 | 02090 | 19 | Solar | 148-H3 | 2025-06-17 | 2025-07-20 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19 | STA_148 Needham
NSTAR | Centerville | ESMAEX-05103 | 02632 | 67.3 | Solar | 4-82-82 | 2025-06-23 | 2025-07-02 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-23 | Online |  |  |  | Cape |  |  |  |  | STA_920 Oak Street
NSTAR | Westwood | ESMAEX-05086 | 02090 | 15.2 | Solar | 456-H1 | 2025-06-18 | 2025-07-03 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-04 | Online | [8 empty] | STA_456 Dover
NSTAR | Lexington | ESMAEX-05087 | 02420 | 15.2 | Solar | 533-H9 | 2025-06-18 | 2025-07-02 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Hopkinton | ESMAEX-05130 | 01748 | 29.952 | Solar & Battery | 126-H4 | 2025-06-26 | 2025-07-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 8.9 | STA_126 Hopkinton
NSTAR | Maynard | ESMAEX-05090 | 01754 | 27.28 | Solar & Battery | 416-H6 | 2025-06-18 | 2025-08-08 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-12 | Online | [7 empty] | 14.85 | STA_416 Maynard
NSTAR | West Yarmouth | ESMAEX-05097 | 02673 | 11.5 | Solar & Battery | 4-92A-561 | 2025-06-20 | 2025-08-11 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_961 Hyannis Junction
NSTAR | Walpole | ESMAEX-05113 | 02081 | 240 | Solar | 146-H8 | 2025-06-25 | 2025-07-07 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_146 Walpole
NSTAR | Mattapoisett | ESMAEX-05098 | 02739 | 3.8 | Solar | 2-301-305 | 2025-06-20 | 2025-07-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Bedford | ESMAEX-05108 | 01730 | 19 | Solar | 533-H3 | 2025-06-23 | 2025-07-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-23 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Cataumet | ESMAEX-05135 | 02534 | 19.18 | Solar & Battery | 4-78-410 | 2025-06-26 | 2025-07-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-11 | Compliance Documents |  |  |  | Cape |  |  |  | 19.8 | STA_936 Hatchville
NSTAR | Framingham | ESMAEX-05112 | 01701 | 15.376 | Solar & Battery | 278-H1 | 2025-06-24 | 2025-09-17 | 61 |  | 61 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-16 | Online | [8 empty] | STA_278 Saxonville
NSTAR | Sherborn | ESMAEX-05129 | 01770 | 4.392 | Solar & Battery | 130-H2 | 2025-06-26 | 2025-07-24 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_130 Holliston
NSTAR | Wayland | ESMAEX-05137 | 01778 | 15.738 | Solar | 278-H2 | 2025-06-27 | 2025-07-08 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-09-09 | Online | [8 empty] | STA_278 Saxonville
NSTAR | Mattapoisett | ESMAEX-05128 | 02739 | 15 | Solar | 2-301-305 | 2025-06-26 | 2025-07-07 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-07 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Framingham | ESMAEX-05121 | 01701 | 7.6 | Solar | 433-H4 | 2025-06-25 | 2025-07-03 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | STA_433 Speen Street
NSTAR | Canton | ESMAEX-05138 | 02021 | 20 | Solar & Battery | 269-1320H1 | 2025-06-27 | 2025-08-22 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_470 Canton
NSTAR | Maynard | ESMAEX-05122 | 01754 | 199.8 | Solar | 342-H8 | 2025-06-25 | 2025-08-18 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_342 Sudbury
NSTAR | Plymouth | ESMAEX-05163 | 02360 | 990 | Solar | 3-14-911 | 2025-08-26 | 2025-10-14 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_737 West Pond
NSTAR | Assonett | ESMAEX-05134 | 02702 | 23 | Solar & Battery | 2-606-606 | 2025-06-26 | 2025-07-17 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-29 | Online | [7 empty] | 20 | STA_661 Bell Rock
NSTAR | New Bedford | ESMAEX-05255 | 02740 | 27.3 | Solar | 2-55-55 | 2025-07-30 | 2025-08-07 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 25 | STA_611 Pine Street
NSTAR | Waltham | ESMAEX-05144 | 02451 | 7.296 | Solar & Battery | 450-H6 | 2025-06-30 | 2025-09-05 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-23 | Online | [7 empty] | 12.75 | STA_450 Trapelo Road
NSTAR | Weston | ESMAEX-05201 | 02493 | 22.8 | Solar | 282-H1 | 2025-07-15 | 2025-08-01 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-07 | Online | [8 empty] | STA_282 Waltham
NSTAR | Carlisle | ESMAEX-05146 | 01741 | 17.875 | Solar | 533-H8 | 2025-06-30 | 2025-07-07 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-06 | Online | [7 empty] | 1.59 | STA_533 Hartwell Avenue
NSTAR | Winchester | ESMAEX-05147 | 01890 | 31.95 | Solar & Battery | 211-H7XY | 2025-06-30 | 2025-07-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-29 | Online | [7 empty] | 20 | STA_211 Woburn
NSTAR | Millis | ESMAEX-05149 | 02054 | 15.744 | Solar & Battery | 130-H2 | 2025-07-01 | 2025-07-24 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-04 | Online | [8 empty] | STA_130 Holliston
NSTAR | Hyannis | ESMAEX-05157 | 02601 | 20.86 | Solar | 4-63-531 | 2025-07-07 | 2025-08-05 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-10 | Online |  |  |  | Cape |  |  |  | 15 | STA_961 Hyannis Junction
NSTAR | Framingham | ESMAEX-05152 | 01702 | 7.8 | Battery | 455-H5 | 2025-07-02 | 2025-07-24 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 5.34 | STA_455 West Framingham
NSTAR | Fairhaven | ESMAEX-05159 | 02719 | 150 | Solar | 2-220-220 | 2025-07-07 | 2025-08-01 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Marion-Fairhaven |  |  |  |  | STA_654 Arsene
NSTAR | Fairhaven | ESMAEX-05158 | 02719 | 150 | Solar | 2-240-209 | 2025-07-07 | 2025-08-01 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Marion-Fairhaven |  |  |  |  | STA_624 Wing Lane
NSTAR | Wayland | ESMAEX-05156 | 01778 | 34.5 | Other | 342-H1 | 2025-07-04 | 2025-08-15 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_342 Sudbury
NSTAR | Canton | ESMAEX-05164 | 02021 | 21.88 | Solar | 470-H6 | 2025-07-08 | 2025-07-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-17 | Online | [8 empty] | STA_470 Canton
NSTAR | Woburn | ESMAEX-05167 | 01801 | 15.2 | Solar | 211-H6 | 2025-07-08 | 2025-07-21 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [7 empty] | 15.2 | STA_211 Woburn
NSTAR | Dedham | ESMAEX-05175 | 02026 | 7.6 | Solar | 344-1412H1 | 2025-07-08 | 2025-07-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-07-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-08-06 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Woburn | ESMAEX-05177 | 01801 | 15.2 | Solar | 375-H6 | 2025-07-08 | 2025-07-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-09 | Online | [8 empty] | STA_375 Dragon Court
NSTAR | Acton | ESMAEX-05180 | 01720 | 17.66 | Solar | 126-H2 | 2025-07-08 | 2025-08-18 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-09 | Online | [7 empty] | 9.63 | STA_126 Hopkinton
NSTAR | Westwood | ESMAEX-05181 | 02090 | 15.2 | Solar | 148-H3 | 2025-07-08 | 2025-07-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-13 | Online | [8 empty] | STA_148 Needham
NSTAR | New Bedford | ESMAEX-05200 | 02745 | 38.95 | Solar | 2-104-104 | 2025-07-16 | 2025-08-18 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-18 | Online |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Framingham | ESMAEX-05187 | 01701 | 300 | Solar | 455-H6 | 2025-08-01 | 2025-08-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_455 West Framingham
NSTAR | New Bedford | ESMAEX-05185 | 02744 | 480 | Solar | 2-25-25 | 2025-08-20 | 2025-11-05 | 55 |  | 55 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 480 | STA_611 Pine Street
NSTAR | Sherborn | ESMAEX-05218 | 01770 | 21.12 | Solar | 274-H2 | 2025-07-23 | 2025-08-25 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-16 | Online | [7 empty] | 19 | STA_274 Sherborn
NSTAR | Medfield | ESMAEX-05224 | 02052 | 16.512 | Solar | 146-H6 | 2025-07-24 | 2025-08-15 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-19 | Online | [8 empty] | STA_146 Walpole
NSTAR | Jamaica Plain | ESMAEX-05191 | 02130 | 10 | Solar | 350-H2 | 2025-07-11 | 2025-07-24 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_350 Colburn Street
NSTAR | Burlington | ESMAEX-05520 | 01803 | 100 | Solar | 391-H8 | 2025-09-26 | 2025-10-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_391 Burlington
NSTAR | Bellingham | ESMAEX-05196 | 02019 | 140 | Solar | 65-H4 | 2025-07-14 | 2025-08-01 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_065 Medway
NSTAR | Boston | ESMAEX-05220 | 02127 | 67.3 | Solar | 465-129H | 2025-07-22 | 2025-07-31 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_106 Andrew Square
NSTAR | Sagamore | ESMAEX-05406 | 02561 | 10.045 | Solar & Battery | 4-81A-81A | 2025-08-31 | 2025-09-11 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-17 | Online | [7 empty] | 20 | STA_915 Otis
NSTAR | Somerville | ESMAEX-05211 | 02143 | 17.28 | Solar | 13N29 | 2025-07-16 | 2025-08-01 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_250 Mystic
NSTAR | Boston | ESMAEX-05199 | 80302 | 249.99 | Solar | 323-78H1 | 2025-07-31 | 2025-09-17 | 34 |  | 34 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_106 Andrew Square
NSTAR | Boston | ESMAEX-05240 | 02115 | 34.6 | Solar |  | 2025-07-28 | 2025-09-04 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 0
NSTAR | Chelsea | ESMAEX-05208 | 02150 | 67.3 | Solar | 488-H3 | 2025-12-10 | 2025-12-22 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_488 Chelsea
NSTAR | Boston | ESMAEX-05239 | 02136 | 70 | Solar | 60-1409H1 | 2025-07-28 | 2025-08-07 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_496 Hyde Park
NSTAR | Edgartown | ESMAEX-05229 | 02539 | 106.92 | Solar | 4-75-223 | 2025-07-25 | 2025-08-18 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_933 Falmouth
NSTAR | New Bedford | ESMAEX-05253 | 02745 | 200 | Solar | 2-103-103 | 2025-07-30 | 2025-09-25 | 41 |  | 41 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | On Hold |  |  |  | Cape |  |  |  |  | STA_636 Industrial Park
NSTAR | Waltham | ESMAEX-05217 | 02453 | 45.87 | Solar | 467-H5 | 2025-07-18 | 2025-08-19 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [8 empty] | STA_467 Watertown
NSTAR | Barnstable | ESMAEX-05237 | 02648 | 11.5 | Other |  | 2025-07-31 | 2025-08-25 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-08 | Online | [7 empty] | 0
NSTAR | Fairhaven | ESMAEX-05230 | 02719 | 200 | Solar | 2-220-201 | 2025-07-25 | 2025-08-01 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Marion-Fairhaven |  |  |  |  | STA_654 Arsene
NSTAR | Dorchester | ESMAEX-05382 | 02125 | 200 | Solar | 511-1498H | 2025-08-27 | 2025-09-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_483 Dewar Street
NSTAR | Mattapoisett | ESMAEX-05238 | 02739 | 16 | Battery | 2-221-221 | 2025-07-28 | 2025-08-29 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Marion-Fairhaven |  |  |  | 15.9 | STA_654 Arsene
NSTAR | Dedham | ESMAEX-05225 | 02026 | 15.36 | Solar | 344-1413H1 | 2025-07-24 | 2025-08-14 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-31 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Plympton | ESMAEX-05352 | 02367 | 15 | Other | 3-50-50 | 2025-08-21 | 2025-09-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Plymouth |  |  |  | 5 | STA_727 Brook Street
NSTAR | Watertown | ESMAEX-05264 | 02472 | 240 | Solar | 467-H4 | 2025-07-31 | 2025-08-14 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2010-11-30 | Compliance Documents | [8 empty] | STA_467 Watertown
NSTAR | Lexington | ESMAEX-05231 | 02421 | 23 | Solar & Battery | 533-H4 | 2025-07-25 | 2025-08-11 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-29 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Truro | ESMAEX-05228 | 02666 | 996 | Solar | 4-96-96 | 2025-11-18 | 2025-12-22 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_976 Wellfleet
NSTAR | Bellingham | ESMAEX-05263 | 02019 | 200 | Solar | 65-H4 | 2025-07-31 | 2025-08-13 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_065 Medway
NSTAR | Sudbury | ESMAEX-05232 | 01776 | 23.33 | Solar | 342-H8 | 2025-07-25 | 2025-08-11 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-03 | Online | [7 empty] | 20 | STA_342 Sudbury
NSTAR | Bourne | ESMAEX-05246 | 02559 | 160 | Solar | 4-81A-81A | 2025-08-05 | 2025-08-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_915 Otis
NSTAR | Sharon | ESMAEX-05241 | 02067 | 15.2 | Solar | 470-H12 | 2025-07-28 | 2025-08-11 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_470 Canton
NSTAR | Falmouth | ESMAEX-05298 | 02540 | 200 | Solar | 4-98A-98A | 2025-08-08 | 2025-09-24 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  | 200 | STA_933 Falmouth
NSTAR | Ashland | ESMAEX-05248 | 01721 | 250 | Solar | 274-H1 | 2025-11-14 | 2025-12-22 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_274 Sherborn
NSTAR | Sudbury | ESMAEX-05342 | 01776 | 11.5 | Other | 342-H2 | 2025-08-20 | 2025-09-17 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19.34 | STA_342 Sudbury
NSTAR | Plymouth | ESMAEX-05254 | 02360 | 15.705 | Solar | 3-88-923 | 2025-07-30 | 2025-08-18 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-14 | Online |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | North Falmouth | ESMAEX-05329 | 02556 | 150 | Solar | 4-78-420 | 2025-08-15 | 2025-09-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_936 Hatchville
NSTAR | Wayland | ESMAEX-05257 | 01778 | 15.76 | Solar | 278-H2 | 2025-07-30 | 2025-08-11 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_278 Saxonville
NSTAR | North Dartmouth | ESMAEX-05258 | 02747 | 7.6 | Solar | 2-541-541 | 2025-07-30 | 2025-08-11 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-14 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_651 Cross Road
NSTAR | Mashpee | ESMAEX-05267 | 02649 | 30 | Other |  | 2025-07-31 | 2025-08-07 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Cape
NSTAR | West Yarmouth | ESMAEX-05266 | 02673 | 25 | Other | 4-64-557 | 2025-07-31 | 2025-09-04 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 25 | STA_961 Hyannis Junction
NSTAR | Westwood | ESMAEX-05261 | 02090 | 4999 | Other | 469-H4 | 2025-10-14 | 2025-11-05 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 4999 | STA_469 Ellis Avenue
NSTAR | North Eastham | ESMAEX-05269 | 02651 | 7.6 | Solar & Battery | 4-94A-94A | 2025-08-01 | 2025-08-22 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19.9 | STA_975 Orleans
NSTAR | Sudbury | ESMAEX-05279 | 01776 | 20 | Other | 342-H7 | 2025-08-05 | 2025-08-18 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_342 Sudbury
NSTAR | Needham | ESMAEX-05284 | 02494 | 15.2 | Solar | 148-H1 | 2025-08-05 | 2025-08-22 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-15 | Online | [8 empty] | STA_148 Needham
NSTAR | West Yarmouth | ESMAEX-05491 | 02673 | 210 | Solar | 4-64-64 | 2025-09-19 | 2025-10-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Hyannis | ESMAEX-05490 | 02601 | 210 | Solar | 4-63-521 | 2025-09-19 | 2025-09-29 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Lexington | ESMAEX-05275 | 02421 | 11.5 | Other | 320-H5XY | 2025-08-04 | 2025-08-11 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-16 | Online | [8 empty] | STA_320 Lexington
NSTAR | South Yarmouth | ESMAEX-05489 | 02664 | 180 | Solar | 4-92A-92A | 2025-09-19 | 2025-10-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | West Roxbury | ESMAEX-05278 | 02132 | 5.376 | Solar & Battery | 496-H6 | 2025-08-05 | 2025-09-24 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_496 Hyde Park
NSTAR | Weston | ESMAEX-05281 | 02493 | 20.73 | Solar | 342-H1 | 2025-08-05 | 2025-08-14 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-14 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Natick | ESMAEX-05293 | 01760 | 17.3 | Solar | 23-H1 | 2025-08-07 | 2025-10-02 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-21 | Online | [8 empty] | STA_240 Framingham
NSTAR | Burlington | ESMAEX-05288 | 01803 | 6 | Solar | 391-H7 | 2025-08-06 | 2025-08-13 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-10 | Online | [8 empty] | STA_391 Burlington
NSTAR | Acton | ESMAEX-05295 | 01720 | 9.1 | Solar & Battery | 416-H5 | 2025-08-08 | 2025-08-22 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-14 | Online | [8 empty] | STA_416 Maynard
NSTAR | Newton Center | ESMAEX-05348 | 02459 | 19.2 | Solar | 292-H8 | 2025-08-22 | 2025-09-01 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-31 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Holliston | ESMAEX-05330 | 01746 | 4.392 | Solar & Battery | 274-H3 | 2025-08-18 | 2025-09-26 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-18 | Online | [7 empty] | 20 | STA_274 Sherborn
NSTAR | Plymouth | ESMAEX-05296 | 02360 | 13.36 | Solar | 3-90-90 | 2025-08-22 | 2025-09-17 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Chestnut Hill | ESMAEX-05299 | 02467 | 19.5 | Solar & Battery | 443-07 | 2025-08-09 | 2025-10-21 | 52 |  | 52 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_110 Baker Street
NSTAR | Waltham | ESMAEX-05380 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Waltham | ESMAEX-05378 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Rochester | ESMAEX-05300 | 02770 | 7.6 | Solar & Battery | 3-703-703 | 2025-08-11 | 2025-08-20 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-26 | Online |  |  |  | Marion-Fairhaven |  |  |  | 20 | STA_745 Rochester
NSTAR | Canton | ESMAEX-05307 | 02021 | 250 | Solar | 470-H7 | 2025-08-11 | 2025-11-03 | 60 |  | 60 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_470 Canton
NSTAR | Lincoln | ESMAEX-05308 | 01773 | 9.15 | Solar | 320-H6 | 2025-08-12 | 2025-09-09 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-02 | Online | [8 empty] | STA_320 Lexington
NSTAR | Westwood | ESMAEX-05305 | 02090 | 16.5 | Solar | 456-H1 | 2025-08-11 | 2025-08-20 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-20 | Online | [8 empty] | STA_456 Dover
NSTAR | East Boston | ESMAEX-05304 | 02128 | 121.1 | Solar | 488-H5 | 2025-08-11 | 2025-09-04 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_488 Chelsea
NSTAR | Canton | ESMAEX-05303 | 02021 | 5.76 | Solar | 269-1320H1 | 2025-08-11 | 2025-08-22 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-15 | Online | [8 empty] | STA_470 Canton
NSTAR | New Bedford | ESMAEX-05756 | 02740 | 163.8 | Solar | 2-73-73 | 2025-11-18 | 2025-12-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_611 Pine Street
NSTAR | Waltham | ESMAEX-05379 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Waltham | ESMAEX-05366 | 02451 | 20 | Solar | 282-H1 | 2025-08-26 | 2025-10-03 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Waltham | ESMAEX-05365 | 02451 | 20 | Solar | 282-H5 | 2025-08-26 | 2025-10-17 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | East Orleans | ESMAEX-05309 | 02643 | 20 | Solar | 4-628-628 | 2025-08-12 | 2025-08-26 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-17 | Online | [8 empty] | STA_975 Orleans
NSTAR | Waltham | ESMAEX-05353 | 02451 | 20 | Solar | 282-H5 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Allston | ESMAEX-05312 | 02134 | 40 | Solar | 3604 | 2025-08-12 | 2025-08-20 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-08-28 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-10 | Online | [7 empty] | 20
NSTAR | Boston | ESMAEX-05371 | 02122 | 250 | Solar | 483-H4 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Holliston | ESMAEX-05313 | 01746 | 17.28 | Solar | 274-H5 | 2025-08-13 | 2025-08-25 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Permission to Operate | [8 empty] | STA_274 Sherborn
NSTAR | Cambridge | ESMAEX-05317 | 02138 | 240 | Solar | 828-1104H | 2025-08-14 | 2025-08-29 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_828 Alewife
NSTAR | Norfolk | ESMAEX-05314 | 02056 | 7.6 | Solar | 146-H3 | 2025-08-13 | 2025-08-22 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-24 | Online | [8 empty] | STA_146 Walpole
NSTAR | Osterville | ESMAEX-05324 | 02655 | 5 | Other | 4-80A-80A | 2025-08-14 | 2025-09-04 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-25 | Online |  |  |  | Cape |  |  |  | 5 | STA_920 Oak Street
NSTAR | Natick | ESMAEX-05328 | 01760 | 220 | Solar | 433-H11 | 2025-08-15 | 2025-09-04 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [8 empty] | STA_433 Speen Street
NSTAR | Yarmouth | ESMAEX-05320 | 02664 | 240 | Solar | 4-64-64 | 2025-08-27 | 2025-10-03 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_961 Hyannis Junction
NSTAR | Pocasset | ESMAEX-05344 | 02559 | 0 | Battery | 4-81A-81A | 2025-08-20 | 2025-12-08 | 78 |  | 78 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Cape |  |  |  |  | STA_915 Otis
NSTAR | East Walpole | ESMAEX-05319 | 02032 | 3.8 | Solar | 135-1319H1 | 2025-08-14 | 2025-08-26 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-13 | Construction Stage | [8 empty] | STA_146 Walpole
NSTAR | Lexington | ESMAEX-05346 | 02421 | 19.2 | Solar & Battery | 3402 | 2025-08-20 | 2025-09-01 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-16 | Online | [7 empty] | 19.99 | STA_320 Lexington
NSTAR | Chatham | ESMAEX-05325 | 02659 | 42.9 | Solar | 4-95A-95A | 2025-08-15 | 2025-08-29 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-17 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Holliston | ESMAEX-05374 | 01746 | 10.56 | Solar & Battery | 274-H3 | 2025-08-26 | 2025-09-11 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 10.7 | STA_274 Sherborn
NSTAR | Sudbury | ESMAEX-05333 | 01776 | 12.81 | Solar & Battery | 416-H6 | 2025-08-18 | 2025-08-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [7 empty] | 16.32 | STA_416 Maynard
NSTAR | Waban | ESMAEX-05335 | 02468 | 15.744 | Solar | 292-H12 | 2025-08-18 | 2025-08-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-11 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Assonett | ESMAEX-05396 | 02702 | 15.2 | Solar | 2-606-606 | 2025-08-29 | 2025-10-09 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_661 Bell Rock
NSTAR | Dedham | ESMAEX-05327 | 02026 | 0 | Solar & Battery | 2007 | 2025-08-15 | 2025-09-15 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_110 Baker Street
NSTAR | Rochester | ESMAEX-05331 | 02770 | 7.6 | Solar | 3-702-702 | 2025-08-15 | 2025-08-29 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-15 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_745 Rochester
NSTAR | Lincoln | ESMAEX-05337 | 01773 | 23.81 | Solar | 320-H8 | 2025-08-18 | 2025-09-01 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-27 | Online | [7 empty] | 20 | STA_320 Lexington
NSTAR | North Dartmouth | ESMAEX-05336 | 02747 | 15.2 | Solar | 2-522-522 | 2025-08-18 | 2025-08-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-03 | Online |  |  |  | Dartmouth-Westport |  |  |  |  | STA_657 Fisher Road
NSTAR | Lexington | ESMAEX-05351 | 02420 | 16.83 | Solar | 533-H9 | 2025-08-21 | 2025-09-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-05 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Weston | ESMAEX-05338 | 02493 | 20 | Solar | 282-H8 | 2025-08-18 | 2025-08-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Acton | ESMAEX-05400 | 01720 | 15.36 | Solar | 416-H8 | 2025-08-29 | 2025-09-10 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-31 | Online | [7 empty] | 13.1 | STA_416 Maynard
NSTAR | Orleans | ESMAEX-05370 | 02653 | 150 | Solar | 4-83-83 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_975 Orleans
NSTAR | Cambridge | ESMAEX-05586 | 02138 | 20 | Solar | 822-22 | 2025-10-14 | 2025-10-24 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_828 Alewife
NSTAR | Cambridge | ESMAEX-05587 | 02139 | 50 | Solar | 831-1NA6 | 2025-10-14 | 2025-10-24 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 0 | STA_831 Putnam
NSTAR | Acton | ESMAEX-05940 | 01720 | 198 | Other | 416-H2 | 2026-01-15 | 2026-02-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_416 Maynard
NSTAR | East Harwich | ESMAEX-05458 | 02645 | 66.24 | Solar | 4-95A-95A | 2025-09-15 | 2025-10-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-02 | Online |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Natick | ESMAEX-05341 | 01760 | 10 | Solar & Battery | 240-H1 | 2025-08-19 | 2025-08-29 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-10-15 | Online | [7 empty] | 14 | STA_240 Framingham
NSTAR | Burlington | ESMAEX-05343 | 01803 | 11.5 | Other | 346-1395H1 | 2025-08-20 | 2025-09-16 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-27 | Online | [7 empty] | 11.5 | STA_391 Burlington
NSTAR | Chelsea | ESMAEX-05345 | 02150 | 200 | Solar | 488-H2 | 2025-08-20 | 2025-09-01 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2012-09-24 | Compliance Documents | [8 empty] | STA_488 Chelsea
NSTAR | Holliston | ESMAEX-05347 | 01746 | 23 | Solar & Battery | 65-H5 | 2025-08-21 | 2025-09-04 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-23 | Online | [7 empty] | 14.24 | STA_065 Medway
NSTAR | Dennisport | ESMAEX-05350 | 02639 | 6.144 | Solar & Battery | 4-92B-583 | 2025-08-21 | 2025-09-09 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_968 Harwich
NSTAR | Lincoln | ESMAEX-05381 | 01773 | 7.6 | Solar | 342-H1 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-09 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Sudbury | ESMAEX-05359 | 01776 | 17.28 | Solar & Battery | 342-H6 | 2025-08-22 | 2025-09-09 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-16 | Online | [7 empty] | 19.99 | STA_342 Sudbury
NSTAR | Dover | ESMAEX-05373 | 02030 | 4.886 | Solar | 456-H5 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | STA_456 Dover
NSTAR | Lexington | ESMAEX-05354 | 02420 | 7.6 | Solar | 391-H11 | 2025-08-22 | 2025-09-05 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_391 Burlington
NSTAR | Watertown | ESMAEX-05372 | 02472 | 10 | Other | 467-H4 | 2025-08-26 | 2025-09-10 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_467 Watertown
NSTAR | Dorchester | ESMAEX-05545 | 02121 | 42.8 | Solar | 143-109H6 | 2025-10-06 | 2025-10-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_106 Andrew Square
NSTAR | Dorchester | ESMAEX-05546 | 02121 | 42.8 | Solar | 143-04 | 2025-10-06 | 2025-10-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_106 Andrew Square
NSTAR | New Bedford | ESMAEX-05395 | 02746 | 15.2 | Solar | 2-110-110 | 2025-08-29 | 2025-10-09 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_611 Pine Street
NSTAR | Medfield | ESMAEX-05383 | 02052 | 18.048 | Solar | 456-H2 | 2025-08-27 | 2025-09-09 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_456 Dover
NSTAR | Wellfleet | ESMAEX-05403 | 02667 | 67.3 | Solar | 4-94B-94B | 2025-08-29 | 2025-10-03 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_976 Wellfleet
NSTAR | Wayland | ESMAEX-05397 | 01778 | 15.84 | Solar | 342-H1 | 2025-08-29 | 2025-09-24 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-15 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Carlisle | ESMAEX-05390 | 01741 | 18.3 | Solar | 533-H8 | 2025-08-28 | 2025-09-10 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-04 | Online | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Canton | ESMAEX-05384 | 02021 | 7.686 | Solar | 470-H10 | 2025-08-28 | 2025-09-24 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-03 | Online | [8 empty] | STA_470 Canton
NSTAR | Allston | ESMAEX-05749 | 02134 | 20 | Solar | 315-H3 | 2025-11-17 | 2025-12-08 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2009-03-26 | Compliance Documents | [8 empty] | STA_315 Electric Avenue
NSTAR | Assonett | ESMAEX-05394 | 02702 | 15.2 | Solar | 2-606-606 | 2025-08-29 | 2025-09-11 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-11-07 | Online | [8 empty] | STA_661 Bell Rock
NSTAR | Plymouth | ESMAEX-05440 | 02360 | 9.772 | Solar & Battery | 3-82-82 | 2025-09-10 | 2025-11-03 | 38 |  | 38 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | STA_714 Wareham
NSTAR | Sudbury | ESMAEX-05386 | 01776 | 0 | Other | 342-H8 | 2025-08-27 | 2025-10-21 | 39 |  | 39 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 9.8 | STA_342 Sudbury
NSTAR | Plymouth | ESMAEX-05387 | 02360 | 15.76 | Solar | 3-73-73 | 2025-08-28 | 2025-09-17 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-30 | Online |  |  |  | Plymouth |  |  |  |  | STA_721 Manomet
NSTAR | Winchester | ESMAEX-05389 | 01890 | 38.064 | Solar & Battery | 211-H7XY | 2025-08-28 | 2025-09-24 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_211 Woburn
NSTAR | Lincoln | ESMAEX-05467 | 01773 | 30 | Other | 320-H6 | 2025-09-17 | 2025-09-29 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_320 Lexington
NSTAR | West Falmouth | ESMAEX-05412 | 02574 | 19.5 | Solar & Battery | 4-78-420 | 2025-09-03 | 2025-09-11 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Cape |  |  |  | 19.4 | STA_936 Hatchville
NSTAR | West Somerville | ESMAEX-05488 | 02144 | 50 | Solar | 250-H6 | 2025-09-19 | 2025-10-02 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2022-02-09 | Compliance Documents | [8 empty] | STA_250 Mystic
EMA | Dartmouth | ESMAEX-05402 | 02747 | 900 | Solar | 2-531-531 | 2025-09-15 | 2025-12-10 | 62 |  | 62 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_651 Cross Road
NSTAR | Rochester | ESMAEX-05399 | 02770 | 15.76 | Solar | 3-703-703 | 2025-08-29 | 2025-09-24 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-29 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_745 Rochester
NSTAR | North Chatham | ESMAEX-05404 | 02650 | 8.58 | Solar | 4-95B-95B | 2025-08-30 | 2025-11-21 | 60 |  | 60 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_975 Orleans
NSTAR | Brookline | ESMAEX-05438 | 02446 | 140 | Solar | 350-H8 | 2025-09-09 | 2025-10-02 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_350 Colburn Street
NSTAR | Winchester | ESMAEX-05421 | 01890 | 36.176 | Solar & Battery | 211-H7XY | 2025-09-04 | 2025-09-15 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [7 empty] | 19.378 | STA_211 Woburn
NSTAR | Hopkinton | ESMAEX-05408 | 01748 | 7.6 | Solar | 126-H2 | 2025-09-02 | 2025-09-18 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-27 | Online | [7 empty] | 0 | STA_126 Hopkinton
NSTAR | Lexington | ESMAEX-05410 | 02420 | 11.5 | Other | 351-02 | 2025-09-02 | 2025-09-17 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-31 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-20 | Online | [7 empty] | 3.88 | STA_211 Woburn
NSTAR | Chestnut Hill | ESMAEX-05413 | 02467 | 7.4 | Solar | 329-H6 | 2025-09-03 | 2025-09-11 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_329 Brighton
NSTAR | East Wareham | ESMAEX-05414 | 02538 | 3.8 | Solar | 3-82-82 | 2025-09-03 | 2025-09-11 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_714 Wareham
NSTAR | Roslindale | ESMAEX-05415 | 02131 | 8.12 | Solar & Battery | 496-H8 | 2025-09-03 | 2025-11-03 | 43 |  | 43 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-23 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Kingston | ESMAEX-05416 | 02364 | 200 | Solar | 3-14-14 | 2025-09-23 | 2025-10-16 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Medway | ESMAEX-05419 | 02053 | 200 | Solar | 65-H1 | 2025-09-03 | 2025-09-16 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_065 Medway
NSTAR | Orleans | ESMAEX-05433 | 02653 | 7.26 | Solar | 4-94A-94A | 2025-09-09 | 2025-10-21 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-23 | Online | [8 empty] | STA_975 Orleans
NSTAR | Cambridge | ESMAEX-05588 | 02139 | 20 | Solar | 814-12 | 2025-10-14 | 2025-10-23 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 0 | STA_402 Newton Street
NSTAR | Boston | ESMAEX-05751 | 02127 | 100 | Solar |  | 2025-11-18 | 2025-12-19 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter
NSTAR | Medfield | ESMAEX-05424 | 02052 | 20.13 | Solar | 146-H2 | 2025-09-05 | 2025-09-18 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-29 | Online | [8 empty] | STA_146 Walpole
NSTAR | Woburn | ESMAEX-05425 | 01801 | 11.5 | Solar & Battery | 533-H9 | 2025-09-05 | 2025-09-17 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 10 | STA_533 Hartwell Avenue
NSTAR | Natick | ESMAEX-05428 | 01760 | 17.49 | Solar | 240-H5 | 2025-09-16 | 2025-09-30 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_240 Framingham
NSTAR | Mashpee | ESMAEX-05426 | 02649 | 20 | Solar & Battery | 4-452-452 | 2025-09-08 | 2026-02-12 | 113 |  | 113 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Cape |  |  |  | 12.39 | STA_946 Mashpee
NSTAR | Lincoln | ESMAEX-05427 | 01773 | 360 | Other | 320-H8 | 2025-11-14 | 2025-12-15 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_320 Lexington
NSTAR | Framingham | ESMAEX-05431 | 01701 | 19.584 | Solar | 455-H1 | 2025-09-08 | 2025-09-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-20 | Online | [7 empty] | 7.25 | STA_455 West Framingham
NSTAR | Westwood | ESMAEX-05430 | 02090 | 20 | Solar | 469-H2 | 2025-09-08 | 2025-09-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Arlington | ESMAEX-05530 | 02474 | 4.95 | Solar & Battery | 211-H11 | 2025-09-30 | 2025-10-14 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-15 | Online | [7 empty] | 16 | STA_211 Woburn
NSTAR | Canton | ESMAEX-05499 | 02021 | 10 | Solar | 470-H11 | 2025-09-23 | 2025-10-06 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 10 | STA_470 Canton
NSTAR | Norfolk | ESMAEX-05441 | 02056 | 14.976 | Solar | 146-H10 | 2025-09-10 | 2025-10-22 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_146 Walpole
NSTAR | Dartmouth | ESMAEX-05436 | 02747 | 367.22 | Solar | 2-541-541 | 2025-09-30 | 2025-10-17 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_651 Cross Road
NSTAR | Canton | ESMAEX-05867 | 02021 | 120 | Solar | 470-H7 | 2025-12-19 | 2025-12-30 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_470 Canton
NSTAR | Hopkinton | ESMAEX-05452 | 01748 | 9.15 | Solar | 126-H4 | 2025-09-23 | 2025-09-30 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-07 | Online | [7 empty] | 0 | STA_126 Hopkinton
NSTAR | Walpole | ESMAEX-05439 | 02081 | 20 | Solar | 456-H1 | 2025-09-09 | 2025-09-24 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-16 | Online | [8 empty] | STA_456 Dover
NSTAR | Arlington | ESMAEX-05442 | 02474 | 17.92 | Solar | 211-H3 | 2025-09-10 | 2025-12-02 | 59 |  | 59 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 11.96 | STA_211 Woburn
NSTAR | Hopkinton | ESMAEX-05444 | 01748 | 11.5 | Other | 126-H1 | 2025-09-10 | 2025-09-24 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 3.8 | STA_126 Hopkinton
NSTAR | East Boston | ESMAEX-05446 | 02128 | 103.8 | Solar | 488-H5 | 2025-09-11 | 2025-10-16 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 103.8 | STA_488 Chelsea
NSTAR | Marshfield | ESMAEX-05445 | 02050 | 30 | Solar | 3-25-25 | 2025-09-10 | 2025-10-03 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Hopkinton | ESMAEX-05512 | 01748 | 18.048 | Solar | 274-H5 | 2025-09-25 | 2025-12-01 | 47 |  | 47 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_274 Sherborn
NSTAR | Milton | ESMAEX-05466 | 02186 | 3.294 | Solar | 496-H7 | 2025-09-16 | 2025-09-29 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-18 | Online | [7 empty] | 16.528 | STA_496 Hyde Park
NSTAR | Boston | ESMAEX-05532 | 02130 | 50 | Solar | 350-H7 | 2025-10-01 | 2025-10-21 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_350 Colburn Street
NSTAR | Dennis | ESMAEX-05448 | 02638 | 15.2 | Solar | 4-89A-89A | 2025-09-12 | 2025-09-24 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-09-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | Lexington | ESMAEX-05453 | 02420 | 7.24 | Solar | 533-H4 | 2025-09-15 | 2025-09-22 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 7.24 | STA_533 Hartwell Avenue
NSTAR | West Newton | ESMAEX-05451 | 02465 | 0 | Other | 1713 | 2025-09-14 | 2025-11-20 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-19 | Online | [8 empty] | STA_292 Newton Highlands
NSTAR | Provincetown | ESMAEX-05456 | 02657 | 25 | Solar | 4-675-974 | 2025-09-15 | 2025-10-15 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Sharon | ESMAEX-05460 | 02067 | 100 | Solar | 146-H1 | 2025-09-15 | 2025-10-03 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_146 Walpole
NSTAR | Sudbury | ESMAEX-05461 | 01776 | 12.87 | Solar | 342-H7 | 2025-09-15 | 2025-12-01 | 55 |  | 55 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 20 | STA_342 Sudbury
NSTAR | Dover | ESMAEX-05462 | 02030 | 38 | Solar | 456-H5 | 2025-09-16 | 2026-01-07 | 81 |  | 81 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19 | STA_456 Dover
NSTAR | North Dartmouth | ESMAEX-05472 | 02747 | 15.2 | Solar | 2-523-523 | 2025-09-23 | 2025-11-02 | 28 |  | 28 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Dartmouth-Westport |  |  |  |  | STA_657 Fisher Road
NSTAR | Canton | ESMAEX-05470 | 02021 | 990 | Solar | 470-H4 | 2025-11-25 | 2026-01-08 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_470 Canton
NSTAR | Wayland | ESMAEX-05478 | 01778 | 18.48 | Solar | 278-H2 | 2025-09-17 | 2025-10-08 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-30 | Online | [8 empty] | STA_278 Saxonville
NSTAR | Milton | ESMAEX-05475 | 02186 | 23 | Solar & Battery | 362-02 | 2025-09-17 | 2025-10-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-10 | Online | [8 empty] | STA_496 Hyde Park
NSTAR | Mattapoisett | ESMAEX-05497 | 02739 | 11.5 | Solar & Battery | 3-702-702 | 2025-09-23 | 2025-11-05 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-10 | Online | [7 empty] | 10 | STA_745 Rochester
NSTAR | New Bedford | ESMAEX-05476 | 02740 | 17.3 | Solar | 2-89-89 | 2025-09-17 | 2025-09-29 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_611 Pine Street
NSTAR | North Dartmouth | ESMAEX-05482 | 02747 | 11.4 | Solar | 2-522-522 | 2025-09-17 | 2025-09-24 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-20 | Online |  |  |  | Dartmouth-Westport |  |  |  | 11 | STA_657 Fisher Road
NSTAR | Carlisle | ESMAEX-05483 | 01741 | 15.2 | Solar & Battery | 533-H8 | 2025-09-18 | 2025-09-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-30 | Online | [7 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | Holliston | ESMAEX-05486 | 01746 | 18.48 | Solar | 274-H3 | 2025-09-19 | 2025-10-10 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-15 | Online | [8 empty] | STA_274 Sherborn
NSTAR | West Tisbury | ESMAEX-05505 | 02568 | 45.6 | Solar & Battery | 4-97-97 | 2025-09-24 | 2025-10-02 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_933 Falmouth
NSTAR | Medfield | ESMAEX-05492 | 02052 | 19.2 | Solar | 146-H2 | 2025-09-22 | 2025-12-02 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_146 Walpole
NSTAR | Oak Bluffs | ESMAEX-05514 | 02557 | 33.6 | Solar |  | 2025-09-25 | 2025-10-21 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-31 | Online |  |  |  | Cape
NSTAR | Arlington | ESMAEX-05494 | 02474 | 13.2 | Solar | 211-H3 | 2025-09-22 | 2025-10-16 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-07 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-19 | Online | [8 empty] | STA_211 Woburn
NSTAR | Sharon | ESMAEX-05496 | 02067 | 50 | Solar | 470-H12 | 2025-09-23 | 2025-10-09 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_470 Canton
NSTAR | Weston | ESMAEX-05509 | 02493 | 21.12 | Solar | 282-H1 | 2025-09-25 | 2025-10-06 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-06 | Online | [8 empty] | STA_282 Waltham
NSTAR | Plymouth | ESMAEX-05507 | 02360 | 320 | Solar | 3-13-943 | 2025-11-20 | 2025-12-12 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_737 West Pond
NSTAR | Plymouth | ESMAEX-05506 | 02360 | 900 | Solar | 3-71-937 | 2025-11-20 | 2025-12-12 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_721 Manomet
NSTAR | Marion | ESMAEX-05516 | 02738 | 499 | Solar | 3-304-304 | 2025-12-15 | 2026-01-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Canton | ESMAEX-05517 | 02021 | 19.2 | Solar | 470-H11 | 2025-09-25 | 2025-10-02 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [8 empty] | STA_470 Canton
NSTAR | Plymouth | ESMAEX-05528 | 02360 | 8.064 | Solar & Battery | 3-73-927 | 2025-09-30 | 2025-11-10 | 29 |  | 29 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_721 Manomet
NSTAR | Weston | ESMAEX-05551 | 02493 | 25.986 | Solar | 282-H1 | 2025-10-06 | 2025-10-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Oak Bluffs | ESMAEX-05585 | 02557 | 10 | Other | 4-99-99 | 2025-10-14 | 2025-11-02 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 0 | STA_933 Falmouth
NSTAR | Waltham | ESMAEX-05562 | 02451 | 20 | Solar | 282-H5 | 2025-10-08 | 2025-10-21 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Waltham | ESMAEX-05563 | 02451 | 20 | Solar | 282-H1 | 2025-10-08 | 2025-10-22 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Roslindale | ESMAEX-05543 | 02131 | 90 | Solar |  | 2025-10-03 | 2025-12-08 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Framingham | ESMAEX-05571 | 01702 | 19 | Solar | 455-H5 | 2025-10-10 | 2025-10-23 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_455 West Framingham
NSTAR | New Bedford | ESMAEX-05564 | 02746 | 110 | Solar | 2-85-85 | 2025-10-10 | 2025-12-22 | 51 |  | 51 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_612 Acushnet
NSTAR | Weston | ESMAEX-05630 | 02493 | 415.04 | Solar | 282-H8 | 2026-01-22 | 2026-02-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | Boston | ESMAEX-05542 | 02118 | 80 | Solar |  | 2025-10-03 | 2025-12-10 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Dorchester | ESMAEX-05541 | 02124 | 150 | Solar | 4302 | 2025-10-03 | 2025-12-08 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Canton | ESMAEX-05537 | 02021 | 17.16 | Solar | 470-H4 | 2025-10-03 | 2025-10-16 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_470 Canton
NSTAR | South Boston | ESMAEX-05540 | 02127 | 150 | Solar | 106-H3 | 2025-10-03 | 2025-12-08 | 46 |  | 46 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_106 Andrew Square
NSTAR | Bellingham | ESMAEX-05836 | 02019 | 240 | Solar | 65-H4 | 2025-12-16 | 2026-01-15 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_065 Medway
NSTAR | Marstons Mills | ESMAEX-05544 | 02648 | 23 | Solar & Battery | 4-80A-80A | 2025-10-06 | 2025-11-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-20 | Online | [7 empty] | 19 | STA_920 Oak Street
NSTAR | Cambridge | ESMAEX-05580 | 02138 | 50 | Solar | 819-1NC5 | 2025-10-14 | 2025-10-21 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 0 | STA_402 Newton Street
NSTAR | Framingham | ESMAEX-05548 | 01701 | 15.2 | Solar & Battery | 455-H1 | 2025-10-06 | 2025-10-16 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [7 empty] | 20 | STA_455 West Framingham
NSTAR | Mashpee | ESMAEX-05549 | 02649 | 23 | Solar & Battery | 4-71-71 | 2025-10-17 | 2025-10-27 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-31 | Online | [7 empty] | 20 | STA_946 Mashpee
NSTAR | Bedford | ESMAEX-05550 | 01730 | 34.5 | Solar | 533-H7 | 2025-10-06 | 2025-10-10 | 4 |  | 4 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_533 Hartwell Avenue
NSTAR | Lincoln | ESMAEX-05560 | 01773 | 24.42 | Solar & Battery | 320-H8 | 2025-10-08 | 2025-10-26 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-20 | Online | [8 empty] | STA_320 Lexington
NSTAR | Lincoln | ESMAEX-05794 | 01773 | 25 | Solar & Battery |  | 2025-12-03 | 2026-01-08 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20
NSTAR | Eastham | ESMAEX-05553 | 02642 | 12.672 | Solar & Battery | 4-94A-94A | 2025-10-07 | 2025-10-21 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_975 Orleans
NSTAR | Lexington | ESMAEX-05578 | 02421 | 10 | Solar | 320-H2 | 2025-10-13 | 2025-10-21 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-13 | Online | [8 empty] | STA_320 Lexington
NSTAR | Boston | ESMAEX-05555 | 02119 | 50 | Solar | 106-1N18H | 2025-10-07 | 2025-11-05 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_106 Andrew Square
NSTAR | South Dartmouth | ESMAEX-05556 | 02748 | 23 | Solar & Battery |  | 2025-10-08 | 2025-12-15 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19.9
NSTAR | Centerville | ESMAEX-05554 | 02632 | 10 | Solar | 4-80A-80A | 2025-10-07 | 2025-11-02 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Cape |  |  |  |  | STA_920 Oak Street
NSTAR | Allston | ESMAEX-05606 | 02134 | 15.7 | Solar | 315-H3 | 2025-10-21 | 2025-11-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_315 Electric Avenue
NSTAR | Chatham | ESMAEX-05557 | 02633 | 33.3 | Solar & Battery | 4-95A-606 | 2025-10-08 | 2025-12-08 | 43 |  | 43 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_968 Harwich
NSTAR | Marion | ESMAEX-05561 | 02738 | 10 | Solar | 3-304-304 | 2025-10-08 | 2025-10-21 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-10-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Framingham | ESMAEX-05569 | 01701 | 20 | Solar & Battery | 455-H1 | 2025-10-09 | 2025-10-22 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-20 | Online | [7 empty] | 20 | STA_455 West Framingham
NSTAR | Natick | ESMAEX-05581 | 01760 | 21.504 | Solar & Battery | 433-H5 | 2025-10-14 | 2025-10-21 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-15 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_433 Speen Street
NSTAR | Dorchester | ESMAEX-05829 | 02124 | 11.5 | Other | 483-H4 | 2025-12-11 | 2025-12-31 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-31 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 11.5 | STA_483 Dewar Street
NSTAR | Boston | ESMAEX-05591 | 02130 | 27.3 | Solar | 284-1430H | 2025-10-15 | 2025-11-05 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_350 Colburn Street
NSTAR | Sherborn | ESMAEX-05574 | 01770 | 22.8 | Solar | 274-H2 | 2025-11-04 | 2025-11-19 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [7 empty] | 20 | STA_274 Sherborn
NSTAR | Cambridge | ESMAEX-05704 | 02139 | 40 | Solar | 819-1NB2 | 2025-11-06 | 2025-11-17 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [7 empty] | 0 | STA_402 Newton Street
NSTAR | Lexington | ESMAEX-05576 | 02421 | 18.24 | Solar | 320-H2 | 2025-10-12 | 2025-12-02 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_320 Lexington
NSTAR | Brookline | ESMAEX-05577 | 02445 | 15.2 | Solar | 25N30 | 2025-10-13 | 2025-12-02 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_329 Brighton
NSTAR | Wayland | ESMAEX-05589 | 01778 | 20.7 | Solar | 342-H1 | 2025-10-14 | 2025-11-13 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-03 | Online | [8 empty] | STA_342 Sudbury
NSTAR | Fairhaven | ESMAEX-05582 | 02719 | 16.128 | Solar | 2-220-201 | 2025-10-14 | 2025-11-06 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Marion-Fairhaven |  |  |  |  | STA_654 Arsene
NSTAR | Canton | ESMAEX-05579 | 02021 | 15.36 | Solar | 269-1320H1 | 2025-10-13 | 2025-10-24 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-25 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2025-12-15 | Online | [8 empty] | STA_470 Canton
NSTAR | Natick | ESMAEX-05597 | 01760 | 15.84 | Solar | 240-H1 | 2025-10-16 | 2025-10-21 | 3 |  | 3 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-27 | Online | [7 empty] | 12.4 | STA_240 Framingham
NSTAR | Acton | ESMAEX-05599 | 01720 | 23.04 | Solar & Battery | 416-H5 | 2025-10-16 | 2025-12-02 | 33 |  | 33 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-31 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_416 Maynard
NSTAR | Westwood | ESMAEX-05608 | 02090 | 3.8 | Solar | 456-H1 | 2025-10-21 | 2025-11-06 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_456 Dover
NSTAR | Holliston | ESMAEX-05682 | 01746 | 18.15 | Solar | 130-H1 | 2025-11-03 | 2025-11-13 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-21 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-20 | Online | [8 empty] | STA_130 Holliston
NSTAR | Lincoln | ESMAEX-05605 | 01773 | 23 | Solar & Battery | 320-H6 | 2025-10-21 | 2025-11-10 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_320 Lexington
NSTAR | Carlisle | ESMAEX-05610 | 01741 | 0 | Other | 512-1399H1 | 2025-10-22 | 2025-11-11 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 0.5 | STA_533 Hartwell Avenue
NSTAR | Boston | ESMAEX-05614 | 02118 | 114.8 | Solar | 318-10 | 2025-10-23 | 2025-12-08 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_106 Andrew Square
NSTAR | Boston | ESMAEX-05656 | 02125 | 34.6 | Solar | 483-H6 | 2025-10-29 | 2025-11-10 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Boston | ESMAEX-05615 | 02215 | 134.6 | Solar | 3603 | 2025-10-23 | 2025-12-08 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_329 Brighton
NSTAR | Boston | ESMAEX-05616 | 02119 | 34.6 | Solar |  | 2025-10-23 | 2025-12-15 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Ashland | ESMAEX-05665 | 01721 | 7.68 | Solar & Battery | 274-H5 | 2025-10-30 | 2025-11-20 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19.1 | STA_274 Sherborn
NSTAR | Boston | ESMAEX-05617 | 02118 | 77.3 | Solar |  | 2025-10-23 | 2025-12-08 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Boston | ESMAEX-05618 | 02126 | 67.3 | Solar |  | 2025-10-23 | 2025-12-15 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement
NSTAR | Boston | ESMAEX-05659 | 02121 | 67.3 | Solar | 483-H5 | 2025-10-29 | 2025-11-10 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Jamaica Plain | ESMAEX-05619 | 02130 | 51.9 | Solar |  | 2025-10-23 | 2025-12-08 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Roxbury | ESMAEX-05620 | 02119 | 100 | Solar |  | 2025-10-23 | 2025-12-08 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Boston | ESMAEX-05621 | 02128 | 66.6 | Solar |  | 2025-10-23 | 2025-12-08 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement
NSTAR | Boston | ESMAEX-05622 | 02116 | 40 | Solar |  | 2025-10-23 | 2025-12-08 | 32 |  | 32 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Westport | ESMAEX-05609 | 02790 | 20 | Solar & Battery | 2-532-532 | 2025-10-21 | 2025-11-06 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Dartmouth-Westport |  |  |  | 25 | STA_651 Cross Road
NSTAR | Canton | ESMAEX-05640 | 02021 | 25.44 | Solar & Battery | 470-H10 | 2025-10-27 | 2025-11-13 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_470 Canton
NSTAR | Brewster | ESMAEX-05625 | 02631 | 57.828 | Solar | 4-89B-89B | 2025-10-23 | 2025-11-20 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_975 Orleans
NSTAR | Natick | ESMAEX-05626 | 01760 | 10 | Solar & Battery | 240-H2 | 2025-10-23 | 2025-11-24 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 7.5 | STA_240 Framingham
NSTAR | Sudbury | ESMAEX-05627 | 01776 | 24 | Solar | 342-H2 | 2025-10-23 | 2026-01-21 | 64 |  | 64 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Permission to Operate | [8 empty] | STA_342 Sudbury
NSTAR | Natick | ESMAEX-05638 | 01760 | 8.25 | Solar | 433-H5 | 2025-10-27 | 2025-11-20 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-26 | Online | [8 empty] | STA_433 Speen Street
NSTAR | East Dennis | ESMAEX-05637 | 02641 | 6.912 | Solar & Battery | 4-89A-89A | 2025-10-28 | 2025-11-06 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_968 Harwich
NSTAR | Watertown | ESMAEX-05641 | 02472 | 150 | Solar | 467-H6 | 2025-10-27 | 2025-11-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_467 Watertown
NSTAR | Dorchester | ESMAEX-05643 | 02124 | 20 | Solar | 483-H1 | 2025-10-27 | 2025-12-22 | 40 |  | 40 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Mattapoisett | ESMAEX-05649 | 02739 | 34.94 | Solar | 2-302-302 | 2025-10-28 | 2025-11-13 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Marion-Fairhaven |  |  |  |  | STA_646 Crystal Spring
NSTAR | Framingham | ESMAEX-05717 | 01702 | 50 | Solar | 24-H1 | 2025-11-10 | 2025-11-17 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_240 Framingham
NSTAR | Dorchester | ESMAEX-05674 | 02125 | 180 | Solar | 511-1498H | 2025-10-31 | 2025-11-20 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_483 Dewar Street
NSTAR | Mashpee | ESMAEX-05672 | 02649 | 108 | Solar | 4-452-452 | 2025-10-30 | 2025-11-20 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_946 Mashpee
NSTAR | Marshfield | ESMAEX-05644 | 02050 | 25 | Solar | 3-24A-24A | 2025-10-27 |  | -32793 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_739 Marshfield
NSTAR | Boston | ESMAEX-05645 | 02118 | 480 | Solar | 323-175H3 | 2025-12-08 | 2026-01-07 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_106 Andrew Square
NSTAR | Boston | ESMAEX-05647 | 02118 | 480 | Solar | 106-H4 | 2025-11-17 | 2025-12-02 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_106 Andrew Square
NSTAR | Acusnet | ESMAEX-05654 | 02743 | 10 | Solar | 2-241-241 | 2025-10-29 | 2025-11-06 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-10 | Online |  |  |  | Marion-Fairhaven |  |  |  |  | STA_624 Wing Lane
NSTAR | Weston | ESMAEX-05678 | 02493 | 15.6 | Solar | 282-H8 | 2025-11-01 | 2025-11-11 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-06 | Online | [8 empty] | STA_282 Waltham
NSTAR | South Walpole | ESMAEX-05700 | 02071 | 19.52 | Solar | 146-H3 | 2025-11-05 | 2025-11-20 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_146 Walpole
NSTAR | Westwood | ESMAEX-05658 | 02090 | 10 | Solar | 148-H3 | 2025-10-29 | 2025-12-01 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_148 Needham
NSTAR | Holliston | ESMAEX-05661 | 01746 | 240 | Solar | 274-H3 | 2025-12-28 | 2026-01-07 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_274 Sherborn
NSTAR | Brewster | ESMAEX-05667 | 02631 | 15.2 | Solar |  | 2025-10-30 |  | -32796 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Eastham | ESMAEX-05668 | 02642 | 7.6 | Solar & Battery | 4-94A-94A | 2025-10-30 | 2025-12-01 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_975 Orleans
NSTAR | Acton | ESMAEX-05669 | 01720 | 12.08 | Solar & Battery |  | 2025-10-30 | 2025-11-20 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 12.08
NSTAR | Wareham | ESMAEX-05673 | 02571 | 100 | Solar | 3-86-966 | 2025-10-31 | 2025-12-01 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | Chilmark | ESMAEX-05801 | 02535 | 46 | Solar | 4-97-97 | 2025-12-04 | 2026-01-08 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Bedford | ESMAEX-05683 | 01730 | 11.5 | Solar |  | 2025-11-03 | 2025-11-11 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 15.44
NSTAR | Lexington | ESMAEX-05679 | 02420 | 24.75 | Solar | 533-H4 | 2025-11-02 | 2025-12-22 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 12 | STA_533 Hartwell Avenue
NSTAR | Framingham | ESMAEX-05680 | 01701 | 8.78 | Solar & Battery | 342-H4 | 2025-11-02 | 2025-12-22 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_342 Sudbury
NSTAR | Acton | ESMAEX-05681 | 01720 | 20 | Solar | 416-H4 | 2025-11-03 | 2025-12-02 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Meter | [7 empty] | 20 | STA_416 Maynard
NSTAR | Orleans | ESMAEX-05705 | 02653 | 25 | Solar | 4-95B-95B | 2025-11-06 | 2025-12-01 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_975 Orleans
NSTAR | Orleans | ESMAEX-05706 | 02653 | 19 | Solar | 4-95B-95B | 2025-11-06 | 2025-11-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19 | STA_975 Orleans
NSTAR | Ashland | ESMAEX-05688 | 01721 | 3.8 | Solar | 455-H8 | 2025-11-03 | 2025-12-01 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-03 | Online | [8 empty] | STA_455 West Framingham
NSTAR | Framingham | ESMAEX-05691 | 01701 | 11.5 | Other | 342-H5 | 2025-11-04 | 2025-12-01 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 8.38 | STA_342 Sudbury
NSTAR | Cambridge | ESMAEX-05696 | 02138 | 6.912 | Solar | 827-21 | 2025-11-04 | 2025-12-02 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_828 Alewife
NSTAR | Burlington | ESMAEX-05697 | 01803 | 7.6 | Solar | 346-1395H1 | 2025-11-04 | 2025-11-13 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-02-09 | Online | [8 empty] | STA_391 Burlington
NSTAR | Carlisle | ESMAEX-05718 | 01741 | 20.13 | Solar | 512-1399H1 | 2026-01-08 | 2026-01-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Newton | ESMAEX-05795 | 02465 | 50 | Solar | 17-H1 | 2025-12-04 | 2025-12-15 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_292 Newton Highlands
NSTAR | Boston | ESMAEX-05800 | 02119 | 100 | Solar | 52-1487H1 | 2025-12-04 | 2025-12-15 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Cambridge | ESMAEX-05698 | 02138 | 11.5 | Other | 821-05 | 2025-11-05 | 2025-12-02 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 8.24 | STA_831 Putnam
NSTAR | Acton | ESMAEX-05744 | 01720 | 200 | Solar | 416-H2 | 2025-11-17 | 2025-12-01 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_416 Maynard
NSTAR | Boston | ESMAEX-05762 | 02210 | 80 | Solar |  | 2025-11-20 |  | -32811 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | West Barnstable | ESMAEX-05716 | 02668 | 19.1 | Solar & Battery | 4-87B-87B | 2025-11-10 | 2026-01-18 | 49 |  | 49 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_920 Oak Street
NSTAR | Lakeville | ESMAEX-05708 | 02347 | 15.2 | Solar & Battery | 2-108-108 | 2025-11-06 | 2025-11-24 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 25 | STA_636 Industrial Park
NSTAR | Brighton | ESMAEX-05715 | 02135 | 27.3 | Solar |  | 2025-11-10 | 2025-12-05 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19.99
NSTAR | Woburn | ESMAEX-05767 | 01801 | 100 | Solar | 211-H8 | 2025-11-21 | 2025-12-02 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_211 Woburn
EMA | Bellingham | ESMAEX-05719 | 02019 | 250 | Solar | 65-H4 | 2025-12-19 | 2026-01-15 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_065 Medway
NSTAR | Bellingham | ESMAEX-05720 | 02019 | 499 | Solar | 65-H4 | 2025-12-22 | 2026-01-15 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 499 | STA_065 Medway
NSTAR | Wareham | ESMAEX-05723 | 02571 | 1000 | Solar | 3-85-928 | 2025-12-08 | 2025-12-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 999 | STA_713 Tremont
NSTAR | Boston | ESMAEX-05743 | 02119 | 200 | Solar | 106-H5 | 2025-11-14 | 2025-12-02 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_106 Andrew Square
NSTAR | Medway | ESMAEX-05727 | 02053 | 15.2 | Solar | 65-H5 | 2025-11-10 | 2025-12-22 | 30 |  | 30 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_065 Medway
NSTAR | Chestnut Hill | ESMAEX-05728 | 02467 | 20 | Solar | 329-H6 | 2025-11-11 | 2025-11-20 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_329 Brighton
NSTAR | Mashpee | ESMAEX-05730 | 02649 | 15.2 | Solar & Battery | 4-77B-454 | 2025-11-11 | 2025-12-04 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 19.99 | STA_946 Mashpee
NSTAR | Plymouth | ESMAEX-05732 | 02360 | 17.4 | Solar | 3-12-12 | 2025-11-11 | 2025-11-21 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-01 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth
NSTAR | Bellingham | ESMAEX-05735 | 02019 | 4895 | Other | 65-H4 | 2025-12-30 | 2026-02-03 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Standard |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_065 Medway
NSTAR | Orleans | ESMAEX-05741 | 02653 | 99.84 | Solar | 4-95B-95B | 2025-11-13 | 2025-11-21 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-11-26 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_975 Orleans
NSTAR | Natick | ESMAEX-05825 | 01760 | 17.3 | Solar | 23-1339H4 | 2025-12-13 | 2025-12-22 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_240 Framingham
NSTAR | New Bedford | ESMAEX-05757 | 02740 | 100 | Solar | 2-73-73 | 2025-11-18 | 2025-12-08 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-22 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_611 Pine Street
NSTAR | Newton | ESMAEX-05752 | 02458 | 23.56 | Solar | 467-H14 | 2025-11-17 | 2025-11-30 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_467 Watertown
NSTAR | Sharon | ESMAEX-05781 | 02067 | 150 | Solar | 146-H1 | 2025-12-01 | 2025-12-15 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_146 Walpole
NSTAR | Winchester | ESMAEX-05768 | 01890 | 27.264 | Solar | 211-H11 | 2025-11-21 | 2025-12-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-23 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_211 Woburn
NSTAR | Lincoln | ESMAEX-05755 | 01773 | 20 | Solar | 342-H1 | 2025-11-18 | 2025-12-02 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_342 Sudbury
NSTAR | Hopkinton | ESMAEX-05860 | 01748 | 220 | Solar | 274-H5 | 2025-12-19 | 2026-01-13 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_274 Sherborn
NSTAR | Marstons Mills | ESMAEX-05765 | 02648 | 6.5 | Solar | 4-88-88 | 2025-11-21 | 2025-12-03 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_946 Mashpee
NSTAR | Acusnet | ESMAEX-05766 | 02743 | 23 | Solar & Battery | 2-241-241 | 2025-11-21 | 2025-12-02 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  | 2026-01-27 | Online | [7 empty] | 20 | STA_624 Wing Lane
NSTAR | Holliston | ESMAEX-05771 | 01746 | 15.74 | Solar | 130-H1 | 2025-11-24 | 2025-12-08 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Construction Stage | [7 empty] | 12.4 | STA_130 Holliston
NSTAR | Sudbury | ESMAEX-05772 | 01776 | 900 | Solar | 342-H8 | 2025-11-24 | 2026-01-13 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_342 Sudbury
NSTAR | Lexington | ESMAEX-05770 | 02421 | 5883.3 | Solar & Battery | 320-H5XY | 2025-12-17 | 2025-12-30 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Complex |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 4999 | STA_320 Lexington
NSTAR | Burlington | ESMAEX-05773 | 01803 | 23 | Solar & Battery | 391-H7 | 2025-11-25 | 2026-01-14 | 36 |  | 36 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_391 Burlington
NSTAR | Sudbury | ESMAEX-05798 | 01776 | 15.51 | Solar | 342-H7 | 2025-12-04 | 2026-01-06 | 23 |  | 23 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 15.51 | STA_342 Sudbury
NSTAR | West Dennis | ESMAEX-05777 | 02670 | 22.8 | Solar | 4-92B-92B | 2025-12-01 | 2025-12-10 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Cape |  |  |  |  | STA_968 Harwich
NSTAR | West Dennis | ESMAEX-05778 | 02670 | 22.8 | Solar | 4-92B-92B | 2025-12-01 |  | -32818 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_968 Harwich
NSTAR | Kingston | ESMAEX-05782 | 02364 | 10 | Solar | 3-15-15 | 2025-12-01 | 2026-01-07 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth
NSTAR | Lincoln | ESMAEX-05799 | 01773 | 15.76 | Solar |  | 2025-12-04 | 2025-12-15 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Orleans | ESMAEX-05791 | 02653 | 15.2 | Solar & Battery | 4-94A-94A | 2025-12-03 | 2026-01-07 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 20 | STA_975 Orleans
NSTAR | Sudbury | ESMAEX-05792 | 01776 | 15.2 | Solar | 416-H6 | 2025-12-03 | 2026-01-07 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_416 Maynard
NSTAR | Plymouth | ESMAEX-05793 | 02360 | 5.76 | Solar & Battery | 3-10-10 | 2025-12-03 | 2026-01-07 | 25 |  | 25 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth
NSTAR | North Cambridge | ESMAEX-05858 | 02140 | 27.3 | Solar | 825-20 | 2025-12-18 | 2026-01-13 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_828 Alewife
NSTAR | North Cambridge | ESMAEX-05857 | 02140 | 27.3 | Solar | 825-20 | 2025-12-18 | 2026-01-13 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_828 Alewife
NSTAR | North Cambridge | ESMAEX-05856 | 02140 | 50 | Solar | 825-20 | 2025-12-18 | 2026-01-13 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_828 Alewife
NSTAR | North Truro | ESMAEX-05797 | 02652 | 64.8 | Solar |  | 2025-12-04 | 2026-01-07 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | North Cambridge | ESMAEX-05855 | 02140 | 27.3 | Solar | 825-20 | 2025-12-18 | 2026-01-13 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-02 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_828 Alewife
NSTAR | Brewster | ESMAEX-05804 | 02631 | 20 | Solar | 4-89B-576 | 2025-12-06 | 2025-12-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_975 Orleans
NSTAR | Wareham | ESMAEX-05806 | 02571 | 100 | Solar | 3-86-966 | 2025-12-08 | 2026-01-07 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-29 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Plymouth |  |  |  |  | STA_713 Tremont
NSTAR | Westwood | ESMAEX-05828 | 02090 | 15.2 | Solar & Battery | 456-H1 | 2025-12-11 | 2026-01-07 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 21.64 | STA_456 Dover
NSTAR | Holliston | ESMAEX-05882 | 01746 | 200 | Solar | 274-H3 | 2025-12-28 | 2026-01-07 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-11 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_274 Sherborn
NSTAR | Sudbury | ESMAEX-05835 | 01776 | 23 | Solar & Battery | 342-H6 | 2025-12-12 | 2026-01-07 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19.9 | STA_342 Sudbury
NSTAR | Holliston | ESMAEX-05834 | 01746 | 20 | Solar | 65-H2 | 2025-12-12 | 2026-01-07 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_065 Medway
NSTAR | Newton | ESMAEX-05859 | 02461 | 320 | Solar | 292-H11 | 2025-12-18 | 2026-01-07 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_292 Newton Highlands
NSTAR | Weston | ESMAEX-05837 | 02493 | 39.6 | Solar | 450-H7 | 2025-12-13 | 2026-01-07 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_450 Trapelo Road
NSTAR | Centerville | ESMAEX-05839 | 02632 | 15.2 | Solar & Battery | 4-80A-80A | 2025-12-15 | 2026-01-09 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 20 | STA_920 Oak Street
NSTAR | Cambridge | ESMAEX-05876 | 02139 | 34.6 | Solar | 831-1394 | 2025-12-23 | 2026-01-05 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_831 Putnam
NSTAR | Cambridge | ESMAEX-05877 | 02139 | 50 | Solar | 831-1394 | 2025-12-23 | 2026-01-05 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-08 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_831 Putnam
NSTAR | Plymouth | ESMAEX-05841 | 02360 | 20.736 | Solar | 3-89-89 | 2025-12-16 | 2026-01-09 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Plymouth |  |  |  |  | STA_715 Valley
NSTAR | Sudbury | ESMAEX-05916 | 01776 | 6.144 | Solar & Battery | 342-H2 | 2026-01-09 | 2026-01-22 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-19 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [7 empty] | 10.9 | STA_342 Sudbury
NSTAR | Sandwich | ESMAEX-05844 | 02563 | 11.5 | Other | 4-87A-87A | 2025-12-16 | 2026-01-07 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-12 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Cape |  |  |  | 10 | STA_916 Sandwich
NSTAR | Plymouth | ESMAEX-05846 | 02360 | 3.8 | Solar & Battery | 3-89-89 | 2025-12-17 | 2026-01-07 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_715 Valley
NSTAR | Acusnet | ESMAEX-05847 | 02743 | 10 | Solar | 2-241-241 | 2025-12-17 | 2026-01-15 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-16 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Marion-Fairhaven |  |  |  |  | STA_624 Wing Lane
NSTAR | North Eastham | ESMAEX-05863 | 02651 | 30 | Solar | 4-94B-647 | 2025-12-18 | 2026-01-23 | 26 |  | 26 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-03 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_976 Wellfleet
NSTAR | North Eastham | ESMAEX-05862 | 02651 | 50 | Solar | 4-94B-647 | 2025-12-18 | 2026-01-15 | 20 |  | 20 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [7 empty] | 50 | STA_976 Wellfleet
NSTAR | North Eastham | ESMAEX-05861 | 02651 | 55 | Solar | 4-94B-647 | 2025-12-18 | 2026-01-13 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 25 | STA_976 Wellfleet
NSTAR | Boston | ESMAEX-05925 | 02128 | 240 | Solar | 592-70H | 2026-01-13 | 2026-01-23 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_488 Chelsea
NSTAR | East Boston | ESMAEX-05853 | 02128 | 280 | Solar | 592-70H | 2026-02-19 |  | -32876 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_488 Chelsea
NSTAR | Cambridge | ESMAEX-05933 | 02139 | 34.6 | Solar | 817-01 | 2026-01-14 | 2026-01-28 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_831 Putnam
NSTAR | East Boston | ESMAEX-05854 | 02128 | 300 | Solar | 592-70H | 2026-02-19 |  | -32876 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_488 Chelsea
NSTAR | East Boston | ESMAEX-05924 | 02128 | 240 | Solar | 592-70H | 2026-01-13 | 2026-01-23 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_488 Chelsea
NSTAR | East Boston | ESMAEX-05923 | 02128 | 240 | Solar | 592-70H | 2026-01-13 | 2026-01-23 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_488 Chelsea
NSTAR | Milton | ESMAEX-05865 | 02186 | 30.72 | Solar | 470-H9 | 2025-12-19 | 2026-01-15 | 19 |  | 19 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_470 Canton
NSTAR | New Bedford | ESMAEX-05980 | 02740 | 50 | Solar | 2-89-89 | 2026-02-02 | 2026-02-23 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_611 Pine Street
NSTAR | Weston | ESMAEX-05871 | 02493 | 29.952 | Solar | 282-H1 | 2025-12-22 | 2025-12-23 | 1 |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2025-12-24 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19.9 | STA_282 Waltham
NSTAR | Newton | ESMAEX-05869 | 02461 | 34.6 | Solar |  | 2025-12-22 | 2026-01-06 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Falmouth | ESMAEX-05873 | 02540 | 20 | Solar | 4-76-436 | 2025-12-22 | 2026-01-08 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_933 Falmouth
NSTAR | Jamaica Plain | ESMAEX-05872 | 02130 | 4.9 | Solar & Battery | 396-01 | 2025-12-22 | 2026-01-14 | 17 |  | 17 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 19.9 | STA_396 Amory Street
NSTAR | Woburn | ESMAEX-05944 | 01801 | 6 | Solar & Battery | 533-H9 | 2026-01-16 | 2026-01-26 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_533 Hartwell Avenue
NSTAR | Waltham | ESMAEX-05881 | 02453 | 69.2 | Solar | 282-H9 | 2025-12-24 | 2026-01-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_282 Waltham
NSTAR | Dorchester | ESMAEX-05880 | 02124 | 51.9 | Solar | 483-H7 | 2025-12-24 | 2026-01-08 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-27 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Roslindale | ESMAEX-05891 | 02131 | 292 | Solar | 496-H4 | 2025-12-30 | 2026-01-12 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 186 | STA_496 Hyde Park
NSTAR | Falmouth | ESMAEX-05883 | 02540 | 51.9 | Solar | 4-76-436 | 2025-12-29 | 2026-01-12 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-13 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents |  |  |  | Cape |  |  |  |  | STA_933 Falmouth
NSTAR | Lexington | ESMAEX-06004 | 02421 | 100 | Solar | 320-H5XY | 2026-02-10 |  | -32869 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_320 Lexington
NSTAR | Lexington | ESMAEX-06003 | 02421 | 50 | Solar | 320-H5XY | 2026-02-10 |  | -32869 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_320 Lexington
NSTAR | Framingham | ESMAEX-05892 | 01702 | 245 | Other |  | 2025-12-31 | 2026-03-09 | 48 |  | 48 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Dorchester | ESMAEX-05897 | 02125 | 16.51 | Solar | 483-H3 | 2026-01-05 | 2026-01-15 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_483 Dewar Street
NSTAR | Hopkinton | ESMAEX-05901 | 01748 | 19.1 | Solar & Battery | 126-H1 | 2026-01-06 | 2026-01-21 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 8.28 | STA_126 Hopkinton
NSTAR | Lincoln | ESMAEX-05894 | 01773 | 19 | Solar |  | 2026-01-05 | 2026-01-12 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-09 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Lexington | ESMAEX-05895 | 02421 | 15.2 | Solar | 320-H5XY | 2026-01-05 | 2026-01-13 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-14 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_320 Lexington
NSTAR | South Dartmouth | ESMAEX-05896 | 02748 | 17.6 | Solar & Battery | 2-2-505 | 2026-01-05 | 2026-01-13 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-17 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 25 | STA_611 Pine Street
NSTAR | Framingham | ESMAEX-05907 | 01701 | 10 | Solar | 433-H4 | 2026-01-07 | 2026-01-22 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_433 Speen Street
NSTAR | Duxbury | ESMAEX-05899 | 02332 | 0 | Other | 3-23-23 | 2026-01-05 | 2026-01-26 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Carver | ESMAEX-05915 | 02330 | 61.4 | Solar | 3-10-917 | 2026-01-08 | 2026-02-06 | 21 |  | 21 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Plymouth |  |  |  |  | STA_737 West Pond
NSTAR | Weston | ESMAEX-05949 | 02493 | 100 | Solar | 282-H8 | 2026-01-20 | 2026-01-28 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_282 Waltham
NSTAR | East Orleans | ESMAEX-05967 | 02643 | 22.8 | Solar | 4-628-628 | 2026-01-27 | 2026-02-10 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_975 Orleans
NSTAR | East Walpole | ESMAEX-05908 | 02032 | 11.5 | Other | 146-H4 | 2026-01-07 | 2026-01-21 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_146 Walpole
NSTAR | Holliston | ESMAEX-05913 | 01746 | 16.89 | Solar | 274-H1 | 2026-01-08 | 2026-01-15 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 10 | STA_274 Sherborn
NSTAR | Mashpee | ESMAEX-05910 | 02649 | 300 | Solar | 4-455-455 | 2026-02-03 | 2026-02-25 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Chestnut Hill | ESMAEX-05911 | 02467 | 18.43 | Solar | 443-08 | 2026-01-07 | 2026-02-02 | 18 |  | 18 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-18 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_110 Baker Street
NSTAR | Sudbury | ESMAEX-05939 | 01776 | 200 | Solar | 342-H2 | 2026-01-15 | 2026-02-06 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_342 Sudbury
NSTAR | Maynard | ESMAEX-05926 | 01754 | 24.96 | Solar | 416-H6 | 2026-01-13 | 2026-02-12 | 22 |  | 22 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_416 Maynard
NSTAR | West Yarmouth | ESMAEX-05912 | 02673 | 198.72 | Solar |  | 2026-01-08 | 2026-01-23 | 11 |  | 11 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Maynard | ESMAEX-05918 | 01754 | 15.2 | Solar | 355-02 | 2026-01-11 | 2026-01-28 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-01-30 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_416 Maynard
NSTAR | Weston | ESMAEX-05928 | 02493 | 17.49 | Solar | 282-H1 | 2026-01-13 | 2026-03-03 | 35 |  | 35 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_282 Waltham
NSTAR | East Harwich | ESMAEX-05919 | 02645 | 10 | Other | 4-95A-95A | 2026-01-12 | 2026-02-18 | 27 |  | 27 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 7.54 | STA_968 Harwich
NSTAR | West Newton | ESMAEX-05942 | 02465 | 3.8 | Solar | 282-H9 | 2026-01-16 | 2026-02-09 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_282 Waltham
NSTAR | Framingham | ESMAEX-05921 | 01702 | 30.72 | Solar | 240-H6 | 2026-01-12 | 2026-01-30 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 20 | STA_240 Framingham
NSTAR | Framingham | ESMAEX-05922 | 01702 | 19 | Solar | 240-H6 | 2026-01-12 | 2026-02-02 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 19 | STA_240 Framingham
NSTAR | Rochester | ESMAEX-05927 | 02770 | 20 | Solar & Battery | 3-85-85 | 2026-01-13 | 2026-01-30 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 25 | STA_713 Tremont
NSTAR | Sudbury | ESMAEX-05929 | 01776 | 22.8 | Solar & Battery | 342-H2 | 2026-01-13 | 2026-01-23 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 20 | STA_342 Sudbury
NSTAR | Acton | ESMAEX-05931 | 01720 | 32.8 | Solar | 416-H4 | 2026-01-13 | 2026-02-04 | 16 |  | 16 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 32.8 | STA_416 Maynard
NSTAR | Hyannis | ESMAEX-05934 | 02601 | 5.76 | Solar & Battery | 4-84A-84A | 2026-01-14 | 2026-01-28 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 12.4 | STA_920 Oak Street
NSTAR | Hopkinton | ESMAEX-05936 | 01748 | 10 | Battery | 455-H8 | 2026-01-21 |  | -32855 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_455 West Framingham
NSTAR | Hopkinton | ESMAEX-05937 | 01748 | 10 | Battery | 455-H8 | 2026-01-21 |  | -32855 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_455 West Framingham
NSTAR | Sudbury | ESMAEX-05938 | 01776 | 10.248 | Solar | 342-H8 | 2026-01-15 | 2026-02-27 | 31 |  | 31 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_342 Sudbury
NSTAR | Sudbury | ESMAEX-05960 | 01776 | 120 | Solar | 342-H6 | 2026-01-23 | 2026-02-06 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_342 Sudbury
NSTAR | Framingham | ESMAEX-05941 | 01702 | 15.2 | Solar | 455-H5 | 2026-01-15 | 2026-03-09 | 37 |  | 37 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_455 West Framingham
NSTAR | Norfolk | ESMAEX-05947 | 02056 | 156.672 | Solar |  | 2026-01-20 | 2026-01-28 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Hyde Park | ESMAEX-06006 | 02136 | 15.744 | Solar | 311-13 | 2026-02-11 |  | -32870 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_496 Hyde Park
NSTAR | South Dartmouth | ESMAEX-05953 | 02748 | 11.5 | Solar & Battery |  | 2026-01-21 | 2026-02-06 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 11.4
NSTAR | Canton | ESMAEX-05955 | 02021 | 16.836 | Solar | 470-H8 | 2026-01-22 | 2026-02-09 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_470 Canton
NSTAR | Centerville | ESMAEX-05956 | 02632 | 10 | Solar | 4-80A-80A | 2026-01-22 | 2026-02-12 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_920 Oak Street
NSTAR | Westwood | ESMAEX-06010 | 02090 | 1.9 | Solar | 148-H3 | 2026-02-13 | 2026-03-03 | 12 |  | 12 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_148 Needham
NSTAR | Hatchville | ESMAEX-05973 | 02536 | 15.2 | Solar | 4-78-78 | 2026-02-24 |  | -32879 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_936 Hatchville
NSTAR | Sudbury | ESMAEX-05958 | 01776 | 23 | Other | 342-H8 | 2026-01-23 |  | -32857 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_342 Sudbury
NSTAR | Harwichport | ESMAEX-05962 | 02646 | 30.4 | Solar | 4-85-592 | 2026-01-26 | 2026-02-04 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 5.6 | STA_968 Harwich
NSTAR | Lincoln | ESMAEX-05971 | 01773 | 17.568 | Solar | 320-H8 | 2026-01-29 | 2026-02-09 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_320 Lexington
NSTAR | Burlington | ESMAEX-05964 | 01803 | 23 | Solar & Battery | 391-H6 | 2026-01-27 |  | -32859 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 18.6 | STA_391 Burlington
NSTAR | Wareham | ESMAEX-05968 | 02571 | 5.76 | Solar | 3-83-83 | 2026-01-28 | 2026-02-06 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_714 Wareham
NSTAR | Hyannis | ESMAEX-05972 | 02601 | 19.968 | Solar | 4-84A-84A | 2026-01-29 | 2026-02-19 | 15 |  | 15 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_920 Oak Street
NSTAR | North Dartmouth | ESMAEX-05974 | 02747 | 11.5 | Solar & Battery | 2-107-107 | 2026-01-30 | 2026-02-12 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_636 Industrial Park
NSTAR | Norfolk | ESMAEX-05976 | 02056 | 18.48 | Solar | 146-H3 | 2026-01-30 | 2026-02-12 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-02-20 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [8 empty] | STA_146 Walpole
NSTAR | New Bedford | ESMAEX-05979 | 02745 | 300 | Solar | 2-79-404 | 2026-02-24 | 2026-03-03 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_612 Acushnet
NSTAR | Holliston | ESMAEX-05984 | 01746 | 23 | Other | 274-H5 | 2026-02-03 | 2026-03-09 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 10.2 | STA_274 Sherborn
NSTAR | Plympton | ESMAEX-06028 | 02367 | 38 | Solar |  | 2026-02-20 |  | -32877 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Marshfield | ESMAEX-05990 | 02050 | 30.29 | Solar & Battery | 3-27-27 | 2026-02-04 | 2026-02-23 | 13 |  | 13 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement | [7 empty] | 19.9
NSTAR | Framingham | ESMAEX-05982 | 01701 | 15.2 | Solar & Battery | 342-H4 | 2026-02-03 | 2026-02-12 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 25 | STA_342 Sudbury
NSTAR | Forestdale | ESMAEX-05983 | 02644 | 11.5 | Other |  | 2026-02-03 | 2026-03-09 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Mashpee | ESMAEX-06042 | 02649 | 175 | Solar | 4-77B-456 | 2026-02-25 | 2026-03-04 | 5 |  | 5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Canton | ESMAEX-05986 | 02021 | 11.4 | Solar & Battery | 470-H6 | 2026-02-03 | 2026-03-09 | 24 |  | 24 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 10.2 | STA_470 Canton
NSTAR | Fairhaven | ESMAEX-05989 | 02719 | 5.76 | Solar | 2-221-221 | 2026-02-04 | 2026-02-12 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-10 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Marion-Fairhaven |  |  |  |  | STA_654 Arsene
NSTAR | Roxbury | ESMAEX-06020 | 02119 | 34.6 | Solar | 510-77H8 | 2026-02-18 | 2026-03-03 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review
NSTAR | Westport | ESMAEX-05991 | 02790 | 17.6 | Solar & Battery | 2-522-522 | 2026-02-05 | 2026-02-19 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-04 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_657 Fisher Road
NSTAR | Mattapan | ESMAEX-05992 | 02126 | 10.61 | Solar | 311-08 | 2026-02-06 | 2026-02-19 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_496 Hyde Park
NSTAR | Chestnut Hill | ESMAEX-05994 | 02467 | 15.2 | Solar | 443-07 | 2026-02-06 | 2026-02-19 | 9 |  | 9 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_110 Baker Street
NSTAR | Fairhaven | ESMAEX-06012 | 02719 | 90 | Solar | 2-220-220 | 2026-02-17 | 2026-02-17 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Marion-Fairhaven |  |  |  |  | STA_654 Arsene
NSTAR | Plympton | ESMAEX-06027 | 02367 | 38 | Solar |  | 2026-02-20 |  | -32877 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents
NSTAR | Yarmouthport | ESMAEX-05995 | 02675 | 15.36 | Solar | 4-92A-92A | 2026-02-09 |  | -32868 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_961 Hyannis Junction
NSTAR | Plymouth | ESMAEX-06001 | 02360 | 15.2 | Solar | 3-73-927 | 2026-02-10 | 2026-02-19 | 7 |  | 7 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-05 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement |  |  |  | Plymouth |  |  |  |  | STA_721 Manomet
NSTAR | North Eastham | ESMAEX-06009 | 02651 | 25 | Solar | 4-94B-647 | 2026-02-13 | 2026-02-23 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_976 Wellfleet
NSTAR | Fairhaven | ESMAEX-06014 | 02719 | 50 | Solar | 2-240-240 | 2026-02-17 | 2026-03-03 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review |  |  |  | Marion-Fairhaven |  |  |  |  | STA_624 Wing Lane
NSTAR | Weston | ESMAEX-06021 | 02493 | 69 | Other | 282-H8 | 2026-02-19 |  | -32876 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_282 Waltham
NSTAR | South Dennis | ESMAEX-06013 | 02660 | 50.4 | Solar | 4-92B-92B | 2026-02-17 | 2026-02-25 | 6 |  | 6 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_968 Harwich
NSTAR | Chelsea | ESMAEX-06015 | 02150 | 76.8 | Solar | 488-H7 | 2026-02-17 |  | -32874 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_488 Chelsea
NSTAR | Pocasset | ESMAEX-06016 | 02559 | 10 | Solar | 4-81A-81A | 2026-02-17 | 2026-03-09 | 14 |  | 14 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [8 empty] | STA_915 Otis
NSTAR | Agawam | ESMAEX-06023 | 01001 | 160 | Solar |  | 2026-02-19 |  | -32876 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Plymouth | ESMAEX-06036 | 02360 | 22.8 | Solar | 3-71-71 | 2026-02-23 | 2026-03-09 | 10 |  | 10 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Technical Review | [7 empty] | 4 | STA_721 Manomet
NSTAR | Duxbury | ESMAEX-06024 | 02332 | 15.705 | Solar | 3-23-23 | 2026-02-19 | 2026-03-03 | 8 |  | 8 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 | 2026-03-06 |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | ISA Agreement
NSTAR | Boston | ESMAEX-06029 | 02210 | 80 | Solar |  | 2026-02-22 |  | -32877 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review
NSTAR | Framingham | ESMAEX-06030 | 01702 | 23.8 | Solar & Battery | 455-H5 | 2026-02-23 |  | -32878 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [7 empty] | 10 | STA_455 West Framingham
NSTAR | Sharon | ESMAEX-06037 | 02067 | 11.4 | Solar | 146-H7 | 2026-02-24 |  | -32879 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_146 Walpole
NSTAR | Assonett | ESMAEX-06049 | 02702 | 46 | Other | 2-605-605 | 2026-02-27 |  | -32882 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 12.4 | STA_661 Bell Rock
NSTAR | Weston | ESMAEX-06039 | 02493 | 46 | Other | 282-H8 | 2026-02-24 |  | -32879 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [7 empty] | 19.9 | STA_282 Waltham
NSTAR | Marshfield | ESMAEX-06040 | 02050 | 7.6 | Solar | 3-24B-915 | 2026-02-24 |  | -32879 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [8 empty] | STA_738 Duxbury
NSTAR | Centerville | ESMAEX-06050 | 02632 | 25.2 | Solar & Battery | 4-82-82 | 2026-02-27 |  | -32882 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 20 | STA_920 Oak Street
NSTAR | Provincetown | ESMAEX-06044 | 02657 | 14.592 | Solar & Battery | 4-96-96 | 2026-02-26 |  | -32881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [8 empty] | STA_976 Wellfleet
NSTAR | Fairhaven | ESMAEX-06046 | 02719 | 23 | Solar & Battery | 2-222-222 | 2026-02-26 |  | -32881 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Compliance Documents | [7 empty] | 5 | STA_654 Arsene
NSTAR | Falmouth | ESMAEX-06048 | 02540 | 23 | Other | 4-76-436 | 2026-02-27 |  | -32882 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  |  | Expedited |  |  |  | 0 |  | 0 |  |  |  | Application Review | [7 empty] | 10.87 | STA_933 Falmouth
WMECO | Springfield | 6S21-2009 | 01105 | 75 | Solar | 8C14 | 2009-03-30 | 2009-04-13 | 11 |  | 11 | [25 empty] | 2009-04-24 |  | 07/2009 | No | EXP | [8 empty] | 2009-07-23 | on line
WMECO | Savoy | 6B44-2009 | 01256 | 10000 | Wind | 18C1 | 2009-06-26 | [31 empty] | 2010-07-01 | Yes | STD | [9 empty] | Was on hold by Cust. Cancelled. Cust can't confirm design. Need design for Impact Study. Stand alone generation. New construction. Application has two options 8,000 kW or 10,000 kW. Highest option listed in Design Capacity.
WMECO | Amherst | 6A82-2009 | 01002 | 39 | Solar | 17K2 | 2009-06-29 | 2009-07-24 | 20 |  | 20 | [25 empty] | 2009-07-30 |  | 08/2009 | No | EXP | [8 empty] | 2009-08-10 | On line. New construction.
WMECO | Leverett | 6A91-2009 | 01054 | 13.8 | Solar | 18G7 | 2009-07-28 | 2009-09-14 | 35 |  | 35 | [25 empty] | 2009-09-17 |  | 08/2009 or 09/2009 | Yes | EXP | [9 empty] | Cancelled by Cust. Cust changed design, reapplied.
WMECO | Pittsfield | 6B46-2009 | 01201 | 86 | Solar | 15E3 | 2009-07-29 | 2009-09-29 | 45 |  | 45 | [25 empty] | 2009-09-30 |  | 11/2009 | No | EXP | [8 empty] | 2010-01-14 | on line
WMECO | Pittsfield | 6B47-2009 | 01201 | 95 | Solar | 19A5 | 2009-07-29 | 2009-09-15 | 35 |  | 35 | [25 empty] | 2009-09-16 |  | 11/2009 | No | EXP | [8 empty] | 2009-11-10 | on line
WMECO | Lee | 6B55-2009 | 01238 | 125 | Solar | 16B5 | 2009-11-05 | [31 empty] | 2009-11-15 | TBD | EXP | [9 empty] | Cancelled by Cust. Application not complete and incorrect, reapplied.
WMECO | Springfield | 6S34-2009 | 01104 | 50 | Solar | 5J13 | 2009-11-13 | [31 empty] | 2009-11-15 | TBD | EXP | [9 empty] | Cancelled by Cust. Application not complete. Cust changed size, reapplied.
WMECO | Pittsfield | 6B59-2009 | 01201 | 126.9 | Solar | 19A2 | 2009-12-01 | [31 empty] | 2009-12-31 | TBD | EXP | [9 empty] | Cancelled by Cust. Application not complete, reapplied.
WMECO | Springfield | 6S35-2009 | 01105 | 30 | Solar | 8C26 | 2009-12-01 | 2009-12-30 | 22 |  | 22 | [25 empty] | 2010-01-11 |  | 2009-12-30 | No | EXP | [8 empty] | 2010-02-12 | On line. Third party owned.
WMECO | Lee | 6B60-2009 | 01238 | 125 | Solar | 16B5 | 2009-12-09 | 2009-12-16 | 6 |  | 6 | [25 empty] | 2009-12-24 |  | 2009-12-31 | No | EXP | [8 empty] | 2009-12-30 | on line
WMECO | Springfield | 6S36-2009 | 01111 | 87 | Solar | 5J14 | 2009-12-24 | 2010-01-29 | 27 |  | 27 | [25 empty] | 2010-02-08 |  | 2010-03-26 | No | EXP | [8 empty] | 2010-08-11 | On line. Will not export.
WMECO | Hancock | 6B62-2009 | 01237 | 81.2 | Solar | 30B7 | 2009-12-28 | [31 empty] | 2009-12-31 | TBD | EXP | [9 empty] | Cancelled by Cust. Application not correct, reapplied.
WMECO | Springfield | 6S37-2009 | 01104 | 95 | Solar | 5J14 | 2009-12-28 | [31 empty] | not supplied | TBD | EXP | [9 empty] | Cancelled by Cust. Wrong application, not complete, reapplied.
WMECO | Hadley | 6A104-2009 | 01002 | 2000 | Natural Gas / Fuel Oil | 18G1 & 18G2 | 2009-12-30 | 2010-02-17 | 36 |  | 36 | [15 empty] | 2010-07-19 |  | -28841 | [7 empty] | 2011-02-22 |  | 09/2010 | Yes | STD | [8 empty] | 2011-03-01 | On line. Removed.
WMECO | Springfield | 6S38-2010 | 01104 | 38.07 | Solar | 5J13 | 2010-01-05 | 2010-01-29 | 19 |  | 19 | [25 empty] | 2010-02-02 |  | 2010-01-15 | No | EXP | [8 empty] | 2010-02-19 | on line
WMECO | Hancock | 6B63-2010 | 01237 | 81.2 | Solar | 30B7 | 2010-01-12 | 2010-02-08 | 20 |  | 20 | [25 empty] | 2010-02-19 |  | 2009-12-31 | No | EXP | [8 empty] | 2010-03-09 | On line. Third party owned.
WMECO | Pittsfield | 6B64-2010 | 01201 | 126.91 | Solar | 19A2 | 2010-01-12 | 2010-01-28 | 13 |  | 13 | [25 empty] | 2010-02-09 |  | 2009-12-31 | No | EXP | [8 empty] | 2010-02-25 | On line. Third party owned.
WMECO | Springfield | 6S39-2010 | 01104 | 95 | Solar | 5J14 | 2010-02-03 | 2010-03-05 | 23 |  | 23 | [25 empty] | 2010-04-05 |  | 2010-03-15 | No | EXP | [8 empty] | 2010-10-13 | On line. Third party owned.
WMECO | Leverett | 6A107-2010 | 01054 | 13.795 | Solar | 18G7 | 2010-02-05 | 2010-02-11 | 5 |  | 5 | [25 empty] | 2010-02-12 |  | 2010-02-01 | Yes | EXP | [8 empty] | 2010-02-18 | On line. New construction.
WMECO | Amherst | 6A110-2010 | 01002 | 14.7 | Solar | 17K3 | 2010-04-01 | 2010-04-12 | 8 |  | 8 | [25 empty] | 2010-05-18 |  | 5/2010 | Yes | EXP | [8 empty] | 2010-06-23 | On line. New construction.
WMECO | Shelburne | 6F155-2010 | 01370 | 24.2 | Solar | 22B5 | 2010-04-06 | 2010-04-22 | 13 |  | 13 | [25 empty] | 2010-04-27 |  | 5/2010 | Yes | EXP | [8 empty] | 2010-05-21 | on line
WMECO | Whately | 6AF157-2010 | 01093 | 20 | Solar | 18G8 | 2010-04-21 | [31 empty] | 7/2010 | TBD | EXP | [9 empty] | Cancelled by Cust. Cust changed design, reapplied.
WMECO | Northfield | 6F158-2010 | 01360 | 65.4 | Solar | 21B8 | 2010-04-21 | [31 empty] | not supplied | TBD | EXP | [9 empty] | Cancelled by Cust. Cust will not make changes to existing system.
WMECO | Whately | 6AF160-2010 | 01093 | 15.6 | Solar | 18G8 | 2010-06-01 | 2010-06-18 | 14 |  | 14 | [25 empty] | 2010-06-28 |  | 7/2010 | Yes | EXP | [8 empty] | 2010-07-09 | on line
WMECO | Pittsfield | 6B71-2010 | 01201 | 36 | Solar | 30B4 | 2010-06-01 | 2010-08-23 | 60 |  | 60 | [25 empty] | 2010-10-04 |  | 2010-09-13 | No | EXP | [8 empty] | 2010-12-22 | On line. New construction service.
WMECO | Greenfield | 6F161-2010 | 01301 | 2000 | Solar | 22B3 | 2010-06-03 | 2011-01-05 | 155 |  | 155 | [15 empty] | 2010-07-20 | 2011-01-28 | 139 |  | 139 | [5 empty] | 2011-01-28 |  | 2011-03-04 | Yes | STD | [8 empty] | 2012-06-20 | On line. Draft Impact Study sent to cust 10/8/11. They changed inverters & design so study was redone. Third party owned. Stand alone generation. New constr.
WMECO | Pittsfield | 6B72-2010 | 01201 | 1800 | Solar | 30B3 | 2010-06-11 | [31 empty] | 11/2010 | Yes | STD | [9 empty] | Cancelled by Cust. Application not correct, reapplied.
WMECO | Pittsfield | 6B74-2010 | 01201 | 1800 | Solar | 30B3 N.C. / 30B2 N.O. * | 2010-06-24 | [31 empty] | 11/2010 | Yes | STD | [9 empty] | Cancelled by Cust. Cust changed design, reapplied.
WMECO | Pittsfield | 6B75-2010 | 01201 | 62 | Hydro | 19A7 | 2010-07-01 | 2011-02-14 | 163 |  | 163 | [15 empty] | 2010-09-30 |  | -28894 | [7 empty] | 2011-04-07 |  | 2010-11-15 | No | STD | [8 empty] | 2011-06-16 | On line. New construction service.
WMECO | Pittsfield | 6B77-2010 | 01201 | 1500 | Solar | 30B3 | 2010-07-30 | 2011-02-02 | 134 |  | 134 | [15 empty] | 2010-08-20 |  | -28865 | [7 empty] | 2011-03-24 |  | 2010-12-10 | Yes | STD | [7 empty] | 2012-02-01 | 2012-02-01 | On line. Stand alone generation. New construction.
WMECO | Greenfield | 6F171-2010 | 01301 | 50 | Solar | 22B7 | 2010-08-03 | 2011-01-11 | 116 |  | 116 | [25 empty] | 2011-01-12 |  | 2010-10-20 | No | EXP | [8 empty] | 2011-02-10 | On line. Customer upgraded service.
WMECO | Springfield | 6S46-2010 | 01118 | 26.4 | Solar | 22H16 | 2010-08-03 | 2010-09-18 | 34 |  | 34 | [25 empty] | 2010-10-20 |  | 2010-09-01 | No | EXP | [8 empty] | 2010-11-03 | On line. New construction.
WMECO | Hadley | 6A134-2010 | 01035 | 30.3 | Solar | 17K5 | 2010-08-20 | 2010-09-03 | 11 |  | 11 | [25 empty] | 2010-09-21 |  | 2010-09-20 | Yes | EXP | [8 empty] | 2010-11-10 | on line
WMECO | Amherst | 6A136-2010 | 01002 | 39.6 | Solar | 19B15 | 2010-08-30 | 2010-09-10 | 10 |  | 10 | [25 empty] | 2010-10-01 |  | 2010-09-01 | No | EXP | [8 empty] | 2010-10-15 | on line
WMECO | Deerfield | 6F175-2010 | 01343 | 50 | Solar | 22B3 | 2010-08-30 | 2010-09-10 | 10 |  | 10 | [25 empty] | 2010-10-26 |  | 2010-09-01 | No | EXP | [8 empty] | 2010-12-17 | on line
WMECO | Lee | 6B78S-2010 | 01238 | 30 | Solar | 17G3 | 2010-09-17 | 2011-03-01 | 118 |  | 118 | [25 empty] | 2011-06-01 |  | 2010-10-01 | Yes | EXP | [8 empty] | 2011-12-01 | On line. Cust has historic hydro.
WMECO | Hadley | 6A138-2010 | 01035 | 25.5 | Solar | 18G5 | 2010-09-21 | 2010-10-22 | 24 |  | 24 | [25 empty] | 2010-11-30 |  | 2010-11-01 | Yes | EXP | [8 empty] | 2011-02-23 | On line. New construction.
WMECO | Ashfield | 6F192-2010 | 01330 | 41.385 | Solar | 38A1 | 2010-12-03 | 2011-01-28 | 41 |  | 41 | [25 empty] | 2011-01-28 |  | 2010-01-01 | Yes | EXP | [8 empty] | 2011-04-19 | On line. Cust installed new service. Verizon pole set area.
WMECO | West Springfield | 6S52-2010 | 01089 | 50 | Solar | 16C14 | 2010-12-07 | 2011-01-25 | 36 |  | 36 | [25 empty] | 2011-03-02 |  | 2011-02-01 | No | EXP | [8 empty] | 2011-03-29 | On line. Third party owned.
WMECO | Pittsfield | 6B82-2010 | 01201 | 195 | Digester Gas | 30B3 | 2010-12-09 | 2011-08-18 | 181 |  | 181 | [25 empty] | 2011-09-27 |  | 2011-01-01 | No | STD | [8 empty] | 2012-02-10 | On line. Will not export.
WMECO | Pittsfield | 6B86-2010 | 01201 | 387.2 | Solar | 30B7 | 2010-12-15 | 2011-06-17 | 133 |  | 133 | [25 empty] | 2011-06-17 |  | 2011-01-01 | No | EXP | [8 empty] | 2011-07-27 | on line
WMECO | Hadley | 6A149-2011 | 01035 | 450 | Biogas | 19B15 | 2011-01-04 | [31 empty] | 2011-07-01 | Yes | STD | [9 empty] | Cancelled by Cust. Cust name and design changed. Reapplied.
WMECO | Greenfield | 6F194-2011 | 01301 | 83 | Solar | 22B7 | 2011-01-04 | 2011-07-08 | 134 |  | 134 | [25 empty] | 2011-12-13 |  | 2011-03-01 | No | EXP | [8 empty] | 2012-02-06 | On line. Cust installed phone line to meter.
WMECO | Deerfield | 6F195-2011 | 01342 | 450 | Biogas | 22B1 | 2011-01-04 | [31 empty] | 2011-06-01 | Yes | STD | [9 empty] | Cancelled by Cust. Cust name and design change, reapplied.
WMECO | Easthampton | 6A151-2011 | 01027 | 2000 | Solar | 15A3 | 2011-01-27 | 2011-03-16 | 35 |  | 35 | [15 empty] | 2011-03-21 | 2011-06-29 | 73 |  | 73 | 2011-07-06 |  | -29093 |  |  | 2011-10-21 |  | 2011-11-19 | Yes | STD | [8 empty] | 2012-06-01 | On line. Int Cust worked with Verizon to get phone lines. Third party owned. Stand alone generation. New construction.
WMECO | Hadley | 6A156-2011 | 01035 | 450 | Biogas | 19B15 | 2011-02-23 | [31 empty] | 2011-07-01 | Yes | STD | [9 empty] | Cancelled by Cust. Cust submitted new application for larger unit.
WMECO | Pittsfield | 6B92-2011 | 01201 | 2000 | Solar | 19A3 | 2011-02-23 | [19 empty] | 2011-05-26 |  | -29064 | [9 empty] | 2011-12-15 | Yes | STD | [9 empty] | Cancelled by Int Cust. Third party owned. Stand alone generation. New construction.
WMECO | Deerfield | 6F201-2011 | 01373 | 450 | Biogas | 22B1 | 2011-02-23 | [31 empty] | 2011-07-01 | Yes | STD | [9 empty] | Cancelled by Cust. Cust submitted new application for larger unit.
WMECO | Sandisfield | 6B93-2011 | 01255 | 14 | Solar | 19J4 | 2011-03-03 | 2011-03-28 | 18 |  | 18 | [25 empty] | 2011-04-27 |  | 2011-06-01 | No | EXP | [8 empty] | 2011-12-05 | on line
WMECO | Greenfield | 6F203-2011 | 01301 | 100 | Solar | 22B4 | 2011-03-04 | 2011-12-07 | 199 |  | 199 | [25 empty] | 2012-03-26 |  | 2011-07-01 | No | EXP | [8 empty] | 2012-05-07 | On line. New construction service.
WMECO | Springfield | 6S56-2011 | 01107 | 120.4 | Solar | 21S7 | 2011-03-17 | 2012-01-06 | 212 |  | 212 | [25 empty] | 2012-01-30 |  | 2011-05-01 | No | STD | [8 empty] | 2012-03-12 | on line
WMECO | Westfield | 6A164-2011 | 01085 | 250 | Solar | 19J2 | 2011-04-07 | [31 empty] | 2011-07-31 | TBD | STD | [9 empty] | Cancelled by Cust. Wrong application submitted. 3rd party info incorrect. Cust submited new application.
WMECO | Northfield | 6F215-2011 | 01360 | 2000 | Solar | 21B8 | 2011-04-07 | 2011-08-18 | 96 |  | 96 | [15 empty] | 2011-07-13 | 2011-12-13 | 110 |  | 110 | 2011-11-28 |  | -29196 |  |  | 2012-02-07 |  | 2011-08-01 | Yes | STD | [8 empty] | 2012-03-30 | On line. Third party owned. Essentially stand alone generation.
WMECO | Agawam | 6S57-2011 | 01001 | 1500 | Solar | 30A6 | 2011-04-19 | 2011-05-26 | 28 |  | 28 | [15 empty] | 2011-06-09 | 2011-10-21 | 97 |  | 97 | 2011-11-14 |  | -29186 |  |  | 2012-04-27 |  | 2011-09-01 | Yes | STD | [6 empty] | 2013-03-11 | 2013-03-13 | 2013-03-13 | On line. Communication work with Verizon in progress. Third party owned. Stand alone generation. New construction.
WMECO | Westfield | 6A168-2011 | 01085 | 1000 | Solar | 19J2 | 2011-05-17 | 2011-07-20 | 47 |  | 47 | [27 empty] | 2011-09-30 | Yes | STD | [9 empty] | Cancelled by Int Cust. Third party owned. Essentially stand alone generation. New construction. Application has two options 250 kW or 1,000 kW. Highest option listed in Design Capacity.
WMECO | Whately | 6A170-2011 | 01373 | 1500 | Solar | 18G8 | 2011-05-19 | 2011-07-21 | 46 |  | 46 | [15 empty] | 2011-07-08 | 2011-12-28 | 124 |  | 124 | 2011-12-21 |  | -29213 |  |  | 2012-04-03 |  | 2011-09-01 | Yes | STD | [6 empty] | 2013-01-29 | 2013-02-01 | 2013-03-11 | On line. Third party owned. Stand alone generation. New construction.
WMECO | Greenfield | 6F230-2011 | 01301 | 34.2 | Solar | 22B4 | 2011-06-14 | [31 empty] | not supplied | TBD | EXP | [9 empty] | Cancelled by Cust. Cust submitted new application.
WMECO | Dalton | 6B105-2011 | 01226 | 224 | Steam | 19A6 | 2011-06-20 | 2012-01-11 | 148 |  | 148 | [15 empty] | 2011-10-20 |  | -29169 | [7 empty] | 2012-01-11 |  | 2011-11-11 | No | STD | [8 empty] | 2012-01-24 | On line. Will not export.
WMECO | Dalton | 6B106-2011 | 01226 | 250 | Hydro | 19A6 | 2011-06-20 | 2012-05-29 | 243 |  | 243 | [15 empty] | 2012-07-16 | 2012-12-19 | 110 |  | 110 | [5 empty] | 2013-04-30 |  | 2012-04-01 | Yes | STD | [6 empty] | 2013-09-27 | 2013-10-03 | 2013-10-03 | on line 10/3/13
WMECO | Greenfield | 6F235-2011 | 01301 | 34.2 | Solar | 22B4 | 2011-06-24 | 2011-07-15 | 16 |  | 16 | [25 empty] | 2011-07-20 |  | 2011-07-21 | No | EXP | [8 empty] | 2011-08-05 | on line
WMECO | Agawam | 6S60-2011 | 01001 | 1500 | Solar | 16C16 | 2011-07-07 | 2011-08-03 | 20 |  | 20 | [15 empty] | 2011-09-01 | 2011-12-29 | 86 |  | 86 | 2011-12-21 |  | -29213 |  |  | 2012-04-13 |  | 2011-12-01 | Yes | STD | [6 empty] | 2013-02-06 | 2013-02-22 | 2013-03-11 | On line. Communication work with Verizon in progress. Third party owned. Stand alone generation. New construction. On line.
WMECO | Chesterfield | 6F243-2011 | 01012 | 12 | Solar | 18K3 | 2011-07-25 | 2011-08-22 | 21 |  | 21 | [25 empty] | 2011-08-23 |  | 2011-08-01 | No | EXP | [8 empty] | 2011-09-15 | on line
WMECO | Amherst | 6A183-2011 | 01002 | 60 | Solar | 19B16 | 2011-07-28 | 2011-09-22 | 41 |  | 41 | [25 empty] | 2011-10-17 |  | 2011-11-01 | No | EXP | [8 empty] | 2011-11-18 | on line
WMECO | Conway | 6F248-2011 | 01341 | 22.8 | Solar | 38A1 | 2011-08-12 | 2011-10-26 | 54 |  | 54 | [25 empty] | 2011-11-17 |  | 2011-09-10 | Yes | EXP | [8 empty] | 2012-02-27 | on line
WMECO | Whately | 6F251-2011 | 01373 | 100 | Solar | 18G8 | 2011-08-18 | 2011-10-13 | 41 |  | 41 | [25 empty] | 2011-10-18 |  | not supplied | No | EXP | [8 empty] | 2011-12-28 | On line. New construction service.
WMECO | Hadley | 6A196-2011 | 01035 | 95 | Solar | 18G4 | 2011-09-01 | 2011-10-25 | 39 |  | 39 | [25 empty] | 2011-11-30 |  | 2011-11-01 | Yes | EXP | [8 empty] | 2012-03-30 | On line. Stand alone generation. New construction.
WMECO | Pittsfield | 6B111-2011 | 01201 | 300 | Solar | 30B4 | 2011-09-02 | 2011-10-05 | 24 |  | 24 | [25 empty] | 2012-02-07 |  | 2011-10-01 | No | EXP | [8 empty] | 2012-06-01 | On line. Cust changed their switchgear. Service upgrade.
WMECO | Springfield | 6S68-2011 | 01111 | 208 | Solar | 5J14 | 2011-09-12 | 2011-11-17 | 49 |  | 49 | [25 empty] | 2011-11-30 |  | 2011-10-15 | No | EXP | [8 empty] | 2012-01-24 | On line. Will not export.
WMECO | Deerfield | 6F264-2011 | 01342 | 30 | Solar | 22B7 | 2011-09-16 | 2011-10-19 | 24 |  | 24 | [25 empty] | 2011-11-07 |  | 2011-10-31 | No | EXP | [8 empty] | 2012-02-03 | on line
WMECO | Hadley | 6A209-2011 | 01035 | 300 | Biogas | 19B15 | 2011-09-21 | 2013-10-18 | 525 |  | 525 | 2013-10-21 |  | -29673 | [22 empty] | 2013-12-19 |  | 2012-04-01 | Yes | STD | [8 empty] | 2013-12-31 | on line
WMECO | Deerfield | 6F265-2011 | 01372 | 600 | Biogas | 22B1 | 2011-09-21 | [31 empty] | 2012-04-01 | Yes | STD | [9 empty] | Sent purge letter 5/20/13. Cust submitted new option 6/17/13. Gen-set nampeplate and application fee required. Stand alone generation. New construction. Design option 600 kW or 300 kW. Highest design listed. Reviewed new option for completeness. App not complete. Cust cancelled 9/10/13.
WMECO | Lee | 6B116-2011 | 01238 | 295 | Solar | 16B5 | 2011-10-21 | [31 empty] | Q2 2012 | TBD | EXP | [9 empty] | Cancelled by Cust. Submitted new application.
WMECO | Colrain | 6F274-2011 | 01340 | 15.36 | Solar | 29R2 | 2011-10-24 | 2012-01-12 | 59 |  | 59 | [25 empty] | 2012-02-07 |  | 2011-11-30 | Yes | EXP | [8 empty] | 2012-05-23 | On line. Essentially stand alone generation.
WMECO | Whately | 6A225-2011 | 01093 | 260 | Solar | 18G8 | 2011-11-07 | [31 empty] | 2012-03-16 | TBD | EXP | [9 empty] | Cancelled by Cust. Cust changed design, submitted new application.
WMECO | Hadley | 6A228-2011 | 01035 | 17.995 | Solar | 18G5 | 2011-11-09 | 2011-12-20 | 30 |  | 30 | [25 empty] | 2011-12-21 |  | 2011-11-28 | No | EXP | [8 empty] | 2012-01-19 | on line
WMECO | Pittsfield | 6B117-2011 | 01201 | 100 | Solar | 30B3 | 2011-11-09 | 2012-01-18 | 50 |  | 50 | [5 empty] | 2011-12-12 |  | -29206 | [17 empty] | 2012-03-02 |  | 2011-12-15 | Yes | EXP | [8 empty] | 2012-05-03 | On line. Generation significantly larger than load.
WMECO | Springfield | 6S74-2011 | 01104 | 60 | Solar | 21S7 | 2011-11-15 | 2012-04-10 | 104 |  | 104 | [25 empty] | 2012-04-10 |  | 2012-03-01 | No | EXP | [9 empty] | Purge letter sent 5/20/13. Waiting for Cust to return IA and completion documents to schedule Witness Test. Withdrawn
WMECO | Springfield | 6S75-2011 | 01104 | 95 | Solar | 21S7 | 2011-11-15 | 2012-04-09 | 103 |  | 103 | 2011-12-20 |  | -29212 | [22 empty] | 2012-04-19 |  | 2012-03-01 | No | EXP | [6 empty] | 2014-04-30 | 2014-05-05 | 2014-05-05 | Waiting for Cust to return IA and completion documents to schedule Witness Test. Have heard nothing from cust as of 8/21/13. Waiting for Customer. Received most of the completion docs from Interconnecting Customer, waiting for revised drawing with inverter settings Received revised drawing, need inverter setting sheet, Int Customer will provide during Witness Test. Witness Test performed, Witness Test passed, Int Customer is on line.
WMECO | Dalton | 6B120-2011 | 01226 | 13 | Solar | 19A2 | 2011-11-23 | [31 empty] | 2011-12-22 | TBD | EXP | [9 empty] | Cancelled by Cust. Application is incomplete and incorrect. Cust changed design and reapplied.
WMECO | Buckland | 6F286-2011 | 01338 | 57 | Solar | 22B5 | 2011-12-07 | 2012-02-22 | 54 |  | 54 | [25 empty] | 2012-03-12 |  | 2012-01-01 | Yes | EXP | [8 empty] | 2012-05-01 | On line. Third party owned.
WMECO | Greenfield | 6F290-2011 | 01301 | 14.7 | Solar | 21C4 | 2011-12-14 | 2012-01-26 | 31 |  | 31 | [25 empty] | 2012-02-08 |  | 2012-01-01 | No | EXP | [8 empty] | 2012-03-19 | on line
WMECO | Whately | 6A239-2011 | 01093 | 260 | Solar | 18G8 | 2011-12-16 | 2012-04-13 | 84 |  | 84 | [25 empty] | 2012-04-19 |  | 2012-03-16 | No | EXP | [8 empty] | 2012-05-01 | on line
WMECO | Easthampton | 6A241-2011 | 01027 | 3.3 | Wind | 15A5 | 2011-12-22 | 2012-01-04 | 10 |  | 10 | [25 empty] | 2012-01-12 |  | not supplied | No | EXP | [8 empty] | 2012-02-13 | On line. Third party owned. Single phase system on three phase service.
WMECO | Hadley | 6A242-2011 | 01035 | 2000 | Solar | 18G4 | 2011-12-27 | 2012-02-16 | 37 |  | 37 | [15 empty] | 2012-04-02 | 2013-07-09 | 318 | 0 | 318 | 2013-05-03 | 2013-09-12 | 91 | 51 | 40 | 2013-10-04 |  | 2012-07-01 | Yes | STD | [9 empty] | Int Cust cancelled project. Int Cust changed inverters and name, (Impact Study 3/12/12 & IS Option 1 10/17/12) new Impact Study approved for option. ISO-NE notification approved. Third party owned. Stand alone generation. New construction. Detailed Study agreement and check returned to WMECO. Project in Detailed Study mode. Site visit 6/5/13 w/ cust, tech and Verizon, cust needs to decide where to interconnect on property, clock stopped for Detailed Study 6/5/13. Cust asked for an extenstion. Second site visit (8/19/13) interconnection poles laid out work order writing to commence. Work orders written need to put together estimate to include in IA. Draft IAs sent out for review 9/12/13, Customer wants breakdown of IA system upgrades. Cust sent comments on draft Exhibit G. waiting for comments on Draft Exhibit H. Sent IAs for signature. Waiting for signed agreements and money. Construction of project may be delayed due to a required Cultural Review at project site. Recvd signed Exhibits G & H, waiting for monies & insurance to schedule construction.
WMECO | Whately | 6A247-2012 | 01093 | 1000 | Solar | 18G8 | 2012-01-04 | [31 empty] | 2012-07-01 | Yes | STD | [9 empty] | Cancelled by Cust. Cust submitted new application. Stand alone generation. New construction.
WMECO | Whately | 6A250-2012 | 01039 | 1000 | Solar | 18G8 | 2012-01-04 | [31 empty] | 2012-07-01 | Yes | STD | [9 empty] | Cancelled by Cust. Cust submitted new application. Stand alone generation. New construction.
WMECO | Blandford | 6BA253-2012 | 01008 | 1000 | Solar | 19J2 | 2012-01-10 | [31 empty] | 2012-09-18 | Yes | STD | [9 empty] | Cust cancelled project. Stand alone generation. New construction.
WMECO | Blandford | 6BA254-2012 | 01008 | 1000 | Solar | 19J2 | 2012-01-10 | [31 empty] | 2012-09-18 | Yes | STD | [9 empty] | Cust cancelled project. Stand alone generation. New construction. Application has three options 500 kW or 750 kW or 1,000 kW. Highest option listed in Design Capacity.
WMECO | Turners Falls | 6F295-2012 | 01376 | 370 | Hydro | 21C6 | 2012-01-10 | 2012-03-05 | 38 |  | 38 | [15 empty] | 2012-03-20 |  | -29275 | [7 empty] | 2013-03-27 |  | not supplied | No | STD | [9 empty] | cancelled
WMECO | Tolland | 6B125-2012 | 01634 | 3500 | Solar | 19J4 | 2012-01-25 | 2013-01-31 | 257 | 0 | 257 | [15 empty] | 2012-06-18 | 2013-06-07 | 245 | 0 | 245 | 2013-07-31 | 2013-09-06 | 27 |  | 27 | 2013-09-06 |  | 2012-09-25 | Yes | COMP | [6 empty] | 2014-09-25 | 2014-10-03 | 2014-10-03 | Early ISA 6/7/13. Impact Study joint with 6B126-2012 and 6B127-2012. (6/5/12) Int Cust submitted new option, new study will continue when agreement executed (1/25/13). ISO-NE notification submitted and approved. Detailed Study required. Stand alone generation. New construction. Application has two options 2,000 kW or 3,500 kW. Selected option listed in Design Capacity. Customer requested early ISA. Detailed Study has not started yet. Early ISA exhibit G & H sent to cust for signature 6/7/13, rcvd signed Early Exhibit G from Int Cust 6/28/13, waiting for signed Early Exhibit H from Host Cst. rcvd detailed Study check 7/31/13. sent e-mail to cust to set up site visit. Site visit 8/8/13 work orders are being written. sent IA to Customer and Interconnecting Customer 9/6/13. Rcvd signed Exhibit H 9/18/13 Waiting for signed Exhibit G and payment for system upgrades. Payment for upgrades received. Easement for interconnection service has not been completed, waiting for the lawyers to finalize. The line recloser controls and tranfer trip equpment have been installed. ION meter has been installed. DTT is commissioned. waiting for revised completion info from Customer. Rcvd revised info, Witness Test scheduled, Witness test passed, Aproval to Operate sent to Interconnecting Customer and Customer, Project is on line.
WMECO | Tolland | 6B126-2012 | 01634 | 1000 | Solar | 19J4 | 2012-01-25 | [19 empty] | 2012-06-18 |  | -29337 | [9 empty] | 2012-09-25 | Yes | STD | [9 empty] | Int cust cancelled 6/12/13. Impact Study joint with 6B126-2012 and 6B127-2012. On hold by Cust. ISO-NE notification and Detailed Study required if project proceeds. Stand alone generation. New construction.
WMECO | Tolland | 6B127-2012 | 01634 | 1000 | Solar | 19J4 | 2012-01-25 | [19 empty] | 2012-06-18 |  | -29337 | [9 empty] | 2012-09-25 | Yes | STD | [9 empty] | Int Cust cancelled 6/12/13. Impact Study joint with 6B126-2012 and 6B127-2012. On hold by Cust. ISO-NE notification and Detailed Study required if project proceeds. Stand alone generation. New construction. Application has three options 500 kW or 750 kW or 1,000 kW. Highest option listed in Design Capacity.
WMECO | Tolland | 6B128-2012 | 01634 | 1000 | Solar | 19J4 | 2012-01-25 | [31 empty] | 2012-09-25 | Yes | STD | [9 empty] | Cancelled by Cust after Scoping Meeting. Stand alone generation. New construction.
WMECO | West Springfield | 6S90-2012 | 01089 | 110 | Solar | 21N5 | 2012-02-01 | 2012-03-02 | 22 |  | 22 | [5 empty] | 2012-02-29 |  | -29261 | [17 empty] | 2012-05-24 |  | not supplied | No | EXP | [8 empty] | 2012-07-12 | On Line. Cust upgraded service.
WMECO | Pittsfield | 6B130-2012 | 01201 | 2000 | Solar | 15E2 | 2012-02-02 | [31 empty] | 2012-10-02 | Yes | STD | [9 empty] | Cancelled by Cust after being on hold by Cust. Impact Study Agreement sent to Cust for joint study with 6B131-2012 who did not execute it. Stand alone generation. New construction.
WMECO | Pittsfield | 6B131-2012 | 01201 | 3000 | Solar | 15E2 | 2012-02-02 | [31 empty] | 2012-10-02 | Yes | STD | [9 empty] | Talked with Customer 9/16/13 re: status of project moving forward, Customer will talk with investors, WMECO to send e-mail with request to Customer of project status. Cust submitted 3 MW option 4/24/13 for separate Impact Study. Impact Study Agreement sent to Cust for joint study with 6B130-2012 who did not execute it. Stand alone generation. New construction. Application has options 500 kW or 750 kW or 1,000 kW or 3,000. Current 3 MW option listed in Design Capacity. withdrawn
WMECO | Ludlow | 6S91-2012 | 01056 | 3000 | Solar | 19S3 | 2012-02-03 | [31 empty] | 2012-09-30 | Yes | STD | [9 empty] | Cancelled by Int Cust who submitted new applications. Stand alone generation. New construction.
WMECO | Hatfield | 6A262-2012 | 01038 | 45.6 | Solar | 18G5 | 2012-02-06 | 2012-04-11 | 47 |  | 47 | [25 empty] | 2012-05-02 |  | not supplied | Yes | EXP | [6 empty] | 2012-08-24 | 2012-08-28 | 2012-08-28 | on line
WMECO | Shutesbury | 6A263-2012 | 01072 | 11.4 | Solar | 18G7 | 2012-02-07 | 2012-05-01 | 59 |  | 59 | [25 empty] | 2012-05-25 |  | 2/2012 | No | EXP | [8 empty] | 2012-06-13 | on line
WMECO | Deerfield | 6F303-2012 | 01342 | 22.8 | Solar | 22B4 | 2012-02-07 | 2012-05-07 | 63 |  | 63 | [5 empty] | 2012-04-17 |  | -29294 | [17 empty] | 2012-05-10 |  | 2012-04-01 | Yes | EXP | [8 empty] | 2012-09-12 | on line
WMECO | Southampton | 6A266-2012 | 01073 | 11.18 | Solar | 15A1 | 2012-02-17 | 2012-04-04 | 33 |  | 33 | [25 empty] | 2012-06-18 |  | 2012-04-25 | No | EXP | [8 empty] | 2012-08-06 | on line
WMECO | Whately | 6A267-2012 | 01373 | 2000 | Solar | 18G8 | 2012-02-17 | 2012-04-10 | 37 |  | 37 | [15 empty] | 2012-05-17 | 2012-11-07 | 121 | 0 | 121 | 2012-09-12 | 2013-01-22 | 90 | 0 | 90 | 2013-02-26 |  | 2012-09-01 | Yes | STD | [6 empty] | 2014-06-09 | 2014-06-16 | 2014-06-25 | Int Cust changed their name. Now 3rd party owned. ISO-NE notification approved. Stand alone generation. New construction. Application has three options 1,000 kW or 1,500 kW or 2,000 kW. Option selected listed in Design Capacity. Waiting for Customer to return signed IA. Cust Exhibit G rcvd 3/6/13. Purge letter sent to Int Cust 5/20/13. Sent new tariff IA form sent to cust & Int Cust for signature 6/6/13. Rcvd new tariff IA from Int Cust 6/11/13. Need payments to schedule construction. Call w/ Cust ISD by early December providing all upgrade monies & insurance recvd by WMECO by 9/3/13. System upgrade monies received, construction scheduled. Construction of interconnection service completed, Customer is energized for testing purposes only, Communication to primary meter is required before ION meter set can be scheduled. POTS line to primary meter delayed by Verizon, WMECO investigated using alternate mode of communicatio, after testing device provided by Customer, the device does not communicate with the ION meter, need Verizon POTS line in service before ION meter is installed. Completion docs have been received and reviewed. ION meter has been set. Witness Test scheduled. Witness Test passed. Approval to operate given. Solar facility is on line.
WMECO | Blandford | 6B133-2012 | 01008 | 2000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | STD | [9 empty] | Cancelled by Cust, had been on hold by Cust. Impact Study Agreement for joint study with 6B135-2012 and 6B136-2012 sent to Cust not executed. Stand alone generation. New construction.
WMECO | Blandford | 6B134-2012 | 01008 | 1000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | STD | [9 empty] | Cancelled by Cust. Not included in joint Impact Study with associated applications. Stand alone generation. New construction.
WMECO | Blandford | 6B135-2012 | 01008 | 1000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | STD | [9 empty] | Cancelled by Cust, had been on hold by Cust. Impact Study Agreement for joint study with 6B133-2012 and 6B136-2012 sent to Cust not executed. Stand alone generation. New construction.
WMECO | Blandford | 6B136-2012 | 01008 | 4000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | STD | [9 empty] | Talked with Customer 9/16/13 re: status of project moving forward, Customer will talk with investors, WMECO to send e-mail with request to Customer of project status. Cust submitted 3 MW and 4 MW options 4/24/13 for separate Impact Study. Impact Study Agreement for joint study with 6B133-2012 and 6B135-2012 sent to Cust not executed. Stand alone generation. New construction. Application has options 1,000 kW or 3,000 kW or 4,000 kW. Highest option listed in Design Capacity. withdrawn
WMECO | Blandford | 6B137-2012 | 01008 | 1000 | Solar | 19J4 | 2012-02-17 | [31 empty] | 2012-10-30 | Yes | STD | [9 empty] | Cancelled by Cust. Not included in joint Impact Study with associated applications. Stand alone generation. New construction.
WMECO | Ludlow | 6S96-2012 | 01056 | 2000 | Solar | 27A5 | 2012-02-23 | 2012-06-29 | 90 |  | 90 | [15 empty] | 2012-08-02 | 2012-10-22 | 56 |  | 56 | 2012-12-26 | 2013-03-08 | 50 | 0 | 50 | 2013-03-14 |  | 2012-09-30 | Yes | STD | 2013-07-31 |  | 2013-07-30 |  |  |  | 2013-08-02 | 2013-08-07 | 2013-08-26 | Scoping Mtg. Held. IA executed. Impact Study Complete. Detailed Study Complete. Line construction complete. System is online under Temporary SOG while DTT/substation issue dealt with. Temporary SOG is valid only until transfer trip is commissioned.
WMECO | Ludlow | 6S97-2012 | 01056 | 1000 | Solar | 19S3 | 2012-02-23 | [31 empty] | 2012-09-30 | Yes | STD | [9 empty] | Cancelled by Int Cust. Proceeding with one application at this site. Third party owned. Stand alone generation. New construction.
WMECO | Hatfield | 6A271-2012 | 01038 | 2000 | Solar | 18G6 | 2012-02-24 | 2012-07-19 | 102 |  | 102 | [15 empty] | 2012-04-30 | 2012-11-01 | 130 | 0 | 130 | 2012-10-10 | 2012-10-17 | 6 | 0 | 6 | 2013-02-13 |  | 2012-11-01 | Yes | STD | [9 empty] | Int Cust trying to find Cust and make this 3rd party owned. ISO-NE notification approved. Stand alone generation. New construction. Sent IA to Jen for signature to send to cust for signature 6/10/13. Developer sent letter 6/30/13 requesting temp suspension due to court case. Developer sent in first part of system upgrade monies, They have 120 days to send in the remainder of the monies. withdrawn
WMECO | Pittsfield | 6B139-2012 | 01201 | 2000 | Solar | 30B2 | 2012-02-24 | [31 empty] | 2012-11-06 | Yes | STD | [9 empty] | Talked with Customer 9/16/13 re: status of project moving forward, Customer will talk with investors, WMECO to send e-mail with request to Customer of project status. Cust decided to move forward with separate Impact Study. Impact Study will no longer be joint with 6B140-2012. Stand alone generation. New construction. withdrawn
WMECO | Pittsfield | 6B140-2012 | 01201 | 1000 | Solar | 30B2 | 2012-02-24 | [31 empty] | 2012-11-06 | Yes | STD | [9 empty] | Cancelled by Cust, had been on hold by Cust. Impact Study will no longer be joint with 6B139-2012. Stand alone generation. New construction. Application has three options 500 kW or 750 kW or 1,000 kW. Highest option listed in Design Capacity.
WMECO | Agawam | 6S98-2012 | 01001 | 2000 | Solar | 30A6 | 2012-02-27 | [31 empty] | 2012-11-06 | Yes | STD | [9 empty] | Cancelled by Int Cust. Stand alone generation. New construction.
WMECO | Agawam | 6S99-2012 | 01001 | 2000 | Solar | 30A6 | 2012-02-27 | [31 empty] | 2012-11-06 | Yes | STD | [9 empty] | Cancelled by Int Cust. Stand alone generation. New construction. Application has three options 1,000 kW or 1,500 kW or 2,000 kW. Highest option listed in Design Capacity.
WMECO | Easthampton | 6A273-2012 | 01027 | 11 | Solar | 15A5 | 2012-03-01 | [31 empty] | 2012-03-20 | TBD | EXP | [9 empty] | Cancelled by Cust. Submitted new Simplified Application.
WMECO | Lee | 6B141-2012 | 01238 | 295 | Solar | 16B5 | 2012-03-01 | 2012-06-11 | 71 |  | 71 | [25 empty] | 2012-06-14 |  | Q2 2012 | No | EXP | [8 empty] | 2012-08-10 | On line. Third party owned.
WMECO | Easthampton | 6A275-2012 | 01027 | 26.4 | Solar | 15A3 | 2012-03-02 | 2012-05-11 | 50 |  | 50 | [25 empty] | 2012-09-12 |  | 2012-04-15 | No | EXP | [8 empty] | 2012-10-04 | On line. New construction service.
WMECO | Hadley | 6A277-2012 | 01035 | 1000 | Solar | 17K1 | 2012-03-12 | [31 empty] | 2012-10-01 | Yes | STD | [9 empty] | Cancelled by Cust. Stand alone generation. New construction.
WMECO | Hadley | 6A278-2012 | 01035 | 2500 | Solar | 17K1 | 2012-03-12 | 2012-07-18 | 90 |  | 90 | [15 empty] | 2012-08-29 | 2013-06-07 | 194 | 0 | 194 | 2013-05-31 | 2013-07-23 | 36 | 18 | 18 | 2013-07-30 |  | 2012-10-12 | Yes | STD | [6 empty] | 2014-06-09 | 2014-06-16 | 2014-07-02 | (impact study 8/7/12) Cust decided on new option. New Impact Study (3/4/13) required. Stand alone generation. New construction. Application has two options 1,500 kW or 2,500 kW. Highest option listed in Design Capacity. Sent Detailed Study to Customer, rcvd signed detailed study agrement 5/16/13, waiting for first check. Check rcvd for Detailed Study 6/5/13. Site visit to design service 6/18/13. Customer needs to decide where to interconnect service. Cust decided on new intconnect point and sent new site plan 7/5/13. Tech to write work order. Work orders completed 7/19/13, sent cust %10 est for circuit upgrades 7/23/13. Rcvd Scheule Z for Town of Ashfield, Project is third party owned as of 7/23/13, waiting for revised app with Town of Ashfield info. Rcvd revised Sched Z 7/23/13, rcvd revised app 7/24/13. Sent draft IAs for signature 7/30/13. Received signd IA. Call w/ Cust ISD by 11/18/13 providing all upgrade monies & insurance recvd by WMECO by 8/5/13. System upgrade monies received, construction scheduled. Construction of interconnection service is compelted, Customer is energized for testing purposes only, Communication to primary meter is required before ION meter set can be scheduled. Completion docs have been received and reviewed. ION meter has been set. Witness Test scheduled. Witness Test passed. Waiting on Verizon to finish the two FDDA lines. Verizon finished FDDA lines, tranfer trip finished and commissioned and in service. Project is on line.
WMECO | Longmeadow | 6S102-2012 | 01106 | 45.6 | Solar | 22H11 | 2012-03-14 | 2012-05-03 | 36 |  | 36 | [25 empty] | 2012-06-11 |  | 2012-07-01 | No | EXP | [8 empty] | 2012-08-15 | On line. Third party owned.
WMECO | Lenoxdale | 6B142-2012 | 01242 | 780 | Solar | 17G3 | 2012-03-19 | 2013-03-27 | 258 |  | 258 |  |  |  | 0 | [11 empty] | 2012-12-17 | 2013-07-08 | 138 | 29 | 109 | 2013-05-10 | 2013-06-07 | 20 | 0 | 20 | 2013-06-03 |  | 2012-05-01 | Yes | STD | [9 empty] | Int Cust changed inverters and size on 021413, almost done w/ report continued w/ original study for final report, cust submitted new option 021913 revised study, waited for updated project info. Detailed Study required. Signed Detailed Study Agreement and check rcvd. Third party owned. Stand alone generation or Cust to upgrade their service. Application has three options 1,000 kW or 885 kW or 780 kW. Customer's current design option listed in Design Capacity. Sent plus/minus 10% and draft IA to Int cust 5/29/13. Sent Exhibit G & H for signatures 6/6/13. Rvcd signed Exhibit H 6/22/13. Sent phone line specs to customer 6/26/13. Conf call w/ customer 7/29/13 to discuss ISD dates and requirements for those dates. Liability insurance received. Sent two revised construction schedules, waiting for Customer to send in system upgrade monies by 8/30/13. Per conf call with Interconnecting Customer on 9/9/13, If the checks and new in service dates are provided before or during our next conference call which is scheduled for 9/23/13, we will be able to discuss the next steps. Until these are provided, we will not prepare another tentative construction schedule. withdrawn Interconnection Customer stated that the ball is in their court and that WMECO will not be held responsible for any delay for construction at this time. It is the understanding of both Interconnection Customer and WMECO that completed construction for this project is not anticipated in 2013. Int Customer in liquidation. Sent notice letter, no response. Withdrawn 6/27/14. Int Cust owes WMECO money.
WMECO | Lee | 6B143-2012 | 01238 | 500 | Solar | 17G7 | 2012-03-19 | 2013-03-27 | 258 |  | 258 | [15 empty] | 2013-01-09 | 2013-07-08 | 123 | 29 | 94 | 2013-05-10 | 2013-06-07 | 20 | 0 | 20 | 2013-06-03 |  | 2012-05-12 | Yes | STD | [9 empty] | Int Cust changed inverters,021413 almost done w/ report continued w/ original study for final report, cust submitted new option 021913, revised study, waited for updated project info. Detailed Study required. Signed detailed Study Agreement and check rcvd. Third party owned. Stand alone generation. New construction. Sent plus/minus 10% and draft IA to Int cust. Sent Exhibit G & H for signatures 6/6/13. Conf call w/ customer 7/29/13 to discuss ISD dates and requirements for those dates. Liability insurance received. Exhibit H from Town of Lee received. Sent two revised construction schedules, waiting for Customer to send in system upgrade monies by 8/30/13. Per conf call with Interconnecting Customer on 9/9/13, If the checks and new in service dates are provided before or during our next conference call which is scheduled for 9/23/13, we will be able to discuss the next steps. Until these are provided, we will not prepare another tentative construction schedule. withdrawn Interconnection Customer stated that the ball is in their court and that WMECO will not be held responsible for any delay for construction at this time. It is the understanding of both Interconnection Customer and WMECO that completed construction for this project is not anticipated in 2013. Int Customer in liquidation. Sent notice letter, no response. Withdrawn 6/27/14. Int Cust owes WMECO money.
WMECO | Lee | 6B144-2012 | 01238 | 750 | Solar | 16B5 | 2012-03-19 | 2013-03-27 | 258 |  | 258 | [15 empty] | 2013-01-09 | 2013-07-08 | 123 | 24 | 99 | 2013-06-04 | 2013-06-07 | 4 | 0 | 4 | 2013-06-26 |  | 2012-05-01 | Yes | STD | [9 empty] | Impact Study joint with 6B145-2012. Int Cust changed inverters, 021413, revised study, waited for updated project info. Detailed Study required. Third party owned. May be new construction service. Application has two options 1,000 kW or 750 kW. Customer's current design option listed in Design Capacity. Received signed Detail Study agreement 052413, waiting for first check. Plus/minus 10% sent to cust 6/7/13. Sent Exhibit G & H for signature 6/28/13. Conf call w/ customer 7/29/13 to discuss ISD dates and requirements for those dates. Liability insurance received. Exhibit H from Town of Lee received. Sent two revised construction schedules, waiting for Customer to send in system upgrade monies by 8/30/13. Per conf call with Interconnecting Customer on 9/9/13, If the checks and new in service dates are provided before or during our next conference call which is scheduled for 9/23/13, we will be able to discuss the next steps. Until these are provided, we will not prepare another tentative construction schedule. withdrawn Interconnection Customer stated that the ball is in their court and that WMECO will not be held responsible for any delay for construction at this time. It is the understanding of both Interconnection Customer and WMECO that completed construction for this project is not anticipated in 2013. Int Customer in liquidation. Sent notice letter, no response. Withdrawn 6/27/14. Int Cust owes WMECO money.
WMECO | Lee | 6B145-2012 | 01238 | 750 | Solar | 16B5 | 2012-03-21 | 2013-03-27 | 256 |  | 256 | [15 empty] | 2013-01-09 | 2013-07-08 | 123 | 24 | 99 | 2013-06-04 | 2013-06-07 | 4 | 0 | 4 | 2013-06-26 |  | 2012-05-01 | Yes | STD | [9 empty] | Impact Study required joint with 6B144-2012. Int Cust changed inverters 021413, revised study, waited for updated project info . Detailed Study required. Third party owned. Stand alone generation. New construction. Application has two options 1,000 kW or 750 kW. Customer's current design option listed in Design Capacity. Received signed Detail Study agreement 052413, waiting for first check. Plus/minus 10% sent to cust 6/7/13. Sent Exhibit G & H for signature 6/28/13. Conf call w/ customer 7/29/13 to discuss ISD dates and requirements for those dates. Liability insurance received. Exhibit H from Town of Lee received. Sent two revised construction schedules, waiting for Customer to send in system upgrade monies by 8/30/13. Per conf call with Interconnecting Customer on 9/9/13, If the checks and new in service dates are provided before or during our next conference call which is scheduled for 9/23/13, we will be able to discuss the next steps. Until these are provided, we will not prepare another tentative construction schedule. withdrawn Interconnection Customer stated that the ball is in their court and that WMECO will not be held responsible for any delay for construction at this time. It is the understanding of both Interconnection Customer and WMECO that completed construction for this project is not anticipated in 2013. Int Customer in liquidation. Sent notice letter, no response. Withdrawn 6/27/14. Int Customer owes WMECO money.
WMECO | Lee | 6B146-2012 | 01238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | STD | [9 empty] | Cancelled by Int Cust. Will be third party owned. Stand alone generation. New construction.
WMECO | Lee | 6B147-2012 | 01238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | STD | [9 empty] | Cancelled by Int Cust. Will be third party owned. Stand alone generation. New construction.
WMECO | Lee | 6B148-2012 | 01238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | STD | [9 empty] | Cancelled by Int Cust. Will be third party owned. Stand alone generation. New construction.
WMECO | Lee | 6B149-2012 | 01238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | STD | [9 empty] | Cancelled by Int Cust. Will be third party owned. Stand alone generation. New construction.
WMECO | Lee | 6B150-2012 | 01238 | 1000 | Solar | 16B5 | 2012-03-21 | [31 empty] | 2012-05-01 | Yes | STD | [9 empty] | Cancelled by Int Cust. Will be third party owned. Stand alone generation. New construction.
WMECO | Amherst | 6A286-2012 | 01002 | 3750 | Solar | 17K2 | 2012-03-22 | [31 empty] | 2012-10-01 | Yes | STD | [9 empty] | Purge letter sent 5/20/13. On hold by Int Cust. Held Scoping Meeting. Impact Study required. Int Cust may submit option(s). Third party owned. Stand alone generation. New construction. Withdrawn
WMECO | Whately | 6A287-2012 | 01373 | 1000 | Solar | 18G8 | 2012-03-22 | [31 empty] | 2012-10-01 | Yes | STD | [9 empty] | Cancelled by Cust who submitted new application. Stand alone generation. New construction.
WMECO | Middlefield | 6B156-2012 | 01243 | 12.04 | Solar | 18C2 | 2012-03-29 | 2012-06-18 | 56 |  | 56 | [25 empty] | 2012-07-17 |  | 2012-04-24 | No | EXP | [7 empty] | 2012-09-13 | 2012-09-13 | on line
WMECO | Whately | 6A289-2012 | 01373 | 1000 | Solar | 18G8 | 2012-04-03 | [31 empty] | 2012-01-01 | Yes | STD | [9 empty] | Purge letter sent 5/20/13. Withdrawn 7/8/13 due to no response. On hold by Int Cust. Held Scoping Meeting. Impact Study required. Int Cust deciding if will move forward. Third party owned. Stand alone generation. New construction.
WMECO | Hatfield | 6A290-2012 | 01038 | 44.4 | Solar | 18G5 | 2012-04-06 | 2012-06-08 | 44 |  | 44 | [25 empty] | 2012-06-29 |  | 2012-04-30 | No | EXP | [8 empty] | 2012-07-27 | on line
WMECO | Hadley | 6A291-2012 | 01035 | 1000 | Solar | 17K1 | 2012-04-06 | 2012-06-29 | 59 |  | 59 | [15 empty] | 2012-08-29 |  | -29388 | [9 empty] | 2012-10-01 | Yes | STD | [9 empty] | Int Cust cancelled project, had been on hold. Joint Impact Study with 6A278-2012 in progress but on hold by Int Cust. Stand alone generation. New construction.
WMECO | Blandford | 6B159-2012 | 01008 | 125 | Solar | 19J4 | 2012-04-09 | [31 empty] | 2012-05-25 | Yes | STD | [9 empty] | Impact Study estimate sent to customer. Cust submitted two options. On hold by Cust. Third party owned. Either new construction or cust to upgrade service. Third party owned. Application has three options 50 kW or 100 kW or 125 kW. Highest option listed in Design Capacity. cancelled
WMECO | Hatfield | 6A294-2012 | 01088 | 67.5 | Solar | 18G5 | 2012-04-10 | 2012-10-09 | 126 |  | 126 | [25 empty] | 2012-10-10 |  | 2012-10-31 | No | EXP | [8 empty] | 2012-11-13 | On line. Third party owned. Will not export.
WMECO | Chesterfield | 6F316-2012 | 01012 | 60 | Solar | 18K3 | 2012-04-11 | 2012-05-18 | 27 |  | 27 | [5 empty] | 2012-07-12 |  | -29354 | [17 empty] | 2012-05-31 |  | 2012-05-01 | No | EXP | [8 empty] | 2012-09-25 | on line
WMECO | Turners Falls | 6F319-2012 | 01376 | 8.6 | Solar | 21C2 | 2012-04-23 | 2012-07-18 | 61 |  | 61 | [25 empty] | 2012-07-25 |  | 2012-04-30 | No | EXP | [8 empty] | 2012-09-18 | On line. Two phase system on three phase service.
WMECO | Cummington | 6F322-2012 | 01026 | 12.255 | Solar | 18K3 | 2012-05-14 | [31 empty] | 2012-05-25 | TBD | EXP | [9 empty] | Purge letter sent 5/20/13. Withdrawn 7/8/13 due to no response. Held Scoping Meeting. Waiting for info.
WMECO | Hadley | 6A312-2012 | 01035 | 95 | Solar | 17K6 | 2012-05-17 | 2012-07-05 | 34 |  | 34 | [25 empty] | 2012-09-25 |  | 2012-07-13 | No | EXP | [6 empty] | 2012-12-27 | 2012-12-28 | 2012-12-28 | on line
WMECO | West Springfield | 6S112-2012 | 01089 | 333 | Solar | 21N8 | 2012-05-18 | 2012-08-15 | 62 |  | 62 | [25 empty] | 2012-08-17 |  | 2012-10-29 | No | EXP | [9 empty] | Int Cust delayed construction to 2013. Need completion documents to schedule Witness Test. Third party owned. Have heard nothing from cust as of 8/21/13. Waiting for Customer. Custoemr may be cancelling this project. Cancelled
WMECO | Turners Falls | 6F325-2012 | 01376 | 500 | Solar | 21C3 | 2012-05-29 | [31 empty] | 2012-11-01 | Yes | EXP | [9 empty] | Purge letter sent 5/20/13. Impact Study Agreement out for signature. Need signed agreement and check for initial payment. Third party owned. Stand alone generation. New construction. Withdrawn
WMECO | Easthampton | 6A316-2012 | 01027 | 298 | Solar | 15A3 | 2012-05-30 | 2013-08-27 | 313 |  | 313 | 2013-08-28 | 2013-12-10 | 71 | 58 | 13 | 2013-12-10 |  | -29707 | 52 | [18 empty] | 2012-08-10 |  | EXP | [9 empty] | New option (option 2) submitted. Application Complete. In Supplemental Review. Held Meeting. Application cancelled per Interconnecting Customer 4/28/14
WMECO | Easthampton | 6A317-2012 | 01027 | 120 | Solar | 15A2 | 2012-05-30 | 2013-08-06 | 298 | 297 | 1 | 2013-08-07 | 2013-09-11 | 25 | 5 | 20 | 2014-04-29 | 2014-05-20 | 16 | 0 | 16 | [15 empty] | 2014-07-31 |  | 2012-08-10 | TBD | EXP | [6 empty] | 2015-06-26 | 2015-06-26 | 2015-07-10 | New option (option 2) submitted. Application Complete. Supplemental Review complete. Received signed Exhibit H. Received signed Exhibit G. Received CoC. Compliance docs received. Witness Test performed. Online
WMECO | Deerfield | 6F328-2012 | 01342 | 19.99 | Solar | 22B1 | 2012-06-04 | 2012-08-14 | 51 |  | 51 | [25 empty] | 2012-08-29 |  | 2012-09-01 | No | EXP | [6 empty] | 2012-11-01 | 2012-11-07 | 2012-11-08 | on line
WMECO | Springfield | 6S115-2012 | 01104 | 500 | Solar | 5J15 | 2012-06-04 | 2012-10-18 | 96 |  | 96 | [25 empty] | 2013-02-21 |  | Q4 2012 | No | EXP | [6 empty] | 2013-05-20 | 2013-05-21 | 2013-05-30 | Third party owned. On line.
WMECO | Hatfield | 6A320-2012 | 01038 | 1000 | Solar | 18G6 | 2012-06-08 | [31 empty] | 2012-06-01 | Yes | STD | [9 empty] | Sent purge letter 5/20/13. Int cust cancelled 6/12/13. Held Scoping Meeting. On hold by Int Cust. See 6A321-2012 and 6A322-2012. Stand alone generation. New construction.
WMECO | Hatfield | 6A321-2012 | 01038 | 1000 | Solar | 18G6 | 2012-06-08 | [31 empty] | 2012-06-01 | Yes | STD | [9 empty] | Sent purge letter 5/20/13. Int cust cancelled 6/12/13. Held Scoping meeting. Was on hold by Int Cust. See 6A320-2012 and 6A322-2012. Stand alone generation. New construction.
WMECO | Hatfield | 6A322-2012 | 01038 | 1000 | Solar | 18G6 | 2012-06-08 | [31 empty] | 2012-06-01 | Yes | STD | [9 empty] | Sent purge letter 5/20/13. Int cust cancelled 6/12/13. Held Scoping Meeting. On hold by Int Cust. See 6A320-2012 and 6A321-2012. Stand alone generation. New construction.
WMECO | Hinsdale | 6B169-2012 | 01235 | 23.995 | Solar | 18C2 | 2012-06-27 | 2012-08-03 | 27 |  | 27 | [25 empty] | 2012-08-10 |  | 2012-08-01 | Yes | EXP | [7 empty] | 2012-09-28 | 2012-09-28 | on line
WMECO | Shelburne Falls | 6F338-2012 | 01370 | 82 | Solar | 29R1 | 2012-06-28 | 2012-10-07 | 70 |  | 70 | [25 empty] | 2012-10-22 |  | 2012-09-01 | No | EXP | [6 empty] | 2012-11-28 | 2012-12-05 | 2012-12-06 | on line
WMECO | Easthampton | 6A332-2012 | 01027 | 14 | Solar | 15A5 | 2012-07-13 | 2012-11-02 | 79 |  | 79 | 2012-11-05 | 2012-11-16 | 10 | 0 | 10 | [20 empty] | 2012-11-20 |  | 2012-09-01 | No | EXP | [6 empty] | 2012-12-14 | 2012-12-20 | 2012-12-20 | on line
WMECO | Springfield | 6S123-2012 | 01104 | 142 | Solar | 5J9 | 2012-07-16 | 2012-10-23 | 70 |  | 70 | [25 empty] | 2013-03-13 |  | not supplied | No | EXP | [6 empty] | 2012-04-10 | 2013-04-11 | 2013-04-23 | On line. Third party owned.
WMECO | Springfield | 6S124-2012 | 01104 | 266 | Solar | 5J18 | 2012-07-16 | 2012-08-30 | 34 |  | 34 | [25 empty] | 2013-04-16 |  | 2012-10-30 | No | EXP | [6 empty] | 2013-05-30 | 2013-05-31 | 2013-05-31 | New construction service. On line
WMECO | Southwick | 6S126-2012 | 01077 | 1500 | Solar | 29A1 | 2012-07-17 | 2012-10-18 | 66 | 65 | 1 | [10 empty] | 2012-10-19 | 2013-03-05 | 93 | 89 | 4 | 2013-04-16 | 2013-09-20 | 110 | 0 | 110 | 2014-03-31 | 2014-08-20 | 99 | 99 | 0 | 2013-12-16 |  | Q4 2012 | Yes | STD | [9 empty] | Impact Study in progress. Cust to submit info. Third party owned. Stand alone generation. New construction. Sent ISO docs to Customer. Waiting for Customer to sned ISO docs. Waiting for final Impact Study report from vendor. Received final report from vendor, sent report to customer 9/20/13. Detailed Stduy Agreement sent to customer. Talked to Carter Wilde-Widling on 11/26/13, the Customer is waiting for the SREC II program results in order to mmove forward with the project. It will not be on line before June 2014 and they may change their design to offset customer load. Received signed Detailed Study Agreement 12/9/13 as well as request for an extension for the Detailed Study phase as the Customer cannot move forward until MA SREC-II is in place. Extension has lapsed, Customer is moving forward with the detailed Study, proposed dates for site visit, Customer is not ready, will notify WMECO when ready, project is on Customer hold. Held site visit, after site visit Customer informed WMECO PM that the adjoining resident objected to overhead poles, PM got information on pad mounted metering, however WMECO does not use padmounted recloser. The Customer informed WMECO that the overhead equipment is no longer an issue. The technician is writing the work order. Work order has been written, Customer has Early ISA from December 2013, sent new Exhibit G & H dated August 20, 2014, Exhibit G included plu/minus 10% and construction schedule. Customer wants to send construction monies ASAP. Waiting for Customer to send system Modifications monies. Verizon has not yet set poles. cancelled
WMECO | Amherst | 6A336-2012 | 01002 | 11.4 | Solar | 19B16 | 2012-07-24 | 2012-09-28 | 48 |  | 48 | [25 empty] | 2012-10-11 |  | 2012-08-01 | No | EXP | [6 empty] | 2012-11-15 | 2012-11-16 | 2012-11-16 | on line
WMECO | Hatfield | 6A339-2012 | 01038 | 175 | Solar | 18G5 | 2012-07-27 | 2012-08-31 | 26 |  | 26 | [25 empty] | 2012-10-09 |  | not supplied | No | EXP | [6 empty] | 2012-11-29 | 2012-12-03 | 2012-12-01 | on line
WMECO | Amherst | 6A341-2012 | 01002 | 34.2 | Solar | 17K2 | 2012-07-30 | 2012-11-29 | 86 |  | 86 | 2012-11-30 | 2012-12-04 | 3 | 0 | 3 | [20 empty] | 2012-12-05 |  | 2012-09-12 | No | EXP | [6 empty] | 2012-12-27 | 2012-12-28 | 2012-12-31 | on line
WMECO | Amherst | 6A343-2012 | 01027 | 57 | Solar | 17K8 | 2012-07-31 | 2012-12-10 | 92 |  | 92 | 2012-12-11 | 2013-01-08 | 19 | 0 | 19 | [20 empty] | 2013-01-10 |  | 2012-09-01 | No | EXP | [6 empty] | 2013-02-26 | 2013-02-28 | 2013-02-28 | on line
WMECO | Amherst | 6A344-2012 | 01002 | 29.985 | Solar | 17K7 | 2012-08-01 | 2012-10-03 | 45 |  | 45 | [25 empty] | 2012-11-20 |  | not supplied | No | EXP | [6 empty] | 2012-12-18 | 2012-12-19 | 2012-12-19 | on line
WMECO | Greenfield | 6F354-2012 | 01301 | 135 | Solar | 21C1 | 2012-08-17 | 2012-10-29 | 50 |  | 50 | [25 empty] | 2012-11-20 |  | not supplied | No | EXP | [6 empty] | 2012-12-10 | 2012-12-12 | 2012-12-12 | on line
WMECO | Gill | 6F355-2012 | 01354 | 1250 | Diesel | 21B8 | 2012-08-20 | 2012-09-12 | 17 |  | 17 | [15 empty] | 2012-12-14 | 2013-08-21 | 171 | 17 | 154 | [5 empty] | 2013-12-12 |  | 2012-11-25 | TBD | STD | [6 empty] | 2017-08-10 | 2017-05-19 | 2017-08-21 | Protection review in progress. Will not export. Closed transition emergency generator. ISO notification not required. Waiting for Customer. No longer waiting for customer, need protection review of information that customer sent. Review finished need to send IA. Waiting for information from Customer. Received signed Exhibit G & H. Waiting for relay test results from Customer.
WMECO | Springfield | 6S136-2012 | 01119 | 333 | Solar | 20A33 | 2012-08-20 | 2012-10-05 | 34 |  | 34 | [25 empty] | 2012-12-21 |  | 2012-11-01 | No | EXP | [6 empty] | 2012-12-27 | 2012-12-31 | 2012-12-31 | On line. Third party owned.
WMECO | Tolland | 6B180-2012 | 01034 | 136.8 | Solar | 19J4 | 2012-08-22 | [31 empty] | 2013-01-01 | Yes | STD | [9 empty] | Purge letter sent 5/20/13. Withdrawn 7/8/13 due to no response. Waiting for Cust to submit info. New Construction.
WMECO | Amherst | 6A347-2012 | 01002 | 14 | Solar | 17K8 | 2012-08-24 | 2012-11-26 | 64 |  | 64 | 2012-11-27 | 2012-11-29 | 3 | 0 | 3 | [20 empty] | 2012-11-30 |  | 2012-12-01 | Yes | EXP |  | 2012-12-06 | 2012-12-06 | 1 | 0 | 1 | 2012-12-14 | 2012-12-17 | 2012-12-17 | on line
WMECO | Leyden | 6F358-2012 | 01337 | 38 | Solar | 22B7 | 2012-08-28 | 2012-09-07 | 8 |  | 8 | [25 empty] | 2012-11-06 |  | 2012-12-01 | Yes | EXP | [6 empty] | 2013-05-17 | 2013-05-22 | 2013-05-22 | on line
WMECO | Easthampton | 6A349-2012 | 01027 | 83 | Solar | 15A2 | 2012-08-29 | 2012-09-26 | 20 |  | 20 | [25 empty] | 2013-01-16 |  | 2012-11-12 | No | EXP | [6 empty] | 2013-03-29 | 2013-04-02 | 2013-04-02 | On line. New construction service.
WMECO | Greenfield | 6F360-2012 | 01301 | 3.4 | Solar | 28WNW_1 | 2012-08-29 | 2012-09-20 | 16 |  | 16 | [25 empty] | 2013-01-15 |  | 2012-09-30 | No | STD | [6 empty] | 2013-04-22 | 2013-04-23 | 2013-04-23 | on line
WMECO | Hancock | 6B183-2012 | 01237 | 6000 | Solar | 30B7 | 2012-09-05 | [31 empty] | Q3 2013 | Yes | STD | [9 empty] | Cust sent purge letter 5/20/13. 7/2/13 Cust said will continue. Int Cust submitted new option. Third party owned. Stand alone generation. New Construction. Applicationm has two options 1,500 kW or 6,000 kW. Highest option listed in Design Capacity. withdrawn
WMECO | Hancock | 6B184-2012 | 01237 | 1500 | Solar | 30B7 | 2012-09-05 | [31 empty] | Q3 2013 | Yes | STD | [9 empty] | Cust sent purge letter 5/20/13. 7/2/13 Cust said will continue. Third party owned. Stand alone generation. New Construction. Project hold per Int Cust due to net metering laws. Submitted option to related project. Withdrawn
WMECO | Hancock | 6B185-2012 | 01237 | 1500 | Solar | 30B7 | 2012-09-05 | [31 empty] | Q3 2013 | Yes | STD | [9 empty] | Cust sent purge letter 5/20/13. 7/2/13 Cust said will continue. Third party owned. Stand alone generation. New Construction. Project hold per Int Cust due to net metering laws. Submitted option to related project. withdrawn
WMECO | Deerfield | 6F368-2012 | 01342 | 34.83 | Solar | 22B1 | 2012-09-06 | 2012-11-09 | 46 |  | 46 | 2012-11-12 | 2012-11-19 | 6 | 0 | 6 | [20 empty] | 2012-11-26 |  | not supplied | No | EXP | [6 empty] | 2012-12-14 | 2013-01-03 | 2013-01-03 | on line
WMECO | Russell | 6A357-2012 | 01071 | 125 | Solar | 19J2 | 2012-09-17 | 2012-10-04 | 14 | 2 | 12 | 2012-11-05 | 2012-11-06 | 2 | 0 | 2 | [10 empty] | 2013-03-18 | 2013-09-03 | 117 | 0 | 117 | 2013-09-18 | 2013-10-10 | 17 | 0 | 17 | 2013-12-10 |  | 2012-11-08 | Yes | STD | [9 empty] | Cust decided on own Impact Study instead of joint study, study in progress. Stand alone generation. New construction. First site visit 6/25/13, second site visit to design new service 7/1/13. Sent prices for two options for upgrades/new service 7/24/13-waiting for customer to contact WMECO with their decision on how to move forward with project. conf cal w/ Paradise 8/21/13 customer needs to decide on option. Customer decided upon a primary metered service. Sent out Detailed Study Agreement for signature 9/3/13. Customer sent signed agreement and first check 9/18/13, work order writing underway. Customer is still deciding on option for interconnection service. Sent Draft IA for review 10/18/13. Sent IA for signature. Customer cancelled project.
WMECO | Middlefield | 6B190-2012 | 01243 | 10.965 | Solar | 18C2 | 2012-09-24 | 2012-10-17 | 17 | 0 | 17 | [25 empty] | 2013-01-24 |  | 2012-11-24 | No | EXP | [6 empty] | 2013-06-18 | 2013-06-20 | 2013-06-20 | On Line 6/20/13.
WMECO | Westhampton | 6A363-2012 | 01027 | 12.9 | Solar | 15A3 | 2012-10-01 | 2012-10-01 | 1 |  | 1 | [25 empty] | 2012-11-27 |  | 2012-09-28 | No | EXP | [6 empty] | 2012-12-26 | 2012-12-31 | 2012-12-31 | on line
WMECO | Pittsfield | 6B194-2012 | 01201 | 23.22 | Solar | 30B4 | 2012-10-02 | 2012-11-15 | 32 |  | 32 | 2012-11-16 |  | -29443 | [22 empty] | 2013-04-11 |  | not supplied | No | EXP | [6 empty] | 2013-05-02 | 2013-05-03 | 2013-05-03 | Was third party owned. Single phase inverters on three phase service. On line.
WMECO | Pittsfield | 6B195-2012 | 01201 | 18.06 | Solar | 30B4 | 2012-10-02 | 2012-11-13 | 30 |  | 30 | 2012-11-14 |  | -29441 | [22 empty] | 2013-04-11 |  | not supplied | No | EXP | [6 empty] | 2013-05-02 | 2013-05-03 | 2013-05-03 | Was third party owned. On line.
WMECO | Ludlow | 6S144-2012 | 01056 | 600 | Diesel | 27A4 | 2012-10-19 | 2012-11-15 | 20 | 0 | 20 | 2012-11-27 | 2013-06-21 | 142 | 40 | 102 | [20 empty] | 2013-07-03 |  | 2012-11-12 | No | EXP | [6 empty] | 2013-07-29 | 2013-07-30 | 2013-08-01 | May not export. Closed transition emergency generator. Generator to be interconnected with Big Y service, cust on line 7/30/13. On line 8/7/13.
WMECO | Pittsfield | 6B225-2012 | 01201 | 23.22 | Solar | 30BNW_1 | 2012-10-23 | 2012-11-07 | 12 |  | 12 | 2012-11-08 |  | -29437 | [22 empty] | 2013-03-21 |  | not supplied | No | EXP | [6 empty] | 2013-04-01 | 2013-04-05 | 2013-04-05 | On line. Single phase inverters on three phase service.
WMECO | Pittsfield | 6B234-2012 | 01201 | 19.78 | Solar | 30B7 | 2012-11-16 | 2013-02-21 | 65 | 28 | 37 | 2013-02-22 | 2013-02-22 | 1 | 0 | 1 | [20 empty] | 2013-04-08 |  | 2013-01-21 | No | EXP | [6 empty] | 2014-03-03 | 2014-03-05 | 2014-03-05 | on line
WMECO | Hadley | 6A381-2012 | 01035 | 760 | Solar | 17K5 | 2012-11-21 | 2013-07-30 | 171 | 2 | 169 | 2012-11-30 | 2013-09-10 | 194 | 153 | 41 | [5 empty] | 2013-01-31 | 2013-01-31 | 1 | 0 | 1 | 2013-10-08 | 2013-11-25 | 33 | 2 | 31 | [7 empty] | 2013-12-15 | Yes | STD | [9 empty] | Stand alone generation. New construction. May be third party owned. Scoping meeting held. Project on hold (2/14/13), customer needs to submit option because of inverter change. Purge letter sent to Int Cust 5/20/13. Rcvd new option 5/28/13 from customer. Need to perform initial review of new option. New project size 10 kW larger than original. Design 750 kW or 760 kW. Highest design listed. 8/20/13 call with designer - Customer sending new option. Recieved new option, need to make project smaller due to wetlands. Customer informed WMECO that they would move forward with the 760 kW project on 9/4/13. Waiting for Customer to revise drawings. Customer wants the Impact Study to inform them of the size project that can be installed without significant system upgrades. Waiting for customer to submit correct site plan and one line. Sent Impact Study agreement for signature 9/26/13. Still waiting for revised project information. Received updated info. Received Impact Study agreement and first check. Sent Impact Study Report and Detailed Study Agreement to Customer. Sents Early ISA to Customer for signature and received signed early ISA from Customer 12/19/13. Detailed Study was sent out for signature, Customer has not returned signed agreement. Project cancelled by Interconnecting Customer.
WMECO | Hadley | 6A382-2012 | 01035 | 760 | Solar | 17K5 | 2012-11-21 | 2012-11-29 | 6 | 2 | 4 | 2012-11-30 | 2013-01-31 | 42 | 0 | 42 | [5 empty] | 2013-01-31 | 2013-01-31 | 1 | 0 | 1 | [12 empty] | 2013-12-15 | Yes | STD | [9 empty] | Stand alone generation. New construction. May be third party owned. Scoping meeting held. Project on hold (2/14/13), customer needs to submit option because of inverter change. Purge letter sent to Int Cust 5/20/13. Rcvd new option 5/28/13 from customer. Need to perform initial review of new option. New project size 10 kW larger than original. Design 750 kW or 760 kW. Highest design listed. 8/20/13 call with deigner - Customer sending new option. Customer sent e-mail 8/29/13 that this project has been cancelled.
WMECO | Lanesborough | 6B236-2012 | 01237 | 20.2 | Solar | 15E1 | 2012-11-21 | 2012-12-03 | 8 | 0 | 8 | 2012-11-22 | 2012-11-22 | 0 | 0 | [23 empty] | 2013-02-07 | TBD | EXP | [9 empty] | Cancelled. New application submitted
WMECO | Springfield | 6S149-2012 | 01105 | 5000 | Natural Gas / Diesel | 08C21, 08C23, 21S3 | 2012-11-26 |  |  | 208 | [28 empty] | 2012-10-15 | TBD | STD | [9 empty] | cancelled
WMECO | Pittsfield | 6B238-2012 | 01201 | 45.795 | Solar | 30B4 | 2012-11-27 | 2012-12-03 | 5 |  | 5 | 2012-12-04 | 2013-06-27 | 141 | 46 | 95 | [20 empty] | 2013-08-19 |  | 2012-11-30 | TBD | EXP | [6 empty] | 2013-09-29 | 2013-09-30 | 2013-09-30 | Customer is on line 9/30/13.
WMECO | Southampton | 6A384-2012 | 01073 | 600 | Diesel | 15A1 | 2012-12-04 | 2012-12-07 | 4 | 0 | 4 | 2013-06-10 | 2013-06-21 | 9 | 8 | 1 | [20 empty] | 2013-07-03 |  | 2012-12-31 | TBD | EXP | [6 empty] | 2013-07-29 | 2013-07-30 | 2013-07-30 | Will not export. Closed transition emergency generator. Generator to be interconnected with Big Y service, Customer on line, 7/30/13.
WMECO | Pittsfield | 6B240-2012 | 01201 | 11.4 | Solar | 30B3 | 2012-12-05 | 2013-03-13 | 67 | 33 | 34 | 2013-03-14 | 2013-04-08 | 18 | 0 | 18 | [20 empty] | 2013-04-09 |  | 2013-01-21 | TBD | EXP | [9 empty] | Cancelled. New application submitted
WMECO | Montague | 6F410-2012 | 01351 | 11.4 | Solar | 21C7 | 2012-12-13 | 2013-02-12 | 41 |  | 41 | 2013-02-12 | 2013-02-12 | 1 | 0 | 1 | [20 empty] | 2013-03-19 |  | 2013-02-01 | No | EXP | [6 empty] | 2013-04-30 | 2013-05-03 | 2013-05-03 | on line
WMECO | Amherst | 6A385-2012 | 01002 | 19.35 | Solar | 17K2 | 2012-12-17 | 2013-02-05 | 34 |  | 34 | 2013-02-05 | 2013-02-12 | 6 | 0 | 6 | [20 empty] | 2013-02-14 |  | not supplied | No | EXP | [6 empty] | 2013-03-29 | 2013-04-01 | 2013-04-01 | Cust made change to service. On line.
WMECO | Springfield | 6S154-2012 | 01111 | 5000 | Diesel | 5J14 | 2012-12-17 | 2013-04-19 | 85 | 0 | 85 | 2013-05-13 | 2013-10-28 | 116 | 45 | 71 | [5 empty] | 2013-04-22 | 2013-04-22 | 1 | 0 | 1 | 2013-10-28 | 2013-11-13 | 12 | 0 | 12 | [5 empty] | 2014-01-09 |  | not supplied | TBD | STD | [6 empty] | 2014-11-13 | 2014-11-30 | 2014-12-01 | Closed transition generator. Will export 250 kW for 10 seconds via reverse power relay. Initial review done. Waiting for cutomer to send revised drawings. Protection review done, need revised info from Customer. Revised info sent is O.K. Sent Draft IA to Customer for review. Sent revised Draft IA for review 11/18/13. Exhibit G for signature sent to Customer 1/9/14. Waiting on Customer for relay test results and final doucumentation to peform a Witness Test. Witness Test originally scheduled for 11/23/14 but Customer rescheduled for 11/30/14. Witness Test originally scheduled for 11/23/14 but Customer rescheduled for 11/30/14. Witness Test performed. Generators on line.
WMECO | Amherst | 6A387-2012 | 01059 | 3000 | Solar | 18G7 | 2012-12-26 |  |  | 148 | [28 empty] | 2013-07-01 | Yes | STD | [9 empty] | Stand alone generation. New construction. Third party owned. Held Scoping meeting. Interconnecint Customer may submit options. Need updated drawings and options to continue. Withdrawn
WMECO | Richmond | 6B254-2013 | 01254 | 11.2 | Solar | 30B7 | 2013-01-08 | 2013-02-20 | 30 | 2 | 28 | 2013-02-21 | 2013-03-11 | 13 | 0 | 13 | [20 empty] | 2013-03-14 |  | 2013-03-13 | No | EXP | [9 empty] | Cancelled. New Simplified application submitted.
WMECO | West Springfield | 6S155-2013 | 01089 | 16.985 | Solar | 21N9 | 2013-01-10 | 2013-03-06 | 38 | 1 | 37 | 2013-03-07 | 2013-03-07 | 1 | 0 | 1 | [20 empty] | 2013-04-01 |  | 2013-01-01 | No | EXP | [6 empty] | 2013-05-08 | 2013-05-09 | 2013-05-09 | on line
WMECO | Pittsfield | 6B257-2013 | 01201 | 21.93 | Solar | 30B4 | 2013-01-16 | 2013-01-23 | 5 | 0 | 5 | 2013-01-24 | 2013-01-24 | 1 | 0 | 1 | [20 empty] | 2013-07-08 |  | not supplied | TBD | EXP | [6 empty] | 2013-10-09 | 2013-10-10 | 2013-10-10 | on line 10/10/13.
WMECO | Bernardston | 6F432-2013 | 01337 | 31.39 | Solar | 21B8 | 2013-02-01 | 2013-03-18 | 31 | 4 | 27 | 2013-03-19 | 2013-04-03 | 12 | 5 | 7 | [20 empty] | 2013-04-08 |  | 2013-05-01 | Yes | EXP | [6 empty] | 2013-05-31 | 2013-06-05 | 2013-06-05 | on line
WMECO | Hadley | 6A405-2013 | 01035 | 833 | Solar | 18G4 | 2013-02-11 | 2013-06-19 | 89 | 26 | 63 | 2013-07-09 | 2013-07-12 | 4 | 0 | 4 | [5 empty] | 2013-07-12 | 2013-07-12 | 1 | 0 | 1 | 2013-10-07 | 2013-11-25 | 34 | 0 | 34 | [5 empty] | 2013-12-23 |  | 2013-12-15 | Yes | STD | [9 empty] | Stand alone generation. New construction. May be third party owned. Will not be third party owned per Customer. Waiting for Customer to revise drawings. Customer wants the Impact Study to inform them of the size project that can be installed without significant system upgrades. Waiting for Customer to supply revised info. Interconnecting Customer wants Impact Study to study 833, 500 and 333 kW projects or other size that will not require significant upgrades for other than the interconnection service. If Impact Study determines project size other than the original submitted inverters, the Interconneting Customer will need to submit new application package and fee and the DG process starts over. Sent Joint Impact Study to Interconnecting Customer 10/2/13 for 6A405-2013 & 6A415-2013 total cost $33,000. Received Impact Study agreement and first check. Sent Impact Study Report and Detailed Study Agreement to Customer. Sent Early ISA to Customer for signature 12/23/13, recieved signed Early ISA from Customer 12/28/13. Detailed Study agreement was sent out for signature, Customer has not returned signed agreement. Customer wanted to interconnect this and the 6A415-2013 project at one interconnection point, WMECO sent them an estimate for this design, the Customer has not decided whether to go with one interconnection point or to only build the 6A415-2013 project. Customer had an extension for the Detailed Syudy phase. Extension expired, WMECO DG sent e-mail to Customer that this project is withdrawn for the interconnection queue.
WMECO | Hadley | 6A408-2013 | 01035 | 2730 | Solar | 17K1 | 2013-02-14 | 2013-03-29 | 31 | 1 | 30 | 2013-04-01 |  | -29534 | 93 | [23 empty] | 2013-10-13 | Yes | STD | [9 empty] | Sent email to schedule Scoping Mtg. Stand alone generation. New construction. May be third party owned. Held Scoping meeting. Need decsision from Interconnecting Customer on how they will move forward. Cancelled
WMECO | Sunderland | 6A411-2013 | 01375 | 300 | Solar | 18G3 | 2013-02-27 | 2013-04-03 | 26 | 18 | 8 | 2013-04-04 | 2013-09-11 | 110 | 84 | 26 | 2013-09-20 | 2013-10-11 | 16 | 0 | 16 | [15 empty] | 2013-12-05 |  | 2013-06-01 | Yes | EXP | [9 empty] | New option (option 2) submitted. Received incremental application fee 8/13/13. Supplemental Review completed. Agreement's out for signature. Interconnecting Customer in liquidation. On hold while Customer seeks new developer. Notice sent to all parties, no response. Application withdrawn 6/27/14.
WMECO | Sunderland | 6A412-2013 | 01375 | 349.5 | Solar | 18G3 | 2013-02-27 | 2013-04-01 | 24 | 16 | 8 | 2013-04-02 | 2013-09-11 | 112 | 85 | 27 | 2013-10-15 | 2013-11-12 | 20 | 0 | 20 | [15 empty] | 2013-12-05 |  | 2013-06-01 | Yes | STD | [9 empty] | New option (option 2) submitted for smaller size. Application was on hold due to delay in application 6A411-2013. Applications are on the same circuit. Supplemental Review completed. Agreement's out for signature. Interconnecting Customer in liquidation. On hold while Customer seeks new developer. Notice sent to all parties, no response. Application withdrawn 6/27/14.
WMECO | Pittsfield | 6B265-2013 | 01201 | 9.89 | Solar | 30BNW_1 | 2013-03-14 | 2013-03-28 | 11 | 0 | 11 | 2013-03-29 | 2013-07-02 | 65 | 8 | 57 | [20 empty] | 2013-08-01 |  | 2013-05-09 | TBD | STD | [8 empty] | 2013-10-25 | Received Comletion Documents. Need updated Witness Test Procedure to schedule Witness Test.
WMECO | Hadley | 6A415-2013 | 01035 | 833 | Solar | 18G4 | 2013-03-18 | 2013-06-18 | 64 | 21 | 43 | 2013-07-11 | 2013-07-12 | 2 | 0 | 2 | [5 empty] | 2013-07-12 | 2013-07-12 | 1 | 0 | 1 | 2013-10-07 | 2013-11-25 | 34 | 0 | 34 | 2014-03-04 | 2014-04-14 | 29 | 3 | 26 | 2014-05-07 |  | 2013-10-15 | Yes | STD | 2014-09-15 | 2014-09-15 |  | -29896 |  |  | 2014-10-21 | 2014-10-30 | 2014-10-30 | May be third party owned. Will not be third party owned per Customer. Waiting for Customer to revise drawings. Customer wants the Impact Study to inform them of the size project that can be installed without significant system upgrades.Waiting for Customer to supply revised info. Interconnecting Customer wants Impact Study to study 833, 500 and 333 kW projects or other size that will not require significant upgrades for other than the interconnection service. If Impact Study determines project size other than the original submitted inverters, the Interconneting Customer will need to submit new application package and fee and the DG process starts over. Sent Joint Impact Study to Interconnecting Customer 10/2/13 for 6A405-2013 & 6A415-2013 total cost $33,000. Received Impact Study agreement and first check. Sent Impact Study Report and Detailed Study Agreement to Customer. Sent Early ISA to Customer for signature 12/23/13, recieved signed Early ISA from Customer 12/28/13. Detailed Study agreement was sent out for signature, Customer has not returned signed agreement. Customer wanted to interconnect this and the 6A405-2013 project at one interconnection point, WMECO sent them an estimate for this design, the Customer has not decided whether to go with one interconnection point or to only build this 6A415-2013 project. The Customer has signed the Detailed Study Agreement and sent in all monies to write work orders and design DTT for the Huntington Rd project only as originally submitted. Work orders have been written, need to give Customer Exhibit G with plus/minus 10%. Customer changed the name from BueWave Capital to BWC Origination Huntington Road, LLC. Sent out Draft IA for review, Customer sent it back with name change. Talked with Customer they are not going to change the name. Need revised insurance certificate with BWC Origination name. Sent out IA for signature. Revised insurance certificate received. Verizon scheduled to set poles. WMECO technician has to go out and restake pole locates for interconnection service because they were knocked down. Construction of interconnection service has started. Interconnection service finished, transfer trip FDDA lines need to be installed by Verizon, Customer did not order the FDDA lines until early October, FDDA lines installed, transfer trip commissioned, Witness Test scheduled. Customer is on line.
WMECO | West Springfield | 6S165-2013 | 01089 | 79.8 | Solar | 21N5 | 2013-03-18 | 2013-04-25 | 28 | 22 | 6 | 2013-04-26 |  | -29552 | 38 | [21 empty] | 2013-08-06 |  | 2013-04-25 | TBD | EXP | [6 empty] | 2013-11-13 | 2013-12-10 | 2013-12-10 | on line
WMECO | Hadley | 6A418-2013 | 01035 | 57.405 | Solar | 17K5 | 2013-04-09 | 2013-06-12 | 45 | 37 | 8 | 2013-06-13 | 2013-08-06 | 37 | 28 | 9 | [20 empty] | 2013-08-09 |  | 2013-07-22 | TBD | EXP | [6 empty] | 2013-11-13 | 2013-12-12 | 2013-12-31 | IA on file. Completed successful Witness Test. Changes were made to the design. Need updated documents before Approval to Operate.
WMECO | Greenfield | 6F447-2013 | 01301 | 300 | Solar | 21C1 | 2013-04-09 | 2013-05-07 | 20 |  | 20 | 2013-05-08 | 2013-05-23 | 12 |  | 12 | 2013-06-03 | 2013-06-26 | 17 | 0 | 17 | [15 empty] | 2013-07-15 |  | not supplied | TBD | EXP | [9 empty] | App complete. Scoping Mtg. held. Supplemental Review complete. Received Signed IA. Need Completion Documents. **** I.C. cancelled *****
WMECO | Amherst | 6A419-2013 | 01002 | 100 | Solar | 18G4 | 2013-04-16 | 2013-04-30 | 11 |  | 11 | 2013-05-01 | 2013-06-06 | 26 | 2 | 24 | [20 empty] | 2013-06-06 |  | 2013-05-01 | TBD | EXP | [6 empty] | 2013-10-15 | 2013-10-22 | 2013-10-22 | Scheduled witness Test on 10/15/13. Performed Witness Test on 10/18/13, the inverter failed on start up. Needs to schedule an addtional Witness Test. Witness test dates = 10/18/2013 & 10/22/2013
WMECO | Otis | 6B269-2013 | 01253 | 1800 | Wind | 19J6 | 2013-04-19 | 2013-05-02 | 10 | 0 | 10 | [10 empty] | 2013-05-03 | 2014-02-18 | 197 | 166 | 31 | 2014-04-10 | 2014-07-01 | 56 | 3 | 53 | [7 empty] | 2013-11-13 | Yes | COMP | [9 empty] | Scoping Mtg held. Need info from Interconnecting Customer. Off hold. Additional option information received. Impact Study Agreement out for siganture 3/5. Signed agreement and payment received 4/9. Impact Study report sent. Detaled Study agreement sent. Interconnecting Customer inidiated ADR. Clock is stopped unitl ADR process completed. cancelled
WMECO | Peru | 6B277-2013 | 01235 | 16500 | Wind | 18C2 | 2013-05-06 | 2013-05-23 | 14 | 2 | 12 | [10 empty] | 2013-05-24 | 2013-09-06 | 72 | 47 | 25 |  |  |  | 29 | [8 empty] | not supplied | Yes | COMP | [9 empty] | Application complete. Held Scoping Mtg. Interconnecting Customer submitted additional options. Impact Study Agreemet out for Signature. Interconnecting Customer timelines expired on execution of Impact Study Agrement. Application withdrawn per the Tariff procedure.
WMECO | Lanesborough | 6B280-2013 | 01237 | 20.21 | Solar | 15E1 | 2013-05-13 | 2013-11-12 | 126 | 120 | 6 | 2013-10-29 | 2013-10-29 | 1 | 0 | 1 | [20 empty] | 2013-11-12 |  | 2013-07-10 | TBD | EXP | [6 empty] | 2014-03-28 | 2014-04-01 | 2014-04-01 | new application. Have not heard from Customer as of 8/21/13. Waiting for service upgrades to be done. Devloper called 9/17/13 project is moving forward, Customer needs to sign lease for solar facility. Sent Drat Exhibit G & H. Rcvd stamped one line. Rcvd initial payment for system modifications. Sent Exhibit G & H for signature. Received signed Exhibit G. Rcvd Exhibit H. The initial check for system modifications was returned to Int Customer (outdated check becuase of project delay). On hold in November. Rcvd new check for system modifications in February. System modification completed, completion docs recvd, Witness Test performed, On line.
WMECO | Amherst | 6A449-2013 | 01002 | 19.99 | Solar | 17K7 | 2013-06-26 | 2013-07-03 | 6 | 0 | 6 | 2013-07-05 | 2013-09-05 | 44 | 21 | 23 | [20 empty] | 2013-10-07 |  | 2013-09-01 | TBD | EXP | [6 empty] | 2013-10-28 | 2013-10-29 | 2013-11-18 | Held site visit. WMECO sent customer estimate for construction required for option 2 (customer has two options, 19.99 kW and 21.395 kW). As of 9/5/2013 Interconnecting Customer is moving forward with 19.99 kW option. Received IA. System Online
WMECO | Southwick | 6S195-2013 | 01077 | 40 | Hydro | 29A5 | 2013-07-09 | 2013-07-30 | 16 | 8 | 8 | 2013-07-31 |  | -29617 | 17 | [23 empty] | 2013-11-01 |  | EXP | [9 empty] | Application complete. Held Scoping Meeting. Interconnecting Customer may cancel application and resubmit new design. Interconnecting Customer requested an extension. Cancelled
WMECO | Conway | 6F473-2013 | 01341 | 19.99 | Solar | 38A1 | 2013-07-15 | 2013-07-24 | 8 | 0 | 8 | 2013-07-25 | 2013-09-19 | 40 | 9 | 31 | 2013-09-26 | 2013-11-04 | 27 | 0 | 27 | [15 empty] | 2013-11-15 |  | 2013-08-01 |  | EXP | [6 empty] | 2013-12-10 | 2013-12-13 | 2013-12-20 | Application Complete. Supplemental Review Complete. Construction Complete. Online.
WMECO | Southwick | 6S200-2013 | 01077 | 3340 | Solar | 29A1 | 2013-07-18 | 2013-08-07 | 15 | 9 | 6 | [10 empty] | 2013-08-08 | 2013-10-15 | 47 | 27 | 20 | 2013-12-13 | 2014-05-01 | 94 | 0 | 94 | 2014-05-05 | 2014-11-05 | 128 | 12 | 116 | 2014-05-01 |  | 2014-08-01 |  | STD |  | 2015-03-09 | 2015-03-20 | 10 |  | 10 | 2015-03-09 | 2015-03-30 | 2015-03-30 | App not complete. Need Information from Interconnecting Customer. Conf call with Customer 9/24/13, Customer needs to decide whether to move forward with existing aproject or cancel and resubmit different size project. Customer informed WMECO on 9/26/13 that the project size will be decreased to 3340 kW (two 1670 kW inverters). They will send send early next week as an option 1 to the original project. Customer sent Option1 app package for 3340 kW on 10/2/13. Sent Impact Study Agreement to Customer. Impact Study complete, Iso notification complete. Project was sold to another developer, names were changed on agreements. Developer sent in all system modification monies, Construction will start January 2015. Insurance cert received, sent revised attachment 3 for system upgrades due to this project moving forward prior to the Customer in the interconnection queue, recevied initialed attachment 3 and check for addional modifications. Project is on hold due to a prject ahead of this ion the DG queue. Substation construction scheduled for February, line constructio scheudled for March, Witness Test scheduled for end of March. Revised application and schedule Z submitted with the Town of West Springfield info, project is now third party owned. Electric account was established. Received completion docs. Some revisions required, Received revised Completion docs, Completion docs reviewed - O.K. Project requires Land Owner agreement. Interconnection service and substation work and transfer trip completed and comissioned. Rcvd signed Exhbit H and landowner agreement. Witness Test performed, Project on line.
WMECO | Richmond | 6B301-2013 | 01254 | 18 | Solar | 30B7 | 2013-08-28 | 2013-10-07 | 28 | 20 | 8 | 2013-10-08 | 2013-11-20 | 30 | 19 | 11 | [20 empty] | 2013-11-20 |  | 2013-09-01 |  | EXP | [6 empty] | 2013-12-13 | 2013-12-18 | 2013-12-31 | on line
WMECO | Springfield | 6S208-2013 | 01129 | 333 | Solar | 20A35 | 2013-08-29 | 2013-09-20 | 16 | 12 | 4 | 2013-10-31 | 2013-10-31 | 1 | 0 | 1 | 2013-12-02 | 2014-01-06 | 24 | 0 | 24 | [15 empty] | 2014-02-06 |  | 2014-06-30 | TBD | EXP | [9 empty] | Application not complete. Information requested. Customer sent revised application for third party on 11/20/13. Suplemental review finished. Drfat Exhibit G & H sent out for review. Sent out Exhibit G & H for signature. Received signed Exhibit G & H. Solar facility will not be built until 2nd or 3rd quarter 2014 per Interconnecting Customer. Customer wants to change inverters, sent them an e-mail informing them that they have a signed agreement and cannot change inverters at this time. They will need to submit a new application with fee and new technical information. cancelled
WMECO | Pittsfield | 6B316-2013 | 01201 | 600 | Diesel | 30B4 | 2013-10-01 | 2013-11-05 | 25 | 13 | 12 | 2013-11-05 | 2014-01-13 | 46 | 45 | 1 | 2014-01-17 | 2014-04-11 | 58 | 44 | 14 | [15 empty] | 2014-05-20 |  | 2013-10-24 |  | EXP | [8 empty] | 2018-04-25 | App complete, supplemental review started, waiting for revised info on watch dog timer, timer is integral part of transfer switch, Protection informed us that timer needs to be in addition to the transfer swtch and cannot be integral. Customer sent revised drawing with additional discreet watch dog timer. Protection sent final comments. Drawings and design O.K. Sent Draft IA to Customer for review. Sent e-mail 2nd request to review Draft Exhibit G. Recvd comments, made changes, sent Executable Exhibit G to Customer. Rceived signed Exhibit G from Customer. Waiting to schedule Witness Test.
WMECO | Southwick | 6S217-2013 | 01077 | 40 | Hydro | 29A2 | 2013-10-21 | 2013-11-05 | 12 | 1 | 11 | 2013-11-06 | 2013-12-04 | 19 | 2 | 17 | 2013-12-09 | 2014-01-30 | 36 | 20 | 16 | [15 empty] | 2014-02-06 |  | 2014-03-28 |  | EXP | [6 empty] | 2015-11-16 | 2015-11-30 | 2015-11-30 | Supplemental Review Comnplete. Executed IA received. Received relay test results. Ned Witness Test procedure and to schedule Witness Test with I.C.
WMECO | Greenfield | 6F508-2013 | 01301 | 29.985 | Solar | 22B2 | 2013-10-25 | 2013-11-05 | 8 | 0 | 8 | 2013-11-05 | 2013-11-05 | 1 | 0 | 1 | [20 empty] | 2014-01-03 |  | ASAP |  | EXP | [6 empty] | 2014-04-14 | 2014-04-15 | 2014-04-15 | Sent app complete info, initial review done, sent DRAFT Exhibit G for signature, ordered Net meter. Exhibig G received. Received completion docs, scheduled DG meter set. Confirmed meter set.Scheduled Witness Test. Witness test successful, Customer on line,
WMECO | Hadley | 6A496-2013 | 01305 | 1950 | Solar | 17K1 | 2013-10-28 | 2014-01-17 | 56 | 10 | 46 | [10 empty] | 2014-01-21 | 2014-03-10 | 34 | 21 | 13 | 2014-04-09 | 2014-06-30 | 56 | 0 | 56 | 2014-12-09 | 2015-05-27 | 121 | 97 | 24 | 2015-07-21 |  |  |  | STD | [7 empty] | 2016-10-20 | 2016-10-25 | App Complete. Scoping Meeting Held. Need Impact Study Agreement. Impact Study Agreement out for signature on 3/12. Executed Agreement received 3/12, payment received 4/8. In Impact Study. Impact Study results meeting held. I.C. reviewed alternate DTT scheme. I.C. requested Detailed Study payment plan. Received signed Exhibit F and payment. Site visit held. Interconnecting Customer reviewed and approved Exhibit G language. On hold for ISO RC. Project was not included on 4/21 meeting agenda despite being submitted correclty before the deadline for that meeting. ISO review complete. Need clarification on ABB/Power One inverters.
WMECO | Greenfield | 6F513-2013 | 01301 | 16 | Solar | 22B7 | 2013-10-29 | 2013-11-05 | 6 | 3 | 3 | 2013-11-07 | 2013-11-12 | 3 | 0 | 3 | [20 empty] | 2013-11-18 |  | 2013-11-10 |  | EXP | [6 empty] | 2013-12-18 | 2013-12-23 | 2014-01-17 | Sent app complete info, initial review done, sent DRAFT Exhibits G & H, ordered Net meter. Witness Test passed, Need Mass ACA Reservied. Recevd Mass ACA Reserved Approval to operate sent to Customer. On Line.
WMECO | Dalton | 6B345-2013 | 01226 | 1650 | Solar | 19A2 or 19A3 | 2013-12-03 | 2014-02-28 | 60 | 57 | 3 | [10 empty] | 2014-03-03 | 2014-04-10 | 28 | 22 | 6 | 2014-05-12 |  | -29810 | 11 | [10 empty] | STD | [9 empty] | Options received. Application Complete. Scoping meeting held. In Impact Study. "Preliminary" report shared (for the purpose of potential alternate DTT solution). Call held with I.C. Cancelled by I.C.
WMECO | Pittsfield | 6B359-2014 | 01201 | 16.5 | Solar | 30B7 | 2014-01-06 | 2014-02-12 | 27 | 15 | 12 | 2014-02-12 | 2014-02-12 | 1 | 0 | 1 | [20 empty] | 2014-02-18 |  | 2014-02-04 |  | EXP | [6 empty] | 2014-04-17 | 2014-04-18 | 2014-04-18 | need additional info from Customer. Rcvd additional info. Sent out Draft Exhibit G for review. Sent out Exhibit G for signature. Rcvd comp docs, need additional info. Rcvd additional info. Ordered meter set. Scheduled Witness Test. On line.
WMECO | Dalton | 6B364-2014 | 01226 | 1250 | Solar | 19A2 or 19A3 | 2014-01-14 | 2014-02-28 | 32 | 16 | 16 | [10 empty] | 2014-03-03 | 2014-04-10 | 28 | 22 | 6 | [14 empty] | STD | [9 empty] | Options received. Application Complete. Scoping meeting held. Impact Study agreement and payment received. Queued behind 6B345-2013. Cancelled by I.C.
WMECO | West Springfield | 6S240-2014 | 01089 | 1950 | Solar | 16C12 | 2014-01-17 | 2014-03-12 | 37 | 22 | 15 | [10 empty] | 2014-03-13 | 2014-06-12 | 63 | 56 | 7 | 2014-07-18 | 2014-12-05 | 97 | 90 | 7 | 2015-04-21 | 2015-11-20 | 154 | 70 | 84 | 2015-11-30 |  | 2014-10-01 |  | COMP | [6 empty] | 2017-03-14 | 2017-03-22 | 2017-03-30 | Application Complete. Screening email sent. In Impact Study. Impact Study time frame was extended to 100 business days per mutual agreement. Received Detailed Study Agreement. Received payment. I.C. requested early ISA. In D.S. but on hold. Need updated drawings from I.C. Need ISO RC. Site visit held. Need to straigten out issues with property lines.
WMECO | Springfield | 6S244-2014 | 01111 | 4000 | Diesel | 5J14 | 2014-02-04 | 2014-02-24 | 14 | 13 | 1 | 2014-02-25 | 2014-03-19 | 16 | 0 | 16 | 2014-04-22 | 2014-05-12 | 15 | 10 | 5 | [15 empty] | 2014-07-02 |  | 2014-06-01 |  | EXP | [6 empty] | 2014-11-13 | 2014-11-30 | 2014-12-01 | Application complete, Initial review done. Supplemental review started. Need revised one line with neutral grnding resistors. Sent protection comments to Customer, need revised 32R setting, received revised info, sent to Protection to review. Sent out Draft IA for comment. Sent out IA for signature. Received signed agreement. Need insurance cert to include these two generators, sent e-mail to Customer. Waiting on Customer for relay test results and final doucumentation to peform a Witness Test. Witness Test originally scheduled for 11/23/14 but Customer rescheduled for 11/30/14. Witness Test performed. Generaotrs on line.
WMECO | Lee | 6B369-2014 | 01238 | 15.265 | Solar | 16B5 | 2014-02-05 | 2014-02-19 | 10 | 6 | 4 | 2014-02-20 |  | -29755 | 25 | [23 empty] | 2014-03-28 |  | EXP | [9 empty] | Application Complete. Screening email sent 2/25. WMECO needs information. Customer cancelled project.
WMECO | Lee | 6B370-2014 | 01238 | 17.325 | Solar | 16B5 | 2014-02-05 | 2014-02-25 | 14 | 10 | 4 | 2014-02-26 | 2014-06-23 | 80 | 71 | 9 | [20 empty] | 2014-08-05 |  | 2014-01-24 |  | EXP | [6 empty] | 2016-02-10 | 2016-02-16 | 2016-02-16 | Application Complete. Screening email sent 3/12. WMECO needs information. Construction required. Site visit held and estimate provided. IA fully executed.
WMECO | Conway | 6F542-2014 | 01341 | 16.125 | Solar | 38A1 | 2014-02-24 | 2014-04-10 | 33 | 25 | 8 | 2014-04-11 | 2014-04-15 | 3 | 1 | 2 | [20 empty] | 2014-04-15 |  | 2014-03-21 |  | EXP | [6 empty] | 2014-04-22 | 2014-04-24 | 2014-04-24 | on line
WMECO | Amherst | 6A540-2014 | 01002 | 24 | Solar | 17K6 | 2014-02-28 | 2014-03-12 | 9 | 8 | 1 | 2014-03-13 | 2014-05-01 | 34 | 14 | 20 | [20 empty] | 2014-05-07 |  | 2014-04-01 |  | EXP | [6 empty] | 2014-05-30 | 2014-06-04 | 2014-06-04 | Existing system on property moved to PPS comensation. Online
WMECO | Lee | 6B383-2014 | 01238 | 19.8 | Solar | 16B5 | 2014-03-03 | 2014-03-19 | 12 | 7 | 5 | 2014-03-20 | 2014-05-20 | 43 | 6 | 37 | [20 empty] | 2014-06-10 |  | 2014-04-15 |  | EXP | [6 empty] | 2014-09-12 | 2014-09-15 | 2014-09-30 | On line 9/30/14
WMECO | West Hatfield | 6A543-2014 | 01088 | 500 | Solar | 18G5 | 2014-03-06 | [31 empty] | 2014-06-01 |  | EXP | [9 empty] | withdrawn
WMECO | Longmeadow | 6S254-2014 | 01106 | 12 | Solar | 22H12 | 2014-03-11 | [31 empty] | 2014-05-30 |  | EXP | [9 empty] | Project cancelled by applicant.
WMECO | Whately | 6A564-2014 | 01093 | 22.8 | Solar | 18G6 | 2014-04-14 | 2014-04-23 | 7 | 0 | 7 | 2014-05-05 | 2014-05-21 | 13 | 7 | 6 | [20 empty] | 2014-05-21 |  | 2014-05-01 |  | EXP | [6 empty] | 2014-08-05 | 2014-08-06 | 2014-08-06 | Reveiwed project, needed ac solar disconnect location reviewed by meter supervisor. Location O.K., Sent out Draft Exhibit G for review. Need revised one line with text for combiner panel "only generation circutis" recevied revised one line. Need Int Customer name and address on 1-line, received revised one line, Sent out Exhibit G for siganture. Received signed Exhibit G from Customer. Witness test performed, Customer on line.
WMECO | Springfield | 6S312-2014 | 01119 | 336 | Solar | 20A33 | 2014-06-11 | 2014-07-03 | 16 | 6 | 10 | 2014-07-07 | 2015-01-20 | 137 | 134 | 3 | 2015-01-21 | 2015-02-11 | 16 | 0 | 16 | [15 empty] | 2015-03-27 |  | 2014-11-17 |  | EXP | [9 empty] | Application is complete, started Initial Review, sent out comments to Custoemr, One line drawing needs revision before the Supplemental Review can be performed. It is difficult to reach the Custoerm by phone in Florida as the phone lines are frequently busy and I cannot get through. waiting for stamped revised one line. Sent Supplemental Review for signature, Int Cust will send stamped drawing ASAP. WMECO rcvd siganed agreement and check, Interconnecting Customer requested an extension to get WMECO information. WMECO granted the extension as part of the initial review stage, expires 1/20/15. Supplemental Review under way. Supplemenatl Review Report sent to Interconnecitng Customer and Customer. IStarted IAs, info required, Rvcd partial info, Rcvd completed info, IAs sent out for signature. Withdrawn after no contact from applicants and none of the contact information is valid. withdrawn
WMECO | Pittsfield | 6B409-2014 | 01201 | 266 | Solar | 15E2 | 2014-06-23 | 2014-07-22 | 21 | 18 | 3 | 2014-07-23 | 2015-05-06 | 201 | 192 | 9 | 2015-05-21 | 2015-06-17 | 20 | 0 | 20 | [15 empty] | 2015-08-14 |  | 2014-08-25 |  | EXP | [6 empty] | 2015-12-17 | 2016-04-21 | 2016-04-21 | app not complete need inverter cut sheet, rcvd cut sheet, Application complete, started initial review, sent out comments info required, held scoping meeting 7/30 sent out minutes, drawings need to be revised, waiting for revised application that includes the information of the two historical diesel generators and the one line to include the relay settings of the two diesel generators. Sent the Supplemental Review agreements to the Customer, have not received the signed agreement nor check. Still have not rcvd application with diesel generator information nor 1-line with diesel generator settings. Sent e-mail that they have 10 days to send info. Rcvd revised app and 1-line with diesel gen info. Need to review. started Supplemental Review, info required from Customer, rcvd info finsihed Supplemental review, sent results to Customer. Watch dog timers required for each existing diesel generator. Conf call with Customer to explain existing gen issues. Revised drawing showing watch Dog timers required for IA to be sent out. W D Timers required to be installed prior to sched Witness Test. Witness Test performed for solar facility, Solar Customer is on line. Customer required to install Watch Dog Time for the two closed transition diesel generators. Witness test scheduled for Watch Dog timer. Witness test failed. A second Witness test is scheduled for the Watch Dog timer, Witness test successful. Diesel generators are on line.
WMECO | Springfield | 6S334-2014 | 01129 | 278.4 | Solar | 20A35 | 2014-06-23 | [31 empty] | 2014-10-31 |  | EXP | [9 empty] | Project cancelled by customer.
WMECO | Windsor | 6B413-2014 | 01270 | 24 | Solar | 18C1 | 2014-07-10 | 2014-07-22 | 9 | 2 | 7 | 2014-08-21 | 2014-09-03 | 9 | 8 | 1 | [20 empty] | 2014-09-05 |  | 2014-11-01 |  | EXP | [6 empty] | 2014-12-09 | 2014-12-16 | 2014-12-16 | app not complete, need app fee, app fee received, app complete, initial review started need revised one line & site plan. Received revised info. Approval to install. Received completion docs, need inspaector requirement in WR. Inspector requirement completed. Scheduled meter set. Witness Test scheduled, Witness Test performed, successful, Customer is on line.
WMECO | Russell | 6A681-2014 | 01071 | 49 | Solar | 19J2 | 2014-07-16 | 2014-09-05 | 37 | 30 | 7 | 2014-09-12 | 2014-12-03 | 56 | 50 | 6 | [20 empty] | 2014-12-16 |  | 2014-09-26 |  | EXP | [6 empty] | 2015-10-02 | 2015-10-06 | 2015-10-06 | Application complete, Initial review done, comments sent to Customer, project requires system modifications, Customer recvd WR #, technician needs to make site visit. Technician is writing up work order for system upgrades. Technician finished writing system mod work order. Exhibit G to be written and sent to Customer. Project on Customer Hold due to Customer land permitting issues. WMECO has notification that the Customer would like to procedd with the 49 kW project, sent DRAFT Exhibit G to Customer for review. Sent Exhibit G for signature. Still need system modification upgrade monies. Rcvd system modification monies, scheduled modifications. Modifications completed. Waiting for system to be installed. rcvd some comp docs, need inverter setting sheets, rvcd setting sheets, scheduled Wit Test, performed wit test, costomer on line.
WMECO | Hadley | 6A682-2014 | 01035 | 24.98 | Solar | 18G4 | 2014-07-16 | 2014-08-26 | 30 | 26 | 4 | 2014-08-27 | 2014-09-04 | 6 | 2 | 4 | [20 empty] | 2014-09-04 |  | not supplied |  | EXP | [6 empty] | 2014-12-22 | 2014-12-22 | 2014-12-22 | app complete, initial review, site address incorrect, insytaller send town assessor records, Customer Care changed site address in WMECO records, new one line requested/received, sent out IA for signature, rcvd signed IA, rcvd wit test docs, schd wit test, Customer on line.
WMECO | Greenfield | 6F594-2014 | 01301 | 600 | Diesel | 22B7 | 2014-07-24 | 2014-08-26 | 24 | 23 | 1 | 2014-08-26 | 2014-12-03 | 68 | 54 | 14 | 2014-12-03 | 2014-12-29 | 18 | 0 | 18 | [15 empty] | 2015-01-07 |  | not supplied |  | EXP | [8 empty] | 2018-04-25 | Application not complete, Application Complete Checklist is required. Application complete, Supplemental Review required, Supplemental review started, Supplemental Review complete, need to send Exhibit G, sent out Exhibit G for signature. Rcvd signed Exhibit G and insurance cert.
WMECO | Springfield | 6S386-2014 | 01103 | 42 | Solar | 8CNW_1 | 2014-08-04 | 2014-08-25 | 16 | 15 | 1 | 2014-08-26 | 2014-09-29 | 24 | 22 | 2 |  |  |  | 17 | [18 empty] | 2014-08-01 |  | STD | [9 empty] | Application not complete, Application Complete Checklist is required, recvd app complete checklist, initial review sent ot Customer, waiting for required info., Customer is located on the area network. Cancelled
WMECO | West Springfield | 6S468-2014 | 01089 | 200 | Solar | 16C12 | 2014-08-25 |  |  | 165 | [28 empty] | 2014-08-01 |  | EXP | [9 empty] | The Customer names on the application do not match the WMECO electric accounts. The Installer is checking with the Customer regarding this issue. The meter department field checked the electric service at the site so that comments can be sent to the installer on how to revise the one line drawing. sent an e-mail to the installer asking if the project is moving forward, have gotten no reply. Interconnecting Customer requested an extension, expires 2/5/15. Received drawings prior to expiration of extension. Reviewed for completeness, app not complete. Project withdrawn, sent e-mail to installer and customer. withdrawn
WMECO | Pittsfield | 6B427-2014 | 01201 | 30.25 | Solar | 30B4 | 2014-08-26 | 2014-09-18 | 17 | 14 | 3 | 2014-09-19 | 2014-09-22 | 2 | 1 | 1 | [20 empty] | 2014-09-22 |  | 2014-12-01 |  | EXP | [6 empty] | 2015-01-29 | 2015-02-04 | 2015-02-04 | Application received, initial review performed, three phase service with single phase inverters, need phase loss relay, meter ordered, revised drawing required, approval to install. Have not rcvd the signed agreement for the Interconnecting Customer. Rvdc signed agreement. Rcvd completion docs, need revised witness test procedure. Rcvd revised witness Test procedure, scheduled Witness Test. Performed Witness Test. Customer on line.
WMECO | Chesterfield | 6F652-2014 | 01012 | 22 | Solar | 18K3 | 2014-09-15 | 2014-10-15 | 22 | 20 | 2 | 2014-10-16 | 2014-11-05 | 15 | 8 | 7 | [20 empty] | 2014-11-12 |  | Q4 2014 |  | EXP | [6 empty] | 2015-01-21 | 2015-01-26 | 2015-01-26 | Application complete, started initial review, made site visit to check tranformer, sent e-mail to installer asking for revised print to show subpanel in small horse barn and that the Customer is requesting a site visit. Resent e-mail to installer that the Custmer wants a site visit. Customer changed DC-STC number. Sent out Draft IA, waiting for stamped one line to send IA out for signature. In the interest of time the Exhibit G was sent to the Customer without the stamped one line, which will be sent at a later date. stamped 1-line rcvd, inspector requirement completed, waiting for completion docs to schedule Witness Test. Rcvd COC and pictures, need Witness Test procedure. Rcvd Witness Test procedure, scheduled Witness Test, performed Witness Test. Customer is on line.
WMECO | Pittsfield | 6B436-2014 | 01201 | 499 | Solar | 30B2 | 2014-09-25 | 2014-10-09 | 11 | 5 | 6 | 2014-10-09 | 2014-10-15 | 4 | 3 | 1 | 2014-10-16 | 2014-11-07 | 17 | 0 | 17 | [15 empty] | 2014-12-02 |  | 2014-12-14 |  | EXP | 2014-12-27 | 2014-12-30 | 2014-12-30 | 1 |  | 1 | 2014-12-26 | 2014-12-31 | 2015-01-12 | Application receved, application reviewed for Completeness - info required, Rcvd info, sent initial review to Customer, need Supplemental review, Customer asking WMECO to send Supplemental Review Agreement. Rcvd signed agreement and check. WMECO internal conf call held. Sent installer & Customer e-mail, info is required from them for the supplemental review. Supplemental Review is underway. The Supplemental Review report was sent to the Interconnecting Customer and Customer. The Interconnecting Customer requested a name /entity for the project. Info on how to process the name change was sent to the Int Cust. Int Cust is required to take out a work request for system modifications but has not yet done this. The project is on Customer Hold until the name change paper work is finalized and a work requist number is provided. Work request was submitted, site visit was performed, work order was written, cost estimate was sent, Draft Exhibit G and H were sent for review, Executable Exhibit G and H were sent. Signed Exhibit G was recevied by WMECO, system modifications are scheduled contingent upon Interconnecting Customer work to be completed. rcvd system modification monies, construction work scheduled, rcvd inspector requirement completion, construction work completed, witness Test scheduled, Witness Test performed, need inverter setting sheets and cap allocation. Cap allocation recvd. Rcvd inverter settting sheets, need PE stamped revised drawing with the correct inverter settings. The Interconnecting Customer cannot get the drawing stamped until 1/19/15, they were given approval to operate on 1/12/15 but they have until 1/20/15 to send the PE stamped drawing. In all of the confusion of this project the CoC and the inspector sign off was not recieved for the solar project prior to being given approval to operate. An e-mail was sent to the Int Customer asking for these two items to be completed. CoC was rcvd, still need electrical inspector sign off in WR.
WMECO | Springfield | 6S530-2014 | 01109 | 44.55 | Solar | 5JNW_1 | 2014-09-29 |  |  | 14 | [28 empty] | 2014-11-01 |  | STD | [9 empty] | Application not complete. Customer is located on the area network. Customer cancelled instead of moving forward with a study.
WMECO | Springfield | 6S531-2014 | 01109 | 44.55 | Solar | 5J9 | 2014-09-29 | 2014-10-28 | 21 | 20 | 1 | 2014-10-29 | 2014-11-18 | 14 | 3 | 11 | [20 empty] | 2014-11-24 |  | 2014-11-01 |  | EXP | [8 empty] | 2015-02-18 | Application received, need info for application complete, recevied info, application complete. Reviewed project, sent Draft Exhibit G and H for review, sent Exhibit G and H for signature. Rcvd signed agreements, rcvd inspector sign off, waiting for completion docs to schedule Witness Test.
WMECO | Indian Orchard | 6S532-2014 | 01151 | 180 | Solar | 27A13 | 2014-09-29 | 2014-10-14 | 11 | 10 | 1 | 2014-10-15 | 2014-11-26 | 30 | 9 | 21 | [20 empty] | 2014-12-05 |  | 2014-11-30 |  | EXP | [6 empty] | 2015-08-28 | 2015-09-02 | 2015-09-02 | App complete. Agreements out for signature. Signed Agreements recevd. Witness Test performed. Comp docs rcvd. Project is on line.
WMECO | Easthampton | 6A880-2014 | 01027 | 98 | Solar | 15A2 | 2014-10-06 | 2014-11-26 | 36 | 34 | 2 | 2014-11-28 | 2015-02-19 | 59 | 35 | 24 | [20 empty] | 2015-04-15 |  | 2014-12-01 |  | EXP | [6 empty] | 2016-03-03 | 2016-03-10 | 2016-03-10 | App complete. Screen Review email sent. Draft IA out for review. Signed Exhibt G and H received, new service required, customer on line
WMECO | Pittsfield | 6B446-2014 | 01201 | 234 | Solar | 19A5 | 2014-10-15 | 2014-10-28 | 10 | 3 | 7 | 2014-10-29 | 2014-12-10 | 29 | 13 | 16 | 2014-12-11 | 2016-02-19 | 311 | 262 | 49 | [15 empty] | 2016-02-22 |  | 2014-12-31 |  | EXP | [6 empty] | 2016-03-17 | 2016-03-23 | 2016-03-23 | application complete. Sent initial review to Customer. Sent Supplemental Agreement for signature. Rcvd signed agreement and payment. Review is started. Supplemenatl Review finished, project requires Direct Transfer Trip. Customer requests a conference call with protection engineer. Customer Hold. Conference call was conducted, the project manager will get back to WMECO whether project will move forward. Interconnecting Customer wants estimates for PLC and phone transfer trip. Need time for other departments to give estimates. Sent estimate to Interconnecting Customer. Customer deceided to ove forward with no export. New drawing requried, Rcvd new drawing, sned to protection dept for review. Customer requested conf call re: comments on drawings, will send three line drawing re: relay connections. received completion docs, scheduled Witness Test. Witness Test successful, Customer on line.
WMECO | Pittsfield | 6B447-2014 | 01201 | 168 | Solar | 30B2 | 2014-10-24 | 2014-10-29 | 4 | 0 | 4 | 2014-10-30 | 2014-11-18 | 13 | 12 | 1 | [20 empty] | 2014-12-09 |  | 2014-12-12 |  | EXP | [6 empty] | 2015-01-21 | 2015-01-22 | 2015-01-22 | application complete. Sent initial Review to Customer. Ordered meter, Meter engineering had questions regarding where solar was interconnecting. Needed revised drawing and explanation of service configuration. Meter supervisor perormed site visit and verified service configuration. Rcvd revised drawing. Sent Exhibit G and H for signature. Rcvd IA docs, waiting for completion docs, rcvd and reviewed comp docs, scheduled Witness Test, Performed Witness Test. Customer on line.
WMECO | Amherst | 6A919-2014 | 01002 | 57.75 | Solar | 17K8 | 2014-11-05 | 2014-11-25 | 14 | 6 | 8 | 2014-11-26 | 2015-03-02 | 67 | 33 | 34 | [20 empty] | 2015-03-04 |  | not supplied |  | EXP | [6 empty] | 2015-06-12 | 2015-06-15 | 2015-06-15 | app complete. Needs site visit. Site visit with meter supervisor and installer, may need to discuss system modifications prior to initial review. Cust putting solar on two buildings but tying both in to one service. The meter supervisor is requireing that the meters be moved outside as the installer is making a change to the service. Customer Hold. The installer will change where the solar will be interconnected. A site visit is required to verify from which transformer the new POI is fed. transformer info was received, Time frame for approval to install was negotiated with installer. Installer is required to send revised application, one line and site plan. Rcvd revised info, sent out Exhibit G for signature. Rcvd signed agreement. Rcvd comp docs, need revised wit test procedure and fist page of Sched Z. Rcvd info Witness Test scheduled. Witness Test performed, Customer is on line.
WMECO | Hatfield | 6A935-2014 | 01038 | 3300 | Solar | 18G5 | 2014-11-13 | 2015-03-04 | 78 | 69 | 9 | [10 empty] | 2015-03-05 | 2015-06-06 | 67 | 61 | 6 | 2015-05-29 | 2015-11-05 | 115 | 12 | 103 | 2016-04-12 |  | -30303 |  |  |  |  | 2015-10-01 |  | COMP | [9 empty] | App rcvd, review for completeness, app not complete, Int Customer asked for an extension. Int Customer requested conference call. Customer requested Impact Study estimates, application still not complete. Info rcvd, application complete, sent out initial review to Customer. Scoping meeting required. Scoping meeting held, info required, property may be more than one parcel. Project may become third party owned. On Customer hold. Proprties are required to be legally combined. Impact Study started. IC requested 30 days for tech reasons in DS. Sold, new applicant cancelled project.
WMECO | Ludlow | 6S672-2014 | 01056 | 998 | Solar | 19S3 | 2014-11-14 | [31 empty] | Summer 2015 |  | EXP | [9 empty] | cancelled
WMECO | Ludlow | 6S673-2014 | 01056 | 499 | Solar | 19S3 | 2014-11-14 | [31 empty] | Summer 2015 |  | EXP | [9 empty] | cancelled
WMECO | Ludlow | 6S674-2014 | 01056 | 499 | Solar | 19S3 | 2014-11-14 | [31 empty] | Summer 2015 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S689-2014 | 01104 | 150 | Solar | 21S7 | 2014-11-25 | 2015-07-30 | 176 | 163 | 13 | 2015-07-31 | 2016-05-05 | 200 | 31 | 169 | [10 empty] | 2016-05-06 | 2016-09-26 | 102 | 46 | 56 | [5 empty] | 2016-09-26 |  | 12/2014 |  | STD | [6 empty] | 2017-08-24 | 2017-08-25 | 2017-08-25 | Application received, review for completeness, app not complete, info required sent e-mail. Rcvd info, initial review sent out to customer, held scoping meeting. Negotiated timeline, customer submitted smaller 150 kW option, 10 days for Impact Study stage, other negotiations to determine creative solution for interconnection. No system modifications required. New service was installed. Service swith gear was delivered as 120/208 instead of 480/277. Inverters were purchased and installed as 120/208. Output of inverters did not change. Witness test performed, project is on line.
WMECO | Otis | 6B458-2014 | 01029 | 1500 | Wind | 19J6 | 2014-12-01 | 2014-12-17 | 13 | 12 | 1 | [10 empty] | 2014-12-18 | 2015-03-26 | 70 | 63 | 7 | 03/27/2015 & 7/15/2016 | 07/23/2015 & 10/5/2016 | #VALUE! | 17 | #VALUE! | 2016-02-23 |  | -30268 | 144 |  | 2015-07-27 |  | 2015-06-01 |  | COMP | [8 empty] | 2018-03-09 | Received new App. App fee waived. Application is Complete with one design option. Impact Study Agreement out for signature. I.S. Agreement and payment received. In Impact Study. On Customer stop from 7/23/15 to 2/22/16. I.C. verified they CAN get the origianl turbine. Another Impact Study started 7/18/16 due to design issue. New ISA issued 10/5/16 for new design option 2.
WMECO | Otis | 6B459-2014 | 01253 | 960 | Solar | 19J4 | 2014-12-02 | 2015-01-19 | 34 | 27 | 7 | 2015-01-20 | 2015-06-15 | 105 | 44 | 61 | [10 empty] | 2015-08-03 | 2016-01-04 | 111 | 41 | 70 | [5 empty] | 2016-02-04 |  | 2015-08-01 |  | COMP | [9 empty] | app rcvd, need check, rcvd check, review for completeness, need info, rcvd info app complete. Sent out initial review, scoping meeting held, info required. Rcvd partial info. Talked with the Town of Otis Administrator, the propertiy is not divided into 2 parcels. Project on Customer Hold. Customer sent e-mail, two projects cannot be installed on the one parcel, they will cancel one project and submit a new project on another project for another parcel. Had multiple calls with Customer, Customer will move forward with the two projects oin the one parcel and get an exception form the DPU for Net metering purposes. Sent out Group Impact Study agreement for both projects 6B459-2015 and 6B463-2014. Rcvd signed agreement and personal check for study, certified check required. Project on hold until certified check rcvd. Rcvd cert check, Impact study in process. Impact Study report sent to Customer. Detailed Study agreement sent out for signature. Withdrawn after agreement not executed, applicant does not have money.
WMECO | Sunderland | 6A962-2014 | 01375 | 22.8 | Solar | 18G3 | 2014-12-03 | 2014-12-30 | 19 | 9 | 10 | 2014-12-31 | 2015-02-27 | 43 | 36 | 7 | [20 empty] | 2015-03-06 |  | 2015-02-01 |  | EXP | [6 empty] | 2015-04-15 | 2015-04-16 | 2015-04-16 | app complete, sent e-mail, need initial review, sent out initial review need revised drawing due to line side tap. Rcvd info. Need tofield check transformer, may be more than 20 kW of generation on shared secondaries, same property, two single phase services. Field check performed , this Customer has one service fed from a pad mounted tranformer. Sent out Exhibit G for signature. Rcvd signed IA. Rcvd revised one line, sent as attachment 1, ordered net meter. Rcvd completion docs, scheduled meter set and Witness Test. Witness Test performed, successful, Customer is on line
WMECO | Pittsfield | 6B462-2014 | 01201 | 3300 | Solar | 15E2 | 2014-12-08 | 2014-12-15 | 6 | 2 | 4 | [10 empty] | 2014-12-16 | 2015-02-17 | 45 | 26 | 19 | 2015-03-16 | 2015-08-24 | 116 | 33 | 83 | 2015-08-11 | 2015-10-22 | 53 | 30 | 23 | 2015-10-23 |  | 2015-08-27 |  | COMP | [8 empty] | 2017-04-13 | app complete, sent e-mail, needs initial review, sent out initial review, info required. Held scoping meeting, info received. Requested estimates for Impact Study, rcvd estimates, sent out Impact Study Agreement, Waiting for signed agreement and check. Rcvd signed agremment and check, sent info to vendor to start study. Impact Stduy check returned for insufficiant funds. Impact Study on hold. Int Customer replaced check with certified check, Impact Study restarted. Conf call with Int Cust. on DG process again. They are searching for Host Customer. DTT estimate requested from line and S/S. Impact Study Report sent out to Customer with plus/minus 25% system modification costs. Held call with customer, revided report. Negotiated timeline. Detailed Study agreement and ISO notification form sent out to Customer. Recevied first payment for the Detailed Study. Site visit performed, Int Customer required to take out WR # to move forward with writing WO.
WMECO | Otis | 6B463-2014 | 01253 | 960 | Solar | 19J4 | 2014-12-08 | 2015-01-19 | 30 | 24 | 6 | 2015-01-20 | 2015-06-15 | 105 | 44 | 61 | [10 empty] | 2015-08-03 | 2016-01-04 | 111 | 41 | 70 | [5 empty] | 2016-02-04 |  | 2015-08-01 |  | COMP | [9 empty] | app rcvd, need check, rcvd check, review for completeness, need info, rcvd info app complete. Sent out initial review, scoping meeting held, info required. Rcvd partial info. Talked with the Town of Otis Administrator, the propertiy is not divided into 2 parcels. Project on Customer Hold. app rcvd, need check, rcvd check, review for completeness, need info, rcvd info app complete. Sent out initial review, scoping meeting held, info required. Rcvd partial info. Talked with the Town of Otis Administrator, the propertiy is not divided into 2 parcels. Project on Customer Hold. Customer sent e-mail, two projects cannot be installed on the one parcel, they will cancel one project and submit a new project on another project for another parcel. Had multiple calls with Customer, Customer will move forward with the two projects oin the one parcel and get an exception form the DPU for Net metering purposes. Sent out Group Impact Study agreement for both projects 6B459-2015 and 6B463-2014. Impact Study report sent to Customer. Detailed Study agreement sent out for signature. Withdrawn after agreement not executed, applicant does not have money.
WMECO | Longmeadow | 6S708-2014 | 01106 | 16.35 | Solar | 22H12 | 2014-12-09 | 2014-12-15 | 5 | 0 | 5 | 2014-12-16 | 2015-01-23 | 28 | 11 | 17 | [20 empty] | 2015-02-03 |  | 2015-02-09 |  | EXP | [9 empty] | app complete, sent e-mail, needs initial review, initial reviewe performed revised drawing required. Rcvd drawing, info for agreements required, sent out Exhibit H and Exhibit G for signature. Cancelled by IC.
WMECO | Greenfield | 6F724-2014 | 01301 | 48 | Solar | 21C1 | 2014-12-12 | 2014-12-30 | 12 | 10 | 2 | 2014-12-31 | 2015-03-09 | 49 | 38 | 11 | [20 empty] | 2015-03-25 |  | 2015-02-15 |  | EXP | [6 empty] | 2015-06-04 | 2015-06-08 | 2015-06-08 | Addition to existing system. Application is Complete with one design option. Screen Review sent. Need updated info from I.C. Have executed IA. Have Comp. Docs. Witness Test Successful. Online 6/8.
WMECO | Deerfield | 6F725-2014 | 01342 | 4500 | Solar | 22B4 | 2014-12-12 | 2015-01-29 | 34 | 23 | 11 | [10 empty] | 2015-01-30 | 2015-03-17 | 33 | 16 | 17 | 2015-03-18 | 2015-11-30 | 184 | 38 | 146 | 2016-03-18 |  | -30286 |  |  | 2015-12-07 |  | Q3/4 2015 |  | COMP | [6 empty] | 2017-10-11 | 2017-10-18 | 2017-12-08 | Review for completeness, app not complete, need UL certs for inverters. Rcvd cert for the 1000 NX need cert for the 1000 NX. Invetigated information that Customer sent for the 500NX inverter and was able to determine that the 500NX is certified for UL1741, Application is complete, needs initial review. Sent out initial review comments, held scoping meeting, info required. Rcvd info, requested Impact Study estimate, Rcvd estimate, sent out Impact Study agreement. Rcdv signed Impact Study agreement and check. Sent info to vendor to start study. Requested estimate for DTT. Issue with high voltage at PCC, snt volt reg info to Asset Mangment, sent out report to Customer. Sent Detailed Study Agreement for signature. Sent early ISA and landowner agreement for signature
WMECO | Greenfield | 6F736-2014 | 01301 | 24 | Solar | 21C4 | 2014-12-26 | 2015-01-22 | 20 | 13 | 7 | 2015-01-23 | 2015-03-12 | 35 | 23 | 12 | [22 empty] | Feb 2015 |  | EXP | [9 empty] | App reviewed for completness, App complete. Initial review performed, site address on electric account does not match town records. Installer submitted smaller project due to the required upgrades. This project is cancelled
WMECO | Springfield | 6S764-2015 | 01108 | 37.8 | Solar | 22H16 | 2015-01-06 | 2015-01-30 | 19 | 17 | 2 | 2015-02-02 | 2015-03-06 | 25 | 15 | 10 | 2015-03-09 | 2015-04-03 | 20 | 1 | 19 | [15 empty] | 2015-04-20 |  | 2015-01-22 |  | EXP | [6 empty] | 2015-08-10 | 2015-08-12 | 2015-08-13 | App complete. Screening email sent. Need information from I.C. and Supplemental Review completed. Signed Exhibit G received. Comp docs rcvd, Wit test perfomed, need RESERVED STATUS for Cap Allocation. Cap Allocation rcvd, project on line.
WMECO | Pittsfield | 6B474-2015 | 01201 | 36 | Solar | 15E3 | 2015-01-07 | 2015-02-11 | 26 | 9 | 17 | 2015-02-12 | 2015-04-08 | 40 | 37 | 3 | 2015-04-28 | 2015-05-18 | 15 | 14 | 1 | [15 empty] | 2015-07-08 |  | 2015-08-01 |  | EXP | [6 empty] | 2015-11-10 | 2015-11-13 | 2015-11-13 | Application received, app acknowledged, need check, app not complete, info required, app complete, initial review, info required, held scoping meeting, drawing needs to be revised, sent to meter engineering for their review and comment. Project requires supplemental review due to distance of tranformers from proposed solar facility i.e.generation may cause high voltage in area, Jon made a complaint to DPU. Suppleeemental agreement was sent for his signature. Conference call with Jon and Cindy. Jon sent stamped drawing will send signed supplemental review agreement and check. Rcvd signed agreement and check, Supp Rev schedueld. Supp Rev completed, system mods required. sent e-mail to Customer with choices and high level costs. Cusotmer does not agree with high level costs. Customer took out request for one of the choices. He will have a site visit with with tech. Technician met with the customer for a site visit. The technicain wrote up the job for the system modiicaiton cost estimate. The Exhibit G and Exhibit H were sent our for signature. The Net meter was ordered. system modifications were completed. Completion docs were received, net meter was set. Electric Customer changed, new account number, new Exhibit H and Exhibit G required. Wtness Test scheduled, sent out revised IAs, Witness test performed, IAs rcvd. Customer on line.
WMECO | Deerfield | 6F749-2015 | 01342 | 40 | Solar | 22B1 | 2015-01-07 | 2015-02-04 | 21 | 15 | 6 | 2015-02-05 | 2015-09-18 | 162 | 111 | 51 | [20 empty] | 2015-09-18 |  | 2015-02-01 |  | EXP | [6 empty] | 2015-11-05 | 2015-11-12 | 2016-02-03 | App reviewed for complteness, not complete. Rcvd info, application complete. Initial Review sent to customer. Scoping meeting held, service required to be uipgraded due to safety hazard at meter socket. Revised one line required.
WMECO | Hadley | 6A1005-2015 | 01035 | 253 | Solar | 17K6 | 2015-01-09 | 2015-01-23 | 11 | 5 | 6 | 2015-01-26 | 2015-03-02 | 26 | 15 | 11 | 2015-03-05 | 2015-03-27 | 17 | 0 | 17 | [15 empty] | 2015-04-03 |  | 2015-05-05 |  | EXP | [6 empty] | 2015-06-24 | 2015-07-01 | 2015-07-23 | App Rcvd, app fee check rcvd, Application reviewed for completeness, app not complete. Rcvd info, app complete, needs initial review. Sent out initial review, info required from Int Customer. Supplemental review required. Info required, rcvd info, sent out supplemental Review for signture. Supplemental Review finished, sent out report to Customer. Started Exhibit G and Exhibit H, sent out for signature. Cell based Net meter is scheduled to be set. Meter is set. Waiting for insigned IAs and completion docs. Recvd compl docs and insurance cert - o.k. Witness Test scheduled. Witness Test performed and was successful. The Customer is required to stay off line until they have CADMUS cap allocation Reserved status. Interconnecting Customer and Customer have been notified numerous times of this issue. Reserved status has been received, Customer is on line.
WMECO | Lanesborough | 6B479-2015 | 01237 | 368 | Solar | 15E2 | 2015-01-21 | 2015-02-04 | 11 | 6 | 5 | 2015-02-05 | 2015-03-03 | 19 | 12 | 7 | 2015-03-04 | 2017-01-08 | 483 | 435 | 48 | [15 empty] | 2017-01-10 |  | 2015-05-05 |  | EXP | [8 empty] | 2017-12-22 | App rcvd, need app fee check, rcvd check, reviewed for copleteness, app not complete, rcvd info, app complete. Sent out initial review, review by meter supervisor is required. info required. Supplemental review required. Rcvd info, Sent out Supplemental Review Agreement for signture. Rcvd signed agreement, review started, review report sent ot Customer. Project requires DTT. High level Estimates for DTT required for Customer. Negotiated timeline, 5 extra days.
WMECO | Becket | 6B481-2015 | 01223 | 24 | Solar | 16B1 | 2015-01-23 | 2015-01-26 | 2 | 1 | 1 | 2015-01-27 | 2015-03-06 | 29 | 16 | 13 | [20 empty] | 2015-03-10 |  | Spring 2015 |  | EXP | [6 empty] | 2015-10-05 | 2015-10-07 | 2015-10-09 | App rcvd, need check for application fee, need projetc check list, rcvd check, review for completeness, app not complete inverter cut sheet required. Rcvd info, app complete, Sent out IA for signature.
WMECO | Whately | 6A1047-2015 | 01093 | 20 | Solar | 18G8 | 2015-02-02 | 2015-02-19 | 14 | 5 | 9 | 2015-02-19 | 2015-02-20 | 2 | 0 | 2 | [20 empty] | 2015-02-20 |  | Q1 2015 |  | EXP | [6 empty] | 2015-07-03 | 2015-07-07 | 2015-07-07 | App rcvd, app fee required, rcvd app fee, review for completeness, app not complete info required, rcvd infor app complete. Initial review sent out. Started IA, sent out IA for signature, Rcvd revised Schedule Z. Rcvd comp docs, rvwd comp docs, need revised CoC with building designation per the electric account address. Rcvd revised CoC, Wit test procedure, scheduled Witness Test, Witness Test successful, project on line.
WMECO | Hatfield | 6A1053-2015 | 01038 | 1890 | Solar | 18G6 | 2015-02-09 | 2015-05-15 | 70 | 65 | 5 | 2015-05-18 | 2015-10-29 | 119 | 76 | 43 | [10 empty] | 2015-10-30 | 2016-02-12 | 76 | 2 | 74 | 2016-03-07 |  | -30277 |  |  | 2016-02-12 |  | Sept 2015 |  | COMP | [6 empty] | 2017-07-03 | 2017-07-10 | 2017-09-07 | Application received, review for completeness, app not complete.
WMECO | Whately | 6A1062-2015 | 01093 | 19.3 | Solar | 18G6 | 2015-02-19 | 2015-04-22 | 45 | 41 | 4 | 2015-04-23 | 2015-07-10 | 57 | 47 | 10 | [20 empty] | 2015-07-10 |  | 2015-04-06 |  | EXP | [6 empty] | 2016-01-29 | 2016-02-02 | 2016-02-02 | Application received, review for completeness, app not complete. Rcvd revised information app complete, Initial review performed, info required
WMECO | Becket | 6B483-2015 | 01223 | 17.5 | Solar | 19J6 | 2015-02-23 | 2015-04-16 | 39 | 18 | 21 | 2015-04-17 | 2015-04-30 | 10 | 8 | 2 | [20 empty] | 2015-05-18 |  | 2015-05-15 |  | EXP | [8 empty] | 2015-11-04 | App rcvd, need check for application fee, need projetc check list, rcvd check, other inor required, rcvd info, technical review of application. The solar facility is shown being located on adjoining parcel. Customer owns both parcels, he will legally combine them. Started IA, talked with Mrs. Haber, address listed on application and electric account are incorrect, sent an e-mail to Customer to call Customer Service to change street number. sent out ISA, ordered meter. Rvcd comp docs, set meter, customer asked that wit test be waived as we did not sched wit test within 10 days of recving comp docs, Wit test waived. project on line.
WMECO | South Deerfield | 6F801-2015 | 01342 | 500 | Biogas | 22B1 | 2015-02-24 | 2015-04-15 | 37 | 34 | 3 | 2015-04-16 | 2015-05-22 | 27 | 16 | 11 | [22 empty] | 2015-12-01 |  | STD | [9 empty] | Application received. Check for fee received. App Complete. Sent Screen Review email. Need Supplemental Review. Scoping call held. Interconnecting Customer elected to go to Impact Study. Impact Sutdy out for signature on 6/1. Have not received agreement or payment yet. withdrawn
WMECO | Deerfield | 6F802-2015 | 01373 | 18 | Solar | 18G3 | 2015-02-24 | 2015-03-05 | 8 | 0 | 8 | 2015-03-06 | 2015-03-13 | 6 | 4 | 2 | [20 empty] | 2015-03-24 |  | March 2015 |  | EXP | [6 empty] | 2015-05-19 | 2015-05-21 | 2015-05-21 | Application rcvd, rvw for completeness. Info required, info received same day, app complete. Initial Review started. New service under construction. New service finished. IA sent out for signature. New service, new electrci account was set up. Rcvd coc, not O.K. rcvd revised CoC , need revised one ine drawing to send to meter engineering, rcvd cap reserved status and remaining comp docs, witness test performed, project in line.
WMECO | Greenfield | 6F815-2015 | 01301 | 56 | Solar | 21C1 | 2015-03-05 | 2015-03-31 | 19 | 15 | 4 | 2015-04-01 | 2015-04-13 | 9 | 2 | 7 | [20 empty] | 2015-04-15 |  | 2015-05-01 |  | EXP | [6 empty] | 2017-04-19 | 2017-04-20 | 2017-04-20 | Application received, need app fee, check rcvd, review for app complete, app complete, initial review started, talked with installer revised one line and site plan required. Info recvd, IA sent for signature
WMECO | Lee | 6B490-2015 | 01238 | 1904 | Solar | 17G7 | 2015-03-12 | 2015-03-20 | 7 | 2 | 5 | [10 empty] | 2015-03-23 | 2015-04-30 | 29 | 23 | 6 | 2015-05-15 | 2015-08-12 | 64 | 3 | 61 | 2015-08-20 |  | -30135 |  |  | 2015-08-27 |  | 2015-09-30 |  | STD | [6 empty] | 2017-03-28 | 2015-04-11 | 2017-04-11 | App rcvd, need check for application fee, rcvd check revw for completeness, app not complete info required, rcvd info, app complete, intial review sent out, info required, sent out dates for scoping meeting. Held scoping meeting, Int Cust wanted to send in options. Rcvd two options both for a smaller project each with different inverters.initial review of options started. Comments sent out, info required, rcvd info, need to rvw. Started Impact Study. Impact Study Report and Detailed Study agreement sent to Customer. Rcvd signed agreement and check. Need to schedule site visit.
WMECO | Pittsfield | 6B497-2015 | 01201 | 2340 | Solar | 19A3 | 2015-03-24 | 2015-03-31 | 6 | 2 | 4 | [10 empty] | 2015-04-01 | 2015-06-04 | 47 | 30 | 17 | 2015-06-05 | 2015-11-06 | 111 | 0 | 111 | 2015-11-24 | 2016-09-21 | 217 | 0 | 217 | 2015-11-09 |  | Fall 2015 |  | COMP | [6 empty] | 2017-01-18 | 2017-01-20 | 2017-01-31 | Application received, reviewed for completeness, infor required, talked with project contact on phone regarding transmission access permission study required. Contacted Transmission real estate that a solar facility is proposing to install/cross the ROW. Application complete, Initial Review sent ot Interconnecting Customer, scoping meeting set up. held site visit with installer, lect customer, transmission ROW. Civil plans required for transmission ROW review, fee and agreement required for review. Solar facility can be installed as long as equipment is located outside of ROW. Rcvd signed T and Impact Study agreements and checks. Impact Study in process. Detailed Study in process. Work orders written, equipment long led. equipment received. Substation work started. Substation work finished, Plc line work finished. witness Test scheduled. witness Test performed. Need updated Schedule Z with correct allocation info. Schedule Z received with correct info. project given approval to operate.
WMECO | Greenfield | 6F836-2015 | 01301 | 19.3 | Solar | 21C4 | 2015-03-27 | 2015-04-20 | 17 | 8 | 9 | 2015-04-21 | 2015-04-21 | 1 | 0 | 1 | [20 empty] | 2015-04-22 |  | 2015-04-01 |  | EXP | [6 empty] | 2015-05-15 | 2015-05-19 | 2015-05-19 | App recvd, app fee required. Rcvd app fee, rvw for completeness, app not complete, address required to be changed to correct address as reflected on asessor's map. Address changed, app complete. Initial review revised 1-line drawing required. Rcvd revised 1-line. IA sent out for signature. Rcvd CoC and pics, need signed Ex G wit test procedure and cap allocation. Received required comp docs, scheduled wit test, project on line.
WMECO | Granville | 6S941-2015 | 01034 | 24.99 | Solar | 29A5 | 2015-04-06 | 2015-04-16 | 9 | 6 | 3 | 2015-04-16 | 2015-04-16 | 1 | 0 | 1 | 2015-04-21 | 2015-05-06 | 12 | 0 | 12 | [15 empty] | 2015-05-07 |  | 2015-06-01 |  | EXP | [6 empty] | 2015-07-30 | 2015-07-31 | 2015-07-31 | Application received, need app fee, received check for app fee, reviewed for completeness, app not complete, info required. Rcvd info, sent out initial review, system mods required, sned out Supp Rev to write WO, sent out IA with est for syst Mods. Rcvd executed IA. Customer wants to remove OH service and install UG service. All work will be scheduled for same day. Construtciot and service work fininshed. Scheduled Witness Test. Performed Witness Test, Customer is on line.
WMECO | Sunderland | 6A1124-2015 | 01375 | 44 | Solar | 18G3 | 2015-04-17 | 2015-05-12 | 18 | 11 | 7 | 2015-05-13 | 2015-06-18 | 27 | 0 | 27 | 2015-06-22 | 2015-06-30 | 7 | 0 | 7 | [15 empty] | 2015-06-30 |  | July 2015 |  | EXP |  |  | 2015-09-25 |  |  |  | 2015-09-24 | 2015-09-30 | 2015-09-30 | App received. Rvw for app cmplt. Info required. Rcvd info app cmplt. Negotiated time line for tech. Supp Review rquired. Sent out agreement to Customer. Rcvd signed agrmnt and check, started review. solar facility was installed prior to approval to install. Supplemental Review performed, system modifications required, sent out early IA for signature. Rvcd signed IA. Rvcd comp docs, electrician required to take out electrical permit for service upgrade. CT rated service. Customer will upgrade service. Customer issue OH service VS UG service. UG service installed, service complete. Net meter set. Witnest scheduled. performed, Customer on line.
WMECO | Northfield | 6F857-2015 | 01360 | 56 | Solar | 21B8 | 2015-04-17 | 2015-05-12 | 18 | 6 | 12 | 2015-05-13 | 2015-05-27 | 11 | 0 | 11 | 2015-06-17 | 2015-07-20 | 24 | 17 | 7 | [15 empty] | 2015-07-31 |  | 7/2015 |  | EXP | [6 empty] | 2016-02-02 | 2016-02-03 | 2016-02-03 | App rcvd. Need app fee. Rcvd app fee, rvw for compltness, app complete. Tech rvw new service requied D transformers required to be as close as possibe to inveters re: volt rise at Customer. Supp Rev to determinte syste mod costs. Sent out agreement, rcvd agrmnt waiting for check, rcvd check. Tech held site meeting with installer and customer. Tech wrote eatimate for OH and UG service. Installer/Customer requested UG service, sent out IA to include UG service estimate. Work required OH primary extension onto Customer's property.
WMECO | Southwick | 6S959-2015 | 01077 | 1316 | Solar | 29A5 | 2015-04-17 | 2015-04-22 | 4 | 0 | 4 | 2015-04-23 | 2015-09-21 | 108 | 93 | 15 | [10 empty] | 2015-09-22 | 2015-12-11 | 59 | 0 | 59 | 2016-01-11 |  | -30237 |  |  | 2016-01-26 |  | 2015-12-01 |  | COMP | [7 empty] | 2016-12-06 | 2016-12-14 | App rcvd, app fee check required, rcvd app fee, reviewed for completeness app complete. Facility to be interconnected on a separate parcel that Big Y owns. Properties required to be legally combined. Customer proposes to install new sw gear with solar facility behind the Customer meter. There is a nonprimary Net meter available for this size project. Eversoure not sure how to interconnect due to project size requiring DTT. Conf call with Customer re: proejct staus update. Conf call with Eversource attorney, exception from DPU required for combining properties. Initial review sent to Customer.
WMECO | Shelburne Falls | 6F872-2015 | 01370 | 39.6 | Solar | 22B5 | 2015-04-23 | [31 empty] | not supplied |  | EXP | [9 empty] | cancelled
WMECO | Hatfield | 6A1145-2015 | 01038 | 18.5 | Solar | 18G6 | 2015-04-27 | 2015-06-02 | 27 | 20 | 7 | 2015-06-03 | 2015-07-02 | 22 | 4 | 18 | [20 empty] | 2015-07-10 |  | June 2015 |  | EXP | [6 empty] | 2015-08-11 | 2015-08-17 | 2015-08-17 | App and app fee recvd., Info required, review for completeness, info required, rcvd info , app complete. Initial review sent out to Customer, revised one line and site plan required.
WMECO | South Deerfield | 6F881-2015 | 01373 | 16.7 | Solar | 22B1 | 2015-04-27 | 2015-05-18 | 16 | 13 | 3 | 2015-05-19 | 2015-05-27 | 7 | 3 | 4 | [20 empty] | 2015-05-29 |  | not supplied |  | EXP | [6 empty] | 2016-02-02 | 2016-02-03 | 2016-02-03
WMECO | Amherst | 6A1148-2015 | 01002 | 54 | Solar | 19B16 | 2015-04-29 | 2015-07-16 | 57 | 40 | 17 | 2015-07-17 | 2015-11-18 | 89 | 18 | 71 | [20 empty] | 2015-11-18 |  | July 2015 |  | EXP | [6 empty] | 2016-09-01 | 2016-09-07 | 2016-09-07
WMECO | Ashfield | 6F890-2015 | 01330 | 1995 | Biogas | 38A1 | 2015-05-01 | 2015-11-02 | 132 | 63 | 69 | 2015-11-03 | 2016-02-17 | 77 | 30 | 47 | [10 empty] | 2016-02-18 | 2016-08-15 | 128 | 54 | 74 | 2016-08-16 | 2017-10-05 | 298 | 34 | 264 | 2017-10-10 |  | 2016-01-01 |  | COMP | [9 empty] | cancelled
WMECO | Richmond | 6B516-2015 | 01254 | 18 | Solar | 30B2 | 2015-05-04 | 2015-08-10 | 71 | 55 | 16 | 2015-08-11 | 2015-10-14 | 47 | 5 | 42 | 2015-10-15 | 2016-01-29 | 77 | 44 | 33 | [15 empty] | 2016-02-02 |  | 2015-06-01 |  | EXP | [6 empty] | 2016-09-21 | 2016-09-26 | 2016-10-18
WMECO | Pittsfield | 6B521-2015 | 01201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-01 | 17 | 8 | 9 | 2015-06-02 | 2015-12-30 | 152 | 44 | 108 | [10 empty] | 2015-12-31 | 2016-04-19 | 79 | 26 | 53 | 2016-06-13 |  | -30347 |  |  | 2016-05-09 |  | 2015-06-30 |  | STD | [8 empty] | 2018-10-30 | App rcvd, need app fee, rcvd fee. Rvw for completeness, app complete, sent out initial review. Sent out group impact study agreement, need signed agreement and check, missed dealine for signed agreement and check, will be withdrawn if not received, signed agreement and check received, Impact study started, Impact Study report sent to customer. Started Ex G, Customer needs to decide on which Option to build. Customer decided on Option1, Ex G and Ex I sent out for signature. Need site plan to complete Detailed Study, extra 20 business days for Detailed Study.
WMECO | Pittsfield | 6B522-2015 | 01201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-10 | 24 | 8 | 16 | 2015-06-11 | 2015-12-30 | 145 | 27 | 118 | [10 empty] | 2015-12-31 | 2016-04-19 | 79 | 26 | 53 | 2016-06-13 |  | -30347 |  |  | 2016-05-09 |  | 2015-06-30 |  | STD | [8 empty] | 2018-10-30 | App rcvd, need app fee, rcvd fee. Rvw for completeness, app complete, sent out initial review. Sent out group impact study agreement, need signed agreement and check, missed dealine for signed agreement and check, will be withdrawn if not received, signed agreement and check received, Impact study started, Impact Study report sent to customer. Started Ex G, Customer needs to decide on which Option to build. Customer decided on Option1, Ex G and Ex I sent out for signature. Need site plan to complete Detailed Study, extra 20 business days for Detailed Study.
WMECO | Pittsfield | 6B523-2015 | 01201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-10 | 24 | 8 | 16 | 2015-06-11 | 2015-12-30 | 145 | 32 | 113 | [10 empty] | 2015-12-31 | 2016-04-19 | 79 | 26 | 53 | 2016-06-13 |  | -30347 |  |  | 2016-05-09 |  | 2015-06-30 |  | STD | [8 empty] | 2018-10-30 | App rcvd, need app fee, rcvd fee. Rvw for completeness, app complete, sent out initial review. Sent out group impact study agreement, need signed agreement and check, missed dealine for signed agreement and check, will be withdrawn if not received, signed agreement and check received, Impact study started, Impact Study report sent to customer. Started Ex G, Customer needs to decide on which Option to build. Customer decided on Option1, Ex G and Ex I sent out for signature. Need site plan to complete Detailed Study, extra 20 business days for Detailed Study.
WMECO | Pittsfield | 6B525-2015 | 01201 | 499 | Solar | 30B5 | 2015-05-08 | 2015-06-10 | 24 | 8 | 16 | 2015-06-11 | 2015-12-30 | 145 | 27 | 118 | [10 empty] | 2015-12-31 | 2016-04-19 | 79 | 26 | 53 | 2016-06-13 |  | -30347 |  |  | 2016-05-09 |  | 2015-06-30 |  | STD | [8 empty] | 2018-10-30 | App rcvd, need app fee, rcvd fee. Rvw for completeness, app complete, sent out initial review. Sent out group impact study agreement, need signed agreement and check, missed dealine for signed agreement and check, will be withdrawn if not received, signed agreement and check received, Impact study started, Impact Study report sent to customer. Started Ex G, Customer needs to decide on which Option to build. Customer decided on Option1, Ex G and Ex I sent out for signature. Need site plan to complete Detailed Study, extra 20 business days for Detailed Study.
WMECO | West Springfield | 6S1051-2015 | 01089 | 180 | Solar | 16C12 | 2015-05-08 | 2015-06-25 | 35 | 20 | 15 | 2015-06-26 |  | -30096 | [24 empty] | 2015-11-15 |  | EXP | [9 empty] | App received. On hold for 6S240-2014, cancelled
WMECO | Hadley | 6A1169-2015 | 01035 | 140 | Solar | 18G5 | 2015-05-12 | 2015-06-11 | 23 | 10 | 13 | 2015-06-12 | 2015-11-16 | 112 | 105 | 7 | [10 empty] | 2015-11-16 | 2016-02-11 | 64 | 5 | 59 | [5 empty] | 2016-02-12 |  | 2015-08-01 |  | STD | [8 empty] | 2016-09-27 | application received, app fee received, need whole amount, remaining amount received. Review for completeness, info required, info received, App complete. On Hold for RES America Impact Study for 110 days, Initial review performed, Impact Study performed, Impact Study report sent out, included design in study. Early IA sent out.
WMECO | Pittsfield | 6B529-2015 | 01201 | 499 | Solar | 30B5 | 2015-05-12 | 2015-07-06 | 40 | 10 | 30 | 2015-07-07 | 2015-12-30 | 127 | 32 | 95 | [10 empty] | 2015-12-31 | 2016-04-19 | 79 | 26 | 53 | 2016-06-13 |  | -30347 |  |  | 2016-05-09 |  | 2015-06-30 |  | COMP | [8 empty] | 2019-10-24 | on line
WMECO | Ludlow | 6S1070-2015 | 01056 | 1095.8 | Solar | 19S2 | 2015-05-15 | 2015-07-30 | 55 | 51 | 4 | 2015-07-31 | 2016-02-18 | 145 | 43 | 102 | [10 empty] | 2016-02-19 | 2016-05-11 | 59 | 0 | 59 | 2016-06-09 |  | -30345 |  |  | 2016-05-11 |  | 2016-04-01 |  | STD | [8 empty] | 2018-01-03 | Negotiated timeline with IC due to new option submitted after deemed complete. Part of group. Fourth applicant cancelled so new Detailed Study Agreements sent out. Application sold.
WMECO | Ludlow | 6S1071-2015 | 01056 | 1095.8 | Solar | 19S2 | 2015-05-15 | 2015-07-30 | 55 | 51 | 4 | 2015-07-31 | 2016-02-18 | 145 | 43 | 102 | [10 empty] | 2016-02-19 | 2016-05-11 | 59 | 0 | 59 | 2016-06-09 |  | -30345 |  |  | 2016-05-11 |  | 2016-04-01 |  | COMP | [8 empty] | 2017-12-21 | Negotiated timeline with IC due to new option submitted after deemed complete. Part of group. Fourth applicant cancelled so new Detailed Study Agreements sent out. Application sold.
WMECO | Shelburne Falls | 6F914-2015 | 01370 | 25 | Solar | 29R2 | 2015-05-19 | 2015-07-10 | 39 | 16 | 23 | 2015-07-13 | 2015-07-14 | 2 | 0 | 2 | [20 empty] | 2015-07-16 |  | not supplied |  | EXP | [6 empty] | 2015-08-24 | 2015-08-25 | 2015-08-25 | app rcvd, cust submited option2 app complete, tech rvw done, IA sent out for signature, signed IA rcvd, scheduled wit test, performed Wit test, project on line.
WMECO | Pittsfield | 6B537-2015 | 01201 | 499 | Solar | 30B7 | 2015-05-20 | 2015-06-15 | 19 | 3 | 16 | 2015-06-16 | 2015-10-20 | 91 | 30 | 61 | [10 empty] | 2015-10-21 | 2016-03-30 | 116 | 0 | 116 | 2016-04-14 |  | -30305 |  |  | 2016-04-25 |  | 2015-10-01 |  | STD | [8 empty] | 2018-02-09 | Rcvd app and app fee, started rvw for completeness, did not rcv all attachements as file was greater than 10 MB. Talked with Customer, they resent file, app complete, initial review sent out. Will require group Impact Study with project 6B553-2015. Held scoping meeting. Sent out Impact Study agrmnt for signature. Impact Study Report and Detailed Study Agreement sent out to Customer. Received payment for Detailed Study, held internal site visit.
WMECO | Pittsfield | 6B538-2015 | 01201 | 499 | Solar | 30B7 | 2015-05-20 | 2015-06-15 | 19 | 3 | 16 | 2015-06-16 | 2015-10-20 | 91 | 29 | 62 | [10 empty] | 2015-10-21 | 2016-03-30 | 116 | 0 | 116 | 2016-04-14 |  | -30305 |  |  | 2016-04-25 |  | 2015-10-01 |  | STD | [8 empty] | 2018-02-09 | Rcvd app and app fee, started rvw for completeness, did not rcv all attachements as file was greater than 10 MB. Talked with Customer, they resent file, app complete, initial review sent out.Will require group Impact Study with project 6B553-2015. Held scoping meeting. Sent out Impact Study agrmnt for signature. Impact Study Report and Detailed Study Agreement sent out to Customer. Received payment for Detailed Study, held internal site visit.
WMECO | Pittsfield | 6B539-2015 | 01201 | 499 | Solar | 30B7 | 2015-05-20 | 2015-06-15 | 19 | 3 | 16 | 2015-06-16 | 2015-10-20 | 91 | 29 | 62 | [10 empty] | 2015-10-21 | 2016-03-30 | 116 | 0 | 116 | 2016-04-14 |  | -30305 |  |  | 2016-04-25 |  | 2015-10-01 |  | STD | [8 empty] | 2018-02-09 | Rcvd app and app fee, started rvw for completeness, did not rcv all attachements as file was greater than 10 MB. Talked with Customer, they resent file, app complete, initial review sent out. Will require group Impact Study with project 6B553-2015. Held scoping meeting. Sent out Impact Study agrmnt for signature. Impact Study Report and Detailed Study Agreement sent out to Customer. Received payment for Detailed Study, held internal site visit.
WMECO | Greenfield | 6F915-2015 | 01301 | 480 | Solar | 21C1 | 2015-05-21 | 2015-07-09 | 36 | 7 | 29 | 2015-07-10 | 2016-01-07 | 130 | 43 | 87 | [10 empty] | 2016-01-08 | 2016-05-13 | 91 | 29 | 62 | [7 empty] | 2015-07-01 |  | STD | [9 empty] | app and fee rcvd. App cplt, initial rvw sent to customer. Scoping meeting scheduled. Work Order to be written for load service and solar using one transformer. Cancelled by applicant
WMECO | Cummington | 6F917-2015 | 01026 | 499 | Solar | 18K3 | 2015-05-21 | 2015-07-30 | 51 | 47 | 4 | 2015-07-31 | 2015-12-30 | 109 | 33 | 76 | [10 empty] | 2015-12-31 | 2016-09-09 | 182 | 59 | 123 | 2016-09-12 |  | -30412 |  |  | 2016-09-26 |  | Oct 2015 |  | COMP | [8 empty] | 2018-08-09 | Impact Study Report and Detailed Study agreement sent to interconnecting Customer. Applicant send revised ap with Landowner info 9/26/16. Two applicants cancelled 1/20/17, Detailed Study and system mod costs need to be recalculated. January 2017 change is assignment
WMECO | Ludlow | 6S1096-2015 | 01056 | 1095.8 | Solar | 19S2 | 2015-05-21 | 2015-06-24 | 25 | 17 | 8 | 2015-06-25 | 2016-02-18 | 171 | 43 | 128 | [10 empty] | 2016-02-19 | 2016-05-11 | 59 | 0 | 59 | 2016-06-09 |  | -30345 |  |  | 2016-05-11 |  | 2016-04-01 |  | STD | [8 empty] | 2018-01-03 | Negotiated timeline with IC due to new option submitted after deemed complete. Part of group. Fourth applicant cancelled so new Detailed Study Agreements sent out. Application sold.
WMECO | Amherst | 6A1199-2015 | 01002 | 2002 | Solar | 19B16 | 2015-05-22 | 2015-07-20 | 42 | 14 | 28 | 2015-07-21 | 2015-11-04 | 77 | 53 | 24 | [10 empty] | 2015-11-05 | 2016-03-03 | 86 | 13 | 73 | 2016-05-17 |  | -30328 |  |  | 2016-03-04 |  | 2015-12-31 |  | COMP | [6 empty] | 2017-05-08 | 2017-05-11 | 2017-05-12 | Application and check received. Review for completeness, info required, rcvd info, itinitial review sent out. The one line drawings that were sent to vendor with requested revisions also had a project size change that was not brought to the attention of Eversource Energy until reviewing the Draft Impact Study Report. Impact Study report was sent to Customer. Early ISA was sent out for signature.
WMECO | Amherst | 6A1200-2015 | 01002 | 1728 | Solar | 19B16 | 2015-05-22 | 2015-07-20 | 42 | 14 | 28 | 2015-07-21 | 2015-11-04 | 77 | 53 | 24 | [10 empty] | 2015-11-05 | 2016-03-03 | 86 | 13 | 73 | 2016-05-17 |  | -30328 |  |  | 2016-03-04 |  | 2015-12-31 |  | COMP | [6 empty] | 2017-11-22 | 2017-11-28 | 2017-12-27 | Application and check received. Review for completeness, info required, rcvd info, itinitial review sent out. The one line drawings that were sent to vendor with requested revisions also had a project size change that was not brought to the attention of Eversource Energy until reviewing the Draft Impact Study Report. Impact Study report was sent to Customer. Early ISA was sent out for signature.
WMECO | Cummington | 6F920-2015 | 01026 | 840 | Solar | 18K3 | 2015-05-22 | 2015-07-30 | 50 | 46 | 4 | 2015-07-31 | 2015-12-30 | 109 | 33 | 76 | [10 empty] | 2015-12-31 | 2016-06-15 | 120 | 0 | 120 | [7 empty] | Oct 2015 |  | STD | [9 empty] | Impact Study Report and Detailed Study agreement sent to interconnecting Customer 6F920-2015 is cancelled by customer
WMECO | Deerfield | 6F921-2015 | 01342 | 19.3 | Solar | 22B7 | 2015-05-26 | 2015-07-06 | 30 | 4 | 26 | 2015-07-07 | 2015-07-22 | 12 | 1 | 11 | [20 empty] | 2015-08-14 |  | Aug 2015 |  | EXP | [6 empty] | 2016-02-04 | 2016-02-08 | 2016-02-08 | app rcvd, app complete, tech rvw, IA sent out for signature, signed IA rcvd. Need RESERVED status and comp docs.
WMECO | Amherst | 6A1211-2015 | 01002 | 192 | Solar | 18G1, 18G2 | 2015-05-29 | 2015-07-06 | 27 | 9 | 18 | 2015-07-07 | 2015-10-08 | 68 | 37 | 31 | [20 empty] | 2015-10-23 |  | 2015-09-01 |  | EXP | [6 empty] | 2016-02-11 | 2016-02-18 | 2016-02-18 | Removed.
WMECO | Plainfield | 6F926-2015 | 01070 | 331 | Solar | 18K3 | 2015-05-29 | 2015-07-30 | 45 | 6 | 39 | 2015-07-31 | 2015-11-05 | 70 |  | 70 | [22 empty] | 2015-12-01 |  | STD | [9 empty] | cancelled
WMECO | Plainfield | 6F927-2015 | 01070 | 499 | Solar | 18K3 | 2015-05-29 | 2015-07-30 | 45 | 6 | 39 | 2015-07-31 | 2015-11-05 | 70 |  | 70 | [22 empty] | 2015-12-01 |  | STD | [9 empty] | cancelled
WMECO | Amherst | 6A1217-2015 | 01002 | 15 | Solar | 17K8 | 2015-06-01 | 2015-07-06 | 26 | 1 | 25 | 2015-07-07 | 2015-07-23 | 13 | 1 | 12 | [20 empty] | 2015-08-14 |  | not supplied |  | EXP | [6 empty] | 2015-09-01 | 2015-09-11 | 2015-09-11 | app rcvd, need info, app complete, sent out initial review. Sentout IA for signature, rcvd signed IA, rcvd comp docs. Scheduled Wit test, performed Wit test. Project on line.
WMECO | Turners Falls | 6F939-2015 | 01376 | 1774 | Solar | 21C3 | 2015-06-05 | 2015-10-05 | 87 | 1 | 86 | 2015-10-06 |  | -30168 | [24 empty] | 2015-11-01 |  | EXP | [9 empty] | Customer did proceed with study, created group when new applications were received. Application withdrawn after missed deadlines and no response.
WMECO | Pittsfield | 6B553-2015 | 01201 | 1480 | Solar | 30B7 | 2015-06-08 | 2015-07-22 | 33 | 17 | 16 | 2015-07-23 | 2015-10-20 | 64 | 29 | 35 | [10 empty] | 2015-10-21 | 2016-03-30 | 116 | 0 | 116 | 2016-04-14 |  | -30305 |  |  | 2016-04-25 |  | 2015-07-30 |  | COMP | [8 empty] | 2017-12-21 | App rcvd, need app fee, check rcvd, app complete, Initial rvw. Will require group study with 6B553-2015. Held scoping meeting, property on which solar to be installed not owned by Int Cust nor host Cust, has different address from that on the application. Installer to submit revised application for the 220 Cloverdale St property that will replace the 1505 West St applicaiton. Sent out Impact Study agrmnt for signature. Impact Study Report and Detailed Study Agreement sent out to Customer. Received payment for Detailed Study,
WMECO | Pittsfield | 6B554-2015 | 01201 | 497 | Solar | 30B2 | 2015-06-08 | 2015-09-08 | 67 | 44 | 23 | 2015-09-09 |  | -30149 | [24 empty] | 2015-07-30 |  | STD | [9 empty] | Group. Cancelled by applicant, incentives changed.
WMECO | Pittsfield | 6B555-2015 | 01201 | 497 | Solar | 30B2 | 2015-06-08 | 2015-09-08 | 67 | 44 | 23 | 2015-09-09 |  | -30149 | [24 empty] | 1901-12-30 |  | STD | [9 empty] | Group. Cancelled by applicant, incentives changed.
WMECO | Shelburne Falls | 6F953-2015 | 01370 | 40 | Solar | 22B5 | 2015-06-10 | 2015-07-17 | 28 | 9 | 19 | 2015-07-20 | 2015-08-10 | 16 | 15 | 1 | 2015-08-20 | 2015-10-05 | 33 | 22 | 11 | [15 empty] | 2015-10-07 |  | 2015-08-01 |  | EXP | [6 empty] | 2015-12-23 | 2015-12-30 | 2015-12-30 | app rvcd, need app fee, rcvd app fee, app complete, initial review, need infor rcvd info, need Supplemental Review sent out agreement. Rcvd agreement, supp Rev started.
WMECO | Easthampton | 6A1251-2015 | 01027 | 244 | Solar | 15A3 | 2015-06-15 | 2015-09-28 | 76 | 12 | 64 | 2015-09-29 |  | -30163 | 117 | [23 empty] | 2015-07-31 |  | STD | [9 empty] | IC sent new option, not sure what they will build, did not execute study, will now be parr of a group, cancelled by applicant
WMECO | Whately | 6A1252-2015 | 01093 | 496 | Solar | 18G8 | 2015-06-15 | 2015-07-17 | 25 | 18 | 7 | 2015-07-20 | 2015-11-02 | 76 | 21 | 55 | [10 empty] | 2015-11-03 | 2016-01-27 | 62 | 3 | 59 | 2016-03-09 |  | -30279 | 0 |  | 2016-02-04 |  | not supplied |  | STD | [6 empty] | 2017-02-28 | 2017-03-01 | 2017-03-02
WMECO | Springfield | 6S1174-2015 | 01104 | 150 | Solar | 5J13 | 2015-06-15 | 2015-09-08 | 62 | 40 | 22 | 2015-09-09 | 2016-06-01 | 191 | 95 | 96 | [10 empty] | 2016-06-02 | 2016-08-23 | 59 | 0 | 59 | 2016-09-14 |  | -30414 |  |  | 2016-09-14 |  | 2015-07-31 |  | STD | [6 empty] | 2017-10-05 | 2017-10-11 | 2017-10-26 | Applicant not sure if they will proceed, requested extension.
WMECO | Springfield | 6S1175-2015 | 01104 | 284 | Solar | 5J13 | 2015-06-15 | 2015-09-08 | 62 | 40 | 22 | 2015-09-09 | 2016-06-01 | 191 | 95 | 96 | [10 empty] | 2016-06-02 | 2016-08-23 | 59 | 0 | 59 | 2016-09-14 |  | -30414 |  |  | 2016-09-14 |  | 1901-12-31 |  | STD | [6 empty] | 2018-01-17 | 2018-01-24 | 2018-01-30 | Applicant not sure if they will proceed., sent 10 day notice of missed deadline.
WMECO | Pittsfield | 6B569-2015 | 01201 | 408 | Solar | 19A8 | 2015-06-18 | 2015-09-29 | 74 | 25 | 49 | 2015-09-30 |  | -30164 | [24 empty] | 2015-07-31 |  | STD | [9 empty] | Cancelled by Interconnecting Customer.
WMECO | Becket | 6B571-2015 | 01223 | 10 | Solar | 19J6 | 2015-06-18 | 2015-07-22 | 25 | 23 | 2 | 2015-07-23 | 2015-08-20 | 21 | 2 | 19 | [20 empty] | 2015-08-20 |  | 08-2015 |  | EXP | [6 empty] | 2016-01-25 | 2016-01-25 | 2016-01-25
WMECO | Shelburne | 6F969-2015 | 01370 | 16.7 | Solar | 22B6 | 2015-06-18 | 2015-07-30 | 31 | 13 | 18 | 2015-07-31 |  | -30121 | [24 empty] | not supplied |  | EXP | [9 empty] | cancelled by applicant
WMECO | Chesterfield | 6F970-2015 | 01012 | 499 | Solar | 18K3 | 2015-06-18 | 2015-10-06 | 79 | 1 | 78 | 2015-10-07 | 2015-12-30 | 61 | 33 | 28 | [10 empty] | 2015-12-31 |  | -30230 | [9 empty] | 2015-10-30 |  | STD | [9 empty] | cancelled by applicant
WMECO | Chesterfield | 6F971-2015 | 01012 | 499 | Solar | 18K3 | 2015-06-18 | 2015-09-29 | 74 | 1 | 73 | 2015-09-30 | 2015-12-30 | 66 | 33 | 33 | [10 empty] | 2015-12-31 | 2016-09-09 | 182 | 59 | 123 | 2016-09-12 |  | -30412 |  |  | 2016-09-26 |  | 2015-10-30 |  | COMP | [9 empty] | Impact Study Report and Detailed Study agreement sent to interconnecting Customer. On 9/23/16 applicant submitted revisd app with Landowner info. Cancelled by applicant.
WMECO | Chesterfield | 6F972-2015 | 01012 | 499 | Solar | 18K3 | 2015-06-18 | 2015-09-29 | 74 | 1 | 73 | 2015-09-30 | 2015-12-30 | 66 | 33 | 33 | [10 empty] | 2015-12-31 | 2016-09-09 | 182 | 59 | 123 | 2016-09-12 |  | -30412 |  |  | 2016-09-26 |  | 2015-10-30 |  | COMP | [9 empty] | Impact Study Report and Detailed Study agreement sent to interconnecting Customer. On 9/23/16 applicant submitted revisd app with Landowner info. Cancelled by applicant.
WMECO | Easthampton | 6A1270-2015 | 01027 | 27 | Solar | 15A3 | 2015-06-19 | 2015-08-10 | 37 | 23 | 14 | 2015-08-11 | 2015-11-10 | 66 | 0 | 66 | [20 empty] | 2015-11-10 |  | not supplied |  | EXP | [6 empty] | 2015-12-15 | 2015-12-17 | 2015-12-18
WMECO | Blandford | 6B572-2015 | 01008 | 499 | Solar | 19J2 | 2015-06-19 | 2015-09-28 | 72 | 4 | 68 | 2015-09-29 |  | -30163 | [24 empty] | Winter 2015 |  | STD | [9 empty] | Cancelled by Interconnecting Customer.
WMECO | Pittsfield | 6B579-2015 | 01201 | 170 | Solar | 30B2 | 2015-06-23 | 2015-09-08 | 56 | 34 | 22 | 2015-09-09 |  | -30149 | [24 empty] | 2015-07-31 |  | EXP | [9 empty] | was behind apps in a group study, nwanted new service, customer cancelled service WR#, sent 10 day notice, no response, withdrawn
WMECO | Greenfield | 6F980-2015 | 01301 | 450 | Diesel | 21C4 | 2015-06-23 | 2015-09-29 | 71 | 17 | 54 | 2015-09-30 | 2016-02-23 | 105 | 18 | 87 | 2016-02-23 | 2016-10-05 | 162 | 5 | 157 | [15 empty] | 2016-10-06 |  | not supplied |  | EXP | [6 empty] | 2016-12-07 | 2016-12-18 | 2016-12-19
WMECO | Plainfield | 6F986-2015 | 01070 | 392 | Solar | 18K3 | 2015-06-29 | 2015-09-29 | 67 | 0 | 67 | 2015-09-30 | 2015-11-05 | 27 |  | 27 | [22 empty] | 2015-10-30 |  | STD | [9 empty] | cancelled
WMECO | Plainfield | 6F987-2015 | 01070 | 499 | Solar | 18K3 | 2015-06-29 | 2015-09-29 | 67 | 0 | 67 | 2015-09-30 | 2015-11-05 | 27 |  | 27 | [22 empty] | 2015-10-30 |  | STD | [9 empty] | cancelled
WMECO | Sunderland | 6A1298-2015 | 01375 | 242 | Solar | 18G3 | 2015-07-02 | 2015-12-21 | 123 | 30 | 93 | 2015-12-22 | 2016-01-28 | 28 | 9 | 19 | [10 empty] | 2016-01-28 | 2016-04-28 | 66 | 0 | 66 | [5 empty] | 2016-05-03 |  | winter 2015 |  | STD | [6 empty] | 2016-12-27 | 2016-12-28 | 2016-12-30 | part of group, not sure what size to install, submitted options, other applicant cancelled
WMECO | Sunderland | 6A1309-2015 | 01375 | 160 | Solar | 18G3 | 2015-07-10 | 2015-12-21 | 117 | 25 | 92 | 2015-12-22 | 2016-01-28 | 28 | 9 | 19 | [10 empty] | 2016-01-28 | 2016-04-28 | 66 | 0 | 66 | [7 empty] | winter 2015 |  | STD | [9 empty] | part of group, not sure what size to install, submitted options, cancelled by Int Cust
WMECO | Conway | 6F1012-2015 | 01341 | 19.8 | Solar | 38A1 | 2015-07-14 | 2015-08-07 | 19 | 6 | 13 | 2015-08-10 | 2015-11-03 | 62 | 11 | 51 | 2015-11-12 | 2015-11-30 | 13 | 0 | 13 | [15 empty] | 2015-12-07 |  | 2015-09-01 |  | EXP | [6 empty] | 2016-03-04 | 2016-03-08 | 2016-03-08
WMECO | Easthampton | 6A1329-2015 | 01027 | 20.5 | Solar | 15A5 | 2015-07-15 | 2015-08-10 | 19 | 18 | 1 | 2015-08-11 | 2015-10-15 | 48 | 0 | 48 | [20 empty] | 2015-11-10 |  | 2015-10-05 |  | EXP | [6 empty] | 2015-12-18 | 2015-12-22 | 2015-12-22
WMECO | Bernardston | 6F1028-2015 | 01337 | 36 | Solar | 21C1 | 2015-07-27 | 2015-09-23 | 43 | 5 | 38 | 2015-09-24 | 2015-10-13 | 14 | 3 | 11 | [20 empty] | 2015-10-13 |  | Sept 2015 |  | EXP | [6 empty] | 2015-12-15 | 2015-12-17 | 2015-12-18
WMECO | Easthampton | 6A1343-2015 | 01027 | 1980 | Solar | 15A2 | 2015-07-30 | 2015-12-09 | 95 | 26 | 69 | 2015-12-10 |  | -30215 | [24 empty] | 2016-05-28 |  | STD | [9 empty] | Int Customer send Impact Study Agreement. Sent 10 day notice because they did not execute agreement. Int Cust cancelled their application.
WMECO | Pittsfield | 6B624-2015 | 01201 | 995 | Solar | 30B7 | 2015-07-31 | 2015-08-06 | 5 | 3 | 2 | 2015-08-07 |  | -30126 | [24 empty] | 10/1/2015 |  | STD | [9 empty] | Rcvd app and app fee, started rvw for completeness, app complete. Will require group Impact Study with project 6B553-2015. Held scoping meeting. Sent out Impact Study agrmnt for signature. Cancelled
WMECO | Pittsfield | 6B625-2015 | 01201 | 870 | Solar | 30B3 | 2015-08-03 | 2015-10-06 | 47 | 13 | 34 | 2015-10-07 | 2016-05-02 | 149 | 92 | 57 | [10 empty] | 2016-05-03 | 2016-07-19 | 56 | 32 | 24 | [7 empty] | 12/1/2015 |  | STD | [9 empty] | Was in group. Group changed. New agreement sent out. Cancelled by applicant.
WMECO | West Springfield | 6S1388-2015 | 01089 | 30 | Solar | 21N6 | 2015-08-03 | 2015-09-23 | 38 | 19 | 19 | 2015-09-24 | 2015-11-10 | 34 | 9 | 25 | [20 empty] | 2015-11-16 |  | Q3 2015 |  | EXP | [6 empty] | 2016-02-11 | 2016-02-17 | 2016-02-17
WMECO | Whately | 6A1350-2015 | 01093 | 1115 | Solar | 18G8 | 2015-08-04 | 2015-11-20 | 79 | 11 | 68 | 2015-11-23 | 2016-04-28 | 114 | 51 | 63 | [10 empty] | 2016-04-29 | 2016-08-31 | 89 | 1 | 88 | 2016-10-31 |  | -30447 |  |  | 2016-10-03 |  | 2/28/16 |  | STD | [8 empty] | 2020-10-01 | on line
WMECO | Hinsdale | 6B635-2015 | 01235 | 1484 | Solar | 18C2 | 2015-08-11 | [31 empty] | 2015-09-01 |  | EXP | [9 empty] | withdrawn
WMECO | Hadley | 6A1366-2015 | 01035 | 32 | Solar | 17K5 | 2015-08-12 | 2015-10-22 | 52 | 39 | 13 | 2015-10-23 | 2015-11-03 | 8 | 0 | 8 | [20 empty] | 2015-11-10 |  | not supplied |  | EXP | [6 empty] | 2016-01-27 | 2016-01-29 | 2016-01-29 | App rcvd, need app fee check, rcvd check, reviewed for copleteness, app complete. Sent out initial review. Sent out Appl to Install. Rcvd Comp Docs. Sch Witness Test. Performed Witness Test. Cust Online.
WMECO | Pittsfield | 6B640-2015 | 01201 | 54 | Solar | 30B2 | 2015-08-12 | 2015-09-23 | 31 | 5 | 26 | 2015-09-24 | 2015-12-29 | 69 | 47 | 22 | [20 empty] | 2015-12-30 |  | 2015-07-01 |  | EXP | [6 empty] | 2016-05-13 | 2016-05-13 | 2016-05-13
WMECO | Springfield | 6S1435-2015 | 01104 | 140 | Solar | 5J16 | 2015-08-13 | 2015-09-24 | 31 | 5 | 26 | 2015-09-25 | 2016-02-05 | 96 | 19 | 77 | [10 empty] | 2016-02-08 | 2016-05-05 | 64 | 0 | 64 | 2016-10-06 |  | -30430 |  |  | 2016-05-05 |  | 2015-10-23 |  | STD | [6 empty] | 2017-09-20 | 2017-09-26 | 2017-10-06 | Revised early ISA sent 9/12/16., with new Detailed Study Agreement.
WMECO | Sandisfield | 6B641-2015 | 01255 | 21.91 | Solar | 19J4 | 2015-08-14 | 2015-09-24 | 30 | 27 | 3 | 2015-09-25 |  | -30161 | [24 empty] | 2015-10-13 |  | EXP | [9 empty] | Cancelled by applicant
WMECO | Pittsfield | 6B655-2015 | 01201 | 1.8 | Solar | 30B7 | 2015-08-14 | 2015-09-23 | 29 | 21 | 8 | 2015-09-23 | 2016-04-08 | 143 | 105 | 38 | [20 empty] | 2016-04-11 |  | 09302015 |  | EXP | [6 empty] | 2017-05-16 | 2017-05-30 | 2017-05-30 | small educational facility for students, addition
WMECO | Hatfield | 6A1390-2015 | 01066 | 584 | Solar | 18G6 | 2015-08-20 | 2015-11-17 | 64 | 4 | 60 | 2015-11-18 | 2016-02-16 | 65 | 28 | 37 | [10 empty] | 2016-02-17 |  | -30264 | [9 empty] | 2015-05-01 |  | STD | [9 empty] | Project cancelled by Int Cust 3/24/16, said customer changed their mind.
WMECO | Sandisfield | 6B651-2015 | 01255 | 16.4 | Solar | 19J4 | 2015-08-21 | 2015-10-27 | 48 | 41 | 7 | 2015-10-28 | 2015-11-04 | 6 | 0 | 6 | 2015-12-02 | 2015-12-03 | 2 | 0 | 2 | [15 empty] | 2015-12-04 |  | Sept 2015 |  | EXP | [6 empty] | 2015-12-22 | 2015-12-24 | 2015-12-24
WMECO | Plainfield | 6F1072-2015 | 01070 | 1050 | Solar | 18K3 | 2015-08-24 | [31 empty] | 2016-06-28 |  | EXP | [9 empty] | withdrawn
WMECO | Southwick | 6S1476-2015 | 01077 | 18.4 | Solar | 29A5 | 2015-08-24 | 2015-10-02 | 30 | 12 | 18 | 2015-10-05 | 2016-03-24 | 124 | 95 | 29 | 2016-03-25 |  | -30291 | [19 empty] | 2015-10-24 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Feeding Hills | 6S1481-2015 | 01030 | 17.25 | Solar | 16C17 | 2015-08-25 | 2015-10-22 | 43 | 30 | 13 | 2015-10-23 | 2015-10-28 | 4 | 0 | 4 | [20 empty] | 2015-10-30 |  | not supplied |  | EXP | [6 empty] | 2015-12-11 | 2015-12-14 | 2015-12-14
WMECO | West Hatfield | 6A1403-2015 | 01088 | 22.5 | Solar | 18G5 | 2015-08-28 | 2015-10-22 | 40 | 27 | 13 | 2015-10-22 | 2015-10-28 | 5 | 2 | 3 | [20 empty] | 2015-10-30 |  | not supplied |  | EXP | [6 empty] | 2015-12-15 | 2015-12-16 | 2015-12-16
WMECO | Dalton | 6B667-2015 | 01226 | 25 | Solar | 18C1 | 2015-09-02 | 2015-11-05 | 47 | 33 | 14 | 2015-11-06 | 2016-01-06 | 44 | 22 | 22 | 2016-01-07 | 2016-01-13 | 5 | 2 | 3 | [15 empty] | 2016-01-13 |  | 2015-09-25 |  | EXP | [6 empty] | 2016-06-27 | 2016-06-29 | 2016-06-29
WMECO | Easthampton | 6A1411-2015 | 01027 | 2100 | Solar | 15A5 | 2015-09-03 | [31 empty] | 2016-08-15 |  | EXP | [9 empty] | Applicant did not respond to requests for information. Sent 10 day notice and tried calling. Application withdrawn after two notices.
WMECO | Feeding Hills | 6S1520-2015 | 01030 | 5440 | Solar | 30A6 | 2015-09-03 | [31 empty] | 2016-08-15 |  | EXP | [9 empty] | Applicant did not respond to requests for information. Sent 10 day notice and tried calling. Application withdrawn after two notices.
WMECO | Pittsfield | 6B670-2015 | 01201 | 1380 | Solar | 30B7 | 2015-09-04 | 2015-09-17 | 10 | 2 | 8 | 2015-09-17 | 2015-10-20 | 24 | 22 | 2 | [10 empty] | 2015-10-21 | 2016-03-30 | 116 | 0 | 116 | 2016-04-14 |  | -30305 |  |  | 2016-04-25 |  | July 2016 |  | STD | [8 empty] | 2018-04-17 | Rcvd app and app fee, started rvw for completeness, app complete. Will require group Impact Study with project 6B553-2015. Sent out Impact Study agrmnt for signature. Impact Study Report and Detailed Study Agreement sent out to Customer. Received payment for Detailed Study, 2 options
WMECO | Springfield | 6S1550-2015 | 01109 | 1980 | Solar | 5J18 | 2015-09-04 | [31 empty] | 2015-05-01 |  | EXP | [9 empty] | withdrawn
WMECO | Southampton | 6A1417-2015 | 01073 | 2000 | Solar | 15A1 | 2015-09-08 | 2015-11-09 | 45 | 35 | 10 | 2015-11-10 | 2016-02-05 | 64 | 14 | 50 | [10 empty] | 2016-02-05 | 2016-07-19 | 118 | 54 | 64 | 2016-07-20 | 2017-04-21 | 198 | 145 | 53 | 2017-04-28 |  | 2016-08-15 |  | COMP | [8 empty] | 2019-02-20 | customer requested extension, application sold
WMECO | Savoy | 6B673-2015 | 01256 | 2000 | Solar | 18C1 | 2015-09-08 | 2015-11-09 | 45 | 17 | 28 | 2015-11-10 | 2016-02-11 | 68 | 20 | 48 | [10 empty] | 2016-02-12 | 2016-07-15 | 111 | 50 | 61 | 2016-07-18 | 2017-04-20 | 199 | 145 | 54 | 2017-05-10 |  | 8/15/2016 |  | COMP | [8 empty] | 2018-12-19 | customer requested extension10 day extension, negotiated timeline, customer selected 2000 kW size to move forward with oin 7/19/16, Customer changed proprty lines, interconnection point changed from Griffin Hill Rd to Windsor Rd. Application sold.
WMECO | Hinsdale | 6B674-2015 | 01235 | 1000 | Solar | 18C2 | 2015-09-08 | 2015-11-16 | 50 | 27 | 23 | 2015-11-17 |  | -30198 | [24 empty] | 8/15/2016 |  | STD | [9 empty] | Negotiated timeline, 20 days, customer submitted new options after complete. In group, group changed. IC cancelled project 5/17/16.
WMECO | Greenfield | 6F1098-2015 | 01301 | 2000 | Solar | 21C1 | 2015-09-08 | 2015-11-13 | 49 | 36 | 13 | 2015-11-16 | 2016-01-07 | 39 | 22 | 17 | [10 empty] | 2016-01-08 | 2016-05-13 | 91 | 29 | 62 | 2016-10-31 |  | -30447 |  |  | 2017-05-22 |  | 2016-08-15 |  | COMP | [8 empty] | 2019-01-25 | In group with another applicant 6F915 who dropped out after Impact Study was sent (7/21/16). Stop dates in Impact Study due to decision needed from other applicant. Negotiated timeline for Impact Study at applicants request, another 20 days. Application sold.
WMECO | Otis | 6B685-2015 | 01253 | 76.65 | Solar | 19J4 | 2015-09-14 | 2015-10-22 | 29 | 20 | 9 | 2015-10-23 | 2015-11-09 | 12 | 0 | 12 | [22 empty] | 2015-10-20 |  | EXP | [9 empty] | cancelled
WMECO | Hinsdale | 6B689-2015 | 01235 | 2000 | Solar | 18C2 | 2015-09-15 | 2015-11-16 | 45 | 27 | 18 | 2015-11-17 | 2016-08-30 | 206 | 152 | 54 | [10 empty] | 2016-08-31 | 2017-03-08 | 136 | 40 | 96 | 2017-03-09 |  | -30540 |  |  | 2017-04-12 |  | 2016-08-15 |  | STD | [8 empty] | 2018-12-19 | Negotiated timeline, 10 days and 15 days, customer submitted new options after complete. In group, group changed. 5/17/16 group changed again, no longer in group. Application sold.
WMECO | Springfield | 6S1577-2015 | 01119 | 16.7 | Solar | 20A12 | 2015-09-18 | 2015-11-20 | 46 | 18 | 28 | 2015-11-23 | 2015-12-21 | 21 | 17 | 4 | 2015-12-22 | 2016-01-14 | 18 | 0 | 18 | [15 empty] | 2016-01-25 |  | not supplied |  | EXP | [6 empty] | 2016-04-21 | 2016-04-27 | 2016-04-27
WMECO | Springfield | 6S1588-2015 | 01107 | 5300 | Natural Gas | 21S8 | 2015-09-22 | 2015-12-01 | 51 | 10 | 41 | 2015-12-02 | 2016-02-22 | 59 | 18 | 41 | 2016-02-23 | 2016-04-27 | 47 | 11 | 36 | [15 empty] | 2016-04-29 |  | June 2017 |  | EXP | [8 empty] | 2018-04-06
WMECO | Southampton | 6A1443-2015 | 01073 | 49.55 | Solar | 15A1 | 2015-09-23 | 2015-11-03 | 30 | 20 | 10 | 2015-11-04 | 2015-12-24 | 37 | 22 | 15 | 2015-12-28 | 2016-02-29 | 46 | 3 | 43 | [15 empty] | 2016-03-01 |  | 2015-10-12 |  | EXP | [6 empty] | 2016-09-09 | 2016-09-14 | 2016-09-14
WMECO | Lenox | 6B702-2015 | 01201 | 448 | Solar | 17G3 | 2015-09-23 | 2015-11-02 | 29 | 3 | 26 | 2015-11-03 | 2015-12-23 | 37 | 25 | 12 | [10 empty] | 2015-12-24 | 2016-02-11 | 36 | 4 | 32 | 2016-02-18 |  | -30265 |  |  | 2016-02-11 |  | 2016-03-31 |  | STD | [8 empty] | 2017-04-12
WMECO | Southwick | 6S1590-2015 | 01077 | 500 | Solar | 29A5 | 2015-09-23 | 2015-12-01 | 50 | 7 | 43 | 2015-12-02 | 2016-03-18 | 78 | 42 | 36 | [10 empty] | 2016-03-21 | 2016-08-22 | 111 | 0 | 111 | [5 empty] | 2016-08-22 |  | 12/1/2015 |  | COMP | [9 empty] | cancelled by applicant
WMECO | Gill | 6F1134-2015 | 01354 | 1992 | Solar | 21B8 | 2015-09-24 | 2015-11-04 | 30 | 3 | 27 | 2015-11-05 | 2016-02-18 | 76 | 9 | 67 | [10 empty] | 2016-02-19 | 2016-04-27 | 49 | 9 | 40 | 2016-05-06 |  | -30321 |  |  | 2016-04-27 |  | 2016-03-01 |  | COMP | [6 empty] | 2017-12-29 | 2017-12-05 | 2018-01-18 | App and fee rcvd and acknowledged. Review for app complete, need UL cert, app complete, sent out initial review, sent out Impact Study agreement, rcvd, signed Impact tudy Agreement, received check for Imapact study, Impact Study started, Impact Study report and Detailed Study agreement sent to Customer. sent Approval to Install to customer. held site visit, Customer needs to take out a request for service.
WMECO | Greenfield | 6F1135-2015 | 01301 | 43.8 | Solar | 22B7 | 2015-09-25 | 2015-10-08 | 10 | 5 | 5 | 2015-10-09 | 2016-02-04 | 85 | 50 | 35 | 2016-02-04 | 2016-02-17 | 10 | 1 | 9 | [15 empty] | 2016-02-17 |  | Jan 2016 |  | EXP | [9 empty] | notice sent to applicant to execute ISA, withdrawn after applicant did not pay for system modifications and fully execute ISA
WMECO | Southwick | 6S1604-2015 | 01077 | 2000 | Solar | 29A5 | 2015-09-25 | 2015-12-04 | 51 | 26 | 25 | 2015-12-07 |  | -30212 | [24 empty] | 8/15/2016 |  | STD | [9 empty] | Cancelled by applicant
WMECO | West Springfield | 6S1610-2015 | 01089 | 112 | Solar | 21N5 | 2015-09-28 | 2015-12-17 | 59 | 49 | 10 | 2015-12-18 |  | -30221 | [24 empty] | Nov 31 |  | EXP | [9 empty] | Withdrawn after no response to calls and emails.
WMECO | Plainfield | 6F1149-2016 | 01070 | 499 | Solar | 18K3 | 2015-10-02 | 2015-10-22 | 15 | 5 | 10 | 2015-10-23 | 2015-11-05 | 10 |  | 10 | [22 empty] | 2016-03-01 |  | STD | [9 empty] | cancelled
WMECO | Plainfield | 6F1150-2015 | 01070 | 1990 | Solar | 18K3 | 2015-10-05 | 2015-10-07 | 3 | 0 | 3 | 2015-10-08 | 2015-12-30 | 60 | 33 | 27 | [10 empty] | 2015-12-31 | 2016-09-09 | 182 | 59 | 123 | 2016-09-12 |  | -30412 |  |  |  |  | 2016-04-30 |  | STD | [9 empty] | Impact Study Report and Detailed Study agreement sent to interconnecting Customer, customer granted 10 day extension, negotiated timeline 10 days, cancelled
WMECO | Plainfield | 6F1151-2015 | 01070 | 1990 | Solar | 18K3 | 2015-10-05 | 2015-10-07 | 3 | 0 | 3 | 2015-10-08 | 2015-12-30 | 60 | 33 | 27 | [10 empty] | 2015-12-31 | 2016-09-09 | 182 | 59 | 123 | 2016-09-12 |  | -30412 |  |  | 2016-12-22 |  | 2016-04-30 |  | COMP | [8 empty] | 2019-02-15 | Impact Study Report and Detailed Study agreement sent to interconnecting Customer. An applicant dropped out of the group so the Impact Study was reevaluated. Two applicants cancelled 1/20/17, Detailed Study and system mod costs need to be recalculated.
WMECO | Amherst | 6A1467-2015 | 01002 | 15.3 | Solar | 17K2 | 2015-10-06 | 2015-11-23 | 35 | 5 | 30 | 2015-11-24 | 2016-03-02 | 72 | 52 | 20 | 2016-03-03 |  | -30275 | 9 | [18 empty] | 2015-12-05 |  | EXP | [9 empty] | Cancelled by applicant
WMECO | Hatfield | 6A1468-2015 | 01038 | 900 | Solar | 18G5 | 2015-10-06 | 2016-01-13 | 72 | 24 | 48 | 2016-01-14 |  | -30240 | [24 empty] | 2015-11-30 |  | STD | [9 empty] | On hold behind 6A935-2014. In group with 6A1528-2015. Cancelled by applicant.
WMECO | Springfield | 6S1673-2015 | 01102 | 1000 | Diesel | 21S7 21S3 | 2015-10-09 | 2016-02-23 | 98 | 51 | 47 | 2016-02-24 | 2016-04-04 | 29 | 17 | 12 | 2016-04-05 | 2016-04-12 | 6 | 0 | 6 | [15 empty] | 2016-04-13 |  | not supplied |  | EXP | [9 empty] | cancelled
WMECO | Whately | 6A1481-2015 | 01093 | 2000 | Solar | 18G8 | 2015-10-15 | 2015-12-11 | 42 | 5 | 37 | 2015-12-14 |  | -30217 | [24 empty] | Summer 2016 |  | STD | [9 empty] | Cancelled by applicant
WMECO | Springfield | 6S1680-2015 | 01128 | 600 | Diesel | 20A34 | 2015-10-15 | 2016-01-20 | 70 | 11 | 59 | 2016-01-21 | 2016-04-14 | 61 | 49 | 12 | 2016-04-15 | 2016-09-08 | 105 | 10 | 95 | [15 empty] | 2016-09-09 |  |  |  | EXP | [8 empty] | 2018-04-25
WMECO | Agawam | 6S1687-2015 | 01001 | 999 | Solar | 30A3 | 2015-10-19 | 2015-12-07 | 36 | 2 | 34 | 2015-12-08 |  | -30213 | [26 empty] | STD | [9 empty] | Cancelled by applicant
WMECO | Agawam | 6S1697-2015 | 01001 | 500 | Solar | 16C16 | 2015-10-21 | 2015-12-22 | 45 | 41 | 4 | 2015-12-23 | 2016-04-22 | 88 | 40 | 48 | [10 empty] | 2016-04-25 | 2016-08-15 | 81 | 0 | 81 | [7 empty] | 2016-08-11 |  | STD | [9 empty] | cancelled by applicant, never executed Detailed Study Agreement
WMECO | Ludlow | 6S1698-2015 | 01056 | 311 | Solar | 19S2 | 2015-10-21 | 2015-12-02 | 31 | 5 | 26 | 2015-12-03 | 2016-02-18 | 56 | 43 | 13 | [10 empty] | 2016-02-19 | 2016-05-11 | 59 | 0 | 59 | [5 empty] | 2016-05-11 |  | 2016-08-11 |  | STD | [9 empty] | part of group, negotiated timeline due to timing ot submitted option, cancelled by applicant
WMECO | Agawam | 6S1699-2015 | 01001 | 500 | Solar | 16C16 | 2015-10-21 | 2016-01-20 | 66 | 1 | 65 | 2016-01-21 | 2016-04-22 | 67 | 40 | 27 | [10 empty] | 2016-04-25 | 2016-08-15 | 81 | 0 | 81 | [7 empty] | 2016-08-11 |  | STD | [9 empty] | cancelled by applicant, never executed Detailed Study Agreement
WMECO | Ludlow | 6S1797-2015 | 01056 | 16.7 | Solar | 19S1 | 2015-10-27 | [31 empty] | 2015-11-20 |  | EXP | [9 empty] | withdrawn
WMECO | Buckland | 6F1201-2015 | 01338 | 16.7 | Solar | 38A1 | 2015-10-28 | 2015-11-30 | 24 | 18 | 6 | 2015-12-01 | 2015-12-15 | 11 | 5 | 6 | [20 empty] | 2015-12-15 |  | not supplied |  | EXP | [6 empty] | 2016-03-07 | 2016-03-09 | 2016-03-09
WMECO | Montague | 6F1203-2015 | 01351 | 408 | Solar | 21C3 | 2015-10-28 | 2016-01-27 | 66 | 3 | 63 | 2016-01-28 | 2016-06-10 | 97 | 35 | 62 | [10 empty] | 2016-06-13 | 2016-08-24 | 53 |  | 53 | [7 empty] | June 2016 |  | STD | [9 empty] | Part of group study. One applicant cancelled their project so group changed. Applicant cancelled this project.
WMECO | Springfield | 6S1730-2015 | 01108 | 299.16 | Solar | 22H17 | 2015-10-29 | 2016-03-08 | 94 | 28 | 66 | 2016-03-09 |  | -30279 | [24 empty] | 2015-03-01 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Montague | 6F1208-2015 | 01351 | 1992 | Solar | 21C3 | 2015-10-30 | 2016-01-27 | 64 | 1 | 63 | 2016-01-28 | 2016-06-10 | 97 | 35 | 62 | [10 empty] | 2016-06-13 | 2016-08-24 | 53 | 0 | 53 | [7 empty] | June 2016 |  | STD | [9 empty] | Part of group study. One applicant cancelled their project so group changed. Applicant cancelled this project.
WMECO | Montague | 6F1209-2015 | 01351 | 4176 | Solar | 21C2 | 2015-10-30 | 2016-02-16 | 78 | 11 | 67 | 2016-02-17 | 2016-06-10 | 83 | 35 | 48 | [10 empty] | 2016-06-13 | 2016-08-24 | 53 | 0 | 53 | 2016-11-08 |  | -30453 |  |  | 2016-09-23 |  | June 2016 |  | COMP | [8 empty] | 2018-09-24 | Part of group study. One applicant cancelled their project so group changed. Customer submitted new option. Negotiated 10 days for review. Other two applicants cancelled their projects after the group Impact Study. Projetc to be 3rd party owned as of April 2017
WMECO | Ashfield | 6F1210-2015 | 01330 | 45.6 | Solar | 38A1 | 2015-11-02 | 2015-11-19 | 14 | 7 | 7 | 2015-11-20 | 2016-01-19 | 43 | 17 | 26 | 2016-01-20 | 2016-01-29 | 8 | 0 | 8 | [15 empty] | 2016-02-03 |  | Nov 2015 |  | EXP | [6 empty] | 2016-05-26 | 2016-05-27 | 2016-05-27
WMECO | Longmeadow | 6S1804-2015 | 01106 | 18 | Solar | 22H17 | 2015-11-03 | 2015-12-15 | 31 | 12 | 19 | 2015-12-15 | 2015-12-17 | 3 | 2 | 1 | [20 empty] | 2015-12-17 |  | 2015-12-26 |  | EXP | [6 empty] | 2016-06-20 | 2016-06-27 | 2016-06-27
WMECO | Southwick | 6S1756-2015 | 01077 | 478 | Solar | 29A5 | 2015-11-06 | 2016-01-20 | 54 | 21 | 33 | 2016-01-20 | 2016-03-18 | 43 | 40 | 3 | [10 empty] | 2016-03-21 | 2016-08-22 | 111 | 0 | 111 | [5 empty] | 2016-08-22 |  | 2016-02-03 |  | COMP | [9 empty] | cancelled by applicant
WMECO | West Hatfield | 6A1528-2015 | 01088 | 292 | Solar | 18G5 | 2015-11-09 | 2015-12-22 | 32 | 12 | 20 | 2015-12-23 |  | -30224 | [24 empty] | 2015-03-15 |  | STD | [9 empty] | On hold behind 6A935-2014. In group with 6A1468-2015. Applicant cancelled.
WMECO | Plainfield | 6F1233-2015 | 01070 | 22.8 | Solar | 18K3 | 2015-11-10 | 2015-11-23 | 10 | 4 | 6 | 2015-11-24 | 2015-12-15 | 16 | 4 | 12 | [20 empty] | 2015-12-15 |  | Nov 2015 |  | EXP | [6 empty] | 2016-04-01 | 2016-04-05 | 2016-04-05
WMECO | Otis | 6B789-2015 | 01253 | 2000 | Solar | 19J4 | 2015-11-13 | 2016-02-02 | 58 | 7 | 51 | 2016-02-03 |  | -30254 | [24 empty] | 2016-07-15 |  | STD | [9 empty] | withdrawn after no response to email notices and voice mails
WMECO | Feeding Hills | 6S1795-2015 | 01030 | 15.3 | Solar | 16C17 | 2015-11-13 | 2015-12-04 | 16 | 8 | 8 | 2015-12-07 | 2015-12-10 | 4 | 0 | 4 | [20 empty] | 2016-01-08 |  | 2016-01-13 |  | EXP | [6 empty] | 2016-03-23 | 2016-04-11 | 2016-04-11
WMECO | South Deerfield | 6F1241-2015 | 01373 | 1992 | Solar | 18G3 | 2015-11-16 | 2015-12-14 | 21 | 1 | 20 | 2015-12-15 |  | -30218 | [24 empty] | Spring 2016 |  | STD | [9 empty] | Cancelled by applicant
WMECO | South Deerfield | 6F1242-2015 | 01373 | 1992 | Solar | 18G3 | 2015-11-16 | 2015-12-14 | 21 | 1 | 20 | 2015-12-15 |  | -30218 | [24 empty] | Spring 2016 |  | STD | [9 empty] | Cancelled by applicant
WMECO | Springfield | 6S1796-2015 | 01104 | 1985 | Solar | 5J18 | 2015-11-16 | 2015-12-21 | 26 | 1 | 25 | 2015-12-22 | 2016-02-23 | 46 | 17 | 29 | [10 empty] | 2016-02-24 | 2016-05-02 | 49 | 0 | 49 | 2016-05-12 |  | -30325 | 7 |  | 2016-05-02 |  | 2016-05-31 |  | STD | [6 empty] | 2017-06-19 | 2017-06-26 | 2017-06-26
WMECO | Hadley | 6A1553-2015 | 01035 | 570 | Biogas | 19B15 | 2015-11-20 | 2016-02-24 | 69 | 63 | 6 | 2016-02-25 | 2016-04-20 | 40 | 36 | 4 | [10 empty] | 2016-04-21 | 2016-07-11 | 58 | 45 | 13 | 2016-08-22 |  | -30397 |  |  | 2016-08-17 |  | 4/30/2016 |  | STD | [6 empty] | 2017-06-30 | 2017-07-13 | 2017-07-13 | On hold behind a group impact study through 4/19/16.
WMECO | Whately | 6A1560-2015 | 01093 | 504 | Solar | 18G8 | 2015-11-24 | 2015-12-16 | 17 | 3 | 14 | 2015-12-17 | 2016-04-28 | 96 | 51 | 45 | [10 empty] | 2016-04-29 | 2016-08-31 | 89 |  | 89 | [7 empty] | March 2016 |  | STD | [9 empty] | Group changed, new study agreement sent out. Application cancelled by applicant.
WMECO | Pittsfield | 6B807-2015 | 01201 | 72 | Solar | 19A7 | 2015-12-01 | 2016-01-06 | 27 | 5 | 22 | 2016-01-07 | 2016-02-10 | 25 | 11 | 14 | [20 empty] | 2016-02-10 |  | 1st qtr 2016 |  | EXP | [6 empty] | 2016-05-20 | 2016-05-24 | 2016-05-24
WMECO | Whately | 6A1570-2015 | 01093 | 2000 | Solar | 18G8 | 2015-12-02 | 2015-12-11 | 8 | 0 | 8 | 2015-12-14 | 2016-04-28 | 99 | 51 | 48 | [10 empty] | 2016-04-29 | 2016-08-31 | 89 | 7 | 82 | 2016-10-31 |  | -30447 |  |  | 2016-10-03 |  | Sept 2016 |  | STD | [8 empty] | 2019-12-20 | on line
WMECO | Lee | 6B809-2015 | 01238 | 2000 | Solar | 16B5 | 2015-12-03 | 2016-02-11 | 51 | 9 | 42 | 2016-02-12 | 2016-04-04 | 37 | 12 | 25 | [10 empty] | 2016-04-05 | 2016-08-05 | 89 | 73 | 16 | [7 empty] | 2016-08-01 |  | STD | [9 empty] | IC requested 55 day extension in I.S., extension granted, study increases by 18 days in length. Impact Study report sent out. Cust ext - need to send out Detailed Study agreement, waiting for information. Application withdrawn after applicant did not move forward.
WMECO | South Deerfield | 6F1262-2015 | 01373 | 452 | Solar | 15E1 | 2015-12-04 | 2016-02-02 | 43 | 2 | 41 | 2016-02-03 |  | -30254 | [24 empty] | 2016-03-31 |  | STD | [9 empty] | cancelled by IC, had sent notice that they missed deadline to execute Impact Study Agreement
WMECO | Easthampton | 6A1578-2015 | 01027 | 496 | Solar | 15A2 | 2015-12-09 | 2016-01-28 | 37 | 25 | 12 | 2016-01-29 | 2016-06-03 | 91 | 49 | 42 | [10 empty] | 2016-06-06 | 2016-09-23 | 80 | 0 | 80 | [5 empty] | 2016-09-23 |  | June 2016 |  | COMP | [9 empty] | Group changed, first applicant dropped out, another project was added. Sent Detailed Study Agreement, reminder to execute agreement, sent 10 day notice. No response from applicant, called them and they thought they would cancel their application. No response so withdrew application.
WMECO | Indian Orchard | 6S1915-2015 | 01151 | 1931.4 | Solar | 27A12 | 2015-12-15 | 2016-02-10 | 42 | 18 | 24 | 2016-02-11 | 2016-03-17 | 26 | 12 | 14 | [10 empty] | 2016-03-18 | 2016-08-08 | 102 | 17 | 85 | [5 empty] | 2016-08-12 |  | 2015-08-01 |  | STD | [6 empty] | 2017-02-10 | 2017-02-16 | 2017-02-16 | applicant submitted a third option, revised study, had to do a second Witness Test
WMECO | Hadley | 6A1588-2015 | 01035 | 1995.4 | Solar | 17K6 | 2015-12-16 | 2016-04-15 | 88 | 42 | 46 | 2016-04-19 | 2016-08-12 | 84 | 51 | 33 | [10 empty] | 2016-08-15 | 2016-12-01 | 79 | 0 | 79 | 2017-01-05 |  | -30495 |  |  | 2017-04-14 |  | Sept 2016 |  | COMP | [8 empty] | 2020-01-16 | on line
WMECO | Hadley | 6A1589-2015 | 01035 | 1995.4 | Solar | 17K1 | 2015-12-16 | 2016-04-15 | 88 | 42 | 46 | 2016-04-19 | 2016-08-12 | 84 | 51 | 33 | [10 empty] | 2016-08-15 | 2017-01-27 | 120 | 24 | 96 | 2017-02-21 |  | -30528 |  |  | 2017-04-14 |  | Sept 2016 |  | COMP | [8 empty] | 2020-01-16 | on line
WMECO | Amherst | 6A1599-2015 | 01002 | 19.3 | Solar | 17K8 | 2015-12-16 | 2016-01-21 | 27 | 13 | 14 | 2016-01-21 | 2016-02-08 | 13 | 9 | 4 | [20 empty] | 2016-02-08 |  | 02/16/2016 |  | EXP | [6 empty] | 2016-11-30 | 2016-12-01 | 2016-12-01
WMECO | Hinsdale | 6B826-2015 | 01235 | 1988 | Solar | 18C2 | 2015-12-16 | 2016-02-23 | 50 | 16 | 34 | 2016-02-24 | 2016-06-10 | 78 | 37 | 41 | [10 empty] | 2016-06-13 | 2016-08-10 | 43 | 0 | 43 | 2016-09-09 |  | -30411 |  |  | 2016-08-19 |  | 2015-09-01 |  | STD | [6 empty] | 2017-11-17 | 2017-11-20 | 2017-11-21 | Negotiated timeline, 20 days for review, customer submitted second option after already deemed complete. In group, group changed, second study agreement sent out. 5/17/16 group changed again. JEversource field checked the installed equipment prior to the Witness Test. Customer performed his own Witness Test and sent certified info.
WMECO | Amherst | 6A1600-2015 | 01006 | 16.7 | Solar | 18G7 | 2015-12-18 | 2016-01-07 | 15 | 8 | 7 | 2016-01-08 | 2016-02-10 | 24 | 21 | 3 | 2016-02-11 | 2016-02-28 | 12 | 0 | 12 | [15 empty] | 2016-02-29 |  |  |  | EXP | [9 empty] | cancelled by customer
WMECO | Feeding Hills | 6S1953-2015 | 01030 | 16.4 | Solar | 16C17 | 2015-12-23 | 2016-01-06 | 11 | 1 | 10 | 2016-01-06 | 2016-01-06 | 1 | 0 | 1 | [20 empty] | 2016-02-01 |  | 2016-02-16 |  | EXP | [6 empty] | 2016-08-15 | 2016-08-23 | 2016-08-23
WMECO | Middlefield | 6F1294-2015 | 01243 | 32.85 | Solar | 18C2 | 2015-12-24 | 2016-01-19 | 19 | 7 | 12 | 2016-01-19 | 2016-07-15 | 129 | 98 | 31 | [20 empty] | 2016-07-15 |  | 2015-12-31 |  | EXP | [6 empty] | 2016-09-07 | 2016-09-13 | 2016-09-13
WMECO | Amherst | 6A1612-2015 | 01003 | 154 | Solar | 18G2 | 2015-12-28 | 2016-01-12 | 12 | 6 | 6 | 2016-01-13 | 2016-03-02 | 36 | 33 | 3 | 2016-03-03 | 2016-04-21 | 36 | 2 | 34 | [15 empty] | 2016-04-22 |  |  |  | EXP | [9 empty] | cancelled by customer
WMECO | Springfield | 6S1979-2015 | 01129 | 343 | Solar | 20A23 | 2015-12-28 | 2016-01-28 | 24 | 20 | 4 | 2016-01-29 |  | -30251 | [26 empty] | STD | [9 empty] | withdrawn after sending 10 day notice that Impact Study was not executed. Called IC who said they were not sure if or when the customer would decide to install generation.
WMECO | Feeding Hills | 6S1978-2015 | 01030 | 20.925 | Solar | 16C17 | 2015-12-29 | 2016-01-20 | 17 | 9 | 8 | 2016-01-21 | 2016-02-17 | 20 | 17 | 3 | 2016-02-18 |  | -30265 | [21 empty] | EXP | [9 empty] | cancelled
WMECO | Pittsfield | 6B851-2016 | 01201 | 1000 | Solar | 30B7 | 2016-01-04 | 2016-04-14 | 74 | 38 | 36 | 2016-04-15 | 2016-05-16 | 22 | 13 | 9 | [10 empty] | 2016-05-17 | 2016-08-10 | 62 | 0 | 62 | 2016-08-31 |  | -30404 |  |  | 2016-08-15 |  | not supplied |  | STD | [8 empty] | 2017-11-20 | Was on hold behind first group study on circuit.
WMECO | Hancock | 6B852-2016 | 01237 | 2000 | Solar | 30B7 | 2016-01-04 | 2016-04-14 | 74 | 38 | 36 | 2016-04-15 | 2016-05-16 | 22 | 13 | 9 | [10 empty] | 2016-05-17 | 2016-08-10 | 62 | 0 | 62 | 2016-08-31 |  | -30404 |  |  | 2016-08-15 |  | not supplied |  | STD | [8 empty] | 2017-11-20 | Was on hold behind first group study on circuit.
WMECO | Hancock | 6B853-2016 | 01201 | 2000 | Solar | 30B7 | 2016-01-04 | 2016-04-14 | 74 | 38 | 36 | 2016-04-15 | 2016-05-16 | 22 | 13 | 9 | [10 empty] | 2016-05-17 | 2016-08-10 | 62 | 0 | 62 | 2016-08-31 |  | -30404 |  |  | 2016-08-15 |  | not supplied |  | STD | [8 empty] | 2017-11-20 | Was on hold behind first group study on circuit.
WMECO | Southwick | 6S1998-2016 | 01077 | 16.7 | Solar | 29A5 | 2016-01-05 | 2016-01-08 | 4 | 2 | 2 | 2016-01-08 |  | -30236 | [24 empty] | 2016-03-04 |  | EXP | [9 empty] | withdrawn after multiple requsts for response
WMECO | Amherst | 6A1621-2016 | 01002 | 17 | Solar | 19B16 | 2016-01-07 | 2016-01-22 | 12 | 6 | 6 | 2016-01-23 | 2016-02-09 | 12 | 0 | 12 | [20 empty] | 2016-02-10 |  | 2016-05-01 |  | EXP | [6 empty] | 2016-06-23 | 2016-06-27 | 2016-06-27
WMECO | Amherst | 6A1622-2016 | 01002 | 27 | Solar | 17K5 | 2016-01-07 | 2016-03-02 | 40 | 19 | 21 | 2016-03-02 | 2016-06-13 | 74 | 63 | 11 | [20 empty] | 2016-06-16 |  | not supplied |  | EXP | [6 empty] | 2016-09-08 | 2016-09-21 | 2016-09-21
WMECO | West Springfield | 6S2018-2016 | 01089 | 24 | Solar | 21N9 | 2016-01-08 | 2016-01-14 | 5 | 1 | 4 | 2016-01-14 | 2016-04-04 | 58 | 54 | 4 | 2016-04-05 | 2016-07-19 | 76 | 0 | 76 | [15 empty] | 2016-08-04 |  | 2016-03-07 |  | EXP | [6 empty] | 2017-01-04 | 2017-01-06 | 2017-01-06
WMECO | Whately | 6A1625-2016 | 01093 | 16.7 | Solar | 18G8 | 2016-01-12 | 2016-01-20 | 7 | 1 | 6 | 2016-01-20 | 2016-02-09 | 15 | 9 | 6 | [20 empty] | 2016-02-11 |  | not supplied |  | EXP | [9 empty] | cancelled by customer
WMECO | Dalton | 6B864-2016 | 01226 | 495.28 | Solar | 19A3 | 2016-01-12 | 2016-07-01 | 124 | 92 | 32 | 2016-07-05 |  | -30363 | [24 empty] | 2016-09-01 |  | STD | [9 empty] | cancelled by applicant
WMECO | Springfield | 6S2043-2016 | 01109 | 16.7 | Solar | 20A32 | 2016-01-19 | 2016-02-09 | 16 | 7 | 9 | 2016-02-09 | 2016-02-29 | 15 | 10 | 5 | [20 empty] | 2016-03-18 |  | 2016-02-02 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Springfield | 6S2044-2016 | 01118 | 14.35 | Solar | 20A32 | 2016-01-19 | [31 empty] | 2016-02-02 |  | EXP | [9 empty] | Cancelled by applicant
WMECO | Longmeadow | 6S2053-2016 | 01106 | 16.7 | Solar | 22H12 | 2016-01-19 | 2016-02-09 | 16 | 7 | 9 | 2016-02-09 | 2016-02-17 | 7 | 5 | 2 | [20 empty] | 2016-02-19 |  | 2016-02-04 |  | EXP | [6 empty] | 2016-04-21 | 2016-04-25 | 2016-04-25
WMECO | Amherst | 6A1637-2016 | 01002 | 99 | Solar | 19B15 | 2016-01-20 | 2016-01-27 | 6 | 4 | 2 | 2016-01-28 | 2016-02-23 | 19 | 0 | 19 | [20 empty] | 2016-02-23 |  | Feb 2016 |  | EXP | [6 empty] | 2016-06-15 | 2016-06-16 | 2016-06-16
WMECO | Agawam | 6S2068-2016 | 01001 | 45 | Solar | 16C16 | 2016-01-22 | 2016-02-11 | 15 | 9 | 6 | 2016-02-11 | 2016-02-18 | 6 | 3 | 3 | [20 empty] | 2016-02-22 |  | 2016-03-15 |  | EXP | [8 empty] | 2016-09-20 | on line
WMECO | Whately | 6A1647-2016 | 01093 | 1992 | Solar | 18G8 | 2016-01-27 | 2016-02-04 | 7 | 1 | 6 | 2016-02-05 |  | -30256 | [24 empty] | Summer 2016 |  | STD | [9 empty] | Cancelled by Interconnecting Customer because SREC program ended.
WMECO | Whately | 6A1652-2016 | 01093 | 1548 | Solar | 18G8 | 2016-01-29 | [31 empty] | Summer 2016 |  | EXP | [9 empty] | withdrawn
WMECO | Springfield | 6S2094-2016 | 01104 | 140 | Solar | 5J11 | 2016-02-02 | 2017-02-13 | 270 | 223 | 47 | 2017-02-14 |  | -30523 | [24 empty] | 3/16 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Agawam | 6S2095-2016 | 01001 | 250 | Solar | 30A6 | 2016-02-02 | 2016-09-08 | 158 | 149 | 9 | 2016-09-09 | 2017-01-27 | 101 | 88 | 13 | 2017-01-30 | 2017-03-01 | 23 | 0 | 23 | [17 empty] | 3/16 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Pittsfield | 6B887-2016 | 01201 | 625.8 | Solar | 30B7 | 2016-02-03 | 2016-03-08 | 25 | 9 | 16 | 2016-03-09 | 2016-05-16 | 49 | 13 | 36 | [10 empty] | 2016-05-17 | 2016-08-10 | 62 | 0 | 62 | 2016-08-31 |  | -30404 |  |  | 2016-08-16 |  | 2016-04-01 |  | STD | [6 empty] | 2017-11-28 | 2017-12-01 | 2017-12-18 | Was on hold behind first group study on circuit.
WMECO | Westhampton | 6A1661-2016 | 01027 | 566.1 | Solar | 15A3 | 2016-02-04 | 2016-04-05 | 44 | 21 | 23 | 2016-04-06 | 2016-07-22 | 78 | 71 | 7 | [10 empty] | 2016-07-25 | 2016-10-07 | 55 |  | 55 | [7 empty] | 2016-04-01 |  | STD | [9 empty] | On hold behind 6A1251, formed froup with 6A1251, 6A1251 cancelled so removed from group. Cancelled by applicant. Had two 10 day extensions..
WMECO | Whately | 6A1662-2016 | 01093 | 8.35 | Solar | 18G6 | 2016-02-04 | 2016-04-11 | 48 | 44 | 4 | 2016-04-11 | 2016-05-04 | 18 | 16 | 2 | 2016-05-05 |  | -30320 | [19 empty] | 2016-04-03 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Pittsfield | 6B896-2016 | 01201 | 390 | Solar | 19A7 | 2016-02-10 | 2016-05-03 | 60 | 23 | 37 | 2016-05-04 |  | -30319 | [24 empty] | not supplied |  | STD | [9 empty] | cancelled by applicant 7/13/16, decided not to proceed, never executed group study agreement
WMECO | Amherst | 6A1697-2015 | 01002 | 22.7 | Solar | 18G7 | 2016-02-22 | 2016-03-10 | 14 | 10 | 4 | 2016-03-10 |  | -30280 | [24 empty] | 2016-03-15 |  | EXP | [9 empty] | Sent Supplemental Review 3/10/16. Int Cust/Cust did not submit executed agreement or respond to notices. Withdrawn after no response.
WMECO | Sunderland | 6A1704-2016 | 01375 | 288 | Solar | 18G3 | 2016-02-23 | 2016-05-04 | 52 | 44 | 8 | 2016-05-05 |  | -30320 | [24 empty] | 2016-05-31 |  | STD | [9 empty] | cancelled by customer
WMECO | Sunderland | 6A1708-2016 | 01375 | 22.5 | Solar | 18G8 | 2016-02-23 | 2016-04-13 | 37 | 6 | 31 | 2016-04-13 | 2016-04-14 | 2 | 1 | 1 | [20 empty] | 2016-04-15 |  | not supplied |  | EXP | [6 empty] | 2016-06-08 | 2016-06-09 | 2016-06-09
WMECO | South Deerfield | 6F1389-2016 | 01373 | 1000 | Biogas | 22B1 | 2016-02-25 | 2016-04-13 | 35 | 12 | 23 | 2016-04-14 | 2016-07-01 | 57 | 20 | 37 | [10 empty] | 2016-07-05 | 2016-10-06 | 68 | 0 | 68 | 2016-10-19 |  | -30439 |  |  | 2016-10-12 |  | 6/20/16 |  | COMP | [6 empty] | 2017-12-06 | 2017-12-11 | 2017-12-11 | applicant submitted design change after complete, negotiated timeline to re do steps, second Impact Study Agreement sent
WMECO | Otis | 6B923-2016 | 01253 | 40.75 | Solar | 19J4 | 2016-03-01 | [31 empty] | 2016-05-02 |  | EXP | [9 empty] | Application withdrawn after calls and email notices that application was not complete and deadlines were missed.
WMECO | Hadley | 6A1736-2016 | 01035 | 16.4 | Solar | 18G4 | 2016-03-03 | 2016-03-10 | 6 | 2 | 4 | 2016-03-10 |  | -30280 | [24 empty] | 2016-05-03 |  | EXP | [9 empty] | Cancelled by applicant
WMECO | Buckland | 6F1417-2016 | 01338 | 25.425 | Solar | 38A1 | 2016-03-04 | 2016-06-27 | 82 | 74 | 8 | 2016-06-27 |  | -30357 | [24 empty] | 2016-04-15 |  | EXP | [9 empty] | Application withdrawn after no response to multiple requests for status and Supplemental Review Agreement was not executed.
WMECO | Agawam | 6S2185-2016 | 01001 | 22.95 | Solar | 16C17 | 2016-03-04 | 2016-03-21 | 12 | 3 | 9 | 2016-03-21 | 2016-03-28 | 6 | 5 | 1 | 2016-03-29 |  | -30293 | [19 empty] | 2016-04-29 |  | EXP | [9 empty] | installer cancelled application due to changs in SREC program
WMECO | Amherst | 6A1743-2016 | 01002 | 19.75 | Solar | 18G4 | 2016-03-07 | 2016-03-14 | 6 | 5 | 1 | 2016-03-15 |  | -30283 | 15 | [23 empty] | Q2 2016 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Agawam | 6S2199-2016 | 01001 | 22.95 | Solar | 16C17 | 2016-03-08 | [31 empty] | 2016-04-30 |  | EXP | [9 empty] | installer cancelled application due to changs in SREC program
WMECO | Easthampton | 6A1754-2016 | 01027 | 180 | Solar | 15A2 | 2016-03-09 | 2016-04-15 | 28 | 0 | 28 | 2016-04-19 | 2016-06-03 | 34 | 25 | 9 | [10 empty] | 2016-06-06 | 2016-09-23 | 80 | 0 | 80 | [5 empty] | 2016-09-23 |  | 5/2016 |  | STD | [6 empty] | 2017-03-28 | 2017-04-04 | 2017-04-04 | application added to group, group changed, this app does not need Detailed Study
WMECO | Amherst | 6A1755-2016 | 01002 | 60 | Solar | 17K4 | 2016-03-09 | 2016-04-06 | 21 | 11 | 10 | 2016-04-06 | 2016-04-12 | 5 | 2 | 3 | [20 empty] | 2016-04-13 |  | May 2016 |  | EXP | [6 empty] | 2016-10-04 | 2016-10-06 | 2016-10-06
WMECO | Hadley | 6A1766-2016 | 01035 | 84 | Solar | 18G5 | 2016-03-11 | 2016-03-21 | 7 | 0 | 7 | 2016-03-21 | 2016-06-20 | 66 | 62 | 4 | 2016-06-21 | 2016-07-18 | 20 | 0 | 20 | [15 empty] | 2016-07-19 |  | 3/2016 |  | EXP | [6 empty] | 2017-03-21 | 2017-03-22 | 2017-03-22
WMECO | Southampton | 6A1767-2016 | 01073 | 23.45 | Solar | 15A1 | 2016-03-11 | 2016-04-11 | 22 | 17 | 5 | 2016-04-11 |  | -30302 | [24 empty] | 5/10/16 |  | EXP | [9 empty] | customer cancelled their application
WMECO | Deerfield | 6F1439-2016 | 01342 | 75 | Solar | 22B3 | 2016-03-11 | 2016-08-10 | 109 | 90 | 19 | 2016-08-10 | 2016-11-30 | 81 | 68 | 13 | [20 empty] | 2016-12-05 |  | 5/2016 |  | EXP | [6 empty] | 2017-12-12 | 2017-12-13 | 2018-04-23 | applicant submitted new option 2, negotiated timeline 10 extra days. Witness test performed. Customer requested that project not be given approval to Operate until the tranfer of ownership was completed.
WMECO | Turners Falls | 6F1440-2016 | 01376 | 19.3 | Solar | 21C6 | 2016-03-14 | 2016-03-25 | 10 | 8 | 2 | 2016-03-25 | 2016-03-31 | 5 | 4 | 1 | [20 empty] | 2016-03-31 |  | 2015-11-09 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Hancock | 6B939-2016 | 01237 | 42.25 | Solar | 30B7 | 2016-03-17 | [31 empty] | 2016-05-16 |  | EXP | [9 empty] | withdrawn
WMECO | Deerfield | 6F1449-2016 | 01342 | 64 | Solar | 22B3 | 2016-03-17 | 2016-06-27 | 73 | 56 | 17 | 2016-06-28 | 2016-08-11 | 33 | 26 | 7 | [20 empty] | 2016-08-11 |  | 6/2016 |  | EXP | [6 empty] | 2017-09-22 | 2017-10-04 | 2018-04-25 | negotiated extra time to review second option, 5 extra days. Customer requested that the project not be given approval to operate until the tranfer of onwership is completed
WMECO | Springfield | 6S2233-2016 | 01105 | 16.95 | Solar | 21S11 | 2016-03-17 | 2016-07-26 | 94 | 80 | 14 | 2016-07-26 | 2016-09-16 | 39 | 37 | 2 | 2016-09-19 |  | -30417 | [19 empty] | 2016-05-16 |  | EXP | [9 empty] | two different 15 day extensions granted, requested information from applicant, no responses so withdrew application after no response to 10 day notice
WMECO | Cheshire | 6B947-2016 | 01225 | 16.7 | Solar | 19A5 | 2016-03-18 | 2016-03-30 | 9 | 7 | 2 | 2016-03-30 |  | -30294 | [24 empty] | 2016-04-03 |  | EXP | [9 empty] | withdrawn due to no response to emails or phone calls to IC and installer
WMECO | Southwick | 6S2236-2016 | 01077 | 21.9 | Solar | 29A5 | 2016-03-22 | 2016-04-07 | 13 | 12 | 1 | 2016-04-07 | 2016-04-28 | 16 | 14 | 2 | 2016-04-29 | 2016-05-20 | 16 | 0 | 16 | [15 empty] | 2016-05-26 |  | 2016-06-17 |  | EXP | [6 empty] | 2017-03-06 | 2017-03-09 | 2017-03-09
WMECO | Springfield | 6S2248-2016 | 01109 | 72 | Solar | 5J15 | 2016-03-24 | 2016-04-05 | 9 | 7 | 2 | 2016-04-05 | 2016-05-30 | 40 | 30 | 10 | [20 empty] | 2016-06-01 |  | July 2015 |  | EXP | [6 empty] | 2017-03-31 | 2017-04-05 | 2017-04-05
WMECO | West Springfield | 6S2264-2016 | 01089 | 16.4 | Solar | 21N4 | 2016-03-29 | 2016-04-07 | 8 | 7 | 1 | 2016-04-07 |  | -30300 | [24 empty] | not supplied |  | EXP | [9 empty] | Applicant requested an extension 5/19/16, extension granted to 6/10/16. No response from calls and emails so withdrawn.
WMECO | Lanesborough | 6B960-2016 | 01201 | 21.9 | Solar | 15E2 | 2016-04-05 | 2016-05-03 | 21 | 18 | 3 | 2016-05-03 | 2016-07-12 | 51 | 39 | 12 | 2016-07-13 |  | -30369 | [19 empty] | 2016-04-23 |  | EXP | [9 empty] | applicant requested an extension, 5 days, cancelled by applicant
WMECO | Lanesborough | 6B973-2016 | 01237 | 16.4 | Solar | 15E1 | 2016-04-11 | 2016-04-19 | 7 | 5 | 2 | 2016-04-19 | 2016-05-09 | 15 | 14 | 1 | 2016-05-10 | 2016-05-10 | 1 | 0 | 1 | [15 empty] | 2016-05-16 |  | 2016-05-04 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Agawam | 6S2294-2016 | 01001 | 45.9 | Solar | 16C17 | 2016-04-11 | 2016-05-03 | 17 | 13 | 4 | 2016-05-03 | 2016-05-11 | 7 | 6 | 1 | 2016-05-12 | 2016-05-18 | 5 | 0 | 5 | [15 empty] | 2016-05-27 |  | 2016-05-28 |  | EXP | [8 empty] | 2016-07-27
WMECO | Agawam | 6S2295-2016 | 01001 | 46.8 | Solar | 16C18 | 2016-04-11 | 2016-05-03 | 17 | 14 | 3 | 2016-05-03 | 2016-05-03 | 1 | 0 | 1 | [20 empty] | 2016-05-05 |  | 2016-05-28 |  | EXP | [6 empty] | 2016-08-09 | 2016-08-11 | 2016-08-11
WMECO | Montague | 6F1484-2016 | 01351 | 18 | Solar | 21C7 | 2016-04-12 | 2016-04-25 | 10 | 8 | 2 | 2016-04-25 |  | -30312 | [24 empty] | July 2016 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Montague | 6F1485-2016 | 01351 | 56.35 | Solar | 21C7 | 2016-04-12 | 2016-04-25 | 10 | 8 | 2 | 2016-04-25 | 2016-05-20 | 20 | 18 | 2 | [20 empty] | 2016-05-26 |  | July 2016 |  | EXP | [6 empty] | 2017-01-18 | 2017-01-26 | 2017-01-26 | failed first Witness Test, rescheduled nd passed second WT
WMECO | Southwick | 6S2301-2016 | 01077 | 2000 | Solar | 29A3 | 2016-04-13 | 2016-06-01 | 36 | 23 | 13 | 2016-06-02 | 2017-05-03 | 240 | 217 | 23 | [10 empty] | 2017-05-04 | 2017-09-19 | 99 | 15 | 84 | 2017-10-28 |  | -30706 |  |  | 2017-10-05 |  | Spring 2017 |  | COMP | [8 empty] | 2018-12-20 | on line
WMECO | Southwick | 6S2303-2016 | 01077 | 2000 | Solar | 29A3 | 2016-04-13 | 2016-06-01 | 36 | 23 | 13 | 2016-06-02 | 2017-05-03 | 240 | 217 | 23 | [10 empty] | 2017-05-04 | 2017-09-19 | 99 | 15 | 84 | 2017-10-28 |  | -30706 |  |  | 2017-10-05 |  | Spring 2017 |  | STD | [8 empty] | 2018-12-20 | on line
WMECO | West Springfield | 6S2305-2016 | 01089 | 12 | Solar | 21N6 | 2016-04-14 | 2016-04-20 | 5 | 3 | 2 | 2016-04-20 |  | -30309 | [24 empty] | 2016-08-07 |  | EXP | [9 empty] | withdrawn
WMECO | Ludlow | 6S2314-2016 | 01056 | 16.7 | Solar | 19S3 | 2016-04-18 | 2016-05-09 | 16 | 14 | 2 | 2016-05-09 |  | -30322 | [24 empty] | 2016-06-18 |  | EXP | [9 empty] | withdrawn after no response to calls and emails and missed timelines
WMECO | Ludlow | 6S2347-2016 | 01056 | 12 | Solar | 19S1 | 2016-04-28 | [31 empty] | 2016-05-25 |  | EXP | [9 empty] | cancelled
WMECO | Pittsfield | 6B996-2016 | 01201 | 1476 | Solar | 30B7 | 2016-05-02 | 2016-05-24 | 17 | 6 | 11 | 2016-05-25 |  | -30334 | [24 empty] | 2016-11-01 |  | STD | [9 empty] | Application on hold behind behind a group study on 30B7 circuit. Negotiated 10 days extra. Customer also requested 10 day extension. Applicant did not execute Impact Study Agreement. Applicant cancelled application.
WMECO | Southwick | 6S2367-2016 | 01077 | 16.7 | Solar | 29A5 | 2016-05-04 | 2016-05-16 | 9 | 8 | 1 | 2016-05-16 | 2016-06-15 | 23 | 21 | 2 | 2016-06-16 | 2016-06-22 | 5 | 0 | 5 | [15 empty] | 2016-06-23 |  | 2016-03-04 |  | EXP | [6 empty] | 2016-11-08 | 2016-11-14 | 2016-11-14
WMECO | Springfield | 6S2368-2016 | 01119 | 152 | Solar | 27A7 | 2016-05-04 | 2016-05-16 | 9 | 1 | 8 | 2016-05-17 | 2016-07-07 | 38 | 18 | 20 | 2016-07-08 | 2016-08-02 | 18 | 0 | 18 | [15 empty] | 2016-08-09 |  | Aug 2016 |  | EXP | [6 empty] | 2017-02-07 | 2017-02-10 | 2017-02-10
WMECO | Hancock | 6B1002-2016 | 01237 | 42.25 | Solar | 30B7 | 2016-05-05 | 2016-09-15 | 96 | 77 | 19 | 2016-09-15 |  | #VALUE! | 42 | #VALUE! | [22 empty] | 2016-05-16 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Dalton | 6B1014-2016 | 01226 | 16.15 | Solar | 18C1 | 2016-05-10 | 2016-05-19 | 8 | 3 | 5 | 2016-05-19 | 2016-06-09 | 16 | 14 | 2 | 2016-06-10 | 2016-07-13 | 24 | 0 | 24 | [15 empty] | 2016-07-14 |  | 2016-07-03 |  | EXP | [6 empty] | 2016-12-07 | 2016-12-13 | 2016-12-13
WMECO | Montague | 6F1500-2016 | 01351 | 36 | Solar | 21C7 | 2016-05-10 | 2016-06-15 | 27 | 22 | 5 | 2016-06-15 | 2016-07-11 | 19 | 16 | 3 | 2016-07-12 | 2016-09-26 | 55 | 17 | 38 | [15 empty] | 2016-09-29 |  | 2016-08-01 |  | EXP | [6 empty] | 2017-06-09 | 2017-06-21 | 2017-11-10
WMECO | Plainfield | 6F1513-2016 | 01070 | 17.5 | Solar | 18K3 | 2016-05-25 | [31 empty] | not supplied |  | EXP | [9 empty] | cancelled
WMECO | Lee | 6B1034-2016 | 01238 | 36 | Solar | 16B5 | 2016-05-26 | 2016-08-05 | 52 | 48 | 4 | 2016-08-05 | 2016-08-29 | 17 | 7 | 10 | [20 empty] | 2016-08-30 |  | Not supplied |  | EXP | [6 empty] | 2017-01-17 | 2017-01-19 | 2017-01-20
WMECO | Turners Falls | 6F1515-2016 | 01376 | 1160 | Solar | 21C8 | 2016-05-27 | 2016-06-28 | 23 | 15 | 8 | 2016-06-29 | 2016-07-22 | 18 | 6 | 12 | [10 empty] | 2016-07-25 | 2016-10-06 | 54 | 0 | 54 | [7 empty] | 2016-10-01 |  | STD | [9 empty] | Negotiated 20 extra days. Applicant not sure if they will proceed. Withdrawn after notices and no response.
WMECO | Southwick | 6S2463-2016 | 01077 | 15.75 | Solar | 29A5 | 2016-05-31 | 2016-06-23 | 18 | 14 | 4 | 2016-06-23 | 2016-07-07 | 11 | 9 | 2 | [20 empty] | 2016-07-14 |  | 2016-06-15 |  | EXP | [6 empty] | 2016-11-28 | 2016-11-29 | 2016-11-29
WMECO | Pittsfield | 6B1040-2016 | 01201 | 60 | Solar | 30B7 | 2016-06-01 | 2016-07-20 | 36 | 32 | 4 | 2016-07-20 | 2016-11-02 | 76 | 48 | 28 | [20 empty] | 2016-11-02 |  | Sept 2016 |  | EXP | [6 empty] | 2017-04-04 | 2017-04-06 | 2017-04-06 | Sent Supplemental Review Agreement. Applicant submitted new Option 2. Negotiated 10 extra days to review new option.
WMECO | Pittsfield | 6B1047-2016 | 01201 | 166.5 | Solar | 30B3 | 2016-06-08 | 2016-06-30 | 17 | 14 | 3 | 2016-06-30 | 2016-07-19 | 14 | 12 | 2 | 2016-07-19 | 2018-07-13 | 519 | 236 | 283 | [15 empty] | 2018-07-17 |  | Oct 2016 |  | STD | [6 empty] | 2018-08-30 | 2018-08-31 | 2018-09-04 | Sent Impact Study, sent 10 day withdrawal notice, negotiated timeline, 10 days, sent another Impact Study, sent withdrawal notice
WMECO | Amherst | 6A1948-2016 | 01002 | 86.995 | Solar | 18G4 | 2016-06-10 | 2016-06-21 | 8 | 5 | 3 | 2016-06-21 |  | -30353 | [24 empty] | Sept 2016 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Lee | 6B1052-2016 | 01238 | 3328 | Natural Gas | 16B3 | 2016-06-10 | 2016-07-12 | 23 | 6 | 17 | 2016-07-13 | 2016-09-21 | 51 | 37 | 14 | [10 empty] | 2016-09-22 | 2017-03-13 | 123 | 78 | 45 | [7 empty] | Not supplied |  | STD | [9 empty] | cancelled by applicant
WMECO | Pittsfield | 6B1053-2016 | 01201 | 460 | Solar | 19A5 | 2016-06-10 | 2017-01-11 | 154 | 137 | 17 | 2017-01-12 | 2017-03-10 | 42 | 38 | 4 | [10 empty] | 2017-03-13 | 2017-05-18 | 49 | 0 | 49 | [7 empty] | Not supplied |  | COMP | [9 empty] | Negotiated timeline - 10 days to Impact Study. Notice sent, withdrawn after applicant did not execute Detailed Study Agreement.
WMECO | Southampton | 6A1949-2016 | 01073 | 18 | Solar | 15A1 | 2016-06-13 | 2016-07-12 | 22 | 15 | 7 | 2016-07-13 | 2016-09-06 | 40 | 37 | 3 | [20 empty] | 2016-09-13 |  | 8/12 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Pelham | 6A1953-2016 | 01002 | 19.3 | Solar | 17K2 | 2016-06-15 | 2016-07-28 | 32 | 26 | 6 | 2016-07-28 | 2016-08-23 | 19 | 18 | 1 | [20 empty] | 2016-08-29 |  | 2016-08-14 |  | EXP | [6 empty] | 2017-03-02 | 2017-03-07 | 2017-03-07
WMECO | West Springfield | 6S2516-2016 | 01089 | 16.4 | Solar | 21N4 | 2016-06-22 | 2016-07-18 | 19 | 12 | 7 | 2016-07-18 | 2016-09-02 | 35 | 34 | 1 | 2016-09-06 |  | -30408 | [19 empty] | Not supplied |  | EXP | [9 empty] | cancelled by applicant
WMECO | Southampton | 6A1971-2016 | 01073 | 21.9 | Solar | 15A1 | 2016-06-23 | 2016-06-29 | 5 | 2 | 3 | 2016-06-29 | 2016-07-19 | 15 | 13 | 2 | 2016-07-20 |  | -30374 | 2 | [18 empty] | 2016-07-04 |  | EXP | [9 empty] | cancelled by applicant
WMECO | West Springfield | 6S2539-2016 | 01089 | 16.4 | Solar | 21N4 | 2016-06-29 | [31 empty] | Not supplied |  | EXP | [9 empty] | cancelled by applicant
WMECO | Ludlow | 6S2573-2016 | 01056 | 396 | Solar | 27A5 | 2016-07-11 | 2016-08-09 | 22 | 19 | 3 | 2016-08-12 |  | -30391 | [24 empty] | 2016-12-31 |  | STD | [9 empty] | New option submitted 9/29/16. Cancelled by applicants.
WMECO | Southampton | 6A2007-2016 | 01073 | 23.4 | Solar | 15A1 | 2016-07-26 | [31 empty] | 2016-05-26 |  | EXP | [9 empty] | cancelled
WMECO | Otis | 6B1113-2016 | 01253 | 67.6 | Solar | 19J4 | 2016-07-26 | 2016-09-23 | 44 | 38 | 6 | 2016-09-26 | 2016-10-07 | 10 | 8 | 2 | 2016-10-11 |  | -30433 | [19 empty] | Not supplied |  | EXP | [9 empty] | negotiated timeline, 35 extra days for new option, withdrawn after application did not move forward
WMECO | Pittsfield | 6B1127-2016 | 01201 | 1476 | Solar | 30B7 | 2016-08-04 | 2016-08-31 | 20 | 15 | 5 | 2016-09-01 |  | -30405 | [24 empty] | 2016-11-01 |  | EXP | [9 empty] | Applicant granted 10 day extension. Applicant did not execute Supplemental Review Agreement. Applicant cancelled application.
WMECO | Bernardston | 6F1588-2016 | 01337 | 42 | Solar | 21C1 | 2016-08-08 | 2016-08-15 | 6 | 5 | 1 | 2016-08-15 |  | -30392 | [24 empty] | Nov 2016 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Greenfield | 6F1590-2016 | 01301 | 50 | Solar | 21C1 | 2016-08-08 | [31 empty] | August |  | EXP | [9 empty] | two or three options, not complete, withdrawn after missed deadlines
WMECO | Hadley | 6A2032-2016 | 01035 | 25 | Solar | 18G6 | 2016-08-12 | 2016-09-13 | 23 | 12 | 11 | 2016-08-31 |  | -30404 | [24 empty] | 2016-10-28 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Pittsfield | 6B1134-2016 | 01201 | 16.75 | Solar | 19A1 | 2016-08-12 | 2016-09-27 | 33 | 13 | 20 | 2016-09-28 | 2016-09-28 | 1 | 0 | 1 | [20 empty] | 2016-09-29 |  | 2016-08-15 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Amherst | 6A2045-2016 | 01002 | 86.995 | Solar | 18G4 | 2016-08-17 | 2016-09-27 | 30 | 18 | 12 | 2016-09-28 | 2016-11-03 | 27 | 11 | 16 | [20 empty] | 2016-11-03 |  | Sept 2016 |  | EXP | [6 empty] | 2017-03-15 | 2017-03-21 | 2017-03-21
WMECO | Pittsfield | 6B1139-2016 | 01201 | 240 | Solar | 19A7 | 2016-08-17 | 2016-09-01 | 12 | 10 | 2 | 2016-09-02 |  | -30406 | 44 | [23 empty] | 2016-11-01 |  | EXP | [9 empty] | cancelled by applicant, not ready to move forward
WMECO | Springfield | 6S2702-2016 | 01104 | 420 | Solar | 5J15 | 2016-08-18 | 2016-09-14 | 20 | 14 | 6 | 2016-09-15 |  | -30415 | [24 empty] | 2016-12-30 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S2703-2016 | 01104 | 300 | Solar | 5J15 | 2016-08-18 | 2016-09-14 | 20 | 14 | 6 | 2016-09-15 |  | -30415 | [24 empty] | 2016-12-30 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S2720-2016 | 01104 | 796 | Solar | 5J13 | 2016-08-23 | 2016-09-13 | 16 | 9 | 7 | 2016-09-14 | 2016-11-29 | 55 | 32 | 23 | [10 empty] | 2016-11-30 | 2017-01-27 | 43 | 0 | 43 | 2017-03-30 |  | -30555 |  |  | 2017-03-21 |  | Not supplied |  | STD | [9 empty] | cancelled by applicant
WMECO | Westhampton | 6A2060-2016 | 01027 | 16.7 | Solar | 15A3 | 2016-08-24 | [31 empty] | 2016-10-20 |  | EXP | [9 empty] | cancelled by applicant, submitted Simplified app
WMECO | Ludlow | 6S2770-2016 | 01056 | 16.7 | Solar | 19S3 | 2016-09-13 | 2016-10-24 | 30 | 19 | 11 | 2016-10-24 |  | -30442 | [24 empty] | 2016-06-18 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Hadley | 6A2086-2016 | 01035 | 399.6 | Solar | 18G5 | 2016-09-14 | 2016-09-27 | 10 | 5 | 5 | 2016-09-28 | 2016-11-10 | 32 | 19 | 13 | [10 empty] | 2016-11-14 | 2017-04-19 | 113 | 56 | 57 | 2017-04-20 | 2017-08-10 | 81 | 21 | 60 | 2017-08-23 |  | Nov 2016 |  | STD | [8 empty] | 2019-06-20 | on line
WMECO | Worthington | 6F1646-2016 | 01098 | 13.5 | Solar | 18K3 | 2016-09-15 | [31 empty] | 2016-11-30 |  | EXP | [9 empty] | cancelled
WMECO | Middlefield | 6F1675-2016 | 01243 | 41.5 | Solar | 18C2 | 2016-10-03 | 2016-10-17 | 11 | 8 | 3 | 2016-10-17 | 2016-11-07 | 16 | 0 | 16 | [20 empty] | 2016-11-07 |  | 2016-12-01 |  | EXP | [6 empty] | 2017-06-01 | 2017-06-05 | 2017-06-06 | addition to existing facility
WMECO | Northfield | 6F1684-2016 | 01360 | 21.9 | Solar | 21B8 | 2016-10-06 | 2016-11-23 | 35 | 32 | 3 | 2016-11-25 |  | -30466 | [24 empty] | 2017-01-01 |  | EXP | [9 empty] | Cancelled by applicant, did not want to pay for Supplemental Review.
WMECO | Worthington | 6F1694-2016 | 01098 | 13.5 | Solar | 18K3 | 2016-10-11 | [31 empty] | 2016-12-15 |  | EXP | [9 empty] | cancelled by applicant, should have submitted a Simplified Application
WMECO | Springfield | 6S2863-2016 | 01109 | 16.7 | Solar | 20A32 | 2016-10-11 | 2016-12-05 | 40 | 33 | 7 | 2016-12-05 | 2016-12-12 | 6 | 1 | 5 | [20 empty] | 2016-12-12 |  | Not supplied |  | EXP | [8 empty] | 2017-02-21
WMECO | Greenfield | 6F1707-2016 | 01301 | 1200 | Solar | 21C1 | 2016-10-18 | 2016-10-31 | 10 | 7 | 3 | 2016-11-01 | 2016-11-17 | 13 | 10 | 3 | [10 empty] | 2016-11-18 | 2017-01-27 | 51 | 0 | 51 | 2017-02-21 |  | -30528 |  |  | 2017-03-10 |  | 2017-09-21 |  | COMP | [8 empty] | 2021-12-23 | on line
WMECO | Pittsfield | 6B1240-2016 | 01201 | 1320 | Solar | 15E3 | 2016-10-25 | 2016-11-23 | 22 | 9 | 13 | 2016-11-25 |  | -30466 | [24 empty] | May 2017 |  | STD | [9 empty] | Negotiated timeline for technical information concerning export or no-export, 15 extra days. Withdrawn with customer's agreement after not proceeding with project.
WMECO | Springfield | 6S2924-2016 | 01104 | 37.8 | Solar | 5J15 | 2016-10-26 | 2016-11-01 | 5 | 3 | 2 | 2016-11-01 | 2016-12-07 | 27 | 18 | 9 | [20 empty] | 2016-12-07 |  | 2016-12-05 |  | EXP | [6 empty] | 2017-05-24 | 2017-05-26 | 2017-05-26 | applicant submitted new option 2
WMECO | Amherst | 6A2150-2016 | 01002 | 19.8 | Solar | 18G4 | 2016-10-27 | [31 empty] | 11/30/2016 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S2929-2016 | 01104 | 252 | Solar | 21S6 | 2016-10-27 | 2016-11-08 | 9 | 6 | 3 | 2016-11-09 | 2016-12-05 | 19 | 15 | 4 | 2016-12-06 | 2016-12-29 | 18 | 6 | 12 | [15 empty] | 2017-03-15 |  | May 2016 |  | EXP | [6 empty] | 2017-11-15 | 2017-12-07 | 2017-12-07
WMECO | Dalton | 6B1258-2016 | 01226 | 27.5 | Solar | 18C1 | 2016-11-03 | 2016-12-13 | 29 | 25 | 4 | 2016-12-13 | 2017-01-20 | 29 | 3 | 26 | [20 empty] | 2017-01-24 |  | Q4 2016 |  | EXP | [6 empty] | 2016-09-22 | 2016-09-27 | 2017-09-27
WMECO | Springfield | 6S2985-2016 | 01118 | 149.9 | Solar | 20A22 | 2016-11-14 | 2016-12-01 | 14 | 10 | 4 | 2016-12-01 | 2016-12-07 | 5 | 2 | 3 | [20 empty] | 2016-12-07 |  | 1/4/2017 |  | EXP | [6 empty] | 2018-01-08 | 2018-01-11 | 2018-01-11
WMECO | Becket | 6B1277-2016 | 01223 | 4950 | Solar | 19J6 | 2016-11-15 | 2016-12-19 | 25 | 21 | 4 | 2016-12-19 |  | -30482 | [24 empty] | 2017-10-18 |  | STD | [9 empty] | Negotiated 10 extra business days for technical review. Customer sent Impact Study Agreement, had two extensions, withdrawn after missing deadlines.
WMECO | Becket | 6B1278-2016 | 01223 | 4950 | Solar | 16B1 | 2016-11-15 | 2016-12-01 | 13 | 9 | 4 | 2016-12-02 | 2017-01-25 | 39 | 29 | 10 | [10 empty] | 2017-01-26 | 2017-03-30 | 46 | 0 | 46 | 2017-04-20 |  | -30570 |  |  | 2017-04-19 |  | 2017-10-18 |  | COMP | [8 empty] | 2018-11-15 | on line
WMECO | Lee | 6B1279-2016 | 01238 | 1860 | Solar | 16B1 | 2016-11-15 | 2017-01-23 | 50 | 39 | 11 | 2017-01-24 | 2017-03-22 | 42 | 3 | 39 | [10 empty] | 2017-03-23 | 2017-07-24 | 88 | 17 | 71 | 2017-07-25 | 2017-11-03 | 74 | 0 | 74 | 2017-11-03 |  | Sept 2017 |  | STD | [8 empty] | 2018-08-24 | applicant submitted second option, requires T ROW study, negotiated timeline due to complicated ROW interconnection, 10 days initial review, 10 days Impact Study.
WMECO | Lanesborough | 6B1280-2016 | 01237 | 4491 | Solar | 15E1 | 2016-11-15 | 2017-02-13 | 65 | 58 | 7 | 2017-02-14 | 2017-03-22 | 27 | 21 | 6 | [10 empty] | 2017-03-23 |  | -30550 | [9 empty] | Sept 2017 |  | STD | [9 empty] | Negotiated timeline - 20 days, cancelled by applicant
WMECO | Pittsfield | 6B1281-2016 | 01201 | 1500 | Solar | 15E2 | 2016-11-15 | 2017-01-23 | 50 | 39 | 11 | 2017-01-04 |  | -30494 | [24 empty] | Sept 2017 |  | STD | [9 empty] | applicant submitted options, cancelled
WMECO | Montague | 6F1738-2016 | 01351 | 4080 | Solar | 21C8 | 2016-11-15 | 2017-02-17 | 69 | 64 | 5 | 2017-02-21 | 2017-03-22 | 22 | 16 | 6 | [10 empty] | 2017-03-23 | 2017-07-28 | 92 | 16 | 76 | 2017-07-31 | 2017-10-02 | 46 | 0 | 46 | 2017-10-19 |  | Sept 2017 |  | COMP | [8 empty] | 2018-10-12 | second option submitted, Negotiated timeline - 15 days
WMECO | Ludlow | 6S2989-2016 | 01056 | 1860 | Solar | 19S1 | 2016-11-15 | 2017-01-23 | 50 | 39 | 11 | 2017-01-24 | 2017-03-02 | 28 | 21 | 7 | [10 empty] | 2017-03-03 | 2017-06-12 | 72 | 20 | 52 | 2017-06-13 | 2017-10-03 | 81 | 0 | 81 | 2017-10-17 |  | Sept 2017 |  | COMP | [8 empty] | 2018-08-29 | applicant submitted second option, requires T ROW study
WMECO | Agawam | 6S2990-2016 | 01030 | 4140 | Solar | 30A6 | 2016-11-15 | 2017-01-23 | 50 | 42 | 8 | 2017-01-24 | 2017-03-02 | 28 | 13 | 15 | [10 empty] | 2017-03-03 | 2017-05-12 | 51 | 0 | 51 | [7 empty] | Sept 2017 |  | COMP | [9 empty] | applicant submitted second option, cancelled by applicant
WMECO | Agawam | 6S2996-2016 | 01001 | 95.4 | Solar | 16C16 | 2016-11-15 | 2016-12-05 | 15 | 11 | 4 | 2016-12-05 | 2016-12-15 | 9 | 6 | 3 | [20 empty] | 2016-12-15 |  | 12/23/2016 |  | EXP | [6 empty] | 2017-07-10 | 2017-07-12 | 2017-07-18
WMECO | Pittsfield | 6B1282-2016 | 01201 | 1590 | Solar | 30B7 | 2016-11-16 | 2016-12-01 | 12 | 6 | 6 | 2016-12-02 | 2016-12-19 | 12 | 4 | 8 | 2016-12-20 | 2017-02-08 | 37 | 15 | 22 | [5 empty] | 2017-02-09 | 2017-04-11 | 44 | 0 | 44 | 2017-04-21 |  | -30571 |  |  | 2017-04-26 |  | 12/2016 |  | STD | [7 empty] | 2018-08-10 | 2018-09-10 | applicant submitted options
WMECO | Hadley | 6A2172-2016 | 01035 | 1630 | Solar | 19B15 | 2016-11-21 | 2017-01-23 | 46 | 35 | 11 | 2017-01-24 | 2017-03-02 | 28 | 21 | 7 | [10 empty] | 2017-03-03 | 2017-05-19 | 56 | 0 | 56 | [7 empty] | 2017-09-28 |  | STD | [9 empty] | applicant submitted second option, cancelled by applicant
WMECO | Lee | 6B1290-2016 | 01238 | 999 | Solar | 16B1 | 2016-11-21 | 2016-12-01 | 9 | 7 | 2 | 2016-12-02 |  | -30471 | [24 empty] | 5/1/2017 |  | STD | [9 empty] | applicant submitted two options, negotiated 10 days, applicant cancelled application
WMECO | Agawam | 6S3021-2016 | 01030 | 849.7 | Solar | 30A6 | 2016-11-21 | 2017-02-28 | 72 | 65 | 7 | 2017-03-01 | 2017-03-22 | 16 | 10 | 6 | [10 empty] | 2017-03-23 |  | -30550 | 24 | [8 empty] | 9/28/2017 |  | STD | [9 empty] | applicant submitted a smaller option to proceed with, on hold behind another application 6S2990-2016, cancelled by applicant
WMECO | Montague | 6A2182-2016 | 01351 | 450 | Solar | 21C8 | 2016-11-22 | 2017-01-03 | 31 | 27 | 4 | 2017-01-04 | 2017-04-05 | 66 | 60 | 6 | [10 empty] | 2017-04-06 | 2018-02-23 | 232 | 179 | 53 | [5 empty] | 2018-02-28 |  | Dec 2016 |  | STD | [9 empty] | cancelled
WMECO | Springfield | 6S3052-2016 | 01118 | 266.4 | Solar | 20A32 | 2016-12-02 | 2017-04-03 | 87 | 81 | 6 | 2017-04-04 |  | -30558 | [24 empty] | 2017-06-30 |  | EXP | [9 empty] | three options, cancelled by applicant, not sure what they will install
WMECO | Agawam | 6S3100-2016 | 01001 | 129.6 | Solar | 30A2 | 2016-12-21 | [31 empty] | 2017-01-28 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Springfield | 6S3147-2017 | 01103 | 1023.24 | Solar | 08C31, 08C32 | 2017-01-03 | 2017-02-14 | 31 | 23 | 8 | 2017-02-15 |  | -30524 | [24 empty] | 2017-10-15 |  | EXP | [9 empty] | negotiated 20 days for option, cancelled by applicant
WMECO | Granville | 6S3151-2017 | 01034 | 475 | Biogas | 29A5 | 2017-01-03 | 2017-02-16 | 33 | 28 | 5 | 2017-02-17 | 2017-04-27 | 50 | 46 | 4 | [10 empty] | 2017-04-28 | 2017-07-20 | 60 | 11 | 49 | 2017-07-21 | 2017-10-03 | 53 | 0 | 53 | 2017-10-19 |  | 2017-10-30 |  | STD | [8 empty] | 2019-05-16 | on line
WMECO | Hatfield | 6A2232-2017 | 01088 | 334.42 | Solar | 18G5 | 2017-01-09 | 2017-03-20 | 51 | 46 | 5 | 2017-03-21 |  | -30548 | [24 empty] | 9/1/2017 |  | STD | [9 empty] | existing non export solar will be removed and replaced by new project, cancelled by applicant
WMECO | Pittsfield | 6B1329-2017 | 01201 | 725 | Natural Gas | 30B1 | 2017-01-10 | 2017-02-13 | 25 | 22 | 3 | 2017-02-14 | 2017-04-21 | 49 | 36 | 13 | 2017-04-24 | 2017-07-13 | 59 | 40 | 19 | [15 empty] | 2017-07-24 |  | 11/1/2017 |  | EXP | [6 empty] | 2018-05-14 | 2018-05-23 | 2018-06-07
WMECO | Erving | 6F1795-2017 | 01344 | 210 | Solar | 21B9 | 2017-01-11 | 2017-03-15 | 46 | 40 | 6 | 2017-03-16 |  | -30545 | [24 empty] | 2017-08-31 |  | STD | [9 empty] | cancelled by applicant
WMECO | Chicopee | 6S3180-2017 | 01013 | 2535 | Solar | 21N7 | 2017-01-18 | 2017-02-14 | 20 | 8 | 12 | 2017-02-15 | 2017-03-09 | 17 | 12 | 5 | [10 empty] | 2017-03-10 | 2017-06-15 | 70 | 3 | 67 | [5 empty] | 2017-06-30 |  | 2017-08-31 |  | STD | [9 empty] | rcvd application, need check, rcvd check, rvw for app complete, requested info, rcvd info app complete, starteted initi revw, init revw sent out customer, customer requested two options, started Impact Study agreement, sent impact study agreement to customer. Draft report sent ot engineering for review. Negotiated 20 days to develope new DTT for this type of circuit. Withdrawn, applicant did not execute Detailed Study.
WMECO | Springfield | 6S3184-2017 | 01103 | 6250 | Diesel | 8C31 | 2017-01-19 | 2017-02-17 | 22 | 12 | 10 | 2017-02-21 | 2017-05-08 | 55 | 18 | 37 | [10 empty] | 2017-05-09 | 2017-08-04 | 64 | 55 | 9 | [5 empty] | 2017-08-24 |  | Not supplied |  | STD | [6 empty] | 2017-09-15 | 2017-09-18 | 2017-09-25 | Negotiated 10 extra days for option and for customer to make decisions. 2 design options, applicant going with only 2 emergency generators on this app
WMECO | Greenfield | 6F1810-2017 | 01301 | 250 | Solar | 22B7 | 2017-01-24 | 2017-03-01 | 27 | 12 | 15 | 2017-03-01 |  | -30534 | [24 empty] | 2017-05-01 |  | EXP | [9 empty] | Was on hold behind prior app on same circuit. Negotiated timeline - IC granted 25 day extension to initial review and 30 days for technical information required. Cancelled by applicant
WMECO | Greenfield | 6F1809-2017 | 01301 | 294 | Solar | 22B7 | 2017-01-25 | 2017-03-01 | 26 | 12 | 14 | 2017-03-01 |  | -30534 | [24 empty] | 2017-05-01 |  | STD | [9 empty] | withdrawn after the applicants did not move forward
WMECO | Savoy | 6B1350-2017 | 01256 | 7500 | Wind | 18C1 | 2017-02-01 | 2017-02-23 | 17 | 12 | 5 | 2017-02-24 | 2017-03-28 | 23 | 15 | 8 | [10 empty] | 2017-03-29 | 2018-02-22 | 237 | 106 | 131 | 2018-02-23 |  | -30791 |  |  |  |  | Sept 2018 |  | COMP | [9 empty] | Applicant submitted 2 options. Negotiated timeline - 20 days Impact Study. Submitted another option. Customer submitted another option. Customer requested another extension, granted 42 days. Cancelled by applicant.
WMECO | Agawam | 6S3221-2017 | 01001 | 1252 | Solar | 30A3 | 2017-02-06 | 2017-02-22 | 13 | 4 | 9 | 2017-02-23 | 2017-06-12 | 78 | 52 | 26 | [10 empty] | 2017-06-13 |  | -30608 |  |  | 2017-08-17 |  | -30655 |  |  |  |  | May 2017 |  | STD | [9 empty] | Negotiated timeline, 10 extra days for submittal and review of new drawing/option. Cancelled by applicant.
WMECO | Agawam | 6S3222-2017 | 01001 | 167 | Solar | 30A3 | 2017-02-06 | 2017-02-22 | 13 | 4 | 9 | 2017-02-23 |  | -30530 | [24 empty] | May 2017 |  | EXP | [9 empty] | Negotiated timeline for option, 10 extra days, on hold behind another app on same circuit, submitted an option, negotiated 7 extra days, applicant cancelled
WMECO | Agawam | 6S3223-2017 | 01001 | 72 | Solar | 30A3 | 2017-02-06 | 2017-02-22 | 13 | 4 | 9 | 2017-02-23 |  | -30530 | [24 empty] | May 2017 |  | EXP | [9 empty] | Negotiated timeline, 20 extra days for submittal of new options, need information. On hold behind another app on same circuit. Applicant cancelled.
WMECO | Springfield | 6S3230-2017 | 01103 | 16.2 | Solar | 8CNW_1 | 2017-02-08 | 2017-03-16 | 27 | 19 | 8 | 2017-03-17 | 2017-04-13 | 20 |  | 20 | [22 empty] | 2017-04-10 |  | STD | [9 empty] | withdrawn
WMECO | Amherst | 6A2263-2017 | 01002 | 3120 | Solar | 18G4 | 2017-02-09 | 2017-02-15 | 5 | 4 | 1 | 2017-02-16 | 2017-05-04 | 56 | 44 | 12 | [10 empty] | 2017-05-05 | 2017-08-04 | 66 | 15 | 51 | 2017-08-07 |  | -30647 |  |  | 2017-08-23 |  | 2017-12-01 |  | STD | [8 empty] | 2019-12-20 | on line
WMECO | Worthington | 6A2274-2017 | 01098 | 5000 | Solar | 18K3 | 2017-02-13 | 2017-03-01 | 13 | 10 | 3 | 2017-03-02 |  | -30535 | [24 empty] | 2018-01-15 |  | STD | [9 empty] | Negotiated 15 days at request of applicant. Withdrawn after missed deadlines and applicant did not execute Impact Study Agreement.
WMECO | Blandford | 6B1362-2017 | 01008 | 1000 | Solar | 19J2 | 2017-02-13 | 2017-02-27 | 11 | 7 | 4 | 2017-02-28 | 2017-04-14 | 34 | 20 | 14 | [10 empty] | 2017-04-17 | 2017-08-08 | 82 | 38 | 44 | 2017-08-09 | 2017-11-17 | 73 | 4 | 69 | 2017-11-17 |  | Dec 2017 |  | STD | [8 empty] | 2019-11-15 | on line
WMECO | Hinsdale | 6B1363-2017 | 01235 | 5000 | Solar | 18C2 | 2017-02-13 | 2017-03-16 | 24 | 21 | 3 | 2017-03-17 |  | -30546 | [24 empty] | Dec 2017 |  | STD | [9 empty] | three options, withdrawn after 10 day extension, notices and decision by applicant to have application withdrawn
WMECO | Pittsfield | 6B1365-2017 | 01201 | 499.5 | Solar | 30B5 | 2017-02-15 | 2017-03-29 | 31 | 20 | 11 | 2017-03-30 |  | -30555 | [24 empty] | Not supplied |  | STD | [9 empty] | cancelled by applicant
WMECO | Dalton | 6B1366-2017 | 01226 | 499.5 | Solar | 19A3 | 2017-02-15 | 2017-03-29 | 31 | 20 | 11 | 2017-03-30 | 2017-05-05 | 27 | 22 | 5 | [10 empty] | 2017-05-08 | 2017-08-14 | 71 | 26 | 45 | 2017-08-24 |  | -30660 |  |  | 2017-08-14 |  | Not supplied |  | STD | [8 empty] | 2018-12-28
WMECO | Cummington | 6A2290-2017 | 01026 | 10.95 | Solar | 18K3 | 2017-02-23 | 2017-03-06 | 8 | 4 | 4 | 2017-03-06 | 2017-04-28 | 40 | 24 | 16 | [20 empty] | 2017-04-28 |  | 2017-05-15 |  | EXP | [6 empty] | 2017-06-26 | 2017-06-30 | 2017-06-30
WMECO | Pittsfield | 6B1375-2017 | 01201 | 1160 | Solar | 15E2 | 2017-02-27 | 2017-03-08 | 8 | 6 | 2 | 2017-03-08 | 2017-03-22 | 11 | 8 | 3 | [10 empty] | 2017-03-23 | 2017-07-28 | 92 | 16 | 76 | 2017-07-31 | 2017-09-29 | 45 | 9 | 36 | 2017-10-06 |  | 2017-09-01 |  | STD | [8 empty] | 2018-08-17 | Negotiated timeline - 20 days
WMECO | Lanesborough | 6B1377-2017 | 01237 | 1998 | Solar | 15E1 | 2017-02-28 | 2017-04-11 | 31 | 28 | 3 | 2017-04-12 |  | -30564 | 9 | [23 empty] | Not supplied |  | STD | [9 empty] | application on hold behind another application intil the first Impact Study is completed, app now moving forward, cancelled by applicant
WMECO | Pittsfield | 6B1378-2017 | 01201 | 27.44 | Solar | 19A7 | 2017-02-28 | 2017-03-29 | 22 | 21 | 1 | 2017-03-29 | 2017-04-20 | 17 | 15 | 2 | 2017-04-21 | 2017-07-14 | 61 | 0 | 61 | [15 empty] | 2017-07-14 |  | Aug 2017 |  | EXP | [6 empty] | 3821/18 | 2018-03-21 | 2018-03-23
WMECO | Greenfield | 6A2305-2017 | 01337 | 995 | Biogas | 22B7 | 2017-03-06 | 2017-03-20 | 11 | 9 | 2 | 2017-03-21 |  | -30548 | 30 | [23 empty] | Not supplied |  | STD | [9 empty] | Sent 10 day notice for missed deadline, application cancelled by application
WMECO | Worthington | 6A2316-2017 | 01098 | 21.9 | Solar | 18K3 | 2017-03-09 | 2017-03-30 | 16 | 14 | 2 | 2017-03-30 |  | -30555 | [24 empty] | 2017-06-15 |  | EXP | [9 empty] | Applicant sent Supplemental Review, sent 10 day notice to move forward or withdraw, applicant decided not to proceed, withdrawn at applicant's request.
WMECO | Lanesborough | 6B1399-2017 | 01237 | 1998 | Solar | 15E1 | 2017-03-20 | [31 empty] | Not supplied |  | EXP | [9 empty] | withdrawn 4/24/17, applicant said this was a duplicate of another application 6B1377-2017
WMECO | Gill | 6A2364-2017 | 01354 | 4998.4 | Solar | 21C5 | 2017-03-29 | 2017-04-17 | 14 | 7 | 7 | 2017-04-18 | 2017-07-24 | 70 | 29 | 41 | [10 empty] | 2017-07-25 | 2017-12-18 | 105 | 18 | 87 | [7 empty] | Not supplied |  | COMP | [9 empty] | Negotiated timeline 25 days to review 3 options, 20 days for review, Complex 20 extra days for Impact Study, applicant must pick option to proceed to Detailed Study with. Cancelled by applicant.
WMECO | Longmeadow | 6S3353-2017 | 01106 | 86.4 | Solar | 22H15 | 2017-04-07 | [31 empty] | 5/7 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Amherst | 6A2398-2017 | 01059 | 996 | Solar | 18G7 | 2017-04-12 | 2017-06-16 | 48 | 41 | 7 | 2017-06-19 |  | -30612 | [24 empty] | 2017-12-31 |  | EXP | [9 empty] | on hold behind other apps on circuit, negotiated 10 days to tech review, cancelled by applicant
WMECO | Amherst | 6A2399-2017 | 01059 | 4980 | Battery | 18G7 | 2017-04-12 | 2017-06-16 | 48 | 41 | 7 | 2017-06-19 | 2017-08-08 | 37 | 28 | 9 | [10 empty] | 2017-08-09 | 2017-10-17 | 50 | 0 | 50 | 2017-12-15 |  | -30741 |  |  | 2017-10-30 |  | 2017-12-31 |  | STD | [8 empty] | 2019-07-30 | on line
WMECO | Amherst | 6A2400-2017 | 01059 | 996 | Solar | 18G7 | 2017-04-12 | 2017-06-16 | 48 | 41 | 7 | 2017-06-19 |  | -30612 | [24 empty] | 2017-12-31 |  | EXP | [9 empty] | on hold behind other apps on circuit, negotiated 10 days to tech review, cancelled by applicant
WMECO | West Springfield | 6S3370-2017 | 01089 | 300 | Natural Gas | 21N5 | 2017-04-13 | 2017-07-20 | 71 | 67 | 4 | 2017-07-21 | 2017-10-10 | 58 | 49 | 9 | [10 empty] | 2017-10-11 | 2017-11-10 | 23 | 0 | 23 | [7 empty] | 2/2018 |  | COMP | [9 empty] | negitiated 20 days for review, 2 designs, cancelled by applicant
WMECO | Springfield | 6S3392-2017 | 01118 | 165 | Solar | 20A32 | 2017-04-21 | 2017-05-01 | 7 | 5 | 2 | 2017-05-01 | 2017-05-08 | 6 | 3 | 3 | 2017-05-09 | 2017-08-31 | 83 | 43 | 40 | [5 empty] | 2017-09-01 | 2017-11-28 | 63 | 7 | 56 | [5 empty] | 2017-11-28 |  | 2017-06-30 |  | STD | [9 empty] | three options, negotiated an extra 25 days for Supp Review, cancelled by applicant
WMECO | Pittsfield | 6B1444-2017 | 01201 | 240 | Solar | 15E2 | 2017-04-25 | 2017-05-15 | 15 | 13 | 2 | 2017-05-16 | 2017-06-23 | 29 | 3 | 26 |  | 2017-07-06 | [8 empty] | 2017-06-23 | 2017-10-04 | 74 | 64 | 10 | 2017-10-05 | 2017-12-21 | 56 | 0 | 56 | 2017-12-21 |  | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Hatfield | 6A2448-2017 | 01038 | 15.36 | Solar | 18G6 | 2017-05-01 | 2017-05-12 | 10 | 7 | 3 | 2017-05-12 |  | -30586 | [24 empty] | 2017-05-29 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Lanesborough | 6B1446-2017 | 01237 | 2597.4 | Solar | 15E2 | 2017-05-04 | 2017-05-18 | 11 | 2 | 9 | 2017-05-19 |  | -30591 | [24 empty] | Not supplied |  | STD | [9 empty] | application on hold behind an earlier application, application cancelled by applicant
WMECO | Pittsfield | 6B1447-2017 | 01201 | 1998 | Solar | 19A4 | 2017-05-05 | 2017-05-18 | 10 | 3 | 7 | 2017-05-19 | 2017-06-02 | 11 | 6 | 5 | [10 empty] | 2017-06-05 | 2017-08-23 | 58 | 4 | 54 | 2017-08-24 |  | -30660 |  |  | 2017-08-30 |  | Not supplied |  | STD | [8 empty] | 2018-12-21
WMECO | Blandford | 6B1451-2017 | 01008 | 4700 | Solar | 19J4 | 2017-05-08 | 2017-08-18 | 75 | 60 | 15 | 2017-08-21 | 2017-09-14 | 19 | 11 | 8 | [10 empty] | 2017-09-15 | 2017-12-04 | 57 | 10 | 47 | 2017-12-19 |  | -30743 |  |  | 2017-12-04 |  | 2018-09-01 |  | COMP | [8 empty] | 2020-06-30 | on line
WMECO | Springfield | 6S3435-2017 | 01104 | 1440 | Solar | 5J11 | 2017-05-08 | 2017-06-01 | 19 | 9 | 10 | 2017-06-02 | 2017-07-19 | 34 | 30 | 4 | [10 empty] | 2017-07-20 | 2017-11-02 | 76 | 17 | 59 | 2017-11-10 |  | -30716 |  |  | 2017-12-11 |  | Nov 2017 |  | COMP | [8 empty] | 2018-10-17 | two options, negotisated an extra 25 days
WMECO | Pittsfield | 6B1454-2017 | 01201 | 1556 | Solar | 30B5 | 2017-05-11 | 2017-06-19 | 28 | 21 | 7 | 2017-06-20 |  | -30613 | [24 empty] | 2018-01-01 |  | STD | [9 empty] | three options, negotiated 10 days to initial review, Impact Study Agreement not executed, cancelled at applicant's request
WMECO | Cummington | 6A2489-2017 | 01026 | 480 | Solar | 18K3 | 2017-05-12 | 2017-06-06 | 18 | 13 | 5 | 2017-06-07 | 2017-07-17 | 29 | 22 | 7 | [10 empty] | 2017-07-18 | 2017-09-28 | 53 | 0 | 53 | [7 empty] | 2018-02-15 |  | COMP | [9 empty] | 2 options, cancelled by applicant
WMECO | Cummington | 6A2491-2017 | 01026 | 240 | Solar | 18K3 | 2017-05-12 | 2017-06-06 | 18 | 13 | 5 | 2017-06-07 |  | -30604 | 111 | [23 empty] | 2018-02-15 |  | STD | [9 empty] | on hold behind another app in queue, sent 10 day notice, withdrawn after missed deadlines
WMECO | Shelburne | 6A2495-2017 | 01370 | 60 | Solar | 29R2 | 2017-05-17 | 2017-05-25 | 7 | 2 | 5 | 2017-05-25 | 2017-06-05 | 8 | 5 | 3 | [20 empty] | 2017-06-09 |  | Not supplied |  | EXP | [6 empty] | 2018-01-31 | 2018-02-02 | 2018-02-02
WMECO | Easthampton | 6A2529-2017 | 01027 | 1095.8 | Solar | 15A5 | 2017-05-25 | 2017-08-17 | 61 | 51 | 10 | 2017-08-18 | 2017-10-27 | 51 | 37 | 14 | [10 empty] | 2017-10-30 | 2018-03-15 | 99 | 21 | 78 | 2018-03-16 | 2018-06-26 | 73 | 11 | 62 | 2018-06-29 |  | 2018-04-15 |  | COMP | [9 empty] | withdrawn
WMECO | Deerfield | 6A2524-2017 | 01342 | 72 | Solar | 22B1 | 2017-05-30 | 2017-06-08 | 8 | 5 | 3 | 2017-06-09 | 2017-06-22 | 10 | 2 | 8 | [20 empty] | 2017-06-22 |  | 2017 |  | EXP | [6 empty] | 2017-12-26 | 2017-12-17 | 2018-01-12
WMECO | Dalton | 6B1482-2017 | 01226 | 4980 | Solar | 29M1 | 2017-06-02 | 2017-06-15 | 10 | 6 | 4 | 2017-06-16 |  | -30611 | [24 empty] | Nov 2017 |  | STD | [9 empty] | cancelled by applicant
WMECO | Lanesborough | 6B1483-2017 | 01237 | 4980 | Solar | 15E2 | 2017-06-02 | 2017-06-15 | 10 | 6 | 4 | 2017-06-16 |  | -30611 | [24 empty] | Nov 2017 |  | STD | [9 empty] | negotiated 10 days initial review, cancelled by applicant
WMECO | Southwick | 6S3507-2017 | 01077 | 4980 | Solar | 29A1 | 2017-06-02 | 2017-06-15 | 10 | 6 | 4 | 2017-06-16 | 2017-09-01 | 56 | 48 | 8 | [10 empty] | 2017-09-05 | 2017-10-20 | 34 | 0 | 34 | 2017-10-31 |  | -30708 |  |  | 2017-10-30 |  | 1905-07-09 |  | STD | [8 empty] | 2019-02-01
WMECO | Greenfield | 6A2544-2017 | 01301 | 380 | Solar | 22B2 | 2017-06-06 | 2017-06-20 | 11 | 4 | 7 | 2017-06-21 | 2017-09-25 | 69 | 30 | 39 | 2017-09-26 | 2017-12-28 | 68 | 41 | 27 | [5 empty] | 2017-12-29 | 2018-02-02 | 26 | 8 | 18 | [5 empty] | 2018-02-07 |  | 10-17 |  | STD | [7 empty] | 2018-04-27 | 2018-04-30 | negotiated, 15 days, 2 options
WMECO | Hatfield | 6A2545-2017 | 01038 | 380 | Biogas | 18G6 | 2017-06-06 | 2017-06-30 | 19 | 10 | 9 | 2017-07-03 | 2017-07-27 | 19 | 8 | 11 | [10 empty] | 2017-07-28 | 2017-11-03 | 71 | 1 | 70 | 2018-01-19 |  | -30766 |  |  | 2017-11-10 |  | 6/2018 |  | STD | [8 empty] | 2019-05-21 | on line
WMECO | Springfield | 6S3522-2017 | 01151 | 3500 | Solar | 27A13 | 2017-06-09 | 2017-09-22 | 76 | 35 | 41 | 2017-09-25 | 2017-12-06 | 53 | 45 | 8 | [10 empty] | 2017-12-07 | 2018-03-19 | 73 | 10 | 63 | 2018-04-03 |  | -30818 |  |  | 2018-04-10 |  | 2018-06-07 |  | STD | [8 empty] | 2019-12-27 | on line
WMECO | Springfield | 6S3523-2017 | 01151 | 2000 | Solar | 27A13 | 2017-06-09 | 2017-09-22 | 76 | 33 | 43 | 2017-09-25 | 2018-02-13 | 102 | 92 | 10 | [10 empty] | 2018-02-14 | 2018-09-04 | 145 |  | 145 | [5 empty] | 2018-08-15 |  | 2018-06-07 |  | STD | [9 empty] | withdrawn
WMECO | Longmeadow | 6S3529-2017 | 01106 | 16 | Solar | 22H12 | 2017-06-12 | 2017-06-22 | 9 | 3 | 6 | 2017-06-22 | 2017-06-26 | 3 | 0 | 3 | [20 empty] | 2017-06-30 |  | 2017-07-15 |  | EXP | [8 empty] | 2017-11-08
WMECO | Pittsfield | 6B1488-2017 | 01201 | 33.3 | Solar | 30B5 | 2017-06-14 | 2017-07-13 | 22 | 13 | 9 | 2017-07-13 | 2017-08-25 | 32 | 15 | 17 | [20 empty] | 2017-09-17 |  | 2017-08-01 |  | EXP | [8 empty] | 2023-08-04 | on line
WMECO | Sunderland | 6A2588-2017 | 01375 | 1084 | Solar | 18G3 | 2017-06-15 | 2017-06-27 | 9 | 1 | 8 | 2017-06-28 | 2017-08-24 | 42 | 30 | 12 | [10 empty] | 2017-08-24 | 2017-10-19 | 41 | 0 | 41 | 2017-11-10 |  | -30716 |  |  | 2017-10-30 |  | DEC 2017 |  | STD | [8 empty] | 2018-09-21
WMECO | Pittsfield | 6B1490-2017 | 01201 | 499.5 | Solar | 30B1 | 2017-06-15 | 2017-07-05 | 15 | 3 | 12 | 2017-07-06 |  | -30625 | [24 empty] | Not supplied |  | STD | [9 empty] | sent Impact Study Agreement to applicant, sent 10 day notice, applicant cancelled
WMECO | Pittsfield | 6B1491-2017 | 01201 | 765.9 | Solar | 30B1 | 2017-06-15 | 2017-07-03 | 13 | 3 | 10 | 2017-07-05 | 2017-12-18 | 119 | 93 | 26 | [10 empty] | 2017-12-19 | 2018-03-21 | 67 |  | 67 | [7 empty] | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Agawam | 6S3543-2017 | 01001 | 4989.8 | Solar | 30A3 | 2017-06-15 | 2017-06-28 | 10 | 6 | 4 | 2017-06-29 |  | -30620 | [24 empty] | Fall 2018 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Agawam | 6S3544-2017 | 01001 | 4990 | Solar | 30A3 | 2017-06-15 | 2017-06-30 | 12 | 6 | 6 | 2017-07-03 | 2017-08-01 | 22 | 14 | 8 | [10 empty] | 2017-08-02 | 2017-12-14 | 97 | 36 | 61 | 2017-12-15 | 2018-03-15 | 65 | 12 | 53 | 2018-03-16 |  | Fall 2018 |  | STD | [8 empty] | 2020-12-11 | on line
WMECO | Springfield | 6S3549-2017 | 01104 | 4000 | Solar | 5J18 | 2017-06-15 | 2017-06-27 | 9 | 1 | 8 | 2017-06-28 | 2017-08-23 | 41 | 32 | 9 | [10 empty] | 2017-08-24 | 2017-11-28 | 69 | 0 | 69 | 2017-12-06 |  | -30734 |  |  | 2017-12-05 |  | DEC 2017 |  | COMP | [8 empty] | 2019-02-01 | Negotiated 10 days for complicated system mods in Impact Study
WMECO | Amherst | 6A2594-2017 | 01002 | 3875 | Solar | 17K8 | 2017-06-19 | 2017-06-29 | 9 | 7 | 2 | 2017-06-30 | 2017-08-29 | 43 | 31 | 12 | [10 empty] | 2017-08-30 | 2017-11-01 | 46 |  | 46 | [5 empty] | 2017-12-05 |  | 7/18 |  | COMP | [9 empty] | in impact study
WMECO | Hinsdale | 6B1495-2017 | 01235 | 999 | Solar | 18C2 | 2017-06-19 | 2017-07-05 | 13 | 5 | 8 | 2017-07-06 | 2017-08-18 | 32 | 23 | 9 | [10 empty] | 2017-08-21 | 2017-10-24 | 47 | 0 | 47 | 2017-11-29 |  | -30729 |  |  | 2017-11-02 |  | Not supplied |  | STD | [8 empty] | 2019-10-30 | on line
WMECO | Feeding Hills | 6S3555-2017 | 01030 | 18.88 | Solar | 16C17 | 2017-06-19 | 2017-07-07 | 15 | 6 | 9 | 2017-07-07 |  | -30626 | [24 empty] | 2017-07-20 |  | EXP | [9 empty] | withdrawn after applicant did not execute Supplemental Review Agreement
WMECO | Lanesborough | 6B1497-2017 | 01237 | 499.5 | Solar | 15E1 | 2017-06-21 | 2017-07-07 | 13 | 6 | 7 | 2017-07-10 | 2017-10-04 | 63 | 55 | 8 | [10 empty] | 2017-10-05 | 2017-12-14 | 51 | 0 | 51 | 2018-01-26 |  | -30771 |  |  | 2017-12-18 |  | Not supplied |  | STD | [8 empty] | 2019-07-25 | on line
WMECO | Southwick | 6S3566-2017 | 01077 | 2000 | Solar | 29A1 | 2017-06-21 | 2017-08-07 | 34 | 16 | 18 | 2017-08-08 |  | -30648 | 37 | [14 empty] | 11 | [8 empty] | Sept 2017 |  | STD | [9 empty] | 10 day notice sent, negotiated timeline, second option, on hold behind another application, withdrawn due to missed deadlines
WMECO | Easthampton | 6A2609-2017 | 01027 | 32.85 | Solar | 15A5 | 2017-06-22 | 2017-06-28 | 5 | 0 | 5 | 2017-06-28 | 2017-08-10 | 32 | 31 | 1 | 2017-08-11 | 2017-08-25 | 11 | 0 | 11 | [15 empty] | 2017-08-28 |  | 2017 |  | EXP | [6 empty] | 2018-08-30 | 2018-08-31 | 2018-08-31
WMECO | Agawam | 6S3582-2017 | 01001 | 2330 | Solar | 30A4 | 2017-06-29 | 2017-11-30 | 111 | 99 | 12 | 2017-12-01 |  | -30731 | [24 empty] | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Agawam | 6S3583-2017 | 01001 | 5555 | Solar | 30A4 | 2017-06-29 | 2017-12-14 | 121 | 112 | 9 | 2017-12-14 | 2017-12-14 | 1 |  | 1 | [22 empty] | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Agawam | 6S3584-2017 | 01001 | 5500 | Solar | 30A4 | 2017-06-29 | 2017-11-30 | 111 | 99 | 12 | 2017-12-01 |  | -30731 | [24 empty] | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Agawam | 6S3585-2017 | 01001 | 2330 | Solar | 30A4 | 2017-06-29 | [31 empty] | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Blandford | 6B1522-2017 | 01008 | 4920 | Solar | 19J2 | 2017-07-17 | 2017-07-20 | 4 | 1 | 3 | 2017-07-21 | 2017-11-10 | 81 | 31 | 50 | [10 empty] | 2017-11-13 | 2018-03-13 | 87 | 7 | 80 | 2018-06-29 |  | -30881 |  |  | 2018-05-07 |  | Not supplied |  | COMP | [8 empty] | 2019-12-27 | on line
WMECO | Hatfield | 6A2693-2017 | 01038 | 3600 | Solar | 18G5 | 2017-07-24 | 2017-07-27 | 4 | 0 | 4 | 2017-07-27 | 2017-09-27 | 45 | 20 | 25 | [10 empty] | 2017-09-28 | 2017-11-16 | 36 | 0 | 36 | 2017-11-28 |  | -30728 |  |  | 2017-11-27 |  | Nov 2017 |  | COMP | [8 empty] | 2018-11-02 | on line
WMECO | Amherst | 6A2698-2017 | 01002 | 98.5 | Solar | 18G4 | 2017-07-26 | 2017-09-22 | 43 | 33 | 10 | 2017-09-25 | 2017-10-20 | 20 | 8 | 12 | [20 empty] | 2017-10-27 |  | 2017 |  | EXP | [8 empty] | 2018-03-30 | on line
WMECO | Pittsfield | 6B1539-2017 | 01201 | 4980 | Solar | 15E2 | 2017-07-28 | 2017-09-11 | 32 | 22 | 10 | 2017-09-12 |  | -30673 | 44 | [23 empty] | Not supplied |  | STD | [9 empty] | two options, negotiated 20 extra days, withdrawn, applicant did not execute Impact Study agreement
WMECO | Deerfield | 6A2710-2017 | 01342 | 2200 | Solar | 22B4 | 2017-07-31 | 2017-08-09 | 8 | 1 | 7 | 2017-08-10 | 2017-08-28 | 13 | 6 | 7 | [10 empty] | 2017-08-29 | 2018-02-26 | 130 | 11 | 119 | [5 empty] | 2018-06-20 |  | 2018-03-02 |  | STD | [9 empty] | cancelled
WMECO | Easthampton | 6A2718-2017 | 01027 | 2200 | Solar | 15A2 | 2017-08-02 | 2017-08-28 | 19 | 15 | 4 | 2017-08-28 | 2017-09-22 | 20 | 18 | 2 | [10 empty] | 2017-09-25 | 2017-12-07 | 54 | 17 | 37 | 2017-12-08 | 2018-03-23 | 76 | 21 | 55 | 2018-04-02 |  | Not supplied |  | COMP | [9 empty] | cancelled
WMECO | Amherst | 6A2774-2017 | 01002 | 233.1 | Solar | 17K8 | 2017-08-16 | 2017-08-25 | 8 | 3 | 5 | 2017-08-28 |  | -30662 | [24 empty] | 2017 |  | STD | [9 empty] | cancelled by applicant
WMECO | Amherst | 6A2776-2017 | 01002 | 233.1 | Solar | 17K2 | 2017-08-16 | 2017-08-25 | 8 | 3 | 5 | 2017-08-28 | 2017-09-28 | 24 | 20 | 4 | [10 empty] | 2017-09-29 | 2017-10-31 | 23 | 0 | 23 | [7 empty] | 2017 |  | STD | [9 empty] | cancelled by applicant
WMECO | Lee | 6B1571-2017 | 01238 | 4993 | Solar | 16B1 | 2017-08-24 | 2017-09-26 | 24 | 15 | 9 | 2017-09-27 | 2018-06-20 | 191 | 62 | 129 | [10 empty] | 2018-06-21 | 2018-11-05 | 98 |  | 98 | [5 empty] | 2018-11-09 |  |  |  | STD | [9 empty] | cancelled
WMECO | West Springfield | 6S3712-2017 | 01089 | 20 | Solar | 21N4 | 2017-08-24 | 2017-09-19 | 19 | 4 | 15 | 2017-09-20 | 2017-10-16 | 19 | 0 | 19 | [20 empty] | 2017-10-16 |  | 2017 |  | EXP | [6 empty] | 2017-12-18 | 2017-12-21 | 2017-12-28 | on line
WMECO | Greenfield | 6A2815-2017 | 01301 | 7190 | Solar | 21C1 | 2017-08-29 | 2017-09-21 | 18 | 4 | 14 | 2017-09-22 |  | -30681 | [24 empty] | 2018-08-18 |  | STD | [9 empty] | sent 10 day notice - cancelled by applicant
WMECO | Erving | 6A2826-2017 | 01344 | 990 | Solar | 21B8 | 2017-09-01 | 2017-10-12 | 30 | 20 | 10 | 2017-10-13 | 2018-02-09 | 86 | 47 | 39 | [10 empty] | 2018-02-09 | 2018-07-19 | 115 | 32 | 83 | 2018-07-20 |  | -30896 |  |  | 2018-08-15 |  | Not supplied |  | COMP | [8 empty] | 2020-09-11 | on line
WMECO | Springfield | 6S3764-2017 | 01105 | 72 | Solar | 5J16 | 2017-09-08 | 2017-09-21 | 10 | 7 | 3 | 2017-09-22 | 2017-12-07 | 55 | 33 | 22 | [20 empty] | 2017-12-08 |  | 11/17 |  | EXP | [9 empty] | cancelled
WMECO | Cummington | 6A2837-2017 | 01026 | 999 | Solar | 18K3 | 2017-09-11 | 2017-10-12 | 24 | 16 | 8 | 2017-10-13 |  | -30696 | [24 empty] | Fall 2018 |  | STD | [9 empty] | cancelled by applicant
WMECO | Leverett | 6A2858-2017 | 01054 | 366.3 | Solar | 18G7 | 2017-09-14 | 2017-09-27 | 10 | 9 | 1 | 2017-09-28 | 2017-11-02 | 26 | 7 | 19 | [10 empty] | 2017-11-03 | 2018-01-23 | 58 | 0 | 58 | [5 empty] | 2018-02-01 |  | 2018-01-20 |  | STD | [8 empty] | 2019-02-14 | on line
WMECO | Springfield | 6S3788-2017 | 01105 | 57.6 | Solar | 8C26 | 2017-09-19 | 2017-09-28 | 8 | 7 | 1 | 2017-09-29 | 2018-01-22 | 82 | 53 | 29 | [20 empty] | 2018-01-22 |  | 2018-10-26 |  | EXP | [8 empty] | 2019-04-26 | on line
WMECO | Springfield | 6S3797-2017 | 01103 | 450 | Natural Gas | 8C31 | 2017-09-20 | 2017-11-06 | 34 | 24 | 10 | 2017-11-07 | 2017-12-05 | 21 | 6 | 15 | 2017-12-06 | 2018-02-26 | 59 | 40 | 19 | [15 empty] | 2018-03-06 |  | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Amherst | 6A2885-2017 | 01002 | 2000 | Diesel | 17K4, (17K5 N.O.) | 2017-09-21 | 2017-10-18 | 20 | 13 | 7 | 2017-10-19 | 2018-02-28 | 95 | 26 | 69 | [20 empty] | 2018-04-10 |  | Sept 2018 |  | EXP | [8 empty] | 2018-11-20 | on line
WMECO | South Deerfield | 6A2888-2017 | 01373 | 57.5 | Solar | 22B1 | 2017-09-22 | 2017-10-05 | 10 | 5 | 5 | 2017-10-06 | 2017-11-07 | 23 | 21 | 2 | 2017-11-08 | 2017-11-14 | 5 | 0 | 5 | [15 empty] | 2017-11-28 |  | Nov 2017 |  | EXP | [8 empty] | 2018-04-20 | on line
WMECO | South Deerfield | 6A2889-2017 | 01373 | 57 | Solar | 22B1 | 2017-09-22 | [31 empty] | Nov 2017 |  | EXP | [9 empty] | 3 phase facility, cancelled by applicant
WMECO | Pittsfield | 6B1612-2017 | 01201 | 22.8 | Solar | 30B3 | 2017-09-22 | 2017-10-10 | 13 | 9 | 4 | 2017-10-11 |  | -30694 | [24 empty] | 12/17 |  | EXP | [9 empty] | cancelled
WMECO | Otis | 6B1616-2017 | 01253 | 24 | Solar | 19J4 | 2017-09-26 | 2017-10-04 | 7 | 5 | 2 | 2017-10-05 | 2018-09-24 | 253 |  | 253 | 2018-09-25 | 2018-10-23 | 21 |  | 21 | [15 empty] | 2018-10-23 |  | 2017-11-22 |  | EXP | [9 empty] | in construction phase
WMECO | Southwick | 6S3810-2017 | 01077 | 4980 | Solar | 29A5 | 2017-09-27 | 2017-09-29 | 3 | 0 | 3 | 2017-10-02 |  | -30687 | [26 empty] | STD | [9 empty] | negotiated 10 days, cancelled by applicant
WMECO | Easthampton | 6A2904-2017 | 01027 | 2460 | Solar | 15A2 | 2017-09-28 | 2017-09-29 | 2 | 0 | 2 | 2017-10-02 | 2017-11-21 | 37 | 10 | 27 | [10 empty] | 2017-11-22 | 2018-02-09 | 58 | 0 | 58 | 2018-02-12 |  | -30782 |  |  | 2018-02-20 |  | Q4 2018 |  | STD | [8 empty] | 2020-09-22 | on line
WMECO | Shelburne Falls | 6A2914-2017 | 01370 | 60 | Solar | 22B5 | 2017-09-28 | 2017-10-17 | 14 | 11 | 3 | 2017-10-18 | 2017-10-27 | 8 | 4 | 4 | 2017-10-27 | 2017-12-06 | 29 | 3 | 26 | [15 empty] | 2017-12-14 |  | Nov 2017 |  | EXP | [6 empty] | 2018-05-15 | 2018-05-17 | 2018-05-17 | on line
WMECO | Shelburne Falls | 6A2915-2017 | 01370 | 50 | Solar | 22B5 | 2017-09-28 | 2017-10-17 | 14 | 11 | 3 | 2017-10-18 |  | -30699 | [24 empty] | Nov 2017 |  | EXP | [9 empty] | cancelled
WMECO | Dalton | 6B1618-2017 | 01226 | 9.28 | Solar | 19A2 | 2017-09-28 | [31 empty] | 2017-12-01 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Hinsdale | 6B1620-2017 | 01235 | 3000 | Solar | 18C2 | 2017-09-28 | 2017-10-04 | 5 | 2 | 3 | 2017-10-05 | 2017-10-24 | 14 | 4 | 10 | [10 empty] | 2017-10-25 | 2018-02-27 | 90 | 0 | 90 | 2018-02-28 |  | -30794 |  |  | 2018-02-27 |  | 12.18 |  | STD | [8 empty] | 2021-10-15 | on line
WMECO | Otis | 6B1625-2017 | 01253 | 24 | Solar | 19J4 | 2017-09-29 | 2017-10-04 | 4 | 2 | 2 | 2017-10-05 | 2018-09-24 | 253 |  | 253 | 2018-09-25 | 2018-10-23 | 21 |  | 21 | [15 empty] | 2018-10-23 |  | Nov 22 |  | EXP | [8 empty] | 2021-12-10 | on line
WMECO | Hinsdale | 6B1626-2017 | 01235 | 2200 | Solar | 18C2 | 2017-09-29 | 2017-10-05 | 5 | 3 | 2 | 2017-10-06 |  | -30691 | [24 empty] | 2018-08-31 |  | STD | [9 empty] | sent 10 day notice, negotiated 20 days, withdrawn after applicant did not execute Impact Study, withdrawn
WMECO | West Springfield | 6S3822-2017 | 01089 | 46.8 | Solar | 16C15 | 2017-10-02 | 2017-11-10 | 30 | 26 | 4 | 2017-11-13 | 2018-01-26 | 55 | 40 | 15 | [20 empty] | 2018-01-26 |  | 2017-11-01 |  | EXP | [6 empty] | 2018-04-02 | 2018-04-10 | 2018-04-13 | on line
WMECO | Russell | 6A2932-2017 | 01071 | 2988 | Solar | 19J2 | 2017-10-04 | 2017-10-17 | 10 | 8 | 2 | 2017-10-18 | 2017-11-27 | 29 | 3 | 26 | [10 empty] | 2017-11-28 | 2018-05-24 | 128 | 60 | 68 | 2018-06-06 |  | -30864 |  |  | 2018-06-01 |  | 2019 |  | COMP | [8 empty] | 2020-10-26 | on line
WMECO | Tolland | 6B1628-2017 | 01034 | 4980 | Solar | 19J4 | 2017-10-04 | 2017-10-17 | 10 | 7 | 3 | 2017-10-18 | 2017-12-11 | 39 | 16 | 23 | [10 empty] | 2017-12-12 | 2018-02-20 | 51 | 0 | 51 | 2018-03-01 |  | -30795 |  |  | 2018-02-27 |  | 2019 |  | COMP | [8 empty] | 2020-12-28 | on line
WMECO | Pittsfield | 6B1632-2017 | 01201 | 4987 | Solar | 15E2 | 2017-10-06 | 2017-10-17 | 8 | 4 | 4 | 2017-10-18 |  | -30699 | [24 empty] | Summer 2018 |  | STD | [9 empty] | cancelled
WMECO | Montague | 6A2951-2017 | 01349 | 800 | Solar | 21C2 | 2017-10-11 | 2017-12-15 | 48 | 45 | 3 | 2017-12-18 | 2018-02-21 | 48 | 28 | 20 | [10 empty] | 2018-02-22 | 2018-05-08 | 54 | 22 | 32 | 2018-05-09 |  | -30844 |  |  | 2018-07-19 |  | 6/31/2018 |  | STD | [8 empty] | 2020-12-31 | on line
WMECO | Windsor | 6B1641-2017 | 01270 | 999 | Solar | 18C1 | 2017-10-12 | 2017-11-16 | 26 | 19 | 7 | 2017-11-17 | 2017-12-27 | 29 | 24 | 5 | [10 empty] | 2017-12-28 | 2018-04-27 | 87 | 42 | 45 | [5 empty] | 2018-10-26 |  | Fall 2018 |  | STD | [8 empty] | 2020-12-29 | on line
WMECO | Springfield | 6S3848-2017 | 01119 | 600 | Diesel | 20A14 | 2017-10-12 | 2017-11-06 | 18 | 13 | 5 | 2017-11-07 | 2018-01-23 | 56 | 35 | 21 | 2018-01-24 | 2018-04-02 | 49 | 41 | 8 | [15 empty] | 2018-04-18 |  | 2017-12-15 |  | EXP | [6 empty] | 2018-04-25 | 2018-06-07 | 2018-06-07 | on line
WMECO | Springfield | 6S3870-2017 | 01103 | 1140 | Solar | 8C31 | 2017-10-18 | 2017-11-06 | 14 | 12 | 2 | 2017-11-07 | 2018-04-20 | 119 | 71 | 48 | [20 empty] | 2018-04-26 |  | 2018-11-30 |  | EXP | [8 empty] | 2020-07-22 | behind two other apps
WMECO | Turners Falls | 6A2995-2017 | 01349 | 996 | Solar | 21C2 | 2017-10-30 | 2017-11-16 | 14 | 8 | 6 | 2017-11-17 | 2018-01-08 | 37 | 26 | 11 | [10 empty] | 2018-01-05 | 2018-06-11 | 112 | 94 | 18 | [5 empty] | 2018-09-20 |  | Not supplied |  | STD | [8 empty] | 2019-12-24 | on line
WMECO | Westhampton | 6A3031-2017 | 01027 | 4980 | Solar | 15A3 | 2017-11-13 | 2017-12-15 | 25 | 22 | 3 | 2017-12-18 | 2018-01-08 | 16 | 2 | 14 | [10 empty] | 2018-01-09 | 2018-04-02 | 60 | 11 | 49 | 2018-04-05 |  | -30820 |  |  | 2018-04-13 |  | 2019 |  | COMP | [8 empty] | 2022-01-26 | on line
WMECO | Agawam | 6S3940-2017 | 01001 | 366.3 | Solar | 16C16 | 2017-11-20 | 2017-12-15 | 20 | 17 | 3 | 2017-12-18 | 2018-02-28 | 53 | 44 | 9 | 2018-03-01 | 2018-03-14 | 10 | 8 | 2 | [15 empty] | 2018-03-29 |  | Not supplied |  | EXP | [6 empty] | 2018-10-03 | 2018-10-03 | 2018-10-05 | on line
WMECO | Lanesborough | 6B1701-2017 | 01237 | 4536 | Solar | 15E2 | 2017-11-21 | 2017-12-22 | 24 | 16 | 8 | 2017-12-22 | 2018-03-12 | 57 | 36 | 21 | [10 empty] | 2018-03-13 | 2018-06-15 | 69 | 4 | 65 | 2018-07-26 |  | -30900 |  |  | 2018-06-28 |  | asap |  | COMP | [8 empty] | 2022-12-09 | on line
WMECO | Lanesborough | 6B1702-2017 | 01237 | 3600 | Solar | 15E1 | 2017-11-21 | 2017-12-22 | 24 | 16 | 8 | 2017-12-22 | 2018-03-12 | 57 | 51 | 6 | [10 empty] | 2018-03-13 | 2018-06-15 | 69 | 4 | 65 | 2018-07-18 |  | -30894 |  |  | 2018-06-28 |  | asap |  | STD | [8 empty] | 2022-12-09 | on line
WMECO | Hadley | 6A3069-2017 | 01035 | 2990 | Solar | 18G5 | 2017-11-27 | 2017-12-18 | 16 | 13 | 3 | 2017-12-19 |  | -30743 | [24 empty] | 2018-10-01 |  | STD | [9 empty] | cancelled by applicant
WMECO | Hadley | 6A3073-2017 | 01035 | 2000 | Solar | 18G5 | 2017-11-27 | 2017-12-18 | 16 | 13 | 3 | 2017-12-19 |  | -30743 | [24 empty] | 2018-10-01 |  | STD | [9 empty] | cancelled
WMECO | Windsor | 6B1708-2017 | 01027 | 2573 | Solar | 18C1 | 2017-11-27 | 2017-12-15 | 15 | 13 | 2 | 2017-12-15 |  | -30741 | [24 empty] | 2019 |  | EXP | [9 empty] | on hold behind another application, cancelled by applicant
WMECO | Montague | 6A3081-2017 | 01376 | 3770 | Solar | 21C2 | 2017-11-29 | 2018-02-28 | 66 | 37 | 29 | 2018-03-01 | 2018-06-11 | 73 | 63 | 10 | [10 empty] | 2018-06-12 | 2018-10-31 | 102 |  | 102 | [5 empty] | 2018-10-29 |  | August 2018 |  | STD | [8 empty] | 2021-11-23 | on line
WMECO | Worthington | 6A3090-2017 | 01098 | 8300 | Solar | 18K3 | 2017-12-01 | 2017-12-18 | 12 | 9 | 3 | 2017-12-19 |  | -30743 | [24 empty] | 2018-08-01 |  | STD | [9 empty] | cancelled by applicant
WMECO | Greenfield | 6A3094-2017 | 01301 | 1000 | Solar | 22B7 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 | 2018-05-03 | 95 | 70 | 25 | [10 empty] | 2018-05-04 | 2018-09-17 | 97 |  | 97 | [5 empty] | 2018-11-20 |  | 2018-03-01 |  | COMP | [9 empty] | sent 10 day notice for missed deadline for executing Impact Study Agreement, 2 options, negotiated 20 days
WMECO | Chesterfield | 6A3095-2017 | 01012 | 500 | Solar | 18K3 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30746 | [24 empty] | 2018-03-01 |  | STD | [9 empty] | cancelled by applicant
WMECO | Greenfield | 6A3096-2017 | 01301 | 500 | Solar | 22B7 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30746 | [24 empty] | 2018-03-01 |  | STD | [9 empty] | cancelled by applicant
WMECO | Northfield | 6A3097-2017 | 01360 | 1000 | Solar | 21B8 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 | 2018-05-03 | 95 | 65 | 30 | [10 empty] | 2018-05-04 | 2018-10-19 | 121 |  | 121 | [5 empty] | 2018-11-20 |  | 2018-03-01 |  | STD | [9 empty] | cancelled by applicant
WMECO | Northfield | 6A3098-2017 | 01360 | 500 | Solar | 21B8 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30746 | [24 empty] | 2018-03-01 |  | STD | [9 empty] | cancelled by applicant
WMECO | Northfield | 6A3099-2017 | 01360 | 500 | Solar | 21B8 | 2017-12-04 | 2017-12-21 | 14 | 11 | 3 | 2017-12-22 |  | -30746 | [24 empty] | 2018-03-01 |  | STD | [9 empty] | cancelled
WMECO | Pittsfield | 6B1724-2017 | 01201 | 1380 | Solar | 30B5 | 2017-12-05 | 2018-01-16 | 31 | 23 | 8 | 2018-01-17 | 2018-02-28 | 31 | 24 | 7 | [10 empty] | 2018-03-01 | 2018-07-16 | 98 | 40 | 58 | 2018-07-17 |  | -30893 |  |  | 2018-07-16 |  | Not supplied |  | STD | [8 empty] | 2020-12-30 | on line
WMECO | Ludlow | 6S3969-2017 | 01056 | 3969 | Solar | 27A5 | 2017-12-05 | 2018-02-08 | 48 | 30 | 18 | 2018-02-09 | 2018-04-27 | 56 | 29 | 27 | [10 empty] | 2018-04-30 | 2018-10-15 | 121 |  | 121 | [5 empty] | 2018-10-27 |  | 2018 |  | COMP | [8 empty] | 2021-01-29 | on line
WMECO | Lanesborough | 6B1728-2017 | 01237 | 3000 | Solar | 15E1 | 2017-12-07 | [31 empty] | 2018-12-31 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Greenfield | 6A3130-2017 | 01301 | 4500 | Solar | 21C1 | 2017-12-14 | 2017-12-27 | 10 | 2 | 8 | 2017-12-28 | 2018-02-14 | 35 | 7 | 28 | [10 empty] | 2018-02-15 | 2018-07-25 | 115 | 42 | 73 | 2018-07-26 |  | -30900 |  |  | 2020-03-23 |  | 2018-12-21 |  | STD | [8 empty] | 2024-07-23 | in construction phase
WMECO | Lanesborough | 6B1736-2017 | 01237 | 4536 | Solar | 15E1 | 2017-12-14 | 2017-12-22 | 7 | 0 | 7 | 2017-12-22 | 2018-05-31 | 115 | 106 | 9 | [10 empty] | 2018-06-01 | 2018-08-27 | 62 |  | 62 | [5 empty] | 2018-09-25 |  | ASAP |  | STD | [8 empty] | 2022-12-09 | on line
WMECO | Lanesborough | 6B1737-2017 | 01237 | 3000 | Solar | 15E1 | 2017-12-14 | 2017-12-15 | 2 | 0 | 2 | 2017-12-18 | 2018-01-16 | 22 | 11 | 11 | [10 empty] | 2018-09-20 | 2018-10-16 | 19 |  | 19 | [5 empty] | 2019-05-21 |  | 2018-12-31 |  | STD | [9 empty] | cancelled
WMECO | Easthampton | 6A3136-2017 | 01027 | 4998 | Solar | 15A3 | 2017-12-15 | 2018-01-02 | 13 | 5 | 8 | 2018-01-03 | 2018-06-05 | 110 | 97 | 13 | [10 empty] | 2018-06-06 | 2018-10-22 | 99 |  | 99 | [5 empty] | 2018-10-18 |  | 2019-01-14 |  | COMP | [8 empty] | 2022-11-30 | on line
WMECO | Pittsfield | 6B1741-2017 | 01201 | 5000 | Solar | 30B2 | 2017-12-18 | 2017-12-27 | 8 | 1 | 7 | 2017-12-28 | 2018-02-28 | 45 | 12 | 33 | [10 empty] | 2018-03-01 | 2018-09-24 | 148 |  | 148 | [5 empty] | 2018-10-05 |  | 2019-01-14 |  | STD | [9 empty] | cancelled
WMECO | West Springfield | 6S4000-2017 | 01089 | 180 | Solar | 16C12 | 2017-12-18 | 2018-02-02 | 35 | 6 | 29 | 2018-02-05 | 2018-03-12 | 26 | 7 | 19 | [20 empty] | 2018-03-15 |  | 2018-03-01 |  | EXP | [9 empty] | withdrawn
WMECO | Conway | 6A3138-2017 | 01341 | 2178 | Solar | 22B1 | 2017-12-19 | 2018-01-10 | 17 | 13 | 4 | 2018-01-11 |  | -30760 | [24 empty] | Dec 2018 |  | STD | [9 empty] | cancelled
WMECO | Springfield | 6S4010-2017 | 01118 | 99.9 | Solar | 20A32 | 2017-12-20 | 2018-01-10 | 16 | 9 | 7 | 2018-01-11 | 2018-02-09 | 22 | 2 | 20 | [20 empty] | 2018-02-09 |  | 2018-05-01 |  | EXP | [8 empty] | 2019-10-03 | on line
WMECO | Southwick | 6S4042-2018 | 01077 | 9950 | Solar | 29A1 | 2018-01-03 | 2018-02-08 | 27 | 21 | 6 | 2018-02-09 |  | -30781 | [24 empty] | 2018-12-10 |  | STD | [9 empty] | multiple options, negotiated 15 days
WMECO | Hatfield | 6A3180-2018 | 01038 | 500 | Solar | 18G5 | 2018-01-08 | 2018-01-31 | 18 | 1 | 17 | 2018-02-01 |  | -30775 | 11 | [23 empty] | 2018-04-01 |  | STD | [9 empty] | cancelled
WMECO | Becket | 6B1756-2018 | 01223 | 33.3 | Solar | 19J6 | 2018-01-12 | 2018-01-22 | 7 | 4 | 3 | 2018-01-23 | 2018-02-28 | 27 | 0 | 27 | [20 empty] | 2018-02-02 |  | 2018-05-01 |  | EXP | [6 empty] | 2018-07-11 | 2018-07-17 | 2018-07-18 | on line
WMECO | Deerfield | 6A3216-2018 | 01373 | 500 | Solar | 22B3 | 2018-01-16 | 2018-01-31 | 12 | 5 | 7 | 2018-02-01 | 2018-03-13 | 29 | 22 | 7 | [10 empty] | 2018-03-14 | 2018-04-30 | 34 | 2 | 32 | [7 empty] | 2018-12-31 |  | STD | [9 empty] | cancelled by applicant
WMECO | Blandford | 6B1761-2018 | 01008 | 4450 | Solar | 19J6 | 2018-01-17 | 2018-01-29 | 9 | 1 | 8 | 2018-01-30 |  | -30773 | [26 empty] | STD | [9 empty] | cancelled
WMECO | Erving | 6A3219-2018 | 01344 | 4980 | Solar | 21C8 | 2018-01-18 | 2018-01-31 | 10 | 1 | 9 | 2018-02-01 | 2018-05-03 | 66 | 43 | 23 | [10 empty] | 2018-05-04 | 2018-08-03 | 66 | 8 | 58 | [5 empty] | 2018-08-10 |  | Summer 2018 |  | COMP | [8 empty] | 2022-11-25 | on line
WMECO | Deerfield | 6A3221-2018 | 01373 | 1000 | Solar | 22B3 | 2018-01-18 | 2018-01-30 | 9 | 3 | 6 | 2018-01-31 | 2018-02-06 | 5 |  | 5 | [22 empty] | 2018-12-31 |  | STD | [9 empty] | cancelled
WMECO | Peru | 6B1762-2018 | 01235 | 3320 | Solar | 18C2 | 2018-01-18 | 2018-01-30 | 9 | 2 | 7 | 2018-01-31 | 2018-03-09 | 28 | 21 | 7 | [10 empty] | 2018-03-12 | 2018-05-11 | 45 | 0 | 45 | 2018-05-16 |  | -30849 |  |  | 2018-05-18 |  | Q4 2018 |  | STD | [8 empty] | 2020-11-18 | on line
WMECO | Northfield | 6A3238-2018 | 01360 | 5000 | Solar | 21B8 | 2018-01-30 | 2018-02-21 | 17 | 7 | 10 | 2018-02-22 | 2018-10-26 | 177 | 165 | 12 | [10 empty] | 2018-10-29 |  | -30967 | [7 empty] | 2018-11-30 |  | 2018-12-31 |  | STD | [9 empty] | cancelled
WMECO | Windsor | 6B1777-2018 | 01270 | 20 | Solar | 18C1 | 2018-01-31 | 2018-02-08 | 7 | 5 | 2 | 2018-02-09 | 2018-04-17 | 48 | 24 | 24 | [20 empty] | 2018-04-17 |  | 2018-03-15 |  | EXP | [6 empty] | 2018-06-12 | 2018-06-15 | 2018-06-18 | on line
WMECO | Leverett | 6A3271-2018 | 01054 | 3120 | Solar | 18G7 | 2018-02-09 | 2018-02-21 | 9 | 6 | 3 | 2018-02-22 | 2018-04-04 | 30 | 28 | 2 | [10 empty] | 2018-04-05 | 2018-05-24 | 36 | 0 | 36 | [5 empty] | 2018-06-28 |  | 2018-12-01 |  | COMP | [9 empty] | cancelled
WMECO | Pittsfield | 6B1787-2018 | 01201 | 2574 | Solar | 30B2 | 2018-02-09 | 2018-03-05 | 17 | 4 | 13 | 2018-03-06 | 2018-03-14 | 7 |  | 7 | [10 empty] | 2019-04-05 | 2019-11-22 | 166 |  | 166 | [5 empty] | 2020-03-23 |  | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Northfield | 6A3277-2018 | 01360 | 3575 | Solar | 21B8 | 2018-02-12 | 2018-03-09 | 20 | 12 | 8 | 2018-03-12 | 2018-03-19 | 6 |  | 6 | [22 empty] | 2018-03-30 |  | STD | [9 empty] | cancelled
WMECO | Whately | 6A3279-2018 | 01093 | 5225 | Solar | 18G8 | 2018-02-12 | 2018-02-22 | 9 | 0 | 9 | 2018-02-23 | 2018-05-10 | 55 | 46 | 9 | [10 empty] | 2018-05-11 | 2018-10-11 | 110 |  | 110 | [7 empty] | 2018-08-30 |  | COMP | [9 empty] | cancelled
WMECO | Bernardston | 6A3280-2018 | 01337 | 1410 | Solar | 21C1 | 2018-02-12 | 2018-02-22 | 9 | 0 | 9 | 2018-02-23 | 2018-05-11 | 56 | 48 | 8 | [10 empty] | 2018-05-14 | 2018-11-14 | 133 |  | 133 | [5 empty] | 2018-11-28 |  | 2018-08-30 |  | STD | [8 empty] | 2022-10-31 | completed
WMECO | Westhampton | 6A3288-2018 | 01027 | 22.8 | Solar | 15A3 | 2018-02-14 | 2018-02-22 | 7 | 4 | 3 | 2018-02-23 | 2018-03-05 | 7 | 3 | 4 | [20 empty] | 2018-03-07 |  | 2018-03-15 |  | EXP | [6 empty] | 2018-05-30 | 2018-06-13 | 2018-06-13 | on line
WMECO | Whately | 6A3295-2018 | 01093 | 1000 | Solar | 18G8 | 2018-02-16 | 2018-02-22 | 5 | 3 | 2 | 2018-02-23 | 2018-07-31 | 113 | 105 | 8 | [10 empty] | 2018-08-01 | 2018-11-18 | 78 |  | 78 | [7 empty] | 2018-12-31 |  | COMP | [9 empty] | cancelled
WMECO | Blandford | 6B1793-2018 | 01008 | 4998 | Solar | 19J4 | 2018-02-16 | 2018-02-22 | 5 | 2 | 3 | 2018-02-23 | 2018-03-08 | 10 |  | 10 | [22 empty] | 2019-10-01 |  | STD | [9 empty] | withdrawn after missed deadlines, applicant does not want to proceed
WMECO | West Springfield | 6S4145-2018 | 01089 | 19.3 | Solar | 16C14 | 2018-02-16 | 2018-02-22 | 5 | 2 | 3 | 2018-02-23 | 2018-03-06 | 8 | 4 | 4 | [20 empty] | 2018-03-07 |  | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Ludlow | 6S4152-2018 | 01056 | 4998 | Solar | 19S3 | 2018-02-16 | 2018-02-22 | 5 | 2 | 3 | 2018-02-23 | 2018-06-20 | 84 | 67 | 17 | [10 empty] | 2018-06-21 | 2018-10-02 | 74 |  | 74 | [5 empty] | 2018-11-12 |  | 2019-10-01 |  | COMP | [8 empty] | 2022-12-16 | on line
WMECO | Ludlow | 6S4153-2018 | 01056 | 5000 | Solar | 19S3 | 2018-02-16 | 2018-02-22 | 5 | 2 | 3 | 2018-02-23 |  | -30791 | [24 empty] | 2019-10-01 |  | STD | [9 empty] | withdrawn
WMECO | Whately | 6A3297-2018 | 01373 | 1925 | Solar | 18G8 | 2018-02-20 | 2018-03-09 | 14 | 9 | 5 | 2018-03-12 | 2018-03-15 | 4 |  | 4 | [22 empty] | 2018-08-30 |  | STD | [9 empty] | cancelled
WMECO | Cheshire | 6B1794-2018 | 01225 | 1650 | Solar | 19A5 | 2018-02-20 | 2018-03-05 | 10 | 7 | 3 | 2018-03-06 |  | -30798 | [24 empty] | 2018-08-30 |  | STD | [9 empty] | 2 options, negotiated 10 days, cancelled by applicant
WMECO | Hinsdale | 6B1795-2018 | 01235 | 2200 | Solar | 18C2 | 2018-02-22 | 2018-03-14 | 15 | 11 | 4 | 2018-03-15 |  | -30805 | [24 empty] | 2018-08-31 |  | EXP | [9 empty] | withdrawn after missed deadlines, applicant does not want to proceed
WMECO | Bernardston | 6A3302-2018 | 01337 | 4160 | Solar | 21C1 | 2018-02-23 | 2018-03-14 | 14 | 10 | 4 | 2018-03-15 | 2018-03-16 | 2 |  | 2 | [22 empty] | 2018-03-01 |  | STD | [9 empty] | withdrawn
WMECO | Pittsfield | 6B1798-2018 | 01201 | 3250 | Solar | 30B5 | 2018-02-26 | 2018-03-28 | 23 | 19 | 4 | 2018-03-29 | 2018-05-14 | 33 | 17 | 16 | [10 empty] | 2018-05-15 | 2018-10-23 | 116 | 37 | 79 | [5 empty] | 2018-11-23 |  | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Southwick | 6S4177-2018 | 01077 | 248 | Solar | 29A1 | 2018-02-28 | 2018-03-29 | 22 | 19 | 3 | 2018-04-02 | 2018-04-23 | 16 | 4 | 12 | [20 empty] | 2018-04-23 |  | 5/2018 |  | EXP | [6 empty] | 2018-10-02 | 2018-10-02 | 2018-10-02 | on line
WMECO | Amherst | 6A3310-2018 | 01002 | 32.95 | Solar | 17K3 | 2018-03-01 | [31 empty] | March 2018 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Amherst | 6A3312-2018 | 01002 | 99.9 | Solar | 17K4, (17K5 N.O.) | 2018-03-02 | 2018-03-14 | 9 | 8 | 1 | 2018-03-15 | 2018-08-06 | 103 | 48 | 55 | [20 empty] | 2018-08-06 |  | 2018-06-01 |  | EXP | [8 empty] | 2019-01-10 | on line
WMECO | Shelburne Falls | 6A3316-2018 | 01370 | 900 | Solar | 22B5 | 2018-03-05 | 2018-06-20 | 78 | 72 | 6 | 2018-06-21 | 2018-06-21 | 1 |  | 1 | [10 empty] | 2018-10-09 | 2019-03-13 | 112 |  | 112 | [7 empty] | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Huntington | 6A3317-2018 | 01050 | 900 | Solar | 19J5 | 2018-03-05 | 2018-06-20 | 78 | 72 | 6 | 2018-06-21 | 2018-06-26 | 4 |  | 4 | [22 empty] | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Westhampton | 6A3322-2018 | 01027 | 2500 | Solar | 15A3 | 2018-03-06 | 2018-04-18 | 32 | 23 | 9 | 2018-04-19 | 2018-10-19 | 132 | 126 | 6 | [10 empty] | 2018-10-19 | 2018-12-18 | 43 |  | 43 | [5 empty] | 2019-01-27 |  | 2019-04-30 |  | STD | [9 empty] | cancelled
WMECO | Springfield | 6S4201-2018 | 01118 | 15.68 | Solar | 20A32 | 2018-03-13 | [31 empty] | 2018-04-05 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Russell | 6A3340-2018 | 01070 | 495 | Solar | 19J5 | 2018-03-14 | 2018-06-13 | 66 | 55 | 11 | 2018-06-14 | 2018-06-22 | 7 |  | 7 | [22 empty] | 2019-04-01 |  | EXP | [9 empty] | cancelled
WMECO | South Deerfield | 6A3341-2018 | 01373 | 2000 | Solar | 18G8 | 2018-03-15 | 2018-03-28 | 10 | 4 | 6 | 2018-03-29 |  | -30815 | [24 empty] | 2018-12-31 |  | STD | [9 empty] | withdrawn
WMECO | Conway | 6A3350-2018 | 01341 | 4400 | Solar | 38A1 | 2018-03-16 | 2018-04-18 | 24 | 17 | 7 | 2018-04-19 | 2018-05-11 | 17 | 11 | 6 | [10 empty] | 2018-05-14 | 2018-09-25 | 97 |  | 97 | [5 empty] | 2019-02-22 |  | 2018-12-01 |  | COMP | [8 empty] | 2021-07-28 | on line
WMECO | Pittsfield | 6B1811-2018 | 01201 | 4890 | Solar | 30B5 | 2018-03-16 | 2018-04-06 | 16 | 9 | 7 | 2018-04-09 | 2018-08-03 | 85 | 17 | 68 | [10 empty] | 2018-08-06 | 2018-11-16 | 75 |  | 75 | [7 empty] | 2018-12-01 |  | STD | [9 empty] | cancelled
WMECO | Pittsfield | 6B1817-2018 | 01201 | 187 | Solar | 30B5 | 2018-03-21 | 2018-04-03 | 10 | 3 | 7 | 2018-04-04 | 2018-04-27 | 18 | 15 | 3 | 2018-04-30 | 2018-07-20 | 60 | 22 | 38 | [15 empty] | 2018-09-17 |  | Not supplied |  | EXP | [8 empty] | 2019-07-30 | on line
WMECO | Pittsfield | 6B1818-2018 | 01201 | 191 | Solar | 30B4 | 2018-03-21 | 2018-04-03 | 10 | 3 | 7 | 2018-04-04 | 2018-04-13 | 8 |  | 8 | [22 empty] | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Pittsfield | 6B1819-2018 | 01201 | 249 | Solar | 30B7 | 2018-03-21 | 2018-04-04 | 11 | 5 | 6 | 2018-04-05 | 2018-05-24 | 36 | 22 | 14 | 2018-05-25 | 2018-09-17 | 82 |  | 82 | [15 empty] | 2018-10-18 |  | Not supplied |  | EXP | [8 empty] | 2020-04-14 | on line
WMECO | Dalton | 6B1825-2018 | 01226 | 4400 | Solar | 18C1 | 2018-03-21 | 2018-04-19 | 22 | 18 | 4 | 2018-04-20 | 2018-08-03 | 76 | 48 | 28 | [10 empty] | 2018-08-06 | 2018-11-29 | 84 |  | 84 | [5 empty] | 2018-11-30 |  | 2018-12-01 |  | STD | [8 empty] | 2021-05-25 | on line
WMECO | Springfield | 6S4229-2018 | 01119 | 14.4 | Solar | 20A35 | 2018-03-21 | [31 empty] | 2018-04-16 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Pittsfield | 6B1824-2018 | 01201 | 480 | Solar | 30B5 | 2018-03-22 | 2018-04-03 | 9 | 2 | 7 | 2018-04-04 | 2021-04-23 | 798 |  | 798 | [22 empty] | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Richmond | 6B1826-2018 | 01254 | 97.75 | Solar | 30B7 | 2018-03-22 | 2018-03-29 | 6 | 1 | 5 | 2018-04-02 | 2018-04-20 | 15 | 6 | 9 | [20 empty] | 2018-04-20 |  | 6/2018 |  | EXP | [8 empty] | 2019-08-28 | on line
WMECO | Pittsfield | 6B1831-2018 | 01201 | 350 | Solar | 19A5 | 2018-03-26 | 2018-07-03 | 72 | 60 | 12 | 2018-07-05 | 2019-07-01 | 258 |  | 258 | [22 empty] | 2018-12-01 |  | EXP | [9 empty] | withdrawn
WMECO | Granville | 6S4247-2018 | 01034 | 4455 | Solar | 29A5 | 2018-03-27 | 2018-04-11 | 12 | 4 | 8 | 2018-04-12 | 2018-06-11 | 43 | 32 | 11 | [10 empty] | 2018-06-12 | 2018-10-29 | 100 |  | 100 | [5 empty] | 2018-11-06 |  | Not supplied |  | COMP | [8 empty] | 2022-05-31 | on line
WMECO | Granville | 6S4248-2018 | 01034 | 996 | Solar | 29A5 | 2018-03-27 | 2018-04-11 | 12 | 4 | 8 | 2018-04-12 | 2018-10-29 | 143 |  | 143 | [10 empty] | 2018-10-29 | 2019-02-14 | 79 |  | 79 | [5 empty] | 2019-04-19 |  | Not supplied |  | COMP | [9 empty] | cancelled
WMECO | Pelham | 6A3370-2018 | 01543 | 4890 | Solar | 17K2 | 2018-03-28 | 2019-02-05 | 225 |  | 225 | 2019-02-05 | 2019-03-22 | 34 |  | 34 | [10 empty] | 2019-10-16 | 2020-01-07 | 60 |  | 60 | [7 empty] | Not supplied |  | STD | [9 empty] | withdrawn
WMECO | Plainfield | 6A3396-2018 | 01070 | 4998 | Solar | 18K3 | 2018-04-06 | 2018-07-05 | 65 | 60 | 5 | 2018-07-06 | 2018-07-30 | 17 |  | 17 | [10 empty] | 2019-01-18 | 2019-04-25 | 70 |  | 70 | [7 empty] | 2019-10-01 |  | STD | [9 empty] | cancelled
WMECO | Hinsdale | 6B1847-2018 | 01235 | 4998 | Solar | 18C2 | 2018-04-09 | 2018-05-07 | 21 | 15 | 6 | 2018-05-08 |  | -30843 | [24 empty] | 2019-10-01 |  | STD | [9 empty] | cancelled
WMECO | Springfield | 6S4298-2018 | 01104 | 500 | Solar | 21S6 | 2018-04-09 | 2018-05-02 | 18 | 14 | 4 | 2018-05-03 | 2018-05-15 | 9 | 7 | 2 | 2018-05-17 | 2018-06-07 | 16 |  | 16 | [5 empty] | 2018-05-16 |  | -30849 | [7 empty] | 2018-11-26 |  | 2018-06-15 |  | STD | [9 empty] | cancelled
WMECO | Agawam | 6S4299-2018 | 01001 | 576.6 | Solar | 16C16 | 2018-04-09 | 2018-05-02 | 18 | 14 | 4 | 2018-05-03 | 2018-05-15 | 9 | 7 | 2 | [10 empty] | 2018-05-16 | 2018-09-29 | 98 |  | 98 | [7 empty] | 2018-06-15 |  | STD | [9 empty] | cancelled
WMECO | Otis | 6B1854-2018 | 01253 | 1375 | Solar | 19J4 | 2018-04-16 | 2018-05-07 | 16 | 5 | 11 | 2018-05-08 | 2018-05-10 | 3 |  | 3 | [22 empty] | April 2019 |  | STD | [9 empty] | withdrawn
WMECO | Northfield | 6A3441-2018 | 01360 | 4988 | Solar | 21B8 | 2018-04-23 | 2018-05-14 | 16 | 6 | 10 | 2019-02-06 |  | -31039 | [24 empty] | 2018 |  | STD | [9 empty] | withdrawn
WMECO | Lanesborough | 6B1868-2018 | 01237 | 15.12 | Solar | 15E2 | 2018-04-27 | [31 empty] | 2018-05-21 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Springfield | 6S4359-2018 | 01129 | 12.32 | Solar | 20A34 | 2018-04-27 | [31 empty] | 2018-05-29 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S4367-2018 | 01104 | 800 | Solar | 5J15 | 2018-05-01 | 2018-06-05 | 26 | 17 | 9 | 2018-06-06 | 2018-07-18 | 31 |  | 31 | [10 empty] | 2018-09-26 | 2018-11-19 | 39 |  | 39 | [5 empty] | 2018-11-21 |  | 2018-08-31 |  | STD | [8 empty] | 2022-08-16 | on line
WMECO | Gill | 6A3473-2018 | 01354 | 132 | Solar | 21B8 | 2018-05-07 | 2018-06-11 | 26 | 20 | 6 | 2018-06-12 | 2018-06-19 | 6 |  | 6 | [22 empty] | 2018-08-01 |  | EXP | [9 empty] | cancelled
WMECO | Gill | 6A3474-2018 | 01354 | 2310 | Solar | 21B8 | 2018-05-08 | 2018-05-29 | 16 | 9 | 7 | 2018-05-30 | 2018-05-31 | 2 |  | 2 | [22 empty] | 2018-08-01 |  | STD | [9 empty] | cancelled
WMECO | Plainfield | 6A3478-2018 | 01070 | 990 | Solar | 18K3 | 2018-05-09 | 2018-06-20 | 31 | 22 | 9 | 2018-06-21 | 2018-07-02 | 8 |  | 8 | [22 empty] | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Shelburne | 6A3480-2018 | 01050 | 900 | Solar | 29R2 | 2018-05-09 | 2018-06-21 | 32 | 23 | 9 | 2018-06-22 | 2018-08-01 | 29 |  | 29 | [10 empty] | 2018-12-04 | 2019-05-17 | 119 |  | 119 | [5 empty] | 2019-06-26 |  | Not supplied |  | COMP | [9 empty] | withdrawn
WMECO | Lanesborough | 6B1875-2018 | 01237 | 990 | Solar | 15E2 | 2018-05-09 | 2018-06-20 | 31 | 22 | 9 | 2018-06-21 | 2018-07-05 | 11 |  | 11 | [22 empty] | Not supplied |  | STD | [9 empty] | withdrawn
WMECO | Granville | 6S4395-2018 | 01034 | 990 | Solar | 29A5 | 2018-05-09 | 2018-06-20 | 31 | 22 | 9 | 2018-06-21 | 2018-07-02 | 8 |  | 8 | [22 empty] | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Windsor | 6B1876-2018 | 01270 | 990 | Solar | 18C1 | 2018-05-10 | 2018-06-20 | 30 | 21 | 9 | 2018-06-21 | 2018-07-23 | 23 |  | 23 | [22 empty] | Not supplied |  | STD | [9 empty] | withdrawn
WMECO | Hatfield | 6A3483-2018 | 01038 | 249.8 | Solar | 18G5 | 2018-05-14 | 2018-06-06 | 18 | 5 | 13 | 2018-06-07 | 2018-08-15 | 50 |  | 50 | [10 empty] | 2018-12-02 | 2018-12-03 | 1 |  | 1 | [7 empty] | 2018-12-31 |  | EXP | [9 empty] | withdrawn
WMECO | Hadley | 6A3484-2018 | 01035 | 499.9 | Solar | 17K5 | 2018-05-14 | 2018-06-06 | 18 | 6 | 12 | 2018-06-07 | 2018-08-06 | 43 |  | 43 | [22 empty] | 2018-12-31 |  | STD | [9 empty] | cancelled
WMECO | Springfield | 6S4407-2018 | 01107 | 240 | Solar | 21S6 | 2018-05-14 | 2018-05-31 | 14 | 5 | 9 | 2018-06-01 | 2018-06-14 | 10 | 8 | 2 | [20 empty] | 2018-06-28 |  | 2018-08-17 |  | EXP | [8 empty] | 2019-12-12 | on line
WMECO | Springfield | 6S4409-2018 | 01104 | 199.8 | Solar | 5J13 | 2018-05-14 | 2018-06-13 | 23 | 14 | 9 | 2018-06-14 | 2018-10-23 | 94 |  | 94 | 2018-10-24 |  | -30964 | [17 empty] | 2018-11-27 |  | 2018-09-01 |  | EXP | [8 empty] | 2020-09-04 | on line
WMECO | Conway | 6A3492-2018 | 01341 | 900 | Solar | 38A1 | 2018-05-15 | 2018-06-20 | 27 | 21 | 6 | 2018-06-21 | 2018-07-06 | 12 |  | 12 | [10 empty] | 2018-12-04 | 2019-05-17 | 119 |  | 119 | [5 empty] | 2019-06-13 |  | Not supplied |  | COMP | [9 empty] | cancelled
WMECO | Worthington | 6A3493-2018 | 01098 | 990 | Solar | 18K3 | 2018-05-15 | 2018-06-20 | 27 | 21 | 6 | 2018-06-21 | 2018-07-06 | 12 |  | 12 | [22 empty] | Not supplied |  | STD | [9 empty] | withdrawn
WMECO | Pittsfield | 6B1881-2018 | 01201 | 250 | Solar | 15E2 | 2018-05-15 | 2018-09-21 | 94 | 0 | 94 | 2018-09-21 | 2018-11-19 | 42 |  | 42 | [20 empty] | 2018-11-26 |  | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Pittsfield | 6B1882-2018 | 01201 | 250 | Solar | 15E2 | 2018-05-15 | 2018-09-21 | 94 | 0 | 94 | 2018-09-21 | 2018-11-19 | 42 |  | 42 | [20 empty] | 2018-11-26 |  | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Shelburne | 6A3497-2018 | 01370 | 990 | Solar | 22B5 | 2018-05-16 | 2018-06-20 | 26 | 21 | 5 | 2018-06-21 | 2019-03-29 | 202 |  | 202 | [22 empty] | Not supplied |  | STD | [9 empty] | withdrawn
WMECO | Worthington | 6A3498-2018 | 01098 | 990 | Solar | 18K3 | 2018-05-16 | 2018-06-20 | 26 | 21 | 5 | 2018-06-21 | 2018-07-27 | 27 |  | 27 | [22 empty] | Not supplied |  | STD | [9 empty] | withdrawn
WMECO | Lee | 6B1887-2018 | 01238 | 480 | Solar | 16B1 | 2018-05-17 | 2018-09-19 | 90 | 0 | 90 | 2018-09-19 | 2018-11-05 | 34 |  | 34 | [10 empty] | 2018-11-14 |  | -30979 | [9 empty] | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S4424-2018 | 01119 | 19.2 | Solar | 20A33 | 2018-05-17 | 2018-11-08 | 126 |  | 126 | 2018-11-08 |  | -30975 | [24 empty] | 2018-07-17 |  | EXP | [9 empty] | withdrawn
WMECO | Ashfield | 6A3509-2018 | 01330 | 4980 | Solar | 38A1 | 2018-05-21 | 2018-06-21 | 24 | 19 | 5 | 2018-06-22 | 2018-07-31 | 28 |  | 28 | [22 empty] | Not supplied |  | STD | [9 empty] | withdrawn
WMECO | Huntington | 6A3510-2018 | 01050 | 4980 | Solar | 19J5 | 2018-05-21 | 2018-06-21 | 24 | 19 | 5 | 2018-06-22 | 2018-07-31 | 28 |  | 28 | [22 empty] | Not supplied |  | STD | [9 empty] | withdrawn
WMECO | Deerfield | 6A3512-2018 | 01342 | 2000 | Solar | 22B3 | 2018-05-22 | 2018-06-05 | 11 | 9 | 2 | 2018-06-06 | 2018-07-16 | 29 | 17 | 12 | [10 empty] | 2018-07-17 | 2018-11-02 | 79 |  | 79 | [5 empty] | 2018-11-29 |  | 2019-01-31 |  | COMP | [8 empty] | 2022-09-20 | on line
WMECO | Granville | 6S4443-2018 | 01034 | 4980 | Solar | 29A5 | 2018-05-23 | 2018-06-21 | 22 | 17 | 5 | 2018-06-22 | 2018-07-30 | 27 |  | 27 | [22 empty] | Not supplied |  | STD | [9 empty] | withdrawn
WMECO | Deerfield | 6A3523-2018 | 01342 | 72 | Solar | 22B1 | 2018-05-24 | 2018-06-20 | 20 | 13 | 7 | 2018-06-21 | 2018-07-16 | 18 |  | 18 | [20 empty] | 2019-08-30 |  | 2018-09-01 |  | EXP | [8 empty] | 2019-10-02 | on line
WMECO | Springfield | 6S4457-2018 | 01104 | 975 | Solar | 5J9 | 2018-05-25 | 2018-06-11 | 12 | 8 | 4 | 2018-06-12 | 2018-09-20 | 73 |  | 73 | [22 empty] | 2018-02-01 |  | STD | [9 empty] | cancelled
WMECO | Springfield | 6S4459-2018 | 01129 | 333.3 | Solar | 20A23 | 2018-05-25 | 2018-06-20 | 19 | 5 | 14 | 2018-06-21 | 2018-06-22 | 2 |  | 2 | [20 empty] | 2019-01-07 |  | 2018-09-01 |  | EXP | [9 empty] | cancelled
WMECO | Southampton | 6A3534-2018 | 01073 | 5000 | Solar | 15A1 | 2018-05-30 | 2018-08-02 | 47 | 39 | 8 | 2018-08-03 | 2018-09-11 | 28 |  | 28 | [22 empty] | 2019-11-01 |  | STD | [9 empty] | withdrawn
WMECO | Pittsfield | 6B1906-2018 | 01201 | 2656 | Solar | 30B2 | 2018-05-30 | 2018-07-31 | 45 | 34 | 11 | 2018-08-01 | 2020-03-18 | 426 |  | 426 | [22 empty] | Not supplied |  | STD | [9 empty] | withdrawn
WMECO | Blandford | 6B1907-2018 | 01008 | 4980 | Solar | 19J2 | 2018-05-30 | 2018-09-12 | 76 | 49 | 27 | 2018-09-13 |  | -30935 | [26 empty] | EXP | [9 empty] | withdrawn
WMECO | Springfield | 6S4467-2018 | 01104 | 210 | Solar | 21S7 | 2018-05-31 | 2018-06-27 | 20 | 3 | 17 | 2018-06-28 | 2018-08-08 | 30 |  | 30 | 2018-11-13 | 2018-11-20 | 6 |  | 6 | [15 empty] | 2018-11-21 |  | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Granville | 6S4468-2018 | 01034 | 594 | Solar | 29A5 | 2018-05-31 | 2018-06-25 | 18 | 14 | 4 | 2018-06-26 | 2018-07-31 | 26 |  | 26 | [22 empty] | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Granville | 6S4469-2018 | 01034 | 1992 | Solar | 29A5 | 2018-05-31 | 2018-07-31 | 44 | 33 | 11 | 2018-08-01 | 2018-08-20 | 14 |  | 14 | [22 empty] | Not supplied |  | STD | [9 empty] | cancelled
WMECO | Gill | 6A3550-2018 | 01344 | 2000 | Solar | 21C5 | 2018-06-05 | 2018-06-28 | 18 | 14 | 4 | 2018-06-29 | 2018-08-01 | 24 |  | 24 | [22 empty] | Not supplied |  | STD | [9 empty] | cancelled by applicant
WMECO | Westhampton | 6A3553-2018 | 01027 | 27 | Solar | 15A3 | 2018-06-07 | 2018-06-20 | 10 | 2 | 8 | 2018-06-21 |  | -30875 | [24 empty] | 2018-08-01 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Springfield | 6S4501-2018 | 01104 | 999 | Solar | 5J13 | 2018-06-07 | 2018-07-12 | 26 | 17 | 9 | 2018-07-13 | 2018-08-24 | 31 |  | 31 | [10 empty] | 2018-12-31 | 2019-05-16 | 99 |  | 99 | [5 empty] | 2019-12-20 |  | Not supplied |  | STD | [8 empty] | 2024-07-23 | in construction phase
WMECO | Amherst | 6A3567-2018 | 01002 | 433.3 | Solar | 17K8 | 2018-06-12 | 2018-06-20 | 7 | 0 | 7 | 2018-06-21 | 2018-09-18 | 64 |  | 64 | 2018-09-19 | 2018-11-02 | 33 |  | 33 | [15 empty] | 2019-01-15 |  | 2018 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S4517-2018 | 01105 | 2500 | Diesel | 8CNW_1 | 2018-06-14 | 2019-02-05 | 169 | 158 | 11 | 2019-02-05 | 2020-01-14 | 246 |  | 246 | [20 empty] | 2023-06-14 |  | 2012 |  | EXP | [9 empty] | in Construction phase
WMECO | Hadley | 6A3587-2018 | 01035 | 133.2 | Solar | 17K5 | 2018-06-20 | 2018-08-01 | 31 | 24 | 7 | 2018-08-02 | 2018-09-05 | 25 |  | 25 | [20 empty] | 2018-12-07 |  | September 2018 |  | EXP | [8 empty] | 2019-04-25 | on line
WMECO | Lee | 6B1926-2018 | 01238 | 2000 | Solar | 17G3 | 2018-06-20 | 2018-07-16 | 19 | 6 | 13 | 2018-07-17 | 2018-08-27 | 30 |  | 30 | [10 empty] | 2018-11-23 | 2019-12-10 | 273 |  | 273 | [5 empty] | 2020-03-24 |  | 2019-01-20 |  | STD | [9 empty] | withdrawn
WMECO | Amherst | 6A3593-2018 | 01002 | 2000 | Battery | 18G7 | 2018-06-22 | 2019-01-17 | 150 |  | 150 | 2019-01-17 | 2019-05-31 | 97 |  | 97 | [10 empty] | 2019-06-10 | 2019-07-31 | 38 |  | 38 | [5 empty] | 2019-09-04 |  | 2018-12-31 |  | EXP | [9 empty] | customer hold
WMECO | Blandford | 6B1932-2018 | 01008 | 4450 | Solar | 19J2 | 2018-06-26 | 2018-08-01 | 27 | 13 | 14 | 2018-08-02 | 2018-10-10 | 50 |  | 50 | [10 empty] | 2019-02-07 | 2019-07-19 | 117 |  | 117 | [5 empty] | 2019-08-05 |  | 2019-09-30 |  | COMP | [9 empty] | customer hold
WMECO | Longmeadow | 6S4578-2018 | 01106 | 600 | Diesel | 22H12 | 2018-06-28 | [31 empty] | Not supplied |  | EXP | [8 empty] | 2022-10-26 | on line
WMECO | Pittsfield | 6B1937-2018 | 01201 | 1850 | Solar | 30B3 | 2018-06-29 | 2018-08-01 | 24 | 19 | 5 | 2018-08-02 |  | -30905 | [24 empty] | 2019-12-31 |  | STD | [9 empty] | cancelled
WMECO | Pittsfield | 6B1938-2018 | 01201 | 4998 | Solar | 30B3 | 2018-06-29 | 2018-08-01 | 24 | 18 | 6 | 2018-08-02 | 2018-08-29 | 20 |  | 20 | [22 empty] | 2019-12-31 |  | STD | [9 empty] | withdrawn
WMECO | Colrain | 6A3610-2018 | 01340 | 3300 | Solar | 29R2 | 2018-07-03 | 2018-07-17 | 11 | 4 | 7 | 2018-07-18 | 2018-08-15 | 21 |  | 21 | [10 empty] | 2019-08-13 |  | -31173 | [9 empty] | 2019 |  | STD | [9 empty] | cancelled
WMECO | Granville | 6S4596-2018 | 01034 | 40 | Solar | 29A5 | 2018-07-03 | 2018-07-24 | 16 | 6 | 10 | 2018-07-25 | 2018-10-22 | 64 |  | 64 | 2018-10-22 |  | -30962 | [17 empty] | 2018-11-29 |  | 2018-08-15 |  | EXP | [8 empty] | 2020-11-24 | on line
WMECO | Greenfield | 6A3611-2018 | 01301 | 4998 | Solar | 22B7 | 2018-07-05 | 2018-07-24 | 14 | 7 | 7 | 2018-07-25 |  | -30899 | [24 empty] | Q2 2019 |  | STD | [9 empty] | withdrawn
WMECO | Hatfield | 6A3612-2018 | 01373 | 4998 | Solar | 18G6 | 2018-07-05 | 2018-07-24 | 14 | 8 | 6 | 2018-07-25 | 2018-08-28 | 25 |  | 25 | [10 empty] | 2018-11-20 | 2019-04-16 | 106 |  | 106 | [5 empty] | 2019-05-15 |  | Q2 2019 |  | COMP | [9 empty] | withdrawn
WMECO | Bernardston | 6A3615-2018 | 01337 | 180 | Solar | 21C1 | 2018-07-05 | 2018-08-01 | 20 | 17 | 3 | 2018-08-02 | 2018-09-05 | 25 |  | 25 |  | 2019-10-09 | [18 empty] | 2019-10-09 |  | 2018-12-15 |  | EXP | [8 empty] | 2020-04-22 | on line
WMECO | Tolland | 6B1941-2018 | 01034 | 4998 | Solar | 19J4 | 2018-07-05 | 2018-07-24 | 14 | 8 | 6 | 2018-07-25 | 2018-08-15 | 16 |  | 16 | [10 empty] | 2019-05-07 |  | -31103 | [9 empty] | Q2 2019 |  | STD | [9 empty] | cancelled
WMECO | Ludlow | 6S4610-2018 | 01056 | 14.08 | Solar | 19S1 | 2018-07-06 | [31 empty] | 2018-08-02 |  | EXP | [9 empty] | cancelled, will submit Simplified application
WMECO | Hadley | 6A3626-2018 | 01035 | 2500 | Solar | 17K5 | 2018-07-11 | 2018-10-01 | 59 |  | 59 | 2018-09-28 | 2019-04-18 | 145 |  | 145 | [22 empty] | 2019-07-15 |  | EXP | [9 empty] | cancelled
WMECO | Hadley | 6A3627-2018 | 01035 | 2500 | Solar | 17K5 | 2018-07-11 | 2018-10-01 | 59 |  | 59 | 2018-10-02 | 2018-10-31 | 22 |  | 22 | [22 empty] | 2019-07-15 |  | EXP | [9 empty] | cancelled
WMECO | Russell | 6A3631-2018 | 01071 | 13.688 | Solar | 19J2 | 2018-07-11 | [31 empty] | 2018-05-28 |  | EXP | [9 empty] | cancelled
WMECO | Feeding Hills | 6S4648-2018 | 01030 | 15.36 | Solar | 16C17 | 2018-07-13 | 2018-10-18 | 70 | 31 | 39 | 2018-10-18 | 2019-01-17 | 66 |  | 66 | [20 empty] | 2019-01-28 |  | 2018-09-10 |  | EXP | [8 empty] | 2019-07-19 | on line
WMECO | Gill | 6A3641-2018 | 01354 | 4950 | Solar | 21C5 | 2018-07-17 | 2018-08-02 | 13 | 0 | 13 | 2018-08-03 | 2018-09-10 | 27 |  | 27 | [22 empty] | 2019-02-25 |  | STD | [9 empty] | cancelled
WMECO | Springfield | 6S4645-2018 | 01108 | 37.6 | Solar | 22H16 | 2018-07-17 | 2018-07-31 | 11 | 2 | 9 | 2018-08-01 | 2018-09-04 | 25 |  | 25 | [20 empty] | 2018-11-26 |  | 2018-08-10 |  | EXP | [8 empty] | 2019-05-03 | on line
WMECO | Springfield | 6S4646-2018 | 01108 | 37.9 | Solar | 22H16 | 2018-07-17 | 2018-07-31 | 11 | 2 | 9 | 2018-08-01 | 2018-09-04 | 25 |  | 25 | [20 empty] | 2018-11-20 |  | 2018-08-10 |  | EXP | [8 empty] | 2019-05-03 | on line
WMECO | Russell | 6A3655-2018 | 01071 | 13.928 | Solar | 19J2 | 2018-07-24 | [31 empty] | 2018-09-24 |  | EXP | [9 empty] | cancelled
WMECO | Lanesborough | 6B1959-2018 | 01237 | 4890 | Solar | 15E1 | 2018-07-24 | 2018-08-31 | 29 | 11 | 18 | 2018-09-04 | 2019-04-01 | 150 |  | 150 | [10 empty] | 2019-05-30 | 2022-06-13 | 793 |  | 793 | [7 empty] | Spring 2019 |  | EXP | [9 empty] | cancelled
WMECO | Agawam | 6S4675-2018 | 01001 | 4890 | Solar | 30A3 | 2018-07-24 | 2018-08-13 | 15 | 13 | 2 | 2018-08-14 | 2019-03-29 | 164 |  | 164 | [22 empty] | Spring 2019 |  | STD | [9 empty] | cancelled
WMECO | Southwick | 6S4685-2018 | 01077 | 1000 | Battery | 29A3 | 2018-07-24 | 2019-01-29 | 136 |  | 136 | 2019-01-29 | 2019-05-07 | 71 |  | 71 | [22 empty] | 2018-12-31 |  | EXP | [9 empty] | cancelled
WMECO | Southwick | 6S4686-2018 | 01077 | 1000 | Battery | 29A3 | 2018-07-24 | 2019-01-29 | 136 |  | 136 | 2019-01-29 | 2019-05-07 | 71 |  | 71 | [22 empty] | 2018-12-31 |  | EXP | [9 empty] | cancelled
WMECO | Longmeadow | 6S4747-2018 | 01106 | 27 | Solar | 22H11 | 2018-08-10 | 2018-09-26 | 34 | 0 | 34 | 2018-09-27 |  | -30945 | [24 empty] | 2018-11-08 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S4748-2018 | 01104 | 209.8 | Solar | 5J14 | 2018-08-10 | [31 empty] | 2018-11-06 |  | EXP | [9 empty] | cancelled by applicant
WMECO | Longmeadow | 6S4750-2018 | 01106 | 27 | Solar | 22H11 | 2018-08-10 | 2018-09-21 | 31 | 0 | 31 | 2018-10-12 | 2018-11-21 | 29 |  | 29 | [20 empty] | 2018-11-25 |  | 2018-11-08 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S4751-2018 | 01104 | 209.8 | Solar | 5J14 | 2018-08-10 | 2018-10-12 | 46 | 0 | 46 | 2018-10-12 | 2018-11-20 | 28 |  | 28 | [22 empty] | 2018-11-06 |  | EXP | [9 empty] | cancelled
WMECO | Agawam | 6S4753-2018 | 01001 | 286.4 | Solar | 30A3 | 2018-08-10 | 2018-10-01 | 37 | 0 | 37 | 2018-10-01 | 2018-11-20 | 37 |  | 37 | [20 empty] | 2019-01-25 |  | 2018-11-06 |  | EXP | [9 empty] | cancelled