WMECO | Longmeadow | 6S4754-2018 | 01106 | 66.6 | Solar | 22H12 | 2018-08-10 | 2018-10-03 | 39 | 0 | 39 | 2018-10-03 | 2018-11-26 | 39 |  | 39 | [20 empty] | 2018-11-26 |  | 2018-11-06 |  | EXP | [8 empty] | 2020-04-01 | on line
WMECO | Northfield | 6A3710-2018 | 01360 | 4950 | Solar | 21B8 | 2018-08-14 | 2018-09-12 | 22 | 1 | 21 | 2018-09-13 | 2019-08-16 | 242 |  | 242 | [22 empty] | 2019-02-15 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S4780-2018 | 01106 | 163.3 | Solar | 22H16 | 2018-08-16 | 2018-10-12 | 42 | 0 | 42 | 2018-10-12 | 2018-11-26 | 32 |  | 32 | [20 empty] | 2018-11-26 |  | 2018-11-12 |  | EXP | [9 empty] | withdrawn
WMECO | Russell | 6A3737-2018 | 01071 | 4998 | Solar | 19J2 | 2018-08-21 | 2018-10-29 | 50 |  | 50 | 2018-10-30 | 2019-04-01 | 110 |  | 110 | [22 empty] | Q4 2019 |  | EXP | [9 empty] | withdrawn
WMECO | Erving | 6A3738-2018 | 01344 | 4494.4 | Solar | 21B9 | 2018-08-21 | 2019-01-03 | 98 |  | 98 | 2019-01-03 | 2019-03-28 | 61 |  | 61 | [22 empty] | Q4 2019 |  | EXP | [9 empty] | cancelled
WMECO | Otis | 6B1993-2018 | 01253 | 4998 | Solar | 19J4 | 2018-08-21 | 2018-12-11 | 81 | 71 | 10 | 2018-12-11 | 2019-04-01 | 80 |  | 80 | [22 empty] | Q4 2019 |  | EXP | [9 empty] | cancelled
WMECO | Lee | 6B1994-2018 | 01238 | 120 | Solar | 17G3 | 2018-08-23 | 2018-10-09 | 34 | 0 | 34 | 2018-10-10 | 2019-01-15 | 70 |  | 70 | 2019-03-26 | 2019-04-30 | 26 |  | 26 | [15 empty] | 2019-05-13 |  | 2018-12-01 |  | EXP | [9 empty] | cancelled
WMECO | Pittsfield | 6B1997-2018 | 01201 | 253.1 | Solar | 30B2 | 2018-08-27 | 2018-09-20 | 19 | 0 | 19 | 2018-09-20 | 2018-12-12 | 60 |  | 60 | [20 empty] | 2019-01-25 |  | 2018-11-30 |  | EXP | [9 empty] | cancelled
WMECO | Feeding Hills | 6S4816-2018 | 01030 | 250 | Solar | 16C17 | 2018-08-28 | 2018-10-24 | 42 | 0 | 42 | 2018-10-25 | 2018-12-12 | 35 |  | 35 | [22 empty] | 11/31/18 |  | EXP | [9 empty] | withdrawn
WMECO | Pittsfield | 6B2002-2018 | 01201 | 1450 | Solar | 19A5 | 2018-08-29 | 2018-11-28 | 66 | 0 | 66 | 2018-11-28 | 2019-03-05 | 70 |  | 70 | [10 empty] | 2019-05-21 | 2019-08-19 | 65 |  | 65 | [5 empty] | 2019-08-19 |  | 2018-09-01 |  | STD | [9 empty] | customer hold
WMECO | Chesterfield | 6A3750-2018 | 01026 | 3500 | Solar | 18K3 | 2018-08-30 | 2018-09-25 | 19 | 0 | 19 | 2018-09-26 |  | -30944 | [24 empty] | 3/15/2019 |  | EXP | [9 empty] | withdrawn
WMECO | Ludlow | 6S4833-2018 | 01056 | 2772 | Solar | 19S1 | 2018-08-31 | 2018-11-28 | 64 | 0 | 64 | 2018-11-28 |  | -30989 | [12 empty] | 2019-07-25 | 2020-03-09 | 163 |  | 163 | [5 empty] | 2020-03-25 |  | 2019-04-01 |  | EXP | [9 empty] | in construction phase
WMECO | Sandisfield | 6B2011-2018 | 01255 | 400 | Solar | 19J4 | 2018-09-06 | 2018-09-21 | 12 | 0 | 12 | 2018-09-24 | 2018-11-25 | 45 |  | 45 | [22 empty] | 2019-08-01 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S4841-2018 | 01104 | 450 | Solar | 5J9 | 2018-09-06 | 2018-11-29 | 61 | 0 | 61 | 2018-11-29 | 2018-12-12 | 10 |  | 10 | [10 empty] | 2018-12-18 | 2018-12-19 | 2 |  | 2 | [7 empty] | 2018-12-01 |  | EXP | [9 empty] | withdrawn
WMECO | Agawam | 6S4842-2018 | 01001 | 580 | Solar | 16C16 | 2018-09-10 | 2018-10-09 | 22 | 0 | 22 | 2018-10-10 | 2020-08-06 | 477 |  | 477 | [20 empty] | 2019-05-29 |  | Not supplied |  | EXP | [9 empty] | withdrawn
WMECO | Ashfield | 6A3767-2018 | 01330 | 4450 | Solar | 38A1 | 2018-09-11 | 2018-11-30 | 59 | 0 | 59 | 2018-12-03 | 2019-02-22 | 60 |  | 60 | [22 empty] | 10/1/2019 |  | EXP | [9 empty] | withdrawn
WMECO | Longmeadow | 6S4890-2018 | 01106 | 16.24 | Solar | 22H12 | 2018-09-19 | 2018-10-24 | 26 | 0 | 26 | 2018-10-25 | 2018-11-21 | 20 |  | 20 | [20 empty] | 2019-01-23 |  | 2018-09-21 |  | EXP | [8 empty] | 2018-11-26 | on line
WMECO | Agawam | 6S4959-2018 | 01001 | 366.3 | Solar | 30A3 | 2018-10-05 | 2018-10-30 | 18 |  | 18 | 2018-10-31 | 2019-01-17 | 57 |  | 57 | [20 empty] | 2019-01-30 |  | 2018-11-26 |  | EXP | [9 empty] | withdrawn
WMECO | Russell | 6A3820-2018 | 01071 | 5000 | Solar | 19J2 | 2018-10-08 | 2018-12-19 | 53 |  | 53 | 2018-12-19 | 2019-05-07 | 100 |  | 100 | [22 empty] | Not supplied |  | EXP | [9 empty] | withdrawn
WMECO | Pittsfield | 6B2036-2018 | 01201 | 1000 | Solar | 30B3 | 2018-10-12 | 2019-01-14 | 67 |  | 67 | 2019-01-14 | 2019-02-04 | 16 |  | 16 | [10 empty] | 2019-12-09 | 2020-03-13 | 70 |  | 70 | [5 empty] | 2020-04-28 |  |  |  | EXP | [9 empty] | cancelled
WMECO | Amherst | 6A3840-2018 | 01002 | 250 | Solar | 19B16 | 2018-10-15 | 2018-11-06 | 17 |  | 17 | 2018-11-06 | 2019-01-10 | 48 |  | 48 | [24 empty] | EXP | [9 empty] | withdrawn
WMECO | Amherst | 6A3841-2018 | 01002 | 1000 | Solar | 19B16 | 2018-10-15 | 2018-11-20 | 27 |  | 27 | 2018-11-20 | 2019-01-28 | 50 |  | 50 | [24 empty] | EXP | [9 empty] | withdrawn
WMECO | Southwick | 6S4998-2018 | 01077 | 18872 | Solar | 29A5 | 2018-10-18 | [33 empty] | EXP | [9 empty] | withdrawn
WMECO | Southwick | 6S5004-2018 | 01077 | 150 | Solar | 29A5 | 2018-10-22 | 2018-10-24 | 3 | 0 | 3 | 2018-10-25 | 2019-01-11 | 57 |  | 57 | [20 empty] | 2019-01-15 |  |  |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S5005-2018 | 01108 | 99.9 | Solar | 21S12 | 2018-10-22 | 2018-10-25 | 4 | 0 | 4 | 2018-10-26 |  | -30966 | [22 empty] | 2019-01-15 |  |  |  | EXP | [9 empty] | cancelled
WMECO | Blandford | 6B2044-2018 | 01008 | 18872 | Solar | 19J2 | 2018-10-23 | 2019-01-14 | 60 |  | 60 | 2019-01-14 | 2019-02-13 | 23 |  | 23 | [24 empty] | EXP | [9 empty] | cancelled
WMECO | Southwick | 6S5010-2018 | 01077 | 4400 | Solar | 29A5 | 2018-10-23 | 2019-02-07 | 78 |  | 78 | 2019-02-07 | 2019-03-28 | 36 |  | 36 | [24 empty] | EXP | [9 empty] | withdrawn
WMECO | Whately | 6A3861-2018 | 01373 | 4885 | Solar | 18G6 | 2018-10-26 | 2019-01-14 | 57 |  | 57 | 2019-01-14 | 2019-04-17 | 68 |  | 68 | [24 empty] | EXP | [9 empty] | cancelled
WMECO | Whately | 6A3868-2018 | 01373 | 999 | Solar | 18G8 | 2018-10-30 | 2019-01-17 | 58 | 50 | 8 | 2019-01-17 | 2019-03-29 | 52 |  | 52 | [11 empty] | 2023-11-09 | [8 empty] | 2023-11-10 |  |  |  | EXP | [9 empty] | ISA issued 11/10/2023
WMECO | Ludlow | 6S5036-2018 | 01056 | 5550 | Solar | 19S1 | 2018-10-30 | 2019-01-17 | 58 |  | 58 | 2019-01-17 | 2019-03-22 | 47 |  | 47 | [24 empty] | EXP | [9 empty] | withdrawn
WMECO | Amherst | 6A3871-2018 | 01002 | 36.496 | Solar | 17K4 | 2018-11-01 | 2018-11-05 | 3 |  | 3 | 2018-11-05 | 2019-01-29 | 62 |  | 62 | [24 empty] | EXP | [9 empty] | cancelled
WMECO | Southampton | 6A3880-2018 | 01073 | 3180 | solar | 15A1 | 2018-11-02 | 2019-01-30 | 64 |  | 64 | 2019-01-30 | 2019-03-29 | 43 |  | 43 | [24 empty] | EXP | [9 empty] | withdrawn
WMECO | Shelburne Falls | 6A3884-2018 | 01370 | 250 | Solar | 29R2 | 2018-11-05 | 2018-12-06 | 24 |  | 24 | 2018-12-06 | 2018-12-19 | 10 |  | 10 | 2019-10-25 | 2019-11-22 | 21 |  | 21 | [15 empty] | 2019-11-26 |  |  |  | EXP | [8 empty] | 2022-07-21 | on line
WMECO | Ludlow | 6S5054-2018 | 01056 | 4400 | Solar | 19S3 | 2018-11-05 | 2018-12-06 | 24 |  | 24 | 2018-12-06 | 2019-01-03 | 21 |  | 21 | [10 empty] | 2019-03-05 | 2019-07-25 | 103 |  | 103 | [5 empty] | 2020-03-25 |  |  |  | EXP | [9 empty] | cancelled
WMECO | Hinsdale | 6A3888-2018 | 01235 | 39600 | Solar | 18C2 | 2018-11-08 | 2019-01-15 | 49 |  | 49 | 2019-01-15 | 2019-03-22 | 49 |  | 49 | [24 empty] | EXP | [9 empty] | withdrawn
WMECO | Hinsdale | 6A3889-2018 | 01235 | 14400 | Solar | 18C2 | 2018-11-08 | 2019-01-15 | 49 |  | 49 | 2019-01-15 |  | -31023 | [26 empty] | EXP | [9 empty] | withdrawn
WMECO | Pittsfield | 6B2053-2018 | 01201 | 4347.65 | Solar | 15E2 | 2018-11-08 | 2019-01-15 | 49 |  | 49 | 2019-01-15 | 2019-02-13 | 22 |  | 22 | [22 empty] | Q4 2020 |  | EXP | [9 empty] | cancelled
WMECO | Northfield | 6A3896-2018 | 01360 | 2104 | Solar | 21B8 | 2018-11-13 | 2019-03-19 | 91 |  | 91 | 2019-03-19 | 2019-03-28 | 8 |  | 8 | [24 empty] | EXP | [9 empty] | withdrawn
WMECO | Hadley | 6A3901-2018 | 01035 | 518.4 | Solar | 17K5 | 2018-11-15 | 2018-12-06 | 16 |  | 16 | 2018-12-06 | 2018-12-26 | 15 |  | 15 | [24 empty] | EXP | [9 empty] | withdrawn
WMECO | Amherst | 6A3916-2018 | 01002 | 3000 | Battery | 18G4 | 2018-11-19 | 2019-02-04 | 56 |  | 56 | 2019-02-04 | 2019-05-08 | 68 |  | 68 | [10 empty] | 2019-07-22 | 2019-10-25 | 70 |  | 70 | [5 empty] | 2020-03-26 |  | 4/5/2019 |  | EXP | [8 empty] | 2024-01-09 | on line
WMECO | Springfield | 6S5117-2018 | 01103 | 32.83 | Solar | 8CNW_1 | 2018-11-20 | 2019-01-18 | 44 |  | 44 | 2019-01-18 | 2019-04-10 | 59 |  | 59 | [22 empty] | not supplied |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S5103-2018 | 01104 | 532.8 | Solar | 5J9 | 2018-11-21 | 2018-11-26 | 4 |  | 4 | 2018-11-26 | 2019-01-17 | 39 |  | 39 | [22 empty] | Nov 2019 |  | EXP | [9 empty] | cancelled
WMECO | Pittsfield | 6B2062-2018 | 01201 | 463.01 | Solar | 19A5 | 2018-11-26 | 2019-01-24 | 44 |  | 44 | 2019-01-24 |  | -31030 | [24 empty] | 2019-04-01 |  | EXP | [9 empty] | cancelled
WMECO | Deerfield | 6A3912-2018 | 01373 | 15.78 | Solar | 22B1 | 2018-11-28 | 2018-12-03 | 4 |  | 4 | 2018-12-03 | 2018-12-24 | 16 |  | 16 | [10 empty] | 2018-12-03 |  | -30992 | [7 empty] | 2019-03-08 |  | 12/2018 |  | EXP | [8 empty] | 2019-07-17 | on line
WMECO | Agawam | 6S5118-2018 | 01001 | 4950 | Solar | 16C16 | 2018-11-30 | 2019-01-15 | 33 |  | 33 | 2019-01-28 | 2019-03-28 | 44 |  | 44 | [22 empty] | 2018-12-14 |  | EXP | [9 empty] | cancelled
WMECO | Amherst | 6A3920-2018 | 01002 | 2500 | Solar | 17K2 | 2018-12-04 | 2019-01-24 | 38 |  | 38 | 2019-01-24 | 2019-03-22 | 42 |  | 42 | [10 empty] | 2019-04-24 | 2019-11-27 | 156 |  | 156 | [5 empty] | 2020-03-27 |  | 10/1/2019 |  | EXP | [8 empty] | 2022-08-23 | on line
WMECO | Lanesborough | 6B2072-2018 | 01237 | 4540 | Solar | 15E1 | 2018-12-11 | 2019-01-15 | 26 |  | 26 | 2019-01-15 | 2019-03-22 | 49 |  | 49 | [22 empty] | Fall 2019 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S5140-2018 | 01109 | 24 | Solar | 5J17 | 2018-12-11 | 2019-01-17 | 28 |  | 28 | 2019-01-17 | 2019-04-02 | 54 |  | 54 | [20 empty] | 2019-03-18 |  |  |  | EXP | [8 empty] | 2019-07-16 | on line
WMECO | Greenfield | 6A3934-2018 | 01301 | 41.47 | Solar | 22B2 | 2018-12-14 | 2019-01-31 | 35 |  | 35 | 2019-01-31 | 2019-03-22 | 37 |  | 37 | [20 empty] | 2019-05-28 |  |  |  | EXP | [9 empty] | withdrawn
WMECO | Greenfield | 6A3935-2018 | 01301 | 96 | Solar | 21C4 | 2018-12-14 | 2019-01-23 | 29 |  | 29 | 2019-01-23 | 2019-03-22 | 43 |  | 43 | [20 empty] | 2019-05-28 |  |  |  | EXP | [9 empty] | cancelled
WMECO | Greenfield | 6A3936-2018 | 01301 | 101.38 | Solar | 22B3 | 2018-12-14 | 2019-02-07 | 40 |  | 40 | 2019-02-07 | 2019-03-22 | 32 |  | 32 | 2019-06-19 |  | -31134 | [17 empty] | 2019-12-04 |  |  |  | EXP | [9 empty] | cancelled
WMECO | Greenfield | 6A3937-2018 | 01301 | 36 | Solar | 22B2 | 2018-12-14 | 2019-01-23 | 29 |  | 29 | 2019-01-23 | 2019-03-22 | 43 |  | 43 | [20 empty] | 2019-06-06 |  |  |  | EXP | [9 empty] | withdrawn
WMECO | Greenfield | 6A3938-2018 | 01301 | 88.13 | Solar | 21C4 | 2018-12-14 | 2019-01-24 | 30 |  | 30 | 2019-01-24 | 2019-03-22 | 42 |  | 42 | [20 empty] | 2019-06-06 |  |  |  | EXP | [9 empty] | withdrawn
WMECO | Greenfield | 6A3939-2018 | 01301 | 194 | Solar | 21C4 | 2018-12-14 | 2019-01-24 | 30 |  | 30 | 2019-01-24 | 2019-04-02 | 49 |  | 49 | [20 empty] | 2019-05-28 |  |  |  | EXP | [9 empty] | withdrawn
WMECO | Amherst | 6A3949-2018 | 01002 | 3182.224 | Solar | 18G7 | 2018-12-19 | [31 empty] | not supplied |  | EXP | [9 empty] | cancelled
WMECO | West Springfield | 6S5163-2018 | 01089 | 228 | Solar | 16C15 | 2018-12-20 | 2019-01-03 | 11 |  | 11 | 2019-01-03 | 2019-01-17 | 11 |  | 11 | [10 empty] | 2019-01-03 |  | -31015 | [11 empty] | EXP | [9 empty] | withdrawn
WMECO | Ashfield | 6A3958-2018 | 01330 | 4998 | Solar | 38A1 | 2018-12-24 | 2019-02-04 | 31 |  | 31 | 2019-02-04 | 2019-03-28 | 39 |  | 39 | [24 empty] | EXP | [9 empty] | cancelled
WMECO | Hadley | 6A4077-2019 | 01035 | 1000 | Battery | 17K6 | 2019-01-03 | 2019-05-06 | 88 |  | 88 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [10 empty] | 2019-07-22 | 2019-10-25 | 70 |  | 70 | [5 empty] | 2019-12-18 |  | Not supplied |  | EXP | [8 empty] | 2024-05-09 | in construction phase
WMECO | Hadley | 6A4078-2019 | 01035 | 1000 | Battery | 17K1 | 2019-01-03 | 2019-05-06 | 88 |  | 88 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [10 empty] | 2019-07-22 | 2019-10-25 | 70 |  | 70 | [5 empty] | 2019-12-18 |  | Not supplied |  | EXP | [8 empty] | 2024-03-26 | on line
WMECO | Plainfield | 6A3984-2019 | 01070 | 1000 | Battery | 18K3 | 2019-01-22 | 2019-02-07 | 13 |  | 13 | 2019-02-07 | 2019-03-22 | 32 |  | 32 | [10 empty] | 2019-07-22 | 2019-10-16 | 63 |  | 63 | [5 empty] | 2020-03-27 |  | not supplied |  | EXP | [8 empty] | 2024-01-24 | on line
WMECO | Hatfied | 6A4031-2019 | 01038 | 232 | Solar | 18G5 | 2019-02-14 | 2019-03-19 | 24 |  | 24 | 2019-03-19 | 2019-04-02 | 11 |  | 11 | [20 empty] | 2019-05-24 |  | not supplied |  | EXP | [8 empty] | 2022-07-21 | on line
WMECO | Leyden | 6A4033-2019 | 01301 | 4980 | Solar | 22B7 | 2019-02-14 | 2019-02-22 | 7 |  | 7 | 2019-02-22 | 2019-04-18 | 40 |  | 40 | [22 empty] | 2019-07-01 |  | EXP | [9 empty] | cancelled
WMECO | Colrain | 6A4034-2019 | 01340 | 1980 | Solar | 29R2 | 2019-02-14 | 2019-02-22 | 7 |  | 7 | 2019-02-22 | 2019-03-19 | 18 |  | 18 | [22 empty] | 2019-07-01 |  | EXP | [9 empty] | cancelled
WMECO | Northfield | 6A4045-2019 | 01360 | 3000 | Solar | 21B8 | 2019-02-20 | 2019-04-01 | 29 | 27 | 2 | 2019-04-01 | 2019-04-18 | 14 |  | 14 | [10 empty] | 2020-08-04 | 2022-12-14 | 617 |  | 617 | [5 empty] | 2023-02-27 |  | 2020-01-29 |  | EXP | [9 empty] | customer hold - construction extension
WMECO | Northfield | 6A4048-2019 | 01360 | 2000 | Solar | 21B8 | 2019-02-20 | 2019-05-06 | 54 | 47 | 7 | 2019-05-06 | 2019-06-07 | 25 |  | 25 | [10 empty] | 2020-08-04 | 2022-12-14 | 617 |  | 617 | [5 empty] | 2023-02-27 |  | 2020-01-29 |  | EXP | [9 empty] | customer hold - construction extension
WMECO | Northfield | 6A4049-2019 | 01360 | 1000 | Solar | 21B8 | 2019-02-20 | 2019-05-06 | 54 | 42 | 12 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [10 empty] | 2020-08-04 | 2022-12-14 | 617 |  | 617 | [5 empty] | 2023-02-27 |  | 2020-01-29 |  | EXP | [9 empty] | customer hold - construction extension
WMECO | Ashfield | 6A4068-2019 | 01330 | 4950 | Solar |  | 2019-03-06 | 2019-05-08 | 46 |  | 46 | [27 empty] | 4/4/2020 |  | EXP | [9 empty] | cancelled
WMECO | Ludlow | 6S5364-2019 | 01056 | 212 | Solar | 27A5 | 2019-03-13 | 2019-05-14 | 45 |  | 45 | 2019-05-14 | 2019-06-28 | 34 |  | 34 | 2020-04-15 | 2020-09-16 | 111 |  | 111 | [15 empty] | 2020-09-16 |  | 2019-11-01 |  | Exp | [8 empty] | 2023-07-10 | on line
WMECO | Whately | 6A4126-2019 | 01093 | 1000 | Battery | 18G8 | 2019-03-18 | 2019-04-22 | 26 |  | 26 | 2019-04-22 | 2019-05-08 | 13 |  | 13 | [11 empty] | 2020-01-16 | [8 empty] | 2020-03-23 |  | 3/1/2020 |  | EXP | [9 empty] | cancelled
WMECO | Ludlow | 6S5370-2019 | 01056 | 136 | Solar | 19S3 | 2019-03-19 | 2019-04-30 | 31 |  | 31 | 2019-04-30 | 2019-05-13 | 10 |  | 10 | 2019-06-04 | 2019-07-30 | 41 |  | 41 | [15 empty] | 2019-10-22 |  | Q3 2019 |  | Exp | [9 empty] | withdrawn
WMECO | Agawam | 6S5376-2019 | 01001 | 15.08 | Solar | 30A5 | 2019-03-19 | [31 empty] | 2019-03-03 |  | Exp | [9 empty] | withdrawn
WMECO | Deerfield | 6A4093-2019 | 01342 | 72 | Solar | 22B1 | 2019-03-25 | 2019-05-07 | 32 |  | 32 | 2019-05-07 | 2019-09-05 | 88 |  | 88 | [20 empty] | 2019-09-26 |  | 5/2019 |  | EXP | [8 empty] | 2020-04-21 | on line
WMECO | Springfield | 6S5394-2019 | 01104 | 80 | Solar | 5J16 | 2019-03-27 | 2019-04-03 | 6 |  | 6 | 2019-04-03 | 2019-04-11 | 7 |  | 7 | [22 empty] | ASAP |  | Exp | [9 empty] | withdrawn
WMECO | Northfield | 6A4098-2019 | 01360 | 1000 | Solar | 21B8 | 2019-03-29 | [31 empty] | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Agawam | 6S5405-2019 | 01001 | 4990 | Solar | 30A3 | 2019-04-03 | 2019-05-06 | 24 |  | 24 | 2019-05-06 | 2019-05-23 | 14 |  | 14 | [11 empty] | 2019-06-24 | [10 empty] | Summer 2019 |  | Exp | [9 empty] | cancelled
WMECO | Deerfield | 6A4131-2019 | 01342 | 25.3 | Solar | 22B7 | 2019-04-17 | 2019-05-07 | 15 |  | 15 | 2019-05-07 | 2019-06-03 | 20 |  | 20 | [20 empty] | 2019-08-15 |  | 6/12/2019 |  | EXP | [8 empty] | 2019-12-11 | on line
WMECO | Lanesborough | 6B2129-2019 | 01237 | 3960 | Solar | 15E1 | 2019-04-17 | 2019-05-07 | 15 |  | 15 | 2019-05-07 | 2019-05-23 | 13 |  | 13 | [22 empty] | Spring 2019 |  | EXP | [9 empty] | cancelled
WMECO | Lanesborough | 6B2130-2019 | 01237 | 4990 | Solar | 15E2 | 2019-04-17 | 2019-05-07 | 15 |  | 15 | 2019-05-07 | 2019-05-23 | 13 |  | 13 | [22 empty] | Spring 2019 |  | EXP | [9 empty] | cancelled
WMECO | Lanesborough | 6B2131-2019 | 01237 | 4990 | Solar | 15E1 | 2019-04-17 | 2019-05-06 | 14 |  | 14 | 2019-05-06 | 2019-05-22 | 13 |  | 13 | [22 empty] | Spring 2019 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S5434-2019 | 01229 | 200 | Solar | 27A13 | 2019-04-17 | 2019-05-08 | 16 |  | 16 | 2019-05-08 | 2019-05-23 | 12 |  | 12 | 2019-09-25 | 2020-06-23 | 195 |  | 195 | [15 empty] | 2020-06-23 |  | 2020-03-24 |  | Exp | [8 empty] | 2022-09-21 | on line
WMECO | Colrain | 6A4169-2019 | 01340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 27 |  | 27 | 2019-06-12 | 2019-06-18 | 5 |  | 5 | [22 empty] | 7/30/2019 |  | EXP | [9 empty] | cancelled
WMECO | Colrain | 6A4199-2019 | 01340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 27 |  | 27 | 2019-06-12 | 2019-06-18 | 5 |  | 5 | [22 empty] | 2019-07-30 |  | EXP | [9 empty] | cancelled
WMECO | Colrain | 6A4200-2019 | 01340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 27 |  | 27 | 2019-06-12 | 2019-06-25 | 10 |  | 10 | [22 empty] | 2019-07-30 |  | EXP | [9 empty] | cancelled
WMECO | Colrain | 6A4201-2019 | 01340 | 25 | Solar | 29R2 | 2019-05-07 | 2019-06-12 | 27 |  | 27 | 2019-06-12 | 2019-06-25 | 10 |  | 10 | [22 empty] | 2019-07-30 |  | EXP | [9 empty] | cancelled
WMECO | Amherst | 6A4175-2019 | 01002 | 3778 | Solar | 18G7 | 2019-05-13 | [29 empty] | 2019-09-11 |  | Oct 2019 |  | EXP | [8 empty] | 2019-07-30 | transmission / ISO
WMECO | Tolland | 6B2161-2019 | 01034 | 5000 | Solar | 19J4 | 2019-06-11 | 2019-06-20 | 8 | 6 | 2 | 2019-06-20 | 2019-06-21 | 2 |  | 2 | [22 empty] | Q4 2020 |  | EXP | [9 empty] | Plainfield / Blandford Group Study
WMECO | Whately | 6A4237-2019 | 01093 | 1000 | Solar | 18G8 | 2019-06-13 | 2019-06-20 | 6 |  | 6 | 2019-06-20 | 2019-06-26 | 5 |  | 5 | [22 empty] | 2020-09-01 |  | EXP | [9 empty] | cancelled
WMECO | Agawam | 6S5606-2019 | 01001 | 4975 | Solar | 30A1 | 2019-06-14 | 2019-06-20 | 5 |  | 5 | 2019-06-20 | 2019-06-24 | 3 |  | 3 | [10 empty] | 2019-12-02 | 2020-02-19 | 58 |  | 58 | [5 empty] | 2020-04-03 |  | 2018-12-14 |  | Exp | [8 empty] | 2021-12-16 | on line
WMECO | Westhampton | 6A4242-2019 | 01027 | 34 | Solar | 15A3 | 2019-06-17 | 2019-09-11 | 63 |  | 63 | 2019-09-11 | 2019-09-12 | 2 |  | 2 | 2019-10-17 | 2020-02-05 | 80 |  | 80 | [15 empty] | 2021-01-12 |  | Not supplied |  | EXP | [8 empty] | 2023-08-17 | on line
WMECO | Greenfield | 6A4259-2019 | 01301 | 20 | Solar | 21C4 | 2019-06-21 | 2019-08-27 | 48 |  | 48 | 2019-08-27 | 2019-10-11 | 34 |  | 34 | [20 empty] | 2020-03-03 |  | 2019-08-15 |  | EXP | [8 empty] | 2020-10-16 | on line
WMECO | Turners Falls | 6A4261-2019 | 01376 | 460 | Solar | 21C2 | 2019-06-25 | 2019-06-26 | 2 |  | 2 | 2019-06-26 | 2019-07-01 | 4 |  | 4 | 2019-09-10 | 2019-10-22 | 31 |  | 31 | [15 empty] | 2019-10-24 |  | Not supplied |  | EXP | [9 empty] | cancelled
WMECO | Huntington | 6A4268-2019 | 01050 | 21.54 | Solar | 19J5 | 2019-06-25 | 2019-09-09 | 55 |  | 55 | 2019-09-09 | 2019-08-14 | -19 |  |  | 2019-09-12 | 2019-10-25 | 32 |  | 32 | [15 empty] | 2019-10-30 |  | Fall 2019 |  | EXP | [8 empty] | 2020-08-20 | on line
WMECO | Springfield | 6S5635-2019 | 01102 | 1875 | Diesel | 5J13 | 2019-07-02 | 2019-09-09 | 50 |  | 50 | 2019-09-09 | 2019-12-11 | 68 |  | 68 | [20 empty] | 2020-08-11 |  | not supplied |  | EXP | [8 empty] | 2020-09-15 | on line
WMECO | Ashfield | 6A4287-2019 | 01330 | 25 | Solar | 22B5 | 2019-07-09 | 2019-07-10 | 2 |  | 2 | 2019-07-10 |  | -31149 | [24 empty] | 2019-09-01 |  | EXP | [9 empty] | withdrawn
WMECO | Shelburne | 6A4288-2019 | 01370 | 25 | Solar | 38A1 | 2019-07-09 | 2019-07-10 | 2 |  | 2 | 2019-07-10 | 2019-08-06 | 20 |  | 20 | [22 empty] | 2019-09-01 |  | EXP | [9 empty] | withdrawn
WMECO | West Springfield | 6S5659-2019 | 01089 | 233.3 | Solar | 21N5 | 2019-07-12 | 2019-07-18 | 5 |  | 5 | 2019-07-18 | 2019-07-29 | 8 |  | 8 | 2020-02-19 |  | -31309 | [17 empty] | 2020-07-01 |  | 2019-12-31 |  | Exp | [9 empty] | cancelled
WMECO | Pelham | 6A4306-2019 | 01002 | 2200/3300/4400 | Solar | 17K2 | 2019-07-15 | 2019-09-26 | 54 | 52 | 2 | 2019-09-26 | 2019-09-30 | 3 |  | 3 | [10 empty] | 2020-12-08 | 2022-06-29 | 407 |  | 407 | [7 empty] | 1/1/21 |  | EXP | [9 empty] | customer hold
WMECO | Amherst | 6A4309-2019 | 01002 | 4400 | Solar | 17K7 | 2019-07-15 | 2019-09-26 | 54 | 51 | 3 | 2019-09-26 | 2019-09-30 | 3 |  | 3 | [10 empty] | 2020-12-08 | 2022-05-13 | 374 |  | 374 | [5 empty] | 2023-01-20 |  | 2021-01-21 |  | EXP | [9 empty] | customer hold
WMECO | Easthampton | 6A4329-2019 | 01027 | 1000 | Solar | 15A3 | 2019-07-19 | 2019-07-31 | 9 | 9 | 0 | 2019-07-31 | 2019-08-21 | 16 |  | 16 | [10 empty] | 2021-03-01 |  | -31577 | [9 empty] | 2020-07-10 |  | EXP | [9 empty] | withdrawn
WMECO | South Deerfield | 6A4414-2019 | 01773 | 25 | Solar | 22B3 | 2019-08-28 | 2019-09-03 | 5 |  | 5 | 2019-09-03 | 2019-09-03 | 1 |  | 1 | 2019-09-24 |  | -31203 | [21 empty] | EXP | [9 empty] | cancelled
WMECO | Gill | 6A4433-2019 | 01354 | 17.6 | Solar | 21C5 | 2019-09-03 | 2019-09-06 | 4 |  | 4 | 2019-09-06 | 2019-10-10 | 25 |  | 25 | [20 empty] | 2019-12-03 |  | 2019-10-15 |  | EXP | [8 empty] | 2020-03-31 | on line
WMECO | Lanesborough | 6B2239-2019 | 01237 | 34.2 | Solar | 15E1 | 2019-09-03 | 2019-10-02 | 22 |  | 22 | 2019-10-02 | 2019-10-10 | 7 |  | 7 | [20 empty] | 2019-12-30 |  | Nov 2019 |  | EXP | [9 empty] | cancelled
WMECO | Greenfield | 6A4430-2019 | 01301 | 25 | Solar | 22B4 | 2019-09-05 | 2019-09-13 | 7 |  | 7 | 2019-09-13 | 2019-09-17 | 3 |  | 3 | [20 empty] | 2019-11-13 |  | Nov 2019 |  | EXP | [8 empty] | 2020-02-07 | on line
WMECO | Windsor | 6B2245-2019 | 01270 | 6 | Solar | 18C1 | 2019-09-05 | 2019-10-30 | 40 |  | 40 | 2019-10-31 | 2019-10-31 | 1 |  | 1 | [22 empty] | Not supplied |  | EXP | [9 empty] | withdrawn
WMECO | Springfield | 6S5825-2019 | 01128 | 72 | Battery | 20A21 | 2019-09-12 | 2019-10-07 | 18 |  | 18 | 2019-10-07 | 2019-10-15 | 7 |  | 7 | [20 empty] | 2020-03-30 |  | 2019-12-30 |  | Exp | [8 empty] | 2020-08-27 | on line
WMECO | Northfield | 6A4475-2019 | 01360 | 25 | Solar | 21B8 | 2019-09-20 | 2019-10-01 | 8 |  | 8 | 2019-10-01 | 2019-10-08 | 6 |  | 6 | [22 empty] | 2019-11-30 |  | EXP | [9 empty] | cancelled
WMECO | Blandford | 6B2269-2019 | 01008 | 4998 | Solar | 19J2 | 2019-10-01 | 2019-10-07 | 5 | 3 | 2 | 2019-10-07 | 2019-10-16 | 8 |  | 8 | [22 empty] | not supplied |  | EXP | [9 empty] | cancelled
WMECO | Indian Orchard | 6S5881-2019 | 01151 | 6780 | Solar | 27A11 | 2019-10-01 | 2019-10-01 | 1 |  | 1 | 2019-10-01 | 2020-01-09 | 73 |  | 73 | [22 empty] | 2020-04-17 |  | EXP | [9 empty] | cancelled
WMECO | Ludlow | 6S5908-2019 | 01056 | 3.8 | Solar | 27A4 | 2019-10-09 | 2019-10-28 | 14 |  | 14 | 2019-10-29 | 2019-11-01 | 4 |  | 4 | 2020-05-19 | 2020-05-20 | 2 |  | 2 | [15 empty] | 2020-05-21 |  | 2019-11-08 |  | EXP | [8 empty] | 2020-09-15 | on line
WMECO | Amherst | 6A4520-2019 | 01002 | 20 | Solar | 17K8 | 2019-10-10 | 2019-10-15 | 4 |  | 4 | 2019-10-15 | 2019-10-21 | 5 |  | 5 | [20 empty] | 2019-11-06 |  | Dec 2019 |  | EXP | [8 empty] | 2020-02-13 | on line
WMECO | Greenfield | 6A4584-2019 | 01301 | 220 | Solar | 21C1 | 2019-11-06 | 2019-11-12 | 5 |  | 5 | 2019-11-13 | 2019-11-21 | 7 |  | 7 | [20 empty] | 2019-12-04 |  | 5/2020 |  | EXP | [8 empty] | 2020-09-30 | on line
WMECO | Greenfield | 6A4585-2019 | 01301 | 220 | Solar | 21C1 | 2019-11-06 | 2019-11-12 | 5 |  | 5 | 2019-11-13 | 2019-11-21 | 7 |  | 7 | [20 empty] | 2019-12-04 |  | 5/2020 |  | EXP | [8 empty] | 2020-09-30 | on line
WMECO | Deerfield | 6A4600-2019 | 01373 | 2250 | Solar | 22B1 | 2019-11-14 | 2019-11-20 | 5 | 3 | 2 | 2019-11-20 | 2019-12-02 | 9 |  | 9 | [10 empty] | 2021-02-26 | 2023-11-07 | 703 |  | 703 | [5 empty] | 2023-11-10 |  | Not Supplied |  | EXP | [9 empty] | ISA issued 11/10/2023
WMECO | Pelham | 6A4622-2019 | 01002 | 17.6 | Solar | 17K2 | 2019-11-21 | 2020-01-30 | 51 |  | 51 | 2020-01-30 | 2020-02-04 | 4 |  | 4 | [20 empty] | 2020-03-30 |  | 2019-12-17 |  | EXP | [8 empty] | 2020-09-14 | on line
WMECO | Tyringham | 6B2332-2019 | 01264 | 26.25 | Solar | 16B1 | 2019-11-27 | 2019-12-17 | 15 |  | 15 | 2019-12-17 | 2020-01-22 | 27 |  | 27 | [22 empty] | not supplied |  | EXP | [9 empty] | withdrawn
WMECO | Greenfield | 6A4674-2019 | 01301 | 23.4 | Solar | 22B7 | 2019-12-31 | 2020-01-10 | 9 |  | 9 | 2020-01-13 | 2020-01-31 | 15 |  | 15 | [20 empty] | 2020-03-24 |  | Not Supplied |  | EXP | [9 empty] | cancelled
WMECO | Russell | 6A4686-2020 | 01071 | 2750 | Solar | 19J2 | 2020-01-13 | 2020-01-15 | 3 | 2 | 1 | 2020-01-16 | 2020-02-10 | 18 |  | 18 | [22 empty] | 2021-09-30 |  | EXP | [9 empty] | Plainfield / Blandford Group Study
WMECO | Greenfield | 6A4689-2020 | 01301 | 23.4 | Solar | 28WNW_1 | 2020-01-13 | 2020-01-28 | 12 |  | 12 | 2020-01-28 | 2020-01-30 | 3 |  | 3 | [20 empty] | 2020-06-01 |  | 2020-03-15 |  | EXP | [8 empty] | 2020-10-08 | on line
WMECO | Windsor | 6B2367-2020 | 01270 | 6 | Solar | 18C1 | 2020-01-16 | 2020-02-28 | 32 |  | 32 | 2020-02-28 | 2020-03-05 | 5 |  | 5 | [20 empty] | 2020-03-13 |  | not supplied |  | EXP | [8 empty] | 2021-01-08 | on line
WMECO | Chesterfield | 6A4702-2020 | 01012 | 17 | Solar | 18K3 | 2020-01-22 | 2020-01-24 | 3 |  | 3 | 2020-01-28 | 2020-01-28 | 1 |  | 1 | [22 empty] | March 2020 |  | EXP | [9 empty] | cancelled
WMECO | Shelburne | 6A4735-2020 | 01370 | 240 | Solar | 29R2 | 2020-02-19 | 2020-02-26 | 6 |  | 6 | 2020-02-27 | 2020-03-09 | 8 |  | 8 | 2020-04-07 | 2020-07-09 | 68 |  | 68 | [15 empty] | 2020-07-09 |  | Nov 2020 |  | EXP | [8 empty] | 2024-10-07 | customer hold
WMECO | Conway | 6A4737-2020 | 01341 | 17.6 | Solar | 38A1 | 2020-02-19 | 2020-02-28 | 8 |  | 8 | 2020-02-28 | 2020-03-05 | 5 |  | 5 | [20 empty] | 2020-04-07 |  | 2020-04-21 |  | EXP | [8 empty] | 2020-09-22 | on line
WMECO | Easthampton | 6A4739-2020 | 01027 | 133 | Solar | 15A3 | 2020-02-21 | 2020-02-28 | 6 |  | 6 | 2020-02-28 | 2020-03-13 | 11 |  | 11 | [20 empty] | 2020-08-27 |  | Nov 2020 |  | EXP | [8 empty] | 2023-09-05 | on line
WMECO | Greenfield | 6A4743-2020 | 01301 | 498 | Solar | 22B7 | 2020-02-25 | 2020-03-09 | 10 | 10 | 0 | 2020-03-09 | 2020-03-17 | 7 |  | 7 | 2020-09-15 | 2020-10-30 | 34 |  | 34 | [5 empty] | 2021-01-09 | 2022-11-14 | 481 | 109 | 372 | [5 empty] | 2023-01-12 |  | 2020 |  | EXP | [9 empty] | customer hold
WMECO | Easthampton | 6A4745-2020 | 01027 | 500 | Solar | 15A3 | 2020-02-26 | 2020-02-28 | 3 |  | 3 | 2020-02-28 | 2020-03-17 | 13 |  | 13 | 2020-06-08 | 2020-08-17 | 51 |  | 51 | [15 empty] | 2020-08-18 |  | Nov 2020 |  | EXP | [8 empty] | 2023-12-15 | on line
WMECO | Haldle | 6A4756-2020 | 01035 | 18 | Solar | 18G5 | 2020-02-27 | [31 empty] | Not Supplied |  | EXP | [9 empty] | cancelled
WMECO | Northfield | 6A4755-2020 | 01360 | 2000 | Solar | 21B8 | 2020-03-02 | 2020-06-24 | 83 | 80 | 3 | 2020-06-25 | 2020-07-23 | 21 |  | 21 | [10 empty] | 2020-11-06 | 2022-12-14 | 549 |  | 549 | [5 empty] | 2023-02-27 |  | 2021-01-29 |  | EXP | [9 empty] | customer hold - construction extension
WMECO | Shelburne Falls | 6A4759-2020 | 01370 | 60 | Solar | 29R2 | 2020-03-03 | 2020-03-09 | 5 |  | 5 | 2020-03-09 | 2020-03-12 | 4 |  | 4 | [20 empty] | 2020-05-27 |  | Nov 2020 |  | EXP | [8 empty] | 2021-01-20 | on line
WMECO | Erving | 6A4764-2020 | 01344 | 43.2 | Solar | 21B8 | 2020-03-09 | 2020-03-11 | 3 |  | 3 | 2020-03-12 | 2020-03-31 | 14 |  | 14 | [20 empty] | 2020-05-04 |  | 2020-02-27 |  | EXP | [8 empty] | 2020-12-01 | on line
WMECO | Amherst | 6A4781-2020 | 01002 | 17 | Solar | 17K2 | 2020-03-17 | 2020-04-02 | 13 |  | 13 | 2020-04-02 | 2020-04-06 | 3 |  | 3 | [20 empty] | 2020-05-28 |  | 2020-04-25 |  | EXP | [8 empty] | 2020-10-15 | on line
WMECO | Springfield | 6S6248-2020 | 01105 | 292 | Solar | 21S4 | 2020-03-18 | 2020-04-21 | 25 |  | 25 | 2020-04-21 | 2020-04-27 | 5 |  | 5 | 2021-01-19 | 2021-02-04 | 13 |  | 13 | [15 empty] | 2021-03-01 |  | Nov 2020 |  | EXP | [8 empty] | 2024-05-07 | on line
WMECO | Bernardston | 6A4815-2020 | 01337 | 996 | Solar | 21B8 | 2020-04-06 | 2020-11-03 | 152 | 0 | 152 | 2020-11-04 | 2020-11-09 | 4 |  | 4 | [22 empty] | July 2021 |  | EXP | [9 empty] | in system impact study queue
WMECO | Hatfield | 6A4825-2020 | 01038 | 2750 | Solar | 18G6 | 2020-04-13 | 2020-04-15 | 3 | 2 | 1 | 2020-04-16 | 2020-04-22 | 5 |  | 5 | [22 empty] | 2021-09-30 |  | EXP | [9 empty] | in system impact study queue
WMECO | Huntington | 6A4832-2020 | 01050 | 20 | Solar | 19J5 | 2020-04-17 | 2020-04-27 | 7 |  | 7 | 2020-04-28 | 2020-05-01 | 4 |  | 4 | [20 empty] | 2020-05-12 |  | Not Supplied |  | EXP | [8 empty] | 2020-09-11 | on line
WMECO | South Deerfield | 6A4834-2020 | 01373 | 10 | Battery | 22B1 | 2020-04-20 | 2020-04-27 | 6 |  | 6 | 2020-04-28 | 2020-05-05 | 6 |  | 6 | [20 empty] | 2020-05-15 |  | asap |  | EXP | [8 empty] | 2021-03-10 | on line
WMECO | Northfield | 6A4835-2020 | 01360 | 2250 | Solar | 21B8 | 2020-04-20 | 2020-06-24 | 48 | 45 | 3 | 2020-06-25 | 2020-07-23 | 21 |  | 21 | [10 empty] | 2020-11-06 |  | -31496 | [9 empty] | 2021-05-13 |  | EXP | [9 empty] | in system impact study queue
WMECO | Northfield | 6A4838-2020 | 01360 | 2000 | Solar | 21B8 | 2020-04-22 | 2020-06-24 | 46 | 43 | 3 | 2020-06-25 | 2020-07-23 | 21 |  | 21 | [10 empty] | 2020-11-06 |  | -31496 | [9 empty] | 2021-05-20 |  | EXP | [9 empty] | cancelled
WMECO | Northfield | 6A4839-2020 | 01360 | 2000 | Solar | 21B8 | 2020-04-23 | 2020-06-25 | 46 | 44 | 2 | 2020-06-26 | 2020-07-29 | 24 |  | 24 | [10 empty] | 2020-11-06 |  | -31496 | [9 empty] | 2021-05-20 |  | EXP | [9 empty] | in system impact study queue
WMECO | Plainfield | 6A4840-2020 | 01070 | 3300 | Solar | 18K3 | 2020-04-23 | 2020-06-26 | 47 |  | 47 | 2020-06-26 | 2020-07-29 | 24 |  | 24 | [22 empty] | 2021-05-20 |  | EXP | [9 empty] | cancelled
WMECO | Plainfield | 6A4841-2020 | 01070 | 3000 | Solar | 18K3 | 2020-04-23 | 2020-06-26 | 47 |  | 47 | 2020-06-26 | 2020-07-29 | 24 |  | 24 | [22 empty] | 2021-05-20 |  | EXP | [9 empty] | cancelled
WMECO | Bernardston | 6A4842-2020 | 01337 | 2000 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 47 | 44 | 3 | 2020-06-26 | 2020-08-06 | 30 |  | 30 | [22 empty] | 2021-05-20 |  | EXP | [9 empty] | in system impact study queue
WMECO | Bernardston | 6A4843-2020 | 01337 | 2000 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 47 | 44 | 3 | 2020-06-26 | 2020-07-29 | 24 |  | 24 | [22 empty] | 2021-05-20 |  | EXP | [9 empty] | cancelled
WMECO | Bernardston | 6A4844-2020 | 01337 | 2000 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 47 | 44 | 3 | 2020-06-26 | 2020-07-29 | 24 |  | 24 | [22 empty] | 2021-05-20 |  | EXP | [9 empty] | cancelled
WMECO | Bernardston | 6A4845-2020 | 01337 | 1570 | Solar | 21C1 | 2020-04-23 | 2020-06-26 | 47 | 44 | 3 | 2020-06-26 | 2020-07-29 | 24 |  | 24 | [22 empty] | 2021-05-20 |  | EXP | [9 empty] | cancelled
WMECO | Becket | 6B2431-2020 | 01223 | 3640 | Solar | 19J6 | 2020-04-23 | 2020-06-25 | 46 | 44 | 2 | 2020-06-26 | 2020-07-23 | 20 |  | 20 | [22 empty] | 2021-05-23 |  | Exp | [9 empty] | in system impact study queue
WMECO | Becket | 6B2432-2020 | 01223 | 7860 | Solar | 19J6 | 2020-04-23 | 2020-06-25 | 46 | 44 | 2 | 2020-06-26 | 2020-07-23 | 20 |  | 20 | [22 empty] | 2021-05-23 |  | Exp | [9 empty] | in system impact study queue
WMECO | Dalton | 6B2451-2020 | 01226 | 16 | Solar | 19A1 | 2020-05-05 | [31 empty] | 2020-06-29 |  | Exp | [9 empty] | cancelled
WMECO | Tolland | 6B2464-2020 | 01034 | 30.36 | Solar | 19J4 | 2020-05-21 | [31 empty] | not supplied |  | EXP | [9 empty] | withdrawn
WMECO | Amherst | 6A4896-2020 | 01002 | 10 | Battery | 17K4 | 2020-06-05 | 2020-07-14 | 28 |  | 28 | 2020-07-15 | 2020-08-19 | 26 |  | 26 | [20 empty] | 2020-09-28 |  | July 2020 |  | EXP | [8 empty] | 2021-12-22 | on line
WMECO | Tolland | 6B2480-2020 | 01034 | 30.36 | Solar | 19J4 | 2020-06-09 | 2020-08-18 | 51 | 49 | 2 | 2020-08-19 | 2020-09-03 | 12 |  | 12 | [20 empty] | 2021-10-21 |  | 2020-08-09 |  | EXP | [8 empty] | 2021-12-16 | on line
WMECO | Springfield | 6S6361-2020 | 01104 | 1669 | Solar | 5J13 | 2020-06-11 | 2020-06-25 | 11 | 11 | 0 | 2020-06-26 | 2020-07-30 | 25 |  | 25 | [10 empty] | 2020-12-04 | 2022-09-09 | 461 |  | 461 | [5 empty] | 2022-09-19 |  | 2020-10-01 |  | EXP | [9 empty] | in construction phase
WMECO | Lee | 6B2503-2020 | 01238 | 4000 | Solar | 16B1 | 2020-06-15 | 2020-07-09 | 19 |  | 19 | 2020-07-10 | 2020-10-15 | 70 |  | 70 | [22 empty] | 2021-04-01 |  | EXP | [9 empty] | cancelled
WMECO | Bernardston | 6A4913-2020 | 01337 | 4500 | Solar | 21C1 | 2020-06-24 | 2020-07-10 | 13 | 12 | 1 | 2020-07-13 | 2020-08-14 | 25 |  | 25 | [22 empty] | 2021-07-18 |  | EXP | [9 empty] | in system impact study queue
WMECO | Greenfield | 6A4914-2020 | 01301 | 1300 | Solar | 21C1 | 2020-06-24 | 2020-07-10 | 13 | 12 | 1 | 2020-07-13 | 2020-08-14 | 25 |  | 25 | [10 empty] | 2020-12-08 | 2022-12-30 | 539 | 18 | 521 | [5 empty] | 2023-01-12 |  | 2021-07-18 |  | EXP | [9 empty] | in construction phase
WMECO | Granville | 6S6392-2020 | 01034 | 6750 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 13 | 12 | 1 | 2020-07-13 | 2020-07-23 | 9 |  | 9 | [22 empty] | 2021-07-18 |  | EXP | [9 empty] | cancelled
WMECO | Granville | 6S6393-2020 | 01034 | 2250 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 13 | 12 | 1 | 2020-07-13 | 2020-07-23 | 9 |  | 9 | [10 empty] | 2022-07-15 | 2023-02-27 | 162 | 13 | 149 | [5 empty] | 2023-03-07 |  | 2021-07-18 |  | EXP | [9 empty] | in construction phase
WMECO | Granville | 6S6394-2020 | 01034 | 2250 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 13 | 12 | 1 | 2020-07-13 | 2020-09-25 | 55 |  | 55 | [10 empty] | 2022-07-15 | 2023-02-27 | 162 | 13 | 149 | [5 empty] | 2023-03-07 |  | 2021-07-18 |  | EXP | [9 empty] | in construction phase
WMECO | Granville | 6S6395-2020 | 01034 | 2250 | Solar | 29A5 | 2020-06-24 | 2020-07-10 | 13 | 13 | 0 | 2020-07-13 | 2020-10-05 | 61 |  | 61 | [10 empty] | 2022-07-15 | 2023-02-27 | 162 | 13 | 149 | [5 empty] | 2023-03-07 |  | 2020-07-18 |  | EXP | [9 empty] | in construction phase
WMECO | Dalton | 6B2502-2020 | 01226 | 499 | Solar | 19A3 | 2020-07-06 | 2020-08-05 | 23 | 22 | 1 | 2020-08-05 | 2020-08-14 | 8 | 34 | -26 |  |  |  | 0 | [16 empty] | 2021-05-12 |  | Dec 2020 |  | EXP | [8 empty] | 2023-12-29 | on line
WMECO | Feeding Hills | 6S6432-2020 | 01030 | 10 | Battery | 30A1 | 2020-07-13 | 2020-08-31 | 36 |  | 36 |  | 2020-09-23 | [23 empty] | 2020-10-02 |  | summer 2020 |  | EXP | [8 empty] | 2023-03-15 | on line
WMECO | Agawam | 6S6455-2020 | 01001 | 50 | Solar | 30A3 | 2020-07-22 | 2020-10-23 | 68 |  | 68 | 2020-10-26 | 2020-11-19 | 19 |  | 19 | [20 empty] | 2020-12-16 |  | 2020-09-21 |  | EXP | [8 empty] | 2021-05-20 | on line
WMECO | Tyringham | 6B2524-2020 | 01264 | 9.6 | Battery | 16B1 | 2020-07-24 | 2020-08-31 | 27 |  | 27 | 2020-08-31 | 2020-09-09 | 8 |  | 8 | [20 empty] | 2020-10-15 |  | Summer 2020 |  | EXP | [8 empty] | 2022-08-03 | on line
WMECO | Hatfield | 6A4961-2020 | 01038 | 20 | Solar | 18G6 | 2020-07-28 | 2020-09-09 | 32 |  | 32 | 2020-09-09 | 2020-09-18 | 8 |  | 8 | [20 empty] | 2020-10-05 |  | Autumn |  | EXP | [8 empty] | 2021-02-10 | on line
WMECO | Deerfield | 6A4968-2020 | 01342 | 900 | Solar | 22B1 | 2020-08-04 | 2020-09-09 | 27 | 24 | 3 | 2020-09-09 | 2020-09-28 | 14 |  | 14 | [22 empty] | April 2021 |  | EXP | [9 empty] | cancelled
WMECO | Granville | 6S6539-2020 | 01034 | 436 | Biogas | 29A5 | 2020-08-17 | 2020-09-16 | 23 | 20 | 3 | 2020-09-16 | 2020-10-21 | 26 |  | 26 | 2020-11-23 | 2021-01-25 | 46 |  | 46 | [17 empty] | 2021-01-15 |  | EXP | [9 empty] | in impact study
WMECO | Springfield | 6S6574-2020 | 01103 | 30 | Diesel | 8C24 | 2020-08-28 | 2020-09-22 | 18 | 15 | 3 | 2020-09-23 | 2020-10-27 | 25 | 21 | 4 | [20 empty] | 2021-03-11 |  | Dec 2020 |  | EXP | [8 empty] | 2021-06-23 | on line
WMECO | Springfield | 6S6575-2020 | 01103 | 75 | Diesel | 8C24 | 2020-08-28 | 2020-09-09 | 9 | 6 | 3 | 2020-09-10 | 2020-10-28 | 35 |  | 35 | [22 empty] | Dec 2020 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S6576-2020 | 01103 | 35 | Diesel | 8C23 | 2020-08-28 | 2020-09-23 | 19 | 16 | 3 | 2020-09-24 | 2020-10-27 | 24 |  | 24 | [22 empty] | Dec 2020 |  | EXP | [9 empty] | cancelled
WMECO | Shelburne | 6A5004-2020 | 01370 | 499 | Solar | 22B5 | 2020-09-03 | 2020-10-20 | 34 | 30 | 4 | 2020-10-21 | 2020-11-03 | 10 |  | 10 | [20 empty] | 2023-09-07 |  | Not Supplied |  | EXP | [9 empty] | ISA Issued - Waiting on Constr Payment
WMECO | Hadley | 6A5016-2020 | 01035 | 5000 | Solar | 18G4 | 2020-09-09 | 2020-09-09 | 1 | 0 | 1 | 2020-09-09 | 2020-09-18 | 8 |  | 8 | [10 empty] | 2021-04-21 | 2022-10-19 | 391 | 49 | 342 | [5 empty] | 2023-01-12 |  | 2020-12-15 |  | EXP | [9 empty] | in construction phase
WMECO | Amherst | 6A5034-2020 | 01002 | 14.64 | Solar | 17K2 | 2020-09-17 | 2020-11-19 | 46 |  | 46 | 2020-11-20 | 2020-11-25 | 4 |  | 4 | [20 empty] | 2020-11-25 |  | 2020-11-17 |  | EXP | [9 empty] | withdrawn
WMECO | Granville | 6S6623-2020 | 01034 | 15.36 | Solar | 29A5 | 2020-09-17 | 2021-09-03 | 252 | 237 | 15 | 2021-09-03 | 2021-09-27 | 17 | 0 | 17 | [20 empty] | 2021-10-01 |  | not supplied |  | EXP | [8 empty] | 2023-04-18 | on line
WMECO | Pittsfield | 6B2615-2020 | 01201 | 2490 | Solar | 30B3 | 2020-09-25 | 2020-10-20 | 18 | 11 | 7 | 2020-10-21 | 2020-11-09 | 14 |  | 14 | [10 empty] | 2021-02-22 | 2022-01-20 | 239 | 17 | 222 | [5 empty] | 2023-01-13 |  | 2021-10-01 |  | EXP | [9 empty] | in construction phase
WMECO | Pittsfield | 6B2616-2020 | 01201 | 996 | Solar | 30B3 | 2020-09-25 | 2020-10-20 | 18 | 11 | 7 | 2020-10-21 | 2020-10-23 | 3 |  | 3 | [10 empty] | 2021-02-22 | 2022-01-20 | 239 | 17 | 222 | [5 empty] | 2022-09-09 |  | 2021-10-01 |  | EXP | [9 empty] | in construction phase
WMECO | Amherst | 6A5066-2020 | 01002 | 20 | Solar | 17K2 | 2020-10-06 | 2020-11-02 | 20 | 15 | 5 | 2020-11-03 | 2020-11-03 | 1 |  | 1 | [20 empty] | 2021-06-03 |  | 2020-11-01 |  | Exp | [8 empty] | 2022-05-26 | on line
WMECO | Ludlow | 6S6730-2020 | 01056 | 990 | Solar | 19S1 | 2020-10-19 | 2020-11-02 | 11 | 7 | 4 | 2020-11-03 | 2021-01-05 | 46 |  | 46 | [10 empty] | 2021-05-11 | 2022-10-07 | 369 | 22 | 347 | [5 empty] | 2022-11-09 |  | 2022-09-01 |  | EXP | [9 empty] | cancelled
WMECO | Longmeadow | 6S6731-2020 | 01106 | 20 | Solar | 22H12 | 2020-10-20 | 2020-11-03 | 11 | 8 | 3 | 2020-11-04 | 2020-11-24 | 15 |  | 15 | [20 empty] | 2021-06-15 |  | 2020-12-20 |  | EXP | [8 empty] | 2023-04-12 | on line
WMECO | Greenfield | 6A5099-2020 | 01301 | 4990 | Battery | 21C1 | 2020-10-27 | 2020-11-05 | 8 |  | 8 | 2020-11-06 | 2020-11-09 | 2 |  | 2 | [22 empty] | 2021-11-20 |  | Exp | [9 empty] | withdrawn
WMECO | Springfield | 6S6762-2020 | 01109 | 130.9 | Solar | 5J17 | 2020-10-27 | 2020-11-09 | 10 | 4 | 6 | 2020-11-10 | 2020-12-21 | 30 | 0 | 30 | 2021-01-15 | 2021-02-17 | 24 | 15 | 9 | [15 empty] | 2021-03-02 |  | not supplied |  | EXP | [9 empty] | withdrawn
WMECO | West Springfield | 6S6770-2020 | 01089 | 20 | Solar | 21N4 | 2020-10-30 | 2020-12-08 | 28 | 23 | 5 | 2020-12-09 | 2021-04-05 | 84 | 0 | 84 | [20 empty] | 2021-04-05 |  | 2020-11-03 |  | EXP | [8 empty] | 2022-02-25 | on line
WMECO | Greenfield | 6A5102-2020 | 01301 | 4990 | Solar | 22B3 | 2020-11-05 | 2020-11-12 | 6 | 0 | 6 | 2020-11-12 | 2020-11-19 | 6 |  | 6 | [10 empty] | 2021-05-13 |  | -31630 | [9 empty] | 2022-09-01 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S6773-2020 | 01104 | 25 | Solar | 5J16 | 2020-11-05 | 2020-11-23 | 13 |  | 13 | 2020-11-24 | 2021-01-22 | 44 |  | 44 | [20 empty] | 2021-01-25 |  | 2021-01-31 |  | EXP | [8 empty] | 2023-01-24 | on line
WMECO | Plainfield | 6A5104-2020 | 01070 | 10 | Battery | 18K3 | 2020-11-09 | 2020-11-23 | 11 |  | 11 | 2020-11-24 | 2020-12-29 | 26 |  | 26 | [20 empty] | 2021-01-20 |  | not supplied |  | EXP | [8 empty] | 2022-05-16 | on line
WMECO | Pittsfield | 6B2658-2020 | 01201 | 2495 | Battery |  | 2020-11-12 | [31 empty] | 2021-11-20 |  | EXP | [9 empty] | cancelled
WMECO | Windsor | 6B2659-2020 | 01270 | 2495 | Battery |  | 2020-11-12 | [31 empty] | 2021-11-20 |  | EXP | [9 empty] | cancelled
WMECO | Agawam | 6S6772-2020 | 01001 | 15.2 | Solar | 16C17 | 2020-11-12 | 2020-11-16 | 3 |  | 3 | 2020-11-16 | 2020-12-03 | 14 |  | 14 | [20 empty] | 2021-03-01 |  | 2021-01-11 |  | EXP | [8 empty] | 2021-12-03 | on line
WMECO | Southwick | 6S6774-2020 | 01077 | 10 | Solar | 29A5 | 2020-11-13 | 2021-02-16 | 68 |  | 68 | 2021-02-16 | 2021-03-05 | 14 |  | 14 | [20 empty] | 2021-03-05 |  | 2021-01-13 |  | EXP | [8 empty] | 2021-11-08 | on line
WMECO | Lee | 6B2660-2020 | 01240 | 3625 | Solar | 16B5 | 2020-11-16 | 2020-11-23 | 6 | 2 | 4 | 2020-11-23 | 2020-11-30 | 6 |  | 6 | [22 empty] | Q 4 2021 |  | EXP | [9 empty] | cancelled
WMECO | Amherst | 6A5103-2020 | 01002 | 2840 | Solar |  | 2020-11-18 | [31 empty] | not supplied |  | EXP | [9 empty] | withdrawn
WMECO | Easthampton | 6A5105-2020 | 01029 | 125 | Solar | 15A2 | 2020-11-24 | 2020-12-09 | 12 |  | 12 | 2020-12-10 | 2021-02-08 | 43 |  | 43 | [20 empty] | 2021-02-08 |  | not supplied |  | EXP | [8 empty] | 2023-06-28 | on line
WMECO | Amherst | 6A5106-2020 | 01002 | 20 | Solar | 19B16 | 2020-12-03 | 2021-01-19 | 34 | 28 | 6 | 2021-01-19 | 2021-04-05 | 55 | 0 | 55 | [20 empty] | 2021-04-05 |  | 2021-01-24 |  | EXP | [8 empty] | 2021-12-02 | on line
WMECO | Deerfield | 6A5118-2020 | 01342 | 17.6 | Solar | 22B1 | 2020-12-10 | 2021-01-19 | 29 |  | 29 | 2021-01-19 | 2021-02-19 | 24 |  | 24 | [20 empty] | 2021-02-24 |  | 2021-02-07 |  | EXP | [8 empty] | 2022-01-11 | on line
WMECO | Amherst | 6A5119-2020 | 01002 | 20 | Solar | 17K5 | 2020-12-10 | 2021-01-19 | 29 |  | 29 | 2021-01-19 | 2021-02-19 | 24 |  | 24 | [20 empty] | 2021-02-24 |  | 2021-02-10 |  | EXP | [8 empty] | 2022-01-03 | on line
WMECO | South Deerfield | 6A5107-2020 | 01373 | 4980 | Solar |  | 2020-12-14 | [31 empty] | Not Supplied |  | EXP | [9 empty] | cancelled
WMECO | Westhampton | 6A5111-2020 | 01027 | 22.8 | Solar | 15A3 | 2020-12-16 | 2021-02-01 | 34 | 26 | 8 | 2021-02-01 | 2021-03-10 | 28 | 0 | 28 | [20 empty] | 2021-03-16 |  | not supplied |  | EXP | [8 empty] | 2021-10-19 | on line
WMECO | Ludlow | 6S6775-2020 | 01056 | 133.2 | Solar | 27A6 | 2020-12-16 | 2020-12-24 | 7 |  | 7 | 2020-12-24 | 2021-02-05 | 32 |  | 32 | [20 empty] | 2021-02-05 |  | 2021-04-01 |  | EXP | [9 empty] | cancelled
WMECO | Montague | 6A5108-2020 | 01376 | 4500 | Battery | 21C2 | 2020-12-17 | 2020-12-22 | 4 |  | 4 | 2020-12-22 | 2021-01-11 | 15 |  | 15 | [22 empty] | 2022-01-14 |  | EXP | [9 empty] | cancelled
WMECO | Montague | 6A5109-2020 | 01376 | 4500 | Battery | 21C2 | 2020-12-17 | 2020-12-22 | 4 |  | 4 | 2020-12-22 | 2021-01-11 | 15 |  | 15 | [22 empty] | 2022-01-14 |  | EXP | [9 empty] | cancelled
WMECO | Northfield | 6A5110-2020 | 01360 | 4500 | Battery | 21B8 | 2020-12-17 | 2020-12-22 | 4 |  | 4 | 2020-12-22 | 2021-01-11 | 15 |  | 15 | [22 empty] | 2022-01-14 |  | EXP | [9 empty] | cancelled
WMECO | Worthington | 6A5112-2020 | 01098 | 1990 | Solar | 18K3 | 2020-12-22 | 2020-12-24 | 3 |  | 3 | 2020-12-24 | 2021-01-11 | 13 |  | 13 | [10 empty] | 2021-04-20 |  | -31613 | [9 empty] | 2022-01-16 |  | EXP | [9 empty] | cancelled
WMECO | Feeding Hills | 6S6776-2020 | 01030 | 7.6 | Solar | 16C17 | 2020-12-22 | 2021-01-21 | 23 |  | 23 | 2021-01-21 | 2021-02-16 | 19 | 0 | 19 | [20 empty] | 2021-02-16 |  | 2020-12-21 |  | EXP | [8 empty] | 2021-07-19 | on line
WMECO | Shelburne | 6A5113-2020 | 01370 | 10 | Solar | 22B5 | 2020-12-23 | 2021-01-05 | 10 |  | 10 | 2021-01-05 | 2021-02-16 | 31 |  | 31 | [20 empty] | 2021-02-16 |  | May |  | EXP | [8 empty] | 2021-12-20 | on line
WMECO | Feeding Hills | 6S6777-2020 | 01030 | 17.6 | Solar | 16C17 | 2020-12-23 | 2021-03-04 | 52 |  | 52 | 2021-03-04 | 2021-03-12 | 7 | 0 | 7 | [20 empty] | 2021-03-19 |  | 2021-02-22 |  | EXP | [8 empty] | 2021-07-19 | on line
WMECO | Cummington | 6A5114-2020 | 01026 | 4990 | Battery | 18K3 | 2020-12-28 | 2021-01-14 | 14 |  | 14 | 2021-01-14 | 2021-01-27 | 10 |  | 10 | [22 empty] | 2022-01-22 |  | EXP | [9 empty] | cancelled
WMECO | Amherst | 6A5115-2020 | 01002 | 4990 | Battery | 18G3 | 2020-12-28 | 2021-01-11 | 11 |  | 11 | 2021-01-11 | 2021-01-29 | 15 |  | 15 | [22 empty] | 2022-01-22 |  | EXP | [9 empty] | cancelled
WMECO | Hinsdale | 6B2662-2020 | 01235 | 2495 | Battery | 18C2 | 2020-12-28 | 2021-01-14 | 14 |  | 14 | 2021-01-14 | 2021-02-10 | 20 |  | 20 | [22 empty] | 2022-01-18 |  | EXP | [9 empty] | cancelled
WMECO | Hinsdale | 6B2663-2020 | 01235 | 2495 | Battery | 18C2 | 2020-12-28 | 2021-01-14 | 14 |  | 14 | 2021-01-14 | 2021-02-10 | 20 |  | 20 | [22 empty] | 2022-01-18 |  | EXP | [9 empty] | cancelled
WMECO | Otis | 6B2664-2020 | 01253 | 4990 | Battery | 19J4 | 2020-12-28 | 2021-01-11 | 11 |  | 11 | 2021-01-11 | 2021-02-02 | 17 |  | 17 | [22 empty] | 2022-01-18 |  | EXP | [9 empty] | cancelled
WMECO | Bernardston | 6A5116-2020 | 01337 | 4990 | Battery | 21C1 | 2020-12-29 | 2021-01-19 | 16 |  | 16 | 2021-01-19 | 2021-01-27 | 7 |  | 7 | [22 empty] | 2022-01-14 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S6778-2020 | 01119 | 4.8 | Solar | 20A33 | 2020-12-29 | [31 empty] | 2021-01-01 |  | EXP | [9 empty] | withdrawn
WMECO | Ludlow | 6S6779-2020 | 01056 | 5000 | Battery |  | 2020-12-29 | 2021-01-19 | 16 |  | 16 | 2021-01-19 | 2021-02-19 | 24 |  | 24 | [22 empty] | 2022-01-14 |  | EXP | [9 empty] | cancelled
WMECO | Easthampton | 6A5120-2021 | 01027 | 120 | Solar | 15A2 | 2021-01-08 | 2021-01-19 | 8 |  | 8 | 2021-01-19 | 2021-02-22 | 25 |  | 25 | [20 empty] | 2021-03-01 |  | 2021-06-01 |  | Exp | [8 empty] | 2021-09-29 | on line
WMECO | Easthampton | 6A5121-2021 | 01027 | 16.86 | Battery | 15A5 | 2021-01-08 | 2021-02-01 | 17 |  | 17 | 2021-02-01 | 2021-03-12 | 30 |  | 30 | [20 empty] | 2021-05-10 |  | March 2021 |  | EXP | [9 empty] | cancelled
WMECO | Windsor | 6A5117-2021 | 01270 | 10 | Battery | 18K3 | 2021-01-11 | 2021-02-01 | 16 |  | 16 | 2021-02-01 | 2021-03-10 | 28 |  | 28 | [20 empty] | 2021-05-11 |  | not supplied |  | EXP | [9 empty] | cancelled
WMECO | Lanesborough | 6B2665-2021 | 01224 | 4990 | Solar | 19A5 | 2021-01-14 | 2021-02-22 | 28 |  | 28 | 2021-02-22 | 2021-03-15 | 16 |  | 16 | [10 empty] | 2021-05-20 |  | -31635 | [9 empty] | ASAP |  | EXP | [9 empty] | withdrawn
WMECO | Westfield | 6S6780-2021 | 01085 | 2000 | Hydro | 18F1 | 2021-01-19 | 2021-02-01 | 10 | 4 | 6 | 2021-02-01 | 2021-04-26 | 61 | 0 | 61 |  |  |  | 0 | [18 empty] | 2023-12-01 |  | EXP | [9 empty] | withdrawn
WMECO | Becket | 6B2666-2021 | 01223 | 10 | Solar | 19J6 | 2021-01-21 | 2021-02-22 | 23 |  | 23 | 2021-02-22 | 2021-03-24 | 23 |  | 23 | [20 empty] | 2021-05-25 |  | Spring 2021 |  | EXP | [8 empty] | 2022-10-05 | on line
WMECO | Ludlow | 6S6781-2021 | 01056 | 990 | Solar | 19S1 | 2021-01-26 | 2021-02-02 | 6 |  | 6 | 2021-02-02 | 2021-02-19 | 14 |  | 14 | [22 empty] | 2022-07-01 |  | EXP | [9 empty] | in impact study
WMECO | Easthampton | 6A5123-2021 | 01027 | 450 | Solar | 15A2 | 2021-01-29 | 2021-02-22 | 17 | 4 | 13 | 2021-02-22 | 2021-03-15 | 16 | 0 | 16 | [10 empty] | 2021-12-01 | 2022-06-14 | 140 | 8 | 132 | [5 empty] | 2022-08-08 |  | 2021-09-01 |  | Exp | [8 empty] | 2023-12-19 | on line
WMECO | Amherst | 6A5122-2021 | 01002 | 25 | Solar | 18G7 | 2021-02-01 | 2021-02-22 | 16 |  | 16 | 2021-02-22 | 2021-03-24 | 23 |  | 23 | [20 empty] | 2021-03-26 |  | not supplied |  | Exp | [8 empty] | 2022-05-26 | on line
WMECO | Dalton | 6B2667-2021 | 01226 | 25 | Solar | 19A2 | 2021-02-03 | 2021-02-22 | 14 |  | 14 | 2021-02-22 | 2021-04-05 | 31 | 0 | 31 | [20 empty] | 2021-05-12 |  | not supplied |  | EXP | [9 empty] | cancelled
WMECO | Southwick | 6S6782-2021 | 01077 | 4600 | Solar | 29A1 | 2021-02-10 | 2021-02-22 | 9 |  | 9 | 2021-02-22 | 2021-03-22 | 21 |  | 21 | [10 empty] | 2021-09-21 | 2022-11-29 | 311 |  | 311 | [5 empty] | 2022-12-08 |  | 2021-12-31 |  | EXP | [9 empty] | in construction phase
WMECO | Dalton | 6B2669-2021 | 01226 | 2660 | Solar | 18C1 | 2021-02-15 | 2021-02-22 | 6 | 3 | 3 | 2021-02-22 | 2021-03-04 | 9 |  | 9 | [10 empty] | 2021-05-19 | 2022-08-23 | 330 | 38 | 292 | [5 empty] | 2023-01-11 |  | not supplied |  | EXP | [9 empty] | in construction phase
WMECO | Pittsfield | 6B2668-2021 | 01201 | 86.4 | Solar | 30B7 | 2021-02-16 | 2021-03-25 | 28 | 27 | 1 | 2021-03-25 | 2021-04-26 | 23 | 0 | 23 | [20 empty] | 2021-05-13 |  | 2021-06-15 |  | EXP | [8 empty] | 2022-06-30 | on line
WMECO | Hadley | 6A5124-2021 | 01035 | 20 | Battery | 17K5 | 2021-02-18 | 2021-03-03 | 10 | 9 | 1 | 2021-03-03 | 2021-04-05 | 24 | 0 | 24 | [20 empty] | 2021-04-05 |  | March 2021 |  | Exp | [8 empty] | 2022-04-15 | on line
WMECO | Springfield | 6S6783-2021 | 01119 | 4.8 | Solar | 20A33 | 2021-02-18 | 2021-02-22 | 3 | 2 | 1 | 2021-02-22 | 2021-03-08 | 11 | 0 | 11 | [20 empty] | 2021-03-11 |  | 2021-01-31 |  | EXP | [9 empty] | cancelled
WMECO | Blandford | 6B2670-2021 | 01008 | 1000 | Solar | 19J2 | 2021-02-26 | 2021-03-25 | 20 | 19 | 1 | 2021-03-25 | 2021-04-23 | 22 | 6 | 16 |  |  |  | 0 | [18 empty] | Jan 2022 |  | EXP | [9 empty] | cancelled
WMECO | Hatfield | 6A5125-2021 | 01038 | 250 | Biogas | 18G6 | 2021-03-01 | 2021-05-19 | 58 | 56 | 2 | 2021-05-19 | 2021-06-14 | 19 | 0 | 19 | [22 empty] | 2021-08-30 |  | Exp | [9 empty] | in system impact study queue
WMECO | Easthampton | 6A5126-2021 | 01027 | 17.6 | Solar | 15A5 | 2021-03-09 | 2021-03-29 | 15 | 6 | 9 | 2021-03-29 | 2021-05-03 | 26 | 2 | 24 | [20 empty] | 2021-05-26 |  | not supplied |  | Exp | [9 empty] | cancelled
WMECO | Agawam | 6S6784-2021 | 01001 | 360 | Solar | 30A2 | 2021-03-09 | 2021-03-25 | 13 | 4 | 9 | 2021-03-25 | 2021-04-22 | 21 | 0 | 21 | [20 empty] | 2021-07-22 |  | 2021-12-31 |  | EXP | [9 empty] | cancelled
WMECO | Agawam | 6S6785-2021 | 01001 | 499.9 | Solar | 30A2 | 2021-03-09 | 2021-03-25 | 13 | 4 | 9 | 2021-03-25 | 2021-04-29 | 26 | 0 | 26 | [20 empty] | 2021-07-22 |  | 2021-12-31 |  | EXP | [9 empty] | cancelled
WMECO | Pittsfield | 6B2671-2021 | 01201 | 166.6 | Solar | 30B4 | 2021-03-12 | 2021-03-29 | 12 | 9 | 3 | 2021-03-29 | 2021-04-26 | 21 | 0 | 21 | [20 empty] | 2021-05-13 |  | 2021-09-01 |  | EXP | [9 empty] | customer hold
WMECO | Lanesborough | 6B2672-2021 | 01237 | 16 | Solar | 15E1 | 2021-03-16 | 2021-03-29 | 10 | 6 | 4 | 2021-03-29 | 2021-04-26 | 21 | 0 | 21 | [20 empty] | 2021-05-13 |  | not supplied |  | EXP | [8 empty] | 2022-05-13 | on line
WMECO | Springfield | 6S6786-2021 | 01128 | 500 | Solar |  | 2021-03-18 | [31 empty] | Oct 2021 |  | EXP | [9 empty] | cancelled
WMECO | Springfield | 6S6787-2021 | 01129 | 500 | Solar |  | 2021-03-18 | [33 empty] | EXP | [9 empty] | cancelled
WMECO | Northfield | 6A5127-2021 | 01360 | 1500 | Solar | 21B8 | 2021-03-26 | 2021-04-09 | 11 | 0 | 11 | 2021-04-09 | 2021-04-19 | 7 |  | 7 | [22 empty] | 2022-04-24 |  | Exp | [9 empty] | cancelled
WMECO | Hadley | ESMAEX-00037 | 01035 | 25 | Solar & Battery | 18G4 | 2021-04-08 | 2021-05-03 | 18 |  | 18 |  |  | 0 | [22 empty] | 2021-05-06 | [12 empty] | 2022-02-11 | Online | [8 empty] | 18G PODICK
WMECO | Southwick | ESMAEX-00043 | 01077 | 8.7 | Solar & Battery | 29A1 | 2021-04-14 | 2021-05-18 | 25 |  | 25 |  |  | 0 | [22 empty] | 2021-06-07 | [12 empty] | 2021-12-16 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Indian Orchard | ESMAEX-00045 | 01151 | 2040 | Solar |  | 2021-05-28 | 2021-06-21 | 17 |  | 17 |  |  | 0 | [22 empty] | 2024-12-06 | [12 empty] | 2025-09-26 | Online | [6 empty] | 2023 ASO Batch 1
WMECO | West Springfield | ESMAEX-00061 | 01089 | 21.4 | Solar & Battery | 21N9 | 2021-04-19 | 2021-05-18 | 22 |  | 22 |  |  | 0 | [22 empty] | 2021-05-24 | [12 empty] | 2022-01-18 | Online | [7 empty] | 11.4 | 21N PIPER
WMECO | Ludlow | ESMAEX-00069 | 01056 | 19.8 | Solar | 27A6 | 2021-04-22 | 2021-05-18 | 19 |  | 19 |  |  | 0 | [22 empty] | 2021-06-21 | [12 empty] | 2021-11-02 | Online | [7 empty] | 9.8 | 27A ORCHARD
WMECO | Amherst | ESMAEX-00170 | 01002 | 66.6 | Solar | 17K4 | 2022-02-11 | 2021-06-21 | -170 |  |  |  |  | 0 | [22 empty] | 2022-02-11 | [12 empty] | 2023-01-11 | Online | [8 empty] | 17K AMHERST
WMECO | Huntington | ESMAEX-00294 | 01050 | 20 | Solar | 19J5 | 2021-08-11 | 2021-08-23 | 9 |  | 9 |  |  | 0 | [22 empty] | 2021-09-21 | [12 empty] | 2022-06-28 | Online
WMECO | Chicopee | ESMAEX-00185 | 01013 | 4999 | Battery | 21N7 | 2021-06-15 | 2024-10-23 | 877 |  | 877 |  |  | 0 | [22 empty] | 2024-03-27 | [13 empty] | Technical Review | [6 empty] | 2023 ASO Batch 1 | 4999 | 21N PIPER
WMECO | Greenfield | ESMAEX-00134 | 01301 | 15 | Solar | 22B7 | 2021-05-18 | 2021-06-01 | 11 |  | 11 |  |  | 0 | [22 empty] | 2021-07-14 | [12 empty] | 2021-10-26 | Online | [8 empty] | 22B CUMBERLAND
WMECO | New Ashford | ESMAEX-00146 | 01237 | 10 | Solar & Battery | 15E1 | 2021-05-24 | 2021-06-21 | 21 |  | 21 |  |  | 0 | [22 empty] | 2021-06-24 | [12 empty] | 2022-10-03 | Online
WMECO | Huntington | ESMAEX-00150 | 01050 | 18 | Solar & Battery | 19J5 | 2021-05-26 | 2021-06-21 | 19 |  | 19 |  |  | 0 | [22 empty] | 2021-08-03 | [12 empty] | 2021-11-15 | Online | [7 empty] | 7.68
WMECO | Colrain | ESMAEX-00162 | 01340 | 22.8 | Solar | 29R2 | 2021-06-02 | 2021-06-21 | 14 |  | 14 |  |  | 0 | [22 empty] | 2021-07-02 | [12 empty] | 2021-12-02 | Online | [8 empty] | 29R SHELBURNE
WMECO | Springfield | ESMAEX-00165 | 01109 | 7.5 | Solar | 5J17 | 2021-06-03 | 2021-06-21 | 13 |  | 13 |  |  | 0 | [22 empty] | 2021-07-12 | [12 empty] | 2021-12-10 | Online | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Hadley | ESMAEX-00177 | 01035 | 375 | Solar | 18G5 | 2021-06-09 | 2021-06-21 | 9 |  | 9 |  |  | 0 | [22 empty] | 2021-11-19 | [12 empty] | 2024-06-14 | Online | [8 empty] | 18G PODICK
WMECO | Agawam | ESMAEX-00366 | 01001 | 17.6 | Solar & Battery | 16C16 | 2021-08-27 | 2021-09-30 | 25 |  | 25 |  |  | 0 | [22 empty] | 2021-10-26 | [12 empty] | 2022-05-13 | Online | [8 empty] | 16C AGAWAM
WMECO | Agawam | ESMAEX-00187 | 01001 | 22 | Solar | 16C16 | 2021-06-15 | 2021-07-16 | 24 |  | 24 |  |  | 0 | [22 empty] | 2021-07-20 | [12 empty] | 2021-10-13 | Online | [7 empty] | 12 | 16C AGAWAM
WMECO | Hadley | ESMAEX-00212 | 01035 | 10.44 | Solar | 19B15 | 2021-06-25 | 2021-07-16 | 16 |  | 16 |  |  | 0 | [22 empty] | 2021-08-03 | [12 empty] | 2021-10-26 | Online | [8 empty] | 19B MIDWAY
WMECO | Pittsfield | ESMAEX-00205 | 01201 | 60 | Internal Combustion Engine | 30B2 | 2021-06-23 | 2021-07-16 | 18 |  | 18 |  |  | 0 | [22 empty] | 2021-12-21 | [12 empty] | 2025-07-28 | Online | [8 empty] | 30B OSWALD
WMECO | Southampton | ESMAEX-00220 | 01073 | 996 | Solar & Battery | 15A1 | 2021-10-20 | 2021-10-26 | 5 |  | 5 |  |  | 0 | [22 empty] | 2024-05-02 | [13 empty] | Compliances Documents | [7 empty] | 2000 | 15A GUNN
WMECO | Greenfield | ESMAEX-00256 | 01301 | 100.8 | Solar | 21C1 | 2021-07-21 | 2021-08-06 | 13 |  | 13 |  |  | 0 | [22 empty] | 2021-08-25 | [12 empty] | 2023-09-14 | Online | [8 empty] | 21C MONTAGUE
WMECO | Tyringham | ESMAEX-00233 | 01264 | 22.8 | Solar | 16B1 | 2021-07-12 | 2021-08-23 | 31 |  | 31 |  |  | 0 | [22 empty] | 2021-11-17 | [12 empty] | 2022-04-11 | Online | [8 empty] | 16B PLEASANT
WMECO | Westhampton | ESMAEX-00728 | 01027 | 30 | Battery | 15A3 | 2022-01-13 | 2022-01-26 | 10 |  | 10 |  |  | 0 | [22 empty] | 2022-01-28 | [12 empty] | 2022-07-27 | Online | [8 empty] | 15A GUNN
WMECO | Feeding Hills | ESMAEX-00242 | 01030 | 8 | Solar | 30A1 | 2021-07-16 | 2021-08-06 | 16 |  | 16 |  |  | 0 | [22 empty] | 2021-08-09 | [12 empty] | 2021-10-07 | Online | [8 empty] | 30A SILVER
WMECO | Springfield | ESMAEX-00290 | 01103 | 150 | Internal Combustion Engine | 8C24 | 2022-01-20 | 2022-02-10 | 16 |  | 16 |  |  | 0 | [22 empty] | 2022-05-18 | [12 empty] | 2022-11-22 | Online | [7 empty] | 0 | 8C WEST SPRINGFIELD
WMECO | Easthampton | ESMAEX-00295 | 01027 | 9.8 | Solar | 15A1 | 2021-08-10 | 2021-10-12 | 46 |  | 46 |  |  | 0 | [22 empty] | 2021-10-26 | [12 empty] | 2022-01-31 | Online | [8 empty] | 15A GUNN
WMECO | Springfield | ESMAEX-00296 | 01129 | 17.6 | Solar | 20A23 | 2021-08-10 | 2021-10-21 | 53 |  | 53 |  |  | 0 | [22 empty] | 2021-11-01 | [12 empty] | 2022-05-10 | Online | [8 empty] | 20A BRECKWOOD
WMECO | Springfield | ESMAEX-00332 | 01105 | 60 | Internal Combustion Engine | 21S5 | 2021-08-19 | 2021-10-22 | 47 |  | 47 |  |  | 0 | [22 empty] | 2021-11-01 | [12 empty] | 2022-05-06 | Online | [8 empty] | 21S CLINTON
WMECO | Hadley | ESMAEX-00369 | 01035 | 45.6 | Solar | 18G4 | 2021-08-30 | 2021-08-30 | 1 |  | 1 |  |  | 0 | [22 empty] | 2022-05-05 | [12 empty] | 2023-10-24 | Online | [8 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-00383 | 01109 | 17.5 | Battery | 5J17 | 2021-09-03 | 2021-10-26 | 38 |  | 38 |  |  | 0 | [22 empty] | 2021-11-02 | [12 empty] | 2021-12-01 | Online | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Springfield | ESMAEX-00370 | 01109 | 15.8 | Solar | 20A31 | 2021-08-30 | 2021-09-20 | 16 |  | 16 |  |  | 0 | [22 empty] | 2021-09-28 | [12 empty] | 2022-01-27 | Online | [8 empty] | 20A BRECKWOOD
WMECO | Southwick | ESMAEX-00401 | 01077 | 18 | Solar | 29A1 | 2021-09-10 | 2021-09-28 | 13 |  | 13 |  |  | 0 | [22 empty] | 2021-09-28 | [12 empty] | 2023-02-07 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Ludlow | ESMAEX-00475 | 01056 | 1992 | Solar & Battery | 27A5 | 2021-10-06 | 2021-10-12 | 5 |  | 5 |  |  | 0 | [22 empty] | 2024-12-17 | [13 empty] | Construction Stage | [6 empty] | 2023 ASO Batch 1 |  | 27A ORCHARD
WMECO | West Springfield | ESMAEX-00456 | 01089 | 16.225 | Solar | 21N9 | 2021-09-29 | 2021-10-26 | 20 |  | 20 |  |  | 0 | [22 empty] | 2021-11-02 | [12 empty] | 2023-10-11 | Online | [8 empty] | 21N PIPER
WMECO | Westhampton | ESMAEX-00459 | 01027 | 9.735 | Solar & Battery | 15A3 | 2021-09-30 | 2021-10-12 | 9 |  | 9 |  |  | 0 | [22 empty] | 2021-11-30 | [12 empty] | 2022-05-24 | Online | [8 empty] | GUNN
WMECO | Longmeadow | ESMAEX-00471 | 01106 | 15.2 | Solar | 22H11 | 2021-10-04 | 2021-11-08 | 26 |  | 26 |  |  | 0 | [22 empty] | 2021-11-29 | [12 empty] | 2022-09-12 | Online | [8 empty] | 22H FRANCONIA
WMECO | Springfield | ESMAEX-00491 | 01107 | 3000 | Internal Combustion Engine | 21S8 | 2021-10-12 | 2021-11-09 | 21 |  | 21 |  |  | 0 | [22 empty] | 2022-04-11 | [12 empty] | 2023-08-07 | Online | [8 empty] | 21S CLINTON
WMECO | Sunderland | ESMAEX-00483 | 01375 | 60 | Solar | 18G3 | 2021-10-08 | 2021-10-26 | 13 |  | 13 |  |  | 0 | [22 empty] | 2021-11-30 | [12 empty] | 2023-08-07 | Online | [8 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-00501 | 01104 | 108 | Solar | 5J9 | 2021-10-14 | 2021-10-26 | 9 |  | 9 |  |  | 0 | [22 empty] | 2022-06-06 | [12 empty] | 2023-08-31 | Online | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Bernardston | ESMAEX-00657 | 01337 | 2200 | Solar & Battery | 21B8 | 2021-12-13 | 2021-12-14 | 2 |  | 2 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Gill-Montague |  | Whatley-Deerfield | 2023 ASO Batch 1 |  | 21B FRENCH KING
WMECO | Colrain | ESMAEX-00550 | 01340 | 10 | Battery | 29R2 | 2021-10-27 | 2021-11-08 | 9 |  | 9 |  |  | 0 | [22 empty] | 2021-12-01 | [12 empty] | 2023-03-07 | Online | [8 empty] | 29R SHELBURNE
WMECO | Hinsdale | ESMAEX-00541 | 01235 | 20 | Solar | 18C2 | 2021-10-25 | 2021-11-08 | 11 |  | 11 |  |  | 0 | [22 empty] | 2021-11-30 | [12 empty] | 2022-09-14 | Online | [8 empty] | BERKSHIRE
WMECO | Agawam | ESMAEX-00578 | 01001 | 4990 | Battery | 30A6 | 2022-01-12 | 2022-01-20 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-12-05 | [13 empty] | Compliances Documents | [6 empty] | 2023 ASO Batch 1 |  | 30A SILVER
WMECO | Chicopee | ESMAEX-00750 | 01013 | 4100 | Fuel Cell | 21N7 | 2022-01-21 | 2022-02-10 | 15 |  | 15 |  |  | 0 | [22 empty] | 2025-04-07 | [12 empty] | 2026-01-29 | Permission to Operate | [6 empty] | 2023 ASO Batch 1 |  | 21N PIPER
WMECO | Hinsdale | ESMAEX-00608 | 01235 | 19.52 | Solar | 18C2 | 2021-11-19 | 2021-12-12 | 16 |  | 16 |  |  | 0 | [22 empty] | 2022-01-10 | [12 empty] | 2022-03-29 | Online |  |  |  | Dalton-Hinsdale |  |  |  |  | 18C BERKSHIRE
WMECO | Dalton | ESMAEX-00846 | 01226 | 42.6 | Solar |  | 2022-02-22 | 2022-03-07 | 10 |  | 10 |  |  | 0 | [22 empty] | 2022-05-10 | [12 empty] | 2022-08-02 | Online
WMECO | Springfield | ESMAEX-00618 | 01128 | 9.92 | Solar & Battery | 20A34 | 2021-11-23 | 2021-12-08 | 12 |  | 12 |  |  | 0 | [22 empty] | 2022-01-11 | [12 empty] | 2022-03-22 | Online | [8 empty] | 20A BRECKWOOD
WMECO | Montague | ESMAEX-00653 | 01351 | 5 | Battery | 21C2 | 2021-12-10 | 2021-12-16 | 5 |  | 5 |  |  | 0 | [22 empty] | 2022-01-18 | [12 empty] | 2022-11-23 | Online |  |  |  | Gill-Montague |  |  |  | 14 | 21C MONTAGUE
WMECO | Southwick | ESMAEX-00695 | 01077 | 3984 | Solar | 29A3 | 2022-01-31 | 2022-02-10 | 9 |  | 9 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Southwick |  |  | 2023 ASO Batch 1 |  | 29A SOUTHWICK
WMECO | Buckland | ESMAEX-00739 | 01338 | 24 | Solar | 38A1 | 2022-01-19 | 2022-01-28 | 8 |  | 8 |  |  | 0 | [22 empty] | 2022-01-31 | [12 empty] | 2023-03-02 | Online | [8 empty] | 38A ASHFIELD
WMECO | Erving | ESMAEX-00810 | 01344 | 2600 | Battery | 21C8 | 2022-02-04 | 2022-02-28 | 17 |  | 17 |  |  | 0 | [36 empty] | Impact Study | [6 empty] | 2023 ASO Batch 1 |  | 21C MONTAGUE
WMECO | Huntington | ESMAEX-01101 | 01050 | 4250 | Solar & Battery | 19J5 | 2022-05-12 | 2022-05-26 | 11 |  | 11 |  |  | 0 | [36 empty] | Compliances Documents |  |  |  | Blandford |  |  | 2023 ASO Batch 1 |  | 19J BLANDFORD
WMECO | Lee | ESMAEX-00749 | 01238 | 9.49 | Solar & Battery | 16B5 | 2022-01-21 | 2022-01-24 | 2 |  | 2 |  |  | 0 | [22 empty] | 2022-03-02 | [12 empty] | 2023-04-03 | Online | [8 empty] | 16B PLEASANT
WMECO | Northfield | ESMAEX-00836 | 01360 | 40 | Battery |  | 2022-02-16 | 2022-03-10 | 17 |  | 17 |  |  | 0 | [22 empty] | 2022-03-15 | [12 empty] | 2022-07-01 | Online
WMECO | Whately | ESMAEX-00756 | 01093 | 6.4 | Battery | 18G6 | 2022-01-25 | 2022-01-28 | 4 |  | 4 |  |  | 0 | [22 empty] | 2022-01-28 | [12 empty] | 2022-06-15 | Online | [8 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-00823 | 01105 | 46.4 | Solar | 21S4 | 2022-02-09 | 2022-02-18 | 8 |  | 8 |  |  | 0 | [22 empty] | 2022-04-01 | [12 empty] | 2023-01-10 | Online | [8 empty] | CLINTON
WMECO | Longmeadow | ESMAEX-00766 | 01106 | 7.09 | Solar & Battery | 22H11 | 2022-01-29 | 2022-02-22 | 17 |  | 17 |  |  | 0 | [22 empty] | 2022-03-09 | [12 empty] | 2022-04-21 | Online | [8 empty] | 22H FRANCONIA
WMECO | Springfield | ESMAEX-00777 | 01118 | 4999.2 | Battery | 20A21 | 2023-01-18 | 2023-02-17 | 23 |  | 23 |  |  | 0 | [26 empty] | Complex | [9 empty] | Exhibit E Agreement | [7 empty] | 4.9998 | 20A BRECKWOOD
WMECO | Lee | ESMAEX-00806 | 01238 | 7.6 | Solar & Battery | 16B5 | 2022-02-03 | 2022-04-06 | 45 |  | 45 |  |  | 0 | [22 empty] | 2022-04-12 | [12 empty] | 2022-09-08 | Online | [8 empty] | 16B PLEASANT
WMECO | Pittsfield | ESMAEX-00914 | 01201 | 440 | Solar | 19A3 | 2022-04-07 | 2022-04-19 | 9 |  | 9 |  |  | 0 | [22 empty] | 2022-07-06 | [12 empty] | 2024-09-12 | Online | [8 empty] | 19A DOREEN
WMECO | Lee | ESMAEX-00855 | 01238 | 19.8 | Solar & Battery | 16B1 | 2022-02-24 | 2022-03-02 | 5 |  | 5 |  |  | 0 | [22 empty] | 2022-04-05 | [12 empty] | 2023-01-09 | Online | [8 empty] | 16B PLEASANT
WMECO | Pittsfield | ESMAEX-00854 | 01201 | 15.2 | Solar & Battery | 30B7 | 2022-02-24 | 2022-04-06 | 30 |  | 30 |  |  | 0 | [22 empty] | 2022-04-12 | [12 empty] | 2023-09-14 | Online | [8 empty] | 30B OSWALD
WMECO | West Springfield | ESMAEX-00868 | 01089 | 5 | Battery | 21N4 | 2022-03-01 | 2022-03-29 | 21 |  | 21 |  |  | 0 | [22 empty] | 2022-05-02 | [12 empty] | 2022-09-01 | Online | [7 empty] | 14 | 21N PIPER
WMECO | Feeding Hills | ESMAEX-00898 | 01030 | 15.2 | Solar | 30A6 | 2022-03-11 | 2022-03-17 | 5 |  | 5 |  |  | 0 | [22 empty] | 2022-03-22 | [12 empty] | 2022-12-21 | Online | [8 empty] | 30A SILVER
WMECO | Springfield | ESMAEX-00942 | 01108 | 13.6 | Solar | 22H16 | 2022-03-17 | 2022-03-28 | 8 |  | 8 |  |  | 0 | [22 empty] | 2022-05-02 | [12 empty] | 2022-10-17 | Online | [8 empty] | 22H FRANCONIA
WMECO | Ludlow | ESMAEX-00910 | 01056 | 9.8 | Solar | 27A5 | 2022-03-11 | 2022-03-17 | 5 |  | 5 |  |  | 0 | [22 empty] | 2022-03-28 | [12 empty] | 2022-09-19 | Online | [8 empty] | 27A ORCHARD
WMECO | Agawam | ESMAEX-00944 | 01001 | 149.1 | Solar | 30A3 | 2022-03-18 | 2022-03-28 | 7 |  | 7 |  |  | 0 | [22 empty] | 2022-04-15 | [12 empty] | 2023-09-12 | Online | [8 empty] | SILVER
WMECO | Southwick | ESMAEX-00933 | 01077 | 15.2 | Solar | 29A5 | 2022-03-16 | 2022-04-12 | 20 |  | 20 |  |  | 0 | [22 empty] | 2022-05-26 | [12 empty] | 2023-01-05 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Pittsfield | ESMAEX-00941 | 01201 | 10 | Solar | 30B7 | 2022-03-17 | 2022-04-07 | 16 |  | 16 |  |  | 0 | [22 empty] | 2022-04-21 | [12 empty] | 2022-08-05 | Online | [8 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-00957 | 01095 | 240 | Solar | 20A35 | 2022-05-10 | 2022-06-09 | 23 |  | 23 |  |  | 0 | [22 empty] | 2022-07-11 | [13 empty] | Technical Review | [8 empty] | 20A BRECKWOOD
WMECO | Southwick | ESMAEX-00958 | 01077 | 240 | Solar | 29A5 | 2022-05-10 | 2022-06-09 | 23 |  | 23 |  |  | 0 | [22 empty] | 2023-06-20 | [12 empty] | 2024-12-30 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Montague | ESMAEX-00988 | 01376 | 11000 | Battery | 21C6 | 2023-01-20 | 2023-01-23 | 2 |  | 2 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Gill-Montague |  | Whatley-Deerfield | 2023 ASO Batch 1 | 4990 | 21C MONTAGUE
WMECO | Granville | ESMAEX-01120 | 01034 | 15.2 | Solar & Battery | 29A5 | 2022-04-27 | 2022-05-09 | 9 |  | 9 |  |  | 0 | [22 empty] | 2022-05-10 | [12 empty] | 2022-11-14 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Dalton | ESMAEX-01075 | 01226 | 20 | Solar | 18C1 | 2022-04-12 | 2022-04-26 | 11 |  | 11 |  |  | 0 | [22 empty] | 2022-05-26 | [12 empty] | 2022-08-08 | Online |  |  |  | Dalton-Hinsdale |  |  |  |  | 18C BERKSHIRE
WMECO | Northfield | ESMAEX-01087 | 01360 | 10 | Battery | 21B8 | 2022-04-16 | 2022-05-16 | 21 |  | 21 |  |  | 0 | [22 empty] | 2022-05-16 | [12 empty] | 2022-11-23 | Online |  |  |  | Gill-Montague |  |  |  |  | 21B FRENCH KING
WMECO | Huntington | ESMAEX-01102 | 01050 | 4999 | Solar | 19J5 | 2022-05-12 | 2022-05-26 | 11 |  | 11 |  |  | 0 | [36 empty] | Compliances Documents |  |  |  | Blandford |  |  | 2023 ASO Batch 1 |  | 19J BLANDFORD
WMECO | Lanesborough | ESMAEX-01110 | 01237 | 3.54 | Solar & Battery | 15E1 | 2022-04-25 | 2022-05-04 | 8 |  | 8 |  |  | 0 | [22 empty] | 2022-05-26 | [12 empty] | 2022-09-14 | Online
WMECO | Ludlow | ESMAEX-01134 | 10709 | 490 | Solar | 27A5 | 2022-06-14 | 2022-06-16 | 3 |  | 3 |  |  | 0 | [22 empty] | 2026-02-12 | [13 empty] | ISA Agreement | [8 empty] | 27A ORCHARD
WMECO | Westhampton | ESMAEX-01141 | 01027 | 3.8 | Solar & Battery | 15A3 | 2022-05-03 | 2022-05-18 | 12 |  | 12 |  |  | 0 | [22 empty] | 2022-05-25 | [12 empty] | 2024-09-24 | Online | [8 empty] | 15A GUNN
WMECO | West Springfield | ESMAEX-01146 | 01089 | 3.8 | Solar & Battery | 21N4 | 2022-05-04 | 2022-05-18 | 11 |  | 11 |  |  | 0 | [22 empty] | 2022-05-24 | [12 empty] | 2023-03-09 | Online | [8 empty] | 21N PIPER
WMECO | Springfield | ESMAEX-01148 | 01104 | 400 | Solar & Battery | 5J9 | 2022-06-14 | 2022-06-30 | 13 |  | 13 |  |  | 0 | [22 empty] | 2023-07-14 | [13 empty] | Compliances Documents | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Greenfield | ESMAEX-01159 | 01301 | 996 | Solar & Battery | 22B7 | 2022-10-10 | 2022-10-21 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-01-28 | [13 empty] | Technical Review | [7 empty] | 996 | 22B CUMBERLAND
WMECO | Agawam | ESMAEX-01547 | 01001 | 117.3 | Solar | 30A2 | 2022-09-06 | 2022-09-13 | 6 |  | 6 |  |  | 0 | [22 empty] | 2022-09-13 | [12 empty] | 2023-10-06 | Online | [8 empty] | 30A SILVER
WMECO | Longmeadow | ESMAEX-01165 | 01106 | 10 | Solar & Battery | 22H17 | 2022-05-10 | 2022-05-18 | 7 |  | 7 |  |  | 0 | [22 empty] | 2022-05-20 | [12 empty] | 2022-08-22 | Online | [8 empty] | 22H FRANCONIA
WMECO | Plainfield | ESMAEX-01166 | 01070 | 4980 | Solar & Battery | 18K3 | 2023-03-24 | 2023-05-05 | 31 |  | 31 |  |  | 0 | [22 empty] | 2025-07-30 |  |  |  | Complex | [9 empty] | Compliances Documents | [7 empty] | 4980 | 18K PLAINFIELD
WMECO | Westhampton | ESMAEX-01182 | 01027 | 15.2 | Solar & Battery | 15A3 | 2022-05-16 | 2022-06-09 | 19 |  | 19 |  |  | 0 | [22 empty] | 2022-06-26 | [12 empty] | 2022-11-22 | Online | [8 empty] | 15A GUNN
WMECO | Springfield | ESMAEX-01230 | 01109 | 791.5 | Solar & Battery | 21S4 | 2022-07-28 | 2022-08-04 | 6 |  | 6 |  |  | 0 | [22 empty] | 2024-11-20 | [13 empty] | Compliances Documents | [8 empty] | 21S CLINTON
WMECO | Bernardston | ESMAEX-01240 | 01337 | 15.2 | Solar | 21C5 | 2022-06-01 | 2022-06-16 | 12 |  | 12 |  |  | 0 | [22 empty] | 2022-07-07 | [12 empty] | 2025-04-07 | Online |  |  |  | Gill-Montague |  |  |  |  | 21C MONTAGUE
WMECO | West Springfield | ESMAEX-01249 | 01089 | 10 | Battery | 21N4 | 2022-06-02 | 2022-06-09 | 6 |  | 6 |  |  | 0 | [22 empty] | 2022-07-11 | [12 empty] | 2023-07-05 | Online | [8 empty] | 21N PIPER
WMECO | Springfield | ESMAEX-01251 | 01103 | 990 | Solar & Battery | 5J13 | 2023-08-02 | 2023-08-11 | 8 |  | 8 |  |  | 0 | [36 empty] | Supplemental Designer | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Springfield | ESMAEX-01257 | 01129 | 6 | Solar | 20A14 | 2022-06-06 | 2022-06-16 | 9 |  | 9 |  |  | 0 | [22 empty] | 2022-06-17 | [12 empty] | 2022-09-19 | Online | [7 empty] | 6 | 20A BRECKWOOD
WMECO | Amherst | ESMAEX-01410 | 01002 | 50 | Solar | 17K5 | 2022-07-25 | 2022-08-04 | 9 |  | 9 |  |  | 0 | [22 empty] | 2022-09-14 | [12 empty] | 2024-04-04 | Online | [8 empty] | 17K AMHERST
WMECO | Easthampton | ESMAEX-01308 | 01027 | 10 | Solar | 15A1 | 2022-06-17 | 2022-06-30 | 10 |  | 10 |  |  | 0 | [22 empty] | 2022-07-26 | [12 empty] | 2022-10-12 | Online | [7 empty] | 10 | 15A GUNN
WMECO | Feeding Hills | ESMAEX-01317 | 01030 | 15.2 | Solar | 30A6 | 2022-06-22 | 2022-06-30 | 7 |  | 7 |  |  | 0 | [22 empty] | 2022-11-09 | [12 empty] | 2023-04-13 | Online | [7 empty] | 16 | 30A SILVER
WMECO | Easthampton | ESMAEX-01326 | 01027 | 17.6 | Battery | 15A3 | 2022-06-27 | 2022-07-01 | 5 |  | 5 |  |  | 0 | [22 empty] | 2022-07-26 | [12 empty] | 2023-10-02 | Online | [8 empty] | 15A GUNN
WMECO | Whately | ESMAEX-01352 | 01093 | 10 | Battery | 18G8 | 2022-07-07 | 2022-07-29 | 17 |  | 17 |  |  | 0 | [22 empty] | 2022-08-23 | [12 empty] | 2023-02-02 | Online | [8 empty] | 18G PODICK
WMECO | Greenfield | ESMAEX-01376 | 01301 | 15.2 | Solar | 22B7 | 2022-07-13 | 2022-08-04 | 17 |  | 17 |  |  | 0 | [22 empty] | 2022-08-23 | [12 empty] | 2022-11-22 | Online | [8 empty] | 22B CUMBERLAND
WMECO | Lanesborough | ESMAEX-01480 | 01224 | 17.6 | Solar & Battery | 19A5 | 2022-08-17 | 2022-09-07 | 16 |  | 16 |  |  | 0 | [22 empty] | 2022-09-28 | [12 empty] | 2023-08-07 | Online | [8 empty] | 19A DOREEN
WMECO | Southampton | ESMAEX-01350 | 01073 | 17.68 | Solar & Battery | 15A1 | 2022-07-06 | 2022-08-04 | 22 |  | 22 |  |  | 0 | [22 empty] | 2022-08-23 | [12 empty] | 2023-01-05 | Online | [7 empty] | 7.68 | 15A GUNN
WMECO | Springfield | ESMAEX-01356 | 01107 | 2000 | Battery | 21S10 | 2022-10-18 | 2022-12-05 | 35 |  | 35 |  |  | 0 | [22 empty] | 2024-01-26 | [12 empty] | 2025-01-08 | Online | [6 empty] | 2023 ASO Batch 1 | 0 | 21S CLINTON
WMECO | Springfield | ESMAEX-01384 | 01109 | 1833.3 | Solar & Battery | 20A33 | 2023-01-13 | 2023-02-02 | 15 |  | 15 |  |  | 0 | [22 empty] | 2026-02-17 | [13 empty] | ISA Agreement | [6 empty] | 2023 ASO Batch 1 |  | 20A BRECKWOOD
WMECO | Longmeadow | ESMAEX-01501 | 01106 | 15.2 | Solar & Battery | 22H11 | 2022-08-23 | 2022-09-23 | 24 |  | 24 |  |  | 0 | [22 empty] | 2022-10-03 | [12 empty] | 2023-06-12 | Online | [8 empty] | 22H FRANCONIA
WMECO | Cheshire | ESMAEX-01421 | 01225 | 3800 | Solar & Battery | 19A5 | 2022-08-15 | 2022-09-07 | 18 |  | 18 |  |  | 0 | [22 empty] | 2024-12-13 | [13 empty] | Compliances Documents | [6 empty] | 2023 ASO Batch 1 | 3800 | 19A DOREEN
WMECO | Southwick | ESMAEX-01444 | 01077 | 15.2 | Solar & Battery |  | 2022-08-08 | 2022-08-24 | 13 |  | 13 |  |  | 0 | [22 empty] | 2022-08-24 | [12 empty] | 2023-01-31 | Online
WMECO | Granville | ESMAEX-01439 | 01034 | 3000 | Solar & Battery | 29A5 | 2022-09-07 | 2022-09-13 | 5 |  | 5 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Southwick |  |  | 2023 ASO Batch 1 | 3000 | 29A SOUTHWICK
WMECO | Amherst | ESMAEX-01445 | 01002 | 69.2 | Solar | 17K4 | 2022-08-08 | 2022-08-16 | 7 |  | 7 |  |  | 0 | [22 empty] | 2022-09-09 | [12 empty] | 2024-02-14 | Online | [8 empty] | 17K AMHERST
WMECO | Ludlow | ESMAEX-01447 | 01056 | 20 | Solar |  | 2022-08-08 | 2022-12-16 | 95 |  | 95 |  |  | 0 | [22 empty] | 2023-01-30 | [12 empty] | 2024-05-01 | Online
WMECO | Springfield | ESMAEX-01448 | 01109 | 1033.1 | Solar & Battery | 20A14 | 2023-01-17 | 2023-02-02 | 13 |  | 13 |  |  | 0 | [22 empty] | 2026-02-19 | [13 empty] | ISA Agreement | [6 empty] | 2023 ASO Batch 1 |  | 20A BRECKWOOD
WMECO | Savoy | ESMAEX-02010 | 01256 | 15.2 | Solar & Battery | 18K4 | 2023-01-12 | 2023-01-23 | 8 |  | 8 |  |  | 0 | [22 empty] | 2023-03-03 | [12 empty] | 2023-06-12 | Online |  |  |  | Dalton-Hinsdale |  |  |  |  | 18C BERKSHIRE
WMECO | Blandford | ESMAEX-01479 | 01008 | 4998 | Solar & Battery | 19J5 | 2022-12-20 | 2022-12-29 | 8 |  | 8 |  |  | 0 | [36 empty] | Compliances Documents |  |  |  | Blandford |  |  | 2023 ASO Batch 1 | 4998 | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-01489 | 01201 | 240 | Solar |  | 2023-01-12 | 2022-09-07 | -92 |  |  |  |  | 0 | [22 empty] | 2022-10-05 | [12 empty] | 2024-03-01 | Online
WMECO | Springfield | ESMAEX-01502 | 01108 | 3 | Solar & Battery | 22H15 | 2022-08-23 | 2022-09-07 | 12 |  | 12 |  |  | 0 | [22 empty] | 2022-10-06 | [12 empty] | 2023-04-12 | Online | [7 empty] | 14 | 22H FRANCONIA
WMECO | Otis | ESMAEX-01512 | 01253 | 20 | Solar | 19J4 | 2022-08-25 | 2022-09-07 | 10 |  | 10 |  |  | 0 | [22 empty] | 2022-10-12 | [12 empty] | 2026-01-21 | Online |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Shelburne Falls | ESMAEX-01514 | 01370 | 20 | Solar | 22B5 | 2022-08-25 | 2022-09-15 | 16 |  | 16 |  |  | 0 | [22 empty] | 2022-10-25 | [12 empty] | 2024-11-22 | Online | [8 empty] | 22B CUMBERLAND
WMECO | Hadley | ESMAEX-01515 | 01035 | 15.6 | Solar & Battery | 18G5 | 2022-08-26 | 2022-09-07 | 9 |  | 9 |  |  | 0 | [22 empty] | 2022-10-04 | [12 empty] | 2023-02-08 | Online | [8 empty] | 18G PODICK
WMECO | Amherst | ESMAEX-01522 | 01002 | 4990 | Battery | 18G6 | 2022-08-29 | 2022-09-14 | 13 |  | 13 |  |  | 0 | [36 empty] | Impact Study | [7 empty] | 4990 | 18G PODICK
WMECO | Agawam | ESMAEX-01527 | 01001 | 960 | Solar | 30A3 | 2022-09-19 | 2022-09-23 | 5 |  | 5 |  |  | 0 | [22 empty] | 2023-02-08 | [12 empty] | 2025-02-14 | Online | [8 empty] | 30A SILVER
WMECO | Hatfield | ESMAEX-01533 | 01038 | 20 | Solar | 18G6 | 2022-09-01 | 2022-09-13 | 9 |  | 9 |  |  | 0 | [22 empty] | 2022-10-04 | [12 empty] | 2022-12-21 | Online | [8 empty] | 18G PODICK
WMECO | Sunderland | ESMAEX-01539 | 01375 | 10 | Solar & Battery | 18G8 | 2022-09-02 | 2022-09-21 | 14 |  | 14 |  |  | 0 | [22 empty] | 2022-10-05 | [12 empty] | 2023-03-06 | Online | [8 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-01563 | 01109 | 60 | Solar | 20A33 | 2022-09-11 | 2022-09-23 | 10 |  | 10 |  |  | 0 | [22 empty] | 2023-01-22 | [13 empty] | Compliances Documents | [8 empty] | 20A BRECKWOOD
WMECO | Southwick | ESMAEX-01581 | 01077 | 4999 | Battery | 29A3 | 2023-03-20 | 2023-04-19 | 23 |  | 23 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Southwick | ESMAEX-01582 | 01077 | 6700 | Solar & Battery | 29A3 | 2023-03-20 | 2023-03-22 | 3 |  | 3 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Amherst | ESMAEX-01586 | 01002 | 3830 | Solar & Battery | 17K8 | 2022-09-14 | 2022-09-15 | 2 |  | 2 |  |  | 0 | [22 empty] | 2023-08-11 | [12 empty] | 2026-01-29 | Online | [7 empty] | 3830 | 17K AMHERST
WMECO | Lanesborough | ESMAEX-01590 | 01237 | 16.4 | Solar | 15E1 | 2022-09-14 | 2022-09-23 | 8 |  | 8 |  |  | 0 | [22 empty] | 2022-09-27 | [12 empty] | 2023-07-06 | Online | [8 empty] | PARTRIDGE
WMECO | Buckland | ESMAEX-01594 | 01338 | 250 | Solar | 29R1 | 2022-10-07 | 2022-10-13 | 5 |  | 5 |  |  | 0 | [22 empty] | 2022-11-02 | [12 empty] | 2024-04-02 | Online | [8 empty] | 29R SHELBURNE
WMECO | Worthington | ESMAEX-01622 | 01098 | 3000 | Solar & Battery | 18K3 | 2023-05-10 | 2023-05-24 | 11 |  | 11 |  |  | 0 | [22 empty] | 2025-07-30 | [13 empty] | Compliances Documents | [7 empty] | 3000 | 18K PLAINFIELD
WMECO | Blandford | ESMAEX-01635 | 01008 | 2000 | Solar | 19J2 | 2022-11-29 | 2022-12-05 | 5 |  | 5 |  |  | 0 | [36 empty] | Compliances Documents |  |  |  | Blandford |  |  | 2023 ASO Batch 1 | 2000 | 19J BLANDFORD
WMECO | Cummington | ESMAEX-01631 | 01026 | 5 | Solar | 18C1 | 2022-09-26 | 2022-10-05 | 8 |  | 8 |  |  | 0 | [22 empty] | 2022-11-02 | [12 empty] | 2023-02-24 | Online |  |  |  | Plainfield |  |  |  |  | 18C BERKSHIRE
WMECO | Hatfield | ESMAEX-01733 | 01038 | 7.6 | Solar & Battery | 18G5 | 2022-10-27 | 2023-01-11 | 55 |  | 55 |  |  | 0 | [22 empty] | 2023-01-18 | [12 empty] | 2023-06-15 | Online | [8 empty] | 18G PODICK
WMECO | Longmeadow | ESMAEX-01682 | 01106 | 10.752 | Solar & Battery | 22H11 | 2022-10-13 | 2022-11-21 | 28 |  | 28 |  |  | 0 | [22 empty] | 2022-12-15 | [12 empty] | 2023-04-27 | Online | [8 empty] | 22H FRANCONIA
WMECO | Richmond | ESMAEX-01647 | 01254 | 22.8 | Solar & Battery | 30B7 | 2022-09-30 | 2022-12-01 | 45 |  | 45 |  |  | 0 | [22 empty] | 2022-12-07 | [12 empty] | 2024-10-11 | Online | [8 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-01645 | 01109 | 12.6 | Solar & Battery | 5J17 | 2022-09-29 | 2022-10-21 | 17 |  | 17 |  |  | 0 | [22 empty] | 2022-10-21 | [12 empty] | 2023-12-21 | Online | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Amherst | ESMAEX-01862 | 01002 | 60 | Solar | 17K6 | 2022-11-29 | 2022-12-05 | 5 |  | 5 |  |  | 0 | [22 empty] | 2023-03-07 | [12 empty] | 2024-08-05 | Online | [8 empty] | 17K AMHERST
WMECO | Becket | ESMAEX-01852 | 01223 | 2490 | Solar | 19J6 | 2022-11-28 | 2022-12-05 | 6 |  | 6 |  |  | 0 | [26 empty] | Complex | [9 empty] | Compliances Documents |  |  |  | Blandford |  |  | 2023 ASO Batch 1 |  | 19J BLANDFORD
WMECO | Ashfield | ESMAEX-01748 | 01330 | 10 | Solar | 38A1 | 2022-11-01 | 2022-11-16 | 12 |  | 12 |  |  | 0 | [22 empty] | 2023-01-03 | [12 empty] | 2023-04-25 | Online | [8 empty] | 38A ASHFIELD
WMECO | Whately | ESMAEX-01677 | 01093 | 400 | Solar | 18G8 | 2023-02-16 | 2023-02-24 | 7 |  | 7 |  |  | 0 | [22 empty] | 2025-02-10 | [13 empty] | Compliances Documents | [8 empty] | 18G PODICK
WMECO | Southwick | ESMAEX-01715 | 01077 | 10 | Solar & Battery | 29A5 | 2022-10-25 | 2022-10-28 | 4 |  | 4 |  |  | 0 | [22 empty] | 2022-10-31 | [12 empty] | 2023-04-06 | Online |  |  |  | Southwick |  |  |  | 7 | 29A SOUTHWICK
WMECO | Ludlow | ESMAEX-01813 | 01056 | 17.6 | Solar & Battery | 19S1 | 2022-11-15 | 2023-01-23 | 50 |  | 50 |  |  | 0 | [22 empty] | 2023-01-31 | [12 empty] | 2023-05-30 | Online | [7 empty] | 17.6 | 19S LUDLOW
WMECO | West Springfield | ESMAEX-01719 | 01089 | 225 | Solar | 21N5 | 2022-10-25 | 2022-11-07 | 10 |  | 10 |  |  | 0 | [22 empty] | 2022-11-30 | [12 empty] | 2024-10-24 | Online | [8 empty] | 21N PIPER
WMECO | Granville | ESMAEX-01695 | 01034 | 17.1 | Solar | 29A5 | 2022-10-19 | 2022-10-28 | 8 |  | 8 |  |  | 0 | [22 empty] | 2023-01-23 | [12 empty] | 2023-04-20 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Lanesborough | ESMAEX-01708 | 01237 | 3800 | Solar & Battery | 30B5 | 2023-01-10 | 2024-07-29 | 405 |  | 405 |  |  | 0 | [22 empty] | 2026-03-05 | [13 empty] | ISA Agreement | [7 empty] | 2800 | 30B OSWALD
WMECO | Conway | ESMAEX-01702 | 01341 | 12.6 | Solar | 38A1 | 2022-10-21 | 2022-11-07 | 12 |  | 12 |  |  | 0 | [22 empty] | 2022-12-12 | [12 empty] | 2023-02-09 | Online | [8 empty] | 38A ASHFIELD
WMECO | Blandford | ESMAEX-01704 | 01008 | 4998 | Solar & Battery | 19J2 | 2022-12-20 | 2022-12-29 | 8 |  | 8 |  |  | 0 | [36 empty] | Compliances Documents |  |  |  | Blandford |  |  | 2023 ASO Batch 1 | 4998 | 19J BLANDFORD
WMECO | Easthampton | ESMAEX-01713 | 01027 | 15.2 | Solar & Battery | 15A2 | 2022-10-25 | 2022-11-07 | 10 |  | 10 |  |  | 0 | [22 empty] | 2022-12-12 | [12 empty] | 2023-04-13 | Online | [8 empty] | 15A GUNN
WMECO | Amherst | ESMAEX-01764 | 01002 | 10 | Battery | 17K8 | 2022-11-03 | 2022-12-07 | 25 |  | 25 |  |  | 0 | [22 empty] | 2023-01-18 | [12 empty] | 2024-02-07 | Online | [8 empty] | 17K AMHERST
WMECO | Southwick | ESMAEX-01830 | 01077 | 15.93 | Solar | 29A1 | 2022-11-17 | 2022-12-05 | 13 |  | 13 |  |  | 0 | [22 empty] | 2022-12-05 | [12 empty] | 2023-08-29 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Southwick | ESMAEX-01769 | 01077 | 10 | Solar & Battery | 29A5 | 2022-11-04 | 2022-11-16 | 9 |  | 9 |  |  | 0 | [22 empty] | 2022-11-16 | [12 empty] | 2023-04-06 | Online |  |  |  | Southwick |  |  |  | 7 | 29A SOUTHWICK
WMECO | Hadley | ESMAEX-01754 | 01035 | 10 | Solar | 18G4 | 2022-11-02 | 2022-11-16 | 11 |  | 11 |  |  | 0 | [22 empty] | 2022-12-14 | [12 empty] | 2023-06-06 | Online | [8 empty] | 18G PODICK
WMECO | Washington | ESMAEX-01766 | 01223 | 5 | Solar & Battery | 19J6 | 2022-11-04 | 2022-11-16 | 9 |  | 9 |  |  | 0 | [22 empty] | 2022-11-18 | [12 empty] | 2023-10-12 | Online
WMECO | Bernardston | ESMAEX-01755 | 01337 | 4700 | Solar & Battery | 21C1 | 2023-09-21 | 2023-09-29 | 7 |  | 7 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Gill-Montague |  | Whatley-Deerfield |  | 4700 | 21C MONTAGUE
WMECO | Feeding Hills | ESMAEX-01802 | 01030 | 10 | Solar | 30A1 | 2022-11-11 | 2022-11-16 | 4 |  | 4 |  |  | 0 | [22 empty] | 2022-11-21 | [12 empty] | 2023-04-07 | Online | [7 empty] | 7 | 30A SILVER
WMECO | Ludlow | ESMAEX-01826 | 01056 | 14.7 | Solar | 27A5 | 2022-11-17 | 2022-12-21 | 25 |  | 25 |  |  | 0 | [22 empty] | 2022-12-23 | [12 empty] | 2023-04-06 | Online | [8 empty] | 27A ORCHARD
WMECO | Conway | ESMAEX-01828 | 01341 | 3984 | Solar & Battery | 22B1 | 2023-01-25 | 2023-02-01 | 6 |  | 6 |  |  | 0 | [26 empty] | Complex | [9 empty] | Technical Review | [7 empty] | 4200 | 22B CUMBERLAND
WMECO | Whately | ESMAEX-01872 | 01093 | 20 | Solar | 18G6 | 2022-11-30 | 2022-12-05 | 4 |  | 4 |  |  | 0 | [22 empty] | 2023-01-25 | [12 empty] | 2023-05-12 | Online | [8 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-01869 | 01118 | 15.2 | Solar & Battery | 20A32 | 2022-11-29 | 2022-12-14 | 12 |  | 12 |  |  | 0 | [22 empty] | 2023-01-03 | [12 empty] | 2023-12-04 | Online | [8 empty] | 20A BRECKWOOD
WMECO | Whately | ESMAEX-02067 | 01093 | 5 | Battery | 18G8 | 2023-01-25 | 2023-02-21 | 20 |  | 20 |  |  | 0 | [22 empty] | 2023-03-09 | [12 empty] | 2024-06-17 | Online | [8 empty] | 18G PODICK
WMECO | Otis | ESMAEX-02145 | 01253 | 15.2 | Solar & Battery | 19J4 | 2023-02-09 | 2023-02-24 | 12 |  | 12 |  |  | 0 | [22 empty] | 2023-03-28 | [12 empty] | 2023-10-23 | Online |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Ashfield | ESMAEX-02059 | 01330 | 20 | Solar | 38A1 | 2023-01-23 | 2023-02-01 | 8 |  | 8 |  |  | 0 | [22 empty] | 2023-03-20 | [12 empty] | 2023-06-12 | Online | [8 empty] | 38A ASHFIELD
WMECO | Whately | ESMAEX-01991 | 01093 | 15.2 | Solar | 18G6 | 2023-01-10 | 2023-01-23 | 10 |  | 10 |  |  | 0 | [22 empty] | 2023-03-15 | [12 empty] | 2024-02-08 | Online | [8 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-01968 | 01056 | 240 | Solar |  | 2023-01-05 | 2023-02-01 | 20 |  | 20 |  |  | 0 | [22 empty] | 2023-05-03 | [13 empty] | Compliances Documents
WMECO | Longmeadow | ESMAEX-02008 | 01106 | 20 | Solar | 22H13 | 2023-01-12 | 2023-02-01 | 15 |  | 15 |  |  | 0 | [22 empty] | 2023-02-15 | [12 empty] | 2023-05-23 | Online | [8 empty] | 22H FRANCONIA
WMECO | Feeding Hills | ESMAEX-02090 | 01030 | 10.62 | Solar & Battery | 30A1 | 2023-01-30 | 2023-03-31 | 45 |  | 45 |  |  | 0 | [22 empty] | 2023-04-03 | [12 empty] | 2023-08-04 | Online | [8 empty] | 30A SILVER
WMECO | Amherst | ESMAEX-02073 | 01002 | 15.2 | Solar | 18G7 | 2023-01-25 | 2023-02-08 | 11 |  | 11 |  |  | 0 | [22 empty] | 2023-03-09 | [12 empty] | 2023-09-05 | Online | [8 empty] | 18G PODICK
WMECO | Feeding Hills | ESMAEX-02040 | 01030 | 15.2 | Solar | 16C17 | 2023-01-19 | 2023-02-01 | 10 |  | 10 |  |  | 0 | [22 empty] | 2023-02-28 | [12 empty] | 2023-08-04 | Online | [7 empty] | 17.4 | 16C AGAWAM
WMECO | Deerfield | ESMAEX-02052 | 01342 | 480 | Solar | 22B3 | 2023-02-17 | 2023-03-03 | 11 |  | 11 |  |  | 0 | [22 empty] | 2026-01-03 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 22B CUMBERLAND
WMECO | Longmeadow | ESMAEX-02128 | 01106 | 10 | Battery | 22H13 | 2023-02-06 | 2023-02-24 | 15 |  | 15 |  |  | 0 | [22 empty] | 2023-03-01 | [12 empty] | 2024-01-25 | Online | [8 empty] | 22H FRANCONIA
WMECO | Agawam | ESMAEX-02138 | 01030 | 15.2 | Solar & Battery | 16C17 | 2023-02-07 | 2023-02-17 | 9 |  | 9 |  |  | 0 | [22 empty] | 2023-02-17 | [12 empty] | 2023-09-07 | Online | [8 empty] | 16C AGAWAM
WMECO | Feeding Hills | ESMAEX-02074 | 01030 | 15.2 | Solar | 30A1 | 2023-01-26 | 2023-02-08 | 10 |  | 10 |  |  | 0 | [22 empty] | 2023-02-08 | [12 empty] | 2023-05-11 | Online | [8 empty] | 30A SILVER
WMECO | Longmeadow | ESMAEX-02093 | 01106 | 20.56 | Solar & Battery | 22H13 | 2023-01-31 | 2023-02-10 | 9 |  | 9 |  |  | 0 | [22 empty] | 2023-02-15 | [12 empty] | 2023-07-07 | Online | [8 empty] | 22H FRANCONIA
WMECO | Pelham | ESMAEX-02103 | 01002 | 13.26 | Solar & Battery | 17K2 | 2023-02-02 | 2023-03-31 | 42 |  | 42 |  |  | 0 | [22 empty] | 2023-04-13 | [12 empty] | 2023-08-07 | Online | [8 empty] | 17K AMHERST
WMECO | Colrain | ESMAEX-02141 | 01340 | 18.24 | Solar & Battery | 29R2 | 2023-02-08 | 2023-02-14 | 5 |  | 5 |  |  | 0 | [22 empty] | 2023-02-27 | [12 empty] | 2023-12-08 | Online | [8 empty] | 29R SHELBURNE
WMECO | Agawam | ESMAEX-02252 | 01001 | 15.2 | Solar | 30A5 | 2023-03-09 | 2023-03-22 | 10 |  | 10 |  |  | 0 | [22 empty] | 2023-03-23 | [12 empty] | 2023-08-14 | Online | [8 empty] | 30A SILVER
WMECO | Springfield | ESMAEX-02230 | 01108 | 15.2 | Solar | 22H15 | 2023-03-03 | 2023-03-08 | 4 |  | 4 |  |  | 0 | [22 empty] | 2023-03-24 | [12 empty] | 2024-05-23 | Online | [8 empty] | 22H FRANCONIA
WMECO | Longmeadow | ESMAEX-02189 | 01106 | 15.2 | Solar & Battery | 22H13 | 2023-02-22 | 2023-03-03 | 8 |  | 8 |  |  | 0 | [22 empty] | 2023-03-28 | [12 empty] | 2023-11-17 | Online | [8 empty] | 22H FRANCONIA
WMECO | Southampton | ESMAEX-02171 | 01073 | 4980 | Solar & Battery | 15A1 | 2023-03-27 | 2023-06-02 | 50 |  | 50 |  |  | 0 | [36 empty] | Transmission | [7 empty] | 4980 | 15A GUNN
WMECO | Lanesborough | ESMAEX-02210 | 01237 | 7.6 | Solar & Battery | 15E1 | 2023-02-28 | 2023-03-03 | 4 |  | 4 |  |  | 0 | [22 empty] | 2023-03-28 | [12 empty] | 2023-12-21 | Online | [7 empty] | 14
WMECO | West Hatfield | ESMAEX-02405 | 01088 | 125 | Solar | 18G5 | 2023-04-21 | 2023-04-28 | 6 |  | 6 |  |  | 0 | [22 empty] | 2023-05-31 | [12 empty] | 2024-08-23 | Online | [8 empty] | 18G PODICK
WMECO | Blandford | ESMAEX-02238 | 01008 | 17.4 | Solar | 29A5 | 2023-03-06 | 2023-03-17 | 10 |  | 10 |  |  | 0 | [22 empty] | 2023-03-17 | [12 empty] | 2023-05-23 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Lee | ESMAEX-02279 | 01238 | 20.736 | Solar | 16B5 | 2023-03-17 | 2023-03-31 | 11 |  | 11 |  |  | 0 | [22 empty] | 2023-05-02 | [12 empty] | 2023-09-08 | Online | [8 empty] | 16B PLEASANT
WMECO | Longmeadow | ESMAEX-02289 | 01106 | 15.2 | Solar & Battery | 22H12 | 2023-03-21 | 2023-03-31 | 9 |  | 9 |  |  | 0 | [22 empty] | 2023-04-03 | [12 empty] | 2023-09-08 | Online | [8 empty] | 22H FRANCONIA
WMECO | Pittsfield | ESMAEX-02258 | 01201 | 12.98 | Solar | 19A7 | 2023-03-10 | 2023-03-22 | 9 |  | 9 |  |  | 0 | [22 empty] | 2023-03-28 | [12 empty] | 2023-07-20 | Online | [8 empty] | 19A DOREEN
WMECO | Amherst | ESMAEX-02259 | 01002 | 84.672 | Solar |  | 2023-03-10 | 2024-03-27 | 274 |  | 274 |  |  | 0 | [22 empty] | 2024-08-07 | [12 empty] | 2025-05-09 | Online
WMECO | Springfield | ESMAEX-02264 | 01108 | 8.26 | Solar & Battery | 21S12 | 2023-03-14 | 2023-03-20 | 5 |  | 5 |  |  | 0 | [22 empty] | 2023-03-21 | [12 empty] | 2023-05-03 | Online | [8 empty] | 21S CLINTON
WMECO | Hadley | ESMAEX-02288 | 01035 | 17.6 | Solar | 18G4 | 2023-03-20 | 2023-03-31 | 10 |  | 10 |  |  | 0 | [22 empty] | 2023-06-12 | [12 empty] | 2023-08-10 | Online | [8 empty] | 18G PODICK
WMECO | Richmond | ESMAEX-02312 | 01254 | 15.2 | Solar & Battery | 30B2 | 2023-03-27 | 2023-04-26 | 23 |  | 23 |  |  | 0 | [22 empty] | 2023-05-02 | [12 empty] | 2023-09-26 | Online | [8 empty] | 30B OSWALD
WMECO | Bernardston | ESMAEX-02295 | 01337 | 15.2 | Solar |  | 2023-03-22 | 2023-05-17 | 41 |  | 41 |  |  | 0 | [22 empty] | 2023-06-27 | [12 empty] | 2023-12-21 | Online
WMECO | Cummington | ESMAEX-02311 | 01026 | 10 | Solar & Battery | 18C1 | 2023-03-27 | 2023-05-01 | 26 |  | 26 |  |  | 0 | [22 empty] | 2023-06-06 | [12 empty] | 2024-04-04 | Online |  |  |  | Plainfield |  |  |  |  | 18C BERKSHIRE
WMECO | Southwick | ESMAEX-02314 | 01077 | 2000 | Solar | 29A5 | 2023-07-27 | 2023-08-02 | 5 |  | 5 |  |  | 0 | [26 empty] | Complex | [9 empty] | Impact Study |  |  |  | Southwick |  |  |  | 2000 | 29A SOUTHWICK
WMECO | Becket | ESMAEX-02317 | 01223 | 9.3 | Solar | 19J6 | 2023-03-28 | 2023-04-07 | 9 |  | 9 |  |  | 0 | [22 empty] | 2023-05-02 | [12 empty] | 2023-08-03 | Online
WMECO | Springfield | ESMAEX-02322 | 01109 | 999 | Solar & Battery | 20A21 | 2023-05-09 | 2023-06-09 | 24 |  | 24 |  |  | 0 | [22 empty] | 2023-08-18 | [13 empty] | ISA Agreement | [8 empty] | 20A BRECKWOOD
WMECO | Amherst | ESMAEX-02326 | 01002 | 10 | Solar | 19B16 | 2023-03-30 | 2023-04-12 | 10 |  | 10 |  |  | 0 | [22 empty] | 2023-05-16 | [12 empty] | 2023-09-21 | Online | [8 empty] | 19B MIDWAY
WMECO | Pittsfield | ESMAEX-02362 | 01201 | 60 | Solar | 19A7 | 2023-04-10 | 2023-04-26 | 13 |  | 13 |  |  | 0 | [22 empty] | 2023-05-02 | [12 empty] | 2024-01-18 | Online | [8 empty] | DOREEN
WMECO | Hadley | ESMAEX-02350 | 01035 | 15.2 | Solar | 19B15 | 2023-04-06 | 2023-04-26 | 15 |  | 15 |  |  | 0 | [22 empty] | 2023-05-26 | [12 empty] | 2023-11-09 | Online | [7 empty] | 15.2 | 19B MIDWAY
WMECO | Southampton | ESMAEX-02348 | 01073 | 6 | Solar | 15A1 | 2023-04-05 | 2023-04-26 | 16 |  | 16 |  |  | 0 | [22 empty] | 2023-05-26 | [12 empty] | 2023-06-26 | Online | [7 empty] | 6 | 15A GUNN
WMECO | Southampton | ESMAEX-02396 | 01073 | 6 | Solar | 15A3 | 2023-04-20 | 2023-05-05 | 12 |  | 12 |  |  | 0 | [22 empty] | 2023-05-31 | [12 empty] | 2023-08-31 | Online | [7 empty] | 6 | 15A GUNN
WMECO | Peru | ESMAEX-02361 | 01235 | 10 | Battery |  | 2023-04-10 | 2023-05-17 | 28 |  | 28 |  |  | 0 | [22 empty] | 2023-06-26 | [12 empty] | 2024-02-07 | Online
WMECO | Longmeadow | ESMAEX-02370 | 01106 | 15.2 | Solar & Battery | 22H17 | 2023-04-11 | 2023-04-26 | 12 |  | 12 |  |  | 0 | [22 empty] | 2023-04-28 | [12 empty] | 2023-09-21 | Online | [8 empty] | 22H FRANCONIA
WMECO | Richmond | ESMAEX-02475 | 01254 | 50 | Solar | 30B7 | 2023-05-15 | 2023-05-24 | 8 |  | 8 |  |  | 0 | [22 empty] | 2023-06-27 | [12 empty] | 2025-01-31 | Online | [8 empty] | 30B OSWALD
WMECO | Greenfield | ESMAEX-02459 | 01301 | 25 | Solar | 22B7 | 2023-05-08 | 2023-05-12 | 5 |  | 5 |  |  | 0 | [22 empty] | 2023-08-23 | [12 empty] | 2023-12-27 | Online | [8 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-02394 | 01105 | 100 | Solar | 5J16 | 2023-04-19 | 2023-06-08 | 37 |  | 37 |  |  | 0 | [22 empty] | 2023-06-08 | [12 empty] | 2025-09-29 | Online | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Otis | ESMAEX-02390 | 01253 | 20 | Solar | 19J4 | 2023-04-19 | 2023-05-15 | 19 |  | 19 |  |  | 0 | [22 empty] | 2023-06-26 | [12 empty] | 2023-11-09 | Online |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Southwick | ESMAEX-02540 | 01077 | 16.52 | Solar | 29A5 | 2023-05-30 | 2023-07-07 | 29 |  | 29 |  |  | 0 | [22 empty] | 2023-07-07 | [12 empty] | 2024-05-23 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Southampton | ESMAEX-02541 | 01073 | 15.2 | Solar & Battery | 15A1 | 2023-05-31 | 2023-06-16 | 13 |  | 13 |  |  | 0 | [22 empty] | 2023-07-13 | [12 empty] | 2024-09-03 | Online | [8 empty] | 15A GUNN
WMECO | Worthington | ESMAEX-02438 | 01098 | 2000 | Solar & Battery | 18K3 | 2023-05-26 | 2023-06-02 | 6 |  | 6 |  |  | 0 | [22 empty] | 2025-07-30 | [13 empty] | Compliances Documents | [7 empty] | 2000 | 18K PLAINFIELD
WMECO | Longmeadow | ESMAEX-02482 | 01106 | 21 | Solar | 22H11 | 2023-05-16 | 2023-05-31 | 12 |  | 12 |  |  | 0 | [22 empty] | 2023-05-31 | [12 empty] | 2024-06-12 | Online | [8 empty] | FRANCONIA
WMECO | Amherst | ESMAEX-02471 | 01002 | 7.8 | Solar & Battery | 17K2 | 2023-05-11 | 2023-05-17 | 5 |  | 5 |  |  | 0 | [22 empty] | 2023-06-02 | [12 empty] | 2023-12-21 | Online | [8 empty] | 17K AMHERST
WMECO | Southampton | ESMAEX-02462 | 01073 | 10 | Solar | 15A3 | 2023-05-08 | 2023-05-17 | 8 |  | 8 |  |  | 0 | [22 empty] | 2023-06-02 | [12 empty] | 2023-09-05 | Online | [7 empty] | 10 | 15A GUNN
WMECO | Longmeadow | ESMAEX-02470 | 01106 | 15.2 | Solar & Battery | 22H13 | 2023-05-10 | 2023-05-24 | 11 |  | 11 |  |  | 0 | [22 empty] | 2023-05-25 | [12 empty] | 2023-09-12 | Online | [8 empty] | 22H FRANCONIA
WMECO | Sunderland | ESMAEX-02492 | 01375 | 25 | Solar | 18G8 | 2023-05-18 | 2023-05-24 | 5 |  | 5 |  |  | 0 | [22 empty] | 2023-06-02 | [12 empty] | 2023-08-02 | Online | [8 empty] | 18G PODICK
WMECO | Montague | ESMAEX-02511 | 01376 | 4000 | Battery | 21C5 | 2023-05-23 | 2023-06-06 | 11 |  | 11 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Gill-Montague |  | Whatley-Deerfield |  | 4000 | 21C MONTAGUE
WMECO | Amherst | ESMAEX-02473 | 01002 | 15.2 | Solar & Battery | 19B16 | 2023-05-11 | 2023-07-06 | 41 |  | 41 |  |  | 0 | [22 empty] | 2023-07-13 | [12 empty] | 2023-10-17 | Online | [8 empty] | 19B MIDWAY
WMECO | Feeding Hills | ESMAEX-02493 | 01030 | 15.2 | Solar | 30A6 | 2023-05-18 | 2023-06-02 | 12 |  | 12 |  |  | 0 | [22 empty] | 2023-06-05 | [12 empty] | 2023-08-10 | Online | [8 empty] | 30A SILVER
WMECO | Worthington | ESMAEX-02520 | 01098 | 23.6 | Solar & Battery | 18C2 | 2023-05-25 | 2023-06-09 | 12 |  | 12 |  |  | 0 | [22 empty] | 2023-06-22 | [12 empty] | 2023-11-17 | Online |  |  |  | Plainfield |  |  |  |  | 18C BERKSHIRE
WMECO | Becket | ESMAEX-02484 | 01223 | 15.2 | Solar & Battery | 19J6 | 2023-05-16 | 2023-05-24 | 7 |  | 7 |  |  | 0 | [22 empty] | 2023-06-27 | [12 empty] | 2023-11-09 | Online
WMECO | Deerfield | ESMAEX-02485 | 01342 | 15.2 | Solar & Battery | 22B1 | 2023-05-16 | 2023-06-06 | 16 |  | 16 |  |  | 0 | [22 empty] | 2023-07-06 | [12 empty] | 2023-10-12 | Online | [8 empty] | 22B CUMBERLAND
WMECO | Becket | ESMAEX-02501 | 01223 | 4999 | Solar & Battery | 16B1 | 2023-05-22 | 2023-05-31 | 8 |  | 8 |  |  | 0 | [22 empty] | 2025-08-04 | [13 empty] | Compliances Documents | [7 empty] | 4999 | 16B PLEASANT
WMECO | Southwick | ESMAEX-02529 | 01077 | 15.2 | Solar | 29A1 | 2023-05-26 | 2023-06-19 | 17 |  | 17 |  |  | 0 | [22 empty] | 2023-06-19 | [12 empty] | 2024-04-30 | Online | [8 empty] | 29A SOUTHWICK
WMECO | Springfield | ESMAEX-02508 | 01109 | 14 | Battery | 5J14 | 2023-05-22 | 2023-07-31 | 51 |  | 51 |  |  | 0 | [22 empty] | 2023-08-10 | [12 empty] | 2024-05-15 | Online | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Blandford | ESMAEX-02512 | 01008 | 2656 | Solar & Battery | 19J2 | 2023-07-05 | 2023-07-13 | 7 |  | 7 |  |  | 0 | [26 empty] | Complex | [9 empty] | Compliances Documents |  |  |  | Blandford |  |  |  | 2490 | 19J BLANDFORD
WMECO | Sunderland | ESMAEX-02515 | 01375 | 15.2 | Solar & Battery | 18G3 | 2023-05-24 | 2023-06-09 | 13 |  | 13 |  |  | 0 | [22 empty] | 2023-07-07 | [12 empty] | 2023-10-23 | Online | [8 empty] | 18G PODICK
WMECO | Montague | ESMAEX-02552 | 01376 | 4999 | Battery | 21C2 | 2023-07-20 | 2023-08-03 | 11 |  | 11 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Gill-Montague |  | Whatley-Deerfield |  |  | 21C MONTAGUE
WMECO | Feeding Hills | ESMAEX-02604 | 01030 | 15.2 | Solar | 16C17 | 2023-06-22 | 2023-07-07 | 12 |  | 12 |  |  | 0 | [22 empty] | 2023-07-07 | [12 empty] | 2023-11-17 | Online | [8 empty] | 16C AGAWAM
WMECO | West Hatfield | ESMAEX-02557 | 01088 | 15.2 | Solar | 18G5 | 2023-06-06 | 2023-06-27 | 16 |  | 16 |  |  | 0 | [22 empty] | 2023-07-13 | [12 empty] | 2024-01-05 | Online | [8 empty] | 18G PODICK
WMECO | Russell | ESMAEX-02599 | 01071 | 5 | Battery | 19J2 | 2023-06-21 | 2023-07-07 | 13 |  | 13 |  |  | 0 | [22 empty] | 2023-07-13 | [12 empty] | 2024-02-07 | Online |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Agawam | ESMAEX-02606 | 01001 | 996 | Solar | 30A3 | 2023-08-15 | 2023-08-17 | 3 |  | 3 |  |  | 0 | [36 empty] | Compliances Documents | [8 empty] | 30A SILVER
WMECO | Hinsdale | ESMAEX-02613 | 01235 | 19 | Solar | 18C2 | 2023-06-23 | 2023-07-06 | 10 |  | 10 |  |  | 0 | [22 empty] | 2023-08-02 | [12 empty] | 2024-06-12 | Online |  |  |  | Dalton-Hinsdale |  |  |  |  | 18C BERKSHIRE
WMECO | South Deerfield | ESMAEX-02623 | 01373 | 20 | Solar | 22B3 | 2023-06-27 | 2023-07-06 | 8 |  | 8 |  |  | 0 | [22 empty] | 2023-08-14 | [12 empty] | 2023-12-18 | Online | [8 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-02625 | 01104 | 6 | Solar | 5J15 | 2023-06-27 | 2023-07-06 | 8 |  | 8 |  |  | 0 | [22 empty] | 2023-07-07 | [12 empty] | 2023-09-26 | Online | [7 empty] | 6 | 5J EAST SPRINGFIELD
WMECO | Tolland | ESMAEX-02715 | 01034 | 6 | Solar & Battery | 19J4 | 2023-07-26 | 2023-08-03 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-01-24 | [12 empty] | 2024-09-25 | Online |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Amherst | ESMAEX-02641 | 01002 | 18.048 | Solar | 17K8 | 2023-07-06 | 2023-08-30 | 40 |  | 40 |  |  | 0 | [22 empty] | 2023-10-03 | [12 empty] | 2023-11-13 | Online | [8 empty] | 17K AMHERST
WMECO | Lee | ESMAEX-02695 | 01238 | 110 | Solar |  | 2023-07-20 | 2023-08-01 | 9 |  | 9 |  |  | 0 | [22 empty] | 2023-08-02 | [12 empty] | 2024-06-20 | Permission to Operate
WMECO | Southwick | ESMAEX-02662 | 01077 | 4998 | Solar & Battery | 29A1 | 2023-08-08 | 2023-08-09 | 2 |  | 2 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Middlefield | ESMAEX-02696 | 01243 | 17.28 | Solar | 18C2 | 2023-07-21 | 2023-08-08 | 13 |  | 13 |  |  | 0 | [22 empty] | 2023-08-08 | [12 empty] | 2024-03-22 | Online |  |  |  | Dalton-Hinsdale |  |  |  |  | 18C BERKSHIRE
WMECO | Pittsfield | ESMAEX-02692 | 01201 | 22.8 | Solar & Battery | 30B4 | 2023-07-19 | 2023-08-03 | 12 |  | 12 |  |  | 0 | [22 empty] | 2023-09-06 | [12 empty] | 2024-04-04 | Online | [8 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-02764 | 01104 | 15.2 | Solar | 5J10 | 2023-08-07 | 2023-08-11 | 5 |  | 5 |  |  | 0 | [22 empty] | 2023-09-28 | [12 empty] | 2024-05-23 | Online | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Easthampton | ESMAEX-02682 | 01027 | 15.2 | Solar & Battery | 15A5 | 2023-07-18 | 2023-12-15 | 109 |  | 109 |  |  | 0 | [22 empty] | 2023-12-29 | [12 empty] | 2024-05-15 | Online | [8 empty] | 15A GUNN
WMECO | Leverett | ESMAEX-02685 | 01054 | 15.2 | Solar & Battery | 21C7 | 2023-07-18 | 2023-09-06 | 37 |  | 37 |  |  | 0 | [22 empty] | 2023-10-25 | [12 empty] | 2024-06-18 | Online |  |  |  | Gill-Montague |  |  |  |  | 21C MONTAGUE
WMECO | West Springfield | ESMAEX-02702 | 01089 | 11.21 | Solar & Battery | 21N4 | 2023-07-21 | 2023-08-07 | 12 |  | 12 |  |  | 0 | [22 empty] | 2023-08-07 | [12 empty] | 2023-10-12 | Online | [8 empty] | 21N PIPER
WMECO | Middlefield | ESMAEX-02742 | 01243 | 10 | Battery | 18C2 | 2023-08-01 | 2023-09-05 | 26 |  | 26 |  |  | 0 | [22 empty] | 2023-10-02 | [12 empty] | 2024-03-01 | Online |  |  |  | Dalton-Hinsdale |  |  |  |  | 18C BERKSHIRE
WMECO | Southampton | ESMAEX-02710 | 01073 | 15.2 | Solar & Battery |  | 2023-07-25 | 2023-08-03 | 8 |  | 8 |  |  | 0 | [22 empty] | 2023-09-12 | [12 empty] | 2024-04-02 | Online
WMECO | Amherst | ESMAEX-02721 | 01002 | 20 | Solar | 17K2 | 2023-07-28 | 2023-08-11 | 11 |  | 11 |  |  | 0 | [22 empty] | 2023-08-22 | [12 empty] | 2023-11-13 | Online | [8 empty] | 17K AMHERST
WMECO | Pittsfield | ESMAEX-02741 | 01201 | 120 | Solar | 30B4 | 2023-10-19 | 2023-11-06 | 13 |  | 13 |  |  | 0 | [22 empty] | 2023-11-09 | [12 empty] | 2024-11-14 | Online | [8 empty] | 30B OSWALD
WMECO | Leverett | ESMAEX-02743 | 01054 | 15.2 | Solar & Battery | 18G7 | 2023-08-01 | 2023-08-15 | 11 |  | 11 |  |  | 0 | [22 empty] | 2023-09-18 | [12 empty] | 2024-03-01 | Online | [8 empty] | 18G PODICK
WMECO | Richmond | ESMAEX-02753 | 01254 | 24.4 | Solar | 30B7 | 2023-08-04 | 2023-08-11 | 6 |  | 6 |  |  | 0 | [22 empty] | 2023-11-15 | [12 empty] | 2025-09-09 | Online | [8 empty] | 30B OSWALD
WMECO | Agawam | ESMAEX-02765 | 01001 | 200 | Solar | 16C16 | 2023-08-29 | 2023-08-11 | -13 |  |  |  |  | 0 | [22 empty] | 2024-02-02 | [12 empty] | 2025-11-24 | Online | [8 empty] | 16C AGAWAM
WMECO | Easthampton | ESMAEX-02766 | 01027 | 10 | Solar | 15A3 | 2023-08-07 | 2023-08-11 | 5 |  | 5 |  |  | 0 | [22 empty] | 2023-11-09 | [12 empty] | 2023-12-18 | Online | [8 empty] | 15A GUNN
WMECO | Becket | ESMAEX-02759 | 01223 | 13.12 | Solar & Battery | 19J6 | 2023-08-04 | 2023-08-30 | 19 |  | 19 |  |  | 0 | [22 empty] | 2023-10-02 | [12 empty] | 2024-04-02 | Online
WMECO | Southampton | ESMAEX-02782 | 01073 | 15.2 | Solar & Battery | 15A1 | 2023-08-09 | 2023-08-17 | 7 |  | 7 |  |  | 0 | [22 empty] | 2023-09-18 | [12 empty] | 2024-01-03 | Online | [8 empty] | 15A GUNN
WMECO | Hinsdale | ESMAEX-02797 | 01235 | 4950 | Solar & Battery | 18C2 | 2023-12-07 | 2023-12-12 | 4 |  | 4 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Berkshire |  | Berkshire |  |  | 18C BERKSHIRE
WMECO | Plainfield | ESMAEX-02897 | 01070 | 5 | Solar & Battery | 18K4 | 2023-09-07 | 2023-09-13 | 5 |  | 5 |  |  | 0 | [22 empty] | 2023-10-18 | [12 empty] | 2024-05-07 | Online |  |  |  | Dalton-Hinsdale |  |  |  |  | 18K PLAINFIELD
WMECO | Plainfield | ESMAEX-02846 | 01075 | 4980 | Solar & Battery | 18K3 | 2023-09-28 | 2023-11-06 | 28 |  | 28 |  |  | 0 | [22 empty] | 2025-07-30 | [13 empty] | Compliances Documents | [7 empty] | 4980 | 18K PLAINFIELD
WMECO | Lanesborough | ESMAEX-02849 | 01237 | 4980 | Solar & Battery | 15E1 | 2023-09-28 | 2023-11-06 | 28 |  | 28 |  |  | 0 | [26 empty] | Complex | [9 empty] | Application Review | [8 empty] | 15E PARTRIDGE
WMECO | Agawam | ESMAEX-02855 | 01001 | 16 | Solar | 30A3 | 2023-08-23 | 2023-08-30 | 6 |  | 6 |  |  | 0 | [22 empty] | 2023-08-31 | [12 empty] | 2024-03-01 | Online | [7 empty] | 16 | SILVER
WMECO | Indian Orchard | ESMAEX-02866 | 01151 | 6 | Solar | 27A13 | 2023-08-25 | 2023-08-30 | 4 |  | 4 |  |  | 0 | [22 empty] | 2023-11-03 | [12 empty] | 2024-06-18 | Online | [8 empty] | 27A ORCHARD
WMECO | Northfield | ESMAEX-03085 | 01360 | 10 | Solar | 21B8 | 2023-10-25 | 2023-11-06 | 9 |  | 9 |  |  | 0 | [22 empty] | 2023-12-04 | [12 empty] | 2024-05-14 | Online |  |  |  | Gill-Montague |  |  |  |  | 21B FRENCH KING
WMECO | Russell | ESMAEX-02942 | 01071 | 25 | Solar | 19J2 | 2023-09-21 | 2023-10-04 | 10 |  | 10 |  |  | 0 | [22 empty] | 2023-11-09 | [12 empty] | 2024-05-29 | Online |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Easthampton | ESMAEX-02907 | 01027 | 21.25 | Solar & Battery | 15A2 | 2023-09-11 | 2023-09-19 | 7 |  | 7 |  |  | 0 | [22 empty] | 2023-11-01 | [12 empty] | 2024-03-11 | Online | [8 empty] | 15A GUNN
WMECO | Dalton | ESMAEX-02940 | 01226 | 22.8 | Solar | 19A2 | 2023-09-21 | 2023-10-12 | 16 |  | 16 |  |  | 0 | [22 empty] | 2023-10-12 | [12 empty] | 2024-09-20 | Online | [8 empty] | 19A DOREEN
WMECO | Springfield | ESMAEX-02924 | 01108 | 10 | Battery | 22H15 | 2023-09-15 | 2023-10-12 | 20 |  | 20 |  |  | 0 | [22 empty] | 2023-10-12 | [12 empty] | 2024-06-21 | Online | [8 empty] | 22H FRANCONIA
WMECO | Tyringham | ESMAEX-02990 | 01264 | 15.2 | Solar & Battery |  | 2023-09-29 | 2023-10-05 | 5 |  | 5 |  |  | 0 | [22 empty] | 2023-10-12 | [12 empty] | 2024-04-02 | Online
WMECO | Dalton | ESMAEX-03002 | 01226 | 15.2 | Solar | 18C1 | 2023-10-02 | 2023-10-12 | 9 |  | 9 |  |  | 0 | [22 empty] | 2023-11-09 | [12 empty] | 2024-06-19 | Online |  |  |  | Dalton-Hinsdale |  |  |  |  | 18C BERKSHIRE
WMECO | Richmond | ESMAEX-03008 | 01254 | 15.2 | Solar | 30B2 | 2023-10-03 | 2023-10-12 | 8 |  | 8 |  |  | 0 | [22 empty] | 2023-10-13 | [12 empty] | 2024-04-16 | Online | [8 empty] | 30B OSWALD
WMECO | Hatfield | ESMAEX-03011 | 01038 | 1992 | Solar & Battery | 18G6 | 2023-11-22 | 2023-11-29 | 6 |  | 6 |  |  | 0 | [36 empty] | Impact Study | [8 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-03039 | 01056 | 20 | Solar | 19S3 | 2023-10-12 | 2023-11-06 | 18 |  | 18 |  |  | 0 | [22 empty] | 2023-11-06 | [12 empty] | 2024-12-13 | Online | [8 empty] | 19S LUDLOW
WMECO | Pittsfield | ESMAEX-03068 | 01201 | 30 | Solar | 30B2 | 2023-10-19 | 2024-09-16 | 238 |  | 238 |  |  | 0 | [22 empty] | 2024-10-08 | [12 empty] | 2025-11-20 | Online | [8 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-03047 | 01107 | 6 | Solar | 21S6 | 2023-10-13 | 2023-10-25 | 9 |  | 9 |  |  | 0 | [22 empty] | 2023-11-06 | [12 empty] | 2024-02-07 | Online | [7 empty] | 6 | 21S CLINTON
WMECO | Ludlow | ESMAEX-03087 | 01056 | 17.28 | Solar | 19S1 | 2023-10-25 | 2023-11-06 | 9 |  | 9 |  |  | 0 | [22 empty] | 2023-11-09 | [12 empty] | 2024-02-08 | Online | [8 empty] | 19S LUDLOW
WMECO | Hadley | ESMAEX-03121 | 01035 | 16 | Solar & Battery | 19B15 | 2023-11-06 | 2023-12-07 | 24 |  | 24 |  |  | 0 | [22 empty] | 2023-12-29 | [12 empty] | 2024-03-05 | Online | [8 empty] | 19B MIDWAY
WMECO | Dalton | ESMAEX-03120 | 01226 | 15.2 | Solar & Battery |  | 2023-11-06 | 2023-11-16 | 9 |  | 9 |  |  | 0 | [22 empty] | 2023-11-22 | [12 empty] | 2024-06-21 | Online
WMECO | Agawam | ESMAEX-03118 | 01001 | 14.79 | Solar | 30A1 | 2023-11-03 | 2023-11-16 | 10 |  | 10 |  |  | 0 | [22 empty] | 2023-12-08 | [12 empty] | 2024-05-20 | Online | [8 empty] | 30A SILVER
WMECO | Amherst | ESMAEX-03125 | 01002 | 15 | Battery |  | 2023-11-07 | 2024-02-27 | 81 |  | 81 |  |  | 0 | [22 empty] | 2024-04-05 | [12 empty] | 2024-10-22 | Online
WMECO | Springfield | ESMAEX-03156 | 01118 | 7.6 | Solar & Battery | 20A32 | 2023-11-15 | 2023-11-20 | 4 |  | 4 |  |  | 0 | [22 empty] | 2024-03-12 | [12 empty] | 2024-11-22 | Online | [8 empty] | 20A BRECKWOOD
WMECO | Hatfield | ESMAEX-03241 | 01088 | 20 | Solar & Battery | 18G5 | 2023-12-06 | 2023-12-28 | 17 |  | 17 |  |  | 0 | [22 empty] | 2024-02-01 | [12 empty] | 2024-09-11 | Online | [8 empty] | 18G PODICK
WMECO | Westhampton | ESMAEX-03179 | 01027 | 15.2 | Solar | 15A3 | 2023-11-20 | 2023-11-29 | 8 |  | 8 |  |  | 0 | [22 empty] | 2023-12-13 | [12 empty] | 2024-06-12 | Online | [8 empty] | 15A GUNN
WMECO | Tolland | ESMAEX-03176 | 01034 | 2988 | Solar & Battery | 19J4 | 2023-11-20 | 2023-12-01 | 10 |  | 10 |  |  | 0 | [26 empty] | Complex | [9 empty] | Technical Review |  |  |  | Blandford |  |  |  | 2988 | 19J BLANDFORD
WMECO | Easthampton | ESMAEX-03184 | 01027 | 100 | Solar | 15A2 | 2023-11-21 | 2023-11-22 | 2 |  | 2 |  |  | 0 | [22 empty] | 2023-12-08 | [12 empty] | 2024-01-24 | Online | [8 empty] | 15A GUNN
WMECO | Plainfield | ESMAEX-03192 | 01070 | 3820 | Solar & Battery | 18K3 | 2023-11-22 | 2023-11-29 | 6 |  | 6 |  |  | 0 | [36 empty] | Technical Review |  |  |  | Plainfield |  |  |  | 3820 | 18K PLAINFIELD
WMECO | Hadley | ESMAEX-03228 | 01035 | 499 | Solar | 18G6 | 2024-02-08 | 2024-02-22 | 11 |  | 11 |  |  | 0 | [22 empty] | 2024-09-24 | [13 empty] | Compliances Documents | [7 empty] | 499 | 18G PODICK
WMECO | Hadley | ESMAEX-03229 | 01035 | 499 | Solar | 18G5 | 2024-02-08 | 2024-02-22 | 11 |  | 11 |  |  | 0 | [22 empty] | 2024-07-02 | [13 empty] | Technical Review | [7 empty] | 499 | 18G PODICK
WMECO | Whately | ESMAEX-03396 | 01093 | 84.6 | Solar & Battery | 18G8 | 2024-01-30 | 2024-02-22 | 18 |  | 18 |  |  | 0 | [22 empty] | 2025-05-16 | [13 empty] | Meter Review Rejected - Customer Action | [8 empty] | 18G PODICK
WMECO | Easthampton | ESMAEX-03234 | 01027 | 15.2 | Solar | 15A3 | 2023-12-06 | 2023-12-22 | 13 |  | 13 |  |  | 0 | [22 empty] | 2023-12-29 | [12 empty] | 2024-06-18 | Online | [8 empty] | 15A GUNN
WMECO | Easthampton | ESMAEX-03323 | 01027 | 15.36 | Solar & Battery | 15A3 | 2024-01-03 | 2024-01-17 | 11 |  | 11 |  |  | 0 | [22 empty] | 2024-01-30 | [12 empty] | 2024-07-16 | Online | [8 empty] | 15A GUNN
WMECO | Ashfield | ESMAEX-03516 | 01330 | 10 | Solar & Battery | 38A1 | 2024-03-08 | 2024-03-19 | 8 |  | 8 |  |  | 0 | [22 empty] | 2024-04-26 | [12 empty] | 2024-08-06 | Online | [7 empty] | 10 | 38A ASHFIELD
WMECO | Richmond | ESMAEX-03326 | 01254 | 15.36 | Solar & Battery | 30B2 | 2024-01-03 | 2024-01-17 | 11 |  | 11 |  |  | 0 | [22 empty] | 2024-02-13 | [12 empty] | 2024-09-25 | Online | [8 empty] | 30B OSWALD
WMECO | Hadley | ESMAEX-03306 | 01035 | 10 | Solar | 18G4 | 2023-12-21 | 2024-01-04 | 11 |  | 11 |  |  | 0 | [22 empty] | 2024-01-30 | [12 empty] | 2024-07-23 | Online | [8 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-03290 | 01056 | 7.6 | Battery | 27A4 | 2023-12-19 | 2024-01-17 | 22 |  | 22 |  |  | 0 | [22 empty] | 2024-05-15 | [12 empty] | 2024-11-19 | Online | [8 empty] | 27A ORCHARD
WMECO | Easthampton | ESMAEX-03304 | 01027 | 18 | Solar | 15A5 | 2023-12-21 | 2023-12-28 | 6 |  | 6 |  |  | 0 | [22 empty] | 2024-02-05 | [12 empty] | 2024-09-19 | Online | [8 empty] | 15A GUNN
WMECO | Easthampton | ESMAEX-03309 | 01027 | 22.8 | Solar | 15A2 | 2023-12-21 | 2023-12-28 | 6 |  | 6 |  |  | 0 | [22 empty] | 2024-01-30 | [12 empty] | 2024-05-15 | Online | [8 empty] | 15A GUNN
WMECO | Longmeadow | ESMAEX-03380 | 01106 | 15.2 | Solar & Battery |  | 2024-01-24 | 2024-02-01 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-02-26 | [12 empty] | 2024-10-28 | Online
WMECO | Buckland | ESMAEX-03311 | 01338 | 37.5 | Solar | 22B5 | 2023-12-22 | 2024-01-09 | 13 |  | 13 |  |  | 0 | [22 empty] | 2024-03-13 | [12 empty] | 2025-01-21 | Online | [8 empty] | 22B CUMBERLAND
WMECO | West Springfield | ESMAEX-03327 | 01089 | 15.2 | Solar | 16C11 | 2024-01-03 | 2024-01-19 | 13 |  | 13 |  |  | 0 | [22 empty] | 2024-01-24 | [12 empty] | 2024-03-05 | Online | [7 empty] | 15.2 | 16C AGAWAM
WMECO | Westhampton | ESMAEX-03330 | 01027 | 15.2 | Solar & Battery | 15A3 | 2024-01-04 | 2024-01-17 | 10 |  | 10 |  |  | 0 | [22 empty] | 2024-01-30 | [12 empty] | 2024-08-29 | Online | [8 empty] | 15A GUNN
WMECO | Amherst | ESMAEX-03343 | 01002 | 16.5 | Solar | 18G4 | 2024-01-09 | 2024-01-17 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-01-30 | [12 empty] | 2024-07-16 | Online | [7 empty] | 15.95 | 18G PODICK
WMECO | Conway | ESMAEX-03473 | 01341 | 20 | Battery | 38A1 | 2024-02-22 | 2024-02-28 | 5 |  | 5 |  |  | 0 | [22 empty] | 2024-04-05 | [12 empty] | 2024-08-30 | Online | [7 empty] | 10 | 38A ASHFIELD
WMECO | Greenfield | ESMAEX-03367 | 01301 | 999 | Solar & Battery | 22B2 | 2025-04-25 | 2025-05-08 | 10 |  | 10 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [7 empty] | 999 | 22B CUMBERLAND
WMECO | Westhampton | ESMAEX-03638 | 01027 | 17.6 | Solar | 15A3 | 2024-04-08 | 2024-04-18 | 9 |  | 9 |  |  | 0 | [22 empty] | 2024-05-28 | [12 empty] | 2025-01-16 | Online | [8 empty] | 15A GUNN
WMECO | Greenfield | ESMAEX-03857 | 01301 | 30 | Solar | 22B4 | 2024-06-24 | 2024-07-25 | 24 |  | 24 |  |  | 0 | [22 empty] | 2024-09-03 | [12 empty] | 2025-03-20 | Online | [8 empty] | 22B CUMBERLAND
WMECO | Hancock | ESMAEX-04296 | 01237 | 2000 | Solar | 30B7 | 2024-11-22 | 2025-01-30 | 50 |  | 50 |  |  | 0 | [22 empty] | 2025-04-16 | [13 empty] | Compliances Documents | [7 empty] | 2000 | 30B OSWALD
WMECO | Tolland | ESMAEX-03388 | 01034 | 9.9 | Solar & Battery | 19J4 | 2024-01-26 | 2024-02-09 | 11 |  | 11 |  |  | 0 | [22 empty] | 2024-02-13 | [12 empty] | 2024-05-20 | Online |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Hancock | ESMAEX-04297 | 01237 | 2000 | Solar | 30B7 | 2024-11-22 | 2025-01-30 | 50 |  | 50 |  |  | 0 | [22 empty] | 2025-04-16 | [13 empty] | Compliances Documents | [7 empty] | 2000 | 30B OSWALD
WMECO | Pittsfield | ESMAEX-04298 | 01201 | 1000 | Solar | 30B7 | 2024-11-22 | 2025-01-22 | 44 |  | 44 |  |  | 0 | [22 empty] | 2025-04-16 | [13 empty] | Compliances Documents | [7 empty] | 1000 | 30B OSWALD
WMECO | South Deerfield | ESMAEX-03438 | 01373 | 10 | Battery | 18G3 | 2024-02-14 | 2024-03-18 | 24 |  | 24 |  |  | 0 | [22 empty] | 2024-04-05 | [12 empty] | 2024-09-17 | Online | [8 empty] | 18G PODICK
WMECO | Hadley | ESMAEX-03394 | 01035 | 15.2 | Solar | 17K5 | 2024-01-29 | 2024-02-01 | 4 |  | 4 |  |  | 0 | [22 empty] | 2024-03-12 | [12 empty] | 2024-09-13 | Online | [8 empty] | 17K AMHERST
WMECO | Springfield | ESMAEX-03437 | 01118 | 5 | Solar & Battery | 20A21 | 2024-02-14 | 2024-02-22 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-02-26 | [12 empty] | 2024-07-16 | Online | [8 empty] | 20A BRECKWOOD
WMECO | Plainfield | ESMAEX-03434 | 01070 | 24 | Solar | 18C1 | 2024-02-13 | 2024-04-23 | 51 |  | 51 |  |  | 0 | [22 empty] | 2024-04-04 | [12 empty] | 2024-10-06 | Online |  |  |  | Plainfield |  |  |  |  | 18C BERKSHIRE
WMECO | Turners Falls | ESMAEX-03587 | 01376 | 40 | Solar | 21C6 | 2024-03-28 | 2024-05-09 | 31 |  | 31 |  |  | 0 | [22 empty] | 2024-07-11 | [12 empty] | 2025-12-10 | Online |  |  |  | Gill-Montague |  |  |  |  | 21C MONTAGUE
WMECO | Agawam | ESMAEX-03455 | 01001 | 1500 | Solar | 30A3 | 2024-05-06 | 2024-06-06 | 24 |  | 24 |  |  | 0 | [36 empty] | Compliance Documents | [8 empty] | 30A SILVER
WMECO | West Springfield | ESMAEX-03502 | 01089 | 250 | Solar | 21N8 | 2024-03-01 | 2024-04-03 | 24 |  | 24 |  |  | 0 | [22 empty] | 2024-06-24 | [12 empty] | 2025-09-05 | Online | [8 empty] | 21N PIPER
WMECO | Springfield | ESMAEX-03541 | 01103 | 700 | Fuel Cell | 8C13 | 2024-03-19 | 2024-04-03 | 12 |  | 12 |  |  | 0 | [22 empty] | 2025-12-03 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 8C WEST SPRINGFIELD
WMECO | Erving | ESMAEX-03495 | 01360 | 4980 | Solar & Battery | 21B8 | 2024-02-29 | 2024-03-18 | 13 |  | 13 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Gill-Montague |  | Whatley-Deerfield |  | 4980 | 21B FRENCH KING
WMECO | Worthington | ESMAEX-03482 | 01098 | 15.2 | Solar | 18C2 | 2024-02-27 | 2024-03-06 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-04-05 | [12 empty] | 2024-09-24 | Online |  |  |  | Plainfield |  |  |  |  | 18C BERKSHIRE
WMECO | Lenox Dale | ESMAEX-03488 | 01242 | 13.6 | Solar & Battery | 17G3 | 2024-02-28 | 2024-03-06 | 6 |  | 6 |  |  | 0 | [22 empty] | 2024-03-06 | [12 empty] | 2025-01-31 | Online | [8 empty] | 17G WOODLAND RD
WMECO | Worthington | ESMAEX-03492 | 01098 | 20 | Solar | 18C2 | 2024-02-29 | 2024-03-06 | 5 |  | 5 |  |  | 0 | [22 empty] | 2024-04-05 | [12 empty] | 2024-10-04 | Online |  |  |  | Plainfield |  |  |  |  | 18C BERKSHIRE
WMECO | Springfield | ESMAEX-03550 | 01104 | 32.83 | Solar | 5J13 | 2024-03-19 | 2024-05-13 | 40 |  | 40 |  |  | 0 | [22 empty] | 2024-05-22 | [12 empty] | 2026-02-13 | Online | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Otis | ESMAEX-03531 | 01253 | 70 | Solar | 19J4 | 2024-03-12 | 2024-04-01 | 15 |  | 15 |  |  | 0 | [22 empty] | 2024-05-24 | [13 empty] | Construction Stage |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Lee | ESMAEX-03528 | 01238 | 10 | Solar & Battery | 16B5 | 2024-03-11 | 2024-03-21 | 9 |  | 9 |  |  | 0 | [22 empty] | 2024-04-25 | [12 empty] | 2024-08-09 | Online | [8 empty] | 16B PLEASANT
WMECO | Turners Falls | ESMAEX-03511 | 01376 | 990 | Battery | 21C8 | 2024-07-24 | 2024-09-16 | 39 |  | 39 |  |  | 0 | [22 empty] | 2025-02-25 | [13 empty] | Technical Review |  |  |  | Gill-Montague |  |  |  | 990 | 21C MONTAGUE
WMECO | Hadley | ESMAEX-03526 | 01035 | 498 | Solar | 18G4 | 2024-06-11 | 2024-06-21 | 9 |  | 9 |  |  | 0 | [22 empty] | 2024-09-23 |  |  |  | Expedited | [9 empty] | Application Review | [8 empty] | 18G PODICK
WMECO | Worthington | ESMAEX-03537 | 01098 | 16.8 | Solar | 18C2 | 2024-03-14 | 2024-03-21 | 6 |  | 6 |  |  | 0 | [22 empty] | 2024-04-05 | [12 empty] | 2024-08-29 | Online |  |  |  | Plainfield |  |  |  |  | 18C BERKSHIRE
WMECO | Easthampton | ESMAEX-03563 | 01027 | 15.2 | Solar & Battery | 15A5 | 2024-03-21 | 2024-03-27 | 5 |  | 5 |  |  | 0 | [22 empty] | 2024-05-01 | [12 empty] | 2024-08-08 | Online | [8 empty] | 15A GUNN
WMECO | Southwick | ESMAEX-04793 | 01077 | 10 | Solar & Battery | 29A1 | 2025-04-15 | 2025-04-29 | 11 |  | 11 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review |  |  |  | Southwick |  |  |  | 8.74 | 29A SOUTHWICK
WMECO | Middlefield | ESMAEX-03579 | 01243 | 10 | Solar & Battery | 18C2 | 2024-03-26 | 2024-04-03 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-07-31 | [12 empty] | 2025-01-24 | Online |  |  |  | Dalton-Hinsdale |  |  |  |  | 18C BERKSHIRE
WMECO | Peru | ESMAEX-03573 | 01235 | 4999.8 | Solar & Battery | 18C2 | 2024-03-25 | 2024-05-15 | 38 |  | 38 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Berkshire |  | Berkshire |  | 4999.8 | 18C BERKSHIRE
WMECO | Easthampton | ESMAEX-03576 | 01027 | 15.2 | Solar | 15A2 | 2024-03-26 | 2024-04-03 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-05-15 | [12 empty] | 2024-09-12 | Online | [8 empty] | 15A GUNN
WMECO | West Springfield | ESMAEX-03620 | 01089 | 50 | Solar |  | 2024-04-03 | 2024-05-15 | 31 |  | 31 |  |  | 0 | [22 empty] | 2024-05-28 | [12 empty] | 2025-01-22 | Online
WMECO | Deerfield | ESMAEX-03581 | 01342 | 46 | Solar & Battery | 22B4 | 2024-03-27 | 2024-04-12 | 13 |  | 13 |  |  | 0 | [22 empty] | 2024-05-21 | [12 empty] | 2024-10-28 | Online | [8 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-03600 | 01118 | 15.2 | Solar | 20A32 | 2024-04-01 | 2024-04-12 | 10 |  | 10 |  |  | 0 | [22 empty] | 2024-11-28 | [12 empty] | 2025-02-26 | Online | [8 empty] | 20A BRECKWOOD
WMECO | Amherst | ESMAEX-03626 | 01002 | 20 | Solar | 18G3 | 2024-04-03 | 2024-06-05 | 46 |  | 46 |  |  | 0 | [22 empty] | 2024-09-23 | [12 empty] | 2024-11-07 | Online | [8 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-03681 | 01108 | 10 | Battery | 22H16 | 2024-04-18 | 2024-04-24 | 5 |  | 5 |  |  | 0 | [22 empty] | 2024-04-26 | [12 empty] | 2024-09-25 | Online | [8 empty] | 22H FRANCONIA
WMECO | Amherst | ESMAEX-03648 | 01002 | 15.2 | Solar | 18G7 | 2024-04-09 | 2024-05-21 | 31 |  | 31 |  |  | 0 | [22 empty] | 2024-07-23 | [12 empty] | 2024-12-13 | Online | [8 empty] | 18G PODICK
WMECO | Lanesborough | ESMAEX-03699 | 01237 | 9.9 | Solar & Battery | 15E1 | 2024-04-22 | 2024-05-13 | 16 |  | 16 |  |  | 0 | [22 empty] | 2024-07-10 | [12 empty] | 2024-09-17 | Online | [7 empty] | 9.75
WMECO | Ludlow | ESMAEX-03662 | 01056 | 3.8 | Solar | 27A4 | 2024-04-12 | 2024-05-28 | 33 |  | 33 |  |  | 0 | [22 empty] | 2024-05-30 | [12 empty] | 2024-09-16 | Online | [8 empty] | 27A ORCHARD
WMECO | Pittsfield | ESMAEX-03669 | 01201 | 7.6 | Solar | 19A1 | 2024-04-15 | 2024-06-06 | 39 |  | 39 |  |  | 0 | [22 empty] | 2024-07-23 | [12 empty] | 2024-09-17 | Online | [8 empty] | 19A DOREEN
WMECO | Savoy | ESMAEX-03695 | 01256 | 10 | Battery | 18K4 | 2024-04-22 | 2024-05-14 | 17 |  | 17 |  |  | 0 | [22 empty] | 2024-05-22 | [12 empty] | 2024-08-28 | Online |  |  |  | Dalton-Hinsdale |  |  |  |  | 18C BERKSHIRE
WMECO | Amherst | ESMAEX-03769 | 01002 | 100 | Solar | 17K7 | 2024-05-15 | 2024-05-22 | 6 |  | 6 |  |  | 0 | [22 empty] | 2025-05-05 | [12 empty] | 2025-12-08 | Permission to Operate | [8 empty] | 17K AMHERST
WMECO | Lee | ESMAEX-03737 | 01238 | 100 | Solar | 16B5 | 2024-05-07 | 2024-05-28 | 16 |  | 16 |  |  | 0 | [22 empty] | 2024-08-30 | [13 empty] | Compliances Documents | [8 empty] | 16B PLEASANT
WMECO | Shutesbury | ESMAEX-03732 | 01072 | 11.5 | Solar & Battery | 18G7 | 2024-05-03 | 2024-05-14 | 8 |  | 8 |  |  | 0 | [22 empty] | 2024-06-18 | [12 empty] | 2024-10-07 | Online | [8 empty] | 18G PODICK
WMECO | Ludlow | ESMAEX-03727 | 01056 | 15.2 | Solar |  | 2024-05-02 | 2024-05-31 | 22 |  | 22 |  |  | 0 | [22 empty] | 2024-07-17 | [12 empty] | 2024-12-17 | Online
WMECO | Sunderland | ESMAEX-03718 | 01375 | 10 | Solar | 18G6 | 2024-04-30 | 2024-06-06 | 28 |  | 28 |  |  | 0 | [22 empty] | 2024-07-30 | [12 empty] | 2025-01-14 | Online | [8 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-03739 | 01108 | 240 | Solar | 22H17 | 2024-05-08 | 2024-05-16 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-08-26 | [13 empty] | Compliances Documents | [8 empty] | 22H FRANCONIA
WMECO | Hatfield | ESMAEX-03738 | 01038 | 15 | Solar | 18G6 | 2024-05-08 | 2024-05-21 | 10 |  | 10 |  |  | 0 | [22 empty] | 2024-07-23 | [12 empty] | 2024-12-02 | Online | [8 empty] | 18G PODICK
WMECO | Agawam | ESMAEX-03748 | 01001 | 9 | Solar | 30A5 | 2024-05-10 | 2024-07-09 | 43 |  | 43 |  |  | 0 | [22 empty] | 2024-07-12 | [12 empty] | 2024-09-03 | Online | [8 empty] | 30A SILVER
WMECO | Hinsdale | ESMAEX-03822 | 01235 | 4999.8 | Solar & Battery | 18C2 | 2024-06-10 | 2024-06-21 | 10 |  | 10 |  |  | 0 | [36 empty] | Impact Study |  |  |  | Berkshire |  | Berkshire |  | 4999.8 | 18C BERKSHIRE
WMECO | Springfield | ESMAEX-03751 | 01108 | 15.2 | Solar | 21S11 | 2024-05-10 | 2024-05-30 | 15 |  | 15 |  |  | 0 | [22 empty] | 2024-06-15 | [12 empty] | 2024-10-30 | Online | [8 empty] | 21S CLINTON
WMECO | Sunderland | ESMAEX-03764 | 01375 | 20 | Solar | 18G6 | 2024-05-14 | 2024-06-06 | 18 |  | 18 |  |  | 0 | [22 empty] | 2024-07-23 | [12 empty] | 2025-04-07 | Online | [8 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-03772 | 01107 | 20 | Solar | 21S10 | 2024-05-15 | 2024-06-21 | 28 |  | 28 |  |  | 0 | [22 empty] | 2025-01-10 | [12 empty] | 2025-06-12 | Online | [8 empty] | 21S CLINTON
WMECO | Turners Falls | ESMAEX-03804 | 01376 | 600 | Internal Combustion Engine | 21C2 | 2024-05-30 | 2024-06-21 | 17 |  | 17 |  |  | 0 | [22 empty] | 2025-09-09 |  |  |  | Expedited | [9 empty] | On Hold |  |  |  | Gill-Montague |  |  |  | 0 | 21C MONTAGUE
WMECO | Montgomery | ESMAEX-03811 | 01085 | 15.2 | Solar | 19J5 | 2024-06-04 | 2024-07-01 | 20 |  | 20 |  |  | 0 | [22 empty] | 2024-08-30 | [12 empty] | 2024-12-20 | Online |  |  |  | Blandford
WMECO | Bernardston | ESMAEX-03897 | 01337 | 240 | Solar | 21B8 | 2024-07-12 | 2024-07-22 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-09-03 | [13 empty] | Compliances Documents |  |  |  | Gill-Montague |  |  |  |  | 21B FRENCH KING
WMECO | Greenfield | ESMAEX-03928 | 01301 | 240 | Solar | 22B7 | 2024-07-26 | 2024-08-06 | 8 |  | 8 |  |  | 0 | [22 empty] | 2024-09-10 | [13 empty] | Construction Stage | [8 empty] | 22B CUMBERLAND
WMECO | Hatfield | ESMAEX-03820 | 01038 | 750 | Solar | 18G5 | 2024-10-24 | 2024-11-01 | 7 |  | 7 |  |  | 0 | [36 empty] | Compliances Documents | [8 empty] | 18G PODICK
WMECO | Sunderland | ESMAEX-03843 | 01375 | 20 | Solar | 18G3 | 2024-06-14 | 2024-08-05 | 37 |  | 37 |  |  | 0 | [22 empty] | 2024-08-30 | [12 empty] | 2025-02-12 | Online | [8 empty] | 18G PODICK
WMECO | Leyden | ESMAEX-03827 | 01337 | 10 | Solar | 22B7 | 2024-06-12 | 2024-07-08 | 19 |  | 19 |  |  | 0 | [22 empty] | 2024-08-07 | [12 empty] | 2025-01-02 | Online | [8 empty] | 22B CUMBERLAND
WMECO | Colrain | ESMAEX-03862 | 01340 | 20 | Solar & Battery | 29R2 | 2024-06-25 | 2024-07-23 | 21 |  | 21 |  |  | 0 | [22 empty] | 2024-08-28 | [12 empty] | 2025-01-02 | Online | [8 empty] | 29R SHELBURNE
WMECO | South Deerfield | ESMAEX-03855 | 01373 | 15.2 | Solar | 22B1 | 2024-06-24 | 2024-07-05 | 10 |  | 10 |  |  | 0 | [22 empty] | 2024-08-08 | [12 empty] | 2024-11-26 | Online | [8 empty] | 22B CUMBERLAND
WMECO | West Springfield | ESMAEX-03872 | 01089 | 20 | Solar | 21N9 | 2024-06-29 | 2024-07-23 | 17 |  | 17 |  |  | 0 | [22 empty] | 2024-07-29 | [12 empty] | 2024-12-13 | Online | [8 empty] | 21N PIPER
WMECO | Ludlow | ESMAEX-03876 | 01056 | 23 | Solar & Battery | 19S3 | 2024-07-01 | 2024-07-09 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-10-29 | [12 empty] | 2025-02-14 | Online | [8 empty] | 19S LUDLOW
WMECO | Amherst | ESMAEX-03880 | 01002 | 23 | Solar | 19B16 | 2024-07-02 | 2024-08-07 | 27 |  | 27 |  |  | 0 | [22 empty] | 2024-08-30 | [12 empty] | 2024-12-24 | Online | [8 empty] | 19B MIDWAY
WMECO | East Otis | ESMAEX-03888 | 01029 | 20 | Solar | 19J4 | 2024-07-10 | 2024-08-06 | 20 |  | 20 |  |  | 0 | [22 empty] | 2024-10-06 | [12 empty] | 2025-01-10 | Online |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-03925 | 01201 | 3500 | Solar & Battery | 15E2 | 2024-07-25 | 2024-08-06 | 9 |  | 9 |  |  | 0 | [36 empty] | Impact Study | [8 empty] | 15E PARTRIDGE
WMECO | Lee | ESMAEX-03914 | 01238 | 4999 | Other | 16B5 | 2025-02-04 | 2025-02-11 | 6 |  | 6 |  |  | 0 | [26 empty] | Standard | [9 empty] | Exhibit E Agreement | [7 empty] | 4999 | 16B PLEASANT
WMECO | Huntington | ESMAEX-03924 | 01050 | 23 | Solar & Battery | 19J5 | 2024-07-25 | 2024-08-20 | 19 |  | 19 |  |  | 0 | [22 empty] | 2024-09-23 | [12 empty] | 2024-12-13 | Online
WMECO | Feeding Hills | ESMAEX-03937 | 01030 | 15.2 | Solar | 30A6 | 2024-07-30 | 2024-09-13 | 34 |  | 34 |  |  | 0 | [22 empty] | 2024-10-16 | [12 empty] | 2025-01-06 | Online | [8 empty] | 30A SILVER
WMECO | Tyringham | ESMAEX-03966 | 01264 | 23 | Solar | 16B1 | 2024-08-14 | 2024-08-28 | 11 |  | 11 |  |  | 0 | [22 empty] | 2024-08-30 | [12 empty] | 2025-01-14 | Online | [8 empty] | 16B PLEASANT
WMECO | Pittsfield | ESMAEX-03954 | 01201 | 180 | Solar | 30B2 | 2024-09-06 | 2024-11-08 | 46 |  | 46 |  |  | 0 | [22 empty] | 2026-02-19 | [13 empty] | ISA Agreement | [8 empty] | 30B OSWALD
WMECO | Longmeadow | ESMAEX-03961 | 01106 | 15.36 | Solar | 22H13 | 2024-08-12 | 2024-08-14 | 3 |  | 3 |  |  | 0 | [22 empty] | 2024-09-16 | [12 empty] | 2025-02-12 | Online | [8 empty] | 22H FRANCONIA
WMECO | Lee | ESMAEX-03957 | 01238 | 15.2 | Solar | 16B5 | 2024-08-09 | 2024-09-11 | 24 |  | 24 |  |  | 0 | [22 empty] | 2024-10-06 | [12 empty] | 2025-02-12 | Online | [8 empty] | 16B PLEASANT
WMECO | Montague | ESMAEX-03967 | 01351 | 20 | Battery | 21C7 | 2024-08-14 | 2024-09-11 | 21 |  | 21 |  |  | 0 | [22 empty] | 2024-10-16 | [12 empty] | 2024-12-30 | Online |  |  |  | Gill-Montague |  |  |  | 10 | 21C MONTAGUE
WMECO | West Hatfield | ESMAEX-03989 | 01088 | 9.57 | Solar | 18G5 | 2024-08-22 | 2024-08-29 | 6 |  | 6 |  |  | 0 | [22 empty] | 2024-09-23 | [12 empty] | 2024-12-13 | Online | [8 empty] | 18G PODICK
WMECO | Whately | ESMAEX-03978 | 01093 | 23 | Solar & Battery | 18G8 | 2024-08-18 | 2024-08-28 | 8 |  | 8 |  |  | 0 | [22 empty] | 2024-09-25 | [13 empty] | Compliances Documents | [7 empty] | 23 | 18G PODICK
WMECO | Otis | ESMAEX-03984 | 01253 | 5000 | Solar & Battery | 19J4 | 2024-09-09 | 2024-09-13 | 5 |  | 5 |  |  | 0 | [26 empty] | Complex | [9 empty] | Technical Review |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Lanesborough | ESMAEX-04002 | 01237 | 16.9 | Battery | 15E1 | 2024-08-27 | 2024-09-16 | 15 |  | 15 |  |  | 0 | [22 empty] | 2024-09-17 | [13 empty] | Permission to Operate | [7 empty] | 6.9
WMECO | Southampton | ESMAEX-04025 | 01073 | 23 | Solar & Battery | 15A3 | 2024-09-04 | 2024-09-26 | 17 |  | 17 |  |  | 0 | [22 empty] | 2024-10-29 | [12 empty] | 2025-02-24 | Online | [8 empty] | 15A GUNN
WMECO | Amherst | ESMAEX-04054 | 01002 | 30 | Solar | 18G7 | 2024-09-12 | 2024-09-20 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-10-29 | [12 empty] | 2025-01-24 | Online | [8 empty] | 18G PODICK
WMECO | Hadley | ESMAEX-04039 | 01035 | 999 | Solar | 17K5 | 2024-11-19 | 2025-01-28 | 51 |  | 51 |  |  | 0 | [22 empty] | 2025-03-04 |  |  |  | Expedited | [9 empty] | Compliances Documents | [7 empty] | 999 | 17K AMHERST
WMECO | Hadley | ESMAEX-04202 | 01035 | 625 | Solar | 17K5 | 2024-10-24 | 2024-11-18 | 18 |  | 18 |  |  | 0 | [22 empty] | 2025-03-26 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 17K AMHERST
WMECO | Lee | ESMAEX-04068 | 01238 | 15.2 | Solar |  | 2024-09-18 | 2024-10-22 | 25 |  | 25 |  |  | 0 | [22 empty] | 2024-10-24 | [12 empty] | 2025-04-07 | Online
WMECO | Hadley | ESMAEX-04056 | 01035 | 240 | Solar | 17K1 | 2024-09-13 | 2024-09-19 | 5 |  | 5 |  |  | 0 | [22 empty] | 2024-12-03 | [13 empty] | Compliances Documents | [8 empty] | 17K AMHERST
WMECO | Southwick | ESMAEX-04115 | 01077 | 7.6 | Solar | 29A1 | 2024-09-26 | 2024-10-17 | 16 |  | 16 |  |  | 0 | [22 empty] | 2025-03-28 | [12 empty] | 2025-07-17 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Southampton | ESMAEX-04155 | 01073 | 15.2 | Solar | 15A1 | 2024-10-08 | 2024-10-28 | 15 |  | 15 |  |  | 0 | [22 empty] | 2024-12-03 | [12 empty] | 2025-03-12 | Online | [8 empty] | 15A GUNN
WMECO | North Hatfield | ESMAEX-04157 | 01066 | 17.16 | Solar | 18G6 | 2024-10-09 | 2024-10-18 | 8 |  | 8 |  |  | 0 | [22 empty] | 2024-12-09 | [12 empty] | 2025-04-08 | Online | [8 empty] | 18G PODICK
WMECO | Dalton | ESMAEX-04162 | 01226 | 2988 | Solar & Battery | 18C1 | 2024-11-01 | 2024-11-18 | 12 |  | 12 |  |  | 0 | [26 empty] | Complex | [9 empty] | Technical Review |  |  |  | Berkshire |  |  |  |  | 18C BERKSHIRE
WMECO | Southampton | ESMAEX-04166 | 01073 | 3000 | Solar & Battery | 15A1 | 2024-11-06 | 2024-11-18 | 9 |  | 9 |  |  | 0 | [26 empty] | Complex | [9 empty] | Transmission | [8 empty] | 15A GUNN
WMECO | Ludlow | ESMAEX-04200 | 01056 | 7.6 | Solar | 19S3 | 2024-10-22 | 2024-11-08 | 14 |  | 14 |  |  | 0 | [22 empty] | 2024-11-18 | [12 empty] | 2025-03-25 | Online | [8 empty] | 19S LUDLOW
WMECO | Richmond | ESMAEX-04237 | 01254 | 10 | Solar & Battery | 30B7 | 2024-11-04 | 2024-11-12 | 7 |  | 7 |  |  | 0 | [22 empty] | 2025-04-02 | [13 empty] | Technical Review | [8 empty] | 30B OSWALD
WMECO | Easthampton | ESMAEX-04203 | 01027 | 11.5 | Battery | 15A2 | 2024-10-24 |  | -32530 |  |  |  |  | 0 | [22 empty] | 2025-04-10 | [12 empty] | 2025-06-13 | Online | [8 empty] | 15A GUNN
WMECO | Southwick | ESMAEX-04231 | 01077 | 15 | Battery | 29A5 | 2024-11-01 | 2024-11-19 | 13 |  | 13 |  |  | 0 | [22 empty] | 2025-04-03 | [12 empty] | 2025-07-18 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Dalton | ESMAEX-04224 | 01226 | 24 | Solar | 19A2 | 2024-10-29 | 2024-11-06 | 7 |  | 7 |  |  | 0 | [22 empty] | 2024-11-06 | [12 empty] | 2025-02-27 | Online | [8 empty] | 19A DOREEN
WMECO | Hinsdale | ESMAEX-04230 | 01235 | 13.8 | Solar | 18C2 | 2024-11-01 | 2025-01-08 | 49 |  | 49 |  |  | 0 | [22 empty] | 2025-02-06 | [13 empty] | Compliances Documents |  |  |  | Dalton-Hinsdale |  |  |  |  | 18C BERKSHIRE
WMECO | Southwick | ESMAEX-04274 | 01077 | 11.5 | Battery | 29A5 | 2024-11-13 |  | -32544 |  |  |  |  | 0 | [22 empty] | 2025-03-27 | [12 empty] | 2025-06-13 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Amherst | ESMAEX-04280 | 01002 | 300 | Solar | 17K5 | 2025-02-14 | 2025-02-24 | 7 |  | 7 |  |  | 0 | [22 empty] | 2026-03-09 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 17K AMHERST
WMECO | Hadley | ESMAEX-04356 | 01035 | 22.8 | Solar | 19B15 | 2024-12-10 | 2025-01-24 | 34 |  | 34 |  |  | 0 | [22 empty] | 2025-03-05 | [13 empty] | Compliances Documents | [8 empty] | 19B MIDWAY
WMECO | Hadley | ESMAEX-04357 | 01035 | 22.8 | Solar | 19B15 | 2024-12-10 | 2025-01-24 | 34 |  | 34 |  |  | 0 | [22 empty] | 2025-03-10 | [13 empty] | Meter | [8 empty] | 19B MIDWAY
WMECO | West Springfield | ESMAEX-04335 | 01089 | 11.5 | Battery | 16C11 | 2024-12-05 | 2025-01-24 | 37 |  | 37 |  |  | 0 | [22 empty] | 2025-03-06 | [13 empty] | Compliances Documents | [8 empty] | 16C AGAWAM
WMECO | Blandford | ESMAEX-04291 | 01008 | 1999 | Solar & Battery | 19J2 | 2024-11-21 | 2024-12-05 | 11 |  | 11 |  |  | 0 | [26 empty] | Complex | [9 empty] | Impact Study |  |  |  | Blandford |  |  |  | 1999 | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-04288 | 01201 | 46 | Solar & Battery |  | 2024-11-20 | 2024-11-26 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-04-02 | [12 empty] | 2025-07-16 | Online
WMECO | West Springfield | ESMAEX-04318 | 01089 | 22.77 | Solar | 21N9 | 2024-12-03 | 2024-12-18 | 12 |  | 12 |  |  | 0 | [22 empty] | 2025-04-14 | [12 empty] | 2025-09-17 | Online | [8 empty] | 21N PIPER
WMECO | Feeding Hills | ESMAEX-04359 | 01030 | 15.2 | Solar | 30A1 | 2024-12-11 | 2025-01-15 | 26 |  | 26 |  |  | 0 | [22 empty] | 2025-04-18 | [12 empty] | 2025-10-20 | Online | [8 empty] | 30A SILVER
WMECO | Deerfield | ESMAEX-04370 | 01342 | 4999 | Solar & Battery | 22B7 | 2024-12-13 |  | -32566 |  |  |  |  | 0 | [26 empty] | Complex | [9 empty] | Technical Review | [8 empty] | 22B CUMBERLAND
WMECO | Erving | ESMAEX-04365 | 01344 | 200 | Solar | 21C8 | 2024-12-17 | 2025-01-28 | 31 |  | 31 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review |  |  |  | Gill-Montague |  |  |  |  | 21C MONTAGUE
WMECO | Amherst | ESMAEX-04361 | 01002 | 15.2 | Solar | 19B16 | 2024-12-11 | 2025-01-15 | 26 |  | 26 |  |  | 0 | [22 empty] | 2025-02-07 | [12 empty] | 2025-04-29 | Online | [8 empty] | 19B MIDWAY
WMECO | Hadley | ESMAEX-04385 | 01035 | 67.3 | Solar | 18G4 | 2024-12-16 | 2025-01-21 | 27 |  | 27 |  |  | 0 | [22 empty] | 2025-02-12 | [12 empty] | 2025-09-29 | Online | [8 empty] | 18G PODICK
WMECO | West Springfield | ESMAEX-04467 | 01089 | 240 | Solar | 21N5 | 2025-06-17 | 2025-06-30 | 10 |  | 10 |  |  | 0 | [26 empty] | Expedited | [9 empty] | ISA Agreement | [8 empty] | 21N PIPER
WMECO | Westhampton | ESMAEX-04403 | 01027 | 15.2 | Solar | 15A3 | 2024-12-23 | 2025-01-22 | 23 |  | 23 |  |  | 0 | [22 empty] | 2025-02-12 | [12 empty] | 2025-06-17 | Online | [8 empty] | 15A GUNN
WMECO | Springfield | ESMAEX-04412 | 01109 | 400 | Solar | 5J18 | 2025-04-15 | 2025-05-02 | 14 |  | 14 |  |  | 0 | [22 empty] | 2025-10-23 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Pittsfield | ESMAEX-04476 | 01201 | 120 | Solar | 30B2 | 2025-01-29 | 2025-02-11 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-05-05 | [13 empty] | Compliances Documents | [8 empty] | 30B OSWALD
WMECO | Whately | ESMAEX-04431 | 01093 | 11.4 | Solar | 18G8 | 2025-01-14 | 2025-01-30 | 13 |  | 13 |  |  | 0 | [22 empty] | 2025-02-12 | [12 empty] | 2025-06-16 | Online | [8 empty] | 18G PODICK
WMECO | Easthampton | ESMAEX-04459 | 01027 | 15.2 | Solar | 15A5 | 2025-01-22 | 2025-02-07 | 13 |  | 13 |  |  | 0 | [22 empty] | 2025-03-17 | [12 empty] | 2025-06-18 | Online | [8 empty] | 15A GUNN
WMECO | Hadley | ESMAEX-04586 | 01035 | 15.2 | Battery | 18G4 | 2025-03-04 | 2025-03-10 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-04-10 |  |  |  | Expedited | [8 empty] | 2025-06-13 | Online | [7 empty] | 13.8 | 18G PODICK
WMECO | Pittsfield | ESMAEX-04470 | 01201 | 120 | Solar | 30B2 | 2025-01-28 | 2025-02-11 | 11 |  | 11 |  |  | 0 | [22 empty] | 2026-02-19 | [13 empty] | ISA Agreement | [8 empty] | 30B OSWALD
WMECO | Chesterfield | ESMAEX-04473 | 01012 | 30 | Solar & Battery | 19J5 | 2025-01-29 | 2025-02-26 | 21 |  | 21 |  |  | 0 | [22 empty] | 2025-03-05 | [13 empty] | Compliances Documents
WMECO | Westhampton | ESMAEX-04474 | 01027 | 15.2 | Solar | 15A3 | 2025-01-29 | 2025-02-25 | 20 |  | 20 |  |  | 0 | [22 empty] | 2025-03-21 | [12 empty] | 2025-06-17 | Online | [8 empty] | 15A GUNN
WMECO | Conway | ESMAEX-04480 | 01341 | 18.48 | Solar | 38A1 | 2025-02-13 | 2025-02-26 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-03-26 | [12 empty] | 2026-02-03 | Online | [8 empty] | 38A ASHFIELD
WMECO | Lee | ESMAEX-04484 | 01238 | 51.9 | Solar | 16B5 | 2025-02-04 | 2025-02-19 | 12 |  | 12 |  |  | 0 | [22 empty] | 2025-02-21 | [12 empty] | 2025-10-03 | Online | [8 empty] | 16B PLEASANT
WMECO | Hatfield | ESMAEX-04498 | 01038 | 9 | Solar | 18G5 | 2025-02-07 | 2025-03-21 | 31 |  | 31 |  |  | 0 | [35 empty] | 2025-10-09 | Online | [7 empty] | 9 | 18G PODICK
WMECO | Leyden | ESMAEX-04516 | 01301 | 23 | Solar & Battery | 22B7 | 2025-02-24 | 2025-03-10 | 11 |  | 11 |  |  | 0 | [22 empty] | 2025-04-29 |  |  |  | Expedited | [8 empty] | 2025-09-10 | Online | [7 empty] | 15 | 22B CUMBERLAND
WMECO | Westhampton | ESMAEX-04497 | 01027 | 10.56 | Solar | 15A3 | 2025-02-07 | 2025-02-20 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-03-31 | [12 empty] | 2025-07-17 | Online | [8 empty] | 15A GUNN
WMECO | Hadley | ESMAEX-04495 | 01035 | 450 | Solar | 18G5 | 2025-03-10 | 2025-04-16 | 28 |  | 28 |  |  | 0 | [22 empty] | 2025-07-10 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 18G PODICK
WMECO | Hinsdale | ESMAEX-04505 | 01235 | 4999 | Solar & Battery | 18C2 | 2025-02-10 | 2025-04-07 | 41 |  | 41 |  |  | 0 | [26 empty] | Complex | [9 empty] | Impact Study |  |  |  | Berkshire |  |  |  | 4999 | 18C BERKSHIRE
WMECO | Ludlow | ESMAEX-04504 | 01056 | 5.76 | Solar | 19S3 | 2025-02-10 | 2025-03-03 | 16 |  | 16 |  |  | 0 | [22 empty] | 2025-04-15 | [12 empty] | 2026-01-21 | Online | [8 empty] | 19S LUDLOW
WMECO | Amherst | ESMAEX-04513 | 01002 | 15.744 | Solar | 17K8 | 2025-02-12 | 2025-02-25 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-03-21 | [12 empty] | 2025-10-08 | Online | [8 empty] | 17K AMHERST
WMECO | Conway | ESMAEX-04521 | 01341 | 11.5 | Solar & Battery | 38A1 | 2025-02-14 | 2025-03-24 | 27 |  | 27 |  |  | 0 | [22 empty] | 2025-04-30 | [13 empty] | Construction Stage | [8 empty] | 38A ASHFIELD
WMECO | Amherst | ESMAEX-04554 | 01002 | 704 | Solar | 17K2 | 2026-01-14 | 2026-01-26 | 9 |  | 9 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 17K AMHERST
WMECO | Greenfield | ESMAEX-04532 | 01301 | 999.45 | Solar & Battery | 22B3 | 2025-03-27 | 2025-04-11 | 12 |  | 12 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [7 empty] | 999.45 | 22B CUMBERLAND
WMECO | Southampton | ESMAEX-04542 | 01073 | 20 | Solar | 15A1 | 2025-02-19 | 2025-03-10 | 14 |  | 14 |  |  | 0 | [22 empty] | 2025-04-10 | [12 empty] | 2025-08-26 | Online | [8 empty] | 15A GUNN
WMECO | Southampton | ESMAEX-04557 | 01073 | 10 | Solar | 15A1 | 2025-02-21 | 2025-03-10 | 12 |  | 12 |  |  | 0 | [22 empty] | 2025-04-10 | [12 empty] | 2025-09-18 | Online | [8 empty] | 15A GUNN
WMECO | Leverett | ESMAEX-04568 | 01054 | 11.4 | Solar | 18G7 | 2025-02-25 | 2025-03-03 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-03-21 |  |  |  | Expedited | [8 empty] | 2025-08-29 | Online | [8 empty] | 18G PODICK
WMECO | Pittsfield | ESMAEX-04562 | 01201 | 21.4 | Solar | 15E2 | 2025-03-03 | 2025-03-17 | 11 |  | 11 |  |  | 0 | [22 empty] | 2025-03-17 |  |  |  | Expedited | [8 empty] | 2025-06-17 | Online
WMECO | Amherst | ESMAEX-04600 | 01002 | 7.6 | Solar | 18G7 | 2025-03-06 | 2025-03-17 | 8 |  | 8 |  |  | 0 | [22 empty] | 2025-04-10 |  |  |  | Expedited | [8 empty] | 2025-06-17 | Online | [8 empty] | 18G PODICK
WMECO | West Springfield | ESMAEX-04628 | 01089 | 50 | Solar | 21N5 | 2025-03-14 | 2025-04-02 | 14 |  | 14 |  |  | 0 | [22 empty] | 2025-05-13 |  |  |  | Expedited | [8 empty] | 2025-12-08 | Online | [8 empty] | 21N PIPER
WMECO | Pittsfield | ESMAEX-04566 | 01201 | 4350 | Other | 15E2 | 2025-07-22 | 2025-08-13 | 17 |  | 17 |  |  | 0 | [26 empty] | Complex | [9 empty] | Technical Review | [7 empty] | 4350 | 15E PARTRIDGE
WMECO | Ludlow | ESMAEX-04570 | 01056 | 8.36 | Solar & Battery | 19S2 | 2025-02-26 | 2025-03-10 | 9 |  | 9 |  |  | 0 | [22 empty] | 2025-03-12 |  |  |  | Expedited | [8 empty] | 2025-08-26 | Online | [8 empty] | 19S LUDLOW
WMECO | Hadley | ESMAEX-04573 | 01035 | 11.5 | Solar & Battery | 18G4 | 2025-02-26 | 2025-03-10 | 9 |  | 9 |  |  | 0 | [22 empty] | 2025-04-14 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-04578 | 01109 | 400 | Solar | 5J18 | 2025-04-15 | 2025-05-02 | 14 |  | 14 |  |  | 0 | [22 empty] | 2025-10-23 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Pittsfield | ESMAEX-04602 | 01201 | 9.6 | Solar | 30B5 | 2025-03-05 | 2025-03-21 | 13 |  | 13 |  |  | 0 | [22 empty] | 2025-04-01 |  |  |  | Expedited | [8 empty] | 2025-07-17 | Online | [8 empty] | 30B OSWALD
WMECO | Longmeadow | ESMAEX-04617 | 01106 | 5.76 | Solar | 22H11 | 2025-03-11 | 2025-03-17 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-03-27 |  |  |  | Expedited | [8 empty] | 2025-06-12 | Online | [8 empty] | 22H FRANCONIA
WMECO | Hadley | ESMAEX-04633 | 01035 | 15.2 | Solar | 19B15 | 2025-03-14 | 2025-03-25 | 8 |  | 8 |  |  | 0 | [22 empty] | 2025-04-23 |  |  |  | Expedited | [8 empty] | 2025-08-05 | Online | [8 empty] | 19B MIDWAY
WMECO | Springfield | ESMAEX-04651 | 01129 | 990 | Solar | 27A7 | 2025-04-11 | 2025-04-24 | 10 |  | 10 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 27A ORCHARD
WMECO | Hadley | ESMAEX-04657 | 01035 | 990 | Solar | 17K5 | 2025-04-11 | 2025-04-24 | 10 |  | 10 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Supplemental Designer | [8 empty] | 17K AMHERST
WMECO | Longmeadow | ESMAEX-04661 | 01106 | 240 | Solar | 22H12 | 2025-04-11 | 2025-04-24 | 10 |  | 10 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 22H FRANCONIA
WMECO | Savoy | ESMAEX-04663 | 01256 | 5.76 | Solar | 18K4 | 2025-03-19 | 2025-04-09 | 16 |  | 16 |  |  | 0 | [22 empty] | 2025-04-10 |  |  |  | Expedited | [8 empty] | 2025-10-15 | Online |  |  |  | Dalton-Hinsdale |  |  |  |  | 18C BERKSHIRE
WMECO | Easthampton | ESMAEX-04670 | 01027 | 17.6 | Solar & Battery | 15A1 | 2025-03-19 | 2025-04-29 | 30 |  | 30 |  |  | 0 | [22 empty] | 2025-05-20 |  |  |  | Expedited | [8 empty] | 2026-02-27 | Online | [8 empty] | 15A GUNN
WMECO | New Ashford | ESMAEX-04682 | 01237 | 9.3 | Solar | 15E1 | 2025-03-24 | 2025-03-31 | 6 |  | 6 |  |  | 0 | [22 empty] | 2025-04-02 |  |  |  | Expedited | [8 empty] | 2026-01-12 | Online |  |  |  | Partridge |  |  |  |  | 15E PARTRIDGE
WMECO | Hadley | ESMAEX-04703 | 01035 | 22.8 | Solar | 18G5 | 2025-03-28 | 2025-04-15 | 13 |  | 13 |  |  | 0 | [22 empty] | 2025-05-15 |  |  |  | Expedited | [8 empty] | 2025-10-29 | Online | [8 empty] | 18G PODICK
WMECO | Deerfield | ESMAEX-04917 | 01342 | 95 | Solar | 22B1 | 2025-05-14 | 2025-07-01 | 35 |  | 35 |  |  | 0 | [22 empty] | 2025-10-01 |  |  |  | Expedited | [8 empty] | 2026-02-04 | Online | [8 empty] | 22B CUMBERLAND
WMECO | Leverett | ESMAEX-04764 | 01054 | 13.8 | Solar | 18G7 | 2025-04-08 | 2025-04-15 | 6 |  | 6 |  |  | 0 | [22 empty] | 2025-05-28 |  |  |  | Expedited | [8 empty] | 2025-09-18 | Online | [8 empty] | 18G PODICK
WMECO | Southampton | ESMAEX-04748 | 01073 | 996 | Solar | 15A1 | 2025-04-07 | 2025-04-24 | 14 |  | 14 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 15A GUNN
WMECO | South Deerfield | ESMAEX-04749 | 01373 | 15.2 | Solar | 22B1 | 2025-04-07 | 2025-04-15 | 7 |  | 7 |  |  | 0 | [22 empty] | 2025-05-13 |  |  |  | Expedited | [8 empty] | 2025-10-03 | Online | [8 empty] | 22B CUMBERLAND
WMECO | Buckland | ESMAEX-04755 | 01370 | 498 | Solar | 38A1 | 2025-04-23 | 2025-05-08 | 12 |  | 12 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 38A ASHFIELD
WMECO | Springfield | ESMAEX-05060 | 01105 | 161 | Solar | 21S12 | 2025-06-13 | 2025-07-02 | 14 |  | 14 |  |  | 0 | [22 empty] | 2026-02-12 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 21S CLINTON
WMECO | Sunderland | ESMAEX-04767 | 01375 | 7.6 | Solar | 18G6 | 2025-04-08 | 2025-04-15 | 6 |  | 6 |  |  | 0 | [22 empty] | 2025-05-19 |  |  |  | Expedited | [8 empty] | 2025-07-30 | Online | [8 empty] | 18G PODICK
WMECO | Southwick | ESMAEX-04769 | 01077 | 20 | Solar | 29A5 | 2025-04-08 | 2025-04-15 | 6 |  | 6 |  |  | 0 | [22 empty] | 2025-05-12 |  |  |  | Expedited | [9 empty] | Compliances Documents |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Northfield | ESMAEX-04863 | 01360 | 11.5 | Solar & Battery | 21B8 | 2025-05-01 | 2025-05-14 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-06-11 |  |  |  | Expedited | [8 empty] | 2025-09-02 | Online |  |  |  | Gill-Montague |  |  |  | 10 | 21B FRENCH KING
WMECO | Hinsdale | ESMAEX-04784 | 01235 | 4999 | Solar & Battery | 18C2 | 2025-04-10 | 2025-04-24 | 11 |  | 11 |  |  | 0 | [26 empty] | Complex | [9 empty] | On Hold |  |  |  | Berkshire |  |  |  | 4999 | 18C BERKSHIRE
WMECO | Lee | ESMAEX-04791 | 01238 | 23 | Solar & Battery | 16B5 | 2025-04-14 | 2025-04-23 | 8 |  | 8 |  |  | 0 | [22 empty] | 2025-06-02 |  |  |  | Expedited | [8 empty] | 2025-07-28 | Online | [7 empty] | 8 | 16B PLEASANT
WMECO | Easthampton | ESMAEX-04803 | 01027 | 11.5 | Other | 15A2 | 2025-04-17 | 2025-04-30 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-05-21 |  |  |  | Expedited | [8 empty] | 2025-09-05 | Online | [8 empty] | 15A GUNN
WMECO | Feeding Hills | ESMAEX-04833 | 01030 | 4.22 | Solar & Battery | 16C17 | 2025-05-01 | 2025-05-12 | 8 |  | 8 |  |  | 0 | [22 empty] | 2025-10-07 |  |  |  | Expedited | [8 empty] | 2025-11-07 | Online | [8 empty] | 16C AGAWAM
WMECO | Springfield | ESMAEX-04814 | 01105 | 99.9 | Solar |  | 2025-04-18 | 2025-06-30 | 52 |  | 52 |  |  | 0 | [22 empty] | 2025-09-24 |  |  |  | Expedited | [9 empty] | Compliances Documents | [7 empty] | 100
WMECO | West Springfield | ESMAEX-04815 | 01089 | 161 | Solar | 21N5 | 2025-04-18 | 2025-07-02 | 54 |  | 54 |  |  | 0 | [22 empty] | 2025-11-06 |  |  |  | Expedited | [9 empty] | Technical Review | [7 empty] | 161 | 21N PIPER
WMECO | Lanesborough | ESMAEX-04806 | 01237 | 5.76 | Solar | 30B5 | 2025-04-17 | 2025-05-01 | 11 |  | 11 |  |  | 0 | [22 empty] | 2025-05-05 |  |  |  | Expedited | [8 empty] | 2025-09-08 | Online | [8 empty] | 30B OSWALD
WMECO | Whately | ESMAEX-04816 | 01093 | 498 | Solar | 18G8 | 2025-05-12 | 2025-06-01 | 15 |  | 15 |  |  | 0 | [22 empty] | 2025-08-04 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 18G PODICK
WMECO | Granville | ESMAEX-04868 | 01034 | 7.6 | Solar | 29A5 | 2025-05-02 | 2025-05-20 | 13 |  | 13 |  |  | 0 | [22 empty] | 2025-05-23 |  |  |  | Expedited | [8 empty] | 2025-06-20 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Agawam | ESMAEX-04834 | 01001 | 15.18 | Solar | 30A1 | 2025-04-25 | 2025-05-14 | 14 |  | 14 |  |  | 0 | [22 empty] | 2025-05-21 |  |  |  | Expedited | [8 empty] | 2025-07-22 | Online | [8 empty] | 30A SILVER
WMECO | Otis | ESMAEX-04873 | 01253 | 16.2 | Solar | 19J4 | 2025-05-05 | 2025-06-11 | 28 |  | 28 |  |  | 0 | [22 empty] | 2025-06-24 |  |  |  | Expedited | [9 empty] | Online |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Hadley | ESMAEX-05100 | 01035 | 20 | Solar | 18G4 | 2025-06-24 | 2025-07-07 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-07-30 |  |  |  | Expedited | [8 empty] | 2026-01-21 | Online | [8 empty] | 18G PODICK
WMECO | Cummington | ESMAEX-04865 | 01026 | 24.42 | Solar | 18C1 | 2025-05-01 | 2025-05-14 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-06-10 |  |  |  | Expedited | [8 empty] | 2025-09-04 | Online |  |  |  | Plainfield |  |  |  |  | 18C BERKSHIRE
WMECO | Leverett | ESMAEX-04895 | 01054 | 15.2 | Solar | 18G7 | 2025-05-09 | 2025-05-22 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-06-12 |  |  |  | Expedited | [8 empty] | 2025-10-29 | Online | [8 empty] | 18G PODICK
WMECO | South Deerfield | ESMAEX-04957 | 01373 | 250 | Solar | 22B3 | 2025-05-20 | 2025-06-01 | 9 |  | 9 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 22B CUMBERLAND
WMECO | Amherst | ESMAEX-04900 | 01002 | 10 | Solar | 19B16 | 2025-05-12 | 2025-05-22 | 9 |  | 9 |  |  | 0 | [22 empty] | 2025-06-12 |  |  |  | Expedited | [9 empty] | Meter | [8 empty] | 19B MIDWAY
WMECO | Ashfield | ESMAEX-04941 | 01330 | 10 | Solar | 38A1 | 2025-05-16 | 2025-06-02 | 12 |  | 12 |  |  | 0 | [22 empty] | 2025-07-25 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 38A ASHFIELD
WMECO | West Springfield | ESMAEX-05066 | 01089 | 80 | Solar |  | 2025-06-16 | 2025-11-11 | 107 |  | 107 |  |  | 0 | [22 empty] | 2026-02-11 |  |  |  | Expedited | [9 empty] | ISA Agreement
WMECO | Longmeadow | ESMAEX-04880 | 01106 | 15.2 | Solar | 22H12 | 2025-05-06 | 2025-05-30 | 19 |  | 19 |  |  | 0 | [22 empty] | 2025-06-03 |  |  |  | Expedited | [8 empty] | 2025-10-10 | Online | [8 empty] | 22H FRANCONIA
WMECO | Amherst | ESMAEX-04891 | 01002 | 10 | Solar | 19B16 | 2025-05-09 | 2025-05-22 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-06-27 |  |  |  | Expedited | [8 empty] | 2025-09-18 | Online | [8 empty] | 19B MIDWAY
WMECO | Otis | ESMAEX-04888 | 01253 | 20 | Solar | 19J4 | 2025-05-06 | 2025-06-23 | 35 |  | 35 |  |  | 0 | [22 empty] | 2025-07-25 |  |  |  | Expedited | [8 empty] | 2026-01-21 | Online |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Greenfield | ESMAEX-04959 | 01301 | 22.8 | Solar | 22B4 | 2025-05-20 | 2025-06-10 | 16 |  | 16 |  |  | 0 | [22 empty] | 2025-06-30 |  |  |  | Expedited | [9 empty] | Construction Stage | [8 empty] | 22B CUMBERLAND
WMECO | Conway | ESMAEX-04906 | 01341 | 15 | Solar & Battery | 38A1 | 2025-05-13 | 2025-05-21 | 7 |  | 7 |  |  | 0 | [22 empty] | 2025-06-16 |  |  |  | Expedited | [8 empty] | 2025-10-07 | Online | [8 empty] | 38A ASHFIELD
WMECO | Bernardston | ESMAEX-04910 | 01337 | 15.2 | Solar | 21C1 | 2025-05-13 | 2025-06-10 | 21 |  | 21 |  |  | 0 | [22 empty] | 2025-07-07 |  |  |  | Expedited | [8 empty] | 2025-11-14 | Online |  |  |  | Gill-Montague |  |  |  |  | 21C MONTAGUE
WMECO | Pittsfield | ESMAEX-04946 | 01201 | 15.18 | Solar | 19A1 | 2025-05-18 | 2025-06-01 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-06-04 |  |  |  | Expedited | [8 empty] | 2025-07-25 | Online | [8 empty] | 19A DOREEN
WMECO | Hadley | ESMAEX-04936 | 01035 | 499 | Other | 17K5 | 2025-08-01 | 2025-08-13 | 9 |  | 9 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [7 empty] | 499 | 17K AMHERST
WMECO | Ashfield | ESMAEX-04962 | 01330 | 50 | Solar | 38A1 | 2025-05-20 | 2025-07-17 | 43 |  | 43 |  |  | 0 | [22 empty] | 2025-10-08 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 38A ASHFIELD
WMECO | Ashfield | ESMAEX-04963 | 01330 | 120 | Solar | 38A1 | 2025-05-20 | 2025-07-17 | 43 |  | 43 |  |  | 0 | [22 empty] | 2026-01-28 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 38A ASHFIELD
WMECO | Huntington | ESMAEX-05030 | 01050 | 10 | Solar | 19J5 | 2025-06-09 | 2025-06-26 | 14 |  | 14 |  |  | 0 | [22 empty] | 2025-07-17 |  |  |  | Expedited | [8 empty] | 2025-10-28 | Online
WMECO | West Springfield | ESMAEX-04964 | 01089 | 15.2 | Solar | 16C11 | 2025-05-21 | 2025-06-04 | 11 |  | 11 |  |  | 0 | [22 empty] | 2025-06-11 |  |  |  | Expedited | [8 empty] | 2025-09-24 | Online | [8 empty] | 16C AGAWAM
WMECO | Lee | ESMAEX-04965 | 01238 | 7.6 | Solar | 16B5 | 2025-05-21 | 2025-06-10 | 15 |  | 15 |  |  | 0 | [22 empty] | 2025-06-16 |  |  |  | Expedited | [8 empty] | 2025-09-18 | Online | [8 empty] | 16B PLEASANT
WMECO | Southampton | ESMAEX-04983 | 01073 | 19 | Solar | 15A1 | 2025-05-27 | 2025-06-05 | 8 |  | 8 |  |  | 0 | [22 empty] | 2025-06-26 |  |  |  | Expedited | [8 empty] | 2025-11-07 | Online | [8 empty] | 15A GUNN
WMECO | Granville | ESMAEX-05010 | 01034 | 498 | Solar | 29A5 | 2025-06-26 | 2025-07-11 | 12 |  | 12 |  |  | 0 | [26 empty] | Expedited | [9 empty] | On Hold |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Feeding Hills | ESMAEX-05012 | 01030 | 5.76 | Solar | 30A6 | 2025-06-04 | 2025-07-10 | 27 |  | 27 |  |  | 0 | [22 empty] | 2025-07-30 |  |  |  | Expedited | [8 empty] | 2025-10-31 | Online | [8 empty] | 30A SILVER
WMECO | Pittsfield | ESMAEX-05016 | 01201 | 5.76 | Solar | 30B5 | 2025-06-05 | 2025-06-23 | 13 |  | 13 |  |  | 0 | [22 empty] | 2025-09-11 |  |  |  | Expedited | [9 empty] | Construction Stage | [8 empty] | 30B OSWALD
WMECO | Southwick | ESMAEX-05043 | 01077 | 15.76 | Solar | 29A1 | 2025-06-10 | 2025-06-24 | 11 |  | 11 |  |  | 0 | [22 empty] | 2025-06-27 |  |  |  | Expedited | [8 empty] | 2025-12-11 | Online |  |  |  | Southwick |  |  |  |  | 29A SOUTHWICK
WMECO | Springfield | ESMAEX-05072 | 01104 | 250 | Solar | 5J9 | 2025-06-19 | 2025-06-30 | 8 |  | 8 |  |  | 0 | [22 empty] | 2025-10-30 |  |  |  | Expedited | [8 empty] | 2025-12-15 | Online | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Easthampton | ESMAEX-05056 | 01027 | 7.6 | Solar | 15A1 | 2025-06-13 | 2025-06-25 | 9 |  | 9 |  |  | 0 | [22 empty] | 2025-07-17 |  |  |  | Expedited | [8 empty] | 2026-01-12 | Online | [8 empty] | 15A GUNN
WMECO | Montgomery | ESMAEX-05069 | 01085 | 20 | Solar | 19J5 | 2025-06-16 | 2025-07-01 | 12 |  | 12 |  |  | 0 | [22 empty] | 2025-07-23 |  |  |  | Expedited | [9 empty] | Compliances Documents
WMECO | Hatfield | ESMAEX-05096 | 01038 | 10 | Solar | 18G5 | 2025-06-20 | 2025-07-03 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-07-28 |  |  |  | Expedited | [8 empty] | 2025-11-18 | Online | [8 empty] | 18G PODICK
WMECO | Hadley | ESMAEX-05106 | 01035 | 999 | Solar | 18G4 | 2025-09-26 | 2026-02-18 | 104 |  | 104 |  |  | 0 | [26 empty] | Standard | [9 empty] | Technical Review | [7 empty] | 999 | 18G PODICK
WMECO | Ludlow | ESMAEX-05166 | 01056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-08-07 |  |  |  | Expedited | [8 empty] | 2026-02-25 | Online | [8 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05168 | 01056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-08-07 |  |  |  | Expedited | [8 empty] | 2026-02-25 | Online | [8 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05169 | 01056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-09-04 |  |  |  | Expedited | [8 empty] | 2026-02-25 | Online | [8 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05170 | 01056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-09-04 |  |  |  | Expedited | [8 empty] | 2026-02-27 | Online | [8 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05171 | 01056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-09-04 |  |  |  | Expedited | [8 empty] | 2026-02-25 | Permission to Operate | [8 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05172 | 01056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-09-04 |  |  |  | Expedited | [8 empty] | 2026-02-25 | Online | [8 empty] | 27A ORCHARD
WMECO | Ludlow | ESMAEX-05173 | 01056 | 22.8 | Solar | 27A4 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-08-07 |  |  |  | Expedited | [8 empty] | 2026-02-25 | Online | [8 empty] | 27A ORCHARD
WMECO | Hadley | ESMAEX-05102 | 01035 | 499 | Solar | 19B15 | 2025-07-21 | 2025-08-13 | 18 |  | 18 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 19B MIDWAY
WMECO | Pittsfield | ESMAEX-05107 | 01201 | 11.5 | Solar & Battery | 30B7 | 2025-06-23 | 2025-07-10 | 14 |  | 14 |  |  | 0 | [22 empty] | 2025-07-31 |  |  |  | Expedited | [8 empty] | 2026-01-21 | Online | [8 empty] | 30B OSWALD
WMECO | Westhampton | ESMAEX-05132 | 01027 | 50 | Solar |  | 2025-06-26 | 2025-07-16 | 15 |  | 15 |  |  | 0 | [22 empty] | 2025-08-13 |  |  |  | Expedited | [9 empty] | Compliances Documents
WMECO | Lanesborough | ESMAEX-05162 | 01237 | 6.9 | Solar | 15E1 | 2025-07-07 | 2025-07-21 | 11 |  | 11 |  |  | 0 | [22 empty] | 2025-10-22 |  |  |  | Expedited | [8 empty] | 2026-02-25 | Permission to Operate
WMECO | Conway | ESMAEX-05133 | 01341 | 28.33 | Solar | 38A1 | 2025-06-26 | 2025-08-22 | 42 |  | 42 |  |  | 0 | [22 empty] | 2025-09-23 |  |  |  | Expedited | [8 empty] | 2025-12-17 | Online | [8 empty] | 38A ASHFIELD
WMECO | Longmeadow | ESMAEX-05136 | 01106 | 22.8 | Solar | 22H13 | 2025-06-27 | 2025-07-07 | 7 |  | 7 |  |  | 0 | [22 empty] | 2025-09-30 |  |  |  | Expedited | [8 empty] | 2026-02-12 | Online | [8 empty] | 22H FRANCONIA
WMECO | West Springfield | ESMAEX-05140 | 01089 | 7.6 | Solar | 16C11 | 2025-06-27 | 2025-07-18 | 16 |  | 16 |  |  | 0 | [22 empty] | 2025-09-04 |  |  |  | Expedited | [8 empty] | 2026-01-08 | Permission to Operate | [8 empty] | 16C AGAWAM
WMECO | Colrain | ESMAEX-05161 | 01340 | 15.2 | Solar | 29R2 | 2025-07-07 | 2025-07-18 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-08-25 |  |  |  | Expedited | [8 empty] | 2025-10-10 | Online | [8 empty] | 29R SHELBURNE
WMECO | Hadley | ESMAEX-05179 | 01035 | 7.6 | Solar | 17K5 | 2025-07-08 | 2025-07-14 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-08-13 |  |  |  | Expedited | [8 empty] | 2025-11-14 | Online | [8 empty] | 17K AMHERST
WMECO | Southwick | ESMAEX-05197 | 01077 | 3340 | Solar | 29A1 | 2025-09-24 | 2025-10-15 | 16 |  | 16 |  |  | 0 | [26 empty] | Expedited | [9 empty] | ISA Agreement | [8 empty] | 29A SOUTHWICK
WMECO | Turners Falls | ESMAEX-05407 | 01376 | 480 | Solar | 21C2 | 2025-09-02 | 2025-09-29 | 20 |  | 20 |  |  | 0 | [26 empty] | Expedited | [9 empty] | On Hold | [8 empty] | 21C MONTAGUE
WMECO | Russell | ESMAEX-05189 | 01071 | 15.2 | Solar | 19J2 | 2025-07-10 | 2025-07-14 | 3 |  | 3 |  |  | 0 | [22 empty] | 2025-07-28 |  |  |  | Expedited | [9 empty] | Compliances Documents |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Pittsfield | ESMAEX-05194 | 01201 | 10.89 | Solar | 30B7 | 2025-07-11 | 2025-07-24 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-07-30 |  |  |  | Expedited | [8 empty] | 2025-09-12 | Online | [8 empty] | 30B OSWALD
WMECO | Huntington | ESMAEX-05195 | 01050 | 20.736 | Solar | 19J5 | 2025-07-11 | 2025-07-22 | 8 |  | 8 |  |  | 0 | [22 empty] | 2025-09-17 |  |  |  | Expedited | [8 empty] | 2025-11-20 | Online
WMECO | Amherst | ESMAEX-05190 | 01002 | 5.76 | Solar | 17K1 | 2025-07-10 | 2025-07-22 | 9 |  | 9 |  |  | 0 | [22 empty] | 2025-10-13 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 17K AMHERST
WMECO | Pittsfield | ESMAEX-05198 | 01201 | 400 | Solar | 19A8 | 2025-08-08 | 2025-08-22 | 11 |  | 11 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Supplemental Designer | [8 empty] | 19A DOREEN
WMECO | Agawam | ESMAEX-05206 | 01001 | 7.6 | Solar | 30A3 | 2025-07-15 | 2025-07-24 | 8 |  | 8 |  |  | 0 | [22 empty] | 2025-08-06 |  |  |  | Expedited | [8 empty] | 2025-09-10 | Online | [8 empty] | 30A SILVER
WMECO | Pelham | ESMAEX-05282 | 01002 | 37.3 | Solar | 17K2 | 2025-08-05 | 2025-09-08 | 25 |  | 25 |  |  | 0 | [22 empty] | 2025-10-02 |  |  |  | Expedited | [8 empty] | 2026-01-13 | Online | [8 empty] | 17K AMHERST
WMECO | Hadley | ESMAEX-05235 | 01035 | 5.76 | Solar | 18G4 | 2025-07-28 | 2025-07-29 | 2 |  | 2 |  |  | 0 | [22 empty] | 2025-11-05 |  |  |  | Expedited | [8 empty] | 2026-02-19 | Online | [8 empty] | 18G PODICK
WMECO | South Deerfield | ESMAEX-05214 | 01373 | 19 | Solar | 22B3 | 2025-07-18 | 2025-07-18 | 1 |  | 1 |  |  | 0 | [22 empty] | 2025-07-21 |  |  |  | Expedited | [8 empty] | 2025-09-05 | Online | [7 empty] | 19 | 22B CUMBERLAND
WMECO | Amherst | ESMAEX-05221 | 01002 | 19.032 | Solar | 18G7 | 2025-07-22 | 2025-07-29 | 6 |  | 6 |  |  | 0 | [22 empty] | 2025-08-14 |  |  |  | Expedited | [8 empty] | 2025-11-20 | Online | [8 empty] | 18G PODICK
WMECO | Granville | ESMAEX-05260 | 01034 | 11.5 | Other | 29A5 | 2025-07-31 | 2025-08-25 | 18 |  | 18 |  |  | 0 | [22 empty] | 2025-09-18 |  |  |  | Expedited | [9 empty] | Compliances Documents | [7 empty] | 0 | 29A SOUTHWICK
WMECO | Feeding Hills | ESMAEX-05243 | 01030 | 7.6 | Solar | 16C17 | 2025-07-29 | 2025-07-31 | 3 |  | 3 |  |  | 0 | [22 empty] | 2026-01-13 |  |  |  | Expedited | [9 empty] | Construction Stage | [8 empty] | 16C AGAWAM
WMECO | Hadley | ESMAEX-05251 | 01035 | 7.6 | Solar | 19B15 | 2025-07-29 | 2025-08-04 | 5 |  | 5 |  |  | 0 | [22 empty] | 2025-08-14 |  |  |  | Expedited | [8 empty] | 2026-01-27 | Online | [8 empty] | 19B MIDWAY
WMECO | Ludlow | ESMAEX-05272 | 01056 | 4988 | Solar & Battery | 19S3 | 2025-08-04 | 2025-08-22 | 15 |  | 15 |  |  | 0 | [22 empty] | 2026-02-18 |  |  |  | Expedited | [9 empty] | ISA Agreement | [7 empty] | 4988 | 19S LUDLOW
WMECO | Amherst | ESMAEX-05291 | 01002 | 15.2 | Solar | 17K8 | 2025-08-07 | 2025-08-20 | 10 |  | 10 |  |  | 0 | [22 empty] | 2025-09-17 |  |  |  | Expedited | [8 empty] | 2025-12-01 | Online | [8 empty] | 17K AMHERST
WMECO | Worthington | ESMAEX-05332 | 01098 | 7.6 | Solar & Battery | 18C2 | 2025-08-18 | 2025-08-26 | 7 |  | 7 |  |  | 0 | [22 empty] | 2025-09-26 |  |  |  | Expedited | [8 empty] | 2026-01-27 | Online | [8 empty] | 18C BERKSHIRE
WMECO | Plainfield | ESMAEX-05280 | 01070 | 4950 | Other | 18K3 | 2025-10-02 | 2025-10-21 | 14 |  | 14 |  |  | 0 | [26 empty] | Complex | [9 empty] | Technical Review | [8 empty] | 18K PLAINFIELD
WMECO | Greenfield | ESMAEX-05511 | 01301 | 67.3 | Solar | 22B8 | 2025-09-29 | 2025-10-08 | 8 |  | 8 |  |  | 0 | [22 empty] | 2026-02-10 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 22B CUMBERLAND
WMECO | Southampton | ESMAEX-05297 | 01073 | 11.4 | Solar | 15A1 | 2025-08-08 | 2025-09-04 | 20 |  | 20 |  |  | 0 | [22 empty] | 2025-10-01 |  |  |  | Expedited | [8 empty] | 2026-02-09 | Online | [8 empty] | 15A GUNN
WMECO | Whately | ESMAEX-05315 | 01093 | 250 | Solar | 18G8 | 2025-10-08 | 2025-10-21 | 10 |  | 10 |  |  | 0 | [22 empty] | 2026-03-02 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 18G PODICK
WMECO | Otis | ESMAEX-05411 | 01253 | 25 | Solar | 19J4 | 2025-09-02 | 2025-09-16 | 11 |  | 11 |  |  | 0 | [22 empty] | 2025-10-08 |  |  |  | Expedited | [9 empty] | Compliances Documents |  |  |  | Blandford |  |  |  | 20 | 19J BLANDFORD
WMECO | West Springfield | ESMAEX-05357 | 01089 | 5.376 | Battery | 16C11 | 2025-08-22 | 2025-09-18 | 20 |  | 20 |  |  | 0 | [22 empty] | 2025-09-29 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 16C AGAWAM
WMECO | 0 | ESMAEX-05340 | 01301 | 240 | Solar | 22B7 | 2025-08-27 | 2025-09-12 | 13 |  | 13 |  |  | 0 | [22 empty] | 2026-02-04 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-05510 | 01105 | 50 | Solar | 8C15 | 2025-09-29 | 2025-10-07 | 7 |  | 7 |  |  | 0 | [22 empty] | 2026-01-12 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 8C WEST SPRINGFIELD
WMECO | Pittsfield | ESMAEX-05361 | 01201 | 15.2 | Solar | 19A7 | 2025-08-25 | 2025-08-26 | 2 |  | 2 |  |  | 0 | [22 empty] | 2025-10-28 |  |  |  | Expedited | [9 empty] | Construction Stage | [8 empty] | 19A DOREEN
WMECO | Chicopee | ESMAEX-05362 | 01013 | 960 | Solar | 21N7 | 2025-10-31 | 2025-11-11 | 8 |  | 8 |  |  | 0 | [26 empty] | Standard | [9 empty] | Technical Review | [8 empty] | 21N PIPER
WMECO | Agawam | ESMAEX-05364 | 01001 | 480 | Solar | 30A3 | 2025-10-03 | 2025-10-15 | 9 |  | 9 |  |  | 0 | [22 empty] | 2026-02-17 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 30A SILVER
WMECO | Bernardston | ESMAEX-05375 | 01337 | 499 | Solar | 21C1 | 2025-09-22 | 2025-10-21 | 22 |  | 22 |  |  | 0 | [26 empty] | Expedited | [9 empty] | On Hold | [8 empty] | 21C MONTAGUE
WMECO | Sunderland | ESMAEX-05409 | 01375 | 11.5 | Other | 18G6 | 2025-09-02 | 2025-09-16 | 11 |  | 11 |  |  | 0 | [22 empty] | 2025-10-09 |  |  |  | Expedited | [9 empty] | Compliances Documents | [7 empty] | 20 | 18G PODICK
WMECO | Greenfield | ESMAEX-05464 | 01301 | 150 | Solar | 22B6 | 2025-09-16 | 2025-11-11 | 41 |  | 41 |  |  | 0 | [22 empty] | 2026-02-11 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 22B CUMBERLAND
WMECO | Middlefield | ESMAEX-05454 | 01243 | 22.8 | Solar | 18C2 | 2025-09-15 | 2025-09-22 | 6 |  | 6 |  |  | 0 | [22 empty] | 2025-10-23 |  |  |  | Expedited | [8 empty] | 2025-12-03 | Online | [8 empty] | 18C BERKSHIRE
WMECO | Easthampton | ESMAEX-05559 | 01027 | 50 | Solar | 15A3 | 2025-10-09 | 2025-10-21 | 9 |  | 9 |  |  | 0 | [22 empty] | 2026-02-05 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 15A GUNN
WMECO | Longmeadow | ESMAEX-05468 | 01106 | 15.2 | Solar | 22H18 | 2025-09-17 | 2025-09-29 | 9 |  | 9 |  |  | 0 | [22 empty] | 2025-11-20 |  |  |  | Expedited | [8 empty] | 2026-01-09 | Online | [8 empty] | 22H FRANCONIA
WMECO | Pittsfield | ESMAEX-05474 | 01201 | 480 | Solar | 15E2 | 2025-10-15 | 2025-10-24 | 8 |  | 8 |  |  | 0 | [22 empty] | 2025-12-10 |  |  |  | Expedited | [9 empty] | Supplemental Designer | [8 empty] | 15E PARTRIDGE
WMECO | Southwick | ESMAEX-05487 | 01077 | 450 | Solar | 29A1 | 2025-10-24 | 2025-11-11 | 13 |  | 13 |  |  | 0 | [26 empty] | Expedited | [9 empty] | On Hold | [8 empty] | 29A SOUTHWICK
WMECO | Lanesborough | ESMAEX-05493 | 01237 | 23 | Other | 30B5 | 2025-09-22 | 2025-10-21 | 22 |  | 22 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review | [8 empty] | 30B OSWALD
WMECO | West Springfield | ESMAEX-05513 | 01089 | 30 | Solar |  | 2025-09-25 | 2025-10-16 | 16 |  | 16 |  |  | 0 | [22 empty] | 2026-02-05 |  |  |  | Expedited | [9 empty] | ISA Agreement
WMECO | Southwick | ESMAEX-05501 | 01077 | 160 | Solar | 29A1 | 2025-09-23 | 2025-10-08 | 12 |  | 12 |  |  | 0 | [26 empty] | Expedited | [9 empty] | On Hold | [8 empty] | 29A SOUTHWICK
WMECO | Easthampton | ESMAEX-05523 | 01027 | 11.5 | Solar & Battery | 15A1 | 2025-09-29 | 2025-10-07 | 7 |  | 7 |  |  | 0 | [22 empty] | 2025-11-07 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 15A GUNN
WMECO | Lanesborough | ESMAEX-05508 | 01237 | 6 | Solar | 15E1 | 2025-09-24 | 2025-10-14 | 15 |  | 15 |  |  | 0 | [22 empty] | 2026-01-12 |  |  |  | Expedited | [9 empty] | Construction Stage
WMECO | Easthampton | ESMAEX-05524 | 01027 | 11.5 | Solar & Battery | 15A5 | 2025-09-29 | 2025-10-02 | 4 |  | 4 |  |  | 0 | [22 empty] | 2025-11-06 |  |  |  | Expedited | [8 empty] | 2026-01-27 | Online | [8 empty] | 15A GUNN
WMECO | Hatfield | ESMAEX-05525 | 01038 | 19.8 | Solar |  | 2025-09-29 | 2025-10-07 | 7 |  | 7 |  |  | 0 | [22 empty] | 2025-10-15 |  |  |  | Expedited | [8 empty] | 2025-12-31 | Online
WMECO | Ludlow | ESMAEX-05526 | 01056 | 360 | Solar | 27A5 | 2025-11-11 | 2025-11-21 | 9 |  | 9 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Supplemental Designer | [8 empty] | 27A ORCHARD
WMECO | Amherst | ESMAEX-05535 | 01002 | 240 | Other | 17K3 | 2025-10-02 | 2025-10-15 | 10 |  | 10 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 17K AMHERST
WMECO | Lee | ESMAEX-05536 | 01238 | 250 | Solar | 16B5 | 2025-10-03 | 2025-10-14 | 8 |  | 8 |  |  | 0 | [26 empty] | Expedited | [9 empty] | ISA Agreement | [7 empty] | 249 | 16B PLEASANT
WMECO | Agawam | ESMAEX-05539 | 01001 | 70 | Solar | 30A3 | 2025-10-03 | 2025-10-15 | 9 |  | 9 |  |  | 0 | [22 empty] | 2025-11-06 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 30A SILVER
WMECO | Pelham | ESMAEX-05613 | 01002 | 18.666 | Solar | 17K2 | 2025-10-23 | 2025-11-13 | 16 |  | 16 |  |  | 0 | [22 empty] | 2025-12-04 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 17K AMHERST
WMECO | Becket | ESMAEX-05552 | 01223 | 4999 | Solar | 16B1 | 2025-10-06 | 2025-10-24 | 15 |  | 15 |  |  | 0 | [26 empty] | Complex | [9 empty] | Technical Review | [7 empty] | 4999 | 16B PLEASANT
WMECO | Otis | ESMAEX-05624 | 01253 | 34.52 | Solar & Battery | 19J4 | 2025-10-23 | 2025-11-05 | 10 |  | 10 |  |  | 0 | [22 empty] | 2026-01-27 |  |  |  | Expedited | [9 empty] | Supplemental Review |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Feeding Hills | ESMAEX-05769 | 01030 | 17.48 | Solar | 30A1 | 2025-11-24 | 2025-12-01 | 6 |  | 6 |  |  | 0 | [22 empty] | 2026-01-05 |  |  |  | Expedited | [9 empty] | Meter | [8 empty] | 30A SILVER
WMECO | South Deerfield | ESMAEX-05590 | 01373 | 17.16 | Solar | 18G3 | 2025-10-15 | 2025-10-22 | 6 |  | 6 |  |  | 0 | [22 empty] | 2025-12-17 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 18G PODICK
WMECO | Southampton | ESMAEX-05731 | 01073 | 2988 | Solar & Battery | 15A1 | 2025-11-11 | 2025-11-17 | 5 |  | 5 |  |  | 0 | [26 empty] | Complex | [9 empty] | Technical Review | [8 empty] | 15A GUNN
WMECO | Greenfield | ESMAEX-05596 | 01301 | 50 | Solar |  | 2025-10-16 | 2025-10-28 | 9 |  | 9 |  |  | 0 | [22 empty] | 2025-11-07 |  |  |  | Expedited | [9 empty] | Compliances Documents
WMECO | Deerfield | ESMAEX-05662 | 01342 | 80 | Solar | 22B3 | 2025-10-31 | 2025-11-17 | 12 |  | 12 |  |  | 0 | [22 empty] | 2026-02-11 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 22B CUMBERLAND
WMECO | Pittsfield | ESMAEX-05603 | 01201 | 15.2 | Solar | 19A1 | 2025-10-20 | 2025-10-31 | 10 |  | 10 |  |  | 0 | [22 empty] | 2026-01-23 |  |  |  | Expedited | [9 empty] | Construction Stage | [8 empty] | 19A DOREEN
WMECO | Turners Falls | ESMAEX-05623 | 01376 | 4950 | Other | 21C2 | 2026-01-21 | 2026-02-05 | 12 |  | 12 |  |  | 0 | [26 empty] | Complex | [9 empty] | Technical Review | [7 empty] | 4950 | 21C MONTAGUE
WMECO | Pittsfield | ESMAEX-05629 | 01201 | 5.76 | Solar | 30B1 | 2025-10-24 | 2025-10-28 | 3 |  | 3 |  |  | 0 | [22 empty] | 2026-01-13 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 30B OSWALD
WMECO | 0 | ESMAEX-05636 | 02137 | 499 | Solar | 15E2 | 2025-11-19 | 2025-12-03 | 11 |  | 11 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Supplemental Designer | [7 empty] | 499 | 15E PARTRIDGE
WMECO | Sandisfield | ESMAEX-05694 | 01255 | 7.59 | Solar & Battery | 19J4 | 2025-11-04 | 2025-11-12 | 7 |  | 7 |  |  | 0 | [22 empty] | 2025-12-05 |  |  |  | Expedited | [8 empty] | 2026-02-24 | Online |  |  |  | Blandford |  |  |  |  | 19J BLANDFORD
WMECO | Westhampton | ESMAEX-05689 | 01770 | 499 | Solar | 15A3 | 2025-11-03 | 2025-11-12 | 8 |  | 8 |  |  | 0 | [26 empty] | Expedited | [9 empty] | ISA Agreement | [8 empty] | 15A GUNN
WMECO | Greenfield | ESMAEX-05737 | 01301 | 17.16 | Solar | 22B2 | 2025-11-12 | 2025-12-30 | 35 |  | 35 |  |  | 0 | [22 empty] | 2026-01-22 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 22B CUMBERLAND
WMECO | Pittsfield | ESMAEX-05699 | 01201 | 11.5 | Other | 30B3 | 2025-11-05 | 2025-12-02 | 20 |  | 20 |  |  | 0 | [22 empty] | 2026-01-13 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 30B OSWALD
WMECO | Springfield | ESMAEX-05711 | 01105 | 15.2 | Solar & Battery | 21S4 | 2025-11-07 | 2025-11-20 | 10 |  | 10 |  |  | 0 | [22 empty] | 2026-03-02 |  |  |  | Expedited | [9 empty] | Construction Stage | [7 empty] | 20 | 21S CLINTON
WMECO | Springfield | ESMAEX-05724 | 01104 | 10 | Solar | 5J16 | 2025-11-10 | 2025-11-13 | 4 |  | 4 |  |  | 0 | [22 empty] | 2026-01-28 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 5J EAST SPRINGFIELD
WMECO | Amherst | ESMAEX-05823 | 01002 | 999 | Solar |  | 2025-12-10 |  | -32824 |  |  |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review
WMECO | Hadley | ESMAEX-05721 | 01035 | 250 | Solar | 17K1 | 2025-12-04 | 2025-12-17 | 10 |  | 10 |  |  | 0 | [22 empty] | 2026-03-05 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 17K AMHERST
WMECO | Hadley | ESMAEX-05722 | 01035 | 999 | Solar | 17K1 | 2025-12-04 | 2025-12-17 | 10 |  | 10 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [7 empty] | 999 | 17K AMHERST
WMECO | Easthampton | ESMAEX-05734 | 01027 | 5.7 | Solar | 15A5 | 2025-11-11 | 2025-12-01 | 15 |  | 15 |  |  | 0 | [22 empty] | 2025-12-04 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 15A GUNN
WMECO | Easthampton | ESMAEX-05740 | 01027 | 15.2 | Solar | 15A5 | 2025-11-13 | 2025-12-01 | 13 |  | 13 |  |  | 0 | [22 empty] | 2025-12-04 |  |  |  | Expedited | [8 empty] | 2026-02-24 | Online | [8 empty] | 15A GUNN
WMECO | Pittsfield | ESMAEX-05745 | 01201 | 3.8 | Solar & Battery | 15E2 | 2025-11-17 | 2025-12-03 | 13 |  | 13 |  |  | 0 | [22 empty] | 2026-01-06 |  |  |  | Expedited | [9 empty] | Compliances Documents
WMECO | Lanesborough | ESMAEX-05849 | 01237 | 13.36 | Solar & Battery | 15E1 | 2025-12-18 | 2026-01-09 | 17 |  | 17 |  |  | 0 | [22 empty] | 2026-01-30 |  |  |  | Expedited | [9 empty] | Compliances Documents
WMECO | Ashfield | ESMAEX-05754 | 01330 | 499 | Solar | 38A1 | 2025-11-18 | 2025-12-03 | 12 |  | 12 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 38A ASHFIELD
WMECO | Longmeadow | ESMAEX-05758 | 01106 | 7.2 | Solar | 22H11 | 2025-11-19 | 2025-12-01 | 9 |  | 9 |  |  | 0 | [26 empty] | Expedited | [9 empty] | ISA Agreement | [8 empty] | 22H FRANCONIA
WMECO | Pittsfield | ESMAEX-05761 | 01201 | 3.8 | Solar & Battery | 30B7 | 2025-11-19 | 2025-12-03 | 11 |  | 11 |  |  | 0 | [22 empty] | 2026-03-05 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 30B OSWALD
WMECO | West Springfield | ESMAEX-05785 | 01089 | 140 | Solar | 21N9 | 2025-12-02 | 2025-12-05 | 4 |  | 4 |  |  | 0 | [22 empty] | 2026-02-02 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 21N PIPER
WMECO | Hinsdale | ESMAEX-05763 | 01235 | 15.2 | Solar | 18C2 | 2025-11-20 | 2026-03-03 | 74 |  | 74 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 18C BERKSHIRE
WMECO | Hadley | ESMAEX-05820 | 01035 | 999 | Solar | 19B15 | 2026-01-29 | 2026-02-18 | 15 |  | 15 |  |  | 0 | [26 empty] | Standard | [9 empty] | Technical Review | [8 empty] | 19B MIDWAY
WMECO | Pelham | ESMAEX-05789 | 01002 | 16 | Other | 17K2 | 2025-12-02 | 2026-03-09 | 70 |  | 70 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 17K AMHERST
WMECO | Springfield | ESMAEX-05780 | 01108 | 5.76 | Solar & Battery | 22H15 | 2025-11-29 | 2025-12-11 | 9 |  | 9 |  |  | 0 | [26 empty] | Expedited | [9 empty] | ISA Agreement | [8 empty] | 22H FRANCONIA
WMECO | 0 | ESMAEX-05787 | 01001 | 4998 | Other | 30A3 | 2025-12-02 | 2026-01-29 | 43 |  | 43 |  |  | 0 | [26 empty] | Complex | [9 empty] | Technical Review | [8 empty] | 30A SILVER
WMECO | Springfield | ESMAEX-05784 | 01128 | 15.2 | Solar | 20A21 | 2025-12-01 | 2025-12-09 | 7 |  | 7 |  |  | 0 | [22 empty] | 2026-02-02 |  |  |  | Expedited | [9 empty] | Construction Stage | [8 empty] | 20A BRECKWOOD
WMECO | Deerfield | ESMAEX-05790 | 01342 | 12 | Solar & Battery | 22B7 | 2025-12-03 | 2025-12-16 | 10 |  | 10 |  |  | 0 | [22 empty] | 2026-01-22 |  |  |  | Expedited | [9 empty] | ISA Agreement | [7 empty] | 17.5 | 22B CUMBERLAND
WMECO | Springfield | ESMAEX-05824 | 01107 | 11.5 | Solar & Battery | 21S6 | 2025-12-10 | 2025-12-23 | 10 |  | 10 |  |  | 0 | [22 empty] | 2026-01-13 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 21S CLINTON
WMECO | Peru | ESMAEX-05803 | 01235 | 9.882 | Solar & Battery | 18C2 | 2025-12-05 | 2025-12-16 | 8 |  | 8 |  |  | 0 | [26 empty] | Expedited | [9 empty] | On Hold | [8 empty] | 18C BERKSHIRE
WMECO | Springfield | ESMAEX-05808 | 01128 | 966 | Solar | 20A34 | 2026-01-09 | 2026-01-22 | 10 |  | 10 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 20A BRECKWOOD
WMECO | Agawam | ESMAEX-05810 | 01001 | 480 | Solar | 30A3 | 2026-01-20 | 2026-01-29 | 8 |  | 8 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 30A SILVER
WMECO | South Deerfield | ESMAEX-05818 | 01373 | 5.76 | Solar | 18G6 | 2025-12-09 | 2026-01-21 | 32 |  | 32 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review | [8 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-05821 | 01109 | 11.5 | Solar & Battery | 20A32 | 2025-12-10 | 2026-01-05 | 19 |  | 19 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review | [8 empty] | 20A BRECKWOOD
WMECO | Feeding Hills | ESMAEX-05822 | 01030 | 11.5 | Solar & Battery | 30A1 | 2025-12-10 | 2025-12-23 | 10 |  | 10 |  |  | 0 | [22 empty] | 2026-01-30 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 30A SILVER
WMECO | West Springfield | ESMAEX-05888 | 01089 | 3.8 | Solar & Battery |  | 2025-12-29 | 2026-01-14 | 13 |  | 13 |  |  | 0 | [22 empty] | 2026-02-04 |  |  |  | Expedited | [9 empty] | Compliances Documents | [7 empty] | 13
WMECO | West Springfield | ESMAEX-05842 | 01089 | 16.512 | Solar | 21N4 | 2025-12-16 | 2026-01-05 | 15 |  | 15 |  |  | 0 | [26 empty] | Expedited | [9 empty] | ISA Agreement | [8 empty] | 21N PIPER
WMECO | New Ashford | ESMAEX-05840 | 01237 | 20 | Solar | 1.50E+02 | 2025-12-15 | 2026-01-26 | 31 |  | 31 |  |  | 0 | [22 empty] | 2026-01-30 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 15E PARTRIDGE
WMECO | Ludlow | ESMAEX-05832 | 01056 | 15.2 | Solar | 19S1 | 2025-12-11 | 2025-12-23 | 9 |  | 9 |  |  | 0 | [22 empty] | 2026-01-06 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 19S LUDLOW
WMECO | Northfield | ESMAEX-05833 | 01360 | 22.96 | Solar | 21B8 | 2025-12-12 |  | -32826 |  |  |  |  | 0 | [26 empty] | Expedited | [9 empty] | On Hold | [8 empty] | 21B FRENCH KING
WMECO | Pelham | ESMAEX-05845 | 01002 | 9.984 | Solar | 17K2 | 2025-12-17 | 2025-12-30 | 10 |  | 10 |  |  | 0 | [22 empty] | 2026-01-28 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 17K AMHERST
WMECO | Colrain | ESMAEX-05878 | 01340 | 249 | Solar | 29R2 | 2025-12-23 | 2026-01-07 | 12 |  | 12 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 29R SHELBURNE
WMECO | Colrain | ESMAEX-05879 | 01340 | 249 | Solar | 29R2 | 2025-12-23 | 2026-01-07 | 12 |  | 12 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 29R SHELBURNE
WMECO | Westhampton | ESMAEX-05900 | 01027 | 75 | Solar | 15A3 | 2026-01-05 | 2026-01-22 | 14 |  | 14 |  |  | 0 | [22 empty] | 2026-02-18 |  |  |  | Expedited | [9 empty] | ISA Agreement | [8 empty] | 15A GUNN
WMECO | Conway | ESMAEX-05906 | 01341 | 15.2 | Solar | 38A1 | 2026-01-06 | 2026-01-14 | 7 |  | 7 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review | [8 empty] | 38A ASHFIELD
WMECO | Hadley | ESMAEX-05909 | 01035 | 23 | Solar & Battery | 19B15 | 2026-01-07 | 2026-01-21 | 11 |  | 11 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Compliances Documents | [8 empty] | 19B MIDWAY
WMECO | Leyden | ESMAEX-05917 | 01337 | 7.6 | Solar | 22B7 | 2026-01-09 | 2026-01-21 | 9 |  | 9 |  |  | 0 | [22 empty] | 2026-02-11 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 22B CUMBERLAND
WMECO | Amherst | ESMAEX-05943 | 01002 | 80 | Solar | 17K5 | 2026-01-16 | 2026-01-27 | 8 |  | 8 |  |  | 0 | [22 empty] | 2026-02-05 |  |  |  | Expedited | [9 empty] | ISA Agreement | [7 empty] | -100 | 17K AMHERST
WMECO | Springfield | ESMAEX-05920 | 01104 | 5.76 | Solar & Battery | 5J12 | 2026-01-12 | 2026-01-22 | 9 |  | 9 |  |  | 0 | [22 empty] | 2026-02-03 |  |  |  | Expedited | [9 empty] | Compliances Documents | [7 empty] | 10 | 5J EAST SPRINGFIELD
WMECO | Greenfield | ESMAEX-05954 | 01301 | 22.8 | Solar |  | 2026-01-22 | 2026-02-02 | 8 |  | 8 |  |  | 0 | [22 empty] | 2026-02-12 |  |  |  | Expedited | [9 empty] | Compliances Documents
WMECO | Amherst | ESMAEX-05946 | 01002 | 15.2 | Solar | 17K8 | 2026-01-20 | 2026-01-28 | 7 |  | 7 |  |  | 0 | [22 empty] | 2026-02-04 |  |  |  | Expedited | [9 empty] | Compliances Documents | [8 empty] | 17K AMHERST
WMECO | Ludlow | ESMAEX-05948 | 01056 | 15.2 | Solar | 27A6 | 2026-01-20 | 2026-01-27 | 6 |  | 6 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review | [8 empty] | 27A ORCHARD
WMECO | Huntington | ESMAEX-05951 | 01050 | 18.43 | Solar | 19J5 | 2026-01-20 | 2026-02-04 | 12 |  | 12 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review
WMECO | Richmond | ESMAEX-05959 | 01254 | 7.6 | Solar | 30B2 | 2026-01-23 |  | -32856 |  |  |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review | [8 empty] | 30B OSWALD
WMECO | Savoy | ESMAEX-05961 | 01256 | 15.2 | Solar | 18K4 | 2026-01-26 | 2026-02-02 | 6 |  | 6 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review
WMECO | Pittsfield | ESMAEX-05965 | 01201 | 30 | Solar & Battery | 30B5 | 2026-01-27 |  | -32858 |  |  |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review | [7 empty] | 20 | 30B OSWALD
WMECO | Bernardston | ESMAEX-05975 | 01337 | 22.8 | Solar | 21C1 | 2026-02-02 | 2026-02-09 | 6 |  | 6 |  |  | 0 | [26 empty] | Expedited | [9 empty] | On Hold | [8 empty] | 21C MONTAGUE
WMECO | Springfield | ESMAEX-05970 | 01128 | 23 | Solar & Battery | 20A34 | 2026-01-28 | 2026-02-19 | 17 |  | 17 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review | [7 empty] | 15 | 20A BRECKWOOD
WMECO | Sunderland | ESMAEX-05988 | 01375 | 5.76 | Solar | 18G6 | 2026-02-04 | 2026-02-12 | 7 |  | 7 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 18G PODICK
WMECO | Springfield | ESMAEX-05993 | 01108 | 23.42 | Solar | 21S5 | 2026-02-06 | 2026-02-13 | 6 |  | 6 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Supplemental Designer | [8 empty] | 21S CLINTON
WMECO | Longmeadow | ESMAEX-05999 | 01106 | 10 | Solar | 22H17 | 2026-02-10 | 2026-02-20 | 9 |  | 9 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 22H FRANCONIA
WMECO | Millers Falls | ESMAEX-06000 | 01349 | 7.6 | Solar | 21C8 | 2026-02-10 |  | -32868 |  |  |  |  | 0 | [26 empty] | Expedited | [9 empty] | On Hold | [8 empty] | 21C MONTAGUE
WMECO | Agawam | ESMAEX-06008 | 01001 | 100 | Solar | 30A1 | 2026-02-11 |  | -32869 |  |  |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review | [8 empty] | 30A SILVER
WMECO | Agawam | ESMAEX-06011 | 01001 | 100 | Solar | 16C16 | 2026-02-13 | 2026-02-27 | 11 |  | 11 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 16C AGAWAM
WMECO | Agawam | ESMAEX-06018 | 01001 | 150 | Solar | 16C18 | 2026-02-18 | 2026-02-27 | 8 |  | 8 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 16C AGAWAM
WMECO | Amherst | ESMAEX-06022 | 01002 | 19.96 | Solar | 17K8 | 2026-02-19 | 2026-03-02 | 8 |  | 8 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 17K AMHERST
WMECO | Agawam | ESMAEX-06025 | 01001 | 150 | Solar | 30A4 | 2026-02-20 | 2026-03-09 | 12 |  | 12 |  |  | 0 | [26 empty] | Expedited | [9 empty] | Technical Review | [8 empty] | 30A SILVER
WMECO | Amherst | ESMAEX-06041 | 01002 | 11.5 | Solar & Battery | 17K8 | 2026-02-25 |  | -32879 |  |  |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review | [7 empty] | 6.6 | 17K AMHERST
WMECO | Bernardston | ESMAEX-06043 | 01337 | 30 | Solar & Battery | 21B8 | 2026-02-25 |  | -32879 |  |  |  |  | 0 | [26 empty] | Expedited | [9 empty] | On Hold | [7 empty] | 15 | 21B FRENCH KING
WMECO | Middlefield | ESMAEX-06047 | 01243 | 23 | Solar & Battery | UNLINKED | 2026-02-26 |  | -32880 |  |  |  |  | 0 | [26 empty] | Expedited | [9 empty] | Application Review | [7 empty] | 10
Fitchburg | Fitchburg | 12062 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F11W11 | 2026-02-05 | 2026-02-17 | 8 | 7 | 1 | 2026-02-17 | 2026-02-18 | 1 | 0 | 1 | [23 empty] | YES | Expedited | [9 empty] | Prepare Estimate | Res | Y
Fitchburg | Ashby | 12078 | 1431 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F39W19 | 2026-02-04 | 2026-02-04 | 1 | 0 | 1 | 2026-02-04 | 2026-02-05 | 1 | 0 | 1 | [20 empty] | 2026-02-06 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12081 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F01W02 | 2026-02-04 | 2026-02-10 | 4 | 3 | 1 | 2026-02-10 | 2026-02-12 | 2 | 0 | 2 | [20 empty] | 2026-02-18 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12082 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F40W42 | 2026-02-04 | 2026-02-09 | 3 | 2 | 1 | 2026-02-13 | 2026-02-16 | 1 | 0 | 1 | [20 empty] | 2026-02-18 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12091 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F40W42 | 2026-02-04 | 2026-02-04 | 1 | 0 | 1 | 2026-02-04 | 2026-02-05 | 1 | 0 | 1 | [20 empty] | 2026-02-06 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 12092 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F25W27 | 2026-02-04 | 2026-02-23 | 13 | 12 | 1 | 2026-02-23 | 2026-02-25 | 2 | 0 | 2 | [23 empty] | YES | Expedited | [9 empty] | Prepare Estimate | Res | Y
Fitchburg | Fitchburg | 12095 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F40W42 | 2026-02-09 | 2026-02-10 | 1 | 0 | 1 | 2026-02-10 | 2026-02-12 | 2 | 0 | 2 | [20 empty] | 2026-02-18 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12097 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F35W36 | 2026-02-12 | 2026-02-24 | 8 | 6 | 2 | 2026-02-24 | [28 empty] | Expedited | [9 empty] | Expedited Screening | Res | Y
Fitchburg | Fitchburg | 12098 | 1420 | 11.5 | 0 | 0 | Energy Storage | Yes | F50W51 | 2026-02-16 | 2026-02-19 | 3 | 0 | 3 | 2026-02-20 | 2026-02-25 | 3 | 0 | 3 | [20 empty] | 2026-02-26 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12101 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F01W02 | 2026-02-09 | 2026-02-10 | 1 | 0 | 1 | 2026-02-10 | 2026-02-12 | 2 | 0 | 2 | [20 empty] | 2026-02-18 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Fitchburg | 12102 | 1420 | 900 | 900 | N/A | Solar | No | F40W40 | 2026-02-09 | 2026-02-25 | 12 | 7 | 5 | [10 empty] | 2026-02-26 | [18 empty] | Standard | [9 empty] | Standard Initial Revoew | Comm | N
Fitchburg | Fitchburg | 12103 | 1420 | 4999.2 | 4999.2 | 4999 | Energy Storage | Yes | F40W40 | 2026-02-09 | 2026-02-26 | 13 | 8 | 5 | [10 empty] | 2026-02-27 | [18 empty] | Standard | [9 empty] | Standard Initial Revoew | Comm | N
Fitchburg | Ashby | 12108 | 1431 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F39W19 | 2026-02-16 | 2026-02-18 | 2 | 0 | 2 | 2026-02-18 | 2026-02-20 | 2 | 0 | 2 | [20 empty] | 2026-02-23 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Lunenburg | 12112 | 1462 | 34.5 | 25 | 0 | Solar + Energy Storage | Yes | F30W30 | 2026-02-19 | 2026-02-26 | 5 | 2 | 3 | 2026-02-26 | [28 empty] | Expedited | [9 empty] | Expedited Screening | Res | Y
Fitchburg | Fitchburg | 12130 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F40W40 | 2026-02-23 | 2026-02-26 | 3 | 0 | 3 | 2026-02-26 | [28 empty] | Expedited | [9 empty] | Expedited Screening | Res | Y
Fitchburg | Lunenburg | 11955 | 1462 | 8.4 | 8.4 | 0 | Solar + Energy Storage | Yes | F30W31 | 2025-12-01 | 2026-01-06 | 24 | 22 | 2 | 2026-01-06 | 2026-01-12 | 4 | 0 | 4 | [20 empty] | 2026-01-12 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12010 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-12-30 | 2026-01-08 | 6 | 5 | 1 | 2026-01-08 | 2026-01-12 | 2 | 0 | 2 | [20 empty] | 2026-01-16 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 12023 | 1462 | 20 | 20 | N/A | Solar | No | F31W37 | 2026-01-07 | 2026-01-08 | 1 | 0 | 1 | 2026-01-08 | 2026-01-13 | 3 | 0 | 3 | [20 empty] | 2026-01-16 |  |  | YES | Expedited | [9 empty] | Waiting for Mods Fee | Res | Y
Fitchburg | Fitchburg | 12030 | 1420 | 240 | 240 | N/A | Solar | No | F35W36 | 2026-01-15 | 2026-02-19 | 25 | 21 | 4 | 2026-02-19 | [28 empty] | Expedited | [9 empty] | Expedited Screening | Comm | Y
Fitchburg | Fitchburg | 12025 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F31W34 | 2026-01-28 | 2026-02-02 | 3 | 2 | 1 | 2026-02-02 | 2026-02-03 | 1 | 0 | 1 | [20 empty] | 2026-02-06 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12026 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F31W34 | 2026-01-05 | 2026-01-07 | 2 | 1 | 1 | 2026-01-07 | 2026-01-12 | 3 | 0 | 3 | [20 empty] | 2026-01-16 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Townsend | 12032 | 1474 | 15.2 | 15.2 | N/A | Solar | No | F39W18 | 2026-01-06 | 2026-02-02 | 19 | 18 | 1 | 2026-02-02 | 2026-02-03 | 1 | 0 | 1 | [20 empty] | 2026-02-06 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Fitchburg | 12035 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F50W51 | 2026-01-09 | 2026-01-13 | 2 | 0 | 2 | 2026-01-13 | 2026-01-15 | 2 | 0 | 2 | [20 empty] | 2026-01-16 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12037 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F11W11 | 2026-01-09 | 2026-01-13 | 2 | 0 | 2 | 2026-01-13 | 2026-01-14 | 1 | 0 | 1 | [20 empty] | 2026-01-20 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 12042 | 1420 | 15.2 | 15.2 | N/A | Solar | No | F25W27 | 2026-01-15 | 2026-01-23 | 6 | 5 | 1 | 2026-01-23 | 2026-01-26 | 3 | 0 | 3 | [20 empty] | 2026-02-02 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12044 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F25W27 | 2026-01-09 | 2026-01-13 | 2 | 0 | 2 | 2026-01-13 | 2026-01-14 | 1 | 0 | 1 | [20 empty] | 2026-01-16 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12059 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F40W40 | 2026-01-19 | 2026-01-21 | 2 | 0 | 2 | 2026-01-21 | 2026-01-23 | 2 | 0 | 2 | [20 empty] | 2026-02-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 12068 | 1431 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F39W19 | 2026-01-28 | 2026-01-29 | 1 | 0 | 1 | 2026-01-29 | 2026-01-30 | 1 | 0 | 1 | [20 empty] | 2026-02-11 |  |  | YES | Expedited | [9 empty] | Waiting for Mods Fee | Res | Y
Fitchburg | Townsend | 11931 | 1469 | 7.6 | 7.6 | N/A | Solar | No | F39W18 | 2025-11-12 | 2025-12-02 | 12 | 9 | 3 | 2025-12-04 | 2025-12-04 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [8 empty] | 2025-12-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 11913 | 1420 | 20 | 20 | N/A | Solar | No | F50W51 | 2025-11-14 | 2025-12-09 | 15 | 8 | 7 | 12/11/205 | 2025-12-12 | 1 | 0 | 1 | [20 empty] | 2025-12-15 |  |  | YES | Expedited | [9 empty] | Waiting for Mods Fee | Res | Y
Fitchburg | Fitchburg | 11940 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F50W55 | 2025-11-24 | 2025-12-01 | 2 | 0 | 2 | 2025-12-01 | 2025-12-02 | 1 | 0 | 1 | [20 empty] | 2025-12-04 | 2026-01-22 |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11992 | 1462 | 20 | 20 | 0 | Solar + Energy Storage | Yes | F30W30 | 2025-12-19 | 2025-12-23 | 2 | 0 | 2 | 2025-12-23 | 2025-12-29 | 3 | 0 | 3 | [23 empty] | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11991 | 1420 | 13.7 | 13.7 | 0 | Solar + Energy Storage | Yes | F35W36 | 2025-12-16 | 2025-12-17 | 1 | 0 | 1 | 2025-12-17 | 2025-12-18 | 1 | 0 | 1 | [20 empty] | 2025-12-16 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11984 | 1420 | 20 | 20 | 0 | Solar + Energy Storage | Yes | F01W04 | 2025-12-16 | 2025-12-29 | 8 | 7 | 1 | 2025-12-29 | 2025-12-30 | 1 | 0 | 1 | [20 empty] | 2026-01-08 | 2026-02-06 |  | YES | Expedited | [9 empty] | Perform Mods | Res | Y
Fitchburg | Fitchburg | 11983 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-12-16 | 2025-12-29 | 8 | 7 | 1 | 2025-12-29 | 2025-12-30 | 1 | 0 | 1 | [20 empty] | 2026-01-08 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11975 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F40W40 | 2025-12-09 | 2025-12-15 | 4 | 3 | 1 | 2025-12-15 | 2025-12-16 | 1 | 0 | 1 | [20 empty] | 2025-12-26 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11968 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-12-09 | 2025-12-15 | 4 | 3 | 1 | 2025-12-15 | 2025-12-16 | 1 | 0 | 1 | [20 empty] | 2025-12-26 | 2026-01-22 |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11952 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F50W55 | 2025-12-02 | 2025-12-04 | 2 | 0 | 2 | 2025-12-04 | 2025-12-09 | 3 | 2 | 1 | [20 empty] | 2025-12-15 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11939 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F40W42 | 2025-11-24 | 2025-12-01 | 3 | 0 | 3 | 2025-12-01 | 2025-12-03 | 2 | 0 | 2 | [20 empty] | 2025-12-11 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11937 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F35W36 | 2025-11-24 | 2025-12-04 | 6 | 4 | 2 | 2025-12-04 | 2025-12-05 | 1 | 0 | 1 | [20 empty] | 2025-12-11 | 2026-01-22 |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 12002 | 1462 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F31W37 | 2025-12-19 | 2025-12-29 | 5 | 3 | 2 | 2025-12-29 | 2025-12-31 | 2 | 1 | 1 | [20 empty] | 2026-01-12 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 12011 | 1420 | 20 | 20 | 0 | Solar + Energy Storage | Yes | F20W22 | 2025-12-30 | 2025-12-30 | 1 | 0 | 1 | 2025-12-30 | 2026-01-05 | 3 | 0 | 3 | [20 empty] | 2026-01-12 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11891 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F35W36 | 2025-11-21 | 2025-12-03 | 6 | 4 | 2 | 2025-12-03 | 2025-12-03 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11903 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F22W1 | 2025-11-14 | 2025-12-02 | 10 | 8 | 2 | 2025-12-02 | 2025-12-02 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11941 | 1420 | 15.7 | 15.7 | N/A | Solar | No | F40W40 | 2025-11-24 | 2025-12-02 | 4 | 1 | 3 | 2025-12-02 | 2025-12-03 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11943 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F40W42 | 2025-11-24 | 2025-12-01 | 3 | 0 | 3 | 2025-12-01 | 2025-12-02 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11946 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-11-24 | 2025-12-03 | 5 | 2 | 3 | 2025-12-03 | 2025-12-04 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11960 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F50W51 | 2025-12-09 | 2025-12-12 | 3 | 0 | 3 | 2025-12-12 | 2025-12-16 | 2 | 0 | 2 | [20 empty] | 2025-12-17 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11967 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F40W40 | 2025-12-09 | 2025-12-15 | 4 | 3 | 1 | 2025-12-15 | 2025-12-16 | 1 | 0 | 1 | [20 empty] | 2025-12-17 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11997 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F20W22 | 2025-12-19 | 2025-12-29 | 5 | 3 | 2 | 2025-12-31 | 2025-12-31 | 1 | 0 | 1 | [20 empty] | 2025-12-31 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Townsend | 11982 | 1474 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F39W18 | 2025-12-16 | 2025-12-29 | 8 | 7 | 1 | 2025-12-29 | 2025-12-30 | 1 | 0 | 1 | [20 empty] | 2025-12-31 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12009 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F35W36 | 2025-12-30 | 2025-12-31 | 1 | 0 | 1 | 2025-12-31 | 2026-01-05 | 3 | 0 | 3 | [20 empty] | 2026-01-05 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11962 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F11W11 | 2025-12-09 | 2025-12-15 | 4 | 1 | 3 | 2025-12-15 | 2025-12-16 | 1 | 0 | 1 | [20 empty] | 2026-01-16 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Lunenburg | 11872 | 1462 | 21.3 | 21.3 | 0 | Solar + Energy Storage | Yes | F31W38 | 2025-10-27 | 2025-11-17 | 15 | 9 | 6 | 2025-11-18 | 2025-11-25 | 6 | 5 | 1 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11873 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F50W51 | 2025-10-27 | 2025-11-17 | 15 | 9 | 6 | 2025-11-17 | 2025-11-19 | 2 | 0 | 2 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11888 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F40W42 | 2025-11-03 | 2025-11-17 | 10 | 9 | 1 | 2025-11-17 | 2025-11-19 | 2 | 0 | 2 | [20 empty] | 2025-12-01 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 11909 | 1462 | 13.8 | 15 | 0 | Solar + Energy Storage | Yes | F31W37 | 2025-11-14 | 2025-11-25 | 8 | 6 | 2 | 2025-11-25 | 2025-11-25 | 1 | 0 | 1 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11912 | 1420 | 21.4 | 21.4 | 0 | Solar + Energy Storage | Yes | F40W42 | 2025-11-14 | 2025-11-25 | 8 | 6 | 2 | 2025-11-25 | 2025-11-25 | 1 | 0 | 1 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11862 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-10-17 | 2025-11-06 | 15 | 10 | 5 | 2025-11-06 | 2025-11-13 | 5 | 2 | 3 | [20 empty] | 2025-11-18 |  |  | NO | Expedited | [8 empty] | 2026-01-21 | In Operation | Res | Y
Fitchburg | Townsend | 11870 | 1474 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F39W18 | 2025-10-27 | 2025-11-14 | 14 | 8 | 6 | 2025-11-14 | 2025-11-25 | 8 | 4 | 4 | [20 empty] | 2025-12-01 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Ashby | 11876 | 1431 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F39W19 | 2025-10-27 | 2025-11-17 | 15 | 9 | 6 | 2025-11-17 | 2025-11-19 | 2 | 0 | 2 | [20 empty] | 2025-11-19 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 11887 | 1462 | 23 | 23 | 0 | Solar + Energy Storage | Yes | F30W30 | 2025-11-17 | 2025-11-26 | 8 | 7 | 1 | 2025-11-26 | 2025-11-26 | 1 | 0 | 1 | [20 empty] | 2025-12-01 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11916 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F25W28 | 2025-11-14 | 2025-11-25 | 8 | 6 | 2 | 2025-11-25 | 2025-11-26 | 1 | 0 | 1 | [20 empty] | 2025-12-01 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11855 | 1462 | 10 | 0 | 0 | Energy Storage | Yes | F30W30 | 2025-10-13 | 2025-10-29 | 12 | 8 | 4 | 2025-10-29 | 2025-11-07 | 8 | 1 | 7 | [20 empty] | 2025-11-12 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11847 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F11W12 | 2025-10-08 | 2025-10-24 | 12 | 4 | 8 | 2025-10-24 | 2025-11-19 | 18 | 16 | 2 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11843 | 1420 | 3.8 |  |  | Solar + Energy Storage |  | F25W28 | 2025-10-07 | 2025-10-23 | 12 | 5 | 7 | 2025-10-23 | [28 empty] | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11834 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F11W12 | 2025-10-01 | 2025-10-09 | 7 | 4 | 3 | 2025-10-09 | 2025-11-19 | 28 | 21 | 7 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 11833 | 1431 | 20 | 20 | 0 | Solar + Energy Storage | Yes | F39W19 | 2025-10-01 | 2025-10-13 | 8 | 4 | 4 | 2025-10-13 | 2025-11-20 | 27 | 25 | 2 | [20 empty] | 2025-12-02 | 2025-12-29 |  | YES | Expedited | [8 empty] | 2026-02-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 11832 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F40W42 | 2025-10-01 | 2025-10-13 | 8 | 4 | 4 | 2025-10-13 | 2025-11-19 | 26 | 22 | 4 | [20 empty] | 2025-11-21 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11831 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F01W04 | 2025-10-01 | 2025-10-13 | 8 | 4 | 4 | 2025-10-13 | 2025-11-19 | 26 | 22 | 4 | [20 empty] | 2025-11-21 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11829 | 1420 | 100 | 100 | N/A | Solar | No | F11W11 | 2025-09-30 | 2025-10-27 | 19 | 16 | 3 | 2025-10-27 | 2025-11-26 | 22 | 18 | 4 | [23 empty] | YES | Expedited | [9 empty] | Create ISA | Comm | Y
Fitchburg | Fitchburg | 11828 | 1420 | 100 | 100 | N/A | Solar | No | F40W39 | 2025-09-30 | 2025-10-24 | 18 | 15 | 3 | 2025-10-24 | 2025-11-26 | 23 | 18 | 5 | [20 empty] | 2026-02-25 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Comm | Y
Fitchburg | Fitchburg | 11822 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F40W38 | 2025-09-29 | 2025-10-13 | 10 | 5 | 5 | 2025-10-13 | 2025-11-19 | 26 | 22 | 4 | [20 empty] | 2025-12-01 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11815 | 1420 | 12.2 | 12.2 | 0 | Solar + Energy Storage | Yes | F40W40 | 2025-09-24 | 2025-10-16 | 16 | 9 | 7 | 2025-10-16 | 2025-11-07 | 17 | 12 | 5 | [20 empty] | 2025-11-12 |  |  | NO | Expedited | [8 empty] | 2026-01-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 11813 | 1420 | 20 | 20 | 0 | Solar + Energy Storage | Yes | F35W36 | 2025-09-23 | 2025-10-16 | 17 | 13 | 4 | 2025-10-16 | 2025-11-19 | 24 | 17 | 7 | [20 empty] | 2025-12-01 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11811 | 1420 | 7.6 |  |  | Solar + Energy Storage |  | F25W27 | 2025-09-23 | 2025-10-14 | 15 | 6 | 9 | 2025-10-14 | [28 empty] | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11803 | 1420 | 15.2 |  |  | Solar |  | F31W34 | 2025-09-22 | 2025-10-01 | 8 | 7 | 1 | 2025-10-01 | 2025-10-02 | 2 | 0 | 2 | [20 empty] | 2025-10-13 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11790 | 1420 | 15.7 |  |  | Solar + Energy Storage |  | F40W40 | 2025-09-17 | 2025-09-24 | 7 | 6 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 11787 | 1462 | 11.5 |  |  | Solar + Energy Storage |  | F30W30 | 2025-09-23 | 2025-10-01 | 11 | 10 | 1 | 2025-10-01 | 2025-10-01 | 1 | 0 | 1 | [20 empty] | 2025-10-01 |  |  | NO | Expedited | [8 empty] | 2026-01-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 11783 | 1462 | 20 |  |  | Solar |  | F30W30 | 2025-09-16 | 2025-09-24 | 8 | 7 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [8 empty] | 2026-01-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 11780 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | F25W27 | 2025-09-16 | 2025-09-24 | 8 | 7 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11773 | 1420 | 17.6 |  |  | Solar + Energy Storage |  | F40W42 | 2025-09-12 | 2025-09-24 | 10 | 9 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11772 | 1420 | 15.7 |  |  | Solar + Energy Storage |  | F25W27 | 2025-09-12 | 2025-09-24 | 10 | 9 | 1 | 2025-09-24 | 2025-09-30 | 5 | 0 | 5 | [20 empty] | 2025-10-16 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11759 | 1420 | 15.7 |  |  | Solar + Energy Storage |  | F40W40 | 2025-09-10 | 2025-09-30 | 15 | 10 | 5 | 2025-09-30 | 2025-10-01 | 1 | 0 | 1 | [20 empty] | 2025-10-01 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11752 | 1462 | 3.8 | 3.8 | N/A | Solar | No | F31W38 | 2025-09-08 | 2025-10-01 | 18 | 12 | 3 | 2025-10-01 | 2025-10-02 | 1 | 0 | 1 | [20 empty] | 2025-10-13 |  |  | NO | Expedited | [8 empty] | 2026-02-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 11742 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | F22W1 | 2025-09-02 | 2025-09-24 | 17 | 16 | 1 | 2025-09-24 | 2025-09-29 | 4 | 0 | 4 | [20 empty] | 2025-09-29 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11739 | 1462 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F30W31 | 2025-09-02 | 2025-10-01 | 22 | 16 | 6 | 2025-10-01 | 2025-11-20 | 35 | 31 | 4 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 11738 | 1474 | 15.7 |  |  | Solar + Energy Storage |  | F39W18 | 2025-09-02 | 2025-09-30 | 21 | 15 | 6 | 2025-09-30 | 2025-10-01 | 1 | 0 | 1 | [20 empty] | 2025-10-01 |  |  | NO | Expedited | [8 empty] | 2025-12-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 11737 | 1420 | 23.8 | 8 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-09-02 | 2025-09-24 | 17 | 16 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-10-01 |  |  | No | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11728 | 1420 | 17.6 |  |  | Solar + Energy Storage |  | F11W12 | 2025-08-28 | 2025-09-03 | 4 | 3 | 1 | 2025-09-03 | 2025-09-04 | 2 | 0 | 2 | [20 empty] | 2025-09-08 |  |  | NO | Expedited | [8 empty] | 2025-12-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 11726 | 1420 | 250.8 | 250.8 | N/A | Solar | No | F50W55 | 2025-08-27 | 2025-09-30 | 24 | 14 | 10 | 2025-09-30 | 2025-10-30 | 22 | 0 | 22 | [23 empty] | YES | Expedited | [9 empty] | Waiting for Supplemental Review Fee | Comm | N
Fitchburg | Fitchburg | 11727 | 1420 | 180.4 | 180.4 | N/A | Solar | No | F50W55 | 2025-08-27 | 2025-10-02 | 26 | 11 | 15 | 2025-10-03 | 2025-10-30 | 19 | 0 | 19 | [23 empty] | YES | Expedited | [9 empty] | Waiting for Supplemental Review Fee | Comm | N
Fitchburg | Fitchburg | 11722 | 1420 | 7.6 |  |  | Solar + Energy Storage |  | F40W42 | 2025-08-26 | 2025-09-23 | 20 | 16 | 4 | 2025-09-23 | 2025-10-06 | 10 | 7 | 3 | [20 empty] | 2025-10-14 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Fitchburg | 11713 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | F22W1 | 2025-08-21 | 2025-09-03 | 9 | 8 | 1 | 2025-09-03 | 2025-09-04 | 2 | 0 | 2 | [20 empty] | 2025-09-23 |  |  | Yes | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11709 | 1420 | 15.7 |  |  | Solar + Energy Storage |  | 25W27 | 2025-08-20 | 2025-08-28 | 8 | 5 | 3 | 2025-08-28 | 2025-08-29 | 1 | 0 | 1 | [20 empty] | 2025-09-07 |  |  | NO | Expedited | [8 empty] | 2025-12-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 11700 | 1462 | 17.6 | 17.6 | N/A | Solar | No | 30W31 | 2025-08-18 | 2025-08-28 | 9 | 7 | 2 | 2025-08-28 | 2025-09-04 | 5 | 0 | 5 | [20 empty] | 2025-09-12 | 2025-11-12 |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11691 | 1420 | 13.8 |  |  | Solar + Energy Storage |  | F40W40 | 2025-08-27 | 2025-09-23 | 19 | 10 | 9 | 2025-09-23 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [8 empty] | 2026-01-07 | In Operation | Res | Y
Fitchburg | Townsend | 11677 | 1474 | 15.7 | 12 | 0 | Solar + Energy Storage | Yes | 39W18 | 2025-08-11 | 2025-08-25 | 11 | 7 | 4 | 2025-08-25 | 2025-08-29 | 5 | 2 | 3 | [20 empty] | 2025-09-07 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11676 | 1420 | 13.7 |  |  | Solar + Energy Storage |  | 25W28 | 2025-08-11 | 2025-08-21 | 9 | 2 | 7 | 2025-08-21 | 2025-08-29 | 7 | 2 | 5 | [20 empty] | 2025-09-07 |  |  | NO | Expedited | [8 empty] | 2025-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 11675 | 1420 | 15.7 |  |  | Solar + Energy Storage |  | 11W12 | 2025-08-11 | 2025-08-21 | 10 | 7 | 3 | 2025-08-21 | 2025-08-29 | 7 | 2 | 5 | [20 empty] | 2025-09-08 |  |  | Yes | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 11674 | 1462 | 17.6 |  |  | Solar + Energy Storage |  | 31W37 | 2025-08-11 | 2025-08-20 | 8 | 7 | 1 | 2025-08-20 | 2025-08-27 | 6 | 0 | 6 | [20 empty] | 2025-08-27 |  |  | NO | Expedited | [8 empty] | 2025-12-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 11663 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | 40W42 | 2025-08-06 | 2025-08-14 | 16 | 10 | 6 | 2025-08-14 | 2025-08-15 | 1 | 0 | 1 | [20 empty] | 2025-08-20 |  |  | NO | Expedited | [8 empty] | 2026-01-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 11658 | 1420 | 13.7 | 13.7 | N/A | Solar | No | F25W28 | 2025-08-11 | 2025-09-11 | 24 | 20 | 4 | 2025-09-11 | 2025-09-12 | 1 | 0 | 1 | [20 empty] | 2025-09-22 |  |  | NO | Expedited | [9 empty] | COC and Photos DER Review | Res | Y
Fitchburg | Fitchburg | 11605 | 1420 | 7.6 |  |  | Solar + Energy Storage |  | 31W34 | 2025-07-16 | 2025-07-29 | 10 | 6 | 4 | 2025-08-11 | 2025-08-11 | 0 | 0 | 0 | [20 empty] | 2025-08-14 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11600 | 1420 | 33.1 |  |  | Solar |  | 20W22 | 2025-07-15 | 2025-07-25 | 9 | 7 | 2 | 2025-07-25 | 2025-07-28 | 3 | 0 | 3 | [20 empty] | 2025-07-29 |  |  | NO | Expedited | [8 empty] | 2025-08-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 11578 | 1420 | 16.2 |  |  | Solar |  | 25W27 | 2025-07-09 | 2025-07-22 | 10 | 7 | 3 | 2025-07-22 | 2025-07-25 | 4 | 0 | 4 | [20 empty] | 2025-07-25 |  |  | NO | Expedited | [8 empty] | 2025-10-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 11571 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | 11W11 | 2025-07-08 | 2025-08-14 | 13 | 9 | 4 | 2025-08-14 | 2025-08-14 | 1 | 0 | 1 | [20 empty] | 2025-08-20 |  |  | NO | Expedited | [8 empty] | 2026-01-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 11554 | 1462 | 17.4 |  |  | Solar |  | 30W30 | 2025-06-27 | 2025-07-23 | 18 | 16 | 2 | 2025-07-23 | 2025-07-24 | 1 | 0 | 1 | [20 empty] | 2025-07-25 |  |  | NO | Expedited | [8 empty] | 2025-12-15 | In Operation | Res | Y
Fitchburg | Ashby | 11539 | 1431 | 990 |  |  | Solar |  | 39W19 | 2025-06-24 | 2025-07-29 | 25 | 22 | 3 | [10 empty] | 2025-07-29 | 2025-08-01 | 3 | 0 | 3 | [14 empty] | Standard | [9 empty] | Cancelled | Comm | N
Fitchburg | Fitchburg | 11527 | 1420 | 996 |  |  | Solar + Energy Storage |  | 40W40 | 2025-06-23 | 2025-06-30 | 5 | 4 | 1 | [10 empty] | 2025-06-30 | 2025-07-09 | 7 | 0 | 7 | [14 empty] | Standard | [9 empty] | On Hold | Comm | N
Fitchburg | West Townsend | 11518 | 1474 | 24.576 |  |  | Solar |  | 39W18 | 2025-07-01 | 2025-07-07 | 3 | 0 | 3 | 2025-07-07 | 2025-07-08 | 1 | 0 | 1 | [20 empty] | 2025-07-16 | 2025-08-18 |  | YES | Expedited | [8 empty] | 2025-12-26 | In Operation | Res | Y
Fitchburg | Ashby | 11517 | 1431 | 20 |  |  | Solar |  | 39W19 | 2025-06-23 | 2025-07-08 | 10 | 6 | 4 | 2025-07-08 | 2025-07-09 | 1 | 0 | 1 | [20 empty] | 2025-07-09 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11513 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | 50W56 | 2025-06-13 | 2025-06-24 | 10 | 3 | 7 | 2025-06-24 | 2025-06-26 | 3 | 0 | 3 | [20 empty] | 2025-07-03 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 11496 | 1431 | 23 | 23 | 10 | Solar + Energy Storage | Yes | 40W40 | 2025-06-09 | 2025-06-25 | 15 | 9 | 6 | 2025-06-25 | 2025-07-21 | 18 | 17 | 1 | [20 empty] | 2025-07-21 |  |  | NO | Expedited | [8 empty] | 2026-01-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 11481 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | 40W40 | 2025-06-02 | 2025-06-16 | 10 | 9 | 1 | 2025-06-16 | 2025-07-07 | 14 | 4 | 10 | [20 empty] | 2025-07-07 |  |  | NO | Expedited | [8 empty] | 2025-12-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 11474 | 1469 | 498 |  |  | Solar |  | 39W18 | 2025-05-29 | 2025-06-05 | 5 | 2 | 3 | [10 empty] | 2025-06-06 | 2025-06-17 | 7 | 0 | 7 | 2025-09-26 | 2026-01-07 | 69 | 0 | 69 | [9 empty] | Standard | [9 empty] | Create ISA | Comm | N
Fitchburg | Lunenburg | 11447 | 1462 | 11.4 |  |  | Solar |  | 31W37 | 2025-05-20 | 2025-06-05 | 22 | 12 | 10 | 2025-06-05 | 2025-06-11 | 5 | 0 | 5 | [20 empty] | 2025-06-14 |  |  | NO | Expedited | [8 empty] | 2025-07-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 11439 | 1462 | 15.2 |  |  | Solar |  | 30W30 | 2025-05-16 | 2025-05-30 | 10 | 8 | 2 | 2025-05-30 | 2025-06-03 | 3 | 0 | 3 | [20 empty] | 2025-06-10 | 2025-08-05 |  | YES | Expedited | [8 empty] | 2025-10-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 11437 | 1420 | 15.4 | 15.4 | N/A | Solar | No | 50W56 | 2025-06-03 | 2025-06-05 | 2 | 1 | 1 | 2025-06-05 | 2025-06-11 | 4 | 0 | 4 | [20 empty] | 2025-06-26 |  |  | NO | Expedited | [8 empty] | 2025-11-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 11351 | 1420 | 49.7 |  |  | Solar |  | 22W1 | 2025-04-18 | 2025-05-12 | 20 | 17 | 3 | 2025-05-12 | 2025-05-13 | 1 | 0 | 1 | [20 empty] | 2025-06-26 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Townsend | 11344 | 1469 | 11.5 |  |  | Solar + Energy Storage |  | 15W17 | 2025-04-17 | 2025-04-28 | 8 | 7 | 1 | 2025-04-28 | 2025-04-30 | 3 | 0 | 3 | [20 empty] | 2025-05-13 |  |  | NO | Expedited | [8 empty] | 2025-08-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 11336 | 1462 | 11.5 |  |  | Solar + Energy Storage |  | 31W37 | 2025-04-15 | 2025-04-28 | 10 | 5 | 5 | 2025-05-01 | 2025-05-02 | 3 | 0 | 3 | [20 empty] | 2025-05-02 |  |  | NO | Expedited | [8 empty] | 2025-10-30 | In Operation | Res | Y
Fitchburg | Townsend | 11328 | 1469 | 10 |  |  | Solar + Energy Storage |  | 39W18 | 2025-04-30 | 2025-05-01 | 1 | 0 | 1 | 2025-05-01 | 2025-05-05 | 4 | 0 | 4 | [20 empty] | 2025-05-02 |  |  | NO | Expedited | [8 empty] | 2025-12-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 11249 | 1420 | 15.2 |  |  | Solar |  | 20W22 | 2025-04-15 | 2025-04-25 | 9 | 4 | 5 | 2025-04-25 | 2025-04-28 | 2 | 0 | 2 | [20 empty] | 2025-04-01 |  |  | NO | Expedited | [8 empty] | 2025-07-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 11240 | 1462 | 38 |  |  | Solar |  | 30W30 | 2025-03-17 | 2025-04-08 | 17 | 5 | 12 | 2025-04-21 | 2025-04-21 | 1 | 0 | 1 | [20 empty] | 2025-04-30 |  |  | NO | Expedited | [8 empty] | 2026-01-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 11230 | 1462 | 9 |  |  | Solar + Energy Storage |  | 31W37 | 2025-04-15 | 2025-05-05 | 15 | 8 | 7 | 2025-05-05 | 2025-05-09 | 5 | 0 | 5 | [20 empty] | 2025-05-02 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11228 | 1462 | 999 | 999 | 0 | Solar + Energy Storage | Yes | 30W30 | 2025-03-12 | 2025-03-26 | 11 | 10 | 1 | [10 empty] | 2025-03-27 | 2025-03-31 | 3 | 0 | 3 | 2025-07-18 | 2025-10-17 | 64 | 0 | 64 | [5 empty] | 2026-02-11 |  |  |  | Standard | [9 empty] | Waiting for ISA Signature | Comm | N
Fitchburg | Fitchburg | 11216 | 1420 | 15.2 |  |  | Solar |  | 50W55 | 2025-03-10 | 2025-04-17 | 29 | 26 | 3 | 2025-04-17 | 2025-04-28 | 8 | 0 | 8 | [20 empty] | 2025-04-30 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Townsend | 11190 | 1469 | 15.84 |  |  | Solar |  | 15W16 | 2025-03-01 | 2025-03-27 | 19 | 0 | 19 | 2025-03-27 | 2025-03-29 | 1 | 0 | 1 | [20 empty] | 2025-04-16 |  |  | No | Expedited | [8 empty] | 2025-10-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 11176 | 1420 | 4999 | 4999 | 4999 | Energy Storage | Yes | 40W39 | 2025-02-28 | 2025-03-13 | 10 | 9 | 1 | [10 empty] | 2025-03-15 | 2025-03-25 | 7 | 0 | 7 | 2025-09-22 | [13 empty] | Standard | [9 empty] | Impact Study in Process | Comm | N | Summer Street Substation Group | Study In Process - Preliminary Assesment Stage
Note on AB24443: Renata J Peloquin: Check and Study were NOT stamped with date received.