## DOER
DG Interconnection Tracking and Reporting Template
Utility Timelines
Reporting Period: |  | from | 2009-01-01 | to | 2026-03-31
Date Filed: |  | 2026-04-01
Force Majeure Reporting |  |  |  | Start Date | End Date | Explanation
Enter Dates (inclusive) of Force Majeure Events with "Clock" Stoppage |  |  | Event #1 | 2012-10-26 | 2012-11-16 | Storm event |  |  |  | 16
|  |  | Event #2 | 2013-02-08 | 2013-02-13 | Storm event |  |  |  | 4
|  |  | Event #3 | 2013-03-06 | 2013-03-08 | Storm event |  |  |  | 3
|  |  | Event #4 | 2017-10-30 | 2017-11-03 | Storm event |  |  |  | 5
|  |  | Event #5 | 2018-03-02 | 2018-03-15 | Storm event |  |  |  | 10
|  |  | Event #6 | 2020-08-05 | 2020-08-09 | Storm event |  |  |  | 3
|  |  | Total Workdays (calculated) |  | 41 |  |  |  |  | 41
Application and Site Information | [6 empty] | Application Receipt |  |  |  |  | Screen Review |  |  |  |  | Supplemental Review |  |  |  |  | Standard Process Initial Review |  |  |  |  | Impact Study |  |  |  | Detailed Study |  |  |  |  | IA and Pre-Construction Information | [6 empty] | Construction |  |  |  |  | Witness Information |  | Authorization and Misc Information |  |  |  | Group Study Info
Company Name | City/Town | Facility ID | Zip Code | Design Capacity (kW) | Fuel Type | Circuit Name | Date Application Received | Date Application Deemed Complete | Application Receipt Total Time Lapsed (Workdays) | Application Receipt Customer Time Lapsed (Workdays) | Application Receipt Utility Time Lapsed (Workdays) | Date of Screen Study Began | Date of Screen Study Completed | Screen Review Total Time Lapsed (Workdays) | Screen Review Customer Time Lapsed (Workdays) | Screen Review Utility Time Lapsed (Workdays) | Date Supplemental Review Began | Date Supplemental Review Complete | Supplemental Review Total Time Lapsed (Workdays) | Supplemental Review Customer Time Lapsed (Workdays) | Supplemental Review Utility Time Lapsed (Workdays) | Date Standard Process Initial Review Began | Date Standard Process Initial Review Complete | Standard Process Total Time Lapsed (Workdays) | Standard Process Customer Time Lapsed (Workdays) | Standard Process Utility Time Lapsed (Workdays) | Date Impact Study Sent | Impact Study Total Time Lapsed (Workdays) | Impact Study Customer Time Lapsed (Workdays) | Impact Study Utility Time Lapsed (Workdays) | Date Detailed Study Began | Date Detailed Study Sent | Detailed Study Total Time Lapsed (Workdays) | Detailed Study Customer Time Lapsed (Workdays) | Detailed Study Utility Time Lapsed (Workdays) | Date Interconnection Agreement Sent | Date ISA & Payment Received | Estimated In-Service Date | System Modification Required | Expedited/Standard/Complex Project | Construction Timeline Commitment (Workdays) | Date Construction Began | Date Construction Completed | Construction Total Time Lapsed (Workdays) | Construction Customer Time Lapsed (Workdays) | Construction Utility Time Lapsed (Workdays) | Date Witness Test Scheduled | Date Witness Test Completed | Authorization to Interconnect | Status | Private/Gov't | Net Metered? (Y/N) | Group Study | Group Study Designation
National Grid | ORANGE | 416537 | 01364 | 200 | Solar | 05_09_705W4 | 03/11/2022 | 03/25/2022 | 10 | 0 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y | Barre-Athol | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | GLOUCESTER | 178526 | 01930 | 3.8 | Solar | 05_12_51T1 | 04/04/2018 | 04/04/2018 | 11 | 10 | 1 | 05/16/2018 | 05/16/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/10/2019 | N | EXP | 323 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol | Scoping Meeting
National Grid | LOWELL | 644511 | 01851 | 7.6 | Solar | 05_14_2L2 | 10/02/2024 | 10/08/2024 | 2 | 0 | 2 | 10/09/2024 | 10/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 10/02/2024 | 12/9/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | WESTFORD | 701934 | 01886 | 19 | Solar | 05_14_57L2 | 07/15/2025 | 07/28/2025 | 8 | 5 | 3 | 07/29/2025 | 07/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2025 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | TEWKSBURY | 176509 | 01876 | 5.5 | Solar | 05_14_70L8 | 03/28/2016 | 03/28/2016 | 3 | 3 | 0 | 04/01/2016 | 04/01/2016 | 196 | 0 | 196 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2016 |  | 4/3/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Barre-Athol | Scoping Meeting
National Grid | LAWRENCE | 225186 | 01841 | 7.6 | Solar | 05_14_8L2 | 05/03/2019 | 05/16/2019 | 0 | 0 | 0 | 05/17/2019 | 05/17/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2019 | 05/03/2019 | 10/23/2021 | Y | EXP | 365 | 12/09/2020 | 01/08/2021 | 30 | 0 | 30 |  |  | 5/27/2021 | Connected |  | N | Barre-Athol | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | WORCESTER | 624586 | 01609 | 21.38 | Solar | 05_01_23W2 | 07/18/2024 | 07/22/2024 | 2 | 0 | 2 | 07/23/2024 | 07/23/2024 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 07/18/2024 | 9/21/2025 | Y | EXP | 365 | 10/29/2024 | 11/01/2024 | 4 | 0 | 4 |  |  | 5/22/2025 | Connected |  | N | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | OXFORD | 646413 | 01540 | 10 | Solar | 05_01_406L4 | 10/18/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 10/18/2024 | 2/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | NORTH BROOKFIELD | 178157 | 01535 | 990 | Solar | 05_01_552L3 | 12/22/2017 | 02/05/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2018 | 02/28/2018 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2018 |  | 12/31/2018 | N | STD | 174 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | WORCESTER | 176397 | 01605 | 2649 | Natural Gas | 05_01_HT61 | 03/10/2016 | 03/10/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2016 | 06/13/2016 | 60 | 44 | 16 |  | 0 | 0 | 0 | 10/04/2016 | 12/13/2016 | 47 | 13 | 34 | 1/25/2017 | 03/10/2016 | 1/31/2019 | Y | STD | 736 | 01/03/2018 | 07/26/2018 | 204 | 0 | 204 | 1/25/2018 | 1/25/2018 | 1/10/2019 | Connected |  | N | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | FALL RIVER | 646688 | 02720 | 0 | Solar | 05_05_28W51 | 10/11/2024 | 12/09/2024 | 8 | 5 | 3 | 12/10/2024 | 12/10/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | ORANGE | 620825 | 01364 | 3602 | Solar | 05_09_705W4 | 12/10/2024 | 05/19/2025 | 110 | 100 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/20/2025 | 07/31/2025 | 50 | 31 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | GLOUCESTER | 178557 | 01930 | 11.4 | Solar | 05_12_51T1 | 04/04/2018 | 04/04/2018 | 11 | 10 | 1 | 05/15/2018 | 05/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/10/2019 | N | EXP | 323 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | CHELMSFORD | 649264 | 01863 | 5.76 | Solar | 05_14_2L2 | 10/30/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 10/30/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | WESTFORD | 718919 | 01886 | 10 | Solar | 05_14_57L2 | 09/14/2025 | 09/18/2025 | 4 | 0 | 4 | 09/19/2025 | 09/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 11/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2026 | Connected |  | N | Ayer-Clinton | Closed
National Grid | TEWKSBURY | 178536 | 01876 | 15.2 | Solar | 05_14_70L8 | 12/07/2017 | 12/07/2017 | 15 | 0 | 15 | 01/02/2018 | 01/02/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 3/22/2019 | N | EXP | 443 |  |  | 0 | 0 | 0 |  |  | 12/19/2018 | Connected |  | N | Ayer-Clinton | Closed
National Grid | LAWRENCE | 242394 | 01841 | 3.8 | Solar | 05_14_8L2 | 08/01/2019 | 08/01/2019 | 0 | 0 | 0 | 08/02/2019 | 08/02/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2019 |  | 7/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2020 | Connected |  | N | Ayer-Clinton | Closed
National Grid | WORCESTER | 736356 | 01602 | 10 | Solar | 05_01_23W3 | 11/25/2025 | 11/26/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 3/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Gardner-Winchendon | Time Frame Suspension
National Grid | OXFORD | 646924 | 01540 | 5.76 | Solar | 05_01_406L4 | 10/29/2024 | 12/03/2024 | 11 | 5 | 6 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 | 10/29/2024 | 1/24/2026 | Y | EXP | 365 | 02/15/2025 | 02/27/2025 | 13 | 0 | 13 |  |  | 4/12/2025 | Connected |  | N | Gardner-Winchendon | Time Frame Suspension
National Grid | SPENCER | 178194 | 01562 | 2450 | Solar | 05_01_552L3 | 01/03/2018 | 02/01/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2018 | 04/17/2018 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2018 | 01/03/2018 | 3/20/2020 | Y | STD | 423 | 12/06/2019 | 02/19/2020 | 75 | 0 | 75 |  |  | 3/16/2020 | Connected |  | N | Gardner-Winchendon | Time Frame Suspension
National Grid | FALL RIVER | 419356 | 02721 | 240 | Solar | 05_05_106W42 | 05/26/2022 | 06/13/2022 | 11 | 3 | 8 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2023 | 05/26/2022 | 6/14/2026 | Y | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N | Gardner-Winchendon | Time Frame Suspension
National Grid | FALL RIVER | 674818 | 02720 | 7.6 | Solar | 05_05_28W51 | 03/05/2025 | 03/10/2025 | 3 | 0 | 3 | 03/11/2025 | 03/11/2025 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N | Gardner-Winchendon | Time Frame Suspension
National Grid | ATHOL | 195816 | 01331 | 4200 | Solar | 05_09_705W4 | 09/14/2018 | 10/05/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/08/2018 | 11/08/2018 | 62 | 14 | 48 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon | Time Frame Suspension
National Grid | ESSEX | 189490 | 01929 | 10 | Solar | 05_12_51T1 | 10/09/2018 | 10/11/2018 | 1 | 0 | 1 | 10/12/2018 | 10/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 |  | 10/15/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2019 | Connected |  | N | Gardner-Winchendon | Time Frame Suspension
National Grid | LOWELL | 654955 | 01851 | 3.8 | Solar | 05_14_2L2 | 11/18/2024 | 12/10/2024 | 4 | 0 | 4 | 12/11/2024 | 12/11/2024 | 30 | 5 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N | Gardner-Winchendon | Time Frame Suspension
National Grid | WESTFORD | 727574 | 01886 | 15.2 | Solar | 05_14_57L2 | 10/19/2025 | 10/22/2025 | 3 | 0 | 3 | 10/23/2025 | 10/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N | Millbury-Grafton | Closed
National Grid | TEWKSBURY | 192658 | 01876 | 10 | Solar | 05_14_70L8 | 08/28/2018 | 10/08/2018 | 17 | 17 | 0 | 10/09/2018 | 10/09/2018 | 41 | 27 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton | Closed
National Grid | LAWRENCE | 278952 | 01841 | 7.6 | Solar | 05_14_8L2 | 02/27/2020 |  | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton | Closed
National Grid | WORCESTER | 743208 | 01602 | 5.76 | Solar | 05_01_23W3 | 01/02/2026 | 01/05/2026 | 3 | 0 | 3 | 01/16/2026 | 01/16/2026 | 51 | 24 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | MPL-East | Closed
National Grid | OXFORD | 650792 | 01540 | 8.41 | Solar | 05_01_406L4 | 11/01/2024 | 11/26/2024 | 3 | 0 | 3 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N | MPL-East | Closed
National Grid | NORTH BROOKFIELD | 178267 | 01535 | 4980 | Solar | 05_01_552L3 | 01/08/2018 | 01/08/2018 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2018 | 03/10/2018 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/14/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East | Closed
National Grid | FALL RIVER | 175293 | 02721 | 20 | Solar | 05_05_106W42 | 11/07/2014 | 11/07/2014 | 6 | 2 | 4 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2014 |  | 2/27/2015 | N | EXP | 93 |  |  | 0 | 0 | 0 | 4/16/2015 | 4/16/2015 | 4/16/2015 | Connected |  | N | MPL-East | Closed
National Grid | ATTLEBORO | 176268 | 02703 | 17.6 | Solar | 05_05_2J1 | 02/18/2015 | 02/18/2015 | 4 | 1 | 3 | 02/25/2015 | 02/25/2015 | 480 | 0 | 480 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 7/31/2015 | N | EXP | 154 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East | Closed
National Grid | PETERSHAM | 195814 | 01366 | 3000 | Solar | 05_09_705W4 | 09/14/2018 | 10/02/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2018 | 11/08/2018 | 65 | 35 | 30 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East | Closed
National Grid | MANCHESTER | 195069 | 01944 | 0 | Solar | 05_12_51T1 | 09/05/2018 | 10/02/2018 | 10 | 4 | 6 | 10/03/2018 | 10/03/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 10/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2018 | Connected |  | N | MPL-East | Closed
National Grid | LOWELL | 671209 | 01851 | 10 | Solar | 05_14_2L2 | 02/10/2025 | 02/26/2025 | 3 | 0 | 3 | 02/27/2025 | 02/27/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N | MPL-East | Closed
National Grid | WESTFORD | 740323 | 01886 | 23 | Solar | 05_14_57L2 | 12/15/2025 | 12/17/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2026 | Connected |  | N | MPL-East | Closed
National Grid | BILLERICA | 259369 | 01821 | 3.8 | Solar | 05_14_70L8 | 10/22/2019 | 10/23/2019 | 0 | 0 | 0 | 10/24/2019 | 10/24/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 |  | 10/21/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2020 | Connected |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | LAWRENCE | 290049 | 01841 | 8.19 | Solar | 05_14_8L2 | 06/09/2020 | 06/15/2020 | 3 | 0 | 3 | 06/16/2020 | 06/16/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/09/2020 | 2/25/2022 | Y | EXP | 365 | 04/14/2021 | 09/22/2021 | 161 | 3 | 158 |  |  | 11/17/2021 | Connected |  | Y | Spencer-Rutland | Time Frame Suspension
National Grid | LEOMINSTER | 744673 | 01524 | 20.16 | Solar | 05_01_23W3 | 01/16/2026 | 01/27/2026 | 5 | 3 | 2 | 01/28/2026 | 01/28/2026 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Spencer-Rutland | Time Frame Suspension - Group Member Withdraw
National Grid | OXFORD | 657763 | 01540 | 10 | Solar | 05_01_406L4 | 12/02/2024 | 01/13/2025 | 16 | 11 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | NORTH BROOKFIELD | 178304 | 01535 | 2780 | Solar | 05_01_552L3 | 01/09/2018 | 03/09/2018 | 41 | 21 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/07/2018 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  | 1/15/2019 | N | STD | 203 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | FALL RIVER | 175292 | 02721 | 20 | Solar | 05_05_106W42 | 11/07/2014 | 11/07/2014 | 6 | 2 | 4 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2014 |  | 2/27/2015 | N | EXP | 80 |  |  | 0 | 0 | 0 | 2/27/2015 | 2/27/2015 | 4/17/2015 | Connected |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | ATTLEBORO | 484664 | 02703 | 6 | Solar | 05_05_2J1 | 01/31/2023 | 02/01/2023 | 1 | 0 | 1 | 02/02/2023 | 02/02/2023 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2023 | 01/31/2023 | 7/26/2024 | Y | EXP | 365 | 07/01/2023 | 07/27/2023 | 27 | 0 | 27 |  |  | 8/2/2023 | Connected |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | AMESBURY | 704916 | 01913 | 50 | Solar | 05_14_5J14 | 08/21/2025 | 08/25/2025 | 2 | 0 | 2 | 08/26/2025 | 08/26/2025 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | GLOUCESTER | 195777 | 01930 | 147.6 | Solar | 05_12_51T1 | 09/12/2018 | 09/19/2018 | 4 | 0 | 4 | 09/20/2018 | 09/20/2018 | 20 | 0 | 20 | 09/13/2019 | 09/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2019 |  | 12/31/2020 | N | EXP | 172 |  |  | 0 | 0 | 0 |  |  | 12/31/2020 | Connected |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | LOWELL | 680319 | 01851 | 7.6 | Solar | 05_14_2L2 | 03/25/2025 | 03/28/2025 | 3 | 0 | 3 | 03/31/2025 | 03/31/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | TYNGSBORO | 710654 | 01879 | 0 | Battery Add-On | 05_14_57L3 | 08/08/2025 | 08/11/2025 | 1 | 0 | 1 | 08/12/2025 | 08/12/2025 | 49 | 34 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | TEWKSBURY | 300909 | 01876 | 0 | Solar | 05_14_70L8 | 07/14/2020 | 08/06/2020 | 17 | 17 | 0 | 08/07/2020 | 08/07/2020 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2020 |  | 8/2/2023 | N | EXP | 750 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | LAWRENCE | 291189 | 01841 | 7.6 | Solar | 05_14_8L2 | 05/08/2020 | 05/11/2020 | 0 | 0 | 0 | 05/12/2020 | 05/12/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/11/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | WORCESTER | 174253 | 01602 | 1095 | Solar | 05_01_23W3 | 02/27/2012 | 02/27/2012 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2012 | 05/21/2012 | 33 | 0 | 33 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | OXFORD | 683430 | 01540 | 7.6 | Solar | 05_01_406L4 | 04/10/2025 | 04/28/2025 | 1 | 0 | 1 | 05/07/2025 | 05/07/2025 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 | 04/10/2025 | 6/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | NORTH BROOKFIELD | 178307 | 01535 | 996 | Solar | 05_01_552L3 | 01/09/2018 | 03/09/2018 | 41 | 41 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/07/2018 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/15/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | FALL RIVER | 177918 | 02721 | 312 | Solar | 05_05_106W42 | 10/20/2017 | 10/20/2017 | 5 | 0 | 5 | 11/03/2017 | 11/03/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2017 |  | 10/28/2018 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 8/3/2018 | Connected |  | N | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | ATTLEBORO | 484658 | 02703 | 6 | Solar | 05_05_2J1 | 01/31/2023 | 02/01/2023 | 1 | 0 | 1 | 02/02/2023 | 02/02/2023 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 |  | 3/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2023 | Connected |  | N | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | AMESBURY | 704904 | 01913 | 50 | Solar | 05_14_5J14 | 08/21/2025 | 08/25/2025 | 2 | 0 | 2 | 08/26/2025 | 08/26/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | GLOUCESTER | 204210 | 01930 | 0 | Solar | 05_12_51T1 | 12/20/2018 | 01/03/2019 | 7 | 0 | 7 | 01/04/2019 | 01/04/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 | 12/20/2018 | 1/3/2020 | Y | EXP | 365 | 08/23/2019 | 12/18/2019 | 117 | 0 | 117 |  |  | 7/31/2020 | Connected |  | N | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | LOWELL | 671910 | 01851 | 150 | Solar | 05_14_2L3 | 02/25/2025 | 03/26/2025 | 22 | 12 | 10 | 03/27/2025 | 03/27/2025 | 47 | 22 | 25 | 03/05/2026 |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | Y | Webster-Southbridge-Charlton | Time Frame Suspension - Group Member Withdraw
National Grid | WESTFORD | 712195 | 01886 | 3.8 | Solar | 05_14_57L3 | 08/14/2025 | 09/05/2025 | 25 | 23 | 2 | 10/23/2025 | 10/23/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 08/14/2025 | 11/17/2026 | Y | EXP | 365 | 01/15/2026 |  | 77 | 0 | 77 |  |  |  | Construction |  | N | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | TEWKSBURY | 362871 | 01876 | 7.83 | Solar | 05_14_70L8 | 07/09/2021 | 07/13/2021 | 2 | 0 | 2 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | Time Frame Suspension - Group Member Withdraw
National Grid | METHUEN | 296373 | 01844 | 6.93 | Solar | 05_14_8L2 | 06/30/2020 | 07/14/2020 | 10 | 7 | 3 | 07/15/2020 | 07/15/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2020 |  | 6/29/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | LEICESTER | 174992 | 01524 | 13.11 | Solar | 05_01_23W3 | 03/11/2013 | 03/11/2013 | 5 | 0 | 5 | 03/20/2013 | 03/20/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2013 |  | 7/5/2013 | N | EXP | 93 |  |  | 0 | 0 | 0 | 4/3/2013 | 4/3/2013 | 5/24/2013 | Connected |  | N | Hopedale-West | Closed
National Grid | OXFORD | 694012 | 01540 | 7.6 | Solar | 05_01_406L4 | 05/29/2025 | 06/20/2025 | 2 | 0 | 2 | 06/23/2025 | 06/23/2025 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/29/2025 | 8/4/2026 | Y | EXP | 365 | 10/11/2025 | 10/10/2025 | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N | Hopedale-West | Closed
National Grid | BROOKFIELD | 178483 | 01515 | 4999 | Solar | 05_01_552L3 | 04/03/2018 | 04/05/2018 | 18 | 18 | 0 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West | Closed
National Grid | FALL RIVER | 178620 | 02721 | 144 | Solar | 05_05_106W42 | 02/01/2018 | 02/01/2018 | 19 | 0 | 19 | 03/05/2018 | 03/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2018 |  | 2/7/2019 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N | Hopedale-West | Closed
National Grid | ATTLEBORO | 505519 | 02703 | 7.6 | Solar | 05_05_2J1 | 03/15/2023 | 03/22/2023 | 5 | 4 | 1 | 03/23/2023 | 03/23/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | Closed - Start Study
National Grid | AMESBURY | 175401 | 01913 | 17 | Solar | 05_14_5J14 | 11/19/2014 | 11/19/2014 | 15 | 15 | 0 | 12/15/2014 | 12/15/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West | Closed
National Grid | MANCHESTER | 217096 | 01944 | 0 | Solar | 05_12_51T1 | 04/03/2019 | 04/09/2019 | 3 | 0 | 3 | 04/10/2019 | 04/10/2019 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2019 | Connected |  | N | Hopedale-West | Closed
National Grid | LOWELL | 701420 | 01854 | 5.76 | Solar | 05_14_2L3 | 06/26/2025 | 07/31/2025 | 4 | 0 | 4 | 08/01/2025 | 08/01/2025 | 27 | 11 | 16 | 09/22/2025 | 10/07/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 10/07/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 10/10/2025 |  | 10/30/2026 | N | EXP | 365 | 03/27/2026 |  | 6 | 0 | 6 |  |  |  | Construction |  | N | Hopedale-West | Closed
National Grid | WESTFORD | 737243 | 01886 | 480 | Solar | 05_14_57L3 | 03/26/2026 |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Hopedale-West | Closed
National Grid | TEWKSBURY | 382224 | 01876 | 15.2 | Solar | 05_14_70L8 | 09/15/2021 | 10/14/2021 | 21 | 19 | 2 | 10/15/2021 | 10/15/2021 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 | 09/15/2021 | 5/2/2023 | Y | EXP | 365 | 04/06/2022 | 05/02/2022 | 27 | 0 | 27 |  |  | 5/20/2022 | Connected |  | N | Hopedale-West | Closed
National Grid | LAWRENCE | 306308 | 01841 | 7.6 | Solar | 05_14_8L2 | 08/28/2020 | 09/02/2020 | 2 | 0 | 2 | 09/03/2020 | 09/03/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 8/2/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West | Closed - Construction Hold
National Grid | WORCESTER | 176357 | 01602 | 10 | Solar | 05_01_23W3 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2015 |  | 10/30/2015 | N | EXP | 163 |  |  | 0 | 0 | 0 | 7/23/2015 | 7/23/2015 | 11/24/2015 | Connected |  | N | Shutesbury | Closed
National Grid | OXFORD | 701278 | 01540 | 18.24 | Solar | 05_01_406L4 | 07/02/2025 | 07/17/2025 | 9 | 7 | 2 | 07/18/2025 | 07/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Shutesbury | Closed
National Grid | BROOKFIELD | 205262 | 01506 | 7.6 | Solar | 05_01_552L3 | 01/07/2019 | 01/17/2019 | 7 | 0 | 7 | 01/18/2019 | 01/18/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 |  | 2/28/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2019 | Connected |  | N | Shutesbury | Closed
National Grid | FALL RIVER | 212413 | 02724 | 233.3 | Solar | 05_05_106W42 | 03/04/2019 | 03/15/2019 | 8 | 4 | 4 | 03/18/2019 | 03/18/2019 | 7 | 3 | 4 | 04/17/2019 | 05/07/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 05/07/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Shutesbury | Closed
National Grid | ATTLEBORO | 608945 | 02703 | 10 | Solar | 05_05_2J2 | 05/06/2024 | 05/16/2024 | 1 | 0 | 1 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 | 05/06/2024 | 6/6/2025 | Y | EXP | 365 | 08/21/2024 | 09/26/2024 | 37 | 0 | 37 |  |  | 10/25/2024 | Connected |  | N | Shutesbury | Closed
National Grid | AMESBURY | 175681 | 01913 | 17 | Solar | 05_14_5J14 | 11/19/2014 | 11/19/2014 | 15 | 0 | 15 | 12/15/2014 | 12/15/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2015 |  | 1/31/2015 | N | EXP | 24 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 10/29/2015 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | MANCHESTER | 221773 | 01944 | 0 | Solar | 05_12_51T1 | 04/23/2019 | 04/30/2019 | 4 | 0 | 4 | 05/01/2019 | 05/01/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/28/2019 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | LOWELL | 753872 | 01854 | 60 | Solar | 05_14_2L3 | 03/03/2026 |  | 21 | 15 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | MPL-East | Scoping Meeting
National Grid | WESTFORD | 174461 | 01886 | 34.2 | Solar | 05_14_57L3 | 09/01/2011 | 09/01/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/01/2011 | 10/31/2012 | Y | EXP | 42 |  |  | 0 | 0 | 0 | 1/10/2013 | 1/10/2013 | 1/25/2013 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | BILLERICA | 526597 | 01821 | 15.2 | Solar | 05_14_70L8 | 05/19/2023 | 05/26/2023 | 5 | 5 | 0 | 05/30/2023 | 05/30/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 |  | 7/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2023 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | LAWRENCE | 322575 | 01841 | 10 | Solar | 05_14_8L2 | 12/22/2020 | 12/30/2020 | 4 | 0 | 4 | 12/31/2020 | 12/31/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/22/2020 |  | Y | EXP | 365 | 04/14/2021 | 04/26/2021 | 12 | 0 | 12 |  |  | 5/29/2021 | Connected |  | N | Ayer-Clinton | Closed
National Grid | WORCESTER | 176882 | 01602 | 7.53 | Solar | 05_01_23W3 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2016 |  | 5/10/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 10/27/2016 | 10/27/2016 | 10/27/2016 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | OXFORD | 710676 | 01540 | 15.58 | Solar | 05_01_406L4 | 08/08/2025 | 08/18/2025 | 5 | 0 | 5 | 08/19/2025 | 08/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N | Millbury-Grafton | Closed
National Grid | NORTH BROOKFIELD | 211642 | 01535 | 4980 | Solar | 05_01_552L3 | 02/27/2019 | 04/02/2019 | 24 | 17 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2019 | 04/24/2019 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | FALL RIVER | 581461 | 02724 | 6 | Solar | 05_05_106W42 | 02/08/2024 | 02/21/2024 | 8 | 5 | 3 | 02/22/2024 | 02/22/2024 | 13 | 7 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2024 | Connected |  | N | MPL-Northwest | Study Complete
National Grid | ATTLEBORO | 174441 | 02703 | 1875 | Solar | 05_05_2J3 | 06/28/2012 | 06/28/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/11/2012 | 08/21/2012 | 29 | 0 | 29 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/15/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | Closed
National Grid | AMESBURY | 339779 | 01913 | 133.2 | Solar | 05_14_5J14 | 02/12/2021 | 03/04/2021 | 12 | 3 | 9 | 03/05/2021 | 03/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Gardner-Winchendon | Scoping Meeting
National Grid | BEVERLY | 225352 | 01915 | 10 | Solar | 05_12_51T1 | 05/06/2019 | 05/16/2019 | 8 | 8 | 0 | 05/17/2019 | 05/17/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2019 |  | 12/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2019 | Connected |  | Y | Barre-Athol | Scoping Meeting
National Grid | LOWELL | 175901 | 01851 | 224 | Solar | 05_14_2L3 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2015 |  | 10/4/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 3/9/2016 | 3/9/2016 | 3/18/2016 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | WESTFORD | 175011 | 01886 | 235 | Solar | 05_14_57L3 | 08/31/2011 | 08/31/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2011 | 08/31/2011 | 11/30/2012 | Y | EXP | 338 | 01/09/2012 | 01/09/2012 | 0 | 0 | 0 | 6/3/2014 | 6/3/2014 | 5/11/2012 | Connected |  | N | Millbury-Grafton | Closed
National Grid | BILLERICA | 529445 | 01821 | 6 | Solar | 05_14_70L8 | 09/06/2023 | 06/06/2023 | 3 | 2 | 1 | 09/12/2023 | 09/12/2023 | 116 | 99 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 4/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N | Ayer-Clinton | Closed
National Grid | LAWRENCE | 349178 | 01841 | 9.8 | Solar | 05_14_8L2 | 04/16/2021 | 04/26/2021 | 4 | 0 | 4 | 04/27/2021 | 04/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  | 6/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Gardner-Winchendon | Scoping Meeting
National Grid | LEICESTER | 177039 | 01524 | 800 | Solar | 05_01_23W3 | 07/27/2016 | 07/27/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/26/2016 | 59 | 44 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2017 | 07/27/2016 | 3/15/2019 | Y | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-Northwest | Study Complete
National Grid | AUBURN | 716071 | 01501 | 15.2 | Solar | 05_01_406L4 | 09/02/2025 | 09/09/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2026 | Connected |  | Y | MPL-Northwest | Study Complete
National Grid | SPENCER | 289954 | 01562 | 0 | Other | 05_01_552L3 | 05/15/2020 | 05/22/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2020 | 10/24/2020 | 43 | 27 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton | Closed
National Grid | FALL RIVER | 661388 | 02721 | 7.6 | Solar | 05_05_106W42 | 12/24/2024 | 01/29/2025 | 9 | 4 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 | 12/24/2024 | 3/24/2026 | Y | EXP | 365 | 05/02/2025 | 07/16/2025 | 76 | 0 | 76 |  |  | 7/22/2025 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | ATTLEBORO | 177231 | 02703 | 72 | Solar | 05_05_2J3 | 11/03/2016 | 11/03/2016 | 8 | 8 | 0 | 11/17/2016 | 11/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/03/2016 | 11/9/2017 | Y | EXP | 352 | 03/02/2017 | 03/20/2017 | 12 | 0 | 12 | 5/16/2017 | 5/16/2017 | 5/22/2017 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | AMESBURY | 425281 | 01913 | 133.2 | Solar | 05_14_5J14 | 04/20/2022 | 05/04/2022 | 10 | 0 | 10 |  |  | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-Northwest | Study Complete
National Grid | WENHAM | 252036 | 01984 | 0 | Solar | 05_12_51T1 | 09/04/2019 | 09/11/2019 | 4 | 0 | 4 | 09/12/2019 | 09/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2019 |  | 12/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West | Time Frame Suspension
National Grid | CHELMSFORD | 176474 | 01863 | 21.8 | Solar | 05_14_2L3 | 03/23/2016 | 03/23/2016 | 3 | 3 | 0 | 03/29/2016 | 03/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2016 |  | 3/29/2017 | N | EXP | 334 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | WESTFORD | 175226 | 01886 | 12 | Solar | 05_14_57L3 | 01/06/2015 | 01/06/2015 | 8 | 4 | 4 | 01/17/2015 | 01/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 10/1/2015 | 10/1/2015 | 6/6/2016 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | BILLERICA | 569114 | 01821 | 0 | Solar | 05_14_70L8 | 11/06/2023 | 11/30/2023 | 17 | 15 | 2 | 12/01/2023 | 12/01/2023 | 54 | 31 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2024 | Connected |  | N | Ayer-Clinton | Closed
National Grid | LAWRENCE | 413386 | 01841 | 6 | Solar | 05_14_8L2 | 03/08/2022 | 03/09/2022 | 1 | 0 | 1 | 03/10/2022 | 03/10/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 | 03/08/2022 | 7/12/2024 | Y | EXP | 365 | 05/09/2023 | 06/08/2023 | 31 | 0 | 31 |  |  | 8/25/2023 | Connected |  | N | MPL-Northwest | Study Complete
National Grid | WORCESTER | 178253 | 01602 | 7.6 | Solar | 05_01_23W3 | 03/27/2018 | 03/27/2018 | 4 | 0 | 4 | 04/03/2018 | 04/03/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 4/2/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton | Closed
National Grid | OXFORD | 715605 | 01540 | 20 | Solar | 05_01_406L4 | 09/02/2025 | 09/09/2025 | 4 | 2 | 2 | 09/10/2025 | 09/10/2025 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West | Time Frame Suspension - Construction Hold
National Grid | NORTH BROOKFIELD | 290420 | 01535 | 0 | Other | 05_01_552L3 | 10/27/2020 | 12/22/2020 | 38 | 30 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2020 | 01/19/2021 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Scoping Meeting
National Grid | FALL RIVER | 663644 | 02721 | 10 | Solar | 05_05_106W42 | 01/03/2025 | 01/16/2025 | 7 | 3 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 01/03/2025 | 3/17/2026 | Y | EXP | 365 | 03/08/2025 | 08/12/2025 | 158 | 0 | 158 |  |  | 8/29/2025 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | SOUTHBOROUGH | 555478 | 01772 | 240 | Solar | 05_05_310W3 | 09/15/2023 | 09/29/2023 | 10 | 1 | 9 | 10/02/2023 | 10/02/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 | 09/15/2023 | 7/8/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y | Webster-Southbridge-Charlton | Closed
National Grid | AMESBURY | 673138 | 01913 | 30 | Solar | 05_14_5J14 | 05/12/2025 | 05/14/2025 | 2 | 0 | 2 | 05/15/2025 | 05/15/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Barre-Athol | Scoping Meeting
National Grid | GLOUCESTER | 260745 | 01930 | 5.76 | Solar | 05_12_51T1 | 10/18/2019 | 11/13/2019 | 1 | 0 | 1 | 11/14/2019 | 11/14/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 | 10/18/2019 | 7/9/2020 | Y | EXP | 365 | 02/29/2020 | 02/28/2020 | 0 | 0 | 0 |  |  | 3/4/2020 | Connected |  | N | Hopedale-West | Time Frame Suspension - Start Study
National Grid | LOWELL | 176504 | 01854 | 150 | Solar | 05_14_2L3 | 02/09/2016 | 02/09/2016 | 7 | 7 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2016 |  | 2/15/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 | 12/7/2016 | 12/7/2016 | 11/23/2016 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | WESTFORD | 175693 | 01886 | 18 | Solar | 05_14_57L3 | 05/23/2014 | 05/23/2014 | 5 | 0 | 5 | 06/03/2014 | 06/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2014 |  | 8/29/2014 | N | EXP | 58 |  |  | 0 | 0 | 0 | 7/2/2014 | 7/2/2014 | 10/13/2014 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | TEWKSBURY | 570311 | 01876 | 7.6 | Solar | 05_14_70L8 | 11/15/2023 | 12/07/2023 | 15 | 13 | 2 | 12/08/2023 | 12/08/2023 | 30 | 8 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 | 11/15/2023 | 2/20/2025 | Y | EXP | 365 | 03/19/2024 | 03/18/2024 | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | LAWRENCE | 428539 | 01841 | 7.6 | Solar | 05_14_8L2 | 05/19/2022 | 05/24/2022 | 4 | 3 | 1 | 05/25/2022 | 05/25/2022 | 122 | 105 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 | 05/19/2022 | 4/9/2024 | Y | EXP | 365 | 03/15/2023 | 04/08/2023 | 25 | 0 | 25 |  |  | 6/12/2023 | Connected |  | N | Hopedale-West | Closed - Start Study
National Grid | WORCESTER | 184545 | 01602 | 7.6 | Solar | 05_01_23W3 | 05/31/2018 | 05/31/2018 | 3 | 0 | 3 | 06/07/2018 | 06/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland | Scoping Meeting
National Grid | OXFORD | 730948 | 01540 | 15.2 | Solar | 05_01_406L4 | 11/03/2025 | 11/07/2025 | 4 | 0 | 4 | 11/10/2025 | 11/10/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N | Millbury-Grafton | Closed
National Grid | SPENCER | 301406 | 01562 | 400 | Natural Gas | 05_01_552L3 | 12/09/2020 | 12/21/2020 | 7 | 0 | 7 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-Northwest | Study Complete
National Grid | FALL RIVER | 518149 | 02720 | 250 | Natural Gas | 05_05_106W43 | 04/23/2024 | 06/24/2024 | 42 | 32 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/25/2024 | 07/19/2024 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 |  | 7/5/2026 | N | STD | 120 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | MARLBOROUGH | 744268 | 01752 | 50 | Solar | 05_05_310W3 | 01/09/2026 | 02/11/2026 | 20 | 11 | 9 | 02/12/2026 | 02/12/2026 | 35 | 22 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Spencer-Rutland | Scoping Meeting
National Grid | GLOUCESTER | 689590 | 01930 | 0 | Battery Add-On | 05_12_24J10 | 05/05/2025 | 06/02/2025 | 19 | 15 | 4 | 06/03/2025 | 06/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | MANCHESTER | 286147 | 01944 | 15.36 | Solar | 05_12_51T1 | 04/01/2020 | 04/03/2020 | 1 | 0 | 1 | 04/06/2020 | 04/06/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2020 |  | 10/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | Time Frame Suspension
National Grid | LOWELL | 176741 | 01851 | 150 | Solar | 05_14_2L3 | 10/30/2015 | 10/30/2015 | 4 | 4 | 0 | 11/06/2015 | 11/06/2015 | 424 | 56 | 368 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2016 |  | 9/7/2017 | N | EXP | 582 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton | Closed
National Grid | WESTFORD | 177025 | 01886 | 86.4 | Solar | 05_14_57L3 | 03/16/2017 | 03/16/2017 | 6 | 5 | 1 | 03/24/2017 | 03/24/2017 | 229 | 0 | 229 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2017 |  | 3/21/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Gardner-Winchendon | Scoping Meeting
National Grid | BILLERICA | 597903 | 01821 | 16.4 | Solar | 05_14_70L8 | 03/19/2024 | 03/21/2024 | 2 | 0 | 2 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2024 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | LAWRENCE | 459549 | 01841 | 6 | Solar | 05_14_8L2 | 11/18/2022 | 11/27/2022 | 5 | 0 | 5 | 11/28/2022 | 11/28/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2022 | 11/18/2022 | 5/16/2024 | Y | EXP | 365 | 09/12/2023 | 10/04/2023 | 23 | 0 | 23 |  |  | 10/10/2023 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | WORCESTER | 186320 | 01602 | 3.8 | Solar | 05_01_23W3 | 06/13/2018 | 06/13/2018 | 28 | 0 | 28 | 07/26/2018 | 07/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton | Closed
National Grid | STURBRIDGE | 648624 | 01518 | 4990 | Other | 05_01_408L1 | 02/20/2025 | 04/30/2025 | 49 | 39 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2025 | 05/29/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | MPL-East | Scoping Meeting
National Grid | NORTH BROOKFIELD | 366176 | 01535 | 10 | Solar | 05_01_552L3 | 07/30/2021 | 08/05/2021 | 5 | 2 | 3 | 08/06/2021 | 08/06/2021 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2021 |  | 10/15/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2021 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | FALL RIVER | 174885 | 02721 | 40 | Solar | 05_05_106W43 | 02/16/2013 | 02/16/2013 | 7 | 0 | 7 | 02/28/2013 | 02/28/2013 | 269 | 0 | 269 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2013 |  | 5/31/2013 | N | EXP | 59 |  |  | 0 | 0 | 0 | 4/2/2013 | 4/2/2013 |  | Withdrawn |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | SOUTHBOROUGH | 174781 | 01772 | 480 | Solar | 05_05_310W3 | 07/08/2013 | 07/08/2013 | 8 | 0 | 8 | 07/19/2013 | 07/19/2013 | 0 | 0 | 0 | 11/05/2013 | 01/23/2014 | 52 | 0 | 52 |  |  | 0 | 0 | 0 | 01/23/2014 | 52 | 0 | 52 |  |  | 0 | 0 | 0 | 2/11/2014 | 07/08/2013 | 12/20/2017 | Y | EXP | 1408 | 09/22/2017 | 10/16/2017 | 15 | 0 | 15 | 9/18/2017 | 9/18/2017 | 12/1/2017 | Connected |  | N | Millbury-Grafton | Closed
National Grid | GLOUCESTER | 731829 | 01930 | 16.24 | Solar | 05_12_24J10 | 12/04/2025 | 02/06/2026 | 42 | 25 | 17 | 02/09/2026 | 02/09/2026 | 36 | 24 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Hopedale-West | Time Frame Suspension
National Grid | GLOUCESTER | 291501 | 01930 | 3.8 | Solar | 05_12_51T1 | 05/25/2020 | 05/26/2020 | 0 | 0 | 0 | 05/27/2020 | 05/27/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 |  | 5/25/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Scoping Meeting
National Grid | LOWELL | 176838 | 01851 | 150 | Solar | 05_14_2L3 | 10/30/2015 | 10/30/2015 | 4 | 0 | 4 | 11/06/2015 | 11/06/2015 | 312 | 56 | 256 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2016 | 10/30/2015 | 11/7/2016 | Y | EXP | 278 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West | Time Frame Suspension
National Grid | WESTFORD | 198756 | 01886 | 174 | Solar | 05_14_57L3 | 11/06/2018 | 11/27/2018 | 0 | 0 | 0 | 11/28/2018 | 11/28/2018 | 11 | 0 | 11 | 04/15/2019 | 05/01/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 05/01/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 6/14/2019 |  | 10/15/2020 | N | EXP | 489 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Ayer-Clinton | Closed
National Grid | BILLERICA | 602386 | 01821 | 5.76 | Solar | 05_14_70L8 | 04/17/2024 | 04/18/2024 | 1 | 0 | 1 | 04/19/2024 | 04/19/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland | Scoping Meeting
National Grid | LAWRENCE | 476315 | 01841 | 0 | Solar | 05_14_8L2 | 06/08/2023 | 08/15/2023 | 46 | 45 | 1 | 08/16/2023 | 08/16/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2023 |  | 9/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton | Closed
National Grid | WORCESTER | 198669 | 01602 | 5 | Solar | 05_01_23W3 | 10/16/2018 | 02/20/2019 | 87 | 83 | 4 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton | Closed
National Grid | STURBRIDGE | 175914 | 01566 | 1500 | Solar | 05_01_408L1 | 03/12/2015 | 03/12/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2015 | 05/12/2015 | 38 | 0 | 38 |  | 0 | 0 | 0 | 07/12/2016 | 10/06/2016 | 61 | 0 | 61 | 10/11/2016 | 03/12/2015 | 10/31/2017 | Y | STD | 385 | 06/22/2017 | 02/28/2018 | 165 | 0 | 165 | 10/18/2017 | 10/18/2017 | 11/29/2017 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | BROOKFIELD | 376647 | 01515 | 3.8 | Solar | 05_01_552L3 | 09/16/2021 | 10/12/2021 | 18 | 17 | 1 | 10/13/2021 | 10/13/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 |  | 10/11/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol | Scoping Meeting
National Grid | FALL RIVER | 176154 | 02720 | 56 | Solar | 05_05_106W43 | 08/28/2015 | 08/28/2015 | 3 | 3 | 0 | 09/03/2015 | 09/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2015 |  | 9/5/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 3/23/2016 | 3/23/2016 | 3/23/2016 | Connected |  | N | Millbury-Grafton | Closed
National Grid | MARLBOROUGH | 176778 | 01752 | 576 | Solar | 05_05_310W3 | 11/04/2015 | 11/04/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/06/2015 | 12/09/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/9/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West | Time Frame Suspension
National Grid | GLOUCESTER | 175642 | 01930 | 17 | Solar | 05_12_24J10 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 |  | 2/6/2015 | N | EXP | 88 |  |  | 0 | 0 | 0 | 6/9/2016 | 6/9/2016 | 6/14/2016 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | MANCHESTER | 292808 | 01944 | 0 | Battery Add-On | 05_12_51T1 | 05/20/2020 | 05/29/2020 | 6 | 5 | 1 | 06/01/2020 | 06/01/2020 | 112 | 53 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Scoping Meeting
National Grid | LOWELL | 178013 | 01851 | 150 | Solar | 05_14_2L3 | 10/30/2015 | 10/30/2015 | 4 | 0 | 4 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2016 |  | 7/4/2018 | N | EXP | 882 |  |  | 0 | 0 | 0 | 7/18/2017 | 7/18/2017 | 7/16/2017 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | WESTFORD | 232316 | 01886 | 249 | Solar | 05_14_57L3 | 11/19/2019 | 01/09/2020 | 19 | 15 | 4 | 04/02/2020 | 04/02/2020 | 16 | 0 | 16 | 05/21/2020 | 10/28/2020 | 100 | 3 | 97 |  |  | 0 | 0 | 0 | 10/28/2020 | 100 | 3 | 97 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 12/30/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West | Closed - Construction Hold
National Grid | TEWKSBURY | 625684 | 01876 | 10 | Solar | 05_14_70L8 | 07/17/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2024 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | LAWRENCE | 533125 | 01841 | 10 | Solar | 05_14_8L2 | 06/16/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 | 06/16/2023 | 8/4/2024 | Y | EXP | 365 | 12/06/2023 | 12/26/2023 | 21 | 3 | 18 |  |  |  | Withdrawn |  | Y | Millbury-Grafton | Closed
National Grid | WORCESTER | 198437 | 01602 | 3.8 | Solar | 05_01_23W3 | 10/12/2018 |  | 69 | 25 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | Closed
National Grid | STURBRIDGE | 193813 | 01566 | 86.4 | Solar | 05_01_408L1 | 08/17/2018 | 08/23/2018 | 3 | 0 | 3 | 08/24/2018 | 08/24/2018 | 248 | 0 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West | Time Frame Suspension
National Grid | BROOKFIELD | 447837 | 01515 | 7.25 | Solar | 05_01_552L3 | 08/24/2022 | 08/30/2022 | 4 | 0 | 4 | 08/31/2022 | 08/31/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | Time Frame Suspension
National Grid | FALL RIVER | 176863 | 02721 | 40.25 | Solar | 05_05_106W43 | 01/21/2016 | 01/21/2016 | 4 | 4 | 0 | 01/27/2016 | 01/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 1/26/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 10/18/2016 | 10/18/2016 | 10/24/2016 | Connected |  | N | Shutesbury | Closed
National Grid | SOUTHBOROUGH | 373284 | 01772 | 10 | Solar | 05_05_310W3 | 08/02/2021 | 08/05/2021 | 3 | 2 | 1 | 08/06/2021 | 08/06/2021 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2021 |  | 9/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2022 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | GLOUCESTER | 176689 | 01930 | 10 | Solar | 05_12_24J10 | 02/19/2016 | 02/19/2016 | 2 | 2 | 0 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2016 |  | 2/24/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 8/16/2016 | 8/16/2016 | 8/16/2016 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | GLOUCESTER | 292006 | 01930 | 10 | Solar | 05_12_51T1 | 06/09/2020 | 06/16/2020 | 5 | 5 | 0 | 06/17/2020 | 06/17/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 6/14/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton | Closed
National Grid | LOWELL | 178705 | 01851 | 249.8 | Solar | 05_14_2L3 | 03/21/2018 | 03/21/2018 | 11 | 0 | 11 | 04/05/2018 | 04/05/2018 | 38 | 13 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 3/31/2021 | N | EXP | 489 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | TYNGSBORO | 243897 | 01879 | 0 | Solar | 05_14_57L3 | 07/17/2019 | 08/07/2019 | 14 | 9 | 5 | 08/08/2019 | 08/08/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2019 | Connected |  | N | Brockton-North | Closed
National Grid | TEWKSBURY | 651555 | 01876 | 7.6 | Solar | 05_14_70L8 | 11/01/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/01/2024 | 2/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N | Brockton-North | Closed
National Grid | LAWRENCE | 537941 | 01841 | 8.7 | Solar | 05_14_8L2 | 12/04/2023 |  | 42 | 30 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North | Closed
National Grid | WORCESTER | 206478 | 01602 | 250 | Solar | 05_01_23W3 | 03/12/2019 | 03/14/2019 | 1 | 1 | 0 |  |  | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2020 | 03/12/2019 | 3/23/2023 | Y | STD | 823 | 10/05/2021 | 08/19/2022 | 319 | 4 | 315 |  |  | 3/9/2023 | Connected |  | N | Brockton-North | Closed
National Grid | STURBRIDGE | 191478 | 01518 | 15.2 | Solar | 05_01_408L1 | 07/23/2018 | 08/29/2018 | 26 | 0 | 26 | 08/30/2018 | 08/30/2018 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Scituate | Closed
National Grid | SPENCER | 547266 | 01562 | 10 | Solar | 05_01_552L3 | 09/07/2023 | 10/06/2023 | 21 | 20 | 1 | 10/10/2023 | 10/10/2023 | 6 | 0 | 6 | 10/27/2023 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/15/2023 |  | 12/19/2024 | N | EXP | 365 | 01/18/2024 | 04/22/2024 | 96 | 23 | 73 |  |  |  | Withdrawn |  | N | Scituate | Closed
National Grid | FALL RIVER | 401104 | 02721 | 0 | Other | 05_05_106W43 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 01/27/2022 | 8 | 0 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South | Closed
National Grid | SOUTHBOROUGH | 417351 | 01772 | 11.4 | Solar | 05_05_310W3 | 03/28/2022 | 03/29/2022 | 1 | 0 | 1 | 03/30/2022 | 03/30/2022 | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-South | Closed
National Grid | GLOUCESTER | 183953 | 01930 | 6.44 | Solar | 05_12_24J10 | 05/09/2018 | 05/09/2018 | 8 | 0 | 8 | 05/22/2018 | 05/22/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2018 |  | 6/24/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2018 | Connected |  | N | Brockton-South | Closed
National Grid | BEVERLY | 295399 | 01915 | 0 | Battery Add-On | 05_12_51T1 | 06/13/2020 | 06/22/2020 | 5 | 4 | 1 | 06/23/2020 | 06/23/2020 | 102 | 81 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 |  | 3/3/2022 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South | Closed
National Grid | LOWELL | 184041 | 01851 | 73.3 | Solar | 05_14_2L3 | 04/30/2018 | 04/30/2018 | 0 | 0 | 0 | 05/01/2018 | 05/01/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 4/27/2019 | N | EXP | 332 |  |  | 0 | 0 | 0 |  |  | 1/8/2019 | Connected |  | N | Brockton-South | Closed
National Grid | TYNGSBORO | 242048 | 01879 | 16 | Solar | 05_14_57L3 | 07/09/2019 | 07/23/2019 | 9 | 9 | 0 | 07/24/2019 | 07/24/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 11/11/2019 | N | EXP | 98 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N | Brockton-South | Closed
National Grid | TEWKSBURY | 653107 | 01876 | 2.32 | Solar | 05_14_70L8 | 11/14/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N | Hopedale-East | Closed
National Grid | LAWRENCE | 555249 | 01841 | 5.76 | Solar | 05_14_8L2 | 09/27/2023 | 11/15/2023 | 34 | 30 | 4 | 11/16/2023 | 11/16/2023 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East | Closed
National Grid | WORCESTER | 230757 | 01602 | 7.6 | Solar | 05_01_23W3 | 07/24/2019 | 07/26/2019 | 1 | 0 | 1 | 07/29/2019 | 07/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 10/15/2019 | N | EXP | 69 |  |  | 0 | 0 | 0 |  |  | 9/10/2019 | Connected |  | N | Marlborough | Closed
National Grid | STURBRIDGE | 503087 | 01566 | 22.62 | Solar | 05_01_408L1 | 02/17/2023 | 02/21/2023 | 1 | 0 | 1 | 02/22/2023 | 02/22/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2023 | Connected |  | N | Marlborough | Closed
National Grid | SPENCER | 547263 | 01562 | 10 | Solar | 05_01_552L3 | 09/07/2023 | 10/10/2023 | 23 | 22 | 1 | 10/11/2023 | 10/11/2023 | 5 | 0 | 5 | 10/27/2023 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/15/2023 |  | 12/19/2024 | N | EXP | 365 | 01/18/2024 | 04/22/2024 | 96 | 23 | 73 |  |  |  | Withdrawn |  | N | Fall River-South | Closed
National Grid | FALL RIVER | 602713 | 02720 | 7.6 | Solar | 05_05_106W43 | 04/09/2024 | 04/13/2024 | 1 | 0 | 1 | 08/07/2024 | 08/07/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2024 | 04/09/2024 | 8/21/2025 | Y | EXP | 365 | 09/06/2024 | 09/20/2024 | 15 | 0 | 15 |  |  | 10/4/2024 | Connected |  | N | Fall River-South | Closed
National Grid | SOUTHBOROUGH | 439607 | 01772 | 15.2 | Solar | 05_05_310W3 | 06/23/2022 | 06/29/2022 | 4 | 0 | 4 | 06/30/2022 | 06/30/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 |  | 8/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/25/2023 | Connected |  | N | Fall River-South | Closed
National Grid | GLOUCESTER | 325646 | 01930 | 10 | Solar | 05_12_24J11 | 11/12/2020 | 01/27/2021 | 49 | 47 | 2 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 |  | 1/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2021 | Connected |  | N | Fall River-South | Closed
National Grid | BEVERLY | 298665 | 01915 | 10 | Solar | 05_12_51T1 | 06/26/2020 | 07/06/2020 | 6 | 1 | 5 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  | 6/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2020 | Connected |  | N | Bridgewater | Closed
National Grid | LOWELL | 381753 | 01851 | 10 | Solar | 05_14_2L3 | 10/11/2021 | 12/07/2021 | 3 | 1 | 2 | 10/18/2021 | 10/18/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2022 | Connected |  | Y | Bridgewater | Closed
National Grid | DUNSTABLE | 248827 | 01827 | 0 | Solar | 05_14_57L3 | 08/14/2019 | 08/19/2019 | 3 | 3 | 0 | 08/20/2019 | 08/20/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2019 |  | 9/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2020 | Connected |  | N | Attleboro | Closed
National Grid | BILLERICA | 657260 | 01821 | 3.8 | Solar | 05_14_70L8 | 11/27/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/27/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | Y | Attleboro | Closed
National Grid | LAWRENCE | 555821 | 01841 | 6 | Solar | 05_14_8L2 | 09/19/2023 | 09/22/2023 | 4 | 3 | 1 | 09/25/2023 | 09/25/2023 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 |  | 12/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2023 | Connected |  | N | Attleboro | Closed
National Grid | WORCESTER | 424314 | 01602 | 3.8 | Solar | 05_01_23W3 | 04/15/2022 | 05/27/2022 | 1 | 0 | 1 | 05/31/2022 | 05/31/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2022 | 04/15/2022 | 9/9/2023 | Y | EXP | 365 | 08/25/2022 | 09/07/2022 | 14 | 0 | 14 |  |  | 9/12/2022 | Connected |  | N | Hanover | Closed
National Grid | STURBRIDGE | 516424 | 01566 | 7.6 | Solar | 05_01_408L1 | 04/04/2023 | 04/10/2023 | 5 | 4 | 1 | 04/11/2023 | 04/11/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2023 |  | 6/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2023 | Connected |  | N | Hanover | Closed
National Grid | SPENCER | 547258 | 01562 | 10 | Solar | 05_01_552L3 | 09/07/2023 | 09/13/2023 | 4 | 3 | 1 | 09/14/2023 | 09/14/2023 | 23 | 0 | 23 | 10/27/2023 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/15/2023 |  | 11/19/2024 | N | EXP | 365 | 01/18/2024 | 03/07/2024 | 50 | 0 | 50 |  |  | 4/1/2024 | Connected |  | N | Hanover | Closed
National Grid | FALL RIVER | 641015 | 02720 | 10 | Solar | 05_05_106W43 | 09/25/2024 | 10/25/2024 | 10 | 9 | 1 | 10/28/2024 | 10/28/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 1/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N | Hanover | Closed
National Grid | SOUTHBOROUGH | 448026 | 01772 | 10 | Solar | 05_05_310W3 | 07/29/2022 | 08/01/2022 | 1 | 0 | 1 | 08/02/2022 | 08/02/2022 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2022 | 07/29/2022 | 9/6/2023 | Y | EXP | 365 | 10/11/2022 | 03/03/2023 | 144 | 0 | 144 |  |  | 3/7/2023 | Connected |  | N | Hanover | Closed
National Grid | GLOUCESTER | 677404 | 01930 | 8.36 | Solar | 05_12_24J11 | 03/12/2025 | 03/26/2025 | 10 | 6 | 4 | 03/27/2025 | 03/27/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N | Hanover | Closed
National Grid | ESSEX | 300315 | 01929 | 0 | Solar | 05_12_51T1 | 07/08/2020 | 07/13/2020 | 2 | 2 | 0 | 07/14/2020 | 07/14/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/12/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | LOWELL | 406001 | 01851 | 0 | Battery Add-On | 05_14_2L3 | 02/01/2022 | 02/07/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2022 | 02/25/2022 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East | Closed
National Grid | WESTFORD | 263166 | 01886 | 10 | Solar | 05_14_57L3 | 10/31/2019 | 11/01/2019 | 1 | 1 | 0 | 11/04/2019 | 11/04/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 |  | 2/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2020 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | TEWKSBURY | 672610 | 01876 | 5.76 | Solar | 05_14_70L8 | 02/18/2025 | 03/17/2025 | 8 | 2 | 6 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | METHUEN | 573304 | 01844 | 10.036 | Solar | 05_14_8L2 | 11/24/2023 | 11/29/2023 | 3 | 0 | 3 | 11/30/2023 | 11/30/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | Time Frame Suspension
National Grid | WORCESTER | 527877 | 01602 | 10 | Solar | 05_01_23W3 | 05/31/2023 | 06/05/2023 | 4 | 3 | 1 | 06/06/2023 | 06/06/2023 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2023 | 05/31/2023 | 8/3/2024 | Y | EXP | 365 | 08/10/2023 | 08/28/2023 | 19 | 0 | 19 |  |  | 10/6/2023 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | STURBRIDGE | 567984 | 01518 | 4956 | Solar | 05_01_408L1 | 04/15/2024 |  | 170 | 160 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol | Scoping Meeting
National Grid | SPENCER | 561832 | 01562 | 10 | Solar | 05_01_552L3 | 10/10/2023 | 10/11/2023 | 1 | 0 | 1 | 10/12/2023 | 10/12/2023 | 56 | 33 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2024 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | FALL RIVER | 729508 | 02723 | 240 | Solar | 05_05_106W44 | 10/31/2025 | 12/03/2025 | 21 | 12 | 9 | 12/04/2025 | 12/04/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Brockton-South | Closed
National Grid | SOUTHBOROUGH | 485238 | 01772 | 15.2 | Solar | 05_05_310W3 | 12/13/2022 | 12/14/2022 | 1 | 0 | 1 | 12/15/2022 | 12/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 |  | 2/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N | Somerset | Closed
National Grid | GLOUCESTER | 691429 | 01930 | 14.79 | Solar | 05_12_24J11 | 05/14/2025 | 05/29/2025 | 9 | 3 | 6 | 05/30/2025 | 05/30/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 | 05/14/2025 | 7/14/2026 | Y | EXP | 365 | 09/26/2025 | 11/18/2025 | 54 | 0 | 54 |  |  | 11/21/2025 | Connected |  | N | Somerset | Closed
National Grid | GLOUCESTER | 302762 | 01930 | 10 | Solar | 05_12_51T1 | 07/29/2020 | 07/31/2020 | 1 | 1 | 0 | 08/03/2020 | 08/03/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 | 07/29/2020 | 7/30/2021 | Y | EXP | 365 | 01/21/2021 | 03/16/2021 | 54 | 0 | 54 |  |  | 5/6/2021 | Connected |  | N | Hopedale-West | Time Frame Suspension - Completion Documents Hold
National Grid | LOWELL | 461779 | 01851 | 0 | Solar | 05_14_2L3 | 09/29/2022 | 09/30/2022 | 1 | 0 | 1 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 |  | 1/13/2024 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | TYNGSBORO | 297374 | 01879 | 0 | Solar | 05_14_57L3 | 06/19/2020 | 06/22/2020 | 0 | 0 | 0 | 06/23/2020 | 06/23/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2021 | Connected |  | N | Hopedale-East | Closed
National Grid | TEWKSBURY | 710520 | 01876 | 18.24 | Solar | 05_14_70L8 | 08/07/2025 | 08/14/2025 | 4 | 1 | 3 | 08/15/2025 | 08/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N | Millbury-Grafton | Closed
National Grid | LAWRENCE | 579143 | 01841 | 10 | Solar | 05_14_8L2 | 01/10/2024 | 01/30/2024 | 14 | 12 | 2 | 01/31/2024 | 01/31/2024 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 |  | 6/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2024 | Connected |  | N | Marlborough | Closed
National Grid | WORCESTER | 575782 | 01602 | 7.83 | Solar | 05_01_23W3 | 12/27/2023 | 12/28/2023 | 1 | 0 | 1 | 12/29/2023 | 12/29/2023 | 22 | 0 | 22 | 02/27/2024 | 03/27/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 03/27/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 3/22/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North | Closed
National Grid | STURBRIDGE | 623841 | 01518 | 10 | Solar | 05_01_408L1 | 07/10/2024 | 07/24/2024 | 5 | 0 | 5 | 07/25/2024 | 07/25/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2024 | 07/10/2024 | 12/3/2025 | Y | EXP | 365 | 04/15/2025 | 10/27/2025 | 196 | 0 | 196 |  |  | 10/28/2025 | Connected |  | N | Brockton-North | Closed
National Grid | SPENCER | 562496 | 01562 | 5 | Solar | 05_01_552L3 | 10/20/2023 | 11/09/2023 | 14 | 11 | 3 | 11/13/2023 | 11/13/2023 | 21 | 0 | 21 | 12/21/2023 | 04/15/2024 | 78 | 1 | 77 |  |  | 0 | 0 | 0 | 04/15/2024 | 78 | 1 | 77 |  |  | 0 | 0 | 0 | 4/17/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Scoping Meeting
National Grid | FALL RIVER | 738197 | 02723 | 250 | Solar | 05_05_106W44 | 12/24/2025 | 01/13/2026 | 12 | 3 | 9 | 01/14/2026 | 01/14/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Fall River-South | Closed
National Grid | SOUTHBOROUGH | 556943 | 01772 | 0 | Solar | 05_05_310W3 | 09/20/2023 | 10/05/2023 | 12 | 11 | 1 | 10/06/2023 | 10/06/2023 | 45 | 22 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  | 3/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | GLOUCESTER | 177146 | 01930 | 25 | Solar | 05_12_24J2 | 08/08/2016 | 08/08/2016 | 0 | 0 | 0 | 08/09/2016 | 08/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2016 |  | 8/14/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 1/9/2017 | 1/9/2017 | 1/9/2017 | Connected |  | N | Hopedale-East | Closed
National Grid | BEVERLY | 312832 | 01915 | 10 | Solar | 05_12_51T1 | 09/15/2020 | 09/16/2020 | 0 | 0 | 0 | 09/17/2020 | 09/17/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 | 09/15/2020 | 10/14/2021 | Y | EXP | 365 | 02/05/2021 | 03/05/2021 | 28 | 0 | 28 |  |  | 3/16/2021 | Connected |  | N | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | LOWELL | 505742 | 01851 | 3.8 | Solar | 05_14_2L3 | 03/15/2023 | 03/20/2023 | 3 | 0 | 3 | 03/21/2023 | 03/21/2023 | 22 | 1 | 21 | 04/26/2023 | 05/31/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 05/31/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 5/18/2023 |  | 9/28/2024 | N | EXP | 365 | 07/29/2023 | 09/28/2023 | 62 | 0 | 62 |  |  | 10/13/2023 | Connected |  | Y | Gardner-Winchendon | Scoping Meeting
National Grid | WESTFORD | 299279 | 01886 | 10 | Solar | 05_14_57L3 | 07/01/2020 | 07/07/2020 | 3 | 0 | 3 | 07/08/2020 | 07/08/2020 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 |  | 7/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2020 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | TEWKSBURY | 709365 | 01876 | 15.2 | Solar | 05_14_70L8 | 08/04/2025 | 08/07/2025 | 3 | 0 | 3 | 08/08/2025 | 08/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N | Bridgewater | Closed
National Grid | LAWRENCE | 582651 | 01841 | 5.22 | Solar | 05_14_8L2 | 02/01/2024 | 02/06/2024 | 3 | 0 | 3 | 02/07/2024 | 02/07/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/01/2024 | 3/27/2025 | Y | EXP | 365 | 04/16/2024 | 08/28/2024 | 135 | 0 | 135 |  |  | 9/19/2024 | Connected |  | N | Methuen | Closed
National Grid | WORCESTER | 599599 | 01602 | 7.6 | Solar | 05_01_23W3 | 03/28/2024 | 04/01/2024 | 2 | 0 | 2 | 04/02/2024 | 04/02/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Methuen | Closed
National Grid | STURBRIDGE | 632114 | 01566 | 7.6 | Solar | 05_01_408L1 | 08/21/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 | 08/21/2024 | 9/20/2025 | Y | EXP | 365 | 11/14/2024 | 11/13/2024 | 0 | 0 | 0 |  |  | 12/10/2024 | Connected |  | N | Fall River-North | Closed
National Grid | BROOKFIELD | 570255 | 01515 | 10 | Solar | 05_01_552L3 | 12/18/2023 | 01/02/2024 | 9 | 7 | 2 | 01/03/2024 | 01/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2024 | 12/18/2023 | 2/7/2025 | Y | EXP | 365 | 03/08/2024 | 05/17/2024 | 71 | 0 | 71 |  |  | 10/9/2024 | Connected |  | N | Fall River-South | Closed
National Grid | FALL RIVER | 739526 | 02723 | 23.732 | Solar | 05_05_106W44 | 12/11/2025 | 12/16/2025 | 2 | 0 | 2 | 12/17/2025 | 12/17/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hopedale-East | Closed
National Grid | SOUTHBOROUGH | 613596 | 01772 | 7.6 | Solar | 05_05_310W3 | 05/28/2024 | 05/30/2024 | 2 | 0 | 2 | 05/31/2024 | 05/31/2024 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | N | Hopedale-East | Closed
National Grid | GLOUCESTER | 396049 | 01930 | 0 | Other | 05_12_24J2 | 01/04/2022 | 01/19/2022 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2022 | 03/01/2022 | 28 | 14 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East | Closed
National Grid | GLOUCESTER | 325210 | 01930 | 0 | Solar | 05_12_51T1 | 12/02/2020 | 01/04/2021 | 21 | 18 | 3 | 01/05/2021 | 01/05/2021 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2021 |  | 3/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2021 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | CHELMSFORD | 553547 | 01863 | 3.8 | Solar | 05_14_2L3 | 09/19/2023 | 09/20/2023 | 1 | 0 | 1 | 09/21/2023 | 09/21/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Worcester North - Dont Use | Closed
National Grid | WESTFORD | 297469 | 01886 | 15.2 | Solar | 05_14_57L3 | 06/30/2020 | 07/06/2020 | 3 | 0 | 3 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 7/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2020 | Connected |  | N | Worcester North - Dont Use | Closed
National Grid | ANDOVER | 715308 | 01845 | 0 | Solar | 05_14_71L1 | 08/28/2025 | 09/02/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Worcester North/South | Closed
National Grid | LAWRENCE | 591651 | 01841 | 0 | Solar | 05_14_8L2 | 06/25/2024 | 07/02/2024 | 6 | 1 | 5 | 07/02/2024 | 07/02/2024 | 73 | 64 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 |  | 10/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N | Somerset | Closed
National Grid | WORCESTER | 618070 | 01602 | 6 | Solar | 05_01_23W3 | 06/17/2024 | 07/09/2024 | 8 | 5 | 3 | 07/10/2024 | 07/10/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann | Closed
National Grid | STURBRIDGE | 651529 | 01518 | 5.76 | Solar | 05_01_408L1 | 11/12/2024 | 12/13/2024 | 7 | 4 | 3 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann | Closed
National Grid | NORTH BROOKFIELD | 575455 | 01535 | 15.2 | Solar | 05_01_552L3 | 12/13/2023 | 01/04/2024 | 15 | 8 | 7 | 01/05/2024 | 01/05/2024 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 3/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N | Cape Ann | Closed
National Grid | FALL RIVER | 174596 | 02723 | 26 | Solar | 05_05_106W44 | 10/18/2011 | 10/18/2011 | 2 | 0 | 2 | 11/15/2011 | 11/15/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2011 |  | 4/13/2012 | N | EXP | 108 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 4/13/2012 | Connected |  | N | Cape Ann | Closed
National Grid | SOUTHBOROUGH | 616124 | 01772 | 15.2 | Solar | 05_05_310W3 | 06/06/2024 | 06/14/2024 | 6 | 4 | 2 | 06/17/2024 | 06/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 |  | 7/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N | Cape Ann | Closed
National Grid | GLOUCESTER | 615112 | 01930 | 6 | Solar | 05_12_24J2 | 06/05/2024 | 06/18/2024 | 2 | 0 | 2 | 06/20/2024 | 06/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 | 06/05/2024 | 8/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2024 | Connected |  | N | Cape Ann | Closed
National Grid | BEVERLY | 327199 | 01915 | 10 | Solar | 05_12_51T1 | 11/19/2020 | 11/25/2020 | 3 | 0 | 3 | 11/27/2020 | 11/27/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 11/19/2020 | 4/26/2022 | Y | EXP | 365 | 04/09/2021 | 04/20/2021 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Y | Cape Ann | Closed
National Grid | LOWELL | 553845 | 01851 | 7.54 | Solar | 05_14_2L3 | 09/07/2023 | 12/07/2023 | 63 | 46 | 17 | 12/08/2023 | 12/08/2023 | 36 | 13 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2024 |  | 6/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2024 | Connected |  | N | Methuen/Haverhill | Closed - Pending
National Grid | WESTFORD | 329231 | 01886 | 7.6 | Solar | 05_14_57L3 | 12/03/2020 |  | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed
National Grid | ANDOVER | 177528 | 01845 | 66.6 | Solar | 05_14_71L1 | 09/11/2017 | 09/11/2017 | 21 | 20 | 1 | 10/11/2017 | 10/11/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2017 |  | 6/29/2018 | N | EXP | 260 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | LAWRENCE | 592133 | 01841 | 10 | Solar | 05_14_8L2 | 03/11/2024 | 03/14/2024 | 3 | 0 | 3 | 03/15/2024 | 03/15/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed
National Grid | WORCESTER | 631649 | 01602 | 5.12 | Solar | 05_01_23W3 | 08/09/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/09/2024 | 9/25/2025 | Y | EXP | 365 | 01/07/2025 | 05/21/2025 | 135 | 0 | 135 |  |  | 6/4/2025 | Connected |  | N | Billerica | Closed
National Grid | STURBRIDGE | 692690 | 01518 | 15.2 | Solar | 05_01_408L1 | 05/19/2025 | 05/23/2025 | 4 | 0 | 4 | 05/27/2025 | 05/27/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2025 | Connected |  | N | North Andover | Closed
National Grid | BROOKFIELD | 626719 | 01515 | 23 | Solar | 05_01_552L3 | 07/22/2024 | 07/25/2024 | 3 | 0 | 3 | 07/26/2024 | 07/26/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/22/2024 | 11/14/2025 | Y | EXP | 365 | 01/18/2025 | 08/11/2025 | 206 | 0 | 206 |  |  | 1/22/2026 | Connected |  | N | North Andover | Closed
National Grid | FALL RIVER | 175252 | 02723 | 20.64 | Solar | 05_05_106W44 | 11/05/2014 | 11/05/2014 | 6 | 3 | 3 | 11/17/2014 | 11/17/2014 | 710 | 0 | 710 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 12/1/2017 | N | EXP | 1107 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 |  | Withdrawn |  | Y | North Andover | Closed
National Grid | MARLBOROUGH | 174829 | 01752 | 270 | Solar | 05_05_310W4 | 12/01/2011 | 12/01/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2012 | 12/01/2011 | 7/9/2012 | Y | EXP | 178 | 06/20/2012 | 06/28/2012 | 6 | 0 | 6 | 8/8/2012 | 8/8/2012 | 7/9/2012 | Connected |  | N | North Andover | Closed
National Grid | GLOUCESTER | 664113 | 01930 | 5.76 | Solar | 05_12_24J2 | 01/07/2025 | 03/11/2025 | 7 | 2 | 5 | 03/12/2025 | 03/12/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | North Andover | Closed
National Grid | BEVERLY | 354200 | 01915 | 250 | Solar | 05_12_51T1 | 05/07/2021 | 05/26/2021 | 13 | 8 | 5 | 05/27/2021 | 05/27/2021 | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2021 |  | 10/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N | Tewksbury | Closed
National Grid | CHELMSFORD | 606324 | 01863 | 3.77 | Solar | 05_14_2L3 | 04/24/2024 | 05/28/2024 | 1 | 0 | 1 | 05/29/2024 | 05/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 |  | 7/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N | Tewksbury | Closed
National Grid | WESTFORD | 335256 | 01886 | 250 | Solar | 05_14_57L3 | 01/15/2021 | 01/26/2021 | 5 | 0 | 5 | 01/27/2021 | 01/27/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Beverly | Closed
National Grid | ANDOVER | 178518 | 01810 | 10 | Solar | 05_14_71L1 | 04/04/2018 | 04/04/2018 | 6 | 0 | 6 | 04/13/2018 | 04/13/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/10/2019 | N | EXP | 323 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Beverly | Closed
National Grid | LAWRENCE | 595888 | 01841 | 7.6 | Solar | 05_14_8L2 | 03/29/2024 | 04/03/2024 | 3 | 0 | 3 | 04/04/2024 | 04/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2024 |  | 5/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2024 | Connected |  | N | Adams-Deerfield | Closed
National Grid | WORCESTER | 634790 | 01602 | 10 | Solar | 05_01_23W3 | 08/22/2024 | 09/03/2024 | 1 | 0 | 1 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/22/2024 | 9/24/2025 | Y | EXP | 365 | 10/24/2024 | 03/21/2025 | 149 | 0 | 149 |  |  | 4/12/2025 | Connected |  | N | Adams-Deerfield | Closed
National Grid | STURBRIDGE | 694502 | 01566 | 17.6 | Solar | 05_01_408L1 | 05/28/2025 | 06/09/2025 | 2 | 0 | 2 | 08/18/2025 | 08/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Leominster | Closed
National Grid | BROOKFIELD | 628778 | 01515 | 10 | Solar | 05_01_552L3 | 07/30/2024 | 08/19/2024 | 4 | 0 | 4 | 08/20/2024 | 08/20/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N | Leominster | Closed
National Grid | FALL RIVER | 306648 | 02723 | 3.8 | Solar | 05_05_106W44 | 08/13/2020 | 08/17/2020 | 1 | 0 | 1 | 08/18/2020 | 08/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 |  | 5/3/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-Southwest | Closed
National Grid | MARLBOROUGH | 175196 | 01752 | 100 | Solar | 05_05_310W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N | MPL-Southwest | Closed
National Grid | GLOUCESTER | 672436 | 01930 | 5.76 | Solar | 05_12_24J2 | 02/17/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Northampton | Closed
National Grid | MANCHESTER | 365294 | 01944 | 9.86 | Solar | 05_12_51T1 | 06/23/2021 | 07/16/2021 | 17 | 14 | 3 | 07/19/2021 | 07/19/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2021 |  | 9/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2021 | Connected |  | N | Brockton-North | Closed
National Grid | LOWELL | 645283 | 01851 | 5.76 | Solar | 05_14_2L3 | 10/07/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/07/2024 | 12/10/2025 | Y | EXP | 365 | 01/15/2025 | 02/11/2025 | 28 | 0 | 28 |  |  | 2/21/2025 | Connected |  | N | Brockton-North | Closed
National Grid | WESTFORD | 340473 | 01886 | 7.6 | Solar | 05_14_57L3 | 02/04/2021 | 02/05/2021 | 0 | 0 | 0 | 02/08/2021 | 02/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  | 6/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2021 | Connected |  | N | Hopedale-East | Closed
National Grid | ANDOVER | 184342 | 01810 | 0 | Solar | 05_14_71L1 | 05/18/2018 | 05/18/2018 | 1 | 0 | 1 | 05/22/2018 | 05/22/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2018 |  | 5/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | Connected |  | N | Hopedale-East | Closed
National Grid | LAWRENCE | 595649 | 01841 | 10 | Solar | 05_14_8L2 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/26/2024 | 9/15/2025 | Y | EXP | 485 | 07/25/2024 | 08/08/2025 | 380 | 0 | 380 |  |  | 9/17/2025 | Connected |  | N | Hopedale-East | Closed
National Grid | LEICESTER | 667463 | 01524 | 0 | Other | 05_01_23W3 | 02/25/2025 | 03/28/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/31/2025 | 04/28/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough | Closed
National Grid | BROOKFIELD | 178274 | 01506 | 4998 | Solar | 05_01_408L2 | 02/21/2018 | 02/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2018 | 05/24/2018 | 67 | 49 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2018 | 02/21/2018 | 1/26/2027 | Y | STD | 798 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N | Brockton-South | Closed
National Grid | BROOKFIELD | 652843 | 01515 | 6 | Solar | 05_01_552L3 | 11/07/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford | Closed
National Grid | FALL RIVER | 605320 | 02723 | 5.76 | Solar | 05_05_106W44 | 04/20/2024 | 04/25/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 | 04/20/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N | Chelmsford/Westford | Closed
National Grid | MARLBOROUGH | 175202 | 01752 | 110 | Solar | 05_05_310W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N | Chelmsford/Westford | Closed
National Grid | GLOUCESTER | 177120 | 01930 | 420 | Solar | 05_12_24J8 | 10/19/2016 | 10/19/2016 | 4 | 4 | 0 | 10/26/2016 | 10/26/2016 | 319 | 44 | 275 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford | Closed
National Grid | BEVERLY | 376945 | 01915 | 6.96 | Solar | 05_12_51T1 | 08/19/2021 | 01/04/2022 | 2 | 0 | 2 | 08/24/2021 | 08/24/2021 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 |  | 10/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2022 | Connected |  | Y | Chelmsford/Westford | Closed
National Grid | CHELMSFORD | 647102 | 01863 | 5.76 | Solar | 05_14_2L3 | 10/23/2024 | 11/14/2024 | 4 | 0 | 4 | 11/15/2024 | 11/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 10/23/2024 | 1/3/2026 | Y | EXP | 365 | 03/04/2025 | 03/24/2025 | 21 | 0 | 21 |  |  | 5/21/2025 | Connected |  | N | Chelmsford/Westford | Closed
National Grid | WESTFORD | 449402 | 01886 | 11.4 | Solar | 05_14_57L3 | 08/12/2022 | 08/15/2022 | 1 | 0 | 1 | 08/16/2022 | 08/16/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Billerica | Closed
National Grid | ANDOVER | 384672 | 01810 | 144 | Solar | 05_14_71L1 | 10/06/2021 | 12/02/2021 | 38 | 29 | 9 | 12/03/2021 | 12/03/2021 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2022 | 10/06/2021 | 8/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2023 | Connected |  | N | North Andover | Closed
National Grid | LAWRENCE | 595986 | 01841 | 6 | Solar | 05_14_8L2 | 03/25/2024 | 03/27/2024 | 2 | 0 | 2 | 03/28/2024 | 03/28/2024 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 | 03/25/2024 | 5/9/2025 | Y | EXP | 365 | 07/31/2024 | 09/17/2024 | 49 | 0 | 49 |  |  | 10/30/2024 | Connected |  | N | North Andover | Closed
National Grid | WORCESTER | 686697 | 01602 | 7.6 | Solar | 05_01_23W3 | 04/23/2025 |  | 88 | 84 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Bridgewater | Closed
National Grid | WEST BROOKFIELD | 578928 | 01585 | 996 | Solar | 05_01_408L2 | 02/29/2024 | 06/07/2024 | 69 | 60 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2024 | 06/18/2024 | 8 | 5 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Marlborough | Closed
National Grid | BROOKFIELD | 670551 | 01506 | 5.76 | Solar | 05_01_552L3 | 02/06/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 02/06/2025 | 4/4/2026 | Y | EXP | 365 | 07/19/2025 | 08/04/2025 | 17 | 0 | 17 |  |  | 9/25/2025 | Connected |  | N | Ayer-Clinton | Closed
National Grid | FALL RIVER | 649038 | 02723 | 5.76 | Solar | 05_05_106W44 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N | Methuen | Closed
National Grid | MARLBOROUGH | 175850 | 01752 | 300 | Solar | 05_05_310W4 | 05/20/2015 | 05/20/2015 | 2 | 2 | 0 | 05/28/2015 | 05/28/2015 | 0 | 0 | 0 | 07/30/2015 | 09/03/2015 | 25 | 6 | 19 |  |  | 0 | 0 | 0 | 09/03/2015 | 25 | 6 | 19 |  |  | 0 | 0 | 0 | 9/22/2015 |  | 12/31/2016 | N | EXP | 466 |  |  | 0 | 0 | 0 | 5/18/2016 | 5/18/2016 | 1/9/2017 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | LYNN | 728080 | 01904 | 11.5 | Solar | 05_12_24W1 | 10/28/2025 | 11/03/2025 | 4 | 0 | 4 | 11/04/2025 | 11/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Beverly | Closed
National Grid | BEVERLY | 382216 | 01915 | 9.772 | Solar | 05_12_51T1 | 09/15/2021 | 09/20/2021 | 4 | 3 | 1 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 11/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2022 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | LOWELL | 647024 | 01851 | 10 | Solar | 05_14_2L3 | 10/16/2024 | 11/04/2024 | 2 | 0 | 2 | 11/05/2024 | 11/05/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/16/2024 | 12/16/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N | Chelmsford/Westford | Closed
National Grid | WESTFORD | 374358 | 01886 | 9.86 | Solar | 05_14_57L3 | 08/16/2021 | 08/17/2021 | 1 | 0 | 1 | 08/18/2021 | 08/18/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 10/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/25/2022 | Connected |  | N | Millbury-Grafton | Closed
National Grid | ANDOVER | 514296 | 01845 | 10 | Solar | 05_14_71L1 | 04/03/2023 | 04/06/2023 | 3 | 0 | 3 | 04/07/2023 | 04/07/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Worcester North/South | Closed - Completion Documents Hold
National Grid | LAWRENCE | 599574 | 01841 | 5.85 | Solar | 05_14_8L2 | 04/01/2024 | 04/03/2024 | 3 | 1 | 2 | 04/04/2024 | 04/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 | 04/01/2024 | 5/1/2025 | Y | EXP | 365 | 06/05/2024 | 09/18/2024 | 106 | 0 | 106 |  |  | 10/24/2024 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | WORCESTER | 735526 | 01602 | 3.8 | Solar | 05_01_23W4 | 11/21/2025 | 11/24/2025 | 3 | 0 | 3 | 12/30/2025 | 12/30/2025 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N | Bridgewater | Closed
National Grid | STURBRIDGE | 706760 | 01518 | 240 | Solar | 05_01_408L2 | 08/21/2025 | 09/10/2025 | 13 | 8 | 5 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Hanover | Closed
National Grid | SPENCER | 671085 | 01562 | 5.76 | Solar | 05_01_552L3 | 02/10/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N | Hanover | Closed
National Grid | FALL RIVER | 663614 | 02723 | 4.8 | Solar | 05_05_106W44 | 01/03/2025 | 01/28/2025 | 2 | 0 | 2 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 5/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N | Hanover | Closed
National Grid | MARLBOROUGH | 177333 | 01752 | 784 | Solar | 05_05_310W4 | 08/30/2016 | 08/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2016 | 09/28/2016 | 20 | 2 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/4/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Tewksbury | Closed
National Grid | LYNN | 175225 | 01904 | 11.25 | Solar | 05_12_24W1 | 01/06/2015 | 01/06/2015 | 10 | 7 | 3 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 |  | 5/31/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 7/6/2015 | Connected |  | N | Ayer-Clinton | Closed
National Grid | BEVERLY | 393606 | 01915 | 10 | Solar | 05_12_51T1 | 11/19/2021 | 11/23/2021 | 3 | 1 | 2 | 11/24/2021 | 11/24/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 |  | 12/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2022 | Connected |  | N | Hopedale-East | Closed
National Grid | LOWELL | 650018 | 01851 | 7.6 | Solar | 05_14_2L3 | 11/06/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 11/06/2024 | 1/3/2026 | Y | EXP | 365 | 03/11/2025 | 05/06/2025 | 57 | 0 | 57 |  |  | 5/20/2025 | Connected |  | N | Hanover | Closed
National Grid | WESTFORD | 388451 | 01886 | 9.8 | Solar | 05_14_57L3 | 11/05/2021 | 12/16/2021 | 4 | 2 | 2 | 11/12/2021 | 11/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/05/2021 | 7/7/2023 | Y | EXP | 365 | 06/14/2022 | 07/06/2022 | 22 | 0 | 22 |  |  | 9/9/2022 | Connected |  | N | Brockton-North | Closed
National Grid | ANDOVER | 543541 | 01845 | 84.6 | Solar | 05_14_71L1 | 07/25/2023 | 08/29/2023 | 26 | 16 | 10 | 08/30/2023 | 08/30/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Bridgewater | Closed
National Grid | LAWRENCE | 602404 | 01841 | 3.8 | Solar | 05_14_8L2 | 04/18/2024 | 04/22/2024 | 2 | 0 | 2 | 04/23/2024 | 04/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  | 5/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Chelmsford/Westford | Closed
National Grid | WORCESTER | 737971 | 01602 | 3.8 | Solar | 05_01_23W4 | 12/03/2025 | 12/05/2025 | 1 | 0 | 1 | 01/08/2026 | 01/08/2026 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hopedale-East | Closed
National Grid | STURBRIDGE | 738783 | 01518 | 7.6 | Solar | 05_01_408L2 | 12/08/2025 | 12/10/2025 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N | Brockton-North | Closed
National Grid | BROOKFIELD | 692136 | 01515 | 5.76 | Solar | 05_01_552L3 | 06/02/2025 | 06/13/2025 | 1 | 0 | 1 | 07/17/2025 | 07/17/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 | 06/02/2025 | 8/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N | Somerset | Closed
National Grid | FALL RIVER | 689724 | 02723 | 200 | Solar | 05_05_106W44 | 05/08/2025 | 08/26/2025 | 74 | 65 | 9 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Bridgewater | Closed
National Grid | MARLBOROUGH | 177480 | 01752 | 952 | Solar | 05_05_310W4 | 07/07/2016 | 07/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2016 | 09/19/2016 | 50 | 29 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/13/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Worcester North - Dont Use | Closed - Completion Documents Hold
National Grid | LYNN | 175968 | 01904 | 6 | Solar | 05_12_24W1 | 08/06/2015 | 08/06/2015 | 0 | 0 | 0 | 08/12/2015 | 08/12/2015 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2015 |  | 8/17/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Methuen/Haverhill | Closed
National Grid | MANCHESTER | 392637 | 01944 | 0 | Other | 05_12_51T1 | 01/04/2022 | 01/28/2022 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 03/02/2022 | 22 | 15 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Methuen/Haverhill | Closed
National Grid | LOWELL | 652090 | 01851 | 5.76 | Solar | 05_14_2L3 | 12/03/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed
National Grid | WESTFORD | 396438 | 01886 | 7.6 | Solar | 05_14_57L3 | 11/18/2021 | 12/20/2021 | 22 | 19 | 3 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 |  | 3/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2022 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | ANDOVER | 573060 | 01810 | 0 | Solar | 05_14_71L1 | 12/04/2023 | 12/12/2023 | 6 | 4 | 2 | 12/13/2023 | 12/13/2023 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2024 | Connected |  | N | Spencer-Rutland | Time Frame Suspension - Group Member Withdraw
National Grid | LAWRENCE | 603795 | 01841 | 7.6 | Solar | 05_14_8L2 | 04/13/2024 | 05/09/2024 | 3 | 2 | 1 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Fall River-North | Closed
National Grid | WORCESTER | 380094 | 01602 | 7.6 | Solar | 05_01_23W4 | 09/05/2021 | 09/07/2021 | 1 | 0 | 1 | 09/08/2021 | 09/08/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2021 | 09/05/2021 | 2/15/2023 | Y | EXP | 365 | 01/19/2022 | 02/14/2022 | 27 | 0 | 27 |  |  | 5/27/2022 | Connected |  | N | Leominster | Closed
National Grid | STURBRIDGE | 742596 | 01518 | 20 | Solar | 05_01_408L2 | 12/29/2025 | 01/15/2026 | 2 | 0 | 2 | 01/16/2026 | 01/16/2026 | 45 | 32 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N | Tewksbury | Closed
National Grid | SPENCER | 174385 | 01562 | 2650 | Solar | 05_01_55K11 | 05/31/2012 | 05/31/2012 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/25/2012 | 10/03/2012 | 49 | 0 | 49 |  | 0 | 0 | 0 | 02/18/2015 | 06/29/2016 | 338 | 0 | 338 | 12/23/2014 | 05/31/2012 | 2/3/2016 | Y | STD | 407 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N | Chelmsford/Westford | Closed
National Grid | FALL RIVER | 691599 | 02720 | 75 | Solar | 05_05_106W45 | 05/20/2025 | 09/25/2025 | 88 | 79 | 9 | 09/26/2025 | 09/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2025 |  | 4/2/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Billerica | Closed
National Grid | MARLBOROUGH | 374486 | 01752 | 9.6 | Solar | 05_05_310W4 | 08/11/2021 | 08/18/2021 | 5 | 1 | 4 | 08/19/2021 | 08/19/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 | 08/11/2021 | 12/22/2023 | Y | EXP | 365 | 04/07/2022 | 12/21/2022 | 259 | 0 | 259 |  |  | 1/26/2023 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | LYNN | 176777 | 01904 | 8.5 | Solar | 05_12_24W1 | 11/04/2015 | 11/04/2015 | 3 | 3 | 0 | 11/09/2015 | 11/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 |  | 11/9/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 2/16/2016 | 2/16/2016 | 1/10/2017 | Connected |  | N | Worcester North/South | Closed - Completion Documents Hold
National Grid | MANCHESTER | 394507 | 01944 | 360 | Solar | 05_12_51T1 | 12/17/2021 | 02/02/2022 | 32 | 24 | 8 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East | Closed
National Grid | LOWELL | 684613 | 01851 | 21.4 | Solar | 05_14_2L3 | 04/14/2025 | 04/30/2025 | 9 | 5 | 4 | 05/01/2025 | 05/01/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N | Hopedale-East | Closed
National Grid | TYNGSBORO | 402600 | 01879 | 15 | Solar | 05_14_57L3 | 12/31/2021 | 01/18/2022 | 10 | 6 | 4 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 7/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2022 | Connected |  | N | Tewksbury | Closed
National Grid | ANDOVER | 575824 | 01845 | 100 | Solar | 05_14_71L1 | 12/08/2023 | 12/22/2023 | 10 | 3 | 7 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Fall River-South | Closed
National Grid | LAWRENCE | 609010 | 01841 | 5.76 | Solar | 05_14_8L2 | 05/06/2024 | 05/28/2024 | 13 | 10 | 3 | 05/29/2024 | 05/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 | 05/06/2024 | 6/24/2025 | Y | EXP | 365 | 07/17/2024 | 10/25/2024 | 101 | 0 | 101 |  |  | 12/21/2024 | Connected |  | N | Brockton-North | Closed
National Grid | WORCESTER | 494547 | 01602 | 18.432 | Solar | 05_01_23W4 | 01/24/2023 | 05/25/2023 | 85 | 81 | 4 |  |  | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East | Closed
National Grid | BRIMFIELD | 174315 | 01010 | 25 | Solar | 05_01_408L2 | 01/17/2012 | 01/17/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2012 | 01/17/2012 | 3/30/2012 | Y | EXP | 28 | 04/26/2012 | 07/27/2012 | 63 | 0 | 63 | 8/3/2012 | 8/3/2012 | 8/10/2012 | Connected |  | N | Fall River-North | Closed - Completion Documents Hold
National Grid | SPENCER | 175669 | 01562 | 1000 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N | North Andover | Closed
National Grid | FALL RIVER | 175777 | 02720 | 85 | Solar | 05_05_106W45 | 08/20/2014 | 08/20/2014 | 7 | 3 | 4 | 09/02/2014 | 09/02/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2014 |  | 12/31/2014 | N | EXP | 112 |  |  | 0 | 0 | 0 | 9/15/2014 | 9/15/2014 | 12/4/2014 | Connected |  | N | Webster-Southbridge-Charlton | Closed - Completion Documents Hold
National Grid | MARLBOROUGH | 473967 | 01752 | 15.2 | Solar | 05_05_310W4 | 11/03/2022 | 11/08/2022 | 2 | 0 | 2 | 11/09/2022 | 11/09/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2022 |  | 1/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2023 | Connected |  | N | Somerset | Closed
National Grid | LYNN | 177282 | 01904 | 10 | Solar | 05_12_24W1 | 06/14/2016 | 06/14/2016 | 1 | 1 | 0 | 06/16/2016 | 06/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/20/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 | 11/16/2016 | 11/16/2016 | 11/16/2016 | Connected |  | N | Somerset | Closed
National Grid | MANCHESTER | 400010 | 01944 | 8.027 | Solar | 05_12_51T1 | 12/08/2021 | 01/05/2022 | 19 | 17 | 2 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 2/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2022 | Connected |  | N | Hanover | Closed
National Grid | CHELMSFORD | 378752 | 01824 | 2999 | Solar | 05_14_2L4 | 02/05/2022 | 03/15/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2022 | 03/16/2022 | 1 | 0 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 | 02/05/2022 | 6/13/2027 | Y | STD | 483 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N | Hopedale-East | Closed
National Grid | WESTFORD | 421328 | 01886 | 0 | Solar | 05_14_57L3 | 04/01/2022 | 04/04/2022 | 1 | 0 | 1 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East | Closed - Construction Hold
National Grid | ANDOVER | 608290 | 01845 | 7.6 | Solar | 05_14_71L1 | 05/04/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 05/04/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton | Closed
National Grid | LAWRENCE | 609653 | 01841 | 7.6 | Solar | 05_14_8L2 | 05/08/2024 | 05/20/2024 | 4 | 0 | 4 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 | 05/08/2024 | 6/28/2025 | Y | EXP | 365 | 08/29/2024 | 01/07/2025 | 132 | 0 | 132 |  |  | 1/29/2025 | Connected |  | N | Ayer-Clinton | Closed
National Grid | WORCESTER | 550048 | 01602 | 9.5 | Solar | 05_01_23W4 | 08/22/2023 | 08/23/2023 | 1 | 0 | 1 | 08/24/2023 | 08/24/2023 | 125 | 106 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Ayer-Clinton | Closed
National Grid | STURBRIDGE | 174616 | 01518 | 300 | Solar | 05_01_408L2 | 12/29/2010 | 12/29/2010 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2011 |  | 2/29/2012 | N | EXP | 336 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 2/29/2012 | Connected |  | N | Attleboro | Closed
National Grid | SPENCER | 175701 | 01562 | 2000 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N | Ayer-Clinton | Closed
National Grid | FALL RIVER | 197438 | 02720 | 1400 | Natural Gas | 05_05_106W45 | 09/20/2019 | 11/07/2019 | 33 | 28 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2019 | 12/09/2019 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover | Closed
National Grid | MARLBOROUGH | 617968 | 01752 | 11.4 | Solar | 05_05_310W4 | 06/14/2024 | 07/03/2024 | 10 | 9 | 1 | 07/05/2024 | 07/05/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-North | Closed
National Grid | LYNN | 177814 | 01904 | 3.8 | Solar | 05_12_24W1 | 03/31/2017 | 03/31/2017 | 5 | 2 | 3 | 04/07/2017 | 04/07/2017 | 219 | 0 | 219 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 4/5/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Beverly | Closed
National Grid | BEVERLY | 426053 | 01915 | 22.272 | Solar | 05_12_51T1 | 04/25/2022 | 06/07/2022 | 30 | 26 | 4 | 06/08/2022 | 06/08/2022 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 8/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2022 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | CHELMSFORD | 582189 | 01863 | 100 | Solar | 05_14_2L4 | 01/19/2024 | 02/09/2024 | 15 | 4 | 11 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Worcester North/South | Closed
National Grid | WESTFORD | 460840 | 01886 | 0 | Solar | 05_14_57L3 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Methuen/Haverhill | Closed
National Grid | ANDOVER | 615033 | 01845 | 7.6 | Solar | 05_14_71L1 | 06/03/2024 | 06/18/2024 | 5 | 0 | 5 | 06/20/2024 | 06/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N | Bridgewater | Closed
National Grid | METHUEN | 611143 | 01844 | 6 | Solar | 05_14_8L2 | 05/15/2024 | 05/21/2024 | 2 | 0 | 2 | 05/22/2024 | 05/22/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Worcester North/South | Closed
National Grid | WORCESTER | 577496 | 01602 | 6 | Solar | 05_01_23W4 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 2/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2024 | Connected |  | N | North Andover | Closed
National Grid | STURBRIDGE | 174615 | 01518 | 585 | Solar | 05_01_408L2 | 12/14/2010 | 12/14/2010 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2011 |  | 2/27/2012 | N | EXP | 334 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 2/27/2012 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | SPENCER | 175700 | 01562 | 860 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 2/3/2016 | Y | STD | 142 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | FALL RIVER | 649212 | 02720 | 3.8 | Solar | 05_05_106W45 | 10/23/2024 | 12/02/2024 | 20 | 17 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 10/23/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y | MPL-East | Scoping Meeting
National Grid | MARLBOROUGH | 649246 | 01752 | 11.4 | Solar | 05_05_310W4 | 10/26/2024 | 11/19/2024 | 2 | 0 | 2 | 11/20/2024 | 11/20/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East | Scoping Meeting
National Grid | LYNN | 177896 | 01904 | 7.6 | Solar | 05_12_24W1 | 06/15/2017 | 06/15/2017 | 9 | 9 | 0 | 06/28/2017 | 06/28/2017 | 150 | 0 | 150 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2017 |  | 6/20/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Attleboro | Closed
National Grid | MANCHESTER | 425303 | 01944 | 15.2 | Solar | 05_12_51T1 | 04/20/2022 | 05/11/2022 | 15 | 14 | 1 | 05/12/2022 | 05/12/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N | Worcester North/South | Closed
National Grid | LOWELL | 174864 | 01851 | 1333 | Solar | 05_14_2L4 | 08/02/2012 | 08/02/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2012 | 10/24/2012 | 49 | 0 | 49 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2013 | 08/02/2012 | 12/31/2012 | Y | STD | 130 | 10/25/2013 | 12/27/2013 | 42 | 0 | 42 | 12/26/2013 | 12/26/2013 | 12/27/2013 | Connected |  | N | Worcester North/South | Closed
National Grid | WESTFORD | 480047 | 01886 | 15.2 | Solar | 05_14_57L3 | 01/13/2023 | 12/05/2022 | 2 | 0 | 2 | 01/19/2023 | 01/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 2/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2023 | Connected |  | N | Millbury-Grafton | Closed
National Grid | ANDOVER | 646857 | 01845 | 10 | Solar | 05_14_71L1 | 10/29/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 10/29/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y | Methuen/Haverhill | Closed
National Grid | LAWRENCE | 613140 | 01841 | 6 | Solar | 05_14_8L2 | 05/23/2024 | 05/29/2024 | 2 | 0 | 2 | 05/30/2024 | 05/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 |  | 10/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed
National Grid | WORCESTER | 652348 | 01602 | 7.6 | Solar | 05_01_23W4 | 11/05/2024 | 11/20/2024 | 5 | 1 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/05/2024 | 5/28/2026 | Y | EXP | 365 | 02/25/2025 | 03/06/2025 | 10 | 0 | 10 |  |  | 7/11/2025 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | BRIMFIELD | 175628 | 01010 | 1000 | Solar | 05_01_408L2 | 08/11/2014 | 08/11/2014 | 37 | 36 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2014 | 10/29/2014 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/29/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Attleboro | Closed
National Grid | SPENCER | 175699 | 01562 | 629 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 12/12/2016 | Connected |  | N | Ayer-Clinton | Closed - Pending Customer Decision
National Grid | FALL RIVER | 672503 | 02720 | 5.76 | Solar | 05_05_106W45 | 02/18/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 02/18/2025 | 5/1/2026 | Y | EXP | 365 | 04/29/2025 | 06/03/2025 | 36 | 0 | 36 |  |  | 10/10/2025 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | MARLBOROUGH | 744230 | 01752 | 5.76 | Solar | 05_05_310W4 | 01/08/2026 | 01/09/2026 | 2 | 0 | 2 | 01/22/2026 | 01/22/2026 | 27 | 16 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Scoping Meeting
National Grid | LYNN | 201447 | 01904 | 7.6 | Solar | 05_12_24W1 | 12/12/2018 | 12/24/2018 | 7 | 0 | 7 | 12/26/2018 | 12/26/2018 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2019 | 12/12/2018 | 4/14/2021 | Y | EXP | 365 | 11/03/2020 | 02/08/2021 | 97 | 0 | 97 |  |  | 3/17/2021 | Connected |  | Y | Tewksbury | Closed
National Grid | GLOUCESTER | 426149 | 01930 | 7.6 | Solar | 05_12_51T1 | 06/13/2022 | 06/13/2022 | 0 | 0 | 0 | 06/14/2022 | 06/14/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2022 |  | 7/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2023 | Connected |  | N | Worcester North/South | Closed
National Grid | LOWELL | 176010 | 01851 | 64.8 | Solar | 05_14_2L4 | 08/13/2015 | 08/13/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2015 |  | 8/19/2016 | N | EXP | 354 |  |  | 0 | 0 | 0 | 5/13/2016 | 5/13/2016 | 5/18/2016 | Connected |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | WESTFORD | 485511 | 01886 | 0 | Solar | 05_14_57L3 | 12/14/2022 | 12/15/2022 | 1 | 0 | 1 | 12/16/2022 | 12/16/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 3/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2023 | Connected |  | N | Ayer-Clinton | Closed
National Grid | LAWRENCE | 661800 | 01843 | 7.6 | Solar | 05_14_71L1 | 12/19/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | LAWRENCE | 617449 | 01841 | 5.76 | Solar | 05_14_8L2 | 06/12/2024 | 06/28/2024 | 5 | 0 | 5 | 07/01/2024 | 07/01/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 7/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WORCESTER | 674211 | 01602 | 5.7 | Solar | 05_01_23W4 | 02/25/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East | Scoping Meeting
National Grid | BRIMFIELD | 175735 | 01010 | 500 | Solar | 05_01_408L2 | 08/11/2014 | 08/11/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2014 | 09/19/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 |  | 5/1/2016 | N | STD | 376 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | SPENCER | 175698 | 01562 | 393 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 12/12/2016 | Connected |  | N | Spencer-Rutland | Time Frame Suspension
National Grid | FALL RIVER | 660363 | 02720 | 499.9 | Solar | 05_05_106W46 | 02/06/2025 | 03/27/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2025 | 07/31/2025 | 86 | 67 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Northampton | Closed
National Grid | MARLBOROUGH | 343005 | 01752 | 208.2 | Solar | 05_05_310W5 | 02/19/2021 | 03/05/2021 | 9 | 0 | 9 |  |  | 34 | 11 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 | 02/19/2021 | 4/29/2027 | Y | STD | 488 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N | Fall River-South | Closed
National Grid | LYNN | 223585 | 01904 | 7.6 | Solar | 05_12_24W1 | 06/05/2019 | 06/06/2019 | 0 | 0 | 0 | 06/07/2019 | 06/07/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2019 | 06/05/2019 | 6/3/2020 | Y | EXP | 365 | 12/05/2019 | 12/16/2019 | 11 | 0 | 11 |  |  | 3/13/2020 | Connected |  | N | MPL-Northwest | Study Complete
National Grid | GLOUCESTER | 431218 | 01930 | 10 | Solar | 05_12_51T1 | 05/17/2022 | 05/18/2022 | 1 | 0 | 1 | 05/19/2022 | 05/19/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 7/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | N | Billerica | Closed
National Grid | LOWELL | 176358 | 01851 | 30 | Solar | 05_14_2L4 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 | 05/19/2015 | 05/19/2015 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland | Time Frame Suspension
National Grid | WESTFORD | 497827 | 01886 | 15.2 | Solar | 05_14_57L3 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 30 | 12 | 18 | 04/10/2023 | 05/15/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 05/15/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 4/19/2023 |  | 11/29/2024 | N | EXP | 365 | 08/31/2023 | 02/27/2024 | 181 | 3 | 178 |  |  | 3/7/2024 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | LAWRENCE | 666713 | 01843 | 5.76 | Solar | 05_14_71L1 | 01/20/2025 | 05/02/2025 | 59 | 58 | 1 | 05/02/2025 | 05/02/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-Northwest | Study Complete
National Grid | METHUEN | 617125 | 01844 | 7.6 | Solar | 05_14_8L2 | 06/11/2024 | 06/18/2024 | 1 | 0 | 1 | 06/20/2024 | 06/20/2024 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N | MPL-Northwest | Study Complete
National Grid | WORCESTER | 743409 | 01606 | 5.76 | Solar | 05_01_24W1 | 01/05/2026 | 01/06/2026 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N | MPL-Northwest | Study Complete
National Grid | WARREN | 177703 | 01083 | 1500 | Solar | 05_01_408L2 | 05/25/2017 | 05/25/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2017 | 06/21/2017 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2018 | 05/25/2017 | 6/15/2020 | Y | STD | 435 | 10/03/2019 | 12/27/2019 | 85 | 0 | 85 |  |  | 6/15/2020 | Connected |  | N | MPL-Northwest | Study Complete
National Grid | SPENCER | 175697 | 01562 | 2000 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N | Hanover | Awaiting Full Payments for Common System Modifications - Completion Documents Hold
National Grid | FALL RIVER | 660362 | 02720 | 499.9 | Solar | 05_05_106W46 | 02/06/2025 | 03/25/2025 | 32 | 22 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2025 | 07/31/2025 | 88 | 69 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Beverly | Closed
National Grid | MARLBOROUGH | 342944 | 01752 | 191.6 | Solar | 05_05_310W5 | 02/18/2021 | 03/04/2021 | 9 | 0 | 9 |  |  | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 | 02/18/2021 | 4/11/2027 | Y | STD | 488 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N | Webster-Southbridge-Charlton | Closed - Completion Documents Hold
National Grid | LYNN | 277587 | 01904 | 10 | Solar | 05_12_24W1 | 03/04/2020 | 03/16/2020 | 7 | 3 | 4 | 03/17/2020 | 03/17/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2020 | 03/04/2020 | 12/21/2022 | Y | EXP | 365 | 12/10/2020 | 03/11/2021 | 91 | 0 | 91 |  |  | 9/22/2022 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | MANCHESTER | 432837 | 01944 | 220 | Solar | 05_12_51T1 | 06/23/2022 | 07/29/2022 | 25 | 15 | 10 |  |  | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 06/23/2022 | 10/31/2024 | Y | STD | 290 |  |  | 0 | 0 | 0 |  |  | 11/20/2024 | Connected |  | N | Webster-Southbridge-Charlton | Closed - Design Hold
National Grid | CHELMSFORD | 202054 | 01824 | 4975 | Solar | 05_14_2L4 | 11/27/2018 | 12/06/2018 | 157 | 2 | 155 |  |  | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West | Time Frame Suspension - Completion Documents Hold
National Grid | WESTFORD | 495618 | 01886 | 7.6 | Solar | 05_14_57L3 | 02/27/2023 | 03/06/2023 | 6 | 5 | 1 | 03/07/2023 | 03/07/2023 | 230 | 206 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-North | 160 Day Study
National Grid | LAWRENCE | 684738 | 01843 | 5.76 | Solar | 05_14_71L1 | 04/11/2025 | 04/29/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N | Attleboro | Closed
National Grid | LAWRENCE | 616791 | 01841 | 5.76 | Solar | 05_14_8L2 | 06/10/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  | 12/6/2025 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Leominster | Closed
National Grid | WORCESTER | 748984 | 01605 | 10.64 | Solar | 05_01_24W1 | 02/03/2026 | 02/04/2026 | 2 | 0 | 2 | 02/12/2026 | 02/12/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Billerica | Closed
National Grid | WARREN | 178484 | 01083 | 3000 | Solar | 05_01_408L2 | 04/03/2018 | 04/18/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/10/2018 | 3 | 0 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2019 |  | 6/27/2023 | N | STD | 553 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Billerica | Closed
National Grid | SPENCER | 175704 | 01562 | 1750 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 | 11/28/2016 | 11/28/2016 | 11/28/2016 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | FALL RIVER | 697565 | 02720 | 19 | Solar | 05_05_106W46 | 06/10/2025 | 06/12/2025 | 2 | 0 | 2 | 06/13/2025 | 06/13/2025 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | North Andover | Closed
National Grid | MARLBOROUGH | 641232 | 01752 | 0 | Other | 05_05_310W5 | 07/12/2025 | 11/23/2025 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 01/27/2026 | 43 | 24 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Scituate | Closed
National Grid | LYNN | 515479 | 01904 | 3.8 | Solar | 05_12_24W1 | 03/30/2023 | 03/31/2023 | 1 | 0 | 1 | 04/03/2023 | 04/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2023 |  | 5/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2023 | Connected |  | N | Somerset | Closed
National Grid | GLOUCESTER | 456681 | 01930 | 15.2 | Solar | 05_12_51T1 | 09/06/2022 | 09/07/2022 | 1 | 0 | 1 | 09/08/2022 | 09/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 |  | 9/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2023 | Connected |  | N | Cape Ann | Closed - Study Hold
National Grid | CHELMSFORD | 202052 | 01824 | 4975 | Solar | 05_14_2L4 | 05/18/2021 |  | 61 | 41 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | WESTFORD | 514032 | 01886 | 0 | Solar | 05_14_57L3 | 03/23/2023 | 03/27/2023 | 3 | 2 | 1 | 03/28/2023 | 03/28/2023 | 252 | 25 | 227 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol | Scoping Meeting
National Grid | ANDOVER | 709192 | 01845 | 9.425 | Solar | 05_14_71L1 | 08/06/2025 | 10/09/2025 | 5 | 2 | 3 | 10/10/2025 | 10/10/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2026 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | LAWRENCE | 619063 | 01841 | 5.76 | Solar | 05_14_8L2 | 06/19/2024 | 07/01/2024 | 3 | 0 | 3 | 07/02/2024 | 07/02/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  | 8/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N | Leominster | Closed
National Grid | WORCESTER | 755044 | 01606 | 15.705 | Solar | 05_01_24W1 | 03/06/2026 | 03/09/2026 | 1 | 0 | 1 | 03/10/2026 | 03/10/2026 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Leominster | Closed
National Grid | STURBRIDGE | 178586 | 01518 | 1.84 | Solar | 05_01_408L2 | 03/13/2018 | 03/13/2018 | 24 | 24 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2018 |  | 3/19/2019 | N | EXP | 322 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Fall River-North | Closed
National Grid | SPENCER | 175703 | 01562 | 1400 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N | Leominster | Closed
National Grid | FALL RIVER | 174254 | 02720 | 95 | Solar | 05_05_106W46 | 02/27/2012 | 02/27/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 02/27/2012 | 6/1/2012 | Y | EXP | 194 | 12/04/2012 | 12/17/2012 | 9 | 0 | 9 | 8/14/2012 | 8/14/2012 | 5/3/2013 | Connected |  | N | Millbury-Grafton | Closed
National Grid | MARLBOROUGH | 560141 | 01752 | 6 | Solar | 05_12_24W1 | 10/19/2023 | 11/13/2023 | 17 | 15 | 2 | 11/14/2023 | 11/14/2023 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton | Closed
National Grid | LYNN | 456466 | 01904 | 0 | Solar | 05_12_51T1 | 09/26/2022 | 09/30/2022 | 4 | 3 | 1 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Leominster | Closed
National Grid | BEVERLY | 207472 | 01915 | 73.3 | Solar | 05_14_2L4 | 01/29/2019 | 01/31/2019 | 1 | 0 | 1 | 02/01/2019 | 02/01/2019 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2019 | Connected |  | N | Leominster | Closed - Study Hold
National Grid | LOWELL | 534960 | 01854 | 15.2 | Solar | 05_14_57L3 | 06/19/2023 | 06/26/2023 | 5 | 2 | 3 | 06/27/2023 | 06/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  | 10/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2023 | Connected |  | N | Billerica | Closed
National Grid | WESTFORD | 719515 | 01886 | 7.6 | Solar | 05_14_71L3 | 09/16/2025 | 10/02/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 | 09/16/2025 | 12/18/2026 | Y | EXP | 365 | 03/06/2026 |  | 27 | 0 | 27 |  |  |  | Construction |  | N | Leominster | Closed
National Grid | ANDOVER | 620656 | 01845 | 7.6 | Solar | 05_14_8L2 | 06/27/2024 | 07/16/2024 | 1 | 1 | 0 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 06/27/2024 | 3/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N | Amesbury Newburyport | Closed
National Grid | LAWRENCE | 196201 | 01841 | 7.6 | Solar | 05_01_24W1 | 09/18/2018 | 10/12/2018 | 3 | 3 | 0 | 10/15/2018 | 10/15/2018 | 57 | 54 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Leominster | Closed
National Grid | WORCESTER | 312005 | 01605 | 15.2 | Solar | 05_01_408L2 | 09/10/2020 | 09/14/2020 | 1 | 0 | 1 | 09/15/2020 | 09/15/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2020 | Connected |  | N | Cape Ann | Closed
National Grid | STURBRIDGE | 175702 | 01518 | 2000 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N | Beverly | Closed
National Grid | SPENCER | 175001 | 01562 | 60 | Solar | 05_05_106W46 | 09/11/2013 | 09/11/2013 | 10 | 3 | 7 | 09/26/2013 | 09/26/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2016 |  | 9/26/2016 | N | EXP | 25 |  |  | 0 | 0 | 0 | 9/15/2016 | 9/15/2016 | 9/26/2016 | Connected |  | N | Chelmsford/Westford | Closed
National Grid | FALL RIVER | 650007 | 02720 | 0 | Other | 05_05_310W5 | 05/02/2025 | 07/11/2025 | 47 | 42 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 08/07/2025 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Methuen/Haverhill | Closed
National Grid | MARLBOROUGH | 565880 | 01752 | 10 | Solar | 05_12_24W1 | 11/03/2023 | 11/07/2023 | 2 | 0 | 2 | 11/08/2023 | 11/08/2023 | 83 | 65 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 | 11/03/2023 | 4/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2024 | Connected |  | N | Hopedale-West | Time Frame Suspension - Draft Ready
National Grid | LYNN | 456448 | 01904 | 22.8 | Solar | 05_12_51T1 | 11/18/2022 | 11/22/2022 | 2 | 0 | 2 | 11/23/2022 | 11/23/2022 | 28 | 14 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 | 11/18/2022 | 7/16/2024 | Y | EXP | 550 | 04/05/2023 | 06/12/2023 | 69 | 0 | 69 |  |  | 5/20/2024 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | MANCHESTER | 175488 | 01944 | 100 | Solar | 05_14_31J1 | 07/23/2014 | 07/23/2014 | 7 | 7 | 0 | 08/04/2014 | 08/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2014 |  | 10/31/2014 | N | EXP | 50 |  |  | 0 | 0 | 0 | 12/8/2014 | 12/8/2014 | 4/9/2015 | Connected |  | N | Millbury-Grafton | Closed - Restudy Hold
National Grid | HAVERHILL | 602139 | 01830 | 16.128 | Solar | 05_14_57L3 | 04/22/2024 | 04/26/2024 | 4 | 2 | 2 | 04/29/2024 | 04/29/2024 | 18 | 12 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-Northwest | Study Complete
National Grid | TYNGSBORO | 721298 | 01879 | 13.36 | Solar | 05_14_71L3 | 09/23/2025 | 10/06/2025 | 3 | 0 | 3 | 12/05/2025 | 12/05/2025 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N | Scituate | Closed
National Grid | ANDOVER | 621743 | 01845 | 7.6 | Solar | 05_14_8L2 | 07/01/2024 | 07/10/2024 | 3 | 0 | 3 | 07/11/2024 | 07/11/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  | 8/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2024 | Connected |  | N | Webster-Southbridge-Charlton | Closed - Draft Agreement
National Grid | LAWRENCE | 193107 | 01841 | 10 | Solar | 05_01_24W1 | 08/08/2018 | 10/26/2018 | 38 | 28 | 10 | 10/29/2018 | 10/29/2018 | 36 | 8 | 28 | 11/06/2018 | 09/17/2019 | 215 | 8 | 207 |  |  | 0 | 0 | 0 | 09/17/2019 | 215 | 8 | 207 |  |  | 0 | 0 | 0 | 12/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East | Scoping Meeting
National Grid | WORCESTER | 379733 | 01605 | 15.2 | Solar | 05_01_408L2 | 09/02/2021 | 09/03/2021 | 1 | 0 | 1 | 09/07/2021 | 09/07/2021 | 68 | 26 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Bridgewater | Time Frame Suspension
National Grid | STURBRIDGE | 178660 | 01518 | 1000 | Solar | 05_01_55K11 | 02/06/2018 | 04/06/2018 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 05/02/2018 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2018 | 02/06/2018 | 11/22/2021 | Y | STD | 416 | 01/09/2021 | 10/21/2021 | 285 | 3 | 282 |  |  | 11/3/2021 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | SPENCER | 273678 | 01562 | 4200 | Solar | 05_05_106W46 | 01/30/2020 | 02/19/2020 | 13 | 9 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/20/2020 | 03/24/2020 | 24 | 14 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Attleboro | Time Frame Suspension
National Grid | FALL RIVER | 720992 | 02720 | 50 | Solar | 05_05_310W5 | 09/22/2025 | 02/04/2026 | 90 | 83 | 7 | 02/05/2026 | 02/05/2026 | 33 | 15 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2026 |  | 3/31/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Attleboro | Time Frame Suspension
National Grid | MARLBOROUGH | 573665 | 01752 | 7.6 | Solar | 05_12_24W1 | 12/11/2023 | 12/12/2023 | 1 | 0 | 1 | 12/13/2023 | 12/13/2023 | 64 | 40 | 24 | 05/03/2024 | 05/20/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 05/20/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 7/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N | Webster-Southbridge-Charlton | Closed - Awaiting Payment
National Grid | LYNN | 480578 | 01904 | 0 | Solar | 05_12_51T1 | 11/28/2022 | 11/29/2022 | 1 | 0 | 1 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 1/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2023 | Connected |  | N | Hanover | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | BEVERLY | 416686 | 01915 | 100 | Solar | 05_14_31J1 | 04/07/2022 | 05/10/2022 | 23 | 14 | 9 | 05/11/2022 | 05/11/2022 | 122 | 100 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Leominster | Closed - Restudy Hold
National Grid | HAVERHILL | 621970 | 01830 | 11.5 | Solar | 05_14_57L3 | 07/02/2024 | 07/05/2024 | 2 | 0 | 2 | 07/08/2024 | 07/08/2024 | 68 | 53 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 |  | 11/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | Y | Leominster | Closed - Restudy Hold
National Grid | WESTFORD | 176651 | 01886 | 524 | Solar | 05_14_71L3 | 02/17/2016 | 02/17/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/19/2016 | 03/08/2016 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/23/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-Northwest | Closed
National Grid | ANDOVER | 622785 | 01845 | 6 | Solar | 05_14_8L2 | 07/05/2024 | 07/18/2024 | 4 | 0 | 4 | 07/19/2024 | 07/19/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 07/05/2024 | 8/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N | MPL-Northwest | Closed
National Grid | LAWRENCE | 261638 | 01841 | 10 | Solar | 05_01_24W1 | 10/25/2019 | 10/28/2019 | 0 | 0 | 0 | 10/29/2019 | 10/29/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 | 10/25/2019 | 10/25/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2020 | Connected |  | N | MPL-Northwest | Closed
National Grid | WORCESTER | 432891 | 01605 | 15.2 | Solar | 05_01_408L2 | 09/15/2022 | 09/15/2022 | 0 | 0 | 0 | 09/16/2022 | 09/16/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 |  | 9/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-Northwest | Closed
National Grid | STURBRIDGE | 682705 | 01518 | 24.7 | Solar | 05_01_55W1 | 04/03/2025 | 04/08/2025 | 4 | 1 | 3 | 04/09/2025 | 04/09/2025 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y | MPL-Northwest | Closed
National Grid | RUTLAND | 396688 | 01543 | 0 | Other | 05_05_106W46 | 01/04/2022 | 01/13/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2022 | 01/27/2022 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Scoping Meeting
National Grid | FALL RIVER | 747566 | 02720 | 0 | Battery Add-On | 05_05_310W5 | 01/26/2026 | 01/29/2026 | 3 | 0 | 3 | 01/30/2026 | 01/30/2026 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2026 |  | 3/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hanover | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | SOUTHBOROUGH | 586866 | 01772 | 7.6 | Solar | 05_12_24W1 | 03/08/2024 | 03/11/2024 | 1 | 0 | 1 | 03/12/2024 | 03/12/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 | 03/08/2024 | 4/24/2025 | Y | EXP | 365 | 05/11/2024 | 07/06/2024 | 57 | 0 | 57 |  |  | 7/13/2024 | Connected |  | N | Millbury-Grafton | Closed
National Grid | LYNN | 486700 | 01904 | 0 | Solar | 05_12_51T1 | 12/21/2022 | 12/27/2022 | 4 | 3 | 1 | 12/28/2022 | 12/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2023 | Connected |  | N | Worcester North/South | Closed
National Grid | BEVERLY | 603273 | 01965 | 3.8 | Solar | 05_14_31J3 | 04/16/2024 | 04/19/2024 | 3 | 0 | 3 | 04/22/2024 | 04/22/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/9/2026 | N | EXP | 730 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Fall River-North | Closed - Completion Documents Hold
National Grid | HAVERHILL | 639845 | 01830 | 17.4 | Solar | 05_14_57L3 | 09/17/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Amesbury Newburyport | Closed
National Grid | TYNGSBORO | 177662 | 01879 | 249 | Solar | 05_14_71L3 | 11/13/2017 | 11/13/2017 | 15 | 5 | 10 | 12/06/2017 | 12/06/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 |  | 12/2/2019 | N | EXP | 711 |  |  | 0 | 0 | 0 |  |  | 12/16/2019 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | ANDOVER | 626779 | 01845 | 10 | Solar | 05_14_8L2 | 07/22/2024 | 09/27/2024 | 36 | 31 | 5 | 09/30/2024 | 09/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 07/22/2024 | 1/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | LAWRENCE | 293766 | 01841 | 0 | Battery Add-On | 05_01_24W1 | 05/28/2020 | 05/29/2020 | 0 | 0 | 0 | 06/01/2020 | 06/01/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/28/2020 | 5/28/2021 | Y | EXP | 365 | 09/01/2020 | 09/29/2020 | 28 | 0 | 28 |  |  | 9/30/2020 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | WORCESTER | 586660 | 01605 | 10 | Solar | 05_01_408L2 | 02/08/2024 | 02/09/2024 | 1 | 0 | 1 | 02/12/2024 | 02/12/2024 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 4/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2024 | Connected |  | N | Millbury-Grafton | Closed
National Grid | STURBRIDGE | 714377 | 01518 | 0 | Other | 05_01_55W1 | 09/26/2025 | 11/12/2025 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 | 12/11/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Millbury-Grafton | Closed
National Grid | RUTLAND | 410239 | 01543 | 500 | Solar | 05_05_106W46 | 03/10/2022 | 04/06/2022 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2022 | 04/20/2022 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | Closed
National Grid | FALL RIVER | 174443 | 02720 | 30 | Solar | 05_05_310W5 | 07/06/2012 | 07/06/2012 | 8 | 0 | 8 | 07/19/2012 | 07/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 10/4/2012 | 10/4/2012 | 1/9/2013 | Connected |  | N | MPL-Northwest | Closed
National Grid | MARLBOROUGH | 592974 | 01752 | 10.73 | Solar | 05_12_24W1 | 03/06/2024 | 03/21/2024 | 12 | 8 | 4 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N | Chelmsford/Westford | Closed
National Grid | LYNN | 495086 | 01904 | 0 | Solar | 05_12_51T1 | 01/27/2023 | 03/16/2023 | 33 | 32 | 1 | 03/17/2023 | 03/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2023 |  | 7/23/2024 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Methuen/Haverhill | Closed
National Grid | MANCHESTER | 176476 | 01944 | 100 | Solar | 05_14_31J5 | 03/24/2016 | 03/24/2016 | 9 | 9 | 0 | 04/07/2016 | 04/07/2016 | 468 | 17 | 451 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2016 |  | 5/31/2018 | N | EXP | 744 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed - Construction Hold
National Grid | HAVERHILL | 645111 | 01830 | 10 | Solar | 05_14_57L3 | 10/04/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton | Closed
National Grid | TYNGSBORO | 378789 | 01879 | 100 | Solar | 05_14_71L3 | 09/03/2021 | 10/06/2021 | 22 | 12 | 10 |  |  | 35 | 4 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 09/03/2021 | 7/9/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N | Scituate | Closed
National Grid | ANDOVER | 631949 | 01845 | 7.6 | Solar | 05_14_8L2 | 08/12/2024 | 08/19/2024 | 1 | 0 | 1 | 08/20/2024 | 08/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2024 | 08/12/2024 | 9/3/2025 | Y | EXP | 365 | 02/25/2025 | 02/24/2025 | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N | Fall River-North | Closed
National Grid | LAWRENCE | 429602 | 01841 | 8.7 | Solar | 05_01_24W1 | 06/09/2022 | 06/22/2022 | 8 | 6 | 2 | 06/23/2022 | 06/23/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/09/2022 | 11/30/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2023 | Connected |  | N | Brockton-North | 160 Day Study - Construction Hold
National Grid | WORCESTER | 620652 | 01605 | 23 | Solar | 05_01_408L2 | 07/03/2024 | 07/11/2024 | 5 | 3 | 2 | 07/12/2024 | 07/12/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/03/2024 | 8/6/2025 | Y | EXP | 365 | 08/30/2024 | 09/12/2024 | 14 | 0 | 14 |  |  | 1/17/2025 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | WARREN | 724459 | 01083 | 7.6 | Solar | 05_01_55W1 | 10/08/2025 | 11/20/2025 | 3 | 0 | 3 | 12/23/2025 | 12/23/2025 | 65 | 49 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N | Brockton-North | 160 Day Study
National Grid | RUTLAND | 431700 | 01543 | 160 | Solar | 05_05_106W46 | 05/20/2022 | 06/21/2022 | 20 | 12 | 8 | 06/22/2022 | 06/22/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 4/28/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford | Closed - Screening Review
National Grid | FALL RIVER | 175274 | 02720 | 42.57 | Solar | 05_05_310W5 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 11/28/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 4/30/2015 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | MARLBOROUGH | 606154 | 01752 | 7.6 | Solar | 05_12_24W1 | 04/23/2024 | 05/07/2024 | 3 | 0 | 3 | 05/08/2024 | 05/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  | 5/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | Y | Scituate | Closed
National Grid | LYNN | 496638 | 01904 | 7.6 | Solar | 05_12_51T1 | 02/24/2023 | 02/28/2023 | 2 | 0 | 2 | 03/01/2023 | 03/01/2023 | 167 | 127 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 11/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2023 | Connected |  | N | Attleboro | Time Frame Suspension
National Grid | BEVERLY | 176513 | 01915 | 99.9 | Solar | 05_14_31J6 | 03/30/2016 | 03/30/2016 | 4 | 4 | 0 | 04/07/2016 | 04/07/2016 | 457 | 77 | 380 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 |  | 12/6/2017 | N | EXP | 477 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Tewksbury | Closed
National Grid | HAVERHILL | 648978 | 01830 | 5.76 | Solar | 05_14_57L3 | 10/22/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2025 | Connected |  | N | Leominster | Closed
National Grid | WESTFORD | 472543 | 01886 | 15.2 | Solar | 05_14_71L3 | 11/22/2022 | 11/28/2022 | 3 | 0 | 3 | 11/29/2022 | 11/29/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 |  | 1/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2023 | Connected |  | N | Walpole/Foxboro | Closed - Design Hold
National Grid | ANDOVER | 634175 | 01845 | 5.76 | Solar | 05_14_8L2 | 08/22/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 08/22/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N | Walpole/Foxboro | Closed - Construction Hold
National Grid | LAWRENCE | 442032 | 01841 | 3.8 | Solar | 05_01_24W1 | 07/27/2022 | 07/29/2022 | 2 | 0 | 2 | 08/01/2022 | 08/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2022 |  | 9/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2022 | Connected |  | N | Bridgewater | Time Frame Suspension
National Grid | WORCESTER | 662427 | 01605 | 9.86 | Solar | 05_01_408L2 | 01/02/2025 | 01/14/2025 | 4 | 0 | 4 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 3/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N | Somerset | Closed
National Grid | STURBRIDGE | 730854 | 01518 | 200 | Solar | 05_01_55W1 | 02/09/2026 | 03/20/2026 | 28 | 18 | 10 | 03/23/2026 | 03/23/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Somerset | Closed
National Grid | RUTLAND | 431612 | 01543 | 240 | Solar | 05_05_106W46 | 05/20/2022 | 06/21/2022 | 20 | 12 | 8 | 06/22/2022 | 06/22/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 4/28/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Somerset | Closed
National Grid | FALL RIVER | 175639 | 02720 | 16 | Solar | 05_05_310W5 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2014 |  | 2/6/2015 | N | EXP | 92 |  |  | 0 | 0 | 0 | 8/11/2016 | 8/11/2016 | 8/16/2016 | Connected |  | N | Somerset | Closed
National Grid | MARLBOROUGH | 610904 | 01752 | 10 | Solar | 05_12_24W1 | 05/14/2024 | 06/03/2024 | 1 | 0 | 1 | 06/04/2024 | 06/04/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/14/2024 | 8/7/2025 | Y | EXP | 365 | 09/27/2024 | 01/09/2025 | 105 | 0 | 105 |  |  | 1/14/2025 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | LYNN | 514443 | 01904 | 0 | Solar | 05_12_51T1 | 03/24/2023 | 03/27/2023 | 1 | 0 | 1 | 03/28/2023 | 03/28/2023 | 72 | 54 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Dracut | Closed
National Grid | MANCHESTER | 650000 | 01944 | 3.8 | Solar | 05_14_31L9 | 10/30/2024 | 11/25/2024 | 5 | 0 | 5 | 11/26/2024 | 11/26/2024 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Dracut | Closed
National Grid | HAVERHILL | 649917 | 01830 | 10 | Solar | 05_14_57L3 | 10/31/2024 | 11/05/2024 | 5 | 0 | 5 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 10/31/2024 | 3/12/2026 | Y | EXP | 365 | 05/01/2025 | 05/14/2025 | 14 | 0 | 14 |  |  | 6/27/2025 | Connected |  | N | Beverly | Closed
National Grid | WESTFORD | 492288 | 01886 | 3.8 | Solar | 05_14_71L3 | 01/24/2023 | 01/27/2023 | 3 | 0 | 3 | 01/30/2023 | 01/30/2023 | 33 | 14 | 19 | 04/18/2023 | 05/16/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 05/16/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 5/1/2023 |  | 11/29/2024 | N | EXP | 365 | 08/09/2023 | 12/28/2023 | 142 | 3 | 139 |  |  | 1/5/2024 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | ANDOVER | 635288 | 01845 | 2.32 | Solar | 05_14_8L2 | 08/26/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 | 08/26/2024 | 10/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N | Attleboro | Time Frame Suspension
National Grid | LAWRENCE | 447540 | 01841 | 3.8 | Solar | 05_01_24W1 | 12/09/2022 | 02/14/2023 | 44 | 42 | 2 | 02/15/2023 | 02/15/2023 | 102 | 81 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 |  | 8/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2023 | Connected |  | N | Fall River-North | Closed
National Grid | WORCESTER | 662789 | 01606 | 9.75 | Solar | 05_01_408L2 | 12/27/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/27/2024 | 5/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N | Millbury-Grafton | Closed
National Grid | STURBRIDGE | 740108 | 01518 | 0 | Battery Add-On | 05_01_55W1 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2026 |  | 3/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | RUTLAND | 537794 | 01543 | 7.6 | Solar | 05_05_106W46 | 07/12/2023 | 07/13/2023 | 1 | 0 | 1 | 07/14/2023 | 07/14/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2023 |  | 8/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | FALL RIVER | 175964 | 02720 | 9.25 | Solar | 05_05_310W5 | 06/05/2015 | 06/05/2015 | 1 | 1 | 0 | 06/09/2015 | 06/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2015 |  | 6/30/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/2/2015 | 7/2/2015 | 8/12/2015 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | SOUTHBOROUGH | 615444 | 01772 | 10.15 | Solar | 05_12_24W1 | 06/04/2024 | 06/14/2024 | 5 | 4 | 1 | 06/17/2024 | 06/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2024 |  | 7/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2024 | Connected |  | N | Scituate | Closed
National Grid | LYNN | 516409 | 01904 | 15.007 | Solar | 05_12_51T1 | 04/14/2023 | 04/19/2023 | 2 | 0 | 2 | 04/20/2023 | 04/20/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann | Closed - Study Hold
National Grid | GLOUCESTER | 650670 | 01930 | 5.76 | Solar | 05_14_31L9 | 10/30/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | HAVERHILL | 656744 | 01830 | 15.2 | Solar | 05_14_57L3 | 11/25/2024 | 12/18/2024 | 15 | 13 | 2 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N | Leominster | Closed
National Grid | TYNGSBORO | 578593 | 01879 | 480 | Solar | 05_14_71L3 | 01/12/2024 | 02/08/2024 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2024 | 02/23/2024 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Scoping Meeting
National Grid | ANDOVER | 638038 | 01845 | 7.6 | Solar | 05_14_8L2 | 09/05/2024 | 10/25/2024 | 22 | 21 | 1 | 10/28/2024 | 10/28/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton | Closed
National Grid | METHUEN | 519419 | 01844 | 12.47 | Solar | 05_01_24W1 | 07/14/2023 | 07/17/2023 | 1 | 0 | 1 | 07/18/2023 | 07/18/2023 | 23 | 0 | 23 | 09/20/2023 | 10/20/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 10/20/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 10/25/2023 |  | 11/26/2024 | N | EXP | 365 | 01/03/2024 | 02/23/2024 | 52 | 0 | 52 |  |  |  | Withdrawn |  | Y | Barre-Athol | Scoping Meeting
National Grid | WORCESTER | 679369 | 01605 | 3.8 | Solar | 05_01_408L2 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 6/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N | Bridgewater | Time Frame Suspension - Change Request Under Review
National Grid | STURBRIDGE | 741875 | 01518 | 10 | Solar | 05_01_55W1 | 12/22/2025 | 12/29/2025 | 2 | 0 | 2 | 01/15/2026 | 01/15/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 | 12/22/2025 | 2/6/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N | Walpole/Foxboro | Closed - Design Hold
National Grid | RUTLAND | 619984 | 01543 | 50 | Solar | 05_05_106W46 | 07/01/2024 | 09/16/2024 | 53 | 45 | 8 | 09/17/2024 | 09/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 |  | 4/11/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N | Somerset | Closed
National Grid | FALL RIVER | 176107 | 02720 | 250 | Natural Gas | 05_05_310W5 | 06/25/2015 | 06/25/2015 | 3 | 3 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2015 |  | 6/30/2016 | N | EXP | 329 |  |  | 0 | 0 | 0 | 12/18/2015 | 12/18/2015 | 12/18/2015 | Connected |  | N | Ayer-Clinton | Closed
National Grid | MARLBOROUGH | 625257 | 01752 | 5 | Solar | 05_12_24W1 | 07/18/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 9/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2025 | Connected |  | N | Millbury-Grafton | Closed
National Grid | LYNN | 554842 | 01904 | 10 | Solar | 05_12_51T1 | 09/12/2023 | 09/14/2023 | 2 | 0 | 2 | 09/15/2023 | 09/15/2023 | 134 | 51 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland | Scoping Meeting
National Grid | BEVERLY | 653300 | 01915 | 10.88 | Solar | 05_14_31L9 | 11/08/2024 | 12/11/2024 | 4 | 1 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East | Scoping Meeting
National Grid | HAVERHILL | 661194 | 01830 | 0 | Battery Add-On | 05_14_57L3 | 12/17/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | TYNGSBORO | 578504 | 01879 | 400 | Solar | 05_14_71L3 | 01/12/2024 | 02/08/2024 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2024 | 02/23/2024 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | Time Frame Suspension
National Grid | ANDOVER | 642722 | 01845 | 5.76 | Solar | 05_14_8L2 | 09/25/2024 | 10/09/2024 | 2 | 0 | 2 | 10/10/2024 | 10/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/25/2024 | 11/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | LAWRENCE | 525753 | 01841 | 6 | Solar | 05_01_24W1 | 06/21/2023 | 06/21/2023 | 0 | 0 | 0 | 06/22/2023 | 06/22/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North | 160 Day Study - Completion Documents Hold
National Grid | WORCESTER | 736063 | 01605 | 10 | Solar | 05_01_412L1 | 11/24/2025 | 12/16/2025 | 1 | 0 | 1 | 01/29/2026 | 01/29/2026 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2026 |  | 3/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Attleboro | Time Frame Suspension
National Grid | WEBSTER | 746396 | 01570 | 10 | Solar | 05_01_55W1 | 01/20/2026 | 01/22/2026 | 3 | 0 | 3 | 03/02/2026 | 03/02/2026 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N | Cape Ann | Closed
National Grid | RUTLAND | 650823 | 01543 | 3.8 | Solar | 05_05_106W46 | 10/30/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Bridgewater | Time Frame Suspension
National Grid | FALL RIVER | 176261 | 02720 | 6 | Solar | 05_05_310W5 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/12/2016 | N | EXP | 353 |  |  | 0 | 0 | 0 | 9/25/2015 | 9/25/2015 | 2/12/2016 | Connected |  | N | Bridgewater | Time Frame Suspension - Change Request Under Review
National Grid | MARLBOROUGH | 630212 | 01752 | 7.6 | Solar | 05_12_24W1 | 08/05/2024 | 08/26/2024 | 1 | 0 | 1 | 08/27/2024 | 08/27/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 |  | 9/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2024 | Connected |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | LYNN | 567996 | 01904 | 10 | Solar | 05_12_51T1 | 11/15/2023 | 11/27/2023 | 7 | 0 | 7 | 11/28/2023 | 11/28/2023 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Fall River-South | Closed
National Grid | ESSEX | 655518 | 01929 | 7.6 | Solar | 05_14_31L9 | 11/19/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Attleboro | Time Frame Suspension
National Grid | HAVERHILL | 664297 | 01830 | 0 | Battery Add-On | 05_14_57L3 | 01/07/2025 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 01/07/2025 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N | Billerica | Closed - Design Hold
National Grid | WESTFORD | 583602 | 01886 | 6.38 | Solar | 05_14_71L3 | 02/14/2024 | 02/15/2024 | 1 | 0 | 1 | 02/16/2024 | 02/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | North Andover | Closed - Construction Hold
National Grid | ANDOVER | 644598 | 01845 | 10 | Solar | 05_14_8L2 | 10/02/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/02/2024 | 12/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N | Scituate | Closed
National Grid | LAWRENCE | 532272 | 01841 | 7.68 | Solar | 05_01_24W1 | 06/14/2023 | 06/20/2023 | 4 | 0 | 4 | 06/21/2023 | 06/21/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Attleboro | Time Frame Suspension
National Grid | WORCESTER | 746938 | 01605 | 5.76 | Solar | 05_01_412L1 | 01/22/2026 | 01/23/2026 | 3 | 0 | 3 | 02/04/2026 | 02/04/2026 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2026 |  | 3/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hanover | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | WEBSTER | 751227 | 01570 | 15.76 | Solar | 05_01_55W1 | 02/13/2026 | 02/19/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Barre-Athol | Scoping Meeting
National Grid | RUTLAND | 664362 | 01543 | 5.76 | Solar | 05_05_106W46 | 01/08/2025 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 01/08/2025 | 3/17/2026 | Y | EXP | 365 | 04/15/2025 | 05/13/2025 | 29 | 0 | 29 |  |  | 7/8/2025 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | FALL RIVER | 185773 | 02720 | 7000 | Solar | 05_05_310W5 | 09/07/2018 |  | 62 | 32 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Worcester North/South | Closed
National Grid | MARLBOROUGH | 645964 | 01752 | 7.6 | Solar | 05_12_24W1 | 10/10/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 10/10/2024 | 1/7/2026 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  | 2/28/2025 | Connected |  | N | Worcester North/South | Closed
National Grid | LYNN | 575964 | 01904 | 8.99 | Solar | 05_12_51T1 | 12/05/2023 | 12/11/2023 | 4 | 3 | 1 | 12/12/2023 | 12/12/2023 | 43 | 20 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2024 |  | 2/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N | Attleboro | Closed
National Grid | GLOUCESTER | 663850 | 01930 | 14.5 | Solar | 05_14_31L9 | 01/08/2025 | 01/17/2025 | 1 | 0 | 1 | 01/17/2025 | 01/17/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N | Attleboro | Closed
National Grid | HAVERHILL | 678244 | 01830 | 20 | Solar | 05_14_57L3 | 03/19/2025 | 03/24/2025 | 3 | 0 | 3 | 03/25/2025 | 03/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N | Worcester North/South | Closed
National Grid | TYNGSBORO | 611670 | 01879 | 3.8 | Solar | 05_14_71L3 | 05/16/2024 | 05/21/2024 | 2 | 0 | 2 | 05/22/2024 | 05/22/2024 | 38 | 25 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 05/16/2024 | 9/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | Y | Hanover | Awaiting Full Payments for Common System Modifications - Completion Documents Hold
National Grid | ANDOVER | 644467 | 01845 | 3.8 | Solar | 05_14_8L2 | 10/02/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 10/02/2024 | 12/9/2025 | Y | EXP | 365 | 09/16/2025 | 09/15/2025 | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N | Millbury-Grafton | Closed
National Grid | LAWRENCE | 541036 | 01841 | 3.8 | Solar | 05_01_24W1 | 07/18/2023 | 07/19/2023 | 1 | 0 | 1 | 07/20/2023 | 07/20/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | WORCESTER | 745944 | 01606 | 1375 | Solar | 05_01_412L1 | 03/27/2026 |  | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WEBSTER | 174218 | 01570 | 11.38 | Solar | 05_01_55W1 | 01/31/2012 | 01/31/2012 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2012 |  | 3/1/2012 | N | EXP | 43 |  |  | 0 | 0 | 0 | 7/23/2012 | 7/23/2012 | 8/7/2012 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | RUTLAND | 667950 | 01543 | 5.76 | Solar | 05_05_106W46 | 01/27/2025 | 03/28/2025 | 13 | 8 | 5 | 03/31/2025 | 03/31/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 225197 | 02720 | 10 | Solar | 05_05_310W5 | 10/28/2019 |  | 118 | 101 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/28/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Scoping Meeting
National Grid | MARLBOROUGH | 660596 | 01752 | 2.03 | Solar | 05_12_24W1 | 12/13/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | LYNN | 590822 | 01904 | 8.7 | Solar | 05_12_51T1 | 03/01/2024 | 03/08/2024 | 5 | 3 | 2 | 03/11/2024 | 03/11/2024 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 | 03/01/2024 | 4/21/2025 | Y | EXP | 365 | 05/16/2024 | 10/02/2024 | 140 | 1 | 139 |  |  | 8/14/2024 | Connected |  | N | Millbury-Grafton | Closed
National Grid | ESSEX | 177941 | 01929 | 120 | Solar | 05_14_32J1 | 06/26/2017 | 06/26/2017 | 105 | 105 | 0 |  |  | 47 | 27 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 5/2/2019 | N | STD | 219 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Billerica | Closed
National Grid | HAVERHILL | 705914 | 01832 | 15.2 | Solar | 05_14_57L3 | 07/22/2025 |  | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Worcester North/South | Closed
National Grid | WESTFORD | 664589 | 01886 | 3.8 | Solar | 05_14_71L3 | 01/08/2025 | 03/19/2025 | 17 | 14 | 3 | 03/20/2025 | 03/20/2025 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 | 01/08/2025 | 6/27/2026 | Y | EXP | 365 | 10/01/2025 | 12/02/2025 | 63 | 0 | 63 |  |  | 12/3/2025 | Connected |  | N | Brockton-South | Closed
National Grid | ANDOVER | 648245 | 01845 | 5.76 | Solar | 05_14_8L2 | 10/30/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 | 01/15/2025 | 02/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 02/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 2/21/2025 | 10/30/2024 | 2/26/2026 | Y | EXP | 365 | 08/20/2025 | 08/19/2025 | 0 | 0 | 0 |  |  | 9/12/2025 | Connected |  | N | Attleboro | Closed - Construction Hold
National Grid | METHUEN | 553080 | 01844 | 11.5 | Solar | 05_01_24W1 | 09/06/2023 | 09/07/2023 | 1 | 0 | 1 | 09/08/2023 | 09/08/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Northampton | Closed
National Grid | WORCESTER | 745922 | 01605 | 1200 | Solar | 05_01_412L1 | 03/23/2026 |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Northampton | Closed
National Grid | WEBSTER | 174355 | 01570 | 1000 | Solar | 05_01_55W1 | 05/17/2012 | 05/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2012 | 08/16/2012 | 54 | 0 | 54 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Northampton | Closed
National Grid | RUTLAND | 688748 | 01543 | 18.24 | Solar | 05_05_106W46 | 04/30/2025 | 05/01/2025 | 1 | 0 | 1 | 05/02/2025 | 05/02/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2025 | 04/30/2025 | 7/17/2026 | Y | EXP | 365 | 08/15/2025 | 10/08/2025 | 55 | 0 | 55 |  |  | 10/10/2025 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 233162 | 02720 | 133.2 | Solar | 05_05_310W5 | 03/23/2020 | 03/31/2020 | 3 | 0 | 3 | 04/01/2020 | 04/01/2020 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 |  | 5/18/2021 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  | 7/22/2021 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | MARLBOROUGH | 668006 | 01752 | 5.76 | Solar | 05_12_24W1 | 01/27/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 01/27/2025 | 4/11/2026 | Y | EXP | 365 | 07/03/2025 | 07/02/2025 | 0 | 0 | 0 |  |  | 8/18/2025 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | LYNN | 610191 | 01904 | 5.76 | Solar | 05_12_51T1 | 05/14/2024 | 05/23/2024 | 3 | 0 | 3 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | MANCHESTER | 176539 | 01944 | 46.8 | Solar | 05_14_32J5 | 02/10/2016 | 02/10/2016 | 5 | 5 | 0 | 02/19/2016 | 02/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2016 |  | 9/16/2017 | N | EXP | 570 |  |  | 0 | 0 | 0 | 3/23/2017 | 3/23/2017 | 3/23/2017 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | HAVERHILL | 705910 | 01830 | 15.2 | Solar | 05_14_57L3 | 08/12/2025 | 09/02/2025 | 13 | 10 | 3 | 09/03/2025 | 09/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2025 | Connected |  | N | Ayer-Clinton | Closed - Completion Documents Hold
National Grid | WESTFORD | 691644 | 01886 | 20 | Solar | 05_14_71L3 | 05/19/2025 | 05/21/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | Closed
National Grid | ANDOVER | 649543 | 01845 | 3.8 | Solar | 05_14_8L2 | 11/05/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | LAWRENCE | 568633 | 01841 | 7.6 | Solar | 05_01_24W1 | 11/21/2023 | 11/30/2023 | 6 | 2 | 4 | 12/01/2023 | 12/01/2023 | 86 | 66 | 20 | 06/05/2024 | 07/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 07/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 7/8/2024 |  | 9/12/2025 | N | EXP | 365 | 09/13/2024 | 09/21/2024 | 9 | 0 | 9 |  |  | 10/18/2024 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | WORCESTER | 745915 | 01605 | 500 | Solar | 05_01_412L1 | 03/23/2026 |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Webster-Southbridge-Charlton | Closed
National Grid | WEBSTER | 174354 | 01570 | 2000 | Solar | 05_01_55W1 | 05/17/2012 | 05/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2012 | 08/16/2012 | 54 | 0 | 54 |  | 0 | 0 | 0 | 03/28/2014 | 03/28/2014 | 0 | 0 | 0 | 9/12/2013 | 05/17/2012 | 12/31/2012 | Y | STD | 255 |  |  | 0 | 0 | 0 | 3/22/2016 | 3/22/2016 | 11/3/2015 | Connected |  | N | Webster-Southbridge-Charlton | Closed - Conditional Approval Hold
National Grid | RUTLAND | 732455 | 01543 | 15.2 | Solar | 05_05_106W46 | 11/12/2025 | 11/17/2025 | 2 | 0 | 2 | 11/18/2025 | 11/18/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2026 | Connected |  | N | Webster-Southbridge-Charlton | Closed - Pending Customer Decision
National Grid | FALL RIVER | 250657 | 02720 | 7.6 | Solar | 05_05_310W5 | 08/26/2019 | 11/01/2019 | 0 | 0 | 0 | 11/04/2019 | 11/04/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland | Scoping Meeting
National Grid | MARLBOROUGH | 679840 | 01752 | 3.8 | Solar | 05_12_24W1 | 04/10/2025 | 06/06/2025 | 12 | 9 | 3 | 06/09/2025 | 06/09/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N | Leominster | Closed
National Grid | LYNN | 613784 | 01904 | 21.125 | Solar | 05_12_51T1 | 06/11/2024 | 06/14/2024 | 4 | 1 | 3 | 06/17/2024 | 06/17/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 9/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2024 | Connected |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | BEVERLY | 756578 | 01915 | 15.2 | Solar | 05_14_33L1 | 03/27/2026 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Brockton-South | Closed
National Grid | BOXFORD | 708703 | 01921 | 15.2 | Solar | 05_14_57L3 | 07/31/2025 | 08/08/2025 | 5 | 1 | 4 | 08/11/2025 | 08/11/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2025 | Connected |  | N | Leominster | Closed
National Grid | WESTFORD | 686461 | 01886 | 7.68 | Solar | 05_14_73L1 | 05/01/2025 | 05/14/2025 | 9 | 6 | 3 | 05/15/2025 | 05/15/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Leominster | Closed
National Grid | WESTFORD | 652216 | 01886 | 7.6 | Solar | 05_14_8L2 | 11/14/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/14/2024 | 2/10/2026 | Y | EXP | 365 | 07/24/2025 | 12/01/2025 | 131 | 0 | 131 |  |  |  | Withdrawn |  | Y | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | LAWRENCE | 582505 | 01841 | 10 | Solar | 05_01_24W1 | 02/16/2024 | 02/23/2024 | 4 | 0 | 4 | 02/26/2024 | 02/26/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WORCESTER | 748832 | 01605 | 5.76 | Solar | 05_01_412L1 | 02/02/2026 | 02/05/2026 | 3 | 0 | 3 | 02/06/2026 | 02/06/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WEBSTER | 174384 | 01570 | 4 | Solar | 05_01_55W1 | 05/31/2012 | 05/31/2012 | 7 | 0 | 7 | 06/13/2012 | 06/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2012 |  | 8/31/2012 | N | EXP | 24 |  |  | 0 | 0 | 0 | 9/6/2012 | 9/6/2012 | 9/24/2012 | Connected |  | N | Billerica | Closed
National Grid | RUTLAND | 663333 | 01543 | 2.32 | Solar | 05_05_106W81 | 01/02/2025 | 01/23/2025 | 11 | 7 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 295196 | 02720 | 0 | Battery Add-On | 05_05_310W5 | 06/06/2020 | 06/10/2020 | 2 | 0 | 2 | 06/11/2020 | 06/11/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 5/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2021 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | SOUTHBOROUGH | 684334 | 01772 | 10 | Solar | 05_12_24W1 | 04/10/2025 | 05/02/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/10/2025 | 6/12/2026 | Y | EXP | 365 | 11/14/2025 | 11/21/2025 | 8 | 0 | 8 |  |  | 11/27/2025 | Connected |  | N | Millbury-Grafton | Closed
National Grid | LYNN | 644032 | 01904 | 10 | Solar | 05_12_51T1 | 10/01/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | MANCHESTER | 210231 | 01944 | 15.2 | Solar | 05_14_33L1 | 03/08/2019 | 04/03/2019 | 10 | 10 | 0 | 04/04/2019 | 04/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2019 |  | 7/26/2019 | N | EXP | 108 |  |  | 0 | 0 | 0 |  |  | 6/25/2019 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | BOXFORD | 717298 | 01921 | 15.2 | Solar | 05_14_57L3 | 09/21/2025 | 09/25/2025 | 4 | 0 | 4 | 09/26/2025 | 09/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2026 | Connected |  | Y | Ayer-Clinton | Closed
National Grid | WESTFORD | 174466 | 01886 | 36 | Solar | 05_14_73L1 | 07/29/2011 | 07/29/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 12/4/2012 | 12/4/2012 | 1/9/2013 | Connected |  | N | Brockton-South | Closed
National Grid | CHELMSFORD | 654360 | 01824 | 7.6 | Solar | 05_14_8L2 | 11/14/2024 | 12/10/2024 | 4 | 0 | 4 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/14/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N | Brockton-South | Closed
National Grid | METHUEN | 595776 | 01844 | 3.8 | Solar | 05_01_24W1 | 03/15/2024 | 03/18/2024 | 1 | 0 | 1 | 03/19/2024 | 03/19/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2024 | Connected |  | N | North Andover | Closed
National Grid | WORCESTER | 752287 | 01605 |  | Battery Add-On | 05_01_412L1 | 02/20/2026 | 02/24/2026 | 2 | 0 | 2 | 02/25/2026 | 02/25/2026 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | MPL-Northwest | Study Complete
National Grid | WEBSTER | 174431 | 01570 | 4680 | Solar | 05_01_55W1 | 06/27/2012 | 06/27/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2012 | 10/09/2012 | 63 | 0 | 63 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2015 | 06/27/2012 | 10/12/2017 | Y | STD | 967 | 03/15/2017 | 08/18/2017 | 109 | 0 | 109 | 8/23/2017 | 8/23/2017 | 9/29/2017 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | RUTLAND | 747295 | 01543 | 10.88 | Solar | 05_05_106W81 | 02/10/2026 | 02/11/2026 | 3 | 1 | 2 | 02/20/2026 | 02/20/2026 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2026 |  | 4/1/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | FALL RIVER | 295368 | 02720 | 8.7 | Solar | 05_05_310W5 | 06/08/2020 | 06/12/2020 | 3 | 2 | 1 | 06/15/2020 | 06/15/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 6/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2020 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | SOUTHBOROUGH | 703102 | 01772 | 15.2 | Solar | 05_12_24W1 | 07/07/2025 | 07/11/2025 | 38 | 38 | 0 | 08/29/2025 | 08/29/2025 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Cape Ann | Closed - Awaiting Payment
National Grid | LYNN | 653896 | 01904 | 7.6 | Solar | 05_12_51T1 | 11/15/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/15/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N | Beverly | Closed
National Grid | BEVERLY | 267108 | 01915 | 0 | Battery Add-On | 05_14_33L1 | 11/25/2019 | 01/02/2020 | 23 | 17 | 6 | 01/03/2020 | 01/03/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 |  | 4/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2020 | Connected |  | N | Somerset | Closed
National Grid | TOPSFIELD | 717812 | 01983 | 15.66 | Solar | 05_14_57L3 | 09/17/2025 | 09/24/2025 | 5 | 0 | 5 | 09/25/2025 | 09/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N | Fall River-South | Closed
National Grid | TYNGSBORO | 174746 | 01879 | 225 | Solar | 05_14_73L1 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 567 | 3 | 564 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2013 |  | 9/1/2014 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Leominster | Closed
National Grid | CHELMSFORD | 654711 | 01824 | 20 | Solar | 05_14_8L2 | 11/20/2024 | 11/25/2024 | 3 | 0 | 3 | 11/26/2024 | 11/26/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | LAWRENCE | 595773 | 01841 | 6.09 | Solar | 05_01_24W1 | 04/08/2024 | 05/17/2024 | 7 | 5 | 2 | 05/20/2024 | 05/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 |  | 7/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WORCESTER | 758849 | 01605 | 5.76 | Solar | 05_01_412L1 | 03/25/2026 |  | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | WEBSTER | 174555 | 01570 | 3000 | Solar | 05_01_55W1 | 10/02/2011 | 10/02/2011 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2013 |  | 10/31/2012 | N | STD | 275 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Cape Ann | Closed
National Grid | RUTLAND | 175183 | 01543 | 60 | Natural Gas | 05_05_106W81 | 05/06/2013 | 05/06/2013 | 8 | 0 | 8 | 05/17/2013 | 05/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2013 |  | 9/30/2013 | N | EXP | 53 |  |  | 0 | 0 | 0 | 12/12/2013 | 12/12/2013 | 12/31/2013 | Connected |  | N | Cape Ann | Closed - Pending Customer Decision
National Grid | FALL RIVER | 312249 | 02720 | 15.2 | Solar | 05_05_310W5 | 09/11/2020 | 09/14/2020 | 0 | 0 | 0 | 09/15/2020 | 09/15/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 10/13/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Fall River-South | Closed
National Grid | SOUTHBOROUGH | 741965 | 01772 | 15.2 | Solar | 05_12_24W2 | 12/23/2025 | 12/24/2025 | 1 | 0 | 1 | 01/22/2026 | 01/22/2026 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  | 4/1/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Fall River-South | Closed
National Grid | LYNN | 657144 | 01904 | 7.6 | Solar | 05_12_51T1 | 11/26/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/26/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y | Hanover | Awaiting Full Payments for Common System Modifications - Completion Documents Hold
National Grid | BEVERLY | 283459 | 01915 | 10 | Solar | 05_14_33L1 | 03/12/2020 | 03/19/2020 | 5 | 5 | 0 | 03/20/2020 | 03/20/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2020 |  | 3/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2020 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | BOXFORD | 725537 | 01921 | 7.6 | Solar | 05_14_57L3 | 10/09/2025 | 10/17/2025 | 5 | 0 | 5 | 10/20/2025 | 10/20/2025 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2026 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WESTFORD | 174750 | 01886 | 225 | Solar | 05_14_73L1 | 07/09/2013 | 07/09/2013 | 18 | 10 | 8 | 08/05/2013 | 08/05/2013 | 568 | 2 | 566 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2013 | 07/09/2013 | 9/30/2014 | Y | EXP | 391 | 07/23/2014 | 11/18/2015 | 329 | 0 | 329 |  |  |  | Withdrawn |  | N | Beverly | Closed
National Grid | CHELMSFORD | 656005 | 01824 | 10 | Solar | 05_14_8L2 | 11/21/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 11/21/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N | Attleboro | Time Frame Suspension
National Grid | LAWRENCE | 612371 | 01841 | 6 | Solar | 05_01_24W1 | 05/20/2024 | 05/28/2024 | 3 | 0 | 3 | 05/29/2024 | 05/29/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/20/2024 | 7/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N | North Andover | Closed - Construction Hold
National Grid | WORCESTER | 174409 | 01605 | 11.18 | Solar | 05_01_412L1 | 06/20/2012 | 06/20/2012 | 5 | 0 | 5 | 06/29/2012 | 06/29/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 9/17/2012 | N | EXP | 86 |  |  | 0 | 0 | 0 | 9/19/2012 | 9/19/2012 | 1/3/2013 | Connected |  | N | Chelmsford/Westford | Closed
National Grid | WEBSTER | 174642 | 01570 | 21 | Solar | 05_01_55W1 | 12/06/2013 | 12/06/2013 | 8 | 0 | 8 | 12/19/2013 | 12/19/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2013 |  | 1/31/2014 | N | EXP | 43 |  |  | 0 | 0 | 0 | 1/21/2014 | 1/21/2014 | 1/30/2015 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | RUTLAND | 176482 | 01543 | 144 | Solar | 05_05_106W81 | 05/20/2016 | 05/20/2016 | 1 | 1 | 0 | 05/26/2016 | 05/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 | 05/20/2016 | 5/30/2017 | Y | EXP | 337 | 10/10/2016 | 11/04/2016 | 18 | 0 | 18 | 12/6/2016 | 12/6/2016 | 12/8/2016 | Connected |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 333500 | 02720 | 52.2 | Solar | 05_05_310W5 | 03/01/2021 | 12/07/2021 | 9 | 0 | 9 | 03/16/2021 | 03/16/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2021 |  | 10/9/2023 | N | EXP | 750 | 08/19/2021 | 09/15/2021 | 26 | 3 | 23 |  |  | 8/24/2023 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | MARLBOROUGH | 754138 | 01752 | 7.6 | Solar | 05_12_24W2 | 03/03/2026 | 03/06/2026 | 4 | 0 | 4 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications - Construction Hold
National Grid | LYNN | 678570 | 01904 | 150 | Solar | 05_12_51T1 | 03/19/2025 | 04/30/2025 | 30 | 20 | 10 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Scituate | Closed
National Grid | MANCHESTER | 294246 | 01944 | 0 | Solar | 05_14_33L1 | 06/01/2020 | 06/02/2020 | 0 | 0 | 0 | 06/03/2020 | 06/03/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2021 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | BOXFORD | 747662 | 01921 | 150 | Solar | 05_14_57L4 | 02/24/2026 |  | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Cape Ann | Closed
National Grid | WESTFORD | 174749 | 01886 | 295 | Solar | 05_14_73L1 | 07/09/2013 | 07/09/2013 | 18 | 10 | 8 | 08/05/2013 | 08/05/2013 | 568 | 16 | 552 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2013 |  | 9/1/2014 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Worcester North/South | Closed
National Grid | CHELMSFORD | 656577 | 01824 | 5.76 | Solar | 05_14_8L2 | 11/25/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/25/2024 | 1/30/2026 | Y | EXP | 365 | 09/13/2025 | 09/12/2025 | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N | Attleboro | Time Frame Suspension
National Grid | LAWRENCE | 619203 | 01841 | 11.4 | Solar | 05_01_24W1 | 10/28/2024 | 11/14/2024 | 9 | 6 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 | 01/06/2025 | 01/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 01/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/25/2026 | N | EXP | 365 | 03/15/2025 | 03/21/2025 | 7 | 0 | 7 |  |  | 4/10/2025 | Connected |  | N | Dracut | Closed - Construction Hold
National Grid | WORCESTER | 175205 | 01605 | 1380 | Solar | 05_01_412L1 | 12/07/2012 | 12/07/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2012 | 01/15/2013 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2014 | 12/07/2012 | 1/20/2016 | Y | STD | 572 | 07/30/2015 | 12/20/2016 | 346 | 0 | 346 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N | Leominster | Closed
National Grid | WEBSTER | 174714 | 01570 | 70 | Solar | 05_01_55W1 | 01/09/2014 | 01/09/2014 | 5 | 0 | 5 | 01/17/2014 | 01/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2014 | 01/09/2014 | 8/29/2014 | Y | EXP | 219 |  |  | 0 | 0 | 0 | 7/28/2014 | 7/28/2014 | 8/6/2015 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | RUTLAND | 364046 | 01543 | 6.24 | Solar | 05_05_106W81 | 07/12/2021 | 07/13/2021 | 2 | 1 | 1 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2021 | 07/12/2021 | 2/8/2023 | Y | EXP | 365 | 12/03/2021 | 02/08/2022 | 68 | 0 | 68 |  |  | 2/10/2022 | Connected |  | N | Leominster | Closed
National Grid | FALL RIVER | 342922 | 02720 | 203.3 | Solar | 05_05_310W5 | 02/18/2021 | 03/04/2021 | 9 | 0 | 9 |  |  | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications
National Grid | MARLBOROUGH | 753974 | 01752 |  | Battery Add-On | 05_12_24W2 | 03/02/2026 | 03/04/2026 | 2 | 0 | 2 | 03/05/2026 | 03/05/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Spencer-Rutland | Scoping Meeting
National Grid | LYNN | 683594 | 01904 | 10 | Solar | 05_12_51T1 | 04/08/2025 | 05/19/2025 | 3 | 0 | 3 | 05/20/2025 | 05/20/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 | 04/08/2025 | 6/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2025 | Connected |  | Y | Hopedale-East | Awaiting Full Payments for Common System Modifications - Completion Documents Hold
National Grid | ESSEX | 306879 | 01929 | 20 | Solar | 05_14_33L1 | 08/14/2020 | 08/18/2020 | 2 | 2 | 0 | 08/19/2020 | 08/19/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2020 | 08/14/2020 | 8/17/2021 | Y | EXP | 365 | 02/05/2021 | 02/04/2021 | 0 | 0 | 0 |  |  | 2/9/2021 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | BOXFORD | 206199 | 01921 | 72 | Solar | 05_14_57L4 | 01/16/2019 | 01/31/2019 | 8 | 3 | 5 | 02/01/2019 | 02/01/2019 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N | Bridgewater | Time Frame Suspension
National Grid | WESTFORD | 175222 | 01886 | 225 | Solar | 05_14_73L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 108 | 03/11/2015 | 04/06/2015 | 17 | 0 | 17 | 5/13/2015 | 5/13/2015 | 6/1/2015 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | CHELMSFORD | 657157 | 01824 | 5.76 | Solar | 05_14_8L2 | 11/26/2024 | 12/13/2024 | 3 | 0 | 3 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/26/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N | Leominster | Closed
National Grid | LAWRENCE | 622805 | 01841 | 5.76 | Solar | 05_01_24W1 | 07/19/2024 | 09/03/2024 | 22 | 21 | 1 | 09/04/2024 | 09/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2024 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | WORCESTER | 175512 | 01605 | 75 | Solar | 05_01_412L1 | 12/05/2014 | 12/05/2014 | 4 | 1 | 3 | 12/12/2014 | 12/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 |  | 4/30/2015 | N | EXP | 139 |  |  | 0 | 0 | 0 | 2/4/2015 | 2/4/2015 | 7/10/2015 | Connected |  | N | Scituate | Closed
National Grid | WEBSTER | 174773 | 01570 | 57.5 | Solar | 05_01_55W1 | 01/17/2013 | 01/17/2013 | 10 | 8 | 2 | 02/04/2013 | 02/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2013 |  | 5/1/2013 | N | EXP | 1 |  |  | 0 | 0 | 0 | 5/2/2013 | 5/2/2013 | 10/4/2013 | Connected |  | N | North Andover | Closed
National Grid | RUTLAND | 451467 | 01543 | 5.76 | Solar | 05_05_106W81 | 10/27/2022 | 11/13/2022 | 11 | 9 | 2 | 11/14/2022 | 11/14/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2022 | Connected |  | Y | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 396057 | 02720 | 0 | Other | 05_05_310W5 | 01/25/2022 | 02/07/2022 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | CMPX | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South | Closed
National Grid | MARLBOROUGH | 755379 | 01752 | 5.76 | Solar | 05_12_24W2 | 03/09/2026 | 03/13/2026 | 4 | 0 | 4 | 03/31/2026 | 03/31/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Attleboro | On Hold Behind Preceding Group Study
National Grid | LYNN | 692067 | 01904 | 13.3 | Solar | 05_12_51T1 | 05/15/2025 | 06/10/2025 | 5 | 0 | 5 | 06/11/2025 | 06/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 | 05/15/2025 | 8/14/2026 | Y | EXP | 365 | 10/17/2025 | 11/21/2025 | 36 | 0 | 36 |  |  | 11/26/2025 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | GLOUCESTER | 463152 | 01930 | 7.6 | Solar | 05_14_33L1 | 12/07/2022 | 12/08/2022 | 1 | 0 | 1 | 12/09/2022 | 12/09/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 | 12/07/2022 | 5/29/2024 | Y | EXP | 365 | 03/28/2023 | 05/30/2023 | 64 | 0 | 64 |  |  | 6/2/2023 | Connected |  | N | Marlborough | Draft ISAs (?3 Applications) - Completion Documents Hold
National Grid | TOPSFIELD | 223164 | 01983 | 99.9 | Solar | 05_14_57L4 | 04/29/2019 | 05/16/2019 | 12 | 8 | 4 | 05/17/2019 | 05/17/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 6/21/2021 | N | EXP | 730 |  |  | 0 | 0 | 0 |  |  | 3/30/2021 | Connected |  | N | Marlborough | Draft ISAs (?3 Applications) - Conditional Approval Hold
National Grid | WESTFORD | 175757 | 01886 | 295 | Solar | 05_14_73L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 113 | 03/10/2015 | 04/28/2015 | 33 | 0 | 33 | 5/22/2015 | 5/22/2015 | 5/22/2015 | Connected |  | N | Marlborough | Draft ISAs (?3 Applications) - Conditional Approval Hold
National Grid | CHELMSFORD | 665462 | 01824 | 15.76 | Solar | 05_14_8L2 | 01/13/2025 | 01/23/2025 | 5 | 0 | 5 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/13/2025 | 4/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N | Marlborough | Draft ISAs (?3 Applications) - Completion Documents Hold
National Grid | LAWRENCE | 634620 | 01841 | 10 | Solar | 05_01_24W1 | 08/22/2024 | 09/03/2024 | 1 | 0 | 1 | 09/04/2024 | 09/04/2024 | 33 | 24 | 9 | 01/24/2025 | 03/11/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 03/11/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 4/8/2026 | N | EXP | 365 | 08/14/2025 | 08/25/2025 | 12 | 0 | 12 |  |  | 9/3/2025 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | WORCESTER | 175511 | 01605 | 140 | Solar | 05_01_412L1 | 12/05/2014 | 12/05/2014 | 4 | 4 | 0 | 12/12/2014 | 12/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 | 12/05/2014 | 4/30/2015 | Y | EXP | 64 | 06/01/2015 | 07/08/2015 | 25 | 0 | 25 | 2/25/2015 | 2/25/2015 | 8/21/2015 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | WEBSTER | 174943 | 01570 | 3000 | Solar | 05_01_55W1 | 10/02/2011 | 10/02/2011 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West | Time Frame Suspension
National Grid | RUTLAND | 456820 | 01543 | 6 | Solar | 05_05_106W81 | 01/26/2023 | 05/02/2023 | 65 | 65 | 0 | 05/03/2023 | 05/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 6/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2023 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | FALL RIVER | 485595 | 02720 | 0 | Solar | 05_05_310W5 | 12/14/2022 | 12/19/2022 | 3 | 2 | 1 | 12/20/2022 | 12/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 2/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2023 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | SOUTHBOROUGH | 176935 | 01772 | 6 | Solar | 05_12_24W2 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 | 01/29/2016 | 2/6/2017 | Y | EXP | 336 |  |  | 0 | 0 | 0 | 9/19/2016 | 9/19/2016 | 9/19/2016 | Connected |  | N | Marlborough | Draft ISAs (?3 Applications)
National Grid | LYNN | 698492 | 01904 | 11.4 | Solar | 05_12_51T1 | 06/13/2025 | 06/30/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N | Marlborough | Draft ISAs (?3 Applications)
National Grid | BEVERLY | 462041 | 01915 | 14.79 | Solar | 05_14_33L1 | 11/17/2022 | 11/23/2022 | 4 | 1 | 3 | 11/25/2022 | 11/25/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  | 1/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2023 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | BOXFORD | 264770 | 01921 | 9.86 | Solar | 05_14_57L4 | 11/25/2019 | 12/04/2019 | 5 | 0 | 5 | 12/05/2019 | 12/05/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 |  | 11/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2020 | Connected |  | N | Marlborough | Draft ISAs (?3 Applications)
National Grid | WESTFORD | 175756 | 01886 | 225 | Solar | 05_14_73L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 108 | 03/10/2015 | 04/24/2015 | 31 | 0 | 31 | 6/2/2015 | 6/2/2015 | 7/13/2015 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | CHELMSFORD | 681899 | 01824 | 7.6 | Solar | 05_14_8L2 | 04/01/2025 | 05/08/2025 | 1 | 0 | 1 | 05/09/2025 | 05/09/2025 | 16 | 0 | 16 | 06/13/2025 | 07/28/2025 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 07/28/2025 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 8/4/2025 |  | 8/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N | Attleboro | On Hold Behind Preceding Group Study
National Grid | METHUEN | 634322 | 01844 | 19 | Solar | 05_01_24W1 | 08/21/2024 | 08/23/2024 | 2 | 0 | 2 | 08/26/2024 | 08/26/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 |  | 9/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N | Hopedale-East | 160 Day Study - Completion Documents Hold
National Grid | WORCESTER | 175799 | 01606 | 16 | Solar | 05_01_412L1 | 02/27/2015 | 02/27/2015 | 6 | 1 | 5 | 03/10/2015 | 03/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2015 |  | 7/31/2015 | N | EXP | 141 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 12/23/2015 | Connected |  | N | North Andover | Closed
National Grid | DOUGLAS | 174942 | 01516 | 286 | Solar | 05_01_55W1 | 10/05/2011 | 10/05/2011 | 485 | 274 | 211 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Bridgewater | Time Frame Suspension
National Grid | RUTLAND | 512760 | 01543 | 6 | Solar | 05_05_106W81 | 07/18/2023 |  | 81 | 79 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Marlborough | Draft ISAs (?3 Applications)
National Grid | FALL RIVER | 516469 | 02720 | 6 | Solar | 05_05_310W5 | 04/17/2023 | 04/18/2023 | 1 | 0 | 1 | 04/19/2023 | 04/19/2023 | 89 | 67 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 8/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2023 | Connected |  | N | Millbury-Grafton | Closed
National Grid | SOUTHBOROUGH | 195033 | 01772 | 22.8 | Solar | 05_12_24W2 | 09/04/2018 | 10/17/2018 | 10 | 10 | 0 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Fall River-North | Closed
National Grid | LYNN | 704375 | 01904 | 24.7 | Solar | 05_12_51T1 | 07/14/2025 | 07/30/2025 | 10 | 8 | 2 | 07/31/2025 | 07/31/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 8/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N | Hopedale-East | 160 Day Study
National Grid | BEVERLY | 479868 | 01915 | 22.8 | Solar | 05_14_33L1 | 11/23/2022 | 11/29/2022 | 3 | 0 | 3 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East | 160 Day Study
National Grid | BOXFORD | 385677 | 01921 | 3.8 | Solar | 05_14_57L4 | 02/07/2022 | 03/02/2022 | 17 | 16 | 1 | 03/03/2022 | 03/03/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2022 |  | 4/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2022 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | WESTFORD | 176727 | 01886 | 10 | Solar | 05_14_73L1 | 02/23/2016 | 02/23/2016 | 3 | 3 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/23/2016 | 8/28/2017 | Y | EXP | 511 | 07/11/2017 | 07/31/2017 | 14 | 0 | 14 | 8/23/2017 | 8/23/2017 | 8/23/2017 | Connected |  | N | Marlborough | Draft ISAs (?3 Applications)
National Grid | CHELMSFORD | 683910 | 01863 | 11.52 | Solar | 05_14_8L2 | 04/11/2025 | 05/21/2025 | 27 | 24 | 3 | 05/22/2025 | 05/22/2025 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough | Draft ISAs (?3 Applications)
National Grid | LAWRENCE | 639891 | 01841 | 5.76 | Solar | 05_01_24W1 | 09/12/2024 | 09/27/2024 | 3 | 0 | 3 | 09/30/2024 | 09/30/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2024 | 09/12/2024 | 12/10/2025 | Y | EXP | 370 | 01/21/2025 | 10/30/2025 | 283 | 0 | 283 |  |  | 12/5/2025 | Connected |  | N | Hopedale-East | 160 Day Study
National Grid | WORCESTER | 177171 | 01606 | 7.6 | Solar | 05_01_412L1 | 01/27/2017 | 01/27/2017 | 4 | 4 | 0 | 02/03/2017 | 02/03/2017 | 200 | 0 | 200 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2017 |  | 2/4/2018 | N | EXP | 363 | 06/19/2017 | 08/09/2017 | 36 | 0 | 36 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | Closed
National Grid | WEBSTER | 175139 | 01570 | 300 | Bio Gas | 05_01_55W1 | 04/23/2013 | 04/23/2013 | 6 | 0 | 6 | 05/02/2013 | 05/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2013 |  | 8/30/2013 | N | EXP | 89 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 4/16/2014 | Connected |  | N | Millbury-Grafton | Closed - Pending Customer Decision
National Grid | RUTLAND | 607663 | 01543 | 6 | Solar | 05_05_106W81 | 04/30/2024 | 05/16/2024 | 4 | 0 | 4 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 | 04/30/2024 | 7/9/2025 | Y | EXP | 365 | 09/17/2024 | 12/17/2024 | 92 | 0 | 92 |  |  | 1/6/2025 | Connected |  | Y | Bridgewater | Time Frame Suspension
National Grid | FALL RIVER | 553692 | 02720 | 10 | Solar | 05_05_310W5 | 09/12/2023 | 09/18/2023 | 4 | 2 | 2 | 09/19/2023 | 09/19/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Methuen/Haverhill | Closed
National Grid | SOUTHBOROUGH | 251755 | 01772 | 10 | Solar | 05_12_24W2 | 10/17/2019 | 10/21/2019 | 1 | 0 | 1 | 10/22/2019 | 10/22/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2019 | 10/17/2019 | 10/17/2020 | Y | EXP | 365 | 02/25/2020 | 04/13/2020 | 48 | 0 | 48 |  |  | 4/29/2020 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | LYNN | 711434 | 01904 | 11.5 | Solar | 05_12_51T1 | 08/12/2025 | 08/15/2025 | 3 | 0 | 3 | 08/18/2025 | 08/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2025 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | ESSEX | 500918 | 01929 | 22.8 | Solar | 05_14_33L1 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed
National Grid | BOXFORD | 643818 | 01921 | 9.75 | Solar | 05_14_57L4 | 09/30/2024 | 10/21/2024 | 3 | 1 | 2 | 10/22/2024 | 10/22/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/30/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N | Chelmsford/Westford | Closed - Construction Hold
National Grid | WESTFORD | 177572 | 01886 | 7.6 | Solar | 05_14_73L1 | 09/15/2017 | 09/15/2017 | 8 | 8 | 0 | 09/27/2017 | 09/27/2017 | 105 | 0 | 105 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/20/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Beverly | Closed
National Grid | CHELMSFORD | 714702 | 01863 | 5.76 | Solar | 05_14_8L2 | 08/26/2025 | 10/01/2025 | 6 | 0 | 6 | 10/02/2025 | 10/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 | 08/26/2025 | 11/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton | Closed - Awaiting Payment
National Grid | LAWRENCE | 640832 | 01841 | 7.6 | Solar | 05_01_24W1 | 09/17/2024 | 09/25/2024 | 1 | 0 | 1 | 09/26/2024 | 09/26/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2025 | Connected |  | N | Hopedale-East | 160 Day Study
National Grid | WORCESTER | 177168 | 01606 | 4980 | Solar | 05_01_412L1 | 01/26/2017 | 02/01/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2017 | 04/05/2017 | 45 | 33 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  |  | N | STD | 1202 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Ayer-Clinton | Closed
National Grid | WEBSTER | 175272 | 01570 | 997.6 | Solar | 05_01_55W1 | 06/23/2014 | 06/23/2014 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2014 | 08/06/2014 | 23 | 0 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2015 | 06/23/2014 | 6/1/2016 | Y | STD | 469 | 11/29/2016 | 01/16/2017 | 32 | 0 | 32 | 1/13/2017 | 1/13/2017 | 1/13/2017 | Connected |  | N | Millbury-Grafton | Closed
National Grid | RUTLAND | 630417 | 01543 | 5.76 | Solar | 05_05_106W81 | 08/06/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 08/06/2024 | 8/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2024 | Connected |  | N | Methuen/Haverhill | Closed - Construction Hold
National Grid | FALL RIVER | 574904 | 02720 | 0 | Battery Add-On | 05_05_310W5 | 11/30/2023 | 01/03/2024 | 22 | 13 | 9 | 01/04/2024 | 01/04/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough | Draft ISAs (?3 Applications)
National Grid | SOUTHBOROUGH | 309907 | 01772 | 7.6 | Solar | 05_12_24W2 | 09/15/2020 | 09/21/2020 | 3 | 0 | 3 | 09/22/2020 | 09/22/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 | 09/15/2020 | 9/1/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2021 | Connected |  | N | Marlborough | Draft ISAs (?3 Applications)
National Grid | LYNN | 713829 | 01904 | 17.6 | Solar | 05_12_51T1 | 08/21/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N | Marlborough | Draft ISAs (?3 Applications) - Completion Documents Hold
National Grid | MANCHESTER | 590429 | 01944 | 23 | Solar | 05_14_33L1 | 02/15/2024 | 02/22/2024 | 4 | 0 | 4 | 02/23/2024 | 02/23/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North | On Hold Behind Preceding Group Study
National Grid | TOPSFIELD | 656473 | 01983 | 8.41 | Solar | 05_14_57L4 | 12/06/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 295384 | 01886 | 10 | Solar | 05_14_73L1 | 06/08/2020 | 06/15/2020 | 4 | 4 | 0 | 06/16/2020 | 06/16/2020 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 6/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Billerica | Pending
National Grid | CHELMSFORD | 723961 | 01824 | 9.56 | Solar | 05_14_8L2 | 10/03/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | LAWRENCE | 641542 | 01841 | 3.8 | Solar | 05_01_24W1 | 09/19/2024 | 10/07/2024 | 4 | 0 | 4 | 10/08/2024 | 10/08/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  | 12/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2025 | Connected |  | N | Fall River-North | Closed
National Grid | WORCESTER | 177197 | 01606 | 7.6 | Solar | 05_01_412L1 | 11/01/2016 | 11/01/2016 | 3 | 3 | 0 | 11/07/2016 | 11/07/2016 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 11/01/2016 | 5/7/2018 | Y | EXP | 538 | 10/20/2017 | 04/11/2018 | 101 | 0 | 101 |  |  | 5/21/2018 | Connected |  | N | Fall River-North | Closed - Completion Documents Hold
National Grid | WEBSTER | 175296 | 01570 | 19.25 | Solar | 05_01_55W1 | 01/14/2015 | 01/14/2015 | 4 | 2 | 2 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 |  | 5/31/2015 | N | EXP | 117 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 6/10/2015 | Connected |  | N | Fall River-North | Closed
National Grid | RUTLAND | 646610 | 01543 | 7.6 | Solar | 05_05_106W81 | 10/18/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N | Fall River-North | Closed
National Grid | FALL RIVER | 574084 | 02720 | 0 | Battery Add-On | 05_05_310W5 | 11/28/2023 | 11/29/2023 | 1 | 0 | 1 | 11/30/2023 | 11/30/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2024 |  | 3/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N | Fall River-North | Closed
National Grid | SOUTHBOROUGH | 362370 | 01772 | 10 | Solar | 05_12_24W2 | 06/09/2021 | 06/15/2021 | 4 | 3 | 1 | 06/16/2021 | 06/16/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2021 | 06/09/2021 | 10/12/2022 | Y | EXP | 365 | 09/16/2021 | 10/12/2021 | 24 | 0 | 24 |  |  | 10/18/2021 | Connected |  | N | Fall River-North | Closed - Completion Documents Hold
National Grid | LYNN | 724900 | 01904 | 9.5 | Solar | 05_12_51T1 | 10/08/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2026 | Connected |  | N | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | MANCHESTER | 620928 | 01944 | 23 | Solar | 05_14_33L1 | 06/27/2024 | 07/01/2024 | 2 | 0 | 2 | 07/02/2024 | 07/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/27/2024 | 7/25/2025 | Y | EXP | 365 | 10/04/2024 | 11/14/2024 | 42 | 0 | 42 |  |  | 10/8/2024 | Connected |  | N | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | TOPSFIELD | 721432 | 01983 | 7.6 | Solar | 05_14_58L1 | 09/24/2025 | 10/03/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 09/24/2025 | 12/22/2026 | Y | EXP | 365 | 03/11/2026 | 03/28/2026 | 18 | 0 | 18 |  |  |  | Meter Installation |  | Y | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 298402 | 01824 | 4.64 | Solar | 05_14_73L1 | 07/14/2020 | 07/15/2020 | 0 | 0 | 0 | 07/16/2020 | 07/16/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2021 | Connected |  | N | Tewksbury | Closed
National Grid | CHELMSFORD | 726834 | 01824 | 11.52 | Solar | 05_14_8L2 | 10/23/2025 |  | 78 | 77 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Tewksbury | Closed - Awaiting Payment
National Grid | LAWRENCE | 642848 | 01841 | 7.6 | Solar | 05_01_24W1 | 09/25/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 56 | 36 | 20 | 03/19/2025 | 03/19/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 03/19/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 4/25/2025 | 09/25/2024 | 5/23/2026 | Y | EXP | 365 | 06/28/2025 | 11/13/2025 | 139 | 0 | 139 |  |  | 12/17/2025 | Connected |  | N | Tewksbury | Closed - Completion Documents Hold
National Grid | WORCESTER | 177263 | 01605 | 19 | Solar | 05_01_412L1 | 08/23/2016 | 08/23/2016 | 2 | 2 | 0 | 08/26/2016 | 08/26/2016 | 227 | 0 | 227 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2016 |  | 8/29/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton | Draft Group Study Agreement
National Grid | WEBSTER | 175294 | 01570 | 6 | Solar | 05_01_55W1 | 01/13/2015 | 01/13/2015 | 28 | 27 | 1 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 |  | 5/31/2015 | N | EXP | 95 |  |  | 0 | 0 | 0 | 4/28/2015 | 4/28/2015 | 11/12/2015 | Connected |  | N | Ayer-Clinton | Draft Group Study Agreement
National Grid | RUTLAND | 649794 | 01543 | 7.6 | Solar | 05_05_106W81 | 10/25/2024 | 11/12/2024 | 8 | 2 | 6 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2025 | Connected |  | N | Ayer-Clinton | Draft Group Study Agreement
National Grid | FALL RIVER | 624754 | 02720 | 15.3 | Solar | 05_05_310W5 | 07/15/2024 | 07/18/2024 | 3 | 0 | 3 | 07/19/2024 | 07/19/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2024 | Connected |  | N | Ayer-Clinton | Draft Group Study Agreement
National Grid | MARLBOROUGH | 367457 | 01752 | 7.6 | Solar | 05_12_24W2 | 07/09/2021 | 07/12/2021 | 1 | 0 | 1 | 07/13/2021 | 07/13/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2021 | 07/09/2021 | 8/16/2022 | Y | EXP | 365 | 01/13/2022 | 03/31/2022 | 78 | 0 | 78 |  |  | 4/11/2022 | Connected |  | N | Leominster | Group Window
National Grid | LYNN | 732153 | 01904 | 23 | Solar | 05_12_51T1 | 11/06/2025 | 11/10/2025 | 2 | 0 | 2 | 11/12/2025 | 11/12/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N | Leominster | Group Window
National Grid | BEVERLY | 624766 | 01915 | 9.86 | Solar | 05_14_33L1 | 07/15/2024 | 08/28/2024 | 3 | 1 | 2 | 08/29/2024 | 08/29/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 | 07/15/2024 | 11/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | Y | Leominster | Group Window
National Grid | TOPSFIELD | 726691 | 01983 | 15.2 | Solar | 05_14_58L1 | 10/15/2025 | 10/20/2025 | 3 | 0 | 3 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  | 11/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Leominster | Group Window
National Grid | WESTFORD | 303103 | 01886 | 200 | Solar | 05_14_73L1 | 08/13/2020 | 01/10/2022 | 23 | 12 | 11 | 09/17/2020 | 09/17/2020 | 83 | 60 | 23 | 01/27/2021 | 03/22/2021 | 38 | 0 | 38 |  |  | 0 | 0 | 0 | 03/22/2021 | 38 | 0 | 38 |  |  | 0 | 0 | 0 | 4/6/2021 | 08/13/2020 | 8/25/2025 | Y | EXP | 147 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 174235 | 01824 | 725 | Solar | 05_14_8L3 | 02/02/2012 | 02/02/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2012 | 09/24/2012 | 123 | 0 | 123 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | LAWRENCE | 650683 | 01843 | 3.8 | Solar | 05_01_24W1 | 11/11/2024 | 12/06/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/11/2024 | 2/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2025 | Connected |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 177697 | 01606 | 3990 | Solar | 05_01_412L1 | 03/21/2017 | 03/21/2017 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2017 | 04/24/2017 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WEBSTER | 175339 | 01570 | 222 | Solar | 05_01_55W1 | 01/20/2015 | 01/20/2015 | 5 | 1 | 4 | 01/28/2015 | 01/28/2015 | 581 | 0 | 581 | 03/27/2015 | 04/28/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 04/28/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 5/5/2015 | 01/20/2015 | 12/31/2016 | Y | EXP | 606 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 729535 | 01543 | 150 | Solar | 05_05_106W82 | 10/31/2025 | 12/03/2025 | 21 | 14 | 7 | 12/04/2025 | 12/04/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Methuen/Haverhill | Closed - Construction Hold
National Grid | FALL RIVER | 638803 | 02723 | 10 | Solar | 05_05_310W5 | 09/09/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 09/09/2024 | 1/8/2026 | Y | EXP | 365 | 12/19/2024 | 02/13/2025 | 57 | 0 | 57 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed
National Grid | MARLBOROUGH | 438823 | 01752 | 7.6 | Solar | 05_12_24W2 | 08/18/2022 | 08/23/2022 | 4 | 3 | 1 | 08/24/2022 | 08/24/2022 | 47 | 28 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2022 |  | 11/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed
National Grid | LYNN | 445040 | 01904 | 250 | Solar | 05_12_51T2 | 08/08/2022 | 08/31/2022 | 17 | 7 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Methuen/Haverhill | Closed
National Grid | HAMILTON | 630827 | 01982 | 4.64 | Solar | 05_14_33L1 | 08/07/2024 | 08/13/2024 | 7 | 3 | 4 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 | 08/07/2024 | 1/3/2026 | Y | EXP | 365 | 01/23/2025 | 01/30/2025 | 8 | 0 | 8 |  |  | 2/5/2025 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | TOPSFIELD | 178428 | 01983 | 22.72 | Solar | 05_14_58L1 | 03/05/2018 | 03/05/2018 | 39 | 37 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 3/11/2019 | N | EXP | 80 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed
National Grid | WESTFORD | 354303 | 01886 | 7.6 | Solar | 05_14_73L1 | 04/23/2021 | 04/27/2021 | 2 | 1 | 1 | 04/28/2021 | 04/28/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2021 |  | 9/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2021 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | CHELMSFORD | 174234 | 01824 | 500 | Solar | 05_14_8L3 | 02/02/2012 | 02/02/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2012 | 09/24/2012 | 123 | 0 | 123 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed - Construction Hold
National Grid | LAWRENCE | 685939 | 01843 | 15.2 | Solar | 05_01_24W1 | 04/17/2025 | 04/22/2025 | 2 | 0 | 2 | 04/23/2025 | 04/23/2025 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed
National Grid | WORCESTER | 178538 | 01606 | 7.6 | Solar | 05_01_412L1 | 01/25/2018 | 02/08/2018 | 9 | 0 | 9 | 02/08/2018 | 02/08/2018 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 |  | 1/31/2019 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 9/11/2019 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | WEBSTER | 175371 | 01570 | 46.08 | Solar | 05_01_55W1 | 02/14/2014 | 02/14/2014 | 5 | 0 | 5 | 02/25/2014 | 02/25/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2014 | 02/14/2014 | 8/29/2014 | Y | EXP | 57 | 01/06/2015 | 01/06/2015 | 0 | 0 | 0 | 3/2/2015 | 3/2/2015 | 3/5/2015 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | RUTLAND | 189412 | 01543 | 740 | Solar | 05_05_106W82 | 08/08/2018 | 10/17/2018 | 44 | 37 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2018 | 11/15/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Methuen/Haverhill | Closed
National Grid | FALL RIVER | 638771 | 02723 | 0 | Solar | 05_05_310W5 | 09/09/2024 | 09/11/2024 | 2 | 0 | 2 | 09/12/2024 | 09/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2024 | Connected |  | N | Cape Ann | Closed - Study Hold
National Grid | SOUTHBOROUGH | 552287 | 01772 | 10 | Solar | 05_12_24W2 | 10/11/2023 | 10/12/2023 | 1 | 0 | 1 | 10/13/2023 | 10/13/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2023 | 10/11/2023 | 2/14/2025 | Y | EXP | 365 | 04/11/2024 | 04/29/2024 | 19 | 0 | 19 |  |  | 5/5/2024 | Connected |  | N | Cape Ann | Closed - Pending Customer Decision
National Grid | LYNN | 515409 | 01904 | 34.6 | Solar | 05_12_51T2 | 05/24/2023 | 07/14/2023 | 34 | 24 | 10 | 07/17/2023 | 07/17/2023 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 | 05/24/2023 | 7/28/2026 | Y | EXP | 220 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y | Cape Ann | Closed - Study Hold
National Grid | HAMILTON | 649671 | 01982 | 7.6 | Solar | 05_14_33L1 | 11/04/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann | Closed - Awaiting Payment
National Grid | TOPSFIELD | 223575 | 01983 | 0 | Solar | 05_14_58L1 | 04/29/2019 | 05/07/2019 | 5 | 0 | 5 | 05/08/2019 | 05/08/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2019 |  | 4/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2020 | Connected |  | N | Cape Ann | Closed
National Grid | WESTFORD | 469528 | 01886 | 7.6 | Solar | 05_14_73L1 | 10/19/2022 | 10/20/2022 | 1 | 0 | 1 | 10/21/2022 | 10/21/2022 | 40 | 22 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2022 |  | 12/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2023 | Connected |  | N | Cape Ann | Closed
National Grid | CHELMSFORD | 175191 | 01824 | 45 | Solar | 05_14_8L3 | 11/22/2013 | 11/22/2013 | 6 | 0 | 6 | 12/04/2013 | 12/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2013 |  | 1/31/2014 | N | EXP | 50 |  |  | 0 | 0 | 0 | 3/26/2014 | 3/26/2014 | 4/25/2014 | Connected |  | N | Cape Ann | Closed - Study Hold
National Grid | LAWRENCE | 660684 | 01843 | 0 | Other | 05_01_24W2 | 04/08/2025 | 06/17/2025 | 48 | 38 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/18/2025 | 07/17/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | WORCESTER | 184051 | 01606 | 2375 | Solar | 05_01_412L1 | 04/30/2018 | 04/30/2018 | 14 | 13 | 1 |  |  | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton | Closed - Completion Documents Hold
National Grid | WEBSTER | 175471 | 01570 | 4.75 | Solar | 05_01_55W1 | 12/01/2014 | 12/01/2014 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2014 | 01/02/2015 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2015 |  | 4/30/2015 | N | STD | 118 |  |  | 0 | 0 | 0 | 6/3/2015 | 6/3/2015 | 6/10/2015 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | RUTLAND | 203924 | 01543 | 10 | Solar | 05_05_106W82 | 01/10/2019 | 01/23/2019 | 7 | 0 | 7 | 01/24/2019 | 01/24/2019 | 148 | 0 | 148 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 657547 | 02723 | 10 | Solar | 05_05_310W5 | 11/28/2024 | 01/14/2025 | 21 | 17 | 4 | 01/15/2025 | 01/15/2025 | 26 | 0 | 26 | 03/03/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/28/2024 | 3/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | SOUTHBOROUGH | 567702 | 01772 | 5 | Solar | 05_12_24W2 | 02/26/2024 | 03/12/2024 | 11 | 6 | 5 | 03/13/2024 | 03/13/2024 | 28 | 24 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 |  | 4/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2024 | Connected |  | N | Methuen/Haverhill | Closed - Completion Documents Hold
National Grid | LYNN | 653313 | 01904 | 240 | Solar | 05_12_51T2 | 11/13/2024 | 12/10/2024 | 18 | 8 | 10 |  |  | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N | Cape Ann | Closed - Sent to Customer
National Grid | WENHAM | 680660 | 01984 | 15.2 | Solar | 05_14_33L1 | 03/26/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North | 160 Day Study
National Grid | BOXFORD | 258486 | 01921 | 10 | Solar | 05_14_58L1 | 10/05/2019 | 10/11/2019 | 4 | 0 | 4 | 10/15/2019 | 10/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  | 10/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2020 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | WESTFORD | 580798 | 01886 | 9.765 | Solar | 05_14_73L1 | 01/23/2024 | 01/26/2024 | 4 | 1 | 3 | 01/29/2024 | 01/29/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  | 3/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2024 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | CHELMSFORD | 723449 | 01824 | 150 | Solar | 05_14_8T1 | 10/30/2025 | 12/08/2025 | 25 | 22 | 3 | 12/09/2025 | 12/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Brockton-North | 160 Day Study
National Grid | ANDOVER | 745145 | 01810 | 8.36 | Solar | 05_01_24W2 | 01/13/2026 | 01/23/2026 | 5 | 2 | 3 | 02/11/2026 | 02/11/2026 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Brockton-North | 160 Day Study
National Grid | WORCESTER | 189710 | 01606 | 2000 | Solar | 05_01_412L1 | 07/16/2018 | 08/06/2018 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2018 | 11/30/2018 | 78 | 25 | 53 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-North | 160 Day Study
National Grid | WEBSTER | 175638 | 01570 | 15.8 | Solar | 05_01_55W1 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2014 |  | 2/6/2015 | N | EXP | 95 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 | 5/27/2016 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | RUTLAND | 220893 | 01543 | 489 | Solar | 05_05_106W82 | 04/19/2019 | 04/23/2019 | 1 | 0 | 1 | 04/24/2019 | 04/24/2019 | 10 | 0 | 10 | 05/23/2019 | 06/11/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 06/11/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-North | 160 Day Study
National Grid | FALL RIVER | 661259 | 02723 | 5.76 | Solar | 05_05_310W5 | 12/17/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/17/2024 | 3/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | MARLBOROUGH | 588113 | 01752 | 10 | Solar | 05_12_24W2 | 02/12/2024 | 02/22/2024 | 7 | 4 | 3 | 02/23/2024 | 02/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/12/2024 | 4/4/2025 | Y | EXP | 365 | 05/17/2024 | 06/06/2024 | 20 | 0 | 20 |  |  | 6/25/2024 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | LYNN | 714498 | 01904 | 20 | Solar | 05_12_51T2 | 08/25/2025 | 09/03/2025 | 6 | 1 | 5 | 09/04/2025 | 09/04/2025 | 39 | 26 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 08/25/2025 | 11/18/2026 | Y | EXP | 365 | 03/07/2026 |  | 26 | 0 | 26 |  |  |  | Construction |  | N | Brockton-North | 160 Day Study
National Grid | HAMILTON | 701737 | 01982 | 17.6 | Solar | 05_14_33L1 | 08/01/2025 | 08/05/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N | Scituate | Closed
National Grid | BOXFORD | 290418 | 01921 | 10 | Solar | 05_14_58L1 | 05/04/2020 | 05/11/2020 | 4 | 0 | 4 | 05/12/2020 | 05/12/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2020 | Connected |  | N | Scituate | Closed
National Grid | WESTFORD | 637040 | 01886 | 17.6 | Solar | 05_14_73L1 | 09/17/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 09/17/2024 | 11/27/2025 | Y | EXP | 365 | 03/26/2025 | 04/16/2025 | 22 | 0 | 22 |  |  | 4/23/2025 | Connected |  | N | Scituate | Closed - Initial Review
National Grid | WESTFORD | 174755 | 01886 | 495 | Solar | 05_14_8T1 | 02/05/2014 | 02/05/2014 | 5 | 0 | 5 | 02/13/2014 | 02/13/2014 | 0 | 0 | 0 | 11/04/2014 | 11/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2014 |  | 6/30/2014 | N | EXP | 111 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 10/2/2014 | Connected |  | N | Bridgewater | Time Frame Suspension
National Grid | ANDOVER | 746118 | 01810 | 11.5 | Solar | 05_01_24W2 | 01/19/2026 | 01/22/2026 | 18 | 15 | 3 | 03/11/2026 | 03/11/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | WORCESTER | 202707 | 01606 | 10 | Solar | 05_01_412L1 | 12/06/2018 | 01/14/2019 | 25 | 20 | 5 | 01/15/2019 | 01/15/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2019 | 12/06/2018 | 10/30/2019 | Y | EXP | 280 | 06/26/2019 | 08/26/2019 | 61 | 0 | 61 |  |  | 9/16/2019 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | WEBSTER | 175720 | 01570 | 499 | Solar | 05_01_55W1 | 12/31/2014 | 12/31/2014 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/15/2015 | 02/12/2015 | 19 | 4 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | RUTLAND | 337864 | 01543 | 7.6 | Solar | 05_05_106W82 | 02/22/2021 | 03/02/2021 | 5 | 0 | 5 | 03/03/2021 | 03/03/2021 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2021 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | FALL RIVER | 685105 | 02723 | 9.6 | Solar | 05_05_310W5 | 04/24/2025 | 05/22/2025 | 2 | 0 | 2 | 05/23/2025 | 05/23/2025 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2025 |  | 7/16/2026 | N | EXP | 365 | 11/04/2025 | 11/21/2025 | 18 | 0 | 18 |  |  | 2/10/2026 | Connected |  | N | Brockton-South | Closed
National Grid | MARLBOROUGH | 599697 | 01752 | 10 | Solar | 05_12_24W2 | 04/12/2024 | 04/15/2024 | 0 | 0 | 0 | 04/16/2024 | 04/16/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 | 04/12/2024 | 6/14/2025 | Y | EXP | 365 | 07/30/2024 | 08/26/2024 | 28 | 0 | 28 |  |  | 9/12/2024 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | LYNN | 724733 | 01904 | 0 | Solar | 05_12_51T2 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 720945 | 01982 | 23 | Solar | 05_14_33L1 | 09/22/2025 | 09/24/2025 | 2 | 0 | 2 | 09/25/2025 | 09/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | TOPSFIELD | 292702 | 01983 | 0 | Solar | 05_14_58L1 | 05/20/2020 | 05/22/2020 | 1 | 0 | 1 | 05/26/2020 | 05/26/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 |  | 5/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2020 | Connected |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 644757 | 01886 | 17.101 | Solar | 05_14_73L1 | 10/03/2024 | 10/07/2024 | 2 | 0 | 2 | 10/08/2024 | 10/08/2024 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 175373 | 01886 | 494 | Solar | 05_14_8T1 | 02/14/2014 | 02/14/2014 | 7 | 1 | 6 | 02/27/2014 | 02/27/2014 | 0 | 0 | 0 | 03/25/2014 | 04/21/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 04/21/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 7/29/2014 | 02/14/2014 | 12/31/2016 | Y | EXP | 886 | 08/13/2015 | 12/23/2015 | 90 | 0 | 90 | 2/19/2015 | 2/19/2015 | 12/21/2015 | Connected |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | ANDOVER | 746119 | 01810 | 11.5 | Solar | 05_01_24W2 | 01/19/2026 | 01/22/2026 | 2 | 0 | 2 | 02/04/2026 | 02/04/2026 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Brockton-South | Closed - Awaiting Payment
National Grid | WORCESTER | 306367 | 01606 | 6 | Solar | 05_01_412L1 | 09/18/2020 | 09/21/2020 | 0 | 0 | 0 | 09/22/2020 | 09/22/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  | 9/20/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-South | Closed
National Grid | WEBSTER | 175828 | 01570 | 10 | Solar | 05_01_55W1 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/27/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 4/4/2016 | 4/4/2016 | 4/8/2016 | Connected |  | N | Hopedale-East | 160 Day Study
National Grid | RUTLAND | 379546 | 01543 | 10 | Solar | 05_05_106W82 | 09/09/2021 | 09/28/2021 | 4 | 3 | 1 | 09/29/2021 | 09/29/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2021 | 09/09/2021 | 1/3/2023 | Y | EXP | 365 | 12/04/2021 | 01/03/2022 | 31 | 0 | 31 |  |  | 2/5/2022 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | FALL RIVER | 686547 | 02723 | 9.86 | Solar | 05_05_310W6 | 04/24/2025 | 06/24/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 | 04/24/2025 | 7/24/2026 | Y | EXP | 365 | 10/01/2025 |  | 183 | 0 | 183 |  |  |  | Completion Documents |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications - Construction Hold
National Grid | SOUTHBOROUGH | 599918 | 01772 | 6 | Solar | 05_12_24W2 | 04/09/2024 | 04/16/2024 | 5 | 1 | 4 | 04/17/2024 | 04/17/2024 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 7/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Scoping Meeting
National Grid | LYNN | 746712 | 01904 | 0 | Battery Add-On | 05_12_51T2 | 01/21/2026 | 01/27/2026 | 4 | 0 | 4 | 01/28/2026 | 01/28/2026 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hopedale-West | Time Frame Suspension
National Grid | BEVERLY | 724078 | 01915 | 16 | Solar | 05_14_33L1 | 10/04/2025 | 10/07/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N | Billerica | Closed
National Grid | TOPSFIELD | 306363 | 01983 | 0 | Battery Add-On | 05_14_58L1 | 08/12/2020 | 08/14/2020 | 1 | 1 | 0 | 08/17/2020 | 08/17/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 |  | 8/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N | Cape Ann | Closed - Design Hold
National Grid | WESTFORD | 645633 | 01886 | 10 | Solar | 05_14_73L1 | 10/21/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Attleboro | Time Frame Suspension
National Grid | CHELMSFORD | 176839 | 01824 | 50 | Solar | 05_14_8T1 | 04/29/2016 | 04/29/2016 | 3 | 3 | 0 | 05/04/2016 | 05/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2016 |  | 5/4/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/13/2016 | 10/13/2016 | 11/3/2016 | Connected |  | N | Dracut | Closed
National Grid | ANDOVER | 174591 | 01810 | 39 | Solar | 05_01_24W2 | 04/27/2011 | 04/27/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2011 |  | 8/4/2012 | N | EXP | 250 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 8/2/2012 | Connected |  | N | Bridgewater | Time Frame Suspension
National Grid | WORCESTER | 312153 | 01606 | 5.76 | Solar | 05_01_412L1 | 12/01/2020 | 12/03/2020 | 1 | 0 | 1 | 12/04/2020 | 12/04/2020 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/01/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill | Closed
National Grid | WEBSTER | 175887 | 01570 | 7.6 | Solar | 05_01_55W1 | 05/26/2015 | 05/26/2015 | 0 | 0 | 0 | 05/28/2015 | 05/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2015 |  | 10/30/2015 | N | EXP | 122 |  |  | 0 | 0 | 0 | 9/22/2015 | 9/22/2015 | 10/2/2015 | Connected |  | N | Attleboro | Time Frame Suspension
National Grid | RUTLAND | 460340 | 01543 | 5.51 | Solar | 05_05_106W82 | 09/27/2022 | 09/29/2022 | 3 | 1 | 2 | 09/30/2022 | 09/30/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2022 |  | 11/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2023 | Connected |  | Y | Dracut | Closed
National Grid | FALL RIVER | 755484 | 02723 | 11.5 | Solar | 05_05_310W6 | 03/09/2026 | 03/11/2026 | 2 | 0 | 2 | 03/12/2026 | 03/12/2026 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Attleboro | Time Frame Suspension
National Grid | SOUTHBOROUGH | 602977 | 01772 | 3.8 | Solar | 05_12_24W2 | 04/23/2024 | 04/26/2024 | 3 | 0 | 3 | 04/29/2024 | 04/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 |  | 6/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N | Attleboro | Time Frame Suspension
National Grid | LYNN | 169987 | 01904 | 10 | Solar | 05_12_51T2 | 07/09/2018 | 07/24/2018 | 11 | 8 | 3 | 07/25/2018 | 07/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 | 07/09/2018 | 10/1/2019 | Y | EXP | 432 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N | Billerica | Closed
National Grid | ESSEX | 731440 | 01929 | 14.44 | Solar | 05_14_33L2 | 11/05/2025 | 11/05/2025 | 2 | 0 | 2 | 12/11/2025 | 12/11/2025 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2026 |  | 3/16/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | BOXFORD | 321713 | 01921 | 16 | Solar | 05_14_58L1 | 10/26/2020 | 10/27/2020 | 0 | 0 | 0 | 10/28/2020 | 10/28/2020 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2020 |  | 4/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2021 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | WESTFORD | 648564 | 01886 | 10 | Solar | 05_14_73L1 | 11/01/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 11/01/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N | Worcester North/South | Closed
National Grid | CHELMSFORD | 177266 | 01824 | 143 | Solar | 05_14_8T1 | 11/08/2016 | 11/08/2016 | 12 | 12 | 0 | 11/28/2016 | 11/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 11/13/2017 | N | EXP | 313 |  |  | 0 | 0 | 0 | 4/7/2017 | 4/7/2017 | 3/30/2017 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | ANDOVER | 174763 | 01810 | 60 | Solar | 05_01_24W2 | 08/23/2012 | 08/23/2012 | 8 | 0 | 8 | 09/06/2012 | 09/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 12/7/2012 | N | EXP | 5 |  |  | 0 | 0 | 0 | 12/17/2012 | 12/17/2012 | 12/31/2012 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | WORCESTER | 365160 | 01606 | 15.6 | Solar | 05_01_412L1 | 06/21/2021 | 06/23/2021 | 2 | 0 | 2 | 06/24/2021 | 06/24/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2021 | 06/21/2021 | 11/5/2023 | Y | EXP | 365 | 07/15/2022 | 08/26/2022 | 43 | 0 | 43 |  |  | 12/7/2022 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | WEBSTER | 176009 | 01570 | 2230 | Solar | 05_01_55W1 | 08/13/2015 | 08/18/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2015 | 09/16/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2017 | 08/13/2015 | 9/19/2019 | Y | STD | 846 | 11/09/2018 | 01/31/2019 | 83 | 0 | 83 | 6/7/2019 | 6/19/2019 | 8/28/2019 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | RUTLAND | 518145 | 01543 | 14.5 | Solar | 05_05_106W82 | 04/15/2023 | 04/19/2023 | 2 | 0 | 2 | 04/20/2023 | 04/20/2023 | 28 | 24 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 11/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2024 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | FALL RIVER | 174836 | 02723 | 1450 | Solar | 05_05_310W6 | 08/31/2012 | 08/31/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/12/2012 | 11/27/2012 | 36 | 0 | 36 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/1/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | SOUTHBOROUGH | 605616 | 01772 | 3.8 | Solar | 05_12_24W2 | 04/22/2024 | 05/01/2024 | 5 | 0 | 5 | 05/02/2024 | 05/02/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 | 04/22/2024 | 6/24/2025 | Y | EXP | 365 | 09/07/2024 | 11/01/2024 | 56 | 0 | 56 |  |  | 11/15/2024 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | LYNN | 174123 | 01904 | 128.25 | Solar | 05_12_51T2 | 04/04/2012 | 04/04/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/15/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | Time Frame Suspension
National Grid | HAMILTON | 177680 | 01982 | 45.6 | Solar | 05_14_33L2 | 07/25/2017 | 07/25/2017 | 35 | 33 | 2 | 09/13/2017 | 09/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2017 |  | 7/30/2018 | N | EXP | 320 |  |  | 0 | 0 | 0 | 2/13/2018 | 2/13/2018 | 2/13/2018 | Connected |  | N | Hopedale-West | Time Frame Suspension
National Grid | BOXFORD | 344742 | 01921 | 15.2 | Solar | 05_14_58L1 | 03/02/2021 | 03/03/2021 | 0 | 0 | 0 | 03/04/2021 | 03/04/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 3/2/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | Time Frame Suspension
National Grid | WESTFORD | 653596 | 01886 | 10 | Solar | 05_14_73L1 | 11/15/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 | 02/13/2025 | 02/12/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 11/15/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North | 160 Day Study
National Grid | WESTFORD | 177265 | 01886 | 161 | Solar | 05_14_8T1 | 11/08/2016 | 11/08/2016 | 12 | 12 | 0 | 11/28/2016 | 11/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 11/13/2017 | N | EXP | 313 |  |  | 0 | 0 | 0 | 3/30/2017 | 3/30/2017 | 3/30/2017 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | ANDOVER | 175456 | 01810 | 87 | Solar | 05_01_24W2 | 07/17/2014 | 07/17/2014 | 3 | 0 | 3 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 11/28/2014 | N | EXP | 53 |  |  | 0 | 0 | 0 | 10/6/2014 | 10/6/2014 | 3/25/2016 | Connected |  | N | Beverly | Closed
National Grid | WORCESTER | 371739 | 01605 | 15.2 | Solar | 05_01_412L1 | 07/23/2021 | 07/26/2021 | 2 | 1 | 1 | 07/27/2021 | 07/27/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2021 |  | 9/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2022 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | WEBSTER | 176053 | 01570 | 22.58 | Solar | 05_01_55W1 | 01/29/2015 | 01/29/2015 | 5 | 4 | 1 | 02/06/2015 | 02/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2015 |  | 6/30/2015 | N | EXP | 141 |  |  | 0 | 0 | 0 | 3/10/2015 | 3/10/2015 | 6/10/2015 | Connected |  | N | Tewksbury | Closed
National Grid | RUTLAND | 529857 | 01543 | 3.8 | Solar | 05_05_106W82 | 07/06/2023 | 08/03/2023 | 21 | 20 | 1 | 08/04/2023 | 08/04/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 07/06/2023 | 11/26/2024 | Y | EXP | 365 | 10/24/2023 | 12/01/2023 | 39 | 0 | 39 |  |  | 12/4/2023 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | FALL RIVER | 175281 | 02723 | 42.57 | Solar | 05_05_310W6 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 4/30/2015 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | SOUTHBOROUGH | 632460 | 01772 | 7.6 | Solar | 05_12_24W2 | 08/15/2024 | 08/23/2024 | 1 | 0 | 1 | 08/26/2024 | 08/26/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-South | Awaiting Full Payments for Common System Modifications
National Grid | LYNN | 174122 | 01904 | 250 | Solar | 05_12_51T2 | 04/04/2012 | 04/04/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/15/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Gardner-Winchendon | Scoping Meeting
National Grid | HAMILTON | 178574 | 01982 | 11.4 | Solar | 05_14_33L2 | 12/11/2017 | 12/11/2017 | 0 | 0 | 0 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 7/15/2020 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 3/23/2020 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications - Design Hold
National Grid | TOPSFIELD | 351803 | 01983 | 10 | Solar | 05_14_58L1 | 04/09/2021 | 04/12/2021 | 0 | 0 | 0 | 04/15/2021 | 04/15/2021 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 7/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2022 | Connected |  | N | Ayer-Clinton | Closed
National Grid | WESTFORD | 660285 | 01886 | 10 | Solar | 05_14_73L1 | 12/12/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Gardner-Winchendon | Scoping Meeting
National Grid | WESTFORD | 195724 | 01886 | 400 | Natural Gas | 05_14_8T1 | 02/28/2019 | 07/02/2019 | 302 | 26 | 276 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford | Closed - Construction Hold
National Grid | ANDOVER | 176042 | 01810 | 476 | Solar | 05_01_24W2 | 08/14/2015 | 08/14/2015 | 1 | 1 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2015 |  | 8/22/2016 | N | EXP | 341 |  |  | 0 | 0 | 0 | 10/6/2015 | 10/6/2015 | 6/9/2016 | Connected |  | N | Ayer-Clinton | Closed
National Grid | WORCESTER | 379708 | 01606 | 9.8 | Solar | 05_01_412L1 | 09/15/2021 | 12/20/2021 | 3 | 0 | 3 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/15/2021 | 4/26/2023 | Y | EXP | 365 | 03/31/2022 | 04/26/2022 | 27 | 0 | 27 |  |  | 5/24/2022 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | WEBSTER | 176129 | 01570 | 4.3 | Solar | 05_01_55W1 | 04/13/2015 | 04/13/2015 | 3 | 2 | 1 | 04/16/2015 | 04/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2015 |  | 8/31/2015 | N | EXP | 137 |  |  | 0 | 0 | 0 | 4/27/2015 | 4/27/2015 | 8/26/2015 | Connected |  | N | MPL-Northwest | Closed
National Grid | RUTLAND | 569078 | 01543 | 3.8 | Solar | 05_05_106W82 | 11/30/2023 | 12/05/2023 | 34 | 32 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Gardner-Winchendon | Scoping Meeting
National Grid | FALL RIVER | 175478 | 02723 | 250 | Solar | 05_05_310W6 | 03/13/2014 | 03/13/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2014 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | North Andover | Closed
National Grid | SOUTHBOROUGH | 634313 | 01772 | 8.125 | Solar | 05_12_24W2 | 08/21/2024 | 09/17/2024 | 10 | 6 | 4 | 09/18/2024 | 09/18/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2024 | 08/21/2024 | 10/16/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N | Chelmsford/Westford | Closed
National Grid | LYNN | 174411 | 01904 | 14 | Solar | 05_12_51T2 | 06/22/2012 | 06/22/2012 | 10 | 0 | 10 | 07/09/2012 | 07/09/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2012 |  | 9/6/2012 | N | EXP | 96 |  |  | 0 | 0 | 0 | 9/28/2012 | 9/28/2012 | 12/11/2012 | Connected |  | N | Beverly | Closed
National Grid | WENHAM | 348454 | 01984 | 10 | Solar | 05_14_33L2 | 04/14/2021 | 04/14/2021 | 0 | 0 | 0 | 04/15/2021 | 04/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 | 04/14/2021 | 4/14/2022 | Y | EXP | 365 | 07/14/2021 | 07/13/2021 | 0 | 0 | 0 |  |  | 9/2/2021 | Connected |  | N | Millbury-Grafton | Closed
National Grid | TOPSFIELD | 373166 | 01983 | 15.2 | Solar | 05_14_58L1 | 07/30/2021 | 09/08/2021 | 27 | 25 | 2 | 09/09/2021 | 09/09/2021 | 85 | 60 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2022 |  | 1/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2022 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications
National Grid | CHELMSFORD | 670687 | 01824 | 7.6 | Solar | 05_14_73L1 | 02/07/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N | Bridgewater | Time Frame Suspension
National Grid | WESTFORD | 176086 | 01886 | 5 | Solar | 05_01_24W2 | 02/02/2015 | 02/02/2015 | 5 | 1 | 4 | 02/10/2015 | 02/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 | 02/02/2015 | 12/31/2016 | Y | EXP | 675 | 03/11/2016 | 03/31/2016 | 13 | 0 | 13 | 8/8/2016 | 8/8/2016 | 8/8/2016 | Connected |  | N | North Andover | Closed
National Grid | ANDOVER | 473685 | 01810 | 11.02 | Solar | 05_01_412L1 | 11/17/2022 | 12/20/2022 | 22 | 20 | 2 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications
National Grid | WORCESTER | 176118 | 01605 | 6 | Solar | 05_01_55W1 | 08/21/2015 | 08/21/2015 | 13 | 13 | 0 | 09/14/2015 | 09/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2015 |  | 8/30/2016 | N | EXP | 348 |  |  | 0 | 0 | 0 | 4/14/2016 | 4/14/2016 | 4/25/2016 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications
National Grid | DOUGLAS | 580036 | 01516 | 6 | Solar | 05_05_106W82 | 02/02/2024 | 02/06/2024 | 2 | 0 | 2 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/02/2024 | 4/17/2025 | Y | EXP | 365 | 07/17/2024 | 08/27/2024 | 42 | 0 | 42 |  |  | 10/18/2024 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications
National Grid | RUTLAND | 176834 | 01543 | 650 | Solar | 05_05_310W6 | 02/29/2016 | 02/29/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/08/2016 | 05/10/2016 | 43 | 43 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2017 |  | 12/8/2017 | N | STD | 294 |  |  | 0 | 0 | 0 | 12/7/2017 | 12/7/2017 | 12/14/2017 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 666059 | 02723 | 10 | Solar | 05_12_24W2 | 01/15/2025 | 02/24/2025 | 5 | 1 | 4 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 | 01/15/2025 | 5/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications
National Grid | SOUTHBOROUGH | 175123 | 01772 | 18 | Solar | 05_12_51T2 | 08/16/2012 | 08/16/2012 | 5 | 0 | 5 | 08/24/2012 | 08/24/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 08/16/2012 | 11/30/2012 | Y | EXP | 12 |  |  | 0 | 0 | 0 | 4/2/2013 | 4/2/2013 | 4/2/2013 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | LYNN | 499234 | 01904 | 15 | Solar | 05_14_33L2 | 02/07/2023 | 02/21/2023 | 10 | 9 | 1 | 02/22/2023 | 02/22/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 3/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2023 | Connected |  | N | MPL-Northwest | Closed
National Grid | ESSEX | 406249 | 01929 | 8.7 | Solar | 05_14_58L1 | 01/12/2022 | 01/13/2022 | 1 | 0 | 1 | 01/14/2022 | 01/14/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2022 | 01/12/2022 | 5/21/2023 | Y | EXP | 365 | 04/22/2022 | 05/20/2022 | 29 | 0 | 29 |  |  | 8/24/2022 | Connected |  | N | Chelmsford/Westford | Closed - Construction Hold
National Grid | BOXFORD | 701811 | 01921 | 15.2 | Solar | 05_14_73L1 | 07/02/2025 | 07/28/2025 | 16 | 14 | 2 | 07/29/2025 | 07/29/2025 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 10/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N | Beverly | Closed
National Grid | WESTFORD | 391856 | 01886 | 0 | Other | 05_14_8T1 | 01/04/2022 | 01/26/2022 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2022 | 03/02/2022 | 24 | 15 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | WESTFORD | 176204 | 01886 | 13.6 | Solar | 05_01_24W2 | 04/24/2015 | 04/24/2015 | 2 | 2 | 0 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2015 | 04/24/2015 | 12/31/2016 | Y | EXP | 598 | 10/14/2016 | 10/26/2016 | 8 | 0 | 8 | 5/13/2015 | 5/13/2015 | 11/15/2016 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications - Completion Documents Hold
National Grid | ANDOVER | 490569 | 01810 | 5.235 | Solar | 05_01_412L1 | 03/06/2024 |  | 108 | 94 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford | Closed
National Grid | WORCESTER | 176264 | 01605 | 380 | Landfill Gas | 05_01_55W1 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2015 | 10/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/14/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Attleboro | Time Frame Suspension
National Grid | WEBSTER | 591268 | 01570 | 6 | Solar | 05_05_106W82 | 03/06/2024 | 03/08/2024 | 2 | 0 | 2 | 03/11/2024 | 03/11/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 03/06/2024 | 4/1/2025 | Y | EXP | 365 | 05/24/2024 | 05/23/2024 | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | RUTLAND | 176890 | 01543 | 54 | Solar | 05_05_310W6 | 11/13/2015 | 11/13/2015 | 24 | 24 | 0 | 12/21/2015 | 12/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2016 |  | 11/21/2016 | N | EXP | 321 |  |  | 0 | 0 | 0 | 1/3/2017 | 1/3/2017 | 1/3/2017 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | FALL RIVER | 701422 | 02723 | 7.6 | Solar | 05_12_24W2 | 06/26/2025 | 07/11/2025 | 1 | 0 | 1 | 07/15/2025 | 07/15/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 9/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | MARLBOROUGH | 175750 | 01752 | 17.2 | Solar | 05_12_51T2 | 10/31/2014 | 10/31/2014 | 6 | 5 | 1 | 11/12/2014 | 11/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2014 |  | 3/31/2015 | N | EXP | 138 |  |  | 0 | 0 | 0 | 1/12/2015 | 1/12/2015 | 9/17/2015 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | LYNN | 566735 | 01904 | 34.2 | Solar | 05_14_33L2 | 02/28/2024 | 07/12/2024 | 93 | 90 | 3 | 07/15/2024 | 07/15/2024 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 8/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | HAMILTON | 420189 | 01982 | 24.43 | Solar | 05_14_58L1 | 03/31/2022 | 04/06/2022 | 5 | 3 | 2 | 04/07/2022 | 04/07/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2022 |  | 4/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2022 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | BOXFORD | 726366 | 01921 | 6.84 | Solar | 05_14_73L1 | 10/14/2025 | 10/23/2025 | 6 | 5 | 1 | 10/24/2025 | 10/24/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WESTFORD | 412234 | 01886 | 0 | Battery Add-On | 05_14_8T1 | 04/26/2022 | 05/27/2022 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2022 | 06/24/2022 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | CHELMSFORD | 176552 | 01824 | 7.6 | Solar | 05_01_24W2 | 10/05/2015 | 10/05/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2015 | 10/05/2015 | 10/13/2016 | Y | EXP | 346 | 08/03/2016 | 08/31/2016 | 20 | 0 | 20 | 9/21/2016 | 9/21/2016 | 9/21/2016 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | ANDOVER | 519952 | 01810 | 11.4 | Solar | 05_01_412L1 | 04/19/2023 | 04/26/2023 | 6 | 5 | 1 |  |  | 70 | 51 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WORCESTER | 176262 | 01605 | 10 | Solar | 05_01_55W1 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2015 |  | 9/13/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/23/2016 | 3/23/2016 | 3/23/2016 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WEBSTER | 635301 | 01570 | 5.76 | Solar | 05_05_106W82 | 08/26/2024 | 09/10/2024 | 4 | 0 | 4 | 09/11/2024 | 09/11/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 08/26/2024 | 10/21/2025 | Y | EXP | 365 | 12/21/2024 | 01/18/2025 | 29 | 0 | 29 |  |  | 1/28/2025 | Connected |  | N | Ayer-Clinton | Closed
National Grid | RUTLAND | 177181 | 01543 | 650 | Solar | 05_05_310W6 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2016 | 10/18/2016 | 45 | 26 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2017 | 08/12/2016 | 2/23/2018 | Y | STD | 347 | 07/06/2017 | 12/19/2017 | 109 | 0 | 109 | 2/15/2018 | 2/15/2018 | 2/16/2018 | Connected |  | N | Dracut | Closed
National Grid | FALL RIVER | 174925 | 02723 | 1000 | Solar | 05_12_25W1 | 02/25/2013 | 02/25/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2013 | 04/09/2013 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Attleboro | Time Frame Suspension
National Grid | SOUTHBOROUGH | 175937 | 01772 | 750 | Solar | 05_12_51T2 | 01/20/2015 | 01/20/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/28/2015 | 02/25/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford | Closed - Completion Documents Hold
National Grid | SAUGUS | 667060 | 01906 | 23 | Solar | 05_14_33L2 | 01/21/2025 | 01/28/2025 | 5 | 0 | 5 | 01/29/2025 | 01/29/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-Northwest | Closed
National Grid | GLOUCESTER | 421774 | 01930 | 15.2 | Solar | 05_14_58L1 | 05/04/2022 | 05/04/2022 | 0 | 0 | 0 | 05/05/2022 | 05/05/2022 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 05/04/2022 | 10/9/2023 | Y | EXP | 365 | 08/30/2022 | 09/24/2022 | 26 | 0 | 26 |  |  | 11/24/2022 | Connected |  | N | Cape Ann | Closed - Study Hold
National Grid | BOXFORD | 640463 | 01921 | 0 | Solar | 05_14_73L2 | 09/16/2024 | 10/31/2024 | 8 | 6 | 2 | 11/01/2024 | 11/01/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/16/2024 | 11/13/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Terminated |  | N | North Andover | Closed
National Grid | WESTFORD | 174280 | 01886 | 600 | Solar | 05_14_8T2 | 12/30/2011 | 12/30/2011 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 12/30/2011 | 6/1/2012 | Y | EXP | 194 | 11/16/2012 | 02/26/2013 | 62 | 0 | 62 | 12/17/2012 | 12/17/2012 | 12/31/2012 | Connected |  | N | Methuen/Haverhill | Closed
National Grid | CHELMSFORD | 176696 | 01863 | 10 | Solar | 05_01_24W2 | 04/21/2016 | 04/21/2016 | 3 | 3 | 0 | 04/28/2016 | 04/28/2016 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Methuen/Haverhill | Closed
National Grid | LAWRENCE | 535445 | 01843 | 3 | Solar | 05_01_412L1 | 06/21/2023 | 06/26/2023 | 3 | 1 | 2 | 06/27/2023 | 06/27/2023 | 463 | 444 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton | Closed
National Grid | WORCESTER | 176290 | 01605 | 22.8 | Solar | 05_01_55W1 | 07/10/2015 | 07/10/2015 | 1 | 1 | 0 | 07/14/2015 | 07/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 | 07/10/2015 | 7/18/2016 | Y | EXP | 354 |  |  | 0 | 0 | 0 | 7/30/2015 | 7/30/2015 | 1/19/2017 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | WEBSTER | 639123 | 01570 | 0 | Solar | 05_05_106W82 | 09/10/2024 | 10/02/2024 | 10 | 5 | 5 | 10/03/2024 | 10/03/2024 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  | 12/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N | Dracut | Closed
National Grid | RUTLAND | 186377 | 01543 | 740 | Solar | 05_05_310W6 | 06/25/2018 | 06/25/2018 | 38 | 28 | 10 | 08/20/2018 | 08/20/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2018 |  | 12/31/2020 | N | EXP | 499 |  |  | 0 | 0 | 0 |  |  | 12/23/2020 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | FALL RIVER | 175253 | 02723 | 8.82 | Solar | 05_12_25W1 | 11/05/2014 | 11/05/2014 | 5 | 0 | 5 | 11/14/2014 | 11/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 |  | 1/30/2015 | N | EXP | 72 |  |  | 0 | 0 | 0 | 1/21/2015 | 1/21/2015 | 9/4/2015 | Connected |  | N | Brockton-North | 160 Day Study
National Grid | MARLBOROUGH | 176160 | 01752 | 17.4 | Solar | 05_12_51T2 | 02/05/2015 | 02/05/2015 | 4 | 1 | 3 | 02/12/2015 | 02/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2015 |  | 6/30/2015 | N | EXP | 137 |  |  | 0 | 0 | 0 | 3/6/2015 | 3/6/2015 | 9/25/2015 | Connected |  | N | Beverly | Closed
National Grid | SAUGUS | 670708 | 01906 | 10 | Solar | 05_14_33L2 | 02/07/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | Time Frame Suspension
National Grid | BEVERLY | 462180 | 01915 | 13.63 | Solar | 05_14_58L1 | 10/10/2022 | 10/12/2022 | 2 | 0 | 2 | 10/13/2022 | 10/13/2022 | 15 | 0 | 15 | 11/08/2022 | 12/13/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 12/13/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 1/6/2024 | N | EXP | 365 | 02/18/2023 | 05/05/2023 | 77 | 0 | 77 |  |  | 6/26/2023 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | TOPSFIELD | 726184 | 01983 | 11.5 | Solar | 05_14_73L2 | 10/20/2025 | 11/03/2025 | 9 | 6 | 3 | 11/04/2025 | 11/04/2025 | 92 | 75 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2026 |  | 3/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Webster-Southbridge-Charlton | Closed
National Grid | WESTFORD | 177246 | 01886 | 1139 | Solar | 05_14_8T2 | 06/13/2016 | 06/13/2016 | 62 | 62 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2016 | 10/18/2016 | 24 | 21 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2017 | 06/13/2016 | 8/6/2018 | Y | STD | 517 | 02/23/2018 | 08/03/2018 | 126 | 0 | 126 | 6/26/2018 | 7/10/2018 | 8/6/2018 | Connected |  | N | Webster-Southbridge-Charlton | Closed
National Grid | WESTFORD | 176856 | 01886 | 9 | Solar | 05_01_24W2 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2015 |  | 11/18/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 5/6/2016 | 5/6/2016 | 5/17/2016 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | LAWRENCE | 555700 | 01843 | 10 | Solar | 05_01_412L1 | 09/18/2023 | 09/19/2023 | 1 | 0 | 1 | 09/20/2023 | 09/20/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2024 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | WORCESTER | 176356 | 01605 | 5 | Solar | 05_01_55W1 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2015 |  | 10/30/2015 | N | EXP | 163 |  |  | 0 | 0 | 0 | 7/30/2015 | 7/30/2015 | 10/1/2015 | Connected |  | N | Chelmsford/Westford | Closed
National Grid | WEBSTER | 655843 | 01570 | 4.35 | Solar | 05_05_106W82 | 12/20/2024 | 01/09/2025 | 4 | 2 | 2 | 01/10/2025 | 01/10/2025 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications - ISA Amendment In Progress
National Grid | RUTLAND | 254944 | 01543 | 15.2 | Solar | 05_05_310W6 | 09/18/2019 | 09/20/2019 | 1 | 1 | 0 | 09/23/2019 | 09/23/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2019 | 09/18/2019 | 5/11/2020 | Y | EXP | 230 | 11/13/2019 | 01/07/2020 | 55 | 0 | 55 |  |  | 1/14/2020 | Connected |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 176097 | 02723 | 1296 | Solar | 05_12_25W1 | 04/06/2015 | 04/06/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2015 | 05/11/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 | 04/06/2015 | 9/29/2017 | Y | STD | 541 |  |  | 0 | 0 | 0 | 9/7/2017 | 9/7/2017 | 9/8/2017 | Connected |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | SOUTHBOROUGH | 177044 | 01772 | 630 | Solar | 05_12_51T2 | 10/17/2016 | 10/17/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/23/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | SAUGUS | 686801 | 01906 | 11.78 | Solar | 05_14_33L2 | 04/22/2025 | 07/25/2025 | 37 | 24 | 13 | 07/28/2025 | 07/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | HAMILTON | 485002 | 01982 | 15.2 | Solar | 05_14_58L1 | 12/13/2022 | 12/15/2022 | 2 | 0 | 2 | 12/16/2022 | 12/16/2022 | 22 | 0 | 22 | 03/21/2023 | 04/27/2023 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 04/27/2023 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 4/5/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | BOXFORD | 729822 | 01921 | 0 | Solar | 05_14_73L2 | 10/29/2025 | 11/12/2025 | 8 | 6 | 2 | 11/13/2025 | 11/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hanover | Awaiting Full Payments for Common System Modifications
National Grid | WESTFORD | 244642 | 01886 | 200 | Solar | 05_14_8T2 | 07/25/2019 | 08/08/2019 | 7 | 3 | 4 | 08/09/2019 | 08/09/2019 | 15 | 3 | 12 | 10/07/2019 | 11/18/2019 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 11/18/2019 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Adams-Deerfield | Closed
National Grid | CHELMSFORD | 177203 | 01824 | 379.7 | Solar | 05_01_24W2 | 02/01/2017 | 02/01/2017 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South | Awaiting Full Payments for Common System Modifications
National Grid | LAWRENCE | 562803 | 01843 | 23 | Solar | 05_01_412L1 | 10/13/2023 | 10/30/2023 | 12 | 11 | 1 | 10/31/2023 | 10/31/2023 | 47 | 26 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | WORCESTER | 176383 | 01606 | 28 | Solar | 05_01_55W1 | 11/25/2015 | 11/25/2015 | 8 | 8 | 0 | 12/08/2015 | 12/08/2015 | 511 | 72 | 439 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2016 |  | 6/29/2018 | N | EXP | 815 |  |  | 0 | 0 | 0 |  |  | 8/30/2018 | Connected |  | N | North Andover | Closed
National Grid | DOUGLAS | 666670 | 01516 | 10 | Solar | 05_05_106W82 | 01/20/2025 | 01/30/2025 | 3 | 0 | 3 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/20/2025 | 9/7/2026 | Y | EXP | 365 | 06/13/2025 | 08/15/2025 | 64 | 0 | 64 |  |  | 2/6/2026 | Connected |  | Y | North Andover | Closed
National Grid | RUTLAND | 369538 | 01543 | 220 | Solar | 05_05_310W6 | 07/21/2021 | 08/01/2021 | 8 | 0 | 8 |  |  | 31 | 3 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2022 | 07/21/2021 | 7/9/2024 | Y | STD | 440 | 03/23/2024 | 03/27/2024 | 0 | 0 | 0 |  |  | 5/6/2024 | Connected |  | N | North Andover | Closed
National Grid | FALL RIVER | 176438 | 02723 | 10 | Solar | 05_12_25W1 | 03/16/2016 | 03/16/2016 | 2 | 2 | 0 | 03/22/2016 | 03/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 |  | 3/22/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 | 7/29/2016 | 7/29/2016 | 7/29/2016 | Connected |  | N | North Andover | Closed
National Grid | SOUTHBOROUGH | 177335 | 01772 | 186.5 | Solar | 05_12_51T2 | 08/31/2016 | 08/31/2016 | 2 | 2 | 0 | 09/02/2016 | 09/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2016 |  | 9/5/2017 | N | EXP | 361 |  |  | 0 | 0 | 0 | 1/9/2017 | 1/9/2017 | 1/9/2017 | Connected |  | N | North Andover | Closed
National Grid | SAUGUS | 697072 | 01906 | 20.16 | Solar | 05_14_33L2 | 06/11/2025 | 06/13/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2025 | Connected |  | N | Tewksbury | Closed - Awaiting Payment
National Grid | HAMILTON | 491393 | 01982 | 14.592 | Solar | 05_14_58L1 | 01/19/2023 | 01/20/2023 | 1 | 0 | 1 | 01/23/2023 | 01/23/2023 | 274 | 112 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Bridgewater | Time Frame Suspension
National Grid | BOXFORD | 174304 | 01921 | 500 | Solar | 05_14_73L2 | 12/29/2011 | 12/29/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WESTFORD | 356820 | 01886 | 150 | Solar | 05_14_8T2 | 05/10/2021 | 06/07/2021 | 18 | 10 | 8 | 06/08/2021 | 06/08/2021 | 60 | 36 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Fall River-North | Closed - Completion Documents Hold
National Grid | WESTFORD | 177592 | 01886 | 339.7 | Solar | 05_01_24W2 | 05/21/2017 | 05/21/2017 | 37 | 33 | 4 | 07/14/2017 | 07/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2017 |  | 5/27/2018 | N | EXP | 278 |  |  | 0 | 0 | 0 | 2/12/2018 | 2/12/2018 | 2/12/2018 | Connected |  | N | Billerica | Closed - Construction Hold
National Grid | LAWRENCE | 576129 | 01843 | 11.4 | Solar | 05_01_412L1 | 01/22/2024 | 02/21/2024 | 21 | 19 | 2 | 02/22/2024 | 02/22/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 | 01/22/2024 | 6/1/2025 | Y | EXP | 365 | 05/11/2024 | 08/16/2024 | 98 | 0 | 98 |  |  | 10/24/2024 | Connected |  | N | Chelmsford/Westford | Closed
National Grid | WORCESTER | 176511 | 01605 | 10 | Solar | 05_01_55W1 | 03/28/2016 | 03/28/2016 | 3 | 3 | 0 | 04/01/2016 | 04/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 |  | 4/3/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/31/2016 | 8/31/2016 | 8/31/2016 | Connected |  | N | Bridgewater | Time Frame Suspension
National Grid | WEBSTER | 677978 | 01570 | 3.42 | Solar | 05_05_106W82 | 03/14/2025 | 04/08/2025 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | Time Frame Suspension
National Grid | RUTLAND | 426147 | 01543 | 10 | Solar | 05_05_310W6 | 06/01/2022 | 06/30/2022 | 20 | 18 | 2 | 07/01/2022 | 07/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 | 06/01/2022 | 6/13/2024 | Y | EXP | 365 | 10/11/2022 | 06/14/2023 | 247 | 0 | 247 |  |  | 8/7/2023 | Connected |  | Y | Tewksbury | Closed - Completion Documents Hold
National Grid | FALL RIVER | 176708 | 02723 | 10 | Solar | 05_12_25W1 | 10/27/2015 | 10/27/2015 | 1 | 1 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 | 10/27/2015 | 11/3/2016 | Y | EXP | 344 | 09/21/2016 | 10/11/2016 | 13 | 0 | 13 | 11/25/2015 | 11/25/2015 | 10/26/2016 | Connected |  | N | Methuen/Haverhill | Closed - Completion Documents Hold
National Grid | SOUTHBOROUGH | 177600 | 01772 | 28.75 | Solar | 05_12_51T2 | 07/19/2017 | 07/19/2017 | 40 | 31 | 9 | 09/15/2017 | 09/15/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2017 |  | 7/24/2018 | N | EXP | 312 |  |  | 0 | 0 | 0 | 3/16/2018 | 3/16/2018 | 4/25/2018 | Connected |  | N | Chelmsford/Westford | Closed - Awaiting Payment
National Grid | SAUGUS | 177297 | 01906 | 16 | Solar | 05_14_34M1 | 08/26/2016 | 08/26/2016 | 7 | 7 | 0 | 09/08/2016 | 09/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2016 |  | 9/3/2017 | N | EXP | 359 |  |  | 0 | 0 | 0 | 11/21/2016 | 11/21/2016 | 11/23/2016 | Connected |  | N | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | ESSEX | 506132 | 01929 | 15.2 | Solar | 05_14_58L1 | 03/02/2023 | 03/07/2023 | 3 | 0 | 3 | 03/08/2023 | 03/08/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover | 160 Day Study
National Grid | BYFIELD | 175635 | 01922 | 998 | Solar | 05_14_73L2 | 10/17/2014 | 10/17/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2014 | 11/05/2014 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough | Draft ISAs (?3 Applications)
National Grid | WESTFORD | 359565 | 01886 | 466.6 | Solar | 05_14_8T2 | 07/09/2021 | 07/23/2021 | 9 | 3 | 6 | 07/26/2021 | 07/26/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2021 |  | 3/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2022 | Connected |  | N | Chelmsford/Westford | Closed - Completion Documents Hold
National Grid | WESTFORD | 177694 | 01886 | 5 | Solar | 05_01_24W2 | 03/21/2017 | 03/21/2017 | 10 | 10 | 0 | 04/04/2017 | 04/04/2017 | 211 | 0 | 211 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2017 |  | 3/26/2018 | N | EXP | 354 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton | Closed
National Grid | LAWRENCE | 604870 | 01843 | 10 | Solar | 05_01_412L1 | 04/18/2024 | 04/30/2024 | 4 | 0 | 4 | 05/01/2024 | 05/01/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 04/18/2024 | 5/16/2025 | Y | EXP | 365 | 08/15/2024 | 08/14/2024 | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N | Tewksbury | Closed - Awaiting Payment
National Grid | WORCESTER | 176609 | 01605 | 616 | Solar | 05_01_55W1 | 02/12/2016 | 02/12/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/22/2016 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/20/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton | Closed
National Grid | WEBSTER | 707962 | 01570 | 6.46 | Solar | 05_05_106W82 | 07/28/2025 | 08/13/2025 | 5 | 0 | 5 | 09/03/2025 | 09/03/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2025 | Connected |  | N | Leominster | Closed
National Grid | RUTLAND | 618186 | 01543 | 9.765 | Solar | 05_05_310W6 | 07/26/2024 |  | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Bridgewater | Time Frame Suspension
National Grid | FALL RIVER | 176712 | 02723 | 8.75 | Solar | 05_12_25W1 | 01/07/2016 | 01/07/2016 | 3 | 3 | 0 | 01/13/2016 | 01/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2016 |  | 1/13/2017 | N | EXP | 360 |  |  | 0 | 0 | 0 | 2/22/2016 | 2/22/2016 | 2/25/2016 | Connected |  | N | Lowell | 125 Day Study
National Grid | SOUTHBOROUGH | 177599 | 01772 | 28.75 | Solar | 05_12_51T2 | 07/19/2017 | 07/19/2017 | 40 | 31 | 9 | 09/14/2017 | 09/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2017 |  | 7/24/2018 | N | EXP | 313 |  |  | 0 | 0 | 0 | 3/9/2018 | 3/9/2018 | 3/9/2018 | Connected |  | N | Lowell | 125 Day Study
National Grid | SAUGUS | 277157 | 01906 | 0 | Battery Add-On | 05_14_34M1 | 01/30/2020 | 01/31/2020 | 1 | 1 | 0 | 02/03/2020 | 02/03/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 1/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2020 | Connected |  | N | Lowell | 125 Day Study
National Grid | ESSEX | 515435 | 01929 | 12.6 | Solar | 05_14_58L1 | 03/29/2023 | 03/31/2023 | 2 | 0 | 2 | 04/03/2023 | 04/03/2023 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2023 |  | 6/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N | Lowell | 125 Day Study
National Grid | NEWBURY | 176615 | 01985 | 55 | Solar | 05_14_73L2 | 02/15/2016 | 02/15/2016 | 48 | 48 | 0 | 04/26/2016 | 04/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2016 |  | 2/21/2017 | N | EXP | 284 |  |  | 0 | 0 | 0 | 9/14/2016 | 9/14/2016 | 9/26/2016 | Connected |  | N | Scituate | Closed
National Grid | WESTFORD | 430644 | 01886 | 0 | Battery Add-On | 05_14_8T2 | 08/23/2022 | 09/06/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/07/2022 | 09/30/2022 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Scituate | Closed
National Grid | CHELMSFORD | 203085 | 01863 | 150 | Solar | 05_01_24W2 | 12/06/2018 | 01/02/2019 | 14 | 12 | 2 | 01/03/2019 | 01/03/2019 | 3 | 0 | 3 | 01/18/2019 | 04/30/2019 | 70 | 4 | 66 |  |  | 0 | 0 | 0 | 04/30/2019 | 70 | 4 | 66 |  |  | 0 | 0 | 0 | 5/17/2019 | 12/06/2018 | 9/25/2020 | Y | EXP | 349 | 02/14/2020 | 03/12/2020 | 27 | 0 | 27 |  |  | 9/25/2020 | Connected |  | N | Ayer-Clinton | Draft Group Study Agreement
National Grid | LAWRENCE | 608295 | 01843 | 23 | Solar | 05_01_412L1 | 05/02/2024 | 05/16/2024 | 10 | 8 | 2 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 |  | 6/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | WORCESTER | 176629 | 01606 | 6 | Solar | 05_01_55W1 | 10/15/2015 | 10/15/2015 | 3 | 3 | 0 | 10/21/2015 | 10/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2015 |  | 10/21/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 4/29/2016 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | DOUGLAS | 177384 | 01516 | 12 | Solar | 05_05_108W51 | 11/28/2016 | 11/28/2016 | 2 | 2 | 0 | 12/01/2016 | 12/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2016 |  | 12/4/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 6/14/2017 | 6/14/2017 | 6/19/2017 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | RUTLAND | 631656 | 01543 | 10 | Solar | 05_05_310W6 | 08/09/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-South | Closed
National Grid | BELLINGHAM | 176752 | 02019 | 34.2 | Solar | 05_12_25W1 | 01/12/2016 | 01/12/2016 | 8 | 8 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 | 01/12/2016 | 1/18/2017 | Y | EXP | 344 | 05/27/2016 | 06/03/2016 | 4 | 0 | 4 | 8/19/2016 | 8/19/2016 | 8/19/2016 | Connected |  | N | Brockton-South | Closed
National Grid | SOUTHBOROUGH | 178038 | 01745 | 17.6 | Solar | 05_12_51T2 | 10/27/2017 | 10/27/2017 | 66 | 66 | 0 | 02/13/2018 | 02/13/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 3/30/2019 | N | EXP | 410 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 418217 | 01906 | 9.772 | Solar | 05_14_34M1 | 05/11/2022 | 05/12/2022 | 1 | 0 | 1 | 05/13/2022 | 05/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2022 | 05/11/2022 | 8/23/2023 | Y | EXP | 365 | 10/06/2022 | 11/03/2022 | 29 | 0 | 29 |  |  | 11/10/2022 | Connected |  | N | Bridgewater | On Hold Behind Preceding Group Study
National Grid | ESSEX | 541791 | 01929 | 15.2 | Solar | 05_14_58L1 | 07/18/2023 | 07/24/2023 | 4 | 2 | 2 | 07/25/2023 | 07/25/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2023 | 07/18/2023 | 1/24/2025 | Y | EXP | 365 | 03/29/2024 | 06/05/2024 | 69 | 0 | 69 |  |  | 6/15/2024 | Connected |  | N | Bridgewater | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 194444 | 01985 | 7.6 | Solar | 05_14_73L2 | 08/26/2018 | 10/31/2018 | 3 | 3 | 0 | 11/01/2018 | 11/01/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 646241 | 01886 | 480 | Solar | 05_14_92L1 | 03/13/2025 | 05/27/2025 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2025 | 07/30/2025 | 44 | 25 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N | Brockton-North | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 204161 | 01863 | 426.4 | Solar | 05_01_24W2 | 12/18/2018 | 01/22/2019 | 22 | 17 | 5 | 01/23/2019 | 01/23/2019 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford | Draft Group Study Agreement
National Grid | BILLERICA | 611622 | 01821 | 10 | Solar | 05_01_412L1 | 05/16/2024 |  | 76 | 75 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 176698 | 01606 | 380 | Bio Gas | 05_01_55W1 | 04/25/2016 | 05/16/2016 | 15 | 15 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2016 | 07/06/2016 | 34 | 13 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2016 | 04/25/2016 | 7/5/2022 | Y | STD | 70 | 03/09/2019 | 09/26/2019 | 202 | 107 | 95 |  |  | 3/16/2022 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | WEBSTER | 177504 | 01570 | 10 | Solar | 05_05_108W51 | 03/06/2017 | 03/06/2017 | 9 | 7 | 2 | 03/17/2017 | 03/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 |  | 3/11/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/30/2017 | 8/30/2017 | 9/6/2017 | Connected |  | N | Millbury-Grafton | Closed
National Grid | RUTLAND | 638307 | 01543 | 11.517 | Solar | 05_05_310W6 | 09/12/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 |  | 11/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2024 | Connected |  | N | Millbury-Grafton | Closed - Study Hold
National Grid | BELLINGHAM | 176963 | 02019 | 15.2 | Solar | 05_12_25W1 | 07/18/2016 | 07/18/2016 | 0 | 0 | 0 | 07/19/2016 | 07/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 07/18/2016 | 10/12/2018 | Y | EXP | 808 | 01/18/2018 | 03/05/2018 | 30 | 0 | 30 |  |  | 9/26/2018 | Connected |  | N | Millbury-Grafton | Closed
National Grid | SOUTHBOROUGH | 205162 | 01772 | 0 | Solar | 05_12_51T2 | 01/07/2019 | 01/17/2019 | 7 | 0 | 7 | 01/18/2019 | 01/18/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  | 7/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N | Millbury-Grafton | Closed - ASO Hold
National Grid | SAUGUS | 605342 | 01906 | 10 | Solar | 05_14_34M1 | 06/05/2024 | 06/11/2024 | 1 | 0 | 1 | 06/12/2024 | 06/12/2024 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2024 | 06/05/2024 | 7/19/2025 | Y | EXP | 365 | 10/12/2024 | 10/28/2024 | 17 | 0 | 17 |  |  | 11/14/2024 | Connected |  | N | Leominster | Group Window
National Grid | HAMILTON | 547989 | 01982 | 15.2 | Solar | 05_14_58L1 | 08/14/2023 | 08/15/2023 | 2 | 1 | 1 | 08/16/2023 | 08/16/2023 | 35 | 17 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  | 11/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2024 | Connected |  | N | Leominster | Group Window
National Grid | NEWBURY | 273784 | 01985 | 8.88 | Solar | 05_14_73L2 | 02/03/2020 | 02/05/2020 | 1 | 1 | 0 | 02/06/2020 | 02/06/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 2/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2020 | Connected |  | N | Hanover | 160 Day Study
National Grid | WESTFORD | 175648 | 01886 | 4.73 | Solar | 05_14_92L1 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2015 |  | 2/16/2015 | N | EXP | 41 |  |  | 0 | 0 | 0 | 2/19/2015 | 2/19/2015 | 12/10/2015 | Connected |  | N | Hanover | 160 Day Study
National Grid | CHELMSFORD | 206472 | 01863 | 250 | Solar | 05_01_24W2 | 03/12/2019 | 03/18/2019 | 4 | 2 | 2 | 03/19/2019 | 03/19/2019 | 17 | 11 | 6 | 05/31/2019 | 10/25/2019 | 102 | 26 | 76 |  |  | 0 | 0 | 0 | 10/25/2019 | 102 | 26 | 76 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 619932 | 01821 | 10 | Solar | 05_01_412L1 | 06/24/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 88 | 74 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Marlborough | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 176872 | 01605 | 10 | Solar | 05_01_55W1 | 03/01/2016 | 03/01/2016 | 2 | 2 | 0 | 03/04/2016 | 03/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 |  | 3/7/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 8/2/2016 | 8/2/2016 | 8/8/2016 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | WEBSTER | 177664 | 01570 | 15.2 | Solar | 05_05_108W51 | 05/24/2017 | 05/24/2017 | 2 | 2 | 0 | 05/30/2017 | 05/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 | 05/24/2017 | 5/30/2018 | Y | EXP | 363 | 10/24/2017 | 11/15/2017 | 10 | 0 | 10 | 12/15/2017 | 12/15/2017 | 12/27/2017 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | RUTLAND | 660473 | 01543 | 5.76 | Solar | 05_05_310W6 | 12/13/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | BELLINGHAM | 185047 | 02019 | 13.6 | Solar | 05_12_25W1 | 07/09/2018 | 07/18/2018 | 7 | 3 | 4 | 07/19/2018 | 07/19/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  | 7/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2018 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | SOUTHBOROUGH | 238751 | 01772 | 10 | Solar | 05_12_51T2 | 06/19/2019 | 06/20/2019 | 0 | 0 | 0 | 06/21/2019 | 06/21/2019 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  | 9/6/2019 | N | EXP | 67 |  |  | 0 | 0 | 0 |  |  | 8/28/2019 | Connected |  | N | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 641381 | 01906 | 10 | Solar | 05_14_34M1 | 09/18/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 09/18/2024 | 12/10/2025 | Y | EXP | 365 | 02/12/2025 | 02/26/2025 | 15 | 0 | 15 |  |  | 3/7/2025 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | ESSEX | 549217 | 01929 | 7.6 | Solar | 05_14_58L1 | 08/17/2023 | 08/21/2023 | 2 | 1 | 1 | 08/22/2023 | 08/22/2023 | 76 | 60 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  | 1/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2024 | Connected |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | BYFIELD | 297463 | 01922 | 10 | Solar | 05_14_73L2 | 06/20/2020 | 06/23/2020 | 1 | 0 | 1 | 06/24/2020 | 06/24/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2020 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | WESTFORD | 177104 | 01886 | 288 | Solar | 05_14_92L1 | 05/27/2016 | 05/27/2016 | 3 | 3 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2016 | 05/27/2016 | 7/5/2017 | Y | EXP | 307 |  |  | 0 | 0 | 0 | 5/30/2017 | 5/30/2017 | 5/30/2017 | Connected |  | N | Hopedale-East | 160 Day Study
National Grid | CHELMSFORD | 207134 | 01863 | 240 | Solar | 05_01_24W2 | 01/30/2019 | 02/11/2019 | 8 | 2 | 6 | 02/12/2019 | 02/12/2019 | 39 | 20 | 19 | 08/07/2019 | 09/04/2019 | 19 | 1 | 18 |  |  | 0 | 0 | 0 | 09/04/2019 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Cape Ann | Pending
National Grid | BILLERICA | 631896 | 01821 | 9.86 | Solar | 05_01_412L1 | 08/12/2024 | 09/27/2024 | 4 | 0 | 4 | 09/30/2024 | 09/30/2024 | 25 | 7 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 08/12/2024 | 11/26/2025 | Y | EXP | 365 | 02/11/2025 | 03/17/2025 | 35 | 0 | 35 |  |  | 3/21/2025 | Connected |  | N | Bridgewater | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 177129 | 01606 |  |  | 05_01_55W1 | 01/23/2017 | 01/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/28/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford | Draft Group Study Agreement
National Grid | WEBSTER | 402732 | 01570 | 3.48 | Solar | 05_05_108W51 | 01/28/2022 | 02/07/2022 | 6 | 3 | 3 | 02/08/2022 | 02/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 |  | 9/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2022 | Connected |  | N | Leominster | Group Window
National Grid | RUTLAND | 670809 | 01543 | 7.6 | Solar | 05_05_310W6 | 02/07/2025 | 02/27/2025 | 4 | 0 | 4 | 02/28/2025 | 02/28/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Lowell | On Hold Behind Preceding Group Study
National Grid | BELLINGHAM | 219604 | 02019 | 7.6 | Solar | 05_12_25W1 | 04/12/2019 | 10/02/2019 | 119 | 114 | 5 | 10/03/2019 | 10/03/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 9/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2020 | Connected |  | N | Lowell | On Hold Behind Preceding Group Study
National Grid | SOUTHBOROUGH | 242810 | 01772 | 7.6 | Solar | 05_12_51T2 | 07/16/2019 | 07/17/2019 | 0 | 0 | 0 | 07/18/2019 | 07/18/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2019 |  | 7/27/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N | Hanover | 160 Day Study
National Grid | SAUGUS | 454032 | 01906 | 21.75 | Solar | 05_14_36J2 | 09/01/2022 | 09/08/2022 | 4 | 4 | 0 | 09/09/2022 | 09/09/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North | On Hold Behind Preceding Group Study
National Grid | ESSEX | 555011 | 01929 | 9.57 | Solar | 05_14_58L1 | 09/25/2023 | 09/28/2023 | 4 | 1 | 3 | 09/29/2023 | 09/29/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 317580 | 01950 | 9.28 | Solar | 05_14_73L2 | 10/09/2020 | 10/12/2020 | 0 | 0 | 0 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 4/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2021 | Connected |  | N | Hopedale-East | 160 Day Study
National Grid | WESTFORD | 177103 | 01886 | 288 | Solar | 05_14_92L1 | 05/27/2016 | 05/27/2016 | 3 | 3 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 | 05/27/2016 | 7/5/2017 | Y | EXP | 320 |  |  | 0 | 0 | 0 | 5/30/2017 | 5/30/2017 | 5/30/2017 | Connected |  | N | Chelmsford/Westford | Draft Group Study Agreement
National Grid | WESTFORD | 209361 | 01886 | 72 | Solar | 05_01_24W2 | 02/12/2019 | 04/10/2019 | 4 | 0 | 4 | 04/11/2019 | 04/11/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Scoping Meeting
National Grid | BILLERICA | 632100 | 01821 | 10 | Solar | 05_01_412L1 | 08/20/2024 | 08/23/2024 | 3 | 0 | 3 | 08/26/2024 | 08/26/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/20/2024 | 9/11/2025 | Y | EXP | 365 | 10/11/2024 | 10/14/2024 | 4 | 0 | 4 |  |  | 12/4/2024 | Connected |  | N | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 177130 | 01606 | 7.25 | Solar | 05_01_55W1 | 01/23/2017 | 01/23/2017 | 10 | 9 | 1 | 02/06/2017 | 02/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2017 |  | 1/28/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 5/31/2017 | 5/31/2017 | 5/31/2017 | Connected |  | N | Chelmsford/Westford | Draft Group Study Agreement
National Grid | WEBSTER | 551974 | 01570 | 10 | Solar | 05_05_108W51 | 09/11/2023 | 09/18/2023 | 5 | 0 | 5 | 09/19/2023 | 09/19/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 | 09/11/2023 | 12/31/2024 | Y | EXP | 365 | 04/25/2025 | 05/08/2025 | 14 | 0 | 14 |  |  | 6/12/2025 | Connected |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 671407 | 01543 | 7.6 | Solar | 05_05_310W6 | 02/12/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | BELLINGHAM | 234682 | 02019 | 3.8 | Solar | 05_12_25W1 | 07/24/2019 | 08/30/2019 | 27 | 26 | 1 | 09/03/2019 | 09/03/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2019 |  | 12/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2020 | Connected |  | N | Hanover | 160 Day Study
National Grid | MARLBOROUGH | 260576 | 01752 | 13.6 | Solar | 05_12_51T2 | 10/17/2019 | 10/24/2019 | 5 | 3 | 2 | 10/25/2019 | 10/25/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 |  | 2/28/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2020 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | SAUGUS | 451338 | 01906 | 67.3 | Solar | 05_14_36J6 | 08/12/2022 | 09/19/2022 | 26 | 16 | 10 | 09/20/2022 | 09/20/2022 | 27 | 6 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2022 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2023 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | HAMILTON | 637421 | 01936 | 5.525 | Solar | 05_14_58L1 | 09/04/2024 | 09/24/2024 | 8 | 4 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N | Attleboro | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 452930 | 01950 | 7.6 | Solar | 05_14_73L2 | 08/19/2022 | 08/22/2022 | 1 | 0 | 1 | 08/23/2022 | 08/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2022 | 08/19/2022 | 9/30/2023 | Y | EXP | 365 | 12/06/2022 | 12/05/2022 | 0 | 0 | 0 |  |  | 3/17/2023 | Connected |  | N | Attleboro | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 216947 | 01886 | 10 | Solar | 05_14_92L1 | 09/21/2019 | 09/25/2019 | 2 | 2 | 0 | 09/26/2019 | 09/26/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2019 | 09/21/2019 | 5/28/2020 | Y | EXP | 365 | 12/27/2019 | 12/26/2019 | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N | Attleboro | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 274013 | 01886 | 250 | Solar | 05_01_24W2 | 02/11/2020 | 02/14/2020 | 3 | 1 | 2 |  |  | 60 | 43 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 | 02/11/2020 | 6/23/2023 | Y | STD | 858 | 04/02/2022 | 06/06/2023 | 430 | 0 | 430 | 5/25/2023 | 6/7/2023 | 6/16/2023 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | BILLERICA | 646578 | 01821 | 3.8 | Solar | 05_01_412L1 | 10/22/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/22/2024 | 12/20/2025 | Y | EXP | 365 | 01/23/2025 | 03/21/2025 | 58 | 0 | 58 |  |  | 4/1/2025 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | WORCESTER | 177173 | 01605 | 5.59 | Solar | 05_01_55W1 | 05/31/2016 | 05/31/2016 | 17 | 17 | 0 | 06/27/2016 | 06/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2016 |  | 6/6/2017 | N | EXP | 341 |  |  | 0 | 0 | 0 | 12/20/2016 | 12/20/2016 | 12/20/2016 | Connected |  | N | Leominster | Group Window
National Grid | WEBSTER | 564861 | 01570 | 10 | Solar | 05_05_108W51 | 11/10/2023 | 11/14/2023 | 2 | 0 | 2 | 11/15/2023 | 11/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 | 11/10/2023 | 1/22/2025 | Y | EXP | 365 | 03/07/2024 | 04/20/2024 | 45 | 0 | 45 |  |  | 5/16/2024 | Connected |  | N | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 706145 | 01543 | 15.356 | Solar | 05_05_310W6 | 07/24/2025 | 07/31/2025 | 5 | 1 | 4 | 08/01/2025 | 08/01/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 | 07/24/2025 | 9/9/2026 | Y | EXP | 365 | 10/04/2025 | 11/21/2025 | 49 | 0 | 49 |  |  | 11/24/2025 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | BELLINGHAM | 276489 | 02019 | 400 | Solar | 05_12_25W1 | 04/09/2020 | 04/22/2020 | 7 | 2 | 5 |  |  | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2020 | 04/09/2020 | 5/13/2022 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover | 160 Day Study
National Grid | SOUTHBOROUGH | 283128 | 01772 | 8.7 | Solar | 05_12_51T2 | 03/10/2020 | 03/11/2020 | 0 | 0 | 0 | 03/12/2020 | 03/12/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 |  | 3/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2020 | Connected |  | N | Brockton-North | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 728333 | 01906 | 23 | Solar | 05_14_36L1 | 10/22/2025 | 10/27/2025 | 3 | 0 | 3 | 10/28/2025 | 10/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | WENHAM | 427890 | 01984 | 875 | Solar | 05_14_58L2 | 08/25/2022 | 12/13/2022 | 74 | 64 | 10 |  |  | 51 | 26 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Bridgewater | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 378620 | 01950 | 7.6 | Solar | 05_14_73L2 | 09/01/2021 | 09/02/2021 | 1 | 0 | 1 | 09/03/2021 | 09/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  | 5/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/25/2022 | Connected |  | N | Attleboro | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 339861 | 01824 | 15.2 | Solar | 05_14_92L1 | 02/01/2021 | 02/04/2021 | 3 | 2 | 1 | 02/05/2021 | 02/05/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  | 4/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2021 | Connected |  | N | Millbury-Grafton | Closed
National Grid | WESTFORD | 307776 | 01886 | 9.12 | Solar | 05_01_24W2 | 08/31/2020 | 09/16/2020 | 11 | 11 | 0 | 09/17/2020 | 09/17/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | BILLERICA | 646439 | 01821 | 10 | Solar | 05_01_412L1 | 10/25/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/25/2024 | 12/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East | Scoping Meeting
National Grid | WORCESTER | 177420 | 01606 | 5 | Solar | 05_01_55W1 | 12/05/2016 | 12/05/2016 | 2 | 2 | 0 | 12/08/2016 | 12/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2016 |  | 12/11/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/7/2017 | 3/7/2017 | 3/7/2017 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | WEBSTER | 658856 | 01570 | 3.8 | Solar | 05_05_108W51 | 12/05/2024 | 12/11/2024 | 4 | 1 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 3/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N | Hopedale-East | 160 Day Study
National Grid | RUTLAND | 659021 | 01543 | 0 | Other | 05_05_311W1 | 03/31/2025 | 06/18/2025 | 54 | 44 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2025 | 07/17/2025 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Hopedale-East | 160 Day Study
National Grid | BELLINGHAM | 374165 | 02019 | 9.98 | Solar | 05_12_25W1 | 11/05/2021 |  | 57 | 26 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East | 160 Day Study
National Grid | MARLBOROUGH | 293961 | 01752 | 15.08 | Solar | 05_12_51T2 | 05/29/2020 | 06/04/2020 | 3 | 0 | 3 | 06/05/2020 | 06/05/2020 | 92 | 82 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2021 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | SAUGUS | 744809 | 01906 | 5.76 | Solar | 05_14_36L1 | 02/04/2026 | 02/05/2026 | 1 | 0 | 1 | 02/06/2026 | 02/06/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Barre-Athol | Scoping Meeting
National Grid | WENHAM | 744151 | 01984 | 11.52 | Solar | 05_14_58L2 | 01/09/2026 | 01/14/2026 | 3 | 0 | 3 | 01/15/2026 | 01/15/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 385131 | 01950 | 7.6 | Solar | 05_14_73L2 | 09/28/2021 | 10/01/2021 | 4 | 3 | 1 | 10/04/2021 | 10/04/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2021 |  | 9/30/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Marlborough | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 599440 | 01824 | 15.744 | Solar | 05_14_92L1 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 5/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2024 | Connected |  | Y | MPL-East | Scoping Meeting
National Grid | WESTFORD | 322315 | 01886 | 10 | Solar | 05_01_24W2 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2021 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | BILLERICA | 647877 | 01821 | 7.6 | Solar | 05_01_412L1 | 10/28/2024 | 11/05/2024 | 4 | 0 | 4 | 11/06/2024 | 11/06/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/28/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N | Millbury-Grafton | Group Window
National Grid | WORCESTER | 178189 | 01605 | 296 | Solar | 05_01_55W1 | 12/28/2017 | 12/28/2017 | 10 | 0 | 10 | 02/13/2018 | 02/13/2018 | 36 | 0 | 36 | 10/25/2018 | 11/05/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/05/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/7/2018 |  | 2/3/2020 | N | EXP | 208 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | WEBSTER | 670566 | 01570 | 7.6 | Solar | 05_05_108W51 | 02/06/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 730626 | 01543 | 10 | Solar | 05_05_311W1 | 11/11/2025 | 11/21/2025 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 56 | 24 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | BELLINGHAM | 410526 | 02019 | 0 | Solar | 05_12_25W1 | 02/04/2022 | 02/08/2022 | 2 | 1 | 1 | 02/09/2022 | 02/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2022 | Connected |  | N | Brockton-North | On Hold Behind Preceding Group Study
National Grid | MARLBOROUGH | 293270 | 01752 | 0 | Battery Add-On | 05_12_51T2 | 05/27/2020 | 06/08/2020 | 7 | 7 | 0 | 06/09/2020 | 06/09/2020 | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 05/27/2020 | 4/9/2022 | Y | EXP | 365 | 03/10/2021 | 04/05/2021 | 26 | 0 | 26 |  |  |  | Withdrawn |  | N | MPL-East | Scoping Meeting
National Grid | MELROSE | 749885 | 02176 | 150 | Solar | 05_14_36L1 | 02/13/2026 | 03/24/2026 | 26 | 16 | 10 | 03/25/2026 | 03/25/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | MPL-East | Scoping Meeting
National Grid | ESSEX | 753835 | 01929 | 5.76 | Solar | 05_14_58L2 | 03/02/2026 | 03/04/2026 | 3 | 0 | 3 | 03/23/2026 | 03/23/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Hanover | 160 Day Study
National Grid | NEWBURY | 392677 | 01950 | 7.6 | Solar | 05_14_73L2 | 04/25/2022 | 06/15/2022 | 36 | 35 | 1 | 06/16/2022 | 06/16/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2022 | 04/25/2022 | 8/20/2023 | Y | EXP | 365 | 12/22/2022 | 02/17/2023 | 58 | 0 | 58 |  |  | 5/11/2023 | Connected |  | N | Hanover | 160 Day Study
National Grid | CHELMSFORD | 637006 | 01824 | 3.8 | Solar | 05_14_92L1 | 08/30/2024 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover | 160 Day Study
National Grid | WESTFORD | 351365 | 01886 | 7.6 | Solar | 05_01_24W2 | 05/06/2021 | 05/12/2021 | 3 | 0 | 3 | 05/13/2021 | 05/13/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  | 10/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2021 | Connected |  | N | Hanover | 160 Day Study
National Grid | BILLERICA | 652003 | 01821 | 7.6 | Solar | 05_01_412L1 | 11/13/2024 | 12/17/2024 | 7 | 0 | 7 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/13/2024 | 2/28/2026 | Y | EXP | 365 | 06/12/2025 | 11/21/2025 | 163 | 0 | 163 |  |  | 12/1/2025 | Connected |  | N | Hanover | 160 Day Study
National Grid | WORCESTER | 178188 | 01605 | 294 | Solar | 05_01_55W1 | 12/28/2017 | 12/28/2017 | 0 | 0 | 0 | 02/13/2018 | 02/13/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2018 |  | 2/3/2020 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N | Chelmsford/Westford | Draft Group Study Agreement
National Grid | WEBSTER | 745830 | 01570 |  | Battery Add-On | 05_05_108W60 | 01/16/2026 | 01/20/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | MPL-East | Scoping Meeting
National Grid | RUTLAND | 175172 | 01543 | 85 | Solar | 05_05_311W1 | 11/16/2012 | 11/16/2012 | 10 | 0 | 10 | 12/05/2012 | 12/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2013 | 11/16/2012 | 4/1/2013 | Y | EXP | 39 |  |  | 0 | 0 | 0 | 2/21/2013 | 2/21/2013 | 7/12/2013 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | BELLINGHAM | 537105 | 02019 | 10 | Solar | 05_12_25W1 | 08/01/2023 | 08/07/2023 | 4 | 0 | 4 | 08/08/2023 | 08/08/2023 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 | 08/01/2023 | 11/18/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2024 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | MARLBOROUGH | 301864 | 01752 | 7.6 | Solar | 05_12_51T2 | 08/14/2020 | 08/18/2020 | 1 | 0 | 1 | 08/19/2020 | 08/19/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2020 | 08/14/2020 | 2/5/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2021 | Connected |  | N | Barre-Athol | Scoping Meeting
National Grid | SAUGUS | 175095 | 01906 | 12 | Solar | 05_14_36L1 | 10/23/2012 | 10/23/2012 | 2 | 0 | 2 | 11/19/2012 | 11/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2013 |  | 1/31/2013 | N | EXP | 6 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 3/14/2013 | Connected |  | N | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 759450 | 01982 | 15.2 | Solar | 05_14_58L2 | 03/27/2026 | 04/01/2026 | 3 | 1 | 2 | 04/02/2026 | 04/02/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 402422 | 01950 | 7.6 | Solar | 05_14_73L2 | 03/17/2022 | 03/18/2022 | 1 | 0 | 1 | 03/21/2022 | 03/21/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2022 |  | 5/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2022 | Connected |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 637131 | 01824 | 5.76 | Solar | 05_14_92L1 | 09/02/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  | 1/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 376655 | 01886 | 9.8 | Solar | 05_01_24W2 | 08/31/2021 |  | 50 | 45 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 655660 | 01821 | 7.6 | Solar | 05_01_412L1 | 11/20/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/20/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | WORCESTER | 178233 | 01605 | 133.2 | Solar | 05_01_55W1 | 01/07/2018 | 01/07/2018 | 0 | 0 | 0 | 01/25/2018 | 01/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2018 |  | 4/16/2021 | N | EXP | 490 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | WEBSTER | 751142 | 01570 | 15.76 | Solar | 05_05_108W60 | 02/20/2026 | 02/24/2026 | 2 | 0 | 2 | 02/25/2026 | 02/25/2026 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Bridgewater | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 177943 | 01543 | 333.2 | Solar | 05_05_311W1 | 08/18/2017 | 08/18/2017 | 127 | 91 | 36 | 02/21/2018 | 02/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2018 | 08/18/2017 | 2/10/2021 | Y | EXP | 680 |  |  | 0 | 0 | 0 |  |  | 2/10/2021 | Connected |  | N | Bridgewater | On Hold Behind Preceding Group Study
National Grid | BELLINGHAM | 578612 | 02019 | 8.7 | Solar | 05_12_25W1 | 01/08/2024 | 01/11/2024 | 3 | 0 | 3 | 01/12/2024 | 01/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland | Scoping Meeting
National Grid | MARLBOROUGH | 330460 | 01752 | 9.8 | Solar | 05_12_51T2 | 01/21/2021 | 12/07/2021 | 1 | 0 | 1 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2021 | 01/21/2021 | 4/9/2023 | Y | EXP | 365 | 07/31/2021 | 08/26/2021 | 26 | 1 | 25 |  |  | 7/20/2022 | Connected |  | N | Gardner-Winchendon | Scoping Meeting
National Grid | SAUGUS | 218135 | 01906 | 18.85 | Solar | 05_14_36L1 | 04/09/2019 | 04/12/2019 | 3 | 3 | 0 | 04/15/2019 | 04/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2019 |  | 8/20/2019 | N | EXP | 125 |  |  | 0 | 0 | 0 |  |  | 8/15/2019 | Connected |  | N | Leominster | Group Window
National Grid | HAMILTON | 174602 | 01982 | 95 | Solar | 05_14_58L2 | 09/20/2011 | 09/20/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2011 |  | 1/20/2012 | N | EXP | 58 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 1/20/2012 | Connected |  | N | Hopedale-East | 160 Day Study
National Grid | NEWBURY | 415211 | 01950 | 7.6 | Solar | 05_14_73L2 | 09/29/2022 | 03/07/2022 | 1 | 0 | 1 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2022 |  | 12/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | N | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 648337 | 01886 | 10 | Solar | 05_14_92L1 | 10/30/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 93 | 71 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 410649 | 01863 | 6 | Solar | 05_01_24W2 | 02/07/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 54 | 39 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Bridgewater | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 663882 | 01821 | 5.76 | Solar | 05_01_412L1 | 01/06/2025 | 01/16/2025 | 4 | 0 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 178262 | 01605 | 7.6 | Solar | 05_01_55W1 | 04/17/2018 | 04/17/2018 | 19 | 0 | 19 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2018 |  | 4/23/2019 | N | EXP | 340 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland | Scoping Meeting
National Grid | WEBSTER | 171881 | 01570 | 10 | Solar | 05_05_108W60 | 07/01/2018 | 07/01/2018 | 5 | 5 | 0 | 07/11/2018 | 07/11/2018 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East | Scoping Meeting
National Grid | RUTLAND | 196371 | 01543 | 100 | Solar | 05_05_311W1 | 09/19/2018 | 10/05/2018 | 7 | 0 | 7 | 10/08/2018 | 10/08/2018 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 |  | 6/1/2020 | N | EXP | 530 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | BELLINGHAM | 647190 | 02019 | 6 | Solar | 05_12_25W1 | 10/15/2024 | 10/18/2024 | 1 | 0 | 1 | 10/21/2024 | 10/21/2024 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2024 | Connected |  | N | Millbury-Grafton | Group Window
National Grid | MARLBOROUGH | 330933 | 01752 | 5 | Solar | 05_12_51T2 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 | 12/10/2020 | 12/13/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2021 | Connected |  | N | Attleboro | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 258094 | 01906 | 3.8 | Solar | 05_14_36L1 | 10/10/2019 | 10/21/2019 | 5 | 0 | 5 | 10/22/2019 | 10/22/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 |  | 10/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Marlborough | On Hold Behind Preceding Group Study
National Grid | ESSEX | 175285 | 01929 | 30 | Solar | 05_14_58L2 | 11/05/2014 | 11/05/2014 | 5 | 1 | 4 | 11/14/2014 | 11/14/2014 | 147 | 4 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2014 | 11/05/2014 | 1/30/2015 | Y | EXP | 50 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 3/6/2015 | Connected |  | N | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 424042 | 01950 | 10 | Solar | 05_14_73L2 | 05/05/2022 | 05/25/2022 | 14 | 14 | 0 | 05/26/2022 | 05/26/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 |  | 7/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2022 | Connected |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 656745 | 01824 | 8.99 | Solar | 05_14_92L1 | 11/25/2024 | 03/04/2025 | 11 | 7 | 4 | 03/05/2025 | 03/05/2025 | 39 | 14 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 418368 | 01886 | 9.8 | Solar | 05_01_24W2 | 04/14/2022 | 04/15/2022 | 1 | 0 | 1 | 04/19/2022 | 04/19/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2022 | 04/14/2022 | 9/5/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 674780 | 01821 | 7.6 | Solar | 05_01_412L1 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 178361 | 01605 | 3000 | Solar | 05_01_55W1 | 03/30/2018 | 03/30/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2018 | 05/21/2018 | 33 | 18 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/7/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | WEBSTER | 175746 | 01570 | 20 | Solar | 05_05_108W60 | 10/29/2014 | 10/29/2014 | 5 | 3 | 2 | 11/10/2014 | 11/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2014 |  | 1/15/2015 | N | EXP | 64 |  |  | 0 | 0 | 0 | 1/30/2015 | 1/30/2015 | 3/3/2015 | Connected |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 233077 | 01543 | 25 | Solar | 05_05_311W1 | 06/19/2019 | 06/20/2019 | 1 | 1 | 0 | 06/21/2019 | 06/21/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2019 |  | 12/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | BLACKSTONE | 656366 | 01504 | 10 | Solar | 05_12_25W1 | 11/22/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland | On Hold Behind Preceding Group Study
National Grid | MARLBOROUGH | 333234 | 01752 | 7.6 | Solar | 05_12_51T2 | 01/27/2021 | 12/08/2021 | 3 | 0 | 3 | 02/03/2021 | 02/03/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  | 4/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Attleboro | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 432857 | 01906 | 0 | Solar | 05_14_36L1 | 06/21/2022 | 06/22/2022 | 1 | 0 | 1 | 06/23/2022 | 06/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 7/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2023 | Connected |  | N | Leominster | Group Window
National Grid | HAMILTON | 175898 | 01982 | 476 | Solar | 05_14_58L2 | 07/31/2015 | 07/31/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2015 | 09/03/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/10/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Attleboro | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 423112 | 01950 | 7.6 | Solar | 05_14_73L2 | 04/11/2022 | 04/12/2022 | 1 | 0 | 1 | 04/13/2022 | 04/13/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover | 160 Day Study
National Grid | CHELMSFORD | 668349 | 01824 | 11.5 | Solar | 05_14_92L1 | 01/28/2025 | 01/31/2025 | 3 | 0 | 3 | 02/03/2025 | 02/03/2025 | 51 | 33 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N | Hopedale-East | 160 Day Study
National Grid | WESTFORD | 423774 | 01886 | 67.3 | Solar | 05_01_24W2 | 04/20/2022 | 05/04/2022 | 10 | 1 | 9 | 05/05/2022 | 05/05/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2022 | 04/20/2022 | 11/8/2023 | Y | EXP | 278 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 674712 | 01821 | 3.8 | Solar | 05_01_412L1 | 03/05/2025 | 03/14/2025 | 4 | 0 | 4 | 03/24/2025 | 03/24/2025 | 102 | 85 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N | Chelmsford/Westford | Draft Group Study Agreement - Screening Review
National Grid | WORCESTER | 178535 | 01604 | 7.6 | Solar | 05_01_55W1 | 12/07/2017 | 12/07/2017 | 17 | 0 | 17 | 01/04/2018 | 01/04/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 | 12/07/2017 | 3/22/2019 | Y | EXP | 441 |  |  | 0 | 0 | 0 |  |  | 12/21/2018 | Connected |  | N | Chelmsford/Westford | Draft Group Study Agreement - Study Hold
National Grid | WEBSTER | 175939 | 01570 | 7.6 | Solar | 05_05_108W60 | 01/21/2015 | 01/21/2015 | 23 | 22 | 1 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 |  | 5/31/2015 | N | EXP | 83 |  |  | 0 | 0 | 0 | 3/13/2015 | 3/13/2015 | 12/7/2015 | Connected |  | N | Chelmsford/Westford | Draft Group Study Agreement
National Grid | RUTLAND | 251090 | 01543 | 75 | Natural Gas | 05_05_311W1 | 12/06/2019 | 12/26/2019 | 12 | 7 | 5 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 | 12/06/2019 | 6/2/2022 | Y | STD | 323 | 08/21/2021 | 03/21/2022 | 213 | 21 | 192 |  |  | 5/5/2022 | Connected |  | Y | Chelmsford/Westford | Draft Group Study Agreement
National Grid | BLACKSTONE | 665766 | 01504 | 7.6 | Solar | 05_12_25W1 | 01/15/2025 | 02/04/2025 | 4 | 0 | 4 | 02/05/2025 | 02/05/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/15/2025 | 3/21/2026 | Y | EXP | 365 | 10/28/2025 | 10/29/2025 | 2 | 0 | 2 |  |  |  | Withdrawn |  | Y | Leominster | Group Window
National Grid | MARLBOROUGH | 341902 | 01752 | 15.2 | Solar | 05_12_51T2 | 02/11/2021 | 02/12/2021 | 0 | 0 | 0 | 02/16/2021 | 02/16/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 |  | 11/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2021 | Connected |  | N | Spencer-Rutland | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 438236 | 01906 | 15.2 | Solar | 05_14_36L1 | 06/16/2022 | 06/21/2022 | 2 | 0 | 2 | 06/22/2022 | 06/22/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2022 | Connected |  | N | Leominster | Group Window
National Grid | ESSEX | 175897 | 01929 | 1988 | Solar | 05_14_58L2 | 07/31/2015 | 07/31/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2015 | 09/03/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/10/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton | Group Window
National Grid | NEWBURY | 437862 | 01950 | 7.6 | Solar | 05_14_73L2 | 01/17/2023 | 01/19/2023 | 2 | 0 | 2 | 01/20/2023 | 01/20/2023 | 204 | 184 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton | Draft Group Study Agreement
National Grid | CHELMSFORD | 670946 | 01824 | 7.6 | Solar | 05_14_92L1 | 02/12/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 02/12/2025 | 4/11/2026 | Y | EXP | 365 | 06/14/2025 | 06/13/2025 | 0 | 0 | 0 |  |  | 6/21/2025 | Connected |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 425538 | 01886 | 250 | Solar | 05_01_24W2 | 06/01/2022 | 06/15/2022 | 10 | 2 | 8 |  |  | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 674907 | 01821 | 10 | Solar | 05_01_412L1 | 03/03/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 178532 | 01606 | 7.6 | Solar | 05_01_55W1 | 12/05/2017 | 12/05/2017 | 83 | 82 | 1 | 06/06/2018 | 06/06/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2018 |  | 12/10/2018 | N | EXP | 188 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | WEBSTER | 176333 | 01570 | 6 | Solar | 05_05_108W60 | 09/15/2015 | 09/15/2015 | 4 | 4 | 0 | 09/22/2015 | 09/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 | 09/15/2015 | 9/21/2016 | Y | EXP | 348 | 10/18/2016 | 10/27/2016 | 7 | 0 | 7 | 12/13/2016 | 12/13/2016 | 12/16/2016 | Connected |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 287875 | 01543 | 17.7 | Solar | 05_05_311W1 | 04/15/2020 | 06/03/2020 | 8 | 7 | 1 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2020 |  | 7/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2021 | Connected |  | N | Hopedale-East | On Hold Behind Preceding Group Study
National Grid | BLACKSTONE | 673544 | 01504 | 10 | Solar | 05_12_25W1 | 02/21/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/21/2025 | 6/7/2026 | Y | EXP | 365 | 06/14/2025 | 10/29/2025 | 138 | 0 | 138 |  |  | 1/5/2026 | Connected |  | N | MPL-East | Scoping Meeting
National Grid | MARLBOROUGH | 347745 | 01752 | 10 | Solar | 05_12_51T2 | 04/15/2021 | 05/05/2021 | 13 | 12 | 1 | 05/06/2021 | 05/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  | 7/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2021 | Connected |  | N | Ayer-Clinton | Draft Group Study Agreement
National Grid | SAUGUS | 463499 | 01906 | 15.2 | Solar | 05_14_36L1 | 09/27/2022 | 10/04/2022 | 6 | 5 | 1 | 10/05/2022 | 10/05/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2022 |  | 1/10/2024 | N | EXP | 430 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Adams-Deerfield | Closed
National Grid | HAMILTON | 175896 | 01982 | 476 | Solar | 05_14_58L2 | 07/31/2015 | 07/31/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2015 | 09/03/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/10/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Ayer-Clinton | Draft Group Study Agreement
National Grid | NEWBURY | 442456 | 01950 | 7.6 | Solar | 05_14_73L2 | 07/20/2022 | 07/21/2022 | 1 | 0 | 1 | 07/22/2022 | 07/22/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton | Draft Group Study Agreement
National Grid | CHELMSFORD | 688427 | 01824 | 20 | Solar | 05_14_92L1 | 05/02/2025 | 05/27/2025 | 16 | 14 | 2 | 05/28/2025 | 05/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Marlborough | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 426710 | 01886 | 15.2 | Solar | 05_01_24W2 | 04/27/2022 | 04/29/2022 | 2 | 0 | 2 | 05/02/2022 | 05/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  | 8/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2022 | Connected |  | N | Leominster | Group Window
National Grid | BILLERICA | 677792 | 01821 | 10 | Solar | 05_01_412L1 | 03/13/2025 | 04/10/2025 | 3 | 0 | 3 | 04/22/2025 | 04/22/2025 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 03/13/2025 | 6/10/2026 | Y | EXP | 365 | 09/05/2025 | 10/25/2025 | 51 | 0 | 51 |  |  | 12/2/2025 | Connected |  | N | Brockton-North | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 176365 | 01605 | 3.8 | Solar | 05_05_108W60 | 03/08/2016 | 03/08/2016 | 3 | 3 | 0 | 03/15/2016 | 03/15/2016 | 227 | 0 | 227 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2016 |  | 3/15/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East | On Hold Behind Preceding Group Study
National Grid | WEBSTER | 389739 | 01570 | 0 | Other | 05_05_311W1 | 11/10/2021 | 01/05/2022 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 01/26/2022 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 686943 | 01543 | 3.8 | Solar | 05_12_25W1 | 04/22/2025 | 05/08/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Gardner-Winchendon | On Hold Behind Preceding Group Study
National Grid | BLACKSTONE | 368281 | 01504 | 7.6 | Solar | 05_12_51T2 | 07/23/2021 | 01/07/2022 | 2 | 0 | 2 | 07/28/2021 | 07/28/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 | 07/23/2021 | 1/10/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2022 | Connected |  | N | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | MARLBOROUGH | 555470 | 01752 | 7.54 | Solar | 05_14_36L1 | 09/14/2023 | 09/18/2023 | 3 | 1 | 2 | 09/19/2023 | 09/19/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  | 10/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2024 | Connected |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 176030 | 01906 | 30 | Solar | 05_14_58L2 | 11/05/2014 | 11/05/2014 | 3 | 0 | 3 | 11/12/2014 | 11/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2014 | 11/05/2014 | 9/30/2015 | Y | EXP | 293 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 3/6/2015 | Connected |  | N | Spencer-Rutland | Scoping Meeting
National Grid | ESSEX | 445349 | 01929 | 7.6 | Solar | 05_14_73L2 | 07/19/2022 | 07/22/2022 | 4 | 3 | 1 | 07/25/2022 | 07/25/2022 | 57 | 39 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Barre-Athol | Scoping Meeting
National Grid | NEWBURY | 719555 | 01950 | 11.4 | Solar | 05_14_92L1 | 09/16/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 84 | 25 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East | Scoping Meeting
National Grid | CHELMSFORD | 436749 | 01824 | 2.32 | Solar | 05_01_24W2 | 06/17/2022 | 06/22/2022 | 2 | 0 | 2 | 06/23/2022 | 06/23/2022 | 65 | 40 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 | 06/17/2022 | 12/26/2024 | Y | EXP | 365 | 06/26/2024 | 07/02/2024 | 7 | 0 | 7 |  |  | 8/9/2024 | Connected |  | N | Marlborough | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 680197 | 01886 | 11.5 | Solar | 05_01_412L1 | 04/08/2025 | 04/23/2025 | 1 | 0 | 1 | 05/13/2025 | 05/13/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 | 04/08/2025 | 6/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2025 | Connected |  | N | Hopedale-East | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 178563 | 01821 | 2500 | Solar | 05_01_55W1 | 04/05/2018 | 04/05/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 07/20/2018 | 68 | 52 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 176355 | 01605 | 6 | Solar | 05_05_108W60 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2015 | 05/14/2015 | 12/31/2016 | Y | EXP | 578 | 11/19/2015 | 12/15/2015 | 17 | 0 | 17 | 3/22/2016 | 3/22/2016 | 3/28/2016 | Connected |  | N | Millbury-Grafton | Group Window
National Grid | WEBSTER | 586186 | 01570 | 150 | Solar | 05_05_311W1 | 02/01/2024 | 03/25/2024 | 36 | 28 | 8 | 03/26/2024 | 03/26/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2024 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 716298 | 01543 | 0 | Battery Add-On | 05_12_25W1 | 09/03/2025 | 10/17/2025 | 3 | 0 | 3 | 10/20/2025 | 10/20/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Attleboro | On Hold Behind Preceding Group Study
National Grid | BELLINGHAM | 369753 | 02019 | 8.376 | Solar | 05_12_51T2 | 08/17/2021 | 08/27/2021 | 9 | 8 | 1 | 08/30/2021 | 08/30/2021 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2021 |  | 11/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2022 | Connected |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | MARLBOROUGH | 578652 | 01752 | 11.4 | Solar | 05_14_36L1 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 | 12/27/2023 | 2/27/2025 | Y | EXP | 365 | 03/16/2024 | 04/10/2024 | 26 | 0 | 26 |  |  | 4/16/2024 | Connected |  | N | Leominster | Group Window
National Grid | SAUGUS | 176726 | 01906 | 179 | Solar | 05_14_58L2 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2016 | 03/22/2016 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2016 |  | 2/28/2017 | N | STD | 210 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | BEVERLY | 445187 | 01915 | 15.08 | Solar | 05_14_73L2 | 07/18/2022 | 08/03/2022 | 13 | 11 | 2 | 08/04/2022 | 08/04/2022 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 | 07/18/2022 | 10/1/2023 | Y | EXP | 365 | 10/19/2022 | 11/09/2022 | 22 | 0 | 22 |  |  | 11/29/2022 | Connected |  | N | Attleboro | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 727308 | 01950 | 11.4 | Solar | 05_14_92L1 | 10/17/2025 | 10/23/2025 | 4 | 0 | 4 | 11/05/2025 | 11/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 534808 | 01886 | 15.2 | Solar | 05_01_24W2 | 06/19/2023 | 08/01/2023 | 30 | 26 | 4 | 08/02/2023 | 08/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N | Hanover | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 680170 | 01863 | 10 | Solar | 05_01_412L1 | 03/24/2025 | 04/22/2025 | 21 | 16 | 5 | 04/23/2025 | 04/23/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 185992 | 01821 | 8.4 | Solar | 05_01_55W1 | 07/17/2018 | 08/14/2018 | 19 | 0 | 19 | 08/15/2018 | 08/15/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 |  | 9/25/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2018 | Connected |  | N | Leominster | Group Window
National Grid | WORCESTER | 176417 | 01606 | 10 | Solar | 05_05_108W60 | 12/02/2015 | 12/02/2015 | 3 | 3 | 0 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2015 |  | 12/8/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 12/15/2015 | 12/15/2015 | 6/6/2016 | Connected |  | N | Amesbury Newburyport | Pending - Screening Review
National Grid | WEBSTER | 656819 | 01570 | 10 | Solar | 05_05_311W1 | 11/25/2024 | 02/27/2025 | 40 | 37 | 3 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Gardner-Winchendon | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 726138 | 01543 | 17.2 | Solar | 05_12_25W2 | 10/13/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | BELLINGHAM | 372473 | 02019 | 6.96 | Solar | 05_12_51T2 | 07/28/2021 | 07/29/2021 | 1 | 0 | 1 | 07/30/2021 | 07/30/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2021 |  | 8/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2021 | Connected |  | N | Gardner-Winchendon | On Hold Behind Preceding Group Study
National Grid | MARLBOROUGH | 629011 | 01752 | 23 | Solar | 05_14_36L1 | 07/31/2024 | 08/05/2024 | 6 | 5 | 1 | 09/27/2024 | 09/27/2024 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/31/2024 | 11/21/2025 | Y | EXP | 365 | 01/11/2025 | 02/24/2025 | 45 | 0 | 45 |  |  | 3/5/2025 | Connected |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | MELROSE | 176756 | 02176 | 20.86 | Solar | 05_14_58L2 | 02/23/2016 | 02/23/2016 | 1 | 1 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2016 |  | 3/1/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 11/1/2016 | 11/1/2016 | 11/1/2016 | Connected |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | BEVERLY | 473412 | 01915 | 15.2 | Solar | 05_14_73L2 | 11/01/2022 | 11/02/2022 | 1 | 0 | 1 | 11/03/2022 | 11/03/2022 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 11/01/2022 | 12/19/2023 | Y | EXP | 365 | 01/28/2023 | 02/15/2023 | 19 | 0 | 19 |  |  | 6/13/2023 | Connected |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 511257 | 01950 | 249 | Solar | 05_14_92L2 | 03/16/2023 | 04/07/2023 | 16 | 6 | 10 | 04/10/2023 | 04/10/2023 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 | 03/16/2023 | 9/7/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 540716 | 01824 | 0 | Solar | 05_01_24W2 | 07/14/2023 | 07/19/2023 | 3 | 0 | 3 | 07/20/2023 | 07/20/2023 | 54 | 30 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 |  | 10/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 699214 | 01886 | 9.423 | Solar | 05_01_412L1 | 06/23/2025 | 06/25/2025 | 2 | 0 | 2 | 06/26/2025 | 06/26/2025 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2025 |  | 8/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 190717 | 01821 | 10 | Solar | 05_01_55W1 | 07/13/2018 | 10/23/2018 | 30 | 24 | 6 | 10/24/2018 | 10/24/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2018 | 07/13/2018 | 8/28/2019 | Y | EXP | 302 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 5/23/2019 | Connected |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 176794 | 01606 | 7.6 | Solar | 05_05_108W60 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 | 02/24/2016 | 3/1/2017 | Y | EXP | 329 | 06/28/2016 | 09/15/2016 | 55 | 0 | 55 | 4/6/2016 | 4/6/2016 | 11/18/2016 | Connected |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | WEBSTER | 661545 | 01570 | 10 | Solar | 05_05_311W1 | 12/30/2024 | 01/17/2025 | 5 | 0 | 5 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/30/2024 | 6/5/2026 | Y | EXP | 365 | 08/21/2025 | 01/27/2026 | 160 | 0 | 160 |  |  | 12/9/2025 | Connected |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 174932 | 01543 | 278.4 | Solar | 05_12_25W2 | 08/29/2013 | 08/29/2013 | 7 | 0 | 7 | 09/11/2013 | 09/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 08/29/2013 | 10/31/2014 | Y | EXP | 378 | 12/19/2014 | 02/12/2015 | 36 | 0 | 36 | 4/1/2015 | 4/1/2015 | 4/6/2015 | Connected |  | N | Gardner-Winchendon | On Hold Behind Preceding Group Study
National Grid | BELLINGHAM | 396471 | 02019 | 0 | Other | 05_12_51T2 | 01/04/2022 | 01/28/2022 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 03/02/2022 | 22 | 15 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon | On Hold Behind Preceding Group Study
National Grid | MARLBOROUGH | 628681 | 01752 | 19 | Solar | 05_14_36L1 | 07/30/2024 | 08/01/2024 | 2 | 0 | 2 | 08/02/2024 | 08/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2024 | Connected |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 177190 | 01906 | 323 | Solar | 05_14_58L2 | 08/21/2015 | 08/21/2015 | 4 | 0 | 4 | 08/27/2015 | 08/27/2015 | 0 | 0 | 0 | 11/05/2015 | 01/06/2016 | 40 | 12 | 28 |  |  | 0 | 0 | 0 | 01/06/2016 | 40 | 12 | 28 |  |  | 0 | 0 | 0 | 2/9/2016 | 08/21/2015 | 8/1/2017 | Y | EXP | 539 | 06/15/2017 | 09/06/2017 | 57 | 0 | 57 | 8/30/2017 | 8/30/2017 | 9/7/2017 | Connected |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | ESSEX | 642436 | 01929 | 10 | Solar | 05_14_73L2 | 09/29/2024 | 10/17/2024 | 5 | 2 | 3 | 10/18/2024 | 10/18/2024 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 09/29/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N | Gardner-Winchendon | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 724655 | 01950 | 11.5 | Solar | 05_14_92L2 | 10/07/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 3/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 575704 | 01886 | 14.4 | Solar | 05_01_24W2 | 12/07/2023 | 12/08/2023 | 1 | 0 | 1 | 12/11/2023 | 12/11/2023 | 28 | 3 | 25 | 02/07/2024 | 03/18/2024 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 03/18/2024 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 3/22/2024 |  | 5/30/2025 | N | EXP | 365 | 06/08/2024 | 08/28/2024 | 82 | 0 | 82 |  |  | 10/2/2024 | Connected |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 642827 | 01863 | 4990 | Other | 05_01_412L2 | 11/21/2024 | 12/12/2024 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 01/13/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Gardner-Winchendon | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 195060 | 01821 | 10 | Solar | 05_01_55W1 | 09/04/2018 | 10/12/2018 | 11 | 10 | 1 | 10/15/2018 | 10/15/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 176831 | 01606 | 6 | Solar | 05_05_108W60 | 02/25/2016 | 02/25/2016 | 3 | 3 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 |  | 3/5/2017 | N | EXP | 327 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 2/22/2017 | Connected |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | WEBSTER | 662117 | 01570 | 5.76 | Solar | 05_05_311W1 | 12/21/2024 | 02/12/2025 | 2 | 0 | 2 | 02/13/2025 | 02/13/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N | MPL-East | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 178186 | 01543 | 15.2 | Solar | 05_12_25W2 | 04/13/2018 | 04/13/2018 | 6 | 0 | 6 | 04/25/2018 | 04/25/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/21/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  | 1/25/2019 | Connected |  | N | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | BELLINGHAM | 401039 | 02019 | 15.2 | Solar | 05_12_51T2 | 02/03/2022 | 02/04/2022 | 1 | 0 | 1 | 02/07/2022 | 02/07/2022 | 29 | 18 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  | 7/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | MARLBOROUGH | 656931 | 01752 | 0 | Battery Add-On | 05_14_36L1 | 11/26/2024 | 12/23/2024 | 6 | 1 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | SAUGUS | 178313 | 01906 | 875 | Solar | 05_14_58L2 | 02/26/2018 | 02/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/26/2018 | 04/06/2018 | 29 | 0 | 29 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 02/26/2018 | 4/4/2022 | Y | STD | 100 | 04/20/2021 | 10/12/2021 | 175 | 3 | 172 |  |  | 3/28/2022 | Connected |  | N
National Grid | HAMILTON | 648149 | 01982 | 23 | Solar | 05_14_73L2 | 10/18/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 175361 | 01950 | 8 | Solar | 05_14_92L2 | 11/13/2014 | 11/13/2014 | 5 | 0 | 5 | 11/21/2014 | 11/21/2014 | 249 | 0 | 249 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2014 |  | 1/11/2015 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 576161 | 01824 | 10 | Solar | 05_01_24W2 | 01/03/2024 | 01/05/2024 | 2 | 0 | 2 | 01/08/2024 | 01/08/2024 | 44 | 19 | 25 | 05/22/2024 | 07/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 07/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 6/5/2024 |  | 6/11/2025 | N | EXP | 365 | 06/27/2024 | 07/10/2024 | 14 | 0 | 14 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 670827 | 01824 | 3.8 | Solar | 05_01_412L2 | 02/07/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 9/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 197026 | 01821 | 8.4 | Solar | 05_01_55W1 | 09/26/2018 | 11/08/2018 | 27 | 17 | 10 | 11/09/2018 | 11/09/2018 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 | 09/26/2018 | 12/23/2019 | Y | EXP | 365 | 06/18/2019 | 06/17/2019 | 0 | 0 | 0 |  |  | 8/1/2019 | Connected |  | N
National Grid | WORCESTER | 177051 | 01606 | 7.6 | Solar | 05_05_108W60 | 01/11/2017 | 01/11/2017 | 4 | 3 | 1 | 01/18/2017 | 01/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2017 | 01/11/2017 | 1/18/2018 | Y | EXP | 364 | 03/08/2017 | 03/01/2017 | 0 | 0 | 0 | 6/19/2017 | 6/19/2017 | 6/22/2017 | Connected |  | N
National Grid | WEBSTER | 667325 | 01570 | 14.625 | Solar | 05_05_311W2 | 01/29/2025 | 02/05/2025 | 1 | 0 | 1 | 12/11/2025 | 12/11/2025 | 76 | 65 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RUTLAND | 178740 | 01543 | 15.2 | Solar | 05_12_25W2 | 04/18/2018 | 04/18/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 4/24/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 421351 | 02019 | 0 | Solar | 05_12_51T2 | 04/01/2022 | 04/04/2022 | 1 | 0 | 1 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 659827 | 01752 | 3.8 | Solar | 05_14_36L1 | 12/11/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 378906 | 01906 | 11.4 | Solar | 05_14_58L2 | 08/30/2021 | 10/07/2021 | 27 | 26 | 1 | 10/08/2021 | 10/08/2021 | 81 | 58 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2022 |  | 5/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2022 | Connected |  | N
National Grid | ESSEX | 650207 | 01929 | 12.16 | Solar | 05_14_73L2 | 10/28/2024 | 11/26/2024 | 9 | 6 | 3 | 11/27/2024 | 11/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 176022 | 01950 | 3 | Solar | 05_14_92L2 | 03/25/2015 | 03/25/2015 | 6 | 0 | 6 | 04/03/2015 | 04/03/2015 | 464 | 0 | 464 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2015 |  | 8/31/2015 | N | EXP | 147 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 587993 | 01824 | 3.77 | Solar | 05_01_24W2 | 04/16/2024 | 04/19/2024 | 3 | 1 | 2 | 04/22/2024 | 04/22/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2024 | Connected |  | N
National Grid | CHELMSFORD | 670548 | 01863 | 0 | Other | 05_01_412L2 | 08/11/2025 | 09/15/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2025 | 10/03/2025 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BILLERICA | 199337 | 01821 | 4998 | Solar | 05_01_55W1 | 11/19/2018 | 12/05/2018 | 9 | 0 | 9 |  |  | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177115 | 01606 | 10 | Solar | 05_05_108W60 | 08/05/2016 | 08/05/2016 | 1 | 1 | 0 | 08/10/2016 | 08/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2016 | 08/05/2016 | 8/14/2017 | Y | EXP | 364 | 12/05/2016 | 01/16/2017 | 28 | 0 | 28 | 3/16/2017 | 3/16/2017 | 3/20/2017 | Connected |  | N
National Grid | WEBSTER | 742966 | 01570 | 7.6 | Solar | 05_05_311W2 | 01/02/2026 | 01/07/2026 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RUTLAND | 327874 | 01543 | 7.6 | Solar | 05_12_25W2 | 11/23/2020 | 11/25/2020 | 1 | 0 | 1 | 11/27/2020 | 11/27/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 | 11/23/2020 | 9/10/2022 | Y | EXP | 365 | 04/22/2021 | 08/10/2021 | 110 | 0 | 110 |  |  | 9/24/2021 | Connected |  | N
National Grid | BELLINGHAM | 433980 | 02019 | 7.6 | Solar | 05_12_51T2 | 06/14/2022 | 06/15/2022 | 2 | 1 | 1 | 06/16/2022 | 06/16/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 |  | 7/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2023 | Connected |  | N
National Grid | MARLBOROUGH | 665116 | 01752 | 10 | Solar | 05_14_36L1 | 01/10/2025 | 01/14/2025 | 3 | 0 | 3 | 04/02/2025 | 04/02/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2025 | Connected |  | N
National Grid | MELROSE | 410741 | 02176 | 6 | Solar | 05_14_58L2 | 02/21/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/21/2022 | 2/15/2024 | Y | EXP | 365 | 01/28/2023 | 02/14/2023 | 18 | 0 | 18 |  |  | 3/10/2023 | Connected |  | N
National Grid | HAMILTON | 657626 | 01982 | 3.8 | Solar | 05_14_73L2 | 11/29/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 176148 | 01950 | 172 | Solar | 05_14_92L2 | 08/27/2015 | 08/27/2015 | 0 | 0 | 0 | 08/31/2015 | 08/31/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 |  | 9/5/2016 | N | EXP | 370 |  |  | 0 | 0 | 0 | 2/2/2016 | 2/2/2016 | 5/5/2016 | Connected |  | N
National Grid | CHELMSFORD | 595137 | 01824 | 8.7 | Solar | 05_01_24W2 | 03/29/2024 | 04/04/2024 | 4 | 0 | 4 | 04/05/2024 | 04/05/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 4/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2024 | Connected |  | N
National Grid | WESTFORD | 689117 | 01886 | 15.2 | Solar | 05_01_412L2 | 05/05/2025 | 05/06/2025 | 1 | 0 | 1 | 05/07/2025 | 05/07/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 199325 | 01821 | 4998 | Solar | 05_01_55W1 | 11/19/2018 | 11/28/2018 | 4 | 0 | 4 |  |  | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177305 | 01605 | 50.4 | Solar | 05_05_108W60 | 11/15/2016 | 11/15/2016 | 10 | 10 | 0 | 11/30/2016 | 11/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2016 |  | 11/21/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 | 5/10/2017 | 5/10/2017 | 5/17/2017 | Connected |  | N
National Grid | WEBSTER | 745339 | 01570 | 11.5 | Solar | 05_05_311W2 | 01/14/2026 | 01/16/2026 | 2 | 0 | 2 | 01/28/2026 | 01/28/2026 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2026 |  | 3/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RUTLAND | 475161 | 01543 | 15.2 | Solar | 05_12_25W2 | 11/07/2022 | 11/08/2022 | 2 | 1 | 1 | 11/09/2022 | 11/09/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 433829 | 02019 | 5.76 | Solar | 05_12_51T2 | 06/07/2022 | 06/15/2022 | 6 | 5 | 1 | 06/16/2022 | 06/16/2022 | 74 | 42 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 667873 | 01752 | 10.15 | Solar | 05_14_36L1 | 01/26/2025 | 02/25/2025 | 2 | 0 | 2 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | SAUGUS | 576775 | 01906 | 23 | Solar | 05_14_58L2 | 12/08/2023 | 12/12/2023 | 2 | 0 | 2 | 03/05/2024 | 03/05/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2024 | Connected |  | N
National Grid | ESSEX | 658155 | 01929 | 0 | Battery Add-On | 05_14_73L2 | 12/03/2024 | 12/05/2024 | 2 | 0 | 2 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 12/03/2024 | 3/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | NEWBURY | 176761 | 01950 | 7.6 | Solar | 05_14_92L2 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 3/1/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N
National Grid | CHELMSFORD | 598070 | 01824 | 7.6 | Solar | 05_01_24W2 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/21/2024 | 4/11/2025 | Y | EXP | 365 | 06/13/2024 | 09/11/2024 | 91 | 0 | 91 |  |  | 9/17/2024 | Connected |  | N
National Grid | WESTFORD | 709362 | 01886 | 11.4 | Solar | 05_01_412L2 | 08/08/2025 | 08/19/2025 | 6 | 5 | 1 | 08/20/2025 | 08/20/2025 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 210006 | 01821 | 7.6 | Solar | 05_01_55W1 | 02/15/2019 | 02/28/2019 | 7 | 0 | 7 | 03/01/2019 | 03/01/2019 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177521 | 01606 | 7.6 | Solar | 05_05_108W60 | 09/29/2016 | 09/29/2016 | 3 | 3 | 0 | 10/04/2016 | 10/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 | 09/29/2016 | 10/4/2017 | Y | EXP | 364 | 01/03/2017 | 01/16/2017 | 9 | 0 | 9 | 2/16/2017 | 2/16/2017 | 2/22/2017 | Connected |  | N
National Grid | DUDLEY | 747806 | 01571 | 3.8 | Solar | 05_05_311W2 | 01/27/2026 | 01/30/2026 | 3 | 0 | 3 | 03/17/2026 | 03/17/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RUTLAND | 608064 | 01543 | 0 | Battery Add-On | 05_12_25W2 | 05/09/2024 | 05/10/2024 | 1 | 0 | 1 | 05/13/2024 | 05/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 | 05/09/2024 | 6/20/2025 | Y | EXP | 365 | 07/31/2024 | 12/05/2024 | 127 | 0 | 127 |  |  | 12/11/2024 | Connected |  | N
National Grid | BELLINGHAM | 448083 | 02019 | 7.6 | Solar | 05_12_51T2 | 08/17/2022 | 08/22/2022 | 17 | 9 | 8 | 08/23/2022 | 08/23/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 |  | 10/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2023 | Connected |  | N
National Grid | MARLBOROUGH | 669838 | 01752 | 6.84 | Solar | 05_14_36L1 | 02/04/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | MELROSE | 579860 | 02176 | 7.875 | Solar | 05_14_58L2 | 01/18/2024 | 02/01/2024 | 11 | 9 | 2 | 02/02/2024 | 02/02/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 01/18/2024 | 2/26/2025 | Y | EXP | 365 | 03/20/2024 | 04/09/2024 | 21 | 0 | 21 |  |  | 4/12/2024 | Connected |  | N
National Grid | BEVERLY | 664749 | 01915 | 5.7 | Solar | 05_14_73L2 | 01/09/2025 | 02/06/2025 | 13 | 8 | 5 | 02/07/2025 | 02/07/2025 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N
National Grid | NEWBURY | 177216 | 01950 | 75 | Solar | 05_14_92L2 | 06/10/2016 | 06/10/2016 | 4 | 4 | 0 | 06/17/2016 | 06/17/2016 | 144 | 0 | 144 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/18/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 604247 | 01824 | 3.19 | Solar | 05_01_24W2 | 04/19/2024 | 04/24/2024 | 3 | 0 | 3 | 04/25/2024 | 04/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 730060 | 01886 | 20 | Solar | 05_01_412L2 | 10/30/2025 | 10/31/2025 | 1 | 0 | 1 | 11/03/2025 | 11/03/2025 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 208913 | 01821 | 7.6 | Solar | 05_01_55W1 | 02/08/2019 | 02/20/2019 | 6 | 0 | 6 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 | 02/08/2019 | 7/22/2020 | Y | EXP | 365 | 10/05/2019 | 12/02/2019 | 58 | 0 | 58 |  |  | 2/28/2020 | Connected |  | N
National Grid | WORCESTER | 177602 | 01606 | 7.04 | Solar | 05_05_108W60 | 07/19/2017 | 07/19/2017 | 7 | 6 | 1 | 07/28/2017 | 07/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2017 |  | 7/24/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 | 9/29/2017 | 9/29/2017 | 10/3/2017 | Connected |  | N
National Grid | WEBSTER | 176966 | 01570 | 6 | Solar | 05_05_311W2 | 10/03/2016 | 10/03/2016 | 0 | 0 | 0 | 10/04/2016 | 10/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 | 10/03/2016 | 5/12/2017 | Y | EXP | 213 | 11/22/2016 | 11/23/2016 | 1 | 0 | 1 | 5/15/2017 | 5/15/2017 | 5/15/2017 | Connected |  | N
National Grid | RUTLAND | 625229 | 01543 | 15.2 | Solar | 05_12_25W2 | 07/18/2024 | 07/25/2024 | 5 | 3 | 2 | 07/26/2024 | 07/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 8/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 457042 | 01504 | 15.2 | Solar | 05_12_51T2 | 09/07/2022 | 09/08/2022 | 1 | 0 | 1 | 09/09/2022 | 09/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 |  | 6/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 710902 | 01752 | 15.2 | Solar | 05_14_36L1 | 08/10/2025 | 08/14/2025 | 4 | 0 | 4 | 08/15/2025 | 08/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | SAUGUS | 636327 | 01906 | 5 | Solar | 05_14_58L2 | 08/29/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 10/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | HAMILTON | 683559 | 01982 | 23 | Solar | 05_14_73L2 | 04/09/2025 | 04/11/2025 | 0 | 0 | 0 | 04/11/2025 | 04/11/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2025 | Connected |  | N
National Grid | NEWBURY | 178502 | 01950 | 250 | Solar | 05_14_92L2 | 12/15/2017 | 12/15/2017 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2018 | 02/28/2018 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2018 | 12/15/2017 | 12/20/2019 | Y | STD | 660 |  |  | 0 | 0 | 0 |  |  | 12/20/2019 | Connected |  | N
National Grid | WESTFORD | 626022 | 01886 | 7.6 | Solar | 05_01_24W2 | 07/18/2024 | 07/29/2024 | 0 | 0 | 0 | 07/30/2024 | 07/30/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 |  | 9/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | CHELMSFORD | 743323 | 01824 | 10 | Solar | 05_01_412L2 | 01/05/2026 | 01/06/2026 | 1 | 0 | 1 | 01/07/2026 | 01/07/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 245447 | 01821 | 10 | Solar | 05_01_55W1 | 07/25/2019 | 07/30/2019 | 2 | 0 | 2 | 07/31/2019 | 07/31/2019 | 14 | 7 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 8/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N
National Grid | WORCESTER | 177667 | 01605 | 10 | Solar | 05_05_108W60 | 05/24/2017 | 05/24/2017 | 3 | 3 | 0 | 05/31/2017 | 05/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 | 05/24/2017 | 5/30/2018 | Y | EXP | 363 | 10/02/2017 | 11/30/2017 | 35 | 0 | 35 | 12/20/2017 | 12/20/2017 | 1/5/2018 | Connected |  | N
National Grid | WEBSTER | 177011 | 01570 | 10 | Solar | 05_05_311W2 | 10/14/2016 | 10/14/2016 | 1 | 1 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2016 | 10/14/2016 | 10/23/2017 | Y | EXP | 364 | 01/20/2017 | 03/02/2017 | 28 | 0 | 28 | 3/29/2017 | 3/29/2017 | 3/31/2017 | Connected |  | N
National Grid | RUTLAND | 628432 | 01543 | 23 | Solar | 05_12_25W2 | 07/29/2024 | 07/31/2024 | 2 | 0 | 2 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | BLACKSTONE | 459143 | 01504 | 15.2 | Solar | 05_12_51T2 | 09/15/2022 | 09/19/2022 | 2 | 0 | 2 | 09/20/2022 | 09/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 10/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2023 | Connected |  | N
National Grid | MARLBOROUGH | 549712 | 01752 | 4998 | Other | 05_14_36L2 | 10/25/2023 | 11/16/2023 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 02/16/2024 | 62 | 43 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MELROSE | 695649 | 02176 | 5.76 | Solar | 05_14_58L2 | 06/09/2025 | 06/12/2025 | 3 | 0 | 3 | 06/13/2025 | 06/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2025 | Connected |  | N
National Grid | ESSEX | 719098 | 01929 | 11.5 | Battery Add-On | 05_14_73L2 | 09/16/2025 | 09/24/2025 | 5 | 3 | 2 | 09/25/2025 | 09/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 192826 | 01950 | 3.64 | Solar | 05_14_92L2 | 08/20/2018 | 09/13/2018 | 7 | 1 | 6 | 09/14/2018 | 09/14/2018 | 68 | 3 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 630081 | 01886 | 7.6 | Solar | 05_01_24W2 | 08/05/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | WESTFORD | 745414 | 01886 | 5.76 | Solar | 05_01_412L2 | 01/14/2026 | 01/20/2026 | 7 | 4 | 3 | 02/03/2026 | 02/03/2026 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | BILLERICA | 282553 | 01821 | 4950 | Other | 05_01_55W1 | 04/07/2020 | 04/24/2020 | 12 | 9 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/09/2020 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177874 | 01605 | 3600 | Solar | 05_05_108W60 | 08/14/2017 | 08/14/2017 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2017 | 09/25/2017 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2018 | 08/14/2017 | 9/26/2022 | Y | STD | 505 | 01/22/2022 | 06/01/2022 | 131 | 0 | 131 |  |  | 8/3/2022 | Connected |  | N
National Grid | WEBSTER | 177457 | 01570 | 3.8 | Solar | 05_05_311W2 | 12/07/2016 | 12/07/2016 | 1 | 1 | 0 | 12/12/2016 | 12/12/2016 | 323 | 0 | 323 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 12/07/2016 | 12/30/2018 | Y | EXP | 745 | 12/27/2017 | 10/26/2018 | 303 | 0 | 303 |  |  | 10/26/2018 | Connected |  | N
National Grid | RUTLAND | 644449 | 01543 | 3.8 | Solar | 05_12_25W2 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BLACKSTONE | 476277 | 01504 | 0 | Solar | 05_12_51T2 | 11/09/2022 | 12/19/2022 | 27 | 26 | 1 | 12/20/2022 | 12/20/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 5/15/2024 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 704769 | 01752 | 210 | Solar | 05_14_36L2 | 07/14/2025 | 08/07/2025 | 18 | 8 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MELROSE | 710905 | 02176 | 4.93 | Solar | 05_14_58L2 | 08/10/2025 | 09/17/2025 | 4 | 0 | 4 | 09/25/2025 | 09/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2026 | Connected |  | N
National Grid | HAMILTON | 728805 | 01982 | 10.7 | Solar | 05_14_73L2 | 10/23/2025 | 11/03/2025 | 6 | 2 | 4 | 11/04/2025 | 11/04/2025 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2026 | Connected |  | N
National Grid | NEWBURY | 213493 | 01950 | 10 | Solar | 05_14_92L2 | 04/10/2019 | 05/29/2019 | 48 | 47 | 1 | 06/20/2019 | 06/20/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2019 | 04/10/2019 | 7/31/2020 | Y | EXP | 365 | 02/22/2020 | 06/03/2020 | 102 | 0 | 102 |  |  | 7/10/2020 | Connected |  | N
National Grid | CHELMSFORD | 639285 | 01824 | 7.6 | Solar | 05_01_24W2 | 09/11/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | WESTFORD | 748720 | 01886 | 11.4 | Solar | 05_01_412L2 | 02/02/2026 | 02/03/2026 | 2 | 0 | 2 | 02/13/2026 | 02/13/2026 | 33 | 19 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BILLERICA | 284371 | 01821 | 4950 | Other | 05_01_55W1 | 04/07/2020 | 04/24/2020 | 12 | 9 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/09/2020 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177909 | 01605 | 11.4 | Solar | 05_05_108W60 | 08/16/2017 | 08/16/2017 | 13 | 13 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 | 08/16/2017 | 8/21/2018 | Y | EXP | 348 | 01/18/2018 | 02/14/2018 | 19 | 0 | 19 | 2/27/2018 | 2/27/2018 | 3/6/2018 | Connected |  | N
National Grid | WEBSTER | 177786 | 01570 | 3.8 | Solar | 05_05_311W2 | 06/01/2017 | 06/01/2017 | 7 | 5 | 2 | 06/13/2017 | 06/13/2017 | 198 | 0 | 198 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 | 06/01/2017 | 12/28/2018 | Y | EXP | 563 |  |  | 0 | 0 | 0 |  |  | 10/26/2018 | Connected |  | N
National Grid | RUTLAND | 646179 | 01543 | 7.6 | Solar | 05_12_25W2 | 10/18/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/18/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | BLACKSTONE | 477583 | 01504 | 9.57 | Solar | 05_12_51T2 | 11/15/2022 | 11/17/2022 | 2 | 0 | 2 | 11/18/2022 | 11/18/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 |  | 1/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2023 | Connected |  | N
National Grid | MARLBOROUGH | 720430 | 01752 | 480 | Solar | 05_14_36L2 | 03/09/2026 |  | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MELROSE | 613783 | 02176 | 0 | Battery Add-On | 05_14_58L3 | 05/28/2024 | 06/20/2024 | 16 | 13 | 3 | 06/21/2024 | 06/21/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Terminated |  | Y
National Grid | ESSEX | 457510 | 01929 | 100 | Solar | 05_14_74L1 | 10/10/2022 | 01/04/2023 | 58 | 48 | 10 | 01/05/2023 | 01/05/2023 | 23 | 0 | 23 | 07/10/2025 | 08/28/2025 | 36 | 0 | 36 |  |  | 0 | 0 | 0 | 08/28/2025 | 36 | 0 | 36 |  |  | 0 | 0 | 0 | 9/5/2025 | 10/10/2022 | 2/10/2027 | Y | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NEWBURY | 214979 | 01950 | 3.8 | Solar | 05_14_92L2 | 03/22/2019 | 07/22/2019 | 86 | 86 | 0 | 07/23/2019 | 07/23/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 11/29/2019 | N | EXP | 116 |  |  | 0 | 0 | 0 |  |  | 11/13/2019 | Connected |  | N
National Grid | WESTFORD | 640951 | 01886 | 10 | Solar | 05_01_24W2 | 09/17/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 25 | 0 | 25 | 02/03/2025 | 02/11/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 02/11/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/14/2026 | N | EXP | 365 | 05/28/2025 | 06/25/2025 | 29 | 0 | 29 |  |  | 7/16/2025 | Connected |  | N
National Grid | METHUEN | 174756 | 01844 | 1000 | Solar | 05_01_412L2 | 02/03/2014 | 02/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2014 | 02/26/2014 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2014 |  | 8/14/2016 | N | STD | 681 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 294525 | 01821 | 10 | Solar | 05_01_55W1 | 06/06/2020 | 06/10/2020 | 2 | 0 | 2 | 06/11/2020 | 06/11/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2020 | 06/06/2020 | 10/7/2021 | Y | EXP | 365 | 04/07/2021 | 04/15/2021 | 8 | 0 | 8 |  |  | 8/14/2021 | Connected |  | N
National Grid | WORCESTER | 178247 | 01605 | 4990 | Solar | 05_05_108W60 | 03/27/2018 | 03/27/2018 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/29/2018 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/2/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 178441 | 01570 | 5 | Solar | 05_05_311W2 | 04/02/2018 | 04/02/2018 | 5 | 0 | 5 | 04/10/2018 | 04/10/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 4/8/2019 | N | EXP | 332 |  |  | 0 | 0 | 0 |  |  | 5/29/2019 | Connected |  | N
National Grid | RUTLAND | 650631 | 01543 | 7.6 | Solar | 05_12_25W2 | 10/29/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/29/2024 | 1/7/2026 | Y | EXP | 365 | 04/15/2025 | 09/09/2025 | 148 | 0 | 148 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 483824 | 01504 | 0 | Solar | 05_12_51T2 | 12/08/2022 | 12/15/2022 | 6 | 4 | 2 | 12/16/2022 | 12/16/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 |  | 6/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2023 | Connected |  | N
National Grid | MARLBOROUGH | 729925 | 01752 | 34.6 | Solar | 05_14_36L2 | 11/06/2025 | 11/20/2025 | 9 | 7 | 2 | 11/21/2025 | 11/21/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MELROSE | 710796 | 02176 | 200 | Solar | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 72 | 64 | 8 | 01/07/2026 | 01/07/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ESSEX | 444190 | 01929 | 499 | Solar | 05_14_74L1 | 09/26/2022 | 10/31/2022 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/02/2022 | 12/01/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | NEWBURY | 645210 | 01950 | 7.6 | Solar | 05_01_24W2 | 10/04/2024 | 11/04/2024 | 8 | 4 | 4 | 11/05/2024 | 11/05/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 175472 | 01886 | 762 | Solar | 05_01_412L2 | 11/26/2014 | 11/26/2014 | 28 | 28 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/13/2015 | 02/04/2015 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 |  | 3/16/2016 | N | STD | 114 | 08/11/2017 | 09/09/2017 | 20 | 0 | 20 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 309418 | 01844 | 10 | Solar | 05_01_55W1 | 08/27/2020 | 08/28/2020 | 1 | 1 | 0 | 08/31/2020 | 08/31/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 8/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2020 | Connected |  | N
National Grid | BILLERICA | 178519 | 01821 | 7.6 | Solar | 05_05_108W60 | 04/04/2018 | 04/04/2018 | 14 | 0 | 14 | 05/17/2018 | 05/17/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 | 04/04/2018 | 11/30/2019 | Y | EXP | 541 |  |  | 0 | 0 | 0 |  |  | 10/23/2019 | Connected |  | N
National Grid | WORCESTER | 178533 | 01605 | 110 | Solar | 05_05_311W2 | 12/05/2017 | 12/05/2017 | 26 | 9 | 17 | 01/16/2018 | 01/16/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 |  | 12/11/2018 | N | EXP | 306 |  |  | 0 | 0 | 0 |  |  | 12/21/2018 | Connected |  | N
National Grid | WEBSTER | 651937 | 01570 | 6.84 | Solar | 05_12_25W2 | 11/04/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | Y
National Grid | RUTLAND | 485658 | 01543 | 7.6 | Solar | 05_12_51T2 | 12/15/2022 | 12/19/2022 | 2 | 0 | 2 | 12/20/2022 | 12/20/2022 | 63 | 40 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 3/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2023 | Connected |  | N
National Grid | BELLINGHAM | 737803 | 02019 | 11.5 | Solar | 05_14_36L2 | 12/03/2025 | 12/05/2025 | 2 | 0 | 2 | 01/05/2026 | 01/05/2026 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | MARLBOROUGH | 710791 | 01752 | 240 | Solar | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 72 | 64 | 8 | 01/07/2026 | 01/07/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MELROSE | 660642 | 02176 | 5.76 | Solar | 05_14_74L1 | 12/13/2024 | 01/30/2025 | 27 | 25 | 2 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 | 12/13/2024 | 4/10/2026 | Y | EXP | 365 | 05/07/2025 | 12/22/2025 | 230 | 0 | 230 |  |  |  | Completion Documents |  | N
National Grid | ESSEX | 384627 | 01929 | 400 | Solar | 05_14_92L2 | 08/11/2022 | 10/04/2022 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2022 | 10/28/2022 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 652585 | 01950 | 9.074 | Solar | 05_01_24W2 | 11/06/2024 | 11/25/2024 | 3 | 1 | 2 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2025 | Connected |  | N
National Grid | WESTFORD | 175748 | 01886 | 16 | Solar | 05_01_412L2 | 10/30/2014 | 10/30/2014 | 6 | 4 | 2 | 11/10/2014 | 11/10/2014 | 251 | 0 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2014 |  | 12/30/2014 | N | EXP | 48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 312260 | 01844 | 5.52 | Solar | 05_01_55W1 | 09/29/2020 | 12/03/2020 | 43 | 40 | 3 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 | 09/29/2020 | 12/24/2022 | Y | EXP | 550 | 01/28/2021 | 02/25/2021 | 28 | 0 | 28 |  |  | 12/8/2022 | Connected |  | N
National Grid | BILLERICA | 178665 | 01821 | 4200 | Solar | 05_05_108W60 | 03/16/2018 | 03/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2018 | 04/17/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2018 | 03/16/2018 | 8/5/2022 | Y | STD | 505 | 02/09/2022 | 07/06/2022 | 146 | 0 | 146 |  |  | 7/19/2022 | Connected |  | N
National Grid | WORCESTER | 193822 | 01605 | 15.2 | Solar | 05_05_311W2 | 08/17/2018 |  | 82 | 26 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 662178 | 01571 | 12.92 | Solar | 05_12_25W2 | 12/23/2024 | 01/27/2025 | 3 | 0 | 3 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2025 | Connected |  | N
National Grid | RUTLAND | 501092 | 01543 | 5.76 | Solar | 05_12_51T2 | 03/30/2023 | 04/03/2023 | 2 | 0 | 2 | 04/04/2023 | 04/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2023 | 03/30/2023 | 5/21/2024 | Y | EXP | 365 | 07/20/2023 | 07/24/2023 | 5 | 0 | 5 |  |  | 8/1/2023 | Connected |  | Y
National Grid | BLACKSTONE | 742426 | 01504 | 50 | Solar | 05_14_36L2 | 12/29/2025 | 12/31/2025 | 2 | 0 | 2 | 01/02/2026 | 01/02/2026 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MARLBOROUGH | 710790 | 01752 | 240 | Solar | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 72 | 64 | 8 | 01/07/2026 | 01/07/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SAUGUS | 733696 | 01906 | 5.76 | Solar | 05_14_74L1 | 11/13/2025 | 11/14/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ESSEX | 384623 | 01929 | 400 | Solar | 05_14_92L2 | 08/11/2022 | 10/05/2022 | 38 | 28 | 10 |  |  | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 657142 | 01950 | 7.6 | Solar | 05_01_24W2 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 | 11/26/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | WESTFORD | 176055 | 01886 | 15.48 | Solar | 05_01_412L2 | 01/30/2015 | 01/30/2015 | 11 | 11 | 0 | 02/19/2015 | 02/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2015 |  | 6/30/2015 | N | EXP | 130 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 11/19/2015 | Connected |  | N
National Grid | METHUEN | 318655 | 01844 | 0 | Other | 05_01_55W1 | 12/04/2020 | 01/05/2021 | 20 | 16 | 4 |  |  | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 01/06/2021 | 02/09/2021 | 22 | 5 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 185770 | 01821 | 11.4 | Solar | 05_05_108W60 | 05/18/2018 | 05/18/2018 | 5 | 0 | 5 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 | 05/18/2018 |  | Y | EXP | 466 | 07/11/2019 | 07/10/2019 | 0 | 0 | 0 |  |  | 11/8/2019 | Connected |  | N
National Grid | WORCESTER | 191496 | 01606 | 10 | Solar | 05_05_311W2 | 08/01/2018 | 08/21/2018 | 9 | 4 | 5 | 08/22/2018 | 08/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 672929 | 01570 | 7.6 | Solar | 05_12_25W2 | 02/19/2025 | 03/24/2025 | 5 | 0 | 5 | 03/25/2025 | 03/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | RUTLAND | 524266 | 01543 | 9.28 | Solar | 05_12_51T2 | 05/08/2023 | 05/10/2023 | 2 | 0 | 2 | 05/11/2023 | 05/11/2023 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  | 8/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2023 | Connected |  | N
National Grid | BELLINGHAM | 745432 | 02019 | 21.28 | Solar | 05_14_36L2 | 02/27/2026 | 03/09/2026 | 6 | 4 | 2 | 03/10/2026 | 03/10/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MARLBOROUGH | 710780 | 01752 | 67.3 | Solar | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 72 | 64 | 8 | 01/07/2026 | 01/07/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SAUGUS | 734937 | 01906 | 11.5 | Solar | 05_14_74L1 | 11/19/2025 | 12/01/2025 | 12 | 8 | 4 | 01/07/2026 | 01/07/2026 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 4/1/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HAMILTON | 448098 | 01982 | 280 | Solar | 05_14_92L2 | 04/13/2023 | 08/09/2023 | 80 | 70 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/10/2023 | 09/07/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 667809 | 01950 | 480 | Solar | 05_01_24W2 | 09/16/2025 |  | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 176658 | 01886 | 6 | Solar | 05_01_412L2 | 04/19/2016 | 04/19/2016 | 13 | 13 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 |  | 4/26/2017 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 452194 | 01844 | 6.09 | Solar | 05_01_55W1 | 10/27/2022 | 11/22/2022 | 17 | 15 | 2 | 11/23/2022 | 11/23/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2022 | 10/27/2022 | 6/14/2024 | Y | EXP | 365 | 06/06/2023 | 06/14/2023 | 9 | 0 | 9 |  |  | 7/12/2023 | Connected |  | N
National Grid | BILLERICA | 191437 | 01821 | 7.6 | Solar | 05_05_108W60 | 07/22/2018 | 10/01/2018 | 20 | 11 | 9 | 10/02/2018 | 10/02/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2018 |  | 7/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2020 | Connected |  | N
National Grid | WORCESTER | 255015 | 01606 | 7.6 | Solar | 05_05_311W2 | 09/18/2019 | 10/03/2019 | 0 | 0 | 0 | 10/04/2019 | 10/04/2019 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2019 |  | 9/18/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2020 | Connected |  | N
National Grid | WEBSTER | 673521 | 01570 | 5.76 | Solar | 05_12_25W2 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 526797 | 01543 | 15.2 | Solar | 05_12_51T2 | 05/16/2023 | 05/18/2023 | 2 | 0 | 2 | 05/19/2023 | 05/19/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 8/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N
National Grid | BELLINGHAM | 753619 | 02019 | 5.76 | Solar | 05_14_36L2 | 02/27/2026 | 03/06/2026 | 1 | 0 | 1 | 03/30/2026 | 03/30/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 725182 | 01752 | 15.2 | Solar | 05_14_58L3 | 10/09/2025 | 10/20/2025 | 5 | 0 | 5 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 738754 | 01906 | 7.6 | Solar | 05_14_74L1 | 12/08/2025 | 12/22/2025 | 1 | 0 | 1 | 01/13/2026 | 01/13/2026 | 53 | 36 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | HAMILTON | 470694 | 01982 | 3.8 | Solar | 05_14_92L2 | 11/11/2022 | 11/17/2022 | 4 | 0 | 4 | 11/18/2022 | 11/18/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 | 11/11/2022 | 4/25/2024 | Y | EXP | 365 | 04/05/2023 | 04/25/2023 | 21 | 0 | 21 |  |  | 5/2/2023 | Connected |  | N
National Grid | NEWBURY | 718545 | 01950 | 4.93 | Solar | 05_01_24W2 | 09/11/2025 | 10/24/2025 | 5 | 1 | 4 | 10/27/2025 | 10/27/2025 | 66 | 50 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 176764 | 01886 | 6 | Solar | 05_01_412L2 | 02/24/2016 | 02/24/2016 | 5 | 5 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/24/2016 | 3/1/2017 | Y | EXP | 331 | 08/04/2016 | 08/23/2016 | 13 | 0 | 13 | 4/4/2016 | 4/4/2016 | 9/15/2016 | Connected |  | N
National Grid | METHUEN | 367324 | 01844 | 11.025 | Solar | 05_01_55W1 | 07/25/2021 | 09/03/2021 | 30 | 30 | 0 | 09/07/2021 | 09/07/2021 | 36 | 14 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 12/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2022 | Connected |  | N
National Grid | BILLERICA | 215936 | 01821 | 10 | Solar | 05_05_108W60 | 06/25/2019 | 07/03/2019 | 5 | 0 | 5 | 07/05/2019 | 07/05/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 268191 | 01605 | 7.6 | Solar | 05_05_311W2 | 12/09/2019 | 12/15/2019 | 4 | 0 | 4 | 12/16/2019 | 12/16/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2020 |  | 2/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 681135 | 01570 | 17.1 | Solar | 05_12_25W2 | 03/27/2025 | 04/16/2025 | 4 | 0 | 4 | 05/28/2025 | 05/28/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | RUTLAND | 566169 | 01543 | 0 | Solar | 05_12_51T2 | 10/25/2023 | 11/02/2023 | 6 | 3 | 3 | 11/03/2023 | 11/03/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2023 |  | 12/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2024 | Connected |  | N
National Grid | BELLINGHAM | 174790 | 02019 | 1020 | Diesel | 05_14_36L2 | 06/16/2011 | 06/16/2011 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2011 |  | 5/2/2012 | N | STD | 147 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 5/2/2012 | Connected |  | N
National Grid | MARLBOROUGH | 174768 | 01752 | 75 | Solar | 05_14_58L3 | 08/24/2012 | 08/24/2012 | 8 | 0 | 8 | 09/06/2012 | 09/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2013 |  | 12/14/2012 | N | EXP | 139 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 12/10/2013 | Connected |  | N
National Grid | MELROSE | 744891 | 02176 | 19.38 | Solar | 05_14_74L1 | 01/13/2026 | 01/21/2026 | 4 | 0 | 4 | 01/22/2026 | 01/22/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ESSEX | 610419 | 01929 | 23 | Solar | 05_14_92L2 | 05/13/2024 | 05/20/2024 | 5 | 1 | 4 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2024 | Connected |  | N
National Grid | NEWBURY | 720253 | 01950 | 3.8 | Solar | 05_01_24W2 | 09/18/2025 | 09/30/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 32 | 19 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 176851 | 01886 | 45.6 | Solar | 05_01_412L2 | 11/11/2015 | 11/11/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2015 | 11/11/2015 | 11/18/2016 | Y | EXP | 350 | 05/11/2016 | 07/13/2016 | 42 | 0 | 42 | 12/4/2015 | 12/4/2015 | 8/23/2016 | Connected |  | N
National Grid | HAVERHILL | 368515 | 01832 | 4300 | Solar | 05_01_55W1 | 08/10/2021 | 09/07/2021 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/08/2021 | 10/05/2021 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 215927 | 01821 | 3960 | Solar | 05_05_108W60 | 04/24/2019 | 05/09/2019 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2019 | 06/04/2019 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 291983 | 01606 | 249 | Solar | 05_05_311W2 | 05/14/2020 | 05/21/2020 | 4 | 0 | 4 | 05/22/2020 | 05/22/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 685291 | 01570 | 15.2 | Solar | 05_12_25W2 | 04/21/2025 | 05/12/2025 | 14 | 10 | 4 | 05/13/2025 | 05/13/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | RUTLAND | 562855 | 01543 | 16.065 | Solar | 05_12_51T2 | 10/17/2023 | 10/31/2023 | 10 | 7 | 3 | 11/01/2023 | 11/01/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2024 | Connected |  | N
National Grid | BLACKSTONE | 174865 | 01504 | 30 | Solar | 05_14_36L2 | 04/08/2011 | 04/08/2011 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2012 | 04/08/2011 | 5/2/2012 | Y | EXP | 0 | 02/21/2012 | 03/13/2012 | 15 | 0 | 15 | 8/9/2012 | 8/9/2012 | 5/2/2012 | Connected |  | N
National Grid | MARLBOROUGH | 174767 | 01752 | 100 | Solar | 05_14_58L3 | 08/24/2012 | 08/24/2012 | 8 | 0 | 8 | 09/06/2012 | 09/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2013 |  | 12/14/2012 | N | EXP | 139 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 12/10/2013 | Connected |  | N
National Grid | MELROSE | 753849 | 02176 | 5.76 | Solar | 05_14_74L1 | 03/02/2026 | 03/04/2026 | 1 | 0 | 1 | 03/27/2026 | 03/27/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAMILTON | 637600 | 01982 | 320 | Solar | 05_14_92L2 | 11/01/2024 | 05/19/2025 | 131 | 121 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/20/2025 | 06/17/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 751295 | 01950 | 11.5 | Solar | 05_01_24W2 | 02/16/2026 | 02/18/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 176899 | 01886 | 23.4 | Solar | 05_01_412L2 | 01/26/2016 | 01/26/2016 | 3 | 3 | 0 | 01/29/2016 | 01/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2016 |  | 1/31/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/16/2016 | 9/16/2016 | 9/16/2016 | Connected |  | N
National Grid | METHUEN | 378372 | 01844 | 5.52 | Solar | 05_01_55W1 | 10/11/2021 | 10/19/2021 | 6 | 6 | 0 | 10/20/2021 | 10/20/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 | 10/11/2021 | 10/21/2023 | Y | EXP | 555 | 02/01/2022 | 02/14/2022 | 14 | 0 | 14 |  |  | 8/23/2023 | Connected |  | N
National Grid | BILLERICA | 215920 | 01821 | 4950 | Solar | 05_05_108W60 | 04/24/2019 | 05/09/2019 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2019 | 06/01/2019 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 298911 | 01606 | 24.78 | Solar | 05_05_311W2 | 08/14/2020 | 08/17/2020 | 0 | 0 | 0 | 08/18/2020 | 08/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2021 | Connected |  | N
National Grid | WEBSTER | 689325 | 01570 | 20 | Solar | 05_12_25W2 | 05/06/2025 | 05/16/2025 | 7 | 2 | 5 | 05/19/2025 | 05/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 7/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | RUTLAND | 574209 | 01543 | 490 | Solar | 05_12_51T2 | 12/15/2023 | 01/09/2024 | 14 | 5 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2024 | 03/11/2024 | 43 | 25 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 175714 | 01504 | 64 | Solar | 05_14_36L2 | 12/24/2014 | 12/24/2014 | 7 | 4 | 3 | 01/06/2015 | 01/06/2015 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2015 |  | 12/31/2016 | N | EXP | 683 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 174796 | 01752 | 13 | Solar | 05_14_58L3 | 08/28/2012 | 08/28/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2012 |  | 11/30/2012 | N | EXP | 1 |  |  | 0 | 0 | 0 | 2/7/2013 | 2/7/2013 | 2/21/2013 | Connected |  | N
National Grid | SAUGUS | 753410 | 01906 | 19 | Solar | 05_14_74L1 | 03/03/2026 | 03/26/2026 | 17 | 14 | 3 | 03/27/2026 | 03/27/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAMILTON | 640240 | 01982 | 5.76 | Solar | 05_14_92L2 | 09/13/2024 | 10/02/2024 | 4 | 0 | 4 | 10/03/2024 | 10/03/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 09/13/2024 | 11/6/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 690411 | 01950 | 7.6 | Solar | 05_01_24W3 | 05/07/2025 | 05/21/2025 | 4 | 0 | 4 | 06/10/2025 | 06/10/2025 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2025 | 05/07/2025 | 8/18/2026 | Y | EXP | 365 | 11/07/2025 |  | 146 | 0 | 146 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 177152 | 01886 | 762 | Solar | 05_01_412L2 | 11/26/2014 | 11/26/2014 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/13/2015 | 02/04/2015 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2015 | 11/26/2014 | 12/31/2017 | Y | STD | 766 | 08/11/2017 | 09/09/2017 | 20 | 0 | 20 | 12/1/2017 | 12/1/2017 | 12/19/2017 | Connected |  | N
National Grid | HAVERHILL | 390938 | 01832 | 10 | Solar | 05_01_55W1 | 11/08/2021 | 12/13/2021 | 3 | 1 | 2 | 11/12/2021 | 11/12/2021 | 42 | 27 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 | 11/08/2021 |  | Y | EXP | 365 | 03/08/2022 | 04/11/2022 | 35 | 0 | 35 |  |  | 4/19/2022 | Connected |  | N
National Grid | BILLERICA | 263498 | 01821 | 7.6 | Solar | 05_05_108W60 | 11/19/2019 | 11/20/2019 | 0 | 0 | 0 | 11/21/2019 | 11/21/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2019 | 11/19/2019 | 11/19/2020 | Y | EXP | 365 | 06/04/2020 | 07/07/2020 | 33 | 0 | 33 |  |  | 7/22/2020 | Connected |  | N
National Grid | WORCESTER | 300432 | 01606 | 10 | Solar | 05_05_311W2 | 07/09/2020 | 07/10/2020 | 0 | 0 | 0 | 07/13/2020 | 07/13/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2020 | Connected |  | N
National Grid | WEBSTER | 174478 | 01570 | 164 | Solar | 05_12_25W3 | 04/27/2011 | 04/27/2011 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2011 |  | 10/31/2012 | N | EXP | 329 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 6/27/2012 | Connected |  | N
National Grid | RUTLAND | 625514 | 01543 | 0 | Battery Add-On | 05_12_51T2 | 07/17/2024 | 10/11/2024 | 60 | 50 | 10 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N
National Grid | BLACKSTONE | 177069 | 01504 | 150 | Solar | 05_14_36L2 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 07/29/2016 | 07/29/2016 | 315 | 26 | 289 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/29/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 177122 | 01752 | 0 | Solar | 05_14_58L3 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 | 02/03/2017 | 70 | 58 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/26/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 758818 | 01906 | 5.76 | Solar | 05_14_74L1 | 03/26/2026 | 04/01/2026 | 4 | 0 | 4 | 04/02/2026 | 04/02/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAMILTON | 649338 | 01982 | 7.6 | Solar | 05_14_92L2 | 11/04/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/04/2024 | 1/2/2026 | Y | EXP | 365 | 03/04/2025 | 04/18/2025 | 46 | 0 | 46 |  |  | 5/2/2025 | Connected |  | N
National Grid | NEWBURY | 716020 | 01950 | 11.5 | Solar | 05_01_24W3 | 09/28/2025 | 10/06/2025 | 5 | 1 | 4 | 10/07/2025 | 10/07/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 177281 | 01886 | 1000 | Solar | 05_01_412L2 | 02/08/2017 | 02/17/2017 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2017 | 02/22/2017 | 2 | 0 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2018 | 02/08/2017 | 11/12/2021 | Y | STD | 571 | 02/06/2021 | 08/13/2021 | 189 | 0 | 189 | 8/16/2021 | 9/30/2021 | 11/2/2021 | Connected |  | N
National Grid | HAVERHILL | 417891 | 01832 | 6.528 | Solar | 05_01_55W1 | 04/29/2022 | 04/29/2022 | 0 | 0 | 0 | 05/02/2022 | 05/02/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2022 |  | 5/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2022 | Connected |  | N
National Grid | BILLERICA | 294047 | 01821 | 15.2 | Solar | 05_05_108W60 | 05/29/2020 | 06/04/2020 | 3 | 0 | 3 | 06/05/2020 | 06/05/2020 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2020 | Connected |  | N
National Grid | WORCESTER | 328171 | 01606 | 15.2 | Solar | 05_05_311W2 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 |  | 8/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2022 | Connected |  | N
National Grid | WEBSTER | 177207 | 01570 | 259.8 | Solar | 05_12_25W3 | 02/01/2017 | 02/01/2017 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 641444 | 01543 | 8.775 | Solar | 05_12_51T2 | 09/19/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 | 10/22/2024 | 10/25/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 10/25/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 10/30/2024 |  | 11/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 177596 | 01504 | 180 | Solar | 05_14_36L2 | 07/18/2017 | 07/18/2017 | 73 | 69 | 4 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2018 | 07/18/2017 | 8/31/2021 | Y | STD | 533 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 202799 | 01752 | 10 | Solar | 05_14_58L3 | 12/06/2018 | 12/14/2018 | 2 | 0 | 2 | 12/17/2018 | 12/17/2018 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2019 |  | 2/6/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2019 | Connected |  | N
National Grid | SAUGUS | 174576 | 01906 | 1000 | Solar | 05_14_74L1 | 04/01/2011 | 04/01/2011 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 06/22/2011 | 08/20/2012 | 289 | 0 | 289 | 05/04/2011 | 06/15/2011 | 29 | 0 | 29 | 08/20/2012 | 289 | 0 | 289 |  |  | 0 | 0 | 0 | 10/11/2012 | 04/01/2011 | 10/31/2012 | Y | STD | 20 | 05/14/2013 | 09/16/2013 | 85 | 0 | 85 | 7/9/2013 | 7/9/2013 | 7/25/2013 | Connected |  | N
National Grid | ESSEX | 652994 | 01929 | 7.6 | Solar | 05_14_92L2 | 11/08/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 | 11/08/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | NEWBURY | 755946 | 01950 | 15.2 | Solar | 05_01_24W3 | 03/11/2026 | 03/16/2026 | 3 | 0 | 3 | 03/17/2026 | 03/17/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTFORD | 178324 | 01886 | 2000 | Solar | 05_01_412L2 | 03/29/2018 | 04/09/2018 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2018 | 05/12/2018 | 25 | 10 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 504707 | 01844 | 10 | Solar | 05_01_55W1 | 03/28/2023 | 03/30/2023 | 2 | 0 | 2 | 03/31/2023 | 03/31/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 304759 | 01821 | 9.8 | Solar | 05_05_108W60 | 10/02/2020 | 10/15/2020 | 8 | 8 | 0 | 10/16/2020 | 10/16/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 10/02/2020 | 10/15/2021 | Y | EXP | 365 | 03/31/2021 | 05/21/2021 | 51 | 0 | 51 |  |  | 5/27/2021 | Connected |  | N
National Grid | WORCESTER | 449265 | 01606 | 10 | Solar | 05_05_311W2 | 08/12/2022 | 08/19/2022 | 5 | 4 | 1 | 08/22/2022 | 08/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 178123 | 01570 | 300 | Natural Gas | 05_12_25W3 | 05/12/2017 | 05/12/2017 | 22 | 19 | 3 | 06/14/2017 | 06/14/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2017 |  | 9/7/2018 | N | EXP | 423 |  |  | 0 | 0 | 0 |  |  | 8/14/2018 | Connected |  | N
National Grid | RUTLAND | 643245 | 01543 | 7.6 | Solar | 05_12_51T2 | 09/26/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 38 | 15 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 1/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | BLACKSTONE | 177863 | 01504 | 990 | Solar | 05_14_36L2 | 06/13/2017 | 06/13/2017 | 8 | 7 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2017 | 07/31/2017 | 24 | 9 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 | 06/13/2017 | 3/15/2024 | Y | STD | 753 | 05/29/2020 | 03/31/2021 | 306 | 5 | 301 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 247730 | 01752 | 10 | Solar | 05_14_58L3 | 08/12/2019 | 08/13/2019 | 0 | 0 | 0 | 08/14/2019 | 08/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 8/13/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2019 | Connected |  | N
National Grid | SAUGUS | 175052 | 01906 | 2000 | Solar | 05_14_74L1 | 07/20/2011 | 07/20/2011 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2011 | 09/13/2011 | 22 | 0 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2012 | 07/20/2011 | 6/30/2014 | Y | STD | 740 | 04/01/2014 | 06/18/2014 | 53 | 0 | 53 | 6/25/2014 | 6/25/2014 | 6/23/2014 | Connected |  | N
National Grid | ESSEX | 662574 | 01929 | 7.6 | Solar | 05_14_92L2 | 12/26/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 175256 | 01950 | 56 | Solar | 05_01_24W3 | 01/08/2015 | 01/08/2015 | 4 | 2 | 2 | 01/15/2015 | 01/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 9/17/2015 | Connected |  | N
National Grid | WESTFORD | 190340 | 01886 | 1500 | Solar | 05_01_412L2 | 08/16/2018 | 08/27/2018 | 3 | 0 | 3 |  |  | 53 | 19 | 34 |  |  | 0 | 0 | 0 | 09/13/2018 | 11/12/2018 | 42 | 8 | 34 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 506739 | 01844 | 6.96 | Solar | 05_01_55W1 | 03/08/2023 | 03/10/2023 | 2 | 0 | 2 | 03/13/2023 | 03/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 |  | 5/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2023 | Connected |  | N
National Grid | BILLERICA | 316764 | 01821 | 10 | Solar | 05_05_108W60 | 11/02/2020 | 11/04/2020 | 1 | 0 | 1 | 11/05/2020 | 11/05/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/02/2020 |  | Y | EXP | 0 | 02/09/2021 | 05/18/2021 | 98 | 0 | 98 |  |  | 6/2/2021 | Connected |  | N
National Grid | WORCESTER | 421735 | 01606 | 12 | Solar | 05_05_311W2 | 05/10/2022 | 05/12/2022 | 3 | 2 | 1 | 05/13/2022 | 05/13/2022 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2022 |  | 7/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2022 | Connected |  | N
National Grid | WEBSTER | 204173 | 01570 | 259.8 | Solar | 05_12_25W3 | 12/18/2018 | 01/17/2019 | 19 | 12 | 7 | 01/18/2019 | 01/18/2019 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 644917 | 01543 | 6 | Solar | 05_12_51T2 | 10/07/2024 | 10/28/2024 | 10 | 6 | 4 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/07/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | BLACKSTONE | 177940 | 01504 | 125 | Solar | 05_14_36L2 | 06/22/2017 | 06/22/2017 | 0 | 0 | 0 | 02/12/2018 | 02/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2018 | 06/22/2017 | 12/31/2019 | Y | EXP | 675 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N
National Grid | MARLBOROUGH | 263958 | 01752 | 0 | Solar | 05_14_58L3 | 11/05/2019 | 11/05/2019 | 0 | 0 | 0 | 11/06/2019 | 11/06/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 |  | 1/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2020 | Connected |  | N
National Grid | SAUGUS | 176057 | 01906 | 996 | Solar | 05_14_74L1 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 05/04/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2015 | 03/27/2015 | 8/1/2015 | Y | STD | 132 | 08/22/2017 | 01/31/2018 | 104 | 0 | 104 | 11/16/2017 | 11/16/2017 | 11/16/2017 | Connected |  | N
National Grid | HAMILTON | 668829 | 01982 | 3.9 | Solar | 05_14_92L2 | 02/06/2025 | 02/28/2025 | 10 | 6 | 4 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N
National Grid | NEWBURY | 175457 | 01950 | 56 | Solar | 05_01_24W3 | 07/17/2014 | 07/17/2014 | 3 | 0 | 3 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2014 |  | 11/28/2014 | N | EXP | 35 |  |  | 0 | 0 | 0 | 12/15/2014 | 12/15/2014 | 1/21/2016 | Connected |  | N
National Grid | WESTFORD | 190782 | 01886 | 23.04 | Solar | 05_01_412L2 | 07/16/2018 | 08/29/2018 | 31 | 0 | 31 | 08/30/2018 | 08/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 505628 | 01832 | 7.83 | Solar | 05_01_55W1 | 03/03/2023 | 03/07/2023 | 2 | 0 | 2 | 03/08/2023 | 03/08/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 03/03/2023 | 8/1/2024 | Y | EXP | 365 | 10/04/2023 | 10/16/2023 | 13 | 0 | 13 |  |  | 10/30/2023 | Connected |  | N
National Grid | BILLERICA | 321256 | 01821 | 7.6 | Solar | 05_05_108W60 | 10/23/2020 | 10/27/2020 | 1 | 0 | 1 | 10/28/2020 | 10/28/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 | 10/23/2020 | 10/27/2021 | Y | EXP | 365 | 02/05/2021 | 02/12/2021 | 7 | 0 | 7 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 424366 | 01606 | 0 | Solar | 05_05_311W2 | 04/22/2022 | 04/25/2022 | 2 | 1 | 1 | 04/26/2022 | 04/26/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 253386 | 01570 | 262.5 | Natural Gas | 05_12_25W3 | 09/24/2019 | 11/04/2019 | 27 | 24 | 3 | 11/05/2019 | 11/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 652283 | 01543 | 10 | Solar | 05_12_51T2 | 11/14/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/14/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 187091 | 02019 | 86.4 | Solar | 05_14_36L2 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 | 07/02/2018 | 07/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2018 |  | 7/1/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2018 | Connected |  | N
National Grid | MARLBOROUGH | 353145 | 01752 | 5.8 | Solar | 05_14_58L3 | 04/16/2021 | 05/10/2021 | 15 | 13 | 2 | 05/11/2021 | 05/11/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 5/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2021 | Connected |  | N
National Grid | SAUGUS | 176056 | 01906 | 980 | Solar | 05_14_74L1 | 03/27/2015 | 03/27/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 05/04/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2015 | N | STD | 0 | 08/22/2017 | 01/31/2018 | 104 | 0 | 104 |  |  |  | Withdrawn |  | N
National Grid | HAMILTON | 671980 | 01982 | 10 | Solar | 05_14_92L2 | 02/13/2025 | 03/18/2025 | 1 | 0 | 1 | 03/19/2025 | 03/19/2025 | 40 | 23 | 17 | 06/05/2025 | 06/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 06/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 7/1/2025 | 02/13/2025 | 7/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | NEWBURY | 175679 | 01950 | 30 | Solar | 05_01_24W3 | 12/18/2014 | 12/18/2014 | 6 | 1 | 5 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2015 |  | 2/28/2015 | N | EXP | 51 |  |  | 0 | 0 | 0 | 4/6/2015 | 4/6/2015 | 6/1/2015 | Connected |  | N
National Grid | WESTFORD | 196422 | 01886 | 66.6 | Solar | 05_01_412L2 | 09/19/2018 | 10/08/2018 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 |  | 6/30/2020 | N | EXP | 602 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 526469 | 01832 | 9.86 | Solar | 05_01_55W1 | 06/07/2023 | 06/08/2023 | 1 | 0 | 1 | 06/09/2023 | 06/09/2023 | 58 | 38 | 20 | 09/26/2023 | 11/20/2023 | 39 | 0 | 39 |  |  | 0 | 0 | 0 | 11/20/2023 | 39 | 0 | 39 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 3/4/2025 | N | EXP | 365 | 04/19/2024 | 05/14/2024 | 26 | 0 | 26 |  |  | 6/6/2024 | Connected |  | N
National Grid | BILLERICA | 325072 | 01821 | 0 | Solar | 05_05_108W60 | 11/13/2020 | 12/15/2020 | 20 | 17 | 3 | 12/16/2020 | 12/16/2020 | 67 | 46 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2021 |  | 4/5/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 441361 | 01606 | 15.2 | Solar | 05_05_311W2 | 06/30/2022 | 07/07/2022 | 4 | 3 | 1 | 07/08/2022 | 07/08/2022 | 79 | 51 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 302630 | 01570 | 262.5 | Natural Gas | 05_12_25W3 | 08/05/2020 | 09/30/2020 | 39 | 28 | 11 | 10/01/2020 | 10/01/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2020 |  | 2/21/2022 | N | EXP | 308 |  |  | 0 | 0 | 0 |  |  | 2/18/2022 | Connected |  | N
National Grid | RUTLAND | 652513 | 01543 | 13.05 | Solar | 05_12_51T2 | 11/13/2024 | 12/05/2024 | 1 | 0 | 1 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | BLACKSTONE | 210060 | 01504 | 7.6 | Solar | 05_14_36L2 | 03/19/2019 |  | 142 | 26 | 116 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 369368 | 01752 | 7.6 | Solar | 05_14_58L3 | 07/13/2021 | 08/24/2021 | 30 | 26 | 4 | 08/25/2021 | 08/25/2021 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 |  | 12/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2022 | Connected |  | N
National Grid | SAUGUS | 176913 | 01906 | 7.6 | Solar | 05_14_74L1 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 |  | 5/10/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMILTON | 680282 | 01982 | 10 | Solar | 05_14_92L2 | 03/25/2025 | 04/11/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 24 | 0 | 24 | 07/23/2025 | 09/08/2025 | 33 | 0 | 33 |  |  | 0 | 0 | 0 | 09/08/2025 | 33 | 0 | 33 |  |  | 0 | 0 | 0 | 9/10/2025 | 03/25/2025 | 9/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2025 | Connected |  | N
National Grid | NEWBURY | 175904 | 01950 | 10 | Solar | 05_01_24W3 | 09/18/2015 | 09/18/2015 | 0 | 0 | 0 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2015 |  | 10/6/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 10/13/2015 | 10/13/2015 | 1/26/2016 | Connected |  | N
National Grid | WESTFORD | 206984 | 01886 | 3.8 | Solar | 05_01_412L2 | 02/10/2019 | 02/19/2019 | 5 | 0 | 5 | 02/20/2019 | 02/20/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2019 | Connected |  | N
National Grid | METHUEN | 534007 | 01844 | 6 | Solar | 05_01_55W1 | 06/28/2023 | 06/30/2023 | 2 | 0 | 2 | 07/03/2023 | 07/03/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 344703 | 01821 | 6.72 | Solar | 05_05_108W60 | 03/24/2021 | 04/02/2021 | 6 | 6 | 0 | 04/05/2021 | 04/05/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2021 |  | 4/1/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 479117 | 01606 | 7.6 | Solar | 05_05_311W2 | 11/21/2022 | 11/22/2022 | 1 | 0 | 1 | 11/23/2022 | 11/23/2022 | 56 | 32 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2023 |  | 2/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 357487 | 01570 | 240 | Solar | 05_12_25W3 | 05/14/2021 | 06/23/2021 | 26 | 16 | 10 | 06/24/2021 | 06/24/2021 | 343 | 319 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 669106 | 01543 | 10 | Solar | 05_12_51T2 | 02/04/2025 | 02/26/2025 | 2 | 0 | 2 | 02/27/2025 | 02/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2025 | Connected |  | N
National Grid | BLACKSTONE | 243484 | 01504 | 53 | Solar | 05_14_36L2 | 07/15/2019 | 07/30/2019 | 11 | 3 | 8 | 07/31/2019 | 07/31/2019 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 401888 | 01752 | 15.2 | Solar | 05_14_58L3 | 12/17/2021 | 12/23/2021 | 5 | 3 | 2 | 12/24/2021 | 12/24/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 |  | 3/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 176972 | 01906 | 7.6 | Solar | 05_14_74L1 | 10/05/2016 | 10/05/2016 | 2 | 2 | 0 | 10/10/2016 | 10/10/2016 | 91 | 0 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2016 |  | 10/11/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 706418 | 01915 | 23 | Solar | 05_14_92L2 | 07/29/2025 | 08/04/2025 | 4 | 0 | 4 | 08/05/2025 | 08/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | NEWBURY | 176013 | 01950 | 17.6 | Solar | 05_01_24W3 | 01/23/2015 | 01/23/2015 | 8 | 6 | 2 | 02/05/2015 | 02/05/2015 | 175 | 0 | 175 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2015 |  | 6/30/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 2/24/2015 | 2/24/2015 |  | Withdrawn |  | N
National Grid | WESTFORD | 207611 | 01886 | 500 | Solar | 05_01_412L2 | 03/14/2019 | 04/30/2019 | 33 | 26 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2019 | 06/03/2019 | 23 | 5 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 536354 | 01844 | 5 | Solar | 05_01_55W1 | 06/28/2023 | 06/30/2023 | 3 | 1 | 2 | 07/03/2023 | 07/03/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 | 06/28/2023 | 8/30/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2023 | Connected |  | N
National Grid | BILLERICA | 373157 | 01821 | 3.8 | Solar | 05_05_108W60 | 08/06/2021 | 08/10/2021 | 2 | 0 | 2 | 08/11/2021 | 08/11/2021 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 |  | 4/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/3/2023 | Connected |  | N
National Grid | WORCESTER | 488924 | 01606 | 6.09 | Solar | 05_05_311W2 | 01/25/2023 | 01/31/2023 | 5 | 3 | 2 | 02/01/2023 | 02/01/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 |  | 3/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2023 | Connected |  | N
National Grid | WEBSTER | 419316 | 01570 | 240 | Solar | 05_12_25W3 | 05/26/2022 | 06/27/2022 | 20 | 14 | 6 | 06/28/2022 | 06/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2022 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2024 | Connected |  | N
National Grid | RUTLAND | 678202 | 01543 | 5.76 | Solar | 05_12_51T2 | 03/17/2025 | 03/24/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 | 03/17/2025 | 5/29/2026 | Y | EXP | 365 | 08/19/2025 | 11/05/2025 | 79 | 0 | 79 |  |  | 11/14/2025 | Connected |  | Y
National Grid | BELLINGHAM | 259475 | 02019 | 53 | Solar | 05_14_36L2 | 10/25/2019 | 11/18/2019 | 15 | 13 | 2 | 11/19/2019 | 11/19/2019 | 51 | 28 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2020 | Connected |  | N
National Grid | MARLBOROUGH | 401105 | 01752 | 0 | Other | 05_14_58L3 | 01/06/2022 | 01/19/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2022 | 02/10/2022 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 177164 | 01906 | 7.6 | Solar | 05_14_74L1 | 01/24/2017 | 01/24/2017 | 3 | 2 | 1 | 01/27/2017 | 01/27/2017 | 88 | 0 | 88 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2017 |  | 1/29/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 710015 | 01915 | 15.2 | Solar | 05_14_92L2 | 08/06/2025 | 08/12/2025 | 3 | 1 | 2 | 08/13/2025 | 08/13/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | NEWBURY | 176730 | 01950 | 6 | Solar | 05_01_24W3 | 04/25/2016 | 04/25/2016 | 2 | 2 | 0 | 04/28/2016 | 04/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2016 | 04/25/2016 | 5/1/2017 | Y | EXP | 355 |  |  | 0 | 0 | 0 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N
National Grid | WESTFORD | 226260 | 01886 | 150 | Solar | 05_01_412L2 | 05/08/2019 | 05/21/2019 | 7 | 0 | 7 | 05/22/2019 | 05/22/2019 | 21 | 9 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 561632 | 01844 | 7.6 | Solar | 05_01_55W1 | 10/13/2023 | 10/16/2023 | 1 | 0 | 1 | 10/17/2023 | 10/17/2023 | 68 | 45 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 | 10/13/2023 | 5/4/2025 | Y | EXP | 365 | 10/02/2024 | 10/10/2024 | 9 | 0 | 9 |  |  | 10/24/2024 | Connected |  | N
National Grid | BILLERICA | 376465 | 01821 | 15.2 | Solar | 05_05_108W60 | 08/17/2021 | 09/20/2021 | 23 | 22 | 1 | 09/21/2021 | 09/21/2021 | 176 | 153 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 517555 | 01606 | 15.2 | Solar | 05_05_311W2 | 04/06/2023 | 04/07/2023 | 1 | 0 | 1 | 04/10/2023 | 04/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 | 04/06/2023 | 5/10/2024 | Y | EXP | 365 | 07/04/2023 | 11/06/2023 | 126 | 0 | 126 |  |  | 11/14/2023 | Connected |  | N
National Grid | WEBSTER | 476349 | 01570 | 240 | Solar | 05_12_25W3 | 02/23/2023 | 08/22/2023 | 36 | 26 | 10 | 08/23/2023 | 08/23/2023 | 179 | 93 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 689316 | 01543 | 15.2 | Solar | 05_12_51T2 | 05/02/2025 | 05/22/2025 | 14 | 11 | 3 | 05/23/2025 | 05/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | BLACKSTONE | 270895 | 01504 | 10 | Solar | 05_14_36L2 | 12/31/2019 | 01/10/2020 | 6 | 0 | 6 | 01/13/2020 | 01/13/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 |  | 12/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2020 | Connected |  | N
National Grid | MARLBOROUGH | 402235 | 01752 | 0 | Solar | 05_14_58L3 | 12/20/2021 | 12/21/2021 | 1 | 0 | 1 | 12/22/2021 | 12/22/2021 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 | 12/20/2021 | 4/11/2023 | Y | EXP | 365 | 03/09/2022 | 04/11/2022 | 34 | 0 | 34 |  |  | 5/12/2022 | Connected |  | N
National Grid | SAUGUS | 177621 | 01906 | 15.2 | Solar | 05_14_74L1 | 11/09/2017 | 11/09/2017 | 11 | 10 | 1 | 11/29/2017 | 11/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 |  | 11/15/2018 | N | EXP | 520 |  |  | 0 | 0 | 0 |  |  | 10/2/2018 | Connected |  | N
National Grid | HAMILTON | 177716 | 01982 | 112 | Solar | 05_14_92L3 | 07/26/2017 | 07/26/2017 | 6 | 6 | 0 | 08/04/2017 | 08/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 8/1/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 | 1/24/2018 | 1/24/2018 | 1/24/2018 | Connected |  | N
National Grid | NEWBURY | 176780 | 01950 | 7.6 | Solar | 05_01_24W3 | 11/04/2015 | 11/04/2015 | 2 | 2 | 0 | 11/09/2015 | 11/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 |  | 11/10/2016 | N | EXP | 351 |  |  | 0 | 0 | 0 | 11/25/2015 | 11/25/2015 | 5/25/2016 | Connected |  | N
National Grid | WESTFORD | 293823 | 01886 | 8.88 | Solar | 05_01_412L2 | 05/28/2020 | 06/03/2020 | 3 | 0 | 3 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 5/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N
National Grid | METHUEN | 569867 | 01844 | 10 | Solar | 05_01_55W1 | 12/05/2023 | 12/07/2023 | 3 | 2 | 1 | 12/08/2023 | 12/08/2023 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2024 | Connected |  | N
National Grid | BILLERICA | 379282 | 01821 | 9.6 | Solar | 05_05_108W60 | 11/03/2021 | 12/16/2021 | 5 | 0 | 5 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/03/2021 | 7/28/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2022 | Connected |  | Y
National Grid | WORCESTER | 534257 | 01606 | 0 | Solar | 05_05_311W2 | 07/21/2023 | 07/26/2023 | 3 | 1 | 2 | 07/27/2023 | 07/27/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 10/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2024 | Connected |  | N
National Grid | DUDLEY | 488519 | 01571 | 480 | Solar | 05_12_25W3 | 02/24/2023 | 06/28/2023 | 85 | 74 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2023 | 07/27/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 691103 | 01543 | 15.2 | Solar | 05_12_51T2 | 06/02/2025 | 06/04/2025 | 2 | 0 | 2 | 06/05/2025 | 06/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | BELLINGHAM | 324647 | 02019 | 15.2 | Solar | 05_14_36L2 | 11/09/2020 | 11/12/2020 | 1 | 0 | 1 | 11/13/2020 | 11/13/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2021 | Connected |  | N
National Grid | MARLBOROUGH | 427118 | 01752 | 15.2 | Solar | 05_14_58L3 | 04/28/2022 | 06/09/2022 | 29 | 29 | 0 | 06/10/2022 | 06/10/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 04/28/2022 | 1/30/2024 | Y | EXP | 365 | 01/07/2023 | 01/30/2023 | 24 | 0 | 24 |  |  | 4/27/2023 | Connected |  | N
National Grid | SAUGUS | 177732 | 01906 | 8.32 | Solar | 05_14_74L1 | 03/22/2017 | 03/22/2017 | 27 | 27 | 0 | 05/01/2017 | 05/01/2017 | 126 | 0 | 126 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2017 |  | 3/27/2018 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMILTON | 644567 | 01982 | 10 | Solar | 05_14_92L3 | 10/02/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/02/2024 | 12/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N
National Grid | NEWBURY | 176779 | 01951 | 7.6 | Solar | 05_01_24W3 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 317070 | 01886 | 10 | Solar | 05_01_412L2 | 10/19/2020 | 11/03/2020 | 10 | 8 | 2 | 11/04/2020 | 11/04/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 4/11/2022 | N | EXP | 480 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 578149 | 01844 | 2.32 | Solar | 05_01_55W1 | 01/08/2024 | 01/10/2024 | 1 | 1 | 0 | 01/11/2024 | 01/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 |  | 2/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | BILLERICA | 412984 | 01821 | 3.8 | Solar | 05_05_108W60 | 02/17/2022 | 02/23/2022 | 3 | 0 | 3 | 02/24/2022 | 02/24/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  | 4/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/28/2022 | Connected |  | N
National Grid | WORCESTER | 538691 | 01606 | 11.05 | Solar | 05_05_311W2 | 10/09/2023 | 10/10/2023 | 1 | 0 | 1 | 10/11/2023 | 10/11/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 657521 | 01570 | 7.6 | Solar | 05_12_25W4 | 11/27/2024 | 02/05/2025 | 3 | 0 | 3 | 02/06/2025 | 02/06/2025 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | RUTLAND | 700744 | 01543 | 0 | Solar | 05_12_51T2 | 06/24/2025 | 06/30/2025 | 4 | 0 | 4 | 07/01/2025 | 07/01/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 | 06/24/2025 | 8/15/2026 | Y | EXP | 365 | 11/04/2025 | 11/18/2025 | 15 | 0 | 15 |  |  | 11/21/2025 | Connected |  | N
National Grid | BELLINGHAM | 354525 | 02019 | 100 | Solar | 05_14_36L2 | 05/27/2021 | 07/02/2021 | 24 | 14 | 10 | 07/06/2021 | 07/06/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2021 |  | 4/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 534351 | 01752 | 15.2 | Solar | 05_14_58L3 | 06/15/2023 | 06/27/2023 | 7 | 5 | 2 | 06/28/2023 | 06/28/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 8/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N
National Grid | MELROSE | 178372 | 02176 | 20 | Solar | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 44 | 0 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 2/15/2019 | N | EXP | 381 |  |  | 0 | 0 | 0 |  |  | 3/23/2019 | Connected |  | N
National Grid | HAMILTON | 646579 | 01982 | 10 | Solar | 05_14_92L3 | 10/18/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 176980 | 01950 | 6.6 | Solar | 05_01_24W3 | 12/29/2016 | 12/29/2016 | 1 | 1 | 0 | 01/04/2017 | 01/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2017 | 12/29/2016 | 1/7/2018 | Y | EXP | 366 | 06/07/2017 | 07/12/2017 | 24 | 0 | 24 | 9/28/2017 | 9/28/2017 | 9/28/2017 | Connected |  | N
National Grid | WESTFORD | 325654 | 01886 | 10 | Solar | 05_01_412L2 | 11/12/2020 | 01/25/2021 | 50 | 48 | 2 | 01/26/2021 | 01/26/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  | 1/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2021 | Connected |  | N
National Grid | METHUEN | 584251 | 01844 | 3.8 | Solar | 05_01_55W1 | 02/01/2024 | 02/05/2024 | 2 | 0 | 2 | 02/06/2024 | 02/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 420677 | 01821 | 6 | Solar | 05_05_108W60 | 04/04/2022 | 04/05/2022 | 1 | 0 | 1 | 04/06/2022 | 04/06/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 | 04/04/2022 | 1/27/2024 | Y | EXP | 365 | 06/11/2022 | 01/26/2023 | 230 | 0 | 230 |  |  | 2/14/2023 | Connected |  | Y
National Grid | WORCESTER | 562727 | 01606 | 0 | Battery Add-On | 05_05_311W2 | 10/13/2023 | 10/16/2023 | 1 | 0 | 1 | 10/17/2023 | 10/17/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 4/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2024 | Connected |  | N
National Grid | WEBSTER | 728422 | 01570 | 5.44 | Solar | 05_12_25W4 | 10/22/2025 | 10/27/2025 | 2 | 0 | 2 | 11/06/2025 | 11/06/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 10/22/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | RUTLAND | 708571 | 01543 | 9.86 | Solar | 05_12_51T2 | 07/30/2025 | 09/15/2025 | 32 | 29 | 3 | 09/16/2025 | 09/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | BELLINGHAM | 668934 | 02019 | 0 | Battery Add-On | 05_14_36L2 | 01/30/2025 | 03/14/2025 | 5 | 0 | 5 | 03/17/2025 | 03/17/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 554429 | 01752 | 0 | Battery Add-On | 05_14_58L3 | 10/20/2023 | 10/23/2023 | 1 | 0 | 1 | 10/24/2023 | 10/24/2023 | 69 | 48 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 178371 | 02176 | 20 | Solar | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 44 | 0 | 01/26/2018 | 01/26/2018 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 2/15/2019 | N | EXP | 381 |  |  | 0 | 0 | 0 |  |  | 5/24/2019 | Connected |  | N
National Grid | WENHAM | 648246 | 01984 | 10 | Solar | 05_14_92L3 | 10/18/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/18/2024 | 1/1/2026 | Y | EXP | 365 | 03/15/2025 | 03/24/2025 | 10 | 0 | 10 |  |  | 3/27/2025 | Connected |  | N
National Grid | NEWBURY | 193768 | 01950 | 10 | Solar | 05_01_24W3 | 08/17/2018 | 10/12/2018 | 7 | 7 | 0 | 10/15/2018 | 10/15/2018 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 440022 | 01886 | 3.77 | Solar | 05_01_412L2 | 07/15/2022 | 08/12/2022 | 21 | 20 | 1 | 08/15/2022 | 08/15/2022 | 63 | 44 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 |  | 11/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2023 | Connected |  | N
National Grid | METHUEN | 591901 | 01844 | 6 | Solar | 05_01_55W1 | 02/27/2024 | 02/29/2024 | 3 | 1 | 2 | 03/01/2024 | 03/01/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 | 02/27/2024 | 3/20/2025 | Y | EXP | 365 | 05/09/2024 | 06/14/2024 | 37 | 0 | 37 |  |  | 6/25/2024 | Connected |  | N
National Grid | BILLERICA | 425396 | 01821 | 10 | Solar | 05_05_108W60 | 06/16/2022 | 06/23/2022 | 5 | 3 | 2 | 06/24/2022 | 06/24/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 | 06/16/2022 | 2/2/2024 | Y | EXP | 365 | 10/12/2022 | 01/14/2023 | 95 | 0 | 95 |  |  | 5/23/2023 | Connected |  | Y
National Grid | WORCESTER | 581937 | 01606 | 5.376 | Solar | 05_05_311W2 | 01/23/2024 | 02/06/2024 | 11 | 10 | 1 | 02/07/2024 | 02/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/23/2024 | 4/1/2025 | Y | EXP | 365 | 04/30/2024 | 07/03/2024 | 65 | 0 | 65 |  |  | 12/5/2024 | Connected |  | N
National Grid | WEBSTER | 176158 | 01570 | 15.2 | Solar | 05_12_25W4 | 01/29/2015 | 01/29/2015 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 714207 | 01543 | 15.04 | Solar | 05_12_51T2 | 08/22/2025 | 09/16/2025 | 4 | 0 | 4 | 09/17/2025 | 09/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | BELLINGHAM | 701387 | 02019 | 17.6 | Solar | 05_14_36L2 | 07/03/2025 | 07/08/2025 | 2 | 0 | 2 | 07/09/2025 | 07/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | MARLBOROUGH | 650740 | 01752 | 8.376 | Solar | 05_14_58L3 | 10/30/2024 | 12/02/2024 | 10 | 5 | 5 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 10/30/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | MELROSE | 178370 | 02176 | 20 | Solar | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 44 | 0 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 11/26/2018 | N | EXP | 300 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | Connected |  | N
National Grid | BEVERLY | 670042 | 01915 | 10 | Solar | 05_14_92L3 | 02/11/2025 | 03/06/2025 | 3 | 0 | 3 | 03/07/2025 | 03/07/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | NEWBURY | 196491 | 01950 | 5 | Solar | 05_01_24W3 | 09/20/2018 | 10/24/2018 | 19 | 18 | 1 | 10/25/2018 | 10/25/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  | 10/31/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | Connected |  | N
National Grid | WESTFORD | 446153 | 01886 | 7.6 | Solar | 05_01_412L2 | 09/14/2022 | 10/11/2022 | 18 | 16 | 2 | 10/12/2022 | 10/12/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 09/14/2022 | 3/27/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 597641 | 01844 | 0 | Solar | 05_01_55W1 | 08/27/2024 | 09/03/2024 | 4 | 0 | 4 | 09/04/2024 | 09/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | BILLERICA | 469025 | 01821 | 3.8 | Solar | 05_05_108W60 | 10/21/2022 | 10/26/2022 | 4 | 1 | 3 | 10/27/2022 | 10/27/2022 | 33 | 20 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 599668 | 01606 | 11 | Solar | 05_05_311W2 | 04/24/2024 | 04/25/2024 | 1 | 0 | 1 | 04/26/2024 | 04/26/2024 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 5/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 177407 | 01570 | 56 | Solar | 05_12_25W4 | 09/09/2016 | 09/09/2016 | 17 | 17 | 0 | 10/04/2016 | 10/04/2016 | 60 | 60 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 7/31/2018 | N | EXP | 573 |  |  | 0 | 0 | 0 |  |  | 12/12/2018 | Connected |  | N
National Grid | RUTLAND | 729870 | 01543 | 9.28 | Solar | 05_12_51T2 | 11/02/2025 | 11/18/2025 | 10 | 5 | 5 | 11/19/2025 | 11/19/2025 | 78 | 64 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2026 |  | 3/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2026 | Connected |  | N
National Grid | BLACKSTONE | 710220 | 01504 | 26.6 | Solar | 05_14_36L2 | 08/06/2025 | 08/28/2025 | 16 | 14 | 2 | 08/29/2025 | 08/29/2025 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | MARLBOROUGH | 657428 | 01752 | 7.6 | Solar | 05_14_58L3 | 11/27/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | MELROSE | 178369 | 02176 | 20 | Solar | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 8 | 36 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 3/22/2019 | N | EXP | 416 |  |  | 0 | 0 | 0 |  |  | 3/23/2019 | Connected |  | N
National Grid | ESSEX | 197046 | 01929 | 2500 | Natural Gas | 05_14_92L4 | 10/04/2019 | 11/07/2019 | 23 | 19 | 4 |  |  | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2020 | 10/04/2019 | 5/5/2026 | Y | STD | 490 | 10/28/2020 | 09/23/2021 | 134 | 0 | 134 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 246025 | 01951 | 6 | Solar | 05_01_24W3 | 08/05/2019 | 08/20/2019 | 10 | 4 | 6 | 08/21/2019 | 08/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | WESTFORD | 458959 | 01886 | 3.8 | Solar | 05_01_412L2 | 11/02/2022 | 11/04/2022 | 3 | 1 | 2 | 11/07/2022 | 11/07/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 |  | 4/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | METHUEN | 608010 | 01844 | 11.7 | Solar | 05_01_55W1 | 05/02/2024 | 05/13/2024 | 3 | 1 | 2 | 05/14/2024 | 05/14/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 |  | 6/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 478954 | 01821 | 10 | Solar | 05_05_108W60 | 01/23/2023 | 01/24/2023 | 1 | 0 | 1 | 01/25/2023 | 01/25/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 | 01/23/2023 | 4/18/2024 | Y | EXP | 365 | 03/21/2023 | 04/19/2023 | 30 | 0 | 30 |  |  | 7/17/2023 | Connected |  | N
National Grid | WORCESTER | 609713 | 01606 | 10 | Solar | 05_05_311W2 | 05/08/2024 | 05/16/2024 | 6 | 5 | 1 | 05/17/2024 | 05/17/2024 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2024 | 05/08/2024 | 7/2/2025 | Y | EXP | 365 | 09/10/2024 | 10/16/2024 | 37 | 0 | 37 |  |  | 2/28/2025 | Connected |  | N
National Grid | WEBSTER | 191843 | 01570 | 50 | Solar | 05_12_25W4 | 08/21/2018 | 09/17/2018 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2019 |  | 11/29/2019 | N | EXP | 239 |  |  | 0 | 0 | 0 |  |  | 11/19/2019 | Connected |  | N
National Grid | RUTLAND | 703588 | 01543 | 0 | Solar | 05_12_51T3 | 07/08/2025 | 07/14/2025 | 3 | 1 | 2 | 07/15/2025 | 07/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BLACKSTONE | 558936 | 01504 | 240 | Solar | 05_14_3J4 | 09/29/2023 | 10/23/2023 | 15 | 6 | 9 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 | 09/29/2023 | 7/8/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | MARLBOROUGH | 663371 | 01752 | 17.6 | Solar | 05_14_58L3 | 01/02/2025 | 01/06/2025 | 3 | 1 | 2 | 01/07/2025 | 01/07/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 01/02/2025 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | MELROSE | 178489 | 02176 | 7 | Solar | 05_14_74L1 | 11/30/2017 | 11/30/2017 | 0 | 0 | 0 | 01/04/2018 | 01/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 |  | 12/6/2018 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N
National Grid | ROCKPORT | 174891 | 01966 | 990 | Solar | 05_14_92L4 | 08/14/2013 | 08/14/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 10/22/2013 | 11/22/2013 | 22 | 0 | 22 | 08/23/2013 | 10/01/2013 | 26 | 0 | 26 | 11/22/2013 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 12/2/2013 |  | 12/31/2013 | N | STD | 29 |  |  | 0 | 0 | 0 | 12/28/2013 | 12/28/2013 | 12/31/2013 | Connected |  | N
National Grid | LOWELL | 283927 | 01852 | 10 | Solar | 05_01_24W3 | 04/28/2020 | 04/29/2020 | 1 | 1 | 0 | 04/30/2020 | 04/30/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 | 04/28/2020 | 4/28/2021 | Y | EXP | 365 | 11/07/2020 | 01/06/2021 | 60 | 0 | 60 |  |  | 1/8/2021 | Connected |  | N
National Grid | WESTFORD | 482139 | 01886 | 0 | Battery Add-On | 05_01_412L2 | 12/02/2022 | 12/06/2022 | 2 | 0 | 2 | 12/07/2022 | 12/07/2022 | 58 | 25 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 616463 | 01844 | 5.76 | Solar | 05_01_55W1 | 06/07/2024 | 07/01/2024 | 2 | 0 | 2 | 07/02/2024 | 07/02/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 480519 | 01821 | 0 | Solar | 05_05_108W60 | 11/28/2022 | 11/29/2022 | 2 | 1 | 1 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 2/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2023 | Connected |  | N
National Grid | WORCESTER | 611935 | 01606 | 20 | Solar | 05_05_311W2 | 05/22/2024 | 06/24/2024 | 21 | 20 | 1 | 06/25/2024 | 06/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | WEBSTER | 206824 | 01570 | 0 | Solar | 05_12_25W4 | 01/25/2019 | 02/11/2019 | 10 | 0 | 10 | 02/12/2019 | 02/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2019 | Connected |  | N
National Grid | RUTLAND | 738933 | 01543 | 10 | Solar | 05_12_51T3 | 12/09/2025 | 12/10/2025 | 1 | 0 | 1 | 12/11/2025 | 12/11/2025 | 44 | 24 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BLACKSTONE | 735290 | 01504 | 17.6 | Solar | 05_14_3J4 | 11/24/2025 | 12/01/2025 | 4 | 0 | 4 | 12/02/2025 | 12/02/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2026 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MARLBOROUGH | 698097 | 01752 | 9.5 | Solar | 05_14_58L3 | 06/12/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 72 | 47 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2026 | Connected |  | N
National Grid | MELROSE | 178539 | 02176 | 7.6 | Solar | 05_14_74L1 | 01/26/2018 | 01/26/2018 | 9 | 1 | 8 | 02/08/2018 | 02/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 | 01/26/2018 | 1/31/2019 | Y | EXP | 356 | 06/12/2018 | 06/21/2018 | 9 | 0 | 9 |  |  | 8/20/2018 | Connected |  | N
National Grid | GLOUCESTER | 201405 | 01930 | 15.2 | Solar | 05_14_92L4 | 11/16/2018 | 11/21/2018 | 3 | 3 | 0 | 11/26/2018 | 11/26/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 |  | 11/16/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 368621 | 01852 | 6 | Solar | 05_01_24W3 | 08/19/2021 | 12/31/2021 | 4 | 2 | 2 | 08/27/2021 | 08/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 516396 | 01886 | 12.76 | Solar | 05_01_412L2 | 08/17/2023 | 09/07/2023 | 15 | 14 | 1 | 09/08/2023 | 09/08/2023 | 24 | 0 | 24 | 11/22/2023 | 01/17/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 | 01/17/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 | 1/22/2024 |  | 2/19/2025 | N | EXP | 365 | 04/13/2024 | 05/28/2024 | 46 | 0 | 46 |  |  | 5/30/2024 | Connected |  | N
National Grid | METHUEN | 634556 | 01844 | 8.775 | Solar | 05_01_55W1 | 08/22/2024 | 09/03/2024 | 4 | 1 | 3 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 9/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | BILLERICA | 489055 | 01821 | 10 | Solar | 05_05_108W60 | 01/23/2023 | 01/25/2023 | 2 | 0 | 2 | 01/26/2023 | 01/26/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 624368 | 01606 | 10 | Solar | 05_05_311W2 | 07/12/2024 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 447514 | 01570 | 15.66 | Solar | 05_12_25W4 | 08/25/2022 | 09/13/2022 | 13 | 12 | 1 | 09/14/2022 | 09/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2022 |  | 10/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2023 | Connected |  | N
National Grid | RUTLAND | 757517 | 01543 | 10 | Solar | 05_12_51T3 | 03/20/2026 | 03/24/2026 | 2 | 0 | 2 | 03/25/2026 | 03/25/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BELLINGHAM | 397015 | 02019 | 200 | Solar | 05_14_3J4 | 11/24/2021 | 12/06/2021 | 7 | 0 | 7 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2022 |  | 6/2/2023 | N | STD | 65 |  |  | 0 | 0 | 0 |  |  | 5/24/2023 | Connected |  | N
National Grid | MARLBOROUGH | 729434 | 01752 | 5.76 | Solar | 05_14_58L3 | 10/27/2025 | 10/29/2025 | 3 | 0 | 3 | 12/05/2025 | 12/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 186105 | 02176 | 15.2 | Solar | 05_14_74L1 | 05/23/2018 | 05/23/2018 | 3 | 0 | 3 | 05/31/2018 | 05/31/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 372447 | 01966 | 9.8 | Solar | 05_14_92L4 | 08/05/2021 | 12/10/2021 | 2 | 1 | 1 | 08/09/2021 | 08/09/2021 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2022 | Connected |  | N
National Grid | LOWELL | 443258 | 01852 | 7.6 | Solar | 05_01_24W3 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 | 07/19/2022 | 2/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | WESTFORD | 517386 | 01886 | 3 | Solar | 05_01_412L2 | 05/17/2023 | 06/12/2023 | 18 | 18 | 0 | 06/13/2023 | 06/13/2023 | 20 | 0 | 20 | 08/09/2023 | 09/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 09/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 9/29/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 637398 | 01844 | 5.8 | Solar | 05_01_55W1 | 09/03/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N
National Grid | BILLERICA | 491574 | 01821 | 20 | Solar | 05_05_108W60 | 01/11/2023 | 01/13/2023 | 3 | 2 | 1 | 01/17/2023 | 01/17/2023 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 | 01/11/2023 | 3/2/2024 | Y | EXP | 365 | 03/21/2023 | 04/22/2023 | 33 | 0 | 33 |  |  | 6/26/2023 | Connected |  | N
National Grid | WORCESTER | 663953 | 01606 | 10 | Solar | 05_05_311W2 | 01/06/2025 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2026 | Connected |  | N
National Grid | DUDLEY | 475633 | 01570 | 50 | Solar | 05_12_25W4 | 11/10/2022 | 11/23/2022 | 8 | 0 | 8 | 11/25/2022 | 11/25/2022 | 44 | 24 | 20 | 02/02/2023 | 03/22/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 03/22/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 11/29/2024 | N | EXP | 365 | 10/21/2023 | 12/05/2023 | 46 | 0 | 46 |  |  | 8/23/2024 | Connected |  | N
National Grid | RUTLAND | 175636 | 01543 | 45 | Solar | 05_12_51T3 | 10/19/2014 | 10/19/2014 | 6 | 2 | 4 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 1/15/2015 | 1/15/2015 | 2/13/2015 | Connected |  | N
National Grid | BLACKSTONE | 174366 | 01504 | 45.6 | Solar | 05_14_3J40 | 05/21/2012 | 05/21/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2012 |  | 8/1/2012 | N | EXP | 2 |  |  | 0 | 0 | 0 | 10/1/2012 | 10/1/2012 | 10/19/2012 | Connected |  | N
National Grid | MARLBOROUGH | 551107 | 01752 | 240 | Solar | 05_14_59L1 | 01/05/2024 | 02/07/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2024 | 02/23/2024 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | MELROSE | 187541 | 02176 | 11.4 | Solar | 05_14_74L1 | 06/08/2018 | 06/08/2018 | 10 | 0 | 10 | 06/25/2018 | 06/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  | 6/8/2020 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  | 6/5/2020 | Connected |  | N
National Grid | GLOUCESTER | 465206 | 01930 | 15.2 | Solar | 05_14_92L4 | 10/02/2022 | 10/05/2022 | 4 | 3 | 1 | 10/06/2022 | 10/06/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2022 |  | 11/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2023 | Connected |  | N
National Grid | ANDOVER | 476456 | 01810 | 6 | Solar | 05_01_24W3 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 2/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | ANDOVER | 520273 | 01810 | 14.79 | Solar | 05_01_412L2 | 04/20/2023 | 04/24/2023 | 3 | 2 | 1 | 04/25/2023 | 04/25/2023 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  | 9/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2023 | Connected |  | N
National Grid | METHUEN | 644740 | 01844 | 9.9 | Solar | 05_01_55W1 | 10/03/2024 | 11/14/2024 | 12 | 9 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/03/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | BILLERICA | 503144 | 01821 | 6 | Solar | 05_05_108W60 | 03/28/2023 | 03/30/2023 | 2 | 0 | 2 | 03/31/2023 | 03/31/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/28/2023 | 5/21/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 666520 | 01606 | 0 | Battery Add-On | 05_05_311W2 | 02/06/2025 | 02/19/2025 | 8 | 3 | 5 | 02/20/2025 | 02/20/2025 | 57 | 39 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | WEBSTER | 491299 | 01570 | 6.48 | Solar | 05_12_25W4 | 01/20/2023 | 01/24/2023 | 2 | 0 | 2 | 01/25/2023 | 01/25/2023 | 21 | 0 | 21 | 03/28/2023 | 06/27/2023 | 63 | 0 | 63 |  |  | 0 | 0 | 0 | 06/27/2023 | 63 | 0 | 63 |  |  | 0 | 0 | 0 | 7/24/2023 |  | 11/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2023 | Connected |  | N
National Grid | RUTLAND | 175788 | 01543 | 200 | Solar | 05_12_51T3 | 09/17/2015 | 09/17/2015 | 0 | 0 | 0 | 09/18/2015 | 09/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/17/2015 | 9/23/2016 | Y | EXP | 366 |  |  | 0 | 0 | 0 | 4/15/2016 | 4/15/2016 | 5/3/2016 | Connected |  | N
National Grid | BELLINGHAM | 174644 | 02019 | 18 | Solar | 05_14_3J40 | 12/17/2013 | 12/17/2013 | 5 | 0 | 5 | 12/27/2013 | 12/27/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2014 |  | 2/28/2014 | N | EXP | 57 |  |  | 0 | 0 | 0 | 1/13/2014 | 1/13/2014 | 4/25/2014 | Connected |  | N
National Grid | MARLBOROUGH | 174889 | 01752 | 20 | Solar | 05_14_59L1 | 08/13/2013 | 08/13/2013 | 7 | 0 | 7 | 08/23/2013 | 08/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2013 |  | 9/25/2013 | N | EXP | 9 |  |  | 0 | 0 | 0 | 12/9/2013 | 12/9/2013 | 2/10/2014 | Connected |  | N
National Grid | MELROSE | 205269 | 02176 | 1500 | Solar | 05_14_74L1 | 01/04/2019 | 02/08/2019 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/11/2019 | 03/06/2019 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 705471 | 01930 | 13.36 | Solar | 05_14_92L4 | 07/21/2025 | 08/21/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 54 | 39 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 502075 | 01810 | 7.68 | Solar | 05_01_24W3 | 03/06/2023 | 03/08/2023 | 2 | 1 | 1 | 03/09/2023 | 03/09/2023 | 25 | 0 | 25 | 05/12/2023 | 06/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 06/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 6/13/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 521145 | 01810 | 0 | Solar | 05_01_412L2 | 07/19/2023 | 07/20/2023 | 2 | 1 | 1 | 07/21/2023 | 07/21/2023 | 151 | 130 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2024 | Connected |  | N
National Grid | METHUEN | 655165 | 01844 | 5.76 | Solar | 05_01_55W1 | 11/20/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 44 | 19 | 25 | 03/28/2025 | 06/12/2025 | 53 | 0 | 53 |  |  | 0 | 0 | 0 | 06/12/2025 | 53 | 0 | 53 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 7/8/2026 | N | EXP | 365 | 11/11/2025 | 12/22/2025 | 42 | 0 | 42 |  |  | 12/4/2025 | Connected |  | N
National Grid | BILLERICA | 508947 | 01821 | 10 | Solar | 05_05_108W60 | 03/20/2023 | 03/21/2023 | 1 | 0 | 1 | 03/22/2023 | 03/22/2023 | 52 | 31 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  | 6/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | WORCESTER | 667203 | 01606 | 0 | Solar | 05_05_311W2 | 01/23/2025 | 02/13/2025 | 9 | 4 | 5 | 02/14/2025 | 02/14/2025 | 29 | 8 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | WEBSTER | 536960 | 01570 | 10 | Solar | 05_12_25W4 | 07/10/2023 | 07/11/2023 | 1 | 0 | 1 | 07/12/2023 | 07/12/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 176028 | 01543 | 30.25 | Solar | 05_12_51T3 | 06/16/2015 | 06/16/2015 | 4 | 4 | 0 | 06/23/2015 | 06/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/21/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 12/20/2016 | 12/20/2016 | 12/20/2016 | Connected |  | N
National Grid | BLACKSTONE | 479312 | 01504 | 15.2 | Solar | 05_14_3J41 | 11/21/2022 | 11/23/2022 | 2 | 0 | 2 | 11/25/2022 | 11/25/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2023 | Connected |  | N
National Grid | MARLBOROUGH | 174978 | 01752 | 950 | Solar | 05_14_59L1 | 09/13/2011 | 09/13/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/13/2011 | 11/30/2012 | Y | STD | 12 | 04/11/2013 | 12/14/2013 | 169 | 0 | 169 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N
National Grid | MELROSE | 208621 | 02176 | 900 | Solar | 05_14_74L1 | 03/27/2019 | 04/20/2019 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2019 | 05/17/2019 | 20 | 4 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/15/2021 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 702356 | 01930 | 20 | Solar | 05_14_92L6 | 07/02/2025 | 08/04/2025 | 13 | 11 | 2 | 08/05/2025 | 08/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ANDOVER | 576736 | 01810 | 6 | Solar | 05_01_24W3 | 01/03/2024 | 01/08/2024 | 3 | 1 | 2 | 01/09/2024 | 01/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 01/03/2024 | 3/4/2025 | Y | EXP | 365 | 04/24/2024 | 09/05/2024 | 135 | 0 | 135 |  |  | 9/10/2024 | Connected |  | N
National Grid | TEWKSBURY | 545472 | 01876 | 5.8 | Solar | 05_01_412L2 | 08/08/2023 | 08/28/2023 | 15 | 14 | 1 | 08/29/2023 | 08/29/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 | 08/08/2023 | 10/11/2024 | Y | EXP | 365 | 01/16/2024 | 02/08/2024 | 24 | 0 | 24 |  |  | 2/22/2024 | Connected |  | N
National Grid | METHUEN | 660326 | 01844 | 7.6 | Solar | 05_01_55W1 | 12/12/2024 | 01/07/2025 | 8 | 6 | 2 | 01/08/2025 | 01/08/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | BILLERICA | 525114 | 01821 | 0 | Solar | 05_05_108W60 | 05/11/2023 | 07/18/2023 | 45 | 42 | 3 | 05/01/2024 | 05/01/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 |  | 5/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 727052 | 01606 | 7.6 | Solar | 05_05_311W2 | 10/16/2025 | 10/21/2025 | 3 | 0 | 3 | 10/22/2025 | 10/22/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 613279 | 01570 | 6.825 | Solar | 05_12_25W4 | 05/28/2024 | 06/12/2024 | 1 | 0 | 1 | 06/13/2024 | 06/13/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 | 05/28/2024 | 7/19/2025 | Y | EXP | 365 | 09/19/2024 | 10/28/2024 | 40 | 0 | 40 |  |  | 5/14/2025 | Connected |  | N
National Grid | RUTLAND | 176270 | 01543 | 17.42 | Solar | 05_12_51T3 | 02/18/2015 | 02/18/2015 | 4 | 0 | 4 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 7/31/2015 | N | EXP | 154 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 6/30/2015 | Connected |  | N
National Grid | BLACKSTONE | 577657 | 01504 | 23 | Solar | 05_14_3J44 | 12/13/2023 | 12/18/2023 | 3 | 2 | 1 | 12/19/2023 | 12/19/2023 | 83 | 28 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 174979 | 01752 | 950 | Solar | 05_14_59L1 | 09/13/2011 | 09/13/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/13/2011 | 11/30/2012 | Y | STD | 12 | 04/11/2013 | 12/14/2013 | 169 | 0 | 169 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N
National Grid | MELROSE | 208566 | 02176 | 3.8 | Solar | 05_14_74L1 | 02/18/2019 | 02/28/2019 | 7 | 0 | 7 | 03/01/2019 | 03/01/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 752916 | 01930 | 11.4 | Solar | 05_14_92L6 | 02/24/2026 | 02/27/2026 | 3 | 0 | 3 | 03/02/2026 | 03/02/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ANDOVER | 591330 | 01810 | 3.8 | Solar | 05_01_24W3 | 02/26/2024 | 03/05/2024 | 6 | 0 | 6 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 02/26/2024 | 4/6/2025 | Y | EXP | 365 | 07/16/2024 | 09/11/2024 | 58 | 0 | 58 |  |  | 9/20/2024 | Connected |  | N
National Grid | TEWKSBURY | 547164 | 01876 | 3.8 | Solar | 05_01_412L2 | 09/13/2023 | 09/20/2023 | 5 | 2 | 3 | 09/21/2023 | 09/21/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  | 11/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2024 | Connected |  | N
National Grid | METHUEN | 669686 | 01844 | 7.6 | Solar | 05_01_55W1 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 140 | 123 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 563891 | 01821 | 3.8 | Solar | 05_05_108W60 | 10/30/2023 | 12/29/2023 | 42 | 37 | 5 | 01/02/2024 | 01/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 |  | 2/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N
National Grid | WORCESTER | 587963 | 01606 | 325 | Natural Gas | 05_05_311W3 | 02/23/2024 | 08/02/2024 | 111 | 101 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2024 | 08/27/2024 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 7/29/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 640889 | 01570 | 9 | Solar | 05_12_25W4 | 09/18/2024 | 11/01/2024 | 17 | 11 | 6 | 11/04/2024 | 11/04/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | RUTLAND | 176530 | 01543 | 108 | Solar | 05_12_51T3 | 12/16/2015 | 12/16/2015 | 0 | 0 | 0 | 12/17/2015 | 12/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2016 |  | 12/22/2016 | N | EXP | 353 |  |  | 0 | 0 | 0 | 8/19/2016 | 8/19/2016 | 8/19/2016 | Connected |  | N
National Grid | BLACKSTONE | 646072 | 01504 | 7.6 | Solar | 05_14_3J44 | 10/10/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 10/10/2024 | 1/14/2026 | Y | EXP | 365 | 03/27/2025 | 05/07/2025 | 42 | 0 | 42 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175015 | 01752 | 950 | Solar | 05_14_59L1 | 08/29/2011 | 08/29/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/19/2011 | 11/03/2011 | 33 | 0 | 33 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 08/29/2011 | 11/30/2012 | Y | STD | 12 | 04/11/2013 | 12/14/2013 | 169 | 0 | 169 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N
National Grid | MELROSE | 277815 | 02176 | 7.6 | Solar | 05_14_74L1 | 03/03/2020 | 03/09/2020 | 3 | 0 | 3 | 03/10/2020 | 03/10/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2020 | 03/03/2020 |  | Y | EXP | 365 | 02/06/2021 | 02/12/2021 | 6 | 0 | 6 |  |  | 4/27/2021 | Connected |  | N
National Grid | GLOUCESTER | 174140 | 01930 | 82.3 | Solar | 05_14_92L6 | 04/11/2012 | 04/11/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2012 |  | 7/6/2012 | N | EXP | 31 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 12/27/2012 | Connected |  | N
National Grid | ANDOVER | 624975 | 01810 | 3.8 | Solar | 05_01_24W3 | 07/15/2024 | 07/22/2024 | 1 | 0 | 1 | 07/23/2024 | 07/23/2024 | 31 | 20 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 549203 | 01810 | 12 | Solar | 05_01_412L2 | 09/05/2023 | 11/14/2023 | 49 | 46 | 3 | 11/15/2023 | 11/15/2023 | 68 | 36 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 671268 | 01844 | 5.76 | Solar | 05_01_55W1 | 02/11/2025 | 03/10/2025 | 4 | 0 | 4 | 03/11/2025 | 03/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 5/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | BILLERICA | 580770 | 01821 | 7.296 | Solar | 05_05_108W60 | 02/23/2024 | 03/01/2024 | 6 | 2 | 4 | 03/04/2024 | 03/04/2024 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 02/23/2024 | 6/17/2025 | Y | EXP | 365 | 04/30/2024 | 05/08/2024 | 9 | 0 | 9 |  |  | 11/15/2024 | Connected |  | N
National Grid | WORCESTER | 676908 | 01606 | 3.8 | Solar | 05_05_311W3 | 03/10/2025 | 03/22/2025 | 17 | 13 | 4 | 04/29/2025 | 04/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 03/10/2025 | 6/10/2026 | Y | EXP | 365 | 07/19/2025 | 09/18/2025 | 62 | 0 | 62 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 645195 | 01570 | 7.6 | Solar | 05_12_25W4 | 10/25/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 177374 | 01543 | 345 | Solar | 05_12_51T3 | 09/08/2016 | 09/08/2016 | 2 | 2 | 0 | 09/12/2016 | 09/12/2016 | 361 | 2 | 359 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2016 |  | 6/29/2018 | N | EXP | 640 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 662149 | 01504 | 5.76 | Solar | 05_14_3J45 | 12/23/2024 | 01/15/2025 | 1 | 0 | 1 | 01/15/2025 | 01/15/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 12/23/2024 | 2/26/2026 | Y | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175240 | 01752 | 15.2 | Solar | 05_14_59L1 | 08/21/2014 | 08/21/2014 | 7 | 0 | 7 | 09/03/2014 | 09/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 11/28/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 12/8/2014 | Connected |  | N
National Grid | MELROSE | 283578 | 02176 | 9.57 | Solar | 05_14_74L1 | 06/17/2020 | 06/19/2020 | 1 | 0 | 1 | 06/22/2020 | 06/22/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/17/2020 | 6/17/2021 | Y | EXP | 365 | 02/10/2021 | 04/09/2021 | 58 | 0 | 58 |  |  | 4/13/2021 | Connected |  | N
National Grid | GLOUCESTER | 175938 | 01930 | 16 | Solar | 05_14_92L6 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 | 01/29/2015 | 01/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 |  | 5/31/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 6/15/2016 | Connected |  | N
National Grid | ANDOVER | 637116 | 01810 | 5.76 | Solar | 05_01_24W3 | 09/02/2024 | 09/12/2024 | 2 | 0 | 2 | 09/13/2024 | 09/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 551576 | 01810 | 4.64 | Solar | 05_01_412L2 | 09/19/2023 | 09/22/2023 | 3 | 0 | 3 | 09/25/2023 | 09/25/2023 | 20 | 0 | 20 | 11/13/2023 | 03/15/2024 | 58 | 41 | 17 |  |  | 0 | 0 | 0 | 03/15/2024 | 58 | 41 | 17 |  |  | 0 | 0 | 0 | 2/13/2024 |  | 2/18/2025 | N | EXP | 365 | 04/13/2024 | 05/22/2024 | 40 | 0 | 40 |  |  | 6/10/2024 | Connected |  | N
National Grid | METHUEN | 671566 | 01844 | 10 | Solar | 05_01_55W1 | 02/11/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/11/2025 | 5/25/2026 | Y | EXP | 365 | 08/28/2025 | 12/01/2025 | 96 | 0 | 96 |  |  | 1/16/2026 | Connected |  | N
National Grid | BILLERICA | 585799 | 01821 | 6 | Solar | 05_05_108W60 | 02/07/2024 | 02/14/2024 | 5 | 0 | 5 | 02/15/2024 | 02/15/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 716400 | 01606 | 17.6 | Solar | 05_05_311W3 | 09/08/2025 | 09/11/2025 | 3 | 0 | 3 | 09/12/2025 | 09/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 10/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 647977 | 01570 | 6.67 | Solar | 05_12_25W4 | 10/17/2024 | 11/26/2024 | 6 | 1 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | RUTLAND | 177959 | 01543 | 20 | Solar | 05_12_51T3 | 10/24/2017 | 10/24/2017 | 2 | 0 | 2 | 11/06/2017 | 11/06/2017 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 10/31/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | BELLINGHAM | 488581 | 02019 | 300 | Solar | 05_14_3J5 | 02/24/2023 |  | 302 | 204 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 177624 | 01752 | 15.2 | Solar | 05_14_59L1 | 11/09/2017 | 11/09/2017 | 1 | 0 | 1 | 12/05/2017 | 12/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2017 |  | 11/15/2018 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N
National Grid | MELROSE | 321316 | 02176 | 7.6 | Solar | 05_14_74L1 | 11/04/2020 | 11/09/2020 | 2 | 0 | 2 | 11/10/2020 | 11/10/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 176225 | 01930 | 7.6 | Solar | 05_14_92L6 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/01/2015 | 9/12/2016 | Y | EXP | 355 | 05/06/2016 | 09/02/2016 | 82 | 0 | 82 | 9/23/2015 | 9/23/2015 | 9/13/2016 | Connected |  | N
National Grid | LOWELL | 638002 | 01852 | 3.8 | Solar | 05_01_24W3 | 09/05/2024 | 09/19/2024 | 3 | 0 | 3 | 09/20/2024 | 09/20/2024 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | ANDOVER | 613016 | 01810 | 6 | Solar | 05_01_412L2 | 05/23/2024 | 06/11/2024 | 9 | 5 | 4 | 06/12/2024 | 06/12/2024 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 05/23/2024 | 1/26/2026 | Y | EXP | 365 | 09/04/2024 | 09/26/2024 | 23 | 0 | 23 |  |  | 3/26/2025 | Connected |  | N
National Grid | METHUEN | 679462 | 01844 | 11.52 | Solar | 05_01_55W1 | 03/25/2025 | 09/15/2025 | 29 | 25 | 4 | 09/16/2025 | 09/16/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | BILLERICA | 587149 | 01821 | 7.6 | Solar | 05_05_108W60 | 03/26/2024 | 04/17/2024 | 15 | 13 | 2 | 04/18/2024 | 04/18/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 | 03/26/2024 | 5/3/2025 | Y | EXP | 365 | 05/11/2024 | 05/10/2024 | 0 | 0 | 0 |  |  | 10/3/2024 | Connected |  | N
National Grid | WORCESTER | 718553 | 01606 | 4995 | Other | 05_05_311W3 | 09/29/2025 | 10/30/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 | 12/01/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WEBSTER | 648629 | 01570 | 7.6 | Solar | 05_12_25W4 | 10/22/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/22/2024 | 3/7/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 6/21/2025 | Connected |  | N
National Grid | RUTLAND | 186691 | 01543 | 6 | Solar | 05_12_51T3 | 06/15/2018 | 06/15/2018 | 9 | 5 | 4 | 06/29/2018 | 06/29/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  | 5/30/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 11/16/2018 | Connected |  | N
National Grid | BLACKSTONE | 707495 | 01504 | 10 | Solar | 05_14_3J7 | 07/25/2025 | 09/12/2025 | 4 | 0 | 4 | 09/22/2025 | 09/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 | 07/25/2025 | 10/24/2026 | Y | EXP | 365 | 12/18/2025 |  | 105 | 0 | 105 |  |  |  | Construction |  | N
National Grid | MARLBOROUGH | 247404 | 01752 | 0 | Solar | 05_14_59L1 | 08/07/2019 | 08/07/2019 | 0 | 0 | 0 | 08/08/2019 | 08/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 |  | 10/11/2019 | N | EXP | 57 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | MELROSE | 323842 | 02176 | 9.8 | Solar | 05_14_74L1 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 176469 | 01930 | 10 | Solar | 05_14_92L6 | 03/17/2016 | 03/17/2016 | 2 | 2 | 0 | 03/22/2016 | 03/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/17/2016 | 3/23/2017 | Y | EXP | 345 | 06/21/2016 | 07/29/2016 | 27 | 0 | 27 | 9/20/2016 | 9/20/2016 | 9/23/2016 | Connected |  | N
National Grid | LOWELL | 639629 | 01852 | 10 | Solar | 05_01_24W3 | 09/12/2024 | 09/20/2024 | 5 | 2 | 3 | 09/23/2024 | 09/23/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | ANDOVER | 613403 | 01810 | 6.67 | Solar | 05_01_412L2 | 05/28/2024 | 06/03/2024 | 1 | 0 | 1 | 06/04/2024 | 06/04/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/28/2024 | 7/1/2025 | Y | EXP | 365 | 09/19/2024 | 09/18/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 683396 | 01844 | 20 | Solar | 05_01_55W1 | 04/07/2025 | 04/11/2025 | 4 | 0 | 4 | 04/14/2025 | 04/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | BILLERICA | 587903 | 01821 | 7.83 | Solar | 05_05_108W60 | 02/16/2024 | 02/21/2024 | 2 | 0 | 2 | 02/22/2024 | 02/22/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2024 | Connected |  | N
National Grid | WORCESTER | 725014 | 01606 | 5.76 | Solar | 05_05_311W3 | 10/10/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 665545 | 01570 | 7.6 | Solar | 05_12_25W4 | 01/14/2025 | 01/30/2025 | 3 | 0 | 3 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  | 7/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | RUTLAND | 396042 | 01543 | 0 | Other | 05_12_51T3 | 01/04/2022 | 02/04/2022 | 22 | 14 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2022 | 03/02/2022 | 17 | 15 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 647453 | 02019 | 6.67 | Solar | 05_14_3J7 | 10/16/2024 | 10/22/2024 | 3 | 0 | 3 | 10/23/2024 | 10/23/2024 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 272817 | 01752 | 0 | Solar | 05_14_59L1 | 01/10/2020 | 01/21/2020 | 5 | 0 | 5 | 01/22/2020 | 01/22/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 |  | 1/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N
National Grid | MELROSE | 334306 | 02176 | 7.6 | Solar | 05_14_74L1 | 01/13/2021 | 01/29/2021 | 11 | 11 | 0 | 02/01/2021 | 02/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2021 | 01/13/2021 | 9/29/2022 | Y | EXP | 365 | 09/11/2021 | 09/24/2021 | 14 | 0 | 14 |  |  | 3/3/2022 | Connected |  | N
National Grid | GLOUCESTER | 199034 | 01930 | 7.6 | Solar | 05_14_92L6 | 10/19/2018 | 11/01/2018 | 1 | 0 | 1 | 11/02/2018 | 11/02/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 641869 | 01852 | 7.8 | Solar | 05_01_24W3 | 09/20/2024 | 10/03/2024 | 3 | 0 | 3 | 10/04/2024 | 10/04/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/20/2024 | 12/3/2025 | Y | EXP | 365 | 01/21/2025 | 06/10/2025 | 141 | 0 | 141 |  |  | 6/13/2025 | Connected |  | N
National Grid | ANDOVER | 636521 | 01810 | 3.8 | Solar | 05_01_412L2 | 08/29/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2024 | Connected |  | N
National Grid | METHUEN | 684897 | 01844 | 5.76 | Solar | 05_01_55W1 | 04/14/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 52 | 44 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 599414 | 01821 | 7.6 | Solar | 05_05_108W60 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 38 | 25 | 13 | 06/11/2024 | 09/11/2024 | 64 | 0 | 64 |  |  | 0 | 0 | 0 | 09/11/2024 | 64 | 0 | 64 |  |  | 0 | 0 | 0 | 8/12/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 726755 | 01606 | 15.2 | Solar | 05_05_311W3 | 10/15/2025 | 10/21/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 665306 | 01570 | 5.76 | Solar | 05_12_25W4 | 01/13/2025 | 01/31/2025 | 4 | 0 | 4 | 02/03/2025 | 02/03/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 6/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N
National Grid | RUTLAND | 419846 | 01543 | 0 | Other | 05_12_51T3 | 06/14/2022 | 07/19/2022 | 23 | 18 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/20/2022 | 08/08/2022 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 647340 | 02019 | 8.12 | Solar | 05_14_3J7 | 10/21/2024 | 10/29/2024 | 2 | 0 | 2 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/21/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | MARLBOROUGH | 279685 | 01752 | 10 | Solar | 05_14_59L1 | 02/24/2020 | 02/25/2020 | 0 | 0 | 0 | 02/26/2020 | 02/26/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2020 |  | 2/25/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2020 | Connected |  | N
National Grid | MELROSE | 338817 | 02176 | 937.5 | Solar | 05_14_74L1 | 05/17/2021 | 08/04/2021 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2021 | 09/08/2021 | 24 | 3 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2022 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 221173 | 01930 |  | Solar | 05_14_92L6 | 04/19/2019 |  | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 657941 | 01852 | 7.6 | Solar | 05_01_24W3 | 12/02/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 12/02/2024 | 2/24/2026 | Y | EXP | 365 | 07/03/2025 | 07/15/2025 | 13 | 0 | 13 |  |  | 7/28/2025 | Connected |  | N
National Grid | ANDOVER | 636496 | 01810 | 10 | Solar | 05_01_412L2 | 08/29/2024 | 10/28/2024 | 28 | 25 | 3 | 10/29/2024 | 10/29/2024 | 175 | 160 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 685863 | 01844 | 0 | Solar | 05_01_55W1 | 04/28/2025 | 04/30/2025 | 2 | 0 | 2 | 05/01/2025 | 05/01/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 600470 | 01821 | 11.02 | Solar | 05_05_108W60 | 05/13/2024 | 05/14/2024 | 1 | 0 | 1 | 05/15/2024 | 05/15/2024 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2024 | Connected |  | N
National Grid | WORCESTER | 739918 | 01606 | 10 | Solar | 05_05_311W3 | 12/12/2025 | 12/17/2025 | 3 | 0 | 3 | 12/18/2025 | 12/18/2025 | 71 | 60 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEBSTER | 671938 | 01570 | 9.88 | Solar | 05_12_25W4 | 02/13/2025 | 03/19/2025 | 3 | 0 | 3 | 03/20/2025 | 03/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N
National Grid | RUTLAND | 496619 | 01543 | 110 | Solar | 05_12_51T3 | 02/21/2023 | 04/21/2023 | 41 | 31 | 10 |  |  | 35 | 13 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 648266 | 02019 | 5.76 | Solar | 05_14_3J7 | 10/30/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/30/2024 | 1/8/2026 | Y | EXP | 365 | 03/04/2025 | 05/14/2025 | 72 | 0 | 72 |  |  | 5/23/2025 | Connected |  | N
National Grid | MARLBOROUGH | 301740 | 01752 | 15.2 | Solar | 05_14_59L1 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 |  | 5/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2021 | Connected |  | N
National Grid | MELROSE | 340566 | 02176 | 6 | Solar | 05_14_74L1 | 03/26/2021 | 03/31/2021 | 2 | 0 | 2 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 230013 | 01930 | 15.2 | Solar | 05_14_92L6 | 05/21/2019 | 05/28/2019 | 3 | 1 | 2 | 05/29/2019 | 05/29/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2019 | 05/21/2019 | 11/1/2019 | Y | EXP | 147 | 07/25/2019 | 10/02/2019 | 69 | 0 | 69 |  |  | 10/8/2019 | Connected |  | N
National Grid | LOWELL | 659022 | 01852 | 9.88 | Solar | 05_01_24W3 | 12/06/2024 | 01/08/2025 | 13 | 8 | 5 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 4/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | ANDOVER | 650945 | 01810 | 3.8 | Solar | 05_01_412L2 | 11/12/2024 | 12/06/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/12/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | METHUEN | 694884 | 01844 | 11.4 | Solar | 05_01_55W1 | 06/02/2025 | 06/13/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 38 | 26 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 | 06/02/2025 | 9/4/2026 | Y | EXP | 365 | 11/14/2025 | 11/21/2025 | 8 | 0 | 8 |  |  | 11/24/2025 | Connected |  | N
National Grid | BILLERICA | 613326 | 01821 | 11.5 | Solar | 05_05_108W60 | 05/28/2024 | 06/11/2024 | 11 | 9 | 2 | 06/12/2024 | 06/12/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 7/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2024 | Connected |  | N
National Grid | WORCESTER | 750679 | 01606 | 30 | Solar | 05_05_311W3 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2026 |  | 3/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 694846 | 01570 | 11.4 | Solar | 05_12_25W4 | 06/12/2025 | 06/20/2025 | 4 | 0 | 4 | 06/23/2025 | 06/23/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | RUTLAND | 572797 | 01543 | 7.6 | Solar | 05_12_51T3 | 02/12/2024 | 02/15/2024 | 3 | 0 | 3 | 02/16/2024 | 02/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/12/2024 | 3/24/2025 | Y | EXP | 365 | 08/01/2024 | 09/25/2024 | 56 | 0 | 56 |  |  | 10/29/2024 | Connected |  | N
National Grid | BELLINGHAM | 653837 | 02019 | 3.8 | Solar | 05_14_3J7 | 11/13/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | MARLBOROUGH | 306442 | 01752 | 0 | Solar | 05_14_59L1 | 08/12/2020 | 09/14/2020 | 21 | 21 | 0 | 09/15/2020 | 09/15/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/12/2020 | 9/14/2021 | Y | EXP | 365 | 01/05/2021 | 01/19/2021 | 14 | 0 | 14 |  |  | 3/2/2021 | Connected |  | N
National Grid | MELROSE | 346362 | 02176 | 7.6 | Solar | 05_14_74L1 | 03/26/2021 | 03/31/2021 | 2 | 0 | 2 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 | 03/26/2021 | 10/19/2022 | Y | EXP | 365 | 09/29/2021 | 10/29/2021 | 31 | 4 | 27 |  |  | 11/30/2021 | Connected |  | Y
National Grid | GLOUCESTER | 354556 | 01930 | 10 | Solar | 05_14_92L6 | 04/26/2021 | 05/04/2021 | 5 | 5 | 0 | 05/05/2021 | 05/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 6/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2021 | Connected |  | N
National Grid | LOWELL | 660119 | 01852 | 7.475 | Solar | 05_01_24W3 | 12/12/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 651603 | 01810 | 10 | Solar | 05_01_412L2 | 11/12/2024 | 01/28/2025 | 5 | 0 | 5 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 11/12/2024 | 3/17/2026 | Y | EXP | 365 | 06/12/2025 | 12/01/2025 | 173 | 0 | 173 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 702598 | 01844 | 11.5 | Solar | 05_01_55W1 | 07/14/2025 | 07/21/2025 | 5 | 0 | 5 | 07/22/2025 | 07/22/2025 | 64 | 55 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 620631 | 01821 | 10 | Solar | 05_05_108W60 | 06/26/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2024 | Connected |  | N
National Grid | WORCESTER | 175946 | 01606 | 2.4 | Solar | 05_05_311W3 | 03/17/2015 | 03/17/2015 | 3 | 2 | 1 | 03/23/2015 | 03/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2015 |  | 7/17/2015 | N | EXP | 113 |  |  | 0 | 0 | 0 | 9/22/2016 | 9/22/2016 | 5/5/2017 | Connected |  | N
National Grid | WEBSTER | 699634 | 01570 | 7.678 | Solar | 05_12_25W4 | 06/18/2025 | 07/02/2025 | 3 | 0 | 3 | 08/01/2025 | 08/01/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 |  | 8/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | RUTLAND | 615411 | 01543 | 25 | Solar | 05_12_51T3 | 06/10/2024 | 11/07/2024 | 104 | 95 | 9 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | BELLINGHAM | 662094 | 02019 | 6.46 | Solar | 05_14_3J7 | 12/20/2024 | 03/17/2025 | 53 | 49 | 4 | 03/18/2025 | 03/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 308036 | 01752 | 0 | Battery Add-On | 05_14_59L1 | 09/30/2020 | 10/16/2020 | 11 | 9 | 2 | 10/19/2020 | 10/19/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 |  | 4/15/2022 | N | EXP | 500 |  |  | 0 | 0 | 0 |  |  | 3/25/2022 | Connected |  | N
National Grid | MELROSE | 364103 | 02176 | 4.08 | Solar | 05_14_74L1 | 07/22/2021 | 07/27/2021 | 3 | 0 | 3 | 07/28/2021 | 07/28/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 367329 | 01966 | 7.6 | Solar | 05_14_92L6 | 07/20/2021 | 07/21/2021 | 0 | 0 | 0 | 07/22/2021 | 07/22/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2021 | 07/20/2021 | 5/20/2023 | Y | EXP | 365 | 01/18/2022 | 05/20/2022 | 123 | 0 | 123 |  |  | 6/8/2022 | Connected |  | N
National Grid | LOWELL | 660120 | 01852 | 7.475 | Solar | 05_01_24W3 | 12/12/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2025 | Connected |  | N
National Grid | ANDOVER | 653524 | 01810 | 5.76 | Solar | 05_01_412L2 | 11/15/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/15/2024 | 3/21/2026 | Y | EXP | 365 | 08/05/2025 | 10/01/2025 | 58 | 0 | 58 |  |  | 10/2/2025 | Connected |  | N
National Grid | METHUEN | 707581 | 01844 | 10 | Solar | 05_01_55W1 | 07/25/2025 | 09/03/2025 | 3 | 0 | 3 | 09/04/2025 | 09/04/2025 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 637783 | 01821 | 10 | Solar | 05_05_108W60 | 09/04/2024 | 09/20/2024 | 3 | 0 | 3 | 09/23/2024 | 09/23/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176678 | 01606 | 6 | Solar | 05_05_311W3 | 01/04/2016 | 01/04/2016 | 0 | 0 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 |  | 1/11/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 | 7/26/2016 | 7/26/2016 | 8/23/2016 | Connected |  | N
National Grid | WEBSTER | 658099 | 01570 | 3.8 | Solar | 05_12_25W5 | 12/03/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RUTLAND | 700819 | 01543 | 15.76 | Solar | 05_12_51T3 | 07/02/2025 | 07/09/2025 | 3 | 0 | 3 | 07/10/2025 | 07/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 07/02/2025 | 8/4/2026 | Y | EXP | 365 | 11/04/2025 | 11/18/2025 | 15 | 0 | 15 |  |  | 12/8/2025 | Connected |  | N
National Grid | BLACKSTONE | 666688 | 01504 | 3.8 | Solar | 05_14_3J7 | 01/20/2025 | 02/11/2025 | 4 | 0 | 4 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N
National Grid | MARLBOROUGH | 309991 | 01752 | 9.6 | Solar | 05_14_59L1 | 09/01/2020 | 09/08/2020 | 3 | 0 | 3 | 09/09/2020 | 09/09/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2021 | Connected |  | N
National Grid | MELROSE | 395653 | 02176 | 6 | Solar | 05_14_74L1 | 12/06/2021 | 01/07/2022 | 1 | 0 | 1 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 12/06/2021 | 6/28/2023 | Y | EXP | 365 | 05/24/2022 | 06/28/2022 | 36 | 0 | 36 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 638125 | 01930 | 10 | Solar | 05_14_92L6 | 09/05/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 668899 | 01852 | 7.6 | Solar | 05_01_24W3 | 02/03/2025 | 04/16/2025 | 1 | 0 | 1 | 05/01/2025 | 05/01/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | ANDOVER | 653708 | 01810 | 4950 | Other | 05_01_412L2 | 04/10/2025 |  | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 727815 | 01844 | 5.76 | Solar | 05_01_55W1 | 10/20/2025 | 11/14/2025 | 17 | 15 | 2 | 11/17/2025 | 11/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2026 | Connected |  | N
National Grid | BILLERICA | 640399 | 01821 | 0 | Battery Add-On | 05_05_108W60 | 09/16/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 171 | 136 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2026 | Connected |  | N
National Grid | WORCESTER | 184521 | 01606 | 17.6 | Solar | 05_05_311W3 | 05/04/2018 | 05/04/2018 | 16 | 2 | 14 | 06/06/2018 | 06/06/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 |  | 7/22/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | WEBSTER | 707442 | 01570 | 7.6 | Solar | 05_12_25W5 | 07/25/2025 | 08/13/2025 | 4 | 0 | 4 | 09/16/2025 | 09/16/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RUTLAND | 703384 | 01543 | 90 | Solar | 05_12_51T3 | 07/10/2025 | 08/07/2025 | 20 | 11 | 9 | 08/08/2025 | 08/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 669223 | 02019 | 6 | Solar | 05_14_3J7 | 01/31/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 397084 | 01752 | 1375 | Solar | 05_14_59L1 | 03/15/2022 | 02/08/2023 | 57 | 48 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/08/2022 | 06/30/2022 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 409865 | 02176 | 6.67 | Solar | 05_14_74L1 | 03/24/2022 | 04/06/2022 | 10 | 9 | 1 | 04/07/2022 | 04/07/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2022 | 03/24/2022 | 7/8/2023 | Y | EXP | 365 | 06/08/2022 | 06/28/2022 | 21 | 0 | 21 |  |  | 8/1/2022 | Connected |  | N
National Grid | GLOUCESTER | 643835 | 01930 | 7.6 | Solar | 05_14_92L6 | 10/01/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 12/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | LOWELL | 714389 | 01852 | 5.76 | Solar | 05_01_24W3 | 08/25/2025 | 09/05/2025 | 7 | 2 | 5 | 09/08/2025 | 09/08/2025 | 59 | 47 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 657794 | 01876 | 20 | Solar | 05_01_412L2 | 12/02/2024 | 12/06/2024 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 174972 | 01844 | 4999 | Solar | 05_01_55W3 | 09/26/2011 | 09/26/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2011 | 12/20/2011 | 36 | 0 | 36 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2012 | 09/26/2011 | 6/1/2014 | Y | STD | 590 | 03/12/2014 | 12/18/2014 | 192 | 0 | 192 | 7/9/2014 | 7/9/2014 | 7/11/2014 | Connected |  | N
National Grid | BILLERICA | 643794 | 01821 | 7.6 | Solar | 05_05_108W60 | 10/04/2024 | 10/18/2024 | 4 | 4 | 0 | 10/21/2024 | 10/21/2024 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 12/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | WORCESTER | 190641 | 01606 | 11.4 | Solar | 05_05_311W3 | 07/13/2018 | 09/10/2018 | 23 | 9 | 14 | 09/11/2018 | 09/11/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 | 07/13/2018 | 10/10/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2019 | Connected |  | N
National Grid | WEBSTER | 175387 | 01570 | 90 | Solar | 05_12_25W5 | 09/10/2014 | 09/10/2014 | 7 | 0 | 7 | 09/22/2014 | 09/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2014 |  | 12/15/2014 | N | EXP | 68 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 1/15/2015 | Connected |  | N
National Grid | RUTLAND | 628375 | 01543 | 34.5 | Battery Add-On | 05_12_52J2 | 07/29/2024 | 08/01/2024 | 3 | 0 | 3 | 08/02/2024 | 08/02/2024 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2024 | Connected |  | N
National Grid | BLACKSTONE | 700371 | 01504 | 11.02 | Solar | 05_14_3J7 | 06/23/2025 | 08/13/2025 | 5 | 3 | 2 | 08/14/2025 | 08/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 408840 | 01752 | 0 | Battery Add-On | 05_14_59L1 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 03/02/2022 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 474114 | 02176 | 10 | Solar | 05_14_74L1 | 12/20/2022 | 12/21/2022 | 1 | 0 | 1 | 12/22/2022 | 12/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/20/2022 | 4/19/2024 | Y | EXP | 365 | 03/14/2023 | 04/19/2023 | 37 | 0 | 37 |  |  | 5/15/2023 | Connected |  | N
National Grid | GLOUCESTER | 645912 | 01930 | 7.6 | Solar | 05_14_92L6 | 10/18/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 10/18/2024 | 1/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | LOWELL | 174797 | 01852 | 100 | Solar | 05_01_24W4 | 08/29/2012 | 08/29/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 438 | 119 | 319 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/7/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 667026 | 01810 | 5.76 | Solar | 05_01_412L2 | 01/21/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2025 | Connected |  | N
National Grid | METHUEN | 176162 | 01844 | 1000 | Solar | 05_01_55W3 | 02/06/2015 | 02/06/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2015 | 03/16/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2015 | 02/06/2015 | 9/24/2017 | Y | STD | 648 | 08/11/2017 | 09/15/2017 | 24 | 0 | 24 | 9/8/2017 | 9/8/2017 | 9/29/2017 | Connected |  | N
National Grid | BILLERICA | 644592 | 01821 | 10 | Solar | 05_05_108W60 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/02/2024 | 12/18/2025 | Y | EXP | 365 | 08/22/2025 | 09/18/2025 | 28 | 0 | 28 |  |  | 10/18/2025 | Connected |  | N
National Grid | WORCESTER | 193918 | 01605 | 6 | Solar | 05_05_311W3 | 08/20/2018 | 10/12/2018 | 27 | 24 | 3 | 10/15/2018 | 10/15/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 10/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2019 | Connected |  | N
National Grid | WEBSTER | 176038 | 01570 | 10 | Solar | 05_12_25W5 | 08/13/2015 | 08/13/2015 | 2 | 2 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 |  | 8/19/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 6/22/2016 | 6/22/2016 | 8/5/2016 | Connected |  | N
National Grid | RUTLAND | 657154 | 01543 | 3.8 | Solar | 05_12_52L1 | 11/26/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 4/21/2026 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BELLINGHAM | 557014 | 02019 | 200 | Solar | 05_14_3L2 | 09/21/2023 | 10/06/2023 | 11 | 2 | 9 | 10/10/2023 | 10/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 | 09/21/2023 | 5/12/2026 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | MARLBOROUGH | 412219 | 01752 | 0 | Battery Add-On | 05_14_59L1 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/14/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 492624 | 02176 | 17.45 | Solar | 05_14_74L1 | 01/16/2023 | 01/18/2023 | 2 | 0 | 2 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 | 01/16/2023 | 6/14/2024 | Y | EXP | 470 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 646409 | 01930 | 5.76 | Solar | 05_14_92L6 | 10/25/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/25/2024 | 1/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | LOWELL | 174964 | 01852 | 81 | Solar | 05_01_24W4 | 08/30/2013 | 08/30/2013 | 7 | 0 | 7 | 09/12/2013 | 09/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2013 |  | 11/29/2013 | N | EXP | 66 |  |  | 0 | 0 | 0 | 12/11/2013 | 12/11/2013 | 12/11/2013 | Connected |  | N
National Grid | ANDOVER | 674700 | 01810 | 10 | Solar | 05_01_412L2 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 178360 | 01844 | 4300 | Solar | 05_01_55W3 | 03/30/2018 | 03/30/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2018 | 05/21/2018 | 33 | 18 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 651065 | 01821 | 6.175 | Solar | 05_05_108W60 | 10/31/2024 | 11/14/2024 | 4 | 0 | 4 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/31/2024 | 1/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | WORCESTER | 194787 | 01606 | 7.6 | Solar | 05_05_311W3 | 08/30/2018 | 11/14/2018 | 29 | 25 | 4 | 11/15/2018 | 11/15/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 178553 | 01570 | 120 | Solar | 05_12_25W5 | 03/12/2018 | 03/12/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 11/14/2019 | N | EXP | 393 |  |  | 0 | 0 | 0 |  |  | 12/18/2019 | Connected |  | N
National Grid | RUTLAND | 691723 | 01543 | 11.5 | Solar | 05_12_52L1 | 06/12/2025 | 07/22/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 61 | 47 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BELLINGHAM | 674259 | 02019 | 220 | Solar | 05_14_3L2 | 02/28/2025 | 03/14/2025 | 10 | 0 | 10 | 03/17/2025 | 03/17/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2025 | 02/28/2025 | 5/9/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | MARLBOROUGH | 457561 | 01752 | 9.6 | Solar | 05_14_59L1 | 09/09/2022 | 09/27/2022 | 13 | 12 | 1 | 09/28/2022 | 09/28/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2022 |  | 11/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2023 | Connected |  | Y
National Grid | MELROSE | 515458 | 02176 | 12.6 | Solar | 05_14_74L1 | 04/24/2023 | 04/26/2023 | 2 | 0 | 2 | 04/27/2023 | 04/27/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 | 04/24/2023 | 11/5/2024 | Y | EXP | 365 | 09/12/2023 | 10/24/2023 | 43 | 0 | 43 |  |  | 11/18/2023 | Connected |  | N
National Grid | GLOUCESTER | 653778 | 01930 | 10 | Solar | 05_14_92L6 | 11/18/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/18/2024 | 3/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N
National Grid | LOWELL | 202543 | 01852 | 249.9 | Solar | 05_01_24W4 | 12/21/2018 | 01/10/2019 | 5 | 0 | 5 | 01/11/2019 | 01/11/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 681581 | 01810 | 15.76 | Solar | 05_01_412L2 | 04/01/2025 | 04/07/2025 | 4 | 0 | 4 | 04/08/2025 | 04/08/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 5/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 543236 | 01844 | 0 | Other | 05_01_602W2 | 09/07/2023 | 10/02/2023 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2023 | 11/07/2023 | 26 | 6 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BILLERICA | 660346 | 01821 | 10 | Solar | 05_05_108W60 | 12/12/2024 | 02/13/2025 | 4 | 0 | 4 | 02/14/2025 | 02/14/2025 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | WORCESTER | 201858 | 01606 | 10 | Solar | 05_05_311W3 | 11/21/2018 | 01/25/2019 | 19 | 19 | 0 | 01/28/2019 | 01/28/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2019 |  | 1/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2020 | Connected |  | N
National Grid | WEBSTER | 195099 | 01570 | 7.6 | Solar | 05_12_25W5 | 09/05/2018 | 09/26/2018 | 3 | 3 | 0 | 09/27/2018 | 09/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 740577 | 01452 | 11.52 | Solar | 05_12_52L1 | 12/19/2025 | 12/26/2025 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 41 | 23 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BLACKSTONE | 734040 | 01504 | 18.24 | Solar | 05_14_3L2 | 11/14/2025 | 11/20/2025 | 4 | 0 | 4 | 11/21/2025 | 11/21/2025 | 53 | 35 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MARLBOROUGH | 501458 | 01752 | 15.2 | Solar | 05_14_59L1 | 02/13/2023 | 02/14/2023 | 1 | 0 | 1 | 02/15/2023 | 02/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 558385 | 02176 | 990 | Solar | 05_14_74L1 | 12/04/2023 |  | 181 | 172 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 654416 | 01930 | 5 | Solar | 05_14_92L6 | 11/14/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/14/2024 | 2/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | LOWELL | 396605 | 01852 | 0 | Other | 05_01_24W4 | 05/11/2022 | 05/27/2022 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2022 | 06/22/2022 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 690834 | 01810 | 15.2 | Solar | 05_01_412L2 | 05/21/2025 | 05/27/2025 | 3 | 0 | 3 | 05/28/2025 | 05/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 706227 | 01844 | 7.6 | Solar | 05_01_602W2 | 07/21/2025 | 07/23/2025 | 2 | 0 | 2 | 07/24/2025 | 07/24/2025 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 661870 | 01821 | 5.76 | Solar | 05_05_108W60 | 12/19/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | WORCESTER | 233157 | 01606 | 166.6 | Solar | 05_05_311W3 | 03/25/2020 | 03/31/2020 | 3 | 0 | 3 |  |  | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 03/25/2020 | 10/20/2021 | Y | STD | 112 | 08/20/2021 | 08/19/2021 | 0 | 0 | 0 |  |  | 10/20/2021 | Connected |  | N
National Grid | WEBSTER | 192454 | 01570 | 10 | Solar | 05_12_25W5 | 08/02/2018 | 08/11/2018 | 2 | 2 | 0 | 08/13/2018 | 08/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  | 8/26/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2019 | Connected |  | N
National Grid | WESTMINSTER | 753100 | 01473 | 22.8 | Solar | 05_12_52L1 | 02/25/2026 | 02/27/2026 | 2 | 0 | 2 | 03/02/2026 | 03/02/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2026 |  | 3/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BLACKSTONE | 424685 | 01504 | 6.09 | Solar | 05_14_3L2 | 05/13/2022 | 05/16/2022 | 1 | 0 | 1 | 05/17/2022 | 05/17/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2022 | 05/13/2022 | 8/19/2024 | Y | EXP | 365 | 04/16/2023 | 05/03/2023 | 18 | 0 | 18 |  |  | 10/12/2023 | Connected |  | N
National Grid | MARLBOROUGH | 504001 | 01752 | 0 | Solar | 05_14_59L1 | 02/24/2023 | 02/27/2023 | 1 | 0 | 1 | 02/28/2023 | 02/28/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2023 | 02/24/2023 | 7/27/2024 | Y | EXP | 365 | 08/29/2023 | 10/04/2023 | 37 | 0 | 37 |  |  | 11/20/2023 | Connected |  | N
National Grid | MELROSE | 655710 | 02176 | 3.8 | Solar | 05_14_92L6 | 11/20/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 11/20/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2025 | Connected |  | N
National Grid | GLOUCESTER | 601631 | 01930 | 3.8 | Solar | 05_01_24W4 | 04/10/2024 | 04/11/2024 | 1 | 0 | 1 | 04/12/2024 | 04/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/10/2024 | 4/25/2025 | Y | EXP | 365 | 05/24/2024 | 09/12/2024 | 112 | 0 | 112 |  |  | 9/26/2024 | Connected |  | N
National Grid | TEWKSBURY | 708501 | 01876 | 3.8 | Solar | 05_01_412L2 | 08/11/2025 | 08/28/2025 | 13 | 9 | 4 | 08/29/2025 | 08/29/2025 | 45 | 28 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | ANDOVER | 713175 | 01810 | 23 | Solar | 05_01_602W2 | 08/19/2025 | 08/21/2025 | 2 | 0 | 2 | 08/22/2025 | 08/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | METHUEN | 674897 | 01844 | 7.6 | Solar | 05_05_108W60 | 03/13/2025 | 03/18/2025 | 3 | 0 | 3 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | BILLERICA | 233442 | 01821 | 400 | Solar | 05_05_311W3 | 04/15/2020 | 06/04/2020 | 32 | 25 | 7 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 04/15/2020 | 11/30/2021 | Y | STD | 120 | 09/08/2021 | 09/07/2021 | 0 | 0 | 0 |  |  | 11/24/2021 | Connected |  | N
National Grid | WORCESTER | 222080 | 01606 | 7.6 | Solar | 05_12_25W5 | 06/05/2019 | 06/06/2019 | 0 | 0 | 0 | 06/07/2019 | 06/07/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2019 | 06/05/2019 | 9/8/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2023 | Connected |  | Y
National Grid | WEBSTER | 175870 | 01570 | 25 | Solar | 05_12_52L1 | 09/25/2015 | 09/25/2015 | 1 | 1 | 0 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2015 |  | 10/3/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 1/29/2016 | 1/29/2016 | 2/3/2016 | Connected |  | N
National Grid | WESTMINSTER | 583375 | 01473 | 10 | Solar | 05_14_3L2 | 01/26/2024 | 01/30/2024 | 2 | 0 | 2 | 01/31/2024 | 01/31/2024 | 57 | 45 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 01/26/2024 | 6/3/2025 | Y | EXP | 365 | 09/14/2024 | 11/04/2024 | 52 | 0 | 52 |  |  | 11/18/2024 | Connected |  | N
National Grid | BLACKSTONE | 512029 | 01504 | 15.2 | Solar | 05_14_59L1 | 03/16/2023 | 03/20/2023 | 2 | 0 | 2 | 03/21/2023 | 03/21/2023 | 59 | 39 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2023 |  | 7/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2024 | Connected |  | N
National Grid | MARLBOROUGH | 559307 | 01752 | 240 | Solar | 05_14_74L1 | 11/17/2023 | 12/08/2023 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 11/17/2023 | 4/17/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 656812 | 02176 | 5.76 | Solar | 05_14_92L6 | 11/25/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 11/25/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | GLOUCESTER | 632651 | 01930 | 5.76 | Solar | 05_01_24W4 | 08/14/2024 | 09/10/2024 | 3 | 0 | 3 | 09/11/2024 | 09/11/2024 | 105 | 31 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 734850 | 01852 | 9.57 | Solar | 05_01_412L2 | 11/19/2025 | 11/20/2025 | 3 | 0 | 3 | 12/03/2025 | 12/03/2025 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 | 11/19/2025 | 1/23/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2026 | Connected |  | N
National Grid | ANDOVER | 714916 | 01810 | 12.16 | Solar | 05_01_602W2 | 08/26/2025 | 09/16/2025 | 5 | 0 | 5 | 10/02/2025 | 10/02/2025 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 08/26/2025 | 12/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 461538 | 01844 | 490 | Solar | 05_05_115W42 | 02/08/2023 | 06/22/2023 | 92 | 81 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2023 | 01/08/2024 | 136 | 115 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 | 02/08/2023 | 11/28/2026 | Y | STD | 329 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BILLERICA | 249197 | 01821 | 7.6 | Solar | 05_05_311W3 | 10/03/2019 | 10/11/2019 | 6 | 5 | 1 | 10/15/2019 | 10/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 269791 | 01606 | 3 | Solar | 05_12_25W5 | 12/20/2019 | 01/02/2020 | 6 | 0 | 6 | 01/03/2020 | 01/03/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/20/2019 | 12/20/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2020 | Connected |  | N
National Grid | WEBSTER | 177815 | 01570 | 15.2 | Solar | 05_12_52L1 | 03/31/2017 | 03/31/2017 | 7 | 4 | 3 | 04/11/2017 | 04/11/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2017 | 03/31/2017 | 8/10/2018 | Y | EXP | 485 | 01/24/2018 | 02/23/2018 | 21 | 0 | 21 |  |  | 7/30/2018 | Connected |  | N
National Grid | HUBBARDSTON | 641313 | 01452 | 7.6 | Solar | 05_14_3L2 | 09/18/2024 | 10/07/2024 | 4 | 0 | 4 | 10/08/2024 | 10/08/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/18/2024 | 1/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 541519 | 02724 | 9.57 | Solar | 05_14_59L1 | 09/22/2023 | 09/26/2023 | 2 | 0 | 2 | 09/27/2023 | 09/27/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 09/22/2023 | 11/22/2024 | Y | EXP | 365 | 03/26/2024 | 07/23/2024 | 120 | 0 | 120 |  |  | 7/25/2024 | Connected |  | N
National Grid | MARLBOROUGH | 559191 | 01752 | 240 | Solar | 05_14_74L1 | 11/03/2023 | 11/21/2023 | 12 | 0 | 12 | 11/22/2023 | 11/22/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 11/03/2023 | 4/16/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 656807 | 02176 | 7.6 | Solar | 05_14_92L6 | 11/25/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | GLOUCESTER | 755883 | 01930 | 5.76 | Solar | 05_01_24W5 | 03/11/2026 | 03/16/2026 | 3 | 0 | 3 | 03/17/2026 | 03/17/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 175080 | 01852 | 1000 | Natural Gas | 05_01_412L3 | 10/01/2013 | 10/01/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2013 | 12/11/2013 | 41 | 0 | 41 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2015 | 10/01/2013 | 12/31/2016 | Y | STD | 664 | 06/17/2016 | 09/01/2016 | 52 | 0 | 52 | 10/2/2013 | 10/2/2013 | 6/14/2016 | Connected |  | N
National Grid | ANDOVER | 715276 | 01810 | 10 | Solar | 05_01_602W2 | 08/28/2025 | 09/18/2025 | 2 | 0 | 2 | 10/01/2025 | 10/01/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 08/28/2025 | 11/4/2026 | Y | EXP | 365 | 01/15/2026 |  | 77 | 0 | 77 |  |  |  | Construction |  | N
National Grid | METHUEN | 666238 | 01844 | 120 | Solar | 05_05_115W42 | 02/03/2025 | 03/11/2025 | 26 | 16 | 10 | 03/12/2025 | 03/12/2025 | 25 | 0 | 25 | 05/20/2025 | 05/29/2025 | 7 | 4 | 3 |  |  | 0 | 0 | 0 | 05/29/2025 | 7 | 4 | 3 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 7/8/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 287957 | 01821 | 200 | Solar | 05_05_311W3 | 04/16/2020 | 06/04/2020 | 32 | 25 | 7 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 04/16/2020 | 9/6/2022 | Y | STD | 300 | 05/10/2022 | 05/09/2022 | 0 | 0 | 0 |  |  | 5/19/2022 | Connected |  | N
National Grid | WORCESTER | 294223 | 01606 | 0 | Solar | 05_12_25W5 | 06/01/2020 | 06/04/2020 | 3 | 3 | 0 | 06/05/2020 | 06/05/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2020 | Connected |  | N
National Grid | OXFORD | 274362 | 01540 | 4.32 | Solar | 05_12_52L1 | 02/12/2020 | 02/26/2020 | 8 | 8 | 0 | 02/27/2020 | 02/27/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 | 02/12/2020 | 2/26/2021 | Y | EXP | 365 | 07/23/2020 | 09/15/2020 | 55 | 5 | 50 |  |  | 9/16/2020 | Connected |  | N
National Grid | HUBBARDSTON | 647155 | 01452 | 6 | Solar | 05_14_3L2 | 10/24/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2025 | Connected |  | N
National Grid | FALL RIVER | 564915 | 02724 | 0 | Solar | 05_14_59L1 | 10/20/2023 | 10/23/2023 | 1 | 0 | 1 | 10/24/2023 | 10/24/2023 | 90 | 78 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 10/20/2023 | 3/20/2025 | Y | EXP | 365 | 07/06/2024 | 09/03/2024 | 60 | 0 | 60 |  |  | 9/10/2024 | Connected |  | N
National Grid | MARLBOROUGH | 539516 | 01752 | 10 | Solar | 05_14_74L1 | 08/01/2023 | 08/02/2023 | 1 | 0 | 1 | 08/03/2023 | 08/03/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 658010 | 02176 | 7.6 | Solar | 05_14_92L6 | 12/03/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 12/03/2024 | 8/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 178232 | 01930 | 43.2 | Solar | 05_01_24W5 | 01/05/2018 | 01/05/2018 | 0 | 0 | 0 | 01/25/2018 | 01/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2018 |  | 1/13/2019 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  | 6/8/2018 | Connected |  | N
National Grid | LOWELL | 176487 | 01852 | 3000 | Natural Gas | 05_01_412L3 | 12/08/2015 | 12/10/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 01/11/2016 | 20 | 0 | 20 |  | 0 | 0 | 0 | 05/23/2016 | 06/23/2016 | 21 | 0 | 21 | 11/7/2016 |  | 1/31/2019 | N | STD | 815 |  |  | 0 | 0 | 0 |  |  | 1/19/2019 | Connected |  | N
National Grid | ANDOVER | 743484 | 01810 | 11.52 | Solar | 05_01_602W2 | 01/06/2026 | 01/09/2026 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 40 | 22 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2026 |  | 3/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 751950 | 01844 | 200 | Solar | 05_05_115W42 | 03/20/2026 |  | 8 | 7 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BILLERICA | 297691 | 01821 | 66.6 | Solar | 05_05_311W3 | 06/30/2020 | 07/27/2020 | 18 | 18 | 0 | 07/28/2020 | 07/28/2020 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2021 | Connected |  | N
National Grid | WORCESTER | 334088 | 01606 | 10 | Solar | 05_12_25W5 | 12/28/2020 | 01/07/2021 | 7 | 7 | 0 | 01/08/2021 | 01/08/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2021 |  | 1/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2021 | Connected |  | N
National Grid | OXFORD | 303344 | 01540 | 15.2 | Solar | 05_12_52L1 | 07/27/2020 | 08/28/2020 | 24 | 24 | 0 | 08/31/2020 | 08/31/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 |  | 4/11/2022 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  | 2/10/2022 | Connected |  | N
National Grid | WESTMINSTER | 649912 | 01473 | 3.8 | Solar | 05_14_3L2 | 11/06/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/06/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | FALL RIVER | 608981 | 02724 | 23 | Battery Add-On | 05_14_59L1 | 05/06/2024 | 05/07/2024 | 1 | 0 | 1 | 05/08/2024 | 05/08/2024 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 6/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | MARLBOROUGH | 551550 | 01752 | 12 | Solar | 05_14_74L1 | 09/05/2023 |  | 110 | 53 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 662600 | 02176 | 7.6 | Solar | 05_14_92L6 | 12/26/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | GLOUCESTER | 226537 | 01930 | 4405 | Solar | 05_01_24W5 | 05/20/2019 | 05/31/2019 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/03/2019 | 06/27/2019 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 210192 | 01852 | 4250 | Natural Gas | 05_01_412L3 | 06/24/2019 | 07/16/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2019 | 07/25/2019 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2020 | 06/24/2019 | 9/9/2023 | Y | STD | 336 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | ANDOVER | 746247 | 01810 | 11.5 | Solar | 05_01_602W2 | 01/19/2026 | 01/27/2026 | 3 | 0 | 3 | 02/24/2026 | 02/24/2026 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | METHUEN | 174581 | 01844 | 190 | Solar | 05_05_115W42 | 10/18/2011 | 10/18/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2011 |  | 10/31/2012 | N | EXP | 314 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 7/11/2012 | Connected |  | N
National Grid | BILLERICA | 311908 | 01821 | 10 | Solar | 05_05_311W3 | 09/10/2020 | 09/11/2020 | 0 | 0 | 0 | 09/14/2020 | 09/14/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2020 |  | 9/10/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 376077 | 01606 | 15.2 | Solar | 05_12_25W5 | 09/06/2021 | 09/07/2021 | 1 | 0 | 1 | 09/08/2021 | 09/08/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2021 |  | 9/13/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 371202 | 01540 | 7.6 | Solar | 05_12_52L1 | 08/03/2021 | 08/18/2021 | 12 | 11 | 1 | 08/19/2021 | 08/19/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 9/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2021 | Connected |  | N
National Grid | GARDNER | 651647 | 01440 | 7.6 | Solar | 05_14_3L2 | 11/13/2024 | 12/08/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/13/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | FALL RIVER | 627752 | 02724 | 23.725 | Solar | 05_14_59L1 | 08/23/2024 | 08/27/2024 | 2 | 0 | 2 | 08/28/2024 | 08/28/2024 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | MARLBOROUGH | 552256 | 01752 | 0 | Solar | 05_14_74L1 | 08/30/2023 | 09/08/2023 | 6 | 4 | 2 | 09/11/2023 | 09/11/2023 | 104 | 82 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2024 |  | 2/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 663221 | 02176 | 7.6 | Solar | 05_14_92L6 | 12/31/2024 | 01/17/2025 | 6 | 0 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | ROCKPORT | 309000 | 01966 | 7.6 | Solar | 05_01_24W5 | 10/06/2020 | 10/12/2020 | 3 | 0 | 3 | 10/13/2020 | 10/13/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2020 |  | 3/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 578994 | 01852 | 240 | Solar | 05_01_412L4 | 12/22/2023 | 01/09/2024 | 10 | 0 | 10 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | ANDOVER | 752597 | 01810 | 7.6 | Solar | 05_01_602W2 | 02/26/2026 | 03/16/2026 | 2 | 0 | 2 | 03/30/2026 | 03/30/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 175817 | 01844 | 150 | Solar | 05_05_115W42 | 07/28/2015 | 07/28/2015 | 2 | 2 | 0 | 07/31/2015 | 07/31/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2015 |  | 8/3/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/7/2016 | 9/7/2016 | 9/7/2016 | Connected |  | N
National Grid | BILLERICA | 328441 | 01821 | 10 | Solar | 05_05_311W3 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 |  | 11/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2021 | Connected |  | N
National Grid | WORCESTER | 410315 | 01606 | 8.99 | Solar | 05_12_25W5 | 02/03/2022 | 02/04/2022 | 1 | 0 | 1 | 02/07/2022 | 02/07/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2022 | Connected |  | N
National Grid | DUDLEY | 375231 | 01571 | 11.4 | Solar | 05_12_52L1 | 08/11/2021 | 08/31/2021 | 14 | 13 | 1 | 09/01/2021 | 09/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2021 | 08/11/2021 | 2/14/2023 | Y | EXP | 365 | 01/06/2022 | 02/14/2022 | 40 | 0 | 40 |  |  | 4/19/2022 | Connected |  | Y
National Grid | HUBBARDSTON | 661000 | 01452 | 8.74 | Solar | 05_14_3L2 | 12/18/2024 | 01/06/2025 | 5 | 0 | 5 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/18/2024 | 2/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | FALL RIVER | 631986 | 02724 | 0 | Solar | 05_14_59L1 | 08/12/2024 | 08/15/2024 | 3 | 0 | 3 | 08/16/2024 | 08/16/2024 | 101 | 77 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | MARLBOROUGH | 551686 | 01752 | 6.38 | Solar | 05_14_74L1 | 08/29/2023 | 08/31/2023 | 2 | 0 | 2 | 09/01/2023 | 09/01/2023 | 25 | 0 | 25 | 10/13/2023 | 10/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 10/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 710907 | 02176 | 15.68 | Solar | 05_14_92L6 | 09/10/2025 | 09/22/2025 | 7 | 4 | 3 | 09/23/2025 | 09/23/2025 | 23 | 9 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2026 | Connected |  | N
National Grid | ROCKPORT | 396684 | 01966 | 0 | Other | 05_01_24W5 | 04/28/2022 | 05/19/2022 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/20/2022 | 06/16/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 578997 | 01852 | 140 | Solar | 05_01_412L4 | 12/22/2023 | 01/08/2024 | 9 | 0 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | ANDOVER | 174177 | 01810 | 11.4 | Solar | 05_01_602W2 | 03/06/2012 | 03/06/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2012 |  | 6/4/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 | 6/4/2012 | 6/4/2012 | 7/16/2012 | Connected |  | N
National Grid | METHUEN | 176031 | 01844 | 450 | Solar | 05_05_115W42 | 06/18/2015 | 06/18/2015 | 34 | 34 | 0 | 08/07/2015 | 08/07/2015 | 308 | 0 | 308 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2015 |  | 1/30/2017 | N | EXP | 490 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 333111 | 01821 | 5.76 | Solar | 05_05_311W3 | 03/22/2021 | 03/24/2021 | 1 | 1 | 0 | 03/25/2021 | 03/25/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 |  | 4/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2021 | Connected |  | N
National Grid | WORCESTER | 437932 | 01606 | 9.984 | Solar | 05_12_25W5 | 06/15/2022 | 06/24/2022 | 3 | 1 | 2 | 06/30/2022 | 06/30/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2022 |  | 7/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2023 | Connected |  | N
National Grid | DUDLEY | 380590 | 01571 | 7.6 | Solar | 05_12_52L1 | 11/16/2021 | 12/20/2021 | 23 | 22 | 1 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 666669 | 01473 | 7.6 | Solar | 05_14_3L2 | 01/20/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 01/20/2025 | 4/14/2026 | Y | EXP | 365 | 07/24/2025 | 12/22/2025 | 152 | 0 | 152 |  |  | 12/4/2025 | Connected |  | N
National Grid | FALL RIVER | 662547 | 02724 | 7.6 | Solar | 05_14_59L1 | 01/02/2025 | 01/17/2025 | 4 | 0 | 4 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | MARLBOROUGH | 571764 | 01752 | 240 | Solar | 05_14_74L1 | 11/17/2023 | 12/06/2023 | 12 | 3 | 9 | 12/07/2023 | 12/07/2023 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 | 11/17/2023 | 7/10/2026 | Y | EXP | 280 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 714061 | 02176 | 7.6 | Solar | 05_14_92L6 | 08/29/2025 | 10/23/2025 | 5 | 0 | 5 | 11/04/2025 | 11/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 415781 | 01930 | 8.41 | Solar | 05_01_24W5 | 07/11/2022 |  | 30 | 27 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 657806 | 01852 | 7.6 | Solar | 05_01_412L4 | 12/02/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 12/02/2024 | 4/7/2026 | Y | EXP | 425 | 07/30/2025 | 08/04/2025 | 6 | 0 | 6 |  |  |  | Completion Documents |  | N
National Grid | TEWKSBURY | 174293 | 01876 | 2000 | Solar | 05_01_602W2 | 12/27/2011 | 12/27/2011 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2012 | 12/27/2011 | 10/1/2012 | Y | STD | 66 | 01/24/2014 | 02/10/2014 | 11 | 0 | 11 | 11/8/2013 | 11/8/2013 | 12/9/2013 | Connected |  | N
National Grid | METHUEN | 176427 | 01844 | 10 | Solar | 05_05_115W42 | 02/03/2016 | 02/03/2016 | 3 | 3 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 | 02/03/2016 | 1/8/2018 | Y | EXP | 672 | 08/11/2017 | 09/06/2017 | 17 | 0 | 17 | 9/27/2017 | 9/27/2017 | 9/29/2017 | Connected |  | N
National Grid | BILLERICA | 416970 | 01821 | 19 | Solar | 05_05_311W3 | 03/10/2022 | 03/14/2022 | 2 | 0 | 2 | 03/15/2022 | 03/15/2022 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2022 | 03/10/2022 | 6/3/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2022 | Connected |  | N
National Grid | WORCESTER | 530600 | 01606 | 0 | Solar | 05_12_25W5 | 10/09/2023 | 06/13/2023 | 5 | 4 | 1 | 10/17/2023 | 10/17/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 11/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | DUDLEY | 412422 | 01571 | 15.2 | Solar | 05_12_52L1 | 02/23/2022 | 02/24/2022 | 2 | 1 | 1 | 02/25/2022 | 02/25/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 3/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2022 | Connected |  | N
National Grid | HUBBARDSTON | 679992 | 01452 | 11.52 | Solar | 05_14_3L2 | 03/24/2025 | 04/11/2025 | 10 | 6 | 4 | 04/30/2025 | 04/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 664232 | 02724 | 0 | Battery Add-On | 05_14_59L1 | 01/07/2025 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 78 | 25 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 591226 | 01752 | 6 | Solar | 05_14_74L1 | 08/22/2024 | 08/27/2024 | 3 | 0 | 3 | 08/28/2024 | 08/28/2024 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 686883 | 02176 | 12 | Solar | 05_14_9J1 | 04/30/2025 | 07/21/2025 | 54 | 50 | 4 | 07/22/2025 | 07/22/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GLOUCESTER | 440578 | 01930 | 8.41 | Solar | 05_01_24W5 | 07/20/2022 | 08/03/2022 | 11 | 8 | 3 | 08/04/2022 | 08/04/2022 | 28 | 7 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2022 | 07/20/2022 | 6/8/2024 | Y | EXP | 365 | 05/24/2023 | 06/08/2023 | 16 | 0 | 16 |  |  | 6/30/2023 | Connected |  | Y
National Grid | LOWELL | 672839 | 01852 | 700 | Solar | 05_01_412L4 | 04/14/2025 | 10/10/2025 | 124 | 115 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 | 10/21/2025 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ANDOVER | 174382 | 01810 | 2.58 | Solar | 05_01_602W2 | 05/30/2012 | 05/30/2012 | 7 | 0 | 7 | 06/13/2012 | 06/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2012 |  | 8/15/2012 | N | EXP | 26 |  |  | 0 | 0 | 0 | 9/10/2012 | 9/10/2012 | 1/22/2013 | Connected |  | N
National Grid | METHUEN | 176919 | 01844 | 6 | Solar | 05_05_115W42 | 05/05/2016 | 05/05/2016 | 4 | 4 | 0 | 05/12/2016 | 05/12/2016 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 |  | 5/11/2017 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 491445 | 01824 | 15.2 | Solar | 05_05_311W3 | 01/11/2023 | 01/12/2023 | 1 | 0 | 1 | 01/13/2023 | 01/13/2023 | 47 | 25 | 22 | 04/25/2023 | 05/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 05/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 5/16/2023 |  | 8/16/2024 | N | EXP | 365 | 07/26/2023 | 08/10/2023 | 16 | 0 | 16 |  |  | 10/16/2023 | Connected |  | Y
National Grid | WORCESTER | 545446 | 01606 | 6 | Solar | 05_12_25W5 | 08/08/2023 | 08/11/2023 | 3 | 0 | 3 | 08/14/2023 | 08/14/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 9/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2023 | Connected |  | N
National Grid | DUDLEY | 485413 | 01571 | 7.6 | Solar | 05_12_52L1 | 01/05/2023 | 01/06/2023 | 1 | 0 | 1 | 01/09/2023 | 01/09/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 |  | 12/31/2024 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 707901 | 01452 | 3.8 | Solar | 05_14_3L2 | 07/28/2025 | 08/29/2025 | 5 | 0 | 5 | 09/02/2025 | 09/02/2025 | 63 | 48 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 678283 | 02724 | 5.76 | Solar | 05_14_59L1 | 03/19/2025 | 03/28/2025 | 8 | 3 | 5 | 03/31/2025 | 03/31/2025 | 116 | 94 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 593838 | 01752 | 15.2 | Solar | 05_14_74L1 | 03/01/2024 | 04/15/2024 | 28 | 25 | 3 | 04/16/2024 | 04/16/2024 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2024 |  | 6/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2024 | Connected |  | N
National Grid | MELROSE | 175760 | 02176 | 75 | Solar | 05_14_9J1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 113 | 03/06/2015 | 04/28/2015 | 35 | 0 | 35 | 6/2/2015 | 6/2/2015 | 6/2/2015 | Connected |  | N
National Grid | GLOUCESTER | 552074 | 01930 | 5.985 | Solar | 05_01_24W5 | 10/25/2023 | 12/08/2023 | 30 | 25 | 5 | 12/11/2023 | 12/11/2023 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 | 10/25/2023 | 3/15/2025 | Y | EXP | 365 | 05/15/2024 | 07/03/2024 | 50 | 0 | 50 |  |  | 8/13/2024 | Connected |  | N
National Grid | LOWELL | 677465 | 01852 | 20 | Solar | 05_01_412L4 | 03/12/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 25 | 0 | 25 | 05/27/2025 | 07/28/2025 | 43 | 0 | 43 |  |  | 0 | 0 | 0 | 07/28/2025 | 43 | 0 | 43 |  |  | 0 | 0 | 0 | 8/4/2025 |  | 8/21/2026 | N | EXP | 365 | 10/01/2025 | 03/11/2026 | 162 | 0 | 162 |  |  |  | Completion Documents |  | N
National Grid | TEWKSBURY | 174549 | 01876 | 2800 | Solar | 05_01_602W2 | 11/03/2011 | 11/03/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2011 | 02/16/2012 | 39 | 0 | 39 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2013 | 11/03/2011 | 4/1/2014 | Y | STD | 433 |  |  | 0 | 0 | 0 | 6/12/2014 | 6/12/2014 | 6/23/2014 | Connected |  | N
National Grid | METHUEN | 178444 | 01844 | 7.6 | Solar | 05_05_115W42 | 04/03/2018 | 04/03/2018 | 8 | 0 | 8 | 04/27/2018 | 04/27/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2018 |  | 4/9/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  | 11/20/2018 | Connected |  | N
National Grid | CHELMSFORD | 503948 | 01824 | 10 | Solar | 05_05_311W3 | 02/27/2023 | 03/01/2023 | 2 | 0 | 2 | 03/02/2023 | 03/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2023 |  | 8/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2023 | Connected |  | N
National Grid | WORCESTER | 560633 | 01606 | 9.57 | Solar | 05_12_25W5 | 10/04/2023 | 10/05/2023 | 2 | 1 | 1 | 10/06/2023 | 10/06/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 12/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2024 | Connected |  | N
National Grid | DUDLEY | 488780 | 01571 | 15.2 | Solar | 05_12_52L1 | 01/12/2023 | 01/17/2023 | 2 | 0 | 2 | 01/18/2023 | 01/18/2023 | 67 | 25 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 710001 | 01452 | 5.933 | Solar | 05_14_3L2 | 08/06/2025 | 08/26/2025 | 3 | 0 | 3 | 09/03/2025 | 09/03/2025 | 62 | 47 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 681004 | 02724 | 13.8 | Solar | 05_14_59L1 | 03/28/2025 | 04/09/2025 | 3 | 0 | 3 | 04/17/2025 | 04/17/2025 | 22 | 0 | 22 | 06/17/2025 | 07/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 07/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 7/28/2025 | 03/28/2025 | 7/31/2026 | Y | EXP | 365 | 11/14/2025 | 11/21/2025 | 8 | 0 | 8 |  |  | 11/24/2025 | Connected |  | N
National Grid | MARLBOROUGH | 596597 | 01752 | 6 | Solar | 05_14_74L1 | 03/18/2024 | 03/19/2024 | 1 | 0 | 1 | 03/20/2024 | 03/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 | 03/18/2024 | 4/29/2025 | Y | EXP | 365 | 07/31/2024 | 09/28/2024 | 60 | 0 | 60 |  |  | 10/7/2024 | Connected |  | N
National Grid | MELROSE | 418712 | 02176 | 6 | Solar | 05_14_9J1 | 07/26/2022 | 07/28/2022 | 2 | 0 | 2 | 07/29/2022 | 07/29/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2022 | 07/26/2022 | 5/10/2024 | Y | EXP | 365 | 02/22/2023 | 05/10/2023 | 78 | 0 | 78 |  |  | 5/23/2023 | Connected |  | Y
National Grid | GLOUCESTER | 554530 | 01930 | 3.8 | Solar | 05_01_24W5 | 09/12/2023 | 09/18/2023 | 4 | 0 | 4 | 09/19/2023 | 09/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 10/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N
National Grid | LOWELL | 699718 | 01852 | 10 | Solar | 05_01_412L4 | 06/19/2025 | 07/02/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 06/19/2025 | 9/5/2026 | Y | EXP | 365 | 02/13/2026 | 03/11/2026 | 27 | 0 | 27 |  |  |  | Completion Documents |  | N
National Grid | TEWKSBURY | 174681 | 01876 | 30 | Solar | 05_01_602W2 | 01/08/2014 | 01/08/2014 | 2 | 0 | 2 | 01/13/2014 | 01/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2014 | 01/08/2014 | 6/20/2014 | Y | EXP | 142 |  |  | 0 | 0 | 0 | 1/29/2014 | 1/29/2014 | 6/24/2014 | Connected |  | N
National Grid | METHUEN | 194988 | 01844 | 7.6 | Solar | 05_05_115W42 | 09/04/2018 | 10/29/2018 | 19 | 19 | 0 | 10/30/2018 | 10/30/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 559734 | 01824 | 400 | Solar | 05_05_311W3 | 10/12/2023 | 12/08/2023 | 39 | 29 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 | 01/26/2024 | 32 | 12 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 603372 | 01606 | 7.54 | Solar | 05_12_25W5 | 04/19/2024 | 05/07/2024 | 13 | 11 | 2 | 05/08/2024 | 05/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 |  | 5/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | DUDLEY | 570135 | 01571 | 15.2 | Solar | 05_12_52L1 | 11/09/2023 | 11/27/2023 | 11 | 9 | 2 | 11/28/2023 | 11/28/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2024 |  | 2/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2024 | Connected |  | Y
National Grid | HUBBARDSTON | 642855 | 01452 | 120 | Solar | 05_14_3L4 | 09/30/2024 | 01/30/2025 | 81 | 73 | 8 | 01/31/2025 | 01/31/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 | 09/30/2024 | 3/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | FALL RIVER | 681911 | 02724 | 15.2 | Solar | 05_14_59L1 | 04/01/2025 | 04/10/2025 | 8 | 3 | 5 | 04/11/2025 | 04/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 |  | 5/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2025 | Connected |  | N
National Grid | MARLBOROUGH | 597545 | 01752 | 7.6 | Solar | 05_14_74L1 | 03/21/2024 | 04/30/2024 | 28 | 25 | 3 | 05/01/2024 | 05/01/2024 | 10 | 3 | 7 | 05/17/2024 | 07/09/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 07/09/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 432583 | 02176 | 15.2 | Solar | 05_14_9J1 | 05/23/2022 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 587312 | 01930 | 7.6 | Solar | 05_01_24W5 | 02/03/2024 | 02/05/2024 | 1 | 0 | 1 | 02/06/2024 | 02/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 02/03/2024 | 2/22/2025 | Y | EXP | 365 | 05/04/2024 | 08/15/2024 | 104 | 0 | 104 |  |  | 10/25/2024 | Connected |  | N
National Grid | LOWELL | 734536 | 01852 | 5.76 | Solar | 05_01_412L4 | 11/18/2025 | 11/19/2025 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ANDOVER | 174986 | 01810 | 1000 | Solar | 05_01_602W2 | 11/03/2011 | 11/03/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2011 | 02/16/2012 | 39 | 0 | 39 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2013 |  | 12/31/2012 | N | STD | 23 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 209761 | 01844 | 7.04 | Solar | 05_05_115W42 | 03/20/2019 | 03/28/2019 | 5 | 0 | 5 | 03/29/2019 | 03/29/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2019 | 03/20/2019 | 4/10/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2019 | Connected |  | N
National Grid | CHELMSFORD | 528910 | 01824 | 360 | Solar | 05_05_311W3 | 09/29/2023 | 10/30/2023 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 12/01/2023 | 22 | 0 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 623061 | 01606 | 6 | Solar | 05_12_25W5 | 07/08/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 574937 | 01571 | 23 | Solar | 05_12_52L1 | 11/30/2023 | 12/04/2023 | 2 | 0 | 2 | 12/05/2023 | 12/05/2023 | 114 | 90 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 |  | 5/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | HUBBARDSTON | 659689 | 01452 | 7.6 | Solar | 05_14_3L4 | 12/10/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FALL RIVER | 686755 | 02724 | 19.14 | Solar | 05_14_59L1 | 04/22/2025 | 04/29/2025 | 5 | 0 | 5 | 04/30/2025 | 04/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 |  | 5/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | MARLBOROUGH | 600465 | 01752 | 10 | Solar | 05_14_74L1 | 04/04/2024 | 04/16/2024 | 8 | 7 | 1 | 04/17/2024 | 04/17/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/04/2024 | 5/25/2025 | Y | EXP | 365 | 08/01/2024 | 01/02/2025 | 155 | 0 | 155 |  |  | 4/1/2025 | Connected |  | N
National Grid | MELROSE | 437921 | 02176 | 15.2 | Solar | 05_14_9J1 | 06/15/2022 | 06/16/2022 | 1 | 0 | 1 | 06/17/2022 | 06/17/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | GLOUCESTER | 615561 | 01930 | 3.8 | Solar | 05_01_24W5 | 06/04/2024 | 06/27/2024 | 12 | 11 | 1 | 06/28/2024 | 06/28/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 739355 | 01852 | 7.6 | Solar | 05_01_412L4 | 12/10/2025 | 12/11/2025 | 1 | 0 | 1 | 01/02/2026 | 01/02/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2026 | 12/10/2025 | 2/9/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ANDOVER | 175020 | 01810 | 150 | Solar | 05_01_602W2 | 10/08/2012 | 10/08/2012 | 7 | 0 | 7 | 10/18/2012 | 10/18/2012 | 342 | 0 | 342 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2013 |  | 6/3/2013 | N | EXP | 21 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 376028 | 01844 | 3.8 | Solar | 05_05_115W42 | 08/25/2021 | 08/27/2021 | 2 | 0 | 2 | 08/30/2021 | 08/30/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2021 | 08/25/2021 | 1/24/2023 | Y | EXP | 365 | 12/02/2021 | 01/12/2022 | 42 | 0 | 42 |  |  | 2/7/2022 | Connected |  | Y
National Grid | CHELMSFORD | 569808 | 01824 | 6 | Solar | 05_05_311W3 | 11/20/2023 | 11/30/2023 | 8 | 4 | 4 | 12/01/2023 | 12/01/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 | 11/20/2023 | 2/4/2026 | Y | EXP | 730 | 07/25/2024 | 09/12/2024 | 50 | 0 | 50 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 644273 | 01606 | 5.76 | Solar | 05_12_25W5 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 12/3/2025 | Y | EXP | 365 | 03/15/2025 | 03/21/2025 | 7 | 0 | 7 |  |  | 4/10/2025 | Connected |  | N
National Grid | CHARLTON | 581847 | 01507 | 0 | Solar | 05_12_52L1 | 01/08/2024 | 02/07/2024 | 22 | 19 | 3 | 02/08/2024 | 02/08/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 679179 | 01440 | 250 | Solar | 05_14_3L4 | 04/14/2025 | 05/19/2025 | 24 | 14 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | FALL RIVER | 709203 | 02724 | 22.8 | Solar | 05_14_59L1 | 08/03/2025 | 08/21/2025 | 13 | 10 | 3 | 08/22/2025 | 08/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2025 | Connected |  | N
National Grid | MARLBOROUGH | 605469 | 01752 | 11.4 | Solar | 05_14_74L1 | 04/23/2024 | 04/30/2024 | 2 | 0 | 2 | 05/01/2024 | 05/01/2024 | 12 | 5 | 7 | 06/03/2024 | 07/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 07/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 6/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 176716 | 02176 | 10 | Solar | 05_14_9J3 | 01/11/2016 | 01/11/2016 | 1 | 1 | 0 | 01/13/2016 | 01/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 |  | 1/17/2017 | N | EXP | 354 |  |  | 0 | 0 | 0 | 3/7/2016 | 3/7/2016 | 8/11/2016 | Connected |  | N
National Grid | GLOUCESTER | 643869 | 01930 | 10 | Solar | 05_01_24W5 | 10/04/2024 | 10/17/2024 | 4 | 0 | 4 | 10/18/2024 | 10/18/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/04/2024 | 12/9/2025 | Y | EXP | 365 | 02/13/2025 | 03/21/2025 | 37 | 0 | 37 |  |  | 4/16/2025 | Connected |  | N
National Grid | LOWELL | 174760 | 01852 | 497.6 | Solar | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 4/28/2017 | Y | STD | 840 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 4/18/2017 | Connected |  | N
National Grid | ANDOVER | 175019 | 01810 | 350 | Solar | 05_01_602W2 | 10/08/2012 | 10/08/2012 | 7 | 0 | 7 | 10/18/2012 | 10/18/2012 | 919 | 0 | 919 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2013 |  | 12/31/2016 | N | EXP | 1328 |  |  | 0 | 0 | 0 |  |  | 9/10/2013 | Connected |  | N
National Grid | METHUEN | 387941 | 01844 | 3 | Solar | 05_05_115W42 | 10/21/2021 | 12/21/2021 | 9 | 4 | 5 | 11/04/2021 | 11/04/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 10/21/2021 | 5/25/2024 | Y | EXP | 365 | 01/26/2023 | 05/15/2023 | 110 | 0 | 110 |  |  | 7/11/2023 | Connected |  | N
National Grid | CHELMSFORD | 570780 | 01824 | 10 | Solar | 05_05_311W3 | 11/20/2023 | 11/21/2023 | 1 | 0 | 1 | 11/22/2023 | 11/22/2023 | 64 | 41 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2024 | 11/20/2023 | 4/18/2025 | Y | EXP | 365 | 06/08/2024 | 09/03/2024 | 88 | 0 | 88 |  |  | 11/2/2024 | Connected |  | N
National Grid | WORCESTER | 652699 | 01606 | 5.76 | Solar | 05_12_25W5 | 11/07/2024 | 11/25/2024 | 4 | 0 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 11/07/2024 | 2/14/2026 | Y | EXP | 365 | 07/02/2025 | 10/11/2025 | 102 | 0 | 102 |  |  | 11/14/2025 | Connected |  | N
National Grid | DUDLEY | 593568 | 01571 | 0 | Solar | 05_12_52L1 | 03/18/2024 | 03/19/2024 | 1 | 0 | 1 | 03/20/2024 | 03/20/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | GARDNER | 727228 | 01440 | 7.6 | Solar | 05_14_3L4 | 10/16/2025 | 01/22/2026 | 1 | 0 | 1 | 02/02/2026 | 02/02/2026 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2026 |  | 3/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 755366 | 02724 | 5.76 | Solar | 05_14_59L3 | 03/09/2026 | 03/16/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MARLBOROUGH | 609378 | 01752 | 5.76 | Solar | 05_14_74L1 | 05/07/2024 | 05/14/2024 | 1 | 0 | 1 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 11/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N
National Grid | MELROSE | 178384 | 02176 | 3.8 | Solar | 05_14_9J3 | 01/15/2018 | 01/15/2018 | 32 | 3 | 29 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 |  | 1/21/2019 | N | EXP | 314 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 665488 | 01930 | 3.8 | Solar | 05_01_24W5 | 01/14/2025 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174759 | 01852 | 497.6 | Solar | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 6/30/2017 | Y | STD | 903 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 6/28/2017 | Connected |  | N
National Grid | TEWKSBURY | 175067 | 01876 | 675 | Solar | 05_01_602W2 | 03/28/2013 | 03/28/2013 | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2013 | 06/03/2013 | 25 | 0 | 25 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2013 | 03/28/2013 | 2/3/2014 | Y | STD | 94 | 10/09/2014 | 12/10/2014 | 41 | 0 | 41 | 12/23/2014 | 12/23/2014 | 12/23/2014 | Connected |  | N
National Grid | METHUEN | 422789 | 01844 | 3.8 | Solar | 05_05_115W42 | 04/07/2022 | 08/04/2022 | 2 | 0 | 2 | 08/05/2022 | 08/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 584824 | 01824 | 7.6 | Solar | 05_05_311W3 | 01/22/2024 | 01/25/2024 | 3 | 0 | 3 | 01/26/2024 | 01/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 684394 | 01606 | 7.6 | Solar | 05_12_25W5 | 04/10/2025 | 05/30/2025 | 1 | 0 | 1 | 06/02/2025 | 06/02/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 635534 | 01571 | 5.76 | Solar | 05_12_52L1 | 09/04/2024 | 09/06/2024 | 3 | 1 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 |  | 9/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | HUBBARDSTON | 748135 | 01452 | 3.8 | Solar | 05_14_3L4 | 01/29/2026 | 02/03/2026 | 3 | 0 | 3 | 03/03/2026 | 03/03/2026 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 176542 | 02724 | 10 | Solar | 05_14_59L3 | 03/30/2016 | 03/30/2016 | 2 | 2 | 0 | 04/05/2016 | 04/05/2016 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 |  | 4/6/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 610663 | 01752 | 10 | Solar | 05_14_74L1 | 05/14/2024 | 05/29/2024 | 1 | 0 | 1 | 05/30/2024 | 05/30/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 | 05/14/2024 | 12/31/2025 | Y | EXP | 365 | 08/28/2025 | 11/21/2025 | 86 | 0 | 86 |  |  | 11/24/2025 | Connected |  | N
National Grid | MELROSE | 249645 | 02176 | 3.8 | Solar | 05_14_9J3 | 08/30/2019 | 09/04/2019 | 1 | 0 | 1 | 09/05/2019 | 09/05/2019 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2019 | 08/30/2019 | 10/13/2021 | Y | EXP | 365 | 08/04/2020 | 08/21/2020 | 17 | 0 | 17 |  |  | 11/18/2020 | Connected |  | N
National Grid | GLOUCESTER | 672053 | 01930 | 5.76 | Solar | 05_01_24W5 | 02/13/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | LOWELL | 174758 | 01852 | 497.6 | Solar | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 8/31/2017 | Y | STD | 965 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 8/11/2017 | Connected |  | N
National Grid | TEWKSBURY | 175102 | 01876 | 1000 | Solar | 05_01_602W2 | 11/02/2012 | 11/02/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2012 | 01/14/2013 | 36 | 0 | 36 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2013 | 11/02/2012 | 4/1/2014 | Y | STD | 319 | 03/21/2014 | 04/29/2014 | 26 | 0 | 26 | 6/13/2014 | 6/13/2014 | 6/13/2014 | Connected |  | N
National Grid | METHUEN | 445797 | 01844 | 6 | Solar | 05_05_115W42 | 07/27/2022 | 07/29/2022 | 2 | 0 | 2 | 08/01/2022 | 08/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2022 |  | 9/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2022 | Connected |  | Y
National Grid | CHELMSFORD | 603043 | 01824 | 10 | Solar | 05_05_311W3 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 704751 | 01606 | 15.2 | Solar | 05_12_26L1 | 07/14/2025 | 07/15/2025 | 1 | 0 | 1 | 07/16/2025 | 07/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DUDLEY | 640394 | 01571 | 3 | Solar | 05_12_52L1 | 09/24/2024 | 11/26/2024 | 28 | 27 | 1 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 | 09/24/2024 | 3/24/2026 | Y | EXP | 365 | 04/24/2025 | 08/06/2025 | 105 | 0 | 105 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 754632 | 01440 | 10 | Solar | 05_14_3L4 | 03/06/2026 | 03/10/2026 | 2 | 0 | 2 | 03/24/2026 | 03/24/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 176927 | 02724 | 7.6 | Solar | 05_14_59L3 | 11/20/2015 | 11/20/2015 | 2 | 2 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2015 |  | 11/25/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 5/19/2016 | 5/19/2016 | 5/23/2016 | Connected |  | N
National Grid | MARLBOROUGH | 611903 | 01752 | 7.6 | Solar | 05_14_74L1 | 07/04/2024 | 10/14/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TOPSFIELD | 393377 | 01983 | 9.772 | Solar | 05_14_9J3 | 11/04/2021 | 11/16/2021 | 8 | 5 | 3 | 11/17/2021 | 11/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 12/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2022 | Connected |  | Y
National Grid | GLOUCESTER | 673375 | 01930 | 999 | Solar | 05_01_26W1 | 11/07/2025 | 01/15/2026 | 44 | 35 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/16/2026 | 02/09/2026 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LOWELL | 174757 | 01852 | 448 | Solar | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 4/30/2017 | Y | STD | 842 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 4/18/2017 | Connected |  | N
National Grid | TEWKSBURY | 175302 | 01876 | 1000 | Solar | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 | 01/17/2015 | 10/16/2019 | Y | STD | 1079 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 480673 | 01844 | 6 | Solar | 05_05_115W42 | 12/07/2022 | 12/11/2022 | 3 | 0 | 3 | 12/12/2022 | 12/12/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 |  | 2/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2023 | Connected |  | N
National Grid | CHELMSFORD | 625953 | 01824 | 3.8 | Solar | 05_05_311W3 | 07/18/2024 | 07/25/2024 | 2 | 0 | 2 | 07/26/2024 | 07/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 07/18/2024 | 9/24/2025 | Y | EXP | 365 | 10/11/2024 | 12/03/2024 | 54 | 0 | 54 |  |  | 12/27/2024 | Connected |  | N
National Grid | AUBURN | 711334 | 01501 | 11.5 | Battery Add-On | 05_12_26L1 | 08/12/2025 | 08/18/2025 | 4 | 0 | 4 | 08/19/2025 | 08/19/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DUDLEY | 643700 | 01571 | 5.76 | Solar | 05_12_52L1 | 10/01/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/01/2024 | 12/12/2025 | Y | EXP | 365 | 01/06/2025 | 02/11/2025 | 36 | 0 | 36 |  |  | 2/28/2025 | Connected |  | N
National Grid | WESTMINSTER | 387537 | 01473 | 18.148 | Solar | 05_14_3L4 | 10/12/2021 | 01/07/2022 | 6 | 0 | 6 | 10/21/2021 | 10/21/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 |  | 1/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2022 | Connected |  | N
National Grid | FALL RIVER | 177144 | 02724 | 10 | Solar | 05_14_59L3 | 05/29/2016 | 05/29/2016 | 2 | 2 | 0 | 06/03/2016 | 06/03/2016 | 164 | 0 | 164 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 |  | 6/6/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 617697 | 01752 | 10 | Solar | 05_14_74L1 | 06/13/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 32 | 21 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TOPSFIELD | 719817 | 01983 | 3.8 | Solar | 05_12_5C3 | 09/17/2025 | 11/04/2025 | 4 | 0 | 4 | 11/05/2025 | 11/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GLOUCESTER | 729908 | 01930 | 5.76 | Solar | 05_01_26W1 | 10/29/2025 | 12/01/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 60 | 43 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 175265 | 01852 | 15.8 | Solar | 05_01_412L4 | 06/16/2014 | 06/16/2014 | 6 | 0 | 6 | 06/26/2014 | 06/26/2014 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2014 |  | 9/1/2014 | N | EXP | 41 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 175301 | 01876 | 1000 | Solar | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 |  | 10/16/2019 | N | STD | 1079 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 480438 | 01844 | 3.8 | Solar | 05_05_115W42 | 11/29/2022 | 12/06/2022 | 5 | 0 | 5 | 12/07/2022 | 12/07/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 5/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2023 | Connected |  | N
National Grid | MALDEN | 641237 | 02148 | 5.76 | Solar | 05_05_311W3 | 09/18/2024 | 10/08/2024 | 3 | 0 | 3 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/18/2024 | 12/4/2025 | Y | EXP | 365 | 02/11/2025 | 03/04/2025 | 22 | 0 | 22 |  |  | 4/1/2025 | Connected |  | N
National Grid | AUBURN | 745104 | 01501 | 6.84 | Solar | 05_12_26L1 | 02/05/2026 | 02/09/2026 | 2 | 0 | 2 | 02/10/2026 | 02/10/2026 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DUDLEY | 645714 | 01571 | 10 | Solar | 05_12_52L1 | 10/10/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 12/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | WESTMINSTER | 422062 | 01473 | 0 | Battery Add-On | 05_14_3L4 | 10/05/2022 | 06/22/2023 | 176 | 166 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2023 | 07/18/2023 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 177325 | 02724 | 6 | Solar | 05_14_59L3 | 06/17/2016 | 06/17/2016 | 1 | 1 | 0 | 06/22/2016 | 06/22/2016 | 73 | 0 | 73 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2016 |  | 6/26/2017 | N | EXP | 354 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 619049 | 01752 | 3.8 | Solar | 05_14_74L1 | 06/19/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 67 | 52 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 | 06/19/2024 | 1/1/2026 | Y | EXP | 365 | 12/11/2024 | 04/04/2025 | 115 | 26 | 89 |  |  | 8/29/2025 | Connected |  | N
National Grid | TOPSFIELD | 176869 | 01983 | 10 | Solar | 05_12_5C3 | 03/01/2016 | 03/01/2016 | 1 | 1 | 0 | 03/03/2016 | 03/03/2016 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2016 |  | 3/7/2017 | N | EXP | 323 |  |  | 0 | 0 | 0 | 4/18/2016 | 4/18/2016 |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 739680 | 01930 | 10 | Solar | 05_01_26W1 | 12/11/2025 | 12/15/2025 | 1 | 0 | 1 | 01/13/2026 | 01/13/2026 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LOWELL | 175582 | 01852 | 19 | Solar | 05_01_412L4 | 12/14/2014 | 12/14/2014 | 6 | 4 | 2 | 12/23/2014 | 12/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2015 |  | 2/28/2015 | N | EXP | 53 |  |  | 0 | 0 | 0 | 1/7/2016 | 1/7/2016 | 1/7/2016 | Connected |  | N
National Grid | TEWKSBURY | 175300 | 01876 | 4875 | Solar | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 | 01/17/2015 | 6/7/2021 | Y | STD | 1373 | 10/28/2020 | 03/26/2021 | 149 | 0 | 149 |  |  | 6/4/2021 | Connected |  | N
National Grid | LAWRENCE | 482372 | 01844 | 3 | Solar | 05_05_115W42 | 12/05/2022 | 12/19/2022 | 10 | 5 | 5 | 12/20/2022 | 12/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 5/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | Y
National Grid | MALDEN | 645368 | 02148 | 3.8 | Solar | 05_05_311W3 | 10/07/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 63 | 39 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 10/07/2024 | 3/4/2026 | Y | EXP | 365 | 04/30/2025 | 06/05/2025 | 37 | 0 | 37 |  |  | 6/5/2025 | Connected |  | N
National Grid | AUBURN | 175550 | 01501 | 33.3 | Solar | 05_12_26L1 | 04/11/2014 | 04/11/2014 | 6 | 0 | 6 | 04/23/2014 | 04/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2014 |  | 8/29/2014 | N | EXP | 108 |  |  | 0 | 0 | 0 | 6/17/2014 | 6/17/2014 | 9/2/2014 | Connected |  | N
National Grid | DUDLEY | 656918 | 01571 | 6.282 | Solar | 05_12_52L1 | 11/27/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | WESTMINSTER | 500890 | 01473 | 100 | Solar | 05_14_3L4 | 02/24/2023 | 04/07/2023 | 30 | 21 | 9 | 04/10/2023 | 04/10/2023 | 43 | 18 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2023 | 02/24/2023 | 1/27/2026 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 177655 | 02724 | 2838 | Solar | 05_14_59L3 | 11/09/2017 | 11/09/2017 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 01/30/2018 | 34 | 0 | 34 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 | 11/09/2017 | 4/10/2022 | Y | STD | 266 | 11/17/2021 | 01/13/2022 | 57 | 0 | 57 |  |  | 2/18/2022 | Connected |  | N
National Grid | MARLBOROUGH | 630260 | 01752 | 10 | Solar | 05_14_74L1 | 08/05/2024 | 08/21/2024 | 9 | 6 | 3 | 08/22/2024 | 08/22/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/05/2024 | 9/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | TOPSFIELD | 177760 | 01983 | 468 | Solar | 05_12_5C3 | 08/02/2017 | 08/02/2017 | 95 | 95 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2017 | 01/25/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/7/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 742988 | 01930 | 5.76 | Solar | 05_01_26W1 | 01/02/2026 | 01/05/2026 | 3 | 0 | 3 | 01/23/2026 | 01/23/2026 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 175747 | 01852 | 1000 | Solar | 05_01_412L4 | 10/30/2014 | 10/30/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 12/08/2014 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 | 10/30/2014 | 9/1/2017 | Y | STD | 707 | 06/05/2017 | 08/16/2017 | 51 | 0 | 51 | 8/21/2017 | 8/21/2017 | 9/14/2017 | Connected |  | N
National Grid | TEWKSBURY | 175333 | 01876 | 1000 | Solar | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 |  | 10/16/2019 | N | STD | 1079 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 482174 | 01844 | 3.8 | Solar | 05_05_115W42 | 12/20/2022 | 12/26/2022 | 4 | 0 | 4 | 12/27/2022 | 12/27/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 2/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | N
National Grid | MALDEN | 657483 | 02148 | 3.8 | Solar | 05_05_311W3 | 11/27/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/27/2024 | 2/20/2026 | Y | EXP | 365 | 03/29/2025 | 03/28/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 177483 | 01501 | 19 | Solar | 05_12_26L1 | 09/22/2016 | 09/22/2016 | 2 | 2 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2016 |  | 10/13/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 9/26/2017 | 9/26/2017 | 9/26/2017 | Connected |  | N
National Grid | DUDLEY | 662099 | 01571 | 3.8 | Solar | 05_12_52L1 | 12/20/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/20/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | WESTMINSTER | 556411 | 01473 | 250 | Solar | 05_14_3L4 | 12/01/2023 | 12/26/2023 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 | 01/23/2024 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2024 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 178219 | 02724 | 7.6 | Solar | 05_14_59L3 | 04/13/2018 | 04/13/2018 | 10 | 0 | 10 | 04/30/2018 | 04/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/21/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 631163 | 01752 | 10 | Solar | 05_14_74L1 | 08/08/2024 | 08/20/2024 | 4 | 0 | 4 | 08/21/2024 | 08/21/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/08/2024 | 11/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | TOPSFIELD | 563209 | 01983 | 10 | Solar | 05_12_5C3 | 12/06/2023 | 03/07/2024 | 52 | 50 | 2 | 03/08/2024 | 03/08/2024 | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  | 5/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | GLOUCESTER | 175987 | 01930 | 1000 | Solar | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/30/2015 | N | STD | 412 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 175872 | 01852 | 56 | Solar | 05_01_412L4 | 09/28/2015 | 09/28/2015 | 3 | 3 | 0 | 10/02/2015 | 10/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2015 |  | 10/4/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 2/24/2016 | 2/24/2016 | 2/24/2016 | Connected |  | N
National Grid | TEWKSBURY | 175332 | 01876 | 1000 | Solar | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 | 01/17/2015 | 10/16/2019 | Y | STD | 1079 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 484096 | 01844 | 10 | Solar | 05_05_115W42 | 12/15/2022 | 12/20/2022 | 3 | 0 | 3 | 12/21/2022 | 12/21/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 1/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2023 | Connected |  | N
National Grid | MALDEN | 673014 | 02148 | 3.8 | Solar | 05_05_311W3 | 02/19/2025 | 03/26/2025 | 17 | 12 | 5 | 04/23/2025 | 04/23/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | AUBURN | 178107 | 01501 | 103.5 | Solar | 05_12_26L1 | 11/03/2017 | 11/03/2017 | 41 | 41 | 0 | 01/08/2018 | 01/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 |  | 9/16/2019 | N | EXP | 616 |  |  | 0 | 0 | 0 |  |  | 9/23/2019 | Connected |  | N
National Grid | WEBSTER | 668880 | 01570 | 3.8 | Solar | 05_12_52L1 | 02/03/2025 | 03/11/2025 | 14 | 9 | 5 | 03/12/2025 | 03/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 | 02/03/2025 | 4/18/2026 | Y | EXP | 365 | 10/28/2025 | 11/24/2025 | 28 | 0 | 28 |  |  | 12/10/2025 | Connected |  | N
National Grid | WESTMINSTER | 551159 | 01473 | 6 | Solar | 05_14_3L4 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 |  | 6/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | FALL RIVER | 178637 | 02724 | 7.6 | Solar | 05_14_59L3 | 04/09/2018 | 04/09/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 632110 | 01752 | 10 | Solar | 05_14_74L1 | 08/21/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 08/21/2024 | 10/29/2025 | Y | EXP | 365 | 03/05/2025 | 03/04/2025 | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | TOPSFIELD | 683574 | 01983 | 16.53 | Solar | 05_12_5C3 | 04/08/2025 | 04/14/2025 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2025 | Connected |  | N
National Grid | GLOUCESTER | 175986 | 01930 | 1000 | Solar | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/30/2015 | N | STD | 412 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 175895 | 01852 | 7.6 | Solar | 05_01_412L4 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2015 | 08/04/2015 | 8/10/2016 | Y | EXP | 358 | 09/13/2016 | 09/23/2016 | 8 | 0 | 8 | 8/18/2015 | 8/18/2015 | 9/28/2016 | Connected |  | N
National Grid | TEWKSBURY | 175378 | 01876 | 278.4 | Solar | 05_01_602W2 | 07/09/2014 | 07/09/2014 | 1 | 0 | 1 | 07/10/2014 | 07/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2014 |  | 11/28/2014 | N | EXP | 121 |  |  | 0 | 0 | 0 | 10/16/2014 | 10/16/2014 | 12/31/2014 | Connected |  | N
National Grid | METHUEN | 486948 | 01844 | 3 | Solar | 05_05_115W42 | 01/17/2023 | 01/18/2023 | 1 | 0 | 1 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 673800 | 02148 | 7.6 | Solar | 05_05_311W3 | 02/24/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | AUBURN | 191835 | 01501 | 22.8 | Solar | 05_12_26L1 | 07/25/2018 | 09/04/2018 | 12 | 0 | 12 | 09/05/2018 | 09/05/2018 | 47 | 36 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  | 12/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2019 | Connected |  | N
National Grid | DUDLEY | 715316 | 01571 | 20 | Solar | 05_12_52L1 | 08/28/2025 | 09/05/2025 | 4 | 0 | 4 | 09/08/2025 | 09/08/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | GARDNER | 595183 | 01440 | 3.8 | Solar | 05_14_3L4 | 03/13/2024 | 03/14/2024 | 1 | 0 | 1 | 03/15/2024 | 03/15/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 03/13/2024 | 4/1/2025 | Y | EXP | 365 | 05/07/2024 | 08/08/2024 | 94 | 0 | 94 |  |  | 9/16/2024 | Connected |  | N
National Grid | FALL RIVER | 183612 | 02724 | 7.6 | Solar | 05_14_59L3 | 04/23/2018 | 04/23/2018 | 0 | 0 | 0 | 07/02/2018 | 07/02/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2019 | Connected |  | N
National Grid | MARLBOROUGH | 644612 | 01752 | 10 | Solar | 05_14_74L1 | 10/02/2024 | 11/07/2024 | 1 | 0 | 1 | 11/08/2024 | 11/08/2024 | 52 | 34 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 10/02/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | TOPSFIELD | 745544 | 01983 | 11.4 | Solar | 05_12_67J1 | 01/15/2026 |  | 25 | 24 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | GLOUCESTER | 175985 | 01930 | 1000 | Solar | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/30/2015 | N | STD | 412 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 175969 | 01852 | 19.75 | Solar | 05_01_412L4 | 08/07/2015 | 08/07/2015 | 0 | 0 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2015 |  | 8/17/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 9/15/2016 | 9/15/2016 | 9/15/2016 | Connected |  | N
National Grid | TEWKSBURY | 175367 | 01876 | 960 | Solar | 05_01_602W2 | 11/17/2014 | 11/17/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 | 12/24/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 | 05/13/2016 | 09/19/2016 | 87 | 0 | 87 | 1/17/2017 | 11/17/2014 | 3/31/2017 | Y | STD | 73 | 03/29/2017 | 03/27/2017 | 0 | 0 | 0 | 4/21/2017 | 4/21/2017 | 5/5/2017 | Connected |  | N
National Grid | METHUEN | 500885 | 01844 | 3.8 | Solar | 05_05_115W42 | 03/10/2023 | 03/20/2023 | 6 | 0 | 6 | 03/21/2023 | 03/21/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2023 |  | 8/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | MEDFORD | 681814 | 02155 | 5.76 | Solar | 05_05_311W3 | 04/01/2025 | 05/20/2025 | 30 | 25 | 5 | 05/21/2025 | 05/21/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 203602 | 01501 | 10 | Solar | 05_12_26L1 | 12/18/2018 | 12/31/2018 | 7 | 0 | 7 | 01/02/2019 | 01/02/2019 | 242 | 19 | 223 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 | 12/18/2018 | 3/3/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2020 | Connected |  | N
National Grid | DUDLEY | 724732 | 01571 | 19.2 | Solar | 05_12_52L1 | 10/13/2025 | 10/14/2025 | 1 | 0 | 1 | 10/15/2025 | 10/15/2025 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2026 | Connected |  | N
National Grid | HUBBARDSTON | 601232 | 01452 | 6 | Solar | 05_14_3L4 | 04/08/2024 | 04/10/2024 | 2 | 0 | 2 | 04/11/2024 | 04/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 189478 | 02724 | 7.6 | Solar | 05_14_59L3 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 | 07/02/2018 | 07/02/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 645335 | 01752 | 3.8 | Solar | 05_14_74L1 | 10/07/2024 | 12/04/2024 | 25 | 20 | 5 | 12/05/2024 | 12/05/2024 | 30 | 9 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 10/07/2024 | 2/25/2026 | Y | EXP | 365 | 05/29/2025 | 05/28/2025 | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | TOPSFIELD | 331978 | 01983 | 7.6 | Solar | 05_12_67J1 | 12/16/2020 | 01/08/2021 | 15 | 12 | 3 | 01/11/2021 | 01/11/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2021 |  | 1/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2021 | Connected |  | N
National Grid | GLOUCESTER | 175984 | 01930 | 1000 | Solar | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/21/2015 | N | STD | 421 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176200 | 01852 | 17.6 | Solar | 05_01_412L4 | 02/11/2015 | 02/11/2015 | 4 | 2 | 2 | 02/19/2015 | 02/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2015 |  | 12/31/2016 | N | EXP | 668 |  |  | 0 | 0 | 0 | 3/4/2015 | 3/4/2015 | 12/11/2015 | Connected |  | N
National Grid | TEWKSBURY | 175403 | 01876 | 960 | Solar | 05_01_602W2 | 11/21/2014 | 11/21/2014 | 8 | 7 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2014 | 01/06/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 05/13/2016 | 09/19/2016 | 87 | 0 | 87 | 1/17/2017 | 11/21/2014 | 4/10/2017 | Y | STD | 83 | 02/10/2017 | 09/05/2017 | 142 | 0 | 142 | 4/21/2017 | 4/21/2017 | 5/5/2017 | Connected |  | N
National Grid | METHUEN | 504881 | 01844 | 6 | Solar | 05_05_115W42 | 03/09/2023 | 03/13/2023 | 2 | 0 | 2 | 03/14/2023 | 03/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2023 | 03/09/2023 | 7/13/2024 | Y | EXP | 365 | 06/20/2023 | 07/13/2023 | 24 | 0 | 24 |  |  | 8/23/2023 | Connected |  | N
National Grid | MEDFORD | 727492 | 02155 | 20.14 | Solar | 05_05_311W3 | 10/17/2025 | 10/20/2025 | 1 | 0 | 1 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  | 11/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2026 | Connected |  | N
National Grid | AUBURN | 208186 | 01540 | 10 | Solar | 05_12_26L1 | 02/13/2019 | 02/19/2019 | 3 | 3 | 0 | 02/20/2019 | 02/20/2019 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2019 | 02/13/2019 | 10/30/2019 | Y | EXP | 236 | 06/28/2019 | 07/24/2019 | 26 | 0 | 26 |  |  | 7/27/2019 | Connected |  | N
National Grid | DUDLEY | 644938 | 01571 | 4.225 | Solar | 05_12_5C2 | 10/03/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/03/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | HUBBARDSTON | 641328 | 01452 | 6 | Solar | 05_14_3L4 | 09/20/2024 | 09/30/2024 | 4 | 0 | 4 | 10/01/2024 | 10/01/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 | 09/20/2024 | 11/20/2025 | Y | EXP | 365 | 02/19/2025 | 03/12/2025 | 22 | 0 | 22 |  |  | 3/19/2025 | Connected |  | Y
National Grid | FALL RIVER | 321076 | 02724 | 6.38 | Solar | 05_14_59L3 | 10/22/2020 | 10/23/2020 | 1 | 1 | 0 | 10/26/2020 | 10/26/2020 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 | 10/22/2020 | 10/22/2021 | Y | EXP | 365 | 03/19/2021 | 03/18/2021 | 0 | 0 | 0 |  |  | 4/28/2021 | Connected |  | N
National Grid | MARLBOROUGH | 646267 | 01752 | 10 | Solar | 05_14_74L1 | 10/21/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/21/2024 | 1/19/2026 | Y | EXP | 365 | 03/04/2025 | 03/03/2025 | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | TOPSFIELD | 331636 | 01983 | 10 | Solar | 05_12_67J1 | 01/08/2021 | 01/12/2021 | 2 | 2 | 0 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 | 01/08/2021 | 1/11/2022 | Y | EXP | 365 | 03/25/2021 | 06/24/2021 | 91 | 0 | 91 |  |  | 6/30/2021 | Connected |  | N
National Grid | MALDEN | 175983 | 02148 | 4875 | Solar | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 03/20/2015 | 5/25/2022 | Y | STD | 610 |  |  | 0 | 0 | 0 |  |  | 5/17/2022 | Connected |  | N
National Grid | LOWELL | 176592 | 01852 | 10 | Solar | 05_01_412L4 | 10/08/2015 | 10/08/2015 | 1 | 1 | 0 | 10/13/2015 | 10/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2015 | 10/08/2015 | 10/14/2016 | Y | EXP | 347 | 08/31/2016 | 10/28/2016 | 40 | 0 | 40 | 11/2/2015 | 11/2/2015 | 11/2/2016 | Connected |  | N
National Grid | TEWKSBURY | 175417 | 01876 | 16 | Solar | 05_01_602W2 | 07/10/2014 | 07/10/2014 | 7 | 0 | 7 | 07/22/2014 | 07/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2014 |  | 9/30/2014 | N | EXP | 68 |  |  | 0 | 0 | 0 | 8/12/2014 | 8/12/2014 | 10/14/2014 | Connected |  | N
National Grid | METHUEN | 529991 | 01844 | 3.8 | Solar | 05_05_115W42 | 10/20/2023 | 10/24/2023 | 2 | 0 | 2 | 10/25/2023 | 10/25/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 12/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2024 | Connected |  | N
National Grid | MEDFORD | 659874 | 02155 | 3.8 | Solar | 05_05_311W4 | 12/11/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/11/2024 | 4/26/2026 | Y | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | AUBURN | 208665 | 01501 | 15 | Solar | 05_12_26L1 | 02/06/2019 | 02/12/2019 | 3 | 0 | 3 | 02/13/2019 | 02/13/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 174340 | 01571 | 50 | Solar | 05_12_5C5 | 12/13/2011 | 12/13/2011 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2012 |  | 3/30/2012 | N | EXP | 11 |  |  | 0 | 0 | 0 | 6/5/2012 | 6/5/2012 | 7/18/2012 | Connected |  | N
National Grid | HUBBARDSTON | 646620 | 01452 | 5.76 | Solar | 05_14_3L4 | 10/22/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/22/2024 | 12/20/2025 | Y | EXP | 365 | 03/04/2025 | 03/24/2025 | 21 | 0 | 21 |  |  | 3/27/2025 | Connected |  | N
National Grid | FALL RIVER | 349329 | 02724 | 3.8 | Solar | 05_14_59L3 | 04/16/2021 | 04/26/2021 | 4 | 0 | 4 | 04/27/2021 | 04/27/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2021 | Connected |  | N
National Grid | MARLBOROUGH | 647971 | 01752 | 7.6 | Solar | 05_14_74L1 | 10/17/2024 | 01/22/2025 | 3 | 0 | 3 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 10/17/2024 | 3/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | TOPSFIELD | 502077 | 01983 | 15.744 | Solar | 05_12_67J1 | 03/06/2023 | 03/14/2023 | 6 | 5 | 1 | 03/15/2023 | 03/15/2023 | 30 | 5 | 25 | 05/12/2023 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 6/22/2023 |  | 8/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2023 | Connected |  | N
National Grid | MALDEN | 176341 | 02148 | 8.6 | Solar | 05_01_26W1 | 02/25/2015 | 02/25/2015 | 9 | 6 | 3 | 03/11/2015 | 03/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 | 02/25/2015 | 12/31/2016 | Y | EXP | 655 | 02/18/2016 | 03/14/2016 | 17 | 0 | 17 | 3/17/2015 | 3/17/2015 | 5/5/2016 | Connected |  | N
National Grid | LOWELL | 176959 | 01852 | 9 | Solar | 05_01_412L4 | 07/16/2016 | 07/16/2016 | 2 | 2 | 0 | 07/20/2016 | 07/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 07/16/2016 | 7/23/2017 | Y | EXP | 362 | 03/24/2017 | 05/04/2017 | 28 | 0 | 28 | 6/27/2017 | 6/27/2017 | 6/27/2017 | Connected |  | N
National Grid | TEWKSBURY | 176044 | 01876 | 630 | Solar | 05_01_602W2 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2015 | 09/15/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/23/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 594405 | 01844 | 5 | Solar | 05_05_115W42 | 03/19/2024 | 03/25/2024 | 4 | 0 | 4 | 03/26/2024 | 03/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/19/2024 | 4/24/2025 | Y | EXP | 365 | 05/24/2024 | 07/05/2024 | 43 | 0 | 43 |  |  | 8/1/2024 | Connected |  | N
National Grid | MEDFORD | 175299 | 02155 | 300 | Solar | 05_05_311W4 | 01/15/2015 | 01/15/2015 | 3 | 1 | 2 | 01/23/2015 | 01/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 |  | 5/31/2015 | N | EXP | 117 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 9/18/2015 | Connected |  | N
National Grid | AUBURN | 214988 | 01501 | 20.8 | Solar | 05_12_26L1 | 03/22/2019 | 03/28/2019 | 3 | 0 | 3 | 03/29/2019 | 03/29/2019 | 10 | 7 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2019 |  | 4/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2019 | Connected |  | N
National Grid | DUDLEY | 185756 | 01571 | 150 | Solar | 05_12_5J10 | 05/22/2018 | 05/22/2018 | 4 | 0 | 4 | 05/31/2018 | 05/31/2018 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2018 |  | 12/2/2019 | N | EXP | 536 |  |  | 0 | 0 | 0 |  |  | 1/17/2020 | Connected |  | N
National Grid | WESTMINSTER | 652013 | 01473 | 15.2 | Solar | 05_14_3L4 | 11/04/2024 | 11/25/2024 | 14 | 10 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | FALL RIVER | 396310 | 02724 | 0 | Other | 05_14_59L3 | 02/17/2022 | 04/04/2022 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2022 | 04/05/2022 | 1 | 0 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 648935 | 01752 | 5.76 | Solar | 05_14_74L1 | 11/04/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 11/04/2024 | 1/15/2026 | Y | EXP | 365 | 03/15/2025 | 03/25/2025 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Y
National Grid | TOPSFIELD | 555081 | 01983 | 10 | Solar | 05_12_67J1 | 09/15/2023 | 09/19/2023 | 3 | 2 | 1 | 09/20/2023 | 09/20/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2023 | 09/15/2023 | 10/26/2024 | Y | EXP | 365 | 02/16/2024 | 05/21/2024 | 96 | 0 | 96 |  |  | 8/3/2024 | Connected |  | N
National Grid | MALDEN | 177031 | 02148 | 3.8 | Solar | 05_01_26W1 | 03/20/2017 | 03/20/2017 | 6 | 5 | 1 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 |  | 3/25/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 10/17/2017 | 10/17/2017 | 10/17/2017 | Connected |  | N
National Grid | LOWELL | 176931 | 01852 | 22.8 | Solar | 05_01_412L4 | 01/28/2016 | 01/28/2016 | 0 | 0 | 0 | 01/28/2016 | 01/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 4/2/2017 | N | EXP | 422 |  |  | 0 | 0 | 0 | 11/7/2016 | 11/7/2016 | 11/17/2016 | Connected |  | N
National Grid | ANDOVER | 176043 | 01876 | 1000 | Solar | 05_01_602W2 | 08/14/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2015 | 09/15/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2016 | 08/14/2015 | 2/24/2020 | Y | STD | 1225 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 608980 | 01844 | 0 | Solar | 05_05_115W42 | 06/17/2024 | 07/23/2024 | 9 | 7 | 2 | 07/24/2024 | 07/24/2024 | 16 | 5 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | MEDFORD | 175990 | 02155 | 12 | Solar | 05_05_311W4 | 03/18/2015 | 03/18/2015 | 4 | 0 | 4 | 03/25/2015 | 03/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2015 |  | 12/31/2016 | N | EXP | 631 |  |  | 0 | 0 | 0 | 4/10/2015 | 4/10/2015 | 10/5/2016 | Connected |  | N
National Grid | AUBURN | 243526 | 01501 | 4000 | Solar | 05_12_26L1 | 08/15/2019 | 09/12/2019 | 19 | 11 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2019 | 10/07/2019 | 17 | 9 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 587973 | 01571 | 550 | Natural Gas | 05_12_5J9 | 02/28/2024 | 08/06/2024 | 110 | 101 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2024 | 08/28/2024 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 652158 | 01473 | 3.8 | Solar | 05_14_3L4 | 11/05/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 525204 | 02724 | 4.41 | Solar | 05_14_59L3 | 05/16/2023 | 05/17/2023 | 1 | 0 | 1 | 05/18/2023 | 05/18/2023 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2023 |  | 8/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | N
National Grid | MARLBOROUGH | 650870 | 01752 | 10 | Solar | 05_14_74L1 | 11/11/2024 | 12/18/2024 | 1 | 0 | 1 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/11/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2025 | Connected |  | N
National Grid | TOPSFIELD | 628731 | 01983 | 11.5 | Solar | 05_12_67J1 | 07/30/2024 | 09/20/2024 | 49 | 44 | 5 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | MALDEN | 177489 | 02148 | 288 | Solar | 05_01_26W1 | 09/23/2016 | 09/23/2016 | 1 | 1 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 |  | 10/1/2017 | N | EXP | 313 |  |  | 0 | 0 | 0 | 6/14/2017 | 6/14/2017 | 6/14/2017 | Connected |  | N
National Grid | LOWELL | 176996 | 01852 | 3.8 | Solar | 05_01_412L4 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 242 | 0 | 242 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 |  | 7/25/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 176306 | 01876 | 15.2 | Solar | 05_01_602W2 | 02/20/2015 | 02/20/2015 | 7 | 0 | 7 | 03/04/2015 | 03/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2015 |  | 7/31/2015 | N | EXP | 148 |  |  | 0 | 0 | 0 | 5/12/2017 | 5/12/2017 | 5/12/2017 | Connected |  | N
National Grid | METHUEN | 625117 | 01844 | 3.8 | Solar | 05_05_115W42 | 07/16/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | MALDEN | 177257 | 02148 | 396 | Solar | 05_05_311W4 | 08/17/2016 | 08/17/2016 | 2 | 2 | 0 | 08/22/2016 | 08/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2016 |  | 8/23/2017 | N | EXP | 336 |  |  | 0 | 0 | 0 | 4/21/2017 | 4/21/2017 | 4/28/2017 | Connected |  | N
National Grid | AUBURN | 243633 | 01501 | 9.84 | Solar | 05_12_26L1 | 07/19/2019 | 07/26/2019 | 5 | 5 | 0 | 07/29/2019 | 07/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 11/11/2019 | N | EXP | 96 |  |  | 0 | 0 | 0 |  |  | 10/16/2019 | Connected |  | N
National Grid | DUDLEY | 667538 | 01571 | 7.6 | Solar | 05_12_64J1 | 01/31/2025 | 02/13/2025 | 2 | 0 | 2 | 02/14/2025 | 02/14/2025 | 120 | 104 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HUBBARDSTON | 652366 | 01452 | 3.8 | Solar | 05_14_3L4 | 11/14/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/14/2024 | 1/23/2026 | Y | EXP | 365 | 03/11/2025 | 03/24/2025 | 14 | 0 | 14 |  |  | 5/3/2025 | Connected |  | N
National Grid | FALL RIVER | 585728 | 02724 | 0 | Solar | 05_14_59L3 | 01/26/2024 | 02/01/2024 | 5 | 3 | 2 | 02/02/2024 | 02/02/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 650926 | 01752 | 10 | Solar | 05_14_74L1 | 11/12/2024 | 12/02/2024 | 2 | 0 | 2 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | TOPSFIELD | 637387 | 01983 | 6.4 | Solar | 05_12_67J1 | 09/03/2024 | 09/06/2024 | 6 | 2 | 4 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 2/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2025 | Connected |  | N
National Grid | MEDFORD | 177645 | 02155 | 10 | Solar | 05_01_26W1 | 09/25/2017 | 11/13/2017 | 27 | 27 | 0 | 11/13/2017 | 11/13/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 |  | 10/1/2018 | N | EXP | 321 |  |  | 0 | 0 | 0 |  |  | 11/27/2018 | Connected |  | N
National Grid | LOWELL | 177938 | 01852 | 96 | Solar | 05_01_412L4 | 06/26/2017 | 06/26/2017 | 28 | 27 | 1 | 08/07/2017 | 08/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2017 |  | 7/2/2018 | N | EXP | 327 |  |  | 0 | 0 | 0 | 12/8/2017 | 12/8/2017 | 12/8/2017 | Connected |  | N
National Grid | TEWKSBURY | 176398 | 01876 | 10 | Solar | 05_01_602W2 | 03/10/2016 | 03/10/2016 | 1 | 1 | 0 | 03/14/2016 | 03/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2016 |  | 3/16/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 4/28/2016 | 4/28/2016 | 6/13/2016 | Connected |  | N
National Grid | METHUEN | 640702 | 01844 | 5.8 | Solar | 05_05_115W42 | 09/17/2024 | 10/15/2024 | 5 | 2 | 3 | 10/16/2024 | 10/16/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  | 1/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | Y
National Grid | MEDFORD | 178581 | 02155 | 10 | Solar | 05_05_311W4 | 01/31/2018 | 01/31/2018 | 20 | 0 | 20 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 11/25/2019 | N | EXP | 614 | 07/28/2018 | 08/29/2018 | 32 | 0 | 32 |  |  | 10/7/2019 | Connected |  | N
National Grid | AUBURN | 393102 | 01501 | 11.4 | Solar | 05_12_26L1 | 11/03/2021 | 11/04/2021 | 1 | 0 | 1 | 11/05/2021 | 11/05/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 3/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2022 | Connected |  | N
National Grid | DUDLEY | 561812 | 01571 | 6.3 | Solar | 05_12_64J1 | 12/13/2023 | 12/14/2023 | 2 | 1 | 1 | 12/15/2023 | 12/15/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2024 |  | 2/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2024 | Connected |  | N
National Grid | WESTMINSTER | 653277 | 01473 | 7.6 | Solar | 05_14_3L4 | 11/14/2024 | 01/16/2025 | 31 | 25 | 6 | 01/17/2025 | 01/17/2025 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 606299 | 02724 | 7.6 | Solar | 05_14_59L3 | 04/24/2024 | 05/03/2024 | 5 | 0 | 5 | 05/06/2024 | 05/06/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/24/2024 | 5/20/2025 | Y | EXP | 365 | 07/24/2024 | 02/26/2025 | 218 | 0 | 218 |  |  | 3/7/2025 | Connected |  | N
National Grid | MARLBOROUGH | 651514 | 01752 | 5.76 | Solar | 05_14_74L1 | 11/21/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TOPSFIELD | 688261 | 01983 | 5.76 | Solar | 05_12_67J1 | 05/01/2025 |  | 65 | 63 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 178467 | 02155 | 299.7 | Solar | 05_01_26W1 | 01/23/2018 | 02/22/2018 | 2 | 2 | 0 | 02/22/2018 | 02/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2018 |  | 2/28/2020 | N | EXP | 518 |  |  | 0 | 0 | 0 |  |  | 4/30/2020 | Connected |  | N
National Grid | LOWELL | 178095 | 01852 | 7.6 | Solar | 05_01_412L4 | 07/10/2017 | 07/19/2017 | 7 | 6 | 1 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/15/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 |  |  | 10/30/2018 | Connected |  | N
National Grid | TEWKSBURY | 176879 | 01876 | 266.4 | Solar | 05_01_602W2 | 05/04/2016 | 05/04/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2016 | 06/28/2016 | 35 | 14 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 | 05/04/2016 | 12/29/2017 | Y | STD | 373 | 05/01/2017 | 10/04/2017 | 109 | 0 | 109 | 1/11/2018 | 1/11/2018 | 12/11/2017 | Connected |  | N
National Grid | METHUEN | 644030 | 01844 | 5.28 | Solar | 05_05_115W42 | 10/01/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | MEDFORD | 186667 | 02155 | 7.6 | Solar | 05_05_311W4 | 06/07/2018 | 06/07/2018 | 4 | 0 | 4 | 06/15/2018 | 06/15/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 495464 | 01501 | 16.53 | Solar | 05_12_26L1 | 01/27/2023 | 02/03/2023 | 5 | 2 | 3 | 02/06/2023 | 02/06/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2023 |  | 3/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2023 | Connected |  | N
National Grid | DUDLEY | 562644 | 01571 | 2.52 | Solar | 05_12_64J1 | 12/13/2023 | 12/20/2023 | 5 | 3 | 2 | 12/21/2023 | 12/21/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2024 |  | 2/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2024 | Connected |  | N
National Grid | HUBBARDSTON | 653437 | 01452 | 5.76 | Solar | 05_14_3L4 | 11/18/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 55 | 33 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 612327 | 02724 | 7.6 | Solar | 05_14_59L3 | 05/20/2024 | 06/03/2024 | 3 | 0 | 3 | 06/04/2024 | 06/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 | 05/20/2024 | 7/25/2025 | Y | EXP | 365 | 08/29/2024 | 10/23/2024 | 56 | 0 | 56 |  |  | 12/4/2024 | Connected |  | N
National Grid | MARLBOROUGH | 655742 | 01752 | 3.8 | Solar | 05_14_74L1 | 11/20/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | TOPSFIELD | 730479 | 01983 | 3.8 | Solar | 05_12_67J1 | 10/30/2025 | 11/05/2025 | 4 | 0 | 4 | 11/06/2025 | 11/06/2025 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 |  | 1/15/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2026 | Connected |  | N
National Grid | MEDFORD | 194297 | 02155 | 250 | Solar | 05_01_26W1 | 08/24/2018 | 08/28/2018 | 1 | 0 | 1 | 08/29/2018 | 08/29/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 178192 | 01852 | 3630 | Solar | 05_01_412L4 | 01/02/2018 | 02/23/2018 | 35 | 9 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 04/02/2018 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2020 | 01/02/2018 | 6/28/2024 | Y | STD | 45 | 07/07/2023 | 09/21/2023 | 77 | 0 | 77 |  |  | 6/10/2024 | Connected |  | N
National Grid | TEWKSBURY | 176901 | 01876 | 6 | Solar | 05_01_602W2 | 01/27/2016 | 01/27/2016 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/1/2017 | N | EXP | 350 |  |  | 0 | 0 | 0 | 2/19/2016 | 2/19/2016 | 4/11/2016 | Connected |  | N
National Grid | METHUEN | 645420 | 01844 | 5.76 | Solar | 05_05_115W42 | 10/31/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | MEDFORD | 219586 | 02155 | 800 | Solar | 05_05_311W4 | 04/19/2019 | 08/09/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2019 | 10/29/2019 | 54 | 40 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 569963 | 01501 | 2500 | Solar | 05_12_26L1 | 06/07/2024 |  | 277 | 267 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 637288 | 01571 | 6.98 | Solar | 05_12_64J1 | 09/03/2024 | 12/19/2024 | 29 | 23 | 6 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 09/03/2024 | 2/10/2026 | Y | EXP | 365 | 05/07/2025 | 08/06/2025 | 92 | 0 | 92 |  |  | 8/15/2025 | Connected |  | N
National Grid | WESTMINSTER | 654034 | 01473 | 5.76 | Solar | 05_14_3L4 | 11/13/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | FALL RIVER | 642192 | 02724 | 0 | Battery Add-On | 05_14_59L3 | 09/27/2024 | 10/02/2024 | 3 | 0 | 3 | 10/03/2024 | 10/03/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | MARLBOROUGH | 657618 | 01752 | 10 | Solar | 05_14_74L1 | 11/29/2024 | 01/10/2025 | 2 | 0 | 2 | 01/13/2025 | 01/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 11/29/2024 | 3/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | TOPSFIELD | 721153 | 01983 | 100 | Solar | 05_01_HT56B | 02/22/2026 |  | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MEDFORD | 205077 | 02155 | 7.6 | Solar | 05_01_26W1 | 02/07/2019 |  | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 178264 | 01852 | 1250 | Solar | 05_01_412L4 | 04/18/2018 | 04/30/2018 | 8 | 8 | 0 |  |  | 39 | 14 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2021 | 04/18/2018 | 4/14/2025 | Y | STD | 485 | 08/20/2024 | 02/13/2025 | 178 | 178 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | TEWKSBURY | 177318 | 01876 | 2000 | Solar | 05_01_602W2 | 02/14/2017 | 02/14/2017 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/01/2017 | 03/27/2017 | 18 | 7 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/20/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 645390 | 01844 | 5.76 | Solar | 05_05_115W42 | 10/07/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/07/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | WORCESTER | 609102 | 01604 | 15.2 | Solar | 05_12_26L1 | 05/06/2024 | 05/08/2024 | 2 | 0 | 2 | 05/09/2024 | 05/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 | 05/06/2024 | 6/24/2025 | Y | EXP | 365 | 10/01/2024 | 01/02/2025 | 94 | 0 | 94 |  |  | 1/13/2025 | Connected |  | N
National Grid | AUBURN | 357707 | 01501 | 66.6 | Solar | 05_12_64J2 | 05/17/2021 | 05/11/2022 | 248 | 244 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 05/17/2021 | 7/11/2024 | Y | EXP | 90 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | DUDLEY | 657027 | 01571 | 7.6 | Solar | 05_14_3L4 | 11/26/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 | 11/26/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | HUBBARDSTON | 647522 | 01452 | 7.6 | Solar | 05_14_59L3 | 10/22/2024 | 11/19/2024 | 7 | 5 | 2 | 11/20/2024 | 11/20/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 663020 | 02724 | 5.76 | Solar | 05_14_74L1 | 12/30/2024 | 01/23/2025 | 4 | 0 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 | 12/30/2024 | 3/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | MARLBOROUGH | 578624 | 01752 | 200 | Solar | 05_01_HT56B | 02/06/2024 | 01/17/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 208525 | 01983 | 2340 | Solar | 05_01_26W1 | 02/13/2019 |  | 176 | 51 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 178355 | 02155 | 2990 | Solar | 05_01_412L4 | 02/28/2018 | 02/28/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2018 | 06/15/2018 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/6/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 178021 | 01852 | 900 | Solar | 05_01_602W2 | 08/29/2017 | 08/29/2017 | 8 | 8 | 0 |  |  | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/5/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 653947 | 01876 | 5.76 | Solar | 05_05_115W42 | 11/15/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | METHUEN | 299754 | 01844 | 10 | Solar | 05_05_311W4 | 09/02/2020 | 09/18/2020 | 11 | 11 | 0 | 09/21/2020 | 09/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2020 | 09/02/2020 | 10/15/2021 | Y | EXP | 365 | 12/29/2020 | 03/01/2021 | 62 | 0 | 62 |  |  | 3/3/2021 | Connected |  | N
National Grid | WORCESTER | 611833 | 01604 | 6.38 | Solar | 05_12_26L1 | 05/20/2024 | 05/29/2024 | 2 | 1 | 1 | 05/30/2024 | 05/30/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 | 05/20/2024 | 9/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | Y
National Grid | AUBURN | 661943 | 01501 | 5.76 | Solar | 05_12_64J3 | 12/20/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | DUDLEY | 658318 | 01571 | 3.8 | Solar | 05_14_3L4 | 12/04/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | HUBBARDSTON | 648085 | 01452 | 3 | Solar | 05_14_59L3 | 10/18/2024 | 10/29/2024 | 5 | 1 | 4 | 10/30/2024 | 10/30/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | FALL RIVER | 667339 | 02724 | 5.76 | Solar | 05_14_74L1 | 01/23/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 | 01/23/2025 | 3/28/2026 | Y | EXP | 365 | 06/18/2025 | 12/22/2025 | 188 | 0 | 188 |  |  | 12/4/2025 | Connected |  | N
National Grid | MARLBOROUGH | 680413 | 01752 | 7.6 | Solar | 05_01_216W4 | 04/07/2025 | 04/25/2025 | 13 | 9 | 4 | 04/28/2025 | 04/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 | 04/07/2025 | 6/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TOPSFIELD | 223683 | 01983 | 10 | Solar | 05_01_26W1 | 04/30/2019 | 05/07/2019 | 4 | 0 | 4 | 05/08/2019 | 05/08/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2019 | 04/30/2019 | 8/16/2022 | Y | EXP | 1100 | 09/23/2020 | 11/18/2020 | 56 | 0 | 56 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 178442 | 02155 | 9 | Solar | 05_01_412L4 | 04/02/2018 | 04/10/2018 | 5 | 0 | 5 | 04/10/2018 | 04/10/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 | 04/02/2018 | 5/6/2019 | Y | EXP | 333 | 03/30/2019 | 03/29/2019 | 0 | 0 | 0 |  |  | 5/2/2019 | Connected |  | N
National Grid | LOWELL | 178134 | 01852 | 15.2 | Solar | 05_01_602W2 | 07/12/2017 | 07/12/2017 | 4 | 4 | 0 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/18/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/25/2018 | 1/25/2018 | 1/25/2018 | Connected |  | N
National Grid | TEWKSBURY | 660383 | 01876 | 3.8 | Solar | 05_05_115W42 | 12/17/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 12/17/2024 | 2/25/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | METHUEN | 436246 | 01844 | 9.984 | Solar | 05_05_311W4 | 06/23/2022 | 06/24/2022 | 1 | 0 | 1 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/23/2022 |  | Y | EXP | 365 | 09/15/2022 | 10/18/2022 | 34 | 0 | 34 |  |  | 5/19/2023 | Connected |  | N
National Grid | LANCASTER | 649651 | 01523 | 9.28 | Solar | 05_12_26L1 | 10/25/2024 | 11/12/2024 | 8 | 3 | 5 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/25/2024 | 1/21/2026 | Y | EXP | 365 | 02/18/2025 | 03/03/2025 | 14 | 0 | 14 |  |  | 3/11/2025 | Connected |  | N
National Grid | AUBURN | 664919 | 01501 | 10 | Solar | 05_12_64J3 | 01/10/2025 | 02/05/2025 | 5 | 1 | 4 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 661851 | 01571 | 3.8 | Solar | 05_14_3L4 | 12/19/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 651393 | 01473 | 3.8 | Solar | 05_14_59L3 | 11/22/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 668089 | 02724 | 3.8 | Solar | 05_14_74L1 | 01/27/2025 | 02/18/2025 | 1 | 0 | 1 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | MARLBOROUGH | 721352 | 01752 | 9.074 | Solar | 05_01_216W4 | 09/27/2025 | 10/03/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 | 09/27/2025 | 11/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | TOPSFIELD | 247021 | 01983 | 10 | Solar | 05_01_26W1 | 08/19/2019 | 08/26/2019 | 4 | 3 | 1 | 08/27/2019 | 08/27/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2019 |  | 11/25/2019 | N | EXP | 76 |  |  | 0 | 0 | 0 |  |  | 10/23/2019 | Connected |  | N
National Grid | SOMERVILLE | 195056 | 02145 | 7.6 | Solar | 05_01_412L4 | 09/04/2018 | 10/26/2018 | 21 | 21 | 0 | 10/29/2018 | 10/29/2018 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 | 09/04/2018 | 11/8/2019 | Y | EXP | 359 | 07/11/2019 | 09/16/2019 | 67 | 0 | 67 |  |  | 10/9/2019 | Connected |  | N
National Grid | LOWELL | 178224 | 01852 | 2375 | Solar | 05_01_602W2 | 04/16/2018 | 04/16/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/09/2018 | 3 | 0 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/21/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 661562 | 01876 | 3.8 | Solar | 05_05_115W42 | 12/18/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/18/2024 | 3/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | METHUEN | 644500 | 01844 | 10 | Solar | 05_05_311W4 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/02/2024 | 2/10/2026 | Y | EXP | 425 | 01/07/2025 | 02/13/2025 | 38 | 0 | 38 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 657173 | 01523 | 10 | Solar | 05_12_26L1 | 11/26/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/26/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | AUBURN | 746651 | 01501 | 237.5 | Solar | 05_12_64J5 | 03/17/2026 |  | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | DUDLEY | 663246 | 01571 | 3.8 | Solar | 05_14_3L4 | 01/10/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 5/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | HUBBARDSTON | 653564 | 01452 | 5.76 | Solar | 05_14_59L3 | 11/15/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/15/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | FALL RIVER | 668858 | 02724 | 10 | Solar | 05_14_74L1 | 01/30/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | MARLBOROUGH | 725215 | 01752 | 60 | Solar | 05_01_216W4 | 10/09/2025 | 10/29/2025 | 13 | 6 | 7 |  |  | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | TOPSFIELD | 248514 | 01983 | 10 | Solar | 05_01_26W1 | 09/04/2019 | 09/05/2019 | 0 | 0 | 0 | 09/06/2019 | 09/06/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 | 09/04/2019 | 5/11/2020 | Y | EXP | 237 | 12/21/2019 | 01/24/2020 | 34 | 0 | 34 |  |  | 2/10/2020 | Connected |  | N
National Grid | MEDFORD | 268311 | 02155 | 10 | Solar | 05_01_412L4 | 01/17/2020 | 02/10/2020 | 1 | 1 | 0 | 02/11/2020 | 02/11/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2020 |  | 2/10/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 178326 | 01852 | 5000 | Solar | 05_01_602W2 | 03/26/2018 | 03/26/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 05/04/2018 | 32 | 10 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 663099 | 01876 | 10 | Solar | 05_05_115W42 | 01/02/2025 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 01/02/2025 | 3/24/2026 | Y | EXP | 365 | 04/29/2025 | 05/15/2025 | 17 | 0 | 17 |  |  | 6/6/2025 | Connected |  | N
National Grid | METHUEN | 668317 | 01844 | 3.8 | Solar | 05_05_311W4 | 01/30/2025 | 03/19/2025 | 16 | 11 | 5 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | LANCASTER | 659886 | 01523 | 9.57 | Solar | 05_12_26L1 | 12/11/2024 | 12/24/2024 | 9 | 5 | 4 | 12/26/2024 | 12/26/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | AUBURN | 223134 | 01501 | 106 | Solar | 05_12_64J5 | 04/27/2019 | 05/21/2019 | 16 | 11 | 5 | 05/22/2019 | 05/22/2019 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2019 |  | 6/21/2021 | N | EXP | 720 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | Connected |  | N
National Grid | DUDLEY | 674880 | 01571 | 9.86 | Solar | 05_14_3L4 | 02/28/2025 | 03/12/2025 | 2 | 1 | 1 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 02/28/2025 | 5/29/2026 | Y | EXP | 365 | 09/17/2025 | 09/16/2025 | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | HUBBARDSTON | 659218 | 01452 | 9.6 | Solar | 05_14_59L3 | 12/09/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/09/2024 | 4/14/2026 | Y | EXP | 365 | 05/23/2025 | 05/22/2025 | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | FALL RIVER | 673277 | 02724 | 23 | Solar | 05_14_74L1 | 02/20/2025 | 06/05/2025 | 72 | 38 | 34 | 06/06/2025 | 06/06/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | MARLBOROUGH | 174206 | 01752 | 2450 | Solar | 05_01_216W4 | 02/29/2012 | 02/29/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2012 | 05/22/2012 | 34 | 0 | 34 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2012 |  | 1/1/2013 | N | STD | 33 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 338558 | 01983 | 7.6 | Solar | 05_01_26W1 | 03/12/2021 | 03/15/2021 | 0 | 0 | 0 | 03/16/2021 | 03/16/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 | 03/12/2021 | 1/20/2023 | Y | EXP | 365 | 12/15/2021 | 01/19/2022 | 36 | 0 | 36 |  |  | 1/25/2022 | Connected |  | N
National Grid | MEDFORD | 299874 | 02155 | 9.36 | Solar | 05_01_412L4 | 07/07/2020 | 07/09/2020 | 1 | 0 | 1 | 07/10/2020 | 07/10/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | LOWELL | 178567 | 01852 | 4950 | Solar | 05_01_602W2 | 12/07/2017 | 01/08/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/07/2018 | 21 | 7 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/13/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 728667 | 01876 | 5.76 | Solar | 05_05_115W42 | 10/27/2025 | 10/28/2025 | 3 | 0 | 3 | 11/10/2025 | 11/10/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 2/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2026 | Connected |  | N
National Grid | METHUEN | 668726 | 01844 | 5.12 | Solar | 05_05_311W4 | 01/29/2025 | 02/13/2025 | 5 | 2 | 3 | 02/14/2025 | 02/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | BOLTON | 676798 | 01740 | 22.8 | Solar | 05_12_26L1 | 03/11/2025 | 03/14/2025 | 3 | 0 | 3 | 03/17/2025 | 03/17/2025 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2025 | Connected |  | N
National Grid | AUBURN | 394755 | 01501 | 0 | Solar | 05_12_64J5 | 12/16/2021 | 01/05/2022 | 13 | 10 | 3 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2022 |  | 3/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2022 | Connected |  | N
National Grid | DUDLEY | 647611 | 01571 | 0 | Hydro | 05_14_3L5 | 02/04/2025 | 03/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GARDNER | 661819 | 01440 | 7.6 | Solar | 05_14_59L3 | 12/19/2024 | 01/14/2025 | 3 | 0 | 3 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | FALL RIVER | 679348 | 02724 | 7.6 | Solar | 05_14_74L1 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 176516 | 01752 | 10 | Solar | 05_01_216W4 | 10/02/2015 | 10/02/2015 | 0 | 0 | 0 | 10/05/2015 | 10/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2015 |  | 10/10/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 12/29/2015 | 12/29/2015 | 1/12/2016 | Connected |  | N
National Grid | TOPSFIELD | 438906 | 01983 | 9.86 | Solar | 05_01_26W1 | 07/22/2022 | 07/26/2022 | 2 | 2 | 0 | 07/27/2022 | 07/27/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 | 07/22/2022 | 9/1/2023 | Y | EXP | 365 | 10/20/2022 | 03/08/2023 | 140 | 0 | 140 |  |  | 3/9/2023 | Connected |  | N
National Grid | MEDFORD | 320511 | 02155 | 9.8 | Solar | 05_01_412L4 | 11/04/2020 | 11/09/2020 | 2 | 0 | 2 | 11/10/2020 | 11/10/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2020 |  | 1/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 206349 | 01852 | 2340 | Solar | 05_01_602W2 | 02/06/2019 |  | 140 | 26 | 114 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 700098 | 01876 | 9.5 | Solar | 05_05_115W44 | 06/20/2025 | 09/22/2025 | 4 | 0 | 4 | 10/09/2025 | 10/09/2025 | 31 | 13 | 18 | 12/04/2025 | 12/03/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 3/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 511796 | 01832 | 249 | Solar | 05_05_311W5 | 07/06/2023 | 09/01/2023 | 41 | 32 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 | 07/06/2023 | 9/29/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LANCASTER | 693020 | 01523 | 31.04 | Solar | 05_12_26L1 | 05/29/2025 | 06/03/2025 | 3 | 0 | 3 | 06/04/2025 | 06/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2025 | 05/29/2025 | 8/4/2026 | Y | EXP | 365 | 09/19/2025 | 09/18/2025 | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | AUBURN | 177360 | 01501 | 43.2 | Solar | 05_12_67J3 | 06/21/2016 | 06/21/2016 | 0 | 0 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/28/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 5/23/2017 | 5/23/2017 | 5/23/2017 | Connected |  | N
National Grid | DUDLEY | 647609 | 01571 | 0 | Hydro | 05_14_3L5 | 02/04/2025 | 03/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTMINSTER | 664658 | 01473 | 6.84 | Solar | 05_14_59L3 | 01/09/2025 | 01/31/2025 | 7 | 2 | 5 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/09/2025 | 4/10/2026 | Y | EXP | 365 | 06/07/2025 | 06/06/2025 | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | FALL RIVER | 682711 | 02721 | 5.76 | Solar | 05_14_74L1 | 04/03/2025 | 04/09/2025 | 4 | 0 | 4 | 04/10/2025 | 04/10/2025 | 67 | 49 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | MARLBOROUGH | 176510 | 01752 | 10 | Solar | 05_01_216W4 | 03/28/2016 | 03/28/2016 | 3 | 3 | 0 | 04/01/2016 | 04/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 |  | 4/3/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/11/2016 | 8/11/2016 | 8/11/2016 | Connected |  | N
National Grid | TOPSFIELD | 478360 | 01983 | 13.34 | Solar | 05_01_26W1 | 12/07/2022 | 12/14/2022 | 5 | 2 | 3 | 12/15/2022 | 12/15/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 1/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2023 | Connected |  | N
National Grid | MELROSE | 375104 | 02176 | 9.8 | Solar | 05_01_412L4 | 09/28/2021 | 12/16/2021 | 4 | 0 | 4 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 12/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2022 | Connected |  | N
National Grid | LOWELL | 282891 | 01852 | 4950 | Other | 05_01_602W2 | 03/19/2020 | 03/27/2020 | 5 | 1 | 4 |  |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 03/30/2020 | 04/29/2020 | 21 | 8 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174492 | 01876 | 120 | Solar | 05_05_115W44 | 06/03/2011 | 06/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2011 |  | 3/2/2012 | N | EXP | 234 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 3/2/2012 | Connected |  | N
National Grid | METHUEN | 739106 | 01844 | 10 | Solar | 05_05_311W5 | 12/09/2025 | 12/11/2025 | 3 | 0 | 3 | 01/13/2026 | 01/13/2026 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2026 |  | 3/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CLINTON | 717527 | 01510 | 18.85 | Solar | 05_12_26L1 | 09/08/2025 | 09/18/2025 | 6 | 2 | 4 | 09/19/2025 | 09/19/2025 | 86 | 70 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 327303 | 01505 | 43.2 | Solar | 05_12_67J3 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  | 3/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 647617 | 01571 | 0 | Hydro | 05_14_3L5 | 02/04/2025 | 03/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HUBBARDSTON | 668537 | 01565 | 5.76 | Solar | 05_14_59L3 | 01/29/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 689896 | 02721 | 11.5 | Solar | 05_14_74L1 | 05/06/2025 | 05/08/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 186590 | 01752 | 15.2 | Solar | 05_01_216W4 | 05/29/2018 | 05/29/2018 | 8 | 0 | 8 | 06/12/2018 | 06/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2018 |  |  | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  | 11/8/2019 | Connected |  | N
National Grid | TOPSFIELD | 480883 | 01983 | 0 | Solar | 05_01_26W1 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 391345 | 02176 | 7.6 | Solar | 05_01_412L4 | 11/11/2021 | 12/28/2021 | 3 | 0 | 3 | 11/17/2021 | 11/17/2021 | 42 | 22 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2022 | 11/11/2021 | 8/26/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2022 | Connected |  | N
National Grid | LOWELL | 287828 | 01852 | 0 | Other | 05_01_602W2 | 05/06/2020 | 05/12/2020 | 4 | 1 | 3 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 | 08/24/2020 | 10/20/2020 | 39 | 25 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174491 | 01876 | 82 | Solar | 05_05_115W44 | 06/03/2011 | 06/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2011 |  | 2/28/2012 | N | EXP | 231 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 2/28/2012 | Connected |  | N
National Grid | METHUEN | 158029 | 01844 | 7.6 | Solar | 05_05_311W5 | 01/26/2016 | 01/26/2016 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/1/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 714746 | 01561 | 0 | Solar | 05_12_28L2 | 08/28/2025 | 09/10/2025 | 8 | 4 | 4 | 09/11/2025 | 09/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AUBURN | 349034 | 01501 | 9.8 | Solar | 05_12_67J4 | 04/15/2021 | 04/19/2021 | 1 | 0 | 1 | 04/20/2021 | 04/20/2021 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 11/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2021 | Connected |  | N
National Grid | DUDLEY | 175719 | 01571 | 120.9 | Solar | 05_14_3L5 | 12/29/2014 | 12/29/2014 | 8 | 6 | 2 | 01/12/2015 | 01/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 | 12/29/2014 | 5/31/2015 | Y | EXP | 117 |  |  | 0 | 0 | 0 | 2/4/2015 | 2/4/2015 | 11/25/2015 | Connected |  | N
National Grid | HUBBARDSTON | 671372 | 01452 | 10 | Solar | 05_14_59L3 | 02/11/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2025 | Connected |  | N
National Grid | FALL RIVER | 700558 | 02721 | 15.2 | Solar | 05_14_74L1 | 06/23/2025 | 07/25/2025 | 22 | 17 | 5 | 07/28/2025 | 07/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 9/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2025 | Connected |  | N
National Grid | MARLBOROUGH | 430312 | 01752 | 0 | Other | 05_01_216W4 | 01/04/2023 | 01/19/2023 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2023 | 02/22/2023 | 22 | 0 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 514516 | 01930 | 14.79 | Solar | 05_01_26W1 | 04/07/2023 | 04/20/2023 | 8 | 7 | 1 | 04/21/2023 | 04/21/2023 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2023 |  | 9/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | MALDEN | 440471 | 02148 | 15.2 | Solar | 05_01_412L4 | 06/27/2022 | 06/30/2022 | 3 | 0 | 3 | 07/01/2022 | 07/01/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 290747 | 01852 | 0 | Other | 05_01_602W2 | 08/31/2020 | 09/16/2020 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/17/2020 | 10/08/2020 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174711 | 01876 | 485 | Solar | 05_05_115W44 | 06/21/2013 | 06/21/2013 | 6 | 0 | 6 | 07/02/2013 | 07/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2013 |  | 11/1/2013 | N | EXP | 113 |  |  | 0 | 0 | 0 | 12/31/2013 | 12/31/2013 | 12/31/2013 | Connected |  | N
National Grid | HAVERHILL | 175319 | 01832 | 440.8 | Solar | 05_05_311W5 | 08/29/2014 | 08/29/2014 | 6 | 2 | 4 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 12/23/2014 | 12/23/2014 | 12/31/2014 | Connected |  | N
National Grid | LANCASTER | 725607 | 01523 | 0 | Solar | 05_12_28L2 | 10/13/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 11/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AUBURN | 468598 | 01501 | 6 | Solar | 05_12_67J4 | 10/21/2022 | 10/28/2022 | 5 | 2 | 3 | 10/31/2022 | 10/31/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 177150 | 01571 | 7.56 | Solar | 05_14_3L5 | 08/10/2016 | 08/10/2016 | 3 | 3 | 0 | 08/16/2016 | 08/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 | 08/10/2016 | 8/16/2017 | Y | EXP | 362 | 12/14/2016 | 01/06/2017 | 15 | 0 | 15 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N
National Grid | WESTMINSTER | 684665 | 01473 | 23 | Solar | 05_14_59L3 | 04/11/2025 | 05/01/2025 | 13 | 10 | 3 | 05/02/2025 | 05/02/2025 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N
National Grid | FALL RIVER | 713543 | 02723 | 7.6 | Solar | 05_14_74L1 | 08/20/2025 | 09/10/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 60 | 47 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 438016 | 01752 | 10 | Solar | 05_01_216W4 | 07/18/2022 | 07/20/2022 | 2 | 0 | 2 | 07/21/2022 | 07/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2022 | 07/18/2022 | 8/25/2023 | Y | EXP | 365 | 10/11/2022 | 12/21/2022 | 72 | 0 | 72 |  |  | 1/10/2023 | Connected |  | N
National Grid | GLOUCESTER | 518028 | 01930 | 6 | Solar | 05_01_26W1 | 09/22/2023 | 09/25/2023 | 2 | 1 | 1 | 09/26/2023 | 09/26/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 11/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2024 | Connected |  | N
National Grid | MALDEN | 443970 | 02148 | 0 | Other | 05_01_412L4 | 01/30/2023 | 02/15/2023 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 291986 | 01852 | 5.76 | Solar | 05_01_602W2 | 05/14/2020 | 05/15/2020 | 0 | 0 | 0 | 05/18/2020 | 05/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2020 |  | 5/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | TEWKSBURY | 175053 | 01876 | 80.25 | Solar | 05_05_115W44 | 08/13/2012 | 08/13/2012 | 8 | 3 | 5 | 08/24/2012 | 08/24/2012 | 276 | 0 | 276 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176533 | 01844 | 7.6 | Solar | 05_05_311W5 | 02/09/2016 | 02/09/2016 | 3 | 3 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 |  | 2/15/2017 | N | EXP | 344 |  |  | 0 | 0 | 0 | 7/8/2016 | 7/8/2016 | 7/12/2016 | Connected |  | N
National Grid | LANCASTER | 750287 | 01523 | 3.8 | Solar | 05_12_28L2 | 02/10/2026 | 02/11/2026 | 2 | 0 | 2 | 02/23/2026 | 02/23/2026 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AUBURN | 649994 | 01501 | 3.8 | Solar | 05_12_67J4 | 11/07/2024 | 11/20/2024 | 3 | 0 | 3 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/07/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | WEBSTER | 370918 | 01570 | 100 | Solar | 05_14_3L5 | 08/16/2021 | 09/10/2021 | 18 | 8 | 10 | 09/13/2021 | 09/13/2021 | 66 | 13 | 53 | 12/30/2021 | 01/27/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 01/27/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 2/3/2022 |  | 6/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2022 | Connected |  | N
National Grid | GARDNER | 710883 | 01440 | 9.92 | Solar | 05_14_59L3 | 08/09/2025 | 08/14/2025 | 4 | 0 | 4 | 08/15/2025 | 08/15/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | FALL RIVER | 720467 | 02721 | 15.2 | Solar | 05_14_74L1 | 09/19/2025 | 09/24/2025 | 3 | 0 | 3 | 09/25/2025 | 09/25/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | MARLBOROUGH | 481067 | 01752 | 6.38 | Solar | 05_01_216W4 | 12/15/2022 | 12/26/2022 | 7 | 1 | 6 | 12/27/2022 | 12/27/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 12/15/2022 | 5/16/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | GLOUCESTER | 523508 | 01930 | 3 | Solar | 05_01_26W1 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 05/05/2023 | 6/21/2024 | Y | EXP | 365 | 08/19/2023 | 09/29/2023 | 42 | 0 | 42 |  |  | 10/10/2023 | Connected |  | N
National Grid | MALDEN | 445324 | 02148 | 7.6 | Solar | 05_01_412L4 | 09/27/2022 | 10/12/2022 | 10 | 7 | 3 | 10/13/2022 | 10/13/2022 | 18 | 0 | 18 | 11/29/2022 | 04/24/2023 | 100 | 0 | 100 |  |  | 0 | 0 | 0 | 04/24/2023 | 100 | 0 | 100 |  |  | 0 | 0 | 0 | 5/15/2023 |  | 10/25/2024 | N | EXP | 365 | 04/10/2024 | 06/13/2024 | 65 | 0 | 65 |  |  | 7/8/2024 | Connected |  | N
National Grid | LOWELL | 294861 | 01852 | 0 | Other | 05_01_602W2 | 09/09/2020 | 09/22/2020 | 8 | 1 | 7 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 175291 | 01876 | 36 | Solar | 05_05_115W44 | 11/06/2014 | 11/06/2014 | 5 | 2 | 3 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 2/27/2015 | N | EXP | 99 |  |  | 0 | 0 | 0 | 2/27/2015 | 2/27/2015 | 4/16/2015 | Connected |  | N
National Grid | HAVERHILL | 177888 | 01832 | 300 | Natural Gas | 05_05_311W5 | 04/11/2017 | 04/11/2017 | 55 | 52 | 3 | 06/30/2017 | 06/30/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2017 |  | 4/17/2018 | N | EXP | 264 |  |  | 0 | 0 | 0 |  |  | 9/27/2018 | Connected |  | N
National Grid | LANCASTER | 176498 | 01523 | 22.8 | Solar | 05_12_28L2 | 02/09/2016 | 02/09/2016 | 1 | 1 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2016 |  | 2/15/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 2/19/2016 | 2/19/2016 | 10/24/2016 | Connected |  | N
National Grid | AUBURN | 685446 | 01501 | 3.84 | Solar | 05_12_67J4 | 04/16/2025 | 05/23/2025 | 3 | 1 | 2 | 05/27/2025 | 05/27/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 | 04/16/2025 | 6/16/2026 | Y | EXP | 365 | 10/01/2025 | 11/21/2025 | 52 | 0 | 52 |  |  | 11/25/2025 | Connected |  | N
National Grid | DUDLEY | 642148 | 01571 | 3.84 | Solar | 05_14_3L5 | 09/23/2024 | 09/27/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2024 | 09/23/2024 | 2/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | HUBBARDSTON | 178363 | 01452 | 4920 | Solar | 05_14_59L4 | 03/30/2018 | 03/30/2018 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 04/18/2019 | 260 | 9 | 251 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/7/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 727180 | 02721 | 5.76 | Solar | 05_14_74L1 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 10/23/2025 | 10/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 506925 | 01752 | 8.7 | Solar | 05_01_216W4 | 05/25/2023 | 06/05/2023 | 6 | 4 | 2 | 06/06/2023 | 06/06/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 | 05/25/2023 | 8/12/2024 | Y | EXP | 365 | 05/07/2024 | 05/14/2024 | 8 | 0 | 8 |  |  | 5/15/2024 | Connected |  | N
National Grid | MANCHESTER | 568871 | 01944 | 10 | Solar | 05_01_26W1 | 11/14/2023 | 11/16/2023 | 2 | 0 | 2 | 11/17/2023 | 11/17/2023 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 484394 | 02148 | 7.6 | Solar | 05_01_412L4 | 12/09/2022 | 12/14/2022 | 3 | 1 | 2 | 12/15/2022 | 12/15/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 319090 | 01852 | 15.2 | Solar | 05_01_602W2 | 10/14/2020 | 10/15/2020 | 0 | 0 | 0 | 10/16/2020 | 10/16/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 | 10/14/2020 | 10/15/2021 | Y | EXP | 365 | 03/02/2021 | 03/19/2021 | 17 | 0 | 17 |  |  | 7/15/2021 | Connected |  | N
National Grid | ANDOVER | 176473 | 01810 | 72 | Solar | 05_05_115W44 | 03/22/2016 | 03/22/2016 | 3 | 3 | 0 | 03/28/2016 | 03/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2016 |  | 9/30/2016 | N | EXP | 143 |  |  | 0 | 0 | 0 | 9/21/2016 | 9/21/2016 | 10/4/2016 | Connected |  | N
National Grid | METHUEN | 178141 | 01844 | 7.6 | Solar | 05_05_311W5 | 03/22/2018 | 03/22/2018 | 18 | 9 | 9 | 04/05/2018 | 04/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2019 |  | 3/28/2019 | N | EXP | 15 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 176791 | 01523 | 7.6 | Solar | 05_12_28L2 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2016 |  | 1/20/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 8/2/2016 | Connected |  | N
National Grid | AUBURN | 241200 | 01501 | 7.6 | Solar | 05_12_6J2 | 07/03/2019 | 07/10/2019 | 3 | 0 | 3 | 07/11/2019 | 07/11/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 | 07/03/2019 | 8/3/2020 | Y | EXP | 365 | 05/20/2020 | 06/17/2020 | 28 | 0 | 28 |  |  | 7/21/2020 | Connected |  | N
National Grid | DUDLEY | 656613 | 01571 | 7.6 | Solar | 05_14_3L5 | 11/25/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | HUBBARDSTON | 175357 | 01452 | 30 | Solar | 05_14_59L5 | 09/08/2014 | 09/08/2014 | 17 | 14 | 3 | 10/02/2014 | 10/02/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 1/30/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 10/6/2014 | 10/6/2014 | 8/20/2015 | Connected |  | N
National Grid | FALL RIVER | 665501 | 02721 | 999 | Solar | 05_14_74L2 | 01/29/2025 | 02/24/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/25/2025 | 03/25/2025 | 22 | 2 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MARLBOROUGH | 640010 | 01752 | 3.77 | Solar | 05_01_216W4 | 09/13/2024 | 09/25/2024 | 5 | 2 | 3 | 09/26/2024 | 09/26/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 | 09/13/2024 | 12/2/2025 | Y | EXP | 365 | 04/15/2025 | 11/09/2025 | 209 | 0 | 209 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 569888 | 01930 | 10 | Solar | 05_01_26W1 | 11/20/2023 | 11/21/2023 | 1 | 0 | 1 | 11/22/2023 | 11/22/2023 | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/20/2023 | 1/25/2025 | Y | EXP | 365 | 03/16/2024 | 06/18/2024 | 95 | 0 | 95 |  |  | 7/1/2024 | Connected |  | N
National Grid | LYNN | 517480 | 01905 | 14.79 | Solar | 05_01_412L4 | 04/06/2023 | 04/10/2023 | 2 | 0 | 2 | 04/11/2023 | 04/11/2023 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 326400 | 01852 | 84 | Solar | 05_01_602W2 | 11/17/2020 | 02/18/2021 | 62 | 54 | 8 |  |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 | 02/19/2021 | 02/23/2021 | 2 | 0 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 387395 | 01876 | 0 | Other | 05_05_115W44 | 10/25/2021 | 01/04/2022 | 49 | 40 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 178593 | 01844 | 240 | Solar | 05_05_311W5 | 03/14/2018 | 03/14/2018 | 24 | 24 | 0 |  |  | 0 | 0 | 0 | 04/10/2018 | 04/24/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 | 04/24/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 3/20/2019 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 176789 | 01510 | 7.6 | Solar | 05_12_28L2 | 01/14/2016 | 01/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/20/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 342995 | 01501 | 7.6 | Solar | 05_12_6J2 | 03/02/2021 |  | 61 | 47 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 658847 | 01571 | 3.8 | Solar | 05_14_3L5 | 12/05/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 175492 | 01452 | 1800 | Solar | 05_14_59L5 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/03/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2015 | 07/25/2014 | 3/1/2016 | Y | STD | 354 | 10/28/2015 | 07/13/2017 | 424 | 0 | 424 | 5/24/2017 | 5/24/2017 | 6/26/2017 | Connected |  | N
National Grid | FALL RIVER | 688247 | 02723 | 100 | Solar | 05_14_74L2 | 10/17/2025 |  | 112 | 25 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MARLBOROUGH | 650594 | 01752 | 10 | Solar | 05_01_216W4 | 11/11/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/11/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | GLOUCESTER | 581921 | 01930 | 6.38 | Solar | 05_01_26W1 | 01/23/2024 | 01/29/2024 | 4 | 0 | 4 | 01/30/2024 | 01/30/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 01/23/2024 | 3/6/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2024 | Connected |  | N
National Grid | LYNN | 516711 | 01905 | 9.28 | Solar | 05_01_412L4 | 08/29/2023 | 08/30/2023 | 1 | 0 | 1 | 08/31/2023 | 08/31/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 | 08/29/2023 | 12/7/2024 | Y | EXP | 365 | 03/01/2024 | 04/23/2024 | 5 | 0 | 5 |  |  | 5/2/2024 | Connected |  | N
National Grid | LOWELL | 342428 | 01852 | 9.6 | Solar | 05_01_602W2 | 02/16/2021 | 02/17/2021 | 0 | 0 | 0 | 02/18/2021 | 02/18/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2021 | Connected |  | N
National Grid | ANDOVER | 501029 | 01810 | 100 | Solar | 05_05_115W44 | 02/24/2023 |  | 257 | 163 | 94 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 178613 | 01844 | 240 | Solar | 05_05_311W5 | 12/14/2017 | 12/14/2017 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 178625 | 01523 | 11.4 | Solar | 05_12_28L2 | 03/15/2018 | 03/15/2018 | 14 | 0 | 14 | 04/05/2018 | 04/05/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2018 |  | 3/21/2019 | N | EXP | 325 |  |  | 0 | 0 | 0 |  |  | 9/6/2019 | Connected |  | N
National Grid | AUBURN | 613313 | 01501 | 5 | Solar | 05_12_6J2 | 05/28/2024 | 06/18/2024 | 3 | 1 | 2 | 06/20/2024 | 06/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2024 |  | 7/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | DUDLEY | 660925 | 01571 | 7.6 | Solar | 05_14_3L5 | 12/16/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/16/2024 | 3/4/2026 | Y | EXP | 365 | 06/12/2025 | 12/02/2025 | 174 | 0 | 174 |  |  | 12/15/2025 | Connected |  | N
National Grid | WESTMINSTER | 175822 | 01473 | 120 | Solar | 05_14_59L5 | 08/03/2015 | 08/03/2015 | 10 | 10 | 0 | 08/17/2015 | 08/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2015 |  | 2/15/2016 | N | EXP | 116 |  |  | 0 | 0 | 0 | 2/11/2016 | 2/11/2016 | 2/17/2016 | Connected |  | N
National Grid | FALL RIVER | 722959 | 02721 | 3.8 | Solar | 05_14_74L2 | 10/01/2025 | 10/06/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 10/01/2025 | 12/17/2026 | Y | EXP | 365 | 02/11/2026 |  | 50 | 0 | 50 |  |  |  | Construction |  | N
National Grid | MARLBOROUGH | 670659 | 01752 | 13.3 | Solar | 05_01_216W4 | 02/08/2025 | 02/18/2025 | 6 | 1 | 5 | 02/19/2025 | 02/19/2025 | 56 | 35 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 02/08/2025 | 5/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | GLOUCESTER | 599053 | 01930 | 15.2 | Solar | 05_01_26W1 | 04/18/2024 | 06/21/2024 | 45 | 43 | 2 | 06/24/2024 | 06/24/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 | 04/18/2024 | 7/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 556681 | 01905 | 10 | Solar | 05_01_412L4 | 09/25/2023 | 10/03/2023 | 6 | 0 | 6 | 10/04/2023 | 10/04/2023 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 | 09/25/2023 | 12/20/2024 | Y | EXP | 365 | 03/06/2024 | 04/17/2024 | 43 | 0 | 43 |  |  | 5/22/2024 | Connected |  | N
National Grid | LOWELL | 342936 | 01852 | 7.68 | Solar | 05_01_602W2 | 03/02/2021 | 03/08/2021 | 4 | 4 | 0 | 03/09/2021 | 03/09/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 |  | 4/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2021 | Connected |  | Y
National Grid | TEWKSBURY | 544185 | 01876 | 18.85 | Solar | 05_05_115W44 | 08/04/2023 | 08/08/2023 | 2 | 0 | 2 | 08/09/2023 | 08/09/2023 | 161 | 28 | 133 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 194004 | 01844 | 136 | Solar | 05_05_311W5 | 08/30/2018 | 09/27/2018 | 8 | 5 | 3 | 09/28/2018 | 09/28/2018 | 54 | 25 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2018 |  | 12/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 203910 | 01523 | 0 | Solar | 05_12_28L2 | 12/18/2018 | 12/31/2018 | 7 | 0 | 7 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  | 1/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | Connected |  | N
National Grid | AUBURN | 630759 | 01501 | 10 | Solar | 05_12_6J2 | 08/07/2024 | 08/14/2024 | 3 | 0 | 3 | 08/15/2024 | 08/15/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 668859 | 01571 | 6 | Solar | 05_14_3L5 | 01/30/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 176048 | 01440 | 300 | Solar | 05_14_59L5 | 01/26/2015 | 01/26/2015 | 4 | 0 | 4 | 02/03/2015 | 02/03/2015 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 734586 | 02721 | 11.5 | Solar | 05_14_74L2 | 11/18/2025 | 11/19/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 | 11/18/2025 | 2/4/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | MARLBOROUGH | 685367 | 01752 | 16.34 | Solar | 05_01_216W4 | 04/21/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | MANCHESTER | 664182 | 01944 | 3.8 | Solar | 05_01_26W1 | 01/07/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 66 | 44 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 558380 | 01905 | 15.2 | Solar | 05_01_412L4 | 10/02/2023 | 10/23/2023 | 15 | 14 | 1 | 10/24/2023 | 10/24/2023 | 55 | 39 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  | 1/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2024 | Connected |  | N
National Grid | LOWELL | 346682 | 01852 | 22.8 | Solar | 05_01_602W2 | 03/18/2021 | 04/01/2021 | 10 | 10 | 0 | 04/02/2021 | 04/02/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 03/18/2021 | 4/1/2022 | Y | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 662528 | 01876 | 7.6 | Solar | 05_05_115W44 | 12/26/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 12/26/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | METHUEN | 200830 | 01844 | 10 | Solar | 05_05_311W5 | 11/09/2018 | 11/20/2018 | 4 | 0 | 4 | 11/21/2018 | 11/21/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2018 |  | 12/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2019 | Connected |  | N
National Grid | LANCASTER | 203625 | 01523 | 3.8 | Solar | 05_12_28L2 | 12/27/2018 | 01/04/2019 | 4 | 0 | 4 | 01/07/2019 | 01/07/2019 | 155 | 0 | 155 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 657888 | 01501 | 7.6 | Solar | 05_12_6J2 | 12/02/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 671248 | 01571 | 5.76 | Solar | 05_14_43L2 | 02/10/2025 | 02/27/2025 | 2 | 0 | 2 | 02/28/2025 | 02/28/2025 | 70 | 52 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | HUBBARDSTON | 176478 | 01452 | 133.2 | Solar | 05_14_59L5 | 05/18/2016 | 05/18/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 428 | 0 | 428 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2016 |  | 2/28/2018 | N | EXP | 617 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 756155 | 02723 | 3.8 | Solar | 05_14_74L2 | 03/12/2026 | 03/19/2026 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MARLBOROUGH | 686227 | 01752 | 10 | Solar | 05_01_216W4 | 04/18/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 696569 | 01930 | 15.96 | Solar | 05_01_26W1 | 06/05/2025 | 06/09/2025 | 2 | 0 | 2 | 06/10/2025 | 06/10/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | LYNN | 527634 | 01905 | 6 | Solar | 05_01_412L4 | 10/24/2023 | 05/25/2023 | 11 | 10 | 1 | 11/08/2023 | 11/08/2023 | 65 | 42 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 2/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | METHUEN | 351897 | 01844 | 3.8 | Solar | 05_01_602W2 | 05/10/2021 | 05/14/2021 | 3 | 0 | 3 | 05/17/2021 | 05/17/2021 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 176354 | 01876 | 38 | Solar | 05_05_115W45 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 | 05/18/2015 | 05/18/2015 | 386 | 0 | 386 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 205105 | 01844 | 5 | Solar | 05_05_311W5 | 01/17/2019 | 01/30/2019 | 8 | 8 | 0 | 01/31/2019 | 01/31/2019 | 152 | 0 | 152 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 293839 | 01510 | 10 | Solar | 05_12_28L2 | 05/28/2020 | 06/15/2020 | 12 | 12 | 0 | 06/16/2020 | 06/16/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 6/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2020 | Connected |  | N
National Grid | AUBURN | 701479 | 01501 | 6.72 | Solar | 05_12_6J2 | 06/28/2025 | 07/14/2025 | 5 | 0 | 5 | 07/28/2025 | 07/28/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/28/2025 | 9/10/2026 | Y | EXP | 365 | 11/14/2025 | 12/15/2025 | 32 | 0 | 32 |  |  | 1/20/2026 | Connected |  | N
National Grid | DUDLEY | 710789 | 01571 | 11.4 | Solar | 05_14_43L2 | 08/08/2025 | 10/20/2025 | 4 | 0 | 4 | 10/21/2025 | 10/21/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 | 08/08/2025 | 12/17/2026 | Y | EXP | 365 | 01/28/2026 |  | 64 | 0 | 64 |  |  |  | Construction |  | N
National Grid | GARDNER | 405741 | 01440 | 0 | Battery Add-On | 05_14_59L5 | 01/23/2022 | 01/31/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 03/02/2022 | 21 | 15 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTPORT | 176004 | 02790 | 7.6 | Solar | 05_14_74L2 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2015 |  | 8/19/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 1/25/2017 | 1/25/2017 | 1/25/2017 | Connected |  | N
National Grid | MARLBOROUGH | 696423 | 01752 | 10 | Solar | 05_01_216W4 | 06/09/2025 | 06/18/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 9/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | GLOUCESTER | 710851 | 01930 | 5.76 | Solar | 05_01_26W1 | 08/08/2025 | 09/05/2025 | 4 | 0 | 4 | 09/08/2025 | 09/08/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | LYNN | 547469 | 01905 | 6 | Solar | 05_01_412L4 | 08/23/2023 | 08/28/2023 | 3 | 1 | 2 | 08/29/2023 | 08/29/2023 | 53 | 26 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 452437 | 01832 | 8.12 | Solar | 05_01_602W2 | 10/04/2022 | 10/28/2022 | 18 | 14 | 4 | 10/31/2022 | 10/31/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 | 10/04/2022 | 5/4/2024 | Y | EXP | 365 | 04/20/2023 | 05/03/2023 | 14 | 0 | 14 |  |  | 5/12/2023 | Connected |  | N
National Grid | TEWKSBURY | 176796 | 01876 | 216 | Solar | 05_05_115W45 | 02/25/2016 | 02/25/2016 | 1 | 1 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2016 | 02/25/2016 | 3/2/2017 | Y | EXP | 120 | 01/05/2017 | 01/30/2017 | 16 | 0 | 16 | 5/5/2017 | 5/5/2017 | 5/8/2017 | Connected |  | N
National Grid | METHUEN | 289784 | 01844 | 8.41 | Solar | 05_05_311W5 | 04/29/2020 | 05/05/2020 | 3 | 0 | 3 | 05/06/2020 | 05/06/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2021 | Connected |  | N
National Grid | CLINTON | 359131 | 01510 | 5.22 | Solar | 05_12_28L2 | 05/19/2021 | 06/07/2021 | 12 | 11 | 1 | 06/08/2021 | 06/08/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2021 |  | 6/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2021 | Connected |  | N
National Grid | AUBURN | 712486 | 01501 | 10.47 | Solar | 05_12_6J2 | 08/22/2025 | 08/26/2025 | 2 | 0 | 2 | 08/27/2025 | 08/27/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | DUDLEY | 747031 | 01571 | 11.2 | Solar | 05_14_43L2 | 01/23/2026 | 01/30/2026 | 2 | 0 | 2 | 02/09/2026 | 02/09/2026 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2026 |  | 3/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HUBBARDSTON | 586370 | 01452 | 2890 | Battery Add-On | 05_14_59L5 | 02/01/2024 |  | 264 | 254 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 177002 | 02723 | 195 | Solar | 05_14_74L2 | 07/21/2016 | 07/21/2016 | 0 | 0 | 0 | 07/22/2016 | 07/22/2016 | 389 | 6 | 383 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2016 |  | 2/28/2018 | N | EXP | 555 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 546068 | 01752 | 500 | Solar | 05_01_216W5 | 09/07/2023 | 10/12/2023 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 | 11/03/2023 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MANCHESTER | 716350 | 01944 | 11.517 | Solar | 05_01_26W1 | 09/03/2025 | 09/29/2025 | 4 | 0 | 4 | 10/08/2025 | 10/08/2025 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2026 | Connected |  | N
National Grid | LYNN | 552482 | 01905 | 10 | Solar | 05_01_412L4 | 09/13/2023 | 09/19/2023 | 4 | 2 | 2 | 09/20/2023 | 09/20/2023 | 27 | 6 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 |  | 2/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | HAVERHILL | 438280 | 01832 | 15.2 | Solar | 05_01_602W2 | 03/12/2024 | 07/04/2022 | 15 | 13 | 2 | 04/02/2024 | 04/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2025 | Connected |  | N
National Grid | ANDOVER | 177182 | 01810 | 120 | Solar | 05_05_115W45 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2016 | 08/12/2016 | 8/17/2017 | Y | EXP | 343 | 01/05/2017 | 05/04/2017 | 82 | 0 | 82 | 5/5/2017 | 5/5/2017 | 5/8/2017 | Connected |  | N
National Grid | METHUEN | 324974 | 01844 | 115.2 | Solar | 05_05_311W5 | 11/10/2020 |  | 14 | 9 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 453090 | 01510 | 8.7 | Solar | 05_12_28L2 | 09/26/2022 | 09/29/2022 | 3 | 2 | 1 | 09/30/2022 | 09/30/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2022 |  | 12/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2023 | Connected |  | N
National Grid | AUBURN | 715339 | 01501 | 2.7 | Solar | 05_12_6J2 | 08/29/2025 | 09/19/2025 | 4 | 0 | 4 | 10/07/2025 | 10/07/2025 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 178362 | 01571 | 3.8 | Solar | 05_14_43L2 | 03/30/2018 | 03/30/2018 | 5 | 5 | 0 | 04/09/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 |  | 4/7/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 587585 | 01440 | 23 | Solar | 05_14_59L5 | 02/02/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 177887 | 02723 | 300 | Natural Gas | 05_14_74L2 | 04/11/2017 | 04/11/2017 | 40 | 40 | 0 | 06/14/2017 | 06/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 4/17/2018 | N | EXP | 284 |  |  | 0 | 0 | 0 | 4/5/2018 | 4/5/2018 | 4/5/2018 | Connected |  | N
National Grid | MARLBOROUGH | 174377 | 01752 | 1000 | Solar | 05_01_216W5 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 08/17/2012 | 47 | 0 | 47 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/15/2013 | N | STD | 0 | 11/02/2017 | 08/10/2017 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 719926 | 01930 | 11.5 | Solar | 05_01_26W1 | 09/17/2025 | 09/30/2025 | 5 | 3 | 2 | 10/27/2025 | 10/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 | 09/17/2025 | 1/7/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | LYNN | 552358 | 01905 | 6 | Solar | 05_01_412L4 | 09/01/2023 | 09/05/2023 | 1 | 0 | 1 | 09/06/2023 | 09/06/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 | 09/01/2023 | 10/27/2024 | Y | EXP | 365 | 01/27/2024 | 04/03/2024 | 68 | 0 | 68 |  |  | 4/16/2024 | Connected |  | N
National Grid | METHUEN | 473103 | 01844 | 14.79 | Solar | 05_01_602W2 | 11/03/2022 |  | 171 | 72 | 99 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 177406 | 01810 | 7.6 | Solar | 05_05_115W45 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 139 | 0 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 |  | 7/5/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 329523 | 01844 | 100.8 | Solar | 05_05_311W5 | 12/14/2020 | 12/21/2020 | 4 | 0 | 4 | 12/22/2020 | 12/22/2020 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 12/14/2020 |  | Y | EXP | 0 | 04/07/2021 | 12/20/2021 | 257 | 7 | 250 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 373988 | 01510 | 9.86 | Solar | 05_12_28L2 | 08/04/2021 | 08/09/2021 | 4 | 2 | 2 | 08/10/2021 | 08/10/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2021 | Connected |  | N
National Grid | AUBURN | 226580 | 01501 | 1950 | Natural Gas | 05_12_72L1 | 07/25/2019 | 10/29/2019 | 65 | 58 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2019 | 01/31/2020 | 63 | 31 | 32 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2021 | 07/25/2019 | 9/9/2026 | Y | STD | 161 | 10/09/2024 |  | 540 | 540 | 0 |  |  |  | Construction |  | Y
National Grid | DUDLEY | 178551 | 01571 | 9 | Solar | 05_14_43L2 | 03/09/2018 | 03/09/2018 | 18 | 18 | 0 | 04/12/2018 | 04/12/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2018 |  | 3/18/2019 | N | EXP | 322 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 609316 | 01440 | 23 | Solar | 05_14_59L5 | 05/07/2024 | 05/17/2024 | 9 | 7 | 2 | 05/20/2024 | 05/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2024 |  | 6/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 177993 | 02790 | 15.2 | Solar | 05_14_74L2 | 10/24/2017 | 10/24/2017 | 14 | 14 | 0 | 11/27/2017 | 11/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 11/1/2018 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  | 7/18/2018 | Connected |  | N
National Grid | MARLBOROUGH | 174376 | 01752 | 1954 | Solar | 05_01_216W5 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 08/17/2012 | 47 | 0 | 47 |  | 0 | 0 | 0 | 03/26/2014 | 03/26/2014 | 0 | 0 | 0 | 3/14/2013 | 05/29/2012 | 8/31/2017 | Y | STD | 1631 | 11/02/2017 | 08/10/2017 | 0 | 0 | 0 | 6/27/2017 | 6/27/2017 | 9/29/2017 | Connected |  | N
National Grid | MANCHESTER | 728456 | 01944 | 10 | Solar | 05_01_26W1 | 10/22/2025 | 10/26/2025 | 18 | 17 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 572497 | 01915 | 7.25 | Solar | 05_01_412L4 | 12/11/2023 | 12/14/2023 | 3 | 0 | 3 | 12/15/2023 | 12/15/2023 | 31 | 6 | 25 | 02/09/2024 | 03/12/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 03/12/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 2/29/2024 |  | 3/7/2025 | N | EXP | 365 | 03/08/2024 | 04/19/2024 | 43 | 0 | 43 |  |  | 5/30/2024 | Connected |  | N
National Grid | METHUEN | 487740 | 01844 | 9.86 | Solar | 05_01_602W2 | 01/05/2023 | 01/09/2023 | 2 | 0 | 2 | 01/10/2023 | 01/10/2023 | 86 | 25 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 177402 | 01810 | 10 | Solar | 05_05_115W45 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2016 | 06/29/2016 | 7/5/2017 | Y | EXP | 352 | 05/23/2017 | 06/23/2017 | 22 | 0 | 22 | 7/17/2017 | 7/17/2017 | 7/19/2017 | Connected |  | N
National Grid | METHUEN | 355075 | 01844 | 166.6 | Solar | 05_05_311W5 | 05/21/2021 | 06/06/2021 | 9 | 0 | 9 |  |  | 41 | 16 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 397029 | 01510 | 20 | Solar | 05_12_28L2 | 12/09/2021 | 12/20/2021 | 8 | 6 | 2 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 |  | 1/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 724946 | 01501 | 1000 | Solar | 05_12_72L1 | 12/08/2025 | 03/10/2026 | 61 | 51 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/11/2026 |  | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DUDLEY | 178603 | 01571 | 3.8 | Solar | 05_14_43L2 | 04/09/2018 | 04/09/2018 | 13 | 0 | 13 | 04/27/2018 | 04/27/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2018 | 04/09/2018 | 11/29/2019 | Y | EXP | 568 | 09/12/2019 | 10/15/2019 | 33 | 0 | 33 |  |  | 10/23/2019 | Connected |  | N
National Grid | WESTMINSTER | 645946 | 01473 | 10 | Solar | 05_14_59L5 | 10/10/2024 | 10/28/2024 | 12 | 10 | 2 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2025 | Connected |  | N
National Grid | FALL RIVER | 184808 | 02721 | 25.2 | Solar | 05_14_74L2 | 05/08/2018 | 05/08/2018 | 6 | 0 | 6 | 05/17/2018 | 05/17/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 177492 | 01752 | 7.6 | Solar | 05_01_216W5 | 12/13/2016 | 12/13/2016 | 6 | 6 | 0 | 12/21/2016 | 12/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 |  | 12/18/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 9/22/2017 | 9/22/2017 | 9/22/2017 | Connected |  | N
National Grid | GLOUCESTER | 587625 | 01930 | 200 | Solar | 05_01_26W2 | 03/14/2024 | 07/10/2025 | 328 | 322 | 6 |  |  | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | BEVERLY | 573922 | 01915 | 10 | Solar | 05_01_412L4 | 12/01/2023 | 12/06/2023 | 3 | 0 | 3 | 12/07/2023 | 12/07/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 | 12/01/2023 | 4/14/2025 | Y | EXP | 365 | 05/02/2024 | 08/23/2024 | 114 | 0 | 114 |  |  | 11/24/2024 | Connected |  | N
National Grid | METHUEN | 493004 | 01844 | 15.95 | Solar | 05_01_602W2 | 01/17/2023 | 02/08/2023 | 16 | 15 | 1 | 02/09/2023 | 02/09/2023 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2023 | 01/17/2023 | 7/26/2024 | Y | EXP | 365 | 08/15/2023 | 09/22/2023 | 39 | 0 | 39 |  |  | 10/3/2023 | Connected |  | N
National Grid | TEWKSBURY | 177448 | 01876 | 96 | Solar | 05_05_115W45 | 09/20/2016 | 09/20/2016 | 0 | 0 | 0 | 09/20/2016 | 09/20/2016 | 54 | 2 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/25/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 365643 | 01844 | 7.54 | Solar | 05_05_311W5 | 07/07/2021 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 422580 | 01510 | 0 | Solar | 05_12_28L2 | 04/08/2022 | 04/21/2022 | 9 | 8 | 1 | 04/22/2022 | 04/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2022 |  | 5/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N
National Grid | AUBURN | 177522 | 01501 | 24 | Solar | 05_12_72L1 | 02/11/2016 | 02/11/2016 | 3 | 0 | 3 | 02/17/2016 | 02/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 10/4/2017 | N | EXP | 595 |  |  | 0 | 0 | 0 | 9/29/2016 | 9/29/2016 | 10/5/2016 | Connected |  | N
National Grid | DUDLEY | 194175 | 01571 | 65 | Solar | 05_14_43L2 | 08/23/2018 | 10/16/2018 | 35 | 0 | 35 | 10/17/2018 | 10/17/2018 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 667034 | 01473 | 10 | Solar | 05_14_59L5 | 02/03/2025 | 02/20/2025 | 4 | 0 | 4 | 02/21/2025 | 02/21/2025 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 222991 | 02723 | 153.3 | Solar | 05_14_74L2 | 04/26/2019 | 05/16/2019 | 14 | 9 | 5 | 05/17/2019 | 05/17/2019 | 18 | 4 | 14 | 08/13/2019 | 09/18/2019 | 26 | 26 | 0 |  |  | 0 | 0 | 0 | 09/18/2019 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | EXP | 734 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 178289 | 01752 | 11.4 | Solar | 05_01_216W5 | 03/28/2018 | 03/28/2018 | 7 | 7 | 0 | 04/09/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 4/3/2019 | N | EXP | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 641473 | 01944 | 125 | Solar | 05_01_26W2 | 09/19/2024 | 10/29/2024 | 27 | 18 | 9 | 10/30/2024 | 10/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 6/8/2026 | N | EXP | 120 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 574933 | 01915 | 499 | Solar | 05_01_412L4 | 01/19/2024 |  | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 511164 | 01844 | 9.57 | Solar | 05_01_602W2 | 03/15/2023 | 04/21/2023 | 26 | 25 | 1 | 04/24/2023 | 04/24/2023 | 90 | 73 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 9/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | TEWKSBURY | 178081 | 01876 | 10 | Solar | 05_05_115W45 | 05/08/2017 | 05/08/2017 | 6 | 6 | 0 | 05/17/2017 | 05/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2017 | 05/08/2017 | 5/14/2018 | Y | EXP | 361 | 10/23/2017 | 11/09/2017 | 8 | 0 | 8 | 11/9/2017 | 11/9/2017 | 11/28/2017 | Connected |  | N
National Grid | METHUEN | 592139 | 01844 | 6 | Solar | 05_05_311W5 | 02/27/2024 | 03/05/2024 | 5 | 0 | 5 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 02/27/2024 | 3/22/2026 | Y | EXP | 365 | 04/17/2024 | 04/16/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 430870 | 01510 | 15.2 | Solar | 05_12_28L2 | 05/16/2022 | 05/17/2022 | 1 | 0 | 1 | 07/12/2022 | 07/12/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 12/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 177914 | 01501 | 365 | Natural Gas | 05_12_72L1 | 10/20/2017 | 10/20/2017 | 55 | 0 | 55 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 |  | 6/28/2019 | N | STD | 252 |  |  | 0 | 0 | 0 |  |  | 6/13/2019 | Connected |  | N
National Grid | DUDLEY | 305828 | 01571 | 9.6 | Solar | 05_14_43L2 | 08/10/2020 | 09/15/2020 | 25 | 23 | 2 | 09/16/2020 | 09/16/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2020 | Connected |  | N
National Grid | HUBBARDSTON | 724788 | 01452 | 5.76 | Solar | 05_14_59L5 | 10/08/2025 | 10/22/2025 | 9 | 8 | 1 | 10/23/2025 | 10/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2026 | Connected |  | N
National Grid | FALL RIVER | 327655 | 02721 | 7.6 | Solar | 05_14_74L2 | 12/08/2020 | 12/09/2020 | 0 | 0 | 0 | 12/10/2020 | 12/10/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 | 12/08/2020 |  | Y | EXP | 365 | 05/05/2021 | 06/18/2021 | 44 | 0 | 44 |  |  | 8/24/2021 | Connected |  | N
National Grid | MARLBOROUGH | 178323 | 01752 | 249.8 | Solar | 05_01_216W5 | 03/29/2018 | 03/29/2018 | 9 | 0 | 9 | 05/30/2018 | 05/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2018 |  | 12/31/2020 | N | EXP | 373 |  |  | 0 | 0 | 0 |  |  | 2/19/2021 | Connected |  | N
National Grid | GLOUCESTER | 649613 | 01930 | 200 | Solar | 05_01_26W2 | 05/06/2025 | 07/25/2025 | 55 | 45 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | BEVERLY | 587291 | 01915 | 4.93 | Solar | 05_01_412L4 | 02/13/2024 | 02/15/2024 | 2 | 0 | 2 | 02/16/2024 | 02/16/2024 | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 523055 | 01832 | 7.6 | Solar | 05_01_602W2 | 05/15/2023 | 05/15/2023 | 0 | 0 | 0 | 05/16/2023 | 05/16/2023 | 195 | 34 | 161 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 178427 | 01876 | 42 | Solar | 05_05_115W45 | 01/18/2018 | 01/18/2018 | 15 | 0 | 15 | 02/08/2018 | 02/08/2018 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 |  | 1/23/2019 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  | 8/15/2018 | Connected |  | N
National Grid | METHUEN | 647601 | 01844 | 7.6 | Solar | 05_05_311W5 | 10/18/2024 | 11/19/2024 | 8 | 5 | 3 | 11/20/2024 | 11/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N
National Grid | CLINTON | 178031 | 01510 | 5.2 | Solar | 05_12_72L1 | 10/25/2017 | 10/25/2017 | 24 | 24 | 0 | 12/11/2017 | 12/11/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 10/25/2017 | 10/15/2019 | Y | EXP | 673 | 08/08/2018 | 10/05/2018 | 58 | 0 | 58 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 364023 | 01501 | 9.8 | Solar | 05_14_43L2 | 06/28/2021 | 12/15/2021 | 1 | 0 | 1 | 06/30/2021 | 06/30/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 | 06/28/2021 | 12/26/2023 | Y | EXP | 365 | 01/18/2022 | 07/26/2022 | 189 | 0 | 189 |  |  | 8/3/2023 | Connected |  | N
National Grid | DUDLEY | 724647 | 01571 | 0 | Solar | 05_14_59L6 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTMINSTER | 348265 | 01473 | 499.9 | Solar | 05_14_74L2 | 06/10/2021 |  | 315 | 315 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 256639 | 02721 | 7.6 | Solar | 05_01_216W5 | 10/14/2019 | 10/21/2019 | 4 | 0 | 4 | 10/22/2019 | 10/22/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 | 10/14/2019 | 10/21/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2021 | Connected |  | N
National Grid | MARLBOROUGH | 742221 | 01752 | 15.76 | Solar | 05_01_26W2 | 12/25/2025 | 12/31/2025 | 3 | 0 | 3 | 01/02/2026 | 01/02/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GLOUCESTER | 595397 | 01930 | 7.296 | Solar | 05_01_412L4 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 | 04/01/2024 | 7/2/2025 | Y | EXP | 365 | 08/01/2024 | 08/19/2024 | 19 | 0 | 19 |  |  | 8/22/2024 | Connected |  | N
National Grid | BEVERLY | 553543 | 01915 | 6 | Solar | 05_01_602W2 | 09/22/2023 | 09/26/2023 | 2 | 0 | 2 | 09/27/2023 | 09/27/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 09/22/2023 | 12/2/2024 | Y | EXP | 365 | 05/03/2024 | 05/18/2024 | 16 | 0 | 16 |  |  | 5/23/2024 | Connected |  | N
National Grid | HAVERHILL | 192209 | 01832 | 17.6 | Solar | 05_05_115W45 | 07/31/2018 | 08/30/2018 | 12 | 2 | 10 | 08/31/2018 | 08/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2018 | 07/31/2018 | 10/3/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2019 | Connected |  | N
National Grid | ANDOVER | 664880 | 01810 | 7.6 | Solar | 05_05_311W5 | 01/09/2025 | 01/31/2025 | 4 | 0 | 4 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/09/2025 | 3/19/2026 | Y | EXP | 365 | 03/25/2025 | 09/10/2025 | 170 | 0 | 170 |  |  | 10/14/2025 | Connected |  | N
National Grid | METHUEN | 558123 | 01844 | 3.8 | Solar | 05_12_28L2 | 09/25/2023 | 10/03/2023 | 6 | 0 | 6 | 10/04/2023 | 10/04/2023 | 52 | 30 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 1/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | CLINTON | 178181 | 01510 | 3.8 | Solar | 05_12_72L1 | 04/13/2018 | 04/13/2018 | 13 | 0 | 13 | 05/02/2018 | 05/02/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 4/18/2019 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 378895 | 01501 | 6 | Solar | 05_14_43L2 | 09/16/2021 | 12/21/2021 | 3 | 0 | 3 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 |  | 3/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2022 | Connected |  | Y
National Grid | DUDLEY | 738704 | 01571 | 22.8 | Solar | 05_14_59L6 | 12/08/2025 | 12/10/2025 | 2 | 0 | 2 | 12/11/2025 | 12/11/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HUBBARDSTON | 348029 | 01452 | 7.6 | Solar | 05_14_74L2 | 05/04/2021 | 05/05/2021 | 0 | 0 | 0 | 05/06/2021 | 05/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 | 05/04/2021 | 2/28/2023 | Y | EXP | 365 | 11/25/2021 | 01/24/2022 | 61 | 0 | 61 |  |  | 3/9/2022 | Connected |  | N
National Grid | FALL RIVER | 497623 | 02721 | 18.27 | Solar | 05_01_216W5 | 02/01/2023 | 02/03/2023 | 3 | 2 | 1 | 02/06/2023 | 02/06/2023 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2023 | 02/01/2023 | 3/5/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 174587 | 01752 | 22.8 | Solar | 05_01_26W2 | 08/29/2011 | 08/29/2011 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2011 |  | 6/28/2012 | N | EXP | 227 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 6/28/2012 | Connected |  | N
National Grid | GLOUCESTER | 605221 | 01930 | 7.6 | Solar | 05_01_412L4 | 04/23/2024 | 05/14/2024 | 12 | 10 | 2 | 05/15/2024 | 05/15/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2024 | Connected |  | N
National Grid | BEVERLY | 561273 | 01915 | 6.38 | Solar | 05_01_602W2 | 11/14/2023 | 01/10/2024 | 39 | 31 | 8 | 01/11/2024 | 01/11/2024 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 192619 | 01832 | 10 | Solar | 05_05_115W45 | 08/06/2018 | 08/30/2018 | 7 | 2 | 5 | 08/31/2018 | 08/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 | 08/06/2018 | 9/27/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2019 | Connected |  | N
National Grid | ANDOVER | 703220 | 01810 | 7.6 | Solar | 05_05_311W5 | 07/08/2025 | 07/31/2025 | 2 | 0 | 2 | 08/01/2025 | 08/01/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | METHUEN | 555498 | 01844 | 23.8 | Solar | 05_12_28L2 | 09/14/2023 | 10/25/2023 | 28 | 23 | 5 | 10/26/2023 | 10/26/2023 | 49 | 30 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  | 1/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | CLINTON | 178590 | 01510 | 3.2 | Solar | 05_12_72L1 | 03/14/2018 | 03/14/2018 | 0 | 0 | 0 | 04/24/2018 | 04/24/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/20/2019 | N | EXP | 313 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 396668 | 01501 | 0 | Other | 05_14_43L2 | 01/04/2022 | 01/14/2022 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 03/02/2022 | 31 | 15 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 749645 | 01571 | 20.9 | Solar | 05_14_59L6 | 02/12/2026 | 03/17/2026 | 21 | 19 | 2 | 03/18/2026 | 03/18/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HUBBARDSTON | 361148 | 01452 | 7.6 | Solar | 05_14_74L2 | 07/04/2021 | 07/07/2021 | 2 | 0 | 2 | 07/08/2021 | 07/08/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2021 | 07/04/2021 | 3/10/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2022 | Connected |  | Y
National Grid | FALL RIVER | 521794 | 02721 | 13 | Solar | 05_01_216W5 | 04/28/2023 | 05/08/2023 | 7 | 5 | 2 | 05/09/2023 | 05/09/2023 | 65 | 47 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 9/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2023 | Connected |  | N
National Grid | MARLBOROUGH | 175624 | 01752 | 684 | Solar | 05_01_26W2 | 05/05/2014 | 05/05/2014 | 7 | 0 | 7 | 05/15/2014 | 05/15/2014 | 0 | 0 | 0 | 07/30/2014 | 08/29/2014 | 22 | 4 | 18 |  |  | 0 | 0 | 0 | 08/29/2014 | 22 | 4 | 18 |  |  | 0 | 0 | 0 | 10/2/2014 | 05/05/2014 | 12/31/2015 | Y | EXP | 455 | 08/25/2015 | 11/23/2015 | 61 | 0 | 61 | 11/18/2015 | 11/18/2015 | 12/16/2015 | Connected |  | N
National Grid | GLOUCESTER | 606033 | 01930 | 10 | Solar | 05_01_412L4 | 04/26/2024 | 05/03/2024 | 5 | 0 | 5 | 05/06/2024 | 05/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | BEVERLY | 566632 | 01915 | 2000 | Solar | 05_01_602W2 | 11/01/2023 |  | 95 | 55 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 197978 | 01844 | 6 | Solar | 05_05_115W45 | 10/08/2018 | 01/03/2019 | 43 | 41 | 2 | 01/04/2019 | 01/04/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 475389 | 01810 | 0 | Other | 05_05_311W6 | 12/08/2022 | 02/01/2023 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2023 | 03/02/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | METHUEN | 560873 | 01844 | 23 | Solar | 05_12_28L2 | 10/05/2023 | 10/06/2023 | 1 | 0 | 1 | 10/10/2023 | 10/10/2023 | 112 | 91 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 3/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2024 | Connected |  | N
National Grid | CLINTON | 196655 | 01510 | 3.8 | Solar | 05_12_72L1 | 09/21/2018 | 10/16/2018 | 5 | 5 | 0 | 10/17/2018 | 10/17/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 400900 | 01527 | 16.53 | Solar | 05_14_43L2 | 02/01/2022 | 02/03/2022 | 2 | 0 | 2 | 02/04/2022 | 02/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  | 6/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N
National Grid | DUDLEY | 175499 | 01571 | 29.455 | Solar | 05_14_59L6 | 09/26/2014 | 09/26/2014 | 6 | 0 | 6 | 10/07/2014 | 10/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2015 | 09/26/2014 | 12/31/2016 | Y | EXP | 641 | 10/22/2015 | 02/01/2016 | 67 | 0 | 67 | 5/17/2016 | 5/17/2016 | 6/2/2016 | Connected |  | N
National Grid | HUBBARDSTON | 365469 | 01452 | 7.6 | Solar | 05_14_74L2 | 07/13/2021 | 07/16/2021 | 3 | 0 | 3 | 07/19/2021 | 07/19/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2021 | 07/13/2021 | 8/16/2024 | Y | EXP | 365 | 01/18/2022 | 02/22/2022 | 36 | 0 | 36 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 641059 | 02721 | 5 | Solar | 05_01_216W5 | 09/19/2024 | 10/15/2024 | 3 | 0 | 3 | 10/16/2024 | 10/16/2024 | 57 | 40 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 09/19/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | MARLBOROUGH | 175849 | 01752 | 1000 | Solar | 05_01_26W2 | 05/20/2015 | 05/20/2015 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2015 | 07/08/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 | 02/10/2017 | 06/30/2016 | 0 | 0 | 0 | 8/3/2016 |  | 9/30/2017 | N | STD | 423 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 660754 | 01944 | 10 | Solar | 05_01_412L4 | 12/16/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 155 | 137 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 565997 | 01915 | 10 | Solar | 05_01_602W2 | 11/07/2023 | 11/09/2023 | 2 | 0 | 2 | 11/13/2023 | 11/13/2023 | 30 | 7 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 | 11/07/2023 | 1/10/2025 | Y | EXP | 365 | 03/23/2024 | 04/22/2024 | 31 | 0 | 31 |  |  | 4/30/2024 | Connected |  | N
National Grid | METHUEN | 205831 | 01844 | 4.8 | Solar | 05_05_115W45 | 02/27/2019 | 03/15/2019 | 12 | 11 | 1 | 03/18/2019 | 03/18/2019 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 | 02/27/2019 | 11/13/2019 | Y | EXP | 236 | 05/08/2019 | 06/06/2019 | 29 | 0 | 29 |  |  | 7/5/2019 | Connected |  | N
National Grid | ANDOVER | 175178 | 01810 | 1073.6 | Solar | 05_05_311W6 | 05/03/2013 | 05/03/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2013 | 07/02/2013 | 32 | 0 | 32 |  | 0 | 0 | 0 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 | 3/3/2014 |  | 12/31/2016 | N | STD | 1034 |  |  | 0 | 0 | 0 | 12/18/2015 | 12/18/2015 | 12/21/2015 | Connected |  | N
National Grid | METHUEN | 586229 | 01844 | 6 | Solar | 05_12_28L2 | 02/05/2024 | 02/07/2024 | 2 | 0 | 2 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 02/05/2024 | 3/18/2025 | Y | EXP | 365 | 05/08/2024 | 05/20/2024 | 13 | 0 | 13 |  |  | 7/19/2024 | Connected |  | N
National Grid | CLINTON | 468924 | 01510 | 10 | Solar | 05_12_72L1 | 11/01/2022 | 11/02/2022 | 1 | 0 | 1 | 11/03/2022 | 11/03/2022 | 60 | 42 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2023 | 11/01/2022 | 7/2/2024 | Y | EXP | 365 | 04/22/2023 | 06/30/2023 | 70 | 0 | 70 |  |  | 8/9/2023 | Connected |  | N
National Grid | MILLBURY | 406366 | 01527 | 470 | Solar | 05_14_43L2 | 01/28/2022 | 05/02/2022 | 64 | 54 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2023 | 01/28/2022 | 8/27/2024 | Y | STD | 209 |  |  | 0 | 0 | 0 |  |  | 7/5/2024 | Connected |  | N
National Grid | DUDLEY | 177121 | 01571 | 540 | Solar | 05_14_59L6 | 10/19/2016 | 10/19/2016 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2016 | 02/03/2017 | 46 | 36 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 392129 | 01473 | 7.6 | Solar | 05_14_74L2 | 10/29/2021 | 11/09/2021 | 5 | 5 | 0 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 3/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2023 | Connected |  | N
National Grid | FALL RIVER | 649301 | 02712 | 5.76 | Solar | 05_01_216W5 | 11/05/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 | 11/05/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 177238 | 01752 | 186.6 | Solar | 05_01_26W2 | 02/03/2017 | 02/03/2017 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/8/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 664981 | 01930 | 10 | Solar | 05_01_412L4 | 01/10/2025 | 01/28/2025 | 7 | 2 | 5 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 01/10/2025 | 7/12/2026 | Y | EXP | 365 | 06/12/2025 | 07/08/2025 | 27 | 0 | 27 |  |  | 10/28/2025 | Connected |  | N
National Grid | BEVERLY | 569809 | 01915 | 0 | Solar | 05_01_602W2 | 11/08/2023 | 11/13/2023 | 2 | 1 | 1 | 11/14/2023 | 11/14/2023 | 50 | 28 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2024 |  | 9/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | HAVERHILL | 304302 | 01832 | 3.8 | Solar | 05_05_115W45 | 08/07/2020 | 08/11/2020 | 1 | 0 | 1 | 08/12/2020 | 08/12/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 176833 | 01810 | 10 | Solar | 05_05_311W6 | 02/28/2016 | 02/28/2016 | 3 | 3 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2016 |  | 3/5/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/19/2016 | 7/19/2016 | 7/19/2016 | Connected |  | N
National Grid | METHUEN | 624869 | 01844 | 6.825 | Solar | 05_12_28L2 | 07/15/2024 | 03/25/2025 | 4 | 1 | 3 | 03/26/2025 | 03/26/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | CLINTON | 516020 | 01510 | 5 | Solar | 05_12_72L1 | 04/26/2023 | 05/26/2023 | 22 | 21 | 1 | 05/30/2023 | 05/30/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 04/26/2023 | 8/18/2024 | Y | EXP | 365 | 10/25/2023 | 10/25/2023 | 1 | 0 | 1 |  |  | 11/17/2023 | Connected |  | N
National Grid | AUBURN | 425587 | 01501 | 498 | Solar | 05_14_43L2 | 08/31/2022 | 09/20/2022 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2022 | 10/19/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 177730 | 01571 | 20 | Solar | 05_14_59L6 | 10/05/2017 | 10/05/2017 | 0 | 0 | 0 | 02/13/2018 | 02/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 10/10/2018 | N | EXP | 239 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N
National Grid | HUBBARDSTON | 405990 | 01452 | 0 | Battery Add-On | 05_14_74L2 | 02/01/2022 | 02/07/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2022 | 02/14/2022 | 5 | 0 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTPORT | 654500 | 02790 | 10 | Solar | 05_01_216W5 | 11/18/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | MARLBOROUGH | 177496 | 01752 | 15.2 | Solar | 05_01_26W2 | 12/13/2016 | 12/13/2016 | 4 | 4 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2016 |  | 12/19/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 2/7/2017 | 2/7/2017 | 2/7/2017 | Connected |  | N
National Grid | MANCHESTER | 669061 | 01944 | 11.5 | Solar | 05_01_412L4 | 02/04/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 | 02/04/2025 | 4/14/2026 | Y | EXP | 365 | 05/06/2025 | 07/11/2025 | 67 | 0 | 67 |  |  | 7/30/2025 | Connected |  | N
National Grid | BEVERLY | 570427 | 01915 | 10 | Solar | 05_01_602W2 | 11/21/2023 | 11/30/2023 | 7 | 4 | 3 | 12/01/2023 | 12/01/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 377985 | 01832 | 6 | Solar | 05_05_115W45 | 09/10/2021 | 12/07/2021 | 3 | 0 | 3 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 | 09/10/2021 | 5/25/2023 | Y | EXP | 365 | 04/12/2022 | 05/18/2022 | 37 | 0 | 37 |  |  | 6/29/2022 | Connected |  | N
National Grid | ANDOVER | 202096 | 01810 | 450 | Solar | 05_05_311W6 | 11/30/2018 | 12/21/2018 | 15 | 11 | 4 | 12/24/2018 | 12/24/2018 | 92 | 26 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 650150 | 01844 | 23 | Solar | 05_12_28L2 | 10/28/2024 | 11/20/2024 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 5/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2025 | Connected |  | N
National Grid | CLINTON | 565683 | 01510 | 3.8 | Solar | 05_12_72L1 | 10/24/2023 | 11/14/2023 | 3 | 1 | 2 | 11/15/2023 | 11/15/2023 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 433206 | 01501 | 10 | Solar | 05_14_43L2 | 06/07/2022 | 06/09/2022 | 2 | 0 | 2 | 06/10/2022 | 06/10/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2022 | 06/07/2022 | 10/20/2023 | Y | EXP | 365 | 09/28/2022 | 10/19/2022 | 22 | 0 | 22 |  |  | 11/17/2022 | Connected |  | N
National Grid | DUDLEY | 243231 | 01571 | 10 | Solar | 05_14_59L6 | 08/15/2019 | 08/21/2019 | 3 | 0 | 3 | 08/22/2019 | 08/22/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/15/2019 | 8/15/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N
National Grid | WESTMINSTER | 414167 | 01473 | 10 | Solar | 05_14_74L2 | 03/22/2022 |  | 328 | 156 | 172 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 656839 | 02721 | 5.76 | Solar | 05_01_216W5 | 11/25/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 177735 | 01752 | 1000 | Solar | 05_01_26W2 | 05/20/2015 | 05/20/2015 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2015 | 07/08/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 | 05/12/2016 | 06/30/2016 | 33 | 0 | 33 | 8/3/2016 | 05/20/2015 | 9/21/2018 | Y | STD | 779 |  |  | 0 | 0 | 0 |  |  | 9/10/2018 | Connected |  | N
National Grid | MANCHESTER | 685553 | 01944 | 11.4 | Solar | 05_01_412L4 | 04/16/2025 | 04/24/2025 | 5 | 0 | 5 | 04/25/2025 | 04/25/2025 | 98 | 90 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2025 |  | 9/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2025 | Connected |  | N
National Grid | BEVERLY | 579357 | 01915 | 5.22 | Solar | 05_01_602W2 | 02/26/2024 | 02/27/2024 | 1 | 0 | 1 | 02/28/2024 | 02/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/26/2024 | 3/19/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | METHUEN | 401114 | 01844 | 0 | Other | 05_05_115W45 | 01/06/2022 | 01/31/2022 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 02/02/2022 | 2 | 0 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 229547 | 01810 | 240 | Solar | 05_05_311W6 | 05/20/2019 | 06/05/2019 | 9 | 4 | 5 | 06/06/2019 | 06/06/2019 | 40 | 27 | 13 | 09/03/2019 | 10/07/2019 | 25 | 11 | 14 |  |  | 0 | 0 | 0 | 10/07/2019 | 25 | 11 | 14 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 651396 | 01844 | 9.86 | Solar | 05_12_28L2 | 11/01/2024 | 12/02/2024 | 5 | 0 | 5 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 | 11/01/2024 | 3/14/2026 | Y | EXP | 365 | 06/12/2025 | 06/12/2025 | 1 | 0 | 1 |  |  | 6/20/2025 | Connected |  | N
National Grid | CLINTON | 596850 | 01510 | 3.77 | Solar | 05_12_72L1 | 03/19/2024 | 03/21/2024 | 2 | 1 | 1 | 03/22/2024 | 03/22/2024 | 8 | 6 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 4/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 443275 | 01527 | 15.2 | Solar | 05_14_43L2 | 07/11/2022 | 07/13/2022 | 2 | 0 | 2 | 07/14/2022 | 07/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 |  | 8/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2022 | Connected |  | N
National Grid | DUDLEY | 257906 | 01571 | 11.4 | Solar | 05_14_59L6 | 10/02/2019 | 10/03/2019 | 0 | 0 | 0 | 10/04/2019 | 10/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 10/2/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2020 | Connected |  | N
National Grid | HUBBARDSTON | 529105 | 01452 | 3.8 | Solar | 05_14_74L2 | 06/21/2023 | 06/26/2023 | 3 | 0 | 3 | 06/27/2023 | 06/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 668947 | 02724 | 5 | Solar | 05_01_216W5 | 01/30/2025 | 04/25/2025 | 14 | 11 | 3 | 04/28/2025 | 04/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 | 01/30/2025 | 7/3/2026 | Y | EXP | 365 | 09/05/2025 | 09/04/2025 | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | MARLBOROUGH | 178054 | 01752 | 10 | Solar | 05_01_26W2 | 07/05/2017 | 07/05/2017 | 25 | 25 | 0 | 08/10/2017 | 08/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 7/11/2018 | N | EXP | 330 |  |  | 0 | 0 | 0 |  |  | 5/25/2018 | Connected |  | N
National Grid | MANCHESTER | 693374 | 01944 | 12.54 | Solar | 05_01_412L4 | 05/28/2025 |  | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 599345 | 01915 | 0 | Solar | 05_01_602W2 | 03/26/2024 | 04/26/2024 | 22 | 20 | 2 | 04/29/2024 | 04/29/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 5/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2024 | Connected |  | N
National Grid | HAVERHILL | 565509 | 01832 | 5 | Solar | 05_05_115W45 | 11/08/2023 | 11/29/2023 | 13 | 10 | 3 | 11/30/2023 | 11/30/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 296692 | 01810 | 10 | Solar | 05_05_311W6 | 06/16/2020 | 06/18/2020 | 1 | 0 | 1 | 06/19/2020 | 06/19/2020 | 51 | 26 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2021 | Connected |  | N
National Grid | METHUEN | 659984 | 01844 | 11.7 | Solar | 05_12_28L2 | 12/11/2024 | 03/26/2025 | 4 | 1 | 3 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | CLINTON | 641368 | 01510 | 10 | Solar | 05_12_72L1 | 09/18/2024 | 10/07/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/18/2024 | 11/20/2025 | Y | EXP | 365 | 01/29/2025 | 02/06/2025 | 9 | 0 | 9 |  |  | 2/25/2025 | Connected |  | Y
National Grid | AUBURN | 562970 | 01501 | 10 | Solar | 05_14_43L2 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 34 | 12 | 22 | 02/13/2024 | 03/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 03/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/25/2025 | N | EXP | 365 | 05/22/2024 | 01/31/2025 | 267 | 0 | 267 |  |  | 1/31/2025 | Connected |  | N
National Grid | DUDLEY | 306710 | 01571 | 133.2 | Solar | 05_14_59L6 | 08/18/2020 | 10/05/2020 | 33 | 28 | 5 | 10/06/2020 | 10/06/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 1/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 571180 | 01473 | 10 | Solar | 05_14_74L2 | 12/08/2023 | 12/13/2023 | 3 | 1 | 2 | 12/14/2023 | 12/14/2023 | 50 | 28 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 686255 | 02721 | 15.76 | Solar | 05_01_216W5 | 04/18/2025 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 178522 | 01752 | 2297.7 | Solar | 05_01_26W2 | 04/04/2018 | 04/05/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 693113 | 01944 | 23 | Solar | 05_01_412L4 | 05/29/2025 | 06/03/2025 | 3 | 0 | 3 | 06/04/2025 | 06/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2025 | 05/29/2025 | 7/28/2026 | Y | EXP | 365 | 10/29/2025 | 01/20/2026 | 84 | 0 | 84 |  |  | 1/9/2026 | Connected |  | N
National Grid | BEVERLY | 625690 | 01915 | 6 | Solar | 05_01_602W2 | 07/19/2024 | 08/05/2024 | 5 | 3 | 2 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/19/2024 | 9/11/2025 | Y | EXP | 365 | 10/10/2024 | 10/31/2024 | 22 | 0 | 22 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 570860 | 01832 | 6 | Solar | 05_05_115W45 | 11/20/2023 | 12/05/2023 | 11 | 7 | 4 | 12/06/2023 | 12/06/2023 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 11/20/2023 | 4/1/2025 | Y | EXP | 365 | 05/29/2024 | 07/25/2024 | 58 | 0 | 58 |  |  | 7/30/2024 | Connected |  | N
National Grid | ANDOVER | 311656 | 01810 | 10 | Solar | 05_05_311W6 | 09/22/2020 | 09/24/2020 | 1 | 0 | 1 | 09/25/2020 | 09/25/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 | 09/22/2020 | 9/1/2021 | Y | EXP | 365 | 02/26/2021 | 03/12/2021 | 14 | 0 | 14 |  |  | 4/7/2021 | Connected |  | N
National Grid | METHUEN | 664791 | 01844 | 4.64 | Solar | 05_12_28L2 | 01/09/2025 | 01/23/2025 | 4 | 0 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | CLINTON | 351267 | 01510 | 100 | Solar | 05_12_79J1 | 04/07/2021 | 04/30/2021 | 16 | 6 | 10 |  |  | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 622796 | 01501 | 7.6 | Solar | 05_14_43L2 | 07/05/2024 | 07/17/2024 | 1 | 0 | 1 | 07/18/2024 | 07/18/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 | 07/05/2024 | 11/24/2025 | Y | EXP | 365 | 09/19/2024 | 12/02/2024 | 75 | 0 | 75 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 309079 | 01571 | 3.8 | Solar | 05_14_59L6 | 08/26/2020 | 09/15/2020 | 13 | 13 | 0 | 09/16/2020 | 09/16/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2021 | Connected |  | N
National Grid | GARDNER | 646050 | 01440 | 6 | Solar | 05_14_74L2 | 10/09/2024 | 10/18/2024 | 4 | 0 | 4 | 10/21/2024 | 10/21/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/09/2024 | 1/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | FALL RIVER | 693561 | 02721 | 11.5 | Solar | 05_01_216W5 | 05/22/2025 | 06/04/2025 | 2 | 0 | 2 | 06/11/2025 | 06/11/2025 | 48 | 34 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 | 05/22/2025 | 9/2/2026 | Y | EXP | 365 | 11/04/2025 | 11/26/2025 | 23 | 0 | 23 |  |  | 12/3/2025 | Connected |  | N
National Grid | MARLBOROUGH | 194034 | 01752 | 150 | Solar | 05_01_26W2 | 08/23/2018 | 08/24/2018 | 0 | 0 | 0 | 08/27/2018 | 08/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 697368 | 01930 | 15.58 | Solar | 05_01_412L4 | 06/10/2025 | 06/24/2025 | 9 | 6 | 3 | 06/25/2025 | 06/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2025 | Connected |  | N
National Grid | NAHANT | 626147 | 01908 | 6 | Solar | 05_01_602W2 | 07/22/2024 | 08/19/2024 | 7 | 5 | 2 | 08/20/2024 | 08/20/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | METHUEN | 647595 | 01844 | 7.6 | Solar | 05_05_115W45 | 10/16/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 473323 | 01810 | 120 | Solar | 05_05_311W6 | 11/14/2022 | 12/13/2022 | 20 | 11 | 9 | 12/14/2022 | 12/14/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 | 11/14/2022 | 7/24/2025 | Y | EXP | 245 | 12/04/2024 | 12/10/2024 | 7 | 0 | 7 |  |  | 2/27/2025 | Connected |  | N
National Grid | METHUEN | 676411 | 01844 | 15.2 | Solar | 05_12_28L2 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 55 | 34 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 387711 | 01510 | 15.2 | Solar | 05_12_79J1 | 10/11/2021 | 10/13/2021 | 2 | 0 | 2 | 10/14/2021 | 10/14/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 |  | 2/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2022 | Connected |  | N
National Grid | AUBURN | 632056 | 01501 | 7.6 | Solar | 05_14_43L2 | 08/13/2024 | 09/24/2024 | 8 | 3 | 5 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 | 08/13/2024 | 12/31/2025 | Y | EXP | 365 | 01/25/2025 | 09/12/2025 | 231 | 0 | 231 |  |  | 11/7/2025 | Connected |  | N
National Grid | DUDLEY | 360062 | 01571 | 130 | Natural Gas | 05_14_59L6 | 06/09/2021 | 07/20/2021 | 28 | 18 | 10 |  |  | 54 | 29 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2022 | 06/09/2021 | 8/20/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | N
National Grid | WESTMINSTER | 648151 | 01473 | 5.76 | Solar | 05_14_74L2 | 10/30/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 724889 | 02790 |  | Battery Add-On | 05_01_216W6 | 10/15/2025 | 10/24/2025 | 6 | 2 | 4 | 10/27/2025 | 10/27/2025 | 48 | 33 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MARLBOROUGH | 204134 | 01752 | 333 | Solar | 05_01_26W2 | 12/18/2018 | 01/10/2019 | 14 | 12 | 2 | 01/11/2019 | 01/11/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 725829 | 01930 | 7.6 | Solar | 05_01_412L4 | 10/10/2025 | 10/24/2025 | 8 | 2 | 6 | 10/27/2025 | 10/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | NAHANT | 644276 | 01908 | 5.76 | Solar | 05_01_602W2 | 10/01/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/01/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | HAVERHILL | 661519 | 01832 | 3.2 | Solar | 05_05_115W45 | 12/18/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/18/2024 | 4/21/2026 | Y | EXP | 365 | 05/10/2025 | 05/09/2025 | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | ANDOVER | 588582 | 01810 | 5 | Solar | 05_05_311W6 | 03/11/2024 | 03/12/2024 | 1 | 0 | 1 | 03/13/2024 | 03/13/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 683914 | 01844 | 11.05 | Solar | 05_12_28L2 | 04/09/2025 | 05/07/2025 | 6 | 3 | 3 | 05/08/2025 | 05/08/2025 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | BOLTON | 490037 | 01740 | 4.06 | Solar | 05_12_79J1 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 |  | 4/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2023 | Connected |  | N
National Grid | AUBURN | 637795 | 01501 | 10 | Solar | 05_14_43L2 | 09/04/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/04/2024 | 11/2/2025 | Y | EXP | 365 | 12/19/2024 | 03/15/2025 | 86 | 0 | 86 |  |  | 3/22/2025 | Connected |  | N
National Grid | DUDLEY | 398978 | 01571 | 11.4 | Solar | 05_14_59L6 | 01/04/2022 | 01/07/2022 | 3 | 0 | 3 | 01/10/2022 | 01/10/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2022 |  | 3/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2022 | Connected |  | N
National Grid | GARDNER | 658199 | 01440 | 5.76 | Solar | 05_14_74L2 | 12/04/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2025 | Connected |  | N
National Grid | FALL RIVER | 750991 | 02721 | 10 | Solar | 05_01_216W6 | 02/20/2026 | 02/26/2026 | 4 | 0 | 4 | 02/27/2026 | 02/27/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2026 |  | 3/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MARLBOROUGH | 312600 | 01752 | 10 | Solar | 05_01_26W2 | 09/15/2020 | 09/16/2020 | 0 | 0 | 0 | 09/17/2020 | 09/17/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2021 | Connected |  | N
National Grid | MANCHESTER | 704897 | 01944 | 15.2 | Solar | 05_01_412L5 | 07/15/2025 | 08/07/2025 | 17 | 12 | 5 | 08/08/2025 | 08/08/2025 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NAHANT | 656989 | 01908 | 7.6 | Solar | 05_01_602W2 | 11/26/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/26/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | METHUEN | 667660 | 01844 | 7.6 | Solar | 05_05_115W45 | 01/24/2025 | 02/07/2025 | 5 | 1 | 4 | 02/10/2025 | 02/10/2025 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | ANDOVER | 618845 | 01810 | 11.4 | Solar | 05_05_311W6 | 06/18/2024 | 07/09/2024 | 4 | 2 | 2 | 07/10/2024 | 07/10/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2024 | Connected |  | N
National Grid | METHUEN | 691827 | 01844 | 23.8 | Solar | 05_12_28L2 | 05/15/2025 | 05/20/2025 | 3 | 0 | 3 | 05/21/2025 | 05/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | CLINTON | 711878 | 01510 | 17.6 | Solar | 05_12_79J1 | 08/15/2025 | 08/21/2025 | 4 | 0 | 4 | 08/22/2025 | 08/22/2025 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | AUBURN | 647179 | 01501 | 5.12 | Solar | 05_14_43L2 | 10/15/2024 | 10/25/2024 | 4 | 1 | 3 | 10/28/2024 | 10/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2024 | 10/15/2024 | 12/12/2025 | Y | EXP | 365 | 02/14/2025 | 04/28/2025 | 74 | 0 | 74 |  |  | 4/30/2025 | Connected |  | N
National Grid | DUDLEY | 405190 | 01571 | 0 | Battery Add-On | 05_14_59L6 | 01/24/2022 | 02/03/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2022 | 03/02/2022 | 18 | 15 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 668418 | 01440 | 3.8 | Solar | 05_14_74L2 | 01/28/2025 | 03/18/2025 | 25 | 20 | 5 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 | 01/28/2025 | 4/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 174686 | 02724 | 5.3 | Solar | 05_01_216W6 | 01/24/2011 | 01/24/2011 | 8 | 0 | 8 | 02/04/2011 | 02/04/2011 | 451 | 0 | 451 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 339198 | 01752 | 9.8 | Solar | 05_01_26W2 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 739666 | 01930 | 15.2 | Solar | 05_01_412L5 | 12/17/2025 | 12/18/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NAHANT | 664441 | 01908 | 0 | Solar | 05_01_602W2 | 01/08/2025 | 02/17/2025 | 7 | 2 | 5 | 02/18/2025 | 02/18/2025 | 15 | 0 | 15 | 03/11/2025 | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2025 | Connected |  | N
National Grid | HAVERHILL | 671676 | 01832 | 7.6 | Solar | 05_05_115W45 | 02/12/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 | 02/12/2025 | 4/9/2026 | Y | EXP | 365 | 05/02/2025 | 06/06/2025 | 36 | 0 | 36 |  |  | 6/23/2025 | Connected |  | N
National Grid | ANDOVER | 643293 | 01810 | 10 | Solar | 05_05_311W6 | 09/27/2024 | 10/11/2024 | 4 | 0 | 4 | 10/15/2024 | 10/15/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/27/2024 | 11/30/2025 | Y | EXP | 365 | 04/03/2025 | 04/09/2025 | 7 | 0 | 7 |  |  | 9/24/2025 | Connected |  | N
National Grid | METHUEN | 713834 | 01844 | 15.2 | Solar | 05_12_28L2 | 08/21/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 | 08/21/2025 | 10/24/2026 | Y | EXP | 365 | 11/21/2025 | 11/24/2025 | 4 | 0 | 4 |  |  | 12/13/2025 | Connected |  | N
National Grid | HARVARD | 754738 | 01451 | 16.72 | Solar | 05_12_79J2 | 03/11/2026 | 03/19/2026 | 5 | 2 | 3 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AUBURN | 647458 | 01501 | 7.6 | Solar | 05_14_43L2 | 10/22/2024 | 11/12/2024 | 2 | 0 | 2 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/22/2024 | 3/27/2026 | Y | EXP | 365 | 04/08/2025 | 12/22/2025 | 259 | 12 | 247 |  |  | 2/10/2026 | Connected |  | N
National Grid | DUDLEY | 414820 | 01571 | 7.6 | Solar | 05_14_59L6 | 03/01/2022 | 03/02/2022 | 1 | 0 | 1 | 03/03/2022 | 03/03/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 685217 | 01452 | 10 | Solar | 05_14_74L2 | 04/15/2025 | 05/13/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 04/15/2025 | 7/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | FALL RIVER | 174815 | 02721 | 995 | Solar | 05_01_216W6 | 07/31/2013 | 07/31/2013 | 7 | 0 | 7 | 08/12/2013 | 08/12/2013 | 0 | 0 | 0 | 01/14/2014 | 03/05/2014 | 34 | 0 | 34 |  |  | 0 | 0 | 0 | 03/05/2014 | 34 | 0 | 34 |  |  | 0 | 0 | 0 | 3/14/2014 |  | 12/31/2013 | N | EXP | 73 |  |  | 0 | 0 | 0 | 12/24/2014 | 12/24/2014 | 12/30/2014 | Connected |  | N
National Grid | MARLBOROUGH | 344165 | 01752 | 2000 | Solar | 05_01_26W2 | 07/28/2021 | 08/23/2021 | 18 | 10 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2021 | 11/23/2021 | 79 | 59 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 176210 | 01944 | 5 | Solar | 05_01_412L5 | 04/27/2015 | 04/27/2015 | 0 | 0 | 0 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2015 |  | 9/30/2015 | N | EXP | 153 |  |  | 0 | 0 | 0 | 3/22/2016 | 3/22/2016 | 3/29/2016 | Connected |  | N
National Grid | NAHANT | 666513 | 01908 | 23 | Solar | 05_01_602W2 | 01/17/2025 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 687395 | 01832 | 498 | Solar | 05_05_115W45 | 05/16/2025 | 07/08/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2025 | 08/05/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 662998 | 01810 | 3.8 | Solar | 05_05_311W6 | 12/30/2024 | 01/22/2025 | 4 | 0 | 4 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 | 12/30/2024 | 3/11/2026 | Y | EXP | 365 | 05/06/2025 | 12/22/2025 | 231 | 0 | 231 |  |  | 11/26/2025 | Connected |  | N
National Grid | METHUEN | 703718 | 01844 | 6.72 | Solar | 05_12_29W1 | 07/09/2025 | 07/29/2025 | 9 | 3 | 6 | 09/30/2025 | 09/30/2025 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 07/09/2025 | 12/5/2026 | Y | EXP | 365 | 01/22/2026 |  | 70 | 0 | 70 |  |  |  | Construction |  | N
National Grid | BOLTON | 392553 | 01740 | 13.96 | Solar | 05_12_79J2 | 11/22/2021 | 01/06/2022 | 10 | 6 | 4 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 11/22/2021 | 7/27/2023 | Y | EXP | 365 | 04/28/2022 | 06/02/2022 | 36 | 0 | 36 |  |  | 8/9/2022 | Connected |  | N
National Grid | MILLBURY | 649032 | 01527 | 13.975 | Solar | 05_14_43L2 | 10/22/2024 | 11/05/2024 | 10 | 7 | 3 | 11/06/2024 | 11/06/2024 | 61 | 25 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | DUDLEY | 486898 | 01571 | 16 | Solar | 05_14_59L6 | 01/11/2023 | 01/24/2023 | 9 | 8 | 1 | 01/25/2023 | 01/25/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | N
National Grid | WESTMINSTER | 637381 | 01473 | 7.6 | Solar | 05_14_74L3 | 09/03/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/03/2024 | 12/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTPORT | 175571 | 02790 | 6 | Solar | 05_01_216W6 | 10/10/2014 | 10/10/2014 | 10 | 7 | 3 | 10/28/2014 | 10/28/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 | 10/10/2014 | 4/22/2015 | Y | EXP | 153 | 03/11/2015 | 03/16/2015 | 3 | 0 | 3 | 3/12/2015 | 3/12/2015 | 6/1/2015 | Connected |  | N
National Grid | MARLBOROUGH | 358733 | 01752 | 133.2 | Solar | 05_01_26W2 | 09/03/2021 | 05/12/2022 | 172 | 162 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2024 |  | 1/25/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | LYNN | 177367 | 01905 | 528 | Solar | 05_01_412L5 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/28/2016 | 08/23/2016 | 39 | 21 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/3/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NAHANT | 686395 | 01908 | 3.9 | Solar | 05_01_602W2 | 04/21/2025 | 10/09/2025 | 2 | 0 | 2 | 10/15/2025 | 10/15/2025 | 55 | 38 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2026 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2026 | Connected |  | N
National Grid | METHUEN | 663198 | 01844 | 999.9 | Solar | 05_05_115W52 | 02/06/2025 | 04/24/2025 | 53 | 44 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/25/2025 | 05/22/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2026 | 02/06/2025 | 1/18/2027 | Y | STD | 308 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | ANDOVER | 670581 | 01810 | 3.8 | Solar | 05_05_311W6 | 02/06/2025 | 02/18/2025 | 2 | 0 | 2 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | METHUEN | 700420 | 01844 | 7.6 | Solar | 05_12_29W1 | 07/01/2025 | 07/15/2025 | 3 | 0 | 3 | 07/24/2025 | 07/24/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 07/01/2025 | 1/3/2027 | Y | EXP | 365 | 11/14/2025 | 11/14/2025 | 1 | 0 | 1 |  |  |  | Completion Documents |  | N
National Grid | HARVARD | 398056 | 01451 | 15.2 | Solar | 05_12_79J2 | 11/29/2021 | 12/08/2021 | 7 | 6 | 1 | 12/09/2021 | 12/09/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2022 |  | 5/1/2023 | N | EXP | 420 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 650321 | 01527 | 10 | Solar | 05_14_43L2 | 11/07/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 3/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | WEBSTER | 499224 | 01570 | 15.08 | Solar | 05_14_59L6 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2023 |  | 9/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2023 | Connected |  | Y
National Grid | WESTMINSTER | 656139 | 01473 | 6.175 | Solar | 05_14_74L3 | 11/28/2024 | 03/17/2025 | 28 | 26 | 2 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FALL RIVER | 177884 | 02721 | 38 | Solar | 05_01_216W6 | 10/19/2017 | 10/19/2017 | 10 | 10 | 0 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 |  | 10/25/2018 | N | EXP | 345 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 432998 | 01752 | 100 | Solar | 05_01_26W2 | 06/01/2022 | 06/30/2022 | 20 | 12 | 8 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 178735 | 01905 | 3.8 | Solar | 05_01_412L5 | 02/12/2018 | 03/15/2018 | 12 | 0 | 12 | 03/15/2018 | 03/15/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 | 02/12/2018 | 11/21/2019 | Y | EXP | 615 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 8/16/2019 | Connected |  | N
National Grid | NAHANT | 692468 | 01908 | 3.8 | Solar | 05_01_602W2 | 05/19/2025 | 07/30/2025 | 3 | 0 | 3 | 07/31/2025 | 07/31/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 05/19/2025 | 9/19/2026 | Y | EXP | 365 | 12/31/2025 | 01/30/2026 | 31 | 0 | 31 |  |  | 2/5/2026 | Connected |  | N
National Grid | METHUEN | 683283 | 01844 | 3.8 | Solar | 05_05_115W52 | 04/07/2025 | 04/24/2025 | 3 | 0 | 3 | 05/07/2025 | 05/07/2025 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 | 04/07/2025 | 6/24/2026 | Y | EXP | 365 | 07/09/2025 | 08/29/2025 | 52 | 0 | 52 |  |  |  | Completion Documents |  | Y
National Grid | ANDOVER | 671735 | 01810 | 3.8 | Solar | 05_05_311W6 | 02/12/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 | 02/12/2025 | 4/15/2026 | Y | EXP | 365 | 04/30/2025 | 11/21/2025 | 206 | 0 | 206 |  |  | 11/25/2025 | Connected |  | N
National Grid | LAWRENCE | 717420 | 01841 | 5.76 | Solar | 05_12_29W1 | 09/10/2025 | 10/03/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 | 09/10/2025 | 11/6/2026 | Y | EXP | 365 | 03/27/2026 |  | 6 | 0 | 6 |  |  |  | Construction |  | N
National Grid | CLINTON | 404987 | 01510 | 15.356 | Solar | 05_12_79J2 | 01/05/2022 | 01/06/2022 | 1 | 0 | 1 | 01/07/2022 | 01/07/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2022 | 01/05/2022 | 6/9/2023 | Y | EXP | 365 | 04/28/2022 | 06/08/2022 | 42 | 0 | 42 |  |  | 6/15/2022 | Connected |  | N
National Grid | AUBURN | 652297 | 01501 | 5.76 | Solar | 05_14_43L2 | 11/14/2024 | 12/17/2024 | 7 | 0 | 7 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 530104 | 01570 | 9.86 | Solar | 05_14_59L6 | 06/17/2023 | 06/20/2023 | 13 | 8 | 5 | 06/21/2023 | 06/21/2023 | 21 | 0 | 21 | 08/09/2023 | 09/12/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 09/12/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 10/10/2024 | N | EXP | 365 | 10/06/2023 | 10/05/2023 | 0 | 0 | 0 |  |  | 11/29/2023 | Connected |  | Y
National Grid | GARDNER | 668860 | 01440 | 10 | Solar | 05_14_74L3 | 01/30/2025 | 03/28/2025 | 6 | 1 | 5 | 03/31/2025 | 03/31/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FALL RIVER | 188838 | 02721 | 1560 | Solar | 05_01_216W6 | 07/16/2018 | 07/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2018 | 07/20/2018 | 2 | 2 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 455849 | 01752 | 299.7 | Solar | 05_01_26W2 | 05/05/2023 |  | 120 | 112 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 187735 | 01904 | 466.6 | Solar | 05_01_412L5 | 06/28/2018 | 06/28/2018 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2018 | 08/14/2018 | 12 | 2 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NAHANT | 692073 | 01908 | 10 | Solar | 05_01_602W2 | 06/02/2025 | 06/16/2025 | 2 | 0 | 2 | 07/09/2025 | 07/09/2025 | 20 | 9 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | HAVERHILL | 692739 | 01832 | 20 | Solar | 05_05_115W52 | 05/19/2025 | 05/21/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 52 | 43 | 9 | 11/04/2025 |  | 101 | 84 | 17 |  |  | 0 | 0 | 0 |  | 101 | 84 | 17 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | Y
National Grid | ANDOVER | 672840 | 01810 | 3.8 | Solar | 05_05_311W6 | 02/19/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | METHUEN | 721288 | 01844 | 7.6 | Solar | 05_12_29W1 | 09/23/2025 | 10/21/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BOLTON | 422671 | 01740 | 15.2 | Solar | 05_12_79J2 | 04/07/2022 | 04/08/2022 | 1 | 0 | 1 | 04/11/2022 | 04/11/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2022 | 04/07/2022 | 6/6/2024 | Y | EXP | 365 | 05/18/2023 | 06/07/2023 | 21 | 0 | 21 |  |  | 7/10/2023 | Connected |  | N
National Grid | AUBURN | 652375 | 01501 | 5.76 | Solar | 05_14_43L2 | 12/04/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/04/2024 | 2/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | DUDLEY | 555740 | 01571 | 10 | Solar | 05_14_59L6 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 21 | 0 | 21 | 01/31/2024 | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 4/2/2025 | N | EXP | 365 | 05/04/2024 | 01/30/2025 | 272 | 0 | 272 |  |  | 3/6/2025 | Connected |  | N
National Grid | GARDNER | 692028 | 01440 | 7.6 | Solar | 05_14_74L3 | 05/26/2025 | 06/16/2025 | 2 | 0 | 2 | 07/14/2025 | 07/14/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FALL RIVER | 196197 | 02720 | 15.2 | Solar | 05_01_216W6 | 09/25/2018 | 10/04/2018 | 12 | 11 | 1 | 10/11/2018 | 10/11/2018 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  | 12/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2019 | Connected |  | N
National Grid | MARLBOROUGH | 513820 | 01752 | 0 | Other | 05_01_26W2 | 07/11/2023 | 08/25/2023 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 11/28/2023 | 62 | 43 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 201618 | 01905 | 10 | Solar | 05_01_412L5 | 11/19/2018 | 01/03/2019 | 3 | 0 | 3 | 01/04/2019 | 01/04/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 | 11/19/2018 | 1/7/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2021 | Connected |  | N
National Grid | NAHANT | 693377 | 01908 | 11.4 | Solar | 05_01_602W2 | 05/21/2025 | 05/28/2025 | 4 | 0 | 4 | 05/29/2025 | 05/29/2025 | 141 | 131 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 711421 | 01832 | 11.4 | Solar | 05_05_115W52 | 09/09/2025 | 10/01/2025 | 15 | 9 | 6 | 10/02/2025 | 10/02/2025 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  | 1/28/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 678199 | 01810 | 13.36 | Solar | 05_05_311W6 | 03/14/2025 | 04/10/2025 | 1 | 0 | 1 | 04/17/2025 | 04/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 744859 | 01844 | 3.8 | Solar | 05_12_29W1 | 01/15/2026 | 01/20/2026 | 8 | 4 | 4 | 02/05/2026 | 02/05/2026 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2026 |  | 3/16/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BOLTON | 538674 | 01740 | 15.2 | Solar | 05_12_79J2 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 656096 | 01501 | 3.8 | Solar | 05_14_43L2 | 11/21/2024 | 12/04/2024 | 4 | 0 | 4 | 12/05/2024 | 12/05/2024 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/21/2024 | 3/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | WEBSTER | 554641 | 01570 | 15 | Solar | 05_14_59L6 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 11/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | GARDNER | 709517 | 01440 | 5.76 | Solar | 05_14_74L3 | 08/04/2025 | 08/28/2025 | 2 | 0 | 2 | 08/29/2025 | 08/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTPORT | 212493 | 02790 | 0 | Solar | 05_01_216W6 | 03/05/2019 | 03/12/2019 | 4 | 0 | 4 | 03/13/2019 | 03/13/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 | 03/05/2019 | 3/6/2020 | Y | EXP | 365 | 09/05/2019 | 09/11/2019 | 6 | 0 | 6 |  |  | 2/4/2020 | Connected |  | N
National Grid | MARLBOROUGH | 522113 | 01752 | 15.08 | Solar | 05_01_26W2 | 11/29/2023 | 05/05/2023 | 7 | 6 | 1 | 12/08/2023 | 12/08/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2024 |  | 1/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2024 | Connected |  | N
National Grid | LYNN | 203677 | 01905 | 9.57 | Solar | 05_01_412L5 | 12/31/2018 | 01/11/2019 | 7 | 1 | 6 | 01/18/2019 | 01/18/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  | 2/12/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2019 | Connected |  | N
National Grid | NAHANT | 693699 | 01908 | 3.8 | Solar | 05_01_602W2 | 05/27/2025 | 07/03/2025 | 2 | 0 | 2 | 07/07/2025 | 07/07/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | METHUEN | 714265 | 01844 | 2000 | Solar | 05_05_115W52 | 09/09/2025 | 10/02/2025 | 17 | 12 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2025 | 10/17/2025 | 9 | 4 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | ANDOVER | 724550 | 01810 | 20.14 | Solar | 05_05_311W6 | 10/07/2025 | 10/20/2025 | 7 | 3 | 4 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2026 | Connected |  | N
National Grid | METHUEN | 747398 | 01844 | 7.6 | Solar | 05_12_29W1 | 01/26/2026 | 02/02/2026 | 10 | 7 | 3 | 02/20/2026 | 02/20/2026 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HARVARD | 612259 | 01451 | 15.2 | Solar | 05_12_79J2 | 05/20/2024 | 05/23/2024 | 4 | 3 | 1 | 05/24/2024 | 05/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | AUBURN | 660296 | 01501 | 15.2 | Solar | 05_14_43L2 | 12/19/2024 | 01/08/2025 | 13 | 9 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/19/2024 | 3/21/2026 | Y | EXP | 365 | 07/02/2025 | 07/24/2025 | 22 | 0 | 22 |  |  | 8/21/2025 | Connected |  | N
National Grid | DUDLEY | 568051 | 01571 | 0 | Solar | 05_14_59L6 | 11/01/2023 | 11/02/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 32 | 11 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 1/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2024 | Connected |  | N
National Grid | HUBBARDSTON | 738712 | 01452 | 10 | Solar | 05_14_74L3 | 12/08/2025 | 12/10/2025 | 3 | 0 | 3 | 01/02/2026 | 01/02/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 | 12/08/2025 | 2/12/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WESTPORT | 243391 | 02790 | 0 | Solar | 05_01_216W6 | 07/17/2019 | 07/18/2019 | 0 | 0 | 0 | 07/19/2019 | 07/19/2019 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2019 | 07/17/2019 | 3/4/2020 | Y | EXP | 211 | 11/14/2019 | 11/26/2019 | 12 | 0 | 12 |  |  | 1/28/2020 | Connected |  | N
National Grid | MARLBOROUGH | 524124 | 01752 | 8.41 | Solar | 05_01_26W2 | 05/16/2023 | 05/30/2023 | 9 | 8 | 1 | 05/31/2023 | 05/31/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 208138 | 01904 | 10 | Solar | 05_01_412L5 | 02/19/2019 | 02/19/2019 | 0 | 0 | 0 | 02/20/2019 | 02/20/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/19/2019 | 11/5/2019 | Y | EXP | 257 | 09/17/2019 | 09/18/2019 | 1 | 0 | 1 |  |  | 9/23/2019 | Connected |  | N
National Grid | NAHANT | 318674 | 01908 | 0 | Other | 05_01_602W3 | 04/06/2021 | 04/30/2021 | 17 | 8 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 731372 | 01844 | 11.4 | Solar | 05_05_115W52 | 11/06/2025 | 11/14/2025 | 2 | 0 | 2 | 01/15/2026 | 01/15/2026 | 51 | 36 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 742327 | 01810 | 5.32 | Solar | 05_05_311W6 | 12/26/2025 | 12/30/2025 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 176207 | 01844 | 11.4 | Solar | 05_12_29W1 | 04/24/2015 | 04/24/2015 | 2 | 2 | 0 | 04/30/2015 | 04/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 | 04/24/2015 | 12/31/2016 | Y | EXP | 597 | 08/29/2016 | 09/30/2016 | 23 | 0 | 23 | 9/12/2016 | 9/12/2016 | 9/12/2016 | Connected |  | N
National Grid | BOLTON | 710901 | 01740 | 9.6 | Solar | 05_12_79J2 | 08/20/2025 | 09/15/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2026 | Connected |  | N
National Grid | AUBURN | 670504 | 01501 | 7.54 | Solar | 05_14_43L2 | 02/06/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 594025 | 01571 | 10 | Solar | 05_14_59L6 | 03/11/2024 | 03/14/2024 | 3 | 0 | 3 | 03/15/2024 | 03/15/2024 | 23 | 20 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 751572 | 01473 | 7.6 | Solar | 05_14_74L3 | 02/17/2026 | 02/23/2026 | 3 | 0 | 3 | 03/11/2026 | 03/11/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTPORT | 248297 | 02790 | 0 | Solar | 05_01_216W6 | 08/12/2019 | 08/21/2019 | 7 | 7 | 0 | 08/22/2019 | 08/22/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2019 |  | 11/22/2019 | N | EXP | 74 |  |  | 0 | 0 | 0 |  |  | 10/22/2019 | Connected |  | N
National Grid | MARLBOROUGH | 557228 | 01752 | 12.18 | Solar | 05_01_26W2 | 09/21/2023 | 09/21/2023 | 0 | 0 | 0 | 09/22/2023 | 09/22/2023 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 11/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2024 | Connected |  | N
National Grid | LYNN | 207488 | 01904 | 10 | Solar | 05_01_412L5 | 01/30/2019 | 02/04/2019 | 3 | 3 | 0 | 02/05/2019 | 02/05/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2019 | 01/30/2019 | 11/25/2019 | Y | EXP | 292 | 05/25/2019 | 07/12/2019 | 48 | 0 | 48 |  |  | 9/10/2019 | Connected |  | N
National Grid | NAHANT | 487745 | 01908 | 2000 | Solar | 05_01_602W3 | 01/27/2023 | 02/22/2023 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2023 | 03/23/2023 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HAVERHILL | 732789 | 01832 | 3.8 | Solar | 05_05_115W52 | 11/10/2025 | 12/10/2025 | 2 | 0 | 2 | 03/18/2026 | 03/18/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 571788 | 01810 | 0 | Other | 05_05_312W1 | 01/11/2024 | 04/22/2025 | 317 | 307 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/23/2025 | 05/20/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LAWRENCE | 176763 | 01841 | 6 | Solar | 05_12_29W1 | 02/24/2016 | 02/24/2016 | 1 | 1 | 0 | 02/26/2016 | 02/26/2016 | 248 | 0 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 |  | 5/1/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 4/28/2016 | 4/28/2016 |  | Withdrawn |  | Y
National Grid | BOLTON | 639120 | 01740 | 7.36 | Solar | 05_12_7J1 | 09/10/2024 | 10/02/2024 | 4 | 0 | 4 | 10/03/2024 | 10/03/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | AUBURN | 683783 | 01501 | 0 | Battery Add-On | 05_14_43L2 | 04/08/2025 | 04/21/2025 | 8 | 4 | 4 | 04/22/2025 | 04/22/2025 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2025 | Connected |  | N
National Grid | DUDLEY | 607739 | 01571 |  | Battery Add-On | 05_14_59L6 | 04/30/2024 | 05/03/2024 | 3 | 0 | 3 | 05/06/2024 | 05/06/2024 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 5/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N
National Grid | WESTMINSTER | 174308 | 01473 | 190 | Solar | 05_14_74L3 | 12/09/2011 | 12/09/2011 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2012 | 12/09/2011 | 2/1/2012 | Y | EXP | 41 | 05/08/2012 | 05/09/2012 | 1 | 0 | 1 | 5/11/2012 | 5/11/2012 | 5/23/2012 | Connected |  | N
National Grid | WESTPORT | 251196 | 02790 | 7.6 | Solar | 05_01_216W6 | 08/28/2019 | 10/14/2019 | 3 | 0 | 3 | 10/15/2019 | 10/15/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 | 08/28/2019 | 10/8/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2021 | Connected |  | N
National Grid | WESTBOROUGH | 569868 | 01581 | 10 | Solar | 05_01_26W2 | 12/06/2023 | 12/14/2023 | 6 | 3 | 3 | 12/15/2023 | 12/15/2023 | 41 | 19 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 315053 | 01905 | 50 | Solar | 05_01_412L5 | 09/25/2020 | 10/06/2020 | 6 | 1 | 5 | 10/07/2020 | 10/07/2020 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2021 | Connected |  | N
National Grid | REVERE | 661234 | 02151 | 5000 | Solar | 05_01_602W3 | 04/28/2025 | 11/21/2025 | 142 | 132 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 01/06/2026 | 29 | 10 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HAVERHILL | 741857 | 01832 | 11.4 | Solar | 05_05_115W52 | 12/22/2025 | 12/29/2025 | 4 | 0 | 4 | 12/30/2025 | 12/30/2025 | 43 | 28 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2026 |  | 3/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 660928 | 01810 | 5.76 | Solar | 05_05_312W1 | 12/16/2024 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 12/16/2024 | 5/18/2026 | Y | EXP | 425 | 05/29/2025 | 05/28/2025 | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 177003 | 01844 | 6.6 | Solar | 05_12_29W1 | 10/07/2016 | 10/07/2016 | 1 | 1 | 0 | 10/11/2016 | 10/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2016 | 10/07/2016 | 3/30/2018 | Y | EXP | 529 | 10/09/2017 | 10/11/2017 | 1 | 0 | 1 | 2/12/2018 | 2/12/2018 | 3/23/2018 | Connected |  | N
National Grid | CLINTON | 743642 | 01510 | 3.8 | Solar | 05_12_7J2 | 01/06/2026 | 01/08/2026 | 1 | 0 | 1 | 01/22/2026 | 01/22/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AUBURN | 714209 | 01501 | 15.2 | Solar | 05_14_43L2 | 08/24/2025 | 09/17/2025 | 16 | 15 | 1 | 09/18/2025 | 09/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  | 10/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2026 | Connected |  | N
National Grid | WEBSTER | 652980 | 01570 | 5.76 | Solar | 05_14_59L6 | 11/14/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | WESTMINSTER | 176470 | 01473 | 252 | Solar | 05_14_74L3 | 03/20/2016 | 03/20/2016 | 13 | 13 | 0 | 04/07/2016 | 04/07/2016 | 383 | 0 | 383 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2016 |  | 12/31/2017 | N | EXP | 611 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 263665 | 02790 | 0 | Solar | 05_01_216W6 | 11/04/2019 | 11/08/2019 | 3 | 0 | 3 | 11/12/2019 | 11/12/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2019 | 11/04/2019 | 11/4/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2020 | Connected |  | N
National Grid | WESTBOROUGH | 572356 | 01581 | 7.6 | Solar | 05_01_26W2 | 01/09/2024 | 01/24/2024 | 11 | 7 | 4 | 01/25/2024 | 01/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/09/2024 | 4/17/2025 | Y | EXP | 365 | 05/22/2024 | 09/07/2024 | 109 | 0 | 109 |  |  | 9/17/2024 | Connected |  | N
National Grid | LYNN | 329818 | 01904 | 15.2 | Solar | 05_01_412L5 | 12/05/2020 | 12/08/2020 | 1 | 0 | 1 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  | 4/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2022 | Connected |  | N
National Grid | REVERE | 725531 | 02151 | 49.875 | Solar | 05_01_602W3 | 10/22/2025 | 12/30/2025 | 46 | 36 | 10 | 12/31/2025 | 12/31/2025 | 62 | 46 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAVERHILL | 748790 | 01832 | 11.4 | Solar | 05_05_115W52 | 02/03/2026 | 02/04/2026 | 4 | 0 | 4 | 02/24/2026 | 02/24/2026 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ANDOVER | 174200 | 01810 | 260 | Solar | 05_05_312W1 | 03/27/2012 | 03/27/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 03/27/2012 | 10/1/2012 | Y | EXP | 72 | 02/06/2013 | 03/04/2013 | 13 | 0 | 13 | 3/21/2013 | 3/21/2013 | 4/1/2013 | Connected |  | N
National Grid | METHUEN | 177253 | 01844 | 3.8 | Solar | 05_12_29W1 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/17/2016 | 06/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 | 06/14/2016 | 6/20/2017 | Y | EXP | 358 |  |  | 0 | 0 | 0 | 10/26/2016 | 10/26/2016 | 10/26/2016 | Connected |  | N
National Grid | BOLTON | 234799 | 01740 | 10 | Solar | 05_12_7J2 | 07/19/2019 | 07/30/2019 | 6 | 0 | 6 | 07/31/2019 | 07/31/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2019 |  | 12/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2020 | Connected |  | N
National Grid | AUBURN | 724254 | 01501 | 11.4 | Solar | 05_14_43L2 | 10/06/2025 | 12/18/2025 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 679799 | 01571 | 3.8 | Solar | 05_14_59L6 | 03/21/2025 | 04/03/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 176680 | 01473 | 6 | Solar | 05_14_74L3 | 01/04/2016 | 01/04/2016 | 0 | 0 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2016 |  | 1/11/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 4/18/2016 | 4/18/2016 | 5/24/2016 | Connected |  | N
National Grid | WESTPORT | 289076 | 02790 | 7.68 | Solar | 05_01_216W6 | 04/23/2020 | 04/27/2020 | 1 | 0 | 1 | 04/28/2020 | 04/28/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2020 | 04/23/2020 | 8/18/2022 | Y | EXP | 759 | 12/02/2020 | 12/11/2020 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 587534 | 01581 | 200 | Solar | 05_01_26W2 | 03/14/2024 |  | 56 | 50 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 332213 | 01904 | 7.6 | Solar | 05_01_412L5 | 01/12/2021 | 01/15/2021 | 2 | 0 | 2 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/12/2021 | 3/8/2022 | Y | EXP | 365 | 09/23/2021 | 01/19/2022 | 119 | 4 | 115 |  |  | 2/5/2022 | Connected |  | N
National Grid | REVERE | 731396 | 02151 | 9.5 | Solar | 05_01_602W3 | 11/06/2025 | 11/10/2025 | 2 | 0 | 2 | 11/12/2025 | 11/12/2025 | 29 | 8 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 | 11/06/2025 | 1/30/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | HAVERHILL | 748169 | 01832 | 11.4 | Solar | 05_05_115W52 | 01/29/2026 | 02/03/2026 | 3 | 0 | 3 | 02/04/2026 | 02/04/2026 | 38 | 24 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ANDOVER | 174427 | 01810 | 600 | Solar | 05_05_312W1 | 11/21/2011 | 11/21/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2012 | 11/21/2011 | 10/31/2012 | Y | STD | 98 | 08/21/2012 | 10/11/2012 | 35 | 0 | 35 | 10/9/2012 | 10/9/2012 | 10/15/2012 | Connected |  | N
National Grid | METHUEN | 204587 | 01844 | 3.8 | Solar | 05_12_29W1 | 01/07/2019 | 01/18/2019 | 8 | 0 | 8 | 01/22/2019 | 01/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 01/07/2019 | 9/16/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2021 | Connected |  | N
National Grid | HARVARD | 553820 | 01451 | 8.725 | Solar | 05_12_7J2 | 11/22/2023 | 12/29/2023 | 25 | 20 | 5 | 01/02/2024 | 01/02/2024 | 179 | 25 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 704923 | 01501 | 200 | Solar | 05_14_43L3 | 07/15/2025 | 09/10/2025 | 40 | 31 | 9 | 09/11/2025 | 09/11/2025 | 52 | 33 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEBSTER | 712505 | 01570 | 6.08 | Solar | 05_14_59L6 | 08/18/2025 | 08/20/2025 | 2 | 0 | 2 | 08/21/2025 | 08/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  | 9/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | WESTMINSTER | 176823 | 01473 | 6 | Solar | 05_14_74L3 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 1/20/2017 | N | EXP | 350 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 8/25/2016 | Connected |  | N
National Grid | WESTPORT | 293500 | 02790 | 200 | Solar | 05_01_216W6 | 05/27/2020 | 06/16/2020 | 14 | 12 | 2 | 06/17/2020 | 06/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 588475 | 01581 | 125 | Solar | 05_01_26W2 | 04/17/2024 |  | 94 | 86 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 346007 | 01904 | 7.6 | Solar | 05_01_412L5 | 03/19/2021 | 03/22/2021 | 0 | 0 | 0 | 03/23/2021 | 03/23/2021 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/21/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 174307 | 02151 | 500 | Solar | 05_01_602W3 | 01/10/2012 | 01/10/2012 | 23 | 0 | 23 | 02/13/2012 | 02/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2012 |  | 7/1/2012 | N | EXP | 8 |  |  | 0 | 0 | 0 | 12/5/2012 | 12/5/2012 | 12/6/2012 | Connected |  | N
National Grid | HAVERHILL | 748001 | 01835 | 15.2 | Solar | 05_05_115W52 | 01/28/2026 | 02/02/2026 | 3 | 0 | 3 | 02/03/2026 | 02/03/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  | 3/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 174993 | 01810 | 100 | Solar | 05_05_312W1 | 03/11/2013 | 03/11/2013 | 4 | 0 | 4 | 03/19/2013 | 03/19/2013 | 978 | 0 | 978 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2013 |  | 12/31/2016 | N | EXP | 1341 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 205264 | 01844 | 7.6 | Solar | 05_12_29W1 | 02/04/2019 | 02/07/2019 | 3 | 3 | 0 | 02/08/2019 | 02/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 583707 | 01451 | 7.6 | Solar | 05_12_7J2 | 01/29/2024 | 02/02/2024 | 5 | 4 | 1 | 02/05/2024 | 02/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/29/2024 | 3/17/2025 | Y | EXP | 365 | 05/09/2024 | 05/20/2024 | 12 | 0 | 12 |  |  | 8/20/2024 | Connected |  | N
National Grid | AUBURN | 750989 | 01501 | 15.96 | Solar | 05_14_43L3 | 02/12/2026 | 02/18/2026 | 3 | 0 | 3 | 02/19/2026 | 02/19/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2026 |  | 3/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DUDLEY | 730098 | 01571 | 10 | Solar | 05_14_59L6 | 10/29/2025 | 10/30/2025 | 4 | 0 | 4 | 12/10/2025 | 12/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 176884 | 01473 | 7.6 | Solar | 05_14_74L3 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 |  | 5/10/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 295570 | 02790 | 0 | Solar | 05_01_216W6 | 10/26/2020 | 10/27/2020 | 0 | 0 | 0 | 10/28/2020 | 10/28/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 | 10/26/2020 | 10/25/2022 | Y | EXP | 365 | 04/07/2021 | 04/28/2021 | 21 | 0 | 21 |  |  | 7/27/2022 | Connected |  | N
National Grid | WESTBOROUGH | 608555 | 01581 | 10 | Solar | 05_01_26W2 | 05/03/2024 | 05/08/2024 | 1 | 0 | 1 | 05/09/2024 | 05/09/2024 | 98 | 75 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 442567 | 01904 | 15.2 | Solar | 05_01_412L5 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 |  | 8/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2022 | Connected |  | N
National Grid | REVERE | 175778 | 02151 | 480 | Solar | 05_01_602W3 | 08/20/2014 | 08/20/2014 | 7 | 0 | 7 | 09/02/2014 | 09/02/2014 | 0 | 0 | 0 | 10/21/2014 | 11/26/2014 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 11/26/2014 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 12/31/2014 | 08/20/2014 | 9/1/2015 | Y | EXP | 244 | 09/18/2015 | 11/03/2015 | 31 | 0 | 31 | 10/23/2015 | 10/23/2015 | 11/16/2015 | Connected |  | N
National Grid | HAVERHILL | 175769 | 01835 | 4800 | Solar | 05_05_115W52 | 06/10/2014 | 06/10/2014 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2014 | 07/21/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 |  | 12/31/2016 | N | STD | 614 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 177043 | 01810 | 792 | Solar | 05_05_312W1 | 10/17/2016 | 10/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 02/07/2017 | 69 | 56 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2018 | 10/17/2016 | 3/28/2022 | Y | STD | 1002 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 207594 | 01844 | 6 | Solar | 05_12_29W1 | 02/05/2019 | 02/13/2019 | 6 | 6 | 0 | 02/14/2019 | 02/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/05/2019 | 2/5/2020 | Y | EXP | 349 | 09/25/2019 | 11/19/2019 | 55 | 0 | 55 |  |  | 12/3/2019 | Connected |  | N
National Grid | BOLTON | 638214 | 01740 | 19.76 | Solar | 05_12_7J2 | 09/06/2024 | 09/11/2024 | 3 | 1 | 2 | 09/12/2024 | 09/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2025 | Connected |  | N
National Grid | AUBURN | 176543 | 01501 | 476 | Solar | 05_14_43L3 | 03/30/2016 | 03/30/2016 | 4 | 4 | 0 | 04/07/2016 | 04/07/2016 | 457 | 0 | 457 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 10/31/2017 | N | EXP | 546 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 607813 | 01571 | 175 | Solar | 05_14_5J11 | 05/01/2024 | 07/25/2024 | 58 | 52 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2024 | 08/13/2024 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTMINSTER | 176943 | 01473 | 5.75 | Solar | 05_14_74L3 | 12/12/2016 | 12/12/2016 | 1 | 1 | 0 | 12/21/2016 | 12/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 | 12/12/2016 | 12/25/2017 | Y | EXP | 368 | 06/20/2017 | 07/05/2017 | 10 | 0 | 10 | 9/21/2017 | 9/21/2017 | 9/21/2017 | Connected |  | N
National Grid | WESTPORT | 298017 | 02790 | 10 | Solar | 05_01_216W6 | 06/24/2020 | 06/29/2020 | 2 | 0 | 2 | 06/30/2020 | 06/30/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2020 | Connected |  | N
National Grid | WESTBOROUGH | 658756 | 01581 | 7.6 | Solar | 05_01_26W2 | 12/05/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/05/2024 | 2/13/2026 | Y | EXP | 365 | 05/22/2025 | 05/21/2025 | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | LYNN | 477663 | 01905 | 15.2 | Solar | 05_01_412L5 | 01/12/2023 | 01/17/2023 | 2 | 0 | 2 | 01/18/2023 | 01/18/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 3/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2023 | Connected |  | N
National Grid | REVERE | 176816 | 02151 | 2200 | Solar | 05_01_602W3 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/28/2015 | 31 | 0 | 31 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/11/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 175819 | 01835 | 2000 | Solar | 05_05_115W52 | 07/30/2015 | 07/30/2015 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2015 | 09/09/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 07/30/2015 | 7/15/2017 | Y | STD | 333 | 03/01/2017 | 06/23/2017 | 80 | 0 | 80 | 6/27/2017 | 6/27/2017 | 7/31/2017 | Connected |  | N
National Grid | AMESBURY | 177570 | 01913 | 15.2 | Solar | 05_05_312W1 | 09/15/2017 | 09/15/2017 | 8 | 8 | 0 | 09/27/2017 | 09/27/2017 | 124 | 0 | 124 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/20/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 252203 | 01841 | 11.4 | Solar | 05_12_29W1 | 10/01/2019 | 11/06/2019 | 25 | 25 | 0 | 11/07/2019 | 11/07/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 | 10/01/2019 | 12/7/2020 | Y | EXP | 365 | 08/05/2020 | 11/16/2020 | 104 | 5 | 99 |  |  | 11/24/2020 | Connected |  | N
National Grid | HARVARD | 638789 | 01451 | 3.8 | Solar | 05_12_7J2 | 09/09/2024 | 12/02/2024 | 3 | 0 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | AUBURN | 177341 | 01501 | 750 | Solar | 05_14_43L3 | 11/18/2016 | 11/18/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2016 | 12/28/2016 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/26/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 174139 | 01571 | 22.8 | Solar | 05_14_5J11 | 04/10/2012 | 04/10/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2012 |  | 6/1/2012 | N | EXP | 60 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 11/19/2012 | Connected |  | N
National Grid | WESTMINSTER | 176936 | 01473 | 7.6 | Solar | 05_14_74L3 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 |  | 2/6/2017 | N | EXP | 336 |  |  | 0 | 0 | 0 | 8/4/2016 | 8/4/2016 | 8/8/2016 | Connected |  | N
National Grid | WESTPORT | 311915 | 02790 | 14.5 | Solar | 05_01_216W6 | 09/10/2020 | 09/14/2020 | 1 | 0 | 1 | 09/15/2020 | 09/15/2020 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2020 |  | 9/1/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 696813 | 01581 | 15.2 | Solar | 05_01_26W2 | 06/10/2025 | 06/17/2025 | 5 | 0 | 5 | 06/18/2025 | 06/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | LYNN | 483367 | 01904 | 7.6 | Solar | 05_01_412L5 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 89 | 65 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2023 | Connected |  | Y
National Grid | REVERE | 176815 | 02151 | 2200 | Solar | 05_01_602W3 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/28/2015 | 31 | 0 | 31 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/11/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176227 | 01835 | 10 | Solar | 05_05_115W52 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/01/2015 | 9/12/2016 | Y | EXP | 355 | 01/21/2016 | 01/28/2016 | 5 | 0 | 5 | 9/23/2015 | 9/23/2015 | 5/5/2016 | Connected |  | N
National Grid | AMESBURY | 191397 | 01913 | 7.6 | Solar | 05_05_312W1 | 07/20/2018 | 09/05/2018 | 3 | 3 | 0 | 09/06/2018 | 09/06/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 307291 | 01844 | 6.72 | Solar | 05_12_29W1 | 10/20/2020 | 10/21/2020 | 0 | 0 | 0 | 10/22/2020 | 10/22/2020 | 33 | 15 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 10/20/2020 | 9/25/2022 | Y | EXP | 365 | 09/09/2021 | 09/23/2021 | 15 | 0 | 15 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 643463 | 01740 | 21.4 | Solar | 05_12_7J2 | 10/22/2024 | 10/24/2024 | 2 | 0 | 2 | 10/25/2024 | 10/25/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/22/2024 | 12/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | AUBURN | 177479 | 01501 | 75.6 | Solar | 05_14_43L3 | 07/06/2016 | 07/06/2016 | 35 | 35 | 0 | 08/26/2016 | 08/26/2016 | 244 | 55 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2016 |  | 8/31/2017 | N | EXP | 273 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 176451 | 01571 | 52.8 | Solar | 05_14_5J11 | 12/08/2015 | 12/08/2015 | 7 | 7 | 0 | 12/17/2015 | 12/17/2015 | 122 | 0 | 122 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/13/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 177053 | 01473 | 7.6 | Solar | 05_14_74L3 | 01/11/2017 | 01/11/2017 | 4 | 3 | 1 | 01/18/2017 | 01/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2017 |  | 1/16/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 | 5/30/2017 | 5/30/2017 | 5/30/2017 | Connected |  | N
National Grid | WESTPORT | 336027 | 02790 | 200 | Solar | 05_01_216W6 | 01/11/2021 | 12/07/2021 | 9 | 1 | 8 | 02/03/2021 | 02/03/2021 | 74 | 51 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2021 |  | 7/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2022 | Connected |  | N
National Grid | WESTBOROUGH | 744507 | 01581 | 5.76 | Solar | 05_01_26W2 | 01/13/2026 | 01/20/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2026 | Connected |  | N
National Grid | LYNN | 489902 | 01905 | 15.2 | Solar | 05_01_412L5 | 01/05/2023 | 01/06/2023 | 1 | 0 | 1 | 01/09/2023 | 01/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2023 |  | 2/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N
National Grid | REVERE | 176813 | 02151 | 2000 | Solar | 05_01_602W3 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2015 | 12/07/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176895 | 01832 | 1500 | Solar | 05_05_115W52 | 01/22/2016 | 01/22/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2016 | 03/18/2016 | 33 | 0 | 33 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 01/22/2016 | 12/6/2018 | Y | STD | 842 |  |  | 0 | 0 | 0 |  |  | 12/3/2018 | Connected |  | N
National Grid | AMESBURY | 196685 | 01913 | 8.7 | Solar | 05_05_312W1 | 09/21/2018 | 10/24/2018 | 3 | 3 | 0 | 10/25/2018 | 10/25/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2018 | 09/21/2018 | 6/10/2019 | Y | EXP | 222 | 03/16/2019 | 03/15/2019 | 0 | 0 | 0 |  |  | 4/19/2019 | Connected |  | N
National Grid | METHUEN | 311321 | 01844 | 6.48 | Solar | 05_12_29W1 | 10/12/2020 | 10/14/2020 | 1 | 0 | 1 | 10/15/2020 | 10/15/2020 | 60 | 41 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2021 | Connected |  | N
National Grid | HARVARD | 682939 | 01451 | 3.8 | Solar | 05_12_7J2 | 04/04/2025 | 05/05/2025 | 2 | 0 | 2 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/04/2025 | 6/12/2026 | Y | EXP | 365 | 09/11/2025 | 12/01/2025 | 82 | 0 | 82 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 201984 | 01501 | 3.8 | Solar | 05_14_43L3 | 11/26/2018 | 12/20/2018 | 4 | 0 | 4 | 12/21/2018 | 12/21/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 177462 | 01571 | 43.2 | Solar | 05_14_5J11 | 12/12/2016 | 12/12/2016 | 7 | 7 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 |  | 12/17/2017 | N | EXP | 360 |  |  | 0 | 0 | 0 | 8/23/2017 | 8/23/2017 | 8/23/2017 | Connected |  | N
National Grid | WESTMINSTER | 178183 | 01473 | 7.6 | Solar | 05_14_74L3 | 04/13/2018 | 04/13/2018 | 21 | 21 | 0 | 05/02/2018 | 05/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/21/2019 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTPORT | 356319 | 02790 | 9.28 | Solar | 05_01_216W6 | 05/05/2021 | 05/11/2021 | 4 | 4 | 0 | 05/12/2021 | 05/12/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 5/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2021 | Connected |  | N
National Grid | WESTBOROUGH | 690816 | 01581 | 499 | Other | 05_01_26W3 | 07/11/2025 | 08/29/2025 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/02/2025 | 10/15/2025 | 31 | 15 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LYNN | 517520 | 01904 | 10 | Solar | 05_01_412L5 | 08/22/2023 | 04/15/2023 | 5 | 4 | 1 | 08/29/2023 | 08/29/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2023 | 08/22/2023 | 10/23/2024 | Y | EXP | 365 | 03/13/2024 | 03/22/2024 | 10 | 0 | 10 |  |  | 3/25/2024 | Connected |  | N
National Grid | REVERE | 176848 | 02151 | 480 | Solar | 05_01_602W3 | 11/09/2015 | 11/09/2015 | 1 | 1 | 0 | 11/10/2015 | 11/10/2015 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/14/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176894 | 01835 | 4000.002 | Solar | 05_05_115W52 | 01/22/2016 | 01/22/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2016 | 03/18/2016 | 33 | 0 | 33 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 01/22/2016 | 12/5/2018 | Y | STD | 841 | 05/05/2018 | 10/03/2018 | 151 | 0 | 151 |  |  | 11/30/2018 | Connected |  | N
National Grid | AMESBURY | 200805 | 01913 | 7.6 | Solar | 05_05_312W1 | 11/08/2018 | 12/19/2018 | 6 | 0 | 6 | 12/20/2018 | 12/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 | 11/08/2018 | 11/8/2020 | Y | EXP | 365 | 03/04/2020 | 03/25/2020 | 21 | 0 | 21 |  |  | 7/16/2020 | Connected |  | N
National Grid | METHUEN | 313176 | 01844 | 7.6 | Solar | 05_12_29W1 | 11/02/2020 | 11/03/2020 | 0 | 0 | 0 | 11/04/2020 | 11/04/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 | 11/02/2020 | 11/2/2021 | Y | EXP | 365 | 03/25/2021 | 08/16/2021 | 144 | 0 | 144 |  |  | 9/7/2021 | Connected |  | N
National Grid | BOLTON | 178628 | 01740 | 3.8 | Solar | 05_12_7J3 | 03/15/2018 | 03/15/2018 | 13 | 13 | 0 | 04/05/2018 | 04/05/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/21/2019 | N | EXP | 314 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 322749 | 01501 | 7.6 | Solar | 05_14_43L3 | 11/12/2020 | 11/17/2020 | 2 | 0 | 2 | 11/18/2020 | 11/18/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2020 | 11/12/2020 |  | Y | EXP | 365 | 04/14/2021 | 04/26/2021 | 12 | 0 | 12 |  |  | 6/29/2021 | Connected |  | N
National Grid | DUDLEY | 195497 | 01571 | 7.6 | Solar | 05_14_5J11 | 09/10/2018 | 10/30/2018 | 7 | 0 | 7 | 10/31/2018 | 10/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 | 09/10/2018 | 10/30/2020 | Y | EXP | 400 | 02/14/2020 | 02/18/2020 | 4 | 0 | 4 |  |  | 5/4/2020 | Connected |  | N
National Grid | WESTMINSTER | 193240 | 01473 | 6 | Solar | 05_14_74L3 | 08/10/2018 | 11/30/2018 | 42 | 34 | 8 | 12/03/2018 | 12/03/2018 | 21 | 10 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2019 |  | 8/10/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 367483 | 02790 | 0 | Solar | 05_01_216W6 | 07/02/2021 | 07/06/2021 | 1 | 0 | 1 | 07/07/2021 | 07/07/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2021 |  | 9/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2022 | Connected |  | N
National Grid | WESTBOROUGH | 704637 | 01581 | 480 | Solar | 05_01_26W3 | 10/29/2025 | 11/10/2025 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 12/10/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LYNN | 523805 | 01905 | 6.67 | Solar | 05_01_412L5 | 05/08/2023 | 05/12/2023 | 4 | 2 | 2 | 05/15/2023 | 05/15/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 05/08/2023 | 7/12/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2023 | Connected |  | N
National Grid | REVERE | 184587 | 02151 | 3000 | Solar | 05_01_602W3 | 06/04/2018 | 06/04/2018 | 11 | 0 | 11 |  |  | 29 | 0 | 29 |  |  | 0 | 0 | 0 | 06/20/2018 | 07/11/2018 | 29 | 0 | 29 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176902 | 01835 | 750 | Solar | 05_05_115W52 | 01/22/2016 | 01/22/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2016 | 03/18/2016 | 33 | 0 | 33 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 01/22/2016 | 12/5/2018 | Y | STD | 841 |  |  | 0 | 0 | 0 |  |  | 11/14/2018 | Connected |  | N
National Grid | AMESBURY | 200739 | 01913 | 3.8 | Solar | 05_05_312W1 | 11/08/2018 | 01/10/2019 | 26 | 20 | 6 | 01/11/2019 | 01/11/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 11/08/2018 | 5/19/2020 | Y | EXP | 488 | 01/14/2020 | 01/27/2020 | 13 | 0 | 13 |  |  | 2/6/2020 | Connected |  | N
National Grid | LAWRENCE | 362142 | 01841 | 7.6 | Solar | 05_12_29W1 | 07/01/2021 | 01/06/2022 | 6 | 0 | 6 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 | 07/01/2021 | 8/21/2024 | Y | EXP | 365 | 03/22/2022 | 08/18/2023 | 515 | 0 | 515 |  |  | 9/8/2023 | Connected |  | N
National Grid | HARVARD | 407783 | 01451 | 3.84 | Solar | 05_12_7J3 | 02/21/2022 | 02/22/2022 | 1 | 0 | 1 | 02/23/2022 | 02/23/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 342609 | 01501 | 5 | Solar | 05_14_43L3 | 03/04/2021 | 03/09/2021 | 2 | 0 | 2 | 03/10/2021 | 03/10/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 | 03/04/2021 | 10/5/2022 | Y | EXP | 365 | 09/11/2021 | 09/21/2021 | 6 | 0 | 6 |  |  | 9/29/2021 | Connected |  | N
National Grid | DUDLEY | 191148 | 01571 | 6.96 | Solar | 05_14_5J11 | 07/19/2018 | 07/31/2018 | 0 | 0 | 0 | 08/01/2018 | 08/01/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 7/31/2019 | N | EXP | 309 |  |  | 0 | 0 | 0 |  |  | 2/14/2019 | Connected |  | N
National Grid | WESTMINSTER | 221314 | 01473 | 7.6 | Solar | 05_14_74L3 | 04/19/2019 | 06/05/2019 | 0 | 0 | 0 | 06/06/2019 | 06/06/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2019 | 04/19/2019 | 7/16/2020 | Y | EXP | 365 | 03/04/2020 | 05/21/2020 | 78 | 0 | 78 |  |  | 6/5/2020 | Connected |  | N
National Grid | WESTPORT | 366741 | 02790 | 7.6 | Solar | 05_01_216W6 | 06/29/2021 | 06/30/2021 | 1 | 0 | 1 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2021 |  | 10/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2022 | Connected |  | N
National Grid | WESTBOROUGH | 757163 | 01581 | 11.5 | Solar | 05_01_26W3 | 03/17/2026 | 03/19/2026 | 2 | 0 | 2 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 535016 | 01905 | 15.2 | Solar | 05_01_412L5 | 06/19/2023 | 06/26/2023 | 5 | 2 | 3 | 06/27/2023 | 06/27/2023 | 75 | 61 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  | 1/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2024 | Connected |  | N
National Grid | REVERE | 189902 | 02151 | 950 | Solar | 05_01_602W3 | 07/25/2018 | 09/17/2018 | 101 | 12 | 89 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 12/19/2018 | 62 | 0 | 62 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176922 | 01835 | 996 | Solar | 05_05_115W52 | 11/12/2015 | 11/12/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 12/14/2015 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 11/12/2015 | 12/30/2017 | Y | STD | 522 | 04/14/2017 | 12/27/2017 | 170 | 0 | 170 | 12/29/2017 | 12/29/2017 | 12/30/2017 | Connected |  | N
National Grid | AMESBURY | 203444 | 01913 | 0 | Solar | 05_05_312W1 | 12/12/2018 | 12/21/2018 | 6 | 0 | 6 | 12/24/2018 | 12/24/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 380798 | 01841 | 5 | Solar | 05_12_29W1 | 09/10/2021 | 09/24/2021 | 1 | 0 | 1 | 09/27/2021 | 09/27/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2021 | 09/10/2021 | 2/27/2023 | Y | EXP | 365 | 01/13/2022 | 02/24/2022 | 43 | 0 | 43 |  |  | 3/3/2022 | Connected |  | N
National Grid | BOLTON | 210788 | 01740 | 7.6 | Solar | 05_12_7J4 | 03/04/2019 | 03/05/2019 | 0 | 0 | 0 | 03/06/2019 | 03/06/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2019 | 03/04/2019 | 7/21/2020 | Y | EXP | 365 | 02/25/2020 | 03/19/2020 | 23 | 0 | 23 |  |  | 5/26/2020 | Connected |  | N
National Grid | AUBURN | 412233 | 01501 | 0 | Battery Add-On | 05_14_43L3 | 05/28/2022 | 08/09/2022 | 48 | 38 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/10/2022 | 09/07/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 451807 | 01571 | 10 | Solar | 05_14_5J11 | 09/20/2022 | 09/21/2022 | 1 | 0 | 1 | 09/22/2022 | 09/22/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 09/20/2022 | 11/23/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2023 | Connected |  | N
National Grid | WESTMINSTER | 215214 | 01473 | 7.6 | Solar | 05_14_74L3 | 04/17/2019 | 04/24/2019 | 4 | 0 | 4 | 04/25/2019 | 04/25/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2019 | 04/17/2019 | 9/17/2020 | Y | EXP | 365 | 03/04/2020 | 03/19/2020 | 15 | 0 | 15 |  |  | 7/10/2020 | Connected |  | N
National Grid | FALL RIVER | 374977 | 02720 | 11.4 | Solar | 05_01_216W6 | 08/10/2021 | 09/07/2021 | 19 | 18 | 1 | 09/08/2021 | 09/08/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2021 |  | 12/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2022 | Connected |  | N
National Grid | WESTBOROUGH | 176827 | 01581 | 10 | Solar | 05_01_26W3 | 01/18/2016 | 01/18/2016 | 5 | 5 | 0 | 01/26/2016 | 01/26/2016 | 261 | 0 | 261 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2016 |  | 1/30/2017 | N | EXP | 320 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 548244 | 01905 | 6 | Solar | 05_01_412L5 | 08/23/2023 | 08/24/2023 | 1 | 0 | 1 | 08/25/2023 | 08/25/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 12/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N
National Grid | REVERE | 201267 | 02151 | 996 | Solar | 05_01_602W3 | 01/11/2019 | 02/11/2019 | 20 | 13 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2019 | 03/18/2019 | 24 | 18 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 176921 | 01835 | 996 | Solar | 05_05_115W52 | 11/12/2015 | 11/12/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 12/14/2015 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 11/12/2015 | 12/30/2017 | Y | STD | 522 | 04/14/2017 | 12/27/2017 | 170 | 0 | 170 | 12/29/2017 | 12/29/2017 | 12/30/2017 | Connected |  | N
National Grid | AMESBURY | 209566 | 01913 | 433.3 | Solar | 05_05_312W1 | 04/24/2019 | 05/06/2019 | 8 | 6 | 2 | 05/30/2019 | 05/30/2019 | 0 | 0 | 0 | 07/12/2019 | 08/19/2019 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 08/19/2019 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 379716 | 01841 | 9.8 | Solar | 05_12_29W1 | 09/23/2021 | 12/16/2021 | 4 | 0 | 4 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 184583 | 01740 | 15.2 | Solar | 05_12_7J6 | 07/15/2018 | 07/18/2018 | 1 | 0 | 1 | 07/19/2018 | 07/19/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 |  | 7/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2019 | Connected |  | N
National Grid | AUBURN | 498937 | 01501 | 5.04 | Solar | 05_14_43L3 | 02/28/2023 | 03/07/2023 | 5 | 3 | 2 | 03/08/2023 | 03/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 | 02/28/2023 | 11/29/2024 | Y | EXP | 365 | 06/09/2023 | 02/03/2024 | 240 | 3 | 237 |  |  | 2/6/2024 | Connected |  | N
National Grid | DUDLEY | 727510 | 01571 | 11.5 | Solar | 05_14_5J11 | 10/23/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | WESTMINSTER | 255172 | 01473 | 7.6 | Solar | 05_14_74L3 | 09/27/2019 | 10/02/2019 | 2 | 1 | 1 | 10/03/2019 | 10/03/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2019 | 09/27/2019 | 9/27/2020 | Y | EXP | 365 | 02/12/2020 | 03/12/2020 | 29 | 0 | 29 |  |  | 6/16/2020 | Connected |  | N
National Grid | FALL RIVER | 376566 | 02720 | 7.6 | Solar | 05_01_216W6 | 11/04/2021 | 12/06/2021 | 21 | 18 | 3 | 12/07/2021 | 12/07/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  | 1/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2022 | Connected |  | N
National Grid | WESTBOROUGH | 177912 | 01581 | 9 | Solar | 05_01_26W3 | 08/17/2017 | 08/17/2017 | 8 | 2 | 6 | 08/29/2017 | 08/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 |  | 8/22/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 551716 | 01904 | 15.2 | Solar | 05_01_412L5 | 09/05/2023 | 09/07/2023 | 3 | 1 | 2 | 09/08/2023 | 09/08/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 |  | 11/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2023 | Connected |  | N
National Grid | REVERE | 321925 | 02151 | 7.6 | Solar | 05_01_602W3 | 10/27/2020 | 10/28/2020 | 0 | 0 | 0 | 10/29/2020 | 10/29/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 11/19/2022 | N | EXP | 510 |  |  | 0 | 0 | 0 |  |  | 10/5/2022 | Connected |  | N
National Grid | HAVERHILL | 176947 | 01835 | 11.4 | Solar | 05_05_115W52 | 03/06/2017 | 03/06/2017 | 8 | 7 | 1 | 03/17/2017 | 03/17/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2017 |  | 1/21/2020 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 1/11/2020 | Connected |  | N
National Grid | AMESBURY | 209564 | 01913 | 700 | Solar | 05_05_312W1 | 04/24/2019 | 06/11/2019 | 26 | 18 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2019 | 07/08/2019 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 407981 | 01844 | 7.6 | Solar | 05_12_29W1 | 02/15/2022 | 02/16/2022 | 1 | 0 | 1 | 02/17/2022 | 02/17/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 | 02/15/2022 | 11/2/2023 | Y | EXP | 365 | 06/03/2022 | 06/10/2022 | 8 | 0 | 8 |  |  | 11/9/2022 | Connected |  | N
National Grid | BOLTON | 309830 | 01740 | 10 | Solar | 05_12_7J6 | 09/23/2020 |  | 62 | 54 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 529552 | 01501 | 10 | Solar | 05_14_43L3 | 05/26/2023 | 06/05/2023 | 5 | 1 | 4 | 06/06/2023 | 06/06/2023 | 238 | 218 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 7/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | DUDLEY | 616963 | 01571 | 6 | Solar | 05_14_5J12 | 06/11/2024 | 06/25/2024 | 4 | 0 | 4 | 06/26/2024 | 06/26/2024 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 8/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2024 | Connected |  | N
National Grid | WESTMINSTER | 261505 | 01473 | 0 | Solar | 05_14_74L3 | 10/22/2019 | 10/27/2019 | 3 | 0 | 3 | 10/28/2019 | 10/28/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 | 10/22/2019 | 11/15/2020 | Y | EXP | 365 | 04/25/2020 | 07/06/2020 | 72 | 0 | 72 |  |  | 2/8/2021 | Connected |  | N
National Grid | WESTPORT | 379354 | 02790 | 0 | Solar | 05_01_216W6 | 09/01/2021 | 09/13/2021 | 7 | 7 | 0 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2021 |  | 10/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2021 | Connected |  | N
National Grid | WESTBOROUGH | 178217 | 01581 | 3.8 | Solar | 05_01_26W3 | 04/13/2018 | 04/13/2018 | 9 | 0 | 9 | 07/16/2018 | 07/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 4/21/2019 | N | EXP | 279 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 565284 | 01904 | 6 | Solar | 05_01_412L5 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 27 | 5 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 11/01/2023 | 1/1/2025 | Y | EXP | 365 | 05/02/2024 | 06/06/2024 | 36 | 0 | 36 |  |  | 6/13/2024 | Connected |  | N
National Grid | REVERE | 345465 | 02151 | 500 | Solar | 05_01_602W3 | 04/07/2021 |  | 314 | 158 | 156 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176941 | 01835 | 7.6 | Solar | 05_05_115W52 | 12/19/2016 | 12/19/2016 | 3 | 2 | 1 | 12/22/2016 | 12/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2017 | 12/19/2016 | 2/28/2018 | Y | EXP | 421 | 09/15/2017 | 12/11/2017 | 53 | 0 | 53 | 2/20/2018 | 2/20/2018 | 3/6/2018 | Connected |  | N
National Grid | AMESBURY | 209562 | 01913 | 700 | Solar | 05_05_312W1 | 04/25/2019 | 06/11/2019 | 26 | 18 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2019 | 07/08/2019 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 420646 | 01841 | 10 | Solar | 05_12_29W1 | 03/31/2022 | 04/25/2022 | 16 | 13 | 3 | 04/26/2022 | 04/26/2022 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2022 | Connected |  | N
National Grid | BOLTON | 330995 | 01740 | 10 | Solar | 05_12_7J6 | 12/30/2020 | 01/05/2021 | 2 | 0 | 2 | 01/06/2021 | 01/06/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 4/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 637884 | 01501 | 5.76 | Solar | 05_14_43L3 | 10/24/2024 | 11/01/2024 | 5 | 1 | 4 | 11/04/2024 | 11/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/24/2024 | 3/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N
National Grid | WEBSTER | 201623 | 01570 | 7.6 | Solar | 05_14_5J13 | 11/19/2018 |  | 197 | 26 | 171 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 270454 | 01473 | 7.6 | Solar | 05_14_74L3 | 12/26/2019 | 01/06/2020 | 5 | 0 | 5 | 01/07/2020 | 01/07/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2020 | 12/26/2019 | 12/26/2020 | Y | EXP | 365 | 09/23/2020 | 10/13/2020 | 20 | 0 | 20 |  |  | 10/27/2020 | Connected |  | N
National Grid | FALL RIVER | 395135 | 02721 | 250 | Solar | 05_01_216W6 | 12/14/2021 | 01/03/2022 | 14 | 8 | 6 |  |  | 40 | 15 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 178678 | 01581 | 7.6 | Solar | 05_01_26W3 | 04/11/2018 | 04/11/2018 | 29 | 28 | 1 | 05/21/2018 | 05/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 |  | 4/17/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 564963 | 01905 | 6 | Solar | 05_01_412L5 | 11/15/2023 | 11/20/2023 | 3 | 1 | 2 | 11/21/2023 | 11/21/2023 | 46 | 21 | 25 | 04/01/2024 | 05/13/2024 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 05/13/2024 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 5/23/2025 | N | EXP | 365 | 07/25/2024 | 12/19/2024 | 148 | 0 | 148 |  |  | 12/31/2024 | Connected |  | N
National Grid | REVERE | 556865 | 02151 | 4998 | Solar | 05_01_602W3 | 07/02/2024 |  | 60 | 50 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 177142 | 01835 | 6 | Solar | 05_05_115W52 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2016 | 05/27/2016 | 6/6/2017 | Y | EXP | 350 | 09/01/2016 | 09/12/2016 | 6 | 0 | 6 | 12/1/2016 | 12/1/2016 | 12/1/2016 | Connected |  | N
National Grid | AMESBURY | 228960 | 01913 | 10 | Solar | 05_05_312W1 | 05/17/2019 | 05/24/2019 | 4 | 0 | 4 | 05/28/2019 | 05/28/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 542019 | 01844 | 3.8 | Solar | 05_12_29W1 | 07/26/2023 | 07/27/2023 | 1 | 0 | 1 | 07/28/2023 | 07/28/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2023 | 07/26/2023 | 8/24/2024 | Y | EXP | 365 | 10/20/2023 | 11/03/2023 | 15 | 0 | 15 |  |  | 11/15/2023 | Connected |  | N
National Grid | BOLTON | 333059 | 01740 | 7.6 | Solar | 05_12_7J6 | 03/08/2021 | 03/10/2021 | 1 | 0 | 1 | 03/11/2021 | 03/11/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 9/5/2022 | N | EXP | 480 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 654621 | 01540 | 10 | Solar | 05_14_43L3 | 11/15/2024 | 12/17/2024 | 8 | 4 | 4 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/15/2024 | 3/18/2026 | Y | EXP | 365 | 04/22/2025 | 04/30/2025 | 9 | 0 | 9 |  |  | 4/5/2025 | Connected |  | N
National Grid | DUDLEY | 203345 | 01571 | 13.8 | Solar | 05_14_5J13 | 12/21/2018 | 01/25/2019 | 22 | 22 | 0 | 01/25/2019 | 01/25/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 | 12/21/2018 | 3/26/2020 | Y | EXP | 422 | 10/18/2019 | 02/21/2020 | 126 | 0 | 126 |  |  | 2/25/2020 | Connected |  | N
National Grid | WESTMINSTER | 298830 | 01473 | 7.6 | Solar | 05_14_74L3 | 07/08/2020 | 07/15/2020 | 4 | 0 | 4 | 07/16/2020 | 07/16/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 404028 | 02790 | 12.86 | Solar | 05_01_216W6 | 12/29/2021 | 01/03/2022 | 3 | 0 | 3 | 01/04/2022 | 01/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2022 |  | 1/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2022 | Connected |  | N
National Grid | WESTBOROUGH | 189536 | 01581 | 17.6 | Solar | 05_01_26W3 | 06/28/2018 | 06/28/2018 | 13 | 11 | 2 | 07/19/2018 | 07/19/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2018 |  | 8/23/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2019 | Connected |  | N
National Grid | LYNN | 577506 | 01904 | 7.6 | Solar | 05_01_412L5 | 12/21/2023 | 12/22/2023 | 1 | 0 | 1 | 12/26/2023 | 12/26/2023 | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 2/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | REVERE | 608973 | 02151 | 10 | Solar | 05_01_602W3 | 05/06/2024 | 05/08/2024 | 1 | 0 | 1 | 05/09/2024 | 05/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 |  | 5/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 177134 | 01835 | 15.2 | Solar | 05_05_115W52 | 01/24/2017 | 01/24/2017 | 3 | 2 | 1 | 01/27/2017 | 01/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2017 |  | 1/29/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/26/2017 | 10/26/2017 | 11/17/2017 | Connected |  | N
National Grid | AMESBURY | 240960 | 01913 | 6 | Solar | 05_05_312W1 | 06/26/2019 | 08/07/2019 | 7 | 7 | 0 | 08/08/2019 | 08/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2019 | 06/26/2019 | 5/1/2020 | Y | EXP | 259 | 11/13/2019 | 11/27/2019 | 14 | 0 | 14 |  |  | 12/13/2019 | Connected |  | N
National Grid | LAWRENCE | 552539 | 01841 | 3.8 | Solar | 05_12_29W1 | 09/20/2023 | 09/22/2023 | 3 | 2 | 1 | 09/25/2023 | 09/25/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 12/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2024 | Connected |  | N
National Grid | BOLTON | 471831 | 01740 | 15.2 | Solar | 05_12_7J6 | 10/27/2022 | 10/28/2022 | 1 | 0 | 1 | 10/31/2022 | 10/31/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2022 |  | 3/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2023 | Connected |  | N
National Grid | AUBURN | 655934 | 01501 | 5.76 | Solar | 05_14_43L3 | 11/21/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | DUDLEY | 290419 | 01571 | 10 | Solar | 05_14_5J13 | 05/04/2020 | 05/06/2020 | 2 | 2 | 0 | 05/07/2020 | 05/07/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 |  | 5/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2020 | Connected |  | N
National Grid | WESTMINSTER | 312794 | 01473 | 3.84 | Solar | 05_14_74L3 | 10/27/2020 |  | 61 | 26 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 407694 | 02790 | 10 | Solar | 05_01_216W6 | 01/20/2022 | 01/24/2022 | 3 | 1 | 2 | 01/25/2022 | 01/25/2022 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 | 01/20/2022 | 8/31/2023 | Y | EXP | 365 | 05/07/2022 | 08/25/2022 | 108 | 0 | 108 |  |  | 9/1/2022 | Connected |  | N
National Grid | WESTBOROUGH | 189789 | 01581 | 15.2 | Solar | 05_01_26W3 | 07/02/2018 | 07/02/2018 | 5 | 4 | 1 | 07/11/2018 | 07/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 585721 | 01904 | 8.12 | Solar | 05_01_412L5 | 02/19/2024 | 04/18/2024 | 43 | 40 | 3 | 04/19/2024 | 04/19/2024 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2024 | 02/19/2024 | 6/21/2025 | Y | EXP | 365 | 07/03/2024 | 07/02/2024 | 0 | 0 | 0 |  |  | 7/16/2024 | Connected |  | N
National Grid | REVERE | 650633 | 02151 | 3.77 | Solar | 05_01_602W3 | 10/29/2024 | 11/06/2024 | 3 | 0 | 3 | 11/07/2024 | 11/07/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 177294 | 01835 | 17.6 | Solar | 05_05_115W52 | 08/24/2016 | 08/24/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/3/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 287290 | 01913 | 0 | Solar | 05_05_312W1 | 04/09/2020 | 04/10/2020 | 0 | 0 | 0 | 04/13/2020 | 04/13/2020 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2020 | 04/09/2020 | 4/9/2021 | Y | EXP | 365 | 09/05/2020 | 11/10/2020 | 66 | 0 | 66 |  |  | 2/23/2021 | Connected |  | N
National Grid | METHUEN | 554746 | 01844 | 10 | Solar | 05_12_29W1 | 09/25/2023 | 09/29/2023 | 4 | 0 | 4 | 10/02/2023 | 10/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 | 09/25/2023 | 12/10/2024 | Y | EXP | 365 | 02/09/2024 | 05/01/2024 | 83 | 0 | 83 |  |  | 8/4/2024 | Connected |  | N
National Grid | BOLTON | 567022 | 01740 | 6.96 | Solar | 05_12_7J6 | 11/15/2023 | 11/20/2023 | 3 | 1 | 2 | 11/21/2023 | 11/21/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 |  | 1/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2024 | Connected |  | N
National Grid | AUBURN | 657060 | 01501 | 10 | Solar | 05_14_43L3 | 11/26/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 525541 | 01571 | 15 | Solar | 05_14_5J13 | 05/10/2023 | 05/12/2023 | 2 | 0 | 2 | 05/15/2023 | 05/15/2023 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2023 |  | 7/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2023 | Connected |  | Y
National Grid | WESTMINSTER | 318214 | 01473 | 6.38 | Solar | 05_14_74L3 | 10/09/2020 | 10/12/2020 | 0 | 0 | 0 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N
National Grid | WESTPORT | 435624 | 02790 | 15.2 | Solar | 05_01_216W6 | 06/06/2022 | 06/24/2022 | 13 | 11 | 2 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N
National Grid | WESTBOROUGH | 194766 | 01581 | 650 | Solar | 05_01_26W3 | 09/19/2018 | 10/16/2018 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 | 11/20/2018 | 23 | 5 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 592892 | 01905 | 6 | Solar | 05_01_412L5 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/21/2024 | 7/26/2025 | Y | EXP | 365 | 06/28/2024 | 07/02/2024 | 5 | 0 | 5 |  |  | 11/14/2024 | Connected |  | N
National Grid | REVERE | 652673 | 02151 | 4.06 | Solar | 05_01_602W3 | 11/06/2024 | 12/02/2024 | 8 | 4 | 4 | 12/03/2024 | 12/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 178128 | 01835 | 7.6 | Solar | 05_05_115W52 | 07/11/2017 | 07/11/2017 | 5 | 5 | 0 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2017 |  | 7/17/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 10/23/2017 | 10/23/2017 | 10/23/2017 | Connected |  | N
National Grid | AMESBURY | 289142 | 01913 | 7.6 | Solar | 05_05_312W1 | 04/23/2020 | 06/09/2020 | 31 | 26 | 5 | 06/10/2020 | 06/10/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2020 | Connected |  | N
National Grid | METHUEN | 566137 | 01844 | 6 | Solar | 05_12_29W1 | 11/06/2023 |  | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 562600 | 01740 | 6 | Solar | 05_12_7J6 | 10/16/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 87 | 69 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 657119 | 01501 | 5.76 | Solar | 05_14_43L3 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | DUDLEY | 625454 | 01571 | 10 | Solar | 05_14_5J13 | 07/17/2024 | 07/29/2024 | 0 | 0 | 0 | 07/30/2024 | 07/30/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/17/2024 | 10/8/2025 | Y | EXP | 365 | 11/13/2024 | 01/13/2025 | 62 | 0 | 62 |  |  | 1/30/2025 | Connected |  | N
National Grid | WESTMINSTER | 401100 | 01473 | 0 | Other | 05_14_74L3 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 02/02/2022 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTPORT | 515975 | 02790 | 7.6 | Solar | 05_01_216W6 | 05/09/2023 | 08/16/2023 | 68 | 66 | 2 | 08/17/2023 | 08/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 11/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2023 | Connected |  | N
National Grid | WESTBOROUGH | 197089 | 01581 | 3.8 | Solar | 05_01_26W3 | 09/27/2018 | 10/12/2018 | 3 | 3 | 0 | 10/15/2018 | 10/15/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 10/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2019 | Connected |  | N
National Grid | LYNN | 609568 | 01904 | 3.8 | Solar | 05_01_412L5 | 05/08/2024 | 05/16/2024 | 2 | 0 | 2 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/08/2024 | 6/14/2025 | Y | EXP | 365 | 09/19/2024 | 09/30/2024 | 12 | 0 | 12 |  |  | 11/5/2024 | Connected |  | N
National Grid | REVERE | 656529 | 02151 | 7.98 | Solar | 05_01_602W3 | 11/24/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/24/2024 | 3/26/2026 | Y | EXP | 365 | 06/11/2025 | 11/21/2025 | 164 | 0 | 164 |  |  | 2/11/2026 | Connected |  | Y
National Grid | HAVERHILL | 178175 | 01835 | 15.2 | Solar | 05_05_115W52 | 03/23/2018 | 03/23/2018 | 2 | 1 | 1 | 03/28/2018 | 03/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 3/31/2019 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  | 10/2/2018 | Connected |  | N
National Grid | AMESBURY | 293153 | 01913 | 86 | Solar | 05_05_312W1 | 06/08/2020 | 06/24/2020 | 12 | 6 | 6 | 06/25/2020 | 06/25/2020 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 563069 | 01844 | 2.9 | Solar | 05_12_29W1 | 11/08/2023 | 11/13/2023 | 2 | 0 | 2 | 11/14/2023 | 11/14/2023 | 77 | 61 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 9/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | CLINTON | 599877 | 01510 | 6 | Solar | 05_12_7J6 | 04/15/2024 | 04/16/2024 | 1 | 0 | 1 | 04/17/2024 | 04/17/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/15/2024 | 4/25/2025 | Y | EXP | 365 | 08/22/2024 | 03/04/2025 | 195 | 0 | 195 |  |  | 3/19/2025 | Connected |  | Y
National Grid | AUBURN | 658163 | 01501 | 7.6 | Solar | 05_14_43L3 | 12/03/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/03/2024 | 2/21/2026 | Y | EXP | 365 | 02/20/2025 | 03/19/2025 | 28 | 14 | 14 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 177256 | 01571 | 43.2 | Solar | 05_14_5J15 | 08/17/2016 | 08/17/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 |  | 8/22/2017 | N | EXP | 321 |  |  | 0 | 0 | 0 | 8/23/2017 | 8/23/2017 | 8/22/2017 | Connected |  | N
National Grid | WESTMINSTER | 461031 | 01473 | 6 | Solar | 05_14_74L3 | 09/28/2022 | 10/06/2022 | 6 | 3 | 3 | 10/07/2022 | 10/07/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2022 |  | 12/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | WESTPORT | 543308 | 02790 | 15 | Solar | 05_01_216W6 | 07/24/2023 | 07/25/2023 | 1 | 0 | 1 | 07/26/2023 | 07/26/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2023 |  | 9/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2024 | Connected |  | N
National Grid | WESTBOROUGH | 196917 | 01581 | 9.2 | Solar | 05_01_26W3 | 09/25/2018 | 10/11/2018 | 10 | 9 | 1 | 10/12/2018 | 10/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2018 | 09/25/2018 | 3/8/2019 | Y | EXP | 147 | 12/25/2018 | 01/08/2019 | 14 | 0 | 14 |  |  | 3/4/2019 | Connected |  | N
National Grid | LYNN | 613091 | 01905 | 9.56 | Solar | 05_01_412L5 | 05/23/2024 | 06/04/2024 | 3 | 0 | 3 | 06/05/2024 | 06/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/23/2024 | 7/5/2025 | Y | EXP | 365 | 10/03/2024 | 11/21/2024 | 50 | 0 | 50 |  |  | 1/29/2025 | Connected |  | N
National Grid | REVERE | 739400 | 02151 | 7.6 | Solar | 05_01_602W3 | 12/10/2025 | 12/15/2025 | 3 | 0 | 3 | 12/16/2025 | 12/16/2025 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2026 | Connected |  | N
National Grid | HAVERHILL | 178687 | 01835 | 3500 | Solar | 05_05_115W52 | 12/19/2017 | 01/22/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2018 | 12/19/2017 | 12/5/2018 | Y | STD | 261 | 08/03/2018 | 10/09/2018 | 67 | 0 | 67 |  |  | 11/27/2018 | Connected |  | N
National Grid | AMESBURY | 299813 | 01913 | 10 | Solar | 05_05_312W1 | 03/03/2021 | 07/08/2020 | 0 | 0 | 0 | 03/04/2021 | 03/04/2021 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2021 | Connected |  | N
National Grid | METHUEN | 572266 | 01844 | 7.6 | Solar | 05_12_29W1 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 33 | 20 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2024 | 12/07/2023 | 1/31/2025 | Y | EXP | 365 | 04/17/2024 | 06/17/2024 | 62 | 0 | 62 |  |  | 7/4/2024 | Connected |  | N
National Grid | BOLTON | 602832 | 01740 | 6 | Solar | 05_12_7J6 | 04/17/2024 | 04/18/2024 | 1 | 0 | 1 | 04/19/2024 | 04/19/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 661220 | 01540 | 10 | Solar | 05_14_43L3 | 12/17/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | DUDLEY | 299817 | 01571 | 7.6 | Solar | 05_14_5J15 | 02/04/2021 | 02/08/2021 | 1 | 0 | 1 | 02/09/2021 | 02/09/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 460980 | 01473 | 3.8 | Solar | 05_14_74L3 | 09/29/2022 | 10/10/2022 | 7 | 3 | 4 | 10/11/2022 | 10/11/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 | 09/29/2022 | 7/19/2024 | Y | EXP | 390 | 01/24/2023 | 02/01/2023 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 568830 | 02790 | 15.435 | Solar | 05_01_216W6 | 11/06/2023 | 11/08/2023 | 2 | 0 | 2 | 11/09/2023 | 11/09/2023 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 |  | 5/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2024 | Connected |  | N
National Grid | WESTBOROUGH | 258441 | 01581 | 10 | Solar | 05_01_26W3 | 10/17/2019 | 10/23/2019 | 3 | 0 | 3 | 10/24/2019 | 10/24/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 | 10/17/2019 | 3/4/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | LYNN | 677277 | 01905 | 7.6 | Solar | 05_01_412L5 | 03/11/2025 | 03/25/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2025 | Connected |  | N
National Grid | REVERE | 614910 | 02151 | 4000 | Solar | 05_01_607W1 | 09/25/2024 | 10/30/2024 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 12/02/2024 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HAVERHILL | 178686 | 01835 | 1500 | Solar | 05_05_115W52 | 12/19/2017 | 01/22/2016 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2018 | 12/19/2017 | 12/6/2018 | Y | STD | 262 | 08/03/2018 | 02/20/2020 | 566 | 0 | 566 |  |  | 12/6/2018 | Connected |  | N
National Grid | AMESBURY | 328513 | 01913 | 0 | Solar | 05_05_312W1 | 11/27/2020 | 12/03/2020 | 3 | 0 | 3 | 12/04/2020 | 12/04/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2021 |  | 8/26/2022 | N | EXP | 560 |  |  | 0 | 0 | 0 |  |  | 7/19/2022 | Connected |  | N
National Grid | METHUEN | 572647 | 01844 | 5.8 | Solar | 05_12_29W1 | 11/27/2023 | 11/30/2023 | 3 | 2 | 1 | 12/01/2023 | 12/01/2023 | 37 | 16 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2024 | Connected |  | N
National Grid | BOLTON | 189881 | 01740 | 3.8 | Solar | 05_12_7J7 | 07/03/2018 | 07/03/2018 | 5 | 0 | 5 | 10/31/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 662220 | 01501 | 5.76 | Solar | 05_14_43L3 | 12/23/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 307055 | 01570 | 7.6 | Solar | 05_14_5J15 | 08/28/2020 | 08/31/2020 | 0 | 0 | 0 | 09/01/2020 | 09/01/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 | 08/28/2020 | 8/30/2021 | Y | EXP | 365 | 12/19/2020 | 01/21/2021 | 33 | 0 | 33 |  |  | 5/25/2021 | Connected |  | N
National Grid | GARDNER | 468024 | 01440 | 10 | Solar | 05_14_74L3 | 10/20/2022 | 10/24/2022 | 2 | 0 | 2 | 10/25/2022 | 10/25/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  | 12/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | WESTPORT | 570119 | 02790 | 9.45 | Solar | 05_01_216W6 | 01/31/2024 | 02/06/2024 | 4 | 1 | 3 | 02/07/2024 | 02/07/2024 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 01/31/2024 | 4/26/2025 | Y | EXP | 365 | 07/10/2024 | 07/16/2024 | 7 | 0 | 7 |  |  | 7/26/2024 | Connected |  | N
National Grid | WESTBOROUGH | 286480 | 01581 | 7.6 | Solar | 05_01_26W3 | 05/26/2020 | 06/03/2020 | 5 | 0 | 5 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 678787 | 01905 | 11.52 | Solar | 05_01_412L5 | 03/18/2025 | 04/01/2025 | 5 | 0 | 5 | 05/22/2025 | 05/22/2025 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 03/18/2025 | 7/11/2026 | Y | EXP | 365 | 09/17/2025 | 10/10/2025 | 24 | 0 | 24 |  |  | 10/22/2025 | Connected |  | N
National Grid | REVERE | 673050 | 02151 | 5.76 | Solar | 05_01_607W1 | 02/20/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | HAVERHILL | 178798 | 01835 | 6 | Solar | 05_05_115W52 | 02/14/2018 | 02/14/2018 | 18 | 0 | 18 | 03/28/2018 | 03/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2018 |  | 2/19/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 338021 | 01913 | 80 | Solar | 05_05_312W1 | 01/21/2021 | 01/26/2021 | 2 | 0 | 2 | 01/27/2021 | 01/27/2021 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2021 | 01/21/2021 | 12/31/2024 | Y | EXP | 386 | 08/26/2024 | 08/26/2024 | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | LAWRENCE | 583921 | 01841 | 5.22 | Solar | 05_12_29W1 | 02/12/2024 | 02/20/2024 | 5 | 2 | 3 | 02/21/2024 | 02/21/2024 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 4/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2024 | Connected |  | N
National Grid | BOLTON | 225696 | 01740 | 7.6 | Solar | 05_12_7J7 | 06/12/2019 | 06/18/2019 | 3 | 0 | 3 | 06/19/2019 | 06/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2019 | 06/12/2019 | 4/23/2021 | Y | EXP | 365 | 10/03/2020 | 11/18/2020 | 46 | 0 | 46 |  |  | 1/8/2021 | Connected |  | N
National Grid | AUBURN | 662119 | 01501 | 3.8 | Solar | 05_14_43L3 | 12/21/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | DUDLEY | 533655 | 01571 | 10 | Solar | 05_14_5J16 | 06/20/2023 | 06/28/2023 | 6 | 4 | 2 | 06/29/2023 | 06/29/2023 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 06/20/2023 | 9/28/2024 | Y | EXP | 365 | 01/04/2024 | 01/18/2024 | 15 | 0 | 15 |  |  | 1/29/2024 | Connected |  | N
National Grid | GARDNER | 475239 | 01440 | 7.6 | Solar | 05_14_74L3 | 12/07/2022 | 12/11/2022 | 3 | 0 | 3 | 12/12/2022 | 12/12/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 |  | 1/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2023 | Connected |  | N
National Grid | WESTPORT | 574056 | 02790 | 0 | Battery Add-On | 05_01_216W6 | 11/28/2023 | 01/02/2024 | 23 | 17 | 6 | 01/03/2024 | 01/03/2024 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | WESTBOROUGH | 337541 | 01581 | 9.8 | Solar | 05_01_26W3 | 01/19/2021 | 01/25/2021 | 3 | 0 | 3 | 01/26/2021 | 01/26/2021 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  | 3/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2021 | Connected |  | N
National Grid | LYNN | 731941 | 01904 | 13.36 | Solar | 05_01_412L5 | 11/06/2025 | 11/24/2025 | 11 | 8 | 3 | 11/25/2025 | 11/25/2025 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 704606 | 02151 | 3.8 | Solar | 05_01_607W1 | 07/14/2025 | 09/11/2025 | 5 | 1 | 4 | 09/12/2025 | 09/12/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 | 07/14/2025 | 10/20/2026 | Y | EXP | 365 | 03/07/2026 |  | 26 | 0 | 26 |  |  |  | Construction |  | N
National Grid | HAVERHILL | 186693 | 01835 | 3300 | Solar | 05_05_115W52 | 08/07/2018 | 09/21/2018 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/24/2018 | 11/01/2018 | 29 | 10 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 343902 | 01913 | 7.6 | Solar | 05_05_312W1 | 02/25/2021 | 02/26/2021 | 0 | 0 | 0 | 03/01/2021 | 03/01/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2021 |  | 2/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2022 | Connected |  | N
National Grid | LAWRENCE | 587528 | 01841 | 7.6 | Solar | 05_12_29W1 | 02/09/2024 | 02/14/2024 | 3 | 0 | 3 | 02/15/2024 | 02/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 659647 | 01740 | 5.76 | Solar | 05_12_7J7 | 12/10/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 494666 | 01501 | 360 | Solar | 05_14_43L4 | 07/11/2023 | 09/01/2023 | 39 | 30 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/05/2023 | 10/02/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | DUDLEY | 753145 | 01571 | 110 | Solar | 05_14_5J40 | 03/10/2026 |  | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | GARDNER | 505172 | 01440 | 6 | Solar | 05_14_74L3 | 03/09/2023 | 03/16/2023 | 5 | 0 | 5 | 03/17/2023 | 03/17/2023 | 23 | 0 | 23 | 04/27/2023 | 05/31/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 05/31/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 5/18/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 582430 | 02790 | 15.2 | Solar | 05_01_216W6 | 01/09/2024 | 01/11/2024 | 2 | 0 | 2 | 01/12/2024 | 01/12/2024 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 4/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | WESTBOROUGH | 450660 | 01581 | 19 | Solar | 05_01_26W3 | 08/10/2022 | 09/12/2022 | 22 | 22 | 0 | 09/13/2022 | 09/13/2022 | 13 | 0 | 13 | 12/07/2022 | 03/20/2023 | 70 | 0 | 70 |  |  | 0 | 0 | 0 | 03/20/2023 | 70 | 0 | 70 |  |  | 0 | 0 | 0 | 3/23/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 635538 | 01904 | 0 | Other | 05_01_412L6 | 11/08/2024 | 12/12/2024 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 01/13/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | REVERE | 739577 | 02151 | 7.6 | Solar | 05_01_607W1 | 12/11/2025 | 12/12/2025 | 3 | 0 | 3 | 01/13/2026 | 01/13/2026 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 191028 | 01844 | 233.1 | Solar | 05_05_115W52 | 08/27/2018 | 09/10/2018 | 8 | 1 | 7 | 09/11/2018 | 09/11/2018 | 63 | 30 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 356524 | 01844 | 9.86 | Solar | 05_05_312W1 | 05/06/2021 | 05/07/2021 | 1 | 1 | 0 | 05/10/2021 | 05/10/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 5/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2021 | Connected |  | N
National Grid | LAWRENCE | 588428 | 01841 | 3.8 | Solar | 05_12_29W1 | 02/21/2024 | 04/17/2024 | 28 | 25 | 3 | 04/18/2024 | 04/18/2024 | 24 | 11 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2024 |  | 5/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2024 | Connected |  | N
National Grid | BOLTON | 725831 | 01740 | 5.76 | Solar | 05_12_7J901 | 10/10/2025 | 12/10/2025 | 2 | 0 | 2 | 01/02/2026 | 01/02/2026 | 17 | 6 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AUBURN | 678808 | 01501 | 5.76 | Solar | 05_14_43L4 | 03/18/2025 | 09/04/2025 | 7 | 2 | 5 | 09/19/2025 | 09/19/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 | 03/18/2025 | 11/3/2026 | Y | EXP | 365 | 01/13/2026 |  | 79 | 0 | 79 |  |  |  | Construction |  | N
National Grid | WEBSTER | 501981 | 01570 | 11.02 | Solar | 05_14_5J40 | 02/14/2023 | 03/21/2023 | 25 | 23 | 2 | 03/22/2023 | 03/22/2023 | 129 | 109 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 10/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2023 | Connected |  | N
National Grid | GARDNER | 516649 | 01440 | 10 | Solar | 05_14_74L3 | 05/19/2023 | 05/22/2023 | 2 | 1 | 1 | 05/23/2023 | 05/23/2023 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 05/19/2023 | 8/16/2024 | Y | EXP | 365 | 01/24/2024 | 01/31/2024 | 8 | 0 | 8 |  |  | 2/28/2024 | Connected |  | N
National Grid | FALL RIVER | 582976 | 02722 | 8.775 | Solar | 05_01_216W6 | 01/29/2024 | 02/08/2024 | 9 | 8 | 1 | 02/09/2024 | 02/09/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N
National Grid | WESTBOROUGH | 403477 | 01581 | 9.57 | Solar | 05_01_26W3 | 08/01/2022 | 01/13/2022 | 21 | 21 | 0 | 08/31/2022 | 08/31/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 |  | 10/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2023 | Connected |  | N
National Grid | LYNN | 718416 | 01904 | 0 | Other | 05_01_412L6 | 10/27/2025 | 01/15/2026 | 54 | 48 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/16/2026 | 02/09/2026 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LYNN | 174398 | 01905 | 1000 | Solar | 05_01_607W1 | 06/14/2012 | 06/14/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2012 | 09/26/2012 | 64 | 0 | 64 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 196024 | 01844 | 7.6 | Solar | 05_05_115W52 | 11/27/2018 | 12/05/2018 | 5 | 0 | 5 | 12/06/2018 | 12/06/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 384615 | 01844 | 200 | Solar | 05_05_312W1 | 06/13/2022 | 08/04/2022 | 36 | 28 | 8 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 590460 | 01841 | 5 | Solar | 05_12_29W1 | 03/01/2024 | 05/28/2024 | 16 | 16 | 0 | 05/29/2024 | 05/29/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | BOLTON | 749030 | 01740 | 11.4 | Solar | 05_12_7J901 | 02/03/2026 | 02/04/2026 | 2 | 0 | 2 | 03/18/2026 | 03/18/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MILLBURY | 709253 | 01527 | 10 | Solar | 05_14_43L4 | 08/04/2025 | 09/02/2025 | 4 | 0 | 4 | 09/03/2025 | 09/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 | 08/04/2025 | 11/3/2026 | Y | EXP | 365 | 12/18/2025 |  | 105 | 0 | 105 |  |  |  | Construction |  | N
National Grid | WEBSTER | 534674 | 01570 | 7.6 | Solar | 05_14_5J40 | 06/28/2023 | 07/05/2023 | 5 | 4 | 1 | 07/06/2023 | 07/06/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2023 |  | 8/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2023 | Connected |  | N
National Grid | GARDNER | 539231 | 01440 | 5.76 | Solar | 05_14_74L3 | 07/11/2023 | 07/12/2023 | 1 | 0 | 1 | 07/13/2023 | 07/13/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  | 11/13/2024 | N | EXP | 365 | 04/17/2024 | 05/28/2024 | 42 | 0 | 42 |  |  | 6/10/2024 | Connected |  | N
National Grid | WESTPORT | 588321 | 02790 | 6.282 | Solar | 05_01_216W6 | 03/05/2024 | 03/27/2024 | 17 | 16 | 1 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2024 | Connected |  | N
National Grid | WESTBOROUGH | 404298 | 01581 | 6 | Solar | 05_01_26W3 | 01/13/2022 | 01/18/2022 | 2 | 0 | 2 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 | 01/13/2022 | 7/13/2023 | Y | EXP | 365 | 05/27/2022 | 06/13/2022 | 18 | 0 | 18 |  |  | 7/26/2022 | Connected |  | Y
National Grid | LYNN | 745924 | 01904 | 120 | Solar | 05_01_412L6 | 03/23/2026 |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LYNN | 174397 | 01905 | 1000 | Solar | 05_01_607W1 | 06/14/2012 | 06/14/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 199068 | 01841 | 10 | Solar | 05_05_115W52 | 10/21/2018 | 11/08/2018 | 12 | 6 | 6 | 11/09/2018 | 11/09/2018 | 45 | 26 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 |  | 1/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2019 | Connected |  | N
National Grid | METHUEN | 384619 | 01844 | 400 | Solar | 05_05_312W1 | 06/13/2022 | 08/04/2022 | 36 | 27 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 596319 | 01844 | 3.8 | Solar | 05_12_29W1 | 03/20/2024 | 03/25/2024 | 3 | 0 | 3 | 03/26/2024 | 03/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 | 03/20/2024 | 5/29/2025 | Y | EXP | 365 | 10/17/2024 | 02/12/2025 | 68 | 0 | 68 |  |  | 12/31/2024 | Connected |  | N
National Grid | BOLTON | 176380 | 01740 | 1520 | Solar | 05_12_7J901 | 11/23/2015 | 11/23/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 | 12/18/2015 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2016 |  | 11/29/2016 | N | STD | 251 |  |  | 0 | 0 | 0 | 12/6/2016 | 12/6/2016 | 12/12/2016 | Connected |  | N
National Grid | AUBURN | 715619 | 01501 | 13.12 | Solar | 05_14_43L4 | 08/29/2025 | 10/07/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEBSTER | 534198 | 01570 | 6.912 | Solar | 05_14_5J40 | 03/20/2024 | 04/15/2024 | 18 | 15 | 3 | 04/16/2024 | 04/16/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 544120 | 01440 | 5.04 | Solar | 05_14_74L3 | 09/05/2023 | 09/06/2023 | 1 | 0 | 1 | 09/07/2023 | 09/07/2023 | 24 | 0 | 24 | 10/24/2023 | 11/27/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 11/27/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 11/17/2023 |  | 11/29/2024 | N | EXP | 365 | 02/01/2024 | 04/19/2024 | 79 | 0 | 79 |  |  | 5/6/2024 | Connected |  | N
National Grid | WESTPORT | 598176 | 02790 | 11.5 | Solar | 05_01_216W6 | 03/20/2024 | 04/11/2024 | 16 | 13 | 3 | 04/12/2024 | 04/12/2024 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 |  | 4/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 430569 | 01581 | 11.02 | Solar | 05_01_26W3 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2022 | 07/19/2022 | 11/16/2023 | Y | EXP | 365 | 10/12/2022 | 11/14/2022 | 34 | 0 | 34 |  |  | 12/7/2022 | Connected |  | Y
National Grid | LYNN | 745928 | 01905 | 180 | Solar | 05_01_412L6 | 03/23/2026 |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LYNN | 174396 | 01905 | 2000 | Solar | 05_01_607W1 | 06/14/2012 | 06/14/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2012 | 09/24/2012 | 62 | 0 | 62 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2013 | 06/14/2012 | 2/11/2014 | Y | STD | 270 | 11/27/2013 | 04/25/2014 | 100 | 0 | 100 | 5/6/2014 | 5/6/2014 | 5/23/2014 | Connected |  | N
National Grid | LAWRENCE | 204363 | 01841 | 0 | Solar | 05_05_115W52 | 12/27/2018 | 01/04/2019 | 4 | 0 | 4 | 01/07/2019 | 01/07/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2019 | Connected |  | N
National Grid | METHUEN | 384617 | 01844 | 400 | Solar | 05_05_312W1 | 06/13/2022 | 08/04/2022 | 36 | 27 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 600626 | 01844 | 3.8 | Solar | 05_12_29W1 | 04/10/2024 | 04/15/2024 | 3 | 0 | 3 | 04/16/2024 | 04/16/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 280354 | 01740 | 7.6 | Solar | 05_12_7J901 | 03/04/2020 | 06/02/2020 | 63 | 62 | 1 | 06/03/2020 | 06/03/2020 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 | 03/04/2020 | 6/2/2021 | Y | EXP | 365 | 12/11/2020 | 03/16/2021 | 95 | 0 | 95 |  |  | 3/19/2021 | Connected |  | N
National Grid | AUBURN | 732219 | 01501 | 7.6 | Solar | 05_14_43L4 | 11/07/2025 | 11/20/2025 | 1 | 0 | 1 | 01/13/2026 | 01/13/2026 | 37 | 23 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2026 |  | 3/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 574631 | 01570 | 6.38 | Solar | 05_14_5J40 | 01/23/2024 | 01/29/2024 | 4 | 0 | 4 | 01/30/2024 | 01/30/2024 | 79 | 54 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2024 | 01/23/2024 | 6/3/2025 | Y | EXP | 365 | 10/15/2024 | 01/03/2025 | 81 | 0 | 81 |  |  | 1/24/2025 | Connected |  | Y
National Grid | GARDNER | 544833 | 01440 | 10 | Solar | 05_14_74L3 | 08/16/2023 | 08/21/2023 | 3 | 0 | 3 | 08/22/2023 | 08/22/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2023 | 08/16/2023 | 9/24/2024 | Y | EXP | 365 | 03/26/2024 | 04/23/2024 | 29 | 0 | 29 |  |  | 6/1/2024 | Connected |  | N
National Grid | WESTPORT | 609347 | 02790 | 100 | Solar | 05_01_216W6 | 05/29/2024 | 08/20/2024 | 57 | 48 | 9 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 | 05/29/2024 | 11/16/2025 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2025 | Connected |  | N
National Grid | WESTBOROUGH | 433265 | 01581 | 150 | Solar | 05_01_26W3 | 06/01/2022 | 06/30/2022 | 20 | 12 | 8 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 176664 | 01905 | 660 | Solar | 05_01_412L6 | 10/20/2015 | 10/20/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 | 11/24/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2017 |  | 10/25/2016 | N | STD | 237 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 174707 | 01905 | 60 | Natural Gas | 05_01_607W1 | 06/17/2013 | 06/17/2013 | 13 | 5 | 8 | 07/08/2013 | 07/08/2013 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2013 |  | 12/1/2017 | N | EXP | 1592 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 257375 | 01844 | 10 | Solar | 05_05_115W52 | 10/14/2019 | 10/21/2019 | 5 | 5 | 0 | 10/22/2019 | 10/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2019 | 10/14/2019 | 7/7/2020 | Y | EXP | 365 | 12/20/2019 | 02/19/2020 | 61 | 0 | 61 |  |  | 2/20/2020 | Connected |  | N
National Grid | METHUEN | 471366 | 01844 | 9.75 | Solar | 05_05_312W1 | 11/09/2022 | 11/21/2022 | 8 | 3 | 5 | 11/22/2022 | 11/22/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  | 1/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | N
National Grid | METHUEN | 605243 | 01844 | 6.96 | Solar | 05_12_29W1 | 04/19/2024 | 06/11/2024 | 22 | 20 | 2 | 06/12/2024 | 06/12/2024 | 155 | 25 | 130 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 603654 | 01740 | 3.8 | Solar | 05_12_7J901 | 04/15/2024 | 04/23/2024 | 7 | 3 | 4 | 04/24/2024 | 04/24/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 | 04/15/2024 | 5/16/2025 | Y | EXP | 365 | 08/29/2024 | 12/05/2024 | 99 | 0 | 99 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 735576 | 01501 |  | Solar | 05_14_43L4 | 11/21/2025 | 11/24/2025 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WEBSTER | 596274 | 01570 | 5 | Solar | 05_14_5J40 | 04/01/2024 | 05/08/2024 | 26 | 23 | 3 | 05/09/2024 | 05/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 | 04/01/2024 | 5/31/2025 | Y | EXP | 365 | 07/16/2024 | 09/25/2024 | 72 | 0 | 72 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 547080 | 01440 | 6 | Solar | 05_14_74L3 | 08/16/2023 | 08/17/2023 | 1 | 0 | 1 | 08/18/2023 | 08/18/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2023 | 08/16/2023 | 11/14/2024 | Y | EXP | 365 | 01/24/2024 | 01/31/2024 | 8 | 0 | 8 |  |  | 3/18/2024 | Connected |  | N
National Grid | WESTPORT | 638189 | 02790 | 10 | Solar | 05_01_216W6 | 09/06/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 09/06/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | WESTBOROUGH | 476717 | 01581 | 160 | Solar | 05_01_26W3 | 12/13/2022 | 02/20/2023 | 45 | 38 | 7 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 12/13/2022 | 3/9/2025 | Y | STD | 133 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | LYNN | 176663 | 01905 | 1000 | Solar | 05_01_412L6 | 10/20/2015 | 10/23/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 | 11/24/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2017 | 10/20/2015 | 6/10/2021 | Y | STD | 316 | 10/03/2020 | 02/26/2021 | 146 | 0 | 146 |  |  | 6/8/2021 | Connected |  | N
National Grid | LYNN | 175258 | 01905 | 42 | Solar | 05_01_607W1 | 01/08/2015 | 01/08/2015 | 4 | 2 | 2 | 01/15/2015 | 01/15/2015 | 425 | 0 | 425 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 |  | Withdrawn |  | N
National Grid | METHUEN | 280942 | 01844 | 3.8 | Solar | 05_05_115W52 | 03/02/2020 | 03/11/2020 | 7 | 3 | 4 | 03/12/2020 | 03/12/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2020 | 03/02/2020 | 2/26/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2020 | Connected |  | N
National Grid | METHUEN | 501473 | 01844 | 15.2 | Solar | 05_05_312W1 | 02/13/2023 | 02/15/2023 | 2 | 1 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | N
National Grid | LAWRENCE | 607470 | 01841 | 7.6 | Solar | 05_12_29W1 | 04/30/2024 | 05/10/2024 | 1 | 0 | 1 | 05/13/2024 | 05/13/2024 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 04/30/2024 | 12/31/2025 | Y | EXP | 365 | 02/19/2025 | 10/03/2025 | 227 | 0 | 227 |  |  | 10/29/2025 | Connected |  | N
National Grid | BOLTON | 657216 | 01740 | 2.9 | Solar | 05_12_7J901 | 11/27/2024 | 02/25/2025 | 6 | 3 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | AUBURN | 742927 | 01501 | 0 | Other | 05_14_43L4 | 02/24/2026 |  | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WEBSTER | 597978 | 01570 | 3.8 | Solar | 05_14_5J40 | 04/18/2024 | 04/22/2024 | 2 | 0 | 2 | 04/23/2024 | 04/23/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 04/18/2024 | 7/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 551612 | 01440 | 6.09 | Solar | 05_14_74L3 | 09/05/2023 | 09/25/2023 | 15 | 14 | 1 | 09/26/2023 | 09/26/2023 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2023 | 09/05/2023 | 2/9/2025 | Y | EXP | 365 | 01/31/2024 | 03/22/2024 | 52 | 0 | 52 |  |  | 6/13/2024 | Connected |  | N
National Grid | FALL RIVER | 645214 | 02721 | 6.175 | Solar | 05_01_216W6 | 10/08/2024 | 10/22/2024 | 3 | 0 | 3 | 10/23/2024 | 10/23/2024 | 76 | 25 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 520551 | 01581 | 0 | Solar | 05_01_26W3 | 04/20/2023 | 04/27/2023 | 5 | 3 | 2 | 04/28/2023 | 04/28/2023 | 231 | 210 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 |  | 5/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 201422 | 01904 | 500 | Solar | 05_01_412L6 | 12/07/2018 | 01/05/2019 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2019 | 02/05/2019 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 176116 | 01905 | 7.6 | Solar | 05_01_607W1 | 08/20/2015 | 08/20/2015 | 0 | 0 | 0 | 08/24/2015 | 08/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 8/29/2016 | N | EXP | 354 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 3/18/2016 | Connected |  | N
National Grid | METHUEN | 301536 | 01844 | 3.8 | Solar | 05_05_115W52 | 07/16/2020 | 07/22/2020 | 3 | 0 | 3 | 07/23/2020 | 07/23/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 557462 | 01844 | 7.6 | Solar | 05_05_312W1 | 02/23/2024 | 10/03/2023 | 7 | 5 | 2 | 03/06/2024 | 03/06/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/23/2024 | 3/14/2025 | Y | EXP | 365 | 04/20/2024 | 05/20/2024 | 31 | 0 | 31 |  |  | 5/22/2024 | Connected |  | N
National Grid | METHUEN | 613294 | 01844 | 3.8 | Solar | 05_12_29W1 | 05/31/2024 | 06/10/2024 | 1 | 0 | 1 | 06/11/2024 | 06/11/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 657861 | 01740 | 5.76 | Solar | 05_12_7J901 | 12/05/2024 | 01/17/2025 | 5 | 0 | 5 | 01/21/2025 | 01/21/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | AUBURN | 174281 | 01501 | 55 | Solar | 05_14_43L4 | 12/31/2011 | 12/31/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 | 03/07/2012 | 02/02/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2012 | 12/31/2011 | 1/24/2012 | Y | EXP | 85 | 05/14/2012 | 05/18/2012 | 4 | 0 | 4 | 6/15/2012 | 6/15/2012 | 7/3/2012 | Connected |  | N
National Grid | WEBSTER | 651593 | 01570 | 3.8 | Solar | 05_14_5J40 | 11/12/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/12/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 560972 | 01440 | 7.6 | Solar | 05_14_74L3 | 10/05/2023 | 05/07/2024 | 2 | 0 | 2 | 05/08/2024 | 05/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 | 10/05/2023 | 6/12/2025 | Y | EXP | 365 | 07/31/2024 | 09/30/2024 | 62 | 0 | 62 |  |  | 10/17/2024 | Connected |  | N
National Grid | WESTPORT | 655285 | 02790 | 7.6 | Solar | 05_01_216W6 | 11/22/2024 | 11/26/2024 | 2 | 0 | 2 | 11/27/2024 | 11/27/2024 | 52 | 28 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | WESTBOROUGH | 520407 | 01581 | 15 | Solar | 05_01_26W3 | 04/20/2023 | 04/24/2023 | 2 | 0 | 2 | 04/25/2023 | 04/25/2023 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2023 |  | 8/18/2025 | N | EXP | 730 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 311549 | 01905 | 250 | Hydro | 05_01_412L6 | 02/22/2022 | 05/27/2022 | 67 | 59 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2022 | 06/21/2022 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 | 02/22/2022 | 12/31/2024 | Y | STD | 306 | 10/01/2024 | 10/31/2024 | 31 | 0 | 31 |  |  | 1/9/2025 | Connected |  | N
National Grid | LYNN | 176507 | 01905 | 6 | Solar | 05_01_607W1 | 03/24/2016 | 03/24/2016 | 36 | 36 | 0 | 05/17/2016 | 05/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 03/24/2016 | 3/30/2017 | Y | EXP | 297 | 07/28/2016 | 09/23/2016 | 40 | 0 | 40 | 11/8/2016 | 11/8/2016 | 11/10/2016 | Connected |  | N
National Grid | METHUEN | 320315 | 01844 | 15.6 | Solar | 05_05_115W52 | 10/20/2020 | 01/27/2021 | 66 | 59 | 7 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 | 10/20/2020 | 7/16/2022 | Y | EXP | 365 | 04/03/2021 | 05/17/2021 | 44 | 0 | 44 |  |  | 10/26/2021 | Connected |  | N
National Grid | METHUEN | 573957 | 01844 | 0 | Battery Add-On | 05_05_312W1 | 11/28/2023 | 12/28/2023 | 21 | 20 | 1 | 12/29/2023 | 12/29/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2024 |  | 3/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2024 | Connected |  | N
National Grid | LAWRENCE | 619178 | 01841 | 5 | Solar | 05_12_29W1 | 06/19/2024 | 06/28/2024 | 5 | 0 | 5 | 07/01/2024 | 07/01/2024 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 | 06/19/2024 | 7/30/2025 | Y | EXP | 365 | 09/06/2024 | 12/19/2024 | 105 | 0 | 105 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 691255 | 01740 | 3.8 | Solar | 05_12_7J901 | 05/13/2025 | 05/23/2025 | 1 | 0 | 1 | 06/16/2025 | 06/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2025 | 05/13/2025 | 7/15/2026 | Y | EXP | 365 | 10/01/2025 | 11/18/2025 | 49 | 0 | 49 |  |  | 12/15/2025 | Connected |  | N
National Grid | AUBURN | 177608 | 01501 | 42 | Solar | 05_14_43L4 | 09/20/2017 | 09/20/2017 | 12 | 11 | 1 | 10/09/2017 | 10/09/2017 | 1 | 0 | 1 | 02/09/2018 | 02/09/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 9/26/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  | 7/16/2018 | Connected |  | N
National Grid | WEBSTER | 656760 | 01570 | 10 | Solar | 05_14_5J40 | 12/03/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 567261 | 01440 | 5 | Solar | 05_14_74L3 | 03/28/2024 | 12/26/2023 | 12 | 9 | 3 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 03/28/2024 | 5/23/2025 | Y | EXP | 365 | 06/05/2024 | 08/20/2024 | 77 | 0 | 77 |  |  | 10/11/2024 | Connected |  | N
National Grid | WESTPORT | 657684 | 02790 | 10 | Solar | 05_01_216W6 | 12/02/2024 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 544706 | 01581 | 10 | Solar | 05_01_26W3 | 08/08/2023 | 08/10/2023 | 2 | 0 | 2 | 08/11/2023 | 08/11/2023 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2023 | 08/08/2023 | 10/10/2024 | Y | EXP | 365 | 03/05/2024 | 03/04/2024 | 0 | 0 | 0 |  |  | 3/26/2024 | Connected |  | N
National Grid | LYNN | 455151 | 01904 | 100 | Solar | 05_01_412L6 | 11/15/2022 |  | 237 | 229 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 177059 | 01905 | 900 | Solar | 05_01_607W1 | 01/17/2017 | 01/17/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/09/2017 | 15 | 1 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/23/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 450178 | 01841 | 10 | Solar | 05_05_115W52 | 08/26/2022 | 09/22/2022 | 18 | 15 | 3 | 09/23/2022 | 09/23/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 | 08/26/2022 | 2/8/2024 | Y | EXP | 365 | 01/07/2023 | 02/07/2023 | 32 | 0 | 32 |  |  | 3/23/2023 | Connected |  | N
National Grid | METHUEN | 573239 | 01844 | 500 | Solar | 05_05_312W1 | 02/08/2024 | 05/15/2024 | 66 | 57 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2024 | 05/29/2024 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 628547 | 01841 | 7.6 | Solar | 05_12_29W1 | 09/17/2024 | 11/25/2024 | 26 | 25 | 1 | 11/26/2024 | 11/26/2024 | 61 | 41 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 09/17/2024 | 4/10/2026 | Y | EXP | 365 | 07/24/2025 | 11/18/2025 | 118 | 0 | 118 |  |  | 12/1/2025 | Connected |  | N
National Grid | BOLTON | 177808 | 01740 | 7.6 | Solar | 05_12_7J903 | 10/12/2017 | 10/12/2017 | 8 | 0 | 8 | 10/25/2017 | 10/25/2017 | 86 | 0 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2017 |  | 10/18/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 186476 | 01501 | 15.04 | Solar | 05_14_43L4 | 06/04/2018 | 06/04/2018 | 0 | 0 | 0 | 06/05/2018 | 06/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 6/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2018 | Connected |  | N
National Grid | WEBSTER | 677063 | 01570 | 100 | Solar | 05_14_5J40 | 03/31/2025 | 05/06/2025 | 25 | 16 | 9 | 05/07/2025 | 05/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2025 |  | 3/28/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 3/6/2026 | Connected |  | N
National Grid | WINCHENDON | 580225 | 01475 | 5.8 | Solar | 05_14_74L3 | 01/11/2024 | 01/22/2024 | 7 | 6 | 1 | 01/23/2024 | 01/23/2024 | 88 | 71 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 01/11/2024 | 6/4/2025 | Y | EXP | 365 | 09/19/2024 | 11/06/2024 | 49 | 0 | 49 |  |  | 11/19/2024 | Connected |  | N
National Grid | WESTPORT | 659631 | 02790 | 27.55 | Solar | 05_01_216W6 | 12/16/2024 | 01/28/2025 | 28 | 26 | 2 | 01/29/2025 | 01/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 553735 | 01581 | 6.912 | Solar | 05_01_26W3 | 09/25/2023 | 10/12/2023 | 12 | 5 | 7 | 10/13/2023 | 10/13/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 09/25/2023 | 2/25/2025 | Y | EXP | 365 | 05/16/2024 | 06/11/2024 | 27 | 0 | 27 |  |  | 6/20/2024 | Connected |  | N
National Grid | LYNN | 605768 | 01905 | 6 | Solar | 05_01_412L6 | 04/24/2024 | 05/03/2024 | 3 | 0 | 3 | 05/06/2024 | 05/06/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/24/2024 | 5/20/2025 | Y | EXP | 365 | 09/06/2024 | 10/11/2024 | 36 | 0 | 36 |  |  | 10/18/2024 | Connected |  | N
National Grid | SAUGUS | 177058 | 01906 | 4500 | Solar | 05_01_607W1 | 01/17/2017 | 01/17/2017 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/09/2017 | 15 | 1 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/23/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 380699 | 01844 | 480 | Solar | 05_05_115W52 | 10/29/2021 | 12/15/2021 | 30 | 20 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 573242 | 01844 | 500 | Solar | 05_05_312W1 | 02/08/2024 | 05/15/2024 | 66 | 57 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2024 | 05/29/2024 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 632467 | 01841 | 3.8 | Solar | 05_12_29W1 | 08/15/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/15/2024 | 9/10/2025 | Y | EXP | 365 | 10/30/2024 | 04/14/2025 | 167 | 0 | 167 |  |  | 5/6/2025 | Connected |  | N
National Grid | BOLTON | 178676 | 01740 | 7.6 | Solar | 05_12_7J903 | 04/10/2018 | 04/10/2018 | 0 | 0 | 0 | 04/30/2018 | 04/30/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2018 |  | 1/8/2020 | N | EXP | 614 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 193103 | 01501 | 650 | Solar | 05_14_43L4 | 08/22/2018 | 10/25/2018 | 45 | 3 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 | 01/31/2019 | 62 | 26 | 36 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 692129 | 01570 | 11.52 | Solar | 05_14_5J41 | 05/29/2025 | 08/08/2025 | 1 | 0 | 1 | 08/18/2025 | 08/18/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WINCHENDON | 586831 | 01475 | 7.83 | Solar | 05_14_74L3 | 02/02/2024 | 02/06/2024 | 2 | 0 | 2 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/02/2024 | 7/24/2025 | Y | EXP | 465 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | FALL RIVER | 678256 | 02723 | 17.6 | Solar | 05_01_216W6 | 03/21/2025 | 03/26/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 | 03/21/2025 | 5/2/2026 | Y | EXP | 365 | 07/04/2025 | 11/17/2025 | 137 | 0 | 137 |  |  | 12/4/2025 | Connected |  | N
National Grid | WESTBOROUGH | 570140 | 01581 | 13.325 | Solar | 05_01_26W3 | 12/04/2023 | 12/07/2023 | 3 | 0 | 3 | 12/08/2023 | 12/08/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 | 12/04/2023 | 3/12/2025 | Y | EXP | 365 | 04/16/2024 | 07/12/2024 | 88 | 0 | 88 |  |  | 7/22/2024 | Connected |  | N
National Grid | LYNN | 633327 | 01904 | 5 | Solar | 05_01_412L6 | 08/19/2024 | 09/03/2024 | 2 | 1 | 1 | 09/04/2024 | 09/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/19/2024 | 11/6/2025 | Y | EXP | 365 | 11/19/2024 | 02/28/2025 | 102 | 0 | 102 |  |  | 3/27/2025 | Connected |  | N
National Grid | SAUGUS | 177090 | 01906 | 4500 | Solar | 05_01_607W1 | 01/17/2017 | 01/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/10/2017 | 16 | 1 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/24/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 454988 | 01844 | 6.96 | Solar | 05_05_115W52 | 11/16/2022 | 01/03/2023 | 29 | 25 | 4 | 01/04/2023 | 01/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2023 | 11/16/2022 | 6/25/2024 | Y | EXP | 365 | 03/29/2023 | 05/03/2023 | 36 | 0 | 36 |  |  | 7/20/2023 | Connected |  | N
National Grid | METHUEN | 591712 | 01844 | 8.96 | Solar | 05_05_312W1 | 02/27/2024 | 03/01/2024 | 3 | 1 | 2 | 03/04/2024 | 03/04/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 |  | 3/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | LAWRENCE | 641041 | 01841 | 7.6 | Solar | 05_12_29W1 | 11/08/2024 | 03/12/2025 | 10 | 7 | 3 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | BOLTON | 194313 | 01740 | 7.6 | Solar | 05_12_7J903 | 09/19/2018 | 10/12/2018 | 2 | 0 | 2 | 10/15/2018 | 10/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 | 09/19/2018 | 10/12/2020 | Y | EXP | 450 | 05/02/2019 | 05/14/2019 | 12 | 0 | 12 |  |  | 2/7/2020 | Connected |  | N
National Grid | AUBURN | 219512 | 01501 | 10 | Solar | 05_14_43L4 | 11/14/2019 | 11/20/2019 | 3 | 2 | 1 | 11/21/2019 | 11/21/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2019 |  | 7/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2021 | Connected |  | N
National Grid | WEBSTER | 742521 | 01570 | 150 | Solar | 05_14_5J41 | 12/31/2025 | 02/04/2026 | 22 | 13 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WINCHENDON | 597076 | 01475 | 8.12 | Solar | 05_14_74L3 | 03/22/2024 | 03/27/2024 | 3 | 0 | 3 | 03/28/2024 | 03/28/2024 | 26 | 25 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 699612 | 02790 | 15.2 | Solar | 05_01_216W6 | 06/25/2025 | 06/30/2025 | 10 | 7 | 3 | 07/14/2025 | 07/14/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2025 | Connected |  | N
National Grid | WESTBOROUGH | 588492 | 01581 | 9.135 | Solar | 05_01_26W3 | 02/23/2024 | 03/01/2024 | 5 | 1 | 4 | 03/04/2024 | 03/04/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/23/2024 | 4/18/2025 | Y | EXP | 365 | 05/02/2024 | 07/15/2024 | 75 | 0 | 75 |  |  | 8/23/2024 | Connected |  | N
National Grid | LYNN | 644967 | 01905 | 10 | Solar | 05_01_412L6 | 10/04/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/04/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | SAUGUS | 177393 | 01906 | 4950 | Solar | 05_01_607W1 | 02/17/2017 | 02/27/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2017 | 03/14/2017 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2017 | 02/17/2017 | 12/31/2020 | Y | STD | 838 | 12/12/2019 | 12/31/2020 | 385 | 5 | 380 | 12/30/2020 | 12/31/2020 | 12/31/2019 | Connected |  | N
National Grid | LAWRENCE | 465035 | 01841 | 4.06 | Solar | 05_05_115W52 | 09/30/2022 | 10/20/2022 | 13 | 12 | 1 | 10/21/2022 | 10/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  | 1/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2023 | Connected |  | N
National Grid | METHUEN | 596048 | 01844 | 15.2 | Solar | 05_05_312W1 | 03/12/2024 | 03/18/2024 | 4 | 0 | 4 | 03/19/2024 | 03/19/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | METHUEN | 642538 | 01844 | 7.54 | Solar | 05_12_29W1 | 09/24/2024 | 10/11/2024 | 3 | 0 | 3 | 10/15/2024 | 10/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 199443 | 01451 | 3.8 | Solar | 05_12_7J903 | 11/02/2018 | 11/29/2018 | 7 | 0 | 7 | 11/30/2018 | 11/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 |  | 1/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2019 | Connected |  | N
National Grid | AUBURN | 326326 | 01501 | 7.6 | Solar | 05_14_43L4 | 01/08/2021 | 01/11/2021 | 0 | 0 | 0 | 01/12/2021 | 01/12/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2021 | 01/08/2021 |  | Y | EXP | 365 | 05/25/2021 | 06/18/2021 | 24 | 0 | 24 |  |  | 8/27/2021 | Connected |  | N
National Grid | WEBSTER | 176466 | 01570 | 408 | Solar | 05_14_5J41 | 02/05/2016 | 02/05/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 210 | 0 | 210 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/13/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 607376 | 01440 | 7.6 | Solar | 05_14_74L3 | 04/30/2024 | 05/06/2024 | 1 | 0 | 1 | 05/07/2024 | 05/07/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 | 04/30/2024 | 6/4/2025 | Y | EXP | 365 | 07/31/2024 | 10/01/2024 | 63 | 0 | 63 |  |  | 10/8/2024 | Connected |  | N
National Grid | WESTPORT | 706361 | 02790 | 10 | Solar | 05_01_216W6 | 07/22/2025 | 08/06/2025 | 3 | 0 | 3 | 08/15/2025 | 08/15/2025 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2025 | Connected |  | N
National Grid | WESTBOROUGH | 614949 | 01581 | 10 | Solar | 05_01_26W3 | 06/04/2024 | 06/17/2024 | 4 | 0 | 4 | 06/18/2024 | 06/18/2024 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 | 06/04/2024 | 7/25/2025 | Y | EXP | 365 | 09/18/2024 | 10/21/2024 | 34 | 0 | 34 |  |  | 10/24/2024 | Connected |  | N
National Grid | LYNN | 661555 | 01904 | 5.76 | Solar | 05_01_412L6 | 12/18/2024 | 01/09/2025 | 5 | 0 | 5 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/18/2024 | 2/25/2026 | Y | EXP | 365 | 05/15/2025 | 05/14/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 177538 | 01906 | 4990 | Solar | 05_01_607W1 | 11/06/2017 | 12/15/2017 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2017 | 01/10/2018 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 473743 | 01844 | 10 | Solar | 05_05_115W52 | 12/20/2022 | 12/27/2022 | 4 | 2 | 2 | 12/28/2022 | 12/28/2022 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2023 | 12/20/2022 | 4/6/2024 | Y | EXP | 365 | 04/22/2023 | 05/25/2023 | 34 | 0 | 34 |  |  | 6/1/2023 | Connected |  | N
National Grid | METHUEN | 614675 | 01844 | 6 | Solar | 05_05_312W1 | 05/31/2024 | 06/06/2024 | 1 | 0 | 1 | 06/07/2024 | 06/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 05/31/2024 | 8/12/2025 | Y | EXP | 365 | 08/22/2024 | 09/10/2024 | 20 | 0 | 20 |  |  | 11/9/2024 | Connected |  | N
National Grid | METHUEN | 643215 | 01844 | 10 | Solar | 05_12_29W1 | 09/26/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/26/2024 | 11/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | BOLTON | 214350 | 01740 | 3.8 | Solar | 05_12_7J903 | 04/02/2019 | 04/09/2019 | 4 | 0 | 4 | 04/10/2019 | 04/10/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 347618 | 01540 | 6.09 | Solar | 05_14_43L4 | 04/15/2021 | 04/22/2021 | 3 | 1 | 2 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  | 4/22/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 418542 | 01570 | 7.6 | Solar | 05_14_5J41 | 03/21/2022 | 03/25/2022 | 4 | 0 | 4 | 03/28/2022 | 03/28/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2022 | 03/21/2022 | 5/27/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2022 | Connected |  | N
National Grid | GARDNER | 619623 | 01440 | 6 | Solar | 05_14_74L3 | 06/21/2024 | 07/02/2024 | 3 | 0 | 3 | 07/03/2024 | 07/03/2024 | 17 | 5 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 714691 | 02790 | 25 | Solar | 05_01_216W6 | 08/28/2025 | 09/09/2025 | 6 | 4 | 2 | 09/10/2025 | 09/10/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N
National Grid | WESTBOROUGH | 647810 | 01581 | 10 | Solar | 05_01_26W3 | 10/18/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 10/18/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | LYNN | 672975 | 01904 | 17.6 | Solar | 05_01_412L6 | 03/03/2025 | 03/14/2025 | 10 | 5 | 5 | 03/17/2025 | 03/17/2025 | 33 | 10 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 03/03/2025 | 6/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N
National Grid | SAUGUS | 177882 | 01906 | 3300 | Solar | 05_01_607W1 | 10/18/2017 | 12/21/2017 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 | 12/21/2017 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  | 10/24/2018 | N | STD | 43 | 10/10/2018 | 03/01/2019 | 142 | 0 | 142 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 523454 | 01844 | 10 | Solar | 05_05_115W52 | 06/05/2023 | 06/12/2023 | 5 | 4 | 1 | 06/13/2023 | 06/13/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 | 06/05/2023 | 7/16/2024 | Y | EXP | 365 | 08/16/2023 | 10/11/2023 | 57 | 0 | 57 |  |  | 10/16/2023 | Connected |  | N
National Grid | METHUEN | 654529 | 01844 | 7.6 | Solar | 05_05_312W1 | 11/15/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | LAWRENCE | 652674 | 01841 | 7.6 | Solar | 05_12_29W1 | 11/06/2024 | 12/04/2024 | 10 | 5 | 5 | 12/05/2024 | 12/05/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/06/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2025 | Connected |  | N
National Grid | BOLTON | 501622 | 01740 | 7.6 | Solar | 05_12_7J903 | 05/01/2023 | 05/04/2023 | 3 | 1 | 2 | 05/05/2023 | 05/05/2023 | 23 | 0 | 23 | 06/14/2023 | 09/18/2023 | 66 | 0 | 66 |  |  | 0 | 0 | 0 | 09/18/2023 | 66 | 0 | 66 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 10/27/2024 | N | EXP | 365 | 12/07/2023 | 12/06/2023 | 0 | 0 | 0 |  |  | 1/12/2024 | Connected |  | N
National Grid | OXFORD | 349417 | 01540 | 9.8 | Solar | 05_14_43L4 | 05/13/2021 | 05/21/2021 | 5 | 0 | 5 | 05/24/2021 | 05/24/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | WEBSTER | 456175 | 01570 | 5 | Solar | 05_14_5J41 | 10/11/2022 | 10/24/2022 | 10 | 9 | 1 | 10/25/2022 | 10/25/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/11/2022 | 1/6/2024 | Y | EXP | 365 | 03/15/2023 | 03/31/2023 | 17 | 0 | 17 |  |  | 4/3/2023 | Connected |  | N
National Grid | WINCHENDON | 627966 | 01475 | 5.22 | Solar | 05_14_74L3 | 07/26/2024 | 09/05/2024 | 19 | 18 | 1 | 09/06/2024 | 09/06/2024 | 37 | 31 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 720645 | 02790 | 11.78 | Solar | 05_01_216W6 | 09/21/2025 | 09/26/2025 | 5 | 0 | 5 | 09/29/2025 | 09/29/2025 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | WESTBOROUGH | 650772 | 01581 | 10 | Solar | 05_01_26W3 | 10/30/2024 | 11/11/2024 | 5 | 0 | 5 | 11/12/2024 | 11/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/30/2024 | 1/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | LYNN | 680767 | 01904 | 3.8 | Solar | 05_01_412L6 | 03/26/2025 | 04/16/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 177919 | 01906 | 3300 | Solar | 05_01_607W1 | 10/23/2017 | 10/23/2017 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 |  | 100 | 0 | 100 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 560606 | 01841 | 15.08 | Solar | 05_05_115W52 | 10/05/2023 | 10/09/2023 | 2 | 0 | 2 | 10/10/2023 | 10/10/2023 | 63 | 41 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  | 3/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2024 | Connected |  | N
National Grid | METHUEN | 660757 | 01844 | 8.45 | Solar | 05_05_312W1 | 12/31/2024 | 01/15/2025 | 7 | 1 | 6 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/31/2024 | 3/4/2026 | Y | EXP | 365 | 06/12/2025 | 08/06/2025 | 56 | 0 | 56 |  |  | 8/14/2025 | Connected |  | N
National Grid | LAWRENCE | 653618 | 01841 | 4.56 | Solar | 05_12_29W1 | 11/12/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 519264 | 01451 | 3.8 | Solar | 05_12_7J903 | 05/03/2023 | 05/08/2023 | 3 | 0 | 3 | 05/09/2023 | 05/09/2023 | 21 | 0 | 21 | 06/14/2023 | 09/15/2023 | 65 | 0 | 65 |  |  | 0 | 0 | 0 | 09/15/2023 | 65 | 0 | 65 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 10/22/2024 | N | EXP | 365 | 01/03/2024 | 01/09/2024 | 7 | 0 | 7 |  |  | 1/13/2024 | Connected |  | N
National Grid | AUBURN | 373213 | 01501 | 10 | Solar | 05_14_43L4 | 09/10/2021 | 01/06/2022 | 3 | 0 | 3 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2021 | 09/10/2021 | 7/27/2023 | Y | EXP | 365 | 06/09/2022 | 06/08/2022 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 592556 | 01570 | 3.8 | Solar | 05_14_5J41 | 03/01/2024 | 04/18/2024 | 33 | 32 | 1 | 04/19/2024 | 04/19/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2024 |  | 5/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | GARDNER | 636115 | 01440 | 6 | Solar | 05_14_74L3 | 08/28/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 736348 | 02790 | 7.6 | Solar | 05_01_216W6 | 11/25/2025 | 12/10/2025 | 10 | 7 | 3 | 12/11/2025 | 12/11/2025 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 674775 | 01581 | 5.76 | Solar | 05_01_26W3 | 02/27/2025 | 03/18/2025 | 2 | 0 | 2 | 03/19/2025 | 03/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 | 02/27/2025 | 4/18/2026 | Y | EXP | 365 | 10/28/2025 | 10/27/2025 | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | LYNN | 687053 | 01904 | 3.8 | Solar | 05_01_412L6 | 04/23/2025 | 07/09/2025 | 52 | 48 | 4 | 07/10/2025 | 07/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | SAUGUS | 177998 | 01906 | 660 | Solar | 05_01_607W1 | 10/25/2017 | 01/05/2018 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/19/2018 | 25 | 16 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 583847 | 01844 | 480 | Solar | 05_05_115W52 | 02/22/2024 | 05/22/2024 | 63 | 53 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2024 | 06/04/2024 | 8 | 0 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 676389 | 01844 | 5.76 | Solar | 05_05_312W1 | 03/07/2025 | 03/27/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 85 | 75 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 655690 | 01841 | 6 | Solar | 05_12_29W1 | 11/20/2024 | 12/26/2024 | 7 | 3 | 4 | 12/27/2024 | 12/27/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | HARVARD | 562325 | 01451 | 3.8 | Solar | 05_12_7J903 | 10/24/2023 | 10/25/2023 | 1 | 0 | 1 | 10/26/2023 | 10/26/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2023 |  | 11/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2024 | Connected |  | N
National Grid | MILLBURY | 378603 | 01527 | 9.8 | Solar | 05_14_43L4 | 09/10/2021 | 01/03/2022 | 3 | 2 | 1 | 09/15/2021 | 09/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 606739 | 01570 | 10 | Solar | 05_14_5J41 | 04/25/2024 | 05/03/2024 | 1 | 0 | 1 | 05/06/2024 | 05/06/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 | 04/25/2024 | 5/30/2025 | Y | EXP | 365 | 07/31/2024 | 09/28/2024 | 60 | 0 | 60 |  |  | 10/12/2024 | Connected |  | N
National Grid | WINCHENDON | 636493 | 01475 | 5.22 | Solar | 05_14_74L3 | 08/29/2024 | 12/12/2024 | 21 | 19 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 178695 | 02723 | 500 | Solar | 05_01_219W1 | 02/06/2018 | 02/06/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 06/21/2018 | 07/19/2018 | 19 | 0 | 19 | 03/05/2018 | 04/11/2018 | 28 | 8 | 20 | 07/19/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 7/25/2018 |  | 11/1/2019 | N | STD | 464 |  |  | 0 | 0 | 0 |  |  | 12/23/2019 | Connected |  | N
National Grid | WESTBOROUGH | 683563 | 01581 | 13.8 | Solar | 05_01_26W3 | 04/16/2025 | 08/29/2025 | 29 | 24 | 5 | 09/02/2025 | 09/02/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 | 04/16/2025 | 10/20/2026 | Y | EXP | 365 | 02/04/2026 | 02/11/2026 | 8 | 0 | 8 |  |  | 2/13/2026 | Connected |  | N
National Grid | LYNN | 466552 | 01904 | 250 | Solar | 05_01_413L1 | 10/21/2022 | 11/07/2022 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2022 | 12/05/2022 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SAUGUS | 178113 | 01906 | 4990 | Solar | 05_01_607W1 | 11/06/2017 | 12/12/2017 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/10/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 598026 | 01844 | 2.9 | Solar | 05_05_115W52 | 04/11/2024 | 05/01/2024 | 13 | 10 | 3 | 05/02/2024 | 05/02/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 | 04/11/2024 | 5/20/2025 | Y | EXP | 365 | 07/03/2024 | 08/08/2024 | 37 | 0 | 37 |  |  | 9/28/2024 | Connected |  | N
National Grid | METHUEN | 739032 | 01844 | 0 | Battery Add-On | 05_05_312W1 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2026 | Connected |  | N
National Grid | LAWRENCE | 688867 | 01841 | 11.4 | Solar | 05_12_29W1 | 05/01/2025 | 06/18/2025 | 13 | 8 | 5 | 06/20/2025 | 06/20/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/01/2025 | 7/28/2026 | Y | EXP | 365 | 08/21/2025 | 10/29/2025 | 70 | 0 | 70 |  |  | 11/5/2025 | Connected |  | N
National Grid | LEOMINSTER | 587947 | 01453 | 3.8 | Solar | 05_12_7J903 | 02/10/2024 | 02/12/2024 | 1 | 0 | 1 | 02/13/2024 | 02/13/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 2/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | AUBURN | 381715 | 01501 | 11.04 | Solar | 05_14_43L4 | 09/16/2021 | 09/20/2021 | 2 | 0 | 2 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 607882 | 01550 | 7.6 | Solar | 05_14_5J41 | 05/01/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 05/01/2024 | 4/22/2026 | Y | EXP | 365 | 05/16/2025 | 09/15/2025 | 123 | 0 | 123 |  |  | 10/17/2025 | Connected |  | N
National Grid | GARDNER | 636179 | 01440 | 10 | Solar | 05_14_74L3 | 08/28/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  | 11/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2024 | Connected |  | N
National Grid | FALL RIVER | 340774 | 02721 | 25.52 | Solar | 05_01_219W1 | 02/09/2021 | 04/19/2021 | 47 | 46 | 1 | 04/20/2021 | 04/20/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2021 | Connected |  | N
National Grid | WESTBOROUGH | 707156 | 01581 | 11.31 | Solar | 05_01_26W3 | 07/24/2025 | 07/28/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | LYNN | 643826 | 01904 | 5.76 | Solar | 05_01_413L1 | 09/30/2024 | 10/11/2024 | 5 | 1 | 4 | 10/15/2024 | 10/15/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/30/2024 | 7/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 178530 | 01906 | 1250 | Solar | 05_01_607W1 | 12/04/2017 | 12/04/2017 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/01/2018 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/10/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 601783 | 01844 | 0 | Solar | 05_05_115W52 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 419359 | 01844 | 499 | Solar | 05_05_312W2 | 05/26/2022 | 06/14/2022 | 12 | 7 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/15/2022 | 07/18/2022 | 22 | 2 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 05/26/2022 | 8/12/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | METHUEN | 691976 | 01844 | 5.12 | Solar | 05_12_29W1 | 05/15/2025 | 06/18/2025 | 5 | 1 | 4 | 07/03/2025 | 07/03/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 05/15/2025 | 10/10/2026 | Y | EXP | 365 | 10/07/2025 | 10/17/2025 | 11 | 0 | 11 |  |  | 11/25/2025 | Connected |  | N
National Grid | LEOMINSTER | 174990 | 01453 | 75 | Diesel | 05_12_7W1 | 03/06/2013 | 03/06/2013 | 5 | 0 | 5 | 03/18/2013 | 03/18/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2013 |  | 6/28/2013 | N | EXP | 70 |  |  | 0 | 0 | 0 | 9/13/2013 | 9/13/2013 | 9/17/2013 | Connected |  | N
National Grid | AUBURN | 390053 | 01501 | 7.6 | Solar | 05_14_43L4 | 10/26/2021 | 11/02/2021 | 5 | 0 | 5 | 11/03/2021 | 11/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 | 10/26/2021 | 2/7/2023 | Y | EXP | 365 | 01/19/2022 | 02/07/2022 | 20 | 0 | 20 |  |  | 2/15/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 617581 | 01550 | 3.8 | Solar | 05_14_5J41 | 06/12/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 06/12/2024 | 7/19/2025 | Y | EXP | 365 | 11/13/2024 | 11/26/2024 | 14 | 0 | 14 |  |  | 12/6/2024 | Connected |  | N
National Grid | WINCHENDON | 639000 | 01475 | 9.28 | Solar | 05_14_74L3 | 09/10/2024 | 10/08/2024 | 11 | 10 | 1 | 10/09/2024 | 10/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 427478 | 02790 | 0 | Other | 05_01_219W1 | 07/13/2022 | 08/16/2022 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2022 | 09/14/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 711413 | 01581 | 15.2 | Solar | 05_01_26W3 | 08/12/2025 | 08/13/2025 | 1 | 0 | 1 | 08/14/2025 | 08/14/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 | 08/12/2025 | 10/10/2026 | Y | EXP | 365 | 02/03/2026 | 02/05/2026 | 3 | 0 | 3 |  |  | 3/4/2026 | Connected |  | N
National Grid | LYNN | 661362 | 01904 | 5.76 | Solar | 05_01_413L1 | 12/18/2024 | 01/03/2025 | 4 | 2 | 2 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/18/2024 | 4/20/2026 | Y | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 178646 | 02151 | 4980 | Solar | 05_01_607W1 | 12/15/2017 | 09/07/2018 | 75 | 51 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2018 | 05/29/2018 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 603266 | 01844 | 4.06 | Solar | 05_05_115W52 | 04/11/2024 | 05/10/2024 | 8 | 3 | 5 | 05/13/2024 | 05/13/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 |  | 8/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2024 | Connected |  | N
National Grid | METHUEN | 561576 | 01844 | 1980 | Solar | 05_05_312W2 | 05/15/2024 | 06/13/2024 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/14/2024 | 07/12/2024 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LAWRENCE | 731709 | 01841 | 3.8 | Solar | 05_12_29W1 | 11/05/2025 | 11/19/2025 | 1 | 0 | 1 | 12/12/2025 | 12/12/2025 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 177794 | 01453 | 7.6 | Solar | 05_12_7W1 | 08/02/2017 | 08/02/2017 | 4 | 0 | 4 | 08/09/2017 | 08/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2017 |  | 8/8/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  | 8/1/2018 | Connected |  | N
National Grid | AUBURN | 395186 | 01501 | 6 | Solar | 05_14_43L4 | 11/18/2021 | 01/06/2022 | 2 | 0 | 2 | 11/23/2021 | 11/23/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/18/2021 | 6/16/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2022 | Connected |  | Y
National Grid | SOUTHBRIDGE | 618583 | 01550 | 10 | Solar | 05_14_5J41 | 06/17/2024 | 07/09/2024 | 4 | 0 | 4 | 07/10/2024 | 07/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 639679 | 01475 | 5.856 | Solar | 05_14_74L3 | 09/12/2024 | 10/04/2024 | 8 | 2 | 6 | 10/07/2024 | 10/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/12/2024 | 11/14/2025 | Y | EXP | 365 | 01/30/2025 | 04/24/2025 | 85 | 0 | 85 |  |  | 4/28/2025 | Connected |  | N
National Grid | FALL RIVER | 701156 | 02721 | 6 | Solar | 05_01_219W1 | 06/25/2025 | 07/23/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/25/2025 | 9/25/2026 | Y | EXP | 365 | 09/20/2025 | 09/19/2025 | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | WESTBOROUGH | 722655 | 01581 | 10 | Solar | 05_01_26W4 | 09/29/2025 | 10/02/2025 | 3 | 0 | 3 | 10/03/2025 | 10/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | LYNN | 739089 | 01905 | 20 | Solar | 05_01_413L1 | 12/10/2025 | 12/15/2025 | 3 | 0 | 3 | 12/16/2025 | 12/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 | 12/10/2025 | 3/18/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | REVERE | 647197 | 02151 | 7.6 | Solar | 05_05_115W52 | 10/17/2024 | 10/29/2024 | 2 | 0 | 2 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 12/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | METHUEN | 602516 | 01844 | 999 | Solar | 05_05_312W2 | 05/09/2024 | 08/01/2024 | 57 | 47 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2024 | 08/12/2024 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 742453 | 01844 | 17.16 | Solar | 05_12_29W1 | 12/29/2025 | 12/31/2025 | 2 | 0 | 2 | 01/02/2026 | 01/02/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 394618 | 01841 | 28.8 | Solar | 05_12_7W1 | 01/13/2022 | 01/26/2022 | 9 | 7 | 2 | 01/27/2022 | 01/27/2022 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  | 3/18/2024 | N | EXP | 700 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | LEOMINSTER | 401101 | 01453 | 0 | Other | 05_14_43L4 | 01/06/2022 | 01/19/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2022 | 03/02/2022 | 29 | 15 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 625945 | 01501 | 15.2 | Solar | 05_14_5J41 | 07/18/2024 | 07/24/2024 | 4 | 0 | 4 | 07/25/2024 | 07/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/18/2024 | 12/9/2025 | Y | EXP | 365 | 01/25/2025 | 03/04/2025 | 39 | 0 | 39 |  |  | 6/21/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 643551 | 01550 | 10 | Solar | 05_14_74L3 | 09/27/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/27/2024 | 11/20/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | WINCHENDON | 682588 | 01475 | 11.866 | Solar | 05_01_219W2 | 04/10/2025 | 06/26/2025 | 7 | 3 | 4 | 07/15/2025 | 07/15/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | FALL RIVER | 347070 | 02720 | 26 | Solar | 05_01_27W1 | 03/31/2022 | 04/11/2022 | 7 | 0 | 7 | 04/12/2022 | 04/12/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/11/2026 | N | EXP | 10 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 745492 | 01581 | 7.6 | Solar | 05_01_413L1 | 01/15/2026 | 01/30/2026 | 5 | 2 | 3 | 02/24/2026 | 02/24/2026 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 195209 | 01904 | 8290 | Solar | 05_01_607W1 | 10/22/2018 | 10/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 | 12/06/2018 | 30 | 11 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 677831 | 02151 | 5.76 | Solar | 05_05_115W52 | 03/13/2025 | 03/25/2025 | 8 | 4 | 4 | 03/26/2025 | 03/26/2025 | 56 | 38 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 03/13/2025 | 6/30/2026 | Y | EXP | 365 | 08/23/2025 | 10/01/2025 | 40 | 0 | 40 |  |  | 10/13/2025 | Connected |  | N
National Grid | METHUEN | 590683 | 01844 | 499 | Solar | 05_05_312W2 | 07/08/2024 | 08/26/2024 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2024 | 10/03/2024 | 28 | 23 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 605829 | 01844 | 484.6 | Solar | 05_12_29W2 | 05/13/2024 | 07/02/2024 | 34 | 26 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2024 | 07/16/2024 | 9 | 2 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 05/13/2024 | 5/15/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | LAWRENCE | 616872 | 01841 | 7.6 | Solar | 05_12_7W1 | 06/11/2024 | 06/20/2024 | 3 | 0 | 3 | 06/21/2024 | 06/21/2024 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | LEOMINSTER | 435737 | 01453 | 15.2 | Solar | 05_14_43L4 | 06/06/2022 | 06/16/2022 | 9 | 8 | 1 | 06/17/2022 | 06/17/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2022 | Connected |  | N
National Grid | WORCESTER | 637475 | 01604 | 7.6 | Solar | 05_14_5J41 | 09/09/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 | 09/09/2024 | 11/20/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 646410 | 01550 | 11.4 | Solar | 05_14_74L3 | 10/17/2024 | 11/12/2024 | 14 | 11 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 2/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | GARDNER | 717728 | 01440 | 3.8 | Solar | 05_01_219W2 | 09/09/2025 | 09/23/2025 | 4 | 0 | 4 | 10/03/2025 | 10/03/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 | 09/09/2025 | 12/1/2026 | Y | EXP | 365 | 02/19/2026 |  | 42 | 0 | 42 |  |  |  | Construction |  | N
National Grid | WESTPORT | 665454 | 02790 | 60 | Solar | 05_01_27W1 | 02/10/2025 | 03/26/2025 | 31 | 22 | 9 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/23/2026 | N | EXP | 120 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | N
National Grid | WESTBOROUGH | 751787 | 01581 | 11.52 | Solar | 05_01_413L1 | 02/18/2026 | 02/24/2026 | 4 | 1 | 3 | 02/25/2026 | 02/25/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2026 |  | 3/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 261017 | 01970 | 10 | Solar | 05_01_607W1 | 11/20/2019 | 11/26/2019 | 3 | 0 | 3 | 11/27/2019 | 11/27/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 |  | 11/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 680103 | 02151 | 7.6 | Solar | 05_05_115W52 | 03/24/2025 | 04/23/2025 | 5 | 0 | 5 | 04/24/2025 | 04/24/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 737811 | 01844 | 480 | Solar | 05_05_312W2 | 02/05/2026 |  | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | METHUEN | 605827 | 01844 | 250 | Solar | 05_12_29W2 | 05/13/2024 | 07/15/2024 | 42 | 33 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/16/2024 | 07/16/2024 | 1 | 0 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 05/13/2024 | 5/15/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | METHUEN | 648905 | 01844 | 7.68 | Solar | 05_12_7W1 | 10/22/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | LEOMINSTER | 470911 | 01453 | 10 | Solar | 05_14_43L4 | 11/17/2022 |  | 162 | 50 | 112 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 646096 | 01604 | 11.02 | Solar | 05_14_5J41 | 10/22/2024 | 11/26/2024 | 11 | 7 | 4 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 | 10/22/2024 | 2/5/2026 | Y | EXP | 365 | 04/15/2025 | 07/11/2025 | 88 | 0 | 88 |  |  | 7/18/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 649008 | 01550 | 10 | Solar | 05_14_74L3 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | GARDNER | 733103 | 01440 | 10 | Solar | 05_01_219W2 | 11/12/2025 | 12/26/2025 | 2 | 0 | 2 | 12/29/2025 | 12/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 739521 | 02721 | 5.76 | Solar | 05_01_27W1 | 12/11/2025 | 02/06/2026 | 7 | 5 | 2 | 02/09/2026 | 02/09/2026 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTBOROUGH | 175324 | 01581 | 262.8 | Solar | 05_01_413L1 | 11/07/2014 | 11/07/2014 | 6 | 0 | 6 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2014 |  | 3/31/2015 | N | EXP | 105 |  |  | 0 | 0 | 0 | 10/20/2015 | 10/20/2015 | 10/21/2015 | Connected |  | N
National Grid | SALEM | 355755 | 01970 | 10 | Solar | 05_01_607W1 | 06/07/2021 | 06/15/2021 | 6 | 0 | 6 | 06/16/2021 | 06/16/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 685905 | 02151 | 7.6 | Solar | 05_05_115W52 | 04/17/2025 | 07/08/2025 | 9 | 7 | 2 | 07/24/2025 | 07/24/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2026 | Connected |  | N
National Grid | LAWRENCE | 174332 | 01841 | 300 | Solar | 05_05_312W2 | 01/18/2012 | 01/18/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2012 | 01/18/2012 | 7/1/2012 | Y | EXP | 59 | 09/25/2012 | 11/29/2012 | 29 | 0 | 29 | 1/22/2013 | 1/22/2013 | 2/6/2013 | Connected |  | N
National Grid | METHUEN | 177353 | 01844 | 3.8 | Solar | 05_12_29W2 | 02/15/2017 | 02/15/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2017 | 02/15/2017 | 7/17/2019 | Y | EXP | 870 | 05/24/2018 | 05/24/2018 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 666990 | 01841 | 3.2 | Solar | 05_12_7W1 | 01/21/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 | 01/21/2025 | 5/16/2026 | Y | EXP | 365 | 08/08/2025 | 11/21/2025 | 106 | 0 | 106 |  |  | 12/1/2025 | Connected |  | N
National Grid | LEOMINSTER | 479994 | 01453 | 7.6 | Solar | 05_14_43L4 | 12/19/2022 | 12/26/2022 | 5 | 0 | 5 | 12/27/2022 | 12/27/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 662588 | 01604 | 10 | Solar | 05_14_5J41 | 01/03/2025 | 01/21/2025 | 5 | 2 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 650775 | 01550 | 10 | Solar | 05_14_74L3 | 11/11/2024 | 11/21/2024 | 2 | 0 | 2 | 11/22/2024 | 11/22/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 746248 | 01440 | 5.76 | Solar | 05_01_219W2 | 01/20/2026 | 01/22/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTPORT | 174418 | 02790 | 110 | Solar | 05_01_27W1 | 10/20/2011 | 10/20/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2011 | 10/20/2011 | 5/4/2012 | Y | EXP | 137 | 03/12/2012 | 04/12/2012 | 22 | 0 | 22 | 1/25/2013 | 1/25/2013 | 5/4/2012 | Connected |  | N
National Grid | NORTHBOROUGH | 176176 | 01532 | 1000 | Solar | 05_01_413L1 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/03/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2015 | 07/02/2015 | 7/11/2016 | Y | STD | 201 | 08/04/2017 | 09/20/2017 | 32 | 0 | 32 | 10/16/2017 | 10/16/2017 | 10/13/2015 | Connected |  | N
National Grid | SALEM | 450860 | 01970 | 5 | Solar | 05_01_607W1 | 10/11/2022 | 11/18/2022 | 27 | 24 | 3 | 11/21/2022 | 11/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/25/2022 | 10/11/2022 | 9/20/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2023 | Connected |  | N
National Grid | REVERE | 694610 | 02151 | 15.96 | Solar | 05_05_115W52 | 06/23/2025 | 07/28/2025 | 23 | 22 | 1 | 07/29/2025 | 07/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | METHUEN | 175072 | 01844 | 95 | Solar | 05_05_312W2 | 11/21/2012 | 11/21/2012 | 9 | 0 | 9 | 12/07/2012 | 12/07/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 |  | 5/31/2013 | N | EXP | 78 |  |  | 0 | 0 | 0 | 3/21/2013 | 3/21/2013 | 4/16/2013 | Connected |  | N
National Grid | METHUEN | 196948 | 01844 | 8.64 | Solar | 05_12_29W2 | 09/25/2018 | 10/17/2018 | 13 | 7 | 6 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 683414 | 01844 | 14.95 | Solar | 05_12_7W1 | 04/23/2025 | 05/23/2025 | 4 | 0 | 4 | 06/12/2025 | 06/12/2025 | 68 | 24 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 486205 | 01453 | 7.6 | Solar | 05_14_43L4 | 12/27/2022 | 12/29/2022 | 2 | 0 | 2 | 12/30/2022 | 12/30/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2023 | Connected |  | N
National Grid | WORCESTER | 688562 | 01604 | 5.76 | Solar | 05_14_5J41 | 04/30/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 657183 | 01550 | 5.76 | Solar | 05_14_74L3 | 11/26/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 745876 | 01440 | 11.5 | Battery Add-On | 05_01_219W2 | 01/16/2026 | 01/22/2026 | 3 | 0 | 3 | 02/18/2026 | 02/18/2026 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTPORT | 175075 | 02790 | 75 | Solar | 05_01_27W1 | 09/23/2013 | 09/23/2013 | 6 | 0 | 6 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2013 |  | 11/10/2016 | N | EXP | 1122 |  |  | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 12/15/2016 | Connected |  | N
National Grid | WESTBOROUGH | 177030 | 01581 | 224 | Solar | 05_01_413L1 | 03/19/2017 | 03/19/2017 | 69 | 68 | 1 | 06/27/2017 | 06/27/2017 | 0 | 0 | 0 | 12/07/2017 | 01/04/2018 | 106 | 0 | 106 |  |  | 0 | 0 | 0 | 01/04/2018 | 106 | 0 | 106 |  |  | 0 | 0 | 0 | 9/14/2017 |  | 3/30/2018 | N | EXP | 197 |  |  | 0 | 0 | 0 | 3/14/2018 | 3/14/2018 | 3/14/2018 | Connected |  | N
National Grid | SALEM | 372586 | 01970 | 9.8 | Solar | 05_01_607W1 | 08/04/2021 | 08/05/2021 | 1 | 0 | 1 | 08/06/2021 | 08/06/2021 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 | 08/04/2021 | 11/24/2022 | Y | EXP | 365 | 10/15/2021 | 11/23/2021 | 40 | 4 | 36 |  |  | 12/1/2021 | Connected |  | Y
National Grid | REVERE | 700073 | 02151 | 17.6 | Solar | 05_05_115W52 | 08/04/2025 | 08/06/2025 | 2 | 0 | 2 | 08/07/2025 | 08/07/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2025 | Connected |  | N
National Grid | METHUEN | 175174 | 01844 | 95 | Solar | 05_05_312W2 | 11/21/2012 | 11/21/2012 | 9 | 0 | 9 | 12/07/2012 | 12/07/2012 | 74 | 3 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 |  | 2/28/2013 | N | EXP | 14 |  |  | 0 | 0 | 0 | 3/21/2013 | 3/21/2013 |  | Withdrawn |  | Y
National Grid | METHUEN | 208985 | 01844 | 7.6 | Solar | 05_12_29W2 | 03/15/2019 | 03/18/2019 | 1 | 1 | 0 | 03/19/2019 | 03/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2019 | 03/15/2019 | 2/21/2020 | Y | EXP | 337 | 08/16/2019 | 10/02/2019 | 47 | 0 | 47 |  |  | 10/31/2019 | Connected |  | N
National Grid | LAWRENCE | 744816 | 01844 | 5.76 | Solar | 05_12_7W2 | 01/14/2026 | 01/20/2026 | 7 | 5 | 2 | 02/11/2026 | 02/11/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2026 | 01/14/2026 | 3/17/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LEOMINSTER | 489999 | 01453 | 10 | Solar | 05_14_43L4 | 02/10/2023 |  | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178227 | 01604 | 7.6 | Solar | 05_14_5J42 | 01/03/2018 | 01/03/2018 | 15 | 9 | 6 | 01/29/2018 | 01/29/2018 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 1/10/2019 | N | EXP | 345 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 657165 | 01550 | 5.76 | Solar | 05_14_74L3 | 11/26/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/26/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 174697 | 01440 | 2000 | Solar | 05_01_219W2 | 12/31/2012 | 12/31/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2013 | 03/20/2013 | 39 | 0 | 39 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2014 | 12/31/2012 | 1/31/2014 | Y | STD | 67 | 12/26/2014 | 04/14/2015 | 73 | 0 | 73 | 4/9/2015 | 4/9/2015 | 4/9/2015 | Connected |  | N
National Grid | WESTPORT | 175074 | 02790 | 100 | Solar | 05_01_27W1 | 09/23/2013 | 09/23/2013 | 6 | 0 | 6 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2013 |  | 12/5/2016 | N | EXP | 1119 |  |  | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 12/6/2016 | Connected |  | N
National Grid | WESTBOROUGH | 178353 | 01581 | 5 | Solar | 05_01_413L1 | 02/27/2018 | 02/27/2018 | 2 | 2 | 0 | 03/06/2018 | 03/06/2018 | 239 | 0 | 239 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 |  | 3/5/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 9/12/2018 | Connected |  | N
National Grid | SALEM | 389904 | 01970 | 9.57 | Solar | 05_01_607W1 | 10/26/2021 | 12/16/2021 | 2 | 2 | 0 | 10/29/2021 | 10/29/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 | 10/26/2021 | 5/26/2023 | Y | EXP | 365 | 04/27/2022 | 05/04/2022 | 8 | 0 | 8 |  |  | 6/29/2022 | Connected |  | N
National Grid | REVERE | 720034 | 02151 | 11.4 | Solar | 05_05_115W52 | 09/18/2025 | 10/03/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 26 | 13 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | METHUEN | 175204 | 01844 | 1800 | Solar | 05_05_312W2 | 12/06/2012 | 12/06/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2012 | 03/21/2013 | 54 | 0 | 54 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 216823 | 01844 | 3.8 | Solar | 05_12_29W2 | 04/02/2019 | 04/23/2019 | 14 | 10 | 4 | 04/24/2019 | 04/24/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2019 | Connected |  | N
National Grid | LAWRENCE | 744515 | 01841 | 7.6 | Solar | 05_12_7W2 | 01/14/2026 | 01/15/2026 | 19 | 16 | 3 | 02/25/2026 | 02/25/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2026 |  | 4/1/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 491242 | 01453 | 7.83 | Solar | 05_14_43L4 | 01/20/2023 | 01/25/2023 | 3 | 1 | 2 | 01/26/2023 | 01/26/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 | 01/20/2023 | 8/3/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2023 | Connected |  | N
National Grid | WORCESTER | 178338 | 01604 | 5 | Solar | 05_14_5J42 | 11/17/2017 | 11/17/2017 | 48 | 47 | 1 | 01/31/2018 | 01/31/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 |  | 11/25/2018 | N | EXP | 298 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 657640 | 01550 | 9.1 | Solar | 05_14_74L3 | 12/11/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | GARDNER | 175935 | 01440 | 10 | Solar | 05_01_219W2 | 08/06/2015 | 08/06/2015 | 4 | 2 | 2 | 08/12/2015 | 08/12/2015 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 |  | Withdrawn |  | N
National Grid | WESTPORT | 189268 | 02790 | 15.2 | Solar | 05_01_27W1 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 06/26/2018 | 10/13/2019 | Y | EXP | 500 | 05/02/2020 | 05/01/2020 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 184817 | 01581 | 478 | Solar | 05_01_413L1 | 01/04/2019 | 01/08/2019 | 1 | 0 | 1 |  |  | 52 | 27 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 389245 | 01970 | 3.84 | Solar | 05_01_607W1 | 12/15/2021 | 01/07/2022 | 2 | 0 | 2 | 12/20/2021 | 12/20/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 742764 | 02151 | 5.76 | Solar | 05_05_115W53 | 12/30/2025 | 12/31/2025 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 | 12/30/2025 | 2/11/2027 | Y | EXP | 365 | 03/04/2026 | 03/30/2026 | 27 | 0 | 27 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 175259 | 01844 | 138 | Solar | 05_05_312W2 | 01/07/2015 | 01/07/2015 | 4 | 0 | 4 | 01/14/2015 | 01/14/2015 | 0 | 0 | 0 | 03/11/2015 | 06/23/2015 | 70 | 30 | 40 |  |  | 0 | 0 | 0 | 06/23/2015 | 70 | 30 | 40 |  |  | 0 | 0 | 0 | 11/2/2015 |  | 12/31/2016 | N | EXP | 425 |  |  | 0 | 0 | 0 | 11/2/2015 | 11/2/2015 | 6/21/2017 | Connected |  | N
National Grid | METHUEN | 228309 | 01844 | 10 | Solar | 05_12_29W2 | 05/15/2019 | 05/22/2019 | 4 | 3 | 1 | 05/23/2019 | 05/23/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2019 |  | 7/30/2019 | N | EXP | 55 |  |  | 0 | 0 | 0 |  |  | 7/25/2019 | Connected |  | N
National Grid | LAWRENCE | 745715 | 01841 | 15.76 | Solar | 05_12_7W2 | 01/20/2026 | 01/27/2026 | 5 | 0 | 5 | 01/28/2026 | 01/28/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 | 01/20/2026 | 3/5/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LEOMINSTER | 512389 | 01453 | 9.86 | Solar | 05_14_43L4 | 05/10/2023 | 05/15/2023 | 3 | 0 | 3 | 05/16/2023 | 05/16/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 320041 | 01604 | 9.8 | Solar | 05_14_5J42 | 11/30/2020 | 12/03/2020 | 2 | 0 | 2 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 | 11/30/2020 | 9/3/2022 | Y | EXP | 365 | 08/19/2021 | 10/12/2021 | 40 | 3 | 37 |  |  | 6/2/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 663368 | 01550 | 8.96 | Solar | 05_14_74L3 | 01/02/2025 | 02/10/2025 | 16 | 12 | 4 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | GARDNER | 176076 | 01440 | 10 | Solar | 05_01_219W2 | 08/20/2015 | 08/20/2015 | 0 | 0 | 0 | 08/20/2015 | 08/20/2015 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 8/25/2016 | N | EXP | 350 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 197109 | 02721 | 7.6 | Solar | 05_01_27W1 | 09/27/2018 | 10/18/2018 | 4 | 3 | 1 | 10/19/2018 | 10/19/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 |  | 8/30/2019 | N | EXP | 247 |  |  | 0 | 0 | 0 |  |  | 7/26/2019 | Connected |  | N
National Grid | WESTBOROUGH | 193984 | 01581 | 72 | Solar | 05_01_413L1 | 10/23/2018 | 10/25/2018 | 178 | 28 | 150 | 12/14/2018 | 12/14/2018 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 395576 | 01970 | 20.355 | Solar | 05_01_607W1 | 11/17/2021 | 12/22/2021 | 2 | 0 | 2 | 11/19/2021 | 11/19/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 |  | 2/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2022 | Connected |  | N
National Grid | REVERE | 177926 | 02151 | 7.6 | Solar | 05_05_115W53 | 04/18/2017 | 04/18/2017 | 4 | 4 | 0 | 04/24/2017 | 04/24/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2017 |  | 4/23/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 10/26/2017 | 10/26/2017 | 10/26/2017 | Connected |  | N
National Grid | METHUEN | 175377 | 01844 | 368 | Solar | 05_05_312W2 | 07/09/2014 | 07/09/2014 | 1 | 0 | 1 | 07/10/2014 | 07/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2014 |  | 11/28/2014 | N | EXP | 122 |  |  | 0 | 0 | 0 | 12/15/2014 | 12/15/2014 | 12/31/2014 | Connected |  | N
National Grid | METHUEN | 230204 | 01844 | 0 | Solar | 05_12_29W2 | 05/22/2019 | 05/30/2019 | 4 | 0 | 4 | 05/31/2019 | 05/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2019 | Connected |  | N
National Grid | LAWRENCE | 176039 | 01841 | 2.58 | Solar | 05_12_7W2 | 08/13/2015 | 08/13/2015 | 2 | 2 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 8/19/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 5/12/2016 | 5/12/2016 | 6/27/2016 | Connected |  | N
National Grid | LEOMINSTER | 521781 | 01453 | 11.04 | Solar | 05_14_43L4 | 04/27/2023 |  | 136 | 135 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 558417 | 01607 | 10 | Solar | 05_14_5J42 | 10/11/2023 | 10/12/2023 | 1 | 0 | 1 | 10/13/2023 | 10/13/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 11/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 665241 | 01550 | 15.2 | Solar | 05_14_74L3 | 01/16/2025 | 01/31/2025 | 10 | 4 | 6 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/16/2025 | 3/18/2026 | Y | EXP | 365 | 08/09/2025 | 08/18/2025 | 10 | 0 | 10 |  |  | 8/26/2025 | Connected |  | N
National Grid | GARDNER | 176257 | 01440 | 252 | Solar | 05_01_219W2 | 09/03/2015 | 09/03/2015 | 0 | 0 | 0 | 09/07/2015 | 09/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2015 | 09/03/2015 | 9/12/2016 | Y | EXP | 354 | 06/22/2016 | 08/30/2016 | 48 | 0 | 48 | 9/24/2015 | 9/24/2015 | 10/7/2016 | Connected |  | N
National Grid | FALL RIVER | 201073 | 02721 | 396 | Solar | 05_01_27W1 | 11/15/2018 | 11/21/2018 | 4 | 2 | 2 | 11/26/2018 | 11/26/2018 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 196406 | 01532 | 66.6 | Solar | 05_01_413L1 | 09/19/2018 | 10/08/2018 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  | 5/1/2020 | N | EXP | 379 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 524121 | 01970 | 14.5 | Solar | 05_01_607W1 | 05/04/2023 | 06/07/2023 | 24 | 22 | 2 | 06/08/2023 | 06/08/2023 | 64 | 44 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2023 |  | 9/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2023 | Connected |  | Y
National Grid | REVERE | 178132 | 02151 | 3.8 | Solar | 05_05_115W53 | 07/12/2017 | 07/12/2017 | 4 | 4 | 0 | 07/19/2017 | 07/19/2017 | 173 | 0 | 173 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/18/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175809 | 01844 | 741 | Solar | 05_05_312W2 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 | 07/11/2015 | 10/06/2015 | 60 | 28 | 32 |  |  | 0 | 0 | 0 | 10/06/2015 | 60 | 28 | 32 |  |  | 0 | 0 | 0 | 10/30/2015 | 05/18/2015 | 12/31/2016 | Y | EXP | 428 | 03/29/2016 | 06/02/2016 | 45 | 0 | 45 | 11/30/2016 | 11/30/2016 | 6/28/2016 | Connected |  | N
National Grid | METHUEN | 278977 | 01844 | 9.36 | Solar | 05_12_29W2 | 03/05/2020 | 03/11/2020 | 3 | 0 | 3 | 03/12/2020 | 03/12/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176339 | 01844 | 3.8 | Solar | 05_12_7W2 | 09/17/2015 | 09/17/2015 | 5 | 5 | 0 | 09/24/2015 | 09/24/2015 | 330 | 0 | 330 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 |  | 9/22/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 524638 | 01453 | 6 | Solar | 05_14_43L4 | 06/08/2023 | 06/12/2023 | 2 | 0 | 2 | 06/13/2023 | 06/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 533962 | 01604 | 10 | Solar | 05_14_5J42 | 07/06/2023 | 07/13/2023 | 6 | 5 | 1 | 07/14/2023 | 07/14/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2023 | 07/06/2023 | 9/2/2024 | Y | EXP | 365 | 02/17/2024 | 02/16/2024 | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 669715 | 01550 | 7.6 | Solar | 05_14_74L3 | 02/03/2025 | 03/12/2025 | 20 | 16 | 4 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | GARDNER | 176439 | 01440 | 10 | Solar | 05_01_219W2 | 08/06/2015 | 08/06/2015 | 4 | 0 | 4 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 3/17/2016 | 3/17/2016 | 7/19/2016 | Connected |  | N
National Grid | FALL RIVER | 206484 | 02721 | 480 | Solar | 05_01_27W1 | 03/13/2019 | 04/27/2019 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2019 | 05/23/2019 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 03/13/2019 | 6/30/2023 | Y | STD | 644 |  |  | 0 | 0 | 0 |  |  | 6/16/2023 | Connected |  | N
National Grid | WESTBOROUGH | 293474 | 01581 | 7.92 | Solar | 05_01_413L1 | 06/17/2020 | 07/09/2020 | 16 | 12 | 4 | 07/10/2020 | 07/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 7/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N
National Grid | SALEM | 558965 | 01970 | 11.5 | Solar | 05_01_607W1 | 01/11/2024 | 03/04/2024 | 35 | 31 | 4 | 03/05/2024 | 03/05/2024 | 24 | 22 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 | 01/11/2024 | 4/19/2025 | Y | EXP | 365 | 05/11/2024 | 05/15/2024 | 5 | 0 | 5 |  |  | 8/9/2024 | Connected |  | N
National Grid | REVERE | 178394 | 02151 | 2470 | Solar | 05_05_115W53 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2018 | 04/12/2018 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 176027 | 01844 | 475 | Solar | 05_05_312W2 | 03/30/2015 | 03/30/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/25/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 286474 | 01844 | 3.8 | Solar | 05_12_29W2 | 04/17/2020 | 04/22/2020 | 1 | 0 | 1 | 04/23/2020 | 04/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 | 04/17/2020 | 10/21/2021 | Y | EXP | 365 | 04/13/2021 | 05/03/2021 | 20 | 0 | 20 |  |  | 9/3/2021 | Connected |  | N
National Grid | LAWRENCE | 176788 | 01841 | 11.4 | Solar | 05_12_7W2 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 | 01/14/2016 | 10/31/2017 | Y | EXP | 616 | 09/18/2017 | 11/14/2017 | 34 | 0 | 34 | 4/28/2017 | 4/28/2017 | 11/16/2017 | Connected |  | N
National Grid | LEOMINSTER | 527935 | 01453 | 10 | Solar | 05_14_43L4 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 7/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 534971 | 01604 | 7.6 | Solar | 05_14_5J42 | 07/06/2023 | 07/25/2023 | 14 | 13 | 1 | 07/26/2023 | 07/26/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2023 | 07/06/2023 | 9/20/2024 | Y | EXP | 365 | 01/24/2024 | 02/14/2024 | 22 | 0 | 22 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 670532 | 01550 | 3.8 | Solar | 05_14_74L3 | 02/06/2025 | 03/25/2025 | 25 | 20 | 5 | 03/26/2025 | 03/26/2025 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 02/06/2025 | 5/20/2026 | Y | EXP | 365 | 06/24/2025 | 07/28/2025 | 35 | 0 | 35 |  |  | 8/1/2025 | Connected |  | N
National Grid | GARDNER | 176738 | 01440 | 900 | Solar | 05_01_219W2 | 10/29/2015 | 10/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2015 | 12/01/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/4/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 260892 | 02721 | 6 | Solar | 05_01_27W1 | 11/01/2019 | 01/02/2020 | 40 | 38 | 2 | 01/03/2020 | 01/03/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 | 11/01/2019 | 9/3/2021 | Y | EXP | 365 | 05/06/2021 | 06/10/2021 | 35 | 0 | 35 |  |  | 8/10/2021 | Connected |  | N
National Grid | WESTBOROUGH | 419438 | 01581 | 7.6 | Solar | 05_01_413L1 | 03/23/2022 | 05/05/2022 | 31 | 30 | 1 | 05/06/2022 | 05/06/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 |  | 8/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2022 | Connected |  | N
National Grid | SALEM | 533436 | 01970 | 0 | Battery Add-On | 05_01_607W1 | 06/16/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 90 | 25 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 193191 | 02151 | 199.9 | Solar | 05_05_115W53 | 08/13/2018 | 10/15/2018 | 21 | 17 | 4 | 10/16/2018 | 10/16/2018 | 23 | 0 | 23 | 12/07/2018 | 01/24/2019 | 32 | 12 | 20 |  |  | 0 | 0 | 0 | 01/24/2019 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 176026 | 01844 | 266 | Solar | 05_05_312W2 | 03/30/2015 | 03/30/2015 | 7 | 3 | 4 | 04/09/2015 | 04/09/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/30/2015 | 8/25/2015 | Y | EXP | 0 | 03/29/2016 | 06/02/2016 | 45 | 0 | 45 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 583402 | 01844 | 10 | Solar | 05_12_29W2 | 01/19/2024 | 02/13/2024 | 18 | 16 | 2 | 02/14/2024 | 02/14/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 01/19/2024 | 3/1/2025 | Y | EXP | 365 | 05/15/2024 | 05/28/2024 | 14 | 0 | 14 |  |  | 5/31/2024 | Connected |  | N
National Grid | LAWRENCE | 177141 | 01841 | 10 | Solar | 05_12_7W2 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 162 | 0 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 |  | 6/6/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 527661 | 01453 | 10 | Solar | 05_14_43L4 | 06/01/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 596892 | 01604 | 5 | Solar | 05_14_5J42 | 03/19/2024 | 03/25/2024 | 4 | 0 | 4 | 03/26/2024 | 03/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/19/2024 | 8/29/2025 | Y | EXP | 405 | 10/03/2024 | 10/02/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 676986 | 01550 | 3.8 | Solar | 05_14_74L3 | 03/10/2025 | 03/22/2025 | 1 | 0 | 1 | 04/04/2025 | 04/04/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 03/10/2025 | 5/13/2026 | Y | EXP | 365 | 10/01/2025 | 12/02/2025 | 63 | 0 | 63 |  |  | 12/18/2025 | Connected |  | N
National Grid | GARDNER | 176747 | 01440 | 3 | Solar | 05_01_219W2 | 01/11/2016 | 01/11/2016 | 3 | 3 | 0 | 01/15/2016 | 01/15/2016 | 274 | 0 | 274 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2016 |  | 4/2/2017 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 336430 | 02721 | 6 | Solar | 05_01_27W1 | 01/15/2021 | 01/25/2021 | 4 | 0 | 4 | 01/26/2021 | 01/26/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2021 | Connected |  | N
National Grid | WESTBOROUGH | 482280 | 01581 | 18.816 | Solar | 05_01_413L1 | 01/03/2023 | 01/25/2023 | 15 | 14 | 1 | 01/26/2023 | 01/26/2023 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  | 3/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | SALEM | 555974 | 01970 | 10 | Solar | 05_01_607W1 | 09/26/2023 | 09/28/2023 | 2 | 0 | 2 | 09/29/2023 | 09/29/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2023 | 09/26/2023 | 11/18/2024 | Y | EXP | 365 | 01/18/2024 | 01/23/2024 | 6 | 0 | 6 |  |  | 2/26/2024 | Connected |  | N
National Grid | REVERE | 193337 | 02151 | 290 | Solar | 05_05_115W53 | 08/13/2018 | 10/12/2018 | 2 | 0 | 2 | 10/15/2018 | 10/15/2018 | 26 | 5 | 21 | 12/07/2018 | 01/24/2019 | 32 | 11 | 21 |  |  | 0 | 0 | 0 | 01/24/2019 | 32 | 11 | 21 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176093 | 01844 | 475 | Solar | 05_05_312W2 | 03/30/2015 | 03/30/2015 | 8 | 0 | 8 | 04/10/2015 | 04/10/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/25/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 632118 | 01844 | 10 | Solar | 05_12_29W2 | 08/23/2024 | 08/26/2024 | 1 | 0 | 1 | 08/27/2024 | 08/27/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  | 11/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2024 | Connected |  | N
National Grid | METHUEN | 177738 | 01844 | 6 | Solar | 05_12_7W2 | 03/24/2017 | 03/24/2017 | 4 | 4 | 0 | 03/31/2017 | 03/31/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 | 03/24/2017 | 8/10/2018 | Y | EXP | 493 | 10/24/2017 | 11/29/2017 | 19 | 0 | 19 |  |  | 8/29/2018 | Connected |  | N
National Grid | LEOMINSTER | 534617 | 01453 | 11.31 | Solar | 05_14_43L4 | 07/27/2023 | 07/28/2023 | 1 | 0 | 1 | 07/31/2023 | 07/31/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 07/27/2023 | 10/31/2024 | Y | EXP | 365 | 12/06/2023 | 12/12/2023 | 7 | 0 | 7 |  |  | 1/12/2024 | Connected |  | N
National Grid | WORCESTER | 639677 | 01604 | 7.6 | Solar | 05_14_5J42 | 09/12/2024 | 09/26/2024 | 1 | 0 | 1 | 09/27/2024 | 09/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 09/12/2024 | 11/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 681130 | 01550 | 3.8 | Solar | 05_14_74L3 | 03/27/2025 | 04/16/2025 | 4 | 0 | 4 | 08/11/2025 | 08/11/2025 | 85 | 64 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2026 | Connected |  | N
National Grid | GARDNER | 177417 | 01440 | 7.6 | Solar | 05_01_219W2 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 | 12/01/2016 | 12/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2016 | 11/29/2016 | 12/6/2017 | Y | EXP | 365 | 07/25/2017 | 09/26/2017 | 44 | 0 | 44 | 10/23/2017 | 10/23/2017 | 10/20/2017 | Connected |  | N
National Grid | FALL RIVER | 396408 | 02721 | 9.772 | Solar | 05_01_27W1 | 11/22/2021 | 12/22/2021 | 6 | 3 | 3 | 12/02/2021 | 12/02/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 5/31/2023 | N | EXP | 455 |  |  | 0 | 0 | 0 |  |  | 6/6/2023 | Connected |  | N
National Grid | WESTBOROUGH | 573990 | 01581 | 6 | Solar | 05_01_413L1 | 12/13/2023 | 12/14/2023 | 2 | 1 | 1 | 12/15/2023 | 12/15/2023 | 14 | 3 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 564080 | 01970 | 0 | Battery Add-On | 05_01_607W1 | 10/19/2023 |  | 222 | 222 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 193334 | 02151 | 119.9 | Solar | 05_05_115W53 | 08/13/2018 | 10/22/2018 | 6 | 1 | 5 | 10/23/2018 | 10/23/2018 | 45 | 29 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176785 | 01844 | 726 | Solar | 05_05_312W2 | 01/13/2016 | 01/13/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2016 | 01/27/2016 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2016 | 01/13/2016 | 1/19/2017 | Y | STD | 246 |  |  | 0 | 0 | 0 | 12/22/2016 | 12/22/2016 | 12/22/2016 | Connected |  | N
National Grid | METHUEN | 636021 | 01844 | 4.93 | Solar | 05_12_29W2 | 08/28/2024 | 09/19/2024 | 3 | 0 | 3 | 09/20/2024 | 09/20/2024 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 11/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2024 | Connected |  | N
National Grid | LAWRENCE | 178212 | 01841 | 3.8 | Solar | 05_12_7W2 | 03/23/2018 | 03/23/2018 | 9 | 0 | 9 | 05/14/2018 | 05/14/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2018 | 03/23/2018 | 7/31/2019 | Y | EXP | 408 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 553269 | 01453 | 6 | Solar | 05_14_43L4 | 09/15/2023 | 09/28/2023 | 9 | 7 | 2 | 09/29/2023 | 09/29/2023 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 644236 | 01604 | 5.76 | Solar | 05_14_5J42 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 682830 | 01550 | 8.027 | Solar | 05_14_74L3 | 04/04/2025 | 05/12/2025 | 3 | 0 | 3 | 05/19/2025 | 05/19/2025 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | GARDNER | 178627 | 01440 | 7.6 | Solar | 05_01_219W2 | 03/15/2018 | 03/15/2018 | 13 | 13 | 0 | 04/05/2018 | 04/05/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2018 |  | 3/21/2019 | N | EXP | 324 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 467875 | 02721 | 6 | Solar | 05_01_27W1 | 11/28/2022 |  | 239 | 65 | 174 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 579815 | 01581 | 7.25 | Solar | 05_01_413L1 | 01/05/2024 | 01/12/2024 | 5 | 3 | 2 | 01/16/2024 | 01/16/2024 | 170 | 25 | 145 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 593301 | 01970 | 7.6 | Solar | 05_01_607W1 | 03/06/2024 | 03/08/2024 | 2 | 0 | 2 | 03/11/2024 | 03/11/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 03/06/2024 | 4/1/2025 | Y | EXP | 365 | 07/25/2024 | 07/29/2024 | 5 | 0 | 5 |  |  | 8/20/2024 | Connected |  | N
National Grid | REVERE | 206944 | 02151 | 420 | Solar | 05_05_115W53 | 01/24/2019 | 02/07/2019 | 8 | 6 | 2 | 02/08/2019 | 02/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2020 | Connected |  | N
National Grid | LAWRENCE | 178271 | 01841 | 766.6 | Solar | 05_05_312W2 | 01/09/2018 | 01/09/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/10/2018 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2018 | 01/09/2018 | 2/26/2021 | Y | STD | 712 | 10/28/2020 | 12/14/2020 | 47 | 0 | 47 | 2/16/2021 | 2/16/2021 | 2/26/2021 | Connected |  | N
National Grid | METHUEN | 647623 | 01844 | 3.8 | Solar | 05_12_29W2 | 10/28/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/28/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | LAWRENCE | 178452 | 01841 | 10 | Solar | 05_12_7W2 | 11/29/2017 | 11/29/2017 | 38 | 36 | 2 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 | 11/29/2017 | 11/25/2019 | Y | EXP | 640 | 01/08/2019 | 04/19/2019 | 101 | 0 | 101 |  |  | 11/6/2019 | Connected |  | N
National Grid | LEOMINSTER | 564231 | 01453 | 7.6 | Solar | 05_14_43L4 | 11/08/2023 | 11/17/2023 | 6 | 3 | 3 | 11/20/2023 | 11/20/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 |  | 1/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2024 | Connected |  | N
National Grid | WORCESTER | 655097 | 01604 | 10 | Solar | 05_14_5J42 | 11/21/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/21/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 684455 | 01550 | 10 | Solar | 05_14_74L3 | 04/10/2025 | 05/02/2025 | 15 | 12 | 3 | 05/05/2025 | 05/05/2025 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2025 | 04/10/2025 | 8/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | GARDNER | 200671 | 01440 | 7.6 | Solar | 05_01_219W2 | 11/07/2018 | 12/17/2018 | 21 | 13 | 8 | 12/18/2018 | 12/18/2018 | 14 | 5 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 556062 | 02721 | 7.6 | Solar | 05_01_27W1 | 03/15/2024 | 09/22/2023 | 1 | 0 | 1 | 03/19/2024 | 03/19/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2024 | Connected |  | N
National Grid | WESTBOROUGH | 585346 | 01581 | 8.12 | Solar | 05_01_413L1 | 03/15/2024 | 03/20/2024 | 3 | 0 | 3 | 03/21/2024 | 03/21/2024 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 | 03/15/2024 | 4/23/2025 | Y | EXP | 365 | 07/17/2024 | 08/13/2024 | 28 | 0 | 28 |  |  | 8/31/2024 | Connected |  | N
National Grid | SALEM | 593486 | 01970 | 7.6 | Solar | 05_01_607W1 | 03/18/2024 | 03/21/2024 | 3 | 0 | 3 | 03/22/2024 | 03/22/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/18/2024 | 5/9/2025 | Y | EXP | 365 | 05/24/2024 | 05/23/2024 | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | REVERE | 210964 | 02151 | 7.6 | Solar | 05_05_115W53 | 03/17/2019 | 03/19/2019 | 1 | 1 | 0 | 03/20/2019 | 03/20/2019 | 113 | 25 | 88 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 351004 | 01844 | 220 | Solar | 05_05_312W2 | 05/20/2021 | 07/22/2021 | 43 | 33 | 10 |  |  | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2022 | 05/20/2021 | 11/21/2023 | Y | STD | 263 | 03/30/2023 | 04/15/2023 | 16 | 0 | 16 |  |  | 11/29/2023 | Connected |  | N
National Grid | METHUEN | 648716 | 01844 | 5.76 | Solar | 05_12_29W2 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | METHUEN | 184518 | 01844 | 10 | Solar | 05_12_7W2 | 05/15/2018 | 05/15/2018 | 0 | 0 | 0 | 06/12/2018 | 06/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 |  | 6/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2018 | Connected |  | N
National Grid | LEOMINSTER | 578821 | 01453 | 7.6 | Solar | 05_14_43L4 | 07/15/2024 | 01/08/2024 | 6 | 1 | 5 | 07/24/2024 | 07/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | WORCESTER | 660963 | 01604 | 7.6 | Solar | 05_14_5J42 | 12/16/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 735225 | 01550 | 15.76 | Solar | 05_14_74L3 | 11/20/2025 | 11/26/2025 | 4 | 0 | 4 | 11/28/2025 | 11/28/2025 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/21/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2026 | Connected |  | N
National Grid | GARDNER | 211055 | 01440 | 50 | Solar | 05_01_219W2 | 02/22/2019 | 03/11/2019 | 10 | 7 | 3 | 03/12/2019 | 03/12/2019 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 573451 | 02721 | 5.51 | Solar | 05_01_27W1 | 12/12/2023 | 12/14/2023 | 2 | 1 | 1 | 12/15/2023 | 12/15/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2024 | Connected |  | N
National Grid | WESTBOROUGH | 657508 | 01581 | 9.88 | Solar | 05_01_413L1 | 11/27/2024 | 12/29/2024 | 12 | 8 | 4 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 605406 | 01970 | 3.8 | Solar | 05_01_607W1 | 04/19/2024 | 04/30/2024 | 3 | 0 | 3 | 05/01/2024 | 05/01/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 214093 | 02151 | 7.36 | Solar | 05_05_115W53 | 05/17/2019 | 05/30/2019 | 7 | 1 | 6 | 05/31/2019 | 05/31/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 | 05/17/2019 | 6/16/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2019 | Connected |  | N
National Grid | LAWRENCE | 384611 | 01841 | 400 | Solar | 05_05_312W2 | 06/13/2022 | 08/12/2022 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/15/2022 | 09/13/2022 | 22 | 2 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 672412 | 01844 | 5.76 | Solar | 05_12_29W2 | 02/17/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | Y
National Grid | LAWRENCE | 195384 | 01841 | 499.9 | Solar | 05_12_7W2 | 09/12/2018 | 09/21/2018 | 5 | 0 | 5 | 09/24/2018 | 09/24/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 12/31/2020 | N | EXP | 392 |  |  | 0 | 0 | 0 |  |  | 10/22/2020 | Connected |  | N
National Grid | LEOMINSTER | 585644 | 01453 | 9.28 | Solar | 05_14_43L4 | 02/02/2024 | 02/06/2024 | 2 | 0 | 2 | 02/07/2024 | 02/07/2024 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/02/2024 | 3/6/2025 | Y | EXP | 365 | 07/16/2024 | 11/04/2024 | 112 | 0 | 112 |  |  | 11/9/2024 | Connected |  | N
National Grid | WORCESTER | 728326 | 01604 | 5.76 | Solar | 05_14_5J42 | 11/17/2025 | 11/20/2025 | 3 | 0 | 3 | 11/21/2025 | 11/21/2025 | 59 | 25 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 556519 | 01550 | 340 | Natural Gas | 05_14_74L4 | 02/20/2024 | 07/03/2025 | 341 | 331 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/07/2025 | 08/01/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y
National Grid | GARDNER | 283064 | 01440 | 7.6 | Solar | 05_01_219W2 | 05/18/2020 | 05/20/2020 | 1 | 0 | 1 | 05/21/2020 | 05/21/2020 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/18/2020 | 8/11/2022 | Y | EXP | 365 | 09/24/2021 | 10/12/2021 | 11 | 0 | 11 |  |  | 2/25/2022 | Connected |  | N
National Grid | FALL RIVER | 596342 | 02721 | 0 | Solar | 05_01_27W1 | 03/28/2024 | 04/01/2024 | 7 | 3 | 4 | 04/09/2024 | 04/09/2024 | 17 | 11 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 5/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2024 | Connected |  | N
National Grid | WESTBOROUGH | 663838 | 01581 | 3.8 | Solar | 05_01_413L1 | 01/06/2025 | 01/22/2025 | 5 | 0 | 5 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 642870 | 01970 | 7.83 | Solar | 05_01_607W1 | 09/25/2024 | 11/05/2024 | 13 | 8 | 5 | 11/06/2024 | 11/06/2024 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 09/25/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2025 | Connected |  | N
National Grid | REVERE | 278494 | 02151 | 5 | Solar | 05_05_115W53 | 03/04/2020 | 03/18/2020 | 10 | 7 | 3 | 03/19/2020 | 03/19/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2020 | 03/04/2020 |  | Y | EXP | 365 | 07/03/2020 | 07/31/2020 | 28 | 0 | 28 |  |  | 8/25/2020 | Connected |  | N
National Grid | METHUEN | 639701 | 01844 | 333 | Solar | 05_05_312W3 | 10/02/2024 | 10/22/2024 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 11/20/2024 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 697403 | 01844 | 12.92 | Solar | 05_12_29W2 | 06/10/2025 | 09/18/2025 | 7 | 2 | 5 | 10/03/2025 | 10/03/2025 | 40 | 35 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2025 |  | 1/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2026 | Connected |  | Y
National Grid | LAWRENCE | 192939 | 01841 | 7.6 | Solar | 05_12_7W2 | 08/08/2018 | 09/04/2018 | 12 | 0 | 12 | 09/05/2018 | 09/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 589208 | 01453 | 7.6 | Solar | 05_14_43L4 | 02/23/2024 | 03/04/2024 | 6 | 0 | 6 | 03/05/2024 | 03/05/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 02/23/2024 | 4/23/2025 | Y | EXP | 365 | 07/16/2024 | 09/20/2024 | 67 | 0 | 67 |  |  | 10/23/2024 | Connected |  | N
National Grid | WORCESTER | 729809 | 01604 | 10 | Solar | 05_14_5J43 | 10/28/2025 | 10/29/2025 | 18 | 15 | 3 | 12/09/2025 | 12/09/2025 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 | 10/28/2025 | 2/24/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SOUTHBRIDGE | 672131 | 01550 | 180 | Solar | 05_14_74L4 | 04/04/2025 |  | 246 | 32 | 214 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | Y
National Grid | GARDNER | 285851 | 01440 | 6 | Solar | 05_01_219W2 | 04/22/2020 | 04/27/2020 | 3 | 1 | 2 | 04/28/2020 | 04/28/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2020 | 04/22/2020 | 4/28/2022 | Y | EXP | 365 | 05/07/2021 | 06/23/2021 | 47 | 0 | 47 |  |  | 9/24/2021 | Connected |  | N
National Grid | FALL RIVER | 600309 | 02721 | 5 | Solar | 05_01_27W1 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 23 | 18 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 663621 | 01532 | 10 | Solar | 05_01_413L1 | 01/03/2025 | 01/17/2025 | 6 | 0 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | SALEM | 651319 | 01970 | 5.76 | Solar | 05_01_607W1 | 11/12/2024 | 01/13/2025 | 22 | 17 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 11/12/2024 | 3/14/2026 | Y | EXP | 365 | 06/11/2025 | 10/04/2025 | 116 | 0 | 116 |  |  | 11/24/2025 | Connected |  | N
National Grid | REVERE | 281069 | 02151 | 5 | Solar | 05_05_115W53 | 04/06/2020 | 04/20/2020 | 9 | 9 | 0 | 04/21/2020 | 04/21/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2020 | 04/06/2020 | 4/19/2021 | Y | EXP | 365 | 07/03/2020 | 07/31/2020 | 28 | 0 | 28 |  |  | 8/12/2020 | Connected |  | Y
National Grid | METHUEN | 676971 | 01844 | 750 | Solar | 05_05_312W3 | 04/08/2025 | 06/26/2025 | 54 | 44 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2025 | 07/23/2025 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 725929 | 01844 | 5.76 | Solar | 05_12_29W2 | 10/13/2025 | 10/20/2025 | 7 | 5 | 2 | 11/10/2025 | 11/10/2025 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 197019 | 01840 | 7.6 | Solar | 05_12_7W2 | 09/27/2018 | 10/17/2018 | 3 | 3 | 0 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 591270 | 01453 | 6 | Solar | 05_14_43L4 | 02/23/2024 | 02/26/2024 | 1 | 0 | 1 | 02/27/2024 | 02/27/2024 | 19 | 15 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 | 02/23/2024 | 3/27/2025 | Y | EXP | 365 | 05/30/2024 | 07/17/2024 | 49 | 0 | 49 |  |  | 7/19/2024 | Connected |  | N
National Grid | WORCESTER | 515931 | 01604 | 3.8 | Solar | 05_14_5J43 | 04/07/2023 |  | 149 | 148 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 677996 | 01550 | 15.2 | Solar | 05_14_74L4 | 03/17/2025 | 03/24/2025 | 5 | 1 | 4 | 03/25/2025 | 03/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | GARDNER | 341966 | 01440 | 3.8 | Solar | 05_01_219W2 | 02/22/2021 | 02/23/2021 | 0 | 0 | 0 | 02/24/2021 | 02/24/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2021 |  | 2/22/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 600630 | 02721 | 6 | Solar | 05_01_27W1 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 673133 | 01581 | 10 | Solar | 05_01_413L1 | 02/21/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 | 02/21/2025 | 4/11/2026 | Y | EXP | 365 | 09/23/2025 | 09/22/2025 | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | SALEM | 651317 | 01970 | 3.8 | Solar | 05_01_607W1 | 11/14/2024 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | REVERE | 280777 | 02151 | 3.8 | Solar | 05_05_115W53 | 03/10/2020 | 03/18/2020 | 5 | 0 | 5 | 03/19/2020 | 03/19/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 755684 | 01844 | 5.76 | Solar | 05_05_312W3 | 03/10/2026 | 03/16/2026 | 2 | 0 | 2 | 03/27/2026 | 03/27/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 736817 | 01844 |  | Battery Add-On | 05_12_29W3 | 12/03/2025 | 12/04/2025 | 2 | 0 | 2 | 01/22/2026 | 01/22/2026 | 43 | 31 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2026 |  | 3/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 197013 | 01841 | 3 | Solar | 05_12_7W2 | 09/27/2018 | 10/17/2018 | 3 | 3 | 0 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 | 09/27/2018 | 5/20/2019 | Y | EXP | 213 | 02/12/2019 | 04/11/2019 | 58 | 0 | 58 |  |  | 4/27/2019 | Connected |  | N
National Grid | LEOMINSTER | 595579 | 01453 | 7.6 | Solar | 05_14_43L4 | 03/13/2024 | 03/19/2024 | 4 | 0 | 4 | 03/20/2024 | 03/20/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 | 03/13/2024 | 4/17/2025 | Y | EXP | 365 | 04/16/2024 | 09/03/2024 | 141 | 0 | 141 |  |  | 9/26/2024 | Connected |  | N
National Grid | WORCESTER | 588136 | 01604 | 7.6 | Solar | 05_14_5J43 | 04/05/2024 | 04/17/2024 | 7 | 4 | 3 | 04/18/2024 | 04/18/2024 | 91 | 79 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 697435 | 01550 | 15.2 | Solar | 05_14_74L4 | 06/10/2025 | 06/24/2025 | 8 | 0 | 8 | 08/21/2025 | 08/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GARDNER | 352779 | 01440 | 5.76 | Solar | 05_01_219W2 | 05/04/2021 | 05/05/2021 | 0 | 0 | 0 | 05/06/2021 | 05/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  | 6/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2021 | Connected |  | N
National Grid | FALL RIVER | 604510 | 02721 | 5.76 | Solar | 05_01_27W1 | 04/17/2024 | 05/01/2024 | 5 | 0 | 5 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/17/2024 | 6/7/2025 | Y | EXP | 365 | 08/16/2024 | 10/29/2024 | 75 | 0 | 75 |  |  | 11/12/2024 | Connected |  | N
National Grid | WESTBOROUGH | 686535 | 01581 | 20 | Solar | 05_01_413L1 | 04/23/2025 | 04/29/2025 | 4 | 0 | 4 | 04/30/2025 | 04/30/2025 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 659940 | 01905 | 7.6 | Solar | 05_01_607W1 | 12/11/2024 | 12/18/2024 | 2 | 0 | 2 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/11/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | REVERE | 317453 | 02151 | 50 | Solar | 05_05_115W53 | 10/06/2020 | 11/03/2020 | 18 | 13 | 5 | 11/04/2020 | 11/04/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2021 | Connected |  | N
National Grid | LAWRENCE | 174837 | 01841 | 30 | Solar | 05_05_312W3 | 09/04/2012 | 09/04/2012 | 6 | 0 | 6 | 09/13/2012 | 09/13/2012 | 433 | 0 | 433 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2012 |  | 12/28/2012 | N | EXP | 24 |  |  | 0 | 0 | 0 | 12/4/2012 | 12/4/2012 |  | Withdrawn |  | Y
National Grid | METHUEN | 176276 | 01844 | 79 | Solar | 05_12_29W3 | 05/04/2015 | 05/04/2015 | 0 | 0 | 0 | 05/07/2015 | 05/07/2015 | 349 | 0 | 349 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 |  | 10/30/2015 | N | EXP | 171 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 |  | Withdrawn |  | N
National Grid | LAWRENCE | 196955 | 01841 | 3.8 | Solar | 05_12_7W2 | 11/26/2018 | 02/04/2019 | 49 | 44 | 5 | 02/05/2019 | 02/05/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2019 |  | 11/26/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 595995 | 01453 | 7.6 | Solar | 05_14_43L4 | 04/05/2024 | 04/15/2024 | 6 | 2 | 4 | 04/16/2024 | 04/16/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 | 04/05/2024 | 4/25/2025 | Y | EXP | 365 | 06/05/2024 | 06/21/2024 | 17 | 0 | 17 |  |  | 7/18/2024 | Connected |  | N
National Grid | WORCESTER | 608023 | 01604 | 3.8 | Solar | 05_14_5J43 | 05/02/2024 | 05/09/2024 | 1 | 0 | 1 | 05/10/2024 | 05/10/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2024 | 05/02/2024 | 8/3/2025 | Y | EXP | 365 | 09/19/2024 | 10/29/2024 | 41 | 0 | 41 |  |  | 1/17/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 712563 | 01550 | 15.2 | Solar | 05_14_74L4 | 08/15/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 104 | 77 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | GARDNER | 451693 | 01440 | 6 | Solar | 05_01_219W2 | 08/25/2022 | 08/30/2022 | 3 | 0 | 3 | 08/31/2022 | 08/31/2022 | 71 | 27 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 605299 | 02721 | 3.8 | Solar | 05_01_27W1 | 04/19/2024 | 04/26/2024 | 4 | 0 | 4 | 04/29/2024 | 04/29/2024 | 57 | 47 | 10 | 08/05/2024 | 09/17/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 09/17/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 9/23/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 688107 | 01581 | 15.2 | Solar | 05_01_413L1 | 04/28/2025 | 04/30/2025 | 2 | 0 | 2 | 05/01/2025 | 05/01/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 670136 | 01905 | 5.76 | Solar | 05_01_607W1 | 02/05/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | REVERE | 391147 | 02151 | 10 | Solar | 05_05_115W53 | 11/03/2021 | 01/10/2022 | 5 | 0 | 5 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 | 11/03/2021 | 5/3/2023 | Y | EXP | 365 | 03/11/2022 | 04/29/2022 | 50 | 0 | 50 |  |  | 7/9/2022 | Connected |  | N
National Grid | METHUEN | 175231 | 01844 | 504 | Solar | 05_05_312W3 | 06/10/2014 | 06/10/2014 | 7 | 3 | 4 | 06/23/2014 | 06/23/2014 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2014 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176604 | 01844 | 4.25 | Solar | 05_12_29W3 | 12/30/2015 | 12/30/2015 | 3 | 3 | 0 | 01/05/2016 | 01/05/2016 | 270 | 0 | 270 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2016 |  | 1/4/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 198416 | 01841 | 3.8 | Solar | 05_12_7W2 | 11/09/2018 | 11/20/2018 | 5 | 0 | 5 | 11/21/2018 | 11/21/2018 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 |  | 11/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2020 | Connected |  | N
National Grid | LEOMINSTER | 597509 | 01453 | 13.325 | Solar | 05_14_43L4 | 04/03/2024 | 04/17/2024 | 9 | 6 | 3 | 04/18/2024 | 04/18/2024 | 37 | 32 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 616382 | 01604 | 3.8 | Solar | 05_14_5J43 | 06/07/2024 | 06/28/2024 | 1 | 0 | 1 | 07/01/2024 | 07/01/2024 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 | 06/07/2024 | 8/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 727868 | 01550 | 7.6 | Solar | 05_14_74L4 | 10/20/2025 | 10/23/2025 | 3 | 0 | 3 | 10/24/2025 | 10/24/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GARDNER | 367884 | 01440 | 10 | Solar | 05_01_219W2 | 07/13/2021 | 12/20/2021 | 3 | 0 | 3 | 07/19/2021 | 07/19/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 | 07/13/2021 | 8/8/2023 | Y | EXP | 365 | 05/03/2022 | 05/17/2022 | 15 | 0 | 15 |  |  | 8/17/2022 | Connected |  | Y
National Grid | FALL RIVER | 610657 | 02721 | 3.8 | Solar | 05_01_27W1 | 05/14/2024 | 05/21/2024 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 695187 | 01532 | 15.2 | Solar | 05_01_413L1 | 06/13/2025 | 06/24/2025 | 5 | 2 | 3 | 06/25/2025 | 06/25/2025 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | LYNN | 686443 | 01905 | 15.2 | Solar | 05_01_607W1 | 04/21/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 440461 | 02151 | 250 | Solar | 05_05_115W53 | 07/25/2022 | 08/10/2022 | 12 | 2 | 10 | 08/11/2022 | 08/11/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 | 07/25/2022 | 10/22/2025 | Y | EXP | 133 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175601 | 01841 | 460 | Solar | 05_05_312W3 | 10/15/2014 | 10/15/2014 | 5 | 0 | 5 | 10/23/2014 | 10/23/2014 | 0 | 0 | 0 | 01/27/2015 | 03/06/2015 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 03/06/2015 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 3/20/2015 |  | 1/31/2015 | N | EXP | 48 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 2/4/2016 | Connected |  | N
National Grid | METHUEN | 177962 | 01844 | 3.8 | Solar | 05_12_29W3 | 10/24/2017 | 10/24/2017 | 15 | 14 | 1 | 11/27/2017 | 11/27/2017 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 10/31/2018 | N | EXP | 338 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 198866 | 01844 | 7.6 | Solar | 05_12_7W2 | 10/19/2018 | 11/05/2018 | 7 | 1 | 6 | 11/06/2018 | 11/06/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 | 10/19/2018 | 1/27/2020 | Y | EXP | 365 | 06/05/2019 | 06/22/2019 | 17 | 0 | 17 |  |  | 1/16/2020 | Connected |  | N
National Grid | LEOMINSTER | 597079 | 01453 | 2.32 | Solar | 05_14_43L4 | 03/22/2024 | 03/29/2024 | 5 | 2 | 3 | 04/01/2024 | 04/01/2024 | 12 | 6 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 4/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | WORCESTER | 625674 | 01604 | 7.6 | Solar | 05_14_5J43 | 07/17/2024 | 07/26/2024 | 2 | 0 | 2 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 756687 | 01550 | 17.16 | Solar | 05_14_74L4 | 03/17/2026 | 03/25/2026 | 6 | 4 | 2 | 03/26/2026 | 03/26/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GARDNER | 420950 | 01440 | 8.99 | Solar | 05_01_219W2 | 04/06/2022 | 04/21/2022 | 11 | 10 | 1 | 04/22/2022 | 04/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 610041 | 02721 | 7.6 | Solar | 05_01_27W1 | 05/09/2024 | 05/23/2024 | 3 | 0 | 3 | 05/24/2024 | 05/24/2024 | 59 | 45 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 197148 | 01532 | 996 | Solar | 05_01_413L2 | 10/04/2018 | 11/02/2018 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2018 | 12/05/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2020 | 10/04/2018 | 3/7/2026 | Y | STD | 476 | 12/23/2025 |  | 100 | 0 | 100 |  |  |  | Construction |  | N
National Grid | LYNN | 357820 | 01905 | 240 | Solar | 05_01_607W2 | 05/14/2021 | 06/02/2021 | 10 | 0 | 10 |  |  | 53 | 28 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | REVERE | 492560 | 02151 | 7.6 | Solar | 05_05_115W53 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 | 02/01/2023 | 7/1/2024 | Y | EXP | 365 | 07/13/2023 | 09/15/2023 | 65 | 0 | 65 |  |  | 11/21/2023 | Connected |  | N
National Grid | LAWRENCE | 177986 | 01841 | 366.3 | Solar | 05_05_312W3 | 08/28/2017 | 08/28/2017 | 99 | 96 | 3 | 02/01/2018 | 02/01/2018 | 22 | 0 | 22 | 03/19/2018 | 04/13/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 04/13/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 4/27/2018 |  | 9/4/2018 | N | EXP | 130 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 189736 | 01844 | 7.6 | Solar | 05_12_29W3 | 07/02/2018 | 07/02/2018 | 2 | 0 | 2 | 08/06/2018 | 08/06/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 07/02/2018 | 11/15/2019 | Y | EXP | 463 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | LAWRENCE | 200168 | 01841 | 3.8 | Solar | 05_12_7W2 | 11/05/2018 | 11/20/2018 | 3 | 3 | 0 | 11/21/2018 | 11/21/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 |  | 12/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2019 | Connected |  | N
National Grid | LEOMINSTER | 602477 | 01453 | 11.4 | Solar | 05_14_43L4 | 04/17/2024 | 06/25/2024 | 47 | 47 | 0 | 06/26/2024 | 06/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 | 04/17/2024 | 8/12/2025 | Y | EXP | 365 | 10/03/2024 | 11/26/2024 | 55 | 0 | 55 |  |  | 12/18/2024 | Connected |  | N
National Grid | WORCESTER | 177329 | 01604 | 120 | Solar | 05_14_5J44 | 06/21/2016 | 06/21/2016 | 2 | 2 | 0 | 06/27/2016 | 06/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2016 | 06/21/2016 | 6/28/2017 | Y | EXP | 320 | 02/15/2017 | 02/28/2017 | 8 | 0 | 8 | 4/19/2017 | 4/19/2017 | 4/19/2017 | Connected |  | N
National Grid | SOUTHBRIDGE | 174279 | 01550 | 491 | Solar | 05_14_74L4 | 12/13/2011 | 12/13/2011 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2012 | 12/13/2011 | 3/1/2012 | Y | EXP | 62 | 06/06/2012 | 07/16/2012 | 26 | 0 | 26 | 6/26/2012 | 6/26/2012 | 7/2/2012 | Connected |  | N
National Grid | GARDNER | 437201 | 01440 | 5.76 | Solar | 05_01_219W2 | 07/18/2022 | 07/19/2022 | 1 | 0 | 1 | 07/20/2022 | 07/20/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 | 07/18/2022 | 2/1/2024 | Y | EXP | 365 | 01/07/2023 | 02/01/2023 | 26 | 0 | 26 |  |  | 5/8/2023 | Connected |  | N
National Grid | FALL RIVER | 612619 | 02721 | 5 | Solar | 05_01_27W1 | 05/29/2024 | 06/13/2024 | 1 | 0 | 1 | 06/14/2024 | 06/14/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 419334 | 01532 | 240 | Solar | 05_01_413L2 | 05/26/2022 | 06/13/2022 | 11 | 6 | 5 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 | 05/26/2022 | 7/22/2026 | Y | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 605595 | 01905 | 100 | Solar | 05_01_607W2 | 04/22/2024 | 05/08/2024 | 12 | 5 | 7 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | REVERE | 501441 | 02151 | 14.79 | Solar | 05_05_115W53 | 06/13/2023 | 02/23/2023 | 13 | 9 | 4 | 07/05/2023 | 07/05/2023 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 319057 | 01844 | 249 | Solar | 05_05_312W3 | 10/13/2020 | 11/04/2020 | 15 | 8 | 7 | 11/18/2020 | 11/18/2020 | 63 | 50 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  | 8/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2023 | Connected |  | N
National Grid | METHUEN | 220688 | 01844 | 3 | Solar | 05_12_29W3 | 04/24/2019 | 04/29/2019 | 4 | 4 | 0 | 04/30/2019 | 04/30/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 200027 | 01840 | 10 | Solar | 05_12_7W2 | 11/01/2018 | 11/21/2018 | 2 | 1 | 1 | 11/26/2018 | 11/26/2018 | 28 | 15 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 11/01/2018 | 7/17/2020 | Y | EXP | 365 | 07/26/2019 | 07/31/2019 | 5 | 0 | 5 |  |  | 7/13/2020 | Connected |  | N
National Grid | LEOMINSTER | 610901 | 01453 | 10 | Solar | 05_14_43L4 | 05/31/2024 | 06/12/2024 | 2 | 0 | 2 | 06/13/2024 | 06/13/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 258970 | 01604 | 10 | Solar | 05_14_5J44 | 10/24/2019 | 10/25/2019 | 0 | 0 | 0 | 10/28/2019 | 10/28/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 | 10/24/2019 | 10/24/2020 | Y | EXP | 365 | 02/27/2020 | 03/03/2020 | 5 | 0 | 5 |  |  | 3/4/2020 | Connected |  | N
National Grid | STURBRIDGE | 174828 | 01566 | 100 | Solar | 05_14_74L4 | 08/15/2011 | 08/15/2011 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2011 | 08/15/2011 | 3/6/2012 | Y | EXP | 81 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 3/6/2012 | Connected |  | N
National Grid | GARDNER | 440596 | 01440 | 10 | Solar | 05_01_219W2 | 07/14/2022 | 07/15/2022 | 2 | 1 | 1 | 07/18/2022 | 07/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 614361 | 02721 | 3.8 | Solar | 05_01_27W1 | 05/30/2024 | 06/10/2024 | 3 | 0 | 3 | 06/11/2024 | 06/11/2024 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 406202 | 01532 | 249 | Solar | 05_01_413L2 | 01/14/2022 | 03/03/2022 | 32 | 24 | 8 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 | 01/14/2022 | 6/6/2026 | Y | STD | 224 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 708125 | 01904 | 15.58 | Solar | 05_01_607W2 | 07/29/2025 | 08/05/2025 | 4 | 0 | 4 | 08/06/2025 | 08/06/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | REVERE | 519921 | 02151 | 6 | Solar | 05_05_115W53 | 04/21/2023 | 04/24/2023 | 1 | 0 | 1 | 04/25/2023 | 04/25/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 409851 | 01844 | 86.4 | Solar | 05_05_312W3 | 02/04/2022 | 02/09/2022 | 3 | 0 | 3 | 02/10/2022 | 02/10/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2022 | 02/04/2022 | 1/11/2023 | Y | EXP | 196 | 12/01/2022 | 12/06/2022 | 6 | 6 | 0 |  |  | 1/19/2023 | Connected |  | N
National Grid | METHUEN | 242778 | 01844 | 3.8 | Solar | 05_12_29W3 | 07/24/2019 | 07/29/2019 | 2 | 0 | 2 | 07/30/2019 | 07/30/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2019 |  | 11/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 200644 | 01840 | 10 | Solar | 05_12_7W2 | 11/08/2018 | 11/20/2018 | 2 | 0 | 2 | 11/21/2018 | 11/21/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 629865 | 01453 | 6 | Solar | 05_14_43L4 | 08/02/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 08/02/2024 | 11/25/2025 | Y | EXP | 365 | 01/09/2025 | 01/08/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 290050 | 01604 | 7.6 | Solar | 05_14_5J44 | 05/05/2020 |  | 48 | 48 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 175933 | 01566 | 7.6 | Solar | 05_14_74L4 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 362 | 0 | 362 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 |  | Withdrawn |  | Y
National Grid | GARDNER | 513551 | 01440 | 0 | Solar | 05_01_219W2 | 03/21/2023 | 03/22/2023 | 1 | 0 | 1 | 03/23/2023 | 03/23/2023 | 54 | 33 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2023 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 615988 | 02721 | 5.76 | Solar | 05_01_27W1 | 06/06/2024 | 06/14/2024 | 0 | 0 | 0 | 06/17/2024 | 06/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 | 06/06/2024 | 7/5/2025 | Y | EXP | 365 | 10/03/2024 | 11/07/2024 | 36 | 0 | 36 |  |  | 12/19/2024 | Connected |  | N
National Grid | WESTBOROUGH | 431376 | 01581 | 500 | Solar | 05_01_413L2 | 06/06/2022 | 06/22/2022 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2022 | 07/21/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/06/2022 | 2/23/2027 | Y | STD | 397 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LYNN | 174639 | 01905 | 60 | Solar | 05_01_607W2 | 05/23/2013 | 05/23/2013 | 7 | 0 | 7 | 06/05/2013 | 06/05/2013 | 1121 | 0 | 1121 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2013 |  | 10/14/2020 | N | EXP | 1745 |  |  | 0 | 0 | 0 | 3/3/2015 | 3/3/2015 | 10/14/2020 | Connected |  | N
National Grid | REVERE | 546881 | 02151 | 10 | Solar | 05_05_115W53 | 09/05/2023 | 08/15/2023 | 4 | 0 | 4 | 09/12/2023 | 09/12/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2023 |  | 10/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2024 | Connected |  | N
National Grid | METHUEN | 552640 | 01844 | 333 | Solar | 05_05_312W3 | 11/21/2023 |  | 192 | 183 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 255456 | 01844 | 7.6 | Solar | 05_12_29W3 | 10/07/2019 | 10/08/2019 | 0 | 0 | 0 | 10/09/2019 | 10/09/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2019 |  | 10/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2020 | Connected |  | N
National Grid | METHUEN | 203133 | 01844 | 7.6 | Solar | 05_12_7W2 | 12/19/2018 | 12/31/2018 | 6 | 0 | 6 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 631324 | 01453 | 10 | Solar | 05_14_43L4 | 08/08/2024 | 08/21/2024 | 5 | 0 | 5 | 08/22/2024 | 08/22/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 10/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | WORCESTER | 304996 | 01604 | 7.6 | Solar | 05_14_5J44 | 08/04/2020 | 08/06/2020 | 1 | 0 | 1 | 08/07/2020 | 08/07/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 176269 | 01566 | 17.6 | Solar | 05_14_74L4 | 02/18/2015 | 02/18/2015 | 4 | 1 | 3 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 7/13/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 | 10/1/2015 | 10/1/2015 | 7/25/2016 | Connected |  | N
National Grid | GARDNER | 527887 | 01440 | 6 | Solar | 05_01_219W2 | 05/30/2023 | 06/01/2023 | 2 | 0 | 2 | 06/02/2023 | 06/02/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 622781 | 02721 | 9.8 | Solar | 05_01_27W1 | 07/05/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 708984 | 01532 | 0 | Other | 05_01_413L2 | 10/08/2025 | 11/20/2025 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 12/17/2025 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LYNN | 178322 | 01905 | 2510 | Solar | 05_01_607W2 | 03/29/2018 | 04/03/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/25/2018 | 13 | 0 | 13 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 575780 | 02151 | 9.765 | Solar | 05_05_115W53 | 12/11/2023 | 12/14/2023 | 3 | 0 | 3 | 12/15/2023 | 12/15/2023 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 | 12/11/2023 | 2/25/2025 | Y | EXP | 365 | 07/02/2024 | 08/02/2024 | 32 | 0 | 32 |  |  | 8/20/2024 | Connected |  | N
National Grid | METHUEN | 582654 | 01844 | 0 | Solar | 05_05_312W3 | 02/02/2024 | 03/21/2024 | 34 | 32 | 2 | 03/22/2024 | 03/22/2024 | 19 | 15 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | METHUEN | 286083 | 01844 | 3.8 | Solar | 05_12_29W3 | 05/08/2020 | 05/27/2020 | 12 | 12 | 0 | 05/28/2020 | 05/28/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/08/2020 | 5/26/2021 | Y | EXP | 365 | 12/05/2020 | 01/06/2021 | 32 | 0 | 32 |  |  | 1/7/2021 | Connected |  | N
National Grid | METHUEN | 204942 | 01844 | 3.8 | Solar | 05_12_7W2 | 12/31/2018 | 01/25/2019 | 17 | 17 | 0 | 01/28/2019 | 01/28/2019 | 142 | 0 | 142 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 633402 | 01453 | 5 | Solar | 05_14_43L4 | 08/19/2024 | 10/04/2024 | 31 | 25 | 6 | 10/07/2024 | 10/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 426328 | 01604 | 5.51 | Solar | 05_14_5J44 | 05/11/2022 | 05/24/2022 | 10 | 7 | 3 | 05/25/2022 | 05/25/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 |  | 7/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2022 | Connected |  | N
National Grid | STURBRIDGE | 176665 | 01566 | 17.25 | Solar | 05_14_74L4 | 10/19/2015 | 10/19/2015 | 7 | 7 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2015 |  | 10/26/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/9/2016 | 8/9/2016 | 8/9/2016 | Connected |  | N
National Grid | HUBBARDSTON | 571393 | 01452 | 10 | Solar | 05_01_219W2 | 11/24/2023 | 12/11/2023 | 12 | 11 | 1 | 12/12/2023 | 12/12/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 625053 | 02721 | 3.8 | Solar | 05_01_27W1 | 07/16/2024 | 07/19/2024 | 1 | 0 | 1 | 07/22/2024 | 07/22/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/16/2024 | 8/6/2025 | Y | EXP | 365 | 08/29/2024 | 08/28/2024 | 0 | 0 | 0 |  |  | 9/27/2024 | Connected |  | N
National Grid | WESTBOROUGH | 737365 | 01851 | 7.6 | Solar | 05_01_413L2 | 12/02/2025 | 12/03/2025 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 192422 | 01904 | 100 | Solar | 05_01_607W2 | 08/01/2018 | 08/20/2018 | 11 | 0 | 11 | 08/21/2018 | 08/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  | 1/7/2020 | N | EXP | 475 | 11/13/2019 | 11/12/2019 | 0 | 0 | 0 |  |  | 1/7/2020 | Connected |  | N
National Grid | REVERE | 577963 | 02151 | 10 | Solar | 05_05_115W53 | 12/18/2023 | 01/02/2024 | 8 | 6 | 2 | 01/03/2024 | 01/03/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 | 12/18/2023 | 2/6/2025 | Y | EXP | 365 | 03/26/2024 | 03/25/2024 | 0 | 0 | 0 |  |  | 4/23/2024 | Connected |  | N
National Grid | LAWRENCE | 743633 | 01841 | 23 | Battery Add-On | 05_05_312W4 | 01/08/2026 | 01/12/2026 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 310786 | 01844 | 7.68 | Solar | 05_12_29W3 | 10/19/2020 | 10/20/2020 | 1 | 1 | 0 | 10/21/2020 | 10/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2020 | 10/19/2020 | 4/21/2022 | Y | EXP | 365 | 01/20/2021 | 03/12/2021 | 51 | 0 | 51 |  |  | 10/14/2021 | Connected |  | N
National Grid | METHUEN | 234798 | 01844 | 7.6 | Solar | 05_12_7W2 | 07/10/2019 | 07/18/2019 | 5 | 0 | 5 | 07/19/2019 | 07/19/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2019 |  | 7/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2020 | Connected |  | N
National Grid | LEOMINSTER | 636570 | 01453 | 5.76 | Solar | 05_14_43L4 | 08/29/2024 | 09/23/2024 | 4 | 0 | 4 | 09/24/2024 | 09/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 | 08/29/2024 | 10/30/2025 | Y | EXP | 365 | 12/19/2024 | 03/03/2025 | 75 | 0 | 75 |  |  | 3/12/2025 | Connected |  | N
National Grid | WORCESTER | 671959 | 01604 | 11.52 | Solar | 05_14_5J44 | 02/13/2025 | 02/27/2025 | 2 | 0 | 2 | 02/28/2025 | 02/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 194731 | 01550 | 10 | Solar | 05_14_74L4 | 08/31/2018 | 09/18/2018 | 4 | 4 | 0 | 09/19/2018 | 09/19/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 | 08/31/2018 | 5/21/2019 | Y | EXP | 238 | 03/09/2019 | 04/09/2019 | 31 | 0 | 31 |  |  | 4/16/2019 | Connected |  | N
National Grid | GARDNER | 604880 | 01440 | 5.76 | Solar | 05_01_219W2 | 04/18/2024 | 05/21/2024 | 19 | 14 | 5 | 05/22/2024 | 05/22/2024 | 22 | 9 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 | 04/18/2024 | 7/25/2025 | Y | EXP | 365 | 09/04/2024 | 09/12/2024 | 9 | 0 | 9 |  |  | 12/12/2024 | Connected |  | N
National Grid | FALL RIVER | 625527 | 02721 | 5 | Solar | 05_01_27W1 | 07/18/2024 | 07/31/2024 | 3 | 0 | 3 | 08/01/2024 | 08/01/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 741674 | 01581 | 11.5 | Solar | 05_01_413L2 | 12/22/2025 | 12/29/2025 | 4 | 0 | 4 | 12/30/2025 | 12/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 1/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 482643 | 01904 | 17.4 | Solar | 05_01_607W2 | 02/06/2023 | 03/24/2023 | 33 | 32 | 1 | 03/27/2023 | 03/27/2023 | 72 | 52 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 617210 | 02151 | 7.6 | Solar | 05_05_115W53 | 06/11/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 | 06/11/2024 | 8/7/2025 | Y | EXP | 365 | 09/25/2024 | 10/16/2024 | 22 | 0 | 22 |  |  | 10/29/2024 | Connected |  | N
National Grid | METHUEN | 757368 | 01844 |  | Battery Add-On | 05_05_312W4 | 03/18/2026 | 03/23/2026 | 3 | 0 | 3 | 03/24/2026 | 03/24/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 378521 | 01844 | 5.76 | Solar | 05_12_29W3 | 09/08/2021 | 09/13/2021 | 3 | 0 | 3 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2021 |  | 11/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2022 | Connected |  | N
National Grid | METHUEN | 301272 | 01844 | 7.6 | Solar | 05_12_7W2 | 08/03/2020 | 08/05/2020 | 1 | 0 | 1 | 08/06/2020 | 08/06/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 |  | 8/4/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 637943 | 01453 | 6.98 | Solar | 05_14_43L4 | 09/05/2024 | 10/16/2024 | 4 | 0 | 4 | 10/17/2024 | 10/17/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/05/2024 | 11/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | WORCESTER | 193954 | 01604 | 357 | Hydro | 05_14_5J45 | 08/31/2018 | 09/27/2018 | 18 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2019 |  | 2/26/2021 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  | 2/12/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 200801 | 01550 | 7.6 | Solar | 05_14_74L4 | 11/08/2018 | 12/31/2018 | 2 | 2 | 0 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 11/08/2018 | 3/10/2020 | Y | EXP | 418 | 09/05/2019 | 09/26/2019 | 21 | 0 | 21 |  |  | 10/9/2019 | Connected |  | N
National Grid | GARDNER | 621331 | 01440 | 9.45 | Solar | 05_01_219W2 | 07/03/2024 | 07/05/2024 | 7 | 5 | 2 | 10/03/2024 | 10/03/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2024 | 07/03/2024 | 11/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | FALL RIVER | 625256 | 02721 | 3.8 | Solar | 05_01_27W1 | 07/16/2024 | 07/29/2024 | 3 | 0 | 3 | 07/30/2024 | 07/30/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | WESTBOROUGH | 754770 | 01581 | 15.2 | Solar | 05_01_413L2 | 03/10/2026 | 03/11/2026 | 1 | 0 | 1 | 03/12/2026 | 03/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 620468 | 01905 | 3.8 | Solar | 05_01_607W2 | 06/25/2024 | 07/15/2024 | 3 | 0 | 3 | 07/16/2024 | 07/16/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | REVERE | 634387 | 02151 | 10 | Solar | 05_05_115W53 | 08/21/2024 | 09/17/2024 | 4 | 0 | 4 | 09/18/2024 | 09/18/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2024 | 08/21/2024 | 10/28/2025 | Y | EXP | 365 | 11/14/2024 | 11/13/2024 | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N
National Grid | LAWRENCE | 174127 | 01841 | 13.97 | Solar | 05_05_312W4 | 04/26/2012 | 04/26/2012 | 9 | 0 | 9 | 05/14/2012 | 05/14/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2012 |  | 6/29/2012 | N | EXP | 97 |  |  | 0 | 0 | 0 | 8/29/2012 | 8/29/2012 | 10/10/2012 | Connected |  | N
National Grid | METHUEN | 488328 | 01844 | 6 | Solar | 05_12_29W3 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 | 01/10/2023 | 6/13/2024 | Y | EXP | 365 | 06/09/2023 | 06/09/2023 | 1 | 0 | 1 |  |  | 7/11/2023 | Connected |  | N
National Grid | METHUEN | 311805 | 01844 | 7.6 | Solar | 05_12_7W2 | 09/29/2020 | 10/02/2020 | 2 | 0 | 2 | 10/05/2020 | 10/05/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 643784 | 01453 | 13.12 | Solar | 05_14_43L4 | 09/30/2024 | 10/11/2024 | 4 | 0 | 4 | 10/15/2024 | 10/15/2024 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178560 | 01604 | 432.9 | Solar | 05_14_60L1 | 04/05/2018 | 04/16/2018 | 6 | 6 | 0 |  |  | 44 | 19 | 25 | 07/02/2018 | 10/09/2018 | 69 | 0 | 69 |  |  | 0 | 0 | 0 | 10/09/2018 | 69 | 0 | 69 |  |  | 0 | 0 | 0 | 4/12/2019 | 04/05/2018 | 9/2/2026 | Y | STD | 154 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SOUTHBRIDGE | 215445 | 01550 | 10 | Solar | 05_14_74L4 | 06/25/2019 | 07/02/2019 | 5 | 5 | 0 | 07/03/2019 | 07/03/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 639575 | 01440 | 10 | Solar | 05_01_219W2 | 09/12/2024 | 09/25/2024 | 4 | 0 | 4 | 09/26/2024 | 09/26/2024 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 09/12/2024 | 12/3/2025 | Y | EXP | 365 | 12/19/2024 | 01/07/2025 | 20 | 0 | 20 |  |  | 1/17/2025 | Connected |  | N
National Grid | FALL RIVER | 632259 | 02721 | 10 | Solar | 05_01_27W1 | 08/20/2024 | 08/23/2024 | 3 | 0 | 3 | 08/26/2024 | 08/26/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/20/2024 | 9/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 174118 | 01581 | 1725 | Solar | 05_01_413L2 | 03/15/2012 | 03/15/2012 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 312828 | 01904 | 762 | Solar | 05_01_607W3 | 04/29/2021 | 10/03/2021 | 108 | 98 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/04/2021 | 12/04/2021 | 42 | 4 | 38 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2025 | 04/29/2021 | 2/12/2026 | Y | STD | 2 | 01/01/2026 | 12/31/2025 | 0 | 0 | 0 |  |  | 12/31/2025 | Witness Test |  | N
National Grid | REVERE | 640654 | 02151 | 7.6 | Solar | 05_05_115W53 | 09/18/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/18/2024 | 12/4/2025 | Y | EXP | 365 | 01/03/2025 | 01/14/2025 | 12 | 0 | 12 |  |  | 2/18/2025 | Connected |  | N
National Grid | LAWRENCE | 174164 | 01841 | 10.75 | Solar | 05_05_312W4 | 04/23/2012 | 04/23/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2012 |  | 6/1/2012 | N | EXP | 83 |  |  | 0 | 0 | 0 | 8/23/2012 | 8/23/2012 | 12/21/2012 | Connected |  | N
National Grid | NEWBURY | 573455 | 01951 | 5.8 | Solar | 05_12_29W3 | 12/20/2023 | 01/02/2024 | 6 | 1 | 5 | 01/03/2024 | 01/03/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 | 12/20/2023 | 12/31/2025 | Y | EXP | 365 | 09/10/2024 | 11/18/2025 | 435 | 0 | 435 |  |  | 11/25/2025 | Connected |  | N
National Grid | METHUEN | 318712 | 01844 | 7.6 | Solar | 05_12_7W2 | 10/27/2020 | 11/02/2020 | 3 | 0 | 3 | 11/03/2020 | 11/03/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 644259 | 01453 | 3.8 | Solar | 05_14_43L4 | 10/01/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 12/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 555669 | 01604 | 0 | Solar | 05_14_60L1 | 09/14/2023 | 09/19/2023 | 4 | 3 | 1 | 09/20/2023 | 09/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2023 |  | 10/14/2026 | N | EXP | 1095 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOUTHBRIDGE | 268864 | 01550 | 10 | Solar | 05_14_74L4 | 12/17/2019 | 12/20/2019 | 2 | 0 | 2 | 12/23/2019 | 12/23/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2020 | 12/17/2019 | 12/17/2020 | Y | EXP | 365 | 07/16/2020 | 08/19/2020 | 34 | 0 | 34 |  |  | 10/28/2020 | Connected |  | N
National Grid | GARDNER | 644853 | 01440 | 10 | Solar | 05_01_219W2 | 10/03/2024 | 10/29/2024 | 3 | 0 | 3 | 10/30/2024 | 10/30/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/03/2024 | 12/13/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | FALL RIVER | 634251 | 02721 | 3.8 | Solar | 05_01_27W1 | 08/21/2024 | 09/18/2024 | 15 | 13 | 2 | 09/19/2024 | 09/19/2024 | 83 | 66 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | WESTBOROUGH | 175101 | 01581 | 2000 | Solar | 05_01_413L2 | 10/25/2012 | 10/25/2012 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2012 | 12/31/2012 | 27 | 0 | 27 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/13/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175152 | 01904 | 750 | Solar | 05_01_607W3 | 11/01/2013 | 11/20/2013 | 11 | 11 | 0 |  |  | 0 | 0 | 0 | 01/02/2014 |  | 1053 | 203 | 850 | 11/20/2013 | 01/02/2014 | 28 | 28 | 0 |  | 1053 | 203 | 850 |  |  | 0 | 0 | 0 | 9/11/2015 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 644253 | 02151 | 7.6 | Solar | 05_05_115W53 | 10/01/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | METHUEN | 174272 | 01844 | 1820 | Solar | 05_05_312W4 | 11/01/2011 | 11/01/2011 | 61 | 0 | 61 |  |  | 0 | 0 | 0 | 02/01/2013 | 02/01/2013 | 0 | 0 | 0 | 02/13/2012 | 04/11/2012 | 40 | 0 | 40 | 02/01/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2013 | 11/01/2011 | 1/16/2012 | Y | STD | 409 | 10/24/2013 | 12/12/2013 | 33 | 0 | 33 | 2/12/2014 | 2/12/2014 | 4/1/2014 | Connected |  | N
National Grid | NEWBURY | 574706 | 01951 | 3.8 | Solar | 05_12_29W3 | 12/01/2023 | 12/06/2023 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | METHUEN | 462753 | 01844 | 7.6 | Solar | 05_12_7W2 | 10/06/2022 | 10/12/2022 | 4 | 1 | 3 | 10/13/2022 | 10/13/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 645461 | 01453 | 7.54 | Solar | 05_14_43L4 | 10/11/2024 | 10/21/2024 | 2 | 0 | 2 | 10/22/2024 | 10/22/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 |  | 11/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | WORCESTER | 703373 | 01604 | 2.9 | Solar | 05_14_60L1 | 07/08/2025 | 07/10/2025 | 2 | 0 | 2 | 07/11/2025 | 07/11/2025 | 164 | 151 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | STURBRIDGE | 273564 | 01566 | 360 | Natural Gas | 05_14_74L4 | 05/12/2020 | 06/04/2020 | 16 | 10 | 6 |  |  | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2022 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 647432 | 01440 | 3.8 | Solar | 05_01_219W2 | 10/30/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | FALL RIVER | 636951 | 02721 | 3.8 | Solar | 05_01_27W1 | 08/30/2024 | 09/13/2024 | 3 | 0 | 3 | 09/16/2024 | 09/16/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 175596 | 01581 | 480 | Solar | 05_01_413L2 | 08/01/2014 | 08/01/2014 | 6 | 0 | 6 | 08/12/2014 | 08/12/2014 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/15/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 178561 | 01904 | 1666 | Solar | 05_01_607W3 | 04/05/2018 | 04/05/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 10/26/2018 | 137 | 70 | 67 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 647339 | 02151 | 10 | Solar | 05_05_115W53 | 10/15/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/15/2024 | 11/27/2025 | Y | EXP | 365 | 01/07/2025 | 01/06/2025 | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | Y
National Grid | METHUEN | 174274 | 01844 | 1000 | Solar | 05_05_312W4 | 11/01/2011 | 11/01/2011 | 63 | 0 | 63 |  |  | 0 | 0 | 0 | 04/12/2012 | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/16/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 585391 | 01951 | 2.03 | Solar | 05_12_29W3 | 01/29/2024 | 01/30/2024 | 1 | 0 | 1 | 01/31/2024 | 01/31/2024 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 503442 | 01841 | 10 | Solar | 05_12_7W2 | 03/19/2023 | 03/21/2023 | 2 | 0 | 2 | 03/22/2023 | 03/22/2023 | 25 | 0 | 25 | 05/08/2023 | 06/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 06/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 7/31/2024 | N | EXP | 365 | 08/01/2023 | 07/31/2023 | 0 | 0 | 0 |  |  | 8/8/2023 | Connected |  | Y
National Grid | LEOMINSTER | 649010 | 01453 | 10 | Solar | 05_14_43L4 | 11/18/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | WORCESTER | 752120 | 01604 | 11.5 | Solar | 05_14_60L1 | 02/23/2026 | 02/26/2026 | 3 | 0 | 3 | 02/27/2026 | 02/27/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2026 |  | 3/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | STURBRIDGE | 281460 | 01566 | 10 | Solar | 05_14_74L4 | 03/11/2020 | 03/23/2020 | 0 | 0 | 0 | 03/24/2020 | 03/24/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2020 | 03/11/2020 | 3/22/2021 | Y | EXP | 365 | 05/27/2020 | 06/11/2020 | 15 | 0 | 15 |  |  | 6/15/2020 | Connected |  | N
National Grid | WINCHENDON | 647479 | 01475 | 5.76 | Solar | 05_01_219W2 | 10/29/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/29/2024 | 1/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N
National Grid | FALL RIVER | 636882 | 02721 | 10 | Solar | 05_01_27W1 | 08/30/2024 | 09/11/2024 | 1 | 0 | 1 | 09/12/2024 | 09/12/2024 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 175595 | 01581 | 996 | Solar | 05_01_413L2 | 08/01/2014 | 08/01/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2014 | 09/09/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 | 08/01/2014 | 4/1/2016 | Y | STD | 340 | 05/24/2016 | 06/28/2016 | 23 | 0 | 23 | 6/27/2016 | 6/27/2016 | 6/30/2016 | Connected |  | N
National Grid | LYNN | 200441 | 01905 | 4998 | Solar | 05_01_607W3 | 11/15/2018 | 11/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2018 | 01/25/2019 | 57 | 20 | 37 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 651440 | 02151 | 4.35 | Solar | 05_05_115W53 | 11/01/2024 | 12/09/2024 | 8 | 4 | 4 | 12/10/2024 | 12/10/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/01/2024 | 3/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | LAWRENCE | 174273 | 01841 | 0 | Solar | 05_05_312W4 | 11/01/2011 | 11/01/2011 | 63 | 0 | 63 |  |  | 0 | 0 | 0 | 04/12/2012 | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/16/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 588850 | 01951 | 5 | Solar | 05_12_29W3 | 02/23/2024 | 03/06/2024 | 9 | 8 | 1 | 03/07/2024 | 03/07/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/23/2024 | 6/24/2025 | Y | EXP | 365 | 07/25/2024 | 10/30/2024 | 98 | 0 | 98 |  |  | 11/14/2024 | Connected |  | N
National Grid | METHUEN | 516902 | 01844 | 6.38 | Solar | 05_12_7W2 | 08/07/2023 |  | 84 | 26 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 649801 | 01453 | 5.2 | Solar | 05_14_43L4 | 10/30/2024 | 11/12/2024 | 4 | 0 | 4 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/30/2024 | 1/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | WORCESTER | 175109 | 01604 | 1992 | Solar | 05_14_60L1 | 04/22/2013 | 04/22/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2013 | 06/24/2013 | 35 | 0 | 35 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2014 | 04/22/2013 | 12/31/2016 | Y | STD | 943 | 01/03/2017 | 04/18/2017 | 72 | 0 | 72 |  |  | 5/4/2017 | Connected |  | N
National Grid | STURBRIDGE | 590983 | 01566 | 6 | Solar | 05_14_74L4 | 03/11/2024 | 03/13/2024 | 2 | 0 | 2 | 03/14/2024 | 03/14/2024 | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 | 03/11/2024 | 7/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | WINCHENDON | 648304 | 01475 | 10 | Solar | 05_01_219W2 | 10/21/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2024 | 10/21/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2025 | Connected |  | N
National Grid | FALL RIVER | 654101 | 02721 | 11.89 | Solar | 05_01_27W1 | 11/25/2024 | 01/14/2025 | 19 | 17 | 2 | 01/15/2025 | 01/15/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | Y
National Grid | WESTBOROUGH | 175664 | 01581 | 996 | Solar | 05_01_413L2 | 08/11/2014 | 08/11/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 09/09/2014 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 | 08/11/2014 | 3/15/2016 | Y | STD | 323 | 05/24/2016 | 06/28/2016 | 23 | 0 | 23 | 6/27/2016 | 6/27/2016 | 6/30/2016 | Connected |  | N
National Grid | LYNN | 282444 | 01905 | 831 | Natural Gas | 05_01_607W3 | 05/20/2020 | 07/06/2020 | 31 | 25 | 6 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 654700 | 02151 | 3.8 | Solar | 05_05_115W53 | 11/19/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/19/2024 | 3/18/2026 | Y | EXP | 365 | 04/02/2025 | 04/18/2025 | 17 | 0 | 17 |  |  | 5/3/2025 | Connected |  | N
National Grid | METHUEN | 175780 | 01844 | 866 | Solar | 05_05_312W4 | 07/22/2015 | 07/22/2015 | 10 | 10 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2015 | 08/28/2015 | 17 | 0 | 17 |  | 0 | 0 | 0 | 01/05/2016 | 05/17/2016 | 91 | 10 | 81 | 6/3/2016 | 07/22/2015 | 7/27/2016 | Y | STD | 54 | 11/09/2016 | 01/25/2017 | 50 | 0 | 50 | 1/26/2017 | 1/26/2017 | 2/1/2017 | Connected |  | N
National Grid | NEWBURY | 595104 | 01951 | 3.8 | Solar | 05_12_29W3 | 04/09/2024 | 04/10/2024 | 1 | 0 | 1 | 04/11/2024 | 04/11/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/09/2024 | 5/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | METHUEN | 530131 | 01844 | 8.12 | Solar | 05_12_7W2 | 07/12/2023 | 08/02/2023 | 16 | 15 | 1 | 08/03/2023 | 08/03/2023 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 651165 | 01453 | 6.825 | Solar | 05_14_43L4 | 10/31/2024 | 11/22/2024 | 4 | 0 | 4 | 11/25/2024 | 11/25/2024 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 10/31/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | WORCESTER | 175203 | 01604 | 3000 | Solar | 05_14_60L1 | 11/30/2012 | 11/30/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2012 | 01/14/2013 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 593130 | 01566 | 10 | Solar | 05_14_74L4 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/03/2024 | 5/31/2025 | Y | EXP | 365 | 07/16/2024 | 11/18/2024 | 126 | 0 | 126 |  |  | 12/21/2024 | Connected |  | N
National Grid | GARDNER | 655579 | 01440 | 3.8 | Solar | 05_01_219W2 | 11/20/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | FALL RIVER | 656846 | 02721 | 6 | Solar | 05_01_27W1 | 11/26/2024 | 03/20/2025 | 21 | 16 | 5 | 02/24/2025 | 02/24/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 11/26/2024 | 4/14/2026 | Y | EXP | 365 | 06/24/2025 | 07/16/2025 | 23 | 0 | 23 |  |  | 7/22/2025 | Connected |  | N
National Grid | WESTBOROUGH | 176660 | 01581 | 1440 | Solar | 05_01_413L2 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 439984 | 01905 | 9.86 | Solar | 05_01_607W3 | 06/29/2022 | 06/30/2022 | 1 | 0 | 1 | 07/01/2022 | 07/01/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 |  | 8/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 660461 | 02151 | 4.64 | Solar | 05_05_115W53 | 12/13/2024 | 01/30/2025 | 28 | 25 | 3 | 01/31/2025 | 01/31/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176096 | 01844 | 300 | Solar | 05_05_312W4 | 04/03/2015 | 04/03/2015 | 5 | 0 | 5 | 04/13/2015 | 04/13/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2015 |  | 2/7/2018 | N | EXP | 1024 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 602833 | 01951 | 3.8 | Solar | 05_12_29W3 | 04/10/2024 | 04/11/2024 | 1 | 0 | 1 | 04/12/2024 | 04/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/10/2024 | 5/18/2025 | Y | EXP | 365 | 08/22/2024 | 02/12/2025 | 175 | 0 | 175 |  |  | 3/20/2025 | Connected |  | N
National Grid | METHUEN | 591484 | 01844 | 3.8 | Solar | 05_12_7W2 | 02/27/2024 | 04/11/2024 | 30 | 25 | 5 | 04/12/2024 | 04/12/2024 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 652499 | 01453 | 9.5 | Solar | 05_14_43L4 | 11/06/2024 | 11/26/2024 | 4 | 1 | 3 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176968 | 01604 | 20 | Solar | 05_14_60L1 | 10/04/2016 | 10/04/2016 | 2 | 2 | 0 | 10/06/2016 | 10/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2016 |  | 10/9/2017 | N | EXP | 361 |  |  | 0 | 0 | 0 | 8/31/2017 | 8/31/2017 | 8/31/2017 | Connected |  | N
National Grid | SOUTHBRIDGE | 621133 | 01550 | 15.2 | Solar | 05_14_74L4 | 06/29/2024 | 07/11/2024 | 8 | 6 | 2 | 07/12/2024 | 07/12/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 659724 | 01440 | 2.32 | Solar | 05_01_219W2 | 12/10/2024 | 01/03/2025 | 3 | 0 | 3 | 01/06/2025 | 01/06/2025 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | FALL RIVER | 658492 | 02721 | 7.6 | Solar | 05_01_27W1 | 12/16/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 46 | 21 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | WESTBOROUGH | 177438 | 01581 | 260 | Solar | 05_01_413L2 | 07/01/2016 | 07/01/2016 | 2 | 2 | 0 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2016 | 07/01/2016 | 10/6/2017 | Y | EXP | 382 | 07/17/2017 | 09/27/2017 | 51 | 0 | 51 | 9/29/2017 | 9/29/2017 | 9/29/2017 | Connected |  | N
National Grid | LYNN | 641030 | 01904 | 9.86 | Solar | 05_01_607W3 | 09/17/2024 | 11/05/2024 | 11 | 9 | 2 | 11/06/2024 | 11/06/2024 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2024 | Connected |  | N
National Grid | REVERE | 661398 | 02151 | 3.8 | Solar | 05_05_115W53 | 12/19/2024 | 01/29/2025 | 16 | 11 | 5 | 01/30/2025 | 01/30/2025 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176165 | 01844 | 850 | Solar | 05_05_312W4 | 04/17/2015 | 04/17/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2015 | 05/07/2015 | 11 | 0 | 11 |  | 0 | 0 | 0 | 12/22/2015 | 05/11/2016 | 95 | 0 | 95 | 6/3/2016 | 04/17/2015 | 3/17/2017 | Y | STD | 287 | 10/13/2016 | 04/07/2017 | 120 | 0 | 120 | 4/26/2017 | 4/26/2017 | 4/26/2017 | Connected |  | N
National Grid | NEWBURY | 616805 | 01950 | 2.9 | Solar | 05_12_29W3 | 06/10/2024 |  | 39 | 37 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 657188 | 01841 | 15.2 | Solar | 05_14_43L4 | 11/26/2024 | 01/27/2025 | 3 | 0 | 3 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | LEOMINSTER | 178071 | 01453 | 15.2 | Solar | 05_14_60L1 | 10/31/2017 | 10/31/2017 | 0 | 0 | 0 | 11/06/2017 | 11/06/2017 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 11/6/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 624281 | 01604 | 10 | Solar | 05_14_74L4 | 07/15/2024 | 07/23/2024 | 1 | 0 | 1 | 07/24/2024 | 07/24/2024 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 660535 | 01550 | 10 | Solar | 05_01_219W2 | 12/13/2024 | 01/08/2025 | 1 | 0 | 1 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 661842 | 01440 | 3.8 | Solar | 05_01_27W1 | 01/06/2025 | 02/11/2025 | 22 | 18 | 4 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/06/2025 | 4/28/2026 | Y | EXP | 365 | 06/14/2025 | 02/03/2026 | 235 | 6 | 229 |  |  | 3/2/2026 | Connected |  | N
National Grid | FALL RIVER | 178281 | 02721 | 7.6 | Solar | 05_01_413L2 | 02/23/2018 | 02/23/2018 | 4 | 4 | 0 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2018 |  | 3/3/2019 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  | 12/21/2018 | Connected |  | N
National Grid | WESTBOROUGH | 644604 | 01581 | 10 | Solar | 05_01_607W3 | 10/02/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/02/2024 | 12/24/2025 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 663847 | 01905 | 3.8 | Solar | 05_05_115W53 | 01/06/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 176494 | 02151 | 15.25 | Solar | 05_05_312W4 | 12/10/2015 | 12/10/2015 | 29 | 29 | 0 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 12/15/2016 | N | EXP | 314 |  |  | 0 | 0 | 0 | 2/18/2016 | 2/18/2016 | 2/24/2016 | Connected |  | N
National Grid | METHUEN | 622079 | 01844 | 10 | Solar | 05_12_29W3 | 07/02/2024 | 07/18/2024 | 9 | 8 | 1 | 07/19/2024 | 07/19/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/02/2024 | 8/7/2025 | Y | EXP | 365 | 10/04/2024 | 02/20/2025 | 140 | 0 | 140 |  |  | 3/3/2025 | Connected |  | N
National Grid | NEWBURY | 600033 | 01951 | 10 | Solar | 05_12_7W2 | 03/29/2024 | 04/15/2024 | 11 | 8 | 3 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 03/29/2024 | 5/14/2025 | Y | EXP | 365 | 07/31/2024 | 08/30/2024 | 31 | 0 | 31 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 660661 | 01844 | 7.6 | Solar | 05_14_43L4 | 12/14/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | LEOMINSTER | 178240 | 01453 | 10 | Solar | 05_14_60L1 | 02/20/2018 | 02/20/2018 | 6 | 6 | 0 | 02/28/2018 | 02/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2018 |  | 2/25/2019 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  | 10/17/2018 | Connected |  | N
National Grid | WORCESTER | 626258 | 01604 | 10 | Solar | 05_14_74L4 | 07/19/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/19/2024 | 8/26/2025 | Y | EXP | 365 | 11/26/2024 | 03/25/2025 | 120 | 0 | 120 |  |  | 4/7/2025 | Connected |  | N
National Grid | STURBRIDGE | 663860 | 01566 | 3.8 | Solar | 05_01_219W2 | 01/06/2025 | 01/21/2025 | 4 | 0 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 | 01/06/2025 | 3/17/2026 | Y | EXP | 365 | 04/30/2025 | 10/24/2025 | 178 | 0 | 178 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 662937 | 01475 | 7.6 | Solar | 05_01_27W1 | 12/30/2024 | 02/12/2025 | 2 | 0 | 2 | 02/13/2025 | 02/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2025 | Connected |  | N
National Grid | FALL RIVER | 178286 | 02721 | 5 | Solar | 05_01_413L2 | 03/28/2018 | 03/28/2018 | 6 | 0 | 6 | 04/06/2018 | 04/06/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 | 03/28/2018 | 4/3/2019 | Y | EXP | 336 |  |  | 0 | 0 | 0 |  |  | 3/26/2019 | Connected |  | N
National Grid | WESTBOROUGH | 656728 | 01581 | 5.76 | Solar | 05_01_607W3 | 11/25/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | LYNN | 669664 | 01902 | 5.76 | Solar | 05_05_115W53 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 | 02/03/2025 | 4/7/2026 | Y | EXP | 365 | 04/29/2025 | 06/24/2025 | 57 | 0 | 57 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 176745 | 02151 | 50.4 | Solar | 05_05_312W4 | 11/02/2015 | 11/02/2015 | 3 | 3 | 0 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2015 |  | 11/8/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 1/4/2017 | 1/4/2017 | 1/6/2017 | Connected |  | N
National Grid | METHUEN | 630545 | 01844 | 3.8 | Solar | 05_12_29W3 | 08/09/2024 | 08/21/2024 | 3 | 0 | 3 | 08/22/2024 | 08/22/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | NEWBURY | 604225 | 01951 | 3.48 | Solar | 05_12_7W2 | 04/16/2024 |  | 75 | 75 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 661675 | 01844 | 10 | Solar | 05_14_43L4 | 12/20/2024 | 01/22/2025 | 5 | 1 | 4 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 12/20/2024 | 3/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2025 | Connected |  | N
National Grid | LEOMINSTER | 178380 | 01453 | 20 | Solar | 05_14_60L1 | 01/15/2018 | 01/15/2018 | 0 | 0 | 0 | 04/10/2018 | 04/10/2018 | 32 | 3 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2018 |  | 1/20/2019 | N | EXP | 241 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 640113 | 01604 | 10 | Solar | 05_14_74L4 | 09/13/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 670221 | 01550 | 39.9 | Solar | 05_01_219W2 | 03/18/2025 | 03/27/2025 | 7 | 4 | 3 | 03/28/2025 | 03/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 5/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | GARDNER | 668077 | 01440 | 3.8 | Solar | 05_01_27W1 | 01/27/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | FALL RIVER | 191126 | 02721 | 3.8 | Solar | 05_01_413L2 | 07/19/2018 | 10/24/2018 | 4 | 4 | 0 | 10/25/2018 | 10/25/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 659120 | 01581 | 0 | Battery Add-On | 05_01_607W3 | 12/06/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 673224 | 01904 | 7.6 | Solar | 05_05_115W53 | 02/25/2025 | 03/14/2025 | 13 | 9 | 4 | 03/17/2025 | 03/17/2025 | 126 | 25 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 178005 | 02151 | 15.2 | Solar | 05_05_312W4 | 04/27/2017 | 04/27/2017 | 8 | 8 | 0 | 05/09/2017 | 05/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2017 |  | 5/2/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 | 8/24/2017 | 8/24/2017 | 8/29/2017 | Connected |  | N
National Grid | METHUEN | 631549 | 01844 | 7.6 | Solar | 05_12_29W3 | 08/09/2024 | 09/12/2024 | 5 | 4 | 1 | 09/13/2024 | 09/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 10/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | NEWBURY | 613662 | 01951 | 11.4 | Solar | 05_12_7W2 | 05/29/2024 | 06/11/2024 | 6 | 4 | 2 | 06/12/2024 | 06/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 | 05/29/2024 | 8/6/2025 | Y | EXP | 365 | 08/21/2024 | 10/03/2024 | 44 | 0 | 44 |  |  | 2/8/2025 | Connected |  | N
National Grid | METHUEN | 662855 | 01844 | 7.6 | Solar | 05_14_43L4 | 12/27/2024 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | LEOMINSTER | 190362 | 01453 | 15.2 | Solar | 05_14_60L1 | 07/25/2018 | 08/28/2018 | 23 | 23 | 0 | 08/29/2018 | 08/29/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 |  | 9/6/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2019 | Connected |  | N
National Grid | WORCESTER | 640945 | 01604 | 7.6 | Solar | 05_14_74L4 | 09/17/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 693924 | 01566 | 6.96 | Solar | 05_01_219W2 | 05/23/2025 | 06/03/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2025 | Connected |  | N
National Grid | GARDNER | 679786 | 01440 | 3.8 | Solar | 05_01_27W1 | 03/21/2025 | 06/03/2025 | 3 | 0 | 3 | 06/11/2025 | 06/11/2025 | 44 | 32 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 199144 | 02721 | 11.4 | Solar | 05_01_413L2 | 10/22/2018 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 673971 | 01568 | 11.5 | Solar | 05_01_607W3 | 02/27/2025 | 03/10/2025 | 7 | 4 | 3 | 03/11/2025 | 03/11/2025 | 108 | 85 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 673848 | 01905 | 4.93 | Solar | 05_05_115W53 | 02/24/2025 | 03/27/2025 | 4 | 2 | 2 | 03/28/2025 | 03/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 02/24/2025 | 8/29/2026 | Y | EXP | 365 | 09/30/2025 | 10/08/2025 | 9 | 0 | 9 |  |  | 10/10/2025 | Connected |  | N
National Grid | REVERE | 178334 | 02151 | 10 | Solar | 05_05_312W4 | 11/15/2017 | 11/15/2017 | 70 | 59 | 11 | 03/09/2018 | 03/09/2018 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2018 |  | 11/22/2018 | N | EXP | 255 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 633685 | 01844 | 10 | Solar | 05_12_29W3 | 08/19/2024 | 08/23/2024 | 2 | 0 | 2 | 08/26/2024 | 08/26/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | Y
National Grid | NEWBURY | 616866 | 01951 | 3 | Solar | 05_12_7W2 | 06/10/2024 |  | 18 | 16 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 669208 | 01841 | 3.8 | Solar | 05_14_43L4 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 | 02/03/2025 | 4/12/2026 | Y | EXP | 365 | 05/15/2025 | 11/03/2025 | 172 | 3 | 169 |  |  | 7/29/2025 | Connected |  | N
National Grid | LEOMINSTER | 296240 | 01453 | 3.8 | Solar | 05_14_60L1 | 07/03/2020 | 07/08/2020 | 2 | 0 | 2 | 07/09/2020 | 07/09/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 642225 | 01604 | 10 | Solar | 05_14_74L4 | 09/23/2024 | 10/24/2024 | 2 | 0 | 2 | 10/25/2024 | 10/25/2024 | 98 | 78 | 20 | 03/31/2025 | 04/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 04/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 4/30/2025 | 09/23/2024 | 5/28/2026 | Y | EXP | 365 | 06/28/2025 | 12/22/2025 | 178 | 0 | 178 |  |  | 12/15/2025 | Connected |  | N
National Grid | STURBRIDGE | 696159 | 01566 | 5.76 | Solar | 05_01_219W2 | 06/11/2025 | 06/26/2025 | 2 | 0 | 2 | 07/02/2025 | 07/02/2025 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2026 | Connected |  | N
National Grid | GARDNER | 701051 | 01440 | 3.8 | Solar | 05_01_27W1 | 06/25/2025 | 07/10/2025 | 4 | 0 | 4 | 07/17/2025 | 07/17/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 | 06/25/2025 | 8/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | FALL RIVER | 204532 | 02721 | 7.6 | Solar | 05_01_413L2 | 01/10/2019 | 01/23/2019 | 7 | 0 | 7 | 01/24/2019 | 01/24/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2019 | 01/10/2019 | 8/19/2020 | Y | EXP | 365 | 06/24/2020 | 06/30/2020 | 6 | 0 | 6 |  |  | 7/30/2020 | Connected |  | N
National Grid | UPTON | 674436 | 01568 | 3.8 | Solar | 05_01_607W3 | 02/26/2025 | 04/25/2025 | 2 | 0 | 2 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 02/26/2025 | 7/31/2026 | Y | EXP | 365 | 08/07/2025 | 10/24/2025 | 79 | 0 | 79 |  |  | 1/16/2026 | Connected |  | N
National Grid | LYNN | 684035 | 01905 | 7.6 | Solar | 05_05_115W53 | 04/14/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 178679 | 02151 | 15.2 | Solar | 05_05_312W4 | 04/11/2018 | 04/11/2018 | 16 | 0 | 16 | 05/21/2018 | 05/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/17/2019 | N | EXP | 331 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | METHUEN | 655348 | 01844 | 6.72 | Solar | 05_12_29W3 | 11/19/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | NEWBURY | 623418 | 01951 | 4.64 | Solar | 05_12_7W2 | 07/09/2024 | 07/31/2024 | 11 | 8 | 3 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 672120 | 01844 | 7.6 | Solar | 05_14_43L4 | 02/14/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | LEOMINSTER | 316180 | 01453 | 6 | Solar | 05_14_60L1 | 10/15/2020 | 10/20/2020 | 2 | 0 | 2 | 10/21/2020 | 10/21/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 | 10/15/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2021 | Connected |  | N
National Grid | WORCESTER | 657516 | 01604 | 7.6 | Solar | 05_14_74L4 | 11/27/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/7/2026 | N | EXP | 365 | 03/11/2025 | 03/25/2025 | 15 | 0 | 15 |  |  | 5/22/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 701355 | 01550 | 11.5 | Solar | 05_01_219W2 | 06/27/2025 | 07/08/2025 | 6 | 3 | 3 | 07/09/2025 | 07/09/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2025 | Connected |  | N
National Grid | GARDNER | 710806 | 01440 | 7.22 | Solar | 05_01_27W1 | 08/29/2025 | 10/13/2025 | 4 | 0 | 4 | 10/24/2025 | 10/24/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 225333 | 02721 | 10 | Solar | 05_01_413L2 | 05/07/2019 | 07/19/2019 | 54 | 53 | 1 | 07/22/2019 | 07/22/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 459174 | 01581 | 240 | Solar | 05_01_607W4 | 09/23/2022 | 10/17/2022 | 16 | 8 | 8 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LYNN | 687844 | 01905 | 10.24 | Solar | 05_05_115W53 | 04/28/2025 | 05/28/2025 | 2 | 0 | 2 | 05/29/2025 | 05/29/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 | 04/28/2025 | 7/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | REVERE | 190317 | 02151 | 3.8 | Solar | 05_05_312W4 | 07/10/2018 | 08/15/2018 | 9 | 2 | 7 | 08/16/2018 | 08/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 660896 | 01844 | 3.8 | Solar | 05_12_29W3 | 12/16/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/16/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | NEWBURY | 632337 | 01951 | 6 | Solar | 05_12_7W2 | 08/13/2024 | 08/30/2024 | 2 | 0 | 2 | 09/03/2024 | 09/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2024 |  | 9/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | METHUEN | 672915 | 01844 | 10 | Solar | 05_14_43L4 | 02/19/2025 | 04/08/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 344862 | 01453 | 7.6 | Solar | 05_14_60L1 | 03/03/2021 | 03/04/2021 | 0 | 0 | 0 | 03/05/2021 | 03/05/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 |  | 12/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2022 | Connected |  | N
National Grid | WORCESTER | 661078 | 01604 | 5 | Solar | 05_14_74L4 | 12/17/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 715054 | 01566 | 7.6 | Solar | 05_01_219W2 | 09/10/2025 | 09/16/2025 | 4 | 0 | 4 | 09/17/2025 | 09/17/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2026 | Connected |  | N
National Grid | GARDNER | 723925 | 01440 | 7.6 | Solar | 05_01_27W1 | 10/03/2025 | 12/09/2025 | 3 | 0 | 3 | 12/10/2025 | 12/10/2025 | 25 | 13 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 |  | 2/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2026 | Connected |  | N
National Grid | FALL RIVER | 260850 | 02721 | 10 | Solar | 05_01_413L2 | 10/28/2019 | 10/31/2019 | 3 | 3 | 0 | 11/01/2019 | 11/01/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 | 10/28/2019 | 10/28/2020 | Y | EXP | 365 | 02/19/2020 | 03/03/2020 | 13 | 0 | 13 |  |  | 3/6/2020 | Connected |  | N
National Grid | WESTBOROUGH | 722236 | 01581 | 10 | Solar | 05_01_607W4 | 09/26/2025 | 10/03/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 696536 | 01905 | 7.6 | Solar | 05_05_115W54 | 06/05/2025 | 06/17/2025 | 4 | 0 | 4 | 07/17/2025 | 07/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 9/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | REVERE | 194239 | 02151 | 15.2 | Solar | 05_05_312W4 | 08/22/2018 | 09/19/2018 | 19 | 19 | 0 | 09/20/2018 | 09/20/2018 | 248 | 0 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 660840 | 01844 | 5.76 | Solar | 05_12_29W3 | 12/31/2024 | 01/16/2025 | 6 | 0 | 6 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | NEWBURY | 642706 | 01951 | 5.76 | Solar | 05_12_7W2 | 09/25/2024 | 10/04/2024 | 1 | 0 | 1 | 10/07/2024 | 10/07/2024 | 68 | 44 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | LAWRENCE | 673315 | 01841 | 10 | Solar | 05_14_43L4 | 02/20/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 349237 | 01453 | 0 | Solar | 05_14_60L1 | 04/08/2021 | 04/27/2021 | 12 | 12 | 0 | 04/28/2021 | 04/28/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2021 |  | 8/24/2022 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 665950 | 01604 | 0 | Solar | 05_14_74L4 | 01/15/2025 | 01/16/2025 | 1 | 0 | 1 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 01/15/2025 | 6/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | STURBRIDGE | 729072 | 01566 | 11.5 | Solar | 05_01_219W2 | 11/04/2025 | 11/10/2025 | 4 | 0 | 4 | 11/12/2025 | 11/12/2025 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 735996 | 01440 | 5.76 | Solar | 05_01_27W1 | 11/24/2025 | 12/22/2025 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 313745 | 02724 | 10 | Solar | 05_01_413L2 | 10/07/2020 | 10/27/2020 | 13 | 12 | 1 | 10/28/2020 | 10/28/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  | 10/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2021 | Connected |  | N
National Grid | WESTBOROUGH | 747256 | 01581 | 0 | Battery Add-On | 05_01_607W4 | 01/23/2026 | 01/27/2026 | 2 | 0 | 2 | 01/28/2026 | 01/28/2026 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 759915 | 01904 | 150 | Solar | 05_05_115W54 | 03/31/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | REVERE | 207296 | 02151 | 15.2 | Solar | 05_05_312W4 | 01/28/2019 | 02/11/2019 | 9 | 0 | 9 | 02/12/2019 | 02/12/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 | 01/28/2019 | 9/23/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 662949 | 01844 | 3.8 | Solar | 05_12_29W3 | 12/30/2024 | 01/13/2025 | 4 | 0 | 4 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 643644 | 01951 | 2.61 | Solar | 05_12_7W2 | 09/30/2024 | 10/08/2024 | 5 | 1 | 4 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 677373 | 01844 | 5.76 | Solar | 05_14_43L4 | 03/12/2025 | 03/26/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | LEOMINSTER | 367210 | 01453 | 7.6 | Solar | 05_14_60L1 | 07/01/2021 | 11/01/2021 | 84 | 63 | 21 | 11/02/2021 | 11/02/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 |  | 10/31/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 668181 | 01604 | 7.6 | Solar | 05_14_74L4 | 01/27/2025 | 02/17/2025 | 15 | 14 | 1 | 02/18/2025 | 02/18/2025 | 51 | 30 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 749323 | 01550 | 0 | Battery Add-On | 05_01_219W2 | 02/04/2026 | 02/10/2026 | 4 | 0 | 4 | 02/11/2026 | 02/11/2026 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 177653 | 01440 | 464 | Solar | 05_01_27W2 | 09/29/2017 | 09/29/2017 | 14 | 8 | 6 | 10/20/2017 | 10/20/2017 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/4/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 335828 | 02724 | 0 | Other | 05_01_413L2 | 04/07/2021 | 04/30/2021 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 750045 | 01568 | 250 | Solar | 05_01_607W4 | 03/03/2026 | 03/17/2026 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2026 |  | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 418915 | 01905 | 15.2 | Solar | 05_05_115W54 | 03/21/2022 | 03/25/2022 | 4 | 3 | 1 | 03/28/2022 | 03/28/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 221730 | 02151 | 0 | Solar | 05_05_312W4 | 06/19/2019 | 06/26/2019 | 3 | 0 | 3 | 06/27/2019 | 06/27/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 | 06/19/2019 | 11/8/2020 | Y | EXP | 365 | 07/07/2020 | 10/10/2020 | 96 | 5 | 91 |  |  | 11/12/2020 | Connected |  | N
National Grid | LAWRENCE | 664528 | 01841 | 7.6 | Solar | 05_12_29W3 | 01/09/2025 | 02/26/2025 | 4 | 1 | 3 | 02/27/2025 | 02/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 643619 | 01951 | 8.99 | Solar | 05_12_7W2 | 09/30/2024 | 10/08/2024 | 5 | 1 | 4 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/30/2024 | 12/23/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | METHUEN | 678663 | 01844 | 15.96 | Solar | 05_14_43L4 | 03/18/2025 | 04/07/2025 | 14 | 9 | 5 | 04/08/2025 | 04/08/2025 | 33 | 19 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | LEOMINSTER | 421113 | 01453 | 0 | Solar | 05_14_60L1 | 03/31/2022 | 04/04/2022 | 2 | 0 | 2 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2022 |  | 4/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2022 | Connected |  | N
National Grid | WORCESTER | 679170 | 01605 | 10 | Solar | 05_14_74L4 | 03/19/2025 | 05/22/2025 | 4 | 0 | 4 | 05/23/2025 | 05/23/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 435107 | 01550 | 0 | Other | 05_01_219W3 | 07/05/2022 | 10/20/2022 | 75 | 65 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2022 | 11/08/2022 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | GARDNER | 193702 | 01440 | 832.5 | Solar | 05_01_27W2 | 09/18/2018 | 10/31/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/01/2018 | 04/01/2019 | 101 | 82 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 | 09/18/2018 | 4/25/2024 | Y | STD | 1142 | 05/18/2023 | 04/22/2024 | 339 | 144 | 195 |  |  | 4/15/2024 | Connected |  | N
National Grid | FALL RIVER | 418074 | 02721 | 15.2 | Solar | 05_01_413L2 | 03/16/2022 | 03/18/2022 | 3 | 2 | 1 | 03/21/2022 | 03/21/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2022 |  | 4/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2022 | Connected |  | N
National Grid | WESTBOROUGH | 752918 | 01581 | 10 | Solar | 05_01_607W4 | 02/24/2026 | 02/27/2026 | 3 | 0 | 3 | 03/25/2026 | 03/25/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 439740 | 01904 | 15.2 | Solar | 05_05_115W54 | 06/23/2022 |  | 42 | 33 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 230666 | 02151 | 0 | Solar | 05_05_312W4 | 05/24/2019 | 06/18/2019 | 15 | 10 | 5 | 06/19/2019 | 06/19/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2019 |  | 7/19/2019 | N | EXP | 25 |  |  | 0 | 0 | 0 |  |  | 7/26/2019 | Connected |  | N
National Grid | LAWRENCE | 701959 | 01841 | 3.8 | Solar | 05_12_29W4 | 06/30/2025 | 09/23/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 87 | 74 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NEWBURY | 656953 | 01951 | 7.6 | Solar | 05_12_7W2 | 11/26/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/26/2024 | 2/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | METHUEN | 684928 | 01844 | 7.6 | Solar | 05_14_43L4 | 04/14/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 04/14/2025 | 7/8/2026 | Y | EXP | 365 | 09/25/2025 | 10/30/2025 | 36 | 0 | 36 |  |  | 11/7/2025 | Connected |  | N
National Grid | LEOMINSTER | 508264 | 01453 | 9.57 | Solar | 05_14_60L1 | 03/28/2023 | 03/30/2023 | 2 | 1 | 1 | 03/31/2023 | 03/31/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2023 |  | 5/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | WORCESTER | 681572 | 01605 | 0 | Solar | 05_14_74L4 | 04/02/2025 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 174600 | 01566 | 225 | Solar | 05_01_219W3 | 10/03/2011 | 10/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2011 | 10/03/2011 | 3/1/2012 | Y | EXP | 87 | 02/16/2012 | 02/24/2012 | 5 | 0 | 5 | 8/9/2012 | 8/9/2012 | 3/1/2012 | Connected |  | N
National Grid | GARDNER | 197375 | 01440 | 10 | Solar | 05_01_27W2 | 10/08/2018 | 10/29/2018 | 13 | 13 | 0 | 10/30/2018 | 10/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 471227 | 02721 | 7.6 | Solar | 05_01_413L2 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 155 | 21 | 134 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 174498 | 01568 | 3300 | Wind | 05_01_607W4 | 06/10/2010 | 06/10/2010 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 06/10/2010 | 10/31/2012 | Y | STD | 42 |  |  | 0 | 0 | 0 | 4/12/2013 | 4/12/2013 | 4/4/2013 | Connected |  | N
National Grid | LYNN | 649641 | 01904 | 6.72 | Solar | 05_05_115W54 | 10/25/2024 | 11/15/2024 | 12 | 7 | 5 | 11/18/2024 | 11/18/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | REVERE | 271250 | 02151 | 400 | Solar | 05_05_312W4 | 01/24/2020 | 01/31/2020 | 5 | 1 | 4 |  |  | 34 | 32 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 | 01/24/2020 | 3/10/2022 | Y | STD | 408 | 08/05/2021 | 08/10/2021 | 6 | 0 | 6 |  |  | 3/7/2022 | Connected |  | N
National Grid | METHUEN | 706810 | 01844 | 11.5 | Solar | 05_12_29W4 | 08/25/2025 | 09/02/2025 | 5 | 0 | 5 | 09/03/2025 | 09/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 660061 | 01532 | 10 | Solar | 05_12_7W2 | 12/20/2024 | 01/16/2025 | 4 | 0 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | METHUEN | 684767 | 01844 | 11.4 | Solar | 05_14_43L4 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 8/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | LEOMINSTER | 520810 | 01453 | 0 | Other | 05_14_60L1 | 06/02/2023 | 06/22/2023 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2023 | 08/14/2023 | 37 | 17 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 685925 | 01605 | 11.52 | Solar | 05_14_74L4 | 04/17/2025 | 07/21/2025 | 7 | 2 | 5 | 07/22/2025 | 07/22/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 176977 | 01550 | 35 | Solar | 05_01_219W3 | 12/27/2016 | 12/27/2016 | 4 | 3 | 1 | 01/03/2017 | 01/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2017 |  | 1/2/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 3/30/2017 | 3/30/2017 | 3/30/2017 | Connected |  | N
National Grid | GARDNER | 495536 | 01440 | 11.4 | Solar | 05_01_27W2 | 02/04/2023 | 02/06/2023 | 26 | 25 | 1 | 03/14/2023 | 03/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2023 |  | 4/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/25/2023 | Connected |  | N
National Grid | FALL RIVER | 471147 | 02721 | 10 | Solar | 05_01_413L2 | 11/23/2022 | 11/29/2022 | 3 | 0 | 3 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 | 11/23/2022 | 8/29/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2023 | Connected |  | N
National Grid | WESTBOROUGH | 176405 | 01581 | 1500 | Wind | 05_01_607W4 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2016 | 07/06/2016 | 37 | 13 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/16/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 671800 | 01907 | 3.8 | Solar | 05_05_115W54 | 02/12/2025 | 03/11/2025 | 7 | 2 | 5 | 03/12/2025 | 03/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | REVERE | 286836 | 02151 | 15.2 | Solar | 05_05_312W4 | 04/07/2020 | 04/08/2020 | 0 | 0 | 0 | 04/09/2020 | 04/09/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2020 |  | 4/7/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 749412 | 01841 | 5.76 | Solar | 05_12_29W4 | 02/04/2026 | 02/09/2026 | 4 | 0 | 4 | 02/24/2026 | 02/24/2026 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NEWBURY | 662068 | 01922 | 11.5 | Solar | 05_12_7W2 | 12/20/2024 | 12/30/2024 | 6 | 2 | 4 | 12/31/2024 | 12/31/2024 | 39 | 16 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 685249 | 01841 | 7.6 | Solar | 05_14_43L4 | 04/15/2025 | 05/13/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 603110 | 01453 | 46 | Solar | 05_14_60L1 | 04/10/2024 | 05/29/2024 | 27 | 25 | 2 | 05/30/2024 | 05/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 7/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | WORCESTER | 688618 | 01605 | 3.8 | Solar | 05_14_74L4 | 05/01/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 05/01/2025 | 6/27/2026 | Y | EXP | 365 | 09/25/2025 | 12/01/2025 | 68 | 0 | 68 |  |  | 12/3/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 193664 | 01550 | 7.6 | Solar | 05_01_219W3 | 08/15/2018 | 09/05/2018 | 4 | 4 | 0 | 09/06/2018 | 09/06/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 500916 | 01440 | 100 | Solar | 05_01_27W2 | 02/24/2023 | 04/07/2023 | 31 | 21 | 10 | 04/10/2023 | 04/10/2023 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 478408 | 02724 | 8.7 | Solar | 05_01_413L2 | 01/20/2023 | 01/23/2023 | 1 | 0 | 1 | 01/24/2023 | 01/24/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2023 | Connected |  | N
National Grid | UPTON | 176399 | 01568 | 7.6 | Solar | 05_01_607W4 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 | 03/14/2016 | 03/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2016 | 03/10/2016 | 3/19/2017 | Y | EXP | 328 | 07/18/2016 | 08/11/2016 | 18 | 0 | 18 | 4/25/2016 | 4/25/2016 | 9/8/2016 | Connected |  | N
National Grid | SALEM | 755485 | 01970 | 3.8 | Solar | 05_05_115W55 | 03/09/2026 | 03/11/2026 | 4 | 2 | 2 | 03/27/2026 | 03/27/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 334005 | 02151 | 7.6 | Solar | 05_05_312W4 | 12/28/2020 | 01/07/2021 | 7 | 7 | 0 | 01/08/2021 | 01/08/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2021 |  | 5/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2021 | Connected |  | N
National Grid | METHUEN | 752028 | 01844 | 20 | Solar | 05_12_29W4 | 02/19/2026 | 02/20/2026 | 1 | 0 | 1 | 02/23/2026 | 02/23/2026 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NEWBURY | 669313 | 01950 | 1.625 | Solar | 05_12_7W2 | 02/10/2025 | 03/19/2025 | 2 | 0 | 2 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 704124 | 01841 | 7.6 | Solar | 05_14_43L4 | 07/10/2025 | 07/25/2025 | 3 | 0 | 3 | 08/06/2025 | 08/06/2025 | 89 | 75 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 613820 | 01453 | 5.22 | Solar | 05_14_60L1 | 05/28/2024 | 06/04/2024 | 1 | 0 | 1 | 06/05/2024 | 06/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 6/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 703871 | 01605 | 17.16 | Solar | 05_14_74L5 | 07/09/2025 | 07/31/2025 | 12 | 8 | 4 | 12/24/2025 | 12/24/2025 | 30 | 12 | 18 | 03/05/2026 | 03/25/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 03/25/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 7/31/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SOUTHBRIDGE | 322879 | 01550 | 43.2 | Solar | 05_01_219W3 | 11/02/2020 | 11/13/2020 | 7 | 0 | 7 | 11/16/2020 | 11/16/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 4/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2021 | Connected |  | N
National Grid | GARDNER | 648354 | 01440 | 3.8 | Solar | 05_01_27W2 | 10/30/2024 | 05/05/2025 | 3 | 1 | 2 | 05/06/2025 | 05/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 480272 | 02724 | 7.6 | Solar | 05_01_413L2 | 12/07/2022 | 01/12/2023 | 25 | 22 | 3 | 01/13/2023 | 01/13/2023 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2023 | 12/07/2022 | 8/9/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2023 | Connected |  | N
National Grid | WESTBOROUGH | 176568 | 01581 | 7.6 | Solar | 05_01_607W4 | 12/23/2015 | 12/23/2015 | 20 | 20 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 | 12/23/2015 | 12/29/2016 | Y | EXP | 310 | 07/18/2016 | 08/16/2016 | 21 | 0 | 21 | 9/1/2016 | 9/1/2016 | 9/1/2016 | Connected |  | N
National Grid | LYNN | 175360 | 01904 | 20 | Solar | 05_05_115W55 | 11/12/2014 | 11/12/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 449344 | 02151 | 3.8 | Solar | 05_05_312W4 | 08/04/2022 | 08/09/2022 | 3 | 0 | 3 | 08/10/2022 | 08/10/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 |  | 9/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2023 | Connected |  | N
National Grid | METHUEN | 175227 | 01844 | 7.6 | Solar | 05_12_29W4 | 01/06/2015 | 01/06/2015 | 4 | 0 | 4 | 01/13/2015 | 01/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2015 | 01/06/2015 | 12/31/2016 | Y | EXP | 687 | 11/16/2015 | 12/29/2015 | 29 | 0 | 29 | 4/16/2015 | 4/16/2015 | 6/14/2016 | Connected |  | N
National Grid | NEWBURY | 669803 | 01950 | 3.8 | Solar | 05_12_7W2 | 02/04/2025 | 02/26/2025 | 3 | 0 | 3 | 02/27/2025 | 02/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | METHUEN | 725772 | 01844 | 15.2 | Solar | 05_14_43L4 | 10/10/2025 | 10/27/2025 | 9 | 6 | 3 | 10/28/2025 | 10/28/2025 | 53 | 41 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 624569 | 01453 | 10 | Solar | 05_14_60L1 | 07/26/2024 | 07/31/2024 | 3 | 0 | 3 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/25/2025 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | WORCESTER | 748180 | 01605 | 16.72 | Solar | 05_14_74L5 | 02/02/2026 | 02/05/2026 | 3 | 0 | 3 | 02/06/2026 | 02/06/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOUTHBRIDGE | 520020 | 01550 | 250 | Solar | 05_01_219W4 | 05/09/2023 | 07/25/2023 | 53 | 43 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | GARDNER | 666140 | 01440 | 5.76 | Solar | 05_01_27W2 | 01/16/2025 | 02/04/2025 | 8 | 4 | 4 | 02/05/2025 | 02/05/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 520785 | 02724 | 10 | Solar | 05_01_413L2 | 05/12/2023 | 05/16/2023 | 2 | 0 | 2 | 05/17/2023 | 05/17/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 05/12/2023 | 6/22/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2024 | Connected |  | N
National Grid | WESTBOROUGH | 177006 | 01581 | 10 | Solar | 05_01_607W4 | 10/11/2016 | 10/13/2016 | 1 | 1 | 0 | 10/13/2016 | 10/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2016 | 10/11/2016 | 9/30/2019 | Y | EXP | 1078 | 05/05/2017 | 05/05/2017 | 39 | 0 | 39 | 3/13/2018 | 3/13/2018 | 9/13/2019 | Connected |  | N
National Grid | LYNN | 177153 | 01904 | 60 | Solar | 05_05_115W55 | 08/12/2016 | 08/12/2016 | 1 | 1 | 0 | 08/15/2016 | 08/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 |  | 8/17/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 12/12/2016 | 12/12/2016 | 12/14/2016 | Connected |  | N
National Grid | REVERE | 376567 | 02151 | 15.2 | Solar | 05_05_312W4 | 09/01/2021 | 01/24/2022 | 98 | 92 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/26/2022 | Connected |  | N
National Grid | LAWRENCE | 175298 | 01841 | 5 | Solar | 05_12_29W4 | 01/15/2015 | 01/15/2015 | 43 | 43 | 0 | 03/24/2015 | 03/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 5/31/2015 | N | EXP | 65 |  |  | 0 | 0 | 0 | 1/8/2016 | 1/8/2016 | 1/8/2016 | Connected |  | N
National Grid | NEWBURY | 673349 | 01951 | 3.8 | Solar | 05_12_7W2 | 02/21/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 728924 | 01832 | 5.76 | Solar | 05_14_43L4 | 10/24/2025 | 10/27/2025 | 10 | 8 | 2 | 12/09/2025 | 12/09/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/28/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2026 | Connected |  | N
National Grid | LEOMINSTER | 627652 | 01453 | 5.76 | Solar | 05_14_60L1 | 07/25/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/25/2024 | 9/4/2025 | Y | EXP | 365 | 10/11/2024 | 10/11/2024 | 1 | 0 | 1 |  |  | 11/4/2024 | Connected |  | N
National Grid | WORCESTER | 751928 | 01605 | 11.5 | Solar | 05_14_74L5 | 02/18/2026 | 02/24/2026 | 3 | 0 | 3 | 03/11/2026 | 03/11/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STURBRIDGE | 667799 | 01566 | 450 | Solar | 05_01_219W4 | 03/14/2025 | 04/28/2025 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2025 | 05/27/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | GARDNER | 670172 | 01440 | 10 | Solar | 05_01_27W2 | 02/05/2025 | 03/19/2025 | 3 | 0 | 3 | 03/20/2025 | 03/20/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | FALL RIVER | 521609 | 02724 | 7.6 | Solar | 05_01_413L2 | 05/03/2023 | 05/04/2023 | 1 | 0 | 1 | 05/05/2023 | 05/05/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 177832 | 01581 | 900 | Solar | 05_01_607W4 | 08/08/2017 | 08/08/2017 | 10 | 5 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/23/2017 | 09/26/2017 | 24 | 24 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2018 | 08/08/2017 | 10/8/2021 | Y | STD | 555 | 01/07/2021 | 09/21/2021 | 258 | 80 | 178 | 9/22/2021 | 9/30/2021 | 10/7/2021 | Connected |  | N
National Grid | LYNN | 549206 | 01904 | 25 | Solar | 05_05_115W55 | 09/12/2023 | 09/16/2023 | 4 | 2 | 2 | 09/18/2023 | 09/18/2023 | 34 | 18 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2024 | Connected |  | N
National Grid | REVERE | 394972 | 02151 | 7.6 | Solar | 05_05_312W4 | 02/11/2022 | 02/14/2022 | 1 | 0 | 1 | 02/15/2022 | 02/15/2022 | 102 | 90 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2022 |  | 8/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | METHUEN | 175646 | 01844 | 5.16 | Solar | 05_12_29W4 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2015 |  | 2/16/2015 | N | EXP | 25 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 10/21/2015 | Connected |  | N
National Grid | NEWBURY | 683296 | 01951 | 5.76 | Solar | 05_12_7W2 | 04/07/2025 | 06/18/2025 | 3 | 0 | 3 | 06/20/2025 | 06/20/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 | 04/07/2025 | 8/1/2026 | Y | EXP | 365 | 11/14/2025 | 12/02/2025 | 19 | 0 | 19 |  |  | 12/2/2025 | Connected |  | N
National Grid | METHUEN | 547085 | 01844 | 50 | Solar | 05_14_43L6 | 11/14/2023 | 02/07/2024 | 57 | 47 | 10 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 7/22/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 629796 | 01453 | 3.8 | Solar | 05_14_60L1 | 08/19/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 08/19/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | WORCESTER | 177322 | 01605 | 7.6 | Solar | 05_14_74L5 | 06/17/2016 | 06/17/2016 | 1 | 1 | 0 | 06/21/2016 | 06/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/25/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/3/2016 | 11/3/2016 | 11/7/2016 | Connected |  | N
National Grid | SOUTHBRIDGE | 671681 | 01550 | 0 | Other | 05_01_219W4 | 01/08/2026 | 03/25/2026 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2026 |  | 5 | 0 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTMINSTER | 685699 | 01473 | 5.76 | Solar | 05_01_27W2 | 04/28/2025 | 05/13/2025 | 7 | 2 | 5 | 06/12/2025 | 06/12/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | FALL RIVER | 545544 | 02724 | 15.2 | Solar | 05_01_413L2 | 08/02/2023 | 08/09/2023 | 6 | 5 | 1 | 08/10/2023 | 08/10/2023 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 | 08/02/2023 | 1/31/2025 | Y | EXP | 365 | 05/16/2024 | 05/15/2024 | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | WESTBOROUGH | 193550 | 01581 | 250 | Solar | 05_01_607W4 | 08/15/2018 | 08/27/2018 | 6 | 0 | 6 | 08/28/2018 | 08/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 550284 | 01970 | 10 | Solar | 05_05_115W55 | 08/25/2023 | 08/29/2023 | 2 | 0 | 2 | 08/30/2023 | 08/30/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 | 08/25/2023 | 11/29/2024 | Y | EXP | 365 | 01/10/2024 | 02/28/2024 | 50 | 0 | 50 |  |  | 5/30/2024 | Connected |  | N
National Grid | REVERE | 393761 | 02151 | 15.2 | Solar | 05_05_312W4 | 11/05/2021 | 12/08/2021 | 2 | 0 | 2 | 11/10/2021 | 11/10/2021 | 60 | 26 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 175645 | 01832 | 5.16 | Solar | 05_12_29W4 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2015 |  | 2/16/2015 | N | EXP | 25 |  |  | 0 | 0 | 0 | 6/11/2015 | 6/11/2015 | 10/21/2015 | Connected |  | N
National Grid | NEWBURY | 701317 | 01951 | 10.24 | Solar | 05_12_7W2 | 06/26/2025 | 07/11/2025 | 1 | 0 | 1 | 07/17/2025 | 07/17/2025 | 32 | 19 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | METHUEN | 744884 | 01844 | 15.2 | Solar | 05_14_43L6 | 01/12/2026 | 02/10/2026 | 19 | 15 | 4 | 02/11/2026 | 02/11/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2026 |  | 3/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 642862 | 01453 | 7.6 | Solar | 05_14_60L1 | 09/26/2024 | 09/30/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177355 | 01605 | 7.6 | Solar | 05_14_74L5 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2017 |  | 2/21/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 7/12/2017 | 7/12/2017 | 7/12/2017 | Connected |  | N
National Grid | SOUTHBRIDGE | 678562 | 01550 | 420 | Solar | 05_01_219W4 | 06/18/2025 | 10/29/2025 | 91 | 82 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 | 11/20/2025 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GARDNER | 174467 | 01440 | 250 | Natural Gas | 05_01_27W3 | 07/20/2011 | 07/20/2011 | 43 | 0 | 43 | 09/20/2011 | 09/20/2011 | 1281 | 0 | 1281 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2011 |  | 12/31/2016 | N | EXP | 1852 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 568896 | 02724 | 6 | Solar | 05_01_413L2 | 01/08/2024 | 01/23/2024 | 11 | 9 | 2 | 01/24/2024 | 01/24/2024 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 01/08/2024 | 5/24/2025 | Y | EXP | 365 | 06/05/2024 | 06/04/2024 | 0 | 0 | 0 |  |  | 8/20/2024 | Connected |  | N
National Grid | WESTBOROUGH | 195651 | 01581 | 5 | Solar | 05_01_607W4 | 09/11/2018 | 10/24/2018 | 15 | 15 | 0 | 10/25/2018 | 10/25/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 | 09/11/2018 | 4/26/2019 | Y | EXP | 176 |  |  | 0 | 0 | 0 |  |  | 3/13/2019 | Connected |  | N
National Grid | SALEM | 582671 | 01970 | 1.74 | Solar | 05_05_115W55 | 01/26/2024 | 01/30/2024 | 2 | 0 | 2 | 01/31/2024 | 01/31/2024 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 |  | 4/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | REVERE | 423473 | 02151 | 15.2 | Solar | 05_05_312W4 | 04/12/2022 | 04/13/2022 | 1 | 0 | 1 | 04/14/2022 | 04/14/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 |  | 5/27/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 176142 | 01832 | 7.75 | Solar | 05_12_29W4 | 06/29/2015 | 06/29/2015 | 6 | 6 | 0 | 07/10/2015 | 07/10/2015 | 398 | 0 | 398 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2015 |  | 7/6/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 7/27/2015 | 7/27/2015 |  | Withdrawn |  | Y
National Grid | NEWBURY | 704708 | 01951 | 3.8 | Solar | 05_12_7W2 | 07/14/2025 | 07/29/2025 | 1 | 0 | 1 | 08/01/2025 | 08/01/2025 | 73 | 59 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 753422 | 01832 | 3.8 | Solar | 05_14_43L6 | 02/26/2026 | 03/03/2026 | 1 | 0 | 1 | 03/11/2026 | 03/11/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 645437 | 01453 | 23 | Solar | 05_14_60L1 | 10/07/2024 | 10/16/2024 | 5 | 3 | 2 | 10/17/2024 | 10/17/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | WORCESTER | 177904 | 01604 | 20 | Solar | 05_14_74L5 | 08/15/2017 | 08/15/2017 | 15 | 15 | 0 | 08/29/2017 | 08/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 8/20/2018 | N | EXP | 346 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/14/2017 | Connected |  | N
National Grid | SOUTHBRIDGE | 739118 | 01550 | 15.2 | Solar | 05_01_219W4 | 12/11/2025 | 12/22/2025 | 6 | 4 | 2 | 12/23/2025 | 12/23/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GARDNER | 198897 | 01440 | 3000 | Natural Gas | 05_01_27W3 | 07/11/2019 | 08/30/2019 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2019 | 10/14/2019 | 29 | 21 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 601302 | 02724 | 10 | Solar | 05_01_413L2 | 04/04/2024 | 04/10/2024 | 4 | 0 | 4 | 04/11/2024 | 04/11/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/04/2024 | 4/22/2025 | Y | EXP | 365 | 05/11/2024 | 06/04/2024 | 25 | 0 | 25 |  |  | 11/14/2024 | Connected |  | N
National Grid | WESTBOROUGH | 192916 | 01581 | 2040 | Solar | 05_01_607W4 | 10/25/2018 |  | 232 | 26 | 206 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 627842 | 01970 | 3.8 | Solar | 05_05_115W55 | 07/25/2024 | 08/05/2024 | 6 | 5 | 1 | 08/06/2024 | 08/06/2024 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 | 07/25/2024 | 9/11/2025 | Y | EXP | 365 | 09/25/2024 | 10/11/2024 | 17 | 0 | 17 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 436643 | 02151 | 15.2 | Solar | 05_05_312W4 | 06/09/2022 | 06/13/2022 | 2 | 0 | 2 | 06/14/2022 | 06/14/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2022 | Connected |  | N
National Grid | HAVERHILL | 176626 | 01832 | 7.6 | Solar | 05_12_29W4 | 04/15/2016 | 04/15/2016 | 1 | 1 | 0 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2016 | 04/15/2016 | 10/30/2017 | Y | EXP | 467 | 04/26/2017 | 08/02/2017 | 68 | 0 | 68 | 4/20/2017 | 4/20/2017 | 8/18/2017 | Connected |  | N
National Grid | NEWBURY | 742271 | 01951 | 18.88 | Solar | 05_12_7W3 | 02/18/2026 | 02/25/2026 | 1 | 0 | 1 | 02/26/2026 | 02/26/2026 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 176497 | 01844 | 34.2 | Solar | 05_14_43L6 | 02/07/2016 | 02/07/2016 | 5 | 5 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 | 02/07/2016 | 2/13/2017 | Y | EXP | 348 | 06/28/2016 | 07/05/2016 | 4 | 0 | 4 | 4/11/2016 | 4/11/2016 | 8/11/2016 | Connected |  | N
National Grid | LEOMINSTER | 651238 | 01453 | 17.6 | Solar | 05_14_60L1 | 11/04/2024 | 01/15/2025 | 40 | 36 | 4 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/04/2024 | 3/4/2026 | Y | EXP | 365 | 08/26/2025 | 09/03/2025 | 9 | 0 | 9 |  |  | 9/23/2025 | Connected |  | N
National Grid | WORCESTER | 178343 | 01602 | 500 | Solar | 05_14_74L5 | 01/10/2018 | 01/10/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 | 05/10/2018 | 11/16/2018 | 133 | 109 | 24 | 03/12/2018 | 04/09/2018 | 15 | 0 | 15 | 11/16/2018 | 133 | 109 | 24 |  |  | 0 | 0 | 0 | 12/20/2018 |  | 11/15/2019 | N | STD | 330 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 175288 | 01550 | 225 | Solar | 05_01_219W4 | 11/06/2014 | 11/06/2014 | 5 | 0 | 5 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2014 |  | 4/1/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 12/19/2014 | 12/19/2014 | 10/22/2015 | Connected |  | N
National Grid | GARDNER | 378510 | 01440 | 3000 | Natural Gas | 05_01_27W3 | 04/12/2022 | 05/16/2022 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2022 | 06/15/2022 | 21 | 2 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 04/12/2022 | 2/10/2026 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2026 | Connected |  | N
National Grid | FALL RIVER | 602467 | 02724 | 9.88 | Solar | 05_01_413L2 | 04/12/2024 | 04/18/2024 | 3 | 0 | 3 | 04/19/2024 | 04/19/2024 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | WESTBOROUGH | 371045 | 01581 | 7.6 | Solar | 05_01_607W4 | 08/03/2021 | 12/30/2021 | 1 | 0 | 1 | 08/05/2021 | 08/05/2021 | 53 | 29 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 |  | 11/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2022 | Connected |  | N
National Grid | SALEM | 630792 | 01970 | 5.76 | Solar | 05_05_115W55 | 08/07/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/07/2024 | 11/30/2025 | Y | EXP | 365 | 10/03/2024 | 10/07/2024 | 5 | 0 | 5 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 470820 | 02151 | 15.2 | Solar | 05_05_312W4 | 10/24/2022 | 10/25/2022 | 1 | 0 | 1 | 10/26/2022 | 10/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 10/24/2022 | 12/19/2023 | Y | EXP | 365 | 02/15/2023 | 04/27/2023 | 72 | 0 | 72 |  |  | 6/22/2023 | Connected |  | N
National Grid | HAVERHILL | 176880 | 01832 | 10 | Solar | 05_12_29W4 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 | 05/04/2016 | 5/10/2017 | Y | EXP | 349 | 03/22/2017 | 04/10/2017 | 13 | 0 | 13 | 4/20/2017 | 4/20/2017 | 4/25/2017 | Connected |  | N
National Grid | NEWBURY | 395249 | 01951 | 34.6 | Solar | 05_12_7W3 | 02/17/2022 | 03/22/2022 | 22 | 20 | 2 | 03/23/2022 | 03/23/2022 | 48 | 29 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2022 |  | 3/31/2024 | N | EXP | 620 |  |  | 0 | 0 | 0 |  |  | 3/25/2024 | Connected |  | N
National Grid | HAVERHILL | 176496 | 01832 | 17.6 | Solar | 05_14_43L6 | 02/05/2016 | 02/05/2016 | 8 | 8 | 0 | 02/19/2016 | 02/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2016 |  | 2/13/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 9/20/2016 | 9/20/2016 | 9/20/2016 | Connected |  | N
National Grid | LEOMINSTER | 652089 | 01453 | 2.9 | Solar | 05_14_60L1 | 11/06/2024 | 01/22/2025 | 5 | 3 | 2 | 01/23/2025 | 01/23/2025 | 70 | 25 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 193466 | 01602 | 15.2 | Solar | 05_14_74L5 | 08/14/2018 | 09/04/2018 | 13 | 0 | 13 | 09/05/2018 | 09/05/2018 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 175419 | 01566 | 30 | Solar | 05_01_219W4 | 07/11/2014 | 07/11/2014 | 6 | 0 | 6 | 07/22/2014 | 07/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2014 |  | 11/28/2014 | N | EXP | 123 |  |  | 0 | 0 | 0 | 7/29/2014 | 7/29/2014 | 12/18/2014 | Connected |  | N
National Grid | GARDNER | 676963 | 01440 | 960 | Solar | 05_01_27W4 | 04/10/2025 | 06/10/2025 | 41 | 32 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 609343 | 02724 | 3.8 | Solar | 05_01_413L2 | 05/07/2024 | 05/14/2024 | 5 | 0 | 5 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 10/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | WESTBOROUGH | 407933 | 01581 | 6 | Solar | 05_01_607W4 | 02/04/2022 | 02/09/2022 | 3 | 0 | 3 | 02/10/2022 | 02/10/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 | 02/04/2022 | 4/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | SALEM | 633673 | 01970 | 9.88 | Solar | 05_05_115W55 | 08/19/2024 | 09/03/2024 | 3 | 0 | 3 | 09/04/2024 | 09/04/2024 | 26 | 11 | 15 | 11/20/2024 | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 12/12/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 479590 | 02151 | 7.6 | Solar | 05_05_312W4 | 01/05/2023 | 01/10/2023 | 3 | 0 | 3 | 01/11/2023 | 01/11/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2023 |  | 4/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2023 | Connected |  | N
National Grid | HAVERHILL | 177620 | 01832 | 10 | Solar | 05_12_29W4 | 11/08/2017 | 11/08/2017 | 99 | 89 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/14/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 464788 | 01951 | 8.99 | Solar | 05_12_7W3 | 11/15/2022 | 11/18/2022 | 3 | 0 | 3 | 11/21/2022 | 11/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/25/2022 |  | 12/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2023 | Connected |  | N
National Grid | HAVERHILL | 176538 | 01832 | 34.2 | Solar | 05_14_43L6 | 02/10/2016 | 02/10/2016 | 5 | 5 | 0 | 02/19/2016 | 02/19/2016 | 434 | 0 | 434 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 11/20/2017 | N | EXP | 628 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 655001 | 01453 | 5.2 | Solar | 05_14_60L1 | 11/19/2024 | 12/09/2024 | 6 | 3 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | WORCESTER | 296655 | 01605 | 7.6 | Solar | 05_14_74L5 | 06/18/2020 | 06/23/2020 | 2 | 0 | 2 | 06/24/2020 | 06/24/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 175892 | 01550 | 5 | Solar | 05_01_219W4 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2015 | 08/04/2015 | 8/10/2016 | Y | EXP | 357 | 05/24/2016 | 06/22/2016 | 19 | 0 | 19 | 8/19/2015 | 8/19/2015 | 8/29/2016 | Connected |  | N
National Grid | GARDNER | 679785 | 01440 | 117.3 | Solar | 05_01_27W4 | 09/03/2025 | 10/03/2025 | 22 | 14 | 8 | 10/06/2025 | 10/06/2025 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 618333 | 02724 | 10 | Solar | 05_01_413L2 | 01/17/2025 | 02/05/2025 | 3 | 0 | 3 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | WESTBOROUGH | 437898 | 01581 | 10 | Solar | 05_01_607W4 | 06/28/2022 |  | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 657557 | 01904 | 6 | Solar | 05_05_115W55 | 11/28/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | REVERE | 479439 | 02151 | 11.4 | Solar | 05_05_312W4 | 03/29/2023 | 12/07/2022 | 2 | 0 | 2 | 04/03/2023 | 04/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2022 |  | 5/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | N
National Grid | HAVERHILL | 184469 | 01832 | 3.8 | Solar | 05_12_29W4 | 06/07/2018 | 06/07/2018 | 16 | 7 | 9 | 06/29/2018 | 06/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 565408 | 01951 | 25 | Solar | 05_12_7W3 | 11/03/2023 | 01/31/2024 | 59 | 55 | 4 | 02/01/2024 | 02/01/2024 | 82 | 70 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 193994 | 01832 | 540 | Solar | 05_14_43L6 | 09/18/2018 | 10/02/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2018 | 01/31/2019 | 80 | 0 | 80 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 655842 | 01453 | 3.8 | Solar | 05_14_60L1 | 11/20/2024 | 01/21/2025 | 4 | 0 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/20/2024 | 2/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | WORCESTER | 357875 | 01605 | 9.8 | Solar | 05_14_74L5 | 05/25/2021 | 05/26/2021 | 0 | 0 | 0 | 05/27/2021 | 05/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2021 |  | 8/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2022 | Connected |  | N
National Grid | STURBRIDGE | 184325 | 01566 | 7.6 | Solar | 05_01_219W4 | 05/24/2018 | 05/24/2018 | 21 | 20 | 1 | 06/21/2018 | 06/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 706238 | 01440 | 200 | Solar | 05_01_27W4 | 08/11/2025 | 09/18/2025 | 27 | 17 | 10 | 09/19/2025 | 09/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 624915 | 02724 | 7.6 | Solar | 05_01_413L2 | 07/15/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 527513 | 01581 | 10 | Solar | 05_01_607W4 | 06/13/2023 | 06/14/2023 | 1 | 0 | 1 | 06/15/2023 | 06/15/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 682467 | 01970 | 6.08 | Solar | 05_05_115W55 | 04/04/2025 | 04/28/2025 | 15 | 10 | 5 | 09/26/2025 | 09/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | REVERE | 489567 | 02151 | 15.2 | Solar | 05_05_312W4 | 01/04/2023 | 01/06/2023 | 3 | 2 | 1 | 01/09/2023 | 01/09/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 |  | 2/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | HAVERHILL | 185702 | 01835 | 7.6 | Solar | 05_12_29W4 | 06/13/2018 | 06/13/2018 | 30 | 25 | 5 | 07/27/2018 | 07/27/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 | 06/13/2018 | 9/20/2019 | Y | EXP | 416 | 05/17/2019 | 05/16/2019 | 0 | 0 | 0 |  |  | 8/27/2019 | Connected |  | N
National Grid | NEWBURY | 587779 | 01951 | 7.6 | Solar | 05_12_7W3 | 02/05/2024 | 02/13/2024 | 6 | 0 | 6 | 02/14/2024 | 02/14/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 3/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2024 | Connected |  | N
National Grid | METHUEN | 193993 | 01844 | 650 | Solar | 05_14_43L6 | 09/12/2018 | 10/02/2018 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2018 | 01/31/2019 | 80 | 0 | 80 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 659314 | 01453 | 7.6 | Solar | 05_14_60L1 | 12/09/2024 | 01/03/2025 | 16 | 11 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | WORCESTER | 375924 | 01605 | 9.8 | Solar | 05_14_74L5 | 08/26/2021 | 12/07/2021 | 3 | 0 | 3 | 09/01/2021 | 09/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2021 |  | 12/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2022 | Connected |  | N
National Grid | STURBRIDGE | 194293 | 01566 | 250 | Solar | 05_01_219W4 | 08/24/2018 | 09/04/2018 | 3 | 0 | 3 | 09/05/2018 | 09/05/2018 | 304 | 56 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 716552 | 01473 | 67.3 | Solar | 05_01_27W4 | 09/23/2025 | 10/20/2025 | 17 | 8 | 9 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 641629 | 02724 | 10 | Solar | 05_01_413L2 | 10/02/2024 | 10/23/2024 | 7 | 4 | 3 | 10/24/2024 | 10/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/02/2024 | 1/3/2026 | Y | EXP | 365 | 06/11/2025 | 07/30/2025 | 50 | 0 | 50 |  |  | 10/7/2025 | Connected |  | N
National Grid | WESTBOROUGH | 600531 | 01581 | 7.6 | Solar | 05_01_607W4 | 04/04/2024 | 04/10/2024 | 4 | 0 | 4 | 04/11/2024 | 04/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/04/2024 | 6/4/2025 | Y | EXP | 365 | 08/21/2024 | 09/09/2024 | 20 | 0 | 20 |  |  | 9/14/2024 | Connected |  | N
National Grid | LYNN | 689895 | 01904 | 7.6 | Solar | 05_05_115W55 | 05/06/2025 | 06/26/2025 | 3 | 0 | 3 | 07/15/2025 | 07/15/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 05/06/2025 | 10/10/2026 | Y | EXP | 365 | 01/06/2026 | 01/05/2026 | 0 | 0 | 0 |  |  | 1/12/2026 | Connected |  | N
National Grid | REVERE | 501896 | 02151 | 13.975 | Solar | 05_05_312W4 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2023 |  | 4/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2023 | Connected |  | N
National Grid | HAVERHILL | 187782 | 01835 | 7.6 | Solar | 05_12_29W4 | 06/25/2018 | 06/25/2018 | 27 | 26 | 1 | 08/06/2018 | 08/06/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 06/25/2018 | 8/8/2019 | Y | EXP | 365 | 12/27/2018 | 01/03/2019 | 7 | 0 | 7 |  |  | 5/10/2019 | Connected |  | N
National Grid | NEWBURY | 636110 | 01951 | 8.12 | Solar | 05_12_7W3 | 08/28/2024 | 09/10/2024 | 1 | 0 | 1 | 09/11/2024 | 09/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/28/2024 | 10/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | HAVERHILL | 313668 | 01832 | 6 | Solar | 05_14_43L6 | 09/18/2020 | 09/21/2020 | 0 | 0 | 0 | 09/22/2020 | 09/22/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2020 |  | 9/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 705439 | 01453 | 5.85 | Solar | 05_14_60L1 | 07/21/2025 | 08/06/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | WORCESTER | 401112 | 01605 | 0 | Other | 05_14_74L5 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 02/02/2022 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 245798 | 01550 | 7.6 | Solar | 05_01_219W4 | 10/09/2019 | 10/15/2019 | 2 | 0 | 2 | 10/16/2019 | 10/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2019 | 10/09/2019 | 10/9/2020 | Y | EXP | 365 | 09/16/2020 | 09/21/2020 | 5 | 0 | 5 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 716453 | 01440 | 100 | Solar | 05_01_27W4 | 09/23/2025 | 10/14/2025 | 14 | 5 | 9 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 647245 | 02724 | 5.76 | Solar | 05_01_413L2 | 10/15/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/15/2024 | 12/23/2025 | Y | EXP | 365 | 08/22/2025 | 08/28/2025 | 7 | 0 | 7 |  |  | 9/15/2025 | Connected |  | N
National Grid | WESTBOROUGH | 601448 | 01581 | 3.8 | Solar | 05_01_607W4 | 04/10/2024 | 04/16/2024 | 3 | 0 | 3 | 04/17/2024 | 04/17/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | LYNN | 721391 | 01902 | 11.5 | Solar | 05_05_115W55 | 09/23/2025 | 10/08/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 544251 | 02151 | 14.805 | Solar | 05_05_312W4 | 08/21/2023 | 09/14/2023 | 17 | 13 | 4 | 09/15/2023 | 09/15/2023 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2023 |  | 10/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N
National Grid | HAVERHILL | 191643 | 01832 | 10 | Solar | 05_12_29W4 | 07/24/2018 | 08/29/2018 | 7 | 0 | 7 | 08/30/2018 | 08/30/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 637079 | 01950 | 5.76 | Solar | 05_12_7W3 | 09/02/2024 | 09/16/2024 | 5 | 4 | 1 | 09/17/2024 | 09/17/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 10/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 375768 | 01832 | 7.6 | Solar | 05_14_43L6 | 08/13/2021 | 08/30/2021 | 12 | 11 | 1 | 08/31/2021 | 08/31/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 8/29/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 694244 | 01453 | 22.8 | Solar | 05_14_60L2 | 05/27/2025 | 06/16/2025 | 13 | 11 | 2 | 06/17/2025 | 06/17/2025 | 19 | 0 | 19 | 07/24/2025 | 08/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 08/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 565286 | 01605 | 11.97 | Solar | 05_14_74L5 | 01/05/2024 | 01/08/2024 | 1 | 0 | 1 | 01/09/2024 | 01/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2024 | 01/05/2024 | 2/14/2025 | Y | EXP | 365 | 06/28/2024 | 07/01/2024 | 4 | 0 | 4 |  |  | 8/16/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 377934 | 01550 | 700 | Natural Gas | 05_01_219W4 | 03/10/2022 | 05/26/2022 | 54 | 45 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/27/2022 | 11/18/2022 | 120 | 101 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 740379 | 01440 | 5.76 | Solar | 05_01_27W4 | 12/15/2025 | 01/20/2026 | 1 | 0 | 1 | 02/02/2026 | 02/02/2026 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 648427 | 02724 | 3.8 | Solar | 05_01_413L2 | 11/07/2024 | 11/21/2024 | 4 | 0 | 4 | 11/22/2024 | 11/22/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 | 11/07/2024 | 2/18/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | WESTBOROUGH | 660589 | 01581 | 10 | Solar | 05_01_607W4 | 12/13/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 12/13/2024 | 2/21/2026 | Y | EXP | 365 | 05/08/2025 | 10/11/2025 | 157 | 0 | 157 |  |  | 11/21/2025 | Connected |  | N
National Grid | SWAMPSCOTT | 741858 | 01907 | 7.6 | Solar | 05_05_115W55 | 12/22/2025 | 12/29/2025 | 2 | 0 | 2 | 01/08/2026 | 01/08/2026 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 546560 | 02151 | 0 | Solar | 05_05_312W4 | 08/07/2023 | 08/08/2023 | 1 | 0 | 1 | 08/09/2023 | 08/09/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 |  | 12/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2024 | Connected |  | N
National Grid | HAVERHILL | 198918 | 01832 | 7.6 | Solar | 05_12_29W4 | 11/05/2018 | 11/05/2018 | 0 | 0 | 0 | 11/06/2018 | 11/06/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 | 11/05/2018 | 11/5/2020 | Y | EXP | 450 | 11/15/2019 | 11/27/2019 | 12 | 0 | 12 |  |  | 1/16/2020 | Connected |  | N
National Grid | BYFIELD | 636904 | 01922 | 5 | Solar | 05_12_7W3 | 08/30/2024 | 10/11/2024 | 4 | 2 | 2 | 10/15/2024 | 10/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 416288 | 01844 | 7.6 | Solar | 05_14_43L6 | 12/20/2022 | 01/05/2023 | 10 | 10 | 0 | 01/06/2023 | 01/06/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 2/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | N
National Grid | LEOMINSTER | 176109 | 01453 | 47.1 | Solar | 05_14_60L2 | 06/26/2015 | 06/26/2015 | 2 | 2 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2015 |  | 7/1/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 7/22/2015 | 7/22/2015 | 11/3/2015 | Connected |  | N
National Grid | WORCESTER | 569971 | 01605 | 16.53 | Solar | 05_14_74L5 | 11/08/2023 | 11/21/2023 | 8 | 5 | 3 | 11/22/2023 | 11/22/2023 | 69 | 45 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 427472 | 01550 | 0 | Other | 05_01_219W4 | 07/13/2022 | 08/16/2022 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2022 | 09/13/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 747555 | 01440 | 15.2 | Solar | 05_01_27W4 | 01/29/2026 | 02/02/2026 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 655030 | 02724 | 8.99 | Solar | 05_01_413L2 | 11/18/2024 | 03/10/2025 | 26 | 25 | 1 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | WESTBOROUGH | 678299 | 01581 | 5.76 | Solar | 05_01_607W4 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 76 | 60 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 562342 | 01902 | 4990 | Solar | 05_05_11W81 | 12/05/2023 | 01/19/2024 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2024 | 03/28/2024 | 48 | 30 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 | 12/05/2023 | 12/18/2026 | Y | STD | 406 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | REVERE | 573934 | 02151 | 15.2 | Solar | 05_05_312W4 | 11/28/2023 | 12/13/2023 | 11 | 8 | 3 | 12/14/2023 | 12/14/2023 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  | 5/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | HAVERHILL | 206834 | 01832 | 3.8 | Solar | 05_12_29W4 | 02/15/2019 | 02/28/2019 | 7 | 0 | 7 | 03/01/2019 | 03/01/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 |  | 3/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2019 | Connected |  | N
National Grid | NEWBURY | 647963 | 01951 | 15.2 | Solar | 05_12_7W3 | 10/17/2024 | 11/04/2024 | 12 | 10 | 2 | 11/05/2024 | 11/05/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/17/2024 | 1/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 418171 | 01844 | 149.9 | Solar | 05_14_43L6 | 03/17/2022 | 03/28/2022 | 7 | 0 | 7 |  |  | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 03/17/2022 | 12/8/2023 | Y | STD | 165 |  |  | 0 | 0 | 0 |  |  | 12/8/2023 | Connected |  | N
National Grid | LEOMINSTER | 177160 | 01453 | 32 | Solar | 05_14_60L2 | 10/28/2016 | 10/28/2016 | 2 | 2 | 0 | 11/01/2016 | 11/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2016 |  | 11/2/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 3/21/2017 | 3/21/2017 | 3/21/2017 | Connected |  | N
National Grid | WORCESTER | 642704 | 01605 | 10 | Solar | 05_14_74L5 | 09/25/2024 | 10/02/2024 | 5 | 0 | 5 | 10/03/2024 | 10/03/2024 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 09/25/2024 | 12/3/2025 | Y | EXP | 365 | 03/15/2025 | 03/17/2025 | 3 | 0 | 3 |  |  | 5/22/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 429601 | 01550 | 15.2 | Solar | 05_01_219W4 | 05/11/2022 | 05/16/2022 | 4 | 3 | 1 | 05/17/2022 | 05/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 7/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2022 | Connected |  | N
National Grid | GARDNER | 174500 | 01440 | 300 | Natural Gas | 05_01_27W4 | 11/17/2009 | 11/17/2009 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2010 |  | 10/31/2012 | N | EXP | 1010 |  |  | 0 | 0 | 0 | 9/18/2012 | 9/18/2012 | 7/7/2010 | Connected |  | N
National Grid | SWANSEA | 658103 | 02777 | 7.6 | Solar | 05_01_413L2 | 12/03/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 699431 | 01581 | 18.48 | Solar | 05_01_607W4 | 07/02/2025 | 07/24/2025 | 14 | 10 | 4 | 07/25/2025 | 07/25/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 9/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | LYNN | 693170 | 01902 | 5.76 | Solar | 05_05_11W81 | 06/02/2025 | 07/15/2025 | 7 | 4 | 3 | 08/06/2025 | 08/06/2025 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 599975 | 02151 | 11.6 | Solar | 05_05_312W4 | 04/04/2024 | 04/17/2024 | 8 | 4 | 4 | 04/18/2024 | 04/18/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 | 04/04/2024 | 7/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2024 | Connected |  | N
National Grid | HAVERHILL | 224995 | 01832 | 3.8 | Solar | 05_12_29W4 | 06/25/2019 | 07/03/2019 | 5 | 0 | 5 | 07/05/2019 | 07/05/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BYFIELD | 649136 | 01922 | 7.6 | Solar | 05_12_7W3 | 11/06/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 418169 | 01844 | 133.2 | Solar | 05_14_43L6 | 03/17/2022 | 04/11/2022 | 17 | 11 | 6 |  |  | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 03/17/2022 | 12/12/2023 | Y | STD | 165 |  |  | 0 | 0 | 0 |  |  | 12/29/2023 | Connected |  | N
National Grid | LEOMINSTER | 270193 | 01453 | 10 | Solar | 05_14_60L2 | 01/06/2020 | 01/07/2020 | 0 | 0 | 0 | 01/08/2020 | 01/08/2020 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2020 |  | 1/6/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  | 7/9/2020 | Connected |  | N
National Grid | WORCESTER | 643144 | 01605 | 5.76 | Solar | 05_14_74L5 | 09/26/2024 | 11/09/2024 | 13 | 11 | 2 | 11/12/2024 | 11/12/2024 | 20 | 0 | 20 | 12/31/2024 | 12/30/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 | 09/26/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 439536 | 01550 | 18.56 | Solar | 05_01_219W4 | 06/23/2022 | 07/12/2022 | 12 | 10 | 2 | 07/13/2022 | 07/13/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 |  | 8/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2022 | Connected |  | Y
National Grid | GARDNER | 174641 | 01440 | 82.8 | Solar | 05_01_27W4 | 12/04/2013 | 12/04/2013 | 5 | 0 | 5 | 12/11/2013 | 12/11/2013 | 941 | 6 | 935 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2013 | 12/04/2013 | 12/31/2016 | Y | EXP | 1100 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 658241 | 02777 | 5.76 | Solar | 05_01_413L2 | 12/03/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | WESTBOROUGH | 707825 | 01581 | 18.81 | Solar | 05_01_607W4 | 07/28/2025 | 08/01/2025 | 4 | 0 | 4 | 08/04/2025 | 08/04/2025 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 730560 | 01970 | 23 | Solar | 05_05_11W81 | 10/31/2025 | 11/04/2025 | 2 | 0 | 2 | 11/05/2025 | 11/05/2025 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  | 1/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 603992 | 02151 | 10 | Solar | 05_05_312W4 | 04/17/2024 | 04/18/2024 | 1 | 0 | 1 | 04/19/2024 | 04/19/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 241818 | 01832 | 10 | Solar | 05_12_29W4 | 07/12/2019 | 07/24/2019 | 8 | 8 | 0 | 07/25/2019 | 07/25/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 2/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2019 | Connected |  | N
National Grid | BYFIELD | 653572 | 01922 | 8.125 | Solar | 05_12_7W3 | 11/22/2024 | 01/15/2025 | 24 | 17 | 7 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/22/2024 | 8/9/2026 | Y | EXP | 365 | 10/01/2025 | 10/29/2025 | 29 | 0 | 29 |  |  | 2/13/2026 | Connected |  | N
National Grid | HAVERHILL | 418150 | 01832 | 149.9 | Solar | 05_14_43L6 | 03/17/2022 | 03/28/2022 | 7 | 0 | 7 |  |  | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 03/17/2022 | 12/12/2023 | Y | STD | 165 |  |  | 0 | 0 | 0 |  |  | 12/29/2023 | Connected |  | N
National Grid | LEOMINSTER | 291579 | 01453 | 10 | Solar | 05_14_60L2 | 06/15/2020 | 06/18/2020 | 3 | 2 | 1 | 06/19/2020 | 06/19/2020 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2020 |  | 6/16/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2021 | Connected |  | N
National Grid | WORCESTER | 648578 | 01605 | 3.8 | Solar | 05_14_74L5 | 11/12/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 492026 | 01550 | 450 | Solar | 05_01_219W4 | 03/17/2023 |  | 246 | 236 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 175270 | 01440 | 336 | Solar | 05_01_27W4 | 06/16/2014 | 06/16/2014 | 7 | 0 | 7 | 06/27/2014 | 06/27/2014 | 687 | 32 | 655 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2014 |  | 11/28/2014 | N | EXP | 77 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 659732 | 02777 | 7.6 | Solar | 05_01_413L2 | 12/10/2024 | 01/01/2025 | 5 | 0 | 5 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/10/2024 | 2/20/2026 | Y | EXP | 365 | 04/30/2025 | 08/04/2025 | 97 | 0 | 97 |  |  | 9/8/2025 | Connected |  | N
National Grid | WESTBOROUGH | 385049 | 01581 | 4920 | Solar | 05_01_609W1 | 10/29/2021 | 12/02/2021 | 44 | 34 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2021 | 01/05/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LYNN | 174269 | 01902 | 300 | Solar | 05_05_11W81 | 12/19/2011 | 12/19/2011 | 30 | 0 | 30 | 02/02/2012 | 02/02/2012 | 486 | 0 | 486 | 01/29/2013 | 01/29/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2012 |  | 6/1/2012 | N | EXP | 44 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 610948 | 02151 | 8.775 | Solar | 05_05_312W4 | 05/14/2024 | 05/23/2024 | 4 | 3 | 1 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 |  | 6/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | HAVERHILL | 254139 | 01832 | 10 | Solar | 05_12_29W4 | 10/11/2019 | 10/21/2019 | 4 | 0 | 4 | 10/22/2019 | 10/22/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 | 10/11/2019 | 10/19/2021 | Y | EXP | 365 | 05/27/2020 | 06/12/2020 | 16 | 0 | 16 |  |  | 10/21/2020 | Connected |  | N
National Grid | BYFIELD | 655714 | 01922 | 7.6 | Solar | 05_12_7W3 | 11/20/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/27/2025 | Connected |  | N
National Grid | HAVERHILL | 532437 | 01832 | 6 | Solar | 05_14_43L6 | 06/14/2023 | 06/16/2023 | 2 | 0 | 2 | 06/20/2023 | 06/20/2023 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 347069 | 01453 | 8.7 | Solar | 05_14_60L2 | 04/19/2021 | 04/22/2021 | 2 | 0 | 2 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  | 7/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2021 | Connected |  | N
National Grid | WORCESTER | 650671 | 01605 | 10 | Solar | 05_14_74L5 | 11/04/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | STURBRIDGE | 652365 | 01566 | 10 | Solar | 05_01_219W4 | 11/14/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 176705 | 01473 | 6 | Solar | 05_01_27W4 | 10/27/2015 | 10/27/2015 | 2 | 2 | 0 | 10/30/2015 | 10/30/2015 | 368 | 0 | 368 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 10/27/2015 | 11/2/2016 | Y | EXP | 358 | 05/19/2016 | 06/01/2016 | 8 | 0 | 8 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 659432 | 02777 | 7.68 | Solar | 05_01_413L2 | 12/10/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 617857 | 01581 | 4999 | Solar | 05_01_609W1 | 08/14/2024 | 11/14/2024 | 65 | 55 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 05/09/2025 | 119 | 98 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LYNN | 174873 | 01902 | 2000 | Solar | 05_05_11W81 | 09/10/2012 | 09/10/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 11/27/2012 | 30 | 0 | 30 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 625957 | 02151 | 0 | Solar | 05_05_312W4 | 07/18/2024 | 07/24/2024 | 4 | 0 | 4 | 07/25/2024 | 07/25/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2024 | Connected |  | N
National Grid | HAVERHILL | 290811 | 01835 | 10 | Solar | 05_12_29W4 | 06/26/2020 | 07/06/2020 | 5 | 0 | 5 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BYFIELD | 669707 | 01922 | 3.8 | Solar | 05_12_7W3 | 02/13/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 550928 | 01832 | 7.6 | Solar | 05_14_43L6 | 10/11/2023 | 10/12/2023 | 1 | 0 | 1 | 10/13/2023 | 10/13/2023 | 18 | 0 | 18 | 12/12/2023 | 01/25/2024 | 30 | 3 | 27 |  |  | 0 | 0 | 0 | 01/25/2024 | 30 | 3 | 27 |  |  | 0 | 0 | 0 | 1/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 378339 | 01453 | 11.4 | Solar | 05_14_60L2 | 08/26/2021 | 09/21/2021 | 17 | 16 | 1 | 09/22/2021 | 09/22/2021 | 62 | 39 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 1/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2022 | Connected |  | N
National Grid | WORCESTER | 650791 | 01605 | 10 | Solar | 05_14_74L5 | 10/31/2024 | 11/19/2024 | 2 | 0 | 2 | 11/20/2024 | 11/20/2024 | 52 | 27 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 679496 | 01550 | 5.76 | Solar | 05_01_219W4 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 177829 | 01452 | 7.6 | Solar | 05_01_27W4 | 08/04/2017 | 08/04/2017 | 4 | 0 | 4 | 08/11/2017 | 08/11/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 8/12/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N
National Grid | SWANSEA | 673435 | 02777 | 5.76 | Solar | 05_01_413L2 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | WESTBOROUGH | 708824 | 01581 | 7.6 | Solar | 05_01_609W1 | 09/08/2025 | 09/23/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 09/08/2025 | 11/7/2026 | Y | EXP | 365 | 03/07/2026 |  | 26 | 0 | 26 |  |  |  | Construction |  | N
National Grid | LYNN | 174930 | 01904 | 50 | Solar | 05_05_11W81 | 08/26/2013 | 08/26/2013 | 11 | 4 | 7 | 09/13/2013 | 09/13/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2013 |  | 12/31/2013 | N | EXP | 96 |  |  | 0 | 0 | 0 | 12/6/2013 | 12/6/2013 | 12/12/2013 | Connected |  | N
National Grid | REVERE | 642208 | 02151 | 11.5 | Solar | 05_05_312W4 | 09/23/2024 | 10/03/2024 | 9 | 7 | 2 | 10/04/2024 | 10/04/2024 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 |  | 10/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | HAVERHILL | 302539 | 01835 | 10 | Solar | 05_12_29W4 | 09/14/2020 | 09/21/2020 | 4 | 0 | 4 | 09/22/2020 | 09/22/2020 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N
National Grid | NEWBURY | 687889 | 01922 | 10 | Solar | 05_12_7W3 | 04/28/2025 | 07/31/2025 | 1 | 0 | 1 | 08/01/2025 | 08/01/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | Y
National Grid | METHUEN | 593129 | 01844 | 7.6 | Solar | 05_14_43L6 | 03/16/2024 | 03/18/2024 | 1 | 0 | 1 | 03/19/2024 | 03/19/2024 | 6 | 1 | 5 | 04/16/2024 | 05/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 5/15/2024 |  | 6/22/2025 | N | EXP | 365 | 07/10/2024 | 08/30/2024 | 52 | 0 | 52 |  |  | 10/12/2024 | Connected |  | N
National Grid | LEOMINSTER | 443818 | 01453 | 50 | Solar | 05_14_60L2 | 07/15/2022 | 07/29/2022 | 10 | 0 | 10 | 08/01/2022 | 08/01/2022 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2022 |  | 2/23/2024 | N | EXP | 275 |  |  | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | WORCESTER | 651903 | 01605 | 5.76 | Solar | 05_14_74L5 | 11/25/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 738314 | 01550 | 17.86 | Solar | 05_01_219W4 | 12/08/2025 | 12/10/2025 | 2 | 0 | 2 | 12/11/2025 | 12/11/2025 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 178284 | 01473 | 684 | Solar | 05_01_27W4 | 03/28/2018 | 03/28/2018 | 17 | 11 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/2/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 677981 | 02777 | 10 | Solar | 05_01_413L2 | 03/13/2025 | 09/15/2025 | 118 | 25 | 93 | 09/16/2025 | 09/16/2025 | 53 | 52 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 716246 | 01581 | 3.8 | Solar | 05_01_609W1 | 09/03/2025 | 09/22/2025 | 2 | 0 | 2 | 10/03/2025 | 10/03/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 175116 | 01904 | 25 | Solar | 05_05_11W81 | 10/16/2013 | 10/16/2013 | 6 | 0 | 6 | 10/25/2013 | 10/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2013 |  | 9/1/2014 | N | EXP | 299 |  |  | 0 | 0 | 0 | 5/27/2014 | 5/27/2014 | 7/3/2014 | Connected |  | N
National Grid | REVERE | 643356 | 02151 | 15.2 | Solar | 05_05_312W4 | 09/27/2024 | 09/30/2024 | 1 | 0 | 1 | 10/01/2024 | 10/01/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 313757 | 01832 | 7.83 | Solar | 05_12_29W4 | 10/20/2020 | 10/21/2020 | 0 | 0 | 0 | 10/22/2020 | 10/22/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 | 10/20/2020 | 8/31/2022 | Y | EXP | 365 | 06/30/2021 | 07/26/2021 | 27 | 0 | 27 |  |  | 9/27/2021 | Connected |  | Y
National Grid | BYFIELD | 175084 | 01922 | 144.3 | Solar | 05_12_7W4 | 08/14/2012 | 08/14/2012 | 5 | 0 | 5 | 08/22/2012 | 08/22/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2013 |  | 11/15/2012 | N | EXP | 88 |  |  | 0 | 0 | 0 | 2/11/2013 | 2/11/2013 | 8/8/2014 | Connected |  | N
National Grid | METHUEN | 605419 | 01844 | 7.6 | Solar | 05_14_43L6 | 04/22/2024 | 05/01/2024 | 8 | 7 | 1 | 05/02/2024 | 05/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 04/22/2024 | 5/23/2025 | Y | EXP | 365 | 08/22/2024 | 03/04/2025 | 195 | 0 | 195 |  |  | 3/6/2025 | Connected |  | N
National Grid | LEOMINSTER | 488659 | 01453 | 10.752 | Solar | 05_14_60L2 | 02/08/2023 | 02/09/2023 | 2 | 1 | 1 | 02/10/2023 | 02/10/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2023 | Connected |  | N
National Grid | WORCESTER | 657128 | 01605 | 7.6 | Solar | 05_14_74L5 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 495510 | 01550 | 1600 | Solar | 05_01_219W5 | 04/16/2023 | 06/29/2023 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2023 | 07/26/2023 | 19 | 3 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTMINSTER | 357062 | 01473 | 7.6 | Solar | 05_01_27W4 | 05/26/2021 | 06/03/2021 | 4 | 0 | 4 | 06/04/2021 | 06/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 688350 | 02777 | 10 | Solar | 05_01_413L2 | 04/29/2025 | 06/06/2025 | 3 | 0 | 3 | 06/09/2025 | 06/09/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 04/29/2025 | 8/4/2026 | Y | EXP | 365 | 11/07/2025 | 12/18/2025 | 42 | 0 | 42 |  |  | 12/3/2025 | Connected |  | N
National Grid | WESTBOROUGH | 744618 | 01581 | 11.5 | Battery Add-On | 05_01_609W1 | 01/15/2026 | 01/21/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 175934 | 01902 | 8.6 | Solar | 05_05_11W81 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 |  | 8/15/2016 | N | EXP | 349 |  |  | 0 | 0 | 0 | 3/14/2016 | 3/14/2016 | 3/16/2016 | Connected |  | N
National Grid | REVERE | 643250 | 02151 | 10 | Solar | 05_05_312W4 | 09/27/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 | 09/27/2024 | 12/12/2025 | Y | EXP | 365 | 01/16/2025 | 02/13/2025 | 29 | 0 | 29 |  |  | 2/22/2025 | Connected |  | N
National Grid | HAVERHILL | 451712 | 01835 | 10 | Solar | 05_12_29W4 | 12/19/2022 | 12/20/2022 | 1 | 0 | 1 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2023 | 12/19/2022 | 9/10/2024 | Y | EXP | 365 | 08/09/2023 | 08/29/2023 | 21 | 0 | 21 |  |  | 9/26/2023 | Connected |  | N
National Grid | BYFIELD | 175320 | 01922 | 417.6 | Solar | 05_12_7W4 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 12/23/2014 | 12/23/2014 | 12/31/2014 | Connected |  | N
National Grid | METHUEN | 608805 | 01844 | 7.6 | Solar | 05_14_43L6 | 05/04/2024 | 05/20/2024 | 4 | 0 | 4 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 643637 | 01453 | 10 | Solar | 05_14_60L2 | 09/30/2024 | 10/29/2024 | 1 | 0 | 1 | 10/30/2024 | 10/30/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/30/2024 | 12/10/2025 | Y | EXP | 365 | 02/12/2025 | 02/26/2025 | 15 | 0 | 15 |  |  | 3/7/2025 | Connected |  | N
National Grid | WORCESTER | 665424 | 01605 | 3.8 | Solar | 05_14_74L5 | 01/13/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/13/2025 | 3/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 752371 | 01550 |  | Battery Add-On | 05_01_219W5 | 02/20/2026 | 02/27/2026 | 5 | 0 | 5 | 04/01/2026 | 04/01/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HUBBARDSTON | 442781 | 01452 | 10 | Solar | 05_01_27W4 | 07/14/2022 | 07/18/2022 | 2 | 0 | 2 | 07/19/2022 | 07/19/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2022 | 07/14/2022 | 8/25/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 705879 | 02777 | 10 | Solar | 05_01_413L2 | 07/18/2025 | 08/04/2025 | 5 | 0 | 5 | 08/18/2025 | 08/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 07/18/2025 | 9/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | WESTBOROUGH | 747380 | 01581 | 21.638 | Solar | 05_01_609W1 | 01/28/2026 | 01/30/2026 | 2 | 0 | 2 | 02/02/2026 | 02/02/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  | 2/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SWAMPSCOTT | 176169 | 01907 | 476 | Solar | 05_05_11W81 | 04/17/2015 | 04/17/2015 | 1 | 1 | 0 | 04/22/2015 | 04/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2015 | 04/17/2015 | 12/31/2016 | Y | EXP | 582 | 08/30/2016 | 12/12/2016 | 70 | 0 | 70 | 5/29/2015 | 5/29/2015 | 12/13/2016 | Connected |  | N
National Grid | REVERE | 650666 | 02151 | 1.74 | Solar | 05_05_312W4 | 10/29/2024 | 12/20/2024 | 28 | 24 | 4 | 12/23/2024 | 12/23/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | HAVERHILL | 391442 | 01832 | 3.8 | Solar | 05_12_29W4 | 11/24/2021 | 01/07/2022 | 13 | 9 | 4 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 | 11/24/2021 | 8/2/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2022 | Connected |  | Y
National Grid | BYFIELD | 178244 | 01922 | 153.2 | Solar | 05_12_7W4 | 02/20/2018 | 02/20/2018 | 3 | 0 | 3 | 06/14/2018 | 06/14/2018 | 18 | 14 | 4 | 04/04/2018 | 06/14/2018 | 51 | 44 | 7 |  |  | 0 | 0 | 0 | 06/14/2018 | 51 | 44 | 7 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/31/2021 | N | EXP | 984 |  |  | 0 | 0 | 0 |  |  | 7/14/2021 | Connected |  | N
National Grid | HAVERHILL | 619180 | 01832 | 10 | Solar | 05_14_43L6 | 06/19/2024 | 07/10/2024 | 5 | 1 | 4 | 07/11/2024 | 07/11/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2024 | Connected |  | N
National Grid | LEOMINSTER | 646226 | 01453 | 5.76 | Solar | 05_14_60L2 | 10/21/2024 | 11/07/2024 | 6 | 0 | 6 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/21/2024 | 12/24/2025 | Y | EXP | 365 | 02/26/2025 | 02/25/2025 | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | WORCESTER | 672317 | 01605 | 10 | Solar | 05_14_74L5 | 02/16/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 176008 | 01550 | 6 | Solar | 05_01_219W5 | 08/13/2015 | 08/13/2015 | 2 | 2 | 0 | 08/18/2015 | 08/18/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/19/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 459363 | 01452 | 3.8 | Solar | 05_01_27W4 | 01/05/2023 |  | 213 | 213 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 674825 | 02777 | 7.6 | Solar | 05_01_413L3 | 03/05/2025 | 03/11/2025 | 4 | 0 | 4 | 03/12/2025 | 03/12/2025 | 64 | 47 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 749034 | 01581 | 7.6 | Solar | 05_01_609W1 | 02/03/2026 | 02/06/2026 | 3 | 0 | 3 | 02/09/2026 | 02/09/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SALEM | 176583 | 01970 | 7.6 | Solar | 05_05_11W81 | 04/07/2016 | 04/07/2016 | 4 | 4 | 0 | 04/13/2016 | 04/13/2016 | 199 | 0 | 199 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 |  | 4/12/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 652265 | 02151 | 11.5 | Solar | 05_05_312W4 | 11/05/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 66 | 45 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2025 | Connected |  | N
National Grid | HAVERHILL | 424741 | 01832 | 220 | Solar | 05_12_29W4 | 05/23/2022 | 06/15/2022 | 17 | 8 | 9 | 06/16/2022 | 06/16/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BYFIELD | 596446 | 01922 | 6 | Solar | 05_12_7W4 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2024 | Connected |  | N
National Grid | HAVERHILL | 620785 | 01832 | 7.6 | Solar | 05_14_43L6 | 06/26/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 10/19/2025 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 681996 | 01453 | 22.8 | Solar | 05_14_60L2 | 04/01/2025 | 04/23/2025 | 15 | 12 | 3 | 04/24/2025 | 04/24/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | WORCESTER | 679744 | 01605 | 13.8 | Solar | 05_14_74L5 | 03/21/2025 | 04/01/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2025 | 03/21/2025 | 5/30/2026 | Y | EXP | 365 | 06/13/2025 | 08/22/2025 | 71 | 0 | 71 |  |  | 9/12/2025 | Connected |  | N
National Grid | DUDLEY | 176033 | 01571 | 6.45 | Solar | 05_01_219W5 | 06/19/2015 | 06/19/2015 | 2 | 2 | 0 | 06/23/2015 | 06/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2015 |  | 6/24/2016 | N | EXP | 344 |  |  | 0 | 0 | 0 | 4/7/2016 | 4/7/2016 | 4/13/2016 | Connected |  | N
National Grid | HUBBARDSTON | 582263 | 01452 | 10.44 | Solar | 05_01_27W4 | 01/09/2024 | 01/11/2024 | 3 | 1 | 2 | 01/12/2024 | 01/12/2024 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2024 | Connected |  | N
National Grid | SWANSEA | 680048 | 02777 | 10 | Solar | 05_01_413L3 | 03/26/2025 | 04/30/2025 | 24 | 22 | 2 | 05/01/2025 | 05/01/2025 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 758593 | 01581 | 7.6 | Solar | 05_01_609W1 | 03/24/2026 | 03/25/2026 | 1 | 0 | 1 | 03/26/2026 | 03/26/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 176748 | 01970 | 5 | Solar | 05_05_11W81 | 01/11/2016 | 01/11/2016 | 3 | 3 | 0 | 01/15/2016 | 01/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2016 |  | 1/17/2017 | N | EXP | 350 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 9/1/2016 | Connected |  | N
National Grid | REVERE | 652105 | 02151 | 10 | Solar | 05_05_312W4 | 11/14/2024 | 01/08/2025 | 24 | 19 | 5 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 429973 | 01832 | 6 | Solar | 05_12_29W4 | 05/27/2022 | 06/02/2022 | 3 | 1 | 2 | 06/03/2022 | 06/03/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BYFIELD | 657102 | 01922 | 3.8 | Solar | 05_12_7W4 | 12/02/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 629859 | 01832 | 7.6 | Solar | 05_14_43L6 | 08/02/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/02/2024 | 8/28/2025 | Y | EXP | 365 | 02/28/2025 | 03/20/2025 | 21 | 0 | 21 |  |  | 4/1/2025 | Connected |  | N
National Grid | LEOMINSTER | 725530 | 01453 | 23 | Solar | 05_14_60L2 | 10/09/2025 | 10/17/2025 | 5 | 3 | 2 | 10/20/2025 | 10/20/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2026 | Connected |  | N
National Grid | WORCESTER | 706445 | 01605 | 7.6 | Solar | 05_14_74L5 | 07/22/2025 | 08/28/2025 | 1 | 0 | 1 | 08/29/2025 | 08/29/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 176908 | 01550 | 231 | Solar | 05_01_219W5 | 03/07/2016 | 03/07/2016 | 4 | 4 | 0 | 03/11/2016 | 03/11/2016 | 425 | 14 | 411 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2016 |  | 3/12/2017 | N | EXP | 319 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 623960 | 01452 | 3.8 | Solar | 05_01_27W4 | 07/10/2024 | 07/26/2024 | 2 | 0 | 2 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 07/10/2024 | 8/14/2025 | Y | EXP | 365 | 09/19/2024 | 10/07/2024 | 19 | 0 | 19 |  |  | 11/26/2024 | Connected |  | N
National Grid | SWANSEA | 685196 | 02777 | 10 | Solar | 05_01_413L3 | 04/15/2025 | 04/21/2025 | 4 | 0 | 4 | 04/22/2025 | 04/22/2025 | 34 | 18 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 174268 | 01581 | 300 | Solar | 05_01_609W1 | 12/26/2011 | 12/26/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/16/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 177167 | 01904 | 2.75 | Solar | 05_05_11W81 | 01/25/2017 | 01/25/2017 | 80 | 78 | 2 | 05/22/2017 | 05/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2017 | 01/25/2017 | 1/31/2018 | Y | EXP | 253 | 07/18/2017 | 07/24/2017 | 4 | 0 | 4 | 11/3/2017 | 11/3/2017 | 11/3/2017 | Connected |  | N
National Grid | REVERE | 654499 | 02151 | 9.88 | Solar | 05_05_312W4 | 11/14/2024 | 12/06/2024 | 10 | 5 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | HAVERHILL | 435355 | 01832 | 7.6 | Solar | 05_12_29W4 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 242 | 216 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BYFIELD | 317386 | 01922 | 10 | Solar | 05_12_96W1 | 01/27/2021 | 02/02/2021 | 3 | 0 | 3 | 02/03/2021 | 02/03/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  | 3/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 632034 | 01844 | 3.8 | Solar | 05_14_43L6 | 08/21/2024 | 08/23/2024 | 2 | 0 | 2 | 08/26/2024 | 08/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2024 | Connected |  | N
National Grid | LEOMINSTER | 426194 | 01453 | 460 | Solar | 05_14_60L3 | 05/18/2022 | 07/14/2022 | 38 | 31 | 7 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2023 | 05/18/2022 | 5/22/2026 | Y | STD | 500 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 712554 | 01605 | 17.6 | Solar | 05_14_74L5 | 08/25/2025 | 08/26/2025 | 1 | 0 | 1 | 08/27/2025 | 08/27/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | CHARLTON | 176925 | 01507 | 500 | Solar | 05_01_219W5 | 11/20/2015 | 11/20/2015 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/08/2015 | 01/06/2016 | 19 | 0 | 19 |  | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 | 8/2/2016 | 11/20/2015 | 4/27/2018 | Y | STD | 633 | 10/23/2017 | 03/02/2018 | 83 | 0 | 83 | 4/11/2018 | 4/11/2018 | 4/27/2018 | Connected |  | N
National Grid | WESTMINSTER | 623801 | 01473 | 5.76 | Solar | 05_01_27W4 | 07/10/2024 | 08/02/2024 | 4 | 3 | 1 | 08/05/2024 | 08/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | SWANSEA | 701578 | 02777 | 4980 | Solar | 05_01_413L3 | 12/24/2025 | 02/03/2026 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2026 | 02/25/2026 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTBOROUGH | 174322 | 01581 | 1125 | Solar | 05_01_609W1 | 01/13/2012 | 01/13/2012 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2012 | 05/23/2012 | 49 | 0 | 49 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/8/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 177423 | 01970 | 1260 | Solar | 05_05_11W81 | 12/06/2016 | 12/06/2016 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 01/12/2017 | 18 | 4 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2017 |  | 6/11/2020 | N | STD | 1052 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 664419 | 02152 | 11.5 | Solar | 05_05_312W4 | 01/08/2025 | 03/19/2025 | 3 | 0 | 3 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | HAVERHILL | 448048 | 01832 | 6 | Solar | 05_12_29W4 | 08/15/2022 | 08/23/2022 | 7 | 6 | 1 | 08/24/2022 | 08/24/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 |  | 10/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | Connected |  | N
National Grid | NEWBURY | 329452 | 01950 | 7.6 | Solar | 05_12_96W1 | 02/26/2021 | 03/08/2021 | 5 | 0 | 5 | 03/09/2021 | 03/09/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 5/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 632339 | 01844 | 3.8 | Solar | 05_14_43L6 | 09/11/2024 | 09/16/2024 | 3 | 0 | 3 | 09/17/2024 | 09/17/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 | 09/11/2024 | 10/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2025 | Connected |  | N
National Grid | LEOMINSTER | 475737 | 01453 | 100 | Solar | 05_14_60L3 | 12/15/2022 | 01/18/2023 | 21 | 12 | 9 | 01/19/2023 | 01/19/2023 | 40 | 15 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2023 | 12/15/2022 | 2/19/2027 | Y | EXP | 326 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 590405 | 01605 | 25 | Solar | 05_14_74L6 | 02/15/2024 | 06/24/2024 | 87 | 86 | 1 | 06/25/2024 | 06/25/2024 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2024 |  | 7/1/2026 | N | EXP | 700 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SOUTHBRIDGE | 177974 | 01550 | 6 | Solar | 05_01_219W5 | 06/27/2017 | 06/27/2017 | 37 | 36 | 1 | 08/18/2017 | 08/18/2017 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 |  | 7/2/2018 | N | EXP | 308 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 633504 | 01452 | 5 | Solar | 05_01_27W4 | 08/19/2024 | 08/22/2024 | 2 | 1 | 1 | 08/23/2024 | 08/23/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 | 08/19/2024 | 10/6/2025 | Y | EXP | 365 | 12/07/2024 | 04/24/2025 | 139 | 0 | 139 |  |  | 5/14/2025 | Connected |  | N
National Grid | SWANSEA | 703963 | 02777 | 475 | Solar | 05_01_413L3 | 08/11/2025 | 09/17/2025 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2025 | 10/16/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTBOROUGH | 174685 | 01581 | 7.6 | Solar | 05_01_609W1 | 03/09/2011 | 03/09/2011 | 423 | 60 | 363 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 177710 | 01970 | 7.6 | Solar | 05_05_11W81 | 05/30/2017 | 05/30/2017 | 7 | 7 | 0 | 06/08/2017 | 06/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2017 | 05/30/2017 | 6/4/2018 | Y | EXP | 360 | 09/28/2017 | 10/13/2017 | 10 | 0 | 10 | 10/25/2017 | 10/25/2017 | 10/30/2017 | Connected |  | N
National Grid | WINTHROP | 674216 | 02152 | 15.2 | Solar | 05_05_312W4 | 02/25/2025 | 02/27/2025 | 2 | 0 | 2 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | HAVERHILL | 520372 | 01832 | 6 | Solar | 05_12_29W4 | 04/28/2023 | 05/02/2023 | 3 | 1 | 2 | 05/03/2023 | 05/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 330348 | 01950 | 7.6 | Solar | 05_12_96W1 | 12/08/2020 | 12/29/2020 | 13 | 8 | 5 | 12/30/2020 | 12/30/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 |  | 12/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2021 | Connected |  | N
National Grid | LAWRENCE | 637411 | 01840 | 5.76 | Solar | 05_14_43L6 | 09/03/2024 | 09/26/2024 | 4 | 0 | 4 | 09/27/2024 | 09/27/2024 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/03/2024 | 11/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | LEOMINSTER | 510521 | 01453 | 480 | Solar | 05_14_60L3 | 08/01/2023 | 09/08/2023 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2023 | 12/11/2023 | 63 | 45 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 | 08/01/2023 | 10/26/2027 | Y | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WORCESTER | 605450 | 01605 | 11.4 | Solar | 05_14_74L6 | 04/24/2024 | 07/19/2024 | 39 | 39 | 0 | 07/22/2024 | 07/22/2024 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 | 04/24/2024 | 10/10/2025 | Y | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SOUTHBRIDGE | 178765 | 01550 | 495 | Solar | 05_01_219W5 | 07/29/2013 | 07/29/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2013 | 03/03/2014 | 139 | 0 | 139 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2014 |  | 1/31/2014 | N | STD | 41 |  |  | 0 | 0 | 0 | 7/14/2014 | 7/14/2014 | 7/24/2014 | Connected |  | N
National Grid | WESTMINSTER | 643734 | 01473 | 7.6 | Solar | 05_01_27W4 | 10/01/2024 | 11/18/2024 | 18 | 13 | 5 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | SWANSEA | 711116 | 02777 | 150 | Solar | 05_01_413L3 | 08/11/2025 | 09/08/2025 | 19 | 9 | 10 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTBOROUGH | 174973 | 01581 | 91.2 | Solar | 05_01_609W1 | 09/26/2011 | 09/26/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 177751 | 01902 | 5.2 | Solar | 05_05_11W81 | 07/27/2017 | 07/27/2017 | 9 | 9 | 0 | 08/09/2017 | 08/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2017 | 07/27/2017 | 8/1/2018 | Y | EXP | 348 | 08/24/2017 | 09/09/2017 | 11 | 0 | 11 | 11/27/2017 | 11/27/2017 | 12/1/2017 | Connected |  | N
National Grid | WINTHROP | 676548 | 02152 | 10 | Solar | 05_05_312W4 | 03/11/2025 | 03/27/2025 | 13 | 8 | 5 | 03/28/2025 | 03/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 536037 | 01832 | 3.8 | Solar | 05_12_29W4 | 08/21/2023 | 08/29/2023 | 7 | 5 | 2 | 08/30/2023 | 08/30/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 |  | 11/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2024 | Connected |  | N
National Grid | NEWBURY | 366061 | 01950 | 6 | Solar | 05_12_96W1 | 08/06/2021 | 01/03/2022 | 18 | 16 | 2 | 09/01/2021 | 09/01/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 | 08/06/2021 | 6/8/2023 | Y | EXP | 365 | 02/11/2022 | 03/29/2022 | 47 | 0 | 47 |  |  | 8/16/2022 | Connected |  | Y
National Grid | METHUEN | 644208 | 01844 | 5.76 | Solar | 05_14_43L6 | 10/01/2024 | 11/01/2024 | 7 | 2 | 5 | 11/04/2024 | 11/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/01/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 176280 | 01453 | 42 | Solar | 05_14_60L3 | 05/06/2015 | 05/06/2015 | 0 | 0 | 0 | 05/07/2015 | 05/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2015 | 05/06/2015 | 10/30/2015 | Y | EXP | 161 | 03/14/2016 | 03/14/2016 | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 5/13/2016 | Connected |  | N
National Grid | WORCESTER | 719923 | 01605 | 5.76 | Solar | 05_14_74L6 | 09/22/2025 | 10/06/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 | 09/22/2025 | 12/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SOUTHBRIDGE | 186058 | 01550 | 4600 | Solar | 05_01_219W5 | 06/28/2018 | 06/28/2018 | 23 | 14 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2018 | 08/02/2018 | 1 | 1 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  | 6/28/2021 | N | STD | 613 | 12/04/2020 | 06/10/2021 | 188 | 0 | 188 |  |  | 6/21/2021 | Connected |  | N
National Grid | WESTMINSTER | 647137 | 01473 | 3.8 | Solar | 05_01_27W4 | 10/23/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 50 | 32 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | SWANSEA | 741865 | 02777 | 5.76 | Solar | 05_01_413L3 | 12/22/2025 | 12/29/2025 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 175523 | 01581 | 499 | Solar | 05_01_609W1 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/04/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 | 07/25/2014 | 3/31/2018 | Y | STD | 974 | 05/09/2017 | 03/19/2018 | 198 | 0 | 198 | 2/13/2018 | 2/13/2018 | 3/19/2018 | Connected |  | N
National Grid | LYNN | 178549 | 01904 | 5 | Solar | 05_05_11W81 | 03/09/2018 | 03/09/2018 | 22 | 0 | 22 | 04/27/2018 | 04/27/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2018 |  | 3/18/2019 | N | EXP | 314 |  |  | 0 | 0 | 0 |  |  | 10/29/2018 | Connected |  | N
National Grid | WINTHROP | 681799 | 02152 | 20 | Solar | 05_05_312W4 | 04/02/2025 | 04/07/2025 | 3 | 0 | 3 | 04/08/2025 | 04/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | HAVERHILL | 553302 | 01835 | 5 | Solar | 05_12_29W4 | 09/18/2023 | 10/02/2023 | 10 | 8 | 2 | 10/03/2023 | 10/03/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 383495 | 01950 | 9.8 | Solar | 05_12_96W1 | 11/09/2021 | 12/20/2021 | 1 | 0 | 1 | 11/12/2021 | 11/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 |  | 12/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2022 | Connected |  | Y
National Grid | METHUEN | 646547 | 01844 | 3.8 | Solar | 05_14_43L6 | 10/21/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/21/2024 | 12/30/2025 | Y | EXP | 365 | 03/15/2025 | 04/10/2025 | 27 | 0 | 27 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 177073 | 01523 | 36 | Solar | 05_14_60L3 | 08/03/2016 | 08/03/2016 | 1 | 0 | 1 | 08/05/2016 | 08/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2016 |  | 8/9/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 12/29/2016 | 12/29/2016 | 12/27/2016 | Connected |  | N
National Grid | WORCESTER | 177324 | 01605 | 10 | Solar | 05_14_74L6 | 06/17/2016 | 06/17/2016 | 0 | 0 | 0 | 06/21/2016 | 06/21/2016 | 156 | 0 | 156 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2016 |  | 6/26/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 373151 | 01550 | 7.6 | Solar | 05_01_219W5 | 08/18/2021 | 08/31/2021 | 8 | 3 | 5 | 09/01/2021 | 09/01/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 680013 | 01473 | 15.76 | Solar | 05_01_27W4 | 03/24/2025 | 03/26/2025 | 2 | 0 | 2 | 03/27/2025 | 03/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | SWANSEA | 742664 | 02777 | 11.4 | Solar | 05_01_413L3 | 12/30/2025 | 01/02/2026 | 2 | 0 | 2 | 01/05/2026 | 01/05/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 175522 | 01581 | 499 | Solar | 05_01_609W1 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/04/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 | 07/25/2014 | 3/31/2018 | Y | STD | 974 | 05/09/2017 | 03/19/2018 | 198 | 0 | 198 | 2/13/2018 | 2/13/2018 | 3/19/2018 | Connected |  | N
National Grid | LYNN | 178548 | 01904 | 6 | Solar | 05_05_11W81 | 03/09/2018 | 03/09/2018 | 24 | 24 | 0 | 04/27/2018 | 04/27/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2018 |  | 3/18/2019 | N | EXP | 318 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N
National Grid | WINTHROP | 696492 | 02152 | 23 | Solar | 05_05_312W4 | 06/05/2025 | 06/10/2025 | 3 | 0 | 3 | 06/11/2025 | 06/11/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | HAVERHILL | 560742 | 01832 | 10 | Solar | 05_12_29W4 | 10/11/2023 | 10/13/2023 | 3 | 2 | 1 | 10/16/2023 | 10/16/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2023 |  | 1/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | NEWBURY | 533569 | 01950 | 0 | Solar | 05_12_96W1 | 06/16/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2023 |  | 8/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | METHUEN | 647008 | 01844 | 5.76 | Solar | 05_14_43L6 | 10/29/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 10/29/2024 | 2/10/2026 | Y | EXP | 365 | 06/12/2025 | 11/26/2025 | 168 | 0 | 168 |  |  | 12/10/2025 | Connected |  | N
National Grid | LEOMINSTER | 177456 | 01453 | 594 | Solar | 05_14_60L3 | 12/07/2016 | 12/07/2016 | 40 | 25 | 15 | 02/06/2017 | 02/06/2017 | 0 | 0 | 0 | 05/22/2017 | 03/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2017 |  | 12/12/2017 | N | EXP | 172 |  |  | 0 | 0 | 0 | 10/11/2017 | 10/11/2017 | 10/17/2017 | Connected |  | N
National Grid | WORCESTER | 177643 | 01605 | 10 | Solar | 05_14_74L6 | 07/20/2017 | 07/20/2017 | 5 | 0 | 5 | 07/28/2017 | 07/28/2017 | 131 | 0 | 131 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2017 |  | 7/26/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 438321 | 01550 | 5.22 | Solar | 05_01_219W5 | 06/21/2022 | 06/23/2022 | 2 | 1 | 1 | 06/24/2022 | 06/24/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 | 06/21/2022 | 4/4/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | Y
National Grid | WESTMINSTER | 678914 | 01473 | 3.8 | Solar | 05_01_27W5 | 03/18/2025 | 03/26/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 | 03/18/2025 | 6/16/2026 | Y | EXP | 365 | 08/05/2025 | 09/30/2025 | 57 | 0 | 57 |  |  |  | Completion Documents |  | N
National Grid | SWANSEA | 749054 | 02777 | 19.12 | Solar | 05_01_413L3 | 02/03/2026 |  | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WESTBOROUGH | 175521 | 01581 | 499 | Solar | 05_01_609W1 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/04/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 | 07/25/2014 | 3/31/2018 | Y | STD | 974 | 05/09/2017 | 03/19/2018 | 198 | 0 | 198 | 12/5/2017 | 12/5/2017 | 3/19/2018 | Connected |  | N
National Grid | SWAMPSCOTT | 178609 | 01902 | 6 | Solar | 05_05_11W81 | 12/13/2017 | 12/13/2017 | 49 | 35 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 |  | 12/18/2018 | N | EXP | 295 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | WINTHROP | 698560 | 02152 | 6.27 | Solar | 05_05_312W4 | 06/23/2025 | 09/15/2025 | 59 | 55 | 4 | 09/16/2025 | 09/16/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | HAVERHILL | 568043 | 01832 | 60 | Solar | 05_12_29W4 | 06/12/2024 | 07/09/2024 | 17 | 9 | 8 | 07/10/2024 | 07/10/2024 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | NEWBURY | 562542 | 01950 | 10 | Solar | 05_12_96W1 | 10/17/2023 | 10/20/2023 | 4 | 1 | 3 | 10/23/2023 | 10/23/2023 | 55 | 31 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  | 1/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2024 | Connected |  | N
National Grid | METHUEN | 646952 | 01844 | 3.8 | Solar | 05_14_43L6 | 01/13/2025 | 03/20/2025 | 13 | 8 | 5 | 03/21/2025 | 03/21/2025 | 66 | 50 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 216789 | 01453 | 55 | Solar | 05_14_60L3 | 04/02/2019 | 04/11/2019 | 6 | 5 | 1 | 04/12/2019 | 04/12/2019 | 3 | 0 | 3 | 05/23/2019 | 06/20/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 06/20/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 7/12/2019 |  | 7/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 178226 | 01604 | 11.4 | Solar | 05_14_74L6 | 01/03/2018 | 01/03/2018 | 15 | 9 | 6 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 | 01/03/2018 | 1/10/2019 | Y | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 12/12/2019 | Connected |  | N
National Grid | DUDLEY | 472241 | 01571 | 6.38 | Solar | 05_01_219W5 | 11/17/2022 | 01/30/2023 | 47 | 46 | 1 | 01/31/2023 | 01/31/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  | 5/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2023 | Connected |  | N
National Grid | WESTMINSTER | 689732 | 01473 | 5.76 | Solar | 05_01_27W5 | 05/05/2025 | 05/16/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SWANSEA | 757329 | 02777 |  | Battery Add-On | 05_01_413L3 | 03/18/2026 | 03/20/2026 | 2 | 0 | 2 | 03/23/2026 | 03/23/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 175773 | 01581 | 480 | Solar | 05_01_609W1 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 199525 | 01970 | 1000 | Solar | 05_05_11W81 | 10/26/2018 | 11/16/2018 | 15 | 9 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2018 | 12/18/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 699713 | 02152 | 7.6 | Solar | 05_05_312W4 | 06/19/2025 | 07/02/2025 | 5 | 2 | 3 | 07/29/2025 | 07/29/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/19/2025 | 8/18/2026 | Y | EXP | 365 | 09/13/2025 | 11/05/2025 | 54 | 0 | 54 |  |  | 1/7/2026 | Connected |  | N
National Grid | HAVERHILL | 572629 | 01832 | 10 | Solar | 05_12_29W4 | 12/01/2023 | 12/04/2023 | 1 | 0 | 1 | 12/05/2023 | 12/05/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 | 12/01/2023 | 1/25/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | NEWBURY | 588443 | 01950 | 22.8 | Solar | 05_12_96W1 | 08/05/2024 | 08/19/2024 | 10 | 9 | 1 | 08/20/2024 | 08/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/05/2024 | 9/27/2025 | Y | EXP | 365 | 12/03/2024 | 01/08/2025 | 37 | 0 | 37 |  |  | 1/21/2025 | Connected |  | Y
National Grid | LAWRENCE | 651431 | 01841 | 7.6 | Solar | 05_14_43L6 | 11/13/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/13/2024 | 1/27/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | LEOMINSTER | 276671 | 01453 | 400 | Solar | 05_14_60L3 | 05/29/2020 | 07/09/2020 | 29 | 23 | 6 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178524 | 01604 | 10 | Solar | 05_14_74L6 | 04/04/2018 | 04/04/2018 | 11 | 10 | 1 | 05/18/2018 | 05/18/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2018 |  | 4/10/2019 | N | EXP | 316 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 505826 | 01550 | 6 | Solar | 05_01_219W5 | 05/03/2023 | 05/04/2023 | 1 | 0 | 1 | 05/05/2023 | 05/05/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 706568 | 01452 | 15.76 | Solar | 05_01_27W5 | 07/23/2025 | 07/29/2025 | 4 | 0 | 4 | 07/30/2025 | 07/30/2025 | 67 | 49 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SWANSEA | 175014 | 02777 | 1500 | Solar | 05_01_413L3 | 07/29/2011 | 07/29/2011 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2011 | 12/02/2011 | 46 | 0 | 46 |  | 0 | 0 | 0 | 03/16/2012 | 04/23/2012 | 24 | 0 | 24 | 12/12/2012 | 07/29/2011 | 1/1/2013 | Y | STD | 20 | 03/04/2014 | 03/07/2014 | 3 | 0 | 3 | 4/24/2013 | 4/24/2013 | 4/24/2013 | Connected |  | N
National Grid | WESTBOROUGH | 175772 | 01581 | 480 | Solar | 05_01_609W1 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 315459 | 01902 | 998 | Solar | 05_05_11W81 | 02/22/2021 | 04/30/2021 | 48 | 39 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2021 | 06/15/2021 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 711356 | 02152 | 13.12 | Solar | 05_05_312W4 | 08/15/2025 | 10/09/2025 | 12 | 10 | 2 | 10/10/2025 | 10/10/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/26/2025 | Connected |  | N
National Grid | HAVERHILL | 576101 | 01832 | 6 | Solar | 05_12_29W4 | 12/19/2023 |  | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 645728 | 01950 | 5.76 | Solar | 05_12_96W1 | 10/08/2024 | 10/29/2024 | 2 | 1 | 1 | 10/31/2024 | 10/31/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/08/2024 | 12/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | LAWRENCE | 652542 | 01841 | 4.35 | Solar | 05_14_43L6 | 11/06/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2025 | Connected |  | N
National Grid | LEOMINSTER | 349427 | 01453 | 9.8 | Solar | 05_14_60L3 | 04/21/2021 | 04/26/2021 | 2 | 0 | 2 | 04/27/2021 | 04/27/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178591 | 01604 | 3.8 | Solar | 05_14_74L6 | 03/14/2018 | 03/14/2018 | 24 | 24 | 0 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 3/20/2019 | N | EXP | 302 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 540185 | 01550 | 4.35 | Solar | 05_01_219W5 | 08/31/2023 | 09/01/2023 | 1 | 0 | 1 | 09/05/2023 | 09/05/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 08/31/2023 | 10/13/2024 | Y | EXP | 365 | 01/18/2024 | 02/07/2024 | 21 | 0 | 21 |  |  | 2/7/2024 | Connected |  | N
National Grid | HUBBARDSTON | 731667 | 01452 | 7.6 | Solar | 05_01_27W5 | 11/12/2025 | 01/26/2026 | 2 | 0 | 2 | 02/04/2026 | 02/04/2026 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SWANSEA | 175013 | 02777 | 1500 | Solar | 05_01_413L3 | 07/29/2011 | 07/29/2011 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2011 | 12/02/2011 | 46 | 0 | 46 |  | 0 | 0 | 0 | 03/16/2012 | 04/23/2012 | 24 | 0 | 24 | 12/12/2012 | 07/29/2011 | 1/1/2013 | Y | STD | 20 |  |  | 0 | 0 | 0 | 4/24/2013 | 4/24/2013 | 4/24/2013 | Connected |  | N
National Grid | WESTBOROUGH | 175836 | 01581 | 990 | Solar | 05_01_609W1 | 02/27/2015 | 02/27/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/08/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 349385 | 01970 | 7.6 | Solar | 05_05_11W81 | 04/05/2021 | 04/14/2021 | 6 | 0 | 6 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2021 | Connected |  | N
National Grid | WINTHROP | 718516 | 02152 | 15.2 | Solar | 05_05_312W4 | 09/11/2025 | 09/18/2025 | 5 | 0 | 5 | 09/19/2025 | 09/19/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N
National Grid | HAVERHILL | 599284 | 01832 | 0 | Battery Add-On | 05_12_29W4 | 03/25/2024 | 03/28/2024 | 3 | 1 | 2 | 03/29/2024 | 03/29/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 | 03/25/2024 | 7/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | NEWBURY | 657458 | 01950 | 3.8 | Solar | 05_12_96W1 | 11/27/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | LAWRENCE | 652555 | 01841 | 5.76 | Solar | 05_14_43L6 | 11/06/2024 | 12/02/2024 | 6 | 0 | 6 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 396682 | 01453 | 0 | Other | 05_14_60L3 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 03/03/2022 | 32 | 0 | 32 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 215537 | 01604 | 10 | Solar | 05_14_74L6 | 04/02/2019 | 04/10/2019 | 6 | 6 | 0 | 04/11/2019 | 04/11/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2019 | 04/02/2019 | 2/5/2020 | Y | EXP | 296 | 11/06/2019 | 11/22/2019 | 16 | 0 | 16 |  |  | 11/26/2019 | Connected |  | N
National Grid | SOUTHBRIDGE | 546565 | 01550 | 7.6 | Solar | 05_01_219W5 | 08/08/2023 |  | 120 | 120 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 735538 | 01452 | 10 | Solar | 05_01_27W5 | 11/21/2025 | 11/24/2025 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 57 | 44 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | SWANSEA | 175096 | 02777 | 500 | Solar | 05_01_413L3 | 10/26/2012 | 10/26/2012 | 0 | 0 | 0 | 11/19/2012 | 11/19/2012 | 203 | 0 | 203 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 175834 | 01581 | 990 | Solar | 05_01_609W1 | 02/27/2015 | 02/27/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/08/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 443975 | 01902 | 0 | Other | 05_05_11W81 | 11/09/2022 | 01/31/2023 | 50 | 40 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2023 | 03/02/2023 | 22 | 2 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 679646 | 02152 | 0 | Other | 05_05_312W5 | 10/08/2025 | 11/20/2025 | 29 | 19 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 12/17/2025 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HAVERHILL | 607416 | 01832 | 0 | Battery Add-On | 05_12_29W4 | 04/29/2024 | 05/23/2024 | 18 | 14 | 4 | 05/24/2024 | 05/24/2024 | 56 | 41 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 658693 | 01950 | 5.76 | Solar | 05_12_96W1 | 12/05/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | LAWRENCE | 653571 | 01841 | 7.6 | Solar | 05_14_43L6 | 11/13/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 521128 | 01453 | 0 | Other | 05_14_60L3 | 08/11/2023 | 08/28/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2023 | 02/09/2024 | 112 | 93 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 261851 | 01604 | 7.6 | Solar | 05_14_74L6 | 11/05/2019 | 01/08/2020 | 40 | 33 | 7 | 01/09/2020 | 01/09/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 | 11/05/2019 | 1/15/2021 | Y | EXP | 365 | 07/07/2020 | 07/10/2020 | 3 | 0 | 3 |  |  | 1/11/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 554393 | 01550 | 12.285 | Solar | 05_01_219W5 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2023 |  | 11/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2024 | Connected |  | N
National Grid | HUBBARDSTON | 746935 | 01452 | 11.4 | Solar | 05_01_27W5 | 01/22/2026 | 01/28/2026 | 3 | 0 | 3 | 02/06/2026 | 02/06/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 | 01/22/2026 | 2/27/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SWANSEA | 175249 | 02777 | 1000 | Solar | 05_01_413L3 | 11/04/2014 | 11/04/2014 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2014 | 01/05/2015 | 21 | 21 | 0 |  | 0 | 0 | 0 | 01/20/2017 | 02/17/2017 | 20 | 0 | 20 | 7/11/2017 | 11/04/2014 | 7/31/2018 | Y | STD | 385 | 12/27/2017 | 05/08/2018 | 132 | 0 | 132 | 6/12/2018 | 6/20/2018 | 7/26/2018 | Connected |  | N
National Grid | WESTBOROUGH | 176313 | 01581 | 96 | Solar | 05_01_609W1 | 05/07/2015 | 05/07/2015 | 0 | 0 | 0 | 05/11/2015 | 05/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2015 |  | 10/30/2015 | N | EXP | 170 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 5/10/2016 | Connected |  | N
National Grid | LYNN | 489747 | 01902 | 10 | Solar | 05_05_11W81 | 01/09/2023 | 01/11/2023 | 2 | 0 | 2 | 01/12/2023 | 01/12/2023 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2023 | 01/09/2023 | 5/3/2024 | Y | EXP | 365 | 04/11/2023 | 05/02/2023 | 22 | 0 | 22 |  |  | 6/21/2023 | Connected |  | Y
National Grid | WINTHROP | 174692 | 02152 | 4000 |  | 05_05_312W5 | 10/26/2010 | 10/26/2010 | 81 | 0 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 615475 | 01832 | 6 | Solar | 05_12_29W4 | 06/04/2024 | 06/17/2024 | 4 | 0 | 4 | 06/18/2024 | 06/18/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2024 | Connected |  | N
National Grid | NEWBURY | 672877 | 01922 | 5.76 | Solar | 05_12_96W1 | 02/19/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/19/2025 | 5/16/2026 | Y | EXP | 365 | 09/23/2025 | 09/22/2025 | 0 | 0 | 0 |  |  | 9/28/2025 | Connected |  | N
National Grid | LAWRENCE | 661414 | 01841 | 5.76 | Solar | 05_14_43L6 | 12/18/2024 | 01/03/2025 | 11 | 7 | 4 | 01/06/2025 | 01/06/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | LEOMINSTER | 665620 | 01453 | 67.3 | Solar | 05_14_60L3 | 01/22/2025 | 02/14/2025 | 17 | 7 | 10 | 02/18/2025 | 02/18/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 1/16/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 11/13/2025 | Connected |  | N
National Grid | WORCESTER | 289216 | 01604 | 7.6 | Solar | 05_14_74L6 | 05/21/2020 | 05/27/2020 | 2 | 0 | 2 | 05/28/2020 | 05/28/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/21/2020 | 9/17/2021 | Y | EXP | 365 | 01/20/2021 | 01/28/2021 | 8 | 0 | 8 |  |  | 7/16/2021 | Connected |  | N
National Grid | DUDLEY | 642791 | 01571 | 15.2 | Solar | 05_01_219W5 | 03/11/2025 | 03/27/2025 | 12 | 8 | 4 | 03/28/2025 | 03/28/2025 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | HUBBARDSTON | 750555 | 01452 | 3.8 | Solar | 05_01_27W5 | 02/11/2026 | 02/17/2026 | 1 | 0 | 1 | 02/26/2026 | 02/26/2026 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SWANSEA | 175248 | 02777 | 1000 | Solar | 05_01_413L3 | 11/04/2014 | 11/04/2014 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2014 | 01/05/2015 | 21 | 21 | 0 |  | 0 | 0 | 0 | 01/20/2017 | 02/17/2017 | 20 | 0 | 20 | 7/11/2017 | 11/04/2014 | 7/31/2018 | Y | STD | 385 | 12/27/2017 | 05/08/2018 | 132 | 0 | 132 |  |  | 7/26/2018 | Connected |  | N
National Grid | WESTBOROUGH | 176505 | 01581 | 540 | Solar | 05_01_609W1 | 03/24/2016 | 03/29/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2016 | 05/26/2016 | 41 | 37 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 03/24/2016 | 12/31/2018 | Y | STD | 746 | 12/12/2018 | 01/02/2019 | 21 | 0 | 21 |  |  | 12/31/2018 | Connected |  | N
National Grid | LYNN | 533802 | 01904 | 2400 | Solar | 05_05_11W81 | 07/24/2023 | 09/08/2023 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2023 | 09/18/2023 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 174886 | 02152 | 1500 | Solar | 05_05_312W5 | 02/21/2013 | 02/21/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/05/2013 | 04/05/2013 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 |  | 8/30/2013 | N | STD | 18 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 649937 | 01832 | 7.6 | Solar | 05_12_29W4 | 10/29/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2025 | Connected |  | N
National Grid | NEWBURY | 644686 | 01950 | 3.8 | Solar | 05_12_9C1 | 10/03/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2024 |  | 12/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2025 | Connected |  | Y
National Grid | LAWRENCE | 664963 | 01841 | 9.86 | Solar | 05_14_43L6 | 01/21/2025 | 02/18/2025 | 7 | 2 | 5 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 | 01/21/2025 | 3/26/2026 | Y | EXP | 365 | 06/12/2025 | 08/19/2025 | 69 | 0 | 69 |  |  | 8/22/2025 | Connected |  | N
National Grid | LEOMINSTER | 174776 | 01453 | 3000 | Solar | 05_14_60L4 | 01/22/2013 | 01/22/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/30/2013 | 05/21/2013 | 69 | 0 | 69 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 334597 | 01604 | 7.6 | Solar | 05_14_74L6 | 01/13/2021 | 02/05/2021 | 16 | 16 | 0 | 02/08/2021 | 02/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/13/2021 | 9/2/2022 | Y | EXP | 365 | 08/15/2021 | 09/01/2021 | 16 | 3 | 13 |  |  | 2/2/2022 | Connected |  | N
National Grid | DUDLEY | 651521 | 01571 | 10 | Solar | 05_01_219W5 | 11/13/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 35 | 10 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2025 | Connected |  | N
National Grid | WESTMINSTER | 753948 | 01473 | 16.403 | Solar | 05_01_27W5 | 03/02/2026 | 03/10/2026 | 5 | 2 | 3 | 03/11/2026 | 03/11/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SWANSEA | 175245 | 02777 | 1000 | Solar | 05_01_413L3 | 08/28/2014 | 08/28/2014 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/09/2014 | 10/07/2014 | 21 | 21 | 0 |  | 0 | 0 | 0 | 01/20/2017 | 02/17/2017 | 20 | 0 | 20 | 7/11/2017 | 08/28/2014 | 7/31/2018 | Y | STD | 385 | 12/27/2017 | 05/08/2018 | 132 | 0 | 132 | 6/11/2018 | 6/20/2018 | 7/18/2018 | Connected |  | N
National Grid | WESTBOROUGH | 176744 | 01581 | 2000 | Solar | 05_01_609W1 | 11/02/2015 | 11/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/04/2015 | 12/04/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/8/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 564941 | 01904 | 10 | Solar | 05_05_11W81 | 11/03/2023 | 12/12/2023 | 26 | 23 | 3 | 12/13/2023 | 12/13/2023 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 11/03/2023 | 5/2/2025 | Y | EXP | 365 | 04/19/2024 | 05/17/2024 | 29 | 0 | 29 |  |  | 7/19/2024 | Connected |  | N
National Grid | MEDFORD | 175128 | 02155 | 750 | Solar | 05_05_312W5 | 07/27/2011 | 07/27/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2011 | 01/23/2013 | 335 | 0 | 335 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2012 | 07/27/2011 | 12/31/2012 | Y | STD | 116 | 03/05/2013 | 04/22/2013 | 29 | 0 | 29 | 6/12/2013 | 6/12/2013 | 7/11/2013 | Connected |  | N
National Grid | HAVERHILL | 653916 | 01832 | 3.8 | Solar | 05_12_29W4 | 11/15/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 11/15/2024 | 2/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2025 | Connected |  | N
National Grid | NEWBURY | 178026 | 01951 | 166.75 | Solar | 05_12_9C2 | 08/31/2017 | 08/31/2017 | 21 | 20 | 1 | 10/03/2017 | 10/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2017 |  | 12/16/2019 | N | EXP | 804 |  |  | 0 | 0 | 0 |  |  | 1/23/2020 | Connected |  | N
National Grid | METHUEN | 665201 | 01844 | 3.8 | Solar | 05_14_43L6 | 01/13/2025 | 01/29/2025 | 5 | 0 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 | 01/13/2025 | 3/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 175389 | 01453 | 100 | Solar | 05_14_60L4 | 09/11/2014 | 09/11/2014 | 7 | 0 | 7 | 09/23/2014 | 09/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2014 |  | 12/19/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 2/5/2015 | 2/5/2015 | 2/18/2015 | Connected |  | N
National Grid | WORCESTER | 501293 | 01604 | 6 | Solar | 05_14_74L6 | 04/13/2023 |  | 202 | 198 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 655465 | 01571 | 7.6 | Solar | 05_01_219W5 | 11/20/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 176244 | 01452 | 96 | Solar | 05_01_27W5 | 04/30/2015 | 04/30/2015 | 1 | 1 | 0 | 05/05/2015 | 05/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 |  | 10/30/2015 | N | EXP | 171 |  |  | 0 | 0 | 0 | 6/1/2015 | 6/1/2015 | 12/2/2016 | Connected |  | N
National Grid | SWANSEA | 175794 | 02777 | 1000 | Solar | 05_01_413L3 | 09/16/2015 | 09/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2015 | 10/19/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/26/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 176743 | 01581 | 2200 | Solar | 05_01_609W1 | 11/02/2015 | 11/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/04/2015 | 12/04/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/8/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 562469 | 01902 | 5 | Solar | 05_05_11W81 | 11/06/2023 | 11/28/2023 | 14 | 12 | 2 | 11/29/2023 | 11/29/2023 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 176007 | 02155 | 857.1 | Solar | 05_05_312W5 | 08/12/2015 | 08/12/2015 | 2 | 2 | 0 | 08/20/2015 | 08/20/2015 | 42 | 15 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 655303 | 01832 | 10 | Solar | 05_12_29W4 | 11/19/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/19/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | NEWBURY | 225166 | 01950 | 0 | Other | 05_12_9C2 | 05/07/2019 | 07/02/2019 | 8 | 7 | 1 |  |  | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 | 05/07/2019 | 2/6/2022 | Y | STD | 104 | 07/23/2021 | 07/22/2021 | 0 | 0 | 0 |  |  | 12/30/2021 | Connected |  | N
National Grid | LAWRENCE | 681823 | 01841 | 6.5 | Solar | 05_14_43L6 | 04/02/2025 | 04/18/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 72 | 58 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 178375 | 01453 | 7.6 | Solar | 05_14_60L4 | 11/21/2017 | 11/21/2017 | 10 | 0 | 10 | 12/07/2017 | 12/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2017 |  | 2/15/2019 | N | EXP | 435 |  |  | 0 | 0 | 0 |  |  | 11/12/2019 | Connected |  | N
National Grid | WORCESTER | 516167 | 01604 | 6 | Solar | 05_14_74L6 | 06/20/2023 | 06/22/2023 | 3 | 1 | 2 | 06/23/2023 | 06/23/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 9/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 680944 | 01550 | 20 | Solar | 05_01_219W5 | 03/27/2025 | 04/14/2025 | 12 | 8 | 4 | 04/15/2025 | 04/15/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 209675 | 01452 | 7.6 | Solar | 05_01_27W5 | 02/21/2019 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 | 02/21/2019 | 10/10/2019 | Y | EXP | 223 | 05/30/2019 | 07/15/2019 | 46 | 0 | 46 |  |  | 8/27/2019 | Connected |  | N
National Grid | SWANSEA | 175793 | 02777 | 760 | Solar | 05_01_413L3 | 09/16/2015 | 09/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2015 | 10/19/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/26/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 177289 | 01581 | 174 | Hydro | 05_01_609W1 | 06/17/2016 | 07/06/2016 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2016 | 09/06/2016 | 43 | 25 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 | 06/17/2016 | 9/25/2020 | Y | STD | 1176 |  |  | 0 | 0 | 0 |  |  | 9/28/2020 | Connected |  | N
National Grid | LYNN | 569149 | 01904 | 15 | Solar | 05_05_11W81 | 11/06/2023 | 11/17/2023 | 9 | 6 | 3 | 11/20/2023 | 11/20/2023 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 |  | 1/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2024 | Connected |  | N
National Grid | MEDFORD | 176852 | 02155 | 60.42 | Solar | 05_05_312W5 | 11/11/2015 | 11/11/2015 | 1 | 1 | 0 | 11/16/2015 | 11/16/2015 | 267 | 0 | 267 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2015 |  | 11/18/2016 | N | EXP | 367 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 663743 | 01832 | 5.76 | Solar | 05_12_29W4 | 01/03/2025 | 01/16/2025 | 5 | 0 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 01/03/2025 | 3/11/2026 | Y | EXP | 365 | 06/26/2025 | 06/28/2025 | 3 | 0 | 3 |  |  | 7/18/2025 | Connected |  | N
National Grid | NEWBURY | 290620 | 01950 | 60 | Solar | 05_12_9C2 | 06/05/2020 | 08/10/2020 | 46 | 39 | 7 | 08/11/2020 | 08/11/2020 | 43 | 26 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 5/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2021 | Connected |  | N
National Grid | LAWRENCE | 695537 | 01841 | 7.6 | Solar | 05_14_43L6 | 06/04/2025 | 06/16/2025 | 13 | 11 | 2 | 08/14/2025 | 08/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2025 |  | 9/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | LEOMINSTER | 178464 | 01453 | 199.8 | Solar | 05_14_60L4 | 01/22/2018 | 01/22/2018 | 0 | 0 | 0 | 03/21/2018 | 03/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 |  | 1/28/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 6/28/2018 | Connected |  | N
National Grid | WORCESTER | 558017 | 01604 | 7.6 | Solar | 05_14_74L6 | 10/04/2023 | 10/09/2023 | 3 | 0 | 3 | 10/10/2023 | 10/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 10/04/2023 | 11/29/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 683085 | 01550 | 7.6 | Solar | 05_01_219W5 | 04/04/2025 | 05/08/2025 | 24 | 22 | 2 | 05/09/2025 | 05/09/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 210574 | 01473 | 10 | Solar | 05_01_27W5 | 03/14/2019 | 03/15/2019 | 0 | 0 | 0 | 03/18/2019 | 03/18/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2019 | 03/14/2019 | 11/19/2019 | Y | EXP | 243 | 05/21/2019 | 05/29/2019 | 8 | 0 | 8 |  |  | 6/19/2019 | Connected |  | N
National Grid | SWANSEA | 175874 | 02777 | 25 | Solar | 05_01_413L3 | 03/09/2015 | 03/09/2015 | 4 | 0 | 4 | 03/16/2015 | 03/16/2015 | 382 | 0 | 382 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 |  | 12/31/2016 | N | EXP | 655 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 177715 | 01581 | 4686 | Solar | 05_01_609W1 | 07/26/2017 | 10/06/2017 | 51 | 51 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2017 | 10/25/2017 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 | 07/26/2017 | 10/31/2022 | Y | STD | 273 | 08/26/2022 | 10/12/2022 | 48 | 0 | 48 | 10/13/2022 | 11/4/2022 | 11/18/2022 | Connected |  | N
National Grid | SALEM | 632418 | 01970 | 10 | Solar | 05_05_11W81 | 08/13/2024 | 08/16/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 | 08/13/2024 | 3/4/2026 | Y | EXP | 365 | 03/27/2025 | 04/17/2025 | 22 | 0 | 22 |  |  | 4/22/2025 | Connected |  | N
National Grid | MEDFORD | 177275 | 02155 | 4500 | Solar | 05_05_312W5 | 02/06/2017 | 02/06/2017 | 14 | 13 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2017 | 03/02/2017 | 2 | 0 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/15/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 675838 | 01832 | 15.2 | Solar | 05_12_29W4 | 03/05/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 66 | 44 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 409266 | 01950 | 17.11 | Solar | 05_12_9C3 | 03/15/2022 | 03/24/2022 | 7 | 2 | 5 | 03/25/2022 | 03/25/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2022 |  | 6/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2022 | Connected |  | N
National Grid | LAWRENCE | 704610 | 01841 | 480 | Solar | 05_14_43L8 | 10/17/2025 | 10/31/2025 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2025 | 11/24/2025 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LEOMINSTER | 178529 | 01453 | 5000 | Solar | 05_14_60L4 | 12/04/2017 | 12/04/2017 | 21 | 21 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2018 | 02/08/2018 | 23 | 11 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/10/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 552870 | 01604 | 10 | Solar | 05_14_74L6 | 11/06/2023 | 11/15/2023 | 6 | 4 | 2 | 11/16/2023 | 11/16/2023 | 48 | 41 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 11/06/2023 | 4/17/2025 | Y | EXP | 365 | 07/31/2024 | 10/23/2024 | 85 | 0 | 85 |  |  | 11/13/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 747732 | 01550 | 20 | Solar | 05_01_219W5 | 01/27/2026 | 01/30/2026 | 2 | 0 | 2 | 02/02/2026 | 02/02/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2026 |  | 2/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2026 | Connected |  | N
National Grid | WESTMINSTER | 243356 | 01473 | 3.8 | Solar | 05_01_27W5 | 07/24/2019 | 07/29/2019 | 2 | 0 | 2 | 07/30/2019 | 07/30/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2019 | 07/24/2019 | 7/23/2020 | Y | EXP | 365 | 04/17/2020 | 06/09/2020 | 53 | 0 | 53 |  |  | 6/25/2020 | Connected |  | N
National Grid | SWANSEA | 175996 | 02777 | 18.75 | Solar | 05_01_413L3 | 06/11/2015 | 06/11/2015 | 6 | 6 | 0 | 06/23/2015 | 06/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/17/2016 | N | EXP | 352 |  |  | 0 | 0 | 0 | 11/6/2015 | 11/6/2015 | 11/6/2015 | Connected |  | N
National Grid | WESTBOROUGH | 178022 | 01581 | 500 | Solar | 05_01_609W1 | 08/29/2017 | 09/13/2017 | 8 | 8 | 0 |  |  | 24 | 12 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 654991 | 01902 | 3.8 | Solar | 05_05_11W81 | 11/19/2024 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | MEDFORD | 177676 | 02155 | 56 | Solar | 05_05_312W5 | 07/21/2017 | 07/21/2017 | 8 | 4 | 4 | 08/03/2017 | 08/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2017 |  | 7/29/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 12/27/2017 | 12/27/2017 | 12/27/2017 | Connected |  | N
National Grid | HAVERHILL | 680507 | 01835 | 10 | Solar | 05_12_29W4 | 04/09/2025 | 04/29/2025 | 13 | 11 | 2 | 05/21/2025 | 05/21/2025 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 175106 | 01951 | 20 | Solar | 05_12_9C4 | 04/18/2013 | 04/18/2013 | 6 | 0 | 6 | 04/30/2013 | 04/30/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2013 |  | 6/21/2013 | N | EXP | 1 |  |  | 0 | 0 | 0 | 10/28/2013 | 10/28/2013 | 11/12/2013 | Connected |  | N
National Grid | LAWRENCE | 174270 | 01841 | 229.68 | Solar | 05_14_43L8 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2012 |  | 5/1/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 6/26/2013 | Connected |  | N
National Grid | LEOMINSTER | 426844 | 01453 | 4998 | Solar | 05_14_60L4 | 05/31/2022 | 07/25/2022 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 05/31/2022 | 10/18/2026 | Y | CMPX | 308 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 562808 | 01604 | 6 | Solar | 05_14_74L6 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2023 | 11/01/2023 | 12/20/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | CHARLTON | 725691 | 01507 | 5.76 | Solar | 05_01_219W6 | 10/10/2025 | 11/07/2025 | 4 | 0 | 4 | 12/08/2025 | 12/08/2025 | 57 | 38 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HUBBARDSTON | 369971 | 01452 | 7.6 | Solar | 05_01_27W5 | 07/15/2021 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 176639 | 02777 | 1000 | Solar | 05_01_413L3 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/14/2016 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2016 | 12/29/2015 | 1/9/2017 | Y | STD | 245 | 09/11/2017 | 11/07/2017 | 35 | 0 | 35 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | WESTBOROUGH | 178110 | 01581 | 8730 | Solar | 05_01_609W1 | 11/06/2017 | 12/11/2017 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 01/09/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 655862 | 01904 | 10 | Solar | 05_05_11W81 | 11/21/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | MEDFORD | 222837 | 02155 | 144 | Solar | 05_05_312W5 | 04/26/2019 | 06/14/2019 | 22 | 15 | 7 | 06/17/2019 | 06/17/2019 | 5 | 0 | 5 | 07/19/2019 | 09/19/2019 | 44 | 26 | 18 |  |  | 0 | 0 | 0 | 09/19/2019 | 44 | 26 | 18 |  |  | 0 | 0 | 0 | 2/26/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 695694 | 01835 | 12.48 | Solar | 05_12_29W4 | 06/03/2025 | 07/14/2025 | 3 | 1 | 2 | 07/21/2025 | 07/21/2025 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 177371 | 01951 | 60 | Solar | 05_12_9C4 | 09/06/2016 | 09/06/2016 | 5 | 5 | 0 | 09/14/2016 | 09/14/2016 | 46 | 45 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/13/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176413 | 01841 | 92.4 | Solar | 05_14_43L8 | 11/12/2015 | 11/12/2015 | 5 | 0 | 5 | 11/20/2015 | 11/20/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2015 |  | 11/18/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 3/3/2016 | 3/3/2016 | 3/3/2016 | Connected |  | N
National Grid | LEOMINSTER | 636277 | 01453 | 18.525 | Solar | 05_14_60L4 | 08/29/2024 | 09/04/2024 | 3 | 1 | 2 | 09/05/2024 | 09/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 9/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2024 | Connected |  | N
National Grid | WORCESTER | 578472 | 01604 | 2.03 | Solar | 05_14_74L6 | 01/02/2024 | 01/05/2024 | 3 | 0 | 3 | 01/08/2024 | 01/08/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2024 |  | 2/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 744345 | 01550 | 23 | Solar | 05_01_219W6 | 01/09/2026 | 01/13/2026 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 53 | 24 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HUBBARDSTON | 398037 | 01452 | 3.8 | Solar | 05_01_27W5 | 12/17/2021 | 01/07/2022 | 2 | 0 | 2 | 12/22/2021 | 12/22/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  | 5/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2022 | Connected |  | N
National Grid | SWANSEA | 176638 | 02777 | 1000 | Solar | 05_01_413L3 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/14/2016 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2016 | 12/29/2015 | 1/9/2017 | Y | STD | 245 | 09/11/2017 | 11/07/2017 | 35 | 0 | 35 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | WESTBOROUGH | 178109 | 01581 | 3396 | Solar | 05_01_609W1 | 11/06/2017 | 12/11/2017 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 01/09/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 666526 | 01904 | 7.6 | Solar | 05_05_11W81 | 02/05/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 02/05/2025 | 4/23/2026 | Y | EXP | 365 | 05/29/2025 | 08/01/2025 | 65 | 0 | 65 |  |  | 8/11/2025 | Connected |  | N
National Grid | MEDFORD | 287647 | 02155 | 616 | Solar | 05_05_312W5 | 04/24/2020 | 05/06/2020 | 8 | 3 | 5 |  |  | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2021 |  | 8/24/2022 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 701469 | 01835 | 7.68 | Solar | 05_12_29W4 | 06/26/2025 | 07/11/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 58 | 25 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 248807 | 01950 | 216 | Solar | 05_12_9C4 | 08/14/2019 | 08/30/2019 | 11 | 4 | 7 | 09/03/2019 | 09/03/2019 | 18 | 9 | 9 | 10/09/2019 | 11/25/2019 | 32 | 8 | 24 |  |  | 0 | 0 | 0 | 11/25/2019 | 32 | 8 | 24 |  |  | 0 | 0 | 0 | 12/6/2019 | 08/14/2019 | 4/1/2022 | Y | EXP | 403 | 05/07/2021 | 05/14/2021 | 7 | 0 | 7 |  |  | 2/9/2022 | Connected |  | N
National Grid | LAWRENCE | 176854 | 01841 | 92.4 | Solar | 05_14_43L8 | 11/12/2015 | 11/12/2015 | 5 | 5 | 0 | 11/20/2015 | 11/20/2015 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2015 | 11/12/2015 | 11/18/2016 | Y | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 201742 | 01453 | 372 | Solar | 05_14_61L1 | 11/21/2018 | 11/29/2018 | 4 | 4 | 0 | 11/30/2018 | 11/30/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 |  | 7/30/2021 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 580061 | 01604 | 10 | Solar | 05_14_74L6 | 02/28/2024 | 03/04/2024 | 3 | 0 | 3 | 03/05/2024 | 03/05/2024 | 12 | 5 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 3/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 176432 | 01550 | 1965 | Natural Gas | 05_01_219W6 | 03/14/2016 | 03/14/2016 | 13 | 13 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/01/2016 | 06/23/2016 | 56 | 38 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2017 | 03/14/2016 | 6/30/2019 | Y | STD | 832 | 10/11/2017 | 04/04/2018 | 103 | 0 | 103 | 1/5/2018 | 1/5/2018 | 8/8/2018 | Connected |  | N
National Grid | HUBBARDSTON | 462891 | 01452 | 480 | Solar | 05_01_27W5 | 01/20/2023 | 04/10/2023 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2023 | 05/09/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 176637 | 02777 | 1000 | Solar | 05_01_413L3 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/14/2016 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2016 | 12/29/2015 | 1/9/2017 | Y | STD | 245 | 09/11/2017 | 11/07/2017 | 35 | 0 | 35 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | WESTBOROUGH | 178332 | 01581 | 1875 | Solar | 05_01_609W1 | 11/16/2017 | 02/23/2018 | 65 | 53 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 03/27/2018 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 671235 | 01902 | 3.8 | Solar | 05_05_11W81 | 02/10/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | MEDFORD | 287637 | 02155 | 200 | Solar | 05_05_312W5 | 04/13/2020 | 04/17/2020 | 3 | 0 | 3 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2021 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 701437 | 01835 | 8.64 | Solar | 05_12_29W4 | 06/26/2025 | 07/11/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/26/2025 | 11/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2025 | Connected |  | N
National Grid | LAWRENCE | 562890 | 01843 | 6.96 | Solar | 05_12_9C6 | 12/01/2023 | 12/06/2023 | 4 | 2 | 2 | 12/07/2023 | 12/07/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 12/01/2023 | 1/18/2025 | Y | EXP | 365 | 04/25/2024 | 10/07/2024 | 166 | 0 | 166 |  |  | 8/4/2024 | Connected |  | N
National Grid | LAWRENCE | 184923 | 01841 | 250 | Solar | 05_14_43L8 | 05/10/2018 | 05/10/2018 | 6 | 0 | 6 | 05/18/2018 | 05/18/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2018 |  | 5/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2019 | Connected |  | N
National Grid | LEOMINSTER | 285209 | 01453 | 4.08 | Solar | 05_14_61L1 | 05/18/2020 | 05/20/2020 | 1 | 0 | 1 | 05/21/2020 | 05/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/18/2020 | 4/3/2021 | Y | EXP | 365 | 11/17/2020 | 02/08/2021 | 83 | 0 | 83 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 603429 | 01527 | 10 | Solar | 05_14_74L6 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 | 04/17/2024 | 6/24/2025 | Y | EXP | 365 | 10/23/2024 | 12/02/2024 | 41 | 0 | 41 |  |  | 12/6/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 196233 | 01550 | 7.6 | Solar | 05_01_219W6 | 09/18/2018 | 08/09/2019 | 147 | 145 | 2 | 08/12/2019 | 08/12/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 6/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | Connected |  | N
National Grid | WESTMINSTER | 469690 | 01473 | 9.84 | Solar | 05_01_27W5 | 11/11/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 | 11/11/2022 | 9/13/2024 | Y | EXP | 365 | 07/20/2023 | 09/14/2023 | 57 | 0 | 57 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 176768 | 02777 | 1872 | Solar | 05_01_413L3 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 05/31/2016 | 23 | 15 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/7/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 217237 | 01581 | 10 | Solar | 05_01_609W1 | 04/03/2019 | 04/04/2019 | 0 | 0 | 0 | 04/05/2019 | 04/05/2019 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2019 |  | 6/28/2019 | N | EXP | 74 |  |  | 0 | 0 | 0 |  |  | 6/5/2019 | Connected |  | N
National Grid | LYNN | 700720 | 01902 | 15.2 | Solar | 05_05_11W81 | 07/07/2025 | 07/08/2025 | 1 | 0 | 1 | 07/09/2025 | 07/09/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 293197 | 02155 | 7.6 | Solar | 05_05_312W5 | 05/22/2020 |  | 38 | 38 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 710848 | 01835 | 7.6 | Solar | 05_12_29W5 | 08/08/2025 | 09/19/2025 | 3 | 0 | 3 | 09/22/2025 | 09/22/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 603258 | 01843 | 200 | Solar | 05_12_9J1 | 05/13/2024 | 08/09/2024 | 61 | 53 | 8 |  |  | 57 | 51 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2025 | 05/13/2024 | 4/5/2026 | Y | STD | 147 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y
National Grid | LAWRENCE | 185057 | 01841 | 250 | Solar | 05_14_43L8 | 05/10/2018 | 05/10/2018 | 2 | 0 | 2 | 05/17/2018 | 05/17/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 336498 | 01453 | 10 | Solar | 05_14_61L1 | 06/10/2021 | 08/30/2021 | 56 | 55 | 1 | 08/31/2021 | 08/31/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 8/29/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 609579 | 01604 | 13.6 | Solar | 05_14_74L6 | 05/09/2024 | 05/16/2024 | 3 | 0 | 3 | 05/17/2024 | 05/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/09/2024 | 8/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 193270 | 01550 | 3.8 | Solar | 05_01_219W6 | 08/11/2018 | 09/24/2018 | 3 | 3 | 0 | 09/25/2018 | 09/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 526849 | 01473 | 9.57 | Solar | 05_01_27W5 | 05/23/2023 | 05/25/2023 | 2 | 0 | 2 | 05/26/2023 | 05/26/2023 | 18 | 0 | 18 | 06/28/2023 | 08/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 08/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 7/28/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 177748 | 02777 | 1500 | Solar | 05_01_413L3 | 05/26/2017 | 06/09/2017 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2017 | 07/07/2017 | 19 | 2 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2018 | 05/26/2017 | 10/31/2020 | Y | STD | 1174 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 257644 | 01581 | 0 | Battery Add-On | 05_01_609W1 | 10/07/2019 | 11/06/2019 | 0 | 0 | 0 | 11/07/2019 | 11/07/2019 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 | 10/07/2019 | 6/24/2020 | Y | EXP | 365 | 01/03/2020 | 01/09/2020 | 6 | 0 | 6 |  |  | 3/4/2020 | Connected |  | N
National Grid | LYNN | 707625 | 01902 | 11.4 | Solar | 05_05_11W81 | 07/27/2025 | 08/21/2025 | 18 | 15 | 3 | 08/22/2025 | 08/22/2025 | 32 | 18 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 | 07/27/2025 | 10/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | SWAMPSCOTT | 300962 | 01907 | 3.8 | Solar | 05_05_312W5 | 07/13/2020 | 12/14/2021 | 299 | 114 | 185 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 |  | 6/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 742210 | 01835 | 5.76 | Solar | 05_12_29W5 | 12/24/2025 | 12/30/2025 | 3 | 0 | 3 | 01/23/2026 | 01/23/2026 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2026 |  | 3/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 619859 | 01843 | 5 | Solar | 05_12_9J1 | 06/25/2024 | 06/27/2024 | 4 | 0 | 4 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 | 06/25/2024 | 1/30/2027 | Y | EXP | 730 | 10/01/2025 | 10/18/2025 | 18 | 0 | 18 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 194241 | 01841 | 120 | Solar | 05_14_43L8 | 08/23/2018 | 08/29/2018 | 3 | 0 | 3 | 08/30/2018 | 08/30/2018 | 148 | 0 | 148 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 450745 | 01453 | 6 | Solar | 05_14_61L1 | 08/15/2022 | 08/31/2022 | 12 | 10 | 2 | 09/01/2022 | 09/01/2022 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2022 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 614816 | 01604 | 10 | Solar | 05_14_74L6 | 06/04/2024 | 06/07/2024 | 1 | 0 | 1 | 06/10/2024 | 06/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 199248 | 01550 | 7.6 | Solar | 05_01_219W6 | 11/08/2018 | 12/03/2018 | 13 | 10 | 3 | 12/04/2018 | 12/04/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 562649 | 01473 | 7.6 | Solar | 05_01_27W5 | 10/24/2023 | 10/25/2023 | 1 | 0 | 1 | 10/26/2023 | 10/26/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 | 10/24/2023 | 11/29/2024 | Y | EXP | 365 | 02/23/2024 | 03/26/2024 | 33 | 0 | 33 |  |  | 4/12/2024 | Connected |  | N
National Grid | SWANSEA | 178534 | 02777 | 3744 | Solar | 05_01_413L3 | 12/05/2017 | 12/05/2017 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 | 12/05/2017 | 12/31/2020 | Y | STD | 784 | 06/12/2020 | 11/23/2020 | 165 | 5 | 160 | 12/14/2020 | 12/22/2020 | 12/31/2020 | Connected |  | N
National Grid | WESTBOROUGH | 257344 | 01581 | 9.765 | Solar | 05_01_609W1 | 12/09/2019 | 12/11/2019 | 2 | 2 | 0 | 12/12/2019 | 12/12/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 | 12/09/2019 | 12/9/2020 | Y | EXP | 365 | 05/29/2020 | 06/15/2020 | 17 | 0 | 17 |  |  | 9/22/2020 | Connected |  | N
National Grid | LYNN | 175614 | 01902 | 0 | Solar | 05_05_11W82 | 12/16/2014 | 12/16/2014 | 4 | 2 | 2 | 12/23/2014 | 12/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2015 | 12/16/2014 | 4/30/2015 | Y | EXP | 97 |  |  | 0 | 0 | 0 | 4/6/2016 | 4/6/2016 | 4/6/2016 | Terminated |  | N
National Grid | SWAMPSCOTT | 697790 | 01907 | 3.84 | Solar | 05_05_312W5 | 06/19/2025 | 07/07/2025 | 4 | 0 | 4 | 07/30/2025 | 07/30/2025 | 43 | 28 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | HAVERHILL | 750194 | 01835 | 5.76 | Solar | 05_12_29W5 | 02/09/2026 | 02/10/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 30 | 14 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 566018 | 01843 | 200 | Solar | 05_12_9J1 | 11/15/2023 | 12/08/2023 | 16 | 6 | 10 | 12/11/2023 | 12/11/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 194218 | 01841 | 300 | Solar | 05_14_43L8 | 08/23/2018 | 08/28/2018 | 2 | 0 | 2 | 08/29/2018 | 08/29/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 407121 | 01453 | 7.54 | Solar | 05_14_61L1 | 03/24/2022 | 04/05/2022 | 9 | 7 | 2 | 04/06/2022 | 04/06/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 03/24/2022 | 8/20/2023 | Y | EXP | 365 | 06/08/2022 | 07/14/2022 | 37 | 0 | 37 |  |  | 9/1/2022 | Connected |  | N
National Grid | WORCESTER | 625512 | 01604 | 5.76 | Solar | 05_14_74L6 | 07/17/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 230771 | 01550 | 7.6 | Solar | 05_01_219W6 | 06/18/2019 | 06/24/2019 | 3 | 0 | 3 | 06/25/2019 | 06/25/2019 | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 581603 | 01452 | 10 | Solar | 05_01_27W5 | 01/19/2024 | 01/23/2024 | 2 | 0 | 2 | 01/24/2024 | 01/24/2024 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 4/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2024 | Connected |  | N
National Grid | SOMERSET | 194187 | 02726 | 333 | Solar | 05_01_413L3 | 08/23/2018 | 08/23/2018 | 0 | 0 | 0 | 08/24/2018 | 08/24/2018 | 20 | 19 | 1 | 11/15/2018 | 03/11/2019 | 76 | 0 | 76 |  |  | 0 | 0 | 0 | 03/11/2019 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 283891 | 01581 | 0 | Battery Add-On | 05_01_609W1 | 03/30/2020 | 04/06/2020 | 5 | 5 | 0 | 04/07/2020 | 04/07/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2020 |  | 4/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2020 | Connected |  | N
National Grid | LYNN | 562551 | 01904 | 3125 | Solar | 05_05_11W82 | 02/20/2024 | 07/22/2024 | 105 | 96 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2024 | 09/04/2024 | 31 | 18 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 | 02/20/2024 | 4/14/2027 | Y | STD | 420 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SWAMPSCOTT | 737224 | 01907 | 3.8 | Solar | 05_05_313W1 | 12/01/2025 | 01/12/2026 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 38 | 22 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HAVERHILL | 177658 | 01835 | 66.6 | Solar | 05_12_29W5 | 11/13/2017 | 11/13/2017 | 49 | 49 | 0 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2018 |  | 4/19/2019 | N | EXP | 445 |  |  | 0 | 0 | 0 |  |  | 2/4/2019 | Connected |  | N
National Grid | LAWRENCE | 194214 | 01843 | 100 | Solar | 05_14_43L8 | 10/15/2018 | 10/15/2018 | 0 | 0 | 0 | 10/16/2018 | 10/16/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 407034 | 01841 | 9.57 | Solar | 05_14_61L1 | 03/24/2022 | 03/28/2022 | 2 | 1 | 1 | 03/29/2022 | 03/29/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2022 |  | 7/13/2023 | N | EXP | 365 | 06/08/2022 | 07/12/2022 | 35 | 0 | 35 |  |  | 7/23/2022 | Connected |  | N
National Grid | LEOMINSTER | 629733 | 01453 | 10 | Solar | 05_14_74L6 | 08/02/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 08/02/2024 | 11/25/2025 | Y | EXP | 365 | 11/22/2024 | 12/05/2024 | 14 | 0 | 14 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 606789 | 01604 | 10 | Solar | 05_01_219W6 | 04/26/2024 | 05/16/2024 | 10 | 9 | 1 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 | 04/26/2024 | 7/23/2025 | Y | EXP | 365 | 09/18/2024 | 09/17/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 628532 | 01550 | 5.76 | Solar | 05_01_27W5 | 07/29/2024 | 08/02/2024 | 1 | 0 | 1 | 08/05/2024 | 08/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/29/2024 | 8/23/2025 | Y | EXP | 365 | 03/06/2025 | 06/06/2025 | 93 | 0 | 93 |  |  | 8/19/2025 | Connected |  | N
National Grid | HUBBARDSTON | 241223 | 01452 | 400 | Solar | 05_01_413L3 | 04/14/2020 | 05/11/2020 | 17 | 11 | 6 |  |  | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 289990 | 02777 | 4950 | Other | 05_01_609W1 | 05/16/2020 | 05/22/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2020 | 06/18/2020 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 639826 | 01532 | 240 | Solar | 05_05_11W82 | 04/02/2025 | 04/29/2025 | 18 | 9 | 9 | 04/30/2025 | 04/30/2025 | 57 | 33 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 7/27/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 176924 | 01904 | 28 | Solar | 05_05_313W1 | 11/19/2015 | 11/19/2015 | 3 | 3 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2015 |  | 11/24/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 5/26/2016 | 5/26/2016 | 7/6/2016 | Connected |  | N
National Grid | SWAMPSCOTT | 178626 | 01907 |  | Solar | 05_12_29W5 | 03/15/2018 | 03/15/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/21/2019 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 625493 | 01835 | 200 | Solar | 05_12_9J1 | 08/06/2024 | 10/14/2024 | 48 | 38 | 10 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 194210 | 01843 | 120 | Solar | 05_14_43L8 | 08/22/2018 | 10/15/2018 | 36 | 0 | 36 | 10/16/2018 | 10/16/2018 | 68 | 26 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 530025 | 01841 | 5.85 | Solar | 05_14_61L1 | 06/08/2023 | 06/28/2023 | 14 | 12 | 2 | 06/29/2023 | 06/29/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 |  | 8/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2023 | Connected |  | N
National Grid | LEOMINSTER | 630908 | 01453 | 3.8 | Solar | 05_14_74L6 | 08/07/2024 | 11/04/2024 | 1 | 0 | 1 | 11/05/2024 | 11/05/2024 | 32 | 11 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 608585 | 01604 | 23 | Solar | 05_01_219W6 | 05/06/2024 | 05/14/2024 | 7 | 4 | 3 | 05/15/2024 | 05/15/2024 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 05/06/2024 | 6/20/2025 | Y | EXP | 365 | 07/17/2024 | 07/16/2024 | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 635563 | 01550 | 10 | Solar | 05_01_27W5 | 08/26/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 08/26/2024 | 3/4/2026 | Y | EXP | 365 | 06/12/2025 | 10/01/2025 | 112 | 0 | 112 |  |  | 10/28/2025 | Connected |  | N
National Grid | HUBBARDSTON | 273618 | 01452 | 5000 | Other | 05_01_413L3 | 03/03/2020 | 03/17/2020 | 10 | 7 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2020 | 04/02/2020 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 291210 | 02726 | 0 | Other | 05_01_609W1 | 08/31/2020 | 09/23/2020 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/24/2020 | 10/16/2020 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 725092 | 01532 | 7.6 | Solar | 05_05_11W82 | 10/08/2025 | 10/30/2025 | 3 | 0 | 3 | 12/10/2025 | 12/10/2025 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 177320 | 01902 | 26.6 | Solar | 05_05_313W1 | 02/15/2017 | 02/15/2017 | 5 | 3 | 2 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2017 |  | 2/20/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 9/28/2017 | 9/28/2017 | 10/23/2017 | Connected |  | N
National Grid | SWAMPSCOTT | 183811 | 01907 | 5 | Solar | 05_12_29W5 | 04/30/2018 | 04/30/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 289689 | 01835 | 12.96 | Solar | 05_12_9J2 | 04/28/2020 | 05/05/2020 | 4 | 1 | 3 | 05/06/2020 | 05/06/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2020 | Connected |  | N
National Grid | LAWRENCE | 194207 | 01843 | 180 | Solar | 05_14_43L8 | 08/22/2018 | 08/29/2018 | 4 | 0 | 4 | 08/30/2018 | 08/30/2018 | 149 | 0 | 149 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 535614 | 01844 | 3 | Solar | 05_14_61L1 | 07/04/2023 | 07/10/2023 | 4 | 3 | 1 | 07/11/2023 | 07/11/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 637230 | 01453 | 10 | Solar | 05_14_74L6 | 09/03/2024 | 10/04/2024 | 1 | 0 | 1 | 10/07/2024 | 10/07/2024 | 78 | 42 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | WORCESTER | 636595 | 01604 | 7.6 | Solar | 05_01_219W6 | 08/29/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2024 |  | 11/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 639402 | 01550 | 7.6 | Solar | 05_01_27W5 | 09/11/2024 | 09/24/2024 | 3 | 0 | 3 | 09/25/2024 | 09/25/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | HUBBARDSTON | 282071 | 01452 | 4950 | Other | 05_01_413L3 | 05/06/2020 | 05/12/2020 | 4 | 1 | 3 |  |  | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 05/13/2020 | 06/10/2020 | 19 | 1 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 299242 | 02726 | 0 | Solar | 05_01_609W1 | 09/02/2020 | 09/21/2020 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/13/2020 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 753311 | 01532 | 3.8 | Solar | 05_05_11W82 | 02/26/2026 | 03/04/2026 | 3 | 0 | 3 | 03/18/2026 | 03/18/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 178346 | 01902 | 56 | Solar | 05_05_313W1 | 01/11/2018 | 01/11/2018 | 29 | 19 | 10 | 02/02/2018 | 02/02/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 |  | 1/17/2019 | N | EXP | 325 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | SWAMPSCOTT | 191753 | 01907 | 7.6 | Solar | 05_12_29W5 | 07/24/2018 | 10/03/2018 | 41 | 38 | 3 | 10/04/2018 | 10/04/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 309022 | 01835 | 7.6 | Solar | 05_12_9J2 | 08/26/2020 | 08/27/2020 | 0 | 0 | 0 | 08/28/2020 | 08/28/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 8/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N
National Grid | LAWRENCE | 194203 | 01843 | 240 | Solar | 05_14_43L8 | 08/22/2018 | 08/28/2018 | 3 | 0 | 3 | 08/29/2018 | 08/29/2018 | 101 | 0 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 541415 | 01844 | 11.31 | Solar | 05_14_61L1 | 08/14/2023 | 08/28/2023 | 11 | 10 | 1 | 08/29/2023 | 08/29/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 | 08/14/2023 | 10/18/2024 | Y | EXP | 365 | 01/24/2024 | 02/02/2024 | 10 | 0 | 10 |  |  | 2/6/2024 | Connected |  | N
National Grid | LEOMINSTER | 640464 | 01453 | 10 | Solar | 05_14_74L6 | 09/17/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/17/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | WORCESTER | 656186 | 01604 | 7.6 | Solar | 05_01_219W6 | 11/21/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 644294 | 01550 | 3.8 | Solar | 05_01_27W5 | 10/02/2024 | 11/07/2024 | 13 | 11 | 2 | 11/08/2024 | 11/08/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2025 | Connected |  | N
National Grid | WESTMINSTER | 300622 | 01473 | 0 | Other | 05_01_413L3 | 09/22/2020 | 10/01/2020 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2020 | 10/29/2020 | 18 | 1 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 299584 | 02726 | 7.68 | Solar | 05_01_609W1 | 07/02/2020 | 07/08/2020 | 3 | 0 | 3 | 07/09/2020 | 07/09/2020 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2020 |  | 7/6/2022 | N | EXP | 629 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 172587 | 01532 | 3.8 | Solar | 05_05_11W82 | 05/22/2018 | 05/22/2018 | 11 | 2 | 9 | 06/29/2018 | 06/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 | 05/22/2018 | 7/12/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2019 | Connected |  | N
National Grid | LYNN | 178345 | 01902 | 72 | Solar | 05_05_313W1 | 01/11/2018 | 01/11/2018 | 25 | 15 | 10 | 02/20/2018 | 02/20/2018 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2018 |  | 1/17/2019 | N | EXP | 331 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | Connected |  | N
National Grid | SWAMPSCOTT | 216929 | 01907 | 7.6 | Solar | 05_12_29W5 | 05/07/2019 | 05/08/2019 | 0 | 0 | 0 | 05/09/2019 | 05/09/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 | 05/07/2019 | 5/12/2021 | Y | EXP | 365 | 05/27/2020 | 10/24/2020 | 151 | 5 | 146 |  |  | 2/5/2021 | Connected |  | N
National Grid | HAVERHILL | 380086 | 01835 | 15.2 | Solar | 05_12_9J2 | 09/05/2021 | 09/27/2021 | 15 | 14 | 1 | 09/28/2021 | 09/28/2021 | 48 | 29 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 |  | 1/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2022 | Connected |  | N
National Grid | LAWRENCE | 194190 | 01843 | 240 | Solar | 05_14_43L8 | 08/23/2018 | 08/28/2018 | 2 | 0 | 2 | 08/29/2018 | 08/29/2018 | 101 | 0 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 549692 | 01844 | 480 | Solar | 05_14_61L1 | 09/01/2023 | 10/12/2023 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 | 11/08/2023 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 645132 | 01453 | 1.74 | Solar | 05_14_74L6 | 10/04/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | WORCESTER | 677866 | 01604 | 13.8 | Solar | 05_01_219W6 | 03/13/2025 | 03/19/2025 | 4 | 0 | 4 | 03/20/2025 | 03/20/2025 | 123 | 103 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 644817 | 01550 | 5.76 | Solar | 05_01_27W5 | 10/03/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | WESTMINSTER | 307951 | 01473 | 9.6 | Solar | 05_01_413L3 | 08/20/2020 | 08/21/2020 | 0 | 0 | 0 | 08/24/2020 | 08/24/2020 | 47 | 26 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2020 | 08/20/2020 | 11/2/2021 | Y | EXP | 365 | 03/11/2021 | 03/15/2021 | 4 | 0 | 4 |  |  | 4/12/2021 | Connected |  | N
National Grid | SOMERSET | 311144 | 02726 | 9.6 | Solar | 05_01_609W1 | 09/07/2020 | 09/08/2020 | 0 | 0 | 0 | 09/09/2020 | 09/09/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 09/07/2020 | 9/7/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 176184 | 01532 | 1143 | Solar | 05_05_11W82 | 08/28/2015 | 08/28/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2015 | 12/17/2015 | 71 | 37 | 34 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2016 | 08/28/2015 | 9/6/2016 | Y | STD | 138 | 08/11/2016 | 11/07/2016 | 60 | 0 | 60 | 6/27/2017 | 6/27/2017 | 5/17/2017 | Connected |  | N
National Grid | LYNN | 207452 | 01902 | 10 | Solar | 05_05_313W1 | 01/29/2019 | 02/12/2019 | 9 | 0 | 9 | 02/13/2019 | 02/13/2019 | 16 | 13 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 3/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2019 | Connected |  | N
National Grid | SWAMPSCOTT | 265737 | 01907 | 7.6 | Solar | 05_12_29W5 | 12/04/2019 | 12/10/2019 | 3 | 0 | 3 | 12/11/2019 | 12/11/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2020 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 405582 | 01835 | 0 | Solar | 05_12_9J2 | 01/09/2022 | 01/10/2022 | 1 | 0 | 1 | 01/11/2022 | 01/11/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  | 5/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 193992 | 01840 | 650 | Solar | 05_14_43L8 | 09/11/2018 | 10/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 01/31/2019 | 81 | 0 | 81 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 587226 | 01844 | 6 | Solar | 05_14_61L1 | 02/21/2024 | 02/26/2024 | 3 | 0 | 3 | 02/27/2024 | 02/27/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 645336 | 01453 | 7.6 | Solar | 05_14_74L6 | 10/07/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2025 | Connected |  | N
National Grid | WORCESTER | 707464 | 01604 | 12.672 | Solar | 05_01_21W1 | 07/30/2025 | 09/09/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 | 07/30/2025 | 10/14/2026 | Y | EXP | 365 | 02/03/2026 |  | 58 | 0 | 58 |  |  |  | Construction |  | N
National Grid | DUDLEY | 647364 | 01571 | 7.6 | Solar | 05_01_27W5 | 10/30/2024 | 11/21/2024 | 2 | 0 | 2 | 11/22/2024 | 11/22/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 318399 | 01473 | 19.2 | Solar | 05_01_413L3 | 10/09/2020 |  | 40 | 39 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 343989 | 02726 | 7.6 | Solar | 05_01_609W1 | 02/25/2021 | 03/01/2021 | 1 | 0 | 1 | 03/02/2021 | 03/02/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 176875 | 01532 | 7.6 | Solar | 05_05_11W82 | 03/02/2016 | 03/02/2016 | 30 | 30 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 03/02/2016 | 3/7/2017 | Y | EXP | 315 | 09/06/2016 | 09/21/2016 | 11 | 0 | 11 | 11/4/2016 | 11/4/2016 | 11/9/2016 | Connected |  | N
National Grid | LYNN | 224878 | 01902 | 10 | Solar | 05_05_313W1 | 05/28/2019 | 05/30/2019 | 1 | 0 | 1 | 05/31/2019 | 05/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2019 |  | 6/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2019 | Connected |  | N
National Grid | SWAMPSCOTT | 289054 | 01907 | 3 | Solar | 05_12_29W5 | 05/06/2020 | 05/11/2020 | 2 | 0 | 2 | 05/12/2020 | 05/12/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 | 05/06/2020 | 10/21/2021 | Y | EXP | 365 | 03/20/2021 | 05/04/2021 | 45 | 0 | 45 |  |  | 5/13/2021 | Connected |  | N
National Grid | HAVERHILL | 714650 | 01835 | 30 | Solar | 05_12_9J2 | 09/19/2025 | 09/24/2025 | 3 | 0 | 3 | 09/25/2025 | 09/25/2025 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2026 | Connected |  | Y
National Grid | LAWRENCE | 195374 | 01843 | 240 | Solar | 05_14_43L8 | 09/12/2018 | 09/21/2018 | 4 | 0 | 4 | 09/24/2018 | 09/24/2018 | 27 | 11 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 597488 | 01841 | 10.075 | Solar | 05_14_61L1 | 03/19/2024 | 03/28/2024 | 7 | 5 | 2 | 03/29/2024 | 03/29/2024 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 03/19/2024 | 7/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | SPENCER | 651851 | 01562 | 10 | Solar | 05_14_74L6 | 11/13/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/13/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | WORCESTER | 749988 | 01604 | 5.76 | Solar | 05_01_21W1 | 02/09/2026 | 02/10/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DUDLEY | 647973 | 01571 | 7.6 | Solar | 05_01_27W5 | 10/28/2024 | 12/12/2024 | 23 | 20 | 3 | 12/13/2024 | 12/13/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2025 | Connected |  | N
National Grid | WESTMINSTER | 324361 | 01473 | 0 | Solar | 05_01_413L3 | 11/06/2020 | 12/18/2020 | 28 | 27 | 1 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 | 11/06/2020 | 12/17/2021 | Y | EXP | 365 | 05/20/2021 | 06/25/2021 | 36 | 0 | 36 |  |  | 6/29/2021 | Connected |  | N
National Grid | SOMERSET | 402697 | 02726 | 0 | Solar | 05_01_609W1 | 12/21/2021 | 01/10/2022 | 13 | 12 | 1 | 01/11/2022 | 01/11/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  | 3/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 178007 | 01532 | 15 | Solar | 05_05_11W82 | 04/28/2017 | 04/28/2017 | 10 | 10 | 0 | 05/12/2017 | 05/12/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2017 |  | 5/3/2018 | N | EXP | 353 |  |  | 0 | 0 | 0 | 8/2/2017 | 8/2/2017 | 8/7/2017 | Connected |  | N
National Grid | LYNN | 253609 | 01902 | 15.2 | Solar | 05_05_313W1 | 09/11/2019 | 09/16/2019 | 3 | 3 | 0 | 09/17/2019 | 09/17/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 9/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2020 | Connected |  | N
National Grid | SWAMPSCOTT | 450088 | 01907 | 6 | Solar | 05_12_29W5 | 09/20/2022 | 09/21/2022 | 1 | 0 | 1 | 09/22/2022 | 09/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 349109 | 01835 | 150 | Solar | 05_14_12J1 | 03/26/2021 | 04/13/2021 | 11 | 2 | 9 | 06/16/2021 | 06/16/2021 | 109 | 84 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 03/26/2021 | 7/12/2022 | Y | EXP | 147 | 03/13/2022 | 04/07/2022 | 26 | 0 | 26 |  |  | 5/26/2022 | Connected |  | N
National Grid | LAWRENCE | 250814 | 01843 | 230.4 | Solar | 05_14_43L8 | 09/05/2019 | 10/07/2019 | 21 | 17 | 4 | 10/08/2019 | 10/08/2019 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 4/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 608292 | 01844 | 7.6 | Solar | 05_14_61L1 | 05/02/2024 | 05/21/2024 | 3 | 0 | 3 | 05/22/2024 | 05/22/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 | 05/02/2024 | 7/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | LEICESTER | 653191 | 01524 | 10 | Solar | 05_14_74L6 | 11/12/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/12/2024 | 2/26/2026 | Y | EXP | 365 | 05/24/2025 | 11/21/2025 | 182 | 0 | 182 |  |  | 11/24/2025 | Connected |  | N
National Grid | WORCESTER | 174335 | 01604 | 2000 | Solar | 05_01_21W1 | 01/25/2012 | 01/25/2012 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2012 | 05/16/2012 | 37 | 0 | 37 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 660823 | 01550 | 5.76 | Solar | 05_01_27W5 | 12/16/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/16/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | Y
National Grid | HUBBARDSTON | 335832 | 01452 | 0 | Other | 05_01_413L3 | 04/07/2021 | 04/30/2021 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 426230 | 02777 | 7.6 | Solar | 05_01_609W1 | 06/01/2022 | 06/06/2022 | 4 | 2 | 2 | 06/07/2022 | 06/07/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2022 |  | 7/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 178006 | 01532 | 20 | Solar | 05_05_11W82 | 04/28/2017 | 04/28/2017 | 10 | 10 | 0 | 05/12/2017 | 05/12/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2017 |  | 5/3/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 | 8/2/2017 | 8/2/2017 | 8/8/2017 | Connected |  | N
National Grid | LYNN | 259202 | 01902 | 3.8 | Solar | 05_05_313W1 | 10/18/2019 | 10/22/2019 | 1 | 0 | 1 | 10/23/2019 | 10/23/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2019 | 10/18/2019 | 10/18/2020 | Y | EXP | 365 | 02/12/2020 | 04/02/2020 | 50 | 0 | 50 |  |  | 6/3/2020 | Connected |  | N
National Grid | WESTFORD | 370923 | 01886 | 3.8 | Solar | 05_12_29W5 | 07/22/2021 | 07/27/2021 | 3 | 0 | 3 | 07/28/2021 | 07/28/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 699707 | 01835 | 40.85 | Solar | 05_14_13J2 | 06/19/2025 | 07/08/2025 | 12 | 10 | 2 | 07/09/2025 | 07/09/2025 | 54 | 38 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 196059 | 01843 | 2000 | Solar | 05_14_47L1 | 09/21/2018 | 11/07/2018 | 20 | 13 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2018 | 01/07/2019 | 37 | 19 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 | 09/21/2018 | 5/10/2026 | Y | STD | 553 | 12/10/2024 |  | 478 | 304 | 174 |  |  |  | Construction |  | N
National Grid | METHUEN | 618440 | 01844 | 10 | Solar | 05_14_61L1 | 06/17/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 | 06/17/2024 | 7/23/2025 | Y | EXP | 365 | 08/09/2024 | 10/21/2024 | 74 | 0 | 74 |  |  | 10/25/2024 | Connected |  | N
National Grid | SPENCER | 657035 | 01562 | 7.6 | Solar | 05_14_74L6 | 11/28/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 86 | 25 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174573 | 01604 | 1000 | Solar | 05_01_21W1 | 10/11/2011 | 10/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 667511 | 01550 | 11.4 | Solar | 05_01_27W5 | 02/04/2025 | 03/11/2025 | 16 | 12 | 4 | 03/12/2025 | 03/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | WESTMINSTER | 399464 | 01473 | 2625 | Solar | 05_01_413L3 | 03/15/2022 |  | 161 | 153 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 472538 | 02777 | 7.6 | Solar | 05_01_609W1 | 11/18/2022 | 11/23/2022 | 3 | 0 | 3 | 11/25/2022 | 11/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 | 11/18/2022 | 3/2/2024 | Y | EXP | 365 | 02/23/2023 | 03/02/2023 | 8 | 0 | 8 |  |  | 6/24/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 263922 | 01532 | 8.7 | Solar | 05_05_11W82 | 11/15/2019 | 11/18/2019 | 0 | 0 | 0 | 11/19/2019 | 11/19/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2019 | 11/15/2019 | 7/22/2020 | Y | EXP | 365 | 01/10/2020 | 02/26/2020 | 46 | 0 | 46 |  |  | 2/27/2020 | Connected |  | N
National Grid | LYNN | 317103 | 01902 | 10 | Solar | 05_05_313W1 | 10/05/2020 | 10/08/2020 | 2 | 0 | 2 | 10/09/2020 | 10/09/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2020 |  | 10/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2020 | Connected |  | N
National Grid | LOWELL | 544488 | 01854 | 7.83 | Solar | 05_12_29W5 | 11/20/2023 |  | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 174626 | 01830 | 15 | Solar | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 146 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | LAWRENCE | 413785 | 01843 | 312.5 | Solar | 05_14_47L1 | 12/01/2022 | 07/12/2023 | 151 | 144 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2023 | 09/15/2023 | 46 | 28 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 | 12/01/2022 | 8/11/2026 | Y | STD | 308 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | METHUEN | 627408 | 01844 | 12.16 | Solar | 05_14_61L1 | 07/24/2024 | 08/01/2024 | 2 | 1 | 1 | 08/02/2024 | 08/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 12/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | SPENCER | 682135 | 01562 | 20 | Solar | 05_14_74L6 | 04/03/2025 | 04/07/2025 | 2 | 0 | 2 | 04/08/2025 | 04/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 6/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | WORCESTER | 174572 | 01604 | 1000 | Solar | 05_01_21W1 | 10/11/2011 | 10/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 680717 | 01550 | 7.6 | Solar | 05_01_27W5 | 03/26/2025 | 04/11/2025 | 3 | 0 | 3 | 04/22/2025 | 04/22/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 424618 | 01473 | 7.54 | Solar | 05_01_413L3 | 05/04/2022 | 05/09/2022 | 4 | 1 | 3 | 05/10/2022 | 05/10/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2022 | 05/04/2022 | 1/10/2024 | Y | EXP | 365 | 12/28/2022 | 01/10/2023 | 14 | 0 | 14 |  |  | 1/13/2023 | Connected |  | N
National Grid | SWANSEA | 542295 | 02777 | 0 | Other | 05_01_609W1 | 08/28/2023 | 09/12/2023 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2023 | 10/11/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 271016 | 01532 | 999 | Solar | 05_05_11W82 | 01/06/2020 | 01/17/2020 | 9 | 7 | 2 |  |  | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 343188 | 01902 | 11.4 | Solar | 05_05_313W1 | 02/21/2021 | 02/22/2021 | 0 | 0 | 0 | 02/23/2021 | 02/23/2021 | 121 | 73 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/21/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 550054 | 01854 | 6 | Solar | 05_12_29W5 | 08/23/2023 | 08/28/2023 | 3 | 2 | 1 | 08/29/2023 | 08/29/2023 | 25 | 0 | 25 | 10/18/2023 | 12/04/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 12/04/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 12/27/2023 |  | 1/1/2025 | N | EXP | 365 | 03/14/2024 | 09/11/2024 | 159 | 0 | 159 |  |  | 8/20/2024 | Connected |  | N
National Grid | NEWBURY | 174625 | 01985 | 15 | Solar | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 146 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | LAWRENCE | 753576 | 01843 | 7.6 | Solar | 05_14_47L1 | 02/27/2026 | 03/23/2026 | 4 | 0 | 4 | 03/24/2026 | 03/24/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 632220 | 01844 | 6 | Solar | 05_14_61L1 | 08/20/2024 | 08/27/2024 | 5 | 0 | 5 | 08/28/2024 | 08/28/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 | 08/20/2024 | 1/18/2026 | Y | EXP | 365 | 03/01/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | SPENCER | 705538 | 01562 | 13.68 | Solar | 05_14_75L1 | 07/18/2025 | 09/15/2025 | 5 | 0 | 5 | 10/09/2025 | 10/09/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 174571 | 01604 | 2000 | Solar | 05_01_21W1 | 10/11/2011 | 10/11/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2011 | 12/20/2011 | 26 | 0 | 26 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2012 | 10/11/2011 | 10/31/2012 | Y | STD | 38 | 04/09/2013 | 06/21/2013 | 50 | 0 | 50 | 6/21/2013 | 6/21/2013 | 8/7/2013 | Connected |  | N
National Grid | SOUTHBRIDGE | 681379 | 01550 | 15.2 | Solar | 05_01_27W5 | 03/28/2025 | 04/01/2025 | 2 | 0 | 2 | 04/02/2025 | 04/02/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 447179 | 01473 | 7.6 | Solar | 05_01_413L3 | 08/31/2022 | 10/14/2022 | 30 | 30 | 0 | 10/17/2022 | 10/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 | 08/31/2022 | 2/15/2024 | Y | EXP | 365 | 04/27/2023 | 06/08/2023 | 43 | 0 | 43 |  |  | 10/20/2023 | Connected |  | N
National Grid | SOMERSET | 552766 | 02726 | 0 | Solar | 05_01_609W1 | 09/01/2023 | 09/05/2023 | 1 | 0 | 1 | 09/06/2023 | 09/06/2023 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 412047 | 01532 | 0 | Other | 05_05_11W82 | 03/30/2022 | 04/21/2022 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2022 | 04/21/2022 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 381762 | 01902 | 15.2 | Solar | 05_05_313W1 | 09/13/2021 | 10/04/2021 | 15 | 14 | 1 | 10/05/2021 | 10/05/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  | 1/17/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | N
National Grid | LOWELL | 551927 | 01854 | 7.54 | Solar | 05_12_29W5 | 09/28/2023 | 11/15/2023 | 32 | 29 | 3 | 11/16/2023 | 11/16/2023 | 105 | 40 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 174628 | 01985 | 44 | Solar | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 145 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | LAWRENCE | 174888 | 01843 | 630 | Solar | 05_14_47L1 | 11/16/2012 | 11/16/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2012 | 03/05/2013 | 56 | 0 | 56 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2013 | 11/16/2012 | 6/30/2014 | Y | STD | 294 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 640683 | 01850 | 4.16 | Solar | 05_14_61L1 | 09/17/2024 | 10/23/2024 | 20 | 17 | 3 | 10/24/2024 | 10/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 12/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | SPENCER | 717529 | 01562 | 7.6 | Solar | 05_14_75L1 | 09/10/2025 | 09/29/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 16 | 1 | 15 | 11/05/2025 | 12/01/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/01/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/5/2026 | N | EXP | 365 | 03/27/2026 |  | 6 | 0 | 6 |  |  |  | Construction |  | N
National Grid | WORCESTER | 174617 | 01604 | 22.8 | Solar | 05_01_21W1 | 12/14/2010 | 12/14/2010 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2011 |  | 2/8/2012 | N | EXP | 309 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 2/8/2012 | Connected |  | N
National Grid | SOUTHBRIDGE | 684979 | 01550 | 15.2 | Solar | 05_01_27W5 | 04/14/2025 | 04/23/2025 | 4 | 1 | 3 | 04/24/2025 | 04/24/2025 | 35 | 22 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | HUBBARDSTON | 457748 | 01452 | 0 | Other | 05_01_413L3 | 11/23/2022 | 12/21/2022 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2022 | 01/23/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 560920 | 02777 | 5.235 | Solar | 05_01_609W1 | 11/07/2023 | 11/14/2023 | 4 | 3 | 1 | 11/15/2023 | 11/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 11/07/2023 | 1/29/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 416604 | 01532 | 250 | Solar | 05_05_11W82 | 04/04/2022 | 04/11/2022 | 5 | 0 | 5 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 04/04/2022 | 3/25/2025 | Y | STD | 455 |  |  | 0 | 0 | 0 |  |  | 4/29/2024 | Connected |  | N
National Grid | LYNN | 414064 | 01902 | 15.2 | Solar | 05_05_313W1 | 02/24/2022 | 02/28/2022 | 3 | 2 | 1 | 03/01/2022 | 03/01/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 591596 | 01852 | 6 | Solar | 05_12_29W5 | 03/07/2024 | 03/11/2024 | 2 | 0 | 2 | 03/12/2024 | 03/12/2024 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2024 | Connected |  | N
National Grid | HAVERHILL | 174627 | 01830 | 66 | Solar | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2011 | 05/02/2011 | 2/10/2012 | Y | EXP | 176 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 2/10/2012 | Connected |  | N
National Grid | LAWRENCE | 175171 | 01843 | 800 | Solar | 05_14_47L1 | 11/16/2012 | 11/16/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2012 | 03/05/2013 | 56 | 0 | 56 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 11/16/2012 | 12/31/2016 | Y | STD | 1237 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 652584 | 01826 | 3.8 | Solar | 05_14_61L1 | 11/14/2024 | 12/16/2024 | 7 | 0 | 7 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | LEICESTER | 755210 | 01524 | 11.5 | Solar | 05_14_75L1 | 03/06/2026 | 03/12/2026 | 3 | 0 | 3 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 175220 | 01604 | 17.5 | Solar | 05_01_21W1 | 11/03/2014 | 11/03/2014 | 6 | 1 | 5 | 11/13/2014 | 11/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2014 |  | 1/30/2015 | N | EXP | 77 |  |  | 0 | 0 | 0 | 2/26/2015 | 2/26/2015 | 3/8/2016 | Connected |  | N
National Grid | SOUTHBRIDGE | 689710 | 01550 | 5.76 | Solar | 05_01_27W5 | 05/05/2025 | 05/20/2025 | 2 | 0 | 2 | 05/28/2025 | 05/28/2025 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | WESTMINSTER | 471682 | 01473 | 3.8 | Solar | 05_01_413L3 | 12/05/2022 | 12/08/2022 | 3 | 0 | 3 | 12/09/2022 | 12/09/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2023 | 12/05/2022 | 3/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | SOMERSET | 566961 | 02726 | 5 | Solar | 05_01_609W1 | 11/08/2023 | 11/09/2023 | 1 | 0 | 1 | 11/13/2023 | 11/13/2023 | 38 | 14 | 24 | 03/01/2024 | 03/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 03/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 3/19/2024 |  | 4/23/2025 | N | EXP | 365 | 05/31/2024 | 07/05/2024 | 36 | 0 | 36 |  |  | 8/9/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 424766 | 01532 | 7.6 | Solar | 05_05_11W82 | 05/27/2022 | 06/01/2022 | 2 | 0 | 2 | 06/02/2022 | 06/02/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2022 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/16/2022 | Connected |  | Y
National Grid | LYNN | 430956 | 01902 | 15.2 | Solar | 05_05_313W1 | 05/16/2022 | 05/18/2022 | 2 | 0 | 2 | 05/19/2022 | 05/19/2022 | 111 | 92 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2022 | 05/16/2022 | 7/27/2024 | Y | EXP | 365 | 02/07/2023 | 07/25/2023 | 169 | 0 | 169 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 592433 | 01854 | 6 | Solar | 05_12_29W5 | 02/27/2024 | 03/04/2024 | 4 | 0 | 4 | 03/05/2024 | 03/05/2024 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2024 | Connected |  | N
National Grid | HAVERHILL | 556428 | 01830 | 480 | Solar | 05_14_13L1 | 11/22/2023 | 12/18/2023 | 18 | 10 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 02/14/2024 | 40 | 21 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 175806 | 01843 | 27.6 | Solar | 05_14_47L1 | 05/15/2015 | 05/15/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2015 | 05/15/2015 | 12/31/2016 | Y | EXP | 576 | 05/10/2016 | 05/13/2016 | 3 | 0 | 3 | 7/20/2015 | 7/20/2015 | 7/15/2016 | Connected |  | N
National Grid | LOWELL | 659408 | 01850 | 10 | Solar | 05_14_61L1 | 12/09/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 178139 | 01562 | 7.6 | Solar | 05_14_75L1 | 03/22/2018 | 03/22/2018 | 9 | 9 | 0 | 04/05/2018 | 04/05/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2018 |  | 3/28/2019 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 8/5/2019 | Connected |  | N
National Grid | WORCESTER | 175263 | 01604 | 1000 | Solar | 05_01_21W1 | 01/13/2015 | 01/13/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2015 | 02/20/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 698095 | 01571 | 13.36 | Solar | 05_01_27W5 | 07/09/2025 | 08/06/2025 | 20 | 16 | 4 | 09/09/2025 | 09/09/2025 | 61 | 47 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 585545 | 01473 | 498 | Solar | 05_01_413L3 | 02/14/2024 | 05/01/2024 | 53 | 45 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2024 | 05/08/2024 | 5 | 0 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 569500 | 02726 | 7.6 | Solar | 05_01_609W1 | 11/27/2023 | 11/29/2023 | 3 | 2 | 1 | 11/30/2023 | 11/30/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 429706 | 01532 | 240 | Solar | 05_05_11W82 | 06/01/2022 | 06/30/2022 | 20 | 15 | 5 | 07/01/2022 | 07/01/2022 | 524 | 500 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 492962 | 01902 | 14.5 | Solar | 05_05_313W1 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/01/2023 | 9/8/2024 | Y | EXP | 365 | 05/11/2023 | 09/06/2023 | 119 | 0 | 119 |  |  | 1/27/2024 | Connected |  | N
National Grid | LOWELL | 601269 | 01852 | 11.4 | Solar | 05_12_29W5 | 04/09/2024 | 06/25/2024 | 44 | 40 | 4 | 06/26/2024 | 06/26/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 566922 | 01985 | 250 | Solar | 05_14_13L1 | 12/01/2023 | 12/26/2023 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 | 01/26/2024 | 21 | 2 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 | 12/01/2023 | 4/17/2026 | Y | STD | 119 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | LAWRENCE | 176540 | 01843 | 1250 | Solar | 05_14_47L1 | 02/10/2016 | 02/10/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2016 | 03/16/2016 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2016 |  | 2/16/2017 | N | STD | 104 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 661281 | 01826 | 10 | Solar | 05_14_61L1 | 12/17/2024 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | LEICESTER | 184581 | 01524 | 15.2 | Solar | 05_14_75L1 | 07/10/2018 | 07/12/2018 | 1 | 0 | 1 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | WORCESTER | 175903 | 01604 | 224 | Solar | 05_01_21W1 | 09/28/2015 | 09/28/2015 | 0 | 0 | 0 | 09/30/2015 | 09/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 09/28/2015 | 10/5/2016 | Y | EXP | 330 | 12/23/2015 | 12/28/2015 | 2 | 0 | 2 | 2/17/2016 | 2/17/2016 | 3/24/2016 | Connected |  | N
National Grid | SOUTHBRIDGE | 711138 | 01550 | 8 | Solar | 05_01_27W5 | 08/18/2025 | 09/05/2025 | 17 | 13 | 4 | 10/03/2025 | 10/03/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 08/18/2025 | 12/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2026 | Connected |  | Y
National Grid | WESTMINSTER | 611319 | 01473 | 20 | Solar | 05_01_413L3 | 05/23/2024 | 05/24/2024 | 1 | 0 | 1 | 05/28/2024 | 05/28/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 |  | 6/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2025 | Connected |  | N
National Grid | SOMERSET | 578023 | 02726 | 9.86 | Solar | 05_01_609W1 | 01/03/2024 | 02/20/2024 | 32 | 25 | 7 | 02/21/2024 | 02/21/2024 | 41 | 35 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 443979 | 01532 | 0 | Other | 05_05_11W82 | 01/30/2023 | 02/15/2023 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 557386 | 01902 | 17.4 | Solar | 05_05_313W1 | 09/22/2023 | 10/11/2023 | 12 | 9 | 3 | 10/12/2023 | 10/12/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 603809 | 01852 | 6 | Solar | 05_12_29W5 | 04/16/2024 | 04/26/2024 | 1 | 0 | 1 | 04/29/2024 | 04/29/2024 | 75 | 66 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | HAVERHILL | 580139 | 01830 | 200 | Solar | 05_14_13L1 | 01/15/2024 | 05/15/2024 | 85 | 74 | 11 | 05/16/2024 | 05/16/2024 | 17 | 8 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 |  | 4/20/2026 | N | EXP | 196 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | LAWRENCE | 177505 | 01843 | 7.6 | Solar | 05_14_47L1 | 03/06/2017 | 03/06/2017 | 9 | 3 | 6 | 03/17/2017 | 03/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 | 03/06/2017 | 3/11/2018 | Y | EXP | 355 | 07/10/2017 | 07/31/2017 | 15 | 0 | 15 | 9/8/2017 | 9/8/2017 | 9/8/2017 | Connected |  | N
National Grid | DRACUT | 666707 | 01826 | 7.6 | Solar | 05_14_61L1 | 01/20/2025 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | SPENCER | 187051 | 01562 | 9.92 | Solar | 05_14_75L1 | 06/04/2018 | 06/04/2018 | 8 | 0 | 8 | 06/16/2018 | 06/16/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2018 |  | 6/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2019 | Connected |  | N
National Grid | WORCESTER | 175943 | 01604 | 1000 | Solar | 05_01_21W1 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2015 | 02/26/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 | 01/21/2015 | 9/28/2018 | Y | STD | 1134 | 04/09/2018 | 08/27/2018 | 130 | 0 | 130 |  |  | 9/6/2018 | Connected |  | N
National Grid | SOUTHBRIDGE | 175928 | 01550 | 99 | Solar | 05_01_2J328 | 08/05/2015 | 08/05/2015 | 2 | 2 | 0 | 08/10/2015 | 08/10/2015 | 418 | 0 | 418 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2015 |  | 8/11/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 615697 | 01473 | 20 | Solar | 05_01_413L3 | 06/05/2024 | 06/14/2024 | 7 | 5 | 2 | 06/17/2024 | 06/17/2024 | 61 | 50 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 593641 | 02726 | 0 | Battery Add-On | 05_01_609W1 | 03/08/2024 | 03/14/2024 | 4 | 0 | 4 | 03/15/2024 | 03/15/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 | 03/08/2024 | 4/1/2025 | Y | EXP | 365 | 05/24/2024 | 05/23/2024 | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 468426 | 01532 | 10 | Solar | 05_05_11W82 | 10/18/2022 | 10/20/2022 | 2 | 0 | 2 | 10/21/2022 | 10/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 |  | 2/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2023 | Connected |  | N
National Grid | LYNN | 553637 | 01902 | 160 | Solar | 05_05_313W1 | 09/11/2023 | 09/24/2023 | 9 | 0 | 9 | 09/25/2023 | 09/25/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 09/11/2023 | 1/5/2026 | Y | EXP | 280 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | LOWELL | 604998 | 01852 | 7.6 | Solar | 05_12_29W5 | 04/18/2024 | 04/25/2024 | 1 | 0 | 1 | 04/26/2024 | 04/26/2024 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2024 |  | 7/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | HAVERHILL | 744754 | 01830 | 7.6 | Solar | 05_14_14L1 | 01/12/2026 | 01/13/2026 | 2 | 0 | 2 | 01/29/2026 | 01/29/2026 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 177495 | 01843 | 12.2 | Solar | 05_14_47L1 | 12/13/2016 | 12/13/2016 | 4 | 4 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 | 12/13/2016 | 12/19/2017 | Y | EXP | 363 | 07/05/2017 | 07/24/2017 | 13 | 0 | 13 | 11/13/2017 | 11/13/2017 | 9/25/2017 | Connected |  | N
National Grid | DRACUT | 696253 | 01826 | 7.6 | Solar | 05_14_61L1 | 06/05/2025 | 07/08/2025 | 3 | 0 | 3 | 07/15/2025 | 07/15/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 06/05/2025 | 8/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | LEICESTER | 203291 | 01524 | 3.8 | Solar | 05_14_75L1 | 12/19/2018 | 12/21/2018 | 1 | 0 | 1 | 12/24/2018 | 12/24/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176203 | 01602 | 3.8 | Solar | 05_01_21W1 | 04/24/2015 | 04/24/2015 | 2 | 2 | 0 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 | 04/24/2015 | 12/31/2016 | Y | EXP | 597 | 06/17/2016 | 06/15/2016 | 0 | 0 | 0 | 5/26/2016 | 5/26/2016 | 5/26/2016 | Connected |  | N
National Grid | CHARLTON | 376505 | 01507 | 43.2 | Solar | 05_01_2J328 | 08/18/2021 | 09/10/2021 | 16 | 6 | 10 |  |  | 200 | 172 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2023 |  | 11/20/2023 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  | 11/17/2023 | Connected |  | N
National Grid | HUBBARDSTON | 648192 | 01452 | 3.8 | Solar | 05_01_413L3 | 10/30/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/30/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | SOMERSET | 598052 | 02726 | 15.2 | Solar | 05_01_609W1 | 03/23/2024 | 03/29/2024 | 5 | 2 | 3 | 04/01/2024 | 04/01/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/23/2024 | 5/23/2025 | Y | EXP | 365 | 07/03/2024 | 07/31/2024 | 29 | 0 | 29 |  |  | 10/2/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 475488 | 01532 | 15.08 | Solar | 05_05_11W82 | 11/08/2022 | 11/14/2022 | 3 | 2 | 1 | 11/15/2022 | 11/15/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 555486 | 01902 | 240 | Solar | 05_05_313W1 | 09/15/2023 | 10/13/2023 | 19 | 10 | 9 | 10/16/2023 | 10/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 | 09/15/2023 | 6/17/2025 | Y | EXP | 252 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 605339 | 01876 | 5 | Solar | 05_12_29W5 | 04/20/2024 | 05/01/2024 | 3 | 0 | 3 | 05/02/2024 | 05/02/2024 | 72 | 66 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 178225 | 01830 | 10 | Solar | 05_14_14L1 | 01/03/2018 | 01/03/2018 | 38 | 32 | 6 | 03/05/2018 | 03/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 |  | 1/10/2019 | N | EXP | 310 | 05/09/2018 | 05/08/2018 | 0 | 0 | 0 |  |  | 11/15/2018 | Connected |  | N
National Grid | LAWRENCE | 177942 | 01843 | 3.8 | Solar | 05_14_47L1 | 06/26/2017 | 06/26/2017 | 6 | 5 | 1 | 07/06/2017 | 07/06/2017 | 163 | 0 | 163 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 7/2/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 699828 | 01826 | 240 | Solar | 05_14_61L2 | 08/18/2025 | 09/04/2025 | 10 | 4 | 6 | 09/05/2025 | 09/05/2025 | 34 | 16 | 18 | 11/18/2025 | 02/12/2026 | 59 | 0 | 59 |  |  | 0 | 0 | 0 | 02/12/2026 | 59 | 0 | 59 |  |  | 0 | 0 | 0 | 2/19/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SPENCER | 317751 | 01562 | 9.6 | Solar | 05_14_75L1 | 10/20/2020 | 12/15/2020 | 38 | 37 | 1 | 12/16/2020 | 12/16/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/13/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176216 | 01602 | 1000 | Solar | 05_01_21W1 | 07/02/2015 | 07/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/03/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 | 07/02/2015 | 10/7/2017 | Y | STD | 598 | 10/11/2017 | 12/21/2017 | 44 | 0 | 44 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | SOUTHBRIDGE | 646548 | 01550 | 3.8 | Solar | 05_01_2J328 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 15 | 0 | 15 | 12/05/2024 | 01/07/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 01/07/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 649017 | 01473 | 7.6 | Solar | 05_01_413L3 | 11/04/2024 | 11/27/2024 | 6 | 0 | 6 | 12/02/2024 | 12/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/04/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N
National Grid | SOMERSET | 634319 | 02726 | 10 | Solar | 05_01_609W1 | 08/21/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 08/21/2024 | 1/27/2026 | Y | EXP | 365 | 04/30/2025 | 11/21/2025 | 206 | 0 | 206 |  |  | 12/4/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 475485 | 01532 | 15.08 | Solar | 05_05_11W82 | 11/08/2022 | 11/14/2022 | 3 | 2 | 1 | 11/15/2022 | 11/15/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 584740 | 01902 | 9.28 | Solar | 05_05_313W1 | 01/23/2024 | 01/30/2024 | 6 | 5 | 1 | 01/31/2024 | 01/31/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | TEWKSBURY | 613150 | 01876 | 3.8 | Solar | 05_12_29W5 | 05/23/2024 | 05/28/2024 | 1 | 0 | 1 | 05/29/2024 | 05/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 278152 | 01830 | 383 | Solar | 05_14_14L1 | 02/05/2020 | 02/13/2020 | 5 | 0 | 5 | 02/14/2020 | 02/14/2020 | 15 | 4 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2020 |  | 3/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 178511 | 01845 | 7.6 | Solar | 05_14_47L1 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 3/13/2019 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 175960 | 01850 | 227 | Solar | 05_14_61L2 | 06/04/2015 | 06/04/2015 | 2 | 2 | 0 | 06/08/2015 | 06/08/2015 | 418 | 0 | 418 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2015 | 06/04/2015 | 6/30/2016 | Y | EXP | 331 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 330115 | 01562 | 5.76 | Solar | 05_14_75L1 | 12/14/2020 | 02/12/2021 | 41 | 38 | 3 | 02/16/2021 | 02/16/2021 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2021 | 12/14/2020 | 9/2/2022 | Y | EXP | 365 | 05/28/2021 | 09/01/2021 | 95 | 3 | 92 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176215 | 01602 | 1000 | Solar | 05_01_21W1 | 07/02/2015 | 07/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/03/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 | 07/02/2015 | 10/7/2017 | Y | STD | 598 | 10/11/2017 | 12/21/2017 | 44 | 0 | 44 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | DUDLEY | 340607 | 01571 | 726.6 | Solar | 05_01_2J335 | 10/13/2021 | 02/28/2022 | 94 | 86 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/01/2022 | 03/01/2022 | 1 | 0 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2023 | 10/13/2021 | 4/21/2026 | Y | STD | 245 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HUBBARDSTON | 649412 | 01452 | 3.8 | Solar | 05_01_413L3 | 11/05/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 651918 | 02726 | 12.54 | Solar | 05_01_609W1 | 11/04/2024 | 12/05/2024 | 7 | 2 | 5 | 12/06/2024 | 12/06/2024 | 67 | 49 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 510632 | 01532 | 30 | Solar | 05_05_11W82 | 05/14/2023 | 05/30/2023 | 11 | 2 | 9 | 05/31/2023 | 05/31/2023 | 66 | 42 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2023 |  | 11/29/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/6/2025 | Connected |  | N
National Grid | LYNN | 607157 | 01902 | 9.135 | Solar | 05_05_313W1 | 04/27/2024 | 06/24/2024 | 39 | 34 | 5 | 06/25/2024 | 06/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | TEWKSBURY | 624218 | 01876 | 7.6 | Solar | 05_12_29W5 | 07/11/2024 | 09/18/2024 | 25 | 20 | 5 | 09/19/2024 | 09/19/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  | 12/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | Y
National Grid | NEWBURY | 381249 | 01985 | 10 | Solar | 05_14_14L1 | 09/15/2021 | 12/08/2021 | 3 | 0 | 3 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/15/2021 | 9/2/2023 | Y | EXP | 365 | 07/01/2022 | 08/02/2022 | 33 | 0 | 33 |  |  | 10/12/2022 | Connected |  | N
National Grid | LAWRENCE | 183620 | 01843 | 15.2 | Solar | 05_14_47L1 | 06/25/2018 | 06/25/2018 | 0 | 0 | 0 | 06/27/2018 | 06/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 | 06/25/2018 |  | Y | EXP | 505 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N
National Grid | LOWELL | 176749 | 01850 | 6.45 | Solar | 05_14_61L2 | 01/11/2016 | 01/11/2016 | 5 | 5 | 0 | 01/20/2016 | 01/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 | 01/11/2016 | 1/17/2017 | Y | EXP | 343 | 07/07/2016 | 08/01/2016 | 17 | 0 | 17 | 10/21/2016 | 10/21/2016 | 10/25/2016 | Connected |  | N
National Grid | SPENCER | 382184 | 01562 | 16.56 | Solar | 05_14_75L1 | 09/15/2021 | 09/17/2021 | 2 | 0 | 2 | 09/20/2021 | 09/20/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | WORCESTER | 177040 | 01602 | 2592 | Solar | 05_01_21W1 | 07/27/2016 | 08/02/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/26/2016 | 59 | 44 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2017 | 07/27/2016 | 5/31/2021 | Y | STD | 1251 | 11/05/2020 | 04/15/2021 | 110 | 0 | 110 | 5/3/2021 | 5/26/2021 | 6/15/2021 | Connected |  | N
National Grid | CHARLTON | 725024 | 01507 | 7.6 | Solar | 05_01_2J335 | 10/08/2025 | 11/11/2025 | 4 | 0 | 4 | 12/16/2025 | 12/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  | 3/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTMINSTER | 655973 | 01473 | 0 | Battery Add-On | 05_01_413L3 | 11/21/2024 | 11/25/2024 | 2 | 0 | 2 | 11/26/2024 | 11/26/2024 | 58 | 33 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 | 11/21/2024 | 3/14/2026 | Y | EXP | 365 | 07/26/2025 | 07/29/2025 | 4 | 0 | 4 |  |  | 11/24/2025 | Connected |  | N
National Grid | SOMERSET | 665038 | 02726 | 7.25 | Solar | 05_01_609W1 | 02/06/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 616104 | 01532 | 250 | Solar | 05_05_11W82 | 08/08/2024 | 02/05/2025 | 120 | 110 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2025 | 03/06/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 624536 | 01902 | 3.78 | Solar | 05_05_313W1 | 07/12/2024 | 07/26/2024 | 3 | 1 | 2 | 07/29/2024 | 07/29/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 | 07/12/2024 | 9/28/2025 | Y | EXP | 365 | 10/03/2024 | 10/24/2024 | 22 | 0 | 22 |  |  | 11/26/2024 | Connected |  | N
National Grid | TEWKSBURY | 625525 | 01876 | 5.76 | Solar | 05_12_29W5 | 07/17/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 469773 | 01985 | 15.2 | Solar | 05_14_14L1 | 10/20/2022 | 11/08/2022 | 14 | 13 | 1 | 11/09/2022 | 11/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 |  | 2/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2023 | Connected |  | N
National Grid | LAWRENCE | 188160 | 01843 | 15.2 | Solar | 05_14_47L1 | 06/14/2018 | 06/14/2018 | 5 | 0 | 5 | 06/25/2018 | 06/25/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 206222 | 01850 | 3.8 | Solar | 05_14_61L2 | 02/11/2019 | 02/20/2019 | 5 | 0 | 5 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 383819 | 01524 | 9.8 | Solar | 05_14_75L1 | 10/14/2021 | 12/16/2021 | 4 | 0 | 4 | 10/21/2021 | 10/21/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177038 | 01602 | 800 | Solar | 05_01_21W1 | 07/27/2016 | 07/27/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/26/2016 | 59 | 44 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2017 | 07/27/2016 | 3/15/2019 | Y | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 475993 | 01507 | 15.08 | Solar | 05_01_2J335 | 11/09/2022 | 12/07/2022 | 18 | 17 | 1 | 12/08/2022 | 12/08/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  | 2/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2023 | Connected |  | N
National Grid | HUBBARDSTON | 669716 | 01452 | 0 | Other | 05_01_413L3 | 03/07/2025 | 03/31/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/01/2025 | 04/29/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 665954 | 02726 | 10 | Solar | 05_01_609W1 | 01/15/2025 | 01/30/2025 | 4 | 0 | 4 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 630480 | 01532 | 7.83 | Solar | 05_05_11W82 | 08/06/2024 | 09/09/2024 | 17 | 13 | 4 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/06/2024 | 10/28/2025 | Y | EXP | 365 | 11/13/2024 | 12/05/2024 | 23 | 0 | 23 |  |  | 2/8/2025 | Connected |  | N
National Grid | LYNN | 645344 | 01904 | 5.76 | Solar | 05_05_313W1 | 10/07/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 10/07/2024 | 12/16/2025 | Y | EXP | 365 | 01/16/2025 | 02/13/2025 | 29 | 0 | 29 |  |  | 2/19/2025 | Connected |  | N
National Grid | TEWKSBURY | 635728 | 01876 | 4.06 | Solar | 05_12_29W5 | 08/27/2024 | 10/04/2024 | 19 | 16 | 3 | 10/07/2024 | 10/07/2024 | 191 | 173 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 668835 | 01985 | 5.76 | Solar | 05_14_14L1 | 01/29/2025 | 02/05/2025 | 5 | 1 | 4 | 02/06/2025 | 02/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 189468 | 01843 | 2800 | Solar | 05_14_47L1 | 10/09/2018 | 10/15/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2018 | 11/13/2018 | 21 | 1 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2019 | 10/09/2018 | 11/20/2025 | Y | STD | 809 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 318215 | 01826 | 7.6 | Solar | 05_14_61L2 | 10/28/2020 | 11/02/2020 | 2 | 0 | 2 | 11/03/2020 | 11/03/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 543272 | 01524 | 160 | Solar | 05_14_75L1 | 08/01/2023 | 08/21/2023 | 14 | 3 | 11 | 08/22/2023 | 08/22/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 08/01/2023 | 12/31/2025 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | WORCESTER | 177271 | 01609 | 40 | Solar | 05_01_21W1 | 11/14/2016 | 11/14/2016 | 1 | 1 | 0 | 11/16/2016 | 11/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2016 |  | 11/20/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 | 2/17/2017 | 2/17/2017 | 2/16/2017 | Connected |  | N
National Grid | SOUTHBRIDGE | 523999 | 01550 | 6.09 | Solar | 05_01_2J335 | 09/14/2023 | 09/15/2023 | 1 | 0 | 1 | 09/18/2023 | 09/18/2023 | 59 | 25 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 699104 | 01473 | 13.8 | Solar | 05_01_413L3 | 06/24/2025 | 07/22/2025 | 1 | 0 | 1 | 07/29/2025 | 07/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 06/24/2025 | 8/26/2026 | Y | EXP | 365 | 11/14/2025 | 02/13/2026 | 92 | 0 | 92 |  |  | 11/26/2025 | Connected |  | N
National Grid | SOMERSET | 668956 | 02726 | 15.2 | Solar | 05_01_609W1 | 01/30/2025 | 02/05/2025 | 4 | 0 | 4 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/30/2025 | 4/3/2026 | Y | EXP | 365 | 06/14/2025 | 11/24/2025 | 164 | 0 | 164 |  |  | 11/25/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 633722 | 01532 | 7.6 | Solar | 05_05_11W82 | 08/19/2024 | 12/30/2024 | 18 | 13 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 08/19/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | LYNN | 646139 | 01902 | 5.76 | Solar | 05_05_313W1 | 10/22/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/22/2024 | 1/3/2026 | Y | EXP | 365 | 01/16/2025 | 02/27/2025 | 42 | 0 | 42 |  |  | 3/15/2025 | Connected |  | N
National Grid | TEWKSBURY | 644942 | 01876 | 5.76 | Solar | 05_12_29W5 | 10/04/2024 | 02/13/2025 | 5 | 1 | 4 | 02/14/2025 | 02/14/2025 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | HAVERHILL | 702081 | 01830 | 3.04 | Solar | 05_14_14L1 | 06/30/2025 | 08/05/2025 | 11 | 6 | 5 | 09/25/2025 | 09/25/2025 | 68 | 53 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 192934 | 01843 | 7.6 | Solar | 05_14_47L1 | 08/07/2018 | 08/28/2018 | 3 | 3 | 0 | 08/29/2018 | 08/29/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 426133 | 01850 | 4.06 | Solar | 05_14_61L2 | 04/28/2022 | 05/05/2022 | 5 | 2 | 3 | 05/06/2022 | 05/06/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 04/28/2022 | 1/3/2024 | Y | EXP | 365 | 12/22/2022 | 01/03/2023 | 13 | 0 | 13 |  |  | 1/7/2023 | Connected |  | N
National Grid | SPENCER | 543762 | 01562 | 220 | Solar | 05_14_75L1 | 07/31/2023 | 08/17/2023 | 13 | 4 | 9 | 08/18/2023 | 08/18/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 | 07/31/2023 | 12/31/2025 | Y | EXP | 119 | 06/19/2025 | 06/18/2025 | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | WORCESTER | 177846 | 01602 | 1460 | Solar | 05_01_21W1 | 10/17/2017 | 10/17/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 | 12/11/2017 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 645982 | 01550 | 8.32 | Solar | 05_01_2J335 | 10/09/2024 |  | 26 | 25 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 321753 | 01452 | 0 | Other | 05_01_413L4 | 04/13/2021 | 04/30/2021 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2026 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SOMERSET | 675973 | 02726 | 5.76 | Solar | 05_01_609W1 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 83 | 67 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 662986 | 01532 | 8.36 | Solar | 05_05_11W82 | 12/30/2024 | 02/11/2025 | 5 | 2 | 3 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 12/30/2024 | 4/7/2026 | Y | EXP | 365 | 04/16/2025 | 05/20/2025 | 35 | 0 | 35 |  |  | 6/3/2025 | Connected |  | N
National Grid | LYNN | 651516 | 01902 | 7.6 | Solar | 05_05_313W1 | 11/13/2024 | 01/15/2025 | 24 | 17 | 7 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | TEWKSBURY | 646085 | 01876 | 5.76 | Solar | 05_12_29W5 | 10/10/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | NEWBURY | 174727 | 01985 | 260 | Solar | 05_14_14L2 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2012 |  | 11/1/2012 | N | EXP | 40 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | N
National Grid | LAWRENCE | 260717 | 01843 | 20 | Solar | 05_14_47L1 | 10/17/2019 | 12/02/2019 | 29 | 28 | 1 | 12/03/2019 | 12/03/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 |  | 10/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 501424 | 01850 | 10 | Solar | 05_14_61L2 | 02/27/2023 | 03/01/2023 | 2 | 0 | 2 | 03/02/2023 | 03/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 |  | 8/21/2024 | N | EXP | 730 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 553986 | 01542 | 10 | Solar | 05_14_75L1 | 09/21/2023 | 10/23/2023 | 22 | 20 | 2 | 10/24/2023 | 10/24/2023 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178344 | 01602 | 498 | Solar | 05_01_21W1 | 01/11/2018 | 02/12/2018 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2018 | 03/01/2018 | 11 | 1 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 662096 | 01507 | 3.8 | Solar | 05_01_2J335 | 12/20/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2025 | Connected |  | N
National Grid | WESTMINSTER | 684764 | 01473 | 11.4 | Solar | 05_01_413L4 | 06/09/2025 | 07/25/2025 | 10 | 7 | 3 | 08/20/2025 | 08/20/2025 | 62 | 43 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | SOMERSET | 679660 | 02726 | 7.6 | Solar | 05_01_609W1 | 03/26/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 679803 | 01532 | 7.6 | Solar | 05_05_11W82 | 03/21/2025 | 04/03/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 | 03/21/2025 | 6/2/2026 | Y | EXP | 365 | 07/24/2025 | 07/24/2025 | 1 | 0 | 1 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 653530 | 01905 | 10 | Solar | 05_05_313W1 | 11/18/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/18/2024 | 2/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | TEWKSBURY | 647380 | 01876 | 3.8 | Solar | 05_12_29W5 | 10/15/2024 | 11/01/2024 | 8 | 3 | 5 | 11/04/2024 | 11/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/15/2024 | 11/26/2025 | Y | EXP | 365 | 02/26/2025 | 03/24/2025 | 27 | 0 | 27 |  |  | 3/28/2025 | Connected |  | N
National Grid | NEWBURY | 198677 | 01985 | 0 | Solar | 05_14_14L2 | 11/13/2018 | 12/03/2018 | 11 | 4 | 7 | 12/04/2018 | 12/04/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 263544 | 01843 | 15 | Solar | 05_14_47L1 | 11/25/2019 | 12/04/2019 | 5 | 0 | 5 | 12/05/2019 | 12/05/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 11/25/2019 | 11/25/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | LOWELL | 533130 | 01850 | 3.8 | Solar | 05_14_61L2 | 06/14/2023 | 06/15/2023 | 1 | 0 | 1 | 06/16/2023 | 06/16/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 592767 | 01524 | 10 | Solar | 05_14_75L1 | 03/13/2024 | 03/19/2024 | 4 | 0 | 4 | 03/20/2024 | 03/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 192241 | 01602 | 10 | Solar | 05_01_21W1 | 07/30/2018 | 09/27/2018 | 24 | 23 | 1 | 09/28/2018 | 09/28/2018 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 662500 | 01550 | 9.75 | Solar | 05_01_2J335 | 12/24/2024 | 01/22/2025 | 13 | 11 | 2 | 01/23/2025 | 01/23/2025 | 68 | 45 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 709185 | 01452 | 4.537 | Solar | 05_01_413L4 | 08/06/2025 | 08/26/2025 | 15 | 11 | 4 | 10/28/2025 | 10/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 688130 | 02726 | 7.6 | Solar | 05_01_609W1 | 04/28/2025 | 07/10/2025 | 4 | 0 | 4 | 10/03/2025 | 10/03/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 613222 | 01532 | 3320 | Solar | 05_05_11W83 | 07/11/2024 | 07/30/2024 | 14 | 7 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2024 | 08/07/2024 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LYNN | 655152 | 01902 | 7.6 | Solar | 05_05_313W1 | 11/19/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 650334 | 01876 | 7.6 | Solar | 05_12_29W5 | 11/07/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 | 11/07/2024 | 1/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | NEWBURY | 437891 | 01985 | 15.2 | Solar | 05_14_14L2 | 06/15/2022 | 06/23/2022 | 5 | 3 | 2 | 06/24/2022 | 06/24/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 8/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | N
National Grid | LAWRENCE | 310000 | 01843 | 7.6 | Solar | 05_14_47L1 | 09/01/2020 | 09/08/2020 | 3 | 0 | 3 | 09/09/2020 | 09/09/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2020 | Connected |  | N
National Grid | DRACUT | 552329 | 01826 | 7.6 | Solar | 05_14_61L2 | 09/01/2023 | 09/08/2023 | 5 | 2 | 3 | 09/11/2023 | 09/11/2023 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 09/01/2023 | 12/2/2024 | Y | EXP | 365 | 03/26/2024 | 05/15/2024 | 51 | 0 | 51 |  |  | 5/21/2024 | Connected |  | N
National Grid | SPENCER | 617236 | 01562 | 10 | Solar | 05_14_75L1 | 06/11/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2024 | Connected |  | N
National Grid | WORCESTER | 192732 | 01602 | 4580 | Solar | 05_01_21W1 | 08/06/2018 | 08/27/2018 | 256 | 20 | 236 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/24/2018 | 10/17/2018 | 17 | 12 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 667803 | 01550 | 3.8 | Solar | 05_01_2J335 | 01/24/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 115 | 97 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 708616 | 01473 | 24.576 | Solar | 05_01_413L4 | 08/06/2025 | 08/14/2025 | 5 | 2 | 3 | 08/15/2025 | 08/15/2025 | 20 | 5 | 15 | 09/26/2025 | 02/05/2026 | 89 | 32 | 57 |  |  | 0 | 0 | 0 | 02/05/2026 | 89 | 32 | 57 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 3/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SWANSEA | 713491 | 02777 | 11.4 | Solar | 05_01_609W1 | 08/29/2025 | 09/08/2025 | 5 | 0 | 5 | 09/09/2025 | 09/09/2025 | 27 | 11 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 747624 | 01532 | 13.36 | Solar | 05_05_11W83 | 01/27/2026 | 01/30/2026 | 3 | 0 | 3 | 02/02/2026 | 02/02/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 3/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 660905 | 01904 | 10 | Solar | 05_05_313W1 | 12/16/2024 | 02/18/2025 | 5 | 0 | 5 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 650659 | 01876 | 8.45 | Solar | 05_12_29W5 | 11/06/2024 | 02/24/2025 | 18 | 14 | 4 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 11/06/2024 | 8/15/2026 | Y | EXP | 365 | 09/25/2025 | 11/05/2025 | 42 | 0 | 42 |  |  | 2/6/2026 | Connected |  | N
National Grid | NEWBURY | 199222 | 01985 | 820 | Solar | 05_14_14L3 | 11/20/2018 | 11/28/2018 | 3 | 0 | 3 |  |  | 68 | 43 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 320289 | 01843 | 11.4 | Solar | 05_14_47L1 | 11/06/2020 | 11/12/2020 | 2 | 0 | 2 | 11/13/2020 | 11/13/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/06/2020 | 2/23/2022 | Y | EXP | 365 | 05/26/2021 | 06/30/2021 | 35 | 0 | 35 |  |  | 9/24/2021 | Connected |  | N
National Grid | DRACUT | 568004 | 01826 | 7.6 | Solar | 05_14_61L2 | 11/30/2023 | 12/05/2023 | 3 | 0 | 3 | 12/06/2023 | 12/06/2023 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 627744 | 01524 | 10 | Solar | 05_14_75L1 | 07/25/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 | 07/25/2024 | 9/26/2025 | Y | EXP | 365 | 11/01/2024 | 11/08/2024 | 8 | 0 | 8 |  |  | 12/6/2024 | Connected |  | N
National Grid | WORCESTER | 199985 | 01602 | 7.6 | Solar | 05_01_21W1 | 11/01/2018 | 12/31/2018 | 8 | 0 | 8 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 671129 | 01550 | 5.76 | Solar | 05_01_2J335 | 02/10/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 106 | 90 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 724466 | 01473 | 5.76 | Solar | 05_01_413L4 | 10/06/2025 | 10/13/2025 | 3 | 0 | 3 | 11/04/2025 | 11/04/2025 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 10/06/2025 | 12/17/2026 | Y | EXP | 365 | 03/07/2026 |  | 26 | 0 | 26 |  |  |  | Construction |  | N
National Grid | SWANSEA | 301762 | 02777 | 2300 | Solar | 05_01_609W2 | 07/27/2020 | 08/03/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/04/2020 | 08/28/2020 | 19 | 7 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | NORTHBOROUGH | 174178 | 01532 | 20 | Solar | 05_05_11W83 | 03/05/2012 | 03/05/2012 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2012 |  | 5/16/2012 | N | EXP | 20 |  |  | 0 | 0 | 0 | 6/5/2012 | 6/5/2012 | 8/2/2012 | Connected |  | N
National Grid | LYNN | 662299 | 01902 | 0 | Solar | 05_05_313W1 | 01/09/2025 | 01/22/2025 | 8 | 4 | 4 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | TEWKSBURY | 654196 | 01876 | 5.76 | Solar | 05_12_29W5 | 11/18/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/18/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2025 | Connected |  | N
National Grid | NEWBURY | 517633 | 01985 | 72 | Solar | 05_14_16L1 | 04/29/2023 | 01/07/2024 | 172 | 162 | 10 |  |  | 57 | 35 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 |  | 7/14/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 340844 | 01843 | 0 | Solar | 05_14_47L1 | 02/12/2021 | 03/09/2021 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2021 | 03/29/2021 | 14 | 4 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 579602 | 01850 | 8.7 | Solar | 05_14_61L2 | 01/23/2024 | 01/25/2024 | 2 | 0 | 2 | 01/26/2024 | 01/26/2024 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 01/23/2024 | 3/13/2025 | Y | EXP | 365 | 05/16/2024 | 06/08/2024 | 24 | 0 | 24 |  |  | 6/14/2024 | Connected |  | N
National Grid | LEICESTER | 640887 | 01524 | 5.76 | Solar | 05_14_75L1 | 09/17/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 |  | 11/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 200549 | 01602 | 363.2 | Solar | 05_01_21W1 | 04/09/2019 | 06/29/2019 | 22 | 21 | 1 | 07/01/2019 | 07/01/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 682678 | 01550 | 11.4 | Solar | 05_01_2J335 | 04/03/2025 | 04/23/2025 | 3 | 0 | 3 | 05/01/2025 | 05/01/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | WESTMINSTER | 739668 | 01473 | 3.8 | Solar | 05_01_413L4 | 12/11/2025 | 12/22/2025 | 4 | 0 | 4 | 01/22/2026 | 01/22/2026 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SWANSEA | 695376 | 02777 | 25.96 | Solar | 05_01_609W2 | 06/01/2025 | 10/21/2025 | 4 | 0 | 4 | 11/04/2025 | 11/04/2025 | 100 | 82 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHBOROUGH | 176000 | 01532 | 10 | Solar | 05_05_11W83 | 06/11/2015 | 06/11/2015 | 0 | 0 | 0 | 06/16/2015 | 06/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 |  | 6/21/2016 | N | EXP | 340 |  |  | 0 | 0 | 0 | 3/24/2016 | 3/24/2016 | 3/28/2016 | Connected |  | N
National Grid | LYNN | 668429 | 01902 | 17.225 | Solar | 05_05_313W1 | 02/04/2025 | 02/26/2025 | 15 | 10 | 5 | 02/27/2025 | 02/27/2025 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | Y
National Grid | CHELMSFORD | 664824 | 01824 | 7.6 | Solar | 05_12_29W5 | 01/10/2025 | 02/03/2025 | 10 | 5 | 5 | 02/04/2025 | 02/04/2025 | 22 | 0 | 22 | 03/10/2025 | 03/07/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2025 | Connected |  | N
National Grid | HAVERHILL | 174748 | 01830 | 75 | Solar | 05_14_16L1 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 567 | 3 | 564 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2013 |  | 9/1/2014 | N | EXP | 381 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 356972 | 01843 | 7.6 | Solar | 05_14_47L1 | 05/20/2021 | 05/21/2021 | 0 | 0 | 0 | 05/24/2021 | 05/24/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2021 |  | 5/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 583839 | 01850 | 4.06 | Solar | 05_14_61L2 | 01/22/2024 | 01/25/2024 | 3 | 0 | 3 | 01/26/2024 | 01/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 01/22/2024 | 4/16/2025 | Y | EXP | 365 | 04/16/2024 | 06/18/2024 | 64 | 0 | 64 |  |  | 7/12/2024 | Connected |  | N
National Grid | SPENCER | 646841 | 01562 | 3.8 | Solar | 05_14_75L1 | 10/29/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | WORCESTER | 289979 | 01602 | 0 | Other | 05_01_21W1 | 01/14/2021 | 02/25/2021 | 27 | 18 | 9 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 743680 | 01550 | 13.36 | Solar | 05_01_2J335 | 01/06/2026 | 01/09/2026 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 20 | 9 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 744557 | 01473 | 9.423 | Solar | 05_01_413L4 | 01/20/2026 | 01/27/2026 | 8 | 6 | 2 | 02/19/2026 | 02/19/2026 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2026 | 01/20/2026 | 3/19/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SWANSEA | 717106 | 02777 | 3.8 | Solar | 05_01_609W2 | 09/11/2025 | 09/26/2025 | 2 | 0 | 2 | 10/20/2025 | 10/20/2025 | 31 | 20 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 12/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 177145 | 01532 | 15.2 | Solar | 05_05_11W83 | 08/08/2016 | 08/08/2016 | 4 | 4 | 0 | 08/15/2016 | 08/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 |  | 8/14/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/5/2017 | 1/5/2017 | 1/6/2017 | Connected |  | N
National Grid | LYNN | 677961 | 01902 | 15.76 | Solar | 05_05_313W1 | 03/13/2025 | 03/19/2025 | 4 | 0 | 4 | 03/20/2025 | 03/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | CHELMSFORD | 698445 | 01824 | 5.76 | Solar | 05_12_29W5 | 06/18/2025 | 07/18/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 | 06/18/2025 | 11/14/2026 | Y | EXP | 365 | 09/04/2025 | 09/03/2025 | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | NEWBURY | 661964 | 01985 | 6.08 | Solar | 05_14_16L1 | 12/20/2024 | 12/29/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | LAWRENCE | 418273 | 01843 | 500 | Solar | 05_14_47L1 | 09/30/2022 | 02/14/2023 | 89 | 79 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2023 | 03/20/2023 | 23 | 0 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 594483 | 01850 | 7.6 | Solar | 05_14_61L2 | 03/05/2024 | 06/11/2024 | 7 | 5 | 2 | 10/31/2024 | 10/31/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2024 | 03/05/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | LEICESTER | 656128 | 01524 | 3.8 | Solar | 05_14_75L1 | 11/23/2024 | 01/27/2025 | 7 | 2 | 5 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/23/2024 | 3/18/2026 | Y | EXP | 365 | 05/16/2025 | 10/01/2025 | 139 | 0 | 139 |  |  | 6/14/2025 | Connected |  | N
National Grid | WORCESTER | 306359 | 01602 | 5 | Solar | 05_01_21W1 | 09/10/2020 | 10/06/2020 | 17 | 14 | 3 | 10/07/2020 | 10/07/2020 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 09/10/2020 | 12/24/2021 | Y | EXP | 365 | 11/09/2021 | 01/25/2022 | 78 | 0 | 78 |  |  | 2/12/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 742117 | 01550 | 20 | Solar | 05_01_2J335 | 12/23/2025 | 01/02/2026 | 6 | 4 | 2 | 01/05/2026 | 01/05/2026 | 60 | 24 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 746755 | 01473 | 5.76 | Solar | 05_01_413L4 | 01/21/2026 | 01/22/2026 | 3 | 0 | 3 | 02/04/2026 | 02/04/2026 | 18 | 2 | 16 | 03/23/2026 |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | SWANSEA | 743472 | 02777 | 10 | Solar | 05_01_609W2 | 01/05/2026 | 01/08/2026 | 3 | 0 | 3 | 01/09/2026 | 01/09/2026 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 | 01/05/2026 | 2/9/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTHBOROUGH | 177194 | 01532 | 28 | Solar | 05_05_11W83 | 10/31/2016 | 10/31/2016 | 2 | 2 | 0 | 11/03/2016 | 11/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2016 |  | 11/6/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 5/18/2017 | 5/18/2017 | 5/22/2017 | Connected |  | N
National Grid | LYNN | 686739 | 01902 | 7.6 | Solar | 05_05_313W1 | 04/23/2025 |  | 84 | 80 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 710194 | 01824 | 240 | Solar | 05_12_29W6 | 08/12/2025 | 09/11/2025 | 21 | 11 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | HAVERHILL | 637603 | 01830 | 480 | Solar | 05_14_16L2 | 04/11/2025 | 06/23/2025 | 48 | 38 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/24/2025 | 07/14/2025 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LAWRENCE | 466928 | 01843 | 20 | Solar | 05_14_47L1 | 10/24/2022 |  | 226 | 25 | 201 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 616821 | 01850 | 3.8 | Solar | 05_14_61L2 | 06/10/2024 | 06/25/2024 | 3 | 0 | 3 | 06/26/2024 | 06/26/2024 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 656241 | 01524 | 5.76 | Solar | 05_14_75L1 | 11/22/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N
National Grid | WORCESTER | 307858 | 01602 | 15.2 | Solar | 05_01_21W1 | 08/27/2020 | 09/01/2020 | 2 | 0 | 2 | 09/02/2020 | 09/02/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/27/2020 | 11/15/2023 | Y | EXP | 0 | 06/16/2021 | 01/17/2022 | 216 | 7 | 209 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 323572 | 01550 | 7.92 | Solar | 05_01_2J345 | 11/03/2020 | 12/07/2020 | 21 | 19 | 2 | 12/08/2020 | 12/08/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 |  | 12/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2021 | Connected |  | N
National Grid | WESTMINSTER | 174325 | 01473 | 2000 | Solar | 05_01_413L4 | 01/18/2012 | 01/18/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 04/30/2014 | 06/19/2014 | 34 | 0 | 34 |  |  | 6/30/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 745987 | 02777 | 4.94 | Solar | 05_01_609W2 | 01/16/2026 | 01/21/2026 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTHBOROUGH | 178193 | 01532 | 6.6 | Solar | 05_05_11W83 | 01/02/2018 | 01/02/2018 | 24 | 0 | 24 | 02/07/2018 | 02/07/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 1/8/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  | 10/9/2018 | Connected |  | N
National Grid | SALEM | 699455 | 01970 | 16.403 | Solar | 05_05_313W1 | 07/03/2025 | 07/09/2025 | 3 | 0 | 3 | 07/10/2025 | 07/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 | 07/03/2025 | 8/11/2026 | Y | EXP | 365 | 10/03/2025 | 10/02/2025 | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | LOWELL | 720948 | 01852 | 150 | Solar | 05_12_29W6 | 09/23/2025 | 10/31/2025 | 27 | 20 | 7 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NEWBURY | 642166 | 01985 | 500 | Solar | 05_14_16L2 | 12/23/2024 |  | 316 | 62 | 254 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 496631 | 01843 | 10 | Solar | 05_14_47L1 | 02/10/2023 | 02/13/2023 | 1 | 0 | 1 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 621422 | 01826 | 7.6 | Solar | 05_14_61L2 | 06/28/2024 | 07/05/2024 | 2 | 0 | 2 | 07/08/2024 | 07/08/2024 | 72 | 25 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 657304 | 01562 | 3.8 | Solar | 05_14_75L1 | 11/27/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/27/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | WORCESTER | 337144 | 01602 | 1100 | Solar | 05_01_21W1 | 05/14/2021 | 06/23/2021 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/23/2021 | 10/14/2022 | 288 | 171 | 117 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 657160 | 01550 | 5.76 | Solar | 05_01_2J345 | 11/26/2024 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 174717 | 01473 | 52.8 | Solar | 05_01_413L4 | 01/13/2014 | 01/13/2014 | 6 | 0 | 6 | 01/24/2014 | 01/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2014 |  | 3/31/2014 | N | EXP | 60 |  |  | 0 | 0 | 0 | 3/10/2014 | 3/10/2014 | 7/21/2015 | Connected |  | N
National Grid | SWANSEA | 748805 | 02777 | 17.6 | Solar | 05_01_609W2 | 02/02/2026 | 02/03/2026 | 1 | 0 | 1 | 02/04/2026 | 02/04/2026 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 178395 | 01532 | 7.6 | Solar | 05_05_11W83 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 3/11/2019 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | Connected |  | N
National Grid | SALEM | 737612 | 01970 | 17.16 | Solar | 05_05_313W1 | 12/02/2025 | 12/08/2025 | 4 | 0 | 4 | 12/09/2025 | 12/09/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  | 2/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | LOWELL | 720438 | 01852 | 150 | Solar | 05_12_29W6 | 09/22/2025 | 11/14/2025 | 37 | 29 | 8 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NEWBURY | 714530 | 01985 | 1000 | Solar | 05_14_16L2 | 10/10/2025 | 11/12/2025 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 | 12/11/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LAWRENCE | 543688 | 01843 | 15.2 | Solar | 05_14_47L1 | 07/26/2023 | 07/30/2023 | 3 | 0 | 3 | 07/31/2023 | 07/31/2023 | 69 | 45 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2024 | Connected |  | N
National Grid | DRACUT | 637450 | 01826 | 6.195 | Solar | 05_14_61L2 | 09/04/2024 | 12/18/2024 | 25 | 21 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2025 | Connected |  | N
National Grid | LEICESTER | 662567 | 01524 | 10 | Solar | 05_14_75L1 | 12/26/2024 | 01/21/2025 | 10 | 8 | 2 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/26/2024 | 3/7/2026 | Y | EXP | 365 | 05/06/2025 | 12/22/2025 | 231 | 0 | 231 |  |  | 12/4/2025 | Connected |  | N
National Grid | WORCESTER | 341311 | 01602 | 13.8 | Solar | 05_01_21W1 | 02/09/2021 | 03/08/2021 | 17 | 14 | 3 | 03/09/2021 | 03/09/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 9/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 677870 | 01507 | 3.839 | Solar | 05_01_2J349 | 03/13/2025 | 04/07/2025 | 11 | 7 | 4 | 04/07/2025 | 04/07/2025 | 145 | 127 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTMINSTER | 174814 | 01473 | 60 | Solar | 05_01_413L4 | 07/30/2013 | 07/30/2013 | 6 | 0 | 6 | 08/08/2013 | 08/08/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2013 |  | 1/31/2014 | N | EXP | 141 |  |  | 0 | 0 | 0 | 12/11/2013 | 12/11/2013 | 12/11/2013 | Connected |  | N
National Grid | SWANSEA | 174115 | 02777 | 2000 | Solar | 05_01_609W2 | 03/30/2012 | 03/30/2012 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 178392 | 01532 | 10 | Solar | 05_05_11W83 | 03/02/2018 | 03/02/2018 | 41 | 40 | 1 | 04/04/2018 | 04/04/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2018 |  | 3/7/2019 | N | EXP | 175 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 614470 | 01970 | 240 | Solar | 05_05_313W2 | 06/07/2024 | 07/09/2024 | 20 | 13 | 7 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 | 06/07/2024 | 2/21/2027 | Y | STD | 364 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LOWELL | 177264 | 01852 | 784 | Solar | 05_12_29W6 | 11/08/2016 | 11/08/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 01/18/2017 | 42 | 29 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/13/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 174629 | 01985 | 500 | Solar | 05_14_16L2 | 05/17/2011 | 05/17/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2011 | 05/17/2011 | 1/23/2012 | Y | EXP | 217 | 10/19/2011 | 11/18/2011 | 21 | 0 | 21 | 8/6/2012 | 8/6/2012 | 1/23/2012 | Connected |  | N
National Grid | LAWRENCE | 563377 | 01843 | 0 | Solar | 05_14_47L1 | 10/16/2023 | 10/17/2023 | 1 | 0 | 1 | 10/18/2023 | 10/18/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 |  | 1/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2024 | Connected |  | N
National Grid | LOWELL | 651306 | 01850 | 7.6 | Solar | 05_14_61L2 | 10/31/2024 | 11/12/2024 | 6 | 1 | 5 | 11/13/2024 | 11/13/2024 | 94 | 73 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 10/31/2024 | 5/20/2026 | Y | EXP | 365 | 07/24/2025 | 12/22/2025 | 152 | 32 | 120 |  |  | 1/7/2026 | Connected |  | N
National Grid | SPENCER | 663641 | 01562 | 15.2 | Solar | 05_14_75L1 | 01/06/2025 | 01/14/2025 | 2 | 0 | 2 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | WORCESTER | 449868 | 01603 | 10 | Solar | 05_01_21W1 | 12/29/2022 | 01/04/2023 | 3 | 0 | 3 | 01/05/2023 | 01/05/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 534979 | 01507 | 14.21 | Solar | 05_01_2J349 | 06/19/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2023 |  | 8/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2023 | Connected |  | N
National Grid | WESTMINSTER | 175237 | 01473 | 480 | Solar | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  | 0 | 0 | 0 | 12/25/2014 | 12/25/2014 | 0 | 0 | 0 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 660 | 01/28/2016 | 04/01/2016 | 44 | 0 | 44 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | SWANSEA | 174702 | 02777 | 13.5 | Solar | 05_01_609W2 | 01/03/2013 | 01/03/2013 | 16 | 9 | 7 | 01/29/2013 | 01/29/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2013 |  | 3/29/2013 | N | EXP | 55 |  |  | 0 | 0 | 0 | 6/5/2013 | 6/5/2013 | 8/15/2013 | Connected |  | N
National Grid | NORTHBOROUGH | 178672 | 01532 | 7.6 | Solar | 05_05_11W83 | 03/20/2018 | 03/20/2018 | 25 | 0 | 25 | 05/08/2018 | 05/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/26/2019 | N | EXP | 319 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 621987 | 01970 | 300 | Solar | 05_05_313W2 | 05/30/2025 | 10/15/2025 | 94 | 85 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 | 11/03/2025 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LOWELL | 177927 | 01851 | 784 | Solar | 05_12_29W6 | 11/08/2016 | 11/08/2016 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 01/18/2017 | 42 | 29 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2017 |  | 6/15/2018 | N | STD | 262 |  |  | 0 | 0 | 0 |  |  | 6/14/2018 | Connected |  | N
National Grid | NEWBURY | 177800 | 01985 | 266.4 | Solar | 05_14_16L2 | 08/03/2017 | 08/03/2017 | 14 | 14 | 0 | 08/24/2017 | 08/24/2017 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 | 08/03/2017 | 11/30/2020 | Y | EXP | 879 |  |  | 0 | 0 | 0 |  |  | 10/28/2020 | Connected |  | N
National Grid | LAWRENCE | 626005 | 01843 | 50 | Solar | 05_14_47L1 | 07/22/2024 | 09/27/2024 | 48 | 39 | 9 | 09/30/2024 | 09/30/2024 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 2/16/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | LOWELL | 663551 | 01850 | 5.76 | Solar | 05_14_61L2 | 01/03/2025 | 01/16/2025 | 6 | 0 | 6 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 664382 | 01524 | 3.8 | Solar | 05_14_75L1 | 01/08/2025 | 01/15/2025 | 2 | 0 | 2 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | WORCESTER | 452991 | 01603 | 10 | Solar | 05_01_21W1 | 11/02/2022 | 11/09/2022 | 6 | 4 | 2 | 11/10/2022 | 11/10/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 | 11/02/2022 | 8/5/2024 | Y | EXP | 365 | 06/16/2023 | 08/03/2023 | 49 | 0 | 49 |  |  | 8/29/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 661625 | 01550 | 3.8 | Solar | 05_01_2J349 | 12/19/2024 | 01/14/2025 | 5 | 0 | 5 | 01/15/2025 | 01/15/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 175236 | 01473 | 480 | Solar | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  | 0 | 0 | 0 | 12/25/2014 | 03/11/2015 | 50 | 0 | 50 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 660 | 01/28/2016 | 04/01/2016 | 44 | 0 | 44 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | SWANSEA | 174879 | 02777 | 1800 | Solar | 05_01_609W2 | 02/06/2013 | 02/06/2013 | 210 | 207 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 193254 | 01532 | 6 | Solar | 05_05_11W83 | 08/10/2018 | 10/08/2018 | 15 | 15 | 0 | 10/09/2018 | 10/09/2018 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 | 08/10/2018 | 10/30/2019 | Y | EXP | 378 | 05/08/2019 | 05/07/2019 | 0 | 0 | 0 |  |  | 6/4/2019 | Connected |  | N
National Grid | SALEM | 664586 | 01970 | 960 | Solar | 05_05_313W2 | 05/19/2025 | 07/10/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/11/2025 | 08/07/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LOWELL | 188370 | 01852 | 7.6 | Solar | 05_12_29W6 | 07/03/2018 | 07/03/2018 | 3 | 0 | 3 | 07/11/2018 | 07/11/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 177798 | 01985 | 233.1 | Solar | 05_14_16L2 | 08/03/2017 | 08/03/2017 | 14 | 14 | 0 | 08/18/2017 | 08/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 | 08/03/2017 | 8/9/2018 | Y | EXP | 336 | 02/12/2018 | 03/07/2018 | 13 | 0 | 13 | 3/9/2018 | 3/9/2018 | 3/9/2018 | Connected |  | N
National Grid | LAWRENCE | 627775 | 01843 | 23 | Battery Add-On | 05_14_47L1 | 07/25/2024 | 07/29/2024 | 2 | 0 | 2 | 07/30/2024 | 07/30/2024 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | N
National Grid | LOWELL | 667365 | 01850 | 7.6 | Solar | 05_14_61L2 | 01/23/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 667677 | 01562 | 3.8 | Solar | 05_14_75L1 | 01/24/2025 | 02/17/2025 | 3 | 0 | 3 | 02/18/2025 | 02/18/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 01/24/2025 | 4/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | WORCESTER | 367365 | 01603 | 3.8 | Solar | 05_01_21W1 | 07/08/2021 | 07/13/2021 | 3 | 0 | 3 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2021 |  | 11/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 698530 | 01550 | 11.4 | Solar | 05_01_2J353 | 06/27/2025 | 07/23/2025 | 4 | 0 | 4 | 08/01/2025 | 08/01/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTMINSTER | 175235 | 01473 | 480 | Solar | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  | 0 | 0 | 0 | 12/25/2014 | 03/11/2015 | 50 | 0 | 50 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 660 | 01/18/2016 | 04/01/2016 | 51 | 0 | 51 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | SWANSEA | 176737 | 02777 | 496 | Solar | 05_01_609W2 | 10/29/2015 | 10/29/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2015 | 12/04/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 |  | 11/3/2016 | N | STD | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 320884 | 01532 | 10.56 | Solar | 05_05_11W83 | 11/09/2020 | 11/12/2020 | 1 | 0 | 1 | 11/13/2020 | 11/13/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 670266 | 01906 | 960 | Solar | 05_05_313W2 | 10/01/2025 | 11/23/2025 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 12/23/2025 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LOWELL | 195677 | 01851 | 5 | Solar | 05_12_29W6 | 09/11/2018 | 11/09/2018 | 12 | 11 | 1 | 11/13/2018 | 11/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 178588 | 01830 | 350 | Solar | 05_14_16L2 | 03/13/2018 | 03/13/2018 | 1 | 0 | 1 | 05/16/2018 | 05/16/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 12/2/2019 | N | EXP | 551 |  |  | 0 | 0 | 0 |  |  | 12/16/2019 | Connected |  | N
National Grid | LAWRENCE | 636761 | 01843 | 5.76 | Solar | 05_14_47L1 | 08/30/2024 | 09/16/2024 | 2 | 0 | 2 | 09/17/2024 | 09/17/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 | 08/30/2024 | 11/25/2025 | Y | EXP | 365 | 02/05/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 4/29/2025 | Connected |  | N
National Grid | LOWELL | 671905 | 01850 | 7.25 | Solar | 05_14_61L2 | 02/13/2025 | 03/10/2025 | 4 | 0 | 4 | 03/11/2025 | 03/11/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 5/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | SPENCER | 678762 | 01562 | 10 | Solar | 05_14_75L1 | 03/18/2025 | 03/24/2025 | 5 | 2 | 3 | 03/25/2025 | 03/25/2025 | 195 | 176 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 382477 | 01602 | 15.2 | Solar | 05_01_21W1 | 09/29/2021 | 12/29/2021 | 22 | 19 | 3 | 11/02/2021 | 11/02/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 12/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 619089 | 01550 | 5.76 | Solar | 05_01_2J353 | 06/19/2024 | 06/26/2024 | 0 | 0 | 0 | 06/27/2024 | 06/27/2024 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 175264 | 01473 | 480 | Solar | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  | 0 | 0 | 0 | 12/25/2014 | 12/25/2014 | 0 | 0 | 0 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 660 | 03/29/2016 | 04/01/2016 | 3 | 0 | 3 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | SWANSEA | 178301 | 02777 | 1440 | Solar | 05_01_609W2 | 11/16/2017 | 11/16/2017 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2017 | 01/18/2018 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/21/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 348833 | 01532 | 499 | Solar | 05_05_11W83 | 04/20/2021 | 05/04/2021 | 9 | 0 | 9 |  |  | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 737222 | 01970 | 0 | Battery Add-On | 05_05_313W2 | 12/01/2025 | 12/02/2025 | 1 | 0 | 1 |  |  | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LOWELL | 343901 | 01852 | 7.6 | Solar | 05_12_29W6 | 04/02/2021 | 04/06/2021 | 1 | 0 | 1 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | NEWBURY | 314332 | 01985 | 10 | Solar | 05_14_16L2 | 10/08/2020 | 10/12/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  | 1/1/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 646391 | 01843 | 5.76 | Solar | 05_14_47L1 | 10/16/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/16/2024 | 12/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | DRACUT | 674367 | 01826 | 10 | Solar | 05_14_61L3 | 03/03/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 | 03/03/2025 | 10/13/2026 | Y | EXP | 365 | 12/31/2025 |  | 92 | 0 | 92 |  |  |  | Construction |  | N
National Grid | SPENCER | 684922 | 01562 | 15.76 | Solar | 05_14_75L1 | 04/15/2025 | 04/21/2025 | 4 | 0 | 4 | 04/22/2025 | 04/22/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 520923 | 01602 | 0 | Solar | 05_01_21W1 | 04/21/2023 | 04/24/2023 | 1 | 0 | 1 | 04/25/2023 | 04/25/2023 | 349 | 196 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 661853 | 01550 | 5.76 | Solar | 05_01_2J353 | 12/19/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | Y
National Grid | WESTMINSTER | 175396 | 01473 | 480 | Solar | 05_01_413L4 | 11/17/2014 | 11/17/2014 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 | 12/24/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 178331 | 02777 | 3000 | Solar | 05_01_609W2 | 11/16/2017 | 12/18/2017 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2017 | 01/19/2018 | 22 | 0 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 | 11/16/2017 | 3/26/2021 | Y | STD | 564 | 06/05/2020 | 03/05/2021 | 273 | 41 | 232 | 2/18/2021 | 3/4/2021 | 3/12/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 524644 | 01532 | 0 | Solar | 05_05_11W83 | 05/09/2023 | 05/10/2023 | 1 | 0 | 1 | 05/11/2023 | 05/11/2023 | 197 | 176 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 |  | 3/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2024 | Connected |  | N
National Grid | SALEM | 174471 | 01970 | 285 | Solar | 05_05_313W2 | 05/06/2011 | 05/06/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2011 | 05/06/2011 | 10/31/2012 | Y | EXP | 429 | 05/07/2012 | 07/19/2012 | 50 | 0 | 50 | 9/20/2012 | 9/20/2012 | 8/13/2012 | Connected |  | N
National Grid | CHELMSFORD | 348179 | 01824 | 499.9 | Solar | 05_12_29W6 | 05/14/2021 |  | 373 | 363 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 599266 | 01985 | 6 | Solar | 05_14_16L2 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 | 03/26/2024 | 4/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | LAWRENCE | 653693 | 01843 | 0 | Solar | 05_14_47L1 | 11/12/2024 | 11/14/2024 | 2 | 0 | 2 | 11/15/2024 | 11/15/2024 | 116 | 91 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | LOWELL | 709911 | 01850 | 7.6 | Solar | 05_14_61L3 | 08/05/2025 | 09/16/2025 | 2 | 0 | 2 | 09/17/2025 | 09/17/2025 | 40 | 24 | 16 | 11/19/2025 | 12/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 12/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/12/2026 | N | EXP | 365 | 03/11/2026 |  | 22 | 0 | 22 |  |  |  | Construction |  | N
National Grid | LEICESTER | 717230 | 01524 | 11.5 | Solar | 05_14_75L1 | 09/05/2025 | 09/16/2025 | 14 | 10 | 4 | 10/23/2025 | 10/23/2025 | 56 | 47 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 536765 | 01602 | 13.8 | Solar | 05_01_21W1 | 07/11/2023 | 11/07/2023 | 82 | 72 | 10 | 11/08/2023 | 11/08/2023 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 692871 | 01550 | 9.28 | Solar | 05_01_2J353 | 05/20/2025 | 06/04/2025 | 2 | 0 | 2 | 06/05/2025 | 06/05/2025 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid | WESTMINSTER | 175474 | 01473 | 984 | Solar | 05_01_413L4 | 12/05/2014 | 12/05/2014 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/09/2015 | 18 | 18 | 0 |  | 0 | 0 | 0 | 08/11/2015 | 10/05/2015 | 39 | 39 | 0 | 2/5/2016 | 12/05/2014 | 12/31/2017 | Y | STD | 695 | 05/04/2017 | 12/12/2017 | 147 | 0 | 147 | 12/13/2017 | 12/13/2017 | 12/31/2017 | Connected |  | N
National Grid | SWANSEA | 272136 | 02777 | 5000 | Other | 05_01_609W2 | 03/03/2020 | 03/17/2020 | 10 | 6 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2020 | 04/02/2020 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 559394 | 01532 | 5 | Solar | 05_05_11W83 | 10/02/2023 | 10/16/2023 | 10 | 7 | 3 | 10/17/2023 | 10/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 10/02/2023 | 11/10/2024 | Y | EXP | 365 | 01/12/2024 | 02/21/2024 | 41 | 0 | 41 |  |  | 5/7/2024 | Connected |  | N
National Grid | SALEM | 174470 | 01970 | 95 | Solar | 05_05_313W2 | 05/06/2011 | 05/06/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2011 | 05/06/2011 | 10/31/2012 | Y | EXP | 429 | 05/07/2012 | 07/19/2012 | 50 | 0 | 50 | 9/20/2012 | 9/20/2012 | 8/20/2012 | Connected |  | N
National Grid | LOWELL | 364264 | 01852 | 0 | Solar | 05_12_29W6 | 07/14/2021 | 07/29/2021 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2021 | 09/01/2021 | 23 | 3 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 639458 | 01985 | 5.76 | Solar | 05_14_16L2 | 09/11/2024 | 10/04/2024 | 3 | 0 | 3 | 10/07/2024 | 10/07/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/11/2024 | 11/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | LAWRENCE | 653594 | 01843 | 7.6 | Solar | 05_14_47L1 | 11/12/2024 | 11/14/2024 | 2 | 0 | 2 | 11/15/2024 | 11/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 712782 | 01850 | 11.5 | Solar | 05_14_61L3 | 08/18/2025 | 01/06/2026 | 44 | 43 | 1 | 01/07/2026 | 01/07/2026 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 3/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LEICESTER | 733331 | 01524 | 5.76 | Solar | 05_14_75L1 | 11/12/2025 | 12/10/2025 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 620137 | 01602 | 7.6 | Solar | 05_01_21W1 | 06/24/2024 | 07/23/2024 | 5 | 0 | 5 | 07/24/2024 | 07/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 06/24/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 728739 | 01550 | 17.6 | Solar | 05_01_2J393 | 12/12/2025 | 12/16/2025 | 2 | 0 | 2 | 12/17/2025 | 12/17/2025 | 71 | 24 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTMINSTER | 175473 | 01473 | 480 | Solar | 05_01_413L4 | 12/02/2014 | 12/02/2014 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 01/09/2015 | 14 | 0 | 14 |  | 0 | 0 | 0 | 08/11/2015 | 10/05/2015 | 38 | 1 | 37 | 2/5/2016 | 12/02/2014 | 12/31/2017 | Y | STD | 695 | 05/04/2017 | 12/12/2017 | 147 | 0 | 147 | 12/13/2017 | 12/13/2017 | 12/31/2017 | Connected |  | N
National Grid | SWANSEA | 310476 | 02777 | 10 | Hydro | 05_01_609W2 | 09/03/2020 | 10/07/2020 | 23 | 17 | 6 | 10/08/2020 | 10/08/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 638473 | 01532 | 10 | Solar | 05_05_11W83 | 09/06/2024 | 09/27/2024 | 3 | 0 | 3 | 09/30/2024 | 09/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 09/06/2024 | 12/26/2025 | Y | EXP | 365 | 12/19/2024 | 02/05/2025 | 49 | 0 | 49 |  |  | 3/27/2025 | Connected |  | N
National Grid | SALEM | 174469 | 01970 | 120 | Solar | 05_05_313W2 | 05/06/2011 | 05/06/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2011 | 05/06/2011 | 10/31/2012 | Y | EXP | 429 | 05/07/2012 | 07/19/2012 | 50 | 0 | 50 | 9/20/2012 | 9/20/2012 | 8/13/2012 | Connected |  | N
National Grid | LOWELL | 364600 | 01851 | 6 | Solar | 05_12_29W6 | 06/28/2021 | 09/02/2021 | 48 | 47 | 1 | 09/03/2021 | 09/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 | 06/28/2021 | 5/13/2023 | Y | EXP | 365 | 03/24/2022 | 04/21/2022 | 29 | 0 | 29 |  |  | 5/16/2022 | Connected |  | N
National Grid | HAVERHILL | 671565 | 01830 | 3.8 | Solar | 05_14_16L2 | 02/11/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2025 | Connected |  | N
National Grid | LAWRENCE | 654681 | 01843 | 22.8 | Solar | 05_14_47L1 | 11/15/2024 | 01/07/2025 | 27 | 25 | 2 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | DRACUT | 732991 | 01826 | 3.8 | Solar | 05_14_61L3 | 12/23/2025 | 12/29/2025 | 1 | 0 | 1 | 01/15/2026 | 01/15/2026 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 744459 | 01562 | 0 | Solar | 05_14_75L1 | 01/09/2026 | 01/14/2026 | 2 | 1 | 1 | 01/15/2026 | 01/15/2026 | 30 | 16 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2026 |  | 3/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2026 | Connected |  | Y
National Grid | WORCESTER | 640689 | 01610 | 4.35 | Solar | 05_01_21W1 | 09/17/2024 | 10/08/2024 | 10 | 7 | 3 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/17/2024 | 12/19/2025 | Y | EXP | 365 | 01/23/2025 | 06/20/2025 | 149 | 0 | 149 |  |  | 6/30/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 648206 | 01550 | 5.76 | Solar | 05_01_2J393 | 10/30/2024 |  | 75 | 71 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 175559 | 01473 | 480 | Solar | 05_01_413L4 | 07/30/2014 | 07/30/2014 | 7 | 0 | 7 | 08/11/2014 | 08/11/2014 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 311776 | 02777 | 4990 | Solar | 05_01_609W2 | 10/05/2020 | 10/14/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2020 | 11/09/2020 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 662100 | 01532 | 5.76 | Solar | 05_05_11W83 | 12/20/2024 | 02/11/2025 | 4 | 0 | 4 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | SALEM | 176385 | 01970 | 480 | Solar | 05_05_313W2 | 12/01/2015 | 12/01/2015 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 12/18/2015 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2016 |  | 8/1/2017 | N | STD | 326 |  |  | 0 | 0 | 0 | 6/21/2017 | 6/21/2017 | 7/6/2017 | Connected |  | N
National Grid | LOWELL | 493073 | 01851 | 0 | Other | 05_12_29W6 | 05/02/2023 | 10/23/2023 | 119 | 109 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2023 | 12/09/2023 | 33 | 16 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 558959 | 01985 | 240 | Solar | 05_14_16L3 | 09/29/2023 | 10/23/2023 | 15 | 5 | 10 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 | 09/29/2023 | 3/3/2027 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | ANDOVER | 655659 | 01810 | 10 | Solar | 05_14_47L1 | 11/20/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/20/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | LOWELL | 732315 | 01850 | 4600 | Other | 05_14_61L3 | 03/06/2026 |  | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LEICESTER | 174877 | 01524 | 30 | Solar | 05_14_75L2 | 10/25/2011 | 10/25/2011 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2012 |  | 12/31/2012 | N | EXP | 273 |  |  | 0 | 0 | 0 | 4/16/2012 | 4/16/2012 | 4/17/2012 | Terminated |  | N
National Grid | WORCESTER | 656080 | 01602 | 3.8 | Solar | 05_01_21W1 | 11/21/2024 | 01/10/2025 | 28 | 22 | 6 | 01/13/2025 | 01/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 649074 | 01507 | 5.584 | Solar | 05_01_2J393 | 10/23/2024 | 01/01/2025 | 31 | 26 | 5 | 01/02/2025 | 01/02/2025 | 74 | 52 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 175558 | 01473 | 480 | Solar | 05_01_413L4 | 07/30/2014 | 07/30/2014 | 7 | 0 | 7 | 08/11/2014 | 08/11/2014 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/3/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 356001 | 02777 | 7.68 | Solar | 05_01_609W2 | 05/03/2021 | 05/04/2021 | 0 | 0 | 0 | 05/05/2021 | 05/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 5/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | MARLBOROUGH | 662103 | 01752 | 10 | Solar | 05_05_11W83 | 12/20/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/20/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 177359 | 01907 | 10.5 | Solar | 05_05_313W2 | 06/21/2016 | 06/21/2016 | 3 | 3 | 0 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 | 06/21/2016 | 6/28/2017 | Y | EXP | 344 | 11/01/2016 | 12/07/2016 | 24 | 0 | 24 | 1/17/2017 | 1/17/2017 | 1/23/2017 | Connected |  | N
National Grid | LOWELL | 573931 | 01851 | 10.47 | Solar | 05_12_29W6 | 11/28/2023 | 12/20/2023 | 16 | 16 | 0 | 12/21/2023 | 12/21/2023 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2024 | Connected |  | N
National Grid | NEWBURY | 664845 | 01985 | 140 | Solar | 05_14_16L3 | 01/13/2025 | 03/19/2025 | 45 | 36 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LAWRENCE | 660760 | 01843 | 15.76 | Solar | 05_14_47L1 | 12/16/2024 | 12/26/2024 | 7 | 3 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | LOWELL | 746274 | 01852 | 17.86 | Solar | 05_14_61L3 | 01/20/2026 | 02/02/2026 | 9 | 4 | 5 | 02/03/2026 | 02/03/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 175932 | 01562 | 4.3 | Solar | 05_14_75L2 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 | 08/06/2015 | 8/15/2016 | Y | EXP | 349 | 04/25/2016 | 05/17/2016 | 16 | 0 | 16 | 6/20/2016 | 6/20/2016 | 6/22/2016 | Connected |  | N
National Grid | WORCESTER | 659845 | 01602 | 10 | Solar | 05_01_21W1 | 12/11/2024 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | CHARLTON | 649633 | 01507 | 4.93 | Solar | 05_01_2J393 | 10/25/2024 | 11/05/2024 | 4 | 0 | 4 | 11/06/2024 | 11/06/2024 | 18 | 0 | 18 | 12/17/2024 | 08/26/2025 | 173 | 108 | 65 |  |  | 0 | 0 | 0 | 08/26/2025 | 173 | 108 | 65 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 175600 | 01473 | 1000 | Solar | 05_01_413L4 | 08/04/2014 | 08/04/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/15/2014 | 09/15/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 08/04/2014 | 7/30/2018 | Y | STD | 980 | 11/28/2016 | 03/28/2017 | 82 | 0 | 82 |  |  | 7/20/2018 | Connected |  | N
National Grid | SWANSEA | 371839 | 02777 | 15.2 | Solar | 05_01_609W2 | 07/23/2021 | 07/28/2021 | 4 | 3 | 1 | 07/29/2021 | 07/29/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 |  | 8/31/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2022 | Connected |  | N
National Grid | WESTBOROUGH | 663923 | 01581 | 7.6 | Solar | 05_05_11W83 | 01/06/2025 | 01/17/2025 | 4 | 0 | 4 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 | 01/06/2025 | 3/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | SALEM | 178636 | 01970 | 10 | Solar | 05_05_313W2 | 04/09/2018 | 04/09/2018 | 8 | 0 | 8 | 04/20/2018 | 04/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2018 |  | 4/15/2019 | N | EXP | 215 |  |  | 0 | 0 | 0 |  |  | 6/12/2019 | Connected |  | N
National Grid | LOWELL | 610926 | 01851 | 9.57 | Solar | 05_12_29W6 | 05/14/2024 | 08/21/2024 | 5 | 2 | 3 | 08/22/2024 | 08/22/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 10/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2024 | Connected |  | N
National Grid | NEWBURY | 676981 | 01985 | 750 | Solar | 05_14_16L3 | 04/07/2025 | 06/10/2025 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LAWRENCE | 667332 | 01843 | 7.6 | Solar | 05_14_47L1 | 01/23/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 | 01/23/2025 | 5/1/2026 | Y | EXP | 365 | 10/01/2025 | 11/25/2025 | 56 | 0 | 56 |  |  | 12/4/2025 | Connected |  | N
National Grid | DRACUT | 749217 | 01826 | 23 | Solar | 05_14_61L3 | 02/04/2026 | 02/06/2026 | 2 | 0 | 2 | 02/09/2026 | 02/09/2026 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2026 |  | 3/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEICESTER | 176005 | 01524 | 10.32 | Solar | 05_14_75L2 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 |  | 8/19/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 | 4/6/2016 | 4/6/2016 | 4/8/2016 | Connected |  | N
National Grid | WORCESTER | 659461 | 01610 | 3.8 | Solar | 05_01_21W1 | 12/09/2024 | 01/03/2025 | 17 | 14 | 3 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 654942 | 01507 | 5.76 | Solar | 05_01_2J393 | 11/18/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 122 | 100 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 175654 | 01473 | 480 | Solar | 05_01_413L4 | 05/05/2014 | 05/05/2014 | 7 | 0 | 7 | 05/15/2014 | 05/15/2014 | 46 | 8 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2014 |  | 10/31/2014 | N | EXP | 128 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 373050 | 02777 | 7.68 | Solar | 05_01_609W2 | 08/05/2021 | 08/27/2021 | 17 | 16 | 1 | 08/30/2021 | 08/30/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 1/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 667625 | 01532 | 7.6 | Solar | 05_05_11W83 | 01/24/2025 | 02/18/2025 | 5 | 0 | 5 | 02/19/2025 | 02/19/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | SALEM | 188768 | 01970 | 120 | Solar | 05_05_313W2 | 07/04/2018 | 07/04/2018 | 8 | 0 | 8 | 07/18/2018 | 07/18/2018 | 276 | 26 | 250 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 621136 | 01851 | 7.6 | Solar | 05_12_29W6 | 06/27/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 |  | 8/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | NEWBURY | 718425 | 01985 | 12.215 | Solar | 05_14_16L3 | 09/16/2025 | 09/29/2025 | 5 | 0 | 5 | 10/20/2025 | 10/20/2025 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 | 09/16/2025 | 11/24/2026 | Y | EXP | 365 | 01/22/2026 |  | 70 | 0 | 70 |  |  |  | Construction |  | N
National Grid | ANDOVER | 691485 | 01810 | 7.6 | Solar | 05_14_47L1 | 05/23/2025 | 06/13/2025 | 6 | 2 | 4 | 07/02/2025 | 07/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 754059 | 01826 | 7.6 | Solar | 05_14_61L3 | 03/02/2026 | 03/05/2026 | 2 | 0 | 2 | 03/19/2026 | 03/19/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEICESTER | 177911 | 01524 | 7.6 | Solar | 05_14_75L2 | 08/16/2017 | 08/16/2017 | 13 | 13 | 0 | 09/30/2017 | 09/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 |  | 8/21/2018 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 661410 | 01602 | 5.76 | Solar | 05_01_21W1 | 12/18/2024 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 655707 | 01507 | 3.8 | Solar | 05_01_2J393 | 11/20/2024 | 12/06/2024 | 6 | 1 | 5 | 12/09/2024 | 12/09/2024 | 69 | 50 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 176353 | 01473 | 2500 | Solar | 05_01_413L4 | 05/15/2015 | 05/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2015 | 06/12/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 | 11/25/2015 | 12/23/2015 | 19 | 0 | 19 | 12/23/2015 | 05/15/2015 | 10/30/2015 | Y | STD | 54 |  |  | 0 | 0 | 0 | 10/3/2017 | 10/3/2017 | 10/3/2017 | Connected |  | N
National Grid | SWANSEA | 413977 | 02777 | 13.05 | Solar | 05_01_609W2 | 06/28/2022 | 07/01/2022 | 3 | 0 | 3 | 07/05/2022 | 07/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 06/28/2022 | 1/18/2024 | Y | EXP | 365 | 01/07/2023 | 01/14/2023 | 8 | 0 | 8 |  |  | 6/29/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 712019 | 01532 | 7.329 | Solar | 05_05_11W83 | 08/14/2025 | 09/09/2025 | 3 | 0 | 3 | 09/10/2025 | 09/10/2025 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2026 | Connected |  | N
National Grid | SALEM | 205688 | 01970 | 250 | Solar | 05_05_313W2 | 01/10/2019 | 01/16/2019 | 2 | 0 | 2 | 01/17/2019 | 01/17/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 652997 | 01851 | 7.6 | Solar | 05_12_29W6 | 11/14/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/14/2024 | 2/26/2026 | Y | EXP | 365 | 06/12/2025 | 11/26/2025 | 168 | 0 | 168 |  |  | 12/15/2025 | Connected |  | N
National Grid | NEWBURY | 175900 | 01985 | 100 | Solar | 05_14_16L3 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2015 |  | 10/4/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 3/9/2016 | 3/9/2016 | 3/11/2016 | Connected |  | N
National Grid | LAWRENCE | 737669 | 01843 | 13.3 | Solar | 05_14_47L1 | 12/02/2025 |  | 60 | 25 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 176512 | 01826 | 7.6 | Solar | 05_14_61L3 | 03/29/2016 | 03/29/2016 | 2 | 2 | 0 | 04/01/2016 | 04/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 | 03/29/2016 | 8/4/2017 | Y | EXP | 472 | 08/26/2016 | 01/11/2017 | 92 | 0 | 92 | 5/31/2017 | 5/31/2017 | 5/31/2017 | Connected |  | N
National Grid | SPENCER | 198227 | 01562 | 6 | Solar | 05_14_75L2 | 11/08/2018 | 12/13/2018 | 21 | 17 | 4 | 12/14/2018 | 12/14/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 | 11/08/2018 | 9/16/2019 | Y | EXP | 262 | 04/05/2019 | 04/18/2019 | 13 | 0 | 13 |  |  | 9/10/2019 | Connected |  | N
National Grid | WORCESTER | 667337 | 01602 | 10 | Solar | 05_01_21W1 | 01/23/2025 | 02/14/2025 | 7 | 3 | 4 | 02/18/2025 | 02/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 | 01/23/2025 | 4/24/2026 | Y | EXP | 365 | 06/13/2025 | 06/23/2025 | 11 | 0 | 11 |  |  | 6/26/2025 | Connected |  | N
National Grid | CHARLTON | 174551 | 01507 | 1500 | Solar | 05_01_304W2 | 11/16/2011 | 11/16/2011 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/17/2012 | 02/27/2012 | 28 | 0 | 28 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2012 | 11/16/2011 | 10/31/2012 | Y | STD | 62 | 08/08/2013 | 10/18/2013 | 49 | 0 | 49 | 9/24/2013 | 9/24/2013 | 10/11/2013 | Connected |  | N
National Grid | WESTMINSTER | 176661 | 01473 | 720 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/21/2016 | 06/02/2016 | 29 | 19 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 461669 | 02777 | 7.68 | Solar | 05_01_609W2 | 10/05/2022 | 10/10/2022 | 3 | 0 | 3 | 10/11/2022 | 10/11/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 | 10/05/2022 |  | Y | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 737037 | 01532 | 15.2 | Solar | 05_05_11W83 | 12/01/2025 | 12/08/2025 | 4 | 2 | 2 | 12/09/2025 | 12/09/2025 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2025 | 12/01/2025 | 1/13/2027 | Y | EXP | 365 | 01/22/2026 | 02/11/2026 | 21 | 0 | 21 |  |  | 3/3/2026 | Connected |  | N
National Grid | SALEM | 306227 | 01970 | 11.4 | Solar | 05_05_313W2 | 08/11/2020 | 08/13/2020 | 1 | 0 | 1 | 08/14/2020 | 08/14/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 |  | 8/12/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2020 | Connected |  | N
National Grid | LOWELL | 669791 | 01851 | 7.6 | Solar | 05_12_29W6 | 02/04/2025 | 03/19/2025 | 18 | 14 | 4 | 03/20/2025 | 03/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | NEWBURY | 200444 | 01985 | 201.6 | Solar | 05_14_16L3 | 11/05/2018 | 11/08/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 06/13/2019 | 06/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2019 | 11/05/2018 | 11/8/2024 | Y | EXP | 70 | 03/01/2024 | 10/08/2024 | 222 | 182 | 40 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 683265 | 01843 | 4998 | Other | 05_14_47L2 | 10/16/2025 | 12/10/2025 | 37 | 27 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 | 01/09/2026 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | DRACUT | 177202 | 01826 | 3.8 | Solar | 05_14_61L3 | 02/01/2017 | 02/01/2017 | 0 | 0 | 0 | 02/17/2017 | 02/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2017 |  | 7/31/2018 | N | EXP | 525 |  |  | 0 | 0 | 0 |  |  | 4/29/2018 | Connected |  | N
National Grid | SPENCER | 200569 | 01562 | 7.6 | Solar | 05_14_75L2 | 11/06/2018 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 689892 | 01519 | 3.8 | Solar | 05_01_21W1 | 05/06/2025 | 05/20/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 98 | 88 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 175211 | 01550 | 12.255 | Solar | 05_01_304W2 | 12/04/2012 | 12/04/2012 | 11 | 8 | 3 | 12/21/2012 | 12/21/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2013 |  | 2/28/2013 | N | EXP | 8 |  |  | 0 | 0 | 0 | 3/8/2013 | 3/8/2013 | 4/22/2013 | Connected |  | N
National Grid | WESTMINSTER | 176659 | 01473 | 936 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 473722 | 02777 | 8.99 | Solar | 05_01_609W2 | 11/23/2022 | 11/29/2022 | 3 | 1 | 2 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 | 11/23/2022 | 6/8/2024 | Y | EXP | 365 | 04/27/2023 | 06/08/2023 | 43 | 0 | 43 |  |  | 6/16/2023 | Connected |  | Y
National Grid | NORTHBOROUGH | 465846 | 01532 | 0 | Other | 05_05_11W84 | 02/17/2023 | 05/03/2023 | 51 | 43 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2023 | 06/07/2023 | 24 | 4 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 | 02/17/2023 | 9/11/2026 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SALEM | 318450 | 01970 | 15.2 | Solar | 05_05_313W2 | 10/09/2020 | 10/14/2020 | 1 | 0 | 1 | 10/15/2020 | 10/15/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2021 | Connected |  | N
National Grid | LOWELL | 674089 | 01851 | 14.82 | Solar | 05_12_29W6 | 02/25/2025 | 03/05/2025 | 7 | 4 | 3 | 03/06/2025 | 03/06/2025 | 59 | 35 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 9/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | NEWBURY | 202097 | 01950 | 3.8 | Solar | 05_14_16L3 | 11/27/2018 | 01/25/2019 | 19 | 19 | 0 | 01/28/2019 | 01/28/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 | 11/27/2018 | 11/27/2020 | Y | EXP | 365 | 07/17/2020 | 08/12/2020 | 26 | 0 | 26 |  |  | 8/17/2020 | Connected |  | N
National Grid | LAWRENCE | 738893 | 01843 | 3.49 | Solar | 05_14_47L2 | 12/15/2025 | 12/17/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 46 | 31 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 177722 | 01852 | 6 | Solar | 05_14_61L3 | 10/04/2017 | 10/04/2017 | 19 | 17 | 2 | 11/08/2017 | 11/08/2017 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2017 |  | 10/9/2018 | N | EXP | 330 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 266776 | 01562 | 6.67 | Solar | 05_14_75L2 | 11/22/2019 | 11/25/2019 | 0 | 0 | 0 | 11/26/2019 | 11/26/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 |  | 11/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2020 | Connected |  | N
National Grid | SUTTON | 691681 | 01590 | 11.4 | Solar | 05_01_21W1 | 05/14/2025 | 05/27/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 175576 | 01550 | 20 | Solar | 05_01_304W2 | 12/09/2014 | 12/09/2014 | 4 | 2 | 2 | 12/16/2014 | 12/16/2014 | 223 | 0 | 223 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2014 |  | 2/28/2015 | N | EXP | 74 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 |  | Withdrawn |  | N
National Grid | WESTMINSTER | 176693 | 01473 | 1872 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 485301 | 02777 | 11.4 | Solar | 05_01_609W2 | 12/28/2022 |  | 136 | 59 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 707245 | 01532 | 250 | Solar | 05_05_11W84 | 12/13/2025 |  | 73 | 64 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SALEM | 323644 | 01970 | 7.6 | Solar | 05_05_313W2 | 02/23/2021 | 02/24/2021 | 0 | 0 | 0 | 02/25/2021 | 02/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2021 |  | 2/23/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 657092 | 01851 | 5.76 | Solar | 05_12_2W1 | 11/26/2024 | 01/30/2025 | 2 | 0 | 2 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 | 11/26/2024 | 5/17/2026 | Y | EXP | 425 | 06/14/2025 | 09/12/2025 | 91 | 0 | 91 |  |  |  | Completion Documents |  | Y
National Grid | NEWBURY | 260377 | 01985 | 5 | Solar | 05_14_16L3 | 11/12/2019 | 11/18/2019 | 3 | 0 | 3 | 11/19/2019 | 11/19/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 | 11/12/2019 | 3/3/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2021 | Connected |  | N
National Grid | LAWRENCE | 759542 | 01843 | 5.76 | Solar | 05_14_47L2 | 03/30/2026 | 04/01/2026 | 2 | 0 | 2 | 04/02/2026 | 04/02/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 200394 | 01810 | 3.8 | Solar | 05_14_61L3 | 11/05/2018 | 12/17/2018 | 18 | 9 | 9 | 12/18/2018 | 12/18/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 273439 | 01562 | 0 | Solar | 05_14_75L2 | 01/23/2020 | 01/27/2020 | 2 | 2 | 0 | 01/28/2020 | 01/28/2020 | 33 | 29 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 | 01/23/2020 | 1/25/2021 | Y | EXP | 365 | 06/06/2020 | 06/13/2020 | 7 | 0 | 7 |  |  | 6/15/2020 | Connected |  | N
National Grid | SUTTON | 701290 | 01590 | 15.2 | Solar | 05_01_21W1 | 06/26/2025 | 07/14/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 175728 | 01550 | 1000 | Solar | 05_01_304W2 | 06/02/2014 | 06/02/2014 | 19 | 13 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/30/2014 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 176692 | 01473 | 1872 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 557260 | 02725 | 0 | Solar | 05_01_609W2 | 09/21/2023 | 10/06/2023 | 11 | 10 | 1 | 10/10/2023 | 10/10/2023 | 54 | 31 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 732923 | 01532 | 998.9 | Solar | 05_05_11W84 | 01/07/2026 | 03/24/2026 | 49 | 39 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/25/2026 |  | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 326856 | 01970 | 8.4 | Solar | 05_05_313W2 | 12/03/2020 | 12/08/2020 | 2 | 0 | 2 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2021 |  | 12/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2021 | Connected |  | N
National Grid | LOWELL | 724976 | 01851 | 6.72 | Solar | 05_12_2W1 | 10/08/2025 | 10/31/2025 | 15 | 13 | 2 | 11/03/2025 | 11/03/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 270083 | 01985 | 95.4 | Solar | 05_14_16L3 | 01/31/2020 | 01/31/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2020 |  | 12/17/2024 | N | EXP | 70 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 757015 | 01843 | 21.289 | Solar | 05_14_47L2 | 03/23/2026 | 03/26/2026 | 3 | 1 | 2 | 03/27/2026 | 03/27/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | TEWKSBURY | 202318 | 01876 | 7.6 | Solar | 05_14_61L3 | 11/28/2018 | 01/09/2019 | 7 | 0 | 7 | 01/10/2019 | 01/10/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2019 | 11/28/2018 | 11/28/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2020 | Connected |  | N
National Grid | LEICESTER | 325076 | 01524 | 7.6 | Solar | 05_14_75L2 | 12/11/2020 | 12/18/2020 | 4 | 0 | 4 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 718922 | 01519 | 18.56 | Solar | 05_01_21W1 | 09/14/2025 | 09/29/2025 | 10 | 5 | 5 | 09/30/2025 | 09/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 175727 | 01550 | 1000 | Solar | 05_01_304W2 | 06/02/2014 | 06/02/2014 | 19 | 13 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/30/2014 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 176691 | 01473 | 936 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 605267 | 02777 | 20 | Solar | 05_01_609W2 | 04/24/2024 | 05/01/2024 | 5 | 4 | 1 | 05/02/2024 | 05/02/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 742250 | 01581 | 10 | Solar | 05_05_11W84 | 12/26/2025 | 12/30/2025 | 2 | 0 | 2 | 01/26/2026 | 01/26/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 | 12/26/2025 | 2/13/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 334003 | 01970 | 10 | Solar | 05_05_313W2 | 12/30/2020 | 01/05/2021 | 2 | 0 | 2 | 01/06/2021 | 01/06/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2021 | Connected |  | N
National Grid | LOWELL | 176002 | 01851 | 8.17 | Solar | 05_12_2W1 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 | 08/11/2015 | 8/19/2016 | Y | EXP | 346 | 08/19/2016 | 09/21/2016 | 22 | 0 | 22 | 5/10/2016 | 5/10/2016 | 10/28/2016 | Connected |  | N
National Grid | NEWBURY | 270081 | 01985 | 37.8 | Solar | 05_14_16L3 | 01/31/2020 | 01/31/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2020 |  | 12/17/2024 | N | EXP | 70 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175224 | 01843 | 19 | Solar | 05_14_47L2 | 01/06/2015 | 01/06/2015 | 43 | 40 | 3 | 03/11/2015 | 03/11/2015 | 349 | 0 | 349 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2015 |  | 5/1/2015 | N | EXP | 50 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 205028 | 01852 | 7.6 | Solar | 05_14_61L3 | 01/22/2019 | 02/06/2019 | 10 | 0 | 10 | 02/07/2019 | 02/07/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 | 01/22/2019 | 10/21/2020 | Y | EXP | 365 | 04/25/2020 | 05/26/2020 | 31 | 0 | 31 |  |  | 6/18/2020 | Connected |  | N
National Grid | SPENCER | 340366 | 01562 | 15.2 | Solar | 05_14_75L2 | 02/03/2021 | 02/22/2021 | 12 | 11 | 1 | 02/23/2021 | 02/23/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2021 | Connected |  | N
National Grid | GRAFTON | 720360 | 01519 | 10 | Solar | 05_01_21W2 | 09/19/2025 | 09/25/2025 | 4 | 1 | 3 | 09/26/2025 | 09/26/2025 | 27 | 15 | 12 | 11/21/2025 | 11/20/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SOUTHBRIDGE | 176224 | 01550 | 7.6 | Solar | 05_01_304W2 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 358 | 0 | 358 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 9/12/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 176732 | 01473 | 936 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 06/02/2016 | 25 | 15 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 | 04/20/2016 | 12/31/2020 | Y | STD | 384 | 08/22/2020 | 11/25/2020 | 95 | 0 | 95 | 12/3/2020 | 12/10/2020 | 12/31/2020 | Connected |  | N
National Grid | SOMERSET | 646003 | 02725 | 5 | Solar | 05_01_609W2 | 10/10/2024 | 11/04/2024 | 5 | 0 | 5 | 11/05/2024 | 11/05/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/10/2024 | 12/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 751362 | 01532 | 11.5 | Solar | 05_05_11W84 | 02/16/2026 | 02/20/2026 | 2 | 0 | 2 | 03/09/2026 | 03/09/2026 | 18 | 6 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 375628 | 01970 | 43.2 | Solar | 05_05_313W2 | 08/18/2021 | 11/20/2021 | 65 | 57 | 8 | 11/22/2021 | 11/22/2021 | 22 | 0 | 22 | 08/05/2022 | 10/19/2022 | 52 | 0 | 52 |  |  | 0 | 0 | 0 | 10/19/2022 | 52 | 0 | 52 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 3/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | LOWELL | 176624 | 01851 | 6 | Solar | 05_12_2W1 | 04/15/2016 | 04/15/2016 | 1 | 1 | 0 | 04/20/2016 | 04/20/2016 | 198 | 0 | 198 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2016 |  | 4/24/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 379349 | 01985 | 5 | Solar | 05_14_16L3 | 10/08/2021 | 01/04/2022 | 2 | 0 | 2 | 10/14/2021 | 10/14/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 2/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2022 | Connected |  | N
National Grid | LAWRENCE | 175431 | 01843 | 354 | Solar | 05_14_47L2 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 | 09/29/2014 | 09/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 | 09/18/2014 | 6/1/2015 | Y | EXP | 208 | 10/07/2015 | 11/23/2015 | 31 | 0 | 31 | 11/5/2014 | 11/5/2014 | 11/23/2015 | Connected |  | N
National Grid | TEWKSBURY | 206502 | 01876 | 7.6 | Solar | 05_14_61L3 | 03/04/2019 | 03/12/2019 | 5 | 0 | 5 | 03/13/2019 | 03/13/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 411194 | 01507 | 9.57 | Solar | 05_14_75L2 | 03/21/2022 | 05/10/2022 | 36 | 35 | 1 | 05/11/2022 | 05/11/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 | 03/21/2022 | 8/26/2023 | Y | EXP | 365 | 08/09/2022 | 08/25/2022 | 17 | 0 | 17 |  |  | 9/15/2022 | Connected |  | N
National Grid | GRAFTON | 749805 | 01519 | 10 | Solar | 05_01_21W2 | 02/06/2026 | 02/10/2026 | 2 | 0 | 2 | 02/23/2026 | 02/23/2026 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBRIDGE | 176366 | 01550 | 10 | Solar | 05_01_304W2 | 03/09/2016 | 03/09/2016 | 3 | 3 | 0 | 03/15/2016 | 03/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2016 |  | 3/15/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N
National Grid | WESTMINSTER | 176731 | 01473 | 999 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2016 | 06/02/2016 | 26 | 15 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2017 | 04/20/2016 | 12/31/2020 | Y | STD | 889 | 08/22/2020 | 12/03/2020 | 103 | 0 | 103 | 12/14/2020 | 12/16/2020 | 12/30/2020 | Connected |  | N
National Grid | SWANSEA | 656341 | 02777 | 10 | Solar | 05_01_609W2 | 11/22/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 751305 | 01581 | 10 | Solar | 05_05_11W84 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 30 | 19 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 380928 | 01970 | 0 | Solar | 05_05_313W2 | 09/27/2021 | 12/16/2021 | 2 | 0 | 2 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 177088 | 01851 | 432.6 | Solar | 05_12_2W1 | 01/18/2017 | 01/18/2017 | 2 | 0 | 2 | 01/23/2017 | 01/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2017 |  | 1/24/2018 | N | EXP | 337 |  |  | 0 | 0 | 0 | 8/8/2017 | 8/8/2017 | 8/8/2017 | Connected |  | N
National Grid | NEWBURY | 405329 | 01985 | 150 | Solar | 05_14_16L3 | 02/16/2022 | 04/04/2022 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 | 02/16/2022 | 10/26/2024 | Y | STD | 98 | 07/09/2024 | 02/13/2025 | 220 | 19 | 201 |  |  | 10/21/2024 | Connected |  | N
National Grid | LAWRENCE | 175784 | 01843 | 14 | Solar | 05_14_47L2 | 07/24/2015 | 07/24/2015 | 0 | 0 | 0 | 09/25/2015 | 09/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2015 |  | 8/1/2016 | N | EXP | 244 |  |  | 0 | 0 | 0 | 12/19/2017 | 12/19/2017 | 9/25/2017 | Connected |  | N
National Grid | TEWKSBURY | 213800 | 01876 | 6 | Solar | 05_14_61L3 | 04/02/2019 | 04/10/2019 | 6 | 6 | 0 | 04/11/2019 | 04/11/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2019 | 04/02/2019 | 7/30/2019 | Y | EXP | 105 | 07/09/2019 | 07/16/2019 | 7 | 0 | 7 |  |  | 7/18/2019 | Connected |  | N
National Grid | LEICESTER | 420643 | 01524 | 0 | Battery Add-On | 05_14_75L2 | 08/10/2022 | 08/26/2022 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2022 | 09/23/2022 | 19 | 2 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 757961 | 01560 | 7.6 | Solar | 05_01_21W2 | 03/20/2026 | 03/25/2026 | 3 | 0 | 3 | 03/26/2026 | 03/26/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBRIDGE | 176400 | 01550 | 7.6 | Solar | 05_01_304W2 | 03/11/2016 | 03/11/2016 | 3 | 3 | 0 | 03/18/2016 | 03/18/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 |  | 3/19/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 9/1/2016 | 9/1/2016 | 9/1/2016 | Connected |  | N
National Grid | WESTMINSTER | 176767 | 01473 | 936 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 06/02/2016 | 25 | 15 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2019 | 04/20/2016 | 12/18/2020 | Y | STD | 461 | 07/08/2020 | 10/14/2020 | 99 | 5 | 94 |  |  | 12/16/2020 | Connected |  | N
National Grid | SWANSEA | 666877 | 02777 | 7.6 | Solar | 05_01_609W2 | 01/21/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 754208 | 01532 | 5.76 | Solar | 05_05_11W84 | 03/03/2026 | 03/05/2026 | 3 | 0 | 3 | 03/19/2026 | 03/19/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 478391 | 01970 | 0 | Other | 05_05_313W2 | 12/02/2022 | 04/07/2023 | 75 | 75 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/10/2023 | 10/26/2023 | 138 | 119 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 177135 | 01851 | 3.8 | Solar | 05_12_2W1 | 01/24/2017 | 01/24/2017 | 3 | 2 | 1 | 01/27/2017 | 01/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2017 |  | 1/29/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 1/11/2018 | 1/11/2018 | 1/11/2018 | Connected |  | N
National Grid | NEWBURY | 513162 | 01985 | 5.67 | Solar | 05_14_16L3 | 04/13/2023 | 04/19/2023 | 3 | 1 | 2 | 04/20/2023 | 04/20/2023 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2023 | 04/13/2023 | 6/9/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2023 | Connected |  | N
National Grid | LAWRENCE | 177603 | 01843 | 12 | Solar | 05_14_47L2 | 07/19/2017 | 07/19/2017 | 11 | 11 | 0 | 08/03/2017 | 08/03/2017 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2017 |  | 7/24/2018 | N | EXP | 354 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 240228 | 01752 | 10 | Solar | 05_14_61L3 | 10/23/2019 | 10/30/2019 | 4 | 0 | 4 | 10/31/2019 | 10/31/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 |  | 10/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 465832 | 01611 | 14.5 | Solar | 05_14_75L2 | 10/20/2022 | 10/31/2022 | 7 | 6 | 1 | 11/01/2022 | 11/01/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2022 | 10/20/2022 | 1/24/2024 | Y | EXP | 365 | 03/22/2023 | 04/05/2023 | 15 | 0 | 15 |  |  | 6/30/2023 | Connected |  | N
National Grid | SUTTON | 174330 | 01590 | 14.28 | Solar | 05_01_21W2 | 01/17/2012 | 01/17/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2012 |  | 2/20/2012 | N | EXP | 46 |  |  | 0 | 0 | 0 | 4/30/2012 | 4/30/2012 | 7/18/2012 | Connected |  | N
National Grid | SOUTHBRIDGE | 176463 | 01550 | 7.6 | Solar | 05_01_304W2 | 02/04/2016 | 02/04/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/13/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 5/9/2016 | 5/9/2016 | 5/12/2016 | Connected |  | N
National Grid | WESTMINSTER | 176766 | 01473 | 1872 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 06/02/2016 | 25 | 15 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/2/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 673174 | 02777 | 10 | Solar | 05_01_609W2 | 03/13/2025 | 03/19/2025 | 4 | 0 | 4 | 03/20/2025 | 03/20/2025 | 97 | 57 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 756195 | 01752 | 11.5 | Solar | 05_05_11W84 | 03/12/2026 | 03/20/2026 | 3 | 0 | 3 | 04/02/2026 | 04/02/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 548448 | 01970 | 10 | Solar | 05_05_313W2 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 |  | 10/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N
National Grid | LOWELL | 177151 | 01851 | 5.2 | Solar | 05_12_2W1 | 08/11/2016 | 08/11/2016 | 3 | 3 | 0 | 08/16/2016 | 08/16/2016 | 203 | 0 | 203 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 |  | 8/16/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 556991 | 01950 | 80 | Solar | 05_14_16L3 | 09/21/2023 | 10/12/2023 | 14 | 3 | 11 |  |  | 93 | 72 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 178075 | 01843 | 3375 | Solar | 05_14_47L2 | 11/03/2017 | 11/03/2017 | 24 | 19 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/09/2018 | 18 | 4 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/8/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 248995 | 01876 | 250 | Solar | 05_14_61L3 | 08/15/2019 | 08/30/2019 | 10 | 2 | 8 | 09/03/2019 | 09/03/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2019 |  | 9/23/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2020 | Connected |  | N
National Grid | LEICESTER | 472086 | 01524 | 15.2 | Solar | 05_14_75L2 | 10/28/2022 | 10/31/2022 | 1 | 0 | 1 | 11/01/2022 | 11/01/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2022 |  | 12/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2023 | Connected |  | Y
National Grid | GRAFTON | 174430 | 01560 | 3000 | Solar | 05_01_21W2 | 11/18/2011 | 11/18/2011 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 176489 | 01550 | 7.6 | Solar | 05_01_304W2 | 12/09/2015 | 12/09/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2015 |  | 12/14/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 9/1/2016 | 9/1/2016 | 9/1/2016 | Connected |  | N
National Grid | WESTMINSTER | 177502 | 01473 | 2000 |  | 05_01_413L4 | 03/06/2017 | 03/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 691407 | 02777 | 11.4 | Solar | 05_01_609W2 | 06/03/2025 | 06/10/2025 | 5 | 0 | 5 | 06/11/2025 | 06/11/2025 | 78 | 55 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 174266 | 01532 | 26 | Solar | 05_05_11W84 | 12/28/2011 | 12/28/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2012 |  | 2/25/2012 | N | EXP | 47 |  |  | 0 | 0 | 0 | 5/8/2012 | 5/8/2012 | 5/16/2012 | Connected |  | N
National Grid | SALEM | 571722 | 01970 | 10 | Solar | 05_05_313W2 | 11/21/2023 | 12/11/2023 | 14 | 11 | 3 | 12/12/2023 | 12/12/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | LOWELL | 186237 | 01851 | 3.8 | Solar | 05_12_2W1 | 05/24/2018 | 05/24/2018 | 2 | 0 | 2 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 556253 | 01985 | 0 | Battery Add-On | 05_14_16L3 | 09/18/2023 | 10/06/2023 | 15 | 14 | 1 | 10/10/2023 | 10/10/2023 | 86 | 69 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 2/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | LAWRENCE | 178312 | 01843 | 7.6 | Solar | 05_14_47L2 | 02/26/2018 | 02/26/2018 | 4 | 4 | 0 | 03/05/2018 | 03/05/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2018 |  | 3/3/2019 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  | 10/11/2019 | Connected |  | N
National Grid | DRACUT | 256506 | 01826 | 7.6 | Solar | 05_14_61L3 | 10/17/2019 | 10/23/2019 | 3 | 0 | 3 | 10/24/2019 | 10/24/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 524377 | 01524 | 7.6 | Solar | 05_14_75L2 | 05/15/2023 | 05/18/2023 | 3 | 0 | 3 | 05/19/2023 | 05/19/2023 | 23 | 0 | 23 | 06/26/2023 | 07/31/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 07/31/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 7/18/2023 |  | 11/29/2024 | N | EXP | 365 | 11/04/2023 | 12/13/2023 | 40 | 0 | 40 |  |  | 12/28/2023 | Connected |  | Y
National Grid | GRAFTON | 174428 | 01560 | 4883 | Solar | 05_01_21W2 | 11/18/2011 | 11/18/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 03/18/2014 | 03/18/2014 | 0 | 0 | 0 | 3/14/2012 | 11/18/2011 | 6/1/2014 | Y | STD | 809 |  |  | 0 | 0 | 0 | 1/23/2015 | 1/23/2015 | 1/29/2015 | Connected |  | N
National Grid | SOUTHBRIDGE | 176514 | 01550 | 10 | Solar | 05_01_304W2 | 10/01/2015 | 10/01/2015 | 1 | 1 | 0 | 10/06/2015 | 10/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2015 |  | 10/10/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 4/20/2016 | 4/20/2016 | 4/27/2016 | Connected |  | N
National Grid | WESTMINSTER | 178044 | 01473 | 4900 | Solar | 05_01_413L4 | 05/04/2017 | 05/04/2017 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2017 | 06/02/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/10/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 697495 | 02725 | 11.4 | Solar | 05_01_609W2 | 06/10/2025 | 06/24/2025 | 1 | 0 | 1 | 07/29/2025 | 07/29/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/10/2025 | 8/11/2026 | Y | EXP | 365 | 10/22/2025 | 12/18/2025 | 58 | 0 | 58 |  |  | 11/26/2025 | Connected |  | N
National Grid | WESTBOROUGH | 174457 | 01581 | 623 | Solar | 05_05_11W84 | 10/13/2011 | 10/13/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2011 | 12/01/2011 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2011 | 10/13/2011 | 10/31/2012 | Y | STD | 330 |  |  | 0 | 0 | 0 | 5/30/2013 | 5/30/2013 | 6/13/2013 | Connected |  | N
National Grid | SALEM | 574880 | 01970 | 0 | Solar | 05_05_313W2 | 11/30/2023 | 12/12/2023 | 9 | 6 | 3 | 12/13/2023 | 12/13/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 186574 | 01851 | 3.8 | Solar | 05_12_2W1 | 06/22/2018 | 06/22/2018 | 2 | 1 | 1 | 06/27/2018 | 06/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 558659 | 01985 | 200 | Solar | 05_14_16L3 | 10/05/2023 | 10/23/2023 | 12 | 2 | 10 |  |  | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 178352 | 01843 | 10 | Solar | 05_14_47L2 | 02/27/2018 | 02/27/2018 | 2 | 2 | 0 | 03/13/2018 | 03/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 |  | 3/5/2019 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 10/15/2019 | Connected |  | N
National Grid | LOWELL | 278404 | 01852 | 5.76 | Solar | 05_14_61L3 | 04/21/2021 | 04/28/2021 | 4 | 0 | 4 | 04/29/2021 | 04/29/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 12/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2022 | Connected |  | N
National Grid | LEICESTER | 569622 | 01524 | 6 | Solar | 05_14_75L2 | 11/20/2023 | 11/30/2023 | 8 | 4 | 4 | 12/01/2023 | 12/01/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 175244 | 01560 | 684 | Solar | 05_01_21W2 | 08/27/2014 | 08/27/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/09/2014 | 10/06/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2015 | 08/27/2014 | 6/30/2016 | Y | STD | 422 | 02/19/2016 | 06/28/2016 | 88 | 0 | 88 | 6/22/2016 | 6/22/2016 | 6/29/2016 | Connected |  | N
National Grid | CHARLTON | 176877 | 01507 | 995 | Solar | 05_01_304W2 | 05/04/2016 | 05/04/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/13/2016 | 06/20/2016 | 24 | 11 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 |  | 9/1/2018 | N | STD | 680 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 198216 | 01473 | 3000 | Solar | 05_01_413L4 | 08/13/2020 | 10/15/2020 | 42 | 40 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2020 | 11/10/2020 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/13/2020 | 2/16/2025 | Y | STD | 700 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 487743 | 02725 | 0 | Other | 05_01_610W3 | 04/26/2023 | 05/08/2023 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2023 | 05/31/2023 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTHBOROUGH | 174647 | 01532 | 3000 | Solar | 05_05_11W84 | 12/17/2013 | 12/17/2013 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2014 | 02/07/2014 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2014 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 644993 | 01970 | 8.7 | Solar | 05_05_313W2 | 10/04/2024 | 10/24/2024 | 3 | 1 | 2 | 10/25/2024 | 10/25/2024 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2025 | Connected |  | N
National Grid | LOWELL | 187385 | 01851 | 3.8 | Solar | 05_12_2W1 | 06/22/2018 | 06/22/2018 | 7 | 4 | 3 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 592199 | 01985 | 7.6 | Solar | 05_14_16L3 | 02/27/2024 | 03/05/2024 | 5 | 0 | 5 | 03/06/2024 | 03/06/2024 | 4 | 2 | 2 | 03/29/2024 | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 198160 | 01843 | 7.6 | Solar | 05_14_47L2 | 11/16/2018 | 11/19/2018 | 0 | 0 | 0 | 11/20/2018 | 11/20/2018 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 293829 | 01826 | 3.8 | Solar | 05_14_61L3 | 06/08/2020 | 06/10/2020 | 1 | 0 | 1 | 06/11/2020 | 06/11/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 06/08/2020 | 11/11/2021 | Y | EXP | 365 | 11/18/2020 | 12/09/2020 | 21 | 0 | 21 |  |  | 8/6/2021 | Connected |  | N
National Grid | LEICESTER | 569134 | 01524 | 6 | Solar | 05_14_75L2 | 11/10/2023 | 11/27/2023 | 10 | 4 | 6 | 11/28/2023 | 11/28/2023 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 175336 | 01519 | 1000 | Solar | 05_01_21W2 | 01/17/2015 | 01/17/2015 | 38 | 38 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2015 | 04/13/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 | 04/07/2016 | 12/22/2016 | 177 | 0 | 177 |  |  | 11/1/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 184400 | 01550 | 6 | Solar | 05_01_304W2 | 05/11/2018 | 05/11/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 265989 | 01473 | 0 | Other | 05_01_413L4 | 02/27/2020 | 03/17/2020 | 13 | 7 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2020 | 04/02/2020 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/27/2020 |  | Y | STD | 665 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 629414 | 02726 | 4980 | Solar | 05_01_610W3 | 10/02/2024 | 12/05/2024 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/06/2024 | 02/10/2025 | 44 | 25 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTBOROUGH | 174646 | 01581 | 3000 | Solar | 05_05_11W84 | 12/17/2013 | 12/17/2013 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2014 | 02/07/2014 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 12/17/2013 | 6/30/2014 | Y | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 666566 | 01970 | 3.8 | Solar | 05_05_313W2 | 01/17/2025 | 03/20/2025 | 10 | 6 | 4 | 03/21/2025 | 03/21/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | LOWELL | 188870 | 01851 | 3.8 | Solar | 05_12_2W1 | 06/21/2018 | 06/21/2018 | 3 | 0 | 3 | 07/27/2018 | 07/27/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 598082 | 01950 | 3.8 | Solar | 05_14_16L3 | 03/21/2024 | 03/26/2024 | 3 | 0 | 3 | 03/27/2024 | 03/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 198970 | 01843 | 7.6 | Solar | 05_14_47L2 | 12/21/2018 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 296132 | 01826 | 5.04 | Solar | 05_14_61L3 | 07/02/2020 | 07/07/2020 | 2 | 0 | 2 | 07/08/2020 | 07/08/2020 | 71 | 50 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2020 |  | 10/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 585135 | 01524 | 10 | Solar | 05_14_75L2 | 01/26/2024 | 02/13/2024 | 12 | 11 | 1 | 02/14/2024 | 02/14/2024 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 01/26/2024 | 3/1/2025 | Y | EXP | 365 | 04/23/2024 | 06/27/2024 | 66 | 0 | 66 |  |  | 6/29/2024 | Connected |  | N
National Grid | SUTTON | 175335 | 01590 | 800 | Solar | 05_01_21W2 | 01/17/2015 | 01/17/2015 | 40 | 40 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2015 | 04/13/2015 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 185479 | 01507 | 5 | Solar | 05_01_304W2 | 06/26/2018 | 06/26/2018 | 11 | 7 | 4 | 07/13/2018 | 07/13/2018 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 |  | 7/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2019 | Connected |  | N
National Grid | WESTMINSTER | 281257 | 01473 | 0 | Other | 05_01_413L4 | 03/17/2020 | 04/24/2020 | 27 | 27 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/09/2020 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/17/2020 | 3/5/2025 | Y | STD | 665 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 667321 | 02726 | 7.6 | Solar | 05_01_610W3 | 01/22/2025 | 02/25/2025 | 3 | 0 | 3 | 02/06/2025 | 02/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 | 01/22/2025 | 6/4/2026 | Y | EXP | 365 | 03/25/2026 |  | 8 | 0 | 8 |  |  |  | Construction |  | Y
National Grid | NORTHBOROUGH | 174875 | 01532 | 3000 | Solar | 05_05_11W84 | 09/11/2012 | 09/11/2012 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2012 | 12/24/2012 | 45 | 0 | 45 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/14/2014 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 708079 | 01970 | 11.05 | Solar | 05_05_313W2 | 08/12/2025 | 08/13/2025 | 1 | 0 | 1 | 08/14/2025 | 08/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | LOWELL | 192482 | 01851 | 7.6 | Solar | 05_12_2W1 | 08/01/2018 | 10/01/2018 | 22 | 22 | 0 | 10/02/2018 | 10/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2018 | 08/01/2018 | 4/22/2020 | Y | EXP | 568 | 11/15/2019 | 12/23/2019 | 38 | 0 | 38 |  |  | 1/6/2020 | Connected |  | N
National Grid | NEWBURY | 598212 | 01950 | 3.8 | Solar | 05_14_16L3 | 03/21/2024 | 03/26/2024 | 3 | 0 | 3 | 03/27/2024 | 03/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 199289 | 01843 | 7.6 | Solar | 05_14_47L2 | 10/24/2018 | 12/20/2018 | 20 | 19 | 1 | 12/21/2018 | 12/21/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 | 10/24/2018 | 12/20/2019 | Y | EXP | 365 | 10/17/2019 | 10/25/2019 | 8 | 0 | 8 |  |  | 11/15/2019 | Connected |  | N
National Grid | DRACUT | 302207 | 01826 | 7.6 | Solar | 05_14_61L3 | 08/19/2020 | 08/26/2020 | 4 | 0 | 4 | 08/27/2020 | 08/27/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2021 | Connected |  | N
National Grid | LEICESTER | 611949 | 01524 | 3.8 | Solar | 05_14_75L2 | 05/17/2024 | 05/23/2024 | 1 | 0 | 1 | 05/24/2024 | 05/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2024 | Connected |  | N
National Grid | GRAFTON | 175334 | 01519 | 800 | Solar | 05_01_21W2 | 01/17/2015 | 01/17/2015 | 40 | 40 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2015 | 04/13/2015 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 185476 | 01507 | 6 | Solar | 05_01_304W2 | 06/26/2018 | 06/26/2018 | 5 | 2 | 3 | 07/05/2018 | 07/05/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 | 06/26/2018 | 7/1/2019 | Y | EXP | 343 | 04/10/2019 | 04/18/2019 | 8 | 0 | 8 |  |  | 6/20/2019 | Connected |  | N
National Grid | WESTMINSTER | 280097 | 01473 | 8.64 | Solar | 05_01_413L4 | 02/19/2020 | 02/25/2020 | 3 | 0 | 3 | 02/26/2020 | 02/26/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2020 | 02/19/2020 | 2/3/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2021 | Connected |  | N
National Grid | SWANSEA | 739544 | 02777 | 15.2 | Solar | 05_01_610W3 | 12/11/2025 | 12/16/2025 | 3 | 0 | 3 | 12/17/2025 | 12/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 | 12/11/2025 | 1/29/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTHBOROUGH | 175105 | 01532 | 400 | Solar | 05_05_11W84 | 04/08/2013 | 04/08/2013 | 7 | 2 | 5 | 04/22/2013 | 04/22/2013 | 361 | 0 | 361 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2013 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 711406 | 01970 | 5.76 | Solar | 05_05_313W2 | 08/13/2025 | 08/26/2025 | 11 | 7 | 4 | 09/16/2025 | 09/16/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 | 08/13/2025 | 11/6/2026 | Y | EXP | 365 | 12/16/2025 | 12/15/2025 | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | LOWELL | 203384 | 01851 | 10 | Solar | 05_12_2W1 | 02/21/2019 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 623126 | 01950 | 5.76 | Solar | 05_14_16L3 | 07/08/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 15 | 0 | 15 | 08/21/2024 | 09/17/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 09/17/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 9/23/2024 |  | 9/27/2025 | N | EXP | 365 | 09/28/2024 | 02/07/2025 | 133 | 0 | 133 |  |  | 3/12/2025 | Connected |  | N
National Grid | LAWRENCE | 201008 | 01843 | 10 | Solar | 05_14_47L2 | 03/06/2019 | 03/18/2019 | 7 | 0 | 7 | 03/19/2019 | 03/19/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 | 03/06/2019 | 4/3/2020 | Y | EXP | 365 | 09/06/2019 | 09/23/2019 | 17 | 0 | 17 |  |  | 10/25/2019 | Connected |  | N
National Grid | DRACUT | 317759 | 01826 | 7.6 | Solar | 05_14_61L3 | 10/29/2020 | 11/02/2020 | 1 | 0 | 1 | 11/03/2020 | 11/03/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 | 10/29/2020 |  | Y | EXP | 365 | 04/17/2021 | 09/01/2021 | 136 | 3 | 133 |  |  | 9/8/2021 | Connected |  | N
National Grid | LEICESTER | 645072 | 01524 | 7.6 | Solar | 05_14_75L2 | 10/04/2024 | 10/15/2024 | 2 | 0 | 2 | 10/16/2024 | 10/16/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 175641 | 01519 | 16 | Solar | 05_01_21W2 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2014 | 10/21/2014 | 12/31/2016 | Y | EXP | 768 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 10/20/2016 | Connected |  | N
National Grid | CHARLTON | 190346 | 01507 | 10 | Solar | 05_01_304W2 | 07/10/2018 | 08/28/2018 | 19 | 0 | 19 | 08/29/2018 | 08/29/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 282050 | 01473 | 4950 | Other | 05_01_413L4 | 05/15/2020 | 05/22/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2020 | 06/18/2020 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 743645 | 02777 | 11.4 | Solar | 05_01_610W3 | 01/06/2026 | 01/09/2026 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 49 | 31 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2026 |  | 3/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 175127 | 01532 | 1760 | Solar | 05_05_11W84 | 08/20/2012 | 08/20/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2012 | 12/24/2012 | 63 | 0 | 63 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/28/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 718595 | 01970 | 9.75 | Solar | 05_05_313W2 | 09/11/2025 | 11/17/2025 | 19 | 17 | 2 | 11/18/2025 | 11/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | LOWELL | 223128 | 01851 | 120 | Solar | 05_12_2W1 | 04/27/2019 | 05/21/2019 | 17 | 17 | 0 | 05/22/2019 | 05/22/2019 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 |  | 8/13/2021 | N | EXP | 720 |  |  | 0 | 0 | 0 |  |  | 8/19/2021 | Connected |  | N
National Grid | NEWBURY | 644209 | 01950 | 5.76 | Solar | 05_14_16L3 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/01/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | LAWRENCE | 207035 | 01843 | 7.6 | Solar | 05_14_47L2 | 02/10/2019 | 03/20/2019 | 26 | 26 | 0 | 03/21/2019 | 03/21/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 321550 | 01876 | 3.6 | Solar | 05_14_61L3 | 11/09/2020 | 11/12/2020 | 1 | 0 | 1 | 11/13/2020 | 11/13/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/09/2020 | 12/21/2021 | Y | EXP | 365 | 08/06/2021 | 10/11/2021 | 60 | 3 | 57 |  |  | 10/21/2021 | Connected |  | N
National Grid | LEICESTER | 671138 | 01524 | 10 | Solar | 05_14_75L2 | 02/10/2025 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 81 | 62 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | GRAFTON | 176144 | 01519 | 17.6 | Solar | 05_01_21W2 | 06/29/2015 | 06/29/2015 | 6 | 6 | 0 | 07/10/2015 | 07/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 | 06/29/2015 | 7/6/2016 | Y | EXP | 344 | 02/08/2017 | 02/22/2017 | 9 | 0 | 9 | 7/28/2015 | 7/28/2015 | 3/20/2017 | Connected |  | N
National Grid | CHARLTON | 287978 | 01507 | 7.6 | Solar | 05_01_304W2 | 04/15/2020 | 05/06/2020 | 11 | 9 | 2 | 05/07/2020 | 05/07/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 |  | 4/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2020 | Connected |  | N
National Grid | WESTMINSTER | 416620 | 01473 | 10 | Solar | 05_01_413L4 | 03/14/2022 | 03/15/2022 | 1 | 0 | 1 | 03/16/2022 | 03/16/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2022 | 03/14/2022 | 1/18/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2023 | Connected |  | N
National Grid | SWANSEA | 174375 | 02777 | 600 | Solar | 05_01_610W3 | 05/29/2012 | 05/29/2012 | 11 | 0 | 11 | 06/18/2012 | 06/18/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 05/29/2012 | 12/31/2016 | Y | EXP | 1388 | 10/01/2015 | 10/09/2015 | 6 | 0 | 6 | 6/3/2012 | 6/3/2012 | 12/24/2015 | Connected |  | N
National Grid | WESTBOROUGH | 175126 | 01581 | 1656 | Solar | 05_05_11W84 | 08/20/2012 | 08/20/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2012 | 12/24/2012 | 63 | 0 | 63 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2013 | 08/20/2012 | 9/8/2017 | Y | STD | 1456 | 03/14/2017 | 08/29/2017 | 117 | 0 | 117 | 8/29/2017 | 8/29/2017 | 8/31/2017 | Connected |  | N
National Grid | SALEM | 553649 | 01970 | 160 | Solar | 05_05_313W3 | 09/11/2023 | 09/29/2023 | 14 | 5 | 9 | 10/02/2023 | 10/02/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 | 09/11/2023 | 5/22/2027 | Y | EXP | 217 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | LOWELL | 235959 | 01851 | 3.8 | Solar | 05_12_2W1 | 07/22/2019 | 07/25/2019 | 3 | 3 | 0 | 07/26/2019 | 07/26/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2019 |  | 8/4/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2020 | Connected |  | N
National Grid | NEWBURY | 644966 | 01950 | 7.6 | Solar | 05_14_16L3 | 10/04/2024 | 11/11/2024 | 12 | 7 | 5 | 11/12/2024 | 11/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/04/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | LAWRENCE | 213962 | 01843 | 0 | Solar | 05_14_47L2 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  | 4/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | DRACUT | 320644 | 01826 | 3.8 | Solar | 05_14_61L3 | 11/03/2020 | 11/05/2020 | 1 | 0 | 1 | 11/06/2020 | 11/06/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 672050 | 01524 | 7.6 | Solar | 05_14_75L2 | 02/13/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 176183 | 01590 | 517 | Solar | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2016 | N | STD | 0 | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 322290 | 01550 | 7.6 | Solar | 05_01_304W2 | 02/03/2021 | 03/26/2021 | 35 | 34 | 1 | 03/29/2021 | 03/29/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2021 |  | 3/25/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 560222 | 01473 | 7.749 | Solar | 05_01_413L4 | 11/01/2023 | 11/07/2023 | 5 | 2 | 3 | 11/08/2023 | 11/08/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 | 11/01/2023 | 2/3/2025 | Y | EXP | 365 | 04/18/2024 | 05/29/2024 | 42 | 0 | 42 |  |  | 7/4/2024 | Connected |  | N
National Grid | SWANSEA | 175446 | 02777 | 450 | Solar | 05_01_610W3 | 03/10/2014 | 03/10/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2014 | 04/09/2014 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2014 | 03/10/2014 | 6/9/2016 | Y | STD | 546 | 06/20/2016 | 09/08/2016 | 56 | 0 | 56 |  |  | 9/27/2016 | Connected |  | N
National Grid | NORTHBOROUGH | 175229 | 01532 | 483 | Solar | 05_05_11W84 | 01/07/2015 | 01/07/2015 | 14 | 12 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2015 | 02/27/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2015 |  | 5/31/2015 | N | STD | 36 |  |  | 0 | 0 | 0 | 7/6/2015 | 7/6/2015 | 2/1/2016 | Connected |  | N
National Grid | SALEM | 740091 | 01970 | 360 | Solar | 05_05_313W3 | 03/14/2026 |  | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LOWELL | 256763 | 01851 | 5 | Solar | 05_12_2W1 | 10/14/2019 | 10/21/2019 | 4 | 0 | 4 | 10/22/2019 | 10/22/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 | 10/14/2019 | 10/14/2020 | Y | EXP | 365 | 06/10/2020 | 06/22/2020 | 12 | 0 | 12 |  |  | 7/6/2020 | Connected |  | N
National Grid | NEWBURY | 649171 | 01985 | 8.7 | Solar | 05_14_16L3 | 10/25/2024 | 11/04/2024 | 3 | 0 | 3 | 11/05/2024 | 11/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 | 10/25/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | LAWRENCE | 223680 | 01843 | 7 | Solar | 05_14_47L2 | 04/30/2019 | 09/11/2019 | 40 | 36 | 4 | 09/12/2019 | 09/12/2019 | 26 | 20 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2019 |  | 9/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2020 | Connected |  | N
National Grid | DRACUT | 342956 | 01826 | 11.4 | Solar | 05_14_61L3 | 02/18/2021 | 02/19/2021 | 0 | 0 | 0 | 02/22/2021 | 02/22/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 | 02/18/2021 | 2/18/2022 | Y | EXP | 365 | 05/26/2021 | 07/08/2021 | 43 | 0 | 43 |  |  | 8/13/2021 | Connected |  | N
National Grid | LEICESTER | 466563 | 01524 | 600 | Other | 05_14_75L3 | 04/27/2023 | 06/29/2023 | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2023 | 07/28/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 04/27/2023 | 10/25/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | GRAFTON | 176182 | 01519 | 499 | Solar | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2016 | N | STD | 0 | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 324435 | 01550 | 7.6 | Solar | 05_01_304W2 | 11/19/2020 | 11/24/2020 | 2 | 0 | 2 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 548793 | 01473 | 15 | Solar | 05_01_413L4 | 08/18/2023 | 08/21/2023 | 1 | 0 | 1 | 08/22/2023 | 08/22/2023 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2023 | 08/18/2023 | 10/22/2024 | Y | EXP | 365 | 12/08/2023 | 01/24/2024 | 48 | 3 | 45 |  |  | 2/3/2024 | Connected |  | N
National Grid | SWANSEA | 175731 | 02777 | 499 | Solar | 05_01_610W3 | 06/03/2014 | 06/03/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2014 | 06/27/2014 | 10 | 4 | 6 |  | 0 | 0 | 0 | 03/18/2016 | 03/15/2016 | 0 | 0 | 0 | 8/15/2016 | 06/03/2014 | 10/15/2018 | Y | STD | 791 |  |  | 0 | 0 | 0 | 9/7/2018 | 9/13/2018 | 10/5/2018 | Connected |  | N
National Grid | NORTHBOROUGH | 175247 | 01532 | 999 | Solar | 05_05_11W84 | 11/04/2014 | 11/04/2014 | 21 | 19 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/08/2014 | 01/05/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2015 | N | STD | 0 | 03/14/2017 | 08/29/2017 | 117 | 0 | 117 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 174179 | 01970 | 54 | Solar | 05_05_313W3 | 03/06/2012 | 03/06/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2012 |  | 8/1/2012 | N | EXP | 54 |  |  | 0 | 0 | 0 | 6/8/2012 | 6/8/2012 | 10/2/2012 | Connected |  | N
National Grid | LOWELL | 263264 | 01851 | 6 | Solar | 05_12_2W1 | 12/05/2019 | 12/15/2019 | 6 | 0 | 6 | 12/16/2019 | 12/16/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/05/2019 | 12/5/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2020 | Connected |  | N
National Grid | NEWBURY | 649125 | 01985 | 10 | Solar | 05_14_16L3 | 10/23/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | ANDOVER | 248584 | 01810 | 10 | Solar | 05_14_47L2 | 08/14/2019 | 08/14/2019 | 0 | 0 | 0 | 08/15/2019 | 08/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 10/21/2019 | N | EXP | 62 |  |  | 0 | 0 | 0 |  |  | 10/2/2019 | Connected |  | N
National Grid | DRACUT | 449817 | 01826 | 9.45 | Solar | 05_14_61L3 | 08/09/2022 | 08/12/2022 | 3 | 0 | 3 | 08/15/2022 | 08/15/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2022 | 08/09/2022 | 2/24/2024 | Y | EXP | 365 | 01/24/2023 | 02/07/2023 | 15 | 0 | 15 |  |  | 6/8/2023 | Connected |  | N
National Grid | LEICESTER | 748927 | 01524 | 17.3 | Solar | 05_14_75L3 | 02/05/2026 | 02/24/2026 | 12 | 2 | 10 | 02/25/2026 | 02/25/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | GRAFTON | 176181 | 01519 | 2886 | Solar | 05_01_21W2 | 07/06/2015 | 07/06/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 08/09/2016 | 10/06/2016 | 41 | 0 | 41 | 3/10/2017 | 07/06/2015 | 7/11/2018 | Y | STD | 488 | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 | 3/30/2018 | 3/30/2018 | 4/5/2018 | Connected |  | N
National Grid | SOUTHBRIDGE | 332953 | 01550 | 7.6 | Solar | 05_01_304W2 | 12/18/2020 | 01/07/2021 | 12 | 11 | 1 | 01/08/2021 | 01/08/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 7/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2022 | Connected |  | N
National Grid | WESTMINSTER | 555308 | 01473 | 5 | Solar | 05_01_413L4 | 10/10/2023 | 10/11/2023 | 1 | 0 | 1 | 10/12/2023 | 10/12/2023 | 93 | 70 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | SWANSEA | 175730 | 02777 | 1000 | Solar | 05_01_610W3 | 06/03/2014 | 06/03/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2014 | 06/27/2014 | 10 | 4 | 6 |  | 0 | 0 | 0 | 03/18/2016 | 03/15/2016 | 0 | 0 | 0 | 8/15/2016 | 06/03/2014 | 10/15/2018 | Y | STD | 791 |  |  | 0 | 0 | 0 | 9/7/2018 | 9/13/2018 | 10/5/2018 | Connected |  | N
National Grid | NORTHBOROUGH | 175392 | 01532 | 19.13 | Solar | 05_05_11W84 | 09/15/2014 | 09/15/2014 | 13 | 5 | 8 | 10/03/2014 | 10/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2014 |  | 11/28/2014 | N | EXP | 49 |  |  | 0 | 0 | 0 | 6/16/2015 | 6/16/2015 | 11/20/2015 | Connected |  | N
National Grid | SALEM | 174194 | 01970 | 22.5 | Solar | 05_05_313W3 | 03/19/2012 | 03/19/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2012 |  | 6/4/2012 | N | EXP | 10 |  |  | 0 | 0 | 0 | 6/12/2012 | 6/12/2012 | 7/25/2012 | Connected |  | N
National Grid | LOWELL | 266036 | 01851 | 7.6 | Solar | 05_12_2W1 | 09/24/2020 | 09/25/2020 | 0 | 0 | 0 | 09/28/2020 | 09/28/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 | 09/24/2020 | 10/15/2021 | Y | EXP | 0 | 02/05/2021 | 03/17/2021 | 40 | 0 | 40 |  |  | 3/20/2021 | Connected |  | N
National Grid | NEWBURY | 652993 | 01985 | 3.84 | Solar | 05_14_16L3 | 11/08/2024 | 11/13/2024 | 2 | 0 | 2 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 283910 | 01843 | 10 | Solar | 05_14_47L2 | 03/17/2020 | 04/01/2020 | 10 | 7 | 3 | 04/02/2020 | 04/02/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2020 | Connected |  | Y
National Grid | DRACUT | 450807 | 01826 | 5 | Solar | 05_14_61L3 | 09/27/2022 | 09/30/2022 | 4 | 1 | 3 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2022 | 09/27/2022 | 1/21/2024 | Y | EXP | 365 | 01/21/2023 | 01/20/2023 | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N
National Grid | LEICESTER | 751379 | 01524 | 11.52 | Solar | 05_14_75L3 | 02/16/2026 | 02/19/2026 | 2 | 0 | 2 | 03/12/2026 | 03/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SUTTON | 176214 | 01590 | 499 | Solar | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2015 | N | STD | 0 | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 337127 | 01550 | 9.86 | Solar | 05_01_304W2 | 01/15/2021 | 01/22/2021 | 3 | 0 | 3 | 01/25/2021 | 01/25/2021 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2021 | 01/15/2021 | 1/21/2022 | Y | EXP | 365 | 05/04/2021 | 05/21/2021 | 17 | 0 | 17 |  |  | 8/5/2021 | Connected |  | N
National Grid | WESTMINSTER | 591210 | 01473 | 6 | Solar | 05_01_413L4 | 03/08/2024 | 03/14/2024 | 4 | 0 | 4 | 03/15/2024 | 03/15/2024 | 13 | 10 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 |  | 4/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2024 | Connected |  | N
National Grid | SWANSEA | 175830 | 02777 | 6 | Solar | 05_01_610W3 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 |  | 9/27/2016 | N | EXP | 340 |  |  | 0 | 0 | 0 | 10/23/2015 | 10/23/2015 | 5/12/2016 | Connected |  | N
National Grid | NORTHBOROUGH | 175810 | 01532 | 5 | Solar | 05_05_11W84 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2015 |  | 10/30/2015 | N | EXP | 143 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 174244 | 01970 | 10.32 | Solar | 05_05_313W3 | 02/22/2012 | 02/22/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2012 |  | 5/15/2012 | N | EXP | 14 |  |  | 0 | 0 | 0 | 6/18/2012 | 6/18/2012 | 7/26/2012 | Connected |  | N
National Grid | LOWELL | 270246 | 01851 | 6.3 | Solar | 05_12_2W1 | 06/02/2020 | 06/04/2020 | 1 | 0 | 1 | 06/05/2020 | 06/05/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/02/2020 | 5/6/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2021 | Connected |  | N
National Grid | NEWBURY | 661655 | 01950 | 5.76 | Solar | 05_14_16L3 | 12/19/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | LAWRENCE | 408613 | 01843 | 15.2 | Solar | 05_14_47L2 | 01/26/2022 | 02/03/2022 | 7 | 6 | 1 | 02/04/2022 | 02/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  | 7/15/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 426525 | 01826 | 10 | Solar | 05_14_61L3 | 05/13/2022 | 05/17/2022 | 2 | 0 | 2 | 05/18/2022 | 05/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2022 | 05/13/2022 | 10/19/2023 | Y | EXP | 365 | 08/16/2022 | 10/19/2022 | 65 | 0 | 65 |  |  | 11/2/2022 | Connected |  | N
National Grid | LEICESTER | 752359 | 01524 | 5.76 | Solar | 05_14_75L3 | 02/24/2026 | 02/27/2026 | 3 | 0 | 3 | 03/02/2026 | 03/02/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2026 |  | 4/1/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SUTTON | 176213 | 01590 | 499 | Solar | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 374481 | 01550 | 7.6 | Solar | 05_01_304W2 | 08/06/2021 | 09/09/2021 | 23 | 13 | 10 | 09/10/2021 | 09/10/2021 | 139 | 115 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 592756 | 01473 | 7.6 | Solar | 05_01_413L4 | 02/28/2024 | 05/22/2024 | 53 | 50 | 3 | 05/23/2024 | 05/23/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 | 02/28/2024 | 12/31/2025 | Y | EXP | 365 | 09/30/2025 | 09/29/2025 | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | SOMERSET | 175891 | 02725 | 5 | Solar | 05_01_610W3 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 379 | 0 | 379 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2015 |  | 8/10/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 175851 | 01532 | 17.6 | Solar | 05_05_11W84 | 05/20/2015 | 05/20/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 174490 | 01970 | 1000 | Solar | 05_05_313W3 | 07/26/2012 | 07/26/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2012 | 10/09/2012 | 42 | 0 | 42 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 279630 | 01851 | 10 | Solar | 05_12_2W1 | 02/25/2020 | 02/26/2020 | 0 | 0 | 0 | 02/27/2020 | 02/27/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2020 | 02/25/2020 | 2/25/2021 | Y | EXP | 365 | 05/15/2020 | 06/03/2020 | 19 | 0 | 19 |  |  | 6/4/2020 | Connected |  | N
National Grid | NEWBURY | 666095 | 01950 | 5.76 | Solar | 05_14_16L3 | 01/16/2025 | 03/05/2025 | 17 | 12 | 5 | 03/06/2025 | 03/06/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 5/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2025 | Connected |  | N
National Grid | LAWRENCE | 461606 | 01843 | 7.6 | Solar | 05_14_47L2 | 09/29/2022 | 12/20/2022 | 5 | 0 | 5 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 09/29/2022 | 6/27/2024 | Y | EXP | 365 | 08/10/2023 | 08/22/2023 | 13 | 0 | 13 |  |  | 9/11/2023 | Connected |  | N
National Grid | DRACUT | 433662 | 01826 | 10 | Solar | 05_14_61L3 | 06/22/2022 | 06/24/2022 | 2 | 0 | 2 | 06/27/2022 | 06/27/2022 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 753601 | 01524 | 5.76 | Solar | 05_14_75L3 | 02/27/2026 | 03/03/2026 | 1 | 0 | 1 | 03/10/2026 | 03/10/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2026 | 02/27/2026 | 4/1/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | GRAFTON | 176211 | 01519 | 499 | Solar | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 08/09/2016 | 01/19/2017 | 110 | 0 | 110 |  |  | 7/11/2016 | N | STD | 0 | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 382046 | 01550 | 7.6 | Solar | 05_01_304W2 | 01/20/2022 | 02/14/2022 | 17 | 13 | 4 | 02/15/2022 | 02/15/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 633183 | 01473 | 10 | Solar | 05_01_413L4 | 08/15/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 175905 | 02777 | 5.94 | Solar | 05_01_610W3 | 10/01/2015 | 10/01/2015 | 4 | 4 | 0 | 10/07/2015 | 10/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2015 | 10/01/2015 | 10/6/2016 | Y | EXP | 350 | 04/21/2016 | 04/21/2016 | 0 | 0 | 0 | 10/22/2015 | 10/22/2015 | 6/17/2016 | Connected |  | N
National Grid | NORTHBOROUGH | 175880 | 01532 | 450 | Solar | 05_05_11W84 | 03/06/2015 | 03/06/2015 | 5 | 0 | 5 | 03/16/2015 | 03/16/2015 | 101 | 6 | 95 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 174489 | 01970 | 2000 | Solar | 05_05_313W3 | 07/26/2012 | 07/26/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2012 | 10/09/2012 | 42 | 0 | 42 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 281332 | 01851 | 12 | Solar | 05_12_2W1 | 02/27/2020 | 03/04/2020 | 3 | 3 | 0 | 03/05/2020 | 03/05/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2020 |  | 3/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2020 | Connected |  | N
National Grid | NEWBURY | 671508 | 01985 | 10 | Solar | 05_14_16L3 | 02/13/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 7/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | LAWRENCE | 464397 | 01843 | 9.86 | Solar | 05_14_47L2 | 10/14/2022 | 10/27/2022 | 9 | 0 | 9 | 10/28/2022 | 10/28/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2022 | 10/14/2022 | 12/5/2023 | Y | EXP | 365 | 01/25/2023 | 02/01/2023 | 8 | 0 | 8 |  |  | 4/7/2023 | Connected |  | N
National Grid | METHUEN | 436374 | 01844 | 3.8 | Solar | 05_14_61L3 | 06/21/2022 | 06/22/2022 | 1 | 0 | 1 | 06/23/2022 | 06/23/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 | 06/21/2022 | 8/21/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 756202 | 01524 | 16.72 | Solar | 05_14_75L3 | 03/12/2026 | 04/01/2026 | 6 | 2 | 4 | 04/02/2026 | 04/02/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GRAFTON | 176285 | 01519 | 1000 | Solar | 05_01_21W2 | 07/09/2015 | 07/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2015 | 08/07/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 05/05/2017 | 10/06/2016 | 0 | 0 | 0 | 10/6/2016 | 07/09/2015 | 7/15/2016 | Y | STD | 83 | 08/07/2017 | 10/27/2017 | 57 | 0 | 57 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | CHARLTON | 425991 | 01507 | 7.25 | Solar | 05_01_304W2 | 06/26/2022 | 07/18/2022 | 16 | 13 | 3 | 07/19/2022 | 07/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 | 06/26/2022 | 4/3/2024 | Y | EXP | 365 | 03/25/2023 | 04/04/2023 | 11 | 0 | 11 |  |  | 4/5/2023 | Connected |  | N
National Grid | WESTMINSTER | 644414 | 01473 | 5.76 | Solar | 05_01_413L4 | 10/02/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/02/2024 | 2/3/2026 | Y | EXP | 365 | 01/04/2025 | 02/11/2025 | 39 | 0 | 39 |  |  | 4/30/2025 | Connected |  | N
National Grid | SWANSEA | 176131 | 02777 | 19 | Solar | 05_01_610W3 | 04/14/2015 | 04/14/2015 | 1 | 1 | 0 | 04/16/2015 | 04/16/2015 | 445 | 0 | 445 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2015 |  | 8/31/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 176059 | 01532 | 980 | Solar | 05_05_11W84 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 04/29/2015 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/7/2015 | N | STD | 0 | 09/11/2017 | 10/24/2017 | 30 | 0 | 30 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 174916 | 01970 | 760 | Solar | 05_05_313W3 | 02/14/2013 | 02/14/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2013 | 04/09/2013 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 |  | 6/30/2014 | N | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/31/2014 | Connected |  | N
National Grid | LOWELL | 314997 | 01851 | 3.8 | Solar | 05_12_2W1 | 10/07/2020 | 10/12/2020 | 2 | 0 | 2 | 10/13/2020 | 10/13/2020 | 39 | 25 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 10/07/2020 | 7/7/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2021 | Connected |  | Y
National Grid | NEWBURY | 682707 | 01985 | 15.2 | Solar | 05_14_16L3 | 04/03/2025 | 04/07/2025 | 2 | 0 | 2 | 04/08/2025 | 04/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | LAWRENCE | 550096 | 01843 | 9.984 | Solar | 05_14_47L2 | 01/10/2024 | 09/07/2023 | 0 | 0 | 0 | 01/23/2024 | 01/23/2024 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 2/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2024 | Connected |  | N
National Grid | DRACUT | 439483 | 01826 | 6 | Solar | 05_14_61L3 | 06/29/2022 | 07/01/2022 | 2 | 0 | 2 | 07/05/2022 | 07/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 06/29/2022 | 4/13/2024 | Y | EXP | 365 | 03/15/2023 | 04/12/2023 | 29 | 0 | 29 |  |  | 6/12/2023 | Connected |  | N
National Grid | LEICESTER | 174327 | 01524 | 1500 | Solar | 05_14_75L3 | 12/20/2011 | 12/20/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 177930 | 01519 | 2000 | Solar | 05_01_21W2 | 04/19/2017 | 04/19/2017 | 235 | 234 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/25/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 427817 | 01550 | 7.54 | Solar | 05_01_304W2 | 08/17/2022 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 669910 | 01473 | 7.8 | Solar | 05_01_413L4 | 02/04/2025 | 02/24/2025 | 4 | 0 | 4 | 02/25/2025 | 02/25/2025 | 74 | 57 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 177663 | 02777 | 4980 | Solar | 05_01_610W3 | 11/13/2017 | 11/13/2017 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2017 | 12/20/2017 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 |  | 11/19/2018 | N | STD | 125 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 176058 | 01532 | 996 | Solar | 05_05_11W84 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 04/29/2015 | 17 | 0 | 17 |  | 0 | 0 | 0 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 | 2/24/2016 | 03/27/2015 | 10/15/2017 | Y | STD | 599 | 09/11/2017 | 10/24/2017 | 30 | 0 | 30 | 10/12/2017 | 10/12/2017 | 10/17/2017 | Connected |  | N
National Grid | SALEM | 176105 | 01970 | 20 | Solar | 05_05_313W3 | 06/24/2015 | 06/24/2015 | 3 | 3 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/30/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 11/3/2015 | 11/3/2015 | 11/4/2015 | Connected |  | N
National Grid | LOWELL | 318458 | 01851 | 9.36 | Solar | 05_12_2W1 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/10/2020 | 7/8/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2022 | Connected |  | N
National Grid | NEWBURY | 682361 | 01985 | 15.2 | Solar | 05_14_16L3 | 04/02/2025 | 04/25/2025 | 16 | 12 | 4 | 04/28/2025 | 04/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | LAWRENCE | 566203 | 01843 | 86.4 | Solar | 05_14_47L2 | 12/05/2023 | 02/20/2024 | 51 | 41 | 10 | 02/21/2024 | 02/21/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 12/05/2023 | 2/8/2025 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | Y
National Grid | DRACUT | 442804 | 01826 | 7.6 | Solar | 05_14_61L3 | 08/04/2022 | 08/05/2022 | 1 | 0 | 1 | 08/08/2022 | 08/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 174326 | 01524 | 1000 | Solar | 05_14_75L3 | 12/20/2011 | 12/20/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 04/30/2014 | 09/04/2014 | 87 | 0 | 87 |  |  | 9/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 255873 | 01560 | 5000 | Solar | 05_01_21W2 | 11/20/2019 | 12/01/2019 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2019 | 12/09/2019 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 506760 | 01550 | 18.85 | Solar | 05_01_304W2 | 03/06/2023 | 03/07/2023 | 1 | 0 | 1 | 03/08/2023 | 03/08/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  | 4/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2023 | Connected |  | N
National Grid | WESTMINSTER | 682067 | 01473 | 10 | Solar | 05_01_413L4 | 04/01/2025 | 05/22/2025 | 2 | 0 | 2 | 05/23/2025 | 05/23/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 11/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | SWANSEA | 178300 | 02777 | 4875 | Solar | 05_01_610W3 | 11/16/2017 | 12/18/2017 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2017 | 01/17/2018 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2018 | 11/16/2017 | 3/31/2023 | Y | STD | 725 | 08/12/2022 | 01/03/2023 | 145 | 0 | 145 | 3/9/2023 | 3/23/2023 | 3/31/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 176328 | 01532 | 3.8 | Solar | 05_05_11W84 | 07/20/2015 | 07/20/2015 | 4 | 4 | 0 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 | 07/20/2015 | 7/26/2016 | Y | EXP | 364 |  |  | 0 | 0 | 0 | 5/3/2016 | 5/3/2016 | 5/3/2016 | Connected |  | N
National Grid | SALEM | 177233 | 01970 | 156 | Solar | 05_05_313W3 | 11/04/2016 | 11/04/2016 | 1 | 1 | 0 | 11/08/2016 | 11/08/2016 | 240 | 0 | 240 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2016 |  | 11/12/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 326340 | 01851 | 8.7 | Solar | 05_12_2W1 | 02/03/2021 | 02/08/2021 | 2 | 0 | 2 | 02/09/2021 | 02/09/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 | 02/03/2021 | 1/11/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2021 | Connected |  | N
National Grid | NEWBURY | 688012 | 01950 | 7.6 | Solar | 05_14_16L3 | 04/29/2025 | 06/13/2025 | 3 | 0 | 3 | 06/16/2025 | 06/16/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | LAWRENCE | 600694 | 01843 | 15.2 | Solar | 05_14_47L2 | 04/05/2024 | 04/09/2024 | 2 | 0 | 2 | 04/10/2024 | 04/10/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 477774 | 01826 | 11.89 | Solar | 05_14_61L3 | 01/25/2023 | 01/26/2023 | 1 | 0 | 1 | 01/27/2023 | 01/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 174961 | 01524 | 60 | Solar | 05_14_75L3 | 03/05/2013 | 03/05/2013 | 4 | 0 | 4 | 03/15/2013 | 03/15/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2013 | 03/05/2013 | 6/14/2013 | Y | EXP | 108 | 01/30/2014 | 03/11/2014 | 27 | 0 | 27 | 4/24/2014 | 4/24/2014 | 4/24/2014 | Connected |  | N
National Grid | GRAFTON | 272127 | 01519 | 4950 | Other | 05_01_21W2 | 02/24/2020 | 04/10/2020 | 33 | 27 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2020 | 05/11/2020 | 19 | 9 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 514181 | 01550 | 10 | Solar | 05_01_304W2 | 03/23/2023 | 03/24/2023 | 1 | 0 | 1 | 03/27/2023 | 03/27/2023 | 253 | 25 | 228 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 693150 | 01473 | 7.6 | Solar | 05_01_413L4 | 05/21/2025 | 05/28/2025 | 4 | 0 | 4 | 05/29/2025 | 05/29/2025 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 | 05/21/2025 | 8/11/2026 | Y | EXP | 365 | 11/22/2025 | 11/21/2025 | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | SOMERSET | 178378 | 02725 | 5000 | Solar | 05_01_610W3 | 11/22/2017 | 11/22/2017 | 44 | 35 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2018 | 02/25/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/27/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 176755 | 01532 | 300 | Solar | 05_05_11W84 | 01/13/2016 | 01/13/2016 | 3 | 3 | 0 | 01/19/2016 | 01/19/2016 | 179 | 0 | 179 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/18/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 177390 | 01970 | 15.2 | Solar | 05_05_313W3 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 274 | 0 | 274 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2017 |  | 2/21/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 328907 | 01851 | 8.64 | Solar | 05_12_2W1 | 12/01/2020 | 12/08/2020 | 4 | 0 | 4 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 12/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2021 | Connected |  | N
National Grid | NEWBURY | 708313 | 01985 | 12.54 | Solar | 05_14_16L3 | 07/30/2025 | 09/15/2025 | 26 | 24 | 2 | 09/16/2025 | 09/16/2025 | 53 | 50 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 602560 | 01843 | 15.2 | Solar | 05_14_47L2 | 04/08/2024 | 05/07/2024 | 21 | 19 | 2 | 05/08/2024 | 05/08/2024 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 |  | 5/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2024 | Connected |  | N
National Grid | DRACUT | 483461 | 01826 | 10 | Solar | 05_14_61L3 | 12/13/2022 | 12/20/2022 | 5 | 0 | 5 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 12/13/2022 | 5/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2023 | Connected |  | N
National Grid | LEICESTER | 175207 | 01524 | 12 | Solar | 05_14_75L3 | 12/04/2012 | 12/04/2012 | 7 | 0 | 7 | 12/17/2012 | 12/17/2012 | 214 | 0 | 214 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2013 |  | 3/1/2013 | N | EXP | 14 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 293665 | 01519 | 8.4 | Solar | 05_01_21W2 | 06/11/2020 | 06/29/2020 | 11 | 6 | 5 | 06/30/2020 | 06/30/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2020 | Connected |  | N
National Grid | SOUTHBRIDGE | 523131 | 01550 | 9.216 | Solar | 05_01_304W2 | 06/08/2023 | 06/12/2023 | 2 | 0 | 2 | 06/13/2023 | 06/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 339091 | 01473 | 4999 | Solar | 05_01_413L6 | 04/07/2021 | 04/28/2021 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2021 | 05/28/2021 | 22 | 1 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SOMERSET | 192451 | 02725 | 3780 | Solar | 05_01_610W3 | 09/18/2018 | 10/05/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2018 | 11/17/2018 | 30 | 0 | 30 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 177033 | 01532 | 225 | Solar | 05_05_11W84 | 07/26/2016 | 07/26/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 09/15/2016 | 10/13/2016 | 19 | 0 | 19 | 07/28/2016 | 08/25/2016 | 20 | 0 | 20 | 10/13/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 8/1/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 177966 | 01970 | 480 | Solar | 05_05_313W3 | 04/21/2017 | 04/21/2017 | 197 | 194 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/29/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 379550 | 01851 | 0 | Solar | 05_12_2W1 | 09/02/2021 | 09/07/2021 | 2 | 0 | 2 | 09/08/2021 | 09/08/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2021 |  | 11/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2022 | Connected |  | N
National Grid | NEWBURY | 613760 | 01950 | 5.76 | Solar | 05_14_47L2 | 05/28/2024 | 06/05/2024 | 1 | 0 | 1 | 06/06/2024 | 06/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/28/2024 | 11/30/2025 | Y | EXP | 365 | 09/28/2024 | 09/27/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 494773 | 01843 | 6 | Solar | 05_14_61L3 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 02/09/2023 | 10/5/2024 | Y | EXP | 365 | 08/12/2023 | 10/05/2023 | 55 | 0 | 55 |  |  | 10/12/2023 | Connected |  | N
National Grid | DRACUT | 175812 | 01826 | 17.63 | Solar | 05_14_75L3 | 05/18/2015 | 05/18/2015 | 3 | 3 | 0 | 05/27/2015 | 05/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2015 |  | 10/30/2015 | N | EXP | 151 |  |  | 0 | 0 | 0 | 7/13/2015 | 7/13/2015 | 11/20/2015 | Connected |  | N
National Grid | LEICESTER | 336469 | 01542 | 10 | Solar | 05_01_21W2 | 01/22/2021 | 01/10/2022 | 2 | 0 | 2 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/22/2021 | 5/13/2023 | Y | EXP | 365 | 02/22/2022 | 04/11/2022 | 48 | 0 | 48 |  |  | 5/20/2022 | Connected |  | N
National Grid | SUTTON | 523641 | 01590 | 5 | Solar | 05_01_304W2 | 05/17/2023 | 05/18/2023 | 1 | 0 | 1 | 05/19/2023 | 05/19/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 | 05/17/2023 | 4/18/2025 | Y | EXP | 465 | 01/10/2024 | 02/23/2024 | 45 | 0 | 45 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 438733 | 01550 | 0 | Natural Gas | 05_01_413L6 | 08/16/2022 | 10/26/2022 | 49 | 40 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 | 11/28/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | WESTMINSTER | 200898 | 01473 | 4998 | Solar | 05_01_610W3 | 11/12/2018 | 11/30/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 01/25/2019 | 37 | 18 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 177209 | 02725 | 10 | Solar | 05_05_11W84 | 06/06/2016 | 06/06/2016 | 1 | 1 | 0 | 06/08/2016 | 06/08/2016 | 210 | 0 | 210 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 |  | 6/12/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 178354 | 01532 | 480 | Solar | 05_05_313W3 | 02/27/2018 | 02/27/2018 | 2 | 2 | 0 | 03/02/2018 | 03/02/2018 | 169 | 9 | 160 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/5/2019 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 387155 | 01970 | 7.6 | Solar | 05_12_2W1 | 10/27/2021 | 11/08/2021 | 9 | 5 | 4 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 | 10/27/2021 | 6/3/2023 | Y | EXP | 365 | 04/22/2022 | 05/26/2022 | 35 | 0 | 35 |  |  | 6/29/2022 | Connected |  | N
National Grid | LOWELL | 517634 | 01851 | 100 | Solar | 05_14_16L4 | 04/29/2023 | 07/20/2023 | 56 | 46 | 10 |  |  | 118 | 97 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 |  | 12/24/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 634503 | 01950 | 0 | Battery Add-On | 05_14_47L2 | 09/06/2024 | 01/16/2025 | 18 | 13 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 09/06/2024 | 3/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | LAWRENCE | 519281 | 01843 | 7.6 | Solar | 05_14_61L3 | 04/26/2023 | 05/02/2023 | 4 | 0 | 4 | 05/03/2023 | 05/03/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 | 04/26/2023 | 8/2/2024 | Y | EXP | 365 | 09/12/2023 | 10/05/2023 | 24 | 0 | 24 |  |  | 10/16/2023 | Connected |  | N
National Grid | DRACUT | 178497 | 01826 | 7.6 | Solar | 05_14_75L3 | 12/04/2017 | 12/04/2017 | 64 | 59 | 5 | 03/26/2018 | 03/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2018 |  | 12/10/2018 | N | EXP | 259 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 384247 | 01524 | 0 | Other | 05_01_21W2 | 03/30/2022 | 04/27/2022 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/28/2022 | 06/01/2022 | 25 | 6 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 591813 | 01590 | 3.8 | Solar | 05_01_304W2 | 02/26/2024 | 03/07/2024 | 8 | 3 | 5 | 03/08/2024 | 03/08/2024 | 18 | 17 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 | 02/26/2024 | 5/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | CHARLTON | 175098 | 01507 | 2000 | Solar | 05_01_413L6 | 10/26/2012 | 10/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 | 12/28/2012 | 27 | 0 | 27 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 370345 | 01473 | 11.4 | Solar | 05_01_610W3 | 07/16/2021 | 08/19/2021 | 24 | 23 | 1 | 08/20/2021 | 08/20/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 | 07/16/2021 | 7/15/2023 | Y | EXP | 365 | 02/17/2022 | 02/28/2022 | 12 | 0 | 12 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 177350 | 02777 | 7.6 | Solar | 05_05_11W84 | 02/15/2017 | 02/15/2017 | 5 | 3 | 2 | 02/23/2017 | 02/23/2017 | 274 | 0 | 274 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2017 |  | 2/20/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 196299 | 01532 | 236 | Solar | 05_05_313W3 | 11/14/2018 | 11/20/2018 | 3 | 0 | 3 | 11/21/2018 | 11/21/2018 | 18 | 2 | 16 | 06/11/2019 | 06/10/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 406678 | 01970 | 15.2 | Solar | 05_12_2W1 | 01/14/2022 | 01/18/2022 | 1 | 0 | 1 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 669042 | 01824 | 0 | Battery Add-On | 05_14_16L4 | 02/03/2025 | 02/05/2025 | 2 | 0 | 2 | 02/06/2025 | 02/06/2025 | 84 | 60 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 638266 | 01950 | 0 | Battery Add-On | 05_14_47L2 | 09/06/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | LAWRENCE | 518138 | 01843 | 10 | Solar | 05_14_61L3 | 04/17/2023 | 04/19/2023 | 2 | 0 | 2 | 04/20/2023 | 04/20/2023 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 178631 | 01826 | 7.6 | Solar | 05_14_75L3 | 03/15/2018 | 03/15/2018 | 13 | 13 | 0 | 04/05/2018 | 04/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 |  | 3/21/2019 | N | EXP | 311 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 396703 | 01524 | 250 | Solar | 05_01_21W2 | 12/27/2021 |  | 215 | 208 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 626207 | 01519 | 10 | Solar | 05_01_304W2 | 07/19/2024 | 09/17/2024 | 31 | 25 | 6 | 09/18/2024 | 09/18/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 175097 | 01550 | 1000 | Solar | 05_01_413L6 | 10/26/2012 | 10/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 | 12/28/2012 | 27 | 0 | 27 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 382185 | 01473 | 15.2 | Solar | 05_01_610W3 | 09/15/2021 | 12/08/2021 | 3 | 0 | 3 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/15/2021 | 11/3/2023 | Y | EXP | 365 | 09/02/2022 | 10/26/2022 | 55 | 0 | 55 |  |  | 12/13/2022 | Connected |  | N
National Grid | SWANSEA | 177712 | 02777 | 1000 | Solar | 05_05_11W84 | 07/25/2017 | 07/25/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2017 | 12/15/2017 | 79 | 0 | 79 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 196297 | 01532 | 496 | Solar | 05_05_313W3 | 11/15/2018 | 11/20/2018 | 2 | 0 | 2 | 11/21/2018 | 11/21/2018 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 415655 | 01970 | 10 | Solar | 05_12_2W1 | 03/14/2022 | 03/23/2022 | 7 | 3 | 4 | 03/24/2022 | 03/24/2022 | 54 | 26 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 679246 | 01824 | 15.2 | Solar | 05_14_16L4 | 04/02/2025 | 04/14/2025 | 9 | 6 | 3 | 04/15/2025 | 04/15/2025 | 33 | 22 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | NEWBURY | 651318 | 01950 | 10 | Solar | 05_14_47L2 | 11/12/2024 | 01/03/2025 | 3 | 0 | 3 | 01/06/2025 | 01/06/2025 | 25 | 0 | 25 | 02/25/2025 | 03/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 03/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 3/31/2025 | 11/12/2024 | 4/7/2026 | Y | EXP | 365 | 09/10/2025 | 09/16/2025 | 7 | 0 | 7 |  |  | 9/24/2025 | Connected |  | N
National Grid | LAWRENCE | 543146 | 01843 | 9.6 | Solar | 05_14_61L3 | 08/30/2023 | 09/08/2023 | 6 | 5 | 1 | 09/11/2023 | 09/11/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 | 08/30/2023 | 11/17/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2024 | Connected |  | N
National Grid | METHUEN | 199466 | 01844 | 10 | Solar | 05_14_75L3 | 10/25/2018 | 11/01/2018 | 1 | 0 | 1 | 11/02/2018 | 11/02/2018 | 77 | 35 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 457727 | 01542 | 5.22 | Solar | 05_01_21W2 | 09/27/2022 | 09/30/2022 | 3 | 0 | 3 | 10/03/2022 | 10/03/2022 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 09/27/2022 | 5/19/2024 | Y | EXP | 365 | 04/21/2023 | 05/19/2023 | 29 | 0 | 29 |  |  | 6/9/2023 | Connected |  | N
National Grid | GRAFTON | 638284 | 01519 | 15.2 | Solar | 05_01_304W2 | 09/09/2024 | 09/23/2024 | 5 | 2 | 3 | 09/24/2024 | 09/24/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 11/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2025 | Connected |  | Y
National Grid | SOUTHBRIDGE | 176301 | 01550 | 1126 | Natural Gas | 05_01_413L6 | 09/11/2015 | 09/11/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2015 | 10/30/2015 | 31 | 0 | 31 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 |  | 7/1/2018 | N | STD | 305 |  |  | 0 | 0 | 0 | 3/23/2018 | 3/23/2018 | 8/27/2018 | Connected |  | N
National Grid | WESTMINSTER | 423419 | 01473 | 2.33 | Solar | 05_01_610W3 | 02/13/2023 | 02/15/2023 | 2 | 0 | 2 | 02/16/2023 | 02/16/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 177736 | 02725 | 3.6 | Solar | 05_05_11W84 | 03/23/2017 | 03/23/2017 | 6 | 6 | 0 | 03/31/2017 | 03/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 | 03/23/2017 | 3/28/2018 | Y | EXP | 358 | 08/09/2017 | 08/14/2017 | 3 | 0 | 3 | 3/1/2018 | 3/1/2018 | 3/23/2018 | Connected |  | N
National Grid | NORTHBOROUGH | 201086 | 01532 | 2460 | Solar | 05_05_313W3 | 02/20/2019 | 01/15/2020 | 226 | 26 | 200 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2020 | 08/19/2020 | 148 | 0 | 148 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 437523 | 01970 | 15.2 | Solar | 05_12_2W1 | 06/14/2022 | 06/15/2022 | 1 | 0 | 1 | 06/16/2022 | 06/16/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2022 | 06/14/2022 | 2/29/2024 | Y | EXP | 365 | 01/25/2023 | 04/17/2023 | 83 | 0 | 83 |  |  | 5/22/2023 | Connected |  | N
National Grid | CHELMSFORD | 727121 | 01824 | 19 | Solar | 05_14_16L4 | 10/28/2025 | 11/12/2025 | 5 | 0 | 5 | 11/13/2025 | 11/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 1/8/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 662520 | 01950 | 5.76 | Solar | 05_14_47L2 | 12/26/2024 | 02/03/2025 | 7 | 1 | 6 | 02/04/2025 | 02/04/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | LAWRENCE | 543499 | 01843 | 6 | Solar | 05_14_61L3 | 07/28/2023 | 07/31/2023 | 1 | 0 | 1 | 08/01/2023 | 08/01/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 211523 | 01826 | 23.4 | Solar | 05_14_75L3 | 03/19/2019 | 03/26/2019 | 5 | 3 | 2 | 03/27/2019 | 03/27/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2019 |  | 3/19/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2020 | Connected |  | N
National Grid | LEICESTER | 651889 | 01524 | 18.85 | Solar | 05_01_304W2 | 11/27/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | GRAFTON | 192559 | 01560 | 5786 | Solar | 05_01_413L6 | 08/23/2018 | 09/17/2018 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 03/28/2019 | 214 | 110 | 104 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 468590 | 01550 | 16.24 | Solar | 05_01_610W3 | 11/26/2022 | 12/01/2022 | 4 | 2 | 2 | 12/02/2022 | 12/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2023 | Connected |  | N
National Grid | WESTMINSTER | 177848 | 01473 | 300 | Natural Gas | 05_05_11W84 | 04/06/2017 | 04/06/2017 | 54 | 54 | 0 | 06/26/2017 | 06/26/2017 | 189 | 53 | 136 | 08/17/2017 | 10/16/2017 | 40 | 22 | 18 |  |  | 0 | 0 | 0 | 10/16/2017 | 40 | 22 | 18 |  |  | 0 | 0 | 0 | 12/15/2017 |  | 4/12/2018 | N | EXP | 118 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 460824 | 02725 | 6 | Solar | 05_12_2W1 | 09/26/2022 | 09/28/2022 | 2 | 0 | 2 | 09/29/2022 | 09/29/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 09/26/2022 | 9/3/2024 | Y | EXP | 450 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 748336 | 01532 | 7.6 | Solar | 05_14_16L4 | 01/30/2026 | 02/04/2026 | 3 | 0 | 3 | 02/05/2026 | 02/05/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 713199 | 01970 | 20 | Solar | 05_14_47L2 | 08/19/2025 | 08/20/2025 | 1 | 0 | 1 | 08/21/2025 | 08/21/2025 | 70 | 56 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 546077 | 01824 | 3.8 | Solar | 05_14_61L3 | 08/07/2023 | 08/08/2023 | 1 | 0 | 1 | 08/09/2023 | 08/09/2023 | 20 | 1 | 19 | 09/15/2023 | 10/10/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 10/10/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 10/6/2023 |  | 12/31/2024 | N | EXP | 365 | 01/20/2024 | 01/19/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 212099 | 01985 | 10 | Solar | 05_14_75L3 | 04/12/2019 | 05/28/2019 | 30 | 30 | 0 | 05/29/2019 | 05/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2019 | 04/12/2019 | 2/21/2020 | Y | EXP | 259 | 12/19/2019 | 01/29/2020 | 41 | 0 | 41 |  |  | 1/31/2020 | Connected |  | N
National Grid | LAWRENCE | 470048 | 01843 | 20 | Solar | 05_01_21W2 | 10/21/2022 | 10/27/2022 | 4 | 2 | 2 | 10/28/2022 | 10/28/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2022 | 10/21/2022 | 6/11/2024 | Y | EXP | 365 | 05/16/2023 | 06/12/2023 | 28 | 0 | 28 |  |  | 6/21/2023 | Connected |  | N
National Grid | DRACUT | 663082 | 01826 | 10 | Solar | 05_01_304W2 | 12/30/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | LEICESTER | 174130 | 01524 | 2000 | Solar | 05_01_413L7 | 05/01/2012 | 05/01/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2012 | 08/16/2012 | 63 | 0 | 63 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 477503 | 01560 | 7.6 | Solar | 05_01_610W3 | 11/18/2022 | 11/22/2022 | 2 | 0 | 2 | 11/23/2022 | 11/23/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2022 |  | 12/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 178036 | 01550 | 9.86 | Solar | 05_05_11W84 | 10/27/2017 | 10/27/2017 | 39 | 39 | 0 | 01/04/2018 | 01/04/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 |  | 11/5/2018 | N | EXP | 301 |  |  | 0 | 0 | 0 |  |  | 5/17/2018 | Connected |  | N
National Grid | WESTMINSTER | 288940 | 01472 | 11.4 | Solar | 05_05_313W3 | 04/22/2020 | 04/30/2020 | 6 | 6 | 0 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 |  | 4/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2020 | Connected |  | N
National Grid | SOMERSET | 557503 | 02726 | 7.6 | Solar | 05_12_2W1 | 10/18/2023 | 10/23/2023 | 3 | 0 | 3 | 10/24/2023 | 10/24/2023 | 31 | 20 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 749081 | 01532 | 120 | Solar | 05_14_16L4 | 02/25/2026 |  | 25 | 19 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SALEM | 714914 | 01970 | 15.2 | Solar | 05_14_47L2 | 09/02/2025 | 09/19/2025 | 11 | 6 | 5 | 09/22/2025 | 09/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2026 | Connected |  | N
National Grid | CHELMSFORD | 566020 | 01824 | 7.6 | Solar | 05_14_61L3 | 11/15/2023 | 12/05/2023 | 13 | 8 | 5 | 12/06/2023 | 12/06/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/15/2023 | 8/12/2025 | Y | EXP | 365 | 06/06/2024 | 09/16/2024 | 103 | 0 | 103 |  |  | 4/1/2025 | Connected |  | N
National Grid | NEWBURY | 218706 | 01985 | 7.6 | Solar | 05_14_75L3 | 05/16/2019 | 05/24/2019 | 5 | 0 | 5 | 05/28/2019 | 05/28/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 479173 | 01843 | 15.2 | Solar | 05_01_21W2 | 11/21/2022 | 11/27/2022 | 4 | 0 | 4 | 11/28/2022 | 11/28/2022 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 |  | 5/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 672732 | 01826 | 3.8 | Solar | 05_01_304W2 | 02/18/2025 | 03/25/2025 | 4 | 0 | 4 | 03/26/2025 | 03/26/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | LEICESTER | 178064 | 01611 | 9 | Solar | 05_01_413L7 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 | 09/05/2017 | 09/05/2017 | 140 | 15 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/10/2018 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 494286 | 01590 | 7.6 | Solar | 05_01_610W3 | 02/06/2023 | 02/08/2023 | 2 | 0 | 2 | 02/09/2023 | 02/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/06/2023 | 7/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2023 | Connected |  | Y
National Grid | STURBRIDGE | 178046 | 01566 | 3.8 | Solar | 05_05_11W84 | 05/05/2017 | 05/05/2017 | 2 | 2 | 0 | 05/09/2017 | 05/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2017 |  | 5/10/2018 | N | EXP | 365 |  |  | 0 | 0 | 0 | 10/27/2017 | 10/27/2017 | 10/27/2017 | Connected |  | N
National Grid | WESTMINSTER | 387185 | 01473 | 8.12 | Solar | 05_05_313W3 | 11/29/2021 | 01/07/2022 | 11 | 4 | 7 | 12/15/2021 | 12/15/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 569404 | 02725 | 7.6 | Solar | 05_12_2W1 | 11/27/2023 | 11/28/2023 | 1 | 0 | 1 | 11/29/2023 | 11/29/2023 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/27/2023 | 4/20/2025 | Y | EXP | 365 | 08/07/2024 | 10/24/2024 | 79 | 0 | 79 |  |  | 10/30/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 174780 | 01532 | 100 | Solar | 05_14_16L4 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 583 | 7 | 576 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2013 |  | 12/31/2016 | N | EXP | 1222 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 733360 | 01970 | 17.28 | Solar | 05_14_47L2 | 11/18/2025 | 11/20/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 561606 | 01824 | 3.8 | Solar | 05_14_61L3 | 10/10/2023 | 10/16/2023 | 5 | 3 | 2 | 10/17/2023 | 10/17/2023 | 34 | 16 | 18 | 12/11/2023 | 01/17/2024 | 21 | 3 | 18 |  |  | 0 | 0 | 0 | 01/17/2024 | 21 | 3 | 18 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 11/30/2025 | N | EXP | 600 | 05/02/2024 | 05/29/2024 | 28 | 0 | 28 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 223770 | 01985 | 10 | Solar | 05_14_75L3 | 06/05/2019 | 06/12/2019 | 4 | 0 | 4 | 06/13/2019 | 06/13/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2019 | 06/05/2019 | 10/20/2021 | Y | EXP | 365 | 09/05/2020 | 09/28/2020 | 23 | 0 | 23 |  |  | 1/8/2021 | Connected |  | N
National Grid | LAWRENCE | 485085 | 01843 | 6 | Solar | 05_01_21W2 | 12/14/2022 | 12/20/2022 | 4 | 0 | 4 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2023 | Connected |  | N
National Grid | DRACUT | 678189 | 01826 | 3.8 | Solar | 05_01_304W2 | 03/14/2025 | 03/20/2025 | 4 | 0 | 4 | 03/21/2025 | 03/21/2025 | 55 | 34 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | LEICESTER | 200645 | 01524 | 20 | Solar | 05_01_413L7 | 02/21/2019 | 04/12/2019 | 36 | 25 | 11 | 04/15/2019 | 04/15/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2019 |  | 4/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2019 | Connected |  | N
National Grid | GRAFTON | 536407 | 01560 | 15.2 | Solar | 05_01_610W3 | 06/30/2023 | 07/05/2023 | 2 | 1 | 1 | 07/06/2023 | 07/06/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 |  | 8/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N
National Grid | STURBRIDGE | 178101 | 01566 | 3.8 | Solar | 05_05_11W84 | 09/08/2017 | 09/08/2017 | 7 | 7 | 0 | 09/19/2017 | 09/19/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2017 |  | 9/13/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  | 7/25/2018 | Connected |  | N
National Grid | WESTMINSTER | 415225 | 01473 | 15.2 | Solar | 05_05_313W3 | 03/03/2022 |  | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 597666 | 02777 | 3.8 | Solar | 05_12_2W1 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/26/2024 | 4/16/2025 | Y | EXP | 365 | 05/24/2024 | 08/21/2024 | 90 | 0 | 90 |  |  | 8/5/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 174786 | 01532 | 300 | Solar | 05_14_16L4 | 08/06/2013 | 08/06/2013 | 1 | 0 | 1 | 08/07/2013 | 08/07/2013 | 566 | 5 | 561 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2013 |  | 9/14/2014 | N | EXP | 383 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 738477 | 01970 | 18.24 | Solar | 05_14_47L2 | 01/15/2026 | 02/02/2026 | 11 | 8 | 3 | 02/03/2026 | 02/03/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2026 | Connected |  | N
National Grid | CHELMSFORD | 562630 | 01824 | 10 | Solar | 05_14_61L3 | 10/12/2023 | 11/02/2023 | 15 | 12 | 3 | 11/03/2023 | 11/03/2023 | 87 | 66 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 10/12/2023 | 3/23/2025 | Y | EXP | 365 | 05/16/2024 | 06/03/2024 | 19 | 0 | 19 |  |  | 6/7/2024 | Connected |  | N
National Grid | NEWBURY | 234804 | 01985 | 10 | Solar | 05_14_75L3 | 07/15/2019 | 07/16/2019 | 0 | 0 | 0 | 07/17/2019 | 07/17/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2019 | 07/15/2019 | 12/7/2020 | Y | EXP | 365 | 10/28/2020 | 11/09/2020 | 12 | 0 | 12 |  |  | 11/17/2020 | Connected |  | N
National Grid | LAWRENCE | 523512 | 01843 | 4000 | Solar | 05_01_21W2 | 07/06/2023 | 08/28/2023 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2023 | 10/13/2023 | 33 | 14 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 694781 | 01826 | 5.76 | Solar | 05_01_304W2 | 06/06/2025 | 06/13/2025 | 5 | 0 | 5 | 06/16/2025 | 06/16/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | LEICESTER | 204724 | 01524 | 7.6 | Solar | 05_01_413L7 | 01/11/2019 | 02/11/2019 | 19 | 10 | 9 | 02/12/2019 | 02/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 | 01/11/2019 | 2/27/2020 | Y | EXP | 365 | 04/18/2019 | 05/28/2019 | 40 | 0 | 40 |  |  | 6/29/2019 | Connected |  | N
National Grid | SUTTON | 623866 | 01590 | 3.8 | Solar | 05_01_610W3 | 07/10/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 178265 | 01566 | 4998 | Solar | 05_05_11W84 | 01/08/2018 | 03/06/2018 | 27 | 20 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2018 | 04/10/2018 | 25 | 0 | 25 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2018 |  | 7/9/2020 | N | STD | 660 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 420767 | 01473 | 15.2 | Solar | 05_05_313W3 | 03/30/2022 | 03/31/2022 | 1 | 0 | 1 | 04/01/2022 | 04/01/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2022 |  | 5/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2022 | Connected |  | N
National Grid | SWANSEA | 641278 | 02777 | 5.76 | Solar | 05_12_2W1 | 09/18/2024 | 10/07/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  | 11/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 175754 | 01532 | 100 | Solar | 05_14_16L4 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 108 | 03/06/2015 | 05/06/2015 | 41 | 0 | 41 | 6/1/2015 | 6/1/2015 | 6/1/2015 | Connected |  | N
National Grid | SALEM | 735545 | 01970 | 200 | Solar | 05_14_48L1 | 11/25/2025 | 01/06/2026 | 27 | 21 | 6 | 01/07/2026 | 01/07/2026 | 52 | 25 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHELMSFORD | 573321 | 01824 | 3.8 | Solar | 05_14_61L3 | 01/12/2024 | 01/30/2024 | 11 | 8 | 3 | 01/31/2024 | 01/31/2024 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 01/12/2024 | 4/10/2025 | Y | EXP | 365 | 05/16/2024 | 08/21/2024 | 98 | 0 | 98 |  |  | 8/31/2024 | Connected |  | N
National Grid | NEWBURY | 260249 | 01985 | 9.86 | Solar | 05_14_75L3 | 10/20/2019 | 11/08/2019 | 14 | 9 | 5 | 11/12/2019 | 11/12/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 | 10/20/2019 | 10/20/2020 | Y | EXP | 365 | 04/21/2020 | 05/13/2020 | 22 | 0 | 22 |  |  | 8/25/2020 | Connected |  | N
National Grid | LAWRENCE | 526652 | 01843 | 14.5 | Solar | 05_01_21W2 | 06/27/2023 | 06/28/2023 | 1 | 1 | 0 | 06/29/2023 | 06/29/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 | 06/27/2023 | 7/31/2024 | Y | EXP | 365 | 09/14/2023 | 10/10/2023 | 27 | 0 | 27 |  |  | 10/16/2023 | Connected |  | N
National Grid | DRACUT | 744323 | 01826 | 11.5 | Solar | 05_01_304W2 | 01/09/2026 | 01/12/2026 | 3 | 0 | 3 | 01/27/2026 | 01/27/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 | 01/09/2026 | 2/10/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2026 | Connected |  | N
National Grid | LEICESTER | 284646 | 01542 | 9.84 | Solar | 05_01_413L7 | 03/23/2020 | 04/13/2020 | 0 | 0 | 0 | 04/14/2020 | 04/14/2020 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2020 | 03/23/2020 | 4/13/2021 | Y | EXP | 365 | 07/30/2020 | 09/10/2020 | 42 | 5 | 37 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 623437 | 01560 | 1.74 | Solar | 05_01_610W3 | 07/09/2024 | 07/19/2024 | 2 | 0 | 2 | 07/22/2024 | 07/22/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2024 | Connected |  | N
National Grid | STURBRIDGE | 178294 | 01566 | 2050 | Solar | 05_05_11W84 | 11/14/2017 | 11/14/2017 | 49 | 49 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2018 | 03/23/2018 | 27 | 14 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 437383 | 01473 | 15.2 | Solar | 05_05_313W3 | 06/13/2022 | 06/14/2022 | 1 | 0 | 1 | 06/15/2022 | 06/15/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2022 |  | 8/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2022 | Connected |  | N
National Grid | SWANSEA | 648870 | 02777 | 7.6 | Solar | 05_12_2W1 | 11/05/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 175753 | 01532 | 300 | Solar | 05_14_16L4 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 118 | 03/10/2015 | 06/26/2015 | 74 | 0 | 74 | 5/22/2015 | 5/22/2015 | 5/22/2015 | Connected |  | N
National Grid | SALEM | 174294 | 01970 | 300 | Solar | 05_14_48L1 | 12/15/2011 | 12/15/2011 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2012 |  | 1/28/2012 | N | EXP | 30 |  |  | 0 | 0 | 0 | 6/1/2012 | 6/1/2012 | 6/4/2012 | Connected |  | N
National Grid | CHELMSFORD | 581506 | 01824 | 7.6 | Solar | 05_14_61L3 | 01/04/2024 |  | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 263447 | 01832 | 10 | Solar | 05_14_75L3 | 11/01/2019 | 11/06/2019 | 2 | 0 | 2 | 11/07/2019 | 11/07/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 |  | 11/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2020 | Connected |  | N
National Grid | LAWRENCE | 566580 | 01843 | 17.6 | Solar | 05_01_21W2 | 12/14/2023 | 12/27/2023 | 8 | 4 | 4 | 12/28/2023 | 12/28/2023 | 83 | 62 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | METHUEN | 173360 | 01844 | 7.6 | Solar | 05_01_304W3 | 07/31/2018 | 08/06/2018 | 1 | 0 | 1 | 08/07/2018 | 08/07/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 07/31/2018 | 8/8/2019 | Y | EXP | 365 | 04/03/2019 | 04/02/2019 | 0 | 0 | 0 |  |  | 4/18/2019 | Connected |  | N
National Grid | LEICESTER | 449561 | 01524 | 19 | Solar | 05_01_413L7 | 08/04/2022 | 08/12/2022 | 6 | 3 | 3 | 08/15/2022 | 08/15/2022 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2022 |  | 9/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2023 | Connected |  | N
National Grid | GRAFTON | 655947 | 01519 | 10 | Solar | 05_01_610W3 | 11/21/2024 | 01/06/2025 | 16 | 12 | 4 | 01/07/2025 | 01/07/2025 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2025 | Connected |  | N
National Grid | STURBRIDGE | 197466 | 01566 | 480 | Solar | 05_05_11W84 | 01/16/2019 | 02/04/2019 | 12 | 4 | 8 | 02/05/2019 | 02/05/2019 | 23 | 11 | 12 | 04/10/2019 | 05/07/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 05/07/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 5/4/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 619299 | 01473 | 50 | Solar | 05_05_313W3 | 06/26/2024 | 07/24/2024 | 19 | 12 | 7 | 07/25/2024 | 07/25/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 |  | 11/15/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 652022 | 02725 | 5.76 | Solar | 05_12_2W1 | 11/13/2024 | 12/11/2024 | 7 | 6 | 1 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 178333 | 01532 | 7.6 | Solar | 05_14_16L4 | 11/17/2017 | 11/17/2017 | 37 | 36 | 1 | 01/12/2018 | 01/12/2018 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2018 |  | 11/22/2018 | N | EXP | 310 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 174816 | 01970 | 3000 | Solar | 05_14_48L1 | 07/31/2013 | 07/31/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/13/2013 | 09/24/2013 | 29 | 0 | 29 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2014 | 07/31/2013 | 9/15/2017 | Y | STD | 1187 |  |  | 0 | 0 | 0 | 9/15/2017 | 9/15/2017 | 9/27/2017 | Connected |  | N
National Grid | CHELMSFORD | 582729 | 01824 | 9.86 | Solar | 05_14_61L3 | 02/21/2024 | 04/09/2024 | 34 | 25 | 9 | 04/10/2024 | 04/10/2024 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 292693 | 01832 | 7.6 | Solar | 05_14_75L3 | 06/23/2020 | 06/24/2020 | 0 | 0 | 0 | 06/25/2020 | 06/25/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2020 | 06/23/2020 | 11/26/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2020 | Connected |  | N
National Grid | LAWRENCE | 575102 | 01843 | 9.6 | Solar | 05_01_21W2 | 12/19/2023 | 12/20/2023 | 1 | 1 | 0 | 12/21/2023 | 12/21/2023 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | DRACUT | 173709 | 01826 | 3.8 | Solar | 05_01_304W3 | 04/16/2018 | 04/16/2018 | 0 | 0 | 0 | 06/05/2018 | 06/05/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 365963 | 01611 | 7.6 | Solar | 05_01_413L7 | 08/10/2021 | 01/05/2022 | 2 | 0 | 2 | 08/13/2021 | 08/13/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 | 08/10/2021 | 6/3/2023 | Y | EXP | 365 | 03/01/2022 | 03/28/2022 | 28 | 0 | 28 |  |  | 6/15/2022 | Connected |  | N
National Grid | MILLBURY | 554299 | 01527 | 1999.998 | Solar | 05_01_612W1 | 04/23/2024 | 10/18/2024 | 123 | 116 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 | 05/06/2025 | 134 | 115 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | STURBRIDGE | 259604 | 01566 | 7.6 | Solar | 05_05_11W84 | 10/29/2019 | 10/30/2019 | 0 | 0 | 0 | 10/31/2019 | 10/31/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 |  | 10/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 620202 | 01473 | 3.8 | Solar | 05_05_313W3 | 06/24/2024 | 08/13/2024 | 35 | 30 | 5 | 08/14/2024 | 08/14/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 9/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2024 | Connected |  | N
National Grid | SWANSEA | 655422 | 02777 | 7.6 | Solar | 05_12_2W1 | 11/21/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/21/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 178633 | 01532 | 9 | Solar | 05_14_16L4 | 04/09/2018 | 04/09/2018 | 7 | 7 | 0 | 04/25/2018 | 04/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 175551 | 01970 | 196 | Solar | 05_14_48L1 | 04/07/2014 | 04/07/2014 | 8 | 0 | 8 | 04/18/2014 | 04/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2014 |  | 10/1/2014 | N | EXP | 141 |  |  | 0 | 0 | 0 | 6/18/2014 | 6/18/2014 | 5/27/2015 | Connected |  | N
National Grid | CHELMSFORD | 590957 | 01824 | 3.8 | Solar | 05_14_61L3 | 02/29/2024 | 03/06/2024 | 5 | 2 | 3 | 03/07/2024 | 03/07/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 02/29/2024 | 3/21/2025 | Y | EXP | 365 | 05/16/2024 | 05/21/2024 | 6 | 0 | 6 |  |  | 5/23/2024 | Connected |  | N
National Grid | HAVERHILL | 377474 | 01832 | 237.5 | Solar | 05_14_75L3 | 08/30/2021 | 10/07/2021 | 28 | 18 | 10 | 10/08/2021 | 10/08/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 643792 | 01843 | 5.76 | Solar | 05_01_21W2 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/01/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | DRACUT | 175254 | 01826 | 6.88 | Solar | 05_01_304W3 | 11/05/2014 | 11/05/2014 | 5 | 0 | 5 | 11/14/2014 | 11/14/2014 | 147 | 0 | 147 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2014 |  | 1/30/2015 | N | EXP | 53 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 404096 | 01524 | 7.6 | Solar | 05_01_413L7 | 12/30/2021 | 01/26/2022 | 17 | 15 | 2 | 01/27/2022 | 01/27/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2022 |  | 8/2/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  | 7/10/2023 | Connected |  | N
National Grid | MILLBURY | 553455 | 01527 | 120 | Solar | 05_01_612W1 | 09/11/2023 | 09/29/2023 | 15 | 5 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | STURBRIDGE | 274437 | 01566 | 6 | Solar | 05_05_11W84 | 01/30/2020 | 02/11/2020 | 7 | 3 | 4 | 02/12/2020 | 02/12/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 | 01/30/2020 | 2/5/2021 | Y | EXP | 365 | 06/25/2020 | 08/12/2020 | 48 | 0 | 48 |  |  | 10/16/2020 | Connected |  | N
National Grid | WINCHENDON | 675814 | 01475 | 5.76 | Solar | 05_05_313W3 | 03/05/2025 | 03/11/2025 | 4 | 0 | 4 | 03/12/2025 | 03/12/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | SOMERSET | 663678 | 02725 | 7.6 | Solar | 05_12_2W1 | 01/03/2025 | 02/05/2025 | 11 | 6 | 5 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 194082 | 01532 | 9 | Solar | 05_14_16L4 | 09/19/2018 | 10/09/2018 | 1 | 0 | 1 | 10/10/2018 | 10/10/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 | 09/19/2018 | 10/31/2019 | Y | EXP | 365 | 03/07/2019 | 03/19/2019 | 12 | 0 | 12 |  |  | 5/25/2019 | Connected |  | N
National Grid | SALEM | 185025 | 01970 | 14.72 | Solar | 05_14_48L1 | 05/23/2018 | 05/23/2018 | 3 | 0 | 3 | 05/31/2018 | 05/31/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2018 |  | 6/5/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2018 | Connected |  | N
National Grid | CHELMSFORD | 595150 | 01824 | 7.6 | Solar | 05_14_61L3 | 03/29/2024 | 04/16/2024 | 11 | 7 | 4 | 04/17/2024 | 04/17/2024 | 26 | 21 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 387839 | 01832 | 50 | Solar | 05_14_75L3 | 11/01/2021 | 12/16/2021 | 31 | 23 | 8 | 12/17/2021 | 12/17/2021 | 65 | 50 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2022 | 11/01/2021 | 6/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | Y
National Grid | LAWRENCE | 645392 | 01843 | 7.6 | Solar | 05_01_21W2 | 10/07/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/07/2024 | 1/22/2026 | Y | EXP | 365 | 06/24/2025 | 07/08/2025 | 15 | 0 | 15 |  |  | 8/23/2025 | Connected |  | N
National Grid | METHUEN | 175251 | 01844 | 17.2 | Solar | 05_01_304W3 | 11/05/2014 | 11/05/2014 | 6 | 3 | 3 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 1/30/2015 | N | EXP | 71 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 4/19/2016 | Connected |  | N
National Grid | LEICESTER | 436971 | 01524 | 10 | Solar | 05_01_413L7 | 06/10/2022 | 06/13/2022 | 0 | 0 | 0 | 06/14/2022 | 06/14/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2022 | Connected |  | N
National Grid | MILLBURY | 579723 | 01527 | 3000 | Solar | 05_01_612W1 | 04/26/2024 | 10/18/2024 | 120 | 111 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 | 05/06/2025 | 134 | 115 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | STURBRIDGE | 290789 | 01566 | 10 | Solar | 05_05_11W84 | 05/06/2020 | 05/14/2020 | 5 | 5 | 0 | 05/15/2020 | 05/15/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2020 | 05/06/2020 | 5/7/2021 | Y | EXP | 365 | 07/02/2020 | 08/31/2020 | 59 | 0 | 59 |  |  | 9/2/2020 | Connected |  | N
National Grid | WINCHENDON | 684650 | 01475 | 20 | Solar | 05_05_313W3 | 04/11/2025 | 06/13/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | SWANSEA | 670542 | 02777 | 3.77 | Solar | 05_12_2W1 | 02/06/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 54 | 30 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 196414 | 01532 | 9.6 | Solar | 05_14_16L4 | 11/09/2018 | 12/07/2018 | 16 | 15 | 1 | 12/10/2018 | 12/10/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 187781 | 01970 | 179.9 | Solar | 05_14_48L1 | 06/12/2018 | 06/12/2018 | 1 | 0 | 1 | 06/14/2018 | 06/14/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2018 |  | 11/28/2019 | N | EXP | 526 |  |  | 0 | 0 | 0 |  |  | 12/20/2019 | Connected |  | N
National Grid | CHELMSFORD | 600825 | 01824 | 7.6 | Solar | 05_14_61L3 | 04/04/2024 | 05/23/2024 | 6 | 6 | 0 | 05/24/2024 | 05/24/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 | 04/04/2024 | 6/20/2025 | Y | EXP | 365 | 02/07/2025 | 02/06/2025 | 0 | 0 | 0 |  |  | 2/18/2025 | Connected |  | N
National Grid | HAVERHILL | 396830 | 01832 | 16 | Solar | 05_14_75L3 | 11/24/2021 | 12/22/2021 | 36 | 28 | 8 | 11/30/2021 | 11/30/2021 | 36 | 18 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  | 1/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2022 | Connected |  | N
National Grid | LAWRENCE | 646994 | 01843 | 7.6 | Solar | 05_01_21W2 | 10/28/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 175362 | 01844 | 336 | Solar | 05_01_304W3 | 11/14/2014 | 11/14/2014 | 4 | 1 | 3 | 11/21/2014 | 11/21/2014 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2015 |  | 3/31/2015 | N | EXP | 76 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 477664 | 01524 | 9.57 | Solar | 05_01_413L7 | 02/22/2023 | 02/23/2023 | 1 | 0 | 1 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 | 02/22/2023 | 8/21/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2023 | Connected |  | N
National Grid | MILLBURY | 729943 | 01527 |  | Battery Add-On | 05_01_612W1 | 10/29/2025 | 11/11/2025 | 1 | 0 | 1 | 12/18/2025 | 12/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 | 10/29/2025 | 1/23/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | STURBRIDGE | 292543 | 01566 | 3.8 | Solar | 05_05_11W84 | 06/25/2020 | 06/29/2020 | 1 | 0 | 1 | 06/30/2020 | 06/30/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 | 06/25/2020 | 8/1/2021 | Y | EXP | 365 | 12/16/2020 | 01/25/2021 | 40 | 0 | 40 |  |  | 2/9/2021 | Connected |  | N
National Grid | WINCHENDON | 695134 | 01475 | 16.34 | Solar | 05_05_313W3 | 06/02/2025 | 06/05/2025 | 3 | 0 | 3 | 06/06/2025 | 06/06/2025 | 31 | 17 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2025 | Connected |  | N
National Grid | SWANSEA | 706875 | 02777 | 5.76 | Solar | 05_12_2W1 | 07/24/2025 | 08/20/2025 | 1 | 0 | 1 | 08/21/2025 | 08/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 | 07/24/2025 | 9/25/2026 | Y | EXP | 365 | 11/14/2025 | 12/02/2025 | 19 | 0 | 19 |  |  | 12/17/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 203428 | 01532 | 3.8 | Solar | 05_14_16L4 | 12/27/2018 | 01/25/2019 | 19 | 19 | 0 | 01/28/2019 | 01/28/2019 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 191116 | 01970 | 1594 | Solar | 05_14_48L1 | 07/20/2018 | 08/24/2018 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2018 | 10/15/2018 | 36 | 16 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2020 | 07/20/2018 | 3/22/2024 | Y | STD | 275 | 08/29/2023 | 01/05/2024 | 130 | 3 | 127 |  |  | 2/28/2024 | Connected |  | N
National Grid | CHELMSFORD | 611921 | 01824 | 10 | Solar | 05_14_61L3 | 05/22/2024 | 06/21/2024 | 7 | 4 | 3 | 06/24/2024 | 06/24/2024 | 56 | 39 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 403697 | 01832 | 0 | Solar | 05_14_75L3 | 12/28/2021 | 01/05/2022 | 6 | 2 | 4 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 2/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2022 | Connected |  | N
National Grid | LAWRENCE | 662098 | 01843 | 0 | Solar | 05_01_21W2 | 01/09/2025 | 01/10/2025 | 1 | 0 | 1 | 01/13/2025 | 01/13/2025 | 75 | 53 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | DRACUT | 176069 | 01826 | 6 | Solar | 05_01_304W3 | 06/19/2015 | 06/19/2015 | 6 | 6 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2015 |  | 6/27/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 7/29/2016 | Connected |  | N
National Grid | LEICESTER | 505691 | 01524 | 15 | Solar | 05_01_413L7 | 03/02/2023 | 04/20/2023 | 34 | 25 | 9 | 04/21/2023 | 04/21/2023 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2023 |  | 6/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2023 | Connected |  | N
National Grid | MILLBURY | 751636 | 01527 | 5.76 | Solar | 05_01_612W1 | 02/17/2026 | 02/23/2026 | 2 | 0 | 2 | 03/24/2026 | 03/24/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STURBRIDGE | 298454 | 01566 | 23.4 | Solar | 05_05_11W84 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2020 |  | 12/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2021 | Connected |  | N
National Grid | WINCHENDON | 704593 | 01475 | 21.52 | Solar | 05_05_313W3 | 07/14/2025 | 07/23/2025 | 7 | 2 | 5 | 07/24/2025 | 07/24/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 | 07/14/2025 | 8/27/2026 | Y | EXP | 365 | 12/17/2025 | 02/06/2026 | 52 | 0 | 52 |  |  | 2/9/2026 | Connected |  | N
National Grid | SOMERSET | 175372 | 02725 | 820 | Natural Gas | 05_12_2W2 | 02/19/2014 | 02/19/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2014 | 03/21/2014 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2014 |  | 7/31/2014 | N | STD | 70 |  |  | 0 | 0 | 0 | 11/3/2015 | 11/3/2015 | 11/3/2015 | Connected |  | N
National Grid | NORTHBOROUGH | 290312 | 01532 | 9.6 | Solar | 05_14_16L4 | 05/07/2020 | 05/13/2020 | 3 | 0 | 3 | 05/13/2020 | 05/13/2020 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2020 |  | 4/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2021 | Connected |  | N
National Grid | SALEM | 357413 | 01970 | 290 | Solar | 05_14_48L1 | 06/24/2021 | 12/01/2021 | 109 | 99 | 10 |  |  | 121 | 96 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2022 | 06/24/2021 | 10/10/2024 | Y | STD | 408 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | CHELMSFORD | 612901 | 01824 | 7.6 | Solar | 05_14_61L3 | 05/29/2024 | 06/07/2024 | 1 | 0 | 1 | 06/10/2024 | 06/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2024 | 05/29/2024 | 8/5/2025 | Y | EXP | 365 | 01/29/2025 | 01/28/2025 | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | HAVERHILL | 405449 | 01832 | 7.54 | Solar | 05_14_75L3 | 03/01/2022 | 05/05/2022 | 47 | 45 | 2 | 05/06/2022 | 05/06/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 | 03/01/2022 | 10/1/2023 | Y | EXP | 365 | 09/20/2022 | 09/28/2022 | 9 | 0 | 9 |  |  | 1/17/2023 | Connected |  | N
National Grid | LAWRENCE | 667331 | 01843 | 10 | Solar | 05_01_21W2 | 01/23/2025 | 02/13/2025 | 2 | 0 | 2 | 02/14/2025 | 02/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 | 01/23/2025 | 4/7/2026 | Y | EXP | 365 | 08/05/2025 | 10/01/2025 | 58 | 0 | 58 |  |  | 11/20/2025 | Connected |  | N
National Grid | DRACUT | 176101 | 01826 | 7.6 | Solar | 05_01_304W3 | 06/19/2015 | 06/19/2015 | 5 | 5 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/28/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 4/19/2016 | Connected |  | N
National Grid | CHARLTON | 594094 | 01507 | 9.86 | Solar | 05_01_413L7 | 03/19/2024 | 04/18/2024 | 22 | 19 | 3 | 04/19/2024 | 04/19/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 174657 | 01527 | 2000 | Solar | 05_01_612W1 | 03/28/2011 | 03/28/2011 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 03/28/2011 | 12/31/2012 | Y | STD | 19 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 318194 | 01566 | 5.76 | Solar | 05_05_11W84 | 10/08/2020 | 10/20/2020 | 7 | 6 | 1 | 10/21/2020 | 10/21/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2021 | Connected |  | N
National Grid | WINCHENDON | 714034 | 01475 | 10.15 | Solar | 05_05_313W3 | 08/25/2025 | 09/02/2025 | 4 | 2 | 2 | 09/03/2025 | 09/03/2025 | 61 | 42 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | SWANSEA | 176003 | 02777 | 9.46 | Solar | 05_12_2W2 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 | 08/11/2015 | 7/27/2018 | Y | EXP | 1053 | 11/07/2017 | 05/03/2018 | 177 | 0 | 177 |  |  | 7/25/2018 | Connected |  | N
National Grid | NORTHBOROUGH | 337957 | 01532 | 7.6 | Solar | 05_14_16L4 | 01/21/2021 | 02/17/2021 | 18 | 17 | 1 | 02/18/2021 | 02/18/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2021 | Connected |  | N
National Grid | SALEM | 595357 | 01970 | 9.57 | Solar | 05_14_48L1 | 03/13/2024 | 03/19/2024 | 4 | 0 | 4 | 03/20/2024 | 03/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 | 03/13/2024 | 4/9/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | CHELMSFORD | 614068 | 01824 | 5.76 | Solar | 05_14_61L3 | 05/29/2024 | 06/18/2024 | 12 | 11 | 1 | 06/20/2024 | 06/20/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 | 05/29/2024 | 7/23/2025 | Y | EXP | 365 | 08/29/2024 | 12/03/2024 | 97 | 0 | 97 |  |  | 3/18/2025 | Connected |  | N
National Grid | HAVERHILL | 423047 | 01832 | 150 | Solar | 05_14_75L3 | 04/14/2022 | 05/24/2022 | 27 | 19 | 8 | 05/25/2022 | 05/25/2022 | 50 | 27 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 |  | 11/27/2023 | N | EXP | 154 |  |  | 0 | 0 | 0 |  |  | 10/18/2023 | Connected |  | N
National Grid | LAWRENCE | 670752 | 01843 | 7.6 | Solar | 05_01_21W2 | 02/07/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176140 | 01844 | 6.88 | Solar | 05_01_304W3 | 06/26/2015 | 06/26/2015 | 0 | 0 | 0 | 07/01/2015 | 07/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 |  | 7/6/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 4/27/2016 | 4/27/2016 | 6/22/2016 | Connected |  | N
National Grid | LEICESTER | 595438 | 01611 | 46 | Solar | 05_01_413L7 | 03/08/2024 | 03/12/2024 | 2 | 0 | 2 | 03/13/2024 | 03/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 174753 | 01527 | 24.73 | Solar | 05_01_612W1 | 01/31/2014 | 01/31/2014 | 6 | 0 | 6 | 02/11/2014 | 02/11/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2014 |  | 4/30/2014 | N | EXP | 6 |  |  | 0 | 0 | 0 | 7/10/2014 | 7/10/2014 | 8/26/2014 | Connected |  | N
National Grid | STURBRIDGE | 322573 | 01566 | 22.05 | Solar | 05_05_11W84 | 02/08/2021 | 02/25/2021 | 11 | 8 | 3 | 02/26/2021 | 02/26/2021 | 66 | 41 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  | 9/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2021 | Connected |  | Y
National Grid | WINCHENDON | 729724 | 01475 | 12.16 | Solar | 05_05_313W3 | 11/04/2025 | 11/05/2025 | 1 | 0 | 1 | 11/06/2025 | 11/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2026 | Connected |  | N
National Grid | SWANSEA | 198887 | 02777 | 900 | Natural Gas | 05_12_2W2 | 10/19/2018 | 11/09/2018 | 15 | 4 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 | 04/02/2019 | 96 | 76 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2020 | 10/19/2018 |  | Y | STD | 365 | 02/25/2020 | 02/24/2020 | 0 | 0 | 0 |  |  | 4/3/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 398325 | 01532 | 9.772 | Solar | 05_14_16L4 | 11/30/2021 | 12/20/2021 | 14 | 13 | 1 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 | 11/30/2021 | 4/15/2023 | Y | EXP | 365 | 04/12/2022 | 04/13/2022 | 2 | 0 | 2 |  |  | 5/20/2022 | Connected |  | N
National Grid | SALEM | 627023 | 01970 | 10 | Solar | 05_14_48L1 | 07/23/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 07/23/2024 | 9/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | CHELMSFORD | 634009 | 01824 | 10 | Solar | 05_14_61L3 | 09/10/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | HAVERHILL | 454191 | 01830 | 3.48 | Solar | 05_14_75L3 | 09/13/2022 | 09/15/2022 | 2 | 0 | 2 | 09/16/2022 | 09/16/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2022 |  | 2/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2023 | Connected |  | N
National Grid | LAWRENCE | 680083 | 01843 | 22.672 | Solar | 05_01_21W2 | 04/15/2025 | 04/25/2025 | 7 | 0 | 7 | 04/28/2025 | 04/28/2025 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | DRACUT | 176387 | 01826 | 11.4 | Solar | 05_01_304W3 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 260 | 0 | 260 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 |  | 2/6/2017 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 615975 | 01524 | 17.48 | Solar | 05_01_413L7 | 06/10/2024 | 07/11/2024 | 22 | 19 | 3 | 07/12/2024 | 07/12/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | MILLBURY | 176230 | 01527 | 500 | Solar | 05_01_612W1 | 02/11/2015 | 02/11/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 | 04/09/2015 | 07/24/2015 | 72 | 0 | 72 | 02/23/2015 | 03/24/2015 | 20 | 0 | 20 | 07/24/2015 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 348299 | 01566 | 433.3 | Solar | 05_05_11W84 | 06/09/2021 | 08/11/2021 | 44 | 35 | 9 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2022 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 174586 | 01475 | 155 | Solar | 05_05_313W4 | 08/30/2011 | 08/30/2011 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2011 |  | 10/31/2012 | N | EXP | 335 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 7/3/2012 | Connected |  | N
National Grid | SOMERSET | 213359 | 02725 | 0 | Solar | 05_12_2W2 | 03/12/2019 | 03/21/2019 | 6 | 0 | 6 | 03/22/2019 | 03/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  | 4/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 402022 | 01532 | 187.5 | Solar | 05_14_16L4 | 12/20/2021 | 01/06/2022 | 13 | 5 | 8 |  |  | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 11/28/2024 | N | STD | 21 |  |  | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | N
National Grid | SALEM | 632030 | 01970 | 7.6 | Solar | 05_14_48L1 | 08/12/2024 | 08/26/2024 | 3 | 0 | 3 | 08/27/2024 | 08/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 635906 | 01824 | 5.76 | Solar | 05_14_61L3 | 08/27/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 08/27/2024 | 10/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | HAVERHILL | 557324 | 01832 | 3.8 | Solar | 05_14_75L3 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 79 | 24 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 712833 | 01843 | 7.6 | Solar | 05_01_21W2 | 08/27/2025 | 09/15/2025 | 12 | 9 | 3 | 09/16/2025 | 09/16/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2026 | Connected |  | N
National Grid | METHUEN | 176551 | 01844 | 7.6 | Solar | 05_01_304W3 | 10/05/2015 | 10/05/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2015 |  | 10/13/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/23/2016 | 8/23/2016 | 8/23/2016 | Connected |  | N
National Grid | LEICESTER | 623119 | 01542 | 9.86 | Solar | 05_01_413L7 | 07/08/2024 | 07/31/2024 | 14 | 12 | 2 | 08/01/2024 | 08/01/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/08/2024 | 8/26/2025 | Y | EXP | 365 | 08/30/2024 | 10/03/2024 | 35 | 0 | 35 |  |  | 10/24/2024 | Connected |  | N
National Grid | MILLBURY | 176256 | 01527 | 2000 | Solar | 05_01_612W1 | 07/09/2015 | 07/09/2015 | 18 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2015 | 08/26/2015 | 15 | 0 | 15 |  | 0 | 0 | 0 | 07/01/2016 | 07/20/2016 | 12 | 0 | 12 | 7/6/2016 | 07/09/2015 | 8/31/2018 | Y | STD | 786 | 04/30/2018 | 06/05/2018 | 36 | 0 | 36 |  |  | 8/10/2018 | Connected |  | N
National Grid | STURBRIDGE | 383131 | 01566 | 0 | Other | 05_05_11W84 | 11/29/2021 | 03/24/2022 | 80 | 70 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/25/2022 | 03/27/2022 | 2 | 0 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 174651 | 01475 | 125 | Solar | 05_05_313W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N
National Grid | SOMERSET | 676951 | 02725 | 10 | Solar | 05_12_2W2 | 03/10/2025 | 04/03/2025 | 2 | 0 | 2 | 04/14/2025 | 04/14/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 418467 | 01532 | 6 | Solar | 05_14_16L4 | 04/08/2022 | 04/11/2022 | 1 | 0 | 1 | 04/12/2022 | 04/12/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 04/08/2022 | 9/11/2023 | Y | EXP | 365 | 08/09/2022 | 08/29/2022 | 21 | 0 | 21 |  |  | 12/9/2022 | Connected |  | N
National Grid | SALEM | 652477 | 01970 | 5.76 | Solar | 05_14_48L1 | 11/19/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 637769 | 01824 | 7.6 | Solar | 05_14_61L3 | 09/04/2024 | 09/18/2024 | 1 | 0 | 1 | 09/19/2024 | 09/19/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 559163 | 01830 | 250 | Solar | 05_14_75L3 | 11/03/2023 | 11/21/2023 | 12 | 0 | 12 |  |  | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 680372 | 01843 | 0 | Battery Add-On | 05_01_225W1 | 03/25/2025 | 05/22/2025 | 40 | 36 | 4 | 05/23/2025 | 05/23/2025 | 114 | 96 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 176946 | 01826 | 3.8 | Solar | 05_01_304W3 | 12/21/2016 | 12/21/2016 | 4 | 3 | 1 | 12/28/2016 | 12/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 12/26/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 8/17/2017 | 8/17/2017 | 8/16/2017 | Connected |  | N
National Grid | CHARLTON | 642171 | 01507 | 23 | Solar | 05_01_413L7 | 10/18/2024 | 10/23/2024 | 4 | 2 | 2 | 10/24/2024 | 10/24/2024 | 70 | 58 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | MILLBURY | 176274 | 01527 | 984 | Solar | 05_01_612W1 | 02/19/2015 | 03/02/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2015 | 03/31/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2016 | 02/19/2015 | 12/31/2019 | Y | STD | 1229 | 06/08/2019 | 06/07/2019 | 0 | 0 | 0 | 10/15/2019 | 12/4/2019 | 12/27/2019 | Connected |  | N
National Grid | STURBRIDGE | 394593 | 01566 | 78.8 | Solar | 05_05_11W84 | 11/15/2021 | 11/30/2021 | 10 | 2 | 8 | 12/01/2021 | 12/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 | 11/15/2021 | 4/10/2023 | Y | EXP | 386 |  |  | 0 | 0 | 0 |  |  | 2/16/2023 | Connected |  | N
National Grid | WINCHENDON | 174650 | 01475 | 110 | Solar | 05_05_313W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N
National Grid | SWANSEA | 676829 | 02777 | 7.6 | Solar | 05_12_2W2 | 03/10/2025 | 03/27/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 03/10/2025 | 6/16/2026 | Y | EXP | 365 | 08/28/2025 | 10/29/2025 | 63 | 0 | 63 |  |  | 11/13/2025 | Connected |  | N
National Grid | MARLBOROUGH | 441231 | 01752 | 6 | Solar | 05_14_16L4 | 07/28/2022 | 07/29/2022 | 1 | 0 | 1 | 08/01/2022 | 08/01/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2022 | 07/28/2022 | 12/22/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2023 | Connected |  | N
National Grid | SALEM | 683789 | 01970 | 5.76 | Solar | 05_14_48L1 | 04/08/2025 | 04/28/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 | 04/08/2025 | 7/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | CHELMSFORD | 641933 | 01824 | 6 | Solar | 05_14_61L3 | 09/20/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 09/20/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | HAVERHILL | 559958 | 01832 | 10 | Solar | 05_14_75L3 | 10/19/2023 | 10/26/2023 | 5 | 4 | 1 | 10/27/2023 | 10/27/2023 | 44 | 19 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 | 10/19/2023 | 1/7/2025 | Y | EXP | 365 | 03/06/2024 | 03/26/2024 | 21 | 0 | 21 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 685002 | 01843 | 5000 | Solar | 05_01_225W1 | 12/19/2025 | 01/30/2026 | 25 | 22 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2026 | 03/17/2026 | 30 | 15 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 177867 | 01844 | 7.6 | Solar | 05_01_304W3 | 08/09/2017 | 08/09/2017 | 4 | 4 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/15/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 3/29/2018 | 3/29/2018 | 3/29/2018 | Connected |  | N
National Grid | BOLTON | 691149 | 01740 | 15.2 | Solar | 05_01_413L7 | 05/19/2025 | 05/22/2025 | 3 | 0 | 3 | 05/23/2025 | 05/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2025 |  | 7/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | MILLBURY | 176273 | 01527 | 984 | Solar | 05_01_612W1 | 02/19/2015 | 03/02/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2015 | 03/31/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2016 | 02/19/2015 | 12/31/2019 | Y | STD | 1229 | 06/08/2019 | 06/07/2019 | 0 | 0 | 0 | 10/9/2019 | 12/4/2019 | 12/27/2019 | Connected |  | N
National Grid | STURBRIDGE | 433811 | 01566 | 10 | Solar | 05_05_11W84 | 05/27/2022 | 07/21/2022 | 0 | 0 | 0 | 07/22/2022 | 07/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2022 | 05/27/2022 | 1/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2023 | Connected |  | N
National Grid | WINCHENDON | 174730 | 01475 | 100 | Solar | 05_05_313W4 | 08/22/2012 | 08/22/2012 | 7 | 0 | 7 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 12/12/2013 | 12/12/2013 | 12/13/2013 | Connected |  | N
National Grid | SOMERSET | 311130 | 02726 | 7.6 | Solar | 05_12_35J1 | 09/30/2020 | 10/06/2020 | 3 | 0 | 3 | 10/07/2020 | 10/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 9/1/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 468824 | 01752 | 6.144 | Solar | 05_14_16L4 | 03/22/2023 | 03/24/2023 | 2 | 0 | 2 | 03/27/2023 | 03/27/2023 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 03/22/2023 | 7/13/2024 | Y | EXP | 365 | 07/06/2023 | 07/13/2023 | 8 | 0 | 8 |  |  | 9/23/2023 | Connected |  | N
National Grid | SALEM | 705677 | 01970 | 8.027 | Solar | 05_14_48L1 | 07/17/2025 | 08/04/2025 | 7 | 3 | 4 | 08/20/2025 | 08/20/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2025 | Connected |  | N
National Grid | CHELMSFORD | 643919 | 01824 | 7.6 | Solar | 05_14_61L3 | 09/30/2024 | 11/04/2024 | 13 | 11 | 2 | 11/05/2024 | 11/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 09/30/2024 | 1/8/2026 | Y | EXP | 365 | 08/07/2025 | 09/06/2025 | 31 | 0 | 31 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 538861 | 01832 | 15 | Solar | 05_14_75L3 | 07/12/2023 | 07/17/2023 | 3 | 0 | 3 | 07/18/2023 | 07/18/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 |  | 9/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2023 | Connected |  | Y
National Grid | LAWRENCE | 684346 | 01843 | 7.6 | Solar | 05_01_225W1 | 04/10/2025 | 04/29/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 42 | 29 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DRACUT | 184779 | 01826 | 249.8 | Solar | 05_01_304W3 | 05/08/2018 | 05/08/2018 | 20 | 4 | 16 | 06/07/2018 | 06/07/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2018 | 05/08/2018 | 7/16/2020 | Y | EXP | 663 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 306145 | 01523 | 0 | Other | 05_01_415L1 | 09/08/2020 | 10/02/2020 | 18 | 13 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2020 | 10/26/2020 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/08/2020 |  | Y | STD | 700 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILLBURY | 176430 | 01527 | 2000 | Solar | 05_01_612W1 | 02/04/2016 | 02/04/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2016 | 03/07/2016 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/9/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 433519 | 01566 | 10 | Solar | 05_05_11W84 | 07/14/2022 | 07/21/2022 | 5 | 0 | 5 | 07/22/2022 | 07/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2022 |  | 8/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2023 | Connected |  | N
National Grid | WINCHENDON | 174769 | 01475 | 110 | Solar | 05_05_313W4 | 08/27/2012 | 08/27/2012 | 10 | 4 | 6 | 09/13/2012 | 09/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 12/13/2013 | Connected |  | N
National Grid | SWANSEA | 514805 | 02777 | 6 | Solar | 05_12_35J1 | 04/07/2023 | 04/10/2023 | 1 | 0 | 1 | 04/11/2023 | 04/11/2023 | 25 | 0 | 25 | 06/26/2023 | 08/23/2023 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 08/23/2023 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 8/24/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 555930 | 01752 | 10 | Solar | 05_14_16L4 | 09/26/2023 | 09/28/2023 | 2 | 0 | 2 | 09/29/2023 | 09/29/2023 | 21 | 0 | 21 | 12/05/2023 | 01/17/2024 | 22 | 3 | 19 |  |  | 0 | 0 | 0 | 01/17/2024 | 22 | 3 | 19 |  |  | 0 | 0 | 0 | 1/10/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 707574 | 02151 | 17.48 | Solar | 05_14_48L1 | 07/25/2025 | 07/29/2025 | 2 | 0 | 2 | 07/30/2025 | 07/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | CHELMSFORD | 645579 | 01824 | 3.9 | Solar | 05_14_61L3 | 10/08/2024 | 10/17/2024 | 1 | 0 | 1 | 10/18/2024 | 10/18/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/08/2024 | 12/1/2025 | Y | EXP | 365 | 02/13/2025 | 03/06/2025 | 22 | 0 | 22 |  |  | 3/21/2025 | Connected |  | N
National Grid | HAVERHILL | 542582 | 01830 | 6.67 | Solar | 05_14_75L3 | 08/21/2023 | 09/19/2023 | 21 | 19 | 2 | 09/20/2023 | 09/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 692829 | 01843 | 999 | Solar | 05_01_225W1 | 11/18/2025 | 12/09/2025 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 01/06/2026 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DRACUT | 186422 | 01826 | 15.2 | Solar | 05_01_304W3 | 05/25/2018 | 05/25/2018 | 9 | 0 | 9 | 06/12/2018 | 06/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 637437 | 01740 | 499.9 | Solar | 05_01_415L1 | 09/17/2024 | 11/04/2024 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2024 | 03/13/2025 | 87 | 67 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | MILLBURY | 176700 | 01527 | 1980 | Solar | 05_01_612W1 | 04/22/2016 | 04/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2016 | 06/03/2016 | 27 | 21 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/1/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 471482 | 01507 | 7.6 | Solar | 05_05_11W84 | 11/18/2022 | 11/28/2022 | 6 | 4 | 2 | 11/29/2022 | 11/29/2022 | 393 | 51 | 342 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 175199 | 01475 | 125 | Solar | 05_05_313W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N
National Grid | SWANSEA | 544704 | 02777 | 100 | Solar | 05_12_35J1 | 08/02/2023 | 10/24/2023 | 57 | 48 | 9 | 10/25/2023 | 10/25/2023 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 9/22/2024 | N | EXP | 86 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | MARLBOROUGH | 589144 | 01752 | 3.8 | Solar | 05_14_16L4 | 02/22/2024 | 02/26/2024 | 3 | 1 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/22/2024 | 4/22/2025 | Y | EXP | 365 | 06/19/2024 | 07/25/2024 | 37 | 0 | 37 |  |  | 8/21/2024 | Connected |  | N
National Grid | REVERE | 711691 | 02151 | 4.537 | Solar | 05_14_48L1 | 08/15/2025 | 09/04/2025 | 16 | 12 | 4 | 10/01/2025 | 10/01/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 647544 | 01824 | 5.76 | Solar | 05_14_61L3 | 10/22/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 45 | 21 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 10/22/2024 | 2/25/2026 | Y | EXP | 365 | 12/20/2025 | 02/02/2026 | 45 | 0 | 45 |  |  | 2/19/2026 | Connected |  | Y
National Grid | HAVERHILL | 574265 | 01830 | 6 | Solar | 05_14_75L3 | 12/04/2023 | 12/06/2023 | 2 | 0 | 2 | 12/07/2023 | 12/07/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 | 12/04/2023 | 3/5/2025 | Y | EXP | 365 | 09/05/2024 | 10/17/2024 | 43 | 0 | 43 |  |  | 10/24/2024 | Connected |  | N
National Grid | LAWRENCE | 720104 | 01843 | 11.5 | Solar | 05_01_225W1 | 09/18/2025 | 10/16/2025 | 2 | 0 | 2 | 10/23/2025 | 10/23/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 200350 | 01826 | 7.6 | Solar | 05_01_304W3 | 11/05/2018 | 11/14/2018 | 5 | 0 | 5 | 11/15/2018 | 11/15/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  | 3/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2020 | Connected |  | N
National Grid | LANCASTER | 656358 | 01523 | 487.5 | Solar | 05_01_415L1 | 12/06/2024 | 02/12/2025 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2025 | 03/13/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | MILLBURY | 176699 | 01527 | 288 | Solar | 05_01_612W1 | 04/22/2016 | 04/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2016 | 05/27/2016 | 23 | 16 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/1/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 485618 | 01566 | 10 | Solar | 05_05_11W84 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 | 01/10/2023 | 4/22/2024 | Y | EXP | 365 | 07/04/2023 | 07/12/2023 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 176206 | 01475 | 15.6 | Solar | 05_05_313W4 | 04/24/2015 | 04/24/2015 | 6 | 6 | 0 | 05/05/2015 | 05/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 |  | 8/31/2015 | N | EXP | 111 |  |  | 0 | 0 | 0 | 3/23/2016 | 3/23/2016 | 3/23/2016 | Connected |  | N
National Grid | SWANSEA | 598590 | 02777 | 7.6 | Solar | 05_12_35J1 | 03/21/2024 | 03/26/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | MARLBOROUGH | 637093 | 01752 | 10 | Solar | 05_14_16L4 | 09/02/2024 | 09/16/2024 | 1 | 0 | 1 | 09/17/2024 | 09/17/2024 | 20 | 13 | 7 | 12/13/2024 | 12/30/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 12/30/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 1/23/2026 | N | EXP | 365 | 06/06/2025 | 06/13/2025 | 8 | 0 | 8 |  |  | 7/9/2025 | Connected |  | N
National Grid | REVERE | 733818 | 02151 | 3.8 | Solar | 05_14_48L1 | 11/14/2025 | 12/02/2025 | 1 | 0 | 1 | 01/02/2026 | 01/02/2026 | 61 | 24 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 647901 | 01824 | 10 | Solar | 05_14_61L3 | 10/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 592634 | 01832 | 50 | Solar | 05_14_75L3 | 02/26/2024 | 04/03/2024 | 27 | 18 | 9 | 04/04/2024 | 04/04/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 5/15/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | LAWRENCE | 726260 | 01843 | 0 | Battery Add-On | 05_01_225W1 | 10/14/2025 | 10/16/2025 | 2 | 0 | 2 | 10/17/2025 | 10/17/2025 | 76 | 66 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 202103 | 01826 | 3.8 | Solar | 05_01_304W3 | 11/27/2018 | 12/20/2018 | 4 | 0 | 4 | 12/21/2018 | 12/21/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2019 | 11/27/2018 | 5/14/2020 | Y | EXP | 482 | 11/23/2019 | 01/03/2020 | 41 | 0 | 41 |  |  | 2/27/2020 | Connected |  | N
National Grid | HARVARD | 697596 | 01451 | 15.08 | Solar | 05_01_415L1 | 06/10/2025 | 06/12/2025 | 2 | 0 | 2 | 06/13/2025 | 06/13/2025 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILLBURY | 176920 | 01527 | 3100 | Solar | 05_01_612W1 | 11/16/2015 | 11/16/2015 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2015 | 12/28/2015 | 22 | 0 | 22 |  | 0 | 0 | 0 | 04/12/2017 | 05/15/2018 | 275 | 0 | 275 | 8/25/2016 | 11/16/2015 | 10/22/2018 | Y | STD | 788 | 05/02/2018 | 07/05/2018 | 64 | 0 | 64 |  |  | 9/25/2018 | Connected |  | N
National Grid | STURBRIDGE | 494490 | 01566 | 10 | Solar | 05_05_11W84 | 01/26/2023 | 01/30/2023 | 2 | 0 | 2 | 01/31/2023 | 01/31/2023 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2023 | 01/26/2023 | 9/14/2024 | Y | EXP | 365 | 06/24/2023 | 09/14/2023 | 83 | 0 | 83 |  |  | 9/20/2023 | Connected |  | N
National Grid | WINCHENDON | 176862 | 01475 | 10 | Solar | 05_05_313W4 | 01/21/2016 | 01/21/2016 | 3 | 3 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 1/26/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 7/19/2016 | Connected |  | N
National Grid | SOMERSET | 632210 | 02725 | 10 | Solar | 05_12_35J1 | 08/13/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 | 08/13/2024 | 3/25/2026 | Y | EXP | 365 | 12/21/2024 | 09/10/2025 | 264 | 0 | 264 |  |  | 9/17/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 644852 | 01532 | 7.6 | Solar | 05_14_16L4 | 10/03/2024 | 10/31/2024 | 4 | 0 | 4 | 11/01/2024 | 11/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2024 | 10/03/2024 | 12/17/2025 | Y | EXP | 365 | 01/16/2025 | 03/03/2025 | 46 | 0 | 46 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 703899 | 02151 | 6 | Solar | 05_14_48L2 | 07/10/2025 | 08/13/2025 | 3 | 0 | 3 | 08/14/2025 | 08/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 | 07/10/2025 | 10/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | CHELMSFORD | 651538 | 01824 | 7.6 | Solar | 05_14_61L3 | 11/12/2024 | 12/02/2024 | 3 | 0 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/12/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | HAVERHILL | 631905 | 01830 | 14.5 | Solar | 05_14_75L3 | 08/14/2024 | 08/23/2024 | 7 | 4 | 3 | 08/26/2024 | 08/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | LAWRENCE | 739094 | 01843 | 0 | Battery Add-On | 05_01_225W1 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 63 | 45 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | DRACUT | 201445 | 01826 | 7.6 | Solar | 05_01_304W3 | 11/17/2018 | 12/03/2018 | 7 | 5 | 2 | 12/04/2018 | 12/04/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 10/21/2019 | N | EXP | 304 |  |  | 0 | 0 | 0 |  |  | 9/12/2019 | Connected |  | N
National Grid | BOLTON | 731442 | 01740 | 11.5 | Solar | 05_01_415L1 | 11/13/2025 | 11/20/2025 | 5 | 4 | 1 | 11/21/2025 | 11/21/2025 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILLBURY | 177177 | 01527 | 144 | Solar | 05_01_612W1 | 06/02/2016 | 06/02/2016 | 5 | 5 | 0 | 06/10/2016 | 06/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2016 |  | 6/8/2017 | N | EXP | 329 |  |  | 0 | 0 | 0 | 11/16/2016 | 11/16/2016 | 11/16/2016 | Connected |  | N
National Grid | CHARLTON | 515758 | 01507 | 15.2 | Solar | 05_05_11W84 | 07/17/2023 | 04/07/2023 | 1 | 0 | 1 | 07/19/2023 | 07/19/2023 | 100 | 78 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2023 |  | 1/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2024 | Connected |  | N
National Grid | WINCHENDON | 177487 | 01475 | 5.2 | Solar | 05_05_313W4 | 09/23/2016 | 09/23/2016 | 3 | 3 | 0 | 09/29/2016 | 09/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 |  | 10/1/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 | 5/10/2017 | 5/10/2017 | 5/12/2017 | Connected |  | N
National Grid | SWANSEA | 633469 | 02777 | 6 | Solar | 05_12_35J1 | 08/19/2024 | 08/27/2024 | 5 | 0 | 5 | 08/28/2024 | 08/28/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 666027 | 01532 | 13.36 | Solar | 05_14_16L4 | 01/17/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 28 | 8 | 20 | 04/22/2025 | 06/05/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 06/05/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 6/10/2025 | 01/17/2025 | 6/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | REVERE | 730051 | 02151 | 150 | Solar | 05_14_48L2 | 10/30/2025 | 11/24/2025 | 16 | 7 | 9 | 11/25/2025 | 11/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2026 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHELMSFORD | 651823 | 01824 | 5.76 | Solar | 05_14_61L3 | 11/13/2024 | 03/13/2025 | 68 | 63 | 5 | 03/14/2025 | 03/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2025 | Connected |  | N
National Grid | HAVERHILL | 644476 | 01830 | 7.6 | Solar | 05_14_75L3 | 10/16/2024 | 11/01/2024 | 3 | 0 | 3 | 11/04/2024 | 11/04/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/16/2024 | 12/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | LAWRENCE | 750984 | 01843 | 10 | Solar | 05_01_225W1 | 02/12/2026 | 02/13/2026 | 1 | 0 | 1 | 02/17/2026 | 02/17/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2026 |  | 3/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 207293 | 01826 | 10 | Solar | 05_01_304W3 | 01/31/2019 | 02/11/2019 | 6 | 6 | 0 | 02/12/2019 | 02/12/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 01/31/2019 | 10/17/2019 | Y | EXP | 238 | 04/23/2019 | 05/30/2019 | 37 | 0 | 37 |  |  | 6/24/2019 | Connected |  | N
National Grid | LANCASTER | 741796 | 01523 | 10 | Solar | 05_01_415L1 | 12/22/2025 | 12/23/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILLBURY | 177187 | 01527 | 498 | Solar | 05_01_612W1 | 08/12/2016 | 08/12/2016 | 30 | 30 | 0 | 09/28/2016 | 09/28/2016 | 116 | 25 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/21/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 532784 | 01507 | 0 | Other | 05_05_11W84 | 08/15/2023 | 10/05/2023 | 37 | 27 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2023 | 12/06/2023 | 42 | 23 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 186922 | 01475 | 230 | Solar | 05_05_313W4 | 06/01/2018 | 06/01/2018 | 4 | 0 | 4 | 06/15/2018 | 06/15/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2018 |  | 12/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2020 | Connected |  | N
National Grid | SWANSEA | 641020 | 02777 | 6 | Solar | 05_12_35J1 | 09/17/2024 | 10/08/2024 | 5 | 0 | 5 | 10/09/2024 | 10/09/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/17/2024 | 11/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 672940 | 01532 | 3.8 | Solar | 05_14_16L4 | 02/19/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 100 | 86 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 744896 | 02151 | 10 | Solar | 05_14_48L2 | 01/14/2026 | 01/15/2026 | 9 | 6 | 3 | 03/06/2026 | 03/06/2026 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 651661 | 01851 | 5.76 | Solar | 05_14_61L3 | 11/12/2024 | 02/18/2025 | 58 | 56 | 2 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | HAVERHILL | 651164 | 01832 | 9.28 | Solar | 05_14_75L3 | 10/31/2024 | 11/21/2024 | 3 | 1 | 2 | 11/22/2024 | 11/22/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | LAWRENCE | 754286 | 01843 |  | Solar | 05_01_225W1 | 03/04/2026 | 03/05/2026 | 2 | 0 | 2 | 03/17/2026 | 03/17/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 209039 | 01826 | 10 | Solar | 05_01_304W3 | 02/19/2019 | 03/29/2019 | 27 | 26 | 1 | 04/01/2019 | 04/01/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 | 02/19/2019 | 5/17/2021 | Y | EXP | 365 | 10/02/2020 | 12/08/2020 | 67 | 0 | 67 |  |  | 4/30/2021 | Connected |  | N
National Grid | BOLTON | 742734 | 01740 | 9.12 | Solar | 05_01_415L1 | 12/30/2025 | 01/05/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILLBURY | 177186 | 01527 | 498 | Solar | 05_01_612W1 | 08/12/2016 | 08/12/2016 | 30 | 30 | 0 | 09/28/2016 | 09/28/2016 | 116 | 25 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/21/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 549535 | 01507 | 0 | Solar | 05_05_11W84 | 08/23/2023 | 08/30/2023 | 6 | 4 | 2 | 08/31/2023 | 08/31/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 189709 | 01475 | 381.5 | Natural Gas | 05_05_313W4 | 07/03/2018 | 07/03/2018 | 32 | 23 | 9 |  |  | 24 | 0 | 24 | 10/19/2018 | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 10/30/2019 |  | 5/13/2020 | N | STD | 41 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N
National Grid | SWANSEA | 664554 | 02777 | 4.64 | Solar | 05_12_35J1 | 01/24/2025 | 03/05/2025 | 3 | 0 | 3 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 | 01/24/2025 | 4/8/2026 | Y | EXP | 365 | 09/23/2025 | 09/22/2025 | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | MARLBOROUGH | 677854 | 01752 | 7.6 | Solar | 05_14_16L4 | 03/17/2025 | 03/20/2025 | 3 | 0 | 3 | 03/21/2025 | 03/21/2025 | 100 | 80 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176994 | 02151 | 82 | Solar | 05_14_48L2 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2016 |  | 7/25/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 12/2/2016 | 12/2/2016 | 12/2/2016 | Connected |  | N
National Grid | CHELMSFORD | 654440 | 01824 | 7.6 | Solar | 05_14_61L3 | 11/14/2024 | 01/29/2025 | 3 | 0 | 3 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | HAVERHILL | 671868 | 01832 | 7.6 | Solar | 05_14_75L3 | 02/13/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2025 | Connected |  | N
National Grid | LAWRENCE | 757750 | 01843 | 13.8 | Solar | 05_01_225W1 | 03/20/2026 | 03/25/2026 | 3 | 0 | 3 | 03/26/2026 | 03/26/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 219923 | 01844 | 7.6 | Solar | 05_01_304W3 | 06/07/2019 | 06/18/2019 | 6 | 0 | 6 | 06/19/2019 | 06/19/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 | 06/07/2019 | 9/16/2020 | Y | EXP | 365 | 05/29/2020 | 06/23/2020 | 25 | 0 | 25 |  |  | 7/25/2020 | Connected |  | N
National Grid | LANCASTER | 747449 | 01523 | 9.12 | Solar | 05_01_415L1 | 02/11/2026 | 02/12/2026 | 1 | 0 | 1 | 02/27/2026 | 02/27/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MILLBURY | 177215 | 01527 | 60 | Solar | 05_01_612W1 | 06/10/2016 | 06/10/2016 | 7 | 7 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2016 |  | 6/18/2017 | N | EXP | 341 |  |  | 0 | 0 | 0 | 11/15/2016 | 11/15/2016 | 11/15/2016 | Connected |  | N
National Grid | CHARLTON | 565023 | 01507 | 5 | Solar | 05_05_11W84 | 10/25/2023 | 10/30/2023 | 4 | 2 | 2 | 10/31/2023 | 10/31/2023 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 1/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 191688 | 01475 | 133.2 | Solar | 05_05_313W4 | 07/24/2018 | 09/05/2018 | 26 | 17 | 9 | 09/06/2018 | 09/06/2018 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 |  | 9/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 752663 | 02725 | 11.4 | Solar | 05_12_35J2 | 02/23/2026 | 03/02/2026 | 2 | 0 | 2 | 03/13/2026 | 03/13/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 624477 | 01752 | 200 | Solar | 05_14_16L7 | 07/25/2024 | 08/26/2024 | 22 | 16 | 6 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 | 07/25/2024 | 12/17/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | REVERE | 177118 | 02151 | 510 | Solar | 05_14_48L2 | 10/19/2016 | 10/19/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/10/2017 | 50 | 39 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 655150 | 01824 | 10 | Solar | 05_14_61L3 | 11/20/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/20/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 674866 | 01830 | 3.8 | Solar | 05_14_75L3 | 03/06/2025 | 03/26/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 82 | 70 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 174116 | 01843 | 2000 | Solar | 05_01_225W1 | 03/30/2012 | 03/30/2012 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 219134 | 01844 | 4.56 | Solar | 05_01_304W3 | 07/01/2019 | 08/02/2019 | 22 | 18 | 4 | 08/05/2019 | 08/05/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 | 07/01/2019 | 8/3/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N
National Grid | LANCASTER | 754179 | 01523 | 31.41 | Solar | 05_01_415L1 | 03/16/2026 | 03/20/2026 | 4 | 2 | 2 | 03/23/2026 | 03/23/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MILLBURY | 177429 | 01527 | 4980 | Solar | 05_01_612W1 | 02/27/2017 | 03/29/2017 | 20 | 18 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2017 | 04/14/2017 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2017 | 02/27/2017 | 2/28/2020 | Y | STD | 771 | 10/04/2019 | 12/20/2019 | 77 | 0 | 77 |  |  | 1/30/2020 | Connected |  | N
National Grid | CHARLTON | 575399 | 01507 | 6 | Solar | 05_05_11W84 | 12/12/2023 | 12/19/2023 | 5 | 2 | 3 | 12/20/2023 | 12/20/2023 | 26 | 6 | 20 | 02/13/2024 | 03/07/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 03/07/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 2/29/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 285220 | 01475 | 15.2 | Solar | 05_05_313W4 | 03/25/2020 | 03/30/2020 | 2 | 0 | 2 | 03/31/2020 | 03/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2020 | Connected |  | N
National Grid | SWANSEA | 175751 | 02777 | 21.07 | Solar | 05_12_35J2 | 10/31/2014 | 10/31/2014 | 6 | 5 | 1 | 11/12/2014 | 11/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2014 | 10/31/2014 | 12/31/2016 | Y | EXP | 757 | 04/29/2016 | 04/30/2016 | 1 | 0 | 1 | 1/28/2015 | 1/28/2015 | 5/20/2016 | Connected |  | N
National Grid | MARLBOROUGH | 346400 | 01752 | 250 | Solar | 05_14_16L7 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 |  |  | 134 | 109 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 177188 | 02151 | 51 | Solar | 05_14_48L2 | 08/15/2016 | 08/15/2016 | 1 | 1 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 |  | 1/21/2018 | N | EXP | 510 |  |  | 0 | 0 | 0 | 12/20/2017 | 12/20/2017 | 1/8/2018 | Connected |  | N
National Grid | CHELMSFORD | 657463 | 01824 | 7.6 | Solar | 05_14_61L3 | 11/27/2024 | 01/06/2025 | 17 | 12 | 5 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | HAVERHILL | 681276 | 01832 | 0 | Solar | 05_14_75L3 | 03/31/2025 | 05/06/2025 | 26 | 23 | 3 | 05/07/2025 | 05/07/2025 | 36 | 24 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 174208 | 01843 | 450 | Solar | 05_01_225W1 | 02/29/2012 | 02/29/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/1/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 265736 | 01826 | 10 | Solar | 05_01_304W3 | 11/20/2019 | 11/21/2019 | 0 | 0 | 0 | 11/22/2019 | 11/22/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2019 | 11/20/2019 | 7/22/2020 | Y | EXP | 365 | 03/28/2020 | 03/30/2020 | 2 | 0 | 2 |  |  | 4/6/2020 | Connected |  | N
National Grid | LANCASTER | 174213 | 01523 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 178389 | 01527 | 15.2 | Solar | 05_01_612W1 | 03/01/2018 | 04/03/2018 | 11 | 11 | 0 | 04/03/2018 | 04/03/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/7/2019 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 626348 | 01507 | 9.92 | Solar | 05_05_11W84 | 07/19/2024 | 07/29/2024 | 2 | 0 | 2 | 07/30/2024 | 07/30/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/19/2024 | 8/21/2025 | Y | EXP | 365 | 09/06/2024 | 09/18/2024 | 13 | 0 | 13 |  |  | 10/31/2024 | Connected |  | N
National Grid | WINCHENDON | 286585 | 01475 | 250 | Solar | 05_05_313W4 | 04/07/2020 | 04/11/2020 | 2 | 0 | 2 | 04/13/2020 | 04/13/2020 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2020 |  | 6/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2021 | Connected |  | N
National Grid | SWANSEA | 240171 | 02777 | 10 | Solar | 05_12_35J2 | 07/11/2019 | 07/19/2019 | 6 | 6 | 0 | 07/22/2019 | 07/22/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 |  | 11/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 176414 | 01532 | 480 | Solar | 05_14_18L1 | 11/30/2015 | 11/30/2015 | 0 | 0 | 0 | 12/03/2015 | 12/03/2015 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 6/28/2018 | N | EXP | 786 |  |  | 0 | 0 | 0 |  |  | 6/22/2018 | Connected |  | N
National Grid | REVERE | 177362 | 02151 | 150 | Solar | 05_14_48L2 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2016 |  | 6/28/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 | 3/8/2017 | 3/8/2017 | 3/8/2017 | Connected |  | N
National Grid | LOWELL | 662558 | 01852 | 11.4 | Solar | 05_14_61L3 | 12/27/2024 | 01/08/2025 | 4 | 2 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/27/2024 | 4/28/2026 | Y | EXP | 365 | 08/19/2025 | 08/19/2025 | 1 | 0 | 1 |  |  | 8/22/2025 | Connected |  | N
National Grid | HAVERHILL | 682755 | 01830 | 5.76 | Solar | 05_14_75L3 | 04/03/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174207 | 01843 | 500 | Solar | 05_01_225W1 | 02/29/2012 | 02/29/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/1/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 330585 | 01826 | 3.12 | Solar | 05_01_304W3 | 12/29/2020 | 12/31/2020 | 1 | 0 | 1 | 01/04/2021 | 01/04/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 174212 | 01740 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 190055 | 01527 | 2000 | Solar | 05_01_612W1 | 07/18/2018 | 09/17/2018 | 160 | 0 | 160 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 01/03/2019 | 144 | 72 | 72 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 633817 | 01508 | 7.475 | Solar | 05_05_11W84 | 08/20/2024 | 08/23/2024 | 2 | 0 | 2 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 | 08/20/2024 | 12/18/2025 | Y | EXP | 365 | 01/03/2025 | 01/14/2025 | 12 | 0 | 12 |  |  | 1/23/2025 | Connected |  | N
National Grid | WINCHENDON | 326590 | 01475 | 11.4 | Solar | 05_05_313W4 | 11/17/2020 | 11/20/2020 | 2 | 0 | 2 | 11/23/2020 | 11/23/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 11/17/2020 | 9/9/2022 | Y | EXP | 365 | 06/12/2021 | 08/31/2021 | 80 | 3 | 77 |  |  | 9/13/2021 | Connected |  | N
National Grid | SOMERSET | 298672 | 02725 | 4.32 | Solar | 05_12_35J2 | 07/10/2020 | 07/17/2020 | 4 | 0 | 4 | 07/20/2020 | 07/20/2020 | 75 | 49 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2020 |  | 3/29/2022 | N | EXP | 545 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 177575 | 01532 | 480 | Solar | 05_14_18L1 | 09/19/2017 | 09/19/2017 | 28 | 19 | 9 | 11/03/2017 | 11/03/2017 | 12 | 12 | 0 | 02/09/2018 | 02/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 02/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 3/23/2018 |  | 9/24/2018 | N | EXP | 185 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | REVERE | 188201 | 02151 | 150 | Solar | 05_14_48L2 | 06/15/2018 | 06/15/2018 | 3 | 0 | 3 | 06/22/2018 | 06/22/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  | 12/2/2019 | N | EXP | 524 |  |  | 0 | 0 | 0 |  |  | 10/29/2019 | Connected |  | N
National Grid | BILLERICA | 670838 | 01821 | 3.8 | Solar | 05_14_61L3 | 02/07/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 691425 | 01830 | 19.195 | Solar | 05_14_75L3 | 05/19/2025 | 06/04/2025 | 10 | 6 | 4 | 06/05/2025 | 06/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | LAWRENCE | 174205 | 01843 | 4950 | Solar | 05_01_225W1 | 02/29/2012 | 02/29/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2012 | 05/22/2012 | 34 | 0 | 34 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2012 | 02/29/2012 | 1/1/2013 | Y | STD | 33 | 10/11/2013 | 12/03/2013 | 34 | 0 | 34 | 12/12/2013 | 12/12/2013 | 12/12/2013 | Connected |  | N
National Grid | DRACUT | 331259 | 01826 | 7.6 | Solar | 05_01_304W3 | 01/04/2021 | 01/21/2021 | 12 | 11 | 1 | 01/22/2021 | 01/22/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/04/2021 | 6/24/2023 | Y | EXP | 365 | 03/25/2022 | 06/17/2022 | 85 | 0 | 85 |  |  | 8/30/2022 | Connected |  | N
National Grid | BOLTON | 174211 | 01740 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 192564 | 01527 | 4950 | Solar | 05_01_612W1 | 08/21/2018 | 08/27/2018 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2018 | 09/28/2018 | 69 | 3 | 66 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 644735 | 01508 | 3.8 | Solar | 05_05_11W84 | 10/03/2024 | 10/29/2024 | 3 | 0 | 3 | 10/30/2024 | 10/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2025 | Connected |  | N
National Grid | WINCHENDON | 346371 | 01475 | 250 | Solar | 05_05_313W4 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 | 04/30/2021 | 04/30/2021 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2021 |  | 7/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 457238 | 02777 | 7.6 | Solar | 05_12_35J2 | 09/07/2022 | 09/09/2022 | 2 | 0 | 2 | 09/12/2022 | 09/12/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 |  | 11/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 189998 | 01532 | 15.2 | Solar | 05_14_18L1 | 07/05/2018 | 07/05/2018 | 2 | 0 | 2 | 07/11/2018 | 07/11/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 8/12/2019 | N | EXP | 392 |  |  | 0 | 0 | 0 |  |  | 8/14/2019 | Connected |  | N
National Grid | REVERE | 248292 | 02151 | 7.6 | Solar | 05_14_48L2 | 08/12/2019 | 08/14/2019 | 0 | 0 | 0 | 01/31/2020 | 01/31/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 | 08/12/2019 | 11/6/2020 | Y | EXP | 365 | 05/27/2020 | 06/11/2020 | 15 | 0 | 15 |  |  | 6/15/2020 | Connected |  | N
National Grid | BILLERICA | 672008 | 01821 | 15.2 | Solar | 05_14_61L3 | 02/13/2025 | 03/05/2025 | 14 | 10 | 4 | 03/06/2025 | 03/06/2025 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 727475 | 01830 | 11.5 | Solar | 05_14_75L3 | 10/17/2025 | 10/24/2025 | 4 | 3 | 1 | 10/27/2025 | 10/27/2025 | 71 | 60 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 174229 | 01843 | 26 | Solar | 05_01_225W1 | 12/08/2011 | 12/08/2011 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2012 |  | 12/30/2011 | N | EXP | 76 |  |  | 0 | 0 | 0 | 4/24/2012 | 4/24/2012 | 4/24/2012 | Connected |  | N
National Grid | METHUEN | 449447 | 01844 | 16.896 | Solar | 05_01_304W3 | 08/04/2022 | 08/31/2022 | 19 | 18 | 1 | 09/01/2022 | 09/01/2022 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 174362 | 01740 | 17 | Solar | 05_01_415L1 | 05/17/2012 | 05/17/2012 | 6 | 0 | 6 | 05/30/2012 | 05/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 7/31/2012 | N | EXP | 134 |  |  | 0 | 0 | 0 | 9/7/2012 | 9/7/2012 | 4/1/2013 | Connected |  | N
National Grid | MILLBURY | 205568 | 01527 | 984 | Solar | 05_01_612W1 | 02/22/2019 | 03/25/2019 | 21 | 14 | 7 |  |  | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 645472 | 01508 | 2.03 | Solar | 05_05_11W84 | 10/31/2024 | 11/20/2024 | 2 | 0 | 2 | 11/21/2024 | 11/21/2024 | 25 | 0 | 25 | 01/17/2025 | 01/28/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 01/28/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 471917 | 01475 | 3.8 | Solar | 05_05_313W4 | 11/08/2022 | 11/14/2022 | 3 | 0 | 3 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 487786 | 02725 | 6 | Solar | 05_12_35J2 | 01/11/2023 | 01/12/2023 | 2 | 1 | 1 | 01/13/2023 | 01/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 2/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | MARLBOROUGH | 268931 | 01752 | 3.8 | Solar | 05_14_18L1 | 12/18/2019 | 12/18/2019 | 0 | 0 | 0 | 12/19/2019 | 12/19/2019 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2020 |  | 12/18/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2020 | Connected |  | N
National Grid | REVERE | 300239 | 02151 | 3.8 | Solar | 05_14_48L2 | 07/17/2020 | 07/27/2020 | 5 | 0 | 5 | 07/28/2020 | 07/28/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2020 | 07/17/2020 | 6/18/2021 | Y | EXP | 365 | 01/13/2021 | 01/19/2021 | 6 | 0 | 6 |  |  | 2/12/2021 | Connected |  | N
National Grid | BILLERICA | 673492 | 01821 | 7.6 | Solar | 05_14_61L3 | 02/21/2025 | 03/26/2025 | 15 | 12 | 3 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 02/21/2025 | 5/12/2026 | Y | EXP | 365 | 07/24/2025 | 12/22/2025 | 152 | 0 | 152 |  |  | 12/26/2025 | Connected |  | N
National Grid | HAVERHILL | 744262 | 01832 | 5.76 | Solar | 05_14_75L3 | 01/08/2026 | 01/12/2026 | 2 | 0 | 2 | 01/22/2026 | 01/22/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 174878 | 01843 | 1800 | Solar | 05_01_225W1 | 02/06/2013 | 02/06/2013 | 210 | 207 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 427594 | 01826 | 15.66 | Solar | 05_01_304W3 | 06/26/2022 | 08/30/2022 | 47 | 44 | 3 | 08/31/2022 | 08/31/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2022 |  | 10/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 174548 | 01523 | 1000 | Solar | 05_01_415L1 | 11/08/2011 | 11/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 04/30/2014 | 08/01/2014 | 64 | 0 | 64 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 206008 | 01527 | 500 | Solar | 05_01_612W1 | 02/22/2019 | 03/25/2019 | 21 | 14 | 7 |  |  | 140 | 75 | 65 |  |  | 0 | 0 | 0 | 08/05/2019 | 08/02/2019 | 75 | 75 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 647182 | 01507 | 10 | Solar | 05_05_11W84 | 10/15/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | WINCHENDON | 483268 | 01475 | 10 | Solar | 05_05_313W4 | 12/14/2022 | 12/20/2022 | 4 | 0 | 4 | 12/21/2022 | 12/21/2022 | 28 | 4 | 24 | 02/06/2023 | 03/20/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 03/20/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 4/25/2024 | N | EXP | 365 | 04/08/2023 | 04/26/2023 | 19 | 0 | 19 |  |  | 7/20/2023 | Connected |  | N
National Grid | SOMERSET | 684658 | 02725 | 3.8 | Solar | 05_12_35J2 | 04/11/2025 | 05/05/2025 | 1 | 0 | 1 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 04/11/2025 | 6/9/2026 | Y | EXP | 365 | 10/03/2025 | 12/02/2025 | 61 | 0 | 61 |  |  | 12/3/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 268241 | 01532 | 3.8 | Solar | 05_14_18L1 | 12/05/2019 | 12/10/2019 | 3 | 3 | 0 | 12/11/2019 | 12/11/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2019 |  | 12/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 376194 | 02151 | 7.6 | Solar | 05_14_48L2 | 08/16/2021 | 10/15/2021 | 19 | 18 | 1 | 10/18/2021 | 10/18/2021 | 37 | 15 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 | 08/16/2021 | 4/16/2023 | Y | EXP | 365 | 01/12/2022 | 02/09/2022 | 29 | 0 | 29 |  |  | 4/22/2022 | Connected |  | N
National Grid | BILLERICA | 673460 | 01821 | 13.8 | Solar | 05_14_61L3 | 02/21/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 02/21/2025 | 5/27/2026 | Y | EXP | 365 | 10/25/2025 | 12/01/2025 | 38 | 0 | 38 |  |  | 12/9/2025 | Connected |  | N
National Grid | HAVERHILL | 194135 | 01832 | 130 | Solar | 05_14_75L4 | 08/23/2018 | 08/24/2018 | 0 | 0 | 0 | 08/27/2018 | 08/27/2018 | 103 | 26 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175575 | 01843 | 22.8 | Solar | 05_01_225W1 | 12/09/2014 | 12/09/2014 | 4 | 3 | 1 | 12/16/2014 | 12/16/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2014 |  | 2/28/2015 | N | EXP | 59 |  |  | 0 | 0 | 0 | 4/9/2015 | 4/9/2015 | 9/25/2015 | Connected |  | N
National Grid | DRACUT | 460302 | 01826 | 13.92 | Solar | 05_01_304W3 | 10/19/2022 | 10/24/2022 | 3 | 0 | 3 | 10/25/2022 | 10/25/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 174547 | 01523 | 1000 | Solar | 05_01_415L1 | 11/09/2011 | 11/09/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 04/30/2014 | 08/01/2014 | 64 | 0 | 64 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 318681 | 01527 | 0 | Other | 05_01_612W1 | 11/05/2020 | 12/10/2020 | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2020 | 12/10/2020 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 652291 | 01507 | 15 | Solar | 05_05_11W84 | 11/05/2024 | 11/20/2024 | 2 | 0 | 2 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 11/05/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | WINCHENDON | 521440 | 01475 | 6.175 | Solar | 05_05_313W4 | 06/12/2023 | 06/13/2023 | 1 | 0 | 1 | 06/14/2023 | 06/14/2023 | 78 | 57 | 21 | 10/11/2023 | 10/31/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 10/31/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/18/2024 | N | EXP | 365 | 03/26/2024 | 04/11/2024 | 17 | 0 | 17 |  |  | 5/3/2024 | Connected |  | N
National Grid | SOMERSET | 173414 | 02725 | 7.6 | Solar | 05_12_35J3 | 04/11/2018 | 04/11/2018 | 0 | 0 | 0 | 05/09/2018 | 05/09/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 408871 | 01532 | 0 | Battery Add-On | 05_14_18L1 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/06/2022 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 571517 | 02151 | 3.8 | Solar | 05_14_48L2 | 02/05/2024 | 02/05/2024 | 0 | 0 | 0 | 02/06/2024 | 02/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 02/05/2024 | 3/15/2025 | Y | EXP | 365 | 05/30/2024 | 10/29/2024 | 153 | 0 | 153 |  |  | 12/3/2024 | Connected |  | N
National Grid | BILLERICA | 673361 | 01821 | 5.76 | Solar | 05_14_61L3 | 02/21/2025 | 02/26/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 80 | 57 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 311773 | 01832 | 150 | Solar | 05_14_75L4 | 09/10/2020 | 09/16/2020 | 3 | 0 | 3 | 09/17/2020 | 09/17/2020 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 175801 | 01843 | 1980 | Solar | 05_01_225W1 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/07/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 | 02/27/2015 | 12/31/2016 | Y | STD | 494 | 11/14/2016 | 01/06/2017 | 36 | 0 | 36 | 12/22/2016 | 12/22/2016 | 12/27/2016 | Connected |  | N
National Grid | METHUEN | 471063 | 01844 | 6 | Solar | 05_01_304W3 | 11/08/2022 | 11/14/2022 | 3 | 0 | 3 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 174737 | 01523 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2012 | 06/13/2012 | 55 | 0 | 55 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/15/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 325150 | 01527 | 0 | Other | 05_01_612W1 | 12/31/2020 | 01/06/2021 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2021 | 01/29/2021 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 655751 | 01507 | 11.5 | Solar | 05_05_11W84 | 11/20/2024 | 11/21/2024 | 1 | 0 | 1 | 11/22/2024 | 11/22/2024 | 57 | 33 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | WINCHENDON | 540566 | 01475 | 480 | Solar | 05_05_313W4 | 09/18/2023 | 12/06/2023 | 54 | 46 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/07/2023 | 02/21/2024 | 51 | 32 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 175520 | 02777 | 266 | Solar | 05_12_35J3 | 04/09/2014 | 04/09/2014 | 10 | 4 | 6 | 04/25/2014 | 04/25/2014 | 608 | 2 | 606 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2014 | 04/09/2014 | 2/4/2016 | Y | EXP | 639 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 672467 | 01532 | 5.76 | Solar | 05_14_18L1 | 02/17/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | REVERE | 586282 | 02151 | 15.2 | Solar | 05_14_48L2 | 01/31/2024 | 02/20/2024 | 13 | 10 | 3 | 02/21/2024 | 02/21/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | BILLERICA | 683655 | 01821 | 5.76 | Solar | 05_14_61L3 | 04/08/2025 | 05/13/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 318966 | 01830 | 249 | Solar | 05_14_75L4 | 10/13/2020 | 01/04/2022 | 19 | 12 | 7 | 11/10/2020 | 11/10/2020 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2021 |  | 1/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 176132 | 01843 | 495 | Solar | 05_01_225W1 | 04/14/2015 | 04/14/2015 | 4 | 4 | 0 | 04/22/2015 | 04/22/2015 | 166 | 0 | 166 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 526963 | 01844 | 7.6 | Solar | 05_01_304W3 | 05/24/2023 | 06/12/2023 | 13 | 12 | 1 | 06/13/2023 | 06/13/2023 | 35 | 14 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 174736 | 01740 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2012 | 06/13/2012 | 55 | 0 | 55 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/15/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 330507 | 01527 | 15.2 | Solar | 05_01_612W1 | 12/08/2020 | 12/13/2020 | 3 | 0 | 3 | 12/14/2020 | 12/14/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 12/08/2020 | 2/8/2023 | Y | EXP | 365 | 09/04/2021 | 10/21/2021 | 48 | 0 | 48 |  |  | 3/28/2022 | Connected |  | N
National Grid | CHARLTON | 657190 | 01508 | 5.76 | Solar | 05_05_11W84 | 11/26/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 11/26/2024 | 2/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | WINCHENDON | 551451 | 01475 | 250 | Solar | 05_05_313W4 | 09/18/2023 | 12/26/2023 | 67 | 58 | 9 | 12/27/2023 | 12/27/2023 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2024 |  | 1/20/2026 | N | EXP | 33 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | SWANSEA | 177083 | 02777 | 750 | Solar | 05_12_35J3 | 10/18/2016 | 10/18/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/09/2017 | 49 | 39 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 687181 | 01532 | 7.6 | Solar | 05_14_18L1 | 04/23/2025 | 05/12/2025 | 3 | 0 | 3 | 05/22/2025 | 05/22/2025 | 15 | 0 | 15 | 06/25/2025 | 07/28/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 07/28/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 8/4/2025 | 04/23/2025 | 9/4/2026 | Y | EXP | 365 | 11/04/2025 | 11/26/2025 | 23 | 0 | 23 |  |  | 12/3/2025 | Connected |  | N
National Grid | REVERE | 587167 | 02151 | 10.24 | Solar | 05_14_48L2 | 02/01/2024 | 02/08/2024 | 3 | 1 | 2 | 01/23/2025 | 01/23/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 | 02/01/2024 | 3/6/2026 | Y | EXP | 365 | 07/02/2025 | 07/11/2025 | 10 | 0 | 10 |  |  | 7/15/2025 | Connected |  | N
National Grid | BILLERICA | 689858 | 01821 | 5.76 | Solar | 05_14_61L3 | 05/06/2025 | 06/06/2025 | 3 | 0 | 3 | 06/09/2025 | 06/09/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 | 05/06/2025 | 7/25/2026 | Y | EXP | 365 | 11/04/2025 | 01/27/2026 | 85 | 2 | 83 |  |  | 12/23/2025 | Connected |  | N
National Grid | HAVERHILL | 379113 | 01830 | 7.6 | Solar | 05_14_75L4 | 11/01/2021 | 01/14/2022 | 52 | 50 | 2 | 01/18/2022 | 01/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176465 | 01843 | 99.9 | Solar | 05_01_225W1 | 02/05/2016 | 02/05/2016 | 0 | 0 | 0 | 02/08/2016 | 02/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 2/13/2017 | N | EXP | 370 |  |  | 0 | 0 | 0 | 11/18/2016 | 11/18/2016 | 11/18/2016 | Connected |  | N
National Grid | METHUEN | 536757 | 01844 | 10 | Solar | 05_01_304W3 | 06/27/2023 |  | 71 | 25 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 174735 | 01523 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2012 | 06/13/2012 | 55 | 0 | 55 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/15/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 361142 | 01527 | 17.6 | Solar | 05_01_612W1 | 06/07/2021 | 01/07/2022 | 51 | 50 | 1 | 08/18/2021 | 08/18/2021 | 155 | 127 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/17/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 672553 | 01508 | 5.76 | Solar | 05_05_11W84 | 02/18/2025 | 04/09/2025 | 2 | 0 | 2 | 04/17/2025 | 04/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 02/18/2025 | 6/10/2026 | Y | EXP | 365 | 08/01/2025 | 07/31/2025 | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | WINCHENDON | 619949 | 01475 | 11.5 | Solar | 05_05_313W4 | 06/24/2024 | 06/26/2024 | 4 | 0 | 4 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2024 | 06/24/2024 | 1/28/2026 | Y | EXP | 365 | 02/25/2025 | 02/24/2025 | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | SWANSEA | 215113 | 02777 | 7.6 | Solar | 05_12_35J3 | 05/15/2019 | 05/16/2019 | 0 | 0 | 0 | 05/17/2019 | 05/17/2019 | 59 | 48 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2019 |  | 10/23/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 705483 | 01532 | 8.32 | Solar | 05_14_18L1 | 07/17/2025 | 08/15/2025 | 8 | 2 | 6 | 09/29/2025 | 09/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2025 | Connected |  | N
National Grid | REVERE | 592029 | 02151 | 3.8 | Solar | 05_14_48L2 | 02/22/2024 | 04/30/2024 | 3 | 0 | 3 | 05/01/2024 | 05/01/2024 | 15 | 10 | 5 | 06/10/2024 | 08/02/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 08/02/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 6/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | BILLERICA | 691695 | 01821 | 11.52 | Solar | 05_14_61L3 | 05/21/2025 | 05/30/2025 | 3 | 0 | 3 | 06/24/2025 | 06/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/21/2025 | 7/28/2026 | Y | EXP | 365 | 09/25/2025 | 12/01/2025 | 68 | 0 | 68 |  |  | 12/4/2025 | Connected |  | N
National Grid | HAVERHILL | 668677 | 01830 | 20 | Solar | 05_14_75L4 | 01/29/2025 | 02/04/2025 | 5 | 2 | 3 | 02/05/2025 | 02/05/2025 | 67 | 25 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 177345 | 01843 | 15.2 | Solar | 05_01_225W1 | 11/22/2016 | 11/22/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2016 |  | 11/28/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/2/2017 | 8/2/2017 | 8/2/2017 | Connected |  | N
National Grid | METHUEN | 593460 | 01844 | 7.6 | Solar | 05_01_304W3 | 03/05/2024 | 03/08/2024 | 3 | 0 | 3 | 03/11/2024 | 03/11/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 | 03/05/2024 | 3/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2024 | Connected |  | N
National Grid | LANCASTER | 175532 | 01523 | 499 | Solar | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 | 09/29/2014 | 5/1/2016 | Y | STD | 177 |  |  | 0 | 0 | 0 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | MILLBURY | 427507 | 01527 | 13 | Solar | 05_01_612W1 | 05/13/2022 | 05/13/2022 | 0 | 0 | 0 | 05/16/2022 | 05/16/2022 | 74 | 55 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 709427 | 01508 | 9.56 | Solar | 05_05_11W84 | 08/04/2025 | 08/27/2025 | 4 | 0 | 4 | 09/08/2025 | 09/08/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 | 08/04/2025 | 10/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2026 | Connected |  | N
National Grid | WINCHENDON | 655214 | 01475 | 10 | Solar | 05_05_313W4 | 11/19/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | SWANSEA | 231907 | 02777 | 5 | Solar | 05_12_35J3 | 05/30/2019 | 06/26/2019 | 4 | 4 | 0 | 06/27/2019 | 06/27/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 736074 | 01532 | 3.8 | Solar | 05_14_18L2 | 11/24/2025 | 01/06/2026 | 3 | 0 | 3 | 02/23/2026 | 02/23/2026 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 604752 | 02151 | 10 | Solar | 05_14_48L2 | 04/17/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 04/17/2024 | 8/5/2025 | Y | EXP | 365 | 09/12/2024 | 03/31/2025 | 201 | 0 | 201 |  |  | 4/10/2025 | Connected |  | N
National Grid | BILLERICA | 701747 | 01821 | 7.6 | Solar | 05_14_61L3 | 06/28/2025 | 07/25/2025 | 9 | 5 | 4 | 08/08/2025 | 08/08/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 06/28/2025 | 9/9/2026 | Y | EXP | 365 | 11/04/2025 | 11/21/2025 | 18 | 0 | 18 |  |  | 12/4/2025 | Connected |  | N
National Grid | HAVERHILL | 682085 | 01830 | 15.2 | Solar | 05_14_75L4 | 04/03/2025 | 04/09/2025 | 4 | 0 | 4 | 04/10/2025 | 04/10/2025 | 35 | 17 | 18 | 06/17/2025 | 07/28/2025 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 07/28/2025 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 8/4/2025 | 04/03/2025 | 8/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | LAWRENCE | 177807 | 01843 | 20 | Solar | 05_01_225W1 | 10/12/2017 | 10/12/2017 | 10 | 0 | 10 | 10/27/2017 | 10/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2017 |  | 10/18/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 12/28/2017 | 12/28/2017 | 12/28/2017 | Connected |  | N
National Grid | METHUEN | 626487 | 01844 | 7.6 | Solar | 05_01_304W3 | 07/22/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 07/22/2024 | 12/31/2025 | Y | EXP | 365 | 02/25/2025 | 10/23/2025 | 241 | 0 | 241 |  |  | 11/17/2025 | Connected |  | N
National Grid | BOLTON | 175531 | 01740 | 499 | Solar | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 |  | 5/1/2016 | N | STD | 177 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 441942 | 01527 | 7.54 | Solar | 05_01_612W1 | 07/22/2022 | 07/26/2022 | 2 | 1 | 1 | 07/27/2022 | 07/27/2022 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2022 | 07/22/2022 | 9/2/2023 | Y | EXP | 365 | 09/21/2022 | 11/01/2022 | 41 | 0 | 41 |  |  | 1/20/2023 | Connected |  | N
National Grid | CHARLTON | 719327 | 01507 | 15.2 | Solar | 05_05_11W84 | 09/16/2025 | 10/06/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 09/16/2025 | 11/26/2026 | Y | EXP | 365 | 11/26/2025 | 01/27/2026 | 63 | 13 | 50 |  |  | 12/31/2025 | Connected |  | N
National Grid | WINCHENDON | 674719 | 01475 | 3.8 | Solar | 05_05_313W4 | 02/27/2025 | 03/19/2025 | 80 | 80 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 270600 | 02725 | 3.8 | Solar | 05_12_35J3 | 01/21/2020 | 03/09/2020 | 32 | 29 | 3 | 03/10/2020 | 03/10/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2020 | 01/21/2020 | 11/1/2022 | Y | EXP | 935 | 10/03/2020 | 12/15/2020 | 73 | 0 | 73 |  |  | 10/26/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 751755 | 01532 | 15.76 | Solar | 05_14_18L2 | 02/18/2026 | 02/20/2026 | 2 | 0 | 2 | 02/23/2026 | 02/23/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2026 |  | 3/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 619097 | 02151 | 10 | Solar | 05_14_48L2 | 06/20/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 50 | 40 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 | 06/20/2024 | 2/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 703776 | 01821 | 5.76 | Solar | 05_14_61L3 | 07/09/2025 | 08/12/2025 | 2 | 0 | 2 | 08/13/2025 | 08/13/2025 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 666789 | 01832 | 7.6 | Solar | 05_14_75L5 | 01/20/2025 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 85 | 65 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 178028 | 01843 | 69 | Solar | 05_01_225W1 | 08/31/2017 | 08/31/2017 | 1 | 0 | 1 | 09/05/2017 | 09/05/2017 | 103 | 0 | 103 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 9/6/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 628108 | 01844 | 3.8 | Solar | 05_01_304W3 | 07/26/2024 | 08/15/2024 | 1 | 0 | 1 | 08/16/2024 | 08/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 9/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | BOLTON | 175530 | 01740 | 499 | Solar | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2014 | 11/05/2014 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 | 09/29/2014 | 5/1/2016 | Y | STD | 177 |  |  | 0 | 0 | 0 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | MILLBURY | 474354 | 01527 | 3.8 | Solar | 05_01_612W1 | 11/16/2022 | 12/20/2022 | 23 | 21 | 2 | 12/21/2022 | 12/21/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 11/16/2022 | 3/8/2024 | Y | EXP | 365 | 03/02/2023 | 03/09/2023 | 8 | 0 | 8 |  |  | 4/4/2023 | Connected |  | N
National Grid | CHARLTON | 724378 | 01507 | 23 | Solar | 05_05_11W84 | 10/06/2025 | 10/21/2025 | 9 | 6 | 3 | 10/22/2025 | 10/22/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | WINCHENDON | 731390 | 01475 | 3.8 | Solar | 05_05_313W4 | 11/04/2025 | 11/05/2025 | 1 | 0 | 1 | 12/03/2025 | 12/03/2025 | 38 | 25 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 294945 | 02777 | 10 | Solar | 05_12_35J3 | 06/15/2020 | 06/18/2020 | 2 | 0 | 2 | 06/19/2020 | 06/19/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/15/2020 | 4/8/2022 | Y | EXP | 365 | 01/21/2021 | 02/18/2021 | 28 | 0 | 28 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 176623 | 01532 | 3 | Solar | 05_14_18L2 | 04/14/2016 | 04/14/2016 | 2 | 2 | 0 | 04/19/2016 | 04/19/2016 | 144 | 0 | 144 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 |  | 4/19/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 627679 | 02151 | 6 | Solar | 05_14_48L2 | 07/25/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/25/2024 | 8/27/2025 | Y | EXP | 365 | 03/05/2025 | 03/04/2025 | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | BILLERICA | 717411 | 01821 | 7.6 | Solar | 05_14_61L3 | 09/08/2025 | 09/23/2025 | 23 | 22 | 1 | 11/17/2025 | 11/17/2025 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 731105 | 01830 | 3.8 | Solar | 05_14_75L5 | 11/03/2025 | 11/04/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  | 2/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 178357 | 01843 | 1980 | Solar | 05_01_225W1 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/07/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 | 02/27/2015 | 3/6/2019 | Y | STD | 1289 | 11/14/2016 | 01/06/2017 | 36 | 0 | 36 | 12/23/2016 | 12/23/2016 | 12/27/2016 | Connected |  | N
National Grid | DRACUT | 643329 | 01826 | 7.6 | Solar | 05_01_304W3 | 09/27/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | LANCASTER | 175538 | 01523 | 499 | Solar | 05_01_415L1 | 10/06/2014 | 10/06/2014 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 497546 | 01527 | 6.528 | Solar | 05_01_612W1 | 03/10/2023 | 03/14/2023 | 2 | 0 | 2 | 03/15/2023 | 03/15/2023 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2023 |  | 5/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2023 | Connected |  | N
National Grid | CHARLTON | 494888 | 01507 | 1500 | Solar | 05_05_11W85 | 07/12/2023 | 07/28/2023 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2023 | 09/18/2023 | 35 | 19 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 07/12/2023 | 12/10/2027 | Y | STD | 791 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WINCHENDON | 452182 | 01475 | 999 | Solar | 05_05_314W1 | 08/25/2022 | 10/06/2023 | 278 | 268 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2023 | 02/27/2024 | 96 | 80 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 1/6/2027 | N | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SWANSEA | 488509 | 02777 | 9.8 | Solar | 05_12_35J3 | 11/23/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/23/2024 | 2/24/2026 | Y | EXP | 365 | 06/12/2025 | 10/02/2025 | 113 | 0 | 113 |  |  | 10/16/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 177548 | 01532 | 11.4 | Solar | 05_14_18L2 | 05/12/2017 | 05/12/2017 | 5 | 5 | 0 | 05/22/2017 | 05/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 |  | 5/20/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/28/2017 | 11/28/2017 | 11/28/2017 | Connected |  | N
National Grid | REVERE | 633406 | 02151 | 3.8 | Solar | 05_14_48L2 | 08/20/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 | 08/20/2024 | 1/8/2026 | Y | EXP | 365 | 08/28/2025 | 11/21/2025 | 86 | 0 | 86 |  |  | 12/4/2025 | Connected |  | N
National Grid | BILLERICA | 175840 | 01821 | 16 | Solar | 05_14_62L2 | 03/04/2015 | 03/04/2015 | 10 | 6 | 4 | 03/20/2015 | 03/20/2015 | 346 | 0 | 346 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2015 |  | 7/31/2015 | N | EXP | 127 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 743594 | 01830 | 9 | Solar | 05_14_75L5 | 01/07/2026 | 01/09/2026 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 253910 | 01843 | 22.8 | Solar | 05_01_225W1 | 09/13/2019 | 09/19/2019 | 4 | 4 | 0 | 09/20/2019 | 09/20/2019 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2019 |  | 4/15/2021 | N | EXP | 545 |  |  | 0 | 0 | 0 |  |  | 1/5/2021 | Connected |  | N
National Grid | LOWELL | 645157 | 01850 | 7.6 | Solar | 05_01_304W3 | 10/11/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 47 | 27 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | BOLTON | 175533 | 01740 | 499 | Solar | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 |  | 5/1/2016 | N | STD | 177 |  |  | 0 | 0 | 0 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | MILLBURY | 522629 | 01527 | 10 | Solar | 05_01_612W1 | 05/10/2023 | 05/15/2023 | 3 | 2 | 1 | 05/16/2023 | 05/16/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2023 | 05/10/2023 | 6/20/2024 | Y | EXP | 365 | 07/07/2023 | 08/08/2023 | 33 | 0 | 33 |  |  | 8/25/2023 | Connected |  | N
National Grid | CHARLTON | 494886 | 01507 | 2000 | Solar | 05_05_11W85 | 07/06/2023 | 08/24/2023 | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2023 | 09/18/2023 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 07/06/2023 | 12/14/2027 | Y | STD | 791 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WINCHENDON | 432400 | 01475 | 999 | Solar | 05_05_314W1 | 08/25/2022 | 10/24/2023 | 289 | 279 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2023 | 02/27/2024 | 85 | 65 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 1/5/2027 | N | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SWANSEA | 499811 | 02777 | 50 | Solar | 05_12_35J3 | 02/17/2023 | 05/10/2023 | 56 | 48 | 8 | 05/11/2023 | 05/11/2023 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 12/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2024 | Connected |  | N
National Grid | WESTBOROUGH | 189415 | 01581 | 15.2 | Solar | 05_14_18L2 | 06/27/2018 | 06/27/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  | 2/21/2020 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N
National Grid | REVERE | 641356 | 02151 | 4.64 | Solar | 05_14_48L2 | 09/20/2024 | 10/09/2024 | 5 | 0 | 5 | 10/10/2024 | 10/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/20/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | BILLERICA | 177883 | 01821 | 20 | Solar | 05_14_62L2 | 10/19/2017 | 10/19/2017 | 58 | 52 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176870 | 01830 | 7.6 | Solar | 05_14_75L5 | 03/01/2016 | 03/01/2016 | 1 | 1 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2016 | 03/01/2016 | 3/7/2017 | Y | EXP | 323 | 09/30/2016 | 10/18/2016 | 11 | 0 | 11 | 4/18/2016 | 4/18/2016 | 10/17/2016 | Connected |  | N
National Grid | ANDOVER | 262760 | 01810 | 19.2 | Solar | 05_01_225W1 | 10/29/2019 | 11/04/2019 | 3 | 3 | 0 | 11/05/2019 | 11/05/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 |  | 10/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2020 | Connected |  | N
National Grid | LOWELL | 655225 | 01850 | 3.8 | Solar | 05_01_304W3 | 11/19/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | HARVARD | 175652 | 01451 | 499 | Solar | 05_01_415L1 | 12/17/2014 | 12/17/2014 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 | 12/17/2014 | 5/25/2018 | Y | STD | 847 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | MILLBURY | 529144 | 01527 | 5.76 | Solar | 05_01_612W1 | 06/09/2023 | 06/13/2023 | 2 | 0 | 2 | 06/14/2023 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 | 06/09/2023 | 7/28/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2023 | Connected |  | N
National Grid | CHARLTON | 711672 | 01507 | 260 | Solar | 05_05_11W85 | 02/03/2026 | 03/05/2026 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2026 |  | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WINCHENDON | 749495 | 01475 | 150 | Solar | 05_05_314W1 | 02/17/2026 |  | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SWANSEA | 537998 | 02777 | 2.32 | Solar | 05_12_35J3 | 06/30/2023 | 07/05/2023 | 2 | 0 | 2 | 07/06/2023 | 07/06/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 225966 | 01581 | 6 | Solar | 05_14_18L2 | 05/09/2019 | 05/13/2019 | 2 | 1 | 1 | 05/14/2019 | 05/14/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 | 05/09/2019 | 7/31/2020 | Y | EXP | 365 | 04/15/2020 | 04/16/2020 | 1 | 0 | 1 |  |  | 4/20/2020 | Connected |  | N
National Grid | REVERE | 642251 | 02151 | 10 | Solar | 05_14_48L2 | 09/25/2024 | 10/18/2024 | 4 | 0 | 4 | 10/21/2024 | 10/21/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 09/25/2024 | 11/27/2025 | Y | EXP | 365 | 03/15/2025 | 09/06/2025 | 176 | 0 | 176 |  |  | 9/18/2025 | Connected |  | N
National Grid | BILLERICA | 186432 | 01821 | 0 | Solar | 05_14_62L2 | 06/20/2018 | 06/20/2018 | 42 | 35 | 7 | 08/21/2018 | 08/21/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 |  | 8/21/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2019 | Connected |  | N
National Grid | HAVERHILL | 186665 | 01830 | 3.8 | Solar | 05_14_75L5 | 05/30/2018 | 05/30/2018 | 10 | 9 | 1 | 07/11/2018 | 07/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 7/15/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2019 | Connected |  | N
National Grid | ANDOVER | 277546 | 01810 | 9.6 | Solar | 05_01_225W1 | 01/31/2020 | 02/06/2020 | 3 | 0 | 3 | 02/07/2020 | 02/07/2020 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2020 |  | 1/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2020 | Connected |  | N
National Grid | DRACUT | 659616 | 01826 | 6.825 | Solar | 05_01_304W3 | 12/16/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | HARVARD | 175651 | 01451 | 1000 | Solar | 05_01_415L1 | 12/17/2014 | 12/17/2014 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 | 12/17/2014 | 5/29/2018 | Y | STD | 851 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | MILLBURY | 637211 | 01527 | 3.8 | Solar | 05_01_612W1 | 09/03/2024 | 10/08/2024 | 3 | 2 | 1 | 10/09/2024 | 10/09/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/03/2024 | 11/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 174338 | 01507 | 260 | Solar | 05_05_11W85 | 01/27/2012 | 01/27/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 | 3/1/2013 |  | 2/15/2012 | N | STD | 380 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 5/8/2015 | Connected |  | N
National Grid | WINCHENDON | 348940 | 01475 | 100 | Solar | 05_05_314W1 | 03/25/2021 | 04/30/2021 | 25 | 16 | 9 | 05/11/2021 | 05/11/2021 | 40 | 15 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2021 |  | 7/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 601237 | 02777 | 5 | Solar | 05_12_35J3 | 04/09/2024 | 04/15/2024 | 4 | 0 | 4 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 04/09/2024 | 6/4/2025 | Y | EXP | 365 | 09/27/2024 | 11/26/2024 | 61 | 0 | 61 |  |  | 1/30/2025 | Connected |  | N
National Grid | WESTBOROUGH | 372933 | 01581 | 7.6 | Solar | 05_14_18L2 | 08/06/2021 | 08/09/2021 | 2 | 1 | 1 | 08/10/2021 | 08/10/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 | 08/06/2021 | 3/29/2023 | Y | EXP | 365 | 01/19/2022 | 02/11/2022 | 24 | 0 | 24 |  |  | 12/17/2022 | Connected |  | N
National Grid | REVERE | 647358 | 02151 | 15.2 | Solar | 05_14_48L2 | 11/07/2024 | 11/12/2024 | 2 | 0 | 2 | 11/13/2024 | 11/13/2024 | 36 | 23 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | BILLERICA | 194474 | 01821 | 480 | Solar | 05_14_62L2 | 08/27/2018 | 09/04/2018 | 5 | 5 | 0 | 09/05/2018 | 09/05/2018 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2019 |  | 9/4/2020 | N | EXP | 541 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 199149 | 01832 | 10 | Solar | 05_14_75L5 | 12/04/2018 | 01/10/2019 | 24 | 16 | 8 | 01/11/2019 | 01/11/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2019 | 12/04/2018 | 10/2/2019 | Y | EXP | 253 | 05/01/2019 | 06/11/2019 | 41 | 0 | 41 |  |  | 9/3/2019 | Connected |  | N
National Grid | ANDOVER | 289477 | 01810 | 12 | Solar | 05_01_225W1 | 05/12/2020 | 05/13/2020 | 0 | 0 | 0 | 05/14/2020 | 05/14/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2020 |  | 6/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 667220 | 01850 | 0 | Battery Add-On | 05_01_304W3 | 01/22/2025 | 01/28/2025 | 4 | 0 | 4 | 01/29/2025 | 01/29/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | BOLTON | 175687 | 01740 | 1000 | Solar | 05_01_415L1 | 12/23/2014 | 12/23/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 | 12/23/2014 | 5/25/2018 | Y | STD | 847 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | MILLBURY | 640886 | 01527 | 34.6 | Solar | 05_01_612W1 | 09/18/2024 | 10/22/2024 | 23 | 17 | 6 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 174337 | 01507 | 499 | Solar | 05_05_11W85 | 01/27/2012 | 01/27/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2013 |  | 4/14/2012 | N | STD | 285 |  |  | 0 | 0 | 0 | 1/29/2015 | 1/29/2015 | 2/18/2015 | Connected |  | N
National Grid | WINCHENDON | 348897 | 01475 | 150 | Solar | 05_05_314W1 | 03/25/2021 | 04/30/2021 | 25 | 16 | 9 | 05/03/2021 | 05/03/2021 | 46 | 8 | 38 | 07/21/2021 | 01/11/2022 | 120 | 7 | 113 |  |  | 0 | 0 | 0 | 01/11/2022 | 120 | 7 | 113 |  |  | 0 | 0 | 0 | 1/12/2022 |  | 3/14/2023 | N | EXP | 365 | 01/10/2023 | 01/10/2023 | 1 | 0 | 1 |  |  | 4/5/2023 | Connected |  | N
National Grid | SWANSEA | 641513 | 02777 | 10 | Solar | 05_12_35J3 | 09/19/2024 | 10/10/2024 | 7 | 6 | 1 | 10/11/2024 | 10/11/2024 | 69 | 45 | 24 | 02/24/2025 | 08/05/2025 | 112 | 25 | 87 |  |  | 0 | 0 | 0 | 08/05/2025 | 112 | 25 | 87 |  |  | 0 | 0 | 0 | 8/8/2025 | 09/19/2024 | 8/18/2026 | Y | EXP | 365 | 11/04/2025 | 01/27/2026 | 85 | 0 | 85 |  |  | 12/10/2025 | Connected |  | N
National Grid | WESTBOROUGH | 413120 | 01581 | 15.2 | Solar | 05_14_18L2 | 02/18/2022 | 02/24/2022 | 4 | 2 | 2 | 02/25/2022 | 02/25/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 3/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2022 | Connected |  | N
National Grid | REVERE | 648633 | 02151 | 5.76 | Solar | 05_14_48L2 | 11/01/2024 | 12/03/2024 | 13 | 9 | 4 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 200806 | 01821 | 4.8 | Solar | 05_14_62L2 | 11/08/2018 | 12/05/2018 | 5 | 0 | 5 | 12/06/2018 | 12/06/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2019 |  | 1/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2019 | Connected |  | N
National Grid | HAVERHILL | 217114 | 01832 | 10 | Solar | 05_14_75L5 | 04/10/2019 | 04/25/2019 | 11 | 11 | 0 | 04/26/2019 | 04/26/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2019 | 04/10/2019 | 3/31/2020 | Y | EXP | 336 | 09/27/2019 | 10/23/2019 | 26 | 0 | 26 |  |  | 10/28/2019 | Connected |  | N
National Grid | ANDOVER | 290294 | 01810 | 15.2 | Solar | 05_01_225W1 | 05/04/2020 | 05/11/2020 | 5 | 5 | 0 | 05/12/2020 | 05/12/2020 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2020 | Connected |  | N
National Grid | DRACUT | 673393 | 01826 | 5.76 | Solar | 05_01_304W3 | 02/25/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 62 | 43 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 175678 | 01740 | 1000 | Solar | 05_01_415L1 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 12/01/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 645430 | 01527 | 10 | Solar | 05_01_612W1 | 10/08/2024 | 10/10/2024 | 2 | 0 | 2 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | CHARLTON | 174334 | 01507 | 185.6 | Solar | 05_05_11W85 | 01/24/2012 | 01/24/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 2/15/2012 | N | EXP | 301 |  |  | 0 | 0 | 0 | 11/21/2012 | 11/21/2012 | 12/13/2012 | Connected |  | N
National Grid | WINCHENDON | 580711 | 01475 | 150 | Solar | 05_05_314W1 | 01/07/2024 | 02/07/2024 | 21 | 11 | 10 |  |  | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 200545 | 02777 | 10 | Solar | 05_12_35J4 | 11/08/2018 | 11/28/2018 | 6 | 3 | 3 | 11/29/2018 | 11/29/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 653923 | 01581 | 3.8 | Solar | 05_14_18L2 | 11/18/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2025 | Connected |  | N
National Grid | REVERE | 650991 | 02151 | 5.76 | Solar | 05_14_48L2 | 11/12/2024 | 12/09/2024 | 1 | 0 | 1 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/12/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | BILLERICA | 233871 | 01821 | 10 | Solar | 05_14_62L2 | 06/06/2019 | 06/28/2019 | 16 | 13 | 3 | 07/01/2019 | 07/01/2019 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 8/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | HAVERHILL | 284540 | 01832 | 5.67 | Solar | 05_14_75L5 | 07/01/2020 | 07/07/2020 | 3 | 0 | 3 | 07/08/2020 | 07/08/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/5/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 291401 | 01810 | 0 | Battery Add-On | 05_01_225W1 | 05/11/2020 | 05/12/2020 | 0 | 0 | 0 | 05/13/2020 | 05/13/2020 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2020 | 05/11/2020 | 5/11/2021 | Y | EXP | 365 | 08/27/2020 | 09/10/2020 | 14 | 0 | 14 |  |  | 12/9/2020 | Connected |  | N
National Grid | LOWELL | 697399 | 01850 | 8.7 | Solar | 05_01_304W3 | 06/10/2025 | 07/02/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 63 | 58 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 175706 | 01740 | 1000 | Solar | 05_01_415L1 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 12/01/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 650021 | 01527 | 4.06 | Solar | 05_01_612W1 | 10/28/2024 | 11/07/2024 | 6 | 0 | 6 | 11/08/2024 | 11/08/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 10/28/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | CHARLTON | 174454 | 01507 | 3260 | Solar | 05_05_11W85 | 07/13/2012 | 07/13/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/28/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 650009 | 01475 | 0 | Other | 05_05_314W2 | 05/02/2025 | 07/11/2025 | 46 | 39 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 08/27/2025 | 32 | 17 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SWANSEA | 314661 | 02777 | 3.8 | Solar | 05_12_35J4 | 10/01/2020 | 10/05/2020 | 1 | 0 | 1 | 10/06/2020 | 10/06/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2020 | 10/01/2020 | 11/5/2021 | Y | EXP | 365 | 01/21/2021 | 04/08/2021 | 77 | 0 | 77 |  |  | 7/14/2021 | Connected |  | N
National Grid | WESTBOROUGH | 660841 | 01581 | 10 | Solar | 05_14_18L2 | 12/16/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 | 02/21/2025 | 04/16/2025 | 55 | 0 | 55 |  |  | 4/24/2025 | Connected |  | N
National Grid | REVERE | 653889 | 02151 | 3.8 | Solar | 05_14_48L2 | 12/04/2024 | 01/21/2025 | 4 | 0 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/04/2024 | 3/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | BILLERICA | 300290 | 01821 | 0 | Solar | 05_14_62L2 | 07/08/2020 | 07/13/2020 | 2 | 2 | 0 | 07/14/2020 | 07/14/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/12/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2020 | Connected |  | N
National Grid | HAVERHILL | 307087 | 01832 | 7.6 | Solar | 05_14_75L5 | 09/18/2020 | 09/24/2020 | 3 | 0 | 3 | 09/25/2020 | 09/25/2020 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 297124 | 01810 | 15.2 | Solar | 05_01_225W1 | 06/20/2020 | 06/23/2020 | 1 | 0 | 1 | 06/24/2020 | 06/24/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2021 | Connected |  | Y
National Grid | LOWELL | 736690 | 01850 | 21.28 | Solar | 05_01_304W3 | 11/26/2025 | 12/01/2025 | 2 | 0 | 2 | 12/02/2025 | 12/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2026 | Connected |  | N
National Grid | HARVARD | 176018 | 01451 | 7.6 | Solar | 05_01_415L1 | 03/20/2015 | 03/20/2015 | 2 | 1 | 1 | 03/25/2015 | 03/25/2015 | 343 | 0 | 343 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 7/20/2015 | N | EXP | 115 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 652565 | 01527 | 15.2 | Solar | 05_01_612W1 | 11/13/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 11/13/2024 | 1/8/2026 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  | 2/21/2025 | Connected |  | N
National Grid | CHARLTON | 174708 | 01507 | 500 | Solar | 05_05_11W85 | 06/17/2013 | 06/17/2013 | 46 | 38 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/29/2013 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 650006 | 01475 | 0 | Other | 05_05_314W2 | 05/02/2025 | 07/11/2025 | 46 | 39 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 08/27/2025 | 32 | 17 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SWANSEA | 617299 | 02777 | 5.76 | Solar | 05_12_35J4 | 06/14/2024 | 07/16/2024 | 16 | 15 | 1 | 07/17/2024 | 07/17/2024 | 22 | 10 | 12 | 09/06/2024 | 10/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 10/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 11/13/2025 | N | EXP | 365 | 02/26/2025 | 11/21/2025 | 269 | 0 | 269 |  |  | 12/6/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 669702 | 01772 | 1.74 | Solar | 05_14_18L2 | 02/04/2025 | 02/07/2025 | 3 | 0 | 3 | 02/10/2025 | 02/10/2025 | 133 | 121 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 657537 | 02151 | 3.8 | Solar | 05_14_48L2 | 11/28/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 | 11/28/2024 | 3/17/2026 | Y | EXP | 365 | 05/30/2025 | 12/01/2025 | 186 | 0 | 186 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 328453 | 01821 | 0 | Solar | 05_14_62L2 | 11/25/2020 | 01/26/2021 | 39 | 38 | 1 | 01/27/2021 | 01/27/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2021 |  | 6/23/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 4/28/2022 | Connected |  | N
National Grid | HAVERHILL | 349177 | 01830 | 7.6 | Solar | 05_14_75L5 | 04/15/2021 | 04/26/2021 | 5 | 0 | 5 | 04/27/2021 | 04/27/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2021 |  | 6/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 310710 | 01810 | 0 | Solar | 05_01_225W1 | 09/14/2020 | 09/21/2020 | 4 | 0 | 4 | 09/22/2020 | 09/22/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 7/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | N
National Grid | LOWELL | 735413 | 01850 | 5.76 | Solar | 05_01_304W3 | 11/20/2025 | 11/24/2025 | 2 | 0 | 2 | 11/25/2025 | 11/25/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2026 | Connected |  | N
National Grid | BOLTON | 176323 | 01740 | 30 | Solar | 05_01_415L1 | 07/15/2015 | 07/15/2015 | 3 | 3 | 0 | 07/20/2015 | 07/20/2015 | 390 | 0 | 390 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2015 | 07/15/2015 | 7/20/2017 | Y | EXP | 713 | 04/05/2017 | 04/21/2017 | 11 | 0 | 11 | 7/31/2015 | 7/31/2015 |  | Withdrawn |  | N
National Grid | MILLBURY | 685264 | 01527 | 15.2 | Solar | 05_01_612W1 | 05/09/2025 | 05/16/2025 | 4 | 0 | 4 | 05/19/2025 | 05/19/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 175268 | 01507 | 130 | Solar | 05_05_11W85 | 06/20/2014 | 06/20/2014 | 9 | 7 | 2 | 07/07/2014 | 07/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2014 |  | 10/31/2014 | N | EXP | 88 |  |  | 0 | 0 | 0 | 12/8/2014 | 12/8/2014 | 12/22/2014 | Connected |  | N
National Grid | WINCHENDON | 746953 | 01475 | 3.8 | Solar | 05_05_314W2 | 01/22/2026 | 01/23/2026 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SWANSEA | 645906 | 02777 | 10 | Solar | 05_12_35J4 | 10/17/2024 | 12/12/2024 | 27 | 25 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 710356 | 01772 | 8.32 | Solar | 05_14_18L2 | 08/08/2025 | 08/28/2025 | 3 | 2 | 1 | 09/19/2025 | 09/19/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 658084 | 02151 | 5.76 | Solar | 05_14_48L2 | 12/03/2024 | 03/17/2025 | 61 | 57 | 4 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 331152 | 01821 | 0 | Solar | 05_14_62L2 | 12/11/2020 | 12/18/2020 | 4 | 0 | 4 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2021 | 12/11/2020 | 9/5/2023 | Y | EXP | 475 | 08/15/2021 | 09/16/2021 | 32 | 3 | 29 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 383082 | 01830 | 6 | Solar | 05_14_75L5 | 10/13/2021 | 12/21/2021 | 4 | 0 | 4 | 10/20/2021 | 10/20/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 |  | 4/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2022 | Connected |  | N
National Grid | ANDOVER | 312902 | 01810 | 22.8 | Solar | 05_01_225W1 | 09/15/2020 | 09/16/2020 | 0 | 0 | 0 | 09/17/2020 | 09/17/2020 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2020 |  | 11/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2021 | Connected |  | N
National Grid | LOWELL | 299022 | 01850 | 996 | Solar | 05_01_304W4 | 09/08/2020 | 10/05/2020 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2020 | 10/29/2020 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/08/2020 | 4/12/2026 | Y | STD | 371 | 05/09/2025 | 11/24/2025 | 223 | 0 | 223 |  |  |  | Completion Documents |  | N
National Grid | BOLTON | 177175 | 01740 | 22.8 | Solar | 05_01_415L1 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2016 | 06/01/2016 | 6/6/2017 | Y | EXP | 370 | 04/05/2017 | 04/21/2017 | 11 | 0 | 11 | 6/1/2016 | 6/1/2016 | 5/15/2017 | Connected |  | N
National Grid | MILLBURY | 685677 | 01527 | 4980 | Solar | 05_01_612W1 | 05/06/2025 | 06/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/04/2025 | 07/02/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 207776 | 01507 | 60 | Solar | 05_05_11W85 | 02/08/2019 | 02/22/2019 | 9 | 4 | 5 | 02/25/2019 | 02/25/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 3/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2019 | Connected |  | N
National Grid | WINCHENDON | 174569 | 01475 | 1000 | Solar | 05_05_314W2 | 04/17/2011 | 04/17/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2012 | 04/17/2011 | 10/31/2012 | Y | STD | 264 | 05/07/2012 | 07/23/2012 | 52 | 0 | 52 | 8/6/2012 | 8/6/2012 | 8/17/2012 | Connected |  | N
National Grid | SWANSEA | 658236 | 02777 | 3.8 | Solar | 05_12_35J4 | 12/03/2024 |  | 131 | 25 | 106 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 690634 | 01772 | 10 | Solar | 05_14_18L3 | 05/08/2025 | 07/01/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 | 05/08/2025 | 9/15/2026 | Y | EXP | 365 | 03/27/2026 |  | 6 | 0 | 6 |  |  |  | Construction |  | N
National Grid | REVERE | 660636 | 02151 | 3.8 | Solar | 05_14_48L2 | 12/13/2024 | 03/26/2025 | 56 | 52 | 4 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 12/13/2024 | 5/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 370322 | 01821 | 7.6 | Solar | 05_14_62L2 | 07/16/2021 |  | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 521839 | 01830 | 4.93 | Solar | 05_14_75L5 | 04/26/2023 | 07/17/2023 | 55 | 54 | 1 | 07/18/2023 | 07/18/2023 | 149 | 126 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2024 | Connected |  | N
National Grid | ANDOVER | 338763 | 01810 | 7.6 | Solar | 05_01_225W1 | 03/05/2021 | 03/08/2021 | 0 | 0 | 0 | 03/09/2021 | 03/09/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 | 03/05/2021 | 3/7/2022 | Y | EXP | 365 | 06/17/2021 | 08/17/2021 | 61 | 0 | 61 |  |  | 8/25/2021 | Connected |  | N
National Grid | LOWELL | 683158 | 01850 | 6.46 | Solar | 05_01_304W4 | 04/06/2025 | 04/25/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOLTON | 177536 | 01740 | 19 | Solar | 05_01_415L1 | 09/14/2017 | 09/14/2017 | 13 | 13 | 0 | 09/28/2017 | 09/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2017 |  | 9/19/2018 | N | EXP | 350 |  |  | 0 | 0 | 0 | 1/4/2018 | 1/4/2018 | 1/2/2018 | Connected |  | N
National Grid | MILLBURY | 696246 | 01527 | 17.92 | Solar | 05_01_612W1 | 06/19/2025 | 07/15/2025 | 16 | 13 | 3 | 07/16/2025 | 07/16/2025 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 291768 | 01507 | 0 | Other | 05_05_11W85 | 10/28/2020 | 12/21/2020 | 36 | 29 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 01/19/2021 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2021 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 177081 | 01475 | 600 | Solar | 05_05_314W2 | 10/18/2016 | 10/18/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/13/2017 | 53 | 46 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2017 | 10/18/2016 | 3/6/2021 | Y | STD | 1355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 687658 | 02777 | 7.6 | Solar | 05_12_37J3 | 04/25/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SOUTHBOROUGH | 732460 | 01772 | 3.8 | Solar | 05_14_18L3 | 11/10/2025 | 11/12/2025 | 1 | 0 | 1 | 12/30/2025 | 12/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 660965 | 02151 | 3.8 | Solar | 05_14_48L2 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | BILLERICA | 380185 | 01821 | 7.6 | Solar | 05_14_62L2 | 09/06/2021 |  | 75 | 69 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 543771 | 01830 | 9.6 | Solar | 05_14_75L5 | 08/25/2023 | 08/29/2023 | 2 | 0 | 2 | 08/30/2023 | 08/30/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 08/25/2023 | 10/17/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2024 | Connected |  | N
National Grid | ANDOVER | 338749 | 01810 | 7.6 | Solar | 05_01_225W1 | 01/26/2021 | 01/29/2021 | 2 | 0 | 2 | 02/01/2021 | 02/01/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2021 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | DRACUT | 748378 | 01826 | 5.76 | Solar | 05_01_304W4 | 01/30/2026 | 02/13/2026 | 10 | 8 | 2 | 02/17/2026 | 02/17/2026 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HARVARD | 178004 | 01451 | 3500 | Solar | 05_01_415L1 | 04/26/2017 | 04/26/2017 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2017 | 06/13/2017 | 15 | 2 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/2/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 704688 | 01527 | 4980 | Solar | 05_01_612W1 | 08/13/2025 | 08/27/2025 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2025 | 09/18/2025 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 398023 | 01566 | 0 | Other | 05_05_11W85 | 12/06/2021 | 02/04/2022 | 42 | 34 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2022 | 02/09/2022 | 3 | 0 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 177785 | 01475 | 56 | Solar | 05_05_314W2 | 06/01/2017 | 06/01/2017 | 4 | 3 | 1 | 06/08/2017 | 06/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2017 |  | 6/7/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 3/22/2018 | 3/22/2018 | 4/2/2018 | Connected |  | N
National Grid | SWANSEA | 727136 | 02777 | 10 | Solar | 05_12_37J3 | 10/16/2025 | 03/03/2026 | 2 | 0 | 2 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBOROUGH | 175826 | 01772 | 7.6 | Solar | 05_14_18L3 | 09/18/2015 | 09/18/2015 | 3 | 3 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 | 09/18/2015 | 9/26/2016 | Y | EXP | 350 | 04/04/2016 | 05/13/2016 | 28 | 0 | 28 | 5/4/2016 | 5/4/2016 | 6/17/2016 | Connected |  | N
National Grid | EVERETT | 682063 | 02149 | 5.76 | Solar | 05_14_48L2 | 04/01/2025 | 06/10/2025 | 28 | 24 | 4 | 06/11/2025 | 06/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2025 | 04/01/2025 | 7/18/2026 | Y | EXP | 365 | 11/21/2025 | 11/21/2025 | 1 | 0 | 1 |  |  | 12/9/2025 | Connected |  | N
National Grid | BILLERICA | 394876 | 01862 | 7.6 | Solar | 05_14_62L2 | 11/11/2021 | 12/20/2021 | 27 | 24 | 3 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 |  | 8/2/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 576217 | 01830 | 15.2 | Solar | 05_14_75L5 | 12/06/2023 | 12/27/2023 | 13 | 10 | 3 | 12/28/2023 | 12/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 340547 | 01810 | 10 | Solar | 05_01_225W1 | 03/11/2021 | 03/31/2021 | 13 | 11 | 2 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 | 03/11/2021 | 12/8/2022 | Y | EXP | 365 | 08/10/2021 | 10/08/2021 | 57 | 3 | 54 |  |  | 12/1/2021 | Connected |  | N
National Grid | LOWELL | 752468 | 01850 | 5.76 | Solar | 05_01_304W4 | 02/20/2026 | 02/26/2026 | 1 | 0 | 1 | 03/16/2026 | 03/16/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LANCASTER | 178003 | 01523 | 4500 | Solar | 05_01_415L1 | 04/26/2017 | 05/22/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2017 | 06/13/2017 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2018 | 04/26/2017 | 8/24/2020 | Y | STD | 617 | 02/26/2020 | 08/24/2020 | 180 | 0 | 180 |  |  | 8/24/2020 | Connected |  | N
National Grid | GRAFTON | 706143 | 01536 | 15.2 | Solar | 05_01_612W1 | 07/21/2025 | 07/22/2025 | 1 | 0 | 1 | 07/23/2025 | 07/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 |  | 8/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2025 | Connected |  | N
National Grid | CHARLTON | 443980 | 01507 | 0 | Other | 05_05_11W85 | 01/30/2023 | 02/14/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2023 | 03/21/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 178034 | 01475 | 92 | Solar | 05_05_314W2 | 10/26/2017 | 10/26/2017 | 5 | 0 | 5 | 11/13/2017 | 11/13/2017 | 98 | 0 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 |  | 11/1/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 177347 | 02777 | 7.6 | Solar | 05_12_37J3 | 11/22/2016 | 11/22/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2016 |  | 11/28/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 4/17/2017 | 4/17/2017 | 4/24/2017 | Connected |  | N
National Grid | SOUTHBOROUGH | 176859 | 01772 | 30 | Hydrogen | 05_14_18L3 | 01/20/2016 | 01/20/2016 | 1 | 1 | 0 | 01/21/2016 | 01/21/2016 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 11/16/2020 | N | EXP | 1358 |  |  | 0 | 0 | 0 |  |  | 12/18/2020 | Connected |  | N
National Grid | EVERETT | 698019 | 02149 | 4.48 | Solar | 05_14_48L2 | 06/12/2025 | 07/29/2025 | 2 | 0 | 2 | 08/11/2025 | 08/11/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 404321 | 01821 | 7.6 | Solar | 05_14_62L2 | 01/02/2022 | 01/04/2022 | 1 | 0 | 1 | 01/05/2022 | 01/05/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  | 6/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | HAVERHILL | 584135 | 01830 | 7.6 | Solar | 05_14_75L5 | 02/06/2024 | 02/07/2024 | 1 | 0 | 1 | 02/08/2024 | 02/08/2024 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 5/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2024 | Connected |  | N
National Grid | ANDOVER | 342501 | 01810 | 0 | Battery Add-On | 05_01_225W1 | 02/17/2021 |  | 32 | 26 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 175804 | 01850 | 990 | Solar | 05_01_304W4 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 178154 | 01451 | 5000 | Solar | 05_01_415L1 | 12/21/2017 | 12/21/2017 | 23 | 14 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/30/2018 | 02/21/2018 | 15 | 1 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 709014 | 01527 | 15.76 | Solar | 05_01_612W1 | 08/01/2025 | 08/05/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | CHARLTON | 668365 | 01507 | 60 | Solar | 05_05_11W85 | 03/05/2025 | 04/11/2025 | 28 | 18 | 10 | 04/14/2025 | 04/14/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | WINCHENDON | 187658 | 01475 | 100 | Solar | 05_05_314W2 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 07/02/2018 | 07/02/2018 | 153 | 22 | 131 | 08/15/2018 | 10/11/2018 | 40 | 18 | 22 |  |  | 0 | 0 | 0 | 10/11/2018 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 178067 | 02777 | 240 | Solar | 05_12_37J3 | 09/05/2017 | 09/05/2017 | 45 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/13/2017 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2018 | 09/05/2017 | 4/15/2021 | Y | STD | 352 | 09/16/2020 | 03/24/2021 | 189 | 0 | 189 |  |  | 4/13/2021 | Connected |  | N
National Grid | SOUTHBOROUGH | 177535 | 01772 | 999 | Solar | 05_14_18L3 | 09/14/2017 | 09/14/2017 | 23 | 23 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 | 11/09/2017 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2018 |  | 9/19/2019 | N | STD | 458 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 707779 | 02149 | 6.08 | Solar | 05_14_48L2 | 07/30/2025 | 08/04/2025 | 3 | 0 | 3 | 08/05/2025 | 08/05/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | BILLERICA | 442063 | 01821 | 13.6 | Solar | 05_14_62L2 | 08/02/2022 | 08/03/2022 | 2 | 1 | 1 | 08/04/2022 | 08/04/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2022 | 08/02/2022 | 8/30/2023 | Y | EXP | 365 | 09/28/2022 | 12/21/2022 | 85 | 0 | 85 |  |  | 1/5/2023 | Connected |  | N
National Grid | HAVERHILL | 637007 | 01830 | 5.76 | Solar | 05_14_75L5 | 08/30/2024 | 09/13/2024 | 3 | 0 | 3 | 09/16/2024 | 09/16/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 | 08/30/2024 | 10/24/2025 | Y | EXP | 365 | 10/24/2024 | 03/19/2025 | 148 | 14 | 134 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 361381 | 01810 | 7.6 | Solar | 05_01_225W1 | 06/01/2021 | 08/10/2021 | 48 | 46 | 2 | 08/11/2021 | 08/11/2021 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2022 | Connected |  | N
National Grid | LOWELL | 176092 | 01850 | 980 | Solar | 05_01_304W4 | 04/06/2015 | 04/06/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2015 | 04/20/2015 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 178297 | 01451 | 2640 | Solar | 05_01_415L1 | 11/15/2017 | 01/18/2018 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/13/2018 | 25 | 14 | 11 |  | 0 | 0 | 0 | 08/14/2018 | 11/06/2018 | 60 | 0 | 60 | 7/6/2018 | 11/15/2017 |  | Y | STD | 966 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 721110 | 01527 | 15.2 | Solar | 05_01_612W1 | 09/23/2025 | 09/29/2025 | 3 | 1 | 2 | 09/30/2025 | 09/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2025 | Connected |  | N
National Grid | CHARLTON | 671086 | 01507 | 5.76 | Solar | 05_05_17J1 | 02/10/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | WINCHENDON | 229154 | 01475 | 7.6 | Solar | 05_05_314W2 | 05/18/2019 | 05/23/2019 | 3 | 0 | 3 | 05/24/2019 | 05/24/2019 | 15 | 9 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 8/30/2019 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  | 8/12/2019 | Connected |  | N
National Grid | SWANSEA | 178098 | 02777 | 240 | Solar | 05_12_37J3 | 09/05/2017 | 09/05/2017 | 45 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/13/2017 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2018 | 09/05/2017 | 4/15/2021 | Y | STD | 598 | 09/16/2020 | 03/24/2021 | 189 | 0 | 189 |  |  | 4/14/2021 | Connected |  | N
National Grid | SOUTHBOROUGH | 253359 | 01772 | 7.6 | Solar | 05_14_18L3 | 09/24/2019 | 09/25/2019 | 0 | 0 | 0 | 09/26/2019 | 09/26/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 177399 | 02188 | 75 | Solar | 05_14_48L3 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 | 06/29/2016 | 06/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 | 06/28/2016 | 7/5/2017 | Y | EXP | 310 | 08/03/2016 | 09/21/2016 | 34 | 0 | 34 | 3/8/2017 | 3/8/2017 | 3/8/2017 | Connected |  | N
National Grid | BILLERICA | 470177 | 01821 | 15.2 | Solar | 05_14_62L2 | 10/21/2022 | 10/25/2022 | 2 | 0 | 2 | 10/26/2022 | 10/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 10/21/2022 | 1/20/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2023 | Connected |  | N
National Grid | HAVERHILL | 636786 | 01830 | 10 | Solar | 05_14_75L5 | 08/30/2024 | 09/23/2024 | 3 | 0 | 3 | 09/24/2024 | 09/24/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 362751 | 01810 | 10 | Solar | 05_01_225W1 | 06/15/2021 | 06/16/2021 | 1 | 0 | 1 | 06/17/2021 | 06/17/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2021 |  | 7/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | Connected |  | Y
National Grid | LOWELL | 176166 | 01850 | 990 | Solar | 05_01_304W4 | 02/27/2015 | 02/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 178454 | 01523 | 4430 | Solar | 05_01_415L1 | 12/01/2017 | 12/01/2017 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/03/2018 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/6/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 616454 | 01527 | 4000 | Solar | 05_01_612W3 | 08/01/2024 | 11/25/2024 | 80 | 70 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 06/30/2025 | 146 | 127 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | CHARLTON | 691231 | 01507 | 20 | Solar | 05_05_17J1 | 05/13/2025 | 05/20/2025 | 5 | 0 | 5 | 05/21/2025 | 05/21/2025 | 23 | 0 | 23 | 07/29/2025 | 08/20/2025 | 17 | 16 | 1 |  |  | 0 | 0 | 0 | 08/20/2025 | 17 | 16 | 1 |  |  | 0 | 0 | 0 | 8/25/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 342097 | 01475 | 3.84 | Solar | 05_05_314W2 | 02/12/2021 | 02/16/2021 | 0 | 0 | 0 | 02/17/2021 | 02/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/15/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 464132 | 02726 | 80 | Solar | 05_12_37J3 | 10/26/2022 | 02/14/2023 | 74 | 63 | 11 | 02/15/2023 | 02/15/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2023 | 10/26/2022 | 7/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 254107 | 01772 | 100 | Solar | 05_14_18L3 | 11/27/2019 | 12/13/2019 | 9 | 0 | 9 | 12/16/2019 | 12/16/2019 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 | 11/27/2019 |  | Y | EXP | 365 | 08/04/2020 | 08/27/2020 | 23 | 0 | 23 |  |  | 9/21/2020 | Connected |  | N
National Grid | WEYMOUTH | 196416 | 02188 | 66.6 | Solar | 05_14_48L3 | 09/19/2018 | 10/08/2018 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 7/1/2020 | N | EXP | 406 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 481649 | 01821 | 9.984 | Solar | 05_14_62L2 | 01/16/2023 | 01/18/2023 | 2 | 0 | 2 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  | 10/27/2024 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  | 9/25/2024 | Connected |  | N
National Grid | HAVERHILL | 637809 | 01830 | 3.8 | Solar | 05_14_75L5 | 09/04/2024 | 09/18/2024 | 1 | 0 | 1 | 09/19/2024 | 09/19/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 377961 | 01810 | 7.6 | Solar | 05_01_225W1 | 08/25/2021 | 10/06/2021 | 29 | 28 | 1 | 10/07/2021 | 10/07/2021 | 70 | 47 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  | 10/5/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 176228 | 01826 | 6 | Solar | 05_01_304W4 | 09/02/2015 | 09/02/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/02/2015 | 9/12/2016 | Y | EXP | 355 | 07/29/2016 | 08/06/2016 | 6 | 0 | 6 | 9/23/2015 | 9/23/2015 | 8/23/2016 | Connected |  | N
National Grid | LANCASTER | 178578 | 01523 | 4950 | Solar | 05_01_415L1 | 01/30/2018 | 03/14/2018 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2018 | 05/18/2018 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2019 | 01/30/2018 | 4/22/2022 | Y | STD | 1197 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 715711 | 01527 | 7.6 | Solar | 05_01_612W3 | 08/29/2025 | 09/12/2025 | 12 | 9 | 3 | 12/08/2025 | 12/08/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 |  | 4/1/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHARLTON | 702804 | 01507 | 22.04 | Solar | 05_05_17J1 | 07/03/2025 | 07/10/2025 | 4 | 0 | 4 | 07/11/2025 | 07/11/2025 | 71 | 58 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 366728 | 01475 | 7.6 | Solar | 05_05_314W2 | 06/29/2021 | 08/26/2021 | 41 | 38 | 3 | 08/27/2021 | 08/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 | 06/29/2021 | 12/2/2023 | Y | EXP | 365 | 01/06/2022 | 10/31/2022 | 299 | 0 | 299 |  |  | 1/25/2023 | Connected |  | N
National Grid | SOMERSET | 754529 | 02726 | 18.497 | Solar | 05_12_37J4 | 03/10/2026 | 03/25/2026 | 10 | 9 | 1 | 03/26/2026 | 03/26/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBOROUGH | 330833 | 01772 | 4125 | Solar | 05_14_18L3 | 12/17/2021 | 01/26/2022 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2022 | 03/02/2022 | 24 | 15 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 413354 | 02149 | 3.8 | Solar | 05_14_48L3 | 02/25/2022 | 03/01/2022 | 2 | 0 | 2 | 03/02/2022 | 03/02/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2022 |  | 3/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2022 | Connected |  | N
National Grid | BILLERICA | 483147 | 01821 | 15.2 | Solar | 05_14_62L2 | 12/28/2022 | 01/18/2023 | 14 | 13 | 1 | 01/19/2023 | 01/19/2023 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 638053 | 01830 | 10.89 | Solar | 05_14_75L5 | 09/05/2024 | 09/26/2024 | 7 | 3 | 4 | 09/27/2024 | 09/27/2024 | 17 | 3 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 | 09/05/2024 | 11/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | ANDOVER | 396398 | 01810 | 0 | Solar | 05_01_225W1 | 11/18/2021 | 11/23/2021 | 4 | 2 | 2 | 11/24/2021 | 11/24/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 |  | 12/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2022 | Connected |  | N
National Grid | LOWELL | 176282 | 01850 | 19 | Solar | 05_01_304W4 | 05/06/2015 | 05/06/2015 | 3 | 3 | 0 | 05/13/2015 | 05/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 |  | 10/30/2015 | N | EXP | 169 |  |  | 0 | 0 | 0 | 12/7/2015 | 12/7/2015 | 12/7/2015 | Connected |  | N
National Grid | BOLTON | 178771 | 01740 | 1980 | Solar | 05_01_415L1 | 01/03/2012 | 01/03/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2012 | 09/25/2013 | 402 | 0 | 402 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2014 | 01/03/2012 | 12/31/2016 | Y | STD | 955 | 03/08/2016 | 09/02/2016 | 123 | 0 | 123 | 9/1/2016 | 9/1/2016 | 10/7/2016 | Connected |  | N
National Grid | MILLBURY | 724158 | 01527 | 7.6 | Solar | 05_01_612W3 | 11/05/2025 | 11/05/2025 | 3 | 0 | 3 | 11/26/2025 | 11/26/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 703902 | 01507 | 11.52 | Solar | 05_05_17J1 | 07/10/2025 | 08/13/2025 | 10 | 6 | 4 | 08/14/2025 | 08/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2026 | Connected |  | N
National Grid | WINCHENDON | 375292 | 01475 | 15.2 | Solar | 05_05_314W2 | 08/11/2021 | 12/27/2021 | 12 | 8 | 4 | 08/30/2021 | 08/30/2021 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2021 |  | 1/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2022 | Connected |  | N
National Grid | SOMERSET | 662378 | 02726 | 10 | Solar | 05_12_37J4 | 01/10/2025 | 02/07/2025 | 4 | 0 | 4 | 02/10/2025 | 02/10/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 406505 | 01772 | 8.027 | Solar | 05_14_18L3 | 04/19/2022 | 04/27/2022 | 6 | 6 | 0 | 04/28/2022 | 04/28/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 | 04/19/2022 | 11/19/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | EVERETT | 618825 | 02149 | 7.6 | Solar | 05_14_48L3 | 06/18/2024 | 06/24/2024 | 2 | 0 | 2 | 07/07/2025 | 07/07/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 06/18/2024 | 8/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2026 | Connected |  | N
National Grid | BILLERICA | 489268 | 01821 | 22.75 | Solar | 05_14_62L2 | 01/13/2023 | 01/18/2023 | 3 | 1 | 2 | 01/19/2023 | 01/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2023 |  | 2/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N
National Grid | HAVERHILL | 643195 | 01830 | 7.6 | Solar | 05_14_75L5 | 09/27/2024 | 10/16/2024 | 5 | 2 | 3 | 10/17/2024 | 10/17/2024 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 09/27/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | ANDOVER | 416510 | 01810 | 0 | Solar | 05_01_225W1 | 03/09/2022 | 03/10/2022 | 1 | 0 | 1 | 03/11/2022 | 03/11/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 |  | 4/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2022 | Connected |  | N
National Grid | DRACUT | 176446 | 01826 | 72 | Solar | 05_01_304W4 | 05/17/2016 | 05/17/2016 | 20 | 20 | 0 | 06/15/2016 | 06/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2016 |  | 5/22/2017 | N | EXP | 332 |  |  | 0 | 0 | 0 | 10/3/2016 | 10/3/2016 | 10/3/2016 | Connected |  | N
National Grid | BOLTON | 213693 | 01740 | 30 | Solar | 05_01_415L1 | 03/21/2019 | 05/21/2019 | 43 | 40 | 3 | 05/22/2019 | 05/22/2019 | 267 | 73 | 194 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 737858 | 01527 | 10 | Solar | 05_01_612W3 | 12/03/2025 | 12/10/2025 | 1 | 0 | 1 | 12/18/2025 | 12/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 640868 | 01507 | 15.2 | Solar | 05_05_17J3 | 11/13/2024 | 11/19/2024 | 5 | 3 | 2 | 11/20/2024 | 11/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2025 | Connected |  | N
National Grid | WINCHENDON | 375895 | 01475 | 9.6 | Solar | 05_05_314W2 | 08/13/2021 | 09/15/2021 | 22 | 21 | 1 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 | 08/13/2021 | 5/7/2023 | Y | EXP | 365 | 04/07/2022 | 04/27/2022 | 21 | 0 | 21 |  |  | 5/27/2022 | Connected |  | N
National Grid | SOMERSET | 578954 | 02726 | 200 | Solar | 05_12_37W1 | 01/03/2024 | 01/11/2024 | 6 | 0 | 6 | 01/12/2024 | 01/12/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 7/15/2026 | N | EXP | 180 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SOUTHBOROUGH | 413213 | 01772 | 9.57 | Solar | 05_14_18L3 | 02/21/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  | 4/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/26/2022 | Connected |  | N
National Grid | EVERETT | 669659 | 02149 | 0 | Battery Add-On | 05_14_48L3 | 02/03/2025 | 02/06/2025 | 3 | 0 | 3 | 02/07/2025 | 02/07/2025 | 59 | 38 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2025 | Connected |  | N
National Grid | BILLERICA | 571929 | 01821 | 0 | Solar | 05_14_62L2 | 11/16/2023 | 11/27/2023 | 6 | 0 | 6 | 11/28/2023 | 11/28/2023 | 71 | 51 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | HAVERHILL | 646399 | 01830 | 5.76 | Solar | 05_14_75L5 | 10/16/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/16/2024 | 12/24/2025 | Y | EXP | 365 | 01/16/2025 | 02/18/2025 | 33 | 0 | 33 |  |  | 3/14/2025 | Connected |  | N
National Grid | ANDOVER | 422557 | 01810 | 15.2 | Solar | 05_01_225W1 | 04/14/2022 | 04/20/2022 | 4 | 3 | 1 | 04/21/2022 | 04/21/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2022 |  | 5/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2022 | Connected |  | N
National Grid | LOWELL | 176464 | 01850 | 4.3 | Solar | 05_01_304W4 | 02/05/2016 | 02/05/2016 | 4 | 4 | 0 | 02/12/2016 | 02/12/2016 | 235 | 0 | 235 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 |  | 2/13/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 214422 | 01740 | 3.655 | Solar | 05_01_415L1 | 03/20/2019 | 06/05/2019 | 23 | 19 | 4 | 06/06/2019 | 06/06/2019 | 16 | 13 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2019 |  | 9/17/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 174544 | 01527 | 2000 | Solar | 05_01_612W3 | 11/16/2011 | 11/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 741251 | 01507 | 7.6 | Solar | 05_05_17J3 | 12/18/2025 | 12/22/2025 | 2 | 0 | 2 | 12/23/2025 | 12/23/2025 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 375524 | 01475 | 7.6 | Solar | 05_05_314W2 | 08/12/2021 | 09/02/2021 | 16 | 15 | 1 | 09/03/2021 | 09/03/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2021 |  | 11/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2022 | Connected |  | N
National Grid | SOMERSET | 658074 | 02726 | 84.6 | Solar | 05_12_37W1 | 01/09/2025 |  | 305 | 58 | 247 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SOUTHBOROUGH | 434023 | 01772 | 0 | Other | 05_14_18L3 | 09/07/2022 | 09/28/2022 | 15 | 6 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/29/2022 | 10/26/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 691118 | 02155 | 13.8 | Solar | 05_14_48L3 | 05/15/2025 | 05/20/2025 | 3 | 0 | 3 | 05/21/2025 | 05/21/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | BILLERICA | 572719 | 01821 | 22.8 | Solar | 05_14_62L2 | 11/20/2023 | 12/11/2023 | 14 | 13 | 1 | 12/12/2023 | 12/12/2023 | 32 | 12 | 20 | 01/31/2024 | 02/21/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 02/21/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 3/5/2025 | N | EXP | 365 | 05/18/2024 | 06/28/2024 | 42 | 0 | 42 |  |  | 7/3/2024 | Connected |  | Y
National Grid | HAVERHILL | 646853 | 01830 | 5.76 | Solar | 05_14_75L5 | 10/29/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | ANDOVER | 424363 | 01810 | 7.6 | Solar | 05_01_225W1 | 05/11/2022 | 05/18/2022 | 6 | 5 | 1 | 05/19/2022 | 05/19/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 8/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2022 | Connected |  | N
National Grid | DRACUT | 176619 | 01826 | 10 | Solar | 05_01_304W4 | 04/11/2016 | 04/11/2016 | 2 | 2 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/11/2016 | 10/17/2017 | Y | EXP | 539 | 06/30/2017 | 06/28/2017 | 0 | 0 | 0 | 7/14/2017 | 7/14/2017 | 7/14/2017 | Connected |  | N
National Grid | LANCASTER | 265490 | 01523 | 4950 | Other | 05_01_415L1 | 03/17/2020 | 04/24/2020 | 27 | 24 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/11/2020 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 174543 | 01527 | 2000 | Solar | 05_01_612W3 | 11/16/2011 | 11/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 743962 | 01566 | 7.6 | Solar | 05_05_18J5 | 01/07/2026 | 01/09/2026 | 2 | 1 | 1 | 01/12/2026 | 01/12/2026 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WINCHENDON | 420913 | 01475 | 15.2 | Solar | 05_05_314W2 | 06/17/2022 | 06/22/2022 | 2 | 0 | 2 | 06/23/2022 | 06/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 192277 | 02726 | 340 | Solar | 05_12_37W1 | 09/11/2018 | 09/13/2018 | 1 | 0 | 1 | 09/14/2018 | 09/14/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  | 5/10/2021 | N | EXP | 409 | 02/13/2020 | 05/06/2021 | 449 | 5 | 444 |  |  | 5/19/2021 | Connected |  | N
National Grid | SOUTHBOROUGH | 503842 | 01772 | 10 | Solar | 05_14_18L3 | 03/09/2023 | 03/10/2023 | 2 | 1 | 1 | 03/13/2023 | 03/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 | 03/09/2023 | 5/25/2024 | Y | EXP | 365 | 09/26/2023 | 10/12/2023 | 17 | 0 | 17 |  |  | 10/16/2023 | Connected |  | N
National Grid | MEDFORD | 685494 | 02155 | 180 | Solar | 05_14_48L4 | 04/16/2025 | 05/23/2025 | 26 | 17 | 9 | 05/27/2025 | 05/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 | 04/16/2025 | 6/29/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BILLERICA | 604796 | 01821 | 0 | Battery Add-On | 05_14_62L2 | 04/22/2024 | 05/20/2024 | 21 | 20 | 1 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 651149 | 01830 | 5.76 | Solar | 05_14_75L5 | 11/12/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | ANDOVER | 428357 | 01810 | 9.57 | Solar | 05_01_225W1 | 05/04/2022 | 05/05/2022 | 1 | 1 | 0 | 05/06/2022 | 05/06/2022 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 | 05/04/2022 | 11/10/2023 | Y | EXP | 365 | 09/30/2022 | 11/09/2022 | 41 | 0 | 41 |  |  | 6/14/2023 | Connected |  | N
National Grid | DRACUT | 178124 | 01826 | 1000 | Solar | 05_01_304W4 | 05/15/2017 | 05/15/2017 | 18 | 14 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2017 | 07/03/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2017 | 05/15/2017 | 6/28/2019 | Y | STD | 596 | 12/13/2018 | 05/23/2019 | 161 | 0 | 161 |  |  | 6/27/2019 | Connected |  | N
National Grid | BOLTON | 265320 | 01740 | 0 | Other | 05_01_415L1 | 02/14/2020 | 03/23/2020 | 25 | 22 | 3 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 | 03/24/2020 | 03/23/2020 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 174542 | 01527 | 2000 | Solar | 05_01_612W3 | 11/16/2011 | 11/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 175863 | 01507 | 7.6 | Solar | 05_05_18J5 | 09/21/2015 | 09/21/2015 | 2 | 2 | 0 | 09/25/2015 | 09/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 |  | 9/28/2016 | N | EXP | 341 |  |  | 0 | 0 | 0 | 10/23/2015 | 10/23/2015 | 4/29/2016 | Connected |  | N
National Grid | WINCHENDON | 430664 | 01475 | 5.04 | Solar | 05_05_314W2 | 06/03/2022 | 06/06/2022 | 1 | 0 | 1 | 06/07/2022 | 06/07/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 06/03/2022 | 12/12/2023 | Y | EXP | 365 | 12/13/2022 | 01/03/2023 | 22 | 0 | 22 |  |  | 1/5/2023 | Connected |  | N
National Grid | SOMERSET | 280051 | 02726 | 462.5 | Solar | 05_12_37W1 | 04/24/2020 | 05/12/2020 | 12 | 8 | 4 |  |  | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 559528 | 01772 | 13.34 | Solar | 05_14_18L3 | 10/03/2023 | 10/12/2023 | 6 | 4 | 2 | 10/13/2023 | 10/13/2023 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 710023 | 02148 | 240 | Solar | 05_14_48L4 | 08/07/2025 | 09/16/2025 | 27 | 17 | 10 | 09/17/2025 | 09/17/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 | 08/07/2025 | 9/23/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BILLERICA | 670001 | 01821 | 5.76 | Solar | 05_14_62L2 | 02/11/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 145 | 127 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 651011 | 01830 | 6 | Solar | 05_14_75L5 | 11/12/2024 | 02/05/2025 | 30 | 25 | 5 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | ANDOVER | 442327 | 01810 | 15 | Solar | 05_01_225W1 | 07/18/2022 | 07/20/2022 | 3 | 2 | 1 | 07/21/2022 | 07/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2022 |  | 9/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2022 | Connected |  | N
National Grid | LOWELL | 178699 | 01850 | 2000 | Solar | 05_01_304W4 | 02/07/2018 | 03/26/2018 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2018 | 04/23/2018 | 164 | 42 | 122 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/13/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 273360 | 01451 | 5000 | Other | 05_01_415L1 | 03/19/2020 | 03/25/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2020 | 04/07/2020 | 8 | 0 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 174980 | 01527 | 1000 | Solar | 05_01_612W3 | 09/07/2011 | 09/07/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 176359 | 01507 | 5 | Solar | 05_05_18J5 | 03/07/2016 | 03/07/2016 | 2 | 2 | 0 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2016 | 03/07/2016 | 3/13/2017 | Y | EXP | 325 | 07/27/2016 | 08/15/2016 | 13 | 0 | 13 | 4/22/2016 | 4/22/2016 | 10/19/2016 | Connected |  | N
National Grid | WINCHENDON | 643694 | 01475 | 19 | Solar | 05_05_314W2 | 09/30/2024 | 10/22/2024 | 16 | 14 | 2 | 10/23/2024 | 10/23/2024 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 315641 | 02726 | 7.68 | Solar | 05_12_37W1 | 09/28/2020 | 10/19/2020 | 14 | 12 | 2 | 10/20/2020 | 10/20/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 10/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2021 | Connected |  | N
National Grid | SOUTHBOROUGH | 587504 | 01772 | 7.25 | Solar | 05_14_18L3 | 02/12/2024 | 02/15/2024 | 3 | 0 | 3 | 02/16/2024 | 02/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 02/12/2024 | 2/28/2025 | Y | EXP | 365 | 06/05/2024 | 07/17/2024 | 43 | 0 | 43 |  |  | 7/24/2024 | Connected |  | N
National Grid | MEDFORD | 735933 | 02155 | 10 | Solar | 05_14_48L4 | 11/24/2025 | 11/25/2025 | 2 | 0 | 2 | 12/16/2025 | 12/16/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 715329 | 01821 | 11.84 | Solar | 05_14_62L2 | 09/02/2025 | 11/07/2025 | 9 | 5 | 4 | 11/10/2025 | 11/10/2025 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2026 | Connected |  | N
National Grid | HAVERHILL | 654398 | 01832 | 5.32 | Solar | 05_14_75L5 | 11/14/2024 | 01/06/2025 | 28 | 24 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 3/21/2026 | N | EXP | 365 | 02/21/2025 | 04/29/2025 | 68 | 27 | 41 |  |  | 5/6/2025 | Connected |  | N
National Grid | ANDOVER | 444227 | 01810 | 7.6 | Solar | 05_01_225W1 | 07/14/2022 | 07/25/2022 | 3 | 0 | 3 | 11/03/2022 | 11/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 | 07/14/2022 | 8/30/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2023 | Connected |  | N
National Grid | LOWELL | 186042 | 01850 | 3400 | Solar | 05_01_304W4 | 06/07/2018 | 07/18/2018 | 28 | 26 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2018 | 07/30/2018 | 8 | 7 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2019 | 06/07/2018 | 8/4/2023 | Y | STD | 488 | 04/02/2022 | 01/13/2023 | 287 | 0 | 287 | 6/7/2023 | 6/27/2023 | 7/25/2023 | Connected |  | N
National Grid | BOLTON | 308485 | 01740 | 0 | Other | 05_01_415L1 | 09/08/2020 | 09/21/2020 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/09/2020 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 175008 | 01536 | 1900 | Solar | 05_01_612W3 | 09/07/2011 | 09/07/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/07/2011 | 11/30/2012 | Y | STD | 12 |  |  | 0 | 0 | 0 | 3/6/2014 | 3/6/2014 | 3/7/2014 | Connected |  | N
National Grid | CHARLTON | 176564 | 01507 | 42 | Solar | 05_05_18J5 | 12/22/2015 | 12/22/2015 | 22 | 22 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2016 |  | 12/27/2016 | N | EXP | 335 |  |  | 0 | 0 | 0 | 2/4/2016 | 2/4/2016 | 6/16/2016 | Connected |  | N
National Grid | WINCHENDON | 674379 | 01475 | 15.356 | Solar | 05_05_314W2 | 03/11/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | SOMERSET | 563473 | 02726 | 10 | Solar | 05_12_37W1 | 11/15/2023 | 11/16/2023 | 1 | 0 | 1 | 11/17/2023 | 11/17/2023 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2024 | 11/15/2023 | 1/26/2025 | Y | EXP | 365 | 03/14/2024 | 06/14/2024 | 93 | 0 | 93 |  |  | 7/18/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 609946 | 01772 | 19.175 | Solar | 05_14_18L3 | 05/14/2024 | 05/28/2024 | 10 | 8 | 2 | 05/29/2024 | 05/29/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/14/2024 | 7/22/2025 | Y | EXP | 365 | 08/09/2024 | 08/28/2024 | 20 | 0 | 20 |  |  | 9/12/2024 | Connected |  | N
National Grid | MEDFORD | 756064 | 02155 | 5.76 | Solar | 05_14_48L4 | 03/11/2026 | 03/17/2026 | 4 | 0 | 4 | 03/31/2026 | 03/31/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BILLERICA | 702798 | 01862 | 3 | Solar | 05_14_63L1 | 07/07/2025 | 07/23/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 56 | 44 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 654202 | 01832 | 7.6 | Solar | 05_14_75L5 | 11/13/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/13/2024 | 3/27/2026 | Y | EXP | 365 | 05/24/2025 | 11/17/2025 | 178 | 0 | 178 |  |  | 7/21/2025 | Connected |  | N
National Grid | ANDOVER | 460092 | 01810 | 7.6 | Solar | 05_01_225W1 | 09/19/2022 | 10/03/2022 | 10 | 5 | 5 | 10/04/2022 | 10/04/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 |  | 11/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/24/2023 | Connected |  | N
National Grid | LOWELL | 189157 | 01850 | 200 | Solar | 05_01_304W4 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 308478 | 01740 | 0 | Other | 05_01_415L1 | 08/25/2020 | 09/30/2020 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 11/17/2020 | 31 | 14 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/25/2020 | 2/17/2025 | Y | STD | 700 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 176569 | 01527 | 7.6 | Solar | 05_01_612W3 | 12/24/2015 | 12/24/2015 | 4 | 4 | 0 | 12/31/2015 | 12/31/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2016 |  | 12/29/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 5/26/2016 | 5/26/2016 | 9/12/2016 | Connected |  | N
National Grid | CHARLTON | 176988 | 01507 | 3.8 | Solar | 05_05_18J5 | 03/10/2017 | 03/10/2017 | 4 | 2 | 2 | 03/16/2017 | 03/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 |  | 3/15/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 6/5/2017 | 6/5/2017 | 6/7/2017 | Connected |  | N
National Grid | WINCHENDON | 683056 | 01475 | 15.2 | Solar | 05_05_314W2 | 04/07/2025 | 04/10/2025 | 3 | 0 | 3 | 04/11/2025 | 04/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 5/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | SOMERSET | 639527 | 02726 | 7.6 | Solar | 05_12_37W1 | 09/11/2024 | 09/27/2024 | 2 | 0 | 2 | 09/30/2024 | 09/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 09/11/2024 | 11/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 649590 | 01772 | 7.6 | Solar | 05_14_18L3 | 10/24/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 176406 | 02155 | 720 | Solar | 05_14_48L4 | 05/09/2016 | 05/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2016 | 07/13/2016 | 42 | 32 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/16/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 710704 | 01862 | 15.32 | Solar | 05_14_63L1 | 08/08/2025 | 08/15/2025 | 5 | 0 | 5 | 08/18/2025 | 08/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | HAVERHILL | 657885 | 01832 | 6.38 | Solar | 05_14_75L5 | 12/02/2024 | 01/03/2025 | 4 | 2 | 2 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | METHUEN | 484329 | 01844 | 0 | Solar | 05_01_225W1 | 12/09/2022 | 02/10/2023 | 42 | 35 | 7 | 02/13/2023 | 02/13/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 189148 | 01850 | 200 | Solar | 05_01_304W4 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 315126 | 01523 | 0 | Other | 05_01_415L1 | 01/02/2021 | 02/04/2021 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2021 | 03/08/2021 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 176754 | 01057 | 10 | Solar | 05_01_612W3 | 01/12/2016 | 01/12/2016 | 4 | 4 | 0 | 01/20/2016 | 01/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2016 |  | 1/18/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/27/2016 | 1/27/2016 | 5/27/2016 | Connected |  | N
National Grid | CHARLTON | 188458 | 01507 | 8.36 | Solar | 05_05_18J5 | 07/05/2018 | 08/03/2018 | 21 | 0 | 21 | 08/06/2018 | 08/06/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 741732 | 01475 | 7.6 | Solar | 05_05_314W3 | 12/22/2025 | 01/02/2026 | 7 | 6 | 1 | 01/05/2026 | 01/05/2026 | 32 | 18 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 658042 | 02726 | 84.6 | Solar | 05_12_37W1 | 01/09/2025 |  | 93 | 83 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 662428 | 01772 | 5.76 | Solar | 05_14_18L3 | 12/23/2024 | 03/12/2025 | 19 | 14 | 5 | 03/13/2025 | 03/13/2025 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 176573 | 02155 | 1462 | Solar | 05_14_48L4 | 02/11/2016 | 02/11/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/17/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 717012 | 01821 | 10 | Solar | 05_14_63L1 | 09/05/2025 | 09/16/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 661283 | 01832 | 15.2 | Solar | 05_14_75L5 | 02/11/2025 |  | 101 | 80 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 483675 | 01844 | 13.92 | Solar | 05_01_225W1 | 12/14/2022 | 12/20/2022 | 4 | 1 | 3 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 5/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2023 | Connected |  | N
National Grid | DRACUT | 189080 | 01826 | 200 | Solar | 05_01_304W4 | 06/25/2018 | 06/25/2018 | 1 | 0 | 1 | 06/28/2018 | 06/28/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 365577 | 01451 | 7.6 | Solar | 05_01_415L1 | 06/23/2021 | 07/20/2021 | 18 | 14 | 4 | 07/21/2021 | 07/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2021 |  | 9/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2021 | Connected |  | Y
National Grid | PALMER | 177431 | 01069 | 0 | Solar | 05_01_612W3 | 02/27/2017 | 02/27/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2017 | 04/14/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/6/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 200437 | 01507 | 10 | Solar | 05_05_18J5 | 11/06/2018 | 02/14/2019 | 58 | 57 | 1 | 02/15/2019 | 02/15/2019 | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2019 | 11/06/2018 | 12/6/2019 | Y | EXP | 275 | 06/06/2019 | 07/19/2019 | 43 | 0 | 43 |  |  | 8/6/2019 | Connected |  | N
National Grid | WINCHENDON | 749261 | 01477 |  | Battery Add-On | 05_05_314W3 | 02/04/2026 | 02/06/2026 | 2 | 0 | 2 | 02/09/2026 | 02/09/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  | 3/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 668952 | 02726 | 7.6 | Solar | 05_12_37W1 | 02/03/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | WESTBOROUGH | 679351 | 01581 | 13.25 | Solar | 05_14_18L3 | 03/22/2025 | 03/27/2025 | 4 | 1 | 3 | 03/28/2025 | 03/28/2025 | 55 | 40 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2025 | Connected |  | Y
National Grid | MEDFORD | 176616 | 02155 | 1335.6 | Solar | 05_14_48L4 | 02/11/2016 | 02/11/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/22/2016 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2016 |  | 2/22/2017 | N | STD | 161 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 722551 | 01862 | 5.584 | Solar | 05_14_63L1 | 09/29/2025 | 10/07/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 661713 | 01832 | 3.8 | Solar | 05_14_75L5 | 12/19/2024 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 485679 | 01844 | 15.6 | Solar | 05_01_225W1 | 12/15/2022 | 02/09/2023 | 37 | 36 | 1 | 02/10/2023 | 02/10/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  | 3/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2023 | Connected |  | N
National Grid | LOWELL | 224988 | 01850 | 2.4 | Solar | 05_01_304W4 | 06/25/2019 | 10/15/2019 | 104 | 102 | 2 | 10/24/2019 | 10/24/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 | 06/25/2019 | 6/10/2021 | Y | EXP | 365 | 01/12/2021 | 02/04/2021 | 23 | 0 | 23 |  |  | 2/17/2021 | Connected |  | N
National Grid | BOLTON | 377511 | 01740 | 999 | Solar | 05_01_415L1 | 04/26/2022 | 05/18/2022 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/19/2022 | 06/15/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 177430 | 01057 | 1000 | Solar | 05_01_612W3 | 02/27/2017 | 03/23/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2017 | 04/14/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 | 02/27/2017 | 12/31/2020 | Y | STD | 1142 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 291755 | 01507 | 7.6 | Solar | 05_05_18J5 | 05/19/2020 | 05/20/2020 | 0 | 0 | 0 | 05/21/2020 | 05/21/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 174313 | 01475 | 95 | Solar | 05_05_314W3 | 01/11/2012 | 01/11/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2012 |  | 5/1/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 8/27/2012 | 8/27/2012 | 9/10/2012 | Connected |  | N
National Grid | SOMERSET | 707738 | 02726 | 7.6 | Solar | 05_12_37W10 | 08/01/2025 | 08/22/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 | 08/01/2025 | 10/17/2026 | Y | EXP | 365 | 01/13/2026 |  | 79 | 0 | 79 |  |  |  | Construction |  | N
National Grid | WESTBOROUGH | 178218 | 01581 | 10 | Solar | 05_14_1J1 | 04/13/2018 | 04/13/2018 | 10 | 0 | 10 | 05/01/2018 | 05/01/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 |  | 4/21/2019 | N | EXP | 333 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 184579 | 02155 | 37.6 | Solar | 05_14_48L4 | 05/07/2018 | 05/07/2018 | 0 | 0 | 0 | 05/17/2018 | 05/17/2018 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 722050 | 01821 | 0 | Battery Add-On | 05_14_63L1 | 10/15/2025 | 10/31/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 37 | 20 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/21/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 732423 | 01832 | 5.76 | Solar | 05_14_75L5 | 11/12/2025 | 11/13/2025 | 4 | 0 | 4 | 11/28/2025 | 11/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 488296 | 01844 | 0 | Solar | 05_01_225W1 | 12/27/2022 | 01/03/2023 | 4 | 1 | 3 | 01/04/2023 | 01/04/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 228730 | 01850 | 7.6 | Solar | 05_01_304W4 | 07/05/2019 | 10/03/2019 | 63 | 58 | 5 | 10/04/2019 | 10/04/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 |  | 7/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 409406 | 01740 | 7.6 | Solar | 05_01_415L1 | 10/28/2022 | 01/24/2023 | 57 | 51 | 6 | 01/25/2023 | 01/25/2023 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 | 10/28/2022 | 5/29/2024 | Y | EXP | 365 | 04/27/2023 | 06/08/2023 | 43 | 0 | 43 |  |  | 8/24/2023 | Connected |  | N
National Grid | MILLBURY | 177470 | 01527 | 0 | Solar | 05_01_612W3 | 02/28/2017 | 02/28/2017 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2017 | 04/20/2017 | 19 | 4 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/7/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 324590 | 01507 | 7.6 | Solar | 05_05_18J5 | 11/25/2020 | 11/30/2020 | 1 | 0 | 1 | 12/01/2020 | 12/01/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 189184 | 01475 | 15.2 | Solar | 05_05_314W3 | 06/26/2018 | 06/26/2018 | 15 | 9 | 6 | 07/23/2018 | 07/23/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 254430 | 02726 | 3.8 | Solar | 05_12_37W10 | 10/02/2019 | 10/07/2019 | 2 | 0 | 2 | 10/08/2019 | 10/08/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 546449 | 01581 | 4.93 | Solar | 05_14_1J1 | 08/23/2023 | 09/06/2023 | 10 | 9 | 1 | 09/07/2023 | 09/07/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2023 |  | 11/18/2024 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | MALDEN | 191108 | 02148 | 52.2 | Solar | 05_14_48L4 | 07/18/2018 | 08/06/2018 | 13 | 11 | 2 | 08/07/2018 | 08/07/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 725342 | 01843 | 3.8 | Solar | 05_14_63L1 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 51 | 34 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 | 10/09/2025 | 12/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | HAVERHILL | 654679 | 01830 | 7.6 | Solar | 05_14_75L6 | 11/15/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 11/15/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 495716 | 01841 | 0 | Solar | 05_01_225W1 | 01/27/2023 | 02/01/2023 | 4 | 3 | 1 | 02/02/2023 | 02/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2023 |  | 3/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2024 | Connected |  | N
National Grid | DRACUT | 242650 | 01826 | 3.8 | Solar | 05_01_304W4 | 07/24/2019 | 08/02/2019 | 6 | 5 | 1 | 08/05/2019 | 08/05/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 | 07/24/2019 | 8/3/2020 | Y | EXP | 365 | 02/01/2020 | 02/26/2020 | 25 | 0 | 25 |  |  | 3/2/2020 | Connected |  | N
National Grid | HARVARD | 414142 | 01451 | 0 | Solar | 05_01_415L1 | 02/24/2022 | 04/15/2022 | 36 | 35 | 1 | 04/19/2022 | 04/19/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 |  | 7/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 177469 | 01527 | 4979.98 | Solar | 05_01_612W3 | 02/28/2017 | 03/29/2017 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2017 | 04/20/2017 | 15 | 4 | 11 |  | 0 | 0 | 0 | 12/16/2017 | 10/10/2018 | 74 | 0 | 74 | 11/20/2017 | 02/28/2017 | 12/31/2019 | Y | STD | 351 | 09/14/2019 | 12/26/2019 | 103 | 0 | 103 |  |  | 12/26/2019 | Connected |  | N
National Grid | STURBRIDGE | 467759 | 01566 | 6 | Solar | 05_05_18J5 | 10/14/2022 | 10/21/2022 | 6 | 5 | 1 | 10/24/2022 | 10/24/2022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 202461 | 01475 | 75 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 313741 | 02726 | 7.6 | Solar | 05_12_37W10 | 10/01/2020 | 10/06/2020 | 2 | 0 | 2 | 10/07/2020 | 10/07/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2020 | 10/01/2020 | 11/13/2021 | Y | EXP | 365 | 08/02/2021 | 08/11/2021 | 9 | 0 | 9 |  |  | 9/15/2021 | Connected |  | Y
National Grid | WESTBOROUGH | 612368 | 01581 | 5.76 | Solar | 05_14_1J1 | 05/20/2024 | 05/29/2024 | 2 | 0 | 2 | 05/30/2024 | 05/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | EVERETT | 267314 | 02149 | 37.8 | Solar | 05_14_48L4 | 06/18/2020 | 07/13/2020 | 17 | 17 | 0 | 07/14/2020 | 07/14/2020 | 80 | 57 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2020 |  | 6/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2021 | Connected |  | N
National Grid | LAWRENCE | 738581 | 01843 | 11.5 | Solar | 05_14_63L1 | 12/08/2025 | 12/19/2025 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 58 | 46 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HAVERHILL | 737727 | 01830 | 5.76 | Solar | 05_14_75L6 | 12/03/2025 | 12/17/2025 | 2 | 0 | 2 | 12/24/2025 | 12/24/2025 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 |  | 1/28/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 506817 | 01844 | 13.34 | Solar | 05_01_225W1 | 03/20/2023 | 03/23/2023 | 3 | 0 | 3 | 03/24/2023 | 03/24/2023 | 25 | 0 | 25 | 06/21/2023 | 08/09/2023 | 35 | 0 | 35 |  |  | 0 | 0 | 0 | 08/09/2023 | 35 | 0 | 35 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 8/14/2024 | N | EXP | 365 | 10/05/2023 | 10/18/2023 | 14 | 0 | 14 |  |  | 10/27/2023 | Connected |  | Y
National Grid | METHUEN | 244233 | 01844 | 3.8 | Solar | 05_01_304W4 | 07/24/2019 | 07/26/2019 | 1 | 0 | 1 | 07/29/2019 | 07/29/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 12/2/2019 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | BOLTON | 418661 | 01740 | 8.12 | Solar | 05_01_415L1 | 04/20/2022 | 04/21/2022 | 1 | 0 | 1 | 04/22/2022 | 04/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 | 04/20/2022 | 4/12/2024 | Y | EXP | 365 | 04/06/2023 | 04/12/2023 | 7 | 0 | 7 |  |  | 5/15/2023 | Connected |  | N
National Grid | MILLBURY | 177468 | 01527 | 3150 | Solar | 05_01_612W3 | 02/28/2017 | 03/29/2017 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2017 | 04/20/2017 | 15 | 4 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2017 | 02/28/2017 | 12/31/2019 | Y | STD | 330 | 08/29/2019 | 12/26/2019 | 119 | 0 | 119 |  |  | 12/26/2019 | Connected |  | N
National Grid | CHARLTON | 522489 | 01507 | 6 | Solar | 05_05_18J5 | 07/18/2023 | 08/10/2023 | 18 | 15 | 3 | 08/11/2023 | 08/11/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 | 07/18/2023 | 10/5/2024 | Y | EXP | 365 | 12/07/2023 | 12/07/2023 | 1 | 0 | 1 |  |  | 12/28/2023 | Connected |  | N
National Grid | WINCHENDON | 202201 | 01475 | 120 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 532886 | 02726 | 6 | Solar | 05_12_37W10 | 09/13/2023 | 09/19/2023 | 5 | 2 | 3 | 09/20/2023 | 09/20/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 641339 | 01581 | 7.6 | Solar | 05_14_1J1 | 09/18/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 1/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | MALDEN | 438729 | 02148 | 6 | Solar | 05_14_48L4 | 06/29/2022 | 07/05/2022 | 3 | 0 | 3 | 07/06/2022 | 07/06/2022 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2022 | 06/29/2022 | 8/25/2023 | Y | EXP | 365 | 10/13/2022 | 10/25/2022 | 13 | 0 | 13 |  |  | 10/31/2022 | Connected |  | Y
National Grid | LAWRENCE | 752895 | 01843 | 15 | Solar | 05_14_63L1 | 02/25/2026 | 03/03/2026 | 2 | 0 | 2 | 03/27/2026 | 03/27/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAVERHILL | 174341 | 01832 | 225 | Solar | 05_14_75L6 | 01/30/2012 | 01/30/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 524294 | 01844 | 15.2 | Solar | 05_01_225W1 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 6/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2023 | Connected |  | N
National Grid | METHUEN | 286667 | 01844 | 10 | Solar | 05_01_304W4 | 05/18/2020 | 05/19/2020 | 0 | 0 | 0 | 05/20/2020 | 05/20/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 |  | 5/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 429910 | 01740 | 15.2 | Solar | 05_01_415L1 | 05/11/2022 | 05/17/2022 | 5 | 4 | 1 | 05/18/2022 | 05/18/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 6/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2022 | Connected |  | N
National Grid | MILLBURY | 177920 | 01527 | 9765 | Solar | 05_01_612W3 | 10/23/2017 | 11/21/2017 | 13 | 8 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/19/2017 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/23/2017 |  | Y | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 176821 | 01566 | 6 | Solar | 05_05_18J7 | 01/14/2016 | 01/14/2016 | 2 | 2 | 0 | 01/20/2016 | 01/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 1/20/2017 | N | EXP | 346 |  |  | 0 | 0 | 0 | 6/1/2016 | 6/1/2016 | 6/6/2016 | Connected |  | N
National Grid | WINCHENDON | 203268 | 01475 | 105 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 640115 | 02726 | 3.8 | Solar | 05_12_37W10 | 09/13/2024 | 10/10/2024 | 3 | 0 | 3 | 10/11/2024 | 10/11/2024 | 38 | 23 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 09/13/2024 | 12/30/2025 | Y | EXP | 365 | 02/26/2025 | 03/21/2025 | 24 | 0 | 24 |  |  | 4/2/2025 | Connected |  | N
National Grid | WESTBOROUGH | 174789 | 01581 | 60 | Solar | 05_14_1J2 | 06/03/2011 | 06/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2011 |  | 3/12/2012 | N | EXP | 147 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 3/12/2012 | Connected |  | N
National Grid | MALDEN | 488061 | 02148 | 7.6 | Solar | 05_14_48L4 | 02/24/2023 | 01/01/2023 | 3 | 0 | 3 | 03/02/2023 | 03/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/1/2023 | 02/24/2023 | 5/14/2024 | Y | EXP | 365 | 08/12/2023 | 10/09/2023 | 59 | 0 | 59 |  |  | 10/18/2023 | Connected |  | Y
National Grid | LAWRENCE | 757058 | 01843 | 11.4 | Solar | 05_14_63L1 | 03/17/2026 | 03/20/2026 | 3 | 0 | 3 | 03/23/2026 | 03/23/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAVERHILL | 177114 | 01832 | 3.8 | Solar | 05_14_75L6 | 08/05/2016 | 08/05/2016 | 1 | 1 | 0 | 08/10/2016 | 08/10/2016 | 125 | 0 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2016 |  | 8/14/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 556180 | 01844 | 0 | Battery Add-On | 05_01_225W1 | 09/18/2023 | 10/11/2023 | 17 | 16 | 1 | 10/12/2023 | 10/12/2023 | 223 | 205 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 440801 | 01844 | 11.89 | Solar | 05_01_304W4 | 07/27/2022 | 08/01/2022 | 4 | 3 | 1 | 08/02/2022 | 08/02/2022 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2022 |  | 9/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N
National Grid | BOLTON | 435573 | 01740 | 7.6 | Solar | 05_01_415L1 | 06/14/2022 | 06/15/2022 | 1 | 0 | 1 | 06/16/2022 | 06/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2022 | 06/14/2022 | 6/22/2024 | Y | EXP | 365 | 05/10/2023 | 06/22/2023 | 44 | 0 | 44 |  |  | 6/30/2023 | Connected |  | N
National Grid | GRAFTON | 178258 | 01536 | 4999 | Solar | 05_01_612W3 | 04/17/2018 | 04/17/2018 | 4 | 3 | 1 |  |  | 79 | 67 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 176860 | 01566 | 7.6 | Solar | 05_05_18J7 | 01/20/2016 | 01/20/2016 | 3 | 3 | 0 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 1/25/2017 | N | EXP | 337 |  |  | 0 | 0 | 0 | 7/13/2016 | 7/13/2016 | 7/18/2016 | Connected |  | N
National Grid | WINCHENDON | 203267 | 01475 | 105 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 644021 | 02726 | 23 | Solar | 05_12_37W10 | 10/01/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 10/01/2024 | 3/21/2026 | Y | EXP | 365 | 06/27/2025 | 09/08/2025 | 74 | 0 | 74 |  |  | 10/21/2025 | Connected |  | N
National Grid | WESTBOROUGH | 178293 | 01581 | 160 | Solar | 05_14_1J2 | 11/14/2017 | 11/14/2017 | 35 | 26 | 9 | 01/08/2018 | 01/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2018 |  | 12/23/2019 | N | EXP | 713 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 586272 | 02149 | 3.19 | Solar | 05_14_48L4 | 02/07/2024 | 02/12/2024 | 3 | 0 | 3 | 02/13/2024 | 02/13/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 | 02/07/2024 | 3/15/2025 | Y | EXP | 365 | 06/06/2024 | 11/02/2024 | 150 | 0 | 150 |  |  | 11/16/2024 | Connected |  | N
National Grid | LAWRENCE | 175873 | 01843 | 16 | Solar | 05_14_63L1 | 03/09/2015 | 03/09/2015 | 11 | 9 | 2 | 03/26/2015 | 03/26/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 8/10/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 | 7/21/2015 | 7/21/2015 | 12/9/2015 | Connected |  | N
National Grid | HAVERHILL | 177251 | 01832 | 6 | Solar | 05_14_75L6 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/17/2016 | 06/17/2016 | 241 | 0 | 241 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/20/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 532056 | 01844 | 15 | Solar | 05_01_225W1 | 06/07/2023 | 06/27/2023 | 13 | 12 | 1 | 06/28/2023 | 06/28/2023 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 12/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2024 | Connected |  | N
National Grid | METHUEN | 505155 | 01844 | 7.6 | Solar | 05_01_304W4 | 03/09/2023 | 03/20/2023 | 7 | 0 | 7 | 03/21/2023 | 03/21/2023 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2023 | 03/09/2023 | 7/28/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2024 | Connected |  | N
National Grid | BOLTON | 466862 | 01740 | 20 | Solar | 05_01_415L1 | 10/10/2022 | 11/03/2022 | 18 | 17 | 1 | 11/04/2022 | 11/04/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 |  | 9/2/2024 | N | EXP | 550 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 178601 | 01536 | 4998 | Solar | 05_01_612W3 | 04/06/2018 | 04/06/2018 | 22 | 9 | 13 |  |  | 1969 | 0 | 1969 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 178512 | 01566 | 16.6 | Solar | 05_05_18J7 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 | 03/12/2018 | 03/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2018 |  | 3/13/2019 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 203266 | 01475 | 60 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 652275 | 02726 | 3.8 | Solar | 05_12_37W10 | 11/05/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | WESTBOROUGH | 504462 | 01581 | 0 | Other | 05_14_1J2 | 09/13/2023 | 11/07/2023 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2023 | 12/09/2023 | 21 | 2 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 626731 | 02149 | 9.86 | Solar | 05_14_48L4 | 07/22/2024 | 07/31/2024 | 5 | 3 | 2 | 08/01/2024 | 08/01/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/22/2024 | 8/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2024 | Connected |  | N
National Grid | LAWRENCE | 176711 | 01843 | 6 | Solar | 05_14_63L1 | 01/07/2016 | 01/07/2016 | 10 | 10 | 0 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 1/13/2017 | N | EXP | 339 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 5/9/2016 | Connected |  | N
National Grid | HAVERHILL | 177396 | 01832 | 6 | Solar | 05_14_75L6 | 02/21/2017 | 02/21/2017 | 6 | 1 | 5 | 03/01/2017 | 03/01/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2017 | 02/21/2017 | 2/26/2018 | Y | EXP | 360 | 10/16/2017 | 10/20/2017 | 4 | 0 | 4 | 6/27/2017 | 6/27/2017 | 11/2/2017 | Connected |  | N
National Grid | METHUEN | 535567 | 01844 | 15.12 | Solar | 05_01_225W1 | 06/30/2023 | 07/05/2023 | 2 | 0 | 2 | 07/06/2023 | 07/06/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  | 10/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2024 | Connected |  | N
National Grid | METHUEN | 529519 | 01844 | 12.6 | Solar | 05_01_304W4 | 05/26/2023 | 05/30/2023 | 1 | 0 | 1 | 05/31/2023 | 05/31/2023 | 35 | 13 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2024 | Connected |  | N
National Grid | BOLTON | 484990 | 01740 | 5.51 | Solar | 05_01_415L1 | 12/15/2022 | 12/26/2022 | 7 | 1 | 6 | 12/27/2022 | 12/27/2022 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 |  | 3/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/26/2023 | Connected |  | N
National Grid | GRAFTON | 178729 | 01536 | 3900 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 33 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 20 | 7 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 | 12/20/2017 | 1/24/2025 | Y | STD | 610 | 12/31/2021 | 05/03/2022 | 124 | 78 | 46 |  |  | 1/15/2025 | Connected |  | N
National Grid | CHARLTON | 221739 | 01507 | 0 | Solar | 05_05_18J7 | 04/23/2019 | 04/30/2019 | 4 | 0 | 4 | 05/01/2019 | 05/01/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2019 | Connected |  | N
National Grid | WINCHENDON | 203263 | 01475 | 90 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 661110 | 02726 | 15.2 | Solar | 05_12_37W10 | 12/19/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 651856 | 01581 | 3.8 | Solar | 05_14_1J4 | 11/04/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | MALDEN | 637124 | 02148 | 7.6 | Solar | 05_14_48L4 | 09/02/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 | 09/02/2024 | 10/29/2025 | Y | EXP | 365 | 06/27/2025 | 06/26/2025 | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | LAWRENCE | 176841 | 01843 | 10 | Solar | 05_14_63L1 | 05/02/2016 | 05/02/2016 | 3 | 3 | 0 | 05/05/2016 | 05/05/2016 | 449 | 0 | 449 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2016 | 05/02/2016 | 7/31/2018 | Y | EXP | 810 | 07/11/2017 | 07/28/2017 | 13 | 0 | 13 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 177646 | 01832 | 11.4 | Solar | 05_14_75L6 | 09/26/2017 | 09/26/2017 | 7 | 7 | 0 | 10/06/2017 | 10/06/2017 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 10/2/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 5/17/2018 | Connected |  | N
National Grid | METHUEN | 537573 | 01844 | 50 | Solar | 05_01_225W1 | 06/28/2023 | 01/07/2024 | 130 | 120 | 10 | 01/08/2024 | 01/08/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 6/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 570827 | 01844 | 23 | Solar | 05_01_304W4 | 11/13/2023 | 11/15/2023 | 2 | 0 | 2 | 11/16/2023 | 11/16/2023 | 74 | 50 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  | 4/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2024 | Connected |  | N
National Grid | BOLTON | 498882 | 01740 | 12.6 | Solar | 05_01_415L1 | 04/06/2023 | 04/26/2023 | 14 | 12 | 2 | 04/27/2023 | 04/27/2023 | 45 | 22 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 |  | 8/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N
National Grid | GRAFTON | 178728 | 01536 | 1000 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 07/26/2018 | 37 | 0 | 37 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 636152 | 01566 | 16.24 | Solar | 05_05_18J7 | 08/29/2024 | 09/05/2024 | 5 | 3 | 2 | 09/06/2024 | 09/06/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 203260 | 01475 | 60 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 667228 | 02726 | 15.2 | Solar | 05_12_37W10 | 02/07/2025 | 02/19/2025 | 7 | 3 | 4 | 02/20/2025 | 02/20/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 685230 | 01581 | 7.68 | Solar | 05_14_1J4 | 04/15/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 | 04/15/2025 | 8/22/2026 | Y | EXP | 365 | 10/30/2025 | 03/09/2026 | 131 | 0 | 131 |  |  | 3/11/2026 | Connected |  | Y
National Grid | MALDEN | 668948 | 02148 | 10.44 | Solar | 05_14_48L4 | 02/06/2025 | 02/12/2025 | 4 | 0 | 4 | 02/13/2025 | 02/13/2025 | 30 | 5 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 10/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | LAWRENCE | 177252 | 01843 | 6 | Solar | 05_14_63L1 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/17/2016 | 06/17/2016 | 157 | 0 | 157 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/20/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 177837 | 01832 | 15.2 | Solar | 05_14_75L6 | 08/09/2017 | 08/09/2017 | 5 | 5 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/14/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 2/15/2018 | 2/15/2018 | 2/15/2018 | Connected |  | N
National Grid | METHUEN | 569141 | 01844 | 7.6 | Solar | 05_01_225W1 | 11/14/2023 | 11/27/2023 | 2 | 0 | 2 | 11/28/2023 | 11/28/2023 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2024 | 11/14/2023 | 1/11/2025 | Y | EXP | 365 | 02/17/2024 | 03/19/2024 | 32 | 0 | 32 |  |  | 4/16/2024 | Connected |  | N
National Grid | DRACUT | 616690 | 01826 | 7.6 | Solar | 05_01_304W4 | 06/10/2024 | 06/17/2024 | 5 | 0 | 5 | 06/18/2024 | 06/18/2024 | 24 | 10 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | LANCASTER | 536279 | 01523 | 7.6 | Solar | 05_01_415L1 | 08/28/2023 | 08/30/2023 | 2 | 0 | 2 | 08/31/2023 | 08/31/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 178727 | 01536 | 1990 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 45 | 9 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 07/26/2018 | 37 | 0 | 37 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 676835 | 01566 | 22.272 | Solar | 05_05_18J7 | 03/10/2025 | 03/21/2025 | 10 | 6 | 4 | 03/24/2025 | 03/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | WINCHENDON | 222595 | 01475 | 432 | Solar | 05_05_314W3 | 04/25/2019 | 05/03/2019 | 6 | 5 | 1 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 | 04/25/2019 | 12/12/2024 | Y | STD | 274 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 724792 | 02726 | 15.2 | Solar | 05_12_37W10 | 10/07/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 641530 | 01581 | 11.52 | Solar | 05_14_1J6 | 09/19/2024 | 10/11/2024 | 4 | 0 | 4 | 10/15/2024 | 10/15/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 09/19/2024 | 4/16/2026 | Y | EXP | 365 | 07/08/2025 | 11/21/2025 | 137 | 0 | 137 |  |  | 11/26/2025 | Connected |  | N
National Grid | MALDEN | 725190 | 02148 | 10 | Solar | 05_14_50L1 | 10/08/2025 | 11/14/2025 | 4 | 0 | 4 | 11/17/2025 | 11/17/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 177425 | 01843 | 7.6 | Solar | 05_14_63L1 | 12/06/2016 | 12/06/2016 | 3 | 2 | 1 | 12/12/2016 | 12/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2016 | 12/06/2016 | 12/12/2017 | Y | EXP | 365 | 10/16/2017 | 11/16/2017 | 17 | 0 | 17 | 11/21/2017 | 11/21/2017 | 11/21/2017 | Connected |  | N
National Grid | HAVERHILL | 192225 | 01832 | 7.6 | Solar | 05_14_75L6 | 07/30/2018 | 09/19/2018 | 2 | 0 | 2 | 09/20/2018 | 09/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 574015 | 01844 | 0 | Battery Add-On | 05_01_225W1 | 11/28/2023 | 12/05/2023 | 6 | 5 | 1 | 12/06/2023 | 12/06/2023 | 78 | 62 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2024 | Connected |  | N
National Grid | METHUEN | 625716 | 01844 | 210 | Solar | 05_01_304W4 | 07/19/2024 | 09/06/2024 | 35 | 28 | 7 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 528584 | 01740 | 11.34 | Solar | 05_01_415L1 | 05/26/2023 | 06/01/2023 | 3 | 0 | 3 | 06/02/2023 | 06/02/2023 | 62 | 44 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 9/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | GRAFTON | 178726 | 01536 | 4990 | Solar | 05_01_612W3 | 12/20/2017 | 02/14/2018 | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/14/2018 | 03/12/2018 | 11 | 0 | 11 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 717271 | 01507 | 22.8 | Solar | 05_05_19W72 | 09/06/2025 | 09/09/2025 | 2 | 0 | 2 | 09/10/2025 | 09/10/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WINCHENDON | 452283 | 01475 | 100 | Solar | 05_05_314W3 | 09/01/2022 | 09/19/2022 | 11 | 2 | 9 | 09/20/2022 | 09/20/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 | 09/01/2022 | 4/15/2024 | Y | EXP | 119 | 09/15/2023 | 02/08/2024 | 146 | 145 | 1 |  |  | 4/9/2024 | Connected |  | N
National Grid | SOMERSET | 174415 | 02762 | 833 | Solar | 05_12_37W2 | 06/25/2012 | 06/25/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/05/2012 | 10/05/2012 | 65 | 0 | 65 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/5/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 661824 | 01581 | 7.6 | Solar | 05_14_1J7 | 12/19/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/19/2024 | 4/2/2026 | Y | EXP | 365 | 04/30/2025 | 10/07/2025 | 161 | 0 | 161 |  |  | 10/8/2025 | Connected |  | N
National Grid | MALDEN | 739126 | 02148 | 0 | Solar | 05_14_50L1 | 01/15/2026 | 01/21/2026 | 3 | 0 | 3 | 01/22/2026 | 01/22/2026 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 177824 | 01843 | 9.6 | Solar | 05_14_63L1 | 06/06/2017 | 06/06/2017 | 3 | 3 | 0 | 06/13/2017 | 06/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 | 06/06/2017 | 6/13/2018 | Y | EXP | 365 | 08/08/2017 | 08/16/2017 | 6 | 0 | 6 | 2/14/2018 | 2/14/2018 | 2/20/2018 | Connected |  | N
National Grid | ANDOVER | 447195 | 01810 | 10 | Solar | 05_14_75L6 | 08/02/2022 | 08/03/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 582536 | 01844 | 24.375 | Solar | 05_01_225W1 | 01/12/2024 | 01/17/2024 | 3 | 1 | 2 | 01/18/2024 | 01/18/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 2/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2024 | Connected |  | N
National Grid | METHUEN | 643375 | 01844 | 7.6 | Solar | 05_01_304W4 | 09/27/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/27/2024 | 1/30/2026 | Y | EXP | 365 | 02/26/2025 | 08/21/2025 | 176 | 49 | 127 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 572984 | 01740 | 7.6 | Solar | 05_01_415L1 | 11/21/2023 | 11/30/2023 | 10 | 8 | 2 | 07/08/2024 | 07/08/2024 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 | 11/21/2023 | 8/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | MILLBURY | 178725 | 01527 | 1000 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 735330 | 01566 | 5.76 | Solar | 05_05_19W72 | 02/03/2026 | 02/11/2026 | 6 | 4 | 2 | 02/12/2026 | 02/12/2026 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WINCHENDON | 648892 | 01475 | 10 | Solar | 05_05_314W3 | 11/01/2024 | 01/08/2025 | 38 | 34 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | SOMERSET | 174795 | 02726 | 50 | Solar | 05_12_37W2 | 10/02/2009 | 10/02/2009 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2009 |  | 12/31/2012 | N | EXP | 1111 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 681430 | 01581 | 10 | Solar | 05_14_1J7 | 04/01/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 176001 | 02155 | 20 | Solar | 05_14_50L1 | 06/15/2015 | 06/15/2015 | 16 | 16 | 0 | 07/10/2015 | 07/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2015 |  | 6/21/2016 | N | EXP | 344 |  |  | 0 | 0 | 0 | 9/23/2015 | 9/23/2015 | 9/29/2015 | Connected |  | N
National Grid | LAWRENCE | 178126 | 01843 | 7.6 | Solar | 05_14_63L1 | 07/11/2017 | 07/11/2017 | 3 | 3 | 0 | 07/17/2017 | 07/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2017 |  | 7/17/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/18/2017 | 10/18/2017 | 10/18/2017 | Connected |  | N
National Grid | ANDOVER | 457130 | 01810 | 0 | Other | 05_14_75L6 | 11/15/2022 | 02/08/2023 | 57 | 47 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2023 | 03/29/2023 | 34 | 14 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 601438 | 01844 | 0 | Solar | 05_01_225W1 | 04/03/2024 | 05/02/2024 | 21 | 19 | 2 | 05/03/2024 | 05/03/2024 | 91 | 88 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | DRACUT | 667645 | 01826 | 3.8 | Solar | 05_01_304W4 | 01/24/2025 | 02/05/2025 | 4 | 0 | 4 | 02/06/2025 | 02/06/2025 | 22 | 0 | 22 | 03/11/2025 | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 575137 | 01451 | 6 | Solar | 05_01_415L1 | 12/28/2023 | 01/02/2024 | 2 | 0 | 2 | 01/03/2024 | 01/03/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2024 | 12/28/2023 | 1/31/2025 | Y | EXP | 365 | 06/05/2024 | 07/17/2024 | 43 | 0 | 43 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 178724 | 01527 | 1990 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 740920 | 01507 | 7.6 | Solar | 05_05_19W72 | 12/19/2025 | 12/22/2025 | 1 | 0 | 1 | 12/23/2025 | 12/23/2025 | 56 | 35 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2026 |  | 3/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WINCHENDON | 654182 | 01475 | 5.76 | Solar | 05_05_314W3 | 11/18/2024 | 12/20/2024 | 3 | 0 | 3 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/18/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 177293 | 02726 | 64 | Solar | 05_12_37W2 | 08/25/2016 | 08/25/2016 | 1 | 0 | 1 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2016 |  | 8/31/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 11/15/2017 | 11/15/2017 | 11/15/2017 | Connected |  | N
National Grid | WESTBOROUGH | 746934 | 01581 | 11.4 | Solar | 05_14_1J7 | 01/22/2026 | 02/05/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2026 |  | 3/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2026 | Connected |  | N
National Grid | MEDFORD | 178145 | 02155 | 10 | Solar | 05_14_50L1 | 04/12/2018 | 04/12/2018 | 374 | 34 | 340 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 188740 | 01843 | 7.6 | Solar | 05_14_63L1 | 07/10/2018 | 09/04/2018 | 39 | 33 | 6 | 12/17/2018 | 12/17/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 07/10/2018 | 2/18/2020 | Y | EXP | 365 | 05/21/2019 | 07/12/2019 | 52 | 0 | 52 |  |  | 1/10/2020 | Connected |  | N
National Grid | ANDOVER | 512343 | 01810 | 5.76 | Solar | 05_14_75L6 | 03/17/2023 | 07/23/2024 | 5 | 3 | 2 | 07/24/2024 | 07/24/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 |  | 8/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | METHUEN | 612134 | 01844 | 50 | Solar | 05_01_225W1 | 05/20/2024 | 05/21/2024 | 1 | 0 | 1 | 05/22/2024 | 05/22/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2024 |  | 7/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2024 | Connected |  | N
National Grid | DRACUT | 670474 | 01826 | 4999.2 | Solar | 05_01_304W5 | 03/20/2025 | 05/12/2025 | 37 | 27 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | HARVARD | 606685 | 01451 | 10 | Solar | 05_01_415L1 | 04/25/2024 | 05/01/2024 | 2 | 0 | 2 | 05/02/2024 | 05/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 178723 | 01527 | 4990 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  | 0 | 0 | 0 | 07/10/2020 | 10/01/2020 | 59 | 3 | 56 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 757054 | 01507 | 18.497 | Solar | 05_05_19W72 | 03/17/2026 | 03/23/2026 | 4 | 0 | 4 | 03/24/2026 | 03/24/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WINCHENDON | 597738 | 01475 | 120 | Solar | 05_05_314W4 | 04/18/2024 | 05/03/2024 | 12 | 3 | 9 |  |  | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SOMERSET | 177365 | 02726 | 390 | Solar | 05_12_37W2 | 06/24/2016 | 06/24/2016 | 0 | 0 | 0 | 06/27/2016 | 06/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2016 | 06/24/2016 | 7/2/2017 | Y | EXP | 290 | 12/12/2016 | 01/28/2017 | 32 | 0 | 32 | 3/10/2017 | 3/10/2017 | 3/9/2017 | Connected |  | N
National Grid | WESTBOROUGH | 177026 | 01581 | 23 | Solar | 05_14_1J8 | 08/05/2016 | 08/05/2016 | 1 | 0 | 1 | 08/17/2016 | 08/17/2016 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 |  | 6/29/2018 | N | EXP | 669 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 203934 | 02155 | 0 | Battery Add-On | 05_14_50L1 | 12/19/2018 | 12/31/2018 | 6 | 0 | 6 | 01/02/2019 | 01/02/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2019 | Connected |  | N
National Grid | LAWRENCE | 194880 | 01843 | 3.8 | Solar | 05_14_63L1 | 08/31/2018 | 10/30/2018 | 7 | 0 | 7 | 10/31/2018 | 10/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 524863 | 01810 | 7.68 | Solar | 05_14_75L6 | 05/22/2023 | 05/23/2023 | 1 | 0 | 1 | 05/24/2023 | 05/24/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 |  | 8/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2023 | Connected |  | Y
National Grid | METHUEN | 631386 | 01844 | 0 | Battery Add-On | 05_01_225W1 | 08/09/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 08/09/2024 | 10/13/2025 | Y | EXP | 405 | 01/07/2025 | 12/22/2025 | 350 | 0 | 350 |  |  | 11/21/2025 | Connected |  | N
National Grid | METHUEN | 686006 | 01844 | 3.8 | Solar | 05_01_304W5 | 04/17/2025 | 04/25/2025 | 5 | 0 | 5 | 04/28/2025 | 04/28/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 612835 | 01523 | 9.86 | Solar | 05_01_415L1 | 05/22/2024 | 06/03/2024 | 6 | 5 | 1 | 06/04/2024 | 06/04/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 |  | 6/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2024 | Connected |  | N
National Grid | MILLBURY | 178722 | 01527 | 1000 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 174604 | 01566 | 42 | Solar | 05_05_19W72 | 08/24/2011 | 08/24/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2011 |  | 3/2/2012 | N | EXP | 66 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 6/27/2012 | Connected |  | N
National Grid | WINCHENDON | 597594 | 01475 | 120 | Solar | 05_05_314W4 | 03/18/2024 | 04/22/2024 | 24 | 16 | 8 |  |  | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SOMERSET | 252582 | 02726 | 200 | Solar | 05_12_37W2 | 09/06/2019 | 09/10/2019 | 0 | 0 | 0 | 09/11/2019 | 09/11/2019 | 88 | 26 | 62 | 10/30/2019 | 01/21/2020 | 57 | 25 | 32 |  |  | 0 | 0 | 0 | 01/21/2020 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 177189 | 01581 | 23 | Solar | 05_14_1J8 | 08/15/2016 | 08/15/2016 | 1 | 1 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 |  | 12/21/2017 | N | EXP | 479 |  |  | 0 | 0 | 0 | 11/29/2017 | 11/29/2017 | 11/29/2017 | Connected |  | N
National Grid | MEDFORD | 213038 | 02155 | 10 | Solar | 05_14_50L1 | 03/08/2019 | 03/11/2019 | 5 | 0 | 5 | 04/08/2019 | 04/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 3/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2019 | Connected |  | N
National Grid | LAWRENCE | 198050 | 01843 | 5 | Solar | 05_14_63L1 | 10/09/2018 | 10/22/2018 | 7 | 6 | 1 | 10/23/2018 | 10/23/2018 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 | 10/09/2018 | 5/22/2019 | Y | EXP | 198 | 01/29/2019 | 02/05/2019 | 7 | 0 | 7 |  |  | 3/15/2019 | Connected |  | N
National Grid | ANDOVER | 558735 | 01810 | 350 | Solar | 05_14_75L6 | 12/04/2023 | 01/04/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2024 | 01/31/2024 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 635160 | 01844 | 9.88 | Solar | 05_01_225W1 | 08/26/2024 | 09/09/2024 | 3 | 0 | 3 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/26/2024 | 10/6/2025 | Y | EXP | 365 | 11/07/2024 | 11/19/2024 | 13 | 0 | 13 |  |  | 2/13/2025 | Connected |  | N
National Grid | METHUEN | 755047 | 01844 | 0 | Battery Add-On | 05_01_304W5 | 03/06/2026 | 03/10/2026 | 2 | 0 | 2 | 03/11/2026 | 03/11/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BOLTON | 622514 | 01740 | 3.8 | Solar | 05_01_415L1 | 07/03/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/03/2024 | 8/28/2025 | Y | EXP | 365 | 09/19/2024 | 05/28/2025 | 252 | 0 | 252 |  |  | 8/22/2025 | Connected |  | N
National Grid | MILLBURY | 178721 | 01527 | 1990 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/14/2018 | 03/12/2018 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 175180 | 01566 | 3130 | Solar | 05_05_19W72 | 05/06/2013 | 05/06/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2013 | 06/24/2013 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2014 | 05/06/2013 | 7/7/2017 | Y | STD | 990 | 03/17/2017 | 06/30/2017 | 73 | 0 | 73 | 6/29/2017 | 6/29/2017 | 7/13/2017 | Connected |  | N
National Grid | WINCHENDON | 702409 | 01475 | 5.76 | Solar | 05_05_314W4 | 07/02/2025 | 10/14/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 1/29/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DIGHTON | 384625 | 02715 | 298.8 | Solar | 05_12_37W2 | 08/11/2022 | 11/08/2022 | 61 | 51 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2022 | 09/21/2023 | 216 | 197 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 198686 | 01581 | 7.6 | Solar | 05_14_1J9 | 10/16/2018 |  | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 227099 | 02155 | 0 | Solar | 05_14_50L1 | 05/13/2019 | 05/14/2019 | 0 | 0 | 0 | 05/15/2019 | 05/15/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2019 | Connected |  | N
National Grid | LAWRENCE | 204929 | 01843 | 7.6 | Solar | 05_14_63L1 | 02/06/2019 | 02/28/2019 | 14 | 7 | 7 | 03/01/2019 | 03/01/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 |  | 3/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2019 | Connected |  | N
National Grid | ANDOVER | 597814 | 01810 | 14.3 | Solar | 05_14_75L6 | 03/28/2024 | 04/02/2024 | 4 | 2 | 2 | 04/03/2024 | 04/03/2024 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 03/28/2024 | 8/11/2025 | Y | EXP | 365 | 02/15/2025 | 03/14/2025 | 28 | 0 | 28 |  |  | 4/4/2025 | Connected |  | N
National Grid | METHUEN | 641650 | 01844 | 7.6 | Solar | 05_01_225W1 | 11/13/2024 | 12/05/2024 | 9 | 5 | 4 | 12/06/2024 | 12/06/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2025 | Connected |  | N
National Grid | METHUEN | 758301 | 01844 | 20 | Solar | 05_01_304W5 | 03/23/2026 | 04/01/2026 | 6 | 4 | 2 | 04/02/2026 | 04/02/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LANCASTER | 625725 | 01523 | 7.6 | Solar | 05_01_415L1 | 07/17/2024 | 08/14/2024 | 3 | 0 | 3 | 08/15/2024 | 08/15/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 10/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | SUTTON | 184650 | 01590 | 990 | Solar | 05_01_612W3 | 05/11/2018 | 05/11/2018 | 1 | 0 | 1 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 06/05/2018 | 06/14/2018 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 175398 | 01566 | 475 | Solar | 05_05_19W72 | 11/17/2014 | 11/17/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2014 | 12/29/2014 | 23 | 4 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 12/31/2016 | N | STD | 520 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 756831 | 01475 | 11.52 | Solar | 05_05_314W4 | 03/16/2026 | 03/19/2026 | 3 | 0 | 3 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DIGHTON | 648827 | 02715 | 4.35 | Solar | 05_12_37W2 | 10/22/2024 | 11/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 200094 | 01532 | 10 | Solar | 05_14_1J9 | 11/02/2018 | 12/03/2018 | 9 | 2 | 7 | 12/04/2018 | 12/04/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 326510 | 02155 | 10 | Solar | 05_14_50L1 | 11/17/2020 | 12/03/2020 | 10 | 8 | 2 | 12/04/2020 | 12/04/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/18/2021 | Connected |  | N
National Grid | LAWRENCE | 205072 | 01843 | 5 | Solar | 05_14_63L1 | 02/07/2019 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 618488 | 01810 | 7.6 | Solar | 05_14_75L6 | 06/28/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 8/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | METHUEN | 644960 | 01844 | 8.12 | Solar | 05_01_225W1 | 10/03/2024 | 11/13/2024 | 4 | 1 | 3 | 11/14/2024 | 11/14/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2025 | Connected |  | N
National Grid | METHUEN | 174666 | 01844 | 19.99 | Solar | 05_01_304W5 | 12/18/2012 | 12/18/2012 | 8 | 0 | 8 | 01/02/2013 | 01/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2013 |  | 3/8/2013 | N | EXP | 10 |  |  | 0 | 0 | 0 | 5/22/2013 | 5/22/2013 | 6/11/2013 | Connected |  | N
National Grid | LANCASTER | 645265 | 01523 | 10 | Solar | 05_01_415L1 | 10/07/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 12/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | SUTTON | 192506 | 01590 | 6.4 | Solar | 05_01_612W3 | 09/17/2018 | 12/14/2018 | 11 | 11 | 0 | 11/05/2018 | 11/05/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  | 11/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2019 | Connected |  | N
National Grid | STURBRIDGE | 175613 | 01566 | 258 | Solar | 05_05_19W72 | 12/16/2014 | 12/16/2014 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 174880 | 01475 | 250.8 | Solar | 05_05_314W4 | 02/14/2013 | 02/14/2013 | 7 | 2 | 5 | 02/27/2013 | 02/27/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2013 | 02/14/2013 | 10/1/2013 | Y | EXP | 7 | 11/19/2013 | 03/15/2014 | 79 | 0 | 79 | 11/20/2014 | 11/20/2014 | 12/2/2014 | Connected |  | N
National Grid | DIGHTON | 742314 | 02715 | 11.5 | Battery Add-On | 05_12_37W3 | 12/26/2025 | 01/05/2026 | 5 | 0 | 5 | 01/06/2026 | 01/06/2026 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 202595 | 01532 | 7.6 | Solar | 05_14_1J9 | 02/07/2019 | 02/13/2019 | 4 | 4 | 0 | 02/14/2019 | 02/14/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/07/2019 | 5/28/2020 | Y | EXP | 365 | 01/16/2020 | 02/07/2020 | 22 | 0 | 22 |  |  | 2/11/2020 | Connected |  | N
National Grid | MEDFORD | 424059 | 02155 | 9.772 | Solar | 05_14_50L1 | 04/24/2022 | 05/05/2022 | 10 | 9 | 1 | 05/06/2022 | 05/06/2022 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2022 | 04/24/2022 | 8/11/2023 | Y | EXP | 365 | 07/07/2022 | 08/11/2022 | 36 | 0 | 36 |  |  | 10/21/2022 | Connected |  | N
National Grid | LAWRENCE | 211661 | 01843 | 5 | Solar | 05_14_63L1 | 03/05/2019 | 03/06/2019 | 0 | 0 | 0 | 03/07/2019 | 03/07/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 634167 | 01810 | 7.6 | Solar | 05_14_75L6 | 08/20/2024 | 09/03/2024 | 3 | 0 | 3 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 9/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2024 | Connected |  | N
National Grid | METHUEN | 646978 | 01844 | 10 | Solar | 05_01_225W1 | 10/29/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | METHUEN | 174701 | 01844 | 11.5 | Solar | 05_01_304W5 | 01/04/2013 | 01/04/2013 | 8 | 0 | 8 | 01/17/2013 | 01/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2013 |  | 4/30/2013 | N | EXP | 53 |  |  | 0 | 0 | 0 | 6/3/2013 | 6/3/2013 | 6/6/2013 | Connected |  | N
National Grid | BOLTON | 657791 | 01740 | 11.5 | Solar | 05_01_415L1 | 12/02/2024 | 12/17/2024 | 3 | 0 | 3 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/02/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | MILLBURY | 256917 | 01527 | 7.6 | Solar | 05_01_612W3 | 09/27/2019 | 10/01/2019 | 1 | 0 | 1 | 10/02/2019 | 10/02/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2019 | Connected |  | N
National Grid | STURBRIDGE | 175855 | 01566 | 10 | Solar | 05_05_19W72 | 08/03/2015 | 08/03/2015 | 4 | 4 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 |  | 8/9/2016 | N | EXP | 343 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 2/18/2016 | Connected |  | N
National Grid | WINCHENDON | 176836 | 01475 | 3.75 | Solar | 05_05_314W4 | 02/29/2016 | 02/29/2016 | 5 | 5 | 0 | 03/08/2016 | 03/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2016 |  | 3/6/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 5/10/2016 | 5/10/2016 | 5/12/2016 | Connected |  | N
National Grid | SOMERSET | 178470 | 02726 | 60 | Solar | 05_12_37W3 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/13/2018 | 03/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 |  |  | N | EXP | 692 |  |  | 0 | 0 | 0 |  |  | 8/14/2020 | Connected |  | N
National Grid | WESTBOROUGH | 208645 | 01581 | 10 | Solar | 05_14_1J9 | 02/13/2019 | 02/22/2019 | 5 | 0 | 5 | 02/25/2019 | 02/25/2019 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 431159 | 02155 | 15.2 | Solar | 05_14_50L1 | 05/18/2022 | 05/19/2022 | 1 | 0 | 1 | 05/20/2022 | 05/20/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 6/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/11/2023 | Connected |  | Y
National Grid | LAWRENCE | 219723 | 01843 | 5 | Solar | 05_14_63L1 | 05/01/2019 | 05/01/2019 | 0 | 0 | 0 | 05/02/2019 | 05/02/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2019 | 05/01/2019 | 1/21/2020 | Y | EXP | 263 | 07/16/2019 | 08/12/2019 | 27 | 0 | 27 |  |  | 10/8/2019 | Connected |  | N
National Grid | ANDOVER | 637971 | 01810 | 7.6 | Solar | 05_14_75L6 | 09/09/2024 | 09/30/2024 | 6 | 5 | 1 | 10/01/2024 | 10/01/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 648121 | 01844 | 9.88 | Solar | 05_01_225W1 | 10/18/2024 | 11/06/2024 | 13 | 10 | 3 | 11/07/2024 | 11/07/2024 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | DRACUT | 174906 | 01826 | 15 | Solar | 05_01_304W5 | 09/14/2012 | 09/14/2012 | 7 | 4 | 3 | 09/26/2012 | 09/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/15/2012 | N | EXP | 27 |  |  | 0 | 0 | 0 | 2/8/2013 | 2/8/2013 | 3/2/2013 | Connected |  | N
National Grid | BOLTON | 658052 | 01740 | 20 | Solar | 05_01_415L1 | 12/04/2024 | 12/17/2024 | 9 | 5 | 4 | 12/18/2024 | 12/18/2024 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | MILLBURY | 581103 | 01527 | 7.6 | Solar | 05_01_612W3 | 01/25/2024 | 01/29/2024 | 3 | 1 | 2 | 01/30/2024 | 01/30/2024 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/25/2024 | 3/19/2025 | Y | EXP | 365 | 05/21/2024 | 05/20/2024 | 0 | 0 | 0 |  |  | 6/10/2024 | Connected |  | N
National Grid | CHARLTON | 175893 | 01507 | 7.6 | Solar | 05_05_19W72 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2015 |  | 8/10/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 8/31/2015 | 8/31/2015 | 1/28/2016 | Connected |  | N
National Grid | WINCHENDON | 176928 | 01475 | 32.4 | Solar | 05_05_314W4 | 11/20/2015 | 11/20/2015 | 16 | 16 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2015 |  | 11/25/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 | 1/3/2017 | 1/3/2017 | 1/11/2017 | Connected |  | N
National Grid | SOMERSET | 599355 | 02726 | 50 | Solar | 05_12_37W3 | 04/26/2024 | 05/17/2024 | 16 | 8 | 8 | 05/20/2024 | 05/20/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 301209 | 01532 | 10 | Solar | 05_14_1J9 | 02/03/2021 | 02/08/2021 | 2 | 0 | 2 | 02/09/2021 | 02/09/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2021 | 02/03/2021 | 3/29/2022 | Y | EXP | 365 | 09/02/2021 | 01/27/2022 | 148 | 4 | 144 |  |  | 1/31/2022 | Connected |  | Y
National Grid | MEDFORD | 433986 | 02155 | 19 | Solar | 05_14_50L1 | 05/27/2022 | 06/24/2022 | 19 | 18 | 1 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2023 | Connected |  | Y
National Grid | LAWRENCE | 216261 | 01843 | 10 | Solar | 05_14_63L1 | 06/10/2019 | 06/21/2019 | 8 | 2 | 6 | 06/24/2019 | 06/24/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 | 06/10/2019 | 9/16/2020 | Y | EXP | 365 | 05/27/2020 | 06/01/2020 | 5 | 0 | 5 |  |  | 7/2/2020 | Connected |  | N
National Grid | ANDOVER | 645604 | 01810 | 11.4 | Solar | 05_14_75L6 | 10/08/2024 |  | 13 | 8 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 650897 | 01844 | 11.5 | Solar | 05_01_225W1 | 10/30/2024 | 12/02/2024 | 13 | 10 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | METHUEN | 175169 | 01844 | 20 | Solar | 05_01_304W5 | 11/14/2012 | 11/14/2012 | 7 | 1 | 6 | 11/29/2012 | 11/29/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2013 |  | 1/31/2013 | N | EXP | 13 |  |  | 0 | 0 | 0 | 2/13/2013 | 2/13/2013 | 4/12/2013 | Connected |  | N
National Grid | BOLTON | 662122 | 01740 | 3.8 | Solar | 05_01_415L1 | 12/21/2024 | 01/16/2025 | 3 | 0 | 3 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 657817 | 01590 | 5.76 | Solar | 05_01_612W3 | 12/02/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 3/5/2026 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 175974 | 01566 | 258 | Solar | 05_05_19W72 | 01/20/2015 | 01/20/2015 | 3 | 0 | 3 | 01/28/2015 | 01/28/2015 | 345 | 0 | 345 | 03/11/2015 | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 4/17/2015 |  | 12/31/2016 | N | EXP | 624 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 176933 | 01475 | 72 | Solar | 05_05_314W4 | 01/28/2016 | 01/28/2016 | 4 | 4 | 0 | 02/03/2016 | 02/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 2/2/2017 | N | EXP | 345 |  |  | 0 | 0 | 0 | 11/7/2016 | 11/7/2016 | 8/12/2016 | Connected |  | N
National Grid | SOMERSET | 662041 | 02726 | 11.5 | Solar | 05_12_37W3 | 12/27/2024 | 01/02/2025 | 3 | 0 | 3 | 01/03/2025 | 01/03/2025 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | WESTBOROUGH | 347908 | 01581 | 7.6 | Solar | 05_14_1J9 | 04/06/2021 | 04/14/2021 | 5 | 0 | 5 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2021 | Connected |  | N
National Grid | MALDEN | 485562 | 02148 | 15.2 | Solar | 05_14_50L1 | 01/20/2023 | 01/27/2023 | 5 | 5 | 0 | 01/30/2023 | 01/30/2023 | 136 | 25 | 111 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 228343 | 01843 | 10 | Solar | 05_14_63L1 | 07/08/2019 | 07/17/2019 | 6 | 6 | 0 | 07/18/2019 | 07/18/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 652506 | 01810 | 12.18 | Solar | 05_14_75L6 | 11/14/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | METHUEN | 651005 | 01844 | 7.6 | Solar | 05_01_225W1 | 11/12/2024 | 12/27/2024 | 24 | 20 | 4 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 | 02/27/2025 | 03/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 03/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | METHUEN | 175160 | 01844 | 3000 | Solar | 05_01_304W5 | 08/04/2011 | 08/04/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2011 | 02/24/2012 | 102 | 0 | 102 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 08/04/2011 | 12/31/2012 | Y | STD | 73 | 11/13/2013 | 03/12/2014 | 80 | 0 | 80 | 2/28/2014 | 2/28/2014 | 3/6/2014 | Connected |  | N
National Grid | HARVARD | 674999 | 01451 | 20 | Solar | 05_01_415L1 | 03/04/2025 | 03/20/2025 | 13 | 8 | 5 | 03/21/2025 | 03/21/2025 | 36 | 15 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 03/04/2025 | 5/27/2026 | Y | EXP | 365 | 09/30/2025 | 10/08/2025 | 9 | 0 | 9 |  |  | 12/9/2025 | Connected |  | N
National Grid | SUTTON | 663132 | 01590 | 7.25 | Solar | 05_01_612W3 | 12/31/2024 | 01/08/2025 | 4 | 2 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/31/2024 | 3/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | STURBRIDGE | 176485 | 01566 | 6 | Solar | 05_05_19W72 | 05/23/2016 | 05/23/2016 | 1 | 1 | 0 | 05/26/2016 | 05/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/23/2016 | 5/30/2017 | Y | EXP | 358 | 10/03/2016 | 10/13/2016 | 7 | 0 | 7 | 2/16/2017 | 2/16/2017 | 2/16/2017 | Connected |  | N
National Grid | WINCHENDON | 177970 | 01475 | 414 | Solar | 05_05_314W4 | 04/25/2017 | 04/25/2017 | 28 | 26 | 2 | 06/06/2017 | 06/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2017 | 04/25/2017 | 5/1/2017 | Y | EXP | 73 | 09/22/2017 | 10/13/2017 | 14 | 0 | 14 | 11/27/2017 | 11/27/2017 | 11/27/2017 | Connected |  | N
National Grid | SOMERSET | 676058 | 02726 | 45.6 | Solar | 05_12_37W4 | 04/03/2025 | 04/25/2025 | 15 | 11 | 4 | 04/28/2025 | 04/28/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTBOROUGH | 644454 | 01581 | 2.32 | Solar | 05_14_1J9 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 41 | 22 | 19 | 01/09/2025 | 01/27/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 01/27/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 503342 | 02155 | 18.85 | Solar | 05_14_50L1 | 02/22/2023 | 02/23/2023 | 1 | 0 | 1 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2023 | Connected |  | N
National Grid | LAWRENCE | 239280 | 01843 | 7.6 | Solar | 05_14_63L1 | 06/27/2019 | 07/01/2019 | 2 | 2 | 0 | 07/02/2019 | 07/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 | 06/27/2019 | 4/22/2020 | Y | EXP | 287 | 01/03/2020 | 01/02/2020 | 0 | 0 | 0 |  |  | 1/10/2020 | Connected |  | N
National Grid | ANDOVER | 654316 | 01810 | 8.91 | Solar | 05_14_75L6 | 11/14/2024 | 12/17/2024 | 10 | 6 | 4 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/14/2024 | 2/19/2026 | Y | EXP | 365 | 04/16/2025 |  | 351 | 0 | 351 |  |  | 3/28/2025 | Connected |  | N
National Grid | LAWRENCE | 655903 | 01841 | 15 | Solar | 05_01_225W1 | 11/21/2024 | 12/02/2024 | 3 | 1 | 2 | 12/03/2024 | 12/03/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | METHUEN | 175680 | 01844 | 97.5 | Solar | 05_01_304W5 | 12/19/2014 | 12/19/2014 | 5 | 0 | 5 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2015 | 12/19/2014 | 12/31/2016 | Y | EXP | 719 | 12/10/2015 | 01/19/2016 | 25 | 0 | 25 | 4/1/2015 | 4/1/2015 | 4/8/2016 | Connected |  | N
National Grid | BOLTON | 675967 | 01740 | 15.2 | Solar | 05_01_415L1 | 03/05/2025 | 03/12/2025 | 5 | 1 | 4 | 03/13/2025 | 03/13/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | MILLBURY | 690406 | 01527 | 7.6 | Solar | 05_01_612W3 | 05/07/2025 | 06/05/2025 | 4 | 0 | 4 | 06/25/2025 | 06/25/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 176479 | 01507 | 288 | Solar | 05_05_19W72 | 05/19/2016 | 05/19/2016 | 20 | 20 | 0 | 06/24/2016 | 06/24/2016 | 0 | 0 | 0 | 08/16/2016 | 09/16/2016 | 22 | 7 | 15 |  |  | 0 | 0 | 0 | 09/16/2016 | 22 | 7 | 15 |  |  | 0 | 0 | 0 | 3/3/2017 |  | 7/15/2017 | N | EXP | 134 |  |  | 0 | 0 | 0 | 6/28/2017 | 6/28/2017 | 8/3/2017 | Connected |  | N
National Grid | WINCHENDON | 194780 | 01475 | 7.6 | Solar | 05_05_314W4 | 11/27/2018 | 12/05/2018 | 6 | 0 | 6 | 12/06/2018 | 12/06/2018 | 160 | 0 | 160 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 748843 | 02726 | 5.76 | Solar | 05_12_37W4 | 02/02/2026 | 02/12/2026 | 7 | 4 | 3 | 02/13/2026 | 02/13/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2026 |  | 3/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 647960 | 01581 | 3 | Solar | 05_14_1J9 | 10/17/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/17/2024 | 1/6/2026 | Y | EXP | 365 | 04/15/2025 | 11/13/2025 | 213 | 0 | 213 |  |  | 11/17/2025 | Connected |  | N
National Grid | MEDFORD | 520199 | 02155 | 10 | Solar | 05_14_50L1 | 06/09/2023 | 06/12/2023 | 1 | 0 | 1 | 06/13/2023 | 06/13/2023 | 103 | 25 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 242735 | 01843 | 10 | Solar | 05_14_63L1 | 08/28/2019 | 08/29/2019 | 1 | 1 | 0 | 08/30/2019 | 08/30/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2019 | 08/28/2019 | 6/11/2020 | Y | EXP | 365 | 01/16/2020 | 02/20/2020 | 35 | 0 | 35 |  |  | 2/24/2020 | Connected |  | N
National Grid | ANDOVER | 654188 | 01810 | 7.6 | Solar | 05_14_75L6 | 11/18/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/18/2024 | 2/12/2026 | Y | EXP | 365 | 05/07/2025 | 07/10/2025 | 65 | 0 | 65 |  |  | 7/25/2025 | Connected |  | N
National Grid | METHUEN | 665152 | 01844 | 7.6 | Solar | 05_01_225W1 | 01/13/2025 | 02/04/2025 | 4 | 0 | 4 | 02/05/2025 | 02/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176351 | 01844 | 7 | Solar | 05_01_304W5 | 05/13/2015 | 05/13/2015 | 2 | 2 | 0 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2015 | 05/13/2015 | 12/31/2016 | Y | EXP | 575 | 03/17/2016 | 03/25/2016 | 5 | 0 | 5 | 5/10/2016 | 5/10/2016 | 5/12/2016 | Connected |  | N
National Grid | LANCASTER | 681472 | 01532 | 12.18 | Solar | 05_01_415L1 | 04/01/2025 | 04/15/2025 | 10 | 6 | 4 | 04/16/2025 | 04/16/2025 | 111 | 86 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2026 | Connected |  | N
National Grid | MILLBURY | 653327 | 01527 | 10 | Solar | 05_01_6J304 | 11/08/2024 | 11/27/2024 | 1 | 0 | 1 | 12/02/2024 | 12/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | Y
National Grid | CHARLTON | 176648 | 01507 | 7.6 | Solar | 05_05_19W72 | 02/17/2016 | 02/17/2016 | 2 | 2 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2016 | 02/17/2016 | 2/23/2017 | Y | EXP | 339 | 07/18/2016 | 07/26/2016 | 6 | 0 | 6 | 3/21/2016 | 3/21/2016 | 10/13/2016 | Connected |  | N
National Grid | WINCHENDON | 208290 | 01475 | 3 | Solar | 05_05_314W4 | 02/13/2019 | 02/25/2019 | 6 | 1 | 5 | 02/26/2019 | 02/26/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 3/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2019 | Connected |  | N
National Grid | SOMERSET | 175484 | 02726 | 75 | Natural Gas | 05_12_37W4 | 03/18/2014 | 03/18/2014 | 8 | 2 | 6 | 03/31/2014 | 03/31/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2014 |  | 9/30/2014 | N | EXP | 172 |  |  | 0 | 0 | 0 | 10/15/2014 | 10/15/2014 | 10/28/2014 | Connected |  | N
National Grid | WESTBOROUGH | 653186 | 01581 | 6.72 | Solar | 05_14_1J9 | 11/08/2024 | 12/03/2024 | 11 | 8 | 3 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2025 | Connected |  | N
National Grid | MEDFORD | 556272 | 02155 | 0 | Battery Add-On | 05_14_50L1 | 09/18/2023 | 10/10/2023 | 15 | 14 | 1 | 10/11/2023 | 10/11/2023 | 157 | 28 | 129 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 250742 | 01843 | 7.6 | Solar | 05_14_63L1 | 10/07/2019 | 10/11/2019 | 3 | 0 | 3 | 10/15/2019 | 10/15/2019 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 |  | 10/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2020 | Connected |  | N
National Grid | ANDOVER | 657523 | 01810 | 5.76 | Solar | 05_14_75L6 | 11/28/2024 | 12/17/2024 | 3 | 0 | 3 | 12/18/2024 | 12/18/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | METHUEN | 665518 | 01844 | 20 | Solar | 05_01_225W1 | 01/14/2025 | 01/16/2025 | 2 | 0 | 2 | 01/17/2025 | 01/17/2025 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | METHUEN | 176378 | 01844 | 16 | Solar | 05_01_304W5 | 11/20/2015 | 11/20/2015 | 1 | 1 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2015 |  | 11/28/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 3/2/2016 | 3/2/2016 | 3/9/2016 | Connected |  | N
National Grid | LANCASTER | 699606 | 01523 | 5.76 | Solar | 05_01_415L1 | 06/20/2025 | 07/07/2025 | 4 | 0 | 4 | 07/28/2025 | 07/28/2025 | 44 | 24 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2025 |  | 10/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 728152 | 01527 | 7.98 | Solar | 05_01_6J312 | 10/21/2025 | 10/26/2025 | 7 | 6 | 1 | 12/24/2025 | 12/24/2025 | 66 | 24 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STURBRIDGE | 176645 | 01566 | 5 | Solar | 05_05_19W72 | 02/17/2016 | 02/17/2016 | 3 | 3 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2016 | 02/17/2016 | 2/22/2017 | Y | EXP | 338 | 06/01/2016 | 06/10/2016 | 7 | 0 | 7 | 3/21/2016 | 3/21/2016 | 1/3/2017 | Connected |  | N
National Grid | WORCESTER | 246090 | 01603 | 0 | Solar | 05_05_314W4 | 07/30/2019 | 07/31/2019 | 0 | 0 | 0 | 08/01/2019 | 08/01/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2019 |  | 11/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 176729 | 02726 | 150 | Solar | 05_12_37W4 | 04/25/2016 | 04/25/2016 | 1 | 1 | 0 | 04/27/2016 | 04/27/2016 | 279 | 9 | 270 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 |  | 5/1/2017 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 547517 | 01581 | 360 | Solar | 05_14_211L1 | 09/22/2023 | 10/16/2023 | 15 | 6 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 | 11/13/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 | 09/22/2023 | 8/21/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | MALDEN | 528645 | 02148 | 9.86 | Solar | 05_14_50L1 | 05/23/2023 | 05/25/2023 | 2 | 0 | 2 | 05/26/2023 | 05/26/2023 | 65 | 45 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 9/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2023 | Connected |  | N
National Grid | LAWRENCE | 251517 | 01843 | 7.6 | Solar | 05_14_63L1 | 10/10/2019 | 10/15/2019 | 14 | 12 | 2 | 10/16/2019 | 10/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2019 |  | 10/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 661267 | 01810 | 2.32 | Solar | 05_14_75L6 | 12/17/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/17/2024 | 2/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 665398 | 01844 | 3.8 | Solar | 05_01_225W1 | 01/14/2025 | 02/10/2025 | 6 | 2 | 4 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | METHUEN | 176403 | 01844 | 3.8 | Solar | 05_01_304W5 | 03/11/2016 | 03/11/2016 | 3 | 3 | 0 | 03/17/2016 | 03/17/2016 | 234 | 0 | 234 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2016 |  | 3/19/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 716574 | 01523 | 21.4 | Solar | 05_01_415L1 | 09/10/2025 | 09/15/2025 | 3 | 0 | 3 | 09/16/2025 | 09/16/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N
National Grid | MILLBURY | 728147 | 01527 | 6.84 | Solar | 05_01_6J312 | 10/21/2025 | 10/26/2025 | 2 | 0 | 2 | 12/10/2025 | 12/10/2025 | 18 | 0 | 18 | 03/24/2026 |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | CHARLTON | 176684 | 01507 | 6 | Solar | 05_05_19W72 | 02/18/2016 | 02/18/2016 | 1 | 1 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2016 | 02/18/2016 | 2/24/2017 | Y | EXP | 340 | 07/18/2016 | 08/05/2016 | 14 | 0 | 14 | 12/29/2016 | 12/29/2016 | 1/4/2017 | Connected |  | N
National Grid | WORCESTER | 318365 | 01610 | 10 | Solar | 05_05_314W4 | 10/09/2020 | 10/12/2020 | 0 | 0 | 0 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 10/09/2020 | 4/30/2021 | Y | EXP | 365 | 01/28/2021 | 02/17/2021 | 20 | 0 | 20 |  |  | 3/4/2021 | Connected |  | N
National Grid | SOMERSET | 177838 | 02726 | 3.8 | Solar | 05_12_37W4 | 10/13/2017 | 10/13/2017 | 11 | 10 | 1 | 10/31/2017 | 10/31/2017 | 78 | 0 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2017 |  | 10/18/2018 | N | EXP | 350 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 690375 | 01532 | 875 | Solar | 05_14_211L1 | 06/10/2025 | 08/21/2025 | 50 | 40 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2025 | 09/18/2025 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MEDFORD | 534892 | 02155 | 15.2 | Solar | 05_14_50L1 | 06/26/2023 | 06/29/2023 | 4 | 3 | 1 | 06/30/2023 | 06/30/2023 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/11/2023 | Connected |  | N
National Grid | TYNGSBORO | 273652 | 01879 | 10 | Solar | 05_14_63L1 | 02/03/2020 | 02/06/2020 | 2 | 0 | 2 | 02/07/2020 | 02/07/2020 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 661225 | 01810 | 5.76 | Solar | 05_14_75L6 | 12/17/2024 | 02/12/2025 | 3 | 0 | 3 | 02/13/2025 | 02/13/2025 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 | 12/17/2024 | 4/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | METHUEN | 666895 | 01844 | 20.48 | Solar | 05_01_225W1 | 01/28/2025 | 02/18/2025 | 14 | 11 | 3 | 02/19/2025 | 02/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | METHUEN | 178381 | 01844 | 8.96 | Solar | 05_01_304W5 | 01/15/2018 | 01/15/2018 | 0 | 0 | 0 | 02/27/2018 | 02/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2018 |  | 1/21/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 7/31/2018 | Connected |  | N
National Grid | LANCASTER | 742683 | 01523 | 7.6 | Solar | 05_01_415L1 | 12/30/2025 | 01/06/2026 | 3 | 1 | 2 | 01/15/2026 | 01/15/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 | 12/30/2025 | 2/17/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2026 | Connected |  | N
National Grid | MILLBURY | 670775 | 01527 | 7.6 | Solar | 05_01_6J312 | 02/07/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2025 | Connected |  | N
National Grid | CHARLTON | 176701 | 01507 | 12 | Solar | 05_05_19W72 | 10/26/2015 | 10/26/2015 | 9 | 9 | 0 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2015 |  | 10/31/2016 | N | EXP | 357 |  |  | 0 | 0 | 0 | 3/14/2016 | 3/14/2016 | 3/17/2016 | Connected |  | N
National Grid | WORCESTER | 343155 | 01610 | 0 | Solar | 05_05_314W4 | 02/19/2021 | 02/24/2021 | 3 | 2 | 1 | 02/25/2021 | 02/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2021 |  | 2/24/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 233361 | 02726 | 7.6 | Solar | 05_12_37W4 | 07/05/2019 | 07/15/2019 | 5 | 0 | 5 | 07/16/2019 | 07/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 | 07/05/2019 | 8/20/2021 | Y | EXP | 365 | 10/15/2020 | 08/09/2021 | 293 | 0 | 293 |  |  | 8/14/2021 | Connected |  | N
National Grid | WESTBOROUGH | 724263 | 01581 | 150 | Solar | 05_14_211L1 | 10/06/2025 | 11/06/2025 | 22 | 15 | 7 | 11/07/2025 | 11/07/2025 | 53 | 30 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MEDFORD | 538685 | 02155 | 15 | Solar | 05_14_50L1 | 07/05/2023 | 07/06/2023 | 1 | 0 | 1 | 07/07/2023 | 07/07/2023 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2023 |  | 10/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2023 | Connected |  | N
National Grid | TYNGSBORO | 282749 | 01879 | 10 | Solar | 05_14_63L1 | 04/09/2020 | 04/21/2020 | 6 | 4 | 2 | 04/22/2020 | 04/22/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2020 | 04/09/2020 | 3/12/2021 | Y | EXP | 365 | 08/25/2020 | 10/13/2020 | 49 | 0 | 49 |  |  | 10/22/2020 | Connected |  | N
National Grid | ANDOVER | 675285 | 01810 | 10 | Solar | 05_14_75L6 | 03/03/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 670869 | 01841 | 5.76 | Solar | 05_01_225W1 | 02/07/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | METHUEN | 178488 | 01844 | 499.5 | Solar | 05_01_304W5 | 12/01/2017 | 01/23/2018 | 36 | 13 | 23 |  |  | 51 | 51 | 0 | 02/27/2018 | 03/12/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 03/12/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 8/20/2020 | 12/01/2017 | 9/28/2022 | Y | STD | 550 |  |  | 0 | 0 | 0 |  |  | 9/27/2022 | Connected |  | N
National Grid | BOLTON | 308483 | 01740 | 0 | Other | 05_01_415L2 | 08/25/2020 | 09/30/2020 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/26/2020 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/25/2020 |  | Y | STD | 707 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILLBURY | 187209 | 01527 | 200 | Solar | 05_01_6J316 | 06/05/2018 | 06/05/2018 | 3 | 0 | 3 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 176835 | 01507 | 3.8 | Solar | 05_05_19W72 | 02/29/2016 | 02/29/2016 | 2 | 2 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 |  | 3/6/2017 | N | EXP | 328 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 8/9/2016 | Connected |  | N
National Grid | WORCESTER | 415123 | 01603 | 15.2 | Solar | 05_05_314W4 | 03/02/2022 | 03/03/2022 | 1 | 0 | 1 | 03/04/2022 | 03/04/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 243069 | 02715 | 7.6 | Solar | 05_12_37W4 | 10/25/2019 | 10/30/2019 | 2 | 0 | 2 | 10/31/2019 | 10/31/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 |  | 10/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 735051 | 01532 | 250 | Solar | 05_14_211L1 | 11/27/2025 | 01/20/2026 | 35 | 27 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2026 | 02/02/2026 | 8 | 4 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MEDFORD | 560942 | 02155 | 0 | Solar | 05_14_50L1 | 11/20/2023 | 11/27/2023 | 4 | 2 | 2 | 11/28/2023 | 11/28/2023 | 67 | 44 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 |  | 3/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N
National Grid | TYNGSBORO | 287307 | 01879 | 6 | Solar | 05_14_63L1 | 05/06/2020 | 05/08/2020 | 1 | 0 | 1 | 05/11/2020 | 05/11/2020 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 676647 | 01844 | 5.8 | Solar | 05_14_75L6 | 03/18/2025 | 03/26/2025 | 8 | 6 | 2 | 04/09/2025 | 04/09/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 676081 | 01844 | 20 | Solar | 05_01_225W1 | 03/12/2025 | 04/14/2025 | 24 | 21 | 3 | 04/15/2025 | 04/15/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | METHUEN | 178572 | 01844 | 4980 | Solar | 05_01_304W5 | 12/08/2017 | 12/08/2017 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2018 | 03/07/2018 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2018 | 12/08/2017 | 10/28/2022 | Y | STD | 553 | 01/22/2022 | 05/03/2022 | 102 | 0 | 102 | 9/21/2022 | 10/19/2022 | 10/26/2022 | Connected |  | N
National Grid | LANCASTER | 493328 | 01523 | 499 | Solar | 05_01_415L2 | 02/21/2024 | 07/29/2024 | 109 | 52 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2024 | 08/14/2024 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILLBURY | 599616 | 01527 | 7.6 | Solar | 05_01_6J316 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 96 | 25 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 176897 | 01507 | 2000 | Solar | 05_05_19W72 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2016 | 02/19/2016 | 18 | 0 | 18 |  | 0 | 0 | 0 | 04/04/2017 | 04/17/2017 | 9 | 0 | 9 | 9/29/2016 |  | 1/30/2017 | N | STD | 123 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 472757 | 01603 | 11.31 | Solar | 05_05_314W4 | 11/11/2022 | 11/18/2022 | 6 | 2 | 4 | 11/21/2022 | 11/21/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2022 | 11/11/2022 | 4/24/2024 | Y | EXP | 365 | 02/07/2023 | 04/25/2023 | 78 | 0 | 78 |  |  | 12/1/2023 | Connected |  | N
National Grid | SOMERSET | 250240 | 02726 | 7.6 | Solar | 05_12_37W4 | 08/22/2019 | 09/18/2019 | 18 | 18 | 0 | 09/19/2019 | 09/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 6/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 174305 | 01532 | 475 | Solar | 05_14_211L1 | 01/01/2012 | 01/01/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2012 |  | 5/16/2012 | N | EXP | 23 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 566383 | 02155 | 0 | Solar | 05_14_50L1 | 10/26/2023 | 10/27/2023 | 1 | 0 | 1 | 10/30/2023 | 10/30/2023 | 74 | 52 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 289256 | 01879 | 3.8 | Solar | 05_14_63L1 | 05/06/2020 | 05/07/2020 | 0 | 0 | 0 | 05/08/2020 | 05/08/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/6/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 693695 | 01810 | 20 | Solar | 05_14_75L6 | 05/29/2025 | 06/04/2025 | 4 | 0 | 4 | 06/05/2025 | 06/05/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2025 | Connected |  | N
National Grid | LAWRENCE | 681615 | 01841 | 10.64 | Solar | 05_01_225W1 | 04/02/2025 | 04/15/2025 | 10 | 6 | 4 | 04/16/2025 | 04/16/2025 | 62 | 37 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2025 |  | 7/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | METHUEN | 178571 | 01844 |  | Solar | 05_01_304W5 | 12/08/2017 | 12/08/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/16/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 669726 | 01523 | 3.8 | Solar | 05_01_6J316 | 02/03/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | MILLBURY | 176896 | 01527 | 2000 | Solar | 05_05_19W72 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2016 | 02/19/2016 | 18 | 0 | 18 |  | 0 | 0 | 0 | 03/23/2017 |  | 254 | 0 | 254 | 9/29/2016 |  | 1/30/2017 | N | STD | 123 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 495314 | 01507 | 11.136 | Solar | 05_05_314W4 | 04/10/2023 | 05/02/2023 | 15 | 13 | 2 | 05/03/2023 | 05/03/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2023 |  | 7/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | WORCESTER | 258934 | 01603 | 3.8 | Solar | 05_12_37W4 | 10/12/2019 | 10/14/2019 | 0 | 0 | 0 | 10/15/2019 | 10/15/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  | 11/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 175050 | 02715 | 37.8 | Solar | 05_14_211L1 | 08/10/2012 | 08/10/2012 | 5 | 0 | 5 | 08/20/2012 | 08/20/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/15/2012 | N | EXP | 27 |  |  | 0 | 0 | 0 | 12/9/2013 | 12/9/2013 | 12/9/2013 | Connected |  | N
National Grid | NORTHBOROUGH | 569243 | 01532 | 0 | Solar | 05_14_50L1 | 11/06/2023 | 11/08/2023 | 2 | 0 | 2 | 11/09/2023 | 11/09/2023 | 59 | 35 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 292786 | 02155 | 15.705 | Solar | 05_14_63L1 | 09/22/2020 | 03/23/2021 | 126 | 125 | 1 | 03/24/2021 | 03/24/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 |  | 10/9/2022 | N | EXP | 500 |  |  | 0 | 0 | 0 |  |  | 9/28/2022 | Connected |  | N
National Grid | TYNGSBORO | 698874 | 01879 | 4200 | Other | 05_14_75L6 | 10/16/2025 | 11/26/2025 | 29 | 22 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2025 | 12/26/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 683232 | 01810 | 7.6 | Solar | 05_01_225W1 | 04/15/2025 | 07/15/2025 | 29 | 24 | 5 | 07/16/2025 | 07/16/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2025 |  | 8/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | LAWRENCE | 178681 | 01841 | 4950 | Solar | 05_01_304W5 | 04/11/2018 | 04/11/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 11/05/2018 | 139 | 119 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 740995 | 01844 | 19 | Solar | 05_01_415L2 | 12/18/2025 | 01/04/2026 | 9 | 5 | 4 | 01/05/2026 | 01/05/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOLTON | 710713 | 01740 | 7.6 | Solar | 05_01_6J316 | 08/08/2025 | 09/02/2025 | 1 | 0 | 1 | 09/17/2025 | 09/17/2025 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 176981 | 01527 | 5.2 | Solar | 05_05_19W72 | 12/29/2016 | 12/29/2016 | 1 | 1 | 0 | 01/04/2017 | 01/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2017 | 12/29/2016 | 1/7/2018 | Y | EXP | 366 | 05/01/2017 | 06/08/2017 | 27 | 0 | 27 | 6/28/2017 | 6/28/2017 | 6/30/2017 | Connected |  | N
National Grid | CHARLTON | 544895 | 01507 | 15.2 | Solar | 05_05_314W4 | 08/01/2023 | 08/07/2023 | 4 | 0 | 4 | 08/08/2023 | 08/08/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 |  | 10/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2023 | Connected |  | N
National Grid | WORCESTER | 323871 | 01603 | 7.6 | Solar | 05_12_37W4 | 01/11/2021 | 01/22/2021 | 7 | 7 | 0 | 01/25/2021 | 01/25/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2021 |  | 1/21/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 175350 | 02715 | 491 | Solar | 05_14_211L1 | 01/01/2012 | 01/01/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2014 | 01/01/2012 | 12/31/2014 | Y | EXP | 117 | 05/04/2015 | 05/22/2015 | 14 | 0 | 14 | 9/17/2014 | 9/17/2014 | 5/27/2015 | Connected |  | N
National Grid | NORTHBOROUGH | 582479 | 01532 | 6 | Solar | 05_14_50L1 | 02/01/2024 | 02/06/2024 | 3 | 0 | 3 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/01/2024 | 4/12/2025 | Y | EXP | 365 | 06/06/2024 | 07/24/2024 | 49 | 0 | 49 |  |  | 9/21/2024 | Connected |  | N
National Grid | MEDFORD | 306473 | 02155 | 10 | Solar | 05_14_63L1 | 09/18/2020 | 09/24/2020 | 3 | 0 | 3 | 09/25/2020 | 09/25/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 618791 | 01879 | 160 | Solar | 05_14_76L1 | 07/11/2024 | 11/25/2024 | 94 | 85 | 9 | 11/26/2024 | 11/26/2024 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  | 9/14/2026 | N | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ANDOVER | 714705 | 01810 | 0 | Battery Add-On | 05_01_225W1 | 08/26/2025 | 09/16/2025 | 12 | 9 | 3 | 09/17/2025 | 09/17/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2026 | Connected |  | N
National Grid | METHUEN | 193416 | 01844 | 24 | Solar | 05_01_304W5 | 08/14/2018 | 09/04/2018 | 13 | 0 | 13 | 09/05/2018 | 09/05/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2018 | 08/14/2018 |  | Y | EXP | 427 | 08/21/2019 | 09/11/2019 | 21 | 0 | 21 |  |  | 12/5/2019 | Connected |  | N
National Grid | DRACUT | 743675 | 01826 | 20.52 | Solar | 05_01_415L2 | 01/06/2026 | 01/12/2026 | 2 | 2 | 0 | 01/13/2026 | 01/13/2026 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BOLTON | 661862 | 01740 | 5.76 | Solar | 05_01_6J318 | 12/19/2024 | 01/15/2025 | 6 | 0 | 6 | 01/16/2025 | 01/16/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | SUTTON | 177262 | 01590 | 270 | Solar | 05_05_19W72 | 01/20/2015 | 01/20/2015 | 3 | 0 | 3 | 01/28/2015 | 01/28/2015 | 0 | 0 | 0 | 03/11/2015 | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 4/17/2015 | 01/20/2015 | 8/28/2017 | Y | EXP | 864 | 05/13/2016 | 06/20/2016 | 24 | 0 | 24 | 11/2/2016 | 11/2/2016 | 11/7/2016 | Connected |  | N
National Grid | CHARLTON | 548633 | 01507 | 5.985 | Solar | 05_05_314W4 | 08/22/2023 | 08/25/2023 | 3 | 1 | 2 | 08/28/2023 | 08/28/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 |  | 11/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2024 | Connected |  | N
National Grid | WORCESTER | 331642 | 01603 | 10 | Solar | 05_12_37W4 | 12/15/2020 | 12/21/2020 | 3 | 0 | 3 | 12/22/2020 | 12/22/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2021 | 12/15/2020 | 12/16/2021 | Y | EXP | 365 | 04/16/2021 | 05/04/2021 | 18 | 0 | 18 |  |  | 6/28/2021 | Connected |  | N
National Grid | SOMERSET | 175496 | 02726 | 68.4 | Solar | 05_14_211L1 | 09/25/2014 | 09/25/2014 | 6 | 0 | 6 | 10/06/2014 | 10/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 09/25/2014 | 12/31/2014 | Y | EXP | 51 | 01/23/2015 | 02/19/2015 | 18 | 0 | 18 | 2/26/2015 | 2/26/2015 | 4/16/2015 | Connected |  | N
National Grid | NORTHBOROUGH | 597748 | 01532 | 1.45 | Solar | 05_14_50L1 | 04/02/2024 | 06/11/2024 | 48 | 47 | 1 | 06/12/2024 | 06/12/2024 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 |  | 7/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | MEDFORD | 314982 | 02155 | 9.765 | Solar | 05_14_63L1 | 12/04/2020 | 12/07/2020 | 0 | 0 | 0 | 12/08/2020 | 12/08/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 12/04/2020 | 11/22/2022 | Y | EXP | 365 | 08/06/2021 | 12/07/2021 | 123 | 63 | 60 |  |  | 12/9/2021 | Connected |  | N
National Grid | TYNGSBORO | 722747 | 01879 | 22.8 | Solar | 05_14_76L1 | 09/30/2025 | 10/02/2025 | 2 | 0 | 2 | 10/03/2025 | 10/03/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 715560 | 01810 | 13.36 | Solar | 05_01_225W1 | 09/03/2025 | 09/10/2025 | 5 | 1 | 4 | 09/11/2025 | 09/11/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2026 | Connected |  | N
National Grid | METHUEN | 199870 | 01844 | 10 | Solar | 05_01_304W5 | 10/31/2018 | 12/31/2018 | 3 | 1 | 2 | 01/02/2019 | 01/02/2019 | 52 | 47 | 5 | 05/13/2020 | 06/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 06/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 4/3/2019 | 10/31/2018 | 1/6/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2020 | Connected |  | N
National Grid | HAVERHILL | 748920 | 01830 | 10 | Solar | 05_01_415L2 | 02/03/2026 | 02/04/2026 | 3 | 0 | 3 | 03/18/2026 | 03/18/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HARVARD | 726459 | 01451 | 10 | Solar | 05_01_6J319 | 02/17/2026 | 02/19/2026 | 2 | 0 | 2 | 03/05/2026 | 03/05/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MILLBURY | 177733 | 01527 | 3.8 | Solar | 05_05_19W72 | 03/22/2017 | 03/22/2017 | 4 | 4 | 0 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 | 03/22/2017 | 3/27/2018 | Y | EXP | 363 | 08/09/2017 | 09/12/2017 | 23 | 0 | 23 | 10/16/2017 | 10/16/2017 | 10/18/2017 | Connected |  | N
National Grid | CHARLTON | 553642 | 01507 | 120 | Solar | 05_05_314W4 | 09/11/2023 | 09/29/2023 | 14 | 5 | 9 | 10/02/2023 | 10/02/2023 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 | 09/11/2023 | 10/14/2025 | Y | EXP | 217 | 01/30/2025 | 01/20/2025 | 0 | 0 | 0 |  |  | 5/9/2025 | Connected |  | N
National Grid | WORCESTER | 347803 | 01603 | 4.64 | Solar | 05_12_37W4 | 04/07/2021 | 01/06/2022 | 4 | 0 | 4 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  | 1/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2022 | Connected |  | N
National Grid | SOMERSET | 175775 | 02726 | 60 | Solar | 05_14_211L1 | 08/15/2014 | 08/15/2014 | 7 | 0 | 7 | 08/27/2014 | 08/27/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2014 |  | 11/28/2014 | N | EXP | 70 |  |  | 0 | 0 | 0 | 9/19/2014 | 9/19/2014 | 11/24/2014 | Connected |  | N
National Grid | NORTHBOROUGH | 600002 | 01532 | 23 | Solar | 05_14_50L1 | 03/27/2024 | 03/29/2024 | 2 | 0 | 2 | 04/01/2024 | 04/01/2024 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  | 5/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | Y
National Grid | MEDFORD | 316168 | 02155 | 7.6 | Solar | 05_14_63L1 | 10/21/2020 | 10/22/2020 | 0 | 0 | 0 | 10/23/2020 | 10/23/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2020 | 10/21/2020 | 10/21/2021 | Y | EXP | 365 | 02/10/2021 | 04/05/2021 | 54 | 0 | 54 |  |  | 4/27/2021 | Connected |  | N
National Grid | TYNGSBORO | 756892 | 01879 | 13.8 | Solar | 05_14_76L1 | 03/16/2026 | 03/19/2026 | 3 | 0 | 3 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 718559 | 01810 | 11.5 | Solar | 05_01_225W1 | 09/11/2025 | 09/16/2025 | 3 | 0 | 3 | 09/17/2025 | 09/17/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2026 | Connected |  | N
National Grid | LAWRENCE | 229816 | 01841 | 10 | Solar | 05_01_304W5 | 05/21/2019 | 05/30/2019 | 5 | 0 | 5 | 05/31/2019 | 05/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N
National Grid | HAVERHILL | 749797 | 01830 | 15.2 | Solar | 05_01_415L2 | 02/06/2026 | 02/10/2026 | 2 | 0 | 2 | 02/11/2026 | 02/11/2026 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HARVARD | 726456 | 01451 | 13.8 | Solar | 05_01_6J319 | 02/17/2026 | 02/19/2026 | 2 | 0 | 2 | 03/05/2026 | 03/05/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MILLBURY | 178080 | 01527 | 2800 | Solar | 05_05_19W72 | 05/08/2017 | 05/08/2017 | 121 | 121 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 | 11/29/2017 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2018 | 05/08/2017 | 12/2/2020 | Y | STD | 680 | 10/12/2019 | 09/21/2020 | 346 | 126 | 220 |  |  | 12/7/2020 | Connected |  | N
National Grid | CHARLTON | 567577 | 01507 | 240 | Solar | 05_05_314W4 | 10/31/2023 |  | 97 | 27 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 359749 | 01603 | 15 | Solar | 05_12_37W4 | 08/24/2021 | 04/28/2022 | 168 | 159 | 9 | 04/29/2022 | 04/29/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 176422 | 02726 | 2000 | Solar | 05_14_211L1 | 02/02/2016 | 02/02/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2016 | 03/08/2016 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/9/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 604454 | 01532 | 0 | Battery Add-On | 05_14_50L1 | 07/16/2024 | 07/31/2024 | 11 | 9 | 2 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 327152 | 02155 | 7.6 | Solar | 05_14_63L1 | 12/14/2020 | 12/18/2020 | 3 | 0 | 3 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/14/2020 | 3/2/2022 | Y | EXP | 365 | 09/24/2021 | 10/12/2021 | 18 | 0 | 18 |  |  | 12/9/2021 | Connected |  | N
National Grid | TYNGSBORO | 175917 | 01879 | 1000 | Solar | 05_14_76L1 | 03/12/2015 | 03/12/2015 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2015 | 04/16/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 |  | 12/14/2016 | N | STD | 442 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 722322 | 01810 | 20.242 | Solar | 05_01_225W1 | 09/30/2025 | 10/08/2025 | 5 | 0 | 5 | 10/09/2025 | 10/09/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | LAWRENCE | 301583 | 01841 | 7.92 | Solar | 05_01_304W5 | 07/16/2020 | 08/04/2020 | 12 | 12 | 0 | 08/05/2020 | 08/05/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 |  | 8/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | HAVERHILL | 751116 | 01830 | 10 | Solar | 05_01_415L2 | 02/13/2026 | 02/18/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 30 | 18 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HARVARD | 726402 | 01451 | 10 | Solar | 05_01_6J319 | 02/17/2026 | 02/19/2026 | 2 | 0 | 2 | 03/05/2026 | 03/05/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MILLBURY | 178605 | 01527 | 10 | Solar | 05_05_19W72 | 12/12/2017 | 12/12/2017 | 14 | 0 | 14 | 01/04/2018 | 01/04/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 |  | 12/18/2018 | N | EXP | 347 | 05/30/2018 | 06/25/2018 | 26 | 0 | 26 |  |  | 7/11/2018 | Connected |  | N
National Grid | CHARLTON | 593596 | 01507 | 6.282 | Solar | 05_05_314W4 | 03/08/2024 | 03/13/2024 | 3 | 0 | 3 | 03/14/2024 | 03/14/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2024 | Connected |  | N
National Grid | WORCESTER | 469990 | 01603 | 0 | Solar | 05_12_37W4 | 11/09/2022 | 12/19/2022 | 27 | 26 | 1 | 12/20/2022 | 12/20/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 4/20/2024 | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 177132 | 02715 | 566.1 | Solar | 05_14_211L1 | 01/23/2017 | 01/23/2017 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/29/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 606583 | 01581 | 23 | Solar | 05_14_50L1 | 04/25/2024 | 05/03/2024 | 4 | 0 | 4 | 07/29/2024 | 07/29/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2024 | Connected |  | N
National Grid | MEDFORD | 326918 | 02155 | 9.8 | Solar | 05_14_63L1 | 12/21/2020 | 12/30/2020 | 5 | 0 | 5 | 12/31/2020 | 12/31/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 196058 | 01879 | 240 | Solar | 05_14_76L1 | 10/16/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/01/2018 | 11/21/2018 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2020 | 10/16/2018 | 3/9/2027 | Y | STD | 798 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 721741 | 01810 | 7.6 | Solar | 05_01_225W1 | 10/05/2025 | 11/12/2025 | 8 | 4 | 4 | 11/13/2025 | 11/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | METHUEN | 303514 | 01844 | 0 | Other | 05_01_304W5 | 09/15/2020 | 10/09/2020 | 18 | 13 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 | 11/09/2020 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/15/2020 |  | Y | STD | 539 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 174193 | 01830 | 14.19 | Solar | 05_01_415L2 | 03/16/2012 | 03/16/2012 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2012 |  | 4/19/2012 | N | EXP | 53 |  |  | 0 | 0 | 0 | 6/11/2012 | 6/11/2012 | 8/3/2012 | Connected |  | N
National Grid | BOLTON | 174966 | 01740 | 154 | Solar | 05_01_6J319 | 09/03/2013 | 09/03/2013 | 9 | 0 | 9 | 09/17/2013 | 09/17/2013 | 353 | 3 | 350 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2013 |  | 8/1/2014 | N | EXP | 303 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 190436 | 01527 | 250 | Solar | 05_05_19W72 | 07/11/2018 | 08/15/2018 | 5 | 0 | 5 | 08/16/2018 | 08/16/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 621808 | 01507 | 11.5 | Solar | 05_05_314W4 | 07/01/2024 | 08/19/2024 | 9 | 4 | 5 | 08/20/2024 | 08/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 9/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | WORCESTER | 541845 | 01603 | 15.66 | Solar | 05_12_37W4 | 07/24/2023 |  | 96 | 70 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 178607 | 02726 | 150 | Solar | 05_14_211L1 | 12/12/2017 | 12/12/2017 | 24 | 12 | 12 | 01/19/2018 | 01/19/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2018 |  | 12/18/2018 | N | EXP | 330 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | NORTHBOROUGH | 616825 | 01532 |  | Battery Add-On | 05_14_50L1 | 06/10/2024 | 06/17/2024 | 5 | 0 | 5 | 06/18/2024 | 06/18/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | MEDFORD | 329444 | 02155 | 7.6 | Solar | 05_14_63L1 | 12/29/2020 | 12/31/2020 | 1 | 0 | 1 | 01/04/2021 | 01/04/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/29/2020 | 12/22/2022 | Y | EXP | 365 | 08/06/2021 | 10/12/2021 | 61 | 3 | 58 |  |  | 12/1/2021 | Connected |  | Y
National Grid | TYNGSBORO | 196057 | 01879 | 960 | Solar | 05_14_76L1 | 10/18/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2020 | 10/18/2018 | 3/9/2027 | Y | CMPX | 798 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 721546 | 01810 | 5.76 | Solar | 05_01_225W1 | 09/30/2025 | 10/06/2025 | 4 | 0 | 4 | 10/07/2025 | 10/07/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | METHUEN | 311604 | 01844 | 19 | Solar | 05_01_304W5 | 09/09/2020 | 09/14/2020 | 3 | 3 | 0 | 09/15/2020 | 09/15/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 09/09/2020 | 6/2/2022 | Y | EXP | 475 | 01/12/2021 | 02/05/2021 | 24 | 0 | 24 |  |  | 4/22/2022 | Connected |  | N
National Grid | HAVERHILL | 174545 | 01830 | 2000 | Solar | 05_01_415L2 | 11/08/2011 | 11/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 04/16/2013 | 04/16/2013 | 0 | 0 | 0 | 4/9/2013 | 11/08/2011 | 10/31/2012 | Y | STD | 160 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/31/2014 | Connected |  | N
National Grid | BOLTON | 363819 | 01740 | 100 | Solar | 05_01_6J319 | 12/29/2021 | 10/19/2022 | 202 | 202 | 0 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 12/29/2021 | 12/31/2024 | Y | STD | 130 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | MILLBURY | 239803 | 01527 | 6 | Solar | 05_05_19W72 | 06/26/2019 | 07/08/2019 | 7 | 3 | 4 | 07/09/2019 | 07/09/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 | 06/26/2019 | 6/26/2020 | Y | EXP | 365 | 11/07/2019 | 12/19/2019 | 42 | 0 | 42 |  |  | 1/21/2020 | Connected |  | N
National Grid | CHARLTON | 657569 | 01507 | 5.76 | Solar | 05_05_314W4 | 11/28/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/28/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | WORCESTER | 578165 | 01610 | 10 | Solar | 05_12_37W4 | 12/20/2023 | 01/04/2024 | 8 | 8 | 0 | 01/05/2024 | 01/05/2024 | 19 | 0 | 19 | 02/05/2024 | 03/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 03/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/26/2025 | N | EXP | 365 | 03/16/2024 | 07/23/2024 | 130 | 29 | 101 |  |  | 8/5/2024 | Connected |  | N
National Grid | SOMERSET | 178719 | 02726 | 86.19 | Solar | 05_14_211L1 | 04/12/2018 | 04/12/2018 | 380 | 24 | 356 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 618866 | 01532 | 23 | Battery Add-On | 05_14_50L1 | 06/18/2024 | 06/24/2024 | 3 | 0 | 3 | 06/25/2024 | 06/25/2024 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | MEDFORD | 330332 | 02155 | 9.8 | Solar | 05_14_63L1 | 01/04/2021 | 01/07/2021 | 2 | 0 | 2 | 01/08/2021 | 01/08/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 01/04/2021 | 3/7/2022 | Y | EXP | 365 | 09/14/2021 | 10/14/2021 | 31 | 0 | 31 |  |  | 12/13/2021 | Connected |  | Y
National Grid | TYNGSBORO | 196056 | 01879 | 3600 | Solar | 05_14_76L1 | 10/18/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2020 | 10/18/2018 | 3/9/2027 | Y | CMPX | 798 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 727783 | 01810 | 5.76 | Solar | 05_01_225W1 | 10/27/2025 | 10/29/2025 | 2 | 0 | 2 | 10/30/2025 | 10/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2026 | Connected |  | N
National Grid | METHUEN | 319874 | 01844 | 15.2 | Solar | 05_01_304W5 | 10/16/2020 | 10/23/2020 | 4 | 4 | 0 | 10/26/2020 | 10/26/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2020 | 10/16/2020 | 3/26/2022 | Y | EXP | 365 | 03/05/2021 | 03/16/2021 | 11 | 0 | 11 |  |  | 9/10/2021 | Connected |  | N
National Grid | HAVERHILL | 174546 | 01830 | 2000 | Solar | 05_01_415L2 | 11/08/2011 | 11/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 04/16/2013 | 04/16/2013 | 0 | 0 | 0 | 4/9/2013 | 11/08/2011 | 10/31/2012 | Y | STD | 160 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/31/2014 | Connected |  | N
National Grid | BOLTON | 650619 | 01740 | 10 | Solar | 05_01_6J319 | 10/30/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 10/30/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | SUTTON | 278585 | 01590 | 7.6 | Solar | 05_05_19W72 | 04/14/2020 | 04/16/2020 | 2 | 2 | 0 | 04/17/2020 | 04/17/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2020 | 04/14/2020 | 4/15/2021 | Y | EXP | 365 | 06/24/2020 | 08/27/2020 | 64 | 0 | 64 |  |  | 10/5/2020 | Connected |  | Y
National Grid | CHARLTON | 663565 | 01507 | 10 | Solar | 05_05_314W4 | 01/03/2025 | 01/29/2025 | 12 | 8 | 4 | 01/30/2025 | 01/30/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 580959 | 01610 | 23 | Solar | 05_12_37W4 | 01/02/2024 | 03/14/2024 | 44 | 43 | 1 | 03/15/2024 | 03/15/2024 | 41 | 36 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 01/02/2024 | 5/23/2025 | Y | EXP | 365 | 07/03/2024 | 07/18/2024 | 16 | 0 | 16 |  |  | 9/25/2024 | Connected |  | N
National Grid | SOMERSET | 185409 | 02726 | 4999 | Solar | 05_14_211L1 | 06/15/2018 | 06/15/2018 | 32 | 32 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2018 | 08/17/2018 | 12 | 12 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2019 | 06/15/2018 | 8/6/2021 | Y | STD | 498 | 03/04/2020 | 05/27/2021 | 450 | 5 | 445 |  |  | 8/2/2021 | Connected |  | N
National Grid | WESTBOROUGH | 625996 | 01581 |  | Battery Add-On | 05_14_50L1 | 07/18/2024 | 07/19/2024 | 1 | 0 | 1 | 07/22/2024 | 07/22/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 |  | 7/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2024 | Connected |  | N
National Grid | MEDFORD | 335650 | 02155 | 7.6 | Solar | 05_14_63L1 | 01/22/2021 |  | 31 | 31 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 245548 | 01879 | 17.6 | Solar | 05_14_76L1 | 07/26/2019 | 07/29/2019 | 0 | 0 | 0 | 07/30/2019 | 07/30/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2019 |  | 7/26/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 174154 | 01810 | 1000 | Solar | 05_01_225W2 | 04/23/2012 | 04/23/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2012 | 06/22/2012 | 31 | 0 | 31 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 324458 | 01844 | 0 | Solar | 05_01_304W5 | 11/07/2020 | 11/10/2020 | 1 | 0 | 1 | 11/12/2020 | 11/12/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 2/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 175243 | 01830 | 17 | Solar | 05_01_415L2 | 08/25/2014 | 08/25/2014 | 7 | 0 | 7 | 09/05/2014 | 09/05/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2014 | 08/25/2014 | 12/10/2014 | Y | EXP | 70 | 01/14/2015 | 01/06/2015 | 0 | 0 | 0 | 1/13/2015 | 1/13/2015 | 3/6/2015 | Connected |  | N
National Grid | LANCASTER | 706197 | 01523 | 6.08 | Solar | 05_01_6J319 | 07/21/2025 | 08/07/2025 | 3 | 0 | 3 | 08/15/2025 | 08/15/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | MILLBURY | 289859 | 01527 | 10 | Solar | 05_05_19W72 | 06/19/2020 | 07/21/2020 | 21 | 17 | 4 | 07/22/2020 | 07/22/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 06/19/2020 | 8/1/2021 | Y | EXP | 365 | 01/06/2021 | 02/23/2021 | 48 | 0 | 48 |  |  | 3/9/2021 | Connected |  | N
National Grid | CHARLTON | 695567 | 01507 | 15.2 | Solar | 05_05_314W4 | 06/04/2025 | 06/11/2025 | 4 | 1 | 3 | 06/12/2025 | 06/12/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | WORCESTER | 608550 | 01603 | 6 | Solar | 05_12_37W4 | 05/03/2024 | 05/14/2024 | 3 | 0 | 3 | 05/15/2024 | 05/15/2024 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/03/2024 | 7/3/2025 | Y | EXP | 365 | 08/20/2024 | 01/20/2025 | 154 | 0 | 154 |  |  | 2/3/2025 | Connected |  | N
National Grid | SOMERSET | 185918 | 02726 | 37.8 | Solar | 05_14_211L1 | 05/22/2018 | 05/22/2018 | 4 | 0 | 4 | 05/30/2018 | 05/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 5/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 644839 | 01532 |  | Battery Add-On | 05_14_50L1 | 10/03/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 11/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | N
National Grid | MEDFORD | 339133 | 02155 | 7.92 | Solar | 05_14_63L1 | 03/26/2021 | 04/06/2021 | 6 | 0 | 6 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2021 |  | 6/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 295965 | 01879 | 9.36 | Solar | 05_14_76L1 | 06/11/2020 | 07/06/2020 | 16 | 11 | 5 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 7/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | ANDOVER | 176327 | 01810 | 2800 | Solar | 05_01_225W2 | 07/17/2015 | 07/17/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2015 | 08/18/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 |  | 7/1/2016 | N | STD | 221 |  |  | 0 | 0 | 0 |  |  | 12/19/2016 | Withdrawn |  | N
National Grid | METHUEN | 339473 | 01844 | 3.8 | Solar | 05_01_304W5 | 01/29/2021 | 03/30/2021 | 38 | 37 | 1 | 03/31/2021 | 03/31/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 01/29/2021 | 7/23/2022 | Y | EXP | 365 | 06/12/2021 | 07/06/2021 | 19 | 0 | 19 |  |  | 7/8/2022 | Connected |  | N
National Grid | HAVERHILL | 175323 | 01830 | 630 | Solar | 05_01_415L2 | 11/07/2014 | 11/07/2014 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/19/2014 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 755205 | 01523 | 3.8 | Solar | 05_01_6J326 | 03/06/2026 | 03/11/2026 | 2 | 0 | 2 | 03/23/2026 | 03/23/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SUTTON | 300899 | 01590 | 10 | Solar | 05_05_19W72 | 09/25/2020 | 11/03/2020 | 26 | 24 | 2 | 11/04/2020 | 11/04/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 | 09/25/2020 | 11/3/2021 | Y | EXP | 365 | 02/05/2021 | 04/06/2021 | 60 | 0 | 60 |  |  | 4/8/2021 | Connected |  | N
National Grid | CHARLTON | 724347 | 01507 | 11.4 | Solar | 05_05_314W4 | 10/06/2025 | 10/14/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 1/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2026 | Connected |  | N
National Grid | WORCESTER | 618725 | 01603 | 6 | Solar | 05_12_37W4 | 06/18/2024 | 07/03/2024 | 5 | 4 | 1 | 07/05/2024 | 07/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 |  | 7/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2024 | Connected |  | N
National Grid | SOMERSET | 186232 | 02726 | 249.8 | Solar | 05_14_211L1 | 05/24/2018 | 05/24/2018 | 2 | 0 | 2 | 05/31/2018 | 05/31/2018 | 33 | 11 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 | 05/24/2018 | 8/31/2021 | Y | EXP | 455 |  |  | 0 | 0 | 0 |  |  | 8/20/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 690506 | 01532 |  | Solar | 05_14_50L1 | 05/27/2025 | 06/10/2025 | 9 | 5 | 4 | 06/11/2025 | 06/11/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | MEDFORD | 342738 | 02155 | 7.6 | Solar | 05_14_63L1 | 02/24/2021 | 03/16/2021 | 14 | 14 | 0 | 03/17/2021 | 03/17/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 | 02/24/2021 | 9/17/2022 | Y | EXP | 365 | 08/15/2021 | 09/01/2021 | 16 | 3 | 13 |  |  | 2/2/2022 | Connected |  | N
National Grid | TYNGSBORO | 448164 | 01879 | 30 | Solar | 05_14_76L1 | 07/31/2022 | 08/01/2022 | 1 | 0 | 1 | 08/02/2022 | 08/02/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2022 |  | 10/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 177388 | 01810 | 2800 | Solar | 05_01_225W2 | 07/17/2015 | 07/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2015 | 08/18/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 07/17/2015 | 7/20/2018 | Y | STD | 970 | 08/28/2017 | 06/18/2018 | 145 | 0 | 145 |  |  | 7/20/2017 | Connected |  | N
National Grid | LAWRENCE | 352535 | 01841 | 7.54 | Solar | 05_01_304W5 | 04/14/2021 | 04/15/2021 | 0 | 0 | 0 | 04/16/2021 | 04/16/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 |  | 4/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2021 | Connected |  | N
National Grid | HAVERHILL | 175578 | 01830 | 30 | Solar | 05_01_415L2 | 12/09/2014 | 12/09/2014 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 504930 | 01453 | 20 | Solar | 05_01_6J326 | 03/01/2023 | 03/21/2023 | 14 | 4 | 10 | 03/22/2023 | 03/22/2023 | 252 | 233 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 330085 | 01590 | 6 | Solar | 05_05_19W72 | 01/05/2021 | 01/07/2021 | 1 | 0 | 1 | 01/08/2021 | 01/08/2021 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2021 | 01/05/2021 |  | Y | EXP | 365 | 05/27/2021 | 07/08/2021 | 42 | 0 | 42 |  |  | 8/6/2021 | Connected |  | N
National Grid | CHARLTON | 175947 | 01507 | 336 | Solar | 05_05_314W5 | 03/17/2015 | 03/17/2015 | 2 | 1 | 1 | 03/20/2015 | 03/20/2015 | 410 | 13 | 397 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2015 |  | 8/17/2015 | N | EXP | 101 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 637464 | 01603 | 7.6 | Solar | 05_12_37W4 | 09/03/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 09/03/2024 | 11/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | SOMERSET | 186708 | 02726 | 249.8 | Solar | 05_14_211L1 | 05/30/2018 | 05/30/2018 | 1 | 0 | 1 | 06/04/2018 | 06/04/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2018 | 05/30/2018 | 10/30/2020 | Y | EXP | 598 | 09/25/2020 | 09/24/2020 | 0 | 0 | 0 |  |  | 10/28/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 266407 | 01532 | 17.6 | Solar | 05_14_50L2 | 01/31/2020 | 02/06/2020 | 4 | 3 | 1 | 02/07/2020 | 02/07/2020 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 2/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2020 | Connected |  | N
National Grid | MEDFORD | 379714 | 02155 | 6 | Solar | 05_14_63L1 | 09/20/2021 | 12/09/2021 | 4 | 0 | 4 | 09/27/2021 | 09/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 461652 | 01879 | 0 | Solar | 05_14_76L1 | 09/28/2022 | 10/04/2022 | 4 | 3 | 1 | 10/05/2022 | 10/05/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 453761 | 01810 | 499 | Solar | 05_01_225W2 | 09/08/2022 | 10/04/2022 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2022 | 10/31/2022 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 397095 | 01844 | 1500 | Solar | 05_01_304W5 | 03/15/2022 |  | 161 | 153 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176201 | 01830 | 2000 | Solar | 05_01_415L2 | 02/11/2015 | 02/11/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/19/2015 | 03/19/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 | 12/11/2015 | 02/11/2015 | 2/8/2018 | Y | STD | 790 | 03/20/2018 | 03/20/2018 | 0 | 0 | 0 | 12/13/2017 | 12/13/2017 | 12/31/2017 | Connected |  | N
National Grid | LEOMINSTER | 596707 | 01453 | 3.8 | Solar | 05_01_6J326 | 03/13/2024 | 05/08/2024 | 1 | 0 | 1 | 05/09/2024 | 05/09/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2024 |  | 5/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | SUTTON | 331847 | 01590 | 8.75 | Solar | 05_05_19W72 | 01/04/2021 | 01/07/2021 | 2 | 0 | 2 | 01/08/2021 | 01/08/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2021 | 01/04/2021 |  | Y | EXP | 365 | 08/03/2021 | 08/17/2021 | 15 | 0 | 15 |  |  | 8/26/2021 | Connected |  | N
National Grid | CHARLTON | 176866 | 01507 | 1232 | Solar | 05_05_314W5 | 01/22/2016 | 01/22/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/26/2016 | 02/17/2016 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/27/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 639222 | 01610 | 6 | Solar | 05_12_37W4 | 09/10/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 09/10/2024 | 11/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | SOMERSET | 200571 | 02726 | 883.2 | Solar | 05_14_211L1 | 06/04/2019 | 07/29/2019 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2019 | 08/28/2019 | 21 | 5 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 176393 | 01582 | 56 | Solar | 05_14_50L3 | 02/02/2016 | 02/02/2016 | 4 | 4 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2016 |  | 9/8/2017 | N | EXP | 576 |  |  | 0 | 0 | 0 | 2/16/2016 | 2/16/2016 | 6/23/2017 | Connected |  | N
National Grid | MEDFORD | 393677 | 02155 | 7.25 | Solar | 05_14_63L1 | 11/05/2021 | 12/13/2021 | 4 | 2 | 2 | 12/14/2021 | 12/14/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2022 | 11/05/2021 | 7/28/2023 | Y | EXP | 365 | 05/13/2022 | 06/07/2022 | 26 | 0 | 26 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 500093 | 01879 | 15.36 | Solar | 05_14_76L1 | 02/07/2023 | 02/24/2023 | 13 | 12 | 1 | 02/27/2023 | 02/27/2023 | 61 | 42 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2023 | 02/07/2023 | 6/27/2024 | Y | EXP | 365 | 07/27/2023 | 10/25/2023 | 91 | 0 | 91 |  |  | 10/27/2023 | Connected |  | N
National Grid | ANDOVER | 582926 | 01810 | 0 | Solar | 05_01_225W3 | 02/06/2024 | 04/10/2024 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2024 | 04/24/2024 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 486689 | 01844 | 4999 | Other | 05_01_304W5 | 01/19/2023 | 02/03/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2023 | 03/27/2023 | 35 | 16 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176243 | 01830 | 275 | Solar | 05_01_415L2 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2015 | 06/01/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 | 08/19/2016 | 07/11/2016 | 0 | 0 | 0 | 7/11/2016 |  | 10/30/2015 | N | STD | 255 | 07/31/2017 | 02/08/2018 | 126 | 0 | 126 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 650995 | 01453 | 10 | Solar | 05_01_6J326 | 11/07/2024 | 11/25/2024 | 6 | 3 | 3 | 11/26/2024 | 11/26/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | MILLBURY | 341066 | 01527 | 10 | Solar | 05_05_19W72 | 03/04/2021 | 03/10/2021 | 4 | 1 | 3 | 03/11/2021 | 03/11/2021 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 03/04/2021 |  | Y | EXP | 365 | 06/04/2021 | 06/03/2021 | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | CHARLTON | 196392 | 01507 | 496 | Solar | 05_05_314W5 | 09/19/2018 | 10/01/2018 | 5 | 2 | 3 |  |  | 73 | 51 | 22 |  |  | 0 | 0 | 0 | 10/02/2018 | 02/26/2019 | 97 | 57 | 40 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 651801 | 01610 | 7.6 | Solar | 05_12_37W4 | 11/04/2024 | 11/27/2024 | 14 | 10 | 4 | 12/02/2024 | 12/02/2024 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/04/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | SOMERSET | 203063 | 02726 | 250 | Solar | 05_14_211L1 | 12/06/2018 | 01/02/2019 | 14 | 10 | 4 | 01/03/2019 | 01/03/2019 | 17 | 0 | 17 | 07/12/2019 | 07/11/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/11/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 |  | 6/9/2021 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  | 6/9/2021 | Connected |  | N
National Grid | WESTBOROUGH | 176499 | 01582 | 98 | Solar | 05_14_50L3 | 02/08/2016 | 02/08/2016 | 5 | 5 | 0 | 02/18/2016 | 02/18/2016 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2016 |  | 4/30/2018 | N | EXP | 794 |  |  | 0 | 0 | 0 | 3/23/2018 | 3/23/2018 | 4/29/2018 | Connected |  | N
National Grid | MEDFORD | 410011 | 02155 | 4.8 | Solar | 05_14_63L1 | 02/18/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/18/2022 | 2/7/2024 | Y | EXP | 365 | 05/24/2022 | 06/21/2022 | 29 | 0 | 29 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 519947 | 01879 | 0 | Solar | 05_14_76L1 | 04/18/2023 | 04/21/2023 | 3 | 0 | 3 | 04/24/2023 | 04/24/2023 | 211 | 192 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | ANDOVER | 676973 | 01810 | 840 | Solar | 05_01_225W3 | 04/08/2025 | 06/24/2025 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/25/2025 | 07/23/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 519333 | 01844 | 0 | Battery Add-On | 05_01_304W5 | 04/14/2023 | 04/24/2023 | 5 | 0 | 5 | 04/25/2023 | 04/25/2023 | 226 | 204 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 3/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | HAVERHILL | 176242 | 01830 | 2000 | Solar | 05_01_415L2 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2015 | 06/01/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 | 08/11/2016 | 07/11/2016 | 0 | 0 | 0 | 7/11/2016 | 04/29/2015 | 4/1/2018 | Y | STD | 629 | 07/31/2017 | 02/08/2018 | 126 | 0 | 126 | 3/15/2018 | 3/15/2018 | 3/15/2018 | Connected |  | N
National Grid | LANCASTER | 661648 | 01523 | 5.76 | Solar | 05_01_6J326 | 12/19/2024 | 01/29/2025 | 16 | 11 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | MILLBURY | 387698 | 01527 | 10 | Solar | 05_05_19W72 | 10/15/2021 | 12/29/2021 | 3 | 0 | 3 | 10/21/2021 | 10/21/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 10/15/2021 | 8/18/2023 | Y | EXP | 365 | 05/14/2022 | 07/13/2022 | 61 | 0 | 61 |  |  | 9/23/2022 | Connected |  | N
National Grid | CHARLTON | 201712 | 01507 | 7.6 | Solar | 05_05_314W5 | 11/20/2018 | 12/14/2018 | 4 | 0 | 4 | 12/17/2018 | 12/17/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2019 | 11/20/2018 | 4/14/2020 | Y | EXP | 467 | 11/13/2019 | 11/27/2019 | 14 | 0 | 14 |  |  | 1/14/2020 | Connected |  | N
National Grid | WORCESTER | 669101 | 01603 | 4.06 | Solar | 05_12_37W4 | 01/31/2025 | 02/13/2025 | 6 | 2 | 4 | 02/14/2025 | 02/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | SOMERSET | 207367 | 02726 | 72 | Solar | 05_14_211L1 | 01/28/2019 | 02/26/2019 | 7 | 2 | 5 | 02/27/2019 | 02/27/2019 | 30 | 21 | 9 | 04/22/2019 | 08/08/2019 | 77 | 9 | 68 |  |  | 0 | 0 | 0 | 08/08/2019 | 77 | 9 | 68 |  |  | 0 | 0 | 0 | 8/29/2019 | 01/28/2019 | 12/28/2021 | Y | EXP | 739 | 12/10/2021 | 12/09/2021 | 0 | 0 | 0 |  |  | 12/23/2021 | Connected |  | N
National Grid | WESTBOROUGH | 202797 | 01582 | 0 | Solar | 05_14_50L3 | 12/06/2018 | 12/18/2018 | 7 | 0 | 7 | 12/19/2018 | 12/19/2018 | 149 | 21 | 128 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 415153 | 02155 | 9.28 | Solar | 05_14_63L1 | 03/10/2022 | 03/14/2022 | 2 | 0 | 2 | 03/15/2022 | 03/15/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2022 |  | 4/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2022 | Connected |  | N
National Grid | TYNGSBORO | 621040 | 01879 | 120 | Solar | 05_14_76L1 | 06/27/2024 |  | 33 | 24 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 684731 | 01810 | 6.67 | Solar | 05_01_225W3 | 04/11/2025 | 05/02/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | METHUEN | 525794 | 01844 | 10 | Solar | 05_01_304W5 | 07/05/2023 | 07/06/2023 | 1 | 0 | 1 | 07/07/2023 | 07/07/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 07/05/2023 | 10/30/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2024 | Connected |  | N
National Grid | HAVERHILL | 176331 | 01830 | 40 | Solar | 05_01_415L2 | 07/21/2015 | 07/21/2015 | 3 | 3 | 0 | 07/27/2015 | 07/27/2015 | 388 | 0 | 388 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2015 |  | 7/27/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/7/2015 | 8/7/2015 |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 656764 | 01453 | 3.8 | Solar | 05_01_6J342 | 11/25/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | SUTTON | 484722 | 01590 | 7.6 | Solar | 05_05_19W72 | 01/03/2023 | 01/04/2023 | 1 | 0 | 1 | 01/05/2023 | 01/05/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 205806 | 01507 | 7.6 | Solar | 05_05_314W5 | 04/15/2019 | 06/12/2019 | 39 | 32 | 7 | 06/13/2019 | 06/13/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 | 04/15/2019 | 3/6/2020 | Y | EXP | 262 |  |  | 0 | 0 | 0 |  |  | 11/21/2019 | Connected |  | N
National Grid | WORCESTER | 677804 | 01603 | 5.8 | Solar | 05_12_37W4 | 03/18/2025 | 03/31/2025 | 1 | 0 | 1 | 04/14/2025 | 04/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2025 | Connected |  | N
National Grid | SOMERSET | 268890 | 02726 | 249.5 | Solar | 05_14_211L1 | 02/21/2020 | 03/27/2020 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2020 | 04/24/2020 | 19 | 4 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 311831 | 01581 | 250 | Solar | 05_14_50L3 | 09/11/2020 | 09/16/2020 | 2 | 0 | 2 | 09/17/2020 | 09/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2021 |  | 8/20/2025 | N | EXP | 720 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 465385 | 02155 | 10 | Solar | 05_14_63L1 | 10/06/2022 |  | 59 | 37 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 623525 | 01879 | 10 | Solar | 05_14_76L1 | 07/09/2024 | 07/24/2024 | 5 | 0 | 5 | 07/25/2024 | 07/25/2024 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 | 07/09/2024 | 9/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2025 | Connected |  | N
National Grid | ANDOVER | 683667 | 01810 | 10 | Solar | 05_01_225W3 | 04/08/2025 | 06/24/2025 | 25 | 24 | 1 | 08/21/2025 | 08/21/2025 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 | 04/08/2025 | 9/29/2026 | Y | EXP | 365 | 01/13/2026 |  | 79 | 0 | 79 |  |  |  | Construction |  | N
National Grid | METHUEN | 556313 | 01844 | 15 | Solar | 05_01_304W5 | 09/21/2023 | 10/02/2023 | 7 | 6 | 1 | 10/03/2023 | 10/03/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2023 |  | 11/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2024 | Connected |  | N
National Grid | HAVERHILL | 176584 | 01830 | 9.5 | Solar | 05_01_415L2 | 04/07/2016 | 04/07/2016 | 31 | 31 | 0 | 05/24/2016 | 05/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 04/07/2016 | 4/13/2017 | Y | EXP | 311 | 11/30/2016 | 12/08/2016 | 6 | 0 | 6 | 5/10/2017 | 5/10/2017 | 5/15/2017 | Connected |  | N
National Grid | LEOMINSTER | 676125 | 01453 | 5.76 | Solar | 05_01_6J342 | 03/06/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | MILLBURY | 565151 | 01527 | 13.262 | Solar | 05_05_19W72 | 11/15/2023 | 12/06/2023 | 15 | 13 | 2 | 12/07/2023 | 12/07/2023 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 | 11/15/2023 | 2/6/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | CHARLTON | 650005 | 01507 | 0 | Other | 05_05_317W1 | 05/02/2025 | 07/11/2025 | 46 | 38 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 12/18/2025 | 110 | 92 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 686001 | 01603 | 5.76 | Solar | 05_12_37W4 | 04/17/2025 | 05/21/2025 | 5 | 0 | 5 | 05/22/2025 | 05/22/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | DIGHTON | 316773 | 02715 | 7.6 | Solar | 05_14_211L1 | 11/11/2020 | 11/17/2020 | 3 | 0 | 3 | 11/18/2020 | 11/18/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/11/2020 | 3/13/2022 | Y | EXP | 365 | 05/19/2021 | 11/08/2021 | 174 | 7 | 167 |  |  | 1/11/2022 | Connected |  | N
National Grid | WESTBOROUGH | 406250 | 01581 | 10 | Solar | 05_14_50L3 | 05/04/2022 | 06/06/2022 | 22 | 19 | 3 | 06/07/2022 | 06/07/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 | 05/04/2022 | 5/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2023 | Connected |  | Y
National Grid | MEDFORD | 488617 | 02155 | 6 | Solar | 05_14_63L1 | 01/18/2023 | 01/19/2023 | 1 | 0 | 1 | 01/20/2023 | 01/20/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 | 01/18/2023 | 7/2/2024 | Y | EXP | 365 | 04/18/2023 | 06/30/2023 | 74 | 0 | 74 |  |  | 7/12/2023 | Connected |  | N
National Grid | TYNGSBORO | 650180 | 01879 | 5.76 | Solar | 05_14_76L1 | 11/07/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/07/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 725837 | 01810 | 200 | Solar | 05_01_225W3 | 11/26/2025 | 02/04/2026 | 45 | 39 | 6 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 566450 | 01844 | 10 | Solar | 05_01_304W5 | 12/08/2023 | 12/12/2023 | 2 | 0 | 2 | 12/13/2023 | 12/13/2023 | 28 | 5 | 23 | 01/31/2024 | 05/23/2024 | 80 | 55 | 25 |  |  | 0 | 0 | 0 | 05/23/2024 | 80 | 55 | 25 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 176600 | 01830 | 1000 | Solar | 05_01_415L2 | 12/29/2015 | 12/29/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/12/2016 | 5 | 0 | 5 |  | 0 | 0 | 0 | 03/29/2016 | 07/05/2016 | 66 | 17 | 49 | 7/19/2016 | 12/29/2015 | 1/4/2017 | Y | STD | 169 |  |  | 0 | 0 | 0 | 12/8/2017 | 12/8/2017 | 12/8/2017 | Connected |  | N
National Grid | LEOMINSTER | 684243 | 01453 | 77.3 | Solar | 05_01_6J356 | 04/21/2025 | 06/02/2025 | 29 | 20 | 9 | 06/03/2025 | 06/03/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MILLBURY | 590736 | 01527 | 3.8 | Solar | 05_05_19W72 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 25 | 22 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 02/22/2024 | 4/4/2025 | Y | EXP | 365 | 05/11/2024 | 05/10/2024 | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | CHARLTON | 175356 | 01507 | 1200 | Bio Gas | 05_05_317W1 | 09/05/2014 | 09/05/2014 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/19/2014 | 10/20/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2014 |  | 12/31/2016 | N | STD | 738 |  |  | 0 | 0 | 0 | 12/22/2015 | 12/22/2015 | 12/22/2015 | Connected |  | N
National Grid | WORCESTER | 708255 | 01603 | 7.6 | Solar | 05_12_37W4 | 07/29/2025 | 08/15/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 19 | 6 | 13 | 10/14/2025 | 11/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 11/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 11/20/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 343831 | 02726 | 0 | Solar | 05_14_211L1 | 03/12/2021 | 03/15/2021 | 0 | 0 | 0 | 03/16/2021 | 03/16/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 | 03/12/2021 | 9/1/2022 | Y | EXP | 365 | 08/04/2021 | 08/31/2021 | 26 | 3 | 23 |  |  | 3/14/2022 | Connected |  | N
National Grid | SOUTHBOROUGH | 484404 | 01772 | 14.5 | Solar | 05_14_50L3 | 03/06/2023 | 03/24/2023 | 14 | 12 | 2 | 03/27/2023 | 03/27/2023 | 66 | 48 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 |  | 8/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2023 | Connected |  | N
National Grid | MEDFORD | 491261 | 02155 | 10 | Solar | 05_14_63L1 | 06/01/2023 | 06/05/2023 | 3 | 2 | 1 | 06/06/2023 | 06/06/2023 | 75 | 43 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 651643 | 01879 | 7.6 | Solar | 05_14_76L1 | 11/13/2024 | 12/10/2024 | 4 | 0 | 4 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/13/2024 | 1/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | ANDOVER | 740892 | 01810 | 10 | Solar | 05_01_225W3 | 12/19/2025 | 12/23/2025 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 55 | 41 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 575814 | 01844 | 0 | Solar | 05_01_304W5 | 01/23/2024 | 03/14/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/15/2024 | 04/11/2024 | 21 | 16 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 177235 | 01830 | 54.2 | Solar | 05_01_415L2 | 11/07/2016 | 11/07/2016 | 2 | 2 | 0 | 11/10/2016 | 11/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2017 |  | 11/13/2017 | N | EXP | 307 |  |  | 0 | 0 | 0 | 5/24/2017 | 5/24/2017 | 5/24/2017 | Connected |  | N
National Grid | LEOMINSTER | 684212 | 01453 | 77.3 | Solar | 05_01_6J356 | 04/21/2025 | 06/02/2025 | 29 | 20 | 9 | 06/03/2025 | 06/03/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MILLBURY | 609919 | 01527 | 6 | Solar | 05_05_19W72 | 05/09/2024 | 06/10/2024 | 2 | 0 | 2 | 06/11/2024 | 06/11/2024 | 59 | 50 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 176480 | 01507 | 75 | Solar | 05_05_317W1 | 05/19/2016 | 05/19/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2016 |  | 5/31/2019 | N | EXP | 1029 |  |  | 0 | 0 | 0 |  |  | 7/2/2019 | Connected |  | N
National Grid | WORCESTER | 657513 | 01603 | 3.8 | Solar | 05_12_37W5 | 11/27/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 4/1/2026 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 450750 | 02726 | 11.4 | Solar | 05_14_211L1 | 12/06/2022 | 12/07/2022 | 1 | 0 | 1 | 12/08/2022 | 12/08/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  | 1/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | Y
National Grid | MARLBOROUGH | 492109 | 01752 | 9.86 | Solar | 05_14_50L3 | 01/24/2023 | 02/06/2023 | 10 | 9 | 1 | 02/07/2023 | 02/07/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2023 |  | 4/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2023 | Connected |  | N
National Grid | MEDFORD | 503150 | 02155 | 6 | Solar | 05_14_63L1 | 03/09/2023 | 03/10/2023 | 1 | 0 | 1 | 03/13/2023 | 03/13/2023 | 23 | 0 | 23 | 04/18/2023 | 05/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 05/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 5/18/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 672054 | 01879 | 10 | Solar | 05_14_76L1 | 02/14/2025 | 03/03/2025 | 2 | 0 | 2 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 752994 | 01810 | 10 | Solar | 05_01_225W3 | 02/24/2026 | 03/03/2026 | 4 | 0 | 4 | 03/19/2026 | 03/19/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 590002 | 01844 | 7.6 | Solar | 05_01_304W5 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/22/2024 | 4/22/2025 | Y | EXP | 365 | 08/08/2024 | 10/02/2024 | 56 | 0 | 56 |  |  | 10/11/2024 | Connected |  | N
National Grid | HAVERHILL | 177317 | 01830 | 1393 | Solar | 05_01_415L2 | 02/14/2017 | 03/10/2017 | 16 | 15 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2017 | 04/03/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 |  | 5/29/2020 | N | STD | 651 | 06/08/2019 | 11/21/2019 | 166 | 0 | 166 |  |  | 6/5/2020 | Connected |  | N
National Grid | LEOMINSTER | 731603 | 01453 | 17.92 | Solar | 05_01_6J356 | 11/07/2025 | 11/14/2025 | 4 | 0 | 4 | 11/17/2025 | 11/17/2025 | 63 | 48 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 643901 | 01527 | 3.8 | Solar | 05_05_19W72 | 10/01/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 176631 | 01507 | 75 | Solar | 05_05_317W1 | 10/16/2015 | 10/16/2015 | 3 | 3 | 0 | 10/23/2015 | 10/23/2015 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 691591 | 01603 | 7.6 | Solar | 05_12_37W5 | 05/14/2025 | 10/09/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 398399 | 02726 | 43.2 | Solar | 05_14_211L1 | 12/02/2021 | 12/28/2021 | 19 | 12 | 7 | 12/29/2021 | 12/29/2021 | 36 | 23 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 |  | 2/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2022 | Connected |  | Y
National Grid | MARLBOROUGH | 682703 | 01752 | 0 | Battery Add-On | 05_14_50L3 | 04/03/2025 | 05/02/2025 | 21 | 17 | 4 | 05/05/2025 | 05/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 | 04/03/2025 | 7/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | MEDFORD | 515091 | 02155 | 6 | Solar | 05_14_63L1 | 04/03/2023 | 04/05/2023 | 2 | 0 | 2 | 04/06/2023 | 04/06/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2023 | 04/03/2023 | 9/19/2024 | Y | EXP | 365 | 08/12/2023 | 09/20/2023 | 40 | 0 | 40 |  |  | 9/22/2023 | Connected |  | N
National Grid | TYNGSBORO | 690910 | 01879 | 9.88 | Solar | 05_14_76L1 | 05/09/2025 | 05/29/2025 | 2 | 0 | 2 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 05/09/2025 | 6/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | ANDOVER | 174136 | 01810 | 1000 | Solar | 05_01_225W3 | 04/06/2012 | 04/06/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 604919 | 01844 | 7.6 | Solar | 05_01_304W5 | 04/19/2024 | 05/09/2024 | 5 | 1 | 4 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 04/19/2024 | 12/31/2025 | Y | EXP | 365 | 09/10/2024 | 12/05/2024 | 87 | 0 | 87 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 177363 | 01832 | 6.67 | Solar | 05_01_415L2 | 06/23/2016 | 06/23/2016 | 7 | 7 | 0 | 07/07/2016 | 07/07/2016 | 145 | 0 | 145 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 |  | 7/2/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 741220 | 01453 | 3.8 | Solar | 05_01_6W1 | 12/18/2025 | 12/23/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 28 | 12 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILLBURY | 679843 | 01527 | 20 | Solar | 05_05_19W72 | 03/25/2025 | 03/28/2025 | 3 | 0 | 3 | 03/31/2025 | 03/31/2025 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 | 03/25/2025 | 6/8/2026 | Y | EXP | 365 | 07/01/2025 | 07/29/2025 | 29 | 0 | 29 |  |  | 8/13/2025 | Connected |  | N
National Grid | CHARLTON | 176857 | 01507 | 75 | Solar | 05_05_317W1 | 01/19/2016 | 01/19/2016 | 0 | 0 | 0 | 01/19/2016 | 01/19/2016 | 166 | 0 | 166 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/24/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 711000 | 01603 | 7.6 | Solar | 05_12_37W5 | 08/11/2025 | 10/03/2025 | 3 | 0 | 3 | 11/12/2025 | 11/12/2025 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 | 08/11/2025 | 1/14/2027 | Y | EXP | 365 | 03/12/2026 |  | 21 | 0 | 21 |  |  |  | Construction |  | N
National Grid | DIGHTON | 555818 | 02715 | 6 | Solar | 05_14_211L1 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 102 | 25 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 699800 | 01752 | 9.69 | Solar | 05_14_50L3 | 06/19/2025 | 07/02/2025 | 1 | 0 | 1 | 07/29/2025 | 07/29/2025 | 17 | 6 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 9/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | MEDFORD | 516114 | 02155 | 7.6 | Solar | 05_14_63L1 | 05/30/2023 | 06/02/2023 | 3 | 1 | 2 | 06/05/2023 | 06/05/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | N
National Grid | TYNGSBORO | 554496 | 01879 | 480 | Solar | 05_14_76L3 | 10/06/2023 | 10/23/2023 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2023 | 09/25/2024 | 232 | 216 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 | 10/06/2023 | 11/8/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ANDOVER | 174125 | 01810 | 3000 | Solar | 05_01_225W3 | 04/06/2012 | 04/06/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/23/2012 | 06/22/2012 | 42 | 0 | 42 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2013 | 04/06/2012 | 12/1/2012 | Y | STD | 34 | 10/22/2013 | 02/22/2014 | 83 | 0 | 83 | 11/29/2013 | 11/29/2013 | 11/30/2013 | Connected |  | N
National Grid | LAWRENCE | 608984 | 01841 | 2.61 | Solar | 05_01_304W5 | 05/16/2024 | 06/14/2024 | 21 | 20 | 1 | 06/17/2024 | 06/17/2024 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 |  | 8/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 177552 | 01830 | 3500 | Solar | 05_01_415L2 | 05/15/2017 | 06/12/2017 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2017 | 07/14/2017 | 23 | 6 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2018 | 05/15/2017 | 12/20/2022 | Y | STD | 586 |  |  | 0 | 0 | 0 |  |  | 12/19/2022 | Connected |  | N
National Grid | LANCASTER | 174950 | 01523 | 1000 | Solar | 05_01_6W1 | 11/18/2011 | 11/18/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2012 | 03/12/2012 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/3/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 680454 | 01527 | 17.16 | Solar | 05_05_19W72 | 03/25/2025 | 03/28/2025 | 3 | 0 | 3 | 03/31/2025 | 03/31/2025 | 24 | 1 | 23 | 05/07/2025 | 05/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 05/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 5/19/2025 |  | 7/10/2026 | N | EXP | 365 | 08/21/2025 | 09/03/2025 | 14 | 0 | 14 |  |  | 9/12/2025 | Connected |  | N
National Grid | CHARLTON | 177517 | 01507 | 75 | Solar | 05_05_317W1 | 06/23/2016 | 06/23/2016 | 5 | 0 | 5 | 06/30/2016 | 06/30/2016 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 720644 | 01603 | 8 | Solar | 05_12_37W5 | 10/17/2025 | 01/16/2026 | 3 | 0 | 3 | 01/20/2026 | 01/20/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2026 |  | 3/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DIGHTON | 583467 | 02715 | 10 | Solar | 05_14_211L1 | 01/15/2024 | 03/07/2024 | 37 | 28 | 9 | 03/08/2024 | 03/08/2024 | 6 | 3 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2024 | Connected |  | N
National Grid | MARLBOROUGH | 586777 | 01752 | 7.6 | Solar | 05_14_53J1 | 02/26/2024 | 05/08/2024 | 51 | 48 | 3 | 05/09/2024 | 05/09/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 |  | 5/30/2025 | N | EXP | 720 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MEDFORD | 521435 | 02155 | 10.368 | Solar | 05_14_63L1 | 05/10/2023 | 05/25/2023 | 11 | 8 | 3 | 05/26/2023 | 05/26/2023 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 670636 | 01879 | 11.5 | Solar | 05_14_76L3 | 02/14/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 64 | 45 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ANDOVER | 174908 | 01810 | 499 | Solar | 05_01_225W3 | 09/14/2012 | 09/14/2012 | 22 | 21 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 630164 | 01844 | 32.88 | Solar | 05_01_304W5 | 08/05/2024 | 08/07/2024 | 3 | 1 | 2 | 08/08/2024 | 08/08/2024 | 91 | 74 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | HAVERHILL | 177818 | 01830 | 13.76 | Solar | 05_01_415L2 | 04/04/2017 | 04/04/2017 | 218 | 216 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/10/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 174949 | 01523 | 2000 | Solar | 05_01_6W1 | 11/18/2011 | 11/18/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2012 | 03/12/2012 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/3/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 694616 | 01527 | 5.76 | Solar | 05_05_19W72 | 05/29/2025 | 06/18/2025 | 3 | 0 | 3 | 06/20/2025 | 06/20/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 178234 | 01507 | 1200 | Landfill Gas | 05_05_317W1 | 01/08/2018 | 01/08/2018 | 36 | 3 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/01/2018 | 04/13/2018 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/13/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 722271 | 01524 | 10 | Solar | 05_12_37W5 | 09/26/2025 | 10/03/2025 | 4 | 0 | 4 | 11/20/2025 | 11/20/2025 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 | 09/26/2025 | 1/7/2027 | Y | EXP | 365 | 03/19/2026 |  | 14 | 0 | 14 |  |  |  | Construction |  | N
National Grid | SOMERSET | 590700 | 02726 | 7.6 | Solar | 05_14_211L1 | 03/04/2024 | 03/11/2024 | 5 | 1 | 4 | 03/12/2024 | 03/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2024 | Connected |  | N
National Grid | MARLBOROUGH | 642635 | 01752 | 10 | Solar | 05_14_53J1 | 09/24/2024 |  | 19 | 16 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 525627 | 02155 | 6 | Solar | 05_14_63L1 | 06/01/2023 | 06/05/2023 | 2 | 1 | 1 | 06/06/2023 | 06/06/2023 | 57 | 38 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 | 06/01/2023 | 10/3/2024 | Y | EXP | 365 | 12/09/2023 | 12/30/2023 | 22 | 3 | 19 |  |  | 1/18/2024 | Connected |  | N
National Grid | TYNGSBORO | 686382 | 01879 | 34.675 | Solar | 05_14_76L3 | 04/21/2025 | 05/13/2025 | 15 | 11 | 4 | 05/14/2025 | 05/14/2025 | 53 | 34 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 175018 | 01840 | 500 | Solar | 05_01_225W3 | 10/08/2012 | 10/08/2012 | 7 | 0 | 7 | 10/18/2012 | 10/18/2012 | 286 | 223 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 641209 | 01841 | 7.6 | Solar | 05_01_304W5 | 09/18/2024 | 10/08/2024 | 5 | 0 | 5 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/18/2024 | 1/13/2026 | Y | EXP | 365 | 04/15/2025 | 08/15/2025 | 123 | 0 | 123 |  |  | 9/30/2025 | Connected |  | N
National Grid | HAVERHILL | 177922 | 01830 | 4980 | Solar | 05_01_415L2 | 10/24/2017 | 10/24/2017 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 | 12/08/2017 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 176281 | 01453 | 16.32 | Solar | 05_01_6W1 | 05/06/2015 | 05/06/2015 | 3 | 3 | 0 | 05/13/2015 | 05/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 |  | 10/30/2015 | N | EXP | 169 |  |  | 0 | 0 | 0 | 5/9/2016 | 5/9/2016 | 5/12/2016 | Connected |  | N
National Grid | MILLBURY | 704382 | 01527 | 10 | Solar | 05_05_19W72 | 07/11/2025 | 07/28/2025 | 4 | 0 | 4 | 09/03/2025 | 09/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | CHARLTON | 178387 | 01507 | 10 | Solar | 05_05_317W1 | 01/16/2018 | 01/16/2018 | 16 | 0 | 16 | 02/08/2018 | 02/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 |  | 1/22/2019 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  | 6/1/2018 | Connected |  | N
National Grid | LEICESTER | 733641 | 01524 | 5.76 | Solar | 05_12_37W5 | 11/13/2025 | 11/19/2025 | 4 | 0 | 4 | 12/09/2025 | 12/09/2025 | 78 | 68 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOMERSET | 633351 | 02726 | 7.6 | Solar | 05_14_211L1 | 08/19/2024 | 08/22/2024 | 4 | 0 | 4 | 09/24/2024 | 09/24/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 | 08/19/2024 | 11/15/2025 | Y | EXP | 365 | 12/19/2024 | 02/24/2025 | 68 | 0 | 68 |  |  | 2/28/2025 | Connected |  | N
National Grid | MARLBOROUGH | 699429 | 01752 | 10 | Solar | 05_14_53J1 | 06/18/2025 | 07/03/2025 | 19 | 15 | 4 | 08/12/2025 | 08/12/2025 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | MEDFORD | 525411 | 02155 | 6 | Solar | 05_14_63L1 | 06/12/2023 | 08/06/2023 | 38 | 33 | 5 | 08/07/2023 | 08/07/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 | 06/12/2023 | 9/23/2024 | Y | EXP | 365 | 01/24/2024 | 02/09/2024 | 17 | 0 | 17 |  |  | 2/21/2024 | Connected |  | N
National Grid | TYNGSBORO | 176961 | 01879 | 0 | Solar | 05_14_76L3 | 07/18/2016 | 07/18/2016 | 2 | 2 | 0 | 07/20/2016 | 07/20/2016 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/23/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 176193 | 01841 | 260 | Solar | 05_01_225W3 | 02/09/2015 | 02/09/2015 | 4 | 0 | 4 | 02/17/2015 | 02/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 |  | 7/31/2015 | N | EXP | 156 |  |  | 0 | 0 | 0 | 10/7/2015 | 10/7/2015 | 10/7/2015 | Connected |  | N
National Grid | METHUEN | 643175 | 01844 | 0 | Other | 05_01_304W5 | 12/10/2024 | 01/31/2025 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/03/2025 | 03/10/2025 | 26 | 6 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 178290 | 01835 | 1000 | Solar | 05_01_415L2 | 03/28/2018 | 03/28/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 05/10/2018 | 28 | 6 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/3/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 176484 | 01453 | 7.6 | Solar | 05_01_6W1 | 05/23/2016 | 05/23/2016 | 1 | 1 | 0 | 05/26/2016 | 05/26/2016 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2016 |  | 5/30/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 721805 | 01527 | 17.1 | Solar | 05_05_19W72 | 09/25/2025 | 09/29/2025 | 2 | 0 | 2 | 09/30/2025 | 09/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2025 | Connected |  | N
National Grid | CHARLTON | 193382 | 01507 | 3.8 | Solar | 05_05_317W1 | 08/14/2018 | 08/31/2018 | 2 | 2 | 0 | 09/04/2018 | 09/04/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 734653 | 01501 | 3.8 | Solar | 05_12_37W5 | 11/18/2025 | 11/19/2025 | 26 | 23 | 3 | 02/11/2026 | 02/11/2026 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOMERSET | 635683 | 02726 | 150 | Solar | 05_14_211L1 | 09/11/2024 | 10/04/2024 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2024 | 06/04/2025 | 162 | 75 | 87 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 662479 | 01772 | 7.6 | Solar | 05_14_53J2 | 12/24/2024 | 03/04/2025 | 0 | 0 | 0 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MEDFORD | 546709 | 02155 | 10 | Solar | 05_14_63L1 | 08/30/2023 |  | 70 | 54 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 177296 | 01879 | 60 | Solar | 05_14_76L3 | 08/26/2016 | 08/26/2016 | 0 | 0 | 0 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2016 |  | 9/3/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/27/2017 | 3/27/2017 | 3/27/2017 | Connected |  | N
National Grid | LAWRENCE | 176674 | 01841 | 100 | Solar | 05_01_225W3 | 01/04/2016 | 01/04/2016 | 0 | 0 | 0 | 01/05/2016 | 01/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2016 |  | 1/10/2017 | N | EXP | 354 |  |  | 0 | 0 | 0 | 1/6/2017 | 1/6/2017 | 1/4/2017 | Connected |  | N
National Grid | METHUEN | 645815 | 01844 | 6.72 | Solar | 05_01_304W5 | 10/09/2024 | 10/17/2024 | 2 | 0 | 2 | 10/18/2024 | 10/18/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 | 10/09/2024 | 4/16/2026 | Y | EXP | 365 | 03/06/2025 |  | 392 | 0 | 392 |  |  | 6/10/2025 | Connected |  | N
National Grid | HAVERHILL | 188710 | 01830 | 250 | Solar | 05_01_415L2 | 06/20/2018 | 06/20/2018 | 4 | 0 | 4 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 300516 | 01453 | 8.64 | Solar | 05_01_6W1 | 07/09/2020 | 07/10/2020 | 0 | 0 | 0 | 07/13/2020 | 07/13/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 8/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/8/2020 | Connected |  | N
National Grid | SUTTON | 557478 | 01590 | 2512 | Solar | 05_05_19W73 | 12/07/2023 | 01/18/2024 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2024 | 05/24/2024 | 89 | 70 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | CHARLTON | 421420 | 01507 | 0 | Solar | 05_05_317W1 | 12/07/2022 | 12/19/2022 | 8 | 7 | 1 | 12/20/2022 | 12/20/2022 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  | 3/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2023 | Connected |  | N
National Grid | WORCESTER | 206779 | 01603 | 7.6 | Solar | 05_12_37W5 | 02/11/2019 | 02/14/2019 | 3 | 3 | 0 | 02/15/2019 | 02/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/11/2019 | 5/28/2020 | Y | EXP | 365 | 03/25/2020 | 04/07/2020 | 13 | 0 | 13 |  |  | 5/14/2020 | Connected |  | N
National Grid | SOMERSET | 666071 | 02726 | 0 | Battery Add-On | 05_14_211L1 | 01/15/2025 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 710450 | 01581 | 10 | Solar | 05_14_53J2 | 08/07/2025 | 09/17/2025 | 4 | 0 | 4 | 09/26/2025 | 09/26/2025 | 19 | 2 | 17 | 10/30/2025 | 11/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 11/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 11/20/2025 |  | 12/1/2026 | N | EXP | 365 | 03/11/2026 |  | 22 | 0 | 22 |  |  |  | Construction |  | N
National Grid | MEDFORD | 554723 | 02155 | 7.6 | Solar | 05_14_63L1 | 09/27/2023 | 09/28/2023 | 1 | 0 | 1 | 09/29/2023 | 09/29/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 09/27/2023 | 12/5/2024 | Y | EXP | 365 | 01/24/2024 | 02/09/2024 | 17 | 0 | 17 |  |  | 3/5/2024 | Connected |  | N
National Grid | TYNGSBORO | 177403 | 01879 | 10 | Solar | 05_14_76L3 | 06/30/2016 | 06/30/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/5/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176871 | 01841 | 6 | Solar | 05_01_225W3 | 03/01/2016 | 03/01/2016 | 2 | 2 | 0 | 03/04/2016 | 03/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2016 | 03/01/2016 | 3/7/2017 | Y | EXP | 319 | 07/07/2016 | 07/27/2016 | 14 | 0 | 14 | 1/19/2017 | 1/19/2017 | 1/19/2017 | Connected |  | N
National Grid | METHUEN | 648088 | 01844 | 15.2 | Solar | 05_01_304W5 | 10/21/2024 | 10/23/2024 | 2 | 1 | 1 | 10/24/2024 | 10/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | HAVERHILL | 195208 | 01830 | 6930 | Solar | 05_01_415L2 | 10/01/2018 | 10/22/2018 | 15 | 15 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 | 12/04/2018 | 28 | 9 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 321984 | 01453 | 250 | Solar | 05_01_6W1 | 07/21/2021 | 08/04/2021 | 10 | 0 | 10 | 08/05/2021 | 08/05/2021 | 44 | 19 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2021 | 07/21/2021 | 2/2/2023 | Y | EXP | 304 |  |  | 0 | 0 | 0 |  |  | 12/8/2022 | Connected |  | N
National Grid | MILLBURY | 733709 | 01527 | 3.8 | Solar | 05_05_19W73 | 11/13/2025 | 12/23/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 1/28/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 610366 | 01507 | 10.15 | Solar | 05_05_317W1 | 05/20/2024 | 06/24/2024 | 5 | 2 | 3 | 06/25/2024 | 06/25/2024 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  | 10/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2024 | Connected |  | N
National Grid | AUBURN | 235994 | 01501 | 7.6 | Solar | 05_12_37W5 | 06/21/2019 | 06/28/2019 | 4 | 0 | 4 | 07/01/2019 | 07/01/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 06/21/2019 | 6/21/2020 | Y | EXP | 365 | 03/06/2020 | 03/09/2020 | 3 | 0 | 3 |  |  | 5/1/2020 | Connected |  | N
National Grid | SWANSEA | 706405 | 02777 | 0 | Solar | 05_14_211L1 | 07/22/2025 | 07/24/2025 | 2 | 0 | 2 | 07/25/2025 | 07/25/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 723314 | 01772 | 12.76 | Solar | 05_14_53J2 | 10/01/2025 | 10/17/2025 | 1 | 0 | 1 | 10/30/2025 | 10/30/2025 | 26 | 9 | 17 | 12/12/2025 | 12/17/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 12/17/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | MEDFORD | 570739 | 02155 | 9.28 | Solar | 05_14_63L1 | 11/22/2023 | 11/29/2023 | 5 | 2 | 3 | 11/30/2023 | 11/30/2023 | 30 | 7 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 11/22/2023 | 1/21/2025 | Y | EXP | 365 | 05/14/2024 | 06/07/2024 | 25 | 0 | 25 |  |  | 6/14/2024 | Connected |  | N
National Grid | TYNGSBORO | 177899 | 01879 | 8.4 | Solar | 05_14_76L3 | 06/15/2017 | 06/15/2017 | 107 | 107 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/21/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 178266 | 01841 | 990 | Solar | 05_01_225W3 | 01/08/2018 | 01/08/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2018 | 03/19/2018 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2018 | 01/08/2018 | 8/17/2020 | Y | STD | 399 | 01/17/2020 | 06/04/2020 | 139 | 0 | 139 | 6/18/2020 | 6/22/2020 | 8/10/2020 | Connected |  | N
National Grid | METHUEN | 654542 | 01844 | 7.6 | Solar | 05_01_304W5 | 11/18/2024 | 01/06/2025 | 17 | 12 | 5 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | HAVERHILL | 202001 | 01830 | 0 | Solar | 05_01_415L2 | 01/15/2019 | 02/25/2019 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/26/2019 | 06/27/2019 | 87 | 72 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 373959 | 01453 | 3.8 | Solar | 05_01_6W1 | 08/09/2021 | 08/12/2021 | 3 | 0 | 3 | 08/13/2021 | 08/13/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2021 |  | 10/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 738982 | 01527 | 10 | Solar | 05_05_19W73 | 12/09/2025 | 12/11/2025 | 1 | 0 | 1 | 12/12/2025 | 12/12/2025 | 75 | 3 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 660358 | 01507 | 16.8 | Solar | 05_05_317W1 | 01/22/2025 | 01/27/2025 | 3 | 0 | 3 | 01/28/2025 | 01/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 01/22/2025 | 3/14/2026 | Y | EXP | 365 | 12/05/2025 | 12/04/2025 | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | WORCESTER | 456275 | 01603 | 10 | Solar | 05_12_37W5 | 09/16/2022 | 10/14/2022 | 19 | 19 | 0 | 10/17/2022 | 10/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 |  | 2/13/2024 | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 564846 | 02715 | 200 | Solar | 05_14_211L2 | 10/24/2023 | 11/07/2023 | 10 | 0 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 | 10/24/2023 | 3/14/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WESTBOROUGH | 177566 | 01581 | 15.2 | Solar | 05_14_53J2 | 09/14/2017 | 09/14/2017 | 9 | 9 | 0 | 09/27/2017 | 09/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/19/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 | 1/9/2018 | 1/9/2018 | 1/9/2018 | Connected |  | N
National Grid | MEDFORD | 572865 | 02155 | 3.8 | Solar | 05_14_63L1 | 11/29/2023 | 12/05/2023 | 4 | 0 | 4 | 12/06/2023 | 12/06/2023 | 46 | 23 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | TYNGSBORO | 178408 | 01879 | 10 | Solar | 05_14_76L3 | 11/22/2017 | 11/22/2017 | 52 | 51 | 1 | 02/12/2018 | 02/12/2018 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2018 | 11/22/2017 | 12/2/2018 | Y | EXP | 293 | 06/19/2018 | 07/17/2018 | 28 | 0 | 28 |  |  | 8/23/2018 | Connected |  | N
National Grid | LAWRENCE | 197643 | 01841 | 10 | Solar | 05_01_225W3 | 11/13/2018 | 04/22/2019 | 108 | 103 | 5 | 04/23/2019 | 04/23/2019 | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 661844 | 01844 | 5.76 | Solar | 05_01_304W5 | 12/19/2024 | 02/24/2025 | 22 | 17 | 5 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 244622 | 01830 | 10 | Solar | 05_01_415L2 | 07/22/2019 | 07/23/2019 | 0 | 0 | 0 | 07/24/2019 | 07/24/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 9/30/2019 | N | EXP | 56 |  |  | 0 | 0 | 0 |  |  | 9/26/2019 | Connected |  | N
National Grid | LANCASTER | 595595 | 01523 | 5.76 | Solar | 05_01_6W1 | 03/28/2024 | 04/01/2024 | 2 | 0 | 2 | 04/02/2024 | 04/02/2024 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 5/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 742528 | 01527 | 3.8 | Solar | 05_05_19W73 | 12/30/2025 | 01/05/2026 | 3 | 0 | 3 | 01/06/2026 | 01/06/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHARLTON | 174312 | 01507 | 333 | Solar | 05_05_317W2 | 12/21/2011 | 12/21/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 03/26/2012 | 03/26/2012 | 0 | 0 | 0 | 4/2/2012 |  | 6/8/2012 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/12/2012 | 9/12/2012 | 9/17/2012 | Connected |  | N
National Grid | WORCESTER | 463128 | 01603 | 15 | Solar | 05_12_37W5 | 10/05/2022 | 10/13/2022 | 5 | 3 | 2 | 10/14/2022 | 10/14/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 |  | 1/8/2024 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 174740 | 02777 | 5500 | Solar | 05_14_211L2 | 01/15/2013 | 01/15/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2013 | 04/04/2013 | 40 | 0 | 40 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 521243 | 01772 | 10 | Solar | 05_14_53J2 | 05/25/2023 | 05/26/2023 | 1 | 0 | 1 | 05/30/2023 | 05/30/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 579133 | 02155 | 9.57 | Solar | 05_14_63L1 | 12/21/2023 | 12/22/2023 | 1 | 0 | 1 | 12/26/2023 | 12/26/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 199477 | 01879 | 7.6 | Solar | 05_14_76L3 | 11/05/2018 | 11/14/2018 | 5 | 0 | 5 | 11/15/2018 | 11/15/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 204026 | 01841 | 500 | Solar | 05_01_225W3 | 01/16/2019 | 02/07/2019 | 15 | 7 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2019 | 02/27/2019 | 12 | 5 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 679629 | 01844 | 3.8 | Solar | 05_01_304W5 | 03/21/2025 | 06/18/2025 | 4 | 0 | 4 | 07/28/2025 | 07/28/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 327784 | 01830 | 9.8 | Solar | 05_01_415L2 | 12/28/2020 | 12/31/2020 | 2 | 0 | 2 | 01/04/2021 | 01/04/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 2/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 605951 | 01453 | 3.8 | Solar | 05_01_6W1 | 04/23/2024 | 05/01/2024 | 4 | 0 | 4 | 05/02/2024 | 05/02/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 750543 | 01590 | 7.6 | Solar | 05_05_19W73 | 02/11/2026 | 02/13/2026 | 2 | 0 | 2 | 02/17/2026 | 02/17/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 175038 | 01507 | 100 | Solar | 05_05_317W2 | 09/22/2013 | 09/22/2013 | 7 | 0 | 7 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2013 |  | 12/31/2013 | N | EXP | 60 |  |  | 0 | 0 | 0 | 11/8/2013 | 11/8/2013 | 1/8/2014 | Connected |  | N
National Grid | WORCESTER | 499173 | 01603 | 15.2 | Solar | 05_12_37W5 | 03/15/2023 | 03/16/2023 | 1 | 0 | 1 | 03/17/2023 | 03/17/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 | 03/15/2023 | 9/1/2024 | Y | EXP | 365 | 07/28/2023 | 08/28/2023 | 32 | 0 | 32 |  |  | 9/20/2023 | Connected |  | N
National Grid | DIGHTON | 177013 | 02715 | 7.6 | Solar | 05_14_211L2 | 01/05/2017 | 01/05/2017 | 8 | 8 | 0 | 01/18/2017 | 01/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2017 |  | 1/10/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 | 8/3/2017 | 8/3/2017 | 8/2/2017 | Connected |  | N
National Grid | MARLBOROUGH | 538670 | 01752 | 12.76 | Solar | 05_14_53J2 | 09/05/2023 | 02/07/2024 | 105 | 95 | 10 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 | 02/27/2024 | 04/16/2024 | 35 | 0 | 35 |  |  | 0 | 0 | 0 | 04/16/2024 | 35 | 0 | 35 |  |  | 0 | 0 | 0 | 4/20/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 580779 | 02155 | 5.8 | Solar | 05_14_63L1 | 02/08/2024 | 02/21/2024 | 9 | 5 | 4 | 02/22/2024 | 02/22/2024 | 9 | 6 | 3 | 03/29/2024 | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 4/25/2025 | N | EXP | 365 | 06/06/2024 | 02/12/2025 | 126 | 0 | 126 |  |  | 10/29/2024 | Connected |  | N
National Grid | TYNGSBORO | 368286 | 01879 | 15.2 | Solar | 05_14_76L3 | 07/07/2021 | 08/18/2021 | 31 | 30 | 1 | 08/19/2021 | 08/19/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 10/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2021 | Connected |  | N
National Grid | LAWRENCE | 233067 | 01841 | 7.6 | Solar | 05_01_225W3 | 07/05/2019 | 07/08/2019 | 0 | 0 | 0 | 07/09/2019 | 07/09/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 07/05/2019 | 5/28/2020 | Y | EXP | 365 | 12/17/2019 | 01/24/2020 | 38 | 0 | 38 |  |  | 2/14/2020 | Connected |  | N
National Grid | METHUEN | 688408 | 01844 | 10 | Solar | 05_01_304W5 | 04/29/2025 | 05/06/2025 | 5 | 2 | 3 | 05/07/2025 | 05/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2026 | Connected |  | N
National Grid | HAVERHILL | 349183 | 01830 | 7.6 | Solar | 05_01_415L2 | 05/04/2021 | 05/07/2021 | 2 | 0 | 2 | 05/10/2021 | 05/10/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  | 10/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2022 | Connected |  | Y
National Grid | LEOMINSTER | 647056 | 01453 | 10 | Solar | 05_01_6W1 | 10/23/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/23/2024 | 4/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N
National Grid | MILLBURY | 749683 | 01527 | 23 | Solar | 05_05_19W73 | 02/06/2026 | 02/09/2026 | 1 | 0 | 1 | 02/10/2026 | 02/10/2026 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2026 |  | 3/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 189707 | 01507 | 472.5 | Natural Gas | 05_05_317W2 | 07/03/2018 | 07/03/2018 | 33 | 24 | 9 |  |  | 24 | 0 | 24 | 10/19/2018 | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 10/30/2019 |  | 12/31/2019 | N | STD | 41 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N
National Grid | WORCESTER | 506789 | 01603 | 5.04 | Solar | 05_12_37W5 | 05/09/2023 | 05/11/2023 | 2 | 0 | 2 | 05/12/2023 | 05/12/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2023 | Connected |  | N
National Grid | SWANSEA | 177845 | 02777 | 910 | Solar | 05_14_211L2 | 10/17/2017 | 10/17/2017 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/14/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 600641 | 01752 | 7.6 | Solar | 05_14_53J2 | 04/12/2024 | 05/30/2024 | 1 | 0 | 1 | 05/31/2024 | 05/31/2024 | 31 | 19 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 04/12/2024 | 10/4/2025 | Y | EXP | 365 | 08/22/2024 | 09/11/2024 | 21 | 0 | 21 |  |  | 12/6/2024 | Connected |  | N
National Grid | MEDFORD | 580403 | 02155 | 10 | Solar | 05_14_63L1 | 01/12/2024 | 03/04/2024 | 27 | 25 | 2 | 03/05/2024 | 03/05/2024 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 | 01/12/2024 | 4/4/2025 | Y | EXP | 365 | 06/06/2024 | 09/11/2024 | 98 | 0 | 98 |  |  | 10/7/2024 | Connected |  | N
National Grid | TYNGSBORO | 465137 | 01879 | 3.8 | Solar | 05_14_76L3 | 10/07/2022 | 10/11/2022 | 1 | 0 | 1 | 10/12/2022 | 10/12/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2022 | 10/07/2022 | 4/30/2024 | Y | EXP | 365 | 04/11/2023 | 04/28/2023 | 18 | 0 | 18 |  |  | 6/6/2023 | Connected |  | N
National Grid | LAWRENCE | 231390 | 01841 | 10 | Solar | 05_01_225W3 | 05/28/2019 | 06/27/2019 | 22 | 17 | 5 | 06/28/2019 | 06/28/2019 | 23 | 14 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 8/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N
National Grid | METHUEN | 702694 | 01844 | 17.101 | Solar | 05_01_304W5 | 07/08/2025 | 07/14/2025 | 4 | 0 | 4 | 07/15/2025 | 07/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | HAVERHILL | 356489 | 01830 | 21.36 | Solar | 05_01_415L2 | 05/05/2021 | 05/12/2021 | 4 | 2 | 2 | 05/13/2021 | 05/13/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2021 |  | 1/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2022 | Connected |  | N
National Grid | LEOMINSTER | 648471 | 01453 | 10 | Solar | 05_01_6W1 | 12/23/2024 | 01/21/2025 | 19 | 15 | 4 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | SUTTON | 170590 | 01590 | 15.4 | Solar | 05_05_19W73 | 06/07/2018 | 06/07/2018 | 8 | 8 | 0 | 06/26/2018 | 06/26/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 | 06/07/2018 | 12/24/2019 | Y | EXP | 550 | 07/06/2019 | 08/01/2019 | 26 | 0 | 26 |  |  | 12/11/2019 | Connected |  | N
National Grid | CHARLTON | 549586 | 01507 | 200 | Solar | 05_05_317W2 | 09/25/2023 | 03/07/2024 | 111 | 102 | 9 | 03/08/2024 | 03/08/2024 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 |  | 5/27/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | AUBURN | 522539 | 01501 | 15.2 | Solar | 05_12_37W5 | 04/28/2023 | 06/07/2023 | 27 | 26 | 1 | 06/08/2023 | 06/08/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 |  | 8/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2023 | Connected |  | N
National Grid | SWANSEA | 187599 | 02777 | 240 | Solar | 05_14_211L2 | 06/08/2018 | 06/12/2018 | 3 | 0 | 3 | 06/22/2018 | 06/22/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 |  | 7/10/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2019 | Connected |  | N
National Grid | MARLBOROUGH | 623222 | 01752 | 3.8 | Solar | 05_14_53J2 | 07/08/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 07/08/2024 | 8/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | MEDFORD | 590846 | 02155 | 5 | Solar | 05_14_63L1 | 03/07/2024 | 03/12/2024 | 3 | 0 | 3 | 03/13/2024 | 03/13/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 03/07/2024 | 8/29/2025 | Y | EXP | 365 | 10/03/2024 | 03/07/2025 | 156 | 0 | 156 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 478125 | 01879 | 15.2 | Solar | 05_14_76L3 | 12/01/2022 | 12/07/2022 | 4 | 2 | 2 | 12/08/2022 | 12/08/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | LAWRENCE | 246795 | 01841 | 10 | Solar | 05_01_225W3 | 11/20/2019 | 03/12/2020 | 76 | 76 | 0 | 03/13/2020 | 03/13/2020 | 68 | 46 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2020 |  | 11/20/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 713450 | 01844 | 11.4 | Solar | 05_01_304W5 | 08/20/2025 | 09/04/2025 | 10 | 8 | 2 | 09/05/2025 | 09/05/2025 | 53 | 37 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  | 12/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | HAVERHILL | 396888 | 01830 | 7.68 | Solar | 05_01_415L2 | 01/24/2022 | 01/25/2022 | 1 | 0 | 1 | 01/26/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2022 | 01/24/2022 | 7/27/2023 | Y | EXP | 365 | 06/30/2022 | 07/26/2022 | 27 | 0 | 27 |  |  | 9/7/2022 | Connected |  | N
National Grid | LEOMINSTER | 650193 | 01453 | 5.76 | Solar | 05_01_6W1 | 11/07/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 | 11/07/2024 | 3/1/2026 | Y | EXP | 365 | 04/15/2025 | 08/08/2025 | 116 | 0 | 116 |  |  | 10/9/2025 | Connected |  | N
National Grid | SUTTON | 170569 | 01590 | 15.4 | Solar | 05_05_19W73 | 07/17/2018 | 08/13/2018 | 19 | 7 | 12 | 08/14/2018 | 08/14/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 |  | 12/24/2019 | N | EXP | 550 |  |  | 0 | 0 | 0 |  |  | 12/11/2019 | Connected |  | N
National Grid | CHARLTON | 625569 | 01507 | 499 | Solar | 05_05_317W2 | 09/25/2024 |  | 73 | 66 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 563912 | 01603 | 7.6 | Solar | 05_12_37W5 | 11/07/2023 | 11/09/2023 | 2 | 0 | 2 | 11/13/2023 | 11/13/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2023 | 11/07/2023 | 1/8/2025 | Y | EXP | 365 | 05/10/2024 | 05/14/2024 | 5 | 0 | 5 |  |  | 5/31/2024 | Connected |  | N
National Grid | DIGHTON | 190345 | 02715 | 7.6 | Solar | 05_14_211L2 | 07/10/2018 | 07/13/2018 | 2 | 0 | 2 | 07/13/2018 | 07/13/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 637397 | 01752 | 5.76 | Solar | 05_14_53J2 | 09/03/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 | 09/03/2024 | 11/1/2025 | Y | EXP | 365 | 05/07/2025 | 05/20/2025 | 14 | 0 | 14 |  |  | 6/13/2025 | Connected |  | N
National Grid | MEDFORD | 600702 | 02155 | 5 | Solar | 05_14_63L1 | 07/02/2024 | 07/09/2024 | 4 | 0 | 4 | 07/10/2024 | 07/10/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2024 | Connected |  | N
National Grid | TYNGSBORO | 491622 | 01879 | 6 | Solar | 05_14_76L3 | 01/23/2023 | 01/25/2023 | 2 | 0 | 2 | 01/26/2023 | 01/26/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 | 01/23/2023 | 9/4/2024 | Y | EXP | 365 | 07/01/2023 | 09/05/2023 | 67 | 0 | 67 |  |  | 9/18/2023 | Connected |  | Y
National Grid | LAWRENCE | 272614 | 01841 | 499.9 | Solar | 05_01_225W3 | 02/20/2020 | 02/27/2020 | 5 | 2 | 3 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2020 | 02/20/2020 | 4/1/2024 | Y | STD | 1112 | 01/26/2024 | 04/22/2024 | 88 | 36 | 52 |  |  | 3/25/2024 | Connected |  | N
National Grid | LAWRENCE | 654741 | 01841 | 240 | Solar | 05_01_304W6 | 11/15/2024 | 02/10/2025 | 56 | 46 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | HAVERHILL | 398624 | 01830 | 19 | Solar | 05_01_415L2 | 12/09/2021 | 12/14/2021 | 3 | 0 | 3 | 12/15/2021 | 12/15/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2022 |  | 2/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2022 | Connected |  | N
National Grid | LEOMINSTER | 650851 | 01453 | 6.175 | Solar | 05_01_6W1 | 10/30/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/30/2024 | 4/4/2026 | Y | EXP | 365 | 01/23/2025 | 08/08/2025 | 198 | 0 | 198 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 174564 | 01527 | 500 | Solar | 05_05_19W73 | 08/08/2011 | 08/08/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2012 | 08/08/2011 | 10/31/2012 | Y | STD | 229 | 08/27/2012 | 01/18/2013 | 83 | 0 | 83 | 12/5/2012 | 12/5/2012 | 12/10/2012 | Connected |  | N
National Grid | CHARLTON | 650004 | 01507 | 0 | Other | 05_05_317W3 | 05/02/2025 | 07/11/2025 | 46 | 38 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 12/18/2025 | 109 | 92 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | AUBURN | 575277 | 01501 | 25 | Solar | 05_12_37W5 | 01/08/2024 | 01/22/2024 | 9 | 6 | 3 | 01/23/2024 | 01/23/2024 | 106 | 88 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2024 | Connected |  | N
National Grid | DIGHTON | 193772 | 02715 | 15.2 | Solar | 05_14_211L2 | 08/17/2018 | 08/29/2018 | 7 | 0 | 7 | 08/30/2018 | 08/30/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 639334 | 01752 | 2.32 | Solar | 05_14_53J2 | 09/11/2024 | 09/23/2024 | 2 | 0 | 2 | 09/24/2024 | 09/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | MEDFORD | 604153 | 02155 | 5.76 | Solar | 05_14_63L1 | 04/18/2024 | 04/22/2024 | 2 | 0 | 2 | 04/23/2024 | 04/23/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 | 04/18/2024 | 5/8/2025 | Y | EXP | 365 | 07/18/2024 | 11/18/2024 | 124 | 0 | 124 |  |  | 2/6/2025 | Connected |  | N
National Grid | TYNGSBORO | 559445 | 01879 | 11.05 | Solar | 05_14_76L3 | 11/21/2023 | 11/22/2023 | 1 | 0 | 1 | 11/24/2023 | 11/24/2023 | 84 | 29 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 291030 | 01841 | 4948 | Other | 05_01_225W3 | 09/15/2020 | 09/24/2020 | 5 | 0 | 5 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/15/2020 | 8/24/2025 | Y | STD | 616 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 730087 | 01841 | 10 | Solar | 05_01_304W6 | 10/30/2025 | 10/30/2025 | 2 | 0 | 2 | 11/13/2025 | 11/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 10/30/2025 | 12/12/2026 | Y | EXP | 365 | 02/19/2026 | 02/22/2026 | 4 | 0 | 4 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 423224 | 01830 | 13.12 | Solar | 05_01_415L2 | 04/28/2022 | 05/02/2022 | 2 | 1 | 1 | 05/03/2022 | 05/03/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 652101 | 01453 | 7.6 | Solar | 05_01_6W1 | 11/14/2024 | 12/11/2024 | 7 | 6 | 1 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/14/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | MILLBURY | 174691 | 01527 | 1500 | Solar | 05_05_19W73 | 04/08/2011 | 04/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 | 04/08/2011 | 12/31/2012 | Y | STD | 185 | 05/30/2012 | 02/26/2013 | 165 | 0 | 165 | 12/5/2012 | 12/5/2012 | 12/6/2012 | Connected |  | N
National Grid | CHARLTON | 177488 | 01507 | 7.6 | Solar | 05_05_317W3 | 09/23/2016 | 09/23/2016 | 3 | 3 | 0 | 09/29/2016 | 09/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 | 09/23/2016 | 10/1/2017 | Y | EXP | 361 | 08/22/2017 | 09/12/2017 | 14 | 0 | 14 | 9/25/2017 | 9/25/2017 | 9/28/2017 | Connected |  | N
National Grid | WORCESTER | 581300 | 01603 | 0 | Battery Add-On | 05_12_37W5 | 01/03/2024 | 01/05/2024 | 2 | 0 | 2 | 01/08/2024 | 01/08/2024 | 64 | 47 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2024 | Connected |  | N
National Grid | SWANSEA | 240929 | 02777 | 10 | Solar | 05_14_211L2 | 08/07/2019 | 08/13/2019 | 3 | 0 | 3 | 08/14/2019 | 08/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | SOUTHBOROUGH | 639669 | 01772 | 13.12 | Solar | 05_14_53J2 | 09/12/2024 | 10/03/2024 | 5 | 3 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2024 | 09/12/2024 | 2/4/2026 | Y | EXP | 365 | 02/20/2025 | 08/18/2025 | 180 | 0 | 180 |  |  | 8/30/2025 | Connected |  | N
National Grid | MEDFORD | 614412 | 02155 | 5.76 | Solar | 05_14_63L1 | 05/30/2024 | 06/06/2024 | 1 | 0 | 1 | 06/07/2024 | 06/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2025 | Connected |  | N
National Grid | TYNGSBORO | 566963 | 01879 | 7.6 | Solar | 05_14_76L3 | 11/10/2023 | 11/16/2023 | 4 | 1 | 3 | 11/17/2023 | 11/17/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2023 | 11/10/2023 | 5/16/2025 | Y | EXP | 500 | 06/06/2024 | 02/19/2025 | 259 | 0 | 259 |  |  | 3/1/2025 | Connected |  | N
National Grid | LAWRENCE | 310355 | 01841 | 6 | Solar | 05_01_225W3 | 09/22/2020 | 09/24/2020 | 1 | 0 | 1 | 09/25/2020 | 09/25/2020 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 09/22/2020 | 9/1/2021 | Y | EXP | 365 | 05/25/2021 | 06/15/2021 | 21 | 0 | 21 |  |  | 8/6/2021 | Connected |  | N
National Grid | LAWRENCE | 737133 | 01841 | 17.16 | Solar | 05_01_304W6 | 12/01/2025 | 12/03/2025 | 2 | 0 | 2 | 12/04/2025 | 12/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 482703 | 01830 | 23.49 | Solar | 05_01_415L2 | 12/05/2022 | 12/08/2022 | 3 | 0 | 3 | 12/09/2022 | 12/09/2022 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 | 12/05/2022 | 1/24/2024 | Y | EXP | 365 | 05/05/2023 | 06/08/2023 | 35 | 0 | 35 |  |  | 7/27/2023 | Connected |  | N
National Grid | LANCASTER | 654308 | 01523 | 5.76 | Solar | 05_01_6W1 | 11/15/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/15/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | SUTTON | 174690 | 01590 | 1000 | Solar | 05_05_19W73 | 04/08/2011 | 04/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 | 04/08/2011 | 12/31/2012 | Y | STD | 185 | 05/30/2012 | 02/26/2013 | 165 | 0 | 165 | 12/5/2012 | 12/5/2012 | 12/5/2012 | Connected |  | N
National Grid | CHARLTON | 289768 | 01507 | 166.6 | Solar | 05_05_317W3 | 06/10/2020 | 07/06/2020 | 18 | 13 | 5 | 07/07/2020 | 07/07/2020 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2020 |  | 7/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2021 | Connected |  | N
National Grid | WORCESTER | 635886 | 01603 | 7.6 | Solar | 05_12_37W5 | 08/29/2024 | 09/16/2024 | 7 | 4 | 3 | 09/17/2024 | 09/17/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 254655 | 02777 | 10 | Solar | 05_14_211L2 | 10/01/2019 | 10/04/2019 | 2 | 2 | 0 | 10/07/2019 | 10/07/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 | 10/01/2019 | 10/1/2020 | Y | EXP | 365 | 01/09/2020 | 04/17/2020 | 99 | 0 | 99 |  |  | 5/19/2020 | Connected |  | N
National Grid | SOUTHBOROUGH | 640559 | 01772 | 15.2 | Solar | 05_14_53J2 | 09/24/2024 | 10/03/2024 | 8 | 6 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2024 |  | 11/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | MEDFORD | 618251 | 02155 | 6 | Solar | 05_14_63L1 | 06/17/2024 | 07/02/2024 | 1 | 0 | 1 | 07/03/2024 | 07/03/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | TYNGSBORO | 591663 | 01879 | 0 | Battery Add-On | 05_14_76L3 | 03/06/2024 | 03/20/2024 | 11 | 9 | 2 | 03/21/2024 | 03/21/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 |  | 4/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | LAWRENCE | 317408 | 01841 | 7.25 | Solar | 05_01_225W3 | 10/16/2020 | 10/20/2020 | 1 | 0 | 1 | 10/21/2020 | 10/21/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 747999 | 01841 | 10 | Solar | 05_01_304W6 | 01/28/2026 | 02/02/2026 | 8 | 5 | 3 | 03/17/2026 | 03/17/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAVERHILL | 487520 | 01830 | 8.7 | Solar | 05_01_415L2 | 01/06/2023 | 01/12/2023 | 4 | 0 | 4 | 01/13/2023 | 01/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 9/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2023 | Connected |  | N
National Grid | LEOMINSTER | 735202 | 01453 | 23 | Solar | 05_01_6W1 | 11/20/2025 | 11/25/2025 | 3 | 0 | 3 | 11/26/2025 | 11/26/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 175157 | 01590 | 2000 | Solar | 05_05_19W73 | 07/25/2011 | 07/25/2011 | 97 | 0 | 97 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2011 | 02/25/2014 | 523 | 0 | 523 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 324464 | 01507 | 16 | Solar | 05_05_317W3 | 11/07/2020 | 11/10/2020 | 1 | 0 | 1 | 11/12/2020 | 11/12/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 11/10/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 651935 | 01501 | 5.32 | Solar | 05_12_37W5 | 11/04/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 11/04/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | SWANSEA | 368610 | 02777 | 6 | Solar | 05_14_211L2 | 07/12/2021 | 07/13/2021 | 1 | 0 | 1 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 642771 | 01772 | 15.2 | Solar | 05_14_53J2 | 09/25/2024 | 09/26/2024 | 1 | 0 | 1 | 09/27/2024 | 09/27/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 09/25/2024 | 10/24/2025 | Y | EXP | 365 | 01/09/2025 | 06/10/2025 | 153 | 0 | 153 |  |  | 7/1/2025 | Connected |  | N
National Grid | MEDFORD | 619181 | 02155 | 10 | Solar | 05_14_63L1 | 06/20/2024 | 07/15/2024 | 4 | 0 | 4 | 07/16/2024 | 07/16/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 06/20/2024 | 8/23/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | TYNGSBORO | 638521 | 01879 | 6 | Solar | 05_14_76L3 | 09/10/2024 | 10/08/2024 | 16 | 11 | 5 | 10/09/2024 | 10/09/2024 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 337622 | 01841 | 9.57 | Solar | 05_01_225W3 | 03/12/2021 | 03/18/2021 | 3 | 0 | 3 | 03/19/2021 | 03/19/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2021 |  | 9/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2021 | Connected |  | N
National Grid | METHUEN | 174356 | 01844 | 143 | Natural Gas | 05_01_304W6 | 05/11/2012 | 05/11/2012 | 154 | 0 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 521797 | 01830 | 12.288 | Solar | 05_01_415L2 | 07/10/2023 | 07/12/2023 | 3 | 1 | 2 | 07/13/2023 | 07/13/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2023 | 07/10/2023 | 9/8/2024 | Y | EXP | 365 | 10/24/2023 | 12/13/2023 | 51 | 0 | 51 |  |  | 7/9/2024 | Connected |  | N
National Grid | LEOMINSTER | 656032 | 01453 | 7.6 | Solar | 05_01_6W2 | 11/21/2024 | 04/07/2025 | 29 | 27 | 2 | 04/08/2025 | 04/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SUTTON | 175622 | 01590 | 996 | Solar | 05_05_19W73 | 05/05/2014 | 05/05/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2014 | 06/02/2014 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2015 | 05/05/2014 | 12/31/2016 | Y | STD | 575 | 12/01/2016 | 12/30/2016 | 20 | 0 | 20 | 12/30/2016 | 12/30/2016 | 12/30/2016 | Connected |  | N
National Grid | CHARLTON | 422790 | 01507 | 17.6 | Solar | 05_05_317W3 | 04/08/2022 | 05/05/2022 | 19 | 17 | 2 | 05/06/2022 | 05/06/2022 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2022 | 04/08/2022 | 3/8/2024 | Y | EXP | 365 | 08/11/2022 | 01/11/2023 | 154 | 0 | 154 |  |  | 8/23/2023 | Connected |  | N
National Grid | WORCESTER | 653334 | 01603 | 3.8 | Solar | 05_12_37W5 | 11/08/2024 | 11/25/2024 | 4 | 0 | 4 | 11/26/2024 | 11/26/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | DIGHTON | 475793 | 02715 | 3.8 | Solar | 05_14_211L2 | 11/11/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2022 |  | 12/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | SOUTHBOROUGH | 659995 | 01772 | 12.76 | Solar | 05_14_53J2 | 12/11/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 57 | 33 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 622624 | 02155 | 3.8 | Solar | 05_14_63L1 | 07/04/2024 | 07/11/2024 | 2 | 0 | 2 | 07/12/2024 | 07/12/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  | 8/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | TYNGSBORO | 645705 | 01879 | 6.72 | Solar | 05_14_76L3 | 10/08/2024 | 11/05/2024 | 4 | 0 | 4 | 11/06/2024 | 11/06/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/08/2024 | 1/23/2026 | Y | EXP | 365 | 05/10/2025 | 11/21/2025 | 196 | 0 | 196 |  |  | 12/2/2025 | Connected |  | N
National Grid | LAWRENCE | 396879 | 01841 | 1500 | Solar | 05_01_225W3 | 03/14/2022 |  | 166 | 157 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 174658 | 01844 | 150 | Natural Gas | 05_01_304W6 | 12/10/2012 | 12/10/2012 | 20 | 14 | 6 | 01/10/2013 | 01/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2013 |  | 10/15/2014 | N | EXP | 576 |  |  | 0 | 0 | 0 | 6/15/2015 | 6/15/2015 | 6/30/2015 | Connected |  | N
National Grid | HAVERHILL | 557025 | 01830 | 0 | Solar | 05_01_415L2 | 12/22/2023 | 01/02/2024 | 5 | 2 | 3 | 01/03/2024 | 01/03/2024 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2024 | Connected |  | N
National Grid | LEOMINSTER | 689362 | 01453 | 990 | Solar | 05_01_6W2 | 06/23/2025 | 09/10/2025 | 55 | 48 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2025 | 09/30/2025 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SUTTON | 175763 | 01590 | 684 | Solar | 05_05_19W73 | 06/05/2014 | 06/05/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/16/2014 | 09/04/2014 | 55 | 0 | 55 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2014 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 439477 | 01507 | 7.6 | Solar | 05_05_317W3 | 07/28/2022 | 08/01/2022 | 2 | 0 | 2 | 08/02/2022 | 08/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 | 07/28/2022 | 1/5/2024 | Y | EXP | 365 | 10/11/2022 | 01/24/2023 | 106 | 0 | 106 |  |  | 1/14/2023 | Connected |  | N
National Grid | WORCESTER | 730332 | 01602 | 9.6 | Solar | 05_12_37W5 | 10/30/2025 | 10/30/2025 | 5 | 1 | 4 | 11/13/2025 | 11/13/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 576580 | 02715 | 0 | Battery Add-On | 05_14_211L2 | 12/07/2023 | 02/08/2024 | 43 | 39 | 4 | 02/09/2024 | 02/09/2024 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 | 12/07/2023 | 4/29/2025 | Y | EXP | 365 | 05/23/2024 | 05/22/2024 | 0 | 0 | 0 |  |  | 10/14/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 670934 | 01772 | 4.56 | Solar | 05_14_53J2 | 02/07/2025 | 02/27/2025 | 4 | 0 | 4 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | MEDFORD | 627956 | 02155 | 7.6 | Solar | 05_14_63L1 | 07/26/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/26/2024 | 8/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | TYNGSBORO | 648301 | 01879 | 5.76 | Solar | 05_14_76L3 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | LAWRENCE | 416915 | 01841 | 9.772 | Solar | 05_01_225W3 | 03/11/2022 | 03/29/2022 | 13 | 12 | 1 | 03/30/2022 | 03/30/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2022 |  | 5/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2023 | Connected |  | N
National Grid | LAWRENCE | 174996 | 01841 | 1250 | Solar | 05_01_304W6 | 03/08/2013 | 03/08/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2013 | 04/30/2013 | 29 | 0 | 29 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 548536 | 01830 | 7.6 | Solar | 05_01_415L2 | 08/25/2023 | 08/29/2023 | 3 | 2 | 1 | 08/30/2023 | 08/30/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2023 | 08/25/2023 | 11/9/2024 | Y | EXP | 365 | 03/09/2024 | 04/10/2024 | 33 | 0 | 33 |  |  | 6/27/2024 | Connected |  | N
National Grid | LANCASTER | 742785 | 01523 | 5.76 | Solar | 05_01_6W2 | 12/30/2025 | 01/09/2026 | 3 | 0 | 3 | 01/16/2026 | 01/16/2026 | 29 | 16 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2026 |  | 3/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SUTTON | 175926 | 01590 | 16 | Solar | 05_05_19W73 | 06/01/2015 | 06/01/2015 | 11 | 11 | 0 | 06/17/2015 | 06/17/2015 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2015 |  | 6/30/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 7/6/2015 | 7/6/2015 |  | Withdrawn |  | N
National Grid | CHARLTON | 456585 | 01507 | 10 | Solar | 05_05_317W3 | 09/05/2022 | 09/06/2022 | 1 | 0 | 1 | 09/07/2022 | 09/07/2022 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 10/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | N
National Grid | WORCESTER | 733722 | 01603 | 140 | Solar | 05_12_37W6 | 03/30/2026 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SWANSEA | 644867 | 02777 | 8.45 | Solar | 05_14_211L2 | 10/03/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 18 | 3 | 15 | 11/14/2024 | 12/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 12/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 12/25/2025 | N | EXP | 365 | 01/14/2025 | 03/28/2025 | 74 | 0 | 74 |  |  | 4/2/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 685070 | 01772 | 13.8 | Solar | 05_14_53J2 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 04/22/2025 | 6/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | MEDFORD | 633390 | 02155 | 5 | Solar | 05_14_63L1 | 08/19/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 08/19/2024 | 10/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | TYNGSBORO | 655955 | 01879 | 10 | Solar | 05_14_76L3 | 11/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | LAWRENCE | 426808 | 01841 | 9.57 | Solar | 05_01_225W3 | 07/14/2022 | 08/04/2022 | 16 | 9 | 7 | 08/05/2022 | 08/05/2022 | 51 | 32 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 10/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2023 | Connected |  | N
National Grid | METHUEN | 175250 | 01844 | 24.94 | Solar | 05_01_304W6 | 11/05/2014 | 11/05/2014 | 6 | 3 | 3 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 |  | 1/30/2015 | N | EXP | 72 |  |  | 0 | 0 | 0 | 11/19/2015 | 11/19/2015 | 11/19/2015 | Connected |  | N
National Grid | HAVERHILL | 614260 | 01830 | 6 | Solar | 05_01_415L2 | 05/30/2024 | 06/06/2024 | 1 | 0 | 1 | 06/07/2024 | 06/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/30/2024 | 7/9/2025 | Y | EXP | 365 | 08/06/2024 | 08/15/2024 | 10 | 0 | 10 |  |  | 12/20/2024 | Connected |  | N
National Grid | LEOMINSTER | 750002 | 01453 | 10 | Solar | 05_01_6W2 | 02/09/2026 | 02/11/2026 | 2 | 0 | 2 | 02/23/2026 | 02/23/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2026 | 02/09/2026 | 3/19/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SUTTON | 175915 | 01590 | 2000 | Solar | 05_05_19W73 | 03/11/2015 | 03/11/2015 | 9 | 6 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 04/22/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2016 | 03/11/2015 | 12/31/2017 | Y | STD | 642 | 09/19/2017 | 12/14/2017 | 54 | 0 | 54 | 12/15/2017 | 12/15/2017 | 12/19/2017 | Connected |  | N
National Grid | CHARLTON | 507198 | 01507 | 19.72 | Solar | 05_05_317W3 | 03/09/2023 | 03/10/2023 | 1 | 0 | 1 | 03/13/2023 | 03/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2023 |  | 4/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2023 | Connected |  | N
National Grid | WORCESTER | 742301 | 01602 |  | Solar | 05_12_37W6 | 03/06/2026 |  | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SWANSEA | 649505 | 02777 | 8.12 | Solar | 05_14_211L2 | 10/26/2024 | 12/03/2024 | 8 | 6 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 652357 | 01772 | 7.6 | Solar | 05_14_53J3 | 01/22/2025 | 02/19/2025 | 9 | 4 | 5 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 01/22/2025 | 3/28/2026 | Y | EXP | 365 | 06/12/2025 | 09/18/2025 | 99 | 0 | 99 |  |  | 10/7/2025 | Connected |  | N
National Grid | EVERETT | 635398 | 02149 | 7.6 | Solar | 05_14_63L1 | 08/26/2024 | 09/03/2024 | 3 | 0 | 3 | 09/04/2024 | 09/04/2024 | 110 | 24 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 703835 | 01879 | 6.46 | Solar | 05_14_76L3 | 07/11/2025 | 07/14/2025 | 1 | 0 | 1 | 07/15/2025 | 07/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 |  | 8/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | LAWRENCE | 437424 | 01841 | 0 | Other | 05_01_225W3 | 09/22/2022 | 10/18/2022 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 11/09/2022 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175459 | 01844 | 499 | Solar | 05_01_304W6 | 09/19/2014 | 09/19/2014 | 7 | 0 | 7 | 10/01/2014 | 10/01/2014 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 665982 | 01830 | 7.6 | Solar | 05_01_415L2 | 01/15/2025 | 03/21/2025 | 9 | 5 | 4 | 03/24/2025 | 03/24/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 01/15/2025 | 8/29/2026 | Y | EXP | 365 | 10/01/2025 | 09/30/2025 | 0 | 0 | 0 |  |  | 2/4/2026 | Connected |  | N
National Grid | LEOMINSTER | 166072 | 01453 | 7.6 | Solar | 05_01_6W2 | 04/24/2018 | 04/24/2018 | 9 | 0 | 9 | 07/27/2018 | 07/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 |  | 11/18/2020 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | SUTTON | 176025 | 01590 | 980 | Solar | 05_05_19W73 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 05/04/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 511745 | 01507 | 15.2 | Solar | 05_05_317W3 | 03/16/2023 | 03/17/2023 | 1 | 0 | 1 | 03/20/2023 | 03/20/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2023 | 03/16/2023 | 4/27/2024 | Y | EXP | 365 | 05/06/2023 | 12/06/2023 | 215 | 0 | 215 |  |  | 12/14/2023 | Connected |  | N
National Grid | LEICESTER | 174623 | 01611 | 200 | Solar | 05_12_37W6 | 04/14/2011 | 04/14/2011 | 155 | 0 | 155 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2011 |  | 6/29/2012 | N | EXP | 214 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 6/29/2012 | Connected |  | N
National Grid | DIGHTON | 657556 | 02715 | 10 | Solar | 05_14_211L2 | 11/28/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/28/2024 | 2/12/2026 | Y | EXP | 365 | 07/30/2025 | 02/02/2026 | 188 | 0 | 188 |  |  | 11/21/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 662820 | 01772 | 9.1 | Solar | 05_14_53J3 | 12/27/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 12/27/2024 | 4/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | EVERETT | 637653 | 02149 | 10 | Solar | 05_14_63L1 | 09/04/2024 | 09/19/2024 | 3 | 0 | 3 | 09/20/2024 | 09/20/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 | 09/04/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 742161 | 01879 | 5.76 | Solar | 05_14_77L1 | 12/24/2025 | 12/29/2025 | 2 | 0 | 2 | 12/30/2025 | 12/30/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 466225 | 01841 | 13.824 | Solar | 05_01_225W3 | 10/18/2022 | 11/01/2022 | 10 | 8 | 2 | 11/02/2022 | 11/02/2022 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 2/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2023 | Connected |  | N
National Grid | LAWRENCE | 175617 | 01841 | 114 | Solar | 05_01_304W6 | 04/24/2014 | 04/24/2014 | 6 | 0 | 6 | 05/05/2014 | 05/05/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2014 | 04/24/2014 | 9/30/2014 | Y | EXP | 118 | 10/15/2014 | 12/17/2014 | 43 | 0 | 43 | 7/21/2014 | 7/21/2014 | 12/19/2014 | Connected |  | N
National Grid | HAVERHILL | 666943 | 01830 | 10.47 | Solar | 05_01_415L2 | 01/24/2025 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | LEOMINSTER | 174126 | 01453 | 135 | Solar | 05_01_6W2 | 04/27/2012 | 04/27/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2013 |  | 8/9/2012 | N | EXP | 232 |  |  | 0 | 0 | 0 | 3/29/2013 | 3/29/2013 | 1/6/2014 | Connected |  | N
National Grid | GRAFTON | 176085 | 01519 | 499 | Solar | 05_05_19W73 | 02/04/2015 | 02/04/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 | 03/19/2015 | 02/14/2017 | 474 | 0 | 474 | 02/11/2015 | 03/18/2015 | 23 | 0 | 23 | 02/14/2017 | 474 | 0 | 474 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 554254 | 01507 | 0 | Solar | 05_05_317W3 | 09/08/2023 | 09/12/2023 | 2 | 0 | 2 | 09/13/2023 | 09/13/2023 | 29 | 7 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 | 09/08/2023 | 12/7/2024 | Y | EXP | 365 | 11/21/2023 | 11/21/2023 | 1 | 0 | 1 |  |  | 2/12/2024 | Connected |  | N
National Grid | WORCESTER | 175081 | 01603 | 30 | Solar | 05_12_37W6 | 10/01/2013 | 10/01/2013 | 6 | 0 | 6 | 10/10/2013 | 10/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2013 |  | 12/31/2013 | N | EXP | 70 |  |  | 0 | 0 | 0 | 12/23/2013 | 12/23/2013 | 12/27/2013 | Connected |  | N
National Grid | SWANSEA | 659846 | 02777 | 7.6 | Solar | 05_14_211L2 | 12/11/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 667264 | 01772 | 7.6 | Solar | 05_14_53J3 | 02/04/2025 | 02/21/2025 | 3 | 0 | 3 | 02/24/2025 | 02/24/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 642797 | 02149 | 15.2 | Solar | 05_14_63L1 | 09/25/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 118 | 101 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 | 09/25/2024 | 5/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | TYNGSBORO | 751319 | 01879 | 11.4 | Solar | 05_14_77L1 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 02/25/2026 | 02/25/2026 | 26 | 9 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 491913 | 01841 | 3.8 | Solar | 05_01_225W3 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2023 | 02/01/2023 | 6/7/2024 | Y | EXP | 365 | 05/02/2023 | 06/08/2023 | 38 | 0 | 38 |  |  | 8/10/2023 | Connected |  | N
National Grid | LAWRENCE | 175603 | 01841 | 990 | Solar | 05_01_304W6 | 10/15/2014 | 10/15/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2014 | 11/19/2014 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 | 10/15/2014 | 12/31/2016 | Y | STD | 599 | 07/12/2017 | 07/12/2017 | 0 | 0 | 0 | 8/15/2017 | 8/15/2017 | 8/15/2017 | Connected |  | N
National Grid | LOWELL | 668885 | 01854 | 10 | Solar | 05_01_415L2 | 01/30/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | LANCASTER | 174417 | 01523 | 142 | Solar | 05_01_6W2 | 06/21/2012 | 06/21/2012 | 6 | 0 | 6 | 07/03/2012 | 07/03/2012 | 293 | 0 | 293 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 9/10/2012 | N | EXP | 93 |  |  | 0 | 0 | 0 | 9/25/2012 | 9/25/2012 |  | Withdrawn |  | N
National Grid | SUTTON | 176362 | 01590 | 10 | Solar | 05_05_19W73 | 03/08/2016 | 03/08/2016 | 1 | 1 | 0 | 03/11/2016 | 03/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2016 |  | 3/15/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/15/2016 | 7/15/2016 | 7/15/2016 | Connected |  | N
National Grid | CHARLTON | 645386 | 01507 | 10 | Solar | 05_05_317W3 | 10/18/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 | 10/18/2024 | 1/3/2026 | Y | EXP | 365 | 01/16/2025 | 02/19/2025 | 34 | 0 | 34 |  |  | 4/22/2025 | Connected |  | N
National Grid | WORCESTER | 177276 | 01603 | 5.2 | Solar | 05_12_37W6 | 02/06/2017 | 02/06/2017 | 4 | 4 | 0 | 02/13/2017 | 02/13/2017 | 194 | 0 | 194 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2017 |  | 2/12/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 672483 | 02715 | 6 | Solar | 05_14_211L2 | 02/18/2025 | 03/25/2025 | 4 | 0 | 4 | 03/26/2025 | 03/26/2025 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 | 02/18/2025 | 6/6/2026 | Y | EXP | 365 | 10/01/2025 | 01/27/2026 | 119 | 0 | 119 |  |  | 12/4/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 319285 | 01772 | 8.12 | Solar | 05_14_53J4 | 11/12/2020 | 11/17/2020 | 2 | 0 | 2 | 11/18/2020 | 11/18/2020 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2020 | 11/12/2020 | 11/12/2021 | Y | EXP | 365 | 04/14/2021 | 05/20/2021 | 36 | 0 | 36 |  |  | 5/21/2021 | Connected |  | N
National Grid | EVERETT | 645251 | 02149 | 5.76 | Solar | 05_14_63L1 | 10/07/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/07/2024 | 12/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | TYNGSBORO | 176630 | 01879 | 10 | Solar | 05_14_77L1 | 10/15/2015 | 10/15/2015 | 3 | 3 | 0 | 10/21/2015 | 10/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 |  | 10/21/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 | 8/19/2016 | 8/19/2016 | 8/19/2016 | Connected |  | N
National Grid | LAWRENCE | 564107 | 01841 | 10 | Solar | 05_01_225W3 | 11/08/2023 | 11/13/2023 | 2 | 0 | 2 | 11/14/2023 | 11/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2023 | 11/08/2023 | 1/2/2025 | Y | EXP | 365 | 05/16/2024 | 05/29/2024 | 14 | 0 | 14 |  |  | 7/5/2024 | Connected |  | N
National Grid | METHUEN | 175745 | 01844 | 496.8 | Solar | 05_01_304W6 | 10/28/2014 | 10/28/2014 | 5 | 0 | 5 | 11/05/2014 | 11/05/2014 | 151 | 16 | 135 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 |  | 3/31/2015 | N | EXP | 27 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 688903 | 01854 | 10 | Solar | 05_01_415L2 | 05/01/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 05/01/2025 | 6/27/2026 | Y | EXP | 365 | 07/31/2025 | 07/30/2025 | 0 | 0 | 0 |  |  | 9/25/2025 | Connected |  | N
National Grid | LEOMINSTER | 174924 | 01453 | 75 | Solar | 05_01_6W2 | 02/26/2013 | 02/26/2013 | 5 | 1 | 4 | 03/11/2013 | 03/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2013 |  | 7/31/2013 | N | EXP | 70 |  |  | 0 | 0 | 0 | 7/3/2013 | 7/3/2013 | 7/19/2013 | Connected |  | N
National Grid | SUTTON | 176537 | 01590 | 10 | Solar | 05_05_19W73 | 02/10/2016 | 02/10/2016 | 15 | 15 | 0 | 03/04/2016 | 03/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2016 | 02/10/2016 | 2/16/2017 | Y | EXP | 321 | 08/16/2016 | 08/30/2016 | 10 | 0 | 10 | 10/24/2016 | 10/24/2016 | 10/26/2016 | Connected |  | N
National Grid | CHARLTON | 649999 | 01507 | 16.72 | Solar | 05_05_317W3 | 10/25/2024 | 10/30/2024 | 3 | 0 | 3 | 10/31/2024 | 10/31/2024 | 51 | 27 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | WORCESTER | 178386 | 01602 | 7.6 | Solar | 05_12_37W6 | 01/15/2018 | 01/15/2018 | 0 | 0 | 0 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2018 |  | 1/21/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N
National Grid | DIGHTON | 676121 | 02715 | 11.4 | Solar | 05_14_211L2 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 322607 | 01772 | 5 | Solar | 05_14_53J4 | 12/22/2020 | 12/30/2020 | 4 | 0 | 4 | 12/31/2020 | 12/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/22/2020 | 4/3/2022 | Y | EXP | 365 | 08/15/2021 | 09/24/2021 | 40 | 3 | 37 |  |  | 11/9/2021 | Connected |  | N
National Grid | EVERETT | 645235 | 02149 | 8.41 | Solar | 05_14_63L1 | 10/06/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 176717 | 01879 | 5 | Solar | 05_14_77L1 | 01/11/2016 | 01/11/2016 | 3 | 3 | 0 | 01/15/2016 | 01/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2016 |  | 1/17/2017 | N | EXP | 350 |  |  | 0 | 0 | 0 | 8/1/2016 | 8/1/2016 | 8/2/2016 | Connected |  | N
National Grid | METHUEN | 587327 | 01844 | 19 | Solar | 05_01_225W3 | 02/01/2024 | 02/06/2024 | 3 | 1 | 2 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 175807 | 01844 | 27.95 | Solar | 05_01_304W6 | 05/15/2015 | 05/15/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2015 |  | 10/30/2015 | N | EXP | 161 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 1/22/2016 | Connected |  | N
National Grid | LOWELL | 178200 | 01854 | 4999 | Solar | 05_01_415L3 | 02/15/2018 | 02/22/2018 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2018 | 03/20/2018 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 | 02/15/2018 | 5/22/2026 | Y | STD | 747 | 02/07/2026 |  | 54 | 0 | 54 |  |  |  | Construction |  | N
National Grid | LEOMINSTER | 175045 | 01453 | 246.5 | Solar | 05_01_6W2 | 09/23/2013 | 09/23/2013 | 6 | 0 | 6 | 10/02/2013 | 10/02/2013 | 335 | 0 | 335 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2014 |  | 9/1/2015 | N | EXP | 526 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 176655 | 01590 | 4.25 | Solar | 05_05_19W73 | 04/18/2016 | 04/18/2016 | 2 | 2 | 0 | 04/21/2016 | 04/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2016 | 04/18/2016 | 4/24/2017 | Y | EXP | 355 | 05/11/2017 | 05/31/2017 | 13 | 0 | 13 | 6/2/2017 | 6/2/2017 | 6/6/2017 | Connected |  | N
National Grid | CHARLTON | 756503 | 01507 | 11.4 | Solar | 05_05_317W4 | 03/13/2026 | 03/18/2026 | 3 | 0 | 3 | 03/19/2026 | 03/19/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEICESTER | 329274 | 01524 | 5 | Solar | 05_12_37W6 | 01/08/2021 | 01/12/2021 | 1 | 0 | 1 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/08/2021 | 8/3/2022 | Y | EXP | 365 | 06/02/2021 | 12/09/2021 | 191 | 7 | 184 |  |  | 12/22/2021 | Connected |  | N
National Grid | DIGHTON | 708614 | 02715 | 23 | Solar | 05_14_211L2 | 08/01/2025 | 08/05/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 540408 | 01772 | 6 | Solar | 05_14_53J4 | 07/26/2023 | 08/22/2023 | 20 | 19 | 1 | 08/23/2023 | 08/23/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 649440 | 02149 | 7.6 | Solar | 05_14_63L1 | 11/11/2024 | 12/19/2024 | 11 | 5 | 6 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | TYNGSBORO | 178127 | 01879 | 10 | Solar | 05_14_77L1 | 07/11/2017 | 07/11/2017 | 4 | 4 | 0 | 07/18/2017 | 07/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2017 |  | 7/17/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/24/2018 | 1/24/2018 | 1/24/2018 | Connected |  | N
National Grid | LAWRENCE | 595356 | 01841 | 7.6 | Solar | 05_01_225W3 | 03/15/2024 | 03/19/2024 | 2 | 0 | 2 | 03/20/2024 | 03/20/2024 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 | 03/15/2024 | 4/4/2025 | Y | EXP | 365 | 06/11/2024 | 06/18/2024 | 8 | 0 | 8 |  |  | 6/27/2024 | Connected |  | Y
National Grid | METHUEN | 175861 | 01844 | 100 | Solar | 05_01_304W6 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2015 |  | 8/10/2016 | N | EXP | 357 |  |  | 0 | 0 | 0 | 8/19/2015 | 8/19/2015 | 12/18/2015 | Connected |  | N
National Grid | LOWELL | 663974 | 01854 | 200 | Solar | 05_01_415L3 | 01/13/2025 | 02/03/2025 | 15 | 5 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LANCASTER | 175640 | 01523 | 354 | Solar | 05_01_6W2 | 10/20/2014 | 10/20/2014 | 8 | 4 | 4 | 10/31/2014 | 10/31/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 |  | 9/1/2016 | N | EXP | 528 |  |  | 0 | 0 | 0 | 10/23/2014 | 10/23/2014 | 6/16/2016 | Connected |  | N
National Grid | SUTTON | 177463 | 01590 | 528 | Solar | 05_05_19W73 | 03/01/2017 | 03/01/2017 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2017 | 05/09/2017 | 17 | 5 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2017 | 03/01/2017 | 5/7/2019 | Y | STD | 782 | 05/22/2018 | 07/30/2018 | 68 | 0 | 68 | 12/6/2018 | 2/15/2019 | 5/7/2019 | Connected |  | N
National Grid | CHARLTON | 177389 | 01507 | 15.2 | Solar | 05_05_317W4 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2017 |  | 2/21/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 6/8/2017 | 6/8/2017 | 6/13/2017 | Connected |  | N
National Grid | WORCESTER | 454546 | 01603 | 15.744 | Solar | 05_12_37W6 | 08/26/2022 | 09/23/2022 | 20 | 19 | 1 | 09/26/2022 | 09/26/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 11/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | DIGHTON | 660873 | 02715 | 5.76 | Solar | 05_14_21L1 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/16/2024 | 4/11/2026 | Y | EXP | 365 | 07/08/2025 |  | 268 | 0 | 268 |  |  |  | Completion Documents |  | Y
National Grid | SOUTHBOROUGH | 589338 | 01772 | 10 | Solar | 05_14_53J4 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/22/2024 | 3/8/2025 | Y | EXP | 365 | 05/02/2024 | 07/18/2024 | 78 | 0 | 78 |  |  | 8/2/2024 | Connected |  | N
National Grid | EVERETT | 652252 | 02149 | 10 | Solar | 05_14_63L1 | 11/14/2024 | 12/11/2024 | 7 | 6 | 1 | 12/12/2024 | 12/12/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 196418 | 01879 | 100 | Solar | 05_14_77L1 | 09/19/2018 | 10/04/2018 | 2 | 0 | 2 | 10/05/2018 | 10/05/2018 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  | 7/6/2020 | N | EXP | 467 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 614607 | 01841 | 10 | Solar | 05_01_225W3 | 05/31/2024 | 06/06/2024 | 3 | 1 | 2 | 06/07/2024 | 06/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/31/2024 | 6/24/2025 | Y | EXP | 365 | 09/19/2024 | 09/18/2024 | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N
National Grid | METHUEN | 175902 | 01844 | 308 | Solar | 05_01_304W6 | 09/28/2015 | 09/28/2015 | 3 | 3 | 0 | 10/02/2015 | 10/02/2015 | 254 | 0 | 254 | 01/04/2016 | 02/23/2016 | 34 | 0 | 34 |  |  | 0 | 0 | 0 | 02/23/2016 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 10/4/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174387 | 01854 | 2000 | Solar | 05_01_415L3 | 06/01/2012 | 06/01/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/14/2012 | 08/20/2012 | 45 | 0 | 45 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/15/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 175981 | 01453 | 28 | Solar | 05_01_6W2 | 01/23/2015 | 01/23/2015 | 6 | 0 | 6 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2015 |  | 6/30/2015 | N | EXP | 141 |  |  | 0 | 0 | 0 | 6/23/2015 | 6/23/2015 | 7/7/2015 | Connected |  | N
National Grid | SUTTON | 177486 | 01590 | 8 | Solar | 05_05_19W73 | 09/23/2016 | 09/23/2016 | 1 | 1 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2016 | 09/23/2016 | 10/1/2017 | Y | EXP | 367 | 03/31/2017 | 04/13/2017 | 9 | 0 | 9 | 5/1/2017 | 5/1/2017 | 5/3/2017 | Connected |  | N
National Grid | STURBRIDGE | 255931 | 01566 | 10 | Solar | 05_05_317W4 | 09/23/2019 | 09/25/2019 | 2 | 2 | 0 | 09/26/2019 | 09/26/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2019 |  | 9/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N
National Grid | WORCESTER | 566763 | 01603 | 7.6 | Solar | 05_12_37W6 | 11/02/2023 | 11/08/2023 | 4 | 2 | 2 | 11/09/2023 | 11/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 706895 | 02764 | 7.6 | Solar | 05_14_21L1 | 07/23/2025 | 10/15/2025 | 7 | 4 | 3 | 11/13/2025 | 11/13/2025 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 | 07/23/2025 | 12/23/2026 | Y | EXP | 365 | 03/12/2026 |  | 21 | 0 | 21 |  |  |  | Construction |  | N
National Grid | SOUTHBOROUGH | 590580 | 01772 | 10 | Solar | 05_14_53J4 | 02/23/2024 | 02/27/2024 | 2 | 0 | 2 | 02/28/2024 | 02/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 | 02/23/2024 | 3/8/2025 | Y | EXP | 365 | 05/02/2024 | 09/11/2024 | 133 | 0 | 133 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 655004 | 02149 | 3.8 | Solar | 05_14_63L1 | 11/19/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 36 | 14 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 374425 | 01826 | 7.68 | Solar | 05_14_77L1 | 01/12/2022 | 01/18/2022 | 3 | 0 | 3 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 | 01/12/2022 | 1/14/2024 | Y | EXP | 365 | 05/26/2022 | 01/13/2023 | 232 | 0 | 232 |  |  | 1/25/2023 | Connected |  | N
National Grid | METHUEN | 622239 | 01844 | 5.76 | Solar | 05_01_225W3 | 07/02/2024 | 07/17/2024 | 1 | 0 | 1 | 07/18/2024 | 07/18/2024 | 50 | 31 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 | 07/02/2024 | 10/10/2025 | Y | EXP | 365 | 12/03/2024 | 12/16/2024 | 14 | 0 | 14 |  |  | 4/5/2025 | Connected |  | N
National Grid | LAWRENCE | 175978 | 01841 | 95 | Solar | 05_01_304W6 | 01/23/2015 | 01/23/2015 | 24 | 22 | 2 | 03/02/2015 | 03/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2015 |  | 6/30/2015 | N | EXP | 84 |  |  | 0 | 0 | 0 | 4/8/2015 | 4/8/2015 | 6/11/2015 | Connected |  | N
National Grid | LOWELL | 174874 | 01854 | 1000 | Solar | 05_01_415L3 | 09/10/2012 | 09/10/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 09/26/2012 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 09/10/2012 | 6/13/2016 | Y | STD | 1036 |  |  | 0 | 0 | 0 | 10/19/2017 | 10/19/2017 | 10/19/2017 | Connected |  | N
National Grid | LEOMINSTER | 176334 | 01453 | 6.67 | Solar | 05_01_6W2 | 09/15/2015 | 09/15/2015 | 4 | 4 | 0 | 09/22/2015 | 09/22/2015 | 349 | 0 | 349 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/21/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 177696 | 01527 | 11.4 | Solar | 05_05_19W73 | 03/21/2017 | 03/21/2017 | 7 | 7 | 0 | 03/30/2017 | 03/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2017 |  | 3/26/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 | 1/9/2018 | 1/9/2018 | 1/12/2018 | Connected |  | N
National Grid | STURBRIDGE | 299834 | 01566 | 10 | Solar | 05_05_317W4 | 07/06/2020 | 07/29/2020 | 16 | 14 | 2 | 07/30/2020 | 07/30/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 10/16/2021 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 591336 | 01602 | 10 | Solar | 05_12_37W6 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/27/2024 | 11/30/2025 | Y | EXP | 365 | 09/19/2024 | 10/02/2025 | 379 | 0 | 379 |  |  | 11/7/2025 | Connected |  | N
National Grid | DIGHTON | 174507 | 02715 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | SOUTHBOROUGH | 598618 | 01772 | 9.56 | Solar | 05_14_53J4 | 03/27/2024 | 04/03/2024 | 5 | 2 | 3 | 04/04/2024 | 04/04/2024 | 24 | 20 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | EVERETT | 656998 | 02149 | 7.6 | Solar | 05_14_63L1 | 11/26/2024 | 01/03/2025 | 15 | 11 | 4 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 11/26/2024 | 4/16/2026 | Y | EXP | 365 | 05/15/2025 | 05/20/2025 | 6 | 0 | 6 |  |  | 9/9/2025 | Connected |  | N
National Grid | DRACUT | 480217 | 01826 | 7.6 | Solar | 05_14_77L1 | 01/17/2023 | 01/18/2023 | 1 | 0 | 1 | 01/19/2023 | 01/19/2023 | 21 | 2 | 19 | 02/23/2023 | 03/22/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 03/22/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | Y
National Grid | METHUEN | 653119 | 01844 | 11.78 | Solar | 05_01_225W3 | 11/08/2024 | 12/02/2024 | 3 | 0 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | METHUEN | 177386 | 01844 | 17.25 | Solar | 05_01_304W6 | 11/29/2016 | 11/29/2016 | 14 | 14 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 |  | 12/5/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 | 5/5/2017 | 5/5/2017 | 5/8/2017 | Connected |  | N
National Grid | LOWELL | 174907 | 01854 | 1000 | Solar | 05_01_415L3 | 09/14/2012 | 09/14/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 09/26/2012 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 09/14/2012 | 6/13/2016 | Y | STD | 1036 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 176843 | 01453 | 6 | Solar | 05_01_6W2 | 05/02/2016 | 05/02/2016 | 2 | 2 | 0 | 05/05/2016 | 05/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2016 | 05/02/2016 | 1/8/2018 | Y | EXP | 606 | 10/31/2016 | 10/25/2016 | 0 | 0 | 0 | 5/31/2017 | 5/31/2017 | 5/31/2017 | Connected |  | N
National Grid | SUTTON | 177823 | 01590 | 15.2 | Solar | 05_05_19W73 | 06/06/2017 | 06/06/2017 | 4 | 4 | 0 | 06/13/2017 | 06/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 |  | 6/12/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/18/2017 | 10/18/2017 | 10/24/2017 | Connected |  | N
National Grid | STURBRIDGE | 428460 | 01566 | 7.6 | Solar | 05_05_317W4 | 05/04/2022 | 05/12/2022 | 7 | 6 | 1 | 05/13/2022 | 05/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2022 |  | 8/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2022 | Connected |  | N
National Grid | WORCESTER | 596442 | 01603 | 7.6 | Solar | 05_12_37W6 | 03/21/2024 | 03/27/2024 | 4 | 0 | 4 | 03/28/2024 | 03/28/2024 | 101 | 96 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 174506 | 02764 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | SOUTHBOROUGH | 613386 | 01772 | 10 | Solar | 05_14_53J4 | 05/29/2024 | 06/21/2024 | 2 | 0 | 2 | 06/24/2024 | 06/24/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 657645 | 02149 | 3.8 | Solar | 05_14_63L1 | 11/29/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/29/2024 | 5/13/2026 | Y | EXP | 365 | 08/19/2025 | 12/01/2025 | 105 | 0 | 105 |  |  | 12/2/2025 | Connected |  | N
National Grid | DRACUT | 543280 | 01826 | 240 | Solar | 05_14_77L1 | 08/01/2023 | 08/16/2023 | 11 | 0 | 11 | 08/17/2023 | 08/17/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 | 08/01/2023 | 1/10/2026 | Y | EXP | 49 | 04/11/2025 | 04/18/2025 | 8 | 0 | 8 |  |  | 12/31/2025 | Connected |  | N
National Grid | METHUEN | 666473 | 01844 | 18.24 | Solar | 05_01_225W3 | 01/17/2025 | 03/05/2025 | 20 | 15 | 5 | 03/06/2025 | 03/06/2025 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 5/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2025 | Connected |  | N
National Grid | LAWRENCE | 178598 | 01841 | 2500 | Solar | 05_01_304W6 | 04/06/2018 | 04/06/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 07/21/2018 | 68 | 53 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 175328 | 01854 | 540 | Solar | 05_01_415L3 | 11/10/2014 | 11/10/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/17/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/15/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 177158 | 01453 | 10 | Solar | 05_01_6W2 | 10/26/2016 | 10/26/2016 | 3 | 3 | 0 | 11/01/2016 | 11/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2016 | 10/26/2016 | 11/1/2017 | Y | EXP | 363 | 04/17/2017 | 04/25/2017 | 5 | 0 | 5 | 5/18/2017 | 5/18/2017 | 5/18/2017 | Connected |  | N
National Grid | SUTTON | 177995 | 01590 | 20 | Solar | 05_05_19W73 | 10/24/2017 | 10/24/2017 | 8 | 8 | 0 | 11/16/2017 | 11/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2017 |  | 11/1/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 | 12/27/2017 | 12/27/2017 | 1/5/2018 | Connected |  | N
National Grid | STURBRIDGE | 497172 | 01566 | 15.356 | Solar | 05_05_317W4 | 03/03/2023 | 03/06/2023 | 1 | 0 | 1 | 03/07/2023 | 03/07/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 03/03/2023 | 10/31/2024 | Y | EXP | 365 | 06/14/2023 | 11/01/2023 | 141 | 0 | 141 |  |  | 11/11/2023 | Connected |  | N
National Grid | WORCESTER | 633047 | 01602 | 3.8 | Solar | 05_12_37W6 | 08/15/2024 | 08/30/2024 | 3 | 0 | 3 | 09/03/2024 | 09/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 174505 | 02764 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | SOUTHBOROUGH | 622922 | 01772 | 7.6 | Solar | 05_14_53J4 | 07/05/2024 | 08/15/2024 | 2 | 0 | 2 | 08/16/2024 | 08/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 07/05/2024 | 8/28/2025 | Y | EXP | 365 | 03/01/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | EVERETT | 657611 | 02149 | 10 | Solar | 05_14_63L1 | 11/29/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/29/2024 | 2/10/2026 | Y | EXP | 365 | 06/14/2025 | 02/03/2026 | 235 | 0 | 235 |  |  | 12/3/2025 | Connected |  | N
National Grid | DRACUT | 576639 | 01826 | 9.984 | Solar | 05_14_77L1 | 12/14/2023 | 01/22/2024 | 24 | 23 | 1 | 01/23/2024 | 01/23/2024 | 82 | 65 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 673213 | 01841 | 23 | Solar | 05_01_225W3 | 02/20/2025 | 05/06/2025 | 52 | 50 | 2 | 05/07/2025 | 05/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | METHUEN | 178682 | 01844 | 4000 | Solar | 05_01_304W6 | 04/11/2018 | 04/11/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 11/05/2018 | 137 | 0 | 137 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176124 | 01854 | 540 | Solar | 05_01_415L3 | 01/29/2015 | 01/29/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 01/29/2015 | 7/31/2015 | Y | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 178137 | 01453 | 3.8 | Solar | 05_01_6W2 | 03/22/2018 | 04/05/2018 | 9 | 9 | 0 | 04/05/2018 | 04/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2018 |  | 3/28/2019 | N | EXP | 331 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 178125 | 01527 | 3.8 | Solar | 05_05_19W73 | 05/12/2017 | 05/12/2017 | 5 | 5 | 0 | 05/22/2017 | 05/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 |  | 5/20/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/7/2017 | 11/7/2017 | 11/7/2017 | Connected |  | N
National Grid | STURBRIDGE | 625861 | 01566 | 15.2 | Solar | 05_05_317W4 | 07/18/2024 | 07/24/2024 | 5 | 3 | 2 | 07/25/2024 | 07/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | WORCESTER | 635118 | 01603 | 4.35 | Solar | 05_12_37W6 | 08/26/2024 | 10/14/2024 | 5 | 0 | 5 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 174504 | 02715 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | SOUTHBOROUGH | 639127 | 01772 | 8.7 | Solar | 05_14_53J4 | 09/10/2024 | 10/11/2024 | 3 | 0 | 3 | 10/15/2024 | 10/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2024 | Connected |  | N
National Grid | EVERETT | 660632 | 02149 | 5.76 | Solar | 05_14_63L1 | 12/23/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 579700 | 01826 | 6 | Solar | 05_14_77L1 | 01/24/2024 | 01/30/2024 | 4 | 0 | 4 | 01/31/2024 | 01/31/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 3/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2024 | Connected |  | N
National Grid | LAWRENCE | 675974 | 01841 | 5.76 | Solar | 05_01_225W3 | 03/07/2025 | 03/12/2025 | 3 | 0 | 3 | 03/13/2025 | 03/13/2025 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 184056 | 01841 | 999 | Battery Add-On | 05_01_304W6 | 05/01/2018 | 05/01/2018 | 6 | 0 | 6 |  |  | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176481 | 01854 | 57.6 | Solar | 05_01_415L3 | 05/20/2016 | 05/20/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2016 | 05/20/2016 | 5/30/2017 | Y | EXP | 356 | 05/01/2017 | 05/09/2017 | 6 | 0 | 6 | 6/21/2017 | 6/21/2017 | 6/28/2017 | Connected |  | N
National Grid | LEOMINSTER | 178216 | 01453 | 7.6 | Solar | 05_01_6W2 | 04/13/2018 | 04/13/2018 | 14 | 0 | 14 | 05/04/2018 | 05/04/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2018 |  | 4/21/2019 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 178656 | 01590 | 4875 | Solar | 05_05_19W73 | 02/02/2018 | 02/02/2018 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/10/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 660095 | 01566 | 23 | Solar | 05_05_317W4 | 12/11/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | WORCESTER | 637627 | 01603 | 10 | Solar | 05_12_37W6 | 09/04/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 | 09/04/2024 | 11/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | SWANSEA | 174509 | 02777 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | SOUTHBOROUGH | 650617 | 01772 | 17.28 | Solar | 05_14_53J4 | 10/29/2024 | 11/01/2024 | 3 | 1 | 2 | 11/04/2024 | 11/04/2024 | 131 | 111 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2025 | Connected |  | N
National Grid | EVERETT | 665076 | 02149 | 0 | Battery Add-On | 05_14_63L1 | 01/10/2025 | 01/14/2025 | 2 | 0 | 2 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | DRACUT | 598862 | 01826 | 7.6 | Solar | 05_14_77L1 | 04/05/2024 | 04/12/2024 | 5 | 0 | 5 | 04/16/2024 | 04/16/2024 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | LAWRENCE | 679537 | 01841 | 15.2 | Solar | 05_01_225W3 | 03/24/2025 | 06/05/2025 | 0 | 0 | 0 | 06/06/2025 | 06/06/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | METHUEN | 184748 | 01844 | 594 | Solar | 05_01_304W6 | 05/31/2018 | 08/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2018 | 08/22/2018 | 4 | 2 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2019 |  | 8/21/2020 | N | STD | 403 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176677 | 01854 | 112 | Solar | 05_01_415L3 | 01/05/2016 | 01/05/2016 | 0 | 0 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 | 06/28/2016 | 09/15/2016 | 55 | 34 | 21 |  |  | 0 | 0 | 0 | 09/15/2016 | 55 | 34 | 21 |  |  | 0 | 0 | 0 | 10/31/2016 | 01/05/2016 | 1/11/2018 | Y | EXP | 437 | 07/26/2017 | 07/28/2017 | 2 | 0 | 2 | 11/21/2017 | 11/21/2017 | 11/21/2017 | Connected |  | N
National Grid | LEOMINSTER | 178252 | 01453 | 11.4 | Solar | 05_01_6W2 | 03/27/2018 | 04/03/2018 | 4 | 0 | 4 | 04/03/2018 | 04/03/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 | 03/27/2018 | 4/10/2020 | Y | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 3/20/2020 | Connected |  | N
National Grid | SUTTON | 185430 | 01590 | 4998 | Solar | 05_05_19W73 | 05/29/2018 | 05/29/2018 | 61 | 44 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2018 | 09/21/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 454160 | 01566 | 133.2 | Solar | 05_05_317W6 | 10/06/2022 | 01/24/2023 | 72 | 62 | 10 | 01/25/2023 | 01/25/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 | 10/06/2022 | 10/14/2026 | Y | EXP | 245 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 647126 | 01602 | 7.6 | Solar | 05_12_37W6 | 10/23/2024 | 11/27/2024 | 6 | 0 | 6 | 12/02/2024 | 12/02/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 |  | 1/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | DIGHTON | 174508 | 02715 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | SOUTHBOROUGH | 652019 | 01772 | 15.2 | Solar | 05_14_53J4 | 11/04/2024 | 11/20/2024 | 12 | 10 | 2 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/04/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | EVERETT | 666060 | 02149 | 7.6 | Solar | 05_14_63L1 | 01/15/2025 | 03/11/2025 | 3 | 0 | 3 | 03/12/2025 | 03/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 | 01/15/2025 | 4/17/2026 | Y | EXP | 365 | 06/14/2025 | 12/22/2025 | 193 | 0 | 193 |  |  | 12/4/2025 | Connected |  | N
National Grid | DRACUT | 628395 | 01826 | 7.6 | Solar | 05_14_77L1 | 07/29/2024 | 08/02/2024 | 1 | 0 | 1 | 08/05/2024 | 08/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 | 07/29/2024 | 10/8/2025 | Y | EXP | 365 | 10/04/2024 | 11/22/2024 | 50 | 0 | 50 |  |  | 3/13/2025 | Connected |  | Y
National Grid | LAWRENCE | 687754 | 01841 | 10 | Solar | 05_01_225W3 | 05/01/2025 | 05/15/2025 | 4 | 0 | 4 | 06/11/2025 | 06/11/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | METHUEN | 189175 | 01844 | 2050 | Solar | 05_01_304W6 | 09/11/2018 | 10/18/2018 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 | 11/23/2018 | 23 | 4 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 178084 | 01854 | 1000 | Solar | 05_01_415L3 | 09/14/2012 | 09/14/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 09/26/2012 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 09/14/2012 | 5/14/2018 | Y | STD | 1736 | 04/13/2015 | 08/29/2017 | 593 | 0 | 593 | 10/19/2017 | 10/19/2017 | 10/19/2017 | Connected |  | N
National Grid | LEOMINSTER | 178734 | 01453 | 3.8 | Solar | 05_01_6W2 | 02/12/2018 | 03/07/2018 | 0 | 0 | 0 | 03/07/2018 | 03/07/2018 | 189 | 0 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2018 |  | 2/18/2019 | N | EXP | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 188745 | 01590 | 129.6 | Solar | 05_05_19W73 | 06/20/2018 | 06/20/2018 | 10 | 0 | 10 | 08/21/2018 | 08/21/2018 | 32 | 31 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 347804 | 01507 | 216 | Solar | 05_05_317W6 | 03/19/2021 | 04/05/2021 | 9 | 0 | 9 | 04/06/2021 | 04/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2021 |  | 6/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2021 | Connected |  | N
National Grid | WORCESTER | 176325 | 01602 | 495 | Solar | 05_12_37W7 | 07/14/2015 | 07/14/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/21/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 176937 | 02764 | 6 | Solar | 05_14_21L1 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2016 |  | 2/6/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 6/10/2016 | Connected |  | N
National Grid | MARLBOROUGH | 661153 | 01752 | 10 | Solar | 05_14_53J4 | 12/17/2024 | 01/30/2025 | 4 | 0 | 4 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 667679 | 02149 | 7.6 | Solar | 05_14_63L1 | 01/24/2025 | 03/05/2025 | 12 | 8 | 4 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | DRACUT | 642143 | 01826 | 5.76 | Solar | 05_14_77L1 | 09/23/2024 | 11/12/2024 | 14 | 12 | 2 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2025 | Connected |  | N
National Grid | LAWRENCE | 695812 | 01841 | 10 | Solar | 05_01_225W3 | 06/05/2025 | 07/01/2025 | 2 | 0 | 2 | 07/08/2025 | 07/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/11/2025 | Connected |  | N
National Grid | METHUEN | 202902 | 01844 | 0 | Battery Add-On | 05_01_304W6 | 12/06/2018 | 12/14/2018 | 2 | 0 | 2 | 12/17/2018 | 12/17/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2019 |  | 1/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2019 | Connected |  | N
National Grid | LOWELL | 437435 | 01854 | 0 | Other | 05_01_415L3 | 02/27/2023 | 03/16/2023 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2023 | 04/18/2023 | 22 | 3 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 197997 | 01453 | 6 | Solar | 05_01_6W2 | 11/05/2018 | 01/14/2019 | 6 | 0 | 6 | 01/15/2019 | 01/15/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 195428 | 01590 | 1500 | Solar | 05_05_19W73 | 09/13/2017 | 09/25/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2018 | 07/29/2019 | 37 | 6 | 31 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 348992 | 01566 | 100 | Solar | 05_05_317W6 | 03/26/2021 | 05/03/2021 | 24 | 15 | 9 | 05/04/2021 | 05/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2021 |  | 6/26/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 221781 | 01603 | 100 | Solar | 05_12_37W7 | 04/23/2019 | 04/25/2019 | 1 | 0 | 1 | 04/26/2019 | 04/26/2019 | 11 | 3 | 8 | 06/25/2019 | 07/30/2019 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 07/30/2019 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 8/2/2019 |  | 8/3/2020 | N | EXP | 367 |  |  | 0 | 0 | 0 |  |  | 3/9/2020 | Connected |  | N
National Grid | DIGHTON | 178450 | 02715 | 3.8 | Solar | 05_14_21L1 | 11/29/2017 | 11/29/2017 | 39 | 36 | 3 | 01/29/2018 | 01/29/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 |  | 12/31/2020 | N | EXP | 422 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 679548 | 01752 | 10 | Solar | 05_14_53J4 | 03/21/2025 | 04/16/2025 | 16 | 9 | 7 | 05/20/2025 | 05/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 03/21/2025 | 7/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | MALDEN | 668519 | 02148 | 7.6 | Solar | 05_14_63L1 | 01/29/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | DRACUT | 646859 | 01826 | 7.6 | Solar | 05_14_77L1 | 10/28/2024 | 11/07/2024 | 1 | 0 | 1 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/28/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 711810 | 01841 | 10 | Solar | 05_01_225W3 | 08/13/2025 | 08/26/2025 | 8 | 5 | 3 | 08/27/2025 | 08/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2026 | Connected |  | N
National Grid | METHUEN | 292740 | 01844 | 192 | Solar | 05_01_304W6 | 05/22/2020 | 06/16/2020 | 15 | 11 | 4 | 06/17/2020 | 06/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 437621 | 01854 | 4482 | Solar | 05_01_415L3 | 02/27/2023 | 03/16/2023 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2023 | 03/27/2023 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 204022 | 01453 | 3.8 | Solar | 05_01_6W2 | 02/21/2019 | 03/07/2019 | 10 | 10 | 0 | 03/08/2019 | 03/08/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 235724 | 01590 | 7.6 | Solar | 05_05_19W73 | 07/03/2019 | 07/16/2019 | 8 | 8 | 0 | 07/17/2019 | 07/17/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 |  | 10/21/2019 | N | EXP | 82 |  |  | 0 | 0 | 0 |  |  | 9/5/2019 | Connected |  | N
National Grid | CHARLTON | 494891 | 01507 | 24.94 | Solar | 05_05_317W6 | 02/15/2023 | 03/20/2023 | 23 | 22 | 1 | 03/21/2023 | 03/21/2023 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2023 |  | 7/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2023 | Connected |  | N
National Grid | WORCESTER | 448424 | 01603 | 67.3 | Solar | 05_12_37W7 | 08/08/2022 | 08/17/2022 | 7 | 0 | 7 | 08/18/2022 | 08/18/2022 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2022 |  | 12/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2023 | Connected |  | N
National Grid | SWANSEA | 178635 | 02777 | 0 | Solar | 05_14_21L1 | 04/09/2018 | 04/09/2018 | 6 | 0 | 6 | 04/18/2018 | 04/18/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  | 3/20/2019 | Connected |  | N
National Grid | MARLBOROUGH | 703816 | 01752 | 6 | Solar | 05_14_53J4 | 07/09/2025 | 07/23/2025 | 4 | 0 | 4 | 08/01/2025 | 08/01/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | MALDEN | 673030 | 02148 | 5.76 | Solar | 05_14_63L1 | 02/19/2025 | 03/14/2025 | 5 | 0 | 5 | 03/17/2025 | 03/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | DRACUT | 647929 | 01826 | 9.6 | Solar | 05_14_77L1 | 10/18/2024 |  | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 718439 | 01841 | 5.76 | Solar | 05_01_225W3 | 09/11/2025 | 09/26/2025 | 4 | 0 | 4 | 11/04/2025 | 11/04/2025 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 294263 | 01844 | 10 | Solar | 05_01_304W6 | 06/02/2020 | 06/15/2020 | 8 | 8 | 0 | 06/16/2020 | 06/16/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2021 | Connected |  | N
National Grid | LOWELL | 533391 | 01854 | 16.24 | Solar | 05_01_415L3 | 06/13/2023 | 06/20/2023 | 4 | 2 | 2 | 06/21/2023 | 06/21/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2023 | Connected |  | N
National Grid | LEOMINSTER | 218065 | 01453 | 792.6 | Solar | 05_01_6W2 | 06/07/2019 | 09/17/2019 | 70 | 69 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2019 | 10/04/2019 | 12 | 3 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 | 06/07/2019 | 4/27/2023 | Y | STD | 782 | 06/04/2021 | 03/09/2023 | 644 | 7 | 637 | 3/10/2023 | 4/3/2023 | 4/17/2023 | Connected |  | N
National Grid | SUTTON | 285962 | 01590 | 15.2 | Solar | 05_05_19W73 | 03/31/2020 | 04/01/2020 | 0 | 0 | 0 | 04/02/2020 | 04/02/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 |  | 4/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2020 | Connected |  | N
National Grid | STURBRIDGE | 597028 | 01566 | 46.5 | Solar | 05_05_317W6 | 03/22/2024 | 05/17/2024 | 26 | 19 | 7 | 05/20/2024 | 05/20/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2024 | Connected |  | N
National Grid | WORCESTER | 476941 | 01603 | 9.074 | Solar | 05_12_37W7 | 11/11/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 | 11/11/2022 | 1/23/2024 | Y | EXP | 365 | 07/01/2023 | 11/03/2023 | 126 | 0 | 126 |  |  | 11/14/2023 | Connected |  | N
National Grid | DIGHTON | 193380 | 02715 | 7.6 | Solar | 05_14_21L1 | 10/18/2018 | 10/24/2018 | 4 | 4 | 0 | 10/25/2018 | 10/25/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 | 10/18/2018 | 7/15/2021 | Y | EXP | 365 | 11/14/2020 | 12/10/2020 | 26 | 0 | 26 |  |  | 12/29/2020 | Connected |  | N
National Grid | MARLBOROUGH | 688403 | 01752 | 12.54 | Solar | 05_14_53J5 | 05/05/2025 | 06/09/2025 | 22 | 18 | 4 | 06/10/2025 | 06/10/2025 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 | 05/05/2025 | 1/15/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MALDEN | 674798 | 02148 | 11.4 | Solar | 05_14_63L1 | 04/10/2025 | 04/28/2025 | 10 | 6 | 4 | 04/29/2025 | 04/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | DRACUT | 654048 | 01826 | 9.6 | Solar | 05_14_77L1 | 11/13/2024 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 724994 | 01841 | 7.6 | Solar | 05_01_225W3 | 10/08/2025 | 10/14/2025 | 1 | 0 | 1 | 10/29/2025 | 10/29/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | LAWRENCE | 305873 | 01841 | 1750 | Solar | 05_01_304W6 | 10/05/2020 | 10/21/2020 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2020 | 11/16/2020 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 657366 | 01854 | 7.6 | Solar | 05_01_415L3 | 11/27/2024 | 12/20/2024 | 5 | 0 | 5 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/27/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 219190 | 01453 | 3.8 | Solar | 05_01_6W2 | 04/11/2019 | 06/26/2019 | 4 | 0 | 4 | 06/27/2019 | 06/27/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 328690 | 01590 | 8.19 | Solar | 05_05_19W73 | 12/22/2020 | 12/28/2020 | 2 | 2 | 0 | 12/29/2020 | 12/29/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 | 12/22/2020 | 5/30/2022 | Y | EXP | 365 | 03/25/2021 | 04/30/2021 | 36 | 0 | 36 |  |  | 12/13/2021 | Connected |  | N
National Grid | STURBRIDGE | 430828 | 01566 | 237.5 | Solar | 05_05_317W7 | 05/25/2022 | 06/24/2022 | 20 | 14 | 6 | 06/27/2022 | 06/27/2022 | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2022 | 05/25/2022 | 7/7/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 656154 | 01603 | 10 | Solar | 05_12_37W7 | 11/25/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/25/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | DIGHTON | 285172 | 02764 | 5 | Solar | 05_14_21L1 | 04/01/2020 | 05/28/2020 | 5 | 4 | 1 | 05/29/2020 | 05/29/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 04/01/2020 | 5/28/2021 | Y | EXP | 365 | 10/24/2020 | 11/19/2020 | 26 | 0 | 26 |  |  | 11/20/2020 | Connected |  | N
National Grid | MARLBOROUGH | 699286 | 01752 | 7.6 | Solar | 05_14_53J5 | 06/19/2025 | 07/03/2025 | 1 | 0 | 1 | 07/15/2025 | 07/15/2025 | 53 | 38 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MALDEN | 674773 | 02148 | 11.5 | Solar | 05_14_63L1 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | DRACUT | 657225 | 01826 | 6.38 | Solar | 05_14_77L1 | 12/02/2024 | 12/29/2024 | 7 | 3 | 4 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/02/2024 | 3/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | METHUEN | 294875 | 01844 | 4947 | Other | 05_01_225W4 | 10/05/2020 | 10/07/2020 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/08/2020 | 11/02/2020 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2023 | 10/05/2020 | 9/24/2027 | Y | STD | 673 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LAWRENCE | 308498 | 01841 | 4990 | Solar | 05_01_304W6 | 09/14/2020 | 09/28/2020 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/29/2020 | 10/24/2020 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 681045 | 01854 | 11.5 | Solar | 05_01_415L3 | 03/27/2025 | 04/01/2025 | 3 | 0 | 3 | 04/02/2025 | 04/02/2025 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2025 | Connected |  | N
National Grid | LEOMINSTER | 236417 | 01453 | 7.6 | Solar | 05_01_6W2 | 06/27/2019 | 07/05/2019 | 5 | 5 | 0 | 07/08/2019 | 07/08/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2019 | 06/27/2019 | 6/27/2020 | Y | EXP | 365 | 03/28/2020 | 04/22/2020 | 25 | 0 | 25 |  |  | 4/24/2020 | Connected |  | N
National Grid | SUTTON | 342952 | 01590 | 11.4 | Solar | 05_05_19W73 | 02/18/2021 | 02/25/2021 | 4 | 0 | 4 | 02/26/2021 | 02/26/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2021 | Connected |  | N
National Grid | STURBRIDGE | 175489 | 01566 | 16.8 | Solar | 05_05_317W7 | 07/23/2014 | 07/23/2014 | 7 | 7 | 0 | 08/04/2014 | 08/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2014 |  | 10/31/2014 | N | EXP | 53 |  |  | 0 | 0 | 0 | 9/8/2014 | 9/8/2014 | 12/11/2015 | Connected |  | N
National Grid | WORCESTER | 304213 | 01603 | 6 | Solar | 05_12_37W8 | 09/24/2020 | 12/23/2020 | 61 | 40 | 21 | 12/24/2020 | 12/24/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 368249 | 02777 | 7.6 | Solar | 05_14_21L1 | 07/07/2021 | 07/29/2021 | 17 | 16 | 1 | 07/30/2021 | 07/30/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2021 |  | 9/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2022 | Connected |  | N
National Grid | MARLBOROUGH | 381732 | 01752 | 6 | Solar | 05_14_53J5 | 09/23/2021 | 01/03/2022 | 4 | 0 | 4 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 | 09/23/2021 | 5/28/2023 | Y | EXP | 365 | 04/14/2022 | 05/21/2022 | 36 | 0 | 36 |  |  | 6/30/2022 | Connected |  | Y
National Grid | MALDEN | 674155 | 02148 | 5.76 | Solar | 05_14_63L1 | 02/25/2025 | 03/06/2025 | 3 | 0 | 3 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 664857 | 01826 | 6.5 | Solar | 05_14_77L1 | 01/09/2025 | 01/23/2025 | 4 | 0 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/09/2025 | 4/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | LAWRENCE | 627849 | 01841 | 6 | Solar | 05_01_225W4 | 07/27/2024 | 08/08/2024 | 1 | 0 | 1 | 08/09/2024 | 08/09/2024 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 | 07/27/2024 | 9/24/2025 | Y | EXP | 365 | 11/06/2024 | 11/18/2024 | 13 | 0 | 13 |  |  |  | Completion Documents |  | Y
National Grid | METHUEN | 310798 | 01844 | 4990 | Solar | 05_01_304W6 | 09/17/2020 | 09/30/2020 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/26/2020 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174965 | 01854 | 130 | Solar | 05_01_4J324 | 08/30/2013 | 08/30/2013 | 7 | 0 | 7 | 09/12/2013 | 09/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2013 |  | 11/29/2013 | N | EXP | 63 |  |  | 0 | 0 | 0 | 2/20/2014 | 2/20/2014 | 2/20/2014 | Connected |  | N
National Grid | LEOMINSTER | 256583 | 01453 | 3.8 | Solar | 05_01_6W2 | 10/08/2019 | 10/09/2019 | 0 | 0 | 0 | 10/10/2019 | 10/10/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  | 10/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2020 | Connected |  | N
National Grid | SUTTON | 342591 | 01590 | 499 | Solar | 05_05_19W73 | 03/22/2021 | 04/22/2021 | 22 | 12 | 10 |  |  | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 714695 | 01566 | 7.6 | Solar | 05_05_317W8 | 08/26/2025 | 09/16/2025 | 5 | 2 | 3 | 11/25/2025 | 11/25/2025 | 36 | 22 | 14 | 02/13/2026 | 03/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 03/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 3/12/2026 |  | 3/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 387541 | 01603 | 7.6 | Solar | 05_12_37W8 | 10/10/2021 |  | 147 | 137 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 372068 | 02715 | 15.2 | Solar | 05_14_21L1 | 07/26/2021 | 07/28/2021 | 3 | 2 | 1 | 07/29/2021 | 07/29/2021 | 64 | 43 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 | 07/26/2021 | 9/5/2023 | Y | EXP | 365 | 01/18/2022 | 09/02/2022 | 227 | 0 | 227 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 522777 | 01752 | 3.8 | Solar | 05_14_53J5 | 05/17/2023 | 05/19/2023 | 2 | 2 | 0 | 05/22/2023 | 05/22/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 7/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2023 | Connected |  | N
National Grid | MALDEN | 677396 | 02148 | 7.6 | Solar | 05_14_63L1 | 03/12/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 670340 | 01879 | 7.6 | Solar | 05_14_77L1 | 02/10/2025 | 03/03/2025 | 2 | 0 | 2 | 03/04/2025 | 03/04/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 | 02/10/2025 | 4/21/2026 | Y | EXP | 365 | 07/24/2025 | 12/22/2025 | 152 | 0 | 152 |  |  | 11/24/2025 | Connected |  | N
National Grid | LAWRENCE | 665675 | 01841 | 0 | Other | 05_01_225W4 | 07/22/2025 | 09/15/2025 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2025 | 10/03/2025 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LAWRENCE | 348697 | 01841 | 9.28 | Solar | 05_01_304W6 | 04/06/2021 | 04/07/2021 | 0 | 0 | 0 | 04/08/2021 | 04/08/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2021 |  | 7/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2022 | Connected |  | N
National Grid | LOWELL | 175149 | 01854 | 50 | Solar | 05_01_4J324 | 10/21/2013 | 10/21/2013 | 8 | 0 | 8 | 11/01/2013 | 11/01/2013 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2014 |  | 1/6/2017 | N | EXP | 1085 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 265671 | 01453 | 7.6 | Solar | 05_01_6W2 | 12/04/2019 | 12/17/2019 | 9 | 9 | 0 | 12/18/2019 | 12/18/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2019 |  | 5/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2020 | Connected |  | N
National Grid | SUTTON | 381880 | 01590 | 7.54 | Solar | 05_05_19W73 | 09/16/2021 | 12/30/2021 | 15 | 13 | 2 | 10/08/2021 | 10/08/2021 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/16/2021 | 1/20/2023 | Y | EXP | 365 | 01/04/2022 | 01/13/2022 | 10 | 0 | 10 |  |  | 2/4/2022 | Connected |  | N
National Grid | WORCESTER | 717150 | 01610 | 12.92 | Solar | 05_05_317W8 | 09/05/2025 | 09/23/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 | 09/05/2025 | 1/20/2027 | Y | EXP | 365 | 02/07/2026 | 02/13/2026 | 7 | 0 | 7 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 662091 | 01602 | 3.8 | Solar | 05_12_37W8 | 12/20/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 403830 | 02715 | 50 | Solar | 05_14_21L1 | 01/11/2022 | 02/02/2022 | 16 | 10 | 6 | 02/03/2022 | 02/03/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2022 | 01/11/2022 | 10/9/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2022 | Connected |  | N
National Grid | MARLBOROUGH | 500876 | 01752 | 120 | Solar | 05_14_54L3 | 03/31/2023 | 04/17/2023 | 10 | 0 | 10 | 04/18/2023 | 04/18/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 03/31/2023 | 3/28/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | MALDEN | 679876 | 02148 | 11.5 | Solar | 05_14_63L1 | 03/21/2025 | 04/23/2025 | 23 | 20 | 3 | 04/24/2025 | 04/24/2025 | 68 | 24 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 699607 | 01879 | 9.28 | Solar | 05_14_77L1 | 06/18/2025 | 07/02/2025 | 2 | 0 | 2 | 09/05/2025 | 09/05/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2026 | Connected |  | N
National Grid | METHUEN | 705025 | 01844 | 0 | Other | 05_01_225W4 | 09/24/2025 | 11/06/2025 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/07/2025 | 12/08/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 382260 | 01844 | 7.6 | Solar | 05_01_304W6 | 09/15/2021 | 09/17/2021 | 2 | 1 | 1 | 09/20/2021 | 09/20/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 3/17/2023 | N | EXP | 500 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 178291 | 01854 | 200 | Solar | 05_01_4J324 | 03/28/2018 | 04/20/2018 | 15 | 15 | 0 | 04/20/2018 | 04/20/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  | 12/2/2019 | N | EXP | 382 |  |  | 0 | 0 | 0 |  |  | 11/7/2019 | Connected |  | N
National Grid | LEOMINSTER | 274538 | 01453 | 48 | Natural Gas | 05_01_6W2 | 02/19/2021 | 03/05/2021 | 9 | 0 | 9 | 03/08/2021 | 03/08/2021 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 |  | 6/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2021 | Connected |  | N
National Grid | SUTTON | 392747 | 01590 | 9.8 | Solar | 05_05_19W73 | 11/24/2021 | 01/06/2022 | 3 | 0 | 3 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 728722 | 01610 | 11.5 | Solar | 05_05_317W8 | 10/23/2025 | 10/27/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 662931 | 01602 | 3.8 | Solar | 05_12_37W8 | 12/30/2024 | 01/16/2025 | 5 | 0 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 414979 | 02777 | 15.2 | Solar | 05_14_21L1 | 03/02/2022 | 03/23/2022 | 16 | 15 | 1 | 03/24/2022 | 03/24/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 702988 | 01752 | 11.78 | Solar | 05_14_54L3 | 07/06/2025 | 09/04/2025 | 43 | 42 | 1 | 09/05/2025 | 09/05/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MALDEN | 681026 | 02148 | 11.5 | Solar | 05_14_63L1 | 03/27/2025 | 04/01/2025 | 3 | 0 | 3 | 04/02/2025 | 04/02/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 705084 | 01826 | 3.8 | Solar | 05_14_77L1 | 07/15/2025 | 08/13/2025 | 3 | 0 | 3 | 08/14/2025 | 08/14/2025 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 | 07/15/2025 | 11/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2026 | Connected |  | N
National Grid | ANDOVER | 750877 | 01810 | 11.5 | Solar | 05_01_225W4 | 02/12/2026 | 02/17/2026 | 2 | 0 | 2 | 02/18/2026 | 02/18/2026 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 457862 | 01844 | 1800 | Solar | 05_01_304W6 | 11/03/2022 | 11/17/2022 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2022 | 12/15/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 184789 | 01854 | 249.8 | Solar | 05_01_4J324 | 05/08/2017 | 05/08/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/23/2018 | 03/12/2019 | 135 | 21 | 114 |  |  | 0 | 0 | 0 | 03/12/2019 | 135 | 21 | 114 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 291970 | 01453 | 3.8 | Solar | 05_01_6W2 | 06/16/2020 | 06/17/2020 | 0 | 0 | 0 | 06/18/2020 | 06/18/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2020 |  | 6/16/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 437709 | 01590 | 999 | Solar | 05_05_19W73 | 08/15/2022 | 09/13/2022 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2022 | 10/05/2022 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2024 | 08/15/2022 | 10/31/2025 | Y | STD | 392 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176029 | 01608 | 23.75 | Solar | 05_05_317W8 | 06/16/2015 | 06/16/2015 | 22 | 22 | 0 | 07/21/2015 | 07/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 |  | 6/22/2016 | N | EXP | 330 |  |  | 0 | 0 | 0 | 12/10/2015 | 12/10/2015 | 12/10/2015 | Connected |  | N
National Grid | WORCESTER | 701523 | 01602 | 6.631 | Solar | 05_12_37W8 | 06/27/2025 | 07/01/2025 | 2 | 0 | 2 | 07/02/2025 | 07/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | DIGHTON | 490227 | 02715 | 7.6 | Solar | 05_14_21L1 | 01/06/2023 | 01/09/2023 | 1 | 0 | 1 | 01/10/2023 | 01/10/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 734376 | 01752 | 37.82 | Solar | 05_14_54L3 | 11/17/2025 | 11/18/2025 | 1 | 0 | 1 | 11/19/2025 | 11/19/2025 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MALDEN | 685181 | 02148 | 5.76 | Solar | 05_14_63L1 | 04/15/2025 | 04/25/2025 | 8 | 4 | 4 | 04/28/2025 | 04/28/2025 | 38 | 24 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 558618 | 01826 | 240 | Solar | 05_14_77L2 | 09/29/2023 | 10/23/2023 | 15 | 6 | 9 | 10/24/2023 | 10/24/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 | 09/29/2023 | 5/6/2026 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | ANDOVER | 174798 | 01810 | 400 | Solar | 05_01_225W4 | 08/29/2012 | 08/29/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 473792 | 01844 | 9.28 | Solar | 05_01_304W6 | 12/07/2022 | 12/14/2022 | 6 | 5 | 1 | 12/15/2022 | 12/15/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 1/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2023 | Connected |  | N
National Grid | LOWELL | 197101 | 01854 | 25 | Solar | 05_01_4J324 | 09/27/2018 | 10/04/2018 | 8 | 5 | 3 | 10/11/2018 | 10/11/2018 | 29 | 18 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  | 10/2/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 318228 | 01453 | 10 | Solar | 05_01_6W2 | 11/02/2020 | 11/13/2020 | 7 | 6 | 1 | 11/16/2020 | 11/16/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/02/2020 | 10/14/2022 | Y | EXP | 365 | 07/02/2021 | 10/13/2021 | 104 | 3 | 101 |  |  | 1/10/2022 | Connected |  | N
National Grid | MILLBURY | 461180 | 01527 | 10 | Solar | 05_05_19W73 | 10/18/2022 | 10/20/2022 | 2 | 0 | 2 | 10/21/2022 | 10/21/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 |  | 2/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2023 | Connected |  | N
National Grid | WORCESTER | 343536 | 01608 | 100 | Solar | 05_05_317W8 | 02/26/2021 | 03/15/2021 | 10 | 0 | 10 | 03/16/2021 | 03/16/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2021 |  | 7/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2022 | Connected |  | N
National Grid | WORCESTER | 178254 | 01602 | 33.3 | Solar | 05_12_37W9 | 03/12/2018 | 03/12/2018 | 28 | 0 | 28 | 05/08/2018 | 05/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 |  | 4/2/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 12/19/2018 | Connected |  | N
National Grid | DIGHTON | 626584 | 02715 | 3.8 | Solar | 05_14_21L1 | 07/22/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/22/2024 | 8/29/2025 | Y | EXP | 365 | 09/19/2024 | 10/11/2024 | 23 | 0 | 23 |  |  | 11/22/2024 | Connected |  | N
National Grid | MARLBOROUGH | 175182 | 01752 | 490 | Solar | 05_14_54L3 | 05/09/2013 | 05/09/2013 | 7 | 0 | 7 | 05/21/2013 | 05/21/2013 | 419 | 4 | 415 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2013 |  | 12/31/2013 | N | EXP | 181 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 692844 | 02148 | 10 | Solar | 05_14_63L1 | 05/20/2025 | 06/23/2025 | 3 | 0 | 3 | 06/24/2025 | 06/24/2025 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 05/20/2025 | 8/29/2026 | Y | EXP | 365 | 11/21/2025 | 11/24/2025 | 4 | 0 | 4 |  |  | 11/24/2025 | Connected |  | N
National Grid | DRACUT | 558966 | 01826 | 200 | Solar | 05_14_77L2 | 10/05/2023 | 10/23/2023 | 11 | 2 | 9 | 10/24/2023 | 10/24/2023 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 10/05/2023 | 1/1/2027 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | ANDOVER | 174890 | 01810 | 300 | Solar | 05_01_225W4 | 10/12/2012 | 10/12/2012 | 7 | 0 | 7 | 10/24/2012 | 10/24/2012 | 916 | 0 | 916 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2013 |  | 10/31/2013 | N | EXP | 241 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 570231 | 01844 | 10 | Solar | 05_01_304W6 | 11/16/2023 | 11/21/2023 | 3 | 1 | 2 | 11/22/2023 | 11/22/2023 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2024 | 11/16/2023 | 1/31/2025 | Y | EXP | 365 | 06/05/2024 | 08/28/2024 | 85 | 0 | 85 |  |  | 9/5/2024 | Connected |  | N
National Grid | LOWELL | 202335 | 01854 | 72 | Solar | 05_01_4J324 | 11/29/2018 | 12/04/2018 | 2 | 0 | 2 | 12/05/2018 | 12/05/2018 | 17 | 13 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 12/17/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 324658 | 01453 | 3.8 | Solar | 05_01_6W2 | 11/27/2020 | 12/02/2020 | 2 | 0 | 2 | 12/03/2020 | 12/03/2020 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 480346 | 01590 | 5.22 | Solar | 05_05_19W73 | 01/09/2023 | 01/27/2023 | 13 | 10 | 3 | 01/30/2023 | 01/30/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 | 01/09/2023 | 6/23/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2023 | Connected |  | Y
National Grid | WORCESTER | 625321 | 01609 | 0 | Other | 05_05_318W1 | 01/16/2025 | 05/01/2025 | 72 | 63 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2025 | 05/30/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 178283 | 01603 | 133.2 | Solar | 05_12_37W9 | 03/12/2018 | 03/12/2018 | 8 | 0 | 8 | 05/09/2018 | 05/09/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 |  | 4/2/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 1/25/2019 | Connected |  | N
National Grid | DIGHTON | 626563 | 02715 | 0 | Battery Add-On | 05_14_21L1 | 07/23/2024 | 08/14/2024 | 6 | 0 | 6 | 08/15/2024 | 08/15/2024 | 33 | 21 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 10/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | MARLBOROUGH | 175885 | 01752 | 6.75 | Solar | 05_14_54L3 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 | 05/26/2015 | 05/26/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2015 |  | 10/30/2015 | N | EXP | 151 |  |  | 0 | 0 | 0 | 8/26/2015 | 8/26/2015 | 9/1/2015 | Connected |  | N
National Grid | EVERETT | 730850 | 02149 | 5.76 | Solar | 05_14_63L1 | 11/03/2025 | 11/10/2025 | 5 | 0 | 5 | 11/12/2025 | 11/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2026 | Connected |  | N
National Grid | DRACUT | 733768 | 01826 | 17.48 | Solar | 05_14_77L2 | 11/17/2025 | 12/10/2025 | 2 | 0 | 2 | 12/23/2025 | 12/23/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 | 11/17/2025 | 3/17/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | ANDOVER | 175026 | 01810 | 400 | Solar | 05_01_225W4 | 10/12/2012 | 10/12/2012 | 7 | 0 | 7 | 10/24/2012 | 10/24/2012 | 704 | 0 | 704 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2013 |  | 6/3/2013 | N | EXP | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 634466 | 01841 | 15.705 | Solar | 05_01_304W6 | 08/27/2024 | 08/29/2024 | 2 | 0 | 2 | 08/30/2024 | 08/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2024 | Connected |  | N
National Grid | LOWELL | 321058 | 01854 | 75 | Natural Gas | 05_01_4J324 | 11/20/2020 | 12/07/2020 | 9 | 0 | 9 |  |  | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 |  | 4/27/2023 | N | STD | 187 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | LEOMINSTER | 325927 | 01453 | 7.68 | Solar | 05_01_6W2 | 01/29/2021 | 02/08/2021 | 5 | 5 | 0 | 02/09/2021 | 02/09/2021 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2021 |  | 2/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2021 | Connected |  | N
National Grid | SUTTON | 482133 | 01590 | 8.12 | Solar | 05_05_19W73 | 12/16/2022 | 12/20/2022 | 3 | 2 | 1 | 12/21/2022 | 12/21/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/16/2022 | 3/20/2024 | Y | EXP | 365 | 02/11/2023 | 03/17/2023 | 35 | 0 | 35 |  |  | 6/16/2023 | Connected |  | N
National Grid | WORCESTER | 174933 | 01610 | 371.2 | Solar | 05_05_318W1 | 08/29/2013 | 08/29/2013 | 7 | 0 | 7 | 09/11/2013 | 09/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2014 | 08/29/2013 | 10/30/2014 | Y | EXP | 290 | 04/02/2015 | 04/10/2015 | 6 | 0 | 6 | 5/22/2015 | 5/22/2015 | 5/22/2015 | Connected |  | N
National Grid | WORCESTER | 178308 | 01603 | 3807.99 | Natural Gas | 05_12_37W9 | 01/10/2018 | 03/30/2018 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2018 | 04/26/2018 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 |  | 6/7/2019 | N | STD | 149 |  |  | 0 | 0 | 0 | 5/31/2019 | 5/30/2019 | 6/7/2019 | Connected |  | N
National Grid | DIGHTON | 640655 | 02715 | 7.475 | Solar | 05_14_21L1 | 09/17/2024 | 10/03/2024 | 1 | 0 | 1 | 10/04/2024 | 10/04/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 09/17/2024 | 11/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | MARLBOROUGH | 177008 | 01752 | 494.5 | Solar | 05_14_54L3 | 10/13/2016 | 10/13/2016 | 0 | 0 | 0 | 10/14/2016 | 10/14/2016 | 0 | 0 | 0 | 02/16/2017 | 03/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2017 | 10/13/2016 | 4/9/2018 | Y | EXP | 374 | 06/01/2017 | 06/01/2017 | 0 | 0 | 0 | 4/3/2018 | 4/3/2018 | 4/3/2018 | Connected |  | N
National Grid | EVERETT | 646555 | 02149 | 9.86 | Solar | 05_14_63L2 | 10/15/2024 | 10/28/2024 | 6 | 3 | 3 | 10/29/2024 | 10/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/15/2024 | 12/19/2025 | Y | EXP | 365 | 04/01/2025 | 10/15/2025 | 198 | 0 | 198 |  |  |  | Completion Documents |  | Y
National Grid | TYNGSBORO | 750324 | 01879 | 7.6 | Solar | 05_14_77L2 | 02/10/2026 | 02/11/2026 | 3 | 0 | 3 | 02/24/2026 | 02/24/2026 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 175736 | 01810 | 27 | Solar | 05_01_225W4 | 08/14/2014 | 08/14/2014 | 7 | 0 | 7 | 08/26/2014 | 08/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2014 | 08/14/2014 | 11/28/2014 | Y | EXP | 58 | 12/10/2014 | 12/23/2014 | 9 | 0 | 9 | 10/6/2014 | 10/6/2014 | 1/12/2015 | Connected |  | N
National Grid | METHUEN | 644551 | 01844 | 10 | Solar | 05_01_304W6 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/02/2024 | 6/19/2026 | Y | EXP | 365 | 11/14/2025 | 02/13/2026 | 92 | 0 | 92 |  |  | 1/14/2026 | Connected |  | N
National Grid | LOWELL | 174963 | 01854 | 60 | Solar | 05_01_4J336 | 08/30/2013 | 08/30/2013 | 7 | 0 | 7 | 09/12/2013 | 09/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2013 |  | 11/29/2013 | N | EXP | 25 |  |  | 0 | 0 | 0 | 2/28/2014 | 2/28/2014 | 2/28/2014 | Connected |  | N
National Grid | LEOMINSTER | 336649 | 01453 | 7.6 | Solar | 05_01_6W2 | 01/25/2021 | 01/27/2021 | 1 | 0 | 1 | 01/28/2021 | 01/28/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2021 | 01/25/2021 | 1/26/2022 | Y | EXP | 365 | 05/27/2021 | 05/28/2021 | 1 | 0 | 1 |  |  | 8/11/2021 | Connected |  | N
National Grid | SUTTON | 484704 | 01590 | 8.7 | Solar | 05_05_19W73 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 17 | 3 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2023 | 01/10/2023 | 4/14/2024 | Y | EXP | 365 | 03/04/2023 | 04/13/2023 | 41 | 0 | 41 |  |  | 7/17/2023 | Connected |  | N
National Grid | WORCESTER | 177383 | 01610 | 366.3 | Solar | 05_05_318W1 | 11/28/2016 | 11/28/2016 | 0 | 0 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 |  | 12/4/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 | 6/22/2017 | 6/22/2017 | 6/27/2017 | Connected |  | N
National Grid | WORCESTER | 253372 | 01603 | 7.6 | Solar | 05_12_37W9 | 09/14/2019 | 09/17/2019 | 1 | 1 | 0 | 09/18/2019 | 09/18/2019 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 9/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 647295 | 02715 | 5.76 | Solar | 05_14_21L1 | 10/22/2024 | 11/14/2024 | 4 | 0 | 4 | 11/15/2024 | 11/15/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | MARLBOROUGH | 178419 | 01752 | 19 | Solar | 05_14_54L3 | 01/16/2018 | 01/16/2018 | 23 | 0 | 23 | 02/20/2018 | 02/20/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2018 |  | 1/22/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 11/7/2018 | Connected |  | N
National Grid | EVERETT | 711911 | 02149 | 249 | Solar | 05_14_63L2 | 08/13/2025 | 09/05/2025 | 16 | 7 | 9 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | DRACUT | 178138 | 01826 | 3.8 | Solar | 05_14_77L2 | 03/22/2018 | 03/22/2018 | 4 | 4 | 0 | 03/29/2018 | 03/29/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2018 |  | 3/28/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 9/4/2019 | Connected |  | N
National Grid | ANDOVER | 176068 | 01810 | 7.6 | Solar | 05_01_225W4 | 06/19/2015 | 06/19/2015 | 6 | 6 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 | 06/19/2015 | 6/27/2016 | Y | EXP | 346 | 03/14/2016 | 03/23/2016 | 6 | 0 | 6 | 11/13/2015 | 11/13/2015 | 4/27/2016 | Connected |  | N
National Grid | METHUEN | 657952 | 01844 | 10 | Solar | 05_01_304W6 | 12/02/2024 |  | 68 | 63 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 514581 | 01854 | 9.6 | Solar | 05_01_4J336 | 03/30/2023 | 05/30/2023 | 41 | 40 | 1 | 05/31/2023 | 05/31/2023 | 35 | 13 | 22 | 08/07/2023 | 03/28/2024 | 162 | 28 | 134 |  |  | 0 | 0 | 0 | 03/28/2024 | 162 | 28 | 134 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 336435 | 01453 | 10 | Solar | 05_01_6W2 | 03/17/2021 | 03/24/2021 | 4 | 0 | 4 | 03/25/2021 | 03/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 486122 | 01590 | 10 | Solar | 05_05_19W73 | 01/03/2023 | 01/04/2023 | 1 | 0 | 1 | 01/05/2023 | 01/05/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2023 |  | 2/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | WORCESTER | 178048 | 01610 | 750 | Solar | 05_05_318W1 | 05/05/2017 | 05/05/2017 | 15 | 13 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2017 | 06/15/2017 | 12 | 0 | 12 |  | 0 | 0 | 0 | 01/16/2018 | 10/25/2019 | 449 | 20 | 429 | 12/21/2018 | 05/05/2017 | 2/19/2021 | Y | STD | 500 | 01/04/2020 | 12/16/2020 | 347 | 5 | 342 |  |  | 2/12/2021 | Connected |  | N
National Grid | WORCESTER | 384620 | 01603 | 1266 | Solar | 05_12_37W9 | 08/10/2022 |  | 231 | 63 | 168 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 654926 | 02764 | 3.8 | Solar | 05_14_21L1 | 11/20/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/20/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | MARLBOROUGH | 178410 | 01752 | 34.5 | Solar | 05_14_54L3 | 11/22/2017 | 11/22/2017 | 8 | 0 | 8 | 12/07/2017 | 12/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 |  | 12/2/2018 | N | EXP | 193 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 752801 | 02149 | 3.8 | Solar | 05_14_63L2 | 02/24/2026 | 03/02/2026 | 3 | 0 | 3 | 03/25/2026 | 03/25/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | TYNGSBORO | 199543 | 01879 | 10 | Solar | 05_14_77L2 | 10/26/2018 | 01/03/2019 | 32 | 28 | 4 | 01/04/2019 | 01/04/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 6/17/2019 | N | EXP | 151 |  |  | 0 | 0 | 0 |  |  | 6/1/2019 | Connected |  | N
National Grid | ANDOVER | 176260 | 01810 | 10 | Solar | 05_01_225W4 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/12/2016 | N | EXP | 353 |  |  | 0 | 0 | 0 | 9/25/2015 | 9/25/2015 | 3/17/2016 | Connected |  | N
National Grid | METHUEN | 660387 | 01844 | 10 | Solar | 05_01_304W6 | 12/12/2024 | 12/30/2024 | 3 | 1 | 2 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | LOWELL | 616884 | 01854 | 5.76 | Solar | 05_01_4J336 | 06/10/2024 | 06/21/2024 | 1 | 0 | 1 | 06/24/2024 | 06/24/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2024 | Connected |  | N
National Grid | LEOMINSTER | 357858 | 01453 | 2.88 | Solar | 05_01_6W2 | 05/20/2021 | 05/25/2021 | 2 | 0 | 2 | 05/26/2021 | 05/26/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2021 |  | 11/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2023 | Connected |  | N
National Grid | SUTTON | 498979 | 01590 | 7.54 | Solar | 05_05_19W73 | 03/08/2023 | 03/10/2023 | 2 | 0 | 2 | 03/13/2023 | 03/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2023 |  | 4/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | N
National Grid | WORCESTER | 178327 | 01610 | 1300 | Solar | 05_05_318W1 | 03/30/2018 | 03/30/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 06/18/2018 | 54 | 32 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/4/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 592425 | 01603 | 6 | Solar | 05_12_37W9 | 03/04/2024 | 03/05/2024 | 1 | 0 | 1 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 03/04/2024 | 3/12/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 657560 | 02764 | 5.76 | Solar | 05_14_21L1 | 11/28/2024 | 12/13/2024 | 3 | 0 | 3 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/28/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 190956 | 01532 | 77 | Solar | 05_14_54L3 | 07/17/2018 | 08/03/2018 | 9 | 6 | 3 | 08/06/2018 | 08/06/2018 | 9 | 0 | 9 | 10/05/2018 | 10/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 |  | 10/1/2019 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  | 12/16/2019 | Connected |  | N
National Grid | EVERETT | 174297 | 02149 | 1800 | Solar | 05_14_63L2 | 12/23/2011 | 12/23/2011 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2012 | 04/25/2012 | 42 | 0 | 42 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2012 | 12/23/2011 | 9/1/2012 | Y | STD | 114 | 10/21/2013 | 01/02/2014 | 49 | 0 | 49 | 12/31/2013 | 12/31/2013 | 2/7/2014 | Connected |  | N
National Grid | DRACUT | 416317 | 01826 | 7.68 | Solar | 05_14_77L2 | 03/16/2022 | 03/23/2022 | 5 | 0 | 5 | 03/24/2022 | 03/24/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 176887 | 01810 | 10 | Solar | 05_01_225W4 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 187 | 0 | 187 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2015 |  | 11/18/2016 | N | EXP | 350 |  |  | 0 | 0 | 0 | 12/4/2015 | 12/4/2015 |  | Withdrawn |  | N
National Grid | METHUEN | 667531 | 01844 | 4990 | Other | 05_01_304W6 | 02/25/2025 | 03/31/2025 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/01/2025 | 04/29/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 636567 | 01854 | 10 | Solar | 05_01_4J336 | 08/29/2024 | 09/09/2024 | 3 | 0 | 3 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | LEOMINSTER | 390140 | 01453 | 9.8 | Solar | 05_01_6W2 | 11/11/2021 | 12/16/2021 | 3 | 0 | 3 | 11/17/2021 | 11/17/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 11/11/2021 | 6/8/2023 | Y | EXP | 365 | 03/31/2022 | 06/03/2022 | 65 | 0 | 65 |  |  | 7/8/2022 | Connected |  | N
National Grid | SUTTON | 578440 | 01590 | 10 | Solar | 05_05_19W73 | 12/20/2023 | 01/03/2024 | 7 | 3 | 4 | 01/04/2024 | 01/04/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  | 2/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2024 | Connected |  | N
National Grid | WORCESTER | 482180 | 01610 | 1800 | Solar | 05_05_318W3 | 07/06/2023 | 10/25/2023 | 78 | 68 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 | 11/16/2023 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2026 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 638410 | 01602 | 10 | Solar | 05_12_37W9 | 09/06/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 |  | 11/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2024 | Connected |  | N
National Grid | DIGHTON | 668768 | 02715 | 10 | Solar | 05_14_21L1 | 02/04/2025 | 02/26/2025 | 2 | 0 | 2 | 02/27/2025 | 02/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 02/04/2025 | 4/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | MARLBOROUGH | 194950 | 01752 | 10 | Solar | 05_14_54L3 | 10/03/2018 | 10/04/2018 | 0 | 0 | 0 | 10/05/2018 | 10/05/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2018 |  | 10/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2019 | Connected |  | N
National Grid | EVERETT | 176912 | 02149 | 10 | Solar | 05_14_63L2 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 253 | 0 | 253 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 |  | 5/10/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 481185 | 01826 | 201.9 | Solar | 05_14_77L2 | 12/20/2022 | 03/14/2023 | 56 | 47 | 9 | 03/15/2023 | 03/15/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2023 | 12/20/2022 | 10/21/2024 | Y | EXP | 380 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | ANDOVER | 176962 | 01845 | 3.8 | Solar | 05_01_225W4 | 07/18/2016 | 07/18/2016 | 1 | 1 | 0 | 07/20/2016 | 07/20/2016 | 254 | 0 | 254 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 |  | 7/24/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 686174 | 01844 | 20 | Solar | 05_01_304W6 | 04/18/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid | LOWELL | 636464 | 01854 | 6 | Solar | 05_01_4J336 | 09/16/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | LEOMINSTER | 444419 | 01453 | 0 | Other | 05_01_6W2 | 03/14/2023 | 07/14/2023 | 84 | 74 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2023 | 08/09/2023 | 19 | 2 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 580411 | 01590 | 3.8 | Solar | 05_05_19W73 | 01/16/2024 | 01/19/2024 | 3 | 0 | 3 | 01/22/2024 | 01/22/2024 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 01/16/2024 | 2/20/2025 | Y | EXP | 365 | 04/17/2024 | 05/31/2024 | 45 | 0 | 45 |  |  | 10/14/2024 | Connected |  | N
National Grid | WORCESTER | 619605 | 01603 | 4980 | Solar | 05_05_318W3 | 07/17/2024 | 08/21/2024 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2024 | 08/29/2024 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 639926 | 01603 | 7.6 | Solar | 05_12_37W9 | 09/12/2024 | 10/04/2024 | 3 | 0 | 3 | 10/07/2024 | 10/07/2024 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 11/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2025 | Connected |  | N
National Grid | DIGHTON | 670942 | 02764 | 11.52 | Solar | 05_14_21L1 | 02/07/2025 | 03/11/2025 | 6 | 1 | 5 | 03/12/2025 | 03/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 02/07/2025 | 4/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 206827 | 01532 | 0 | Solar | 05_14_54L3 | 01/25/2019 | 02/11/2019 | 10 | 0 | 10 | 07/30/2019 | 07/30/2019 | 249 | 121 | 128 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/14/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 177064 | 02149 | 3.8 | Solar | 05_14_63L2 | 03/20/2017 | 03/20/2017 | 9 | 8 | 1 | 03/31/2017 | 03/31/2017 | 224 | 0 | 224 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 |  | 3/25/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 656692 | 01826 | 7.6 | Solar | 05_14_77L2 | 11/25/2024 | 01/17/2025 | 22 | 16 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 176995 | 01845 | 6 | Solar | 05_01_225W4 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 242 | 0 | 242 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 |  | 7/25/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 712153 | 01844 | 7.6 | Solar | 05_01_304W6 | 08/14/2025 | 09/16/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2026 | Connected |  | N
National Grid | LOWELL | 651217 | 01854 | 7.6 | Solar | 05_01_4J336 | 11/01/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 | 12/31/2024 | 03/25/2025 | 58 | 0 | 58 |  |  | 0 | 0 | 0 | 03/25/2025 | 58 | 0 | 58 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | LEOMINSTER | 445228 | 01453 | 9.57 | Solar | 05_01_6W2 | 08/03/2022 | 08/09/2022 | 4 | 0 | 4 | 08/10/2022 | 08/10/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 | 08/03/2022 | 5/9/2024 | Y | EXP | 365 | 04/20/2023 | 05/04/2023 | 15 | 0 | 15 |  |  | 5/21/2023 | Connected |  | N
National Grid | SUTTON | 622852 | 01590 | 10 | Solar | 05_05_19W73 | 07/09/2024 | 08/13/2024 | 4 | 1 | 3 | 08/14/2024 | 08/14/2024 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 692505 | 01603 | 3.8 | Solar | 05_05_318W3 | 05/18/2025 | 11/26/2025 | 1 | 0 | 1 | 02/09/2026 | 02/09/2026 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 650947 | 01603 | 5.76 | Solar | 05_12_37W9 | 11/04/2024 | 11/22/2024 | 4 | 0 | 4 | 11/25/2024 | 11/25/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | DIGHTON | 685406 | 02715 | 5.76 | Solar | 05_14_21L1 | 04/17/2025 | 04/23/2025 | 3 | 0 | 3 | 04/24/2025 | 04/24/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | BERLIN | 292996 | 01503 | 10 | Solar | 05_14_54L3 | 05/21/2020 | 05/22/2020 | 0 | 0 | 0 | 05/26/2020 | 05/26/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2020 |  | 5/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2020 | Connected |  | N
National Grid | EVERETT | 177138 | 02149 | 6 | Solar | 05_14_63L2 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2016 |  | 6/6/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 9/28/2016 | 9/28/2016 | 10/4/2016 | Connected |  | N
National Grid | DRACUT | 669826 | 01826 | 3.8 | Solar | 05_14_77L2 | 02/04/2025 | 02/14/2025 | 2 | 0 | 2 | 02/18/2025 | 02/18/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | ANDOVER | 177095 | 01810 | 7.6 | Solar | 05_01_225W4 | 01/20/2017 | 01/20/2017 | 2 | 2 | 0 | 01/25/2017 | 01/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2017 | 01/20/2017 | 1/28/2018 | Y | EXP | 366 | 06/15/2017 | 07/28/2017 | 30 | 0 | 30 | 8/28/2017 | 8/28/2017 | 8/28/2017 | Connected |  | N
National Grid | METHUEN | 711907 | 01844 | 32.5 | Solar | 05_01_304W6 | 08/13/2025 | 08/18/2025 | 3 | 0 | 3 | 08/19/2025 | 08/19/2025 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | LOWELL | 656348 | 01854 | 7.6 | Solar | 05_01_4J336 | 11/22/2024 | 03/04/2025 | 55 | 50 | 5 | 03/05/2025 | 03/05/2025 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 6/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | LEOMINSTER | 492821 | 01453 | 7.6 | Solar | 05_01_6W2 | 02/23/2023 | 02/24/2023 | 1 | 0 | 1 | 02/27/2023 | 02/27/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 02/23/2023 | 6/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2023 | Connected |  | N
National Grid | WHITINSVILLE | 623790 | 01588 | 5.76 | Solar | 05_05_19W73 | 07/10/2024 | 07/30/2024 | 2 | 0 | 2 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 709064 | 01610 | 5.76 | Solar | 05_05_318W3 | 08/04/2025 | 08/07/2025 | 3 | 0 | 3 | 08/08/2025 | 08/08/2025 | 80 | 60 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 08/04/2025 | 12/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 368844 | 01602 | 100.8 | Solar | 05_12_3J1 | 08/24/2021 | 09/15/2021 | 15 | 6 | 9 |  |  | 42 | 12 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 699289 | 02764 | 15.2 | Solar | 05_14_21L1 | 06/17/2025 | 06/27/2025 | 6 | 4 | 2 | 06/30/2025 | 06/30/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | BOLTON | 299887 | 01740 | 6 | Solar | 05_14_54L3 | 07/07/2020 | 07/09/2020 | 1 | 0 | 1 | 07/10/2020 | 07/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2020 | Connected |  | N
National Grid | EVERETT | 177698 | 02149 | 7.6 | Solar | 05_14_63L2 | 03/21/2017 | 03/21/2017 | 7 | 7 | 0 | 03/31/2017 | 03/31/2017 | 210 | 0 | 210 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 | 03/21/2017 | 3/27/2018 | Y | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 174165 | 01826 | 566 | Solar | 05_14_77L3 | 04/24/2012 | 04/24/2012 | 13 | 0 | 13 | 05/11/2012 | 05/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 |  | 7/31/2012 | N | EXP | 111 |  |  | 0 | 0 | 0 | 3/25/2013 | 3/25/2013 | 5/21/2013 | Connected |  | N
National Grid | ANDOVER | 178543 | 01845 | 3.8 | Solar | 05_01_225W4 | 01/29/2018 | 01/29/2018 | 19 | 0 | 19 | 02/27/2018 | 02/27/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2018 |  | 2/4/2019 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | Connected |  | N
National Grid | METHUEN | 722290 | 01844 | 15.76 | Solar | 05_01_304W6 | 09/26/2025 | 10/03/2025 | 4 | 0 | 4 | 10/06/2025 | 10/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | LOWELL | 656746 | 01854 | 5.76 | Solar | 05_01_4J336 | 11/25/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | LEOMINSTER | 558041 | 01453 | 7.6 | Solar | 05_01_6W2 | 09/29/2023 | 10/05/2023 | 4 | 0 | 4 | 10/06/2023 | 10/06/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 09/29/2023 | 11/19/2024 | Y | EXP | 365 | 04/24/2024 | 09/04/2024 | 134 | 0 | 134 |  |  | 9/10/2024 | Connected |  | N
National Grid | SUTTON | 630724 | 01590 | 10 | Solar | 05_05_19W73 | 08/07/2024 | 09/24/2024 | 13 | 10 | 3 | 09/25/2024 | 09/25/2024 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 08/07/2024 | 1/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 742068 | 01603 | 45.6 | Solar | 05_05_318W3 | 12/31/2025 | 01/21/2026 | 13 | 11 | 2 | 01/22/2026 | 01/22/2026 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 368795 | 01603 | 151.2 | Solar | 05_12_3J1 | 07/12/2021 | 08/03/2021 | 16 | 9 | 7 |  |  | 72 | 46 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 | 07/12/2021 | 5/22/2024 | Y | STD | 250 | 01/30/2024 | 01/29/2024 | 0 | 0 | 0 |  |  | 5/16/2024 | Connected |  | N
National Grid | DIGHTON | 720590 | 02715 | 10 | Solar | 05_14_21L2 | 09/19/2025 | 10/20/2025 | 3 | 0 | 3 | 10/21/2025 | 10/21/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 09/19/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BERLIN | 301678 | 01503 | 10 | Solar | 05_14_54L3 | 07/16/2020 | 07/21/2020 | 3 | 3 | 0 | 07/22/2020 | 07/22/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 |  | 7/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | SALEM | 185125 | 01970 | 7.6 | Solar | 05_14_63L2 | 05/11/2018 | 05/11/2018 | 0 | 0 | 0 | 06/13/2018 | 06/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2018 |  | 6/17/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2019 | Connected |  | N
National Grid | DRACUT | 177405 | 01826 | 7.6 | Solar | 05_14_77L3 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 146 | 0 | 146 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 |  | 7/5/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 194206 | 01810 | 10 | Solar | 05_01_225W4 | 08/22/2018 | 08/13/2019 | 248 | 248 | 0 | 08/14/2019 | 08/14/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 367448 | 01844 | 7.6 | Solar | 05_01_3J371 | 07/23/2021 | 12/20/2021 | 2 | 0 | 2 | 07/28/2021 | 07/28/2021 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2021 |  | 9/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2022 | Connected |  | N
National Grid | LOWELL | 730887 | 01854 | 11.4 | Solar | 05_01_4J339 | 11/03/2025 | 11/04/2025 | 4 | 0 | 4 | 12/16/2025 | 12/16/2025 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 536053 | 01453 | 850 | Solar | 05_01_6W2 | 07/21/2023 | 08/25/2023 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 03/28/2024 | 145 | 94 | 51 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 643457 | 01590 | 7.6 | Solar | 05_05_19W73 | 09/27/2024 | 11/01/2024 | 7 | 2 | 5 | 11/04/2024 | 11/04/2024 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 | 09/27/2024 | 2/14/2026 | Y | EXP | 365 | 03/19/2025 | 04/21/2025 | 34 | 0 | 34 |  |  | 5/16/2025 | Connected |  | N
National Grid | WORCESTER | 174857 | 01603 | 750 | Solar | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | WORCESTER | 647145 | 01602 | 10 | Solar | 05_12_3J2 | 10/29/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | DIGHTON | 722100 | 02715 | 3.8 | Solar | 05_14_21L2 | 10/14/2025 | 11/14/2025 | 2 | 0 | 2 | 12/24/2025 | 12/24/2025 | 26 | 9 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  | 2/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BERLIN | 320280 | 01053 | 8 | Solar | 05_14_54L3 | 10/20/2020 | 11/10/2020 | 14 | 13 | 1 | 11/12/2020 | 11/12/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 11/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2021 | Connected |  | N
National Grid | SALEM | 188327 | 01970 | 7.6 | Solar | 05_14_63L2 | 06/18/2018 | 06/18/2018 | 7 | 3 | 4 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  | 6/28/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2019 | Connected |  | N
National Grid | LOWELL | 177401 | 01854 | 3.44 | Solar | 05_14_77L3 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/5/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 199725 | 01810 | 10 | Solar | 05_01_225W4 | 12/11/2018 | 12/19/2018 | 5 | 0 | 5 | 12/20/2018 | 12/20/2018 | 247 | 0 | 247 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 12/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 728709 | 01844 | 15.76 | Solar | 05_01_3J372 | 12/12/2025 | 12/16/2025 | 2 | 0 | 2 | 12/17/2025 | 12/17/2025 | 59 | 37 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LOWELL | 643519 | 01854 | 19 | Solar | 05_01_4J339 | 10/01/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 165 | 146 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 542169 | 01453 | 7.6 | Solar | 05_01_6W2 | 08/05/2023 | 08/07/2023 | 1 | 0 | 1 | 08/08/2023 | 08/08/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 | 08/05/2023 | 11/11/2024 | Y | EXP | 365 | 02/16/2024 | 04/11/2024 | 56 | 0 | 56 |  |  | 5/6/2024 | Connected |  | N
National Grid | WORCESTER | 646259 | 01602 | 3.8 | Solar | 05_05_19W73 | 10/17/2024 | 12/16/2024 | 7 | 0 | 7 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | WORCESTER | 174856 | 01610 | 750 | Solar | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | WORCESTER | 698376 | 01602 | 9.88 | Solar | 05_12_3J2 | 06/13/2025 | 06/27/2025 | 4 | 2 | 2 | 07/09/2025 | 07/09/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 06/13/2025 | 8/25/2026 | Y | EXP | 365 | 10/25/2025 | 11/05/2025 | 12 | 0 | 12 |  |  | 11/14/2025 | Connected |  | N
National Grid | DIGHTON | 177701 | 02764 | 7.6 | Solar | 05_14_21L2 | 03/21/2017 | 03/21/2017 | 6 | 6 | 0 | 03/30/2017 | 03/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2017 |  | 3/27/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 10/3/2017 | 10/3/2017 | 10/3/2017 | Connected |  | N
National Grid | BERLIN | 326283 | 01503 | 11.4 | Solar | 05_14_54L3 | 11/16/2020 | 11/18/2020 | 1 | 0 | 1 | 11/19/2020 | 11/19/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 2/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2021 | Connected |  | N
National Grid | SALEM | 188961 | 01970 | 1750 | Solar | 05_14_63L2 | 07/06/2018 | 09/05/2018 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/06/2018 | 10/10/2018 | 23 | 3 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2019 | 07/06/2018 | 9/27/2021 | Y | STD | 483 | 06/22/2021 | 08/02/2021 | 42 | 0 | 42 |  |  | 9/22/2021 | Connected |  | N
National Grid | LOWELL | 178339 | 01850 | 10 | Solar | 05_14_77L3 | 11/20/2017 | 11/20/2017 | 33 | 32 | 1 | 01/09/2018 | 01/09/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2018 | 11/20/2017 | 11/25/2018 | Y | EXP | 319 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | ANDOVER | 204484 | 01810 | 0 | Solar | 05_01_225W4 | 01/17/2019 | 02/01/2019 | 9 | 0 | 9 | 02/04/2019 | 02/04/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 446320 | 01844 | 16.24 | Solar | 05_01_3J372 | 08/30/2022 | 09/15/2022 | 11 | 9 | 2 | 09/16/2022 | 09/16/2022 | 134 | 117 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2023 |  | 6/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2024 | Connected |  | N
National Grid | LOWELL | 647997 | 01854 | 15.2 | Solar | 05_01_4J339 | 10/17/2024 | 11/12/2024 | 17 | 15 | 2 | 11/13/2024 | 11/13/2024 | 74 | 49 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | Y
National Grid | LEOMINSTER | 581993 | 01453 | 9.86 | Solar | 05_01_6W2 | 01/22/2024 | 01/23/2024 | 1 | 0 | 1 | 01/24/2024 | 01/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2024 | Connected |  | N
National Grid | WORCESTER | 653935 | 01610 | 5.76 | Solar | 05_05_19W73 | 11/18/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/18/2024 | 2/6/2026 | Y | EXP | 365 | 04/15/2025 | 04/15/2025 | 1 | 0 | 1 |  |  | 4/22/2025 | Connected |  | N
National Grid | WORCESTER | 174855 | 01610 | 750 | Solar | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | WORCESTER | 700251 | 01603 | 11.4 | Solar | 05_12_3J2 | 06/23/2025 | 07/23/2025 | 7 | 3 | 4 | 07/24/2025 | 07/24/2025 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 424750 | 02777 | 7.6 | Solar | 05_14_21L2 | 07/21/2022 | 08/09/2022 | 13 | 10 | 3 | 08/10/2022 | 08/10/2022 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 1/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2023 | Connected |  | N
National Grid | BERLIN | 326749 | 01503 | 10 | Solar | 05_14_54L3 | 11/18/2020 | 11/23/2020 | 2 | 0 | 2 | 11/24/2020 | 11/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2021 | Connected |  | N
National Grid | SALEM | 194325 | 01970 | 7.6 | Solar | 05_14_63L2 | 11/18/2018 | 11/29/2018 | 6 | 0 | 6 | 11/30/2018 | 11/30/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 |  | 11/27/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2020 | Connected |  | N
National Grid | DRACUT | 188816 | 01826 | 10 | Solar | 05_14_77L3 | 06/21/2018 | 06/21/2018 | 2 | 0 | 2 | 07/11/2018 | 07/11/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 | 06/21/2018 | 7/22/2020 | Y | EXP | 600 | 10/04/2019 | 10/22/2019 | 18 | 0 | 18 |  |  | 7/3/2020 | Connected |  | N
National Grid | ANDOVER | 264869 | 01810 | 0 | Solar | 05_01_225W4 | 11/11/2019 | 11/13/2019 | 1 | 0 | 1 | 11/14/2019 | 11/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2019 | 11/11/2019 | 3/16/2021 | Y | EXP | 365 | 06/24/2020 | 06/24/2020 | 0 | 0 | 0 |  |  | 8/14/2020 | Connected |  | N
National Grid | METHUEN | 446313 | 01844 | 14.5 | Solar | 05_01_3J372 | 08/30/2022 | 10/11/2022 | 28 | 27 | 1 | 10/12/2022 | 10/12/2022 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2022 |  | 6/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2024 | Connected |  | N
National Grid | LOWELL | 661902 | 01854 | 5.76 | Solar | 05_01_4J339 | 12/20/2024 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | Y
National Grid | LEOMINSTER | 583917 | 01453 | 4.93 | Solar | 05_01_6W2 | 02/09/2024 | 02/14/2024 | 3 | 0 | 3 | 02/15/2024 | 02/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 4/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | WORCESTER | 673697 | 01610 | 3.8 | Solar | 05_05_19W73 | 02/24/2025 | 03/14/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 104 | 90 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174894 | 01610 | 666 | Solar | 05_05_318W3 | 08/20/2013 | 08/20/2013 | 52 | 43 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2013 | 09/16/2014 | 213 | 0 | 213 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2014 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 749324 | 01603 | 23 | Solar | 05_12_3J2 | 02/04/2026 | 02/11/2026 | 4 | 0 | 4 | 02/12/2026 | 02/12/2026 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2026 |  | 3/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2026 | Connected |  | N
National Grid | DIGHTON | 441257 | 02715 | 3.48 | Solar | 05_14_21L2 | 07/15/2022 | 07/19/2022 | 2 | 0 | 2 | 07/20/2022 | 07/20/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 | 07/15/2022 | 3/1/2024 | Y | EXP | 365 | 02/17/2023 | 02/28/2023 | 12 | 0 | 12 |  |  | 9/6/2023 | Connected |  | Y
National Grid | BERLIN | 338222 | 01503 | 11.52 | Solar | 05_14_54L3 | 01/22/2021 | 01/28/2021 | 4 | 4 | 0 | 01/29/2021 | 01/29/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2021 | Connected |  | N
National Grid | SALEM | 195563 | 01970 | 180 | Solar | 05_14_63L2 | 09/11/2018 | 10/03/2018 | 15 | 0 | 15 | 10/04/2018 | 10/04/2018 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2020 | Connected |  | N
National Grid | LOWELL | 197115 | 01850 | 3.8 | Solar | 05_14_77L3 | 09/27/2018 | 11/02/2018 | 3 | 3 | 0 | 11/05/2018 | 11/05/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 09/27/2018 | 4/22/2020 | Y | EXP | 512 | 11/14/2019 | 11/15/2019 | 1 | 0 | 1 |  |  | 1/22/2020 | Connected |  | N
National Grid | ANDOVER | 288685 | 01810 | 10 | Solar | 05_01_225W4 | 07/20/2020 | 07/27/2020 | 4 | 0 | 4 | 07/28/2020 | 07/28/2020 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 07/20/2020 | 4/3/2021 | Y | EXP | 365 | 01/20/2021 | 01/26/2021 | 6 | 0 | 6 |  |  | 2/19/2021 | Connected |  | N
National Grid | METHUEN | 649062 | 01844 | 7.6 | Solar | 05_01_3J373 | 10/23/2024 | 11/13/2024 | 7 | 1 | 6 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 686548 | 01854 | 17.86 | Solar | 05_01_4J339 | 05/30/2025 | 06/05/2025 | 4 | 0 | 4 | 06/06/2025 | 06/06/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | LEOMINSTER | 592273 | 01453 | 3 | Solar | 05_01_6W2 | 03/08/2024 | 03/29/2024 | 16 | 13 | 3 | 04/01/2024 | 04/01/2024 | 81 | 67 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 03/08/2024 | 7/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 700565 | 01610 | 11.4 | Solar | 05_05_19W73 | 06/24/2025 | 08/01/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 | 06/24/2025 | 9/7/2026 | Y | EXP | 365 | 10/01/2025 | 09/30/2025 | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | WORCESTER | 174960 | 01610 | 750 | Solar | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | WORCESTER | 672445 | 01602 | 10 | Solar | 05_12_3J6 | 02/17/2025 | 03/14/2025 | 4 | 0 | 4 | 03/17/2025 | 03/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DIGHTON | 493449 | 02715 | 6 | Solar | 05_14_21L2 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 359718 | 01532 | 54.6 | Solar | 05_14_54L3 | 05/26/2021 | 06/08/2021 | 7 | 1 | 6 | 06/09/2021 | 06/09/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2021 |  | 8/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2022 | Connected |  | N
National Grid | SALEM | 195141 | 01970 | 15.2 | Solar | 05_14_63L2 | 09/05/2018 | 10/17/2018 | 31 | 26 | 5 | 10/18/2018 | 10/18/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2018 |  | 7/5/2019 | N | EXP | 256 |  |  | 0 | 0 | 0 |  |  | 6/21/2019 | Connected |  | N
National Grid | DRACUT | 201056 | 01826 | 7.6 | Solar | 05_14_77L3 | 11/13/2018 | 01/30/2019 | 41 | 34 | 7 | 01/31/2019 | 01/31/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 327211 | 01845 | 7.6 | Solar | 05_01_225W4 | 12/04/2020 | 12/10/2020 | 3 | 0 | 3 | 12/11/2020 | 12/11/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/6/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 667941 | 01844 | 5.76 | Solar | 05_01_3J373 | 01/27/2025 | 03/26/2025 | 4 | 0 | 4 | 04/08/2025 | 04/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 01/27/2025 | 5/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2025 | Connected |  | N
National Grid | LOWELL | 699261 | 01854 | 5.76 | Solar | 05_01_4J339 | 06/18/2025 | 07/02/2025 | 33 | 30 | 3 | 08/27/2025 | 08/27/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2025 | Connected |  | N
National Grid | LEOMINSTER | 605256 | 01453 | 5 | Solar | 05_01_6W2 | 05/01/2024 | 05/02/2024 | 2 | 1 | 1 | 05/03/2024 | 05/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 | 05/01/2024 | 6/12/2025 | Y | EXP | 365 | 10/18/2024 | 10/24/2024 | 7 | 0 | 7 |  |  | 10/28/2024 | Connected |  | N
National Grid | WORCESTER | 717276 | 01610 | 10 | Solar | 05_05_19W73 | 09/07/2025 | 10/08/2025 | 3 | 0 | 3 | 10/29/2025 | 10/29/2025 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2026 | Connected |  | N
National Grid | WORCESTER | 177688 | 01610 | 4950 | Solar | 05_05_318W3 | 10/03/2017 | 10/24/2017 | 15 | 12 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2017 | 11/27/2017 | 21 | 6 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 | 10/03/2017 | 8/5/2021 | Y | STD | 1006 | 03/14/2021 | 07/30/2021 | 138 | 0 | 138 | 6/18/2021 | 7/30/2021 | 7/30/2021 | Connected |  | N
National Grid | LEICESTER | 230775 | 01611 | 66.6 | Solar | 05_12_3J6 | 07/16/2020 | 07/31/2020 | 11 | 5 | 6 | 08/03/2020 | 08/03/2020 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2020 |  | 10/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 574472 | 02715 | 10 | Solar | 05_14_21L2 | 12/08/2023 | 12/12/2023 | 2 | 0 | 2 | 12/13/2023 | 12/13/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | BERLIN | 405836 | 01503 | 0 | Battery Add-On | 05_14_54L3 | 01/24/2022 | 02/03/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2022 | 03/02/2022 | 18 | 15 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 197393 | 01970 | 7.6 | Solar | 05_14_63L2 | 10/01/2018 | 10/26/2018 | 4 | 4 | 0 | 10/29/2018 | 10/29/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 251766 | 01850 | 7.6 | Solar | 05_14_77L3 | 09/11/2019 | 09/16/2019 | 2 | 2 | 0 | 09/17/2019 | 09/17/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 | 09/11/2019 | 6/17/2021 | Y | EXP | 0 |  |  | 0 | 0 | 0 |  |  | 1/26/2021 | Connected |  | N
National Grid | ANDOVER | 331301 | 01810 | 9.8 | Solar | 05_01_225W4 | 02/16/2021 | 02/17/2021 | 0 | 0 | 0 | 02/18/2021 | 02/18/2021 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 5/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 697845 | 01844 | 7.6 | Solar | 05_01_3J373 | 06/11/2025 | 06/24/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2025 | Connected |  | N
National Grid | LOWELL | 611044 | 01854 | 6.09 | Solar | 05_01_4J340 | 05/28/2024 | 06/20/2024 | 3 | 0 | 3 | 06/21/2024 | 06/21/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2024 | Connected |  | N
National Grid | LEOMINSTER | 607670 | 01453 | 7.6 | Solar | 05_01_6W2 | 04/30/2024 | 05/09/2024 | 2 | 0 | 2 | 05/10/2024 | 05/10/2024 | 19 | 7 | 12 | 06/17/2024 | 07/24/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 07/24/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 8/1/2024 | 04/30/2024 | 10/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | WORCESTER | 719867 | 01610 | 23 | Solar | 05_05_19W74 | 09/17/2025 | 10/17/2025 | 19 | 17 | 2 | 10/20/2025 | 10/20/2025 | 110 | 95 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 184729 | 01610 | 16.64 | Solar | 05_05_318W3 | 05/07/2018 | 05/07/2018 | 9 | 0 | 9 | 07/13/2018 | 07/13/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 655816 | 01603 | 7.6 | Solar | 05_12_3J6 | 11/20/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | SWANSEA | 644522 | 02777 | 5.76 | Solar | 05_14_21L2 | 10/02/2024 | 10/29/2024 | 10 | 7 | 3 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | BERLIN | 464540 | 01503 | 23.32 | Solar | 05_14_54L3 | 09/29/2022 | 10/04/2022 | 3 | 0 | 3 | 10/05/2022 | 10/05/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2023 |  | 3/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2023 | Connected |  | N
National Grid | SALEM | 204947 | 01970 | 3.8 | Solar | 05_14_63L2 | 01/16/2019 | 01/30/2019 | 9 | 8 | 1 | 01/31/2019 | 01/31/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 261453 | 01826 | 7.6 | Solar | 05_14_77L3 | 10/29/2019 | 11/05/2019 | 4 | 0 | 4 | 11/06/2019 | 11/06/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 | 10/29/2019 | 10/29/2020 | Y | EXP | 365 | 03/04/2020 | 04/08/2020 | 35 | 0 | 35 |  |  | 7/30/2020 | Connected |  | N
National Grid | ANDOVER | 335169 | 01810 | 5.76 | Solar | 05_01_225W4 | 02/17/2021 | 03/24/2021 | 24 | 24 | 0 | 03/25/2021 | 03/25/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2021 | 02/17/2021 | 3/24/2022 | Y | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 737387 | 01844 | 10 | Solar | 05_01_3J374 | 12/02/2025 | 12/04/2025 | 2 | 0 | 2 | 12/05/2025 | 12/05/2025 | 37 | 23 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 459951 | 01854 | 4999 | Solar | 05_01_525L1 | 11/02/2022 | 11/17/2022 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2022 | 12/15/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEOMINSTER | 616449 | 01453 | 3.8 | Solar | 05_01_6W2 | 06/07/2024 | 06/18/2024 | 2 | 0 | 2 | 06/20/2024 | 06/20/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2024 | Connected |  | N
National Grid | WORCESTER | 721916 | 01610 | 20 | Solar | 05_05_19W74 | 10/16/2025 | 10/22/2025 | 3 | 1 | 2 | 10/23/2025 | 10/23/2025 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 | 10/16/2025 | 1/8/2027 | Y | EXP | 365 | 01/30/2026 | 02/11/2026 | 13 | 0 | 13 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 195130 | 01610 | 479.904 | Solar | 05_05_318W3 | 09/06/2018 | 09/21/2018 | 4 | 0 | 4 | 09/24/2018 | 09/24/2018 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2018 |  | 5/31/2020 | N | EXP | 389 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | WORCESTER | 665449 | 01603 | 5.76 | Solar | 05_12_3J901 | 01/15/2025 | 03/03/2025 | 2 | 0 | 2 | 03/04/2025 | 03/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 | 01/15/2025 | 5/10/2026 | Y | EXP | 365 | 07/12/2025 | 10/15/2025 | 96 | 0 | 96 |  |  | 11/26/2025 | Connected |  | N
National Grid | DIGHTON | 645288 | 02764 | 7.6 | Solar | 05_14_21L2 | 10/07/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | BERLIN | 485876 | 01503 | 0 | Solar | 05_14_54L3 | 12/15/2022 | 12/19/2022 | 2 | 0 | 2 | 12/20/2022 | 12/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 | 12/15/2022 | 4/26/2024 | Y | EXP | 365 | 05/09/2023 | 06/08/2023 | 31 | 0 | 31 |  |  | 1/17/2024 | Connected |  | N
National Grid | SALEM | 205248 | 01970 | 10 | Solar | 05_14_63L2 | 01/25/2019 | 03/14/2019 | 32 | 26 | 6 | 03/15/2019 | 03/15/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 333029 | 01854 | 7.6 | Solar | 05_14_77L3 | 12/18/2020 | 12/21/2020 | 0 | 0 | 0 | 12/22/2020 | 12/22/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 351150 | 01810 | 7.6 | Solar | 05_01_225W4 | 04/29/2021 | 05/06/2021 | 4 | 0 | 4 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  | 7/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 570742 | 01844 | 10 | Solar | 05_01_3J374 | 12/19/2023 | 04/17/2024 | 81 | 77 | 4 | 04/18/2024 | 04/18/2024 | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 715897 | 01854 | 5.76 | Solar | 05_01_525L1 | 09/01/2025 | 09/19/2025 | 26 | 22 | 4 | 11/13/2025 | 11/13/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 622524 | 01453 | 10 | Solar | 05_01_6W2 | 07/03/2024 | 07/16/2024 | 3 | 0 | 3 | 07/17/2024 | 07/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/03/2024 | 8/29/2025 | Y | EXP | 365 | 10/10/2024 | 10/23/2024 | 14 | 0 | 14 |  |  | 11/16/2024 | Connected |  | N
National Grid | WORCESTER | 727861 | 01609 | 10 | Solar | 05_05_19W74 | 10/21/2025 | 10/23/2025 | 2 | 0 | 2 | 10/24/2025 | 10/24/2025 | 84 | 72 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTH BROOKFIELD | 202568 | 01535 | 15.2 | Solar | 05_05_318W3 | 12/10/2018 | 12/21/2018 | 6 | 0 | 6 | 12/24/2018 | 12/24/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2019 | 12/10/2018 | 9/23/2021 | Y | EXP | 365 | 04/07/2021 | 04/14/2021 | 7 | 0 | 7 |  |  | 4/23/2021 | Connected |  | N
National Grid | WORCESTER | 670878 | 01602 | 7.6 | Solar | 05_12_3J901 | 02/07/2025 | 03/13/2025 | 13 | 9 | 4 | 03/14/2025 | 03/14/2025 | 117 | 100 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 649324 | 02715 | 10 | Solar | 05_14_21L2 | 11/05/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | HUDSON | 492260 | 01749 | 14.79 | Solar | 05_14_54L3 | 01/18/2023 | 01/19/2023 | 1 | 0 | 1 |  |  | 222 | 204 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 244231 | 01902 | 7.6 | Solar | 05_14_63L2 | 07/23/2019 | 08/02/2019 | 7 | 2 | 5 | 08/05/2019 | 08/05/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  | 8/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N
National Grid | DRACUT | 558692 | 01826 | 7.6 | Solar | 05_14_77L3 | 10/03/2023 | 10/05/2023 | 2 | 0 | 2 | 10/06/2023 | 10/06/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2023 | 10/03/2023 | 11/16/2024 | Y | EXP | 365 | 05/07/2024 | 07/24/2024 | 79 | 0 | 79 |  |  | 8/9/2024 | Connected |  | N
National Grid | ANDOVER | 388913 | 01810 | 10 | Solar | 05_01_225W4 | 11/22/2021 | 01/06/2022 | 5 | 0 | 5 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2021 | 11/22/2021 | 10/26/2023 | Y | EXP | 365 | 04/13/2022 | 10/26/2022 | 197 | 0 | 197 |  |  | 11/14/2022 | Connected |  | N
National Grid | METHUEN | 634549 | 01844 | 9.57 | Solar | 05_01_3J374 | 08/22/2024 | 10/14/2024 | 14 | 13 | 1 | 10/15/2024 | 10/15/2024 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 730670 | 01854 | 15.2 | Solar | 05_01_525L1 | 11/06/2025 | 12/05/2025 | 19 | 16 | 3 | 12/08/2025 | 12/08/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  | 2/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 636208 | 01453 | 3.8 | Solar | 05_01_6W2 | 08/28/2024 | 09/09/2024 | 4 | 0 | 4 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/28/2024 | 10/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | WORCESTER | 731625 | 01609 | 22.8 | Solar | 05_05_19W74 | 11/20/2025 | 11/24/2025 | 2 | 0 | 2 | 11/25/2025 | 11/25/2025 | 39 | 25 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 1/29/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTH BROOKFIELD | 202205 | 01535 | 20 | Solar | 05_05_318W3 | 11/27/2018 | 12/05/2018 | 5 | 0 | 5 | 12/06/2018 | 12/06/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 349185 | 01602 | 7.6 | Solar | 05_12_3J903 | 04/28/2021 | 05/03/2021 | 2 | 0 | 2 | 05/04/2021 | 05/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 655399 | 02764 | 4.06 | Solar | 05_14_21L2 | 11/19/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/19/2024 | 2/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | BERLIN | 495148 | 01503 | 15.2 | Solar | 05_14_54L3 | 05/11/2023 | 05/15/2023 | 2 | 0 | 2 | 05/16/2023 | 05/16/2023 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 259289 | 01902 | 7.6 | Solar | 05_14_63L2 | 10/17/2019 | 10/22/2019 | 2 | 0 | 2 | 10/23/2019 | 10/23/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 | 10/17/2019 | 7/7/2020 | Y | EXP | 365 | 03/13/2020 | 06/01/2020 | 80 | 0 | 80 |  |  | 6/5/2020 | Connected |  | N
National Grid | LOWELL | 536046 | 01850 | 900 | Solar | 05_14_77L3 | 07/21/2023 | 08/25/2023 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 12/04/2023 | 67 | 48 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 421215 | 01810 | 0 | Solar | 05_01_225W4 | 03/31/2022 | 04/04/2022 | 2 | 0 | 2 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 636727 | 01844 | 10 | Solar | 05_01_3J374 | 08/30/2024 | 09/06/2024 | 4 | 0 | 4 | 11/01/2024 | 11/01/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | LOWELL | 174425 | 01854 | 1000 | Solar | 05_01_525L1 | 11/23/2011 | 11/23/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 636971 | 01453 | 3.8 | Solar | 05_01_6W2 | 08/30/2024 | 12/04/2024 | 57 | 56 | 1 | 12/05/2024 | 12/05/2024 | 25 | 0 | 25 | 01/22/2025 | 02/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 02/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 | 05/02/2025 | 05/30/2025 | 29 | 0 | 29 |  |  | 7/10/2025 | Connected |  | N
National Grid | WORCESTER | 741060 | 01609 | 7.6 | Solar | 05_05_19W74 | 12/18/2025 | 12/22/2025 | 2 | 0 | 2 | 12/23/2025 | 12/23/2025 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTH BROOKFIELD | 241787 | 01535 | 9.28 | Solar | 05_05_318W3 | 09/30/2019 | 10/07/2019 | 4 | 1 | 3 | 10/08/2019 | 10/08/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2019 |  | 9/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2020 | Connected |  | N
National Grid | WORCESTER | 584871 | 01602 | 7.6 | Solar | 05_12_3J903 | 02/01/2024 | 02/16/2024 | 12 | 10 | 2 | 02/20/2024 | 02/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 3/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | DIGHTON | 667886 | 02715 | 21.4 | Solar | 05_14_21L2 | 01/26/2025 | 02/06/2025 | 3 | 0 | 3 | 02/07/2025 | 02/07/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/26/2025 | 5/12/2026 | Y | EXP | 365 | 06/26/2025 | 12/22/2025 | 197 | 0 | 197 |  |  | 11/21/2025 | Connected |  | N
National Grid | BERLIN | 502282 | 01503 | 15.2 | Solar | 05_14_54L3 | 02/15/2023 | 02/16/2023 | 1 | 0 | 1 | 02/17/2023 | 02/17/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 4/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2024 | Connected |  | N
National Grid | LYNN | 269213 | 01902 | 9.84 | Solar | 05_14_63L2 | 12/11/2019 | 12/13/2019 | 2 | 2 | 0 | 12/16/2019 | 12/16/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 |  | 12/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2020 | Connected |  | N
National Grid | DRACUT | 576999 | 01826 | 5.51 | Solar | 05_14_77L3 | 01/16/2024 | 12/14/2023 | 2 | 0 | 2 | 01/19/2024 | 01/19/2024 | 20 | 0 | 20 | 03/22/2024 | 04/22/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 04/22/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 4/11/2024 | 01/16/2024 | 5/29/2025 | Y | EXP | 365 | 05/18/2024 | 06/06/2024 | 20 | 0 | 20 |  |  | 9/6/2024 | Connected |  | N
National Grid | ANDOVER | 443788 | 01810 | 11.02 | Solar | 05_01_225W4 | 07/19/2022 | 07/25/2022 | 4 | 2 | 2 | 07/26/2022 | 07/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2022 | 07/19/2022 | 2/2/2024 | Y | EXP | 365 | 02/02/2023 | 02/01/2023 | 0 | 0 | 0 |  |  | 2/28/2023 | Connected |  | N
National Grid | METHUEN | 658582 | 01844 | 9.57 | Solar | 05_01_3J374 | 12/05/2024 | 12/19/2024 | 8 | 6 | 2 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | LOWELL | 174424 | 01854 | 1000 | Solar | 05_01_525L1 | 11/23/2011 | 11/23/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 643927 | 01453 | 5.76 | Solar | 05_01_6W2 | 10/01/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N
National Grid | WORCESTER | 748734 | 01609 | 10 | Solar | 05_05_19W74 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 38 | 21 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTH BROOKFIELD | 346401 | 01535 | 250 | Solar | 05_05_318W3 | 04/07/2021 | 04/23/2021 | 11 | 0 | 11 |  |  | 171 | 98 | 73 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 | 04/07/2021 | 7/20/2024 | Y | STD | 437 | 08/16/2023 | 10/27/2023 | 73 | 0 | 73 |  |  | 5/22/2024 | Connected |  | N
National Grid | WORCESTER | 584595 | 01603 | 5 | Solar | 05_12_3J903 | 02/09/2024 | 02/12/2024 | 2 | 1 | 1 | 02/13/2024 | 02/13/2024 | 25 | 19 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 02/09/2024 | 4/23/2025 | Y | EXP | 365 | 08/21/2024 | 10/10/2024 | 51 | 0 | 51 |  |  | 10/4/2024 | Connected |  | N
National Grid | DIGHTON | 676616 | 02764 | 11.4 | Solar | 05_14_21L2 | 03/27/2025 | 04/11/2025 | 11 | 8 | 3 | 04/14/2025 | 04/14/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 518526 | 01740 | 8.99 | Solar | 05_14_54L3 | 04/11/2023 | 04/12/2023 | 2 | 1 | 1 | 04/13/2023 | 04/13/2023 | 34 | 12 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2023 |  | 6/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2023 | Connected |  | N
National Grid | LYNN | 278631 | 01902 | 7.6 | Solar | 05_14_63L2 | 03/05/2020 |  | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 583929 | 01826 | 5.22 | Solar | 05_14_77L3 | 02/01/2024 | 02/06/2024 | 3 | 0 | 3 | 02/07/2024 | 02/07/2024 | 12 | 0 | 12 | 03/29/2024 | 05/01/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 05/01/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 4/11/2024 |  | 6/25/2025 | N | EXP | 365 | 10/24/2024 | 11/07/2024 | 15 | 0 | 15 |  |  | 12/16/2024 | Connected |  | N
National Grid | ANDOVER | 455958 | 01845 | 9.6 | Solar | 05_01_225W4 | 09/13/2022 | 09/15/2022 | 2 | 0 | 2 | 09/16/2022 | 09/16/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 | 09/13/2022 | 2/3/2024 | Y | EXP | 365 | 02/03/2023 | 02/02/2023 | 0 | 0 | 0 |  |  | 6/5/2023 | Connected |  | N
National Grid | METHUEN | 482717 | 01844 | 24.779 | Solar | 05_01_3J375 | 12/05/2022 | 12/08/2022 | 4 | 1 | 3 | 12/09/2022 | 12/09/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 |  | 3/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2023 | Connected |  | N
National Grid | LOWELL | 174422 | 01854 | 3000 | Solar | 05_01_525L1 | 11/23/2011 | 11/23/2011 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2012 | 11/23/2011 | 10/31/2012 | Y | STD | 34 | 02/13/2014 | 06/13/2014 | 82 | 0 | 82 | 6/16/2014 | 6/16/2014 | 6/16/2014 | Connected |  | N
National Grid | LEOMINSTER | 655083 | 01453 | 5.76 | Solar | 05_01_6W2 | 11/18/2024 | 01/30/2025 | 40 | 34 | 6 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 5/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | Y
National Grid | WORCESTER | 748174 | 01609 | 17.48 | Solar | 05_05_19W74 | 01/29/2026 | 02/04/2026 | 3 | 1 | 2 | 02/05/2026 | 02/05/2026 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTH BROOKFIELD | 355955 | 01535 | 7.83 | Solar | 05_05_318W3 | 05/03/2021 | 05/06/2021 | 3 | 1 | 2 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2021 | Connected |  | N
National Grid | WORCESTER | 592529 | 01603 | 3.8 | Solar | 05_12_3J903 | 02/27/2024 | 03/05/2024 | 5 | 0 | 5 | 03/06/2024 | 03/06/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 5/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2024 | Connected |  | N
National Grid | DIGHTON | 692133 | 02715 | 10 | Solar | 05_14_21L3 | 05/30/2025 | 07/08/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 31 | 16 | 15 | 09/23/2025 | 10/08/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 10/08/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 10/30/2026 | N | EXP | 365 | 03/27/2026 |  | 6 | 0 | 6 |  |  |  | Construction |  | Y
National Grid | BERLIN | 543279 | 01503 | 14.79 | Solar | 05_14_54L3 | 07/24/2023 | 07/26/2023 | 2 | 0 | 2 | 07/27/2023 | 07/27/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2023 | 07/24/2023 | 11/29/2024 | Y | EXP | 365 | 12/04/2023 | 01/16/2024 | 44 | 3 | 41 |  |  | 1/19/2024 | Connected |  | N
National Grid | LYNN | 360395 | 01902 | 8.99 | Solar | 05_14_63L2 | 07/27/2021 | 12/28/2021 | 10 | 8 | 2 | 08/11/2021 | 08/11/2021 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 | 07/27/2021 |  | Y | EXP | 365 | 03/08/2022 | 03/30/2022 | 23 | 0 | 23 |  |  | 4/7/2022 | Connected |  | N
National Grid | DRACUT | 599934 | 01826 | 15.2 | Solar | 05_14_77L3 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 490204 | 01810 | 7.68 | Solar | 05_01_225W4 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2023 | Connected |  | Y
National Grid | METHUEN | 575082 | 01844 | 9.6 | Solar | 05_01_3J375 | 03/05/2024 | 03/11/2024 | 4 | 1 | 3 | 03/12/2024 | 03/12/2024 | 4 | 0 | 4 | 03/29/2024 | 05/07/2024 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 05/07/2024 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 175219 | 01854 | 18 | Solar | 05_01_525L1 | 11/03/2014 | 11/03/2014 | 6 | 2 | 4 | 11/13/2014 | 11/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2014 |  | 6/1/2015 | N | EXP | 199 |  |  | 0 | 0 | 0 | 2/18/2015 | 2/18/2015 | 9/30/2015 | Connected |  | N
National Grid | LEOMINSTER | 657449 | 01453 | 3.8 | Solar | 05_01_6W2 | 11/27/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/27/2024 | 2/21/2026 | Y | EXP | 365 | 06/12/2025 | 07/15/2025 | 34 | 0 | 34 |  |  | 7/26/2025 | Connected |  | N
National Grid | WORCESTER | 749533 | 01609 | 10 | Solar | 05_05_19W74 | 02/05/2026 | 02/06/2026 | 3 | 0 | 3 | 02/20/2026 | 02/20/2026 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTH BROOKFIELD | 366496 | 01535 | 8.7 | Solar | 05_05_318W3 | 09/07/2021 | 09/13/2021 | 4 | 0 | 4 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 | 09/07/2021 | 12/21/2023 | Y | EXP | 365 | 04/13/2022 | 12/21/2022 | 253 | 0 | 253 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 599564 | 01602 | 3.8 | Solar | 05_12_3J903 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 | 04/04/2024 | 7/21/2025 | Y | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | DIGHTON | 723479 | 02764 | 20 | Solar | 05_14_21L3 | 10/01/2025 | 10/07/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 12/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOLTON | 569398 | 01740 | 7.6 | Solar | 05_14_54L3 | 11/07/2023 | 02/13/2024 | 65 | 63 | 2 | 02/14/2024 | 02/14/2024 | 18 | 11 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | LYNN | 367847 | 01902 | 7.6 | Solar | 05_14_63L2 | 07/19/2021 | 07/22/2021 | 3 | 0 | 3 | 07/23/2021 | 07/23/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2021 | 07/19/2021 |  | Y | EXP | 365 | 01/21/2022 | 01/24/2022 | 4 | 0 | 4 |  |  | 4/4/2022 | Connected |  | N
National Grid | LOWELL | 616157 | 01854 | 13.6 | Solar | 05_14_77L3 | 06/06/2024 | 06/25/2024 | 3 | 1 | 2 | 06/26/2024 | 06/26/2024 | 38 | 26 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 06/06/2024 | 10/12/2025 | Y | EXP | 365 | 10/30/2024 | 01/23/2025 | 86 | 0 | 86 |  |  | 2/13/2025 | Connected |  | N
National Grid | ANDOVER | 503390 | 01810 | 16.24 | Solar | 05_01_225W4 | 02/20/2023 | 03/16/2023 | 19 | 18 | 1 | 03/17/2023 | 03/17/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2023 | 02/20/2023 | 4/26/2024 | Y | EXP | 365 | 07/06/2023 | 08/15/2023 | 41 | 0 | 41 |  |  | 1/31/2024 | Connected |  | N
National Grid | METHUEN | 621063 | 01844 | 7.6 | Solar | 05_01_3J375 | 06/27/2024 | 07/29/2024 | 17 | 16 | 1 | 07/30/2024 | 07/30/2024 | 123 | 25 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 175629 | 01879 | 120 | Solar | 05_01_525L1 | 08/06/2014 | 08/06/2014 | 7 | 0 | 7 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2014 |  | 1/30/2015 | N | EXP | 135 |  |  | 0 | 0 | 0 | 9/17/2014 | 9/17/2014 | 2/20/2015 | Connected |  | N
National Grid | LEOMINSTER | 657837 | 01453 | 3.8 | Solar | 05_01_6W2 | 12/02/2024 |  | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 751360 | 01609 | 11.5 | Solar | 05_05_19W74 | 02/16/2026 | 02/20/2026 | 1 | 0 | 1 | 03/11/2026 | 03/11/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTH BROOKFIELD | 372931 | 01535 | 7.6 | Solar | 05_05_318W3 | 08/31/2021 | 09/08/2021 | 4 | 4 | 0 | 09/09/2021 | 09/09/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 |  | 5/14/2023 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 625884 | 01611 | 5.76 | Solar | 05_12_3J903 | 07/18/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | Y
National Grid | DIGHTON | 745622 | 02764 | 7.6 | Solar | 05_14_21L3 | 01/16/2026 | 01/21/2026 | 3 | 0 | 3 | 02/04/2026 | 02/04/2026 | 37 | 21 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BOLTON | 576984 | 01740 | 0 | Solar | 05_14_54L3 | 12/11/2023 | 12/13/2023 | 2 | 0 | 2 | 12/14/2023 | 12/14/2023 | 52 | 28 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 392062 | 01902 | 8.7 | Solar | 05_14_63L2 | 11/29/2021 | 02/07/2022 | 48 | 44 | 4 | 02/08/2022 | 02/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 644945 | 01854 | 3.8 | Solar | 05_14_77L3 | 10/03/2024 | 10/29/2024 | 5 | 1 | 4 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 1/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | Y
National Grid | ANDOVER | 502848 | 01810 | 14.79 | Solar | 05_01_225W4 | 04/12/2023 | 04/17/2023 | 3 | 1 | 2 | 04/18/2023 | 04/18/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2023 | 04/12/2023 | 5/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2023 | Connected |  | N
National Grid | METHUEN | 643130 | 01844 | 3.8 | Solar | 05_01_3J375 | 09/26/2024 | 10/08/2024 | 3 | 0 | 3 | 10/09/2024 | 10/09/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 11/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | TYNGSBORO | 177746 | 01879 | 15 | Solar | 05_01_525L1 | 05/31/2017 | 05/31/2017 | 48 | 48 | 0 | 08/08/2017 | 08/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2017 |  | 6/5/2018 | N | EXP | 286 |  |  | 0 | 0 | 0 | 12/26/2017 | 12/26/2017 | 12/26/2017 | Connected |  | N
National Grid | LEOMINSTER | 661445 | 01453 | 4.64 | Solar | 05_01_6W2 | 12/18/2024 | 01/10/2025 | 5 | 0 | 5 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 757464 | 01609 | 7.6 | Solar | 05_05_19W74 | 03/18/2026 | 03/20/2026 | 2 | 0 | 2 | 03/23/2026 | 03/23/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTH BROOKFIELD | 384559 | 01535 | 7.6 | Solar | 05_05_318W3 | 09/27/2021 | 09/28/2021 | 1 | 0 | 1 | 09/29/2021 | 09/29/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  | 5/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2022 | Connected |  | N
National Grid | WORCESTER | 644776 | 01603 | 3.8 | Solar | 05_12_3J903 | 10/03/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 174624 | 02715 | 40 | Solar | 05_14_21L3 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 145 | 12/12/2011 | 12/12/2011 | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | BOLTON | 604615 | 01740 | 17.6 | Solar | 05_14_54L3 | 06/07/2024 | 06/10/2024 | 1 | 0 | 1 | 06/11/2024 | 06/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 7/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2026 | Connected |  | N
National Grid | LYNN | 402955 | 01902 | 99.9 | Solar | 05_14_63L2 | 07/12/2022 | 09/07/2022 | 41 | 30 | 11 | 09/08/2022 | 09/08/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 722072 | 01854 | 11.5 | Solar | 05_14_77L3 | 10/02/2025 | 10/13/2025 | 6 | 3 | 3 | 10/14/2025 | 10/14/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 578035 | 01810 | 8.7 | Solar | 05_01_225W4 | 01/08/2024 | 01/12/2024 | 4 | 0 | 4 | 01/16/2024 | 01/16/2024 | 23 | 0 | 23 | 04/05/2024 | 09/19/2024 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 09/19/2024 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 5/29/2024 |  | 5/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | METHUEN | 654226 | 01844 | 10 | Solar | 05_01_3J375 | 11/15/2024 | 01/08/2025 | 13 | 10 | 3 | 01/09/2025 | 01/09/2025 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | TYNGSBORO | 177743 | 01879 | 5 | Solar | 05_01_525L1 | 05/31/2017 | 05/31/2017 | 47 | 47 | 0 | 08/08/2017 | 08/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2017 |  | 5/31/2018 | N | EXP | 281 |  |  | 0 | 0 | 0 | 12/19/2017 | 12/19/2017 | 12/20/2017 | Connected |  | N
National Grid | LEOMINSTER | 662668 | 01453 | 4.225 | Solar | 05_01_6W2 | 12/26/2024 | 01/15/2025 | 9 | 7 | 2 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | WORCESTER | 174648 | 01609 | 499 | Solar | 05_05_19W74 | 12/24/2013 | 12/24/2013 | 6 | 0 | 6 | 01/06/2014 | 01/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2014 | 12/24/2013 | 4/8/2016 | Y | EXP | 801 | 01/28/2016 | 03/25/2016 | 39 | 0 | 39 | 1/25/2016 | 1/25/2016 | 4/14/2016 | Connected |  | N
National Grid | NORTH BROOKFIELD | 388680 | 01535 | 9.86 | Solar | 05_05_318W3 | 10/14/2021 | 10/19/2021 | 3 | 3 | 0 | 10/20/2021 | 10/20/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 |  | 1/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N
National Grid | WORCESTER | 657446 | 01602 | 13.775 | Solar | 05_12_3J903 | 11/27/2024 | 12/24/2024 | 11 | 7 | 4 | 12/26/2024 | 12/26/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 175458 | 02715 | 60 | Natural Gas | 05_14_21L3 | 07/17/2014 | 07/17/2014 | 3 | 0 | 3 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2014 |  | 10/31/2014 | N | EXP | 70 |  |  | 0 | 0 | 0 | 11/4/2014 | 11/4/2014 | 11/10/2014 | Connected |  | N
National Grid | BOLTON | 606384 | 01740 |  | Battery Add-On | 05_14_54L3 | 04/24/2024 | 04/29/2024 | 3 | 0 | 3 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  | 10/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2024 | Connected |  | N
National Grid | LYNN | 408867 | 01902 | 0 | Other | 05_14_63L2 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/05/2022 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 722435 | 01854 | 23 | Solar | 05_14_77L3 | 10/31/2025 | 11/12/2025 | 6 | 1 | 5 | 11/13/2025 | 11/13/2025 | 50 | 28 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | ANDOVER | 598623 | 01810 | 15.2 | Solar | 05_01_225W4 | 03/21/2024 | 03/26/2024 | 14 | 12 | 2 | 08/12/2024 | 08/12/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 9/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | METHUEN | 666721 | 01844 | 5.76 | Solar | 05_01_3J375 | 01/20/2025 | 01/30/2025 | 4 | 0 | 4 | 01/31/2025 | 01/31/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 178239 | 01854 | 2000 | Solar | 05_01_525L1 | 02/20/2018 | 02/20/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2018 |  | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/25/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 662627 | 01453 | 6.825 | Solar | 05_01_6W2 | 12/26/2024 | 01/15/2025 | 6 | 0 | 6 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 12/26/2024 | 3/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N
National Grid | WORCESTER | 175198 | 01609 | 2000 | Solar | 05_05_19W74 | 04/26/2011 | 04/26/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/25/2011 | 06/28/2011 | 23 | 0 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2014 |  | 12/31/2016 | N | STD | 901 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 418047 | 01535 | 15.2 | Solar | 05_05_318W3 | 03/16/2022 | 03/18/2022 | 3 | 2 | 1 | 03/21/2022 | 03/21/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 668521 | 01603 | 3.8 | Solar | 05_12_3J903 | 01/29/2025 | 02/17/2025 | 3 | 0 | 3 | 02/18/2025 | 02/18/2025 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 01/29/2025 | 6/25/2026 | Y | EXP | 365 | 06/14/2025 | 10/29/2025 | 138 | 0 | 138 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 176420 | 02715 | 6 | Solar | 05_14_21L3 | 12/07/2015 | 12/07/2015 | 2 | 2 | 0 | 12/10/2015 | 12/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2015 |  | 12/13/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 5/10/2016 | 5/10/2016 | 6/2/2016 | Connected |  | N
National Grid | BERLIN | 619582 | 01503 | 0 | Battery Add-On | 05_14_54L3 | 06/21/2024 | 06/25/2024 | 2 | 0 | 2 | 06/26/2024 | 06/26/2024 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2024 | Connected |  | N
National Grid | LYNN | 414323 | 01902 | 499 | Solar | 05_14_63L2 | 04/01/2022 | 05/25/2022 | 37 | 31 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2022 | 06/28/2022 | 22 | 0 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 04/01/2022 | 1/20/2025 | Y | STD | 43 | 04/19/2024 | 08/16/2024 | 120 | 28 | 92 |  |  | 1/17/2025 | Connected |  | N
National Grid | LOWELL | 757292 | 01852 | 19.38 | Solar | 05_14_78L1 | 03/19/2026 | 03/23/2026 | 2 | 0 | 2 | 03/24/2026 | 03/24/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 612544 | 01810 | 5.76 | Solar | 05_01_225W4 | 05/21/2024 | 07/01/2024 | 2 | 0 | 2 | 07/02/2024 | 07/02/2024 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 | 05/21/2024 | 7/31/2025 | Y | EXP | 365 | 09/18/2024 | 09/17/2024 | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | METHUEN | 709748 | 01844 | 5.76 | Solar | 05_01_3J375 | 08/07/2025 | 08/12/2025 | 2 | 0 | 2 | 08/13/2025 | 08/13/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 178298 | 01854 | 4980 | Solar | 05_01_525L1 | 11/15/2017 | 01/08/2018 | 34 | 23 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/09/2018 | 23 | 12 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2018 |  | 12/31/2019 | N | STD | 502 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 663489 | 01453 | 3.8 | Solar | 05_01_6W2 | 01/02/2025 | 01/16/2025 | 5 | 0 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 01/02/2025 | 3/14/2026 | Y | EXP | 365 | 05/16/2025 | 11/21/2025 | 190 | 0 | 190 |  |  | 12/9/2025 | Connected |  | N
National Grid | WORCESTER | 175717 | 01610 | 1000 | Solar | 05_05_19W74 | 12/26/2014 | 12/26/2014 | 17 | 15 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 429894 | 01535 | 15.2 | Solar | 05_05_318W3 | 05/11/2022 | 05/12/2022 | 1 | 0 | 1 | 05/13/2022 | 05/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2022 |  | 8/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2022 | Connected |  | N
National Grid | WORCESTER | 670620 | 01602 | 7.6 | Solar | 05_12_3J903 | 02/11/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2025 | Connected |  | N
National Grid | DIGHTON | 176495 | 02764 | 6 | Solar | 05_14_21L3 | 12/11/2015 | 12/11/2015 | 2 | 2 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2015 |  | 12/16/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 5/10/2016 | 5/10/2016 | 6/22/2016 | Connected |  | N
National Grid | BERLIN | 624612 | 01503 | 22.8 | Solar | 05_14_54L3 | 07/15/2024 | 07/17/2024 | 2 | 0 | 2 | 07/18/2024 | 07/18/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 458326 | 01902 | 7.83 | Solar | 05_14_63L2 | 10/27/2022 | 11/21/2022 | 16 | 14 | 2 | 11/22/2022 | 11/22/2022 | 21 | 0 | 21 | 01/17/2023 | 03/03/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 03/03/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 2/2/2023 |  | 11/30/2024 | N | EXP | 365 | 06/15/2023 | 01/26/2024 | 226 | 3 | 223 |  |  | 3/9/2024 | Connected |  | N
National Grid | LOWELL | 173451 | 01854 | 11.4 | Solar | 05_14_78L1 | 04/11/2018 | 04/11/2018 | 10 | 5 | 5 | 07/11/2018 | 07/11/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 | 04/11/2018 | 8/30/2019 | Y | EXP | 409 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 8/8/2019 | Connected |  | N
National Grid | ANDOVER | 661154 | 01810 | 2.61 | Solar | 05_01_225W4 | 12/17/2024 | 01/24/2025 | 9 | 4 | 5 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 12/17/2024 | 3/14/2026 | Y | EXP | 365 | 05/17/2025 | 05/28/2025 | 12 | 0 | 12 |  |  | 6/7/2025 | Connected |  | N
National Grid | METHUEN | 652194 | 01844 | 0 | Solar | 05_01_406L1 | 12/05/2024 | 12/30/2024 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 02/09/2026 | 276 | 257 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DRACUT | 178480 | 01826 | 4999 | Solar | 05_01_525L1 | 04/03/2018 | 04/04/2018 | 12 | 12 | 0 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 667926 | 01453 | 7.6 | Solar | 05_01_6W2 | 01/27/2025 | 02/14/2025 | 5 | 0 | 5 | 02/18/2025 | 02/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | WORCESTER | 175837 | 01610 | 15.2 | Solar | 05_05_19W74 | 03/04/2015 | 03/04/2015 | 5 | 1 | 4 | 03/12/2015 | 03/12/2015 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2015 |  | 7/31/2015 | N | EXP | 140 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 434493 | 01585 | 15.2 | Solar | 05_05_318W3 | 06/01/2022 | 06/03/2022 | 2 | 0 | 2 | 06/06/2022 | 06/06/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2022 |  | 7/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2023 | Connected |  | N
National Grid | WORCESTER | 676181 | 01602 | 15.2 | Solar | 05_12_3J903 | 03/06/2025 | 04/18/2025 | 31 | 28 | 3 | 04/22/2025 | 04/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 176706 | 02715 | 6.8 | Solar | 05_14_21L3 | 10/27/2015 | 10/27/2015 | 2 | 2 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2015 | 10/27/2015 | 11/2/2016 | Y | EXP | 351 | 05/11/2016 | 05/26/2016 | 11 | 0 | 11 | 11/17/2015 | 11/17/2015 | 10/25/2016 | Connected |  | N
National Grid | BERLIN | 645228 | 01503 | 0 | Battery Add-On | 05_14_54L3 | 10/05/2024 | 10/08/2024 | 2 | 0 | 2 | 10/09/2024 | 10/09/2024 | 83 | 65 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | LYNN | 480100 | 01902 | 3.8 | Solar | 05_14_63L2 | 01/17/2023 | 01/19/2023 | 2 | 0 | 2 | 01/20/2023 | 01/20/2023 | 104 | 83 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 175869 | 01854 | 22.8 | Solar | 05_14_78L1 | 09/25/2015 | 09/25/2015 | 3 | 3 | 0 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2015 |  | 10/3/2016 | N | EXP | 367 |  |  | 0 | 0 | 0 | 12/7/2015 | 12/7/2015 | 12/7/2015 | Connected |  | N
National Grid | ANDOVER | 666188 | 01810 | 10 | Solar | 05_01_225W4 | 01/16/2025 | 02/14/2025 | 5 | 1 | 4 | 02/18/2025 | 02/18/2025 | 103 | 88 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 648676 | 01844 | 999 | Solar | 05_01_406L1 | 12/11/2024 | 03/07/2025 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2025 | 01/28/2026 | 222 | 203 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DRACUT | 184669 | 01826 | 1800 | Solar | 05_01_525L1 | 05/09/2018 | 05/09/2018 | 4 | 0 | 4 |  |  | 43 | 41 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 670286 | 01453 | 3.49 | Solar | 05_01_6W2 | 02/05/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | LEICESTER | 175827 | 01611 | 7.6 | Solar | 05_05_19W74 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2015 |  | 9/27/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 3/24/2016 | 3/24/2016 | 3/24/2016 | Connected |  | N
National Grid | SPENCER | 462578 | 01562 | 60 | Solar | 05_05_318W3 | 10/06/2022 | 11/07/2022 | 22 | 12 | 10 | 11/08/2022 | 11/08/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2023 | 10/06/2022 | 6/25/2024 | Y | EXP | 133 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N
National Grid | WORCESTER | 753088 | 01603 | 10 | Solar | 05_12_40J2 | 02/25/2026 | 03/03/2026 | 2 | 0 | 2 | 03/27/2026 | 03/27/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DIGHTON | 176926 | 02715 | 10 | Solar | 05_14_21L3 | 11/20/2015 | 11/20/2015 | 2 | 2 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2015 |  | 11/25/2016 | N | EXP | 347 |  |  | 0 | 0 | 0 | 12/14/2015 | 12/14/2015 | 9/14/2016 | Connected |  | N
National Grid | BERLIN | 657336 | 01503 | 10 | Solar | 05_14_54L3 | 11/27/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/27/2024 | 2/21/2026 | Y | EXP | 365 | 04/24/2025 | 04/23/2025 | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | LYNN | 524456 | 01902 | 3.8 | Solar | 05_14_63L2 | 05/15/2023 | 05/16/2023 | 1 | 0 | 1 | 05/17/2023 | 05/17/2023 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 177087 | 01854 | 170 | Solar | 05_14_78L1 | 10/14/2016 | 10/14/2016 | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2016 | 10/14/2016 | 6/11/2019 | Y | EXP | 910 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | Connected |  | N
National Grid | ANDOVER | 417558 | 01810 | 4999.2 | Solar | 05_01_226L1 | 04/20/2022 | 06/21/2022 | 42 | 34 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/22/2022 | 07/20/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 04/20/2022 | 10/23/2027 | Y | STD | 673 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | METHUEN | 677898 | 01844 | 100 | Solar | 05_01_406L1 | 04/24/2025 | 06/06/2025 | 30 | 20 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DRACUT | 195871 | 01826 | 2000 | Solar | 05_01_525L1 | 12/04/2018 | 12/24/2018 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 | 01/24/2019 | 37 | 0 | 37 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 680789 | 01453 | 15.08 | Solar | 05_01_6W2 | 03/26/2025 | 03/28/2025 | 3 | 1 | 2 | 03/31/2025 | 03/31/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2025 | Connected |  | N
National Grid | LEICESTER | 176302 | 01542 | 490 | Solar | 05_05_19W74 | 09/15/2015 | 09/15/2015 | 0 | 0 | 0 | 09/15/2015 | 09/15/2015 | 243 | 0 | 243 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/20/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 478862 | 01005 | 16.82 | Solar | 05_05_318W3 | 11/18/2022 | 11/23/2022 | 3 | 0 | 3 | 11/25/2022 | 11/25/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 |  | 5/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2023 | Connected |  | N
National Grid | WORCESTER | 757860 | 01602 | 0 | Solar | 05_12_40J2 | 03/26/2026 | 03/30/2026 | 2 | 0 | 2 | 03/31/2026 | 03/31/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOMERSET | 177872 | 02726 | 6 | Solar | 05_14_21L3 | 08/14/2017 | 08/14/2017 | 170 | 0 | 170 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/19/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 657602 | 01503 | 10 | Solar | 05_14_54L3 | 11/29/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/29/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | ROCKPORT | 527876 | 01966 | 3.8 | Solar | 05_14_63L2 | 06/01/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 177116 | 01854 | 150 | Solar | 05_14_78L1 | 10/14/2016 | 10/14/2016 | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2017 | 10/14/2016 | 3/11/2019 | Y | EXP | 774 |  |  | 0 | 0 | 0 |  |  | 2/26/2019 | Connected |  | N
National Grid | ANDOVER | 541794 | 01810 | 999 | Solar | 05_01_226L1 | 10/13/2023 | 12/18/2023 | 45 | 36 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 12/24/2024 | 03/14/2025 | 54 | 0 | 54 | 10/4/2024 | 10/13/2023 |  | Y | CMPX | 358 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | METHUEN | 746404 | 01844 | 20 | Solar | 05_01_406L1 | 01/21/2026 | 01/27/2026 | 4 | 0 | 4 | 01/28/2026 | 01/28/2026 | 45 | 30 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 385041 | 01826 | 2000 | Solar | 05_01_525L1 | 10/29/2021 | 12/02/2021 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2021 | 01/05/2022 | 23 | 0 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 683397 | 01463 | 7.6 | Solar | 05_01_6W2 | 04/07/2025 | 04/24/2025 | 4 | 1 | 3 | 05/08/2025 | 05/08/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/07/2025 | 6/12/2026 | Y | EXP | 365 | 10/02/2025 | 10/03/2025 | 2 | 0 | 2 |  |  | 10/7/2025 | Connected |  | N
National Grid | OXFORD | 176535 | 01537 | 6 | Solar | 05_05_19W74 | 02/09/2016 | 02/09/2016 | 3 | 3 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/15/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 6/16/2016 | 6/16/2016 | 6/23/2016 | Connected |  | N
National Grid | NORTH BROOKFIELD | 482613 | 01535 | 0 | Solar | 05_05_318W3 | 12/13/2022 | 01/03/2023 | 13 | 8 | 5 | 01/04/2023 | 01/04/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 1/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2024 | Connected |  | N
National Grid | WORCESTER | 176236 | 01603 | 15 | Solar | 05_12_40J2 | 02/17/2015 | 02/17/2015 | 5 | 0 | 5 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2015 |  | 6/30/2015 | N | EXP | 124 |  |  | 0 | 0 | 0 | 4/1/2015 | 4/1/2015 | 7/2/2015 | Connected |  | N
National Grid | DIGHTON | 177958 | 02764 | 6 | Solar | 05_14_21L3 | 10/26/2017 | 10/26/2017 | 80 | 79 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 666604 | 01503 | 0 | Battery Add-On | 05_14_54L3 | 01/17/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2025 | Connected |  | N
National Grid | ROCKPORT | 568866 | 01966 | 10 | Solar | 05_14_63L2 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 36 | 12 | 24 | 04/01/2024 | 04/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 04/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 4/22/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 178082 | 01854 | 16.08 | Solar | 05_14_78L1 | 05/09/2017 | 05/09/2017 | 195 | 195 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/14/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 723303 | 01810 | 13.611 | Solar | 05_01_226L1 | 10/07/2025 | 10/14/2025 | 2 | 0 | 2 | 10/30/2025 | 10/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 | 10/07/2025 | 12/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | METHUEN | 750264 | 01844 | 5.76 | Solar | 05_01_406L1 | 02/10/2026 | 02/11/2026 | 3 | 0 | 3 | 02/24/2026 | 02/24/2026 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 406582 | 01826 | 6 | Solar | 05_01_525L1 | 02/09/2022 | 02/14/2022 | 3 | 0 | 3 | 02/15/2022 | 02/15/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 | 02/09/2022 | 5/26/2023 | Y | EXP | 365 | 04/29/2022 | 05/19/2022 | 21 | 0 | 21 |  |  | 6/2/2022 | Connected |  | Y
National Grid | PEPPERELL | 687066 | 01463 | 15.2 | Solar | 05_01_6W2 | 04/23/2025 | 05/06/2025 | 9 | 5 | 4 | 05/07/2025 | 05/07/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | LEICESTER | 176649 | 01524 | 6 | Solar | 05_05_19W74 | 02/17/2016 | 02/17/2016 | 2 | 2 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2016 |  | 2/23/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 6/6/2016 | Connected |  | N
National Grid | NORTH BROOKFIELD | 484982 | 01535 | 7.6 | Solar | 05_05_318W3 | 01/04/2023 | 01/05/2023 | 1 | 0 | 1 | 01/06/2023 | 01/06/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 2/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2023 | Connected |  | Y
National Grid | WORCESTER | 177497 | 01603 | 15.2 | Solar | 05_12_40J2 | 12/14/2016 | 12/14/2016 | 4 | 3 | 1 | 12/20/2016 | 12/20/2016 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 | 12/14/2016 | 10/12/2018 | Y | EXP | 660 | 05/28/2016 | 02/03/2017 | 169 | 3 | 166 |  |  | 10/3/2018 | Connected |  | N
National Grid | DIGHTON | 178024 | 02764 | 5.47 | Solar | 05_14_21L3 | 08/31/2017 | 08/31/2017 | 29 | 27 | 2 | 10/13/2017 | 10/13/2017 | 78 | 0 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 |  | 9/5/2018 | N | EXP | 324 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 674675 | 01503 | 10 | Solar | 05_14_54L3 | 03/03/2025 | 03/06/2025 | 3 | 0 | 3 | 03/07/2025 | 03/07/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | ROCKPORT | 599558 | 01966 | 10.075 | Solar | 05_14_63L2 | 04/05/2024 | 04/09/2024 | 3 | 1 | 2 | 04/10/2024 | 04/10/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  | 4/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | LOWELL | 178663 | 01854 | 42 | Solar | 05_14_78L1 | 03/16/2018 | 03/16/2018 | 5 | 0 | 5 | 03/23/2018 | 03/23/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 |  | 3/21/2019 | N | EXP | 316 | 10/31/2018 | 02/07/2019 | 99 | 0 | 99 |  |  | 5/1/2019 | Connected |  | N
National Grid | ANDOVER | 742259 | 01845 | 11.5 | Solar | 05_01_226L1 | 12/26/2025 | 12/30/2025 | 1 | 0 | 1 | 01/29/2026 | 01/29/2026 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 757731 | 01844 | 20 | Solar | 05_01_406L1 | 03/19/2026 | 03/24/2026 | 3 | 0 | 3 | 03/25/2026 | 03/25/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 534547 | 01826 | 0 | Solar | 05_01_525L1 | 06/16/2023 | 06/23/2023 | 4 | 3 | 1 | 06/26/2023 | 06/26/2023 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 4/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 692430 | 01463 | 10 | Solar | 05_01_6W2 | 08/22/2025 | 09/11/2025 | 12 | 9 | 3 | 09/11/2025 | 09/11/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | OXFORD | 177124 | 01537 | 2000 | Solar | 05_05_19W74 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 | 01/04/2017 | 49 | 35 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2017 | 10/20/2016 | 4/22/2019 | Y | STD | 640 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 488595 | 01535 | 15.95 | Solar | 05_05_318W3 | 01/11/2023 | 01/27/2023 | 12 | 11 | 1 | 01/30/2023 | 01/30/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 4/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2023 | Connected |  | N
National Grid | WORCESTER | 320446 | 01603 | 8 | Solar | 05_12_40J2 | 10/20/2020 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 178418 | 02726 | 6 | Solar | 05_14_21L3 | 01/16/2018 | 01/16/2018 | 22 | 0 | 22 | 01/31/2018 | 01/31/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2018 |  | 1/22/2019 | N | EXP | 340 |  |  | 0 | 0 | 0 |  |  | 6/8/2018 | Connected |  | N
National Grid | BERLIN | 694492 | 01503 | 10 | Solar | 05_14_54L3 | 06/02/2025 | 06/16/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 37 | 23 | 14 | 08/22/2025 | 08/21/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 619212 | 01966 | 14.95 | Solar | 05_14_63L2 | 06/22/2024 | 07/23/2024 | 9 | 7 | 2 | 07/24/2024 | 07/24/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 06/22/2024 | 9/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | LOWELL | 178685 | 01854 | 7.6 | Solar | 05_14_78L1 | 12/18/2017 | 12/18/2017 | 8 | 0 | 8 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 12/24/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 11/7/2018 | Connected |  | N
National Grid | ANDOVER | 175223 | 01810 | 5 | Solar | 05_01_226L1 | 01/05/2015 | 01/05/2015 | 28 | 25 | 3 | 02/17/2015 | 02/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2015 |  | 5/31/2015 | N | EXP | 103 |  |  | 0 | 0 | 0 | 5/11/2015 | 5/11/2015 | 2/11/2016 | Connected |  | N
National Grid | METHUEN | 174214 | 01844 | 1000 | Solar | 05_01_406L1 | 12/20/2011 | 12/20/2011 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 571567 | 01826 | 10 | Solar | 05_01_525L1 | 12/29/2023 | 02/07/2024 | 27 | 26 | 1 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 12/29/2023 | 2/28/2025 | Y | EXP | 365 | 04/30/2024 | 05/14/2024 | 15 | 0 | 15 |  |  | 7/3/2024 | Connected |  | N
National Grid | PEPPERELL | 711191 | 01463 | 5.76 | Solar | 05_01_6W2 | 08/11/2025 | 08/29/2025 | 2 | 0 | 2 | 09/12/2025 | 09/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | OXFORD | 177123 | 01537 | 3625 | Solar | 05_05_19W74 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2016 | 01/04/2017 | 48 | 35 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2017 | 10/20/2016 | 6/27/2024 | Y | STD | 404 | 09/29/2023 | 02/05/2024 | 129 | 45 | 84 |  |  | 6/24/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 502268 | 01535 | 7.6 | Solar | 05_05_318W3 | 03/09/2023 | 03/31/2023 | 17 | 16 | 1 | 04/03/2023 | 04/03/2023 | 66 | 46 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 8/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2023 | Connected |  | N
National Grid | WORCESTER | 336432 | 01611 | 7.44 | Solar | 05_12_40J2 | 01/12/2021 | 01/13/2021 | 0 | 0 | 0 | 01/14/2021 | 01/14/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 | 01/12/2021 | 1/12/2022 | Y | EXP | 365 | 04/21/2021 | 04/20/2021 | 0 | 0 | 0 |  |  | 5/25/2021 | Connected |  | N
National Grid | DIGHTON | 198546 | 02715 | 7.6 | Solar | 05_14_21L3 | 11/16/2018 | 11/21/2018 | 3 | 3 | 0 | 11/26/2018 | 11/26/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 696418 | 01740 | 0 | Battery Add-On | 05_14_54L3 | 06/05/2025 | 06/20/2025 | 10 | 6 | 4 | 06/23/2025 | 06/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 8/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 641365 | 01966 | 7.6 | Solar | 05_14_63L2 | 09/18/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | LOWELL | 188124 | 01854 | 15.2 | Solar | 05_14_78L1 | 06/14/2018 | 06/14/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175461 | 01810 | 499 | Solar | 05_01_226L1 | 09/23/2014 | 09/23/2014 | 32 | 27 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 12/04/2014 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 174473 | 01844 | 32.4 | Solar | 05_01_406L1 | 04/27/2011 | 04/27/2011 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2011 |  | 10/31/2012 | N | EXP | 329 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 7/2/2012 | Connected |  | N
National Grid | DRACUT | 646275 | 01826 | 5.76 | Solar | 05_01_525L1 | 10/10/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | PEPPERELL | 742103 | 01463 | 5.76 | Solar | 05_01_6W2 | 12/23/2025 | 12/29/2025 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 177288 | 01507 | 233.1 | Solar | 05_05_19W74 | 06/17/2016 | 06/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/16/2016 | 09/15/2016 | 21 | 4 | 17 | 06/20/2016 | 07/15/2016 | 18 | 5 | 13 | 09/15/2016 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 6/25/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 554413 | 01535 | 0 | Battery Add-On | 05_05_318W3 | 09/22/2023 | 09/26/2023 | 2 | 0 | 2 | 09/27/2023 | 09/27/2023 | 81 | 60 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | WORCESTER | 376072 | 01602 | 10 | Solar | 05_12_40J2 | 09/02/2021 | 09/02/2021 | 12 | 10 | 2 | 09/03/2021 | 09/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2021 | 09/02/2021 | 1/28/2023 | Y | EXP | 365 | 12/10/2021 | 01/27/2022 | 49 | 0 | 49 |  |  | 1/31/2022 | Connected |  | N
National Grid | DIGHTON | 305218 | 02715 | 10 | Solar | 05_14_21L3 | 08/31/2020 | 09/03/2020 | 2 | 0 | 2 | 09/04/2020 | 09/04/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/31/2020 | 8/2/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2021 | Connected |  | N
National Grid | BERLIN | 706271 | 01503 | 3.8 | Solar | 05_14_54L3 | 07/21/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 646960 | 01966 | 10 | Solar | 05_14_63L2 | 10/24/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | LOWELL | 196115 | 01854 | 10 | Solar | 05_14_78L1 | 09/17/2018 | 10/30/2018 | 19 | 18 | 1 | 10/31/2018 | 10/31/2018 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 09/17/2018 | 5/27/2019 | Y | EXP | 181 | 02/21/2019 | 02/20/2019 | 0 | 0 | 0 |  |  | 5/13/2019 | Connected |  | N
National Grid | ANDOVER | 175774 | 01810 | 990 | Solar | 05_01_226L1 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/26/2014 | 09/25/2014 | 21 | 0 | 21 |  | 0 | 0 | 0 | 10/08/2015 | 10/28/2015 | 13 | 13 | 0 | 12/11/2015 | 08/15/2014 | 7/30/2016 | Y | STD | 232 | 04/06/2016 | 07/28/2016 | 77 | 0 | 77 | 7/21/2016 | 7/21/2016 | 7/28/2016 | Connected |  | N
National Grid | METHUEN | 174794 | 01844 | 1000 | Solar | 05_01_406L1 | 07/05/2011 | 07/05/2011 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2012 | 07/05/2011 | 7/24/2012 | Y | STD | 10 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 7/24/2012 | Connected |  | N
National Grid | DRACUT | 670518 | 01826 | 3.8 | Solar | 05_01_525L1 | 02/06/2025 | 02/26/2025 | 3 | 0 | 3 | 02/27/2025 | 02/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | PEPPERELL | 730496 | 01463 | 5.76 | Solar | 05_01_7J386 | 10/30/2025 | 11/01/2025 | 2 | 0 | 2 | 12/04/2025 | 12/04/2025 | 29 | 17 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | OXFORD | 177465 | 01537 | 192 | Solar | 05_05_19W74 | 03/01/2017 | 03/01/2017 | 15 | 13 | 2 | 03/23/2017 | 03/23/2017 | 42 | 28 | 14 | 06/21/2017 | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 | 7/27/2017 |  | 3/7/2018 | N | EXP | 223 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | NORTH BROOKFIELD | 566220 | 01535 | 7.6 | Solar | 05_05_318W3 | 10/25/2023 | 10/26/2023 | 1 | 0 | 1 | 10/27/2023 | 10/27/2023 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2023 | Connected |  | N
National Grid | WORCESTER | 398018 | 01602 | 5.52 | Solar | 05_12_40J2 | 11/29/2021 | 11/30/2021 | 1 | 1 | 0 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 12/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2022 | Connected |  | N
National Grid | DIGHTON | 330497 | 02715 | 3.8 | Solar | 05_14_21L3 | 12/21/2020 | 12/30/2020 | 5 | 0 | 5 | 12/31/2020 | 12/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/21/2020 | 9/26/2022 | Y | EXP | 365 | 08/25/2021 | 10/05/2021 | 36 | 0 | 36 |  |  | 6/15/2022 | Connected |  | N
National Grid | BERLIN | 708145 | 01503 | 17.6 | Solar | 05_14_54L3 | 08/01/2025 | 08/06/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 |  | 9/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | ROCKPORT | 657546 | 01966 | 5.76 | Solar | 05_14_63L2 | 11/28/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | LOWELL | 193202 | 01854 | 15.2 | Solar | 05_14_78L1 | 08/10/2018 | 09/10/2018 | 6 | 6 | 0 | 09/11/2018 | 09/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2018 | 08/10/2018 | 7/7/2020 | Y | EXP | 500 | 02/14/2019 | 03/11/2019 | 25 | 0 | 25 |  |  | 6/19/2020 | Connected |  | N
National Grid | ANDOVER | 175871 | 01810 | 7.6 | Solar | 05_01_226L1 | 09/25/2015 | 09/25/2015 | 2 | 2 | 0 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2015 |  | 10/4/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 12/2/2015 | 12/2/2015 | 12/2/2015 | Connected |  | N
National Grid | METHUEN | 174835 | 01844 | 0 | Solar | 05_01_406L1 | 08/03/2011 | 08/03/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2012 | 08/03/2011 | 12/31/2012 | Y | STD | 277 | 07/09/2012 | 10/18/2012 | 71 | 0 | 71 | 9/27/2012 | 9/27/2012 | 10/16/2012 | Connected |  | N
National Grid | DRACUT | 681289 | 01826 | 15 | Solar | 05_01_525L1 | 03/31/2025 | 05/23/2025 | 39 | 35 | 4 | 05/27/2025 | 05/27/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | PEPPERELL | 178422 | 01463 | 4000 | Solar | 05_01_7J386 | 01/16/2018 | 02/21/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2018 | 03/20/2018 | 19 | 1 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 177464 | 01507 | 96 | Solar | 05_05_19W74 | 03/01/2017 | 03/01/2017 | 15 | 13 | 2 | 03/23/2017 | 03/23/2017 | 13 | 0 | 13 | 06/21/2017 | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 | 7/27/2017 |  | 3/7/2018 | N | EXP | 223 |  |  | 0 | 0 | 0 |  |  | 5/22/2018 | Connected |  | N
National Grid | NORTH BROOKFIELD | 612829 | 01535 | 10 | Solar | 05_05_318W3 | 05/22/2024 | 05/24/2024 | 3 | 2 | 1 | 05/28/2024 | 05/28/2024 | 34 | 22 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2024 | Connected |  | N
National Grid | WORCESTER | 418962 | 01603 | 0 | Solar | 05_12_40J2 | 04/04/2022 | 04/05/2022 | 1 | 0 | 1 | 04/06/2022 | 04/06/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 |  | 4/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2022 | Connected |  | N
National Grid | DIGHTON | 406690 | 02764 | 43.2 | Solar | 05_14_21L3 | 01/19/2022 | 01/21/2022 | 3 | 1 | 2 | 01/24/2022 | 01/24/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 |  | 3/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2022 | Connected |  | N
National Grid | BOLTON | 712170 | 01740 | 15.2 | Solar | 05_14_54L3 | 08/18/2025 | 08/20/2025 | 2 | 0 | 2 | 08/21/2025 | 08/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | N
National Grid | ROCKPORT | 668345 | 01966 | 3.8 | Solar | 05_14_63L2 | 01/28/2025 | 03/17/2025 | 9 | 3 | 6 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 01/28/2025 | 4/25/2026 | Y | EXP | 365 | 07/24/2025 | 02/02/2026 | 194 | 0 | 194 |  |  | 11/24/2025 | Connected |  | N
National Grid | LOWELL | 192918 | 01854 | 7.6 | Solar | 05_14_78L1 | 08/07/2018 | 10/26/2018 | 7 | 7 | 0 | 10/29/2018 | 10/29/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 176103 | 01810 | 6 | Solar | 05_01_226L1 | 06/19/2015 | 06/19/2015 | 5 | 5 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/28/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 12/1/2015 | Connected |  | N
National Grid | METHUEN | 174948 | 01844 | 1000 | Solar | 05_01_406L1 | 11/18/2011 | 11/18/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2012 | 03/12/2012 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/3/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 360612 | 01826 | 1625 | Solar | 05_01_525L2 | 09/16/2021 | 12/13/2021 | 60 | 50 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PEPPERELL | 190628 | 01463 | 5 | Solar | 05_01_7J386 | 07/13/2018 | 08/29/2018 | 23 | 0 | 23 | 08/30/2018 | 08/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 177891 | 01524 | 3.8 | Solar | 05_05_19W74 | 04/13/2017 | 04/13/2017 | 6 | 6 | 0 | 04/24/2017 | 04/24/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2017 |  | 4/18/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 10/27/2017 | 10/27/2017 | 10/27/2017 | Connected |  | N
National Grid | NORTH BROOKFIELD | 637222 | 01535 | 6.08 | Solar | 05_05_318W3 | 09/03/2024 | 09/16/2024 | 3 | 1 | 2 | 09/17/2024 | 09/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | AUBURN | 420293 | 01501 | 10 | Solar | 05_12_40J2 | 03/28/2022 | 03/29/2022 | 1 | 0 | 1 | 03/30/2022 | 03/30/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2022 |  | 4/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2022 | Connected |  | N
National Grid | DIGHTON | 409499 | 02764 | 6 | Solar | 05_14_21L3 | 04/12/2022 |  | 63 | 27 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 713352 | 01503 | 10.88 | Solar | 05_14_54L3 | 09/10/2025 | 09/22/2025 | 7 | 3 | 4 | 09/23/2025 | 09/23/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | ROCKPORT | 682966 | 01966 | 0 | Solar | 05_14_63L2 | 04/07/2025 | 04/25/2025 | 13 | 9 | 4 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 214576 | 01854 | 3 | Solar | 05_14_78L1 | 03/22/2019 | 03/29/2019 | 4 | 0 | 4 | 04/01/2019 | 04/01/2019 | 125 | 25 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 177228 | 01810 | 38 | Solar | 05_01_226L1 | 11/02/2016 | 11/02/2016 | 2 | 2 | 0 | 11/07/2016 | 11/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2016 |  | 11/8/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | METHUEN | 175031 | 01844 | 1000 | Solar | 05_01_406L1 | 03/21/2013 | 03/21/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2013 | 05/07/2013 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 650533 | 01826 | 4980 | Solar | 05_01_525L2 | 01/13/2025 | 01/29/2025 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/30/2025 | 03/10/2025 | 28 | 8 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PEPPERELL | 195599 | 01463 | 7.6 | Solar | 05_01_7J386 | 09/11/2018 | 12/03/2018 | 26 | 20 | 6 | 12/04/2018 | 12/04/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 178015 | 01524 | 15.2 | Solar | 05_05_19W74 | 06/29/2017 | 06/29/2017 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/4/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 640073 | 01531 | 0 | Battery Add-On | 05_05_318W3 | 09/13/2024 | 09/17/2024 | 2 | 0 | 2 | 09/18/2024 | 09/18/2024 | 14 | 6 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2024 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | WORCESTER | 442681 | 01603 | 5.8 | Solar | 05_12_40J2 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2022 | 07/19/2022 | 4/23/2024 | Y | EXP | 365 | 12/22/2022 | 04/24/2023 | 124 | 0 | 124 |  |  | 4/27/2023 | Connected |  | N
National Grid | SOMERSET | 493495 | 02726 | 16680 | Hydro | 05_14_21L3 | 01/19/2023 | 04/17/2023 | 60 | 51 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2023 | 06/05/2023 | 34 | 15 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 732162 | 01503 | 13.8 | Solar | 05_14_54L3 | 11/06/2025 | 11/07/2025 | 2 | 0 | 2 | 11/19/2025 | 11/19/2025 | 69 | 53 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 699916 | 01966 | 16.72 | Solar | 05_14_63L2 | 06/23/2025 | 06/27/2025 | 4 | 0 | 4 | 06/30/2025 | 06/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 | 06/23/2025 | 8/8/2026 | Y | EXP | 365 | 11/14/2025 | 11/26/2025 | 13 | 0 | 13 |  |  | 12/11/2025 | Connected |  | N
National Grid | LOWELL | 218549 | 01854 | 3 | Solar | 05_14_78L1 | 05/08/2019 | 05/17/2019 | 7 | 7 | 0 | 05/20/2019 | 05/20/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 | 05/08/2019 | 3/31/2020 | Y | EXP | 301 | 10/17/2019 | 10/25/2019 | 8 | 0 | 8 |  |  | 11/1/2019 | Connected |  | N
National Grid | ANDOVER | 177520 | 01810 | 1132.2 | Solar | 05_01_226L1 | 09/27/2016 | 09/27/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 | 12/27/2016 | 52 | 40 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/4/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175133 | 01844 | 500 | Solar | 05_01_406L1 | 11/08/2012 | 11/08/2012 | 4 | 0 | 4 | 11/26/2012 | 11/26/2012 | 435 | 0 | 435 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/16/2013 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 654404 | 01826 | 996 | Solar | 05_01_525L2 | 04/23/2025 | 06/20/2025 | 40 | 29 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2025 | 07/21/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PEPPERELL | 201180 | 01463 | 5 | Solar | 05_01_7J386 | 11/14/2018 | 11/15/2018 | 7 | 0 | 7 | 01/22/2019 | 01/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 | 11/14/2018 | 11/13/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2020 | Connected |  | N
National Grid | LEICESTER | 178152 | 01524 | 2700 | Solar | 05_05_19W74 | 12/21/2017 | 12/21/2017 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2018 | 02/09/2018 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 | 12/21/2017 | 9/29/2025 | Y | STD | 414 | 06/04/2021 | 12/31/2021 | 211 | 10 | 201 |  |  | 9/4/2025 | Connected |  | N
National Grid | WEST BROOKFIELD | 682747 | 01585 | 15.2 | Solar | 05_05_318W3 | 04/04/2025 | 04/10/2025 | 4 | 0 | 4 | 04/11/2025 | 04/11/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 04/04/2025 | 5/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | WORCESTER | 523300 | 01603 | 10 | Solar | 05_12_40J2 | 05/02/2023 | 05/04/2023 | 2 | 0 | 2 | 05/05/2023 | 05/05/2023 | 160 | 137 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  | 11/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2024 | Connected |  | N
National Grid | SOMERSET | 537411 | 02726 | 10 | Solar | 05_14_21L3 | 08/07/2023 | 08/08/2023 | 1 | 0 | 1 | 08/09/2023 | 08/09/2023 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 740761 | 01503 | 15.2 | Solar | 05_14_55L1 | 12/17/2025 | 12/18/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2026 |  | 1/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ROCKPORT | 737259 | 01966 | 5.76 | Solar | 05_14_63L2 | 12/01/2025 | 12/03/2025 | 3 | 0 | 3 | 01/21/2026 | 01/21/2026 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 229113 | 01852 | 7.6 | Solar | 05_14_78L1 | 08/30/2019 | 09/04/2019 | 2 | 2 | 0 | 09/05/2019 | 09/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 |  | 9/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2020 | Connected |  | N
National Grid | ANDOVER | 177839 | 01810 | 266.4 | Solar | 05_01_226L1 | 10/13/2017 | 10/13/2017 | 54 | 50 | 4 | 01/11/2018 | 01/11/2018 | 0 | 0 | 0 | 02/28/2018 | 07/26/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 07/26/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 10/21/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175340 | 01844 | 1000 | Solar | 05_01_406L1 | 01/16/2015 | 01/16/2015 | 24 | 21 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2015 | 04/21/2015 | 39 | 0 | 39 |  | 0 | 0 | 0 | 09/30/2015 | 10/29/2015 | 20 | 0 | 20 | 10/29/2015 | 01/16/2015 | 3/31/2018 | Y | STD | 884 |  |  | 0 | 0 | 0 | 7/24/2017 | 7/24/2017 | 3/26/2018 | Connected |  | N
National Grid | DRACUT | 685405 | 01826 | 10 | Solar | 05_01_525L2 | 06/04/2025 | 06/10/2025 | 4 | 0 | 4 | 06/11/2025 | 06/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 | 06/04/2025 | 8/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 227161 | 01463 | 5 | Solar | 05_01_7J386 | 05/20/2019 | 05/28/2019 | 63 | 11 | 52 | 05/29/2019 | 05/29/2019 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 178164 | 01507 | 617 | Solar | 05_05_19W74 | 02/13/2018 | 02/13/2018 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/30/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 | 02/13/2018 | 5/13/2022 | Y | STD | 82 | 05/27/2020 | 08/31/2021 | 461 | 8 | 453 |  |  | 5/13/2022 | Connected |  | N
National Grid | WEST BROOKFIELD | 685270 | 01585 | 15.2 | Solar | 05_05_318W3 | 04/15/2025 | 04/23/2025 | 5 | 0 | 5 | 04/24/2025 | 04/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 534135 | 01603 | 14.79 | Solar | 05_12_40J2 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 52 | 29 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 |  | 9/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2023 | Connected |  | N
National Grid | DIGHTON | 588627 | 02715 | 15 | Solar | 05_14_21L3 | 02/12/2024 | 03/06/2024 | 17 | 15 | 2 | 03/07/2024 | 03/07/2024 | 11 | 8 | 3 | 08/28/2024 | 10/08/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 10/08/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 9/11/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 174994 | 01503 | 13 | Solar | 05_14_55L1 | 03/13/2013 | 03/13/2013 | 6 | 0 | 6 | 03/25/2013 | 03/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2013 |  | 6/28/2013 | N | EXP | 78 |  |  | 0 | 0 | 0 | 4/15/2013 | 4/15/2013 | 6/5/2013 | Connected |  | N
National Grid | ROCKPORT | 208615 | 01966 | 500 | Solar | 05_14_65L1 | 03/25/2019 | 04/23/2019 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2019 | 03/17/2020 | 213 | 42 | 171 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2020 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 242622 | 01854 | 5 | Solar | 05_14_78L1 | 07/18/2019 | 08/14/2019 | 19 | 19 | 0 | 08/15/2019 | 08/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 7/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2020 | Connected |  | N
National Grid | ANDOVER | 177871 | 01845 | 160 | Solar | 05_01_226L1 | 08/11/2017 | 08/11/2017 | 3 | 3 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/16/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 1/4/2018 | 1/4/2018 | 1/4/2018 | Connected |  | N
National Grid | METHUEN | 175439 | 01844 | 1000 | Solar | 05_01_406L1 | 11/24/2014 | 11/24/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2014 | 01/02/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2015 |  | 8/30/2016 | N | STD | 411 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 715702 | 01826 | 10 | Solar | 05_01_525L2 | 08/29/2025 | 09/26/2025 | 3 | 0 | 3 | 09/29/2025 | 09/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 | 08/29/2025 | 11/4/2026 | Y | EXP | 365 | 01/17/2026 |  | 75 | 0 | 75 |  |  |  | Construction |  | N
National Grid | PEPPERELL | 340849 | 01463 | 15.2 | Solar | 05_01_7J386 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2021 | 02/05/2021 | 1/20/2023 | Y | EXP | 475 | 10/05/2022 | 11/14/2022 | 41 | 0 | 41 |  |  | 12/21/2022 | Connected |  | N
National Grid | LEICESTER | 178213 | 01524 | 2000 | Solar | 05_05_19W74 | 03/26/2018 | 03/26/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/30/2018 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2019 | 03/26/2018 | 5/5/2024 | Y | STD | 555 | 01/14/2022 | 02/01/2024 | 748 | 680 | 68 |  |  | 4/15/2024 | Connected |  | N
National Grid | WEST BROOKFIELD | 712988 | 01585 | 19.1 | Solar | 05_05_318W3 | 10/01/2025 | 10/27/2025 | 16 | 14 | 2 | 10/28/2025 | 10/28/2025 | 47 | 28 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 |  | 1/8/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2026 | Connected |  | N
National Grid | WORCESTER | 551438 | 01603 | 10 | Solar | 05_12_40J2 | 11/16/2023 | 11/20/2023 | 2 | 0 | 2 | 11/21/2023 | 11/21/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 1/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2024 | Connected |  | N
National Grid | SOMERSET | 600344 | 02726 | 3.8 | Solar | 05_14_21L3 | 04/05/2024 | 04/09/2024 | 3 | 1 | 2 | 04/10/2024 | 04/10/2024 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 | 04/05/2024 | 5/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2024 | Connected |  | N
National Grid | BERLIN | 177989 | 01503 | 15.2 | Solar | 05_14_55L1 | 08/28/2017 | 08/28/2017 | 27 | 26 | 1 | 10/10/2017 | 10/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 9/4/2018 | N | EXP | 329 |  |  | 0 | 0 | 0 | 12/28/2017 | 12/28/2017 | 12/28/2017 | Connected |  | N
National Grid | ROCKPORT | 653568 | 01966 | 3.8 | Solar | 05_14_65L1 | 11/12/2024 | 12/02/2024 | 4 | 0 | 4 | 12/03/2024 | 12/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 250354 | 01854 | 7.6 | Solar | 05_14_78L1 | 08/26/2019 | 09/03/2019 | 4 | 4 | 0 | 09/04/2019 | 09/04/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2019 | 08/26/2019 | 8/26/2020 | Y | EXP | 365 | 03/13/2020 | 06/02/2020 | 81 | 0 | 81 |  |  | 7/24/2020 | Connected |  | N
National Grid | BOXFORD | 178659 | 01921 | 415 | Solar | 05_01_226L1 | 02/05/2018 | 02/05/2018 | 9 | 0 | 9 | 03/20/2018 | 03/20/2018 | 25 | 0 | 25 | 07/11/2018 | 08/06/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 08/06/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 8/13/2018 |  | 10/21/2020 | N | EXP | 566 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | HAVERHILL | 175598 | 01830 | 772.8 | Solar | 05_01_406L1 | 08/01/2014 | 08/01/2014 | 15 | 10 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2014 | 09/22/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 |  | 12/31/2016 | N | STD | 739 |  |  | 0 | 0 | 0 | 6/20/2016 | 6/20/2016 | 7/20/2016 | Connected |  | N
National Grid | DRACUT | 729007 | 01826 | 7.6 | Solar | 05_01_525L2 | 10/24/2025 | 10/30/2025 | 3 | 0 | 3 | 12/05/2025 | 12/05/2025 | 80 | 65 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PEPPERELL | 341888 | 01463 | 7.6 | Solar | 05_01_7J386 | 02/11/2021 | 02/12/2021 | 0 | 0 | 0 | 02/16/2021 | 02/16/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 | 02/11/2021 | 7/21/2023 | Y | EXP | 365 | 09/23/2021 | 01/17/2022 | 117 | 4 | 113 |  |  | 10/12/2022 | Connected |  | N
National Grid | CHARLTON | 178393 | 01507 | 10 | Solar | 05_05_19W74 | 03/02/2018 | 03/02/2018 | 8 | 0 | 8 | 03/29/2018 | 03/29/2018 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2018 | 03/02/2018 | 3/11/2019 | Y | EXP | 186 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | BROOKFIELD | 723459 | 01506 | 3.8 | Solar | 05_05_318W3 | 10/02/2025 | 10/07/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | LEICESTER | 562901 | 01611 | 9.86 | Solar | 05_12_40J2 | 11/01/2023 | 11/07/2023 | 5 | 2 | 3 | 11/08/2023 | 11/08/2023 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2023 | 11/01/2023 | 12/28/2024 | Y | EXP | 365 | 03/21/2024 | 04/03/2024 | 14 | 0 | 14 |  |  | 6/22/2024 | Connected |  | N
National Grid | DIGHTON | 601226 | 02764 | 5 | Solar | 05_14_21L3 | 04/09/2024 | 04/15/2024 | 4 | 0 | 4 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/09/2024 | 4/23/2025 | Y | EXP | 365 | 05/22/2024 | 07/23/2024 | 63 | 0 | 63 |  |  | 8/21/2024 | Connected |  | N
National Grid | BOLTON | 198292 | 01740 | 9.92 | Solar | 05_14_55L1 | 10/11/2018 | 11/01/2018 | 11 | 4 | 7 | 11/02/2018 | 11/02/2018 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2018 |  | 4/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2020 | Connected |  | N
National Grid | ROCKPORT | 659339 | 01966 | 7.6 | Solar | 05_14_65L1 | 12/10/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 253040 | 01854 | 17.6 | Solar | 05_14_78L1 | 09/09/2019 | 09/11/2019 | 1 | 0 | 1 | 09/12/2019 | 09/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 9/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2020 | Connected |  | N
National Grid | ANDOVER | 185818 | 01845 | 999 | Solar | 05_01_226L1 | 06/27/2018 | 06/27/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/16/2018 | 07/19/2018 | 4 | 3 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2019 |  | 9/3/2020 | N | STD | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 175650 | 01830 | 18 | Solar | 05_01_406L1 | 12/17/2014 | 12/17/2014 | 5 | 1 | 4 | 12/26/2014 | 12/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2015 | 12/17/2014 | 12/31/2016 | Y | EXP | 710 |  |  | 0 | 0 | 0 | 8/30/2016 | 8/30/2016 | 8/30/2016 | Connected |  | N
National Grid | DRACUT | 730718 | 01826 | 10 | Solar | 05_01_525L2 | 11/02/2025 | 11/03/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 54 | 37 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 3/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | PEPPERELL | 627279 | 01463 | 4.06 | Solar | 05_01_7J386 | 07/24/2024 | 07/30/2024 | 3 | 2 | 1 | 07/31/2024 | 07/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 07/24/2024 | 8/13/2025 | Y | EXP | 365 | 10/29/2024 | 10/28/2024 | 0 | 0 | 0 |  |  | 11/1/2024 | Connected |  | N
National Grid | CHARLTON | 178694 | 01507 | 5.2 | Solar | 05_05_19W74 | 02/06/2018 | 02/06/2018 | 16 | 0 | 16 | 03/14/2018 | 03/14/2018 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 2/12/2019 | N | EXP | 286 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 661572 | 01506 | 11.5 | Solar | 05_05_318W5 | 12/23/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 3/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | LEICESTER | 630449 | 01611 | 4.06 | Solar | 05_12_40J2 | 08/06/2024 | 09/17/2024 | 1 | 0 | 1 | 09/18/2024 | 09/18/2024 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | DIGHTON | 617219 | 02764 | 7.6 | Solar | 05_14_21L3 | 06/11/2024 | 06/28/2024 | 3 | 0 | 3 | 07/01/2024 | 07/01/2024 | 18 | 8 | 10 | 08/16/2024 | 09/13/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 09/13/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 9/23/2024 | 06/11/2024 |  | Y | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 247814 | 01740 | 0 | Solar | 05_14_55L1 | 08/22/2019 | 08/22/2019 | 0 | 0 | 0 | 08/23/2019 | 08/23/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/22/2019 | 9/17/2020 | Y | EXP | 365 | 01/11/2020 | 02/07/2020 | 27 | 0 | 27 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 657492 | 01966 | 5.76 | Solar | 05_14_65L3 | 11/27/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/27/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LOWELL | 301330 | 01854 | 7.6 | Solar | 05_14_78L1 | 08/07/2020 | 08/10/2020 | 0 | 0 | 0 | 08/11/2020 | 08/11/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/07/2020 | 8/9/2021 | Y | EXP | 365 | 10/28/2020 | 11/10/2020 | 13 | 0 | 13 |  |  | 1/25/2021 | Connected |  | N
National Grid | ANDOVER | 186572 | 01845 | 1590 | Solar | 05_01_226L1 | 04/15/2019 | 06/05/2019 | 36 | 29 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/06/2019 | 07/02/2019 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 175729 | 01830 | 996 | Solar | 05_01_406L1 | 06/03/2014 | 06/03/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2014 | 07/10/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2014 | 06/03/2014 | 4/23/2016 | Y | STD | 516 | 10/20/2015 | 04/27/2016 | 128 | 0 | 128 | 6/5/2014 | 6/5/2014 | 5/12/2016 | Connected |  | N
National Grid | DRACUT | 734531 | 01826 | 11.52 | Solar | 05_01_525L2 | 11/18/2025 | 11/19/2025 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2026 |  | 3/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | PEPPERELL | 636729 | 01463 | 5.76 | Solar | 05_01_7J386 | 08/30/2024 | 09/06/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 2/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | N
National Grid | CHARLTON | 195446 | 01507 | 2000 | Solar | 05_05_19W74 | 02/07/2020 |  | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 716128 | 01506 | 11.4 | Solar | 05_05_320W1 | 09/02/2025 | 10/02/2025 | 20 | 16 | 4 | 11/04/2025 | 11/04/2025 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 659692 | 01603 | 7.83 | Solar | 05_12_40J2 | 12/10/2024 | 12/29/2024 | 9 | 4 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/10/2024 | 3/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 632778 | 02715 | 10 | Solar | 05_14_21L3 | 08/14/2024 | 08/26/2024 | 1 | 0 | 1 | 08/27/2024 | 08/27/2024 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 310835 | 01532 | 10 | Solar | 05_14_55L1 | 09/03/2020 | 09/08/2020 | 1 | 0 | 1 | 09/09/2020 | 09/09/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2020 |  | 9/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2021 | Connected |  | N
National Grid | ROCKPORT | 176146 | 01966 | 1700 | Solar | 05_14_65L3 | 08/24/2015 | 08/24/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/31/2015 | 09/29/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 05/27/2016 |  | 457 | 21 | 436 | 5/12/2016 |  | 8/12/2016 | N | STD | 92 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 339584 | 01854 | 7.6 | Solar | 05_14_78L1 | 01/29/2021 | 02/02/2021 | 1 | 0 | 1 | 02/03/2021 | 02/03/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2021 | Connected |  | N
National Grid | BOXFORD | 188134 | 01921 | 1000 | Solar | 05_01_226L1 | 06/18/2018 | 06/18/2018 | 23 | 23 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2018 | 07/24/2018 | 1 | 0 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2019 |  | 9/3/2020 | N | STD | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 175808 | 01835 | 100 | Solar | 05_01_406L1 | 05/18/2015 | 05/18/2015 | 5 | 5 | 0 | 05/29/2015 | 05/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2015 |  | 12/31/2016 | N | EXP | 540 |  |  | 0 | 0 | 0 | 10/19/2016 | 10/19/2016 | 9/16/2016 | Connected |  | N
National Grid | DRACUT | 751044 | 01826 | 7.6 | Solar | 05_01_525L2 | 02/13/2026 | 02/16/2026 | 2 | 0 | 2 | 03/03/2026 | 03/03/2026 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PEPPERELL | 654479 | 01463 | 5.76 | Solar | 05_01_7J386 | 11/18/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 215929 | 01540 | 2970 | Solar | 05_05_19W74 | 04/24/2019 | 05/09/2019 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2019 | 06/06/2019 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 726974 | 01585 | 15.2 | Solar | 05_05_320W1 | 10/16/2025 | 10/21/2025 | 3 | 0 | 3 | 10/22/2025 | 10/22/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 706632 | 01603 | 20.475 | Solar | 05_12_40J2 | 07/22/2025 | 08/14/2025 | 16 | 13 | 3 | 08/15/2025 | 08/15/2025 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/8/2025 | Connected |  | N
National Grid | DIGHTON | 639539 | 02715 | 3.8 | Solar | 05_14_21L3 | 09/11/2024 | 10/22/2024 | 26 | 23 | 3 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/11/2024 | 11/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 375312 | 01534 | 8.376 | Solar | 05_14_55L1 | 08/17/2021 | 08/19/2021 | 2 | 0 | 2 | 08/20/2021 | 08/20/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  | 10/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2022 | Connected |  | N
National Grid | ROCKPORT | 270545 | 01966 | 0 | Solar | 05_14_65L3 | 12/20/2019 | 12/30/2019 | 4 | 0 | 4 | 12/31/2019 | 12/31/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2020 | 12/20/2019 | 12/20/2020 | Y | EXP | 365 | 03/10/2020 | 04/02/2020 | 23 | 0 | 23 |  |  | 9/14/2020 | Connected |  | N
National Grid | LOWELL | 356821 | 01854 | 7.6 | Solar | 05_14_78L1 | 06/03/2021 | 01/07/2022 | 2 | 0 | 2 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2021 | 06/03/2021 | 3/8/2023 | Y | EXP | 365 | 01/26/2022 | 03/07/2022 | 41 | 0 | 41 |  |  | 8/11/2022 | Connected |  | Y
National Grid | ANDOVER | 213711 | 01845 | 8.64 | Solar | 05_01_226L1 | 03/19/2019 | 03/29/2019 | 8 | 8 | 0 | 04/01/2019 | 04/01/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2019 |  | 5/30/2019 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | HAVERHILL | 175877 | 01830 | 2000 | Solar | 05_01_406L1 | 03/06/2015 | 03/06/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2015 | 04/16/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 | 01/22/2016 | 05/17/2016 | 79 | 0 | 79 | 5/17/2016 | 03/06/2015 | 12/31/2017 | Y | STD | 593 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 12/31/2017 | 12/31/2017 | 12/31/2017 | Connected |  | N
National Grid | DRACUT | 754489 | 01826 | 3.8 | Solar | 05_01_525L2 | 03/04/2026 | 03/06/2026 | 2 | 0 | 2 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PEPPERELL | 662745 | 01463 | 10 | Solar | 05_01_7J386 | 12/27/2024 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 141 | 117 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 232600 | 01540 | 15.2 | Solar | 05_05_19W74 | 05/31/2019 | 06/12/2019 | 7 | 0 | 7 | 06/13/2019 | 06/13/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 6/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2020 | Connected |  | N
National Grid | BROOKFIELD | 728545 | 01506 | 0 | Battery Add-On | 05_05_320W1 | 10/23/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 | 10/23/2025 | 12/9/2026 | Y | EXP | 365 | 01/08/2026 | 02/04/2026 | 28 | 0 | 28 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 713056 | 01603 | 9.772 | Solar | 05_12_40J2 | 10/06/2025 | 10/08/2025 | 2 | 0 | 2 | 10/09/2025 | 10/09/2025 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 |  | 11/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2025 | Connected |  | N
National Grid | DIGHTON | 646886 | 02779 | 5.76 | Solar | 05_14_21L3 | 10/14/2024 | 12/18/2024 | 37 | 34 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITINSVILLE | 379389 | 01588 | 9.57 | Solar | 05_14_55L1 | 09/02/2021 |  | 23 | 23 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 330625 | 01966 | 15.2 | Solar | 05_14_65L3 | 12/09/2020 | 12/18/2020 | 6 | 0 | 6 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 359517 | 01826 | 15.12 | Solar | 05_14_78L1 | 05/20/2021 | 07/22/2021 | 42 | 35 | 7 | 07/23/2021 | 07/23/2021 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 272824 | 01845 | 3.8 | Solar | 05_01_226L1 | 02/21/2020 | 04/30/2020 | 50 | 49 | 1 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 4/29/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 175875 | 01835 | 2000 | Solar | 05_01_406L1 | 03/06/2015 | 03/06/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2015 | 04/16/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 | 01/22/2016 | 05/17/2016 | 79 | 0 | 79 | 5/17/2016 | 03/06/2015 | 12/31/2017 | Y | STD | 593 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 12/31/2017 | 12/31/2017 | 12/31/2017 | Connected |  | N
National Grid | DRACUT | 174181 | 01826 | 800 | Solar | 05_01_525L2 | 10/14/2011 | 10/14/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2013 | 10/14/2011 | 3/1/2014 | Y | STD | 325 |  |  | 0 | 0 | 0 | 6/3/2015 | 6/3/2015 | 6/19/2015 | Connected |  | N
National Grid | PEPPERELL | 716720 | 01463 | 7.6 | Solar | 05_01_7J386 | 09/04/2025 | 09/22/2025 | 5 | 0 | 5 | 10/02/2025 | 10/02/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 09/04/2025 | 11/21/2026 | Y | EXP | 365 | 01/13/2026 | 02/10/2026 | 29 | 0 | 29 |  |  | 3/12/2026 | Connected |  | Y
National Grid | LEICESTER | 383763 | 01524 | 233.3 | Solar | 05_05_19W74 | 09/27/2021 | 10/12/2021 | 10 | 2 | 8 |  |  | 36 | 4 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2023 |  | 5/4/2024 | N | STD | 203 |  |  | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | WEST BROOKFIELD | 733037 | 01585 | 15.2 | Solar | 05_05_320W1 | 11/11/2025 | 11/19/2025 | 5 | 2 | 3 | 11/20/2025 | 11/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 556928 | 01603 | 6 | Solar | 05_12_40J4 | 10/27/2023 | 10/30/2023 | 1 | 0 | 1 | 10/31/2023 | 10/31/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 | 10/27/2023 | 12/7/2024 | Y | EXP | 365 | 03/30/2024 | 06/18/2024 | 81 | 0 | 81 |  |  | 7/11/2024 | Connected |  | N
National Grid | DIGHTON | 655534 | 02764 | 3.8 | Solar | 05_14_21L3 | 11/19/2024 | 12/16/2024 | 6 | 0 | 6 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | UPTON | 387061 | 01568 | 9.57 | Solar | 05_14_55L1 | 10/07/2021 | 10/14/2021 | 4 | 4 | 0 | 10/15/2021 | 10/15/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 |  | 11/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2022 | Connected |  | N
National Grid | ROCKPORT | 487600 | 01966 | 7.54 | Solar | 05_14_65L3 | 02/15/2023 | 02/16/2023 | 1 | 0 | 1 | 02/17/2023 | 02/17/2023 | 184 | 162 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 377505 | 01854 | 4.93 | Solar | 05_14_78L1 | 09/13/2021 | 01/07/2022 | 2 | 0 | 2 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2021 | 09/13/2021 |  | Y | EXP | 365 | 02/22/2022 | 03/10/2022 | 16 | 0 | 16 |  |  | 3/29/2022 | Connected |  | N
National Grid | ANDOVER | 287295 | 01845 | 200 | Solar | 05_01_226L1 | 04/17/2020 | 05/29/2020 | 27 | 21 | 6 | 06/01/2020 | 06/01/2020 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2020 |  | 9/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2021 | Connected |  | N
National Grid | HAVERHILL | 175878 | 01835 | 1000 | Solar | 05_01_406L1 | 03/06/2015 | 03/06/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2015 | 04/16/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 | 01/22/2016 | 05/17/2016 | 79 | 0 | 79 | 5/17/2016 | 03/06/2015 | 12/31/2017 | Y | STD | 593 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 12/31/2017 | 12/31/2017 | 12/31/2017 | Connected |  | N
National Grid | DRACUT | 174180 | 01826 | 1400 | Solar | 05_01_525L2 | 10/17/2011 | 10/17/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2014 | 10/17/2011 | 12/31/2016 | Y | STD | 1023 |  |  | 0 | 0 | 0 | 1/28/2016 | 1/28/2016 | 1/29/2016 | Connected |  | N
National Grid | PEPPERELL | 715579 | 01463 | 10 | Solar | 05_01_7J387 | 08/29/2025 | 10/08/2025 | 14 | 11 | 3 | 11/06/2025 | 11/06/2025 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEICESTER | 390978 | 01524 | 150 | Solar | 05_05_19W74 | 10/29/2021 | 11/11/2021 | 8 | 0 | 8 |  |  | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2023 | 10/29/2021 | 5/2/2024 | Y | STD | 203 | 11/30/2023 | 01/22/2024 | 54 | 0 | 54 |  |  | 4/30/2024 | Connected |  | N
National Grid | WEST BROOKFIELD | 174792 | 01585 | 225 | Solar | 05_05_320W1 | 06/20/2011 | 06/20/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2011 |  | 3/16/2012 | N | EXP | 185 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 3/16/2012 | Connected |  | N
National Grid | WORCESTER | 681602 | 01603 | 50 | Solar | 05_12_40L1 | 05/20/2025 | 05/23/2025 | 3 | 0 | 3 | 05/27/2025 | 05/27/2025 | 35 | 10 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DIGHTON | 666729 | 02715 | 7.6 | Solar | 05_14_21L3 | 01/20/2025 | 01/31/2025 | 4 | 0 | 4 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/20/2025 | 4/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 393293 | 01534 | 6.38 | Solar | 05_14_55L1 | 12/17/2021 | 01/06/2022 | 13 | 12 | 1 | 01/07/2022 | 01/07/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2022 |  | 3/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2022 | Connected |  | N
National Grid | ROCKPORT | 586417 | 01966 | 0 | Battery Add-On | 05_14_65L3 | 01/30/2024 | 02/15/2024 | 12 | 9 | 3 | 02/16/2024 | 02/16/2024 | 14 | 9 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2024 | Connected |  | N
National Grid | LOWELL | 402327 | 01854 | 15.2 | Solar | 05_14_78L1 | 12/20/2021 | 12/23/2021 | 3 | 2 | 1 | 12/24/2021 | 12/24/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 |  | 2/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 314437 | 01845 | 3.8 | Solar | 05_01_226L1 | 10/02/2020 | 10/06/2020 | 1 | 0 | 1 | 10/07/2020 | 10/07/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2021 | Connected |  | N
National Grid | HAVERHILL | 176149 | 01835 | 6 | Solar | 05_01_406L1 | 08/25/2015 | 08/25/2015 | 0 | 0 | 0 | 08/31/2015 | 08/31/2015 | 606 | 0 | 606 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 9/5/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 174550 | 01826 | 39 | Solar | 05_01_525L2 | 07/25/2012 | 07/25/2012 | 7 | 0 | 7 | 08/06/2012 | 08/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 07/25/2012 | 10/31/2012 | Y | EXP | 42 | 03/29/2013 | 03/29/2013 | 0 | 0 | 0 | 3/29/2013 | 3/29/2013 | 4/16/2013 | Connected |  | N
National Grid | PEPPERELL | 721057 | 01463 | 1.45 | Solar | 05_01_7J387 | 09/23/2025 | 10/02/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEICESTER | 393641 | 01524 | 10 | Solar | 05_05_19W74 | 12/06/2021 | 12/07/2021 | 1 | 0 | 1 | 12/08/2021 | 12/08/2021 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2022 |  | 1/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2022 | Connected |  | N
National Grid | WEST BROOKFIELD | 174791 | 01585 | 120 | Solar | 05_05_320W1 | 06/20/2011 | 06/20/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2011 |  | 3/12/2012 | N | EXP | 181 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 3/12/2012 | Connected |  | N
National Grid | WORCESTER | 366436 | 01603 | 6.96 | Solar | 05_12_40L1 | 06/28/2021 | 06/30/2021 | 2 | 0 | 2 | 07/01/2021 | 07/01/2021 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/28/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 649096 | 02715 | 11.5 | Solar | 05_14_24L1 | 10/24/2024 | 12/11/2024 | 4 | 1 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 10/24/2024 | 3/2/2026 | Y | EXP | 395 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WHITINSVILLE | 479560 | 01588 | 15.2 | Solar | 05_14_55L1 | 11/22/2022 | 11/29/2022 | 4 | 0 | 4 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2023 |  | 1/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2023 | Connected |  | N
National Grid | ROCKPORT | 655978 | 01966 | 3.8 | Solar | 05_14_65L3 | 11/21/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | LOWELL | 425044 | 01854 | 10 | Solar | 05_14_78L1 | 05/09/2022 | 05/09/2022 | 0 | 0 | 0 | 05/10/2022 | 05/10/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 05/09/2022 | 7/20/2023 | Y | EXP | 365 | 07/16/2022 | 07/18/2022 | 3 | 0 | 3 |  |  | 5/1/2023 | Connected |  | Y
National Grid | ANDOVER | 355070 | 01845 | 20 | Solar | 05_01_226L1 | 04/28/2021 | 12/15/2021 | 0 | 0 | 0 | 05/04/2021 | 05/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 | 04/28/2021 | 12/2/2022 | Y | EXP | 365 | 11/16/2021 | 11/23/2021 | 8 | 0 | 8 |  |  | 12/21/2021 | Connected |  | N
National Grid | HAVERHILL | 176593 | 01835 | 496 | Solar | 05_01_406L1 | 10/09/2015 | 10/12/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 | 06/04/2018 | 20 | 0 | 20 |  | 0 | 0 | 0 | 07/15/2016 | 06/04/2018 | 44 | 5 | 39 | 2/21/2017 | 10/09/2015 | 1/31/2020 | Y | STD | 982 | 03/14/2019 | 12/02/2019 | 263 | 81 | 182 |  |  | 1/14/2020 | Connected |  | N
National Grid | DRACUT | 174597 | 01826 | 300 | Solar | 05_01_525L2 | 10/13/2011 | 10/13/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2011 | 10/13/2011 | 3/28/2012 | Y | EXP | 99 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 3/28/2012 | Connected |  | N
National Grid | PEPPERELL | 189805 | 01463 | 10 | Solar | 05_01_7J387 | 07/02/2018 | 07/02/2018 | 4 | 4 | 0 | 10/25/2018 | 10/25/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 | 07/02/2018 | 12/5/2019 | Y | EXP | 398 | 07/17/2019 | 09/04/2019 | 49 | 0 | 49 |  |  | 10/29/2019 | Connected |  | N
National Grid | CHARLTON | 402596 | 01507 | 2.03 | Solar | 05_05_19W74 | 01/05/2022 | 01/06/2022 | 1 | 0 | 1 | 01/07/2022 | 01/07/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 5/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2022 | Connected |  | N
National Grid | WEST BROOKFIELD | 175581 | 01585 | 13.6 | Solar | 05_05_320W1 | 12/12/2014 | 12/12/2014 | 38 | 38 | 0 | 02/10/2015 | 02/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2015 |  | 4/30/2015 | N | EXP | 78 |  |  | 0 | 0 | 0 | 2/5/2016 | 2/5/2016 | 2/5/2016 | Connected |  | N
National Grid | WORCESTER | 430455 | 01603 | 15.2 | Solar | 05_12_40L1 | 05/19/2022 | 05/20/2022 | 1 | 0 | 1 | 05/23/2022 | 05/23/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 7/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2022 | Connected |  | N
National Grid | DIGHTON | 740250 | 02764 | 5.76 | Solar | 05_14_24L1 | 12/16/2025 | 12/18/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 62 | 47 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WHITINSVILLE | 572292 | 01588 | 480 | Solar | 05_14_55L1 | 12/07/2023 | 02/01/2024 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2024 | 02/20/2024 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 671344 | 01966 | 5.76 | Solar | 05_14_65L3 | 02/11/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | CHELMSFORD | 428394 | 01824 | 5.8 | Solar | 05_14_78L1 | 05/09/2022 | 05/11/2022 | 2 | 0 | 2 | 05/12/2022 | 05/12/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2022 |  | 7/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2022 | Connected |  | N
National Grid | ANDOVER | 388303 | 01845 | 7.6 | Solar | 05_01_226L1 | 05/27/2022 | 06/01/2022 | 2 | 0 | 2 | 06/02/2022 | 06/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2022 |  | 11/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 176688 | 01835 | 6 | Solar | 05_01_406L1 | 02/18/2016 | 02/18/2016 | 2 | 2 | 0 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2016 |  | 2/24/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 12/1/2016 | 12/1/2016 | 12/1/2016 | Connected |  | N
National Grid | DRACUT | 175312 | 01826 | 1414 | Solar | 05_01_525L2 | 06/27/2014 | 06/27/2014 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2014 | 08/07/2014 | 21 | 0 | 21 |  | 0 | 0 | 0 | 08/11/2016 | 08/11/2016 | 0 | 0 | 0 | 3/23/2015 | 06/27/2014 | 2/18/2016 | Y | STD | 332 | 03/31/2016 | 06/08/2016 | 47 | 0 | 47 | 8/23/2016 | 8/23/2016 | 8/23/2016 | Connected |  | N
National Grid | PEPPERELL | 189778 | 01463 | 10 | Solar | 05_01_7J387 | 11/13/2018 | 07/02/2018 | 11 | 7 | 4 | 12/04/2018 | 12/04/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 |  | 11/13/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 425019 | 01507 | 7.68 | Solar | 05_05_19W74 | 06/27/2022 | 06/29/2022 | 2 | 0 | 2 | 06/30/2022 | 06/30/2022 | 290 | 270 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 06/27/2022 | 9/13/2024 | Y | EXP | 365 | 11/28/2023 | 01/16/2024 | 50 | 3 | 47 |  |  | 1/20/2024 | Connected |  | N
National Grid | WEST BROOKFIELD | 175862 | 01585 | 5 | Solar | 05_05_320W1 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/10/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 5/5/2016 | Connected |  | N
National Grid | WORCESTER | 434717 | 01603 | 10 | Solar | 05_12_40L1 | 06/16/2022 | 06/21/2022 | 2 | 0 | 2 | 06/22/2022 | 06/22/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  | 5/15/2024 | N | EXP | 365 | 01/07/2023 | 05/15/2023 | 129 | 0 | 129 |  |  | 5/24/2023 | Connected |  | N
National Grid | DIGHTON | 749125 | 02715 | 11.4 | Solar | 05_14_24L1 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2026 |  | 3/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | UPTON | 575743 | 01568 | 240 | Solar | 05_14_55L1 | 12/08/2023 | 02/01/2024 | 36 | 25 | 11 |  |  | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 673956 | 01966 | 5.76 | Solar | 05_14_65L3 | 02/24/2025 | 03/04/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 02/24/2025 | 4/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | CHELMSFORD | 430404 | 01824 | 6 | Solar | 05_14_78L1 | 05/24/2022 | 06/02/2022 | 7 | 5 | 2 | 06/03/2022 | 06/03/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2022 | 05/24/2022 | 10/13/2023 | Y | EXP | 365 | 09/28/2022 | 10/12/2022 | 15 | 0 | 15 |  |  | 10/24/2022 | Connected |  | N
National Grid | ANDOVER | 471136 | 01845 | 15.2 | Solar | 05_01_226L1 | 11/23/2022 | 11/29/2022 | 3 | 0 | 3 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2022 |  | 1/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2023 | Connected |  | N
National Grid | HAVERHILL | 176885 | 01835 | 11.4 | Solar | 05_01_406L1 | 11/12/2015 | 11/12/2015 | 89 | 89 | 0 | 03/25/2016 | 03/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 11/12/2015 | 11/18/2016 | Y | EXP | 220 | 11/09/2016 | 11/16/2016 | 4 | 0 | 4 | 2/7/2017 | 2/7/2017 | 2/7/2017 | Connected |  | N
National Grid | DRACUT | 175469 | 01826 | 2250 | Solar | 05_01_525L2 | 11/25/2014 | 11/25/2014 | 6 | 3 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2014 | 01/06/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 190326 | 01463 | 10 | Solar | 05_01_7J387 | 07/13/2018 | 08/24/2018 | 27 | 0 | 27 | 08/27/2018 | 08/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 07/13/2018 |  | Y | EXP | 421 | 10/17/2019 | 10/16/2019 | 0 | 0 | 0 |  |  | 11/6/2019 | Connected |  | N
National Grid | CHARLTON | 458078 | 01507 | 13 | Solar | 05_05_19W74 | 09/15/2022 | 09/16/2022 | 1 | 0 | 1 | 09/19/2022 | 09/19/2022 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 175949 | 01585 | 15.2 | Solar | 05_05_320W1 | 03/13/2015 | 03/13/2015 | 7 | 4 | 3 | 03/26/2015 | 03/26/2015 | 468 | 0 | 468 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 7/31/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 4/14/2015 | 4/14/2015 |  | Withdrawn |  | N
National Grid | WORCESTER | 471710 | 01603 | 5.22 | Solar | 05_12_40L1 | 11/14/2022 | 11/22/2022 | 6 | 3 | 3 | 11/23/2022 | 11/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 | 11/14/2022 | 11/15/2024 | Y | EXP | 365 | 05/17/2023 | 11/06/2023 | 174 | 0 | 174 |  |  | 12/6/2023 | Connected |  | Y
National Grid | DIGHTON | 175186 | 02764 | 335 | Solar | 05_14_24L1 | 11/18/2013 | 11/18/2013 | 1 | 0 | 1 | 11/20/2013 | 11/20/2013 | 494 | 0 | 494 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2013 |  | 4/30/2014 | N | EXP | 155 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 640040 | 01568 | 23.8 | Solar | 05_14_55L1 | 09/13/2024 | 09/17/2024 | 3 | 1 | 2 | 09/18/2024 | 09/18/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2024 |  | 10/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | ROCKPORT | 691483 | 01966 | 17.11 | Solar | 05_14_65L3 | 05/13/2025 | 05/16/2025 | 3 | 0 | 3 | 05/19/2025 | 05/19/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 05/13/2025 | 6/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | CHELMSFORD | 499858 | 01824 | 10 | Solar | 05_14_78L1 | 02/16/2023 | 02/23/2023 | 4 | 3 | 1 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 3/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2023 | Connected |  | N
National Grid | ANDOVER | 477267 | 01845 | 17.45 | Solar | 05_01_226L1 | 01/17/2023 | 01/18/2023 | 1 | 0 | 1 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 2/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2023 | Connected |  | N
National Grid | HAVERHILL | 177091 | 01835 | 7.6 | Solar | 05_01_406L1 | 01/18/2017 | 01/18/2017 | 4 | 3 | 1 | 01/25/2017 | 01/25/2017 | 139 | 0 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2017 |  | 1/24/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 175494 | 01826 | 480 | Solar | 05_01_525L2 | 07/23/2014 | 07/23/2014 | 7 | 0 | 7 | 08/05/2014 | 08/05/2014 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2014 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 196395 | 01463 | 100 | Solar | 05_01_7J387 | 09/19/2018 | 10/01/2018 | 3 | 0 | 3 | 10/02/2018 | 10/02/2018 | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 532519 | 01507 | 11.4 | Solar | 05_05_19W74 | 06/13/2023 | 06/26/2023 | 8 | 5 | 3 | 06/27/2023 | 06/27/2023 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 8/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2023 | Connected |  | N
National Grid | WEST BROOKFIELD | 176133 | 01585 | 10 | Solar | 05_05_320W1 | 04/15/2015 | 04/15/2015 | 1 | 1 | 0 | 04/17/2015 | 04/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 | 04/15/2015 | 12/31/2016 | Y | EXP | 614 | 02/19/2016 | 02/29/2016 | 6 | 0 | 6 | 4/27/2015 | 4/27/2015 | 8/8/2016 | Connected |  | N
National Grid | WORCESTER | 522876 | 01603 | 10 | Solar | 05_12_40L1 | 05/08/2023 | 05/09/2023 | 1 | 0 | 1 | 05/10/2023 | 05/10/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 | 05/08/2023 | 6/20/2024 | Y | EXP | 365 | 08/19/2023 | 10/18/2023 | 61 | 0 | 61 |  |  | 10/23/2023 | Connected |  | N
National Grid | DIGHTON | 175755 | 02715 | 325 | Solar | 05_14_24L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 108 | 03/10/2015 | 04/24/2015 | 31 | 0 | 31 | 5/22/2015 | 5/22/2015 | 5/26/2015 | Connected |  | N
National Grid | NORTHBRIDGE | 650727 | 01534 | 23 | Solar | 05_14_55L1 | 10/31/2024 | 11/12/2024 | 8 | 6 | 2 | 11/13/2024 | 11/13/2024 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 10/31/2024 | 4/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2026 | Connected |  | N
National Grid | ROCKPORT | 715617 | 01966 | 17.6 | Solar | 05_14_65L3 | 09/08/2025 | 09/10/2025 | 2 | 0 | 2 | 09/11/2025 | 09/11/2025 | 56 | 43 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 521189 | 01824 | 7.6 | Solar | 05_14_78L1 | 05/02/2023 | 05/03/2023 | 1 | 0 | 1 | 05/04/2023 | 05/04/2023 | 51 | 28 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 |  | 7/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2023 | Connected |  | N
National Grid | ANDOVER | 491024 | 01845 | 10 | Solar | 05_01_226L1 | 03/14/2023 | 03/20/2023 | 4 | 0 | 4 | 03/21/2023 | 03/21/2023 | 55 | 39 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 177213 | 01835 | 1000 | Solar | 05_01_406L1 | 06/08/2016 | 06/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2016 | 07/26/2016 | 31 | 14 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/14/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 175792 | 01826 | 1000 | Solar | 05_01_525L2 | 09/16/2015 | 09/16/2015 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 11/23/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 | 09/16/2015 | 9/23/2016 | Y | STD | 148 | 08/22/2017 | 11/14/2017 | 52 | 0 | 52 | 11/17/2017 | 11/17/2017 | 11/17/2017 | Connected |  | N
National Grid | PEPPERELL | 198809 | 01463 | 7.6 | Solar | 05_01_7J387 | 10/17/2018 | 11/08/2018 | 5 | 0 | 5 | 11/09/2018 | 11/09/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 541084 | 01507 | 10 | Solar | 05_05_19W74 | 07/18/2023 | 07/19/2023 | 1 | 0 | 1 | 07/20/2023 | 07/20/2023 | 58 | 37 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 | 07/18/2023 | 10/18/2024 | Y | EXP | 365 | 10/25/2023 | 01/22/2024 | 90 | 3 | 87 |  |  | 1/25/2024 | Connected |  | N
National Grid | BROOKFIELD | 176293 | 01515 | 7.6 | Solar | 05_05_320W1 | 07/10/2015 | 07/10/2015 | 15 | 15 | 0 | 08/03/2015 | 08/03/2015 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/18/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 559826 | 01603 |  | Solar | 05_12_40L1 | 10/18/2023 | 10/20/2023 | 3 | 1 | 2 | 10/23/2023 | 10/23/2023 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2024 | Connected |  | N
National Grid | DIGHTON | 176456 | 02764 | 7.6 | Solar | 05_14_24L1 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2016 |  | 12/14/2016 | N | EXP | 342 |  |  | 0 | 0 | 0 | 6/10/2016 | 6/10/2016 | 6/16/2016 | Connected |  | N
National Grid | NORTHBRIDGE | 654018 | 01534 | 17.6 | Solar | 05_14_55L1 | 11/20/2024 | 12/02/2024 | 6 | 2 | 4 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | ROCKPORT | 727455 | 01966 | 5.76 | Solar | 05_14_65L3 | 10/17/2025 | 10/24/2025 | 3 | 0 | 3 | 11/26/2025 | 11/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | CHELMSFORD | 559780 | 01824 | 8.505 | Solar | 05_14_78L1 | 11/13/2023 | 11/28/2023 | 10 | 6 | 4 | 11/29/2023 | 11/29/2023 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2024 | 11/13/2023 | 2/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2024 | Connected |  | N
National Grid | ANDOVER | 493769 | 01845 | 24.94 | Solar | 05_01_226L1 | 01/20/2023 | 01/23/2023 | 2 | 1 | 1 | 01/24/2023 | 01/24/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 3/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | HAVERHILL | 177278 | 01835 | 1980 | Solar | 05_01_406L1 | 02/08/2017 | 03/27/2017 | 30 | 28 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/24/2017 | 05/04/2017 | 28 | 14 | 14 |  | 0 | 0 | 0 | 01/13/2018 | 02/14/2020 | 523 | 0 | 523 | 10/20/2017 | 02/08/2017 | 1/31/2020 | Y | STD | 741 | 05/03/2019 | 01/22/2020 | 263 | 0 | 263 |  |  | 1/22/2020 | Connected |  | N
National Grid | DRACUT | 175791 | 01826 | 1000 | Solar | 05_01_525L2 | 09/16/2015 | 09/16/2015 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 11/23/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 |  | 9/23/2016 | N | STD | 148 | 08/22/2017 | 11/14/2017 | 52 | 0 | 52 | 11/17/2017 | 11/17/2017 | 11/17/2017 | Connected |  | N
National Grid | PEPPERELL | 224318 | 01463 | 7.6 | Solar | 05_01_7J387 | 05/09/2019 | 05/15/2019 | 4 | 4 | 0 | 05/16/2019 | 05/16/2019 | 14 | 3 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2019 | 05/09/2019 | 2/28/2020 | Y | EXP | 268 | 08/31/2019 | 09/13/2019 | 13 | 0 | 13 |  |  | 11/7/2019 | Connected |  | N
National Grid | CHARLTON | 543936 | 01507 | 7.68 | Solar | 05_05_19W74 | 07/28/2023 |  | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 176431 | 01535 | 6 | Solar | 05_05_320W1 | 03/11/2016 | 03/11/2016 | 3 | 3 | 0 | 03/17/2016 | 03/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 |  | 3/19/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 10/28/2016 | 10/28/2016 | 11/1/2016 | Connected |  | N
National Grid | WORCESTER | 608732 | 01603 | 3.8 | Solar | 05_12_40L1 | 05/03/2024 | 05/20/2024 | 4 | 0 | 4 | 05/21/2024 | 05/21/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 05/03/2024 | 7/9/2025 | Y | EXP | 365 | 08/15/2024 | 11/06/2024 | 83 | 0 | 83 |  |  | 11/20/2024 | Connected |  | N
National Grid | SOMERSET | 176621 | 02726 | 7.6 | Solar | 05_14_24L1 | 04/12/2016 | 04/12/2016 | 1 | 1 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/12/2016 | 4/18/2017 | Y | EXP | 357 | 08/16/2016 | 08/31/2016 | 11 | 0 | 11 | 3/1/2017 | 3/1/2017 | 3/1/2017 | Connected |  | N
National Grid | NORTHBRIDGE | 657089 | 01534 | 10 | Solar | 05_14_55L1 | 11/26/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 757450 | 01966 |  | Battery Add-On | 05_14_66L1 | 03/18/2026 | 03/27/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | CHELMSFORD | 531489 | 01824 | 15.2 | Solar | 05_14_78L1 | 06/05/2023 | 06/06/2023 | 1 | 0 | 1 | 06/07/2023 | 06/07/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  | 8/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 532028 | 01845 | 10 | Solar | 05_01_226L1 | 07/07/2023 | 07/11/2023 | 2 | 0 | 2 | 07/12/2023 | 07/12/2023 | 22 | 0 | 22 | 10/02/2023 | 11/01/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 11/01/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 10/30/2023 |  | 12/11/2024 | N | EXP | 365 | 12/22/2023 | 01/24/2024 | 34 | 0 | 34 |  |  | 2/1/2024 | Connected |  | Y
National Grid | HAVERHILL | 177409 | 01835 | 1980 | Solar | 05_01_406L1 | 09/11/2016 | 10/13/2016 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2016 | 11/01/2016 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2017 | 09/11/2016 | 12/31/2020 | Y | STD | 365 | 09/29/2020 | 12/02/2020 | 64 | 0 | 64 |  |  | 12/21/2020 | Connected |  | N
National Grid | DRACUT | 176288 | 01826 | 17.4 | Solar | 05_01_525L2 | 07/10/2015 | 07/10/2015 | 1 | 1 | 0 | 07/14/2015 | 07/14/2015 | 394 | 0 | 394 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2015 |  | 7/18/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 256144 | 01463 | 10 | Solar | 05_01_7J387 | 11/07/2019 | 11/07/2019 | 0 | 0 | 0 | 11/08/2019 | 11/08/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 | 11/07/2019 | 7/8/2020 | Y | EXP | 365 | 02/14/2020 | 03/03/2020 | 18 | 0 | 18 |  |  | 5/5/2020 | Connected |  | N
National Grid | CHARLTON | 565988 | 01507 | 10 | Solar | 05_05_19W74 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 57 | 26 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 176467 | 01535 | 27 | Solar | 05_05_320W1 | 02/05/2016 | 02/05/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2016 |  | 2/13/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 11/18/2016 | 11/18/2016 | 12/5/2016 | Connected |  | N
National Grid | WORCESTER | 640630 | 01603 | 6.09 | Solar | 05_12_40L1 | 09/16/2024 | 11/15/2024 | 30 | 26 | 4 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 176675 | 02764 | 10 | Solar | 05_14_24L1 | 01/04/2016 | 01/04/2016 | 1 | 1 | 0 | 01/06/2016 | 01/06/2016 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 |  | 1/10/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 674728 | 01568 | 19 | Solar | 05_14_55L1 | 02/28/2025 | 03/05/2025 | 3 | 0 | 3 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | ROCKPORT | 174723 | 01966 | 35 | Solar | 05_14_66L1 | 07/29/2010 | 07/29/2010 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/29/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 | 3/13/2017 | 3/13/2017 |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 569358 | 01824 | 6.09 | Solar | 05_14_78L1 | 11/14/2023 | 11/20/2023 | 4 | 1 | 3 | 11/21/2023 | 11/21/2023 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 | 11/14/2023 | 1/1/2025 | Y | EXP | 365 | 05/30/2024 | 07/15/2024 | 47 | 0 | 47 |  |  | 7/26/2024 | Connected |  | N
National Grid | ANDOVER | 577018 | 01845 | 6.67 | Solar | 05_01_226L1 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 177477 | 01913 | 20 | Solar | 05_01_406L1 | 07/06/2016 | 07/06/2016 | 1 | 1 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2016 | 07/06/2016 | 8/31/2017 | Y | EXP | 398 | 06/03/2017 | 08/25/2017 | 58 | 0 | 58 | 8/23/2017 | 8/23/2017 | 8/22/2017 | Connected |  | N
National Grid | DRACUT | 176669 | 01826 | 499 | Solar | 05_01_525L2 | 10/20/2015 | 10/20/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 11/23/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 |  | 10/26/2016 | N | STD | 181 | 08/22/2017 | 11/14/2017 | 52 | 0 | 52 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 273828 | 01463 | 7.6 | Solar | 05_01_7J387 | 01/23/2020 | 02/18/2020 | 16 | 14 | 2 | 02/19/2020 | 02/19/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2020 | 01/23/2020 | 8/12/2021 | Y | EXP | 365 | 02/03/2021 | 03/15/2021 | 40 | 0 | 40 |  |  | 4/7/2021 | Connected |  | N
National Grid | CHARLTON | 611840 | 01507 | 3 | Solar | 05_05_19W74 | 05/31/2024 | 06/21/2024 | 7 | 6 | 1 | 06/24/2024 | 06/24/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 |  | 7/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2024 | Connected |  | N
National Grid | WEST BROOKFIELD | 176739 | 01585 | 3 | Solar | 05_05_320W1 | 10/29/2015 | 10/29/2015 | 2 | 2 | 0 | 11/04/2015 | 11/04/2015 | 275 | 0 | 275 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2015 |  | 11/7/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 11/17/2015 | 11/17/2015 |  | Withdrawn |  | N
National Grid | WORCESTER | 663214 | 01603 | 4.55 | Solar | 05_12_40L1 | 12/31/2024 | 01/16/2025 | 6 | 0 | 6 | 01/17/2025 | 01/17/2025 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | DIGHTON | 177455 | 02715 | 10 | Solar | 05_14_24L1 | 12/06/2016 | 12/06/2016 | 2 | 2 | 0 | 12/09/2016 | 12/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 12/06/2016 | 12/12/2017 | Y | EXP | 362 | 10/03/2017 | 10/17/2017 | 9 | 0 | 9 | 10/17/2017 | 10/17/2017 | 10/17/2017 | Connected |  | N
National Grid | WHITINSVILLE | 690737 | 01588 | 7.6 | Solar | 05_14_55L1 | 05/09/2025 | 05/22/2025 | 5 | 0 | 5 | 06/11/2025 | 06/11/2025 | 44 | 28 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2025 | Connected |  | N
National Grid | ROCKPORT | 178684 | 01966 | 20 | Solar | 05_14_66L1 | 12/18/2017 | 12/18/2017 | 17 | 17 | 0 | 02/01/2018 | 02/01/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2018 |  | 12/24/2018 | N | EXP | 326 |  |  | 0 | 0 | 0 |  |  | 5/1/2018 | Connected |  | N
National Grid | CHELMSFORD | 613831 | 01824 | 7.6 | Solar | 05_14_78L1 | 05/28/2024 | 06/05/2024 | 0 | 0 | 0 | 06/06/2024 | 06/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | ANDOVER | 586042 | 01845 | 8.41 | Solar | 05_01_226L1 | 02/09/2024 | 02/13/2024 | 2 | 0 | 2 | 02/14/2024 | 02/14/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/09/2024 | 3/1/2025 | Y | EXP | 365 | 04/16/2024 | 06/05/2024 | 51 | 0 | 51 |  |  | 6/13/2024 | Connected |  | N
National Grid | AMESBURY | 177508 | 01913 | 99.9 | Solar | 05_01_406L1 | 07/08/2016 | 07/08/2016 | 0 | 0 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2017 |  | 8/31/2017 | N | EXP | 160 |  |  | 0 | 0 | 0 | 8/3/2017 | 8/3/2017 | 8/3/2017 | Connected |  | N
National Grid | DRACUT | 176811 | 01826 | 2000 | Solar | 05_01_525L2 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2015 | 12/08/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 427946 | 01463 | 11.4 | Solar | 05_01_7J387 | 05/03/2022 | 05/03/2022 | 0 | 0 | 0 | 05/04/2022 | 05/04/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  | 7/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2022 | Connected |  | N
National Grid | OXFORD | 614244 | 01537 | 11.4 | Solar | 05_05_19W74 | 05/30/2024 | 06/11/2024 | 9 | 7 | 2 | 06/12/2024 | 06/12/2024 | 14 | 5 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2024 | 05/30/2024 | 8/5/2025 | Y | EXP | 365 | 08/29/2024 | 09/24/2024 | 27 | 0 | 27 |  |  | 9/25/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 176840 | 01535 | 7 | Solar | 05_05_320W1 | 05/02/2016 | 05/02/2016 | 5 | 5 | 0 | 05/09/2016 | 05/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2016 | 05/02/2016 | 5/7/2017 | Y | EXP | 347 | 08/01/2016 | 10/19/2016 | 55 | 0 | 55 | 10/26/2016 | 10/26/2016 | 10/26/2016 | Connected |  | N
National Grid | WORCESTER | 688401 | 01603 | 4.537 | Solar | 05_12_40L1 | 07/09/2025 | 07/25/2025 | 2 | 0 | 2 | 08/07/2025 | 08/07/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | DIGHTON | 177491 | 02715 | 330 | Solar | 05_14_24L1 | 12/12/2016 | 12/12/2016 | 3 | 3 | 0 | 01/27/2017 | 01/27/2017 | 0 | 0 | 0 | 03/21/2017 | 04/19/2017 | 36 | 36 | 0 |  |  | 0 | 0 | 0 | 04/19/2017 | 36 | 36 | 0 |  |  | 0 | 0 | 0 | 7/6/2017 |  | 3/20/2019 | N | EXP | 622 |  |  | 0 | 0 | 0 |  |  | 1/31/2019 | Connected |  | N
National Grid | UPTON | 725323 | 01568 | 15.2 | Solar | 05_14_55L1 | 10/09/2025 | 10/17/2025 | 5 | 0 | 5 | 10/20/2025 | 10/20/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 12/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2026 | Connected |  | N
National Grid | ROCKPORT | 688941 | 01966 | 12.92 | Solar | 05_14_66L1 | 05/08/2025 | 05/23/2025 | 4 | 0 | 4 | 05/27/2025 | 05/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | CHELMSFORD | 619601 | 01824 | 10 | Solar | 05_14_78L1 | 06/21/2024 | 07/18/2024 | 8 | 6 | 2 | 07/19/2024 | 07/19/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 | 06/21/2024 | 9/18/2025 | Y | EXP | 365 | 02/28/2025 | 04/21/2025 | 53 | 0 | 53 |  |  | 5/2/2025 | Connected |  | N
National Grid | ANDOVER | 623421 | 01845 | 2100 | Solar | 05_01_226L1 | 07/11/2024 |  | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 177726 | 01913 | 7.6 | Solar | 05_01_406L1 | 10/04/2017 | 10/04/2017 | 9 | 8 | 1 | 10/19/2017 | 10/19/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/10/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 177650 | 01826 | 500 | Solar | 05_01_525L2 | 09/27/2017 | 09/27/2017 | 63 | 58 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2018 | 02/01/2018 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/4/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 496344 | 01463 | 9.86 | Solar | 05_01_7J387 | 02/08/2023 | 02/09/2023 | 1 | 0 | 1 | 02/10/2023 | 02/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2023 | 02/08/2023 | 7/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2023 | Connected |  | N
National Grid | CHARLTON | 616349 | 01507 | 7.6 | Solar | 05_05_19W74 | 06/07/2024 | 08/13/2024 | 5 | 0 | 5 | 08/14/2024 | 08/14/2024 | 13 | 6 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 | 06/07/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 177348 | 01535 | 7.6 | Solar | 05_05_320W1 | 11/23/2016 | 11/23/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2016 |  | 11/28/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 644663 | 01603 | 10 | Solar | 05_12_49W2 | 10/03/2024 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DIGHTON | 177929 | 02715 | 396 | Solar | 05_14_24L1 | 04/19/2017 | 04/19/2017 | 9 | 8 | 1 | 05/02/2017 | 05/02/2017 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2017 | 04/19/2017 | 2/11/2019 | Y | EXP | 607 |  |  | 0 | 0 | 0 |  |  | 2/11/2019 | Connected |  | N
National Grid | UPTON | 198828 | 01568 | 10 | Solar | 05_14_55L2 | 10/19/2018 | 10/31/2018 | 3 | 3 | 0 | 11/01/2018 | 11/01/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 |  | 7/1/2019 | N | EXP | 230 |  |  | 0 | 0 | 0 |  |  | 6/19/2019 | Connected |  | N
National Grid | ROCKPORT | 722850 | 01966 | 16.403 | Solar | 05_14_66L2 | 10/03/2025 | 10/13/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 |  | 2/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHELMSFORD | 625470 | 01824 | 6 | Solar | 05_14_78L1 | 07/17/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 648781 | 01845 | 10 | Solar | 05_01_226L1 | 10/22/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/22/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | AMESBURY | 177741 | 01913 | 1740 | Solar | 05_01_406L1 | 05/30/2017 | 11/01/2017 | 105 | 100 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/01/2017 | 12/06/2017 | 20 | 9 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 177789 | 01826 | 4500 | Solar | 05_01_525L2 | 06/05/2017 | 06/12/2017 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2017 | 07/05/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2018 | 06/05/2017 | 7/15/2020 | Y | STD | 632 | 06/28/2019 | 06/01/2020 | 339 | 0 | 339 |  |  | 7/14/2020 | Connected |  | N
National Grid | PEPPERELL | 567253 | 01463 | 6 | Solar | 05_01_7J387 | 11/15/2023 | 11/17/2023 | 2 | 0 | 2 | 11/20/2023 | 11/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  | 12/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2024 | Connected |  | N
National Grid | CHARLTON | 628852 | 01507 | 5 | Solar | 05_05_19W74 | 07/30/2024 | 08/13/2024 | 4 | 3 | 1 | 08/14/2024 | 08/14/2024 | 29 | 20 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  | 10/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | BROOKFIELD | 177890 | 01506 | 15.2 | Solar | 05_05_320W1 | 04/12/2017 | 04/12/2017 | 4 | 3 | 1 | 04/20/2017 | 04/20/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2017 |  | 4/18/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/29/2017 | 8/29/2017 | 9/5/2017 | Connected |  | N
National Grid | WORCESTER | 674332 | 01603 | 450 | Solar | 05_12_49W2 | 06/10/2025 | 09/11/2025 | 63 | 54 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/12/2025 | 12/03/2025 | 56 | 37 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SOMERSET | 184582 | 02726 | 233.1 | Solar | 05_14_24L1 | 04/30/2018 | 04/30/2018 | 0 | 0 | 0 | 05/31/2018 | 05/31/2018 | 339 | 66 | 273 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 348152 | 01568 | 7.25 | Solar | 05_14_55L2 | 03/22/2021 | 03/25/2021 | 3 | 3 | 0 | 03/26/2021 | 03/26/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2021 |  | 3/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2021 | Connected |  | N
National Grid | SALEM | 193104 | 01970 | 455 | Solar | 05_14_66L2 | 08/23/2018 | 08/28/2018 | 2 | 0 | 2 |  |  | 101 | 22 | 79 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 635771 | 01824 | 5.76 | Solar | 05_14_78L1 | 08/27/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 08/27/2024 | 9/24/2025 | Y | EXP | 365 | 01/22/2025 | 01/21/2025 | 0 | 0 | 0 |  |  | 1/24/2025 | Connected |  | Y
National Grid | ANDOVER | 653619 | 01845 | 8.125 | Solar | 05_01_226L1 | 11/12/2024 | 11/19/2024 | 2 | 0 | 2 | 11/20/2024 | 11/20/2024 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | AMESBURY | 177847 | 01913 | 900 | Solar | 05_01_406L1 | 10/17/2017 | 11/15/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 | 12/11/2017 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/17/2017 | 10/1/2019 | Y | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 178421 | 01826 | 3375 | Solar | 05_01_525L2 | 01/17/2018 | 02/01/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2018 | 02/26/2018 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 | 01/17/2018 | 4/16/2022 | Y | STD | 439 | 03/14/2021 | 12/02/2021 | 264 | 7 | 257 | 12/3/2021 | 12/16/2021 | 12/27/2021 | Connected |  | N
National Grid | PEPPERELL | 586363 | 01463 | 5.76 | Solar | 05_01_7J387 | 02/14/2024 | 02/21/2024 | 4 | 2 | 2 | 02/22/2024 | 02/22/2024 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/14/2024 | 4/17/2025 | Y | EXP | 365 | 07/10/2024 | 11/07/2024 | 121 | 0 | 121 |  |  | 10/28/2024 | Connected |  | N
National Grid | LEICESTER | 647648 | 01524 | 3.8 | Solar | 05_05_19W74 | 10/16/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/16/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | WEST BROOKFIELD | 178493 | 01585 | 4980 | Solar | 05_05_320W1 | 12/01/2017 | 12/01/2017 | 45 | 43 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2018 | 03/26/2018 | 25 | 0 | 25 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2018 | 12/01/2017 | 3/31/2021 | Y | STD | 434 | 01/14/2021 | 03/31/2021 | 76 | 0 | 76 |  |  | 3/31/2021 | Connected |  | N
National Grid | WORCESTER | 730129 | 01603 | 60 | Solar | 05_12_49W2 | 11/10/2025 | 12/24/2025 | 30 | 22 | 8 | 12/26/2025 | 12/26/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2026 |  | 3/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 185021 | 02726 | 3.8 | Solar | 05_14_24L1 | 05/10/2018 | 05/10/2018 | 4 | 0 | 4 | 05/17/2018 | 05/17/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 553486 | 01568 | 15.2 | Solar | 05_14_55L2 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  | 12/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2024 | Connected |  | Y
National Grid | SALEM | 520212 | 01970 | 15.08 | Solar | 05_14_6J1 | 04/19/2023 | 04/20/2023 | 1 | 0 | 1 | 04/21/2023 | 04/21/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2023 |  | 7/16/2024 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 643912 | 01824 | 7.6 | Solar | 05_14_78L1 | 10/02/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/02/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | ANDOVER | 684832 | 01845 | 17.6 | Solar | 05_01_226L1 | 04/14/2025 | 04/21/2025 | 4 | 1 | 3 | 04/22/2025 | 04/22/2025 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | AMESBURY | 178172 | 01913 | 7800 | Solar | 05_01_406L1 | 03/23/2018 | 03/23/2018 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2018 | 06/26/2018 | 59 | 43 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 185007 | 01826 | 1000 | Solar | 05_01_525L2 | 05/17/2018 | 05/17/2018 | 32 | 15 | 17 |  |  | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 07/05/2018 | 09/11/2018 | 36 | 5 | 31 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 622055 | 01463 | 3.8 | Solar | 05_01_7J387 | 07/02/2024 | 07/09/2024 | 1 | 0 | 1 | 07/10/2024 | 07/10/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 07/02/2024 | 7/31/2025 | Y | EXP | 365 | 10/04/2024 | 10/17/2024 | 14 | 0 | 14 |  |  | 11/16/2024 | Connected |  | N
National Grid | LEICESTER | 677411 | 01542 | 5.76 | Solar | 05_05_19W74 | 03/12/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 178492 | 01506 | 4980 | Solar | 05_05_320W1 | 12/01/2017 | 12/01/2017 | 45 | 43 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2018 | 03/26/2018 | 25 | 0 | 25 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2018 | 12/01/2017 | 3/31/2021 | Y | STD | 434 | 12/19/2020 | 03/24/2021 | 95 | 0 | 95 |  |  | 3/31/2021 | Connected |  | N
National Grid | WORCESTER | 174825 | 01603 | 164 | Solar | 05_12_49W2 | 07/20/2011 | 07/20/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2011 |  | 4/24/2012 | N | EXP | 207 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 4/24/2012 | Connected |  | N
National Grid | DIGHTON | 243846 | 02764 | 0 | Solar | 05_14_24L1 | 07/24/2019 | 07/30/2019 | 3 | 0 | 3 | 07/31/2019 | 07/31/2019 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 07/24/2019 | 7/24/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2020 | Connected |  | N
National Grid | NORTHBRIDGE | 598369 | 01534 | 14.208 | Solar | 05_14_55L2 | 04/15/2024 | 04/17/2024 | 2 | 1 | 1 | 04/18/2024 | 04/18/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 |  | 5/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2024 | Connected |  | N
National Grid | SALEM | 552102 | 01970 | 150 | Solar | 05_14_6J1 | 09/01/2023 | 09/24/2023 | 15 | 6 | 9 |  |  | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 643820 | 01824 | 7.6 | Solar | 05_14_78L1 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/01/2024 | 12/19/2025 | Y | EXP | 365 | 01/16/2025 | 02/26/2025 | 42 | 0 | 42 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 696444 | 01845 | 9.5 | Solar | 05_01_226L1 | 06/05/2025 | 06/25/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | LAWRENCE | 178255 | 01841 | 1375 | Solar | 05_01_406L1 | 04/16/2018 | 04/16/2018 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/09/2018 | 3 | 0 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/21/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 186901 | 01826 | 4980 | Solar | 05_01_525L2 | 06/01/2018 | 06/01/2018 | 0 | 0 | 0 |  |  | 54 | 43 | 11 |  |  | 0 | 0 | 0 | 08/17/2018 | 08/17/2018 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 628232 | 01463 | 5.76 | Solar | 05_01_7J387 | 07/29/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | N
National Grid | AUBURN | 685887 | 01501 | 15.2 | Solar | 05_05_19W74 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 186263 | 01515 | 17.6 | Solar | 05_05_320W1 | 06/13/2018 | 06/13/2018 | 12 | 6 | 6 | 07/02/2018 | 07/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 7/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2018 | Connected |  | N
National Grid | WORCESTER | 175188 | 01603 | 18 | Solar | 05_12_49W2 | 11/19/2013 | 11/19/2013 | 4 | 0 | 4 | 11/26/2013 | 11/26/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2013 |  | 1/31/2014 | N | EXP | 50 |  |  | 0 | 0 | 0 | 12/17/2013 | 12/17/2013 | 8/1/2014 | Connected |  | N
National Grid | DIGHTON | 255612 | 02715 | 3.8 | Solar | 05_14_24L1 | 09/23/2019 | 09/24/2019 | 0 | 0 | 0 | 09/25/2019 | 09/25/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2019 | 09/23/2019 | 5/19/2020 | Y | EXP | 236 | 01/29/2020 | 02/25/2020 | 27 | 0 | 27 |  |  | 3/31/2020 | Connected |  | N
National Grid | NORTHBRIDGE | 661473 | 01534 | 7.6 | Solar | 05_14_55L2 | 12/18/2024 | 02/21/2025 | 11 | 7 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | SALEM | 635232 | 01970 | 7.6 | Solar | 05_14_6J1 | 08/26/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/26/2024 | 9/30/2025 | Y | EXP | 365 | 06/18/2025 | 06/17/2025 | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | CHELMSFORD | 644842 | 01824 | 5.76 | Solar | 05_14_78L1 | 10/03/2024 | 11/07/2024 | 6 | 0 | 6 | 11/08/2024 | 11/08/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 701906 | 01845 | 10.64 | Solar | 05_01_226L1 | 07/05/2025 | 07/23/2025 | 5 | 2 | 3 | 08/04/2025 | 08/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2025 | 07/05/2025 | 9/23/2026 | Y | EXP | 365 | 01/13/2026 | 03/05/2026 | 52 | 0 | 52 |  |  | 3/20/2026 | Connected |  | N
National Grid | LAWRENCE | 178479 | 01841 | 5000 | Solar | 05_01_406L1 | 04/03/2018 | 04/03/2018 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 190339 | 01826 | 250 | Solar | 05_01_525L2 | 07/10/2018 | 08/20/2018 | 28 | 0 | 28 | 08/21/2018 | 08/21/2018 | 91 | 21 | 70 | 11/20/2018 | 01/03/2019 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 01/03/2019 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 646407 | 01463 | 3.8 | Solar | 05_01_7J387 | 10/16/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 51 | 25 | 26 | 02/07/2025 | 03/14/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 03/14/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 4/10/2025 | 10/16/2024 | 4/11/2026 | Y | EXP | 365 | 05/09/2025 | 09/02/2025 | 117 | 0 | 117 |  |  | 9/4/2025 | Connected |  | N
National Grid | AUBURN | 688155 | 01501 | 15.58 | Solar | 05_05_19W74 | 04/28/2025 | 05/05/2025 | 5 | 1 | 4 | 05/06/2025 | 05/06/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 | 04/28/2025 | 7/11/2026 | Y | EXP | 365 | 08/19/2025 | 10/03/2025 | 46 | 0 | 46 |  |  | 11/1/2025 | Connected |  | N
National Grid | WARREN | 198326 | 01083 | 10 | Solar | 05_05_320W1 | 11/02/2018 | 11/13/2018 | 1 | 1 | 0 | 11/14/2018 | 11/14/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177361 | 01603 | 75 | Natural Gas | 05_12_49W2 | 06/22/2016 | 06/22/2016 | 18 | 18 | 0 | 07/20/2016 | 07/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2016 |  | 6/28/2017 | N | EXP | 289 |  |  | 0 | 0 | 0 | 11/17/2016 | 11/17/2016 | 12/7/2016 | Connected |  | N
National Grid | DIGHTON | 257941 | 02764 | 10 | Solar | 05_14_24L1 | 10/08/2019 | 10/15/2019 | 3 | 0 | 3 | 10/16/2019 | 10/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2019 | 10/08/2019 | 10/8/2020 | Y | EXP | 365 | 03/10/2020 | 03/11/2020 | 1 | 0 | 1 |  |  | 5/15/2020 | Connected |  | N
National Grid | UPTON | 671315 | 01568 | 7.6 | Solar | 05_14_55L2 | 02/11/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 653900 | 01970 | 5.76 | Solar | 05_14_6J1 | 11/29/2024 | 12/31/2024 | 9 | 5 | 4 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 649061 | 01824 | 3.8 | Solar | 05_14_78L1 | 11/05/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/05/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | ANDOVER | 712303 | 01845 | 22.8 | Solar | 05_01_226L2 | 10/02/2025 | 10/10/2025 | 6 | 4 | 2 | 10/14/2025 | 10/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 12/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 178565 | 01841 | 4998 | Solar | 05_01_406L1 | 04/05/2018 | 04/16/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 07/09/2018 | 59 | 35 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 213652 | 01826 | 7.36 | Solar | 05_01_525L2 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 655540 | 01463 | 3.8 | Solar | 05_01_7J387 | 11/19/2024 | 12/19/2024 | 5 | 0 | 5 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2026 | Connected |  | N
National Grid | OXFORD | 689939 | 01540 | 23.18 | Solar | 05_05_19W74 | 05/06/2025 | 05/21/2025 | 10 | 7 | 3 | 05/22/2025 | 05/22/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 8/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2025 | Connected |  | N
National Grid | WEST BROOKFIELD | 294823 | 01585 | 10 | Solar | 05_05_320W1 | 06/16/2020 | 06/29/2020 | 8 | 4 | 4 | 06/30/2020 | 06/30/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 186726 | 01603 | 88 | Solar | 05_12_49W2 | 05/31/2018 | 05/31/2018 | 0 | 0 | 0 | 06/04/2018 | 06/04/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 |  | 5/26/2020 | N | EXP | 555 |  |  | 0 | 0 | 0 |  |  | 6/9/2020 | Connected |  | N
National Grid | SOMERSET | 415288 | 02726 | 11.4 | Solar | 05_14_24L1 | 03/03/2022 | 03/04/2022 | 1 | 0 | 1 | 03/07/2022 | 03/07/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2022 |  | 4/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2022 | Connected |  | N
National Grid | UPTON | 726653 | 01568 | 11.5 | Solar | 05_14_56L1 | 10/15/2025 | 10/21/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 760390 | 01970 | 7.6 | Solar | 05_14_6J2 | 04/01/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | CHELMSFORD | 650662 | 01824 | 5.76 | Solar | 05_14_78L1 | 11/11/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/11/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | ANDOVER | 725613 | 01845 | 4.56 | Solar | 05_01_226L2 | 10/10/2025 | 10/16/2025 | 1 | 0 | 1 | 10/28/2025 | 10/28/2025 | 49 | 33 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 191612 | 01841 | 272 | Solar | 05_01_406L1 | 11/27/2018 | 11/27/2018 | 0 | 0 | 0 |  |  | 108 | 56 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 272131 | 01826 | 0 | Other | 05_01_525L2 | 02/24/2020 | 04/10/2020 | 33 | 27 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2020 | 05/11/2020 | 19 | 9 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 176338 | 01463 | 308 | Solar | 05_01_8J364 | 09/17/2015 | 09/17/2015 | 3 | 3 | 0 | 09/22/2015 | 09/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2015 |  | 9/22/2016 | N | EXP | 329 |  |  | 0 | 0 | 0 | 2/8/2016 | 2/8/2016 | 2/12/2016 | Connected |  | N
National Grid | OXFORD | 690064 | 01537 | 18.62 | Solar | 05_05_19W74 | 05/06/2025 | 05/16/2025 | 7 | 0 | 7 | 05/19/2025 | 05/19/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 | 05/06/2025 | 6/12/2026 | Y | EXP | 365 | 06/25/2025 | 07/23/2025 | 29 | 0 | 29 |  |  | 9/6/2025 | Connected |  | N
National Grid | WARREN | 335875 | 01083 | 9.6 | Solar | 05_05_320W1 | 01/08/2021 | 01/20/2021 | 6 | 5 | 1 | 01/21/2021 | 01/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2021 |  | 1/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2021 | Connected |  | N
National Grid | WORCESTER | 194178 | 01603 | 146 | Solar | 05_12_49W2 | 08/24/2018 | 08/29/2018 | 0 | 0 | 0 | 08/30/2018 | 08/30/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 |  | 5/26/2020 | N | EXP | 417 |  |  | 0 | 0 | 0 |  |  | 7/27/2020 | Connected |  | N
National Grid | DIGHTON | 426459 | 02764 | 15.2 | Solar | 05_14_24L1 | 05/23/2022 | 06/10/2022 | 14 | 13 | 1 | 06/13/2022 | 06/13/2022 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2022 | 05/23/2022 | 11/14/2023 | Y | EXP | 365 | 10/19/2022 | 11/14/2022 | 27 | 0 | 27 |  |  | 12/15/2022 | Connected |  | N
National Grid | NORTHBRIDGE | 725726 | 01534 | 46 | Solar | 05_14_56L1 | 11/12/2025 | 11/14/2025 | 2 | 1 | 1 | 11/17/2025 | 11/17/2025 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 |  | 1/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 175682 | 01970 | 115.2 | Solar | 05_14_6J2 | 12/24/2014 | 12/24/2014 | 4 | 0 | 4 | 01/02/2015 | 01/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 | 12/24/2014 | 1/19/2016 | Y | EXP | 350 | 11/12/2015 | 09/01/2016 | 200 | 0 | 200 | 2/4/2015 | 2/4/2015 | 12/22/2015 | Connected |  | N
National Grid | CHELMSFORD | 650608 | 01824 | 12.16 | Solar | 05_14_78L1 | 10/29/2024 | 11/04/2024 | 2 | 0 | 2 | 11/05/2024 | 11/05/2024 | 49 | 24 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 738225 | 01845 | 7.6 | Solar | 05_01_226L2 | 12/04/2025 | 01/14/2026 | 2 | 0 | 2 | 01/15/2026 | 01/15/2026 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 198041 | 01841 | 15.2 | Solar | 05_01_406L1 | 10/09/2018 | 10/12/2018 | 2 | 0 | 2 | 10/15/2018 | 10/15/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 |  | 11/1/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2019 | Connected |  | N
National Grid | DRACUT | 281385 | 01826 | 0 | Other | 05_01_525L2 | 08/31/2020 | 09/24/2020 | 17 | 13 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/25/2020 | 10/20/2020 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 680111 | 01463 | 3.8 | Solar | 05_01_8J364 | 03/24/2025 | 04/04/2025 | 1 | 0 | 1 | 04/18/2025 | 04/18/2025 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | CHARLTON | 704932 | 01507 | 17.48 | Solar | 05_05_19W74 | 07/15/2025 | 09/08/2025 | 37 | 32 | 5 | 09/09/2025 | 09/09/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 390487 | 01535 | 9.765 | Solar | 05_05_320W1 | 11/12/2021 | 01/05/2022 | 2 | 0 | 2 | 11/16/2021 | 11/16/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/12/2021 | 4/3/2023 | Y | EXP | 365 | 02/08/2022 | 03/31/2022 | 52 | 0 | 52 |  |  | 5/11/2022 | Connected |  | N
National Grid | WORCESTER | 290730 | 01607 | 100 | Solar | 05_12_49W2 | 05/26/2020 | 06/16/2020 | 15 | 12 | 3 | 06/17/2020 | 06/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2020 |  | 8/10/2022 | N | EXP | 625 |  |  | 0 | 0 | 0 |  |  | 8/19/2022 | Connected |  | N
National Grid | DIGHTON | 439488 | 02764 | 5.76 | Solar | 05_14_24L1 | 06/29/2022 | 07/01/2022 | 2 | 0 | 2 | 07/05/2022 | 07/05/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBRIDGE | 174528 | 01534 | 500 | Solar | 05_14_56L1 | 08/09/2011 | 08/09/2011 | 29 | 0 | 29 | 09/20/2011 | 09/20/2011 | 1281 | 0 | 1281 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2011 |  | 12/31/2016 | N | EXP | 1915 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 177413 | 01970 | 3.8 | Solar | 05_14_6J2 | 09/12/2016 | 09/12/2016 | 1 | 1 | 0 | 09/14/2016 | 09/14/2016 | 282 | 0 | 282 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2016 | 09/12/2016 | 11/18/2017 | Y | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 651579 | 01824 | 3.8 | Solar | 05_14_78L1 | 11/12/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/12/2024 | 4/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | ANDOVER | 743829 | 01845 | 0 | Battery Add-On | 05_01_226L2 | 01/08/2026 | 01/12/2026 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 204158 | 01841 | 306.4 | Solar | 05_01_406L1 | 12/18/2018 | 01/10/2019 | 14 | 12 | 2 | 01/11/2019 | 01/11/2019 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 283873 | 01826 | 0 | Other | 05_01_525L2 | 09/02/2020 | 09/21/2020 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/13/2020 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 680491 | 01463 | 3.8 | Solar | 05_01_8J364 | 03/25/2025 | 04/07/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 715587 | 01507 | 30 | Solar | 05_05_19W74 | 08/29/2025 | 09/09/2025 | 5 | 3 | 2 | 09/10/2025 | 09/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | N
National Grid | BROOKFIELD | 415301 | 01506 | 30 | Solar | 05_05_320W1 | 03/03/2022 | 03/04/2022 | 1 | 0 | 1 | 03/07/2022 | 03/07/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2022 | Connected |  | N
National Grid | WORCESTER | 291146 | 01607 | 7.54 | Solar | 05_12_49W2 | 05/11/2020 | 05/12/2020 | 0 | 0 | 0 | 05/13/2020 | 05/13/2020 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2020 | 05/11/2020 | 5/11/2021 | Y | EXP | 365 | 09/11/2020 | 09/22/2020 | 11 | 0 | 11 |  |  | 11/18/2020 | Connected |  | N
National Grid | DIGHTON | 475619 | 02764 | 100 | Solar | 05_14_24L1 | 11/08/2022 | 12/12/2022 | 23 | 13 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 290152 | 01568 | 10 | Solar | 05_14_56L1 | 05/01/2020 | 05/04/2020 | 0 | 0 | 0 | 05/05/2020 | 05/05/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2020 | Connected |  | N
National Grid | SALEM | 177910 | 01970 | 7.6 | Solar | 05_14_6J2 | 08/16/2017 | 08/16/2017 | 13 | 13 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 |  | 8/25/2020 | N | EXP | 622 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 652420 | 01824 | 3.8 | Solar | 05_14_78L1 | 11/14/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | ANDOVER | 748763 | 01845 | 24.96 | Solar | 05_01_226L2 | 02/09/2026 | 02/26/2026 | 12 | 8 | 4 | 02/27/2026 | 02/27/2026 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 245016 | 01841 | 10 | Solar | 05_01_406L1 | 07/23/2019 | 10/08/2019 | 4 | 3 | 1 | 10/09/2019 | 10/09/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 | 07/23/2019 | 7/7/2020 | Y | EXP | 365 | 02/19/2020 | 02/20/2020 | 1 | 0 | 1 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 289281 | 01826 | 4950 | Other | 05_01_525L2 | 05/15/2020 | 05/27/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2020 | 06/23/2020 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 681766 | 01463 | 3.8 | Solar | 05_01_8J364 | 04/01/2025 | 04/24/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | OXFORD | 747749 | 01537 | 3.8 | Solar | 05_05_19W74 | 01/27/2026 | 01/28/2026 | 2 | 0 | 2 | 02/09/2026 | 02/09/2026 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2026 |  | 3/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 526206 | 01585 | 15.2 | Solar | 05_05_320W1 | 08/27/2023 | 08/28/2023 | 1 | 0 | 1 | 08/29/2023 | 08/29/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 292831 | 01607 | 100 | Solar | 05_12_49W2 | 07/08/2020 | 07/15/2020 | 4 | 0 | 4 | 07/16/2020 | 07/16/2020 | 256 | 26 | 230 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 511233 | 02764 | 0 | Solar | 05_14_24L1 | 03/15/2023 | 09/28/2023 | 135 | 132 | 3 | 09/29/2023 | 09/29/2023 | 98 | 65 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITINSVILLE | 339459 | 01588 | 0 | Battery Add-On | 05_14_56L1 | 01/29/2021 | 02/01/2021 | 0 | 0 | 0 | 02/02/2021 | 02/02/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2021 |  | 3/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2022 | Connected |  | N
National Grid | SALEM | 197441 | 01970 | 3.8 | Solar | 05_14_6J2 | 10/04/2018 |  | 203 | 23 | 180 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 653219 | 01824 | 6.08 | Solar | 05_14_78L1 | 11/08/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/08/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | ANDOVER | 174867 | 01845 | 11 | Solar | 05_01_226L2 | 08/06/2012 | 08/06/2012 | 6 | 0 | 6 | 08/16/2012 | 08/16/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 12/21/2012 | 12/21/2012 | 2/14/2013 | Connected |  | N
National Grid | LAWRENCE | 281119 | 01841 | 2400 | Natural Gas | 05_01_406L1 | 06/09/2020 | 07/14/2020 | 25 | 17 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2020 | 08/04/2020 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2021 | 06/09/2020 | 9/19/2023 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 330996 | 01826 | 9.8 | Solar | 05_01_525L2 | 12/30/2020 | 01/04/2021 | 1 | 0 | 1 | 01/05/2021 | 01/05/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 696783 | 01463 | 7.6 | Solar | 05_01_8J364 | 06/23/2025 | 09/18/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 66 | 48 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 711394 | 01540 | 13.8 | Solar | 05_05_1J1 | 08/12/2025 | 09/11/2025 | 2 | 0 | 2 | 09/19/2025 | 09/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 | 08/12/2025 | 11/24/2026 | Y | EXP | 365 | 01/13/2026 | 02/05/2026 | 24 | 0 | 24 |  |  |  | Completion Documents |  | N
National Grid | BROOKFIELD | 573240 | 01515 | 50 | Solar | 05_05_320W1 | 12/18/2023 |  | 47 | 38 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 371169 | 01607 | 100 | Solar | 05_12_49W2 | 07/21/2021 | 08/01/2021 | 8 | 0 | 8 |  |  | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2022 | 07/21/2021 | 12/28/2022 | Y | STD | 61 |  |  | 0 | 0 | 0 |  |  | 12/30/2022 | Connected |  | N
National Grid | DIGHTON | 532374 | 02715 | 9.765 | Solar | 05_14_24L1 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 21 | 0 | 21 | 08/04/2023 | 08/24/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 08/24/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 11/29/2024 | N | EXP | 365 | 02/02/2024 | 04/26/2024 | 85 | 0 | 85 |  |  | 5/3/2024 | Connected |  | N
National Grid | UPTON | 451464 | 01568 | 50 | Solar | 05_14_56L1 | 08/12/2022 | 09/19/2022 | 26 | 16 | 10 |  |  | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 297222 | 01970 | 249 | Solar | 05_14_6J2 | 06/18/2020 | 06/24/2020 | 4 | 3 | 1 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 655515 | 01824 | 5.76 | Solar | 05_14_78L1 | 11/19/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | ANDOVER | 176589 | 01845 | 19.75 | Solar | 05_01_226L2 | 10/08/2015 | 10/08/2015 | 0 | 0 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2015 |  | 10/14/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 12/24/2015 | 12/24/2015 | 12/24/2015 | Connected |  | N
National Grid | LAWRENCE | 292506 | 01841 | 0 | Other | 05_01_406L1 | 09/16/2020 | 09/29/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/30/2020 | 10/24/2020 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 343332 | 01826 | 9.8 | Solar | 05_01_525L2 | 03/05/2021 | 03/16/2021 | 6 | 4 | 2 | 03/17/2021 | 03/17/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 | 03/05/2021 | 6/20/2022 | Y | EXP | 365 | 08/10/2021 | 09/03/2021 | 23 | 3 | 20 |  |  | 11/5/2021 | Connected |  | N
National Grid | PEPPERELL | 730871 | 01463 | 15.2 | Solar | 05_01_8J365 | 11/03/2025 | 12/11/2025 | 1 | 1 | 0 | 12/12/2025 | 12/12/2025 | 74 | 24 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEICESTER | 721844 | 01524 | 10 | Solar | 05_05_1J1 | 09/25/2025 | 10/13/2025 | 3 | 0 | 3 | 11/21/2025 | 11/21/2025 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 | 09/25/2025 | 1/9/2027 | Y | EXP | 365 | 03/07/2026 |  | 26 | 0 | 26 |  |  |  | Construction |  | N
National Grid | WEST BROOKFIELD | 586651 | 01585 | 10 | Solar | 05_05_320W1 | 02/16/2024 | 03/18/2024 | 21 | 17 | 4 | 03/19/2024 | 03/19/2024 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 488516 | 01610 | 80 | Solar | 05_12_49W2 | 12/29/2022 | 01/23/2023 | 15 | 6 | 9 | 01/24/2023 | 01/24/2023 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  | 3/24/2025 | N | EXP | 105 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | Y
National Grid | ATTLEBORO | 642866 | 02703 | 8.45 | Solar | 05_14_24L1 | 09/25/2024 | 10/11/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/25/2024 | 12/2/2025 | Y | EXP | 365 | 01/04/2025 | 01/24/2025 | 21 | 0 | 21 |  |  | 2/3/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 378880 | 01534 | 15.2 | Solar | 05_14_56L1 | 08/30/2021 | 08/31/2021 | 1 | 0 | 1 | 09/01/2021 | 09/01/2021 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 335011 | 01970 | 166.6 | Solar | 05_14_6J2 | 01/15/2021 | 01/26/2021 | 5 | 0 | 5 | 01/27/2021 | 01/27/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 657540 | 01824 | 10 | Solar | 05_14_78L1 | 11/28/2024 |  | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 176760 | 01845 | 10 | Solar | 05_01_226L2 | 02/24/2016 | 02/24/2016 | 1 | 1 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/24/2016 | 3/1/2017 | Y | EXP | 331 | 07/06/2016 | 08/27/2016 | 38 | 0 | 38 | 4/4/2016 | 4/4/2016 | 11/4/2016 | Connected |  | N
National Grid | LAWRENCE | 295119 | 01841 | 0 | Other | 05_01_406L1 | 09/02/2020 | 09/21/2020 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/13/2020 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 353809 | 01826 | 15.2 | Solar | 05_01_525L2 | 08/18/2021 | 09/20/2021 | 23 | 22 | 1 | 09/21/2021 | 09/21/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 | 08/18/2021 | 7/15/2023 | Y | EXP | 390 | 02/09/2022 | 03/23/2022 | 43 | 0 | 43 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 470212 | 01463 | 6 | Solar | 05_05_1J1 | 01/24/2023 | 01/26/2023 | 2 | 0 | 2 | 01/27/2023 | 01/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2023 | 01/24/2023 | 6/7/2024 | Y | EXP | 365 | 05/16/2023 | 06/08/2023 | 24 | 0 | 24 |  |  | 7/10/2023 | Connected |  | N
National Grid | CHARLTON | 610138 | 01507 | 15.2 | Solar | 05_05_320W1 | 05/14/2024 | 05/16/2024 | 2 | 0 | 2 | 05/17/2024 | 05/17/2024 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 05/14/2024 | 7/19/2025 | Y | EXP | 365 | 08/07/2024 | 08/26/2024 | 20 | 0 | 20 |  |  | 9/24/2024 | Connected |  | N
National Grid | BROOKFIELD | 511480 | 01506 | 15.2 | Solar | 05_12_49W2 | 03/22/2023 | 03/23/2023 | 1 | 0 | 1 | 03/24/2023 | 03/24/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 | 03/22/2023 | 4/26/2024 | Y | EXP | 365 | 07/28/2023 | 08/09/2023 | 13 | 0 | 13 |  |  | 8/14/2023 | Connected |  | N
National Grid | WORCESTER | 657505 | 01610 | 7.6 | Solar | 05_14_24L1 | 11/27/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 11/27/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 473878 | 02703 | 22.8 | Solar | 05_14_56L1 | 11/02/2022 | 11/03/2022 | 1 | 0 | 1 | 11/04/2022 | 11/04/2022 | 325 | 266 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 506007 | 01568 | 17.6 | Solar | 05_14_6J2 | 03/07/2023 | 03/09/2023 | 2 | 0 | 2 | 03/10/2023 | 03/10/2023 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2023 | 03/07/2023 | 6/6/2024 | Y | EXP | 365 | 08/12/2023 | 10/11/2023 | 61 | 0 | 61 |  |  | 10/14/2023 | Connected |  | N
National Grid | SALEM | 662302 | 01970 | 5.76 | Solar | 05_14_78L1 | 12/23/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/23/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | CHELMSFORD | 177411 | 01824 | 20 | Solar | 05_01_226L2 | 09/12/2016 | 09/12/2016 | 10 | 10 | 0 | 09/26/2016 | 09/26/2016 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 |  | 9/17/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 313292 | 01845 | 10 | Solar | 05_01_406L1 | 10/21/2020 | 10/22/2020 | 0 | 0 | 0 | 10/23/2020 | 10/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2020 |  | 10/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2021 | Connected |  | N
National Grid | LAWRENCE | 449501 | 01841 | 3.8 | Solar | 05_01_525L2 | 05/22/2023 | 09/01/2022 | 2 | 0 | 2 | 05/25/2023 | 05/25/2023 | 53 | 34 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2022 |  | 12/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2023 | Connected |  | N
National Grid | DRACUT | 493074 | 01826 | 6 | Solar | 05_05_1J1 | 02/15/2023 | 02/16/2023 | 1 | 0 | 1 | 02/17/2023 | 02/17/2023 | 46 | 23 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 02/15/2023 | 7/8/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2024 | Connected |  | N
National Grid | PEPPERELL | 615196 | 01463 | 7.6 | Solar | 05_05_320W1 | 06/05/2024 | 06/20/2024 | 3 | 0 | 3 | 06/21/2024 | 06/21/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/05/2024 | 7/30/2025 | Y | EXP | 365 | 08/21/2024 | 09/12/2024 | 23 | 0 | 23 |  |  | 10/7/2024 | Connected |  | N
National Grid | OXFORD | 559364 | 01537 | 5 | Solar | 05_12_49W2 | 10/17/2023 | 10/19/2023 | 2 | 0 | 2 | 10/20/2023 | 10/20/2023 | 54 | 38 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  | 1/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2024 | Connected |  | N
National Grid | WEST BROOKFIELD | 685057 | 01585 | 10 | Solar | 05_14_24L1 | 04/17/2025 |  | 120 | 25 | 95 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 567932 | 01610 | 60 | Solar | 05_14_56L1 | 06/04/2024 | 07/02/2024 | 19 | 12 | 7 | 07/03/2024 | 07/03/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 6/30/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 3/11/2026 | Connected |  | N
National Grid | ATTLEBORO | 549133 | 02703 | 6 | Solar | 05_14_6J2 | 09/06/2023 | 09/11/2023 | 4 | 3 | 1 | 09/12/2023 | 09/12/2023 | 46 | 22 | 24 | 11/28/2023 | 01/23/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 | 01/23/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 | 1/23/2024 |  | 3/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 711464 | 01568 | 7.6 | Solar | 05_14_78L1 | 08/12/2025 | 09/08/2025 | 4 | 0 | 4 | 10/07/2025 | 10/07/2025 | 60 | 47 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 178118 | 01970 | 10 | Solar | 05_01_226L2 | 05/11/2017 | 05/11/2017 | 4 | 4 | 0 | 05/17/2017 | 05/17/2017 | 181 | 0 | 181 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2017 |  | 5/16/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 350779 | 01824 | 24 | Solar | 05_01_406L1 | 05/05/2021 | 01/07/2022 | 0 | 0 | 0 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2021 | 05/05/2021 | 3/9/2023 | Y | EXP | 365 | 01/14/2022 | 01/14/2022 | 1 | 0 | 1 |  |  | 4/5/2022 | Connected |  | N
National Grid | ANDOVER | 389963 | 01845 | 6 | Solar | 05_01_525L2 | 11/03/2021 | 01/06/2022 | 5 | 1 | 4 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 206485 | 01841 | 210 | Solar | 05_01_8J365 | 03/19/2019 | 03/22/2019 | 2 | 0 | 2 |  |  | 26 | 21 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 | 03/19/2019 | 6/22/2023 | Y | STD | 927 |  |  | 0 | 0 | 0 |  |  | 6/20/2023 | Connected |  | N
National Grid | DRACUT | 647523 | 01826 | 7.6 | Solar | 05_05_1J1 | 10/22/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 10/22/2024 | 2/19/2026 | Y | EXP | 365 | 02/28/2025 | 07/16/2025 | 139 | 0 | 139 |  |  | 7/31/2025 | Connected |  | N
National Grid | PEPPERELL | 618849 | 01463 | 34.6 | Solar | 05_05_320W1 | 08/12/2024 | 08/15/2024 | 4 | 3 | 1 | 08/16/2024 | 08/16/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 |  | 10/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2025 | Connected |  | N
National Grid | CHARLTON | 622085 | 01507 | 60 | Solar | 05_12_49W2 | 07/08/2024 | 12/12/2024 | 108 | 100 | 8 | 12/13/2024 | 12/13/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 3/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2026 | Connected |  | N
National Grid | WEST BROOKFIELD | 686019 | 01585 | 20 | Solar | 05_14_24L1 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2025 | Connected |  | N
National Grid | WORCESTER | 604257 | 01610 | 23 | Solar | 05_14_56L1 | 04/16/2024 | 04/18/2024 | 2 | 0 | 2 | 04/19/2024 | 04/19/2024 | 81 | 56 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | ATTLEBORO | 582362 | 02703 | 2.9 | Solar | 05_14_6J2 | 01/17/2024 | 01/19/2024 | 2 | 0 | 2 | 01/22/2024 | 01/22/2024 | 69 | 50 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBRIDGE | 723417 | 01534 | 6.282 | Solar | 05_14_78L3 | 10/02/2025 | 10/06/2025 | 2 | 0 | 2 | 10/07/2025 | 10/07/2025 | 43 | 20 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 178432 | 01970 | 636 | Solar | 05_01_226L2 | 03/05/2018 | 03/05/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 419196 | 01824 | 9.28 | Solar | 05_01_406L1 | 04/28/2022 |  | 303 | 21 | 282 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 414330 | 01845 | 7.6 | Solar | 05_01_525L2 | 02/25/2022 | 02/28/2022 | 1 | 0 | 1 | 03/01/2022 | 03/01/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 6/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2022 | Connected |  | N
National Grid | LAWRENCE | 594220 | 01841 | 7.6 | Solar | 05_01_8J365 | 03/05/2024 | 03/08/2024 | 3 | 0 | 3 | 03/11/2024 | 03/11/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 |  | 3/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2024 | Connected |  | N
National Grid | DRACUT | 654221 | 01826 | 9.5 | Solar | 05_05_1J1 | 11/14/2024 | 11/26/2024 | 2 | 0 | 2 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 619888 | 01463 | 7.6 | Solar | 05_05_320W1 | 06/24/2024 | 07/01/2024 | 3 | 0 | 3 | 07/02/2024 | 07/02/2024 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 06/24/2024 | 12/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | N
National Grid | CHARLTON | 628651 | 01507 | 3.8 | Solar | 05_12_49W2 | 08/06/2024 | 08/07/2024 | 1 | 0 | 1 | 08/08/2024 | 08/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N
National Grid | WEST BROOKFIELD | 699938 | 01585 | 15.2 | Solar | 05_14_24L1 | 06/25/2025 | 06/27/2025 | 2 | 0 | 2 | 06/30/2025 | 06/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 06/25/2025 | 8/5/2026 | Y | EXP | 365 | 11/04/2025 | 12/02/2025 | 29 | 0 | 29 |  |  | 12/6/2025 | Connected |  | N
National Grid | WORCESTER | 659758 | 01604 | 23 | Solar | 05_14_56L1 | 12/10/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 643758 | 02703 | 4.64 | Solar | 05_14_6J2 | 09/30/2024 | 11/12/2024 | 4 | 0 | 4 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 189632 | 01534 | 11.4 | Solar | 05_14_78L3 | 07/10/2019 | 06/29/2018 | 134 | 126 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 178743 | 01970 | 990 | Solar | 05_01_226L2 | 05/30/2018 | 07/18/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2018 | 08/01/2018 | 10 | 2 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/24/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 420713 | 01824 | 240 | Solar | 05_01_406L1 | 06/22/2022 | 10/07/2022 | 74 | 64 | 10 |  |  | 322 | 298 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 414012 | 01845 | 15.2 | Solar | 05_01_525L2 | 02/24/2022 | 03/01/2022 | 4 | 3 | 1 | 03/02/2022 | 03/02/2022 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 600333 | 01841 | 10 | Solar | 05_01_8J365 | 03/29/2024 | 04/02/2024 | 2 | 0 | 2 | 04/03/2024 | 04/03/2024 | 15 | 9 | 6 | 05/22/2024 | 05/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 05/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 7/3/2025 | N | EXP | 365 | 08/13/2024 | 01/16/2025 | 157 | 0 | 157 |  |  | 1/30/2025 | Connected |  | N
National Grid | DRACUT | 699205 | 01826 | 5.7 | Solar | 05_05_1J1 | 06/30/2025 | 07/11/2025 | 7 | 4 | 3 | 07/14/2025 | 07/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | PEPPERELL | 622626 | 01463 | 10 | Solar | 05_05_320W1 | 07/11/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/11/2024 | 11/30/2025 | Y | EXP | 365 | 10/03/2024 | 10/02/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 640219 | 01540 | 3.8 | Solar | 05_12_49W2 | 09/13/2024 | 10/04/2024 | 3 | 0 | 3 | 10/07/2024 | 10/07/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/13/2024 | 11/20/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | WEST BROOKFIELD | 704907 | 01585 | 7.6 | Solar | 05_14_24L1 | 07/15/2025 | 09/15/2025 | 6 | 1 | 5 | 09/25/2025 | 09/25/2025 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | WORCESTER | 661777 | 01607 | 5.76 | Solar | 05_14_56L1 | 12/19/2024 | 01/22/2025 | 5 | 0 | 5 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 661733 | 02703 | 10 | Solar | 05_14_6J2 | 12/19/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 194002 | 01534 | 15.2 | Solar | 05_14_78L3 | 08/20/2018 | 09/04/2018 | 20 | 10 | 10 | 10/11/2018 | 10/11/2018 | 71 | 53 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 185273 | 01970 | 5310 | Solar | 05_01_226L2 | 07/23/2018 | 08/08/2018 | 12 | 12 | 0 |  |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 08/09/2018 | 08/14/2018 | 3 | 0 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 427518 | 01824 | 996 | Solar | 05_01_406L1 | 12/20/2022 | 04/06/2023 | 73 | 73 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2023 | 05/03/2023 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 424701 | 01845 | 3.8 | Solar | 05_01_525L2 | 04/22/2022 | 04/29/2022 | 5 | 3 | 2 | 05/02/2022 | 05/02/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 645707 | 01841 | 11.5 | Solar | 05_01_8J365 | 10/09/2024 | 11/07/2024 | 2 | 0 | 2 | 11/08/2024 | 11/08/2024 | 18 | 1 | 17 | 01/15/2025 | 10/16/2025 | 189 | 80 | 109 |  |  | 0 | 0 | 0 | 10/16/2025 | 189 | 80 | 109 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 357772 | 01826 | 133.2 | Solar | 05_05_1J3 | 07/14/2021 | 08/10/2021 | 19 | 10 | 9 |  |  | 67 | 7 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2022 | 07/14/2021 | 3/23/2024 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 645388 | 01463 | 5.76 | Solar | 05_05_320W1 | 10/07/2024 | 11/04/2024 | 4 | 0 | 4 | 11/05/2024 | 11/05/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/07/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | CHARLTON | 647501 | 01507 | 5.76 | Solar | 05_12_49W2 | 10/22/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/22/2024 | 1/6/2026 | Y | EXP | 365 | 02/12/2025 | 03/01/2025 | 18 | 0 | 18 |  |  | 5/2/2025 | Connected |  | N
National Grid | BROOKFIELD | 731515 | 01506 | 15.2 | Solar | 05_14_24L1 | 11/05/2025 | 11/10/2025 | 3 | 0 | 3 | 11/12/2025 | 11/12/2025 | 36 | 15 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2026 |  | 1/21/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2026 | Connected |  | N
National Grid | WORCESTER | 693032 | 01607 | 13.05 | Solar | 05_14_56L1 | 05/20/2025 | 05/22/2025 | 2 | 0 | 2 | 05/23/2025 | 05/23/2025 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2025 | Connected |  | N
National Grid | ATTLEBORO | 682496 | 02703 | 15.2 | Solar | 05_14_6J3 | 04/03/2025 | 04/14/2025 | 7 | 5 | 2 | 04/15/2025 | 04/15/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | UPTON | 194659 | 01568 | 7.6 | Solar | 05_14_78L3 | 08/28/2018 | 09/13/2018 | 8 | 0 | 8 | 09/14/2018 | 09/14/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 198924 | 01970 | 10 | Solar | 05_01_226L2 | 10/18/2018 | 03/18/2019 | 39 | 35 | 4 | 03/19/2019 | 03/19/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 | 10/18/2018 | 1/14/2021 | Y | EXP | 365 | 06/03/2020 | 06/18/2020 | 15 | 0 | 15 |  |  | 7/3/2020 | Connected |  | N
National Grid | CHELMSFORD | 433800 | 01824 | 9.984 | Solar | 05_01_406L1 | 06/15/2022 | 06/16/2022 | 1 | 0 | 1 | 06/17/2022 | 06/17/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2022 |  | 2/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 457878 | 01845 | 3.77 | Solar | 05_01_525L2 | 10/13/2022 | 10/18/2022 | 4 | 1 | 3 | 10/19/2022 | 10/19/2022 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/13/2022 | 8/6/2024 | Y | EXP | 365 | 07/19/2023 | 08/04/2023 | 17 | 0 | 17 |  |  | 8/24/2023 | Connected |  | N
National Grid | LAWRENCE | 680752 | 01841 | 10 | Solar | 05_01_8J365 | 03/26/2025 | 04/03/2025 | 7 | 5 | 2 | 04/04/2025 | 04/04/2025 | 49 | 29 | 20 | 08/04/2025 | 10/27/2025 | 58 | 4 | 54 |  |  | 0 | 0 | 0 | 10/27/2025 | 58 | 4 | 54 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | DRACUT | 646703 | 01826 | 7.6 | Solar | 05_05_1J3 | 10/25/2024 | 11/12/2024 | 2 | 0 | 2 | 11/13/2024 | 11/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 |  | 12/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 660931 | 01463 | 7.6 | Solar | 05_05_320W1 | 12/16/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 57 | 35 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 12/16/2024 | 4/14/2026 | Y | EXP | 365 | 06/24/2025 | 07/16/2025 | 23 | 0 | 23 |  |  | 8/19/2025 | Connected |  | N
National Grid | OXFORD | 688394 | 01537 | 15.2 | Solar | 05_12_49W2 | 04/29/2025 | 05/01/2025 | 2 | 0 | 2 | 05/02/2025 | 05/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 657917 | 01506 | 3.8 | Solar | 05_14_24L2 | 12/02/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 4/11/2026 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 704185 | 01610 | 15.76 | Solar | 05_14_56L1 | 07/16/2025 | 07/18/2025 | 2 | 0 | 2 | 07/21/2025 | 07/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  | 9/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | ATTLEBORO | 285114 | 02703 | 7.6 | Solar | 05_14_6J3 | 04/01/2020 | 04/22/2020 | 1 | 0 | 1 | 04/23/2020 | 04/23/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITINSVILLE | 264017 | 01588 | 0 | Solar | 05_14_78L3 | 11/05/2019 | 11/08/2019 | 2 | 0 | 2 | 11/12/2019 | 11/12/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 |  | 11/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2020 | Connected |  | N
National Grid | SALEM | 204874 | 01970 | 7.6 | Solar | 05_01_226L2 | 12/31/2018 | 01/25/2019 | 17 | 17 | 0 | 01/28/2019 | 01/28/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2019 |  | 12/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2019 | Connected |  | N
National Grid | CHELMSFORD | 439718 | 01824 | 15.2 | Solar | 05_01_406L1 | 06/23/2022 | 06/24/2022 | 1 | 0 | 1 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2023 | Connected |  | N
National Grid | ANDOVER | 496520 | 01845 | 15.2 | Solar | 05_01_525L2 | 01/30/2023 | 02/17/2023 | 15 | 14 | 1 | 02/21/2023 | 02/21/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2023 | Connected |  | N
National Grid | LAWRENCE | 691733 | 01841 | 7.6 | Solar | 05_01_8J365 | 05/14/2025 | 06/03/2025 | 2 | 0 | 2 | 06/06/2025 | 06/06/2025 | 50 | 38 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 699742 | 01826 | 13.36 | Solar | 05_05_1J4 | 06/27/2025 | 07/01/2025 | 2 | 0 | 2 | 07/02/2025 | 07/02/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 | 06/27/2025 | 1/6/2027 | Y | EXP | 365 | 02/11/2026 | 02/19/2026 | 9 | 0 | 9 |  |  |  | Completion Documents |  | Y
National Grid | PEPPERELL | 661979 | 01463 | 3.8 | Solar | 05_05_320W1 | 12/20/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | CHARLTON | 641227 | 01507 | 0 | Other | 05_12_49W4 | 07/12/2025 | 11/23/2025 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 87 | 25 | 62 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BROOKFIELD | 711798 | 01585 | 3.8 | Solar | 05_14_24L2 | 08/13/2025 | 09/05/2025 | 4 | 0 | 4 | 09/22/2025 | 09/22/2025 | 82 | 68 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 | 08/13/2025 | 1/27/2027 | Y | EXP | 365 | 03/11/2026 | 03/24/2026 | 14 | 0 | 14 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 738785 | 01610 | 0 | Battery Add-On | 05_14_56L1 | 12/08/2025 | 12/11/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 1/14/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2026 | Connected |  | N
National Grid | ATTLEBORO | 315756 | 02703 | 7.6 | Solar | 05_14_6J3 | 10/13/2020 |  | 39 | 38 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBRIDGE | 299147 | 01534 | 10 | Solar | 05_14_78L3 | 07/13/2020 |  | 33 | 24 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 218005 | 01970 | 15.2 | Solar | 05_01_226L2 | 04/05/2019 | 04/12/2019 | 4 | 0 | 4 | 04/15/2019 | 04/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2019 |  | 4/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | CHELMSFORD | 483875 | 01824 | 10 | Solar | 05_01_406L1 | 02/23/2023 | 02/24/2023 | 1 | 0 | 1 | 02/27/2023 | 02/27/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 02/23/2023 | 7/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2023 | Connected |  | N
National Grid | ANDOVER | 514350 | 01845 | 13.92 | Solar | 05_01_525L2 | 04/04/2023 | 04/05/2023 | 1 | 0 | 1 | 04/06/2023 | 04/06/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 177481 | 01841 | 150 | Solar | 05_01_8J389 | 07/08/2016 | 07/08/2016 | 0 | 0 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2016 |  | 7/16/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 | 3/20/2017 | 3/20/2017 | 3/20/2017 | Connected |  | N
National Grid | DRACUT | 744449 | 01826 | 0 | Battery Add-On | 05_05_1J4 | 01/09/2026 | 01/14/2026 | 3 | 0 | 3 | 01/15/2026 | 01/15/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 668717 | 01463 | 1.9 | Solar | 05_05_320W1 | 01/29/2025 | 02/03/2025 | 3 | 0 | 3 | 02/04/2025 | 02/04/2025 | 49 | 28 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | CHARLTON | 725938 | 01507 | 23.034 | Solar | 05_14_24L2 | 10/21/2025 | 10/27/2025 | 4 | 0 | 4 | 10/28/2025 | 10/28/2025 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROOKFIELD | 688268 | 01506 | 20 | Solar | 05_14_56L2 | 05/01/2025 | 05/02/2025 | 1 | 0 | 1 | 05/05/2025 | 05/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 177072 | 01610 | 75 | Solar | 05_14_6J4 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2016 |  | 8/7/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N
National Grid | ATTLEBORO | 381009 | 02703 | 7.6 | Solar | 05_14_78L3 | 10/08/2021 | 01/10/2022 | 0 | 0 | 0 | 10/12/2021 | 10/12/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2021 |  | 5/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2022 | Connected |  | N
National Grid | WHITINSVILLE | 257041 | 01588 | 4890 | Solar | 05_01_226L2 | 04/13/2020 | 05/19/2020 | 25 | 21 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/20/2020 | 06/18/2020 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 538718 | 01463 | 20.01 | Solar | 05_01_406L1 | 07/05/2023 | 07/11/2023 | 4 | 3 | 1 | 07/12/2023 | 07/12/2023 | 114 | 25 | 89 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 572189 | 01824 | 9.28 | Solar | 05_01_525L2 | 01/10/2024 | 03/11/2024 | 41 | 37 | 4 | 03/12/2024 | 03/12/2024 | 40 | 35 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 584498 | 01845 | 10 | Solar | 05_01_8J389 | 02/14/2024 | 02/16/2024 | 2 | 0 | 2 | 02/20/2024 | 02/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | LAWRENCE | 188562 | 01841 | 15.2 | Solar | 05_05_1J4 | 06/19/2018 | 06/19/2018 | 2 | 0 | 2 | 06/29/2018 | 06/29/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2019 | Connected |  | N
National Grid | DRACUT | 678749 | 01826 | 10 | Solar | 05_05_320W1 | 03/19/2025 | 03/24/2025 | 3 | 0 | 3 | 03/25/2025 | 03/25/2025 | 66 | 45 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | PEPPERELL | 683682 | 01463 | 0 | Other | 05_12_49W4 | 12/29/2025 | 03/02/2026 | 40 | 32 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2026 | 03/24/2026 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | OXFORD | 736316 | 01537 | 7.6 | Solar | 05_14_24L2 | 11/25/2025 | 12/29/2025 | 5 | 3 | 2 | 02/03/2026 | 02/03/2026 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEST BROOKFIELD | 733362 | 01585 | 20 | Solar | 05_14_56L2 | 11/12/2025 | 11/18/2025 | 4 | 0 | 4 | 11/19/2025 | 11/19/2025 | 57 | 41 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 177070 | 01607 | 108 | Solar | 05_14_6J4 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2016 |  | 8/7/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 3/8/2017 | 3/8/2017 | 3/8/2017 | Connected |  | N
National Grid | ATTLEBORO | 405981 | 02703 | 0 | Battery Add-On | 05_14_78L3 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 03/04/2022 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 312534 | 01534 | 7.6 | Solar | 05_01_226L2 | 10/06/2020 | 10/12/2020 | 3 | 0 | 3 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 10/06/2020 | 10/1/2021 | Y | EXP | 365 | 07/23/2021 | 07/26/2021 | 4 | 0 | 4 |  |  | 8/12/2021 | Connected |  | N
National Grid | PEPPERELL | 550427 | 01463 | 6 | Solar | 05_01_406L1 | 08/23/2023 | 08/25/2023 | 3 | 1 | 2 | 08/28/2023 | 08/28/2023 | 60 | 26 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 572056 | 01824 | 5.22 | Solar | 05_01_525L2 | 11/21/2023 | 11/28/2023 | 4 | 0 | 4 | 11/29/2023 | 11/29/2023 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 11/21/2023 | 2/17/2025 | Y | EXP | 365 | 06/05/2024 | 07/29/2024 | 55 | 0 | 55 |  |  | 8/29/2024 | Connected |  | N
National Grid | ANDOVER | 176189 | 01845 | 0 | Battery Add-On | 05_01_8W1 | 09/01/2015 | 09/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2015 | 10/06/2015 | 22 | 0 | 22 |  | 0 | 0 | 0 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 | 5/2/2016 | 09/01/2015 | 9/8/2016 | Y | STD | 129 | 04/19/2017 | 06/08/2017 | 35 | 0 | 35 | 8/1/2017 | 8/1/2017 | 8/29/2017 | Terminated |  | N
National Grid | LAWRENCE | 476497 | 01841 | 240 | Solar | 05_05_2468W1 | 12/07/2022 | 01/06/2023 | 20 | 11 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 | 12/07/2022 | 7/3/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | DRACUT | 736897 | 01826 | 11.52 | Solar | 05_05_320W1 | 11/28/2025 | 12/01/2025 | 1 | 0 | 1 | 12/02/2025 | 12/02/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | DUNSTABLE | 290691 | 01827 | 0 | Battery Add-On | 05_12_49W4 | 05/06/2020 | 05/06/2020 | 0 | 0 | 0 | 05/07/2020 | 05/07/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2020 | Connected |  | N
National Grid | OXFORD | 743169 | 01537 | 10 | Solar | 05_14_24L2 | 01/02/2026 | 01/06/2026 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 37 | 20 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEST BROOKFIELD | 735129 | 01585 | 15.04 | Solar | 05_14_56L2 | 12/02/2025 | 12/08/2025 | 4 | 0 | 4 | 12/09/2025 | 12/09/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 317552 | 01607 | 33.3 | Solar | 05_14_6J4 | 10/06/2020 | 11/06/2020 | 23 | 15 | 8 | 11/09/2020 | 11/09/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2021 | Connected |  | N
National Grid | ATTLEBORO | 417105 | 02703 | 362.5 | Solar | 05_14_78L3 | 03/25/2022 | 06/15/2022 | 56 | 47 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/16/2022 | 07/15/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 321315 | 01568 | 8.41 | Solar | 05_01_226L2 | 10/23/2020 | 11/18/2020 | 16 | 15 | 1 | 11/19/2020 | 11/19/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 11/18/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 586275 | 01970 | 20.01 | Solar | 05_01_406L1 | 02/19/2024 | 04/25/2024 | 48 | 46 | 2 | 04/26/2024 | 04/26/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 574688 | 01824 | 0 | Battery Add-On | 05_01_525L2 | 11/30/2023 | 12/04/2023 | 2 | 0 | 2 | 12/05/2023 | 12/05/2023 | 196 | 25 | 171 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 724366 | 01845 | 3.8 | Solar | 05_01_8W1 | 10/06/2025 | 10/13/2025 | 4 | 1 | 3 | 10/14/2025 | 10/14/2025 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 475897 | 01840 | 240 | Solar | 05_05_2468W1 | 11/18/2022 | 01/17/2023 | 38 | 28 | 10 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 11/18/2022 | 7/8/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | DRACUT | 710539 | 01826 | 21.66 | Solar | 05_05_320W2 | 08/14/2025 | 08/25/2025 | 6 | 3 | 3 | 08/26/2025 | 08/26/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | PEPPERELL | 357389 | 01463 | 200 | Solar | 05_12_49W4 | 05/28/2021 | 03/18/2022 | 202 | 186 | 16 | 03/21/2022 | 03/21/2022 | 35 | 14 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 | 05/28/2021 | 11/25/2023 | Y | EXP | 280 |  |  | 0 | 0 | 0 |  |  | 12/1/2023 | Connected |  | N
National Grid | OXFORD | 753489 | 01540 | 5.76 | Solar | 05_14_24L2 | 02/27/2026 | 03/03/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEST BROOKFIELD | 744768 | 01585 | 0 | Solar | 05_14_56L2 | 02/09/2026 | 02/10/2026 | 1 | 0 | 1 | 02/11/2026 | 02/11/2026 | 33 | 20 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 604190 | 01604 | 6.09 | Solar | 05_14_6J4 | 04/17/2024 | 04/23/2024 | 5 | 2 | 3 | 04/24/2024 | 04/24/2024 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 483029 | 02035 | 0 | Other | 05_14_78L3 | 01/12/2023 | 02/15/2023 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2023 | 03/21/2023 | 23 | 0 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 334209 | 01534 | 17.6 | Solar | 05_01_226L2 | 01/29/2021 | 02/17/2021 | 12 | 12 | 0 | 02/18/2021 | 02/18/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2021 |  | 2/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2021 | Connected |  | N
National Grid | SALEM | 638065 | 01970 | 10.44 | Solar | 05_01_406L1 | 01/17/2025 | 03/20/2025 | 8 | 3 | 5 | 03/21/2025 | 03/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | CHELMSFORD | 641967 | 01824 | 10 | Solar | 05_01_525L2 | 09/20/2024 | 10/23/2024 | 1 | 0 | 1 | 10/24/2024 | 10/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 174487 | 01845 | 300 | Solar | 05_01_8W1 | 11/12/2010 | 11/12/2010 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2011 | 11/12/2010 | 10/31/2012 | Y | EXP | 610 | 05/30/2012 | 07/30/2012 | 41 | 0 | 41 | 1/18/2013 | 1/18/2013 | 8/17/2012 | Connected |  | N
National Grid | LAWRENCE | 509726 | 01841 | 240 | Solar | 05_05_2468W1 | 03/15/2023 | 04/07/2023 | 17 | 7 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 | 03/15/2023 | 9/30/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | DRACUT | 742639 | 01826 | 3.8 | Solar | 05_05_320W2 | 12/30/2025 | 12/31/2025 | 3 | 0 | 3 | 01/15/2026 | 01/15/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 | 12/30/2025 | 2/20/2027 | Y | EXP | 365 | 02/28/2026 |  | 33 | 0 | 33 |  |  |  | Construction |  | N
National Grid | PEPPERELL | 431968 | 01463 | 7.83 | Solar | 05_12_49W4 | 06/30/2022 | 07/05/2022 | 3 | 2 | 1 | 07/06/2022 | 07/06/2022 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 | 06/30/2022 | 5/22/2024 | Y | EXP | 365 | 11/15/2022 | 05/19/2023 | 186 | 0 | 186 |  |  | 6/17/2023 | Connected |  | N
National Grid | OXFORD | 174747 | 01537 | 225 | Solar | 05_14_24L2 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 407 | 1 | 406 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2013 |  | 8/1/2014 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 757757 | 01585 | 23 | Battery Add-On | 05_14_56L2 | 03/24/2026 | 03/27/2026 | 3 | 0 | 3 | 03/30/2026 | 03/30/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 659147 | 01607 | 11.4 | Solar | 05_14_6J4 | 12/08/2024 |  | 23 | 18 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 491978 | 02035 | 7.6 | Solar | 05_14_78L3 | 03/03/2023 | 03/06/2023 | 1 | 0 | 1 | 03/07/2023 | 03/07/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 | 03/03/2023 | 6/29/2024 | Y | EXP | 365 | 06/13/2023 | 06/30/2023 | 18 | 0 | 18 |  |  | 7/13/2023 | Connected |  | N
National Grid | DOUGLAS | 343268 | 01516 | 10 | Solar | 05_01_226L2 | 02/22/2021 | 03/02/2021 | 5 | 0 | 5 | 03/03/2021 | 03/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 |  | 3/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2021 | Connected |  | N
National Grid | SALEM | 641186 | 01970 | 17.11 | Solar | 05_01_406L1 | 09/27/2024 | 10/17/2024 | 13 | 11 | 2 | 10/18/2024 | 10/18/2024 | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | CHELMSFORD | 645312 | 01824 | 3.8 | Solar | 05_01_525L2 | 10/07/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/07/2024 | 2/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 175354 | 01845 | 2100 | Solar | 05_01_8W1 | 09/09/2014 | 09/09/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2014 | 10/17/2014 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2015 | 09/09/2014 | 12/31/2016 | Y | STD | 579 | 12/28/2016 | 09/09/2017 | 176 | 0 | 176 | 5/17/2017 | 5/17/2017 | 5/17/2017 | Connected |  | N
National Grid | LAWRENCE | 448988 | 01841 | 250 | Solar | 05_05_28W40 | 08/26/2022 | 10/28/2022 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/29/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DRACUT | 749864 | 01826 | 15.2 | Solar | 05_05_320W2 | 02/11/2026 | 02/20/2026 | 5 | 2 | 3 | 02/23/2026 | 02/23/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 444421 | 01463 | 0 | Other | 05_12_49W4 | 03/14/2023 | 07/14/2023 | 84 | 74 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2023 | 08/08/2023 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 175759 | 01507 | 225 | Solar | 05_14_24L2 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 108 | 03/11/2015 | 04/24/2015 | 30 | 0 | 30 | 5/26/2015 | 5/26/2015 | 5/26/2015 | Connected |  | N
National Grid | BROOKFIELD | 174365 | 01506 | 7.5 | Solar | 05_14_56L2 | 05/21/2012 | 05/21/2012 | 8 | 0 | 8 | 06/05/2012 | 06/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2012 | 05/21/2012 | 8/1/2012 | Y | EXP | 106 | 10/04/2012 | 11/19/2012 | 15 | 0 | 15 | 11/15/2012 | 11/15/2012 | 11/15/2012 | Connected |  | N
National Grid | MILLBURY | 665348 | 01527 | 6.09 | Solar | 05_14_6J4 | 01/13/2025 | 03/04/2025 | 18 | 13 | 5 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | FOXBOROUGH | 602555 | 02035 | 0 | Battery Add-On | 05_14_78L3 | 04/10/2024 | 05/09/2024 | 20 | 16 | 4 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 04/10/2024 | 12/31/2025 | Y | EXP | 365 | 07/17/2024 | 07/16/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 357623 | 01516 | 9.8 | Solar | 05_01_226L2 | 05/12/2021 | 05/13/2021 | 1 | 1 | 0 | 05/14/2021 | 05/14/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  | 5/12/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2021 | Connected |  | N
National Grid | SALEM | 650479 | 01970 | 9.423 | Solar | 05_01_406L1 | 10/29/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | CHELMSFORD | 647627 | 01824 | 22.8 | Solar | 05_01_525L2 | 11/06/2024 | 11/12/2024 | 4 | 1 | 3 | 11/13/2024 | 11/13/2024 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | ANDOVER | 175690 | 01845 | 225 | Solar | 05_01_8W1 | 05/23/2014 | 05/23/2014 | 6 | 0 | 6 | 06/04/2014 | 06/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2014 |  | 8/29/2014 | N | EXP | 63 |  |  | 0 | 0 | 0 | 7/2/2014 | 7/2/2014 | 10/29/2014 | Connected |  | N
National Grid | LAWRENCE | 696064 | 01843 | 180 | Solar | 05_05_28W40 | 07/21/2025 | 10/21/2025 | 64 | 55 | 9 | 10/22/2025 | 10/22/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | DRACUT | 174450 | 01826 | 2000 | Solar | 05_05_320W2 | 10/07/2011 | 10/07/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 10/07/2011 | 5/1/2012 | Y | STD | 225 | 10/09/2012 | 01/09/2013 | 47 | 0 | 47 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | N
National Grid | PEPPERELL | 492195 | 01463 | 750 | Solar | 05_12_49W4 | 04/07/2023 | 06/12/2023 | 44 | 34 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2023 | 07/12/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 175833 | 01537 | 16.34 | Solar | 05_14_24L2 | 03/03/2015 | 03/03/2015 | 8 | 5 | 3 | 03/16/2015 | 03/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2015 |  | 7/14/2015 | N | EXP | 120 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 6/15/2015 | Connected |  | N
National Grid | WEST BROOKFIELD | 175130 | 01585 | 12 | Solar | 05_14_56L2 | 11/02/2012 | 11/02/2012 | 1 | 0 | 1 | 11/20/2012 | 11/20/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2013 |  | 2/15/2013 | N | EXP | 4 |  |  | 0 | 0 | 0 | 2/19/2013 | 2/19/2013 | 5/7/2013 | Connected |  | N
National Grid | WORCESTER | 174705 | 01602 | 250 | Solar | 05_14_6J5 | 11/11/2012 | 11/11/2012 | 5 | 0 | 5 | 11/27/2012 | 11/27/2012 | 192 | 0 | 192 | 07/12/2013 | 09/16/2013 | 45 | 0 | 45 |  |  | 0 | 0 | 0 | 09/16/2013 | 45 | 0 | 45 |  |  | 0 | 0 | 0 | 7/12/2013 |  | 8/15/2013 | N | EXP | 34 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 629864 | 02720 | 5.76 | Solar | 05_14_78L3 | 08/02/2024 | 08/29/2024 | 2 | 0 | 2 | 08/30/2024 | 08/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 | 08/02/2024 | 9/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | DOUGLAS | 399819 | 01516 | 7.6 | Solar | 05_01_226L2 | 12/16/2021 | 12/20/2021 | 2 | 0 | 2 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 | 12/16/2021 | 6/8/2023 | Y | EXP | 365 | 05/11/2022 | 06/07/2022 | 28 | 0 | 28 |  |  | 6/16/2022 | Connected |  | N
National Grid | SALEM | 658838 | 01970 | 5.76 | Solar | 05_01_406L1 | 12/05/2024 | 12/20/2024 | 5 | 0 | 5 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 12/05/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 651760 | 01824 | 3.8 | Solar | 05_01_525L2 | 11/13/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | ANDOVER | 177625 | 01845 | 0 | Solar | 05_01_8W1 | 05/23/2017 | 05/23/2017 | 12 | 11 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2017 | 07/03/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/28/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 712877 | 01841 | 3.8 | Solar | 05_05_28W40 | 08/18/2025 | 12/31/2025 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 174445 | 01826 | 60 | Solar | 05_05_320W2 | 07/09/2012 | 07/09/2012 | 6 | 0 | 6 | 07/19/2012 | 07/19/2012 | 0 | 0 | 0 | 02/11/2013 | 02/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2013 | 07/09/2012 | 11/30/2012 | Y | EXP | 73 | 06/18/2013 | 07/31/2013 | 30 | 0 | 30 | 2/11/2013 | 2/11/2013 | 8/12/2013 | Connected |  | N
National Grid | PEPPERELL | 530784 | 01463 | 7.6 | Solar | 05_12_49W4 | 06/12/2023 | 06/14/2023 | 2 | 0 | 2 | 06/15/2023 | 06/15/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 178000 | 01542 | 7.6 | Solar | 05_14_24L2 | 10/25/2017 | 10/25/2017 | 62 | 62 | 0 | 02/06/2018 | 02/06/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2018 |  | 11/1/2018 | N | EXP | 267 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 177954 | 01585 | 20 | Solar | 05_14_56L2 | 10/23/2017 | 10/23/2017 | 101 | 100 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175136 | 01607 | 100 | Solar | 05_14_6J5 | 11/11/2012 | 11/11/2012 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2013 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 636599 | 02720 | 5.76 | Solar | 05_14_78L3 | 08/29/2024 | 09/26/2024 | 7 | 4 | 3 | 09/27/2024 | 09/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 08/29/2024 | 11/25/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | DOUGLAS | 401910 | 01516 | 0 | Battery Add-On | 05_01_226L2 | 12/29/2021 | 01/04/2022 | 3 | 0 | 3 | 01/05/2022 | 01/05/2022 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 660796 | 01970 | 10 | Solar | 05_01_406L1 | 12/16/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | CHELMSFORD | 654347 | 01824 | 10 | Solar | 05_01_525L2 | 11/14/2024 | 12/02/2024 | 4 | 0 | 4 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/14/2024 | 3/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | ANDOVER | 178575 | 01845 | 15.2 | Solar | 05_01_8W1 | 12/11/2017 | 12/11/2017 | 12 | 0 | 12 | 01/02/2018 | 01/02/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 12/18/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N
National Grid | LAWRENCE | 739135 | 01840 | 20.96 | Solar | 05_05_28W40 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2026 |  | 1/15/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 174722 | 01826 | 14 | Solar | 05_05_320W2 | 08/03/2010 | 08/03/2010 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2010 |  | 12/31/2012 | N | EXP | 881 |  |  | 0 | 0 | 0 | 11/29/2012 | 11/29/2012 | 8/3/2010 | Connected |  | N
National Grid | PEPPERELL | 618836 | 01463 | 0 | Battery Add-On | 05_12_49W4 | 06/18/2024 | 06/21/2024 | 3 | 1 | 2 | 06/24/2024 | 06/24/2024 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2024 | Connected |  | N
National Grid | OXFORD | 178611 | 01537 | 0 | Other | 05_14_24L2 | 12/14/2017 | 12/14/2017 | 0 | 0 | 0 | 05/11/2018 | 05/11/2018 | 0 | 0 | 0 | 06/15/2018 | 09/18/2018 | 66 | 40 | 26 |  |  | 0 | 0 | 0 | 09/18/2018 | 66 | 40 | 26 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 4/30/2021 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  | 4/14/2021 | Connected |  | N
National Grid | WEST BROOKFIELD | 178069 | 01585 | 20 | Solar | 05_14_56L2 | 10/30/2017 | 10/30/2017 | 66 | 66 | 0 | 02/13/2018 | 02/13/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 11/5/2018 | N | EXP | 265 |  |  | 0 | 0 | 0 |  |  | 10/16/2018 | Connected |  | N
National Grid | WORCESTER | 175134 | 01607 | 100 | Solar | 05_14_6J5 | 11/11/2012 | 11/11/2012 | 5 | 5 | 0 | 11/27/2012 | 11/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2013 | 11/11/2012 | 1/31/2013 | Y | EXP | 169 | 02/06/2014 | 04/14/2014 | 45 | 0 | 45 | 8/5/2013 | 8/5/2013 | 4/24/2014 | Connected |  | N
National Grid | FALL RIVER | 641351 | 02720 | 5.76 | Solar | 05_14_78L3 | 09/18/2024 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 426686 | 01516 | 0 | Solar | 05_01_226L2 | 04/27/2022 | 07/21/2022 | 58 | 49 | 9 | 07/22/2022 | 07/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2022 |  | 9/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2022 | Connected |  | N
National Grid | SALEM | 661695 | 01970 | 10 | Solar | 05_01_406L1 | 12/19/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 657273 | 01824 | 9.57 | Solar | 05_01_525L2 | 11/29/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/29/2024 | 1/28/2026 | Y | EXP | 365 | 07/02/2025 | 07/14/2025 | 13 | 0 | 13 |  |  | 7/24/2025 | Connected |  | N
National Grid | ANDOVER | 178666 | 01845 | 2112 | Solar | 05_01_8W1 | 03/16/2018 | 03/16/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2018 | 04/13/2018 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/24/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 741831 | 01840 | 11.5 | Solar | 05_05_28W40 | 12/22/2025 | 12/26/2025 | 3 | 0 | 3 | 01/21/2026 | 01/21/2026 | 49 | 24 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 174903 | 01826 | 1000 | Solar | 05_05_320W2 | 08/10/2012 | 08/10/2012 | 244 | 241 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 652802 | 01463 | 10 | Solar | 05_12_49W4 | 12/11/2024 | 12/30/2024 | 12 | 9 | 3 | 12/31/2024 | 12/31/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | CHARLTON | 312556 | 01507 | 7.6 | Solar | 05_14_24L2 | 09/14/2020 | 09/16/2020 | 1 | 0 | 1 | 09/17/2020 | 09/17/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 10/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2021 | Connected |  | N
National Grid | BROOKFIELD | 189257 | 01506 | 15.2 | Solar | 05_14_56L2 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178531 | 01607 | 60 | Solar | 05_14_6J5 | 12/05/2017 | 12/05/2017 | 18 | 0 | 18 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 12/10/2018 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  | 8/10/2018 | Connected |  | N
National Grid | FALL RIVER | 647602 | 02720 | 6 | Solar | 05_14_78L3 | 10/16/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2025 | Connected |  | N
National Grid | DOUGLAS | 433783 | 01516 | 15.2 | Solar | 05_01_226L2 | 06/08/2022 | 06/09/2022 | 1 | 0 | 1 | 06/10/2022 | 06/10/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2022 |  | 7/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | N
National Grid | SALEM | 667149 | 01970 | 12.54 | Solar | 05_01_406L1 | 01/22/2025 | 02/13/2025 | 6 | 1 | 5 | 02/14/2025 | 02/14/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 | 01/22/2025 | 4/16/2026 | Y | EXP | 365 | 07/02/2025 | 10/23/2025 | 114 | 0 | 114 |  |  | 10/24/2025 | Connected |  | N
National Grid | CHELMSFORD | 657862 | 01824 | 10 | Solar | 05_01_525L2 | 12/02/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 12/02/2024 | 4/6/2026 | Y | EXP | 365 | 09/26/2025 | 09/25/2025 | 0 | 0 | 0 |  |  | 12/5/2025 | Connected |  | N
National Grid | ANDOVER | 193914 | 01845 | 60 | Solar | 05_01_8W1 | 08/20/2018 | 08/29/2018 | 6 | 0 | 6 | 08/30/2018 | 08/30/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174536 | 01840 | 950 | Solar | 05_05_28W40 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 175936 | 01826 | 22.8 | Solar | 05_05_320W2 | 01/20/2015 | 01/20/2015 | 5 | 1 | 4 | 01/28/2015 | 01/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2015 |  | 6/30/2015 | N | EXP | 130 |  |  | 0 | 0 | 0 | 3/11/2015 | 3/11/2015 | 9/28/2015 | Connected |  | N
National Grid | PEPPERELL | 657217 | 01463 | 3.8 | Solar | 05_12_49W4 | 11/27/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | CHARLTON | 317800 | 01507 | 10 | Solar | 05_14_24L2 | 10/07/2020 | 11/04/2020 | 19 | 17 | 2 | 11/05/2020 | 11/05/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 11/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2021 | Connected |  | N
National Grid | NORTH BROOKFIELD | 284143 | 01535 | 12 | Solar | 05_14_56L2 | 03/17/2020 | 04/06/2020 | 13 | 13 | 0 | 04/07/2020 | 04/07/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 |  | 4/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2021 | Connected |  | N
National Grid | WORCESTER | 314998 | 01604 | 7.6 | Solar | 05_14_6J5 | 11/03/2020 | 11/05/2020 | 1 | 0 | 1 | 11/06/2020 | 11/06/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/03/2020 |  | Y | EXP | 365 | 04/14/2021 | 06/30/2021 | 77 | 0 | 77 |  |  | 8/10/2021 | Connected |  | N
National Grid | FALL RIVER | 658910 | 02720 | 5.76 | Solar | 05_14_78L3 | 12/06/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/06/2024 | 2/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 435399 | 01516 | 10 | Solar | 05_01_226L2 | 06/23/2022 | 07/21/2022 | 20 | 16 | 4 | 07/22/2022 | 07/22/2022 | 65 | 45 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2022 |  | 11/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2023 | Connected |  | N
National Grid | SALEM | 671156 | 01970 | 9.28 | Solar | 05_01_406L1 | 02/10/2025 | 03/15/2025 | 14 | 10 | 4 | 03/17/2025 | 03/17/2025 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 666204 | 01824 | 7.6 | Solar | 05_01_525L2 | 01/16/2025 | 02/12/2025 | 3 | 0 | 3 | 02/13/2025 | 02/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 192232 | 01845 | 199.8 | Solar | 05_01_8W1 | 08/07/2018 | 08/22/2018 | 10 | 0 | 10 | 08/23/2018 | 08/23/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 | 08/07/2018 | 2/17/2021 | Y | EXP | 433 | 12/21/2019 | 03/01/2021 | 437 | 268 | 169 |  |  | 3/16/2021 | Connected |  | N
National Grid | LAWRENCE | 174744 | 01840 | 2000 | Solar | 05_05_28W40 | 07/02/2013 | 07/02/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/12/2013 | 08/09/2013 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2014 | 07/02/2013 | 6/30/2014 | Y | STD | 88 | 03/10/2015 | 04/02/2015 | 16 | 0 | 16 | 4/30/2015 | 4/30/2015 | 5/7/2015 | Connected |  | N
National Grid | DRACUT | 177725 | 01826 | 4982 | Solar | 05_05_320W2 | 10/04/2017 | 10/04/2017 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 | 12/07/2017 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2018 |  | 4/5/2019 | N | STD | 332 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 646626 | 01463 | 170 | Solar | 05_12_49W6 | 11/04/2024 | 12/13/2024 | 26 | 17 | 9 | 12/16/2024 | 12/16/2024 | 55 | 31 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2025 | 11/04/2024 | 9/28/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | CHARLTON | 343183 | 01507 | 9.6 | Solar | 05_14_24L2 | 02/21/2021 | 02/22/2021 | 0 | 0 | 0 | 02/23/2021 | 02/23/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 |  | 2/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2021 | Connected |  | N
National Grid | BROOKFIELD | 284117 | 01506 | 11.4 | Solar | 05_14_56L2 | 03/17/2020 |  | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 633921 | 01607 | 10 | Solar | 05_14_6J5 | 08/20/2024 | 08/30/2024 | 6 | 0 | 6 | 09/03/2024 | 09/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/20/2024 | 9/17/2025 | Y | EXP | 365 | 12/11/2024 | 02/25/2025 | 77 | 0 | 77 |  |  | 2/28/2025 | Connected |  | N
National Grid | FALL RIVER | 660373 | 02720 | 7.6 | Solar | 05_14_78L3 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 440673 | 01516 | 9.28 | Solar | 05_01_226L2 | 06/30/2022 | 07/01/2022 | 1 | 0 | 1 | 07/05/2022 | 07/05/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 671401 | 01970 | 23 | Solar | 05_01_406L1 | 02/11/2025 | 02/14/2025 | 4 | 1 | 3 | 02/18/2025 | 02/18/2025 | 123 | 102 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 670491 | 01824 | 15.04 | Solar | 05_01_525L2 | 02/06/2025 | 06/09/2025 | 11 | 6 | 5 | 06/10/2025 | 06/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | ANDOVER | 206477 | 01845 | 360 | Solar | 05_01_8W1 | 03/21/2019 | 04/02/2019 | 8 | 7 | 1 | 04/03/2019 | 04/03/2019 | 35 | 21 | 14 | 10/16/2019 | 01/23/2020 | 67 | 50 | 17 |  |  | 0 | 0 | 0 | 01/23/2020 | 67 | 50 | 17 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175033 | 01841 | 900 | Wind | 05_05_28W40 | 03/25/2013 | 03/25/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2013 | 06/14/2013 | 49 | 0 | 49 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2014 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 178465 | 01826 | 1750 | Solar | 05_05_320W2 | 01/22/2018 | 01/22/2018 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/12/2018 | 05/05/2018 | 40 | 19 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/28/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 707425 | 01463 | 50 | Solar | 05_12_49W6 | 08/01/2025 | 08/08/2025 | 4 | 2 | 2 | 08/11/2025 | 08/11/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 344721 | 01507 | 11.4 | Solar | 05_14_24L2 | 03/02/2021 | 03/03/2021 | 0 | 0 | 0 | 03/04/2021 | 03/04/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 3/2/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 285219 | 01506 | 23.78 | Solar | 05_14_56L2 | 03/25/2020 | 04/01/2020 | 4 | 0 | 4 | 04/02/2020 | 04/02/2020 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2020 | Connected |  | N
National Grid | WORCESTER | 643271 | 01607 | 10 | Solar | 05_14_6J5 | 09/27/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | FALL RIVER | 662183 | 02720 | 3.8 | Solar | 05_14_78L3 | 12/23/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 473320 | 01516 | 3.48 | Solar | 05_01_226L2 | 11/18/2022 | 11/22/2022 | 2 | 0 | 2 | 11/23/2022 | 11/23/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 | 11/18/2022 | 4/19/2024 | Y | EXP | 365 | 04/12/2023 | 04/19/2023 | 8 | 0 | 8 |  |  | 6/23/2023 | Connected |  | N
National Grid | SALEM | 676130 | 01970 | 20 | Solar | 05_01_406L1 | 03/07/2025 | 03/17/2025 | 6 | 0 | 6 | 03/18/2025 | 03/18/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 676836 | 01824 | 15.2 | Solar | 05_01_525L2 | 03/10/2025 | 03/26/2025 | 5 | 1 | 4 | 05/19/2025 | 05/19/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | ANDOVER | 307513 | 01845 | 3.8 | Solar | 05_01_8W1 | 10/21/2020 | 10/26/2020 | 2 | 0 | 2 | 10/27/2020 | 10/27/2020 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 228014 | 01841 | 10 | Solar | 05_05_28W40 | 06/21/2019 | 07/03/2019 | 7 | 7 | 0 | 07/05/2019 | 07/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 06/21/2019 | 10/10/2019 | Y | EXP | 84 | 08/30/2019 | 09/13/2019 | 14 | 0 | 14 |  |  | 9/23/2019 | Connected |  | N
National Grid | DRACUT | 178564 | 01826 | 4998 | Solar | 05_05_320W2 | 04/05/2018 | 04/05/2018 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2018 | 09/06/2018 | 74 | 66 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2019 |  | 4/11/2020 | N | STD | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 707396 | 01463 | 67.3 | Solar | 05_12_49W6 | 08/01/2025 | 09/10/2025 | 27 | 18 | 9 | 09/11/2025 | 09/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | OXFORD | 379424 | 01537 | 7.6 | Solar | 05_14_24L2 | 09/21/2021 | 12/16/2021 | 3 | 0 | 3 | 09/27/2021 | 09/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 315160 | 01585 | 15.2 | Solar | 05_14_56L2 | 09/25/2020 | 10/01/2020 | 3 | 0 | 3 | 10/02/2020 | 10/02/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2021 | Connected |  | N
National Grid | WORCESTER | 648222 | 01607 | 10 | Solar | 05_14_6J5 | 10/30/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 | 10/30/2024 | 1/3/2026 | Y | EXP | 365 | 04/15/2025 | 05/06/2025 | 22 | 0 | 22 |  |  | 5/23/2025 | Connected |  | N
National Grid | FALL RIVER | 668197 | 02720 | 7.68 | Solar | 05_14_78L3 | 02/03/2025 | 02/25/2025 | 2 | 0 | 2 | 02/26/2025 | 02/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | DOUGLAS | 478031 | 01516 | 4.64 | Solar | 05_01_226L2 | 12/15/2022 | 12/20/2022 | 3 | 0 | 3 | 12/21/2022 | 12/21/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 3/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2023 | Connected |  | N
National Grid | SALEM | 703419 | 01970 | 7.6 | Solar | 05_01_406L1 | 07/10/2025 | 07/23/2025 | 3 | 0 | 3 | 08/01/2025 | 08/01/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 | 07/10/2025 | 9/8/2026 | Y | EXP | 365 | 11/14/2025 | 12/02/2025 | 19 | 0 | 19 |  |  | 12/4/2025 | Connected |  | N
National Grid | CHELMSFORD | 705957 | 01824 | 4980 | Solar | 05_01_525L2 | 08/26/2025 | 09/05/2025 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/08/2025 | 09/26/2025 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 360536 | 01845 | 7.6 | Solar | 05_01_8W1 | 06/17/2021 | 06/21/2021 | 2 | 0 | 2 | 06/22/2021 | 06/22/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2021 |  | 8/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 225621 | 01841 | 233.3 | Solar | 05_05_28W40 | 06/29/2020 | 07/06/2020 | 5 | 4 | 1 | 07/07/2020 | 07/07/2020 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2020 |  | 8/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2021 | Connected |  | N
National Grid | DRACUT | 178647 | 01826 | 1750 | Solar | 05_05_320W2 | 12/15/2017 | 12/15/2017 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 727468 | 01463 | 84.6 | Solar | 05_12_49W6 | 10/20/2025 | 11/10/2025 | 15 | 6 | 9 | 11/12/2025 | 11/12/2025 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2026 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHARLTON | 408495 | 01507 | 0 | Solar | 05_14_24L2 | 11/29/2022 |  | 220 | 204 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 319343 | 01585 | 15.2 | Solar | 05_14_56L2 | 10/14/2020 | 10/15/2020 | 0 | 0 | 0 | 10/16/2020 | 10/16/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 | 10/14/2020 | 10/15/2021 | Y | EXP | 365 | 01/22/2021 | 02/04/2021 | 13 | 0 | 13 |  |  | 6/7/2021 | Connected |  | N
National Grid | WORCESTER | 660639 | 01610 | 7.6 | Solar | 05_14_6J5 | 12/13/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | FALL RIVER | 668055 | 02720 | 5.76 | Solar | 05_14_78L3 | 01/27/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 488269 | 01516 | 20.591 | Solar | 05_01_226L2 | 12/27/2022 |  | 42 | 41 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 724654 | 01970 | 23 | Solar | 05_01_406L1 | 10/07/2025 | 10/13/2025 | 3 | 0 | 3 | 10/14/2025 | 10/14/2025 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2026 | Connected |  | N
National Grid | CHELMSFORD | 713186 | 01824 | 10 | Solar | 05_01_525L2 | 08/19/2025 |  | 86 | 27 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 396740 | 01845 | 3486 | Other | 05_01_8W1 | 07/07/2023 | 09/05/2023 | 41 | 31 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/06/2023 | 01/22/2024 | 93 | 75 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 388401 | 01841 | 15.2 | Solar | 05_05_28W40 | 10/13/2021 | 10/20/2021 | 5 | 5 | 0 | 10/21/2021 | 10/21/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 |  | 3/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | Y
National Grid | DRACUT | 178717 | 01826 | 1000 | Solar | 05_05_320W2 | 04/11/2018 | 04/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2018 | 05/25/2018 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 177085 | 01463 | 540 | Solar | 05_12_49W6 | 10/18/2016 | 10/18/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/10/2017 | 50 | 39 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 517472 | 01507 | 8.7 | Solar | 05_14_24L2 | 05/22/2023 | 05/26/2023 | 4 | 0 | 4 | 05/30/2023 | 05/30/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 |  | 7/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | Y
National Grid | BROOKFIELD | 327991 | 01506 | 7.6 | Solar | 05_14_56L2 | 11/24/2020 | 12/02/2020 | 4 | 0 | 4 | 12/03/2020 | 12/03/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2021 |  | 11/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2021 | Connected |  | N
National Grid | WORCESTER | 664939 | 01607 | 5.76 | Solar | 05_14_6J5 | 01/10/2025 | 01/22/2025 | 4 | 0 | 4 | 01/23/2025 | 01/23/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/10/2025 | 3/11/2026 | Y | EXP | 365 | 04/29/2025 | 05/06/2025 | 8 | 0 | 8 |  |  | 6/17/2025 | Connected |  | Y
National Grid | FALL RIVER | 685222 | 02720 | 6.282 | Solar | 05_14_78L3 | 04/15/2025 | 04/23/2025 | 5 | 0 | 5 | 04/24/2025 | 04/24/2025 | 65 | 49 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 498726 | 01516 | 12.47 | Solar | 05_01_226L2 | 02/02/2023 | 02/06/2023 | 2 | 0 | 2 | 02/07/2023 | 02/07/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2023 |  | 7/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2023 | Connected |  | Y
National Grid | SALEM | 679432 | 01970 | 0 | Battery Add-On | 05_01_406L2 | 04/14/2025 | 04/25/2025 | 7 | 3 | 4 | 04/28/2025 | 04/28/2025 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHELMSFORD | 719575 | 01824 | 7.6 | Solar | 05_01_525L2 | 10/06/2025 | 11/18/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 27 | 11 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2026 | Connected |  | N
National Grid | ANDOVER | 396738 | 01845 | 0 | Other | 05_01_8W1 | 07/13/2022 | 08/16/2022 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2022 | 09/13/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 531727 | 01841 | 9.984 | Solar | 05_05_28W40 | 06/08/2023 | 06/14/2023 | 4 | 1 | 3 | 06/15/2023 | 06/15/2023 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 | 06/08/2023 | 8/17/2024 | Y | EXP | 365 | 08/31/2023 | 09/02/2023 | 3 | 0 | 3 |  |  | 11/15/2023 | Connected |  | N
National Grid | DRACUT | 178716 | 01826 | 250 | Solar | 05_05_320W2 | 04/11/2018 | 04/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2018 | 05/07/2018 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 177244 | 01463 | 191 | Solar | 05_12_49W6 | 02/06/2017 | 02/06/2017 | 4 | 0 | 4 | 02/10/2017 | 02/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2017 |  | 2/11/2018 | N | EXP | 361 | 07/27/2017 | 07/31/2017 | 2 | 0 | 2 | 10/5/2017 | 10/5/2017 | 10/18/2017 | Connected |  | N
National Grid | OXFORD | 566273 | 01537 | 4.095 | Solar | 05_14_24L2 | 10/31/2023 | 11/02/2023 | 2 | 0 | 2 | 11/03/2023 | 11/03/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 | 10/31/2023 | 12/26/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | WEST BROOKFIELD | 335404 | 01585 | 9.36 | Solar | 05_14_56L2 | 01/06/2021 | 01/25/2021 | 12 | 12 | 0 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/06/2021 | 1/24/2022 | Y | EXP | 365 | 05/12/2021 | 06/02/2021 | 21 | 0 | 21 |  |  | 7/23/2021 | Connected |  | N
National Grid | WORCESTER | 177071 | 01607 | 90 | Solar | 05_14_6J6 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2016 |  | 8/7/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 4/25/2017 | 4/25/2017 | 4/25/2017 | Connected |  | N
National Grid | FALL RIVER | 714136 | 02720 | 7.6 | Solar | 05_14_78L3 | 08/22/2025 | 10/02/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 79 | 65 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 559025 | 01516 | 9.57 | Solar | 05_01_226L2 | 09/29/2023 | 10/12/2023 | 9 | 8 | 1 | 10/13/2023 | 10/13/2023 | 75 | 52 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | SALEM | 684121 | 01970 | 11.4 | Solar | 05_01_406L2 | 04/14/2025 | 04/18/2025 | 4 | 0 | 4 | 04/22/2025 | 04/22/2025 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHELMSFORD | 492345 | 01824 | 5000 | Solar | 05_01_552L1 | 02/24/2023 | 03/21/2023 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/22/2023 | 05/16/2023 | 39 | 24 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ANDOVER | 396692 | 01845 | 0 | Other | 05_01_8W1 | 09/19/2022 | 10/24/2022 | 24 | 13 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2022 | 11/10/2022 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 599193 | 01841 | 7.6 | Solar | 05_05_28W40 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 9 | 4 | 5 | 05/03/2024 | 05/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 05/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 6/13/2025 | N | EXP | 365 | 07/15/2024 | 08/08/2024 | 25 | 0 | 25 |  |  | 8/28/2024 | Connected |  | N
National Grid | DRACUT | 178715 | 01826 | 1000 | Solar | 05_05_320W2 | 04/11/2018 | 04/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2018 | 05/10/2018 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 273131 | 01463 | 0 | Solar | 05_12_49W6 | 01/14/2020 | 01/14/2020 | 0 | 0 | 0 | 01/15/2020 | 01/15/2020 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2020 |  | 1/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2020 | Connected |  | N
National Grid | AUBURN | 638354 | 01501 | 15.356 | Solar | 05_14_24L2 | 09/13/2024 | 09/18/2024 | 3 | 0 | 3 | 09/19/2024 | 09/19/2024 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/13/2024 | 11/1/2025 | Y | EXP | 365 | 12/18/2024 | 03/05/2025 | 78 | 0 | 78 |  |  | 3/11/2025 | Connected |  | N
National Grid | BROOKFIELD | 347328 | 01506 | 0 | Solar | 05_14_56L2 | 03/17/2021 | 03/18/2021 | 0 | 0 | 0 | 03/19/2021 | 03/19/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 | 03/17/2021 | 3/17/2022 | Y | EXP | 365 | 05/26/2021 | 07/13/2021 | 48 | 0 | 48 |  |  | 7/30/2021 | Connected |  | N
National Grid | WORCESTER | 600180 | 01607 | 6 | Solar | 05_14_6J6 | 04/06/2024 | 04/09/2024 | 2 | 0 | 2 | 04/10/2024 | 04/10/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  | 4/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2024 | Connected |  | N
National Grid | FALL RIVER | 718161 | 02720 | 11.375 | Solar | 05_14_78L3 | 09/10/2025 | 09/24/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | DOUGLAS | 559004 | 01516 | 30 | Solar | 05_01_226L2 | 09/29/2023 | 10/06/2023 | 5 | 4 | 1 | 10/10/2023 | 10/10/2023 | 117 | 92 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 09/29/2023 | 4/9/2025 | Y | EXP | 365 | 08/21/2024 | 10/17/2024 | 58 | 0 | 58 |  |  | 10/23/2024 | Connected |  | N
National Grid | SALEM | 726973 | 01970 | 7.6 | Solar | 05_01_406L2 | 10/16/2025 | 11/13/2025 | 5 | 0 | 5 | 01/06/2026 | 01/06/2026 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 3/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHELMSFORD | 661587 | 01824 | 3.8 | Solar | 05_01_552L1 | 12/19/2024 | 01/14/2025 | 5 | 0 | 5 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 12/19/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 398501 | 01845 | 9.8 | Solar | 05_01_8W1 | 02/03/2022 | 05/13/2022 | 3 | 3 | 0 | 05/16/2022 | 05/16/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 | 02/03/2022 | 8/12/2023 | Y | EXP | 365 | 07/15/2022 | 08/11/2022 | 28 | 0 | 28 |  |  | 9/6/2022 | Connected |  | N
National Grid | LAWRENCE | 600530 | 01841 | 7.6 | Solar | 05_05_28W40 | 03/29/2024 | 06/25/2024 | 5 | 1 | 4 | 06/26/2024 | 06/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | DRACUT | 178714 | 01826 | 500 | Solar | 05_05_320W2 | 04/11/2018 | 04/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2018 | 05/25/2018 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 277189 | 01463 | 3.36 | Solar | 05_12_49W6 | 04/27/2020 | 04/30/2020 | 2 | 0 | 2 | 05/01/2020 | 05/01/2020 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 656616 | 01501 | 9.28 | Solar | 05_14_24L2 | 11/25/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | Y
National Grid | SPENCER | 363866 | 01562 | 9.8 | Solar | 05_14_56L2 | 06/15/2021 | 06/17/2021 | 2 | 0 | 2 | 06/18/2021 | 06/18/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2021 |  | 8/26/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2022 | Connected |  | N
National Grid | WORCESTER | 646983 | 01607 | 7.6 | Solar | 05_14_6J6 | 11/22/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/22/2024 | 1/28/2026 | Y | EXP | 365 | 08/26/2025 | 09/17/2025 | 23 | 0 | 23 |  |  | 9/23/2025 | Connected |  | N
National Grid | FALL RIVER | 723653 | 02720 | 3.8 | Solar | 05_14_78L9 | 10/03/2025 | 10/13/2025 | 5 | 1 | 4 | 10/14/2025 | 10/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DOUGLAS | 550348 | 01516 | 0 | Solar | 05_01_226L2 | 08/24/2023 | 08/25/2023 | 1 | 0 | 1 | 08/28/2023 | 08/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 | 08/24/2023 | 11/10/2024 | Y | EXP | 365 | 06/04/2024 | 06/03/2024 | 0 | 0 | 0 |  |  | 6/3/2024 | Connected |  | N
National Grid | SALEM | 174703 | 01970 | 492 | Solar | 05_01_406L2 | 06/10/2013 | 06/10/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2013 | 07/22/2013 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 06/10/2013 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | CHELMSFORD | 694028 | 01824 | 5.76 | Solar | 05_01_552L1 | 05/29/2025 | 08/13/2025 | 51 | 47 | 4 | 08/14/2025 | 08/14/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 | 05/29/2025 | 12/4/2026 | Y | EXP | 365 | 03/10/2026 |  | 23 | 0 | 23 |  |  |  | Construction |  | N
National Grid | ANDOVER | 408866 | 01845 | 0 | Battery Add-On | 05_01_8W1 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 09/02/2022 | 135 | 129 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 604010 | 01841 | 497.5 | Solar | 05_05_28W40 | 04/18/2024 | 05/24/2024 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2024 | 07/17/2024 | 36 | 25 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 178713 | 01826 | 1000 | Solar | 05_05_320W2 | 04/11/2018 | 04/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2018 | 05/25/2018 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 296513 | 01463 | 3.36 | Solar | 05_12_49W6 | 07/13/2020 | 07/17/2020 | 3 | 0 | 3 | 07/20/2020 | 07/20/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 687682 | 01501 | 15.2 | Solar | 05_14_24L2 | 04/25/2025 | 04/29/2025 | 2 | 0 | 2 | 04/30/2025 | 04/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2025 | Connected |  | N
National Grid | SPENCER | 385253 | 01562 | 9.8 | Solar | 05_14_56L2 | 09/29/2021 | 10/04/2021 | 4 | 3 | 1 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  | 11/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2022 | Connected |  | N
National Grid | AUBURN | 500858 | 01501 | 60 | Solar | 05_14_6J8 | 02/24/2023 |  | 257 | 163 | 94 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 730658 | 02720 | 11.5 | Solar | 05_14_78L9 | 10/31/2025 | 11/03/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 42 | 27 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DOUGLAS | 570251 | 01516 | 6 | Solar | 05_01_226L2 | 12/18/2023 | 01/02/2024 | 9 | 3 | 6 | 01/03/2024 | 01/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 | 12/18/2023 | 7/31/2025 | Y | EXP | 535 | 05/24/2024 | 08/28/2024 | 97 | 0 | 97 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 175330 | 01970 | 996 | Solar | 05_01_406L2 | 11/11/2014 | 11/11/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/01/2014 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 11/11/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | CHELMSFORD | 705952 | 01824 | 996 | Solar | 05_01_552L1 | 08/14/2025 | 09/02/2025 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2025 | 10/16/2025 | 30 | 15 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ANDOVER | 559181 | 01845 | 10 | Solar | 05_01_8W1 | 10/09/2023 | 10/13/2023 | 5 | 4 | 1 | 10/16/2023 | 10/16/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 10/09/2023 | 12/23/2024 | Y | EXP | 365 | 01/12/2024 | 01/18/2024 | 7 | 0 | 7 |  |  | 3/6/2024 | Connected |  | N
National Grid | LAWRENCE | 607518 | 01841 | 5.76 | Solar | 05_05_28W40 | 04/29/2024 | 05/14/2024 | 3 | 0 | 3 | 05/15/2024 | 05/15/2024 | 54 | 45 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 04/29/2024 | 8/20/2025 | Y | EXP | 365 | 10/12/2024 | 01/17/2025 | 98 | 0 | 98 |  |  | 1/24/2025 | Connected |  | Y
National Grid | DRACUT | 178712 | 01826 | 4998 | Solar | 05_05_320W2 | 04/12/2018 | 04/12/2018 | 14 | 1 | 13 |  |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 | 04/12/2018 | 1/26/2022 | Y | STD | 455 | 06/09/2021 | 12/28/2021 | 203 | 7 | 196 |  |  | 1/24/2022 | Connected |  | N
National Grid | PEPPERELL | 302107 | 01463 | 86.4 | Solar | 05_12_49W6 | 07/21/2020 | 07/29/2020 | 5 | 0 | 5 | 07/30/2020 | 07/30/2020 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 |  | 1/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2021 | Connected |  | N
National Grid | OXFORD | 707310 | 01540 | 23 | Solar | 05_14_24L2 | 08/04/2025 | 08/06/2025 | 2 | 0 | 2 | 08/07/2025 | 08/07/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | SPENCER | 396669 | 01562 | 0 | Other | 05_14_56L2 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 03/02/2022 | 31 | 23 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 550550 | 01604 | 200 | Solar | 05_14_6J8 | 08/25/2023 | 09/08/2023 | 9 | 1 | 8 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2024 | 08/25/2023 | 6/1/2026 | Y | STD | 546 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 731066 | 02720 | 240 | Solar | 05_14_78L9 | 11/10/2025 | 12/09/2025 | 19 | 11 | 8 | 12/10/2025 | 12/10/2025 | 18 | 0 | 18 | 02/18/2026 |  | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | DOUGLAS | 599998 | 01516 | 3.8 | Solar | 05_01_226L2 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 | 04/01/2024 | 5/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | SALEM | 175412 | 01970 | 2000 | Solar | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 712983 | 01824 | 7.6 | Solar | 05_01_552L1 | 08/19/2025 | 10/02/2025 | 7 | 3 | 4 | 10/22/2025 | 10/22/2025 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 | 08/19/2025 | 12/4/2026 | Y | EXP | 365 | 02/03/2026 |  | 58 | 0 | 58 |  |  |  | Construction |  | N
National Grid | ANDOVER | 559088 | 01845 | 10 | Solar | 05_01_8W1 | 10/03/2023 | 10/06/2023 | 3 | 0 | 3 | 10/10/2023 | 10/10/2023 | 106 | 28 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 621029 | 01841 | 6.08 | Solar | 05_05_28W40 | 06/27/2024 | 07/25/2024 | 14 | 12 | 2 | 07/26/2024 | 07/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 178711 | 01826 | 250 | Solar | 05_05_320W2 | 04/11/2018 | 05/23/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 342002 | 01463 | 40 | Solar | 05_12_49W6 | 03/30/2021 | 04/22/2021 | 14 | 9 | 5 | 04/23/2021 | 04/23/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2021 |  | 7/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2021 | Connected |  | N
National Grid | OXFORD | 725617 | 01540 | 7.6 | Solar | 05_14_24L2 | 11/03/2025 | 11/05/2025 | 2 | 0 | 2 | 11/06/2025 | 11/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2026 | Connected |  | N
National Grid | SPENCER | 579731 | 01562 | 7.6 | Solar | 05_14_6J8 | 12/29/2023 | 01/16/2024 | 11 | 8 | 3 | 01/17/2024 | 01/17/2024 | 33 | 12 | 21 | 04/24/2024 | 05/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 05/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/9/2025 | N | EXP | 365 | 05/16/2024 | 06/12/2024 | 28 | 0 | 28 |  |  | 7/6/2024 | Connected |  | N
National Grid | WORCESTER | 749121 | 01607 | 10 | Solar | 05_14_78L9 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 03/06/2026 | 03/06/2026 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 615849 | 02720 | 3.8 | Solar | 05_01_226L2 | 06/05/2024 | 06/06/2024 | 2 | 0 | 2 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2024 | 06/05/2024 | 1/21/2026 | Y | EXP | 365 | 03/06/2025 |  | 392 | 0 | 392 |  |  | 3/18/2025 | Connected |  | N
National Grid | DOUGLAS | 175411 | 01516 | 1992 | Solar | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | SALEM | 741140 | 01970 | 5.76 | Solar | 05_01_552L1 | 12/18/2025 | 12/19/2025 | 3 | 0 | 3 | 01/16/2026 | 01/16/2026 | 34 | 23 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHELMSFORD | 568724 | 01824 | 7.6 | Solar | 05_01_8W1 | 11/10/2023 | 11/15/2023 | 3 | 1 | 2 | 11/16/2023 | 11/16/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2023 |  | 5/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2024 | Connected |  | N
National Grid | ANDOVER | 636299 | 01845 | 6 | Solar | 05_05_28W40 | 08/29/2024 | 09/24/2024 | 1 | 0 | 1 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 185136 | 01841 | 4980 | Solar | 05_05_320W2 | 05/21/2018 | 05/21/2018 | 34 | 29 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/11/2018 | 09/12/2018 | 45 | 15 | 30 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2019 | 05/21/2018 | 1/8/2024 | Y | STD | 701 | 08/12/2022 | 07/19/2023 | 342 | 174 | 168 |  |  | 12/14/2023 | Connected |  | N
National Grid | DRACUT | 370832 | 01826 | 250 | Solar | 05_12_49W6 | 08/06/2021 | 08/20/2021 | 10 | 0 | 10 |  |  | 30 | 3 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 | 08/06/2021 | 8/1/2023 | Y | STD | 41 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | PEPPERELL | 746949 | 01463 | 0 | Other | 05_14_24L3 | 03/03/2026 |  | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | OXFORD | 421208 | 01540 | 15.2 | Solar | 05_14_56L2 | 05/04/2022 | 05/10/2022 | 4 | 0 | 4 | 05/11/2022 | 05/11/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 |  | 6/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2023 | Connected |  | Y
National Grid | SPENCER | 594507 | 01562 | 3.8 | Solar | 05_14_6J8 | 03/07/2024 | 03/12/2024 | 3 | 0 | 3 | 03/13/2024 | 03/13/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175382 | 01607 | 18 | Solar | 05_14_78L9 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2014 |  | 9/30/2014 | N | EXP | 49 |  |  | 0 | 0 | 0 | 9/12/2014 | 9/12/2014 | 10/31/2014 | Connected |  | N
National Grid | FALL RIVER | 619525 | 02720 | 7.6 | Solar | 05_01_226L2 | 06/20/2024 | 06/25/2024 | 3 | 1 | 2 | 10/29/2024 | 10/29/2024 | 37 | 16 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 175410 | 01516 | 1992 | Solar | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  | 12/1/2016 | Connected |  | N
National Grid | SALEM | 743429 | 01970 | 9 | Solar | 05_01_552L1 | 01/05/2026 | 01/29/2026 | 17 | 17 | 0 | 01/30/2026 | 01/30/2026 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHELMSFORD | 571635 | 01824 | 6 | Solar | 05_01_8W1 | 12/04/2023 | 12/05/2023 | 1 | 0 | 1 | 12/06/2023 | 12/06/2023 | 45 | 21 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 | 12/04/2023 | 5/10/2025 | Y | EXP | 365 | 06/08/2024 | 07/17/2024 | 40 | 0 | 40 |  |  | 9/11/2024 | Connected |  | N
National Grid | ANDOVER | 642560 | 01845 | 10 | Solar | 05_05_28W40 | 09/30/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 185462 | 01841 | 15.2 | Solar | 05_05_320W2 | 05/22/2018 | 05/22/2018 | 11 | 8 | 3 | 06/14/2018 | 06/14/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 7/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2019 | Connected |  | N
National Grid | DRACUT | 647135 | 01826 | 7.6 | Solar | 05_12_49W6 | 10/29/2024 | 10/31/2024 | 17 | 15 | 2 | 01/30/2025 | 01/30/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 748273 | 01463 | 150 | Solar | 05_14_24L3 | 02/18/2026 | 03/11/2026 | 13 | 7 | 6 | 03/12/2026 | 03/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | OXFORD | 446210 | 01540 | 15.2 | Solar | 05_14_56L2 | 07/22/2022 | 07/22/2022 | 0 | 0 | 0 | 07/25/2022 | 07/25/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 |  | 8/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2023 | Connected |  | N
National Grid | SPENCER | 637388 | 01562 | 7.6 | Solar | 05_14_6J8 | 09/03/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175670 | 01607 | 7.6 | Solar | 05_14_78L9 | 10/21/2014 | 10/21/2014 | 6 | 0 | 6 | 10/30/2014 | 10/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2014 | 10/21/2014 | 12/31/2016 | Y | EXP | 766 | 06/24/2016 | 06/24/2016 | 0 | 0 | 0 | 2/26/2015 | 2/26/2015 | 8/17/2016 | Connected |  | N
National Grid | FALL RIVER | 629731 | 02720 | 10 | Solar | 05_01_226L2 | 08/02/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/02/2024 | 9/11/2025 | Y | EXP | 365 | 10/24/2024 | 11/08/2024 | 16 | 0 | 16 |  |  | 12/21/2024 | Connected |  | N
National Grid | DOUGLAS | 175409 | 01516 | 996 | Solar | 05_01_406L2 | 03/04/2014 | 03/04/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/04/2014 | 9/14/2016 | Y | STD | 532 | 06/27/2016 | 12/20/2016 | 121 | 0 | 121 |  |  | 11/23/2016 | Connected |  | N
National Grid | SALEM | 756834 | 01970 |  | Battery Add-On | 05_01_552L1 | 03/16/2026 | 03/23/2026 | 1 | 0 | 1 | 03/27/2026 | 03/27/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHELMSFORD | 609603 | 01824 | 10 | Solar | 05_01_8W1 | 05/08/2024 | 05/16/2024 | 1 | 0 | 1 | 05/17/2024 | 05/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 |  | 6/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2024 | Connected |  | N
National Grid | ANDOVER | 646767 | 01845 | 10 | Solar | 05_05_28W40 | 10/14/2024 | 12/04/2024 | 3 | 0 | 3 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | LAWRENCE | 296412 | 01841 | 10 | Solar | 05_05_320W2 | 06/16/2020 | 06/18/2020 | 1 | 1 | 0 | 06/19/2020 | 06/19/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2020 | 06/16/2020 | 6/16/2021 | Y | EXP | 365 | 08/20/2020 | 09/15/2020 | 26 | 0 | 26 |  |  | 1/29/2021 | Connected |  | N
National Grid | DRACUT | 657099 | 01826 | 75 | Solar | 05_12_49W6 | 12/11/2024 | 01/17/2025 | 25 | 16 | 9 | 01/21/2025 | 01/21/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 9/19/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | PEPPERELL | 174751 | 01463 | 150 | Solar | 05_14_24L3 | 07/09/2013 | 07/09/2013 | 18 | 10 | 8 | 08/05/2013 | 08/05/2013 | 568 | 39 | 529 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2013 |  | 9/30/2014 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 466523 | 01540 | 6 | Solar | 05_14_56L2 | 10/06/2022 | 10/12/2022 | 3 | 1 | 2 | 10/13/2022 | 10/13/2022 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2022 | 10/06/2022 | 11/10/2023 | Y | EXP | 365 | 12/21/2022 | 12/21/2022 | 1 | 0 | 1 |  |  | 4/14/2023 | Connected |  | N
National Grid | SPENCER | 673283 | 01562 | 6.825 | Solar | 05_14_6J8 | 02/20/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | WORCESTER | 176654 | 01604 | 7.6 | Solar | 05_14_78L9 | 04/15/2016 | 04/15/2016 | 1 | 1 | 0 | 04/20/2016 | 04/20/2016 | 198 | 0 | 198 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 4/24/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 644163 | 02720 | 5.76 | Solar | 05_01_226L2 | 10/01/2024 | 10/28/2024 | 4 | 1 | 3 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 10/01/2024 | 12/19/2025 | Y | EXP | 365 | 01/16/2025 | 02/11/2025 | 27 | 0 | 27 |  |  | 2/19/2025 | Connected |  | N
National Grid | DOUGLAS | 175408 | 01516 | 2000 | Solar | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 | 06/27/2016 | 12/20/2016 | 121 | 0 | 121 |  |  | 11/23/2016 | Connected |  | N
National Grid | SALEM | 758944 | 01970 | 15.2 | Solar | 05_01_552L1 | 03/26/2026 |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | CHELMSFORD | 616890 | 01824 | 5.76 | Solar | 05_01_8W1 | 06/10/2024 | 06/21/2024 | 1 | 0 | 1 | 06/24/2024 | 06/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | ANDOVER | 649643 | 01845 | 5.76 | Solar | 05_05_28W40 | 10/24/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 371684 | 01844 | 1000 | Solar | 05_05_320W2 | 10/15/2021 | 01/04/2022 | 55 | 46 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 11/22/2022 | 220 | 211 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 708169 | 01826 | 17.101 | Solar | 05_12_49W6 | 08/22/2025 | 08/28/2025 | 4 | 0 | 4 | 08/29/2025 | 08/29/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | PEPPERELL | 175758 | 01463 | 150 | Solar | 05_14_24L3 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 113 | 03/06/2015 | 05/06/2015 | 41 | 0 | 41 | 6/1/2015 | 6/1/2015 | 6/1/2015 | Connected |  | N
National Grid | OXFORD | 529680 | 01540 | 7.875 | Solar | 05_14_56L2 | 06/20/2023 | 06/29/2023 | 21 | 16 | 5 | 06/30/2023 | 06/30/2023 | 17 | 0 | 17 | 09/29/2023 | 11/01/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 11/01/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 10/13/2023 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 547089 | 01562 | 240 | Solar | 05_14_70L1 | 12/12/2023 | 02/05/2024 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2024 | 02/20/2024 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2025 | 12/12/2023 | 8/16/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 176709 | 01607 | 3.8 | Solar | 05_14_78L9 | 10/28/2015 | 10/28/2015 | 3 | 3 | 0 | 11/03/2015 | 11/03/2015 | 366 | 0 | 366 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2015 |  | 11/3/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 648356 | 02720 | 3.8 | Solar | 05_01_226L2 | 10/30/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 10/30/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | DOUGLAS | 175667 | 01516 | 470 | Solar | 05_01_406L2 | 08/08/2014 | 08/08/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 08/08/2014 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | SALEM | 174248 | 01970 | 1000 | Solar | 05_01_552L1 | 02/23/2012 | 02/23/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2012 | 10/01/2012 | 127 | 0 | 127 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/6/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 619190 | 01824 | 5.76 | Solar | 05_01_8W1 | 06/20/2024 | 07/03/2024 | 1 | 0 | 1 | 07/05/2024 | 07/05/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 660889 | 01845 | 10 | Solar | 05_05_28W40 | 12/16/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2025 | Connected |  | N
National Grid | LAWRENCE | 398313 | 01841 | 9.772 | Solar | 05_05_320W2 | 12/03/2021 | 12/07/2021 | 3 | 1 | 2 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  | 1/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2022 | Connected |  | N
National Grid | DRACUT | 591000 | 01826 | 10 | Solar | 05_12_4J2 | 03/06/2024 | 03/08/2024 | 2 | 0 | 2 | 03/11/2024 | 03/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 199628 | 01463 | 3.8 | Solar | 05_14_24L3 | 10/29/2018 | 12/18/2018 | 25 | 24 | 1 | 12/19/2018 | 12/19/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2019 |  | 10/11/2019 | N | EXP | 238 |  |  | 0 | 0 | 0 |  |  | 8/27/2019 | Connected |  | N
National Grid | OXFORD | 572842 | 01540 | 250 | Solar | 05_14_56L2 | 12/07/2023 | 02/04/2024 | 38 | 29 | 9 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 742796 | 01562 | 5.76 | Solar | 05_14_70L1 | 01/09/2026 | 01/12/2026 | 38 | 24 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WORCESTER | 177476 | 01604 | 10 | Solar | 05_14_78L9 | 07/06/2016 | 07/06/2016 | 1 | 1 | 0 | 07/08/2016 | 07/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 | 07/06/2016 | 12/12/2017 | Y | EXP | 511 | 05/16/2017 | 06/05/2017 | 13 | 0 | 13 | 7/28/2017 | 7/28/2017 | 7/28/2017 | Connected |  | N
National Grid | FALL RIVER | 650386 | 02720 | 8.45 | Solar | 05_01_226L2 | 10/29/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/29/2024 | 1/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | DOUGLAS | 175666 | 01516 | 996 | Solar | 05_01_406L2 | 08/08/2014 | 08/08/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 08/08/2014 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | SALEM | 174246 | 01970 | 1000 | Solar | 05_01_552L1 | 02/23/2012 | 02/23/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2012 | 10/01/2012 | 127 | 0 | 127 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/6/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 639442 | 01824 | 5.76 | Solar | 05_01_8W1 | 09/11/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 09/11/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | ANDOVER | 704820 | 01845 | 1.16 | Solar | 05_05_28W40 | 07/14/2025 | 09/22/2025 | 49 | 45 | 4 | 09/23/2025 | 09/23/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2025 | Connected |  | N
National Grid | TEWKSBURY | 470299 | 01876 | 8.12 | Solar | 05_05_320W2 | 11/10/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 |  | 12/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | DRACUT | 605660 | 01826 | 15.2 | Solar | 05_12_4J2 | 05/02/2024 | 05/10/2024 | 7 | 5 | 2 | 05/13/2024 | 05/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/02/2024 | 6/20/2025 | Y | EXP | 365 | 10/03/2024 | 12/18/2024 | 77 | 0 | 77 |  |  | 1/10/2025 | Connected |  | N
National Grid | PEPPERELL | 341279 | 01463 | 133.2 | Solar | 05_14_24L3 | 02/12/2021 | 03/04/2021 | 13 | 2 | 11 |  |  | 94 | 78 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 | 02/12/2021 | 7/31/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2023 | Connected |  | N
National Grid | OXFORD | 581516 | 01540 | 7.6 | Solar | 05_14_56L2 | 01/04/2024 | 01/23/2024 | 12 | 7 | 5 | 01/24/2024 | 01/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 751582 | 01562 | 6.282 | Solar | 05_14_70L1 | 02/18/2026 | 03/03/2026 | 8 | 6 | 2 | 03/04/2026 | 03/04/2026 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | AUBURN | 177689 | 01501 | 100 | Solar | 05_14_78L9 | 10/03/2017 | 10/03/2017 | 2 | 2 | 0 | 10/27/2017 | 10/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2017 |  | 10/8/2018 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | FALL RIVER | 651609 | 02720 | 10 | Solar | 05_01_226L2 | 11/13/2024 | 12/13/2024 | 2 | 0 | 2 | 12/16/2024 | 12/16/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/13/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | DOUGLAS | 175665 | 01516 | 996 | Solar | 05_01_406L2 | 08/08/2014 | 08/08/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 08/08/2014 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | LYNN | 174527 | 01902 | 1000 | Solar | 05_01_552L1 | 09/12/2011 | 09/12/2011 | 99 | 0 | 99 | 02/06/2012 | 02/06/2012 | 655 | 0 | 655 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 645066 | 01824 | 3.8 | Solar | 05_01_8W1 | 10/04/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | ANDOVER | 388520 | 01845 | 400 | Solar | 05_05_28W41 | 01/12/2022 | 04/13/2022 | 63 | 51 | 12 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 | 01/12/2022 | 6/6/2026 | Y | STD | 161 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 475577 | 01852 | 15.2 | Solar | 05_05_320W2 | 11/08/2022 | 11/09/2022 | 1 | 0 | 1 | 11/10/2022 | 11/10/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 1/16/2024 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 620144 | 01826 | 7.6 | Solar | 05_12_4J2 | 06/25/2024 | 07/10/2024 | 1 | 0 | 1 | 07/11/2024 | 07/11/2024 | 181 | 160 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 341278 | 01463 | 166.6 | Solar | 05_14_24L3 | 02/12/2021 | 03/04/2021 | 13 | 2 | 11 |  |  | 94 | 78 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 | 02/12/2021 | 6/14/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | N
National Grid | OXFORD | 600029 | 01540 | 0 | Battery Add-On | 05_14_56L2 | 03/27/2024 | 03/29/2024 | 2 | 0 | 2 | 04/01/2024 | 04/01/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2024 |  | 4/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2024 | Connected |  | N
National Grid | SPENCER | 756485 | 01562 | 5.76 | Solar | 05_14_70L1 | 03/13/2026 | 03/17/2026 | 2 | 0 | 2 | 03/18/2026 | 03/18/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 353172 | 01607 | 3.8 | Solar | 05_14_78L9 | 05/06/2021 | 05/12/2021 | 3 | 0 | 3 | 05/13/2021 | 05/13/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 653239 | 02720 | 10 | Solar | 05_01_226L2 | 11/14/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 175815 | 01516 | 360 | Solar | 05_01_406L2 | 07/27/2015 | 07/27/2015 | 2 | 2 | 0 | 07/30/2015 | 07/30/2015 | 625 | 0 | 625 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 |  | 8/24/2018 | N | EXP | 1120 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 174577 | 01902 | 3000 | Solar | 05_01_552L1 | 02/14/2011 | 02/14/2011 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2011 | 03/23/2011 | 12 | 0 | 12 |  | 0 | 0 | 0 | 02/01/2016 | 02/01/2016 | 0 | 0 | 0 | 2/28/2012 | 02/14/2011 | 12/31/2016 | Y | STD | 1768 | 11/29/2016 | 08/29/2017 | 188 | 0 | 188 | 3/10/2017 | 3/10/2017 | 3/10/2017 | Connected |  | N
National Grid | CHELMSFORD | 646909 | 01824 | 7.6 | Solar | 05_01_8W1 | 10/31/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/31/2024 | 1/17/2026 | Y | EXP | 365 | 02/15/2025 | 06/04/2025 | 110 | 0 | 110 |  |  | 6/24/2025 | Connected |  | N
National Grid | ANDOVER | 174436 | 01845 | 75 | Solar | 05_05_28W41 | 06/27/2012 | 06/27/2012 | 7 | 0 | 7 | 07/12/2012 | 07/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/22/2012 | N | EXP | 51 |  |  | 0 | 0 | 0 | 9/28/2012 | 9/28/2012 | 12/14/2012 | Connected |  | N
National Grid | LOWELL | 568589 | 01852 | 46 | Solar | 05_05_320W2 | 11/03/2023 | 11/14/2023 | 7 | 5 | 2 | 11/15/2023 | 11/15/2023 | 104 | 87 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 5/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | DRACUT | 643453 | 01826 | 5.8 | Solar | 05_12_4J2 | 09/27/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 107 | 83 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 341277 | 01463 | 180 | Solar | 05_14_24L3 | 02/12/2021 | 03/04/2021 | 13 | 2 | 11 |  |  | 94 | 78 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 | 02/12/2021 | 6/10/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | N
National Grid | OXFORD | 608440 | 01540 | 7.54 | Solar | 05_14_56L2 | 05/03/2024 | 06/26/2024 | 36 | 35 | 1 | 06/27/2024 | 06/27/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  | 8/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2024 | Connected |  | N
National Grid | SPENCER | 756406 | 01562 | 15.2 | Solar | 05_14_70L1 | 03/13/2026 | 03/18/2026 | 3 | 0 | 3 | 03/19/2026 | 03/19/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 557592 | 01604 | 7.6 | Solar | 05_14_78L9 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 654523 | 02720 | 23 | Battery Add-On | 05_01_226L2 | 11/14/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | DOUGLAS | 175945 | 01516 | 1000 | Solar | 05_01_406L2 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2015 | 02/27/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 174632 | 01902 | 1500 | Solar | 05_01_552L1 | 05/13/2013 | 05/13/2013 | 218 | 212 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/1/2014 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 651778 | 01824 | 10 | Solar | 05_01_8W1 | 11/13/2024 | 03/06/2025 | 59 | 53 | 6 | 03/07/2025 | 03/07/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | ANDOVER | 174539 | 01845 | 950 | Solar | 05_05_28W41 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 604715 | 01862 | 8.376 | Solar | 05_05_320W2 | 04/17/2024 | 05/06/2024 | 1 | 0 | 1 | 05/07/2024 | 05/07/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 |  | 5/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | DRACUT | 658811 | 01826 | 5.76 | Solar | 05_12_4J2 | 12/09/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 605610 | 01463 | 12.35 | Solar | 05_14_24L3 | 04/23/2024 | 05/15/2024 | 11 | 9 | 2 | 05/16/2024 | 05/16/2024 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 | 04/23/2024 | 6/7/2025 | Y | EXP | 365 | 07/02/2024 | 07/02/2024 | 1 | 0 | 1 |  |  | 8/8/2024 | Connected |  | N
National Grid | OXFORD | 645686 | 01540 | 23 | Solar | 05_14_56L2 | 10/09/2024 | 10/11/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/09/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 175483 | 01562 | 4999 | Solar | 05_14_70L1 | 03/14/2014 | 03/14/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2014 | 05/14/2014 | 33 | 0 | 33 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 537415 | 01607 | 8.064 | Solar | 05_14_78L9 | 07/07/2023 | 09/19/2023 | 51 | 50 | 1 | 09/20/2023 | 09/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 | 07/07/2023 | 1/22/2025 | Y | EXP | 365 | 03/14/2024 | 05/15/2024 | 63 | 0 | 63 |  |  | 5/23/2024 | Connected |  | N
National Grid | FALL RIVER | 654994 | 02720 | 5.76 | Solar | 05_01_226L2 | 12/02/2024 | 01/01/2025 | 10 | 4 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/02/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 176363 | 01516 | 7.6 | Solar | 05_01_406L2 | 03/08/2016 | 03/08/2016 | 3 | 3 | 0 | 03/15/2016 | 03/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2016 | 03/08/2016 | 1/15/2018 | Y | EXP | 656 | 05/19/2017 | 06/02/2017 | 9 | 0 | 9 | 8/11/2017 | 8/11/2017 | 8/11/2017 | Connected |  | N
National Grid | LYNN | 175566 | 01902 | 997.6 | Solar | 05_01_552L1 | 10/06/2014 | 10/06/2014 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 1 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2015 |  | 9/1/2016 | N | STD | 447 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 684478 | 01824 | 10 | Solar | 05_01_8W1 | 04/11/2025 | 05/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 31 | 17 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 | 04/11/2025 | 7/30/2026 | Y | EXP | 365 | 10/18/2025 | 10/30/2025 | 13 | 0 | 13 |  |  | 11/26/2025 | Connected |  | N
National Grid | ANDOVER | 174538 | 01845 | 950 | Solar | 05_05_28W41 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 620732 | 02072 | 7.68 | Solar | 05_05_320W2 | 06/26/2024 | 07/12/2024 | 1 | 0 | 1 | 07/15/2024 | 07/15/2024 | 28 | 14 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | DRACUT | 439647 | 01826 | 480 | Solar | 05_12_51L1 | 02/06/2023 | 02/16/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2023 | 03/21/2023 | 22 | 0 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 1/19/2027 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 656244 | 01463 | 5.76 | Solar | 05_14_24L3 | 11/22/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/22/2024 | 5/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2026 | Connected |  | N
National Grid | AUBURN | 652213 | 01501 | 7.6 | Solar | 05_14_56L2 | 11/14/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 175480 | 01562 | 4999 | Solar | 05_14_70L1 | 03/21/2014 | 03/21/2014 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2014 | 05/14/2014 | 26 | 0 | 26 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/21/2014 | 3/31/2015 | Y | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 596726 | 01604 | 10 | Solar | 05_14_78L9 | 04/15/2024 | 04/19/2024 | 5 | 4 | 1 | 04/22/2024 | 04/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 04/15/2024 | 6/15/2025 | Y | EXP | 365 | 08/01/2024 | 09/12/2024 | 43 | 0 | 43 |  |  | 10/17/2024 | Connected |  | N
National Grid | FALL RIVER | 660803 | 02720 | 5.76 | Solar | 05_01_226L2 | 12/18/2024 | 02/11/2025 | 22 | 18 | 4 | 02/12/2025 | 02/12/2025 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 176545 | 01516 | 10 | Solar | 05_01_406L2 | 03/31/2016 | 03/31/2016 | 2 | 2 | 0 | 04/05/2016 | 04/05/2016 | 208 | 0 | 208 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 |  | 4/6/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 175715 | 01902 | 1500 | Solar | 05_01_552L1 | 12/30/2014 | 12/30/2014 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2015 | 02/24/2015 | 22 | 0 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 684348 | 01824 | 3.19 | Solar | 05_01_8W1 | 04/10/2025 | 05/02/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2025 | Connected |  | N
National Grid | ANDOVER | 174537 | 01845 | 950 | Solar | 05_05_28W41 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 630622 | 01862 | 8.12 | Solar | 05_05_320W2 | 08/07/2024 | 08/15/2024 | 2 | 1 | 1 | 08/16/2024 | 08/16/2024 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/07/2024 | 9/4/2025 | Y | EXP | 365 | 02/28/2025 | 03/04/2025 | 5 | 0 | 5 |  |  | 3/6/2025 | Connected |  | N
National Grid | DRACUT | 665571 | 01826 | 84.6 | Solar | 05_12_51L1 | 02/14/2025 | 03/28/2025 | 29 | 20 | 9 | 03/31/2025 | 03/31/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2025 |  | 4/16/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 677775 | 01463 | 13.36 | Solar | 05_14_24L3 | 03/13/2025 | 03/24/2025 | 3 | 0 | 3 | 04/10/2025 | 04/10/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 03/13/2025 | 6/24/2026 | Y | EXP | 365 | 08/22/2025 | 12/01/2025 | 102 | 0 | 102 |  |  | 1/20/2026 | Connected |  | N
National Grid | AUBURN | 670110 | 01501 | 10 | Solar | 05_14_56L2 | 02/05/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | SPENCER | 176006 | 01562 | 7.6 | Solar | 05_14_70L1 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 375 | 0 | 375 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 |  | 8/19/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 647856 | 01607 | 7.6 | Solar | 05_14_78L9 | 10/17/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 676260 | 02720 | 7.6 | Solar | 05_01_226L2 | 03/07/2025 |  | 76 | 73 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 178498 | 01516 | 276.4 | Solar | 05_01_406L2 | 01/23/2018 | 02/22/2018 | 0 | 0 | 0 | 02/22/2018 | 02/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2018 |  | 12/31/2019 | N | EXP | 504 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N
National Grid | BEVERLY | 175966 | 01915 | 18 | Solar | 05_01_552L1 | 08/06/2015 | 08/06/2015 | 4 | 4 | 0 | 08/14/2015 | 08/14/2015 | 216 | 0 | 216 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 8/15/2016 | N | EXP | 340 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 684730 | 01824 | 3.8 | Solar | 05_01_8W1 | 04/11/2025 | 10/07/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2026 | Connected |  | N
National Grid | ANDOVER | 176173 | 01845 | 972 | Solar | 05_05_28W41 | 04/23/2015 | 04/23/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2015 | 05/26/2015 | 18 | 0 | 18 |  | 0 | 0 | 0 | 11/18/2015 | 12/21/2015 | 22 | 0 | 22 | 1/22/2016 | 04/23/2015 | 9/30/2015 | Y | STD | 114 | 07/12/2016 | 10/17/2016 | 67 | 0 | 67 | 10/21/2016 | 10/21/2016 | 10/28/2016 | Connected |  | N
National Grid | BILLERICA | 632483 | 01862 | 10 | Solar | 05_05_320W2 | 08/13/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 | 08/13/2024 | 9/20/2025 | Y | EXP | 365 | 11/13/2024 | 12/05/2024 | 22 | 0 | 22 |  |  | 12/20/2024 | Connected |  | N
National Grid | DRACUT | 703620 | 01826 | 0 | Other | 05_12_51L1 | 09/22/2025 | 11/24/2025 | 41 | 34 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 | 12/23/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | PEPPERELL | 734759 | 01463 | 23 | Solar | 05_14_275L2 | 11/19/2025 | 11/20/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AUBURN | 684866 | 01501 | 0 | Solar | 05_14_56L2 | 04/14/2025 | 05/20/2025 | 23 | 17 | 6 | 05/21/2025 | 05/21/2025 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 7/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2025 | Connected |  | N
National Grid | SPENCER | 176041 | 01562 | 11.4 | Solar | 05_14_70L1 | 08/14/2015 | 08/14/2015 | 1 | 1 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 8/22/2016 | N | EXP | 348 |  |  | 0 | 0 | 0 | 3/11/2016 | 3/11/2016 | 3/17/2016 | Connected |  | N
National Grid | WORCESTER | 655530 | 01607 | 3.8 | Solar | 05_14_78L9 | 11/19/2024 | 01/14/2025 | 5 | 0 | 5 | 01/15/2025 | 01/15/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 11/19/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | FALL RIVER | 684274 | 02720 | 7.6 | Solar | 05_01_226L2 | 04/14/2025 | 04/25/2025 | 8 | 5 | 3 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 191422 | 01516 | 10 | Solar | 05_01_406L2 | 08/04/2018 | 09/13/2018 | 3 | 3 | 0 | 09/14/2018 | 09/14/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 | 08/04/2018 | 6/28/2019 | Y | EXP | 275 | 03/26/2019 | 04/01/2019 | 6 | 0 | 6 |  |  | 6/24/2019 | Connected |  | N
National Grid | BEVERLY | 176251 | 01915 | 499 | Solar | 05_01_552L1 | 07/07/2015 | 07/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2016 | 07/07/2015 | 10/26/2017 | Y | STD | 620 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/27/2017 | Connected |  | N
National Grid | CHELMSFORD | 611947 | 01824 | 240 | Solar | 05_01_8W2 | 06/03/2024 | 08/13/2024 | 49 | 25 | 24 |  |  | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2026 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ANDOVER | 177659 | 01845 | 240 | Solar | 05_05_28W41 | 11/13/2017 | 11/13/2017 | 51 | 42 | 9 | 01/29/2018 | 01/29/2018 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 |  | 11/19/2018 | N | EXP | 283 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | TEWKSBURY | 663343 | 01876 | 10 | Solar | 05_05_320W2 | 01/02/2025 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N
National Grid | DRACUT | 721660 | 01826 | 38.08 | Solar | 05_12_51L1 | 10/01/2025 | 10/06/2025 | 2 | 0 | 2 | 10/07/2025 | 10/07/2025 | 72 | 60 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  | 1/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 174700 | 01463 | 595 | Solar | 05_14_275L2 | 01/03/2013 | 01/03/2013 | 7 | 0 | 7 | 01/15/2013 | 01/15/2013 | 332 | 0 | 332 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2013 |  | 5/31/2013 | N | EXP | 29 |  |  | 0 | 0 | 0 | 5/2/2013 | 5/2/2013 |  | Withdrawn |  | N
National Grid | AUBURN | 705068 | 01501 | 17.799 | Solar | 05_14_56L2 | 07/17/2025 | 07/22/2025 | 3 | 0 | 3 | 07/23/2025 | 07/23/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 8/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2025 | Connected |  | N
National Grid | SPENCER | 176226 | 01562 | 10 | Solar | 05_14_70L1 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 358 | 0 | 358 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 9/12/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 661689 | 01607 | 5.76 | Solar | 05_14_78L9 | 12/27/2024 | 01/02/2025 | 3 | 0 | 3 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/27/2024 | 2/28/2026 | Y | EXP | 365 | 10/02/2025 | 10/29/2025 | 28 | 0 | 28 |  |  | 12/2/2025 | Connected |  | N
National Grid | FALL RIVER | 686777 | 02720 | 19 | Solar | 05_01_226L2 | 04/23/2025 | 05/01/2025 | 6 | 2 | 4 | 05/02/2025 | 05/02/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 320744 | 01516 | 10 | Solar | 05_01_406L2 | 11/23/2020 | 01/07/2022 | 1 | 0 | 1 | 11/27/2020 | 11/27/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 11/23/2020 | 10/10/2022 | Y | EXP | 365 | 01/18/2022 | 03/04/2022 | 46 | 0 | 46 |  |  | 3/30/2022 | Connected |  | Y
National Grid | BEVERLY | 176250 | 01915 | 499 | Solar | 05_01_552L1 | 07/07/2015 | 07/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2016 | 07/07/2015 | 10/26/2017 | Y | STD | 620 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/27/2017 | Connected |  | N
National Grid | AMESBURY | 728191 | 01913 | 10 | Solar | 05_01_8W2 | 10/22/2025 | 12/19/2025 | 2 | 0 | 2 | 12/31/2025 | 12/31/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | ANDOVER | 177932 | 01845 | 180 | Solar | 05_05_28W41 | 04/20/2017 | 04/20/2017 | 14 | 13 | 1 | 05/10/2017 | 05/10/2017 | 0 | 0 | 0 | 06/29/2017 | 07/27/2017 | 19 | 1 | 18 |  |  | 0 | 0 | 0 | 07/27/2017 | 19 | 1 | 18 |  |  | 0 | 0 | 0 | 9/20/2017 |  | 4/25/2018 | N | EXP | 217 |  |  | 0 | 0 | 0 | 12/8/2017 | 12/8/2017 | 12/15/2017 | Connected |  | N
National Grid | BILLERICA | 668016 | 01862 | 15.2 | Solar | 05_05_320W2 | 01/27/2025 | 02/19/2025 | 1 | 0 | 1 | 03/28/2025 | 03/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | DRACUT | 727172 | 01826 | 10 | Solar | 05_12_51L1 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 23 | 1 | 22 | 01/13/2026 | 01/28/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 01/28/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 3/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | PEPPERELL | 174806 | 01463 | 300 | Solar | 05_14_275L2 | 01/23/2013 | 01/23/2013 | 7 | 0 | 7 | 02/04/2013 | 02/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2013 |  | 6/28/2013 | N | EXP | 92 |  |  | 0 | 0 | 0 | 3/28/2013 | 3/28/2013 | 8/22/2013 | Connected |  | N
National Grid | AUBURN | 707961 | 01501 | 17.6 | Solar | 05_14_56L3 | 08/01/2025 | 08/06/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 | 08/01/2025 | 10/16/2026 | Y | EXP | 365 | 03/27/2026 |  | 6 | 0 | 6 |  |  |  | Construction |  | N
National Grid | SPENCER | 176550 | 01562 | 10 | Solar | 05_14_70L1 | 04/05/2016 | 04/05/2016 | 1 | 1 | 0 | 04/07/2016 | 04/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 | 04/05/2016 | 4/11/2017 | Y | EXP | 357 | 09/06/2016 | 09/14/2016 | 6 | 0 | 6 | 12/7/2016 | 12/7/2016 | 12/7/2016 | Connected |  | N
National Grid | MILLBURY | 686572 | 01527 | 4.8 | Solar | 05_14_78L9 | 04/21/2025 | 05/13/2025 | 4 | 0 | 4 | 05/14/2025 | 05/14/2025 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | FALL RIVER | 712231 | 02720 | 17.16 | Solar | 05_01_226L2 | 08/15/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 359795 | 01516 | 9.6 | Solar | 05_01_406L2 | 05/21/2021 | 05/24/2021 | 0 | 0 | 0 | 05/25/2021 | 05/25/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2021 |  | 7/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2021 | Connected |  | N
National Grid | BEVERLY | 176305 | 01915 | 16.5 | Solar | 05_01_552L1 | 02/20/2015 | 02/20/2015 | 10 | 5 | 5 | 03/07/2015 | 03/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 |  | 7/31/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 7/20/2015 | 7/20/2015 | 7/29/2015 | Connected |  | N
National Grid | AMESBURY | 734507 | 01913 | 3.8 | Solar | 05_01_8W2 | 11/18/2025 | 11/19/2025 | 2 | 0 | 2 | 01/15/2026 | 01/15/2026 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  | 3/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 178275 | 01845 | 990 | Solar | 05_05_28W41 | 02/21/2018 | 02/21/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 05/08/2018 | 29 | 0 | 29 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 673567 | 01876 | 0 | Battery Add-On | 05_05_320W2 | 02/21/2025 | 03/10/2025 | 12 | 7 | 5 | 03/11/2025 | 03/11/2025 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 9/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2026 | Connected |  | N
National Grid | DRACUT | 174524 | 01826 | 75 | Natural Gas | 05_12_51L1 | 04/14/2011 | 04/14/2011 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 4/13/2011 | 4/13/2011 | 4/13/2011 | Connected |  | N
National Grid | PEPPERELL | 176392 | 01463 | 300 | Solar | 05_14_275L2 | 02/02/2016 | 02/02/2016 | 1 | 1 | 0 | 02/04/2016 | 02/04/2016 | 0 | 0 | 0 | 03/16/2016 | 03/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2016 |  | 9/15/2016 | N | EXP | 183 |  |  | 0 | 0 | 0 | 9/29/2016 | 9/29/2016 | 9/30/2016 | Connected |  | N
National Grid | AUBURN | 707764 | 01501 | 19.12 | Solar | 05_14_56L3 | 08/06/2025 | 08/27/2025 | 14 | 9 | 5 | 08/28/2025 | 08/28/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SPENCER | 177569 | 01562 | 15.2 | Solar | 05_14_70L1 | 09/14/2017 | 09/14/2017 | 9 | 9 | 0 | 09/27/2017 | 09/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/19/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 6/7/2018 | Connected |  | N
National Grid | WORCESTER | 686563 | 01607 | 7.6 | Solar | 05_14_78L9 | 04/21/2025 | 05/13/2025 | 4 | 0 | 4 | 05/14/2025 | 05/14/2025 | 50 | 36 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  | 7/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | FALL RIVER | 716113 | 02720 | 13.36 | Solar | 05_01_226L2 | 09/02/2025 | 09/09/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 395838 | 01516 | 9.8 | Solar | 05_01_406L2 | 11/22/2021 | 11/23/2021 | 1 | 0 | 1 | 11/24/2021 | 11/24/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/22/2021 | 6/7/2023 | Y | EXP | 365 | 04/23/2022 | 06/07/2022 | 46 | 0 | 46 |  |  | 6/9/2022 | Connected |  | N
National Grid | BEVERLY | 176428 | 01915 | 10 | Solar | 05_01_552L1 | 02/03/2016 | 02/03/2016 | 3 | 3 | 0 | 02/09/2016 | 02/09/2016 | 232 | 0 | 232 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 |  | 2/9/2017 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 741842 | 01913 | 10 | Solar | 05_01_8W2 | 12/25/2025 | 12/30/2025 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOXFORD | 189617 | 01921 | 249.8 | Solar | 05_05_28W41 | 06/29/2018 | 06/29/2018 | 6 | 5 | 1 | 07/11/2018 | 07/11/2018 | 43 | 21 | 22 | 09/28/2018 | 12/07/2018 | 48 | 19 | 29 |  |  | 0 | 0 | 0 | 12/07/2018 | 48 | 19 | 29 |  |  | 0 | 0 | 0 | 3/18/2019 | 06/29/2018 | 12/30/2021 | Y | EXP | 389 | 10/23/2021 | 11/19/2021 | 28 | 4 | 24 |  |  | 12/30/2021 | Connected |  | N
National Grid | BILLERICA | 685525 | 01862 | 3.8 | Solar | 05_05_320W2 | 04/16/2025 | 06/06/2025 | 34 | 24 | 10 | 06/09/2025 | 06/09/2025 | 35 | 22 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | DRACUT | 175151 | 01826 | 224 | Solar | 05_12_51L1 | 10/30/2013 | 10/30/2013 | 5 | 0 | 5 | 11/07/2013 | 11/07/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2013 | 10/30/2013 | 5/30/2014 | Y | EXP | 170 | 08/04/2014 | 08/04/2014 | 0 | 0 | 0 | 8/6/2014 | 8/6/2014 | 8/7/2014 | Connected |  | N
National Grid | PEPPERELL | 177136 | 01463 | 7.6 | Solar | 05_14_275L2 | 05/27/2016 | 05/27/2016 | 1 | 1 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2016 |  | 6/5/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 9/23/2016 | 9/23/2016 | 9/28/2016 | Connected |  | N
National Grid | AUBURN | 724912 | 01501 | 16 | Solar | 05_14_56L3 | 10/08/2025 | 10/09/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 177756 | 01562 | 324 | Solar | 05_14_70L1 | 08/01/2017 | 08/01/2017 | 83 | 83 | 0 |  |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  | 9/2/2019 | N | STD | 431 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 715946 | 01607 | 6.84 | Solar | 05_14_78L9 | 09/02/2025 | 09/23/2025 | 14 | 9 | 5 | 09/24/2025 | 09/24/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2026 | Connected |  | N
National Grid | FALL RIVER | 722437 | 02720 | 15.2 | Solar | 05_01_226L2 | 09/26/2025 | 10/06/2025 | 5 | 3 | 2 | 10/07/2025 | 10/07/2025 | 39 | 22 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 1/1/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2026 | Connected |  | N
National Grid | DOUGLAS | 402308 | 01516 | 9.8 | Solar | 05_01_406L2 | 01/24/2022 | 02/01/2022 | 6 | 0 | 6 | 02/02/2022 | 02/02/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 | 01/24/2022 | 8/17/2023 | Y | EXP | 365 | 07/15/2022 | 08/16/2022 | 33 | 0 | 33 |  |  | 9/1/2022 | Connected |  | N
National Grid | BEVERLY | 176541 | 01915 | 900 | Solar | 05_01_552L1 | 02/10/2016 | 02/16/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2016 | 03/08/2016 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2016 | 02/10/2016 | 2/11/2022 | Y | STD | 1348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 174185 | 01913 | 91.2 | Solar | 05_01_8W2 | 10/23/2011 | 10/23/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2012 | 10/23/2011 | 5/1/2012 | Y | EXP | 62 | 10/05/2012 | 01/15/2013 | 52 | 0 | 52 | 6/20/2012 | 6/20/2012 | 4/24/2013 | Connected |  | N
National Grid | BOXFORD | 203810 | 01921 | 250 | Solar | 05_05_28W41 | 01/11/2019 | 01/02/2019 | 7 | 4 | 3 | 01/03/2019 | 01/03/2019 | 5 | 0 | 5 | 02/12/2019 | 03/07/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 03/07/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 690252 | 01862 | 15.2 | Solar | 05_05_320W2 | 05/07/2025 | 05/14/2025 | 5 | 1 | 4 | 05/15/2025 | 05/15/2025 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | DRACUT | 175168 | 01826 | 60 | Solar | 05_12_51L1 | 11/14/2012 | 11/14/2012 | 15 | 9 | 6 | 12/11/2012 | 12/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2013 |  | 1/31/2013 | N | EXP | 41 |  |  | 0 | 0 | 0 | 6/25/2013 | 6/25/2013 | 8/21/2013 | Connected |  | N
National Grid | PEPPERELL | 177161 | 01463 | 80 | Solar | 05_14_275L2 | 10/28/2016 | 10/28/2016 | 2 | 2 | 0 | 11/03/2016 | 11/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2016 | 10/28/2016 | 11/6/2017 | Y | EXP | 362 | 01/09/2017 | 05/09/2017 | 83 | 0 | 83 | 6/12/2017 | 6/12/2017 | 6/12/2017 | Connected |  | N
National Grid | AUBURN | 725463 | 01501 | 15.2 | Solar | 05_14_56L3 | 10/13/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 177755 | 01562 | 396 | Solar | 05_14_70L1 | 08/01/2017 | 08/01/2017 | 84 | 84 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2017 | 12/20/2017 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  | 9/2/2019 | N | STD | 431 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 246224 | 01607 | 7.6 | Solar | 05_14_7J1 | 08/12/2019 | 08/28/2019 | 12 | 11 | 1 | 08/29/2019 | 08/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 |  | 2/26/2020 | N | EXP | 168 |  |  | 0 | 0 | 0 |  |  | 1/28/2020 | Connected |  | N
National Grid | FALL RIVER | 730024 | 02720 | 1000 | Solar | 05_01_226L2 | 11/03/2025 | 11/20/2025 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 12/17/2025 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DOUGLAS | 414703 | 01516 | 9.86 | Solar | 05_01_406L2 | 02/28/2022 | 03/11/2022 | 9 | 8 | 1 | 03/14/2022 | 03/14/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 | 02/28/2022 | 8/27/2023 | Y | EXP | 365 | 07/16/2022 | 08/26/2022 | 42 | 0 | 42 |  |  | 3/9/2023 | Connected |  | N
National Grid | BEVERLY | 176750 | 01915 | 11.4 | Solar | 05_01_552L1 | 01/12/2016 | 01/12/2016 | 9 | 9 | 0 | 01/26/2016 | 01/26/2016 | 265 | 0 | 265 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 1/17/2017 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 174739 | 01913 | 300 | Solar | 05_01_8W2 | 01/15/2013 | 01/15/2013 | 6 | 0 | 6 | 01/25/2013 | 01/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2013 |  | 6/28/2013 | N | EXP | 99 |  |  | 0 | 0 | 0 | 3/26/2013 | 3/26/2013 | 8/20/2013 | Connected |  | N
National Grid | BOXFORD | 646539 | 01921 | 2850 | Solar | 05_05_28W50 | 03/28/2025 | 05/07/2025 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2025 | 06/05/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 706306 | 01862 | 11.5 | Solar | 05_05_320W2 | 07/21/2025 | 09/25/2025 | 2 | 0 | 2 | 09/26/2025 | 09/26/2025 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2026 | Connected |  | N
National Grid | DRACUT | 175845 | 01826 | 401 | Solar | 05_12_51L1 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 | 05/22/2015 | 05/22/2015 | 366 | 0 | 366 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 202349 | 01463 | 7.6 | Solar | 05_14_275L2 | 01/09/2019 | 01/18/2019 | 6 | 0 | 6 | 01/22/2019 | 01/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 01/09/2019 | 9/16/2020 | Y | EXP | 365 | 04/17/2020 | 05/12/2020 | 25 | 0 | 25 |  |  | 7/25/2020 | Connected |  | N
National Grid | AUBURN | 734607 | 01501 | 7.6 | Solar | 05_14_56L3 | 01/13/2026 | 01/20/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2026 |  | 3/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 177965 | 01562 | 480 | Solar | 05_14_70L1 | 04/21/2017 | 04/21/2017 | 25 | 22 | 3 | 05/30/2017 | 05/30/2017 | 189 | 46 | 143 | 10/05/2017 | 11/17/2017 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 11/17/2017 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 4/29/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 663217 | 01607 | 11.5 | Solar | 05_14_7J1 | 01/02/2025 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | FALL RIVER | 582916 | 02720 | 0 | Solar | 05_01_227W1 | 02/06/2024 | 04/10/2024 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2024 | 04/24/2024 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DOUGLAS | 473720 | 01516 | 5.76 | Solar | 05_01_406L2 | 12/08/2022 | 12/12/2022 | 2 | 0 | 2 | 12/13/2022 | 12/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 | 12/08/2022 | 4/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2023 | Connected |  | N
National Grid | BEVERLY | 177078 | 01915 | 22.8 | Solar | 05_01_552L1 | 10/17/2016 | 10/17/2016 | 1 | 1 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2016 | 10/17/2016 | 10/23/2017 | Y | EXP | 364 | 03/28/2017 | 05/22/2017 | 38 | 0 | 38 | 8/29/2017 | 8/29/2017 | 9/1/2017 | Connected |  | N
National Grid | AMESBURY | 174946 | 01913 | 142 | Solar | 05_01_8W2 | 09/24/2012 | 09/24/2012 | 7 | 0 | 7 | 10/04/2012 | 10/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2013 |  | 12/3/2012 | N | EXP | 43 |  |  | 0 | 0 | 0 | 1/15/2013 | 1/15/2013 | 2/8/2013 | Connected |  | N
National Grid | BOXFORD | 748496 | 01921 | 11.4 | Solar | 05_05_28W50 | 01/30/2026 | 02/12/2026 | 3 | 0 | 3 | 02/20/2026 | 02/20/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 707731 | 01862 | 10 | Solar | 05_05_320W2 | 07/28/2025 | 08/13/2025 | 11 | 8 | 3 | 08/14/2025 | 08/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2025 | Connected |  | N
National Grid | ANDOVER | 175842 | 01845 | 100 | Solar | 05_12_51L1 | 03/06/2015 | 03/06/2015 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/12/2015 | N | EXP | 0 | 07/28/2016 | 03/12/2015 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 208390 | 01463 | 7.6 | Solar | 05_14_275L2 | 03/01/2019 | 03/04/2019 | 0 | 0 | 0 | 03/05/2019 | 03/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2019 | 03/01/2019 | 9/1/2020 | Y | EXP | 414 | 04/18/2020 | 05/06/2020 | 18 | 0 | 18 |  |  | 8/19/2020 | Connected |  | N
National Grid | AUBURN | 736628 | 01501 | 10 | Solar | 05_14_56L3 | 12/29/2025 | 02/13/2026 | 31 | 25 | 6 | 02/17/2026 | 02/17/2026 | 31 | 22 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SPENCER | 178438 | 01562 | 7.6 | Solar | 05_14_70L1 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 |  | 3/12/2019 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 176081 | 01527 | 27 | Solar | 05_14_7J3 | 08/20/2015 | 08/20/2015 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/26/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 705049 | 02720 | 15.68 | Solar | 05_01_227W1 | 07/15/2025 | 08/07/2025 | 17 | 11 | 6 | 08/08/2025 | 08/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DOUGLAS | 564813 | 01516 | 7.6 | Solar | 05_01_406L2 | 10/24/2023 | 11/07/2023 | 11 | 10 | 1 | 11/08/2023 | 11/08/2023 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2023 | 10/24/2023 | 2/2/2025 | Y | EXP | 365 | 05/02/2024 | 09/07/2024 | 129 | 0 | 129 |  |  | 10/8/2024 | Connected |  | N
National Grid | BEVERLY | 177415 | 01915 | 995 | Landfill Gas | 05_01_552L1 | 09/15/2016 | 09/26/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2016 | 10/18/2016 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2017 | 09/15/2016 | 11/12/2019 | Y | STD | 928 | 01/09/2019 | 02/24/2019 | 46 | 0 | 46 |  |  | 10/31/2019 | Connected |  | N
National Grid | AMESBURY | 175176 | 01913 | 18 | Solar | 05_01_8W2 | 04/30/2013 | 04/30/2013 | 7 | 1 | 6 | 05/10/2013 | 05/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2013 |  | 7/31/2013 | N | EXP | 19 |  |  | 0 | 0 | 0 | 9/13/2013 | 9/13/2013 | 9/25/2013 | Connected |  | N
National Grid | ANDOVER | 174477 | 01845 | 203 | Solar | 05_05_28W50 | 04/27/2011 | 04/27/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 716359 | 01862 | 14.658 | Solar | 05_05_320W2 | 09/03/2025 | 09/09/2025 | 3 | 1 | 2 | 09/10/2025 | 09/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | ANDOVER | 175841 | 01845 | 100 | Solar | 05_12_51L1 | 03/06/2015 | 03/06/2015 | 5 | 0 | 5 | 03/16/2015 | 03/16/2015 | 756 | 0 | 756 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2015 | 03/06/2015 | 6/29/2018 | Y | EXP | 1128 | 07/28/2016 |  | 416 | 0 | 416 | 7/20/2015 | 7/20/2015 |  | Withdrawn |  | N
National Grid | LANCASTER | 245163 | 01523 | 4990 | Solar | 05_14_275L2 | 03/05/2020 | 03/26/2020 | 15 | 11 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2020 | 05/21/2020 | 38 | 19 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 03/05/2020 | 5/15/2030 | Y | STD | 2190 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 748935 | 01501 | 19 | Solar | 05_14_56L3 | 02/17/2026 | 02/19/2026 | 2 | 0 | 2 | 02/20/2026 | 02/20/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2026 |  | 3/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 178546 | 01562 | 604 | Solar | 05_14_70L1 | 01/29/2018 | 01/29/2018 | 36 | 31 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/22/2018 | 04/18/2018 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 176110 | 01527 | 27 | Solar | 05_14_7J3 | 08/20/2015 | 08/20/2015 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/26/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 740278 | 02720 | 0 | Battery Add-On | 05_01_227W1 | 12/15/2025 | 12/17/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DOUGLAS | 590501 | 01516 | 5.8 | Solar | 05_01_406L2 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 |  | 3/13/2026 | N | EXP | 465 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 177649 | 01915 | 7.6 | Solar | 05_01_552L1 | 09/27/2017 | 09/27/2017 | 8 | 8 | 0 | 10/10/2017 | 10/10/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2017 |  | 10/2/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 6/29/2018 | Connected |  | N
National Grid | AMESBURY | 176546 | 01913 | 1992 | Solar | 05_01_8W2 | 04/03/2016 | 04/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2016 | 05/09/2016 | 24 | 5 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 | 04/03/2016 | 11/14/2018 | Y | STD | 807 |  |  | 0 | 0 | 0 |  |  | 11/14/2018 | Connected |  | N
National Grid | BOXFORD | 174472 | 01921 | 250 | Solar | 05_05_28W50 | 04/28/2011 | 04/28/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 6/3/2014 | 6/3/2014 | 9/28/2011 | Connected |  | N
National Grid | BILLERICA | 701275 | 01862 | 10 | Solar | 05_05_320W3 | 06/26/2025 | 09/03/2025 | 12 | 8 | 4 | 09/29/2025 | 09/29/2025 | 48 | 35 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 175920 | 01845 | 9.8 | Solar | 05_12_51L1 | 05/28/2015 | 05/28/2015 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 300662 | 01464 | 7.6 | Solar | 05_14_275L2 | 08/06/2020 | 08/11/2020 | 3 | 1 | 2 | 08/12/2020 | 08/12/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/06/2020 | 12/6/2021 | Y | EXP | 365 | 03/24/2021 | 04/06/2021 | 13 | 0 | 13 |  |  | 10/5/2021 | Connected |  | N
National Grid | AUBURN | 174156 | 01501 | 1000 | Solar | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/5/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 178584 | 01562 | 158 | Solar | 05_14_70L1 | 01/31/2018 | 01/31/2018 | 23 | 3 | 20 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176421 | 01607 | 25 | Solar | 05_14_7J3 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2015 |  | 12/13/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 2/29/2016 | 2/29/2016 | 3/28/2016 | Connected |  | N
National Grid | FALL RIVER | 174132 | 02720 | 300 | Solar | 05_01_227W1 | 05/03/2012 | 05/03/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/29/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 614107 | 01516 | 7.6 | Solar | 05_01_406L2 | 05/30/2024 | 06/12/2024 | 2 | 0 | 2 | 06/13/2024 | 06/13/2024 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | BEVERLY | 177634 | 01915 | 2000 | Solar | 05_01_552L1 | 07/19/2017 | 08/01/2017 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/01/2017 | 08/21/2017 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 | 07/19/2017 | 6/26/2020 | Y | STD | 645 | 10/29/2019 | 05/20/2020 | 202 | 0 | 202 |  |  | 6/26/2020 | Connected |  | N
National Grid | AMESBURY | 177041 | 01913 | 4400 | Solar | 05_01_8W2 | 10/18/2016 | 10/18/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 |  | 10/23/2016 | N | STD | 3 |  |  | 0 | 0 | 0 | 10/26/2016 | 10/26/2016 | 10/26/2016 | Connected |  | N
National Grid | BOXFORD | 174535 | 01921 | 0 | Solar | 05_05_28W50 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 01/27/2012 | 43 | 0 | 43 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2013 | 10/18/2011 | 10/31/2012 | Y | STD | 160 | 11/22/2013 | 12/19/2013 | 18 | 0 | 18 | 12/19/2013 | 12/19/2013 | 12/23/2013 | Connected |  | N
National Grid | TEWKSBURY | 711249 | 01876 | 250 | Solar | 05_05_320W3 | 09/09/2025 | 11/26/2025 | 53 | 43 | 10 |  |  | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ANDOVER | 175991 | 01845 | 100 | Solar | 05_12_51L1 | 03/23/2015 | 03/23/2015 | 2 | 0 | 2 | 03/26/2015 | 03/26/2015 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2015 | 03/23/2015 | 5/31/2018 | Y | EXP | 1099 |  |  | 0 | 0 | 0 | 7/20/2015 | 7/20/2015 |  | Withdrawn |  | N
National Grid | LANCASTER | 348110 | 01523 | 9.8 | Solar | 05_14_275L2 | 04/08/2021 | 04/12/2021 | 1 | 0 | 1 | 04/13/2021 | 04/13/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 |  | 4/12/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 174155 | 01501 | 1000 | Solar | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 178580 | 01562 | 402 | Solar | 05_14_70L1 | 01/31/2018 | 01/31/2018 | 35 | 25 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176450 | 01607 | 27 | Solar | 05_14_7J3 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2015 |  | 12/13/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/28/2016 | 3/28/2016 | 3/1/2016 | Connected |  | N
National Grid | FALL RIVER | 174187 | 02720 | 500 | Solar | 05_01_227W1 | 03/12/2012 | 03/12/2012 | 11 | 0 | 11 | 04/05/2012 | 04/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2013 | 03/12/2012 | 6/1/2012 | Y | EXP | 237 | 07/15/2013 | 09/27/2013 | 53 | 0 | 53 | 9/26/2013 | 9/26/2013 | 9/27/2013 | Connected |  | N
National Grid | NORTHBRIDGE | 621138 | 01534 | 3.8 | Solar | 05_01_406L2 | 06/27/2024 | 07/19/2024 | 1 | 0 | 1 | 07/22/2024 | 07/22/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2024 | Connected |  | N
National Grid | BEVERLY | 178079 | 01915 | 2199 | Solar | 05_01_552L1 | 05/05/2017 | 08/24/2017 | 76 | 75 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2017 | 09/28/2017 | 24 | 9 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2018 | 05/05/2017 | 6/6/2025 | Y | STD | 144 | 02/21/2020 | 05/08/2024 | 1539 | 15 | 1524 |  |  | 6/25/2025 | Connected |  | N
National Grid | AMESBURY | 177204 | 01913 | 299.8 | Solar | 05_01_8W2 | 02/01/2017 | 02/01/2017 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 175803 | 01845 | 990 | Solar | 05_05_28W50 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 713976 | 01876 | 10 | Solar | 05_05_320W3 | 08/22/2025 | 09/24/2025 | 5 | 0 | 5 | 10/02/2025 | 10/02/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ANDOVER | 176135 | 01845 | 3520 | Solar | 05_12_51L1 | 04/16/2015 | 04/16/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2015 | 05/20/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 09/06/2017 | 07/27/2018 | 224 | 0 | 224 | 8/4/2016 | 04/16/2015 | 12/31/2020 | Y | STD | 1310 | 05/22/2020 | 10/26/2020 | 158 | 5 | 153 |  |  | 12/23/2020 | Connected |  | N
National Grid | LEOMINSTER | 574491 | 01453 | 10 | Solar | 05_14_275L2 | 01/12/2024 | 01/22/2024 | 5 | 4 | 1 | 01/23/2024 | 01/23/2024 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 01/12/2024 | 2/14/2025 | Y | EXP | 365 | 04/24/2024 | 05/07/2024 | 14 | 0 | 14 |  |  | 5/14/2024 | Connected |  | N
National Grid | AUBURN | 174172 | 01501 | 1000 | Solar | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/07/2012 | 07/11/2012 | 44 | 0 | 44 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/12/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 178577 | 01562 | 316 | Solar | 05_14_70L1 | 01/30/2018 | 01/30/2018 | 24 | 3 | 21 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177511 | 01602 | 27 | Solar | 05_14_7J3 | 07/12/2016 | 07/12/2016 | 0 | 0 | 0 | 07/12/2016 | 07/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2016 |  | 7/17/2017 | N | EXP | 370 |  |  | 0 | 0 | 0 | 7/12/2016 | 7/12/2016 | 7/25/2016 | Connected |  | N
National Grid | FALL RIVER | 174231 | 02720 | 2000 | Solar | 05_01_227W1 | 01/31/2012 | 01/31/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2013 | 01/31/2012 | 6/30/2014 | Y | STD | 524 | 01/13/2014 | 07/18/2014 | 127 | 0 | 127 | 6/19/2014 | 6/19/2014 | 6/19/2014 | Connected |  | N
National Grid | WHITINSVILLE | 668558 | 01588 | 7.6 | Solar | 05_01_406L2 | 01/29/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 01/29/2025 | 4/14/2026 | Y | EXP | 365 | 07/08/2025 | 12/04/2025 | 150 | 0 | 150 |  |  | 12/24/2025 | Connected |  | N
National Grid | BEVERLY | 178481 | 01915 | 5000 | Solar | 05_01_552L1 | 04/03/2018 | 04/03/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 204126 | 01913 | 313.2 | Solar | 05_01_8W2 | 12/18/2018 | 01/22/2019 | 21 | 17 | 4 | 01/23/2019 | 01/23/2019 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 177533 | 01845 | 9.92 | Solar | 05_05_28W50 | 09/11/2017 | 09/11/2017 | 22 | 22 | 0 | 10/13/2017 | 10/13/2017 | 113 | 0 | 113 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 | 09/11/2017 | 11/30/2018 | Y | EXP | 410 | 07/26/2018 | 08/21/2018 | 26 | 0 | 26 |  |  | 11/26/2018 | Connected |  | N
National Grid | TEWKSBURY | 736065 | 01876 | 11.4 | Solar | 05_05_320W3 | 11/25/2025 | 11/26/2025 | 4 | 0 | 4 | 12/16/2025 | 12/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 |  | 1/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 176345 | 01845 | 6.67 | Solar | 05_12_51L1 | 02/25/2015 | 02/25/2015 | 9 | 5 | 4 | 03/11/2015 | 03/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 | 02/25/2015 | 12/31/2016 | Y | EXP | 655 | 02/11/2016 | 04/30/2016 | 54 | 0 | 54 | 3/17/2015 | 3/17/2015 | 10/12/2016 | Connected |  | N
National Grid | LANCASTER | 613959 | 01523 | 10 | Solar | 05_14_275L2 | 05/30/2024 | 06/24/2024 | 11 | 7 | 4 | 06/25/2024 | 06/25/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 174171 | 01501 | 1000 | Solar | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/07/2012 | 07/11/2012 | 44 | 0 | 44 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/12/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 178576 | 01562 | 524 | Solar | 05_14_70L1 | 01/29/2018 | 01/29/2018 | 36 | 31 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/22/2018 | 04/18/2018 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 332646 | 01607 | 7.6 | Solar | 05_14_7J4 | 01/06/2021 | 01/11/2021 | 2 | 0 | 2 | 01/12/2021 | 01/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 174595 | 02720 | 82 | Solar | 05_01_227W1 | 10/19/2011 | 10/19/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2011 |  | 2/21/2012 | N | EXP | 62 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 2/21/2012 | Connected |  | N
National Grid | NORTHBRIDGE | 678760 | 01534 | 7.6 | Solar | 05_01_406L2 | 03/18/2025 | 05/02/2025 | 3 | 0 | 3 | 06/06/2025 | 06/06/2025 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 | 03/18/2025 | 7/30/2026 | Y | EXP | 365 | 10/30/2025 | 12/02/2025 | 34 | 0 | 34 |  |  | 12/4/2025 | Connected |  | N
National Grid | BEVERLY | 178736 | 01915 | 7.6 | Solar | 05_01_552L1 | 02/12/2018 | 03/15/2018 | 0 | 0 | 0 | 03/15/2018 | 03/15/2018 | 189 | 0 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 |  | 2/18/2019 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 309736 | 01913 | 7.6 | Solar | 05_01_8W2 | 10/02/2020 | 10/06/2020 | 1 | 0 | 1 | 10/07/2020 | 10/07/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 177913 | 01845 | 2000 | Solar | 05_05_28W50 | 07/11/2017 | 07/11/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2017 | 08/22/2017 | 2 | 0 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2018 |  | 6/24/2019 | N | STD | 445 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 735262 | 01862 | 3.8 | Solar | 05_05_320W3 | 11/20/2025 | 12/18/2025 | 15 | 11 | 4 | 12/19/2025 | 12/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/21/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 176394 | 01845 | 10 | Solar | 05_12_51L1 | 02/02/2016 | 02/02/2016 | 4 | 4 | 0 | 02/09/2016 | 02/09/2016 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2016 |  | 2/8/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 653578 | 01523 | 16 | Solar | 05_14_275L2 | 11/11/2024 | 11/27/2024 | 12 | 10 | 2 | 12/02/2024 | 12/02/2024 | 102 | 26 | 76 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 175071 | 01501 | 11.61 | Solar | 05_14_56L3 | 04/08/2013 | 04/08/2013 | 5 | 0 | 5 | 04/17/2013 | 04/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2013 |  | 7/31/2013 | N | EXP | 85 |  |  | 0 | 0 | 0 | 5/7/2013 | 5/7/2013 | 7/29/2013 | Connected |  | N
National Grid | SPENCER | 178616 | 01562 | 444 | Solar | 05_14_70L1 | 01/31/2018 | 01/31/2018 | 35 | 30 | 5 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 747655 | 01607 | 3.8 | Solar | 05_14_7L1 | 01/27/2026 | 02/02/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 175314 | 02720 | 594.4 | Solar | 05_01_227W1 | 08/28/2014 | 08/28/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/10/2014 | 10/09/2014 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 706259 | 01560 | 15.2 | Solar | 05_01_406L2 | 07/22/2025 | 07/25/2025 | 3 | 0 | 3 | 07/28/2025 | 07/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | BEVERLY | 178773 | 01915 | 1980 | Solar | 05_01_552L1 | 04/29/2013 | 04/29/2013 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2013 | 07/22/2013 | 25 | 17 | 8 |  | 0 | 0 | 0 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 | 5/21/2014 | 04/29/2013 | 12/31/2016 | Y | STD | 955 | 06/24/2016 | 09/27/2016 | 65 | 0 | 65 | 10/26/2016 | 10/26/2016 | 10/28/2016 | Connected |  | N
National Grid | AMESBURY | 382570 | 01913 | 350 | Solar | 05_01_8W2 | 11/11/2021 | 12/16/2021 | 24 | 15 | 9 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 177975 | 01845 | 660 | Solar | 05_05_28W50 | 06/27/2017 | 06/27/2017 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/03/2017 | 08/29/2017 | 18 | 3 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2018 | 06/27/2017 | 11/30/2018 | Y | STD | 311 | 09/08/2018 | 11/08/2018 | 61 | 0 | 61 |  |  | 11/27/2018 | Connected |  | N
National Grid | TEWKSBURY | 745529 | 01876 | 10.26 | Solar | 05_05_320W3 | 03/17/2026 |  | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | ANDOVER | 177713 | 01845 | 108 | Solar | 05_12_51L1 | 07/26/2017 | 07/26/2017 | 30 | 29 | 1 | 09/07/2017 | 09/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2017 | 07/26/2017 | 7/31/2018 | Y | EXP | 322 | 09/12/2017 | 09/12/2017 | 29 | 29 | 0 |  |  | 5/29/2018 | Connected |  | N
National Grid | SHIRLEY | 655738 | 01464 | 3.8 | Solar | 05_14_275L2 | 11/20/2024 | 12/02/2024 | 2 | 0 | 2 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/20/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | AUBURN | 175388 | 01501 | 15.2 | Solar | 05_14_56L3 | 09/10/2014 | 09/10/2014 | 7 | 0 | 7 | 09/22/2014 | 09/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2014 |  | 12/1/2014 | N | EXP | 54 |  |  | 0 | 0 | 0 | 10/8/2014 | 10/8/2014 | 12/26/2014 | Connected |  | N
National Grid | SPENCER | 178720 | 01562 | 1950 | Solar | 05_14_70L1 | 04/12/2018 | 04/12/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 05/26/2018 | 26 | 7 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 |  | 7/29/2021 | N | STD | 728 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 200995 | 01607 | 7.6 | Solar | 05_14_7L1 | 11/14/2018 | 01/09/2019 | 39 | 37 | 2 | 01/10/2019 | 01/10/2019 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2019 |  | 1/21/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | Connected |  | N
National Grid | FALL RIVER | 175313 | 02720 | 587.2 | Solar | 05_01_227W1 | 08/28/2014 | 08/28/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/10/2014 | 10/09/2014 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 574156 | 01560 | 480 | Solar | 05_01_406L3 | 12/22/2023 | 01/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/09/2024 | 02/06/2024 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BEVERLY | 184382 | 01915 | 7.6 | Solar | 05_01_552L1 | 05/02/2018 | 05/02/2018 | 2 | 0 | 2 | 06/12/2018 | 06/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 644286 | 01913 | 5.76 | Solar | 05_01_8W2 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | BOXFORD | 177977 | 01921 | 480 | Solar | 05_05_28W50 | 06/27/2017 | 06/27/2017 | 25 | 19 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/03/2017 | 08/29/2017 | 18 | 3 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2018 | 06/27/2017 | 11/30/2018 | Y | STD | 311 | 11/28/2018 | 11/27/2018 | 0 | 0 | 0 |  |  | 11/27/2018 | Connected |  | N
National Grid | BILLERICA | 753170 | 01862 | 15.2 | Solar | 05_05_320W3 | 02/25/2026 | 03/02/2026 | 3 | 0 | 3 | 03/03/2026 | 03/03/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2026 |  | 4/1/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALISBURY | 177916 | 01952 | 144 | Solar | 05_12_51L1 | 10/20/2017 | 10/20/2017 | 4 | 0 | 4 | 10/27/2017 | 10/27/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2017 |  | 10/28/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 5/29/2018 | Connected |  | N
National Grid | LANCASTER | 664839 | 01523 | 15.2 | Solar | 05_14_275L2 | 01/10/2025 | 02/11/2025 | 16 | 11 | 5 | 02/12/2025 | 02/12/2025 | 54 | 37 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 | 01/10/2025 | 5/28/2026 | Y | EXP | 365 | 09/30/2025 | 10/10/2025 | 11 | 0 | 11 |  |  | 11/4/2025 | Connected |  | N
National Grid | AUBURN | 175526 | 01501 | 750 | Solar | 05_14_56L3 | 07/29/2014 | 07/29/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 10/21/2014 | 12/01/2014 | 27 | 1 | 26 | 08/07/2014 | 09/05/2014 | 20 | 0 | 20 | 12/01/2014 | 27 | 1 | 26 |  |  | 0 | 0 | 0 | 4/3/2015 | 07/29/2014 | 9/8/2017 | Y | STD | 889 | 02/24/2017 | 09/12/2017 | 138 | 0 | 138 | 8/18/2017 | 8/18/2017 | 9/15/2017 | Connected |  | N
National Grid | CHARLTON | 243050 | 01507 | 7.6 | Solar | 05_14_70L1 | 08/09/2019 | 01/17/2020 | 111 | 111 | 0 | 01/21/2020 | 01/21/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2020 |  | 8/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 301380 | 01607 | 3.8 | Solar | 05_14_7L1 | 07/31/2020 | 08/03/2020 | 0 | 0 | 0 | 08/04/2020 | 08/04/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 07/31/2020 | 5/20/2021 | Y | EXP | 365 | 12/11/2020 | 01/04/2021 | 23 | 0 | 23 |  |  | 5/11/2021 | Connected |  | N
National Grid | FALL RIVER | 175454 | 02720 | 1500 | Solar | 05_01_227W1 | 07/16/2014 | 07/16/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2014 | 08/20/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 07/16/2014 | 6/1/2016 | Y | STD | 531 | 02/03/2017 | 03/03/2017 | 19 | 0 | 19 | 5/15/2017 | 5/15/2017 | 5/15/2017 | Connected |  | N
National Grid | GRAFTON | 693199 | 01560 | 499 | Other | 05_01_406L3 | 09/03/2025 | 10/17/2025 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2025 | 11/04/2025 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BEVERLY | 189203 | 01915 | 3.8 | Solar | 05_01_552L1 | 06/26/2018 | 06/26/2018 | 24 | 0 | 24 | 08/15/2018 | 08/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 652196 | 01913 | 7.6 | Solar | 05_01_8W2 | 11/14/2024 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | BOXFORD | 177976 | 01921 | 960 | Solar | 05_05_28W50 | 06/27/2017 | 06/27/2017 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/03/2017 | 08/29/2017 | 18 | 3 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2018 | 06/27/2017 | 11/30/2018 | Y | STD | 311 |  |  | 0 | 0 | 0 |  |  | 11/27/2018 | Connected |  | N
National Grid | BILLERICA | 174553 | 01862 | 1910 | Solar | 05_05_320W3 | 10/28/2011 | 10/28/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 | 10/28/2011 | 10/31/2012 | Y | STD | 19 | 05/30/2013 | 07/26/2013 | 39 | 0 | 39 | 7/17/2013 | 7/17/2013 | 9/9/2013 | Connected |  | N
National Grid | SALISBURY | 322713 | 01952 | 14.805 | Solar | 05_12_51L1 | 11/13/2020 | 11/17/2020 | 1 | 0 | 1 | 11/18/2020 | 11/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 11/13/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2021 | Connected |  | N
National Grid | LANCASTER | 686893 | 01523 | 10 | Solar | 05_14_275L2 | 05/01/2025 | 05/21/2025 | 4 | 0 | 4 | 05/22/2025 | 05/22/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 | 05/01/2025 | 6/17/2026 | Y | EXP | 365 | 10/01/2025 | 10/07/2025 | 7 | 0 | 7 |  |  | 10/11/2025 | Connected |  | N
National Grid | CHARLTON | 176627 | 01507 | 1000 | Solar | 05_14_56L3 | 10/15/2015 | 10/15/2015 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 | 11/24/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2017 | 10/15/2015 | 3/22/2019 | Y | STD | 695 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 295835 | 01562 | 7.6 | Solar | 05_14_70L1 | 06/13/2020 | 06/18/2020 | 3 | 0 | 3 | 06/19/2020 | 06/19/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2020 | Connected |  | N
National Grid | WORCESTER | 409895 | 01607 | 7.6 | Solar | 05_14_7L1 | 04/14/2022 | 04/21/2022 | 5 | 4 | 1 | 04/22/2022 | 04/22/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 175579 | 02720 | 150 | Solar | 05_01_227W1 | 12/10/2014 | 12/10/2014 | 27 | 6 | 21 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 |  | 2/28/2015 | N | EXP | 25 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 4/22/2015 | Connected |  | N
National Grid | NORTHBRIDGE | 705917 | 01534 | 0 | Other | 05_01_406L3 | 02/02/2026 | 03/04/2026 | 21 | 16 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/05/2026 | 03/25/2026 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BEVERLY | 189868 | 01915 | 4800 | Solar | 05_01_552L1 | 09/10/2018 | 10/18/2018 | 26 | 17 | 9 |  |  | 33 | 14 | 19 |  |  | 0 | 0 | 0 | 10/19/2018 | 12/08/2018 | 33 | 14 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 709990 | 01913 | 7.98 | Solar | 05_01_8W2 | 08/06/2025 | 09/18/2025 | 9 | 4 | 5 | 09/19/2025 | 09/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | BOXFORD | 369869 | 01921 | 66.6 | Solar | 05_05_28W50 | 07/22/2021 | 01/04/2022 | 7 | 0 | 7 | 08/02/2021 | 08/02/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2021 |  | 10/31/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2022 | Connected |  | N
National Grid | BILLERICA | 174712 | 01862 | 19.35 | Solar | 05_05_320W3 | 06/23/2013 | 06/23/2013 | 7 | 0 | 7 | 07/03/2013 | 07/03/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2013 |  | 12/2/2013 | N | EXP | 143 |  |  | 0 | 0 | 0 | 8/29/2013 | 8/29/2013 | 11/12/2013 | Connected |  | N
National Grid | SALISBURY | 326457 | 01952 | 9.86 | Solar | 05_12_51L1 | 11/18/2020 | 11/23/2020 | 2 | 0 | 2 | 11/24/2020 | 11/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 |  | 11/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2021 | Connected |  | N
National Grid | SHIRLEY | 710143 | 01464 | 7.15 | Solar | 05_14_275L2 | 08/07/2025 | 09/11/2025 | 6 | 0 | 6 | 09/25/2025 | 09/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2026 | Connected |  | N
National Grid | OXFORD | 177771 | 01540 | 15.2 | Solar | 05_14_56L3 | 10/10/2017 | 10/10/2017 | 13 | 4 | 9 | 11/06/2017 | 11/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 10/16/2018 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  | 5/23/2018 | Connected |  | N
National Grid | SPENCER | 325147 | 01562 | 7.68 | Solar | 05_14_70L1 | 01/06/2021 | 02/17/2021 | 28 | 28 | 0 | 02/18/2021 | 02/18/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2021 |  | 2/17/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 440658 | 01607 | 7.6 | Solar | 05_14_7L1 | 06/29/2022 | 06/30/2022 | 1 | 0 | 1 | 07/01/2022 | 07/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 | 06/29/2022 | 8/30/2023 | Y | EXP | 365 | 11/02/2022 | 11/08/2022 | 7 | 0 | 7 |  |  | 11/10/2022 | Connected |  | N
National Grid | FALL RIVER | 176051 | 02720 | 184 | Solar | 05_01_227W1 | 01/12/2015 | 01/12/2015 | 11 | 0 | 11 | 01/29/2015 | 01/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2015 |  | 7/31/2015 | N | EXP | 168 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 2/4/2016 | Connected |  | N
National Grid | GRAFTON | 734311 | 01560 | 7.6 | Solar | 05_01_406L3 | 11/20/2025 | 11/26/2025 | 5 | 2 | 3 | 12/18/2025 | 12/18/2025 | 71 | 53 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BEVERLY | 189663 | 01915 | 15.2 | Solar | 05_01_552L1 | 06/29/2018 | 06/29/2018 | 8 | 7 | 1 | 07/13/2018 | 07/13/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 657038 | 01913 | 7.6 | Solar | 05_01_9J302 | 11/26/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 4/13/2026 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ANDOVER | 397063 | 01845 | 1750 | Solar | 05_05_28W50 | 03/14/2022 |  | 162 | 153 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 175435 | 01862 | 28 | Solar | 05_05_320W3 | 11/24/2014 | 11/24/2014 | 5 | 3 | 2 | 12/03/2014 | 12/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2014 |  | 3/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 1/16/2015 | 1/16/2015 | 6/23/2015 | Connected |  | N
National Grid | SALISBURY | 333031 | 01952 | 100 | Solar | 05_12_51L1 | 03/19/2021 | 12/08/2021 | 11 | 0 | 11 | 04/06/2021 | 04/06/2021 | 129 | 106 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 343628 | 01523 | 499 | Solar | 05_14_275L4 | 07/14/2021 | 08/23/2021 | 28 | 19 | 9 |  |  | 28 | 2 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2022 | 07/14/2021 |  | Y | STD | 336 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | OXFORD | 177817 | 01540 | 11.4 | Solar | 05_14_56L3 | 04/04/2017 | 04/04/2017 | 2 | 0 | 2 | 04/07/2017 | 04/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 4/10/2018 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/22/2017 | 9/22/2017 | 9/22/2017 | Connected |  | N
National Grid | SPENCER | 372170 | 01535 | 7.6 | Solar | 05_14_70L1 | 08/09/2021 | 08/10/2021 | 1 | 0 | 1 | 08/11/2021 | 08/11/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2021 |  | 9/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N
National Grid | WORCESTER | 628133 | 01607 | 7.6 | Solar | 05_14_7L1 | 07/30/2024 | 08/14/2024 | 3 | 0 | 3 | 08/15/2024 | 08/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 176714 | 02720 | 15.2 | Solar | 05_01_227W1 | 01/08/2016 | 01/08/2016 | 3 | 3 | 0 | 01/13/2016 | 01/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2016 |  | 1/13/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/12/2016 | 10/12/2016 | 10/19/2016 | Connected |  | N
National Grid | WHITINSVILLE | 745318 | 01588 | 7.98 | Solar | 05_01_406L3 | 01/14/2026 | 01/20/2026 | 5 | 1 | 4 | 03/09/2026 | 03/09/2026 | 18 | 6 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BEVERLY | 195817 | 01915 | 0 | Solar | 05_01_552L1 | 11/07/2018 |  | 151 | 25 | 126 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 689482 | 01913 | 16.64 | Solar | 05_01_9J302 | 05/06/2025 | 05/12/2025 | 4 | 0 | 4 | 05/13/2025 | 05/13/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | BOXFORD | 455939 | 01921 | 196.175 | Solar | 05_05_28W50 | 09/02/2022 | 10/04/2022 | 22 | 13 | 9 |  |  | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176462 | 01852 | 10 | Solar | 05_05_320W3 | 02/04/2016 | 02/04/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/13/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 5/16/2016 | 5/16/2016 | 5/18/2016 | Connected |  | N
National Grid | SALISBURY | 335686 | 01952 | 7.68 | Solar | 05_12_51L1 | 01/20/2021 | 02/10/2021 | 15 | 14 | 1 | 02/11/2021 | 02/11/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2021 | 01/20/2021 | 2/10/2022 | Y | EXP | 365 | 05/15/2021 | 05/14/2021 | 0 | 0 | 0 |  |  | 5/18/2021 | Connected |  | N
National Grid | LEOMINSTER | 616127 | 01453 | 1996 | Solar | 05_14_275L4 | 08/12/2024 | 09/04/2024 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/05/2024 | 09/18/2024 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | OXFORD | 178587 | 01540 | 20 | Solar | 05_14_56L3 | 03/13/2018 | 03/13/2018 | 13 | 0 | 13 | 04/02/2018 | 04/02/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/19/2019 | N | EXP | 312 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 401363 | 01562 | 0 | Battery Add-On | 05_14_70L1 | 05/11/2022 | 06/16/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/21/2022 | 07/20/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 753177 | 01604 | 3.8 | Solar | 05_14_7L2 | 02/25/2026 | 03/02/2026 | 3 | 0 | 3 | 03/16/2026 | 03/16/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 177900 | 02720 | 3875 | Solar | 05_01_227W1 | 06/15/2017 | 06/15/2017 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2017 | 09/22/2017 | 46 | 0 | 46 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 | 06/15/2017 | 6/18/2021 | Y | STD | 340 | 11/04/2020 | 03/12/2021 | 128 | 0 | 128 | 5/20/2021 | 5/28/2021 | 6/11/2021 | Connected |  | N
National Grid | NORTHBRIDGE | 754135 | 01534 | 11.4 | Solar | 05_01_406L3 | 03/03/2026 | 03/05/2026 | 2 | 0 | 2 | 03/06/2026 | 03/06/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BEVERLY | 193213 | 01915 | 2988 | Solar | 05_01_552L1 | 01/09/2019 | 01/30/2019 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2019 | 02/27/2019 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 578629 | 01913 | 299 | Solar | 05_01_9J303 | 01/29/2024 |  | 470 | 25 | 445 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 487714 | 01921 | 3.8 | Solar | 05_05_28W50 | 01/23/2023 | 01/24/2023 | 1 | 0 | 1 | 01/25/2023 | 01/25/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2023 |  | 3/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2023 | Connected |  | N
National Grid | BILLERICA | 176681 | 01862 | 7.74 | Solar | 05_05_320W3 | 01/04/2016 | 01/04/2016 | 2 | 2 | 0 | 01/08/2016 | 01/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2016 |  | 1/11/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 | 3/11/2016 | 3/11/2016 | 3/17/2016 | Connected |  | N
National Grid | SALISBURY | 335860 | 01952 | 5.52 | Solar | 05_12_51L1 | 01/18/2021 | 01/25/2021 | 4 | 0 | 4 | 04/13/2021 | 04/13/2021 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 723192 | 01453 | 10 | Solar | 05_14_275L4 | 10/01/2025 | 10/07/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 | 10/01/2025 | 12/4/2026 | Y | EXP | 365 | 03/07/2026 |  | 26 | 0 | 26 |  |  |  | Construction |  | N
National Grid | OXFORD | 189024 | 01540 | 0 | Solar | 05_14_56L3 | 08/24/2018 | 09/26/2018 | 22 | 15 | 7 | 09/27/2018 | 09/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2018 | 08/24/2018 |  | Y | EXP | 365 | 03/22/2019 | 03/21/2019 | 0 | 0 | 0 |  |  | 7/3/2019 | Connected |  | N
National Grid | SPENCER | 414875 | 01562 | 15.2 | Solar | 05_14_70L1 | 03/01/2022 | 03/02/2022 | 1 | 0 | 1 | 03/03/2022 | 03/03/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 174732 | 01604 | 32.9 | Solar | 05_14_7L2 | 01/04/2013 | 01/04/2013 | 8 | 0 | 8 | 01/17/2013 | 01/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2013 | 01/04/2013 | 3/29/2013 | Y | EXP | 11 |  |  | 0 | 0 | 0 | 4/17/2013 | 4/17/2013 | 8/15/2013 | Connected |  | N
National Grid | FALL RIVER | 184857 | 02720 | 4980 | Solar | 05_01_227W1 | 05/09/2018 | 06/06/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/07/2018 | 07/25/2018 | 33 | 13 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 05/09/2018 | 1/17/2024 | Y | STD | 880 | 08/12/2022 | 01/18/2023 | 160 | 0 | 160 | 12/15/2023 | 12/19/2023 | 12/29/2023 | Connected |  | N
National Grid | GRAFTON | 174420 | 01519 | 950 | Solar | 05_01_406L3 | 06/27/2012 | 06/27/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2012 | 10/02/2012 | 60 | 0 | 60 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 06/27/2012 | 10/30/2012 | Y | STD | 135 | 08/21/2013 | 01/17/2014 | 101 | 0 | 101 | 11/12/2013 | 11/12/2013 | 12/9/2013 | Connected |  | N
National Grid | BEVERLY | 208846 | 01915 | 6 | Solar | 05_01_552L1 | 03/26/2019 |  | 69 | 26 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 595193 | 01913 | 7.6 | Solar | 05_01_9J303 | 03/27/2024 | 03/29/2024 | 2 | 0 | 2 | 04/01/2024 | 04/01/2024 | 8 | 0 | 8 | 04/23/2024 | 05/15/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 05/15/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 5/15/2025 | N | EXP | 365 | 05/16/2024 | 05/15/2024 | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | BOXFORD | 521951 | 01921 | 6 | Solar | 05_05_28W50 | 05/03/2023 | 05/05/2023 | 2 | 0 | 2 | 05/08/2023 | 05/08/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  | 7/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 176758 | 01876 | 6 | Solar | 05_05_320W3 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/29/2016 | 03/02/2016 | 2 | 0 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 3/1/2017 | N | STD | 364 |  |  | 0 | 0 | 0 | 5/13/2016 | 5/13/2016 | 5/18/2016 | Connected |  | N
National Grid | SALISBURY | 377712 | 01952 | 67 | Solar | 05_12_51L1 | 09/10/2021 | 11/17/2021 | 46 | 36 | 10 | 11/18/2021 | 11/18/2021 | 99 | 51 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2022 | 09/10/2021 | 4/30/2023 | Y | EXP | 157 |  |  | 0 | 0 | 0 |  |  | 5/12/2023 | Connected |  | N
National Grid | LANCASTER | 174182 | 01523 | 190 | Solar | 05_14_275L4 | 11/14/2011 | 11/14/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2012 |  | 3/19/2012 | N | EXP | 5 |  |  | 0 | 0 | 0 | 6/26/2012 | 6/26/2012 | 7/5/2012 | Connected |  | N
National Grid | OXFORD | 198628 | 01540 | 20 | Solar | 05_14_56L3 | 10/17/2018 | 10/31/2018 | 3 | 3 | 0 | 11/01/2018 | 11/01/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 1/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2019 | Connected |  | N
National Grid | SPENCER | 419848 | 01562 | 0 | Other | 05_14_70L1 | 06/29/2022 | 07/12/2022 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2022 | 08/09/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177074 | 01604 | 10 | Solar | 05_14_7L2 | 08/03/2016 | 08/03/2016 | 1 | 1 | 0 | 08/05/2016 | 08/05/2016 | 179 | 0 | 179 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2016 | 08/03/2016 | 8/9/2017 | Y | EXP | 363 | 10/17/2016 | 10/26/2016 | 7 | 0 | 7 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 188006 | 02720 | 11.4 | Solar | 05_01_227W1 | 06/13/2018 | 06/13/2018 | 4 | 0 | 4 | 06/21/2018 | 06/21/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 174421 | 01534 | 950 | Solar | 05_01_406L3 | 06/27/2012 | 06/27/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2012 | 10/02/2012 | 60 | 0 | 60 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 06/27/2012 | 10/30/2012 | Y | STD | 135 | 08/21/2013 | 01/17/2014 | 101 | 0 | 101 | 11/12/2013 | 11/12/2013 | 12/9/2013 | Connected |  | N
National Grid | BEVERLY | 220677 | 01915 | 5.12 | Solar | 05_01_552L1 | 05/20/2019 | 08/27/2019 | 68 | 67 | 1 | 08/28/2019 | 08/28/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 602571 | 01913 | 6 | Solar | 05_01_9J303 | 04/10/2024 | 04/15/2024 | 3 | 0 | 3 | 04/16/2024 | 04/16/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 537229 | 01921 | 4.93 | Solar | 05_05_28W50 | 08/21/2023 | 08/29/2023 | 7 | 6 | 1 | 08/30/2023 | 08/30/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 176786 | 01862 | 0 | Solar | 05_05_320W3 | 01/14/2016 | 01/14/2016 | 0 | 0 | 0 | 01/15/2016 | 01/15/2016 | 228 | 0 | 228 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/20/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 495132 | 01952 | 7.6 | Solar | 05_12_51L1 | 03/07/2023 | 03/09/2023 | 2 | 0 | 2 | 03/10/2023 | 03/10/2023 | 65 | 50 | 15 | 06/16/2023 | 08/24/2023 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 08/24/2023 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 12/16/2024 | N | EXP | 365 | 01/03/2024 | 01/02/2024 | 0 | 0 | 0 |  |  | 1/24/2024 | Connected |  | N
National Grid | LANCASTER | 174265 | 01523 | 19.89 | Solar | 05_14_275L4 | 11/16/2011 | 11/16/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2012 |  | 1/14/2012 | N | EXP | 60 |  |  | 0 | 0 | 0 | 6/26/2012 | 6/26/2012 | 7/16/2012 | Connected |  | N
National Grid | CHARLTON | 203369 | 01507 | 0 | Solar | 05_14_56L3 | 12/12/2018 | 12/24/2018 | 7 | 0 | 7 | 12/26/2018 | 12/26/2018 | 26 | 9 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2019 | Connected |  | N
National Grid | SPENCER | 444078 | 01562 | 9.8 | Solar | 05_14_70L1 | 07/20/2022 |  | 38 | 26 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177273 | 01604 | 20 | Solar | 05_14_7L2 | 02/06/2017 | 02/06/2017 | 6 | 2 | 4 | 02/14/2017 | 02/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2017 |  | 2/11/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 5/15/2017 | 5/15/2017 | 5/15/2017 | Connected |  | N
National Grid | FALL RIVER | 272564 | 02720 | 0 | Solar | 05_01_227W1 | 02/05/2020 | 02/20/2020 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2020 | 03/13/2020 | 15 | 7 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2021 | 02/05/2020 | 9/8/2022 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 174918 | 01560 | 13.12 | Solar | 05_01_406L3 | 02/26/2013 | 02/26/2013 | 7 | 2 | 5 | 03/13/2013 | 03/13/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2013 |  | 5/31/2013 | N | EXP | 70 |  |  | 0 | 0 | 0 | 9/4/2013 | 9/4/2013 | 11/20/2013 | Connected |  | N
National Grid | BEVERLY | 231646 | 01915 | 6.4 | Solar | 05_01_552L1 | 07/02/2019 | 07/17/2019 | 10 | 10 | 0 | 07/18/2019 | 07/18/2019 | 53 | 45 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2019 |  | 7/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2020 | Connected |  | N
National Grid | SALISBURY | 632680 | 01952 | 6 | Solar | 05_01_9J303 | 08/14/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  | 10/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | BOXFORD | 582560 | 01921 | 20 | Battery Add-On | 05_05_28W50 | 01/10/2024 | 01/22/2024 | 7 | 4 | 3 | 04/11/2024 | 04/11/2024 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 |  | 6/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2024 | Connected |  | N
National Grid | BILLERICA | 176832 | 01862 | 10 | Solar | 05_05_320W3 | 02/26/2016 | 02/26/2016 | 6 | 6 | 0 | 03/08/2016 | 03/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2016 |  | 3/5/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 | 6/1/2016 | 6/1/2016 | 6/17/2016 | Connected |  | N
National Grid | SALISBURY | 518913 | 01952 | 10 | Solar | 05_12_51L1 | 09/29/2023 | 10/06/2023 | 6 | 3 | 3 | 10/10/2023 | 10/10/2023 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 174476 | 01523 | 500 | Solar | 05_14_275L4 | 07/18/2012 | 07/18/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 213064 | 01507 | 0 | Solar | 05_14_56L3 | 03/11/2019 | 03/21/2019 | 7 | 0 | 7 | 03/22/2019 | 03/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  | 4/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | SPENCER | 578847 | 01562 | 0 | Solar | 05_14_70L1 | 01/22/2024 | 01/24/2024 | 2 | 0 | 2 | 01/25/2024 | 01/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N
National Grid | WORCESTER | 177398 | 01604 | 57.6 | Solar | 05_14_7L2 | 06/28/2016 | 06/28/2016 | 7 | 7 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2016 |  | 7/5/2017 | N | EXP | 345 |  |  | 0 | 0 | 0 | 9/22/2016 | 9/22/2016 | 9/22/2016 | Connected |  | N
National Grid | FALL RIVER | 287827 | 02720 | 4950 | Other | 05_01_227W1 | 05/06/2020 | 05/12/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/13/2020 | 06/02/2020 | 13 | 1 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 175066 | 01560 | 1500 | Solar | 05_01_406L3 | 03/28/2013 | 03/28/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2013 | 06/24/2013 | 51 | 0 | 51 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2014 | 03/28/2013 | 5/11/2018 | Y | STD | 1572 |  |  | 0 | 0 | 0 | 4/16/2018 | 4/16/2018 | 5/10/2018 | Connected |  | N
National Grid | BEVERLY | 234351 | 01915 | 10 | Solar | 05_01_552L1 | 07/16/2019 | 07/25/2019 | 7 | 7 | 0 | 07/26/2019 | 07/26/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 |  | 7/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2020 | Connected |  | N
National Grid | SALISBURY | 645660 | 01952 | 5.76 | Solar | 05_01_9J303 | 10/25/2024 | 11/12/2024 | 7 | 2 | 5 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | BOXFORD | 614273 | 01921 | 3.8 | Solar | 05_05_28W50 | 05/30/2024 | 06/05/2024 | 0 | 0 | 0 | 06/06/2024 | 06/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/30/2024 | 11/30/2025 | Y | EXP | 365 | 07/26/2024 | 09/03/2024 | 40 | 0 | 40 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 176917 | 01876 | 10 | Solar | 05_05_320W3 | 05/05/2016 | 05/05/2016 | 1 | 1 | 0 | 05/09/2016 | 05/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2016 |  | 5/11/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N
National Grid | SALISBURY | 521346 | 01952 | 10 | Solar | 05_12_51L1 | 04/26/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 174475 | 01523 | 2000 | Solar | 05_14_275L4 | 07/18/2012 | 07/18/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2012 | 10/17/2012 | 57 | 0 | 57 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 236527 | 01540 | 0 | Solar | 05_14_56L3 | 06/13/2019 | 06/18/2019 | 2 | 0 | 2 | 06/19/2019 | 06/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2019 | 06/13/2019 | 6/13/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2020 | Connected |  | N
National Grid | SPENCER | 605506 | 01562 | 10 | Solar | 05_14_70L1 | 04/23/2024 | 04/26/2024 | 1 | 0 | 1 | 04/29/2024 | 04/29/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 | 04/23/2024 | 5/20/2025 | Y | EXP | 365 | 06/26/2024 | 08/09/2024 | 45 | 0 | 45 |  |  | 8/22/2024 | Connected |  | N
National Grid | WORCESTER | 178230 | 01604 | 7.6 | Solar | 05_14_7L2 | 01/03/2018 | 01/03/2018 | 21 | 15 | 6 | 02/06/2018 | 02/06/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2018 |  | 1/10/2019 | N | EXP | 337 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 315362 | 02720 | 0 | Other | 05_01_227W1 | 11/05/2020 | 11/12/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 | 11/30/2020 | 11 | 1 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11/05/2020 | 8/24/2025 | Y | STD | 616 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITINSVILLE | 175246 | 01588 | 800 | Solar | 05_01_406L3 | 11/04/2014 | 11/04/2014 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2014 | 01/05/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 256903 | 01915 | 10 | Solar | 05_01_552L1 | 10/09/2019 | 10/11/2019 | 1 | 1 | 0 | 10/15/2019 | 10/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2019 | 10/09/2019 | 10/9/2020 | Y | EXP | 365 | 02/05/2020 | 03/02/2020 | 26 | 0 | 26 |  |  | 4/22/2020 | Connected |  | N
National Grid | SALISBURY | 650688 | 01952 | 5.76 | Solar | 05_01_9J303 | 11/11/2024 | 01/14/2025 | 0 | 0 | 0 | 01/15/2025 | 01/15/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | BOXFORD | 620166 | 01921 | 7.6 | Solar | 05_05_28W50 | 06/24/2024 | 07/15/2024 | 3 | 0 | 3 | 07/16/2024 | 07/16/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | BILLERICA | 177179 | 01862 | 9 | Solar | 05_05_320W3 | 06/06/2016 | 06/06/2016 | 1 | 1 | 0 | 06/08/2016 | 06/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 |  | 6/12/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/22/2016 | 11/28/2016 | Connected |  | N
National Grid | SALISBURY | 575451 | 01952 | 3.48 | Solar | 05_12_51L1 | 02/08/2024 | 02/14/2024 | 4 | 0 | 4 | 02/15/2024 | 02/15/2024 | 84 | 79 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 |  | 6/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | LANCASTER | 175416 | 01523 | 4500 | Solar | 05_14_275L4 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2014 | 08/14/2014 | 20 | 18 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 | 07/09/2014 | 12/31/2016 | Y | STD | 655 | 08/30/2016 | 01/30/2017 | 102 | 0 | 102 | 12/14/2016 | 12/14/2016 | 12/22/2016 | Connected |  | N
National Grid | OXFORD | 285483 | 01540 | 9.28 | Solar | 05_14_56L3 | 03/27/2020 | 03/31/2020 | 2 | 2 | 0 | 04/01/2020 | 04/01/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 | 03/27/2020 | 3/31/2021 | Y | EXP | 365 | 06/09/2020 | 06/25/2020 | 16 | 0 | 16 |  |  | 10/7/2020 | Connected |  | N
National Grid | SPENCER | 605258 | 01562 | 10 | Solar | 05_14_70L1 | 05/23/2024 | 05/28/2024 | 2 | 0 | 2 | 05/29/2024 | 05/29/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 198767 | 01604 | 13.8 | Solar | 05_14_7L2 | 12/03/2018 | 12/13/2018 | 7 | 0 | 7 | 12/14/2018 | 12/14/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 336841 | 02720 | 6 | Solar | 05_01_227W1 | 02/04/2021 | 02/11/2021 | 4 | 1 | 3 | 02/12/2021 | 02/12/2021 | 29 | 6 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2021 | 02/04/2021 | 5/1/2022 | Y | EXP | 365 | 07/09/2021 | 10/05/2021 | 74 | 3 | 71 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 175504 | 01519 | 1000 | Solar | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 265279 | 01915 | 0 | Other | 05_01_552L1 | 02/24/2020 | 03/17/2020 | 15 | 11 | 4 |  |  | 6 | 6 | 0 |  |  | 0 | 0 | 0 | 08/24/2020 | 10/24/2020 | 43 | 26 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 678617 | 01952 | 13.36 | Solar | 05_01_9J303 | 03/17/2025 | 04/04/2025 | 2 | 0 | 2 | 04/10/2025 | 04/10/2025 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 | 03/17/2025 | 5/20/2026 | Y | EXP | 365 | 11/07/2025 | 12/01/2025 | 25 | 0 | 25 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 619689 | 01921 | 7.6 | Solar | 05_05_28W50 | 06/21/2024 | 07/05/2024 | 6 | 2 | 4 | 07/08/2024 | 07/08/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 | 06/21/2024 | 7/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | LOWELL | 177472 | 01852 | 15.2 | Solar | 05_05_320W3 | 03/02/2017 | 03/02/2017 | 239 | 238 | 1 | 02/12/2018 | 02/12/2018 | 77 | 76 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2018 |  | 6/30/2020 | N | EXP | 92 |  |  | 0 | 0 | 0 |  |  | 6/2/2020 | Connected |  | N
National Grid | SALISBURY | 578751 | 01952 | 0 | Solar | 05_12_51L1 | 12/19/2023 | 12/22/2023 | 2 | 2 | 0 | 12/26/2023 | 12/26/2023 | 38 | 16 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 2/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | LANCASTER | 176775 | 01523 | 2800 | Solar | 05_14_275L4 | 11/03/2015 | 11/03/2015 | 53 | 53 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2016 | 02/04/2016 | 8 | 0 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/9/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 290378 | 01540 | 0 | Solar | 05_14_56L3 | 05/04/2020 | 05/12/2020 | 5 | 0 | 5 | 05/13/2020 | 05/13/2020 | 66 | 56 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2020 |  | 11/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | N
National Grid | SPENCER | 621445 | 01562 | 18.115 | Solar | 05_14_70L1 | 06/28/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2024 |  | 8/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | Y
National Grid | WORCESTER | 213965 | 01604 | 0 | Solar | 05_14_7L2 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2019 | Connected |  | N
National Grid | FALL RIVER | 431629 | 02720 | 11.4 | Solar | 05_01_227W1 | 07/13/2022 | 07/15/2022 | 2 | 0 | 2 | 07/18/2022 | 07/18/2022 | 62 | 42 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 175510 | 01560 | 1000 | Solar | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 264202 | 01915 | 5000 | Other | 05_01_552L1 | 02/12/2020 | 03/16/2020 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2020 | 04/01/2020 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 608618 | 01913 | 10 | Solar | 05_01_9J306 | 05/03/2024 | 05/24/2024 | 1 | 0 | 1 | 05/28/2024 | 05/28/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2025 | Connected |  | Y
National Grid | ANDOVER | 646203 | 01845 | 3.839 | Solar | 05_05_28W50 | 10/10/2024 | 11/06/2024 | 15 | 10 | 5 | 11/07/2024 | 11/07/2024 | 73 | 50 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 177840 | 01862 | 4980 | Solar | 05_05_320W3 | 10/17/2017 | 10/17/2017 | 17 | 12 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 | 11/30/2017 | 18 | 3 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 | 10/17/2017 | 12/31/2021 | Y | STD | 470 | 09/04/2021 | 12/30/2021 | 118 | 4 | 114 |  |  | 12/28/2021 | Connected |  | N
National Grid | SALISBURY | 622202 | 01952 | 6 | Solar | 05_12_51L1 | 07/04/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 | 07/04/2024 | 8/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | SHIRLEY | 177418 | 01464 | 1050 | Solar | 05_14_275L4 | 12/01/2016 | 12/01/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/06/2016 | 03/03/2017 | 59 | 44 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2018 | 12/01/2016 | 1/6/2020 | Y | STD | 620 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 318384 | 01507 | 10 | Solar | 05_14_56L3 | 10/09/2020 | 10/14/2020 | 2 | 2 | 0 | 10/15/2020 | 10/15/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2021 | Connected |  | N
National Grid | SPENCER | 648217 | 01562 | 7.6 | Solar | 05_14_70L1 | 10/30/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 | 10/30/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | WORCESTER | 306671 | 01604 | 9.8 | Solar | 05_14_7L2 | 09/15/2020 | 09/21/2020 | 3 | 0 | 3 | 09/22/2020 | 09/22/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 | 09/15/2020 | 12/14/2022 | Y | EXP | 365 | 06/29/2021 | 08/06/2021 | 38 | 0 | 38 |  |  | 9/10/2021 | Connected |  | Y
National Grid | FALL RIVER | 441594 | 02720 | 0 | Other | 05_01_227W1 | 09/20/2022 | 10/20/2022 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2022 | 11/09/2022 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 175509 | 01534 | 1000 | Solar | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 281057 | 01915 | 10 | Solar | 05_01_552L1 | 04/06/2020 |  | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 610910 | 01913 | 16.4 | Solar | 05_01_9J306 | 05/17/2024 | 05/21/2024 | 2 | 0 | 2 | 05/22/2024 | 05/22/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2024 | Connected |  | N
National Grid | BOXFORD | 651174 | 01921 | 7.6 | Solar | 05_05_28W50 | 11/11/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 11/11/2024 | 2/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | BILLERICA | 178280 | 01862 | 2930 | Solar | 05_05_320W3 | 02/23/2018 | 02/28/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2018 | 03/27/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2018 | 02/23/2018 | 11/22/2024 | Y | STD | 393 | 05/21/2022 | 05/14/2024 | 724 | 625 | 99 |  |  | 10/29/2024 | Connected |  | N
National Grid | SALISBURY | 629790 | 01952 | 10 | Solar | 05_12_51L1 | 08/02/2024 | 08/30/2024 | 16 | 14 | 2 | 09/03/2024 | 09/03/2024 | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 177880 | 01453 | 15.2 | Solar | 05_14_275L4 | 10/18/2017 | 10/18/2017 | 7 | 6 | 1 | 10/31/2017 | 10/31/2017 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2017 |  | 10/24/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 7/18/2018 | Connected |  | N
National Grid | OXFORD | 317831 | 01540 | 25 | Solar | 05_14_56L3 | 10/07/2020 | 10/09/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2021 | Connected |  | N
National Grid | SPENCER | 648708 | 01562 | 10 | Solar | 05_14_70L1 | 11/04/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/04/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | WORCESTER | 345471 | 01604 | 500 | Solar | 05_14_7L2 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 |  |  | 169 | 33 | 136 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 477515 | 02720 | 15.2 | Solar | 05_01_227W1 | 11/22/2022 | 11/29/2022 | 4 | 0 | 4 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2022 |  | 4/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | N
National Grid | NORTHBRIDGE | 175505 | 01534 | 1000 | Solar | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 288064 | 01915 | 0 | Other | 05_01_552L1 | 05/15/2020 | 05/27/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2020 | 09/27/2020 | 24 | 20 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 665392 | 01913 | 7.6 | Solar | 05_01_9J306 | 01/13/2025 | 02/14/2025 | 19 | 14 | 5 | 02/18/2025 | 02/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 | 01/13/2025 | 4/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 657561 | 01845 | 5.76 | Solar | 05_05_28W50 | 11/28/2024 | 01/15/2025 | 20 | 16 | 4 | 01/16/2025 | 01/16/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 | 11/28/2024 | 3/11/2026 | Y | EXP | 365 | 03/20/2025 | 05/29/2025 | 71 | 0 | 71 |  |  | 7/30/2025 | Connected |  | N
National Grid | BILLERICA | 178583 | 01862 | 225 | Solar | 05_05_320W3 | 01/31/2018 | 01/31/2018 | 0 | 0 | 0 | 02/16/2018 | 02/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2018 | 01/31/2018 | 2/6/2019 | Y | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 2/20/2019 | Connected |  | N
National Grid | SALISBURY | 651826 | 01952 | 7.6 | Solar | 05_12_51L1 | 11/04/2024 | 11/13/2024 | 5 | 1 | 4 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 11/04/2024 | 1/5/2026 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  | 2/22/2025 | Connected |  | N
National Grid | LEOMINSTER | 178340 | 01453 | 3294 | Solar | 05_14_275L4 | 11/20/2017 | 11/20/2017 | 63 | 50 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 03/28/2018 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 | 11/20/2017 | 12/31/2019 | Y | STD | 390 | 10/11/2019 | 05/20/2020 | 222 | 0 | 222 |  |  | 12/26/2019 | Connected |  | N
National Grid | OXFORD | 347094 | 01540 | 9.966 | Solar | 05_14_56L3 | 03/26/2021 | 04/09/2021 | 10 | 10 | 0 | 04/12/2021 | 04/12/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 | 03/26/2021 | 8/17/2022 | Y | EXP | 365 | 08/04/2021 | 08/12/2021 | 9 | 0 | 9 |  |  | 11/3/2021 | Connected |  | N
National Grid | SPENCER | 652988 | 01562 | 3.8 | Solar | 05_14_70L1 | 11/14/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | WORCESTER | 346665 | 01610 | 250 | Solar | 05_14_7L2 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 | 04/26/2021 | 04/26/2021 | 193 | 192 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 504134 | 02720 | 7.6 | Solar | 05_01_227W1 | 02/23/2023 |  | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 175540 | 01534 | 1000 | Solar | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 330669 | 01915 | 9.8 | Solar | 05_01_552L1 | 12/09/2020 | 12/17/2020 | 5 | 0 | 5 | 12/18/2020 | 12/18/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 |  | 3/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2021 | Connected |  | N
National Grid | SALISBURY | 718328 | 01952 | 7.6 | Solar | 05_01_9J306 | 09/10/2025 | 09/18/2025 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 662945 | 01921 | 6 | Solar | 05_05_28W50 | 12/30/2024 | 04/09/2025 | 3 | 0 | 3 | 04/10/2025 | 04/10/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | BILLERICA | 178624 | 01862 | 5 | Solar | 05_05_320W3 | 03/15/2018 | 03/15/2018 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2018 |  | 3/20/2019 | N | EXP | 323 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | SALISBURY | 656350 | 01952 | 0 | Battery Add-On | 05_12_51L1 | 11/22/2024 | 11/26/2024 | 2 | 0 | 2 | 11/27/2024 | 11/27/2024 | 188 | 170 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 178415 | 01464 | 6.6 | Solar | 05_14_275L4 | 11/27/2017 | 11/27/2017 | 32 | 31 | 1 | 01/16/2018 | 01/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2018 | 11/27/2017 | 12/3/2018 | Y | EXP | 321 | 06/22/2018 | 08/03/2018 | 42 | 0 | 42 |  |  | 11/15/2018 | Connected |  | N
National Grid | CHARLTON | 365918 | 01507 | 15.36 | Solar | 05_14_56L3 | 06/24/2021 | 06/30/2021 | 4 | 0 | 4 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 655124 | 01562 | 3.8 | Solar | 05_14_70L1 | 11/20/2024 | 02/25/2025 | 46 | 41 | 5 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 467964 | 01610 | 15.2 | Solar | 05_14_7L2 | 10/13/2022 | 12/12/2022 | 40 | 39 | 1 | 12/13/2022 | 12/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 |  | 1/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2023 | Connected |  | N
National Grid | FALL RIVER | 532473 | 02720 | 15.2 | Solar | 05_01_227W1 | 06/08/2023 | 06/12/2023 | 2 | 0 | 2 | 06/13/2023 | 06/13/2023 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  | 9/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2023 | Connected |  | N
National Grid | GRAFTON | 175653 | 01560 | 684 | Solar | 05_01_406L3 | 05/05/2014 | 05/05/2014 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2014 | 09/04/2014 | 76 | 20 | 56 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2015 | 05/05/2014 | 12/30/2015 | Y | STD | 285 | 10/22/2015 | 12/22/2015 | 41 | 0 | 41 | 12/11/2015 | 12/11/2015 | 12/30/2015 | Connected |  | N
National Grid | BEVERLY | 346050 | 01915 | 11.4 | Solar | 05_01_552L1 | 03/10/2021 | 03/16/2021 | 3 | 0 | 3 | 03/17/2021 | 03/17/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2021 |  | 7/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2021 | Connected |  | N
National Grid | AMESBURY | 595739 | 01913 | 10 | Solar | 05_01_9J307 | 03/15/2024 | 06/11/2024 | 52 | 50 | 2 | 06/12/2024 | 06/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | BOXFORD | 713232 | 01921 | 20 | Solar | 05_05_28W50 | 08/19/2025 | 08/26/2025 | 5 | 0 | 5 | 08/27/2025 | 08/27/2025 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | BILLERICA | 185495 | 01862 | 250 | Solar | 05_05_320W3 | 05/16/2018 | 05/16/2018 | 14 | 0 | 14 | 06/08/2018 | 06/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 |  | 7/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2019 | Connected |  | N
National Grid | SALISBURY | 656752 | 01952 | 7.6 | Solar | 05_12_51L1 | 11/25/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/25/2024 | 2/24/2026 | Y | EXP | 365 | 06/11/2025 | 11/25/2025 | 168 | 0 | 168 |  |  | 12/1/2025 | Connected |  | N
National Grid | LANCASTER | 178618 | 01523 | 7.6 | Solar | 05_14_275L4 | 01/31/2018 | 01/31/2018 | 20 | 0 | 20 | 03/07/2018 | 03/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2018 | 01/31/2018 | 11/29/2019 | Y | EXP | 631 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | OXFORD | 378271 | 01540 | 0 | Solar | 05_14_56L3 | 08/26/2021 | 09/14/2021 | 13 | 10 | 3 | 09/15/2021 | 09/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2021 |  | 10/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2022 | Connected |  | N
National Grid | SPENCER | 701468 | 01562 | 10.725 | Solar | 05_14_70L1 | 06/26/2025 | 09/03/2025 | 12 | 10 | 2 | 09/04/2025 | 09/04/2025 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2026 | Connected |  | N
National Grid | WORCESTER | 615634 | 01610 | 3.8 | Solar | 05_14_7L2 | 06/05/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 | 06/05/2024 | 8/26/2025 | Y | EXP | 365 | 11/02/2024 | 11/12/2024 | 11 | 0 | 11 |  |  | 11/13/2024 | Connected |  | N
National Grid | FALL RIVER | 589295 | 02720 | 14.21 | Solar | 05_01_227W1 | 03/22/2024 | 03/27/2024 | 3 | 0 | 3 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | GRAFTON | 175716 | 01560 | 1000 | Solar | 05_01_406L3 | 12/26/2014 | 12/26/2014 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2015 | 02/13/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 |  | 8/1/2016 | N | STD | 301 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 452168 | 01915 | 5 | Solar | 05_01_552L1 | 10/11/2022 | 11/18/2022 | 27 | 24 | 3 | 11/21/2022 | 11/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/25/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 670182 | 01952 | 10 | Solar | 05_01_9J307 | 02/05/2025 | 04/07/2025 | 5 | 0 | 5 | 04/08/2025 | 04/08/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 409703 | 01921 | 0 | Other | 05_05_28W51 | 03/22/2022 | 04/01/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2022 | 04/05/2022 | 2 | 0 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 03/22/2022 | 12/1/2026 | Y | STD | 413 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | TEWKSBURY | 191709 | 01876 | 8 | Solar | 05_05_320W3 | 07/24/2018 | 08/10/2018 | 5 | 0 | 5 | 08/13/2018 | 08/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 677578 | 01952 | 3.8 | Solar | 05_12_51L1 | 03/12/2025 | 04/14/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 | 03/12/2025 | 6/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2025 | Connected |  | N
National Grid | LANCASTER | 187940 | 01523 | 999.9 | Solar | 05_14_275L4 | 06/13/2018 | 06/13/2018 | 4 | 3 | 1 |  |  | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2019 | 06/13/2018 | 5/17/2021 | Y | STD | 448 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 382988 | 01507 | 15.2 | Solar | 05_14_56L3 | 09/19/2021 | 11/09/2021 | 36 | 29 | 7 | 11/10/2021 | 11/10/2021 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2022 | 09/19/2021 | 3/17/2023 | Y | EXP | 365 | 02/23/2022 | 03/17/2022 | 23 | 0 | 23 |  |  | 4/21/2022 | Connected |  | N
National Grid | SPENCER | 727534 | 01562 | 5.8 | Solar | 05_14_70L1 | 10/18/2025 | 10/23/2025 | 4 | 0 | 4 | 10/24/2025 | 10/24/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2025 |  | 1/15/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2026 | Connected |  | N
National Grid | WORCESTER | 654131 | 01604 | 9.86 | Solar | 05_14_7L2 | 11/21/2024 | 12/13/2024 | 9 | 6 | 3 | 12/16/2024 | 12/16/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/21/2024 | 2/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | FALL RIVER | 591793 | 02720 | 15.2 | Solar | 05_01_227W1 | 02/21/2024 | 03/14/2024 | 16 | 11 | 5 | 03/15/2024 | 03/15/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 175931 | 01560 | 10.75 | Solar | 05_01_406L3 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2015 |  | 8/15/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 2/3/2016 | 2/3/2016 | 1/3/2018 | Connected |  | N
National Grid | BEVERLY | 367879 | 01915 | 7.6 | Solar | 05_01_552L1 | 07/22/2021 | 07/29/2021 | 6 | 5 | 1 | 07/30/2021 | 07/30/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 |  | 8/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2021 | Connected |  | N
National Grid | AMESBURY | 175980 | 01913 | 42 | Solar | 05_01_9J315 | 01/23/2015 | 01/23/2015 | 6 | 0 | 6 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2015 |  | 6/30/2015 | N | EXP | 127 |  |  | 0 | 0 | 0 | 8/20/2015 | 8/20/2015 | 8/21/2015 | Connected |  | N
National Grid | BOXFORD | 581883 | 01921 | 100 | Solar | 05_05_28W51 | 01/19/2024 | 02/08/2024 | 14 | 3 | 11 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 7/29/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | TEWKSBURY | 199879 | 01876 | 6 | Solar | 05_05_320W3 | 11/06/2018 | 12/20/2018 | 28 | 28 | 0 | 12/21/2018 | 12/21/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 715101 | 01952 | 10 | Solar | 05_12_51L1 | 08/27/2025 | 09/17/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 08/27/2025 | 11/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 194215 | 01464 | 325 | Solar | 05_14_275L4 | 08/22/2018 | 08/28/2018 | 3 | 0 | 3 | 08/29/2018 | 08/29/2018 | 101 | 1 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 398752 | 01540 | 15.2 | Solar | 05_14_56L3 | 12/01/2021 | 12/02/2021 | 1 | 0 | 1 | 12/03/2021 | 12/03/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 4/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2022 | Connected |  | N
National Grid | SPENCER | 507609 | 01562 | 450 | Solar | 05_14_70L2 | 07/07/2023 | 07/25/2023 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2023 | 08/21/2023 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 | 07/07/2023 | 1/5/2027 | Y | STD | 308 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WORCESTER | 718084 | 01604 | 9.6 | Solar | 05_14_7L2 | 09/10/2025 | 10/01/2025 | 1 | 0 | 1 | 10/08/2025 | 10/08/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2026 | Connected |  | N
National Grid | FALL RIVER | 598492 | 02720 | 20 | Solar | 05_01_227W1 | 03/21/2024 | 04/02/2024 | 8 | 6 | 2 | 04/03/2024 | 04/03/2024 | 36 | 29 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  | 6/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | NORTHBRIDGE | 176139 | 01534 | 8.39 | Solar | 05_01_406L3 | 06/26/2015 | 06/26/2015 | 0 | 0 | 0 | 07/01/2015 | 07/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 |  | 7/6/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/3/2015 | 8/3/2015 | 1/28/2016 | Connected |  | N
National Grid | BEVERLY | 405685 | 01915 | 9.8 | Solar | 05_01_552L1 | 02/03/2022 | 02/07/2022 | 2 | 0 | 2 | 02/08/2022 | 02/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 | 02/03/2022 | 5/30/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2022 | Connected |  | N
National Grid | AMESBURY | 552028 | 01913 | 5.8 | Solar | 05_01_9J321 | 11/16/2023 | 11/20/2023 | 3 | 1 | 2 | 11/21/2023 | 11/21/2023 | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 174517 | 01921 | 1000 | Solar | 05_05_28W51 | 11/11/2010 | 11/11/2010 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2011 | 02/08/2011 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2011 | 11/11/2010 | 10/31/2012 | Y | STD | 504 | 12/10/2012 | 12/13/2012 | 3 | 0 | 3 | 10/18/2013 | 10/18/2013 | 2/22/2013 | Connected |  | N
National Grid | BILLERICA | 216239 | 01862 | 3.8 | Solar | 05_05_320W3 | 04/04/2019 | 04/12/2019 | 5 | 0 | 5 | 04/15/2019 | 04/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 667830 | 01952 | 5.7 | Solar | 05_12_51L2 | 01/24/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SHIRLEY | 333336 | 01464 | 5.04 | Solar | 05_14_275L4 | 12/21/2020 | 12/22/2020 | 0 | 0 | 0 | 12/23/2020 | 12/23/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 |  | 12/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/24/2021 | Connected |  | N
National Grid | OXFORD | 410771 | 01540 | 10 | Solar | 05_14_56L3 | 02/07/2022 | 02/09/2022 | 3 | 1 | 2 | 02/10/2022 | 02/10/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2022 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2022 | Connected |  | N
National Grid | SPENCER | 708850 | 01562 | 17.16 | Solar | 05_14_70L2 | 08/08/2025 | 09/02/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 19 | 0 | 19 | 10/30/2025 | 12/01/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 12/01/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 730322 | 01604 | 3.8 | Solar | 05_14_7L2 | 10/31/2025 | 11/05/2025 | 3 | 0 | 3 | 11/06/2025 | 11/06/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2026 | Connected |  | N
National Grid | FALL RIVER | 623849 | 02720 | 7.6 | Solar | 05_01_227W1 | 07/10/2024 |  | 26 | 25 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITINSVILLE | 176751 | 01588 | 6 | Solar | 05_01_406L3 | 01/12/2016 | 01/12/2016 | 9 | 9 | 0 | 01/26/2016 | 01/26/2016 | 261 | 0 | 261 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2016 |  | 1/27/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 412613 | 01915 | 10 | Solar | 05_01_552L1 | 03/16/2022 | 03/24/2022 | 6 | 1 | 5 | 03/25/2022 | 03/25/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2022 | 03/16/2022 | 6/15/2023 | Y | EXP | 365 | 05/17/2022 | 06/14/2022 | 29 | 0 | 29 |  |  | 8/11/2022 | Connected |  | N
National Grid | AMESBURY | 642954 | 01913 | 7.6 | Solar | 05_01_9J321 | 09/27/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 174516 | 01921 | 1000 | Solar | 05_05_28W51 | 11/11/2010 | 11/11/2010 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2011 | 02/08/2011 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2011 | 11/11/2010 | 10/31/2012 | Y | STD | 504 | 10/19/2012 | 12/26/2012 | 30 | 0 | 30 | 1/25/2013 | 1/25/2013 | 2/22/2013 | Connected |  | N
National Grid | BILLERICA | 222039 | 01821 | 240 | Solar | 05_05_320W3 | 04/24/2019 | 06/03/2019 | 14 | 11 | 3 |  |  | 14 | 4 | 10 | 08/06/2019 | 08/28/2019 | 17 | 1 | 16 |  |  | 0 | 0 | 0 | 08/28/2019 | 17 | 1 | 16 |  |  | 0 | 0 | 0 | 4/27/2020 | 04/24/2019 | 1/28/2022 | Y | STD | 404 |  |  | 0 | 0 | 0 | 12/3/2021 | 1/14/2022 | 1/24/2022 | Connected |  | N
National Grid | SALISBURY | 745352 | 01952 | 3.7 | Battery Add-On | 05_12_51L2 | 01/14/2026 | 01/16/2026 | 2 | 0 | 2 | 01/20/2026 | 01/20/2026 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 339860 | 01523 | 10 | Solar | 05_14_275L4 | 02/01/2021 | 02/03/2021 | 1 | 0 | 1 | 02/04/2021 | 02/04/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2021 |  | 2/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2021 | Connected |  | N
National Grid | OXFORD | 412304 | 01540 | 7.6 | Solar | 05_14_56L3 | 02/24/2022 | 02/28/2022 | 2 | 0 | 2 | 03/01/2022 | 03/01/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/24/2022 | 6/13/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2022 | Connected |  | N
National Grid | SPENCER | 725438 | 01562 | 8.725 | Solar | 05_14_70L2 | 10/14/2025 | 10/22/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 | 10/14/2025 | 12/31/2026 | Y | EXP | 365 | 03/07/2026 |  | 26 | 0 | 26 |  |  |  | Construction |  | N
National Grid | WORCESTER | 711942 | 01604 | 5.76 | Solar | 05_14_7L4 | 08/13/2025 | 09/17/2025 | 3 | 0 | 3 | 10/06/2025 | 10/06/2025 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 631955 | 02720 | 15.2 | Solar | 05_01_227W1 | 08/23/2024 | 08/28/2024 | 3 | 0 | 3 | 08/29/2024 | 08/29/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 9/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N
National Grid | GRAFTON | 176845 | 01560 | 15 | Solar | 05_01_406L3 | 05/02/2016 | 05/02/2016 | 3 | 3 | 0 | 05/06/2016 | 05/06/2016 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2016 |  | 5/8/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 431528 | 01915 | 15.66 | Solar | 05_01_552L1 | 06/29/2022 | 08/01/2022 | 23 | 22 | 1 | 08/02/2022 | 08/02/2022 | 42 | 21 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 10/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | Connected |  | N
National Grid | AMESBURY | 175684 | 01913 | 75.6 | Solar | 05_01_9J327 | 12/24/2014 | 12/24/2014 | 4 | 1 | 3 | 01/02/2015 | 01/02/2015 | 102 | 3 | 99 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 12/24/2014 | 5/31/2015 | Y | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 174541 | 01921 | 475 | Solar | 05_05_28W51 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 232606 | 01821 | 6.72 | Solar | 05_05_320W3 | 06/20/2019 | 06/28/2019 | 5 | 0 | 5 | 07/01/2019 | 07/01/2019 | 24 | 23 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2019 | 06/20/2019 | 9/30/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2020 | Connected |  | N
National Grid | SALISBURY | 753579 | 01952 | 23 | Battery Add-On | 05_12_51L2 | 03/04/2026 | 03/09/2026 | 3 | 0 | 3 | 03/10/2026 | 03/10/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SHIRLEY | 343629 | 01464 | 499 | Solar | 05_14_275L4 | 07/14/2021 | 08/23/2021 | 28 | 19 | 9 |  |  | 28 | 2 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2022 | 07/14/2021 | 12/9/2023 | Y | STD | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 466707 | 01540 | 22.8 | Solar | 05_14_56L3 | 10/21/2022 | 10/25/2022 | 2 | 0 | 2 | 10/26/2022 | 10/26/2022 | 325 | 302 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2024 | Connected |  | N
National Grid | SPENCER | 749075 | 01562 | 11.4 | Solar | 05_14_70L2 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2026 |  | 3/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 726965 | 01604 | 0 | Battery Add-On | 05_14_7L4 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 10/23/2025 | 10/23/2025 | 61 | 47 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | FALL RIVER | 644731 | 02720 | 5.76 | Solar | 05_01_227W1 | 10/03/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | GRAFTON | 176939 | 01560 | 10 | Solar | 05_01_406L3 | 12/16/2016 | 12/16/2016 | 3 | 2 | 1 | 12/22/2016 | 12/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2016 |  | 12/24/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/12/2017 | 7/12/2017 | 7/12/2017 | Connected |  | N
National Grid | BEVERLY | 445609 | 01915 | 24 | Solar | 05_01_552L1 | 07/20/2022 | 07/21/2022 | 29 | 20 | 9 | 12/01/2022 | 12/01/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2022 |  | 1/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2023 | Connected |  | N
National Grid | AMESBURY | 719601 | 01913 | 11.5 | Solar | 05_01_9J337 | 09/23/2025 | 10/23/2025 | 20 | 17 | 3 | 10/24/2025 | 10/24/2025 | 36 | 24 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 174540 | 01845 | 950 | Solar | 05_05_28W51 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 257134 | 01821 | 2930 | Battery Add-On | 05_05_320W3 | 10/21/2019 | 11/07/2019 | 13 | 9 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2019 | 01/10/2020 | 42 | 19 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 176064 | 01952 | 135 | Solar | 05_12_51L2 | 04/02/2015 | 04/02/2015 | 6 | 0 | 6 | 04/10/2015 | 04/10/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 366611 | 01523 | 10 | Solar | 05_14_275L4 | 07/28/2021 | 08/17/2021 | 14 | 13 | 1 | 08/18/2021 | 08/18/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 4/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2022 | Connected |  | N
National Grid | OXFORD | 475112 | 01540 | 15.2 | Solar | 05_14_56L3 | 11/07/2022 | 11/08/2022 | 1 | 0 | 1 | 11/09/2022 | 11/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | SPENCER | 193712 | 01562 | 1491 | Solar | 05_14_70L2 | 09/24/2018 | 11/13/2018 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 | 04/02/2019 | 145 | 77 | 68 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 731443 | 01609 | 5.76 | Solar | 05_14_7L4 | 11/04/2025 | 11/05/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/29/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 645128 | 02720 | 7.6 | Solar | 05_01_227W1 | 10/11/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 35 | 13 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | N
National Grid | GRAFTON | 177113 | 01560 | 936 | Solar | 05_01_406L3 | 08/04/2016 | 08/04/2016 | 128 | 128 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/14/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 742840 | 01915 | 11.52 | Solar | 05_01_9J337 | 01/02/2026 | 02/17/2026 | 29 | 25 | 4 | 02/18/2026 | 02/18/2026 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | AMESBURY | 174534 | 01913 | 950 | Solar | 05_05_28W51 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 01/27/2012 | 43 | 0 | 43 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2013 | 10/18/2011 | 10/31/2012 | Y | STD | 142 | 11/04/2013 | 03/18/2014 | 89 | 0 | 89 | 12/10/2013 | 12/10/2013 | 12/13/2013 | Connected |  | N
National Grid | BOXFORD | 291554 | 01921 | 11.4 | Solar | 05_05_320W3 | 05/12/2020 | 05/14/2020 | 1 | 0 | 1 | 05/15/2020 | 05/15/2020 | 53 | 32 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  | 5/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2022 | Connected |  | Y
National Grid | BILLERICA | 176091 | 01821 | 266 | Solar | 05_12_51L2 | 04/01/2015 | 04/01/2015 | 6 | 0 | 6 | 04/10/2015 | 04/10/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 478526 | 01952 | 22.8 | Solar | 05_14_275L4 | 11/21/2022 | 11/27/2022 | 4 | 0 | 4 | 11/28/2022 | 11/28/2022 | 69 | 25 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LUNENBURG | 525009 | 01462 | 13.824 | Solar | 05_14_56L3 | 05/10/2023 | 05/18/2023 | 6 | 4 | 2 | 05/19/2023 | 05/19/2023 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2024 | Connected |  | N
National Grid | OXFORD | 256057 | 01540 | 10 | Solar | 05_14_70L2 | 10/10/2019 | 10/14/2019 | 1 | 0 | 1 | 10/15/2019 | 10/15/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 | 10/10/2019 | 7/7/2020 | Y | EXP | 365 | 01/29/2020 | 02/25/2020 | 27 | 0 | 27 |  |  | 6/8/2020 | Connected |  | N
National Grid | SPENCER | 731423 | 01562 | 22.8 | Solar | 05_14_7L4 | 11/05/2025 | 11/12/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 94 | 63 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 660768 | 01604 | 5.76 | Solar | 05_01_227W1 | 12/16/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/16/2024 | 3/11/2026 | Y | EXP | 365 | 05/21/2025 | 05/20/2025 | 0 | 0 | 0 |  |  | 6/30/2025 | Connected |  | N
National Grid | FALL RIVER | 177412 | 02720 | 1740 | Solar | 05_01_406L3 | 09/11/2016 | 10/13/2016 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2016 | 11/01/2016 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2017 | 09/11/2016 | 8/24/2020 | Y | STD | 993 | 08/29/2019 | 11/22/2019 | 85 | 0 | 85 |  |  | 8/12/2020 | Connected |  | N
National Grid | NORTHBRIDGE | 448029 | 01534 | 10 | Solar | 05_01_552L1 | 08/10/2022 | 08/15/2022 | 4 | 3 | 1 | 08/16/2022 | 08/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 |  | 10/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2022 | Connected |  | N
National Grid | BEVERLY | 175283 | 01915 | 42.57 | Solar | 05_01_9J337 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/4/2015 | Connected |  | N
National Grid | AMESBURY | 174614 | 01913 | 2000 | Wind | 05_05_28W51 | 11/30/2010 | 11/30/2010 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2011 |  | 4/20/2012 | N | STD | 203 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 4/20/2012 | Connected |  | N
National Grid | BOXFORD | 328163 | 01921 | 7.6 | Solar | 05_05_320W3 | 11/24/2020 | 12/13/2021 | 4 | 0 | 4 | 12/03/2020 | 12/03/2020 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  | 5/27/2022 | N | EXP | 435 |  |  | 0 | 0 | 0 |  |  | 4/22/2022 | Connected |  | N
National Grid | BILLERICA | 177119 | 01821 | 390 | Solar | 05_12_51L2 | 10/19/2016 | 10/19/2016 | 4 | 4 | 0 | 10/26/2016 | 10/26/2016 | 319 | 36 | 283 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 502722 | 01952 | 2000 | Solar | 05_14_275L4 | 03/29/2023 | 08/25/2023 | 103 | 93 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 10/18/2023 | 36 | 17 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 | 03/29/2023 | 10/20/2025 | Y | STD | 252 | 01/14/2025 | 08/04/2025 | 203 | 0 | 203 |  |  | 9/30/2025 | Connected |  | N
National Grid | SHIRLEY | 557784 | 01464 | 13.8 | Solar | 05_14_56L3 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 42 | 20 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 |  | 12/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2024 | Connected |  | N
National Grid | OXFORD | 406289 | 01540 | 0 | Battery Add-On | 05_14_70L2 | 02/04/2022 | 02/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 03/02/2022 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 751336 | 01562 | 17.16 | Solar | 05_14_7L4 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2026 |  | 3/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 661472 | 01604 | 10 | Solar | 05_01_227W1 | 12/18/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/18/2024 | 2/25/2026 | Y | EXP | 365 | 06/12/2025 | 07/10/2025 | 29 | 0 | 29 |  |  | 7/17/2025 | Connected |  | N
National Grid | FALL RIVER | 177669 | 02720 | 2000 | Solar | 05_01_406L3 | 05/25/2017 | 05/31/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2017 | 06/26/2017 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 | 05/25/2017 | 6/29/2020 | Y | STD | 621 | 12/12/2019 | 06/12/2020 | 183 | 0 | 183 |  |  | 6/29/2020 | Connected |  | N
National Grid | NORTHBRIDGE | 460324 | 01534 | 15.66 | Solar | 05_01_552L1 | 10/04/2022 | 10/31/2022 | 19 | 17 | 2 | 11/01/2022 | 11/01/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  | 12/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2023 | Connected |  | N
National Grid | BEVERLY | 236472 | 01915 | 7.6 | Solar | 05_01_9J337 | 07/22/2019 | 07/23/2019 | 0 | 0 | 0 | 07/24/2019 | 07/24/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 12/30/2019 | N | EXP | 46 |  |  | 0 | 0 | 0 |  |  | 12/10/2019 | Connected |  | N
National Grid | AMESBURY | 175108 | 01913 | 1500 | Solar | 05_05_28W51 | 04/22/2013 | 04/22/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2013 | 06/05/2013 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2013 | 04/22/2013 | 9/2/2013 | Y | STD | 73 | 10/03/2014 | 12/08/2014 | 43 | 0 | 43 | 4/22/2013 | 4/22/2013 | 12/18/2014 | Connected |  | N
National Grid | BOXFORD | 382030 | 01921 | 19 | Solar | 05_05_320W3 | 09/14/2021 | 09/21/2021 | 6 | 5 | 1 | 09/22/2021 | 09/22/2021 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 9/20/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 337612 | 01821 | 8.4 | Solar | 05_12_51L2 | 02/01/2021 | 02/04/2021 | 2 | 0 | 2 | 02/05/2021 | 02/05/2021 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 | 02/01/2021 | 9/14/2022 | Y | EXP | 365 | 09/16/2021 | 10/12/2021 | 16 | 0 | 16 |  |  | 12/17/2021 | Connected |  | N
National Grid | SALISBURY | 586162 | 01952 | 1375 | Solar | 05_14_275L4 | 02/05/2024 | 02/22/2024 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2024 | 02/29/2024 | 5 | 0 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 546601 | 01453 | 15.08 | Solar | 05_14_56L3 | 08/07/2023 |  | 50 | 26 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 652181 | 01540 | 7.6 | Solar | 05_14_70L2 | 02/14/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | SPENCER | 174822 | 01562 | 30 | Solar | 05_14_7L4 | 08/02/2013 | 08/02/2013 | 7 | 1 | 6 | 08/14/2013 | 08/14/2013 | 156 | 3 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2013 |  | 11/29/2013 | N | EXP | 84 |  |  | 0 | 0 | 0 | 12/6/2013 | 12/6/2013 |  | Withdrawn |  | N
National Grid | WORCESTER | 667845 | 01604 | 10 | Solar | 05_01_227W1 | 02/03/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 70 | 49 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 178103 | 02720 | 249.8 | Solar | 05_01_406L3 | 09/08/2017 | 02/12/2018 | 10 | 0 | 10 | 02/12/2018 | 02/12/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 |  | 9/16/2019 | N | EXP | 452 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 546629 | 01560 | 4.64 | Solar | 05_01_552L1 | 08/09/2023 | 08/22/2023 | 9 | 9 | 0 | 08/23/2023 | 08/23/2023 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 | 08/09/2023 | 10/10/2024 | Y | EXP | 365 | 10/28/2023 | 01/29/2024 | 94 | 3 | 91 |  |  | 2/1/2024 | Connected |  | N
National Grid | BEVERLY | 279312 | 01915 | 7.6 | Solar | 05_01_9J337 | 04/20/2020 | 04/27/2020 | 4 | 4 | 0 | 04/28/2020 | 04/28/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 |  | 4/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2020 | Connected |  | N
National Grid | AMESBURY | 175675 | 01913 | 500 | Solar | 05_05_28W51 | 10/21/2014 | 10/21/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 11/26/2014 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 | 1/26/2018 | 1/26/2018 |  | Withdrawn |  | N
National Grid | BOXFORD | 411110 | 01921 | 19 | Solar | 05_05_320W3 | 02/09/2022 | 02/10/2022 | 1 | 0 | 1 | 02/11/2022 | 02/11/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 419862 | 01862 | 0 | Other | 05_12_51L2 | 06/14/2022 | 06/28/2022 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2022 | 07/27/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 603133 | 01952 | 17.6 | Solar | 05_14_275L4 | 04/10/2024 | 04/29/2024 | 13 | 9 | 4 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 8/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2024 | Connected |  | N
National Grid | LANCASTER | 587700 | 01523 | 21.735 | Solar | 05_14_56L3 | 02/06/2024 | 02/29/2024 | 16 | 14 | 2 | 03/01/2024 | 03/01/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | CHARLTON | 679382 | 01507 | 11.5 | Solar | 05_14_70L2 | 03/21/2025 | 03/25/2025 | 2 | 0 | 2 | 03/26/2025 | 03/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 6/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2025 | Connected |  | N
National Grid | SPENCER | 175002 | 01562 | 150 | Solar | 05_14_7L4 | 09/12/2013 | 09/12/2013 | 6 | 0 | 6 | 09/23/2013 | 09/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2013 |  | 11/29/2013 | N | EXP | 36 |  |  | 0 | 0 | 0 | 2/28/2014 | 2/28/2014 | 3/7/2014 | Connected |  | N
National Grid | WORCESTER | 683029 | 01604 | 3.8 | Solar | 05_01_227W1 | 04/04/2025 | 05/13/2025 | 4 | 0 | 4 | 05/14/2025 | 05/14/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 | 04/04/2025 | 6/24/2026 | Y | EXP | 365 | 09/03/2025 | 10/28/2025 | 56 | 0 | 56 |  |  | 11/4/2025 | Connected |  | N
National Grid | FALL RIVER | 178302 | 02720 | 0 | Solar | 05_01_406L3 | 01/09/2018 | 03/09/2018 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/05/2018 | 13 | 0 | 13 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 562432 | 01560 | 9.074 | Solar | 05_01_552L1 | 10/16/2023 | 10/19/2023 | 4 | 2 | 2 | 10/20/2023 | 10/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 | 10/16/2023 | 11/19/2024 | Y | EXP | 365 | 12/14/2023 | 02/07/2024 | 56 | 3 | 53 |  |  | 2/8/2024 | Connected |  | N
National Grid | BEVERLY | 601301 | 01915 | 3.8 | Solar | 05_01_9J337 | 04/10/2024 | 04/30/2024 | 14 | 13 | 1 | 05/01/2024 | 05/01/2024 | 30 | 25 | 5 | 07/24/2024 | 08/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 08/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 175725 | 01913 | 500 | Solar | 05_05_28W51 | 05/27/2014 | 05/27/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/04/2014 | 07/10/2014 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 05/27/2014 | 11/28/2014 | Y | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 425276 | 01921 | 0 | Solar | 05_05_320W3 | 04/21/2022 | 04/29/2022 | 7 | 6 | 1 | 05/02/2022 | 05/02/2022 | 36 | 22 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 04/21/2022 | 1/11/2024 | Y | EXP | 500 | 12/29/2023 | 01/05/2024 | 8 | 0 | 8 |  |  | 1/5/2024 | Connected |  | N
National Grid | BILLERICA | 546247 | 01821 | 9.86 | Solar | 05_12_51L2 | 08/06/2023 | 08/07/2023 | 1 | 0 | 1 | 08/08/2023 | 08/08/2023 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 |  | 10/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2023 | Connected |  | N
National Grid | SALISBURY | 626752 | 01952 | 3.8 | Solar | 05_14_275L4 | 07/22/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 | 07/22/2024 | 9/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | LEOMINSTER | 593058 | 01453 | 15.2 | Solar | 05_14_56L3 | 02/27/2024 | 04/09/2024 | 1 | 0 | 1 | 04/10/2024 | 04/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 02/27/2024 | 5/8/2025 | Y | EXP | 365 | 05/23/2024 | 12/17/2024 | 209 | 0 | 209 |  |  | 8/3/2024 | Connected |  | N
National Grid | OXFORD | 745032 | 01540 | 10 | Solar | 05_14_70L3 | 01/13/2026 | 01/20/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 175524 | 01562 | 500 | Solar | 05_14_7L4 | 07/28/2014 | 07/28/2014 | 7 | 0 | 7 | 08/07/2014 | 08/07/2014 | 0 | 0 | 0 | 09/24/2014 | 11/06/2014 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 11/06/2014 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 2/6/2015 | 07/28/2014 | 12/31/2016 | Y | EXP | 694 | 05/30/2017 | 06/24/2017 | 19 | 0 | 19 | 8/1/2017 | 8/1/2017 | 8/4/2017 | Connected |  | N
National Grid | WORCESTER | 688672 | 01604 | 12.16 | Solar | 05_01_227W1 | 05/07/2025 | 05/12/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | FALL RIVER | 201189 | 02720 | 3.8 | Solar | 05_01_406L3 | 08/15/2019 | 08/15/2019 | 0 | 0 | 0 | 08/16/2019 | 08/16/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2019 |  | 10/14/2019 | N | EXP | 52 |  |  | 0 | 0 | 0 |  |  | 9/12/2019 | Connected |  | N
National Grid | GRAFTON | 568209 | 01560 | 13.05 | Solar | 05_01_552L1 | 11/06/2023 | 11/13/2023 | 4 | 2 | 2 | 11/14/2023 | 11/14/2023 | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2024 | Connected |  | N
National Grid | BEVERLY | 652266 | 01915 | 4.225 | Solar | 05_01_9J337 | 11/05/2024 | 11/22/2024 | 4 | 0 | 4 | 11/25/2024 | 11/25/2024 | 83 | 63 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 176454 | 01913 | 3 | Solar | 05_05_28W51 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2015 |  | 12/14/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/9/2016 | 9/9/2016 | 9/13/2016 | Connected |  | N
National Grid | BOXFORD | 427162 | 01921 | 9.8 | Solar | 05_05_320W3 | 06/29/2022 | 06/30/2022 | 1 | 0 | 1 | 07/01/2022 | 07/01/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2022 | Connected |  | N
National Grid | BILLERICA | 652576 | 01821 | 5.76 | Solar | 05_12_51L2 | 11/06/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | SALISBURY | 631814 | 01952 | 7.6 | Solar | 05_14_275L4 | 08/12/2024 | 08/26/2024 | 3 | 0 | 3 | 08/27/2024 | 08/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/12/2024 | 11/24/2025 | Y | EXP | 365 | 01/22/2025 | 01/21/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 597914 | 01453 | 7.68 | Solar | 05_14_56L3 | 05/20/2024 | 08/13/2024 | 19 | 17 | 2 | 08/14/2024 | 08/14/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 |  | 9/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | OXFORD | 176707 | 01540 | 3.8 | Solar | 05_14_70L3 | 10/27/2015 | 10/27/2015 | 2 | 2 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2015 |  | 11/2/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 4/27/2016 | 4/27/2016 | 7/26/2016 | Connected |  | N
National Grid | SPENCER | 176047 | 01562 | 42 | Solar | 05_14_7L4 | 01/26/2015 | 01/26/2015 | 4 | 0 | 4 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2015 |  | 6/30/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 3/31/2015 | Connected |  | N
National Grid | WORCESTER | 394134 | 01604 | 700 | Solar | 05_01_227W3 | 01/17/2022 | 05/24/2022 | 87 | 77 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/25/2022 | 06/27/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | FALL RIVER | 209264 | 02720 | 17.28 | Solar | 05_01_406L3 | 02/11/2019 | 04/22/2019 | 49 | 49 | 0 | 04/23/2019 | 04/23/2019 | 242 | 241 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2020 |  | 1/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/8/2020 | Connected |  | N
National Grid | GRAFTON | 571014 | 01519 | 10 | Solar | 05_01_552L1 | 12/21/2023 | 11/27/2023 | 5 | 0 | 5 | 01/02/2024 | 01/02/2024 | 47 | 27 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 12/21/2023 | 5/3/2025 | Y | EXP | 365 | 06/11/2024 | 08/15/2024 | 66 | 0 | 66 |  |  | 9/24/2024 | Connected |  | N
National Grid | BEVERLY | 653577 | 01915 | 15.2 | Solar | 05_01_9J337 | 11/14/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | AMESBURY | 177098 | 01913 | 3 | Solar | 05_05_28W51 | 05/24/2016 | 05/24/2016 | 2 | 2 | 0 | 05/27/2016 | 05/27/2016 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/30/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 487761 | 01921 | 15.2 | Solar | 05_05_320W3 | 12/22/2022 | 12/27/2022 | 2 | 0 | 2 | 12/28/2022 | 12/28/2022 | 73 | 50 | 23 | 05/03/2023 | 12/14/2023 | 154 | 25 | 129 |  |  | 0 | 0 | 0 | 12/14/2023 | 154 | 25 | 129 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 657811 | 01824 | 5.76 | Solar | 05_12_51L2 | 12/02/2024 | 12/20/2024 | 10 | 7 | 3 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | SALISBURY | 659939 | 01952 | 17.1 | Solar | 05_14_275L4 | 12/11/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | SHIRLEY | 605204 | 01464 | 10 | Solar | 05_14_56L3 | 04/19/2024 | 04/22/2024 | 1 | 0 | 1 | 04/23/2024 | 04/23/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 5/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2024 | Connected |  | N
National Grid | OXFORD | 178184 | 01540 | 3.8 | Solar | 05_14_70L3 | 04/13/2018 | 04/13/2018 | 0 | 0 | 0 | 05/01/2018 | 05/01/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2019 |  | 4/21/2019 | N | EXP | 68 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 177992 | 01562 | 7.6 | Solar | 05_14_7L4 | 10/24/2017 | 10/24/2017 | 5 | 5 | 0 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 |  | 11/1/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  | 2/5/2019 | Connected |  | N
National Grid | WORCESTER | 434882 | 01604 | 2400 | Solar | 05_01_227W3 | 01/12/2023 | 04/25/2023 | 70 | 61 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2023 | 05/23/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FALL RIVER | 243055 | 02720 | 10 | Solar | 05_01_406L3 | 10/07/2019 | 10/14/2019 | 4 | 4 | 0 | 10/15/2019 | 10/15/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 | 10/07/2019 | 10/7/2020 | Y | EXP | 365 | 07/14/2020 | 08/21/2020 | 38 | 0 | 38 |  |  | 9/4/2020 | Connected |  | N
National Grid | NORTHBRIDGE | 588485 | 01534 | 7.6 | Solar | 05_01_552L1 | 02/12/2024 | 02/15/2024 | 4 | 2 | 2 | 02/16/2024 | 02/16/2024 | 18 | 13 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2024 | Connected |  | N
National Grid | BEVERLY | 695515 | 01915 | 6.98 | Solar | 05_01_9J337 | 06/02/2025 | 06/20/2025 | 2 | 0 | 2 | 06/26/2025 | 06/26/2025 | 79 | 71 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | AMESBURY | 217169 | 01913 | 240 | Solar | 05_05_28W51 | 05/06/2019 | 05/21/2019 | 8 | 0 | 8 | 05/22/2019 | 05/22/2019 | 15 | 2 | 13 | 07/03/2019 | 08/29/2019 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 08/29/2019 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 9/4/2019 |  | 6/12/2020 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  | 4/16/2020 | Connected |  | N
National Grid | BOXFORD | 515069 | 01921 | 15.2 | Solar | 05_05_320W3 | 03/28/2023 | 03/29/2023 | 1 | 0 | 1 |  |  | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 665914 | 01852 | 18.85 | Solar | 05_12_51L2 | 01/15/2025 | 01/29/2025 | 7 | 2 | 5 | 01/30/2025 | 01/30/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | SALISBURY | 662699 | 01952 | 7.83 | Solar | 05_14_275L4 | 12/26/2024 | 01/21/2025 | 5 | 1 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 12/26/2024 | 3/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | SHIRLEY | 620829 | 01464 | 15.2 | Solar | 05_14_56L3 | 06/28/2024 | 07/11/2024 | 9 | 7 | 2 | 07/12/2024 | 07/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 8/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2024 | Connected |  | N
National Grid | CHARLTON | 190106 | 01507 | 6 | Solar | 05_14_70L3 | 07/11/2018 | 07/18/2018 | 0 | 0 | 0 | 07/19/2018 | 07/19/2018 | 49 | 1 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 178166 | 01562 | 11.4 | Solar | 05_14_7L4 | 02/14/2018 | 02/14/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2018 |  | 2/20/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 10/3/2019 | Connected |  | N
National Grid | WORCESTER | 644479 | 01604 | 160 | Solar | 05_01_227W3 | 10/02/2024 | 01/28/2025 | 77 | 67 | 10 | 01/29/2025 | 01/29/2025 | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | FALL RIVER | 244524 | 02720 | 249.8 | Solar | 05_01_406L3 | 07/22/2019 | 07/26/2019 | 4 | 3 | 1 |  |  | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2022 | 07/22/2019 | 11/10/2023 | Y | STD | 278 | 11/01/2022 | 05/03/2023 | 184 | 0 | 184 |  |  | 10/17/2023 | Connected |  | N
National Grid | GRAFTON | 603808 | 01560 | 10 | Solar | 05_01_552L1 | 04/16/2024 | 05/02/2024 | 5 | 0 | 5 | 05/03/2024 | 05/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 | 04/16/2024 | 7/22/2025 | Y | EXP | 365 | 08/08/2024 | 09/12/2024 | 36 | 0 | 36 |  |  | 11/22/2024 | Connected |  | N
National Grid | BEVERLY | 714065 | 01915 | 10 | Solar | 05_01_9J337 | 08/22/2025 | 09/15/2025 | 8 | 2 | 6 | 10/22/2025 | 10/22/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2026 | Connected |  | N
National Grid | AMESBURY | 282338 | 01913 | 0 | Other | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 42 | 33 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2020 | 08/11/2020 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2021 | 05/18/2020 | 11/29/2024 | Y | STD | 413 | 04/20/2022 | 03/07/2024 | 688 | 537 | 151 |  |  | 9/20/2024 | Connected |  | N
National Grid | BOXFORD | 520350 | 01921 | 9.86 | Solar | 05_05_320W3 | 04/27/2023 | 05/08/2023 | 7 | 4 | 3 | 05/09/2023 | 05/09/2023 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2023 |  | 8/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2023 | Connected |  | N
National Grid | CHELMSFORD | 669158 | 01824 | 8.125 | Solar | 05_12_51L2 | 01/31/2025 | 02/24/2025 | 4 | 0 | 4 | 02/25/2025 | 02/25/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 01/31/2025 | 4/13/2026 | Y | EXP | 365 | 05/16/2025 | 09/03/2025 | 111 | 0 | 111 |  |  | 9/15/2025 | Connected |  | N
National Grid | SALISBURY | 667969 | 01952 | 7.6 | Solar | 05_14_275L4 | 01/27/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 623174 | 01464 | 0 | Solar | 05_14_56L3 | 07/08/2024 | 07/10/2024 | 2 | 0 | 2 | 07/11/2024 | 07/11/2024 | 38 | 23 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 10/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2024 | Connected |  | N
National Grid | OXFORD | 253690 | 01540 | 10 | Solar | 05_14_70L3 | 09/17/2019 | 09/30/2019 | 8 | 2 | 6 | 10/01/2019 | 10/01/2019 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 |  | 9/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/18/2020 | Connected |  | N
National Grid | SPENCER | 178204 | 01562 | 4000 | Solar | 05_14_7L4 | 02/07/2018 | 02/07/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2018 | 04/18/2018 | 28 | 21 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 | 02/07/2018 | 2/25/2021 | Y | STD | 833 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 742930 | 01604 |  | Battery Add-On | 05_01_227W3 | 01/02/2026 | 01/06/2026 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2026 |  | 2/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 343654 | 02720 | 7.6 | Solar | 05_01_406L3 | 03/16/2021 | 03/17/2021 | 0 | 0 | 0 | 03/18/2021 | 03/18/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 | 03/16/2021 | 12/8/2022 | Y | EXP | 365 | 07/24/2021 | 12/08/2021 | 138 | 7 | 131 |  |  | 1/4/2022 | Connected |  | N
National Grid | GRAFTON | 613530 | 01560 | 36 | Solar | 05_01_552L1 | 08/18/2024 | 10/28/2024 | 49 | 41 | 8 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 2/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | BEVERLY | 731961 | 01915 | 5.76 | Solar | 05_01_9J352 | 11/06/2025 | 11/19/2025 | 4 | 0 | 4 | 12/16/2025 | 12/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 |  | 1/16/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AMESBURY | 335842 | 01913 | 5.52 | Solar | 05_05_28W51 | 01/18/2021 | 12/16/2021 | 4 | 0 | 4 | 01/26/2021 | 01/26/2021 | 64 | 40 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2021 | 01/18/2021 | 9/16/2022 | Y | EXP | 365 | 03/31/2022 | 04/12/2022 | 13 | 0 | 13 |  |  | 6/4/2022 | Connected |  | N
National Grid | BOXFORD | 559289 | 01921 | 7.25 | Solar | 05_05_320W3 | 11/09/2023 | 11/16/2023 | 4 | 1 | 3 | 11/17/2023 | 11/17/2023 | 69 | 48 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2024 | Connected |  | N
National Grid | LOWELL | 700800 | 01852 | 10 | Solar | 05_12_51L2 | 07/01/2025 | 08/19/2025 | 34 | 31 | 3 | 08/20/2025 | 08/20/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | SALISBURY | 672950 | 01952 | 15.2 | Solar | 05_14_275L4 | 02/24/2025 | 03/03/2025 | 5 | 2 | 3 | 03/04/2025 | 03/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | SHIRLEY | 646412 | 01464 | 10 | Solar | 05_14_56L3 | 10/16/2024 | 11/04/2024 | 2 | 0 | 2 | 11/05/2024 | 11/05/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/16/2024 | 12/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | OXFORD | 313391 | 01540 | 10 | Solar | 05_14_70L3 | 09/17/2020 | 10/27/2020 | 26 | 25 | 1 | 10/28/2020 | 10/28/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  | 10/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2021 | Connected |  | Y
National Grid | SPENCER | 184636 | 01562 | 7.6 | Solar | 05_14_7L4 | 05/10/2018 | 05/10/2018 | 11 | 0 | 11 | 05/17/2018 | 05/17/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2018 | 05/10/2018 | 6/3/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2019 | Connected |  | N
National Grid | WORCESTER | 174232 | 01604 | 2000 | Solar | 05_01_227W3 | 01/31/2012 | 01/31/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2013 |  | 11/1/2012 | N | STD | 82 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 353715 | 02720 | 10 | Solar | 05_01_406L3 | 05/18/2022 | 01/06/2022 | 6 | 4 | 2 | 05/26/2022 | 05/26/2022 | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 | 05/18/2022 | 6/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2023 | Connected |  | N
National Grid | NORTHBRIDGE | 619978 | 01588 | 5.76 | Solar | 05_01_552L1 | 06/24/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 06/24/2024 | 9/12/2025 | Y | EXP | 365 | 11/15/2024 | 01/16/2025 | 63 | 0 | 63 |  |  | 1/24/2025 | Connected |  | N
National Grid | BEVERLY | 611572 | 01915 | 6 | Solar | 05_01_9J352 | 05/17/2024 | 05/31/2024 | 1 | 0 | 1 | 06/03/2024 | 06/03/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2024 | Connected |  | N
National Grid | AMESBURY | 397056 | 01913 | 625 | Solar | 05_05_28W51 | 03/14/2022 |  | 166 | 157 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 600585 | 01921 | 10 | Solar | 05_05_320W3 | 04/04/2024 | 04/10/2024 | 4 | 0 | 4 | 04/11/2024 | 04/11/2024 | 10 | 6 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 697184 | 01862 | 17.6 | Solar | 05_12_51L3 | 06/11/2025 | 06/16/2025 | 3 | 0 | 3 | 06/17/2025 | 06/17/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SALISBURY | 690639 | 01952 | 5.76 | Solar | 05_14_275L4 | 05/09/2025 | 06/02/2025 | 4 | 0 | 4 | 06/18/2025 | 06/18/2025 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 655111 | 01464 | 5.76 | Solar | 05_14_56L3 | 11/20/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/20/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | OXFORD | 449194 | 01540 | 15.2 | Solar | 05_14_70L3 | 08/03/2022 | 08/11/2022 | 6 | 4 | 2 | 08/12/2022 | 08/12/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2022 |  | 11/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2023 | Connected |  | N
National Grid | SPENCER | 193070 | 01562 | 246.5 | Solar | 05_14_7L4 | 08/08/2018 | 08/22/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 10/26/2018 | 11/01/2018 | 5 | 1 | 4 | 08/23/2018 | 09/26/2018 | 24 | 6 | 18 | 11/01/2018 | 5 | 1 | 4 |  |  | 0 | 0 | 0 | 4/15/2020 | 08/08/2018 | 11/23/2022 | Y | STD | 98 |  |  | 0 | 0 | 0 |  |  | 10/25/2022 | Connected |  | N
National Grid | WORCESTER | 174230 | 01604 | 2500 | Solar | 05_01_227W3 | 01/31/2012 | 01/31/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2013 | 01/31/2012 | 6/30/2014 | Y | STD | 524 | 01/13/2014 | 07/18/2014 | 127 | 0 | 127 | 1/9/2014 | 1/9/2014 | 1/9/2014 | Connected |  | N
National Grid | FALL RIVER | 418004 | 02720 | 15.2 | Solar | 05_01_406L3 | 03/16/2022 | 03/17/2022 | 1 | 0 | 1 | 03/18/2022 | 03/18/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2022 |  | 3/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2022 | Connected |  | N
National Grid | GRAFTON | 621844 | 01560 | 7.6 | Solar | 05_01_552L1 | 07/01/2024 |  | 86 | 40 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 636156 | 01915 | 7.6 | Solar | 05_01_9J352 | 09/03/2024 | 09/16/2024 | 3 | 0 | 3 | 09/17/2024 | 09/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | N
National Grid | SALISBURY | 401103 | 01952 | 0 | Other | 05_05_28W51 | 01/04/2022 | 01/27/2022 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/28/2022 | 02/02/2022 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 623382 | 01921 | 11.5 | Solar | 05_05_320W3 | 07/09/2024 | 07/12/2024 | 3 | 0 | 3 | 07/15/2024 | 07/15/2024 | 45 | 31 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | LOWELL | 174456 | 01852 | 200 | Solar | 05_12_51L3 | 11/04/2011 | 11/04/2011 | 33 | 0 | 33 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2012 |  | 10/31/2012 | N | EXP | 253 |  |  | 0 | 0 | 0 | 1/28/2013 | 1/28/2013 | 2/12/2013 | Connected |  | N
National Grid | SALISBURY | 727151 | 01952 | 28 | Solar | 05_14_2J2 | 10/17/2025 | 10/21/2025 | 2 | 0 | 2 | 10/22/2025 | 10/22/2025 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 660528 | 01523 | 8.12 | Solar | 05_14_56L3 | 12/16/2024 | 12/26/2024 | 7 | 3 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 449174 | 01507 | 15.2 | Solar | 05_14_70L3 | 08/03/2022 | 08/19/2022 | 13 | 12 | 1 | 08/22/2022 | 08/22/2022 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2022 | 08/03/2022 | 10/10/2023 | Y | EXP | 365 | 10/19/2022 | 10/28/2022 | 10 | 0 | 10 |  |  | 8/30/2023 | Connected |  | N
National Grid | SPENCER | 252060 | 01562 | 7.6 | Solar | 05_14_7L4 | 09/11/2019 | 09/18/2019 | 4 | 0 | 4 | 09/19/2019 | 09/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2019 | 09/11/2019 | 9/11/2020 | Y | EXP | 365 | 02/01/2020 | 02/05/2020 | 4 | 0 | 4 |  |  | 2/14/2020 | Connected |  | N
National Grid | WORCESTER | 174493 | 01604 | 232 | Solar | 05_01_227W3 | 06/13/2011 | 06/13/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2011 |  | 3/7/2012 | N | STD | 156 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 3/7/2012 | Connected |  | N
National Grid | FALL RIVER | 428180 | 02720 | 10 | Solar | 05_01_406L3 | 05/04/2022 | 06/10/2022 | 15 | 13 | 2 | 06/13/2022 | 06/13/2022 | 27 | 5 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 | 05/04/2022 | 4/3/2024 | Y | EXP | 365 | 03/09/2023 | 04/03/2023 | 26 | 0 | 26 |  |  | 4/12/2023 | Connected |  | N
National Grid | WHITINSVILLE | 635360 | 01588 | 0 | Solar | 05_01_552L1 | 08/26/2024 | 08/28/2024 | 2 | 0 | 2 | 08/29/2024 | 08/29/2024 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  | 11/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2024 | Connected |  | N
National Grid | HAMILTON | 645610 | 01982 | 3.8 | Solar | 05_01_9J352 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | AMESBURY | 424613 | 01913 | 10 | Solar | 05_05_28W51 | 04/21/2022 | 04/27/2022 | 4 | 0 | 4 | 04/28/2022 | 04/28/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2022 | 04/21/2022 | 9/20/2023 | Y | EXP | 365 | 08/19/2022 | 09/19/2022 | 32 | 0 | 32 |  |  | 9/27/2022 | Connected |  | Y
National Grid | BOXFORD | 626485 | 01921 | 10 | Solar | 05_05_320W3 | 07/22/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 | 07/22/2024 | 8/27/2025 | Y | EXP | 365 | 10/04/2024 | 10/22/2024 | 19 | 0 | 19 |  |  | 10/30/2024 | Connected |  | N
National Grid | CHELMSFORD | 174970 | 01824 | 85 | Solar | 05_12_51L3 | 09/10/2013 | 09/10/2013 | 7 | 0 | 7 | 09/20/2013 | 09/20/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2013 |  | 12/31/2013 | N | EXP | 19 |  |  | 0 | 0 | 0 | 3/7/2014 | 3/7/2014 | 4/4/2014 | Connected |  | N
National Grid | SALISBURY | 225517 | 01952 | 23.4 | Solar | 05_14_2J2 | 05/23/2019 | 06/21/2019 | 19 | 12 | 7 | 06/24/2019 | 06/24/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 |  | 7/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2020 | Connected |  | N
National Grid | LANCASTER | 661934 | 01523 | 8.74 | Solar | 05_14_56L3 | 12/20/2024 | 01/03/2025 | 4 | 0 | 4 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/20/2024 | 3/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | OXFORD | 396676 | 01540 | 0 | Battery Add-On | 05_14_70L3 | 07/06/2022 | 08/10/2022 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/16/2022 | 27 | 7 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 277711 | 01562 | 5 | Solar | 05_14_7L4 | 02/06/2020 | 02/18/2020 | 6 | 6 | 0 | 02/19/2020 | 02/19/2020 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2020 | 02/06/2020 | 2/18/2021 | Y | EXP | 365 | 06/09/2020 | 06/11/2020 | 2 | 0 | 2 |  |  | 6/13/2020 | Connected |  | N
National Grid | WORCESTER | 175662 | 01604 | 996 | Solar | 05_01_227W3 | 08/07/2014 | 08/07/2014 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 09/19/2014 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2015 | 08/07/2014 | 6/15/2016 | Y | STD | 422 | 11/03/2015 | 01/30/2016 | 59 | 0 | 59 | 12/31/2015 | 12/31/2015 | 12/31/2015 | Connected |  | N
National Grid | FALL RIVER | 440487 | 02720 | 3.8 | Solar | 05_01_406L3 | 07/01/2022 | 07/05/2022 | 1 | 0 | 1 | 07/06/2022 | 07/06/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 9/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2023 | Connected |  | N
National Grid | GRAFTON | 641036 | 01560 | 5.76 | Solar | 05_01_552L1 | 09/17/2024 | 10/07/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/17/2024 | 11/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | HAMILTON | 660942 | 01982 | 5.76 | Solar | 05_01_9J352 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | Y
National Grid | LAWRENCE | 484084 | 01840 | 126.3 | Solar | 05_05_28W51 | 12/14/2022 | 02/10/2023 | 39 | 29 | 10 |  |  | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 629924 | 01845 | 11.4 | Solar | 05_05_320W3 | 08/14/2024 | 08/19/2024 | 3 | 0 | 3 | 08/20/2024 | 08/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 11/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | CHELMSFORD | 175113 | 01824 | 19.99 | Solar | 05_12_51L3 | 10/15/2013 | 10/15/2013 | 7 | 0 | 7 | 10/25/2013 | 10/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2013 |  | 12/31/2013 | N | EXP | 28 |  |  | 0 | 0 | 0 | 2/12/2014 | 2/12/2014 | 2/24/2014 | Connected |  | N
National Grid | SALISBURY | 196571 | 01952 | 43.2 | Solar | 05_14_2J3 | 10/04/2018 | 11/01/2018 | 18 | 1 | 17 | 11/02/2018 | 11/02/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2020 | Connected |  | N
National Grid | AYER | 671510 | 01432 | 10 | Solar | 05_14_56L3 | 02/11/2025 | 02/20/2025 | 6 | 3 | 3 | 02/21/2025 | 02/21/2025 | 161 | 140 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 431972 | 01540 | 11.4 | Solar | 05_14_70L3 | 05/27/2022 | 06/01/2022 | 2 | 0 | 2 | 06/02/2022 | 06/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2022 |  | 11/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2023 | Connected |  | N
National Grid | SPENCER | 301879 | 01562 | 0 | Solar | 05_14_7L4 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 |  | 7/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2020 | Connected |  | N
National Grid | WORCESTER | 175671 | 01604 | 1008 | Solar | 05_01_227W3 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2014 | 11/19/2014 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/15/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 473594 | 02720 | 8.41 | Solar | 05_01_406L3 | 12/08/2022 | 12/20/2022 | 8 | 7 | 1 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 3/28/2024 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 642534 | 01534 | 5.76 | Solar | 05_01_552L1 | 09/24/2024 | 10/08/2024 | 1 | 0 | 1 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | HAMILTON | 671945 | 01982 | 3.8 | Solar | 05_01_9J352 | 02/20/2025 | 03/26/2025 | 8 | 4 | 4 | 03/27/2025 | 03/27/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 329362 | 01840 | 10 | Solar | 05_05_320W5 | 01/18/2021 | 02/12/2021 | 19 | 16 | 3 | 02/16/2021 | 02/16/2021 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/11/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 650597 | 01921 | 7.6 | Solar | 05_05_320W3 | 10/30/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/30/2024 | 1/26/2026 | Y | EXP | 365 | 01/16/2025 | 02/27/2025 | 43 | 0 | 43 |  |  | 7/31/2025 | Connected |  | N
National Grid | BILLERICA | 175187 | 01862 | 60 | Natural Gas | 05_12_51L3 | 11/14/2013 | 11/14/2013 | 6 | 0 | 6 | 11/25/2013 | 11/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2013 |  | 2/17/2014 | N | EXP | 69 |  |  | 0 | 0 | 0 | 5/1/2014 | 5/1/2014 | 5/27/2014 | Connected |  | N
National Grid | SALISBURY | 550449 | 01952 | 50 | Solar | 05_14_2J3 | 08/25/2023 | 09/21/2023 | 18 | 10 | 8 | 09/22/2023 | 09/22/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2023 | 08/25/2023 | 12/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 693640 | 01464 | 17.6 | Solar | 05_14_56L3 | 06/03/2025 | 06/05/2025 | 2 | 0 | 2 | 06/06/2025 | 06/06/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2025 | Connected |  | N
National Grid | OXFORD | 482365 | 01540 | 7.6 | Solar | 05_14_70L3 | 01/17/2023 | 01/19/2023 | 2 | 0 | 2 | 01/20/2023 | 01/20/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 |  | 3/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2023 | Connected |  | N
National Grid | SPENCER | 311019 | 01562 | 7.6 | Solar | 05_14_7L4 | 09/22/2020 | 09/23/2020 | 0 | 0 | 0 | 09/24/2020 | 09/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 |  | 10/20/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175811 | 01604 | 15.2 | Solar | 05_01_227W3 | 05/18/2015 | 05/18/2015 | 3 | 3 | 0 | 05/27/2015 | 05/27/2015 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2015 |  | 1/5/2018 | N | EXP | 938 |  |  | 0 | 0 | 0 | 6/22/2015 | 6/22/2015 |  | Withdrawn |  | Y
National Grid | FALL RIVER | 495957 | 02720 | 6.96 | Solar | 05_01_406L3 | 02/03/2023 | 02/08/2023 | 3 | 1 | 2 | 02/09/2023 | 02/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/03/2023 | 7/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2023 | Connected |  | N
National Grid | NORTHBRIDGE | 648467 | 01534 | 0 | Solar | 05_01_552L1 | 10/21/2024 | 10/24/2024 | 4 | 2 | 2 | 10/25/2024 | 10/25/2024 | 30 | 16 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | BEVERLY | 722531 | 01915 | 15.36 | Solar | 05_01_9J352 | 09/29/2025 | 10/27/2025 | 19 | 17 | 2 | 10/28/2025 | 10/28/2025 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | LAWRENCE | 337942 | 01840 | 0 | Other | 05_05_320W5 | 04/07/2021 | 04/30/2021 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/02/2021 | 21 | 1 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 679652 | 01845 | 7.6 | Solar | 05_05_320W3 | 03/24/2025 | 04/25/2025 | 24 | 20 | 4 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 175468 | 01824 | 4.73 | Solar | 05_12_51L3 | 11/25/2014 | 11/25/2014 | 5 | 0 | 5 | 12/04/2014 | 12/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2015 | 11/25/2014 | 4/30/2015 | Y | EXP | 71 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 | 3/9/2015 | 3/9/2015 | 11/23/2015 | Connected |  | N
National Grid | SALISBURY | 174787 | 01952 | 100 | Solar | 05_14_2J4 | 11/11/2012 | 11/11/2012 | 5 | 0 | 5 | 11/27/2012 | 11/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2013 | 11/11/2012 | 8/11/2013 | Y | EXP | 30 | 03/07/2014 | 12/08/2014 | 187 | 0 | 187 | 4/23/2014 | 4/23/2014 | 4/24/2014 | Connected |  | N
National Grid | SHIRLEY | 707133 | 01464 | 21.38 | Solar | 05_14_56L3 | 07/24/2025 | 07/28/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2026 | Connected |  | N
National Grid | CHARLTON | 503539 | 01507 | 6.3 | Solar | 05_14_70L3 | 02/21/2023 | 02/22/2023 | 1 | 0 | 1 | 02/23/2023 | 02/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 6/22/2024 | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 329558 | 01562 | 7.6 | Solar | 05_14_7L4 | 12/21/2020 | 12/30/2020 | 5 | 0 | 5 | 12/31/2020 | 12/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2021 | 12/21/2020 | 9/14/2022 | Y | EXP | 365 | 07/20/2021 | 09/10/2021 | 52 | 3 | 49 |  |  | 9/27/2021 | Connected |  | N
National Grid | WORCESTER | 175924 | 01604 | 997.6 | Solar | 05_01_227W3 | 05/29/2015 | 05/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2015 | 07/01/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2016 | 05/29/2015 | 11/30/2015 | Y | STD | 58 |  |  | 0 | 0 | 0 | 8/1/2017 | 8/1/2017 | 8/1/2017 | Connected |  | N
National Grid | WHITINSVILLE | 524689 | 01588 | 0 | Solar | 05_01_406L3 | 05/08/2023 | 05/10/2023 | 2 | 0 | 2 | 05/11/2023 | 05/11/2023 | 199 | 180 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 648713 | 01534 | 10 | Solar | 05_01_552L1 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 44 | 19 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/04/2024 | 2/25/2026 | Y | EXP | 365 | 06/12/2025 | 11/21/2025 | 163 | 0 | 163 |  |  | 12/17/2025 | Connected |  | N
National Grid | BEVERLY | 743749 | 01915 | 5.7 | Solar | 05_01_9J360 | 01/06/2026 | 01/28/2026 | 2 | 0 | 2 | 02/05/2026 | 02/05/2026 | 16 | 1 | 15 | 03/24/2026 |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | LAWRENCE | 450732 | 01840 | 19.195 | Solar | 05_05_320W5 | 08/11/2022 | 08/18/2022 | 6 | 4 | 2 | 08/19/2022 | 08/19/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2022 | 08/11/2022 | 10/17/2023 | Y | EXP | 365 | 12/16/2022 | 01/18/2023 | 34 | 0 | 34 |  |  | 1/23/2023 | Connected |  | N
National Grid | BOXFORD | 680520 | 01921 | 3.8 | Solar | 05_05_320W3 | 03/25/2025 | 04/15/2025 | 7 | 2 | 5 | 04/16/2025 | 04/16/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 177285 | 01824 | 10 | Solar | 05_12_51L3 | 06/16/2016 | 06/16/2016 | 1 | 1 | 0 | 06/20/2016 | 06/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 | 06/16/2016 | 6/21/2017 | Y | EXP | 358 | 11/10/2016 | 01/05/2017 | 36 | 0 | 36 | 1/9/2017 | 1/9/2017 | 1/9/2017 | Connected |  | N
National Grid | SALISBURY | 175135 | 01952 | 150 | Solar | 05_14_2J4 | 11/11/2012 | 11/11/2012 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2013 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 717140 | 01464 | 7.6 | Solar | 05_14_56L3 | 09/11/2025 | 10/07/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 09/11/2025 | 11/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | OXFORD | 544628 | 01540 | 0 | Solar | 05_14_70L3 | 07/31/2023 | 08/01/2023 | 1 | 0 | 1 | 08/02/2023 | 08/02/2023 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 |  | 9/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2024 | Connected |  | N
National Grid | SPENCER | 371237 | 01562 | 10 | Solar | 05_14_7L4 | 07/21/2021 | 09/28/2021 | 48 | 38 | 10 | 09/29/2021 | 09/29/2021 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  | 9/27/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176391 | 01604 | 168 | Solar | 05_01_227W3 | 02/01/2016 | 02/01/2016 | 0 | 0 | 0 | 02/03/2016 | 02/03/2016 | 240 | 0 | 240 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 2/8/2017 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 526264 | 01590 | 7.6 | Solar | 05_01_406L3 | 05/22/2023 | 05/25/2023 | 3 | 0 | 3 | 05/26/2023 | 05/26/2023 | 29 | 8 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 | 05/22/2023 | 7/9/2024 | Y | EXP | 365 | 08/10/2023 | 09/11/2023 | 33 | 0 | 33 |  |  | 10/4/2023 | Connected |  | N
National Grid | WHITINSVILLE | 648709 | 01588 | 10 | Solar | 05_01_552L1 | 11/04/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | BEVERLY | 755021 | 01915 | 5.76 | Solar | 05_01_9J360 | 03/06/2026 | 03/10/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 377003 | 01840 | 20.8 | Solar | 05_05_320W5 | 08/26/2021 |  | 186 | 167 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 684546 | 01845 | 3.48 | Solar | 05_05_320W3 | 04/11/2025 | 05/05/2025 | 1 | 0 | 1 | 05/06/2025 | 05/06/2025 | 42 | 26 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | BILLERICA | 178288 | 01862 | 7.6 | Solar | 05_12_51L3 | 03/28/2018 | 03/28/2018 | 7 | 0 | 7 | 04/09/2018 | 04/09/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 | 03/28/2018 | 7/15/2021 | Y | EXP | 317 |  |  | 0 | 0 | 0 |  |  | 6/22/2021 | Connected |  | N
National Grid | SALISBURY | 186700 | 01952 | 15.2 | Solar | 05_14_2J4 | 06/22/2018 | 06/22/2018 | 0 | 0 | 0 | 06/25/2018 | 06/25/2018 | 11 | 10 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2018 | Connected |  | N
National Grid | SHIRLEY | 731974 | 01464 | 20 | Solar | 05_14_56L3 | 11/06/2025 | 11/12/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 1/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2026 | Connected |  | N
National Grid | OXFORD | 655143 | 01540 | 7.6 | Solar | 05_14_70L3 | 11/20/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/20/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | SPENCER | 427409 | 01562 | 60 | Solar | 05_14_7L4 | 05/09/2022 | 05/19/2022 | 8 | 0 | 8 | 05/20/2022 | 05/20/2022 | 35 | 17 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2022 | 05/09/2022 | 9/22/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2022 | Connected |  | N
National Grid | WORCESTER | 176808 | 01604 | 13.6 | Solar | 05_01_227W3 | 04/27/2016 | 04/27/2016 | 8 | 8 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 |  | 5/3/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBRIDGE | 568942 | 01534 | 14.79 | Solar | 05_01_406L3 | 11/08/2023 | 11/13/2023 | 2 | 1 | 1 | 11/14/2023 | 11/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2023 | 11/08/2023 | 12/20/2024 | Y | EXP | 365 | 02/16/2024 | 02/16/2024 | 1 | 0 | 1 |  |  | 4/3/2024 | Connected |  | N
National Grid | GRAFTON | 656206 | 01560 | 7.6 | Solar | 05_01_552L1 | 11/22/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/22/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | BEVERLY | 177344 | 01915 | 15.2 | Solar | 05_01_9J360 | 11/22/2016 | 11/22/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2016 |  | 1/26/2018 | N | EXP | 422 |  |  | 0 | 0 | 0 | 1/9/2018 | 1/9/2018 | 1/9/2018 | Connected |  | N
National Grid | LAWRENCE | 394432 | 01840 | 15.36 | Solar | 05_05_320W5 | 12/16/2021 | 12/28/2021 | 1 | 0 | 1 | 12/20/2021 | 12/20/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 |  | 5/27/2023 | N | EXP | 387 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 685316 | 01921 | 7.6 | Solar | 05_05_320W3 | 04/15/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 | 04/15/2025 | 7/2/2026 | Y | EXP | 365 | 09/16/2025 | 12/02/2025 | 78 | 0 | 78 |  |  | 2/17/2026 | Connected |  | N
National Grid | CHELMSFORD | 184467 | 01824 | 51.75 | Solar | 05_12_51L3 | 06/18/2018 | 06/18/2018 | 0 | 0 | 0 | 06/22/2018 | 06/22/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 |  | 10/7/2019 | N | EXP | 467 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | Connected |  | N
National Grid | SALISBURY | 586766 | 01952 | 15.76 | Solar | 05_14_2J4 | 05/08/2024 | 06/21/2024 | 30 | 29 | 1 | 06/24/2024 | 06/24/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 9/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | SHIRLEY | 712528 | 01464 | 0 | Solar | 05_14_57L1 | 08/15/2025 | 08/25/2025 | 6 | 3 | 3 | 08/26/2025 | 08/26/2025 | 71 | 54 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | OXFORD | 662120 | 01540 | 7.6 | Solar | 05_14_70L3 | 12/21/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 521126 | 01562 | 0 | Solar | 05_14_7L4 | 04/24/2023 | 04/28/2023 | 4 | 1 | 3 | 05/01/2023 | 05/01/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2023 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177274 | 01604 | 0 | Solar | 05_01_227W3 | 02/06/2017 | 02/06/2017 | 45 | 44 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2017 | 04/24/2017 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 | 02/06/2017 | 2/18/2023 | Y | STD | 1017 | 10/30/2019 | 10/29/2019 | 0 | 0 | 0 |  |  | 10/10/2022 | Connected |  | N
National Grid | NORTHBRIDGE | 568197 | 01534 | 0 | Battery Add-On | 05_01_406L3 | 11/02/2023 | 12/13/2023 | 27 | 24 | 3 | 12/14/2023 | 12/14/2023 | 93 | 69 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2024 |  | 6/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | GRAFTON | 662768 | 01560 | 3.8 | Solar | 05_01_552L1 | 12/27/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMILTON | 197281 | 01982 | 10 | Solar | 05_01_9J360 | 10/01/2018 | 10/22/2018 | 3 | 3 | 0 | 10/23/2018 | 10/23/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 | 10/01/2018 | 6/4/2019 | Y | EXP | 224 | 03/21/2019 | 03/20/2019 | 0 | 0 | 0 |  |  | 5/4/2019 | Connected |  | N
National Grid | LAWRENCE | 406978 | 01840 | 10 | Solar | 05_05_320W5 | 02/21/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/21/2022 | 8/3/2023 | Y | EXP | 365 | 06/23/2022 | 07/15/2022 | 23 | 0 | 23 |  |  | 8/13/2022 | Connected |  | N
National Grid | BOXFORD | 708476 | 01921 | 15.2 | Solar | 05_05_320W3 | 07/30/2025 | 08/05/2025 | 4 | 0 | 4 | 08/06/2025 | 08/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2025 | Connected |  | N
National Grid | CHELMSFORD | 184417 | 01824 | 24 | Solar | 05_12_51L3 | 06/22/2018 | 06/22/2018 | 2 | 2 | 0 | 06/27/2018 | 06/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2018 |  | 11/1/2019 | N | EXP | 483 |  |  | 0 | 0 | 0 |  |  | 10/29/2019 | Connected |  | N
National Grid | AMESBURY | 652372 | 01913 | 116 | Solar | 05_14_2J6 | 05/08/2025 | 09/18/2025 | 91 | 82 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 02/20/2026 |  | 29 | 16 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SHIRLEY | 719310 | 01464 | 20.62 | Solar | 05_14_57L1 | 09/16/2025 | 09/17/2025 | 1 | 0 | 1 | 09/18/2025 | 09/18/2025 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 | 09/16/2025 | 11/3/2026 | Y | EXP | 365 | 03/27/2026 |  | 6 | 0 | 6 |  |  |  | Construction |  | N
National Grid | OXFORD | 306207 | 01540 | 246.6 | Solar | 05_14_70L4 | 02/03/2021 | 02/17/2021 | 8 | 0 | 8 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2021 | 02/03/2021 | 8/19/2026 | Y | STD | 392 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SPENCER | 529466 | 01562 | 15.2 | Solar | 05_14_7L4 | 05/26/2023 | 05/30/2023 | 2 | 1 | 1 | 05/31/2023 | 05/31/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2023 |  | 7/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2023 | Connected |  | N
National Grid | WORCESTER | 177337 | 01604 | 16 | Solar | 05_01_227W3 | 09/01/2016 | 09/01/2016 | 12 | 12 | 0 | 09/20/2016 | 09/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2016 |  | 9/6/2017 | N | EXP | 350 |  |  | 0 | 0 | 0 | 3/23/2017 | 3/23/2017 | 3/23/2017 | Connected |  | N
National Grid | SUTTON | 578775 | 01590 | 6.09 | Solar | 05_01_406L3 | 01/08/2024 | 01/12/2024 | 4 | 0 | 4 | 01/16/2024 | 01/16/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | WHITINSVILLE | 668644 | 01588 | 7.6 | Solar | 05_01_552L1 | 01/29/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 01/29/2025 | 4/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2025 | Connected |  | N
National Grid | HAMILTON | 232897 | 01982 | 7.6 | Solar | 05_01_9J360 | 06/19/2019 | 07/08/2019 | 12 | 12 | 0 | 07/09/2019 | 07/09/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 06/19/2019 | 7/20/2020 | Y | EXP | 365 | 04/09/2020 | 05/15/2020 | 34 | 0 | 34 |  |  | 5/18/2020 | Connected |  | N
National Grid | LAWRENCE | 533804 | 01840 | 15.36 | Solar | 05_05_320W5 | 06/26/2023 | 08/07/2023 | 30 | 28 | 2 |  |  | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 716907 | 01886 | 7.68 | Solar | 05_05_320W3 | 09/04/2025 | 10/15/2025 | 3 | 0 | 3 | 10/30/2025 | 10/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 189641 | 01852 | 5 | Solar | 05_12_51L3 | 02/26/2019 | 07/05/2018 | 5 | 0 | 5 | 03/07/2019 | 03/07/2019 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 418695 | 01952 | 57.6 | Solar | 05_14_2J8 | 03/18/2022 | 04/29/2022 | 29 | 19 | 10 | 05/02/2022 | 05/02/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2022 |  | 10/2/2026 | N | EXP | 184 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SHIRLEY | 733497 | 01464 | 19 | Solar | 05_14_57L1 | 01/02/2026 | 01/28/2026 | 15 | 12 | 3 | 01/29/2026 | 01/29/2026 | 44 | 23 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | OXFORD | 714533 | 01540 | 500 | Solar | 05_14_70L4 | 10/10/2025 | 11/10/2025 | 19 | 13 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 12/10/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SPENCER | 566104 | 01562 | 70 | Solar | 05_14_7L4 | 11/06/2023 | 11/21/2023 | 10 | 0 | 10 | 11/22/2023 | 11/22/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 | 11/06/2023 | 5/6/2025 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | Y
National Grid | WORCESTER | 184835 | 01604 | 7.6 | Solar | 05_01_227W3 | 05/23/2018 | 05/23/2018 | 8 | 0 | 8 | 06/06/2018 | 06/06/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2018 |  | 8/5/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2018 | Connected |  | N
National Grid | SUTTON | 579001 | 01590 | 140 | Solar | 05_01_406L3 | 12/21/2023 | 01/07/2024 | 10 | 0 | 10 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 673877 | 01534 | 10 | Solar | 05_01_552L1 | 02/24/2025 | 03/17/2025 | 3 | 0 | 3 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMILTON | 241416 | 01982 | 7.36 | Solar | 05_01_9J360 | 07/16/2019 | 07/17/2019 | 1 | 1 | 0 | 07/18/2019 | 07/18/2019 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 | 07/16/2019 | 11/9/2020 | Y | EXP | 365 | 08/22/2020 | 10/02/2020 | 41 | 0 | 41 |  |  | 11/4/2020 | Connected |  | N
National Grid | LAWRENCE | 542382 | 01840 | 1000 | Solar | 05_05_320W5 | 01/10/2024 |  | 69 | 61 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 722246 | 01886 | 14.44 | Solar | 05_05_320W3 | 09/30/2025 | 10/20/2025 | 4 | 0 | 4 | 11/06/2025 | 11/06/2025 | 78 | 60 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 306908 | 01862 | 13.6 | Solar | 05_12_51L3 | 08/14/2020 | 08/18/2020 | 2 | 2 | 0 | 08/19/2020 | 08/19/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2020 |  | 8/17/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2020 | Connected |  | N
National Grid | SALISBURY | 194466 | 01952 | 480 | Solar | 05_14_2J8 | 08/27/2018 | 08/28/2018 | 4 | 0 | 4 | 09/24/2018 | 09/24/2018 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 176080 | 01464 | 323 | Solar | 05_14_57L1 | 08/21/2015 | 08/21/2015 | 0 | 0 | 0 | 08/21/2015 | 08/21/2015 | 306 | 14 | 292 | 11/05/2015 | 09/23/2016 | 219 | 14 | 205 |  |  | 0 | 0 | 0 | 09/23/2016 | 219 | 14 | 205 |  |  | 0 | 0 | 0 | 2/9/2016 | 08/21/2015 | 4/15/2017 | Y | EXP | 431 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 175414 | 01540 | 76 | Solar | 05_14_70L4 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2014 | 07/09/2014 | 11/28/2014 | Y | EXP | 116 | 03/27/2015 | 05/11/2015 | 30 | 0 | 30 | 8/7/2014 | 8/7/2014 | 7/20/2015 | Connected |  | N
National Grid | SPENCER | 574923 | 01562 | 10 | Solar | 05_14_7L4 | 04/03/2024 | 12/07/2023 | 5 | 3 | 2 | 04/10/2024 | 04/10/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 04/03/2024 | 5/14/2025 | Y | EXP | 365 | 06/05/2024 | 07/17/2024 | 43 | 0 | 43 |  |  | 7/19/2024 | Connected |  | N
National Grid | WORCESTER | 199446 | 01604 | 250 | Solar | 05_01_227W3 | 10/26/2018 | 10/30/2018 | 1 | 0 | 1 | 10/31/2018 | 10/31/2018 | 10 | 0 | 10 | 11/16/2018 | 01/08/2019 | 33 | 0 | 33 |  |  | 0 | 0 | 0 | 01/08/2019 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 594064 | 01590 | 7.6 | Solar | 05_01_406L3 | 03/06/2024 | 03/12/2024 | 4 | 0 | 4 | 03/13/2024 | 03/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | GRAFTON | 676225 | 01560 | 7.6 | Solar | 05_01_552L1 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N
National Grid | BEVERLY | 257227 | 01915 | 7.6 | Solar | 05_01_9J360 | 10/14/2019 | 10/15/2019 | 0 | 0 | 0 | 10/16/2019 | 10/16/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2019 | 10/14/2019 | 10/14/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2020 | Connected |  | N
National Grid | LAWRENCE | 545580 | 01840 | 7.6 | Solar | 05_05_320W5 | 08/21/2023 | 09/01/2023 | 10 | 9 | 1 | 09/05/2023 | 09/05/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 08/21/2023 | 11/15/2024 | Y | EXP | 365 | 01/19/2024 | 04/03/2024 | 76 | 0 | 76 |  |  | 4/5/2024 | Connected |  | N
National Grid | WESTFORD | 177459 | 01886 | 3000 | Solar | 05_05_320W5 | 12/09/2016 | 12/09/2016 | 43 | 43 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/14/2017 | 05/10/2017 | 59 | 45 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/17/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Terminated |  | N
National Grid | BILLERICA | 309531 | 01862 | 5.8 | Solar | 05_12_51L3 | 09/01/2020 | 09/02/2020 | 1 | 1 | 0 | 09/03/2020 | 09/03/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2020 |  | 9/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2020 | Connected |  | N
National Grid | SALISBURY | 552093 | 01952 | 200 | Solar | 05_14_2J8 | 08/31/2023 | 09/28/2023 | 20 | 10 | 10 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 176617 | 01464 | 200 | Solar | 05_14_57L1 | 02/17/2016 | 02/17/2016 | 3 | 3 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2016 |  | 2/22/2017 | N | EXP | 334 |  |  | 0 | 0 | 0 | 5/31/2016 | 5/31/2016 | 5/31/2016 | Connected |  | N
National Grid | CHARLTON | 177237 | 01507 | 472.9 | Solar | 05_14_70L4 | 02/01/2017 | 02/01/2017 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 608674 | 01562 | 3.8 | Solar | 05_14_7L4 | 05/03/2024 | 05/16/2024 | 2 | 0 | 2 | 05/17/2024 | 05/17/2024 | 31 | 22 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 | 05/03/2024 | 7/16/2025 | Y | EXP | 365 | 10/24/2024 | 11/20/2024 | 28 | 0 | 28 |  |  | 1/23/2025 | Connected |  | N
National Grid | WORCESTER | 232315 | 01604 | 250 | Solar | 05_01_227W3 | 12/11/2019 | 01/14/2020 | 20 | 15 | 5 | 01/15/2020 | 01/15/2020 | 56 | 36 | 20 | 05/19/2020 | 09/16/2020 | 98 | 3 | 95 |  |  | 0 | 0 | 0 | 09/16/2020 | 98 | 3 | 95 |  |  | 0 | 0 | 0 | 9/16/2020 |  | 12/30/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 594844 | 01590 | 6 | Solar | 05_01_406L3 | 03/06/2024 | 03/26/2024 | 15 | 12 | 3 | 03/27/2024 | 03/27/2024 | 21 | 17 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 03/06/2024 | 4/30/2025 | Y | EXP | 365 | 06/11/2024 | 08/19/2024 | 70 | 0 | 70 |  |  | 8/20/2024 | Connected |  | N
National Grid | GRAFTON | 678598 | 01519 | 5.76 | Solar | 05_01_552L1 | 03/17/2025 | 04/03/2025 | 8 | 6 | 2 | 04/29/2025 | 04/29/2025 | 24 | 0 | 24 | 07/21/2025 | 09/17/2025 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 09/17/2025 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMILTON | 623844 | 01982 | 7.6 | Solar | 05_01_9J360 | 07/10/2024 | 07/16/2024 | 1 | 0 | 1 | 07/17/2024 | 07/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 |  | 9/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2024 | Connected |  | N
National Grid | LAWRENCE | 620478 | 01840 | 15.2 | Solar | 05_05_320W5 | 06/27/2024 | 07/01/2024 | 2 | 0 | 2 | 07/02/2024 | 07/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/27/2024 | 7/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | WESTFORD | 657149 | 01886 | 5.76 | Solar | 05_05_320W5 | 11/26/2024 | 03/24/2025 | 48 | 43 | 5 | 03/25/2025 | 03/25/2025 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 339578 | 01862 | 7.6 | Solar | 05_12_51L3 | 01/29/2021 | 02/02/2021 | 1 | 0 | 1 | 02/03/2021 | 02/03/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  | 11/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2021 | Connected |  | N
National Grid | SALISBURY | 681059 | 01952 | 10 | Solar | 05_14_2J8 | 04/04/2025 | 04/22/2025 | 3 | 0 | 3 | 05/02/2025 | 05/02/2025 | 45 | 32 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 | 04/04/2025 | 7/15/2026 | Y | EXP | 365 | 11/04/2025 | 11/26/2025 | 23 | 0 | 23 |  |  | 1/30/2026 | Connected |  | N
National Grid | SHIRLEY | 242635 | 01464 | 0 | Solar | 05_14_57L1 | 07/09/2019 | 07/15/2019 | 3 | 0 | 3 | 07/16/2019 | 07/16/2019 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 7/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2020 | Connected |  | N
National Grid | OXFORD | 204163 | 01540 | 453 | Solar | 05_14_70L4 | 12/18/2018 | 01/10/2019 | 14 | 12 | 2 | 01/11/2019 | 01/11/2019 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 635953 | 01562 | 5.76 | Solar | 05_14_7L4 | 08/28/2024 | 09/03/2024 | 1 | 0 | 1 | 09/04/2024 | 09/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 08/28/2024 | 9/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | WORCESTER | 231499 | 01604 | 250 | Solar | 05_01_227W3 | 12/09/2019 | 01/14/2020 | 19 | 14 | 5 | 03/16/2020 | 03/16/2020 | 15 | 15 | 0 | 05/19/2020 | 10/28/2020 | 102 | 3 | 99 |  |  | 0 | 0 | 0 | 10/28/2020 | 102 | 3 | 99 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 12/28/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITINSVILLE | 636073 | 01588 | 7.6 | Solar | 05_01_406L3 | 08/28/2024 | 10/10/2024 | 17 | 13 | 4 | 10/11/2024 | 10/11/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 680821 | 01590 | 20 | Solar | 05_01_552L1 | 03/26/2025 | 04/02/2025 | 6 | 2 | 4 | 04/03/2025 | 04/03/2025 | 33 | 15 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 | 03/26/2025 | 6/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2026 | Connected |  | N
National Grid | WENHAM | 633459 | 01984 | 5.76 | Solar | 05_01_9J360 | 08/19/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  | 9/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2024 | Connected |  | N
National Grid | LAWRENCE | 626980 | 01840 | 7.6 | Solar | 05_05_320W5 | 07/23/2024 | 07/28/2024 | 4 | 0 | 4 | 07/29/2024 | 07/29/2024 | 39 | 25 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 07/23/2024 | 12/18/2025 | Y | EXP | 365 | 05/23/2025 | 05/22/2025 | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | WESTFORD | 677259 | 01886 | 100 | Solar | 05_05_320W5 | 03/24/2025 | 05/19/2025 | 39 | 30 | 9 |  |  | 40 | 15 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | BILLERICA | 342563 | 01862 | 7.68 | Solar | 05_12_51L3 | 02/17/2021 | 02/23/2021 | 4 | 4 | 0 | 02/24/2021 | 02/24/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 |  | 2/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2021 | Connected |  | N
National Grid | SALISBURY | 745534 | 01952 | 999 | Solar | 05_14_2L1 | 02/26/2026 |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SHIRLEY | 283707 | 01464 | 600 | Natural Gas | 05_14_57L1 | 12/02/2021 | 01/13/2022 | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2022 | 03/14/2022 | 40 | 19 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2023 | 12/02/2021 | 11/6/2024 | Y | STD | 279 | 04/04/2024 | 04/18/2024 | 15 | 0 | 15 |  |  | 9/24/2024 | Connected |  | N
National Grid | OXFORD | 613720 | 01540 | 4.06 | Solar | 05_14_70L4 | 05/28/2024 | 07/31/2024 | 5 | 2 | 3 | 08/01/2024 | 08/01/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 05/28/2024 | 10/1/2025 | Y | EXP | 365 | 11/15/2024 | 12/18/2024 | 34 | 0 | 34 |  |  | 1/9/2025 | Connected |  | Y
National Grid | SPENCER | 653448 | 01562 | 7.6 | Solar | 05_14_7L4 | 12/06/2024 | 12/27/2024 | 8 | 2 | 6 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | WORCESTER | 345461 | 01604 | 800 | Solar | 05_01_227W3 | 04/07/2021 | 11/15/2021 | 127 | 122 | 5 |  |  | 101 | 64 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITINSVILLE | 635916 | 01588 | 6 | Solar | 05_01_406L3 | 08/27/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 08/27/2024 | 10/8/2025 | Y | EXP | 365 | 12/13/2024 | 12/12/2024 | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | N
National Grid | SUTTON | 682377 | 01590 | 13.36 | Solar | 05_01_552L1 | 04/02/2025 | 07/02/2025 | 26 | 24 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMILTON | 636201 | 01982 | 5.76 | Solar | 05_01_9J360 | 08/28/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 626948 | 01840 | 7.6 | Solar | 05_05_320W5 | 07/24/2024 | 07/31/2024 | 2 | 1 | 1 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 | 07/24/2024 | 8/15/2025 | Y | EXP | 365 | 11/14/2024 | 12/02/2024 | 19 | 0 | 19 |  |  | 2/5/2025 | Connected |  | N
National Grid | WESTFORD | 710740 | 01886 | 10 | Solar | 05_05_320W5 | 08/08/2025 | 10/10/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 35 | 17 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 354859 | 01862 | 6.38 | Solar | 05_12_51L3 | 04/27/2021 | 04/28/2021 | 1 | 1 | 0 | 04/29/2021 | 04/29/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2021 |  | 4/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | SALISBURY | 757350 | 01952 | 11.52 | Solar | 05_14_2L1 | 03/19/2026 | 04/01/2026 | 9 | 7 | 2 | 04/02/2026 | 04/02/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SHIRLEY | 295174 | 01464 | 7.68 | Solar | 05_14_57L1 | 06/05/2020 | 07/09/2020 | 24 | 23 | 1 | 07/10/2020 | 07/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 7/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2020 | Connected |  | N
National Grid | OXFORD | 636406 | 01540 | 200 | Solar | 05_14_70L4 | 09/06/2024 | 10/23/2024 | 32 | 23 | 9 | 10/24/2024 | 10/24/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 | 09/06/2024 | 5/30/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 501405 | 01562 | 180 | Solar | 05_14_8L1 | 05/10/2023 | 05/31/2023 | 14 | 5 | 9 | 06/01/2023 | 06/01/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 05/10/2023 | 3/28/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 346662 | 01604 | 500 | Solar | 05_01_227W3 | 04/07/2021 | 04/23/2021 | 10 | 0 | 10 |  |  | 240 | 218 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 637279 | 01590 | 6 | Solar | 05_01_406L3 | 09/03/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 20 | 6 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | SUTTON | 688712 | 01590 | 15.2 | Solar | 05_01_552L1 | 05/01/2025 | 05/19/2025 | 7 | 3 | 4 | 07/10/2025 | 07/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | BEVERLY | 641893 | 01915 | 5.76 | Solar | 05_01_9J360 | 09/20/2024 | 02/21/2025 | 3 | 0 | 3 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2025 | Connected |  | N
National Grid | CHELMSFORD | 639198 | 01863 | 7.6 | Solar | 05_05_320W5 | 09/10/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/10/2024 | 12/10/2025 | Y | EXP | 365 | 02/13/2025 | 02/24/2025 | 12 | 0 | 12 |  |  | 4/1/2025 | Connected |  | N
National Grid | WESTFORD | 738203 | 01886 | 11.52 | Solar | 05_05_320W5 | 12/04/2025 | 12/08/2025 | 2 | 0 | 2 | 12/09/2025 | 12/09/2025 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 406056 | 01862 | 0 | Battery Add-On | 05_12_51L3 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 02/14/2022 | 3 | 0 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 175307 | 01952 | 910 | Solar | 05_14_2L1 | 06/30/2014 | 06/30/2014 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2014 | 08/06/2014 | 23 | 0 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2016 | 06/30/2014 | 8/3/2021 | Y | STD | 316 | 05/21/2019 | 07/21/2021 | 406 | 4 | 402 |  |  | 8/3/2021 | Connected |  | N
National Grid | SHIRLEY | 311522 | 01464 | 11.4 | Solar | 05_14_57L1 | 01/20/2021 | 01/25/2021 | 2 | 0 | 2 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2021 | 01/20/2021 | 4/5/2022 | Y | EXP | 365 | 08/06/2021 | 12/29/2021 | 146 | 7 | 139 |  |  | 2/9/2022 | Connected |  | N
National Grid | OXFORD | 673217 | 01540 | 960 | Solar | 05_14_70L5 | 05/23/2025 | 06/26/2025 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2025 | 07/22/2025 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SPENCER | 725174 | 01562 | 7.6 | Solar | 05_14_8L1 | 10/08/2025 | 11/17/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 346659 | 01604 | 250 | Solar | 05_01_227W3 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 | 04/26/2021 | 04/26/2021 | 92 | 29 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITINSVILLE | 638781 | 01588 | 5.76 | Solar | 05_01_406L3 | 09/09/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/09/2024 | 3/5/2026 | Y | EXP | 365 | 06/12/2025 | 12/08/2025 | 180 | 0 | 180 |  |  | 12/1/2025 | Connected |  | N
National Grid | WHITINSVILLE | 693410 | 01588 | 4.94 | Solar | 05_01_552L1 | 05/21/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMILTON | 650128 | 01982 | 6 | Solar | 05_01_9J360 | 10/28/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | TYNGSBORO | 647702 | 01879 | 10 | Solar | 05_05_320W5 | 10/28/2024 | 11/19/2024 | 8 | 5 | 3 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2025 | Connected |  | N
National Grid | WESTFORD | 742575 | 01886 | 10 | Solar | 05_05_320W5 | 12/29/2025 | 01/05/2026 | 3 | 0 | 3 | 01/27/2026 | 01/27/2026 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2026 |  | 3/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 413470 | 01862 | 15.2 | Solar | 05_12_51L3 | 08/16/2022 | 02/26/2022 | 2 | 0 | 2 | 08/19/2022 | 08/19/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2022 |  | 9/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 176776 | 01810 | 390 | Solar | 05_14_2L1 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 | 02/15/2016 | 02/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2016 | 11/04/2015 | 6/14/2019 | Y | EXP | 1206 | 07/11/2017 | 08/23/2017 | 0 | 0 | 0 |  |  | 6/12/2019 | Connected |  | N
National Grid | SHIRLEY | 318483 | 01464 | 20 | Solar | 05_14_57L1 | 10/09/2020 | 10/14/2020 | 1 | 0 | 1 | 10/15/2020 | 10/15/2020 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 4/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2021 | Connected |  | N
National Grid | OXFORD | 737499 | 01540 | 5.76 | Solar | 05_14_70L5 | 12/02/2025 | 12/03/2025 | 1 | 0 | 1 | 01/13/2026 | 01/13/2026 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  | 3/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 728119 | 01562 | 10 | Solar | 05_14_8L1 | 10/21/2025 | 11/03/2025 | 8 | 2 | 6 | 11/04/2025 | 11/04/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 361884 | 01604 | 9.8 | Solar | 05_01_227W3 | 06/03/2021 | 06/08/2021 | 3 | 2 | 1 | 06/09/2021 | 06/09/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2021 |  | 8/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2022 | Connected |  | N
National Grid | WHITINSVILLE | 644256 | 01588 | 5.76 | Solar | 05_01_406L3 | 10/01/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/01/2024 | 12/12/2025 | Y | EXP | 365 | 03/01/2025 | 03/20/2025 | 12 | 0 | 12 |  |  | 4/7/2025 | Connected |  | N
National Grid | SUTTON | 697891 | 01526 | 15.2 | Solar | 05_01_552L1 | 06/11/2025 | 06/23/2025 | 7 | 4 | 3 | 06/24/2025 | 06/24/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | HAMILTON | 652574 | 01982 | 8.41 | Solar | 05_01_9J360 | 11/06/2024 | 12/11/2024 | 13 | 7 | 6 | 12/12/2024 | 12/12/2024 | 65 | 50 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 653727 | 01863 | 10 | Solar | 05_05_320W5 | 11/18/2024 | 12/19/2024 | 4 | 0 | 4 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 3/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | WESTFORD | 174284 | 01886 | 2000 | Solar | 05_05_320W5 | 12/17/2011 | 12/17/2011 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 485207 | 01862 | 19 | Solar | 05_12_51L3 | 12/13/2022 | 12/15/2022 | 2 | 0 | 2 | 12/16/2022 | 12/16/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 2/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | LAWRENCE | 177005 | 01843 | 720 | Solar | 05_14_2L1 | 10/10/2016 | 10/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 | 12/15/2016 | 45 | 33 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 | 10/10/2016 | 10/30/2020 | Y | STD | 707 | 08/06/2019 | 10/16/2020 | 438 | 5 | 433 |  |  | 10/21/2020 | Connected |  | N
National Grid | SHIRLEY | 330673 | 01464 | 15.2 | Solar | 05_14_57L1 | 12/09/2020 | 12/18/2020 | 6 | 0 | 6 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  | 11/3/2022 | N | EXP | 630 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 748234 | 01540 | 5.76 | Solar | 05_14_70L5 | 01/29/2026 | 02/02/2026 | 3 | 0 | 3 | 03/17/2026 | 03/17/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SPENCER | 748992 | 01562 | 22.14 | Solar | 05_14_8L1 | 02/03/2026 | 02/06/2026 | 3 | 0 | 3 | 02/09/2026 | 02/09/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2026 |  | 3/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 562155 | 01604 | 10 | Solar | 05_01_227W3 | 11/29/2023 | 12/19/2023 | 14 | 10 | 4 | 12/20/2023 | 12/20/2023 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 11/29/2023 | 4/1/2025 | Y | EXP | 365 | 06/18/2024 | 07/10/2024 | 23 | 0 | 23 |  |  | 7/22/2024 | Connected |  | Y
National Grid | DOUGLAS | 644594 | 01516 | 10 | Solar | 05_01_406L3 | 10/02/2024 | 11/04/2024 | 4 | 0 | 4 | 11/05/2024 | 11/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | WHITINSVILLE | 702237 | 01588 | 21.75 | Solar | 05_01_552L1 | 07/01/2025 | 08/25/2025 | 37 | 32 | 5 | 08/26/2025 | 08/26/2025 | 41 | 22 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2026 | Connected |  | N
National Grid | HAMILTON | 655724 | 01982 | 7.6 | Solar | 05_01_9J360 | 11/20/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | CHELMSFORD | 664108 | 01824 | 10 | Solar | 05_05_320W5 | 01/07/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | WESTFORD | 174283 | 01886 | 2000 | Solar | 05_05_320W5 | 12/17/2011 | 12/17/2011 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 04/30/2014 | 09/08/2014 | 89 | 0 | 89 |  |  | 8/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 484468 | 01821 | 0 | Solar | 05_12_51L3 | 11/01/2023 | 11/02/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 76 | 25 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 178330 | 01843 | 7.6 | Solar | 05_14_2L1 | 03/30/2018 | 03/30/2018 | 5 | 0 | 5 | 04/09/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 9/23/2020 | N | EXP | 340 |  |  | 0 | 0 | 0 |  |  | 8/20/2020 | Connected |  | N
National Grid | SHIRLEY | 391848 | 01464 | 0 | Other | 05_14_57L1 | 12/16/2021 | 01/05/2022 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 02/03/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 175886 | 01507 | 3.8 | Solar | 05_14_70L5 | 05/26/2015 | 05/26/2015 | 0 | 0 | 0 | 05/28/2015 | 05/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2015 |  | 10/30/2015 | N | EXP | 122 |  |  | 0 | 0 | 0 | 11/16/2015 | 11/16/2015 | 11/19/2015 | Connected |  | N
National Grid | SPENCER | 177700 | 01562 | 7.6 | Solar | 05_14_8L1 | 03/21/2017 | 03/21/2017 | 4 | 4 | 0 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2017 |  | 3/27/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 6/20/2017 | 6/20/2017 | 7/12/2017 | Connected |  | N
National Grid | WORCESTER | 612875 | 01604 | 11.5 | Solar | 05_01_227W3 | 05/23/2024 | 05/31/2024 | 5 | 2 | 3 | 06/03/2024 | 06/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/23/2024 | 8/8/2025 | Y | EXP | 365 | 06/10/2025 | 08/11/2025 | 63 | 0 | 63 |  |  | 8/16/2025 | Connected |  | N
National Grid | SUTTON | 644606 | 01590 | 10 | Solar | 05_01_406L3 | 10/03/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/03/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 703266 | 01590 | 18.829 | Solar | 05_01_552L1 | 07/07/2025 | 07/10/2025 | 3 | 0 | 3 | 07/11/2025 | 07/11/2025 | 71 | 53 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WENHAM | 688483 | 01984 | 7.6 | Solar | 05_01_9J360 | 04/29/2025 | 05/14/2025 | 2 | 0 | 2 | 06/02/2025 | 06/02/2025 | 58 | 45 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 669902 | 01824 | 4.35 | Solar | 05_05_320W5 | 02/10/2025 | 09/15/2025 | 64 | 64 | 0 | 09/16/2025 | 09/16/2025 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2025 | Connected |  | N
National Grid | WESTFORD | 174336 | 01886 | 42 | Solar | 05_05_320W5 | 01/26/2012 | 01/26/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2012 |  | 3/9/2012 | N | EXP | 35 |  |  | 0 | 0 | 0 | 4/27/2012 | 4/27/2012 | 5/4/2012 | Connected |  | N
National Grid | BILLERICA | 517501 | 01862 | 0 | Solar | 05_12_51L3 | 04/06/2023 | 06/02/2023 | 39 | 38 | 1 | 06/05/2023 | 06/05/2023 | 289 | 271 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 | 04/06/2023 | 11/30/2025 | Y | EXP | 365 | 10/03/2024 | 11/12/2024 | 41 | 0 | 41 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 178690 | 01810 | 240 | Solar | 05_14_2L1 | 12/20/2017 | 12/20/2017 | 0 | 0 | 0 | 12/20/2017 | 12/20/2017 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/25/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 467561 | 01464 | 0 | Battery Add-On | 05_14_57L1 | 04/04/2023 | 05/22/2023 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2023 | 06/23/2023 | 23 | 6 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 177357 | 01507 | 168 | Solar | 05_14_70L5 | 02/16/2017 | 02/16/2017 | 1 | 0 | 1 | 05/25/2017 | 05/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2017 |  | 2/21/2018 | N | EXP | 247 |  |  | 0 | 0 | 0 | 12/28/2017 | 12/28/2017 | 1/8/2018 | Connected |  | N
National Grid | SPENCER | 178499 | 01562 | 20 | Solar | 05_14_8L1 | 01/23/2018 | 01/23/2018 | 11 | 0 | 11 | 02/08/2018 | 02/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 |  | 1/29/2019 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 8/2/2018 | Connected |  | N
National Grid | WORCESTER | 624233 | 01604 | 10 | Solar | 05_01_227W3 | 07/11/2024 | 08/01/2024 | 1 | 0 | 1 | 08/02/2024 | 08/02/2024 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 07/11/2024 | 9/27/2025 | Y | EXP | 365 | 12/13/2024 | 12/12/2024 | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | WHITINSVILLE | 656827 | 01588 | 7.6 | Solar | 05_01_406L3 | 12/12/2024 | 12/16/2024 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 12/12/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | SUTTON | 712272 | 01590 | 5.76 | Solar | 05_01_552L1 | 08/14/2025 | 09/05/2025 | 3 | 0 | 3 | 12/11/2025 | 12/11/2025 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMILTON | 699741 | 01982 | 5.76 | Solar | 05_01_9J360 | 06/19/2025 | 07/02/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 9/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | TYNGSBORO | 673581 | 01879 | 5.76 | Solar | 05_05_320W5 | 02/25/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 | 02/25/2025 | 5/1/2026 | Y | EXP | 365 | 08/07/2025 | 10/09/2025 | 64 | 0 | 64 |  |  | 11/20/2025 | Connected |  | N
National Grid | WESTFORD | 174613 | 01886 | 1000 | Solar | 05_05_320W5 | 11/16/2010 | 11/16/2010 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2011 | 11/16/2010 | 2/28/2012 | Y | STD | 277 | 10/14/2011 | 02/22/2012 | 86 | 0 | 86 | 8/3/2012 | 8/3/2012 | 2/28/2012 | Connected |  | N
National Grid | BILLERICA | 592675 | 01862 | 34.5 | Solar | 05_12_51L3 | 02/26/2024 | 02/27/2024 | 1 | 0 | 1 | 02/28/2024 | 02/28/2024 | 26 | 22 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2024 | Connected |  | N
National Grid | LAWRENCE | 209967 | 01843 | 910 | Solar | 05_14_2L1 | 03/04/2019 | 03/19/2019 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/20/2019 | 08/22/2019 | 101 | 35 | 66 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 638330 | 01464 | 9.28 | Solar | 05_14_57L1 | 09/09/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 177550 | 01507 | 10 | Solar | 05_14_70L5 | 05/15/2017 | 05/15/2017 | 4 | 3 | 1 | 05/22/2017 | 05/22/2017 | 189 | 0 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2017 |  | 5/21/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 184904 | 01562 | 7.6 | Solar | 05_14_8L1 | 05/28/2018 | 05/28/2018 | 1 | 0 | 1 | 05/31/2018 | 05/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 1/8/2020 | N | EXP | 448 | 10/24/2019 | 11/04/2019 | 11 | 0 | 11 |  |  | 11/20/2019 | Connected |  | N
National Grid | WORCESTER | 639462 | 01604 | 7.6 | Solar | 05_01_227W3 | 09/13/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 09/13/2024 | 12/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | SUTTON | 667517 | 01590 | 17.3 | Solar | 05_01_406L3 | 01/28/2025 | 02/21/2025 | 18 | 14 | 4 | 02/24/2025 | 02/24/2025 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | SUTTON | 715142 | 01590 | 0 | Battery Add-On | 05_01_552L1 | 08/27/2025 | 09/04/2025 | 5 | 0 | 5 | 09/05/2025 | 09/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N
National Grid | BEVERLY | 701039 | 01915 | 7.6 | Solar | 05_01_9J360 | 06/25/2025 | 07/14/2025 | 4 | 0 | 4 | 07/22/2025 | 07/22/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/25/2025 | 8/14/2026 | Y | EXP | 365 | 10/02/2025 | 10/06/2025 | 5 | 0 | 5 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 685167 | 01863 | 9.6 | Solar | 05_05_320W5 | 04/15/2025 | 05/22/2025 | 3 | 0 | 3 | 05/23/2025 | 05/23/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 174612 | 01886 | 1000 | Solar | 05_05_320W5 | 11/16/2010 | 11/16/2010 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2011 | 11/16/2010 | 2/2/2012 | Y | STD | 251 | 10/14/2011 | 01/20/2012 | 64 | 0 | 64 | 8/3/2012 | 8/3/2012 | 2/2/2012 | Connected |  | N
National Grid | BILLERICA | 648934 | 01862 | 4.56 | Solar | 05_12_51L3 | 10/23/2024 | 11/13/2024 | 4 | 1 | 3 | 11/14/2024 | 11/14/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | ANDOVER | 241760 | 01810 | 7.6 | Solar | 05_14_2L1 | 07/24/2019 | 07/25/2019 | 0 | 0 | 0 | 07/26/2019 | 07/26/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 646518 | 01464 | 10 | Solar | 05_14_57L1 | 10/11/2024 | 10/17/2024 | 3 | 0 | 3 | 10/18/2024 | 10/18/2024 | 46 | 22 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | OXFORD | 178469 | 01540 | 11.4 | Solar | 05_14_70L5 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 |  | 5/17/2021 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N
National Grid | SPENCER | 197977 | 01562 | 10 | Solar | 05_14_8L1 | 10/08/2018 | 11/26/2018 | 16 | 16 | 0 | 11/27/2018 | 11/27/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 | 10/08/2018 | 8/28/2019 | Y | EXP | 257 | 04/23/2019 | 05/03/2019 | 10 | 0 | 10 |  |  | 7/23/2019 | Connected |  | N
National Grid | WORCESTER | 646743 | 01604 | 7.6 | Solar | 05_01_227W3 | 10/14/2024 | 11/12/2024 | 11 | 4 | 7 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/14/2024 | 12/24/2025 | Y | EXP | 365 | 02/12/2025 | 03/04/2025 | 21 | 0 | 21 |  |  | 3/11/2025 | Connected |  | N
National Grid | SUTTON | 677208 | 01590 | 10 | Solar | 05_01_406L3 | 03/11/2025 | 03/22/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 | 03/11/2025 | 5/29/2026 | Y | EXP | 365 | 07/22/2025 | 07/22/2025 | 1 | 0 | 1 |  |  | 8/13/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 725840 | 01534 | 5.76 | Solar | 05_01_552L1 | 10/10/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | BEVERLY | 721533 | 01915 | 5.76 | Solar | 05_01_9J360 | 09/24/2025 | 10/08/2025 | 3 | 0 | 3 | 11/10/2025 | 11/10/2025 | 43 | 26 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 686786 | 01863 | 15.2 | Solar | 05_05_320W5 | 04/22/2025 | 04/25/2025 | 3 | 0 | 3 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 04/22/2025 | 6/11/2026 | Y | EXP | 365 | 08/06/2025 | 12/31/2025 | 148 | 0 | 148 |  |  | 1/9/2026 | Connected |  | N
National Grid | WESTFORD | 174645 | 01886 | 44.4 | Solar | 05_05_320W5 | 12/20/2013 | 12/20/2013 | 6 | 0 | 6 | 01/02/2014 | 01/02/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2014 | 12/20/2013 | 2/28/2014 | Y | EXP | 32 | 06/09/2014 | 06/09/2014 | 0 | 0 | 0 | 7/15/2014 | 7/15/2014 | 7/16/2014 | Connected |  | N
National Grid | BILLERICA | 657644 | 01821 | 10 | Solar | 05_12_51L3 | 11/29/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/29/2024 | 2/19/2026 | Y | EXP | 365 | 06/14/2025 | 09/02/2025 | 81 | 0 | 81 |  |  | 9/11/2025 | Connected |  | N
National Grid | LAWRENCE | 332924 | 01843 | 10 | Solar | 05_14_2L1 | 12/18/2020 | 12/22/2020 | 1 | 0 | 1 | 12/23/2020 | 12/23/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/20/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 651800 | 01464 | 7.6 | Solar | 05_14_57L1 | 11/04/2024 | 01/16/2025 | 4 | 0 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/04/2024 | 3/12/2026 | Y | EXP | 365 | 05/16/2025 | 11/21/2025 | 190 | 0 | 190 |  |  | 11/24/2025 | Connected |  | N
National Grid | OXFORD | 185699 | 01540 | 360 | Solar | 05_14_70L5 | 05/18/2018 | 05/18/2018 | 53 | 47 | 6 | 06/22/2018 | 06/22/2018 | 29 | 6 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 199566 | 01562 | 7.6 | Solar | 05_14_8L1 | 10/26/2018 | 11/20/2018 | 13 | 7 | 6 | 11/21/2018 | 11/21/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 | 10/26/2018 | 12/11/2019 | Y | EXP | 365 | 06/05/2019 | 06/04/2019 | 0 | 0 | 0 |  |  | 10/15/2019 | Connected |  | N
National Grid | WORCESTER | 650217 | 01604 | 17.6 | Solar | 05_01_227W3 | 11/07/2024 | 11/12/2024 | 3 | 0 | 3 | 05/01/2025 | 05/01/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | SUTTON | 683569 | 01526 | 15.2 | Solar | 05_01_406L3 | 04/08/2025 | 04/10/2025 | 2 | 0 | 2 | 04/11/2025 | 04/11/2025 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 04/08/2025 | 6/9/2026 | Y | EXP | 365 | 09/19/2025 | 10/27/2025 | 39 | 0 | 39 |  |  | 10/29/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 681154 | 01534 | 15.2 | Solar | 05_01_552L3 | 03/31/2025 | 04/01/2025 | 1 | 0 | 1 | 04/02/2025 | 04/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAMILTON | 723299 | 01982 | 15.2 | Solar | 05_01_9J360 | 10/01/2025 | 10/09/2025 | 5 | 0 | 5 | 10/10/2025 | 10/10/2025 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 | 10/01/2025 | 11/17/2026 | Y | EXP | 365 | 02/11/2026 | 02/22/2026 | 12 | 0 | 12 |  |  | 2/23/2026 | Connected |  | N
National Grid | TYNGSBORO | 730431 | 01879 | 10 | Solar | 05_05_320W5 | 11/03/2025 | 11/10/2025 | 5 | 0 | 5 | 11/12/2025 | 11/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2026 | Connected |  | N
National Grid | WESTFORD | 174655 | 01886 | 375 | Solar | 05_05_320W5 | 08/21/2012 | 08/21/2012 | 8 | 0 | 8 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2012 |  | 11/1/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | N
National Grid | BILLERICA | 671935 | 01862 | 4.537 | Solar | 05_12_51L3 | 02/13/2025 | 03/19/2025 | 5 | 0 | 5 | 03/20/2025 | 03/20/2025 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | LAWRENCE | 337901 | 01843 | 66.6 | Solar | 05_14_2L1 | 01/22/2021 | 02/03/2021 | 7 | 0 | 7 | 02/04/2021 | 02/04/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 4/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2022 | Connected |  | N
National Grid | SHIRLEY | 665155 | 01464 | 10 | Solar | 05_14_57L1 | 01/13/2025 | 02/25/2025 | 19 | 15 | 4 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | OXFORD | 304749 | 01540 | 10 | Solar | 05_14_70L5 | 08/12/2020 | 08/17/2020 | 2 | 0 | 2 | 08/18/2020 | 08/18/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/12/2020 | 5/3/2021 | Y | EXP | 365 | 12/11/2020 | 01/05/2021 | 25 | 0 | 25 |  |  | 2/11/2021 | Connected |  | N
National Grid | SPENCER | 256188 | 01562 | 24 | Solar | 05_14_8L1 | 10/20/2019 |  | 99 | 95 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 661266 | 01604 | 10 | Solar | 05_01_227W3 | 12/17/2024 | 01/14/2025 | 4 | 0 | 4 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 12/17/2024 | 4/4/2026 | Y | EXP | 365 | 06/11/2025 | 10/20/2025 | 132 | 0 | 132 |  |  | 11/20/2025 | Connected |  | N
National Grid | WHITINSVILLE | 684312 | 01588 | 15.2 | Solar | 05_01_406L3 | 04/10/2025 | 04/14/2025 | 2 | 0 | 2 | 04/15/2025 | 04/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | SUTTON | 753860 | 01526 | 13.5 | Battery Add-On | 05_01_552L3 | 03/02/2026 |  | 22 | 20 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BEVERLY | 695278 | 01915 | 640 | Solar | 05_01_HT15 | 01/29/2026 |  | 43 | 40 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | CHELMSFORD | 313859 | 01863 | 800 | Solar | 05_05_321W1 | 01/27/2021 | 02/21/2021 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2021 | 05/20/2021 | 63 | 41 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 01/27/2021 | 7/15/2026 | Y | STD | 252 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | WESTFORD | 175519 | 01886 | 1950 | Solar | 05_05_320W5 | 04/08/2014 | 04/08/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2014 | 04/28/2014 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 04/08/2014 | 12/31/2016 | Y | STD | 722 |  |  | 0 | 0 | 0 | 11/30/2016 | 11/30/2016 | 11/30/2016 | Connected |  | N
National Grid | BILLERICA | 704327 | 01862 | 15.2 | Solar | 05_12_51L3 | 07/11/2025 | 07/15/2025 | 2 | 0 | 2 | 07/16/2025 | 07/16/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 |  | 8/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | LAWRENCE | 340624 | 01843 | 9.6 | Solar | 05_14_2L1 | 02/04/2021 | 02/05/2021 | 0 | 0 | 0 | 02/08/2021 | 02/08/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  | 2/4/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 673926 | 01464 | 0 | Battery Add-On | 05_14_57L1 | 02/24/2025 | 03/17/2025 | 15 | 12 | 3 | 03/18/2025 | 03/18/2025 | 104 | 82 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 8/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | OXFORD | 339771 | 01540 | 11.4 | Solar | 05_14_70L5 | 02/01/2021 | 06/03/2021 | 85 | 80 | 5 | 06/04/2021 | 06/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2021 |  | 8/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2022 | Connected |  | Y
National Grid | BROOKFIELD | 332871 | 01515 | 7.6 | Solar | 05_14_8L1 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 678660 | 01604 | 15.2 | Solar | 05_01_227W3 | 03/17/2025 | 03/25/2025 | 6 | 2 | 4 | 03/26/2025 | 03/26/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2026 | Connected |  | N
National Grid | SUTTON | 685072 | 01590 | 23 | Solar | 05_01_406L3 | 04/15/2025 | 05/08/2025 | 16 | 12 | 4 | 05/09/2025 | 05/09/2025 | 54 | 33 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 | 04/15/2025 | 8/6/2026 | Y | EXP | 365 | 09/19/2025 | 10/07/2025 | 19 | 0 | 19 |  |  | 10/8/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 174944 | 01534 | 333 | Solar | 05_01_552L3 | 09/29/2011 | 09/29/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2012 | 09/29/2011 | 11/30/2012 | Y | STD | 109 | 07/29/2013 | 09/13/2013 | 33 | 0 | 33 | 9/11/2013 | 9/11/2013 | 9/11/2013 | Connected |  | N
National Grid | BEVERLY | 176249 | 01915 | 140 | Solar | 05_01_HT15 | 07/08/2015 | 07/08/2015 | 2 | 2 | 0 | 07/10/2015 | 07/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2015 | 07/08/2015 | 7/13/2016 | Y | EXP | 343 | 12/10/2015 | 03/17/2016 | 66 | 0 | 66 | 8/15/2016 | 8/15/2016 | 8/15/2016 | Connected |  | N
National Grid | CHELMSFORD | 634878 | 01863 | 996 | Solar | 05_05_321W1 | 12/10/2024 | 01/16/2025 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/17/2025 | 02/19/2025 | 22 | 0 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTFORD | 176067 | 01886 | 10 | Solar | 05_05_320W5 | 06/19/2015 | 06/19/2015 | 6 | 6 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2015 |  | 6/27/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 5/10/2016 | Connected |  | N
National Grid | BILLERICA | 710433 | 01821 | 18.34 | Solar | 05_12_51L3 | 08/07/2025 | 08/13/2025 | 4 | 0 | 4 | 08/14/2025 | 08/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2026 | Connected |  | N
National Grid | ANDOVER | 346687 | 01810 | 11.31 | Solar | 05_14_2L1 | 03/12/2021 | 04/22/2021 | 27 | 25 | 2 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  | 4/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2021 | Connected |  | N
National Grid | SHIRLEY | 692947 | 01464 | 15.2 | Solar | 05_14_57L1 | 05/20/2025 | 05/27/2025 | 4 | 0 | 4 | 05/28/2025 | 05/28/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | CHARLTON | 357954 | 01507 | 0 | Solar | 05_14_70L5 | 05/24/2021 | 05/25/2021 | 0 | 0 | 0 | 05/26/2021 | 05/26/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2021 |  | 5/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2021 | Connected |  | N
National Grid | SPENCER | 342617 | 01562 | 7.6 | Solar | 05_14_8L1 | 04/02/2021 | 04/15/2021 | 8 | 0 | 8 | 04/16/2021 | 04/16/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2021 | Connected |  | N
National Grid | WORCESTER | 711842 | 01610 | 20.9 | Solar | 05_01_227W3 | 08/13/2025 | 08/22/2025 | 6 | 1 | 5 | 08/25/2025 | 08/25/2025 | 90 | 60 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 384307 | 01569 | 75 | Solar | 05_01_406L4 | 10/13/2021 | 11/17/2021 | 24 | 14 | 10 |  |  | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | SUTTON | 175797 | 01590 | 990 | Solar | 05_01_552L3 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 09/22/2015 | 10/20/2015 | 19 | 0 | 19 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 | 10/20/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMILTON | 186780 | 01982 | 788 | Solar | 05_01_HT15 | 06/06/2018 | 06/06/2018 | 9 | 6 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2018 | 08/17/2018 | 46 | 31 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 |  | 12/25/2020 | N | STD | 534 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 735668 | 01886 | 3.8 | Solar | 05_05_321W1 | 11/21/2025 | 12/24/2025 | 2 | 0 | 2 | 01/27/2026 | 01/27/2026 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTFORD | 177280 | 01886 | 2800 | Solar | 05_05_320W5 | 02/08/2017 | 02/08/2017 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/14/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 721115 | 01821 | 0 | Solar | 05_12_51L3 | 09/23/2025 | 10/28/2025 | 2 | 0 | 2 | 10/29/2025 | 10/29/2025 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2026 | Connected |  | N
National Grid | LAWRENCE | 650138 | 01843 | 4.48 | Solar | 05_14_2L1 | 10/28/2024 | 11/12/2024 | 8 | 6 | 2 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 701035 | 01464 | 34.5 | Solar | 05_14_57L1 | 07/07/2025 | 07/08/2025 | 1 | 0 | 1 | 07/09/2025 | 07/09/2025 | 62 | 41 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2026 | Connected |  | N
National Grid | OXFORD | 425627 | 01540 | 9.8 | Solar | 05_14_70L5 | 05/04/2022 | 05/09/2022 | 3 | 1 | 2 | 05/10/2022 | 05/10/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 | 05/04/2022 | 1/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2023 | Connected |  | Y
National Grid | BROOKFIELD | 349605 | 01506 | 6 | Solar | 05_14_8L1 | 04/23/2021 | 01/06/2022 | 2 | 0 | 2 | 04/29/2021 | 04/29/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 727101 | 01610 | 3.8 | Solar | 05_01_227W3 | 10/17/2025 | 11/03/2025 | 10 | 5 | 5 | 11/04/2025 | 11/04/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2026 | Connected |  | N
National Grid | UXBRIDGE | 647870 | 01569 | 5.76 | Solar | 05_01_406L4 | 10/28/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/28/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WHITINSVILLE | 176145 | 01588 | 100 | Solar | 05_01_552L3 | 06/30/2015 | 06/30/2015 | 2 | 2 | 0 | 07/03/2015 | 07/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2015 |  | 7/6/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 2/18/2016 | Connected |  | N
National Grid | BEVERLY | 197318 | 01915 | 200 | Solar | 05_01_HT15 | 10/01/2018 | 10/08/2018 | 5 | 3 | 2 | 10/09/2018 | 10/09/2018 | 63 | 35 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 749744 | 01863 | 15.2 | Solar | 05_05_321W1 | 02/06/2026 | 02/10/2026 | 2 | 0 | 2 | 02/11/2026 | 02/11/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 178078 | 01886 | 3220 | Solar | 05_05_320W5 | 05/05/2017 | 05/25/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/25/2017 | 06/15/2017 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 10/8/2021 | N | STD | 449 |  |  | 0 | 0 | 0 |  |  | 12/30/2021 | Connected |  | N
National Grid | BILLERICA | 535949 | 01821 | 150 | Solar | 05_12_51T1 | 06/22/2023 | 12/07/2023 | 115 | 106 | 9 |  |  | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | LAWRENCE | 664682 | 01843 | 4.18 | Solar | 05_14_2L1 | 01/09/2025 | 01/29/2025 | 5 | 0 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | SHIRLEY | 723177 | 01464 | 17.6 | Solar | 05_14_57L1 | 10/01/2025 | 10/13/2025 | 7 | 3 | 4 | 10/14/2025 | 10/14/2025 | 72 | 61 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 590690 | 01540 | 10 | Solar | 05_14_70L5 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 396873 | 01515 | 7.6 | Solar | 05_14_8L1 | 12/08/2021 | 01/06/2022 | 5 | 4 | 1 | 12/15/2021 | 12/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 734559 | 01610 | 0 | Battery Add-On | 05_01_227W3 | 11/18/2025 | 11/20/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2026 | Connected |  | N
National Grid | UXBRIDGE | 713750 | 01569 | 17.6 | Solar | 05_01_406L4 | 08/27/2025 | 09/04/2025 | 5 | 0 | 5 | 09/05/2025 | 09/05/2025 | 79 | 66 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 | 08/27/2025 | 1/16/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SUTTON | 176143 | 01590 | 76 | Solar | 05_01_552L3 | 06/29/2015 | 06/29/2015 | 1 | 1 | 0 | 07/02/2015 | 07/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2015 | 06/29/2015 | 7/6/2016 | Y | EXP | 350 | 11/12/2015 | 11/30/2015 | 11 | 0 | 11 | 7/22/2015 | 7/22/2015 | 1/15/2016 | Connected |  | N
National Grid | HAMILTON | 438934 | 01982 | 150 | Solar | 05_01_HT17 | 06/27/2022 | 07/11/2022 | 9 | 0 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 177834 | 01863 | 3000 | Solar | 05_05_321W1 | 08/09/2017 | 08/09/2017 | 12 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2017 | 09/20/2017 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2018 |  | 7/1/2019 | N | STD | 459 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 178674 | 01886 | 1000 | Solar | 05_05_320W5 | 04/10/2018 | 04/16/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/18/2018 | 08/14/2018 | 61 | 43 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2019 | 04/10/2018 | 12/16/2020 | Y | STD | 375 | 01/29/2020 | 10/26/2020 | 272 | 5 | 267 | 11/10/2020 | 11/10/2020 | 12/4/2020 | Connected |  | N
National Grid | BILLERICA | 703493 | 01821 | 11.4 | Solar | 05_12_51T1 | 07/08/2025 | 07/11/2025 | 3 | 0 | 3 | 07/14/2025 | 07/14/2025 | 34 | 18 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 686313 | 01843 | 15.04 | Solar | 05_14_2L1 | 05/11/2025 | 07/10/2025 | 39 | 38 | 1 | 07/11/2025 | 07/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 | 05/11/2025 | 9/2/2026 | Y | EXP | 365 | 12/04/2025 | 02/13/2026 | 72 | 0 | 72 |  |  | 2/17/2026 | Connected |  | N
National Grid | SHIRLEY | 726835 | 01464 | 17.48 | Solar | 05_14_57L1 | 10/15/2025 | 10/20/2025 | 3 | 0 | 3 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 633944 | 01540 | 5.76 | Solar | 05_14_70L5 | 08/20/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 | 08/20/2024 | 10/10/2025 | Y | EXP | 365 | 11/28/2024 | 12/26/2024 | 29 | 0 | 29 |  |  | 1/6/2025 | Connected |  | N
National Grid | BROOKFIELD | 426466 | 01515 | 7.6 | Solar | 05_14_8L1 | 06/01/2022 | 06/07/2022 | 4 | 0 | 4 | 06/08/2022 | 06/08/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177934 | 01610 | 15.2 | Solar | 05_01_23W1 | 06/19/2017 | 06/19/2017 | 27 | 27 | 0 | 07/28/2017 | 07/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2017 |  | 6/25/2018 | N | EXP | 329 |  |  | 0 | 0 | 0 | 1/25/2018 | 1/25/2018 | 1/25/2018 | Connected |  | N
National Grid | UXBRIDGE | 738891 | 01569 | 10 | Solar | 05_01_406L4 | 12/09/2025 | 12/10/2025 | 1 | 0 | 1 | 12/11/2025 | 12/11/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 | 12/09/2025 | 1/27/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTHBRIDGE | 176690 | 01534 | 496 | Solar | 05_01_552L3 | 02/19/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/16/2016 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2016 | 02/19/2016 | 12/28/2018 | Y | STD | 821 | 12/19/2018 | 12/18/2018 | 0 | 0 | 0 |  |  | 12/13/2018 | Connected |  | N
National Grid | BEVERLY | 320344 | 01915 | 75 | Natural Gas | 05_01_HT20 | 11/20/2020 | 12/07/2020 | 9 | 0 | 9 |  |  | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 |  | 4/27/2023 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | CHELMSFORD | 177833 | 01863 | 1980 | Solar | 05_05_321W1 | 08/09/2017 | 08/09/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2017 | 09/20/2017 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2018 |  | 7/1/2019 | N | STD | 459 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 178805 | 01886 | 0 | Solar | 05_05_320W5 | 12/17/2011 | 12/17/2011 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 710223 | 01821 | 240 | Solar | 05_12_51T1 | 08/26/2025 | 10/13/2025 | 31 | 27 | 4 |  |  | 89 | 75 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | LAWRENCE | 709518 | 01843 | 11.4 | Solar | 05_14_2L2 | 08/05/2025 | 09/24/2025 | 34 | 24 | 10 | 09/25/2025 | 09/25/2025 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SHIRLEY | 683366 | 01464 | 4998 | Other | 05_14_57L2 | 10/16/2025 | 12/04/2025 | 31 | 23 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2025 | 12/30/2025 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | AUBURN | 643883 | 01501 | 5.76 | Solar | 05_14_70L5 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 431131 | 01515 | 6 | Solar | 05_14_8L1 | 05/26/2022 | 05/31/2022 | 2 | 0 | 2 | 06/01/2022 | 06/01/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2022 |  | 7/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178256 | 01610 | 900 | Solar | 05_01_23W1 | 04/16/2018 | 04/16/2018 | 15 | 15 | 0 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2019 | 04/16/2018 | 8/16/2023 | Y | STD | 1180 | 01/13/2021 | 08/03/2023 | 933 | 7 | 926 | 7/21/2023 | 8/3/2023 | 8/14/2023 | Connected |  | N
National Grid | DOUGLAS | 749907 | 01516 | 11.5 | Solar | 05_01_406L4 | 02/06/2026 | 02/25/2026 | 3 | 0 | 3 | 03/10/2026 | 03/10/2026 | 17 | 5 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SUTTON | 176719 | 01590 | 496 | Solar | 05_01_552L3 | 02/19/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/16/2016 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2016 | 02/19/2016 | 12/28/2018 | Y | STD | 821 | 12/19/2018 | 12/18/2018 | 0 | 0 | 0 |  |  | 12/24/2018 | Connected |  | N
National Grid | GLOUCESTER | 174554 | 01930 | 1333 | Solar | 05_01_HT22 | 10/11/2011 | 10/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 178494 | 01863 | 0 | Solar | 05_05_321W1 | 12/01/2017 | 12/01/2017 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2018 | 03/26/2018 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/9/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 184565 | 01886 | 264 | Solar | 05_05_320W5 | 07/17/2018 | 08/28/2018 | 6 | 0 | 6 |  |  | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2019 |  | 8/3/2020 | N | STD | 479 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 720734 | 01821 | 12.564 | Solar | 05_12_51T1 | 09/22/2025 | 10/24/2025 | 13 | 12 | 1 | 12/02/2025 | 12/02/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 | 09/22/2025 | 12/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LAWRENCE | 740214 | 01843 | 100 | Solar | 05_14_2L2 | 02/13/2026 |  | 32 | 22 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WORCESTER | 750891 | 01602 | 15.2 | Solar | 05_14_57L2 | 02/12/2026 | 02/17/2026 | 2 | 0 | 2 | 02/18/2026 | 02/18/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2026 |  | 3/16/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | OXFORD | 647631 | 01540 | 7.6 | Solar | 05_14_70L5 | 10/21/2024 |  | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 507185 | 01506 | 0 | Solar | 05_14_8L1 | 05/02/2023 | 06/12/2023 | 28 | 25 | 3 | 06/13/2023 | 06/13/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 | 05/02/2023 | 8/11/2025 | Y | EXP | 730 | 04/30/2024 | 05/29/2024 | 30 | 0 | 30 |  |  | 10/1/2024 | Connected |  | N
National Grid | WORCESTER | 385653 | 01609 | 3.8 | Solar | 05_01_23W1 | 11/09/2021 | 01/07/2022 | 1 | 0 | 1 | 11/12/2021 | 11/12/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/09/2021 | 5/7/2023 | Y | EXP | 485 | 04/13/2022 | 04/12/2022 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 755390 | 01516 | 20 | Solar | 05_01_406L4 | 03/11/2026 | 03/16/2026 | 2 | 0 | 2 | 03/17/2026 | 03/17/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SUTTON | 177414 | 01590 | 20.2 | Solar | 05_01_552L3 | 09/12/2016 | 09/12/2016 | 10 | 10 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2016 | 09/12/2016 | 9/18/2017 | Y | EXP | 354 | 12/28/2016 | 01/05/2017 | 5 | 0 | 5 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N
National Grid | GLOUCESTER | 178047 | 01930 | 800 | Solar | 05_01_HT22 | 05/05/2017 | 05/30/2017 | 15 | 13 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2017 | 06/15/2017 | 12 | 0 | 12 |  | 0 | 0 | 0 | 01/18/2018 | 04/06/2020 | 556 | 0 | 556 | 2/15/2018 | 05/05/2017 | 6/17/2021 | Y | STD | 450 | 10/16/2020 | 04/21/2021 | 187 | 0 | 187 |  |  | 6/2/2021 | Connected |  | N
National Grid | LOWELL | 193087 | 01851 | 4280 | Solar | 05_05_321W1 | 08/29/2018 | 09/19/2018 | 13 | 13 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2018 | 10/19/2018 | 21 | 4 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 190183 | 01886 | 250 | Solar | 05_05_320W5 | 07/10/2018 | 07/20/2018 | 1 | 0 | 1 | 07/23/2018 | 07/23/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  | 7/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2019 | Connected |  | N
National Grid | BILLERICA | 736911 | 01821 |  | Battery Add-On | 05_12_51T1 | 11/28/2025 | 12/01/2025 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 3/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 752200 | 01843 | 16.34 | Solar | 05_14_2L2 | 02/19/2026 | 02/27/2026 | 5 | 2 | 3 | 03/02/2026 | 03/02/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 178144 | 01603 | 0 | Solar | 05_14_57L2 | 04/12/2018 | 04/12/2018 | 10 | 0 | 10 | 05/01/2018 | 05/01/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2019 |  | 10/22/2020 | N | EXP | 36 |  |  | 0 | 0 | 0 |  |  | 2/18/2020 | Connected |  | N
National Grid | AUBURN | 519443 | 01501 | 11.375 | Solar | 05_14_8L1 | 09/14/2023 | 09/29/2023 | 11 | 10 | 1 | 10/02/2023 | 10/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 425866 | 01506 | 9.074 | Solar | 05_01_23W1 | 05/05/2022 | 05/09/2022 | 2 | 0 | 2 | 05/10/2022 | 05/10/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  | 6/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2023 | Connected |  | N
National Grid | WORCESTER | 173764 | 01603 | 10 | Solar | 05_01_406L4 | 04/17/2018 | 04/17/2018 | 0 | 0 | 0 | 07/10/2018 | 07/10/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBRIDGE | 177614 | 01534 | 1000 | Solar | 05_01_552L3 | 09/22/2017 | 10/09/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2017 | 10/31/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 | 09/22/2017 | 12/21/2020 | Y | STD | 644 | 05/20/2020 | 09/11/2020 | 115 | 5 | 110 |  |  | 12/14/2020 | Connected |  | N
National Grid | SUTTON | 174342 | 01590 | 7500 | Natural Gas | 05_01_HT25 | 11/08/2010 | 11/08/2010 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 11/08/2010 | 10/31/2012 | Y | STD | 42 | 11/10/2011 | 03/05/2012 | 75 | 0 | 75 | 1/24/2013 | 1/24/2013 | 5/7/2013 | Connected |  | N
National Grid | BEVERLY | 247851 | 01915 | 4966.6 | Solar | 05_05_321W1 | 11/08/2019 | 11/22/2019 | 9 | 6 | 3 |  |  | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 | 11/08/2019 | 1/3/2024 | Y | STD | 392 | 02/09/2023 | 07/18/2023 | 160 | 0 | 160 |  |  | 12/18/2023 | Connected |  | N
National Grid | CHELMSFORD | 193521 | 01863 | 2000 | Solar | 05_05_320W5 | 08/14/2018 | 08/27/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2018 | 10/31/2018 | 46 | 27 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2020 | 08/14/2018 | 4/27/2025 | Y | STD | 280 | 07/12/2023 | 01/07/2025 | 547 | 365 | 182 |  |  | 4/18/2025 | Connected |  | N
National Grid | WESTFORD | 737553 | 01886 | 5.76 | Solar | 05_12_51T1 | 12/02/2025 | 12/03/2025 | 3 | 0 | 3 | 01/13/2026 | 01/13/2026 | 20 | 6 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 753539 | 01862 | 17.45 | Solar | 05_14_2L2 | 03/03/2026 |  | 21 | 19 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 178697 | 01843 | 7.6 | Solar | 05_14_57L2 | 02/06/2018 | 02/06/2018 | 16 | 0 | 16 | 02/20/2018 | 02/20/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2018 |  | 2/12/2019 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  | 10/1/2019 | Connected |  | N
National Grid | WORCESTER | 648641 | 01609 | 10 | Solar | 05_14_70L5 | 10/21/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/21/2024 | 12/30/2025 | Y | EXP | 365 | 04/12/2025 | 04/22/2025 | 11 | 0 | 11 |  |  | 4/29/2025 | Connected |  | N
National Grid | OXFORD | 537292 | 01540 | 0 | Solar | 05_14_8L1 | 06/28/2023 | 10/19/2023 | 77 | 77 | 0 | 10/20/2023 | 10/20/2023 | 71 | 27 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 445969 | 01515 | 7.6 | Solar | 05_01_23W1 | 07/21/2022 | 07/22/2022 | 1 | 0 | 1 | 07/25/2022 | 07/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2022 |  | 8/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | N
National Grid | WORCESTER | 174250 | 01610 | 95 | Solar | 05_01_406L4 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2012 |  | 6/1/2012 | N | EXP | 11 |  |  | 0 | 0 | 0 | 6/18/2012 | 6/18/2012 | 6/29/2012 | Connected |  | N
National Grid | UXBRIDGE | 177893 | 01569 | 2490 | Solar | 05_01_552L3 | 04/13/2017 | 04/21/2017 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/21/2017 | 05/24/2017 | 23 | 11 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2018 |  | 7/9/2020 | N | STD | 685 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 175683 | 01590 | 75.6 | Solar | 05_01_HT26 | 12/24/2014 | 12/24/2014 | 4 | 1 | 3 | 01/02/2015 | 01/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 | 12/24/2014 | 5/31/2015 | Y | EXP | 116 |  |  | 0 | 0 | 0 | 2/4/2015 | 2/4/2015 | 10/28/2015 | Connected |  | N
National Grid | GLOUCESTER | 452462 | 01930 | 15.2 | Solar | 05_05_321W1 | 09/02/2022 | 09/13/2022 | 7 | 5 | 2 | 09/14/2022 | 09/14/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 1/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | Y
National Grid | CHELMSFORD | 208111 | 01863 | 3.8 | Solar | 05_05_320W5 | 02/25/2019 | 03/06/2019 | 6 | 0 | 6 | 03/07/2019 | 03/07/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 750023 | 01886 | 10 | Solar | 05_12_51T1 | 02/09/2026 | 02/11/2026 | 2 | 0 | 2 | 02/12/2026 | 02/12/2026 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BILLERICA | 178453 | 01862 | 7.6 | Solar | 05_14_2L2 | 11/29/2017 | 11/29/2017 | 38 | 36 | 2 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 | 11/29/2017 | 9/19/2019 | Y | EXP | 597 | 06/06/2018 | 06/20/2018 | 14 | 0 | 14 |  |  | 9/5/2019 | Connected |  | N
National Grid | LAWRENCE | 273553 | 01843 | 7.6 | Solar | 05_14_57L2 | 01/23/2020 | 02/05/2020 | 8 | 3 | 5 | 02/06/2020 | 02/06/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 | 01/23/2020 | 7/15/2021 | Y | EXP | 365 | 04/06/2021 | 04/15/2021 | 9 | 0 | 9 |  |  | 4/30/2021 | Connected |  | N
National Grid | WORCESTER | 648920 | 01602 | 5.76 | Solar | 05_14_70L5 | 11/05/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 | 11/05/2024 | 1/2/2026 | Y | EXP | 365 | 02/12/2025 | 03/06/2025 | 22 | 0 | 22 |  |  | 3/26/2025 | Connected |  | N
National Grid | OXFORD | 566189 | 01540 | 5 | Solar | 05_14_8L1 | 11/01/2023 | 11/06/2023 | 3 | 0 | 3 | 11/07/2023 | 11/07/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 | 11/01/2023 | 3/13/2025 | Y | EXP | 365 | 05/15/2024 | 05/31/2024 | 17 | 0 | 17 |  |  | 6/6/2024 | Connected |  | N
National Grid | BROOKFIELD | 502980 | 01515 | 15.2 | Solar | 05_01_23W1 | 02/21/2023 | 02/22/2023 | 1 | 0 | 1 | 02/23/2023 | 02/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  | 4/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | WORCESTER | 174261 | 01604 | 94.25 | Solar | 05_01_406L4 | 02/29/2012 | 02/29/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2012 |  | 6/1/2012 | N | EXP | 122 |  |  | 0 | 0 | 0 | 10/19/2012 | 10/19/2012 | 11/26/2012 | Connected |  | N
National Grid | UXBRIDGE | 177892 | 01569 | 4200 | Solar | 05_01_552L3 | 04/13/2017 | 04/21/2017 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/21/2017 | 05/24/2017 | 23 | 11 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2018 | 04/13/2017 | 6/7/2021 | Y | STD | 685 | 09/23/2020 | 04/14/2021 | 203 | 0 | 203 |  |  | 6/4/2021 | Connected |  | N
National Grid | DOUGLAS | 535525 | 01516 | 990 | Solar | 05_01_HT26 | 11/21/2023 |  | 117 | 109 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 408286 | 01930 | 15.2 | Solar | 05_05_321W1 | 01/24/2022 | 01/26/2022 | 3 | 2 | 1 | 01/27/2022 | 01/27/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 |  | 3/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2022 | Connected |  | N
National Grid | LOWELL | 266587 | 01851 | 15.2 | Solar | 05_05_320W5 | 11/21/2019 | 11/22/2019 | 0 | 0 | 0 | 11/25/2019 | 11/25/2019 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2020 | 11/21/2019 | 11/21/2020 | Y | EXP | 365 | 04/01/2020 | 04/07/2020 | 6 | 0 | 6 |  |  | 7/17/2020 | Connected |  | N
National Grid | WESTFORD | 162552 | 01886 | 10 | Solar | 05_12_51T1 | 10/12/2017 | 10/12/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/12/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 178471 | 01862 | 7.6 | Solar | 05_14_2L2 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 3/12/2019 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 277368 | 01843 | 9.84 | Solar | 05_14_57L2 | 02/03/2020 | 02/05/2020 | 1 | 0 | 1 | 02/06/2020 | 02/06/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2020 | 02/03/2020 | 2/3/2021 | Y | EXP | 365 | 07/11/2020 | 07/27/2020 | 16 | 0 | 16 |  |  | 8/18/2020 | Connected |  | N
National Grid | WORCESTER | 652490 | 01609 | 7.6 | Solar | 05_14_70L5 | 11/14/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 6/11/2026 | Y | EXP | 365 | 04/01/2025 | 04/23/2025 | 23 | 0 | 23 |  |  | 8/29/2025 | Connected |  | N
National Grid | OXFORD | 581109 | 01537 | 0 | Battery Add-On | 05_14_8L1 | 01/03/2024 | 01/05/2024 | 2 | 0 | 2 | 01/08/2024 | 01/08/2024 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 553654 | 01535 | 3.8 | Solar | 05_01_23W1 | 09/19/2023 | 09/20/2023 | 1 | 0 | 1 | 09/21/2023 | 09/21/2023 | 108 | 28 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 174329 | 01604 | 1750 | Solar | 05_01_406L4 | 12/20/2011 | 12/20/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2012 | 12/20/2011 | 9/1/2012 | Y | STD | 88 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 177945 | 01569 | 42.3 | Solar | 05_01_552L3 | 08/21/2017 | 08/21/2017 | 57 | 49 | 8 | 11/20/2017 | 11/20/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2017 |  | 8/26/2018 | N | EXP | 279 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | WHITINSVILLE | 613305 | 01588 | 870 | Solar | 05_01_HT26 | 06/17/2024 | 07/24/2024 | 25 | 17 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/25/2024 | 09/23/2024 | 37 | 25 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 474060 | 01915 | 5100 | Solar | 05_05_321W1 | 06/02/2023 | 09/14/2023 | 71 | 61 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/15/2023 | 10/09/2023 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176883 | 01851 | 10 | Solar | 05_05_344W4 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2016 |  | 5/10/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 | 9/8/2016 | 9/8/2016 | 9/14/2016 | Connected |  | N
National Grid | WESTFORD | 174679 | 01886 | 45 | Solar | 05_12_51T1 | 01/06/2014 | 01/06/2014 | 5 | 0 | 5 | 01/14/2014 | 01/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2014 |  | 3/31/2014 | N | EXP | 69 |  |  | 0 | 0 | 0 | 2/21/2014 | 2/21/2014 | 4/25/2014 | Connected |  | N
National Grid | BILLERICA | 184905 | 01821 | 7.6 | Solar | 05_14_2L2 | 06/11/2018 | 06/11/2018 | 1 | 0 | 1 | 06/13/2018 | 06/13/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2018 |  | 6/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 301130 | 01810 | 10 | Solar | 05_14_57L2 | 08/17/2020 | 08/26/2020 | 7 | 7 | 0 | 08/27/2020 | 08/27/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 | 08/17/2020 | 8/26/2021 | Y | EXP | 365 | 04/21/2021 | 04/30/2021 | 9 | 0 | 9 |  |  | 5/4/2021 | Connected |  | N
National Grid | WORCESTER | 660576 | 01609 | 4.55 | Solar | 05_14_70L5 | 12/13/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | OXFORD | 584528 | 01540 | 11.4 | Solar | 05_14_8L1 | 02/01/2024 | 02/12/2024 | 8 | 6 | 2 | 02/13/2024 | 02/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 622231 | 01535 | 7.6 | Solar | 05_01_23W1 | 07/02/2024 | 07/12/2024 | 4 | 0 | 4 | 07/15/2024 | 07/15/2024 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 07/02/2024 | 12/31/2025 | Y | EXP | 365 | 05/10/2025 | 11/21/2025 | 196 | 0 | 196 |  |  | 12/22/2025 | Connected |  | N
National Grid | WORCESTER | 174328 | 01610 | 2750 | Solar | 05_01_406L4 | 12/20/2011 | 12/20/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2012 | 12/20/2011 | 6/21/2014 | Y | STD | 570 | 03/10/2014 | 05/15/2014 | 46 | 0 | 46 | 6/24/2014 | 6/24/2014 | 7/2/2014 | Connected |  | N
National Grid | UXBRIDGE | 178060 | 01569 | 4980 | Solar | 05_01_552L3 | 09/01/2017 | 09/21/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2017 | 11/03/2017 | 31 | 0 | 31 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 | 09/01/2017 | 7/6/2021 | Y | STD | 708 | 04/02/2020 | 09/11/2020 | 163 | 5 | 158 |  |  | 7/6/2021 | Connected |  | N
National Grid | SUTTON | 192164 | 01590 | 249.8 | Solar | 05_01_HT27 | 08/06/2018 | 09/04/2018 | 18 | 0 | 18 | 09/05/2018 | 09/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ESSEX | 474054 | 01929 | 5100 | Solar | 05_05_321W1 | 06/02/2023 | 09/13/2023 | 70 | 60 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2023 | 10/09/2023 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 177422 | 01863 | 7.6 | Solar | 05_05_344W4 | 12/05/2016 | 12/05/2016 | 2 | 2 | 0 | 12/08/2016 | 12/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2016 |  | 12/11/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 7/5/2017 | 7/5/2017 | 7/5/2017 | Connected |  | N
National Grid | WESTFORD | 175028 | 01886 | 800 | Solar | 05_12_51T1 | 03/20/2013 | 03/20/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2013 | 05/15/2013 | 32 | 0 | 32 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2013 |  | 6/30/2014 | N | STD | 411 |  |  | 0 | 0 | 0 | 12/27/2013 | 12/27/2013 | 12/30/2013 | Connected |  | N
National Grid | BILLERICA | 191228 | 01821 | 3 | Solar | 05_14_2L2 | 07/19/2018 | 09/13/2018 | 31 | 25 | 6 | 09/14/2018 | 09/14/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2018 | 07/19/2018 | 10/8/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | ANDOVER | 307057 | 01810 | 15.2 | Solar | 05_14_57L2 | 08/17/2020 | 08/20/2020 | 2 | 0 | 2 | 08/21/2020 | 08/21/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2020 | Connected |  | N
National Grid | WORCESTER | 666064 | 01602 | 6 | Solar | 05_14_70L5 | 01/15/2025 | 02/04/2025 | 5 | 1 | 4 | 02/05/2025 | 02/05/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2025 | 01/15/2025 | 3/20/2026 | Y | EXP | 365 | 04/12/2025 | 07/07/2025 | 87 | 0 | 87 |  |  | 7/15/2025 | Connected |  | N
National Grid | OXFORD | 593454 | 01540 | 6 | Solar | 05_14_8L1 | 03/25/2024 | 03/27/2024 | 2 | 0 | 2 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 03/25/2024 | 5/6/2025 | Y | EXP | 365 | 07/31/2024 | 09/19/2024 | 51 | 0 | 51 |  |  | 10/31/2024 | Connected |  | N
National Grid | SPENCER | 629723 | 01562 | 3.8 | Solar | 05_01_23W1 | 08/02/2024 | 09/18/2024 | 28 | 25 | 3 | 09/19/2024 | 09/19/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 10/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2024 | Connected |  | N
National Grid | WORCESTER | 175286 | 01610 | 19.78 | Solar | 05_01_406L4 | 11/06/2014 | 11/06/2014 | 5 | 3 | 2 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 1/30/2015 | N | EXP | 71 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 | 4/27/2016 | Connected |  | N
National Grid | UXBRIDGE | 717385 | 01516 | 7.6 | Solar | 05_07_15J1 | 09/18/2025 | 09/25/2025 | 2 | 0 | 2 | 10/23/2025 | 10/23/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 09/18/2025 | 12/5/2026 | Y | EXP | 365 | 01/21/2026 | 02/20/2026 | 31 | 0 | 31 |  |  |  | Completion Documents |  | N
National Grid | BELLINGHAM | 438978 | 02019 | 100 | Solar | 05_01_HT27 | 06/27/2022 | 07/11/2022 | 9 | 0 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 657082 | 01915 | 10 | Solar | 05_05_321W1 | 11/26/2024 | 12/02/2024 | 2 | 0 | 2 | 12/03/2024 | 12/03/2024 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | LOWELL | 177567 | 01851 | 7.6 | Solar | 05_05_344W4 | 09/14/2017 | 09/14/2017 | 9 | 9 | 0 | 09/27/2017 | 09/27/2017 | 124 | 0 | 124 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/19/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 175161 | 01886 | 75 | Solar | 05_12_51T1 | 07/21/2011 | 07/21/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 197063 | 01821 | 7.68 | Solar | 05_14_2L2 | 10/03/2018 | 10/11/2018 | 3 | 3 | 0 | 10/12/2018 | 10/12/2018 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 10/03/2018 | 5/29/2019 | Y | EXP | 225 | 02/01/2019 | 01/31/2019 | 0 | 0 | 0 |  |  | 4/16/2019 | Connected |  | N
National Grid | ANDOVER | 312114 | 01810 | 13.6 | Solar | 05_14_57L2 | 09/17/2020 | 09/24/2020 | 4 | 0 | 4 | 09/25/2020 | 09/25/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2021 | Connected |  | Y
National Grid | WORCESTER | 671256 | 01602 | 3.8 | Solar | 05_14_70L5 | 02/11/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 607693 | 01540 | 0 | Solar | 05_14_8L1 | 04/30/2024 | 06/11/2024 | 29 | 28 | 1 | 06/12/2024 | 06/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 690729 | 01515 | 7.6 | Solar | 05_01_23W1 | 05/09/2025 | 05/28/2025 | 2 | 0 | 2 | 06/23/2025 | 06/23/2025 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175331 | 01603 | 3000 | Solar | 05_01_406L4 | 11/11/2014 | 11/11/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/01/2014 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 11/11/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 353056 | 01569 | 0 | Solar | 05_07_15J1 | 04/16/2021 | 04/22/2021 | 2 | 0 | 2 | 04/23/2021 | 04/23/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 5/16/2023 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  | 4/5/2023 | Connected |  | N
National Grid | BELLINGHAM | 617208 | 02019 | 250 | Solar | 05_01_HT28 | 09/23/2024 | 11/21/2024 | 42 | 32 | 10 |  |  | 86 | 61 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BEVERLY | 660886 | 01915 | 6.825 | Solar | 05_05_321W1 | 12/16/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | LOWELL | 177816 | 01851 | 7.6 | Solar | 05_05_344W4 | 04/04/2017 | 04/04/2017 | 5 | 1 | 4 | 04/11/2017 | 04/11/2017 | 241 | 0 | 241 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2017 |  | 4/9/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 175487 | 01886 | 495 | Solar | 05_12_51T1 | 07/22/2014 | 07/22/2014 | 7 | 7 | 0 | 08/04/2014 | 08/04/2014 | 554 | 2 | 552 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2014 |  | 1/20/2016 | N | EXP | 510 |  |  | 0 | 0 | 0 | 9/15/2014 | 9/15/2014 |  | Withdrawn |  | Y
National Grid | BILLERICA | 198842 | 01862 | 3.8 | Solar | 05_14_2L2 | 12/06/2018 | 12/19/2018 | 8 | 0 | 8 | 12/20/2018 | 12/20/2018 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 321224 | 01843 | 10 | Solar | 05_14_57L2 | 10/23/2020 | 10/27/2020 | 1 | 0 | 1 | 10/28/2020 | 10/28/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 10/27/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175994 | 01609 | 16.35 | Solar | 05_14_70L6 | 06/10/2015 | 06/10/2015 | 6 | 6 | 0 | 06/22/2015 | 06/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/16/2016 | N | EXP | 351 |  |  | 0 | 0 | 0 | 10/6/2016 | 10/6/2016 | 10/6/2016 | Connected |  | N
National Grid | OXFORD | 613634 | 01540 | 23 | Battery Add-On | 05_14_8L1 | 05/28/2024 | 06/03/2024 | 5 | 3 | 2 | 06/04/2024 | 06/04/2024 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 7/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | SCITUATE | 707291 | 02066 | 10 | Solar | 05_01_23W1 | 07/24/2025 | 08/19/2025 | 3 | 0 | 3 | 08/25/2025 | 08/25/2025 | 63 | 50 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175395 | 01610 | 10 | Solar | 05_01_406L4 | 09/16/2014 | 09/16/2014 | 7 | 0 | 7 | 09/26/2014 | 09/26/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2014 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 384763 | 01569 | 15.2 | Solar | 05_07_15J1 | 09/27/2021 |  | 58 | 49 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 196401 | 02019 | 66.6 | Solar | 05_01_HT28 | 09/19/2018 | 08/01/2019 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 28 | 12 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2018 |  | 6/30/2020 | N | EXP | 582 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 673801 | 01930 | 0 | Battery Add-On | 05_05_321W1 | 02/24/2025 | 02/25/2025 | 1 | 0 | 1 | 02/26/2025 | 02/26/2025 | 61 | 41 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 178016 | 01851 | 15.2 | Solar | 05_05_344W4 | 06/29/2017 | 06/29/2017 | 4 | 3 | 1 | 07/06/2017 | 07/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 | 06/29/2017 | 7/4/2018 | Y | EXP | 362 | 12/26/2017 | 12/20/2017 | 0 | 0 | 0 | 1/16/2018 | 1/16/2018 | 1/22/2018 | Connected |  | N
National Grid | WESTFORD | 175656 | 01886 | 17.6 | Solar | 05_12_51T1 | 05/13/2014 | 05/13/2014 | 6 | 0 | 6 | 05/22/2014 | 05/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2014 |  | 9/30/2014 | N | EXP | 99 |  |  | 0 | 0 | 0 | 7/22/2014 | 7/22/2014 | 9/2/2014 | Connected |  | N
National Grid | BILLERICA | 250967 | 01821 | 7.6 | Solar | 05_14_2L2 | 08/27/2019 | 08/28/2019 | 1 | 1 | 0 | 08/29/2019 | 08/29/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/27/2019 | 8/28/2020 | Y | EXP | 233 | 01/09/2020 | 03/12/2020 | 62 | 0 | 62 |  |  | 3/24/2020 | Connected |  | N
National Grid | LAWRENCE | 326885 | 01843 | 10 | Solar | 05_14_57L2 | 11/18/2020 | 11/23/2020 | 2 | 0 | 2 | 11/24/2020 | 11/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2021 | Connected |  | N
National Grid | WORCESTER | 176246 | 01609 | 17.2 | Solar | 05_14_70L6 | 04/30/2015 | 04/30/2015 | 5 | 5 | 0 | 05/13/2015 | 05/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 |  | 10/30/2015 | N | EXP | 169 |  |  | 0 | 0 | 0 | 12/10/2015 | 12/10/2015 | 12/10/2015 | Connected |  | N
National Grid | OXFORD | 615299 | 01540 | 10 | Solar | 05_14_8L1 | 06/04/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 06/04/2024 | 8/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | SCITUATE | 725080 | 02066 | 7.6 | Solar | 05_01_23W1 | 10/08/2025 | 10/20/2025 | 3 | 0 | 3 | 12/18/2025 | 12/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2026 | Connected |  | N
National Grid | WORCESTER | 175686 | 01604 | 17 | Solar | 05_01_406L4 | 12/23/2014 | 12/23/2014 | 8 | 5 | 3 | 01/07/2015 | 01/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2015 |  | 4/30/2015 | N | EXP | 90 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 11/12/2015 | Connected |  | N
National Grid | UXBRIDGE | 411314 | 01569 | 15.2 | Solar | 05_07_15J1 | 02/09/2022 | 02/10/2022 | 1 | 0 | 1 | 02/11/2022 | 02/11/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2022 |  | 3/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2022 | Connected |  | N
National Grid | BELLINGHAM | 177112 | 02019 | 4400 | Natural Gas | 05_01_HT31 | 08/08/2016 | 08/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2016 |  | 8/30/2018 | N | STD | 702 | 05/28/2018 | 05/27/2018 | 0 | 0 | 0 |  |  | 2/4/2019 | Connected |  | N
National Grid | MANCHESTER | 175913 | 01944 | 500 | Natural Gas | 05_05_321W10 | 03/11/2015 | 03/11/2015 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2015 | 04/15/2015 | 20 | 1 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2017 | 03/11/2015 | 6/1/2018 | Y | STD | 441 | 07/12/2017 | 07/28/2017 | 12 | 0 | 12 | 1/26/2018 | 1/26/2018 | 4/27/2018 | Connected |  | N
National Grid | CHELMSFORD | 178065 | 01863 | 15.2 | Solar | 05_05_344W4 | 09/05/2017 | 09/05/2017 | 10 | 9 | 1 | 09/19/2017 | 09/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2017 |  | 9/10/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 | 11/13/2017 | 11/13/2017 | 11/28/2017 | Connected |  | N
National Grid | WESTFORD | 175911 | 01886 | 20 | Solar | 05_12_51T1 | 03/11/2015 | 03/11/2015 | 11 | 8 | 3 | 03/30/2015 | 03/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2015 |  | 7/31/2015 | N | EXP | 122 |  |  | 0 | 0 | 0 | 4/27/2015 | 4/27/2015 | 7/10/2015 | Connected |  | N
National Grid | BILLERICA | 324108 | 01821 | 10 | Solar | 05_14_2L2 | 11/09/2020 | 12/07/2020 | 17 | 14 | 3 | 12/08/2020 | 12/08/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2021 |  | 1/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2021 | Connected |  | N
National Grid | ANDOVER | 332968 | 01810 | 0 | Solar | 05_14_57L2 | 12/18/2020 | 01/04/2021 | 9 | 8 | 1 | 01/05/2021 | 01/05/2021 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/18/2020 | 1/3/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2021 | Connected |  | N
National Grid | WORCESTER | 177836 | 01602 | 15.2 | Solar | 05_14_70L6 | 08/09/2017 | 08/09/2017 | 5 | 5 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/14/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 3/14/2018 | 3/14/2018 | 3/16/2018 | Connected |  | N
National Grid | OXFORD | 616792 | 01540 | 10 | Solar | 05_14_8L1 | 06/11/2024 | 06/25/2024 | 4 | 0 | 4 | 06/26/2024 | 06/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 8/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 739766 | 02066 | 7.6 | Solar | 05_01_23W2 | 12/11/2025 | 12/12/2025 | 2 | 0 | 2 | 01/27/2026 | 01/27/2026 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2026 |  | 3/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 175721 | 01604 | 100 | Solar | 05_01_406L4 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 1/3/2015 | N | EXP | 89 |  |  | 0 | 0 | 0 | 12/26/2014 | 12/26/2014 | 1/20/2015 | Connected |  | N
National Grid | UXBRIDGE | 637597 | 01569 | 8.74 | Solar | 05_07_15J1 | 09/09/2024 | 09/25/2024 | 1 | 0 | 1 | 09/26/2024 | 09/26/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 514546 | 02019 | 0 | Natural Gas | 05_01_HT41 | 05/26/2023 | 06/28/2023 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2023 | 07/21/2023 | 16 | 0 | 16 |  | 0 | 0 | 0 | 04/09/2024 | 02/21/2025 | 216 | 0 | 216 | 3/20/2024 |  | 4/30/2026 | N | STD | 596 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GLOUCESTER | 438621 | 01930 | 10 | Solar | 05_05_321W10 | 10/27/2022 | 06/30/2022 | 2 | 0 | 2 | 11/01/2022 | 11/01/2022 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2022 | 10/27/2022 | 7/20/2024 | Y | EXP | 365 | 06/09/2023 | 06/21/2023 | 13 | 0 | 13 |  |  | 8/2/2023 | Connected |  | N
National Grid | LOWELL | 178693 | 01851 | 10 | Solar | 05_05_344W4 | 02/09/2018 | 02/06/2018 | 70 | 0 | 70 | 05/21/2018 | 05/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2018 |  | 2/12/2019 | N | EXP | 251 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 176156 | 01886 | 21.4 | Solar | 05_12_51T1 | 02/03/2015 | 02/03/2015 | 6 | 3 | 3 | 02/12/2015 | 02/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2015 | 02/03/2015 | 7/19/2016 | Y | EXP | 505 | 05/18/2016 | 10/17/2017 | 353 | 0 | 353 | 4/6/2016 | 4/6/2016 | 4/6/2016 | Connected |  | N
National Grid | BILLERICA | 394090 | 01821 | 6 | Solar | 05_14_2L2 | 11/29/2021 | 01/07/2022 | 11 | 10 | 1 | 12/15/2021 | 12/15/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 335891 | 01843 | 100 | Solar | 05_14_57L2 | 01/11/2021 | 01/25/2021 | 8 | 0 | 8 | 01/26/2021 | 01/26/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  | 3/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 189305 | 01609 | 7.6 | Solar | 05_14_70L6 | 06/27/2018 | 06/27/2018 | 9 | 6 | 3 | 09/14/2018 | 09/14/2018 | 148 | 0 | 148 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 646024 | 01540 | 7.6 | Solar | 05_14_8L1 | 10/10/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 10/10/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | SCITUATE | 750192 | 02066 | 11.5 | Battery Add-On | 05_01_23W2 | 02/09/2026 | 02/10/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 175770 | 01606 | 100 | Solar | 05_01_406L4 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 96 | 0 | 96 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 12/31/2014 | N | EXP | 86 |  |  | 0 | 0 | 0 | 12/26/2014 | 12/26/2014 |  | Withdrawn |  | Y
National Grid | NORTHBRIDGE | 640601 | 01534 | 23 | Battery Add-On | 05_07_15J1 | 09/16/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 54 | 40 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 09/16/2024 | 1/13/2026 | Y | EXP | 365 | 03/21/2025 | 03/27/2025 | 7 | 0 | 7 |  |  | 5/14/2025 | Connected |  | N
National Grid | BELLINGHAM | 174157 | 02019 | 2016 | Natural Gas | 05_01_HT41 | 04/24/2012 | 04/24/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 05/13/2012 | 3 | 0 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2012 |  | 12/31/2016 | N | STD | 1482 |  |  | 0 | 0 | 0 |  |  | 7/14/2017 | Connected |  | N
National Grid | GLOUCESTER | 753399 | 01930 | 10 | Solar | 05_05_321W2 | 02/26/2026 | 03/03/2026 | 3 | 0 | 3 | 03/04/2026 | 03/04/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2026 |  | 4/1/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 186502 | 01851 | 10 | Solar | 05_05_344W4 | 06/13/2018 | 06/13/2018 | 7 | 0 | 7 | 06/26/2018 | 06/26/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 176170 | 01886 | 2.75 | Solar | 05_12_51T1 | 04/22/2015 | 04/22/2015 | 1 | 1 | 0 | 04/24/2015 | 04/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2015 |  | 9/30/2015 | N | EXP | 142 |  |  | 0 | 0 | 0 | 6/1/2015 | 6/1/2015 | 9/24/2015 | Connected |  | N
National Grid | BILLERICA | 488662 | 01821 | 22.272 | Solar | 05_14_2L2 | 12/29/2022 | 04/06/2023 | 68 | 59 | 9 | 04/07/2023 | 04/07/2023 | 150 | 133 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 341508 | 01843 | 9.6 | Solar | 05_14_57L2 | 02/10/2021 | 02/16/2021 | 2 | 0 | 2 | 02/17/2021 | 02/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 12/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2022 | Connected |  | N
National Grid | WORCESTER | 343928 | 01609 | 19 | Solar | 05_14_70L6 | 02/25/2021 |  | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 651615 | 01540 | 7.6 | Solar | 05_14_8L1 | 11/12/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 32 | 7 | 25 | 03/21/2025 | 04/28/2025 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 04/28/2025 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | SCITUATE | 172485 | 02066 | 6 | Solar | 05_01_23W2 | 04/12/2018 | 04/12/2018 | 9 | 0 | 9 | 06/06/2018 | 06/06/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2018 | 04/12/2018 | 7/23/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2019 | Connected |  | N
National Grid | WORCESTER | 176419 | 01610 | 1250 | Solar | 05_01_406L4 | 12/07/2015 | 12/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/08/2015 | 01/07/2016 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/13/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 657499 | 01569 | 0 | Battery Add-On | 05_07_15J1 | 11/27/2024 | 12/12/2024 | 9 | 7 | 2 | 12/13/2024 | 12/13/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | BELLINGHAM | 321061 | 02019 | 75 | Natural Gas | 05_01_HT41 | 11/20/2020 | 12/07/2020 | 9 | 0 | 9 |  |  | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 |  | 4/27/2023 | N | STD | 403 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | BEVERLY | 174622 | 01915 | 2000 | Solar | 05_05_321W2 | 04/14/2011 | 04/14/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2011 | 04/14/2011 | 6/1/2012 | Y | STD | 182 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 6/1/2012 | Connected |  | N
National Grid | LOWELL | 187518 | 01851 | 3.8 | Solar | 05_05_344W4 | 06/25/2018 | 06/25/2018 | 1 | 0 | 1 | 07/02/2018 | 07/02/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 176167 | 01886 | 150 | Solar | 05_12_51T1 | 04/20/2015 | 04/20/2015 | 0 | 0 | 0 | 04/20/2015 | 04/20/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2015 |  | 9/30/2015 | N | EXP | 161 |  |  | 0 | 0 | 0 | 6/19/2015 | 6/19/2015 | 11/6/2015 | Connected |  | N
National Grid | BILLERICA | 561313 | 01821 | 7.25 | Solar | 05_14_2L2 | 01/03/2024 | 02/20/2024 | 32 | 25 | 7 | 02/21/2024 | 02/21/2024 | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 449761 | 01843 | 7.6 | Solar | 05_14_57L2 | 08/09/2022 | 08/10/2022 | 1 | 0 | 1 | 08/11/2022 | 08/11/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 |  | 9/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2024 | Connected |  | N
National Grid | WORCESTER | 367044 | 01609 | 19 | Solar | 05_14_70L6 | 06/30/2021 | 07/01/2021 | 1 | 0 | 1 | 07/02/2021 | 07/02/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 658814 | 01540 | 0 | Solar | 05_14_8L1 | 12/06/2024 | 01/07/2025 | 21 | 18 | 3 | 01/08/2025 | 01/08/2025 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | SCITUATE | 207061 | 02066 | 15.2 | Solar | 05_01_23W2 | 01/30/2019 | 02/12/2019 | 7 | 0 | 7 | 02/13/2019 | 02/13/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 |  | 2/27/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2019 | Connected |  | N
National Grid | WORCESTER | 176458 | 01610 | 6 | Solar | 05_01_406L4 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 |  | 12/14/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 5/9/2016 | 5/9/2016 | 5/10/2016 | Connected |  | N
National Grid | UXBRIDGE | 302775 | 01569 | 7.6 | Solar | 05_07_17J1 | 07/23/2020 | 08/14/2020 | 15 | 15 | 0 | 08/17/2020 | 08/17/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 |  | 8/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2021 | Connected |  | N
National Grid | BELLINGHAM | 174618 | 02019 | 200 | Solar | 05_01_HT42 | 02/07/2011 | 02/07/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2011 | 02/07/2011 | 1/11/2012 | Y | EXP | 245 | 08/02/2011 | 01/28/2012 | 122 | 0 | 122 | 8/3/2012 | 8/3/2012 | 1/11/2012 | Connected |  | N
National Grid | GLOUCESTER | 175163 | 01930 | 1000 | Solar | 05_05_321W2 | 06/02/2011 | 06/02/2011 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 187250 | 01863 | 11.4 | Solar | 05_05_344W4 | 07/10/2018 | 07/27/2018 | 11 | 7 | 4 | 07/30/2018 | 07/30/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 461 |  |  | 0 | 0 | 0 |  |  | 11/7/2019 | Connected |  | N
National Grid | WESTFORD | 176197 | 01886 | 900 | Solar | 05_12_51T1 | 02/06/2015 | 02/06/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2015 | 03/16/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 566878 | 01821 | 7.6 | Solar | 05_14_2L2 | 11/03/2023 | 11/27/2023 | 15 | 8 | 7 | 11/28/2023 | 11/28/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/03/2023 | 2/19/2025 | Y | EXP | 365 | 07/29/2024 | 10/08/2024 | 72 | 0 | 72 |  |  | 10/17/2024 | Connected |  | N
National Grid | LAWRENCE | 373288 | 01843 | 15.2 | Solar | 05_14_57L2 | 09/08/2021 | 09/22/2021 | 11 | 10 | 1 | 09/23/2021 | 09/23/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 |  | 2/1/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 412558 | 01609 | 9.8 | Solar | 05_14_70L6 | 03/01/2022 | 03/02/2022 | 1 | 0 | 1 | 03/03/2022 | 03/03/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2022 | 03/01/2022 | 9/20/2023 | Y | EXP | 365 | 08/18/2022 | 09/15/2022 | 29 | 0 | 29 |  |  | 1/4/2023 | Connected |  | N
National Grid | OXFORD | 661249 | 01540 | 7.6 | Solar | 05_14_8L1 | 12/20/2024 | 12/27/2024 | 4 | 0 | 4 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | SCITUATE | 209250 | 02066 | 9.92 | Solar | 05_01_23W2 | 03/19/2019 | 03/28/2019 | 6 | 0 | 6 | 03/29/2019 | 03/29/2019 | 22 | 19 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2019 | 03/19/2019 | 4/29/2020 | Y | EXP | 365 | 02/22/2020 | 02/21/2020 | 0 | 0 | 0 |  |  | 4/21/2020 | Connected |  | N
National Grid | WORCESTER | 176491 | 01603 | 2000 | Solar | 05_01_406L4 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 01/05/2016 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2017 |  | 12/15/2016 | N | STD | 137 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 662497 | 01569 | 7.8 | Solar | 05_07_17J1 | 12/24/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | BELLINGHAM | 177587 | 02019 | 300 | Natural Gas | 05_01_HT45 | 05/17/2017 | 05/17/2017 | 18 | 15 | 3 | 06/14/2017 | 06/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 5/23/2018 | N | EXP | 320 |  |  | 0 | 0 | 0 | 4/12/2018 | 4/12/2018 | 4/12/2018 | Connected |  | N
National Grid | BEVERLY | 175241 | 01915 | 20 | Solar | 05_05_321W2 | 08/22/2014 | 08/22/2014 | 5 | 0 | 5 | 09/02/2014 | 09/02/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 11/28/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 4/24/2015 | Connected |  | N
National Grid | LOWELL | 189314 | 01851 | 10 | Solar | 05_05_344W4 | 06/27/2018 | 06/27/2018 | 16 | 11 | 5 | 11/21/2018 | 11/21/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 176196 | 01886 | 950 | Solar | 05_12_51T1 | 02/06/2015 | 02/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 583609 | 01821 | 6.67 | Solar | 05_14_2L2 | 04/09/2024 | 03/06/2024 | 1 | 0 | 1 | 04/11/2024 | 04/11/2024 | 71 | 59 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 382038 | 01810 | 19.14 | Solar | 05_14_57L2 | 09/14/2021 | 12/16/2021 | 3 | 0 | 3 | 09/20/2021 | 09/20/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2021 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 430494 | 01609 | 15.2 | Solar | 05_14_70L6 | 05/16/2022 | 05/17/2022 | 1 | 0 | 1 | 05/18/2022 | 05/18/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 6/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2022 | Connected |  | N
National Grid | OXFORD | 661637 | 01540 | 10 | Solar | 05_14_8L1 | 12/19/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/19/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | SCITUATE | 310622 | 02066 | 11.4 | Solar | 05_01_23W2 | 06/23/2021 | 06/25/2021 | 2 | 0 | 2 | 06/28/2021 | 06/28/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176490 | 01603 | 4000.002 | Solar | 05_01_406L4 | 12/08/2015 | 12/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 01/05/2016 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2017 | 12/08/2015 | 2/14/2020 | Y | STD | 805 | 10/16/2019 | 01/14/2020 | 90 | 0 | 90 |  |  | 2/13/2020 | Connected |  | N
National Grid | UXBRIDGE | 176459 | 01569 | 10 | Solar | 05_07_18J1 | 02/04/2016 | 02/04/2016 | 0 | 0 | 0 | 02/05/2016 | 02/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2016 |  | 2/10/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 5/13/2016 | 5/13/2016 | 5/16/2016 | Connected |  | N
National Grid | BELLINGHAM | 265164 | 02019 | 125 | Natural Gas | 05_01_HT46 | 08/10/2020 | 09/16/2020 | 26 | 20 | 6 |  |  | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 175390 | 01930 | 728 | Solar | 05_05_321W2 | 09/11/2014 | 09/11/2014 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/23/2014 | 10/20/2014 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 | 09/11/2014 | 1/26/2016 | Y | STD | 309 |  |  | 0 | 0 | 0 | 7/19/2016 | 7/19/2016 | 6/17/2016 | Connected |  | N
National Grid | LOWELL | 190511 | 01851 | 10 | Solar | 05_05_344W4 | 07/11/2018 | 10/29/2018 | 10 | 7 | 3 | 10/30/2018 | 10/30/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 | 07/11/2018 | 11/12/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | WESTFORD | 176186 | 01886 | 112 | Solar | 05_12_51T1 | 08/28/2015 | 08/28/2015 | 3 | 3 | 0 | 09/04/2015 | 09/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2015 |  | 9/6/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 4/11/2017 | 4/11/2017 | 4/11/2017 | Connected |  | N
National Grid | BILLERICA | 588923 | 01821 | 7.6 | Solar | 05_14_2L2 | 02/28/2024 | 03/05/2024 | 4 | 0 | 4 | 03/06/2024 | 03/06/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 424028 | 01810 | 15.2 | Solar | 05_14_57L2 | 04/14/2022 | 04/15/2022 | 1 | 0 | 1 | 04/19/2022 | 04/19/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 04/14/2022 | 12/7/2024 | Y | EXP | 365 | 06/09/2023 | 12/05/2023 | 180 | 0 | 180 |  |  | 2/27/2025 | Connected |  | N
National Grid | WORCESTER | 460075 | 01609 | 15.2 | Solar | 05_14_70L6 | 09/19/2022 | 09/22/2022 | 3 | 0 | 3 | 09/23/2022 | 09/23/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 3/6/2024 | N | EXP | 365 | 01/07/2023 | 03/03/2023 | 56 | 0 | 56 |  |  | 5/24/2023 | Connected |  | N
National Grid | OXFORD | 669874 | 01540 | 7.6 | Solar | 05_14_8L1 | 02/04/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | SCITUATE | 371778 | 02066 | 11.4 | Solar | 05_01_23W2 | 07/23/2021 | 07/26/2021 | 1 | 0 | 1 | 07/27/2021 | 07/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2021 |  | 3/24/2023 | N | EXP | 535 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176531 | 01606 | 252 | Solar | 05_01_406L4 | 12/17/2015 | 12/17/2015 | 27 | 27 | 0 | 01/28/2016 | 01/28/2016 | 192 | 0 | 192 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/22/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 177907 | 01569 | 43.2 | Solar | 05_07_18J1 | 08/16/2017 | 08/16/2017 | 13 | 13 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 8/21/2018 | N | EXP | 347 |  |  | 0 | 0 | 0 | 10/27/2017 | 10/27/2017 | 11/13/2017 | Connected |  | N
National Grid | BELLINGHAM | 372126 | 02019 | 100 | Solar | 05_01_HT46 | 07/28/2021 | 11/08/2021 | 71 | 62 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 175463 | 01930 | 450 | Solar | 05_05_321W2 | 09/19/2014 | 09/19/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2014 | 10/20/2014 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 | 09/19/2014 | 12/31/2016 | Y | STD | 649 | 10/01/2015 | 06/23/2016 | 179 | 0 | 179 | 7/19/2016 | 7/19/2016 | 6/17/2016 | Connected |  | N
National Grid | LOWELL | 192457 | 01851 | 3.8 | Solar | 05_05_344W4 | 08/01/2018 | 08/27/2018 | 5 | 4 | 1 | 08/28/2018 | 08/28/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  | 10/30/2019 | N | EXP | 414 |  |  | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | WESTFORD | 176185 | 01886 | 112 | Solar | 05_12_51T1 | 08/28/2015 | 08/28/2015 | 3 | 3 | 0 | 09/04/2015 | 09/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 | 08/28/2015 | 9/6/2016 | Y | EXP | 362 | 12/19/2016 | 02/24/2017 | 45 | 0 | 45 | 4/20/2017 | 4/20/2017 | 4/14/2017 | Connected |  | N
National Grid | BILLERICA | 620853 | 01821 | 5.76 | Solar | 05_14_2L2 | 06/26/2024 | 10/11/2024 | 54 | 50 | 4 | 10/15/2024 | 10/15/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 431905 | 01810 | 7.6 | Solar | 05_14_57L2 | 07/08/2022 | 07/19/2022 | 8 | 7 | 1 | 07/20/2022 | 07/20/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 579214 | 01609 | 34.5 | Solar | 05_14_70L6 | 12/20/2023 |  | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 672761 | 01540 | 10 | Solar | 05_14_8L1 | 02/18/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 83 | 64 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 371327 | 02025 | 19 | Solar | 05_01_23W2 | 07/21/2021 | 08/17/2021 | 19 | 18 | 1 | 08/18/2021 | 08/18/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2021 |  | 9/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2022 | Connected |  | N
National Grid | WORCESTER | 177404 | 01609 | 6 | Solar | 05_01_406L4 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 146 | 0 | 146 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2016 |  | 7/5/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 317141 | 01569 | 7.6 | Solar | 05_07_18J1 | 10/05/2020 | 11/02/2020 | 18 | 16 | 2 | 11/03/2020 | 11/03/2020 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2021 | Connected |  | N
National Grid | BELLINGHAM | 177605 | 02019 | 1530.048 | Solar | 05_01_HT48 | 09/19/2017 | 02/26/2018 | 102 | 102 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/26/2018 | 06/22/2018 | 28 | 0 | 28 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2019 | 09/19/2017 | 8/27/2025 | Y | STD | 156 | 10/12/2023 | 08/14/2025 | 672 | 3 | 669 |  |  | 8/28/2025 | Connected |  | N
National Grid | GLOUCESTER | 175462 | 01930 | 950 | Solar | 05_05_321W2 | 09/19/2014 | 09/19/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2014 | 10/20/2014 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 | 09/19/2014 | 2/10/2016 | Y | STD | 324 | 10/01/2015 | 06/23/2016 | 179 | 0 | 179 | 7/19/2016 | 7/19/2016 | 6/17/2016 | Connected |  | N
National Grid | LOWELL | 192331 | 01851 | 3.8 | Solar | 05_05_344W4 | 07/31/2018 | 08/24/2018 | 3 | 3 | 0 | 08/27/2018 | 08/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 07/31/2018 | 5/14/2020 | Y | EXP | 626 | 11/06/2019 | 12/17/2019 | 41 | 0 | 41 |  |  | 1/28/2020 | Connected |  | N
National Grid | WESTFORD | 176284 | 01886 | 126 | Solar | 05_12_51T1 | 05/07/2015 | 05/07/2015 | 14 | 14 | 0 | 06/01/2015 | 06/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2015 |  | 12/31/2016 | N | EXP | 488 |  |  | 0 | 0 | 0 | 2/12/2016 | 2/12/2016 | 3/13/2017 | Connected |  | N
National Grid | BILLERICA | 507289 | 01821 | 12.76 | Solar | 05_07_911W13 | 03/08/2023 | 04/19/2023 | 29 | 27 | 2 | 04/20/2023 | 04/20/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2023 |  | 7/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N
National Grid | ANDOVER | 433175 | 01810 | 10 | Solar | 05_14_57L2 | 06/17/2022 | 06/22/2022 | 2 | 0 | 2 | 06/23/2022 | 06/23/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 | 06/17/2022 | 3/19/2024 | Y | EXP | 365 | 03/08/2023 | 03/20/2023 | 13 | 0 | 13 |  |  | 3/27/2023 | Connected |  | Y
National Grid | WORCESTER | 588066 | 01609 | 9.765 | Solar | 05_14_70L6 | 02/12/2024 | 02/21/2024 | 7 | 5 | 2 | 02/22/2024 | 02/22/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/12/2024 | 4/24/2025 | Y | EXP | 365 | 05/23/2024 | 09/13/2024 | 93 | 0 | 93 |  |  | 7/26/2024 | Connected |  | N
National Grid | OXFORD | 675590 | 01540 | 7.6 | Solar | 05_14_8L1 | 03/04/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 379039 | 02025 | 15.2 | Solar | 05_01_23W2 | 08/31/2021 | 09/20/2021 | 13 | 13 | 0 | 09/21/2021 | 09/21/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 |  | 7/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177886 | 01609 | 10 | Solar | 05_01_406L4 | 04/11/2017 | 04/11/2017 | 2 | 0 | 2 | 04/14/2017 | 04/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2017 | 04/11/2017 | 4/17/2018 | Y | EXP | 365 | 08/04/2017 | 09/05/2017 | 21 | 0 | 21 | 10/17/2017 | 10/17/2017 | 10/17/2017 | Connected |  | N
National Grid | UXBRIDGE | 429558 | 01569 | 15.2 | Solar | 05_07_18J1 | 05/18/2022 | 05/20/2022 | 2 | 0 | 2 | 05/23/2022 | 05/23/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2022 |  | 10/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 178456 | 02019 | 496 | Solar | 05_01_HT48 | 11/30/2017 | 11/30/2017 | 34 | 12 | 22 |  |  | 51 | 0 | 51 | 03/19/2018 | 03/23/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 03/23/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 12/6/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 175502 | 01930 | 1000 | Solar | 05_05_321W2 | 09/29/2014 | 09/29/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2014 | 10/31/2014 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 | 09/29/2014 | 1/21/2016 | Y | STD | 304 | 06/09/2016 | 09/14/2016 | 66 | 0 | 66 | 12/22/2016 | 12/22/2016 | 12/22/2016 | Connected |  | N
National Grid | LOWELL | 198992 | 01851 | 250 | Solar | 05_05_344W4 | 10/19/2018 | 11/14/2018 | 15 | 3 | 12 | 11/15/2018 | 11/15/2018 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 |  | 1/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 176810 | 01886 | 22.8 | Solar | 05_12_51T1 | 04/27/2016 | 04/27/2016 | 1 | 1 | 0 | 04/29/2016 | 04/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 5/3/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 5/25/2016 | 5/25/2016 | 9/15/2016 | Connected |  | N
National Grid | BILLERICA | 512252 | 01821 | 3.84 | Solar | 05_07_911W13 | 03/23/2023 | 03/28/2023 | 3 | 0 | 3 | 03/29/2023 | 03/29/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/23/2023 | 5/16/2024 | Y | EXP | 365 | 07/20/2023 | 07/20/2023 | 1 | 0 | 1 |  |  | 8/3/2023 | Connected |  | N
National Grid | LAWRENCE | 441483 | 01843 | 7.6 | Solar | 05_14_57L2 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 604030 | 01609 | 5 | Solar | 05_14_70L6 | 04/18/2024 | 05/01/2024 | 3 | 0 | 3 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 685276 | 01540 | 15.76 | Solar | 05_14_8L1 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 65 | 24 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 485090 | 02025 | 17.45 | Solar | 05_01_23W2 | 12/21/2022 | 12/22/2022 | 1 | 0 | 1 | 12/23/2022 | 12/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2023 | Connected |  | N
National Grid | WORCESTER | 178569 | 01606 | 10 | Solar | 05_01_406L4 | 12/07/2017 | 12/07/2017 | 17 | 0 | 17 | 01/04/2018 | 01/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 |  | 12/13/2018 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N
National Grid | UXBRIDGE | 201688 | 01569 | 66.6 | Solar | 05_07_1J11 | 12/04/2018 | 12/20/2018 | 11 | 6 | 5 | 03/06/2019 | 03/06/2019 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 722164 | 02019 | 35.705 | Solar | 05_01_HT5 | 09/29/2025 |  | 20 | 17 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | GLOUCESTER | 175493 | 01930 | 1000 | Solar | 05_05_321W2 | 07/25/2014 | 07/25/2014 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2014 | 09/05/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2015 | 07/25/2014 | 6/30/2017 | Y | STD | 781 | 03/03/2016 | 03/13/2017 | 254 | 0 | 254 | 5/17/2017 | 5/17/2017 | 7/18/2017 | Connected |  | N
National Grid | BROCKTON | 200884 | 02301 | 500 | Solar | 05_05_344W4 | 02/25/2019 | 03/18/2019 | 15 | 9 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2019 | 04/09/2019 | 16 | 8 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2019 | 02/25/2019 | 4/7/2021 | Y | STD | 321 | 09/30/2020 | 12/22/2020 | 83 | 0 | 83 | 3/30/2021 | 3/29/2021 | 4/7/2021 | Connected |  | N
National Grid | WESTFORD | 176960 | 01886 | 45 | Solar | 05_12_51T1 | 07/17/2016 | 07/17/2016 | 1 | 1 | 0 | 07/19/2016 | 07/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2016 |  | 7/23/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 | 2/13/2017 | 2/13/2017 | 2/13/2017 | Connected |  | N
National Grid | BILLERICA | 521575 | 01821 | 2.61 | Solar | 05_07_911W13 | 08/14/2023 | 08/17/2023 | 3 | 0 | 3 | 08/18/2023 | 08/18/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 7/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2024 | Connected |  | N
National Grid | LAWRENCE | 458118 | 01843 | 19 | Solar | 05_14_57L2 | 09/12/2022 | 09/12/2022 | 0 | 0 | 0 | 09/13/2022 | 09/13/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 10/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | WORCESTER | 610202 | 01609 | 4.188 | Solar | 05_14_70L6 | 05/14/2024 | 07/09/2024 | 16 | 9 | 7 | 07/10/2024 | 07/10/2024 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 05/14/2024 | 9/10/2025 | Y | EXP | 365 | 09/26/2024 | 10/24/2024 | 29 | 0 | 29 |  |  | 12/4/2024 | Connected |  | N
National Grid | OXFORD | 658936 | 01540 | 499 | Solar | 05_14_8L2 | 04/08/2025 | 04/24/2025 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/25/2025 | 05/28/2025 | 23 | 4 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | COHASSET | 542998 | 02025 | 22.8 | Solar | 05_01_23W2 | 09/22/2023 | 10/05/2023 | 9 | 8 | 1 | 10/06/2023 | 10/06/2023 | 81 | 34 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 198666 | 01605 | 6 | Solar | 05_01_406L4 | 12/13/2018 | 12/24/2018 | 6 | 0 | 6 | 12/26/2018 | 12/26/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 752321 | 01569 | 80 | Solar | 05_07_1J6 | 04/01/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BELLINGHAM | 724047 | 02038 | 67.3 | Solar | 05_01_HT5 | 10/03/2025 | 10/27/2025 | 15 | 8 | 7 | 10/28/2025 | 10/28/2025 | 106 | 25 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GLOUCESTER | 175583 | 01930 | 15.265 | Solar | 05_05_321W2 | 04/16/2014 | 04/16/2014 | 6 | 0 | 6 | 04/28/2014 | 04/28/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2014 |  | 8/29/2014 | N | EXP | 101 |  |  | 0 | 0 | 0 | 5/20/2014 | 5/20/2014 | 8/15/2014 | Connected |  | N
National Grid | BROCKTON | 239323 | 02301 | 10 | Solar | 05_05_344W4 | 02/05/2020 | 02/11/2020 | 3 | 0 | 3 | 02/12/2020 | 02/12/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 | 02/05/2020 | 2/9/2022 | Y | EXP | 365 | 07/15/2020 | 07/28/2020 | 13 | 0 | 13 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 177027 | 01886 | 731 | Solar | 05_12_51T1 | 03/16/2017 | 03/16/2017 | 12 | 10 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2017 | 05/05/2017 | 22 | 8 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 | 03/16/2017 | 8/18/2021 | Y | STD | 1026 | 11/08/2019 | 04/22/2020 | 166 | 0 | 166 |  |  | 8/18/2021 | Connected |  | N
National Grid | BILLERICA | 524386 | 01821 | 6 | Solar | 05_07_911W13 | 05/12/2023 |  | 107 | 91 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 461886 | 01843 | 7.6 | Solar | 05_14_57L2 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2023 | 11/29/2022 | 6/15/2024 | Y | EXP | 365 | 06/09/2023 | 06/12/2023 | 4 | 0 | 4 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 645607 | 01609 | 5.76 | Solar | 05_14_70L6 | 11/20/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | OXFORD | 726407 | 01540 | 5.76 | Solar | 05_14_8L2 | 10/14/2025 | 12/04/2025 | 1 | 0 | 1 | 01/07/2026 | 01/07/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | QUINCY | 575450 | 02169 | 7.6 | Solar | 05_01_23W2 | 12/04/2023 | 01/09/2024 | 25 | 24 | 1 | 01/10/2024 | 01/10/2024 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 306142 | 01609 | 0 | Other | 05_01_406L4 | 09/16/2020 | 09/30/2020 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/26/2020 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 619741 | 01569 | 86 | Solar | 05_07_1J6 | 07/25/2024 | 08/07/2024 | 9 | 4 | 5 | 08/08/2024 | 08/08/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 |  | 4/5/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | BELLINGHAM | 749603 | 02019 | 34.6 | Solar | 05_01_HT5 | 02/05/2026 |  | 25 | 24 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | GLOUCESTER | 176528 | 01930 | 10 | Solar | 05_05_321W2 | 12/15/2015 | 12/15/2015 | 16 | 16 | 0 | 01/08/2016 | 01/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2016 |  | 12/20/2016 | N | EXP | 336 |  |  | 0 | 0 | 0 | 1/20/2016 | 1/20/2016 | 3/7/2016 | Connected |  | N
National Grid | BROCKTON | 251916 | 02301 | 7.6 | Solar | 05_05_344W4 | 10/07/2019 | 10/30/2019 | 15 | 15 | 0 | 10/31/2019 | 10/31/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 |  | 12/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 177155 | 01886 | 20 | Solar | 05_12_51T1 | 10/24/2016 | 10/24/2016 | 4 | 4 | 0 | 10/28/2016 | 10/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2016 |  | 10/29/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 12/20/2016 | 12/20/2016 | 12/20/2016 | Connected |  | N
National Grid | BILLERICA | 558668 | 01821 | 2.61 | Solar | 05_07_911W13 | 10/04/2023 | 10/12/2023 | 6 | 3 | 3 | 10/13/2023 | 10/13/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 2/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2024 | Connected |  | N
National Grid | METHUEN | 479921 | 01844 | 7.6 | Solar | 05_14_57L2 | 01/04/2023 | 01/09/2023 | 3 | 0 | 3 | 01/10/2023 | 01/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 650194 | 01609 | 18.24 | Solar | 05_14_70L6 | 10/28/2024 | 10/30/2024 | 2 | 0 | 2 | 10/31/2024 | 10/31/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | OXFORD | 726315 | 01540 | 20 | Solar | 05_14_8L2 | 10/14/2025 | 10/24/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 45 | 30 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2026 |  | 3/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | QUINCY | 581452 | 02169 | 7.6 | Solar | 05_01_23W2 | 01/04/2024 | 01/17/2024 | 9 | 7 | 2 | 01/18/2024 | 01/18/2024 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | N
National Grid | WORCESTER | 373487 | 01609 | 9.8 | Solar | 05_01_406L4 | 08/05/2021 | 12/13/2021 | 2 | 0 | 2 | 08/10/2021 | 08/10/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2021 | 08/05/2021 | 11/5/2023 | Y | EXP | 365 | 03/29/2022 | 06/22/2022 | 86 | 0 | 86 |  |  | 2/3/2023 | Connected |  | N
National Grid | UXBRIDGE | 673520 | 01569 | 200 | Solar | 05_07_1J6 | 08/04/2025 |  | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 175132 | 02019 | 75 | Solar | 05_01_HT50 | 11/06/2012 | 11/06/2012 | 7 | 7 | 0 | 11/29/2012 | 11/29/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2013 |  | 1/31/2013 | N | EXP | 6 | 03/14/2013 | 04/24/2013 | 27 | 0 | 27 | 2/20/2014 | 2/20/2014 | 4/2/2014 | Connected |  | N
National Grid | HAMILTON | 176607 | 01982 | 1000 | Solar | 05_05_321W2 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/12/2016 | 5 | 1 | 4 |  | 0 | 0 | 0 | 05/06/2016 | 07/19/2016 | 49 | 0 | 49 | 7/19/2016 | 12/29/2015 | 10/20/2017 | Y | STD | 458 | 07/20/2017 | 01/11/2018 | 114 | 0 | 114 | 12/20/2017 | 12/20/2017 | 12/22/2017 | Connected |  | N
National Grid | BROCKTON | 268733 | 02301 | 7.6 | Solar | 05_05_344W4 | 01/02/2020 | 01/10/2020 | 5 | 0 | 5 | 01/13/2020 | 01/13/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2020 | 01/02/2020 | 9/22/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2021 | Connected |  | N
National Grid | WESTFORD | 177559 | 01886 | 3 | Solar | 05_12_51T1 | 07/13/2017 | 07/13/2017 | 22 | 22 | 0 | 08/15/2017 | 08/15/2017 | 117 | 7 | 110 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 |  | 7/19/2018 | N | EXP | 325 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 558405 | 01821 | 3.8 | Solar | 05_07_911W13 | 09/29/2023 | 10/03/2023 | 3 | 1 | 2 | 10/04/2023 | 10/04/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2023 |  | 1/12/2025 | N | EXP | 420 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 540656 | 01841 | 13.92 | Solar | 05_14_57L2 | 07/24/2023 | 07/27/2023 | 4 | 3 | 1 | 07/28/2023 | 07/28/2023 | 64 | 45 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 12/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | WORCESTER | 661714 | 01609 | 10 | Solar | 05_14_70L6 | 12/19/2024 | 01/27/2025 | 13 | 10 | 3 | 01/28/2025 | 01/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | OXFORD | 733514 | 01540 | 15 | Solar | 05_14_8L2 | 11/13/2025 | 11/17/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 35 | 17 | 18 | 03/03/2026 |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | QUINCY | 615221 | 02169 | 9.88 | Solar | 05_01_23W2 | 06/03/2024 | 07/03/2024 | 5 | 2 | 3 | 07/05/2024 | 07/05/2024 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2024 | 06/03/2024 | 7/19/2026 | Y | EXP | 365 | 08/29/2024 | 09/30/2024 | 33 | 0 | 33 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 386256 | 01609 | 7.6 | Solar | 05_01_406L4 | 10/04/2021 |  | 31 | 26 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLVILLE | 688257 | 01529 | 75 | Solar | 05_07_1W1 | 11/14/2025 |  | 78 | 70 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | BELLINGHAM | 177349 | 02019 | 88 | Solar | 05_01_HT50 | 11/23/2016 | 11/23/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2016 | 12/05/2016 | 4 | 4 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 |  | 12/3/2017 | N | STD | 206 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 176636 | 01930 | 2000 | Solar | 05_05_321W2 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/12/2016 | 5 | 1 | 4 |  | 0 | 0 | 0 | 05/06/2016 | 07/19/2016 | 49 | 0 | 49 | 7/19/2016 | 12/29/2015 | 10/20/2017 | Y | STD | 458 | 07/20/2017 | 01/11/2018 | 114 | 0 | 114 | 12/20/2017 | 12/20/2017 | 12/22/2017 | Connected |  | N
National Grid | BROCKTON | 281369 | 02301 | 7.6 | Solar | 05_05_344W4 | 04/14/2020 | 04/20/2020 | 3 | 0 | 3 | 04/21/2020 | 04/21/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2020 | 04/14/2020 | 3/31/2021 | Y | EXP | 365 | 12/23/2020 | 01/08/2021 | 16 | 0 | 16 |  |  | 2/18/2021 | Connected |  | N
National Grid | WESTFORD | 178074 | 01886 | 20 | Solar | 05_12_51T1 | 11/02/2017 | 11/02/2017 | 91 | 91 | 0 | 04/05/2018 | 04/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2018 |  | 11/7/2018 | N | EXP | 215 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 558206 | 01821 | 6 | Solar | 05_07_911W13 | 10/09/2023 | 10/12/2023 | 3 | 0 | 3 | 10/13/2023 | 10/13/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 10/09/2023 | 12/1/2025 | Y | EXP | 730 | 03/14/2024 | 03/21/2024 | 8 | 0 | 8 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 570545 | 01841 |  | Battery Add-On | 05_14_57L2 | 11/10/2023 | 11/30/2023 | 14 | 12 | 2 | 12/01/2023 | 12/01/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 11/10/2023 | 2/21/2025 | Y | EXP | 365 | 04/23/2024 | 06/04/2024 | 43 | 0 | 43 |  |  | 6/7/2024 | Connected |  | N
National Grid | WORCESTER | 672015 | 01605 | 6.08 | Solar | 05_14_70L6 | 02/13/2025 | 02/20/2025 | 4 | 0 | 4 | 02/21/2025 | 02/21/2025 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | OXFORD | 738886 | 01540 | 3.8 | Solar | 05_14_8L2 | 12/09/2025 | 12/11/2025 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 57 | 24 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | QUINCY | 174114 | 02169 | 1500 | Solar | 05_07_92W54 | 03/30/2012 | 03/30/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/17/2012 | 06/25/2012 | 47 | 0 | 47 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2012 | 03/30/2012 | 10/31/2012 | Y | STD | 35 | 07/31/2013 | 09/27/2013 | 41 | 0 | 41 | 9/25/2013 | 9/25/2013 | 10/24/2013 | Connected |  | N
National Grid | WORCESTER | 398616 | 01608 | 11.4 | Solar | 05_01_406L4 | 07/06/2022 | 07/11/2022 | 3 | 2 | 1 | 07/12/2022 | 07/12/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 755465 | 01569 |  | Solar | 05_07_1W1 | 03/13/2026 |  | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BELLINGHAM | 592110 | 02019 | 60 | Solar | 05_01_HT52 | 03/11/2024 | 03/20/2024 | 8 | 2 | 6 | 03/21/2024 | 03/21/2024 | 154 | 140 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 178259 | 01930 | 4990 | Solar | 05_05_321W2 | 04/17/2018 | 04/17/2018 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2018 | 06/21/2018 | 22 | 21 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/22/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 284138 | 02301 | 15.2 | Solar | 05_05_344W4 | 03/17/2020 | 04/13/2020 | 19 | 19 | 0 | 04/14/2020 | 04/14/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2020 | 03/17/2020 | 4/13/2021 | Y | EXP | 365 | 07/15/2020 | 12/05/2020 | 143 | 5 | 138 |  |  | 12/16/2020 | Connected |  | N
National Grid | WESTFORD | 178070 | 01886 | 144 | Solar | 05_12_51T1 | 10/31/2017 | 10/31/2017 | 9 | 9 | 0 | 11/20/2017 | 11/20/2017 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2017 |  | 11/6/2018 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  | 8/27/2018 | Connected |  | N
National Grid | BILLERICA | 529271 | 01821 | 7.6 | Solar | 05_07_911W13 | 05/30/2023 | 06/01/2023 | 2 | 0 | 2 | 06/02/2023 | 06/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 | 05/30/2023 | 11/5/2024 | Y | EXP | 365 | 10/11/2023 | 11/02/2023 | 23 | 0 | 23 |  |  | 2/2/2024 | Connected |  | N
National Grid | LAWRENCE | 588461 | 01841 | 23 | Solar | 05_14_57L2 | 02/07/2024 | 02/14/2024 | 6 | 4 | 2 | 02/15/2024 | 02/15/2024 | 38 | 25 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2024 |  | 4/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2024 | Connected |  | N
National Grid | WORCESTER | 712233 | 01609 | 17.92 | Solar | 05_14_70L6 | 08/18/2025 | 08/19/2025 | 1 | 0 | 1 | 08/20/2025 | 08/20/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N
National Grid | OXFORD | 175079 | 01540 | 300 | Solar | 05_14_8L2 | 09/30/2013 | 09/30/2013 | 7 | 0 | 7 | 10/10/2013 | 10/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2013 |  | 12/31/2013 | N | EXP | 11 |  |  | 0 | 0 | 0 | 3/17/2014 | 3/17/2014 | 5/27/2014 | Connected |  | N
National Grid | QUINCY | 174939 | 02169 | 83.8 | Solar | 05_07_92W54 | 10/31/2011 | 10/31/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 403041 | 01608 | 5.51 | Solar | 05_01_406L4 | 12/28/2021 | 01/03/2022 | 4 | 0 | 4 | 01/04/2022 | 01/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2022 | 12/28/2021 | 9/6/2023 | Y | EXP | 365 | 06/16/2022 | 07/18/2022 | 33 | 0 | 33 |  |  | 10/27/2022 | Connected |  | N
National Grid | UXBRIDGE | 174561 | 01569 | 150 | Solar | 05_07_1W1 | 10/24/2011 | 10/24/2011 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 175078 | 02019 | 200 | Solar | 05_01_HT55 | 09/24/2013 | 09/24/2013 | 4 | 0 | 4 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2013 |  | 12/5/2016 | N | EXP | 1141 |  |  | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 12/5/2016 | Connected |  | N
National Grid | ESSEX | 293030 | 01929 | 0 | Solar | 05_05_344W4 | 05/21/2020 | 06/12/2020 | 14 | 14 | 0 | 06/15/2020 | 06/15/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2020 | Connected |  | N
National Grid | BROCKTON | 178111 | 02301 | 15 | Solar | 05_12_51T1 | 11/06/2017 | 11/06/2017 | 81 | 80 | 1 | 03/23/2018 | 03/23/2018 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 |  | 11/12/2018 | N | EXP | 182 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 550946 | 01886 | 3.8 | Solar | 05_07_911W13 | 09/06/2023 | 09/08/2023 | 2 | 1 | 1 | 09/11/2023 | 09/11/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 604077 | 01821 | 12.35 | Solar | 05_14_57L2 | 04/18/2024 | 04/29/2024 | 2 | 1 | 1 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 6/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2024 | Connected |  | N
National Grid | LAWRENCE | 733690 | 01841 | 10 | Solar | 05_14_70L6 | 11/13/2025 | 11/14/2025 | 3 | 0 | 3 | 12/03/2025 | 12/03/2025 | 81 | 25 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 176483 | 02375 | 6 | Solar | 05_14_8L2 | 05/23/2016 | 05/23/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/23/2016 | 5/30/2017 | Y | EXP | 358 | 11/28/2016 | 12/14/2016 | 12 | 0 | 12 | 4/20/2017 | 4/20/2017 | 4/26/2017 | Connected |  | N
National Grid | OXFORD | 175768 | 01540 | 1000 | Solar | 05_07_92W54 | 06/06/2014 | 06/06/2014 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/25/2014 | 10/03/2014 | 70 | 68 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2014 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 409267 | 02169 | 0 | Other | 05_01_406L4 | 02/14/2023 |  | 104 | 46 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174802 | 01605 | 155 | Solar | 05_07_1W1 | 08/29/2012 | 08/29/2012 | 6 | 0 | 6 | 09/11/2012 | 09/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2013 |  | 12/17/2012 | N | EXP | 29 |  |  | 0 | 0 | 0 | 1/15/2013 | 1/15/2013 | 4/9/2013 | Connected |  | N
National Grid | BLACKSTONE | 174174 | 01504 | 135 | Solar | 05_01_HT59 | 04/27/2012 | 04/27/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 8/20/2012 | N | EXP | 114 |  |  | 0 | 0 | 0 | 6/12/2015 | 6/12/2015 | 3/2/2013 | Connected |  | N
National Grid | BELLINGHAM | 178350 | 02019 | 24.94 | Solar | 05_05_321W2 | 01/12/2018 | 01/12/2018 | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2018 |  | 1/17/2019 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 7/18/2018 | Connected |  | N
National Grid | MANCHESTER | 307866 | 01944 | 7.6 | Solar | 05_05_344W4 | 09/03/2020 | 09/08/2020 | 1 | 0 | 1 | 09/09/2020 | 09/09/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2020 |  | 9/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 178201 | 02301 | 0 | Solar | 05_12_51T1 | 02/15/2018 | 02/15/2018 | 9 | 9 | 0 | 03/08/2018 | 03/08/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2018 |  | 2/21/2019 | N | EXP | 350 |  |  | 0 | 0 | 0 |  |  | 5/7/2019 | Connected |  | N
National Grid | WESTFORD | 550688 | 01886 | 5 | Solar | 05_07_911W13 | 09/11/2023 | 09/18/2023 | 5 | 0 | 5 | 09/19/2023 | 09/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 609526 | 01821 | 11.5 | Solar | 05_14_57L2 | 05/08/2024 | 06/07/2024 | 3 | 0 | 3 | 06/10/2024 | 06/10/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | LAWRENCE | 733043 | 01841 | 22.42 | Solar | 05_14_70L6 | 11/11/2025 | 11/14/2025 | 3 | 0 | 3 | 11/17/2025 | 11/17/2025 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2026 | Connected |  | N
National Grid | EASTON | 178185 | 02375 | 7.6 | Solar | 05_14_8L2 | 04/13/2018 | 04/13/2018 | 5 | 0 | 5 | 04/23/2018 | 04/23/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/21/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 176155 | 01540 | 490 | Solar | 05_07_92W54 | 02/02/2015 | 02/02/2015 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/19/2015 | 03/27/2015 | 25 | 6 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 471444 | 02169 | 6.38 | Solar | 05_01_406L4 | 11/01/2022 | 11/14/2022 | 8 | 3 | 5 | 11/15/2022 | 11/15/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2022 | 11/01/2022 | 3/30/2024 | Y | EXP | 365 | 02/23/2023 | 03/30/2023 | 36 | 0 | 36 |  |  | 5/1/2023 | Connected |  | N
National Grid | WORCESTER | 176826 | 01605 | 54 | Solar | 05_07_1W1 | 01/18/2016 | 01/18/2016 | 2 | 2 | 0 | 01/21/2016 | 01/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2016 | 01/18/2016 | 1/24/2017 | Y | EXP | 347 |  |  | 0 | 0 | 0 | 10/12/2016 | 10/12/2016 | 10/25/2016 | Connected |  | N
National Grid | BLACKSTONE | 174173 | 01504 | 75 | Solar | 05_01_HT59 | 04/27/2012 | 04/27/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 5/15/2012 | N | EXP | 211 |  |  | 0 | 0 | 0 | 2/6/2013 | 2/6/2013 | 3/2/2013 | Connected |  | N
National Grid | FRANKLIN | 178349 | 02038 | 49.88 | Solar | 05_05_321W2 | 01/12/2018 | 01/12/2018 | 14 | 4 | 10 | 02/02/2018 | 02/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2018 |  | 1/17/2019 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 7/18/2018 | Connected |  | N
National Grid | GLOUCESTER | 313308 | 01930 | 25 | Solar | 05_05_344W4 | 09/17/2020 | 09/23/2020 | 3 | 0 | 3 | 09/24/2020 | 09/24/2020 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2020 | 09/17/2020 | 10/22/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2021 | Connected |  | N
National Grid | BROCKTON | 177849 | 02301 | 166.5 | Solar | 05_07_99W63 | 04/06/2017 | 04/06/2017 | 7 | 7 | 0 | 04/19/2017 | 04/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2017 | 04/06/2017 | 4/12/2018 | Y | EXP | 324 | 05/24/2017 | 06/21/2017 | 19 | 0 | 19 | 12/15/2017 | 12/15/2017 | 12/21/2017 | Connected |  | N
National Grid | WESTFORD | 554323 | 01886 | 3.8 | Solar | 05_07_911W13 | 09/12/2023 | 10/23/2023 | 28 | 25 | 3 | 10/24/2023 | 10/24/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 |  | 11/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 616733 | 01821 | 23 | Solar | 05_14_57L2 | 06/10/2024 | 06/14/2024 | 4 | 3 | 1 | 06/17/2024 | 06/17/2024 | 84 | 65 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 757192 | 01841 | 11.5 | Solar | 05_14_70L8 | 03/23/2026 | 03/25/2026 | 2 | 0 | 2 | 03/26/2026 | 03/26/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | EASTON | 178228 | 02375 | 10.4 | Solar | 05_14_8L2 | 01/03/2018 | 01/03/2018 | 15 | 9 | 6 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2018 |  | 1/10/2019 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  | 11/8/2019 | Connected |  | N
National Grid | HAVERHILL | 176272 | 01832 | 3084 | Solar | 05_07_92W54 | 02/19/2015 | 02/19/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2015 | 03/30/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 | 02/19/2015 | 12/14/2017 | Y | STD | 794 | 05/24/2017 | 02/20/2018 | 179 | 0 | 179 | 11/20/2017 | 11/20/2017 | 12/14/2017 | Connected |  | N
National Grid | QUINCY | 489250 | 02169 | 7.6 | Solar | 05_01_406L4 | 05/01/2023 |  | 53 | 25 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 398156 | 01602 | 500 | Solar | 05_07_1W1 | 03/03/2022 | 04/06/2022 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2022 | 05/05/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 674157 | 01569 | 84.6 | Solar | 05_01_HT6 | 03/11/2025 |  | 99 | 48 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 178541 | 02019 | 6 | Solar | 05_05_321W2 | 01/29/2018 | 01/29/2018 | 6 | 0 | 6 | 02/06/2018 | 02/06/2018 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2018 |  | 2/3/2019 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MANCHESTER | 343803 | 01944 | 0 | Solar | 05_05_344W4 | 02/26/2021 | 03/01/2021 | 1 | 1 | 0 | 03/02/2021 | 03/02/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2021 |  | 7/1/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 4/29/2022 | Connected |  | N
National Grid | BROCKTON | 178160 | 02301 | 230 | Solar | 05_07_99W63 | 12/26/2017 | 12/26/2017 | 13 | 10 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/16/2018 | 01/30/2018 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 | 12/26/2017 | 7/10/2019 | Y | STD | 384 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 554975 | 01886 | 6 | Solar | 05_07_911W13 | 09/29/2023 | 10/03/2023 | 2 | 0 | 2 | 10/04/2023 | 10/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 |  | 11/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2024 | Connected |  | N
National Grid | BILLERICA | 617530 | 01821 | 15.2 | Solar | 05_14_57L2 | 09/18/2024 |  | 29 | 27 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 174143 | 01841 | 2000 | Solar | 05_14_70L8 | 04/17/2012 | 04/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2012 |  | 12/3/2012 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 178295 | 02375 | 15.2 | Solar | 05_14_8L2 | 11/15/2017 | 11/15/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 |  | 11/21/2018 | N | EXP | 153 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 177631 | 01540 | 296 | Solar | 05_07_92W54 | 05/24/2017 | 05/24/2017 | 22 | 22 | 0 | 06/29/2017 | 06/29/2017 | 186 | 8 | 178 | 08/07/2017 | 08/29/2017 | 16 | 1 | 15 |  |  | 0 | 0 | 0 | 08/29/2017 | 16 | 1 | 15 |  |  | 0 | 0 | 0 | 9/20/2017 | 05/24/2017 | 8/30/2018 | Y | EXP | 344 | 02/21/2018 | 04/17/2018 | 27 | 0 | 27 |  |  | 8/16/2018 | Connected |  | N
National Grid | QUINCY | 505438 | 02169 | 15 | Solar | 05_01_406L4 | 03/07/2023 | 03/09/2023 | 2 | 0 | 2 | 03/10/2023 | 03/10/2023 | 117 | 95 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 |  | 9/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | WORCESTER | 618129 | 01602 | 200 | Solar | 05_07_1W1 | 08/05/2024 | 10/25/2024 | 57 | 48 | 9 | 10/28/2024 | 10/28/2024 | 128 | 104 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 9/5/2025 | N | EXP | 21 |  |  | 0 | 0 | 0 |  |  | 8/18/2025 | Connected |  | N
National Grid | UXBRIDGE | 175192 | 01569 | 150 | Natural Gas | 05_01_HT61 | 11/21/2013 | 11/21/2013 | 6 | 0 | 6 | 12/04/2013 | 12/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2013 |  | 3/31/2014 | N | EXP | 91 |  |  | 0 | 0 | 0 | 6/2/2014 | 6/2/2014 | 6/2/2014 | Connected |  | N
National Grid | BELLINGHAM | 184500 | 02019 | 1666 | Solar | 05_05_321W2 | 05/04/2018 | 05/04/2018 | 18 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/01/2018 | 06/28/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 376456 | 02370 | 7.6 | Solar | 05_05_344W4 | 08/17/2021 | 09/20/2021 | 23 | 23 | 0 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 9/19/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 178648 | 02301 | 244 | Solar | 05_07_99W63 | 12/15/2017 | 12/15/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/02/2018 | 01/30/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 | 12/15/2017 | 8/6/2021 | Y | STD | 596 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 566755 | 01886 | 7.6 | Solar | 05_07_911W13 | 11/10/2023 | 11/20/2023 | 7 | 4 | 3 | 11/21/2023 | 11/21/2023 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 629694 | 01876 | 10 | Solar | 05_14_57L2 | 08/02/2024 | 08/26/2024 | 8 | 5 | 3 | 08/27/2024 | 08/27/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 | 08/02/2024 | 9/19/2025 | Y | EXP | 365 | 10/24/2024 | 10/30/2024 | 7 | 0 | 7 |  |  | 12/27/2024 | Connected |  | N
National Grid | LAWRENCE | 174142 | 01841 | 2000 | Solar | 05_14_70L8 | 04/17/2012 | 04/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2012 |  | 12/3/2012 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 190234 | 02379 | 70.2 | Solar | 05_14_8L2 | 08/10/2018 | 08/28/2018 | 11 | 0 | 11 | 08/29/2018 | 08/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 178053 | 01540 | 1128 | Solar | 05_07_92W54 | 06/30/2017 | 06/30/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2017 | 10/26/2017 | 72 | 57 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2018 | 06/30/2017 | 2/12/2021 | Y | STD | 422 | 06/30/2020 | 11/13/2020 | 136 | 5 | 131 | 1/28/2021 | 1/27/2021 | 2/12/2021 | Connected |  | N
National Grid | QUINCY | 536014 | 02169 | 7.6 | Solar | 05_01_406L4 | 06/22/2023 | 08/06/2023 | 4 | 1 | 3 | 05/28/2024 | 05/28/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 | 06/22/2023 | 7/10/2025 | Y | EXP | 365 | 09/11/2024 | 10/10/2024 | 30 | 0 | 30 |  |  | 10/22/2024 | Connected |  | N
National Grid | WORCESTER | 655839 | 01609 | 9.88 | Solar | 05_07_1W1 | 11/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 175436 | 01569 | 150 | Natural Gas | 05_01_HT61 | 11/24/2014 | 11/24/2014 | 5 | 3 | 2 | 12/03/2014 | 12/03/2014 | 0 | 0 | 0 | 09/10/2015 | 03/16/2016 | 127 | 114 | 13 |  |  | 0 | 0 | 0 | 03/16/2016 | 127 | 114 | 13 |  |  | 0 | 0 | 0 | 3/23/2016 |  | 12/31/2016 | N | EXP | 283 |  |  | 0 | 0 | 0 | 4/26/2016 | 4/26/2016 | 5/5/2016 | Connected |  | N
National Grid | BELLINGHAM | 184499 | 02019 | 1666 | Solar | 05_05_321W2 | 04/30/2018 | 04/30/2018 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2018 | 06/27/2018 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 391859 | 02370 | 0 | Other | 05_05_344W4 | 01/04/2022 | 01/20/2022 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2022 | 01/27/2022 | 5 | 0 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 386079 | 02301 | 100 | Solar | 05_07_99W63 | 11/01/2021 | 12/09/2021 | 26 | 17 | 9 | 12/10/2021 | 12/10/2021 | 127 | 105 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 563286 | 01886 | 7.6 | Solar | 05_07_911W13 | 11/07/2023 | 11/09/2023 | 2 | 0 | 2 | 11/13/2023 | 11/13/2023 | 31 | 8 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 | 11/07/2023 | 1/29/2025 | Y | EXP | 365 | 04/23/2024 | 05/09/2024 | 17 | 0 | 17 |  |  | 5/30/2024 | Connected |  | N
National Grid | BILLERICA | 633475 | 01821 | 8.7 | Solar | 05_14_57L2 | 09/20/2024 | 10/22/2024 | 9 | 5 | 4 | 10/23/2024 | 10/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | LAWRENCE | 174575 | 01841 | 2000 | Solar | 05_14_70L8 | 09/01/2011 | 09/01/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 199996 | 02375 | 6 | Solar | 05_14_8L2 | 11/01/2018 | 11/19/2018 | 1 | 0 | 1 | 11/20/2018 | 11/20/2018 | 21 | 14 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 178573 | 01540 | 415 | Solar | 05_07_92W54 | 12/11/2017 | 12/11/2017 | 77 | 57 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/18/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 543392 | 02169 | 6 | Solar | 05_01_406L4 | 08/11/2023 | 08/14/2023 | 1 | 0 | 1 | 08/15/2023 | 08/15/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2023 |  | 10/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/26/2023 | Connected |  | N
National Grid | WORCESTER | 664597 | 01605 | 5.76 | Solar | 05_07_1W1 | 01/08/2025 | 01/24/2025 | 6 | 1 | 5 | 01/27/2025 | 01/27/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | UXBRIDGE | 554489 | 01569 | 3.8 | Solar | 05_09_503L2 | 09/12/2023 | 09/13/2023 | 1 | 0 | 1 | 09/14/2023 | 09/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 | 09/12/2023 | 11/11/2024 | Y | EXP | 365 | 12/27/2023 | 01/18/2024 | 23 | 0 | 23 |  |  | 3/8/2024 | Connected |  | N
National Grid | BELLINGHAM | 184491 | 02019 | 1800 | Solar | 05_05_321W2 | 04/28/2018 | 04/28/2018 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2018 | 06/27/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 425595 | 02370 | 996 | Solar | 05_05_344W4 | 08/31/2022 | 09/20/2022 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2022 | 10/19/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 408872 | 02301 | 0 | Battery Add-On | 05_07_99W63 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 03/02/2022 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 571870 | 01886 | 6 | Solar | 05_07_911W13 | 11/29/2023 | 12/05/2023 | 4 | 3 | 1 | 12/06/2023 | 12/06/2023 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 |  | 4/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2024 | Connected |  | N
National Grid | BILLERICA | 637981 | 01821 | 5.2 | Solar | 05_14_57L2 | 09/05/2024 | 10/01/2024 | 2 | 0 | 2 | 10/02/2024 | 10/02/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 09/05/2024 | 11/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | LAWRENCE | 174574 | 01841 | 999 | Solar | 05_14_70L8 | 09/01/2011 | 09/01/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/01/2011 | 10/31/2012 | Y | STD | 42 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 207111 | 02379 | 7.6 | Solar | 05_14_8L2 | 02/21/2019 | 03/05/2019 | 7 | 0 | 7 | 03/06/2019 | 03/06/2019 | 15 | 8 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 | 02/21/2019 | 7/22/2020 | Y | EXP | 365 | 01/16/2020 | 02/28/2020 | 43 | 0 | 43 |  |  | 6/18/2020 | Connected |  | N
National Grid | OXFORD | 185614 | 01540 | 294 | Solar | 05_07_92W54 | 05/17/2018 | 05/17/2018 | 49 | 35 | 14 | 07/30/2018 | 07/30/2018 | 49 | 25 | 24 | 10/09/2018 | 11/29/2018 | 35 | 17 | 18 |  |  | 0 | 0 | 0 | 11/29/2018 | 35 | 17 | 18 |  |  | 0 | 0 | 0 | 1/2/2019 | 05/17/2018 | 4/19/2021 | Y | EXP | 197 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 579324 | 02169 | 1.45 | Solar | 05_01_406L4 | 02/01/2024 | 04/17/2024 | 27 | 25 | 2 | 04/18/2024 | 04/18/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 | 02/01/2024 | 5/7/2025 | Y | EXP | 365 | 06/05/2024 | 08/29/2024 | 86 | 0 | 86 |  |  | 9/26/2024 | Connected |  | N
National Grid | WORCESTER | 175342 | 01608 | 144 | Solar | 05_07_1W2 | 07/02/2014 | 07/02/2014 | 3 | 0 | 3 | 07/09/2014 | 07/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2014 |  | 11/28/2014 | N | EXP | 113 |  |  | 0 | 0 | 0 | 8/7/2014 | 8/7/2014 | 3/16/2015 | Connected |  | N
National Grid | UXBRIDGE | 648797 | 01569 | 5.76 | Solar | 05_09_503L2 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 252243 | 02019 | 0 | Solar | 05_05_321W2 | 09/05/2019 | 09/17/2019 | 8 | 8 | 0 | 09/18/2019 | 09/18/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 9/4/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2020 | Connected |  | N
National Grid | ROCKLAND | 442113 | 02370 | 240 | Solar | 05_05_344W4 | 07/08/2022 | 07/26/2022 | 12 | 3 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 1/7/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  | 2/24/2026 | Connected |  | N
National Grid | BROCKTON | 422057 | 02301 | 4999.2 | Battery Add-On | 05_07_99W63 | 05/17/2022 |  | 188 | 26 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 582426 | 01886 | 10 | Solar | 05_07_911W13 | 02/01/2024 | 03/07/2024 | 25 | 24 | 1 | 03/08/2024 | 03/08/2024 | 48 | 42 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 651787 | 01821 | 7.6 | Solar | 05_14_57L2 | 11/04/2024 | 01/24/2025 | 5 | 0 | 5 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174565 | 01841 | 4999 | Solar | 05_14_70L8 | 08/05/2011 | 08/05/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 09/21/2012 | 09/21/2012 | 0 | 0 | 0 | 12/12/2012 | 08/05/2011 | 12/1/2014 | Y | STD | 719 | 05/19/2014 | 11/12/2014 | 121 | 0 | 121 | 7/31/2014 | 7/31/2014 | 8/13/2014 | Connected |  | N
National Grid | EASTON | 209338 | 02375 | 11.4 | Solar | 05_14_8L2 | 04/22/2019 | 04/26/2019 | 3 | 0 | 3 | 04/29/2019 | 04/29/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2019 | 04/22/2019 | 7/22/2020 | Y | EXP | 365 | 04/25/2020 | 06/12/2020 | 48 | 0 | 48 |  |  | 7/7/2020 | Connected |  | N
National Grid | OXFORD | 185461 | 01540 | 422 | Solar | 05_07_92W54 | 05/17/2018 | 05/17/2018 | 49 | 30 | 19 | 07/30/2018 | 07/30/2018 | 60 | 25 | 35 | 11/06/2018 | 12/14/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 12/14/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 1/2/2019 | 05/17/2018 | 5/2/2021 | Y | EXP | 197 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 585919 | 02169 | 23.4 | Solar | 05_01_406L4 | 01/31/2024 | 02/23/2024 | 16 | 14 | 2 | 02/26/2024 | 02/26/2024 | 32 | 29 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  | 4/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | N
National Grid | MONSON | 175453 | 01057 | 120 | Solar | 05_07_1W2 | 07/15/2014 | 07/15/2014 | 5 | 0 | 5 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2014 |  | 10/31/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 10/1/2014 | 10/1/2014 | 11/23/2015 | Connected |  | N
National Grid | UXBRIDGE | 655987 | 01569 | 7.6 | Solar | 05_09_503L2 | 11/21/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | FRANKLIN | 266700 | 02038 | 0 | Other | 05_05_321W2 | 09/15/2020 | 10/01/2020 | 12 | 7 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2020 | 10/27/2020 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 | 09/15/2020 | 7/12/2027 | Y | STD | 553 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 472217 | 02370 | 10 | Solar | 05_05_344W4 | 12/21/2022 | 12/22/2022 | 1 | 0 | 1 | 12/23/2022 | 12/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/21/2022 | 12/27/2024 | Y | EXP | 365 | 07/28/2023 | 02/13/2024 | 200 | 3 | 197 |  |  | 4/24/2024 | Connected |  | N
National Grid | BROCKTON | 431370 | 02301 | 450 | Solar | 05_07_99W63 | 05/26/2022 | 06/13/2022 | 11 | 3 | 8 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 594698 | 01886 | 10 | Solar | 05_07_911W13 | 03/05/2024 | 04/25/2024 | 2 | 0 | 2 | 04/26/2024 | 04/26/2024 | 24 | 15 | 9 | 06/26/2024 | 08/23/2024 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 08/23/2024 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 8/26/2024 |  | 3/31/2026 | N | EXP | 365 | 11/08/2024 | 01/28/2026 | 446 | 202 | 244 |  |  | 3/16/2026 | Connected |  | N
National Grid | BILLERICA | 662101 | 01821 | 11.5 | Solar | 05_14_57L2 | 12/20/2024 | 12/31/2024 | 6 | 2 | 4 | 01/02/2025 | 01/02/2025 | 52 | 27 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | LAWRENCE | 175159 | 01841 | 2000 | Solar | 05_14_70L8 | 08/05/2011 | 08/05/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 09/21/2012 | 08/11/2014 | 444 | 0 | 444 | 12/12/2012 | 08/05/2011 | 12/31/2012 | Y | STD | 19 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 212730 | 02375 | 7.6 | Solar | 05_14_8L2 | 03/20/2019 | 03/28/2019 | 5 | 0 | 5 | 03/29/2019 | 03/29/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 | 03/20/2019 | 6/17/2020 | Y | EXP | 365 | 01/16/2020 | 02/07/2020 | 22 | 0 | 22 |  |  | 4/17/2020 | Connected |  | N
National Grid | OXFORD | 186104 | 01540 | 500 | Solar | 05_07_92W54 | 08/29/2018 | 09/28/2018 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2018 | 10/26/2018 | 20 | 1 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2019 |  | 5/15/2020 | N | STD | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 602577 | 02169 | 10 | Solar | 05_01_406L4 | 04/12/2024 | 04/19/2024 | 4 | 0 | 4 | 04/22/2024 | 04/22/2024 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 178325 | 01057 | 6 | Solar | 05_07_1W2 | 03/30/2018 | 03/30/2018 | 7 | 0 | 7 | 04/10/2018 | 04/10/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2018 | 03/30/2018 | 4/4/2019 | Y | EXP | 323 |  |  | 0 | 0 | 0 |  |  | 10/29/2018 | Connected |  | N
National Grid | UXBRIDGE | 661116 | 01569 | 11.5 | Solar | 05_09_503L2 | 12/17/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 5/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | BELLINGHAM | 285198 | 02019 | 10 | Solar | 05_05_321W2 | 03/25/2020 | 03/30/2020 | 2 | 2 | 0 | 03/31/2020 | 03/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2020 |  | 3/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N
National Grid | HINGHAM | 478736 | 02043 | 10 | Solar | 05_05_344W4 | 12/08/2022 | 12/12/2022 | 2 | 0 | 2 | 12/13/2022 | 12/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2023 | 12/08/2022 | 7/12/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2023 | Connected |  | N
National Grid | BROCKTON | 577761 | 02301 | 0 | Other | 05_07_99W63 | 01/04/2024 | 02/21/2024 | 31 | 28 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2024 | 02/28/2024 | 5 | 0 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 602397 | 01886 | 6 | Solar | 05_07_911W13 | 04/10/2024 | 04/22/2024 | 8 | 5 | 3 | 04/23/2024 | 04/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/10/2024 | 6/11/2025 | Y | EXP | 365 | 08/21/2024 | 09/25/2024 | 36 | 0 | 36 |  |  | 10/3/2024 | Connected |  | N
National Grid | BILLERICA | 663185 | 01821 | 5.76 | Solar | 05_14_57L2 | 01/02/2025 | 02/19/2025 | 13 | 9 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | LAWRENCE | 175562 | 01841 | 12 | Solar | 05_14_70L8 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2014 |  | 10/31/2014 | N | EXP | 59 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 5/19/2015 | Connected |  | N
National Grid | EASTON | 212812 | 02375 | 7.6 | Solar | 05_14_8L2 | 03/23/2019 | 03/25/2019 | 0 | 0 | 0 | 03/26/2019 | 03/26/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2019 |  | 8/30/2019 | N | EXP | 155 |  |  | 0 | 0 | 0 |  |  | 8/16/2019 | Connected |  | N
National Grid | OXFORD | 204400 | 01540 | 480 | Solar | 05_07_92W54 | 12/26/2018 | 01/17/2019 | 14 | 5 | 9 | 01/18/2019 | 01/18/2019 | 19 | 2 | 17 | 04/09/2019 | 04/29/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 04/29/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 5/9/2019 | 12/26/2018 | 2/19/2021 | Y | EXP | 398 | 12/22/2020 | 12/21/2020 | 0 | 0 | 0 |  |  | 2/17/2021 | Connected |  | N
National Grid | QUINCY | 605711 | 02169 | 15.2 | Solar | 05_01_406L4 | 05/03/2024 | 05/09/2024 | 4 | 3 | 1 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  | 6/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2024 | Connected |  | N
National Grid | MONSON | 178365 | 01057 | 7.6 | Solar | 05_07_1W2 | 03/30/2018 | 03/30/2018 | 4 | 0 | 4 | 04/06/2018 | 04/06/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 |  | 4/7/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 667744 | 01569 | 7.6 | Solar | 05_09_503L2 | 01/24/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | BELLINGHAM | 340617 | 02019 | 10 | Solar | 05_05_321W2 | 02/04/2021 | 03/26/2021 | 35 | 34 | 1 | 03/29/2021 | 03/29/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  | 3/25/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKLAND | 508761 | 02370 | 5.8 | Solar | 05_05_344W4 | 03/14/2023 | 03/14/2023 | 0 | 0 | 0 | 03/15/2023 | 03/15/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2023 | 03/14/2023 | 9/10/2024 | Y | EXP | 365 | 06/30/2023 | 09/08/2023 | 71 | 0 | 71 |  |  | 9/14/2023 | Connected |  | N
National Grid | BROCKTON | 691739 | 02301 | 7.6 | Solar | 05_07_99W63 | 05/26/2025 | 07/01/2025 | 4 | 0 | 4 | 07/02/2025 | 07/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 602146 | 01886 | 3.8 | Solar | 05_07_911W13 | 04/05/2024 | 04/25/2024 | 1 | 0 | 1 | 04/26/2024 | 04/26/2024 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 664396 | 01821 | 7.6 | Solar | 05_14_57L2 | 01/08/2025 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176311 | 01841 | 5 | Solar | 05_14_70L8 | 02/25/2015 | 02/25/2015 | 8 | 5 | 3 | 03/10/2015 | 03/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 7/31/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 6/11/2015 | 6/11/2015 | 10/2/2015 | Connected |  | N
National Grid | EASTON | 454366 | 02375 | 10 | Solar | 05_09_604W3 | 09/06/2022 | 09/12/2022 | 4 | 1 | 3 | 09/13/2022 | 09/13/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 |  | 9/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2023 | Connected |  | N
National Grid | OXFORD | 346957 | 01540 | 499 | Solar | 05_07_92W54 | 07/14/2021 | 08/05/2021 | 16 | 9 | 7 |  |  | 73 | 37 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 07/14/2021 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 639121 | 02169 | 10 | Solar | 05_01_406L4 | 09/10/2024 | 09/25/2024 | 4 | 0 | 4 | 09/26/2024 | 09/26/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 195989 | 01057 | 10 | Solar | 05_07_1W2 | 11/02/2018 | 02/01/2019 | 59 | 54 | 5 | 02/04/2019 | 02/04/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2019 | 11/02/2018 | 10/8/2019 | Y | EXP | 365 | 04/10/2019 | 05/31/2019 | 51 | 0 | 51 |  |  | 10/8/2019 | Connected |  | N
National Grid | UXBRIDGE | 671245 | 01569 | 10 | Solar | 05_09_503L2 | 02/10/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 342437 | 02019 | 0 | Solar | 05_05_321W2 | 02/26/2021 | 03/01/2021 | 1 | 1 | 0 | 03/02/2021 | 03/02/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2021 |  | 5/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2022 | Connected |  | N
National Grid | ROCKLAND | 516130 | 02370 | 5 | Solar | 05_05_344W4 | 04/19/2023 | 04/25/2023 | 5 | 2 | 3 | 04/26/2023 | 04/26/2023 | 65 | 42 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 04/19/2023 | 9/21/2024 | Y | EXP | 365 | 02/29/2024 | 03/26/2024 | 27 | 0 | 27 |  |  | 3/28/2024 | Connected |  | N
National Grid | BROCKTON | 693329 | 02301 | 200 | Solar | 05_07_99W63 | 05/29/2025 | 08/25/2025 | 58 | 48 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 604736 | 01886 | 3.84 | Solar | 05_07_911W13 | 04/17/2024 | 05/01/2024 | 3 | 0 | 3 | 05/02/2024 | 05/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 |  | 5/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | BILLERICA | 666605 | 01821 | 17.2 | Solar | 05_14_57L2 | 01/17/2025 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | METHUEN | 641458 | 01844 | 7.98 | Solar | 05_12_16W2 | 09/19/2024 | 09/27/2024 | 4 | 0 | 4 | 09/30/2024 | 09/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/19/2024 | 11/13/2025 | Y | EXP | 365 | 02/28/2025 | 02/27/2025 | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 479620 | 02379 | 10 | Solar | 05_09_604W3 | 12/08/2022 | 12/12/2022 | 2 | 0 | 2 | 12/13/2022 | 12/13/2022 | 63 | 38 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 351232 | 01540 | 8.7 | Solar | 05_07_92W54 | 04/07/2021 | 04/22/2021 | 9 | 7 | 2 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 4/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2021 | Connected |  | N
National Grid | QUINCY | 176930 | 02169 | 360 | Solar | 05_01_207W3 | 01/27/2016 | 01/27/2016 | 2 | 2 | 0 | 02/01/2016 | 02/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2016 | 01/27/2016 | 4/14/2017 | Y | EXP | 350 | 12/08/2016 | 03/21/2017 | 69 | 0 | 69 | 4/7/2017 | 4/7/2017 | 4/12/2017 | Connected |  | N
National Grid | MONSON | 199529 | 01057 | 7.6 | Solar | 05_07_1W2 | 11/05/2018 | 11/20/2018 | 9 | 7 | 2 | 11/21/2018 | 11/21/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2018 | 11/05/2018 | 11/15/2019 | Y | EXP | 333 |  |  | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | UXBRIDGE | 683451 | 01569 | 3.8 | Solar | 05_09_503L2 | 04/15/2025 |  | 113 | 25 | 88 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 402695 | 02019 | 0 | Solar | 05_05_321W2 | 12/21/2021 | 01/12/2022 | 16 | 15 | 1 | 01/13/2022 | 01/13/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  | 2/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2022 | Connected |  | N
National Grid | ROCKLAND | 516573 | 02370 | 6 | Solar | 05_05_344W4 | 04/20/2023 | 04/21/2023 | 1 | 0 | 1 | 04/24/2023 | 04/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 721206 | 02301 | 0 | Solar | 05_07_9W1 | 09/25/2025 | 10/07/2025 | 8 | 6 | 2 | 10/08/2025 | 10/08/2025 | 53 | 32 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 1/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 619935 | 01886 | 20 | Solar | 05_07_911W13 | 06/24/2024 | 06/26/2024 | 2 | 0 | 2 | 06/27/2024 | 06/27/2024 | 109 | 88 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2025 | Connected |  | N
National Grid | BILLERICA | 667168 | 01821 | 10 | Solar | 05_14_57L2 | 01/22/2025 | 02/13/2025 | 2 | 0 | 2 | 02/14/2025 | 02/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/28/2025 | Connected |  | N
National Grid | NEW BRAINTREE | 676976 | 01531 | 999.9 | Solar | 05_12_16W3 | 04/08/2025 | 06/10/2025 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | EASTON | 480402 | 02356 | 7.6 | Solar | 05_09_604W3 | 11/28/2022 | 12/05/2022 | 6 | 5 | 1 | 12/06/2022 | 12/06/2022 | 58 | 38 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  | 3/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 394878 | 01540 | 9.28 | Solar | 05_07_92W54 | 11/19/2021 | 12/21/2021 | 22 | 19 | 3 | 12/22/2021 | 12/22/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  | 2/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2022 | Connected |  | N
National Grid | QUINCY | 177185 | 02169 | 225 | Solar | 05_01_207W3 | 08/12/2016 | 08/12/2016 | 2 | 2 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2016 |  | 11/20/2017 | N | EXP | 433 |  |  | 0 | 0 | 0 | 9/13/2017 | 9/13/2017 | 9/13/2017 | Connected |  | N
National Grid | MONSON | 254182 | 01057 | 7.6 | Solar | 05_07_1W2 | 09/23/2019 | 10/01/2019 | 5 | 4 | 1 | 10/02/2019 | 10/02/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2019 | 09/23/2019 | 11/6/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2020 | Connected |  | N
National Grid | UXBRIDGE | 699724 | 01569 | 19 | Solar | 05_09_503L2 | 06/19/2025 | 06/23/2025 | 2 | 0 | 2 | 06/24/2025 | 06/24/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N
National Grid | BELLINGHAM | 408025 | 02019 | 7.6 | Solar | 05_05_321W2 | 01/25/2022 | 02/01/2022 | 4 | 4 | 0 | 02/02/2022 | 02/02/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  | 3/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2022 | Connected |  | N
National Grid | ROCKLAND | 521532 | 02370 | 7.6 | Solar | 05_05_344W4 | 05/02/2023 | 05/04/2023 | 2 | 0 | 2 | 05/05/2023 | 05/05/2023 | 104 | 76 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 725210 | 02301 | 18.24 | Solar | 05_07_9W1 | 12/09/2025 | 12/29/2025 | 12 | 11 | 1 | 12/30/2025 | 12/30/2025 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2026 |  | 3/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 641173 | 01886 | 11.4 | Solar | 05_07_911W13 | 09/18/2024 | 10/09/2024 | 1 | 0 | 1 | 10/10/2024 | 10/10/2024 | 74 | 60 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 667573 | 02149 | 11.5 | Solar | 05_14_57L2 | 02/03/2025 | 02/06/2025 | 3 | 0 | 3 | 02/07/2025 | 02/07/2025 | 91 | 69 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | NEW BRAINTREE | 705094 | 01531 | 300 | Solar | 05_12_16W3 | 08/18/2025 | 11/10/2025 | 58 | 51 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 01/05/2026 | 36 | 19 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | EASTON | 492334 | 02375 | 2000 | Solar | 05_09_604W3 | 03/08/2023 | 03/22/2023 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2023 | 05/16/2023 | 39 | 24 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 471914 | 01453 | 10 | Solar | 05_07_92W54 | 11/21/2022 | 12/01/2022 | 8 | 6 | 2 | 12/02/2022 | 12/02/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 | 11/21/2022 | 4/18/2024 | Y | EXP | 365 | 03/29/2023 | 03/28/2023 | 0 | 0 | 0 |  |  | 8/19/2023 | Connected |  | Y
National Grid | QUINCY | 178359 | 02169 | 17.28 | Solar | 05_01_207W3 | 03/01/2018 | 03/01/2018 | 10 | 0 | 10 | 04/27/2018 | 04/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 3/7/2019 | N | EXP | 234 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 309572 | 01057 | 6.96 | Solar | 05_07_1W2 | 09/28/2020 | 10/05/2020 | 5 | 3 | 2 | 10/06/2020 | 10/06/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 | 09/28/2020 | 11/3/2021 | Y | EXP | 365 | 01/13/2021 | 02/24/2021 | 41 | 0 | 41 |  |  | 3/10/2021 | Connected |  | N
National Grid | UXBRIDGE | 745113 | 01569 | 13.36 | Solar | 05_09_503L4 | 01/13/2026 | 01/26/2026 | 4 | 0 | 4 | 02/18/2026 | 02/18/2026 | 18 | 0 | 18 | 03/23/2026 | 03/27/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 03/27/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 4/1/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BELLINGHAM | 425379 | 02019 | 10 | Solar | 05_05_321W2 | 04/21/2022 | 05/31/2022 | 3 | 0 | 3 | 06/01/2022 | 06/01/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2022 | 04/21/2022 | 11/2/2023 | Y | EXP | 365 | 09/27/2022 | 10/27/2022 | 31 | 0 | 31 |  |  | 11/30/2022 | Connected |  | N
National Grid | WEYMOUTH | 556593 | 02189 | 6 | Solar | 05_05_344W4 | 01/05/2024 | 01/16/2024 | 6 | 5 | 1 | 01/17/2024 | 01/17/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2024 | 01/05/2024 | 2/14/2025 | Y | EXP | 365 | 06/12/2024 | 07/17/2024 | 36 | 0 | 36 |  |  | 8/20/2024 | Connected |  | N
National Grid | BROCKTON | 751369 | 02301 | 15.2 | Solar | 05_07_9W1 | 02/23/2026 | 03/16/2026 | 13 | 9 | 4 | 03/17/2026 | 03/17/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTFORD | 651633 | 01886 | 3.8 | Solar | 05_07_911W13 | 11/13/2024 | 12/02/2024 | 3 | 0 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/13/2024 | 2/5/2026 | Y | EXP | 365 | 04/15/2025 | 04/16/2025 | 2 | 0 | 2 |  |  | 7/18/2025 | Connected |  | N
National Grid | SAUGUS | 680865 | 01906 | 12.92 | Solar | 05_14_57L2 | 03/31/2025 | 05/06/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 176460 | 01535 | 56 | Solar | 05_12_16W3 | 02/04/2016 | 02/04/2016 | 1 | 1 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2016 |  | 2/13/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/22/2016 | 11/22/2016 | Connected |  | N
National Grid | EASTON | 669890 | 02356 | 5.76 | Solar | 05_09_604W3 | 02/04/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N
National Grid | LEOMINSTER | 485460 | 01453 | 0 | Solar | 05_07_92W54 | 12/14/2022 |  | 112 | 71 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 185527 | 02169 | 4950 | Solar | 05_01_207W3 | 05/21/2018 | 06/19/2018 | 6 | 0 | 6 |  |  | 30 | 5 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2019 | 05/21/2018 | 4/30/2021 | Y | STD | 726 |  |  | 0 | 0 | 0 |  |  | 4/7/2021 | Connected |  | N
National Grid | MONSON | 317594 | 01057 | 10 | Solar | 05_07_1W2 | 10/06/2020 | 10/09/2020 | 2 | 0 | 2 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2021 | Connected |  | N
National Grid | UXBRIDGE | 754816 | 01569 | 11.5 | Solar | 05_09_503L4 | 03/05/2026 | 03/10/2026 | 2 | 0 | 2 | 03/25/2026 | 03/25/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BELLINGHAM | 475763 | 02019 | 6.96 | Solar | 05_05_321W2 | 11/29/2022 | 12/06/2022 | 5 | 0 | 5 | 12/07/2022 | 12/07/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 |  | 2/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2023 | Connected |  | Y
National Grid | WEYMOUTH | 558155 | 02189 | 7.6 | Solar | 05_05_344W4 | 10/18/2023 | 10/23/2023 | 4 | 1 | 3 | 10/24/2023 | 10/24/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 10/18/2023 | 12/21/2024 | Y | EXP | 365 | 02/06/2024 | 05/14/2024 | 99 | 0 | 99 |  |  | 5/31/2024 | Connected |  | N
National Grid | BROCKTON | 614112 | 02301 | 11.5 | Battery Add-On | 05_07_9W1 | 05/29/2024 | 06/04/2024 | 5 | 4 | 1 | 06/05/2024 | 06/05/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2024 | 05/29/2024 | 7/2/2025 | Y | EXP | 365 | 07/24/2024 | 07/24/2024 | 1 | 0 | 1 |  |  | 8/28/2024 | Connected |  | N
National Grid | WESTFORD | 651979 | 01886 | 3.8 | Solar | 05_07_911W13 | 11/08/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 681569 | 02148 | 15.2 | Solar | 05_14_57L2 | 04/01/2025 | 04/07/2025 | 4 | 0 | 4 | 04/08/2025 | 04/08/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 | 04/01/2025 | 5/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | NEW BRAINTREE | 178582 | 01531 | 37.8 | Solar | 05_12_16W3 | 01/31/2018 | 01/31/2018 | 20 | 0 | 20 | 04/13/2018 | 04/13/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 2/6/2019 | N | EXP | 280 |  |  | 0 | 0 | 0 |  |  | 9/5/2018 | Connected |  | N
National Grid | EASTON | 670324 | 02375 | 17.225 | Solar | 05_09_604W3 | 03/11/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 487262 | 01453 | 15.2 | Solar | 05_07_92W54 | 12/28/2022 | 01/04/2023 | 5 | 1 | 4 | 01/05/2023 | 01/05/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2023 |  | 2/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2023 | Connected |  | N
National Grid | QUINCY | 195313 | 02169 | 995 | Solar | 05_01_207W3 | 05/22/2020 | 06/16/2020 | 15 | 11 | 4 |  |  | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 405421 | 01010 | 4.64 | Solar | 05_07_1W2 | 03/01/2022 | 03/02/2022 | 1 | 0 | 1 | 03/03/2022 | 03/03/2022 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 174449 | 01569 | 1000 | Solar | 05_09_503L4 | 07/11/2012 | 07/11/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/24/2012 | 10/16/2012 | 58 | 0 | 58 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 490668 | 02019 | 22.8 | Solar | 05_05_321W2 | 01/12/2023 | 01/19/2023 | 4 | 2 | 2 | 01/20/2023 | 01/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 2/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2023 | Connected |  | N
National Grid | WEYMOUTH | 558058 | 02189 | 6 | Solar | 05_05_344W4 | 09/29/2023 | 10/05/2023 | 4 | 0 | 4 | 10/06/2023 | 10/06/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2023 |  | 11/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | BROCKTON | 620078 | 02301 | 7.6 | Solar | 05_07_9W1 | 06/25/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 | 06/25/2024 | 8/15/2025 | Y | EXP | 365 | 02/07/2025 | 02/06/2025 | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | WESTFORD | 652437 | 01886 | 5.51 | Solar | 05_07_911W13 | 11/06/2024 | 12/06/2024 | 11 | 5 | 6 | 12/09/2024 | 12/09/2024 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/06/2024 | 2/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | MALDEN | 688631 | 02148 | 12.92 | Solar | 05_14_57L2 | 05/01/2025 | 05/16/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | BARRE | 215396 | 01005 | 5 | Solar | 05_12_16W3 | 04/02/2019 | 04/09/2019 | 4 | 0 | 4 | 04/10/2019 | 04/10/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2019 | 04/02/2019 | 2/17/2020 | Y | EXP | 365 | 01/30/2020 | 01/29/2020 | 0 | 0 | 0 |  |  | 2/19/2020 | Connected |  | N
National Grid | EASTON | 694159 | 02375 | 20 | Solar | 05_09_604W3 | 05/29/2025 | 06/04/2025 | 4 | 0 | 4 | 06/05/2025 | 06/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2025 | 05/29/2025 | 7/11/2026 | Y | EXP | 365 | 11/14/2025 | 12/02/2025 | 19 | 0 | 19 |  |  | 12/27/2025 | Connected |  | N
National Grid | LANCASTER | 494331 | 01523 | 25 | Solar | 05_07_92W54 | 01/23/2023 | 01/24/2023 | 1 | 0 | 1 | 01/25/2023 | 01/25/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2023 | Connected |  | N
National Grid | QUINCY | 203373 | 02169 | 19.52 | Solar | 05_01_207W3 | 12/10/2018 | 12/31/2018 | 13 | 5 | 8 | 01/02/2019 | 01/02/2019 | 28 | 23 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 422902 | 01069 | 0 | Solar | 05_07_1W2 | 04/08/2022 | 04/11/2022 | 1 | 0 | 1 | 04/12/2022 | 04/12/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2022 |  | 6/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2023 | Connected |  | N
National Grid | DOUGLAS | 218392 | 01516 | 5 | Solar | 05_12_16W3 | 04/18/2019 | 04/26/2019 | 6 | 5 | 1 | 04/29/2019 | 04/29/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2019 | 04/18/2019 | 4/24/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2020 | Connected |  | N
National Grid | BELLINGHAM | 699206 | 02019 | 11.4 | Solar | 05_09_604W3 | 06/19/2025 | 07/08/2025 | 13 | 12 | 1 | 07/31/2025 | 07/31/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 525072 | 02189 | 10 | Solar | 05_07_92W54 | 05/09/2023 | 05/11/2023 | 2 | 0 | 2 | 05/12/2023 | 05/12/2023 | 49 | 27 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 11/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2023 | Connected |  | N
National Grid | BROCKTON | 330998 | 02301 | 10 | Solar | 05_01_207W3 | 12/10/2020 | 12/14/2020 | 1 | 0 | 1 | 12/15/2020 | 12/15/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 468425 | 01886 | 9.8 | Solar | 05_07_1W2 | 10/20/2022 | 10/24/2022 | 2 | 0 | 2 | 10/25/2022 | 10/25/2022 | 180 | 25 | 155 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 217215 | 02148 | 3 | Solar | 05_12_16W3 | 04/09/2019 | 04/17/2019 | 5 | 0 | 5 | 04/18/2019 | 04/18/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2019 | 04/09/2019 | 4/2/2020 | Y | EXP | 365 | 02/19/2020 | 02/26/2020 | 7 | 0 | 7 |  |  | 3/12/2020 | Connected |  | N
National Grid | NORTH BROOKFIELD | 334194 | 01535 | 0 | Other | 05_09_604W4 | 04/06/2021 | 04/30/2021 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | EASTON | 590129 | 02375 | 10 | Solar | 05_07_92W54 | 02/15/2024 | 02/20/2024 | 2 | 0 | 2 | 02/21/2024 | 02/21/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/15/2024 | 3/8/2025 | Y | EXP | 365 | 07/17/2024 | 09/04/2024 | 50 | 0 | 50 |  |  | 9/11/2024 | Connected |  | N
National Grid | LEOMINSTER | 348269 | 01453 | 400 | Solar | 05_01_207W3 | 05/14/2021 |  | 373 | 363 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 477496 | 02169 | 2.792 | Solar | 05_07_1W2 | 11/18/2022 | 11/23/2022 | 3 | 0 | 3 | 11/25/2022 | 11/25/2022 | 241 | 222 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIMFIELD | 233774 | 01010 | 3.8 | Solar | 05_12_16W3 | 06/19/2019 | 07/09/2019 | 13 | 13 | 0 | 07/10/2019 | 07/10/2019 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2019 |  | 6/19/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 669274 | 01569 | 4316 | Solar | 05_09_604W4 | 02/21/2025 | 03/17/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2025 | 04/14/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BELLINGHAM | 606070 | 02019 | 10 | Solar | 05_07_92W54 | 04/23/2024 | 05/07/2024 | 8 | 6 | 2 | 05/08/2024 | 05/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 | 04/23/2024 | 9/28/2025 | Y | EXP | 365 | 08/01/2024 | 09/11/2024 | 42 | 0 | 42 |  |  | 1/29/2025 | Connected |  | N
National Grid | WEYMOUTH | 426071 | 02189 | 15.2 | Solar | 05_01_207W3 | 04/26/2022 | 04/27/2022 | 1 | 0 | 1 | 04/28/2022 | 04/28/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2022 | 04/26/2022 | 10/20/2023 | Y | EXP | 365 | 09/30/2022 | 10/18/2022 | 19 | 0 | 19 |  |  | 5/4/2023 | Connected |  | Y
National Grid | BROCKTON | 489308 | 02301 | 4.35 | Solar | 05_07_1W2 | 02/21/2023 | 02/21/2023 | 8 | 0 | 8 | 02/22/2023 | 02/22/2023 | 239 | 213 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 306220 | 01886 | 10 | Solar | 05_12_16W3 | 08/11/2020 | 08/13/2020 | 1 | 0 | 1 | 08/14/2020 | 08/14/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2020 | Connected |  | N
National Grid | SAUGUS | 715130 | 01906 | 5.76 | Solar | 05_09_604W4 | 08/27/2025 | 09/23/2025 | 3 | 0 | 3 | 11/04/2025 | 11/04/2025 | 44 | 24 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 | 08/27/2025 | 1/20/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTH BROOKFIELD | 606788 | 01535 | 0 | Battery Add-On | 05_07_92W54 | 04/25/2024 | 04/30/2024 | 3 | 0 | 3 | 05/01/2024 | 05/01/2024 | 37 | 23 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2024 |  | 7/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | EASTON | 435106 | 02375 | 0 | Other | 05_01_207W3 | 07/01/2022 | 10/24/2022 | 78 | 68 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2022 | 11/17/2022 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 493396 | 01453 | 7.6 | Solar | 05_07_1W2 | 01/23/2023 | 01/25/2023 | 2 | 0 | 2 | 01/26/2023 | 01/26/2023 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 | 01/23/2023 | 7/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2023 | Connected |  | N
National Grid | QUINCY | 405846 | 02169 | 0 | Battery Add-On | 05_12_16W3 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 03/04/2022 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 740862 | 01906 | 5.76 | Solar | 05_09_604W4 | 12/17/2025 | 12/22/2025 | 3 | 0 | 3 | 12/23/2025 | 12/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTH BROOKFIELD | 618835 | 01535 | 7.6 | Solar | 05_07_92W54 | 06/18/2024 | 07/03/2024 | 1 | 0 | 1 | 07/05/2024 | 07/05/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2024 | Connected |  | N
National Grid | EASTON | 439256 | 02375 | 4.64 | Solar | 05_01_207W3 | 06/26/2022 | 07/21/2022 | 18 | 17 | 1 | 07/22/2022 | 07/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 | 06/26/2022 | 8/19/2023 | Y | EXP | 365 | 09/21/2022 | 10/11/2022 | 21 | 0 | 21 |  |  | 5/5/2023 | Connected |  | N
National Grid | LEOMINSTER | 504369 | 01453 | 4.64 | Solar | 05_07_1W2 | 03/16/2023 | 03/22/2023 | 5 | 2 | 3 | 03/23/2023 | 03/23/2023 | 22 | 0 | 22 | 06/02/2023 | 07/12/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 07/12/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 6/29/2023 |  | 9/6/2024 | N | EXP | 365 | 07/06/2023 | 09/01/2023 | 58 | 0 | 58 |  |  | 9/22/2023 | Connected |  | N
National Grid | QUINCY | 434702 | 02169 | 0 | Other | 05_12_16W3 | 07/12/2022 | 07/12/2022 | 67 | 58 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/12/2023 | 02/24/2023 | 30 | 10 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 745132 | 01906 | 5.76 | Solar | 05_09_604W4 | 01/13/2026 | 01/15/2026 | 3 | 0 | 3 | 02/03/2026 | 02/03/2026 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2026 |  | 3/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BARRE | 626173 | 01005 | 1772 | Solar | 05_07_92W54 | 12/20/2024 | 02/18/2025 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/19/2025 | 03/18/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 519207 | 02356 | 10 | Solar | 05_01_207W3 | 05/03/2023 | 05/04/2023 | 1 | 0 | 1 | 05/05/2023 | 05/05/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 | 05/03/2023 | 6/15/2024 | Y | EXP | 365 | 08/26/2023 | 10/19/2023 | 55 | 0 | 55 |  |  | 10/28/2023 | Connected |  | N
National Grid | LEOMINSTER | 559804 | 01453 | 3.8 | Solar | 05_07_1W2 | 10/26/2023 |  | 15 | 13 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 750899 | 02169 | 5.76 | Solar | 05_09_604W4 | 02/12/2026 | 02/13/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SAUGUS | 632417 | 01906 | 10 | Solar | 05_07_92W54 | 08/13/2024 | 08/15/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 | 08/13/2024 | 1/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2025 | Connected |  | Y
National Grid | BARRE | 543114 | 01005 | 7.6 | Solar | 05_01_207W3 | 08/01/2023 | 08/02/2023 | 1 | 0 | 1 | 08/03/2023 | 08/03/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2023 |  | 9/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2023 | Connected |  | N
National Grid | EASTON | 571106 | 02375 | 3.8 | Solar | 05_07_1W2 | 12/01/2023 | 02/27/2024 | 58 | 58 | 0 | 02/28/2024 | 02/28/2024 | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 437637 | 01453 | 350 | Solar | 05_12_16W3 | 09/01/2022 | 09/23/2022 | 15 | 5 | 10 |  |  | 68 | 47 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 09/01/2022 | 8/3/2025 | Y | STD | 133 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 174209 | 02169 | 500 | Solar | 05_09_604W4 | 02/27/2012 | 02/27/2012 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 642648 | 02148 | 3.8 | Solar | 05_07_92W54 | 09/24/2024 | 10/29/2024 | 6 | 4 | 2 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 568532 | 01005 | 6.96 | Solar | 05_01_207W3 | 11/15/2023 | 11/21/2023 | 5 | 3 | 2 | 11/22/2023 | 11/22/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 | 11/15/2023 | 6/30/2025 | Y | EXP | 365 | 01/30/2024 | 02/16/2024 | 18 | 0 | 18 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 586029 | 02375 | 3.19 | Solar | 05_07_1W2 | 02/06/2024 | 02/09/2024 | 3 | 0 | 3 | 02/12/2024 | 02/12/2024 | 171 | 148 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 576689 | 01453 | 0 | Battery Add-On | 05_12_16W3 | 12/08/2023 | 12/19/2023 | 7 | 6 | 1 | 12/20/2023 | 12/20/2023 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | QUINCY | 174323 | 02169 | 1000 | Solar | 05_09_604W4 | 01/13/2012 | 01/13/2012 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/8/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 658372 | 02148 | 2423 | Solar | 05_07_92W54 | 03/04/2025 | 03/26/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2025 | 04/24/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 605468 | 01005 | 11.4 | Solar | 05_01_207W3 | 04/24/2024 | 04/30/2024 | 2 | 0 | 2 | 05/01/2024 | 05/01/2024 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 637734 | 02356 | 2.32 | Solar | 05_07_1W2 | 10/09/2024 | 10/31/2024 | 6 | 2 | 4 | 11/01/2024 | 11/01/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/09/2024 | 1/7/2026 | Y | EXP | 365 | 04/15/2025 | 10/10/2025 | 179 | 0 | 179 |  |  | 10/17/2025 | Connected |  | N
National Grid | LEOMINSTER | 720512 | 01453 | 11.4 | Solar | 05_12_16W3 | 01/12/2026 | 01/13/2026 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 174603 | 02169 | 15 | Solar | 05_09_604W4 | 09/07/2011 | 09/07/2011 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2012 |  | 4/19/2012 | N | EXP | 48 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 4/19/2012 | Connected |  | N
National Grid | SAUGUS | 679507 | 01906 | 15.2 | Solar | 05_07_92W54 | 03/25/2025 | 03/26/2025 | 1 | 0 | 1 | 03/27/2025 | 03/27/2025 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 | 03/25/2025 | 5/20/2026 | Y | EXP | 365 | 09/09/2025 | 09/23/2025 | 15 | 0 | 15 |  |  | 9/23/2025 | Connected |  | N
National Grid | BARRE | 620474 | 01005 | 3.8 | Solar | 05_01_207W3 | 06/25/2024 | 07/19/2024 | 5 | 4 | 1 | 07/22/2024 | 07/22/2024 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 06/25/2024 | 10/4/2025 | Y | EXP | 365 | 12/20/2024 | 01/15/2025 | 27 | 0 | 27 |  |  | 2/4/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 639649 | 02379 | 5.76 | Solar | 05_07_1W2 | 09/12/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 | 09/12/2024 | 10/8/2025 | Y | EXP | 365 | 11/21/2024 | 01/20/2025 | 61 | 0 | 61 |  |  | 1/23/2025 | Connected |  | N
National Grid | LEOMINSTER | 673208 | 01453 | 500 | Solar | 05_12_16W4 | 05/27/2025 | 06/26/2025 | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2025 | 07/21/2025 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | QUINCY | 175214 | 02169 | 960 | Solar | 05_09_604W4 | 11/03/2014 | 11/03/2014 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2014 | 12/08/2014 | 14 | 0 | 14 |  | 0 | 0 | 0 | 03/18/2017 | 02/14/2017 | 0 | 0 | 0 | 5/9/2017 | 11/03/2014 | 9/27/2018 | Y | STD | 506 |  |  | 0 | 0 | 0 |  |  | 9/17/2018 | Connected |  | N
National Grid | SAUGUS | 701340 | 01906 | 15.2 | Solar | 05_07_92W54 | 06/26/2025 | 06/30/2025 | 2 | 0 | 2 | 07/01/2025 | 07/01/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 7/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | HUBBARDSTON | 644944 | 01452 | 3.8 | Solar | 05_01_207W3 | 10/03/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/03/2024 | 3/20/2026 | Y | EXP | 365 | 02/28/2025 | 12/02/2025 | 278 | 111 | 167 |  |  | 12/3/2025 | Connected |  | N
National Grid | EASTON | 655173 | 02375 | 7.6 | Solar | 05_07_1W2 | 11/19/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | LEOMINSTER | 729210 | 01453 | 200 | Solar | 05_12_16W4 | 10/30/2025 | 12/04/2025 | 23 | 17 | 6 | 12/05/2025 | 12/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  | 7/14/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | QUINCY | 175217 | 02169 | 480 | Solar | 05_09_604W4 | 11/03/2014 | 11/03/2014 | 8 | 5 | 3 | 11/17/2014 | 11/17/2014 | 131 | 0 | 131 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 750520 | 02148 | 23 | Solar | 05_07_92W54 | 02/11/2026 | 02/18/2026 | 4 | 0 | 4 | 02/19/2026 | 02/19/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 652489 | 01452 | 0 | Solar | 05_01_207W3 | 11/06/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 50 | 26 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | EASTON | 655168 | 02356 | 5.76 | Solar | 05_07_1W2 | 11/19/2024 | 02/11/2025 | 36 | 33 | 3 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 175479 | 01453 | 240.8 | Solar | 05_12_16W4 | 03/13/2014 | 03/13/2014 | 10 | 5 | 5 | 03/31/2014 | 03/31/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2014 | 03/13/2014 | 8/29/2014 | Y | EXP | 128 | 08/26/2014 | 08/26/2014 | 0 | 0 | 0 | 12/12/2014 | 12/12/2014 | 1/2/2015 | Connected |  | N
National Grid | QUINCY | 175544 | 02189 | 1000 | Solar | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2015 | 12/05/2014 | 3/31/2018 | Y | STD | 830 | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 | 2/21/2018 | 2/21/2018 | 3/6/2018 | Connected |  | N
National Grid | MALDEN | 735708 | 02148 | 15.76 | Solar | 05_07_92W78 | 11/21/2025 | 11/24/2025 | 1 | 0 | 1 | 01/12/2026 | 01/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HUBBARDSTON | 653697 | 01452 | 7.6 | Solar | 05_01_207W3 | 11/15/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/15/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 657457 | 02379 | 11.4 | Solar | 05_07_1W2 | 12/03/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | LEOMINSTER | 175930 | 01453 | 10 | Solar | 05_12_16W4 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 8/2/2016 | Connected |  | N
National Grid | QUINCY | 175543 | 02169 | 557 | Solar | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2015 | N | STD | 0 | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 737552 | 02148 | 0 | Battery Add-On | 05_07_92W78 | 12/03/2025 | 12/08/2025 | 3 | 0 | 3 | 12/09/2025 | 12/09/2025 | 40 | 23 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 3/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BARRE | 676801 | 01005 | 7.6 | Solar | 05_01_207W3 | 03/10/2025 | 04/28/2025 | 18 | 14 | 4 | 04/29/2025 | 04/29/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | EASTON | 716123 | 02375 | 7.98 | Solar | 05_07_1W2 | 09/08/2025 | 09/11/2025 | 2 | 0 | 2 | 09/12/2025 | 09/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | LEOMINSTER | 176915 | 01453 | 14.19 | Solar | 05_12_16W4 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 | 05/04/2016 | 5/10/2017 | Y | EXP | 348 |  |  | 0 | 0 | 0 | 12/6/2016 | 12/6/2016 | 11/15/2016 | Connected |  | N
National Grid | QUINCY | 175542 | 02169 | 540 | Solar | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2015 | 12/05/2014 | 3/31/2018 | Y | STD | 830 | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 | 2/21/2018 | 2/21/2018 | 3/6/2018 | Connected |  | N
National Grid | MALDEN | 756807 | 02148 | 15.2 | Solar | 05_07_92W78 | 03/16/2026 | 03/18/2026 | 2 | 0 | 2 | 03/19/2026 | 03/19/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BARRE | 686521 | 01005 | 5.76 | Solar | 05_01_207W3 | 04/21/2025 | 05/14/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 723086 | 02375 | 17.6 | Solar | 05_07_1W2 | 09/30/2025 | 10/08/2025 | 5 | 0 | 5 | 10/09/2025 | 10/09/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | LEOMINSTER | 177140 | 01453 | 6 | Solar | 05_12_16W4 | 05/27/2016 | 05/27/2016 | 9 | 9 | 0 | 06/14/2016 | 06/14/2016 | 153 | 0 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 |  | 6/6/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 175541 | 02169 | 380 | Solar | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 05/09/2016 | 05/09/2016 | 0 | 0 | 0 | 12/22/2015 | 12/05/2014 | 3/31/2018 | Y | STD | 830 | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 | 2/21/2018 | 2/21/2018 | 3/6/2018 | Connected |  | N
National Grid | REVERE | 175643 | 02151 | 18 | Solar | 05_07_92W78 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 |  | 2/6/2015 | N | EXP | 88 |  |  | 0 | 0 | 0 | 2/26/2015 | 2/26/2015 | 9/24/2015 | Connected |  | N
National Grid | BARRE | 714915 | 01005 | 6.08 | Solar | 05_01_207W3 | 08/26/2025 | 10/22/2025 | 14 | 11 | 3 | 10/23/2025 | 10/23/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 175310 | 02375 | 129 | Solar | 05_07_1W3 | 06/27/2014 | 06/27/2014 | 6 | 1 | 5 | 07/09/2014 | 07/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2014 |  | 11/28/2014 | N | EXP | 115 |  |  | 0 | 0 | 0 | 1/23/2015 | 1/23/2015 | 1/29/2015 | Connected |  | N
National Grid | LEOMINSTER | 177358 | 01453 | 7.6 | Solar | 05_12_16W4 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2017 |  | 2/21/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 10/10/2017 | 10/10/2017 | 8/31/2017 | Connected |  | N
National Grid | QUINCY | 175752 | 02169 | 480 | Solar | 05_09_604W4 | 10/31/2014 | 10/31/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 12/08/2014 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 177881 | 02151 | 19.6 | Solar | 05_07_92W78 | 10/18/2017 | 10/18/2017 | 8 | 2 | 6 | 11/07/2017 | 11/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 10/24/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 | 3/7/2018 | 3/7/2018 | 3/19/2018 | Connected |  | N
National Grid | BARRE | 405711 | 01005 | 0 | Other | 05_01_207W4 | 02/23/2022 | 04/01/2022 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2022 | 04/05/2022 | 2 | 0 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 02/23/2022 | 9/17/2026 | Y | STD | 952 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | EASTON | 564935 | 02356 | 6 | Solar | 05_07_1W3 | 10/24/2023 | 10/26/2023 | 2 | 1 | 1 | 10/27/2023 | 10/27/2023 | 34 | 21 | 13 | 01/18/2024 | 02/21/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/21/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 1/24/2024 |  | 2/7/2025 | N | EXP | 365 | 02/15/2024 | 03/11/2024 | 26 | 0 | 26 |  |  | 4/1/2024 | Connected |  | N
National Grid | LEOMINSTER | 189147 | 01453 | 10 | Solar | 05_12_16W4 | 06/26/2018 | 06/26/2018 | 6 | 1 | 5 | 09/14/2018 | 09/14/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 |  | 10/10/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2018 | Connected |  | N
National Grid | QUINCY | 175977 | 02169 | 760 | Solar | 05_09_604W4 | 05/07/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  | 0 | 0 | 0 | 05/31/2016 | 08/11/2016 | 50 | 0 | 50 | 12/9/2015 | 05/07/2015 | 6/30/2016 | Y | STD | 204 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 178257 | 02151 | 15 | Solar | 05_07_92W78 | 04/17/2018 | 04/17/2018 | 31 | 29 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2019 |  | 4/22/2019 | N | EXP | 40 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 439851 | 01005 | 990 | Solar | 05_01_207W4 | 08/12/2022 | 11/16/2022 | 64 | 54 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 12/13/2022 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | EASTON | 617593 | 02356 | 2.9 | Solar | 05_07_1W3 | 06/13/2024 | 07/23/2024 | 18 | 15 | 3 | 07/24/2024 | 07/24/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 06/13/2024 | 8/8/2025 | Y | EXP | 365 | 10/11/2024 | 10/23/2024 | 13 | 0 | 13 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 189054 | 01453 | 10 | Solar | 05_12_16W4 | 06/26/2018 | 06/26/2018 | 3 | 1 | 2 | 08/06/2018 | 08/06/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 06/26/2018 | 6/26/2020 | Y | EXP | 650 | 05/07/2020 | 05/18/2020 | 9 | 0 | 9 |  |  | 6/3/2020 | Connected |  | N
National Grid | QUINCY | 175975 | 02169 | 990 | Solar | 05_09_604W4 | 05/07/2015 | 05/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 196083 | 02151 | 366.6 | Solar | 05_07_92W78 | 09/17/2018 | 10/01/2018 | 8 | 5 | 3 | 10/02/2018 | 10/02/2018 | 29 | 7 | 22 | 11/29/2018 | 01/10/2019 | 28 | 8 | 20 |  |  | 0 | 0 | 0 | 01/10/2019 | 28 | 8 | 20 |  |  | 0 | 0 | 0 | 2/22/2019 |  | 8/24/2020 | N | EXP | 549 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 657558 | 01005 | 10 | Solar | 05_01_207W4 | 12/16/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/16/2024 | 3/14/2026 | Y | EXP | 365 | 06/12/2025 |  | 294 | 0 | 294 |  |  |  | Completion Documents |  | N
National Grid | EASTON | 174868 | 02356 | 420 | Solar | 05_07_1W4 | 09/06/2012 | 09/06/2012 | 7 | 0 | 7 | 09/18/2012 | 09/18/2012 | 351 | 0 | 351 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2013 |  | 12/11/2012 | N | EXP | 48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 195285 | 01453 | 10 | Solar | 05_12_16W4 | 10/16/2018 | 11/15/2018 | 14 | 9 | 5 | 11/16/2018 | 11/16/2018 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 | 10/16/2018 | 12/27/2019 | Y | EXP | 365 | 07/09/2019 | 07/15/2019 | 6 | 0 | 6 |  |  | 8/20/2019 | Connected |  | N
National Grid | QUINCY | 177057 | 02169 | 4900.5 | Solar | 05_09_604W4 | 01/16/2017 | 01/19/2017 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/03/2017 | 11 | 4 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 | 01/16/2017 | 9/24/2021 | Y | STD | 996 | 02/28/2019 | 10/27/2020 | 608 | 5 | 603 | 6/4/2021 | 9/23/2021 | 9/24/2021 | Connected |  | N
National Grid | REVERE | 191163 | 02151 | 50 | Solar | 05_07_92W78 | 07/19/2018 | 08/08/2018 | 4 | 0 | 4 | 08/09/2018 | 08/09/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2018 |  | 8/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2019 | Connected |  | N
National Grid | BARRE | 725213 | 01005 | 100 | Solar | 05_01_207W4 | 10/08/2025 | 10/29/2025 | 14 | 7 | 7 |  |  | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | EASTON | 176985 | 02356 | 466.2 | Solar | 05_07_1W4 | 03/09/2017 | 03/09/2017 | 12 | 12 | 0 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2017 |  | 3/15/2018 | N | EXP | 346 |  |  | 0 | 0 | 0 | 12/7/2017 | 12/7/2017 | 12/12/2017 | Connected |  | N
National Grid | LEOMINSTER | 195873 | 01453 | 10 | Solar | 05_12_16W4 | 09/27/2019 | 10/01/2019 | 1 | 0 | 1 | 10/02/2019 | 10/02/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 177955 | 02169 | 3300 | Solar | 05_09_604W4 | 10/23/2017 | 12/21/2017 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 | 01/02/2018 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  | 10/31/2018 | N | STD | 92 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 208014 | 02151 | 0 | Solar | 05_07_92W78 | 02/02/2019 | 02/12/2019 | 6 | 0 | 6 | 02/13/2019 | 02/13/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 02/02/2019 | 1/6/2023 | Y | EXP | 365 | 04/16/2022 | 12/20/2022 | 249 | 0 | 249 |  |  | 1/5/2023 | Connected |  | N
National Grid | BARRE | 174277 | 01005 | 25.6 | Solar | 05_01_207W4 | 12/14/2011 | 12/14/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 03/13/2012 | 03/14/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 03/14/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 3/14/2012 |  | 4/14/2012 | N | EXP | 31 |  |  | 0 | 0 | 0 | 4/2/2012 | 4/2/2012 | 4/24/2012 | Connected |  | N
National Grid | EASTON | 328052 | 02356 | 13.8 | Solar | 05_07_1W4 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2021 | Connected |  | N
National Grid | LEOMINSTER | 203604 | 01453 | 3.8 | Solar | 05_12_16W4 | 01/24/2019 | 01/30/2019 | 4 | 4 | 0 | 01/31/2019 | 01/31/2019 | 228 | 0 | 228 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 178496 | 02169 | 10 | Solar | 05_09_604W4 | 12/04/2017 | 02/12/2018 | 46 | 46 | 0 | 02/12/2018 | 02/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2018 |  | 12/10/2018 | N | EXP | 301 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 255776 | 02151 | 24.885 | Solar | 05_07_92W78 | 10/15/2019 | 11/08/2019 | 17 | 13 | 4 | 11/12/2019 | 11/12/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2019 |  | 10/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2020 | Connected |  | N
National Grid | BARRE | 245424 | 01005 | 0 | Solar | 05_01_207W4 | 07/25/2019 | 07/30/2019 | 2 | 0 | 2 | 07/31/2019 | 07/31/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2019 | Connected |  | N
National Grid | EASTON | 531634 | 02356 | 10 | Solar | 05_07_1W4 | 07/18/2023 | 07/19/2023 | 1 | 0 | 1 | 07/20/2023 | 07/20/2023 | 19 | 0 | 19 | 09/06/2023 | 09/22/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 09/22/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 9/21/2023 |  | 11/26/2024 | N | EXP | 365 | 11/02/2023 | 12/08/2023 | 37 | 0 | 37 |  |  | 12/18/2023 | Connected |  | N
National Grid | LEOMINSTER | 223563 | 01453 | 106.6 | Solar | 05_12_16W4 | 04/29/2019 | 05/16/2019 | 12 | 7 | 5 | 05/17/2019 | 05/17/2019 | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2019 | 04/29/2019 | 8/6/2021 | Y | EXP | 720 | 11/04/2020 | 04/07/2021 | 154 | 0 | 154 |  |  | 8/5/2021 | Connected |  | N
National Grid | QUINCY | 189429 | 02169 | 3000 | Solar | 05_09_604W4 | 06/28/2018 | 06/28/2018 | 7 | 7 | 0 |  |  | 10 | 6 | 4 |  |  | 0 | 0 | 0 | 07/25/2018 | 09/13/2018 | 36 | 9 | 27 |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 324369 | 02151 | 0 | Solar | 05_07_92W78 | 11/16/2020 | 11/18/2020 | 1 | 0 | 1 | 11/19/2020 | 11/19/2020 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2021 |  | 6/5/2022 | N | EXP | 500 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 377022 | 01005 | 250 | Solar | 05_01_207W4 | 01/21/2022 | 02/01/2022 | 7 | 1 | 6 |  |  | 30 | 7 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 690107 | 02356 | 17.6 | Solar | 05_07_1W4 | 05/12/2025 | 05/19/2025 | 5 | 0 | 5 | 05/20/2025 | 05/20/2025 | 40 | 20 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/12/2025 | 8/4/2026 | Y | EXP | 365 | 09/06/2025 | 11/21/2025 | 77 | 0 | 77 |  |  | 11/24/2025 | Connected |  | N
National Grid | LEOMINSTER | 257961 | 01453 | 5 | Solar | 05_12_16W4 | 11/13/2019 | 11/20/2019 | 6 | 6 | 0 | 11/21/2019 | 11/21/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2019 | 11/13/2019 | 11/13/2020 | Y | EXP | 365 | 03/25/2020 | 04/07/2020 | 13 | 0 | 13 |  |  | 5/22/2020 | Connected |  | N
National Grid | QUINCY | 190867 | 02169 | 4998 | Solar | 05_09_604W4 | 11/14/2018 | 11/30/2018 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 01/25/2019 | 56 | 20 | 36 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 328800 | 02151 | 15.2 | Solar | 05_07_92W78 | 11/30/2020 | 12/08/2020 | 5 | 0 | 5 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 11/30/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 429394 | 01452 | 0 | Other | 05_01_207W4 | 09/16/2022 | 10/21/2022 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2022 | 11/09/2022 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 587954 | 02356 | 325 | Natural Gas | 05_07_1W5 | 02/26/2024 | 08/06/2024 | 112 | 104 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2024 | 08/13/2024 | 5 | 0 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 | 02/26/2024 | 9/25/2026 | Y | STD | 194 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 263607 | 01453 | 10 | Solar | 05_12_16W4 | 11/12/2019 | 11/20/2019 | 6 | 6 | 0 | 11/21/2019 | 11/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 194815 | 02169 | 250 | Solar | 05_09_604W4 | 11/21/2018 | 12/19/2018 | 17 | 10 | 7 | 12/20/2018 | 12/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 374531 | 02151 | 11.4 | Solar | 05_07_92W78 | 08/09/2021 | 08/25/2021 | 13 | 12 | 1 | 08/26/2021 | 08/26/2021 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 10/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2022 | Connected |  | N
National Grid | HUBBARDSTON | 437417 | 01452 | 0 | Other | 05_01_207W4 | 09/26/2022 | 10/26/2022 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 | 11/17/2022 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 175421 | 02356 | 96 | Solar | 05_07_1W5 | 07/14/2014 | 07/14/2014 | 6 | 3 | 3 | 07/23/2014 | 07/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2014 |  | 10/31/2014 | N | EXP | 77 |  |  | 0 | 0 | 0 | 9/16/2014 | 9/16/2014 | 3/18/2016 | Connected |  | N
National Grid | LEOMINSTER | 341284 | 01453 | 5 | Solar | 05_12_16W4 | 02/12/2021 | 02/17/2021 | 1 | 0 | 1 | 02/18/2021 | 02/18/2021 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 | 02/12/2021 | 5/3/2022 | Y | EXP | 365 | 06/16/2021 | 07/26/2021 | 41 | 0 | 41 |  |  | 1/13/2022 | Connected |  | N
National Grid | QUINCY | 192362 | 02169 | 2400 | Solar | 05_09_604W4 | 10/01/2018 | 10/25/2018 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 | 11/27/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 378621 | 02151 | 7.6 | Solar | 05_07_92W78 | 08/29/2021 | 09/24/2021 | 20 | 19 | 1 | 09/27/2021 | 09/27/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  | 9/23/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 445310 | 01005 | 100 | Solar | 05_01_207W4 | 07/26/2022 | 08/29/2022 | 24 | 15 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 178017 | 02356 | 15.2 | Solar | 05_07_1W5 | 06/29/2017 | 06/29/2017 | 4 | 3 | 1 | 07/06/2017 | 07/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2017 |  | 7/4/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 3/6/2018 | 3/6/2018 | 3/23/2018 | Connected |  | N
National Grid | LEOMINSTER | 346961 | 01453 | 7.6 | Solar | 05_12_16W4 | 03/30/2021 | 03/31/2021 | 0 | 0 | 0 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  | 5/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2022 | Connected |  | N
National Grid | QUINCY | 202897 | 02169 | 20 | Solar | 05_09_604W4 | 02/18/2019 | 12/21/2018 | 0 | 0 | 0 | 02/21/2019 | 02/21/2019 | 19 | 11 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2019 |  | 2/24/2020 | N | EXP | 304 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 422073 | 02151 | 0 | Battery Add-On | 05_07_92W78 | 07/27/2022 | 08/11/2022 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2022 | 09/09/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 485045 | 01452 | 0 | Other | 05_01_207W4 | 02/27/2023 | 03/09/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2023 | 03/24/2023 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 248196 | 02356 | 7.6 | Solar | 05_07_1W5 | 08/12/2019 | 08/12/2019 | 0 | 0 | 0 | 08/13/2019 | 08/13/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2019 | 08/12/2019 | 4/24/2020 | Y | EXP | 247 | 10/23/2019 | 11/09/2019 | 16 | 0 | 16 |  |  | 11/14/2019 | Connected |  | N
National Grid | LEOMINSTER | 408870 | 01453 | 0 | Battery Add-On | 05_12_16W4 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 03/04/2022 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 260756 | 02169 | 10 | Solar | 05_09_604W4 | 10/17/2019 | 10/25/2019 | 5 | 3 | 2 | 10/28/2019 | 10/28/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 |  | 10/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2020 | Connected |  | N
National Grid | REVERE | 421426 | 02151 | 15.2 | Solar | 05_07_92W78 | 04/01/2022 | 06/06/2022 | 44 | 41 | 3 | 06/07/2022 | 06/07/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2022 |  | 7/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2022 | Connected |  | N
National Grid | ATHOL | 579807 | 01331 | 6.38 | Solar | 05_01_207W4 | 02/13/2024 | 03/27/2024 | 30 | 27 | 3 | 03/28/2024 | 03/28/2024 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 |  | 4/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2024 | Connected |  | N
National Grid | EASTON | 311801 | 02356 | 7.6 | Solar | 05_07_1W5 | 09/10/2020 | 09/11/2020 | 0 | 0 | 0 | 09/14/2020 | 09/14/2020 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2020 |  | 10/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2020 | Connected |  | N
National Grid | LEOMINSTER | 534356 | 01453 | 3.8 | Solar | 05_12_16W4 | 06/26/2023 | 06/28/2023 | 2 | 0 | 2 | 06/29/2023 | 06/29/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 297418 | 02169 | 150 | Solar | 05_09_604W4 | 06/19/2020 | 06/26/2020 | 5 | 5 | 0 | 06/29/2020 | 06/29/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 428918 | 02151 | 7.6 | Solar | 05_07_92W78 | 08/19/2022 | 08/22/2022 | 1 | 0 | 1 | 08/23/2022 | 08/23/2022 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2022 | 08/19/2022 | 9/23/2023 | Y | EXP | 365 | 10/27/2022 | 12/07/2022 | 42 | 0 | 42 |  |  | 1/18/2023 | Connected |  | N
National Grid | BARRE | 587583 | 01005 | 7.25 | Solar | 05_01_207W4 | 02/13/2024 | 03/06/2024 | 15 | 12 | 3 | 03/07/2024 | 03/07/2024 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 | 02/13/2024 | 4/4/2025 | Y | EXP | 365 | 06/28/2024 | 08/07/2024 | 41 | 0 | 41 |  |  | 8/16/2024 | Connected |  | N
National Grid | EASTON | 313212 | 02356 | 10 | Solar | 05_07_1W5 | 09/16/2020 | 09/17/2020 | 0 | 0 | 0 | 09/18/2020 | 09/18/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 535671 | 01453 | 5 | Solar | 05_12_16W4 | 01/02/2024 |  | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 296858 | 02169 | 12.285 | Solar | 05_09_604W4 | 08/12/2020 | 08/18/2020 | 3 | 2 | 1 | 08/19/2020 | 08/19/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 | 08/12/2020 | 8/1/2021 | Y | EXP | 365 | 01/20/2021 | 02/11/2021 | 22 | 0 | 22 |  |  | 2/17/2021 | Connected |  | Y
National Grid | REVERE | 448291 | 02151 | 15.2 | Solar | 05_07_92W78 | 08/01/2022 | 08/02/2022 | 1 | 0 | 1 | 08/03/2022 | 08/03/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2022 |  | 9/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 590751 | 01005 | 10 | Solar | 05_01_207W4 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 | 02/22/2024 | 3/23/2025 | Y | EXP | 365 | 05/18/2024 | 05/30/2024 | 13 | 0 | 13 |  |  | 6/21/2024 | Connected |  | N
National Grid | EASTON | 350545 | 02356 | 9.86 | Solar | 05_07_1W5 | 04/14/2021 | 04/15/2021 | 1 | 1 | 0 | 04/16/2021 | 04/16/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 |  | 4/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2021 | Connected |  | N
National Grid | LEOMINSTER | 550822 | 01453 | 3.8 | Solar | 05_12_16W4 | 08/28/2023 | 09/01/2023 | 4 | 2 | 2 | 09/05/2023 | 09/05/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 297555 | 02169 | 84 | Solar | 05_09_604W4 | 06/22/2020 | 06/26/2020 | 4 | 4 | 0 | 06/29/2020 | 06/29/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 479467 | 02151 | 17.28 | Solar | 05_07_92W78 | 11/22/2022 | 02/06/2023 | 50 | 46 | 4 | 02/07/2023 | 02/07/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 598939 | 01005 | 5 | Solar | 05_01_207W4 | 03/28/2024 | 04/01/2024 | 2 | 0 | 2 | 04/02/2024 | 04/02/2024 | 82 | 80 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 419001 | 02356 | 10 | Solar | 05_07_1W5 | 06/02/2022 | 07/06/2022 | 21 | 20 | 1 | 07/07/2022 | 07/07/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2022 | 06/02/2022 | 9/16/2023 | Y | EXP | 365 | 08/27/2022 | 09/14/2022 | 19 | 0 | 19 |  |  | 1/19/2023 | Connected |  | N
National Grid | LEOMINSTER | 581875 | 01453 | 100 | Solar | 05_12_16W4 | 01/19/2024 | 02/08/2024 | 13 | 3 | 10 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 303281 | 02169 | 15.2 | Solar | 05_09_604W4 | 04/12/2021 | 04/19/2021 | 4 | 0 | 4 | 04/20/2021 | 04/20/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2021 | 04/12/2021 | 8/15/2022 | Y | EXP | 365 | 10/21/2022 | 01/06/2023 | 78 | 0 | 78 |  |  | 1/19/2024 | Connected |  | Y
National Grid | REVERE | 479458 | 02151 | 7.6 | Solar | 05_07_92W78 | 11/22/2022 | 11/29/2022 | 4 | 0 | 4 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2023 |  | 1/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 651575 | 01005 | 5.76 | Solar | 05_01_207W4 | 11/04/2024 | 11/26/2024 | 10 | 0 | 10 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 528713 | 02356 | 20 | Solar | 05_07_1W5 | 05/24/2023 | 05/25/2023 | 1 | 0 | 1 | 05/26/2023 | 05/26/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 |  | 9/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2023 | Connected |  | N
National Grid | LEOMINSTER | 600326 | 01453 | 6 | Solar | 05_12_16W4 | 04/05/2024 |  | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 307522 | 02169 | 25 | Solar | 05_09_604W4 | 08/19/2020 | 08/31/2020 | 8 | 0 | 8 | 09/01/2020 | 09/01/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/19/2020 | 11/29/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 489931 | 02151 | 13 | Solar | 05_07_92W78 | 01/10/2023 | 01/17/2023 | 5 | 4 | 1 | 01/18/2023 | 01/18/2023 | 50 | 30 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 | 01/10/2023 | 7/17/2024 | Y | EXP | 365 | 08/10/2023 | 09/08/2023 | 30 | 0 | 30 |  |  | 9/15/2023 | Connected |  | N
National Grid | HUBBARDSTON | 653516 | 01452 | 10.075 | Solar | 05_01_207W4 | 11/20/2024 | 03/04/2025 | 13 | 9 | 4 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 | 11/20/2024 | 4/14/2026 | Y | EXP | 365 | 09/20/2025 | 09/23/2025 | 4 | 0 | 4 |  |  | 10/8/2025 | Connected |  | N
National Grid | EASTON | 573913 | 02356 | 7.25 | Solar | 05_07_1W5 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 612100 | 01453 | 7.6 | Solar | 05_12_16W4 | 05/21/2024 | 06/03/2024 | 2 | 0 | 2 | 06/04/2024 | 06/04/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | QUINCY | 307520 | 02169 | 25 | Solar | 05_09_604W4 | 08/19/2020 | 08/31/2020 | 7 | 0 | 7 | 09/01/2020 | 09/01/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2020 | 08/19/2020 | 4/9/2023 | Y | EXP | 565 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 502360 | 02151 | 13.3 | Solar | 05_07_92W78 | 02/15/2023 | 02/17/2023 | 3 | 2 | 1 | 02/21/2023 | 02/21/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 | 02/15/2023 | 5/4/2024 | Y | EXP | 365 | 07/07/2023 | 07/26/2023 | 20 | 0 | 20 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 684320 | 01452 | 7.6 | Solar | 05_01_207W4 | 04/10/2025 | 05/13/2025 | 2 | 0 | 2 | 06/02/2025 | 06/02/2025 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2025 |  | 9/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | EASTON | 576061 | 02334 | 8.41 | Solar | 05_07_1W5 | 12/06/2023 | 01/16/2024 | 26 | 24 | 2 | 01/17/2024 | 01/17/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 613303 | 01453 | 34.6 | Solar | 05_12_16W4 | 06/05/2024 | 06/07/2024 | 2 | 0 | 2 | 06/10/2024 | 06/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  | 7/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | QUINCY | 319066 | 02169 | 4999 | Solar | 05_09_604W4 | 11/20/2020 | 12/30/2020 | 26 | 20 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2021 | 02/10/2021 | 2 | 0 | 2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 521894 | 02151 | 14.97 | Solar | 05_07_92W78 | 04/26/2023 | 05/01/2023 | 4 | 2 | 2 | 05/02/2023 | 05/02/2023 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2023 | Connected |  | N
National Grid | HUBBARDSTON | 645834 | 01452 | 4950 | Other | 05_01_207W6 | 01/29/2025 | 04/23/2025 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/24/2025 | 05/21/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | EASTON | 590352 | 02356 | 7.6 | Solar | 05_07_1W5 | 02/15/2024 | 02/20/2024 | 2 | 0 | 2 | 02/21/2024 | 02/21/2024 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 5/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2024 | Connected |  | N
National Grid | LEOMINSTER | 643354 | 01453 | 10 | Solar | 05_12_16W4 | 09/27/2024 | 01/03/2025 | 3 | 0 | 3 | 01/06/2025 | 01/06/2025 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 319065 | 02169 | 4999 | Solar | 05_09_604W4 | 11/19/2020 | 12/17/2020 | 18 | 12 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2020 | 01/14/2021 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 532740 | 02151 | 10 | Solar | 05_07_92W78 | 06/09/2023 | 07/20/2023 | 27 | 25 | 2 | 07/21/2023 | 07/21/2023 | 70 | 49 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 |  | 1/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | HUBBARDSTON | 698849 | 01452 | 14.82 | Solar | 05_01_207W6 | 07/01/2025 | 08/20/2025 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 38 | 22 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | EASTON | 616166 | 02334 | 10 | Solar | 05_07_1W5 | 11/04/2024 | 11/20/2024 | 11 | 9 | 2 | 11/21/2024 | 11/21/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | LEOMINSTER | 643781 | 01453 | 10 | Solar | 05_12_16W4 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/01/2024 | 1/6/2026 | Y | EXP | 365 | 07/30/2025 | 10/29/2025 | 92 | 0 | 92 |  |  | 12/3/2025 | Connected |  | N
National Grid | QUINCY | 400502 | 02169 | 10 | Solar | 05_09_604W4 | 12/10/2021 | 12/14/2021 | 2 | 0 | 2 | 12/15/2021 | 12/15/2021 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2022 |  | 2/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2022 | Connected |  | N
National Grid | REVERE | 542282 | 02151 | 0 | Solar | 05_07_92W78 | 07/21/2023 | 07/24/2023 | 1 | 0 | 1 | 07/25/2023 | 07/25/2023 | 113 | 94 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2024 | Connected |  | N
National Grid | HUBBARDSTON | 759935 | 01452 | 24.7 | Solar | 05_01_207W6 | 04/01/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | EASTON | 667016 | 02356 | 10 | Solar | 05_07_1W5 | 01/31/2025 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 16 | 0 | 16 | 03/11/2025 | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 673809 | 01453 | 5.76 | Solar | 05_12_16W4 | 02/24/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 439587 | 02169 | 15.2 | Solar | 05_09_604W4 | 06/23/2022 | 07/06/2022 | 9 | 5 | 4 | 07/07/2022 | 07/07/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 | 06/23/2022 | 9/19/2023 | Y | EXP | 365 | 09/07/2022 | 09/19/2022 | 13 | 0 | 13 |  |  | 12/13/2022 | Connected |  | N
National Grid | REVERE | 632317 | 02151 | 9.88 | Solar | 05_07_92W78 | 08/30/2024 | 09/04/2024 | 2 | 0 | 2 | 09/05/2024 | 09/05/2024 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 | 08/30/2024 | 10/31/2025 | Y | EXP | 365 | 01/23/2025 | 03/27/2025 | 51 | 0 | 51 |  |  | 3/6/2025 | Connected |  | N
National Grid | HUBBARDSTON | 175882 | 01452 | 984 | Solar | 05_01_207W6 | 05/21/2015 | 05/21/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/27/2015 | 06/25/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2016 | 05/21/2015 | 10/31/2017 | Y | STD | 487 | 09/14/2017 | 01/05/2018 | 71 | 0 | 71 | 12/28/2017 | 12/28/2017 | 1/4/2018 | Connected |  | N
National Grid | EASTON | 672397 | 02356 | 8.376 | Solar | 05_07_1W5 | 02/20/2025 | 03/13/2025 | 4 | 3 | 1 | 04/04/2025 | 04/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 | 02/20/2025 | 5/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | LEOMINSTER | 677613 | 01453 | 250 | Solar | 05_12_16W5 | 06/13/2025 | 07/07/2025 | 14 | 5 | 9 | 07/08/2025 | 07/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 7/24/2026 | N | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | QUINCY | 516473 | 02169 | 10 | Solar | 05_09_604W4 | 04/06/2023 | 04/24/2023 | 203 | 133 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 647788 | 02151 | 4.64 | Solar | 05_07_92W78 | 10/17/2024 | 11/13/2024 | 3 | 1 | 2 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | BARRE | 176471 | 01005 | 7.6 | Solar | 05_01_207W6 | 03/20/2016 | 03/20/2016 | 3 | 3 | 0 | 03/24/2016 | 03/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/20/2016 | 3/26/2017 | Y | EXP | 348 | 11/08/2016 | 11/29/2016 | 13 | 0 | 13 | 1/19/2017 | 1/19/2017 | 1/19/2017 | Connected |  | N
National Grid | EASTON | 704480 | 02334 | 4.18 | Solar | 05_07_1W5 | 07/15/2025 | 08/26/2025 | 5 | 0 | 5 | 08/27/2025 | 08/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | LEOMINSTER | 692294 | 01453 | 3.839 | Solar | 05_12_16W5 | 05/16/2025 | 06/05/2025 | 1 | 0 | 1 | 06/10/2025 | 06/10/2025 | 97 | 85 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 | 05/16/2025 | 12/17/2026 | Y | EXP | 365 | 03/27/2026 |  | 6 | 0 | 6 |  |  |  | Construction |  | N
National Grid | QUINCY | 532813 | 02169 | 10 | Solar | 05_09_604W4 | 06/09/2023 | 06/13/2023 | 2 | 1 | 1 | 06/14/2023 | 06/14/2023 | 52 | 33 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 653471 | 02151 | 10 | Solar | 05_07_92W78 | 11/11/2024 | 12/12/2024 | 12 | 9 | 3 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/11/2024 | 2/24/2026 | Y | EXP | 365 | 06/11/2025 | 06/10/2025 | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | BARRE | 176557 | 01005 | 6 | Solar | 05_01_207W6 | 10/07/2015 | 10/07/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 |  | 10/13/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 3/31/2016 | 3/31/2016 | 4/6/2016 | Connected |  | N
National Grid | EASTON | 552146 | 02356 | 360 | Solar | 05_07_1W6 | 02/16/2024 | 05/21/2024 | 65 | 57 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2024 | 06/04/2024 | 9 | 2 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2024 | 02/16/2024 | 9/27/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | LEOMINSTER | 730134 | 01453 | 10 | Solar | 05_12_16W5 | 11/03/2025 | 11/04/2025 | 4 | 0 | 4 | 12/10/2025 | 12/10/2025 | 25 | 13 | 12 | 02/13/2026 | 03/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 03/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 3/12/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | QUINCY | 596912 | 02169 | 7.6 | Solar | 05_09_604W4 | 03/22/2024 | 03/27/2024 | 3 | 0 | 3 | 03/28/2024 | 03/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/22/2024 | 4/9/2025 | Y | EXP | 365 | 04/26/2024 | 05/01/2024 | 6 | 0 | 6 |  |  | 1/9/2025 | Connected |  | N
National Grid | REVERE | 671495 | 02151 | 5.76 | Solar | 05_07_92W78 | 02/11/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | HUBBARDSTON | 176657 | 01452 | 3.8 | Solar | 05_01_207W6 | 04/19/2016 | 04/19/2016 | 13 | 13 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2016 |  | 4/26/2017 | N | EXP | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 731355 | 02356 | 5.76 | Solar | 05_07_1W6 | 11/04/2025 | 12/02/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | LEOMINSTER | 176347 | 01453 | 140 | Solar | 05_12_16W5 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 | 03/09/2015 | 03/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 |  | 9/30/2015 | N | EXP | 191 |  |  | 0 | 0 | 0 | 3/25/2015 | 3/25/2015 | 11/18/2015 | Connected |  | N
National Grid | QUINCY | 608016 | 02169 | 10 | Solar | 05_09_604W4 | 05/03/2024 | 05/09/2024 | 4 | 3 | 1 | 05/10/2024 | 05/10/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 05/03/2024 | 6/28/2025 | Y | EXP | 365 | 09/05/2024 | 09/28/2024 | 24 | 0 | 24 |  |  | 10/16/2024 | Connected |  | N
National Grid | REVERE | 678603 | 02151 | 13.8 | Solar | 05_07_92W78 | 03/19/2025 | 03/26/2025 | 5 | 2 | 3 | 03/27/2025 | 03/27/2025 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | Y
National Grid | BARRE | 176656 | 01005 | 10 | Solar | 05_01_207W6 | 04/20/2016 | 04/20/2016 | 1 | 1 | 0 | 04/21/2016 | 04/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 | 04/20/2016 | 4/25/2017 | Y | EXP | 357 | 08/30/2016 | 09/09/2016 | 7 | 0 | 7 | 12/2/2016 | 12/2/2016 | 12/2/2016 | Connected |  | N
National Grid | EASTON | 738024 | 02356 | 10 | Solar | 05_07_1W6 | 12/05/2025 | 12/09/2025 | 2 | 0 | 2 | 12/10/2025 | 12/10/2025 | 55 | 35 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LEOMINSTER | 176784 | 01453 | 432 | Solar | 05_12_16W5 | 01/13/2016 | 01/13/2016 | 9 | 9 | 0 | 01/27/2016 | 01/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2016 |  | 7/1/2017 | N | EXP | 249 |  |  | 0 | 0 | 0 | 1/12/2017 | 1/12/2017 | 6/30/2017 | Connected |  | N
National Grid | QUINCY | 654668 | 02169 | 9.56 | Solar | 05_09_604W4 | 11/15/2024 | 12/09/2024 | 4 | 2 | 2 | 12/10/2024 | 12/10/2024 | 97 | 72 | 25 | 05/12/2025 | 05/09/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | MALDEN | 706156 | 02148 | 15.2 | Solar | 05_07_92W78 | 07/21/2025 | 07/25/2025 | 4 | 0 | 4 | 07/28/2025 | 07/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | HUBBARDSTON | 176795 | 01452 | 10 | Solar | 05_01_207W6 | 02/25/2016 | 02/25/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2016 | 02/25/2016 | 3/1/2017 | Y | EXP | 328 | 07/18/2016 | 08/01/2016 | 10 | 0 | 10 | 4/7/2016 | 4/7/2016 | 8/3/2016 | Connected |  | N
National Grid | EASTON | 174683 | 02356 | 30 | Solar | 05_07_1W6 | 01/09/2014 | 01/09/2014 | 5 | 0 | 5 | 01/17/2014 | 01/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2014 |  | 3/31/2014 | N | EXP | 66 |  |  | 0 | 0 | 0 | 4/11/2014 | 4/11/2014 | 4/11/2014 | Connected |  | N
National Grid | LEOMINSTER | 323866 | 01453 | 6 | Solar | 05_12_16W5 | 11/23/2020 | 11/25/2020 | 1 | 0 | 1 | 11/27/2020 | 11/27/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 | 11/23/2020 | 6/16/2022 | Y | EXP | 365 | 10/15/2021 | 12/07/2021 | 54 | 4 | 50 |  |  | 12/13/2021 | Connected |  | Y
National Grid | QUINCY | 661929 | 02169 | 3.8 | Solar | 05_09_604W4 | 12/20/2024 | 01/14/2025 | 5 | 0 | 5 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 12/20/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | EVERETT | 714426 | 02149 | 11.4 | Solar | 05_07_92W78 | 08/25/2025 | 09/03/2025 | 5 | 2 | 3 | 09/04/2025 | 09/04/2025 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | BARRE | 177137 | 01005 | 7.6 | Solar | 05_01_207W6 | 05/27/2016 | 05/27/2016 | 1 | 1 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 | 05/27/2016 | 6/5/2017 | Y | EXP | 356 | 11/01/2016 | 11/14/2016 | 8 | 0 | 8 | 12/7/2016 | 12/7/2016 | 12/12/2016 | Connected |  | N
National Grid | EASTON | 174682 | 02356 | 40 | Solar | 05_07_1W6 | 01/09/2014 | 01/09/2014 | 5 | 0 | 5 | 01/17/2014 | 01/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2014 |  | 3/31/2014 | N | EXP | 68 |  |  | 0 | 0 | 0 | 4/22/2014 | 4/22/2014 | 4/25/2014 | Connected |  | N
National Grid | LEOMINSTER | 326220 | 01453 | 7.6 | Solar | 05_12_16W5 | 11/25/2020 | 12/01/2020 | 2 | 0 | 2 | 12/02/2020 | 12/02/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 11/25/2020 | 9/13/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2021 | Connected |  | N
National Grid | QUINCY | 674960 | 02169 | 16.34 | Solar | 05_09_604W4 | 02/28/2025 | 03/05/2025 | 4 | 1 | 3 | 03/06/2025 | 03/06/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 738757 | 02149 | 0 | Battery Add-On | 05_07_92W79 | 12/08/2025 | 12/10/2025 | 2 | 0 | 2 | 12/11/2025 | 12/11/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2026 |  | 1/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BARRE | 177219 | 01005 | 36 | Solar | 05_01_207W6 | 08/15/2016 | 08/15/2016 | 1 | 1 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2016 |  | 1/21/2018 | N | EXP | 486 |  |  | 0 | 0 | 0 | 12/13/2017 | 12/13/2017 | 12/13/2017 | Connected |  | N
National Grid | EASTON | 175343 | 02356 | 42 | Solar | 05_07_1W6 | 07/02/2014 | 07/02/2014 | 3 | 0 | 3 | 07/09/2014 | 07/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2014 |  | 11/28/2014 | N | EXP | 115 |  |  | 0 | 0 | 0 | 1/21/2015 | 1/21/2015 | 1/30/2015 | Connected |  | N
National Grid | LEOMINSTER | 419637 | 01453 | 85 | Solar | 05_12_16W5 | 04/13/2022 | 07/26/2022 | 70 | 62 | 8 | 07/27/2022 | 07/27/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 | 04/13/2022 | 1/18/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2023 | Connected |  | N
National Grid | QUINCY | 676035 | 02170 | 11.5 | Solar | 05_09_604W4 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | MALDEN | 746180 | 02148 | 0 | Battery Add-On | 05_07_92W79 | 01/20/2026 | 01/26/2026 | 3 | 0 | 3 | 01/27/2026 | 01/27/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HUBBARDSTON | 178182 | 01452 | 3.8 | Solar | 05_01_207W6 | 04/13/2018 | 04/13/2018 | 7 | 0 | 7 | 05/02/2018 | 05/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2018 |  | 4/21/2019 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 175423 | 02356 | 195 | Solar | 05_07_1W6 | 07/14/2014 | 07/14/2014 | 6 | 2 | 4 | 07/23/2014 | 07/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2014 |  | 10/31/2014 | N | EXP | 74 |  |  | 0 | 0 | 0 | 8/29/2014 | 8/29/2014 | 1/30/2015 | Connected |  | N
National Grid | LEOMINSTER | 642291 | 01453 | 11.4 | Solar | 05_12_16W5 | 09/25/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 689688 | 02169 | 13.8 | Solar | 05_09_604W4 | 05/05/2025 | 05/27/2025 | 3 | 0 | 3 | 06/04/2025 | 06/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 | 05/05/2025 | 7/16/2026 | Y | EXP | 365 | 10/03/2025 | 10/09/2025 | 7 | 0 | 7 |  |  | 10/11/2025 | Connected |  | N
National Grid | MALDEN | 174695 | 02148 | 900 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2015 |  | 12/31/2015 | N | STD | 238 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 178446 | 01005 | 7.6 | Solar | 05_01_207W6 | 04/03/2018 | 04/03/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2018 |  | 4/9/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2018 | Connected |  | N
National Grid | EASTON | 175633 | 02356 | 120 | Solar | 05_07_1W6 | 08/06/2014 | 08/06/2014 | 36 | 31 | 5 | 09/29/2014 | 09/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2014 |  | 12/31/2014 | N | EXP | 84 |  |  | 0 | 0 | 0 | 1/20/2015 | 1/20/2015 | 1/29/2015 | Connected |  | N
National Grid | LEOMINSTER | 655553 | 01453 | 3.8 | Solar | 05_12_16W5 | 11/20/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 716025 | 02170 | 2988 | Solar | 05_09_701J1 | 09/26/2025 | 10/27/2025 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 12/31/2025 | 44 | 24 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | MALDEN | 174694 | 02148 | 500 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  | 0 | 0 | 0 | 01/15/2014 | 04/03/2014 | 53 | 0 | 53 | 12/31/2013 | 12/21/2012 | 12/31/2016 | Y | STD | 1096 |  |  | 0 | 0 | 0 | 12/25/2012 | 12/25/2012 | 2/23/2016 | Connected |  | N
National Grid | BARRE | 187836 | 01005 | 9.84 | Solar | 05_01_207W6 | 06/13/2018 | 06/12/2018 | 10 | 5 | 5 | 06/28/2018 | 06/28/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2018 | 06/13/2018 | 8/30/2019 | Y | EXP | 394 | 03/09/2019 | 03/08/2019 | 0 | 0 | 0 |  |  | 8/10/2019 | Connected |  | N
National Grid | EASTON | 178001 | 02356 | 86.4 | Solar | 05_07_1W6 | 04/26/2017 | 04/26/2017 | 1 | 1 | 0 | 04/28/2017 | 04/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2017 | 04/26/2017 | 5/2/2018 | Y | EXP | 366 | 01/29/2018 | 02/07/2018 | 7 | 0 | 7 | 4/4/2018 | 4/4/2018 | 4/10/2018 | Connected |  | N
National Grid | LEOMINSTER | 174267 | 01453 | 75 | Solar | 05_12_16W6 | 01/03/2012 | 01/03/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2012 |  | 4/2/2012 | N | EXP | 18 |  |  | 0 | 0 | 0 | 6/26/2012 | 6/26/2012 | 7/5/2012 | Connected |  | N
National Grid | QUINCY | 751184 | 02170 | 0 | Solar | 05_09_701J1 | 02/16/2026 | 02/24/2026 | 5 | 2 | 3 | 02/25/2026 | 02/25/2026 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MALDEN | 175006 | 02148 | 750 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  | 0 | 0 | 0 | 01/15/2014 | 04/03/2014 | 53 | 0 | 53 | 12/31/2013 | 12/21/2012 | 12/31/2016 | Y | STD | 1096 |  |  | 0 | 0 | 0 | 9/18/2013 | 9/18/2013 | 2/23/2016 | Connected |  | N
National Grid | BARRE | 189869 | 01005 | 4999 | Solar | 05_01_207W6 | 09/10/2018 | 09/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2018 | 11/19/2018 | 46 | 20 | 26 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2021 |  | 9/30/2022 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 650648 | 02375 | 3.19 | Solar | 05_07_1W6 | 10/29/2024 | 11/06/2024 | 3 | 0 | 3 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/29/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | LEOMINSTER | 177687 | 01453 | 6.54 | Solar | 05_12_16W6 | 09/29/2017 | 09/29/2017 | 5 | 5 | 0 | 10/06/2017 | 10/06/2017 | 80 | 12 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2017 |  | 10/7/2018 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 178159 | 02170 | 3420 | Solar | 05_09_701J1 | 12/26/2017 | 02/12/2018 | 32 | 24 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2018 | 03/14/2018 | 20 | 0 | 20 |  | 0 | 0 | 0 | 03/03/2020 | 06/05/2020 | 66 | 0 | 66 | 8/16/2018 | 12/26/2017 | 4/26/2022 | Y | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 175005 | 02149 | 750 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  | 0 | 0 | 0 | 01/15/2014 | 04/03/2014 | 53 | 0 | 53 | 12/31/2013 | 12/21/2012 | 12/31/2016 | Y | STD | 1096 |  |  | 0 | 0 | 0 | 9/18/2013 | 9/18/2013 | 2/23/2016 | Connected |  | N
National Grid | BARRE | 241466 | 01005 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | EASTON | 663115 | 02375 | 7.25 | Solar | 05_07_1W6 | 12/30/2024 | 01/07/2025 | 3 | 1 | 2 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | LEOMINSTER | 177718 | 01453 | 3.8 | Solar | 05_12_16W6 | 07/27/2017 | 07/27/2017 | 9 | 9 | 0 | 08/09/2017 | 08/09/2017 | 121 | 0 | 121 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2017 |  | 8/1/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 178669 | 02170 | 4990 | Solar | 05_09_701J1 | 03/16/2018 | 04/02/2018 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/24/2018 | 05/31/2018 | 5 | 5 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 175004 | 02149 | 500 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  | 0 | 0 | 0 | 01/15/2014 | 04/03/2014 | 53 | 0 | 53 | 12/31/2013 | 12/21/2012 | 12/31/2016 | Y | STD | 1096 |  |  | 0 | 0 | 0 |  |  | 2/23/2016 | Connected |  | N
National Grid | BARRE | 241465 | 01005 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 8/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | NORTON | 676729 | 02766 | 16.754 | Solar | 05_07_1W6 | 03/24/2025 | 03/28/2025 | 4 | 0 | 4 | 03/31/2025 | 03/31/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | LEOMINSTER | 177754 | 01453 | 6 | Solar | 05_12_16W6 | 07/31/2017 | 07/31/2017 | 8 | 8 | 0 | 08/11/2017 | 08/11/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 8/6/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 6/12/2018 | Connected |  | N
National Grid | QUINCY | 195813 | 02169 | 7999 | Solar | 05_09_701J1 | 09/14/2018 | 09/21/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2018 | 11/21/2018 | 34 | 26 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 175321 | 02149 | 440.8 | Solar | 05_07_92W79 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 299 | 0 | 299 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2014 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROYALSTON | 241464 | 01368 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | NORTON | 584110 | 02766 | 0 | Other | 05_07_1W8 | 02/28/2024 | 05/23/2024 | 60 | 50 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/24/2024 | 09/03/2024 | 69 | 63 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LEOMINSTER | 178263 | 01453 | 16.32 | Solar | 05_12_16W6 | 04/17/2018 | 04/17/2018 | 3 | 3 | 0 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2018 |  | 4/23/2019 | N | EXP | 340 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 196252 | 02169 | 250 | Solar | 05_09_701J1 | 10/31/2018 | 12/03/2018 | 10 | 5 | 5 | 12/04/2018 | 12/04/2018 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 175514 | 02176 | 500 | Solar | 05_07_92W79 | 12/21/2012 | 12/21/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2013 | 03/20/2013 | 42 | 0 | 42 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2014 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 241463 | 01368 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | NORTON | 174684 | 02766 | 50 | Solar | 05_07_1W8 | 01/09/2014 | 01/09/2014 | 5 | 0 | 5 | 01/17/2014 | 01/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2014 |  | 3/31/2014 | N | EXP | 66 |  |  | 0 | 0 | 0 | 4/7/2014 | 4/7/2014 | 4/24/2014 | Connected |  | N
National Grid | LEOMINSTER | 185547 | 01453 | 17.85 | Solar | 05_12_16W6 | 05/16/2018 | 05/16/2018 | 35 | 25 | 10 | 06/22/2018 | 06/22/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 198058 | 02170 | 2400 | Solar | 05_09_701J1 | 10/16/2018 | 11/26/2018 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 01/14/2019 | 56 | 14 | 42 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 175692 | 02176 | 15.8 | Solar | 05_07_92W79 | 05/23/2014 | 05/23/2014 | 5 | 0 | 5 | 06/03/2014 | 06/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2014 |  | 8/29/2014 | N | EXP | 58 |  |  | 0 | 0 | 0 | 7/2/2014 | 7/2/2014 | 9/25/2015 | Connected |  | N
National Grid | ROYALSTON | 241462 | 01368 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | NORTON | 174713 | 02766 | 85 | Solar | 05_07_1W8 | 01/09/2014 | 01/09/2014 | 5 | 0 | 5 | 01/17/2014 | 01/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2014 |  | 3/31/2014 | N | EXP | 32 |  |  | 0 | 0 | 0 | 4/7/2014 | 4/7/2014 | 4/24/2014 | Connected |  | N
National Grid | LEOMINSTER | 237449 | 01453 | 7.6 | Solar | 05_12_16W6 | 07/15/2019 | 08/06/2019 | 16 | 16 | 0 | 08/07/2019 | 08/07/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 | 07/15/2019 | 3/10/2020 | Y | EXP | 365 | 10/11/2019 | 01/07/2020 | 88 | 0 | 88 |  |  | 1/12/2020 | Connected |  | N
National Grid | QUINCY | 287445 | 02170 | 10 | Solar | 05_09_701J1 | 04/10/2020 | 04/28/2020 | 13 | 12 | 1 | 04/29/2020 | 04/29/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 |  | 4/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2020 | Connected |  | N
National Grid | MELROSE | 176849 | 02176 | 996 | Solar | 05_07_92W79 | 11/09/2015 | 11/09/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2015 | 12/14/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/15/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROYALSTON | 241461 | 01368 | 22.8 | Solar | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | NORTON | 175415 | 02766 | 52 | Solar | 05_07_1W8 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2014 |  | 11/28/2014 | N | EXP | 120 |  |  | 0 | 0 | 0 | 8/11/2014 | 8/11/2014 | 1/8/2015 | Connected |  | N
National Grid | LEOMINSTER | 310897 | 01453 | 10 | Solar | 05_12_16W6 | 11/10/2020 | 11/17/2020 | 3 | 0 | 3 | 11/18/2020 | 11/18/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/10/2020 | 1/4/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2021 | Connected |  | N
National Grid | QUINCY | 291614 | 02169 | 500 | Solar | 05_09_701J1 | 05/18/2020 | 06/24/2020 | 25 | 16 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 178008 | 02148 | 990 | Solar | 05_07_92W79 | 04/28/2017 | 04/28/2017 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2017 | 06/27/2017 | 34 | 19 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 | 04/28/2017 | 12/31/2019 | Y | STD | 499 | 01/24/2019 | 02/06/2019 | 13 | 0 | 13 | 9/3/2019 | 9/3/2019 | 12/31/2019 | Connected |  | N
National Grid | ROYALSTON | 294443 | 01368 | 15.2 | Solar | 05_01_207W6 | 06/02/2020 | 06/04/2020 | 1 | 0 | 1 | 06/05/2020 | 06/05/2020 | 73 | 55 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 | 06/02/2020 | 6/4/2021 | Y | EXP | 365 | 01/20/2021 | 01/26/2021 | 6 | 0 | 6 |  |  | 4/29/2021 | Connected |  | N
National Grid | EASTON | 175599 | 02375 | 72 | Solar | 05_07_1W8 | 08/01/2014 | 08/01/2014 | 6 | 0 | 6 | 08/12/2014 | 08/12/2014 | 616 | 0 | 616 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2014 |  | 11/28/2014 | N | EXP | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 343246 | 01453 | 10 | Solar | 05_12_16W6 | 03/16/2021 | 04/01/2021 | 11 | 6 | 5 | 04/02/2021 | 04/02/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2021 | Connected |  | N
National Grid | QUINCY | 318176 | 02171 | 5000 | Solar | 05_09_701J1 | 11/30/2020 | 01/05/2021 | 23 | 21 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2021 | 01/26/2021 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 185564 | 02148 | 2000 | Solar | 05_07_92W79 | 05/17/2018 | 05/17/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/19/2018 | 07/27/2018 | 28 | 11 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 | 05/17/2018 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 295621 | 01331 | 9.8 | Solar | 05_01_207W6 | 07/30/2020 | 08/03/2020 | 1 | 0 | 1 | 08/04/2020 | 08/04/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 | 07/30/2020 | 8/2/2021 | Y | EXP | 365 | 05/04/2021 | 05/05/2021 | 1 | 0 | 1 |  |  | 5/24/2021 | Connected |  | N
National Grid | NORTON | 175594 | 02766 | 63 | Solar | 05_07_1W8 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2014 |  | 10/31/2014 | N | EXP | 63 |  |  | 0 | 0 | 0 | 3/14/2016 | 3/14/2016 | 3/14/2016 | Connected |  | N
National Grid | LEOMINSTER | 369366 | 01453 | 12.98 | Solar | 05_12_16W6 | 08/06/2021 | 08/31/2021 | 18 | 16 | 2 | 09/01/2021 | 09/01/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 |  | 10/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/11/2022 | Connected |  | Y
National Grid | QUINCY | 494175 | 02170 | 7.6 | Solar | 05_09_701J1 | 03/08/2023 | 03/13/2023 | 4 | 3 | 1 | 03/14/2023 | 03/14/2023 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 |  | 6/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2023 | Connected |  | N
National Grid | MALDEN | 185512 | 02148 | 2000 | Solar | 05_07_92W79 | 05/15/2018 | 05/15/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/19/2018 | 07/27/2018 | 28 | 11 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 | 05/15/2018 | 4/14/2026 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROYALSTON | 326200 | 01368 | 11.4 | Solar | 05_01_207W6 | 11/19/2020 | 11/25/2020 | 4 | 2 | 2 | 11/27/2020 | 11/27/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 |  | 11/24/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | EASTON | 369405 | 02375 | 9.57 | Solar | 05_07_1W8 | 09/17/2021 | 09/21/2021 | 2 | 0 | 2 | 09/22/2021 | 09/22/2021 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2021 |  | 6/26/2023 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  | 6/28/2023 | Connected |  | N
National Grid | LEOMINSTER | 418205 | 01453 | 7.68 | Solar | 05_12_16W6 | 04/06/2022 | 04/18/2022 | 8 | 7 | 1 | 04/19/2022 | 04/19/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2022 | 04/06/2022 | 7/17/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 665005 | 02170 | 10 | Solar | 05_09_701J1 | 01/10/2025 | 02/18/2025 | 23 | 18 | 5 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N
National Grid | MALDEN | 192507 | 02148 | 15.2 | Solar | 05_07_92W79 | 08/01/2018 | 08/15/2018 | 8 | 0 | 8 | 08/16/2018 | 08/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROYALSTON | 325515 | 01368 | 7.6 | Solar | 05_01_207W6 | 11/30/2020 | 12/08/2020 | 5 | 0 | 5 | 12/09/2020 | 12/09/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 11/30/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 414118 | 02375 | 7.6 | Solar | 05_07_1W8 | 02/24/2022 | 02/28/2022 | 2 | 0 | 2 | 03/01/2022 | 03/01/2022 | 60 | 44 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2022 |  | 6/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 475615 | 01453 | 67.3 | Solar | 05_12_16W6 | 11/10/2022 | 11/23/2022 | 8 | 0 | 8 | 11/25/2022 | 11/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2023 |  | 10/27/2024 | N | EXP | 200 |  |  | 0 | 0 | 0 |  |  | 7/22/2024 | Connected |  | N
National Grid | QUINCY | 697634 | 02170 | 11.4 | Solar | 05_09_701J1 | 06/10/2025 | 06/30/2025 | 5 | 0 | 5 | 09/11/2025 | 09/11/2025 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | MALDEN | 291859 | 02148 | 43.2 | Solar | 05_07_92W79 | 05/13/2020 | 05/18/2020 | 2 | 1 | 1 | 05/19/2020 | 05/19/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2020 | Connected |  | N
National Grid | ATHOL | 401899 | 01331 | 6 | Solar | 05_01_207W6 | 01/26/2022 | 01/27/2022 | 0 | 0 | 0 | 01/28/2022 | 01/28/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 |  | 4/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2022 | Connected |  | N
National Grid | EASTON | 444420 | 02375 | 0 | Other | 05_07_1W8 | 03/14/2023 | 07/14/2023 | 84 | 74 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2023 | 08/08/2023 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 582518 | 01453 | 10 | Solar | 05_12_16W6 | 01/12/2024 | 02/07/2024 | 17 | 14 | 3 | 02/08/2024 | 02/08/2024 | 23 | 14 | 9 | 03/29/2024 | 04/26/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 04/26/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 4/26/2024 |  | 4/29/2025 | N | EXP | 365 | 06/05/2024 | 06/14/2024 | 10 | 0 | 10 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 701325 | 02169 | 11.5 | Solar | 05_09_701J1 | 06/27/2025 | 07/15/2025 | 10 | 6 | 4 | 07/16/2025 | 07/16/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 | 06/27/2025 | 9/25/2026 | Y | EXP | 365 | 12/31/2025 | 01/12/2026 | 13 | 0 | 13 |  |  | 1/13/2026 | Connected |  | N
National Grid | MALDEN | 346956 | 02148 | 499 | Solar | 05_07_92W79 | 07/14/2021 | 08/23/2021 | 28 | 19 | 9 |  |  | 58 | 32 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROYALSTON | 409760 | 01368 | 12 | Solar | 05_01_207W6 | 05/12/2022 | 05/17/2022 | 3 | 1 | 2 | 05/18/2022 | 05/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2022 |  | 10/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2022 | Connected |  | N
National Grid | NORTON | 531854 | 02760 | 5 | Solar | 05_07_1W8 | 07/25/2023 | 10/17/2023 | 58 | 52 | 6 | 10/18/2023 | 10/18/2023 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 07/25/2023 | 11/27/2024 | Y | EXP | 365 | 01/10/2024 | 01/09/2024 | 0 | 0 | 0 |  |  | 1/26/2024 | Connected |  | N
National Grid | LEOMINSTER | 587105 | 01453 | 7.68 | Solar | 05_12_16W6 | 02/23/2024 | 03/13/2024 | 13 | 9 | 4 | 03/14/2024 | 03/14/2024 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2024 |  | 4/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 712920 | 02171 | 7.25 | Solar | 05_09_701J1 | 08/18/2025 | 09/22/2025 | 2 | 0 | 2 | 09/23/2025 | 09/23/2025 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2025 | Connected |  | N
National Grid | MELROSE | 346955 | 02176 | 499 | Solar | 05_07_92W79 | 07/14/2021 | 08/04/2021 | 15 | 6 | 9 |  |  | 71 | 45 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROYALSTON | 416852 | 01368 | 9.86 | Solar | 05_01_207W6 | 03/11/2022 | 04/04/2022 | 16 | 13 | 3 | 04/05/2022 | 04/05/2022 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2022 | 03/11/2022 | 7/26/2023 | Y | EXP | 365 | 06/30/2022 | 07/20/2022 | 21 | 0 | 21 |  |  | 8/24/2022 | Connected |  | Y
National Grid | NORTON | 652949 | 02766 | 3.8 | Solar | 05_07_1W8 | 11/07/2024 | 11/25/2024 | 4 | 0 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | LEOMINSTER | 588206 | 01453 | 6 | Solar | 05_12_16W6 | 05/06/2024 | 09/17/2024 | 52 | 50 | 2 | 09/18/2024 | 09/18/2024 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2024 | 05/06/2024 | 2/18/2026 | Y | EXP | 450 | 03/27/2025 | 07/11/2025 | 107 | 0 | 107 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 687139 | 02170 | 4980 | Solar | 05_09_702W1 | 06/03/2025 | 07/09/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 07/28/2025 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MELROSE | 479156 | 02176 | 7.6 | Solar | 05_07_92W79 | 11/21/2022 | 11/28/2022 | 4 | 0 | 4 | 11/29/2022 | 11/29/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 |  | 1/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | ROYALSTON | 427452 | 01368 | 19 | Solar | 05_01_207W6 | 05/03/2022 | 06/28/2022 | 38 | 35 | 3 | 06/29/2022 | 06/29/2022 | 343 | 325 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 708135 | 02375 | 7.678 | Solar | 05_07_1W8 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 34 | 22 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | LEOMINSTER | 588827 | 01453 | 6 | Solar | 05_12_16W6 | 03/04/2024 | 03/07/2024 | 3 | 0 | 3 | 03/08/2024 | 03/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 | 03/04/2024 | 4/21/2025 | Y | EXP | 365 | 05/16/2024 | 08/21/2024 | 98 | 0 | 98 |  |  | 9/11/2024 | Connected |  | N
National Grid | QUINCY | 692776 | 02170 | 7.6 | Solar | 05_09_702W1 | 05/20/2025 | 05/28/2025 | 4 | 0 | 4 | 06/25/2025 | 06/25/2025 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 05/20/2025 | 9/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | MELROSE | 481017 | 02176 | 15.2 | Solar | 05_07_92W79 | 11/29/2022 | 12/12/2022 | 10 | 8 | 2 | 12/13/2022 | 12/13/2022 | 28 | 5 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 | 11/29/2022 | 6/15/2024 | Y | EXP | 365 | 06/15/2023 | 06/16/2023 | 2 | 0 | 2 |  |  | 7/3/2023 | Connected |  | N
National Grid | ROYALSTON | 471046 | 01368 | 6 | Solar | 05_01_207W6 | 11/20/2023 | 11/01/2022 | 1 | 0 | 1 | 11/22/2023 | 11/22/2023 | 40 | 19 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2022 | 11/20/2023 | 2/20/2025 | Y | EXP | 365 | 05/03/2024 | 05/29/2024 | 27 | 0 | 27 |  |  | 7/6/2024 | Connected |  | N
National Grid | EASTON | 591013 | 02375 | 34.6 | Solar | 05_07_20W10 | 02/19/2024 |  | 12 | 9 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 600609 | 01453 | 6 | Solar | 05_12_16W6 | 04/04/2024 | 04/10/2024 | 4 | 0 | 4 | 04/11/2024 | 04/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/04/2024 | 5/14/2026 | Y | EXP | 730 | 08/21/2024 | 10/02/2024 | 43 | 0 | 43 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 716803 | 02171 | 5.76 | Solar | 05_09_702W1 | 09/04/2025 | 10/20/2025 | 3 | 0 | 3 | 12/03/2025 | 12/03/2025 | 38 | 25 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 3/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MELROSE | 484048 | 02176 | 20 | Solar | 05_07_92W79 | 01/26/2023 | 01/31/2023 | 4 | 3 | 1 | 02/01/2023 | 02/01/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  | 3/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2023 | Connected |  | N
National Grid | ROYALSTON | 487948 | 01368 | 10 | Solar | 05_01_207W6 | 02/06/2023 | 02/08/2023 | 2 | 0 | 2 | 02/09/2023 | 02/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/06/2023 | 9/19/2024 | Y | EXP | 365 | 10/18/2023 | 11/14/2023 | 28 | 0 | 28 |  |  | 1/31/2024 | Connected |  | Y
National Grid | EASTON | 192789 | 02375 | 10 | Solar | 05_07_20W13 | 08/06/2018 | 09/10/2018 | 7 | 6 | 1 | 09/10/2018 | 09/10/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 | 08/06/2018 | 10/30/2019 | Y | EXP | 399 | 04/26/2019 | 05/17/2019 | 21 | 0 | 21 |  |  | 10/7/2019 | Connected |  | N
National Grid | LEOMINSTER | 616847 | 01453 | 7.6 | Solar | 05_12_16W6 | 06/10/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | QUINCY | 724125 | 02170 | 20 | Solar | 05_09_702W1 | 10/05/2025 | 10/07/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MELROSE | 585541 | 02176 | 0 | Solar | 05_07_92W79 | 01/31/2024 | 02/16/2024 | 12 | 10 | 2 | 02/20/2024 | 02/20/2024 | 46 | 41 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROYALSTON | 491121 | 01368 | 9.86 | Solar | 05_01_207W6 | 02/02/2023 | 02/06/2023 | 2 | 0 | 2 | 02/07/2023 | 02/07/2023 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2023 | 02/02/2023 | 5/31/2024 | Y | EXP | 365 | 06/01/2023 | 05/31/2023 | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | EASTON | 406009 | 02375 | 5.52 | Solar | 05_07_20W13 | 06/30/2022 |  | 156 | 17 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 628444 | 01453 | 15.2 | Solar | 05_12_16W6 | 07/29/2024 | 08/01/2024 | 1 | 0 | 1 | 12/04/2024 | 12/04/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2024 |  | 1/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | QUINCY | 725118 | 02170 | 8.7 | Solar | 05_09_702W1 | 10/08/2025 | 10/09/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  | 12/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MELROSE | 651942 | 02176 | 20 | Solar | 05_07_92W79 | 11/11/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | ATHOL | 556880 | 01037 | 9.86 | Solar | 05_01_207W6 | 10/18/2023 | 11/08/2023 | 16 | 14 | 2 | 11/09/2023 | 11/09/2023 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 |  | 1/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 408727 | 02375 | 57.6 | Solar | 05_07_20W7 | 01/31/2022 | 02/17/2022 | 13 | 8 | 5 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 648715 | 01453 | 5.76 | Solar | 05_12_16W6 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 728611 | 02170 | 3.8 | Solar | 05_09_702W1 | 10/23/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 55 | 35 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/28/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MELROSE | 174311 | 02176 | 2000 | Solar | 05_07_93W40 | 01/12/2012 | 01/12/2012 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2012 | 05/03/2012 | 63 | 0 | 63 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2012 | 01/12/2012 | 10/1/2012 | Y | STD | 10 | 09/13/2013 | 12/28/2013 | 72 | 0 | 72 | 12/27/2013 | 12/27/2013 | 12/27/2013 | Connected |  | N
National Grid | ATHOL | 571006 | 01331 | 7.6 | Solar | 05_01_207W6 | 11/27/2023 | 11/29/2023 | 3 | 2 | 1 | 11/30/2023 | 11/30/2023 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 | 11/27/2023 | 6/30/2025 | Y | EXP | 365 | 02/17/2024 | 02/16/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 515523 | 02766 | 0 | Natural Gas | 05_07_20W9 | 08/17/2023 |  | 151 | 83 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 650399 | 01453 | 9.88 | Solar | 05_12_16W6 | 11/01/2024 | 11/18/2024 | 4 | 0 | 4 | 11/19/2024 | 11/19/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 11/01/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N
National Grid | BROCKTON | 735694 | 02301 | 7.6 | Solar | 05_09_702W1 | 12/01/2025 | 12/05/2025 | 4 | 0 | 4 | 12/08/2025 | 12/08/2025 | 64 | 48 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2026 |  | 3/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MELROSE | 178473 | 02176 | 10 | Solar | 05_07_93W40 | 03/07/2018 | 03/07/2018 | 6 | 0 | 6 | 03/15/2018 | 03/15/2018 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 | 03/07/2018 | 3/12/2019 | Y | EXP | 305 |  |  | 0 | 0 | 0 |  |  | 12/14/2018 | Connected |  | N
National Grid | ATHOL | 573946 | 01331 | 0 | Battery Add-On | 05_01_207W6 | 11/28/2023 | 11/30/2023 | 2 | 0 | 2 | 12/01/2023 | 12/01/2023 | 66 | 49 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2024 | Connected |  | N
National Grid | EASTON | 736785 | 02375 | 10 | Solar | 05_07_2W1 | 11/26/2025 | 12/01/2025 | 2 | 0 | 2 | 12/02/2025 | 12/02/2025 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2026 | 11/26/2025 | 2/13/2027 | Y | EXP | 365 | 03/26/2026 |  | 7 | 0 | 7 |  |  |  | Construction |  | N
National Grid | LEOMINSTER | 651613 | 01453 | 3.8 | Solar | 05_12_16W6 | 11/20/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 740243 | 02301 | 11.5 | Solar | 05_09_702W1 | 12/15/2025 | 01/06/2026 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2026 |  | 3/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MALDEN | 187879 | 02148 | 1850 | Solar | 05_07_93W40 | 07/05/2018 | 07/05/2018 | 20 | 7 | 13 |  |  | 95 | 27 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 575385 | 01331 | 2.32 | Solar | 05_01_207W6 | 01/15/2024 | 01/24/2024 | 8 | 5 | 3 | 01/25/2024 | 01/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 01/15/2024 | 3/6/2025 | Y | EXP | 365 | 05/30/2024 | 07/01/2024 | 33 | 0 | 33 |  |  | 7/3/2024 | Connected |  | N
National Grid | EASTON | 744023 | 02375 | 13.3 | Solar | 05_07_2W1 | 01/07/2026 | 01/08/2026 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 21 | 9 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 658379 | 01453 | 7.6 | Solar | 05_12_16W6 | 12/10/2024 | 01/07/2025 | 14 | 10 | 4 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | BROCKTON | 749319 | 02301 |  | Battery Add-On | 05_09_702W1 | 02/04/2026 | 02/05/2026 | 1 | 0 | 1 | 02/06/2026 | 02/06/2026 | 28 | 12 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MALDEN | 383891 | 02148 | 8.7 | Solar | 05_07_93W40 | 09/22/2021 | 12/14/2021 | 2 | 0 | 2 | 09/27/2021 | 09/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 |  | 2/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2022 | Connected |  | N
National Grid | ATHOL | 607929 | 01331 | 10 | Solar | 05_01_207W6 | 05/01/2024 | 05/23/2024 | 9 | 3 | 6 | 05/24/2024 | 05/24/2024 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 | 05/01/2024 | 7/11/2025 | Y | EXP | 365 | 10/03/2024 | 10/22/2024 | 20 | 0 | 20 |  |  | 11/9/2024 | Connected |  | N
National Grid | EASTON | 749270 | 02375 | 13.36 | Solar | 05_07_2W1 | 02/04/2026 | 02/06/2026 | 4 | 2 | 2 | 02/23/2026 | 02/23/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LEOMINSTER | 663005 | 01453 | 7.6 | Solar | 05_12_16W6 | 12/30/2024 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2025 | Connected |  | N
National Grid | BROCKTON | 753063 | 02301 | 11.5 | Solar | 05_09_702W1 | 02/25/2026 | 03/03/2026 | 2 | 0 | 2 | 03/12/2026 | 03/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MALDEN | 404082 | 02148 | 240 | Solar | 05_07_93W40 | 08/01/2022 | 08/29/2022 | 21 | 11 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 650816 | 01331 | 10 | Solar | 05_01_207W6 | 10/30/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 10/30/2024 | 12/30/2025 | Y | EXP | 365 | 03/13/2025 | 03/28/2025 | 16 | 0 | 16 |  |  | 4/5/2025 | Connected |  | N
National Grid | ROCKLAND | 174807 | 02370 | 20 | Solar | 05_07_2W1 | 01/22/2013 | 01/22/2013 | 7 | 0 | 7 | 02/01/2013 | 02/01/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2013 |  | 4/30/2013 | N | EXP | 36 |  |  | 0 | 0 | 0 | 3/25/2013 | 3/25/2013 | 4/29/2013 | Connected |  | N
National Grid | LEOMINSTER | 675526 | 01453 | 15.2 | Solar | 05_12_16W6 | 03/04/2025 | 04/09/2025 | 27 | 22 | 5 | 04/10/2025 | 04/10/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N
National Grid | BROCKTON | 174649 | 02301 | 1000 | Solar | 05_09_702W1 | 04/04/2011 | 04/04/2011 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2011 | 09/08/2011 | 34 | 0 | 34 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2012 | 04/04/2011 | 12/31/2012 | Y | STD | 278 | 05/24/2013 | 10/17/2013 | 99 | 0 | 99 | 10/14/2013 | 10/14/2013 | 10/25/2013 | Connected |  | N
National Grid | MELROSE | 412222 | 02176 | 0 | Battery Add-On | 05_07_93W40 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/14/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 659044 | 01331 | 7.6 | Solar | 05_01_207W6 | 12/06/2024 | 12/23/2024 | 8 | 3 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKLAND | 175276 | 02370 | 42.57 | Solar | 05_07_2W1 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2014 |  | 11/28/2014 | N | EXP | 66 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/5/2015 | Connected |  | N
National Grid | LEOMINSTER | 679311 | 01453 | 11.5 | Solar | 05_12_16W6 | 03/20/2025 | 04/07/2025 | 1 | 0 | 1 | 07/16/2025 | 07/16/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2025 | Connected |  | N
National Grid | HOLBROOK | 174984 | 02343 | 1000 | Solar | 05_09_702W1 | 11/10/2011 | 11/10/2011 | 623 | 51 | 572 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 421780 | 02176 | 9.45 | Solar | 05_07_93W40 | 05/05/2022 | 05/09/2022 | 1 | 1 | 0 | 05/10/2022 | 05/10/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2022 |  | 7/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2023 | Connected |  | N
National Grid | ATHOL | 666989 | 01331 | 3.8 | Solar | 05_01_207W6 | 01/21/2025 | 03/11/2025 | 21 | 16 | 5 | 03/12/2025 | 03/12/2025 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 5/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | ROCKLAND | 176098 | 02370 | 16.77 | Solar | 05_07_2W1 | 04/07/2015 | 04/07/2015 | 4 | 1 | 3 | 04/14/2015 | 04/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2015 |  | 8/10/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 4/27/2015 | 4/27/2015 | 7/25/2016 | Connected |  | N
National Grid | LEOMINSTER | 693560 | 01453 | 7.6 | Solar | 05_12_16W6 | 05/22/2025 | 06/18/2025 | 7 | 1 | 6 | 06/20/2025 | 06/20/2025 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N
National Grid | HOLBROOK | 175201 | 02343 | 1000 | Solar | 05_09_702W1 | 04/11/2011 | 04/11/2011 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2011 | 09/08/2011 | 34 | 0 | 34 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 278 |  |  | 0 | 0 | 0 | 10/14/2013 | 10/14/2013 | 10/25/2013 | Connected |  | N
National Grid | MALDEN | 547930 | 02148 | 18.048 | Solar | 05_07_93W40 | 08/14/2023 | 08/17/2023 | 4 | 2 | 2 | 08/18/2023 | 08/18/2023 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 666673 | 01331 | 7.6 | Solar | 05_01_207W6 | 01/20/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 | 01/20/2025 | 4/10/2026 | Y | EXP | 365 | 06/12/2025 | 06/24/2025 | 13 | 0 | 13 |  |  | 8/22/2025 | Connected |  | N
National Grid | ROCKLAND | 176759 | 02370 | 5 | Solar | 05_07_2W1 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2016 | 02/24/2016 | 3/1/2017 | Y | EXP | 327 | 01/11/2017 | 01/17/2017 | 3 | 0 | 3 | 4/8/2016 | 4/8/2016 | 1/30/2017 | Connected |  | N
National Grid | LEOMINSTER | 726424 | 01453 | 3.8 | Solar | 05_12_16W6 | 10/14/2025 | 11/17/2025 | 3 | 0 | 3 | 12/23/2025 | 12/23/2025 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 175200 | 02343 | 1000 | Solar | 05_09_702W1 | 04/11/2011 | 04/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2011 | 09/08/2011 | 34 | 0 | 34 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 278 | 05/24/2013 | 10/17/2013 | 99 | 0 | 99 | 10/14/2013 | 10/14/2013 | 10/25/2013 | Connected |  | N
National Grid | MELROSE | 563028 | 02176 | 7.25 | Solar | 05_07_93W40 | 10/17/2023 | 10/20/2023 | 4 | 1 | 3 | 10/23/2023 | 10/23/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 722918 | 01331 | 3.8 | Solar | 05_01_207W6 | 10/22/2025 | 10/27/2025 | 2 | 0 | 2 | 11/13/2025 | 11/13/2025 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 177622 | 02370 | 7.6 | Solar | 05_07_2W1 | 11/09/2017 | 11/09/2017 | 15 | 14 | 1 | 12/05/2017 | 12/05/2017 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2017 |  | 11/15/2018 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 734529 | 01453 | 15.58 | Solar | 05_12_16W7 | 11/20/2025 | 11/24/2025 | 2 | 0 | 2 | 11/25/2025 | 11/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HOLBROOK | 175979 | 02343 | 990 | Solar | 05_09_702W1 | 01/22/2015 | 01/22/2015 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/03/2015 | 03/05/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 | 06/24/2016 | 08/01/2016 | 25 | 0 | 25 | 6/24/2016 | 01/22/2015 | 6/30/2015 | Y | STD | 360 | 12/20/2016 | 05/02/2017 | 90 | 0 | 90 | 7/6/2017 | 7/6/2017 | 7/6/2017 | Connected |  | N
National Grid | MALDEN | 577762 | 02148 | 0 | Other | 05_07_93W40 | 12/21/2023 | 02/21/2024 | 39 | 30 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2024 | 02/27/2024 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 729074 | 01331 | 7.6 | Solar | 05_01_207W6 | 11/04/2025 | 11/07/2025 | 3 | 0 | 3 | 11/10/2025 | 11/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 177793 | 02370 | 10 | Solar | 05_07_2W1 | 08/02/2017 | 08/02/2017 | 8 | 8 | 0 | 08/15/2017 | 08/15/2017 | 154 | 0 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2017 | 08/02/2017 | 9/7/2018 | Y | EXP | 387 | 02/02/2018 | 02/06/2018 | 2 | 0 | 2 |  |  | 8/21/2018 | Connected |  | N
National Grid | LEOMINSTER | 174063 | 01453 | 3.8 | Solar | 05_12_16W7 | 09/27/2018 | 11/05/2018 | 24 | 20 | 4 | 11/06/2018 | 11/06/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 11/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  | 10/9/2019 | Connected |  | N
National Grid | HOLBROOK | 176330 | 02343 | 16 | Solar | 05_09_702W1 | 07/21/2015 | 07/21/2015 | 3 | 3 | 0 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 |  | 7/27/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 6/22/2016 | 6/22/2016 | 6/22/2016 | Connected |  | N
National Grid | MELROSE | 581852 | 02176 | 3.8 | Solar | 05_07_93W40 | 02/12/2024 | 02/15/2024 | 4 | 1 | 3 | 02/16/2024 | 02/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/12/2024 | 5/16/2025 | Y | EXP | 365 | 06/12/2024 | 07/03/2024 | 22 | 0 | 22 |  |  | 8/8/2024 | Connected |  | N
National Grid | ATHOL | 755188 | 01331 | 11.5 | Solar | 05_01_207W6 | 03/06/2026 | 03/11/2026 | 2 | 0 | 2 | 03/19/2026 | 03/19/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 177921 | 02370 | 10 | Solar | 05_07_2W1 | 10/23/2017 | 10/23/2017 | 2 | 0 | 2 | 11/06/2017 | 11/06/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 10/31/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | LEOMINSTER | 176757 | 01453 | 17.6 | Solar | 05_12_16W7 | 02/24/2016 | 02/24/2016 | 1 | 1 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2016 |  | 3/1/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 8/8/2016 | 8/8/2016 | 8/8/2016 | Connected |  | N
National Grid | HOLBROOK | 176337 | 02343 | 972 | Solar | 05_09_702W1 | 09/16/2015 | 09/16/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2015 | 10/20/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 | 01/27/2016 | 04/04/2016 | 46 | 0 | 46 | 9/20/2016 | 09/16/2015 | 9/22/2016 | Y | STD | 2 |  |  | 0 | 0 | 0 | 10/23/2017 | 10/23/2017 | 10/23/2017 | Connected |  | N
National Grid | MALDEN | 648554 | 02148 | 5.76 | Solar | 05_07_93W40 | 11/01/2024 | 12/04/2024 | 14 | 9 | 5 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 741523 | 01331 | 3.8 | Solar | 05_01_210L1 | 12/20/2025 | 12/24/2025 | 2 | 0 | 2 | 01/15/2026 | 01/15/2026 | 53 | 39 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ROCKLAND | 189677 | 02370 | 15.2 | Solar | 05_07_2W1 | 06/29/2018 | 06/29/2018 | 8 | 7 | 1 | 07/12/2018 | 07/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2019 | Connected |  | N
National Grid | LEOMINSTER | 177951 | 01453 | 3.8 | Solar | 05_12_16W7 | 08/24/2017 | 08/24/2017 | 9 | 9 | 0 | 09/07/2017 | 09/07/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2017 |  | 8/29/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  | 5/3/2018 | Connected |  | N
National Grid | HOLBROOK | 176673 | 02343 | 7.6 | Solar | 05_09_702W1 | 01/04/2016 | 01/04/2016 | 59 | 59 | 0 | 03/30/2016 | 03/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 |  | 1/9/2017 | N | EXP | 272 |  |  | 0 | 0 | 0 | 10/28/2016 | 10/28/2016 | 10/28/2016 | Connected |  | N
National Grid | MALDEN | 651115 | 02148 | 5.7 | Solar | 05_07_93W40 | 11/01/2024 | 11/25/2024 | 8 | 4 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 11/01/2024 | 3/29/2026 | Y | EXP | 365 | 06/13/2025 | 06/17/2025 | 5 | 0 | 5 |  |  | 6/24/2025 | Connected |  | N
National Grid | ATHOL | 742750 | 01331 | 5.584 | Solar | 05_01_210L1 | 01/08/2026 | 01/15/2026 | 4 | 2 | 2 | 01/16/2026 | 01/16/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 3/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ROCKLAND | 296127 | 02370 | 9.57 | Solar | 05_07_2W1 | 06/23/2020 | 06/29/2020 | 3 | 0 | 3 | 06/30/2020 | 06/30/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2020 | Connected |  | N
National Grid | LEOMINSTER | 183731 | 01453 | 11.4 | Solar | 05_12_16W7 | 04/25/2018 | 04/25/2018 | 3 | 0 | 3 | 07/27/2018 | 07/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 | 04/25/2018 | 11/25/2019 | Y | EXP | 482 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 11/1/2019 | Connected |  | N
National Grid | HOLBROOK | 176898 | 02343 | 10 | Solar | 05_09_702W1 | 01/25/2016 | 01/25/2016 | 1 | 1 | 0 | 01/27/2016 | 01/27/2016 | 252 | 0 | 252 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2016 |  | 1/31/2017 | N | EXP | 321 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 651299 | 02148 | 5.76 | Solar | 05_07_93W40 | 11/12/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 4/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | ATHOL | 754901 | 01331 | 19 | Solar | 05_01_210L1 | 03/05/2026 | 03/13/2026 | 5 | 1 | 4 | 03/16/2026 | 03/16/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ROCKLAND | 305147 | 02370 | 7.6 | Solar | 05_07_2W1 | 08/12/2020 | 08/17/2020 | 2 | 0 | 2 | 08/18/2020 | 08/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 | 08/12/2020 | 8/1/2021 | Y | EXP | 365 | 01/05/2021 | 01/26/2021 | 21 | 0 | 21 |  |  | 5/4/2021 | Connected |  | N
National Grid | LEOMINSTER | 207027 | 01453 | 7.6 | Solar | 05_12_16W7 | 02/14/2019 | 02/21/2019 | 3 | 3 | 0 | 02/22/2019 | 02/22/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2019 | 02/14/2019 | 10/11/2019 | Y | EXP | 226 | 08/21/2019 | 08/29/2019 | 8 | 0 | 8 |  |  | 9/20/2019 | Connected |  | N
National Grid | HOLBROOK | 177446 | 02343 | 311 | Solar | 05_09_702W1 | 09/16/2016 | 09/16/2016 | 0 | 0 | 0 | 09/16/2016 | 09/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2016 | 09/16/2016 | 9/21/2017 | Y | EXP | 337 | 10/16/2017 | 12/06/2017 | 30 | 0 | 30 | 12/13/2017 | 12/13/2017 | 12/13/2017 | Connected |  | N
National Grid | EVERETT | 653385 | 02149 | 8.41 | Solar | 05_07_93W40 | 11/12/2024 | 01/24/2025 | 34 | 31 | 3 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 754832 | 01331 | 15.2 | Solar | 05_01_210L1 | 03/05/2026 | 03/09/2026 | 2 | 0 | 2 | 03/10/2026 | 03/10/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ROCKLAND | 324728 | 02370 | 7.6 | Solar | 05_07_2W1 | 11/30/2020 | 12/03/2020 | 2 | 0 | 2 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 | 11/30/2020 | 7/30/2021 | Y | EXP | 365 | 04/27/2021 | 05/19/2021 | 22 | 0 | 22 |  |  | 7/15/2021 | Connected |  | N
National Grid | LEOMINSTER | 220757 | 01453 | 7.6 | Solar | 05_12_16W7 | 08/22/2019 |  | 44 | 39 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 177619 | 02343 | 2200 | Solar | 05_09_702W1 | 11/08/2017 | 11/08/2017 | 55 | 30 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2018 | 04/11/2018 | 37 | 22 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/14/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 663118 | 02151 | 5.12 | Solar | 05_07_93W40 | 12/30/2024 | 01/29/2025 | 4 | 0 | 4 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 | 12/30/2024 | 4/8/2026 | Y | EXP | 365 | 06/26/2025 | 11/21/2025 | 149 | 0 | 149 |  |  | 12/15/2025 | Connected |  | N
National Grid | ATHOL | 174640 | 01331 | 1720 | Solar | 05_01_210L1 | 12/03/2013 | 12/03/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2013 | 01/03/2014 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2015 | 12/03/2013 | 12/31/2016 | Y | STD | 477 | 11/30/2016 | 01/09/2017 | 26 | 0 | 26 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | ROCKLAND | 494242 | 02370 | 10 | Solar | 05_07_2W1 | 02/07/2023 | 02/09/2023 | 2 | 0 | 2 | 02/10/2023 | 02/10/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2023 | Connected |  | N
National Grid | PEPPERELL | 214054 | 01463 | 10 | Solar | 05_12_16W7 | 03/25/2019 | 04/15/2019 | 15 | 14 | 1 | 04/16/2019 | 04/16/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2019 | 03/25/2019 | 12/16/2019 | Y | EXP | 241 | 06/27/2019 | 08/21/2019 | 55 | 0 | 55 |  |  | 8/24/2019 | Connected |  | N
National Grid | HOLBROOK | 178106 | 02343 | 3230 | Solar | 05_09_702W1 | 09/08/2017 | 10/31/2017 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2017 | 11/15/2017 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/16/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 672326 | 02149 | 9.75 | Solar | 05_07_93W40 | 02/19/2025 | 03/03/2025 | 6 | 3 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | ATHOL | 175466 | 01331 | 150 | Solar | 05_01_210L1 | 09/24/2014 | 09/24/2014 | 7 | 0 | 7 | 10/06/2014 | 10/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2014 |  | 1/30/2015 | N | EXP | 105 |  |  | 0 | 0 | 0 | 1/30/2015 | 1/30/2015 | 2/25/2015 | Connected |  | N
National Grid | ROCKLAND | 493719 | 02370 | 10 | Solar | 05_07_2W1 | 01/31/2023 | 02/07/2023 | 5 | 4 | 1 | 02/08/2023 | 02/08/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2023 |  | 3/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2023 | Connected |  | N
National Grid | DUNSTABLE | 229044 | 01827 | 7.245 | Solar | 05_12_16W7 | 06/24/2019 | 06/24/2019 | 0 | 0 | 0 | 06/25/2019 | 06/25/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 178105 | 02343 | 8730 | Solar | 05_09_702W1 | 09/08/2017 | 10/24/2017 | 30 | 20 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2017 | 11/15/2017 | 10 | 0 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/16/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 680985 | 02149 | 7.6 | Solar | 05_07_93W40 | 03/27/2025 | 04/18/2025 | 4 | 0 | 4 | 04/30/2025 | 04/30/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 175821 | 01331 | 5 | Solar | 05_01_210L1 | 07/31/2015 | 07/31/2015 | 2 | 2 | 0 | 08/05/2015 | 08/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2015 | 07/31/2015 | 8/8/2016 | Y | EXP | 356 |  |  | 0 | 0 | 0 | 8/18/2015 | 8/18/2015 | 6/17/2016 | Connected |  | N
National Grid | ROCKLAND | 512728 | 02370 | 6 | Solar | 05_07_2W1 | 04/11/2023 | 04/14/2023 | 3 | 0 | 3 | 04/18/2023 | 04/18/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 269654 | 01827 | 7.6 | Solar | 05_12_16W7 | 05/19/2020 | 07/01/2020 | 29 | 26 | 3 | 07/02/2020 | 07/02/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 | 05/19/2020 | 7/28/2021 | Y | EXP | 365 | 12/05/2020 | 01/04/2021 | 30 | 0 | 30 |  |  | 6/3/2021 | Connected |  | N
National Grid | HOLBROOK | 178458 | 02343 | 10 | Solar | 05_09_702W1 | 01/18/2018 | 01/18/2018 | 10 | 2 | 8 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2018 |  | 1/23/2019 | N | EXP | 302 |  |  | 0 | 0 | 0 |  |  | 7/26/2018 | Connected |  | N
National Grid | MALDEN | 175317 | 02148 | 417.6 | Solar | 05_07_93W41 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 12/24/2014 | 12/24/2014 | 12/31/2014 | Connected |  | N
National Grid | ATHOL | 176061 | 01331 | 900 | Solar | 05_01_210L1 | 03/27/2015 | 03/27/2015 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2015 | 05/05/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2016 | 03/27/2015 | 8/8/2015 | Y | STD | 156 | 11/30/2016 | 01/09/2017 | 26 | 0 | 26 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | ROCKLAND | 513638 | 02370 | 7.6 | Solar | 05_07_2W1 | 05/01/2023 | 05/19/2023 | 14 | 13 | 1 | 05/22/2023 | 05/22/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 | 05/01/2023 | 8/24/2024 | Y | EXP | 365 | 09/28/2023 | 10/09/2023 | 12 | 0 | 12 |  |  | 10/24/2023 | Connected |  | N
National Grid | PEPPERELL | 298842 | 01463 | 7.6 | Solar | 05_12_16W7 | 06/29/2020 | 08/24/2020 | 39 | 38 | 1 | 08/25/2020 | 08/25/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 185392 | 02343 | 4998 | Solar | 05_09_702W1 | 06/29/2018 | 06/29/2018 | 32 | 28 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2018 | 10/12/2018 | 62 | 39 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176195 | 02151 | 800 | Solar | 05_07_93W41 | 02/04/2015 | 02/04/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2015 | 03/12/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 176231 | 01331 | 24 | Solar | 05_01_210L1 | 02/13/2015 | 02/13/2015 | 4 | 0 | 4 | 02/23/2015 | 02/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2015 |  | 6/30/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 3/10/2015 | 3/10/2015 | 8/19/2015 | Connected |  | N
National Grid | ROCKLAND | 519721 | 02370 | 7.6 | Solar | 05_07_2W1 | 04/24/2023 | 05/25/2023 | 24 | 22 | 2 | 05/26/2023 | 05/26/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 04/24/2023 | 7/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2023 | Connected |  | N
National Grid | TYNGSBORO | 310462 | 01879 | 10 | Solar | 05_12_16W7 | 10/02/2020 | 10/06/2020 | 1 | 0 | 1 | 10/07/2020 | 10/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2021 | Connected |  | Y
National Grid | HOLBROOK | 188028 | 02343 | 5000 | Solar | 05_09_702W1 | 06/13/2018 | 06/13/2018 | 21 | 21 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/16/2018 | 08/15/2018 | 23 | 16 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176194 | 02151 | 990 | Solar | 05_07_93W41 | 02/04/2015 | 02/04/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2015 | 03/12/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 176229 | 01331 | 17.6 | Solar | 05_01_210L1 | 02/11/2015 | 02/11/2015 | 4 | 2 | 2 | 02/19/2015 | 02/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2015 |  | 6/30/2015 | N | EXP | 130 |  |  | 0 | 0 | 0 | 10/1/2015 | 10/1/2015 | 4/12/2016 | Connected |  | N
National Grid | HANOVER | 530297 | 02339 | 18.85 | Solar | 05_07_2W1 | 06/05/2023 | 06/29/2023 | 17 | 16 | 1 | 06/30/2023 | 06/30/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 |  | 8/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2023 | Connected |  | N
National Grid | TYNGSBORO | 316112 | 01879 | 10 | Solar | 05_12_16W7 | 12/18/2020 | 12/30/2020 | 6 | 0 | 6 | 12/31/2020 | 12/31/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/18/2020 | 6/15/2022 | Y | EXP | 365 | 08/02/2021 | 08/27/2021 | 23 | 1 | 22 |  |  | 9/13/2021 | Connected |  | N
National Grid | HOLBROOK | 200891 | 02343 | 0 | Solar | 05_09_702W1 | 11/13/2018 | 12/04/2018 | 7 | 0 | 7 | 12/05/2018 | 12/05/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | REVERE | 609078 | 02151 | 3.8 | Solar | 05_07_93W41 | 05/06/2024 | 06/11/2024 | 6 | 4 | 2 | 06/12/2024 | 06/12/2024 | 38 | 22 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 176299 | 01331 | 300 | Solar | 05_01_210L1 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 | 09/14/2015 | 09/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 | 09/11/2015 | 9/19/2016 | Y | EXP | 299 |  |  | 0 | 0 | 0 | 11/25/2015 | 11/25/2015 | 5/2/2016 | Connected |  | N
National Grid | ROCKLAND | 585200 | 02370 | 6.09 | Solar | 05_07_2W1 | 01/24/2024 | 01/30/2024 | 4 | 0 | 4 | 01/31/2024 | 01/31/2024 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 01/24/2024 | 3/9/2025 | Y | EXP | 365 | 04/18/2024 | 05/07/2024 | 20 | 0 | 20 |  |  | 5/14/2024 | Connected |  | N
National Grid | DUNSTABLE | 327499 | 01827 | 7.6 | Solar | 05_12_16W7 | 12/09/2020 | 12/13/2020 | 2 | 0 | 2 | 12/14/2020 | 12/14/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 222507 | 02343 | 7.6 | Solar | 05_09_702W1 | 05/07/2019 | 05/09/2019 | 2 | 2 | 0 | 05/10/2019 | 05/10/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2019 | 05/07/2019 | 1/22/2020 | Y | EXP | 236 | 08/21/2019 | 10/10/2019 | 50 | 0 | 50 |  |  | 10/29/2019 | Connected |  | N
National Grid | REVERE | 676983 | 02151 | 750 | Solar | 05_07_93W42 | 04/08/2025 | 06/25/2025 | 53 | 43 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2025 | 07/23/2025 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATHOL | 176277 | 01331 | 20 | Solar | 05_01_210L1 | 05/05/2015 | 05/05/2015 | 50 | 50 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 585093 | 02351 | 0 | Solar | 05_07_2W1 | 01/23/2024 | 01/24/2024 | 1 | 0 | 1 | 01/25/2024 | 01/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 4/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2024 | Connected |  | N
National Grid | TYNGSBORO | 328785 | 01879 | 10 | Solar | 05_12_16W7 | 12/15/2020 | 12/18/2020 | 2 | 0 | 2 | 12/21/2020 | 12/21/2020 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/15/2020 | 5/19/2022 | Y | EXP | 365 | 04/21/2021 | 05/11/2021 | 20 | 0 | 20 |  |  | 9/20/2021 | Connected |  | Y
National Grid | HOLBROOK | 238129 | 02343 | 25 | Solar | 05_09_702W1 | 06/18/2019 | 07/10/2019 | 15 | 15 | 0 | 07/11/2019 | 07/11/2019 | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2019 |  | 8/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 741952 | 02149 | 11.52 | Solar | 05_07_93W42 | 12/23/2025 | 01/20/2026 | 17 | 17 | 0 | 01/21/2026 | 01/21/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 | 12/23/2025 | 2/18/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ATHOL | 176396 | 01331 | 10 | Solar | 05_01_210L1 | 03/10/2016 | 03/10/2016 | 5 | 5 | 0 | 03/17/2016 | 03/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2016 | 03/10/2016 | 3/15/2017 | Y | EXP | 348 | 09/23/2016 | 11/08/2016 | 31 | 0 | 31 | 6/30/2016 | 6/30/2016 | 7/11/2016 | Connected |  | N
National Grid | ABINGTON | 586498 | 02351 | 10 | Solar | 05_07_2W1 | 02/06/2024 | 02/20/2024 | 10 | 7 | 3 | 02/21/2024 | 02/21/2024 | 144 | 101 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 336201 | 01827 | 7.6 | Solar | 05_12_16W7 | 01/15/2021 | 01/25/2021 | 4 | 0 | 4 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2021 | 01/15/2021 | 4/9/2022 | Y | EXP | 365 | 08/06/2021 | 12/21/2021 | 137 | 7 | 130 |  |  | 2/26/2022 | Connected |  | N
National Grid | HOLBROOK | 280094 | 02343 | 3.8 | Solar | 05_09_702W1 | 05/27/2020 | 05/28/2020 | 1 | 1 | 0 | 05/29/2020 | 05/29/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2020 |  | 5/27/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 757659 | 02149 | 11.5 | Solar | 05_07_93W42 | 03/19/2026 | 03/25/2026 | 3 | 0 | 3 | 03/26/2026 | 03/26/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ATHOL | 176728 | 01331 | 40 | Solar | 05_01_210L1 | 04/25/2016 | 04/25/2016 | 3 | 3 | 0 | 04/29/2016 | 04/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2016 | 04/25/2016 | 5/1/2017 | Y | EXP | 361 | 07/19/2016 | 09/12/2016 | 38 | 0 | 38 | 1/5/2017 | 1/5/2017 | 1/5/2017 | Connected |  | N
National Grid | ABINGTON | 597249 | 02351 | 6.96 | Solar | 05_07_2W1 | 04/18/2024 | 05/10/2024 | 17 | 15 | 2 | 05/13/2024 | 05/13/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 04/18/2024 | 6/6/2025 | Y | EXP | 365 | 09/12/2024 | 10/15/2024 | 34 | 0 | 34 |  |  | 10/23/2024 | Connected |  | N
National Grid | DUNSTABLE | 343326 | 01827 | 6 | Solar | 05_12_16W7 | 03/31/2021 | 04/07/2021 | 4 | 0 | 4 | 04/08/2021 | 04/08/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2021 |  | 5/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2021 | Connected |  | N
National Grid | HOLBROOK | 297385 | 02343 | 4950 | Other | 05_09_702W1 | 08/17/2020 | 09/24/2020 | 25 | 20 | 5 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 174654 | 02151 | 266 | Solar | 05_07_93W42 | 08/21/2012 | 08/21/2012 | 8 | 0 | 8 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2012 |  | 11/1/2012 | N | EXP | 40 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | N
National Grid | ATHOL | 176797 | 01331 | 6 | Solar | 05_01_210L1 | 02/25/2016 | 02/25/2016 | 1 | 1 | 0 | 02/29/2016 | 02/29/2016 | 291 | 0 | 291 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/25/2016 | 5/31/2017 | Y | EXP | 422 | 03/16/2017 | 05/08/2017 | 36 | 0 | 36 | 4/4/2016 | 4/4/2016 |  | Withdrawn |  | N
National Grid | ABINGTON | 608256 | 02351 | 15.6 | Solar | 05_07_2W1 | 05/16/2024 | 05/17/2024 | 1 | 0 | 1 | 05/20/2024 | 05/20/2024 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 345364 | 01879 | 3.8 | Solar | 05_12_16W7 | 03/19/2021 | 03/29/2021 | 6 | 6 | 0 | 03/30/2021 | 03/30/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 03/19/2021 | 7/30/2022 | Y | EXP | 365 | 06/05/2021 | 06/18/2021 | 14 | 0 | 14 |  |  | 9/16/2021 | Connected |  | N
National Grid | HOLBROOK | 305628 | 02343 | 9.8 | Solar | 05_09_702W1 | 08/07/2020 | 08/10/2020 | 0 | 0 | 0 | 08/11/2020 | 08/11/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 |  | 2/26/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2021 | Connected |  | N
National Grid | REVERE | 174941 | 02151 | 34.2 | Solar | 05_07_93W42 | 10/13/2011 | 10/13/2011 | 0 | 0 | 0 | 11/09/2011 | 11/09/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2012 |  | 11/30/2012 | N | EXP | 4 |  |  | 0 | 0 | 0 | 7/1/2013 | 7/1/2013 | 12/16/2014 | Connected |  | N
National Grid | ATHOL | 177009 | 01331 | 18 | Solar | 05_01_210L1 | 10/13/2016 | 10/13/2016 | 1 | 1 | 0 | 10/17/2016 | 10/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2016 |  | 10/19/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 1/5/2017 | 1/5/2017 | 1/5/2017 | Connected |  | N
National Grid | ABINGTON | 634810 | 02351 | 10 | Solar | 05_07_2W1 | 08/22/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 378586 | 01827 | 7.6 | Solar | 05_12_16W7 | 09/13/2021 | 01/10/2022 | 2 | 0 | 2 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2021 | 09/13/2021 | 8/30/2023 | Y | EXP | 365 | 02/22/2022 | 04/06/2022 | 43 | 0 | 43 |  |  | 9/3/2022 | Connected |  | N
National Grid | HOLBROOK | 352917 | 02343 | 10 | Solar | 05_09_702W1 | 04/29/2021 | 04/30/2021 | 1 | 1 | 0 | 05/03/2021 | 05/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 | 04/29/2021 | 10/4/2022 | Y | EXP | 365 | 08/11/2021 | 10/04/2021 | 53 | 3 | 50 |  |  | 10/5/2021 | Connected |  | N
National Grid | REVERE | 174940 | 02151 | 60 | Solar | 05_07_93W42 | 10/13/2011 | 10/13/2011 | 0 | 0 | 0 | 11/09/2011 | 11/09/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 12/10/2014 | 12/10/2014 | 12/16/2014 | Connected |  | N
National Grid | ATHOL | 177032 | 01331 | 10 | Solar | 05_01_210L1 | 07/26/2016 | 07/26/2016 | 3 | 3 | 0 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2016 | 07/26/2016 | 7/31/2017 | Y | EXP | 360 | 12/29/2016 | 01/05/2017 | 4 | 0 | 4 | 2/16/2017 | 2/16/2017 | 2/16/2017 | Connected |  | N
National Grid | ABINGTON | 639943 | 02351 | 7.6 | Solar | 05_07_2W1 | 09/12/2024 | 01/29/2025 | 79 | 78 | 1 | 01/30/2025 | 01/30/2025 | 66 | 51 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 397076 | 01827 | 6 | Solar | 05_12_16W7 | 01/26/2022 | 02/02/2022 | 5 | 0 | 5 | 02/03/2022 | 02/03/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2022 | 01/26/2022 | 5/26/2024 | Y | EXP | 365 | 10/05/2022 | 01/30/2023 | 118 | 0 | 118 |  |  | 9/18/2023 | Connected |  | N
National Grid | HOLBROOK | 360037 | 02343 | 11.4 | Solar | 05_09_702W1 | 05/24/2021 | 06/02/2021 | 6 | 6 | 0 | 06/03/2021 | 06/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2021 |  | 7/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2022 | Connected |  | N
National Grid | EVERETT | 175561 | 02149 | 996 | Solar | 05_07_93W42 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2014 | 09/09/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 177416 | 01331 | 995 | Landfill Gas | 05_01_210L1 | 09/15/2016 | 09/15/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2016 | 10/19/2016 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/20/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 642300 | 02351 | 7.6 | Solar | 05_07_2W1 | 09/30/2024 | 10/25/2024 | 4 | 2 | 2 | 10/28/2024 | 10/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 478025 | 01827 | 15.2 | Solar | 05_12_16W7 | 11/16/2022 | 11/17/2022 | 1 | 0 | 1 | 11/18/2022 | 11/18/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  | 12/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | HOLBROOK | 363344 | 02343 | 10 | Solar | 05_09_702W1 | 06/24/2021 | 06/29/2021 | 3 | 0 | 3 | 06/30/2021 | 06/30/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2021 | 06/24/2021 | 11/9/2022 | Y | EXP | 365 | 09/24/2021 | 11/04/2021 | 42 | 4 | 38 |  |  | 11/10/2021 | Connected |  | N
National Grid | EVERETT | 175560 | 02149 | 996 | Solar | 05_07_93W42 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 106 | 0 | 106 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 177490 | 01331 | 3.8 | Solar | 05_01_210L1 | 09/23/2016 | 09/23/2016 | 3 | 3 | 0 | 09/29/2016 | 09/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 | 09/23/2016 | 10/1/2017 | Y | EXP | 361 | 04/10/2017 | 04/25/2017 | 10 | 0 | 10 | 5/17/2017 | 5/17/2017 | 5/17/2017 | Connected |  | N
National Grid | ABINGTON | 646480 | 02351 | 10 | Solar | 05_07_2W1 | 10/24/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 | 10/24/2024 | 1/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 485036 | 01879 | 7.6 | Solar | 05_12_16W7 | 01/04/2023 | 03/06/2023 | 41 | 35 | 6 | 03/07/2023 | 03/07/2023 | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2023 |  | 9/16/2024 | N | EXP | 500 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 375005 | 02343 | 17.28 | Solar | 05_09_702W1 | 08/19/2021 | 09/10/2021 | 15 | 13 | 2 | 09/13/2021 | 09/13/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 11/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2022 | Connected |  | N
National Grid | EVERETT | 175707 | 02149 | 996 | Solar | 05_07_93W42 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 11/26/2014 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 |  | 12/31/2016 | N | STD | 620 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 177812 | 01331 | 15.2 | Solar | 05_01_210L1 | 03/31/2017 | 03/31/2017 | 5 | 2 | 3 | 04/07/2017 | 04/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 4/5/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 | 8/22/2017 | 8/22/2017 | 8/22/2017 | Connected |  | N
National Grid | WHITMAN | 648675 | 02382 | 5.76 | Solar | 05_07_2W1 | 10/22/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 530667 | 01827 | 10 | Solar | 05_12_16W7 | 06/09/2023 | 06/13/2023 | 2 | 0 | 2 | 06/14/2023 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 483184 | 02343 | 6 | Solar | 05_09_702W1 | 12/07/2022 | 12/12/2022 | 4 | 3 | 1 | 12/13/2022 | 12/13/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2023 |  | 8/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N
National Grid | EVERETT | 175705 | 02149 | 996 | Solar | 05_07_93W42 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 11/26/2014 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 |  | 12/31/2016 | N | STD | 620 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 177964 | 01366 | 6 | Solar | 05_01_210L1 | 02/25/2016 | 02/25/2016 | 0 | 0 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/25/2016 | 4/26/2018 | Y | EXP | 752 | 03/16/2017 | 05/08/2017 | 36 | 0 | 36 | 4/21/2017 | 4/21/2017 | 6/20/2017 | Connected |  | N
National Grid | WHITMAN | 654539 | 02382 | 3.8 | Solar | 05_07_2W1 | 11/18/2024 | 12/20/2024 | 3 | 0 | 3 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 551574 | 01463 | 10 | Solar | 05_12_16W7 | 09/13/2023 | 10/02/2023 | 14 | 12 | 2 | 10/03/2023 | 10/03/2023 | 22 | 0 | 22 | 11/16/2023 | 02/21/2024 | 65 | 3 | 62 |  |  | 0 | 0 | 0 | 02/21/2024 | 65 | 3 | 62 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 4/11/2025 | N | EXP | 365 | 05/21/2024 | 11/05/2024 | 169 | 0 | 169 |  |  | 8/4/2024 | Connected |  | N
National Grid | HOLBROOK | 490479 | 02343 | 15.08 | Solar | 05_09_702W1 | 01/06/2023 | 01/09/2023 | 1 | 0 | 1 | 01/10/2023 | 01/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2023 |  | 3/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | Y
National Grid | REVERE | 176336 | 02151 | 996 | Solar | 05_07_93W42 | 09/17/2015 | 09/17/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/17/2015 | 10/15/2015 | 20 | 20 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2016 | 09/17/2015 | 9/22/2016 | Y | STD | 176 | 09/19/2016 | 12/19/2016 | 62 | 0 | 62 | 12/30/2016 | 12/30/2016 | 12/30/2016 | Connected |  | N
National Grid | ATHOL | 178622 | 01331 | 7.6 | Solar | 05_01_210L1 | 02/01/2018 | 02/01/2018 | 19 | 0 | 19 | 03/02/2018 | 03/02/2018 | 189 | 0 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2018 |  | 2/7/2019 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 658902 | 02351 | 3.8 | Solar | 05_07_2W1 | 12/06/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 | 12/06/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | DUNSTABLE | 569775 | 01827 | 6 | Solar | 05_12_16W7 | 11/22/2023 | 12/05/2023 | 8 | 4 | 4 | 12/06/2023 | 12/06/2023 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 | 11/22/2023 | 4/23/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2024 | Connected |  | N
National Grid | HOLBROOK | 506129 | 02343 | 10 | Solar | 05_09_702W1 | 05/08/2023 | 05/09/2023 | 1 | 0 | 1 | 05/10/2023 | 05/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2023 | 05/08/2023 | 7/12/2024 | Y | EXP | 365 | 09/07/2023 | 10/25/2023 | 49 | 0 | 49 |  |  | 10/27/2023 | Connected |  | N
National Grid | EVERETT | 177048 | 02149 | 1320 | Solar | 05_07_93W42 | 10/17/2016 | 10/17/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/23/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 184039 | 01331 | 4500 | Solar | 05_01_210L1 | 04/28/2018 | 04/28/2018 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2018 | 07/16/2018 | 13 | 5 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2019 | 04/28/2018 | 12/31/2020 | Y | STD | 415 | 02/19/2020 | 08/01/2020 | 163 | 0 | 163 |  |  | 12/31/2020 | Connected |  | N
National Grid | ABINGTON | 660855 | 02351 | 10 | Solar | 05_07_2W1 | 12/16/2024 |  | 65 | 65 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 570139 | 01827 | 6 | Solar | 05_12_16W7 | 11/20/2023 | 11/30/2023 | 7 | 2 | 5 | 12/01/2023 | 12/01/2023 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 522009 | 02343 | 10 | Solar | 05_09_702W1 | 05/18/2023 |  | 255 | 24 | 231 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 177339 | 02148 | 36 | Solar | 05_07_93W42 | 09/01/2016 | 09/01/2016 | 2 | 2 | 0 | 09/06/2016 | 09/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2016 | 09/01/2016 | 9/6/2017 | Y | EXP | 363 | 10/14/2016 | 10/26/2016 | 8 | 0 | 8 | 7/24/2017 | 7/24/2017 | 7/26/2017 | Connected |  | N
National Grid | ATHOL | 190303 | 01331 | 3.8 | Solar | 05_01_210L1 | 07/10/2018 | 09/11/2018 | 14 | 14 | 0 | 09/12/2018 | 09/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 664192 | 02351 | 15.2 | Solar | 05_07_2W1 | 02/17/2025 |  | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 589342 | 01827 | 6 | Solar | 05_12_16W7 | 02/29/2024 | 03/04/2024 | 2 | 0 | 2 | 03/05/2024 | 03/05/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/29/2024 | 3/12/2025 | Y | EXP | 365 | 03/20/2024 | 05/02/2024 | 44 | 0 | 44 |  |  | 5/12/2024 | Connected |  | N
National Grid | HOLBROOK | 526873 | 02343 | 6 | Solar | 05_09_702W1 | 05/16/2023 | 06/21/2023 | 14 | 12 | 2 | 06/22/2023 | 06/22/2023 | 110 | 89 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 |  | 12/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N
National Grid | MALDEN | 178089 | 02148 | 756 | Solar | 05_07_93W42 | 07/06/2017 | 07/06/2017 | 81 | 81 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 |  | 1/13/2020 | N | CMPX | 549 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 222601 | 01331 | 0 | Solar | 05_01_210L1 | 04/25/2019 | 05/06/2019 | 6 | 0 | 6 | 05/07/2019 | 05/07/2019 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 |  | 8/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 664754 | 02351 | 6.96 | Solar | 05_07_2W1 | 01/09/2025 | 01/14/2025 | 4 | 3 | 1 | 01/15/2025 | 01/15/2025 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N
National Grid | TYNGSBORO | 590680 | 01879 | 6 | Solar | 05_12_16W7 | 02/20/2024 | 03/15/2024 | 19 | 18 | 1 | 03/18/2024 | 03/18/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 11/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 557213 | 02343 | 10 | Solar | 05_09_702W1 | 10/25/2023 | 11/14/2023 | 14 | 13 | 1 | 11/15/2023 | 11/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2023 |  | 1/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2024 | Connected |  | N
National Grid | MALDEN | 292499 | 02148 | 0 | Solar | 05_07_93W42 | 05/19/2020 | 05/20/2020 | 1 | 1 | 0 | 05/21/2020 | 05/21/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2020 |  | 5/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2020 | Connected |  | N
National Grid | ATHOL | 274504 | 01331 | 6.38 | Solar | 05_01_210L1 | 03/12/2020 | 03/13/2020 | 1 | 1 | 0 | 03/16/2020 | 03/16/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2020 | 03/12/2020 | 3/12/2021 | Y | EXP | 365 | 06/30/2020 | 07/16/2020 | 16 | 0 | 16 |  |  | 7/20/2020 | Connected |  | N
National Grid | ABINGTON | 683806 | 02351 | 4998 | Other | 05_07_2W1 | 10/16/2025 | 12/04/2025 | 31 | 24 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2025 | 12/30/2025 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 591953 | 01827 | 12 | Solar | 05_12_16W7 | 02/22/2024 | 04/29/2024 | 46 | 26 | 20 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  | 5/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 530162 | 02343 | 10 | Solar | 05_09_702W1 | 06/08/2023 | 06/13/2023 | 4 | 3 | 1 | 06/14/2023 | 06/14/2023 | 67 | 48 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2023 |  | 10/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2024 | Connected |  | N
National Grid | EVERETT | 316919 | 02149 | 0 | Battery Add-On | 05_07_93W42 | 10/05/2020 | 10/08/2020 | 3 | 1 | 2 | 10/09/2020 | 10/09/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 7/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2022 | Connected |  | N
National Grid | ATHOL | 308268 | 01331 | 15.36 | Solar | 05_01_210L1 | 08/22/2020 | 08/24/2020 | 0 | 0 | 0 | 08/25/2020 | 08/25/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 | 08/22/2020 | 9/10/2021 | Y | EXP | 365 | 05/05/2021 | 05/24/2021 | 19 | 0 | 19 |  |  | 8/30/2021 | Connected |  | N
National Grid | ABINGTON | 683462 | 02351 | 13.8 | Solar | 05_07_2W1 | 04/07/2025 | 05/15/2025 | 1 | 0 | 1 | 05/16/2025 | 05/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 596663 | 01827 | 5 | Solar | 05_12_16W7 | 04/12/2024 | 04/23/2024 | 7 | 5 | 2 | 04/24/2024 | 04/24/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 | 04/12/2024 | 5/17/2025 | Y | EXP | 365 | 08/22/2024 | 09/06/2024 | 16 | 0 | 16 |  |  | 9/27/2024 | Connected |  | N
National Grid | HOLBROOK | 544256 | 02343 | 10 | Solar | 05_09_702W1 | 07/28/2023 | 07/31/2023 | 1 | 0 | 1 | 08/01/2023 | 08/01/2023 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 |  | 10/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | MALDEN | 396664 | 02148 | 0 | Other | 05_07_93W42 | 01/14/2022 | 01/28/2022 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 03/02/2022 | 22 | 1 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 342970 | 01331 | 11.4 | Solar | 05_01_210L1 | 02/19/2021 | 03/10/2021 | 12 | 12 | 0 | 03/11/2021 | 03/11/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2021 |  | 1/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2022 | Connected |  | N
National Grid | ABINGTON | 688473 | 02351 | 10 | Solar | 05_07_2W1 | 05/02/2025 | 05/19/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | PEPPERELL | 610885 | 01463 | 6 | Solar | 05_12_16W7 | 05/14/2024 | 06/07/2024 | 3 | 0 | 3 | 06/10/2024 | 06/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | HOLBROOK | 577497 | 02343 | 7.6 | Solar | 05_09_702W1 | 01/31/2024 | 02/07/2024 | 5 | 3 | 2 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2024 | Connected |  | N
National Grid | EVERETT | 401109 | 02149 | 0 | Other | 05_07_93W42 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 03/02/2022 | 31 | 3 | 28 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 354941 | 01331 | 9.6 | Solar | 05_01_210L1 | 04/28/2021 | 04/29/2021 | 1 | 1 | 0 | 05/04/2021 | 05/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 4/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2021 | Connected |  | N
National Grid | ABINGTON | 699400 | 02351 | 7.6 | Solar | 05_07_2W1 | 06/18/2025 | 07/03/2025 | 4 | 0 | 4 | 07/30/2025 | 07/30/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 652410 | 01827 | 5.76 | Solar | 05_12_16W7 | 11/14/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | HOLBROOK | 618189 | 02343 | 7.6 | Solar | 05_09_702W1 | 06/14/2024 | 07/09/2024 | 4 | 0 | 4 | 07/10/2024 | 07/10/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 06/14/2024 | 8/14/2025 | Y | EXP | 365 | 10/03/2024 | 11/18/2024 | 47 | 0 | 47 |  |  | 12/18/2024 | Connected |  | N
National Grid | MALDEN | 443989 | 02148 | 0 | Other | 05_07_93W42 | 11/09/2022 |  | 121 | 113 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 368575 | 01331 | 80 | Solar | 05_01_210L1 | 07/09/2021 | 07/23/2021 | 9 | 3 | 6 | 07/26/2021 | 07/26/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2021 |  | 10/5/2022 | N | EXP | 365 | 05/10/2022 | 05/09/2022 | 0 | 0 | 0 |  |  | 8/17/2022 | Connected |  | N
National Grid | ABINGTON | 713260 | 02351 | 10 | Solar | 05_07_2W1 | 08/19/2025 | 09/08/2025 | 4 | 0 | 4 | 09/25/2025 | 09/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 11/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2026 | Connected |  | N
National Grid | PEPPERELL | 655522 | 01462 | 3.8 | Solar | 05_12_16W7 | 11/20/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2025 | Connected |  | N
National Grid | HOLBROOK | 627710 | 02343 | 12.18 | Solar | 05_09_702W1 | 08/29/2024 | 10/25/2024 | 3 | 1 | 2 | 10/28/2024 | 10/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2024 | 08/29/2024 | 12/16/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | EVERETT | 483153 | 02149 | 13.63 | Solar | 05_07_93W42 | 01/11/2023 | 01/12/2023 | 1 | 0 | 1 | 01/13/2023 | 01/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 3/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2023 | Connected |  | N
National Grid | ATHOL | 373203 | 01331 | 15.4 | Solar | 05_01_210L1 | 07/31/2021 | 08/02/2021 | 1 | 0 | 1 | 08/03/2021 | 08/03/2021 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2021 |  | 8/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2021 | Connected |  | Y
National Grid | ABINGTON | 718315 | 02351 | 11.4 | Solar | 05_07_2W1 | 09/10/2025 | 09/25/2025 | 4 | 0 | 4 | 10/03/2025 | 10/03/2025 | 62 | 48 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 669837 | 01827 | 10 | Solar | 05_12_16W7 | 02/04/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2025 | Connected |  | N
National Grid | HOLBROOK | 634477 | 02343 | 3.8 | Solar | 05_09_702W1 | 08/21/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 08/21/2024 | 9/24/2025 | Y | EXP | 365 | 01/08/2025 | 03/05/2025 | 57 | 0 | 57 |  |  | 3/21/2025 | Connected |  | N
National Grid | MALDEN | 504529 | 02148 | 10.44 | Solar | 05_07_93W42 | 03/15/2023 | 03/20/2023 | 4 | 1 | 3 | 03/21/2023 | 03/21/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2023 | 03/15/2023 | 6/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2023 | Connected |  | N
National Grid | ATHOL | 375882 | 01331 | 9.86 | Solar | 05_01_210L1 | 08/19/2021 | 08/24/2021 | 3 | 3 | 0 | 08/25/2021 | 08/25/2021 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 |  | 10/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2021 | Connected |  | N
National Grid | ABINGTON | 685652 | 02351 | 7.6 | Solar | 05_07_2W2 | 04/16/2025 | 05/05/2025 | 2 | 0 | 2 | 06/17/2025 | 06/17/2025 | 55 | 42 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 | 04/16/2025 | 11/14/2026 | Y | EXP | 365 | 02/13/2026 | 03/02/2026 | 18 | 0 | 18 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 705429 | 01463 | 10 | Solar | 05_12_16W7 | 07/16/2025 | 08/06/2025 | 4 | 0 | 4 | 09/03/2025 | 09/03/2025 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 | 07/16/2025 | 11/12/2026 | Y | EXP | 365 | 12/13/2025 | 01/02/2026 | 21 | 0 | 21 |  |  | 3/18/2026 | Connected |  | N
National Grid | HOLBROOK | 635856 | 02343 | 0 | Battery Add-On | 05_09_702W1 | 08/27/2024 | 08/29/2024 | 2 | 0 | 2 | 08/30/2024 | 08/30/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 531761 | 02148 | 247.3 | Solar | 05_07_93W42 | 07/19/2023 | 09/05/2023 | 33 | 24 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 376595 | 01331 | 7.6 | Solar | 05_01_210L1 | 08/18/2021 | 08/24/2021 | 4 | 4 | 0 | 08/25/2021 | 08/25/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 |  | 8/23/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 174824 | 02351 | 1000 | Natural Gas | 05_07_2W2 | 07/22/2011 | 07/22/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2011 | 09/07/2011 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2012 |  | 4/17/2012 | N | STD | 46 |  |  | 0 | 0 | 0 | 4/13/2012 | 4/13/2012 | 4/17/2012 | Connected |  | N
National Grid | DUNSTABLE | 173494 | 01827 | 10 | Solar | 05_12_16W8 | 04/24/2018 | 04/24/2018 | 1 | 0 | 1 | 05/08/2018 | 05/08/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2018 |  | 5/25/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2019 | Connected |  | N
National Grid | HOLBROOK | 642630 | 02343 | 3.8 | Solar | 05_09_702W1 | 09/24/2024 | 01/06/2025 | 20 | 15 | 5 | 01/07/2025 | 01/07/2025 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | EVERETT | 577755 | 02149 | 0 | Other | 05_07_93W42 | 12/21/2023 | 02/21/2024 | 39 | 30 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2024 | 02/27/2024 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 384470 | 01331 | 7.6 | Solar | 05_01_210L1 | 09/26/2021 |  | 34 | 26 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 175279 | 02351 | 42.57 | Solar | 05_07_2W2 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/1/2015 | Connected |  | N
National Grid | TYNGSBORO | 173375 | 01879 | 10 | Solar | 05_12_16W8 | 04/11/2018 | 04/11/2018 | 0 | 0 | 0 | 05/10/2018 | 05/10/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 642396 | 02343 | 10 | Solar | 05_09_702W1 | 09/24/2024 | 10/25/2024 | 4 | 1 | 3 | 10/28/2024 | 10/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 09/24/2024 | 1/6/2026 | Y | EXP | 365 | 09/04/2025 | 09/29/2025 | 26 | 0 | 26 |  |  | 11/11/2025 | Connected |  | N
National Grid | MALDEN | 596183 | 02148 | 7.6 | Solar | 05_07_93W42 | 04/03/2024 | 04/04/2024 | 1 | 0 | 1 | 04/05/2024 | 04/05/2024 | 134 | 25 | 109 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 392140 | 01331 | 240 | Solar | 05_01_210L1 | 11/02/2021 | 11/17/2021 | 10 | 0 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2022 | 11/02/2021 | 5/15/2023 | Y | STD | 90 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N
National Grid | WHITMAN | 348213 | 02382 | 0 | Battery Add-On | 05_07_2W2 | 03/22/2021 | 03/24/2021 | 1 | 0 | 1 | 03/25/2021 | 03/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2021 |  | 6/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 176303 | 01827 | 4.3 | Solar | 05_12_16W8 | 09/15/2015 | 09/15/2015 | 4 | 4 | 0 | 09/22/2015 | 09/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 | 09/15/2015 | 9/21/2016 | Y | EXP | 348 | 09/01/2016 | 08/31/2016 | 0 | 0 | 0 | 9/12/2016 | 9/12/2016 | 9/12/2016 | Connected |  | N
National Grid | HOLBROOK | 651707 | 02343 | 7.6 | Solar | 05_09_702W1 | 11/03/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | EVERETT | 606147 | 02149 | 7.6 | Solar | 05_07_93W42 | 04/23/2024 | 06/05/2024 | 0 | 0 | 0 | 06/06/2024 | 06/06/2024 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2024 | 04/23/2024 | 6/28/2025 | Y | EXP | 365 | 08/27/2024 | 10/15/2024 | 50 | 0 | 50 |  |  | 10/24/2024 | Connected |  | N
National Grid | ATHOL | 397552 | 01331 | 15.2 | Solar | 05_01_210L1 | 01/04/2022 | 01/05/2022 | 1 | 0 | 1 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 542638 | 02351 | 0 | Solar | 05_07_2W2 | 07/21/2023 | 07/25/2023 | 2 | 0 | 2 | 07/26/2023 | 07/26/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 10/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2024 | Connected |  | N
National Grid | TYNGSBORO | 176787 | 01879 | 6 | Solar | 05_12_16W8 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 267 | 0 | 267 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 1/20/2017 | N | EXP | 332 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 652705 | 02190 | 5.76 | Solar | 05_09_702W1 | 11/14/2024 | 11/20/2024 | 5 | 0 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 11/14/2024 | 4/8/2026 | Y | EXP | 365 | 06/04/2025 | 11/21/2025 | 171 | 0 | 171 |  |  | 12/11/2025 | Connected |  | N
National Grid | MALDEN | 621950 | 02148 | 9.28 | Solar | 05_07_93W42 | 07/02/2024 | 07/22/2024 | 13 | 11 | 2 | 07/23/2024 | 07/23/2024 | 24 | 11 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PETERSHAM | 399903 | 01366 | 0 | Solar | 05_01_210L1 | 12/13/2021 | 12/20/2021 | 6 | 4 | 2 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 | 12/13/2021 | 6/8/2023 | Y | EXP | 365 | 05/26/2022 | 06/08/2022 | 14 | 0 | 14 |  |  | 7/21/2022 | Connected |  | N
National Grid | ABINGTON | 714631 | 02351 | 5.76 | Solar | 05_07_2W2 | 08/27/2025 | 09/05/2025 | 5 | 1 | 4 | 09/08/2025 | 09/08/2025 | 53 | 37 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | DUNSTABLE | 177801 | 01827 | 15.2 | Solar | 05_12_16W8 | 10/09/2017 | 10/09/2017 | 13 | 10 | 3 | 10/25/2017 | 10/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2017 |  | 10/16/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 | 12/13/2017 | 12/13/2017 | 12/13/2017 | Connected |  | N
National Grid | WEYMOUTH | 673827 | 02190 | 5.76 | Solar | 05_09_702W1 | 02/24/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 624545 | 02151 | 7.6 | Solar | 05_07_93W42 | 07/12/2024 | 07/24/2024 | 3 | 0 | 3 | 07/25/2024 | 07/25/2024 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 | 07/12/2024 | 10/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | ATHOL | 407710 | 01331 | 7.678 | Solar | 05_01_210L1 | 05/10/2022 | 06/21/2022 | 28 | 25 | 3 | 06/22/2022 | 06/22/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2022 | Connected |  | N
National Grid | ABINGTON | 714789 | 02351 | 240 | Solar | 05_07_3W1 | 08/27/2025 | 09/30/2025 | 23 | 20 | 3 | 10/01/2025 | 10/01/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 08/27/2025 | 9/30/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | DUNSTABLE | 194567 | 01827 | 7.6 | Solar | 05_12_16W8 | 08/29/2018 | 09/10/2018 | 0 | 0 | 0 | 09/11/2018 | 09/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 | 08/29/2018 | 5/28/2019 | Y | EXP | 259 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | WEYMOUTH | 675149 | 02190 | 5.76 | Solar | 05_09_702W1 | 03/05/2025 | 03/11/2025 | 4 | 0 | 4 | 03/12/2025 | 03/12/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | REVERE | 637008 | 02151 | 10 | Solar | 05_07_93W42 | 09/05/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 39 | 25 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 410230 | 01331 | 8.64 | Solar | 05_01_210L1 | 02/23/2022 | 02/28/2022 | 3 | 0 | 3 | 03/01/2022 | 03/01/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/23/2022 | 7/28/2023 | Y | EXP | 365 | 06/04/2022 | 06/28/2022 | 24 | 0 | 24 |  |  | 1/14/2023 | Connected |  | N
National Grid | ABINGTON | 175344 | 02351 | 60 | Solar | 05_07_3W1 | 07/02/2014 | 07/02/2014 | 3 | 0 | 3 | 07/09/2014 | 07/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2014 |  | 11/28/2014 | N | EXP | 115 |  |  | 0 | 0 | 0 | 1/21/2015 | 1/21/2015 | 1/29/2015 | Connected |  | N
National Grid | TYNGSBORO | 195927 | 01879 | 7.6 | Solar | 05_12_16W8 | 09/13/2018 | 10/23/2018 | 0 | 0 | 0 | 10/24/2018 | 10/24/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 715910 | 02190 | 7.6 | Solar | 05_09_702W1 | 09/12/2025 | 10/28/2025 | 2 | 0 | 2 | 10/29/2025 | 10/29/2025 | 75 | 25 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 653517 | 02151 | 10 | Solar | 05_07_93W42 | 11/15/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/15/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 465180 | 01331 | 15.95 | Solar | 05_01_210L1 | 10/10/2022 | 10/11/2022 | 1 | 0 | 1 | 10/12/2022 | 10/12/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2022 |  | 11/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | Y
National Grid | WHITMAN | 177010 | 02382 | 720 | Solar | 05_07_3W1 | 10/14/2016 | 10/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2016 | 01/20/2017 | 58 | 44 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2018 |  | 8/15/2019 | N | STD | 555 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 203538 | 01827 | 3.8 | Solar | 05_12_16W8 | 12/27/2018 | 01/25/2019 | 19 | 19 | 0 | 01/28/2019 | 01/28/2019 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 665917 | 02190 | 996 | Solar | 05_09_702W2 | 04/17/2025 | 05/13/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/14/2025 | 06/11/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | REVERE | 657055 | 02151 | 11.52 | Solar | 05_07_93W42 | 11/26/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 477387 | 01331 | 7.6 | Solar | 05_01_210L1 | 11/15/2022 | 11/18/2022 | 3 | 0 | 3 | 11/21/2022 | 11/21/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  | 2/29/2024 | N | EXP | 410 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 195170 | 02351 | 233.1 | Solar | 05_07_3W1 | 09/13/2018 | 09/25/2018 | 8 | 6 | 2 | 09/26/2018 | 09/26/2018 | 28 | 3 | 25 | 11/20/2018 | 03/11/2019 | 74 | 24 | 50 |  |  | 0 | 0 | 0 | 03/11/2019 | 74 | 24 | 50 |  |  | 0 | 0 | 0 | 3/26/2019 |  | 8/21/2020 | N | EXP | 280 |  |  | 0 | 0 | 0 |  |  | 8/21/2020 | Connected |  | N
National Grid | TYNGSBORO | 256448 | 01879 | 10 | Solar | 05_12_16W8 | 10/02/2019 | 10/07/2019 | 2 | 0 | 2 | 10/08/2019 | 10/08/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 | 10/02/2019 | 10/13/2021 | Y | EXP | 365 | 07/02/2020 | 03/29/2021 | 271 | 5 | 266 |  |  | 6/15/2021 | Connected |  | N
National Grid | WEYMOUTH | 737148 | 02190 | 15.2 | Solar | 05_09_702W2 | 12/01/2025 | 12/02/2025 | 1 | 0 | 1 | 12/03/2025 | 12/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 676459 | 02151 | 15.2 | Solar | 05_07_93W42 | 03/10/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 4/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | ATHOL | 480125 | 01331 | 16.9 | Solar | 05_01_210L1 | 11/28/2022 | 11/30/2022 | 2 | 0 | 2 | 12/01/2022 | 12/01/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 | 11/28/2022 | 3/6/2024 | Y | EXP | 365 | 02/24/2023 | 03/06/2023 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 348184 | 02302 | 499.9 | Solar | 05_07_3W1 | 06/10/2021 | 07/28/2021 | 33 | 24 | 9 |  |  | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 269219 | 01879 | 3.8 | Solar | 05_12_16W8 | 12/18/2019 |  | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/18/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 744824 | 02169 | 7.6 | Solar | 05_09_702W2 | 01/14/2026 | 01/20/2026 | 1 | 0 | 1 | 02/06/2026 | 02/06/2026 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2026 | 01/14/2026 | 3/16/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | REVERE | 699908 | 02151 | 11.52 | Solar | 05_07_93W42 | 06/25/2025 | 07/15/2025 | 5 | 0 | 5 | 07/25/2025 | 07/25/2025 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 06/25/2025 | 9/15/2026 | Y | EXP | 365 | 11/25/2025 | 12/10/2025 | 16 | 0 | 16 |  |  | 12/23/2025 | Connected |  | N
National Grid | ATHOL | 486759 | 01331 | 13.92 | Solar | 05_01_210L1 | 06/14/2023 | 08/11/2023 | 41 | 40 | 1 | 08/14/2023 | 08/14/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 10/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2024 | Connected |  | N
National Grid | WHITMAN | 447713 | 02382 | 50 | Solar | 05_07_3W1 | 07/28/2022 | 10/27/2022 | 64 | 54 | 10 | 10/28/2022 | 10/28/2022 | 33 | 8 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 277078 | 01827 | 3.8 | Solar | 05_12_16W8 | 02/06/2020 | 02/18/2020 | 6 | 2 | 4 | 02/19/2020 | 02/19/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2020 | 02/06/2020 | 3/31/2021 | Y | EXP | 365 | 06/24/2020 | 01/11/2021 | 202 | 5 | 197 |  |  | 3/20/2021 | Connected |  | N
National Grid | QUINCY | 747023 | 02169 | 160 | Solar | 05_09_702W2 | 02/03/2026 | 03/20/2026 | 32 | 22 | 10 | 03/23/2026 | 03/23/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 673177 | 02151 | 44.6 | Solar | 05_07_93W43 | 02/20/2025 | 02/27/2025 | 6 | 3 | 3 | 02/28/2025 | 02/28/2025 | 39 | 20 | 19 | 06/02/2025 | 07/28/2025 | 39 | 0 | 39 |  |  | 0 | 0 | 0 | 07/28/2025 | 39 | 0 | 39 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | ATHOL | 551822 | 01331 | 15.2 | Solar | 05_01_210L1 | 08/29/2023 | 09/08/2023 | 8 | 6 | 2 | 09/11/2023 | 09/11/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 |  | 10/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2023 | Connected |  | N
National Grid | ABINGTON | 478161 | 02351 | 186 | Solar | 05_07_3W1 | 11/19/2022 | 12/14/2022 | 18 | 11 | 7 | 12/15/2022 | 12/15/2022 | 99 | 78 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 279550 | 01827 | 7.6 | Solar | 05_12_16W8 | 04/13/2020 | 04/27/2020 | 8 | 8 | 0 | 04/28/2020 | 04/28/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 | 04/13/2020 | 4/26/2021 | Y | EXP | 365 | 08/18/2020 | 12/12/2020 | 116 | 0 | 116 |  |  | 12/16/2020 | Connected |  | N
National Grid | QUINCY | 751317 | 02169 | 7.6 | Solar | 05_09_702W2 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 03/02/2026 | 03/02/2026 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 174721 | 02151 | 15.8 | Solar | 05_07_93W43 | 01/15/2014 | 01/15/2014 | 6 | 0 | 6 | 01/27/2014 | 01/27/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2014 |  | 3/31/2014 | N | EXP | 61 |  |  | 0 | 0 | 0 | 2/26/2014 | 2/26/2014 | 3/26/2014 | Connected |  | N
National Grid | ORANGE | 585368 | 01364 | 10 | Solar | 05_01_210L1 | 02/15/2024 | 02/28/2024 | 8 | 4 | 4 | 02/29/2024 | 02/29/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 489665 | 02351 | 499.9 | Solar | 05_07_3W1 | 01/31/2023 |  | 117 | 99 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 299562 | 01827 | 6 | Solar | 05_12_16W8 | 08/18/2020 | 08/20/2020 | 1 | 0 | 1 | 08/21/2020 | 08/21/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 | 08/18/2020 | 6/24/2022 | Y | EXP | 365 | 02/09/2021 | 04/10/2021 | 60 | 0 | 60 |  |  | 5/4/2022 | Connected |  | N
National Grid | QUINCY | 174977 | 02169 | 950 | Solar | 05_09_702W2 | 09/16/2011 | 09/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 175942 | 02151 | 22.6 | Solar | 05_07_93W43 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 | 01/29/2015 | 01/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 |  | 5/31/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 6/1/2016 | 6/1/2016 | 6/1/2016 | Connected |  | N
National Grid | ORANGE | 588595 | 01364 | 9.86 | Solar | 05_01_210L1 | 03/11/2024 | 03/13/2024 | 2 | 0 | 2 | 03/14/2024 | 03/14/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 | 03/11/2024 | 3/29/2025 | Y | EXP | 365 | 05/08/2024 | 06/21/2024 | 45 | 0 | 45 |  |  | 6/29/2024 | Connected |  | N
National Grid | WHITMAN | 671106 | 02382 | 10 | Solar | 05_07_3W1 | 02/10/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N
National Grid | DUNSTABLE | 471406 | 01827 | 14.976 | Solar | 05_12_16W8 | 11/16/2022 | 11/28/2022 | 8 | 7 | 1 | 11/29/2022 | 11/29/2022 | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 | 11/16/2022 | 7/23/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 175048 | 02169 | 750 | Solar | 05_09_702W2 | 06/08/2011 | 06/08/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2012 | 06/08/2011 | 8/19/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/14/2012 | 8/14/2012 | 7/6/2012 | Connected |  | N
National Grid | REVERE | 176335 | 02151 | 70 | Solar | 05_07_93W43 | 09/16/2015 | 09/16/2015 | 1 | 1 | 0 | 09/17/2015 | 09/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2015 |  | 9/21/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/26/2016 | 8/26/2016 | 8/26/2016 | Connected |  | N
National Grid | ATHOL | 594891 | 01331 | 20 | Solar | 05_01_210L1 | 03/06/2024 | 03/12/2024 | 4 | 1 | 3 | 03/13/2024 | 03/13/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | ABINGTON | 681036 | 02351 | 11.5 | Solar | 05_07_3W1 | 03/27/2025 | 04/25/2025 | 21 | 18 | 3 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 483382 | 01827 | 8.7 | Solar | 05_12_16W8 | 02/22/2023 | 03/01/2023 | 5 | 4 | 1 | 03/02/2023 | 03/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 175047 | 02169 | 1000 | Solar | 05_09_702W2 | 06/08/2011 | 06/08/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2012 | 06/08/2011 | 8/19/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/14/2012 | 8/14/2012 | 7/6/2012 | Connected |  | N
National Grid | REVERE | 177086 | 02151 | 720 | Solar | 05_07_93W43 | 10/18/2016 | 10/18/2016 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 613674 | 01331 | 19.1 | Solar | 05_01_210L1 | 05/28/2024 | 05/30/2024 | 2 | 0 | 2 | 05/31/2024 | 05/31/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | WHITMAN | 673424 | 02382 | 0 | Other | 05_07_3W2 | 06/25/2025 | 08/26/2025 | 42 | 32 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2025 | 09/23/2025 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | DUNSTABLE | 538307 | 01827 | 3.8 | Solar | 05_12_16W8 | 07/04/2023 | 07/06/2023 | 2 | 0 | 2 | 07/07/2023 | 07/07/2023 | 63 | 42 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 07/04/2023 | 10/14/2024 | Y | EXP | 365 | 07/09/2024 | 07/30/2024 | 22 | 0 | 22 |  |  | 8/5/2024 | Connected |  | N
National Grid | QUINCY | 175046 | 02169 | 1000 | Solar | 05_09_702W2 | 06/08/2011 | 06/08/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2012 | 06/08/2011 | 8/19/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/14/2012 | 8/14/2012 | 7/6/2012 | Connected |  | N
National Grid | REVERE | 177685 | 02151 | 10 | Solar | 05_07_93W43 | 09/29/2017 | 09/29/2017 | 4 | 0 | 4 | 10/06/2017 | 10/06/2017 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 10/7/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 617302 | 01331 | 19.195 | Solar | 05_01_210L1 | 06/26/2024 | 07/03/2024 | 5 | 2 | 3 | 07/05/2024 | 07/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2024 | Connected |  | N
National Grid | WHITMAN | 721369 | 02382 | 360 | Landfill Gas | 05_07_3W2 | 09/29/2025 | 11/24/2025 | 38 | 28 | 10 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | DUNSTABLE | 539835 | 01827 | 5.76 | Solar | 05_12_16W8 | 07/10/2023 | 07/17/2023 | 3 | 0 | 3 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2023 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | QUINCY | 176742 | 02169 | 1100 | Solar | 05_09_702W2 | 11/03/2015 | 11/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2015 | 12/04/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/8/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 184675 | 02151 | 1328 | Solar | 05_07_93W43 | 05/09/2018 | 05/09/2018 | 55 | 52 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2018 | 08/30/2018 | 24 | 15 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2019 |  | 1/2/2021 | N | STD | 654 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 652470 | 01331 | 7.6 | Solar | 05_01_210L1 | 11/06/2024 | 12/18/2024 | 28 | 25 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | HANSON | 177493 | 02341 | 42 | Solar | 05_07_3W2 | 12/13/2016 | 12/13/2016 | 0 | 0 | 0 | 12/13/2016 | 12/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2016 |  | 12/18/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 5/11/2017 | 5/11/2017 | 5/17/2017 | Connected |  | N
National Grid | DUNSTABLE | 542060 | 01827 | 3.8 | Solar | 05_12_16W8 | 07/19/2023 | 07/29/2023 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2023 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | QUINCY | 176781 | 02169 | 2000 | Solar | 05_09_702W2 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2015 | 12/04/2015 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 188219 | 02151 | 249.8 | Solar | 05_07_93W43 | 06/15/2018 | 06/15/2018 | 7 | 0 | 7 | 07/02/2018 | 07/02/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 656820 | 01364 | 6.175 | Solar | 05_01_210L1 | 11/26/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  | 2/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | WHITMAN | 178072 | 02382 | 7.6 | Solar | 05_07_3W2 | 11/01/2017 | 11/01/2017 | 9 | 9 | 0 | 11/20/2017 | 11/20/2017 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 |  | 11/6/2018 | N | EXP | 350 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 572705 | 01827 | 7.83 | Solar | 05_12_16W8 | 11/28/2023 | 12/21/2023 | 18 | 16 | 2 | 12/22/2023 | 12/22/2023 | 104 | 84 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 177445 | 02169 | 336 | Solar | 05_09_702W2 | 09/16/2016 | 09/16/2016 | 0 | 0 | 0 | 09/16/2016 | 09/16/2016 | 381 | 0 | 381 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 |  | 1/31/2019 | N | EXP | 842 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 234837 | 02151 | 7.6 | Solar | 05_07_93W43 | 07/22/2019 | 07/24/2019 | 1 | 0 | 1 | 07/25/2019 | 07/25/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 8/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2019 | Connected |  | N
National Grid | ORANGE | 661863 | 01364 | 6 | Solar | 05_01_210L1 | 12/19/2024 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | WHITMAN | 256122 | 02382 | 6 | Solar | 05_07_3W2 | 11/01/2019 | 11/05/2019 | 1 | 0 | 1 | 11/06/2019 | 11/06/2019 | 9 | 5 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2019 |  | 4/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2020 | Connected |  | N
National Grid | DUNSTABLE | 575019 | 01827 | 9.86 | Solar | 05_12_16W8 | 12/14/2023 | 12/19/2023 | 3 | 1 | 2 | 12/20/2023 | 12/20/2023 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 12/14/2023 | 3/20/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2024 | Connected |  | N
National Grid | QUINCY | 178025 | 02169 | 4980 | Solar | 05_09_702W2 | 08/31/2017 | 10/03/2017 | 23 | 22 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2017 | 10/30/2017 | 19 | 5 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 239824 | 02151 | 7.6 | Solar | 05_07_93W43 | 07/24/2019 | 10/03/2019 | 50 | 47 | 3 | 10/04/2019 | 10/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2019 |  | 8/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 666043 | 01364 | 5.76 | Solar | 05_01_210L1 | 01/15/2025 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | WHITMAN | 374495 | 02382 | 7.6 | Solar | 05_07_3W2 | 08/06/2021 |  | 34 | 33 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 587620 | 01827 | 11 | Solar | 05_12_16W8 | 02/09/2024 | 02/28/2024 | 13 | 11 | 2 | 02/29/2024 | 02/29/2024 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  | 5/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2024 | Connected |  | N
National Grid | QUINCY | 178250 | 02169 | 2000 | Solar | 05_09_702W2 | 03/27/2018 | 03/27/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2018 | 06/13/2018 | 44 | 31 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/2/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 351890 | 02151 | 7.6 | Solar | 05_07_93W43 | 07/12/2021 | 08/10/2021 | 22 | 21 | 1 | 08/11/2021 | 08/11/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2021 |  | 1/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2022 | Connected |  | N
National Grid | ATHOL | 675295 | 01331 | 7.6 | Solar | 05_01_210L1 | 03/03/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 71 | 56 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 6/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2025 | Connected |  | N
National Grid | HANSON | 379106 | 02341 | 11.4 | Solar | 05_07_3W2 | 08/31/2021 | 01/07/2022 | 23 | 21 | 2 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2021 |  | 11/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/6/2022 | Connected |  | N
National Grid | DUNSTABLE | 588803 | 01827 | 7.6 | Solar | 05_12_16W8 | 04/09/2024 | 04/15/2024 | 4 | 0 | 4 | 04/16/2024 | 04/16/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2024 | Connected |  | N
National Grid | QUINCY | 178311 | 02169 | 1625 | Solar | 05_09_702W2 | 02/26/2018 | 02/26/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2018 | 07/24/2018 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/3/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 409784 | 02151 | 7.6 | Solar | 05_07_93W43 | 02/02/2022 | 02/17/2022 | 8 | 0 | 8 | 03/31/2022 | 03/31/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 685252 | 01331 | 14.44 | Solar | 05_01_210L1 | 04/15/2025 | 05/20/2025 | 23 | 17 | 6 | 05/21/2025 | 05/21/2025 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2025 |  | 8/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | WHITMAN | 539000 | 02382 | 30 | Solar | 05_07_3W2 | 07/06/2023 | 08/18/2023 | 32 | 22 | 10 | 08/21/2023 | 08/21/2023 | 45 | 26 | 19 | 11/01/2023 | 12/11/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 12/11/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 11/22/2023 |  | 12/25/2024 | N | EXP | 365 | 12/07/2023 | 02/16/2024 | 72 | 3 | 69 |  |  | 4/12/2024 | Connected |  | N
National Grid | DUNSTABLE | 602201 | 01827 | 6 | Solar | 05_12_16W8 | 04/22/2024 | 04/23/2024 | 1 | 0 | 1 | 04/24/2024 | 04/24/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2024 | 04/22/2024 | 11/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | QUINCY | 178397 | 02169 | 3332 | Solar | 05_09_702W2 | 03/05/2018 | 03/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2018 | 04/17/2018 | 20 | 7 | 13 |  | 0 | 0 | 0 | 01/09/2019 | 01/06/2020 | 249 | 42 | 207 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 414943 | 02151 | 0 | Solar | 05_07_93W43 | 03/01/2022 | 03/08/2022 | 6 | 5 | 1 | 03/09/2022 | 03/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2022 |  | 5/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 287338 | 01331 | 3200 | Hydro | 05_01_216W1 | 09/24/2021 | 04/27/2022 | 137 | 127 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/28/2022 | 05/23/2022 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WHITMAN | 566869 | 02382 | 3.8 | Solar | 05_07_3W2 | 11/16/2023 | 11/17/2023 | 1 | 0 | 1 | 11/20/2023 | 11/20/2023 | 52 | 31 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 2/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2024 | Connected |  | N
National Grid | PEPPERELL | 602855 | 01463 | 3.8 | Solar | 05_12_16W8 | 04/17/2024 | 04/18/2024 | 1 | 0 | 1 | 04/19/2024 | 04/19/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 178482 | 02169 | 1350 | Solar | 05_09_702W2 | 04/03/2018 | 04/05/2018 | 11 | 11 | 0 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 416681 | 02151 | 15.2 | Solar | 05_07_93W43 | 03/09/2022 | 03/10/2022 | 1 | 0 | 1 | 03/11/2022 | 03/11/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 178032 | 01331 | 299 | Solar | 05_01_216W1 | 10/26/2017 | 10/26/2017 | 17 | 17 | 0 | 11/30/2017 | 11/30/2017 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2018 |  | 11/1/2019 | N | EXP | 666 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 622083 | 02382 | 5.76 | Solar | 05_07_3W2 | 07/02/2024 | 07/17/2024 | 3 | 2 | 1 | 07/18/2024 | 07/18/2024 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2024 | Connected |  | N
National Grid | TYNGSBORO | 618248 | 01879 | 7.25 | Solar | 05_12_16W8 | 06/17/2024 | 07/15/2024 | 12 | 9 | 3 | 07/16/2024 | 07/16/2024 | 30 | 17 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 06/17/2024 | 9/30/2025 | Y | EXP | 365 | 11/13/2024 | 03/06/2025 | 114 | 0 | 114 |  |  | 3/18/2025 | Connected |  | N
National Grid | QUINCY | 178671 | 02169 | 8300 | Solar | 05_09_702W2 | 03/19/2018 |  | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/25/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 427434 | 02151 | 0 | Solar | 05_07_93W43 | 04/29/2022 | 07/19/2022 | 54 | 51 | 3 | 07/20/2022 | 07/20/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 |  | 8/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2022 | Connected |  | N
National Grid | ROYALSTON | 299739 | 01368 | 7.6 | Solar | 05_01_216W1 | 08/03/2020 | 08/05/2020 | 1 | 0 | 1 | 08/06/2020 | 08/06/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2020 | 08/03/2020 | 6/8/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2021 | Connected |  | N
National Grid | WHITMAN | 730876 | 02382 | 15.2 | Solar | 05_07_3W2 | 11/03/2025 | 11/06/2025 | 3 | 0 | 3 | 11/07/2025 | 11/07/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | DUNSTABLE | 642469 | 01827 | 3.84 | Solar | 05_12_16W8 | 09/24/2024 | 10/18/2024 | 4 | 0 | 4 | 10/21/2024 | 10/21/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | QUINCY | 186829 | 02169 | 250 | Solar | 05_09_702W2 | 06/07/2018 | 06/07/2018 | 17 | 16 | 1 | 07/10/2018 | 07/10/2018 | 14 | 13 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 436781 | 02151 | 7.6 | Solar | 05_07_93W43 | 07/05/2022 | 07/06/2022 | 1 | 0 | 1 | 07/07/2022 | 07/07/2022 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2022 | 07/05/2022 | 9/7/2023 | Y | EXP | 365 | 10/12/2022 | 10/26/2022 | 15 | 0 | 15 |  |  | 1/30/2023 | Connected |  | N
National Grid | ORANGE | 321965 | 01368 | 5315 | Solar | 05_01_216W1 | 01/08/2021 | 03/22/2021 | 77 | 68 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2021 | 06/02/2021 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 751839 | 02341 | 200 | Solar | 05_07_3W3 | 03/16/2026 |  | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | DUNSTABLE | 642393 | 01827 | 7.6 | Solar | 05_12_16W8 | 09/24/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/24/2024 | 12/17/2025 | Y | EXP | 365 | 06/18/2025 | 10/20/2025 | 125 | 0 | 125 |  |  | 10/31/2025 | Connected |  | N
National Grid | QUINCY | 471854 | 02169 | 0 | Other | 05_07_93W43 | 04/19/2023 | 05/18/2023 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/19/2023 | 06/21/2023 | 22 | 2 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 393819 | 02151 | 8.7 | Solar | 05_01_216W1 | 11/06/2021 | 12/29/2021 | 4 | 2 | 2 | 11/12/2021 | 11/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 |  | 2/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2023 | Connected |  | N
National Grid | ATHOL | 174402 | 01331 | 116.2 | Solar | 05_07_3W3 | 06/14/2012 | 06/14/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2012 |  | 9/28/2012 | N | EXP | 18 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 11/16/2012 | Connected |  | N
National Grid | ABINGTON | 644001 | 02351 | 7.6 | Solar | 05_12_16W8 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 |  | 12/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 187787 | 01510 | 15.2 | Solar | 05_09_702W2 | 06/12/2018 | 06/12/2018 | 54 | 51 | 3 | 08/28/2018 | 08/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 |  | 10/18/2019 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 9/13/2019 | Connected |  | N
National Grid | QUINCY | 577969 | 02169 | 9.5 | Solar | 05_07_93W43 | 01/24/2024 | 01/26/2024 | 2 | 0 | 2 | 01/29/2024 | 01/29/2024 | 67 | 45 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 7/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2024 | Connected |  | N
National Grid | REVERE | 402759 | 02151 | 980 | Solar | 05_01_216W1 | 02/22/2022 | 04/11/2022 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2022 | 04/14/2022 | 3 | 0 | 3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 175309 | 01364 | 135 | Solar | 05_07_3W3 | 06/27/2014 | 06/27/2014 | 6 | 1 | 5 | 07/09/2014 | 07/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2014 |  | 12/31/2014 | N | EXP | 145 |  |  | 0 | 0 | 0 | 8/8/2014 | 8/8/2014 | 3/31/2016 | Connected |  | N
National Grid | WHITMAN | 653527 | 02382 | 3.8 | Solar | 05_12_16W8 | 11/15/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/15/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | CLINTON | 188362 | 01510 | 8300 | Solar | 05_09_702W2 | 06/18/2018 | 06/18/2018 | 30 | 30 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/01/2018 | 08/17/2018 | 13 | 12 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 580263 | 02169 | 9.984 | Solar | 05_07_93W43 | 01/11/2024 | 02/16/2024 | 26 | 25 | 1 | 02/20/2024 | 02/20/2024 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2024 | Connected |  | N
National Grid | REVERE | 527951 | 02151 | 6 | Solar | 05_01_216W1 | 05/30/2023 | 06/01/2023 | 2 | 0 | 2 | 06/02/2023 | 06/02/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 | 05/30/2023 | 8/3/2024 | Y | EXP | 365 | 05/16/2024 | 06/10/2024 | 26 | 0 | 26 |  |  | 6/18/2024 | Connected |  | N
National Grid | ATHOL | 178002 | 01331 | 66.6 | Solar | 05_07_3W3 | 04/26/2017 | 04/26/2017 | 1 | 1 | 0 | 04/28/2017 | 04/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2017 |  | 5/2/2018 | N | EXP | 366 |  |  | 0 | 0 | 0 | 3/22/2018 | 3/22/2018 | 4/10/2018 | Connected |  | N
National Grid | WHITMAN | 655554 | 02382 | 7.6 | Solar | 05_12_16W8 | 12/16/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2025 | Connected |  | N
National Grid | CLINTON | 190726 | 01510 | 4940 | Solar | 05_09_702W2 | 07/26/2018 | 08/23/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2018 | 08/28/2018 | 3 | 3 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 655884 | 02169 | 8 | Solar | 05_07_93W43 | 11/21/2024 | 12/02/2024 | 3 | 1 | 2 | 12/03/2024 | 12/03/2024 | 25 | 0 | 25 | 02/03/2025 | 02/06/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/06/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | REVERE | 546329 | 02151 | 15.2 | Solar | 05_01_216W1 | 08/14/2023 | 08/15/2023 | 1 | 0 | 1 | 08/16/2023 | 08/16/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2024 | Connected |  | N
National Grid | ATHOL | 204113 | 01331 | 86.6 | Solar | 05_07_3W3 | 01/11/2019 | 01/29/2019 | 11 | 6 | 5 | 01/30/2019 | 01/30/2019 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 656727 | 02341 | 7.6 | Solar | 05_12_16W8 | 11/25/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/25/2024 | 5/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | CLINTON | 252830 | 01510 | 10 | Solar | 05_09_702W2 | 09/24/2019 | 09/30/2019 | 3 | 0 | 3 | 10/01/2019 | 10/01/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 658277 | 02169 | 9.57 | Solar | 05_07_93W43 | 12/04/2024 | 01/07/2025 | 20 | 17 | 3 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | REVERE | 577614 | 02151 | 7.6 | Solar | 05_01_216W1 | 12/28/2023 | 01/04/2024 | 4 | 0 | 4 | 01/05/2024 | 01/05/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2024 |  | 2/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | ATHOL | 306165 | 01331 | 100 | Solar | 05_07_3W3 | 10/08/2020 | 01/05/2022 | 27 | 20 | 7 | 11/20/2020 | 11/20/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2021 |  | 11/2/2022 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  | 10/13/2022 | Connected |  | N
National Grid | ABINGTON | 658086 | 02351 | 8.7 | Solar | 05_12_16W8 | 12/10/2024 | 01/03/2025 | 4 | 1 | 3 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | CLINTON | 265840 | 01510 | 0 | Solar | 05_09_702W2 | 11/16/2019 | 11/21/2019 | 3 | 0 | 3 | 11/22/2019 | 11/22/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 | 11/16/2019 | 8/31/2022 | Y | EXP | 440 | 07/31/2020 | 08/17/2020 | 17 | 0 | 17 |  |  | 8/18/2022 | Connected |  | N
National Grid | QUINCY | 662902 | 02169 | 5.76 | Solar | 05_07_93W43 | 01/22/2025 | 03/11/2025 | 6 | 1 | 5 | 03/12/2025 | 03/12/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 | 01/22/2025 | 5/23/2026 | Y | EXP | 365 | 08/08/2025 | 10/27/2025 | 81 | 0 | 81 |  |  | 11/12/2025 | Connected |  | Y
National Grid | REVERE | 598936 | 02151 | 7.6 | Solar | 05_01_216W1 | 04/11/2024 | 04/15/2024 | 2 | 0 | 2 | 04/16/2024 | 04/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  | 7/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | ORANGE | 447739 | 01364 | 66 | Solar | 05_07_3W3 | 07/28/2022 | 11/03/2022 | 68 | 59 | 9 | 11/04/2022 | 11/04/2022 | 126 | 107 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 665567 | 02382 | 7.6 | Solar | 05_12_16W8 | 01/14/2025 | 01/29/2025 | 8 | 6 | 2 | 01/30/2025 | 01/30/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | CLINTON | 273962 | 01510 | 2500 | Solar | 05_09_702W2 | 10/27/2020 | 02/05/2021 | 67 | 58 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2021 | 03/01/2021 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 673264 | 02169 | 7.6 | Solar | 05_07_93W43 | 02/22/2025 | 03/14/2025 | 4 | 0 | 4 | 03/17/2025 | 03/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 02/22/2025 | 4/23/2026 | Y | EXP | 365 | 07/08/2025 | 08/05/2025 | 29 | 0 | 29 |  |  | 8/5/2025 | Connected |  | N
National Grid | REVERE | 651311 | 02151 | 3.8 | Solar | 05_01_216W1 | 11/12/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/12/2024 | 3/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | ATHOL | 651204 | 01331 | 5.76 | Solar | 05_07_3W3 | 11/12/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | WHITMAN | 671008 | 02382 | 3.8 | Solar | 05_12_16W8 | 04/18/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 285646 | 01510 | 10 | Solar | 05_09_702W2 | 04/29/2020 | 05/04/2020 | 2 | 2 | 0 | 05/05/2020 | 05/05/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2020 | Connected |  | N
National Grid | QUINCY | 701824 | 02169 | 18.24 | Solar | 05_07_93W43 | 06/30/2025 | 07/09/2025 | 5 | 2 | 3 | 07/10/2025 | 07/10/2025 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2025 | Connected |  | Y
National Grid | REVERE | 660341 | 02151 | 3.8 | Solar | 05_01_216W1 | 12/12/2024 | 02/05/2025 | 27 | 22 | 5 | 02/06/2025 | 02/06/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 3/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | ATHOL | 176128 | 01331 | 225 | Natural Gas | 05_07_3W4 | 04/14/2015 | 04/14/2015 | 0 | 0 | 0 | 04/14/2015 | 04/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2015 |  | 9/1/2015 | N | EXP | 138 |  |  | 0 | 0 | 0 | 8/14/2015 | 8/14/2015 | 8/25/2015 | Connected |  | N
National Grid | HANSON | 671747 | 02341 | 7.6 | Solar | 05_12_16W8 | 02/17/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | CLINTON | 302401 | 01510 | 10 | Solar | 05_09_702W2 | 09/25/2020 | 10/01/2020 | 3 | 0 | 3 | 10/02/2020 | 10/02/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2020 | 09/25/2020 | 11/2/2021 | Y | EXP | 365 | 01/27/2021 | 02/12/2021 | 15 | 0 | 15 |  |  | 3/31/2021 | Connected |  | N
National Grid | QUINCY | 711039 | 02169 | 20 | Solar | 05_07_93W43 | 08/15/2025 | 08/22/2025 | 5 | 0 | 5 | 08/25/2025 | 08/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2026 | Connected |  | N
National Grid | REVERE | 690813 | 02151 | 5.76 | Solar | 05_01_216W1 | 05/09/2025 | 05/21/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 | 05/09/2025 | 7/16/2026 | Y | EXP | 365 | 11/07/2025 | 12/18/2025 | 42 | 0 | 42 |  |  | 11/26/2025 | Connected |  | N
National Grid | ROYALSTON | 177988 | 01368 | 3 | Solar | 05_07_4J1 | 08/28/2017 | 08/28/2017 | 5 | 0 | 5 | 09/07/2017 | 09/07/2017 | 138 | 0 | 138 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 9/4/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 671761 | 02382 | 5.76 | Solar | 05_12_16W8 | 02/17/2025 | 03/20/2025 | 9 | 4 | 5 | 03/21/2025 | 03/21/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2025 | Connected |  | N
National Grid | CLINTON | 302982 | 01510 | 9.36 | Solar | 05_09_702W2 | 07/24/2020 | 07/27/2020 | 0 | 0 | 0 | 07/28/2020 | 07/28/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2020 |  | 7/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2020 | Connected |  | N
National Grid | QUINCY | 437923 | 02169 | 250 | Solar | 05_07_94W40 | 09/26/2022 | 10/19/2022 | 16 | 7 | 9 |  |  | 76 | 51 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 09/26/2022 | 8/9/2026 | Y | STD | 224 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | REVERE | 486664 | 02151 | 4999 | Solar | 05_01_216W2 | 05/08/2023 | 05/22/2023 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2023 | 05/23/2023 | 1 | 0 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 05/08/2023 | 3/4/2027 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | ATHOL | 183802 | 01331 | 10 | Solar | 05_07_4J1 | 06/01/2018 | 06/01/2018 | 10 | 9 | 1 | 06/15/2018 | 06/15/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 7/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2019 | Connected |  | N
National Grid | WHITMAN | 681063 | 02382 | 7.6 | Solar | 05_12_16W8 | 03/28/2025 | 04/10/2025 | 2 | 0 | 2 | 04/18/2025 | 04/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 339524 | 01510 | 0 | Solar | 05_09_702W2 | 02/03/2021 | 02/10/2021 | 4 | 3 | 1 | 02/11/2021 | 02/11/2021 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 | 02/03/2021 | 4/18/2022 | Y | EXP | 365 | 04/07/2021 | 04/13/2021 | 6 | 0 | 6 |  |  | 2/23/2022 | Connected |  | N
National Grid | QUINCY | 645816 | 02169 | 7.6 | Solar | 05_07_94W40 | 10/08/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/08/2024 | 12/11/2026 | Y | EXP | 730 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | REVERE | 682136 | 02151 | 2000 | Solar | 05_01_216W2 | 11/25/2025 | 12/18/2025 | 15 | 6 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 | 01/12/2026 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATHOL | 213972 | 01331 | 0 | Solar | 05_07_4J1 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITMAN | 730402 | 02382 | 2.56 | Solar | 05_12_16W8 | 10/30/2025 | 11/19/2025 | 13 | 12 | 1 | 11/20/2025 | 11/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 374024 | 01510 | 0 | Solar | 05_09_702W2 | 08/12/2021 | 12/22/2021 | 22 | 21 | 1 | 09/14/2021 | 09/14/2021 | 92 | 66 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 676914 | 02169 | 999.9 | Solar | 05_07_94W40 | 04/08/2025 | 06/10/2025 | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | REVERE | 694872 | 02151 | 400 | Solar | 05_01_216W2 | 09/09/2025 | 10/09/2025 | 21 | 13 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2025 | 01/09/2026 | 61 | 44 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATHOL | 646324 | 01331 | 7.6 | Solar | 05_07_4J1 | 10/10/2024 | 11/26/2024 | 12 | 8 | 4 | 11/27/2024 | 11/27/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/10/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | HANSON | 654022 | 02341 | 6.46 | Solar | 05_12_17J1 | 11/13/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | CLINTON | 372949 | 01510 | 14.07 | Solar | 05_09_702W2 | 08/19/2021 | 03/02/2022 | 133 | 124 | 9 | 03/03/2022 | 03/03/2022 | 59 | 42 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 728681 | 02169 | 3.8 | Solar | 05_07_94W40 | 10/23/2025 | 10/27/2025 | 3 | 0 | 3 | 11/17/2025 | 11/17/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2026 | 10/23/2025 | 1/13/2027 | Y | EXP | 365 | 02/06/2026 |  | 55 | 0 | 55 |  |  |  | Construction |  | N
National Grid | REVERE | 176314 | 02151 | 183 | Solar | 05_01_216W2 | 05/11/2015 | 05/11/2015 | 4 | 4 | 0 | 05/15/2015 | 05/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2015 | 05/11/2015 | 12/31/2016 | Y | EXP | 561 | 06/21/2016 | 07/27/2016 | 25 | 0 | 25 | 12/11/2015 | 12/11/2015 | 8/4/2016 | Connected |  | N
National Grid | ATHOL | 175593 | 01331 | 132 | Solar | 05_07_4J2 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2014 |  | 11/28/2014 | N | EXP | 91 |  |  | 0 | 0 | 0 | 3/16/2015 | 3/16/2015 | 3/16/2015 | Connected |  | N
National Grid | HANSON | 213815 | 02341 | 0 | Solar | 05_12_17J2 | 03/14/2019 | 03/15/2019 | 2 | 0 | 2 | 09/12/2019 | 09/12/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2019 |  | 3/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2020 | Connected |  | N
National Grid | CLINTON | 435569 | 01510 | 9.86 | Solar | 05_09_702W2 | 06/23/2022 | 06/24/2022 | 1 | 0 | 1 | 06/27/2022 | 06/27/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/23/2022 | 11/13/2023 | Y | EXP | 365 | 10/06/2022 | 11/10/2022 | 36 | 0 | 36 |  |  | 4/27/2023 | Connected |  | N
National Grid | QUINCY | 755775 | 02171 | 15.2 | Solar | 05_07_94W40 | 03/16/2026 | 03/18/2026 | 2 | 0 | 2 | 03/19/2026 | 03/19/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 177307 | 02151 | 15.2 | Solar | 05_01_216W2 | 11/16/2016 | 11/16/2016 | 3 | 3 | 0 | 11/22/2016 | 11/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 |  | 11/22/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 6/8/2017 | 6/8/2017 | 6/8/2017 | Connected |  | N
National Grid | ORANGE | 613587 | 01364 | 7.36 | Solar | 05_07_4J2 | 05/28/2024 | 06/05/2024 | 1 | 0 | 1 | 09/26/2024 | 09/26/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 | 05/28/2024 | 10/23/2025 | Y | EXP | 365 | 12/19/2024 | 02/04/2025 | 48 | 0 | 48 |  |  | 2/7/2025 | Connected |  | N
National Grid | BROCKTON | 635834 | 02301 | 9.074 | Solar | 05_12_17J2 | 08/27/2024 | 10/18/2024 | 2 | 0 | 2 | 10/21/2024 | 10/21/2024 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 479424 | 01510 | 25 | Solar | 05_09_702W2 | 11/28/2022 | 12/05/2022 | 5 | 4 | 1 | 12/06/2022 | 12/06/2022 | 73 | 53 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  | 4/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2023 | Connected |  | N
National Grid | QUINCY | 177149 | 02171 | 10 | Solar | 05_07_94W40 | 08/09/2016 | 08/09/2016 | 2 | 2 | 0 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2016 | 08/09/2016 | 8/15/2017 | Y | EXP | 362 | 10/09/2017 | 11/07/2017 | 15 | 0 | 15 | 11/15/2017 | 11/15/2017 | 11/28/2017 | Connected |  | N
National Grid | REVERE | 178033 | 02151 | 296 | Solar | 05_01_216W2 | 10/26/2017 | 10/26/2017 | 17 | 17 | 0 | 11/30/2017 | 11/30/2017 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2018 |  | 11/1/2019 | N | EXP | 666 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROYALSTON | 625176 | 01368 | 9.57 | Solar | 05_07_4J2 | 07/16/2024 | 08/26/2024 | 2 | 0 | 2 | 08/27/2024 | 08/27/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 | 07/16/2024 | 9/24/2025 | Y | EXP | 365 | 01/28/2025 | 01/27/2025 | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | BROCKTON | 646255 | 02301 | 7.22 | Solar | 05_12_17J2 | 10/10/2024 | 11/22/2024 | 26 | 22 | 4 | 11/25/2024 | 11/25/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 | 10/10/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | CLINTON | 480601 | 01510 | 18.56 | Solar | 05_09_702W2 | 11/28/2022 | 12/05/2022 | 5 | 4 | 1 | 12/06/2022 | 12/06/2022 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 | 11/28/2022 | 10/19/2024 | Y | EXP | 365 | 05/02/2023 | 10/19/2023 | 171 | 0 | 171 |  |  | 10/24/2023 | Connected |  | N
National Grid | QUINCY | 178411 | 02171 | 43.2 | Solar | 05_07_94W40 | 11/27/2017 | 11/27/2017 | 44 | 42 | 2 | 01/31/2018 | 01/31/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 |  | 12/2/2018 | N | EXP | 305 |  |  | 0 | 0 | 0 | 3/28/2018 | 3/28/2018 | 3/30/2018 | Connected |  | N
National Grid | REVERE | 187526 | 02151 | 149.9 | Solar | 05_01_216W2 | 06/08/2018 | 09/03/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 662234 | 01331 | 7.6 | Solar | 05_07_4J2 | 12/23/2024 | 01/07/2025 | 1 | 0 | 1 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 12/23/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | BROCKTON | 750365 | 02301 | 0 | Battery Add-On | 05_12_17J3 | 02/10/2026 | 02/17/2026 | 4 | 0 | 4 | 02/18/2026 | 02/18/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2026 |  | 3/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CLINTON | 517086 | 01510 | 6 | Solar | 05_09_702W2 | 06/09/2023 | 06/15/2023 | 5 | 4 | 1 | 06/16/2023 | 06/16/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 | 06/09/2023 | 8/20/2024 | Y | EXP | 365 | 11/10/2023 | 01/12/2024 | 64 | 3 | 61 |  |  | 1/18/2024 | Connected |  | N
National Grid | QUINCY | 193582 | 02171 | 490 | Solar | 05_07_94W40 | 09/05/2018 | 10/01/2018 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 02/23/2019 | 154 | 83 | 71 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 208503 | 02155 | 86.6 | Solar | 05_01_216W2 | 02/07/2019 | 03/19/2019 | 24 | 17 | 7 | 03/20/2019 | 03/20/2019 | 93 | 88 | 5 | 08/08/2019 | 08/25/2020 | 264 | 182 | 82 |  |  | 0 | 0 | 0 | 08/25/2020 | 264 | 182 | 82 |  |  | 0 | 0 | 0 | 9/4/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 190363 | 01364 | 7.6 | Solar | 05_07_5W1 | 07/10/2018 | 08/27/2018 | 5 | 4 | 1 | 08/28/2018 | 08/28/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 | 07/10/2018 | 5/18/2020 | Y | EXP | 619 | 11/16/2019 | 12/10/2019 | 24 | 0 | 24 |  |  | 12/24/2019 | Connected |  | N
National Grid | BROCKTON | 268101 | 02301 | 7.6 | Solar | 05_12_17J3 | 12/03/2019 | 12/10/2019 | 5 | 4 | 1 | 12/11/2019 | 12/11/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 520344 | 01510 | 14.79 | Solar | 05_09_702W2 | 04/19/2023 | 05/03/2023 | 10 | 7 | 3 | 05/04/2023 | 05/04/2023 | 112 | 97 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 |  | 1/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/18/2024 | Connected |  | N
National Grid | QUINCY | 191161 | 02171 | 250 | Solar | 05_07_94W40 | 08/04/2018 | 08/24/2018 | 17 | 0 | 17 | 08/24/2018 | 08/24/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  | 4/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 470890 | 02155 | 15.2 | Solar | 05_01_216W2 | 10/24/2022 | 10/26/2022 | 2 | 0 | 2 | 10/27/2022 | 10/27/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 |  | 11/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2023 | Connected |  | N
National Grid | ROYALSTON | 215677 | 01331 | 10 | Solar | 05_07_5W1 | 04/02/2019 | 04/09/2019 | 4 | 0 | 4 | 04/10/2019 | 04/10/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 322458 | 02301 | 7.6 | Solar | 05_12_17J3 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 526584 | 01510 | 3.8 | Solar | 05_09_702W2 | 06/13/2023 | 06/14/2023 | 1 | 0 | 1 | 06/15/2023 | 06/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2023 | 06/13/2023 | 7/31/2024 | Y | EXP | 365 | 08/24/2023 | 12/26/2023 | 125 | 3 | 122 |  |  | 1/4/2024 | Connected |  | Y
National Grid | QUINCY | 266977 | 02171 | 7.6 | Solar | 05_07_94W40 | 11/26/2019 | 12/02/2019 | 2 | 0 | 2 | 12/03/2019 | 12/03/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2019 | 11/26/2019 | 12/29/2020 | Y | EXP | 365 | 07/21/2020 | 08/12/2020 | 22 | 0 | 22 |  |  | 12/19/2020 | Connected |  | N
National Grid | MEDFORD | 589386 | 02155 | 7.6 | Solar | 05_01_216W2 | 02/23/2024 | 03/04/2024 | 6 | 0 | 6 | 03/05/2024 | 03/05/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 | 02/23/2024 | 3/21/2025 | Y | EXP | 365 | 05/24/2024 | 05/23/2024 | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | ATHOL | 242725 | 01331 | 10 | Solar | 05_07_5W1 | 08/13/2019 | 09/04/2019 | 15 | 15 | 0 | 09/05/2019 | 09/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 | 08/13/2019 | 5/1/2020 | Y | EXP | 227 | 11/16/2019 | 12/19/2019 | 33 | 0 | 33 |  |  | 4/1/2020 | Connected |  | N
National Grid | BROCKTON | 387786 | 02301 | 9.28 | Solar | 05_12_17J3 | 11/01/2021 | 12/23/2021 | 7 | 4 | 3 | 11/12/2021 | 11/12/2021 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  | 8/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2022 | Connected |  | Y
National Grid | CLINTON | 556896 | 01510 | 8.99 | Solar | 05_09_702W2 | 11/15/2023 | 09/22/2023 | 3 | 1 | 2 | 11/20/2023 | 11/20/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 |  | 12/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2024 | Connected |  | N
National Grid | QUINCY | 305003 | 02170 | 6 | Solar | 05_07_94W40 | 10/08/2020 | 10/12/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 26 | 9 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2021 | Connected |  | N
National Grid | MEDFORD | 601702 | 02155 | 7.6 | Solar | 05_01_216W2 | 04/10/2024 | 04/16/2024 | 3 | 0 | 3 | 04/17/2024 | 04/17/2024 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 | 04/10/2024 | 5/30/2025 | Y | EXP | 365 | 08/21/2024 | 10/17/2024 | 58 | 0 | 58 |  |  | 11/15/2024 | Connected |  | N
National Grid | ATHOL | 450193 | 01331 | 7.6 | Solar | 05_07_5W1 | 08/31/2022 | 09/02/2022 | 2 | 0 | 2 | 09/06/2022 | 09/06/2022 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 | 08/31/2022 | 3/7/2024 | Y | EXP | 365 | 02/24/2023 | 03/08/2023 | 13 | 0 | 13 |  |  | 3/13/2023 | Connected |  | N
National Grid | BROCKTON | 598869 | 02301 | 6.08 | Solar | 05_12_17J4 | 03/29/2024 | 05/01/2024 | 22 | 20 | 2 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 556457 | 01510 | 25 | Solar | 05_09_702W2 | 09/28/2023 | 10/02/2023 | 2 | 0 | 2 | 10/03/2023 | 10/03/2023 | 63 | 42 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | QUINCY | 384235 | 02171 | 0 | Other | 05_07_94W40 | 03/30/2022 | 04/13/2022 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/14/2022 | 04/27/2022 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 715423 | 02155 | 3320 | Solar | 05_01_216W3 | 10/28/2025 | 12/09/2025 | 28 | 20 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 01/08/2026 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATHOL | 586990 | 01331 | 7.6 | Solar | 05_07_5W1 | 02/19/2024 | 06/03/2024 | 73 | 70 | 3 | 06/04/2024 | 06/04/2024 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 | 02/19/2024 | 8/21/2025 | Y | EXP | 365 | 07/18/2024 | 07/30/2024 | 13 | 0 | 13 |  |  | 10/24/2024 | Connected |  | N
National Grid | BROCKTON | 561621 | 02301 | 0 | Solar | 05_12_17J5 | 10/12/2023 | 10/19/2023 | 6 | 4 | 2 | 10/20/2023 | 10/20/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 550568 | 01510 | 15 | Solar | 05_09_702W2 | 09/25/2023 | 10/02/2023 | 5 | 1 | 4 | 10/03/2023 | 10/03/2023 | 43 | 18 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 | 09/25/2023 | 12/20/2024 | Y | EXP | 365 | 01/30/2024 | 03/18/2024 | 49 | 0 | 49 |  |  | 3/20/2024 | Connected |  | N
National Grid | RANDOLPH | 393066 | 02368 | 420 | Solar | 05_07_94W40 | 02/04/2022 | 02/18/2022 | 10 | 4 | 6 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 174358 | 02155 | 10.53 | Solar | 05_01_216W3 | 05/16/2012 | 05/16/2012 | 7 | 0 | 7 | 05/30/2012 | 05/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 7/31/2012 | N | EXP | 134 |  |  | 0 | 0 | 0 | 9/6/2012 | 9/6/2012 | 5/30/2013 | Connected |  | N
National Grid | ATHOL | 625180 | 01331 | 3.8 | Solar | 05_07_5W1 | 07/16/2024 | 07/29/2024 | 3 | 0 | 3 | 07/30/2024 | 07/30/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 07/16/2024 | 9/9/2025 | Y | EXP | 365 | 12/06/2024 | 12/17/2024 | 12 | 0 | 12 |  |  | 1/8/2025 | Connected |  | N
National Grid | BROCKTON | 649388 | 02301 | 6 | Solar | 05_12_17J5 | 10/24/2024 | 11/15/2024 | 7 | 3 | 4 | 11/18/2024 | 11/18/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 550490 | 01510 | 25 | Solar | 05_09_702W2 | 08/25/2023 | 09/12/2023 | 11 | 9 | 2 | 09/13/2023 | 09/13/2023 | 139 | 122 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 |  | 6/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2024 | Connected |  | N
National Grid | RANDOLPH | 473683 | 02368 | 12 | Solar | 05_07_94W40 | 11/29/2022 | 12/30/2022 | 23 | 18 | 5 | 01/03/2023 | 01/03/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2023 |  | 2/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2023 | Connected |  | N
National Grid | MEDFORD | 174374 | 02155 | 1000 | Solar | 05_01_216W3 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 08/17/2012 | 47 | 0 | 47 |  | 0 | 0 | 0 | 09/24/2013 | 09/24/2013 | 0 | 0 | 0 | 3/14/2013 | 05/29/2012 | 3/2/2018 | Y | STD | 1814 | 11/30/2017 | 02/21/2018 | 55 | 0 | 55 | 3/1/2018 | 3/1/2018 | 3/1/2018 | Connected |  | N
National Grid | ROYALSTON | 714659 | 01368 | 10 | Solar | 05_07_5W2 | 08/26/2025 | 09/24/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 | 08/26/2025 | 12/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BROCKTON | 738090 | 02301 | 44.6 | Solar | 05_12_17J6 | 01/07/2026 | 01/08/2026 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CLINTON | 567606 | 01510 | 10 | Solar | 05_09_702W2 | 11/30/2023 | 12/19/2023 | 13 | 11 | 2 | 12/20/2023 | 12/20/2023 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 | 11/30/2023 | 3/4/2025 | Y | EXP | 365 | 06/12/2024 | 07/17/2024 | 36 | 0 | 36 |  |  | 7/23/2024 | Connected |  | N
National Grid | RANDOLPH | 485684 | 02368 | 15.08 | Solar | 05_07_94W40 | 12/15/2022 | 12/20/2022 | 4 | 2 | 2 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | N
National Grid | MEDFORD | 176889 | 02155 | 6.45 | Solar | 05_01_216W3 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2015 |  | 11/18/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 7/26/2016 | 7/26/2016 | 7/26/2016 | Connected |  | N
National Grid | ORANGE | 716756 | 01364 | 13.8 | Solar | 05_07_5W2 | 09/10/2025 | 11/10/2025 | 40 | 34 | 6 | 11/12/2025 | 11/12/2025 | 37 | 20 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 | 09/10/2025 | 3/13/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | BROCKTON | 175209 | 02301 | 12 | Solar | 05_12_17J6 | 12/05/2012 | 12/05/2012 | 10 | 5 | 5 | 12/21/2012 | 12/21/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2013 |  | 2/28/2013 | N | EXP | 13 |  |  | 0 | 0 | 0 | 2/15/2013 | 2/15/2013 | 3/14/2013 | Connected |  | N
National Grid | CLINTON | 577357 | 01510 | 0 | Battery Add-On | 05_09_702W2 | 12/12/2023 | 01/02/2024 | 13 | 11 | 2 | 01/03/2024 | 01/03/2024 | 57 | 32 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 |  | 4/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2024 | Connected |  | N
National Grid | RANDOLPH | 556280 | 02368 | 10 | Solar | 05_07_94W40 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 09/22/2023 | 11/15/2024 | Y | EXP | 365 | 04/18/2024 | 04/17/2024 | 0 | 0 | 0 |  |  | 4/29/2024 | Connected |  | N
National Grid | MEDFORD | 177806 | 02155 | 15 | Solar | 05_01_216W3 | 10/12/2017 | 10/12/2017 | 8 | 0 | 8 | 10/25/2017 | 10/25/2017 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2017 | 10/12/2017 | 9/26/2019 | Y | EXP | 700 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 747514 | 01364 | 11.5 | Solar | 05_07_5W2 | 01/26/2026 | 01/30/2026 | 3 | 0 | 3 | 02/24/2026 | 02/24/2026 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 328772 | 02301 | 7.6 | Solar | 05_12_17J6 | 11/30/2020 | 12/08/2020 | 5 | 0 | 5 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 11/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2021 | Connected |  | N
National Grid | LANCASTER | 594763 | 01523 | 4.64 | Solar | 05_09_702W2 | 03/12/2024 | 03/13/2024 | 1 | 0 | 1 | 03/14/2024 | 03/14/2024 | 16 | 15 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 572349 | 02368 | 3.8 | Solar | 05_07_94W40 | 12/11/2023 | 12/14/2023 | 4 | 3 | 1 | 12/15/2023 | 12/15/2023 | 53 | 30 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 194838 | 02155 | 3.8 | Solar | 05_01_216W3 | 08/30/2018 | 10/29/2018 | 21 | 21 | 0 | 10/30/2018 | 10/30/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 177291 | 01331 | 23.4 | Solar | 05_07_5W2 | 08/24/2016 | 08/24/2016 | 2 | 2 | 0 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2016 |  | 8/30/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/28/2016 | 10/28/2016 | 11/8/2016 | Connected |  | N
National Grid | BROCKTON | 421359 | 02301 | 0 | Solar | 05_12_17J6 | 04/01/2022 | 04/04/2022 | 1 | 0 | 1 | 04/05/2022 | 04/05/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2022 |  | 5/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2022 | Connected |  | N
National Grid | CLINTON | 624205 | 01510 | 0 | Solar | 05_09_702W2 | 07/11/2024 | 07/15/2024 | 2 | 0 | 2 | 07/16/2024 | 07/16/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/11/2024 | 8/12/2025 | Y | EXP | 365 | 10/02/2024 | 10/09/2024 | 8 | 0 | 8 |  |  | 1/24/2025 | Connected |  | N
National Grid | RANDOLPH | 600250 | 02368 | 6.67 | Solar | 05_07_94W40 | 03/29/2024 | 04/03/2024 | 4 | 2 | 2 | 04/04/2024 | 04/04/2024 | 9 | 0 | 9 | 08/27/2024 | 09/17/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 09/17/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 9/20/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 197325 | 02155 | 7.6 | Solar | 05_01_216W3 | 10/01/2018 | 10/22/2018 | 3 | 3 | 0 | 10/23/2018 | 10/23/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 202727 | 01331 | 7.6 | Solar | 05_07_5W2 | 12/06/2018 | 12/18/2018 | 7 | 0 | 7 | 12/19/2018 | 12/19/2018 | 201 | 0 | 201 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2019 |  | 12/6/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 521915 | 02301 | 10 | Solar | 05_12_17J6 | 05/09/2023 | 05/11/2023 | 2 | 0 | 2 | 05/12/2023 | 05/12/2023 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2023 | 05/09/2023 | 1/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 644621 | 01510 | 5.76 | Solar | 05_09_702W2 | 10/03/2024 | 10/31/2024 | 4 | 0 | 4 | 11/01/2024 | 11/01/2024 | 64 | 42 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 10/03/2024 | 3/25/2026 | Y | EXP | 365 | 08/28/2025 | 09/12/2025 | 16 | 0 | 16 |  |  | 9/25/2025 | Connected |  | N
National Grid | RANDOLPH | 645170 | 02368 | 5.76 | Solar | 05_07_94W40 | 10/04/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/04/2024 | 12/12/2025 | Y | EXP | 365 | 02/26/2025 | 10/17/2025 | 234 | 0 | 234 |  |  | 10/29/2025 | Connected |  | N
National Grid | MEDFORD | 217500 | 02155 | 3.8 | Solar | 05_01_216W3 | 06/18/2019 | 10/23/2019 | 87 | 83 | 4 | 10/24/2019 | 10/24/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 292717 | 01331 | 0 | Battery Add-On | 05_07_5W2 | 05/21/2020 | 06/08/2020 | 10 | 10 | 0 | 06/09/2020 | 06/09/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 6/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2020 | Connected |  | N
National Grid | BROCKTON | 612896 | 02301 | 5.76 | Solar | 05_12_17J6 | 05/22/2024 | 05/29/2024 | 2 | 0 | 2 | 05/30/2024 | 05/30/2024 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/22/2024 | 7/5/2025 | Y | EXP | 365 | 03/05/2025 | 03/04/2025 | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | CLINTON | 651793 | 01510 | 3.8 | Solar | 05_09_702W2 | 11/13/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | RANDOLPH | 657028 | 02368 | 5.76 | Solar | 05_07_94W40 | 11/26/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/26/2024 | 2/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | MEDFORD | 242400 | 02155 | 9.92 | Solar | 05_01_216W3 | 07/16/2019 | 07/23/2019 | 4 | 0 | 4 | 07/24/2019 | 07/24/2019 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 | 07/16/2019 | 7/16/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2020 | Connected |  | N
National Grid | ORANGE | 307448 | 01364 | 8.99 | Solar | 05_07_5W2 | 08/18/2020 | 09/15/2020 | 19 | 19 | 0 | 09/16/2020 | 09/16/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2021 | Connected |  | N
National Grid | BROCKTON | 620837 | 02301 | 4.886 | Solar | 05_12_17J6 | 06/26/2024 | 07/11/2024 | 3 | 1 | 2 | 07/12/2024 | 07/12/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 06/26/2024 | 8/6/2025 | Y | EXP | 365 | 08/30/2024 | 02/12/2025 | 88 | 0 | 88 |  |  | 11/26/2024 | Connected |  | N
National Grid | LANCASTER | 651668 | 01523 | 3.8 | Solar | 05_09_702W2 | 11/13/2024 | 12/16/2024 | 7 | 0 | 7 | 12/17/2024 | 12/17/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 660479 | 02368 | 3.8 | Solar | 05_07_94W40 | 12/13/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/13/2024 | 2/25/2026 | Y | EXP | 365 | 08/21/2025 | 02/03/2026 | 167 | 0 | 167 |  |  | 11/24/2025 | Connected |  | N
National Grid | MEDFORD | 287761 | 02155 | 11.52 | Solar | 05_01_216W3 | 04/14/2020 | 04/20/2020 | 3 | 0 | 3 | 04/21/2020 | 04/21/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2020 |  | 9/24/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2021 | Connected |  | N
National Grid | ATHOL | 388130 | 01331 | 3.84 | Solar | 05_07_5W2 | 11/10/2021 | 12/13/2021 | 3 | 0 | 3 | 11/17/2021 | 11/17/2021 | 42 | 22 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 667327 | 02301 | 9.12 | Solar | 05_12_17J6 | 01/22/2025 | 02/18/2025 | 8 | 3 | 5 | 02/19/2025 | 02/19/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2025 | Connected |  | N
National Grid | CLINTON | 665670 | 01510 | 19.1 | Solar | 05_09_702W2 | 01/14/2025 | 02/11/2025 | 16 | 10 | 6 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | RANDOLPH | 701575 | 02368 | 10 | Solar | 05_07_94W40 | 08/01/2025 | 09/08/2025 | 24 | 22 | 2 | 09/09/2025 | 09/09/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | MEDFORD | 320293 | 02155 | 7.6 | Solar | 05_01_216W3 | 10/29/2020 | 11/02/2020 | 1 | 0 | 1 | 11/03/2020 | 11/03/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 | 10/29/2020 | 10/29/2021 | Y | EXP | 365 | 05/06/2021 | 05/07/2021 | 1 | 0 | 1 |  |  | 9/3/2021 | Connected |  | N
National Grid | ORANGE | 457785 | 01364 | 10 | Solar | 05_07_5W2 | 09/15/2022 | 09/16/2022 | 1 | 0 | 1 | 09/19/2022 | 09/19/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175464 | 02301 | 881.6 | Solar | 05_12_18J3 | 09/22/2014 | 09/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2014 | 10/29/2014 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2015 | 09/22/2014 | 1/1/2016 | Y | STD | 297 | 11/04/2015 | 05/19/2016 | 133 | 0 | 133 | 5/6/2016 | 5/6/2016 | 5/6/2016 | Connected |  | N
National Grid | CLINTON | 685853 | 01510 | 3.8 | Solar | 05_09_702W2 | 04/17/2025 | 05/19/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 99 | 83 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 1/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2026 | Connected |  | Y
National Grid | RANDOLPH | 419315 | 02368 | 240 | Solar | 05_07_94W41 | 05/26/2022 | 06/13/2022 | 12 | 5 | 7 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MEDFORD | 396737 | 02155 | 1744 | Other | 05_01_216W3 | 05/25/2022 | 06/04/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/06/2022 | 07/11/2022 | 24 | 5 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 465464 | 01331 | 6 | Solar | 05_07_5W2 | 10/20/2022 | 10/25/2022 | 3 | 0 | 3 | 10/26/2022 | 10/26/2022 | 261 | 247 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 177673 | 02301 | 100 | Solar | 05_12_18J3 | 07/20/2017 | 07/20/2017 | 23 | 19 | 4 | 08/23/2017 | 08/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2017 |  | 7/26/2018 | N | EXP | 331 |  |  | 0 | 0 | 0 |  |  | 11/9/2018 | Connected |  | N
National Grid | CLINTON | 693902 | 01510 | 15.2 | Solar | 05_09_702W2 | 05/23/2025 | 05/29/2025 | 3 | 0 | 3 | 05/30/2025 | 05/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | RANDOLPH | 175597 | 02368 | 998 | Solar | 05_07_94W41 | 08/01/2014 | 08/01/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2014 | 08/29/2014 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2015 | 08/01/2014 | 1/20/2016 | Y | STD | 296 | 09/14/2016 | 01/17/2017 | 83 | 0 | 83 | 4/5/2017 | 4/5/2017 | 4/5/2017 | Connected |  | N
National Grid | MEDFORD | 425604 | 02155 | 15.2 | Solar | 05_01_216W3 | 04/22/2022 | 04/26/2022 | 3 | 2 | 1 | 04/27/2022 | 04/27/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2022 |  | 6/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2022 | Connected |  | N
National Grid | ATHOL | 477574 | 01331 | 10 | Solar | 05_07_5W2 | 11/18/2022 | 11/22/2022 | 2 | 0 | 2 | 11/23/2022 | 11/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 | 11/18/2022 | 12/19/2024 | Y | EXP | 365 | 10/26/2023 | 11/29/2023 | 35 | 0 | 35 |  |  | 1/5/2024 | Connected |  | N
National Grid | BROCKTON | 177609 | 02301 | 92 | Solar | 05_12_18J4 | 09/21/2017 | 09/21/2017 | 6 | 5 | 1 | 09/29/2017 | 09/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2017 |  | 9/26/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 12/18/2017 | 12/18/2017 | 12/29/2017 | Connected |  | N
National Grid | CLINTON | 711382 | 01510 | 15.2 | Solar | 05_09_702W2 | 08/14/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 176307 | 02368 | 252 | Solar | 05_07_94W41 | 02/20/2015 | 02/20/2015 | 11 | 5 | 6 | 03/10/2015 | 03/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2015 |  | 9/30/2015 | N | EXP | 190 |  |  | 0 | 0 | 0 | 5/27/2015 | 5/27/2015 | 7/21/2015 | Connected |  | N
National Grid | MEDFORD | 435349 | 02155 | 0 | Other | 05_01_216W3 | 07/27/2022 | 08/23/2022 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2022 | 09/16/2022 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 481663 | 01331 | 7.6 | Solar | 05_07_5W2 | 12/12/2022 | 12/14/2022 | 2 | 0 | 2 | 12/15/2022 | 12/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 | 12/12/2022 | 10/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2024 | Connected |  | N
National Grid | BROCKTON | 177981 | 02301 | 128 | Solar | 05_12_18J4 | 08/24/2017 | 08/24/2017 | 29 | 29 | 0 | 10/09/2017 | 10/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 9/2/2018 | N | EXP | 327 |  |  | 0 | 0 | 0 | 1/25/2018 | 1/25/2018 | 1/25/2018 | Connected |  | N
National Grid | LANCASTER | 715697 | 01523 | 5.51 | Solar | 05_09_702W2 | 08/29/2025 | 10/03/2025 | 4 | 0 | 4 | 10/06/2025 | 10/06/2025 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2026 | Connected |  | N
National Grid | RANDOLPH | 208613 | 02368 | 972 | Solar | 05_07_94W41 | 03/27/2019 | 04/20/2019 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2019 | 05/14/2019 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 588934 | 02155 | 6 | Solar | 05_01_216W3 | 02/28/2024 | 03/04/2024 | 3 | 0 | 3 | 03/05/2024 | 03/05/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/28/2024 | 12/31/2025 | Y | EXP | 365 | 06/05/2024 | 08/28/2024 | 85 | 0 | 85 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 517154 | 01331 | 7.875 | Solar | 05_07_5W2 | 04/19/2023 | 04/20/2023 | 1 | 0 | 1 | 04/21/2023 | 04/21/2023 | 45 | 22 | 23 | 07/18/2023 | 08/24/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 08/24/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 8/28/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 185017 | 02301 | 458 | Solar | 05_12_18J4 | 09/21/2018 | 10/01/2018 | 0 | 0 | 0 | 10/02/2018 | 10/02/2018 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2018 |  | 8/31/2020 | N | EXP | 368 |  |  | 0 | 0 | 0 |  |  | 8/27/2020 | Connected |  | N
National Grid | CLINTON | 751550 | 01510 | 11.5 | Solar | 05_09_702W3 | 02/17/2026 | 02/20/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | RANDOLPH | 443997 | 02368 | 0 | Other | 05_07_94W41 | 11/09/2022 |  | 121 | 113 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 613402 | 01915 | 3.8 | Solar | 05_01_216W3 | 05/29/2024 | 05/31/2024 | 1 | 0 | 1 | 06/03/2024 | 06/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 |  | 6/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/5/2024 | Connected |  | N
National Grid | ATHOL | 572680 | 01331 | 5 | Solar | 05_07_5W2 | 12/04/2023 | 12/05/2023 | 1 | 0 | 1 | 12/06/2023 | 12/06/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 | 12/04/2023 | 2/4/2025 | Y | EXP | 365 | 05/14/2024 | 05/13/2024 | 0 | 0 | 0 |  |  | 5/17/2024 | Connected |  | N
National Grid | BROCKTON | 177568 | 02301 | 15.2 | Solar | 05_12_18L1 | 09/14/2017 | 09/14/2017 | 9 | 9 | 0 | 09/27/2017 | 09/27/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/19/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 174141 | 01510 | 52.8 | Solar | 05_09_702W3 | 04/13/2012 | 04/13/2012 | 8 | 0 | 8 | 04/27/2012 | 04/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 04/13/2012 | 6/1/2012 | Y | EXP | 194 |  |  | 0 | 0 | 0 | 4/29/2013 | 4/29/2013 | 4/29/2013 | Connected |  | N
National Grid | RANDOLPH | 589714 | 02368 | 980 | Solar | 05_07_94W41 | 03/20/2024 | 06/25/2024 | 66 | 58 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2024 | 09/16/2024 | 58 | 40 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 618307 | 01915 | 10 | Solar | 05_01_216W3 | 06/17/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 | 06/17/2024 | 8/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2024 | Connected |  | N
National Grid | ORANGE | 603025 | 01364 | 10 | Solar | 05_07_5W2 | 04/15/2024 | 04/19/2024 | 4 | 0 | 4 | 04/22/2024 | 04/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 04/15/2024 | 12/31/2025 | Y | EXP | 485 | 07/17/2024 | 10/03/2024 | 79 | 0 | 79 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 177563 | 02301 | 10 | Solar | 05_12_18L1 | 07/14/2017 | 07/14/2017 | 9 | 0 | 9 | 01/03/2018 | 01/03/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2018 |  | 9/28/2018 | N | EXP | 245 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 174501 | 01523 | 230 | Hydro | 05_09_702W3 | 05/08/2009 | 05/08/2009 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2010 |  | 10/31/2012 | N | STD | 903 |  |  | 0 | 0 | 0 | 10/22/2012 | 10/22/2012 | 10/22/2012 | Connected |  | N
National Grid | RANDOLPH | 638244 | 02368 | 990 | Solar | 05_07_94W42 | 07/08/2025 | 08/11/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2025 | 09/09/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BEVERLY | 620430 | 01915 | 6.09 | Solar | 05_01_216W3 | 06/28/2024 | 03/03/2025 | 36 | 32 | 4 | 03/04/2025 | 03/04/2025 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | ATHOL | 616727 | 01331 | 3.8 | Solar | 05_07_5W2 | 06/10/2024 | 06/25/2024 | 4 | 0 | 4 | 06/26/2024 | 06/26/2024 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 06/10/2024 | 12/31/2025 | Y | EXP | 365 | 02/27/2025 | 11/21/2025 | 268 | 0 | 268 |  |  | 12/3/2025 | Connected |  | N
National Grid | BROCKTON | 178337 | 02301 |  | Solar | 05_12_18L1 | 11/17/2017 | 11/17/2017 | 93 | 92 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/25/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 174688 | 01510 | 2000 | Solar | 05_09_702W3 | 04/11/2011 | 04/11/2011 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/22/2011 | 10/06/2011 | 74 | 0 | 74 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 278 | 06/28/2013 | 09/10/2013 | 50 | 0 | 50 | 8/28/2013 | 8/28/2013 | 9/6/2013 | Connected |  | N
National Grid | RANDOLPH | 696434 | 02368 | 360 | Solar | 05_07_94W42 | 08/18/2025 | 03/26/2026 | 148 | 138 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2026 |  | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BEVERLY | 630507 | 01915 | 3.8 | Solar | 05_01_216W3 | 08/06/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 617723 | 01331 | 6 | Solar | 05_07_5W2 | 06/13/2024 | 08/02/2024 | 8 | 6 | 2 | 08/05/2024 | 08/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 11/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | BROCKTON | 178641 | 02301 | 15.2 | Solar | 05_12_18L1 | 04/10/2018 | 04/10/2018 | 27 | 7 | 20 | 05/21/2018 | 05/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 174687 | 01510 | 1000 | Solar | 05_09_702W3 | 04/11/2011 | 04/11/2011 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/22/2011 | 10/06/2011 | 74 | 0 | 74 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 278 | 06/28/2013 | 09/10/2013 | 50 | 0 | 50 | 8/28/2013 | 8/28/2013 | 9/6/2013 | Connected |  | N
National Grid | RANDOLPH | 733055 | 02368 | 620 | Solar | 05_07_94W42 | 01/13/2026 |  | 53 | 43 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BEVERLY | 637107 | 01915 | 10 | Solar | 05_01_216W3 | 09/02/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/02/2024 | 12/3/2025 | Y | EXP | 365 | 03/05/2025 | 03/11/2025 | 7 | 0 | 7 |  |  | 3/25/2025 | Connected |  | N
National Grid | ATHOL | 647267 | 01331 | 5.76 | Solar | 05_07_5W2 | 10/16/2024 | 11/18/2024 | 7 | 4 | 3 | 11/19/2024 | 11/19/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/16/2024 | 1/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | STOUGHTON | 230494 | 02072 | 9.92 | Solar | 05_12_18L1 | 06/17/2019 | 06/24/2019 | 5 | 5 | 0 | 06/25/2019 | 06/25/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 | 06/17/2019 | 10/15/2019 | Y | EXP | 106 | 08/16/2019 | 09/09/2019 | 24 | 0 | 24 |  |  | 9/25/2019 | Connected |  | N
National Grid | CLINTON | 175659 | 01510 | 600 | Solar | 05_09_702W3 | 05/22/2014 | 05/22/2014 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/03/2014 | 07/08/2014 | 23 | 0 | 23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2015 | 05/22/2014 | 11/28/2016 | Y | STD | 626 | 01/22/2016 | 01/22/2016 | 0 | 0 | 0 | 12/6/2016 | 12/6/2016 | 12/29/2016 | Connected |  | N
National Grid | RANDOLPH | 174339 | 02368 | 1725 | Solar | 05_07_94W42 | 01/30/2012 | 01/30/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2012 | 05/05/2012 | 30 | 0 | 30 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 | 01/30/2012 | 12/31/2016 | Y | STD | 1363 | 08/20/2015 | 03/31/2016 | 151 | 0 | 151 | 4/5/2016 | 4/5/2016 | 4/5/2016 | Connected |  | N
National Grid | BEVERLY | 639366 | 01915 | 3.8 | Solar | 05_01_216W3 | 09/11/2024 | 10/10/2024 | 11 | 8 | 3 | 10/11/2024 | 10/11/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/11/2024 | 1/26/2026 | Y | EXP | 365 | 01/16/2025 | 03/13/2025 | 57 | 0 | 57 |  |  | 6/3/2025 | Connected |  | N
National Grid | ORANGE | 662742 | 01364 | 7.6 | Solar | 05_07_5W2 | 12/27/2024 | 02/03/2025 | 4 | 0 | 4 | 02/04/2025 | 02/04/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | BROCKTON | 368295 | 02301 | 53.3 | Solar | 05_12_18L1 | 07/07/2021 | 07/31/2021 | 18 | 9 | 9 | 08/02/2021 | 08/02/2021 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2021 |  | 10/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2021 | Connected |  | N
National Grid | LANCASTER | 175734 | 01523 | 576 | Solar | 05_09_702W3 | 08/11/2014 | 08/11/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2014 | 09/19/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 | 08/11/2014 | 1/31/2018 | Y | STD | 1016 |  |  | 0 | 0 | 0 | 4/4/2018 | 4/4/2018 | 5/31/2018 | Connected |  | N
National Grid | RANDOLPH | 174764 | 02368 | 332 | Solar | 05_07_94W42 | 08/23/2012 | 08/23/2012 | 11 | 3 | 8 | 09/11/2012 | 09/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2013 | 08/23/2012 | 11/30/2012 | Y | EXP | 59 | 02/28/2013 | 05/13/2013 | 47 | 0 | 47 | 5/28/2013 | 5/28/2013 | 5/30/2013 | Connected |  | N
National Grid | BEVERLY | 643765 | 01915 | 3.8 | Solar | 05_01_216W3 | 10/01/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/01/2024 | 12/11/2025 | Y | EXP | 365 | 03/15/2025 | 03/21/2025 | 7 | 0 | 7 |  |  | 4/10/2025 | Connected |  | N
National Grid | ATHOL | 673253 | 01331 | 10 | Solar | 05_07_5W2 | 02/20/2025 | 02/21/2025 | 1 | 0 | 1 | 02/24/2025 | 02/24/2025 | 61 | 40 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | STOUGHTON | 396672 | 02072 | 0 | Other | 05_12_18L1 | 01/06/2022 | 01/19/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2022 | 03/01/2022 | 28 | 14 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 175790 | 01510 | 112 | Solar | 05_09_702W3 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/22/2015 | 09/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 |  | 9/23/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 3/22/2016 | 3/22/2016 | 4/15/2016 | Connected |  | N
National Grid | RANDOLPH | 178270 | 02368 | 936 | Solar | 05_07_94W42 | 01/09/2018 | 01/09/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/21/2018 | 26 | 0 | 26 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2018 | 01/09/2018 | 11/30/2020 | Y | STD | 484 |  |  | 0 | 0 | 0 |  |  | 11/30/2020 | Connected |  | N
National Grid | BEVERLY | 646190 | 01915 | 10.26 | Solar | 05_01_216W3 | 10/10/2024 | 10/21/2024 | 4 | 2 | 2 | 10/22/2024 | 10/22/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/10/2024 | 11/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | ORANGE | 684214 | 01364 | 0 | Solar | 05_07_5W2 | 04/10/2025 |  | 115 | 25 | 90 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 500295 | 02072 | 15.66 | Solar | 05_12_18L1 | 02/10/2023 | 02/15/2023 | 3 | 2 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 5/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | CLINTON | 175865 | 01510 | 1000 | Solar | 05_09_702W3 | 09/22/2015 | 09/22/2015 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2015 | 11/02/2015 | 8 | 0 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/28/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 178269 | 02368 | 233.33 | Solar | 05_07_94W42 | 01/09/2018 | 01/09/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/21/2018 | 26 | 0 | 26 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2018 | 01/09/2018 | 12/31/2020 | Y | STD | 477 |  |  | 0 | 0 | 0 | 12/28/2020 | 12/24/2020 | 12/30/2020 | Connected |  | N
National Grid | BEVERLY | 649756 | 01915 | 3.8 | Solar | 05_01_216W3 | 11/05/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 11/05/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | ORANGE | 711862 | 01364 | 23.18 | Solar | 05_07_5W2 | 08/13/2025 | 08/18/2025 | 3 | 0 | 3 | 08/19/2025 | 08/19/2025 | 54 | 24 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 537790 | 02072 | 60 | Solar | 05_12_18L1 | 08/10/2023 | 09/01/2023 | 16 | 7 | 9 | 09/05/2023 | 09/05/2023 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 176294 | 01510 | 2000 | Solar | 05_09_702W3 | 09/09/2015 | 09/09/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2015 | 10/19/2015 | 25 | 0 | 25 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/15/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 178506 | 02368 | 2000 | Solar | 05_07_94W42 | 01/25/2018 | 03/15/2018 | 25 | 13 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2018 | 05/01/2018 | 33 | 15 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 01/25/2018 | 4/21/2023 | Y | STD | 433 | 07/30/2022 | 01/14/2023 | 169 | 0 | 169 |  |  | 5/8/2023 | Connected |  | N
National Grid | BEVERLY | 665491 | 01915 | 5.76 | Solar | 05_01_216W3 | 01/14/2025 | 01/29/2025 | 5 | 0 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | ATHOL | 715852 | 01331 | 3.8 | Solar | 05_07_5W2 | 09/01/2025 | 09/18/2025 | 5 | 0 | 5 | 10/01/2025 | 10/01/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 568254 | 02072 | 480 | Solar | 05_12_18L1 | 12/19/2023 | 01/08/2024 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/09/2024 | 02/06/2024 | 20 | 1 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 176800 | 01510 | 288 | Solar | 05_09_702W3 | 02/25/2016 | 02/25/2016 | 3 | 3 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 | 07/01/2016 | 08/03/2016 | 22 | 1 | 21 |  |  | 0 | 0 | 0 | 08/03/2016 | 22 | 1 | 21 |  |  | 0 | 0 | 0 | 3/13/2017 |  | 6/29/2018 | N | EXP | 473 |  |  | 0 | 0 | 0 | 12/7/2017 | 12/7/2017 | 12/7/2017 | Connected |  | N
National Grid | RANDOLPH | 178702 | 02368 | 358 | Solar | 05_07_94W42 | 02/09/2018 | 02/09/2018 | 10 | 0 | 10 | 03/12/2018 | 03/12/2018 | 44 | 0 | 44 | 06/21/2018 | 07/20/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 | 07/20/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 | 8/3/2018 |  | 6/30/2020 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 641164 | 01915 | 300 | Solar | 05_07_913W43 | 11/20/2024 | 03/10/2025 | 73 | 64 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/11/2025 | 04/07/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NEW SALEM | 679335 | 01355 | 894 | Solar | 05_07_5W3 | 04/15/2025 | 08/20/2025 | 87 | 77 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2025 | 09/11/2025 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | STOUGHTON | 591448 | 02072 | 20 | Solar | 05_12_18L1 | 02/20/2024 | 03/27/2024 | 26 | 23 | 3 | 03/28/2024 | 03/28/2024 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 02/20/2024 | 7/13/2025 | Y | EXP | 365 | 07/17/2024 | 08/21/2024 | 36 | 0 | 36 |  |  | 12/20/2024 | Connected |  | N
National Grid | CLINTON | 176868 | 01510 | 499 | Solar | 05_09_702W3 | 03/01/2016 | 03/01/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2016 | 05/12/2016 | 48 | 33 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/7/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 208164 | 02368 | 2000 | Solar | 05_07_94W42 | 09/06/2019 | 09/19/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2019 | 10/03/2019 | 9 | 4 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 717898 | 01915 | 7.6 | Solar | 05_07_913W43 | 09/09/2025 | 10/16/2025 | 1 | 0 | 1 | 11/05/2025 | 11/05/2025 | 24 | 6 | 18 | 01/12/2026 | 03/02/2026 | 34 | 0 | 34 |  |  | 0 | 0 | 0 | 03/02/2026 | 34 | 0 | 34 |  |  | 0 | 0 | 0 | 3/5/2026 |  | 3/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ORANGE | 686437 | 01364 | 3.8 | Solar | 05_07_5W3 | 04/21/2025 | 05/08/2025 | 5 | 0 | 5 | 05/22/2025 | 05/22/2025 | 50 | 36 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | STOUGHTON | 611463 | 02072 | 75 | Solar | 05_12_18L1 | 06/13/2024 | 10/03/2024 | 77 | 68 | 9 | 10/04/2024 | 10/04/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 177067 | 01510 | 3276 | Solar | 05_09_702W3 | 03/20/2017 | 03/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2017 | 04/07/2017 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2017 | 03/20/2017 | 3/5/2020 | Y | STD | 709 | 04/09/2019 | 06/06/2019 | 58 | 0 | 58 |  |  | 3/5/2020 | Connected |  | N
National Grid | RANDOLPH | 246166 | 02368 | 2000 | Solar | 05_07_94W42 | 08/28/2019 | 09/30/2019 | 22 | 17 | 5 |  |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/14/2020 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 727503 | 01915 | 3.8 | Solar | 05_07_913W43 | 10/17/2025 | 12/09/2025 | 5 | 0 | 5 | 01/07/2026 | 01/07/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ORANGE | 699809 | 01364 | 23 | Solar | 05_07_5W3 | 06/20/2025 | 09/04/2025 | 6 | 3 | 3 | 09/04/2025 | 09/04/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 06/20/2025 | 11/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | STOUGHTON | 636968 | 02072 | 10 | Solar | 05_12_18L1 | 08/30/2024 | 09/17/2024 | 4 | 0 | 4 | 09/18/2024 | 09/18/2024 | 22 | 14 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 | 08/30/2024 | 10/31/2025 | Y | EXP | 365 | 12/19/2024 | 12/18/2024 | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | CLINTON | 177395 | 01510 | 995 | Landfill Gas | 05_09_702W3 | 02/21/2017 | 02/21/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/24/2017 | 03/09/2017 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/26/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 639911 | 02368 | 5.76 | Solar | 05_07_94W43 | 09/12/2024 | 10/09/2024 | 16 | 12 | 4 | 10/10/2024 | 10/10/2024 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/12/2024 | 12/18/2025 | Y | EXP | 365 | 04/01/2025 | 11/19/2025 | 233 | 0 | 233 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 736782 | 01915 | 10 | Solar | 05_07_913W43 | 11/26/2025 | 01/12/2026 | 2 | 0 | 2 | 02/04/2026 | 02/04/2026 | 28 | 12 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NEW SALEM | 706300 | 01364 | 5.76 | Solar | 05_07_5W3 | 07/21/2025 | 08/05/2025 | 3 | 0 | 3 | 08/14/2025 | 08/14/2025 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 | 07/21/2025 | 11/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | STOUGHTON | 652042 | 02072 | 7.6 | Solar | 05_12_18L1 | 11/13/2024 | 12/27/2024 | 17 | 12 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N
National Grid | CLINTON | 177742 | 01510 | 200 | Solar | 05_09_702W3 | 05/30/2017 | 05/30/2017 | 32 | 29 | 3 | 07/17/2017 | 07/17/2017 | 25 | 2 | 23 | 09/05/2017 | 10/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2017 | 05/30/2017 | 9/21/2018 | Y | EXP | 332 |  |  | 0 | 0 | 0 |  |  | 9/11/2018 | Connected |  | N
National Grid | RANDOLPH | 736705 | 02368 | 11.5 | Solar | 05_07_94W43 | 11/26/2025 | 11/28/2025 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2026 |  | 3/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 737466 | 01915 | 15.2 | Solar | 05_07_913W43 | 12/02/2025 | 12/05/2025 | 3 | 0 | 3 | 12/08/2025 | 12/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ORANGE | 712288 | 01364 | 990 | Solar | 05_07_5W3 | 11/14/2025 | 03/05/2026 | 73 | 67 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2026 | 03/26/2026 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STOUGHTON | 688360 | 02072 | 14.82 | Solar | 05_12_18L1 | 05/12/2025 | 05/22/2025 | 7 | 4 | 3 | 05/23/2025 | 05/23/2025 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 | 05/12/2025 | 7/8/2026 | Y | EXP | 365 | 11/14/2025 | 11/24/2025 | 11 | 0 | 11 |  |  | 11/25/2025 | Connected |  | N
National Grid | STOUGHTON | 177860 | 02072 | 6740 | Solar | 05_09_702W3 | 06/13/2017 | 06/13/2017 | 24 | 24 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2017 | 08/11/2017 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/18/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 742627 | 02368 | 11.5 | Solar | 05_07_94W43 | 12/30/2025 | 01/06/2026 | 4 | 0 | 4 | 01/07/2026 | 01/07/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 747644 | 01915 | 11.5 | Solar | 05_07_913W43 | 01/27/2026 | 01/29/2026 | 2 | 0 | 2 | 01/30/2026 | 01/30/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ORANGE | 717832 | 01364 | 3.8 | Solar | 05_07_5W3 | 09/09/2025 | 10/15/2025 | 2 | 0 | 2 | 01/26/2026 | 01/26/2026 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STOUGHTON | 697074 | 02072 | 50 | Solar | 05_12_18L1 | 06/10/2025 | 06/25/2025 | 9 | 9 | 0 | 06/26/2025 | 06/26/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | STOUGHTON | 177957 | 02072 | 1980 | Solar | 05_09_702W3 | 10/23/2017 | 01/11/2018 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2018 | 02/01/2018 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 |  | 10/31/2018 | N | STD | 141 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 751771 | 02368 | 15.58 | Solar | 05_07_94W43 | 02/18/2026 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WENHAM | 174938 | 01984 | 68.4 | Solar | 05_07_913W43 | 10/13/2011 | 10/13/2011 | 0 | 0 | 0 | 11/09/2011 | 11/09/2011 | 555 | 0 | 555 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2012 |  | 11/30/2012 | N | EXP | 58 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 719796 | 01331 | 3.8 | Solar | 05_07_5W3 | 09/17/2025 | 12/17/2025 | 61 | 57 | 4 | 12/18/2025 | 12/18/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  | 2/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | STOUGHTON | 649950 | 02072 | 3.77 | Solar | 05_12_18L2 | 10/28/2024 | 01/23/2025 | 29 | 25 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 10/28/2024 | 5/9/2026 | Y | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | STOUGHTON | 178055 | 02072 | 8140 | Solar | 05_09_702W3 | 07/03/2017 | 07/18/2017 | 8 | 7 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2017 | 08/11/2017 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 756813 | 02368 | 20 | Solar | 05_07_94W43 | 03/16/2026 | 03/19/2026 | 3 | 0 | 3 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WENHAM | 176878 | 01984 | 28.8 | Solar | 05_07_913W43 | 05/04/2016 | 05/04/2016 | 2 | 2 | 0 | 05/06/2016 | 05/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2016 |  | 5/9/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 1/9/2017 | 1/9/2017 | 1/9/2017 | Connected |  | N
National Grid | ORANGE | 727147 | 01364 | 3.8 | Solar | 05_07_5W3 | 10/16/2025 | 10/23/2025 | 7 | 6 | 1 | 12/02/2025 | 12/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 186491 | 02301 | 15.2 | Solar | 05_12_18L2 | 05/29/2018 | 05/29/2018 | 10 | 0 | 10 | 06/13/2018 | 06/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 6/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2018 | Connected |  | N
National Grid | STOUGHTON | 203390 | 02072 | 1000 | Solar | 05_09_702W3 | 01/11/2019 | 01/25/2019 | 8 | 0 | 8 |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 01/28/2019 | 02/25/2019 | 19 | 6 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 177795 | 02368 | 38.2 | Solar | 05_07_94W43 | 08/02/2017 | 08/02/2017 | 6 | 6 | 0 | 08/11/2017 | 08/11/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 | 08/02/2017 | 8/8/2018 | Y | EXP | 358 | 11/27/2017 | 12/06/2017 | 7 | 0 | 7 | 4/6/2018 | 4/6/2018 | 4/17/2018 | Connected |  | N
National Grid | WENHAM | 177310 | 01984 | 22.8 | Solar | 05_07_913W43 | 11/17/2016 | 11/17/2016 | 2 | 2 | 0 | 11/22/2016 | 11/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 |  | 11/23/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 6/27/2017 | 6/27/2017 | 6/30/2017 | Connected |  | N
National Grid | ATHOL | 727087 | 01331 | 10 | Solar | 05_07_5W3 | 10/16/2025 | 11/14/2025 | 21 | 18 | 3 | 01/08/2026 | 01/08/2026 | 57 | 24 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 210634 | 02301 | 9.92 | Solar | 05_12_18L2 | 03/14/2019 | 03/15/2019 | 0 | 0 | 0 | 03/18/2019 | 03/18/2019 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2019 |  | 7/26/2019 | N | EXP | 105 |  |  | 0 | 0 | 0 |  |  | 7/15/2019 | Connected |  | N
National Grid | STOUGHTON | 289276 | 02072 | 0 | Other | 05_09_702W3 | 05/15/2020 | 05/22/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2020 | 06/18/2020 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 382329 | 02368 | 240 | Solar | 05_07_94W43 | 11/11/2021 | 12/13/2021 | 22 | 15 | 7 | 12/14/2021 | 12/14/2021 | 25 | 2 | 23 | 03/01/2022 | 10/11/2022 | 131 | 0 | 131 |  |  | 0 | 0 | 0 | 10/11/2022 | 131 | 0 | 131 |  |  | 0 | 0 | 0 | 9/20/2022 | 11/11/2021 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WENHAM | 178335 | 01984 | 60.8 | Solar | 05_07_913W43 | 11/17/2017 | 11/17/2017 | 69 | 69 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/25/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 735536 | 01331 | 5.76 | Solar | 05_07_5W3 | 11/21/2025 | 12/01/2025 | 5 | 0 | 5 | 12/02/2025 | 12/02/2025 | 34 | 13 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | EASTON | 302941 | 02356 | 15.2 | Solar | 05_12_18L2 | 07/24/2020 | 07/27/2020 | 0 | 0 | 0 | 07/28/2020 | 07/28/2020 | 36 | 21 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 | 07/24/2020 | 6/30/2021 | Y | EXP | 365 | 01/05/2021 | 02/12/2021 | 37 | 0 | 37 |  |  | 2/24/2021 | Connected |  | N
National Grid | STOUGHTON | 299108 | 02072 | 0 | Other | 05_09_702W3 | 08/17/2020 | 09/30/2020 | 31 | 29 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/24/2020 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 386450 | 02368 | 15.2 | Solar | 05_07_94W43 | 10/05/2021 | 01/05/2022 | 63 | 56 | 7 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2022 |  | 2/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2022 | Connected |  | N
National Grid | WENHAM | 178651 | 01984 | 10 | Solar | 05_07_913W43 | 12/18/2017 | 12/18/2017 | 0 | 0 | 0 | 07/11/2018 | 07/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2018 |  | 12/23/2018 | N | EXP | 166 |  |  | 0 | 0 | 0 |  |  | 5/14/2019 | Connected |  | N
National Grid | ATHOL | 743435 | 01331 | 5.76 | Solar | 05_07_5W3 | 01/05/2026 | 01/06/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROCKTON | 304665 | 02301 | 8.99 | Solar | 05_12_18L2 | 08/04/2020 | 08/19/2020 | 11 | 11 | 0 | 08/20/2020 | 08/20/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2020 |  | 8/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2020 | Connected |  | N
National Grid | STOUGHTON | 302782 | 02072 | 7.92 | Solar | 05_09_702W3 | 07/24/2020 | 08/26/2020 | 22 | 22 | 0 | 08/27/2020 | 08/27/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2020 |  | 9/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2020 | Connected |  | N
National Grid | RANDOLPH | 417294 | 02368 | 15.2 | Solar | 05_07_94W43 | 03/14/2022 | 03/15/2022 | 1 | 0 | 1 | 03/16/2022 | 03/16/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  | 5/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2022 | Connected |  | N
National Grid | HAMILTON | 212974 | 01982 | 6 | Solar | 05_07_913W43 | 03/20/2019 | 03/28/2019 | 5 | 0 | 5 | 03/29/2019 | 03/29/2019 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2019 |  | 4/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2019 | Connected |  | N
National Grid | ATHOL | 750771 | 01331 | 23 | Solar | 05_07_5W3 | 02/12/2026 | 03/24/2026 | 26 | 24 | 2 | 03/25/2026 | 03/25/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | EASTON | 335872 | 02356 | 100 | Solar | 05_12_18L2 | 01/08/2021 | 01/25/2021 | 9 | 0 | 9 | 01/26/2021 | 01/26/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  | 12/16/2022 | N | EXP | 275 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | STOUGHTON | 312441 | 02072 | 0 | Other | 05_09_702W3 | 09/22/2020 | 09/30/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/27/2020 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 418873 | 02368 | 15.2 | Solar | 05_07_94W43 | 03/21/2022 | 03/22/2022 | 1 | 0 | 1 | 03/23/2022 | 03/23/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2022 |  | 6/30/2023 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  | 7/6/2023 | Connected |  | N
National Grid | WENHAM | 273993 | 01984 | 10 | Solar | 05_07_913W43 | 04/17/2020 | 05/28/2020 | 27 | 27 | 0 | 05/29/2020 | 05/29/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 5/28/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEW SALEM | 753188 | 01355 | 3.8 | Solar | 05_07_5W3 | 02/25/2026 | 03/02/2026 | 3 | 0 | 3 | 03/12/2026 | 03/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STOUGHTON | 363282 | 02072 | 7.6 | Solar | 05_12_18L2 | 06/10/2021 | 06/11/2021 | 1 | 0 | 1 | 06/14/2021 | 06/14/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2021 |  | 8/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2022 | Connected |  | N
National Grid | STOUGHTON | 348650 | 02072 | 7.68 | Solar | 05_09_702W3 | 03/26/2021 | 04/02/2021 | 4 | 3 | 1 | 04/05/2021 | 04/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2021 |  | 4/1/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2021 | Connected |  | N
National Grid | RANDOLPH | 420687 | 02368 | 15.2 | Solar | 05_07_94W43 | 03/29/2022 | 03/30/2022 | 1 | 0 | 1 | 03/31/2022 | 03/31/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2022 |  | 4/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2022 | Connected |  | N
National Grid | BEVERLY | 310322 | 01915 | 249 | Solar | 05_07_913W43 | 10/13/2020 | 10/29/2020 | 12 | 4 | 8 | 10/30/2020 | 10/30/2020 | 22 | 0 | 22 | 04/30/2021 | 04/21/2022 | 244 | 33 | 211 |  |  | 0 | 0 | 0 | 04/21/2022 | 244 | 33 | 211 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 753484 | 01364 | 10 | Solar | 05_07_5W3 | 02/27/2026 | 03/04/2026 | 1 | 0 | 1 | 03/12/2026 | 03/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STOUGHTON | 364985 | 02072 | 43.2 | Solar | 05_12_18L2 | 07/14/2021 | 12/27/2021 | 37 | 27 | 10 | 09/03/2021 | 09/03/2021 | 118 | 101 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2022 |  | 3/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2022 | Connected |  | N
National Grid | STOUGHTON | 397106 | 02072 | 3600 | Solar | 05_09_702W3 | 01/31/2022 |  | 52 | 40 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 476653 | 02368 | 0 | Solar | 05_07_94W43 | 02/23/2024 | 07/16/2024 | 63 | 61 | 2 | 07/17/2024 | 07/17/2024 | 57 | 43 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WENHAM | 328974 | 01984 | 7.6 | Solar | 05_07_913W43 | 12/01/2020 | 12/03/2020 | 1 | 0 | 1 | 12/04/2020 | 12/04/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 7/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/3/2022 | Connected |  | N
National Grid | ORANGE | 175383 | 01364 | 17 | Solar | 05_07_5W3 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2014 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 374102 | 02072 | 0 | Solar | 05_12_18L2 | 08/05/2021 | 08/06/2021 | 1 | 0 | 1 | 08/09/2021 | 08/09/2021 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 | 08/05/2021 | 2/9/2023 | Y | EXP | 365 | 01/06/2022 | 02/09/2022 | 35 | 0 | 35 |  |  | 7/12/2022 | Connected |  | N
National Grid | STOUGHTON | 439057 | 02072 | 9.8 | Solar | 05_09_702W3 | 09/14/2022 | 09/23/2022 | 8 | 7 | 1 | 09/26/2022 | 09/26/2022 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 |  | 12/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2023 | Connected |  | N
National Grid | RANDOLPH | 486030 | 02368 | 7.6 | Solar | 05_07_94W43 | 01/12/2023 | 01/18/2023 | 3 | 0 | 3 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 2/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2023 | Connected |  | N
National Grid | WENHAM | 331347 | 01984 | 10 | Solar | 05_07_913W43 | 01/21/2021 | 01/27/2021 | 3 | 2 | 1 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/21/2021 | 10/16/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2021 | Connected |  | N
National Grid | ATHOL | 176957 | 01331 | 105 | Solar | 05_07_5W3 | 07/15/2016 | 07/15/2016 | 2 | 2 | 0 | 07/19/2016 | 07/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2016 |  | 2/1/2017 | N | EXP | 196 |  |  | 0 | 0 | 0 | 2/22/2017 | 2/22/2017 | 3/8/2017 | Connected |  | N
National Grid | STOUGHTON | 628548 | 02072 | 7.6 | Solar | 05_12_18L2 | 07/31/2024 | 09/05/2024 | 17 | 15 | 2 | 09/06/2024 | 09/06/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 07/31/2024 | 10/22/2025 | Y | EXP | 365 | 11/21/2024 | 12/02/2024 | 12 | 0 | 12 |  |  | 3/18/2025 | Connected |  | N
National Grid | STOUGHTON | 440575 | 02072 | 11.4 | Solar | 05_09_702W3 | 09/08/2022 |  | 275 | 63 | 212 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 491489 | 02368 | 7.6 | Solar | 05_07_94W43 | 01/11/2023 | 01/12/2023 | 1 | 0 | 1 | 01/13/2023 | 01/13/2023 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2023 |  | 11/1/2024 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  | 7/27/2024 | Connected |  | N
National Grid | HAMILTON | 331261 | 01982 | 8.88 | Solar | 05_07_913W43 | 12/11/2020 | 01/08/2021 | 18 | 14 | 4 | 01/11/2021 | 01/11/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/11/2020 | 5/15/2023 | Y | EXP | 365 | 11/25/2021 | 02/12/2022 | 80 | 0 | 80 |  |  | 4/5/2023 | Connected |  | N
National Grid | ATHOL | 177737 | 01331 | 10 | Solar | 05_07_5W3 | 03/23/2017 | 03/23/2017 | 2 | 1 | 1 | 03/28/2017 | 03/28/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 | 03/23/2017 | 6/30/2018 | Y | EXP | 458 | 12/28/2017 | 01/19/2018 | 14 | 0 | 14 | 4/17/2018 | 4/17/2018 | 6/8/2018 | Connected |  | N
National Grid | EASTON | 640696 | 02356 | 31.92 | Solar | 05_12_18L2 | 11/25/2024 | 02/03/2025 | 46 | 36 | 10 | 02/04/2025 | 02/04/2025 | 69 | 48 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  | 6/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | STOUGHTON | 501750 | 02072 | 7.6 | Solar | 05_09_702W3 | 03/02/2023 | 03/07/2023 | 3 | 0 | 3 | 03/08/2023 | 03/08/2023 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 |  | 4/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2023 | Connected |  | N
National Grid | RANDOLPH | 494553 | 02368 | 19 | Solar | 05_07_94W43 | 01/24/2023 | 01/25/2023 | 2 | 1 | 1 | 01/26/2023 | 01/26/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 3/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2023 | Connected |  | N
National Grid | WENHAM | 340789 | 01984 | 15.2 | Solar | 05_07_913W43 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 178514 | 01331 | 10 | Solar | 05_07_5W3 | 03/08/2018 | 03/08/2018 | 25 | 0 | 25 | 04/13/2018 | 04/13/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 | 03/08/2018 | 8/1/2019 | Y | EXP | 447 |  |  | 0 | 0 | 0 |  |  | 8/1/2019 | Connected |  | N
National Grid | STOUGHTON | 647884 | 02072 | 4.06 | Solar | 05_12_18L2 | 10/21/2024 | 11/07/2024 | 10 | 8 | 2 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/21/2024 | 12/18/2025 | Y | EXP | 365 | 02/11/2025 | 02/10/2025 | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | STOUGHTON | 504058 | 02072 | 7.6 | Solar | 05_09_702W3 | 02/22/2023 | 03/02/2023 | 6 | 4 | 2 | 03/03/2023 | 03/03/2023 | 78 | 56 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  | 9/30/2025 | N | EXP | 730 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 553165 | 02368 | 10 | Solar | 05_07_94W43 | 09/08/2023 | 11/13/2023 | 44 | 43 | 1 | 11/14/2023 | 11/14/2023 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 3/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMILTON | 375475 | 01982 | 15.2 | Solar | 05_07_913W43 | 08/12/2021 | 01/09/2022 | 4 | 0 | 4 | 08/19/2021 | 08/19/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  | 9/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2022 | Connected |  | N
National Grid | NEW SALEM | 186757 | 01355 | 7.6 | Solar | 05_07_5W3 | 06/18/2018 | 06/18/2018 | 9 | 2 | 7 | 07/02/2018 | 07/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 716971 | 02356 | 7.6 | Solar | 05_12_18L2 | 09/05/2025 | 11/03/2025 | 3 | 0 | 3 | 11/04/2025 | 11/04/2025 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2026 | Connected |  | N
National Grid | STOUGHTON | 512262 | 02072 | 7.6 | Solar | 05_09_702W3 | 03/24/2023 | 03/27/2023 | 1 | 0 | 1 | 03/28/2023 | 03/28/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 03/24/2023 | 7/13/2024 | Y | EXP | 365 | 07/07/2023 | 07/12/2023 | 6 | 0 | 6 |  |  | 8/23/2023 | Connected |  | N
National Grid | RANDOLPH | 560639 | 02368 | 6 | Solar | 05_07_94W43 | 10/23/2023 | 10/25/2023 | 2 | 0 | 2 | 10/26/2023 | 10/26/2023 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 | 10/23/2023 | 1/1/2025 | Y | EXP | 365 | 03/05/2024 | 03/26/2024 | 22 | 0 | 22 |  |  | 4/17/2024 | Connected |  | N
National Grid | WENHAM | 414774 | 01984 | 0 | Solar | 05_07_913W43 | 04/22/2022 | 04/26/2022 | 3 | 1 | 2 | 04/27/2022 | 04/27/2022 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  | 8/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | ATHOL | 188196 | 01331 | 400 | Solar | 05_07_5W3 | 07/10/2018 | 07/18/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 09/25/2018 | 10/25/2018 | 23 | 3 | 20 |  |  | 0 | 0 | 0 | 10/25/2018 | 23 | 3 | 20 |  |  | 0 | 0 | 0 | 11/27/2018 | 07/10/2018 | 7/7/2020 | Y | EXP | 435 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 672537 | 02072 | 5.76 | Solar | 05_12_19W1 | 02/18/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 4/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | STOUGHTON | 548337 | 02072 | 7.6 | Solar | 05_09_702W3 | 08/30/2023 |  | 103 | 75 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 572141 | 02368 | 6 | Solar | 05_07_94W43 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 |  | 1/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2024 | Connected |  | N
National Grid | WENHAM | 420576 | 01984 | 15.2 | Solar | 05_07_913W43 | 04/21/2022 | 04/22/2022 | 1 | 0 | 1 | 04/25/2022 | 04/25/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2022 |  | 9/30/2024 | N | EXP | 650 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEW SALEM | 188743 | 01355 | 7.6 | Solar | 05_07_5W3 | 06/20/2018 | 06/20/2018 | 10 | 8 | 2 | 07/16/2018 | 07/16/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 |  | 7/22/2019 | N | EXP | 365 | 04/24/2019 | 05/08/2019 | 14 | 0 | 14 |  |  | 10/28/2019 | Connected |  | N
National Grid | STOUGHTON | 732034 | 02072 | 5.76 | Solar | 05_12_19W1 | 11/06/2025 | 11/06/2025 | 1 | 0 | 1 | 12/30/2025 | 12/30/2025 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | STOUGHTON | 642119 | 02072 | 3.8 | Solar | 05_09_702W3 | 09/23/2024 | 10/14/2024 | 5 | 0 | 5 | 10/15/2024 | 10/15/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/23/2024 | 12/15/2025 | Y | EXP | 365 | 02/12/2025 | 02/11/2025 | 0 | 0 | 0 |  |  | 2/19/2025 | Connected |  | N
National Grid | RANDOLPH | 592215 | 02368 | 8.832 | Solar | 05_07_94W43 | 02/28/2024 | 03/22/2024 | 17 | 15 | 2 | 03/25/2024 | 03/25/2024 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 474223 | 01915 | 5.8 | Solar | 05_07_913W43 | 12/15/2022 | 01/03/2023 | 11 | 7 | 4 | 01/04/2023 | 01/04/2023 | 49 | 30 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2023 |  | 11/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2024 | Connected |  | N
National Grid | ATHOL | 203646 | 01331 | 5 | Solar | 05_07_5W3 | 01/03/2019 | 01/04/2019 | 0 | 0 | 0 | 01/07/2019 | 01/07/2019 | 136 | 0 | 136 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 753296 | 02301 | 5.76 | Solar | 05_12_19W1 | 02/26/2026 | 03/03/2026 | 4 | 0 | 4 | 03/19/2026 | 03/19/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STOUGHTON | 661629 | 02072 | 5.76 | Solar | 05_09_702W3 | 12/19/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 599024 | 02368 | 6 | Solar | 05_07_94W43 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 5/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2024 | Connected |  | N
National Grid | HAMILTON | 477659 | 01982 | 16.53 | Solar | 05_07_913W43 | 11/17/2022 | 11/22/2022 | 3 | 0 | 3 | 11/23/2022 | 11/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2022 |  | 5/20/2024 | N | EXP | 500 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 217727 | 01331 | 10 | Solar | 05_07_5W3 | 06/25/2019 | 07/02/2019 | 5 | 5 | 0 | 07/03/2019 | 07/03/2019 | 65 | 51 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 755800 | 02301 | 3.8 | Solar | 05_12_19W1 | 03/10/2026 | 03/13/2026 | 3 | 0 | 3 | 03/16/2026 | 03/16/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STOUGHTON | 663607 | 02072 | 10 | Solar | 05_09_702W3 | 01/03/2025 | 01/15/2025 | 4 | 0 | 4 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 01/03/2025 | 5/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2025 | Connected |  | N
National Grid | RANDOLPH | 636421 | 02368 | 23 | Battery Add-On | 05_07_94W43 | 08/29/2024 | 10/14/2024 | 12 | 11 | 1 | 10/15/2024 | 10/15/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  | 11/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2025 | Connected |  | N
National Grid | HAMILTON | 483858 | 01982 | 0 | Solar | 05_07_913W43 | 12/08/2022 | 12/12/2022 | 2 | 0 | 2 | 12/13/2022 | 12/13/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2023 |  | 9/12/2024 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 223582 | 01331 | 186.6 | Solar | 05_07_5W3 | 04/29/2019 | 05/21/2019 | 15 | 9 | 6 | 05/22/2019 | 05/22/2019 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 |  | 5/21/2021 | N | EXP | 720 |  |  | 0 | 0 | 0 |  |  | 6/14/2021 | Connected |  | N
National Grid | STOUGHTON | 174678 | 02072 | 22.8 | Solar | 05_12_19W1 | 12/30/2013 | 12/30/2013 | 286 | 284 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/30/2014 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 671862 | 02072 | 5.76 | Solar | 05_09_702W3 | 02/13/2025 | 03/04/2025 | 6 | 3 | 3 | 03/05/2025 | 03/05/2025 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/13/2025 | 5/20/2026 | Y | EXP | 365 | 10/14/2025 | 11/07/2025 | 25 | 0 | 25 |  |  | 11/21/2025 | Connected |  | N
National Grid | RANDOLPH | 645351 | 02368 | 3.8 | Solar | 05_07_94W43 | 10/08/2024 | 11/04/2024 | 6 | 1 | 5 | 11/05/2024 | 11/05/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/08/2024 | 12/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | Y
National Grid | SAUGUS | 540995 | 01906 | 6 | Solar | 05_07_913W43 | 08/22/2023 | 09/19/2023 | 19 | 16 | 3 | 09/20/2023 | 09/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEW SALEM | 225653 | 01355 | 7.6 | Solar | 05_07_5W3 | 06/25/2019 | 06/26/2019 | 0 | 0 | 0 | 06/27/2019 | 06/27/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  | 10/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 177346 | 02072 | 7.6 | Solar | 05_12_19W1 | 11/22/2016 | 11/22/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2016 |  | 11/28/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/9/2018 | 1/9/2018 | 8/14/2017 | Connected |  | N
National Grid | SHARON | 680545 | 02067 | 5.76 | Solar | 05_09_702W3 | 03/31/2025 | 04/09/2025 | 3 | 0 | 3 | 04/22/2025 | 04/22/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 654730 | 02368 | 15.356 | Solar | 05_07_94W43 | 01/08/2025 | 01/21/2025 | 9 | 7 | 2 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/27/2025 | Connected |  | N
National Grid | SAUGUS | 541916 | 01906 | 0 | Solar | 05_07_913W43 | 07/19/2023 | 07/26/2023 | 5 | 4 | 1 | 07/27/2023 | 07/27/2023 | 132 | 107 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2024 | Connected |  | N
National Grid | NEW SALEM | 234633 | 01355 | 10 | Solar | 05_07_5W3 | 06/14/2019 | 06/24/2019 | 6 | 5 | 1 | 06/25/2019 | 06/25/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 177551 | 02072 | 3.8 | Solar | 05_12_19W1 | 05/15/2017 | 05/15/2017 | 6 | 5 | 1 | 05/24/2017 | 05/24/2017 | 187 | 0 | 187 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2017 |  | 5/21/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 686524 | 02072 | 15.76 | Solar | 05_09_702W3 | 04/24/2025 | 05/05/2025 | 7 | 4 | 3 | 05/06/2025 | 05/06/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 697835 | 02368 | 14.82 | Solar | 05_07_94W43 | 06/11/2025 | 06/17/2025 | 4 | 0 | 4 | 06/18/2025 | 06/18/2025 | 24 | 12 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 | 06/11/2025 | 8/18/2026 | Y | EXP | 365 | 10/30/2025 | 02/11/2026 | 105 | 0 | 105 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 597061 | 01905 | 7.6 | Solar | 05_07_913W43 | 03/21/2024 | 04/08/2024 | 13 | 11 | 2 | 04/09/2024 | 04/09/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  | 4/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2024 | Connected |  | N
National Grid | ATHOL | 239082 | 01331 | 10 | Solar | 05_07_5W3 | 10/17/2019 | 10/23/2019 | 3 | 0 | 3 | 10/24/2019 | 10/24/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 |  | 2/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 190922 | 02072 | 7.6 | Solar | 05_12_19W1 | 07/17/2018 | 08/09/2018 | 3 | 0 | 3 | 08/10/2018 | 08/10/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 687069 | 02072 | 4980 | Solar | 05_09_702W3 | 06/03/2025 | 07/09/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 07/28/2025 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 707153 | 02368 | 12.92 | Solar | 05_07_94W43 | 07/29/2025 | 08/13/2025 | 10 | 5 | 5 | 08/14/2025 | 08/14/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  | 10/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | SAUGUS | 619530 | 01906 | 7.6 | Solar | 05_07_913W43 | 06/21/2024 | 07/02/2024 | 4 | 1 | 3 | 07/03/2024 | 07/03/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | ORANGE | 239710 | 01364 | 7.6 | Solar | 05_07_5W3 | 07/09/2019 | 07/30/2019 | 14 | 9 | 5 | 07/31/2019 | 07/31/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 | 07/09/2019 | 4/8/2021 | Y | EXP | 365 | 01/06/2021 | 01/21/2021 | 15 | 0 | 15 |  |  | 2/19/2021 | Connected |  | N
National Grid | EASTON | 205535 | 02356 | 7.6 | Solar | 05_12_19W1 | 06/17/2019 | 06/21/2019 | 3 | 0 | 3 | 06/24/2019 | 06/24/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 | 06/17/2019 | 6/17/2020 | Y | EXP | 365 | 09/17/2019 | 10/25/2019 | 38 | 0 | 38 |  |  | 3/20/2020 | Connected |  | N
National Grid | STOUGHTON | 555621 | 02072 | 12.5 | Solar | 05_09_704W1 | 07/03/2024 | 09/10/2024 | 46 | 39 | 7 | 09/11/2024 | 09/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2024 |  | 3/15/2026 | N | EXP | 500 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 719404 | 02368 | 10 | Solar | 05_07_94W43 | 09/16/2025 | 09/30/2025 | 4 | 0 | 4 | 10/08/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 625260 | 01906 | 4.18 | Solar | 05_07_913W43 | 07/16/2024 | 08/06/2024 | 12 | 9 | 3 | 08/07/2024 | 08/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/16/2024 | 8/30/2025 | Y | EXP | 365 | 04/08/2025 | 04/07/2025 | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | ATHOL | 267109 | 01331 | 7.6 | Solar | 05_07_5W3 | 11/25/2019 | 12/02/2019 | 4 | 4 | 0 | 12/03/2019 | 12/03/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2019 | 11/25/2019 | 11/25/2020 | Y | EXP | 365 | 02/07/2020 | 02/06/2020 | 0 | 0 | 0 |  |  | 3/10/2020 | Connected |  | N
National Grid | EASTON | 210103 | 02356 | 57.6 | Solar | 05_12_19W1 | 03/07/2019 | 03/12/2019 | 2 | 0 | 2 | 03/13/2019 | 03/13/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 |  | 1/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2020 | Connected |  | N
National Grid | STOUGHTON | 720120 | 02072 | 7.6 | Solar | 05_09_704W1 | 09/18/2025 | 10/03/2025 | 4 | 0 | 4 | 10/20/2025 | 10/20/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 09/18/2025 | 11/13/2026 | Y | EXP | 365 | 01/13/2026 |  | 79 | 0 | 79 |  |  |  | Construction |  | N
National Grid | RANDOLPH | 756795 | 02368 | 20 | Solar | 05_07_94W43 | 03/16/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 625803 | 01906 | 1.74 | Solar | 05_07_913W43 | 07/18/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 66 | 47 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATHOL | 278528 | 01331 | 3.8 | Solar | 05_07_5W3 | 03/19/2020 | 04/27/2020 | 25 | 25 | 0 | 04/28/2020 | 04/28/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 |  | 4/26/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 213005 | 02356 | 60 | Solar | 05_12_19W1 | 03/13/2019 | 03/18/2019 | 3 | 1 | 2 | 03/19/2019 | 03/19/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 |  | 1/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2020 | Connected |  | N
National Grid | STOUGHTON | 752652 | 02072 | 0 | Battery Add-On | 05_09_704W1 | 02/23/2026 | 03/03/2026 | 5 | 3 | 2 | 03/04/2026 | 03/04/2026 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 556459 | 02368 | 4990 | Solar | 05_07_94W44 | 01/30/2024 | 05/16/2024 | 74 | 64 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2024 | 06/03/2024 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SAUGUS | 630486 | 01906 | 3.8 | Solar | 05_07_913W43 | 08/06/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 08/06/2024 | 9/6/2025 | Y | EXP | 365 | 12/13/2024 | 12/12/2024 | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | ATHOL | 282704 | 01331 | 7.6 | Solar | 05_07_5W3 | 04/06/2020 | 04/08/2020 | 2 | 2 | 0 | 04/09/2020 | 04/09/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2020 | 04/06/2020 | 4/7/2021 | Y | EXP | 365 | 09/23/2020 | 10/08/2020 | 15 | 0 | 15 |  |  | 11/17/2020 | Connected |  | N
National Grid | BROCKTON | 384858 | 02301 | 5 | Solar | 05_12_19W1 | 10/26/2021 | 12/21/2021 | 11 | 6 | 5 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 174799 | 02072 | 15 | Solar | 05_09_704W1 | 08/29/2012 | 08/29/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2012 |  | 11/16/2012 | N | EXP | 17 |  |  | 0 | 0 | 0 | 12/3/2012 | 12/3/2012 | 1/15/2013 | Connected |  | N
National Grid | RANDOLPH | 736836 | 02368 | 11.5 | Solar | 05_07_94W44 | 11/27/2025 | 02/05/2026 | 3 | 0 | 3 | 02/06/2026 | 02/06/2026 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SAUGUS | 637012 | 01906 | 0 | Battery Add-On | 05_07_913W43 | 09/03/2024 | 09/18/2024 | 11 | 9 | 2 | 09/19/2024 | 09/19/2024 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2024 |  | 11/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2024 | Connected |  | N
National Grid | ATHOL | 282699 | 01331 | 7.6 | Solar | 05_07_5W3 | 04/28/2020 | 04/30/2020 | 2 | 2 | 0 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 | 04/28/2020 | 4/29/2021 | Y | EXP | 365 | 07/29/2020 | 09/15/2020 | 49 | 5 | 44 |  |  | 9/17/2020 | Connected |  | N
National Grid | EASTON | 404787 | 02356 | 9.8 | Solar | 05_12_19W1 | 02/03/2022 | 02/07/2022 | 2 | 0 | 2 | 02/08/2022 | 02/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 175085 | 02072 | 12.2 | Solar | 05_09_704W1 | 08/14/2012 | 08/14/2012 | 5 | 0 | 5 | 08/22/2012 | 08/22/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 10/24/2012 | 10/24/2012 | 12/28/2012 | Connected |  | N
National Grid | RANDOLPH | 741096 | 02368 | 10 | Solar | 05_07_94W44 | 12/18/2025 | 12/19/2025 | 1 | 0 | 1 | 12/22/2025 | 12/22/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/29/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 655783 | 01906 | 5.76 | Solar | 05_07_913W43 | 11/20/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | SHUTESBURY | 297377 | 01072 | 7.6 | Solar | 05_07_5W3 | 07/15/2020 | 07/22/2020 | 4 | 0 | 4 | 07/23/2020 | 07/23/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 07/15/2020 | 5/28/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2021 | Connected |  | N
National Grid | EASTON | 409848 | 02356 | 8.376 | Solar | 05_12_19W1 | 02/01/2022 | 02/23/2022 | 16 | 15 | 1 | 02/24/2022 | 02/24/2022 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 | 02/01/2022 | 6/27/2023 | Y | EXP | 365 | 04/28/2022 | 06/15/2022 | 49 | 0 | 49 |  |  | 8/24/2022 | Connected |  | N
National Grid | STOUGHTON | 175122 | 02072 | 3000 | Solar | 05_09_704W1 | 08/17/2012 | 08/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2012 | 11/26/2012 | 44 | 0 | 44 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 174720 | 02368 | 500 | Solar | 05_07_94W44 | 01/14/2014 | 01/14/2014 | 6 | 0 | 6 | 01/24/2014 | 01/24/2014 | 43 | 7 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2014 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 656137 | 01906 | 4.94 | Solar | 05_07_913W43 | 11/22/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2025 | Connected |  | N
National Grid | SHUTESBURY | 308462 | 01072 | 6 | Solar | 05_07_5W3 | 09/24/2020 | 09/28/2020 | 1 | 0 | 1 | 09/29/2020 | 09/29/2020 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2021 | Connected |  | N
National Grid | EASTON | 445004 | 02356 | 10 | Solar | 05_12_19W1 | 07/25/2022 | 08/15/2022 | 15 | 15 | 0 | 08/16/2022 | 08/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 | 07/25/2022 | 9/29/2023 | Y | EXP | 365 | 03/23/2023 | 04/21/2023 | 30 | 0 | 30 |  |  | 5/1/2023 | Connected |  | N
National Grid | STOUGHTON | 175121 | 02072 | 3000 | Solar | 05_09_704W1 | 08/17/2012 | 08/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2012 | 12/03/2012 | 49 | 0 | 49 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 175242 | 02368 | 75 | Solar | 05_07_94W44 | 08/25/2014 | 08/25/2014 | 5 | 0 | 5 | 09/03/2014 | 09/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 12/31/2014 | N | EXP | 104 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 11/17/2014 | Connected |  | N
National Grid | SAUGUS | 657653 | 01906 | 5.76 | Solar | 05_07_913W43 | 11/29/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | SHUTESBURY | 307716 | 01072 | 3.8 | Solar | 05_07_5W3 | 10/02/2020 | 10/20/2020 | 10 | 7 | 3 | 10/21/2020 | 10/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2020 | 10/02/2020 | 10/20/2021 | Y | EXP | 365 | 04/17/2021 | 06/10/2021 | 54 | 0 | 54 |  |  | 7/29/2021 | Connected |  | N
National Grid | STOUGHTON | 469141 | 02072 | 10 | Solar | 05_12_19W1 | 10/20/2022 | 10/25/2022 | 3 | 0 | 3 | 10/26/2022 | 10/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 | 10/20/2022 | 4/11/2024 | Y | EXP | 365 | 04/11/2023 | 04/10/2023 | 0 | 0 | 0 |  |  | 4/25/2023 | Connected |  | N
National Grid | STOUGHTON | 176019 | 02072 | 4500 | Solar | 05_09_704W1 | 03/20/2015 | 03/20/2015 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/15/2015 | 05/13/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2016 |  | 4/1/2019 | N | STD | 1132 | 08/04/2018 | 10/18/2018 | 75 | 0 | 75 |  |  | 3/27/2019 | Connected |  | N
National Grid | RANDOLPH | 175691 | 02368 | 880 | Solar | 05_07_94W44 | 05/28/2014 | 05/28/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/05/2014 | 07/08/2014 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2015 |  | 12/31/2016 | N | STD | 681 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 658168 | 01906 | 10 | Solar | 05_07_913W43 | 12/03/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHUTESBURY | 327921 | 01072 | 9.8 | Solar | 05_07_5W3 | 12/09/2020 | 12/18/2020 | 6 | 0 | 6 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/09/2020 | 2/8/2022 | Y | EXP | 365 | 09/29/2021 | 10/22/2021 | 24 | 0 | 24 |  |  | 2/4/2022 | Connected |  | N
National Grid | STOUGHTON | 490857 | 02072 | 6 | Solar | 05_12_19W1 | 01/19/2023 | 01/20/2023 | 1 | 0 | 1 | 01/23/2023 | 01/23/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 177556 | 02072 | 10 | Solar | 05_09_704W1 | 05/16/2017 | 05/16/2017 | 6 | 6 | 0 | 05/25/2017 | 05/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2017 | 05/16/2017 | 5/22/2018 | Y | EXP | 361 | 07/18/2017 | 07/26/2017 | 6 | 0 | 6 | 12/13/2017 | 12/13/2017 | 12/13/2017 | Connected |  | N
National Grid | RANDOLPH | 273969 | 02368 | 7.6 | Solar | 05_07_94W44 | 02/26/2020 | 02/26/2020 | 0 | 0 | 0 | 02/27/2020 | 02/27/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2020 |  | 2/26/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 675761 | 01905 | 5.76 | Solar | 05_07_913W43 | 03/05/2025 | 03/18/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHUTESBURY | 352832 | 01072 | 5.76 | Solar | 05_07_5W3 | 06/18/2021 | 06/25/2021 | 5 | 0 | 5 | 06/28/2021 | 06/28/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 502819 | 02072 | 3.8 | Solar | 05_12_19W1 | 02/23/2023 | 02/27/2023 | 2 | 0 | 2 | 02/28/2023 | 02/28/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 184600 | 02072 | 4998 | Solar | 05_09_704W1 | 09/13/2018 | 10/12/2018 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2018 | 12/18/2018 | 44 | 25 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 298308 | 02368 | 96 | Solar | 05_07_94W44 | 06/25/2020 | 07/06/2020 | 7 | 4 | 3 | 07/07/2020 | 07/07/2020 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2020 | 06/25/2020 | 4/26/2022 | Y | EXP | 365 | 03/11/2021 | 04/21/2021 | 41 | 0 | 41 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 680634 | 01905 | 5.76 | Solar | 05_07_913W43 | 03/26/2025 | 04/29/2025 | 23 | 18 | 5 | 04/30/2025 | 04/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2025 | Connected |  | N
National Grid | SHUTESBURY | 449261 | 01072 | 6 | Solar | 05_07_5W3 | 08/11/2022 | 08/15/2022 | 3 | 1 | 2 | 08/16/2022 | 08/16/2022 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2022 | 08/11/2022 | 11/3/2024 | Y | EXP | 365 | 08/11/2023 | 10/06/2023 | 57 | 0 | 57 |  |  | 11/9/2023 | Connected |  | N
National Grid | STOUGHTON | 510472 | 02072 | 6 | Solar | 05_12_19W1 | 04/06/2023 | 04/10/2023 | 2 | 0 | 2 | 04/11/2023 | 04/11/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 184599 | 02072 | 4998 | Solar | 05_09_704W1 | 09/13/2018 | 10/18/2018 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 | 12/18/2018 | 40 | 21 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 404516 | 02368 | 16.08 | Solar | 05_07_94W44 | 01/03/2022 | 01/07/2022 | 4 | 2 | 2 | 01/10/2022 | 01/10/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 681967 | 01905 | 5 | Solar | 05_07_913W43 | 04/01/2025 | 04/22/2025 | 4 | 0 | 4 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | SHUTESBURY | 404526 | 01072 | 10 | Solar | 05_07_5W3 | 01/26/2022 | 02/18/2022 | 17 | 16 | 1 | 02/22/2022 | 02/22/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 01/26/2022 | 6/30/2023 | Y | EXP | 365 | 06/16/2022 | 06/28/2022 | 13 | 0 | 13 |  |  | 7/6/2022 | Connected |  | N
National Grid | STOUGHTON | 519497 | 02072 | 10 | Solar | 05_12_19W1 | 04/26/2023 | 05/09/2023 | 10 | 6 | 4 | 05/10/2023 | 05/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2023 | 04/26/2023 | 8/25/2024 | Y | EXP | 365 | 01/12/2024 | 03/04/2024 | 53 | 0 | 53 |  |  | 3/8/2024 | Connected |  | N
National Grid | STOUGHTON | 184598 | 02072 | 2998 | Solar | 05_09_704W1 | 09/13/2018 | 10/13/2018 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2018 | 12/19/2018 | 45 | 26 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 437242 | 02368 | 6 | Solar | 05_07_94W44 | 06/24/2022 | 06/28/2022 | 2 | 0 | 2 | 06/29/2022 | 06/29/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 9/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 683413 | 01905 | 15.2 | Solar | 05_07_913W43 | 04/09/2025 | 04/14/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHUTESBURY | 424661 | 01072 | 11.4 | Solar | 05_07_5W3 | 04/21/2022 | 05/20/2022 | 4 | 1 | 3 | 05/23/2022 | 05/23/2022 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2022 | 04/21/2022 | 8/16/2024 | Y | EXP | 365 | 06/09/2023 | 08/11/2023 | 64 | 0 | 64 |  |  | 9/5/2023 | Connected |  | N
National Grid | STOUGHTON | 526047 | 02072 | 7.6 | Solar | 05_12_19W1 | 05/12/2023 | 05/15/2023 | 1 | 0 | 1 | 05/16/2023 | 05/16/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  | 11/8/2024 | N | EXP | 470 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 184597 | 02072 | 4998 | Solar | 05_09_704W1 | 09/13/2018 | 10/12/2018 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2018 | 12/19/2018 | 64 | 45 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 465450 | 02368 | 3.8 | Solar | 05_07_94W44 | 10/03/2022 | 10/04/2022 | 1 | 0 | 1 | 10/05/2022 | 10/05/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2023 | Connected |  | N
National Grid | LYNN | 691658 | 01905 | 10 | Solar | 05_07_913W43 | 05/26/2025 | 06/27/2025 | 2 | 0 | 2 | 07/14/2025 | 07/14/2025 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 | 05/26/2025 | 9/9/2026 | Y | EXP | 365 | 11/26/2025 | 01/08/2026 | 44 | 0 | 44 |  |  | 1/12/2026 | Connected |  | N
National Grid | SHUTESBURY | 427346 | 01072 | 6 | Solar | 05_07_5W3 | 05/02/2022 | 05/17/2022 | 1 | 0 | 1 | 05/18/2022 | 05/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 559420 | 02072 | 3.8 | Solar | 05_12_19W1 | 10/13/2023 | 10/16/2023 | 1 | 0 | 1 | 10/17/2023 | 10/17/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 300938 | 02072 | 4998 | Solar | 05_09_704W1 | 10/29/2020 | 11/06/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 01/05/2021 | 36 | 20 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 514367 | 02368 | 19.968 | Solar | 05_07_94W44 | 03/24/2023 | 03/31/2023 | 6 | 5 | 1 | 04/03/2023 | 04/03/2023 | 308 | 55 | 253 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 709025 | 01905 | 10 | Solar | 05_07_913W43 | 08/01/2025 | 09/15/2025 | 29 | 24 | 5 | 09/16/2025 | 09/16/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHUTESBURY | 434012 | 01072 | 0 | Battery Add-On | 05_07_5W3 | 07/28/2022 | 08/11/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2022 | 09/09/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 537934 | 02072 | 3.8 | Solar | 05_12_19W1 | 07/06/2023 | 07/07/2023 | 1 | 0 | 1 | 07/10/2023 | 07/10/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 300932 | 02072 | 2000 | Solar | 05_09_704W1 | 10/29/2020 | 11/18/2020 | 13 | 7 | 6 |  |  | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 560318 | 02368 | 7.6 | Solar | 05_07_94W44 | 10/09/2023 | 10/12/2023 | 3 | 0 | 3 | 10/13/2023 | 10/13/2023 | 23 | 6 | 17 | 11/22/2023 | 02/23/2024 | 63 | 3 | 60 |  |  | 0 | 0 | 0 | 02/23/2024 | 63 | 3 | 60 |  |  | 0 | 0 | 0 | 3/19/2024 |  | 4/28/2025 | N | EXP | 365 | 04/26/2024 | 05/14/2024 | 19 | 0 | 19 |  |  | 7/11/2024 | Connected |  | N
National Grid | SAUGUS | 722755 | 01906 | 3.8 | Solar | 05_07_913W43 | 09/30/2025 | 10/07/2025 | 5 | 1 | 4 | 10/08/2025 | 10/08/2025 | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2026 | Connected |  | N
National Grid | SHUTESBURY | 456432 | 01072 | 7.6 | Solar | 05_07_5W3 | 09/16/2022 | 09/20/2022 | 2 | 0 | 2 | 09/21/2022 | 09/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 12/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2023 | Connected |  | N
National Grid | STOUGHTON | 575819 | 02072 | 6 | Solar | 05_12_19W1 | 12/11/2023 | 12/12/2023 | 2 | 1 | 1 | 12/13/2023 | 12/13/2023 | 46 | 21 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 | 12/11/2023 | 2/28/2025 | Y | EXP | 365 | 08/22/2024 | 10/23/2024 | 63 | 0 | 63 |  |  | 11/1/2024 | Connected |  | N
National Grid | STOUGHTON | 382341 | 02072 | 10 | Solar | 05_09_704W1 | 10/04/2021 | 01/04/2022 | 5 | 3 | 2 | 10/12/2021 | 10/12/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2021 |  | 12/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2022 | Connected |  | Y
National Grid | RANDOLPH | 550589 | 02368 | 17.98 | Solar | 05_07_94W44 | 03/07/2024 | 03/15/2024 | 7 | 5 | 2 | 03/18/2024 | 03/18/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 03/07/2024 | 5/22/2025 | Y | EXP | 365 | 06/14/2024 | 08/29/2024 | 77 | 0 | 77 |  |  | 7/29/2024 | Connected |  | N
National Grid | SAUGUS | 740976 | 01906 | 6.46 | Solar | 05_07_913W43 | 12/17/2025 | 12/23/2025 | 1 | 0 | 1 | 01/12/2026 | 01/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2026 | Connected |  | N
National Grid | SHUTESBURY | 479096 | 01002 | 6 | Solar | 05_07_5W3 | 01/16/2023 | 01/17/2023 | 1 | 0 | 1 | 01/18/2023 | 01/18/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 3/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2023 | Connected |  | N
National Grid | STOUGHTON | 575591 | 02072 | 3.8 | Solar | 05_12_19W1 | 12/13/2023 | 12/14/2023 | 2 | 1 | 1 | 12/15/2023 | 12/15/2023 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 460940 | 02072 | 5.22 | Solar | 05_09_704W1 | 10/13/2022 | 10/17/2022 | 2 | 0 | 2 | 10/18/2022 | 10/18/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2022 |  | 11/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2023 | Connected |  | Y
National Grid | RANDOLPH | 600322 | 02368 | 13.6 | Solar | 05_07_94W44 | 03/29/2024 | 04/17/2024 | 12 | 11 | 1 | 04/18/2024 | 04/18/2024 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 5/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | LYNN | 668229 | 01905 | 10 | Solar | 05_01_304W1 | 01/28/2025 | 03/08/2025 | 22 | 18 | 4 | 03/10/2025 | 03/10/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SHUTESBURY | 509035 | 01002 | 10 | Solar | 05_07_5W3 | 05/02/2023 | 05/11/2023 | 7 | 5 | 2 | 05/12/2023 | 05/12/2023 | 50 | 27 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 | 05/02/2023 | 6/23/2025 | Y | EXP | 365 | 12/02/2023 | 12/02/2023 | 1 | 0 | 1 |  |  | 8/24/2024 | Connected |  | N
National Grid | STOUGHTON | 597865 | 02072 | 10 | Solar | 05_12_19W1 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 |  | 4/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/24/2024 | Connected |  | N
National Grid | STOUGHTON | 477733 | 02072 | 0 | Solar | 05_09_704W1 | 11/15/2022 | 11/21/2022 | 4 | 2 | 2 | 11/22/2022 | 11/22/2022 | 24 | 12 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  | 1/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2023 | Connected |  | N
National Grid | RANDOLPH | 673244 | 02368 | 7.6 | Solar | 05_07_94W44 | 02/20/2025 | 02/27/2025 | 6 | 3 | 3 | 02/28/2025 | 02/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | LYNN | 718080 | 01905 | 5.76 | Solar | 05_01_304W1 | 09/10/2025 | 09/17/2025 | 4 | 2 | 2 | 09/18/2025 | 09/18/2025 | 117 | 104 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SHUTESBURY | 522183 | 01072 | 6 | Solar | 05_07_5W3 | 05/03/2023 | 05/04/2023 | 1 | 0 | 1 | 05/05/2023 | 05/05/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 6/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | STOUGHTON | 598390 | 02072 | 5 | Solar | 05_12_19W1 | 03/28/2024 | 04/01/2024 | 2 | 0 | 2 | 04/02/2024 | 04/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 | 03/28/2024 | 5/16/2025 | Y | EXP | 365 | 09/24/2024 | 12/19/2024 | 87 | 0 | 87 |  |  | 1/9/2025 | Connected |  | Y
National Grid | STOUGHTON | 491819 | 02072 | 10 | Solar | 05_09_704W1 | 02/06/2023 | 02/08/2023 | 3 | 2 | 1 | 02/09/2023 | 02/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2023 | 02/06/2023 | 8/1/2024 | Y | EXP | 365 | 06/07/2023 | 08/28/2023 | 83 | 0 | 83 |  |  | 9/6/2023 | Connected |  | N
National Grid | RANDOLPH | 703314 | 02368 | 7.6 | Solar | 05_07_94W44 | 07/07/2025 | 08/06/2025 | 2 | 0 | 2 | 08/07/2025 | 08/07/2025 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 | 07/07/2025 | 9/30/2026 | Y | EXP | 365 | 12/23/2025 | 01/07/2026 | 16 | 0 | 16 |  |  | 1/13/2026 | Connected |  | N
National Grid | LYNN | 726510 | 01905 | 10 | Solar | 05_01_304W1 | 10/14/2025 | 11/20/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 | 10/14/2025 | 1/13/2027 | Y | EXP | 365 | 03/25/2026 |  | 8 | 0 | 8 |  |  |  | Construction |  | N
National Grid | SHUTESBURY | 528175 | 01072 | 7.6 | Solar | 05_07_5W3 | 05/30/2023 | 06/01/2023 | 2 | 0 | 2 | 06/02/2023 | 06/02/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 599191 | 02072 | 10 | Solar | 05_12_19W1 | 04/18/2024 | 04/24/2024 | 4 | 0 | 4 | 04/25/2024 | 04/25/2024 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 582306 | 02072 | 10 | Solar | 05_09_704W1 | 01/22/2024 | 01/25/2024 | 3 | 0 | 3 | 01/26/2024 | 01/26/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 01/22/2024 | 3/9/2025 | Y | EXP | 365 | 09/20/2024 | 10/22/2024 | 33 | 0 | 33 |  |  | 11/12/2024 | Connected |  | N
National Grid | RANDOLPH | 413057 | 02368 | 51.9 | Solar | 05_07_95W1 | 05/02/2022 | 06/08/2022 | 26 | 19 | 7 |  |  | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/10/2027 | N | STD | 448 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SAUGUS | 738884 | 01906 | 5.76 | Solar | 05_01_304W1 | 12/09/2025 | 01/02/2026 | 2 | 0 | 2 | 01/23/2026 | 01/23/2026 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SHUTESBURY | 531563 | 01072 | 100 | Solar | 05_07_5W3 | 06/08/2023 | 09/21/2023 | 72 | 62 | 10 | 09/22/2023 | 09/22/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 600347 | 02072 | 7.6 | Solar | 05_12_19W1 | 04/12/2024 | 04/16/2024 | 1 | 0 | 1 | 04/17/2024 | 04/17/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 04/12/2024 | 5/7/2025 | Y | EXP | 365 | 08/20/2024 | 09/24/2024 | 36 | 0 | 36 |  |  | 10/4/2024 | Connected |  | N
National Grid | STOUGHTON | 593171 | 02072 | 0 | Solar | 05_09_704W1 | 02/28/2024 | 03/15/2024 | 12 | 9 | 3 | 03/18/2024 | 03/18/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 4/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2024 | Connected |  | N
National Grid | RANDOLPH | 468958 | 02368 | 250 | Solar | 05_07_95W1 | 11/04/2022 | 11/16/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 12/14/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/10/2027 | N | STD | 448 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LYNN | 744806 | 01905 | 15.2 | Solar | 05_01_304W1 | 01/13/2026 | 01/20/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | SHUTESBURY | 536421 | 01072 | 3.8 | Solar | 05_07_5W3 | 07/10/2023 | 07/11/2023 | 1 | 0 | 1 | 07/12/2023 | 07/12/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 |  | 8/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 608718 | 02072 | 5.76 | Solar | 05_12_19W1 | 05/03/2024 | 05/09/2024 | 0 | 0 | 0 | 05/10/2024 | 05/10/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2024 | 05/03/2024 | 12/28/2025 | Y | EXP | 365 | 09/25/2024 | 11/28/2024 | 65 | 0 | 65 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 658352 | 01519 | 15.2 | Solar | 05_09_704W1 | 12/04/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2025 | Connected |  | N
National Grid | RANDOLPH | 716283 | 02368 | 240 | Solar | 05_07_95W1 | 09/23/2025 | 01/12/2026 | 74 | 55 | 19 |  |  | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SAUGUS | 174133 | 01906 | 24.94 | Solar | 05_01_304W1 | 05/03/2012 | 05/03/2012 | 17 | 0 | 17 | 05/31/2012 | 05/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2012 |  | 8/10/2012 | N | EXP | 54 |  |  | 0 | 0 | 0 | 12/26/2013 | 12/26/2013 | 12/26/2013 | Connected |  | N
National Grid | AMHERST | 542276 | 01072 | 9.57 | Solar | 05_07_5W3 | 07/25/2023 | 08/01/2023 | 5 | 4 | 1 | 08/02/2023 | 08/02/2023 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2023 | 07/25/2023 | 8/27/2024 | Y | EXP | 365 | 10/21/2023 | 10/23/2023 | 3 | 0 | 3 |  |  | 10/27/2023 | Connected |  | N
National Grid | STOUGHTON | 614387 | 02072 | 6 | Solar | 05_12_19W1 | 05/31/2024 | 06/27/2024 | 4 | 3 | 1 | 06/28/2024 | 06/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 05/31/2024 | 1/19/2026 | Y | EXP | 365 | 08/22/2024 | 10/31/2024 | 71 | 0 | 71 |  |  | 5/9/2025 | Connected |  | N
National Grid | GRAFTON | 658943 | 01560 | 7.6 | Solar | 05_09_704W1 | 12/18/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 12/18/2024 | 2/11/2026 | Y | EXP | 365 | 06/14/2025 | 07/25/2025 | 42 | 0 | 42 |  |  | 7/30/2025 | Connected |  | N
National Grid | RANDOLPH | 750713 | 02368 | 7.6 | Solar | 05_07_95W1 | 02/11/2026 | 02/13/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SAUGUS | 174945 | 01906 | 45 | Solar | 05_01_304W1 | 09/21/2012 | 09/21/2012 | 9 | 0 | 9 | 10/04/2012 | 10/04/2012 | 0 | 0 | 0 | 03/28/2013 | 04/30/2013 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 04/30/2013 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 5/6/2013 |  | 2/1/2013 | N | EXP | 94 |  |  | 0 | 0 | 0 | 5/23/2013 | 5/23/2013 | 10/30/2013 | Connected |  | N
National Grid | SHUTESBURY | 545250 | 01072 | 7.6 | Solar | 05_07_5W3 | 08/02/2023 | 08/07/2023 | 3 | 0 | 3 | 08/08/2023 | 08/08/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 | 08/02/2023 | 9/10/2024 | Y | EXP | 365 | 05/02/2024 | 06/18/2024 | 48 | 0 | 48 |  |  | 6/26/2024 | Connected |  | N
National Grid | STOUGHTON | 619336 | 02072 | 7.6 | Solar | 05_12_19W1 | 06/21/2024 | 07/22/2024 | 4 | 2 | 2 | 07/23/2024 | 07/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 672987 | 01527 | 40 | Solar | 05_09_704W1 | 03/13/2025 | 07/03/2025 | 77 | 66 | 11 | 07/07/2025 | 07/07/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | Y
National Grid | RANDOLPH | 174195 | 02368 | 250 | Wind | 05_07_95W1 | 03/17/2011 | 03/17/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2012 | 03/17/2011 | 2/28/2020 | Y | STD | 2852 | 07/24/2012 | 10/19/2012 | 61 | 0 | 61 | 12/16/2015 | 12/16/2015 |  | Withdrawn |  | Y
National Grid | SAUGUS | 175007 | 01906 | 2700 | Solar | 05_01_304W1 | 09/18/2013 | 09/18/2013 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2013 | 10/23/2013 | 14 | 1 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2014 | 09/18/2013 | 5/14/2016 | Y | STD | 740 | 03/18/2016 | 12/20/2016 | 189 | 0 | 189 |  |  | 10/28/2016 | Connected |  | N
National Grid | SHUTESBURY | 566616 | 01072 | 0 | Solar | 05_07_5W3 | 10/26/2023 | 10/27/2023 | 1 | 0 | 1 | 08/12/2024 | 08/12/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2024 | Connected |  | N
National Grid | HANOVER | 630093 | 02339 | 5 | Solar | 05_12_19W1 | 08/13/2024 | 08/19/2024 | 4 | 0 | 4 | 08/20/2024 | 08/20/2024 | 81 | 58 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 692291 | 01519 | 10 | Solar | 05_09_704W1 | 06/06/2025 | 06/18/2025 | 10 | 5 | 5 | 09/17/2025 | 09/17/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  | 10/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | RANDOLPH | 175036 | 02368 | 85 | Solar | 05_07_95W1 | 09/13/2013 | 09/13/2013 | 8 | 0 | 8 | 09/26/2013 | 09/26/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2013 |  | 10/31/2014 | N | EXP | 353 |  |  | 0 | 0 | 0 | 12/1/2014 | 12/1/2014 | 12/19/2014 | Connected |  | N
National Grid | SAUGUS | 175206 | 01906 | 2000 | Solar | 05_01_304W1 | 12/04/2012 | 12/04/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2012 | 01/15/2013 | 19 | 0 | 19 |  | 0 | 0 | 0 | 01/15/2013 | 01/15/2013 | 0 | 0 | 0 | 8/9/2013 | 12/04/2012 | 12/31/2014 | Y | STD | 509 | 08/11/2014 | 03/29/2016 | 404 | 0 | 404 | 3/15/2015 | 3/15/2015 | 3/16/2015 | Connected |  | N
National Grid | SHUTESBURY | 561990 | 01072 | 10 | Solar | 05_07_5W3 | 11/01/2023 | 11/02/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 | 11/01/2023 | 6/20/2025 | Y | EXP | 465 | 03/14/2024 | 03/16/2024 | 3 | 0 | 3 |  |  | 7/18/2025 | Connected |  | N
National Grid | HANOVER | 632559 | 02339 | 5.76 | Solar | 05_12_19W1 | 08/14/2024 | 09/10/2024 | 4 | 0 | 4 | 09/11/2024 | 09/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 08/14/2024 | 10/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | GRAFTON | 724423 | 01519 | 6.08 | Solar | 05_09_704W1 | 10/13/2025 | 10/14/2025 | 1 | 0 | 1 | 10/15/2025 | 10/15/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2026 | Connected |  | N
National Grid | RANDOLPH | 175318 | 02368 | 440.8 | Solar | 05_07_95W1 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 1/5/2015 | 1/5/2015 | 12/31/2014 | Connected |  | N
National Grid | SAUGUS | 175625 | 01906 | 672 | Solar | 05_01_304W1 | 05/05/2014 | 05/05/2014 | 7 | 4 | 3 |  |  | 0 | 0 | 0 | 06/13/2014 | 06/13/2014 | 0 | 0 | 0 | 05/15/2014 | 09/12/2014 | 82 | 12 | 70 | 06/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 | 05/05/2014 | 12/1/2016 | Y | STD | 419 | 04/19/2016 | 12/21/2016 | 169 | 0 | 169 | 12/9/2016 | 12/9/2016 | 12/21/2016 | Connected |  | N
National Grid | SHUTESBURY | 574106 | 01072 | 4.35 | Solar | 05_07_5W3 | 12/13/2023 | 12/19/2023 | 4 | 1 | 3 | 12/20/2023 | 12/20/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 645102 | 02339 | 3.8 | Solar | 05_12_19W1 | 10/04/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | GRAFTON | 177766 | 01519 | 2790 | Solar | 05_09_705W1 | 10/05/2017 | 10/24/2017 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2017 | 11/15/2017 | 10 | 0 | 10 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RANDOLPH | 177450 | 02368 | 84 | Solar | 05_07_95W1 | 09/20/2016 | 09/20/2016 | 4 | 4 | 0 | 09/26/2016 | 09/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2016 | 09/20/2016 | 9/25/2017 | Y | EXP | 364 |  |  | 0 | 0 | 0 | 5/9/2017 | 5/9/2017 | 5/11/2017 | Connected |  | N
National Grid | LYNN | 175713 | 01905 | 5 | Solar | 05_01_304W1 | 10/27/2014 | 10/27/2014 | 6 | 1 | 5 | 11/05/2014 | 11/05/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 |  | 1/28/2015 | N | EXP | 64 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 8/7/2015 | Connected |  | N
National Grid | SHUTESBURY | 583670 | 01072 | 7.6 | Solar | 05_07_5W3 | 02/09/2024 | 02/12/2024 | 1 | 0 | 1 | 02/13/2024 | 02/13/2024 | 18 | 11 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 |  | 3/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 646486 | 02339 | 5 | Solar | 05_12_19W1 | 10/11/2024 |  | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 436398 | 01519 | 3373 | Other | 05_09_705W1 | 10/31/2022 | 04/17/2023 | 113 | 107 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2023 | 07/12/2023 | 59 | 40 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | RANDOLPH | 185230 | 02368 | 500 | Solar | 05_07_95W1 | 07/30/2018 | 09/24/2018 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/25/2018 | 10/22/2018 | 40 | 0 | 40 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 175982 | 01906 | 990 | Solar | 05_01_304W1 | 01/23/2015 | 01/23/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/03/2015 | 03/05/2015 | 21 | 0 | 21 |  | 0 | 0 | 0 | 09/16/2015 | 10/02/2015 | 12 | 0 | 12 | 12/8/2015 | 01/23/2015 | 6/30/2015 | Y | STD | 161 | 09/21/2017 | 11/27/2017 | 39 | 0 | 39 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | SHUTESBURY | 587703 | 01072 | 8.7 | Solar | 05_07_5W3 | 02/08/2024 | 02/16/2024 | 7 | 5 | 2 | 02/20/2024 | 02/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 02/08/2024 | 3/27/2025 | Y | EXP | 365 | 05/09/2024 | 06/27/2024 | 50 | 0 | 50 |  |  | 6/29/2024 | Connected |  | N
National Grid | HANOVER | 651448 | 02339 | 3.8 | Solar | 05_12_19W1 | 11/12/2024 | 12/10/2024 | 4 | 0 | 4 | 12/11/2024 | 12/11/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | GRAFTON | 174661 | 01519 | 1000 | Solar | 05_09_705W1 | 12/11/2012 | 12/26/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2012 | 03/20/2013 | 49 | 0 | 49 |  | 0 | 0 | 0 | 02/06/2015 | 05/10/2018 | 176 | 0 | 176 | 2/6/2015 | 12/11/2012 | 12/31/2018 | Y | STD | 1424 | 11/15/2018 | 12/17/2018 | 32 | 0 | 32 |  |  | 12/28/2018 | Connected |  | N
National Grid | RANDOLPH | 246486 | 02368 | 18.56 | Solar | 05_07_95W1 | 08/07/2019 | 08/08/2019 | 0 | 0 | 0 | 08/09/2019 | 08/09/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 10/25/2019 | N | EXP | 66 |  |  | 0 | 0 | 0 |  |  | 10/14/2019 | Connected |  | N
National Grid | LYNN | 176017 | 01905 | 21.4 | Solar | 05_01_304W1 | 01/26/2015 | 01/26/2015 | 4 | 0 | 4 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2015 |  | 5/31/2015 | N | EXP | 114 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 12/11/2015 | Connected |  | N
National Grid | SHUTESBURY | 599536 | 01072 | 6 | Solar | 05_07_5W3 | 03/26/2024 | 03/27/2024 | 1 | 0 | 1 | 03/28/2024 | 03/28/2024 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 | 03/26/2024 | 7/6/2025 | Y | EXP | 365 | 07/25/2024 | 10/01/2024 | 69 | 0 | 69 |  |  | 12/11/2024 | Connected |  | N
National Grid | HANOVER | 651708 | 02339 | 22.8 | Solar | 05_12_19W1 | 11/03/2024 |  | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 175185 | 01519 | 650 | Natural Gas | 05_09_705W1 | 05/10/2013 | 05/23/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2013 | 07/09/2013 | 30 | 0 | 30 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2013 |  | 6/30/2019 | N | STD | 2029 |  |  | 0 | 0 | 0 |  |  | 5/17/2019 | Connected |  | N
National Grid | RANDOLPH | 268394 | 02368 | 11.4 | Solar | 05_07_95W1 | 12/05/2019 | 12/05/2019 | 0 | 0 | 0 | 12/06/2019 | 12/06/2019 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2020 | 12/05/2019 | 12/5/2020 | Y | EXP | 365 | 04/14/2020 | 05/20/2020 | 36 | 0 | 36 |  |  | 8/11/2020 | Connected |  | N
National Grid | LYNN | 176102 | 01905 | 6.45 | Solar | 05_01_304W1 | 06/19/2015 | 06/19/2015 | 5 | 5 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/28/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 11/13/2015 | Connected |  | N
National Grid | SHUTESBURY | 602927 | 01072 | 7.6 | Solar | 05_07_5W3 | 04/15/2024 | 04/17/2024 | 2 | 0 | 2 | 04/18/2024 | 04/18/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 654963 | 02339 | 22.8 | Solar | 05_12_19W1 | 11/22/2024 | 11/27/2024 | 3 | 2 | 1 | 12/02/2024 | 12/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/22/2024 | 3/13/2026 | Y | EXP | 365 | 07/02/2025 | 11/03/2025 | 125 | 0 | 125 |  |  | 7/9/2025 | Connected |  | N
National Grid | GRAFTON | 175602 | 01519 | 5600 | Natural Gas | 05_09_705W1 | 10/17/2014 | 10/17/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2014 | 11/06/2014 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2015 | 10/17/2014 | 12/31/2016 | Y | STD | 695 | 06/09/2015 | 11/17/2015 | 110 | 0 | 110 | 11/11/2015 | 11/11/2015 | 11/30/2015 | Connected |  | N
National Grid | RANDOLPH | 412226 | 02368 | 0 | Battery Add-On | 05_07_95W1 | 07/27/2022 | 08/10/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/08/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 176508 | 01906 | 5 | Solar | 05_01_304W1 | 03/24/2016 | 03/24/2016 | 3 | 3 | 0 | 03/30/2016 | 03/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 |  | 3/30/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 | 10/5/2016 | 10/5/2016 | 10/11/2016 | Connected |  | N
National Grid | WENDELL | 606501 | 01379 | 5.76 | Solar | 05_07_5W3 | 04/24/2024 | 06/05/2024 | 28 | 23 | 5 | 06/06/2024 | 06/06/2024 | 37 | 24 | 13 | 08/16/2024 | 10/25/2024 | 49 | 5 | 44 |  |  | 0 | 0 | 0 | 10/25/2024 | 49 | 5 | 44 |  |  | 0 | 0 | 0 | 11/12/2024 | 04/24/2024 | 1/23/2026 | Y | EXP | 365 | 04/30/2025 | 10/23/2025 | 177 | 0 | 177 |  |  | 11/26/2025 | Connected |  | N
National Grid | HANOVER | 658152 | 02339 | 10 | Solar | 05_12_19W1 | 12/05/2024 | 12/30/2024 | 8 | 3 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 175689 | 01527 | 480 | Solar | 05_09_705W1 | 05/22/2014 | 05/22/2014 | 6 | 0 | 6 | 06/03/2014 | 06/03/2014 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 520180 | 02368 | 0 | Solar | 05_07_95W1 | 04/19/2023 | 04/24/2023 | 3 | 0 | 3 | 04/25/2023 | 04/25/2023 | 221 | 202 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 11/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 176555 | 01906 | 10 | Solar | 05_01_304W1 | 10/05/2015 | 10/05/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 336 | 0 | 336 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2015 |  | 10/13/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ERVING | 618898 | 01344 | 13.6 | Solar | 05_07_5W3 | 06/20/2024 | 07/09/2024 | 3 | 0 | 3 | 07/10/2024 | 07/10/2024 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 06/20/2024 | 8/6/2025 | Y | EXP | 365 | 10/17/2024 | 02/05/2025 | 112 | 0 | 112 |  |  | 2/13/2025 | Connected |  | N
National Grid | HANOVER | 659661 | 02339 | 10 | Solar | 05_12_19W1 | 12/16/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 12/16/2024 | 2/21/2026 | Y | EXP | 365 | 07/02/2025 | 11/21/2025 | 143 | 0 | 143 |  |  | 11/26/2025 | Connected |  | N
National Grid | GRAFTON | 175764 | 01519 | 480 | Solar | 05_09_705W1 | 05/22/2014 | 05/22/2014 | 6 | 0 | 6 | 06/03/2014 | 06/03/2014 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 647801 | 02368 | 5.76 | Solar | 05_07_95W1 | 10/28/2024 | 12/29/2024 | 4 | 0 | 4 | 12/30/2024 | 12/30/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | LYNN | 176683 | 01905 | 4.73 | Solar | 05_01_304W1 | 02/18/2016 | 02/18/2016 | 35 | 35 | 0 | 04/08/2016 | 04/08/2016 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2016 |  | 2/23/2017 | N | EXP | 316 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WENDELL | 629786 | 01379 | 9.28 | Solar | 05_07_5W3 | 08/02/2024 | 10/03/2024 | 5 | 4 | 1 | 10/04/2024 | 10/04/2024 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | HANOVER | 667525 | 02339 | 5.76 | Solar | 05_12_19W1 | 01/31/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | GRAFTON | 178466 | 01519 | 4800 | Solar | 05_09_705W1 | 01/23/2018 | 01/23/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2018 | 03/22/2018 | 6 | 1 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/29/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 664678 | 02368 | 9.5 | Solar | 05_07_95W1 | 01/09/2025 | 01/13/2025 | 18 | 14 | 4 | 06/02/2025 | 06/02/2025 | 83 | 69 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | SAUGUS | 177835 | 01906 | 1760 | Solar | 05_01_304W1 | 08/09/2017 | 08/09/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2017 | 09/20/2017 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2018 | 08/09/2017 | 7/16/2022 | Y | STD | 434 | 11/25/2021 | 03/14/2022 | 110 | 0 | 110 |  |  | 3/21/2022 | Connected |  | N
National Grid | ERVING | 633007 | 01344 | 10 | Solar | 05_07_5W3 | 08/15/2024 | 09/11/2024 | 3 | 0 | 3 | 09/12/2024 | 09/12/2024 | 26 | 18 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 | 08/15/2024 | 10/31/2025 | Y | EXP | 365 | 12/19/2024 | 01/25/2025 | 38 | 0 | 38 |  |  | 2/11/2025 | Connected |  | N
National Grid | HANOVER | 668988 | 02339 | 7.6 | Solar | 05_12_19W1 | 02/04/2025 | 02/13/2025 | 7 | 3 | 4 | 02/14/2025 | 02/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 178652 | 01527 | 1125 | Solar | 05_09_705W1 | 12/18/2017 | 12/18/2017 | 30 | 14 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2018 | 02/24/2018 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/24/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 243592 | 02368 | 999 | Solar | 05_07_95W2 | 07/25/2019 | 08/12/2019 | 12 | 7 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/13/2019 | 09/04/2019 | 16 | 3 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2020 | 07/25/2019 | 4/20/2026 | Y | STD | 19 | 07/20/2021 | 09/15/2023 | 788 | 631 | 157 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 178296 | 01906 | 10 | Solar | 05_01_304W1 | 11/15/2017 | 11/15/2017 | 63 | 49 | 14 | 02/20/2018 | 02/20/2018 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2018 |  | 11/21/2018 | N | EXP | 273 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ERVING | 638210 | 01344 | 7.25 | Solar | 05_07_5W3 | 09/06/2024 | 10/07/2024 | 14 | 12 | 2 | 10/08/2024 | 10/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 12/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | HANOVER | 670811 | 02339 | 11.4 | Solar | 05_12_19W1 | 02/12/2025 | 03/19/2025 | 1 | 0 | 1 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 | 05/07/2025 | 05/20/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 05/20/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | GRAFTON | 184433 | 01536 | 2600 | Solar | 05_09_705W1 | 05/03/2018 | 05/03/2018 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2018 | 06/01/2018 | 7 | 0 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 500843 | 02368 | 987.5 | Solar | 05_07_95W2 | 03/02/2023 | 03/30/2023 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/31/2023 | 04/28/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/02/2023 | 6/10/2027 | Y | STD | 448 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LYNN | 185050 | 01905 | 240 | Solar | 05_01_304W1 | 05/10/2018 | 05/10/2018 | 17 | 0 | 17 |  |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 | 05/10/2018 | 10/27/2022 | Y | STD | 773 | 10/22/2019 | 07/29/2020 | 282 | 247 | 35 |  |  | 4/15/2022 | Connected |  | N
National Grid | WENDELL | 644185 | 01379 | 5 | Solar | 05_07_5W3 | 10/02/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/02/2024 | 11/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | HANOVER | 672162 | 02339 | 7.6 | Solar | 05_12_19W1 | 02/20/2025 | 03/05/2025 | 10 | 7 | 3 | 03/06/2025 | 03/06/2025 | 118 | 100 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 185644 | 01519 | 220 | Solar | 05_09_705W1 | 05/17/2018 | 05/17/2018 | 32 | 17 | 15 | 07/05/2018 | 07/05/2018 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 691137 | 02368 | 23.8 | Solar | 05_07_95W2 | 05/15/2025 | 05/28/2025 | 8 | 4 | 4 | 05/29/2025 | 05/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2025 | 05/15/2025 | 7/29/2026 | Y | EXP | 365 | 09/26/2025 | 11/25/2025 | 61 | 0 | 61 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 193678 | 01906 | 250 | Solar | 05_01_304W1 | 08/17/2018 | 08/27/2018 | 4 | 0 | 4 | 08/28/2018 | 08/28/2018 | 0 | 0 | 0 | 09/27/2019 | 11/26/2019 | 40 | 20 | 20 |  |  | 0 | 0 | 0 | 11/26/2019 | 40 | 20 | 20 |  |  | 0 | 0 | 0 | 12/12/2019 | 08/17/2018 | 5/17/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2021 | Connected |  | N
National Grid | WENDELL | 646034 | 01379 | 10 | Solar | 05_07_5W3 | 10/10/2024 | 11/04/2024 | 10 | 6 | 4 | 11/05/2024 | 11/05/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 | 10/10/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | HANOVER | 682844 | 02339 | 11.5 | Solar | 05_12_19W1 | 04/08/2025 | 06/02/2025 | 28 | 24 | 4 | 06/03/2025 | 06/03/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | MILLBURY | 188655 | 01527 | 3100 | Solar | 05_09_705W1 | 11/16/2018 | 12/03/2018 | 8 | 0 | 8 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 710703 | 02368 | 249 | Solar | 05_07_95W2 | 08/08/2025 | 09/05/2025 | 19 | 9 | 10 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SAUGUS | 195088 | 01906 | 10 | Solar | 05_01_304W1 | 09/10/2018 | 10/31/2018 | 9 | 8 | 1 | 11/01/2018 | 11/01/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 12/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2019 | Connected |  | N
National Grid | WENDELL | 646615 | 01380 | 10 | Solar | 05_07_5W3 | 10/17/2024 | 12/09/2024 | 17 | 13 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 10/17/2024 | 1/30/2026 | Y | EXP | 365 | 05/10/2025 | 10/23/2025 | 167 | 0 | 167 |  |  | 11/17/2025 | Connected |  | N
National Grid | NORWELL | 697773 | 02061 | 17.45 | Solar | 05_12_19W1 | 06/11/2025 | 06/17/2025 | 4 | 0 | 4 | 06/18/2025 | 06/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 8/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 192888 | 01519 | 1000 | Solar | 05_09_705W1 | 09/07/2018 | 09/25/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2018 | 11/07/2018 | 30 | 11 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 760437 | 02368 | 0 | Battery Add-On | 05_07_95W2 | 04/01/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SAUGUS | 193132 | 01906 | 4000 | Solar | 05_01_304W1 | 10/24/2018 | 11/08/2018 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 05/21/2021 | 05/01/2023 | 486 | 322 | 164 | 3/11/2021 | 10/24/2018 | 2/7/2025 | Y | CMPX | 399 |  |  | 0 | 0 | 0 |  |  | 6/28/2024 | Connected |  | N
National Grid | WENDELL | 647936 | 01379 | 10 | Solar | 05_07_5W3 | 10/28/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/28/2024 | 1/14/2026 | Y | EXP | 365 | 06/11/2025 | 10/29/2025 | 141 | 0 | 141 |  |  | 11/14/2025 | Connected |  | N
National Grid | HANOVER | 716680 | 02339 | 17.45 | Solar | 05_12_19W1 | 09/04/2025 | 09/08/2025 | 1 | 0 | 1 | 09/09/2025 | 09/09/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 |  | 10/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2026 | Connected |  | N
National Grid | GRAFTON | 196745 | 01519 | 10 | Solar | 05_09_705W1 | 09/24/2018 | 10/24/2018 | 18 | 17 | 1 | 10/25/2018 | 10/25/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2018 | 09/24/2018 | 3/11/2019 | Y | EXP | 132 | 02/02/2019 | 02/22/2019 | 20 | 0 | 20 |  |  | 3/5/2019 | Connected |  | N
National Grid | RANDOLPH | 174810 | 02368 | 250 | Solar | 05_07_95W2 | 01/24/2013 | 01/24/2013 | 10 | 4 | 6 | 02/14/2013 | 02/14/2013 | 403 | 0 | 403 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2013 |  | 5/31/2013 | N | EXP | 66 |  |  | 0 | 0 | 0 | 3/26/2013 | 3/26/2013 |  | Withdrawn |  | Y
National Grid | SAUGUS | 196967 | 01906 | 6 | Solar | 05_01_304W1 | 09/26/2018 | 10/18/2018 | 2 | 2 | 0 | 10/19/2018 | 10/19/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 12/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2019 | Connected |  | N
National Grid | WENDELL | 654753 | 01379 | 5 | Solar | 05_07_5W3 | 11/20/2024 | 12/13/2024 | 10 | 9 | 1 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | HANOVER | 719392 | 02339 | 7.6 | Solar | 05_12_19W1 | 09/16/2025 | 09/17/2025 | 1 | 0 | 1 | 09/18/2025 | 09/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | GRAFTON | 270599 | 01519 | 2791 | Battery Add-On | 05_09_705W1 | 04/24/2020 | 05/27/2020 | 22 | 18 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2020 | 07/09/2020 | 31 | 13 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 175381 | 02368 | 1000 | Solar | 05_07_95W2 | 06/26/2014 | 06/26/2014 | 69 | 69 | 0 | 10/06/2014 | 10/06/2014 | 257 | 0 | 257 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2014 |  | 2/27/2015 | N | EXP | 80 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 199009 | 01906 | 10 | Solar | 05_01_304W1 | 01/16/2019 | 01/30/2019 | 8 | 0 | 8 | 01/31/2019 | 01/31/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 | 01/16/2019 | 2/12/2020 | Y | EXP | 365 | 06/22/2019 | 06/21/2019 | 0 | 0 | 0 |  |  | 7/25/2019 | Connected |  | N
National Grid | WENDELL | 656937 | 01379 | 3.8 | Solar | 05_07_5W3 | 11/26/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | HANOVER | 722477 | 02339 | 7.6 | Solar | 05_12_19W1 | 09/30/2025 | 10/03/2025 | 3 | 0 | 3 | 10/06/2025 | 10/06/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | GRAFTON | 465809 | 01519 | 0 | Other | 05_09_705W1 | 02/27/2023 | 04/13/2023 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/14/2023 | 05/26/2023 | 31 | 11 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 175605 | 02368 | 17.6 | Solar | 05_07_95W2 | 10/16/2014 | 10/16/2014 | 8 | 5 | 3 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 |  | 12/31/2014 | N | EXP | 51 |  |  | 0 | 0 | 0 | 1/30/2015 | 1/30/2015 | 2/24/2015 | Connected |  | N
National Grid | SAUGUS | 204685 | 01906 | 0 | Solar | 05_01_304W1 | 01/17/2019 | 02/01/2019 | 9 | 0 | 9 | 02/04/2019 | 02/04/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2019 | Connected |  | N
National Grid | WENDELL | 659867 | 01379 | 2.32 | Solar | 05_07_5W3 | 12/11/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 679038 | 02341 | 400 | Solar | 05_12_19W2 | 04/08/2025 | 06/27/2025 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2025 | 07/22/2025 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | GRAFTON | 515826 | 01536 | 10 | Solar | 05_09_705W1 | 03/30/2023 | 04/28/2023 | 20 | 18 | 2 | 05/01/2023 | 05/01/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 175672 | 02368 | 816 | Solar | 05_07_95W2 | 10/21/2014 | 10/21/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2014 | 11/26/2014 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/15/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 211835 | 01906 | 1760 | Solar | 05_01_304W1 | 02/27/2019 | 04/04/2019 | 25 | 17 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2019 | 07/08/2019 | 65 | 49 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WENDELL | 664368 | 01379 | 6 | Solar | 05_07_5W3 | 01/08/2025 | 02/04/2025 | 4 | 0 | 4 | 02/05/2025 | 02/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | HANSON | 174131 | 02341 | 252 | Solar | 05_12_19W2 | 05/03/2012 | 05/03/2012 | 9 | 0 | 9 | 05/18/2012 | 05/18/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/29/2012 | N | EXP | 44 |  |  | 0 | 0 | 0 | 6/20/2013 | 6/20/2013 | 6/28/2013 | Connected |  | N
National Grid | GRAFTON | 641326 | 01519 | 17.6 | Solar | 05_09_705W1 | 09/18/2024 | 09/20/2024 | 2 | 0 | 2 | 09/23/2024 | 09/23/2024 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 09/18/2024 | 11/10/2025 | Y | EXP | 365 | 01/22/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 2/15/2025 | Connected |  | N
National Grid | RANDOLPH | 176618 | 02368 | 1000 | Solar | 05_07_95W2 | 04/12/2016 | 04/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2016 | 05/20/2016 | 27 | 15 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 213993 | 01906 | 7.6 | Solar | 05_01_304W1 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  | 4/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2019 | Connected |  | N
National Grid | SHUTESBURY | 674330 | 01072 | 3.8 | Solar | 05_07_5W3 | 02/26/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2025 | Connected |  | N
National Grid | HANOVER | 175273 | 02339 | 42.57 | Solar | 05_12_19W2 | 08/28/2014 | 08/28/2014 | 6 | 5 | 1 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 11/28/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 5/29/2015 | Connected |  | N
National Grid | GRAFTON | 680002 | 01536 | 23 | Solar | 05_09_705W1 | 03/27/2025 | 04/02/2025 | 4 | 0 | 4 | 04/03/2025 | 04/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2025 | Connected |  | N
National Grid | RANDOLPH | 178052 | 02368 | 1000 | Solar | 05_07_95W2 | 06/30/2017 | 06/30/2017 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2017 | 08/07/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/5/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 222250 | 01905 | 10 | Solar | 05_01_304W1 | 05/13/2019 | 05/24/2019 | 8 | 1 | 7 | 05/28/2019 | 05/28/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 6/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2019 | Connected |  | N
National Grid | WENDELL | 675412 | 01379 | 3.8 | Solar | 05_07_5W3 | 03/04/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 59 | 36 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | HANOVER | 177308 | 02339 | 7.6 | Solar | 05_12_19W2 | 11/16/2016 | 11/16/2016 | 3 | 3 | 0 | 11/22/2016 | 11/22/2016 | 136 | 0 | 136 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2016 |  | 11/22/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 562198 | 01519 | 100 | Solar | 05_09_705W2 | 10/19/2023 | 11/17/2023 | 19 | 9 | 10 |  |  | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RANDOLPH | 228439 | 02368 | 17.6 | Solar | 05_07_95W2 | 05/15/2019 | 05/16/2019 | 0 | 0 | 0 | 05/17/2019 | 05/17/2019 | 202 | 29 | 173 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2019 | Connected |  | N
National Grid | SAUGUS | 248216 | 01906 | 7.6 | Solar | 05_01_304W1 | 09/19/2019 | 10/04/2019 | 10 | 10 | 0 | 10/07/2019 | 10/07/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2019 | 09/19/2019 | 6/8/2020 | Y | EXP | 365 | 01/16/2020 | 01/31/2020 | 15 | 0 | 15 |  |  | 2/13/2020 | Connected |  | N
National Grid | WENDELL | 676051 | 01379 | 11.5 | Solar | 05_07_5W3 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 121 | 98 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 315451 | 02339 | 12.48 | Solar | 05_12_19W2 | 10/23/2020 | 10/27/2020 | 1 | 0 | 1 | 10/28/2020 | 10/28/2020 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  |  | N | EXP | 365 | 03/25/2021 | 06/24/2021 | 91 | 0 | 91 |  |  | 8/14/2021 | Connected |  | N
National Grid | GRAFTON | 577961 | 01536 | 240 | Solar | 05_09_705W2 | 12/15/2023 | 01/07/2024 | 13 | 3 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | RANDOLPH | 279002 | 02368 | 0 | Solar | 05_07_95W2 | 03/13/2020 | 03/16/2020 | 0 | 0 | 0 | 03/17/2020 | 03/17/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2020 | Connected |  | N
National Grid | SAUGUS | 265476 | 01906 | 0 | Solar | 05_01_304W1 | 11/14/2019 | 11/20/2019 | 3 | 0 | 3 | 11/21/2019 | 11/21/2019 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2020 | 11/14/2019 | 11/14/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2020 | Connected |  | N
National Grid | SHUTESBURY | 680201 | 01072 | 7.6 | Solar | 05_07_5W3 | 03/24/2025 | 03/26/2025 | 2 | 0 | 2 | 03/27/2025 | 03/27/2025 | 40 | 22 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 03/24/2025 | 7/1/2026 | Y | EXP | 365 | 08/13/2025 | 02/13/2026 | 185 | 0 | 185 |  |  | 12/22/2025 | Connected |  | N
National Grid | HANOVER | 447931 | 02339 | 9.6 | Solar | 05_12_19W2 | 08/19/2022 | 08/22/2022 | 1 | 0 | 1 | 08/23/2022 | 08/23/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 |  | 10/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2022 | Connected |  | N
National Grid | GRAFTON | 739260 | 01519 | 0 | Battery Add-On | 05_09_705W2 | 12/10/2025 | 01/12/2026 | 2 | 0 | 2 | 01/26/2026 | 01/26/2026 | 28 | 12 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2026 |  | 3/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 346398 | 02368 | 17.76 | Solar | 05_07_95W2 | 03/11/2021 | 04/07/2021 | 18 | 18 | 0 | 04/08/2021 | 04/08/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2021 |  | 4/6/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 266020 | 01906 | 7.6 | Solar | 05_01_304W1 | 11/21/2019 | 12/10/2019 | 12 | 12 | 0 | 12/11/2019 | 12/11/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 |  | 12/21/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHUTESBURY | 686459 | 01072 | 5.76 | Solar | 05_07_5W3 | 04/21/2025 | 05/12/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 | 04/21/2025 | 6/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2025 | Connected |  | N
National Grid | HANOVER | 660697 | 02339 | 11.5 | Solar | 05_12_19W2 | 12/16/2024 | 12/31/2024 | 3 | 0 | 3 | 01/02/2025 | 01/02/2025 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | GRAFTON | 747254 | 01536 | 10 | Solar | 05_09_705W2 | 01/23/2026 | 02/03/2026 | 3 | 0 | 3 | 02/11/2026 | 02/11/2026 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 348533 | 02368 | 157.52 | Solar | 05_07_95W2 | 03/24/2021 | 07/02/2021 | 70 | 60 | 10 | 07/06/2021 | 07/06/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 290832 | 01906 | 1.68 | Solar | 05_01_304W1 | 05/07/2020 | 05/21/2020 | 10 | 5 | 5 | 05/22/2020 | 05/22/2020 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 |  | 6/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2022 | Connected |  | N
National Grid | WENDELL | 695663 | 01379 | 7.8 | Solar | 05_07_5W3 | 06/02/2025 | 06/16/2025 | 4 | 0 | 4 | 07/22/2025 | 07/22/2025 | 14 | 3 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 663463 | 02339 | 5.76 | Solar | 05_12_19W2 | 01/14/2025 | 01/27/2025 | 3 | 0 | 3 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | GRAFTON | 174113 | 01519 | 13.54 | Solar | 05_09_705W2 | 03/30/2012 | 03/30/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2012 |  | 5/28/2012 | N | EXP | 60 |  |  | 0 | 0 | 0 | 7/27/2012 | 7/27/2012 | 11/29/2012 | Connected |  | N
National Grid | RANDOLPH | 378618 | 02368 | 15.2 | Solar | 05_07_95W2 | 08/29/2021 | 08/30/2021 | 1 | 0 | 1 | 08/31/2021 | 08/31/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 | 08/29/2021 | 8/23/2023 | Y | EXP | 365 | 12/28/2021 | 02/01/2022 | 36 | 0 | 36 |  |  | 10/13/2022 | Connected |  | N
National Grid | SAUGUS | 291144 | 01906 | 9.996 | Solar | 05_01_304W1 | 05/08/2020 | 05/13/2020 | 2 | 0 | 2 | 05/14/2020 | 05/14/2020 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2020 | 05/08/2020 | 4/23/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2021 | Connected |  | N
National Grid | ORANGE | 720806 | 01364 | 6.825 | Solar | 05_07_5W3 | 09/22/2025 | 10/08/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 | 09/22/2025 | 11/4/2026 | Y | EXP | 365 | 12/23/2025 | 01/02/2026 | 11 | 0 | 11 |  |  | 1/6/2026 | Connected |  | N
National Grid | PEMBROKE | 657267 | 02359 | 5.8 | Solar | 05_12_1J4 | 12/02/2024 | 12/30/2024 | 8 | 4 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | MILLBURY | 174190 | 01527 | 1000 | Solar | 05_09_705W2 | 03/15/2012 | 03/15/2012 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 396601 | 02368 | 17.76 | Solar | 05_07_95W2 | 12/01/2021 | 01/07/2022 | 7 | 3 | 4 | 12/10/2021 | 12/10/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2022 |  | 3/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2022 | Connected |  | Y
National Grid | SAUGUS | 301597 | 01906 | 10 | Solar | 05_01_304W1 | 07/30/2020 | 08/12/2020 | 8 | 6 | 2 | 08/13/2020 | 08/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 | 07/30/2020 | 8/5/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2021 | Connected |  | N
National Grid | ORANGE | 726274 | 01364 | 5.76 | Solar | 05_07_5W3 | 10/14/2025 | 10/24/2025 | 7 | 2 | 5 | 10/27/2025 | 10/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2026 | Connected |  | N
National Grid | HANOVER | 710218 | 02339 | 150 | Solar | 05_12_1J6 | 08/12/2025 | 10/10/2025 | 41 | 31 | 10 |  |  | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | GRAFTON | 174228 | 01519 | 1000 | Solar | 05_09_705W2 | 02/09/2012 | 02/09/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 411091 | 02368 | 0 | Solar | 05_07_95W2 | 02/23/2022 | 03/09/2022 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 306191 | 01906 | 15.2 | Solar | 05_01_304W1 | 08/11/2020 | 08/13/2020 | 1 | 0 | 1 | 08/14/2020 | 08/14/2020 | 88 | 64 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/12/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 707573 | 01364 | 5.76 | Solar | 05_07_5W4 | 07/25/2025 | 08/12/2025 | 1 | 0 | 1 | 08/21/2025 | 08/21/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 |  | 9/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HANSON | 345717 | 02341 | 32.4 | Solar | 05_12_1J7 | 03/22/2021 | 04/05/2021 | 9 | 0 | 9 | 04/06/2021 | 04/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2021 |  | 6/1/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2021 | Connected |  | N
National Grid | GRAFTON | 174227 | 01536 | 1000 | Solar | 05_09_705W2 | 02/09/2012 | 02/09/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 421168 | 02368 | 0 | Solar | 05_07_95W2 | 07/18/2022 | 08/11/2022 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2022 | 09/09/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 322960 | 01906 | 5.584 | Solar | 05_01_304W1 | 12/14/2020 | 12/30/2020 | 10 | 6 | 4 | 12/31/2020 | 12/31/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/14/2020 | 2/3/2022 | Y | EXP | 365 | 09/04/2021 | 11/08/2021 | 66 | 4 | 62 |  |  | 1/12/2022 | Connected |  | N
National Grid | ORANGE | 746646 | 01364 | 5.76 | Solar | 05_07_5W4 | 01/21/2026 | 01/28/2026 | 13 | 11 | 2 | 02/23/2026 | 02/23/2026 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HANSON | 522459 | 02341 | 34.6 | Solar | 05_12_1J7 | 05/01/2023 | 05/02/2023 | 1 | 0 | 1 | 05/03/2023 | 05/03/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2023 |  | 6/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2024 | Connected |  | N
National Grid | MILLBURY | 174226 | 01527 | 1000 | Solar | 05_09_705W2 | 02/09/2012 | 02/09/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 456914 | 02368 | 6.96 | Solar | 05_07_95W2 | 09/14/2022 | 09/21/2022 | 6 | 5 | 1 | 09/22/2022 | 09/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 09/14/2022 | 10/21/2023 | Y | EXP | 365 | 11/05/2022 | 12/21/2022 | 47 | 0 | 47 |  |  | 1/12/2023 | Connected |  | N
National Grid | SAUGUS | 339113 | 01906 | 9.8 | Solar | 05_01_304W1 | 01/27/2021 | 01/28/2021 | 0 | 0 | 0 | 01/29/2021 | 01/29/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2021 | Connected |  | N
National Grid | ORANGE | 177952 | 01364 | 10 | Solar | 05_07_5W4 | 08/24/2017 | 08/24/2017 | 10 | 10 | 0 | 09/08/2017 | 09/08/2017 | 137 | 0 | 137 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2017 |  | 8/29/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 644057 | 02359 | 8.027 | Solar | 05_12_1J7 | 10/01/2024 | 10/09/2024 | 2 | 0 | 2 | 10/10/2024 | 10/10/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 | 10/01/2024 | 11/19/2025 | Y | EXP | 365 | 01/23/2025 | 05/02/2025 | 100 | 0 | 100 |  |  | 5/14/2025 | Connected |  | N
National Grid | GRAFTON | 174225 | 01519 | 1000 | Solar | 05_09_705W2 | 02/09/2012 | 02/09/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 592315 | 02368 | 150 | Solar | 05_07_95W2 | 02/26/2024 | 05/24/2024 | 63 | 54 | 9 | 05/28/2024 | 05/28/2024 | 361 | 346 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 339077 | 01970 | 7.6 | Solar | 05_01_304W1 | 01/27/2021 | 01/28/2021 | 0 | 0 | 0 | 01/29/2021 | 01/29/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2021 | Connected |  | N
National Grid | ORANGE | 285394 | 01364 | 6 | Solar | 05_07_5W4 | 04/17/2020 | 05/06/2020 | 12 | 12 | 0 | 05/07/2020 | 05/07/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 | 04/17/2020 | 5/5/2021 | Y | EXP | 365 | 07/29/2020 | 09/18/2020 | 52 | 5 | 47 |  |  | 9/23/2020 | Connected |  | N
National Grid | HANSON | 706419 | 02341 | 300 | Solar | 05_12_1J901 | 10/17/2025 | 12/16/2025 | 38 | 29 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 | 01/08/2026 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MILLBURY | 174224 | 01527 | 6000 | Solar | 05_09_705W2 | 02/09/2012 | 02/09/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 608928 | 02368 | 14.5 | Solar | 05_07_95W2 | 05/29/2024 | 06/14/2024 | 2 | 0 | 2 | 06/17/2024 | 06/17/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 |  | 7/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | SALEM | 338606 | 01970 | 8.725 | Solar | 05_01_304W1 | 02/02/2021 | 02/12/2021 | 8 | 8 | 0 | 02/16/2021 | 02/16/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 | 02/02/2021 | 7/19/2022 | Y | EXP | 365 | 06/25/2021 | 07/15/2021 | 21 | 0 | 21 |  |  | 9/16/2021 | Connected |  | N
National Grid | ORANGE | 286931 | 01364 | 7.6 | Solar | 05_07_5W4 | 04/24/2020 | 04/29/2020 | 3 | 2 | 1 | 04/30/2020 | 04/30/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 |  | 4/28/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 201985 | 02339 | 7.6 | Solar | 05_12_1J901 | 11/27/2018 | 12/17/2018 | 8 | 0 | 8 | 12/18/2018 | 12/18/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  | 1/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2019 | Connected |  | N
National Grid | GRAFTON | 174251 | 01519 | 18 | Solar | 05_09_705W2 | 02/24/2012 | 02/24/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2012 |  | 6/1/2012 | N | EXP | 11 |  |  | 0 | 0 | 0 | 5/21/2012 | 5/21/2012 | 10/19/2012 | Connected |  | N
National Grid | RANDOLPH | 644210 | 02368 | 5.76 | Solar | 05_07_95W2 | 10/02/2024 | 11/12/2024 | 19 | 14 | 5 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/02/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | SALEM | 358023 | 01970 | 0 | Solar | 05_01_304W1 | 05/13/2021 | 05/14/2021 | 0 | 0 | 0 | 05/17/2021 | 05/17/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2021 | 05/13/2021 | 4/24/2023 | Y | EXP | 550 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 320043 | 01364 | 9.8 | Solar | 05_07_5W4 | 12/23/2020 | 12/30/2020 | 3 | 0 | 3 | 12/31/2020 | 12/31/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 360157 | 02339 | 7.6 | Solar | 05_12_1J901 | 07/01/2021 | 07/13/2021 | 6 | 0 | 6 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 174309 | 01519 | 1800 | Solar | 05_09_705W2 | 12/30/2011 | 12/30/2011 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 649658 | 02368 | 10 | Solar | 05_07_95W2 | 10/25/2024 |  | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 449309 | 01970 | 15.2 | Solar | 05_01_304W1 | 08/04/2022 | 08/10/2022 | 4 | 3 | 1 | 08/11/2022 | 08/11/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2022 |  | 1/19/2024 | N | EXP | 474 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 431236 | 01364 | 8.12 | Solar | 05_07_5W4 | 05/09/2023 | 05/12/2023 | 3 | 2 | 1 | 05/15/2023 | 05/15/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2023 | 05/09/2023 | 6/20/2024 | Y | EXP | 365 | 12/07/2023 | 12/12/2023 | 6 | 0 | 6 |  |  | 12/18/2023 | Connected |  | N
National Grid | HANSON | 382866 | 02341 | 3.8 | Solar | 05_12_1J901 | 10/19/2021 | 01/07/2022 | 15 | 6 | 9 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 174975 | 01519 | 500 | Solar | 05_09_705W2 | 09/20/2011 | 09/20/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2011 | 01/03/2012 | 58 | 0 | 58 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2012 | 09/20/2011 | 11/30/2012 | Y | STD | 100 | 06/04/2013 | 07/25/2013 | 35 | 0 | 35 | 7/23/2013 | 7/23/2013 | 7/30/2013 | Connected |  | N
National Grid | RANDOLPH | 650272 | 02368 | 12.35 | Solar | 05_07_95W2 | 10/28/2024 | 11/13/2024 | 3 | 1 | 2 | 11/14/2024 | 11/14/2024 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/28/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | SALEM | 375886 | 01970 | 15.2 | Solar | 05_01_304W1 | 09/01/2021 | 09/09/2021 | 5 | 3 | 2 | 09/10/2021 | 09/10/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2021 |  | 11/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2022 | Connected |  | Y
National Grid | ORANGE | 442826 | 01364 | 8.12 | Solar | 05_07_5W4 | 08/09/2022 | 08/11/2022 | 2 | 0 | 2 | 08/12/2022 | 08/12/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 |  | 9/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 407813 | 02339 | 3.84 | Solar | 05_12_1J901 | 02/04/2022 | 02/08/2022 | 2 | 0 | 2 | 02/09/2022 | 02/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 | 02/04/2022 | 7/26/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2022 | Connected |  | N
National Grid | GRAFTON | 174974 | 01519 | 1500 | Solar | 05_09_705W2 | 09/20/2011 | 09/20/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2011 | 01/03/2012 | 58 | 0 | 58 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2012 | 09/20/2011 | 11/30/2012 | Y | STD | 100 | 06/04/2013 | 07/25/2013 | 35 | 0 | 35 | 7/23/2013 | 7/23/2013 | 7/30/2013 | Connected |  | N
National Grid | RANDOLPH | 654971 | 02368 | 10 | Solar | 05_07_95W2 | 11/19/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/19/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | LYNN | 381612 | 01902 | 20.3 | Solar | 05_01_304W1 | 01/25/2022 |  | 27 | 26 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 459057 | 01364 | 6 | Solar | 05_07_5W4 | 09/21/2022 | 09/23/2022 | 2 | 0 | 2 | 09/26/2022 | 09/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2022 | 09/21/2022 | 10/2/2024 | Y | EXP | 365 | 06/01/2023 | 09/08/2023 | 100 | 0 | 100 |  |  | 10/20/2023 | Connected |  | N
National Grid | HANOVER | 526726 | 02339 | 6 | Solar | 05_12_1J901 | 05/25/2023 | 05/30/2023 | 2 | 0 | 2 | 05/31/2023 | 05/31/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2023 | 05/25/2023 | 11/29/2024 | Y | EXP | 365 | 09/06/2023 | 12/15/2023 | 101 | 0 | 101 |  |  | 1/25/2024 | Connected |  | N
National Grid | MILLBURY | 175012 | 01527 | 3000 | Solar | 05_09_705W2 | 08/30/2011 | 08/30/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 665433 | 02368 | 3.8 | Solar | 05_07_95W2 | 01/13/2025 | 01/22/2025 | 5 | 0 | 5 | 01/23/2025 | 01/23/2025 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 388111 | 01902 | 15.2 | Solar | 05_01_304W1 | 10/17/2021 | 12/16/2021 | 42 | 40 | 2 | 12/17/2021 | 12/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEW SALEM | 518780 | 01355 | 7.54 | Solar | 05_07_5W4 | 04/24/2023 | 04/26/2023 | 2 | 0 | 2 | 04/27/2023 | 04/27/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANSON | 557391 | 02341 | 3.36 | Solar | 05_12_1J901 | 09/22/2023 | 11/06/2023 | 30 | 27 | 3 | 11/07/2023 | 11/07/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  | 12/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2024 | Connected |  | N
National Grid | GRAFTON | 175858 | 01519 | 30 | Solar | 05_09_705W2 | 07/31/2015 | 07/31/2015 | 0 | 0 | 0 | 08/04/2015 | 08/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2015 | 07/31/2015 | 8/9/2016 | Y | EXP | 357 | 09/01/2016 | 09/14/2016 | 8 | 0 | 8 | 8/18/2015 | 8/18/2015 | 10/12/2016 | Connected |  | N
National Grid | RANDOLPH | 671391 | 02368 | 5.76 | Solar | 05_07_95W2 | 02/11/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2025 | Connected |  | N
National Grid | LYNN | 414504 | 01902 | 15.2 | Solar | 05_01_304W1 | 02/28/2022 | 03/02/2022 | 2 | 0 | 2 | 09/13/2022 | 09/13/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2022 |  | 10/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2022 | Connected |  | N
National Grid | ORANGE | 547826 | 01364 | 3 | Solar | 05_07_5W4 | 08/15/2023 | 08/22/2023 | 6 | 5 | 1 | 08/23/2023 | 08/23/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 561827 | 02339 | 5 | Solar | 05_12_1J901 | 10/16/2023 | 10/25/2023 | 7 | 6 | 1 | 10/26/2023 | 10/26/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 10/16/2023 | 11/15/2024 | Y | EXP | 365 | 05/01/2024 | 04/30/2024 | 0 | 0 | 0 |  |  | 5/5/2024 | Connected |  | N
National Grid | GRAFTON | 175857 | 01519 | 30.1 | Solar | 05_09_705W2 | 07/31/2015 | 07/31/2015 | 0 | 0 | 0 | 08/04/2015 | 08/04/2015 | 235 | 0 | 235 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2015 |  | 8/9/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 684271 | 02368 | 17.86 | Solar | 05_07_95W2 | 04/10/2025 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 414386 | 01902 | 15.2 | Solar | 05_01_304W1 | 02/25/2022 | 02/28/2022 | 1 | 0 | 1 | 03/01/2022 | 03/01/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 550147 | 01364 | 5 | Solar | 05_07_5W4 | 08/24/2023 | 08/28/2023 | 3 | 1 | 2 | 08/29/2023 | 08/29/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  | 12/31/2024 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 647807 | 02359 | 6.09 | Solar | 05_12_1J901 | 10/17/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 177183 | 01536 | 990 | Solar | 05_09_705W2 | 08/12/2016 | 08/16/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/16/2016 | 10/06/2016 | 36 | 19 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 | 08/12/2016 | 11/30/2020 | Y | STD | 835 | 01/31/2020 | 10/15/2020 | 259 | 5 | 254 |  |  | 11/20/2020 | Connected |  | N
National Grid | RANDOLPH | 707155 | 02368 | 6.631 | Solar | 05_07_95W2 | 07/24/2025 | 09/15/2025 | 25 | 20 | 5 | 09/16/2025 | 09/16/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | LYNN | 415260 | 01902 | 20.3 | Solar | 05_01_304W1 | 03/03/2022 | 03/04/2022 | 1 | 0 | 1 | 03/07/2022 | 03/07/2022 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2022 |  | 7/6/2023 | N | EXP | 420 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 581941 | 01364 | 8.12 | Solar | 05_07_5W4 | 02/01/2024 | 03/14/2024 | 26 | 25 | 1 | 03/15/2024 | 03/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 3/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2024 | Connected |  | N
National Grid | HANSON | 657771 | 02341 | 5.76 | Solar | 05_12_1J901 | 12/02/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/02/2024 | 3/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | GRAFTON | 177562 | 01519 | 4980 | Solar | 05_09_705W2 | 07/13/2017 | 07/27/2017 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2017 | 08/21/2017 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2017 | 07/13/2017 | 6/1/2021 | Y | STD | 867 | 10/15/2020 | 03/25/2021 | 161 | 0 | 161 |  |  | 4/14/2021 | Connected |  | N
National Grid | RANDOLPH | 438749 | 02368 | 375 | Solar | 05_07_95W3 | 10/10/2022 | 11/07/2022 | 21 | 12 | 9 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/10/2022 | 6/10/2027 | Y | STD | 448 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LYNN | 434574 | 01902 | 10 | Solar | 05_01_304W1 | 06/13/2022 | 06/14/2022 | 1 | 0 | 1 | 06/15/2022 | 06/15/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 589709 | 01364 | 6.96 | Solar | 05_07_5W4 | 02/21/2024 | 02/26/2024 | 3 | 0 | 3 | 02/27/2024 | 02/27/2024 | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 672039 | 02359 | 3.8 | Solar | 05_12_1J901 | 02/13/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 10/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | GRAFTON | 177870 | 01519 | 840 | Solar | 05_09_705W2 | 08/09/2017 | 08/22/2017 | 8 | 0 | 8 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2018 | 08/09/2017 | 12/16/2021 | Y | STD | 20 | 10/03/2020 | 04/22/2021 | 201 | 0 | 201 | 10/18/2021 | 11/8/2021 | 12/8/2021 | Connected |  | N
National Grid | RANDOLPH | 715555 | 02368 | 100 | Solar | 05_07_95W3 | 09/05/2025 | 10/10/2025 | 25 | 17 | 8 |  |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LYNN | 441932 | 01902 | 8.41 | Solar | 05_01_304W1 | 08/11/2022 | 09/01/2022 | 15 | 13 | 2 | 09/02/2022 | 09/02/2022 | 14 | 0 | 14 | 10/05/2022 | 10/19/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 10/19/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 5/16/2024 | N | EXP | 365 | 04/20/2023 | 05/16/2023 | 27 | 0 | 27 |  |  | 5/19/2023 | Connected |  | N
National Grid | NEW SALEM | 606804 | 01355 | 3.8 | Solar | 05_07_5W4 | 04/25/2024 | 04/29/2024 | 1 | 0 | 1 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 | 04/25/2024 | 5/14/2025 | Y | EXP | 365 | 06/13/2024 | 07/19/2024 | 37 | 0 | 37 |  |  | 7/29/2024 | Connected |  | N
National Grid | PEMBROKE | 682311 | 02359 | 5.76 | Solar | 05_12_1J901 | 04/02/2025 | 04/24/2025 | 2 | 0 | 2 | 04/29/2025 | 04/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2025 | 04/02/2025 | 5/29/2026 | Y | EXP | 365 | 11/19/2025 | 12/02/2025 | 14 | 0 | 14 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 178435 | 01519 | 636 | Solar | 05_09_705W2 | 03/05/2018 | 03/05/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 734346 | 02368 | 13.3 | Solar | 05_07_95W3 | 11/21/2025 | 11/30/2025 | 4 | 1 | 3 | 12/01/2025 | 12/01/2025 | 83 | 25 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 444127 | 01902 | 0 | Solar | 05_01_304W1 | 07/14/2022 | 07/15/2022 | 1 | 1 | 0 | 07/18/2022 | 07/18/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 |  | 8/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2023 | Connected |  | N
National Grid | NEW SALEM | 621041 | 01355 | 7.6 | Solar | 05_07_5W4 | 06/27/2024 | 07/10/2024 | 3 | 0 | 3 | 07/11/2024 | 07/11/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 06/27/2024 | 8/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N
National Grid | HANSON | 683766 | 02341 | 7.6 | Solar | 05_12_1J901 | 04/08/2025 | 04/25/2025 | 13 | 11 | 2 | 08/11/2025 | 08/11/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 186988 | 01519 | 6 | Solar | 05_09_705W2 | 06/20/2018 | 06/20/2018 | 4 | 0 | 4 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2018 | 06/20/2018 | 8/27/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2019 | Connected |  | N
National Grid | RANDOLPH | 740992 | 02368 | 15.2 | Solar | 05_07_95W3 | 12/17/2025 | 01/06/2026 | 12 | 7 | 5 | 01/07/2026 | 01/07/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 445236 | 01902 | 15.2 | Solar | 05_01_304W1 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 |  | 9/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2023 | Connected |  | N
National Grid | ORANGE | 623067 | 01364 | 5.76 | Solar | 05_07_5W4 | 07/08/2024 | 08/02/2024 | 16 | 14 | 2 | 08/05/2024 | 08/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/08/2024 | 8/22/2025 | Y | EXP | 365 | 12/03/2024 | 03/06/2025 | 92 | 0 | 92 |  |  | 3/14/2025 | Connected |  | N
National Grid | PEMBROKE | 190057 | 02359 | 9 | Solar | 05_12_1J904 | 07/17/2018 | 10/17/2018 | 6 | 0 | 6 | 10/18/2018 | 10/18/2018 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 189146 | 01519 | 990 | Solar | 05_09_705W2 | 06/28/2018 | 06/28/2018 | 12 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2018 | 09/21/2018 | 46 | 0 | 46 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 742324 | 02368 | 5.76 | Solar | 05_07_95W3 | 12/26/2025 | 12/31/2025 | 3 | 0 | 3 | 01/02/2026 | 01/02/2026 | 17 | 6 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 447696 | 01902 | 9.86 | Solar | 05_01_304W1 | 08/05/2022 | 08/09/2022 | 2 | 0 | 2 | 08/10/2022 | 08/10/2022 | 49 | 26 | 23 | 01/06/2023 | 01/11/2023 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 01/11/2023 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 1/11/2023 |  | 1/13/2024 | N | EXP | 365 | 04/08/2023 | 04/21/2023 | 14 | 0 | 14 |  |  | 4/25/2023 | Connected |  | N
National Grid | ORANGE | 647448 | 01364 | 6.4 | Solar | 05_07_5W4 | 10/16/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 63 | 52 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 10/16/2024 | 3/7/2026 | Y | EXP | 365 | 06/27/2025 | 06/26/2025 | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | HANOVER | 622616 | 02339 | 5.76 | Solar | 05_12_1J904 | 07/04/2024 | 07/23/2024 | 5 | 0 | 5 | 07/24/2024 | 07/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 12/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 189259 | 01527 | 1518 | Solar | 05_09_705W2 | 07/11/2018 | 08/23/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2018 | 08/24/2018 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 260959 | 02368 | 0 | Solar | 05_07_95W3 | 10/23/2019 | 10/23/2019 | 0 | 0 | 0 | 10/24/2019 | 10/24/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2019 | 10/23/2019 | 7/8/2020 | Y | EXP | 365 | 01/31/2020 | 02/19/2020 | 19 | 0 | 19 |  |  | 6/15/2020 | Connected |  | N
National Grid | LYNN | 482228 | 01902 | 20 | Solar | 05_01_304W1 | 12/02/2022 | 12/13/2022 | 8 | 7 | 1 | 12/14/2022 | 12/14/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2023 |  | 1/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2023 | Connected |  | N
National Grid | ORANGE | 652359 | 01364 | 7.6 | Solar | 05_07_5W4 | 11/14/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/14/2024 | 2/14/2026 | Y | EXP | 365 | 05/21/2025 | 11/12/2025 | 176 | 0 | 176 |  |  | 11/13/2025 | Connected |  | N
National Grid | HANSON | 736451 | 02341 | 11.78 | Solar | 05_12_21J21 | 11/25/2025 | 12/01/2025 | 4 | 2 | 2 | 12/18/2025 | 12/18/2025 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 | 11/25/2025 | 2/18/2027 | Y | EXP | 365 | 03/18/2026 |  | 15 | 0 | 15 |  |  |  | Construction |  | N
National Grid | MILLBURY | 196214 | 01527 | 5 | Solar | 05_09_705W2 | 09/18/2018 | 10/16/2018 | 14 | 8 | 6 | 10/17/2018 | 10/17/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  | 11/14/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2019 | Connected |  | N
National Grid | RANDOLPH | 295316 | 02368 | 7.6 | Solar | 05_07_95W3 | 06/08/2020 | 06/10/2020 | 1 | 0 | 1 | 06/11/2020 | 06/11/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 5/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2020 | Connected |  | N
National Grid | LYNN | 533787 | 01902 | 15 | Solar | 05_01_304W1 | 06/15/2023 | 06/21/2023 | 4 | 2 | 2 | 06/22/2023 | 06/22/2023 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 12/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2024 | Connected |  | N
National Grid | ORANGE | 654215 | 01364 | 3.8 | Solar | 05_07_5W4 | 11/14/2024 | 12/09/2024 | 5 | 0 | 5 | 12/10/2024 | 12/10/2024 | 39 | 15 | 24 | 02/18/2025 | 03/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 03/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 3/26/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 347227 | 02359 | 5.76 | Solar | 05_12_21J21 | 04/22/2021 | 04/30/2021 | 5 | 3 | 2 | 05/03/2021 | 05/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 7/31/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | Connected |  | N
National Grid | GRAFTON | 238155 | 01519 | 25 | Solar | 05_09_705W2 | 06/18/2019 | 07/10/2019 | 15 | 15 | 0 | 07/11/2019 | 07/11/2019 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2019 | 06/18/2019 | 9/1/2020 | Y | EXP | 365 | 03/19/2020 | 06/15/2020 | 88 | 0 | 88 |  |  | 6/23/2020 | Connected |  | N
National Grid | RANDOLPH | 375893 | 02368 | 7.6 | Solar | 05_07_95W3 | 08/13/2021 | 09/14/2021 | 21 | 21 | 0 | 09/15/2021 | 09/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2021 |  | 12/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2022 | Connected |  | N
National Grid | LYNN | 562326 | 01902 | 10 | Solar | 05_01_304W1 | 11/01/2023 | 11/02/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 52 | 28 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 675924 | 01364 | 3.8 | Solar | 05_07_5W4 | 03/05/2025 | 03/21/2025 | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANSON | 424060 | 02341 | 4.06 | Solar | 05_12_21J21 | 05/04/2022 | 05/09/2022 | 3 | 2 | 1 | 05/10/2022 | 05/10/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 |  | 6/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2022 | Connected |  | N
National Grid | GRAFTON | 238143 | 01519 | 25 | Solar | 05_09_705W2 | 06/18/2019 | 07/10/2019 | 15 | 15 | 0 | 07/11/2019 | 07/11/2019 | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2019 |  | 8/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 434010 | 02368 | 0 | Battery Add-On | 05_07_95W3 | 08/08/2022 | 08/17/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2022 | 09/15/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 586889 | 01907 | 15.2 | Solar | 05_01_304W1 | 02/02/2024 | 02/16/2024 | 11 | 10 | 1 | 02/20/2024 | 02/20/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 |  | 3/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 688539 | 01364 | 5.76 | Solar | 05_07_5W4 | 05/01/2025 | 06/03/2025 | 1 | 0 | 1 | 06/04/2025 | 06/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 | 05/01/2025 | 8/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 640666 | 02339 | 3.8 | Solar | 05_12_21J21 | 09/16/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  | 12/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | GRAFTON | 255796 | 01519 | 10 | Solar | 05_09_705W2 | 10/10/2019 | 10/14/2019 | 1 | 0 | 1 | 10/15/2019 | 10/15/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 | 10/10/2019 | 10/12/2020 | Y | EXP | 365 | 03/07/2020 | 06/16/2020 | 101 | 0 | 101 |  |  | 6/18/2020 | Connected |  | N
National Grid | RANDOLPH | 497568 | 02368 | 17.28 | Solar | 05_07_95W3 | 02/14/2023 | 03/03/2023 | 12 | 10 | 2 | 03/06/2023 | 03/06/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2023 |  | 4/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 594840 | 01907 | 10 | Solar | 05_01_304W1 | 03/06/2024 | 03/11/2024 | 3 | 0 | 3 | 03/12/2024 | 03/12/2024 | 42 | 35 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 6/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2024 | Connected |  | N
National Grid | ORANGE | 692971 | 01364 | 3.8 | Solar | 05_07_5W4 | 05/23/2025 | 07/03/2025 | 9 | 7 | 2 | 07/25/2025 | 07/25/2025 | 47 | 25 | 22 | 10/14/2025 | 10/28/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 10/28/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 10/31/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 658658 | 02359 | 7.6 | Solar | 05_12_21J21 | 12/05/2024 | 12/19/2024 | 5 | 0 | 5 | 12/20/2024 | 12/20/2024 | 141 | 118 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 290751 | 01519 | 0 | Other | 05_09_705W2 | 08/17/2020 | 09/21/2020 | 23 | 20 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/13/2020 | 15 | 1 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 523276 | 02368 | 6.8 | Solar | 05_07_95W3 | 06/05/2023 | 06/06/2023 | 1 | 0 | 1 | 06/07/2023 | 06/07/2023 | 24 | 5 | 19 | 11/24/2023 | 01/02/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 01/02/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/14/2023 |  | 1/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2024 | Connected |  | N
National Grid | LYNN | 609002 | 01902 | 34.5 | Solar | 05_01_304W1 | 05/06/2024 | 05/24/2024 | 15 | 14 | 1 | 05/28/2024 | 05/28/2024 | 30 | 20 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2024 |  | 7/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2024 | Connected |  | N
National Grid | ORANGE | 695431 | 01364 | 7.6 | Solar | 05_07_5W4 | 06/03/2025 | 07/08/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANSON | 663402 | 02341 | 3.8 | Solar | 05_12_21J21 | 01/06/2025 | 01/28/2025 | 1 | 0 | 1 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 01/06/2025 | 3/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | GRAFTON | 344387 | 01519 | 9.6 | Solar | 05_09_705W2 | 03/01/2021 | 03/08/2021 | 4 | 4 | 0 | 03/09/2021 | 03/09/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 |  | 10/28/2022 | N | EXP | 555 |  |  | 0 | 0 | 0 |  |  | 10/26/2022 | Connected |  | N
National Grid | RANDOLPH | 597316 | 02368 | 6 | Solar | 05_07_95W3 | 04/04/2024 | 04/22/2024 | 12 | 11 | 1 | 04/23/2024 | 04/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 |  | 6/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | LYNN | 613635 | 01902 | 10 | Solar | 05_01_304W1 | 05/28/2024 | 07/31/2024 | 1 | 0 | 1 | 08/01/2024 | 08/01/2024 | 116 | 25 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 696439 | 01364 | 10.64 | Solar | 05_07_5W4 | 06/05/2025 | 07/08/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 45 | 39 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | HANOVER | 698521 | 02339 | 7.6 | Solar | 05_12_21J21 | 06/16/2025 | 07/02/2025 | 4 | 0 | 4 | 07/16/2025 | 07/16/2025 | 74 | 57 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2026 | Connected |  | N
National Grid | MILLBURY | 545906 | 01527 | 10 | Solar | 05_09_705W2 | 08/08/2023 | 08/16/2023 | 6 | 3 | 3 | 08/17/2023 | 08/17/2023 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 9/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2023 | Connected |  | N
National Grid | RANDOLPH | 606471 | 02368 | 7.6 | Solar | 05_07_95W3 | 04/24/2024 | 07/05/2024 | 43 | 43 | 0 | 07/08/2024 | 07/08/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 04/24/2024 | 11/30/2025 | Y | EXP | 365 | 10/11/2024 | 10/31/2024 | 21 | 0 | 21 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 648662 | 01902 | 9.92 | Solar | 05_01_304W1 | 10/22/2024 | 12/04/2024 | 17 | 15 | 2 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | ORANGE | 705802 | 01364 | 3.8 | Solar | 05_07_5W4 | 07/18/2025 | 09/11/2025 | 2 | 0 | 2 | 09/12/2025 | 09/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 704066 | 02341 | 5.76 | Solar | 05_12_21J21 | 07/11/2025 | 07/25/2025 | 3 | 0 | 3 | 08/04/2025 | 08/04/2025 | 50 | 32 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 553560 | 01519 | 13.8 | Solar | 05_09_705W2 | 09/21/2023 | 09/25/2023 | 2 | 0 | 2 | 09/26/2023 | 09/26/2023 | 102 | 50 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 642934 | 02368 | 11.5 | Solar | 05_07_95W3 | 09/27/2024 | 10/18/2024 | 7 | 4 | 3 | 10/21/2024 | 10/21/2024 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2025 | Connected |  | N
National Grid | LYNN | 656253 | 01902 | 7.6 | Solar | 05_01_304W1 | 11/22/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/22/2024 | 2/14/2026 | Y | EXP | 365 | 10/04/2025 | 12/18/2025 | 76 | 0 | 76 |  |  | 1/21/2026 | Connected |  | N
National Grid | NEW SALEM | 760107 | 01355 | 7.6 | Solar | 05_07_60J1 | 03/31/2026 | 04/01/2026 | 1 | 0 | 1 | 04/02/2026 | 04/02/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PEMBROKE | 721276 | 02359 | 5.12 | Solar | 05_12_21J21 | 09/25/2025 | 10/10/2025 | 3 | 0 | 3 | 10/28/2025 | 10/28/2025 | 84 | 75 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 561338 | 01519 | 2.9 | Solar | 05_09_705W2 | 10/13/2023 | 10/17/2023 | 2 | 0 | 2 | 10/18/2023 | 10/18/2023 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | RANDOLPH | 648548 | 02368 | 10 | Solar | 05_07_95W3 | 11/01/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 658212 | 01902 | 6.84 | Solar | 05_01_304W1 | 12/03/2024 | 12/30/2024 | 6 | 1 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | ORANGE | 174390 | 01364 | 230 | Solar | 05_07_60J1 | 06/08/2012 | 06/08/2012 | 5 | 0 | 5 | 06/19/2012 | 06/19/2012 | 370 | 0 | 370 | 01/15/2014 | 01/15/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/15/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANSON | 383844 | 02341 | 75 | Solar | 05_12_21J22 | 10/13/2021 | 11/17/2021 | 24 | 14 | 10 |  |  | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2022 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 569310 | 01519 | 22.995 | Solar | 05_09_705W2 | 11/07/2023 | 11/20/2023 | 8 | 5 | 3 | 11/21/2023 | 11/21/2023 | 33 | 11 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2024 | 11/07/2023 | 2/9/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 653647 | 02368 | 7.6 | Solar | 05_07_95W3 | 11/18/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | LYNN | 663779 | 01902 | 7.6 | Solar | 05_01_304W1 | 01/05/2025 | 01/17/2025 | 6 | 0 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | ORANGE | 322008 | 01364 | 9.84 | Solar | 05_07_60J1 | 10/27/2020 | 10/29/2020 | 1 | 0 | 1 | 10/30/2020 | 10/30/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 10/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2021 | Connected |  | N
National Grid | HANSON | 693732 | 02341 | 10 | Solar | 05_12_21J25 | 05/29/2025 | 06/23/2025 | 4 | 0 | 4 | 07/16/2025 | 07/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2025 | Connected |  | N
National Grid | GRAFTON | 588507 | 01519 | 10 | Solar | 05_09_705W2 | 02/19/2024 | 02/21/2024 | 2 | 0 | 2 | 02/22/2024 | 02/22/2024 | 10 | 6 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2024 | Connected |  | N
National Grid | RANDOLPH | 658119 | 02368 | 16.34 | Solar | 05_07_95W3 | 12/03/2024 | 12/11/2024 | 6 | 3 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | LYNN | 669841 | 01902 | 5.76 | Solar | 05_01_304W1 | 02/05/2025 | 03/18/2025 | 12 | 7 | 5 | 03/19/2025 | 03/19/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 4/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N
National Grid | ORANGE | 336920 | 01364 | 8.7 | Solar | 05_07_60J1 | 01/14/2021 | 01/15/2021 | 0 | 0 | 0 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 |  | 1/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N
National Grid | PEMBROKE | 683953 | 02359 | 340 | Solar | 05_12_21J27 | 05/07/2025 | 09/10/2025 | 85 | 75 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2025 | 10/15/2025 | 24 | 4 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | GRAFTON | 630170 | 01519 | 8 | Solar | 05_09_705W2 | 12/02/2024 | 01/21/2025 | 7 | 3 | 4 | 01/22/2025 | 01/22/2025 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 12/02/2024 | 5/8/2026 | Y | EXP | 365 | 08/20/2025 | 09/10/2025 | 22 | 0 | 22 |  |  | 10/21/2025 | Connected |  | Y
National Grid | RANDOLPH | 478187 | 02368 | 120 | Solar | 05_07_95W4 | 12/14/2022 | 03/31/2023 | 72 | 62 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/10/2027 | N | STD | 448 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LYNN | 691717 | 01902 | 13.975 | Solar | 05_01_304W1 | 05/14/2025 | 06/25/2025 | 8 | 5 | 3 | 06/26/2025 | 06/26/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 | 05/14/2025 | 7/25/2026 | Y | EXP | 365 | 10/29/2025 | 11/21/2025 | 24 | 0 | 24 |  |  | 12/1/2025 | Connected |  | N
National Grid | ORANGE | 336885 | 01364 | 8.7 | Solar | 05_07_60J1 | 01/14/2021 | 01/15/2021 | 0 | 0 | 0 | 01/19/2021 | 01/19/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2021 |  | 1/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N
National Grid | HANSON | 752641 | 02341 | 60 | Solar | 05_12_21J27 | 02/27/2026 |  | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | GRAFTON | 637215 | 01519 | 5.76 | Solar | 05_09_705W2 | 09/03/2024 | 09/23/2024 | 3 | 0 | 3 | 09/24/2024 | 09/24/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 09/03/2024 | 11/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2025 | Connected |  | N
National Grid | ABINGTON | 478163 | 02351 | 120 | Solar | 05_07_95W4 | 12/14/2022 | 03/31/2023 | 72 | 62 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/10/2027 | N | STD | 448 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LYNN | 730026 | 01902 | 15.2 | Solar | 05_01_304W1 | 10/30/2025 | 11/12/2025 | 7 | 3 | 4 | 11/13/2025 | 11/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 1/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2026 | Connected |  | N
National Grid | ORANGE | 368498 | 01364 | 7.6 | Solar | 05_07_60J1 | 07/08/2021 | 08/24/2021 | 32 | 31 | 1 | 08/25/2021 | 08/25/2021 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 |  | 1/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2022 | Connected |  | N
National Grid | HANOVER | 174585 | 02339 | 95 | Solar | 05_12_21J27 | 08/30/2011 | 08/30/2011 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2011 |  | 7/10/2012 | N | EXP | 281 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 7/10/2012 | Connected |  | N
National Grid | GRAFTON | 651608 | 01519 | 7.6 | Solar | 05_09_705W2 | 11/05/2024 | 01/10/2025 | 15 | 10 | 5 | 01/13/2025 | 01/13/2025 | 37 | 16 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | ABINGTON | 689008 | 02351 | 20 | Solar | 05_07_95W4 | 06/02/2025 | 06/12/2025 | 8 | 4 | 4 | 06/13/2025 | 06/13/2025 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2025 |  | 10/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 176286 | 01901 | 130 | Solar | 05_01_HT14 | 07/10/2015 | 07/10/2015 | 209 | 209 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/15/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 649092 | 01364 | 10 | Solar | 05_07_60J1 | 11/04/2024 | 11/20/2024 | 3 | 0 | 3 | 11/21/2024 | 11/21/2024 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 223576 | 02359 | 33.3 | Solar | 05_12_21J27 | 04/29/2019 |  | 283 | 51 | 232 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 665012 | 01527 | 7.6 | Solar | 05_09_705W2 | 01/10/2025 | 02/12/2025 | 18 | 13 | 5 | 02/13/2025 | 02/13/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2026 | Connected |  | N
National Grid | ABINGTON | 731449 | 02351 | 7.6 | Solar | 05_07_95W4 | 11/04/2025 | 11/05/2025 | 3 | 0 | 3 | 12/09/2025 | 12/09/2025 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 | 11/04/2025 | 2/5/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LYNN | 640228 | 01902 | 720 | Solar | 05_01_HT3 | 11/13/2024 | 03/10/2025 | 77 | 68 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/11/2025 | 05/06/2025 | 40 | 21 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ORANGE | 749114 | 01364 | 11.5 | Solar | 05_07_64J1 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HANOVER | 176054 | 02339 | 3 | Solar | 05_12_21J28 | 01/30/2015 | 01/30/2015 | 18 | 18 | 0 | 03/02/2015 | 03/02/2015 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2015 |  | 6/30/2015 | N | EXP | 75 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 670913 | 01519 | 10 | Solar | 05_09_705W2 | 04/03/2025 | 04/18/2025 | 11 | 6 | 5 | 04/22/2025 | 04/22/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 8/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2025 | Connected |  | Y
National Grid | ABINGTON | 176012 | 02351 | 6 | Solar | 05_07_95W4 | 01/23/2015 | 01/23/2015 | 6 | 2 | 4 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2015 |  | 6/30/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 9/24/2015 | Connected |  | N
National Grid | LYNN | 177804 | 01905 | 584 | Solar | 05_01_HT3 | 10/11/2017 | 10/11/2017 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 | 11/28/2017 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/17/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 176418 | 01364 | 86.4 | Solar | 05_07_64J1 | 12/03/2015 | 12/03/2015 | 3 | 3 | 0 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2015 |  | 12/8/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 1/3/2017 | 1/3/2017 | 1/3/2017 | Connected |  | N
National Grid | ROCKLAND | 649089 | 02370 | 7.475 | Solar | 05_12_21J28 | 10/23/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 37 | 21 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 10/23/2024 | 2/6/2026 | Y | EXP | 365 | 03/15/2025 | 03/25/2025 | 11 | 0 | 11 |  |  | 5/28/2025 | Connected |  | N
National Grid | GRAFTON | 538142 | 01519 | 0 | Other | 05_09_705W3 | 07/28/2023 | 10/05/2023 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2023 | 11/03/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ABINGTON | 176310 | 02351 | 10 | Solar | 05_07_95W4 | 02/23/2015 | 02/23/2015 | 6 | 0 | 6 | 03/04/2015 | 03/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2015 |  | 7/31/2015 | N | EXP | 148 |  |  | 0 | 0 | 0 | 9/1/2016 | 9/1/2016 | 9/7/2016 | Connected |  | N
National Grid | LYNN | 176805 | 01905 | 225 | Solar | 05_05_115W43 | 04/27/2016 | 04/27/2016 | 19 | 19 | 0 | 05/24/2016 | 05/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 |  | 3/15/2017 | N | EXP | 208 |  |  | 0 | 0 | 0 | 8/22/2017 | 8/22/2017 | 8/24/2017 | Connected |  | N
National Grid | ORANGE | 177292 | 01364 | 20 | Solar | 05_07_64J1 | 08/24/2016 | 08/24/2016 | 2 | 2 | 0 | 08/29/2016 | 08/29/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 745655 | 02370 | 15.2 | Solar | 05_12_21J28 | 01/15/2026 |  | 51 | 35 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 692494 | 01519 | 11.4 | Solar | 05_09_705W3 | 05/21/2025 | 09/22/2025 | 78 | 75 | 3 | 09/23/2025 | 09/23/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 | 05/21/2025 | 10/14/2026 | Y | EXP | 365 | 01/22/2026 |  | 70 | 0 | 70 |  |  |  | Construction |  | N
National Grid | ABINGTON | 176762 | 02351 | 5 | Solar | 05_07_95W4 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 3/1/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 7/27/2016 | 7/27/2016 | 8/1/2016 | Connected |  | N
National Grid | LYNN | 199674 | 01905 | 133.2 | Solar | 05_05_115W43 | 11/06/2018 | 11/26/2018 | 10 | 2 | 8 | 11/27/2018 | 11/27/2018 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 |  | 12/31/2020 | N | EXP | 525 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEW SALEM | 177873 | 01355 | 5 | Solar | 05_07_64J1 | 08/14/2017 | 08/14/2017 | 1 | 0 | 1 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 | 08/14/2017 | 8/20/2018 | Y | EXP | 368 | 10/04/2017 | 10/23/2017 | 12 | 0 | 12 | 2/20/2018 | 2/20/2018 | 2/27/2018 | Connected |  | N
National Grid | HANOVER | 175306 | 02339 | 232 | Solar | 05_12_21J29 | 06/25/2014 | 06/25/2014 | 6 | 0 | 6 | 07/07/2014 | 07/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2014 |  | 10/31/2014 | N | EXP | 95 |  |  | 0 | 0 | 0 | 7/28/2014 | 7/28/2014 | 12/31/2014 | Connected |  | N
National Grid | WORCESTER | 702549 | 01602 | 9.5 | Solar | 05_09_705W3 | 07/07/2025 | 07/24/2025 | 2 | 0 | 2 | 08/01/2025 | 08/01/2025 | 4 | 0 | 4 | 09/02/2025 | 08/29/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 | 07/07/2025 | 10/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y
National Grid | ABINGTON | 177828 | 02351 | 280 | Solar | 05_07_95W4 | 08/04/2017 | 08/04/2017 | 7 | 7 | 0 | 08/15/2017 | 08/15/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2017 |  | 8/9/2018 | N | EXP | 338 |  |  | 0 | 0 | 0 | 12/19/2017 | 12/19/2017 | 12/27/2017 | Connected |  | N
National Grid | LYNN | 337141 | 01905 | 497.5 | Solar | 05_05_115W43 | 05/14/2021 | 11/09/2021 | 123 | 110 | 13 |  |  | 50 | 27 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 281952 | 01364 | 8.12 | Solar | 05_07_65J1 | 03/02/2020 | 03/03/2020 | 0 | 0 | 0 | 03/04/2020 | 03/04/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2020 |  | 3/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2020 | Connected |  | N
National Grid | HANOVER | 177206 | 02339 | 133.2 | Solar | 05_12_21J29 | 02/01/2017 | 02/01/2017 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 731901 | 01604 | 19.1 | Solar | 05_09_705W3 | 11/06/2025 | 11/12/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 | 11/06/2025 | 1/22/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ABINGTON | 221137 | 02351 | 10 | Solar | 05_07_95W4 | 04/24/2019 | 05/06/2019 | 7 | 0 | 7 | 05/07/2019 | 05/07/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2019 | 04/24/2019 | 6/9/2020 | Y | EXP | 365 | 10/04/2019 | 10/14/2019 | 10 | 0 | 10 |  |  | 1/21/2020 | Connected |  | N
National Grid | LYNN | 504309 | 01902 | 7.6 | Solar | 05_05_115W43 | 06/01/2023 | 06/15/2023 | 11 | 10 | 1 | 06/16/2023 | 06/16/2023 | 102 | 84 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEW SALEM | 663732 | 01355 | 2.66 | Solar | 05_07_65J1 | 01/03/2025 | 01/15/2025 | 6 | 0 | 6 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | ROCKLAND | 204170 | 02370 | 139.9 | Solar | 05_12_21J29 | 12/18/2018 | 01/09/2019 | 13 | 8 | 5 | 01/10/2019 | 01/10/2019 | 19 | 0 | 19 | 03/11/2019 | 03/21/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 03/21/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 731745 | 01604 | 0 | Other | 05_09_705W3 | 11/05/2025 | 11/09/2025 | 4 | 0 | 4 | 12/09/2025 | 12/09/2025 | 78 | 63 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ROCKLAND | 348314 | 02370 | 366.6 | Solar | 05_07_95W4 | 05/14/2021 | 07/30/2021 | 53 | 40 | 13 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 593434 | 01905 | 7.6 | Solar | 05_05_115W43 | 03/29/2024 | 04/04/2024 | 4 | 0 | 4 | 04/05/2024 | 04/05/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 | 03/29/2024 | 5/16/2025 | Y | EXP | 365 | 07/17/2024 | 08/28/2024 | 43 | 0 | 43 |  |  | 11/9/2024 | Connected |  | N
National Grid | ERVING | 726671 | 01344 | 7.04 | Solar | 05_07_65J1 | 10/17/2025 | 10/30/2025 | 2 | 1 | 1 | 10/31/2025 | 10/31/2025 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 266087 | 02370 | 6 | Solar | 05_12_21J30 | 10/12/2020 | 10/19/2020 | 5 | 5 | 0 | 10/20/2020 | 10/20/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2020 |  | 10/18/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 731618 | 02721 | 11.4 | Solar | 05_09_705W3 | 11/12/2025 | 12/22/2025 | 2 | 0 | 2 | 01/06/2026 | 01/06/2026 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | ABINGTON | 424551 | 02351 | 20 | Solar | 05_07_95W4 | 05/20/2022 | 06/21/2022 | 21 | 20 | 1 | 06/22/2022 | 06/22/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 9/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2022 | Connected |  | N
National Grid | LYNN | 174462 | 01902 | 548 | Solar | 05_09_S100 | 08/25/2011 | 08/25/2011 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/15/2011 | 11/14/2011 | 41 | 0 | 41 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2012 |  | 6/30/2014 | N | STD | 811 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 12/23/2013 | Connected |  | N
National Grid | ORANGE | 545216 | 01364 | 15.2 | Solar | 05_07_67J1 | 08/01/2023 | 08/02/2023 | 1 | 0 | 1 | 08/03/2023 | 08/03/2023 | 138 | 109 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2024 | Connected |  | N
National Grid | ROCKLAND | 269148 | 02370 | 7.6 | Solar | 05_12_21J30 | 03/16/2020 | 04/01/2020 | 11 | 11 | 0 | 04/02/2020 | 04/02/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2020 |  | 4/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 741209 | 02723 | 999 | Solar | 05_09_705W3 | 01/13/2026 | 02/04/2026 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2026 | 03/05/2026 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ABINGTON | 503019 | 02351 | 16 | Solar | 05_07_95W4 | 03/17/2023 | 03/21/2023 | 2 | 0 | 2 | 03/22/2023 | 03/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 |  | 6/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2023 | Connected |  | N
National Grid | LYNN | 174724 | 01905 | 3500 | Natural Gas | 05_09_S100 | 03/23/2010 | 03/23/2010 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 03/23/2010 | 12/31/2012 | Y | STD | 19 |  |  | 0 | 0 | 0 | 8/28/2013 | 8/28/2013 | 12/16/2013 | Connected |  | N
National Grid | ORANGE | 606410 | 01364 | 0 | Battery Add-On | 05_07_67J1 | 04/24/2024 |  | 9 | 7 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 346631 | 02061 | 7.6 | Solar | 05_12_21J30 | 03/31/2021 | 04/06/2021 | 3 | 0 | 3 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2021 |  | 6/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 745794 | 02721 | 11.5 | Solar | 05_09_705W3 | 01/16/2026 | 01/22/2026 | 3 | 0 | 3 | 01/23/2026 | 01/23/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SCITUATE | 544647 | 02066 | 16 | Solar | 05_07_95W4 | 07/31/2023 | 08/07/2023 | 5 | 3 | 2 | 08/08/2023 | 08/08/2023 | 124 | 54 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 174805 | 01905 | 300 | Solar | 05_12_11J3 | 01/23/2013 | 01/23/2013 | 6 | 0 | 6 | 02/01/2013 | 02/01/2013 | 346 | 0 | 346 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2013 |  | 6/28/2013 | N | EXP | 87 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARWICK | 685332 | 01378 | 5.76 | Solar | 05_07_67J1 | 04/15/2025 | 05/02/2025 | 27 | 20 | 7 | 07/15/2025 | 07/15/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 | 04/15/2025 | 9/2/2026 | Y | EXP | 365 | 11/22/2025 | 01/06/2026 | 46 | 0 | 46 |  |  | 1/8/2026 | Connected |  | N
National Grid | ROCKLAND | 653772 | 02370 | 20 | Solar | 05_12_21J30 | 11/12/2024 | 11/19/2024 | 5 | 3 | 2 | 11/20/2024 | 11/20/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 747866 | 02721 | 17.6 | Solar | 05_09_705W3 | 01/28/2026 | 02/18/2026 | 14 | 13 | 1 | 02/19/2026 | 02/19/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2026 |  | 3/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | COHASSET | 602975 | 02025 | 7.6 | Solar | 05_07_95W4 | 04/10/2024 | 04/23/2024 | 2 | 0 | 2 | 04/24/2024 | 04/24/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2025 | Connected |  | N
National Grid | LYNN | 175175 | 01905 | 200 | Solar | 05_12_11J3 | 11/27/2012 | 11/27/2012 | 8 | 0 | 8 | 12/10/2012 | 12/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2013 |  | 2/28/2013 | N | EXP | 6 |  |  | 0 | 0 | 0 | 6/18/2013 | 6/18/2013 | 10/9/2013 | Connected |  | N
National Grid | ERVING | 736133 | 01344 | 5.76 | Solar | 05_07_69J1 | 11/24/2025 | 11/25/2025 | 3 | 0 | 3 | 12/30/2025 | 12/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2026 | 11/24/2025 | 2/4/2027 | Y | EXP | 365 | 03/13/2026 |  | 20 | 0 | 20 |  |  |  | Construction |  | N
National Grid | ROCKLAND | 176503 | 02370 | 64.8 | Solar | 05_12_21J32 | 02/09/2016 | 02/09/2016 | 2 | 2 | 0 | 02/12/2016 | 02/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/15/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/13/2016 | 10/13/2016 | 10/19/2016 | Connected |  | N
National Grid | FALL RIVER | 174414 | 02721 | 500 | Solar | 05_09_705W3 | 06/22/2012 | 06/22/2012 | 6 | 0 | 6 | 07/05/2012 | 07/05/2012 | 370 | 0 | 370 | 09/27/2013 | 10/08/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 10/08/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 11/5/2013 |  | 12/30/2013 | N | EXP | 55 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 676721 | 02025 | 7.6 | Solar | 05_07_95W4 | 03/10/2025 | 03/22/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 03/10/2025 | 6/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2025 | Connected |  | N
National Grid | LYNN | 252575 | 01902 | 150 | Solar | 05_12_11J3 | 09/06/2019 | 09/10/2019 | 0 | 0 | 0 | 09/11/2019 | 09/11/2019 | 12 | 1 | 11 | 10/22/2019 | 11/25/2019 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 11/25/2019 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 12/10/2019 | 09/06/2019 | 9/29/2020 | Y | EXP | 365 | 07/29/2020 | 08/25/2020 | 27 | 0 | 27 |  |  | 9/28/2020 | Connected |  | N
National Grid | ORANGE | 748652 | 01364 | 11.5 | Solar | 05_07_69J1 | 02/02/2026 | 02/16/2026 | 3 | 0 | 3 | 03/16/2026 | 03/16/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HANOVER | 196937 | 02339 | 3.84 | Solar | 05_12_21J32 | 11/05/2018 | 11/08/2018 | 3 | 2 | 1 | 11/09/2018 | 11/09/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 174976 | 01060 | 557 | Solar | 05_09_705W3 | 09/20/2011 | 09/20/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2011 | 01/03/2012 | 58 | 0 | 58 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2012 |  | 11/30/2012 | N | STD | 100 | 06/04/2013 | 07/25/2013 | 35 | 0 | 35 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 720878 | 02351 | 15.356 | Solar | 05_07_95W4 | 09/22/2025 | 09/29/2025 | 5 | 0 | 5 | 09/30/2025 | 09/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 1/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2026 | Connected |  | N
National Grid | LYNN | 419319 | 01902 | 240 | Solar | 05_12_11J3 | 05/26/2022 | 06/13/2022 | 11 | 4 | 7 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2022 | 05/26/2022 | 12/21/2024 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2024 | Connected |  | N
National Grid | ORANGE | 176650 | 01364 | 3 | Solar | 05_07_69J1 | 02/17/2016 | 02/17/2016 | 2 | 2 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2016 | 02/17/2016 | 2/23/2017 | Y | EXP | 331 | 08/04/2016 | 08/30/2016 | 18 | 0 | 18 | 12/28/2016 | 12/28/2016 | 1/3/2017 | Connected |  | N
National Grid | HANOVER | 606809 | 02339 | 10 | Solar | 05_12_21J32 | 04/25/2024 |  | 26 | 25 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 175349 | 01060 | 69.6 | Solar | 05_09_705W3 | 07/09/2014 | 07/09/2014 | 1 | 0 | 1 | 07/10/2014 | 07/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2014 |  | 11/28/2014 | N | EXP | 123 |  |  | 0 | 0 | 0 | 7/28/2014 | 7/28/2014 | 12/16/2016 | Connected |  | N
National Grid | ABINGTON | 723938 | 02351 | 11.4 | Solar | 05_07_95W5 | 10/07/2025 | 10/13/2025 | 2 | 0 | 2 | 10/29/2025 | 10/29/2025 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 | 10/07/2025 | 1/12/2027 | Y | EXP | 365 | 02/06/2026 |  | 55 | 0 | 55 |  |  |  | Construction |  | N
National Grid | LYNN | 457068 | 01902 | 15.2 | Solar | 05_12_11J3 | 09/07/2022 | 09/09/2022 | 2 | 0 | 2 | 09/12/2022 | 09/12/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 |  | 10/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2022 | Connected |  | N
National Grid | ORANGE | 191411 | 01364 | 7.6 | Solar | 05_07_69J1 | 07/20/2018 | 10/05/2018 | 278 | 0 | 278 | 10/11/2018 | 10/11/2018 | 48 | 40 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 621560 | 02339 | 10 | Solar | 05_12_21J32 | 07/01/2024 | 07/09/2024 | 1 | 0 | 1 | 07/10/2024 | 07/10/2024 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2024 | Connected |  | N
National Grid | MEDFORD | 175976 | 02155 | 920 | Solar | 05_09_705W3 | 01/22/2015 | 01/22/2015 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2015 | 03/16/2015 | 26 | 0 | 26 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2015 | 01/22/2015 | 12/31/2016 | Y | STD | 515 | 03/16/2017 | 05/23/2017 | 47 | 0 | 47 | 5/30/2017 | 5/30/2017 | 5/30/2017 | Connected |  | N
National Grid | ABINGTON | 749612 | 02351 | 5.76 | Solar | 05_07_95W5 | 02/05/2026 | 03/10/2026 | 4 | 0 | 4 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 484436 | 01902 | 15.2 | Solar | 05_12_11J3 | 12/09/2022 | 12/15/2022 | 5 | 4 | 1 | 12/16/2022 | 12/16/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2023 |  | 2/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2023 | Connected |  | N
National Grid | ORANGE | 203334 | 01364 | 3.8 | Solar | 05_07_69J1 | 12/19/2018 | 12/21/2018 | 1 | 0 | 1 | 12/24/2018 | 12/24/2018 | 314 | 0 | 314 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2019 |  | 12/19/2020 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 634661 | 02370 | 5.525 | Solar | 05_12_21J32 | 08/22/2024 | 08/30/2024 | 3 | 0 | 3 | 09/03/2024 | 09/03/2024 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 |  | 11/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2025 | Connected |  | Y
National Grid | MEDFORD | 176237 | 02155 | 1000 | Solar | 05_09_705W3 | 02/17/2015 | 02/17/2015 | 9 | 5 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/01/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 754686 | 02302 | 7.6 | Solar | 05_07_95W5 | 03/05/2026 | 03/09/2026 | 1 | 0 | 1 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 688885 | 01905 | 3.8 | Solar | 05_12_11J3 | 05/01/2025 | 06/17/2025 | 4 | 0 | 4 | 06/18/2025 | 06/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 | 05/01/2025 | 7/25/2026 | Y | EXP | 365 | 11/15/2025 | 11/14/2025 | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | ORANGE | 369999 | 01364 | 7.6 | Solar | 05_07_69J1 | 07/15/2021 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKLAND | 659725 | 02370 | 8.7 | Solar | 05_12_21J32 | 12/10/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 98 | 75 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 176267 | 02155 | 1000 | Solar | 05_09_705W3 | 02/17/2015 | 02/17/2015 | 9 | 5 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/01/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174826 | 02302 | 30 | Solar | 05_07_95W5 | 08/22/2011 | 08/22/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2011 |  | 2/10/2012 | N | EXP | 81 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 2/10/2012 | Connected |  | N
National Grid | LYNN | 176016 | 01905 | 1000 | Solar | 05_01_601W1 | 01/23/2015 | 01/23/2015 | 26 | 23 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/03/2015 | 22 | 0 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 471403 | 01364 | 6.144 | Solar | 05_07_69J1 | 01/11/2023 | 01/13/2023 | 2 | 0 | 2 | 01/17/2023 | 01/17/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKLAND | 691724 | 02370 | 5.76 | Solar | 05_12_21J32 | 05/22/2025 | 05/29/2025 | 2 | 0 | 2 | 06/23/2025 | 06/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | MEDFORD | 176492 | 02155 | 80 | Solar | 05_09_705W3 | 12/09/2015 | 12/09/2015 | 5 | 5 | 0 | 12/17/2015 | 12/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2016 |  | 12/15/2016 | N | EXP | 331 |  |  | 0 | 0 | 0 | 12/13/2016 | 12/13/2016 | 12/29/2016 | Connected |  | N
National Grid | BROCKTON | 175327 | 02302 | 419 | Solar | 05_07_95W5 | 11/10/2014 | 11/10/2014 | 5 | 2 | 3 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2015 | 11/10/2014 | 4/15/2016 | Y | EXP | 457 | 01/30/2017 | 03/22/2017 | 36 | 0 | 36 | 2/4/2015 | 2/4/2015 | 3/30/2017 | Connected |  | N
National Grid | LYNN | 176015 | 01905 | 1000 | Solar | 05_01_601W1 | 01/23/2015 | 01/23/2015 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/03/2015 | 22 | 0 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 494808 | 01364 | 9.86 | Solar | 05_07_69J1 | 03/31/2023 | 04/03/2023 | 1 | 0 | 1 | 04/04/2023 | 04/04/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 701073 | 02339 | 16.32 | Solar | 05_12_21J32 | 06/25/2025 | 06/27/2025 | 2 | 0 | 2 | 06/30/2025 | 06/30/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | MEDFORD | 178086 | 02155 | 4995 | Solar | 05_09_705W3 | 05/08/2017 | 06/02/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2017 | 06/26/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 | 05/08/2017 | 10/27/2021 | Y | STD | 35 | 07/30/2021 | 09/24/2021 | 57 | 3 | 54 |  |  | 10/27/2021 | Connected |  | N
National Grid | BROCKTON | 184689 | 02302 | 990 | Solar | 05_07_95W5 | 05/16/2018 | 05/16/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2018 | 08/13/2018 | 34 | 15 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 176014 | 01905 | 1000 | Solar | 05_01_601W1 | 01/23/2015 | 01/23/2015 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/03/2015 | 22 | 0 | 22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 505549 | 01364 | 7.6 | Solar | 05_07_69J1 | 03/15/2023 | 03/20/2023 | 3 | 0 | 3 | 03/21/2023 | 03/21/2023 | 58 | 38 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2023 | 03/15/2023 | 9/16/2024 | Y | EXP | 365 | 02/02/2024 | 02/12/2024 | 11 | 0 | 11 |  |  | 5/30/2024 | Connected |  | N
National Grid | HANOVER | 567360 | 02339 | 0 | Other | 05_12_21J33 | 04/18/2024 | 02/28/2025 | 214 | 204 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2025 | 07/31/2025 | 105 | 86 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MEDFORD | 178085 | 02155 | 4995 | Solar | 05_09_705W3 | 05/08/2017 | 06/02/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2017 | 06/26/2017 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 | 05/08/2017 | 10/27/2021 | Y | STD | 77 | 07/30/2021 | 09/24/2021 | 57 | 3 | 54 |  |  | 10/27/2021 | Connected |  | N
National Grid | BROCKTON | 287429 | 02302 | 11.4 | Solar | 05_07_95W5 | 04/10/2020 | 04/29/2020 | 11 | 11 | 0 | 04/30/2020 | 04/30/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 | 04/10/2020 | 8/10/2021 | Y | EXP | 365 | 08/27/2020 | 09/12/2020 | 16 | 0 | 16 |  |  | 7/13/2021 | Connected |  | N
National Grid | LYNN | 638822 | 01905 | 7.6 | Solar | 05_01_601W1 | 09/12/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 09/12/2024 | 2/12/2026 | Y | EXP | 365 | 06/11/2025 | 07/14/2025 | 34 | 0 | 34 |  |  | 7/30/2025 | Connected |  | N
National Grid | ORANGE | 519664 | 01364 | 6 | Solar | 05_07_69J1 | 05/01/2023 | 05/02/2023 | 1 | 0 | 1 | 05/03/2023 | 05/03/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 595928 | 02339 | 3.8 | Solar | 05_12_21J33 | 03/25/2024 | 03/27/2024 | 2 | 1 | 1 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | MEDFORD | 178430 | 02155 | 636 | Solar | 05_09_705W3 | 03/05/2018 | 03/05/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 303247 | 02302 | 112.5 | Solar | 05_07_95W5 | 07/28/2020 | 08/12/2020 | 10 | 0 | 10 | 08/13/2020 | 08/13/2020 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 4/20/2025 | N | EXP | 850 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 650682 | 01905 | 5.76 | Solar | 05_01_601W1 | 11/11/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/11/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | ORANGE | 526991 | 01364 | 14.79 | Solar | 05_07_69J1 | 07/18/2023 | 08/08/2023 | 16 | 15 | 1 | 08/09/2023 | 08/09/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 07/18/2023 | 10/9/2024 | Y | EXP | 365 | 10/24/2023 | 10/23/2023 | 0 | 0 | 0 |  |  | 10/25/2023 | Connected |  | N
National Grid | HANOVER | 729408 | 02339 | 10 | Solar | 05_12_21J34 | 10/27/2025 | 10/28/2025 | 1 | 0 | 1 | 11/13/2025 | 11/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 10/27/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | GARDNER | 178406 | 01440 | 4990 | Solar | 05_09_705W3 | 04/02/2018 | 04/05/2018 | 3 | 2 | 1 |  |  | 39 | 23 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 303246 | 02302 | 62.5 | Solar | 05_07_95W5 | 07/28/2020 | 08/12/2020 | 10 | 0 | 10 | 08/13/2020 | 08/13/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2020 |  | 2/17/2025 | N | EXP | 750 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 193346 | 01905 | 2040 | Solar | 05_01_601W4 | 10/18/2018 |  | 17 | 16 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 527500 | 01364 | 10 | Solar | 05_07_69J1 | 08/03/2023 | 08/04/2023 | 1 | 0 | 1 | 08/07/2023 | 08/07/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 | 08/03/2023 | 9/7/2024 | Y | EXP | 365 | 09/26/2023 | 09/25/2023 | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | N
National Grid | NORWELL | 554220 | 02061 | 10 | Solar | 05_12_21J34 | 09/28/2023 | 10/05/2023 | 5 | 2 | 3 | 10/06/2023 | 10/06/2023 | 89 | 25 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 178604 | 01440 | 3000 | Solar | 05_09_705W3 | 04/09/2018 | 04/10/2018 | 20 | 20 | 0 |  |  | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 313773 | 02302 | 16 | Solar | 05_07_95W5 | 10/19/2020 | 01/05/2022 | 0 | 0 | 0 | 10/21/2020 | 10/21/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  | 1/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 714226 | 01905 | 60 | Solar | 05_05_28W42 | 08/23/2025 | 11/06/2025 | 50 | 41 | 9 | 11/07/2025 | 11/07/2025 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ORANGE | 530664 | 01364 | 6 | Solar | 05_07_69J1 | 06/09/2023 | 06/12/2023 | 1 | 0 | 1 | 06/13/2023 | 06/13/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  | 8/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 648683 | 02061 | 5.76 | Solar | 05_12_21J34 | 11/06/2024 | 11/20/2024 | 5 | 1 | 4 | 11/21/2024 | 11/21/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | Y
National Grid | GARDNER | 178667 | 01440 | 4990 | Solar | 05_09_705W3 | 03/16/2018 | 04/02/2018 | 10 | 10 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2018 | 05/30/2018 | 42 | 27 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 322067 | 02302 | 15.36 | Solar | 05_07_95W5 | 10/27/2020 | 10/29/2020 | 1 | 0 | 1 | 10/30/2020 | 10/30/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 10/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2021 | Connected |  | N
National Grid | LYNN | 211048 | 01905 | 492 | Solar | 05_05_28W42 | 04/17/2019 | 04/25/2019 | 5 | 0 | 5 | 04/26/2019 | 04/26/2019 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 535779 | 01364 | 8.12 | Solar | 05_07_69J1 | 09/29/2023 | 10/26/2023 | 18 | 16 | 2 | 10/27/2023 | 10/27/2023 | 82 | 28 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 661760 | 02339 | 7.6 | Solar | 05_12_21J34 | 12/19/2024 | 01/22/2025 | 8 | 3 | 5 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 184632 | 01535 | 990 | Solar | 05_09_705W3 | 05/10/2018 | 05/10/2018 | 111 | 0 | 111 |  |  | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 344715 | 02302 | 9.6 | Solar | 05_07_95W5 | 03/02/2021 | 03/08/2021 | 3 | 0 | 3 | 03/09/2021 | 03/09/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 |  | 8/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 476578 | 01902 | 180 | Solar | 05_05_28W42 | 11/10/2022 | 12/22/2022 | 28 | 18 | 10 | 12/23/2022 | 12/23/2022 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 567965 | 01364 | 6 | Solar | 05_07_69J1 | 11/10/2023 | 11/27/2023 | 10 | 4 | 6 | 11/28/2023 | 11/28/2023 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | HANOVER | 285404 | 02339 | 7.6 | Solar | 05_12_21J37 | 04/20/2020 | 04/27/2020 | 4 | 4 | 0 | 04/28/2020 | 04/28/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 | 04/20/2020 | 4/26/2021 | Y | EXP | 365 | 12/10/2020 | 02/15/2021 | 67 | 0 | 67 |  |  | 2/22/2021 | Connected |  | N
National Grid | GARDNER | 185922 | 01440 | 480 | Solar | 05_09_705W3 | 07/18/2018 | 07/20/2018 | 1 | 0 | 1 |  |  | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2018 |  | 8/9/2019 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2019 | Connected |  | N
National Grid | BROCKTON | 424728 | 02302 | 15.2 | Solar | 05_07_95W5 | 04/19/2022 | 04/26/2022 | 6 | 4 | 2 | 04/27/2022 | 04/27/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2022 |  | 6/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2022 | Connected |  | N
National Grid | LYNN | 647467 | 01902 | 5.76 | Solar | 49_56_33F1 | 10/21/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 10/21/2024 | 1/27/2026 | Y | EXP | 365 | 03/19/2025 | 05/15/2025 | 58 | 0 | 58 |  |  | 6/4/2025 | Connected |  | N
National Grid | ERVING | 570864 | 01344 | 7.6 | Solar | 05_07_69J1 | 12/06/2023 | 12/12/2023 | 4 | 2 | 2 | 12/13/2023 | 12/13/2023 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 | 12/06/2023 | 2/28/2025 | Y | EXP | 365 | 04/26/2024 | 05/14/2024 | 19 | 0 | 19 |  |  | 6/20/2024 | Connected |  | N
National Grid | HANOVER | 301309 | 02339 | 7.6 | Solar | 05_12_21J37 | 08/13/2020 | 08/17/2020 | 1 | 0 | 1 | 08/18/2020 | 08/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 |  | 8/1/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 189059 | 01440 | 5000 | Solar | 05_09_705W3 | 06/27/2018 | 06/27/2018 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2018 | 08/22/2018 | 19 | 13 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 506126 | 02302 | 10 | Solar | 05_07_95W5 | 03/21/2023 | 01/10/2024 | 202 | 200 | 2 | 01/11/2024 | 01/11/2024 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | LYNN | 746413 | 01902 | 17.6 | Solar | 49_56_33F4 | 01/20/2026 | 01/22/2026 | 2 | 0 | 2 | 01/23/2026 | 01/23/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ORANGE | 575267 | 01364 | 3.8 | Solar | 05_07_69J1 | 12/15/2023 | 12/19/2023 | 2 | 1 | 1 | 12/20/2023 | 12/20/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 533852 | 02339 | 2.925 | Solar | 05_12_21J37 | 09/20/2023 | 11/16/2023 | 39 | 36 | 3 | 11/17/2023 | 11/17/2023 | 72 | 58 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 4/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2024 | Connected |  | N
National Grid | FALL RIVER | 191051 | 02720 | 1860 | Solar | 05_09_705W3 | 09/25/2018 | 11/26/2018 | 107 | 0 | 107 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2018 | 12/21/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 542074 | 02302 | 15.2 | Solar | 05_07_95W5 | 10/18/2023 | 10/20/2023 | 3 | 2 | 1 | 10/23/2023 | 10/23/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 |  | 1/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2024 | Connected |  | N
National Grid | LYNN | 174310 | 01902 | 12 | Solar | 49_56_33F4 | 09/20/2011 | 09/20/2011 | 159 | 0 | 159 | 09/19/2012 | 09/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/20/2011 | 12/31/2011 | Y | EXP | 347 | 02/03/2014 | 02/14/2014 | 9 | 0 | 9 | 4/5/2012 | 4/5/2012 | 1/31/2014 | Connected |  | N
National Grid | ERVING | 584083 | 01344 | 10.15 | Solar | 05_07_69J1 | 01/19/2024 | 02/28/2024 | 27 | 18 | 9 | 02/29/2024 | 02/29/2024 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2024 | 01/19/2024 | 3/27/2025 | Y | EXP | 365 | 05/24/2024 | 06/05/2024 | 13 | 0 | 13 |  |  | 12/23/2024 | Connected |  | N
National Grid | HANOVER | 597743 | 02339 | 7.6 | Solar | 05_12_21J37 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 286855 | 02720 | 4990 | Solar | 05_09_705W3 | 07/17/2020 | 08/26/2020 | 28 | 23 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2020 | 10/08/2020 | 29 | 13 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 573570 | 02302 | 10 | Solar | 05_07_95W5 | 11/27/2023 | 12/04/2023 | 5 | 3 | 2 | 12/05/2023 | 12/05/2023 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 314962 | 01902 | 0 | Solar | 49_56_33F4 | 10/07/2020 | 10/09/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 |  | 10/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2021 | Connected |  | N
National Grid | WARWICK | 591557 | 01378 | 3.8 | Solar | 05_07_69J1 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 | 02/22/2024 | 6/19/2025 | Y | EXP | 365 | 06/29/2024 | 11/01/2024 | 126 | 0 | 126 |  |  | 3/7/2025 | Connected |  | N
National Grid | HANOVER | 607086 | 02339 | 3.8 | Solar | 05_12_21J37 | 04/26/2024 | 06/06/2024 | 20 | 17 | 3 | 06/07/2024 | 06/07/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 |  | 7/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 294566 | 02720 | 0 | Solar | 05_09_705W3 | 09/16/2020 | 10/05/2020 | 13 | 9 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2020 | 10/29/2020 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 652079 | 02302 | 5.76 | Solar | 05_07_95W5 | 11/14/2024 | 12/17/2024 | 7 | 0 | 7 | 12/18/2024 | 12/18/2024 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/14/2024 | 3/17/2026 | Y | EXP | 365 | 06/12/2025 | 09/18/2025 | 99 | 0 | 99 |  |  | 10/15/2025 | Connected |  | N
National Grid | LYNN | 175197 | 01905 | 1000 | Solar | 05_01_0012 | 05/05/2011 | 05/05/2011 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/13/2011 | 06/23/2011 | 28 | 0 | 28 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2012 | 05/05/2011 | 12/31/2012 | Y | STD | 168 | 08/21/2013 | 12/12/2013 | 77 | 0 | 77 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N
National Grid | ATHOL | 592814 | 01331 | 9.984 | Solar | 05_07_69J1 | 03/18/2024 | 03/20/2024 | 3 | 1 | 2 | 03/21/2024 | 03/21/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 3/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2024 | Connected |  | N
National Grid | HANOVER | 619488 | 02339 | 7.6 | Solar | 05_12_21J37 | 06/20/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 403557 | 02721 | 43.2 | Solar | 05_09_705W3 | 12/28/2021 | 12/29/2021 | 1 | 0 | 1 | 12/30/2021 | 12/30/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  | 2/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2022 | Connected |  | N
National Grid | BROCKTON | 653287 | 02302 | 10 | Solar | 05_07_95W5 | 11/14/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2025 | Connected |  | N
National Grid | LYNN | 175195 | 01905 | 1000 | Solar | 05_01_0012 | 05/05/2011 | 05/05/2011 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/13/2011 | 06/23/2011 | 28 | 0 | 28 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2012 | 05/05/2011 | 12/31/2012 | Y | STD | 168 | 08/21/2013 | 12/12/2013 | 77 | 0 | 77 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N
National Grid | ATHOL | 601320 | 01331 | 7.6 | Solar | 05_07_69J1 | 04/10/2024 | 04/16/2024 | 3 | 0 | 3 | 04/17/2024 | 04/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 11/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2024 | Connected |  | N
National Grid | HANOVER | 626781 | 02339 | 6.72 | Solar | 05_12_21J37 | 07/22/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 432618 | 02790 | 9.6 | Solar | 05_09_705W3 | 06/22/2022 | 06/24/2022 | 2 | 0 | 2 | 06/27/2022 | 06/27/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 | 06/22/2022 | 1/5/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 654880 | 02302 | 5.76 | Solar | 05_07_95W5 | 11/20/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/20/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | LYNN | 178087 | 01905 | 4300 | Solar | 05_01_0012 | 05/09/2017 | 05/09/2017 | 18 | 16 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/06/2017 | 08/28/2017 | 58 | 49 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 | 05/09/2017 | 1/10/2022 | Y | STD | 35 | 06/17/2020 | 10/11/2021 | 380 | 5 | 375 | 11/16/2021 | 11/15/2021 | 12/30/2021 | Connected |  | N
National Grid | ORANGE | 610713 | 01364 | 3.8 | Solar | 05_07_69J1 | 05/14/2024 | 05/17/2024 | 1 | 0 | 1 | 05/20/2024 | 05/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 642163 | 02339 | 10 | Solar | 05_12_21J37 | 10/01/2024 | 11/12/2024 | 22 | 15 | 7 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/01/2024 | 3/7/2026 | Y | EXP | 365 | 07/09/2025 | 07/08/2025 | 0 | 0 | 0 |  |  | 12/13/2025 | Connected |  | N
National Grid | WESTPORT | 453993 | 02790 | 7.6 | Solar | 05_09_705W3 | 09/23/2022 | 09/28/2022 | 3 | 0 | 3 | 09/29/2022 | 09/29/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 09/23/2022 | 1/19/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | N
National Grid | BROCKTON | 656245 | 02302 | 3.8 | Solar | 05_07_95W5 | 11/22/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | LYNN | 178116 | 01905 | 1500 | Solar | 05_01_0012 | 05/09/2017 | 05/09/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2017 | 08/28/2017 | 60 | 49 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 | 05/09/2017 | 10/16/2021 | Y | STD | 35 |  |  | 0 | 0 | 0 |  |  | 10/4/2021 | Connected |  | N
National Grid | ATHOL | 617998 | 01331 | 5.76 | Solar | 05_07_69J1 | 06/14/2024 | 06/24/2024 | 1 | 0 | 1 | 06/25/2024 | 06/25/2024 | 17 | 0 | 17 | 07/25/2024 | 08/27/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/27/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 8/26/2024 | 06/14/2024 | 8/27/2025 | Y | EXP | 365 | 10/03/2024 | 10/29/2024 | 27 | 0 | 27 |  |  | 11/14/2024 | Connected |  | N
National Grid | HANOVER | 647804 | 02339 | 5.76 | Solar | 05_12_21J37 | 10/28/2024 | 01/30/2025 | 53 | 50 | 3 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 7/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | WESTPORT | 457131 | 02790 | 160 | Solar | 05_09_705W3 | 09/19/2022 | 10/03/2022 | 10 | 0 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2024 |  | 1/23/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | BROCKTON | 666969 | 02302 | 47.5 | Solar | 05_07_95W5 | 01/21/2025 | 04/14/2025 | 58 | 49 | 9 | 04/15/2025 | 04/15/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2025 | Connected |  | N
National Grid | LYNN | 176232 | 01905 | 60 | Natural Gas | 05_01_HT40 | 02/13/2015 | 02/13/2015 | 10 | 7 | 3 | 03/02/2015 | 03/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2015 |  | 7/31/2015 | N | EXP | 149 |  |  | 0 | 0 | 0 | 2/19/2016 | 2/19/2016 | 2/18/2016 | Connected |  | N
National Grid | ORANGE | 632302 | 01364 | 3.8 | Solar | 05_07_69J1 | 08/13/2024 | 09/10/2024 | 4 | 0 | 4 | 09/11/2024 | 09/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 08/13/2024 | 11/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | HANOVER | 748924 | 02339 | 5.76 | Solar | 05_12_22J1 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTH BROOKFIELD | 506021 | 01535 | 10 | Solar | 05_09_705W3 | 03/27/2023 | 03/28/2023 | 1 | 0 | 1 | 03/29/2023 | 03/29/2023 | 76 | 21 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 666962 | 02302 | 9.5 | Solar | 05_07_95W5 | 01/21/2025 | 02/24/2025 | 4 | 2 | 2 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 01/21/2025 | 4/23/2026 | Y | EXP | 365 | 07/02/2025 | 07/05/2025 | 4 | 0 | 4 |  |  | 7/11/2025 | Connected |  | N
National Grid | LYNN | 174853 | 01905 | 990 | Solar | 05_05_2248 | 04/16/2013 | 04/16/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2013 | 07/16/2013 | 54 | 0 | 54 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2016 | 04/16/2013 | 8/19/2020 | Y | STD | 1358 | 04/14/2020 | 04/13/2020 | 0 | 0 | 0 | 5/15/2020 | 5/14/2020 | 8/19/2020 | Connected |  | N
National Grid | ORANGE | 634714 | 01364 | 5.76 | Solar | 05_07_69J1 | 08/22/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 08/22/2024 | 11/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 375833 | 02339 | 8.7 | Solar | 05_12_22J1 | 09/13/2021 | 09/21/2021 | 7 | 6 | 1 | 09/22/2021 | 09/22/2021 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 11/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2021 | Connected |  | N
National Grid | NORTH BROOKFIELD | 528322 | 01535 | 15.08 | Solar | 05_09_705W3 | 06/07/2023 | 06/08/2023 | 1 | 0 | 1 | 06/09/2023 | 06/09/2023 | 178 | 25 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 666901 | 02302 | 49.4 | Solar | 05_07_95W5 | 01/21/2025 | 03/19/2025 | 41 | 31 | 10 | 03/20/2025 | 03/20/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2025 | Connected |  | N
National Grid | LYNN | 174852 | 01905 | 0 | Solar | 05_05_2248 | 04/16/2013 | 04/16/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2013 | 07/16/2013 | 54 | 0 | 54 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2016 |  | 9/23/2019 | N | STD | 1274 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 637696 | 01364 | 3.8 | Solar | 05_07_69J1 | 09/04/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 09/04/2024 | 10/9/2025 | Y | EXP | 365 | 03/20/2025 | 03/19/2025 | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | HANOVER | 659858 | 02339 | 11.52 | Solar | 05_12_22J1 | 12/11/2024 | 01/06/2025 | 5 | 0 | 5 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/11/2024 | 3/21/2026 | Y | EXP | 365 | 06/04/2025 | 09/04/2025 | 93 | 0 | 93 |  |  | 9/8/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 529380 | 01535 | 7.6 | Solar | 05_09_705W3 | 06/01/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 689624 | 02302 | 20 | Solar | 05_07_95W5 | 05/06/2025 | 05/09/2025 | 3 | 0 | 3 | 05/12/2025 | 05/12/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 | 05/06/2025 | 7/8/2026 | Y | EXP | 365 | 09/11/2025 | 10/24/2025 | 44 | 0 | 44 |  |  | 10/30/2025 | Connected |  | N
National Grid | LYNN | 175082 | 01905 | 75 | Solar | 05_05_2248 | 10/08/2013 | 10/08/2013 | 3 | 0 | 3 | 10/15/2013 | 10/15/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2013 |  | 12/31/2013 | N | EXP | 43 |  |  | 0 | 0 | 0 | 1/8/2014 | 1/8/2014 | 3/20/2014 | Connected |  | N
National Grid | ERVING | 645123 | 01344 | 10 | Solar | 05_07_69J1 | 10/07/2024 | 10/15/2024 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2024 | 10/07/2024 | 2/20/2026 | Y | EXP | 365 | 06/10/2025 | 07/02/2025 | 23 | 0 | 23 |  |  | 7/18/2025 | Connected |  | N
National Grid | HANOVER | 671093 | 02339 | 6.72 | Solar | 05_12_22J2 | 02/10/2025 | 04/09/2025 | 10 | 6 | 4 | 04/10/2025 | 04/10/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | NORTH BROOKFIELD | 546846 | 01535 | 1494 | Solar | 05_09_705W3 | 03/08/2024 | 05/03/2024 | 39 | 31 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2024 | 05/09/2024 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 696791 | 02302 | 15.76 | Solar | 05_07_95W5 | 06/25/2025 | 06/27/2025 | 2 | 0 | 2 | 06/30/2025 | 06/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 175104 | 01905 | 3960 | Solar | 05_05_2248 | 04/16/2013 | 04/16/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2013 | 07/16/2013 | 54 | 0 | 54 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2016 | 04/16/2013 | 8/19/2020 | Y | STD | 1358 | 04/14/2020 | 04/13/2020 | 0 | 0 | 0 | 5/15/2020 | 5/14/2020 | 8/19/2020 | Connected |  | N
National Grid | ORANGE | 659777 | 01364 | 7.6 | Solar | 05_07_69J1 | 12/11/2024 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | HANOVER | 547547 | 02339 | 60 | Solar | 05_12_22J2 | 08/11/2023 | 11/27/2023 | 72 | 61 | 11 | 11/28/2023 | 11/28/2023 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 569219 | 01602 | 10 | Solar | 05_09_705W3 | 05/29/2024 | 07/23/2024 | 36 | 36 | 0 | 07/23/2024 | 07/23/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2024 | Connected |  | N
National Grid | BROCKTON | 637580 | 02302 | 220 | Solar | 05_07_96W40 | 09/05/2024 | 11/07/2024 | 45 | 35 | 10 |  |  | 76 | 57 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WINTHROP | 177702 | 02152 | 3469 | Solar | 05_05_2274 | 05/25/2017 | 05/25/2017 | 54 | 53 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2017 | 09/01/2017 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2018 | 05/25/2017 | 12/31/2020 | Y | STD | 444 |  |  | 0 | 0 | 0 |  |  | 12/31/2020 | Connected |  | N
National Grid | ORANGE | 666267 | 01364 | 7.6 | Solar | 05_07_69J1 | 01/16/2025 | 02/13/2025 | 5 | 0 | 5 | 02/14/2025 | 02/14/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 | 01/16/2025 | 3/31/2026 | Y | EXP | 365 | 09/24/2025 | 10/23/2025 | 30 | 0 | 30 |  |  | 10/27/2025 | Connected |  | N
National Grid | HANOVER | 663028 | 02339 | 11.52 | Solar | 05_12_22J2 | 12/30/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | SEEKONK | 606463 | 02771 | 10 | Solar | 05_09_705W3 | 04/24/2024 | 05/02/2024 | 5 | 0 | 5 | 05/03/2024 | 05/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/24/2024 | 6/3/2025 | Y | EXP | 365 | 10/02/2024 | 01/10/2025 | 101 | 0 | 101 |  |  | 1/16/2025 | Connected |  | N
National Grid | BROCKTON | 730114 | 02302 | 12.96 | Solar | 05_07_96W40 | 11/03/2025 |  | 101 | 25 | 76 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WINTHROP | 174298 | 02152 | 2000 | Solar | 05_05_2284 | 12/22/2011 | 12/22/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2013 | 12/22/2011 | 3/1/2012 | Y | STD | 328 | 01/07/2014 | 03/25/2014 | 52 | 0 | 52 | 12/26/2013 | 12/26/2013 | 12/26/2013 | Connected |  | N
National Grid | ORANGE | 714327 | 01364 | 7.6 | Solar | 05_07_69J1 | 08/25/2025 | 09/11/2025 | 11 | 6 | 5 | 09/12/2025 | 09/12/2025 | 94 | 77 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 199488 | 02339 | 10 | Solar | 05_12_22J3 | 10/26/2018 | 11/27/2018 | 13 | 8 | 5 | 11/28/2018 | 11/28/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 | 10/26/2018 | 12/20/2019 | Y | EXP | 365 | 06/20/2019 | 07/29/2019 | 38 | 0 | 38 |  |  | 10/30/2019 | Connected |  | N
National Grid | SEEKONK | 622235 | 02771 | 7.6 | Solar | 05_09_705W3 | 07/02/2024 | 07/12/2024 | 3 | 1 | 2 | 07/15/2024 | 07/15/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 | 07/02/2024 | 8/14/2025 | Y | EXP | 365 | 10/03/2024 | 01/24/2025 | 114 | 0 | 114 |  |  | 5/20/2025 | Connected |  | N
National Grid | BROCKTON | 748291 | 02302 | 24.7 | Solar | 05_07_96W40 | 01/29/2026 |  | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WINTHROP | 174437 | 02152 | 1000 | Solar | 05_05_2284 | 06/29/2012 | 06/29/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2012 | 08/22/2012 | 28 | 0 | 28 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/12/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 739310 | 01364 | 11.4 | Solar | 05_07_69J1 | 12/10/2025 | 12/11/2025 | 1 | 0 | 1 | 12/12/2025 | 12/12/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2026 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2026 | Connected |  | N
National Grid | HANOVER | 231769 | 02339 | 6 | Solar | 05_12_22J3 | 06/25/2019 | 07/02/2019 | 5 | 5 | 0 | 07/03/2019 | 07/03/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 | 06/25/2019 | 4/16/2020 | Y | EXP | 281 | 01/11/2020 | 01/23/2020 | 12 | 0 | 12 |  |  | 2/6/2020 | Connected |  | N
National Grid | ATTLEBORO | 646287 | 02703 | 7.6 | Solar | 05_09_705W3 | 10/10/2024 | 10/18/2024 | 4 | 0 | 4 | 10/21/2024 | 10/21/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/10/2024 | 12/9/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | BROCKTON | 174256 | 02302 | 135 | Solar | 05_07_96W40 | 02/28/2012 | 02/28/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 | 9/13/2012 | 9/13/2012 |  | Withdrawn |  | N
National Grid | WINTHROP | 174957 | 02152 | 3334 | Solar | 05_05_2284 | 03/01/2013 | 03/01/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 03/21/2013 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 7/16/2015 | 7/16/2015 | 7/21/2015 | Connected |  | N
National Grid | ORANGE | 752853 | 01364 | 11.5 | Solar | 05_07_6W1 | 02/24/2026 | 03/02/2026 | 1 | 0 | 1 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HANOVER | 659889 | 02339 | 5.76 | Solar | 05_12_22J4 | 12/11/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2025 | Connected |  | N
National Grid | SEEKONK | 648204 | 02771 | 3.8 | Solar | 05_09_705W3 | 10/30/2024 | 12/19/2024 | 10 | 5 | 5 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 174255 | 02302 | 50 | Solar | 05_07_96W40 | 02/28/2012 | 02/28/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 7/1/2012 | N | EXP | 164 |  |  | 0 | 0 | 0 | 7/3/2013 | 7/3/2013 | 7/24/2013 | Connected |  | N
National Grid | WINTHROP | 175137 | 02152 | 5000 | Solar | 05_05_2284 | 11/12/2012 | 11/12/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2012 | 01/04/2013 | 26 | 0 | 26 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 755842 | 01364 | 7.6 | Solar | 05_07_6W1 | 03/11/2026 | 03/17/2026 | 2 | 0 | 2 | 03/27/2026 | 03/27/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORWELL | 668411 | 02061 | 11.2 | Solar | 05_12_22J5 | 01/28/2025 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 | 01/28/2025 | 4/15/2026 | Y | EXP | 365 | 06/11/2025 | 11/24/2025 | 167 | 0 | 167 |  |  | 11/25/2025 | Connected |  | N
National Grid | ATTLEBORO | 676362 | 02763 | 50 | Solar | 05_09_705W3 | 03/14/2025 | 03/26/2025 | 8 | 4 | 4 | 03/27/2025 | 03/27/2025 | 55 | 32 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2025 | Connected |  | N
National Grid | BROCKTON | 174584 | 02302 | 200 | Solar | 05_07_96W40 | 11/14/2011 | 11/14/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2012 |  | 6/1/2012 | N | EXP | 98 |  |  | 0 | 0 | 0 | 5/31/2012 | 5/31/2012 | 6/1/2012 | Connected |  | N
National Grid | WINTHROP | 178759 | 02152 | 3000 | Solar | 05_05_2284 | 12/22/2011 | 12/22/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2012 | 12/22/2011 | 3/1/2012 | Y | STD | 250 | 07/02/2013 | 10/04/2013 | 66 | 0 | 66 | 9/19/2013 | 9/19/2013 | 11/18/2013 | Connected |  | N
National Grid | ORANGE | 177066 | 01364 | 3.8 | Solar | 05_07_6W1 | 03/20/2017 | 03/20/2017 | 7 | 7 | 0 | 03/30/2017 | 03/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2017 | 03/20/2017 | 3/26/2018 | Y | EXP | 357 | 08/15/2017 | 09/01/2017 | 13 | 0 | 13 | 11/7/2017 | 11/7/2017 | 11/7/2017 | Connected |  | N
National Grid | NORWELL | 682616 | 02061 | 5.76 | Solar | 05_12_22J5 | 04/04/2025 | 04/22/2025 | 4 | 0 | 4 | 05/01/2025 | 05/01/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2025 | Connected |  | N
National Grid | FRANKLIN | 676809 | 02038 | 12.6 | Solar | 05_09_705W3 | 03/10/2025 | 03/26/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | BROCKTON | 174839 | 02302 | 260 | Solar | 05_07_96W40 | 02/28/2012 | 02/28/2012 | 2 | 0 | 2 | 04/04/2012 | 04/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2012 |  | 9/11/2012 | N | EXP | 2 |  |  | 0 | 0 | 0 | 9/13/2012 | 9/13/2012 | 8/6/2013 | Connected |  | N
National Grid | WINTHROP | 397260 | 02152 | 2250 | Solar | 05_05_2284 | 03/15/2022 |  | 165 | 157 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 177084 | 01364 | 180 | Solar | 05_07_6W1 | 10/18/2016 | 10/18/2016 | 0 | 0 | 0 | 10/27/2017 | 10/27/2017 | 18 | 0 | 18 | 01/12/2018 | 02/16/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 02/16/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 3/30/2018 | 10/18/2016 | 6/9/2021 | Y | EXP | 651 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 692020 | 02061 | 10 | Solar | 05_12_22J5 | 05/19/2025 | 05/29/2025 | 8 | 5 | 3 | 07/14/2025 | 07/14/2025 | 43 | 30 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 | 05/19/2025 | 9/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2026 | Connected |  | N
National Grid | REHOBOTH | 682591 | 02769 | 11.4 | Solar | 05_09_705W3 | 04/03/2025 | 05/14/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 04/03/2025 | 6/24/2026 | Y | EXP | 365 | 09/03/2025 | 09/02/2025 | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid | BROCKTON | 174920 | 02302 | 2000 | Solar | 05_07_96W40 | 02/26/2013 | 02/26/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2013 | 04/08/2013 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/29/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 397258 | 02152 | 1500 | Solar | 05_05_2284 | 03/15/2022 |  | 166 | 158 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARWICK | 178018 | 01378 | 7.6 | Solar | 05_07_6W1 | 06/29/2017 | 06/29/2017 | 4 | 3 | 1 | 07/06/2017 | 07/06/2017 | 140 | 0 | 140 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 7/4/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 757847 | 02061 |  | Battery Add-On | 05_12_22J7 | 03/20/2026 | 03/24/2026 | 2 | 0 | 2 | 03/25/2026 | 03/25/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REHOBOTH | 692741 | 02769 | 11.5 | Solar | 05_09_705W3 | 05/22/2025 | 07/11/2025 | 33 | 31 | 2 | 07/14/2025 | 07/14/2025 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 175057 | 02189 | 135 | Solar | 05_07_96W40 | 02/28/2012 | 02/28/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2012 |  | 11/23/2012 | N | EXP | 37 |  |  | 0 | 0 | 0 | 10/18/2012 | 10/18/2012 | 8/15/2013 | Connected |  | N
National Grid | WINTHROP | 214604 | 02152 | 150 | Solar | 05_05_2285 | 03/28/2019 | 04/17/2019 | 12 | 6 | 6 | 04/18/2019 | 04/18/2019 | 33 | 7 | 26 | 08/07/2019 | 10/18/2019 | 51 | 13 | 38 |  |  | 0 | 0 | 0 | 10/18/2019 | 51 | 13 | 38 |  |  | 0 | 0 | 0 | 10/30/2019 | 03/28/2019 | 3/28/2022 | Y | EXP | 280 | 10/05/2021 | 03/17/2022 | 164 | 4 | 160 |  |  | 3/25/2022 | Connected |  | N
National Grid | ORANGE | 178014 | 01364 | 3.8 | Solar | 05_07_6W1 | 06/29/2017 | 06/29/2017 | 4 | 3 | 1 | 07/06/2017 | 07/06/2017 | 182 | 0 | 182 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 7/4/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 177408 | 02061 | 184 | Solar | 05_12_22J7 | 09/09/2016 | 09/09/2016 | 16 | 16 | 0 | 11/09/2016 | 11/09/2016 | 174 | 174 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2017 |  | 11/30/2018 | N | EXP | 529 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 697621 | 1364 | 10 | Solar | 05_09_705W3 | 06/10/2025 | 06/24/2025 | 3 | 0 | 3 | 07/15/2025 | 07/15/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 | 06/10/2025 | 10/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH WEYMOUTH | 176574 | 02191 | 57.6 | Solar | 05_07_96W40 | 02/11/2016 | 02/11/2016 | 1 | 1 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/17/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 11/29/2016 | 11/29/2016 | 12/1/2016 | Connected |  | N
National Grid | WINTHROP | 176317 | 02152 | 4890 | Solar | 05_05_2286 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/12/2015 | 06/09/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 | 05/08/2015 | 7/7/2017 | Y | STD | 561 | 06/21/2017 | 08/02/2017 | 29 | 0 | 29 | 8/24/2017 | 8/24/2017 | 8/25/2017 | Connected |  | N
National Grid | WENDELL | 190503 | 01379 | 7.6 | Solar | 05_07_6W1 | 07/11/2018 | 08/16/2018 | 8 | 8 | 0 | 08/17/2018 | 08/17/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 204747 | 02061 | 168 | Solar | 05_12_22J7 | 12/27/2018 | 12/28/2018 | 0 | 0 | 0 | 12/31/2018 | 12/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2020 | Connected |  | N
National Grid | FRANKLIN | 699906 | 02038 | 34.2 | Solar | 05_09_705W3 | 06/23/2025 | 06/24/2025 | 1 | 0 | 1 | 06/25/2025 | 06/25/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 06/23/2025 | 8/6/2026 | Y | EXP | 365 | 10/04/2025 | 10/29/2025 | 26 | 0 | 26 |  |  | 12/20/2025 | Connected |  | N
National Grid | WEYMOUTH | 178356 | 02188 | 358.4 | Solar | 05_07_96W40 | 02/28/2018 | 02/28/2018 | 7 | 0 | 7 | 03/12/2018 | 03/12/2018 | 121 | 17 | 104 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2018 |  | 3/6/2020 | N | EXP | 555 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 176520 | 02152 | 768 | Solar | 05_07_1104 | 10/05/2015 | 10/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2016 | 02/10/2016 | 22 | 4 | 18 | 10/06/2015 | 11/04/2015 | 20 | 0 | 20 | 02/10/2016 | 22 | 4 | 18 |  |  | 0 | 0 | 0 | 10/5/2017 |  | 12/1/2017 | N | STD | 57 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARWICK | 208280 | 01378 | 3.8 | Solar | 05_07_6W1 | 02/05/2019 | 02/13/2019 | 5 | 0 | 5 | 02/14/2019 | 02/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 312766 | 02061 | 3.8 | Solar | 05_12_22J7 | 09/24/2020 | 09/28/2020 | 1 | 0 | 1 | 09/29/2020 | 09/29/2020 | 37 | 20 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 705558 | 02038 | 7.6 | Solar | 05_09_705W3 | 07/17/2025 | 09/15/2025 | 40 | 24 | 16 | 09/16/2025 | 09/16/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 178643 | 02184 | 153.2 | Solar | 05_07_96W40 | 12/15/2017 | 12/15/2017 | 31 | 21 | 10 | 02/01/2018 | 02/01/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2018 |  | 12/20/2018 | N | EXP | 318 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | REVERE | 342873 | 02151 | 2575 | Solar | 05_07_1104 | 06/09/2021 | 07/16/2021 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2021 | 08/20/2021 | 25 | 0 | 25 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 06/09/2021 | 10/30/2023 | Y | STD | 490 | 06/14/2023 | 06/13/2023 | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N
National Grid | WARWICK | 209081 | 01378 | 7.6 | Solar | 05_07_6W1 | 03/01/2019 | 03/12/2019 | 6 | 0 | 6 | 03/13/2019 | 03/13/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 574519 | 02061 | 7.6 | Solar | 05_12_22J7 | 12/04/2023 | 01/22/2024 | 32 | 25 | 7 | 01/23/2024 | 01/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 12/04/2023 | 3/15/2025 | Y | EXP | 365 | 07/17/2024 | 07/16/2024 | 0 | 0 | 0 |  |  | 8/30/2024 | Connected |  | N
National Grid | ORANGE | 741470 | 1364 | 15.2 | Solar | 05_09_705W3 | 01/05/2026 | 01/07/2026 | 2 | 0 | 2 | 01/08/2026 | 01/08/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 178649 | 02188 | 72 | Solar | 05_07_96W40 | 12/15/2017 | 12/15/2017 | 23 | 14 | 9 | 01/23/2018 | 01/23/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2018 |  | 12/23/2018 | N | EXP | 333 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | WINTHROP | 175399 | 02152 | 1850 | Natural Gas | 05_07_1202 | 11/17/2014 | 11/17/2014 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2014 | 12/23/2014 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2015 |  | 12/31/2016 | N | STD | 495 |  |  | 0 | 0 | 0 | 12/14/2015 | 12/14/2015 | 12/14/2015 | Connected |  | N
National Grid | ORANGE | 224808 | 01364 | 3.8 | Solar | 05_07_6W1 | 08/08/2019 | 08/13/2019 | 2 | 0 | 2 | 08/14/2019 | 08/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 8/17/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2020 | Connected |  | N
National Grid | NORWELL | 657610 | 02061 | 3.8 | Solar | 05_12_22J7 | 11/29/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | METHUEN | 426180 | 01844 | 580 | Solar | 05_09_901W1 | 06/27/2022 | 08/10/2022 | 31 | 23 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/08/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 | 06/27/2022 | 2/24/2027 | Y | STD | 750 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WEYMOUTH | 220756 | 02188 | 105.6 | Solar | 05_07_96W40 | 05/16/2019 | 05/31/2019 | 10 | 1 | 9 | 06/03/2019 | 06/03/2019 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2019 |  | 12/31/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2020 | Connected |  | N
National Grid | WINTHROP | 174160 | 02152 | 2000 | Solar | 05_09_0504 | 04/16/2012 | 04/16/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 06/26/2012 | 32 | 0 | 32 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/15/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 235878 | 01364 | 7.6 | Solar | 05_07_6W1 | 07/05/2019 | 08/09/2019 | 25 | 25 | 0 | 08/12/2019 | 08/12/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 |  | 8/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2020 | Connected |  | N
National Grid | ROCKLAND | 669460 | 02370 | 3.8 | Solar | 05_12_22J7 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 02/03/2025 | 4/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2025 | Connected |  | N
National Grid | PLAINVILLE | 733098 | 02762 | 17.26 | Solar | 05_09_901W1 | 11/17/2025 | 11/18/2025 | 1 | 0 | 1 | 11/19/2025 | 11/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEYMOUTH | 258675 | 02188 | 24 | Solar | 05_07_96W40 | 11/08/2019 | 11/14/2019 | 2 | 1 | 1 | 11/15/2019 | 11/15/2019 | 47 | 34 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 11/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 174159 | 02152 | 3000 | Solar | 05_09_0504 | 04/16/2012 | 04/16/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 06/26/2012 | 32 | 0 | 32 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/15/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARWICK | 310769 | 01378 | 10 | Solar | 05_07_6W1 | 10/13/2020 | 10/20/2020 | 4 | 0 | 4 | 10/21/2020 | 10/21/2020 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 | 10/13/2020 | 12/1/2022 | Y | EXP | 365 | 06/02/2022 | 07/21/2022 | 50 | 0 | 50 |  |  | 9/22/2022 | Connected |  | Y
National Grid | NORWELL | 176613 | 02061 | 32.4 | Solar | 05_12_22W1 | 02/12/2016 | 02/12/2016 | 3 | 3 | 0 | 02/18/2016 | 02/18/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2016 |  | 8/20/2017 | N | EXP | 478 |  |  | 0 | 0 | 0 | 8/7/2017 | 8/7/2017 | 8/7/2017 | Connected |  | N
National Grid | QUINCY | 174170 | 02171 | 50 | Natural Gas | 05_09_901W1 | 03/14/2012 | 03/14/2012 | 126 | 0 | 126 | 09/18/2012 | 09/18/2012 | 360 | 0 | 360 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2013 |  | 11/30/2012 | N | EXP | 82 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 256924 | 02188 | 24 | Solar | 05_07_96W40 | 11/08/2019 | 11/14/2019 | 2 | 1 | 1 | 11/15/2019 | 11/15/2019 | 47 | 31 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 11/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 174158 | 02152 | 3800 | Solar | 05_09_0504 | 04/16/2012 | 04/16/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 06/26/2012 | 32 | 0 | 32 |  | 0 | 0 | 0 | 08/17/2013 | 10/15/2013 | 39 | 0 | 39 | 8/9/2013 | 04/16/2012 | 12/31/2016 | Y | STD | 1240 |  |  | 0 | 0 | 0 | 2/23/2016 | 2/23/2016 | 2/23/2016 | Connected |  | N
National Grid | ORANGE | 316632 | 01364 | 3.8 | Solar | 05_07_6W1 | 11/03/2020 | 11/09/2020 | 3 | 0 | 3 | 11/10/2020 | 11/10/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 399139 | 02061 | 5.8 | Solar | 05_12_22W1 | 12/09/2021 | 12/13/2021 | 2 | 0 | 2 | 12/14/2021 | 12/14/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 174352 | 02171 | 17 | Solar | 05_09_901W1 | 05/09/2012 | 05/09/2012 | 7 | 0 | 7 | 05/22/2012 | 05/22/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2012 |  | 7/31/2012 | N | EXP | 44 |  |  | 0 | 0 | 0 | 8/30/2012 | 8/30/2012 | 10/11/2012 | Connected |  | N
National Grid | WEYMOUTH | 262162 | 02188 | 100 | Solar | 05_07_96W40 | 11/21/2019 | 12/09/2019 | 11 | 5 | 6 | 12/10/2019 | 12/10/2019 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 | 11/21/2019 | 8/25/2022 | Y | EXP | 365 | 07/21/2020 | 07/26/2022 | 736 | 348 | 388 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 175737 | 02152 | 5350 | Solar | 05_09_0504 | 08/11/2014 | 08/11/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2014 | 09/23/2014 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 |  | 12/31/2016 | N | STD | 640 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 319521 | 01364 | 6.48 | Solar | 05_07_6W1 | 10/27/2020 | 11/13/2020 | 11 | 9 | 2 | 11/16/2020 | 11/16/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 |  | 11/12/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2021 | Connected |  | Y
National Grid | NORWELL | 608123 | 02061 | 2.61 | Solar | 05_12_22W1 | 05/01/2024 | 09/11/2024 | 21 | 20 | 1 | 09/12/2024 | 09/12/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 05/01/2024 | 11/13/2025 | Y | EXP | 365 | 02/27/2025 | 01/22/2026 | 330 | 0 | 330 |  |  | 3/21/2025 | Connected |  | N
National Grid | QUINCY | 174484 | 02169 | 250 | Solar | 05_09_901W1 | 01/25/2011 | 01/25/2011 | 21 | 0 | 21 | 02/24/2011 | 02/24/2011 | 720 | 0 | 720 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2011 |  | 7/29/2012 | N | EXP | 319 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 262160 | 02188 | 24 | Solar | 05_07_96W40 | 11/21/2019 | 12/09/2019 | 11 | 5 | 6 | 12/10/2019 | 12/10/2019 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 11/21/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 176198 | 02152 | 144 | Solar | 05_09_0504 | 02/16/2015 | 02/16/2015 | 4 | 0 | 4 | 02/23/2015 | 02/23/2015 | 206 | 29 | 177 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2015 |  | 6/30/2015 | N | EXP | 69 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 477444 | 01060 | 10 | Solar | 05_07_6W1 | 12/20/2022 | 12/26/2022 | 4 | 0 | 4 | 12/27/2022 | 12/27/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 12/20/2022 | 9/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2023 | Connected |  | N
National Grid | NORWELL | 663578 | 02061 | 3.19 | Solar | 05_12_22W1 | 01/03/2025 | 02/05/2025 | 19 | 14 | 5 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/03/2025 | 7/8/2026 | Y | EXP | 365 | 08/28/2025 | 11/14/2025 | 79 | 0 | 79 |  |  | 11/26/2025 | Connected |  | N
National Grid | PALMER | 174953 | 01069 | 250 | Solar | 05_09_901W1 | 09/28/2012 | 09/28/2012 | 6 | 0 | 6 | 10/10/2012 | 10/10/2012 | 0 | 0 | 0 | 02/08/2013 | 03/14/2013 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 03/14/2013 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 3/19/2013 | 09/28/2012 | 12/31/2012 | Y | EXP | 78 |  |  | 0 | 0 | 0 | 8/15/2013 | 8/15/2013 | 9/6/2013 | Connected |  | N
National Grid | WEYMOUTH | 317863 | 02188 | 162.5 | Solar | 05_07_96W40 | 11/16/2020 | 12/02/2020 | 11 | 6 | 5 | 12/03/2020 | 12/03/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 | 11/16/2020 | 9/5/2022 | Y | EXP | 365 | 10/23/2021 | 01/25/2022 | 95 | 0 | 95 |  |  | 7/27/2022 | Connected |  | N
National Grid | WINTHROP | 178102 | 02152 | 4980 | Solar | 05_09_0504 | 09/08/2017 | 09/14/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2017 | 10/09/2017 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 | 09/08/2017 | 12/29/2023 | Y | STD | 481 | 01/31/2023 | 09/12/2023 | 225 | 121 | 104 |  |  | 12/29/2023 | Connected |  | N
National Grid | NORTHAMPTON | 645162 | 01060 | 3.8 | Solar | 05_07_6W1 | 10/07/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/07/2024 | 12/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | NORWELL | 675270 | 02061 | 67.3 | Solar | 05_12_22W2 | 03/11/2025 | 04/15/2025 | 25 | 16 | 9 | 04/16/2025 | 04/16/2025 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 7/25/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | PALMER | 175972 | 01069 | 176 | Solar | 05_09_901W1 | 08/13/2015 | 08/13/2015 | 0 | 0 | 0 | 08/13/2015 | 08/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2015 | 08/13/2015 | 8/18/2016 | Y | EXP | 342 | 06/03/2016 | 12/08/2016 | 128 | 0 | 128 | 12/14/2016 | 12/14/2016 | 12/20/2016 | Connected |  | N
National Grid | WEYMOUTH | 391838 | 02188 | 0 | Other | 05_07_96W40 | 11/15/2021 | 01/04/2022 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 178162 | 01907 | 2490 | Solar | 05_09_0504 | 02/12/2018 | 02/12/2018 | 31 | 2 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2018 | 04/17/2018 | 1 | 0 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/18/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 661199 | 01060 | 5.76 | Solar | 05_07_6W1 | 12/17/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 25 | 0 | 25 | 03/07/2025 | 04/08/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 04/08/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 4/14/2025 | 12/17/2024 | 4/21/2026 | Y | EXP | 365 | 05/29/2025 | 10/02/2025 | 127 | 0 | 127 |  |  | 11/24/2025 | Connected |  | N
National Grid | NORWELL | 685919 | 02061 | 5.76 | Solar | 05_12_22W2 | 04/18/2025 | 05/12/2025 | 2 | 0 | 2 | 05/30/2025 | 05/30/2025 | 59 | 46 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | PALMER | 177558 | 01069 | 22.8 | Solar | 05_09_901W1 | 07/13/2017 | 07/13/2017 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 9/28/2018 | N | EXP | 435 |  |  | 0 | 0 | 0 |  |  | 8/14/2018 | Connected |  | N
National Grid | WEYMOUTH | 434617 | 02188 | 9.57 | Solar | 05_07_96W40 | 06/27/2022 | 06/29/2022 | 2 | 0 | 2 | 06/30/2022 | 06/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | SWAMPSCOTT | 192369 | 01907 | 410 | Solar | 05_09_0504 | 09/14/2018 | 11/29/2018 | 127 | 26 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2018 | 03/22/2019 | 77 | 26 | 51 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 678608 | 01060 | 15.925 | Solar | 05_07_6W1 | 03/17/2025 | 04/03/2025 | 7 | 4 | 3 | 04/04/2025 | 04/04/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 | 03/17/2025 | 6/4/2026 | Y | EXP | 365 | 09/03/2025 | 11/20/2025 | 79 | 0 | 79 |  |  | 12/26/2025 | Connected |  | N
National Grid | NORWELL | 709673 | 02061 | 10 | Solar | 05_12_22W2 | 08/05/2025 | 10/01/2025 | 4 | 0 | 4 | 10/09/2025 | 10/09/2025 | 37 | 26 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 12/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MONSON | 177588 | 01057 | 4980 | Solar | 05_09_901W1 | 05/17/2017 | 05/17/2017 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/25/2017 | 06/23/2017 | 20 | 6 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/23/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 495669 | 02191 | 220 | Solar | 05_07_96W40 | 02/17/2023 | 04/20/2023 | 42 | 34 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/21/2023 | 05/12/2023 | 17 | 2 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 178039 | 01907 | 2490 | Solar | 05_09_0507 | 10/27/2017 | 11/14/2017 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 | 12/11/2017 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 2/26/2021 | N | STD | 885 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 679356 | 01060 | 3.8 | Solar | 05_07_6W1 | 03/20/2025 | 07/10/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 | 03/20/2025 | 9/10/2026 | Y | EXP | 365 | 10/01/2025 | 09/30/2025 | 0 | 0 | 0 |  |  | 10/28/2025 | Connected |  | N
National Grid | NORWELL | 725517 | 02061 | 5.76 | Solar | 05_12_22W2 | 10/09/2025 | 10/20/2025 | 6 | 1 | 5 | 11/13/2025 | 11/13/2025 | 63 | 47 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2026 |  | 3/31/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PALMER | 178642 | 01069 | 57.6 | Solar | 05_09_901W1 | 04/10/2018 | 04/10/2018 | 7 | 0 | 7 | 04/20/2018 | 04/20/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 |  | 4/16/2019 | N | EXP | 293 |  |  | 0 | 0 | 0 |  |  | 11/26/2019 | Connected |  | N
National Grid | WEYMOUTH | 621643 | 02189 | 26.46 | Solar | 05_07_96W40 | 07/18/2024 | 08/13/2024 | 19 | 17 | 2 | 08/14/2024 | 08/14/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | LYNN | 185520 | 01902 | 1000 | Solar | 05_09_1003 | 05/25/2018 | 05/25/2018 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2018 | 08/10/2018 | 26 | 21 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 676966 | 01060 | 999.9 | Solar | 05_07_6W2 | 04/08/2025 | 06/10/2025 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ROCKLAND | 730600 | 02370 | 5 | Solar | 05_12_22W2 | 11/03/2025 | 11/04/2025 | 3 | 0 | 3 | 11/17/2025 | 11/17/2025 | 17 | 0 | 17 | 12/24/2025 | 01/14/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 01/14/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | PALMER | 193373 | 01069 | 5 | Solar | 05_09_901W1 | 08/13/2018 | 09/27/2018 | 24 | 23 | 1 | 09/28/2018 | 09/28/2018 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2018 | 08/13/2018 | 2/24/2020 | Y | EXP | 500 | 11/01/2019 | 11/04/2019 | 3 | 0 | 3 |  |  | 1/31/2020 | Connected |  | N
National Grid | WEYMOUTH | 634458 | 02188 | 4.18 | Solar | 05_07_96W40 | 08/26/2024 | 09/05/2024 | 6 | 4 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 | 08/26/2024 | 9/23/2025 | Y | EXP | 365 | 10/09/2024 | 11/01/2024 | 24 | 0 | 24 |  |  | 1/14/2025 | Connected |  | N
National Grid | SWAMPSCOTT | 175649 | 01907 | 5.38 | Solar | 05_12_1384 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/16/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 177666 | 01060 | 3.8 | Solar | 05_07_6W2 | 05/24/2017 | 05/24/2017 | 3 | 3 | 0 | 05/31/2017 | 05/31/2017 | 207 | 0 | 207 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 |  | 5/30/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 735887 | 02061 | 6.84 | Solar | 05_12_22W2 | 11/25/2025 | 11/26/2025 | 1 | 0 | 1 | 02/02/2026 | 02/02/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | PALMER | 302123 | 01069 | 2000 | Solar | 05_09_901W1 | 02/19/2021 | 03/30/2021 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/31/2021 | 05/13/2021 | 22 | 3 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 647618 | 02188 | 0 | Other | 05_07_96W40 | 11/15/2024 | 12/10/2024 | 15 | 6 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 | 05/06/2025 | 100 | 81 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 176329 | 01902 | 3.8 | Solar | 05_12_1384 | 07/20/2015 | 07/20/2015 | 4 | 4 | 0 | 07/27/2015 | 07/27/2015 | 198 | 88 | 110 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2016 |  | 7/26/2016 | N | EXP | 169 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 199236 | 01060 | 10 | Solar | 05_07_6W2 | 11/13/2018 | 01/28/2019 | 49 | 45 | 4 | 01/29/2019 | 01/29/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 740958 | 02066 | 14.06 | Solar | 05_12_22W2 | 12/19/2025 | 12/26/2025 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2026 |  | 3/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PALMER | 309180 | 01069 | 22.8 | Solar | 05_09_901W1 | 09/17/2020 | 09/23/2020 | 3 | 0 | 3 | 09/24/2020 | 09/24/2020 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2021 | Connected |  | N
National Grid | WEYMOUTH | 648861 | 02188 | 9.75 | Solar | 05_07_96W40 | 10/22/2024 | 11/19/2024 | 1 | 0 | 1 | 11/18/2024 | 11/18/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2025 | Connected |  | N
National Grid | LYNN | 176389 | 01902 | 6 | Solar | 05_12_1384 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/6/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 205952 | 01060 | 13.6 | Solar | 05_07_6W2 | 02/14/2019 | 02/20/2019 | 2 | 1 | 1 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 | 02/14/2019 | 9/30/2019 | Y | EXP | 220 | 05/16/2019 | 06/06/2019 | 21 | 0 | 21 |  |  | 8/16/2019 | Connected |  | N
National Grid | NORWELL | 749204 | 02061 | 7.6 | Solar | 05_12_22W2 | 02/04/2026 | 02/12/2026 | 2 | 0 | 2 | 02/23/2026 | 02/23/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MONSON | 383931 | 01057 | 20.59 | Solar | 05_09_901W1 | 09/23/2021 | 09/27/2021 | 2 | 0 | 2 | 09/28/2021 | 09/28/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  | 7/21/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 720193 | 02188 | 94.05 | Solar | 05_07_96W40 | 09/25/2025 |  | 25 | 24 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 176486 | 01902 | 5 | Solar | 05_12_1384 | 12/09/2015 | 12/09/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/14/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 296209 | 01060 | 12 | Solar | 05_07_6W2 | 06/12/2020 | 06/29/2020 | 10 | 6 | 4 | 06/30/2020 | 06/30/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 10/25/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 192216 | 02061 | 7.6 | Solar | 05_12_22W2 | 07/30/2018 | 07/31/2018 | 0 | 0 | 0 | 08/02/2018 | 08/02/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 07/30/2018 | 9/30/2019 | Y | EXP | 399 | 03/16/2019 | 03/15/2019 | 0 | 0 | 0 |  |  | 8/21/2019 | Connected |  | N
National Grid | ADAMS | 457933 | 01220 | 6.67 | Solar | 05_09_901W1 | 09/30/2022 | 10/10/2022 | 6 | 2 | 4 | 10/11/2022 | 10/11/2022 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 | 09/30/2022 | 3/29/2024 | Y | EXP | 365 | 03/29/2023 | 03/30/2023 | 2 | 0 | 2 |  |  | 5/31/2023 | Connected |  | Y
National Grid | WEYMOUTH | 658956 | 02191 | 400 | Solar | 05_07_96W41 | 01/15/2025 | 03/11/2025 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/12/2025 | 04/08/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 |  |  | N | STD | 49 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LYNN | 177075 | 01902 | 10 | Solar | 05_12_1384 | 08/03/2016 | 08/03/2016 | 1 | 1 | 0 | 08/05/2016 | 08/05/2016 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/9/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 410224 | 01060 | 15.2 | Solar | 05_07_6W2 | 02/03/2022 | 04/05/2022 | 43 | 25 | 18 | 04/06/2022 | 04/06/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 310486 | 02066 | 7.6 | Solar | 05_12_22W2 | 09/29/2020 | 09/30/2020 | 0 | 0 | 0 | 10/01/2020 | 10/01/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 | 09/29/2020 | 9/1/2021 | Y | EXP | 365 | 03/10/2021 | 06/11/2021 | 93 | 0 | 93 |  |  | 7/2/2021 | Connected |  | N
National Grid | LYNN | 566378 | 01902 | 3.78 | Solar | 05_09_901W1 | 11/13/2023 | 11/14/2023 | 1 | 0 | 1 | 11/15/2023 | 11/15/2023 | 56 | 33 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 174570 | 02191 | 900 | Wind | 05_07_96W41 | 05/17/2011 | 05/17/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 177827 | 01902 | 10 | Solar | 05_12_1384 | 06/09/2017 | 06/09/2017 | 7 | 0 | 7 | 06/20/2017 | 06/20/2017 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/14/2018 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 481330 | 01060 | 15.2 | Solar | 05_07_6W2 | 11/30/2022 | 12/05/2022 | 3 | 2 | 1 | 12/06/2022 | 12/06/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 6/9/2025 | N | EXP | 730 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 324111 | 02061 | 66.6 | Solar | 05_12_22W2 | 11/12/2020 | 12/08/2020 | 16 | 12 | 4 | 12/09/2020 | 12/09/2020 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2021 |  | 10/3/2023 | N | EXP | 722 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 620131 | 01902 | 100 | Solar | 05_09_901W1 | 06/28/2024 | 07/23/2024 | 16 | 7 | 9 | 07/24/2024 | 07/24/2024 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 12/11/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/16/2025 | Connected |  | N
National Grid | WEYMOUTH | 176361 | 02191 | 0 | Solar | 05_07_96W41 | 03/09/2016 | 03/09/2016 | 0 | 0 | 0 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 | 04/18/2016 | 06/17/2016 | 42 | 12 | 30 |  |  | 0 | 0 | 0 | 06/17/2016 | 42 | 12 | 30 |  |  | 0 | 0 | 0 | 7/6/2016 | 03/09/2016 | 9/8/2017 | Y | EXP | 429 | 06/22/2017 | 08/10/2017 | 34 | 0 | 34 | 8/29/2017 | 8/29/2017 | 8/29/2017 | Connected |  | N
National Grid | SWAMPSCOTT | 192763 | 01907 | 8 | Solar | 05_12_1384 | 11/07/2018 |  | 59 | 26 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 489983 | 01060 | 15.2 | Solar | 05_07_6W2 | 01/05/2023 | 01/06/2023 | 1 | 0 | 1 | 01/09/2023 | 01/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2023 |  | 2/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2023 | Connected |  | N
National Grid | SCITUATE | 436299 | 02066 | 6 | Solar | 05_12_22W2 | 06/21/2022 | 06/22/2022 | 1 | 0 | 1 | 06/23/2022 | 06/23/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2022 | Connected |  | N
National Grid | LYNN | 652952 | 01902 | 5.76 | Solar | 05_09_901W1 | 11/07/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | WEYMOUTH | 177045 | 02191 | 696 | Solar | 05_07_96W41 | 10/17/2016 | 10/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2016 | 01/23/2017 | 59 | 44 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2018 | 10/17/2016 | 10/15/2021 | Y | STD | 225 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 525248 | 01902 | 3.84 | Solar | 05_12_1384 | 05/22/2023 | 05/23/2023 | 1 | 0 | 1 | 05/24/2023 | 05/24/2023 | 175 | 149 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 494588 | 01060 | 9.86 | Solar | 05_07_6W2 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 24 | 2 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 02/09/2023 | 6/22/2024 | Y | EXP | 365 | 06/09/2023 | 06/22/2023 | 14 | 0 | 14 |  |  | 7/29/2023 | Connected |  | N
National Grid | NORWELL | 471551 | 02061 | 80 | Solar | 05_12_22W2 | 11/01/2022 | 11/10/2022 | 7 | 0 | 7 | 11/14/2022 | 11/14/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2023 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 652876 | 01902 | 3.48 | Solar | 05_09_901W1 | 11/08/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 11/08/2024 | 12/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | WEYMOUTH | 178632 | 02191 | 10 | Solar | 05_07_96W41 | 03/15/2018 | 03/15/2018 | 4 | 4 | 0 | 03/23/2018 | 03/23/2018 | 402 | 0 | 402 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2018 |  | 3/21/2019 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 661725 | 01907 | 15.2 | Solar | 05_12_1384 | 01/09/2025 | 01/24/2025 | 11 | 7 | 4 | 01/27/2025 | 01/27/2025 | 68 | 50 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 515717 | 01060 | 7.6 | Solar | 05_07_6W2 | 03/30/2023 | 03/31/2023 | 1 | 0 | 1 | 04/03/2023 | 04/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2023 |  | 5/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2023 | Connected |  | N
National Grid | COHASSET | 479881 | 02025 | 0 | Solar | 05_12_22W2 | 12/02/2022 | 12/07/2022 | 3 | 1 | 2 | 12/08/2022 | 12/08/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  | 4/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2023 | Connected |  | N
National Grid | LYNN | 664283 | 01902 | 10 | Solar | 05_09_901W1 | 01/07/2025 | 01/23/2025 | 5 | 0 | 5 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 01/07/2025 | 3/17/2026 | Y | EXP | 365 | 09/19/2025 | 09/18/2025 | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | WEYMOUTH | 200495 | 02191 | 7.5 | Solar | 05_07_96W41 | 11/13/2018 | 04/11/2019 | 0 | 0 | 0 | 04/12/2019 | 04/12/2019 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2019 |  | 5/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2019 | Connected |  | N
National Grid | LYNN | 685356 | 01902 | 10 | Solar | 05_12_1384 | 04/15/2025 | 05/05/2025 | 1 | 0 | 1 | 05/09/2025 | 05/09/2025 | 51 | 39 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  | 7/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/18/2025 | Connected |  | N
National Grid | NORTHAMPTON | 520867 | 01060 | 10.15 | Solar | 05_07_6W2 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  | 6/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | COHASSET | 507161 | 02025 | 4.64 | Solar | 05_12_22W2 | 03/24/2023 | 03/27/2023 | 1 | 0 | 1 | 03/28/2023 | 03/28/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2023 | 03/24/2023 | 7/19/2024 | Y | EXP | 365 | 07/21/2023 | 07/20/2023 | 0 | 0 | 0 |  |  | 7/25/2023 | Connected |  | N
National Grid | LYNN | 677262 | 01902 | 7.6 | Solar | 05_09_901W1 | 03/11/2025 | 03/17/2025 | 5 | 1 | 4 | 03/18/2025 | 03/18/2025 | 61 | 39 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 | 03/11/2025 | 7/17/2026 | Y | EXP | 365 | 08/30/2025 | 08/29/2025 | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | WEYMOUTH | 263280 | 02191 | 0 | Other | 05_07_96W41 | 10/31/2019 | 01/21/2020 | 44 | 39 | 5 | 01/22/2020 | 01/22/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 |  | 10/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N
National Grid | LYNN | 696793 | 01902 | 9.28 | Solar | 05_12_1384 | 06/06/2025 | 06/27/2025 | 5 | 1 | 4 | 06/30/2025 | 06/30/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 649005 | 01060 | 11.4 | Solar | 05_07_6W2 | 10/23/2024 | 11/11/2024 | 5 | 0 | 5 | 11/12/2024 | 11/12/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/23/2024 | 3/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | COHASSET | 527219 | 02025 | 19.43 | Solar | 05_12_22W2 | 06/07/2023 | 06/28/2023 | 13 | 13 | 0 | 06/29/2023 | 06/29/2023 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 |  | 7/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2023 | Connected |  | N
National Grid | LYNN | 698154 | 01902 | 7.6 | Solar | 05_09_901W1 | 06/12/2025 | 06/25/2025 | 3 | 0 | 3 | 07/11/2025 | 07/11/2025 | 22 | 9 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | WEYMOUTH | 288906 | 02191 | 24 | Solar | 05_07_96W41 | 05/08/2020 | 05/11/2020 | 1 | 1 | 0 | 05/12/2020 | 05/12/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 |  | 5/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2020 | Connected |  | N
National Grid | LYNN | 174485 | 01902 | 3 | Solar | 05_12_2302E | 12/29/2010 | 12/29/2010 | 12 | 0 | 12 | 01/21/2011 | 01/21/2011 | 1449 | 0 | 1449 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2011 |  | 12/31/2016 | N | EXP | 2132 |  |  | 0 | 0 | 0 | 1/18/2013 | 1/18/2013 |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 662609 | 01060 | 3.77 | Solar | 05_07_6W2 | 12/31/2024 | 02/07/2025 | 5 | 1 | 4 | 02/10/2025 | 02/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | COHASSET | 536831 | 02025 | 6 | Solar | 05_12_22W2 | 07/14/2023 | 07/17/2023 | 1 | 0 | 1 | 07/18/2023 | 07/18/2023 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 |  | 9/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2024 | Connected |  | N
National Grid | LYNN | 714730 | 01902 | 12.6 | Solar | 05_09_901W1 | 08/26/2025 | 10/21/2025 | 3 | 1 | 2 | 10/22/2025 | 10/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2025 |  | 12/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2026 | Connected |  | N
National Grid | WEYMOUTH | 295339 | 02191 | 10 | Solar | 05_07_96W41 | 06/13/2020 | 06/18/2020 | 3 | 0 | 3 | 06/19/2020 | 06/19/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2020 | Connected |  | N
National Grid | LYNN | 174562 | 01902 | 600 | Wind | 05_12_2305 | 09/30/2011 | 09/30/2011 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2011 | 12/09/2011 | 30 | 0 | 30 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2013 |  | 10/31/2012 | N | STD | 292 |  |  | 0 | 0 | 0 | 1/7/2014 | 1/7/2014 | 1/22/2014 | Connected |  | N
National Grid | NORTHAMPTON | 175158 | 01060 | 95 | Solar | 05_07_70J1 | 08/20/2012 | 08/20/2012 | 7 | 0 | 7 | 08/30/2012 | 08/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2012 |  | 11/1/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 4/2/2013 | 4/2/2013 | 6/18/2013 | Connected |  | N
National Grid | COHASSET | 550854 | 02025 | 6 | Solar | 05_12_22W2 | 09/06/2023 | 09/25/2023 | 14 | 13 | 1 | 09/26/2023 | 09/26/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 11/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2024 | Connected |  | N
National Grid | LYNN | 648271 | 01902 | 80 | Solar | 05_09_901W2 | 10/18/2024 | 01/02/2025 | 49 | 39 | 10 | 01/03/2025 | 01/03/2025 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 |  | 5/6/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WEYMOUTH | 336658 | 02191 | 66.6 | Solar | 05_07_96W41 | 01/15/2021 | 01/26/2021 | 5 | 0 | 5 | 01/27/2021 | 01/27/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 3/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 661151 | 01907 | 2000 | Other | 05_12_2306 | 08/11/2025 |  | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 751944 | 01060 | 13.36 | Solar | 05_07_712J1 | 02/18/2026 | 02/24/2026 | 3 | 1 | 2 | 03/12/2026 | 03/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | COHASSET | 552910 | 02025 | 14.04 | Solar | 05_12_22W2 | 10/25/2023 | 10/31/2023 | 4 | 1 | 3 | 11/01/2023 | 11/01/2023 | 56 | 32 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 691176 | 01902 | 20 | Solar | 05_09_901W2 | 05/13/2025 | 05/20/2025 | 4 | 1 | 3 | 05/21/2025 | 05/21/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WEYMOUTH | 336653 | 02191 | 233.2 | Solar | 05_07_96W41 | 01/15/2021 | 01/26/2021 | 5 | 0 | 5 | 01/27/2021 | 01/27/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 175063 | 01902 | 2880 | Solar | 05_12_2307 | 10/23/2012 | 10/23/2012 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/06/2012 | 12/27/2012 | 26 | 0 | 26 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2014 |  | 7/1/2013 | N | STD | 255 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 174588 | 01060 | 30 | Solar | 05_07_712J1 | 08/29/2011 | 08/29/2011 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2011 |  | 8/4/2012 | N | EXP | 264 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 7/3/2012 | Connected |  | N
National Grid | COHASSET | 579935 | 02025 | 7.6 | Solar | 05_12_22W2 | 12/29/2023 | 01/12/2024 | 9 | 7 | 2 | 01/16/2024 | 01/16/2024 | 48 | 28 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 8/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | LYNN | 757652 | 01902 | 40 | Solar | 05_09_901W2 | 03/19/2026 | 03/24/2026 | 3 | 0 | 3 | 03/25/2026 | 03/25/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEYMOUTH | 336643 | 02191 | 250 | Solar | 05_07_96W41 | 01/28/2021 | 02/03/2021 | 3 | 0 | 3 | 02/04/2021 | 02/04/2021 | 42 | 20 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 723274 | 01902 | 650 | Solar | 05_12_2327 | 03/09/2026 |  | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | NORTHAMPTON | 175363 | 01060 | 5 | Solar | 05_07_712J1 | 11/14/2014 | 11/14/2014 | 4 | 0 | 4 | 11/21/2014 | 11/21/2014 | 442 | 0 | 442 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 |  | 1/31/2015 | N | EXP | 67 |  |  | 0 | 0 | 0 | 2/19/2015 | 2/19/2015 |  | Withdrawn |  | N
National Grid | COHASSET | 589445 | 02025 | 8.99 | Solar | 05_12_22W2 | 02/21/2024 | 02/26/2024 | 3 | 0 | 3 | 02/27/2024 | 02/27/2024 | 8 | 0 | 8 | 04/30/2024 | 02/21/2025 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 02/21/2025 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 7/1/2025 | N | EXP | 365 | 08/20/2024 | 03/03/2025 | 196 | 0 | 196 |  |  | 3/11/2025 | Connected |  | N
National Grid | SALEM | 177630 | 01970 | 80.5 | Solar | 05_09_901W2 | 05/23/2017 | 05/23/2017 | 2 | 0 | 2 | 05/26/2017 | 05/26/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 | 05/23/2017 | 5/29/2018 | Y | EXP | 362 | 02/28/2017 | 08/08/2017 | 112 | 0 | 112 |  |  | 5/17/2018 | Connected |  | N
National Grid | WEYMOUTH | 341800 | 02191 | 11.4 | Solar | 05_07_96W41 | 02/11/2021 | 02/17/2021 | 2 | 0 | 2 | 02/18/2021 | 02/18/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 174252 | 01902 | 450 | Solar | 05_12_2327 | 02/27/2012 | 02/27/2012 | 27 | 0 | 27 | 04/10/2012 | 04/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2012 |  | 6/15/2012 | N | EXP | 181 |  |  | 0 | 0 | 0 | 12/31/2012 | 12/31/2012 | 12/31/2012 | Connected |  | N
National Grid | NORTHAMPTON | 175397 | 01060 | 475.2 | Solar | 05_07_712J1 | 11/17/2014 | 11/17/2014 | 4 | 0 | 4 | 11/24/2014 | 11/24/2014 | 242 | 4 | 238 | 07/31/2015 | 11/16/2015 | 73 | 0 | 73 |  |  | 0 | 0 | 0 | 11/16/2015 | 73 | 0 | 73 |  |  | 0 | 0 | 0 |  |  | 2/15/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 589414 | 02025 | 5.76 | Solar | 05_12_22W2 | 02/21/2024 | 02/26/2024 | 3 | 0 | 3 | 02/27/2024 | 02/27/2024 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | LYNN | 196403 | 01905 | 72 | Solar | 05_09_901W2 | 09/19/2018 | 09/21/2018 | 1 | 0 | 1 | 09/24/2018 | 09/24/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 |  | 2/7/2022 | N | EXP | 493 |  |  | 0 | 0 | 0 |  |  | 1/25/2022 | Connected |  | N
National Grid | PEMBROKE | 352066 | 02359 | 7.6 | Solar | 05_07_96W41 | 04/21/2021 | 04/22/2021 | 0 | 0 | 0 | 04/23/2021 | 04/23/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 4/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2021 | Connected |  | N
National Grid | LYNN | 174956 | 01902 | 260 | Solar | 05_12_2335 | 02/28/2013 | 02/28/2013 | 3 | 0 | 3 | 03/11/2013 | 03/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2013 |  | 7/31/2013 | N | EXP | 54 |  |  | 0 | 0 | 0 | 12/19/2013 | 12/19/2013 | 12/19/2013 | Connected |  | N
National Grid | NORTHAMPTON | 176074 | 01060 | 7.6 | Solar | 05_07_712J1 | 08/19/2015 | 08/19/2015 | 3 | 3 | 0 | 08/24/2015 | 08/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 | 08/19/2015 | 8/24/2016 | Y | EXP | 350 | 01/11/2016 | 02/19/2016 | 27 | 0 | 27 | 5/16/2016 | 5/16/2016 | 5/20/2016 | Connected |  | N
National Grid | COHASSET | 594697 | 02025 | 6 | Solar | 05_12_22W2 | 03/07/2024 | 03/14/2024 | 5 | 0 | 5 | 03/15/2024 | 03/15/2024 | 5 | 0 | 5 | 05/14/2024 | 06/05/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 06/05/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 10/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2024 | Connected |  | N
National Grid | AYER | 277573 | 01432 | 0 | Solar | 05_09_901W2 | 01/31/2020 | 02/14/2020 | 10 | 9 | 1 | 02/18/2020 | 02/18/2020 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 |  | 2/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2020 | Connected |  | N
National Grid | BROCKTON | 409713 | 02302 | 7.6 | Solar | 05_07_96W41 | 02/08/2022 | 02/11/2022 | 4 | 3 | 1 | 02/14/2022 | 02/14/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  | 3/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2022 | Connected |  | N
National Grid | LYNN | 435099 | 01902 | 0 | Other | 05_12_2335 | 07/05/2022 | 10/28/2022 | 81 | 71 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2022 | 11/30/2022 | 21 | 1 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 176275 | 01060 | 10 | Solar | 05_07_712J1 | 05/01/2015 | 05/01/2015 | 70 | 70 | 0 | 08/18/2015 | 08/18/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 | 05/01/2015 | 2/2/2019 | Y | EXP | 1242 | 11/10/2016 | 11/22/2016 | 7 | 0 | 7 |  |  | 1/31/2019 | Connected |  | N
National Grid | COHASSET | 602059 | 02025 | 11.6 | Solar | 05_12_22W2 | 04/09/2024 | 04/10/2024 | 1 | 0 | 1 | 04/11/2024 | 04/11/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 | 04/09/2024 | 5/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 590297 | 02151 | 60 | Solar | 05_09_901W2 | 02/20/2024 |  | 46 | 37 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 458657 | 02302 | 300 | Solar | 05_07_96W41 | 10/26/2022 | 12/19/2022 | 36 | 26 | 10 |  |  | 28 | 5 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 177936 | 01902 | 300 | Natural Gas | 05_12_2338 | 06/20/2017 | 06/20/2017 | 4 | 0 | 4 | 06/26/2017 | 06/26/2017 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2017 |  | 7/27/2018 | N | EXP | 338 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 176437 | 01060 | 10 | Solar | 05_07_712J1 | 03/16/2016 | 03/16/2016 | 3 | 3 | 0 | 03/22/2016 | 03/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/16/2016 | 3/21/2017 | Y | EXP | 343 | 12/14/2016 | 01/05/2017 | 14 | 0 | 14 | 1/19/2017 | 1/19/2017 | 1/23/2017 | Connected |  | N
National Grid | COHASSET | 619036 | 02025 | 10 | Solar | 05_12_22W2 | 06/19/2024 | 06/28/2024 | 3 | 2 | 1 | 07/01/2024 | 07/01/2024 | 28 | 15 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 | 06/19/2024 | 8/13/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | GLOUCESTER | 687294 | 01930 | 7.6 | Solar | 05_09_901W2 | 04/24/2025 | 05/27/2025 | 1 | 0 | 1 | 06/03/2025 | 06/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | BROCKTON | 470354 | 02302 | 150 | Solar | 05_07_96W41 | 10/25/2022 | 03/17/2023 | 97 | 87 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 194606 | 01902 | 336 | Solar | 05_12_2338 | 10/08/2018 | 10/15/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2018 |  | 8/30/2021 | N | EXP | 385 |  |  | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | NORTHAMPTON | 177178 | 01060 | 3.8 | Solar | 05_07_712J1 | 06/05/2016 | 06/05/2016 | 8 | 8 | 0 | 06/20/2016 | 06/20/2016 | 154 | 0 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/12/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 623165 | 02025 | 5.76 | Solar | 05_12_22W2 | 07/08/2024 | 07/16/2024 | 1 | 0 | 1 | 07/17/2024 | 07/17/2024 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 687680 | 01930 | 7.6 | Solar | 05_09_901W3 | 04/25/2025 | 06/09/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 22 | 9 | 13 | 08/11/2025 | 11/13/2025 | 66 | 42 | 24 |  |  | 0 | 0 | 0 | 11/13/2025 | 66 | 42 | 24 |  |  | 0 | 0 | 0 | 11/17/2025 |  | 11/25/2026 | N | EXP | 365 | 02/13/2026 |  | 48 | 0 | 48 |  |  |  | Construction |  | Y
National Grid | BROCKTON | 490600 | 02302 | 20.01 | Solar | 05_07_96W41 | 01/09/2023 | 01/19/2023 | 8 | 7 | 1 | 01/20/2023 | 01/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 175156 | 01902 | 82.8 | Solar | 05_12_2344 | 11/12/2013 | 11/12/2013 | 6 | 0 | 6 | 11/21/2013 | 11/21/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2013 |  | 12/31/2013 | N | EXP | 28 |  |  | 0 | 0 | 0 | 4/24/2014 | 4/24/2014 | 4/24/2014 | Connected |  | N
National Grid | NORTHAMPTON | 190446 | 01060 | 15.2 | Solar | 05_07_712J1 | 07/11/2018 | 08/10/2018 | 8 | 0 | 8 | 08/13/2018 | 08/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2018 |  | 8/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2019 | Connected |  | N
National Grid | COHASSET | 632320 | 02025 | 3.8 | Solar | 05_12_22W2 | 08/14/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 743867 | 02176 | 13.3 | Solar | 05_09_901W3 | 01/07/2026 | 01/21/2026 | 2 | 0 | 2 | 02/13/2026 | 02/13/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROCKTON | 583288 | 02302 | 0 | Battery Add-On | 05_07_96W41 | 01/12/2024 | 02/01/2024 | 13 | 10 | 3 | 02/02/2024 | 02/02/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 01/12/2024 | 3/29/2025 | Y | EXP | 365 | 05/08/2024 | 05/07/2024 | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | LYNN | 176235 | 01902 | 4000 | Natural Gas | 05_12_2344 | 02/17/2015 | 02/17/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/24/2015 | 03/25/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 | 02/17/2015 | 6/15/2017 | Y | STD | 237 | 09/25/2017 | 09/25/2017 | 0 | 0 | 0 | 9/29/2017 | 9/29/2017 | 9/29/2017 | Connected |  | N
National Grid | NORTHAMPTON | 194058 | 01060 | 9.92 | Solar | 05_07_712J1 | 08/21/2018 | 10/04/2018 | 31 | 24 | 7 | 10/11/2018 | 10/11/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  | 11/14/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2019 | Connected |  | N
National Grid | COHASSET | 634484 | 02025 | 11.05 | Solar | 05_12_22W2 | 08/21/2024 |  | 41 | 41 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 747411 | 02176 | 37.6 | Solar | 05_09_901W3 | 01/26/2026 | 01/28/2026 | 2 | 0 | 2 | 01/29/2026 | 01/29/2026 | 18 | 1 | 17 | 03/24/2026 |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | BROCKTON | 656393 | 02302 | 0 | Other | 05_07_96W41 | 02/14/2025 | 03/20/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2025 | 04/17/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 190186 | 01902 | 50 | Solar | 05_12_2344 | 07/09/2018 | 07/13/2018 | 2 | 0 | 2 | 07/16/2018 | 07/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2018 |  | 12/30/2019 | N | EXP | 530 |  |  | 0 | 0 | 0 |  |  | 12/30/2019 | Connected |  | N
National Grid | NORTHAMPTON | 204159 | 01060 | 213.2 | Solar | 05_07_712J1 | 12/18/2018 | 01/24/2019 | 23 | 16 | 7 | 01/25/2019 | 01/25/2019 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 634846 | 02025 | 10 | Solar | 05_12_22W2 | 08/23/2024 | 08/28/2024 | 2 | 0 | 2 | 08/29/2024 | 08/29/2024 | 21 | 14 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 11/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | EVERETT | 752639 | 02149 | 11.5 | Solar | 05_09_901W3 | 02/23/2026 | 02/27/2026 | 2 | 0 | 2 | 03/12/2026 | 03/12/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 443129 | 02302 | 15.2 | Solar | 05_07_96W42 | 07/11/2022 | 07/12/2022 | 1 | 0 | 1 | 07/13/2022 | 07/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 |  | 8/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2023 | Connected |  | N
National Grid | LYNN | 195969 | 01902 | 240 | Solar | 05_12_2344 | 10/04/2018 | 10/26/2018 | 15 | 15 | 0 | 10/29/2018 | 10/29/2018 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2019 |  | 12/16/2019 | N | EXP | 265 |  |  | 0 | 0 | 0 |  |  | 12/30/2019 | Connected |  | N
National Grid | NORTHAMPTON | 293251 | 01060 | 7.6 | Solar | 05_07_712J1 | 07/30/2020 | 09/21/2020 | 34 | 27 | 7 | 09/22/2020 | 09/22/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2020 | 07/30/2020 | 7/29/2021 | Y | EXP | 365 | 12/15/2020 | 01/08/2021 | 24 | 0 | 24 |  |  | 2/6/2021 | Connected |  | N
National Grid | COHASSET | 634799 | 02025 | 7.6 | Solar | 05_12_22W2 | 08/22/2024 | 09/10/2024 | 4 | 0 | 4 | 09/11/2024 | 09/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | EVERETT | 756806 | 02149 | 0 | Solar | 05_09_901W3 | 03/25/2026 | 03/30/2026 | 2 | 0 | 2 | 03/31/2026 | 03/31/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 739875 | 02302 | 15.2 | Solar | 05_07_96W43 | 12/12/2025 |  | 74 | 74 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LYNN | 191794 | 01902 | 66.6 | Solar | 05_12_2344 | 07/25/2018 | 07/26/2018 | 0 | 0 | 0 | 07/27/2018 | 07/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  | 12/16/2019 | N | EXP | 503 |  |  | 0 | 0 | 0 |  |  | 12/30/2019 | Connected |  | N
National Grid | NORTHAMPTON | 324131 | 01062 | 5.76 | Solar | 05_07_712J1 | 04/07/2021 | 04/09/2021 | 1 | 0 | 1 | 04/12/2021 | 04/12/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 |  | 4/8/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 635909 | 02025 | 6 | Solar | 05_12_22W2 | 08/28/2024 | 09/10/2024 | 4 | 0 | 4 | 09/11/2024 | 09/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 174610 | 02155 | 22 | Solar | 05_09_901W3 | 10/19/2010 | 10/19/2010 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2010 |  | 1/3/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 1/3/2012 | Connected |  | N
National Grid | BROCKTON | 174137 | 02302 | 20.5 | Solar | 05_07_96W43 | 04/06/2012 | 04/06/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2012 |  | 6/4/2012 | N | EXP | 59 |  |  | 0 | 0 | 0 | 1/4/2013 | 1/4/2013 | 1/11/2013 | Connected |  | N
National Grid | LYNN | 281295 | 01902 | 0 | Other | 05_12_2344 | 03/04/2020 | 03/11/2020 | 5 | 2 | 3 |  |  | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 03/04/2020 | 2/10/2024 | Y | STD | 70 |  |  | 0 | 0 | 0 |  |  | 12/29/2023 | Connected |  | N
National Grid | NORTHAMPTON | 324110 | 01062 | 7.6 | Solar | 05_07_712J1 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 | 11/25/2020 | 1/25/2022 | Y | EXP | 365 | 08/12/2021 | 09/22/2021 | 36 | 3 | 33 |  |  | 10/6/2021 | Connected |  | N
National Grid | COHASSET | 637467 | 02025 | 5.76 | Solar | 05_12_22W2 | 09/03/2024 | 10/09/2024 | 5 | 0 | 5 | 10/10/2024 | 10/10/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/03/2024 | 1/8/2026 | Y | EXP | 365 | 12/19/2024 | 08/07/2025 | 232 | 0 | 232 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 175153 | 02155 | 40 | Solar | 05_09_901W3 | 11/05/2013 | 11/05/2013 | 5 | 0 | 5 | 11/14/2013 | 11/14/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2013 |  | 12/31/2013 | N | EXP | 29 |  |  | 0 | 0 | 0 | 12/9/2013 | 12/9/2013 | 2/28/2014 | Connected |  | N
National Grid | ABINGTON | 176289 | 02351 | 18.4 | Solar | 05_07_96W43 | 07/10/2015 | 07/10/2015 | 11 | 11 | 0 | 07/28/2015 | 07/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2015 | 07/10/2015 | 7/18/2016 | Y | EXP | 347 | 01/20/2015 | 09/03/2015 | 156 | 11 | 145 | 8/15/2016 | 8/15/2016 | 8/15/2016 | Connected |  | N
National Grid | LYNN | 355956 | 01902 | 240 | Solar | 05_12_2344 | 07/23/2021 | 05/11/2022 | 201 | 191 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 07/23/2021 | 9/2/2026 | Y | EXP | 514 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 330887 | 01060 | 15.2 | Solar | 05_07_712J1 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 | 12/10/2020 | 12/4/2022 | Y | EXP | 365 | 09/03/2021 | 10/08/2021 | 36 | 0 | 36 |  |  | 12/2/2022 | Connected |  | N
National Grid | COHASSET | 643815 | 02025 | 3.8 | Solar | 05_12_22W2 | 10/01/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2024 | 10/01/2024 | 12/2/2025 | Y | EXP | 365 | 12/19/2024 | 12/24/2024 | 6 | 0 | 6 |  |  | 2/20/2025 | Connected |  | N
National Grid | MEDFORD | 175539 | 02155 | 0 | Solar | 05_09_901W3 | 12/04/2014 | 12/04/2014 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2014 | 01/09/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 177100 | 02302 | 20 | Solar | 05_07_96W43 | 05/26/2016 | 05/26/2016 | 3 | 3 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2016 |  | 5/31/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 | 9/2/2016 | 9/2/2016 | 9/2/2016 | Connected |  | N
National Grid | LYNN | 753221 | 01902 | 240 | Solar | 05_12_2349 | 03/24/2026 |  | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | NORTHAMPTON | 382577 | 01060 | 240 | Solar | 05_07_712J1 | 11/11/2021 | 12/13/2021 | 21 | 15 | 6 |  |  | 40 | 2 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 644456 | 02061 | 6 | Solar | 05_12_22W2 | 10/02/2024 | 12/06/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 175749 | 02155 | 11.8 | Solar | 05_09_901W3 | 10/30/2014 | 10/30/2014 | 6 | 0 | 6 | 11/10/2014 | 11/10/2014 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 177286 | 02302 | 0 | Solar | 05_07_96W43 | 06/16/2016 | 06/16/2016 | 0 | 0 | 0 | 06/16/2016 | 06/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2016 |  | 6/21/2017 | N | EXP | 288 |  |  | 0 | 0 | 0 | 3/16/2017 | 3/16/2017 | 3/21/2017 | Connected |  | N
National Grid | LYNN | 175311 | 01902 | 1560 | Natural Gas | 05_12_2349 | 06/27/2014 | 06/27/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/07/2014 | 08/08/2014 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2015 | 06/27/2014 | 11/22/2019 | Y | STD | 1581 | 08/06/2019 | 08/05/2019 | 0 | 0 | 0 |  |  | 11/22/2019 | Connected |  | N
National Grid | NORTHAMPTON | 492024 | 01062 | 6 | Solar | 05_07_712J1 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N
National Grid | NORWELL | 647202 | 02061 | 7.6 | Solar | 05_12_22W2 | 10/15/2024 | 11/12/2024 | 17 | 13 | 4 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | MEDFORD | 175814 | 02155 | 7.6 | Solar | 05_09_901W3 | 05/18/2015 | 05/18/2015 | 4 | 4 | 0 | 05/28/2015 | 05/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2015 |  | 10/30/2015 | N | EXP | 134 |  |  | 0 | 0 | 0 | 9/10/2015 | 9/10/2015 | 9/10/2015 | Connected |  | N
National Grid | BROCKTON | 177295 | 02302 | 12.8 | Solar | 05_07_96W43 | 08/26/2016 | 08/26/2016 | 0 | 0 | 0 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2016 | 08/26/2016 | 9/3/2017 | Y | EXP | 338 | 02/24/2017 | 02/24/2017 | 0 | 0 | 0 | 8/10/2017 | 8/10/2017 | 8/10/2017 | Connected |  | N
National Grid | LYNN | 409260 | 01902 | 480 | Solar | 05_12_2364 | 06/15/2022 | 07/13/2022 | 17 | 8 | 9 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | NORTHAMPTON | 513457 | 01062 | 0 | Solar | 05_07_712J1 | 03/21/2023 |  | 144 | 128 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 650924 | 02061 | 11.05 | Solar | 05_12_22W2 | 10/30/2024 | 01/30/2025 | 33 | 27 | 6 | 01/31/2025 | 01/31/2025 | 159 | 133 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 177682 | 02155 | 90 | Solar | 05_09_901W3 | 07/25/2017 | 07/25/2017 | 7 | 6 | 1 | 08/04/2017 | 08/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 |  | 7/31/2018 | N | EXP | 337 |  |  | 0 | 0 | 0 | 3/2/2018 | 3/2/2018 | 3/22/2018 | Connected |  | N
National Grid | BROCKTON | 177460 | 02302 | 20 | Solar | 05_07_96W43 | 12/09/2016 | 12/09/2016 | 0 | 0 | 0 | 12/12/2016 | 12/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2016 |  | 12/17/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 1/30/2017 | 1/30/2017 | 2/9/2017 | Connected |  | N
National Grid | LYNN | 434942 | 01902 | 240 | Solar | 05_12_2364 | 09/23/2022 | 10/05/2022 | 8 | 0 | 8 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | NORTHAMPTON | 559691 | 01060 | 8.19 | Solar | 05_07_712J1 | 10/24/2023 | 10/26/2023 | 3 | 1 | 2 | 10/27/2023 | 10/27/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 652324 | 02061 | 7.6 | Solar | 05_12_22W2 | 11/05/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | MEDFORD | 228970 | 02155 | 303.4 | Solar | 05_09_901W3 | 06/04/2019 | 06/14/2019 | 8 | 6 | 2 | 06/17/2019 | 06/17/2019 | 740 | 415 | 325 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 177937 | 02302 | 18 | Solar | 05_07_96W43 | 06/20/2017 | 06/20/2017 | 7 | 7 | 0 | 06/29/2017 | 06/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2017 |  | 6/25/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 | 11/14/2017 | 11/14/2017 | 12/5/2017 | Connected |  | N
National Grid | LYNN | 434644 | 01902 | 240 | Solar | 05_12_2364 | 06/06/2022 | 06/30/2022 | 17 | 10 | 7 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2026 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTHAMPTON | 528274 | 01062 | 6 | Solar | 05_07_712J1 | 05/30/2023 | 06/01/2023 | 3 | 2 | 1 | 06/02/2023 | 06/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 | 05/30/2023 | 9/28/2024 | Y | EXP | 365 | 09/06/2023 | 09/27/2023 | 22 | 0 | 22 |  |  | 10/6/2023 | Connected |  | N
National Grid | NORWELL | 655756 | 02061 | 10 | Solar | 05_12_22W2 | 12/02/2024 | 01/06/2025 | 19 | 14 | 5 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | SALEM | 250724 | 01970 | 10 | Solar | 05_09_901W3 | 08/26/2019 | 09/03/2019 | 4 | 0 | 4 | 09/04/2019 | 09/04/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2019 | Connected |  | N
National Grid | BROCKTON | 202681 | 02302 | 10 | Solar | 05_07_96W43 | 12/12/2018 | 01/10/2019 | 16 | 14 | 2 | 01/11/2019 | 01/11/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  | 7/1/2019 | N | EXP | 166 |  |  | 0 | 0 | 0 |  |  | 6/12/2019 | Connected |  | N
National Grid | LYNN | 174567 | 01902 | 2000 | Wind | 05_12_2364 | 07/13/2011 | 07/13/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/28/2011 | 09/13/2011 | 32 | 0 | 32 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2012 | 07/13/2011 | 10/31/2012 | Y | STD | 91 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/31/2012 | Connected |  | N
National Grid | NORTHAMPTON | 571401 | 01060 | 7.6 | Solar | 05_07_712J1 | 12/05/2023 | 12/08/2023 | 3 | 0 | 3 | 12/11/2023 | 12/11/2023 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 663491 | 02061 | 3.8 | Solar | 05_12_22W2 | 01/02/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 01/02/2025 | 4/11/2026 | Y | EXP | 365 | 06/14/2025 | 11/14/2025 | 154 | 0 | 154 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 281120 | 01970 | 3 | Solar | 05_09_901W3 | 04/08/2020 | 04/10/2020 | 1 | 1 | 0 | 04/13/2020 | 04/13/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 | 04/08/2020 | 4/9/2021 | Y | EXP | 365 | 08/29/2020 | 09/09/2020 | 11 | 0 | 11 |  |  | 12/14/2020 | Connected |  | N
National Grid | BROCKTON | 203231 | 02302 | 10 | Solar | 05_07_96W43 | 01/15/2019 | 01/30/2019 | 9 | 0 | 9 | 01/31/2019 | 01/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2019 | 01/15/2019 | 2/25/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2019 | Connected |  | N
National Grid | LYNN | 174566 | 01902 | 2000 | Wind | 05_12_2364 | 07/13/2011 | 07/13/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2012 | 07/13/2011 | 8/1/2012 | Y | STD | 0 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/31/2012 | Connected |  | N
National Grid | NORTHAMPTON | 626740 | 01060 | 7.6 | Solar | 05_07_712J1 | 07/22/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 669422 | 02061 | 7.6 | Solar | 05_12_22W2 | 02/01/2025 | 03/05/2025 | 4 | 1 | 3 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 02/01/2025 | 5/16/2026 | Y | EXP | 365 | 08/19/2025 | 08/25/2025 | 7 | 0 | 7 |  |  | 10/8/2025 | Connected |  | N
National Grid | GLOUCESTER | 312372 | 01930 | 57.6 | Solar | 05_09_901W3 | 09/14/2020 | 01/07/2022 | 1 | 0 | 1 | 09/17/2020 | 09/17/2020 | 59 | 37 | 22 | 12/28/2020 | 02/18/2021 | 35 | 0 | 35 |  |  | 0 | 0 | 0 | 02/18/2021 | 35 | 0 | 35 |  |  | 0 | 0 | 0 | 2/23/2021 |  | 7/22/2022 | N | EXP | 495 |  |  | 0 | 0 | 0 |  |  | 6/3/2022 | Connected |  | N
National Grid | EAST BRIDGEWATER | 300341 | 02333 | 30 | Solar | 05_07_96W43 | 07/11/2020 | 11/10/2020 | 85 | 71 | 14 | 11/12/2020 | 11/12/2020 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2020 | 07/11/2020 | 7/9/2021 | Y | EXP | 365 | 02/18/2021 | 04/07/2021 | 48 | 0 | 48 |  |  | 6/4/2021 | Connected |  | N
National Grid | LYNN | 174899 | 01902 | 2500 | Wind | 05_12_2364 | 10/28/2011 | 10/28/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 02/06/2012 | 49 | 0 | 49 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 10/28/2011 | 11/30/2012 | Y | STD | 12 | 11/20/2012 | 11/26/2012 | 3 | 0 | 3 | 12/10/2012 | 12/10/2012 | 12/14/2012 | Connected |  | N
National Grid | NORTHAMPTON | 642715 | 01060 | 4.64 | Solar | 05_07_712J1 | 09/25/2024 | 01/03/2025 | 4 | 0 | 4 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | NORWELL | 669921 | 02061 | 3.8 | Solar | 05_12_22W2 | 02/04/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | GLOUCESTER | 349680 | 01930 | 0 | Solar | 05_09_901W3 | 03/29/2021 | 03/31/2021 | 2 | 2 | 0 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  | 3/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2021 | Connected |  | N
National Grid | BROCKTON | 342336 | 02302 | 7.6 | Solar | 05_07_96W43 | 02/16/2021 | 02/17/2021 | 0 | 0 | 0 | 02/18/2021 | 02/18/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 | 02/16/2021 | 1/9/2023 | Y | EXP | 450 | 09/14/2021 | 10/11/2021 | 28 | 0 | 28 |  |  | 12/5/2022 | Connected |  | N
National Grid | LYNN | 174823 | 01902 | 2000 | Solar | 05_12_2365 | 07/30/2012 | 07/30/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2012 | 10/19/2012 | 49 | 0 | 49 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2013 | 07/30/2012 | 4/1/2014 | Y | STD | 336 |  |  | 0 | 0 | 0 | 5/1/2014 | 5/1/2014 | 5/8/2014 | Connected |  | N
National Grid | NORTHAMPTON | 650146 | 01060 | 10 | Solar | 05_07_712J1 | 11/07/2024 | 11/20/2024 | 3 | 0 | 3 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 686814 | 02061 | 5.76 | Solar | 05_12_22W2 | 04/22/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2025 | Connected |  | N
National Grid | GLOUCESTER | 362762 | 01930 | 7.6 | Solar | 05_09_901W3 | 07/04/2021 | 07/07/2021 | 1 | 0 | 1 | 07/08/2021 | 07/08/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2021 | 07/04/2021 | 3/2/2023 | Y | EXP | 365 | 02/25/2022 | 03/01/2022 | 5 | 0 | 5 |  |  | 3/29/2022 | Connected |  | Y
National Grid | BROCKTON | 344801 | 02302 | 15.2 | Solar | 05_07_96W43 | 03/03/2021 | 03/09/2021 | 3 | 0 | 3 | 03/10/2021 | 03/10/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2021 | Connected |  | N
National Grid | LYNN | 396930 | 01902 | 1000 | Solar | 05_12_2365 | 04/27/2022 |  | 144 | 136 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 656337 | 01062 | 3.48 | Solar | 05_07_712J1 | 11/22/2024 | 02/13/2025 | 11 | 8 | 3 | 02/14/2025 | 02/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 | 11/22/2024 | 4/10/2026 | Y | EXP | 365 | 05/17/2025 | 08/08/2025 | 84 | 0 | 84 |  |  | 9/12/2025 | Connected |  | N
National Grid | NORWELL | 694314 | 02061 | 3.8 | Solar | 05_12_22W2 | 05/29/2025 | 06/23/2025 | 3 | 0 | 3 | 06/30/2025 | 06/30/2025 | 38 | 24 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 375735 | 01930 | 8.505 | Solar | 05_09_901W3 | 08/23/2021 | 01/04/2022 | 20 | 17 | 3 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 |  | 1/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 376126 | 02302 | 19 | Solar | 05_07_96W43 | 08/16/2021 | 08/18/2021 | 2 | 0 | 2 | 08/19/2021 | 08/19/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2021 |  | 1/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2022 | Connected |  | N
National Grid | SWAMPSCOTT | 621831 | 01907 | 120 | Solar | 05_12_2370 | 07/08/2024 | 12/20/2024 | 114 | 103 | 11 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 07/08/2024 | 3/4/2027 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | NORTHAMPTON | 664339 | 01060 | 7.6 | Solar | 05_07_712J1 | 01/07/2025 | 01/31/2025 | 6 | 0 | 6 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | NORWELL | 701684 | 02061 | 15.2 | Solar | 05_12_22W2 | 06/27/2025 | 07/02/2025 | 3 | 0 | 3 | 07/03/2025 | 07/03/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 378526 | 01930 | 6 | Solar | 05_09_901W3 | 10/01/2021 | 12/29/2021 | 4 | 0 | 4 | 10/08/2021 | 10/08/2021 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 4/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | N
National Grid | BROCKTON | 500310 | 02302 | 8.7 | Solar | 05_07_96W43 | 02/17/2023 | 02/21/2023 | 1 | 0 | 1 | 02/22/2023 | 02/22/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2023 | Connected |  | N
National Grid | LYNN | 186728 | 01902 | 88 | Solar | 05_12_2370 | 05/30/2018 | 05/30/2018 | 0 | 0 | 0 | 06/04/2018 | 06/04/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2018 |  | 5/26/2020 | N | EXP | 510 |  |  | 0 | 0 | 0 |  |  | 8/11/2020 | Connected |  | N
National Grid | NORTHAMPTON | 666538 | 01060 | 11.5 | Solar | 05_07_712J1 | 01/17/2025 | 02/07/2025 | 14 | 10 | 4 | 02/10/2025 | 02/10/2025 | 56 | 34 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 01/17/2025 | 9/29/2026 | Y | EXP | 365 | 10/24/2025 | 11/13/2025 | 21 | 0 | 21 |  |  | 11/15/2025 | Connected |  | Y
National Grid | NORWELL | 705143 | 02061 | 6 | Solar | 05_12_22W2 | 07/15/2025 | 07/30/2025 | 1 | 0 | 1 | 08/11/2025 | 08/11/2025 | 58 | 47 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2026 | Connected |  | N
National Grid | GLOUCESTER | 411322 | 01930 | 10 | Solar | 05_09_901W3 | 02/15/2022 | 02/22/2022 | 4 | 0 | 4 | 02/23/2022 | 02/23/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 |  | 4/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2022 | Connected |  | N
National Grid | BROCKTON | 511876 | 02302 | 13.6 | Solar | 05_07_96W43 | 03/17/2023 | 04/04/2023 | 13 | 11 | 2 | 04/05/2023 | 04/05/2023 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2023 |  | 6/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2023 | Connected |  | N
National Grid | LYNN | 174486 | 01902 | 500 | Diesel | 05_12_2401 | 12/09/2010 | 12/09/2010 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2011 | 02/23/2011 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2011 |  | 10/31/2012 | N | STD | 505 |  |  | 0 | 0 | 0 | 9/19/2012 | 9/19/2012 | 9/24/2012 | Connected |  | N
National Grid | NORTHAMPTON | 680819 | 01060 | 15.76 | Solar | 05_07_712J1 | 03/31/2025 | 04/03/2025 | 3 | 0 | 3 | 04/04/2025 | 04/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | NORWELL | 705139 | 02061 | 5.76 | Solar | 05_12_22W2 | 07/15/2025 | 07/31/2025 | 1 | 0 | 1 | 08/07/2025 | 08/07/2025 | 54 | 25 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 456714 | 01915 | 17.4 | Solar | 05_09_901W3 | 09/06/2022 | 09/08/2022 | 3 | 1 | 2 | 09/09/2022 | 09/09/2022 | 48 | 27 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2022 | 09/06/2022 | 2/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2023 | Connected |  | N
National Grid | EAST BRIDGEWATER | 541284 | 02333 | 15.2 | Solar | 05_07_96W43 | 07/17/2023 | 07/19/2023 | 2 | 0 | 2 | 07/20/2023 | 07/20/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2023 |  | 9/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2023 | Connected |  | N
National Grid | SWAMPSCOTT | 177102 | 01907 | 1332 | Solar | 05_12_2401 | 05/26/2016 | 05/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/27/2016 | 07/07/2016 | 26 | 9 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2016 | 05/26/2016 | 9/29/2017 | Y | STD | 302 | 09/22/2017 | 02/14/2018 | 92 | 0 | 92 | 9/18/2017 | 9/18/2017 | 9/22/2017 | Connected |  | N
National Grid | NORTHAMPTON | 713540 | 01060 | 5.76 | Solar | 05_07_712J1 | 08/20/2025 | 09/19/2025 | 4 | 0 | 4 | 11/21/2025 | 11/21/2025 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 | 08/20/2025 | 1/2/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2026 | Connected |  | N
National Grid | NORWELL | 704803 | 02061 | 5 | Solar | 05_12_22W2 | 07/14/2025 | 07/25/2025 | 29 | 24 | 5 | 09/17/2025 | 09/17/2025 | 51 | 32 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2026 | Connected |  | N
National Grid | BEVERLY | 460740 | 01915 | 15.2 | Solar | 05_09_901W3 | 09/28/2022 | 10/03/2022 | 3 | 2 | 1 | 10/04/2022 | 10/04/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 |  | 11/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | N
National Grid | BROCKTON | 562218 | 02302 | 17.45 | Solar | 05_07_96W43 | 10/12/2023 | 11/06/2023 | 17 | 15 | 2 | 11/07/2023 | 11/07/2023 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2024 |  | 1/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | LYNN | 318011 | 01902 | 250 | Solar | 05_12_2401 | 10/13/2020 | 10/23/2020 | 8 | 1 | 7 |  |  | 44 | 21 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2021 | 10/13/2020 | 11/13/2023 | Y | STD | 604 | 01/18/2023 | 10/31/2023 | 287 | 0 | 287 |  |  | 11/16/2023 | Connected |  | N
National Grid | NORTHAMPTON | 715090 | 01062 | 3.8 | Solar | 05_07_712J1 | 08/28/2025 | 10/01/2025 | 3 | 0 | 3 | 10/23/2025 | 10/23/2025 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 | 08/28/2025 | 12/16/2026 | Y | EXP | 365 | 02/07/2026 | 02/06/2026 | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | NORWELL | 709020 | 02061 | 5.76 | Solar | 05_12_22W2 | 08/01/2025 | 09/02/2025 | 3 | 0 | 3 | 09/03/2025 | 09/03/2025 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 477384 | 01970 | 10 | Solar | 05_09_901W3 | 04/10/2023 | 04/11/2023 | 1 | 0 | 1 | 04/12/2023 | 04/12/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 583818 | 02302 | 21.735 | Solar | 05_07_96W43 | 01/19/2024 | 02/13/2024 | 18 | 16 | 2 | 02/14/2024 | 02/14/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | LYNN | 433145 | 01902 | 0 | Other | 05_12_2401 | 07/06/2022 | 10/28/2022 | 80 | 72 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2022 | 11/22/2022 | 16 | 0 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2024 | 07/06/2022 | 6/21/2026 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 721528 | 01060 | 13.3 | Wind | 05_07_712J1 | 09/24/2025 | 10/09/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 61 | 52 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 708270 | 02061 | 5.76 | Solar | 05_12_22W2 | 07/29/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 46 | 32 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2026 | Connected |  | N
National Grid | SALEM | 479453 | 01970 | 10 | Solar | 05_09_901W3 | 02/27/2023 | 03/01/2023 | 2 | 0 | 2 | 03/02/2023 | 03/02/2023 | 23 | 0 | 23 | 05/26/2023 | 06/28/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 06/28/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 6/20/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 600468 | 02302 | 0 | Solar | 05_07_96W43 | 05/03/2024 | 06/26/2024 | 36 | 34 | 2 | 06/27/2024 | 06/27/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 8/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | LYNN | 215897 | 01902 | 400 | Solar | 05_14_1314 | 04/01/2019 | 04/05/2019 | 19 | 7 | 12 | 04/08/2019 | 04/08/2019 | 13 | 0 | 13 | 07/10/2019 | 07/09/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2019 |  | 12/16/2019 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  | 12/20/2019 | Connected |  | N
National Grid | NORTHAMPTON | 347679 | 01062 | 812.5 | Solar | 05_07_75W1 | 04/22/2021 | 09/10/2021 | 98 | 87 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2021 | 10/07/2021 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 | 04/22/2021 | 8/7/2026 | Y | STD | 518 | 02/01/2025 |  | 425 | 241 | 184 |  |  |  | Construction |  | N
National Grid | NORWELL | 739114 | 02061 | 17.92 | Solar | 05_12_22W2 | 12/17/2025 | 12/22/2025 | 3 | 2 | 1 | 12/23/2025 | 12/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2026 | Connected |  | N
National Grid | EVERETT | 494316 | 02149 | 5 | Solar | 05_09_901W3 | 01/26/2023 | 01/27/2023 | 1 | 0 | 1 | 01/30/2023 | 01/30/2023 | 20 | 2 | 18 | 03/02/2023 | 03/23/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 03/23/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 7/24/2024 | N | EXP | 365 | 07/12/2023 | 07/25/2023 | 14 | 0 | 14 |  |  | 8/3/2023 | Connected |  | Y
National Grid | BROCKTON | 622833 | 02302 | 10 | Solar | 05_07_96W43 | 08/07/2024 | 08/13/2024 | 4 | 2 | 2 | 08/14/2024 | 08/14/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | LYNN | 178156 | 01092 | 176 | Solar | 05_14_1319 | 12/22/2017 | 12/22/2017 | 33 | 29 | 4 | 02/13/2018 | 02/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2018 |  | 1/31/2019 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  | 1/30/2019 | Connected |  | N
National Grid | NORTHAMPTON | 370680 | 01060 | 675 | Solar | 05_07_75W1 | 08/12/2021 | 09/10/2021 | 20 | 13 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2021 | 10/07/2021 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 | 08/12/2021 | 8/21/2026 | Y | STD | 518 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORWELL | 174620 | 02061 | 60 | Solar | 05_12_22W3 | 02/18/2011 | 02/18/2011 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2011 |  | 1/6/2012 | N | EXP | 248 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 1/6/2012 | Connected |  | N
National Grid | EVERETT | 510764 | 02149 | 7.54 | Solar | 05_09_901W3 | 05/10/2023 | 05/15/2023 | 3 | 0 | 3 | 05/16/2023 | 05/16/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2023 | Connected |  | N
National Grid | BROCKTON | 628857 | 02302 | 10 | Solar | 05_07_96W43 | 07/30/2024 | 08/07/2024 | 1 | 0 | 1 | 08/08/2024 | 08/08/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 | 07/30/2024 | 10/19/2025 | Y | EXP | 405 | 12/19/2024 | 01/27/2025 | 40 | 0 | 40 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 587976 | 01902 | 950 | Natural Gas | 05_14_1321 | 03/07/2024 | 07/31/2024 | 100 | 90 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/01/2024 | 09/25/2024 | 39 | 19 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | NORTHAMPTON | 174532 | 01062 | 520 | Solar | 05_07_75W1 | 02/18/2011 | 02/18/2011 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/01/2011 | 05/05/2012 | 232 | 0 | 232 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2012 |  | 10/31/2012 | N | STD | 168 |  |  | 0 | 0 | 0 | 3/6/2013 | 3/6/2013 | 3/6/2013 | Connected |  | N
National Grid | NORWELL | 174619 | 02061 | 350 | Solar | 05_12_22W3 | 02/18/2011 | 02/18/2011 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2011 |  | 2/7/2012 | N | EXP | 209 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 2/7/2012 | Connected |  | N
National Grid | EVERETT | 529560 | 02149 | 10 | Solar | 05_09_901W3 | 06/15/2023 | 06/22/2023 | 4 | 2 | 2 | 06/23/2023 | 06/23/2023 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 | 06/15/2023 | 8/28/2024 | Y | EXP | 365 | 08/30/2023 | 08/29/2023 | 0 | 0 | 0 |  |  | 9/1/2023 | Connected |  | N
National Grid | BROCKTON | 633759 | 02302 | 15.2 | Solar | 05_07_96W43 | 08/26/2024 | 09/03/2024 | 6 | 5 | 1 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 9/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2024 | Connected |  | N
National Grid | LYNN | 174275 | 01902 | 380 | Solar | 05_14_1321 | 12/20/2011 | 12/20/2011 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2012 |  | 4/1/2012 | N | EXP | 31 |  |  | 0 | 0 | 0 | 6/15/2012 | 6/15/2012 | 7/6/2012 | Connected |  | N
National Grid | NORTHAMPTON | 175513 | 01060 | 250 | Solar | 05_07_75W1 | 03/26/2014 | 03/26/2014 | 6 | 0 | 6 | 04/04/2014 | 04/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2014 |  | 7/31/2014 | N | EXP | 90 |  |  | 0 | 0 | 0 | 6/12/2014 | 6/12/2014 | 3/13/2015 | Connected |  | N
National Grid | NORWELL | 178037 | 02061 | 11.4 | Solar | 05_12_22W3 | 10/27/2017 | 10/27/2017 | 4 | 4 | 0 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2017 |  | 11/5/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 7/3/2018 | Connected |  | N
National Grid | EVERETT | 567873 | 02149 | 22.8 | Solar | 05_09_901W3 | 11/21/2023 | 11/22/2023 | 1 | 0 | 1 | 11/24/2023 | 11/24/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 |  | 1/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2024 | Connected |  | N
National Grid | BROCKTON | 644492 | 02302 | 9.86 | Solar | 05_07_96W43 | 10/08/2024 | 10/15/2024 | 2 | 0 | 2 | 10/16/2024 | 10/16/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 174459 | 01902 | 250 | Solar | 05_14_1321 | 09/21/2011 | 09/21/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2012 |  | 10/31/2012 | N | EXP | 295 |  |  | 0 | 0 | 0 | 9/26/2012 | 9/26/2012 | 10/2/2012 | Connected |  | N
National Grid | NORTHAMPTON | 178019 | 01060 | 300 | Natural Gas | 05_07_75W1 | 06/29/2017 | 06/29/2017 | 8 | 6 | 2 | 07/13/2017 | 07/13/2017 | 177 | 0 | 177 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2017 |  | 7/5/2018 | N | EXP | 332 |  |  | 0 | 0 | 0 | 8/18/2017 | 8/18/2017 | 12/20/2018 | Connected |  | N
National Grid | NORWELL | 290037 | 02061 | 7.68 | Solar | 05_12_22W3 | 07/08/2020 | 07/15/2020 | 4 | 0 | 4 | 07/16/2020 | 07/16/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 07/08/2020 | 2/3/2022 | Y | EXP | 365 | 01/20/2021 | 03/22/2021 | 61 | 0 | 61 |  |  | 1/3/2022 | Connected |  | N
National Grid | LAWRENCE | 613757 | 01843 | 13.53 | Solar | 05_09_901W3 | 05/29/2024 | 06/05/2024 | 6 | 4 | 2 | 06/06/2024 | 06/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2024 | Connected |  | N
National Grid | STOUGHTON | 647263 | 02072 | 10 | Solar | 05_07_96W43 | 10/15/2024 | 11/15/2024 | 1 | 0 | 1 | 11/18/2024 | 11/18/2024 | 46 | 23 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 603306 | 01907 | 50 | Solar | 05_14_1324 | 04/22/2024 | 07/31/2024 | 69 | 60 | 9 | 08/01/2024 | 08/01/2024 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 8/27/2026 | N | EXP | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTHAMPTON | 178739 | 01060 | 249 | Solar | 05_07_75W1 | 04/18/2018 | 04/18/2018 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/24/2019 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 547388 | 02061 | 130 | Solar | 05_12_22W5 | 08/11/2023 | 11/27/2023 | 72 | 61 | 11 | 11/28/2023 | 11/28/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 639898 | 01843 | 2.61 | Solar | 05_09_901W3 | 09/12/2024 | 10/24/2024 | 2 | 0 | 2 | 10/25/2024 | 10/25/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 |  | 12/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 603274 | 02072 | 40 | Solar | 05_14_1324 | 04/17/2024 | 08/28/2024 | 92 | 84 | 8 | 08/29/2024 | 08/29/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 8/12/2026 | N | EXP | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | SWAMPSCOTT | 290740 | 01907 | 7.6 | Solar | 05_07_75W1 | 05/11/2020 | 05/22/2020 | 8 | 7 | 1 | 05/26/2020 | 05/26/2020 | 95 | 72 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2020 |  | 11/29/2021 | N | EXP | 405 |  |  | 0 | 0 | 0 |  |  | 11/19/2021 | Connected |  | N
National Grid | NORTHAMPTON | 656725 | 01060 | 1.6 | Solar | 05_12_22W5 | 11/25/2024 | 12/24/2024 | 15 | 10 | 5 | 12/26/2024 | 12/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 652534 | 02061 | 11.5 | Solar | 05_09_901W3 | 11/06/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 1/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | LAWRENCE | 651477 | 01840 | 11.5 | Solar | 05_07_96W43 | 12/23/2024 | 02/12/2025 | 21 | 16 | 5 | 02/13/2025 | 02/13/2025 | 24 | 2 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | AVON | 378285 | 02322 | 60 | Solar | 05_14_1324 | 01/24/2022 | 03/29/2022 | 45 | 36 | 9 | 03/30/2022 | 03/30/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2022 | 01/24/2022 | 2/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2024 | Connected |  | N
National Grid | SWAMPSCOTT | 429417 | 01907 | 480 | Solar | 05_07_75W1 | 06/06/2022 | 07/01/2022 | 18 | 12 | 6 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 174345 | 01060 | 7.5 | Natural Gas | 05_12_2340 | 08/17/2010 | 08/17/2010 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/08/2010 | 10/21/2010 | 31 | 0 | 31 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2011 |  | 12/31/2016 | N | STD | 2145 |  |  | 0 | 0 | 0 | 4/19/2011 | 4/19/2011 |  | Withdrawn |  | Y
National Grid | NORWELL | 666190 | 02061 | 5.76 | Solar | 05_09_901W3 | 01/22/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | LAWRENCE | 712799 | 01841 | 15.2 | Solar | 05_07_96W43 | 08/18/2025 |  | 12 | 11 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 686652 | 02322 | 110 | Solar | 05_14_1324 | 05/05/2025 | 06/20/2025 | 32 | 22 | 10 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 591631 | 01907 | 7.6 | Solar | 05_07_75W1 | 02/23/2024 | 03/04/2024 | 6 | 0 | 6 | 03/05/2024 | 03/05/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 | 02/23/2024 | 11/9/2025 | Y | EXP | 365 | 08/06/2024 | 09/17/2024 | 43 | 0 | 43 |  |  | 4/30/2025 | Connected |  | N
National Grid | NORTHAMPTON | 175070 | 01060 | 200 | Solar | 05_12_2340 | 04/04/2013 | 04/04/2013 | 6 | 0 | 6 | 04/16/2013 | 04/16/2013 | 276 | 0 | 276 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2013 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 670750 | 02061 | 9.6 | Solar | 05_09_901W3 | 02/12/2025 | 02/21/2025 | 7 | 3 | 4 | 02/24/2025 | 02/24/2025 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | LAWRENCE | 717157 | 01840 | 10 | Solar | 05_07_96W43 | 09/08/2025 | 09/17/2025 | 6 | 4 | 2 | 09/18/2025 | 09/18/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | AVON | 423252 | 02322 | 160 | Solar | 05_14_1325 | 04/11/2022 | 05/06/2022 | 18 | 8 | 10 | 05/09/2022 | 05/09/2022 | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 | 04/11/2022 | 1/30/2025 | Y | EXP | 450 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 592939 | 01907 | 6 | Solar | 05_07_75W1 | 03/26/2024 | 04/03/2024 | 7 | 3 | 4 | 04/04/2024 | 04/04/2024 | 10 | 5 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 03/26/2024 | 5/7/2025 | Y | EXP | 365 | 06/01/2024 | 10/28/2024 | 140 | 0 | 140 |  |  | 10/19/2024 | Connected |  | N
National Grid | NORTHAMPTON | 739425 | 01060 | 10.26 | Solar | 05_12_23H2 | 12/15/2025 | 12/16/2025 | 1 | 0 | 1 | 12/17/2025 | 12/17/2025 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORWELL | 671633 | 02061 | 17.6 | Solar | 05_09_901W3 | 02/18/2025 | 03/03/2025 | 10 | 6 | 4 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | LAWRENCE | 710503 | 01840 | 11.5 | Solar | 05_07_96W44 | 08/07/2025 | 08/11/2025 | 2 | 0 | 2 | 08/12/2025 | 08/12/2025 | 159 | 25 | 134 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STOUGHTON | 446168 | 02072 | 50 | Solar | 05_14_1325 | 07/22/2022 | 08/10/2022 | 13 | 4 | 9 | 08/11/2022 | 08/11/2022 | 30 | 10 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2022 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINTHROP | 604070 | 02152 | 10 | Solar | 05_07_75W1 | 04/15/2024 | 04/24/2024 | 4 | 0 | 4 | 04/25/2024 | 04/25/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | NORTHAMPTON | 299137 | 01062 | 8 | Solar | 05_12_23H2 | 06/30/2020 | 07/29/2020 | 20 | 16 | 4 | 07/30/2020 | 07/30/2020 | 58 | 41 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/29/2021 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 683804 | 02061 | 15.2 | Solar | 05_09_901W3 | 04/10/2025 | 04/18/2025 | 5 | 0 | 5 | 04/22/2025 | 04/22/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | LAWRENCE | 174399 | 01840 | 13 | Solar | 05_07_96W44 | 06/15/2012 | 06/15/2012 | 5 | 0 | 5 | 06/26/2012 | 06/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2012 |  | 8/31/2012 | N | EXP | 59 |  |  | 0 | 0 | 0 | 10/2/2012 | 10/2/2012 | 11/29/2012 | Connected |  | N
National Grid | STOUGHTON | 176223 | 02072 | 232 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 | 08/18/2015 | 9/9/2016 | Y | EXP | 340 |  |  | 0 | 0 | 0 | 9/6/2017 | 9/6/2017 | 9/6/2017 | Connected |  | N
National Grid | WINTHROP | 710142 | 02152 | 15.76 | Solar | 05_07_75W1 | 08/15/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | NORTHAMPTON | 627048 | 01060 | 5 | Solar | 05_12_23H2 | 07/23/2024 | 07/25/2024 | 2 | 0 | 2 | 07/26/2024 | 07/26/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2024 | Connected |  | N
National Grid | SCITUATE | 694423 | 02066 | 0 | Solar | 05_09_901W3 | 06/02/2025 | 06/05/2025 | 3 | 0 | 3 | 06/06/2025 | 06/06/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | LAWRENCE | 177157 | 01840 | 20.5 | Solar | 05_07_96W44 | 10/26/2016 | 10/26/2016 | 7 | 7 | 0 | 11/04/2016 | 11/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2016 |  | 10/31/2017 | N | EXP | 361 |  |  | 0 | 0 | 0 | 2/22/2017 | 2/22/2017 | 2/28/2017 | Connected |  | N
National Grid | AVON | 176222 | 02322 | 158 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 558 | 59 | 499 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 | 08/18/2015 | 9/9/2016 | Y | EXP | 340 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 735531 | 02151 | 10 | Solar | 05_07_75W3 | 11/21/2025 | 11/24/2025 | 4 | 0 | 4 | 01/06/2026 | 01/06/2026 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 3/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTHAMPTON | 429415 | 01060 | 10 | Solar | 05_12_23H3 | 06/28/2022 | 06/30/2022 | 2 | 0 | 2 | 07/01/2022 | 07/01/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 8/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2022 | Connected |  | Y
National Grid | NORWELL | 634775 | 02061 | 140 | Solar | 05_09_905W1 | 09/03/2024 | 10/09/2024 | 26 | 17 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2025 | 09/03/2024 | 4/15/2026 | Y | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | LAWRENCE | 202211 | 01840 | 233.3 | Solar | 05_07_96W44 | 09/12/2019 | 09/20/2019 | 5 | 0 | 5 | 09/23/2019 | 09/23/2019 | 4 | 2 | 2 | 10/30/2019 | 11/25/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 11/25/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/10/2019 |  | 8/31/2021 | N | EXP | 395 | 10/13/2020 | 01/06/2021 | 85 | 0 | 85 |  |  | 2/24/2021 | Connected |  | N
National Grid | STOUGHTON | 176221 | 02072 | 122 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 |  | 9/9/2016 | N | EXP | 340 |  |  | 0 | 0 | 0 | 10/4/2017 | 10/4/2017 | 10/4/2017 | Connected |  | N
National Grid | REVERE | 175816 | 02151 | 360 | Solar | 05_07_75W3 | 07/27/2015 | 07/27/2015 | 2 | 2 | 0 | 07/30/2015 | 07/30/2015 | 554 | 0 | 554 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 |  | 9/6/2017 | N | EXP | 768 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 641448 | 01062 | 11.4 | Solar | 05_12_23H3 | 09/19/2024 | 09/24/2024 | 4 | 0 | 4 | 12/03/2024 | 12/03/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | NORWELL | 662850 | 02061 | 100 | Solar | 05_09_905W1 | 12/30/2024 | 02/14/2025 | 32 | 22 | 10 |  |  | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 |  | 5/14/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 202209 | 01840 | 366.6 | Solar | 05_07_96W44 | 04/12/2019 | 04/18/2019 | 4 | 2 | 2 | 04/19/2019 | 04/19/2019 | 12 | 9 | 3 | 06/14/2019 | 07/01/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 07/01/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 7/26/2019 |  | 4/2/2021 | N | EXP | 400 | 10/13/2020 | 01/06/2021 | 85 | 0 | 85 |  |  | 2/24/2021 | Connected |  | N
National Grid | STOUGHTON | 176220 | 02072 | 349 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 185 | 160 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2016 | 08/18/2015 | 10/3/2018 | Y | EXP | 789 |  |  | 0 | 0 | 0 |  |  | 10/29/2018 | Connected |  | N
National Grid | MANCHESTER | 178407 | 01944 | 498 | Solar | 05_07_75W3 | 04/02/2018 | 04/02/2018 | 12 | 3 | 9 |  |  | 67 | 42 | 25 | 08/20/2018 | 10/16/2018 | 41 | 14 | 27 |  |  | 0 | 0 | 0 | 10/16/2018 | 41 | 14 | 27 |  |  | 0 | 0 | 0 | 11/28/2018 |  | 10/1/2019 | N | STD | 307 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 756506 | 01060 | 11.4 | Solar | 05_12_23W1 | 03/13/2026 | 03/17/2026 | 2 | 0 | 2 | 03/18/2026 | 03/18/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORWELL | 662255 | 02061 | 160 | Solar | 05_09_905W1 | 12/30/2024 | 02/14/2025 | 32 | 23 | 9 |  |  | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2025 |  | 5/14/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 211150 | 01840 | 262.5 | Natural Gas | 05_07_96W44 | 09/13/2019 | 11/05/2019 | 36 | 27 | 9 | 11/06/2019 | 11/06/2019 | 8 | 0 | 8 | 01/03/2020 | 04/27/2020 | 79 | 46 | 33 |  |  | 0 | 0 | 0 | 04/27/2020 | 79 | 46 | 33 |  |  | 0 | 0 | 0 | 5/5/2020 |  | 9/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2020 | Connected |  | N
National Grid | STOUGHTON | 176326 | 02072 | 3200 | Natural Gas | 05_14_2326 | 07/17/2015 | 07/17/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2015 | 08/18/2015 | 21 | 21 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 | 07/17/2015 | 8/20/2019 | Y | STD | 1204 | 05/31/2017 | 10/30/2017 | 105 | 0 | 105 |  |  | 8/16/2019 | Connected |  | N
National Grid | MANCHESTER | 184781 | 01944 | 18.9 | Solar | 05_07_75W3 | 06/06/2018 | 06/06/2018 | 48 | 35 | 13 | 08/02/2018 | 08/02/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2018 |  | 8/14/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2019 | Connected |  | N
National Grid | NORTHAMPTON | 176130 | 01060 | 7.1 | Solar | 05_12_23W1 | 04/14/2015 | 04/14/2015 | 1 | 0 | 1 | 04/15/2015 | 04/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2015 |  | 8/31/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 | 7/2/2015 | 7/2/2015 | 7/6/2015 | Connected |  | N
National Grid | NORWELL | 739273 | 02061 | 250 | Solar | 05_09_905W1 | 12/31/2025 | 03/11/2026 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/12/2026 |  | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 265059 | 01843 | 400 | Solar | 05_07_96W44 | 11/13/2019 | 11/21/2019 | 5 | 3 | 2 | 04/08/2020 | 04/08/2020 | 0 | 0 | 0 | 04/08/2020 | 06/23/2020 | 52 | 0 | 52 |  |  | 0 | 0 | 0 | 06/23/2020 | 52 | 0 | 52 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/18/2021 | N | EXP | 365 | 11/10/2020 | 06/11/2021 | 213 | 0 | 213 |  |  | 6/22/2021 | Connected |  | N
National Grid | STOUGHTON | 176448 | 02072 | 140 | Solar | 05_14_2326 | 05/17/2016 | 05/17/2016 | 0 | 0 | 0 | 05/18/2016 | 05/18/2016 | 0 | 0 | 0 | 06/16/2016 | 08/10/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 08/10/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 8/25/2016 |  | 5/23/2017 | N | EXP | 271 |  |  | 0 | 0 | 0 | 5/23/2017 | 5/23/2017 | 5/23/2017 | Connected |  | N
National Grid | MANCHESTER | 318608 | 01944 | 2.4 | Solar | 05_07_75W3 | 10/16/2020 | 10/22/2020 | 3 | 0 | 3 | 10/23/2020 | 10/23/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  | 12/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 177338 | 01060 | 433 | Solar | 05_12_23W1 | 09/01/2016 | 09/01/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/06/2016 | 11/18/2016 | 51 | 46 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/6/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 174897 | 02061 | 32.46 | Solar | 05_09_905W1 | 08/07/2012 | 08/07/2012 | 6 | 0 | 6 | 08/17/2012 | 08/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 3/15/2013 | 3/15/2013 | 4/3/2013 | Connected |  | N
National Grid | LAWRENCE | 287104 | 01843 | 300 | Solar | 05_07_96W44 | 04/11/2020 | 04/22/2020 | 7 | 3 | 4 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 176445 | 02322 | 140 | Solar | 05_14_2326 | 05/16/2016 | 05/16/2016 | 0 | 0 | 0 | 05/16/2016 | 05/16/2016 | 0 | 0 | 0 | 08/19/2016 | 08/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2016 |  | 9/21/2017 | N | EXP | 392 |  |  | 0 | 0 | 0 | 7/19/2017 | 7/19/2017 | 7/19/2017 | Connected |  | N
National Grid | MANCHESTER | 378486 | 01944 | 5.76 | Solar | 05_07_75W3 | 09/08/2021 | 09/13/2021 | 3 | 0 | 3 | 09/14/2021 | 09/14/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 178391 | 01060 | 476 | Solar | 05_12_23W1 | 03/02/2018 | 03/02/2018 | 4 | 0 | 4 | 03/08/2018 | 03/08/2018 | 58 | 37 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 |  | 12/31/2020 | N | EXP | 487 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 175420 | 02061 | 200 | Solar | 05_09_905W1 | 07/18/2014 | 07/18/2014 | 570 | 570 | 0 | 11/01/2016 | 11/01/2016 | 153 | 152 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 289008 | 01843 | 200 | Solar | 05_07_96W44 | 05/14/2020 | 05/21/2020 | 4 | 0 | 4 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 176444 | 02322 | 108 | Solar | 05_14_2326 | 05/06/2016 | 05/06/2016 | 0 | 0 | 0 | 05/16/2016 | 05/16/2016 | 435 | 0 | 435 | 06/16/2016 | 08/10/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 08/10/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 8/25/2016 |  | 2/28/2018 | N | EXP | 552 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MANCHESTER | 391865 | 01944 | 0 | Other | 05_07_75W3 | 01/18/2022 | 01/28/2022 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 02/25/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 194458 | 01060 | 720 | Solar | 05_12_23W1 | 01/15/2019 | 02/26/2019 | 28 | 20 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2019 | 03/25/2019 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 176063 | 02061 | 45 | Solar | 05_09_905W1 | 04/01/2015 | 04/01/2015 | 5 | 0 | 5 | 04/09/2015 | 04/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2015 |  | 4/12/2015 | N | EXP | 1 |  |  | 0 | 0 | 0 | 4/24/2015 | 4/24/2015 | 10/9/2015 | Connected |  | N
National Grid | LAWRENCE | 296764 | 01843 | 10 | Solar | 05_07_96W44 | 06/16/2020 | 06/23/2020 | 4 | 0 | 4 | 06/24/2020 | 06/24/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 | 06/16/2020 | 10/25/2023 | Y | EXP | 365 | 12/15/2020 | 01/15/2021 | 31 | 0 | 31 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 178093 | 02322 | 232 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 | 08/18/2015 | 7/15/2018 | Y | EXP | 1014 |  |  | 0 | 0 | 0 |  |  | 6/11/2018 | Connected |  | N
National Grid | SAUGUS | 412236 | 01906 | 0 | Battery Add-On | 05_07_75W3 | 10/02/2022 | 11/15/2022 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 | 08/03/2023 | 178 | 158 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 194758 | 01060 | 375 | Natural Gas | 05_12_23W1 | 10/12/2018 | 10/31/2018 | 12 | 0 | 12 |  |  | 51 | 27 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2020 |  | 12/31/2020 | N | STD | 365 | 10/28/2020 | 10/27/2020 | 0 | 0 | 0 | 10/28/2020 | 12/17/2020 | 12/17/2020 | Connected |  | N
National Grid | NORWELL | 204335 | 02061 | 233.1 | Solar | 05_09_905W1 | 01/07/2019 | 01/18/2019 | 8 | 2 | 6 | 01/22/2019 | 01/22/2019 | 70 | 48 | 22 | 05/22/2019 | 08/27/2019 | 68 | 7 | 61 |  |  | 0 | 0 | 0 | 08/27/2019 | 68 | 7 | 61 |  |  | 0 | 0 | 0 | 9/12/2019 |  | 8/3/2020 | N | EXP | 172 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 364705 | 01845 | 72 | Solar | 05_07_96W44 | 06/28/2021 | 07/22/2021 | 17 | 9 | 8 | 07/23/2021 | 07/23/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2021 |  | 4/9/2023 | N | EXP | 586 |  |  | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N
National Grid | AVON | 178092 | 02322 | 122 | Solar | 05_14_2326 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 | 09/04/2015 | 09/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 | 08/18/2015 | 10/17/2018 | Y | EXP | 1108 |  |  | 0 | 0 | 0 |  |  | 10/4/2017 | Connected |  | N
National Grid | SAUGUS | 579567 | 01906 | 4.35 | Solar | 05_07_75W3 | 01/18/2024 | 01/19/2024 | 1 | 0 | 1 | 01/22/2024 | 01/22/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2024 | Connected |  | N
National Grid | NORTHAMPTON | 219650 | 01060 | 7.6 | Solar | 05_12_23W1 | 04/24/2019 | 05/01/2019 | 5 | 5 | 0 | 05/02/2019 | 05/02/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2019 | 04/24/2019 | 6/11/2020 | Y | EXP | 365 | 02/25/2020 | 03/10/2020 | 14 | 0 | 14 |  |  | 5/15/2020 | Connected |  | Y
National Grid | HANOVER | 217557 | 02339 | 7.6 | Solar | 05_09_905W1 | 04/30/2020 | 05/04/2020 | 2 | 2 | 0 | 05/05/2020 | 05/05/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 | 04/30/2020 | 5/3/2021 | Y | EXP | 365 | 09/09/2020 | 09/08/2020 | 0 | 0 | 0 |  |  | 12/4/2020 | Connected |  | N
National Grid | ANDOVER | 391836 | 01845 | 0 | Other | 05_07_96W44 | 11/15/2021 | 01/04/2022 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 202326 | 02322 | 450 | Solar | 05_14_2326 | 11/28/2018 | 02/14/2019 | 43 | 38 | 5 | 02/15/2019 | 02/15/2019 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 680142 | 01906 | 11.5 | Solar | 05_07_75W3 | 03/26/2025 | 03/31/2025 | 3 | 0 | 3 | 04/01/2025 | 04/01/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N
National Grid | NORTHAMPTON | 306578 | 01060 | 6 | Solar | 05_12_23W1 | 09/04/2020 | 09/10/2020 | 2 | 0 | 2 | 09/11/2020 | 09/11/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2020 | 09/04/2020 | 9/1/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2021 | Connected |  | N
National Grid | HANOVER | 253402 | 02339 | 10 | Solar | 05_09_905W1 | 09/30/2019 | 10/01/2019 | 1 | 1 | 0 | 10/02/2019 | 10/02/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2019 | 09/30/2019 | 5/21/2020 | Y | EXP | 0 | 12/19/2019 | 12/18/2019 | 0 | 0 | 0 |  |  | 12/19/2019 | Connected |  | N
National Grid | ANDOVER | 477628 | 01845 | 15.2 | Solar | 05_07_96W44 | 11/15/2022 | 11/17/2022 | 2 | 0 | 2 | 11/18/2022 | 11/18/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 206881 | 02322 | 278 | Solar | 05_14_2326 | 01/23/2019 | 03/11/2019 | 29 | 23 | 6 | 03/12/2019 | 03/12/2019 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 699462 | 01906 | 7.6 | Solar | 05_07_75W3 | 06/18/2025 | 10/20/2025 | 1 | 0 | 1 | 10/21/2025 | 10/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 430334 | 01060 | 6 | Solar | 05_12_23W1 | 06/07/2022 | 06/14/2022 | 5 | 3 | 2 | 06/15/2022 | 06/15/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 12/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 280785 | 02339 | 3.8 | Solar | 05_09_905W1 | 03/03/2020 | 03/25/2020 | 16 | 16 | 0 | 03/26/2020 | 03/26/2020 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2020 | 03/03/2020 | 3/25/2021 | Y | EXP | 365 | 10/08/2020 | 10/26/2020 | 18 | 0 | 18 |  |  | 10/28/2020 | Connected |  | N
National Grid | ANDOVER | 495553 | 01845 | 23.808 | Solar | 05_07_96W44 | 01/27/2023 | 03/07/2023 | 27 | 26 | 1 | 03/08/2023 | 03/08/2023 | 86 | 64 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 379254 | 02322 | 200 | Solar | 05_14_2326 | 09/14/2021 | 09/24/2021 | 8 | 0 | 8 |  |  | 44 | 4 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 638260 | 01906 | 990 | Solar | 05_07_75W5 | 05/08/2025 | 07/09/2025 | 40 | 30 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 07/29/2025 | 14 | 0 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTHAMPTON | 630162 | 01060 | 6 | Solar | 05_12_23W1 | 08/05/2024 | 09/04/2024 | 8 | 5 | 3 | 09/05/2024 | 09/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/05/2024 | 10/1/2025 | Y | EXP | 365 | 12/18/2024 | 03/27/2025 | 100 | 0 | 100 |  |  | 4/8/2025 | Connected |  | N
National Grid | NORWELL | 309324 | 02061 | 6 | Solar | 05_09_905W1 | 08/31/2020 | 09/03/2020 | 2 | 0 | 2 | 09/04/2020 | 09/04/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/31/2020 | 11/8/2021 | Y | EXP | 365 | 09/10/2021 | 10/01/2021 | 19 | 0 | 19 |  |  | 10/27/2021 | Connected |  | Y
National Grid | LAWRENCE | 541172 | 01843 | 7.56 | Solar | 05_07_96W44 | 07/17/2023 | 07/19/2023 | 2 | 0 | 2 | 07/20/2023 | 07/20/2023 | 72 | 51 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2023 |  | 11/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2024 | Connected |  | N
National Grid | AVON | 178314 | 02322 | 2800 | Solar | 05_14_2329 | 02/26/2018 | 02/26/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2018 | 04/11/2018 | 19 | 10 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2018 |  | 3/31/2021 | N | STD | 543 | 01/17/2020 | 01/04/2021 | 353 | 5 | 348 |  |  | 3/11/2021 | Connected |  | N
National Grid | SAUGUS | 747001 | 01906 | 11.5 | Solar | 05_07_75W5 | 01/22/2026 | 02/27/2026 | 25 | 23 | 2 | 03/02/2026 | 03/02/2026 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 649256 | 01060 | 11.4 | Solar | 05_12_23W1 | 11/18/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 1/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | Y
National Grid | NORWELL | 337254 | 02061 | 0 | Solar | 05_09_905W1 | 01/21/2021 | 01/26/2021 | 2 | 1 | 1 | 01/27/2021 | 01/27/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2021 |  | 1/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2021 | Connected |  | N
National Grid | LAWRENCE | 586854 | 01843 | 0 | Battery Add-On | 05_07_96W44 | 01/31/2024 | 02/20/2024 | 13 | 11 | 2 | 02/21/2024 | 02/21/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 3/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | AVON | 426199 | 02322 | 100 | Solar | 05_14_2355 | 08/29/2022 | 11/29/2022 | 62 | 54 | 8 |  |  | 33 | 7 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 | 08/29/2022 | 5/24/2026 | Y | STD | 343 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | SAUGUS | 174838 | 01906 | 75 | Solar | 05_07_75W5 | 08/28/2012 | 08/28/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2012 | 08/28/2012 | 12/27/2012 | Y | EXP | 10 | 04/10/2013 | 04/22/2013 | 7 | 0 | 7 | 4/23/2013 | 4/23/2013 | 6/3/2013 | Connected |  | N
National Grid | NORTHAMPTON | 688318 | 01060 | 7.6 | Solar | 05_12_23W1 | 04/29/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 04/29/2025 | 7/9/2026 | Y | EXP | 365 | 10/18/2025 | 12/02/2025 | 46 | 0 | 46 |  |  | 12/4/2025 | Connected |  | N
National Grid | NORWELL | 343658 | 02061 | 7.6 | Solar | 05_09_905W1 | 03/08/2021 | 04/22/2021 | 31 | 26 | 5 | 04/23/2021 | 04/23/2021 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/22/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 604122 | 01843 | 53.58 | Solar | 05_07_96W44 | 04/16/2024 | 07/03/2024 | 54 | 46 | 8 | 07/05/2024 | 07/05/2024 | 39 | 32 | 7 | 08/29/2024 | 11/21/2024 | 59 | 25 | 34 |  |  | 0 | 0 | 0 | 11/21/2024 | 59 | 25 | 34 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 186222 | 02322 | 100.8 | Solar | 05_14_2355 | 05/31/2018 | 05/31/2018 | 0 | 0 | 0 | 06/04/2018 | 06/04/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2018 |  | 3/11/2020 | N | EXP | 535 |  |  | 0 | 0 | 0 |  |  | 3/5/2020 | Connected |  | N
National Grid | SAUGUS | 174929 | 01906 | 990 | Solar | 05_07_75W5 | 08/22/2013 | 08/22/2013 | 6 | 0 | 6 | 09/03/2013 | 09/03/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2014 | 08/22/2013 | 1/31/2014 | Y | EXP | 3 | 11/05/2014 | 12/18/2014 | 29 | 0 | 29 | 12/16/2014 | 12/16/2014 | 12/30/2014 | Connected |  | N
National Grid | NORTHAMPTON | 659868 | 01060 | 2.32 | Solar | 05_12_23W2 | 12/11/2024 | 01/06/2025 | 1 | 0 | 1 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 4/21/2026 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORWELL | 375139 | 02061 | 11.4 | Solar | 05_09_905W1 | 08/10/2021 | 09/09/2021 | 22 | 21 | 1 | 09/10/2021 | 09/10/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 |  | 11/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2022 | Connected |  | N
National Grid | LAWRENCE | 706541 | 01843 | 7.6 | Solar | 05_07_96W44 | 07/25/2025 | 08/08/2025 | 9 | 5 | 4 | 08/11/2025 | 08/11/2025 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 348816 | 02322 | 499 | Solar | 05_14_2355 | 12/21/2021 |  | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 175391 | 01906 | 266 | Solar | 05_07_75W5 | 09/12/2014 | 09/12/2014 | 6 | 0 | 6 | 09/23/2014 | 09/23/2014 | 0 | 0 | 0 | 02/27/2015 | 04/01/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 04/01/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 4/14/2015 |  | 12/31/2016 | N | EXP | 627 |  |  | 0 | 0 | 0 | 6/16/2015 | 6/16/2015 | 3/7/2017 | Connected |  | N
National Grid | NORTHAMPTON | 669124 | 01060 | 7.6 | Solar | 05_12_23W2 | 02/04/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | NORWELL | 419834 | 02061 | 10 | Solar | 05_09_905W1 | 04/13/2022 | 04/14/2022 | 1 | 0 | 1 | 04/15/2022 | 04/15/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 04/13/2022 | 8/17/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N
National Grid | ANDOVER | 715186 | 01845 | 53.58 | Solar | 05_07_96W44 | 08/27/2025 |  | 25 | 24 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 348813 | 02322 | 750 | Solar | 05_14_2355 | 09/21/2021 | 01/20/2022 | 563 | 554 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2022 | 03/03/2022 | 29 | 0 | 29 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 175879 | 01902 | 446.4 | Solar | 05_07_75W5 | 03/09/2015 | 03/09/2015 | 4 | 0 | 4 | 03/16/2015 | 03/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 |  | 9/30/2015 | N | EXP | 182 |  |  | 0 | 0 | 0 | 4/6/2015 | 4/6/2015 | 3/30/2017 | Connected |  | N
National Grid | NORTHAMPTON | 712857 | 01060 | 3.8 | Solar | 05_12_23W2 | 08/18/2025 | 09/19/2025 | 15 | 11 | 4 | 10/22/2025 | 10/22/2025 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | NORWELL | 468492 | 02061 | 10 | Solar | 05_09_905W1 | 11/02/2022 | 11/03/2022 | 1 | 0 | 1 | 11/04/2022 | 11/04/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 11/02/2022 | 1/4/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2023 | Connected |  | N
National Grid | HAVERHILL | 697797 | 01830 | 320 | Solar | 05_07_97W1 | 08/18/2025 | 03/26/2026 | 149 | 139 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2026 |  | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AVON | 174119 | 02322 | 4968 | Solar | 05_14_2356 | 04/05/2012 | 04/19/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2014 | 04/05/2012 | 12/29/2017 | Y | STD | 1327 | 02/15/2017 | 08/21/2017 | 129 | 0 | 129 | 12/19/2017 | 12/19/2017 | 4/3/2017 | Connected |  | N
National Grid | SAUGUS | 176324 | 01906 | 50 | Solar | 05_07_75W5 | 07/16/2015 | 07/16/2015 | 3 | 3 | 0 | 07/21/2015 | 07/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 |  | 7/21/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 2/24/2016 | 2/24/2016 | 2/24/2016 | Connected |  | N
National Grid | NORTHAMPTON | 726137 | 01060 | 15.2 | Solar | 05_12_23W2 | 12/15/2025 | 12/18/2025 | 3 | 0 | 3 | 12/19/2025 | 12/19/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORWELL | 484829 | 02061 | 120 | Solar | 05_09_905W1 | 12/21/2022 | 03/06/2023 | 49 | 38 | 11 |  |  | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 697784 | 01841 | 240 | Solar | 05_07_97W1 | 08/07/2025 | 03/09/2026 | 143 | 136 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AVON | 177224 | 02322 | 995 | Landfill Gas | 05_14_2356 | 08/16/2016 | 08/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/16/2016 | 08/26/2016 | 8 | 3 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2017 | 08/16/2016 | 11/30/2020 | Y | STD | 1077 | 03/11/2020 | 07/06/2020 | 117 | 0 | 117 | 11/4/2020 | 11/3/2020 | 11/12/2020 | Connected |  | N
National Grid | SAUGUS | 176443 | 01906 | 360 | Solar | 05_07_75W5 | 05/15/2016 | 05/15/2016 | 21 | 21 | 0 | 06/15/2016 | 06/15/2016 | 97 | 0 | 97 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/21/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 727782 | 01060 | 6 | Solar | 05_12_23W2 | 10/20/2025 | 10/21/2025 | 1 | 0 | 1 | 10/22/2025 | 10/22/2025 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORWELL | 485578 | 02061 | 120 | Solar | 05_09_905W1 | 12/21/2022 | 03/07/2023 | 50 | 40 | 10 |  |  | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 730347 | 01841 | 5.76 | Solar | 05_07_97W1 | 10/30/2025 | 11/04/2025 | 3 | 0 | 3 | 11/05/2025 | 11/05/2025 | 58 | 39 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AVON | 175612 | 02322 | 2000 | Solar | 05_14_2358 | 12/16/2014 | 12/16/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 | 01/23/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2015 | N | STD | 0 | 12/16/2016 | 08/31/2017 | 177 | 0 | 177 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 177908 | 01906 | 112 | Solar | 05_07_75W5 | 08/16/2017 | 08/16/2017 | 9 | 9 | 0 | 08/29/2017 | 08/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 |  | 8/21/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 12/19/2017 | 12/19/2017 | 12/21/2017 | Connected |  | N
National Grid | NORTHAMPTON | 749919 | 01060 | 11.5 | Solar | 05_12_23W2 | 02/06/2026 | 02/11/2026 | 3 | 0 | 3 | 02/12/2026 | 02/12/2026 | 33 | 24 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORWELL | 545579 | 02061 | 4.06 | Solar | 05_09_905W1 | 08/09/2023 | 08/10/2023 | 1 | 0 | 1 | 08/11/2023 | 08/11/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2023 | 08/09/2023 | 9/13/2024 | Y | EXP | 365 | 10/10/2023 | 10/09/2023 | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N
National Grid | METHUEN | 754294 | 01844 | 10 | Solar | 05_07_97W1 | 03/03/2026 | 03/05/2026 | 2 | 0 | 2 | 03/06/2026 | 03/06/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | AVON | 175611 | 02322 | 3384 | Solar | 05_14_2358 | 12/16/2014 | 12/16/2014 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 | 12/02/2015 | 233 | 232 | 1 |  | 0 | 0 | 0 | 12/07/2015 | 12/07/2015 | 0 | 0 | 0 | 5/1/2016 | 12/16/2014 | 4/1/2023 | Y | STD | 546 | 12/16/2016 | 12/16/2016 | 0 | 0 | 0 | 4/11/2017 | 4/11/2017 | 4/3/2023 | Connected |  | N
National Grid | SAUGUS | 178077 | 01906 | 15.2 | Solar | 05_07_75W5 | 11/03/2017 | 11/03/2017 | 55 | 55 | 0 | 01/29/2018 | 01/29/2018 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2018 |  | 11/27/2020 | N | EXP | 283 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 175967 | 01060 | 11.4 | Solar | 05_12_23W2 | 08/06/2015 | 08/06/2015 | 0 | 0 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 |  | 8/17/2016 | N | EXP | 344 |  |  | 0 | 0 | 0 | 4/6/2016 | 4/6/2016 | 4/26/2016 | Connected |  | N
National Grid | NORWELL | 675548 | 02061 | 11.5 | Solar | 05_09_905W1 | 03/04/2025 | 03/10/2025 | 4 | 0 | 4 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2025 | Connected |  | N
National Grid | LAWRENCE | 177953 | 01841 | 109.25 | Solar | 05_07_97W1 | 08/24/2017 | 08/24/2017 | 5 | 5 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 9/2/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 12/18/2017 | 12/18/2017 | 12/21/2017 | Connected |  | N
National Grid | AVON | 178779 | 02322 | 2000 | Solar | 05_14_2358 | 12/16/2014 | 12/16/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 | 01/23/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2015 |  | 12/31/2016 | N | STD | 458 | 12/16/2016 | 02/14/2018 | 284 | 0 | 284 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 187201 | 01906 | 490 | Solar | 05_07_75W5 | 06/18/2019 | 06/22/2019 | 3 | 0 | 3 | 06/24/2019 | 06/24/2019 | 30 | 26 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 8/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 176687 | 01060 | 6 | Solar | 05_12_23W2 | 02/18/2016 | 02/18/2016 | 2 | 2 | 0 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2016 |  | 2/24/2017 | N | EXP | 361 |  |  | 0 | 0 | 0 | 8/25/2016 | 8/25/2016 | 8/25/2016 | Connected |  | N
National Grid | RANDOLPH | 679353 | 02368 | 12.215 | Solar | 05_09_905W1 | 03/20/2025 | 04/01/2025 | 4 | 0 | 4 | 04/24/2025 | 04/24/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2025 | Connected |  | N
National Grid | HAVERHILL | 177991 | 01830 | 15.2 | Solar | 05_07_97W1 | 10/24/2017 | 10/24/2017 | 14 | 14 | 0 | 11/27/2017 | 11/27/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 11/1/2018 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 178778 | 02322 | 2000 | Solar | 05_14_2358 | 12/16/2014 | 12/16/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 | 01/23/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2015 |  | 12/31/2016 | N | STD | 458 | 12/16/2016 | 01/26/2018 | 271 | 0 | 271 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 187901 | 01906 | 240 | Solar | 05_07_75W5 | 06/13/2018 | 06/13/2018 | 10 | 7 | 3 | 08/06/2018 | 08/06/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2018 |  | 2/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N
National Grid | NORTHAMPTON | 176722 | 01060 | 7.6 | Solar | 05_12_23W2 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2016 |  | 2/28/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 8/17/2016 | 8/17/2016 | 8/19/2016 | Connected |  | N
National Grid | RANDOLPH | 710970 | 02368 | 7.6 | Solar | 05_09_905W1 | 08/11/2025 | 09/23/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/2/2026 | Connected |  | N
National Grid | HAVERHILL | 178414 | 01835 | 7.6 | Solar | 05_07_97W1 | 11/27/2017 | 11/27/2017 | 28 | 27 | 1 | 01/09/2018 | 01/09/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2018 |  | 12/3/2018 | N | EXP | 327 |  |  | 0 | 0 | 0 |  |  | 4/30/2019 | Connected |  | N
National Grid | AVON | 524407 | 02322 | 500 | Solar | 05_14_2358 | 02/15/2024 | 08/01/2024 | 114 | 106 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2024 | 08/30/2024 | 21 | 14 | 7 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 252794 | 01906 | 7.6 | Solar | 05_07_75W5 | 10/07/2019 | 10/11/2019 | 3 | 0 | 3 | 10/15/2019 | 10/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 177143 | 01060 | 6 | Solar | 05_12_23W2 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 | 05/27/2016 | 8/1/2017 | Y | EXP | 407 | 05/31/2017 | 06/14/2017 | 10 | 0 | 10 | 6/29/2017 | 6/29/2017 | 7/10/2017 | Connected |  | N
National Grid | RANDOLPH | 726288 | 02368 | 0 | Battery Add-On | 05_09_905W1 | 10/14/2025 | 10/16/2025 | 2 | 0 | 2 | 10/17/2025 | 10/17/2025 | 113 | 25 | 88 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 189885 | 01845 | 7.6 | Solar | 05_07_97W1 | 07/03/2018 | 07/03/2018 | 14 | 11 | 3 | 09/20/2018 | 09/20/2018 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 619480 | 02322 | 500 | Solar | 05_14_2358 | 06/22/2024 | 08/26/2024 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2024 | 08/30/2024 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 285958 | 01906 | 249 | Solar | 05_07_75W5 | 04/27/2020 | 05/29/2020 | 23 | 16 | 7 | 06/01/2020 | 06/01/2020 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2020 | 04/27/2020 | 1/29/2026 | Y | EXP | 253 | 12/03/2024 | 12/18/2025 | 381 | 309 | 72 |  |  | 12/26/2025 | Connected |  | N
National Grid | NORTHAMPTON | 177796 | 01060 | 15.2 | Solar | 05_12_23W2 | 08/03/2017 | 08/03/2017 | 9 | 8 | 1 | 08/16/2017 | 08/16/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/8/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 10/10/2018 | Connected |  | N
National Grid | RANDOLPH | 672161 | 02368 | 217.3 | Solar | 05_09_909W1 | 02/25/2025 | 03/14/2025 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2025 | 04/18/2025 | 25 | 0 | 25 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 7/16/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 190453 | 01845 | 5 | Solar | 05_07_97W1 | 07/11/2018 | 08/13/2018 | 9 | 0 | 9 | 08/14/2018 | 08/14/2018 | 3 | 0 | 3 | 09/26/2018 | 10/30/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 10/30/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2019 | Connected |  | N
National Grid | AVON | 619478 | 02322 | 500 | Solar | 05_14_2358 | 06/22/2024 | 08/26/2024 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2024 | 08/30/2024 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 331898 | 01906 | 15.2 | Solar | 05_07_75W5 | 12/15/2020 | 12/16/2020 | 0 | 0 | 0 | 12/17/2020 | 12/17/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2021 | Connected |  | N
National Grid | NORTHAMPTON | 177866 | 01060 | 3.8 | Solar | 05_12_23W2 | 06/15/2017 | 06/15/2017 | 6 | 6 | 0 | 06/23/2017 | 06/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2017 | 06/15/2017 | 6/20/2018 | Y | EXP | 357 | 01/18/2018 | 03/28/2018 | 37 | 0 | 37 |  |  | 5/30/2018 | Connected |  | N
National Grid | RANDOLPH | 693642 | 02368 | 5.7 | Solar | 05_09_909W1 | 05/23/2025 | 10/23/2025 | 3 | 0 | 3 | 11/17/2025 | 11/17/2025 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 | 05/23/2025 | 12/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ANDOVER | 197323 | 01845 | 3.8 | Solar | 05_07_97W1 | 11/09/2018 | 11/20/2018 | 4 | 0 | 4 | 11/21/2018 | 11/21/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 11/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | N
National Grid | AVON | 619466 | 02322 | 500 | Solar | 05_14_2358 | 06/22/2024 | 08/26/2024 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2024 | 08/30/2024 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 467612 | 01906 | 0 | Other | 05_07_75W5 | 11/15/2022 | 01/23/2023 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/24/2023 | 02/21/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 177978 | 01060 | 7.6 | Solar | 05_12_23W2 | 06/28/2017 | 06/28/2017 | 5 | 2 | 3 | 07/06/2017 | 07/06/2017 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 7/3/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 709319 | 02368 | 2.66 | Solar | 05_09_909W1 | 08/04/2025 | 10/28/2025 | 9 | 5 | 4 | 10/29/2025 | 10/29/2025 | 49 | 30 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 | 08/04/2025 | 2/2/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ANDOVER | 197198 | 01845 | 7.6 | Solar | 05_07_97W1 | 09/28/2018 | 10/17/2018 | 4 | 3 | 1 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 | 09/28/2018 | 9/30/2019 | Y | EXP | 346 | 07/18/2019 | 08/07/2019 | 19 | 0 | 19 |  |  | 9/6/2019 | Connected |  | N
National Grid | AVON | 174552 | 02322 | 420 | Landfill Gas | 05_14_2371 | 11/07/2011 | 11/07/2011 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 624944 | 01906 | 7.6 | Solar | 05_07_75W5 | 07/15/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 194862 | 01060 | 17.6 | Solar | 05_12_23W2 | 10/08/2018 | 10/17/2018 | 6 | 0 | 6 | 10/18/2018 | 10/18/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 | 10/08/2018 | 6/15/2021 | Y | EXP | 530 | 12/18/2019 | 02/24/2020 | 68 | 0 | 68 |  |  | 6/2/2021 | Connected |  | N
National Grid | RANDOLPH | 177590 | 02368 | 6 | Solar | 05_09_909W1 | 05/18/2017 | 05/18/2017 | 63 | 63 | 0 | 08/21/2017 | 08/21/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 |  | 5/27/2018 | N | EXP | 272 |  |  | 0 | 0 | 0 | 2/15/2018 | 2/15/2018 | 2/15/2018 | Connected |  | N
National Grid | ANDOVER | 202819 | 01845 | 7.6 | Solar | 05_07_97W1 | 01/21/2019 | 01/30/2019 | 7 | 7 | 0 | 01/31/2019 | 01/31/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2019 | 01/21/2019 | 3/26/2020 | Y | EXP | 413 | 11/07/2019 | 01/10/2020 | 64 | 0 | 64 |  |  | 1/21/2020 | Connected |  | N
National Grid | AVON | 174590 | 02322 | 1000 | Solar | 05_14_2376 | 07/20/2011 | 07/20/2011 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | STD | 12 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 634969 | 01906 | 7.6 | Solar | 05_07_75W5 | 08/26/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 64 | 28 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 08/26/2024 | 1/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | NORTHAMPTON | 210282 | 01060 | 5 | Solar | 05_12_23W2 | 02/26/2019 | 03/05/2019 | 5 | 5 | 0 | 03/06/2019 | 03/06/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2019 | 02/26/2019 | 12/30/2019 | Y | EXP | 270 | 10/03/2019 | 11/26/2019 | 54 | 0 | 54 |  |  | 12/6/2019 | Connected |  | N
National Grid | RANDOLPH | 178523 | 02368 | 66.6 | Solar | 05_09_909W1 | 04/04/2018 | 04/04/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 205636 | 01845 | 13.8 | Solar | 05_07_97W1 | 01/29/2019 | 01/30/2019 | 0 | 0 | 0 | 01/31/2019 | 01/31/2019 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 | 01/29/2019 | 10/23/2020 | Y | EXP | 434 | 11/07/2019 | 01/16/2020 | 70 | 0 | 70 |  |  | 10/5/2020 | Connected |  | N
National Grid | AVON | 174522 | 02322 | 1000 | Solar | 05_14_2377N | 10/07/2010 | 10/07/2010 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2011 | 10/07/2010 | 10/31/2012 | Y | STD | 503 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 8/3/2012 | Connected |  | N
National Grid | SAUGUS | 515428 | 01906 | 200 | Solar | 05_07_75W7 | 04/03/2023 | 04/20/2023 | 12 | 3 | 9 | 04/21/2023 | 04/21/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 6/27/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 246187 | 01060 | 10 | Solar | 05_12_23W2 | 07/30/2019 | 10/07/2019 | 48 | 47 | 1 | 10/08/2019 | 10/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  | 7/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/19/2020 | Connected |  | N
National Grid | RANDOLPH | 184686 | 02368 | 66.6 | Solar | 05_09_909W1 | 05/07/2018 | 05/07/2018 | 20 | 0 | 20 | 06/07/2018 | 06/07/2018 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 208541 | 01845 | 10 | Solar | 05_07_97W1 | 02/14/2019 | 02/21/2019 | 4 | 4 | 0 | 02/22/2019 | 02/22/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2019 | 02/14/2019 | 9/30/2019 | Y | EXP | 215 | 06/21/2019 | 08/09/2019 | 49 | 0 | 49 |  |  | 8/21/2019 | Connected |  | N
National Grid | AVON | 174521 | 02322 | 750 | Solar | 05_14_2377N | 10/07/2010 | 10/07/2010 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2011 | 10/07/2010 | 10/31/2012 | Y | STD | 503 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 8/3/2012 | Connected |  | N
National Grid | SAUGUS | 704582 | 01906 | 480 | Solar | 05_07_75W7 | 10/02/2025 | 10/31/2025 | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2025 |  | 101 | 25 | 76 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 247703 | 01060 | 7.6 | Solar | 05_12_23W2 | 08/08/2019 | 09/11/2019 | 23 | 19 | 4 | 09/12/2019 | 09/12/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2019 | 08/08/2019 | 6/15/2021 | Y | EXP | 365 | 02/01/2020 | 03/03/2020 | 31 | 0 | 31 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 185248 | 02368 | 4675 | Solar | 05_09_909W1 | 09/26/2018 | 10/08/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2018 | 11/05/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 | 09/26/2018 | 1/16/2024 | Y | STD | 903 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 208421 | 01845 | 10 | Solar | 05_07_97W1 | 03/18/2019 | 03/19/2019 | 0 | 0 | 0 | 03/20/2019 | 03/20/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2019 | 03/18/2019 | 9/2/2020 | Y | EXP | 527 | 03/04/2020 | 05/12/2020 | 69 | 0 | 69 |  |  | 5/13/2020 | Connected |  | N
National Grid | AVON | 174520 | 02322 | 1000 | Solar | 05_14_2377N | 10/07/2010 | 10/07/2010 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2011 | 10/07/2010 | 10/31/2012 | Y | STD | 503 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 8/3/2012 | Connected |  | N
National Grid | SAUGUS | 176521 | 01906 | 112 | Solar | 05_07_75W7 | 10/05/2015 | 10/05/2015 | 2 | 2 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2015 | 10/05/2015 | 10/12/2016 | Y | EXP | 335 | 03/14/2016 | 04/30/2016 | 33 | 0 | 33 | 5/9/2016 | 5/9/2016 | 5/20/2016 | Connected |  | N
National Grid | NORTHAMPTON | 261261 | 01062 | 7.6 | Solar | 05_12_23W2 | 10/21/2019 | 10/24/2019 | 3 | 2 | 1 | 10/25/2019 | 10/25/2019 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 |  | 11/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2020 | Connected |  | N
National Grid | RANDOLPH | 185190 | 02368 | 467 | Solar | 05_09_909W1 | 05/15/2018 | 05/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/08/2018 | 06/07/2018 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  | 3/2/2020 | N | STD | 445 |  |  | 0 | 0 | 0 |  |  | 12/30/2019 | Connected |  | N
National Grid | HAVERHILL | 229376 | 01835 | 3.8 | Solar | 05_07_97W1 | 03/05/2020 |  | 170 | 126 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 174519 | 02322 | 1000 | Solar | 05_14_2377N | 10/07/2010 | 10/07/2010 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2011 | 10/07/2010 | 10/31/2012 | Y | STD | 503 |  |  | 0 | 0 | 0 | 1/18/2013 | 1/18/2013 | 8/3/2012 | Connected |  | N
National Grid | SAUGUS | 177482 | 01906 | 57.6 | Solar | 05_07_75W7 | 09/21/2016 | 09/21/2016 | 4 | 4 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2016 |  | 9/27/2017 | N | EXP | 343 |  |  | 0 | 0 | 0 | 4/10/2017 | 4/10/2017 | 4/13/2017 | Connected |  | N
National Grid | NORTHAMPTON | 267636 | 01062 | 3.8 | Solar | 05_12_23W2 | 12/04/2019 | 12/10/2019 | 3 | 0 | 3 | 12/11/2019 | 12/11/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/04/2019 | 6/3/2021 | Y | EXP | 365 | 11/04/2020 | 01/19/2021 | 76 | 0 | 76 |  |  | 4/14/2021 | Connected |  | N
National Grid | RANDOLPH | 232983 | 02368 | 0 | Solar | 05_09_909W1 | 06/03/2019 | 06/12/2019 | 6 | 0 | 6 | 06/13/2019 | 06/13/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2019 | Connected |  | N
National Grid | METHUEN | 229007 | 01844 | 7.6 | Solar | 05_07_97W1 | 10/15/2019 | 10/22/2019 | 4 | 0 | 4 | 10/23/2019 | 10/23/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 |  | 5/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 174523 | 02322 | 1000 | Solar | 05_14_2377N | 10/07/2010 | 10/07/2010 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2011 | 10/07/2010 | 10/31/2012 | Y | STD | 503 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 8/3/2012 | Connected |  | N
National Grid | SAUGUS | 178042 | 01906 | 960 | Solar | 05_07_75W7 | 05/01/2017 | 05/01/2017 | 15 | 13 | 2 |  |  | 0 | 0 | 0 | 07/12/2017 | 07/27/2017 | 11 | 0 | 11 | 05/22/2017 | 06/16/2017 | 18 | 4 | 14 | 07/27/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 10/27/2017 | 05/01/2017 | 7/31/2020 | Y | STD | 761 | 08/20/2019 | 06/03/2020 | 286 | 0 | 286 | 6/4/2020 | 7/27/2020 | 8/4/2020 | Connected |  | N
National Grid | NORTHAMPTON | 269234 | 01060 | 7.6 | Solar | 05_12_23W2 | 12/26/2019 | 01/06/2020 | 5 | 0 | 5 | 01/07/2020 | 01/07/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/26/2019 | 3/12/2021 | Y | EXP | 365 | 10/03/2020 | 01/18/2021 | 107 | 0 | 107 |  |  | 2/5/2021 | Connected |  | N
National Grid | RANDOLPH | 253195 | 02368 | 0 | Solar | 05_09_909W1 | 09/09/2019 | 09/10/2019 | 0 | 0 | 0 | 09/11/2019 | 09/11/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2019 |  | 9/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2020 | Connected |  | N
National Grid | SALISBURY | 234729 | 01952 | 7.6 | Solar | 05_07_97W1 | 08/02/2019 | 08/05/2019 | 0 | 0 | 0 | 08/06/2019 | 08/06/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 | 08/02/2019 | 10/2/2020 | Y | EXP | 365 | 03/28/2020 | 05/08/2020 | 41 | 0 | 41 |  |  | 7/16/2020 | Connected |  | N
National Grid | STOUGHTON | 175030 | 02072 | 50 | Solar | 05_14_2377N | 03/21/2013 | 03/21/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 194829 | 01906 | 600 | Solar | 05_07_75W7 | 09/19/2018 | 10/01/2018 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 11/06/2018 | 59 | 7 | 52 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 291136 | 01060 | 10 | Solar | 05_12_23W2 | 07/30/2020 | 11/24/2020 | 79 | 76 | 3 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 07/30/2020 | 10/13/2021 | Y | EXP | 365 | 03/25/2021 | 05/27/2021 | 63 | 0 | 63 |  |  | 6/3/2021 | Connected |  | N
National Grid | RANDOLPH | 338313 | 02368 | 7.6 | Solar | 05_09_909W1 | 01/22/2021 | 01/25/2021 | 0 | 0 | 0 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2021 |  | 3/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | Connected |  | N
National Grid | SALISBURY | 244985 | 01952 | 8.82 | Solar | 05_07_97W1 | 08/20/2019 | 08/23/2019 | 3 | 3 | 0 | 08/26/2019 | 08/26/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/20/2019 | 4/23/2020 | Y | EXP | 225 | 10/23/2019 | 11/08/2019 | 16 | 0 | 16 |  |  | 12/18/2019 | Connected |  | N
National Grid | STOUGHTON | 175029 | 02072 | 300 | Solar | 05_14_2377N | 03/21/2013 | 03/21/2013 | 6 | 0 | 6 | 04/02/2013 | 04/02/2013 | 0 | 0 | 0 | 06/11/2013 | 06/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2013 |  | 8/30/2013 | N | EXP | 79 |  |  | 0 | 0 | 0 | 8/23/2013 | 8/23/2013 | 9/19/2013 | Connected |  | N
National Grid | SAUGUS | 362507 | 01906 | 900 | Solar | 05_07_75W7 | 09/23/2021 | 01/31/2022 | 88 | 78 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 02/25/2022 | 17 | 1 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSBURG | 296623 | 01096 | 0 | Solar | 05_12_23W2 | 06/16/2020 | 07/07/2020 | 14 | 14 | 0 | 07/08/2020 | 07/08/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2020 |  | 8/16/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2021 | Connected |  | N
National Grid | RANDOLPH | 483548 | 02368 | 3.8 | Solar | 05_09_909W1 | 12/20/2022 | 12/22/2022 | 2 | 0 | 2 | 12/23/2022 | 12/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/20/2022 | 6/30/2024 | Y | EXP | 365 | 05/16/2023 | 06/30/2023 | 45 | 0 | 45 |  |  | 7/25/2023 | Connected |  | N
National Grid | SALISBURY | 249024 | 01952 | 6 | Solar | 05_07_97W1 | 09/25/2019 | 10/16/2019 | 14 | 14 | 0 | 10/17/2019 | 10/17/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2019 |  | 9/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2020 | Connected |  | N
National Grid | STOUGHTON | 174350 | 02072 | 675 | Solar | 05_14_2381 | 05/08/2012 | 05/08/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2012 | 07/03/2012 | 28 | 0 | 28 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 367269 | 01906 | 7.6 | Solar | 05_07_75W7 | 07/15/2021 | 07/30/2021 | 12 | 11 | 1 | 08/02/2021 | 08/02/2021 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2021 |  | 10/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2022 | Connected |  | N
National Grid | NORTHAMPTON | 371674 | 01062 | 7.6 | Solar | 05_12_23W2 | 08/02/2021 | 01/04/2022 | 2 | 0 | 2 | 08/05/2021 | 08/05/2021 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 498813 | 02368 | 6 | Solar | 05_09_909W1 | 02/03/2023 | 02/06/2023 | 1 | 0 | 1 | 02/07/2023 | 02/07/2023 | 66 | 48 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2023 |  | 5/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2023 | Connected |  | N
National Grid | SALISBURY | 276855 | 01952 | 10 | Solar | 05_07_97W1 | 03/06/2020 | 04/24/2020 | 36 | 35 | 1 | 04/27/2020 | 04/27/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2020 | 03/06/2020 | 3/9/2021 | Y | EXP | 365 | 07/29/2020 | 08/28/2020 | 30 | 0 | 30 |  |  | 10/7/2020 | Connected |  | N
National Grid | STOUGHTON | 177799 | 02072 | 266.4 | Solar | 05_14_2381 | 08/03/2017 | 08/03/2017 | 14 | 14 | 0 | 08/18/2017 | 08/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2017 |  | 8/9/2018 | N | EXP | 323 | 01/15/2018 | 01/15/2018 | 0 | 0 | 0 | 1/8/2018 | 1/8/2018 | 1/8/2018 | Connected |  | N
National Grid | SAUGUS | 430213 | 01906 | 3.8 | Solar | 05_07_75W7 | 05/25/2022 | 05/26/2022 | 1 | 0 | 1 | 05/27/2022 | 05/27/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2022 | 05/25/2022 | 6/7/2024 | Y | EXP | 365 | 12/01/2022 | 06/08/2023 | 190 | 0 | 190 |  |  | 6/14/2023 | Connected |  | N
National Grid | NORTHAMPTON | 374128 | 01060 | 10 | Solar | 05_12_23W2 | 09/17/2021 | 01/05/2022 | 2 | 0 | 2 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 | 09/17/2021 | 4/7/2023 | Y | EXP | 365 | 02/22/2022 | 03/22/2022 | 28 | 0 | 28 |  |  | 6/8/2022 | Connected |  | N
National Grid | RANDOLPH | 507310 | 02368 | 3.8 | Solar | 05_09_909W1 | 04/28/2023 | 05/01/2023 | 1 | 0 | 1 | 05/02/2023 | 05/02/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 323027 | 01952 | 9.8 | Solar | 05_07_97W1 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 11/24/2020 | 11/23/2022 | Y | EXP | 365 | 08/18/2021 | 10/12/2021 | 54 | 3 | 51 |  |  | 12/22/2021 | Connected |  | N
National Grid | STOUGHTON | 225135 | 02072 | 486 | Solar | 05_14_2381 | 05/07/2019 | 06/06/2019 | 21 | 20 | 1 | 06/07/2019 | 06/07/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 480025 | 01906 | 86 | Solar | 05_07_75W7 | 11/30/2022 | 12/29/2022 | 20 | 10 | 10 |  |  | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 380188 | 01062 | 9.8 | Solar | 05_12_23W2 | 09/18/2021 | 12/08/2021 | 2 | 0 | 2 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 514076 | 02368 | 9.86 | Solar | 05_09_909W1 | 04/14/2023 | 04/19/2023 | 2 | 0 | 2 | 04/20/2023 | 04/20/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2023 | 04/14/2023 | 6/6/2024 | Y | EXP | 365 | 08/01/2023 | 08/04/2023 | 4 | 0 | 4 |  |  | 8/28/2023 | Connected |  | N
National Grid | AMESBURY | 324428 | 01913 | 7.6 | Solar | 05_07_97W1 | 11/30/2020 | 12/03/2020 | 2 | 0 | 2 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 | 11/30/2020 | 4/30/2022 | Y | EXP | 365 | 10/07/2021 | 10/12/2021 | 5 | 0 | 5 |  |  | 3/4/2022 | Connected |  | N
National Grid | STOUGHTON | 732305 | 02072 | 470 | Solar | 05_14_2384 | 01/30/2026 | 02/23/2026 | 14 | 7 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/24/2026 |  | 27 | 17 | 10 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SAUGUS | 500180 | 01906 | 120 | Solar | 05_07_75W7 | 02/13/2023 | 02/22/2023 | 6 | 0 | 6 | 02/23/2023 | 02/23/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 4/15/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | NORTHAMPTON | 393404 | 01062 | 7.25 | Solar | 05_12_23W2 | 12/13/2021 | 01/10/2022 | 6 | 3 | 3 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 | 12/13/2021 | 8/2/2023 | Y | EXP | 365 | 05/06/2022 | 06/03/2022 | 29 | 0 | 29 |  |  | 8/11/2022 | Connected |  | N
National Grid | RANDOLPH | 540910 | 02368 | 6 | Solar | 05_09_909W1 | 08/11/2023 | 08/17/2023 | 5 | 2 | 3 | 08/18/2023 | 08/18/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 325702 | 01913 | 7.6 | Solar | 05_07_97W1 | 12/07/2020 | 12/08/2021 | 4 | 0 | 4 | 12/14/2020 | 12/14/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 12/07/2020 | 8/8/2023 | Y | EXP | 365 | 03/31/2022 | 04/25/2022 | 26 | 0 | 26 |  |  | 4/10/2023 | Connected |  | N
National Grid | STOUGHTON | 184585 | 02072 | 1920 | Solar | 05_14_2384 | 08/07/2018 | 08/22/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/23/2018 | 11/27/2018 | 58 | 38 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2019 | 08/07/2018 | 1/6/2022 | Y | STD | 329 |  |  | 0 | 0 | 0 |  |  | 12/30/2021 | Connected |  | N
National Grid | SAUGUS | 516245 | 01906 | 75 | Solar | 05_07_75W7 | 04/28/2023 | 01/06/2024 | 172 | 162 | 10 | 01/08/2024 | 01/08/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 4/3/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 3/27/2026 | Connected |  | Y
National Grid | NORTHAMPTON | 438832 | 01062 | 15.2 | Solar | 05_12_23W2 | 06/20/2022 | 06/22/2022 | 2 | 0 | 2 | 06/23/2022 | 06/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  | 7/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/25/2023 | Connected |  | Y
National Grid | RANDOLPH | 549354 | 02368 | 2.61 | Solar | 05_09_909W1 | 09/12/2023 | 09/29/2023 | 13 | 8 | 5 | 10/02/2023 | 10/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 | 09/12/2023 | 12/7/2024 | Y | EXP | 365 | 03/07/2024 | 03/06/2024 | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | LOWELL | 330177 | 01852 | 12 | Solar | 05_07_97W1 | 12/07/2020 | 04/01/2021 | 82 | 79 | 3 | 04/02/2021 | 04/02/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  | 6/8/2022 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 243763 | 02072 | 600 | Natural Gas | 05_14_2384 | 10/27/2020 | 12/03/2020 | 25 | 19 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2020 | 01/14/2021 | 28 | 9 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2021 | 10/27/2020 | 10/28/2022 | Y | STD | 399 | 09/22/2022 | 09/21/2022 | 0 | 0 | 0 |  |  | 10/5/2022 | Connected |  | N
National Grid | SAUGUS | 516478 | 01906 | 150 | Solar | 05_07_75W7 | 04/07/2023 | 04/21/2023 | 9 | 0 | 9 |  |  | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 471801 | 01062 | 3.8 | Solar | 05_12_23W2 | 11/21/2022 | 11/27/2022 | 4 | 0 | 4 | 11/28/2022 | 11/28/2022 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 555710 | 02368 | 5 | Solar | 05_09_909W1 | 09/15/2023 | 09/19/2023 | 2 | 0 | 2 | 09/20/2023 | 09/20/2023 | 20 | 0 | 20 | 10/24/2023 | 12/06/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 12/06/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 12/11/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 329783 | 01852 | 3.8 | Solar | 05_07_97W1 | 01/18/2021 | 01/27/2021 | 7 | 4 | 3 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 | 01/18/2021 | 1/27/2022 | Y | EXP | 365 | 04/27/2021 | 05/21/2021 | 24 | 0 | 24 |  |  | 9/1/2021 | Connected |  | N
National Grid | STOUGHTON | 174373 | 02072 | 260 | Solar | 05_14_2385 | 05/29/2012 | 05/29/2012 | 11 | 0 | 11 | 06/18/2012 | 06/18/2012 | 0 | 0 | 0 | 12/17/2012 | 01/30/2013 | 29 | 0 | 29 |  |  | 0 | 0 | 0 | 01/30/2013 | 29 | 0 | 29 |  |  | 0 | 0 | 0 | 1/30/2013 | 05/29/2012 | 10/31/2014 | Y | EXP | 639 | 07/28/2014 | 08/19/2016 | 513 | 0 | 513 | 5/14/2015 | 5/14/2015 | 12/3/2014 | Connected |  | N
National Grid | SAUGUS | 661275 | 01906 | 10 | Solar | 05_07_75W7 | 12/17/2024 | 01/10/2025 | 5 | 0 | 5 | 01/13/2025 | 01/13/2025 | 27 | 2 | 25 | 03/03/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 12/17/2024 | 3/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | NORTHAMPTON | 527299 | 01060 | 16 | Solar | 05_12_23W2 | 11/01/2023 | 05/24/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2023 | Connected |  | N
National Grid | RANDOLPH | 571152 | 02368 | 10 | Solar | 05_09_909W1 | 11/28/2023 | 12/12/2023 | 11 | 8 | 3 | 12/13/2023 | 12/13/2023 | 28 | 5 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 | 11/28/2023 | 2/9/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  | 5/10/2024 | Connected |  | N
National Grid | LOWELL | 336662 | 01852 | 10 | Solar | 05_07_97W1 | 02/05/2021 | 02/12/2021 | 5 | 5 | 0 | 02/16/2021 | 02/16/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 | 02/05/2021 | 2/11/2022 | Y | EXP | 365 | 04/17/2021 | 05/10/2021 | 23 | 0 | 23 |  |  | 5/12/2021 | Connected |  | N
National Grid | RANDOLPH | 175120 | 02368 | 2850 | Solar | 05_14_2385 | 10/18/2013 | 10/18/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2013 | 12/11/2013 | 31 | 0 | 31 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2015 | 10/18/2013 | 12/31/2016 | Y | STD | 725 | 06/23/2016 | 04/07/2017 | 197 | 0 | 197 | 12/21/2016 | 12/21/2016 | 12/28/2016 | Connected |  | N
National Grid | SAUGUS | 676560 | 01906 | 11.5 | Solar | 05_07_75W7 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 119 | 96 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 03/07/2025 | 9/30/2026 | Y | EXP | 365 | 11/18/2025 | 03/11/2026 | 114 | 0 | 114 |  |  | 3/12/2026 | Connected |  | N
National Grid | NORTHAMPTON | 570482 | 01062 | 6 | Solar | 05_12_23W2 | 11/22/2023 | 11/28/2023 | 3 | 1 | 2 | 11/29/2023 | 11/29/2023 | 27 | 6 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 | 11/22/2023 | 1/10/2025 | Y | EXP | 365 | 04/03/2024 | 04/03/2024 | 1 | 0 | 1 |  |  | 4/10/2024 | Connected |  | N
National Grid | RANDOLPH | 585752 | 02368 | 5 | Solar | 05_09_909W1 | 02/23/2024 | 03/04/2024 | 7 | 5 | 2 | 03/05/2024 | 03/05/2024 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2024 | Connected |  | N
National Grid | CHELMSFORD | 342575 | 01824 | 7.6 | Solar | 05_07_97W1 | 02/24/2021 | 03/02/2021 | 3 | 0 | 3 | 03/03/2021 | 03/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2021 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 175685 | 02368 | 4999 | Solar | 05_14_2385 | 12/23/2014 | 12/23/2014 | 16 | 15 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2015 | 01/21/2015 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 | 12/23/2014 | 5/31/2017 | Y | STD | 671 | 01/16/2017 | 07/27/2017 | 133 | 0 | 133 | 6/5/2017 | 6/5/2017 | 6/7/2017 | Connected |  | N
National Grid | SAUGUS | 340182 | 01906 | 100 | Solar | 05_07_797W1 | 02/04/2021 | 02/17/2021 | 7 | 0 | 7 | 02/18/2021 | 02/18/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 |  | 4/15/2026 | N | EXP | 374 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 575934 | 01062 | 9.86 | Solar | 05_12_23W2 | 12/15/2023 | 12/20/2023 | 3 | 2 | 1 | 12/21/2023 | 12/21/2023 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 | 12/15/2023 | 5/22/2025 | Y | EXP | 365 | 05/21/2024 | 06/04/2024 | 15 | 0 | 15 |  |  | 9/26/2024 | Connected |  | Y
National Grid | RANDOLPH | 645469 | 02368 | 7.6 | Solar | 05_09_909W1 | 10/14/2024 | 10/21/2024 | 1 | 0 | 1 | 10/22/2024 | 10/22/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/14/2024 | 11/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | CHELMSFORD | 366170 | 01824 | 6 | Solar | 05_07_97W1 | 06/25/2021 | 06/30/2021 | 4 | 2 | 2 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2021 |  | 8/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2021 | Connected |  | N
National Grid | RANDOLPH | 176502 | 02368 | 499.5 | Solar | 05_14_2385 | 02/08/2016 | 02/08/2016 | 3 | 3 | 0 | 02/16/2016 | 02/16/2016 | 493 | 0 | 493 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/15/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 729872 | 01906 | 7.6 | Solar | 05_07_797W1 | 10/29/2025 | 12/01/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2026 | 10/29/2025 | 2/5/2027 | Y | EXP | 365 | 04/02/2026 |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTHAMPTON | 594738 | 01062 | 2.4 | Solar | 05_12_23W2 | 03/15/2024 | 04/01/2024 | 12 | 10 | 2 | 04/02/2024 | 04/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 647431 | 02368 | 100 | Solar | 05_09_909W1 | 10/16/2024 | 11/12/2024 | 18 | 9 | 9 |  |  | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 392185 | 01824 | 6 | Solar | 05_07_97W1 | 11/18/2021 | 01/05/2022 | 3 | 0 | 3 | 11/23/2021 | 11/23/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/18/2021 | 2/9/2023 | Y | EXP | 365 | 01/19/2022 | 02/08/2022 | 21 | 0 | 21 |  |  | 2/12/2022 | Connected |  | N
National Grid | RANDOLPH | 174303 | 02368 | 500 | Solar | 05_14_2387 | 12/29/2011 | 12/29/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 755889 | 01906 | 10 | Solar | 05_07_797W1 | 03/18/2026 | 03/20/2026 | 2 | 0 | 2 | 03/23/2026 | 03/23/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 620744 | 01060 | 7.6 | Solar | 05_12_23W2 | 06/27/2024 | 07/15/2024 | 3 | 0 | 3 | 07/16/2024 | 07/16/2024 | 15 | 0 | 15 | 08/21/2024 | 09/17/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 09/17/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 9/23/2024 | 06/27/2024 | 10/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2025 | Connected |  | N
National Grid | RANDOLPH | 647909 | 02368 | 7.6 | Solar | 05_09_909W1 | 10/21/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/21/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | TEWKSBURY | 445564 | 01876 | 10 | Solar | 05_07_97W1 | 08/01/2022 | 08/02/2022 | 1 | 0 | 1 | 08/03/2022 | 08/03/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 | 08/01/2022 | 3/1/2024 | Y | EXP | 365 | 03/02/2023 | 03/01/2023 | 0 | 0 | 0 |  |  | 3/7/2023 | Connected |  | N
National Grid | STOUGHTON | 174583 | 02072 | 1000 | Solar | 05_14_2387 | 12/16/2009 | 12/16/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2011 | 12/16/2009 | 10/31/2012 | Y | STD | 454 |  |  | 0 | 0 | 0 | 9/17/2013 | 9/17/2013 | 9/17/2012 | Connected |  | N
National Grid | SAUGUS | 758347 | 01906 | 19.38 | Solar | 05_07_797W1 | 03/23/2026 | 03/26/2026 | 3 | 0 | 3 | 03/27/2026 | 03/27/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 621777 | 01062 | 23 | Solar | 05_12_23W2 | 07/01/2024 | 07/03/2024 | 2 | 0 | 2 | 07/05/2024 | 07/05/2024 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2024 | Connected |  | N
National Grid | RANDOLPH | 657538 | 02368 | 7.6 | Solar | 05_09_909W1 | 11/28/2024 | 01/15/2025 | 4 | 0 | 4 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | BILLERICA | 466464 | 01862 | 10 | Solar | 05_07_97W1 | 10/12/2022 | 10/13/2022 | 1 | 0 | 1 | 10/14/2022 | 10/14/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 | 10/12/2022 | 6/14/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2023 | Connected |  | N
National Grid | STOUGHTON | 174608 | 02072 | 1000 | Solar | 05_14_2387 | 12/16/2009 | 12/16/2009 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2011 | 12/16/2009 | 4/5/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 4/5/2012 | Connected |  | N
National Grid | SAUGUS | 174862 | 01906 | 1000 | Solar | 05_07_797W1 | 08/03/2012 | 08/03/2012 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2012 | 11/24/2012 | 50 | 0 | 50 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2013 |  | 12/31/2012 | N | STD | 178 |  |  | 0 | 0 | 0 |  |  | 8/11/2015 | Withdrawn |  | N
National Grid | NORTHAMPTON | 621470 | 01062 | 7.6 | Solar | 05_12_23W2 | 06/28/2024 | 07/15/2024 | 4 | 1 | 3 | 07/16/2024 | 07/16/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 06/28/2024 | 8/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | RANDOLPH | 657908 | 02368 | 22.8 | Solar | 05_09_909W1 | 12/11/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | BILLERICA | 475958 | 01862 | 3.8 | Solar | 05_07_97W1 | 06/07/2023 | 11/13/2023 | 108 | 106 | 2 | 11/14/2023 | 11/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 174607 | 02324 | 1000 | Solar | 05_14_2387 | 12/16/2009 | 12/16/2009 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2011 | 12/16/2009 | 4/5/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 4/5/2012 | Connected |  | N
National Grid | SAUGUS | 174861 | 01906 | 3000 | Solar | 05_07_797W1 | 08/03/2012 | 08/03/2012 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2012 | 11/24/2012 | 50 | 0 | 50 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2013 | 08/03/2012 | 6/1/2014 | Y | STD | 339 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 8/11/2015 | Connected |  | N
National Grid | NORTHAMPTON | 627380 | 01060 | 6.4 | Solar | 05_12_23W2 | 07/24/2024 | 08/21/2024 | 17 | 14 | 3 | 08/22/2024 | 08/22/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 660016 | 02368 | 5.76 | Solar | 05_09_909W1 | 12/11/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/11/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 508496 | 01862 | 6 | Solar | 05_07_97W1 | 03/23/2023 | 04/12/2023 | 15 | 12 | 3 | 04/13/2023 | 04/13/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2023 | 03/23/2023 | 10/3/2024 | Y | EXP | 365 | 08/01/2023 | 10/04/2023 | 65 | 0 | 65 |  |  | 11/1/2023 | Connected |  | N
National Grid | BRIDGEWATER | 174606 | 02324 | 1000 | Solar | 05_14_2387 | 12/16/2009 | 12/16/2009 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2011 | 12/16/2009 | 4/5/2012 | Y | STD | 226 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 4/5/2012 | Connected |  | N
National Grid | SAUGUS | 175221 | 01906 | 19 | Solar | 05_07_797W1 | 11/03/2014 | 11/03/2014 | 7 | 4 | 3 | 11/14/2014 | 11/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 |  | 1/30/2015 | N | EXP | 72 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 5/10/2016 | Connected |  | N
National Grid | NORTHAMPTON | 641554 | 01060 | 6.72 | Solar | 05_12_23W2 | 09/19/2024 | 10/15/2024 | 5 | 3 | 2 | 10/16/2024 | 10/16/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/19/2024 | 1/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | RANDOLPH | 663194 | 02368 | 7.6 | Solar | 05_09_909W1 | 01/06/2025 | 01/30/2025 | 9 | 4 | 5 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | WESTFORD | 507261 | 01886 | 6 | Solar | 05_07_97W1 | 03/23/2023 | 03/28/2023 | 3 | 0 | 3 | 03/29/2023 | 03/29/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/23/2023 | 9/11/2024 | Y | EXP | 365 | 07/20/2023 | 09/08/2023 | 51 | 0 | 51 |  |  | 9/21/2023 | Connected |  | N
National Grid | BRIDGEWATER | 174144 | 02324 | 999 | Solar | 05_14_2389 | 04/17/2012 | 04/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2012 |  | 12/3/2012 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 176671 | 01906 | 499 | Solar | 05_07_797W1 | 10/22/2015 | 10/22/2015 | 2 | 2 | 0 | 10/27/2015 | 10/27/2015 | 127 | 0 | 127 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/28/2016 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 643916 | 01062 | 5.76 | Solar | 05_12_23W2 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | Y
National Grid | RANDOLPH | 695565 | 02368 | 7.68 | Solar | 05_09_909W1 | 06/10/2025 | 07/14/2025 | 1 | 0 | 1 | 07/16/2025 | 07/16/2025 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | WESTFORD | 522517 | 01886 | 10 | Solar | 05_07_97W1 | 06/01/2023 | 08/21/2023 | 55 | 55 | 0 | 08/22/2023 | 08/22/2023 | 40 | 7 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 176089 | 02324 | 990 | Solar | 05_14_2396N | 01/30/2015 | 01/30/2015 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 10/09/2015 | 11/04/2015 | 17 | 17 | 0 | 1/12/2016 |  | 8/31/2015 | N | STD | 134 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 176910 | 01906 | 499 | Solar | 05_07_797W1 | 03/08/2016 | 03/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2016 | 03/18/2016 | 6 | 0 | 6 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2016 | 03/08/2016 | 12/15/2017 | Y | STD | 528 | 11/10/2016 | 08/09/2017 | 185 | 0 | 185 | 12/21/2016 | 12/21/2016 | 12/8/2017 | Connected |  | N
National Grid | NORTHAMPTON | 645402 | 01060 | 7.6 | Solar | 05_12_23W2 | 10/08/2024 | 11/05/2024 | 4 | 0 | 4 | 11/06/2024 | 11/06/2024 | 23 | 0 | 23 | 12/31/2024 | 01/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 01/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 700054 | 02368 | 11.5 | Solar | 05_09_909W1 | 06/20/2025 | 06/25/2025 | 3 | 0 | 3 | 06/26/2025 | 06/26/2025 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid | WESTFORD | 526253 | 01886 | 10 | Solar | 05_07_97W1 | 05/26/2023 |  | 82 | 80 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 176088 | 02324 | 990 | Solar | 05_14_2396N | 01/30/2015 | 01/30/2015 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 10/09/2015 | 11/04/2015 | 17 | 17 | 0 | 1/12/2016 |  | 8/31/2015 | N | STD | 134 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 186863 | 01906 | 4998 | Solar | 05_07_797W1 | 05/31/2018 | 05/31/2018 | 47 | 4 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2018 | 09/04/2018 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 11/30/2020 | N | STD | 261 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 652136 | 01060 | 3.8 | Solar | 05_12_23W2 | 11/14/2024 | 01/17/2025 | 27 | 21 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 11/14/2024 | 4/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | RANDOLPH | 721445 | 02368 | 10 | Solar | 05_09_909W2 | 09/24/2025 | 10/04/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 | 09/24/2025 | 12/10/2026 | Y | EXP | 365 | 01/15/2026 |  | 77 | 0 | 77 |  |  |  | Construction |  | N
National Grid | WESTFORD | 538902 | 01886 | 10 | Solar | 05_07_97W1 | 07/10/2023 | 08/31/2023 | 35 | 34 | 1 | 09/01/2023 | 09/01/2023 | 70 | 52 | 18 | 01/31/2024 | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 176087 | 02324 | 990 | Solar | 05_14_2396N | 01/30/2015 | 01/30/2015 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 10/09/2015 | 11/04/2015 | 17 | 17 | 0 | 1/12/2016 |  | 8/31/2015 | N | STD | 134 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 188766 | 01906 | 200 | Solar | 05_07_797W1 | 06/21/2018 | 06/21/2018 | 3 | 0 | 3 | 07/02/2018 | 07/02/2018 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 |  | 8/21/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | Connected |  | N
National Grid | NORTHAMPTON | 658919 | 01060 | 3.8 | Solar | 05_12_23W2 | 12/06/2024 | 01/08/2025 | 15 | 9 | 6 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/06/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | RANDOLPH | 175368 | 02368 | 34.2 | Solar | 05_09_909W2 | 02/06/2014 | 02/06/2014 | 5 | 0 | 5 | 02/14/2014 | 02/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2014 |  | 5/30/2014 | N | EXP | 98 |  |  | 0 | 0 | 0 | 2/25/2014 | 2/25/2014 | 6/17/2014 | Connected |  | N
National Grid | WESTFORD | 546614 | 01886 | 3.8 | Solar | 05_07_97W1 | 08/16/2023 | 08/17/2023 | 1 | 0 | 1 | 08/18/2023 | 08/18/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 176122 | 02324 | 990 | Solar | 05_14_2396N | 01/30/2015 | 01/30/2015 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 10/09/2015 | 11/04/2015 | 17 | 17 | 0 | 4/15/2015 |  | 8/31/2015 | N | STD | 138 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 316478 | 01906 | 100 | Solar | 05_07_797W1 | 10/02/2020 | 11/03/2020 | 20 | 14 | 6 | 11/04/2020 | 11/04/2020 | 37 | 15 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2020 |  | 8/19/2022 | N | EXP | 592 |  |  | 0 | 0 | 0 |  |  | 8/1/2022 | Connected |  | N
National Grid | NORTHAMPTON | 667502 | 01062 | 11.4 | Solar | 05_12_23W2 | 02/04/2025 | 05/20/2025 | 33 | 25 | 8 | 05/21/2025 | 05/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 177387 | 02368 | 0 | Solar | 05_09_909W2 | 11/30/2016 | 11/30/2016 | 0 | 0 | 0 | 12/01/2016 | 12/01/2016 | 295 | 0 | 295 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/6/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 548604 | 01821 | 10 | Solar | 05_07_97W1 | 08/23/2023 | 08/29/2023 | 4 | 0 | 4 | 08/30/2023 | 08/30/2023 | 90 | 66 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 |  | 2/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 176121 | 02324 | 990 | Solar | 05_14_2396N | 01/30/2015 | 01/30/2015 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 10/09/2015 | 11/04/2015 | 17 | 17 | 0 | 1/12/2016 |  | 8/31/2015 | N | STD | 134 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 331425 | 01906 | 3286 | Solar | 05_07_797W1 | 01/15/2021 | 02/16/2021 | 20 | 12 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2021 | 08/03/2021 | 117 | 93 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2022 | 01/15/2021 | 11/7/2024 | Y | STD | 700 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 669318 | 01062 | 10 | Solar | 05_12_23W2 | 01/31/2025 | 04/17/2025 | 21 | 17 | 4 | 04/18/2025 | 04/18/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 184687 | 02368 | 990 | Solar | 05_09_909W2 | 05/14/2018 | 06/04/2018 | 1 | 0 | 1 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2019 |  | 7/22/2020 | N | STD | 546 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 569520 | 01952 | 7.6 | Solar | 05_07_97W1 | 11/21/2023 | 12/12/2023 | 15 | 14 | 1 | 12/13/2023 | 12/13/2023 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2024 | Connected |  | N
National Grid | BRIDGEWATER | 175619 | 02324 | 2000 | Hydro | 05_14_2399 | 04/30/2014 | 04/30/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/05/2014 | 08/12/2014 | 68 | 0 | 68 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 363047 | 01906 | 30 | Solar | 05_07_797W1 | 07/19/2021 | 08/04/2021 | 12 | 6 | 6 | 08/05/2021 | 08/05/2021 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2021 |  | 11/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2022 | Connected |  | Y
National Grid | NORTHAMPTON | 674054 | 01062 | 5.76 | Solar | 05_12_23W2 | 03/07/2025 | 03/19/2025 | 8 | 1 | 7 | 03/20/2025 | 03/20/2025 | 44 | 29 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | RANDOLPH | 190049 | 02368 | 990 | Solar | 05_09_909W2 | 08/28/2018 | 11/26/2018 | 59 | 28 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2018 | 03/22/2019 | 81 | 62 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 572609 | 01952 | 6 | Solar | 05_07_97W1 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 28 | 5 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2024 | 12/07/2023 | 4/3/2025 | Y | EXP | 365 | 04/25/2024 | 06/18/2024 | 55 | 0 | 55 |  |  | 8/5/2024 | Connected |  | N
National Grid | BRIDGEWATER | 405845 | 02324 | 0 | Battery Add-On | 05_14_2399 | 01/25/2022 | 02/03/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2022 | 03/02/2022 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 383230 | 01906 | 3000 | Solar | 05_07_797W1 | 03/11/2022 | 03/25/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2022 | 05/20/2022 | 39 | 20 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 679427 | 01060 | 6 | Solar | 05_12_23W2 | 03/24/2025 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 197077 | 02368 | 6 | Solar | 05_09_909W2 | 12/07/2018 | 01/10/2019 | 5 | 0 | 5 | 01/11/2019 | 01/11/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 | 12/07/2018 | 1/28/2020 | Y | EXP | 365 | 03/20/2019 | 03/19/2019 | 0 | 0 | 0 |  |  | 7/16/2019 | Connected |  | N
National Grid | SALISBURY | 575266 | 01952 | 3.19 | Solar | 05_07_97W1 | 12/20/2023 | 01/02/2024 | 6 | 1 | 5 | 01/03/2024 | 01/03/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 | 12/20/2023 | 2/14/2025 | Y | EXP | 365 | 05/02/2024 | 06/25/2024 | 55 | 0 | 55 |  |  | 7/10/2024 | Connected |  | N
National Grid | BRIDGEWATER | 419852 | 02324 | 0 | Other | 05_14_2405 | 06/14/2022 | 08/01/2022 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2022 | 08/24/2022 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SAUGUS | 390299 | 01906 | 43.2 | Solar | 05_07_797W1 | 10/26/2021 | 01/06/2022 | 18 | 13 | 5 | 11/23/2021 | 11/23/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2021 |  | 6/28/2023 | N | EXP | 550 |  |  | 0 | 0 | 0 |  |  | 6/27/2023 | Connected |  | N
National Grid | NORTHAMPTON | 679874 | 01060 | 15.58 | Solar | 05_12_23W2 | 03/21/2025 | 03/26/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | RANDOLPH | 197016 | 02368 | 7.6 | Solar | 05_09_909W2 | 09/26/2018 | 10/16/2018 | 6 | 0 | 6 | 10/22/2018 | 10/22/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2018 | 09/26/2018 | 12/4/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2019 | Connected |  | N
National Grid | SALISBURY | 591148 | 01952 | 6 | Solar | 05_07_97W1 | 03/11/2024 | 03/14/2024 | 3 | 0 | 3 | 03/15/2024 | 03/15/2024 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 | 03/11/2024 | 6/20/2025 | Y | EXP | 365 | 05/09/2024 | 08/08/2024 | 92 | 0 | 92 |  |  | 10/22/2024 | Connected |  | N
National Grid | BRIDGEWATER | 725383 | 02324 | 500 | Solar | 05_14_2405 | 12/30/2025 |  | 63 | 56 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SAUGUS | 467978 | 01906 | 28.8 | Solar | 05_07_797W1 | 10/19/2022 | 10/21/2022 | 2 | 1 | 1 | 10/24/2022 | 10/24/2022 | 25 | 7 | 18 | 07/21/2023 | 09/18/2023 | 41 | 0 | 41 |  |  | 0 | 0 | 0 | 09/18/2023 | 41 | 0 | 41 |  |  | 0 | 0 | 0 | 9/21/2023 |  | 11/30/2025 | N | EXP | 525 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 315692 | 01062 | 3.8 | Solar | 05_12_23W3 | 10/08/2020 | 10/13/2020 | 1 | 0 | 1 | 10/14/2020 | 10/14/2020 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 295561 | 02368 | 0 | Battery Add-On | 05_09_909W2 | 06/10/2020 | 07/20/2020 | 27 | 25 | 2 | 07/21/2020 | 07/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 |  | 7/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2020 | Connected |  | N
National Grid | SALISBURY | 594854 | 01952 | 5 | Solar | 05_07_97W1 | 03/16/2024 | 03/19/2024 | 2 | 0 | 2 | 03/20/2024 | 03/20/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 | 03/16/2024 | 4/8/2025 | Y | EXP | 365 | 04/26/2024 | 05/10/2024 | 15 | 0 | 15 |  |  | 5/14/2024 | Connected |  | N
National Grid | BRIDGEWATER | 174669 | 02324 | 1980 | Solar | 05_14_2405 | 06/05/2013 | 06/05/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/17/2013 | 07/15/2013 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2014 | 06/05/2013 | 12/21/2023 | Y | STD | 15 | 10/11/2023 | 12/06/2023 | 57 | 0 | 57 |  |  | 12/29/2023 | Connected |  | N
National Grid | SAUGUS | 473567 | 01906 | 15.925 | Solar | 05_07_797W1 | 11/03/2022 | 11/07/2022 | 2 | 0 | 2 | 11/08/2022 | 11/08/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 |  | 12/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | NORTHAMPTON | 324075 | 01062 | 1.92 | Solar | 05_12_23W3 | 11/19/2020 | 11/24/2020 | 2 | 0 | 2 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 341230 | 02368 | 14.88 | Solar | 05_09_909W2 | 04/07/2021 | 04/09/2021 | 2 | 1 | 1 | 04/12/2021 | 04/12/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2021 |  | 7/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2021 | Connected |  | N
National Grid | TYNGSBORO | 598614 | 01879 | 7.6 | Solar | 05_07_97W1 | 03/26/2024 | 03/27/2024 | 1 | 0 | 1 | 03/28/2024 | 03/28/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N
National Grid | BRIDGEWATER | 176642 | 02324 | 375 | Solar | 05_14_2405 | 12/31/2015 | 12/31/2015 | 1 | 1 | 0 | 01/05/2016 | 01/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 1/9/2017 | N | EXP | 339 |  |  | 0 | 0 | 0 | 12/30/2016 | 12/30/2016 | 12/30/2016 | Connected |  | N
National Grid | SAUGUS | 482811 | 01906 | 10 | Solar | 05_07_797W1 | 12/12/2022 | 12/13/2022 | 1 | 0 | 1 | 12/14/2022 | 12/14/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 |  | 4/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2023 | Connected |  | N
National Grid | NORTHAMPTON | 490744 | 01060 | 7.6 | Solar | 05_12_23W3 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 359928 | 02368 | 8.12 | Solar | 05_09_909W2 | 06/22/2021 | 06/25/2021 | 3 | 0 | 3 | 06/28/2021 | 06/28/2021 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2021 | 06/22/2021 | 1/14/2023 | Y | EXP | 365 | 11/16/2021 | 11/15/2021 | 0 | 0 | 0 |  |  | 3/3/2022 | Connected |  | N
National Grid | TYNGSBORO | 608388 | 01879 | 5.76 | Solar | 05_07_97W1 | 05/02/2024 | 05/09/2024 | 2 | 0 | 2 | 05/10/2024 | 05/10/2024 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 | 05/02/2024 | 7/22/2025 | Y | EXP | 365 | 10/10/2024 | 02/19/2025 | 133 | 0 | 133 |  |  | 2/28/2025 | Connected |  | N
National Grid | EAST BRIDGEWATER | 396685 | 02333 | 0 | Other | 05_14_2405 | 01/14/2022 | 01/28/2022 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 03/04/2022 | 24 | 0 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 485014 | 01906 | 16 | Solar | 05_07_797W1 | 12/13/2022 | 12/27/2022 | 9 | 8 | 1 | 12/28/2022 | 12/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2023 | Connected |  | N
National Grid | NORTHAMPTON | 531279 | 01062 | 7.6 | Solar | 05_12_23W3 | 06/12/2023 |  | 44 | 27 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 442267 | 02368 | 22.8 | Solar | 05_09_909W2 | 07/07/2022 | 07/12/2022 | 4 | 3 | 1 | 07/13/2022 | 07/13/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 | 07/07/2022 | 9/3/2023 | Y | EXP | 365 | 10/13/2022 | 10/20/2022 | 8 | 0 | 8 |  |  | 11/8/2022 | Connected |  | N
National Grid | NEWBURY | 610295 | 01950 | 3.8 | Solar | 05_07_97W1 | 05/14/2024 | 05/20/2024 | 2 | 0 | 2 | 05/21/2024 | 05/21/2024 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 05/14/2024 | 6/17/2025 | Y | EXP | 365 | 09/12/2024 | 10/30/2024 | 49 | 0 | 49 |  |  | 11/8/2024 | Connected |  | N
National Grid | BRIDGEWATER | 422863 | 02324 | 0 | Other | 05_14_2405 | 08/25/2022 | 09/26/2022 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2022 | 01/03/2023 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 486457 | 01906 | 7.6 | Solar | 05_07_797W1 | 12/19/2022 | 01/03/2023 | 9 | 7 | 2 |  |  | 168 | 148 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 561352 | 01060 | 6.175 | Solar | 05_12_23W3 | 11/21/2023 | 11/22/2023 | 1 | 0 | 1 | 11/24/2023 | 11/24/2023 | 64 | 41 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 445340 | 02368 | 7.6 | Solar | 05_09_909W2 | 08/25/2022 | 08/30/2022 | 3 | 0 | 3 | 08/31/2022 | 08/31/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 | 08/25/2022 | 8/10/2024 | Y | EXP | 365 | 04/25/2023 | 08/09/2023 | 107 | 0 | 107 |  |  | 8/16/2023 | Connected |  | N
National Grid | NEWBURY | 618593 | 01950 | 10 | Solar | 05_07_97W1 | 06/17/2024 | 07/01/2024 | 6 | 4 | 2 | 07/02/2024 | 07/02/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 | 06/17/2024 | 7/31/2025 | Y | EXP | 365 | 09/19/2024 | 09/18/2024 | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | BRIDGEWATER | 213621 | 02324 | 266.4 | Solar | 05_14_301 | 08/30/2019 | 10/24/2019 | 37 | 32 | 5 | 10/25/2019 | 10/25/2019 | 8 | 0 | 8 | 11/15/2019 | 02/18/2020 | 63 | 34 | 29 |  |  | 0 | 0 | 0 | 02/18/2020 | 63 | 34 | 29 |  |  | 0 | 0 | 0 | 2/24/2020 |  | 9/22/2023 | N | EXP | 300 |  |  | 0 | 0 | 0 |  |  | 6/27/2023 | Connected |  | N
National Grid | SAUGUS | 578968 | 01906 | 10 | Solar | 05_07_797W1 | 01/18/2024 | 01/23/2024 | 3 | 0 | 3 | 01/24/2024 | 01/24/2024 | 50 | 33 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 01/18/2024 | 5/29/2025 | Y | EXP | 365 | 07/17/2024 | 07/16/2024 | 0 | 0 | 0 |  |  | 8/8/2024 | Connected |  | N
National Grid | NORTHAMPTON | 588883 | 01060 | 7.6 | Solar | 05_12_23W3 | 02/29/2024 | 04/09/2024 | 27 | 25 | 2 | 04/10/2024 | 04/10/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 02/29/2024 | 5/1/2025 | Y | EXP | 365 | 08/20/2024 | 09/06/2024 | 18 | 0 | 18 |  |  | 12/31/2024 | Connected |  | N
National Grid | RANDOLPH | 460987 | 02368 | 5.8 | Solar | 05_09_909W2 | 11/10/2022 | 11/17/2022 | 4 | 0 | 4 | 11/18/2022 | 11/18/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2022 |  | 12/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2023 | Connected |  | N
National Grid | NEWBURY | 623636 | 01952 | 7.6 | Solar | 05_07_97W1 | 07/09/2024 | 07/10/2024 | 1 | 0 | 1 | 09/23/2024 | 09/23/2024 | 26 | 9 | 17 | 11/20/2024 | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 12/17/2025 | N | EXP | 365 | 04/24/2025 | 08/07/2025 | 106 | 0 | 106 |  |  | 8/22/2025 | Connected |  | N
National Grid | BRIDGEWATER | 647606 | 02324 | 0 | Hydro | 05_14_304 | 02/04/2025 | 03/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SAUGUS | 592007 | 01906 | 8.99 | Solar | 05_07_797W1 | 02/27/2024 | 03/05/2024 | 5 | 3 | 2 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/27/2024 | 3/25/2025 | Y | EXP | 365 | 04/23/2024 | 04/23/2024 | 1 | 0 | 1 |  |  | 5/8/2024 | Connected |  | N
National Grid | NORTHAMPTON | 592548 | 01060 | 6 | Solar | 05_12_23W3 | 04/03/2024 | 04/04/2024 | 1 | 0 | 1 | 04/05/2024 | 04/05/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  | 4/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 472683 | 02368 | 10 | Solar | 05_09_909W2 | 03/21/2023 | 03/23/2023 | 2 | 0 | 2 | 03/24/2023 | 03/24/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/21/2023 | 6/12/2024 | Y | EXP | 365 | 08/01/2023 | 08/04/2023 | 4 | 0 | 4 |  |  | 10/10/2023 | Connected |  | N
National Grid | NEWBURY | 633020 | 01950 | 10 | Solar | 05_07_97W1 | 08/15/2024 | 09/03/2024 | 4 | 0 | 4 | 09/04/2024 | 09/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/15/2024 | 10/21/2025 | Y | EXP | 365 | 11/16/2024 | 02/04/2025 | 81 | 0 | 81 |  |  | 2/24/2025 | Connected |  | N
National Grid | BRIDGEWATER | 174580 | 02324 | 275 | Solar | 05_14_304 | 09/28/2011 | 09/28/2011 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2011 | 09/28/2011 | 10/31/2012 | Y | EXP | 334 |  |  | 0 | 0 | 0 | 1/24/2013 | 1/24/2013 | 8/3/2012 | Connected |  | N
National Grid | SAUGUS | 600324 | 01906 | 12 | Solar | 05_07_797W1 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2024 |  | 5/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | NORTHAMPTON | 615559 | 01060 | 5.76 | Solar | 05_12_23W3 | 06/04/2024 | 06/17/2024 | 1 | 0 | 1 | 06/18/2024 | 06/18/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 543487 | 02368 | 3 | Solar | 05_09_909W2 | 07/28/2023 | 08/01/2023 | 2 | 0 | 2 | 08/02/2023 | 08/02/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 9/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | NEWBURY | 634838 | 01951 | 10 | Solar | 05_07_97W1 | 08/23/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 10/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2025 | Connected |  | N
National Grid | BRIDGEWATER | 679224 | 02324 | 250 | Solar | 05_14_306 | 04/16/2025 | 05/13/2025 | 18 | 8 | 10 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | SAUGUS | 656387 | 01906 | 6.67 | Solar | 05_07_797W1 | 11/24/2024 | 12/11/2024 | 9 | 5 | 4 | 12/12/2024 | 12/12/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/24/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | NORTHAMPTON | 650584 | 01062 | 3.8 | Solar | 05_12_23W3 | 10/30/2024 | 11/26/2024 | 5 | 2 | 3 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | RANDOLPH | 581268 | 02368 | 11.5 | Solar | 05_09_909W2 | 01/11/2024 | 01/16/2024 | 2 | 0 | 2 | 01/17/2024 | 01/17/2024 | 98 | 77 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 6/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2024 | Connected |  | N
National Grid | NEWBURY | 637440 | 01922 | 5.76 | Solar | 05_07_97W1 | 09/03/2024 | 09/27/2024 | 2 | 0 | 2 | 09/30/2024 | 09/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 09/03/2024 | 12/11/2025 | Y | EXP | 365 | 06/12/2025 | 12/08/2025 | 180 | 0 | 180 |  |  | 12/11/2025 | Connected |  | N
National Grid | BRIDGEWATER | 556404 | 02333 | 250 | Solar | 05_14_306 | 11/22/2023 | 12/05/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/06/2023 | 01/11/2024 | 25 | 5 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2024 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 658952 | 01906 | 8.41 | Solar | 05_07_797W1 | 12/06/2024 | 04/14/2025 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 12/06/2024 | 5/29/2026 | Y | EXP | 365 | 07/24/2025 | 10/01/2025 | 70 | 0 | 70 |  |  | 10/16/2025 | Connected |  | N
National Grid | NORTHAMPTON | 654021 | 01060 | 7.6 | Solar | 05_12_23W3 | 11/13/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 | 11/13/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | RANDOLPH | 584005 | 02368 | 3.465 | Solar | 05_09_909W2 | 02/27/2024 | 03/05/2024 | 5 | 1 | 4 | 03/06/2024 | 03/06/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 6/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2024 | Connected |  | N
National Grid | LOWELL | 638291 | 01852 | 5.76 | Solar | 05_07_97W1 | 09/06/2024 | 10/28/2024 | 27 | 25 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 | 12/12/2024 | 03/05/2025 | 56 | 0 | 56 |  |  | 0 | 0 | 0 | 03/05/2025 | 56 | 0 | 56 |  |  | 0 | 0 | 0 | 9/16/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 587969 | 02324 | 325 | Natural Gas | 05_14_306 | 02/26/2024 | 08/01/2024 | 109 | 99 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2024 | 08/27/2024 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 662678 | 01906 | 7.6 | Solar | 05_07_797W1 | 01/02/2025 | 01/29/2025 | 10 | 6 | 4 | 01/30/2025 | 01/30/2025 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2025 | Connected |  | N
National Grid | NORTHAMPTON | 655704 | 01062 | 3.77 | Solar | 05_12_23W3 | 11/25/2024 | 12/23/2024 | 10 | 4 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | RANDOLPH | 605020 | 02368 | 5 | Solar | 05_09_909W2 | 04/18/2024 | 05/06/2024 | 2 | 0 | 2 | 05/07/2024 | 05/07/2024 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 639754 | 01852 | 5.76 | Solar | 05_07_97W1 | 09/12/2024 | 10/04/2024 | 1 | 0 | 1 | 10/07/2024 | 10/07/2024 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 673515 | 02324 | 200 | Solar | 05_14_315 | 02/24/2025 |  | 275 | 67 | 208 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | Y
National Grid | SAUGUS | 667190 | 01906 | 10 | Solar | 05_07_797W1 | 01/22/2025 | 01/28/2025 | 4 | 0 | 4 | 01/29/2025 | 01/29/2025 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2025 | 01/22/2025 | 3/26/2026 | Y | EXP | 365 | 05/21/2025 | 06/10/2025 | 21 | 0 | 21 |  |  | 7/22/2025 | Connected |  | N
National Grid | NORTHAMPTON | 649403 | 01060 | 9.57 | Solar | 05_12_24J1 | 10/24/2024 | 11/13/2024 | 12 | 9 | 3 | 11/14/2024 | 11/14/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 12/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2025 | Connected |  | N
National Grid | RANDOLPH | 643025 | 02368 | 6 | Solar | 05_09_909W2 | 09/26/2024 | 10/29/2024 | 3 | 0 | 3 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/26/2024 | 12/7/2025 | Y | EXP | 365 | 02/12/2025 | 02/11/2025 | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | LOWELL | 643312 | 01852 | 3.8 | Solar | 05_07_97W1 | 09/27/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 09/27/2024 | 12/24/2025 | Y | EXP | 365 | 04/03/2025 | 06/02/2025 | 61 | 0 | 61 |  |  | 6/19/2025 | Connected |  | N
National Grid | BRIDGEWATER | 204310 | 02333 | 2649 | Natural Gas | 05_14_319 | 01/14/2019 | 02/19/2019 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/20/2019 | 02/10/2020 | 245 | 221 | 24 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2020 | 01/14/2019 | 7/20/2022 | Y | STD | 575 | 04/23/2021 | 10/12/2021 | 62 | 0 | 62 |  |  | 5/3/2022 | Connected |  | N
National Grid | SAUGUS | 754701 | 01906 | 7.6 | Solar | 05_07_797W19 | 03/05/2026 | 03/11/2026 | 2 | 0 | 2 | 03/24/2026 | 03/24/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 177484 | 01060 | 19.7 | Solar | 04_04_101L2 | 09/22/2016 | 09/22/2016 | 1 | 1 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2016 | 09/22/2016 | 10/1/2017 | Y | EXP | 363 | 02/21/2017 | 03/16/2017 | 17 | 0 | 17 | 1/4/2017 | 1/4/2017 | 3/21/2017 | Connected |  | N
National Grid | RANDOLPH | 644471 | 02368 | 3.8 | Solar | 05_09_909W2 | 10/02/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 655942 | 01852 | 7.6 | Solar | 05_07_97W1 | 11/21/2024 | 12/16/2024 | 6 | 0 | 6 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | EAST BRIDGEWATER | 274261 | 02333 | 100 | Solar | HVDC Converter to Sandy Pond | 01/22/2020 | 02/10/2020 | 13 | 7 | 6 | 02/11/2020 | 02/11/2020 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2020 |  | 10/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2020 | Connected |  | N
National Grid | SAUGUS | 174196 | 01906 | 1500 | Solar | 05_07_797W19 | 03/20/2012 | 03/20/2012 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2013 |  | 11/1/2012 | N | STD | 111 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 265329 | 01060 | 15.2 | Solar | 04_04_101L2 | 11/15/2019 | 11/18/2019 | 0 | 0 | 0 | 11/19/2019 | 11/19/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2019 |  | 11/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2020 | Connected |  | N
National Grid | RANDOLPH | 645789 | 02368 | 5.76 | Solar | 05_09_909W2 | 10/08/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/08/2024 | 12/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | LOWELL | 657156 | 01852 | 7.6 | Solar | 05_07_97W1 | 11/26/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 11/26/2024 | 3/24/2026 | Y | EXP | 365 | 05/14/2025 | 11/07/2025 | 178 | 0 | 178 |  |  | 12/3/2025 | Connected |  | N
National Grid | BRIDGEWATER | 178439 | 02324 | 132 | Solar | 05_07_68J1 | 04/02/2018 | 04/02/2018 | 12 | 3 | 9 | 04/20/2018 | 04/20/2018 | 60 | 36 | 24 | 09/05/2018 | 10/17/2018 | 30 | 11 | 19 |  |  | 0 | 0 | 0 | 10/17/2018 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 4/8/2019 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 174480 | 01906 | 1500 | Solar | 05_07_797W19 | 04/19/2011 | 04/19/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2011 | 06/20/2011 | 30 | 0 | 30 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2012 | 04/19/2011 | 10/31/2012 | Y | STD | 282 | 05/27/2013 | 07/27/2013 | 42 | 0 | 42 | 7/26/2013 | 7/26/2013 | 8/15/2013 | Connected |  | N
National Grid | NORTHAMPTON | 278387 | 01060 | 15.2 | Solar | 04_04_101L2 | 02/26/2020 | 03/03/2020 | 3 | 0 | 3 | 03/04/2020 | 03/04/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2020 |  | 2/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | RANDOLPH | 664224 | 02368 | 7.6 | Solar | 05_09_909W2 | 01/07/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 | 01/07/2025 | 7/11/2026 | Y | EXP | 365 | 10/23/2025 | 10/30/2025 | 8 | 0 | 8 |  |  | 11/7/2025 | Connected |  | N
National Grid | LOWELL | 666717 | 01852 | 3.8 | Solar | 05_07_97W1 | 01/20/2025 | 02/10/2025 | 16 | 12 | 4 | 02/11/2025 | 02/11/2025 | 52 | 32 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | BRIDGEWATER | 177862 | 02324 | 4990 | Solar | 05_01_601W3 | 06/13/2017 | 06/21/2017 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/21/2017 | 07/19/2017 | 19 | 3 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2019 | 06/13/2017 | 6/12/2020 | Y | STD | 587 | 09/13/2019 | 11/14/2019 | 62 | 0 | 62 |  |  | 6/16/2020 | Connected |  | N
National Grid | SAUGUS | 174898 | 01906 | 1800 | Solar | 05_07_797W19 | 03/20/2012 | 03/20/2012 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2012 | 07/18/2012 | 65 | 0 | 65 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2013 |  | 12/3/2012 | N | STD | 79 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 282436 | 01062 | 15.2 | Solar | 04_04_101L2 | 03/05/2020 | 03/09/2020 | 1 | 1 | 0 | 03/10/2020 | 03/10/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2020 |  | 8/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2021 | Connected |  | N
National Grid | RANDOLPH | 672634 | 02368 | 7.6 | Solar | 05_09_909W2 | 02/18/2025 | 03/14/2025 | 5 | 0 | 5 | 03/17/2025 | 03/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 02/18/2025 | 4/15/2026 | Y | EXP | 365 | 08/07/2025 | 08/06/2025 | 0 | 0 | 0 |  |  | 8/8/2025 | Connected |  | N
National Grid | LOWELL | 670156 | 01852 | 7.6 | Solar | 05_07_97W1 | 02/05/2025 | 02/28/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | BRIDGEWATER | 195202 | 02324 | 2310 | Solar | 05_01_601W3 | 09/28/2018 | 10/22/2018 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 | 12/18/2018 | 38 | 19 | 19 |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 176793 | 01930 | 11.4 | Solar | 05_07_797W19 | 02/24/2016 | 02/24/2016 | 5 | 5 | 0 | 03/03/2016 | 03/03/2016 | 238 | 0 | 238 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2016 |  | 3/1/2017 | N | EXP | 317 |  |  | 0 | 0 | 0 | 4/18/2016 | 4/18/2016 |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 284042 | 01062 | 2850 | Solar | 04_04_101L2 | 08/04/2020 | 08/14/2020 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2020 | 10/06/2020 | 35 | 18 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 08/04/2020 | 6/4/2025 | Y | STD | 572 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 680727 | 02368 | 10 | Solar | 05_09_909W2 | 03/26/2025 | 04/22/2025 | 2 | 0 | 2 | 05/23/2025 | 05/23/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 | 03/26/2025 | 7/1/2026 | Y | EXP | 365 | 07/31/2025 | 07/30/2025 | 0 | 0 | 0 |  |  | 9/20/2025 | Connected |  | N
National Grid | LOWELL | 684485 | 01851 | 7.6 | Solar | 05_07_97W1 | 04/11/2025 | 04/25/2025 | 9 | 6 | 3 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 314893 | 02379 | 25 | Solar | 05_01_601W3 | 09/25/2020 | 09/29/2020 | 1 | 0 | 1 | 09/30/2020 | 09/30/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 09/25/2020 | 2/28/2023 | Y | EXP | 455 | 09/10/2021 | 09/09/2021 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 177635 | 02554 | 8 | Solar | 05_07_797W19 | 07/19/2017 | 07/19/2017 | 23 | 18 | 5 | 08/22/2017 | 08/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 | 07/19/2017 | 7/25/2018 | Y | EXP | 331 | 12/20/2017 | 12/30/2017 | 7 | 0 | 7 | 2/27/2018 | 2/27/2018 | 3/6/2018 | Connected |  | N
National Grid | NORTHAMPTON | 349242 | 01060 | 19.72 | Solar | 04_04_101L2 | 03/26/2021 | 04/16/2021 | 14 | 14 | 0 | 04/20/2021 | 04/20/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2021 | Connected |  | N
National Grid | RANDOLPH | 418955 | 02368 | 3900 | Solar | 05_09_909W3 | 04/14/2022 | 06/02/2022 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/03/2022 | 07/01/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 04/14/2022 | 5/19/2027 | Y | STD | 609 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | AYER | 684712 | 01432 | 11.5 | Solar | 05_07_97W1 | 04/18/2025 | 05/06/2025 | 15 | 10 | 5 | 05/07/2025 | 05/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 399116 | 02379 | 234.6 | Solar | 05_05_3431W2 | 12/07/2021 | 02/26/2022 | 56 | 50 | 6 |  |  | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 | 12/07/2021 | 9/12/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NANTUCKET | 178556 | 02554 | 133.2 | Solar | 05_07_797W19 | 03/12/2018 | 03/12/2018 | 1 | 0 | 1 | 03/30/2018 | 03/30/2018 | 4 | 0 | 4 | 04/06/2018 | 05/16/2018 | 28 | 8 | 20 |  |  | 0 | 0 | 0 | 05/16/2018 | 28 | 8 | 20 |  |  | 0 | 0 | 0 | 5/30/2018 | 03/12/2018 | 1/10/2022 | Y | EXP | 611 | 02/12/2021 | 12/17/2021 | 309 | 6 | 303 |  |  | 12/30/2021 | Connected |  | N
National Grid | NORTHAMPTON | 362967 | 01060 | 19.99 | Solar | 04_04_101L2 | 06/10/2021 | 07/01/2021 | 16 | 13 | 3 | 07/02/2021 | 07/02/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2021 |  | 8/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2021 | Connected |  | N
National Grid | RANDOLPH | 735135 | 02368 | 0 | Solar | 05_09_909W3 | 11/29/2025 | 12/02/2025 | 2 | 0 | 2 | 12/03/2025 | 12/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 1/21/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AVON | 727914 | 02322 | 13.36 | Solar | 05_07_97W2 | 10/21/2025 | 10/25/2025 | 18 | 18 | 0 | 01/22/2026 | 01/22/2026 | 49 | 37 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BRIDGEWATER | 531270 | 02379 | 380 | Solar | 05_05_3431W2 | 07/20/2023 | 08/04/2023 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2023 | 09/05/2023 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 | 07/20/2023 | 7/20/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | NANTUCKET | 191685 | 02554 | 136 | Solar | 05_07_797W19 | 12/05/2018 | 12/12/2018 | 4 | 0 | 4 | 12/13/2018 | 12/13/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 404153 | 01060 | 28.71 | Solar | 04_04_101L2 | 03/11/2022 | 03/14/2022 | 1 | 0 | 1 | 03/15/2022 | 03/15/2022 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2022 |  | 4/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/5/2022 | Connected |  | N
National Grid | RANDOLPH | 174696 | 02368 | 2266 | Solar | 05_09_909W3 | 12/26/2012 | 12/26/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/09/2013 | 03/20/2013 | 40 | 0 | 40 |  | 0 | 0 | 0 | 10/06/2014 | 10/06/2014 | 0 | 0 | 0 | 8/22/2013 | 12/26/2012 | 12/31/2016 | Y | STD | 1227 | 11/26/2014 | 02/12/2016 | 300 | 0 | 300 | 2/26/2016 | 2/26/2016 | 2/26/2016 | Connected |  | N
National Grid | WESTMINSTER | 727611 | 01473 | 15.2 | Solar | 05_07_97W2 | 10/20/2025 | 10/24/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEST BRIDGEWATER | 750606 | 02379 | 0 | Battery Add-On | 05_05_3431W2 | 02/11/2026 | 02/20/2026 | 6 | 4 | 2 | 02/23/2026 | 02/23/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NANTUCKET | 223130 | 02554 | 133.2 | Solar | 05_07_797W19 | 04/27/2019 | 05/21/2019 | 16 | 13 | 3 | 05/22/2019 | 05/22/2019 | 26 | 16 | 10 | 07/26/2019 | 09/04/2020 | 61 | 58 | 3 |  |  | 0 | 0 | 0 | 09/04/2020 | 61 | 58 | 3 |  |  | 0 | 0 | 0 | 9/28/2020 |  | 1/3/2023 | N | EXP | 365 | 02/25/2021 | 12/08/2021 | 286 | 67 | 219 |  |  | 3/7/2022 | Connected |  | N
National Grid | NORTHAMPTON | 411210 | 01060 | 20 | Solar | 04_04_101L2 | 02/10/2022 | 02/11/2022 | 1 | 0 | 1 | 02/14/2022 | 02/14/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 3/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2022 | Connected |  | N
National Grid | RANDOLPH | 174741 | 02368 | 3000 | Solar | 05_09_909W3 | 01/16/2013 | 01/16/2013 | 37 | 31 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 743754 | 01473 | 5.76 | Solar | 05_07_97W2 | 01/06/2026 | 01/07/2026 | 3 | 0 | 3 | 02/27/2026 | 02/27/2026 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BRIDGEWATER | 178801 | 02379 | 275 | Solar | 05_05_3431W2 | 02/27/2018 | 02/27/2018 | 10 | 10 | 0 | 03/29/2018 | 03/29/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2018 |  | 3/5/2019 | N | EXP | 337 |  |  | 0 | 0 | 0 |  |  | 10/12/2018 | Connected |  | N
National Grid | NANTUCKET | 234850 | 02554 | 7.6 | Solar | 05_07_797W19 | 04/29/2020 | 06/09/2020 | 27 | 26 | 1 | 06/10/2020 | 06/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 6/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 422444 | 01060 | 49.68 | Solar | 04_04_101L2 | 04/14/2022 | 09/09/2022 | 101 | 91 | 10 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2023 | 04/14/2022 | 1/11/2024 | Y | STD | 280 | 07/21/2023 | 09/21/2023 | 63 | 0 | 63 |  |  | 11/17/2023 | Connected |  | N
National Grid | RANDOLPH | 174919 | 02368 | 3000 | Solar | 05_09_909W3 | 02/26/2013 | 02/26/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2013 | 04/08/2013 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/29/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 743893 | 01440 | 11.5 | Solar | 05_07_97W2 | 01/07/2026 | 01/12/2026 | 3 | 0 | 3 | 01/13/2026 | 01/13/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEST BRIDGEWATER | 178789 | 02379 | 1775 | Solar | 05_05_3431W2 | 03/04/2016 | 03/04/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2016 | 04/21/2016 | 31 | 17 | 14 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/9/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 245587 | 02554 | 7.6 | Solar | 05_07_797W19 | 07/31/2019 | 08/07/2019 | 4 | 4 | 0 | 08/08/2019 | 08/08/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 | 07/31/2019 | 12/31/2020 | Y | EXP | 365 | 09/02/2020 | 09/18/2020 | 16 | 0 | 16 |  |  | 10/17/2020 | Connected |  | N
National Grid | WILLIAMSBURG | 436989 | 01039 | 17.6 | Solar | 04_04_101L2 | 06/28/2022 | 07/05/2022 | 5 | 3 | 2 | 07/06/2022 | 07/06/2022 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2022 |  | 8/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2022 | Connected |  | N
National Grid | RANDOLPH | 174914 | 02368 | 21 | Solar | 05_09_909W3 | 09/19/2012 | 09/19/2012 | 7 | 0 | 7 | 10/01/2012 | 10/01/2012 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/14/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 745164 | 02035 | 11.4 | Solar | 05_07_97W2 | 01/13/2026 | 01/15/2026 | 2 | 0 | 2 | 02/04/2026 | 02/04/2026 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROCKTON | 184044 | 02301 | 292 | Natural Gas | 05_05_3431W2 | 06/07/2018 | 06/07/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2018 | 08/13/2018 | 37 | 29 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 |  | 3/31/2020 | N | STD | 291 |  |  | 0 | 0 | 0 | 3/31/2020 | 3/30/2020 | 3/30/2020 | Connected |  | N
National Grid | NANTUCKET | 246245 | 02554 | 100 | Solar | 05_07_797W19 | 07/31/2019 | 08/07/2019 | 4 | 1 | 3 | 08/08/2019 | 08/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 |  | 9/23/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 472903 | 01039 | 20 | Solar | 04_04_101L2 | 11/02/2022 | 11/08/2022 | 5 | 4 | 1 | 11/09/2022 | 11/09/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2022 |  | 12/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N
National Grid | RANDOLPH | 175023 | 02368 | 21 | Solar | 05_09_909W3 | 09/19/2012 | 09/19/2012 | 7 | 0 | 7 | 10/01/2012 | 10/01/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2012 | 09/19/2012 | 12/14/2012 | Y | EXP | 65 |  |  | 0 | 0 | 0 | 10/12/2012 | 10/12/2012 | 3/21/2013 | Connected |  | N
National Grid | FOXBOROUGH | 751626 | 02035 | 3.8 | Solar | 05_07_97W2 | 02/17/2026 | 02/23/2026 | 3 | 0 | 3 | 03/04/2026 | 03/04/2026 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 491954 | 02301 | 6.96 | Solar | 05_05_3431W2 | 02/07/2023 | 02/08/2023 | 1 | 0 | 1 | 02/09/2023 | 02/09/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 |  | 12/15/2024 | N | EXP | 465 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | NANTUCKET | 254306 | 02554 | 0 | Solar | 05_07_797W19 | 09/17/2019 | 09/17/2019 | 0 | 0 | 0 | 09/18/2019 | 09/18/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 | 09/17/2019 | 6/22/2020 | Y | EXP | 365 | 12/19/2019 | 01/14/2020 | 26 | 0 | 26 |  |  | 4/3/2020 | Connected |  | N
National Grid | WILLIAMSBURG | 531486 | 01096 | 5.584 | Solar | 04_04_101L2 | 06/26/2023 | 08/28/2023 | 44 | 44 | 0 | 08/29/2023 | 08/29/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 10/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | RANDOLPH | 175173 | 02368 | 19 | Solar | 05_09_909W3 | 11/20/2012 | 11/20/2012 | 7 | 0 | 7 | 12/05/2012 | 12/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2013 |  | 2/28/2013 | N | EXP | 16 |  |  | 0 | 0 | 0 | 2/12/2013 | 2/12/2013 | 7/24/2013 | Connected |  | N
National Grid | FOXBOROUGH | 753611 | 02035 | 3.8 | Solar | 05_07_97W2 | 02/27/2026 | 03/04/2026 | 1 | 0 | 1 | 03/16/2026 | 03/16/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 529749 | 02301 | 6 | Solar | 05_05_3431W2 | 09/06/2023 | 06/04/2023 | 1 | 0 | 1 | 09/08/2023 | 09/08/2023 | 85 | 63 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2023 |  | 1/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | NANTUCKET | 290955 | 02554 | 57.6 | Solar | 05_07_797W19 | 08/03/2020 | 08/13/2020 | 7 | 3 | 4 | 08/14/2020 | 08/14/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 3/7/2022 | N | EXP | 545 |  |  | 0 | 0 | 0 |  |  | 3/4/2022 | Connected |  | N
National Grid | GOSHEN | 606670 | 01032 | 20 | Solar | 04_04_101L2 | 04/29/2024 | 05/01/2024 | 3 | 1 | 2 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 5/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2024 | Connected |  | N
National Grid | RANDOLPH | 175546 | 02368 | 852 | Solar | 05_09_909W3 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 | 6/10/2015 | 12/05/2014 | 12/31/2016 | Y | STD | 570 |  |  | 0 | 0 | 0 | 7/6/2017 | 7/6/2017 | 7/6/2017 | Connected |  | N
National Grid | FOXBOROUGH | 175563 | 02035 | 14.8 | Solar | 05_07_97W2 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2014 | 07/31/2014 | 10/31/2014 | Y | EXP | 59 | 10/07/2015 | 10/13/2015 | 3 | 0 | 3 | 10/26/2015 | 10/26/2015 | 10/26/2015 | Connected |  | N
National Grid | BROCKTON | 637086 | 02301 | 7.6 | Solar | 05_05_3431W2 | 09/02/2024 | 09/18/2024 | 3 | 0 | 3 | 09/19/2024 | 09/19/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2024 |  | 10/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2025 | Connected |  | Y
National Grid | NANTUCKET | 345964 | 02554 | 500 | Solar | 05_07_797W19 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 |  |  | 174 | 126 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GOSHEN | 659599 | 01032 | 12.5 | Solar | 04_04_101L2 | 12/11/2024 | 12/30/2024 | 13 | 10 | 3 | 12/31/2024 | 12/31/2024 | 67 | 45 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | RANDOLPH | 175545 | 02368 | 990 | Solar | 05_09_909W3 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  | 0 | 0 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 | 6/10/2015 | 12/05/2014 | 12/31/2016 | Y | STD | 570 |  |  | 0 | 0 | 0 | 7/6/2017 | 7/6/2017 | 7/6/2017 | Connected |  | N
National Grid | FOXBOROUGH | 175584 | 02035 | 17 | Solar | 05_07_97W2 | 04/18/2014 | 04/18/2014 | 6 | 0 | 6 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2014 |  | 6/30/2014 | N | EXP | 60 |  |  | 0 | 0 | 0 | 6/23/2014 | 6/23/2014 | 7/10/2014 | Connected |  | N
National Grid | WEST BRIDGEWATER | 662546 | 02379 | 3.8 | Solar | 05_05_3431W2 | 12/24/2024 | 01/13/2025 | 4 | 0 | 4 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | NANTUCKET | 389732 | 02554 | 0 | Other | 05_07_797W19 | 11/10/2021 | 01/26/2022 | 51 | 42 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2022 | 02/02/2022 | 5 | 0 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 690788 | 01053 | 17.6 | Solar | 04_04_101L2 | 05/10/2025 | 05/19/2025 | 6 | 2 | 4 | 05/20/2025 | 05/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | RANDOLPH | 175567 | 02368 | 5.5 | Solar | 05_09_909W3 | 10/08/2014 | 10/08/2014 | 6 | 0 | 6 | 10/20/2014 | 10/20/2014 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/2/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 175767 | 02035 | 5000 | Solar | 05_07_97W2 | 06/12/2014 | 06/12/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/17/2014 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 722327 | 02301 | 15.36 | Solar | 05_05_3431W2 | 09/26/2025 |  | 32 | 28 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 412220 | 02554 | 0 | Battery Add-On | 05_07_797W19 | 03/04/2022 | 04/28/2022 | 38 | 29 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2022 | 05/25/2022 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 713236 | 01053 | 18.24 | Solar | 04_04_101L2 | 08/19/2025 | 09/10/2025 | 13 | 8 | 5 | 09/11/2025 | 09/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | RANDOLPH | 175781 | 02368 | 16 | Solar | 05_09_909W3 | 07/22/2015 | 07/22/2015 | 4 | 4 | 0 | 07/28/2015 | 07/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2015 |  | 3/18/2016 | N | EXP | 218 |  |  | 0 | 0 | 0 | 3/11/2016 | 3/11/2016 | 3/23/2016 | Connected |  | N
National Grid | FOXBOROUGH | 175765 | 02035 | 16.01 | Solar | 05_07_97W2 | 06/06/2014 | 06/06/2014 | 5 | 2 | 3 | 06/16/2014 | 06/16/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2014 |  | 8/29/2014 | N | EXP | 49 |  |  | 0 | 0 | 0 | 7/11/2014 | 7/11/2014 | 8/15/2014 | Connected |  | N
National Grid | WEST BRIDGEWATER | 174515 | 02379 | 1000 | Solar | 05_09_524L1 | 07/20/2012 | 07/20/2012 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2012 | 08/23/2012 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/28/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 443983 | 02554 | 0 | Other | 05_07_797W19 | 11/09/2022 |  | 121 | 113 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 744341 | 01096 | 20 | Solar | 04_04_101L3 | 01/13/2026 | 01/15/2026 | 2 | 0 | 2 | 01/16/2026 | 01/16/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 177781 | 02368 | 8.8 | Solar | 05_09_909W3 | 06/01/2017 | 06/01/2017 | 4 | 4 | 0 | 06/07/2017 | 06/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2017 | 06/01/2017 | 6/6/2018 | Y | EXP | 363 | 08/24/2017 | 08/28/2017 | 2 | 0 | 2 | 9/1/2017 | 9/1/2017 | 9/1/2017 | Connected |  | N
National Grid | FOXBOROUGH | 176090 | 02035 | 7.6 | Solar | 05_07_97W2 | 02/02/2015 | 02/02/2015 | 5 | 1 | 4 | 02/10/2015 | 02/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 | 02/02/2015 | 6/30/2015 | Y | EXP | 125 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 | 4/20/2015 | 4/20/2015 | 11/9/2015 | Connected |  | N
National Grid | BROCKTON | 174514 | 02301 | 2000 | Solar | 05_09_524L1 | 07/20/2012 | 07/20/2012 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2012 | 08/23/2012 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/28/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 443981 | 02554 | 0 | Other | 05_07_797W19 | 11/09/2022 | 01/31/2023 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2023 | 03/02/2023 | 22 | 2 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GOSHEN | 745617 | 01032 | 25 | Solar | 04_04_101L3 | 02/03/2026 | 02/04/2026 | 1 | 0 | 1 | 02/05/2026 | 02/05/2026 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2026 |  | 3/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 177869 | 02368 | 176 | Solar | 05_09_909W3 | 08/09/2017 | 08/09/2017 | 15 | 15 | 0 | 08/24/2017 | 08/24/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2017 |  | 8/15/2018 | N | EXP | 348 |  |  | 0 | 0 | 0 | 3/2/2018 | 3/2/2018 | 3/2/2018 | Connected |  | N
National Grid | FOXBOROUGH | 176247 | 02035 | 3780 | Solar | 05_07_97W2 | 05/01/2015 | 05/01/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175022 | 02301 | 2000 | Solar | 05_09_524L1 | 10/08/2012 | 10/08/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2012 | 11/24/2012 | 9 | 0 | 9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 479635 | 02554 | 8.064 | Solar | 05_07_797W19 | 03/07/2023 | 03/07/2023 | 0 | 0 | 0 | 03/08/2023 | 03/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSBURG | 568300 | 01096 | 15.95 | Solar | 04_04_101L3 | 11/02/2023 | 11/09/2023 | 5 | 3 | 2 | 11/13/2023 | 11/13/2023 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 1/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | N
National Grid | RANDOLPH | 177939 | 02368 | 4536 | Solar | 05_09_909W3 | 06/22/2017 | 06/22/2017 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2017 | 07/19/2017 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 176316 | 02035 | 3780 | Solar | 05_07_97W2 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/12/2015 | 06/09/2015 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2016 | 05/08/2015 | 11/9/2017 | Y | STD | 647 | 06/28/2017 | 10/24/2017 | 81 | 0 | 81 | 10/25/2017 | 10/25/2017 | 11/7/2017 | Connected |  | N
National Grid | BROCKTON | 175146 | 02301 | 3500 | Solar | 05_09_524L1 | 04/29/2013 | 04/29/2013 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2013 | 08/11/2014 | 310 | 0 | 310 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2014 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 494818 | 02554 | 19 | Solar | 05_07_797W19 | 01/25/2023 | 01/31/2023 | 5 | 3 | 2 | 02/01/2023 | 02/01/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2023 |  | 3/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSBURG | 176375 | 01039 | 284 | Solar | 04_04_101L4 | 05/06/2016 | 05/06/2016 | 1 | 1 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2016 |  | 5/14/2017 | N | EXP | 305 |  |  | 0 | 0 | 0 | 9/15/2016 | 9/15/2016 | 12/29/2016 | Connected |  | N
National Grid | RANDOLPH | 178010 | 02368 | 1000 | Solar | 05_09_909W3 | 04/28/2017 | 04/28/2017 | 15 | 11 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2017 | 06/07/2017 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/6/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 176580 | 02035 | 3.8 | Solar | 05_07_97W2 | 04/05/2016 | 04/05/2016 | 1 | 1 | 0 | 04/07/2016 | 04/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/05/2016 | 4/11/2017 | Y | EXP | 350 | 09/15/2016 | 10/18/2016 | 22 | 0 | 22 | 8/11/2016 | 8/11/2016 | 12/2/2016 | Connected |  | N
National Grid | WEST BRIDGEWATER | 175138 | 02379 | 1000 | Solar | 05_09_524L1 | 11/12/2012 | 11/12/2012 | 14 | 9 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2012 | 01/16/2013 | 25 | 0 | 25 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 534311 | 02554 | 10 | Solar | 05_07_797W19 | 07/11/2023 | 07/12/2023 | 1 | 0 | 1 | 07/13/2023 | 07/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 9/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSBURG | 176861 | 01096 | 27 | Solar | 04_04_101L4 | 01/20/2016 | 01/20/2016 | 1 | 1 | 0 | 01/22/2016 | 01/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2016 |  | 1/26/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 | 5/18/2016 | 5/18/2016 | 6/13/2016 | Connected |  | N
National Grid | RANDOLPH | 178009 | 02368 | 3995 | Solar | 05_09_909W3 | 04/28/2017 | 04/28/2017 | 15 | 11 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2017 | 06/07/2017 | 11 | 0 | 11 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2017 | 04/28/2017 | 6/10/2019 | Y | STD | 0 |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | HAMPDEN | 176914 | 01036 | 11.4 | Solar | 05_07_97W2 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 | 05/04/2016 | 5/10/2017 | Y | EXP | 348 | 11/07/2016 | 11/26/2016 | 13 | 0 | 13 | 12/5/2016 | 12/5/2016 | 12/5/2016 | Connected |  | N
National Grid | WEST BRIDGEWATER | 174121 | 02379 | 2000 | Solar | 05_14_43L7 | 03/29/2012 | 03/29/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/29/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 546935 | 02554 | 0 | Other | 05_07_797W19 | 03/21/2024 | 06/12/2024 | 57 | 47 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2024 | 07/11/2024 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 467030 | 01096 | 7.6 | Solar | 04_04_101L4 | 10/20/2022 | 11/10/2022 | 16 | 15 | 1 | 11/14/2022 | 11/14/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2022 |  | 5/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/11/2024 | Connected |  | N
National Grid | RANDOLPH | 178190 | 02368 | 1600 | Solar | 05_09_909W3 | 01/02/2018 | 02/02/2018 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2018 | 03/13/2018 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 | 01/02/2018 | 3/11/2020 | Y | STD | 484 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 177471 | 01036 | 3.8 | Solar | 05_07_97W2 | 03/02/2017 | 03/02/2017 | 10 | 9 | 1 | 03/17/2017 | 03/17/2017 | 258 | 0 | 258 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 |  | 3/8/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 174120 | 02379 | 2000 | Solar | 05_14_43L7 | 03/29/2012 | 03/29/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/29/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 564779 | 02554 | 6 | Solar | 05_07_797W19 | 11/01/2023 | 11/06/2023 | 3 | 0 | 3 | 11/07/2023 | 11/07/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  | 12/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2024 | Connected |  | N
National Grid | NORTHAMPTON | 618888 | 01053 | 50 | Solar | 04_04_101L4 | 06/19/2024 | 07/31/2024 | 29 | 22 | 7 | 08/01/2024 | 08/01/2024 | 16 | 0 | 16 | 09/17/2024 | 10/22/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 10/22/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 1/24/2025 | 06/19/2024 | 2/3/2026 | Y | EXP | 280 | 12/17/2025 | 12/16/2025 | 0 | 0 | 0 |  |  | 2/3/2026 | Connected |  | N
National Grid | RANDOLPH | 178376 | 02368 | 4950 | Solar | 05_09_909W3 | 11/21/2017 | 12/20/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2017 | 01/22/2018 | 21 | 0 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 | 11/21/2017 | 9/29/2022 | Y | STD | 171 | 01/27/2021 | 09/22/2022 | 604 | 156 | 448 |  |  | 9/29/2022 | Connected |  | N
National Grid | HAMPDEN | 177961 | 01036 | 8.96 | Solar | 05_07_97W2 | 10/24/2017 | 10/24/2017 | 12 | 11 | 1 | 11/21/2017 | 11/21/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 10/31/2018 | N | EXP | 338 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | BROCKTON | 175384 | 02301 | 52 | Solar | 05_14_43L7 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2014 |  | 11/28/2014 | N | EXP | 120 |  |  | 0 | 0 | 0 | 8/7/2014 | 8/7/2014 | 1/15/2015 | Connected |  | N
National Grid | NANTUCKET | 561847 | 02554 | 7.6 | Solar | 05_07_797W19 | 10/24/2023 | 10/27/2023 | 3 | 1 | 2 | 10/30/2023 | 10/30/2023 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2023 |  | 12/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2024 | Connected |  | N
National Grid | WILLIAMSBURG | 650916 | 01096 | 50 | Solar | 04_04_101L4 | 11/01/2024 | 01/07/2025 | 43 | 33 | 10 | 01/08/2025 | 01/08/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2025 | Connected |  | N
National Grid | RANDOLPH | 178364 | 02368 | 7.6 | Solar | 05_09_909W3 | 03/30/2018 | 03/30/2018 | 5 | 0 | 5 | 04/09/2018 | 04/09/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2018 |  | 11/15/2019 | N | EXP | 568 |  |  | 0 | 0 | 0 |  |  | 10/8/2019 | Connected |  | N
National Grid | HAMPDEN | 187799 | 01036 | 15.2 | Solar | 05_07_97W2 | 06/12/2018 | 06/12/2018 | 12 | 0 | 12 | 06/22/2018 | 06/22/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 177537 | 02301 | 300 | Solar | 05_14_43L7 | 09/14/2017 | 09/14/2017 | 18 | 18 | 0 | 10/11/2017 | 10/11/2017 | 0 | 0 | 0 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2018 |  | 9/19/2018 | N | EXP | 226 |  |  | 0 | 0 | 0 |  |  | 5/11/2018 | Connected |  | N
National Grid | NANTUCKET | 625688 | 02554 | 3.8 | Solar | 05_07_797W19 | 07/17/2024 | 07/29/2024 | 0 | 0 | 0 | 07/30/2024 | 07/30/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2024 | Connected |  | N
National Grid | GOSHEN | 680837 | 01032 | 4.8 | Solar | 04_04_101L4 | 04/14/2025 | 05/28/2025 | 30 | 27 | 3 | 05/29/2025 | 05/29/2025 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2025 | Connected |  | N
National Grid | RANDOLPH | 187389 | 02368 | 72 | Solar | 05_09_909W3 | 06/07/2018 | 06/07/2018 | 14 | 4 | 10 | 06/28/2018 | 06/28/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2018 |  | 8/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2019 | Connected |  | N
National Grid | HAMPDEN | 194982 | 01036 | 7.6 | Solar | 05_07_97W2 | 09/04/2018 | 10/08/2018 | 17 | 17 | 0 | 10/09/2018 | 10/09/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 | 09/04/2018 | 5/21/2019 | Y | EXP | 222 | 11/09/2018 | 02/27/2019 | 110 | 0 | 110 |  |  | 4/18/2019 | Connected |  | N
National Grid | BROCKTON | 327460 | 02301 | 10 | Solar | 05_14_43L7 | 12/09/2020 | 12/17/2020 | 5 | 3 | 2 | 12/18/2020 | 12/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2021 | 12/09/2020 |  | Y | EXP | 365 | 04/14/2021 | 04/26/2021 | 12 | 0 | 12 |  |  | 5/7/2021 | Connected |  | N
National Grid | NANTUCKET | 640558 | 02554 | 7.22 | Solar | 05_07_797W19 | 09/16/2024 | 10/04/2024 | 4 | 1 | 3 | 10/07/2024 | 10/07/2024 | 59 | 38 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2025 | Connected |  | N
National Grid | GOSHEN | 177037 | 01032 | 396 | Solar | 04_04_101L5 | 07/26/2016 | 07/26/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/10/2016 | 48 | 23 | 25 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2017 | 07/26/2016 | 8/1/2017 | Y | STD | 188 | 05/12/2017 | 06/29/2017 | 33 | 0 | 33 | 6/27/2017 | 6/27/2017 | 7/5/2017 | Connected |  | N
National Grid | RANDOLPH | 189354 | 02368 | 10 | Solar | 05_09_909W3 | 06/29/2018 | 06/29/2018 | 15 | 0 | 15 | 08/23/2018 | 08/23/2018 | 81 | 21 | 60 | 11/19/2018 | 01/18/2019 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 01/18/2019 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 12/19/2018 |  | 12/18/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2019 | Connected |  | Y
National Grid | HAVERHILL | 192557 | 01830 | 15.2 | Solar | 05_07_97W2 | 08/02/2018 | 08/15/2018 | 7 | 0 | 7 | 08/16/2018 | 08/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 367917 | 02379 | 900 | Solar | 05_14_43L7 | 09/08/2021 | 10/06/2021 | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2021 | 12/14/2021 | 46 | 21 | 25 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2022 | 09/08/2021 | 7/8/2024 | Y | STD | 308 | 07/12/2023 | 04/10/2024 | 272 | 184 | 88 |  |  | 9/5/2024 | Connected |  | N
National Grid | NANTUCKET | 642255 | 02554 | 5.76 | Solar | 05_07_797W19 | 09/23/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/23/2024 | 12/3/2025 | Y | EXP | 365 | 02/26/2025 | 05/16/2025 | 80 | 0 | 80 |  |  | 6/5/2025 | Connected |  | N
National Grid | WILLIAMSBURG | 177131 | 01039 |  |  | 04_04_101L5 | 07/26/2016 | 07/26/2016 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 190337 | 02368 | 3800 | Solar | 05_09_909W3 | 08/16/2018 | 08/27/2018 | 3 | 0 | 3 |  |  | 8 | 8 | 0 |  |  | 0 | 0 | 0 | 08/29/2018 | 09/07/2018 | 7 | 7 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 201002 | 01830 | 15.2 | Solar | 05_07_97W2 | 11/12/2018 | 11/16/2018 | 2 | 0 | 2 | 11/19/2018 | 11/19/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2019 | 11/12/2018 | 7/22/2020 | Y | EXP | 365 | 01/30/2020 | 02/20/2020 | 21 | 0 | 21 |  |  | 7/14/2020 | Connected |  | N
National Grid | BROCKTON | 422534 | 02301 | 3.8 | Solar | 05_14_43L7 | 04/07/2022 | 04/08/2022 | 1 | 0 | 1 | 04/11/2022 | 04/11/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2022 |  | 4/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2022 | Connected |  | N
National Grid | NANTUCKET | 656078 | 02554 | 4.55 | Solar | 05_07_797W19 | 11/21/2024 | 12/09/2024 | 5 | 0 | 5 | 12/10/2024 | 12/10/2024 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | WILLIAMSBURG | 178585 | 01096 | 1000 | Solar | 04_04_101L5 | 01/31/2018 | 01/31/2018 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/08/2018 | 03/12/2018 | 3 | 3 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 | 01/31/2018 | 12/20/2019 | Y | STD | 387 | 05/22/2019 | 12/03/2019 | 195 | 0 | 195 |  |  | 12/13/2019 | Connected |  | N
National Grid | RANDOLPH | 194600 | 02368 | 4950 | Solar | 05_09_909W3 | 10/11/2018 | 11/01/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/02/2018 | 01/18/2019 | 50 | 32 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 223131 | 01845 | 199.8 | Solar | 05_07_97W2 | 04/27/2019 | 05/21/2019 | 16 | 11 | 5 | 05/22/2019 | 05/22/2019 | 13 | 3 | 10 | 07/19/2019 | 07/30/2020 | 260 | 151 | 109 |  |  | 0 | 0 | 0 | 07/30/2020 | 260 | 151 | 109 |  |  | 0 | 0 | 0 | 9/4/2020 | 04/27/2019 | 10/11/2022 | Y | EXP | 245 | 05/11/2021 | 01/04/2022 | 239 | 226 | 13 |  |  | 9/15/2022 | Connected |  | N
National Grid | BROCKTON | 532991 | 02301 | 0 | Solar | 05_14_43L7 | 06/12/2023 | 06/13/2023 | 1 | 0 | 1 | 06/14/2023 | 06/14/2023 | 30 | 10 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  | 8/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | NANTUCKET | 673546 | 02554 | 3.8 | Solar | 05_07_797W19 | 03/07/2025 | 03/12/2025 | 3 | 0 | 3 | 03/13/2025 | 03/13/2025 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSBURG | 203329 | 01039 | 10 | Solar | 04_04_101L5 | 01/04/2019 | 01/15/2019 | 6 | 0 | 6 | 01/16/2019 | 01/16/2019 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 194591 | 02368 | 4000 | Solar | 05_09_909W3 | 10/09/2018 | 10/17/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2018 | 12/01/2018 | 29 | 10 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 228709 | 01845 | 7.6 | Solar | 05_07_97W2 | 07/24/2019 | 07/30/2019 | 3 | 0 | 3 | 07/31/2019 | 07/31/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 565734 | 02379 | 14.3 | Solar | 05_14_43L7 | 11/01/2023 | 11/17/2023 | 11 | 8 | 3 | 11/20/2023 | 11/20/2023 | 52 | 38 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  | 2/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2024 | Connected |  | N
National Grid | NANTUCKET | 692435 | 02554 | 3.8 | Solar | 05_07_797W19 | 05/23/2025 | 06/27/2025 | 2 | 0 | 2 | 06/30/2025 | 06/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 560671 | 01053 | 20.88 | Solar | 04_04_101L5 | 10/04/2023 | 10/12/2023 | 6 | 4 | 2 | 10/13/2023 | 10/13/2023 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2023 |  | 11/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2024 | Connected |  | N
National Grid | RANDOLPH | 198406 | 02368 | 3400 | Solar | 05_09_909W3 | 11/19/2018 | 12/03/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2018 | 10/08/2019 | 191 | 25 | 166 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 230807 | 01921 | 13.6 | Solar | 05_07_97W2 | 06/26/2019 | 07/05/2019 | 5 | 5 | 0 | 07/08/2019 | 07/08/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2019 | 06/26/2019 | 6/1/2020 | Y | EXP | 365 | 01/24/2020 | 02/05/2020 | 12 | 0 | 12 |  |  | 2/6/2020 | Connected |  | N
National Grid | BROCKTON | 567193 | 02301 | 0 | Battery Add-On | 05_14_43L7 | 11/02/2023 | 11/15/2023 | 8 | 5 | 3 | 11/16/2023 | 11/16/2023 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2024 | Connected |  | N
National Grid | NANTUCKET | 521068 | 02554 | 495.7 | Solar | 05_07_797W20 | 11/02/2023 | 01/19/2024 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2024 | 02/15/2024 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WILLIAMSBURG | 585339 | 01039 | 7.6 | Solar | 04_04_101L5 | 02/06/2024 | 02/09/2024 | 3 | 0 | 3 | 02/12/2024 | 02/12/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 3/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | RANDOLPH | 198758 | 02368 | 3500 | Solar | 05_09_909W3 | 11/26/2018 | 11/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2018 | 02/07/2019 | 52 | 31 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 265635 | 01845 | 4.55 | Solar | 05_07_97W2 | 11/21/2019 |  | 83 | 80 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 650475 | 02379 | 5.76 | Solar | 05_14_43L7 | 10/31/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2025 | Connected |  | N
National Grid | NANTUCKET | 581189 | 02554 | 240 | Solar | 05_07_797W20 | 01/09/2024 | 01/16/2024 | 4 | 0 | 4 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y
National Grid | NORTHAMPTON | 744620 | 01053 | 20 | Solar | 04_04_101L6 | 01/13/2026 | 01/29/2026 | 2 | 0 | 2 | 01/30/2026 | 01/30/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 227986 | 02368 | 10 | Solar | 05_09_909W3 | 06/27/2019 | 07/08/2019 | 5 | 0 | 5 | 07/09/2019 | 07/09/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 | 06/27/2019 | 6/27/2020 | Y | EXP | 365 | 12/06/2019 | 12/20/2019 | 14 | 0 | 14 |  |  | 1/17/2020 | Connected |  | N
National Grid | BOXFORD | 287352 | 01921 | 7.6 | Solar | 05_07_97W2 | 06/10/2020 | 06/15/2020 | 2 | 0 | 2 | 06/16/2020 | 06/16/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/10/2020 | 6/30/2021 | Y | EXP | 365 | 01/29/2021 | 03/11/2021 | 41 | 0 | 41 |  |  | 6/6/2021 | Connected |  | N
National Grid | WEST BRIDGEWATER | 673471 | 02379 | 7.25 | Solar | 05_14_43L7 | 02/21/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | NANTUCKET | 676982 | 02554 | 750 | Solar | 05_07_797W20 | 04/08/2025 | 06/27/2025 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2025 | 07/23/2025 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WILLIAMSBURG | 174904 | 01039 | 900 | Wind | 04_04_101L6 | 10/07/2011 | 10/07/2011 | 594 | 389 | 205 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 271260 | 02368 | 25 | Solar | 05_09_909W3 | 12/31/2019 | 01/29/2020 | 19 | 18 | 1 | 01/30/2020 | 01/30/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 1/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2020 | Connected |  | N
National Grid | BOXFORD | 310071 | 01921 | 5 | Solar | 05_07_97W2 | 01/11/2021 | 01/15/2021 | 3 | 0 | 3 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  | 4/26/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 674186 | 02301 | 3.8 | Solar | 05_14_43L7 | 02/26/2025 | 03/27/2025 | 12 | 8 | 4 | 03/28/2025 | 03/28/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 | 02/26/2025 | 7/24/2026 | Y | EXP | 365 | 08/21/2025 | 12/22/2025 | 124 | 0 | 124 |  |  | 12/3/2025 | Connected |  | N
National Grid | NANTUCKET | 683042 | 02554 | 10 | Solar | 05_07_797W20 | 04/07/2025 | 04/30/2025 | 1 | 0 | 1 | 05/01/2025 | 05/01/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WILLIAMSBURG | 350253 | 01039 | 7.6 | Solar | 04_04_101L6 | 04/05/2021 | 04/06/2021 | 1 | 1 | 0 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2021 |  | 4/5/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2021 | Connected |  | N
National Grid | RANDOLPH | 288067 | 02368 | 4950 | Other | 05_09_909W3 | 05/15/2020 | 05/29/2020 | 8 | 0 | 8 |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 06/01/2020 | 07/30/2020 | 43 | 25 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 319113 | 01921 | 5 | Solar | 05_07_97W2 | 11/22/2020 | 11/24/2020 | 1 | 0 | 1 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 11/22/2020 |  | Y | EXP | 365 | 04/27/2021 | 05/21/2021 | 24 | 0 | 24 |  |  | 6/22/2021 | Connected |  | N
National Grid | BROCKTON | 694259 | 02301 | 15.2 | Solar | 05_14_43L7 | 06/02/2025 | 06/04/2025 | 2 | 0 | 2 | 06/05/2025 | 06/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  | 7/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 695308 | 02554 | 9.772 | Solar | 05_07_797W20 | 02/02/2026 | 02/20/2026 | 13 | 11 | 2 | 02/23/2026 | 02/23/2026 | 28 | 12 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WILLIAMSBURG | 360480 | 01039 | 7.6 | Solar | 04_04_101L6 | 05/27/2021 | 06/01/2021 | 1 | 0 | 1 | 06/02/2021 | 06/02/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2021 |  | 7/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2021 | Connected |  | N
National Grid | RANDOLPH | 332573 | 02368 | 3.48 | Solar | 05_09_909W3 | 01/11/2021 | 01/15/2021 | 3 | 0 | 3 | 01/19/2021 | 01/19/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/11/2021 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2021 | Connected |  | N
National Grid | BOXFORD | 325552 | 01921 | 7.68 | Solar | 05_07_97W2 | 12/28/2020 | 01/12/2021 | 9 | 9 | 0 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 | 12/28/2020 | 5/25/2022 | Y | EXP | 365 | 04/27/2021 | 05/19/2021 | 22 | 0 | 22 |  |  | 10/4/2021 | Connected |  | N
National Grid | WEST BRIDGEWATER | 174844 | 02379 | 2000 | Solar | 05_14_2396 | 11/04/2011 | 11/04/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2011 | 12/28/2011 | 8 | 0 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/5/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 735664 | 02554 | 5.76 | Solar | 05_07_797W20 | 11/21/2025 | 11/24/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WILLIAMSBURG | 398235 | 01039 | 20 | Solar | 04_04_101L6 | 11/30/2021 | 01/04/2022 | 7 | 6 | 1 | 12/10/2021 | 12/10/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 |  | 3/10/2024 | N | EXP | 770 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | RANDOLPH | 345682 | 02368 | 49.08 | Solar | 05_09_909W3 | 03/08/2021 | 03/15/2021 | 4 | 0 | 4 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 332457 | 01835 | 3.8 | Solar | 05_07_97W2 | 01/07/2021 | 01/15/2021 | 6 | 6 | 0 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 |  | 1/14/2022 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 174843 | 02333 | 2000 | Solar | 05_14_2396 | 11/04/2011 | 11/04/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2011 | 12/28/2011 | 8 | 0 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 752108 | 02554 | 13.12 | Solar | 05_07_797W20 | 02/19/2026 | 03/02/2026 | 6 | 3 | 3 | 03/03/2026 | 03/03/2026 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 490698 | 01053 | 19 | Solar | 04_04_101L6 | 02/09/2023 | 02/13/2023 | 3 | 1 | 2 | 02/14/2023 | 02/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2023 |  | 4/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2024 | Connected |  | N
National Grid | RANDOLPH | 357554 | 02368 | 8.99 | Solar | 05_09_909W3 | 05/11/2021 | 05/17/2021 | 4 | 4 | 0 | 05/18/2021 | 05/18/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  | 5/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2021 | Connected |  | N
National Grid | HAVERHILL | 337718 | 01835 | 4.08 | Solar | 05_07_97W2 | 02/05/2021 | 04/26/2021 | 54 | 53 | 1 | 04/27/2021 | 04/27/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 4/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2021 | Connected |  | N
National Grid | WEST BRIDGEWATER | 174842 | 02379 | 2000 | Solar | 05_14_2396 | 11/04/2011 | 11/04/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2011 | 12/28/2011 | 8 | 0 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2013 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 177426 | 02554 | 7.6 | Solar | 05_07_797W20 | 02/27/2017 | 02/27/2017 | 6 | 6 | 0 | 03/08/2017 | 03/08/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2017 |  | 3/5/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 10/4/2018 | Connected |  | N
National Grid | GOSHEN | 572025 | 01096 | 22.8 | Solar | 04_04_101L6 | 11/17/2023 | 11/20/2023 | 1 | 0 | 1 | 11/21/2023 | 11/21/2023 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 2/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2024 | Connected |  | N
National Grid | RANDOLPH | 426237 | 02368 | 7.6 | Solar | 05_09_909W3 | 04/28/2022 | 04/29/2022 | 1 | 0 | 1 | 05/02/2022 | 05/02/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 | 04/28/2022 | 8/11/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2022 | Connected |  | Y
National Grid | HAVERHILL | 399692 | 01835 | 9.8 | Solar | 05_07_97W2 | 12/21/2021 | 12/22/2021 | 1 | 0 | 1 | 12/23/2021 | 12/23/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2022 | 12/21/2021 | 8/2/2023 | Y | EXP | 365 | 07/12/2022 | 08/01/2022 | 21 | 0 | 21 |  |  | 8/25/2022 | Connected |  | N
National Grid | WEST BRIDGEWATER | 175065 | 02379 | 936 | Solar | 05_09_501L4 | 03/28/2013 | 03/28/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2013 | 06/14/2013 | 46 | 0 | 46 |  | 0 | 0 | 0 | 04/23/2014 | 06/11/2014 | 34 | 0 | 34 | 6/11/2014 |  | 7/1/2016 | N | STD | 751 |  |  | 0 | 0 | 0 | 7/12/2017 | 7/12/2017 | 8/4/2017 | Connected |  | N
National Grid | NANTUCKET | 177657 | 02554 | 1000 | Solar | 05_07_797W20 | 11/10/2017 | 11/10/2017 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2017 | 01/12/2018 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 11/19/2018 | N | STD | 159 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 609956 | 01053 | 22.8 | Solar | 04_04_101L6 | 05/09/2024 | 05/14/2024 | 3 | 1 | 2 | 05/15/2024 | 05/15/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2024 | Connected |  | N
National Grid | RANDOLPH | 428923 | 02368 | 23 | Solar | 05_09_909W3 | 05/09/2022 | 05/19/2022 | 2 | 1 | 1 | 06/12/2024 | 06/12/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2022 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | ANDOVER | 412389 | 01845 | 3 | Solar | 05_07_97W2 | 03/24/2022 | 03/28/2022 | 2 | 0 | 2 | 03/29/2022 | 03/29/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2022 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 175064 | 02379 | 4016 | Solar | 05_09_501L4 | 10/23/2012 | 10/23/2012 | 13 | 11 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2012 | 02/05/2013 | 41 | 0 | 41 |  | 0 | 0 | 0 | 04/23/2014 | 06/11/2014 | 34 | 0 | 34 | 6/11/2014 | 10/23/2012 | 7/1/2016 | Y | STD | 751 | 09/09/2016 | 06/20/2017 | 193 | 0 | 193 | 6/28/2017 | 6/28/2017 | 6/28/2017 | Connected |  | N
National Grid | NANTUCKET | 189857 | 02554 | 999 | Solar | 05_07_797W20 | 07/16/2018 | 08/27/2018 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2018 | 03/09/2020 | 186 | 4 | 182 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2019 |  | 4/29/2021 | N | STD | 658 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 659236 | 01096 | 20 | Solar | 04_04_101L6 | 12/09/2024 | 12/16/2024 | 5 | 4 | 1 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N
National Grid | RANDOLPH | 435182 | 02368 | 15.2 | Solar | 05_09_909W3 | 06/09/2022 | 06/14/2022 | 3 | 0 | 3 | 06/15/2022 | 06/15/2022 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 7/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | Y
National Grid | SALISBURY | 416744 | 01952 | 5.51 | Solar | 05_07_97W2 | 04/07/2022 | 04/11/2022 | 2 | 0 | 2 | 04/12/2022 | 04/12/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2022 | 04/07/2022 | 12/13/2023 | Y | EXP | 365 | 11/04/2022 | 12/12/2022 | 39 | 0 | 39 |  |  | 1/7/2023 | Connected |  | N
National Grid | WEST BRIDGEWATER | 677862 | 02379 | 240 | Solar | 05_05_3451W3 | 03/17/2025 | 04/07/2025 | 16 | 6 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NANTUCKET | 198658 | 02554 | 433.3 | Solar | 05_07_797W20 | 11/01/2018 | 11/07/2018 | 3 | 0 | 3 | 11/08/2018 | 11/08/2018 | 37 | 23 | 14 | 01/10/2019 | 03/11/2019 | 40 | 21 | 19 |  |  | 0 | 0 | 0 | 03/11/2019 | 40 | 21 | 19 |  |  | 0 | 0 | 0 | 3/25/2019 |  | 1/2/2021 | N | EXP | 649 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 692607 | 01039 | 100 | Solar | 04_04_101L7 | 05/21/2025 | 06/27/2025 | 24 | 14 | 10 | 06/30/2025 | 06/30/2025 | 16 | 0 | 16 | 08/11/2025 | 09/08/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 09/08/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 485087 | 02368 | 6 | Solar | 05_09_909W3 | 02/08/2023 | 02/09/2023 | 1 | 0 | 1 | 02/10/2023 | 02/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 429334 | 01952 | 15.2 | Solar | 05_07_97W2 | 05/09/2022 | 05/13/2022 | 3 | 3 | 0 | 05/16/2022 | 05/16/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 |  | 6/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2022 | Connected |  | N
National Grid | WEST BRIDGEWATER | 740765 | 02379 | 11.4 | Solar | 05_05_3451W3 | 12/17/2025 | 12/18/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 292016 | 02554 | 7.83 | Solar | 05_07_797W20 | 05/27/2020 | 06/03/2020 | 4 | 0 | 4 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2021 | Connected |  | N
National Grid | NORTHAMPTON | 706278 | 01060 | 50 | Solar | 04_04_101L7 | 08/08/2025 | 08/14/2025 | 3 | 0 | 3 | 08/15/2025 | 08/15/2025 | 19 | 0 | 19 | 09/18/2025 | 10/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 10/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 520969 | 02368 | 6 | Solar | 05_09_909W3 | 06/02/2023 | 06/05/2023 | 1 | 0 | 1 | 06/06/2023 | 06/06/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 7/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 438829 | 01952 | 6 | Solar | 05_07_97W2 | 06/27/2022 | 06/29/2022 | 2 | 0 | 2 | 06/30/2022 | 06/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/27/2022 | 6/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2025 | Connected |  | N
National Grid | BRIDGEWATER | 749879 | 02333 | 8.027 | Solar | 05_05_3451W3 | 03/06/2026 | 03/09/2026 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | NANTUCKET | 337504 | 02554 | 150 | Solar | 05_07_797W20 | 01/26/2021 | 02/03/2021 | 5 | 0 | 5 | 02/04/2021 | 02/04/2021 | 22 | 0 | 22 | 04/12/2021 | 07/13/2021 | 48 | 0 | 48 |  |  | 0 | 0 | 0 | 07/13/2021 | 48 | 0 | 48 |  |  | 0 | 0 | 0 | 7/6/2021 | 01/26/2021 | 11/25/2022 | Y | EXP | 273 | 02/05/2022 | 07/11/2022 | 158 | 119 | 39 |  |  | 12/6/2022 | Connected |  | N
National Grid | NORTHAMPTON | 725845 | 01053 | 11.2 | Solar | 04_04_101L7 | 10/31/2025 | 12/22/2025 | 32 | 27 | 5 | 12/23/2025 | 12/23/2025 | 66 | 49 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 531637 | 02368 | 15.2 | Solar | 05_09_909W3 | 06/06/2023 | 06/12/2023 | 5 | 4 | 1 | 06/13/2023 | 06/13/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2023 |  | 8/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2023 | Connected |  | N
National Grid | WARE | 447515 | 01082 | 10 | Solar | 05_07_97W2 | 08/03/2022 | 08/09/2022 | 4 | 0 | 4 | 08/10/2022 | 08/10/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 |  | 9/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2022 | Connected |  | N
National Grid | WEST BRIDGEWATER | 178767 | 02379 | 225 | Solar | 05_05_3451W3 | 07/31/2012 | 07/31/2012 | 8 | 2 | 6 | 08/14/2012 | 08/14/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 12/18/2012 | 12/18/2012 | 12/31/2012 | Connected |  | N
National Grid | NANTUCKET | 378348 | 02554 | 0 | Solar | 05_07_797W20 | 08/26/2021 | 08/27/2021 | 1 | 0 | 1 | 08/30/2021 | 08/30/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 3/6/2023 | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 751868 | 01039 | 7.6 | Solar | 04_04_101L7 | 02/26/2026 | 03/06/2026 | 4 | 2 | 2 | 03/09/2026 | 03/09/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | RANDOLPH | 532258 | 02368 | 10 | Solar | 05_09_909W3 | 06/07/2023 | 06/22/2023 | 10 | 0 | 10 | 06/23/2023 | 06/23/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 7/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2023 | Connected |  | N
National Grid | WARE | 468022 | 01082 | 6 | Solar | 05_07_97W2 | 12/05/2022 | 12/07/2022 | 2 | 0 | 2 | 12/08/2022 | 12/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 | 12/05/2022 | 4/13/2024 | Y | EXP | 365 | 04/12/2023 | 04/11/2023 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 178780 | 02379 | 19.995 | Solar | 05_05_3451W3 | 08/08/2014 | 08/08/2014 | 7 | 1 | 6 | 08/20/2014 | 08/20/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2014 |  | 11/28/2014 | N | EXP | 85 |  |  | 0 | 0 | 0 | 9/4/2014 | 9/4/2014 | 11/6/2014 | Connected |  | N
National Grid | NANTUCKET | 389737 | 02554 | 0 | Other | 05_07_797W20 | 11/10/2021 | 01/04/2022 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GOSHEN | 175677 | 01032 | 499 | Solar | 04_04_101L7 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 535697 | 02368 | 151.9 | Solar | 05_09_909W3 | 06/29/2023 | 07/14/2023 | 10 | 0 | 10 |  |  | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 5/2/2025 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | PLAINVILLE | 467533 | 02762 | 7.6 | Solar | 05_07_97W2 | 11/16/2022 | 11/18/2022 | 2 | 0 | 2 | 11/21/2022 | 11/21/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2022 |  | 2/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | WEST BRIDGEWATER | 178797 | 02379 | 2310 | Solar | 05_05_3451W3 | 10/23/2017 | 10/23/2017 | 31 | 29 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 | 01/04/2018 | 8 | 0 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2018 |  | 10/31/2018 | N | STD | 77 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 486251 | 02554 | 10 | Solar | 05_07_797W20 | 12/27/2022 | 01/03/2023 | 4 | 0 | 4 | 01/04/2023 | 01/04/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 | 12/27/2022 | 3/26/2024 | Y | EXP | 365 | 03/28/2023 | 03/27/2023 | 0 | 0 | 0 |  |  | 7/24/2023 | Connected |  | N
National Grid | WILLIAMSBURG | 175676 | 01096 | 1596 | Solar | 04_04_101L7 | 10/28/2014 | 10/28/2014 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 12/12/2014 | 28 | 9 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 546867 | 02368 | 9.86 | Solar | 05_09_909W3 | 08/09/2023 | 08/10/2023 | 1 | 0 | 1 | 08/11/2023 | 08/11/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 | 08/09/2023 | 9/30/2024 | Y | EXP | 365 | 10/19/2023 | 10/24/2023 | 6 | 0 | 6 |  |  | 3/20/2024 | Connected |  | N
National Grid | PLAINVILLE | 490321 | 02762 | 6 | Solar | 05_07_97W2 | 01/24/2023 | 01/27/2023 | 3 | 0 | 3 | 01/30/2023 | 01/30/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 | 01/24/2023 | 9/7/2024 | Y | EXP | 365 | 08/17/2023 | 09/01/2023 | 16 | 0 | 16 |  |  | 9/18/2023 | Connected |  | N
National Grid | WEST BRIDGEWATER | 178795 | 02379 | 4950 | Solar | 05_05_3451W3 | 03/06/2017 | 03/06/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2017 | 03/28/2017 | 12 | 0 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2017 | 03/06/2017 | 12/31/2019 | Y | STD | 753 | 03/08/2019 | 03/08/2019 | 0 | 0 | 0 | 10/16/2019 | 12/16/2019 | 12/30/2019 | Connected |  | N
National Grid | NANTUCKET | 591477 | 02554 | 15.2 | Solar | 05_07_797W20 | 02/20/2024 | 02/22/2024 | 2 | 0 | 2 | 02/23/2024 | 02/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSBURG | 175674 | 01096 | 499 | Solar | 04_04_101L7 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 | 10/31/2014 | 10/31/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 585251 | 02368 | 7.6 | Solar | 05_09_909W3 | 02/02/2024 | 02/16/2024 | 10 | 9 | 1 | 02/20/2024 | 02/20/2024 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 492308 | 02762 | 6 | Solar | 05_07_97W2 | 01/26/2023 | 01/27/2023 | 1 | 0 | 1 | 01/30/2023 | 01/30/2023 | 263 | 25 | 238 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 178790 | 02379 | 10 | Solar | 05_05_3451W3 | 10/31/2016 | 10/31/2016 | 4 | 4 | 0 | 11/07/2016 | 11/07/2016 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/6/2017 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 625438 | 02554 | 9.86 | Solar | 05_07_797W20 | 07/17/2024 | 07/24/2024 | 3 | 1 | 2 | 07/25/2024 | 07/25/2024 | 17 | 6 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/17/2024 | 8/23/2025 | Y | EXP | 365 | 10/29/2024 | 11/13/2024 | 16 | 0 | 16 |  |  | 11/15/2024 | Connected |  | N
National Grid | WILLIAMSBURG | 175673 | 01096 | 3024 | Solar | 04_04_101L7 | 10/22/2014 | 10/22/2014 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/2/2015 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 587581 | 02368 | 15.2 | Solar | 05_09_909W3 | 02/02/2024 | 02/06/2024 | 2 | 1 | 1 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2025 | Connected |  | Y
National Grid | PLAINVILLE | 517602 | 02762 | 3.8 | Solar | 05_07_97W2 | 04/24/2023 | 04/26/2023 | 2 | 0 | 2 | 04/27/2023 | 04/27/2023 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 04/24/2023 | 8/22/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2023 | Connected |  | N
National Grid | BRIDGEWATER | 259106 | 02324 | 10 | Solar | 05_05_3451W3 | 10/10/2019 | 10/21/2019 | 5 | 0 | 5 | 10/22/2019 | 10/22/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 |  | 10/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2020 | Connected |  | N
National Grid | NANTUCKET | 634657 | 02554 | 9.86 | Solar | 05_07_797W20 | 08/22/2024 | 09/03/2024 | 4 | 0 | 4 | 09/04/2024 | 09/04/2024 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 | 08/22/2024 | 11/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | NORTHAMPTON | 177279 | 01053 | 3600 | Solar | 04_04_101L7 | 02/08/2017 | 02/08/2017 | 136 | 134 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/14/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 602108 | 02368 | 499 | Solar | 05_09_909W3 | 07/29/2024 | 08/08/2024 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2024 | 08/15/2024 | 5 | 0 | 5 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 519279 | 02762 | 9.984 | Solar | 05_07_97W2 | 06/16/2023 | 06/21/2023 | 2 | 1 | 1 | 06/22/2023 | 06/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 | 06/16/2023 | 12/6/2024 | Y | EXP | 365 | 10/26/2023 | 12/04/2023 | 40 | 0 | 40 |  |  | 12/29/2023 | Connected |  | N
National Grid | WEST BRIDGEWATER | 278143 | 02379 | 4107 | Solar | 05_05_3451W3 | 03/05/2020 | 03/18/2020 | 9 | 7 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2020 | 04/10/2020 | 16 | 4 | 12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2021 | 03/05/2020 | 2/22/2024 | Y | STD | 490 | 09/26/2023 | 01/02/2024 | 99 | 3 | 96 |  |  | 6/26/2024 | Connected |  | N
National Grid | NANTUCKET | 637313 | 02554 | 34.5 | Solar | 05_07_797W20 | 09/03/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 47 | 38 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | WILLIAMSBURG | 177334 | 01039 | 27 | Solar | 04_04_101L7 | 08/31/2016 | 08/31/2016 | 2 | 2 | 0 | 09/02/2016 | 09/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2016 |  | 9/5/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/22/2016 | 11/28/2016 | Connected |  | N
National Grid | RANDOLPH | 606572 | 02368 | 23 | Solar | 05_09_909W3 | 04/25/2024 | 05/01/2024 | 5 | 3 | 2 | 05/02/2024 | 05/02/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  | 6/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2024 | Connected |  | N
National Grid | PLAINVILLE | 559566 | 02762 | 6 | Solar | 05_07_97W2 | 10/25/2023 | 10/26/2023 | 1 | 0 | 1 | 10/27/2023 | 10/27/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 10/25/2023 | 1/22/2025 | Y | EXP | 365 | 03/14/2024 | 05/09/2024 | 57 | 0 | 57 |  |  | 6/8/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 290815 | 02379 | 7.6 | Solar | 05_05_3451W3 | 05/06/2020 | 05/11/2020 | 2 | 0 | 2 | 05/12/2020 | 05/12/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2020 |  | 11/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2022 | Connected |  | N
National Grid | NANTUCKET | 647055 | 02554 | 10 | Solar | 05_07_797W20 | 10/24/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/24/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 177601 | 01053 | 57.6 | Solar | 04_04_101L7 | 07/19/2017 | 07/19/2017 | 18 | 17 | 1 | 08/14/2017 | 08/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 7/24/2018 | N | EXP | 343 |  |  | 0 | 0 | 0 | 12/8/2017 | 12/8/2017 | 12/21/2017 | Connected |  | N
National Grid | RANDOLPH | 610184 | 02368 | 10 | Solar | 05_09_909W3 | 05/16/2024 | 06/05/2024 | 14 | 13 | 1 | 06/06/2024 | 06/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | PLAINVILLE | 550162 | 02762 | 10 | Solar | 05_07_97W2 | 08/29/2023 | 08/30/2023 | 1 | 0 | 1 | 08/31/2023 | 08/31/2023 | 41 | 16 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 08/29/2023 | 11/23/2024 | Y | EXP | 365 | 12/07/2023 | 02/17/2024 | 73 | 3 | 70 |  |  | 3/18/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 313374 | 02379 | 8.64 | Solar | 05_05_3451W3 | 09/17/2020 | 09/18/2020 | 0 | 0 | 0 | 09/21/2020 | 09/21/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/17/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2021 | Connected |  | N
National Grid | NANTUCKET | 654486 | 02554 | 10 | Solar | 05_07_797W20 | 11/18/2024 | 12/18/2024 | 1 | 0 | 1 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/18/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | NORTHAMPTON | 197532 | 01053 | 9.92 | Solar | 04_04_101L7 | 10/02/2018 | 10/22/2018 | 9 | 9 | 0 | 10/23/2018 | 10/23/2018 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 611991 | 02368 | 7.6 | Solar | 05_09_909W3 | 05/19/2024 | 05/21/2024 | 3 | 2 | 1 | 05/22/2024 | 05/22/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | N
National Grid | PLAINVILLE | 555021 | 02762 | 10 | Solar | 05_07_97W2 | 09/15/2023 | 09/18/2023 | 1 | 0 | 1 | 09/19/2023 | 09/19/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2023 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 329828 | 02379 | 15.2 | Solar | 05_05_3451W3 | 12/05/2020 | 12/08/2020 | 1 | 0 | 1 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 3/31/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 2/23/2022 | Connected |  | Y
National Grid | NANTUCKET | 657495 | 02554 | 11.5 | Solar | 05_07_797W20 | 11/27/2024 | 12/11/2024 | 9 | 7 | 2 | 12/12/2024 | 12/12/2024 | 82 | 59 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/19/2025 | Connected |  | N
National Grid | WILLIAMSBURG | 315235 | 01096 | 11.4 | Solar | 04_04_101L7 | 10/05/2020 | 10/12/2020 | 4 | 2 | 2 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2021 | Connected |  | N
National Grid | RANDOLPH | 617800 | 02368 | 10 | Solar | 05_09_909W3 | 06/13/2024 | 06/24/2024 | 3 | 0 | 3 | 06/25/2024 | 06/25/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2024 | 06/13/2024 | 7/30/2025 | Y | EXP | 365 | 08/22/2024 | 08/23/2024 | 2 | 0 | 2 |  |  | 1/7/2025 | Connected |  | N
National Grid | PLAINVILLE | 560567 | 02762 | 6.144 | Solar | 05_07_97W2 | 10/06/2023 | 10/12/2023 | 10 | 6 | 4 | 10/24/2023 | 10/24/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2023 | 10/06/2023 | 12/28/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 412928 | 02379 | 11.4 | Solar | 05_05_3451W3 | 02/17/2022 | 02/23/2022 | 3 | 0 | 3 | 02/24/2022 | 02/24/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  | 7/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2023 | Connected |  | N
National Grid | NANTUCKET | 665671 | 02554 | 0 | Solar | 05_07_797W20 | 01/15/2025 | 01/23/2025 | 5 | 2 | 3 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 | 01/15/2025 | 4/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2025 | Connected |  | N
National Grid | GOSHEN | 324332 | 01032 | 19 | Solar | 04_04_101L7 | 11/10/2020 | 11/17/2020 | 3 | 0 | 3 | 11/18/2020 | 11/18/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2021 | Connected |  | N
National Grid | RANDOLPH | 619298 | 02368 | 11.5 | Solar | 05_09_909W3 | 06/20/2024 | 06/24/2024 | 2 | 0 | 2 | 06/25/2024 | 06/25/2024 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2024 | Connected |  | N
National Grid | PLAINVILLE | 562983 | 02762 | 9.765 | Solar | 05_07_97W2 | 12/04/2023 | 12/27/2023 | 16 | 13 | 3 | 12/28/2023 | 12/28/2023 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 | 12/04/2023 | 2/20/2025 | Y | EXP | 365 | 05/11/2024 | 05/14/2024 | 4 | 0 | 4 |  |  | 5/30/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 490027 | 02379 | 15.2 | Solar | 05_05_3451W3 | 01/23/2023 | 01/25/2023 | 3 | 2 | 1 | 01/26/2023 | 01/26/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  | 8/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2023 | Connected |  | N
National Grid | NANTUCKET | 671083 | 02554 | 15.2 | Solar | 05_07_797W20 | 02/10/2025 | 02/19/2025 | 4 | 0 | 4 | 07/18/2025 | 07/18/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 10/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | NORTHAMPTON | 331118 | 01053 | 19.72 | Solar | 04_04_101L7 | 01/15/2021 | 01/25/2021 | 4 | 0 | 4 | 01/26/2021 | 01/26/2021 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2021 | Connected |  | N
National Grid | RANDOLPH | 631438 | 02368 | 0 | Solar | 05_09_909W3 | 08/09/2024 | 08/15/2024 | 5 | 2 | 3 | 08/16/2024 | 08/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 9/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2024 | Connected |  | N
National Grid | PLAINVILLE | 570882 | 02762 | 10 | Solar | 05_07_97W2 | 12/01/2023 | 12/06/2023 | 3 | 0 | 3 | 12/07/2023 | 12/07/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 12/01/2023 | 1/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 588469 | 02379 | 6 | Solar | 05_05_3451W3 | 02/15/2024 | 02/16/2024 | 1 | 0 | 1 | 02/20/2024 | 02/20/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2024 | Connected |  | N
National Grid | NANTUCKET | 674770 | 02554 | 5.76 | Solar | 05_07_797W20 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N
National Grid | WILLIAMSBURG | 371953 | 01039 | 100 | Solar | 04_04_101L7 | 07/26/2021 | 08/17/2021 | 16 | 6 | 10 | 08/18/2021 | 08/18/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 | 07/26/2021 | 7/14/2023 | Y | EXP | 98 |  |  | 0 | 0 | 0 |  |  | 7/21/2023 | Connected |  | N
National Grid | RANDOLPH | 632702 | 02368 | 7.6 | Solar | 05_09_909W3 | 08/14/2024 | 08/20/2024 | 2 | 1 | 1 | 08/21/2024 | 08/21/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/14/2024 | 9/4/2025 | Y | EXP | 365 | 10/10/2024 | 10/23/2024 | 14 | 0 | 14 |  |  | 1/30/2025 | Connected |  | N
National Grid | PLAINVILLE | 576442 | 02762 | 10 | Solar | 05_07_97W2 | 12/08/2023 | 12/29/2023 | 15 | 12 | 3 | 01/02/2024 | 01/02/2024 | 36 | 14 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 664435 | 02379 | 11.5 | Solar | 05_05_3451W3 | 01/09/2025 | 01/16/2025 | 1 | 0 | 1 | 01/17/2025 | 01/17/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 3/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | NANTUCKET | 688918 | 02554 | 9.425 | Solar | 05_07_797W20 | 05/01/2025 | 09/15/2025 | 93 | 91 | 2 | 09/16/2025 | 09/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GOSHEN | 404158 | 01032 | 60 | Solar | 04_04_101L7 | 12/30/2021 | 02/04/2022 | 25 | 18 | 7 | 02/07/2022 | 02/07/2022 | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2022 |  | 9/16/2023 | N | EXP | 386 |  |  | 0 | 0 | 0 |  |  | 10/21/2022 | Connected |  | N
National Grid | RANDOLPH | 638792 | 02368 | 5.85 | Solar | 05_09_909W3 | 09/09/2024 | 10/21/2024 | 1 | 0 | 1 | 10/22/2024 | 10/22/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 09/09/2024 | 12/3/2025 | Y | EXP | 365 | 01/04/2025 | 02/11/2025 | 39 | 0 | 39 |  |  | 3/6/2025 | Connected |  | N
National Grid | RANDOLPH | 580555 | 2368 | 4.64 | Solar | 05_07_97W2 | 01/12/2024 | 01/18/2024 | 3 | 0 | 3 | 01/19/2024 | 01/19/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 731605 | 02379 | 13.8 | Solar | 05_05_3451W3 | 11/06/2025 | 11/25/2025 | 4 | 1 | 3 | 11/26/2025 | 11/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2026 | Connected |  | N
National Grid | NANTUCKET | 697453 | 02554 | 15.2 | Solar | 05_07_797W20 | 06/12/2025 | 06/25/2025 | 8 | 6 | 2 | 06/26/2025 | 06/26/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/2/2026 | Connected |  | N
National Grid | GOSHEN | 485414 | 01032 | 100 | Solar | 04_04_101L7 | 01/06/2023 | 02/06/2023 | 21 | 11 | 10 | 02/07/2023 | 02/07/2023 | 25 | 0 | 25 | 04/04/2023 | 05/16/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 05/16/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 5/30/2023 |  | 12/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2024 | Connected |  | N
National Grid | RANDOLPH | 641184 | 02368 | 15.2 | Solar | 05_09_909W3 | 09/18/2024 | 09/20/2024 | 3 | 1 | 2 | 09/23/2024 | 09/23/2024 | 16 | 0 | 16 | 11/20/2024 | 12/29/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 12/29/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 1/6/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | RANDOLPH | 581836 | 2368 | 5.51 | Solar | 05_07_97W2 | 01/19/2024 | 01/22/2024 | 1 | 0 | 1 | 01/23/2024 | 01/23/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 676376 | 02379 | 360 | Solar | 05_07_1W10 | 08/01/2025 | 09/23/2025 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/24/2025 | 10/20/2025 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | NANTUCKET | 718781 | 02554 | 12.16 | Solar | 05_07_797W20 | 09/12/2025 | 11/04/2025 | 1 | 0 | 1 | 11/05/2025 | 11/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 492630 | 01096 | 21.638 | Solar | 04_04_101L7 | 01/16/2023 | 01/18/2023 | 2 | 0 | 2 | 01/19/2023 | 01/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2023 |  | 3/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N
National Grid | RANDOLPH | 644899 | 02368 | 16.53 | Solar | 05_09_909W3 | 10/03/2024 | 10/16/2024 | 8 | 6 | 2 | 10/17/2024 | 10/17/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 11/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | PLAINVILLE | 586650 | 02762 | 8.7 | Solar | 05_07_97W2 | 02/07/2024 | 02/09/2024 | 2 | 0 | 2 | 02/12/2024 | 02/12/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/07/2024 | 3/1/2025 | Y | EXP | 365 | 03/30/2024 | 04/17/2024 | 19 | 0 | 19 |  |  | 5/14/2024 | Connected |  | N
National Grid | BRIDGEWATER | 469559 | 02333 | 22.8 | Solar | 05_07_1W10 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 | 11/29/2022 | 1/25/2024 | Y | EXP | 365 | 03/09/2023 | 05/26/2023 | 79 | 0 | 79 |  |  | 6/13/2023 | Connected |  | N
National Grid | NANTUCKET | 649258 | 02554 | 499 | Solar | 05_07_797W23 | 02/14/2025 | 03/12/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2025 | 04/08/2025 | 19 | 0 | 19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GOSHEN | 526775 | 01032 | 16.24 | Solar | 04_04_101L7 | 05/23/2023 | 07/03/2023 | 28 | 26 | 2 | 07/05/2023 | 07/05/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 |  | 8/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2023 | Connected |  | Y
National Grid | RANDOLPH | 645387 | 02368 | 10.725 | Solar | 05_09_909W3 | 10/08/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/08/2024 | 12/8/2025 | Y | EXP | 365 | 02/13/2025 | 02/25/2025 | 13 | 0 | 13 |  |  | 2/28/2025 | Connected |  | N
National Grid | PLAINVILLE | 586576 | 02762 | 7.25 | Solar | 05_07_97W2 | 02/07/2024 | 02/14/2024 | 5 | 0 | 5 | 02/15/2024 | 02/15/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/07/2024 | 3/15/2025 | Y | EXP | 365 | 08/29/2024 | 09/30/2024 | 33 | 0 | 33 |  |  | 10/10/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 662446 | 02379 | 8.45 | Solar | 05_07_1W9 | 12/24/2024 | 02/07/2025 | 4 | 0 | 4 | 02/10/2025 | 02/10/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 656709 | 02554 | 4800 | Solar | 05_07_797W23 | 01/07/2025 | 09/15/2025 | 171 | 162 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2025 | 10/13/2025 | 19 | 3 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTHAMPTON | 551854 | 01060 | 19 | Solar | 04_04_101L7 | 08/29/2023 | 09/14/2023 | 12 | 11 | 1 | 09/15/2023 | 09/15/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2023 |  | 11/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | RANDOLPH | 645594 | 02368 | 10 | Solar | 05_09_909W3 | 10/08/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 587494 | 02762 | 7.6 | Solar | 05_07_97W2 | 02/12/2024 | 02/15/2024 | 3 | 0 | 3 | 02/16/2024 | 02/16/2024 | 5 | 0 | 5 | 03/22/2024 | 02/12/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 02/12/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 5/3/2024 |  | 5/22/2025 | N | EXP | 365 | 06/13/2024 | 10/09/2024 | 119 | 0 | 119 |  |  | 11/7/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 712885 | 02379 | 360 | Solar | 05_07_1W9 | 09/24/2025 | 11/04/2025 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2025 | 12/04/2025 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | NANTUCKET | 717436 | 02554 | 34.2 | Solar | 05_07_797W23 | 09/08/2025 | 09/22/2025 | 9 | 6 | 3 | 09/23/2025 | 09/23/2025 | 122 | 103 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | WILLIAMSBURG | 590905 | 01096 | 0 | Other | 04_04_101L7 | 03/14/2024 | 03/27/2024 | 9 | 7 | 2 | 03/28/2024 | 03/28/2024 | 98 | 74 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 650879 | 02368 | 23 | Solar | 05_09_909W3 | 10/30/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 10/30/2024 | 1/31/2026 | Y | EXP | 365 | 05/15/2025 | 06/16/2025 | 33 | 0 | 33 |  |  | 6/17/2025 | Connected |  | N
National Grid | PLAINVILLE | 590155 | 02762 | 7.6 | Solar | 05_07_97W2 | 02/23/2024 | 04/11/2024 | 34 | 25 | 9 | 04/12/2024 | 04/12/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 | 02/23/2024 | 5/3/2025 | Y | EXP | 365 | 10/05/2024 | 11/22/2024 | 49 | 0 | 49 |  |  | 12/3/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 752339 | 02379 | 17.6 | Solar | 05_07_1W9 | 03/03/2026 | 03/05/2026 | 2 | 0 | 2 | 03/06/2026 | 03/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NANTUCKET | 735422 | 02554 | 5.76 | Solar | 05_07_797W23 | 11/20/2025 | 12/12/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 63 | 48 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 660023 | 01053 | 5 | Solar | 04_04_101L7 | 12/11/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | RANDOLPH | 659585 | 02368 | 11.2 | Solar | 05_09_909W3 | 12/10/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | QUINCY | 589671 | 02169 | 9.57 | Solar | 05_07_97W2 | 02/27/2024 | 02/28/2024 | 1 | 0 | 1 | 02/29/2024 | 02/29/2024 | 94 | 25 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 754311 | 02379 | 7.6 | Solar | 05_07_1W9 | 03/03/2026 | 03/05/2026 | 2 | 0 | 2 | 03/06/2026 | 03/06/2026 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NANTUCKET | 745482 | 02554 | 11.78 | Solar | 05_07_797W23 | 01/15/2026 | 01/16/2026 | 4 | 1 | 3 | 01/29/2026 | 01/29/2026 | 44 | 28 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GOSHEN | 688005 | 01032 | 25 | Solar | 04_04_101L7 | 04/28/2025 | 05/15/2025 | 12 | 9 | 3 | 05/16/2025 | 05/16/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2025 | Connected |  | N
National Grid | RANDOLPH | 663177 | 02368 | 11.5 | Solar | 05_09_909W3 | 12/31/2024 | 01/27/2025 | 2 | 0 | 2 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 12/31/2024 | 4/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | QUINCY | 591319 | 02169 | 7.6 | Solar | 05_07_97W2 | 03/06/2024 | 04/17/2024 | 27 | 25 | 2 | 04/18/2024 | 04/18/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 321557 | 02333 | 21.46 | Solar | 05_07_1W9 | 10/30/2020 | 11/19/2020 | 12 | 9 | 3 | 11/20/2020 | 11/20/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 1/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 745718 | 02554 | 13.8 | Solar | 05_07_797W23 | 01/15/2026 | 01/21/2026 | 1 | 0 | 1 | 01/29/2026 | 01/29/2026 | 44 | 28 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WILLIAMSBURG | 702575 | 01096 | 25.08 | Solar | 04_04_101L7 | 07/07/2025 | 07/11/2025 | 3 | 1 | 2 | 07/14/2025 | 07/14/2025 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | RANDOLPH | 669864 | 02368 | 10 | Solar | 05_09_909W3 | 02/13/2025 | 02/19/2025 | 3 | 0 | 3 | 02/20/2025 | 02/20/2025 | 60 | 37 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 | 02/13/2025 | 5/28/2026 | Y | EXP | 365 | 06/18/2025 | 06/30/2025 | 13 | 0 | 13 |  |  | 9/2/2025 | Connected |  | N
National Grid | QUINCY | 595756 | 02169 | 10 | Solar | 05_07_97W2 | 03/14/2024 | 03/15/2024 | 1 | 0 | 1 | 03/18/2024 | 03/18/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 | 03/14/2024 | 3/25/2025 | Y | EXP | 365 | 10/03/2024 | 11/01/2024 | 30 | 0 | 30 |  |  | 11/9/2024 | Connected |  | N
National Grid | EAST BRIDGEWATER | 379796 | 02333 | 0 | Solar | 05_07_1W9 | 10/21/2021 | 12/17/2021 | 39 | 30 | 9 | 12/20/2021 | 12/20/2021 | 46 | 22 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 757011 | 02554 | 17.28 | Solar | 05_07_797W23 | 03/17/2026 | 03/19/2026 | 2 | 0 | 2 | 03/20/2026 | 03/20/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WILLIAMSBURG | 174809 | 01039 | 145 | Solar | 05_01_10J323 | 01/24/2013 | 01/24/2013 | 7 | 0 | 7 | 02/05/2013 | 02/05/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2013 |  | 5/15/2013 | N | EXP | 33 | 05/22/2013 | 07/17/2013 | 37 | 0 | 37 | 7/29/2013 | 7/29/2013 | 8/20/2013 | Connected |  | N
National Grid | RANDOLPH | 676558 | 02368 | 23 | Solar | 05_09_909W3 | 03/07/2025 |  | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 601570 | 02169 | 7.6 | Solar | 05_07_97W2 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 714507 | 02333 | 11.4 | Solar | 05_12_8W1 | 08/26/2025 | 09/16/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 175228 | 02554 | 17.6 | Solar | 05_07_797W23 | 01/06/2015 | 01/06/2015 | 9 | 4 | 5 | 01/17/2015 | 01/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 10/6/2015 | 10/6/2015 | 6/17/2016 | Connected |  | N
National Grid | NORTHAMPTON | 578609 | 01062 | 6.96 | Solar | 05_01_10J323 | 01/08/2024 | 01/10/2024 | 2 | 0 | 2 | 01/11/2024 | 01/11/2024 | 172 | 25 | 147 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 676776 | 02368 | 20 | Solar | 05_09_909W3 | 03/10/2025 | 04/14/2025 | 26 | 20 | 6 | 04/15/2025 | 04/15/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 607477 | 02169 | 10 | Solar | 05_07_97W2 | 05/01/2024 | 07/15/2024 | 45 | 42 | 3 | 07/16/2024 | 07/16/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 633465 | 02333 | 15.2 | Solar | 05_12_8W1 | 08/26/2024 | 08/29/2024 | 3 | 0 | 3 | 08/30/2024 | 08/30/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 9/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | NANTUCKET | 175295 | 02554 | 21.2 | Solar | 05_07_797W23 | 01/14/2015 | 01/14/2015 | 4 | 1 | 3 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2015 | 01/14/2015 | 12/31/2016 | Y | EXP | 683 | 11/04/2016 | 11/15/2016 | 6 | 0 | 6 | 1/12/2017 | 1/12/2017 | 1/24/2017 | Connected |  | N
National Grid | NORTHAMPTON | 682333 | 01053 | 22.8 | Solar | 05_01_10J323 | 04/07/2025 | 04/21/2025 | 9 | 5 | 4 | 04/22/2025 | 04/22/2025 | 24 | 10 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2026 | Connected |  | N
National Grid | RANDOLPH | 679096 | 02368 | 10 | Solar | 05_09_909W3 | 03/19/2025 | 04/16/2025 | 5 | 0 | 5 | 04/30/2025 | 04/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 03/19/2025 | 6/5/2026 | Y | EXP | 365 | 09/16/2025 | 09/15/2025 | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | QUINCY | 615043 | 02169 | 3.8 | Solar | 05_07_97W2 | 06/04/2024 | 06/12/2024 | 1 | 0 | 1 | 06/13/2024 | 06/13/2024 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 | 06/04/2024 | 8/28/2025 | Y | EXP | 365 | 09/05/2024 | 09/06/2024 | 2 | 0 | 2 |  |  | 11/6/2024 | Connected |  | N
National Grid | BRIDGEWATER | 669645 | 02324 | 3.8 | Solar | 05_12_8W1 | 02/03/2025 | 02/27/2025 | 6 | 3 | 3 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 | 02/03/2025 | 4/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | NANTUCKET | 176549 | 02554 | 9.6 | Solar | 05_07_797W23 | 04/05/2016 | 04/05/2016 | 1 | 1 | 0 | 04/06/2016 | 04/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 | 04/05/2016 | 4/10/2017 | Y | EXP | 356 | 11/10/2016 | 11/21/2016 | 6 | 0 | 6 | 11/28/2016 | 11/28/2016 | 11/30/2016 | Connected |  | N
National Grid | WILLIAMSBURG | 401106 | 01096 | 0 | Other | 05_01_10J366 | 01/24/2022 | 01/31/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 03/01/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 691016 | 02368 | 25 | Other | 05_09_909W3 | 08/07/2025 |  | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 618878 | 02169 | 7.6 | Solar | 05_07_97W2 | 06/18/2024 | 07/03/2024 | 1 | 0 | 1 | 07/05/2024 | 07/05/2024 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2024 | 06/18/2024 | 8/6/2025 | Y | EXP | 365 | 12/12/2024 | 03/14/2025 | 93 | 0 | 93 |  |  | 4/8/2025 | Connected |  | N
National Grid | BRIDGEWATER | 498286 | 02333 | 480 | Solar | 05_05_348W7 | 06/23/2023 | 09/18/2023 | 60 | 50 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/19/2023 | 10/10/2023 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/23/2023 | 9/23/2027 | Y | STD | 651 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NANTUCKET | 176822 | 02554 | 10 | Solar | 05_07_797W23 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 1/20/2017 | N | EXP | 346 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 11/21/2016 | Connected |  | N
National Grid | WILLIAMSBURG | 622728 | 01096 | 10 | Solar | 05_01_10J366 | 07/27/2024 | 08/28/2024 | 23 | 20 | 3 | 08/29/2024 | 08/29/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2024 |  | 11/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | RANDOLPH | 692583 | 02368 | 6.08 | Solar | 05_09_909W3 | 05/19/2025 | 06/18/2025 | 1 | 0 | 1 | 06/23/2025 | 06/23/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  | 8/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | QUINCY | 620708 | 02169 | 6 | Solar | 05_07_97W2 | 06/26/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 48 | 34 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 497564 | 02333 | 480 | Solar | 05_05_348W7 | 06/23/2023 | 09/18/2023 | 60 | 50 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/19/2023 | 10/10/2023 | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/23/2023 | 9/23/2027 | Y | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 177199 | 01604 | 3.8 | Solar | 05_07_797W23 | 02/01/2017 | 02/01/2017 | 2 | 2 | 0 | 02/03/2017 | 02/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2017 |  | 2/6/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/21/2017 | 8/21/2017 | 8/21/2017 | Connected |  | N
National Grid | NORTHAMPTON | 659756 | 01062 | 7.68 | Solar | 05_01_10J366 | 12/11/2024 | 01/13/2025 | 16 | 11 | 5 | 01/14/2025 | 01/14/2025 | 126 | 103 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 701270 | 02368 | 7.6 | Solar | 05_09_909W3 | 06/26/2025 | 07/11/2025 | 3 | 0 | 3 | 07/22/2025 | 07/22/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/26/2025 | 8/21/2026 | Y | EXP | 365 | 09/19/2025 | 09/18/2025 | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | EVERETT | 629620 | 02149 | 6.72 | Solar | 05_07_97W2 | 08/02/2024 | 08/13/2024 | 5 | 0 | 5 | 08/14/2024 | 08/14/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/02/2024 | 9/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | BRIDGEWATER | 591460 | 02333 | 1000 | Solar | 05_05_348W7 | 07/12/2024 | 08/28/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2024 | 09/04/2024 | 4 | 0 | 4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WORCESTER | 177198 | 01604 | 7.6 | Solar | 05_07_797W23 | 02/01/2017 | 02/01/2017 | 2 | 2 | 0 | 02/03/2017 | 02/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2017 |  | 2/6/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/23/2017 | 10/23/2017 | 10/23/2017 | Connected |  | N
National Grid | NORTHAMPTON | 661738 | 01062 | 7.68 | Solar | 05_01_10J366 | 12/20/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2025 | Connected |  | N
National Grid | RANDOLPH | 706628 | 02368 | 0 | Solar | 05_09_909W3 | 07/23/2025 | 07/28/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | EVERETT | 630217 | 02149 | 3.8 | Solar | 05_07_97W2 | 08/05/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | N
National Grid | BRIDGEWATER | 673792 | 02333 | 7.6 | Solar | 05_05_348W7 | 02/28/2025 | 03/26/2025 | 18 | 13 | 5 | 03/27/2025 | 03/27/2025 | 118 | 98 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 177515 | 01604 | 143.2 | Solar | 05_07_797W23 | 07/14/2016 | 07/14/2016 | 1 | 1 | 0 | 07/15/2016 | 07/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2016 | 07/14/2016 | 7/19/2017 | Y | EXP | 330 | 12/05/2016 | 01/05/2017 | 21 | 0 | 21 | 2/15/2017 | 2/15/2017 | 2/23/2017 | Connected |  | N
National Grid | WILLIAMSBURG | 175212 | 01096 | 0 | Natural Gas | 05_01_10J383 | 12/07/2012 | 12/07/2012 | 12 | 7 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2012 | 02/20/2013 | 32 | 0 | 32 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2013 |  | 8/30/2013 | N | STD | 55 |  |  | 0 | 0 | 0 | 10/24/2013 | 10/24/2013 | 10/24/2013 | Terminated |  | N
National Grid | RANDOLPH | 727168 | 02368 | 249 | Solar | 05_09_909W3 | 10/17/2025 | 11/10/2025 | 15 | 8 | 7 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 633443 | 02149 | 9.57 | Solar | 05_07_97W2 | 08/22/2024 | 10/03/2024 | 26 | 24 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  | 11/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N
National Grid | BRIDGEWATER | 686212 | 02333 | 500 | Solar | 05_05_348W7 | 05/28/2025 | 09/30/2025 | 85 | 76 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2025 |  | 124 | 25 | 99 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 177931 | 01604 | 7.6 | Solar | 05_07_797W23 | 04/20/2017 | 04/20/2017 | 7 | 7 | 0 | 05/01/2017 | 05/01/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2017 |  | 4/25/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 | 9/5/2017 | 9/5/2017 | 9/5/2017 | Connected |  | N
National Grid | GOSHEN | 688095 | 01032 | 3.2 | Solar | 05_01_10J383 | 06/26/2025 | 07/11/2025 | 2 | 0 | 2 | 07/18/2025 | 07/18/2025 | 30 | 18 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2025 | 06/26/2025 | 9/17/2026 | Y | EXP | 365 | 03/11/2026 | 03/24/2026 | 14 | 0 | 14 |  |  |  | Meter Installation |  | Y
National Grid | RANDOLPH | 726797 | 02368 | 12.6 | Solar | 05_09_909W3 | 10/15/2025 | 10/27/2025 | 12 | 7 | 5 | 11/25/2025 | 11/25/2025 | 70 | 50 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 639713 | 02038 | 2.32 | Solar | 05_07_97W2 | 09/12/2024 | 09/25/2024 | 1 | 0 | 1 | 09/26/2024 | 09/26/2024 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | BRIDGEWATER | 713187 | 02333 | 500 | Solar | 05_05_348W7 | 01/02/2026 | 03/11/2026 | 44 | 37 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/12/2026 |  | 15 | 0 | 15 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 178409 | 01605 | 10000 | Other | 05_07_797W23 | 11/22/2017 | 11/22/2017 | 89 | 82 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/2/2018 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 718163 | 01053 | 7.36 | Solar | 05_01_10J383 | 09/13/2025 | 09/29/2025 | 32 | 26 | 6 | 12/23/2025 | 12/23/2025 | 58 | 42 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2026 |  | 3/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 723531 | 02368 | 10 | Solar | 05_09_909W4 | 10/02/2025 | 10/09/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 1/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FRANKLIN | 641021 | 02038 | 7.6 | Solar | 05_07_97W2 | 10/07/2024 | 11/12/2024 | 15 | 10 | 5 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/07/2024 | 3/12/2026 | Y | EXP | 365 | 04/15/2025 | 04/29/2025 | 15 | 0 | 15 |  |  | 9/16/2025 | Connected |  | N
National Grid | BRIDGEWATER | 713322 | 02333 | 500 | Solar | 05_05_348W7 | 01/23/2026 |  | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WORCESTER | 178602 | 01605 | 500 | Solar | 05_07_797W23 | 04/06/2018 | 04/06/2018 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/07/2018 | 07/11/2018 | 50 | 11 | 39 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2019 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GOSHEN | 733762 | 01032 | 7.6 | Solar | 05_01_10J383 | 11/13/2025 | 12/11/2025 | 10 | 9 | 1 | 01/12/2026 | 01/12/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 737787 | 02368 | 7.6 | Solar | 05_09_909W4 | 12/03/2025 | 12/04/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 16 | 1 | 15 | 02/03/2026 | 03/02/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 03/02/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 3/4/2026 |  | 3/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | FRANKLIN | 646523 | 02038 | 10 | Solar | 05_07_97W2 | 10/18/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | BRIDGEWATER | 174333 | 02333 | 231 | Solar | 05_05_348W7 | 01/24/2012 | 01/24/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2012 |  | 2/13/2012 | N | EXP | 94 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 9/28/2012 | Connected |  | N
National Grid | WORCESTER | 178599 | 01605 | 72 | Solar | 05_07_797W23 | 04/06/2018 | 04/06/2018 | 1 | 0 | 1 | 04/10/2018 | 04/10/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2018 |  | 4/14/2019 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 12/18/2018 | Connected |  | N
National Grid | GOSHEN | 174271 | 01032 | 517 | Solar | 05_01_10J383 | 12/26/2011 | 12/26/2011 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 04/12/2012 | 06/22/2012 | 48 | 0 | 48 |  |  | 0 | 0 | 0 | 06/22/2012 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 5/16/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 740691 | 02368 | 10 | Solar | 05_09_909W4 | 12/16/2025 | 12/17/2025 | 4 | 0 | 4 | 01/22/2026 | 01/22/2026 | 20 | 6 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BELLINGHAM | 654919 | 02019 | 11.5 | Solar | 05_07_97W2 | 11/19/2024 | 11/25/2024 | 2 | 0 | 2 | 02/06/2025 | 02/06/2025 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | BRIDGEWATER | 175213 | 02333 | 266 | Solar | 05_05_348W7 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2014 | 07/31/2014 | 1/30/2015 | Y | EXP | 164 |  |  | 0 | 0 | 0 | 12/5/2014 | 12/5/2014 | 12/15/2014 | Connected |  | N
National Grid | WORCESTER | 186356 | 01604 | 15.2 | Solar | 05_07_797W23 | 08/22/2018 | 10/11/2018 | 9 | 9 | 0 | 10/12/2018 | 10/12/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 08/22/2018 | 8/20/2019 | Y | EXP | 308 | 05/10/2019 | 06/05/2019 | 26 | 0 | 26 |  |  | 8/8/2019 | Connected |  | N
National Grid | WILLIAMSBURG | 176344 | 01096 | 8.39 | Solar | 05_01_10J383 | 02/25/2015 | 02/25/2015 | 9 | 5 | 4 | 03/11/2015 | 03/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2015 |  | 7/31/2015 | N | EXP | 141 |  |  | 0 | 0 | 0 | 3/12/2015 | 3/12/2015 | 1/13/2016 | Connected |  | N
National Grid | RANDOLPH | 742723 | 02368 | 120 | Solar | 05_09_909W4 | 12/31/2025 | 02/20/2026 | 33 | 23 | 10 |  |  | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | FRANKLIN | 669810 | 02038 | 2.03 | Solar | 05_07_97W2 | 02/04/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | BRIDGEWATER | 175503 | 02333 | 490 | Solar | 05_05_348W7 | 10/01/2014 | 10/01/2014 | 3 | 0 | 3 | 10/07/2014 | 10/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 10/01/2014 | 1/30/2015 | Y | EXP | 81 | 03/10/2015 | 03/17/2015 | 5 | 0 | 5 | 2/6/2015 | 2/6/2015 | 3/19/2015 | Connected |  | N
National Grid | WORCESTER | 273621 | 01604 | 7.6 | Solar | 05_07_797W23 | 01/28/2020 | 02/04/2020 | 5 | 5 | 0 | 02/05/2020 | 02/05/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2020 |  | 1/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2020 | Connected |  | N
National Grid | WILLIAMSBURG | 176587 | 01096 | 6 | Solar | 05_01_10J383 | 04/08/2016 | 04/08/2016 | 2 | 2 | 0 | 04/13/2016 | 04/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/08/2016 | 4/16/2017 | Y | EXP | 355 | 09/14/2016 | 10/03/2016 | 13 | 0 | 13 | 10/19/2016 | 10/19/2016 | 10/19/2016 | Connected |  | N
National Grid | RANDOLPH | 745251 | 02368 | 10 | Solar | 05_09_909W4 | 01/14/2026 | 01/15/2026 | 3 | 1 | 2 | 01/29/2026 | 01/29/2026 | 44 | 34 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FRANKLIN | 674265 | 02038 | 11.4 | Solar | 05_07_97W2 | 02/26/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | BRIDGEWATER | 175592 | 02333 | 266 | Solar | 05_05_348W7 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2014 |  | 10/31/2014 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 300143 | 01604 | 9.8 | Solar | 05_07_797W23 | 09/16/2020 | 09/21/2020 | 2 | 0 | 2 | 09/22/2020 | 09/22/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 | 09/16/2020 | 1/13/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2021 | Connected |  | N
National Grid | NORTHAMPTON | 177001 | 01062 | 52.25 | Solar | 05_01_10J383 | 07/21/2016 | 07/21/2016 | 4 | 4 | 0 | 07/26/2016 | 07/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2016 | 07/21/2016 | 7/26/2017 | Y | EXP | 320 | 04/05/2017 | 04/19/2017 | 9 | 0 | 9 | 6/8/2017 | 6/8/2017 | 6/8/2017 | Connected |  | N
National Grid | RANDOLPH | 174670 | 02368 | 200 | Natural Gas | 05_09_909W4 | 06/06/2013 | 06/06/2013 | 23 | 22 | 1 | 07/12/2013 | 07/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2013 |  | 11/29/2013 | N | EXP | 121 |  |  | 0 | 0 | 0 | 11/24/2015 | 11/24/2015 | 11/24/2015 | Connected |  | N
National Grid | FRANKLIN | 697060 | 02038 | 7.6 | Solar | 05_07_97W2 | 07/10/2025 | 07/16/2025 | 4 | 0 | 4 | 07/17/2025 | 07/17/2025 | 67 | 55 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 177561 | 02333 | 10 | Solar | 05_05_348W7 | 07/13/2017 | 07/13/2017 | 11 | 11 | 0 | 07/31/2017 | 07/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2017 | 07/13/2017 | 7/19/2018 | Y | EXP | 352 |  |  | 0 | 0 | 0 | 1/12/2018 | 1/12/2018 | 1/19/2018 | Connected |  | N
National Grid | WORCESTER | 330658 | 01604 | 10 | Solar | 05_07_797W23 | 12/09/2020 | 01/07/2021 | 19 | 14 | 5 | 01/08/2021 | 01/08/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 1/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2021 | Connected |  | N
National Grid | NORTHAMPTON | 177437 | 01062 | 8.6 | Solar | 05_01_10J383 | 06/30/2016 | 06/30/2016 | 2 | 2 | 0 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2016 | 06/30/2016 | 7/6/2017 | Y | EXP | 353 | 11/10/2016 | 12/02/2016 | 14 | 0 | 14 | 12/20/2016 | 12/20/2016 | 12/20/2016 | Connected |  | N
National Grid | RANDOLPH | 175909 | 02368 | 20 | Solar | 05_09_909W4 | 03/10/2015 | 03/10/2015 | 4 | 0 | 4 | 03/18/2015 | 03/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2015 |  | 7/31/2015 | N | EXP | 134 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 7/23/2015 | Connected |  | N
National Grid | FRANKLIN | 710397 | 02038 | 10 | Solar | 05_07_97W2 | 08/07/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 51 | 25 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 177864 | 02333 | 60 | Solar | 05_05_348W7 | 06/14/2017 | 06/14/2017 | 18 | 17 | 1 | 07/11/2017 | 07/11/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2017 |  | 6/19/2018 | N | EXP | 337 |  |  | 0 | 0 | 0 | 9/7/2017 | 9/7/2017 | 9/14/2017 | Connected |  | N
National Grid | WORCESTER | 340873 | 01604 | 15.2 | Solar | 05_07_797W23 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2021 | 02/05/2021 | 8/9/2023 | Y | EXP | 365 | 06/03/2022 | 06/28/2022 | 25 | 0 | 25 |  |  | 9/30/2022 | Connected |  | N
National Grid | NORTHAMPTON | 177683 | 01062 | 488 | Solar | 05_01_10J383 | 09/29/2017 | 09/29/2017 | 36 | 30 | 6 | 11/30/2017 | 11/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2018 |  | 10/23/2020 | N | EXP | 952 | 01/29/2020 | 04/16/2020 | 78 | 0 | 78 |  |  | 10/23/2020 | Connected |  | N
National Grid | RANDOLPH | 176099 | 02368 | 300 | Solar | 05_09_909W4 | 04/10/2015 | 04/10/2015 | 3 | 3 | 0 | 04/16/2015 | 04/16/2015 | 317 | 0 | 317 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 |  | 9/11/2015 | N | EXP | 143 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 712286 | 02038 | 3.8 | Solar | 05_07_97W2 | 08/14/2025 | 09/05/2025 | 2 | 0 | 2 | 09/11/2025 | 09/11/2025 | 43 | 29 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2025 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 184555 | 02333 | 990 | Solar | 05_05_348W7 | 05/09/2018 | 05/09/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2018 | 07/27/2018 | 23 | 2 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  | 9/4/2020 | N | STD | 560 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 485389 | 01604 | 7.6 | Solar | 05_07_797W23 | 12/29/2022 | 01/03/2023 | 2 | 0 | 2 | 01/04/2023 | 01/04/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 177950 | 01062 | 3.8 | Solar | 05_01_10J383 | 08/23/2017 | 08/23/2017 | 9 | 9 | 0 | 09/07/2017 | 09/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2017 |  | 8/24/2018 | N | EXP | 347 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/14/2017 | Connected |  | N
National Grid | RANDOLPH | 176611 | 02368 | 488 | Solar | 05_09_909W4 | 02/12/2016 | 02/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2016 | 03/11/2016 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/20/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 715435 | 02038 | 10.15 | Solar | 05_07_97W2 | 08/28/2025 | 09/26/2025 | 3 | 0 | 3 | 09/29/2025 | 09/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 | 08/28/2025 | 11/3/2026 | Y | EXP | 365 | 12/24/2025 | 01/06/2026 | 14 | 0 | 14 |  |  | 1/8/2026 | Connected |  | N
National Grid | EAST BRIDGEWATER | 184559 | 02333 | 990 | Solar | 05_05_348W7 | 05/09/2018 | 05/09/2018 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2018 | 07/27/2018 | 23 | 2 | 21 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  | 9/4/2020 | N | STD | 560 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 491623 | 01604 | 7.6 | Solar | 05_07_797W23 | 05/01/2023 | 05/02/2023 | 1 | 0 | 1 | 05/03/2023 | 05/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | NORTHAMPTON | 495040 | 01062 | 3.8 | Solar | 05_01_10J383 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2023 | Connected |  | N
National Grid | RANDOLPH | 176610 | 02368 | 2355 | Solar | 05_09_909W4 | 02/12/2016 | 02/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2016 | 03/11/2016 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2016 | 02/12/2016 | 10/31/2017 | Y | STD | 419 | 08/23/2017 | 10/12/2017 | 34 | 0 | 34 | 10/26/2017 | 10/26/2017 | 11/9/2017 | Connected |  | N
National Grid | FRANKLIN | 715083 | 02038 | 7.6 | Solar | 05_07_97W3 | 08/28/2025 | 09/23/2025 | 1 | 0 | 1 | 10/02/2025 | 10/02/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 08/28/2025 | 2/7/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | BRIDGEWATER | 185866 | 02333 | 4990 | Solar | 05_05_348W7 | 05/24/2018 | 05/24/2018 | 21 | 17 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2018 | 07/23/2018 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2019 | 05/24/2018 | 12/2/2023 | Y | STD | 547 | 08/12/2022 | 12/16/2022 | 127 | 1 | 126 |  |  | 12/29/2023 | Connected |  | N
National Grid | WORCESTER | 563367 | 01604 | 4980 | Solar | 05_07_797W23 | 02/28/2024 | 04/11/2024 | 32 | 22 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2024 | 04/24/2024 | 8 | 0 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 517558 | 01053 | 10 | Solar | 05_01_10J383 | 06/22/2023 | 04/26/2023 | 3 | 0 | 3 | 06/28/2023 | 06/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 176633 | 02368 | 528 | Solar | 05_09_909W4 | 10/16/2015 | 10/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2015 | 11/13/2015 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2016 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 714211 | 02019 | 5.76 | Solar | 05_07_97W3 | 08/22/2025 | 10/03/2025 | 3 | 0 | 3 | 10/28/2025 | 10/28/2025 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BRIDGEWATER | 202003 | 02333 | 7490 | Solar | 05_05_348W7 | 12/28/2018 | 08/26/2019 | 166 | 26 | 140 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2019 | 10/14/2019 | 33 | 16 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 572096 | 01604 | 13.05 | Solar | 05_07_797W23 | 01/22/2024 | 01/29/2024 | 6 | 4 | 2 | 01/30/2024 | 01/30/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 520774 | 01062 | 6 | Solar | 05_01_10J383 | 05/03/2023 | 05/05/2023 | 2 | 0 | 2 | 05/08/2023 | 05/08/2023 | 108 | 25 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 178174 | 02368 | 7.6 | Solar | 05_09_909W4 | 03/23/2018 | 03/23/2018 | 5 | 0 | 5 | 04/02/2018 | 04/02/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2018 |  | 3/31/2019 | N | EXP | 327 |  |  | 0 | 0 | 0 |  |  | 10/30/2019 | Connected |  | N
National Grid | FRANKLIN | 725687 | 02038 | 18.56 | Solar | 05_07_97W3 | 10/10/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BRIDGEWATER | 246153 | 02333 | 20 | Solar | 05_05_348W7 | 08/05/2019 | 08/09/2019 | 3 | 0 | 3 | 08/12/2019 | 08/12/2019 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 9/16/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | WORCESTER | 586841 | 01604 | 15.2 | Solar | 05_07_797W23 | 01/31/2024 | 02/26/2024 | 17 | 15 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  | 3/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2024 | Connected |  | N
National Grid | NORTHAMPTON | 551311 | 01062 | 4.93 | Solar | 05_01_10J383 | 08/28/2023 | 08/30/2023 | 3 | 2 | 1 | 08/31/2023 | 08/31/2023 | 42 | 20 | 22 | 11/07/2023 | 01/05/2024 | 40 | 3 | 37 |  |  | 0 | 0 | 0 | 01/05/2024 | 40 | 3 | 37 |  |  | 0 | 0 | 0 | 1/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 178385 | 02368 | 3.8 | Solar | 05_09_909W4 | 01/15/2018 | 01/15/2018 | 27 | 27 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 |  | 1/21/2019 | N | EXP | 214 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 731036 | 02038 | 7.6 | Solar | 05_07_97W3 | 11/03/2025 | 11/04/2025 | 3 | 0 | 3 | 12/09/2025 | 12/09/2025 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | EAST BRIDGEWATER | 273152 | 02333 | 27.6 | Solar | 05_05_348W7 | 01/14/2020 | 01/17/2020 | 3 | 3 | 0 | 01/21/2020 | 01/21/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2020 |  | 1/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2020 | Connected |  | N
National Grid | WORCESTER | 594128 | 01604 | 12.915 | Solar | 05_07_797W23 | 03/21/2024 | 03/27/2024 | 4 | 2 | 2 | 03/28/2024 | 03/28/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | NORTHAMPTON | 553055 | 01062 | 10 | Solar | 05_01_10J383 | 09/07/2023 | 09/20/2023 | 9 | 7 | 2 | 09/21/2023 | 09/21/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 178658 | 02368 | 3564 | Solar | 05_09_909W4 | 02/05/2018 | 02/05/2018 | 21 | 21 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/08/2018 | 04/11/2018 | 24 | 4 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2018 | 02/05/2018 | 12/31/2020 | Y | STD | 773 | 05/08/2020 | 11/18/2020 | 195 | 5 | 190 | 11/20/2020 | 12/24/2020 | 12/31/2020 | Connected |  | N
National Grid | FRANKLIN | 739909 | 02038 | 11.5 | Solar | 05_07_97W3 | 12/12/2025 | 01/22/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BRIDGEWATER | 286629 | 02333 | 7.6 | Solar | 05_05_348W7 | 04/06/2020 | 04/09/2020 | 2 | 0 | 2 | 04/10/2020 | 04/10/2020 | 28 | 16 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 | 04/06/2020 | 4/3/2021 | Y | EXP | 365 | 07/28/2020 | 01/09/2021 | 165 | 5 | 160 |  |  | 1/14/2021 | Connected |  | N
National Grid | WORCESTER | 598158 | 01604 | 10 | Solar | 05_07_797W23 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2024 | Connected |  | N
National Grid | NORTHAMPTON | 569102 | 01062 | 10 | Solar | 05_01_10J383 | 11/14/2023 | 11/16/2023 | 2 | 0 | 2 | 11/17/2023 | 11/17/2023 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 178700 | 02368 | 4320 | Solar | 05_09_909W4 | 02/08/2018 | 04/09/2018 | 42 | 37 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2018 | 05/02/2018 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 | 02/08/2018 | 12/17/2019 | Y | STD | 294 | 09/11/2019 | 11/19/2019 | 69 | 0 | 69 |  |  | 12/20/2019 | Connected |  | N
National Grid | FRANKLIN | 745422 | 02038 | 11.4 | Solar | 05_07_97W3 | 01/14/2026 | 01/21/2026 | 4 | 0 | 4 | 01/22/2026 | 01/22/2026 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2026 |  | 3/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | EAST BRIDGEWATER | 301858 | 02333 | 10 | Solar | 05_05_348W7 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2020 |  | 7/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2020 | Connected |  | N
National Grid | WORCESTER | 597731 | 01604 | 10.44 | Solar | 05_07_797W23 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | NORTHAMPTON | 607705 | 01062 | 3.19 | Solar | 05_01_10J383 | 04/30/2024 | 05/06/2024 | 1 | 0 | 1 | 05/07/2024 | 05/07/2024 | 86 | 71 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 187299 | 02343 | 10 | Solar | 05_09_909W4 | 06/06/2018 | 06/06/2018 | 3 | 3 | 0 | 09/19/2018 | 09/19/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2018 | 06/06/2018 | 4/17/2019 | Y | EXP | 205 |  |  | 0 | 0 | 0 |  |  | 11/21/2018 | Connected |  | N
National Grid | FRANKLIN | 754577 | 02038 | 10 | Solar | 05_07_97W3 | 03/04/2026 | 03/06/2026 | 2 | 0 | 2 | 03/09/2026 | 03/09/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2026 |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | EAST BRIDGEWATER | 311913 | 02333 | 10 | Solar | 05_05_348W7 | 09/29/2020 | 10/02/2020 | 2 | 0 | 2 | 10/05/2020 | 10/05/2020 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 09/29/2020 | 3/10/2022 | Y | EXP | 365 | 06/09/2021 | 09/10/2021 | 92 | 3 | 89 |  |  | 12/1/2021 | Connected |  | N
National Grid | WORCESTER | 616189 | 01604 | 5.76 | Solar | 05_07_797W23 | 06/06/2024 | 06/25/2024 | 3 | 0 | 3 | 06/26/2024 | 06/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 | 06/06/2024 | 8/1/2025 | Y | EXP | 365 | 09/03/2024 | 02/28/2025 | 179 | 0 | 179 |  |  | 2/28/2025 | Connected |  | N
National Grid | NORTHAMPTON | 607592 | 01062 | 4.225 | Solar | 05_01_10J383 | 05/08/2024 | 05/31/2024 | 6 | 5 | 1 | 06/03/2024 | 06/03/2024 | 51 | 38 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | HOLBROOK | 201270 | 02343 | 3 | Solar | 05_09_909W4 | 11/15/2018 | 12/19/2018 | 7 | 0 | 7 | 12/20/2018 | 12/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2019 | 11/15/2018 | 1/13/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2019 | Connected |  | N
National Grid | FRANKLIN | 753557 | 02038 | 7.6 | Solar | 05_07_97W3 | 02/27/2026 | 03/03/2026 | 4 | 0 | 4 | 04/01/2026 | 04/01/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BRIDGEWATER | 320922 | 02333 | 499.9 | Solar | 05_05_348W7 | 01/06/2021 | 02/19/2021 | 30 | 23 | 7 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 626085 | 01604 | 10 | Solar | 05_07_797W23 | 07/23/2024 | 08/07/2024 | 1 | 0 | 1 | 08/08/2024 | 08/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 8/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2024 | Connected |  | N
National Grid | NORTHAMPTON | 631126 | 01062 | 5.76 | Solar | 05_01_10J383 | 08/08/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 53 | 25 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 203430 | 02343 | 0 | Battery Add-On | 05_09_909W4 | 12/17/2018 | 01/19/2019 | 22 | 14 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2019 | 02/18/2019 | 18 | 0 | 18 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2019 | 12/17/2018 | 12/31/2020 | Y | STD | 365 | 05/08/2020 | 10/21/2020 | 167 | 5 | 162 |  |  | 12/23/2020 | Connected |  | N
National Grid | FRANKLIN | 755947 | 02038 | 20 | Solar | 05_07_97W3 | 03/11/2026 | 03/16/2026 | 3 | 0 | 3 | 03/17/2026 | 03/17/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BRIDGEWATER | 320921 | 02333 | 499.9 | Solar | 05_05_348W7 | 01/06/2021 | 02/19/2021 | 30 | 23 | 7 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 648326 | 01604 | 3.8 | Solar | 05_07_797W23 | 10/21/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | NORTHAMPTON | 641898 | 01060 | 5.76 | Solar | 05_01_10J383 | 11/06/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 40 | 17 | 23 | 01/30/2025 | 03/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 03/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/06/2024 | 4/12/2026 | Y | EXP | 365 | 04/03/2025 | 07/25/2025 | 114 | 0 | 114 |  |  | 9/10/2025 | Connected |  | Y
National Grid | RANDOLPH | 205909 | 02368 | 9.71 | Solar | 05_09_909W4 | 02/01/2019 | 02/13/2019 | 8 | 7 | 1 | 02/14/2019 | 02/14/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 754868 | 02038 | 10 | Solar | 05_07_97W3 | 03/05/2026 | 03/11/2026 | 3 | 1 | 2 | 03/26/2026 | 03/26/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BRIDGEWATER | 322917 | 02333 | 10 | Solar | 05_05_348W7 | 11/03/2020 | 11/05/2020 | 1 | 0 | 1 | 11/06/2020 | 11/06/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  | 11/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2021 | Connected |  | N
National Grid | WORCESTER | 648691 | 01604 | 10 | Solar | 05_07_797W23 | 11/04/2024 | 12/04/2024 | 16 | 11 | 5 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 648562 | 01062 | 5.76 | Solar | 05_01_10J383 | 10/21/2024 | 11/12/2024 | 4 | 0 | 4 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/21/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 234095 | 02343 | 10 | Solar | 05_09_909W4 | 07/01/2019 | 07/02/2019 | 0 | 0 | 0 | 07/03/2019 | 07/03/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2019 |  | 11/15/2019 | N | EXP | 129 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N
National Grid | FRANKLIN | 176628 | 02038 | 10 | Solar | 05_07_97W3 | 10/15/2015 | 10/15/2015 | 4 | 4 | 0 | 10/21/2015 | 10/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 |  | 10/20/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 8/18/2016 | Connected |  | N
National Grid | EAST BRIDGEWATER | 451936 | 02333 | 9.57 | Solar | 05_05_348W7 | 08/18/2022 | 08/22/2022 | 2 | 0 | 2 | 08/23/2022 | 08/23/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2022 | 08/18/2022 | 1/18/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2023 | Connected |  | N
National Grid | WORCESTER | 650281 | 01604 | 10 | Solar | 05_07_797W23 | 10/30/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | NORTHAMPTON | 688082 | 01062 | 7.475 | Solar | 05_01_10J383 | 04/28/2025 | 05/13/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2025 | Connected |  | Y
National Grid | RANDOLPH | 260373 | 02368 | 8.41 | Solar | 05_09_909W4 | 10/29/2019 | 11/05/2019 | 4 | 0 | 4 | 11/06/2019 | 11/06/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 | 10/29/2019 | 10/29/2020 | Y | EXP | 365 | 05/16/2020 | 05/15/2020 | 0 | 0 | 0 |  |  | 5/21/2020 | Connected |  | N
National Grid | FRANKLIN | 176652 | 02038 | 6 | Solar | 05_07_97W3 | 02/17/2016 | 02/17/2016 | 2 | 2 | 0 | 02/22/2016 | 02/22/2016 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2016 | 02/17/2016 | 9/26/2019 | Y | EXP | 1274 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 396718 | 02333 | 996 | Solar | 05_05_348W7 | 01/29/2022 | 03/08/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2022 | 03/09/2022 | 1 | 0 | 1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 655063 | 01604 | 10 | Solar | 05_07_797W23 | 11/18/2024 | 12/09/2024 | 2 | 0 | 2 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/18/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | NORTHAMPTON | 722399 | 01062 | 13.3 | Solar | 05_01_11J330 | 09/26/2025 | 10/15/2025 | 1 | 0 | 1 | 10/17/2025 | 10/17/2025 | 0 | 0 | 0 | 03/19/2026 |  | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | RANDOLPH | 265140 | 02368 | 0 | Solar | 05_09_909W4 | 11/24/2019 | 12/03/2019 | 5 | 0 | 5 | 12/04/2019 | 12/04/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2020 |  | 11/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2020 | Connected |  | N
National Grid | FRANKLIN | 176647 | 02038 | 1260 | Solar | 05_07_97W3 | 02/17/2016 | 02/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/18/2016 | 03/08/2016 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/23/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 411046 | 02333 | 0 | Other | 05_05_348W7 | 03/30/2022 | 04/13/2022 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/14/2022 | 05/12/2022 | 20 | 0 | 20 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 677765 | 01604 | 11.5 | Solar | 05_07_797W23 | 03/13/2025 | 03/18/2025 | 3 | 0 | 3 | 03/19/2025 | 03/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  | 6/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2025 | Connected |  | N
National Grid | NORTHAMPTON | 177844 | 01062 | 17.6 | Solar | 05_01_11J330 | 10/17/2017 | 10/17/2017 | 53 | 53 | 0 | 01/17/2018 | 01/17/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2018 |  | 10/24/2018 | N | EXP | 279 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 284382 | 02368 | 10 | Solar | 05_09_909W4 | 03/26/2020 | 04/08/2020 | 8 | 8 | 0 | 04/09/2020 | 04/09/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2020 |  | 4/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2020 | Connected |  | N
National Grid | FRANKLIN | 176646 | 02038 | 1988 | Solar | 05_07_97W3 | 02/17/2016 | 02/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/18/2016 | 03/08/2016 | 13 | 0 | 13 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/23/2017 | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 540635 | 02333 | 10.44 | Solar | 05_05_348W7 | 08/07/2023 | 08/30/2023 | 18 | 17 | 1 | 08/31/2023 | 08/31/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 | 08/07/2023 | 10/17/2024 | Y | EXP | 365 | 11/02/2023 | 11/29/2023 | 28 | 0 | 28 |  |  | 4/26/2024 | Connected |  | N
National Grid | WORCESTER | 684009 | 01604 | 19.76 | Solar | 05_07_797W23 | 04/09/2025 | 04/15/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | NORTHAMPTON | 646198 | 01062 | 3.8 | Solar | 05_01_11J330 | 10/10/2024 | 02/17/2025 | 83 | 83 | 0 | 02/18/2025 | 02/18/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 287922 | 02368 | 2.4 | Solar | 05_09_909W4 | 05/29/2020 | 06/01/2020 | 0 | 0 | 0 | 06/02/2020 | 06/02/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/29/2020 | 6/1/2021 | Y | EXP | 365 | 10/08/2020 | 10/21/2020 | 13 | 0 | 13 |  |  | 11/10/2020 | Connected |  | N
National Grid | FRANKLIN | 176991 | 02038 | 3.8 | Solar | 05_07_97W3 | 03/13/2017 | 03/13/2017 | 9 | 7 | 2 | 03/28/2017 | 03/28/2017 | 251 | 0 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 |  | 3/20/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 624449 | 02333 | 13.53 | Solar | 05_05_348W7 | 11/27/2024 | 01/09/2025 | 27 | 25 | 2 | 01/10/2025 | 01/10/2025 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | WORCESTER | 709116 | 01604 | 3.8 | Solar | 05_07_797W23 | 08/11/2025 | 09/02/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | NORTHAMPTON | 652361 | 01062 | 9.12 | Solar | 05_01_11J330 | 11/05/2024 | 11/25/2024 | 7 | 5 | 2 | 11/26/2024 | 11/26/2024 | 71 | 47 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 11/05/2024 | 4/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2025 | Connected |  | N
National Grid | HOLBROOK | 303203 | 02343 | 9.12 | Solar | 05_09_909W4 | 08/05/2020 | 08/11/2020 | 3 | 0 | 3 | 08/12/2020 | 08/12/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/05/2020 | 5/3/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2021 | Connected |  | N
National Grid | BELLINGHAM | 177328 | 02019 | 15.2 | Solar | 05_07_97W3 | 06/20/2016 | 06/20/2016 | 2 | 2 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/26/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 10/12/2016 | 10/12/2016 | 10/17/2016 | Connected |  | N
National Grid | BRIDGEWATER | 634679 | 02333 | 0 | Solar | 05_05_348W7 | 08/23/2024 |  | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 719830 | 01604 | 10 | Solar | 05_07_797W23 | 09/18/2025 | 09/22/2025 | 2 | 0 | 2 | 09/23/2025 | 09/23/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 655535 | 01062 | 7.6 | Solar | 05_01_11J330 | 11/19/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 325868 | 02368 | 15.2 | Solar | 05_09_909W4 | 11/13/2020 | 11/17/2020 | 1 | 0 | 1 | 11/18/2020 | 11/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/13/2020 | 12/12/2022 | Y | EXP | 365 | 03/06/2021 | 04/06/2021 | 31 | 0 | 31 |  |  | 3/8/2022 | Connected |  | N
National Grid | FRANKLIN | 177626 | 02038 | 10 | Solar | 05_07_97W3 | 05/23/2017 | 05/23/2017 | 3 | 3 | 0 | 05/30/2017 | 05/30/2017 | 208 | 0 | 208 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 |  | 5/29/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 676078 | 02333 | 3.8 | Solar | 05_05_348W7 | 03/06/2025 | 03/18/2025 | 8 | 4 | 4 | 03/19/2025 | 03/19/2025 | 29 | 7 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | WORCESTER | 651763 | 01605 | 3.8 | Solar | 05_07_797W24 | 11/13/2024 | 02/19/2025 | 2 | 0 | 2 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | NORTHAMPTON | 175077 | 01062 | 35 | Solar | 05_01_11J331 | 09/24/2013 | 09/24/2013 | 4 | 0 | 4 | 10/02/2013 | 10/02/2013 | 818 | 0 | 818 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2013 | 09/24/2013 | 7/31/2016 | Y | EXP | 991 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 330696 | 02343 | 7.6 | Solar | 05_09_909W4 | 12/09/2020 | 12/17/2020 | 5 | 0 | 5 | 12/18/2020 | 12/18/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 |  | 3/6/2022 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 177813 | 02038 | 7.6 | Solar | 05_07_97W3 | 03/31/2017 | 03/31/2017 | 5 | 2 | 3 | 04/07/2017 | 04/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 4/5/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 | 12/15/2017 | 12/15/2017 | 12/15/2017 | Connected |  | N
National Grid | BRIDGEWATER | 418278 | 02333 | 2000 | Solar | 05_01_2236W3 | 02/17/2023 | 07/13/2023 | 98 | 88 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2023 | 08/07/2023 | 17 | 0 | 17 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 680245 | 01605 | 11.5 | Solar | 05_07_797W24 | 03/25/2025 | 06/16/2025 | 15 | 11 | 4 | 06/17/2025 | 06/17/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 587958 | 01062 | 825 | Natural Gas | 05_01_11J331 | 03/07/2024 |  | 179 | 170 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 354333 | 02343 | 10 | Solar | 05_09_909W4 | 04/23/2021 | 04/26/2021 | 0 | 0 | 0 | 04/27/2021 | 04/27/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2021 | Connected |  | N
National Grid | BELLINGHAM | 178683 | 02019 | 149.4 | Solar | 05_07_97W3 | 12/18/2017 | 12/18/2017 | 49 | 41 | 8 | 03/12/2018 | 03/12/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2018 |  | 6/30/2020 | N | EXP | 285 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 177671 | 02333 | 2000 | Solar | 05_01_2236W3 | 05/25/2017 | 06/02/2017 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2017 | 06/29/2017 | 19 | 3 | 16 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 0 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N