**JDAI Massachusetts**

**Strategic Plan 2016-2018 Goals**

**90-180 Day Actions**

Goal 1: Reduce Detention Rates of Low-Risk Youth, Advisor Commissioner Peter Forbes

* Complete ATD bench cards for all six Counties. Distribute to local stakeholders and train on use. (By March 2016)
* Complete study within Probation on overnight arrest data with Ph.D student to support.
* Training DCF Management Team on JDAI principles and seek participation on committee work as appropriate.
* Redesign Data Dashboard to reflect Strategic Plan goals.
* Open Western Region Reception Center as DYS alternative.

Goal 2: Identify Opportunities to Reduce Lengths of Stay in Detention through Case Processing Reforms, Advisor Rachel Wallack

* Engage local leadership on challenges with length of stay (LOS) through the completion survey regarding local practices.
* Create a Master Diagram of flow of cases in the juvenile court, at the state level.
* Conduct data analysis on length of stay by DPI, GRID, offense, race/ethnicity, gender, age, county and DCF-involvement to determine what is driving the LOS up.

Goal 3: Reduce Racial and Ethnic Disparities, Advisor Crystal Collier

* Train all juvenile probation officers on the collection of race and ethnicity data using self-report. (June 2016)
* Offer further implicit bias training with Kimberly Papillion (May 2016)
* Role out RED Training video in June 2016.
* Strengthen relationship with Municipal Police Training Academy.

Goal 4: Replicate JDAI with Fidelity at the Local Level, Advisor Glenn Daly

* Hire Detention Reform Specialist to support the six JDAI counties. (May 2016)
* Begin County Level System Assessments.