## Slide 1
Justice Reinvestment Policy Oversight Board
Cross-Tracking Initiative Update
04/04/22
Executive Office of Public Safety and Security
Executive Office of Technology Services and Security

## Slide 2
Commonwealth Direction
(What we will accomplish)
We will improve the criminal justice system by enhancing the integrity, accuracy, consistency, and transparency of information.
Strategic Focus Areas
(How we will get there)
Common Data Definitions
Governance Framework
Cross-Agency Data Sharing
A common data language to support consistent data definitions
Execution Oversight
Defined interagency roles, responsibilities, accountabilities, and processes
Requirements for the integration and development of supporting technology
Processes and procedures to operationalize and oversee target state implementation
Outcomes
(Where we are going)
Data provide insights into agency performance to understand how to improve operations
Analyze Disparities and Evaluate Effectiveness of Reform Programs
Enable Studies of Recidivism and Other Criminal Justice Research
Drive Operational Efficiency and Effectiveness
Increase Criminal Justice Data Availability, Quality, and Trust
Criminal justice data can be consistently and securely shared and reused
Data support understanding racial disparities and the success of reform programs
Data support criminal justice reform studies more intuitively and through easier access
Enable Linkages of Individual Records Across the Criminal Justice System
Individuals are tracked consistently throughout the entire criminal justice System
Empower Data-Driven Decision Making and Monitoring
Data support key decisions for policies and budgeting
Key Capabilities
(What We Need to Put in Place)
Data
Governance
Process
People / Org.
Technology
Unique ID

## Slide 3: Executing Major Milestones to Build to Cross-Tracking
Maintaining Support and Expanding Participation
There is continued sustained support from members of the cross-jurisdictional Executive Steering Committee (ESC)* to guide program progress
Upcoming outreach and meetings will include representatives from DAs and AGO to broaden understanding and participation
Developing the Cross-Tracking Platform
A cross-agency Commonwealth team in place to support platform development
The vendor and Commonwealth teams have established a cadence and working toward initial design
* Note: The Appendix contains the project governance structure.
Continuing to Develop Standards to Improve Data Quality
Completing training for sheriffs for new OMS upgrade and associated reporting criteria
The law enforcement (local and state PD) is developing an SOP to standardize data collection and reviewing system requirements to support

## Slide 4: Workstream Focus Areas
Sheriffs and DOC
DOC developing metrics to capture progress with the regulations
Sheriffs training to begin in April
OMS upgrade delivered on March 31 for testing
Next step: OMS upgrade user testing and production roll out by county
Trial Court/Probation
Conducting current state analysis
Participation in ESC and OBTN workshop
Next steps: Roadmap to accelerate digitization of the Court
Law Enforcement
Completed current state assessment
Developing and validating SOP
Next steps: Finalize SOP
Data Analytics Platform*
Assembled a Data Strike Team to represent respective Agencies and functions for platform development
Initial environment established
Next steps: Phase 1 public dashboard deployment
* Note: The next slide contains additional details.

## Slide 5: Data Analytics Platform Updates and Next Steps
Immediate Next Steps
Network connectivity for all edge sites Data ingestion Testing initial ingests Initial dashboard testing and validation Custodial agency public-facing dashboards
Completed Activities
20 Agencies signed Data Use License Agreement Vendor SOWs complete with Google and SpringML to build and populate the platform Vendor On Boarding: CJIS compliance and training Readiness sessions with all sheriffs, DOC, Trial Court, and MSP Continued development of technical environment Data staging Google Cloud Platform establishment

## Slide 6
Appendix

## Slide 7: Project Governance
Executive Steering Committee
(EOTSS, EOPSS, DOC, Sheriffs, DCJIS, Trial Courts, Probation)
Weekly meetings
Workstream Management
(Workstream Owners)
Weekly meetings
Project Management
(Gartner, EOTSS and EOPSS)
Weekly meetings
Data Analytics Platform
DOC and Sheriffs
Project Manager
Set touchpoints as needed
Law Enforcement
Trial Court