## Notes and Resources
Workbook Overview
Last updated:
2025-07-24
Purpose
This workbook is intended to be a central location for keeping track of dates for GMAC and related activities.
It is intended to contain the master list of dates, which will be kept updated and can be referenced to update other summaries/ materials, such as the GMAC website.
Calendar tab
This tab displays key meetings and processes for the GMAC and related actvities
Users can toggle between Weekly, Monthly, or Quarterly views by selecting a drop-down in cell C2.
Resources
Useful Links
| GMAC website | Grid Modernization Advisory Council (GMAC) ¦ Mass.gov
| LTSPP website | LTSPP Stakeholder Group
| DPU file room | ByNumber
Docket numbers
| Number | Description
| 24-10 | Eversource ESMP
| 24-11 | National Grid ESMP
| 24-12 | Unitil ESMP

## Calendar
NOTE: DO NOT DRAG FORMULAS DOWN; FORMULAS ARE NOT THE SAME FOR ALL ROWS
View Selection >> | Monthly
|  |  |  | 2025 | [5 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030 | [11 empty] | 2031 | [11 empty] | 2032 | [11 empty] | 2033 | [11 empty] | 2034 | [11 empty] | 2035 | [11 empty] | 2036 | [11 empty] | 2037 | [11 empty] | 2038 | [11 empty] | 2039 | [11 empty] | 2040 | [11 empty] | 2041 | [11 empty] | 2042 | [11 empty] | 2043
|  |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3
| START DATE | END DATE | time axis 2025-07-28 to 2043-08-01
|  |  | Description | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2032 | 2032 | 2032 | 2032 | 2032 | 2032 | 2032 | 2032 | 2032 | 2032 | 2032 | 2032 | 2033 | 2033 | 2033 | 2033 | 2033 | 2033 | 2033 | 2033 | 2033 | 2033 | 2033 | 2033 | 2034 | 2034 | 2034 | 2034 | 2034 | 2034 | 2034 | 2034 | 2034 | 2034 | 2034 | 2034 | 2035 | 2035 | 2035 | 2035 | 2035 | 2035 | 2035 | 2035 | 2035 | 2035 | 2035 | 2035 | 2036 | 2036 | 2036 | 2036 | 2036 | 2036 | 2036 | 2036 | 2036 | 2036 | 2036 | 2036 | 2037 | 2037 | 2037 | 2037 | 2037 | 2037 | 2037 | 2037 | 2037 | 2037 | 2037 | 2037 | 2038 | 2038 | 2038 | 2038 | 2038 | 2038 | 2038 | 2038 | 2038 | 2038 | 2038 | 2038 | 2039 | 2039 | 2039 | 2039 | 2039 | 2039 | 2039 | 2039 | 2039 | 2039 | 2039 | 2039 | 2040 | 2040 | 2040 | 2040 | 2040 | 2040 | 2040 | 2040 | 2040 | 2040 | 2040 | 2040 | 2041 | 2041 | 2041 | 2041 | 2041 | 2041 | 2041 | 2041 | 2041 | 2041 | 2041 | 2041 | 2042 | 2042 | 2042 | 2042 | 2042 | 2042 | 2042 | 2042 | 2042 | 2042 | 2042 | 2042 | 2043 | 2043 | 2043 | 2043 | 2043 | 2043 | 2043 | 2043
GMAC | 2025-02-27 | 2026-01-08 | bar: 2025-07-28 to 2026-01-01
placeholder
GMAC Meetings | Monthly | Monthly | GMAC meetings 4th Thursday of every month 1-3PM | bar: 2025-07-28 to 2025-10-01; 2025-12-01 to 2026-01-01
Feb 2025 meeting | 2025-02-27 | 2025-02-27 | Reporting: existing reports, ESMP metrics
March 2025 meeting | 2025-03-27 | 2025-03-27 | Reporting: ESMP metrics, biannual report content
April 2025 meeting | 2025-05-01 | 2025-05-01 | System Reliability
May 2025 meeting | 2025-05-29 | 2025-05-29 | Proactive Grid Planning (LTSPP Updates)
June 2025 meeting | 2025-06-29 | 2025-06-29 | Integrated Energy Planning (NPA)
July 2025 meeting | 2025-07-31 | 2025-07-31 | Equity in Grid Planning | bar: 2025-07-28
Aug 2025 meeting | 2025-08-28 | 2025-08-28 | System Resilience | bar: 2025-08-01
Sept 2025 meeting | 2025-09-18 | 2025-09-18 | Strategic Planning | bar: 2025-09-01
Oct 2025 meeting | 2025-10-30 | 2025-10-30 | Biannual Reports | bar: 2025-10-01
Nov 2025 meeting | None |  | Skip
Dec 2025 meeting | 2025-12-04 | 2025-12-04 | Integrated Energy Planning (CCP) | bar: 2025-12-01
Jan 2026 meeting | 2026-01-08 | 2026-01-08 | Topic TBD | bar: 2026-01-01
Excom Meetings | Bi-monthly | Bi-monthly | ExCom meetings on Thursdays 9:30-10:30 every other month | bar: 2025-08-01; 2025-10-01; 2025-12-01
April 2025 meeting | 2025-04-24 | 2025-04-24
June 2025 meeting | 2025-06-05 | 2025-06-05
Aug 2025 meeting | 2025-08-14 | 2025-08-14 | bar: 2025-08-01
Oct 2025 meeting | 2025-10-09 | 2025-10-09 | bar: 2025-10-01
Dec 2025 meeting | 2025-12-18 | 2025-12-18 | bar: 2025-12-01
EWG meetings | Quarterly | Quarterly | EWG meetings 10-11:30 AM | bar: 2025-10-01
March 2025 meeting | 2025-03-28 | 2025-03-28
July 2025 meeting | 2025-07-17 | 2025-07-17
Oct 2025 meeting | 2025-10-10 | 2025-10-10 | bar: 2025-10-01
GMAC Stakeholder Sessions | 2025-07-19 | 2025-11-01 | GMAC stakeholder sessions | bar: 2025-11-01
Stakeholder Session #1 | 2025-07-19 | 2025-07-19 | Future Grid from a Municipal Lens
Stakeholder Session #2 | 2025-11-01 | 2025-11-01 | Topic TBD -Dates are placeholders | bar: 2025-11-01
ESMP Phase II (Mertrics & Reporting) | 2025-03-18 | 2025-07-30 | ESMP Phase II (Mertrics & Reporting) | bar: 2025-07-28
EDC proposals due | 2025-03-18 | 2025-03-18 | The Companies shall confer and jointly propose initial ESMP metrics and reporting templates for the September 2025 and March 2026 biannual reports consistent with the Department’s directives
Intervenor comments and proposed metrics due | 2025-04-17 | 2025-04-17
EDC reply comments due | 2025-05-15 | 2025-05-15
Discovery opens on Companies ESMP metrics and reporting proposals | 2025-05-16 | 2025-05-16
Discovery closes | 2025-06-25 | 2025-06-25
Updated discovery logs due | 2025-07-11 | 2025-07-11
Intervenors may submit additional comments | 2025-07-16 | 2025-07-16
Companies may submit additional reply comments | 2025-07-30 | 2025-07-30 | bar: 2025-07-28
Long-Term System Planning Process (LTSPP) | 2025-05-09 | 2025-07-27 | Long-Term System Planning Program
EDC Final Report due to DPU | 2025-05-09 | 2025-05-09 | Extended from original date of 4/4/25
Public Hearing | 2025-07-01 | 2025-07-01
Public comments due | 2025-07-01 | 2025-07-01
Petition to intervene (DPU 25-20) | 2025-07-27 | 2025-07-27
Current ESMPs | 2025-07-01 | 2030-06-30 | D.P.U. 24-10/D.P.U. 24-11/D.P.U. 24-12 | bar: 2025-07-28 to 2030-06-01
ESMP Term | 2025-07-01 | 2030-06-30 | First 5-year ESMP term | bar: 2025-07-28 to 2030-06-01
Biannnual ESMP report due | 2025-09-30 | 2025-09-30 | First EDC biannual report due to DPU | bar: 2025-09-01
Biannnual ESMP report due | 2026-03-31 | 2026-03-31 | Second EDC biannual report due to DPU | bar: 2026-03-01
EDC informative comments on innovative approaches to ESMP cost recovery through base rates due | 2025-09-10 | 2025-09-10 | bar: 2025-09-01
Intervenor informative comments on innovative approaches to ESMP cost recovery through base rates due | 2025-10-08 | 2025-10-08
Reply comments due | 2025-11-05 | 2025-11-05 | bar: 2025-11-01
CESAG | 2025-03-28 | 2025-07-10 | Community Engagement Stakeholder Advisory Group
CESAG Meetings | Bimonthly | Bimonthly | COMPLETE
Kickoff | 2025-03-28 | 2025-03-28
Builidng Trust | 2025-04-11 | 2025-04-11
Mission Statement | 2025-04-25 | 2025-04-25
Co-learning Community Strategy | 2025-05-09 | 2025-05-09
Equitable Engagement | 2025-05-23 | 2025-05-23
Underserved Community Guidelines | 2025-06-12 | 2025-06-12
Communication Strategy | 2025-06-26 | 2025-06-26
Final Framework | 2025-07-10 | 2025-07-10
Integrated Energy Planning (IEP) Working Group | 2025-05-29 | 2025-12-11 | bar: 2025-07-28 to 2025-12-01
IEP WG Meetings | 2025-05-29 | 2025-11-13 | Thursdays | bar: 2025-09-01; 2025-11-01
May 2025 meeting | 2025-05-29 | 2025-05-29
July 2025 meeting | 2025-07-24 | 2025-07-24
September 2025 meeting | 2025-09-18 | 2025-09-18 | bar: 2025-09-01
November 2025 meeting | 2025-11-13 | 2025-11-13 | bar: 2025-11-01
Public Listening Session 1 | 2025-08-24 | 2025-08-24 | bar: 2025-08-01
Public Listening Session 2 | 2025-12-11 | 2025-12-11 | bar: 2025-12-01
Next ESMPs | 2029-02-12 | 2030-04-11 | Five-year term starting July 1, 2030 | bar: 2029-02-01 to 2030-04-01
Draft plans submitted to GMAC | 2029-02-12 | 2029-02-12 | bar: 2029-02-01
GMAC develops recommendations | 2029-02-12 | 2029-06-18 | bar: 2029-02-01 to 2029-06-01
Final plans filed with DPU | 2029-09-11 | 2029-09-11 | bar: 2029-09-01
Department issues final order | 2030-04-11 | 2030-04-11
Other | 2026-03-01 | 2026-03-31 | bar: 2026-03-01
2025 ARR filed with DPU | 2026-03-31 | 2026-03-31 | Annual reliabilility reports (Filled annually March 31) | bar: 2026-03-01
2025 Service Quality filed with DPU | 2026-03-01 | 2026-03-01 | Filed annually March 1 | bar: 2026-03-01