Slide 1

One Care: MassHealth plus Medicare

MassHealth Demonstration  to Integrate Care for Dual Eligibles

Open Meeting

June 28, 2013, 10:00 AM – 12:00 PM

State Transportation Building

Boston, MA

Slide 2

Agenda for Today

- Status Update

- Public Awareness and Targeted Outreach

- Implementation Council Update

- Ombudsman Procurement

Slide 3

Status Update

- Since May 17 Open Meeting, MassHealth, CMS and prospective One Care plans have continued readiness, contracting, and other implementation activities

- Final rate information has been analyzed and processed by plans

  - Additional conversations regarding risk corridors, resulting in a further revised approach.  For plan gains or losses -

    - 0%-1%, no risk sharing

    - 1%-3%, CMS and MassHealth share 90%; plans, 10%

    - 3%-20%, 50%-50% sharing between CMS/MassHealth and plans

    - >20%, no risk sharing

- MassHealth and CMS shared a draft of the three-way contract with plans; target date for signature is mid July

Slide 4

Expected Timeline

Expected Date - Action

- July – Public awareness campaign begins

- July – Three-way contracts signed with One Care plans

- August – MassHealth and One Care plan implementation readiness activities

- Sept. – Enrollment guides and self-selection letters sent to individuals in target population; outreach to potential enrollees begins

- Sept. – One Care plan marketing begins

- Oct. 1 – One Care start date, self-selection enrollments only

- By Nov. 1 – 60-day notice sent to first auto-assignment group

- Jan. 1, 2014 – Effective date for first wave of auto-assignment (C1s only)

- April 1, 2014 (tentative) – Effective date for 2nd wave of auto-assignment

- July 1, 2014 (tentative) – Effective date for possible 3rd wave of auto-assignment

Slide 5

Prospective One Care Plans

- Three plans are moving forward with readiness activities, leading toward contracting

  - Commonwealth Care Alliance

  - Fallon Total Care

  - Network Health

- Plans that sign three-way contracts and complete Readiness Review will be able to accept enrollments in October

- MassHealth and CMS look forward to One Care implementation with a strong group of plans

Slide 6

Key Readiness Review Steps

- Desk Reviews (Phase 1) – complete

  - Submitted policies and procedures for all domains

- Site Visits – complete

  - Reviewed processes for key areas, including assessment, care coordination, enrollee and provider communications, enrollee protections, organizational structure and staffing, systems, and utilization management

- Provider Network Assessments – in progress

  - Evaluate provider network for all covered services

  - Ensure that Medicare and MassHealth access standards are met

- Marketing Materials – in progress

  - Review draft plan marketing materials

Slide 7

Key Readiness Review Steps (cont’d)

- Systems Testing  – July

  - Test cases, e.g.: assign a care team, process claims, access to Centralized Enrollee Record

- Pre-Enrollment Validation – August

  - Vacant positions filled, website, phone lines

- Final Readiness Reports – August

  - Comprehensive determination of readiness for go-live

Slide 8

Public Awareness Campaign and Outreach

Slide 9

Overview

- Kick-off in mid July, with activities continuing through the fall

- Designed to ensure that

  - Consumers, families, providers, CBOs are informed about One Care and prepared for enrollment

  - Key information sources are prepared before MassHealth mails enrollment package

  - Consumers/families have places to go for more information and enrollment assistance after they receive enrollment package

- Components include

  - Materials and website

  - Webinars and other trainings for plans, providers, and others supporting individuals in their enrollment decisions

  - Community outreach sessions and other public forums

Slide 10

Materials and Website

- Print materials will include

  - “One Care at a Glance” flyer

  - Introduction to One Care booklet (see next slide)

  - Posters

- Large print and Braille formats will be available

- Print materials will mailed to approximately 20,000 MassHealth providers, state agencies and CBOs

- New website (to launch mid July), www.mass.gov/masshealth/onecare

  - With text, captioned webinars, videologs

  - Links to other awareness materials and supplemental FAQs

- Radio PSA (English and Spanish)

- Stakeholder input was critical to development of materials – thank you!

Slide 11

Introduction to One Care Booklet Details

- Content

  - One Care overview

  - Understanding One Care plans

  - Signing up for One Care/Selecting a One Care plan

  - Additional Information (covered services, etc.)

- Print and electronic distribution

- Expected to be posted on new One Care website in:

    - English (mid July)

    - Spanish (late July)

    - Large print (August)

    - ASL Videologs (late August)

- Print versions will be mailed to providers, state agencies, and CBOs in August, and available for order in English, Spanish, large print, and Braille

Slide 12

Webinars and Other Training

- SHINE counselors, state agency staff, and CBOs receiving training to ensure they can support people seeking information and assistance starting in July and August

- Webinars:

  - Introduction to One Care (May 23)

  - Contemporary Models of Disability (June 13)

  - Enrollee Rights (planned for August 1)

  - ADA Compliance (planned for Sept/Oct)

  - Cultural Competency Compliance (planned for Sept/Oct)

- Webinars will serve as trainings for plan staff and providers, but also for individuals or organizations providing assistance (e.g. SHINE, state agency staff, CBOs, etc.)

- Online courses and “shared learning” conferences for plans and providers are also being planned for this fall

Slide 13

Community Outreach

- MassHealth also planning to host or participate in other public forums

- Community outreach sessions

  - Planned for fall/winter 2013

  - For potential enrollees, families, guardians to learn more about One Care and ask questions

  - At public libraries and other accessible locations

- One Care plan fairs

  - Planned for fall 2013

  - With representation from plans

  - Opportunity for interaction and Q&A

- Presentations and/or exhibit tables at key conferences and events, such as:  MassHealth Training Forums, ADDP Conference, BIA-MA Conference, EOHHS Consumer Conference

Slide 14

One Care Enrollment Packet

- Enrollment information will be sent to everyone who can enroll in a One Care plan:

  - Welcome letter

  - Enrollment Guide

    - Tips for choosing a One Care plan

    - Ways to find out about a One Care plan’s network of providers

    - Information about the medications a One Care plan will cover

    - One Care plan important phone numbers and information

    - Options for signing up for a One Care plan, including ways to tell MassHealth if a person does not want to join

    - Contact information for MassHealth Customer Service and SHINE

  - Enrollment Decision Form

    - Lists the available plans

    - Includes the option for an individual to not sign up for One Care (opt-out)

  - List of Covered Services

  - One Care at a Glance flyer with FAQs

  - Return mailing envelope

- Materials developed with CMS and stakeholder participation

Slide 15

Implementation Council Update

Slide 16

Ombudsman Procurement

- On June 27, EOHHS issued an RFR seeking a qualified organization to be the One Care ombudsman

- RFR posted on www.comm-pass.com

- Organization must be nonprofit and independent from entities with financial or other interests in One Care that could pose a conflict

- Seeking organization that demonstrates competencies including:

  - Familiarity with disability rights laws and experience assisting individuals with disabilities or underserved populations

  - Cultural competence

  - Expertise and experience promoting rights of Medicare and Medicaid members

  - Familiarity with Massachusetts medical, behavioral health and LTSS delivery systems

  - Ability to provide services in accordance with needs of One Care target population

  - Established relationships with CBOs serving target population

Slide 17

Key Dates for Ombudsman RFR

- Bidders’ Written Questions Due:  July 9, 2013

- Bidders’ Reponses Due:	   July 29, 2013

- Anticipated Date of Contractor Selection:  September 2013

Slide 18

Visit us at www.mass.gov/masshealth/duals

Email us at Duals@state.ma.us