DCR Memorial Drive Phase III Project - 3 Week Look Ahead Schedule

7/27/2026 - 8/14/2026

|  | Week Ending 8/1/26 |  |  |  |  |  |  | Week Ending 8/8/26 |  |  |  |  |  |  | Week Ending 8/15/26 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat |
|  | 7/26 | 7/27 | 7/28 | 7/29 | 7/30 | 7/31 | 8/1 | 8/2 | 8/3 | 8/4 | 8/5 | 8/6 | 8/7 | 8/8 | 8/9 | 8/10 | 8/11 | 8/12 | 8/13 | 8/14 | 8/15 |
| Install Wiring for lightpoles - Dagle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Install Drainage Phase 3 - McCourt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bench removal Phase 3-McCourt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sidewalk removal Phase 3-McCourt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Clearing and Grubbing Phase 3-McCourt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Gerrys Landing Electric Conduit/ Handholes/ Light Bases - McCourt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Remove & Reset Curb Phase III - A&I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Install Barrier Fencing - McCourt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milling Phase 3 - Garrity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Week Ending 8/1/26

Install Wiring for lightpoles - Dagle

Install Drainage Phase 3 - McCourt

Sidewalk removal Phase 3-McCourt

Install Barrier Fencing - McCourt

Milling Phase 3 - Garrity

Week Ending 8/8/26

Gerrys Landing Electric Conduit/ Handholes/ Light Bases - McCourt

Install Drainage Phase 3 - McCourt

Sidewalk removal Phase 3-McCourt

Week Ending 8/15/26

Install Drainage Phase 3 - McCourt

Clearing and Grubbing Phase 3-McCourt

Remove & Reset Curb Phase III - A&I