


[image: McCourt Construction Logo]DCR Memorial Drive Phase III Project - 3 Week Look Ahead Schedule
7/27/2026 - 8/14/2026

	
	Week Ending 8/1/26
	Week Ending 8/8/26
	Week Ending 8/15/26

	Activity
	Sun
	Mon
	Tue
	Wed
	Thu
	Fri
	Sat
	Sun
	Mon
	Tue
	Wed
	Thu
	Fri
	Sat
	Sun
	Mon
	Tue
	Wed
	Thu
	Fri
	Sat

	
	7/26
	7/27
	7/28
	7/29
	7/30
	7/31
	8/1
	8/2
	8/3
	8/4
	8/5
	8/6
	8/7
	8/8
	8/9
	8/10
	8/11
	8/12
	8/13
	8/14
	8/15

	Install Wiring for lightpoles - Dagle
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Install Drainage Phase 3 - McCourt
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Bench removal Phase 3-McCourt
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Sidewalk removal Phase 3-McCourt
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Clearing and Grubbing Phase 3-McCourt
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Gerrys Landing Electric Conduit/ Handholes/ Light Bases - McCourt
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Remove & Reset Curb Phase III - A&I
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Install Barrier Fencing - McCourt
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Milling Phase 3 - Garrity
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	



Week Ending 8/1/26
	Install Wiring for lightpoles - Dagle

	Install Drainage Phase 3 - McCourt

	Sidewalk removal Phase 3-McCourt

	Install Barrier Fencing - McCourt

	Milling Phase 3 - Garrity



Week Ending 8/8/26
	Gerrys Landing Electric Conduit/ Handholes/ Light Bases - McCourt

	Install Drainage Phase 3 - McCourt

	Sidewalk removal Phase 3-McCourt



Week Ending 8/15/26
	Install Drainage Phase 3 - McCourt

	Clearing and Grubbing Phase 3-McCourt

	Remove & Reset Curb Phase III - A&I
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