## Sheet1
MVP 2.0 Process Budget and Timeline [SAMPLE]
This is a sample budget for grantees to use when contracting with a primary vendor on Steps 1-7 and 9. Step 8 ($50,000) will be contracted separately with the Seed Project implementation vendor. | [6 empty] | There is no formal match requirement, but the municipal project manager and any other municipal staff on the Core Team should expect to contribute the following number of hours to the project:
Task | Community Liaisons (+ municipal volunteers) |  |  | Primary Vendor |  | Total Task Cost | Municipal PM | Municipal Member
| 40 |  |  | 150
Step and Deliverables | # People | Hours per person | Total | Total hours | Total | Total | Estimated hours per person | Estimated hours per person
Step 1: Groundwork (August-September of Year 1) Upon completion - Email Part A of your Social Resilience Roadmap to your RC before moving on to Step 2. | 0 | 0 | 0 | 12 | 1800 | 1800 | 10 | 0
Step 2: Recruiting Core Team (September-November of Year 1) Upon completion - Email a list of your Core Team members to your RC before moving on to Step 3. Note which members are community liaisons and the community(ies) they are connected to. | 0 | 0 | 0 | 20 | 3000 | 3000 | 10 | 0
Step 3: Core Team Training (November-December of Year 1) Upon completion - Email your completed discussion guides for the Climate Resilience Video Modules to your RC before moving on to Step 4. | 5 | 10 | 2000 | 15 | 2250 | 4250 | 10 | 10
Step 4: Uncovering Social Resilience (January-March of Year 1) Midway - Check in with your RC once you have completed your Engagement Plan, before starting your engagement activities. Upon completion - Email Part B of your completed Social Resilience Roadmap to your RC before moving on to Step 5. | 5 | 35 | 7000 | 45 | 6750 | 13750 | 26 | 20
Step 5: Revisiting Resilience Priorities (March-May of Year 1) Upon completion - Email your completed Resilience Priorities Guide to your RC before moving on to Step 6. | 5 | 14 | 2800 | 25 | 3750 | 6550 | 12 | 10
Step 6: Selecting Seed Project (May-June of Year 1) Upon completion - Email Part A of your completed Seed Project Plan to your RC by June 15. Submitting Part A and approval from your Regional Coordinator will unlock funding for Seed Project implementation. | 5 | 12 | 2400 | 20 | 3000 | 5400 | 8 | 10
Step 7: Seed Project Implementation Plan (July-August of Year 2) pon completion - Email Part B of your completed Seed Project Plan to your RC before moving on to Step 8. | 5 | 7 | 1400 | 20 | 3000 | 4400 | 10 | 8
Step 8: Implementing Seed Project (September-June of Year 2) | (all costs to be covered by the Seed Project funding)
Step 9: Reflecting, Adjusting, and Next Steps (June of Year 2) Upon completion - Submit the MVP 2.0 Final Submission Form to the MVP Program, including deliverables, photos, and invoices showing all grant funds were spent to close out the MVP 2.0 project. | 5 | 2 | 400 | 5 | 750 | 1150 | 4 | 2
Total | - | 80 | 16000 | 162 | 24300 | 40300 | 90 | 60
DIRECT COSTS
Subject Matter Advisor(s) | [5 empty] | 800
Step 4 Engagement (Uncovering Social Resilience) | [5 empty] | 2000
Step 5 Engagement (Vetting Resilience Priorities) | [5 empty] | 950
Step 6 Engagement (Vetting Seed Project) | [5 empty] | 950
Total DIRECT COSTS | [5 empty] | 4700
TOTAL PROJECT COST | [5 empty] | 45000
NOTES
Assumes 5 community liaisons at $40 per hour; in smaller communities there may be fewer liaisons and this funding may instead support municipal volunteers. Community liaison rate can be adjusted; the recommended rate is between $30-$50 per hour.
Includes a high end ("Municipal PM) and a low end ("Municipal Member") municipal staff time commitment, assuming the high end represents the Project Manager, and the low end is a staff member on the Core Team, but not involved in Steps 1 or 2 or project management.
Translation and interpretation should be included in Engagement costs.