## Instructions
MVP 2.0 Budget [SAMPLE]
Tab 2 includes a sample budget for grantees to use when contracting with a Planning Vendor. Consider whether the municipality will pay Community Liaisons and direct costs directly, or whether those costs will pass through the Planning Vendor. Grantees will receive an additional $50,000 for Step 9. Note: Some communities may be part of a regional grant or may have been awarded a modified scope with a different funding amount. These communities should work with their MVP Regional Coordinator as needed to adjust the budget accordingly. Some communities requested extra funding for translation and interpretation. These communities should add this awarded funding into the budget under direct costs, and consider whether the municipality will pay these costs directly or whether it will pass through the Planning Vendor.

## Sample Budget
MVP 2.0 Budget [SAMPLE]
| Community Liaison budget assumes 5 Community Liaisons at $40 per hour. In smaller communities there may be fewer liaisons and this funding may instead support municipal volunteers. The Community Liaison rate can be adjusted but should be commensurate with municipal staff; the recommended rate is between $30-$50 per hour. | [5 empty] | There is no formal match requirement, but the municipal project manager and any other municipal staff on the Core Team should expect to contribute the following number of hours to the project:
Task | Community Liaisons (+ municipal volunteers) |  |  | Planning Vendor |  | Total Task Cost | Municipal PM | Municipal Member
| 40 |  |  | 150
Step | # People | Hours per person | Total | Total hours | Total | Total | Estimated hours per person | Estimated hours per person
Step 1: Starting to Build Your Team (1-2 months) | 0 | 0 | 0 | 3 | 450 | 450 | 12.5 | 1.5
Step 2: Identifying Lived Expertise (1 month) | 0 | 0 | 0 | 6.5 | 975 | 975 | 6 | 6
Step 3: Recruiting the Rest of Your Team (2 months) | 5 | 3.5 | 700 | 19 | 2850 | 3550 | 13 | 11
Step 4: Kicking off Collaboration (1 month) | 5 | 4.5 | 900 | 9 | 1350 | 2250 | 4.5 | 4.5
Step 5: Uncovering Social Resilience (3 months) | 5 | 25.5 | 5100 | 40 | 6000 | 11100 | 25.5 | 25.5
Step 6: Revisiting Resilience Priorities (2 months) | 5 | 13 | 2600 | 28 | 4200 | 6800 | 14 | 13
Step 7: Selecting Seed Project (1 month) | 5 | 15 | 3000 | 25 | 3750 | 6750 | 16 | 15
Step 8: Seed Project Implementation Plan (1 month) | 5 | 6.5 | 1300 | 14.5 | 2175 | 3475 | 10.5 | 6.5
Step 9: Implementing Seed Project (10 months) | (All costs to be covered by the Seed Project funding) | [5 empty] | (TBD based on Seed Project)
Step 10: Reflecting, Adjusting, and Next Steps (1 month) | 5 | 2 | 400 | 0 | 0 | 400 | 3 | 2
Discretionary Hours | 5 | 10 | 2000 | 50 | 7500 | 9500
Total | - | 80 | 16000 | 195 | 29250 | 45250 | 105 | 85
DIRECT COSTS
Subject Matter Advisor(s) | Funding for a subject matter advisor(s) to advise on the development of the Seed Project Implementation Plan. This total assumes approximately 5 hours at $150 per hour. |  |  |  |  | 800
Core Team Recruitment and Meetings | Direct costs (e.g., translation, printing) for Core Team recruitment; direct costs (e.g., food) for the Core Team Meet & Greet (Step 3) and the "Dinner and a Movie" session (Step 4). |  |  |  |  | 550
Step 5 Engagement (Uncovering Social Resilience) | Direct costs for engagement activities, including (as relevant) translation and interpretation, food, venue, participation gift cards, printing, materials, additional community partners involved in supporting engagement, or other costs. Any costs paid for directly by Core Team members should be reimbursed. There is a statewide contract municipalities may use when procuring translation and interpretation services (https://www.mass.gov/doc/prf75/download). |  |  |  |  | 1500
Step 6 Engagement (Vetting Resilience Priorities) | [5 empty] | 950
Step 7 Engagement (Vetting Seed Project Ideas) | [5 empty] | 950
Total Direct Costs | [5 empty] | 4750
TOTAL PROJECT COST | [5 empty] | 50000