# MT. IDA REST HOME, INC.

## 32 NEWTONVILLE AVENUE

**P.O.BOX 788**

**NEWTON, MA 02460**

**PHONE: 617-527-5657 OR 781-431-7050**

**1-888-302-1838**

**FAX: 617-527-0488**

August 19, 2021

Walter Mackie, J.D.

Massachusetts Department of Public Health

Division of Health Care Facility Licensure & Certification 67 Forest Street

Marlborough, MA 01752

Dear Mr. Mackie:

Please accept this Notice of our intent to cease operations and close our rest home, Mount Ida Rest Home, Inc. (the "Facility"), located at 32 Newtonville Avenue, Newton MA on December 31, 2021 due to costs of operation exceeding current reimbursement. Attached please find our Closure and Relocation Plan (the "Closure Plan")

Copies of this Notice and Draft Closure Plan are being sent simultaneously to the following:

1. Each resident of the Facility, and where applicable, each resident's Legal Representative;
2. A designated Family Member, if applicable, of each resident;
3. Each resident's primary care physician
4. The facility's resident council;
5. Each staff member of the facility;
6. The office of the State Long Term Care Omsbudsman;
7. The office of the Local Long Term Care Omsbudsman;
8. The Office of the Mayor of the City of Newton.

Please note that the facility does not have a family council, nor do they have a labor organization representing its workforce at this time.

The Licensee will work with the Massachusetts Department of Public Health to schedule a public hearing on the proposed closure, which shall be at least 90 days prior to the proposed closure date at a location accessible to residents, family members, and facility staff. Once scheduled, the Notice of Public Hearing will be distributed to all interested parties, and also posted at the Facility. Written comments concerning the proposed closure and the draft closure plan may be submitted to the Department of Public Health, Division of Facility Licensure and Certification, Attn: Closure Coordinator, 67 Forest Street, Marlborough, MA 01752 through the period up to and including the date of the hearing.

A letter will be sent to MassHealth requesting the voluntary withdrawal from the Medicaid Program, effective upon the completion of the proposed closure.

Copies of the draft Closure Plan will be posted in the Facility. Copies may also be obtained by contacting Dr. Indira Desai, President at 508-848-4200. Interested parties may file comments on the proposed closure and the draft Closure Plan with the Facility or the Massachusetts Department of Public Health up until the date of the public hearing.

Residents or their legal representatives, family members, staff, or other interested parties may also contact Dr. Desai if they have questions about the proposed closure.

If you or your staff require any additional information or have any questions, please do not hesitiate to contact me directly at 617-780-0411.

Sincerely,

Mount Ida Rest Home, Inc.

dfa,

by: Dr. Indira Desai its: President

**DRAFT**

**REST HOME**

**CLOSURE AND RELOCATION PLAN**

## INTRODUCTION - NOTICE OF INTENT TO CLOSE

This Closure and Relocation Plan (the "Closure Plan") is being submitted Mount Ida Rest Home, (the "Licensee") to the Department of Public Health (the "Department") for its approval, following a decision to voluntarily close a Rest Home licensed under Massachusetts General Laws Chapter 111, section 71:

Facility Name: Facility License #: Facility Address: Closure Date: Resident Census:

**Mount Ida Rest Home Inc.**

1354

32 Newtonville Avenue

**December 31, 2021**

**13 as of August 19, 2021**

**4 General Relief**

**9 Medicaid**

A Notice of Intent to Close the Facility was filed with the Department on August 19, 2021. **(See Attachment 1: Notice of Intent to Close).** An admissions freeze will go into effect prior to November 1, 2021, 60 days prior to closure.

This Closure Plan is developed in accord with the Department and MassHealth regulations, the MassHealth Relocation Guidelines for Health Care Facilities and the DPH Emergency Patient Relocation Plan.

The underlying objective of this Closure Plan is to ensure a safe, orderly and clinically appropriate transfer of each and every resident with a minimum of stress for residents, family and Facility staff. This objective shall be accomplished in as expeditious a manner as possible under the circumstances. All time frames contained within this Closure Plan are reasonable approximations.

The Licensee understands that it is responsible for accomplishing the safe and orderly closure of the Facility and for assuring that residents receive appropriate care pending the closure. The Licensee is designating a coordinator for the closure, who shall also serve

as the primary contact between the Facility and the Department, and other state agencies as appropriate. The Licensee understands that abandonment of the Licensee's ongoing responsibility to provide care and services during the closure may result in actions against the Licensee, and the closure coordinator.

Facility Closure Coordinator: **Dr. Indira Desai, President**

Telephone Number: 508-848-4200 Fax Number: 508-848-4195

This Closure Plan is organized into the following seven areas of activity which roughly correspond to the chronological process for relocating residents of long term care facilities:

1. Notification Requirements
2. Resident Assessments
3. Family Meetings
4. Staff Meetings
5. Bed Search and Match with Residents
6. Public Hearing
7. Admissions Freeze
8. Resident Relocation
9. Implementation and Coordination

Simultaneous with the filing of the Notice of Intent to Close, a Notice of Withdrawal from the Medicaid Program, effective upon closure, was filed with MassHealth, Attention Medicaid LTC Facility Withdrawal, 600 Washington Street, 5th floor, Boston, MA 02111.

This Closure Plan will serve as the Facility's notice of voluntary withdrawal from the Medicaid program, to become effective on the date the last resident is discharged from the Facility.

## PART 1 - NOTIFICATION REQUIREMENT

**MassHealth**: The Facility shall contact the Long Term Care Division of MassHealth to request their assistance in initiating the closure of the Facility.

**Employees**: The Facility shall notify all staff of the impending closure and of the procedure and time frames contained in the Closure Plan.

**Residents**: Each resident (and his or her designated family member and /or legal representative) shall be immediately notified, orally and in writing, by the Facility management of the impending closure, in accordance with applicable state and federal laws relating to resident notifications. The Notice of Intent to Close, and this draft Closure Plan shall be distributed to all such parties. **(See Attachment2: Sample Letter Notice to Resident/Family Member/ Legal Representative).**

**Physicians and Other Healhcare Providers**: Each resident's attending physician and other care givers (e.g., dentists, podiatrists, mental health service providers and other consultants) shall be notified in writing by the Facility of the impending closure.(See **Attachment 3: Sample Letter Notice to Attending Physicians).** Following relocation of each resident, all affected caregivers shall be notified of the date and location of the resident.

**Pharmacy and Transport Services**: The Facility's pharmacy and transport service providers shall also be notified and informed of their respective roles in the closure.

**Notice of Right to Appeal Discharge**: Notice of the resident's right to appeal discharge under Federal law will be distributed at least 30 days in advance of any discharge. **(See Attachment 4: Notice of Right to Appeal)** once a specific relocation decision has been made. However, should a resident wish to be relocated sooner in order to take advantage of an available bed in another Facility, the Facility will not be constrained by the advance notice requirements.

## PART 2 - RESIDENT ASSESSMENTS

The following types of assessments shall be done:

**Pre-admission Screening**: A pre-admission screening, referred to as a PASSAR screening, will be done for any individual placed in a certified nursing Facility, and for Community Support Facilities or rest homes that have community support residents under the auspices of the Department of Mental Health or the Department of Developmental Services. See 42 USC s.1396 r (e) (7) (A). This screening serves to determine whether individuals need specialized mental health or developmental disability services other than what may be offered in a Facility.

The pre-admission screening shall be performed by the appropriate contract agencies. The Division of Medical Assistance will facilitate the PASSAR screening process with the Department of Mental Health and the Department of Developmental Services or their contracted agents, as appropriate.

**Medicaid Coverage Determination**: Pursuant to 106 CMR 456.251 et seq., the Facility shall complete appropriate assessments of all residents and shall document such assessments on the appropriate forms. These forms will be made available to the Facility by MassHealth during the initial site visit. These long-term care assessment forms will be reviewed by MassHealth staff for the purpose of determining the medical eligibility of residents for continued Medicaid coverage.

**Medical and Social Assessment**: Each resident shall be assessed by nurses and social workers from the Facility, with assistance from the Department and MassHealth as appropriate to identify specific needs, including the need for guardianship that must be considered in finding an appropriate new bed or alternative service. This assessment shall consider the resident's medical needs, family and social ties and other significant factors.

## PART 3-FAMILY MEETINGS

The facility will proceed with consideration of safety and being mindful of the COVID pandemic, all required notifications with residents/families/responsible parties will be completed but with modifications for safety. Each resident and/or family/responsible party will be notified verbally and in writing on an individual basis within 24 hours of DPH receiving the closure package. Additionally, meeting will be made available for those interested in joining a virtual group meeting within 5 days of DPH receipt of the closure package. At this time, we will discuss the closure process, relocation and specific plans to be formulated for each resident and steps the Facility will undertake to ensure the appropriate transfer or discharge of each resident. Subsequent phone conferences or virtual meetings will be scheduled at times to accommodate the availability of family members. At these meetings, resident needs, the possibility of alternative placements and resident and family preferences shall be discussed. The options and responsibilities shall be determined. · The involvement of family and guardians is essential to assuring successful placements for residents and to assure residents' rights are protected in accordance with 42 USC s. 13951- 3 (e) (3) and 42 USC s. 139 r (e) (3). See also 105

CMR 153.023 (A) (2).

**PART 4 - *STAFF* MEETINGS**

A staff meeting and individual conferences with staff members shall be conducted in order to facilitate their transition to a new employer with minimum disruption. Opportunities at Waterview Lodge (sister facility) will be identified and staff will be encouraged to transfer. The Facility will assure appropriate staff coverage throughout the closure process.

## PART 5 - BED SEARCH AND MATCH WlTH RESIDENTS

The Facility staff shall contact long term care facilities in the area and notify them of the impending closure and need for beds. The MassHealth and DPH criteria specify that an appropriate bed be found within a 25-mile radius of the Facility and /or resident's family and friends. See 105 CMR 153 .023 (A) (3). To the extent that a resident has a special need to be met or there are other family considerations or beds within the 25-mile radius have been exhausted, a bed search in other areas will be authorized and initiated.

Upon finding beds, Facility staff shall match available beds with residents to arrange for the best accommodation in terms of location, services and psychosocial needs. To the extent possible, residents and /or their families shall be given an opportunity to participate in this process and to visit a suggested Facility to determine whether it is acceptable

The Facility staff shall identify and contact appropriate transportation services to be used by the Facility to transfer residents and shall establish whether the services have the capacity to handle the projected volume and timetable for relocation. Appropriate transportation arrangements shall be provided for each resident.

Facility will consult with each resident or legal representative and, with the resident's consent, interested family members regarding placement options and the placement process being considered. Once a placement is determined, the resident and family shall be notified in writing by the Facility of the proposed relocation and of their right to appeal such proposed relocation under 42 USC 13951-3 (e) (3) and 42 USC 1396 r (e) (3). **(See Attachment 4 Notice of Right to Appeal).**

## PART 6 - PUBLIC HEARING:

The Licensee will work with the Massachusetts Department of Public Health to schedule a public hearing on the proposed closure, which shall be scheduled at least 90 days prior to the proposed closure date. The Facility will work closely with the Massachusetts Department of Public Health to be mindful of the restrictions during the COVID pandemic and will modify as needed. Will provide appropriate opportunity for the public to be heard.

## PART 7 - ADMISSION FREEZE:

Prior to November 1, 2021 (60 days prior to closure), the Facility will voluntarily freeze all new admissions. This admission freeze shall not apply to Facility residents who are hospitalized and wish to return to the Facility, and are expected to be able to safely return to the Facility prior to the Closure Date. If a resident is hospitalized and able to be returned to the Facility, the Facility shall continue to plan for and coordinate the discharge of the resident to a suitable location.

The Facility has attached to the copy of this Closure Plan filed with the Department, a roster of all Facility residents as of August 17, 2021 **(See Attachment 5 Resident Roster),** including those residents hospitalized but expected to return to the Facility prior to the Closure Date. Due to HIPAA regulations, the roster will be omitted from copies of this Closure Plan being sent to interested parties.

## PART 8-RESIDENT RELOCATION

No more than five residents per day will be transferred without prior written approval by the Department.

Residents will be transferred to receiving facilities in an orderly fashion.

As necessary, appropriate psychological preparation and counseling for each resident shall be provided by the Facility to minimize the impact of the closure on residents and facilitate the residents' adjustment to their new environment.

Measures shall be taken to transfer the following along with each resident:

Medical Records: At a minimum, the facility will complete the Universal Transfer form and send resident's discharge summary completed by the doctor, a copy of the MOLST, HCP, guardianship, Power of Attorney (if applicable), copies of recent lab values and three months of doctor's progress notes.

Medcations: The Facility shall account for resident medications and transfer them with the resident. Any medications not transferred with the residents shall be destroyed in accord with all applicable laws and regulations and appropriate records maintained of such destruction. Such records will be reviewed by the Department on its closure visit to the Facility. If a closure visit is not conducted, the Facility will provide a written account to the Department of medications transferred and destroyed and shall account for all medications previously maintained by the Facility.

Resident Belongings: The resident's personal belongings (clothing, furnishings, etc.) shall be identified and transferred with the resident by the Facility. The resident's personal belongings may be transferred by family members if the resident and the family so desire.

Resident Funds: Funds in each resident's personal needs account shall be transferred for the benefit of the resident.

Social Security lnformation: The Facility shall complete and mail, on behalf of each resident transferred, a Social Security change of address form. In addition, a SC-1 form shall be completed for each transferred resident and mailed to the Regional Mass Health Enrollment Center, Long Term Care Unit.

## PART 9-TMPLEMENTATION& COORDINATION :

Implementation of this plan shall be the responsibility of the Facility.

The Facility shall notify the Department, in writing, of proposed changes in the Closure Plan and obtain the Department's approval of such changes prior to effectuating them.

Record Storage: With respect to records not transferred with residents, and closed records, the licensee has provided for the storage of such records for a period of 5 years as follows:

Records Storage Site: **Waterview Lodge LLC Rehabilitation and Healthcare**

Street Address: 250 West Union Street City/Town: Ashland, MA 01721

Records may be accessed if needed by contacting the person below, who will arrange for access:

Person to Contact: Address:

Telephone Number:

## Dr. Indira Desai

**Waterview Lodge, 250 West Union Street, Ashland MA 01721 508-848-4200**

Facility Reports to the Department: The Facility shall keep the Department informed of the progress of the closure on a weekly basis. As a part of keeping the Department

informed, the Facility will submit reports twice weekly, on Tuesday and Friday, beginning immediately after the submission of the closure plan for approval, detailing the status of each resident in the format specified in Resident Roster **(See Attachment 5: Resident Roster),** and including other information as appropriate.

Monitoring and CIosure Visits: The Facility acknowledges that the Department may conduct monitoring visits and a final closure visit at the discretion of the Department, and agrees to cooperate fully.

Final Closure Visit: The Facility shall submit a final closure report and final resident roster detailing where all residents were transferred at the time the last resident is transferred or discharged. In order to prepare for the final closure visit, the Facility shall make available: (1) a list of all the residents transferred, the facilities to which they were transferred, and the medication which accompanied them; (2) medication disposal records; (3) patient funds accounting records; (4) verification of the successful transmission of the MDS documents; (4) a list of all nurse aides trained by the Facility in a state-approved nurse aide training program after July **1,** 1989, and (5) the location where records will be stored with the name, address and telephone number of the individual responsible for the safekeeping of such records. The licensee is responsible for returning the original license to the Department after the closure visit.

Date Plan Submitted: August 23, 2021

Name/Title: Dr. Indira Desai, President

## Attachments:

1. Notice oflntent to Close
2. Sample Letter- Notice to Resident/Family Member/ Legal Representative
3. Sample Letter- Notice to Attending Physicians
4. Notice of Right to Appeal
5. Resident Roster (to be submitted with plan, and twice weekly after plan approval)

DPH REVIEW AND APPROVAL/DISAPPROVAL

Date Plan Received by DPH:-------

Evaluated By: Date: ---/ /

Approved: Denied: . Comments:

Reviewed By:

Date: ---/ /

Approved:

Denied:

. Comments: - - - - - - - - - - - - - -

ATTACHMENT 1

Notice of Intent to Close

**MT. IDA REST HOME, INC.**

## 32 NEWTONVILLE AVENUE

**P.O.BOX 788**

**NEWTON, MA 02460**

**PHONE: 617-527-5657 OR 781-431-7050**

**1-888-302-1838**

**FAX: 617-527-0488**

August 19, 2021

Walter Mackie, J.D.

Massachusetts Department of Public Health

Division of Health Care Facility Licensure & Certification 67 Forest Street

Marlborough, MA 01752

Dear Mr. Mackie:

Please accept this Notice of our intent to cease operations and close our rest home, Mount Ida Rest Home, Inc. (the "Facility"), located at 32 Newtonville Avenue, Newton MA on December 31, 2021 due to costs of operation exceeding current reimbursement. Attached please find our Closure and Relocation Plan (the "Closure Plan")

Copies of this Notice and Draft Closure Plan are being sent simultaneously to the following:

1. Each resident of the Facility, and where applicable, each resident's Legal Representative;
2. A designated Family Member, if applicable, of each resident;
3. Each resident's primary care physician
4. The facility's resident council;
5. Each staff member of the facility;
6. The office of the State Long Term Care Omsbudsman;
7. The office of the Local Long Term Care Omsbudsman;
8. The Office of the Mayor of the City of Newton.

Please note that the facility does not have a family council, nor do they have a labor organization representing its workforce at this time.

The Licensee will work with the Massachusetts Department of Public Health to schedule a public hearing on the proposed closure, which shall be at least 90 days prior to the proposed closure date at a location accessible to residents, family members, and facility staff. Once scheduled, the Notice of Public Hearing will be distributed to all interested parties, and also posted at the Facility. Written comments concerning the proposed closure and the draft closure plan may be submitted to the Department of Public Health, Division of Facility Licensure and Certification, Attn: Closure Coordinator, 67 Forest Street, Marlborough, MA 01752 through the period up to and including the date of the hearing.

A letter will be sent to MassHealth requesting the voluntary withdrawal from the Medicaid Program, effective upon the completion of the proposed closure.

Copies of the draft Closure Plan will be posted in the Facility. Copies may also be obtained by contacting Dr. Indira Desai, President at 508-848-4200. Interested parties may file comments on the proposed closure and the draft Closure Plan with the Facility or the Massachusetts Department of Public Health up until the date of the public hearing.

Residents or their legal representatives, family members, staff, or other interested parties may also contact Dr. Desai if they have questions about the proposed closure.

If you or your staff require any additional information or have any questions, please do not hesitiate to contact me directly at 617-780-0411.

Sincerely,

Mount Ida Rest Home, Inc.

by: Dr. Indira Desai its: President

ATTACHMENT 2

Sample Letter- Notice to Resident/Family Member/ Legal Representative

**MT. IDA REST HOME, INC.**

## 32 NEWTONVILLE AVENUE

**P.O.BOX 788**

**NEWTON, MA 02460**

**PHONE: 617-527-5657 OR 781-431-7050**

**1-888-302-1838**

**FAX: 617-527-0488**

September 1, 2021

Dear (Resident/Family Member/Legal Representative)

This letter is to inform you of our decision to close Mount Ida Rest Home, Inc. We anticipate closing on or before December 31, 2021.

We will assist you in locating a new care facility to meet your needs. You will continue to receive all the same services you have been, without disruption, until you find alternative placement. As required by Massachusetts law, we have submitted a draft Closure Plan to the Massachusetts Department of Public Health (DPH). Please see the copy of the Notice of lntent to Close, which is attached to this letter. A copy of the draft Closure Plan will be posted in the Facility and is attached to this letter. Copies may also be obtained by contacting me directly.

The closure process entails:

1. Notification to you, your family or legal representative, your physician, and other caregivers
2. Reassessment of your needs
3. Finding an appropriate placement, and
4. Arranging for your relocation along with all of your belongings and appropriate clinical records.

The closing of the facility will be done with a minimum of disruption and inconvenience to you and our other residents.

Mount Ida Rest Home Inc. will proceed with consideration and being mindful of the COVID pandemic, all required notifications with residents/families/responsible parties will be completed, with modifications for safety. In lieu of a Resident and Family Meeting, each resident and/or family member/responsible party will be notified verbally and in writing on an individual basis within 24 hours of DPH receiving the closure package.

The management of Mount Ida Rest Home Inc will be responsible for arranging your transfer to an appropriate healthcare facility. In accordance with state law, we will work to find the most appropriate placement within a 25-mile radius of this home or your family. The choice of a new facility is yours to make and we will obtain your input in finding an appropriate healthcare facility for you.

There are state and federal laws that relate to the transfer or discharge of residents. We are required to inform you of a voluntary closure at least 120 days in advance of such closure. Of course, should you wish to move sooner because an opening is found in a rest home or other appropriate setting and you wish to take advantage of that opportunity, we will facilitate your discharge or transfer as soon as you wish.

This has been a difficult decision and we will do our best to make this transition a smooth one. If you have any questions, feel free to call me at 617-527-5657.

Sincerely,

 Indira Desai D.Sc., RN, LDN, LNHA President

ATTACHMENT 3

Sample Letter to Attending Physicians

**MT. IDA REST HOME, INC.**

## 32 NEWTONVILLE AVENUE

**P.O.BOX 788**

**NEWTON, MA 02460**

**PHONE: 617-527-5657 OR 781-431-7050**

**1-888-302-1838**

**FAX: 617-527-0488**

September 1, 2021 Dear Dr. Anand,

This letter is to inform you of our decision to close the Mount Ida Rest Home, Inc. We anticipate closing on or before December 31, 2021. Our most important priority throughout the closure process is for continued quality care for our residents. The management of Mount Ida Rest Home will need to coordinate with you to arrange for the relocation of your patients: (name of residents). We will not be changing the way we are currently providing care or services. We want a seamless transition for our residents. We will be freezing admissions immediately.

At this time, the management of Mount Ida Rest Home is also notifying all residents and families of the impending closure. Our staff will be evaluating each resident's medical and social needs and the availability of rest home beds in the area to find an appropriate match. We will be contacting you very soon to solicit your input into this relocation effort.

The Massachusetts Department of Public Health has been notified of the impending closure and will be providing assistance in the resident relocation effort. We appreciate the care you have provided to our residents, we value our relationship with you, and we appreciate your support as we go through this difficult time.

For information and assistance, you may contact me at 617-527-5657. Sincerely,

Indira Desai D.Sc., RN, LDN, LNHA President

ATTACHMENT 4

Notice of Right to Appeal

## Notice of Right to Appeal

30 Day Appeal Notice to Resident Transfer/ Discharge

Dear *( Resident / Family Member/ or Legal Representative):*

This letter is to inform you that Mount Ida Rest Home Inc. will be *(transferring or discharging)* you on *(date).* We are *(transferring or discharging)* you for the following reasons:

Arrangements have been made for you to be admitted to *(name of receiving Facility in the event of a transfer).*

-or-

You will be discharged to *(location)* and arrangements have been made for you to receive the following services after your discharge:

You have the right to appeal this decision. If you wish to appeal, you must put your request in writing and mail it to:

## MassHealth Board of Hearings

Office of Medicaid

100 Hancock Street, 6th Floor Quincy, MA 02171

Phone: 1-800-655-0338 or 617-847-1200 Fax:617-847-1204

If you file an appeal within ten (10) days after receiving this notice, you will not be transferred or discharged until after a decision has been made regarding your appeal.

For additional information or assistance, you may also contact the **State Long Term Care Ombudsman** at One Ashburton Place, Boston, MA 02180, (617) 727-7750 or (800) 882-2003.

For developmentally disabled or mentally ill residents add either:

**Disability Law Center,** 11 Beacon Street, Suite 925, Boston, MA 02180, (617) 723-

8455 / (800) 872-9992 Voice, 617) 227-9464 / (800) 381-0577 TTY, (617) 723-9125

Fax; or 32 Industrial Drive East, Northampton, Massachusetts, 01060, (413) 584-6337 /

(800) 222-5619 Voice, (413) 582-6919 TTY, (413) 584-2976 Fax.

**The Center for Public Representation,** 22 Green Street, Northampton, MA 01060, (413) 586-6024 or 246 Walnut Street, Newton , MA 02158, (617) 965-0776.

If you have any questions about this notice, please contact (name of appropriate Facility staff member).

Very truly yours,

ATTACHMENT 5

Resident Roster