 The Commonwealth of Massachusetts

Executive Office of Health and Human Services

Department of Public Health

250 Washington Street, Boston, MA 02108-4619

MAURA T. HEALEY

Governor

KIMBERLEY DRISCOLL

Lieutenant Governor

MARY A BECKMAN

Acting Secretary

MARGRET R. COOKE

Commissioner

**Tel: 617-624-6000**

[**www.mass.gov/dph**](http://www.mass.gov/dph)

February 6, 2023

Mr. Stephen Totino

Executive Director of Finance

Notre Dame Health Care

555-559 Plantation Street

Worcester, MA 01605

Dear Mr. Totino:

I am writing regarding your request for an extension on DoN Project# NDHCV 20080409-CL. You anticipated starting construction in early 2023, however your contractor is terminating their business in April 2023, thereby causing a delay in your construction timeline. Based on this delay, the Determination of Need Program is granting an extension through June 30, 2025.

We request that you send an email to: [DPH.DON@MassMail.State.MA.US](mailto:DPH.DON@MassMail.State.MA.US) when you have met the following milestones:

1. When you have selected your new contractor.
2. When you commence with construction.
3. Provide a construction update the first week of July 2024.

I can be reached at (508) 951-4981 if you have any questions.

Sincerely,

[signature on file]

Dennis Renaud

Director, Determination of Need Program

Massachusetts Department of Public Health