## Slide 1: Digital Accessibility and Equity Governance Board Accessibility Training Plan Working Group Meeting
November 1, 2024

## Slide 2: Meeting Agenda
Introduction and Roll Call
Update on Technology Services and Security Central Accessibility Team Trainings
Discuss Technology Services and Security IT Trainings
Discuss Digital Accessibility Modules Offered by the Cornerstone Learning Library
Discuss Commonwealth Employee Union Contract Agreements
Working Group Next Steps
Working Group Remarks
Public Remarks

## Slide 3: Introduction and Roll Call

## Slide 4: Working Group Member Roll Call
Jason Snyder, Secretary, Executive Office of Technology Services and Security
Ashley Bloom, CIAO, Executive Office of Technology Services and Security
Brian Chase, Secretariat CIO, Executive Office of Veterans Services
Ellen Christy, Secretariat CIO, Executive Office of Economic Development
Larry Goldberg, Public Board Member
David Kingsbury, Public Board Member

## Slide 5: Accessibility Training Plan Objective
Provide accessibility training to introduce Commonwealth employees to digital accessibility in conjunction with role-based accessibility requirements

## Slide 6: Executive Order 614 Training
From Executive Order 614:
The CIAO, in consultation with the Board, shall assess the current digital accessibility training requirements for executive department employees with responsibility for digital content and, in collaboration with Massachusetts Office on Disability and the Human Resources Division, develop and implement a Digital Accessibility and Equity Training Plan that may establish new training or continuing education requirements for such employees.

## Slide 7: Update on Technology Services and Security Central accessibility Team Trainings

## Slide 8: Central Accessibility Team Trainings Update
Have an introduction to accessibility training presentation ready to go to pilot
Plan to pilot this training with EOTSS Mass Digital team in December
Need to create a training feedback survey to gather input to make changes and updates if needed
Will have request process ready to go by the new year for trainings

## Slide 9: Discuss Technology Services and Security IT Training

## Slide 10: EOTSS Skills based Training
EOTSS plans to pilot skills-based trainings for a subset of EOTSS IT team in December
These learning courses will supplement and augment the required annual training that Commonwealth employees must complete
Learning courses will be provided through the Cornerstone platform and will not be required but suggested learning opportunities
May role out to all of EOTSS and additional executive branch employees when courses for job roles have been identified and integrated
Accessibility upskilling courses will be part of these learning courses

## Slide 11: Discuss Digital Accessibility Modules Offered by the Cornerstone Learning Library

## Slide 12: Cornerstone Learning Library Module Offerings
17 modules identified
Coverage areas include:
Introduction to digital accessibility
Standards overview
Web Design
Disability Inclusion
Disability Awareness for Customer Service
Workplace Inclusion

## Slide 13: Discuss Commonwealth Employee Union Contract Agreements

## Slide 14: Commonwealth Employee Union Information
Commonwealth has multiple unions covering over 90% of employees
National Association of Government Employees union covers executive branch employees (may have additional unions)
Most current union contracts commenced in July of 2024 and run through June of 2027
Need to have Human Resources Division work with union administrators to include digital accessibility training into annual required training

## Slide 15: Next Steps for Accessibility Training Plan Working Group

## Slide 16: What is Next for This Working Group
Coming up for this working group
Collaborate with Human Resources division and Massachusetts Office on Disability to investigate training content in the Cornerstone library and content that can be created for required trainings
Finalize Central accessibility Team training coverage deliverables
Continue regular meetings to identify possible tasks for group members to complete to make training plan recommendations
Present recommendations for board feedback at a future meeting

## Slide 17: Working Group Member Remarks

## Slide 18: Public Remarks

## Slide 19: Guidelines for Public Remarks
Time permitting, members of the public are welcomed to provide comments and feedback.
If you would like to speak:
Indicate your desire to provide public comments by using the “raise hand” feature or by commenting in the meeting chat.
Keep remarks to 3 minutes
State your name clearly and any organization you represent
You may also send a comment in the chat (include your name) and the comment will be read out loud on your behalf.

## Slide 20: Thank You