## Slide 1: DAEGB Assistive Technology and Accommodations Working Group
October 13, 2026

## Slide 2: Meeting Agenda

## Slide 3: Agenda
Introduction and Roll Call
Working Group Purpose
Review Feedback on the September 23rd Working Group Presentation
Program Next Steps
Prioritized Quick Wins
Working Group Remarks
Public Remarks

## Slide 4: Roll Call

## Slide 5: Working Group Member Roll Call
Jason Snyder, Secretary, Executive Office of Technology Services and Security
Ashley Bloom, CIAO, Executive Office of Technology Services and Security
Brian Chase, Secretariat IT Accessibility Officer, Executive Office of Health and Human Services
Allan Motenko, Executive Director, Massachusetts Office on Disability
Maria Michalski, Secretariat CIO, Executive Office of Public Safety and Security
Dr. Opeoluwa Sotonwa, Commissioner, Massachusetts Commission for the Deaf and Hard of Hearing
John Oliviera, Commissioner, Massachusetts Commission for the Blind
Carl Richardson, Public Member

## Slide 6: Working Group Purpose

## Slide 7: What is the Purpose of our Working Group?
Provide recommendations that enhance the accommodations
process and supports for employees and end users.
We will achieve this goal through the following Program Improvements.

## Slide 8: Program Improvements – Process and Model
ONE ENTERPRISE PROCESS
Defined, documented, consistently applied accommodations workflow from request through fulfillment and follow-up.
ONE GOVERNANCE MODEL
Clear alignment among EOTSS, MOD, HRD, ADA Coordinators, IT, security, finance/procurement, and agencies on acceptable technology, security, AI usage, funding, and exceptions.

## Slide 9: Program Improvements – Catalog and Support
ONE ENTERPRISE CATALOG
Living catalog of commonly requested assistive technologies, approved/preferred products, standard use cases, vendors, security status, and purchasing paths. (This can live in SharePoint internal)
ONE SUPPORT MODEL
Time-boxed service expectations, transparent escalation, defined non-standard review, and formal follow-up to verify the accommodation meets the employee’s needs.

## Slide 10: Program Improvements – Enterprise
ONE ENTERPRISE STANDARD
Consistent treatment of employees across the Executive Branch, regardless of agency or secretariat.
Move from a collection of agency-level practices to one reliable enterprise accommodation model with clear standards, decision rights, service levels, consistency and accountability.

## Slide 11: Review Feedback on the September 23rd Working Group Presentation

## Slide 12: Program Next Steps

## Slide 13: Phase 1 – Align and Baseline – Participant Groups and Timeline
Timeline: Sept/Oct 2026
Participants:
EOTSS
MOD
HRD
Working Group
ADA Coordinators

## Slide 14: Phase 1 – Align and Baseline – Deliverables
Deliverables:
Confirm enterprise principles for Accommodations (MOD/HRD)
Map current-state agency variations (ADA Coordinators)
Identify mandatory steps (MOD/HRD/ADA)
Define interim escalation path for nonstandard cases (EOTSS)

## Slide 15: Phase 1 – Align and Baseline – Deliverables (continued)
Identify top accommodation use cases (ADA Coordinators)
Start catalog inventory (EOTSS)
Capture Inventory funding/procurement differences (ADA)
Establish baseline metrics to measure progress (Working Group)
Phase 1 Completion Criteria - Agreement on the problem definition, future-state design principles, owners, and priority cases

## Slide 16: Identifying Leads
Identify accountable leads from EOTSS, HRD, and MOD
Identify 1 ADA Coordinator lead from each Secretariat
Ensure leads have the authority and process background to effectively drive solutions
Recommend EOTSS provide a Project Manager and ensure SCIO and Executive Leadership alignment.

## Slide 17: Focus on Quick Wins as We Build Momentum
Why?
Create a strong foundation
Establish a centralized, transparent workflow
Close gaps across the Enterprise

## Slide 18: Breakdown the Milestones – Timelines and Friction Points
Set timeline for Quick Wins
Review and adjust timelines as needed for subsequent phases
Identify any areas of concern or friction in approach
Prioritized Quick Wins

## Slide 19: Prioritized Quick Wins

## Slide 20: Priority 1: Interim Enterprise Decision Path
Issue: The current model has inconsistent IT engagement and review is often delayed.
Owner: EOTSS + MOD + HRD
Assignment:
Define an escalation path for non-standard assistive technology requests.
Identify contacts for security, privacy, accessibility, legal, procurement, AI, and funding decisions.
Establish an accountable owner for each request.

## Slide 21: Priority 2: Create an Enterprise Catalog
Issue: An enterprise catalog and approved products/vendors is needed.
Owner: EOTSS + ADA Coordinators + MOD
Assignment:
Gather the most frequently requested hardware and software.
Map products to standard accommodation scenarios.
Flag items as Approved/Preferred/Requires Review/Not Approved.
Include approved vendors and purchasing path where available.

## Slide 22: Priority 3: Define the Enterprise Standard Workflow
Issue: The current-state process is broadly similar, with variability at the Secretariat level.
Owner: HRD + MOD + EOTSS
Assignment:
Document the expected workflow from request to fulfillment.
Identify mandatory steps versus agency-specific implementations.
Define service-level expectations and escalation points.

## Slide 23: Priority 4: The Rejection Challenge
Issue: Rejected requests do not include an explanation. Requestors also bypass the process due to rejections and delays.
Owner: EOTSS + Secretariats/Agencies
Assignment:
Rejection decisions must include the reason/rationale, with details including the applicable standard/control applied to the decision.
Rejections must include an alternative path to fulfillment.
Requests must be tracked throughout the process with transparent status and contact points.

## Slide 24: Working Group Remarks

## Slide 25: Guidelines for Public Remarks
Time permitting, members of the public are welcomed to provide comments and feedback.
If you would like to speak:
Indicate your desire to provide public comments by using the “raise hand” feature or by commenting in the meeting chat.
Keep remarks to 3 minutes
State your name clearly and any organization you represent
You may also send a comment in the chat (include your name) and the comment will be read out loud on your behalf.

## Slide 26: Public Remarks

## Slide 27: Thank You