## Legend
LEGEND
Acronym | Full Name
Autism Commission | Autism Commission
CEDAC | Community Economic Development Assistance Corporation
DCAMM | Division of Capital Management and Maintenance
DDS | Department of Developmental Services
DHCD | Department of Housing & Community Development
DMH | Department of Mental Health
DPH | Department of Public Health
DTA | Department of Transitional Assistance
DVS | Department of Veterans Services
EOEA | Execuitve Office of Elder Affairs
FCF | Facilities Consolidation Fund
ICHH | Interagency Council on Housing and Homelessness
MassDevelopment | MassDevelopment
MassDOC | MassDOC
MassDOT | MassDOT
MassHealth | MassHealth
MassHire Career Centers | MassHire Career Centers
MassHire Department of Career Services (MDCS) | MassHire Department of Career Services (MDCS)
MassHire Workforce Boards | MassHire Workforce Boards
MassHousing | MassHousing
MassMobility | MassMobility
MCB | Massachusetts Commission for the Blind
MHP | Masssachusetts Housing Partnership
MOD | Massachusetts Office on Disability
MRC | Massachusetts Rehabilitation Commission
Olmstead Implementation Committee | Olmstead Implementation Committee
PCA Workforce Council | PCA Workforce Council

## Goal 1
GOAL #1: Expand Access to Affordable, Accessible Housing with Supports
Activity | Responsible Agency(ies) | Year 1 Measure | Year 1 Progress to Date | Year 2-3 Measure | Year 2-3 Progress to Date
1A. Capital Assistance for Housing Development
1A.1 Develop new housing units for persons with disabilities and new supportive housing units utilizing state capital funding. | Overall: DMH, DDS, MRC and DHCD DHCD and DMH: FCF units serving DMH clients. DHCD and DDS: FCF units serving DDS clients. DHCD and MRC: CBH Units serving individuals with disabilities who are institutionalized or at risk of institutionalization and not DMH or DDS clients | Number of units produced under Community Based Housing (CBH) and Facilities Consolidation Fund (FCF) programs (estimated 150 units). | Certification (Units certified): FY19-8 projects serving 36 clients Q1 FY20 – 1 project serving 1 client New projects funded: Cy19 – 74 units/BRs funded Q1 through Q3. Certification (units certified): CY18 – 18 projects serving 77 clients CY19 – 14 projects serving 61 clients New projects funded: CY19 – 74 units/BRs funded through Sept. 30 CBH units funded in FY19 Q1 through Q3 . DHCD also provides rental assistance for FCF and CHB units. | Number of units produced under the CBH and FCF programs (estimated 150 units annually) as well as units. | DDS: New FCF projects funded: CY20 – 5 projects serving 25 DDS clients CY21-- 10 projects serving 43 DDS clients DMH: New FCF projects funded: CY20- 8 projects serving 34 DMH clients CY21- 8 projects serving 22 DMH Clients MRC: New CBH projects funded: CY20: 10 projects serving 41 individuals with disabilities CY21:11 projects serving 38 individuals with disabilities
1A2 Develop new housing units for persons with disabilities and new supportive housing units utilizing other capital funding. | DHCD | Number of supportive housing units produced with other capital resources such as Housing Trust Fund (estimated 150 units annually). | 114 units of permanent supportive housing (95 units for homeless individuals including 18 units for veterans and 19 units for homeless families) funded in CY 2019 through the annual supportive housing round (funded in part through the Housing Trust Fund). In Winter Rental Round 2019, funding was committed for 95 units of housing for homeless individuals and families (including 54 units for homeless elders, 15 units for non-elderly individuals and 25 units for homeless families). | Number of supportive housing units produced with other capital resources such as Housing Trust Fund (estimated 150 units annually). | CY20: 449 units of permanent supportive housing were funded during CY20 through the mini round, the annual supportive housing round, and the Winter Rental Round 2020. Funding was committed for 171 units of housing for homeless individuals and families (including 119 units for individuals, 33 units for homeless families, and 19 units for other special homeless populations). 278 units of permanent supportive housing was funded for seniors. CY21: 661 units of permanent supportive housing (328 units for homeless individuals and families including 78 units for homeless families) were funded during CY21 through the mini round, the supportive housing round, the rolling SRO NOFA and the winter rental round. PSH units included 266 units for seniors and 47 units for other special populations such as individuals with substance use disorders.
1B. Rental Assistance
1B.1 Include $1 million per year in DMH FY2019, FY2020, and FY2021 budget requests to expand DMH-RSP in order to increase community-integrated housing opportunities, estimated to support an additional 87 individuals with SMI each year, promoting movement within the continuum of DMH residential services. | DMH, DHCD | Allocate to the field estimated 87 subsidy vouchers for leasing. | FY19 included an additional $2M from the Legislature; leased 175 new vouchers*. FY20 included an additional $1M from the Legislature; leased 42 new vouchers through September (68 anticipated). *HUD adjusted up Boston- Cambridge-Quincy FMR upward significantly, which will result in increased cost per unit and in turn will impact the number of units to be leased. | Allocate to the field estimated 170+ subsidy vouchers for leasing. | FY20 leasing increased by 141 vouchers. FY21 budget increased by $3M and an additional 49 vouchers were leased. FY22 included an additional $2M in funding and to date (January 2022), an additional 52 vouchers have leased. It is important to note that COVID-19 did limit leasing and program growth.
1B.2 Utilize Housing Choice Voucher (HCV) or Mass Rental Voucher Program (MRVP) for supportive using units receiving capital funds through DHCD rental funding rounds. The exact commitment of funds (and estimated number of units funded) is dependent on the needs of the specific projects selected for capital funds. | DHCD, DMH | Estimated 100 project-based vouchers tied to supportive housing units, plus an estimated 20-30 project-based vouchers tied to units targeting persons with disabilities, funded annually. | DHCD awarded 46 MRVP project- based vouchers to the Supportive Housing Round in FY19. In addition, DHCD awarded up to 145 additional MRVP project-based vouchers and 160 HCV project-based vouchers to other funding rounds in FY19. | Estimated 100 project-based vouchers tied to supportive housing units, plus an estimated 20-30 project-based vouchers tied to units targeting persons with disabilities, funded annually. | DHCD awarded 206 Supportive Housing MRVP PBVs since FY19. Additionally, in FY21, 100 MRVP PBVs with supportive services were made available to projects through a special NOFA to fund SRO units.
1B.3 Utilize HUD 811 Project Rental Assistance to transition MassHealth members from long-stay facilities to the community and to address the housing needs of other priority populations, with long-term services and supports from MassHealth, MRC and other EOHHS agencies. | MassHealth/DHCD | Lease up all FY12 PRA grant-funded units. The state must lease up all 84 units from the FY12 grant by 9/30/2020. | As of 9/30/19, 28 households had been leased using FY12 grant-funded 811 PRA vouchers. As of that date, 63 units in total have committed to utilize 811 PRA funds (35 units are unavailable or currently under construction). 21 units need to be identified. | Lease-up all FY 13 PRA grant-funded units. The state must lease all units from the FY13 grant by 9/30/2021. | CY20: During calendar year 2020, DHCD was awarded a third Section 811 PRA Grant (FY19) to fund another 72 units for individuals with disabilities. All 84 units for the FY12 grant were made available and 78 are currently leased up. CY21: During calendar year 2021, 19 of the 80 units funded through the FY13 came on line and 19 were leased. 37 more are under construction. HUD has extended the deadline for FY13 grant units so that the final 24 units can be identified and made available to Section 811 eligible non-elderly individuals with disabilities.
1B.4 Apply for new Mainstream (Section 811) Vouchers in response to HUD’s 2018 NOFA to serve non-elderly persons with disabilities who are: transitioning from institutional or other segregated settings to community living; at serious risk of institutionalization; homeless; or at risk of becoming homeless. | DHCD | If awarded, begin implementation of grant (number of vouchers depends on award amount). | DHCD applied for and was awarded approximately $800K for approximately 89 Mainstream Vouchers in response to HUD’s 2018 NOFA. Leasing is underway. DHCD applied for additional Mainstream Vouchers in response to HUD’s 2019 NOFA. | Apply for new vouchers for non-elderly persons with disabilities as they become available in the future, should the agency be eligible and determine it would benefit the Commonwealth’s citizens with disabilities. | DHCD received an additional 27 Mainstream 2018 vouchers as a result of COVID. DHCD applied for an additional 100 Mainstream vouchers. There are a total of 216 vouchers, and approximately 117 are leased.
1C. Policy Initiatives
1C.1 Facilitate the construction and supply of new housing units to increase housing supply and choice. Elements include: • Providing Housing Choice designated municipalities exclusive access to a new state grant program that will make grants for local capital projects as a reward for housing production. • Offering communities that achieve “Housing Choice” designation extra points on a wide variety of state capital grants as incentive to build housing and to adopt housing production best practices. • New and better coordinated technical assistance, including coordination by the Housing Choice Program Director at DHCD, as well as $2 million in planning assistance from MassHousing to help cities and towns achieve their affordable housing goals. • Tracking progress toward a goal of adding 135,000 new housing units statewide by 2025, or about 17,000 units per year. • Legislation, filed as an Act to Promote Housing Choices, that would change state law to reduce the required vote from a 2/3 “supermajority” to a simple majority vote for zoning changes that eliminate barriers to building new housing and improving land use. | DHCD for each Element | Support Housing Choice legislation modifying state zoning laws to make it easier for municipalities to zone for growth. Implement Housing Choice grant program (DHCD), providing grants to municipalities with high rates of housing production, particularly those that have adopted housing best practices designed to support housing production (~$4 million in Y1). Establish “one-stop shopping” coordination for information about technical assistance and related grants for local governments (DHCD). Implement systems to track progress toward production goal. Provide $2 million in planning assistance to help cities and towns achieve their affordable housing goals through MassHousing “Planning for Housing Production” program. | To date, 79 communities have been designated as Housing Choice Communities, and 10 of such designations were made in 2019. In FY19, $4 MM was awarded to 19 Housing Choice Communities. An additional $1 MM was awarded to eligible Small Towns for a total of 12 projects, all of which either created or supported housing projects. DHCD is conducting quarterly coordination meetings across agencies covering 14 different grant and technical assistance programs. DHCD developed and distributed a Database of Technical Assistance and Grants to regional planning agencies, posted on DHCD’s Housing Choice website. Implemented an initial round of funding in May of 2018; from a pool of 29 applicants, 14 projects were awarded a total funding level of $868,500. DHCD has been tracking new unit construction. Following release by the U.S. Census Bureau of the 2018 Building Permit Survey data, DHCD calculated that new construction slightly exceeded the goal of 17,000 units/year in 2018. The Housing Choice legislation was refiled by the Governor in 2019 | Implement Housing Choice legislation if passed, through regulations and/or guidance. Continue and expand Housing Choice grant program, subject to funding availability. Provide additional planning assistance to help cities and towns achieve their affordable housing goals through MassHousing “Planning for Production” program. Track progress toward production goal. | As of 2022, there are 87 communities that have been designated as Housing Choice Communities (HCCs), and 9 of such designations were made in 2022. Over the last 3 years, according to U.S. Census Bureau Building Permit Survey data, DHCD calculated that new construction housing units have consistently exceeded the goal of 16,875 units/year for the last three years. Census data for 2021 is still pending. After implementation of an initial round of funding in May of 2018, Projects have been funded on a rolling basis; 23 Projects have been awarded a total funding level of $1.8 million.
1C.2 Expand the MassHousing 3% Priority Program, currently serving DMH and DDS clients, to housing financed by other state housing funders/lenders such as MassDevelopment and Mass Housing Partnership and to other populations impacted by Olmstead issues, including clients of EOEA and MRC. | DMH DDS MRC EOEA DHCD MassHousing Mass Housing Partnership MassDevelopment | Execute Memorandum of Understanding among State Housing and EOHHS Agencies Publish an Operations Manual Implement requirement for future funding rounds Implement a web-based system for unit notification | MOU is being signed. Effective date is September 1, 2020. Draft Operations Manual is complete. Web-based system for unit notification is being developed. | Agencies sign agreements with Owners/Developers for an estimated 100 new 3% Priority Program units annually. Utilization (by populations eligible for the preference) also anticipated to increase due to expanded eligible populations. | MassHousing has 14 signed Owner's Agreements for the 3% Priority Program, totaling 54 units in the pipeline.
1C.3 Expand TPP with the Housing Court to previously unserved jurisdictions, including Norfolk County, southern Middlesex County, Suffolk County outside of Boston, the Cape and Islands, and continue support for the TPP upstream prevention initiative begun in 2016. | MassHousing/DHCD | 90% of households receiving TPP support will have tenancy preserved by remaining in place or moving to other housing, with 70% remaining in place. An estimated 95% of households receiving TPP upstream prevention support will have tenancy preserved, with 85% remaining in place. | TPP expanded to include the entire state. TPP upstream continues. TPP: 94% tenancy preserved, with 82% remaining in place Upstream: 93% tenancy preserved, with 89% remaining in place. | Maintain tenancy preservation for at least 90% of households receiving TPP support, with 70% remaining in place. Maintain tenancy preservation for at least an estimated 95% of households receiving TPP upstream prevention support, with 85% remaining in place. | TPP preserved tenancies for 95% of households receiving TPP support, with 87% remaining in place. TPP preserved tenancies for 96% of households receiving upstream support, with 94% remaining in place.
1C.4 Develop strategies to enhance utilization by people with disabilities of vouchers provided under programs such as the Alternative Housing Voucher Program. | DHCD/DMH/MRC/DDS | Raise AHVPs ceiling rents to 9% of FMR | AHVP ceiling rents have been raised to 100% FMR | Number of units created under 811 Project Rental Assistance program (estimated 50 units annually). Evaluate utilization of AVHP vouches. | AHVP ceiling rents were raised to 110% of FMR in FY21 and have been subsequently adjusted when FMR is updated. In FY21, DHCD worked with disability advocates to launch a 50 voucher pilot program targeting non-elderly individuals in skilled nursing facilities. Lastly, AHVP began to pay security deposits and first month's rent for AHVP participants in FY22 (January 2022) and has committed to do so at least through the end of FY23. Leasing has been very slow, in part because of COVID-19.
1C.5 Deploy a centralized statewide electronic portal for applications for the state-funded public housing program to allow applicants to apply to any one or more of the 240 local housing authorities in the Commonwealth through submission of a single application. | DHCD | Portal to be made available to LHAs in the summer of 2018 and to housing applicants by January of 2019. | Portal (“CHAMP”) was made available to housing applicants on April 10, 2019. Development of CHAMP expansion to include state rental assistance programs is underway. AHVP is expected to be available in CHAMP by the end of FY20. | Provide ongoing maintenance and evaluation of portal. | AHVP was added to CHAMP and launched live to the public in October 2020.
1C.6 EOEA will work with Continuums of Care to explore implementation of a homeless preference in privately owned senior housing developments developed under the HUD 202 program. | Elder Affairs | At least 5 properties will decide to implement a new waiting list preference for homeless elders. | Two housing agencies are currently finalizing plans to establish a waiting list preference for homeless elders in 8 different properties across the state | At least 15 properties will decide to implement a new waiting list preference for homeless elders. | Three housing agencies established waiting list preferences for homeless elders.
1C.7 Continue to support funding for Housing Consumer Education Centers (HCEC) that can provide affordable housing navigation as well as homelessness prevention across the state. | DHCD | Over $2 million anticipated in funding for HCECs annually (subject to appropriation). | Approximately $3.75 million in funding for HCECs in FY19. | Over $2 million anticipated in funding for HCECs annually (subject to appropriation). | HCECs were given additional funding as part of DHCD's response to COVID-19. HCEC funding in FY20 was $3.75M, $6.5M in FY21, and $8.2M in FY22.
1D. Interagency Collaboration and Program Coordination
1D.1 Pilot joint DHCD/EOHHS procurements to address the housing and service needs of vulnerable populations with disabilities, including elders and individuals and families experiencing homelessness through supportive housing with dedicated services. | ICHH Committee for Supportive Housing Production and Services | ICHH Committee for Supportive Housing Production and Services will identify specific opportunities to test at least three joint procurements to address housing and service needs in supportive housing. | The ICHH Committee for Supportive Housing Production and Services has identified multiple joint procurements to address housing and service needs in supportive housing including the following: - Greater alignment of DHCD family shelter procurement with EOHHS services, including MassHealth flexible services to support housing stabilization for eligible homeless families -Procurement of an HMIS data warehouse to support tracking of homeless populations to inform services provided by DHCD and EOHHS -DHE and DHCD request of HUD to support housing for homeless college students with MTW funds-support for services was approved and implementation will begin in FY21 -DHCD and DPH coordination to support individuals with substance use issues in low-threshold shelters supported by DHCD under its “individual shelter” line item; to date, 4 shelters (247 beds) are operational. | Conduct initial joint procurements in year 2. | Development of a "One Door" proposal, with the guiding principle of coordinating capital, operating and service funding which will support an expedited process for the development of new permanent supportive housing targeted to homeless families and individuals. This proposal will establish a structure to allocate a new pilot flexible PSH services fund, and DHCD will reserve a pool of capital funds and operating subsidies for this PSH.
1D.2 The ICHH Committee for Supportive Housing Production and Services is working to develop goals for production necessary to increase housing inventory for vulnerable populations in need of targeted services. | ICHH Committee for Supportive Housing Production and Services | Develop table of goals for creating housing opportunities for subpopulations – veterans, elders, families, youth, persons with disabilities. | Draft table is in the process of being completed, subject to further agency input | Annually measure progress in addressing housing needs of identified populations.
1D.3 Collaboration between DHCD and EOEA to support modernizing public housing and supporting elders. | DHCD and EOEA | Implement ModPHASE, a partnership between DHCD and EOEA to preserve ch.667 state-aided public housing developments with high capital needs and facilitate partnerships between LHAs and local service agencies to provide service-rich environments that allow residents to age in their community. | The ModPHASE NOFA was issued. DHCD intends to grant up to $10-15M for projects at eligible LHA developments. | Measure impact of pilot on healthcare utilization and residential stability of tenants. | $23.5 M was awarded to 7 LHAs for moderate to substantial rehabilitation projects. Because of the pandemic, progress was much delayed however they are all either reaching the end of their design phases or completing bidding. All awardees secured commitments from local service providers to expand outreach and services to residents of the affected development.
1D.4 Evaluate community integration programs, including through a survey of providers of PSH funded under DHCD supportive housing rounds, to ensure that SH and PSH programs, including those intended as “low threshold,” are serving their intended target populations. | CEDAC/DHCD | Review outcome measurement of survey responses from owners of PSH funded through DHCD supportive housing rounds (for an estimated 6-10 projects annually in addition to the 35 projects previously surveyed) Evaluate survey responses. | Evaluated 2018 PSH survey responses. Determined re- administration of the PSH survey in 2020/2021, which will survey at least 40 projects. | Review outcome measurement of survey responses from owners of PSH funded through DHCD supportive housing rounds (for an estimated additional 6-10 projects annually). Evaluate survey responses. | Re-administration of surveys is currently a longer-term goal due to focus on administering new and increased sources of funding for supportive housing, including through the American Rescue Plan Act.
1D.5 Leverage MassHealth-funded health-related housing supports for certain members enrolled in an Accountable Care Organization (ACO) through the Flexible Services Program, in which ACOs will provide health-related housing supports to members directly or by connecting members to qualified community-based organizations. | MassHealth | Conduct robust stakeholder engagement and release Delivery System Reform Incentive Payment (DSRIP) Flexible Services (FS) Program Guidance to ACOs. | MassHealth conducted robust stakeholder engagement during Year 1 and released DSRIP FS Program Guidance to ACOs in August 2019. |  | Almost all ACOs have contracts with 26 community agencies to provide housing related supports to MassHealth members experiencing or at risk of homelessness.
1E. Accessibility
1E.1 Evaluate the successful use and continued functionality of state-funded supportive housing projects supported by Chapter 689, FCF, CBH, HIF and other state funding sources, in order to better manage and monitor the utilization of this important affordable and accessible housing portfolio, and to improve the affordable and accessible housing portfolio, and to improve the quality and accessibility of the portfolio over time. | DHCD/CEDAC, DMH, DDS, DCAMM | Assemble inventory of properties and develop checklist for evaluation of status. | Established and regularly convening a working group amongst the responsible agencies to prevent loss of inventory of group homes that are vulnerable to loss due to expiring DCAMM leases or outmoded physical plans. DHCD/CEDAC broadened contractor (FinePoint) monitoring to include the FCF portfolio. DDS has been actively engaged in assembling its portfolio of156 Ch 689 sites and 314 FCF residences. DDS meets quarterly with DHCD & CEDAC to review our state funded supported housing projects including our portfolio of 157 Ch. 689 sites and 328 FCF residences. | Evaluate status of properties in state-funded supportive housing and develop strategies and identify funding sources for disposition or renovation/ re-programming, as needed of subsidized portfolio. | DDS has been actively engaged in assembling its portfolio of 156 Ch 689 sites and 332 FCF residences. DDS meets monthly with DHCD & CEDAC to review our state funded supported housing projects including our portfolio of 157 Ch. 689 sites and 332 FCF residences.
1E.2 Provide reasonable accommodation training regularly to PHAs and private management companies. Training to include awareness of reasonable accommodations that may be needed by people who are deaf or hard of hearing. | MassHousing | MassHousing will offer six Fair Housing and Reasonable Accommodation-related trainings, which will include info on accommodations needed by people who are deaf or hard of hearing. MassNAHRO & NEAHMA share MassHousing’s training schedule with their members. | 13 Fair Housing & Reasonable Accommodations trainings | MassHousing will offer 12 Fair Housing and Reasonable Accommodation-related trainings, which will include info on accommodations needed by people who are deaf or hard of hearing. MassNAHRO & NEAHMA share MassHousing’s training schedule with their members. | MassHousing offered 7 Fair Housing and Reasonable Accommodation-related trainings, which included info on accommodations needed by people who are deaf or hard of hearing. MassHousing's training schedule was shared with MassNAHRO & NEAHMA. During CYs 20-21, MassHousing offered fewer Fair Housing and Reasonable Accommodations trainings in order to provide more COVID19-related trainings. DHCD offered training to LHAs regarding reasonable accommodations and issued a Reasonable Accommodation Policy Template for LHAs to follow in developing or amending their Policy. DHCD also provided CHAMP application training to advocates working with deaf and hard of hearing applicants.
1E.3 As public housing capital funds permit, continue to target capital funding of at least $1-2 million annually to increase accessibility in DHCD’s state-aided public housing, including funding to assist LHAs in responding to requests for reasonable modifications to state-aided public housing. DHCD is committed to the goal of having 5% fully accessible units across the entire state- aided portfolio. | DHCD | Continue to target capital funding to assist LHAs in responding to reasonable modification requests and accessibility requirements relating to capital improvements (exceeds at least $1 million annually). | Notice of Funding Availability for Accessible Unit Initiative released April 17, 2019, committing $3 million annually in FY21 and FY22. Subject to funding availability, DHCD plans to continue this level of commitment for at least 5 years. | Continue to target capital funding to assist LHAs in responding to reasonable modification requests and accessibility requirements relating to capital improvements (exceeds at least $1 million annually). Prepare/launch next accessible unit initiative funding round. | Public Housing was granted $150M in ARPA funds. DHCD intends to use $5-7M of those funds specifically targeting accessible unit conversion projects. It is likely that more will be spent addressing accessibility needs through regular capital improvement projects. By the end of the ARPA compliance period (12/31/2024) DHCD will be able to report on the exact amount spent on ADA needs.
1E.4 Provide Home Modification Loan Program (HMLP) funds for access improvements. The Administration has committed up to $6.5 million annually (subject to capital plan approval) in capital bond funds through 2022 for HMLP, including up to 10% of funding program. The bond bill includes administration-proposed program modifications to make HMLP a resource for landlords to make rental housing accessibility improvements. | MRC/CEDAC | Update guidelines for expanded use of HMLP. | For FY 19 through September 2019, 269 loans were closed and 178 consumers had projects completed through HMLP. The program has created policy guidelines for landlord access to grants for rental housing improvements, with a pilot program being launched. Planning for additional accessibility grants relating to AHVP participants under the FY19-FY20 state budget is underway (the Accessible Affordable Housing Grant Program). | Conduct outreach to landlords and families to facilitate use of funds for this purpose – increase projects funded by 10 per year. | HMLP issued an RFP for program marketing services in the fall of 2021 and is currently engaged in updating marketing materials and the website. In calendar year 2020, 185 loans serving 173 households were made; in calendar year 2021, 161 loans serving 148 households were made. The HMLP landlord grant program is still in the pilot phase. 7 grant commitments have been made for the Accessible Affordable Housing Grant Program.
1E.5 Explore how best to increase access to housing options for people with Autism, including identification of housing design features most frequently needed by individuals with Autism and how to incorporate and integrate those in existing, rehabilitated, and new affordable and supportive housing units. | Autism Commission | Identify the different types of low- cost housing potentially available for individuals with disabilities, including for individuals with autism, such as subsidized rental housing and public housing. | The Housing Subcommittee commissioned a state-wide housing survey, which provided details on the types of affordable housing available to individuals with disabilities, including autism spectrum disorder, in the Commonwealth. The Housing Subcommittee also reviewed design specifications on two projects underway on Cape Cod and discussed potential design additions to meet the needs of individuals with autism spectrum disorder. | Examine the accommodations and modifications that can help individuals with ASD access housing and maintain tenancy.
1E.6 Review, refine and update current design guidelines for FCF and CBH and convene a working group to refine and update these guidelines to address the geographic and environmental diversity of rural, suburban and urban constraints and influences. DHCD, EOHHS and CEDAC will convene such working group to review the guidelines. | DMH & DHCD/CEDAC | Assemble working group, identify funding and engage consultants to assist with new guideline development. Complete updated CBH Design Guidelines. | DMH hosted presentation on Housing Design and Mental Health (3-13-19) Updated CBH design guidelines have been drafted and completion is anticipated by the end of 2019; training on updated guidelines to follow. | Draft and disseminate new guidelines, provide outreach and training to developers and managers on new guidelines. Complete amendment of FCF guidelines to include housing design for persons with Autism. | CBH: completed, disseminated, and conducted Zoom webinar trainings for the updated CBH design guidelines in the fall of 2020. FCF: CEDAC engaged a consultant in June of 2021 to update the FCF design guidelines with respect to: 1) group home community residences; and 2) housing developments in which FCF-DDS units are integrated. These guidelines are anticipated for completion later in the spring of 2022, and virtual trainings on these new guidelines will be held.

## Goal 2
GOAL #2: Enhancing Community-Based Long-Term Services and Supports
Activity | Responsible Agency(ies) | Year 1 Measure | Year 1 Progress to Date | Year 2-3 Measure | Year 2-3 Progress to Date
2A. Expanding Access to Community Based Services
2A.1 As part of its Medicaid 1115 Waiver Renewal, Massachusetts will invest $1.8 billion over the next five years to support the transition toward Accountable Care Organizations (ACOs). ACOs that will be held contractually responsible for the quality, coordination and total cost of members’ care. ACOs will contract with designated Community Partners, community-based health care and human service organizations that will partner with ACOs to integrate and improve health outcomes of MassHealth members with complex long term medical and/or behavioral health needs | MassHealth | Contract with Community Partners effective June 1, 2018. In state fiscal year 2019, the State will invest $60 million in the community partners program. | As of September 30, 2019, MassHealth has entered into 27 Community Partner contracts (18 behavioral health CPs and 9 LTSS CPs). MassHealth also invested $98 million in the CP program by the end of SFY 2019. | In state fiscal years 2020 and 2021, the State will invest a total of $217 million in the community partners program.
2A.2 Expand MassHealth coverage for substance use disorder (SUD) and co-occurring disorder (COD) treatment to include a continuum of 24-hour community-based rehabilitation services, care coordination and recovery services, including the evidence- based practices of Medication Assisted Therapy and Critical Time Intervention. | MassHealth | Assess MassHealth Spending for SUD and COD Treatment | MassHealth has taken efforts to identify and track spending on services for SUD and COD treatment during the year. Additionally, in SFY 2019, MassHealth implemented Recovery Coach and Recovery Support Navigator benefits for members with SUD and COD, and has added residential rehabilitation services (RRS) as a MassHealth covered service and increased availability of RRS by expanding the RRS provider network. | Assess MassHealth spending for SUD and COD treatment | FY2020, MassHealth spend for Residential Rehabilitation for SUD (RRS) and Co-Occurring Enhanced RRS (COE RRS) was $17.8M FY2021, MassHealth spend for RRS and COE RRS $40.1M
2B. Promoting Services That Facilitate Transitions from Institutional Settings
2B.1 Increase capacity in two Moving Forward Plan (MFP; formerly Money Follows the Person) HCBS waivers and two Acquired Brain Injury (ABI) HCBS waivers over the course of the five-year renewal period. | MassHealth, Residential Waivers | Increase total unduplicated member slots as follows: • ABI-Nonresidential Habilitation: 120 slots per year (increased from 110 slots in the prior waiver year) • ABI-Residential Habilitation: Yr 1 (5/1/18-4/30/19) – 596 slots (increased from 513 slots in the prior waiver year) • MFP-Community Living: Yr 1 (4/1/18-3/31/19) – 843 slots (increased from 729 slots in the prior waiver year) • MFP-Residential Supports: Yr 1 (4/1/18-3/31/19) – 364 slots (increased from 304 slots in the prior waiver year) | MassHealth renewed the ABI and MFP waivers with slot capacity for Waiver Year 1 as outlined in the Year 1 Measure. | Increase total unduplicated member slots as follows: • ABI-Residential Habilitation:Yr 2 – 636 slots (increased from 596 slots in the prior waiver year) Yr 3 – 676 slots (increased from 636 slots in the prior waiver year) • MFP-Community Living: Yr 2 – 943 slots (increased from 843 slots in the prior waiver year) Yr 3 – 1043 slots (increased from 943 slots in the prior waiver year) • MFP-Residential Supports: Yr 2 – 424 slots (increased from 364 slots in the prior waiver year) Yr 3 – 484 slots (increased from 424 slots in the prior waiver year) | MassHealth added slot capacity to the ABI and MFP waivers for Waiver Years 2 and 3 as outlined in the Year 2-3 Measure.
2B.2 Enhance efforts to transition from State Hospital continuing-care beds individuals with serious and persistent mental illness that are determined discharge ready and able to safely move into community-based living opportunities with appropriate supports. Establish a DMH State Hospital Discharge Review Team that provides Peer-to-Peer case consultation to facilitate discharge planning. | DMH | DMH to organize resources and training to initiate implementation of enhanced efforts to increase the number of continuing-care bed individuals who are determined discharge ready and able to safely reside in the community into community-based living opportunities with appropriate supports. | DMH enhanced its efforts to transition discharge ready individuals through implementation of a standard discharge readiness tool in DMH inpatient facilities, the results of which are reviewed monthly. DMH also implemented Level of Care reviews which are intended to identify Clients ready for movement out of GLEs and into more independent housing. As of October 2019, the Level of Care review process includes Clients in DMH facilities for the purpose of enhancing the community service planning efforts. During FY 2019, 596 continuing-care bed individuals without criminal justice involvement who were determined discharge ready were discharged to community-based settings. | Transition each year 20% of the discharge ready population into the community. Align community system to be more consistent and predict service needs and demand. | DMH increased review of discharge readiness results to weekly and modified the Level of Care reivew process for GLEs with consistent timelines for review based on length of stay in GLE. DMH is developing new proceses for shared treatment and dischage planning with clear roles for inpatient and community team members. Approximately 65% of the discharge ready population was discharged to the community.
2B.3 Continue to assess and divert nursing facility placements when appropriate for individuals with ID/DD by ensuring that people admitted to nursing facilities are determined to need that particular level of services, and when nursing facility care is no longer needed, are transitioned to the community. | EHS/DDS | 100% of individuals determined to have ID/DD through the PASRR process and who are admitted to a nursing facility have a PASRR evaluation indicating NF level of care. Implement 90-day PASRR approvals to allow for short-term nursing facility admissions. Track 100% of individuals receiving a PASRR evaluation through a statewide database. Assure federal compliance through administrative case management processes. | Under federal law and EHS/DDS PASRR processes, every individual seeking admission to a nursing facility who has or is suspected to have ID/DD must receive a PASRR evaluation from DDS. The nursing facility may not admit such an individual unless DDS determines, among other things, that he or she requires a NF level of care. 90-day PASRR approvals implemented. DDS has implemented a PASRR database for individuals with ID/DD. DDS provides administrative case management for individuals who have been determined to have ID/DD through the PASRR process. | 100% of individuals with ID/DD admitted to a nursing facility have a PASRR evaluation indicating NH level of care. Continue utilizing 90-day PASRR approvals to allow for short-term nursing facility admissions. Track 100% of individuals receiving a PASRR evaluation through a statewide database. Continue to assure federal compliance through administrative case management processes. | All individuals seeking admission to or continued stay in a nursing facility as identified correctly through the Level I process have had a Level II PASRR evaluation either prior to admission or by day 30 as evidenced by statewide data. DDS PASRR has a continued its well established 90 day PASRR process which determines either need for return to the community or appropriateness for continued skilled nursing. Data is monitored on a weekly basis to determine compliance with implementation of federal PASRR requirements as well as the commitment to ensuring that people with ID/DD appropriately return to their communities following their rehabilitation stay.
2B.4 Explore expansion of funding for the MRC Supported Living Program in order to serve more individuals. | MRC | Explore feasibility and costs for expansion. Develop budget request for increased funds based on findings. | MRC is presently initiating small- scale pilot expansions of the Supported Living Program in three areas: 1. Case coordination to assist individuals to qualify and obtain housing in the community; 2. Short-term case coordination to assist individuals in resolving short- term challenges or finding and accessing resources; and 3. Expansion of Supported Living services to individuals with disabilities other than a severe physical disability. These pilots will assist MRC in gauging the level of need for these services along with the challenges to providing these expanded models. | If funds are granted, establish expansion and begin service delivery depending on funding and resources. | Through ARPA funding, MRC has dedicated a manager level FTE to develop and implement a program expanding the cohorts in the pilot to include eligible MRC individuals with disabilities and co-occurring behavioral needs such as Severe Mental Illness and Substance abuse Disorders residing in nursing facilities and who want to transition to the community. The position will collaborate with stakeholders including but not limited to: Supported Living staff and service providers, DMH, MassHealth and EOEA.
2C. Promoting Services That Support People with Disabilities to Remain in their Homes and Community-Based Settings
2C.1 Advance self-determination through expanding self-direction outreach and encouragement to share self-direction experiences, developing opportunities for stakeholders to gather on a regular basis to discuss the self-direction model, continuing to improve training materials and simplifying the self-direction process. | DDS | Increase participation in both the Agency with Choice (AWC) and Participant Directed Program (PDP) by a combined total of 120 individuals annually. Introduce self-direction to participants and families prior to transition to DDS adult services. Make self-direction materials available to families and individuals at the annual ISP. Add at least five new speakers in the Self-Direction Speakers Bureau. Host at least monthly support broker/service coordinator forums in each region and an annual statewide support broker conference. Develop survey for stakeholders to gather feedback on the self-direction model, the training materials and simplifying the self-direction process. Continue to work with the financial management services vendor to improve the process of managing the self-direction model through the online portal and call centers. | In FY 2019, participation in AWC/PDP was increased by a combined total of 245 individuals to a total of 1,261 participants Self-direction is introduced to participants and families as part of the Individual transition Planning process for DDS Self-direction materials are made available to families and individuals throughout the ISP process and self-determination forums sponsored by DDS. Five new speakers were added, and a collaborative with DDS and community providers developed a Public Speaking Skill Development curriculum for self-advocates, to help participants improve their public speaking skills on self-determination and self-direction. The speakers provided an update at the December 2019 Self-Determination Advisory Board (SDAB) meeting. DDS conducts support broker development training programs to promote skill development and support for the support brokers statewide. DDS and the services vendor conducted a satisfaction survey and implemented action steps to increase survey response rates and address areas of concern. DDS meets with the financial management services vendor on a regular basis and reports periodically to the SDAB. | Increase participation in both the Agency with Choice (AWC) and Participant Directed Program (PDP) by a combined total of 120 individuals annually. Continue Introducing self- direction to participants and families prior to transition to DDS adult services. Continue making self-direction materials available to families and individuals at the annual ISP. Add at least five new speakers in the Self-Direction Speakers Bureau. Continue hosting at least monthly support broker/service coordinator forums in each region and an annual statewide support broker conference. Monitor need for ongoing guidance on how participants can utilize Flexible Spending allocations and re-issue as needed. Monitor the need for ongoing improvement of the process of managing the self-direction model through the online portal and call centers. | In FY2020, participation in AWC/PDP was increased by a combined 253 individuals for a total of 1,490. In FY2021, participation in AWC/PDP was increased by a combined 197 individuals for a total of 1687 participants. Information on Self-direction is offered to all participants and families as part of the individual transition process. In addition, information sessions are offered to the public twice monthly in a virtual format. DDS has issued and awarded Request for Response to advance consistency and transparency in budget setting and to increase the use of self-directed supports by simplifying the PDP/AWC process. This work will be completed over a 3 year span. DDS has continued focus groups for service coordinators/support brokers, participants and families to address the complexity of self-direction. Monthly meetings are held with PPL and targeted trainings for Support Brokers have been developed and disseminated to the field specific to PPL and their portal/call centers. In addition, PPL has been receptive to feedback and committed to development of several new, participant/family friendly reports as well as reports developed for DDS staff to address timelines and communication gaps.
2C.2 Increase the supply and quality of Personal Care Attendants (PCAs) by improving the online registry to connect PCAs and consumers in the self-directed program and increasing outreach and marketing efforts to attract individuals to work as PCAs. | PCA Workforce Council | Launch upgraded online registry that will include new and enhanced features, such as accessibility through smart phones and other devices, email alerts. PCA workforce council takes steps to recruit new PCAs to participate in the program, such as organizing informal meet-and-greets between consumers and potential PCAs. | The PCA workforce council has launched the upgraded online registry described in the year 1 measure. Similarly, the council has engaged in various PCA recruiting events, including through organizing informal meet-and-greets. The online registry has been enhanced to improve the user experience. The number of consumers and PCAs using the directory has increased by 125% and 143%, respectively, from September 2018 through September 2019. As of September 30, 2019, there have been 33 meet-and-greet events throughout the state. | Continue progress on improving PCA recruitment processes, implementing enhancments to the PCA on-line registry, as well as improving PCA and Consumer utlization of the PCA on-line registry. | The Mass PCA Directory and the PCA recruitment and retention effort focused on streamlining the PCA recruitment process in FY22, including posting references on various job boards (within the state government as well in 31 colleges throughout Massachusetts) to apply for positions on the Mass PCA Directory, and encourage members to post available jobs. PCA recruitment were customized and translated for workforce development partners. The Council obtains feedback from a dedicated stakeholder group from around the state. Information videos were developed to aid in posting or applying on the directory. Features were added to the Directory to improve user experience, including improved search parameters to provide more meaningful results. The number of consumers and PCAs using the Directory increased from June 2021 to July 2022, 26% and 10%, respectively.
2C.3 Increase the current PCA wage to $15/hour effective July 1, 2018, as part of its continued effort to attract and maintain individuals to work as PCAs. | PCA Workforce Council | Implement wage increases. | Wage increase implemented. An additional wage increase to $15.40/hour was implemented on July 1, 2019. | Assess the availability of PCA services for MassHealth members. | To further support availability of PCA services for MassHealth members, wages further increased to $17.71/hour during the COVID-19 public health emergency and will increase to $18.00/hour during state fiscal year 2023.
2C.4 Expand MassHealth initiatives to improve the supply and quality of Continuous Skilled Nursing (CSN) services in the community and increasing annual MassHealth spending on CSN services. | MassHealth | In 2018, MassHealth, in partnership with UMMS’s Community Case Management (CCM) program, will host a training on Inpatient Facility Discharge Planning for CCM members. MassHealth also proposes to increase the scope of CCM to include more case management activities. These enhancements will partially be reflected in the UMMS-MassHealth 2018 ISA. | MassHealth and the CCM program, in collaboration with various stakeholders, developed and implemented a pilot program designed to assist members with identifying available CSN service providers and assist CSN service providers with identifying available CSN hours. The pilot has been extended through fiscal year 2020. | CCM member case management activities will be streamlined between CCM and ACO/MCO models. | In part due to the onset of the COVID-19 pandemic, MassHealth promulgated the following rate increases during SFY20 Q4: •April 2020 issued 10% rate increase due to COVID-19 pandemic and through AB 20-23. Rates effective April 1, 2020 through July 31, 2020. •June 2020 issued an additional 10% increase through AB 20-63. Rates effective May 1, 2020 through July 31, 2020. Additional 10% on top of previous COVID-19 rate. •Permanent rate increase established in July 2020 and increased all CSN rates by 1.57%. · During SFY22 Q1 and Q2, MassHealth also issued a 10% rate increase to all home and community-based services included in the American Rescue Plan Act (ARPA), including for CSN. In addition to the standard 10% rate increase for all HCBS programs, MassHealth issued an additional 20% rate increase for all CSN services. The approximately 30% rate increase for CSN services was established under 101 CMR 447 and are effective for dates of service from July 1, 2021 through December 31, 2021. · During SFY22 Q3, MassHealth extended the standard 10% rate increase for all HCBS programs, including CSN, through June 30, 2022. MassHealth also promulgated a permanent 20% rate increase for all CSN services effective on January 1, 2022. · In addition, MassHealth also temporarily allowed agencies to access and be reimbursed established CSN agency overtime rates for dates of service January 1, 2022 through June 30, 2022. · Create and launch a CSN Provider Online Directory that will help CSN providers with availability to connect with CCM members who need nursing supports. · Establish a CSN Clinical Training grant program where medical entities could receive a grant from MassHealth to establish a CSN Clinical Training program that will train the current CSN nursing workforce, and also attract additional nurses into the workforce. · Launch targeted marketing activities for CSN nurses as a part of EHS’s larger HCBS marketing campaign, “Call to Care.”
2C.5 Explore expansion of funding for the Assistive Technology (AT) Independent living program. | MRC | Explore feasibility and costs for expansion, and create budget request based on serving 475 individuals per year. | 422 individuals received services through this program in FY19. MRC is analyzing the demand and costs in preparation for FY21 budgeting. | Establish expansion and beginning of service depending on funds and resources available. | Initiated expansion of services. Though affected by pandemic, 451 consumers were served in FY20 and 455 in FY21. Devices distributed: FY20:-594, FY21:-778
2C.6 Seek additional funding to expand the REquipment program, which redistributes over 1,000 AT devices annually. | MRC | Explore feasibility and costs for expansion and create a budget request based on identified need. | Increased funding in FY19 allowed program expansion, which has resulted in an increase in the number of reassigned DME devices and the establishment of two new drop-off sites, in Salem and New Bedford. MRC is analyzing program needs and costs to identify long-term budget needs. | Establish expansion and beginning of service depending on outcomes found in feasibility study and funds available. | Expansion of the program has been established and two new drop-off sites were open. Total number of DME assigned in FY20 was 1156 and in FY21 - 1533. MRC continues to analyze the needs and the costs while working on new and updated RFRs reflecting new ARPA funding
2C.7 Improve statewide coverage and expedite access to redistributed AT devices. | MRC | Explore feasibility and costs for expansion and create a budget request based on identified need. Feasibility will be determined using a study of types of AT devices that lend themselves to being refurbished and a survey of the potential of expansion for the program and potential program models. | MRC is exploring available mechanisms for redistribution of AT devices other than Durable Medical Equipment. | Conduct feasibility, needs study. | Two AT Reuse Feasibility reports were developed by Requipment Inc.: one in August 2020, and one in June 2021 MRC will review the reports and assess for next steps.
2C.8 Partner with the Mass Healthy Aging Collaborative to support and increase the number of communities pursuing Age Friendly and/or Dementia Friendly designations or certifications to support Massachusetts in becoming an Age Friendly State. | Elder Affairs, DPH | Continue to build age friendly movement in MA. Deepen capacity building at local level. Embed access, equity and cultural inclusion in age friendly work. | The age- and dementia-friendly movement continues to grow with 191 communities engaged in age-friendly and 165 communities engaged in dementia-friendly. In 2019, 26 communities received an age-friendly designation and 17 committed to a dementia-friendly pledge. Age- and dementia-friendly work has continued to reach new sectors. Springfield became the first city in the United States to be recognized as age- and dementia-friendly in collaboration with an Age-Friendly Health System. The University of Massachusetts system became the first academic system to commit to the global Age-Friendly University movement with five campuses becoming age-friendly. Values of access, equity and inclusion continue to guide this work and resources such as the Inclusive Communities Toolkit and Age- and Dementia-Friendly Integration Toolkit were created to help communities. Mass Municipal Association dedicated an issue of their quarterly magazine, Municipal Advocate, to age- and dementia-friendly work. The issue included resources and highlights from local communities. Mass in Motion (MiM) is a statewide movement to lower the risk of chronic disease by supporting equitable food access and active living opportunities. The Massachusetts Department of Public Health’s (MDPH) MiM program supports communities that have identified older adults as priority populations by supporting Age-Friendly specific strategies and activities as part of approved work plans. The Massachusetts Department of Public Health’s (MDPH) new Determination of Need Community Health Initiative (CHI) Healthy Aging Fund released a funding opportunity in FY20 designed to advance and support the Age Friendly movement. | Continue to build age friendly movement in MA. Continue to deepen capacity building at local level. Embed access, equity and cultural inclusion in age friendly work. | The age- and dementia-friendly movement continued to grow with over 200 cities and towns engaged in this work: 98 communities are now designated age-friendly, and 60 have signed a dementia-friendly pledge. In 2020-2021, the number of regional movements grew, including work in Franklin County.
2C.9 Increase the number of individuals who are legally blind that receive blindness critical specialized wrap-around services (Orientation and Mobility, Rehabilitation Teaching & Assistive Technology), leading to productive independence and full community participation | MCB | Increase the number of individuals who are legally blind that receive blindness critical specialized wrap- around services by 3%. | The target 3% increase in the number of legally blind individuals receiving blindness critical specialized wrap-around services was met. In order to further increase the number of individuals receiving services, MCB is working on a Business Process Redesign for new consumer registration process. In addition, a communication plan for reaching out to eye professionals in the Commonwealth is in progress. | Increase the number of individuals who are legally blind that receive blindness critical specialized wrap-around services by an additional 3%. | The target increase in the number of individuals who are legally blind receiving blindess critical wrap-around services has been met. MCB continues its modernization efforts of the registration process and is in process of hiring another staff member in its Registration unit. MCB has had at least 50% increase in the number of eye doctors using the electronic registration system in FY22 since the previous fiscal year. Agency has continued outreach to eye care providers; provided an informational session during FY21 with plans for another with eye doctors from across the state in FY22.
2C.10 Promote the inclusion of training for DPH Community Health Workers, in both their core competency training and continuing education, the topics of hearing health, aural rehabilitation, vision rehabilitation, use of available technology solutions and a patient long-term support plan incorporating group interventions to improve hearing care treatment, and vision rehabilitation (including services available from the Massachusetts Commission for the Blind, thereby increasing independence and reducing admissions to institutional settings. | DPH, MCB | MCB will provide monthly vision related trainings to new Community Health Workers, and provide at least 15 in-services in consumer settings to enhance the vision related training. | The Board of Certification of CHWs meets monthly and is currently reviewing the application for training programs, which will include submission of their curricula. In FY20, there will be an opportunity to assess current training opportunities and work with the Office of CHWs to support approved training programs in offering topics designed to equip CHWs in supporting individuals’ independent living. All MCB monthly vision related trainings and all in-services were provided. |  | The Board of Certification of CHWs discussed the inclusion of these specific training topics in core competency training during the March 2020 meeting and ultimately decided these topics were a better fit under the 16hrs of special health topics which are required for CHW certification. Although the Board does not mandate what topics those 16hrs should cover it does review proposed topics for each core competency training program seeking Board approval and has agreed these topics would be relevant to the CHW scope of practice. The Board began accepting applications for approval of CHW core competency training programs in Feb 2021 and to date there are two approved core competency training programs in MA. Although neither of these Board-approved training programs currently offers training in these special health topics, they retain the opportunity to do so under any subsequent review year, and the Board is anticipating several more applications in the coming months.
2C.11 Continue and expand DMH Jail/Arrest Diversion Grant Program, which funds local communities/municipalities to train law enforcement and other public safety personnel to: (1) recognize the sign and symptoms of mental disorders, particularly serious mental illness (SMI) and/or serious emotional disturbance (SED); (2) identify person with a mental disorder and employ crisis de-escalation techniques; (3) learn about resources that are available in the community for individuals with a mental disorder; (4) establish linkages with schools, community- based mental health agencies, and to (5) refer individuals with the signs or symptoms of mental illness to appropriate services. | DMH | Expand participation to impact over 75 communities. | DMH has funded 66 communities through FY19 | Expand participation to 100 communities (Yr.2) and 125 communities (Yr.3). Track number persons served and the outcomes to identify best practices. | CY 2020 - 71 communiites participated in JDP grant. CY 2021 - 85 Communities participated in JDP grant. Established a grantee database and created dashboard on the DMH website.
2C.12 Continue DMH provision of funding for: one Forensic Assertive Community Treatment (ACT) Team with Peer support staff; and a Forensic Transition Team (specialty care management service for individuals being release from jails/prisons). | DMH | Serve 850 individuals with MH disorders and criminal justice involvement annually. | DMH served 821 individuals with mental health disorders and criminal justice involvement during FY 2019. | Serve 850 individuals with MH disorders and criminal justice involvement annually. | CY 2020 - 607 individuals served; CY 2021 - 521 individuals served
2D. Improving the Capacity and Quality of Services
2D.1 Bring settings of DDS and MRC residential and other site-based services into compliance with the HCBS final rule by the federal deadline for transition (March 2022), and ensure compliance of new settings, as appropriate. | DDS, MRC | Work with challenged providers on individual transition plans. Work with day providers on enhancing services. Continue surveying providers with strengthened tool to evaluate and ensure compliance. | DDS continues to work collaboratively with providers on achieving the goals set out in their individual transition plans. As of June 2019, one residential provider did not meet the HCBS final rule criteria, based on licensure and certification results. DDS continues to work with this provider to achieve compliance. The final transition plan has been submitted to CMS. The Day/Employment RFR included language and requirements based on the HCBS final rule. All Day/Employment providers are working to achieve compliance with the rule. As of June 2019, the majority of settings were in compliance, based on licensure and certification results. DDS continues to work collaboratively with Day/Employment providers and settings to achieve compliance. All MRC sites are in compliance. | Continue work with providers to complete 50% of the milestones necessary to come into compliance with the final rule. | DDS continues to work collaboratively with providers on achieving the goals set out in their individual transition plans. DDS Licensure and Certification evaluates outcomes related to the HCBS Community Rule on an ongoing basis. The Day/Employment RFR included language and requirements based on the HCBS final rule. All Day/Employment providers are working to achieve compliance with the rule. DDS Licensure and Certification evaluates outcomes related to the HCBS Community Rule on an ongoing basis. All MRC sites are 100% in compliance with the HCBS Final Rule.
2D.2 Invest $83 million to re-design and strengthen DMH’s largest adult community service program to better meet the needs of the approximately 11,000 adults with long- term, serious mental illness enrolled in the program annually. Adult Community Clinical Services will provide: • Clinical services provided by an integrated team 24/7/365; • Individualized care that focuses on Peer Support, includes treatment for SUD as needed and responds to individuals’ needs as they change across the age continuum; and • Focus on achieving greater self-sufficiency, including job placement and education completion. | DMH | New contracts go into effect on July 1, 2018; implement new delivery system, assure adherence to standard implementation tools for all data collection, monitoring and review. | All contracts were procured and are fully operational. | Implement Level of Care Review including housing and community services; develop standard measure of demand & need for affordable housing; Monitor length of stay in Service Types. | Revised Level of Care Review process to establish consisent timelines for review based on
2D.3 Explore strategies to address challenges in attracting and retaining high quality/highly skilled staff across provider agencies, improving training opportunities for staff and/or job applicants to enhance their skills and knowledge, equipping them to successfully serve and support high acuity/high need populations. | EOHHS | Obtain input on recruitment strategies and need for enhanced training and make trainings on social service issues available to staff of service provider agencies. |  | Based on survey results: • Explore feasibility of implementing at least one recruitment strategy. • Work with program agencies to enhance provider training for direct care staff.
2D.4 To support homeless prevention and more effective discharge planning efforts across populations develop new protocols to help ensure that agencies and institutions receiving funding from the Commonwealth must make all legally supportable efforts to ensure that individuals are not discharged to the streets or shelters. | ICHH | Convene working group, identify relevant agencies, and develop outline of contract language required. | Working group convened with support from OSD and state agencies. | Begin requiring use of new contract language and provide training and guidance for agencies and providers.
2E. Promoting Awareness of Community-Based Services
2E.1 EOHHS and EOEA will continue to inform people with disabilities about the opportunities available to them to receive care in the community, including through Self- Directed Care. | Elder Affairs | 93% of consumers (including elders and individuals with disabilities) receiving options counseling services rate the encounter as enabling them to make a more informed choice. | During state FY19 93% of Options Counseling Program survey respondents indicated being better able to make an informed decision about their long term support needs as a result of the counseling they received | 94% of consumers receiving options counseling services rate the encounter as enabling them to make a more informed choice. | During Fiscal Year 2021, 93.4% of Options Counseling Program survey respondents indicated that the counseling was either "extremely helpful" or "somewhat helpful" in enabling them to make better informed decisions about their support needs.
2E.2 Continue optimizing the means by which people with disabilities access community- integrated services, including Self-Directed Care and other supports, and supports of their choice throughout Massachusetts through person-centered, decision-support options counseling services that honor choice and independence throughout Massachusetts. | DDS | DDS has contracted with the Human Services Research Institute to conduct an evaluation and review of the “Real Lives Participant Directed Program.” DDS will publish the results of the evaluation in 2018. | The Human Services Research Institute (HSRI) conducted work related to their three-year evaluation of self-direction program contract to look at the infrastructure of self-direction including service coordination, budget development, service planning, and supports and services. This was presented to the advisory board in June 2019. | Increase the number of new individuals and families enrolled in self-directed care by 120 per year. | During Fiscal Year 2020 there were a total of 253 new individuals enrolled in Self Directed Serivces. During Fiscal Year 2021, there were a total of 197 new individuals enrolled in Self Directed services.
2E.3 Support and expand awareness of newly established “Memory Cafés,” drop-in centers where individuals with memory loss can socialize with their caregivers and friends in a setting outside the home and establish relationships with persons in similar circumstances. | DDS | Continue funding the 11 existing DDS Memory Cafes. Coordinate with ADRCs, MCOA, Area Offices and Regional Offices to publicize the inclusive Memory Cafes. | Funding for the 11 existing DDS Memory Cafes, each of which serves over 100 individuals, has been continued through a dedicated line item, FY20 GAA 5920-3025 “AGING WITH DEVELOPMENTAL DISABILITIES.” DDS and EOEA continue to work with key stakeholders on publicizing the inclusive Memory Cafes. | Continue funding the 11 exisitng DDs Memory Cafes. Ensur that inclusive memory cafes are listed in all Alzheimer's resources, Memory Cafe Directory and Elder resource lists | During the COVID-19 public health emergency, Memory Cafes are no longer being formally funded. DDS is working to develop resources for aging individuals and their aging caregivers including needs assessments, videos and facilitation guides.
2E.4 Build and foster relationships within the disability community as well as identify opportunities to present and/or promote Attainable Savings Plans amongst the community. | Mass Office on Disability (MOD), Massachusetts Educational Financing Authority (MEFA) | Expand awareness of the ABLE Savings Plan (known as Attainable Savings Plan in MA). Conduct regular stakeholder trainings and public outreach events across the state. | MOD provided consultation and guidance to MEFA in its implementation of the Attainable Savings Plan program. MEFA continues to provide regular trainings and outreach events across the state. | Expand awareness by developing a “train the trainer model” designed to empower community-based organizations (CBOs) to advise individuals with disabilities in the local community. Conduct webinars and trainings to support initiative. | 1) MEFA has worked with MOD to make our presentations and website resources more accessible to all. 2) MEFA has continued webinars and in-person trainings through our successful train-the trainer model to expand the reach of providing knowledge and understanding of the ABLE/Attainable program. 3) MEFA will be creating more on-demand webinars within the MEFA Institute so that customers can watch and learn in their own timeframe. 4) MEFA convenes and advisory board to hear more about the needs of different communities so that we may better serve those communities with our expanded resources.
2E.5 Educate state agencies and community- based organizations providing community- based care and housing supports regarding the prevalence of hearing loss and visual impairment across the population and be directed agencies and CBOs to the Massachusetts Commission for the Deaf and Hard of Hearing (MCDHH) and/or the Massachusetts Commission for the Blind for technical assistance. | MCB | Provide monthly In-service training to new employees on blindness | MCB continues to provide the in- services and trainings. | Provide in-service trainings for state agencies and community-based organizations about prevalence of vision loss and visual impairment as well as agency programs and services. | 2) MEFA has continued webinars and in-person trainings through our successful train-the trainer model to expand the reach of providing knowledge and understanding of the ABLE/Attainable program
2E.6 Provide information on community care options and housing supports to Deaf and Hard of Hearing Independent Living Services (DHILS) programs, Independent Living programs, Long-term Care Ombudsmen programs and Aging and Disability Resource Centers. | Olmstead Implementation Committee will identify appropriate agency for this task |  |  |  | 3) MEFA will be creating more on-demand webinars within the MEFA Institute so that customers can watch and learn in their own timeframe.
2E.7 Provide written information about community care options and housing supports as a VLOG in American Sign Language (ASL) and via audio and Braille for people who are blind or have low vision. | MCB | Complete a resource guide in an electronic format and make it available on the MCB website | Resource guide completed. MCB is in the process of hiring a Communications Director who will be responsible for posting and maintaining the guide on Mass.Gov. | Compile and maintain electronic stakeholder resource guide. | 4) MEFA convenes and advisory board to hear more about the needs of different communities so that we may better serve those communities with our expanded resources.
2E.8 Educate EOHHS agency staff and provider organizations on the range of community transportation services that may be available to their consumers. | MassMobility | Offer at least 12 presentations (in- person or by webinar). | Presentations include: • MASILC Conference 9/27/19 • Mass Home Care Conference 9/25/19 • DDS Employment Matters Conference 6/11/19 • Massachusetts Association for Professionals Supporting Employment First Conference 5/29/19 • Adult Family Care Conference, 5/17/19 • Nonotuck staff meeting, 4/30/19 • Community mobility track at the MassDOT Innovation Conference, April 9-10, 2019 • BIA-MA conference 3/28/19 • ICI webinar 3/20/19 • Arc webinar 2/12/19 • MCB Central staff meeting 2/4/19 • Haverhilll Arc peer group 1/15/19 • WWL conference 10/10/18 Brockton DDS staff meeting 9/19/18 | Aim to offer 20 presentations for Year 2, pending requests/invitations for training. | Offered 13 presentations in 2020 and 20 presentations in 2021
2F. Promoting Successful Community Reentry from Incarceration
2F.1 The Department of Corrections (DOC), the Veterans’ Administration, and the state Department of Veterans’ Services identified and developed a comprehensive strategy to increase the number of Veteran Offenders receiving in-reach reentry planning1, community-based referrals, and post release services. | ICHH, VA, DVS and MassDOC | Offer institutional veteran presentations at a minimum of four facilities per year. Benchmark of 90% or greater in attendance. | Progress to date: Old Colony Correctional Center (OCCC) – April 2018 – 26 inmates attended (100%) North Central Correctional Institution (NCCI) – April 2018 – 40 Inmates in attendance (100%). MCI-Norfolk – September 2018 – 47 Inmates in attendance (100%) MCI-Shirley Medium– October 2018 - 26 inmates in attendance (76%). MCI-Shirley Minimum– 10 inmates in attendance (100%). North Eastern Correctional Center– May 2019 – 8 Inmates in attendance (80%) Massachusetts Treatment Center– May 2019 – 33 inmates in attendance (79%). 209 Inmates were scheduled to attend; 190 Inmates attended; To date 91% attended the presentations. Two more institutions to be scheduled in the fall-date TBD. DVS provided a “SAVE 101” to 55 participants at Fort Devens on Nov 1, 2019. Another Battlemind will be conducted in Milford at DOC Headquarters for C.O.’s. The remaining five institutions that have not had the veteran presentations and informational session have a very small cohort. Therefore this population was provided with informational and contact information by institutional staff. Next steps are to schedule the next round of presentations starting at the initial sites (OCCC and NCCI) All Veteran information is available to all DOC institutional staff via Reentry Services Division (RSD) Intranet page and discussion boards. RSD PCIII is monitoring monthly all Veteran releases and corresponding in reach and community referrals for post release services. RSD has instructed all relevant staff to ensure that they are entering all referrals and outcomes into the DOC Inmate Management System (IMS). | Increase from 5 – 10% the number of Veteran Offenders who are aware of and access available resources. | January of 2020: RSD developed posters to be hung in all institutions and common areas to promote the ICHH, VA, and DOC partnerships. In March 2020, our institutions were restricting all individuals from entering the DOC, and this impacted the number of in-reach that occurred. A phased approach to opening the institutions to visitors and partners was rolled out around March 2021, where vender staff returned with strict CDC guidelines with limits on masking and offering packets to continue the in-person programming, but generally, all Local, State and Federal agencies were not permitted by DOC and their own agencies guidelines. In November 2021, vaccinations were mandatory, and there were a lot of staffing reductions. In CY2021, DOC released 51 US veterans, 16 were VA eligible, and 36 DVS eligible; 29 received their DD-214, 46 active MassHealth (1 alt health plan, 2 out of state, 1 refused). Residential housing was made available to 13 of these releases accessing supportive wrap around services through the VA and DVS partnership (5 NECHV, 5 Bedford VA, 1 United House for Veterans, 1 veterans NE outreach center, and 1 Salvation Army).
2F.2 Pilot informational presentations in two DOC facilities with the largest number of incarcerated veterans twice per year in 2018. There will be an evaluation of the presentations by the veteran inmates to determine the value and efficacy for expansion to other DOC facilities as well as on- going bi-annual presentations and workshops. | DOC | Pilot a Veterans Partnership Reentry focused presentation and Q&A sessions at 4 State Correctional facilities. Track percent of invitees that attend. Assess Veteran’s inmates opinions and feedback regarding utility of information presented. | Completed Presentations to date. Evaluations resulted in a rating of 4.2 out of 5.0. Largest feedback was providing an avenue for agencies to follow up to be discussed. | Continue offering Veterans Reentry presentations at 4 State Correctional facilities each year. Modify content based on participants’ requested needs and feedback from previous sessions.Track percent of invitees that attend. | The pilot program for the partners was a great success in the 2018 and 2019 cohorts. However, with CDC COVID restrictions, this initiative needed to be placed on hold.
2F.3 Enhance Department of Corrections (DOC) reentry programs, including counseling individuals with disabilities leaving incarceration and enrolling them as permitted by the inmate in all benefit programs to which they may be entitled including MassHealth, SSI, SSDI, VA benefits and services provided by DMH and DPH as well as DTA cash assistance. | DOC/MassHealth/DMH/DPH/DTA | Decrease refusals for Medical and Mental Health Appointments in the community from 17% to 10% and 23% to 15% respectively. Continue to monitor MassHealth Applications and status at release and develop strategies to decrease pending applications from 5% to 2%. | MassHealth has implemented a process by which it processes MassHealth applications for individuals leaving DOC custody within 3-5 days. As a result, there is no MassHealth application backlog for individuals leaving DOC custody. MassHealth continues to work with DOC to reactivate community MassHealth coverage for individuals at reentry and the success rate continues to be very high. | Monitor refusals for Medical and Mental Health appointments in the community to be sure that levels do not exceed 10% and 15% respectively. Continue to monitor MassHealth Applications and status at release and maintain level of pending applications at no more than 2%. | MassHealth continues to be a reentry initiative that the DOC holds as critical for the public health needs of our releasing population. CY 2020 92% of eligible inmates had approved MassHealth on the day of their release according to MassHealth’s data obtained through MMIS and MAP portals; the reasons for lack of approvals are 1 released out of state so became not eligible, 5 ineligibles due to income (1%) and 3% pending .CY 2021 98% approved, 1 out of state so became ineligible, 1 ineligible due to income, and 1% pending (goal achieved)
2F.4 Develop model for identifying and providing specialized behavioral health and coordination services for justice-involved individuals with serious mental health and addiction needs, ensuring access to services to improve health outcomes. | MassHealth | Measure the number of justice- involved MassHealth members served during Project Year 1, the variety of correctional institutions served, (DOC and HoC), the level of supervision received, and early findings on various member outcome rates (such as housing, employment, recidivism, engagement in treatment, sobriety and health care utilization | To implement this project, MH is in the process of procuring a vendor that will perform the tasks described in the year 1 measure. MH expects this vendor to complete all of these tasks by the end of CY19. MassHealth developed and issued a procurement for Behavioral Health Supports for Justice Involved Individuals (BH-JI), and contracted with two providers in Worcester and Middlesex Counties who have begun enrollments. MassHealth has developed an evaluation plan with UMass to examine enrollment demographics, measure MassHealth utilization, track outcomes and determine best practices for new providers in additional areas of Massachusetts. | Measure the number of justice- involved MassHealth members served during Project Year 2, the number of counties served, the variety of correctional institutions served (DOC and HoC), the level of supervision received (Probation and/or Parole), and early findings on various member outcome rates (such as housing, employment, recidivism, engagement in treatment, sobriety, and health care utilization). | By end of SFY21, 1040 people had enrolled, 60 from Middlesex Sheriff's Office, 153 from Worcester Sheriff's Office, 336 from Probation (including 3 Community Justice Support Centers and 21 courts), 50 from Parole (incl. 4 regional offices, 138 from DOC (incl 10 institutions), 193 from community sources, and 110 from other counties. MassHealth developed and issued a procurement for statewide expansion of BH-JI and submitted a request to CMS for the community supports (what will be Community Support Program for Individuals with Justice Involvement). Some findings from the Demonstration: Approximately two-thirds of people who are referred to the program enroll, and those who enroll participate for six months on average; After six months, individuals who have stable housing increased by 20% and individuals who were employed increased from 27% to 38%; About two-thirds of enrollees were engaged in outpatient behavioral health care, and over 25% were receiving medication assisted treatment for substance use; Individuals enrolled in BH-JI have also had significant decreases in inpatient behavioral health hospitalizations, emergency transportation, and emergency department utilization; and The average cost per member per month for inpatient services reduced by 47% , while outpatient services increased by 39%.
2F.5 Develop and implement a systematic process to suspend MassHealth benefits for individuals who are incarcerated and sentenced, and upon release reset to status prior to incarceration or reassessed if incarcerated for over a year. | MassHealth | Enter into data use agreements with correctional institutions. | As of September 30, 2019, MassHealth has entered into data sharing agreements with DOC and all but one house of corrections (which declined to enter the agreement) to streamline the data transfer process. | Measure the number of individuals tracked and analyze MassHealth health care utilization for tracked individuals. | There are about 3,300 individuals with incarceration designation at any point in time in the MassHealth system. Some analysis of this population requires clarification, however the recent 1115 application requests improvements to MassHealth eligibility for this population which will facilitate improved tracking and care management for the re-entry populations.
2F.6 Continue to establish partnerships between DOC and other agencies in the community, both public and private, to promote the successful community reintegration of high risk/high need populations released from incarceration. | DOC | Develop and implement an approval process for each State Correctional facility, to identify and track the # of external partners/agencies providing in-reach and or community services to high risk/high need populations. | An approval process for clearance to enter DOC institutions established as follows: Either a 40 hour training/orientation or the individual enters as volunteer. The following external stakeholders that provide in-reach or community supportive services are as follows: In reach: Thrive, Safe and Supportive Youth Initiative (SSYI), Thrive, VA, DVS, MassHire, DOR, UTEC, BHJI, CRJ, Community Supportive Services: SSA MassHealth, RMV CCC. | Analyze Yr. 1 data, identify gaps in partner agencies providing in-reach services and foster relationships to address those gaps at each facility. | At this time, in-reach has been minimal. However, RSD PCIII has developed a ZOOM call schedule to allow in-reach to happen in the institutions. This schedule will ensure that inmates receive in reach with their respective clients at least 3 times prior to release and then into the community. When this schedule has been tested, we can expand it to our other community stakeholders.
2F.7 Increase awareness of Substance Use Disorder (SUD) within the EOEA target population through training for elder care providers to identify SUD and community resources and to develop models of SUD services targeting EOEA population. | Elder Affairs / MRC | Identify training needs and curriculum | 1) Curriculum was developed from evaluation input of 750 community based providers within the Aging and Disability network. 2) Established 5 regional meetings throughout the Aging and Disability network where SUD presentations will be on the agenda to educate approximately 200 people through 2020. 80 Master’s level professionals from across the state (representing 15 community agencies, 3 major hospitals and 5 state agencies) are undergoing an intensive 8 day clinical training to more effectively work with people who have a dual diagnosis of Substance Use Disorder and Brain Injury. | Integrate cross-system training within the “Aging with Dignity” conference in 2020 for over 200 attendees from elder services, statewide community centers on aging, substance use treatment and prevention programs, and other professionals. | MRC received an ACL grant and has assembled a workgroup with representation across the state identifying barriers to services and ways to eliminate the barriers and make these services accessible. The goal is to develop and implement a series of learning opportunities by the end of the grant year in 2026.

## Goal 3
GOAL #3: Promoting Community-Integrated Employment of People with Disabilities
Activity | Responsible Agency(ies) | Year 1 Measure | Year 1 Progress to Date | Year 2-3 Measure | Year 2-3 Progress to Date
3A. Improving Access to Gainful Employment and Employment Support
3A.1 Launch interagency initiative of co-case management between Department of Transitional Assistance (DTA) and MRC designed to provide vocational and employment services to DTA clients with disabilities, enhancing their ability to achieve economic self-sufficiency. | MRC, DTA | MRC will fully implement the MRC/DTA employment initiative in select offices. MRC to track number DTA clients: • Referred to MRC • Eligible for Voc Rehab • Employed | MRC and DTA renewed an Inter-agency Service Agreement continuing an employment initiative to serve mutual consumers in their efforts to choose, obtain and maintain employment. | MRC and DTA will evaluate the success of the program, and if successful, will determine feasibility to expand to additional offices. | MRC and DTA have seen success in placing DTA clients with disabilities in employment. A plan is currently being developed to expand to additional offices. To date 458 individuals have been served and 152 have been placed in competitive employment.
3A.2 Collaborate with Career Centers to promote further access and enhance their capacities to create employment opportunities for individuals with disabilities and to ensure One-Stop Centers are accessible. | MassHire Department of Career Services MassHire Workforce Boards MassHire Career Centers | Local Boards and Career Centers establish a plan with goals and benchmarks for WIOA Section 188 accessibility. MOD will continue to partner with EOLWD in addressing accessibility issues as they arise. | The 16 MassHire Workforce Boards have established local inter-service agreements with MRC and MCB for their evaluations and recommendations regarding assistive technologies at MassHire Career Centers. MRC and MCB staff also coordinate with MassHire Career Center staff to provide services to individuals with disabilities on-site at career centers and through referrals. Number of individuals with a self- reported disability served at MassHire Career Centers: FY18 (July 2017- June 2018): 8,519 FY19* (July 2017- March 2019): 8,595 Number of individuals with a self- reported disability who obtained employment in the 2nd Quarter after Exit: FY18 (July 2017- June 2018): 4,006 FY19* (July 2017- March 2019): 3,891 *FY2019 is a partial year. MDCS MassWorkforce Policy 100 DCS 08.109, Accessibility within the Massachusetts Workforce System WIOA Section 188, issued January 25, 2018, is directed toward ensuring that the programs, services and facilities of each MassHire Career Center and any ancillary service delivery system are accessible to all, including individuals with disabilities. MassHire Workforce Boards and MassHIre Career Centers are monitored for adherence to this policy directive. | Local Boards and Career Centers demonstrate measurable progress in WIOA Section 188 accessibility. MOD will continue to partner with EOLWD in addressing accessibility issues as they arise.
3A.3 EOEA will continue to support low income older adults with barriers to employment through the Senior Community Service Employment Program (SCSEP). SCSEP matches older adults with part-time jobs at community service assignments. | Elder Affairs | EOEA will support an estimated 150 older adults with employment barriers in obtaining part-time employment. | From 7/1/19-YTD EOEA supported 123 older adults with significant employment barriers in obtaining part-time employment. | Pending the continued availability of federal funding, annually EOEA will support an estimated 150 older adults with employment barriers in obtaining part-time employment. | From July 1, 2020 through December 31, 2021, SCSEP supported 163 peoples ages 55 and older with significant barriers to employment. Due to the COVID-19 pandemic, many of these participants received training virtually due to onsite work closures at Host Agencies (employers). Additionally, EOEA received a SCSEP demonstration grant from the US DOL to start a remote employment training program with the goal of training 60 low-income people ages 55 and older in remote work. The program began in September 2020 and to date, 38 people have enrolled.
3B. Increasing Access to Vocational Rehabilitation Services and Career Planning
3B.1 Develop a customized MRC employment and peer support model in collaboration between Vocational Rehabilitation and Independent Living Center programs to address the high rate of unemployment amongst individuals with disabilities and to reduce the number of individuals that rely on public benefits. | MRC | As grant ends in December 2018, MRC will build in lessons learned from the grant to assist people with disabilities to live and work in the community. | MRC has developed a support services as part of a new RFR. | Lessons learned, and new practices will be further applied and implemented as part of MRC staff/counselors training. | MRC completed its grant with the Kessler Foundation and the lessons learned on mentorships and peer mentoring has been incorporated into MRC programs.
3B.2 Led by Autism Commission, develop additional materials and trainings regarding the employment training needs and supported employment opportunities needed by individuals with ASD. | Autism Commission | Develop training for providers of employment training. | The Autism Commission’s subcommittee that focuses on employment has created a training for DDS and its providers regarding autism in individuals 14-22 years+. In addition a survey was developed and issued to MRC Pre-Ets providers. The results of that survey are being used by the Federation for Children with Special Needs and Boston Medical Center’s Autism program to design a training for MRC’s providers working on employment skills with individuals with ASD | Assess the impact of the training, as measured by providers reported increase in knowledge on the range of needs of individuals with ASD to prepare them for employment opportunities and maintaining employment. | Working with the Asperger/Autism Network (AANE), a series of training workshops and webinars were provided to MRC staff and MRC provider staff in 2020 and 2021 focusing on Autism and employment, these workshops focused on key features of autism, how those features impact employment, and what strategies best support success. AANE also hosted a virtual conference on Autism and employment, including MRC providers, and has developed e-learning for professionals working to assist people with Autism to find employment.
3B.3 Continue to promote the employment of persons in recovery and peers in the community through Recovery Coaching programming and existing federal grants. | DPH | Document peer recovery workforce to determine employment and skill building needs. | DPH Bureau of Substance Addiction Services has conducted a scan of recovery coaching in the state which was shared with the Recovery Coach Commission. The scan included information on where Recovery Coaches are being hired, their roles, their salaries, current training, and FY18 billing. In the process of creating a Recovery Coach/Recovery Coach Supervisor Hub that will include a registry section for people who have taken the RCA outside of BSAS/AdCare. The Hub will strengthen the statewide recovery coach network, provide resources and be a registry. | Develop and implement models for accessing employment resources. | An updated RC Scan was completed over the summer of 2021 and the report is available as requested. The Recovery Coach Hub is up and running at https://massrchub.org/ and includes resources for any Recovery Coaches and Supervisors working in MA, including information about joining regional Recovery Coach Learning Communities.

## Goal 4
GOAL #4: Investing in Accessible Transportation for Individuals with Disabilities
Activity | Responsible Agency(ies) | Year 1 Measure | Year 1 Progress to Date | Year 2-3 Measure | Year 2-3 Progress to Date
4A. Continue to help build the capacity of the Massachusetts community transportation network. | MassDot | Distribute an estimated $10 million in Community Transit Grant Program (CTGP) funds available for capital and operating enhancements to meet mobility needs of seniors and people with Disabilities. | In FY 2019, MassDOT distributed $9.3 million from federal and state sources for improving transportation for individuals with disabilities and older adults. (vehicles: $8M; Operating projects: $591K, Mobility Management: $664K). In FY 2020, MassDOT will distribute $9.714 million from federal and state sources for improving transportation for individuals with disabilities and older adults. Allocation distribution for vehicles, operating and mobility management projects will be available by Dec 31, 2019. | Distribute an additional estimated $10 million (total of $20 million) in Community Transit Grant Program (CTGP) funds available for capital and operating enhancements to meet mobility needs of seniors and people with Disabilities. | In FY21, MassDOT dispersed $10.2 million for cities, towns and nonprofit organizations under the Community Transit Grant program to improve transportation for older adults and people with disabilities (vehicles: $7.5 million; $2.1 million for operating; $616k for mobility management). In FY22, MassDOT dispersed $8.9 million in funding to improve transportation and access for older adults and people with disabilities (vehicles: $7.5 million; operating: $1.1 million; mobility management: $300k)
4B. Help build the capacity of the Massachusetts community transportation network by sharing best practices and addressing gaps in transportation for people with disabilities | MassMobility | Publish 2 reports highlighting best practices and/or opportunities to improve mobility. Update MassMobility website to ensure information is accurate and comprehensive. Create a set of train-the-trainer tools to help human service agencies institutionalize an understanding of how to help consumers find and use community transportation services. Highlight best practices in the monthly MassMobility newsletter; increase subscribers by 5% annually. Provide technical assistance as requested to help state agencies such as MRC or DDS or provider organizations improve mobility and access for people with disabilities. | Report on partnering with TNCs published April 2019. Whitepaper on volunteer driver programs published June 2019. Updated website summer/fall 2018. Online training will be published by November 1, 2019. Newsletter published monthly Currently at 1504 subscribers as of 11/5/19. Wrote and published a one-pager on transportation for transition-age youth for the DDS- led Massachusetts Partnership for Transition to Employment initiative. | Pilot, revise, and disseminate train-the-trainer tools to help human service agencies better assist consumers in finding and using community transportation. Highlight best practices in the monthly MassMobility newsletter; increase subscribers by 5% annually. Provide technical assistance as requested to help agencies and provider organizations improve mobility and access for people with disabilities. | Train-the-trainer tools online at www.mass.gov/manual/transportation-training-for-staff-of-aging-and-disability-service-providers; MassMobility newsletter published monthly with 1650 subscribers as of 1/18/22 (approximately 10% increase since November 2019); Provided technical assistance as requested to aging & disability services agencies including partnering with MRC to review and improve the transportation content on both MRC and MassMobility's websites (late 2019/early 2020)