## Slide 1
Office of Performance Management & Oversight
Massachusetts Technology Collaborative
Fiscal Year 2025 Report

## Slide 2: CAM Operating Funding
Description: The Center for Advanced Manufacturing (CAM)’s mission is to foster the most complete, most connected, and fastest manufacturing ecosystem from innovation through production. CAM will build on the success of the Massachusetts Manufacturing Innovation Institute Program (M2I2) and increase its impacts on the manufacturing sector by: aligning investments in manufacturing with the state’s vision; leveraging existing programs for increased regional impact; supporting new initiatives from the Advanced Manufacturing Collaborative (AMC); ensuring a deep pipeline for all programs; and tracking outcomes and efficacy of all programs.
Assessment: Registration opened for the 2025 Manufacturing Mash-Up (10/21/25) at Gillette Stadium. The CAM team developed plans for content sessions that address the most important topics in manufacturing today (including supply chains and technology adoption). Executing on Q4 planning carries over into the start of FY26 Q1. The team will continue to line up high-impact speakers, arrange award ceremonies (including the 10th annual Manufacturing Caucus Awards, MMAP award announcement, and a 10 year M2I2 celebration) and secure sponsors for the event. The event is on track to have 1500 attendees across the manufacturing ecosystem.
FY25 Budget: $1,200,000
Key Performance Metric | Key Performance Description | Target | Result | Comments
Foster the advanced manufacturing ecosystem in Massachusetts and facilitate relationships and collaboration between industry, academia, and government through an array of manufacturing and STEM events. | Host and attend events and engagements to support the manufacturing ecosystem. Host events and webinars, attend and speak at relevant external events, and conduct site visits among manufacturers and workforce training providers. Events and engagements could include EWD, technology, cybersecurity, or other advanced manufacturing topics. | Host 2 engagements per quarter Attend 3 stakeholder events per quarter Conduct 5 site visits per quarter Goal total = 40 | 112 | FY25 totals: Hosted 16 engagements Attended 62 engagements Conducted 34 site visits
Showcasing the Massachusetts advanced manufacturing ecosystem by bringing industry, government and students together at the Manufacturing Mash-Up. | Spur economic growth within companies and interest in advanced manufacturing career opportunities for students, increasing previous years' impact | 1500 attendees from across industry, academia, high schools, and state leadership | 0 | The 2024 Mash-Up drew over 1700 attendees to Gillette stadium. Registration for the 2025 Mash-Up, which will take place on Oct 21, 2025, is open. As of August 2025, over 400 people have registered, with a goal of bringing 1500+ attendees together.
Inclusive geographic engagement of the state's advanced manufacturing ecosystem. | Consideration of CAM activities across different regions of the state (e.g Advanced Manufacturing Collaborative meeting locations). Reported annually. | Engage all regions of the state | 1 | In FY25, CAM hosted several events outside of Greater Boston, including: the 2024 Manufacturing Mash-Up in Foxborough, the 2024 MassMakes Innovation Challenge in Springfield, the Q1 AMC meeting in Foxborough, the Q4 AMC meeting in Springfield, the Annual MA Advanced Manufacturing Training Strategic Planning Meeting in Worcester, the MMAP Award Announcement Event in Worcester. In addition, CAM hosted several webinars, including the Tariff Response and Business Operations Support Initiative webinar on state resources and the webinar about applying to the AMTG grant, where we had attendees from across the state. The team successfully engaged all regions in the Commonwealth.

## Slide 3: Innovation Institute
Description: The Innovation Institute works to align state support for the research, technology and business development, capital, talent and other infrastructure needs necessary for vibrant ecosystems for innovation across the Commonwealth. As an agent of the Commonwealth, the Innovation Institute uses this model to fuel economic growth, create wealth and generate improvements in the regions’ standard of living. These efforts are often focused on Regional Support, Entrepreneurship and Start-Up Support and Cluster Development with a focus on technology verticals such as FinTech, Artificial Intelligence, Quantum Computing, Robotics and Blockchain.
Assessment: The Innovation Institute made 5 awards in Q4 totaling $359,999. This includes Quantum Conference Development (Nov. 20, 2025) which will connect high profile stakeholders from Boston with stakeholders from various of regions of Massachusetts; and various sponsorships focused on Women's Leadership, Blockchain and Entrepreneurship. In addition, this program funded a pilot program: the High School Summer Career Academy in Artificial Intelligence (AI), an enrichment program that will engage 50 high school students from school districts in Greater Boston, including schools from the Title I districts of Chelsea and Revere.
In January 2025 (FY25 Q3), the Innovation Institute launched a new solicitation (Massachusetts Tech Hubs) that leveraged the Innovation Fund to make awards that complimented and supported the development of technology clusters. The Innovation Institute received approval of 9 awards totaling over $15M at MassTech's July Board meeting, these awards are accompanied by 14 Tech Hub Designations. This fund specifically supported 3 awards (totaling $600,000) for operating expenses tied to Advanced Optics, Marine, and Biomanufacturing TechHubs.
FY25 Budget: $2,500,000
Key Performance Metric | Key Performance Description | Target | Result | Comments
Support growth in key industry clusters that comprise the state's tech and innovation economy by working with stakeholders to develop economic development strategies and projects that generate economic growth in Massachusetts. | 50 businesses and stakeholders engaged and participating in key cluster development activities. | 50 | 635 | Nine events were sponsored in FY25: Boston Blockchain, Corporate and University Blockchain Series, FinTech Sandbox, Women in Robotics, Women in Leadership Impact Study and Event, The Innovation UnConference, Tufts Fashion Sense Reception & Showcase, RoboBoston and a Quantum Award Announcement. These events convened hundreds of individuals and stakeholders from these clusters
Support regional growth across the state in key industry clusters that comprise the state's tech and innovation economy | 12 regional initiatives outside the Boston area created, retained or expanded. | 12 | 14 | Events included Boston Blockchain, AI Strategic Task Force Capstone Event/ Governor’s AI Recommendation Announcement @Museum of Science, Fintech Sandbox, Women in Robotics , RoboBoston / Cybernetixs Robotics Invest Summit - Blockchain - University and Corporate Blockchain series - Western New England Fintech and AI incubator support; Gloucester Marine Technology Support (eDNA); Quantum Computing Conference Development Award, and their locations spanned from Andover, Burlington, New Bedford, Beverly, Gloucester, Amherst, Sandwich, Chatham, Marblehead, Worcester, Watertown, Springfield, Quincy, to Medford.

## Slide 4: Advanced Manufacturing Training
Description: The Advanced Manufacturing Training Program (AMTG) provides funding to qualifying consortiums to develop, coordinate, and maintain comprehensive manufacturing workforce development systems. Regional systems will provide workforce development services in advanced manufacturing, such as recruitment, job training, placement activities, and supportive services. The program focuses on providing training to unemployed and underemployed individuals, and underrepresented populations including: veterans, minorities, and women.​
Assessment: The Advanced Manufacturing Training Grant reopened on January 27, 2025, and the deadline for submissions was May 16, 2025. In Q4, the Advanced Manufacturing Review Team reviewed all submitted applications and convened to evaluate proposals and develop funding recommendations. Following deliberations, a grant recommendation memo was submitted to EOED on June 25, 2025. This memo included five recommended awards and one application requiring MassTech board approval.
FY25 Budget: $2,500,000
Key Performance Metric | Key Performance Description | Target | Result | Comments
Respond to manufacturing workforce needs by providing access to training and employment opportunities. | Increase access to manufacturing training programs and support services across MA to increase number of individuals completing training and obtaining a job in manufacturing. | 250 persons enrolled in training 200 persons who completed training 175 (80%) who obtained employment in manufacturing after training | 274 persons enrolled in training 229 Persons who completed training 109 (38%) who obtained employment in manufacturing after training | Complete data on program completion becomes available up to 15 months after award. FY25 training numbers are reflective of activity from programs that are ongoing. For more than half of these training providers, they will not provide final training and placement numbers until September 30, 2026.
Host and attend events and engagements to increase coordination and partnerships among manufacturing training efforts. | Work collaboratively with other state training partners (CTI, Community Colleges, MassMEP, etc.) to increase coordination and access to manufacturing training programs across the state. Actively convene these partners and look for opportunities to advance the goals of AMTG while supporting other efforts in the state. | Host or attend at least four convenings | 4 | In FY25, hosted four convenings: Statewide Advanced Manufacturing Strategic Planning meeting, MassBridge Business Industry Leadership team KSA meeting, Statewide Manufacturing Apprenticeship Meeting, TechAmp industry council meeting
Inclusive geographic engagement of the state's advanced manufacturing ecosystem. | Consideration of CAM activities across different regions of the state (e.g Advanced Manufacturing Collaborative meeting locations). Reported annually. | Engage all regions of the state | 1 | In FY25, CAM hosted several events outside of Greater Boston, including: the 2024 Manufacturing Mash-Up in Foxborough, the 2024 MassMakes Innovation Challenge in Springfield, the Q1 AMC meeting in Foxborough, the Q4 AMC meeting in Springfield, the Annual MA Advanced Manufacturing Training Strategic Planning Meeting in Worcester, the MMAP Award Announcement Event in Worcester. In addition, CAM hosted several webinars, including the Tariff Response and Business Operations Support Initiative webinar on state resources and the webinar about applying to the AMTG grant, where we had attendees from across the state. The team successfully engaged all regions in the Commonwealth.

## Slide 5: Internships & Mentorships
Internship
Description: The MassTech Intern Partnership (MTIP) provides stipends to support interns at Massachusetts tech start-ups. The goal of this program is to promote the growth of start-ups, especially in priority sectors, such as Robotics, Digital Health, Cybersecurity, FinTech, Quantum, and Advanced Manufacturing, and retain talent by supporting more internship opportunities that will root student’s technology industry networks in state and lead to them staying in Massachusetts after graduation.
Assessment: The program has received 129 applications so far and will continue accepting applications through the end of August 2025. In addition, the Tech Connect Internship Program (sent to EOED for approval in Q2 FY25) resulted in five proposals. Contracting is underway with the two selected applicants (Greenfield Community College & Benjamin Franklin Cummings Institute of Technology) and is expected to be completed in Q1 FY26.
Mentorship
Description: The Entrepreneur Mentorship Fund strengthens Massachusetts' innovation economy by equipping diverse entrepreneurs and high-growth startups with essential mentorship and resources, fostering resilient regional ecosystems that support business growth across the Commonwealth. Funds from the FY25 Mentorship program funded the Innovation Institute's new Sector Spark program. Sector Spark provides grant funding to support Entrepreneur Support Organizations (ESOs) in Massachusetts as they develop targeted mentorship and entrepreneurial programs for tech-based startups within critical sectors. By enhancing startup access to resources, networks, and specialized industry support, the program aims to drive innovation, job creation, and economic growth in regional priority industries.
Assessment: In FY25 the Mentorship Program is wrapping up its Strong Entrepreneur Ecosystem grant awards that have been active since FY23 and announced a new grant program called Sector Spark. All of the Strong Entrepreneur Ecosystem projects have now been fully executed with the final open award (Venture Forum) concluding its grant funded activities in Q4. The Sector Spark grantees (LabCentral, InnoVenture Labs, Sundai Club, and SeaAhead) have all signed their contracts and several projects are underway. The first project status reports are in Q1 FY26.
FY25 Budget: $1,350,000

## Slide 6: Internships & Mentorships: Results
Key Performance Metric | Key Performance Description | Target | Result | Comments
Aid Entrepreneur Support Organizations (ESOs) or other civic, nonprofit, or academic institutions in their efforts to develop regional entrepreneur ecosystems, generating local entrepreneurial growth and productivity. | Enable partner organizations to strengthen programs and expand engagement with startups | 30 | 42 | Engaged with 42 ESOs through the Sector Spark application process. Selections for the Sector Spark awards include Lab Central, InnoVenture, Sundai Club, and SeaAhead.
Support mentoring and entrepreneurship programming with a focus on models that expand access to entrepreneurship within underserved regions and populations. | Reach diverse entrepreneurs around the state | 40 | 132 | 14 female entrepreneurs supported by CWE Power Forward Accelerator; 10 entrepreneurs in Venture Form's Startup Worcester program; 5 entrepreneurs in Venture Forum's mentor match program; 8 entrepreneurs in Venture Forum's 5 Minute Pitch; 6 entrepreneurs supported in Venture Forum's WooTank; 89 entrepreneurs supported by The Sphere and featured on their female businesses trail map. Sector spark metrics will be reported in Q1 FY26.
Jobs Created by Program-Supported Startups | Provides a clear indication of the program’s contribution to job growth in Massachusetts. | 100 | 151 | 38 MTIP interns were retained at the end of their internship. 15 jobs created by companies participating in Venture Forum's 5 Minute Pitch. 98 positions were created by startups participating in programs run by Mentorship grantees. Please note that this is an estimated figure as the positions were not financially supported by MassTech, but rather downstream employment made possible through participation in Mentorship grants.
Support high level quality internships at technology start-ups and scaling companies in key clusters to increase opportunity for entry level employment in MA. | 100 internships placed at quality MA-based technology firms | 100 | 113 | 
Engage new technology start-ups. | 30% of companies participating in MTIP are first time participants | 0.3 | 0.49 | 30 companies (49% of total) participating in MTIP were first time participants

## Slide 7: Cybersecurity Workforce and Infrastructure
Description: The MassCyberCenter is supporting the launch of statewide programs to promote the development of a diverse cybersecurity workforce and improve local cyber resiliency in the Commonwealth through the establishment of Security Operations Centers (SOCs) and Cyber Ranges at colleges and universities. The MassCyberCenter has funded the non-profit CyberTrust Massachusetts to provide local governments, non-profits, and small businesses with affordable cybersecurity services to manage their defenses and combat growing cyber threats. Cybertrust has conducted 35 assessments of communities in Massachusetts and is currently providing Managed Detection and Response services, which protects more than 1700 computers at six entities.
Assessment: Cyber SOC/Range: As of June 30, 2025, the CyberTrust SOC is providing Managed Detection and Response (MDR) subscription services to 12 entities (11 municipalities), which includes protecting 4,279 computers, laptops, and servers from ransomware, state sponsored groups, and criminal organizations. The program continues to engage with the CyberTrust Consortium to track metrics through the fiscal year close including number of persons trained, job placement, and certifications earned. In June 2025, CyberTrust opened a new SOC provided by Rapid7 in their corporate HQ above North Station in Boston.
Cyber Resilient Massachusetts Grant Program: The team engaged in a program re-design process to add Managed Detection and Response for Municipalities, Small Business, and Non-profits. The updated Notice of Funding Opportunity was approved by EOED in February 2025. As a result, MDR is now included as an approved type of project. This program was added to the Massachusetts Business Front door. Applications remain open and 58 applications have been received as of the June 30, 2025 quarterly review deadline. 45 (21 MDR) applications have been approved to date and contracting/awarding is ongoing. Types of projects include: Managed Detection and Response, Network Infrastructure Upgrades (firewalls, switches), Security Controls Implementation, Web Application Upgrades, and Computer and Server Upgrades. For MDR awards, MassCyberCenter has a formula of having the awardee match dollars in our grant with approximately two dollars of their own funding. Thus far, for MDR grants, MassTech has committed $323,486 and has secured $648, 372 from non MassTech matches. The grant program will result in approximately 18 entities and 5,000 computers subscribing to the Cybertrust SOC, which will bring total endpoints under management for CyberTrust to approximately 9,300.
Alternative Cyber Career Education (ACE) Grant Program: Applications closed on December 31, 2024 and review of the 11 applications received concluded with MassCyberCenter issuing four awards. A grant memo describing awards was approved by EOED in late February. Four grants were awarded to Burlington High School, ISACA, Per Scholas Great Boston, and Westfield Technical Academy. As of June 30, 80 individuals have received training through these grants.
FY25 Budget: $950,000
Key Performance Metric | Key Performance Description | Target | Result | Comments
Establishing operational capacity for SOCs and sustainment of growth of cybersecurity range program. | Achieve at least 750 total users of cyber range services including students and professionals seeking cybersecurity upskilling. | 750 | 3210 | Exceeded FY25 cyber range user goal.
Establish strong outreach with municipalities, small businesses, and non-profits and deliver services through CyberTrust Massachusetts. | Provide cybersecurity assessment or monitoring services to 25 municipalities, small businesses, and non-profits through CyberTrust Massachusetts. | 25 | 35 | Exceeded FY25 assessment and monitoring goal.

## Slide 8: Massachusetts Manufacturing Accelerate Program (MMAP) & Massachusetts Manufacturing Innovation Initiative (M2I2)
Program Description: The Massachusetts Manufacturing Innovation Initiative (M2I2) provides state grant funding to help Massachusetts innovators who are ready to begin manufacturing their hard-tech technologies. The Massachusetts Manufacturing Accelerate Program (MMAP) aims to help Massachusetts-based small to medium-sized manufacturers prepare their businesses to meet the demands of Industry 4.0 and the manufacturing of new technologies and innovations that align with key industries in the state. The Manufacturing Cybersecurity Program (MCP), an MMAP program, provides up to $30,000 in capital cost share for cybersecurity infrastructure improvement projects located within the Commonwealth’s borders, as part of the state’s on-going commitment to the manufacturing industry.
FY25 Budget: $16,675,000
Key Performance Metric | Key Performance Description | Target | Result | Comments
Geographic diversity of investments across programs | Consider concentration of awards in Western Mass, Central Mass, the Northeast, the Southeast/Cape & Islands between MMAP, MCP, and M2I2 | 30 | 0 | Evaluated annually
Generate co-investments through MMAP | At least 30% of awards have exceed the required 1:1 match for FY25 investments | 30 | 0 | Evaluated annually
Generate co-investments through MCP | At least 30% of awards have exceed the required 1:1 match for FY25 investments | 30 | 0 | Evaluated annually
Generate co-investments through M2I2 | At least 30% of awards have exceed the required 1:1 match for FY25 investments | 30 | 0 | Evaluated annually
Increase cybersecurity awareness at SME manufacturers through MCP | At least 15 manufacturers completed required cybersecurity assessments annually | 15 | 0 | Evaluated annually
Number of scientists, engineers, technicians, or others, through M2I2 | At least 75 people hired or retained annually by current M2I2 awardees (includes past program years with active contracts) | 75 | 0 | Data collected annually
Number of highly skilled manufacturing technicians, or other, through MMAP | At least 100 people upskilled, retained, or hired annually by current MMAP awardees (includes past program years with active contracts) | 100 | 0 | Data collected annually

## Slide 9: Middle Mile
Description: The MassBroadband 123 network is an open access, fiber-optic middle mile network that passes through 120+ communities in western and north central Massachusetts that commenced operations in 2014. It is used as a building block to design and build last mile connections to residents and businesses in the regions still lacking high-speed internet services. The network consists of approximately 1,200 miles of fiber and directly connects more than 1,000 community anchor institutions. The network is currently operated by Local Linx. IPSs can purchase dark fiber connections, high speed lit services, and collocation services to house equipment within MassBroadband 123 facilities.
Assessment: MBI and Local Linx have fully executed the 5-year Network Operator Agreement. For every CAI taking service, a connection is required at the Point of Interconnection and at the Community Anchor Institution. MBI is tracking progress for both types of connections. 349 out of 485 CAI installations have been completed on the POI side and 54 of 485 have been completed on the CAI side.
FY25 Budget: $2,100,000
Key Performance Metric | Key Performance Description | Target | Result | Comments
Core network availability | The MassBroadband 123 network will operate without any material disruptions of service to broadband subscribers as measured by core network availability of not less than 99.999%. | 99.999% | 99.64% | Through June 2025, multiple outages at major core POI sites (e.g. Springfield and Northampton) affected June's Core Availability statistic.
Access network availability | The MassBroadband 123 network will operate without any material disruptions of service to broadband subscribers as measured by access network availability of not less than 99.95%. | 99.95% | 99.97% | Through June 2025

## Slide 10: Collaborative Research and Development Matching Grant (R&D) & Tech and Innovation Fund
Description: The Collaborative Research and Development Matching Grant Program supports large-scale, long-term projects that bring together the Commonwealth’s world-class research institutions and class-leading companies and have the potential to spur innovation, promote workforce and cluster development, and grow jobs by investing in critical research and development (R&D) infrastructure. The Tech and Innovation Ecosystem Grant Program is designed to support innovation-based economic development, within the technology and innovation ecosystem across the Commonwealth, by supporting creative ideas and stimulating collaboration with industry that strengthens key technology and innovation sectors.
Assessment: Currently developing $18 Million + worth of projects for FY25/26 consideration in key clusters such as Human Performance, Quantum Computing, Artificial Intelligence, Blue Economy & Sustainable Foods. Similar to past months, the division is intentionally maintaining flexibility in the uncommitted funds to accommodate emerging priorities. Innovation has received a full proposal from UMass Lowell in partnership with Mass General Brigham for an R&D collaboration focused on Human Performance and is preparing for an external review. AI Models Challenge award selection moving forward for June Approval (see milestones below).
FY25 Budget: $16,675,000
Key Performance Metric | Key Performance Description | Target | Result | Comments
Increase Industry Participation | Company engagement in R&D/T&I supported investments | 104 | 361 | This number reflects companies engaged with projects through UMass Lowell MASTS, Qubic Labs, WPI, Western New England University, Boston University, and Barnstable County, UMass Amherst, UMass Boston, MITRE, LEVER and Cape Cod Fisherman Alliance (CCCFA) in FY25. The actual number of companies directly engaged with these companies through engagement events is closer to 950.
Ensure Regional Diversity | R&D/T&I investments in regions outside of Boston area | 4 | 14 | 
Contribute to retention, expansion and/or creation of MA-based companies | IP/Technology Licenses coming out of R&D/T&I supported investments | 12 | 20 | 
Improve conditions for diverse job growth, improving competitive advantage for MA-based companies | Diverse individuals receiving training in specialized skills at R&D/T&I supported investments | 70 | 132 | At least 30% of students and faculty offering services are female. Other numbers are estimates based on reporting of those enrolled.
Attract additional investment further leveraging R&D/T&I Investments | Leveraged dollars above statutory requirements | $10M | 39,497,320 | Leveraged amount large amounts from the following grantees - WPI - AVMI ($17.5) UMass Lowell MASTS ($12M) BU RASTIC ($345,000)UMass Amherst/EMA ($1M) Northeastern Open 6G ($7M)

## Slide 11: MA Tech Hubs
Description: This program will provide grants or other financial assistance for infrastructure support for industry-led consortia focused on advancing the commonwealth’s global leadership and growing jobs in key emerging technology sectors, including, but not limited to, quantum information sciences and technology, bioindustrial manufacturing and non-therapeutic biomanufacturing. The grants shall support the development, demonstration, deployment and commercialization of technology in key emerging technology sectors and shall be expended for infrastructure that support training, company incubation and acceleration, technology testing and evaluation and other commercial and economic development needs. Additionally, $40,000,000 has been identified for a quantum innovation hub to be located in the Pioneer Valley.
Assessment: The Innovation Institute developed and launched the MA Tech Hub solicitation on February 18, 2025. Applications were due on April 14, 2025. 38 proposals were received across 3 program tracks (13 transformation, 19 strategy development, 6 designation-only). A comprehensive review process was conducted with internal MassTech staff and external subject matter experts. By the end of Q4 the review process was complete and 14 applications were recommended for awards which were approved at MassTech's July Board meeting 3 Transformation awards: Berkshire Innovation Center, New Bedford Ocean Cluster, Worcester Polytechnic Institute; 6 Strategy Development awards: Endicott College, InnoVenture Labs, Merrimack College, Old Colony Planning Commission, Western MA EDC, UMass Lowell; 5 Designation-Only awards: Middlesex 3 Coalition, Western MA EDC, MassRobotics, Qubic Labs. Conversations to develop the Quantum Innovation Hub are ongoing.
FY25 Budget: $4,000,000
Key Performance Metric | Key Performance Description | Target | Result | Comments
Release a solicitation and facilitate funding a minimum of 7 awards. | Identify and support pipeline of industry led consortia in key tech sectors in regions around the state positioned to scale growth. Awards will be made in two areas: Strategy support for regions to develop or refine their strategic plans for innovation-driven economic growth; and Transformational support for regions ready to execute projects to enhance innovation ecosystems. | 2 Transformational Awards and 5 Strategy Awards | 3 transformation and 6 strategy development | The program reviewed 38 applications (13 transformation, 19 strategy development, and 6 designation-only). 3 applicants will receive transformation grants and 6 will receive strategy development grants.
Strengthen the regional innovation ecosystem through the development of a peer TechHub Network | MassTech will designate regions as ‘Tech Hubs’ to recognize their innovation capacity through unique assets, partnerships, and industry focus. At least three designations will be made in FY25, initiating a TechHub Network for collaboration, resource sharing, and best practice exchange to advance Massachusetts as a global innovation leader. | 3 | 14 | In total there are 14 MA TechHub designations to be awarded between the 3 transformation grant recipients, 6 strategy development recipients, and 5 designation-only recipients. Leadership teams from each of the 14 MA TechHubs will participate as members of the MA TechHub network. The first convening of the network will likely take place in FY26 Q1 or early Q2.
Engage quantum supply chain and academic stakeholders in support of advancing quantum Tech Hub and make initial investments in the quantum supply chain in the Pioneer Valley accelerator. | Ongoing stakeholder led program development and initiate facility design for accelerator. | 20 | 100 | Engagement with 23 member Pioneer Valley Quantum Innovation Hub Quantum Supply Chain Accelerator; IBM Quantum event focused on Quantum in Healthcare/Life Sciences - 30 attendees; Taiwan Delegation event - 15 participants; Quantum Announcement Event related to MGHPCC/QuEra Neutral Atom Computer Award - 40+ participants.

## Slide 12: Robotics
Description: The Massachusetts Technology Collaborative (MassTech) Innovation Institute’s Robotics Department will provide grants or other financial assistance to support research and development of robotics technology including, but not limited to, robotics incubation, testing, training, workforce development, research and development and commercialization activities; provided, that grants may be made to nonprofit entities, public or private universities or private business entities. Funding from the MassLeads Acts will help MassTech build on momentum from the Robotics ARPA priorities described below.
Assessment: In Q4, the Innovation Institute's Robotics Department engaged in planning toward a Massachusetts Robotics brand campaign, titled "The State of Robotics." This campaign may include a website, social media presence, and events and is intended to launch by end of 2025.It's Robotic Technician Training Program continued its work and has trained 10 students, thus far. The department reviewed and selected a grantee for the Regional Robotics NOFO through both an internal and external review process, and the requisite grant memo has been submitted to EOED. A Notice of Funding Opportunity for a Robotic Digital Twin Initiative was submitted to EOED at the beginning Q4.
FY25 Budget: $2,275,000
Key Performance Metric | Key Performance Description | Target | Result | Comments
Foster the robotics ecosystem in Massachusetts and facilitate relationships and collaboration between industry, academia, and government. | Host and attend events and engagements to support the robotics ecosystem. Host events, attend and speak at relevant external events, and conduct site visits among robotics companies and workforce training providers. Events and engagements could include workshops on verticals, ecosystem, Robotics Industry Steering Committee meetings, knowledge sharing on specific technologies or other robotics topics. Measured in number of events. | 5 | 25 | 14 conferences (8 attended by Robotics staff and 6 where the Robotics team staffed a booth), 4 Robotics Industry Steering Committee (RISC) meetings, several working group meetings, 5 events sponsored and 2 co-hosted events
Showcasing the Massachusetts robotics ecosystem by bringing industry, government and students together at RoboBoston, RoboticsInvest and other such events. | Spur economic growth within companies and interest in robotics career opportunities for students, and fostering entrepreneurship, increasing previous years' impact. Measurement in total attendees. | 500 | 7645 | RoboBoston (sponsored for $30,000) with 7000 attendees. RoboInvest (sponsored for $23,367) 400 attendees. Physical AI panel 30 (MassTech Hosted). Women in Robotics Gala 200 (Sponsored for $6600)
Inclusive geographic engagement of the state's robotics ecosystem. | Consideration of Robotics Department activities across different regions of the state. Number of sponsorships and awards to organizations outside of Boston. Should be reported annually. | 2 | 10 | Regional involvement in Somerville, Pittsfield, Amherst, New Bedford, Lowell, Hudson, Newton, Billerica, Needham, and Waltham and includes Massrobotics Accelerator, Robotics Brand Campaign, the Jumpstart program that extended to Lowell, the Robotics Technician Fellowship with NBRR in New Bedford and the WeRobot sponsorship to 1Berkshire.

## Slide 13: Applied AI Fund
Description: The Applied AI Fund will support the establishment of a MA AI Hub that supports the adoption and application of artificial intelligence capabilities to public policy problems and to leverage emerging AI technologies to advance the commonwealth’s lead in technology sectors including, but not limited to, life sciences, healthcare and hospitals, financial services, advanced manufacturing, robotics and education. Grants from the Applied AI Fund shall support capital expenses related to activities that leverage emerging AI technologies and AI research collaboration between MA based academic institutions and industry to advance the commonwealth’s lead in technology sectors including, but not limited to, life sciences, healthcare and hospitals, financial services, advanced manufacturing, robotics and education; provided further, that funds shall be used to support the incubation of AI firms, advance the adoption of AI technologies and support AI software and hardware technology development and commercialization activities.
Assessment: MassTech continued in its planning stage and coordination with EOED on the sources and uses of various funds including this to support the launch of the AI Hub. Hiring for the Hub commenced and the intention is to draw from the admin portion to support staffing of the AI Hub. MassTech hired its Director for the AI Hub.
The Innovation Institute secured approvals for MGHPCC AI Compute Resource (AICR) and the IBM/RedHat Venture Studio awards. The RFP, issued by the Hub's grantee MGHPCC, issued the AICR procurement.
The MA AI Hub launched its first outward facing educator support programming in June with the Future Ready: AI in the Classroom. This year long 50-hour professional development programming, delivered in partnership with the STEM Advisory Council and Project Lead the Way, kicked off with forty-five k-12 STEM educators from across the Commonwealth participating in a 2-day hands-on session and will be followed up throughout the current academic year with 3 additional cohort convenings through Spring '26.
The MA AI Hub supported the inaugural launch of a High School Summer Career Academy in AI in partnership with Burlington Public Schools, through a JAII Regional Priority Award. This 4-week academy provided 45 high school students with hands-on mentor and instructor lead interventions that included python training, industry site visits to AWS, The Broad Institute and Microsoft and culminated their summer academy by developing AI for Good pilot projects that were presented in a one day science fair themed event with the LG in attendance. In addition to this being a first of its kind AI intervention in the Commonwealth, a key deliverable is the development of a resource playbook for other school districts to adopt this programming for their use in the coming years.
The MA Hub has partnered with Microsoft New England to conduct a non-technical Training and Education for Workforce Development Hackathon. This program is convening ~60 diverse stakeholders from labor, agency, k-12 and higher education. and municipalities among others to ideate on challenge statements that will inform and define potential AII Hub offerings centered around K-12 interventions, support programming for highly skilled talent attraction and retention as well as upskilling/reskilling for existing workers.
FY25 Budget: $45,600,000

## Slide 14: Applied AI Fund: Results
Key Performance Metric | Key Performance Description | Target | Result | Comments
Engagement activities within AI industry and ecosystem | Establish MTC AI Hub presence and AI community engagement activities across the broader MA AI landscape and ecosystem. | 10 | 15 | Amazon, BCG, Accenture, IBM, Dell, NVIDIA, Microsoft, RedHat, IBM, MassChallenge workshop, New England Venture Capital Association, Flagship Pioneering AI summit, Google, Boston AI Week, MA AI Blueprint, DESE
Engage academic institutions in a cross-institution AI Academic Research Collaboration Working Group | In support of establishing the MA AI Hub, and specifically the Hub's research capabilities, establish working dialog across at least 5 MA academic research institutions in support of the MA Applied AI Hub's research collaboration initiatives | 8 | 12 | Harvard, MIT, Boston University, Northeastern (College of Professional Studies and the Lowell Institute WFD Studies) , UMass, Yale, Boston Medical Center (ARPA H Index), Mass Open Cloud, Babson College, Suffolk University, WPI, Bristol Community College
Release AI targeted solicitations and facilitate funding a minimum of two awards. | In support of AI Data Model Innovation Challenge, solicit innovative AI proposals to inform MTCs understanding of the MA AI landscape. Select AI specific proposals that MTC can fund in support of the MA Applied AI Hub through Innovation and/or R&D grants | 1 | 1 | On June 12, 2025 the Masstech Board of Directors approved 7 Awards Totaling $2,882,219. Overall the program received 58 applications representing AI solutions in healthcare, climate tech, robotics, education, life sciences, and advanced manufacturing.

## Slide 15: NEMC Hub Match
Description: The MA state matching funds committed to the NEMC Hub will be utilized for the SCALE Capital: Massachusetts Lab-to-Fab Grant Program. This program will support strategic projects that support the success and long-term sustainability of the Hub as part of the U.S. Dept. of Defense's (DoD) Microelectronics Commons Program while simultaneously strengthening the microelectronics ecosystems in the state. Specifically, this grant program is defined to support projects that are closing the lab-to-fab capability and capacity gaps through the 3 categories of Ecosystem Development, Workforce Development, and Technology Development. To be eligible to receive grant awards tied to these funds, organizations will need to be a NEMC Hub member, the funds must be used for capital expenses, and must be utilized at a location in MA. Co-investment or cost-share is required, target match amounts are 1:1 (cost share: grant $) for technology and ecosystem development and 0.5:1 for workforce development.
Assessment: Program start up was delayed in FY25 as a result of numerous clarifications on source and use of funds with EOED and ANF. Conversations began in June 2024 following signing of an initial "placeholder" contract, carried forward through the signing of the PayGo bill (to change the funding source), and further during the program design and solicitation approval processes (clarifying allowable use of funds) among MassTech and EOED. The team intended to launch SCALE early in calendar year 2025, however was delayed until the end of April. As a result, MassTech and NEMC will report on KPI outcomes in FY26. In FY25 Q4, the team launched the solicitation, received 25 concept papers requesting $42.6M in funding. 15 of those concept papers were invited to submit full proposals by August 1, 2025. MassTech anticipates submitting a grant memo with its selected grantees in September 2025. The process is on track to be presented to the MassTech Executive Committee on October 1, 2025. Three categories and targeted uses are as follows: 1) Ecosystem Development – Capital expenses to fill lab-to-fab facility and/or equipment gaps, to be installed and utilized by broader microelectronics community. 2) Workforce Development – Capital expenses that will enhance existing workforce development programs or contribute to the creation of new programs. Proposals should be for microelectronics education and training programs driven by employer needs in the region. 3) Technology Development – Capital expenses that will support technology and product development of early-stage (e.g., TRL 1-3) microelectronics concepts, helping to mature the technologies to a point of readiness for follow-on public and/or private investment.
FY25 Budget: $0 (implementation of $10 M from FY24)
Key Performance Metric | Key Performance Description | Target | Result | Comments
Strengthening and accelerating the MA microelectronics ecosystem by addressing critical capability and capacity gaps, enabling lab-to-fab technology transitions, and scaling needed education/training opportunities. | Combination of increased availability and accessibility to new microelectronics capabilities or capacity, maturity of microelectronics technologies transferring from lab-to-fab, and expansion of industry-needed training programs. | At least 3 instances of: - addressing a capability/capacity gap, and/or - maturing a critical microelectronics technology from lab-to-fab, and/or - scaling a industry-connected education/training program | 0 | Evaluated annually, dependent on mix of applicant proposals across ecosystem, technology, and workforce
Co-investment generated. | Amount of dollars, in-kind, and time contributions co-invested by awardees and their sub-performers. | At least 30% of awards exceed a 1:1 co-investment rate. | 0 | Evaluated annually
Geographic diversity of awards and project partners. | Concentration of awards in, and partners from, Western Mass, Central Mass, Northeast Mass and Southeast Mass/Cape & Islands | Awards and project partners spanning 2-3 major MA regions | 0 | Evaluated annually