## Revision Notes
DATE | REVISION NOTES Latest revisions are shown in red for ease of reference.
2011-01-01 | Workbook Font changed to Times New Roman to reduce printing costs.
PDDG 2-A-7, 25% Submission, Environmental Coordination Checklist is now included.
PDDG 2-A-8, 25% Checklist updated with question 13.07.
PDDG 2-A-9, 75% Checklist updated with question 22.07.
PDDG 2-A-10, 100% / PSE Checklist updated with question 9.07.
PDDG 9-A-1, Pavement Management Checklist is now included.
Traffic & Safety Engineering Checklist is now included.
Design Submission Distribution Chart updated to reflect:
new Traffic Checklist
new coding for submitting documents in different formats
2011-08-17 | PDDG 2-A-9, 75% Checklist (# 7.12 & 7.16) updated requiring drainage inverts on the plans.
2012-05-16 | "PDDG 2-A-7, 25% Checklist" through "2-A-10, 100% Checklist" updated with questions regarding "Drawing Files" added to the "Plans" section, and questions regarding ADA access added to the "Construction Drawings" Section.
"Traffic Safety Engineering Checklist" updated with questions regarding "Drawing Files" added to the "Plans" section.
Distribution List was updated/revised.
2012-05-30 | Distribution List was updated/revised.
2012-07-09 | CAD Standard Checker, referenced above (5/16/12 revision) was deleted from 25%, 75% & 100% checklists.
2012-10-05 | Updated list of facilities subject to Intelligent Transportation System (ITS) Section review (see the last tab - below).
Distribution List was updated.
2014-01-15 | Distribution list and 25%, 75% and 100% checklists updated for designer project control revisions and other assorted changes,
New tab added, "DSDC NOTES", for detailed notes regarding the Design Submission Distribution Chart.
2015-08-01 | Distribution Chart and DSDC NOTES updated.
2015-12-01 | Distribution Chart and DSDC NOTES updated.
2016-01-11 | Distribution Chart and DSDC NOTES updated.
2016-03-01 | Distribution Chart and DSDC NOTES updated.
2016-06-30 | Distribution Chart and DSDC NOTES updated.
2016-07-11 | Distribution Chart and DSDC NOTES updated. Link to EEC added.
2016-11-09 | Distribution Chart and DSDC NOTES updated for Stormwater Unit, Tunnel Engineer and District.
2019-07-24 | Distribution Chart and DSDC NOTES updated to replace most Hardcopy submissions with Electronic submissions in whichever format complies with Department policy.
2020-01-01 | Distribution Chart, DSDC NOTES, and 25% Checklist updated to reference the Design Justification Workbook instead of DERs. Utility distribution updated to reflect Engineering Directive E-19-004. PMs to now receive 1 hard copy of plans and cross-sections.
2020-05-21 | 100% Design Checklist has been completely revised to ensure incorporation of 75% design comments, ensure the use of the CPE, provide flattened AutoCAD files, capture Consultant Evaluation Scores and enhance formatting features.
2020-07-17 | 25%/75% Checklists updated to capture Consultant Evaluation Scores, clarify policy references and CPE direction. DSDC Chart and notes revised to; 1) reflect new Highway Design and Traffic email addresses in Notes 28 and 35; 2) clarify ProjectInfo Repository vs. Sharepoint usage; 3) eliminate submissions to Office of Performance and Asset Management, and; 4) call attention to the PM responsibility for checklists.
2023-01-06 | 75% Checklist Item 22.6 was updated to reflect the consequences of not having environmental permit applications.
Last revisions are shown in red for ease of reference.

## Design Submission Distr. Chart
DESIGN SUBMISSION DISTRIBUTION CHART
|  | Pre-25% |  |  | 25% | [15 empty] | 75% | [14 empty] | 100%
The Chart uses a code to determine the format of the submission. If hardcopies are required, the number of sets needed will follow the format code. H1 = One Hardcopy; H2 = Two Hardcopies; CD = Compact Disc; E = Electronic (15). Latest revisions are shown in red for ease of reference. |  | PRELIMINARY STRUCTURE REPORT | BRIDGE TYPE SELECTION WORKSHEET (22) | HYDRAULIC REPORT | HIGHWAY PLANS | X-SECTIONS | BRIDGE SUBMISSIONS (10) - Bridge Sketch Plans | GEOTECHNICAL REPORT | ESTIMATE - (Bridge & Highway) | DJW (18) | FDR (11) | PREL. ROW | TRAFFIC & SAFETY ENGINEERING CHECKLIST | 25% DESIGN CHECKLISTS - (Highway & Bridge) (33) | Preliminary Duration & I/Ds | ENVIRON. CHECKLIST | 25% WATER QUALITY DATA FORM (WQDF) | INCENTIVES/DISINCENTIVE PROVISIONS CHECKLIST | PAVEMENT CHECKLIST & CALCS | HORIZONTAL ALIGNMENT REPORT (13) | HIGHWAY PLANS | X-SECTIONS | BRIDGE SUBMISSIONS- 1st Structural Plans | Bridge Design Calculations, Vol. I & II | SPECIAL PROVISIONS | INCENTIVE/DISINCENTIVE PROVISIONS W/BACKUP FOR ROAD USER CALC. | W.A.B.P. ESTIMATE & CALC BOOK | BOTTOMS-UP ESTIMATES | Basis of Cost Estimate Narrative | LAYOUT PLANS & INST | 75% DESIGN CHECKLISTS - (Highway & Bridge) (33) | CONTRACT TIME DETERMINATION SCHEDULES INCLUDING I/D SUPOPORT | 75% WATER QUALITY DATA FORM (WQDF) | PAVEMENT CALCS (12) | HORIZONTAL ALIGNMENT REPORT (13) | HIGHWAY PLANS | X-SECTIONS | BRIDGE SUBMISSIONS (10) & (19)-2nd Structural Plans | Bridge Design Calculations, Vol. I & II | SPECIAL PROVISIONS | INCENTIVE/DISINCENTIVE PROVISIONS W/BACKUP FOR ROAD USER CALC. | W.A.B.P. ESTIMATE & CALC BOOK | DETAIL SHEETS | FINAL ROW PLANS | 100% / PS&E DESIGN CHECKLISTS - (Highway & Bridge) (34) | Project Utility Coordination Form (P.U.C.) | CONTRACT TIME DETERMINATION SCHEDULES | BOTTOMS-UP ESTIMATES | Basis of Cost Estimate Narrative | PAVEMENT CALCS (12) | HORIZONTAL ALIGNMENT REPORT (13)
DISTRICT (31)
| DISTRICT BRIDGE ENGINEER (20) | E | E | E |  |  | E | E | E |  |  |  |  | E | [8 empty] | E |  | E |  | E |  |  |  | E | [6 empty] | E |  | E |  | E |  |  | E
| PROJECT DEVELOPMENT REVIEWER |  |  |  | E | E | E |  | E | E |  | E | [7 empty] | E | E | E | E |  |  |  | E | E | E | E |  |  |  |  | E | E | E | E |  |  |  | E |  | E |  |  |  | E | E |  | E
| TRAFFIC | E | E |  | E | [5 empty] | E | [9 empty] | E | [14 empty] | E
| CONSTRUCTION SCHEDULER | [13 empty] | E |  |  | E |  |  | E | E | E |  | E | E | E | E | E | E | E | E |  |  |  | E | E | E |  | E | E | E |  | E | E | E | E | E | E
| UTILITY/CONSTRUCTABILITY ENGINEER |  | E |  | E | E | [8 empty] | E |  |  | E |  |  | E | E | E |  | E | E |  | E | E |  |  | E |  |  |  | E | E | E |  | E | E |  |  |  |  | E | E | E | E
TRAFFIC (35) |  | E | E |  | E | [5 empty] | E |  | E | [7 empty] | E | [14 empty] | E
| REGULATIONS UNIT (1) | [19 empty] | E | [14 empty] | E
ENVIRONMENTAL (2) |  |  | E |  | E |  | E |  | E |  |  | E |  |  |  | E | E |  |  |  | E |  | E |  |  |  | E | [8 empty] | E |  | E |  | E |  | E
| STORMWATER UNIT (30) |  |  |  | E | E |  | E | E | [7 empty] | E |  |  |  | E | E |  |  | E |  | E | [5 empty] | E |  |  | E | E |  |  | E |  | E
BRIDGE - STATE BRIDGE ENGINEER (18) |  | E | E |  |  |  | E | [15 empty] | E |  | E | [12 empty] | E |  | E
BRIDGE - TECHNICAL REVIEW SECTION |  | E | E | E |  |  | E | E | E |  |  |  |  | E | [8 empty] | E | E | E |  | E |  |  |  | E | [6 empty] | E | E | E |  | E |  |  | E
BRIDGE - STATE TUNNEL ENGINEER(29) |  | E |  |  |  |  | E | [15 empty] | E |  | E | [12 empty] | E |  | E
GEOTECHNICAL SECTION (23) |  | E | E |  |  |  | E | E | E | [13 empty] | E | E | E | [12 empty] | E | E | E
HYDRAULIC SECTION |  | E | E | E | E | E | E | E | [5 empty] | E |  | E | [6 empty] | E |  | E | [5 empty] | E | [6 empty] | E | [6 empty] | E
RIGHT OF WAY
| MUNICIPAL (32) |  |  |  | E | [6 empty] | E, H1 | [8 empty] | E | [8 empty] | E, H1 | [5 empty] | E | [7 empty] | E, H2
| STATE |  |  |  | E | [6 empty] | E, | [8 empty] | E | [8 empty] | E | [5 empty] | E | [7 empty] | E
LAYOUTS | [29 empty] | H2
HIGHWAY DESIGN (AAB/ADA/CSE) (28) |  |  |  |  | E | E |  |  |  | E | [10 empty] | E | E | [13 empty] | E | E
CONSTRUCTION--Boston HQ (4)
| ASST.STATE CONSTRUCTION ENGINEER | [13 empty] | E |  |  | E | [6 empty] | E | E |  | E | E |  |  | E | [8 empty] | E |  |  |  |  | E | E | E | E
| AREA ENGINEER | [13 empty] | E |  |  | E | [6 empty] | E | E | E | E | E |  |  | E |  |  |  | E |  |  |  |  | E |  |  |  |  | E | E | E | E
DESIGN JUSTIFICATION COMMITTEE CHAIR (18) | [9 empty] | E/H1
LANDSCAPE SECTION |  |  |  |  | E | [15 empty] | E | [14 empty] | E
PAVEMENT MANAGEMENT (5) |  |  |  |  | E | [13 empty] | E |  | E | [12 empty] | E |  | E | [13 empty] | E
RESEARCH & MATERIALS (24a & 24b) | [24 empty] | E | [14 empty] | E
FHWA (1/2-size set) (6) & (17) |  |  |  |  | E | E | E |  | E | H | E |  |  | E | [6 empty] | E | E |  |  | E |  | E |  |  |  | E |  |  |  |  | E | E | E |  | E |  | E | E |  | E
MUNICIPALITY/POLICE/OTHER (7) |  |  |  |  | H2 | [15 empty] | H2 | [14 empty] | H2
UTILITIES (8) |  |  |  |  | CD & H1 (color) | CD +H1 | CD +H1 | [13 empty] | CD & H1 (color) | CD +H1 | CD +H1 | [12 empty] | CD & H1 (color) | CD +H1 | CD +H1
INTELLIGENT TRANS. SYSTEMS (9) |  |  |  |  | E | [15 empty] | E | [14 empty] | E
PROJECT MANAGER |  |  |  |  | E + H1 | E + H1 | E |  |  | E | E |  |  | E | [5 empty] | E | E | E | E | [6 empty] | E | E |  |  |  | E | E | E | [6 empty] | E | E | [5 empty] | E
PROJECTINFO FILE REPOSITORY/SHAREPOINT (15) |  | E | E | E | E | E | E (11) | E | E | E | E | E | E | E | E | E |  | E | E | E | E | E | E (11) | E | E | E | E | E | E | E | E | E |  | E | E | E | E | E (11) | E | E | E | E | E | E | E | E | E | E | E | E | E
CAD STANDARDS REVIEWER (14) |  |  |  |  | E | E | E |  |  |  |  | E | [8 empty] | E | E | E | [6 empty] | E | [5 empty] | E | E | E | [5 empty] | E (14)
Notes:
Refer to separate tab in this workbook titled "DSDC NOTES."

## DSDC NOTES
DESIGN SUBMISSION DISTRIBUTION CHART NOTES - Latest revisions in red for ease of reference.
1 | Federal Aid projects only.
2 | Refer to "Chapter 2 Appendix 2-A-6 and 2-A-7, Environmental Requirements for 25% Design" of the Project Development and Design Guidebook.
3 | 75% and 100% submittals to Complete Streets Engineer not necessary if approved at 25% (unless design has changed).
4 | Send plans to Area Construction Engineer for Estimated Construction Duration.
5 | Refer to "Chapter 9 Appendix" of the Project Development and Design Guidebook. Also, Pavement Management will no longer accept paper plans for review.
6 | Refer to Federal Oversight Agreement dated June 2015. FHWA review depends on PoDI and PoCI determinations.
7 | A minimum of two (2) sets of plans are now required for Municipalities and Police Departments. Engineering judgment shall be exercised to determine how many additional submissions are needed for municipalities and other state agencies or affected project stakeholders.
8 | See Engineering Directive E-19-004 for Electronic Utility Plan Submissions.
9 | Refer to ITS PLANS tab below.
10 | Refer to the most recent version of the Bridge Manual for specific submission requirements.
11 | All non-plan submissions should be posted to the ProjectInfo Repository. Use Sharepoint instead of the Repository for any project scheduled for advertisement in the current or next FFY. Engineering judgment shall be exercised to determine the number of paper-based submissions required for each FDR, Calculation Book, or other report.
12 | Pavement Plans and Calcs needed only if not approved at 25%.
13 | Horizontal Alignment Report needed only if horizontal alignment changed from previous submittal.
14 | For all projects initiated after January 1, 2012, CAD files must be submitted electronically to the Project Manager at each submission level for review by the CAD Standards reviewer.
15 | Except for Utility Plan Submissions, for all other specified E-copy reviews , include only one CD with electronic copies (in PDF) of all documents (e.g. design checklist, special provisions, estimates, calcs,D4 detail sheets, responses to comments, construction plans (as one file), ROW plans, ENV documents, etc). Project Manager will distribute to all reviewers. Also submit Excel and/or Word version of estimates, calcs, special provisions and ENV-related forms such as WQDF, EECC, etc.). Use Sharepoint instead of the Repository for any project scheduled for advertisement in the current or next FFY.
16 | Obsolete.
17 | Note to MassDOT only: Refer to cover letters to FHWA under SOPs 205, 250 & 270 for further information. FHWA receives Type Selection Worksheet or Preliminary Structure Report, Sketch Plans, Geotechnical Report, and Hydraulic Report upon internal reviews and approval. Per SOP 208, a stamped DER is required for FHWA PODI projects.
18 | Design Justification Workbooks shall be submitted in electronic format until they are ready for aproval. When ready for approval, a stamped hard copy (2 for FHWA PODI projects) shall be submitted.
19 | FHWA receives Final Structural Submission upon internal reviews and approval.
20 | See Engineering Directive E-13-002 for Role of District Bridge Engineers.
21 | MassDOT PM to determine the required number of hard copies for PS&E submittal based on 100% Design review comments.
22 | Updated to distribution for pre-25% submittal based on approved SOP 203.
23 | Obsolete.
24a | Research & Materials Section needs to receive an electronic and hard copy of the specifications at each stage of design for Design-Build and Bridge projects only. R&M does NOT need to receive the whole submittals, ONLY SPECIFICATIONS.
24b | For Highway projects and at 100% Design Stage only, MassDOT PM to send an email (containing a link to Pinfo where 100% SPEC is stored) to R&M Engineer for his information. No need to send a hard copy.
25 | Updated to design submission distribution chart.
26 | Obsolete.
27 | Obsolete.
28 | If you have any questions regarding AAB/ADA/CS, please email DOTHighwayDesign@dot.state.ma.us.
29 | Obsolete.
30 | Stormwater requires electronic copies as noted and an editable electronic copy of the Water Quality Data Form at 25% and 75%.
31 | Send submission directly to District with MassDOT PMs copied on the transmittal.
32 | Provide one Hardcopy for each municipality to the Municipal ROW Unit.
33 | PMs are responsible for reviewing (and scoring if applicable) the 25% and 75% Design Submission checklists.
34 | PMs are responsible for reviewing and scoring the 100% Design Submission checklists.
35 | If you have any questions regarding HQ Traffic, please email StateTrafficEngineer@dot.state.ma.us.
SOPs referenced in the notes are only for MassDOT PMs information
Latest revisions are shown in red for ease of reference.

## PDDG 2-A-7, 25% EEC Checklist
Please refer to the latest Early Environmental Coordination Checklist found at: | Early Environmental Checklist
25% Design Submission Checklist
Early Environmental Coordination for Design Projects

## PDDG 2-A-8, 25% Checklist
PROJECT/DESCRIPTION________________________________________________ |  |  |  |  | Project #
25% HIGHWAY DESIGN SUBMISSION & REVIEW CHECKLIST Submission Date
| PURPOSE |  |  | The 25% highway design review is intended to provide MassDOT's Highway Division the opportunity to evaluate the proposed design relative to current design standards, right of way impacts, environmental impacts and other potential community concerns associated with the proposed design, and Incentives/Disincentives (I/Ds) Initialization (if applicable) to be defined by P.M. as a reminder.
| GENERAL |  |  | This checklist represents the minimum amount of issues that should be considered when reviewing a 25% highway submittal. The information below is not intended to address all aspects of plan preparation. To the extent practical, any comments relative to plan preparation made at the 25% stage will certainly improve the quality of the 75% submittal.
Any question listed below with a No (N) or Not Applicable (NA) answer requires a written comment.
0.0 DRAWING PLANS
| Y | N | NA
0 |  |  |  | Have the plans been prepared according to and in conformance with the latest MassDOT Highway Division CAD Standards?
Comment:
1.0 TITLE SHEETS
| Y | N | NA
1.1 |  |  |  | Is the Title Sheet prepared consistent with MassDOT's latest format?
Comment:
1.2 |  |  |  | Is the DESIGN DESIGNATION table completed?
Comment:
1.3 |  |  |  | Has the Motor Vehicle Design Speed been selected consistent with PDDG 3.6.5, and identified in the Design Justification Workbook consistent with E-20-001?
Comment:
1.4 |  |  |  | Are the stations and coordinates for the beginning and end of project shown on the locus map?
Comment:
1.5 |  |  |  | Are bridge numbers shown on the locus map?
Comment:
2.0 TYPICAL SECTIONS
| Y | N | NA
2.1 |  |  |  | Do the proposed lane and shoulder widths shown on the typical sections properly account for the offset dimension? (An additional 2 feet of clearance should be added to the usable shoulder dimension to allow for an offset to vertical roadway elements over 0.5 feet in height, such as guardrail, bridge rail, concrete barrier, walls, trees, utility poles, etc.)
Comment:
2.2 |  |  |  | Are the proposed lane and shoulder widths consistent with PDDG Section 5.3.3, and discussed in the Design Justification Workbook, consistent with E-20-001?
Comment:
2.3 |  |  |  | Is the method of banking adequately represented on the Typical Sections in manner consistent with PDDG Section 4.2.5?
Comment:
2.4 |  |  |  | Is the location of the PGL the most appropriate location for the proposed project?
Comment:
2.5 |  |  |  | Does the shoulder break away from travel lanes when the width is greater than 4 feet?
Comment:
2.6 |  |  |  | Is the proposed pavement structure appropriate (full depth, reclamation, overlay)?
Comment:
2.7 |  |  |  | Are the pavement structure materials labeled consistent with the latest pavement Items identified in the CPE?
Comment:
2.8 |  |  |  | Is the proposed wearing surface compatible with the function of the proposed roadway?
Comment:
2.9 |  |  |  | If a narrow (less than 4 feet) box widening is proposed, was Cement Concrete Base Course considered in lieu of full depth pavement?
Comment:
2.1 |  |  |  | Are the guardrail details consistent with the latest CONSTRUCTION AND TRAFFIC STANDARD DETAILS?
Comment:
2.11 |  |  |  | PDDG Section 5.3 and the Separated Bike Lane Planning and Design Guide provided general guidance on a variety of cross section elements for each area type. Are the proposed Typical Sections consistent with these figures relative to dimensions, slopes and materials?
Comment:
2.12 |  |  |  | If retaining walls are proposed, does the design allow for guardrail to be adequately installed? Guardrail located on top of an existing or proposed stone masonry wall generally requires a moment slab.
Comment:
3.00 CONSTRUCTION DRAWINGS
| Y | N | NA
3.1 |  |  |  | Is the existing Base Plan information plotted consistent with PDDG Section 18.2.1.2?
Comment:
3.2 |  |  |  | Is the proposed horizontal geometry adequately described? (PC, PT, R, T, DELTA, L)?
Comment:
3.3 |  |  |  | Is the minimum radius consistent with PDDG Exhibits 4-8 & 4-9 based on the Design Speed noted on the Title Sheet, and discussed in the Design Justification Workbook, consistent with E-20-001?
Comment:
3.4 |  |  |  | If compound curves are employed, are they designed in accordance with Section PDDG 4.2.1.3, and discussed in the Design Justification Workbook, consistent with E-20-001?
Comment:
3.5 |  |  |  | Are there any features which negatively impact horizontal sight distance as described in PDDG Section 4.2.2?
Comment:
3.6 |  |  |  | Are cross culverts and drainage outlet locations shown on the plans?
Comment:
3.7 |  |  |  | Are approximate slope limits shown?
Comment:
3.8 |  |  |  | Based on the cross-sections provided and other available information are the proposed guardrail locations appropriate?
Comment:
3.9 |  |  |  | Have the impacts to existing wetlands and other resource areas been minimized?
Comment:
3.1 |  |  |  | Does the proposed design reasonably accommodate vehicle turning movements based on Auto Turn?
Comment:
3.11 |  |  |  | If applicable, are storage and deceleration lengths consistent with PDDG Section 6.7.3?
Comment:
3.12 |  |  |  | Is the proposed design consistent with ADA and AAB requirements?
Comment:
3.13 |  |  |  | Are stations at the beginning and end of project noted?
Comment:
3.14 |  |  |  | Is the existing layout information accurately depicted?
Comment:
3.15 |  |  |  | Are the approximate limits of proposed takings and easements shown?
Comment:
3.16 |  |  |  | Is sufficient right of way available to perform the work?
Comment:
3.17 |  |  |  | Are all the walks, sidewalks, crosswalks, and curbcut wheelchair ramps meet the requirements listed in Americans with Disabilities Act Accessibility Guidelines (ADAAG) and Public Rights of Way Accessibility Guidelines (PROWAG), which are discussed in the Engineering Directive E-12-005)?
Comment:
3.18 |  |  |  | Is an AAB Variance required for any accessibility nonconformance?
Comment:
4.00 PROFILES
| Y | N | NA
4.1 |  |  |  | Is the existing base profile information plotted consistent with PDDG Section 18.2.1.3? (station equations, cross culverts, bridge structures, sills of structures, high tension lines, bench marks, etc.)
Comment:
4.2 |  |  |  | Are the proposed profiles prepared consistent with PDDG Exhibit 18-11?
Comment:
4.3 |  |  |  | Are all aspects of the vertical geometry noted (Stopping Sight Distance, Passing Sight Distance (if applicable), G1, G2, L, K, station and elevation of the PVC, PVT and PVI)?
Comment:
4.4 |  |  |  | Is the stopping sight distance consistent with the Design Speed noted on the Title Sheet and PDDG Exhibit 3-8, and discussed in the Design Justification Workbook, consistent with E-20-001?
Comment:
4.5 |  |  |  | Is the K value consistent with the Design Speed noted on the Title Sheet and PDDG Exbihit 4-26 or 4-27?
Comment:
4.6 |  |  |  | Is the maximum grade consistent with the Design Speed noted on the Title Sheet and PDDG Exhibit 4-21, and discussed in the Design Justification Workbook, consistent with E-20-001?
Comment:
4.7 |  |  |  | Is the minimum grade consistent with PDDG Section 4.3.1? If a closed drainage system is proposed it is recommended that a minimum grade of 0.6% be used.
Comment:
5.00 TRAFFIC SIGNAL PLANS
| Y | N | NA
5.1 |  |  |  | Are signal heads located in the vision cone specified by the MUTCD?
Comment:
5.2 |  |  |  | Are pavement markings clearly displayed and labeled?
Comment:
5.3 |  |  |  | Does the Phasing Diagram adequately address pedestrian volumes? (pedestrian phases concurrent or actuated)
Comment:
5.4 |  |  |  | If appropriate, does the Phasing Diagram address emergency preemption?
Comment:
6.00 TRAFFIC MANAGEMENT PLANS (may be 8-1/2 x 11 for simple projects)
| Y | N | NA
6.1 |  |  |  | Does the TMP provide sufficient information to determine that the proposed project can be constructed without undue inconvenience to the public?
Comment:
6.2 |  |  |  | For projects with a detour, is the proposed detour reasonable considering available traffic data?
Comment:
6.3 |  |  |  | Does the proposed TMP adequately address bicycle and pedestrian accommodation?
Comment:
7.00 CROSS SECTIONS
(Although only top line sections in critical areas are required according to the PDDG, the latest engineering software makes providing all cross sections a simple matter. The top line information is intended to depict the relationship between the proposed roadway and the existing features only. However, to the extent that additional information is provided, it is worthwhile to comment relative to consistency with PDDG Section 18.2.2.5.)
| Y | N | NA
7.1 |  |  |  | Is the existing cross-section information plotted consistent with PDDG Section 18.2.1.4 and Exhibit 18-5? Are walls, hydrants, poles, trees over 8 inches, sills, wells, septic systems, cross culverts, ledge, layout lines, etc. plotted on the cross-sections?
Comment:
7.2 |  |  |  | Does the proposed cross-section provide sufficient area to install guardrail where necessary?
Comment:
7.3 |  |  |  | Have the proposed side and back slopes been appropriately chosen to balance impacts with safety and slope stability?
Comment:
8.00 PROJECTS THAT INCLUDE BRIDGE(S)
| Y | N | NA
8.1 |  |  |  | Is the project subject to the Highway Division's Non-NHS Bridge R&R Policy? (According to Engineering/Policy Directive P-92-010 in order for these guidelines to apply the roadway must be classified as either a Minor Arterial, Urban Extension of a Minor Arterial, Collector or Local roadway)
Comment:
8.2 |  |  |  | If the project is subject to P-92-010, is the proposed bridge width and approach geometry consistent with the Engineering Directive?
Comment:
8.3 |  |  |  | For bridge projects that are not subject to P-92-010 are the proposed bridge dimensions and vertical clearance consistent with PDDG Section 4.3.4 and Exhibit 4-28, and is the vertical clearance discussed in the Design Justification Workbook, consistent with E-20-001?
Comment:
8.4 |  |  |  | Do the construction drawings adequately depict the existing bridge structure including subsurface features?
Comment:
8.5 |  |  |  | Do the construction drawings adequately depict the relationship between the existing and the proposed bridge structure?
Comment:
8.6 |  |  |  | Does the TMP provide adequate dimensions such that the relationship between the lane configurations and the beam spacing of both the existing and the proposed structure can be evaluated?
Comment:
8.7 |  |  |  | Do the plans and cross-sections indicate that sufficient space is available to install approach guardrail?
Comment:
9.00 FREEWAYS
| Y | N | NA | The review of Freeway designs, particularly those involving grade separated interchanges does not lend itself well to a checklist type review. The design of a grade separated interchange must be evaluated based on the entire contents of PDDG Chapter 6. Listed below are some of the key items that should be reviewed.
9.1 |  |  |  | Is the proposed cross-section consistent with PDDG Section 5.3.4.1?
Comment:
9.2 |  |  |  | Is the median barrier provided consistent PDDG Exhibit 5-33?
Comment:
9.3 |  |  |  | Is the ramp spacing consistent with PDDG Exhibit 7-12?
Comment:
9.4 |  |  |  | Are the deceleration and acceleration lengths consistent with PDDG Exhibits 7-13 & 7-14?
Comment:
9.5 |  |  |  | Are the selected ramp design speeds consistent with PDDG Exhibit 7-15?
Comment:
9.6 |  |  |  | Does the minimum radius meet the criteria in PDDG Exhibit 7-24?
Comment:
9.7 |  |  |  | Are the ramp cross sections consistent with PDDG Section 7.7.1.2 and Exhibits 7-22 & 7-23?
Comment:
9.8 |  |  |  | Is the ramp geometry consistent with the guidelines provided in PDDG Exhibit 7-30 (a-k), and is the ramp length discussed in the Design Justification Workbook, consistent with E-20-001?
Comment:
10.00 ESTIMATE
| Y | N | NA
10.1 |  |  |  | Is sufficient back up information provided to determine if the preliminary cost estimate is reasonable?
Comment:
10.2 |  |  |  | Was the 25% cost estimate developed using the Construction Project Estimator (CPE) with the correct programmed Federal Aid, Non-Federal Aid, and Municipal Funding Categories, and an Excel file provided? The estimate is certified by the consultant's Log-In record using CPE.
Comment:
10.3 |  |  |  | Does the 25% cost estimate include an appropriate design contingency considering this early design stage?
Comment:
10.4 |  |  |  | Does the estimate total qualify for the need to request a 'bottoms-up' estimate at the 75% submission as referenced in Attachment J, Article IV, Section C, Paragraph 1b?
Comment:
10.5 |  |  |  | Has an Incentive/Disincentive (I/D) checklist been used to determine values for any I/Ds if applicable? If I/Ds are required, has a special provision been provided and has a road user benefit calculation been performed? Was a traditional or alternative schedule evaluation performed to support the use of I/Ds? Enter the amount (3-5% budget) as a comment below so the PM can enter it into the CAPE.
Comment:
11.00 FUNCTIONAL DESIGN REPORT
| Y | N | NA
11.1 |  |  |  | Was a Functional Design Report submitted for this project? Please refer to the Traffic & Safety Engineering Checklist.
Comment:
12.00 DESIGN JUSTIFICATION WORKBOOK
| Y | N | NA
12.1 |  |  |  | Was a Design Justification Workbook prepared? E-20-001 updates Section 2.11 of PDDG and supports the MassDOT Healthy Transportation Policy Directive P-13-001.
Comment:
12.2 |  |  |  | Does the design meet the Healthy Transportation Policy?
Comment:
13.00 CONCLUSIONS
| Y | N | NA
13.1 |  |  |  | Is the scope of work consistent with the scope approved by PRC? If no, please provide an explanation for MassDOT's review.
Comment:
13.2 |  |  |  | Is the estimated Total Federal Participating Construction Cost (TFPCC) consistent with the STIP? This includes the Office Estimate, 50% of Anticipated Utility Costs, 5-10% Construction Engineering, 10% Federal Construction Contingency and Traffic Police. If no, please provide an explanation for MassDOT's review.
Comment:
13.3 |  |  |  | Does the project address known geometric and safety concerns?
Comment:
13.4 |  |  |  | Do the plans represent a project that is reasonable from a constructability standpoint with respect to construction techniques and available right of way?
Comment:
13.5 |  |  |  | Is a letter of support and all correspondence with local historic commissions included?
Comment:
13.6 |  |  |  | Are the plans suitable for conducting a Design Public Hearing?
Comment:
13.7 |  |  |  | Does the project require utility relocations? If so, a CTD will be required for this project either as part of your design scope or by the MassDOT District Scheduler.
Comment:
13.8 |  |  |  | Did your DESIGN FIRM conduct a QC/QA review for this 25% submission?
Comment:
13.9 |  |  |  | Was the design schedule provided with this submission in .mpp and .xls formats with all milestones shown? Was the submission made on time based on the approved design schedule?
Comment:
Designer Certification
The Designer certifies that the 25% Design Plans have been reviewed in accordance with this checklist and that all responses are correct and accurately reflect the information presented on the submitted Design Plans.
Consultant Firm Principal Date
Note: Please make sure this checklist is attached to your Firm's submission/transmittal PDF letter.
SCORE:
A review score from 0-10 (10 is high) may be applied by the MassDOT Project Manager if it is determined to be necessary based on the condition of the design submission.

## PDDG 2-A-9, 75% Checklist
PROJECT/DESCRIPTION________________________________________________ |  |  |  |  | Project #
75% HIGHWAY DESIGN SUBMISSION & REVIEW CHECKLIST Submission Date
| PURPOSE |  |  | The purpose of the 75% review is to ensure that all comments from the 25% review have been satisfactorily addressed. The review also provides an opportunity to ensure that a complete contract package will be available for bidding and construction purposes.
| GENERAL |  |  | This checklist represents the minimum amount of issues that should be considered when reviewing a 75% highway submittal. The submittal should include: responses to all comments from the 25% review, plans which are 75% complete, cross-sections, special provisions without proprietary items (unless 3 or more manufacturers are listed), a cost estimate narrative, a cost estimate input into MassDOT's Construction Project Estimator (CPE) with current item numbers and appropriate funding source breakouts (including non-participating items), contract time determination schedules for all projects requiring any utility relocations, bottoms up estimates as applicable, incentive/disincentive (I/D) checklists and provisions, traditional/alternative schedule evaluations to support I/Ds, and road user calculations as applicable.
Any question listed below with a No (N) or Not Applicable (NA) answer requires a written comment.
| REVIEW |  |  | A review score may be applied by the MassDOT Project Manager if it is determined to be necessary based on the condition of the design submission.
1.00 SUBMISSION REQUIREMENTS
| Y | N | NA
1.1 |  |  |  | Have all the design plan PDFs and submission document PDFs been flattened for the 75% Bluebeam Review Session?
Comment:
1.2 |  |  |  | Was a Comment Resolution Meeting (CRM) or virtual meeting held at 25% review and have all 25% review comments been addressed with a written response?
Comment:
1.3 |  |  |  | Has there been any scope of work change since the 25% design submission? If yes, please provide an explanation for MassDOT's review.
Comment:
1.4 |  |  |  | Is there a significant cost increase to the project since the 25% design? If yes, please explain.
Comment:
1.5 |  |  |  | Was a Utility Site Walk or virtual meeting held with representatives from your firm, the City or Town, the MassDOT District DUCE Section, the MassDOT Project Manager, and all utility companies present?
Comment:
1.6 |  |  |  | Are the colored utility plans provided and is each underground and overhead facility shown in the proper color per MassDOT's Engineering Directive E-19-004 and Dig Safe conventions?
Comment:
1.7 |  |  |  | Were all comments regarding utility relocations from the Site Walk incorporated into the 75% submission?
Comment:
1.8 |  |  |  | Were all feasible public comments from the DPH incorporated into the 75% design plans?
Comment:
1.9 |  |  |  | Have the plans been created with the latest MassDOT Highway Division CAD Standards?
Comment:
2.00 TITLE SHEET
| Y | N | NA
2.1 |  |  |  | Are the latest Title Sheet formats followed including the border, title blocks, the latest documents list provided, and stations and coordinates for the beginning and end of the Project Limits labeled on the project locus?
Comment:
2.2 |  |  |  | Does the index indicate that the plans have been organized in the same order as indicated in PDDG Section 18.2.2.6? Does the plan sheet numbering match the index, and is the Project File No. provided on each plan sheet?
Comment:
2.3 |  |  |  | Are all sheets sized in accordance with the latest Project Development and Design Guidebook (PDDG)?
Comment:
3.00 TYPICAL SECTIONS
| Y | N | NA
3.1 |  |  |  | Was the proposed pavement design approved by MassDOT's Pavement Management Section?
Comment:
3.2 |  |  |  | All proposed materials should be labeled on the Typical Sections with dimensions provided and consistent with the approved pavement design. Are the material descriptions identical to the items provided in the CPE or the material description in the latest edition of the STANDARD SPECIFICATIONS FOR HIGHWAYS AND BRIDGES?
Comment:
3.3 |  |  |  | Are the pavement thicknesses and materials consistent with the approved pavement design?
Comment:
3.4 |  |  |  | Is the gravel borrow type specified in the Typical Sections?
Comment:
4.00 CONSTRUCTION DRAWINGS
| Y | N | NA
4.1 |  |  |  | Is the disposition of all existing and proposed features located within the limits of work clearly labeled (e.g. Rem., R&R, R&S, Ret., etc.)?
Comment:
4.2 |  |  |  | Is the proposed design consistent with ADA and AAB requirements? Do all the walks, sidewalks, crosswalks, and curbcut wheelchair ramps meet the requirements listed in Americans with Disabilities Act Accessibility Guidelines (ADAAG) and Public Rights of Way Accessibility Guidelines (PROWAG), which are discussed in the Engineering Directive E-12-005? If not, have all violations been identified and clearly discussed for MassDOT's review? Note that separate drawing details may be required to properly present the dimensions and elevations.
Comment:
4.3 |  |  |  | Are limits of slope work clearly shown throughout the entire project, and are the limits of proposed takings and easements (including any overhead utility easements) shown on the Construction Plans matching the ROW Plans?
Comment:
4.4 |  |  |  | Do the limits of work shown at the back of sidewalks, walls and bridges provide sufficient area for the proposed work to be constructed and to adequately transition to the existing topography?
Comment:
4.5 |  |  |  | Does every item of work shown on the Plans have an associated pay item (unless it is incidental to another pay item as indicated in the latest edition of the STANDARD OR SUPPLEMENTAL SPECIFICATIONS)?
Comment:
4.6 |  |  |  | Are the symbols and abbreviations on the plans used consistent with PDDG Exhibits 18-1 & 18-2, and are the proposed horizontal geometry (PC, PT, R, T, DELTA, L) and lane and shoulder widths shown on every sheet ?
Comment:
4.7 |  |  |  | Is all work not to be performed by the Contractor labeled BY OTHERS?
Comment:
4.8 |  |  |  | Is all necessary information to construct the proposed drainage system shown on the drawings? (The words DRAINAGE DETAILS with location reference SEE BELOW or SEE PAGE NO:__ should appear at the top of each sheet. Depending on the amount of information depicted on the construction drawings a separate set of drawings may be required. Refer to DRAINAGE AND WATER SUPPLY DETAILS below for additional information)
Comment:
4.9 |  |  |  | Do the plans adequately address water supply details? (The words WATER SUPPLY ALTERATIONS with location reference SEE BELOW or SEE PAGE NO:__ should appear at the top of each sheet. Refer to DRAINAGE AND WATER SUPPLY DETAILS below for additional information.)
Comment:
4.1 |  |  |  | Are the proposed guardrail locations consistent with Section 5.6 of THE PROJECT DEVELOPMENT AND DESIGN GUIDE, ENGINEERING DIRECTIVE E-20-004, THE ROADSIDE DESIGN GUIDE, and THE CONSTRUCTION AND TRAFFIC STANDARD DETAILS? (The words HIGHWAY GUARD should appear at the top of each sheet. The type of guardrail, end treatments and stations should be noted for all proposed guardrail.)
Comment:
4.11 |  |  |  | If plan and profile are separate sheets is the sheet number for the profile noted in the lower right corner of the drawing?
Comment:
4.12 |  |  |  | Are all proposed materials adequately labeled? (e.g. type of curb, sidewalk treatment, driveway material, etc.)
Comment:
5.00 PROFILES
| Y | N | NA
5.1 |  |  |  | Are the proposed profiles prepared consistent with Exhibit 18-10?
Comment:
5.2 |  |  |  | Are all aspects of the vertical geometry noted (Stopping Sight Distance, Passing Sight Distance, if applicable, G1, G2, L, K, station and elevation of the PVC, PVT and PVI)?
Comment:
6.00 CURB TIE AND GRADING PLANS
| Y | N | NA
6.1 |  |  |  | Does the curb tie information adequately provide station and offset information to PC's, PT's tapers, etc.?
Comment:
6.2 |  |  |  | Are grades shown every 25 feet, or closer, to note intermediate high or low points?
Comment:
6.3 |  |  |  | Does the curb tie and grading plan provide sufficient information to the contractor to adequately layout the proposed curb and construct a roadway that will not have ponding?
Comment:
7.00 DRAINAGE AND WATER SUPPLY DETAILS
| Y | N | NA
7.1 |  |  |  | Are drainage structures located approximately 300 feet apart on tangents, or closer for intersections?
Comment:
7.2 |  |  |  | Are drainage structures located approximately 200 to 250 feet apart on the inside of superelevated curves?
Comment:
7.3 |  |  |  | Are drainage structures located approximately 250 feet apart on highway grades over 6%?
Comment:
7.4 |  |  |  | Are drainage structures located at the uphill side of bridges?
Comment:
7.5 |  |  |  | For major highways are six drainage structures used at low points (three each side)?
Comment:
7.6 |  |  |  | For all other roadways are four drainage structures used at low points?
Comment:
7.7 |  |  |  | Are drainage structures proposed prior to superelevation transitions?
Comment:
7.8 |  |  |  | Have catch basin to catch basin connections been avoided?
Comment:
7.9 |  |  |  | Is the drainage trunkline located in the most appropriate location for future maintenance?
Comment:
7.1 |  |  |  | Has every effort been made to limit the amount of structures located in the travel lane?
Comment:
7.11 |  |  |  | Does the location and number of pipes entering manholes allow the walls of the manhole to maintain their structural integrity?
Comment:
7.12 |  |  |  | Is the length, size, direction of flow and type of material noted on each length of pipe?
Comment:
7.13 |  |  |  | Is the disposition of the existing drainage system adequately labeled? (RET, ADJ, R&R, ABAN, REM, etc.)
Comment:
7.14 |  |  |  | Do the plans fully address all the impacts that the proposed roadway design may have on the existing water supply system? (Full depth reconstruction, profile changes, roadway widenings, etc. may all influence the water supply alterations required.)
Comment:
7.15 |  |  |  | Are the disposition of all curb stops and service boxes located within the proposed slope limits labeled?
Comment:
7.16 |  |  |  | Have drainage calculations and drainage sketches, with invert elevations, been submitted? Please submit an electronic copy of the drainage calulations. Show invert and rim elevations, pipe sizes and pipe material on the plans.
Comment:
8.00 TRAFFIC SIGNAL PLANS
| Y | N | NA
8.1 |  |  |  | Do plans for signalized intersections include signal equipment locations, sequence and timing chart, phasing diagram, list of major items, pavement markings and signs?
Comment:
8.2 |  |  |  | Are signal heads located in the vision cone specified by the MUTCD?
Comment:
8.3 |  |  |  | Have the borings been taken for the mastarm foundation locations?
Comment:
9.00 TRAFFIC MANAGEMENT PLANS (may be 8-1/2 x 11 for simple projects)
| Y | N | NA
9.1 |  |  |  | Does the TMP provide sufficient information to determine that the proposed project can be constructed without undue inconvenience to the public?
Comment:
9.2 |  |  |  | For projects with a detour, is the proposed detour reasonable considering available traffic data? Has it been approved by the local Police and Fire Departments?
Comment:
9.3 |  |  |  | Does the proposed TMP adequately address bicycle and pedestrian accommodation?
Comment:
9.4 |  |  |  | Does the TMP anticipate the proposed changes in grade? Temporary barrier or sheeting may be required, or sufficient area must be available for slopes.
Comment:
9.5 |  |  |  | For bridge projects, does the TMP provide sufficient space to allow for demolition, forming, dowel bar splicing, etc.?
Comment:
10.00 CROSS SECTIONS
| Y | N | NA
10.1 |  |  |  | Are the cross-sections plotted consistent with Section 18.2.14 (PDDG)?
Comment:
10.2 |  |  |  | Is the proposed profile elevation shown on each cross section?
Comment:
10.3 |  |  |  | Are the edge elevations noted on all sections that are superelevated or located on the transition to a superelevated section?
Comment:
10.4 |  |  |  | Is the PC, R, PT and Rate of Bank noted on each sheet that contains a superelevated or transition cross section?
Comment:
10.5 |  |  |  | Are the pay limits for the appropriate excavation types shown properly? (e.g. ITEM 140. Bridge Excavation, ITEM 141. Class A Trench Excavation, ITEM 123. Muck Excavation, ITEM 125. Topsoil Excavated and Stacked, ITEM 121. Class A Rock Excavation)
Comment:
10.6 |  |  |  | Does the proposed cross-section provide sufficient area to install guardrail where necessary?
Comment:
10.7 |  |  |  | Do the proposed cross sections relate well to the adjacent properties? (e.g. slope, material treatment, existing trees, walls, etc.)
Comment:
10.8 |  |  |  | Are cross sections provided at all intersecting driveways?
Comment:
10.9 |  |  |  | Does the gravel box adjust to cut and fill ("daylight") cross sections consistent with PDDG Chapter 5 and the Typical Sections?
Comment:
11.0 SPECIAL PROVISIONS
Special Provisions should only be written when absolutely necessary to address a project specific issue that is not satisfactorily addressed in the STANDARD SPECIFICATIONS and SUPPLEMENTAL SPECIFICATIONS, or if the item has an asterisk in the Cost Estimate (CPE). If a special provision is absolutely necessary, particular attention should be paid to the basis of payment and method of measurement.
| Y | N | NA
11.1 |  |  |  | Is an adequate Scope of Work provided for the project?
Comment:
11.2 |  |  |  | Is a Contract Time Determination (CTD) being developed if the project requires utility relocations?
Comment:
11.3 |  |  |  | Has the Designer coordinated with the utility companies with facilities within the project limits and the MassDOT DUCE to prepare a Project Utility Coordination (PUC) Form to aid in the development of the CTD, including access restraints and contract milestones? Is a complete list of affected utility companies included as a supplement to subsection 7.13 Protection and Restoration of Property? Has the Section 8.14 (Utility Coordination) documentation been included if required?
Comment:
11.4 |  |  |  | Have Early Utility Relocations been identified as a critical need to support the CTD dates? If so, notify the Project Manager to start early coordination with the District and Utility Company.
Comment:
11.5 |  |  |  | Has an Incentive/Disincentive (I/D) checklist been used to determine values for any I/Ds if applicable? If I/Ds are required, has a special provision been provided and has a road user benefit calculation been performed? Was a traditional or alternative schedule evaluation performed to support the use of I/Ds? Enter the amount (3-5% budget) as a comment below so the PM can enter it into the CAPE.
Comment:
11.6 |  |  |  | If the project requires specific information relative to lane closures and traffic management, is the information concisely conveyed as a supplement to subsection 7.09 Public Safety and Convenience?
Comment:
11.7 |  |  |  | Are all the latest manuals, supplemental manuals and documents listed on the front page of the Special Provisions?
Comment:
11.8 |  |  |  | If workhours, other than the standard eight hour shift, are proposed, is (are) the available workshift(s) described as a supplement to Subsection 8.02 Schedule of Operations?
Comment:
11.9 |  |  |  | Was a special provision provided for every item in the estimate (CPE) that contained an asterisk * (the asterisk * identifies a non-standard item that requires a special provision)? Always consider the use of standard items first.
Comment:
11.10 |  |  |  | Do all item descriptions and units contained in the Special Provisions match exactly to the item descriptions and units in the cost estimate (CPE) and the latest Standard Nomenclature list? This is critical for the Contract Documents!
Comment:
11.11 |  |  |  | If the plans contain work that requires specific construction techniques not defined in the STANDARD SPECIFICATIONS., has a special provision been included?
Comment:
11.12 |  |  |  | Is the location for items to be removed and stacked clearly identified? This is usually a Municipal or State Facility that is referenced.
Comment:
11.13 |  |  |  | Have the special provisions been reviewed to ensure that there are no proprietary items specified? (We recommend using Ctrl-F to perform a word search for: "or approved equal", "or equal") If proprietary items are specified, please justify and supply a letter from the Municipality to the Chief Engineer requesting approval. Before each instance of "or approved equal" in the special provisions, products identified shall represent a minimum of three different manufacturers.
Comment:
12.0 COST ESTIMATE
| Y | N | NA
12.1 |  |  |  | Was a completely new 75% cost estimate entered into the Construction Project Estimator (CPE) with the correct programmed Federal Aid, Non-Federal Aid, and Municipal Funding Categories, and an Excel file provided? The estimate is certified by the consultant's Log-In record using CPE.
Comment:
12.2 |  |  |  | Is the methodology to estimate the project using the latest 12 months of the Weighted Average Bid Application (W.A.B.A.), reflecting the latest pricing trends?
Comment:
12.3 |  |  |  | Does the quantity of each item in the estimate (CPE) match the quantity in the Calculation Book? Please perform a quantity review.
Comment:
12.4 |  |  |  | Is there a clear delineation between highway items and bridge items such that all work is included in the estimate and no work is included twice?
Comment:
12.5 |  |  |  | Does the estimate include a payment method for all work associated with the environmental permits?
Comment:
12.6 |  |  |  | Was a bottoms up estimate developed for all lump sum pay items, which considers the construction duration and staging/phasing of the project?
Comment:
The following issues should be considered when reviewing contract estimates. The issues listed
below are based on analysis of common Extra Work Orders:
13.00 SECTION 100
| Y | N | NA
13.1 |  |  |  | Does the 75% CPE include item 100. (Schedule of Operations)? This Fixed Price pay item is part of Subsection 8.02 Construction Scheduling for schedule and utility coordination?
Comment:
13.2 |  |  |  | Is the estimated area quantity for ITEM 101. (Clearing and Grubbing) of a significant amount? If not, then consider using Earth Excavation for removal.
Comment:
13.3 |  |  |  | If ITEM 101. (Clearing and Grubbing) is included in the estimate then ITEM 103. and 104. (Tree Removal items) should not be used. The only exception would be in instances where the tree removal is outside the limits of the clearing and grubbing. In this case, the Detail Sheets should describe the station and offset for the trees to be paid for under ITEMS 103. or 104.
Comment:
13.4 |  |  |  | Does the pavement structure on the PRELIMINARY ESTIMATE OF QUANTITIES - DETAIL SHEET correspond with the Typical Sections?
Comment:
13.5 |  |  |  | All earthwork volumes shall be calculated using the shrinkage and swell criteria from Exhibit 18-30. The contract quantity will then be calculated using the SUMMARY EARTHWORKS QUANTITY SHEET on page 18-73.
Comment:
13.6 |  |  |  | If ITEM 112. (Building Demolition) is included in the contract, consider the use of ITEM 119 (Rodent Control).
Comment:
13.7 |  |  |  | ITEM 120. (Earth Excavation) includes the excavation of a huge variety of materials and should be used whenever possible. If ITEM 120.1 (Unclassified Excavation) is included in the contract, then do not include ITEM 121. (Class A Rock Excavation) and ITEM 120.
Comment:
13.8 |  |  |  | Considering the boring information available, ITEM 121. (Class A Rock Excavation) and ITEM 144. (Class B Rock Excavation) may be required, unless ITEM 120.1 (Unclassified Excavation) is used.
Comment:
13.9 |  |  |  | ITEM 141.1 (Test Pit for Exploration) should be included in nearly every project that will require excavation.
Comment:
13.1 |  |  |  | ITEM 142. (Class B Trench Excavation) will most likely be required if ITEM 202.2 (Manhole 9 to 14 Foot Depth) or ITEM 202.3 (Manhole 14 to 18 Foot Depth) is proposed.
Comment:
13.11 |  |  |  | Is ITEM 150.1 (Special Borrow) appropriate based on the type of construction involved and the boring information?
Comment:
13.12 |  |  |  | Consider ITEM 156. (Crushed Stone) for contracts that include drainage or water supply work.
Comment:
14.00 SECTION 200
| Y | N | NA
14.1 |  |  |  | In areas with a significant amount of existing utilities, consideration should be given to include ITEMS 204. (Gutter Inlet) and 238.XX (Ductile Iron Pipe).
Comment:
14.2 |  |  |  | Trunklines 36" (900 mm) or greater require ITEM 203. (Special Manhole)
Comment:
14.3 |  |  |  | Grade changes of more than 6" (150 mm) require ITEM 220.5 (Drainage Structure Remodeled).
Comment:
14.4 |  |  |  | The condition of the existing drainage system should be evaluated to determine if ITEMS 221. (Frame and Cover) and 222.X (Frame and Grate - Cascade Type) should be specified rather than 220. (Drainage Structure Adjusted). Also 220.2 (Drainage Structure Rebuilt) should be considered.
Comment:
15.00 SECTION 300
| Y | N | NA
15.1 |  |  |  | Contracts that include alterations to a water system will generally require ITEM 156. (Crushed Stone), ITEM 309. (Ductile Iron Fittings for Water Pipe) and ITEM 903. (3000 PSI, 1.5 Inch, 470 Cement Concrete).
Comment:
15.2 |  |  |  | Consider ITEMS 357.XX (Gate Boxes) and 381. (Service Box) to allow for existing boxes that are not adjustable.
Comment:
15.3 |  |  |  | Consider contingency items for service lines.
Comment:
15.4 |  |  |  | Projects involving roadway widening may require ITEM 376.2 (Hydrant - Removed and Reset).
Comment:
15.5 |  |  |  | Will temporary or transitional water service use be required? Will weekend or evening work be required to implement?
Comment:
16.00 SECTION 400
| Y | N | NA
16.1 |  |  |  | ITEM 440. (Calcium Chloride for Roadway Dust Control) and ITEM 443. (Water for Roadway Dust Control) should be included in all projects with full depth reconstruction.
Comment:
16.2 |  |  |  | ITEM 452. (Asphalt Emulsion for Tack Coat) should be estimated at a rate of 1/20 gal/sy (0.20 l/sm).
Comment:
16.3 |  |  |  | ITEM 451. (HMA for Patching), ITEM 452. (Asphalt Emulsion for Tack Coat), and ITEM 453. (HMA Joint Sealant) should be included in all projects that include paving.
Comment:
16.4 |  |  |  | ITEM 472. (Temporary Asphalt Patching) should be included in nearly every project requiring paving.
Comment:
17.00 SECTION 500
| Y | N | NA
17.1 |  |  |  | Curbing to be set on radius of 100 ft (30 m) or less shall paid for using the appropriate "curved" curb item.
Comment:
17.2 |  |  |  | Edging to be set on radius of 10 ft (3 m) or less shall paid for using the appropriate "curved" edging item.
Comment:
18.00 SECTION 600
| Y | N | NA
18.1 |  |  |  | Wood blocks must be used on all guardrail installations, as shown in the latest Construction Standard Details.
Comment:
18.2 |  |  |  | Refer to Engineering Directive E-20-004 for the design of impact attenuators.
Comment:
18.3 |  |  |  | Buried ends are measured as units of 37.5 ft (11.46 m)
Comment:
18.4 |  |  |  | Leading and trailing ends at bridges are measured as units of 25 ft (7.64 m).
Comment:
18.5 |  |  |  | If Type SS highway guard is proposed, then ITEM. 628.XX (Transition Items) will be required if transitioning to a Bridge Rail, Rigid Barrier, or Thrie Beam.
Comment:
18.6 |  |  |  | Guardrail constructed to a radius of less than 150 ft (45 m) will be paid for under the appropriate curved guardrail item.
Comment:
18.7 |  |  |  | The Method of Measurement and Basis of Payment for stone masonry walls has been revised in the Supplemental Specifications. ITEM 685. (Stone Masonry Wall in Cement Mortar) now includes the cement concrete footing and the coping material. Excavation is still paid for under ITEM 141 (Class A Trench Excavation).
Comment:
19.00 SECTION 700
| Y | N | NA
19.1 |  |  |  | All projects shall include ITEM 748. (Mobilization). This item should be estimated at 3% of construction costs.
Comment:
20.00 SECTION 800
| Y | N | NA
20.1 |  |  |  | Refer to Engineering Directive E-12-009 for estimating procedures for ITEM 851.
Comment:
20.2 |  |  |  | All guardrail installations require delineators. Refer to Subsection 828.60 for estimating.
Comment:
20.3 |  |  |  | ITEM 854.034 and/or 854.036 (Temporary Paving Markings) should be included for temporary pavement markings on proposed top course.
Comment:
20.4 |  |  |  | If the TMP requires the removal of pavement markings, include ITEM 854.1 (Pavement Marking Removal).
Comment:
20.5 |  |  |  | If ITEM 853.2 (Temporary Barrier) is specified, will ITEM 853.21 (Temporary Barrier Removed and Reset) be required?
Comment:
20.6 |  |  |  | Will ITEM 856.12 (Portable Changeable Message Sign) or ITEM 856. (Arrow Board) be required?
Comment:
21.00 SECTION 900
| Y | N | NA
21.1 |  |  |  | If ITEM 987., 987.1, 987.12 or 987.2 (Special Slope Paving Under Bridge Items) is proposed, refer to Engineering Directive E-99-001 for applicability.
Comment:
22.0 CONCLUSIONS
| Y | N | NA
22.1 |  |  |  | Did your DESIGN FIRM conduct a QC/QA review for this 75% submission?
Comment:
22.2 |  |  |  | Is the 75% estimated Total Federal Participating Construction Cost (TFPCC) consistent with the TIP? This includes the Office Estimate plus 5-10% Construction Engineering, 10 % Construction Contingency, 50% of Utility Force Account costs, Traffic Police, and any additional 999. items. If not, please submit an explanation for MassDOT's review.
Comment:
22.3 |  |  |  | Has an independent constructability review been performed for this project?
Comment:
22.4 |  |  |  | Do the design plans represent a project that is reasonable from a constructability standpoint with respect to construction access and techniques, and the available right of way? Will the contractor be able to build the project within the ROW, as defined on the plans?
Comment:
22.5 |  |  |  | If applicable, have staging plans been developed and Temporary Traffic Control Plans (such as one-way alternating or detour plans) been provided? Please be prepared to provide justification for the choices made.
Comment:
22.6 |  |  |  | Are all required draft Environmental Permit Applications submitted with your 75% Design Submission, unless previously submitted? Note: The 75% submission will be rejected or put on hold until the required draft permits are submitted.
Comment:
23.0 DESIGN SCHEDULE
| Y | N | NA
23 |  |  |  | Was the 75% Design Submission on time in line with the latest approved Design Schedule? Was an updated schedule submitted with this design submission?
Comment:
Designer Certification
The Designer certifies that the 75% Design Plans have been reviewed in accordance with this checklist and that all responses are correct and accurately reflect the information presented on the submitted Design Plans.
Consultant Firm Principal Date
Note: Please make sure this checklist is attached to your Firm's submission/transmittal PDF letter.
|  |  |  | REVIEW SCORE: | 0
A review score from 0-10 (10 is high) may be applied by the MassDOT Project Manager if it is determined to be necessary based on the condition of the design submission.

## PDDG 2-A-10, 100% Checklis
PROJECT/DESCRIPTION________________________________________________ |  |  |  |  | Project #
100% - PS&E DESIGN SUBMISSION & REVIEW CHECKLIST Submission Date
| PURPOSE |  |  | The purpose of the 100% review is to ensure that all comments from the 75% review have been satisfactorily addressed. The review also provides an opportunity to ensure that a complete contract package will be available for bidding and construction purposes.
| GENERAL |  |  | The submittal shall include responses to 75% review comments; completed plans, special provisions, estimate and detail sheets, contract time determination schedules (if applicable), bottoms up estimates (if applicable), incentive/disincentive (I/D) checklists and provisions (if applicable), traditional/alternative schedule evaluations to support I/Ds (if applicable), road user calculations as applicable and an updated design schedule.
Any question listed below with a No (N) or Not Applicable (NA) answer requires a written comment.
| SCORING |  |  | Each comment/question below will be reviewed and scored by MassDOT during the review period. A maximum score of 2 can be given for each question/comment: 2 (meets), 1 (partially meets), or 0 (does not meet). The maximum score is 100 for the entire submission/review checklist.
| 1.0 SUBMISSION REQUIREMENTS |  |  |  |  | SCORE
| Y | N | NA |  |  | 0
1.1 |  |  |  | Have all the design plan PDFs been flattened for the 100% Bluebeam Review Session?
|  |  | Comment: |  |  | 0
1.2 |  |  |  | Have all 75% review comments or previous design submission comments been addressed (with a written response)?
|  |  | Comment: |  |  | 0
1.3 |  |  |  | Did the Design Consultant provide a Summary of what has changed since the last submission (not as a result of any MassDOT comments)? This can be very helpful for the reviewers when items have been added or deleted from the project. Please keep track of any changes on a summary sheet.
|  |  | Comment: |  |  | 0
1.4 |  |  |  | Was a Comment Resolution Meeting (CRM) held for the previous review comments?
|  |  | Comment: |  |  | 0
| 2.0 PLANS |  |  |  |  | SCORE
| Y | N | NA | Title Sheet |  | 0
2.1 |  |  |  | Are the latest documents referenced on the Title Sheet?
|  |  | Comment: |  |  | 0
Typical Sections
2.2 |  |  |  | All proposed materials should be labeled on the Typical Sections. Are the material descriptions identical to the items provided in the CPE or the material description in the STANDARD SPECIFICATIONS FOR HIGHWAYS AND BRIDGES?
|  |  | Comment: |  |  | 0
Plans/Drawings
2.3 |  |  |  | Is the disposition of all existing and proposed features located within the limits of work clearly labeled? There should be no overlapping of text.
|  |  | Comment: |  |  | 0
2.4 |  |  |  | Do all the walks, sidewalks, crosswalks, and curbcut wheelchair ramps meet the requirements listed in Americans with Disabilities Act Accessibility Guidelines (ADAAG) and Public Rights of Way Accessibility Guidelines (PROWAG), which are discussed in the Engineering Directive E-12-005?
|  |  | Comment: |  |  | 0
2.5 |  |  |  | If not, have all Architectural Access Board (AAB) violations been identified and clearly discussed for MassDOT's review, and an AAB variance to AAB Regulations submitted to the Project Manager?
|  |  | Comment: |  |  | 0
2.6 |  |  |  | Are there any conflicts between the Plans and the STANDARD SPECIFICATIONS? Always use the Standard Specifications when possible.
|  |  | Comment: |  |  | 0
2.7 |  |  |  | Does every item of work shown on the Plans have an associated pay item?
|  |  | Comment: |  |  | 0
2.8 |  |  |  | Does the plan sheet numbering match the index, and is the Project File No. provided on each plan sheet?
|  |  | Comment: |  |  | 0
| 3.0 SPECIAL PROVISIONS |  |  |  |  | SCORE
|  |  |  | Special Provisions should only be written when absolutely necessary to address a project specific issue that is not satisfactorily addressed in the STANDARD SPECIFICATIONS and SUPPLEMENTAL SPECIFICATIONS, or if the item has an asterisk in the Construction Project Estimator(CPE). If a special provision is absolutely necessary, particular attention should be paid to the basis of payment and method of measurement. |  | 0
| Y | N | NA
3.1 |  |  |  | Is an adequate Scope of Work provided for the project?
|  |  | Comment: |  |  | 0
3.2 |  |  |  | Has a Contract Time Determination (CTD) been developed?
|  |  | Comment: |  |  | 0
3.3 |  |  |  | Has the Project Utility Coordination (PUC) Form been utilized in the development of the CTD, including access restraints and contract milestones?
|  |  | Comment: |  |  | 0
3.4 |  |  |  | Has an Incentive/Disincentive (I/D) checklist been used to determine values for any I/Ds if applicable? If I/Ds are required, has a special provision been provided and has a road user benefit calculation been performed? Was a traditional or alternative schedule evaluation performed to support the use of I/Ds? Enter the amount (3-5% budget) as a comment below so the PM can enter it into the CAPE.
|  |  | Comment: |  |  | 0
3.5 |  |  |  | Has the project been checked for any outdated specifications, requiring an update or superseded by Supplemental Specifications or Interim Supplemental Specifications?
|  |  | Comment: |  |  | 0
3.6 |  |  |  | Are all the latest manuals, supplemental manuals and other documents that are to be part of the contract by reference, listed on the special provisions front page?
|  |  | Comment: |  |  | 0
3.7 |  |  |  | If the project requires specific information relative to lane closures and traffic management, is the information concisely conveyed as a supplement to subsection 7.09 Public Safety and Convenience?
|  |  | Comment: |  |  | 0
3.8 |  |  |  | Is a complete list of affected utility companies included as a supplement to subsection 7.13 Protection and Restoration of Property?
|  |  | Comment: |  |  | 0
3.9 |  |  |  | Is (are) the use of non-standard workhours required for this project? Has approval from the Chief Engineer been requested through the Project Manager?
|  |  | Comment: |  |  | 0
3.1 |  |  |  | Is (are) the available workshift(s) described as a supplement to Subsection 8.02 Schedule of Operations?
|  |  | Comment: |  |  | 0
3.11 |  |  |  | Was a special provision provided for every item in the estimate (CPE) that contained an asterisk * (the asterisk * identifies a non-standard item that requires a special provision)?
|  |  | Comment: |  |  | 0
3.12 |  |  |  | Do all item descriptions and units contained in the special provisions match exactly to the item descriptions and units in the cost estimate (CPE)?
|  |  | Comment: |  |  | 0
3.13 |  |  |  | Do all special provisions include a very specific, unambiguous method of measurement and basis of payment that will minimize the potential for disputes during construction?
|  |  | Comment: |  |  | 0
3.14 |  |  |  | Is the location for items to be removed and stacked clearly identified? This is usually a Municipal or State Facility that is referenced.
|  |  | Comment: |  |  | 0
3.15 |  |  |  | Have the special provisions been reviewed to ensure there are no proprietary items specified? A minimum of three (3) different suppliers/manufacturers shall be provided (Recommend to provide a word search for: "or approved equal", "or equal" to help find these items). If proprietary items are specified on a municipal project, please justify and supply a letter from the Municipality to the Chief Engineer requesting approval.
|  |  | Comment: |  |  | 0
3.16 |  |  |  | Have Early Utility Relocations been identified as a critical need to support the CTD dates? If so, notify the PM, DUCE and Utility Engineer to start early coordination.
|  |  | Comment: |  |  | 0
3.17 |  |  |  | If required, has the Section 8.14 (Utility Coordination) documentation been included?
|  |  | Comment: |  |  | 0
| 4.0 COST ESTIMATE |  |  |  |  | SCORE
| Y | N | NA |  |  | 0
4.1 |  |  |  | Was a completely new estimate entered into the Construction Project Estimator (CPE) with the correct programmed Federal Aid, Non-Federal Aid, and Municipal Funding Categories, and an Excel file provided? The estimate is certified by the consultant's Log-In record using CPE.
|  |  | Comment: |  |  | 0
4.2 |  |  |  | Is the methodology used to estimate the project consistent with the STANDARD SPECIFICATIONS, the latest SUPPLEMENTAL SPECIFICATIONS, and using the latest 12 months of the Weighted Average Bid Application (W.A.B.A.), reflecting the latest pricing trends? (some projects may require an exception to using the WABA).
|  |  | Comment: |  |  | 0
4.3 |  |  |  | Does every item of work shown on the plans have an associated pay item? (Yes, this is a repeat question that requires much attention!)
|  |  | Comment: |  |  | 0
4.4 |  |  |  | Does the quantity of each item in the estimate (CPE) match the quantity in the Calculation Book? Please perform a quantity review.
|  |  | Comment: |  |  | 0
4.5 |  |  |  | Do the unit prices in the CPE reflect the magnitude of the quantity of work vs. mobilization/set up costs? (e.g. 100 Tons of ITEM 460. on a bridge replacement project will cost significantly more than 100,000 Tons on an Interstate resurfacing project)
|  |  | Comment: |  |  | 0
4.6 |  |  |  | Has the cost estimate (CPE) been cross referenced with the Special Provisions? Items identified on the estimate often do not agree with items provided in the special provisions.
|  |  | Comment: |  |  | 0
4.7 |  |  |  | Was a bottoms up estimate (BUE) developed for all lump sum pay items? The BUE should consider the anticipated construction phasing and duration.
|  |  | Comment: |  |  | 0
4.8 |  |  |  | Are there any outdated construction items still being used for this project that have been superceded?
|  |  | Comment: |  |  | 0
4.9 |  |  |  | Are there any Non-Participating (100% City/Town) Items being used for this project? And have you received the Municipality's written approval?
|  |  | Comment: |  |  | 0
4.1 |  |  |  | Have standard construction items been considered first before using non-standard items (non-standard items typically generate more extra work orders)?
|  |  | Comment: |  |  | 0
Detail Sheets
4.11 |  |  |  | Do the Earthwork quantities on the PRELIMINARY ESTIMATE OF QUANTITIES - DETAIL SHEET correspond with those noted on the Summary Quantity Sheet?
|  |  | Comment: |  |  | 0
4.12 |  |  |  | Does the pavement structure on the PRELIMINARY ESTIMATE OF QUANTITIES - DETAIL SHEETS correspond with the Typical Sections?
|  |  | Comment: |  |  | 0
4.13 |  |  |  | Are all items on the detail sheets, not completely described and located on the plans, adequately described by station and offset?
|  |  | Comment: |  |  | 0
Calculation Book
4.14 |  |  |  | Have drainage sketches and invert elevations been included in the Calculation Book?
|  |  | Comment: |  |  | 0
4.15 |  |  |  | Has an index with page numbers been prepared for the Calculation Book?
|  |  | Comment: |  |  | 0
| 5.0 CONCLUSIONS |  |  |  |  | SCORE
| Y | N | NA |  |  | 0
5.1 |  |  |  | Did your DESIGN FIRM conduct a QC/QA review for this 100% submission?
|  |  | Comment: |  |  | 0
5.2 |  |  |  | Is the estimated Total Federal Participating Construction Cost (TFPCC) consistent with the amount programmed on the State Transportation Improvement Program (STIP)?
|  |  | Comment: |  |  | 0
5.3 |  |  |  | Has an independent constructability review been performed for this project?
|  |  | Comment: |  |  | 0
5.4 |  |  |  | Does the Participating Cost include all the Utility Estimates, any 999. Items such as Railroad, and adequate Traffic Police costs?
|  |  | Comment: |  |  | 0
5.5 |  |  |  | Do the plans represent a project that is reasonable from a constructability standpoint with respect to construction access and techniques, and the available right of way? Will the contractor be able to build the project within the ROW, as defined on the plans?
|  |  | Comment: |  |  | 0
5.6 |  |  |  | Have all Environmental Permits been secured? If not, what permits still remain?
|  |  | Comment: |  |  | 0
6.0 DESIGN SCHEDULE - BONUS (0-5)
| Y | N | NA
6 |  |  |  | Was the Design Submission on time in line with the latest approved Design Schedule?
|  |  | Comment: |  |  | 0
DESIGNER CERTIFICATION
Y
The Designer certifies that the 100% Design Plans have been reviewed in accordance with this checklist and that all responses are correct and accurately reflect the information presented on the submitted Design Plans.
|  |  |  | Consultant Firm Principal Signature |  | Date
Note: Please make sure this checklist is attached to your Firm's submission/transmittal PDF letter.
|  |  |  | TOTAL REVIEW SCORE (including Schedule BONUS): |  | 0

## PDDG 9-A-1, Pavement Checklist
MassDOT - Highway Division
Project Development and Design Guide
Appendix 9-A-1, Pavement Design Checklist
I. Project Identification
City/Town: |  |  | Project Number:
Street/Rte. No.: |  |  | Functional Class:
From Station: |  |  | To Station:
From (Landmark): |  |  | To (Landmark):
Date: |  |  | Design Engineer:
II. Traffic Data
Current ADT (year): |  |  | Future ADT (Year)*:
T (ADT): |  |  | T (PEAK HR.):
No. of Lanes: |  |  | Divided/Undivided:
No. of Shoulders
III. Existing Pavement Information
Year Initially Constructed: |  |  | Overlaid:
Existing Pavement Structure** | Existing Pavement Structure: **
Layer | Depth | Type
Surface _____________
Base ________________
Subbase ________________
Document Existing Pavement Distress ***
Type |  | Extent (percentages) | Severity |  |  | Depth Inches
[ ] Alligator Cracking |  |  | High | Medium | Low
[ ] Block Cracking
[ ] Other Cracking (tranverse, longitudinal, reflective)
[ ] Lane/Shoulder Dropoff
[ ] Potholes
[ ] Rutting (wheelpaths)
[ ] Alligator Cracking
[ ] Delamination
[ ] Utility Patches
Notes: | * Minimum 20 yr. servicelife
** If existing pavement is Portland Cement Concrete, provide detailed description.
2. | *** Provide photographs as needed to demonstrate pavement distress
IV. Proposed Corrective Work to Existing Pavement (if any)
[ ] Resurfacing |  |  | [ ] Subdrainage Pipes
[ ] Full Depth Construction |  |  | [ ] Deep Patching/Pothole Filling
[ ] Pavement Preservation Treatment |  |  | [ ] Localized Repairs
[ ] Pavement Milling |  |  | [ ] Crack Sealing *
[ ] Pavement Micromilling |  |  | [ ] SAMI, Fabric Interlayer or other
[ ] Pavement Shims
Discussion (if needed):
Any special site conditions which may limit the practical choices.
V. Proposed Scope of Work
[ ] New Pavement |  |  | [ ] Pavement Overlay
[ ] Reconstructed Pavement |  |  | [ ] With widening
[ ] Full Depth Reclamation |  |  | [ ] Without widening
[ ] Surface Recycling (hot/cold in place) |  |  | [ ] With corrective work to existing pavement
[ ] Cold-Mix |  |  | [ ] Without corrective work to existing pavement
[ ] Hot-Mix |  |  | [ ] Pavement Preservation
Discussion (if needed):
VI. Briefly discuss reasons for proposed work, including estimated costs and any special site conditions which may limit the practical choices.
Discussion (if needed):
* Only done under certain circumstance and with the approval of PDE

## Traffic & Safety Eng. Check
PROJECT/DESCRIPTION _____________________________________________________________
25%TRAFFIC ENGINEERING REVIEW CHECKLIST Submission Date _______
PURPOSE
The 25% Traffic Engineering Review is intended to provide MassDOT the opportunity to evaluate the proposed design and Functional Design Report relative to current design standards, operation impacts, safety impacts and other potential community concerns associated with the proposed design.
GENERAL
This checklist represents the minimum amount of issues that should be considered when reviewing a 25% traffic submittal. The information below is not intended to address all aspects of report or plan preparation. To the extent practical, any comments relative to plan preparation made at the 25% stage will certainly improve the quality of the 75% submittal.
Any question listed below with a No or N/A answer requires a written comment.
I. Functional Design Report
| Yes | No | N/A | A. Existing Conditions
1 |  |  |  | Is a description of the project study area included?
Comment:
2 |  |  |  | Is the project location (locus) map included?
Comment:
3 |  |  |  | Is a discussion of existing deficiencies and an evaluation of the existing signs, signals and markings included?
Comment:
| Yes | No | N/A | B. Traffic Volumes
4 |  |  |  | Is the traffic count data less than 2 years old from the date of FDR submission?
Comment:
5 |  |  |  | Are the Automatic Traffic Recorder (ATR) Counts included for the minor street approach for signalized intersections?
Comment:
6 |  |  |  | Are Manual Turn Movement Counts (TMC): Peak hour data for all study intersections included?
Comment:
7 |  |  |  | Are Peak Hour Factors (PHF) identified?
Comment:
8 |  |  |  | Are heavy vehicle, bicycle, and pedestrian count data included in the TMC?
Comment:
9 |  |  |  | Do the base year volumes represent an average month during the year the FDR is submitted or no more than 2 years for MEPA permitted projects?
Comment:
10 |  |  |  | Have seasonal factors been reviewed and applied as necessary?
Comment:
11 |  |  |  | Do the future year volumes represent a minimum of 7 years from the base year?
Comment:
12 |  |  |  | Do the future year volumes include background growth and site development as necessary?
Comment:
13 |  |  |  | Are trip generation/distribution data for private development trips schematically displayed on the network?
Comment:
14 |  |  |  | Are base year and future year traffic volume networks provided?
Comment:
| Yes | No | N/A | C. Safety Analysis
15 |  |  |  | Are three years of Crash Data analyzed for project locations? (5 years is preferred)
Comment:
16 |  |  |  | Are crash rate calculations included for all study area intersections and segments?
Comment:
17 |  |  |  | Are collision diagrams provided for all study area intersections with more than 3 crashes per year?
Comment:
18 |  |  |  | Is a collision map provided for all study area segments?
Comment:
19 |  |  |  | Was the Safety Review Prompt List utilized during a site visit?
Comment:
20 |  |  |  | Is discussion regarding the Safety Review Prompt List included?
Comment:
| Yes | No | N/A | D. MUTCD Signal Warrants
21 |  |  |  | Is traffic count data provided for a minimum of the 8 highest hours for the major streets and minor street?
Comment:
22 |  |  |  | Was the minor street count data collected by a manual turning movement count method?
Comment:
23 |  |  |  | Does the signal warrant analysis follow procedures from MUTCD?
Comment:
24 |  |  |  | Do proposed signal installations meet an 8-hour volume warrant?
Comment:
| Yes | No | N/A | E. Operational Analysis
25 |  |  |  | Are the intersection approaches evaluated using observed/appropriate peak hour factors?
Comment:
26 |  |  |  | Are heavy vehicle percentages used in the analyses?
Comment:
27 |  |  |  | Are pedestrian volumes and phasing incorporated into the analyses?
Comment:
28 |  |  |  | Are capacity analyses completed for all the required analysis scenarios?
Comment:
29 |  |  |  | Do capacity analyses reflect the existing and proposed geometry conditions?
Comment:
30 |  |  |  | Are coordinated signals/closely spaced intersections evaluated under a systems analysis?
Comment:
31 |  |  |  | Are the 50th and 95th percentile vehicle queues documented?
Comment:
| Yes | No | N/A | F. Proposed Design
32 |  |  |  | Is a description of the proposed geometric changes and/or alternative designs included?
Comment:
33 |  |  |  | Is a narrative describing the pedestrian and bicycle accomodation improvments included?
Comment:
34 |  |  |  | Is discussion included of how the proposed design will alter the traffic control conditions?
Comment:
35 |  |  |  | Was a roundabout design an alternative considered?
Comment:
36 |  |  |  | Are the Section 61 Findings attached for the Private Development projects?
Comment:
37 |  |  |  | Do all traffic calming design treatments (where allowed) follow the Traffic Calming Guidelines?
Comment:
38 |  |  |  | Do all study area intersections include corrective design measures?
Comment:
39 |  |  |  | Has "work to be done by others" been factored into schedule/design?
Comment:
| Yes | No | N/A | G. Traffic Management
40 |  |  |  | Is a Construction Management Outline included?
Comment:
41 |  |  |  | Are the appropriate traffic counts and capacity analyses included?
Comment:
II. 25% Design Plans
| Yes | No | N/A | A. Basic Design Plan Set
42 |  |  |  | Does the plan set follow the preparation guidelines specified in the current Project Development and Design Guidebook?
Comment:
43 |  |  |  | Do the plans provide linework and details of the existing conditions for use in reference to the proposed design?
Comment:
44 |  |  |  | Do the proposed roadway cross-sections conform to current standards?
Comment:
45 |  |  |  | Are provisions made for bicycle accommodation where applicable?
Comment:
46 |  |  |  | Do pedestrian facilities meet the Massachuesetts Architectural Access Board (MAAB) standards?
Comment:
| Yes | No | N/A | B. Traffic Signal Plans
47 |  |  |  | Do the plans indicate the proper placement of the signal heads?
Comment:
48 |  |  |  | Are the signal head configurations in conformance with the MUTCD standards?
Comment:
49 |  |  |  | Do the signal layout plans show the proposed lane assignments and stop lines?
Comment:
50 |  |  |  | Is the Sequence and Timing Chart provided on the plans?
Comment:
51 |  |  |  | Is the Preferential Phasing Diagram, including pedestrian phases, shown on the signal plan?
Comment:
52 |  |  |  | Is a Time-Space Diagram for the interconnected signals included?
Comment:
53 |  |  |  | Is signal detector type and location included on the signal plans?
Comment:
| Yes | No | N/A | C. Traffic Management Plans (TMP)
54 |  |  |  | Are preliminary Temporary Traffic Control Plans provided?
Comment:
55 |  |  |  | Do the typical layouts follow MassDOT's Standard Details and Drawings for the Development of TMP's?
Comment:
56 |  |  |  | If required, have the detour routes been clearly defined?
Comment:
57 |  |  |  | Is pedestrian and bicycle accommodation maintained during construction?
Comment:

## ITS Submissions_9.24.12
Intelligent Transportation System Plan Submissions
25% Design Submissions should be made available for Intelligent Transportation System section review when a Project Scope includes work on or in the vicinity of the facilities listed below. 75% and 100% submittals are not necessary if approved at 25% (unless design has changed).
Facilities subject to ITS Review:
| Route Number | STATUS | FROM | TO
| 1 | Current | I-95 in Topsfield | Tobin Bridge in Boston
| 1 | Current | Route 128/I-95 in Dedham | I-495 in Wrenthem
| 1 | FUTURE | I-495 | RI state line
| 146 | FUTURE | I-90 (MassPike) in Millbury | RI State Line in Uxbridge
| 2 | FUTURE | NY state line | Route 91
| 2 | FUTURE | I-91 | Route 32 Athol
| 2 | FUTURE | Route 32 | I-190
| 2 | FUTURE | I-190 | I- 495
| 2 | Current | I-495 in Littleton | Route 128/1-95 in Lexington
| 2 | Current | Route 128/I-95 in Lexington | Memorial Drive in Cambridge
| 3 | Current | NH state line | Route 495
| 3 | Current | I-495 | Route 128/I-95 in Burlington
| 3 | Current | I-95/Route 3Split in Braintree | Sagamore Bridge
| 6 | FUTURE | Sagamore Bridge | Orleans Rotary
|  | FUTURE | Orleans Rotary | Provincetown
| 7 | FUTURE | VT state line | Route 9 in Pittsfield
|  | FUTURE | Route 9 in Pittsfield | I-90 MassPike
|  | FUTURE | I-90 MassPike | CT state line
| 9 | FUTURE | Pittsfield | Route 91 in Northampton
|  | FUTURE | Route 91 Northampton | Route 32 in Ware
|  | FUTURE | Route 32 in Ware | I-290 in Worcester
|  | FUTURE | I-290 in Worcester | I-495 in Westborough
|  | Current | I-495 in Westborough | Speen St. in Natick
|  | Current | Speen St. in Natick | Route 128/I-95 in Wellesley
|  | Current | Route 128/I-95 in Wellesley | Longwood Medical Center in Boston
| 24 | FUTURE | RI state line | Route 140 in Taunton
|  | Current | Route 140 in Taunton | Route 495 in Raynham
|  | Current | Route 495 in Raynam | Route 128/I-95 in Canton
| 28 | Current | Bourne Bridge | Falmouth
| I-291 | Current | I-90 | I-91
| I-84 | FUTURE | CT state line | I-90 MassPike in Sturbridge
| I-90 (MassPike) | FUTURE | NY state line | I-91 Springfield
|  | Current | I-91 Springfield | I-84 Sturbridge
|  | FUTURE | I-84 Sturbridge | I-290 Worcester
|  | Current | I-290 Worcester | I-495 Northborough
|  | Current | I-495 Northborough | Weston Tolls
|  | Current | Weston Tolls | Allston Tolls
|  | Current | Allston Tolls | Logan Airport
| I-91 | Current | VT state line | Route 2 in Greenfield
|  | Current | Route 2 in Greenfield | Route 9 in Northampton
|  | Current | Route 9 Northampton | I-90 MassPike in Springfield
|  | Current | I-90 MassPike in Springfield | CT state line
| I-93 | Current | NH state line | I-495 in Lawrence
|  | Current | I-495 in Lawrence | Route 128/I-95 in Reading
|  | Current | Route 128/I-95 in Reading | O’Neill Tunnel Boston
| I-93-S.E.Expressway | Current | O’Neill Tunnel in Boston | Route 3 split in Braintree
| I-95 | Current | NH state line | I-495 in Georgetown
|  | Current | I-495 in Georgetown | Route 128 in Lynnfield
| I-95 | Current | RI state line | I-495 in Foxborough
|  | Current | I-495 in Foxborough | Route 128 in Canton
| Route128/I-95 | Current | RT 128 in Gloucester | I-95 in Lynnfield
|  | Current | I-95 in Lynnfield | I-93 in Reading
|  | Current | I-93 in Reading | Route 3 in Burlington
|  | Current | Route 3 in Burlington | I-90 MassPike in Wellesley
| Route 128/I-95 | Current | I-90 MassPike in Wellesley | I-95 split in Canton
|  | Current | I-95 split in Canton | Route 3 split in Braintree
| 140 | FUTURE | Route 24 in Raynham | I-195 in New Bedford
| 146 | FUTURE | RI state line | I-290 Worcester
| I-190 | FUTURE | Route 2 in Leominster | I-290 in Worcester
| I-195 | FUTURE | RI state line | Route 24 in Fall River
|  | FUTURE | Route 24 in Fall River | Route 140 in New Bedford
|  | FUTURE | Route 140 in New Bedford | Route 25 in Wareham
| I-290 | FUTURE | Route 495 | Route 190
|  | FUTURE | Route 190 | I-90 MassPike
| I-395 | FUTURE | I-90 MassPike in Auburn | RI state line
| I-495 | Current | Bourne Bridge | I-195 in Mansfield
|  | Current | I-95 in Mansfield | I-90 MassPike in Westborough
| I-495 | Current | I-90 MassPike in Westborough | Route 3 in Lowell
|  | Current | Route 3 in Lowell | Route 93 in Lawrence
|  | Current | Route 93 in Lawrence | I-95 in Salisbury
| Memorial Drive | Current | Elliot Bridge | Land Boulevard in Cambridge
| Soldiers Field Road | Current | Harvard Univ. Stadium | B.U. Bridge
| Storrow Drive | Current | B.U. Bridge | Leverett Circle
| O’Neill Tunnel | Current | Zakim Bridge | South Station
| Sumner Tunnel | Current | Logan Airport | I-93 Central Artery
| Callahan Tunnel | Current | I-93 Central Artery | Logan Airport
| Route 1A | FUTURE | Bell Circle, Revere | Logan Airport

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only