Integrating Medicare and Medicaid for 
Individuals with Dual Eligibility

Open Public Meeting Presentation

February 28, 2012

Slide 1

MassHealth Demonstration to Integrate Care for Dual Eligibles

Open Public Meeting

February 28, 2012

1 Ashburton Place, Boston

Slide 2

Agenda for Today

- Final Proposal

- Implementation Timeline

- Program Design Operational and Implementation Planning

- Topical Workgroups

- Next Steps

Slide 3

Final Proposal

- Submitted to CMS February 16

  - Included 34 Letters of Support from a range of stakeholders, the Governor, and state agencies

  - Included cover memo outlining revisions made to the draft proposal in light of public comments

  - All documents posted on Duals Initiative website: www.mass.gov/masshealth/duals

- CMS posted final proposal for public comment

  - www.IntegratedCareResourceCenter.com/icmstateproposals.aspx

  - Comments due by March 19, 5 pm to MedicareMedicaidCoordination@cms.hhs.gov

Slide 4

Implementation Timeline

- April 2:	Interested Entity Notice of Intent to Apply due to CMS

- April 27: 	MOU signed by CMS and MA

- April 27: 	Procurement Release

- April 30: 	New Part D formularies due to CMS

- June 4:  	Procurement responses due to CMS/MassHealth

- July 30:  	ICO selection completed

- Sept. 20: 	Execute 3-way contracts (CMS/MassHealth/ICOs)

- Oct. 1: 	Notify members about ICO options

      - CMS - Medicare & You handbook

      - MassHealth – letter

- Jan. 1, 2013: Demonstration begins – ICOs must be able to accept enrollments

- Provide consumer and family member role in overseeing ICOs

- Provide more details on appeals and grievances

- Protect members from losing access to current providers

See all CMS deadlines for interested organizations in CMS’s 1/25/12 Guidance for Organizations Interested in Offering Capitated Financial Alignment Demonstration Plans

Slide 5

Program Design Operational and Implementation Planning

- MOU with CMS will include:

  - Statement of Initiative

  - Specific Purpose of the MOU

  - Program Design / Operational Plan

    - Program Authority

    - Contracting Process

    - Enrollment

    - Delivery Systems and Benefits

    - Beneficiary Protections, Participation and Customer Service

    - Integrated Appeals

    - Administration and Reporting

    - Quality Management

    - Financing and Payment

    - Evaluation

Slide 6

Program Design Operational and Implementation Planning

- MOU appendices will include:

  - Definitions

  - CMS Standards and Conditions Checklist and Supporting State Documentation

  - Details of State Initiative and Geographic Area

  - Medicaid Authorities and Variances

  - Medicare Authorities and Variances

  - Payments to Participating Plans

  - Operation Manual

Slide 7

Process

- Establish and convene topical workgroups

  - Composed primarily of stakeholder representatives with subject matter expertise

  - Led by MassHealth

  - Meetings in mid March

- Start with 5 workgroups; may convene others in subsequent weeks

- Groups will be charged with developing specific implementation recommendations to MassHealth

- To participate in a group, please RSVP to duals@state.ma.us

- Participants should be prepared to engage in focused discussion, and offer constructive input

Slide 8

Workgroup #1: Quality Metrics

- Areas to discuss include:

  - Choice of measures for monitoring quality of ICO care

  - Measures addressing both medical care and LTSS

  - Performance targets

  - Data collection methods beyond claims and encounter data (enrollee surveys, focus groups, key informant interviews, etc.)

- When and where:

  - Tuesday, March 13, 10 am-12 noon, One Ashburton Place, 21st Floor, Boston

Slide 9

Workgroup #2: Grievances, Appeals and Ombudsman

- Areas to discuss include:

  - Ensuring robust and unified processes to serve and protect beneficiaries

  - Requirements for ICOs’ internal grievances and appeals processes

  - Integrated external appeals process that maintains rights and protections afforded by Medicare and Medicaid

  - Ombudsman role

- When and where:

  - Thursday, March 15, 2-4 pm, One Ashburton Place, 11th floor, Matta Conference Room, Boston

Slide 10

Workgroup #3: Assessment and Care Planning

- Areas to discuss include:

  - Required domains and/or specific tool(s) for initial assessment

  - Process for setting up and conducting assessment, including what happens before and after

  - Relationship between assessment and rating categories

  - Standards for how care teams for individual enrollees will

    - Be established

    - Meet (where, when, how)

    - Establish a care plan

    - Maintain the plan over time

  - Qualifications and expectations of Care Coordinators

- When and where:

  - Friday, March 16, 10 am -12 pm, State Transportation Building, Boston

Slide 11

Workgroup #4: Independent LTSS Coordinator

- Areas to discuss include:

  - Independent LTSS Coordinator qualifications

  - Expectations for ICO contracts with community organizations for LTSS Coordinators

  - How LTSS Coordinators will work with care teams and state agency-provided services

- When and where:

  - Friday, March 16, 2-4 pm, State Transportation Building, Boston

Slide 12

Workgroup #5: Enrollment

- Areas to discuss include:

  - Timeline

  - Ensuring clear, accessible information to members

  - Auto-enrollment

  - Partnering or modeling outreach programs to supplement MassHealth enrollment broker (e.g. SHINE)

- When and where:

  - Friday, March 23, 2-4 pm, One Ashburton Place, 21st Floor, Boston

Slide 13

Next Open Meeting

- April 9, 2012, 10:00 AM – 12:00 Noon, State Transportation Building, Conference Rooms 1, 2, & 3, Second Floor, 10 Park Plaza, Boston, MA

Slide 14

Visit us at www.mass.gov/masshealth/duals

Email us at Duals@state.ma.us