Integrating Medicare and Medicaid for 
Individuals with Dual Eligibility

Open Public Meeting Presentation

January 22, 2012

Slide 1

MassHealth Demonstration to Integrate Care for Dual Eligibles

Open Public Meeting

January 22, 2012, 10 am – 12 pm

State Transportation Building,  Boston

Slide 2

Agenda for Today

- Demonstration Timeline

- Implementation Funding

- Implementation Council

- Public Awareness Campaign

- Targeted Outreach to Members and Providers

- Learning Collaboratives

- Stakeholder Workgroups Update

  - Notices

  - Quality

  - Administrative Simplification

- Discussion: IL-LTSS Coordinator Role in Initial Assessment

Slide 3

Revised Timeline

- ICO Selection Announcement:  November 2, 2012

- Readiness Review:  Nov. 2012 – March/April 2013

- 3-Way Contracts:  March/April 2013

- Learning Collaboratives:  March 2013 – Ongoing

- Implementation Activities

  - Stakeholder Workgroups:  Dec. 2012 – Ongoing

  - Implementation Council:  Feb. 2012 – Ongoing

  - Ombudsperson:  May 2013 – Ongoing

- Public Awareness Campaign:  April 2013 - Ongoing

- Member Outreach Activities  (Members can begin to select ICOs for effective date July 1, 2013):   May 2013 – Ongoing

- Self-Selected Enrollments Begin:  July 1, 2013

- Auto-assignments Effective (Members notified at least 60 days prior to the effective date):  Oct. 1, 2013; Jan. 1, 2014

Slide 4

Implementation Funding

- “Implementation Support” for States with a design contract (15 states) and a signed MOU (up to 17 MOUs)

  - $95M budget; $1M - $15M each of up to 17 awards

- 24-month (2 year) award period

  - Year 1: 100% funding for approved implementation activities

  - Year 2: 50% funding for approved implementation activities (state match and regular administrative FFP for other 50%)

- Grant is in lieu of implementation funding negotiated through CMS design contracts and Proposals

- Deadlines:

  - 1st round: Due January 28, 2013; Notice expected March 15, 2013

  - 2nd round: Due April 1, 2013; Notice expected May 15, 2013

  - States implementing in 2013 encouraged to apply in 1st round

Slide 5

Implementation Funding (cont’d)

- Funding request based on Proposal submitted to CMS February 2012 and priorities identified with stakeholders

- Stakeholder Meetings: Accessibility support, materials, and space for open meetings, workgroups, community-based meetings, etc.

- Implementation Council: Accessibility support, transportation, and stipends for consumer representatives; materials, space, and staff support

- Ombudsperson: funding for a 3 person unit for the Demonstration

- Enrollment: Notice production and mailing costs

- Outreach and Decision Support: Community-based resource support for members to access for help in understanding their choices

- Marketing: Public awareness campaign and targeted outreach to subpopulations and providers

- Training: Learning sessions, webinars, and online courses for ICO staff, providers, and community organizations

- Quality Measurement: Survey and data tools and reporting infrastructure

- IT Systems Interface: Changes to allow MMIS to communicate with Medicare about enrollments

- Health Plan Monitoring and Oversight: Program staff and contracted project management

Slide 6

Implementation Council

- Members will be notified soon; final Council roster will be posted on duals website

- MassHealth received many nominations of highly qualified individuals – thank you to all who participated

- First Implementation Council meeting expected to be in mid-February

- As a reminder, meetings of the Implementation Council will be open to the public

Slide 7

Implementation Council (cont’d)

- Agenda for first Council meeting expected to include:

  - Introductions of Council members

  - Discussion of meeting structure and work plan

  - Discussion of the ombudsperson role

  - Other topics as determined by the Council

- In the coming months, other key topic areas MassHealth may ask the Council to provide input on include:

  - Readiness review

  - Marketing and outreach

  - Open enrollment

Slide 8

Public Awareness Campaign

- Public awareness campaign will help raise awareness of and provide general information on the Demonstration

- Massachusetts has engaged MORE Advertising

- In the next 2 weeks, MORE’s work will be gathering stakeholder input, including meeting with:

- Advocacy and community-based organizations

- State agencies

- ICOs and providers

Slide 9

Public Awareness Campaign (cont’d)

- Results of these research activities will be summarized and shared with stakeholders

- Next, MORE will convene 2 consumer focus groups, randomly selecting participants

- All stakeholder research will be used to develop materials and a dissemination strategy, e.g.:

  - Brochures, posters, postcards, etc.

  - Website

  - Social media

  - Traditional media

- Public campaign will begin in April

Slide 10

Targeted Outreach to Members and Providers

- Multi-pronged approach

  - Development of outreach materials

  - Distribution strategy (mailings, meetings, conferences)

- Outreach materials

  - Develop handbook and additional materials for enrollees, family members, and guardians

  - Handbook will include enrollee FAQs and community resource information

  - Additional materials for targeted sub-populations will be created as needed

  - Timeline: Draft materials by March 15

Slide 11

Targeted Outreach to Members and Providers (cont’d)

- Distribution strategy

  - Develop plan to reach all populations of enrollees and providers

  - Identify meetings, conferences, or locations for further discussion and distribution

- Timeline for Outreach: Beginning April 2013

- Stakeholder engagement:

  - Brainstorming on outreach strategy, content/material reviews, identification of consumer stakeholders

    - State Agency Representatives – February

    - Consumers - February

    - Implementation Council – March

    - Monthly stakeholder meeting – March

- Email duals@state.ma.us to get involved

Slide 12

Learning Collaboratives

- UMMS Commonwealth Medicine is leading development of training on certain Demonstration fundamentals for ICOs and providers

- Webinars and Online Course: March – June 2013

  - Topics expected to include: “Duals Demo 101,” disability culture and experience in the healthcare system, ADA, cultural competency, recovery model, independent living philosophy

  - Consumers will be invited to present and interact with the webinar audience

- Regional Learning Sessions - September 2013

  - Audience: ICOs and their network providers.

  - Consumers will be part of planning and will be invited to present and participate at regional learning sessions

Slide 13

Notices Workgroup Update

- Purpose of the workgroup is to provide input regarding

  - Letters that MassHealth will send to members regarding the Demonstration

  - Templates that CMS and MassHealth are creating for ICO materials

- Workgroup has had 3 meetings to date and reviewed drafts of several notices, including:

  - Letters regarding self-selection enrollment opportunity

  - Letters confirming member’s choice of an ICO

  - Letters notifying member of auto-assignment

  - Letters informing a member that they have been disenrolled from an ICO

  - ICO Summary of Benefits

  - ICO Provider Directory

  - ICO List of Covered Drugs

Slide 14

Notices Workgroup Update (cont’d)

- Workgroup comments and suggestions so far include:

  - Keep it simple; more information is not always better

  - Action items and next steps must be clear

  - Use bullets, text boxes, etc. – not long paragraphs

  - Highlight where the member can go for more information and help

  - Use the envelope (e.g. “2nd Notice,” “Action Needed”)

- Workgroup will continue to meet; upcoming meetings:

  - Today,1-3 pm, State Transportation Building

  - January 28, 10am – 12pm, 1 Ashburton, 21st floor

- Email duals@state.ma.us to be added to the distribution list

Slide 15

Quality Workgroup Update

- The workgroup met Dec. 7 – valuable discussion and input

- Group agreed on need for:

  - Input directly from enrollees using a survey tool that asks about member experience/quality of life

  - Encounter/claims based measures

- Concerns were raised about

  - Language and content in current survey tools

  - Lack of qualitative information to understand reasons for emergency room visits (i.e. PCA or DME issues)

- Follow-up workgroup meeting scheduled for Thursday

  - Materials sent on Jan. 18

Slide 16

Quality Workgroup Update

- A new survey tool

  - HCBS Experience survey

  - Tool is being tested nationally

- A quality improvement requirement to better understand reasons for emergency room visits

- Several measures of LTSS utilization based on data from claims, encounters, or ICO records

Slide 17

Administrative Simplification Workgroup

- Will convene a workgroup to address overarching administrative simplification issues specific to:

  - Primary, specialty and acute medical providers

  - Behavioral health providers

  - LTSS providers

- Targeting March for first meeting

Slide 18

Discussion: IL-LTSS Coordinators’ Role in Initial Assessment

Slide 19

Next Open Meeting

February 22, 2013
1:00 – 3:00 PM
State Transportation Building, Boston

Slide 20

Visit us at www.mass.gov/masshealth/duals

Email us at Duals@state.ma.us