Integrating Medicare and Medicaid for 
Individuals with Dual Eligibility

Open Public Meeting Presentation

July 27, 2012

Slide 1

MassHealth Demonstration to Integrate Care for Dual Eligibles

Open Public Meeting

June 1, 2012 10 am – 12 pm

State Transportation Building, Boston

Slide 2

Agenda for Today

- Status Updates

  - ICO RFR and Consumer Consultant RFR

  - Timeline

  - MOU with CMS

- Project Activities and Implementation

- Discussion

Slide 3

Supreme Court Decision on the ACA

- Landmark ruling on June 28 by the Supreme Court upholding the Patient Protection and Affordable Care Act (ACA)

- Massachusetts will continue innovating to improve health care, including through the Duals Demonstration, with our federal government partners

Slide 4

ICO RFR Update

- RFR issued June 19

- Respondents Conference held June 25

  - Robust attendance

  - Q&A spanned wide variety of topics: assessment, provider networks, data, payment, quality, grievances and appeals, enrollment, etc.

- MassHealth received many questions on the RFR, including those submitted at Respondents’ Conference

- EOHHS issued a first Q&A document and RFR Amendment #1 on July 24

Slide 5

Timeline

- Shifts in some procurement dates in amended RFR

  - Deadline for RFR Responses: Aug. 20, 2012

  - Anticipated ICO Selection Date:  Sept. 21, 2012

- Contracting and demonstration start dates unchanged:

  - Anticipated Contract Execution Date:  Dec. 15, 2012

  - Anticipated Service Start Date:  April 1, 2013

- Between selection date and contracting will be a Readiness Review period

Slide 6

Consumer Consultant RFR

- RFR issued July 5

  - To select up to six Consumers (MassHealth members or their immediate family) to form a paid advisory subcommittee

  - To review ICO RFR responses and provide input to the procurement team

  - Will be facilitated by Assistant Secretary Griffin

- Responses were due July 20

- EOHHS now reviewing responses

- Anticipated selection date: July 30

Slide 7

MOU with CMS

- MassHealth actively working with CMS on the Memorandum of Understanding (MOU)

- Discussions continue to be productive on all topics, including:

  - Terms under which the Demonstration will operate

  - Payment rates

  - Other issues

- Will be in place before ICO contracts are signed

Slide 8

Comments or Questions?

Slide 9

Project Activities and Implementation

Slide 10

Implementation Activities

- Beyond the RFR and MOU processes, there will be important topics and activities to work on

- These include:

  - Outreach and enrollment support

  - Training

  - Ombudsman

  - Implementation advisory committee

  - Quality

  - Administrative simplification

Slide 11

Outreach and Enrollment Support

- Helping members in the enrollment process

- How to engage community partners

- Possible contracted support

- Outreach to specific population groups

- Ensuring cultural and language appropriateness

- Stakeholder role in developing, reviewing and disseminating outreach materials

- Engaging providers through outreach

Slide 12

Training

- Curriculum development for Learning Collaboratives

- Consumers as presenters for certain key concepts

- Mutual exchange between ICOs, providers, consumers, state agencies, and CBOs

Slide 13

Ombudsman

- Defining the role and scope of activities

- Options for how to put this in place

Slide 14

Implementation Advisory Committee

- Including members of the disability community

- Promoting transparency in the implementation of the Demonstration

- Developing “early warning system”

- Reviewing input from community partners

- Reviewing ICO reports on grievances and appeals, early quality and member satisfaction data, etc.

- Reviewing enrollment policies, procedures, materials, and outcomes

- Making recommendations to improve services and processes

Slide 15

Quality

- Methods for collecting data

- How to use data for policy and implementation decisions

- How to disseminate information on quality

Slide 16

Administrative Simplification

- Identifying opportunities to streamline administrative processes among providers, ICOs, and MassHealth

Slide 17

Discussion

Slide 18

Next Open Meeting

August 31, 2012

10:00 AM – 12:00 PM

One Ashburton Place, 21st Floor

Slide 19

Visit us at www.mass.gov/masshealth/duals

Email us at Duals@state.ma.us