Integrating Medicare and Medicaid for 
Individuals with Dual Eligibility

Open Public Meeting Presentation

November 2, 2012

Slide 1

MassHealth Demonstration to Integrate Care for Dual Eligibles

Open Public Meeting

November 2, 2012, 2 pm – 4 pm

State Transportation Building,  Boston

Slide 2

Agenda for Today

- Updated Demonstration Timeline

- Implementation Activities

  - Implementation Council

  - Ombudsperson

  - Workgroup Meetings

- Demonstration Options Counseling

Slide 3

Expected Timeline

- ICO Selection Announcement: November 2, 2012

- Readiness Review: Nov. 2012 – Feb. 2012

- 3-way Contracts:  February 2013

- Implementation Activities

  - Stakeholder Workgroups: Quality, Notices, Assessment, Admin. Simplification: Dec. 2012 – Ongoing

  - Implementation Council: Dec. 2012 – Ongoing

  - Ombudsperson: Feb. 2013 - Ongoing

- Member Outreach: Feb. 2013 - Ongoing

- Self-Selected Enrollment: April 1, 2013

- Auto-assignment Enrollment: July 1, 2013; Oct. 1, 2013

Slide 4

Implementation Council

Slide 5

DRAFT Goals of the Implementation Council

- Promote transparency

- Monitor access and ADA compliance

- Track quality of services

- Provide implementation support and input

Slide 6

DRAFT Council Roles and Responsibilities

- Expected roles and responsibilities include:

  - Developing annual work plan

  - Advising EOHHS staff

  - Soliciting input from stakeholders

  - Providing input into the readiness process

  - Examining quality data, including survey and other metrics

  - Reviewing aggregate grievances and appeals data and ombudsperson reports to identify needed course corrections

  - Examining access to services (medical, behavioral health, and LTSS)

  - Assessing use of peers, community health workers, IL-LTSS Coordinators

  - Participating in development of public education and outreach campaigns

  - Developing annual report

Slide 7

DRAFT Size and Meeting Logistics

- Council size: 15 – 21 individuals

- Statewide, with geographic representation of at least one member from:

  - Southeast/Cape/Islands

  - Metro Boston/Northeast

  - Central

  - West

- Include members living in both rural and urban areas

- Meet monthly or bi-monthly as determined by the Council; at least 4 total meetings in the first year

- Serve for duration of the three-year Demonstration

- Council will determine methods of participation (in person, by phone, email)

- Open meetings with time for public comments

Slide 8

DRAFT Membership Requirements

- Seek membership that:

  - Reflects the geographic and demographic diversity of the population, including racial and cultural minorities (including Deaf and GLBT communities), disability, service needs, ages; and

  - Meets county-based and urban/rural regional diversity requirements

- Expected membership to include

  - MassHealth disabled or dual eligible members, including those eligible for the Demonstration

  - Family members/guardians

  - Advocates and peers from community- and disability-based organizations

  - Providers

  - Provider or trade organizations/associations

  - Union representatives

- Individuals may fulfill more than one requirement

Slide 9

DRAFT Membership Requirements

- At least 51% of Council will be:

  - MassHealth disabled or dual eligible members, including those eligible for the Demonstration, and/or

  - Family members or guardians

- Include representation from Demonstration target populations:

  - Adults with physical disabilities

  - Adults with intellectual/developmental disabilities

  - Adults with serious mental illness

  - Adults with substance abuse disorders

  - Adults with disabilities with multiple chronic illnesses or functional and cognitive limitations

  - Adults with disabilities who are homeless

- Representatives from community-based organizations serving Demonstration population (approx. 6 reps)

- Provider or trade assoc. representatives for Demonstration service types: medical, behavioral health, and LTSS (approx. 3 reps)

- One union representative

Slide 10

DRAFT Council Nomination Process

- Broad outreach through such channels as:

  - Demonstration stakeholder and state agency distribution lists and newsletters

  - Demonstration and other www.mass.gov websites

  - Comm-PASS

- Applicants submit nomination form with requested information, such as:

  - Interest in participating

  - Relevant knowledge, skill sets, and experience

  - Relationship to selection criterion

  - Letter of support

- Consumer chair will be identified

Slide 11

DRAFT Supports for Council Members

- Training: Optional orientation opportunities to learn about MassHealth, Medicare, and the Demonstration

- Expected stipends and reimbursement:

  - For consumers and consumer family members/guardians not paid by another organization to participate

  - $50 per meeting; $25 for pre-meeting preparation work

  - Reimbursement for travel

- Accommodations will be member-specific, e.g.:

  - ASL interpreter or Communication Access Realtime Translation (CART) reporter

  - Language interpreter

  - Electronic, large print or Braille versions of documents

  - Flexible meeting schedules

  - Peer supports

  - One-to-one assistance

  - Frequent breaks

Slide 12

DRAFT Staff Supports

- EOHHS will support Council with staff time for:

  - Meeting planning, accommodations and logistics

  - Meeting material and other report development

  - Communication with Council members

  - Support to consumer chair, as requested

- EOHHS representatives will:

  - Attend all meetings to ensure two-way communication

  - Provide regular updates

Slide 13

DRAFT Reporting and Transparency

- Duals Demonstration Implementation Council will complete:

  - Annual work plan

  - Annual report

- Documents posted on website

- Meetings open to the public

Slide 14

Discussion

Slide 15

Ombudsperson

Slide 16

Current State Models

- MassHealth has conducted interviews with current Commonwealth ombudsman:

  - Executive Office of Elder Affairs

    - State Long-Term Care Ombudsman Program (SLTCO)

    - The Community Care Ombudsman (CCO) Program

  - MassHealth Disability Ombudsman

  - Massachusetts Rehabilitation Commission Ombudsman

  - Department of Mental Health Human Rights Office

  - Department of Developmental Services Office of Human Rights

Slide 17

Lessons Learned

- Some ombudsperson programs are very targeted, with focus on:

  - Certain issues only (e.g. eligibility questions)

  - Clients within particular settings (e.g. nursing facilities)

- Many ombudsperson programs engage in both individual and system-wide advocacy

  - Address unique client needs

  - Also work to address larger, systemic issues

- Current state ombudsperson programs funded through general funds, and located within state agencies

  - Independence maintained through clear definition of their advocacy role, and direct reporting to key leadership

Slide 18

Lessons Learned (cont’d)

- Many ombudspersons also have relationships other state agencies, and with local and state-wide advocacy organizations

- Nearly all have a formal reporting structure and report annually to leadership on trends

- Most ombudspersons have strong experience and skills in such areas as:

  - Mediation

  - Case management

  - Program development

  - Social work

Slide 19

DRAFT Duals Ombudsperson

- Roles and Responsibilities

Duals ombudsperson should balance two roles:

  - Individual advocacy

    - Receive, report, and resolve consumer complaints and/or concerns

    - Proactively work with ICOs and CBOs to address individual issues;

and

  - Systemic advocacy

    - Monitor trends, meet with stakeholders, comment on policies and regulations

    - Work with MassHealth, the Implementation Council, and other stakeholders to address systemic issues

Slide 20

DRAFT Duals Ombudsperson (cont’d)

- Data

  - Will need access to MassHealth and other state data systems to effectively address consumer needs

- Staffing

  - One designated staff member, with potential growth as needed

  - Seeking funding from CMS for this position

- Training

  - Skills in mediation, conflict resolution, advocacy and case management are needed

  - Possible on the job training from other ombudsperson programs in the state; additional skills workshops available through local colleges

Slide 21

DRAFT Duals Ombudsperson (cont’d)

- Reporting

  - Track all complaints and issues

  - Report directly to senior leadership with issues that need immediate attention.

  - Produce an annual report which will highlight complaint trends and systemic issues

  - Work with the Implementation Council around policy recommendations and system-wide issues

Slide 22

Discussion

Slide 23

Workgroup Meetings

- Quality Metrics:

  - December 7, 2012, 1:00 – 2:30 pm

1 Ashburton Place, 21st Floor

- Please look for other workgroup meetings to be scheduled

  - Will be posted on duals website (www.mass.gov/masshealth/duals)

  - Emails will be sent to stakeholder distribution list

- All meetings will be open to the public

Slide 24

Demonstration Options Counseling

Slide 25

Grant Overview

- Grant from CMS and the Administration for Community Living for Educational Counseling Program for People Eligible for Medicare-Medicaid Financial Alignment Model

- Financing to State Health Insurance Programs, (SHINE in Mass) and/or ADRCs to:

  - Provide options counseling to dual eligible individuals

  - Ensure access to unbiased and consumer-friendly information and counseling (distinct from the financial Alignment Models’ Demonstration Plan Enrollment Brokers)

- Three year grant; up to $1 M over three-year period

- Application submitted November 2

Slide 26

Stakeholder Input

- EOHHS convened stakeholder workgroup to:

  - Collaborate on development of the grant  proposal,

and

  - Once funded, engage in planning and development of training curricula, strategies for recruiting counselors and protocols for supervising counselors

Slide 27

Implementation Strategies

- Propose to create a new division of SHINE, using SHINE regional offices as administrative infrastructure/base

- SHINE will recruit new staff and counselors, including hiring a coordinator, to oversee this educational effort

- Focus on disability, peer run, behavioral health entities etc. to recruit paid staff and volunteer counselors

- Staff and volunteers to be located at disability/advocacy agency sites in addition to existing SHINE sites

- Training curricula will be developed; training available to all who are interested in serving as counselors across all populations and organizations

- Extensive data maintenance and reporting requirements captured through existing SHINE data system

Slide 28

Questions?

Slide 29

Next Open Meeting

December 7, 2012

10:00 AM – 12:00 PM

1 Ashburton Place, 21st Floor, Boston

Slide 30

Visit us at www.mass.gov/masshealth/duals

Email us at Duals@state.ma.us