## MassLEAP Workplan
Massachusetts Learning Education and Assets Program (MassLEAP)
Workplan | Responsible | Status | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4 | [11 empty] | Year 5
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
I. Outreach and Engagement
Create materials | Program Manager, Justine Francis | e.g. Complete | bar: Year 1 1 to Year 1 4
Baseline Surveys | LHA staff , Nancy Stowe | bar: Year 1 1 to Year 1 2
Distribute information | LHA staff, name | Complete | bar: Year 1 3 to Year 1 5
Orientation meetings | LHA staff | In progress | bar: Year 1 4 to Year 1 6
Site team meetings | site team | Not started | bar: Year 1 1 to Year 1 3; Year 1 5; Year 1 7; Year 1 9
Engage resident participation | Resident Board | Overdue | bar: Year 1 1
II. Program Design
Develop Admin Plan (based on DHCD guidelines) |  | Not started
Create Staffing and Organizational structure |  | Not started
Meeting Schedule |  | Not started
Data entry
Goals and Benchmark Reporting |  | Not started
Grievance and Appeals
DHCD Reporting and Assessment |  | Not started
Resident Involvement |  | Not started
III. Tenant Selection
Develop Selection Plan | e.g. Team
Develop Waitlist Protocol
Review Applicants /Eligibility determination
Tenant Contact/letters
Record baseline information on participants & WL
IV. Enrollment
Launch Session for partnership
Participant orientation
Participant/program paperwork (release, agreement, etc)
Create Individual Participant Plan
IT/ tracking in place /data entry
V. Program Management
Staffing - assign or hire | E.g. Program Manager
Review and Exceute contracts
Budget and Financial Reports
Partnership Meetings
Data Collection
Grievances and Appeals
Escrow management
Program Updates and Reports
Ensure Lease compliance
VI. Data and reporting
Quality Control
Data analysis & sharing (within program and partnership)
Reports (to DHCD)
Program Outreach and Practice results
Marketing
Selected sites teams will change these codes to indicate quarterly progress in DHCD reports) : Not started/In progress/Complete /Overdue. You do not need to fill out this section.
To complete workplan applicants should fill in position (& name of staff) who will be responsible for all activities in I -VI
(see example in I)
To Complete workplan:
Fill In anticpated time required for each activity in all revelant years for I- V. Note: some activites may finish and then repeat in subsequent years.
(See example in Category I)