## Introduction
Chapter 90 Planning Toolkit
Instructions for Use
The Chapter 90 Planning Toolkit is an Excel spreadsheet that includes a collection of tabs that can be used to help plan projects funded through the Chapter 90 Program. More detailed guidance and information can be found on the Chapter 90 webpage: www.mass.gov/chapter-90-program.
Document Contents & Description
Chapter 90 Planning Checklist | A basic list of steps that can be taken on an annual basis to prepare for Chapter 90 funding decisions.
Asset Condition List | A template that can be used to list all assets that may require maintenance as well as track year installed/built, most recent inspection date, and conditions.
Bridge Inventory List | A template that can be used to list all bridges and summarize key data from Inspection Reports to identify urgent needs.
Infrastructure Budget | A basic budget template to compile anticipated revenue from various funding sources, as well as anticipated uses of funds, for a given fiscal year.
Project Planning | A long-term planning tool that lists all potential projects and forecasts their costs into the future, projecting Chapter 90 allocations/carry-overs.
Unweighted Prioritization Matrix | A tool to prioritize or rank potential projects using criteria set by the user, where projects are scored evenly based on all the criteria.
Weighted Prioritization Matrix | A tool to prioritize or rank potential projects, allowing the user to input percent-weights to each category and rank accordingly.
How to Use this Document
The intent of the Chapter 90 Planning Toolkit is to provide municipalities with a basic resource for planning. The Planning Toolkit may be used as a guide for planning as deemed appropriate by the municipality. It should be noted that altering the Excel document from its template form may undermine any preset formulas and conditions of the cells, thereby potentially resulting in mathematical errors. Municipalities should verify that all work is accurate. The Planning Toolkit does not replace any required local, state, or federal planning methods or approvals. This tool requires a fundamental understanding of Excel.
More detailed instructions for each tab can be found as you move through the workbook. Clicking into cells will often provide pop-up information about how to use the tool. Where there is light blue shading and/or red text, input is generally required from the user, as shown below.
MassDOT does not warrant this product in any way and is not responsible for any damages due to errors or mistakes which may exist. The user understands that the use of this product is at their own risk and shall indemnify MassDOT, its employees, consultants, and contractors from any damages, consequential or otherwise, which may result from its use.

## Chapter 90 Planning Checklist
Annual Checklist Prior to Selecting Chapter 90 Projects
x | Update inventory of pavement condition on roadways to see if any are a priority for repair - consult pavement management plan
Update inventory of roadway bridges based on latest inspection reports by MassDOT
Inspect and update inventory of culverts and locally-owned pedestrian bridges
x | Check with Police Department for reports of congestion or crashes that may require addressing
x | Meet with Local Utilities to determine major infrastructure needs
x | Check with Town Planner about economic developments or initiatives
x | Check Municipal Vulnerability and Preparedness Plan (MVP) for FEMA Vulnerability Improvements
x | Check Complete Streets Prioritization Plan to see if any upcoming projects require design or supplemental construction funding
Check Master Plans and Capital Improvement Plans for potential projects
Host a public meeting to hear community needs

## Asset Condition List
ASSET CONDITION INVENTORY LIST | [7 empty] | Consider using the Bridge Invetory List for any bridges.
Asset | Category | Location | Date Built/Installed | Date Inspected | Recent Condition | $ Value | TRUE | Categories: | Roadway | Structures | Utilities | Other
Bridge No. A-01-234 | Structures | Main Street | 1980-02-11 | 2020-01-02 | Good | 900000 | TRUE
Bridge No. A-09-876 | Structures | High Street | 1963-05-10 | 2021-04-02 | Fair | 2000000 | TRUE
Bridge No. A-05-555 | Structures | River Road | 1958-11-07 | 2020-08-06 | Fair | 1300000 | FALSE
Guardrail | Structures | Main Street | 1980-03-01 | 2020-01-02 | Good | 500000 | FALSE
Guardrail | Structures | High Street | 1963-06-08 | 2021-04-02 | Good | 300000 | FALSE
Guardrail | Structures | River Road | 1958-11-20 | 2020-08-06 | Fair | 400000 | FALSE
Guardrail | Structures | Route 123 | 1978-10-02 | 2021-03-23 | Excellent | 1000000 | FALSE
Guardrail | Structures | Valerie Road | 1993-03-03 | 2020-07-25 | Good | 800000 | FALSE
Sidewalk | Roadway | Main Street | 1980-02-20 | 2020-01-02 | Good | 600000 | FALSE
Sidewalk | Roadway | Pleasant Avenue | 1950-01-01 | 2020-11-11 | Poor | 300000 | FALSE
Sidewalk | Roadway | Route 123 | 1978-09-23 | 2021-03-23 | Good | 900000 | FALSE
Pavement | Roadway | Bacon Street | 1993-05-01 | 2020-07-25 | Fair | 1200000 | FALSE
Pavement | Roadway | Main Street | 1980-02-23 | 2020-01-02 | Poor | 2000000 | FALSE
Street Lighting | Utilities | Bacon Street | 1992-02-18 | 2019-08-16 | Poor | 300000 | FALSE
8" Water Main | Utilities | Main Street | 1980-02-27 | 2020-01-02 | Poor | 600000 | FALSE
Drainage - Culvert | Other | Route 123 | 1978-08-10 | 2021-03-23 | Good | 150000 | FALSE
Drainage - Catch Basins | Other | Valerie Road | 1993-03-03 | 2020-07-25 | Fair | 300000 | FALSE
Drainage - Catch Basins | Other | Main Street | 1980-03-03 | 2020-01-02 | Excellent | 340000 | FALSE
FALSE
FALSE
FALSE
FALSE

## Bridge Inventory List
| Bridge Inventory List |  |  |  | Municipality: | Abington
[5 empty] | Last Updated: | 2021-07-21 |  |  | Link to FHWA Bridge Coding Guide: | https://www.fhwa.dot.gov/bridge/mtguide.pdf
| Bridge No. | BIN | Owner (22) | Maintenance Responsibility (21) | Bridge Type | Facility Carried (Street Name) (07) | Feature Intersected (Under) (06) | Facility Under | No. of Spans (45) | Structure Length (49) (ft) | Deck Width (52) | Structure Type - Material (43) | Structure Type - Design (43) | Functional Classification (26) | Structure Status (41) | Year Built (27) | Year Rebuilt (106) | Last Inspection Report Date | Deck (58) | SuperS. (59) | SubS. (60) | Comments and Concerns | Repair Priority | Estimated Costs
1 | A-01-234 | 6H6 | MUN (City/Town) | 1 State Highway Agency | Roadway |  | WATER | SHUMATUSCACANT RIV | 1 | 28.871 | 48.2278 | 5 Prestressed concrete * | 01 Slab | 19 Urban Local | A Open, no restriction | 1956 | - | 2019-09-18 | 6 Satisfactory | 6 Satisfactory | 7 Good | Bridge is in satisfactory condition | 3 | -
2 | A-09-876 | 4BY | RRY (Railroad Company) | 27 Railroad | Railroad |  | WATER | ISLAND GROVE POND | 1 | 317 | 32 | 8 Masonry | 7 Wood or Timber | 16 Urban Minor Arterial | P Posted for load (may include other restrictions such as temporary bridges which are load posted) | 1958 | - | 2020-08-06 | 5 Fair | 5 Fair | 3 Serious | Bridge is in fair to serious condition | 2 | 3000000
EX. | A-01-004 | 41D | MUN (City/Town) | 3 Town or Township Highway Agency | Roadway | HWY ADAMS ST | WATER | SHUMATUSCACANT RIV | 1 | 28.871 | 48.2278 | 5 Prestressed concrete * | 01 Slab | 19 Urban Local | A Open, no restriction | 1956 | - | 2019-09-18 | 6 Satisfactory | 6 Satisfactory | 7 Good | Bridge is in satisfactory condition | 3 | -

## Infrastructure Budget
Municipal Infrastructure Budget |  |  | Current Year: | 2021
| Current Fiscal Year: | 2021
Revenue - Sources of Funds | FY 2021 Budget | FY 2021 Spent | FY 2022 Proposed Budget | Change from Previous Budget
Chapter 90 | 387759 | 256243 | 450000 | 62241
Chapter 90 Carryover | 0 | 0 | 0 | 0
Municipal Budget Allocation | 750000 | 800000 | 810000 | 60000
MVP Grant Program | 35000 | 35000 | 95000 | 60000
Small Bridge | 65000 | 58000 | 0 | -65000
DER Grant | 0 | 0 | 600000 | 600000
Community Transit Grant Program | 18000 | 15200 | 21000 | 3000
Workforce Transportation Program | 45000 | 0 | 30000 | -15000
MassWorks | 1100000 | 998000 | 0 | -1100000
Complete Streets | 350000 | 350000 | 0 | -350000
Safe Routes to Schools | 0 | 0 | 250000 | 250000
Shared Streets | 0 | 0 | 0 | 0
Total Revenue | 2750759 | 2512443 | 2256000 | -
Expenditures - Uses of Funds | FY 2021 Budget | FY 2021 Spent | FY 2022 Proposed Budget | Change from Previous Budget
Salaries & Wages | 750000 | 670950 | 970000 | 220000
Consulting Services | 70000 | 64897 | 60900 | -9100
Equipment | 45000 | 30000 | 40000 | -5000
Materials & Supplies | 90000 | 97500 | 100000 | 10000
Expenditure Recovery | 15000 | 21800 | 23000 | 8000
Budgetary Reserves | 100000 | 0 | 80000 | -20000
Facilities Maintenance | 100000 | 98000 | 120000 | 20000
Capital Renewal | 45000 | 34000 | 50000 | 5000
Capital Projects | 895000 | 700000 | 515000 | -380000
Total Expenditures | 2110000 | 1717147 | 1958900 | -
NET CASHFLOW | 640759 | 795296 | 297100 | -

## Project Planning
[6 empty] | Municipality: | ABINGTON | Ch. 90 Apportionment*: |  | 387759
Municipal Project Planning - Total Project Costs by Year | [5 empty] | Annual Budget Planning
Project | Year | Engineering Cost | Construction Cost | Other (Financing, Police Details, etc) | Total | Year | Ch. 90 Balance after Apportionment | Total Project Costs | Ch. 90 Balance After Costs | Other Funding Required | Carryover?
Main Street Sidewalk Construction | 2021 | 10000 | 750000 |  | 760000 | 2021 | 387759 | 895000 | 0 | 507241 | No
Main Street Sidewalk Construction | 2022 |  | 500000 | 15000 | 515000 | 2022 | 387759 | 515000 | 0 | 127241 | No
North Main Street Rail Trail | 2021 | 5000 | 20000 | 15000 | 40000 | 2023 | 387759 | 741500 | 0 | 353741 | No
Pleasant Avenue ADA Upgrades | 2021 | 20000 | 75000 |  | 95000 | 2024 | 387759 | 1420000 | 0 | 1032241 | No
South Main Street Rail Trail | 2023 | 15000 | 50000 | 1500 | 66500 | 2025 | 387759 | 235000 | 152759 | 0 | Yes
Route 234 at Pleasant Avenue Intersection Reconstruction | 2023 | 175000 | 500000 |  | 675000 | 2026 | 540518 | 3050000 | 0 | 2509482 | No
Route 123 Culvert Repairs | 2024 | 150000 | 400000 | 20000 | 570000 | 2027 | 387759 | 3150000 | 0 | 2762241 | No
Main Street at Bank Street Intersection Reconstruction | 2024 | 150000 | 700000 |  | 850000 | 2028 | 387759 | 1550000 | 0 | 1162241 | No
School Street Sidewalk Construction | 2025 | 35000 | 200000 |  | 235000
High Street Bridge Replacement | 2026 | 350000 | 2700000 |  | 3050000
Route 123 at Bank Street Intersection Reconstruction | 2027 | 100000 | 850000 | 50000 | 1000000
River Road Bridge Replacement | 2027 | 350000 | 1800000 |  | 2150000
Main Street Bridge Replacement | 2028 | 350000 | 1200000 |  | 1550000
* Apportionment is based on the current Fiscal Year. Please select your municipality from the drop-down and then check the Chapter 90 website to confirm that the spreadsheet is accurate.

## Unweighted Prioritization
PRIORITIZATION MATRIX | Safety | Cost Effectiveness | Project Readiness | Public Support | Scoring Criteria | Scoring Criteria | Scoring Criteria | TOTAL SCORE | RANKING
PROJECT | /10 | /10 | /10 | /10 | /10 | /10 | /10 | - | #
Main Street Sidewalk Construction | 3 | 5 | 6 | 7 | 0 | 0 | 0 | 21 | 4
North Main Street Rail Trail | 4 | 3 | 3 | 7 | 0 | 0 | 0 | 17 | 9
Pleasant Avenue ADA Upgrades | 2 | 2 | 1 | 6 | 0 | 0 | 0 | 11 | 10
South Main Street Rail Trail | 5 | 1 | 5 | 9 | 0 | 0 | 0 | 20 | 5
Route 234 at Pleasant Avenue Intersection Reconstruction | 10 | 2 | 10 | 6 | 0 | 0 | 0 | 28 | 1
Route 123 Culvert Repairs | 1 | 1 | 3 | 2 | 0 | 0 | 0 | 7 | 12
Main Street at Bank Street Intersection Reconstruction | 1 | 2 | 3 | 4 | 0 | 0 | 0 | 10 | 11
School Street Sidewalk Construction | 7 | 2 | 3 | 7 | 0 | 0 | 0 | 19 | 6
High Street Bridge Replacement | 2 | 4 | 3 | 10 | 0 | 0 | 0 | 19 | 6
Route 123 at Bank Street Intersection Reconstruction | 8 | 1 | 9 | 5 | 0 | 0 | 0 | 23 | 3
River Road Bridge Replacement | 7 | 2 | 5 | 10 | 0 | 0 | 0 | 24 | 2
Main Street Bridge Replacement | 6 | 3 | 8 | 1 | 0 | 0 | 0 | 18 | 8

## Weighted Prioritization
PRIORITIZATION MATRIX |  | Safety | Cost Effectiveness | Project Readiness | Public Support | TOTAL SCORE | RANKING | Total Wt.
PROJECT | Scoring | 45% | 30% | 15% | 10% | /10 | # | 100%
Main Street Sidewalk Construction | Rating/10 | 3 | 7 | 4 | 8 | 4.85 | 5
| Score | 1.35 | 2.1 | 0.6 | 0.8
Pleasant Avenue ADA Upgrades | Rating/10 | 8 | 4 | 1 | 3 | 5.25 | 3
| Score | 3.6 | 1.2 | 0.15 | 0.3
Route 234 at Pleasant Avenue Intersection Reconstruction | Rating/10 | 7 | 6 | 8 | 2 | 6.35 | 2
| Score | 3.15 | 1.8 | 1.2 | 0.2
Main Street at Bank Street Intersection Reconstruction | Rating/10 | 10 | 7 | 6 | 8 | 8.3 | 1
| Score | 4.5 | 2.1 | 0.9 | 0.8
High Street Bridge Replacement | Rating/10 | 1 | 9 | 10 | 2 | 4.85 | 4
| Score | 0.45 | 2.7 | 1.5 | 0.2
River Road Bridge Replacement | Rating/10 | 1 | 9 | 6 | 2 | 4.25 | 6
| Score | 0.45 | 2.7 | 0.9 | 0.2

## HIDDEN (hidden)
City/Town | Highway District | Miles 2019 | Population 2010 | Employment 2019 | Amount | Bridge Inventory Pull-Downs
ABINGTON | 5 | 60.31 | 15985 | 4311 | 387759 | Owner | Bridge Type | Maint. Resp. (21) | Structure Type (43) | Structure Type (43) | Functional Classification (26) | Structure Status (41) | Ratings
ACTON | 3 | 112.6 | 21924 | 10516 | 702427 | DOT | Roadway | 1 State Highway Agency | 1 Concrete | 01 Slab | 01 Rural Principal Arterial - Interstate | A Open, no restriction | N Not Applicable | NONE
ACUSHNET | 5 | 59.47 | 10303 | 1623 | 316826 | MUN (City/Town) | Pedestrian | 2 County Highway Agency | 2 Concrete continuous | 02 Stringer/Multi-beam or Girder | 02 Rural Principal Arterial - Other | B Open, posting recommended but not legally implemented (all signs not in place or not correctly implemented) | 9 Excellent
ADAMS | 1 | 54.11 | 8485 | 1812 | 286536 | MBT (MBTA) | Railroad | 3 Town or Township Highway Agency | 3 Steel | 03 Girder and Floorbeam System | 06 Rural Minor Arterial | D Open, would be posted or closed except for temporary shoring, etc. to allow for unrestricted traffic | 8 Very Good
AGAWAM | 2 | 128.33 | 28438 | 11887 | 821382 | MDC (DCR) | Utility | 4 City or Municipal Highway Agency | 4 Steel continuous | 04 Tee Beam | 07 Rural Major Collector | E Open, temporary structure in place to carry legal loads while original structure is closed and awaiting replacement or rehabilitation | 7 Good | LOW
ALFORD | 1 | 17.38 | 494 | 29 | 71346 | MPA (MassPORT) |  | 11 State Park, Forest, or Reservation Agency | 5 Prestressed concrete * | 05 Box Beam or Girders - Multiple | 08 Rural Minor Collector | G New structure not yet open to traffic | 6 Satisfactory
AMESBURY | 4 | 60.01 | 16283 | 4852 | 394836 | WRA (Water Resources Authority) |  | 12 Local Park, Forest, or Reservation Agency | 6 Prestressed concrete continuous * | 06 Box Beam or Girders - Single or Spread | 09 Rural Local | K Bridge closed to all traffic | 5 Fair | MEDIUM
AMHERST | 2 | 100 | 37819 | 17684 | 838313 | STA (Other State) |  | 21 Other State Agencies | 7 Wood or Timber | 07 Frame (except frame culverts) | 11 Urban Principal Arterial - Interstate | P Posted for load (may include other restrictions such as temporary bridges which are load posted) | 4 Poor | HIGH
ANDOVER | 4 | 189.78 | 33201 | 35796 | 1371690 | PRI (Private) |  | 25 Other Local Agencies | 8 Masonry | 08 Orthotropic | 12 Urban Principal Arterial - Other | R Posted for other load-capacity restriction | 3 Serious
AQUINNAH | 5 | 8.27 | 311 | 93 | 35354 | RRY (Railroad Company) |  | 26 Private (other than railroad) | 9 Aluminum, Wrought Iron, or Cast Iron | 09 Truss - Deck | 14 Urban Other Principal Arterial |  | 2 Critical | VERY HIGH
ARLINGTON | 4 | 102.96 | 42844 | 9639 | 787671 | DEM (Dept. of Environmental Management) |  | 27 Railroad | 0 Other | 10 Truss - Thru | 16 Urban Minor Arterial |  | 1 Imminent Failure
ASHBURNHAM | 3 | 74.22 | 6081 | 1052 | 340885 |  |  | 31 State Toll Authority |  | 11 Arch - Deck | 17 Urban Collector |  | 0 Failed
ASHBY | 3 | 51.43 | 3074 | 427 | 225418 |  |  | 32 Local Toll Authority |  | 12 Arch - Thru | 19 Urban Local
ASHFIELD | 1 | 71.6 | 1737 | 248 | 293623 |  |  | 60 Other Federal Agencies (not listed below) |  | 13 Suspension
ASHLAND | 3 | 77.83 | 16593 | 4942 | 467464 |  |  | 61 Indian Tribal Government |  | 14 Stayed Girder
ATHOL | 2 | 99.35 | 11584 | 4005 | 508650 |  |  | 62 Bureau of Indian Affairs |  | 15 Movable - Lift
ATTLEBORO | 5 | 184.79 | 43593 | 17891 | 1208641 |  |  | 63 Bureau of Fish and Wildlife |  | 16 Movable - Bascule
AUBURN | 3 | 97.05 | 16188 | 11073 | 611723 |  |  | 64 U.S. Forest Service |  | 17 Movable - Swing
AVON | 5 | 23.86 | 4356 | 5470 | 184974 |  |  | 66 National Park Service |  | 18 Tunnel
AYER | 3 | 37.88 | 7427 | 4902 | 252599 |  |  | 67 Tennessee Valley Authority |  | 19 Culvert (includes frame culverts)
BARNSTABLE | 5 | 353.12 | 45193 | 28363 | 1998124 |  |  | 68 Bureau of Land Management |  | 20 * Mixed types
BARRE | 2 | 97.77 | 5398 | 1316 | 431604 |  |  | 69 Bureau of Reclamation |  | 21 Segmental Box Girder
BECKET | 1 | 56.44 | 1779 | 424 | 236736 |  |  | 70 Corps of Engineers (Civil) |  | 22 Channel Beam
BEDFORD | 4 | 71.96 | 13320 | 23784 | 644364 |  |  | 71 Corps of Engineers (Military) |  | 00 Other
BELCHERTOWN | 2 | 127.4 | 14649 | 2856 | 624267 |  |  | 72 Air Force
BELLINGHAM | 3 | 92.46 | 16332 | 6326 | 539144 |  |  | 73 Navy/Marines
BELMONT | 4 | 74.76 | 24729 | 7877 | 541617 |  |  | 74 Army
BERKLEY | 5 | 54.2 | 6411 | 780 | 261626 |  |  | 75 NASA
BERLIN | 3 | 42.31 | 2866 | 639 | 190975 |  |  | 76 Metropolitan Washington Airports Service
BERNARDSTON | 2 | 41.73 | 2129 | 513 | 182537 |  |  | 80 Unknown
BEVERLY | 4 | 129.9 | 39502 | 24051 | 1040368
BILLERICA | 4 | 194.66 | 40243 | 25604 | 1315776
BLACKSTONE | 3 | 41.08 | 9026 | 1353 | 233746
BLANDFORD | 1 | 63.34 | 1233 | 209 | 257687
BOLTON | 3 | 61.5 | 4897 | 1685 | 291114
BOSTON | 6 | 790.2 | 617594 | 661123 | 14758670
BOURNE | 5 | 97.91 | 19754 | 8317 | 605495
BOXBOROUGH | 3 | 33.86 | 4996 | 3424 | 204144
BOXFORD | 4 | 89.66 | 7965 | 1123 | 414014
BOYLSTON | 3 | 40.06 | 4355 | 1443 | 201090
BRAINTREE | 6 | 104.55 | 35744 | 29876 | 985687
BREWSTER | 5 | 56.05 | 9820 | 2773 | 313890
BRIDGEWATER | 5 | 113.53 | 26563 | 9012 | 717981
BRIMFIELD | 2 | 64.01 | 3609 | 613 | 280152
BROCKTON | 5 | 245.4 | 93810 | 40015 | 2024036
BROOKFIELD | 3 | 36.28 | 3390 | 396 | 167899
BROOKLINE | 6 | 93 | 58732 | 16617 | 931572
BUCKLAND | 1 | 42.49 | 1902 | 572 | 184772
BURLINGTON | 4 | 102.13 | 24498 | 45234 | 1084501
CAMBRIDGE | 6 | 120.66 | 105162 | 133711 | 2706332
CANTON | 6 | 94.47 | 21561 | 22271 | 766981
CARLISLE | 4 | 54.34 | 4852 | 786 | 252301
CARVER | 5 | 79.92 | 11509 | 2483 | 414473
CHARLEMONT | 1 | 42.45 | 1266 | 473 | 179392
CHARLTON | 3 | 126.74 | 12981 | 3970 | 624115
CHATHAM | 5 | 66.49 | 6125 | 3692 | 341914
CHELMSFORD | 4 | 172.01 | 33802 | 22570 | 1151243
CHELSEA | 6 | 44.96 | 35177 | 16162 | 588706
CHESHIRE | 1 | 44.03 | 3235 | 630 | 199916
CHESTER | 1 | 57.64 | 1337 | 109 | 234905
CHESTERFIELD | 1 | 53.11 | 1222 | 154 | 217018
CHICOPEE | 2 | 191.37 | 55298 | 20375 | 1337948
CHILMARK | 5 | 14.11 | 866 | 316 | 64333
CLARKSBURG | 1 | 15.85 | 1702 | 145 | 74430
CLINTON | 3 | 47.82 | 13606 | 4415 | 325072
COHASSET | 5 | 33.58 | 7542 | 2987 | 214119
COLRAIN | 1 | 78.06 | 1671 | 228 | 318185
CONCORD | 4 | 105.47 | 17668 | 13108 | 677874
CONWAY | 1 | 63.88 | 1897 | 218 | 264126
CUMMINGTON | 1 | 48.48 | 872 | 384 | 199410
DALTON | 1 | 40.36 | 6756 | 1856 | 222376
DANVERS | 4 | 106.14 | 26493 | 26605 | 894704
DARTMOUTH | 5 | 195.84 | 34032 | 17951 | 1191659
DEDHAM | 6 | 84.41 | 24729 | 17646 | 693692
DEERFIELD | 2 | 77.33 | 5125 | 4579 | 388265
DENNIS | 5 | 145.57 | 14207 | 5192 | 719759
DIGHTON | 5 | 60.31 | 7086 | 1860 | 302441
DOUGLAS | 3 | 76.33 | 8471 | 1015 | 363912
DOVER | 6 | 59.32 | 5589 | 970 | 278610
DRACUT | 4 | 136.31 | 29457 | 5982 | 789871
DUDLEY | 3 | 82.29 | 11390 | 3126 | 430484
DUNSTABLE | 3 | 41.68 | 3179 | 350 | 187116
DUXBURY | 5 | 103.59 | 15059 | 3165 | 537472
EAST BRIDGEWATER | 5 | 64.38 | 13794 | 2857 | 372674
EAST BROOKFIELD | 3 | 19.17 | 2183 | 498 | 94583
EAST LONGMEADOW | 2 | 98.33 | 15720 | 8320 | 581503
EASTHAM | 5 | 50.57 | 4956 | 1268 | 243895
EASTHAMPTON | 2 | 82.7 | 16053 | 4845 | 481890
EASTON | 5 | 116.94 | 23112 | 10796 | 730231
EDGARTOWN | 5 | 45.42 | 4067 | 2947 | 237803
EGREMONT | 1 | 35.91 | 1225 | 193 | 150320
ERVING | 2 | 17.51 | 1800 | 473 | 85377
ESSEX | 4 | 23.08 | 3504 | 1492 | 129918
EVERETT | 4 | 58.03 | 41667 | 12740 | 641002
FAIRHAVEN | 5 | 82.05 | 15873 | 8111 | 516473
FALL RIVER | 5 | 226.58 | 88857 | 38859 | 1905489
FALMOUTH | 5 | 229.31 | 31531 | 14682 | 1268182
FITCHBURG | 3 | 180.5 | 40318 | 13411 | 1118592
FLORIDA | 1 | 39.82 | 752 | 85 | 161317
FOXBOROUGH | 5 | 90.6 | 16865 | 15092 | 637901
FRAMINGHAM | 3 | 217.29 | 68318 | 48388 | 1850061
FRANKLIN | 3 | 135.24 | 31635 | 16032 | 917261
FREETOWN | 5 | 76.45 | 8870 | 4112 | 403188
GARDNER | 3 | 98.14 | 20228 | 8619 | 612961
GEORGETOWN | 4 | 55.86 | 8183 | 3005 | 305440
GILL | 2 | 34.38 | 1500 | 337 | 147769
GLOUCESTER | 4 | 88.15 | 28789 | 11199 | 658638
GOSHEN | 1 | 24.89 | 1054 | 158 | 105774
GOSNOLD | 5 | 2 | 75 | 46 | 8826
GRAFTON | 3 | 85.05 | 17765 | 4453 | 497382
GRANBY | 2 | 58.04 | 6240 | 999 | 278108
GRANVILLE | 1 | 64.15 | 1566 | 128 | 261996
GREAT BARRINGTON | 1 | 77.86 | 7104 | 5062 | 408565
GREENFIELD | 2 | 101.88 | 17456 | 10570 | 632767
GROTON | 3 | 104.3 | 10646 | 3714 | 518369
GROVELAND | 4 | 44.21 | 6459 | 1190 | 227609
HADLEY | 2 | 64.27 | 5250 | 6238 | 357465
HALIFAX | 5 | 52.33 | 7518 | 1416 | 268814
HAMILTON | 4 | 44.81 | 7764 | 1500 | 242002
HAMPDEN | 2 | 53.93 | 5139 | 1085 | 256039
HANCOCK | 1 | 14.94 | 717 | 416 | 67785
HANOVER | 5 | 85.93 | 13879 | 8122 | 519062
HANSON | 5 | 60.5 | 10209 | 1814 | 322487
HARDWICK | 2 | 85.43 | 2990 | 474 | 358226
HARVARD | 3 | 63.95 | 6520 | 5041 | 350285
HARWICH | 5 | 141.31 | 12243 | 4142 | 678322
HATFIELD | 2 | 50.26 | 3279 | 2079 | 241514
HAVERHILL | 4 | 231.53 | 60879 | 21283 | 1540921
HAWLEY | 1 | 44.11 | 337 | 28 | 174745
HEATH | 1 | 52.1 | 706 | 42 | 208463
HINGHAM | 5 | 111.51 | 22157 | 15756 | 761034
HINSDALE | 1 | 35.57 | 2032 | 319 | 155572
HOLBROOK | 5 | 38.68 | 10791 | 2763 | 252083
HOLDEN | 3 | 119.21 | 17346 | 3908 | 621740
HOLLAND | 2 | 35.88 | 2481 | 222 | 158507
HOLLISTON | 3 | 88.4 | 13547 | 6751 | 510535
HOLYOKE | 2 | 133.1 | 39880 | 22393 | 1035878
HOPEDALE | 3 | 28.19 | 5911 | 1990 | 171009
HOPKINTON | 3 | 106.01 | 14925 | 11160 | 639701
HUBBARDSTON | 3 | 82.37 | 4382 | 412 | 354416
HUDSON | 3 | 87.01 | 19063 | 9892 | 576994
HULL | 5 | 50.94 | 10293 | 1348 | 280261
HUNTINGTON | 1 | 36.6 | 2180 | 399 | 161508
IPSWICH | 4 | 72.83 | 13175 | 6209 | 440991
KINGSTON | 5 | 69.4 | 12629 | 5714 | 418335
LAKEVILLE | 5 | 70.65 | 10602 | 3286 | 381903
LANCASTER | 3 | 63.56 | 8055 | 2344 | 326952
LANESBOROUGH | 1 | 47.46 | 3091 | 1071 | 217570
LAWRENCE | 4 | 123.36 | 76377 | 29031 | 1307805
LEE | 1 | 52.76 | 5943 | 3524 | 285149
LEICESTER | 3 | 84.06 | 10970 | 2366 | 425820
LENOX | 1 | 51.51 | 5025 | 4116 | 281355
LEOMINSTER | 3 | 159.94 | 40759 | 20656 | 1125956
LEVERETT | 2 | 34.65 | 1851 | 175 | 149164
LEXINGTON | 4 | 130.75 | 31394 | 22841 | 977917
LEYDEN | 2 | 35.09 | 711 | 57 | 142255
LINCOLN | 4 | 52.1 | 6362 | 1920 | 266450
LITTLETON | 3 | 62.74 | 8924 | 7779 | 392913
LONGMEADOW | 2 | 84.21 | 15784 | 4245 | 479036
LOWELL | 4 | 188.16 | 106519 | 39810 | 1878937
LUDLOW | 2 | 122.97 | 21103 | 6782 | 694010
LUNENBURG | 3 | 81.76 | 10086 | 2767 | 415929
LYNN | 4 | 160.26 | 90329 | 24908 | 1492436
LYNNFIELD | 4 | 68.01 | 11596 | 5882 | 408304
MALDEN | 4 | 94.36 | 59450 | 13945 | 910155
MANCHESTER | 4 | 22.9 | 5136 | 1644 | 141386
MANSFIELD | 5 | 115.04 | 23184 | 12148 | 739102
MARBLEHEAD | 4 | 68.63 | 19808 | 5198 | 454958
MARION | 5 | 28.65 | 4907 | 2380 | 171015
MARLBOROUGH | 3 | 134 | 38499 | 32346 | 1147143
MARSHFIELD | 5 | 131.95 | 25132 | 6279 | 748833
MASHPEE | 5 | 114.2 | 14006 | 5257 | 596737
MATTAPOISETT | 5 | 42.97 | 6045 | 2019 | 229953
MAYNARD | 3 | 40.99 | 10106 | 3565 | 266163
MEDFIELD | 3 | 76.68 | 12024 | 3151 | 412909
MEDFORD | 4 | 91.72 | 56173 | 21343 | 965641
MEDWAY | 3 | 69.51 | 12752 | 3681 | 395749
MELROSE | 4 | 71.69 | 26983 | 6153 | 523747
MENDON | 3 | 56.02 | 5839 | 1683 | 275653
MERRIMAC | 4 | 37.41 | 6338 | 903 | 197021
METHUEN | 4 | 174.77 | 47255 | 16524 | 1176833
MIDDLEBOROUGH | 5 | 157.19 | 23116 | 9556 | 872590
MIDDLEFIELD | 1 | 38.29 | 521 | 51 | 153449
MIDDLETON | 4 | 48.65 | 8987 | 5384 | 310238
MILFORD | 3 | 109.05 | 27999 | 18157 | 816716
MILLBURY | 3 | 71.03 | 13261 | 5331 | 424242
MILLIS | 3 | 50.84 | 7891 | 2066 | 272982
MILLVILLE | 3 | 22.17 | 3190 | 198 | 109204
MILTON | 6 | 97.22 | 27003 | 6764 | 630775
MONROE | 1 | 16.41 | 121 | 24 | 65131
MONSON | 2 | 100.31 | 8560 | 1594 | 464905
MONTAGUE | 2 | 103.1 | 8437 | 2646 | 487346
MONTEREY | 1 | 48.18 | 961 | 187 | 196487
MONTGOMERY | 1 | 30.4 | 838 | 40 | 124549
MOUNT WASHINGTON | 1 | 17.43 | 167 | 12 | 69270
NAHANT | 4 | 16.56 | 3410 | 416 | 91242
NANTUCKET | 5 | 123.46 | 10172 | 7676 | 636803
NATICK | 3 | 124.1 | 33006 | 23222 | 966686
NEEDHAM | 6 | 120.05 | 28886 | 22137 | 911936
NEW ASHFORD | 1 | 10.52 | 228 | 36 | 42952
NEW BEDFORD | 5 | 264.89 | 95072 | 37157 | 2074700
NEW BRAINTREE | 2 | 49.9 | 999 | 276 | 204485
NEW MARLBOROUGH | 1 | 83.54 | 1509 | 347 | 339941
NEW SALEM | 2 | 35.32 | 990 | 106 | 145504
NEWBURY | 4 | 53.07 | 6666 | 1699 | 269575
NEWBURYPORT | 4 | 68.29 | 17416 | 11947 | 517445
NEWTON | 6 | 278.05 | 85146 | 56015 | 2283772
NORFOLK | 5 | 72.73 | 11227 | 3499 | 396465
NORTH ADAMS | 1 | 70.54 | 13708 | 6168 | 434969
NORTH ANDOVER | 4 | 117.63 | 28352 | 15010 | 815622
NORTH ATTLEBOROUGH | 5 | 120.74 | 28712 | 12093 | 795888
NORTH BROOKFIELD | 3 | 68.91 | 4680 | 949 | 310054
NORTH READING | 4 | 79.69 | 14892 | 9577 | 518167
NORTHAMPTON | 2 | 153.84 | 28549 | 20394 | 1021364
NORTHBOROUGH | 3 | 80.22 | 14155 | 9555 | 515275
NORTHBRIDGE | 3 | 77.97 | 15707 | 5414 | 467888
NORTHFIELD | 2 | 65.41 | 3032 | 899 | 285287
NORTON | 5 | 92.36 | 19031 | 6462 | 557499
NORWELL | 5 | 74.3 | 10506 | 9148 | 464196
NORWOOD | 5 | 99.94 | 28602 | 24110 | 854690
OAK BLUFFS | 5 | 36.38 | 4527 | 2012 | 194440
OAKHAM | 3 | 42.72 | 1902 | 161 | 180832
ORANGE | 2 | 87.03 | 7839 | 1731 | 410070
ORLEANS | 5 | 49.96 | 5890 | 4222 | 282050
OTIS | 1 | 41.91 | 1612 | 370 | 178276
OXFORD | 3 | 90.52 | 13709 | 5946 | 510422
PALMER | 2 | 86.94 | 12140 | 4796 | 472998
PAXTON | 3 | 38.76 | 4806 | 894 | 192438
PEABODY | 4 | 161.41 | 51251 | 24416 | 1242480
PELHAM | 2 | 22.76 | 1321 | 166 | 99251
PEMBROKE | 5 | 94.46 | 17837 | 7022 | 564691
PEPPERELL | 3 | 83.29 | 11497 | 1689 | 418259
PERU | 1 | 35.29 | 847 | 57 | 143906
PETERSHAM | 2 | 61.69 | 1234 | 131 | 250313
PHILLIPSTON | 2 | 44.82 | 1682 | 248 | 188654
PITTSFIELD | 1 | 195.81 | 44737 | 26685 | 1361954
PLAINFIELD | 1 | 47.44 | 648 | 111 | 190714
PLAINVILLE | 5 | 46.87 | 8264 | 4701 | 290720
PLYMOUTH | 5 | 231.94 | 56468 | 26582 | 1576533
PLYMPTON | 5 | 34.78 | 2820 | 1307 | 169092
PRINCETON | 3 | 79.23 | 3413 | 795 | 340477
PROVINCETOWN | 5 | 19.53 | 2942 | 2865 | 128535
QUINCY | 6 | 187.38 | 92271 | 50080 | 1905495
RANDOLPH | 6 | 97.89 | 32112 | 9648 | 699653
RAYNHAM | 5 | 75.69 | 13383 | 10363 | 502151
READING | 4 | 89.17 | 24747 | 7590 | 594643
REHOBOTH | 5 | 132.07 | 11608 | 1891 | 611822
REVERE | 4 | 83.75 | 51755 | 9803 | 771240
RICHMOND | 1 | 39.06 | 1475 | 247 | 164834
ROCHESTER | 5 | 66.23 | 5232 | 828 | 301662
ROCKLAND | 5 | 49.27 | 17489 | 8281 | 400716
ROCKPORT | 4 | 33.03 | 6952 | 1293 | 188396
ROWE | 1 | 35.26 | 393 | 139 | 141851
ROWLEY | 4 | 41.9 | 5856 | 2941 | 235373
ROYALSTON | 2 | 69.58 | 1258 | 96 | 280874
RUSSELL | 1 | 22.31 | 1775 | 142 | 100113
RUTLAND | 3 | 79.08 | 7973 | 1448 | 376561
SALEM | 4 | 90.2 | 41340 | 19174 | 839921
SALISBURY | 4 | 34.94 | 8283 | 3585 | 231162
SANDISFIELD | 1 | 81.02 | 915 | 169 | 324234
SANDWICH | 5 | 150.99 | 20675 | 6067 | 791996
SAUGUS | 4 | 85.02 | 26628 | 10567 | 625247
SAVOY | 1 | 49.11 | 692 | 60 | 196904
SCITUATE | 5 | 102.98 | 18133 | 3586 | 559609
SEEKONK | 5 | 101.66 | 13722 | 8575 | 584796
SHARON | 5 | 108 | 17612 | 3817 | 578595
SHEFFIELD | 1 | 81.17 | 3257 | 1520 | 355535
SHELBURNE | 1 | 48.71 | 1893 | 476 | 207866
SHERBORN | 3 | 55.96 | 4119 | 664 | 252539
SHIRLEY | 3 | 43.39 | 7211 | 3233 | 253231
SHREWSBURY | 3 | 149.95 | 35608 | 14969 | 987552
SHUTESBURY | 2 | 30.94 | 1771 | 164 | 134023
SOMERSET | 5 | 85.47 | 18165 | 4711 | 504578
SOMERVILLE | 4 | 89.77 | 75754 | 35151 | 1244338
SOUTH HADLEY | 2 | 84.35 | 17514 | 4872 | 497943
SOUTHAMPTON | 2 | 67.72 | 5792 | 1103 | 314265
SOUTHBOROUGH | 3 | 70.46 | 9767 | 8291 | 434459
SOUTHBRIDGE | 3 | 79.84 | 16719 | 6431 | 493541
SOUTHWICK | 2 | 73.76 | 9502 | 2972 | 383353
SPENCER | 3 | 99.2 | 11688 | 3095 | 498066
SPRINGFIELD | 2 | 443.18 | 153060 | 83939 | 3686931
STERLING | 3 | 84.61 | 7808 | 2593 | 410493
STOCKBRIDGE | 1 | 42.59 | 1947 | 1731 | 198997
STONEHAM | 4 | 63.58 | 21437 | 7562 | 473284
STOUGHTON | 5 | 112.08 | 26962 | 14058 | 773954
STOW | 3 | 54.69 | 6590 | 2479 | 284561
STURBRIDGE | 3 | 79.2 | 9268 | 5313 | 430518
SUDBURY | 3 | 138.53 | 17659 | 6637 | 731167
SUNDERLAND | 2 | 37.75 | 3684 | 909 | 181540
SUTTON | 3 | 94.79 | 8963 | 3317 | 466119
SWAMPSCOTT | 4 | 42.88 | 13787 | 3372 | 294704
SWANSEA | 5 | 103.12 | 15865 | 5546 | 568660
TAUNTON | 5 | 207.04 | 55874 | 23648 | 1441144
TEMPLETON | 2 | 67.84 | 8013 | 1611 | 334835
TEWKSBURY | 4 | 140.34 | 28961 | 16551 | 926237
TISBURY | 5 | 21.53 | 3949 | 2770 | 141650
TOLLAND | 1 | 39.09 | 485 | 37 | 156177
TOPSFIELD | 4 | 49.91 | 6085 | 2235 | 259823
TOWNSEND | 3 | 85.39 | 8926 | 2071 | 414576
TRURO | 5 | 38.33 | 2003 | 660 | 170187
TYNGSBOROUGH | 4 | 79.41 | 11292 | 4671 | 436531
TYRINGHAM | 1 | 25.62 | 327 | 19 | 102366
UPTON | 3 | 64.66 | 7542 | 1281 | 315555
UXBRIDGE | 3 | 97.77 | 13457 | 3534 | 508888
WAKEFIELD | 4 | 84.99 | 24932 | 15486 | 671939
WALES | 2 | 23.41 | 1838 | 179 | 105226
WALPOLE | 5 | 123.68 | 24070 | 11817 | 774618
WALTHAM | 4 | 113.22 | 60632 | 65001 | 1589266
WARE | 2 | 84.97 | 9872 | 2507 | 424054
WAREHAM | 5 | 127.06 | 21822 | 9456 | 745863
WARREN | 2 | 63.21 | 5135 | 708 | 287836
WARWICK | 2 | 55.44 | 780 | 49 | 222070
WASHINGTON | 1 | 42.2 | 538 | 84 | 169215
WATERTOWN | 6 | 73.2 | 31915 | 21975 | 746351
WAYLAND | 3 | 88.19 | 12994 | 4141 | 475606
WEBSTER | 3 | 72.33 | 16767 | 7388 | 475722
WELLESLEY | 6 | 110.74 | 27982 | 18337 | 825332
WELLFLEET | 5 | 54.02 | 2750 | 1186 | 242367
WENDELL | 2 | 46.37 | 848 | 91 | 187552
WENHAM | 4 | 27.49 | 4875 | 1211 | 152557
WEST BOYLSTON | 3 | 50.4 | 7669 | 3469 | 286287
WEST BRIDGEWATER | 5 | 50.69 | 6916 | 6924 | 323058
WEST BROOKFIELD | 2 | 50.62 | 3701 | 958 | 232470
WEST NEWBURY | 4 | 45.87 | 4235 | 732 | 214695
WEST SPRINGFIELD | 2 | 121.56 | 28391 | 17215 | 857031
WEST STOCKBRIDGE | 1 | 35.94 | 1306 | 229 | 151375
WEST TISBURY | 5 | 13.93 | 2740 | 813 | 81357
WESTBOROUGH | 3 | 95.1 | 18272 | 25689 | 788542
WESTFIELD | 2 | 189.95 | 41094 | 18548 | 1220590
WESTFORD | 3 | 153.04 | 21951 | 13331 | 893519
WESTHAMPTON | 2 | 43.84 | 1607 | 339 | 185427
WESTMINSTER | 3 | 87.55 | 7277 | 2665 | 419470
WESTON | 6 | 86.21 | 11261 | 5189 | 469124
WESTPORT | 5 | 135.99 | 15532 | 3983 | 676604
WESTWOOD | 6 | 81.39 | 14618 | 12833 | 561191
WEYMOUTH | 6 | 149.52 | 53743 | 20150 | 1161958
WHATELY | 2 | 31.27 | 1496 | 1051 | 143976
WHITMAN | 5 | 48.85 | 14489 | 3278 | 321367
WILBRAHAM | 2 | 99.68 | 14219 | 6027 | 550380
WILLIAMSBURG | 1 | 42.46 | 2482 | 597 | 188610
WILLIAMSTOWN | 1 | 52.48 | 7754 | 3983 | 300945
WILMINGTON | 4 | 96.57 | 22325 | 21762 | 774086
WINCHENDON | 2 | 94.97 | 10300 | 1746 | 456901
WINCHESTER | 4 | 73.12 | 21374 | 8216 | 517819
WINDSOR | 1 | 62.32 | 899 | 45 | 249663
WINTHROP | 6 | 36.03 | 17497 | 2156 | 277296
WOBURN | 4 | 129.25 | 38120 | 44087 | 1263668
WORCESTER | 3 | 434.61 | 181045 | 105122 | 4080627
WORTHINGTON | 1 | 57.48 | 1156 | 177 | 233918
WRENTHAM | 5 | 67.33 | 10955 | 6913 | 413620
YARMOUTH | 5 | 150.39 | 23793 | 8885 | 842826

## FOR DOC (hidden)
WEIGHTED PRIORITIZATION SAMPLE |  | Asset Need | Mobility | Equity | TOTAL SCORE | RANKING
PROJECT | Scoring | 50% | 35% | 15% | /10 | #
Sample Project 1 | Rating/10 | 4 | 8 | 10 | 6.3 | 6
| Score | 2 | 2.8 | 1.5
Sample Project 2 | Rating/10 | 10 | 4 | 4 | 7 | 4
| Score | 5 | 1.4 | 0.6
Sample Project 3 | Rating/10 | 8 | 5 | 4 | 6.35 | 5
| Score | 4 | 1.75 | 0.6
UNWEIGHTED PRIORITIZATION SAMPLE |  | Asset Need | Mobility | Equity | TOTAL SCORE | RANKING
PROJECT | Rating | /10 | /10 | /10 | - | #
Sample Project 1 | Rating/10 | 4 | 8 | 10 | 22 | 1
Sample Project 2 | Rating/10 | 10 | 4 | 4 | 18 | 2
Sample Project 3 | Rating/10 | 8 | 5 | 4 | 17 | 3