Draft- Schedule for State Plan and Annual Reports     Updated 4-5-23

WIOA State Plan (every 4 years)

·        SRC Reviews, analyzes, and advises MRC on the VR section: ~ June 2023-October 2023

·        Draft WIOA State Plan to Governor’s Office March 2024

·        Final WIOA State Plan to RSA by July 2024

Next WIOA State Plan update (every 2 years):

·        SRC reviews plan in September 2025

·        Draft WIOA State Plan to Governor’s Office January 28, 2026

·        WIOA State Plan to RSA by March 15, 2026

Cornell Law School’s Requirements for a State Rehabilitation Council: https://www.law.cornell.edu/cfr/text/34/361.17

SRC Annual Report

·        Recommendations for FY2024 due to MRC by June 30, 2023

·        MRC Responses to SRC FY2024 Recommendations by July 31, 2023

·        SRC Chairs provide draft committee reports by August 1, 2023 and State Plan will review drafts on August 9, 2023.

·        FY2023 Final SRC Annual Report due to RSA by November 1, 2023, including MRC Program Results

Detailed SRC 2024 Recommendation Timeline:

·        February 2023- April 2023- Committee start the process of developing their FY24 Recommendations

·        May 4, 2023- All recommendations are due at the Executive Committee meeting

·        June 1, 2023- The Executive Committee reviews and approves the recommendations to be presented at the June SRC meeting

·        June 22, 2023 - SRC members vote on recommendations.

·        June 23, 2023- SRC forwards the approved recommendations to MRC for MRC’s response

·        July 31, 2023- MRC's response to the recommendations is due.

·        August 9, 2023, at 11 am- State Plan Committee reviews MRC’s responses and prepares a work plan with MRC.

About SRC Recommendations

To increase the transparency of the State Plan recommendation process, the Massachusetts Rehabilitation Commission Statewide Rehabilitation Council has developed the following guidelines for State plan recommendations:

- Consistent with MRC and SRC Mission and Vision

- Actionable ideas within the scope of MRC’s authorized activities under the Vocational rehabilitation regulations

  - Use SMART goals as a framework: Specific (simple, sensible, significant) Measurable (meaningful, motivating) Achievable (agreed, attainable) Relevant (reasonable, realistic and resourced, results-based)Time bound (time-based, time limited, time/cost limited, timely, time-sensitive).

- Consistent with the Vocational Rehabilitation goals in the W.I.O.A. Combined State Plan

- Prioritize meeting consumers’ needs and improving consumers’ experiences with vocational rehabilitation service delivery

- Conscious of the resources of the SRC since Committees must agree to advise on and track the progress of working on the recommendations

- The SRC can reject recommendations

  - Attempt to revise to make actionable under VR regs

    - May require help of MRC liaison for Committee

  - If rejected, brief statement to recommender as to why

The SRC does intended that these guidelines be rigid rules. They offer one approach that can help the Council apply consist standards in drafting, accepting, or revising recommendations before the body votes on them.