**Draft- Schedule for State Plan and Annual Reports     Updated 2/8/23**

**WIOA State Plan (every 4 years)**

·        SRC Reviews, analyzes, and advises MRC on the VR section: ~ June 2023-October 2023

·        Draft WIOA State Plan to Governor’s Office October 30,2023

·        Final WIOA State Plan to RSA by April 1, 2024

 **Next WIOA State Plan update (every 2 years)**:

·        SRC reviews plan in September 2025

·        Draft WIOA State Plan to Governor’s Office January 28,2026

·        WIOA State Plan to RSA by March 15, 2026

Cornell Law School’s Requirements for a State Rehabilitation Council:<https://www.law.cornell.edu/cfr/text/34/361.17>

**SRC Annual Report**

·        Recommendations for FY2024 due to MRC by June 30, 2023

·        MRC Responses to SRC FY2024 Recommendations by July 31, 2023

·        SRC Chairs provide draft committee reports by October 11, 2023

·        FY2023 Final SRC Annual Report due to RSA by November 1, 2023, including MRC Program Results

**Draft- Detailed SRC 2024 Recommendation Timeline:**

·        February 2023- April 2023- Committee start the process of developing their FY24 Recommendations

·        May 4, 2023- All recommendations are due at the Executive Committee meeting

·        June 1, 2023- The Executive Committee reviews and approves the recommendations to be presented at the June SRC meeting

·        June 22, 2023 - SRC members vote on recommendations.

·        June 23, 2023- SRC forwards the approved recommendations to MRC for MRC’s response

·        July 31, 2023- MRC's response to the recommendations is due.

·        August 9, 2023, at 11 am- State Plan Committee reviews MRC’s responses and prepares to work on the recommendations.