## Sheet1
Advance Construction (AC) Schedule
MPO Projects |  |  |  |  | STIP: 2024 - 2028 (A) Revision 4+
Project | MPO | MassDOT Project Description | Prior Years | 2024 | 2025 | 2026 | 2027 | 2028 | Future STIP | Total AC Conversion | Adjusted TFPC
AC'd Year: Prior to 2024
602659 | Central Mass | CHARLTON- OXFORD- RECONSTRUCTION ON ROUTE 20, FROM RICHARDSON'S CORNER EASTERLY TO ROUTE 12, INCLUDES REHAB OF C-06-023 & REPLACEMENT OF O-06-002 | 5768000 | 0 | 2776050 | 0 | 0 | 0 | 0 | 2776050 | 81351662.08
607977 | Boston Region | HOPKINTON- WESTBOROUGH- RECONSTRUCTION OF I-90/I-495 INTERCHANGE | 38210845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
608049 | Southeastern Mass | FALL RIVER- CORRIDOR IMPROVEMENTS ON ROUTE 79/DAVOL STREET | 7283745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S12114 | Boston Region | ROYALL STREET SHUTTLE | 386278 | 148542 | 0 | 0 | 0 | 0 | 0 | 148542 | 534820
|  | Scheduled AC Conversions |  | 148542 | 2776050 | 0 | 0 | 0 | 0 | 2924592 | 81886482.08
AC'd Year: Prior to 2024
602202 | Merrimack Valley | SALISBURY- RECONSTRUCTION OF ROUTE 1 (LAFAYETTE ROAD) | 20455002 | 504643 | 0 | 0 | 0 | 0 | 0 | 504643 | 23556437
607403 | Old Colony | STOUGHTON- CORRIDOR IMPROVEMENTS ON ROUTE 138, FROM 300 FEET NORTH OF CHARLES AVENUE TO LINCOLN STREET (PHASE 1) | 8441033 | 8963299 | 0 | 0 | 0 | 0 | 0 | 8963299 | 11281680
607777 | Boston Region | WATERTOWN- REHABILITATION OF MOUNT AUBURN STREET (ROUTE 16) | 24409009 | 3494249 | 0 | 0 | 0 | 0 | 0 | 3494249 | 29430616
S12694 | Boston Region | NEWMO MICROTRANSIT SERVICE EXPANSION | 412665 | 268246 | 209663 | 0 | 0 | 0 | 0 | 477909 | 890574
S12697 | Boston Region | PLEASANT STREET SHUTTLE SERVICE EXPANSION | 437825 | 335434 | 228939 | 0 | 0 | 0 | 0 | 564373 | 1002198
S12699 | Boston Region | STONEHAM SHUTTLE SERVICE | 330189 | 261439 | 205189 | 0 | 0 | 0 | 0 | 466628 | 796817
S12700 | Boston Region | CATA ON DEMAND MICROTRANSIT SERVICE EXPANSION – ROCKPORT AND LANESVILLE | 333450 | 0 | 214776 | 0 | 0 | 0 | 0 | 214776 | 813291
S12701 | Boston Region | MWRTA CATCHCONNECT MICROTRANSIT SERVICE EXPANSION - HUDSON AND MARLBOROUGH | 141250 | 149425 | 159488 | 0 | 0 | 0 | 0 | 308913 | 450163
S12703 | Boston Region | MONTACHUSETT RTA MICROTRANSIT SERVICE | 479066 | 430354 | 406641 | 0 | 0 | 0 | 0 | 836995 | 1316061
S12705 | Boston Region | LYNN STATION IMPROVEMENTS PHASE II | 34500000 | 13600000 | 0 | 0 | 0 | 0 | 0 | 13600000 | 48100000
|  | Scheduled AC Conversions |  | 28007089 | 1424696 | 0 | 0 | 0 | 0 | 29431785 | 117637837
AC'd Year: 2024
603371 | Franklin Region | ORANGE- RECONSTRUCTION OF NORTH MAIN STREET, FROM SCHOOL STREET TO LINCOLN AVENUE (0.4 MILES) INCLUDES RELOCATION OF FALL HILL BROOK CULVERT | 0 | 7722290 | 664163 | 5463072 | 0 | 0 | 0 | 6127235 | 13849525
604499 | Montachusett | LEOMINSTER- RECONSTRUCTION/REHABILITATION ON ROUTE 12 (CENTRAL STREET), INCLUDING REHABILITATION OF L-08-022 | 0 | 13283024 | 4430970 | 0 | 0 | 0 | 0 | 4430970 | 21444970
609459 | Martha's Vineyard | TISBURY- DRAINAGE IMPROVEMENTS ON STATE HIGHWAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
611986 | Cape Cod | MASHPEE- CORRIDOR IMPROVEMENTS & RELATED WORK ON ROUTE 151, FROM THE FALMOUTH T.L. TO OLD BARNSTABLE ROAD (PHASE 2) | 0 | 11379754 | 3397392 | 6044254 | 0 | 0 | 0 | 9441646 | 39176886
613129 | Nantucket | NANTUCKET- INTERSECTION IMPROVEMENTS AT MILESTONE ROAD AND POLPIS ROAD AND EXTENSION OF 'SCONSET BIKEPATH | 0 | 668939 | 657575 | 0 | 0 | 0 | 0 | 657575 | 2952321
S12807 | Boston Region | MWRTA CATCHCONNECT MICROTRANSIT EXPANSION PHASE 2 – FRAMINGHAM AND NATICK EXTENDED HOURS | 0 | 175000 | 165625 | 162500 | 0 | 0 | 0 | 328125 | 503125
S12819 | Boston Region | JACKSON SQUARE STATION ACCESSIBILITY IMPROVEMENTS | 0 | 12250000 | 14000000 | 0 | 0 | 0 | 0 | 14000000 | 26250000
S12822 | Boston Region | COLUMBUS AVENUE BUS LANES PHASE 2 | 0 | 11750000 | 0 | 0 | 0 | 0 | 0 | 0 | 11750000
S12835 | Pioneer Valley | SPRINGFIELD- ARMORY SAFE ROUTES TO NATIONAL PARKS IMPROVEMENTS | 0 | 50000 | 0 | 400000 | 0 | 0 | 0 | 400000 | 698000
|  | Scheduled AC Conversions |  |  | 23315725 | 12069826 | 0 | 0 | 0 | 35385551 | 116624827
AC'd Year: 2025
608095 | Merrimack Valley | NORTH ANDOVER- CORRIDOR IMPROVEMENTS ON ROUTE 114, BETWEEN WAVERLY ROAD & WILLOW/MILL STREET | 0 | 0 | 6751996 | 7824600 | 10740691 | 0 | 6351062 | 18565291 | 45240498.16
608744 | Cape Cod | PROVINCETOWN- CORRIDOR IMPROVEMENTS AND RELATED WORK ON SHANK PAINTER ROAD, FROM ROUTE 6 TO BRADFORD STREET | 0 | 0 | 2457392 | 7325217 | 3139269 | 0 | 0 | 10464486 | 13391878.24
S12113 | Boston Region | TRANSIT MODERNIZATION PROGRAM | 0 | 0 | 2000000 | 6500000 | 6500000 | 6500000 | 0 | 19500000 | 21500000
S12124 | Boston Region | COMMUNITY CONNECTIONS PROGRAM | 0 | 0 | 909679 | 2337500 | 2500000 | 2500000 | 0 | 7337500 | 8334827
609286 | Pioneer Valley | NORTHAMPTON- DOWNTOWN COMPLETE STREETS CORRIDOR AND INTERSECTION IMPROVEMENTS ON MAIN STREET (ROUTE 9) | 0 | 0 | 15473207 | 4188494 | 0 | 0 | 0 | 4188494 | 30864734.16
602843 | Merrimack Valley | GEORGETOWN- RECONSTRUCTION ON ROUTE 97 (W. MAIN STREET) FROM MOULTON STREET TO GROVELAND T.L. | 0 | 0 | 6287978 | 4891456 | 0 | 0 | 0 | 4891456 | 11179434.24
605966 | Northern Middlesex | LOWELL- RECONSTRUCTION & RELATED WORK ON VFW HIGHWAY | 0 | 0 | 4997841 | 7490525 | 0 | 0 | 0 | 7490525 | 12935000
608436 | Boston Region | ASHLAND- REHABILITATION AND RAIL CROSSING IMPROVEMENTS ON CHERRY STREET | 0 | 0 | 0 | 0 | 0 | 831393 | 0 | 831393 | 1363351.48
S12820 | Boston Region | BIKESHARE SUPPORT SET ASIDE | 0 | 0 | 1000000 | 1000000 | 2000000 | 2000000 | 0 | 5000000 | 6000000
|  | Scheduled AC Conversions |  |  |  | 41557792 | 24879960 | 11831393 | 6351062 | 78269145 | 150809723.28
AC'd Year: 2026
605857 | Boston Region | NORWOOD- INTERSECTION IMPROVEMENTS @ ROUTE 1 & UNIVERSITY AVENUE/EVERETT STREET | 0 | 0 | 0 | 11125872 | 17573400 | 0 | 0 | 17573400 | 28699272
605983 | Franklin Region | WHATELY- REHABILITATION OF HAYDENVILLE ROAD, FROM CONWAY ROAD TO THE WILLIAMSBURG T.L. (1.7 MILES) | 0 | 0 | 0 | 1942317 | 9169553 | 1452495 | 0 | 10622048 | 13637966.76
608547 | Berkshire Region | EGREMONT- RECONSTRUCTION OF MOUNT WASHINGTON ROAD (PHASE I) | 0 | 0 | 0 | 10379265 | 3555839 | 0 | 0 | 3555839 | 13935103.92
609213 | Montachusett | HARVARD- RESURFACING AND BOX WIDENING ON AYER ROAD, FROM ROUTE 2 TO THE AYER TOWN LINE | 0 | 0 | 0 | 5640372 | 6424393 | 0 | 0 | 6424393 | 12064765.32
609317 | Northern Middlesex | CHELMSFORD- IMPROVEMENTS ON CHELMSFORD STREET (ROUTE 110) | 0 | 0 | 0 | 3909289 | 7916711 | 0 | 0 | 7916711 | 8956393.56
607231 | Pioneer Valley | WILLIAMSBURG- RECONSTRUCTION OF MOUNTAIN STREET | 0 | 0 | 0 | 11907596 | 2200000 | 0 | 0 | 2200000 | 14122662.12
605743 | Boston Region | IPSWICH- RESURFACING & RELATED WORK ON CENTRAL & SOUTH MAIN STREETS | 0 | 0 | 0 | 5702076 | 6026622 | 0 | 0 | 6026622 | 11728698.48
|  | Scheduled AC Conversions |  |  |  |  | 52866518 | 1452495 | 0 | 54319013 | 103144862.16
AC'd Year: 2027
606226 | Boston Region | BOSTON- RECONSTRUCTION OF RUTHERFORD AVENUE, FROM CITY SQUARE TO SULLIVAN SQUARE | 0 | 0 | 0 | 0 | 8600000 | 33500000 | 155659449 | 33500000 | 197759449.44
607981 | Boston Region | SOMERVILLE- MCGRATH BOULEVARD CONSTRUCTION | 0 | 0 | 0 | 0 | 35000000 | 30000000 | 33840000 | 30000000 | 98840000
609246 | Boston Region | LYNN- REHABILITATION OF WESTERN AVENUE (ROUTE 107) | 0 | 0 | 0 | 0 | 15000000 | 20000000 | 10897600 | 20000000 | 45897600
608196 | Cape Cod | DENNIS- CORRIDOR AND STREETSCAPE IMPROVEMENTS ON MAIN STREET (ROUTE 28), FROM UNCLE BARNEYS ROAD TO OLD MAIN STREET (PHASE 2) | 0 | 0 | 0 | 0 | 10366198 | 1393803 | 0 | 1393803 | 11760000
|  | Scheduled AC Conversions | [5 empty] | 84893803 | 200397049 | 84893803 | 354257049.44
AC'd Year: 2028
608737 | Berkshire Region | DALTON- RECONSTRUCTION OF DALTON DIVISION ROAD | 0 | 0 | 0 | 0 | 0 | 7293798 | 4176282 | 0 | 11470080
608788 | Merrimack Valley | HAVERHILL- ROADWAY RECONSTRUCTION ON NORTH AVENUE, FROM MAIN STREET (ROUTE 125) TO PLAISTOW NH | 0 | 0 | 0 | 0 | 0 | 703246 | 22897751 | 0 | 23600996.92
607610 | Franklin Region | BUCKLAND- RECONSTRUCTION AND BICYCLE ACCOMMODATION ON ROUTE 112 | 0 | 0 | 0 | 0 | 0 | 4373115 | 3177625 | 0 | 7946000
608264 | Cape Cod | YARMOUTH- CORRIDOR IMPROVEMENTS ON ROUTE 28 | 0 | 0 | 0 | 0 | 0 | 15472242 | 9587797 | 0 | 25060039.12
|  | Scheduled AC Conversions | [6 empty] | 39839455 | 0 | 68077116.04
|  | Non-Federal Aid* |  | 28155631 | 27516471 | 53627618 | 77746478 | 98177691 | 246587566 | 285223889 | 992437897

## Sheet2
Advance Construction (AC) Schedule
Statewide Projects |  |  |  |  | STIP: 2024 - 2028 (A) Revision 4+
Project | MPO | MassDOT Project Description | Prior Years | 2024 | 2025 | 2026 | 2027 | 2028 | Future STIP | Total AC Conversion | Adjusted TFPC
AC'd Year: Prior to 2024
602659 | Central Mass | CHARLTON- OXFORD- RECONSTRUCTION ON ROUTE 20, FROM RICHARDSON'S CORNER EASTERLY TO ROUTE 12, INCLUDES REHAB OF C-06-023 & REPLACEMENT OF O-06-002 | 55500000 | 8079873 | 0 | 0 | 0 | 0 | 0 | 8079873 | 78222752
607977 | Boston Region | HOPKINTON- WESTBOROUGH- RECONSTRUCTION OF I-90/I-495 INTERCHANGE | 89813484 | 80277187 | 83719910 | 66631580 | 18763280 | 0 | 0 | 249391957 | 300942837
608049 | Southeastern Mass | FALL RIVER- CORRIDOR IMPROVEMENTS ON ROUTE 79/DAVOL STREET | 49660385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled AC Conversions |  | 88357060 | 83719910 | 66631580 | 18763280 | 0 | 0 | 257471830 | 379165589
AC'd Year: Prior to 2024
602202 | Merrimack Valley | SALISBURY- RECONSTRUCTION OF ROUTE 1 (LAFAYETTE ROAD) | 2596792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheduled AC Conversions |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AC'd Year: 2024
604499 | Montachusett | LEOMINSTER- RECONSTRUCTION/REHABILITATION ON ROUTE 12 (CENTRAL STREET), INCLUDING REHABILITATION OF L-08-022 | 0 | 3730976 | 0 | 0 | 0 | 0 | 0 | 0 | 21444970
608930 | Merrimack Valley | LAWRENCE- LAWRENCE MANCHESTER RAIL CORRIDOR (LMRC) RAIL TRAIL | 0 | 13800000 | 7938600 | 6000000 | 0 | 0 | 0 | 13938600 | 29524355
611986 | Cape Cod | MASHPEE- CORRIDOR IMPROVEMENTS & RELATED WORK ON ROUTE 151, FROM THE FALMOUTH T.L. TO OLD BARNSTABLE ROAD (PHASE 2) | 0 | 9000000 | 0 | 0 | 0 | 0 | 0 | 0 | 39176886
S12632 | Statewide | 2024 Bridge Inspection & Data Control | 0 | 17900000 | 10619719 | 0 | 0 | 0 | 0 | 10619719 | 28519719
S12660 | Statewide | BIL-BFP SYSTEMATIC BRIDGE MAINTENANCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161000000
606522 | Merrimack Valley | ANDOVER- LAWRENCE- BRIDGE REHABILITATION, A-09-036, I-495 OVER ST 28 (SB), A-09-037, I-495 OVER B&M AND MBTA, A-09-041, I-495 OVER ST 28 (NB) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
609466 | Merrimack Valley | HAVERHILL- METHUEN- BRIDGE REPLACEMENT, H-12-040=M-17-030, I-495 (NB & SB) OVER MERRIMACK RIVER AND M-17-031, I-495 (NB & SB) OVER ROUTE 110 AND H-12-056, INDUSTRIAL AVENUE (EB & WB) OVER I-495 | 0 | 331731568 | 54475844 | 23780466 | 3896315 | 0 | 0 | 82152625 | 413082405
606527 | Southeastern Mass | NEW BEDFORD- BRIDGE REPLACEMENT, N-06-020, I-195 (EB & WB), RAMP C & F OVER ST 18, COUNTY STREET, STATE STREET, MASS COASTAL RAILROAD, PURCHASE STREET, WELD STREET, INCLUDES IMPROVEMENTS TO N-06-021, N-06-022, F-01-008 | 0 | 150000000 | 100000000 | 106263160 | 0 | 0 | 0 | 206263160 | 361234196
609411 | Montachusett | FITCHBURG- LEOMINSTER- TWIN CITIES RAIL TRAIL CONSTRUCTION (PHASE II) | 0 | 1000000 | 9583505 | 14000000 | 0 | 0 | 0 | 23583505 | 27981128
613129 | Nantucket | NANTUCKET- INTERSECTION IMPROVEMENTS AT MILESTONE ROAD AND POLPIS ROAD AND EXTENSION OF 'SCONSET BIKEPATH | 0 | 531061 | 1094746 | 0 | 0 | 0 | 0 | 1094746 | 2952321
S12783 | Statewide | STATEWIDE ITS Program - 2024-2028 | 0 | 5798028 | 10309868 | 10309868 | 10309868 | 10309868 | 0 | 41239472 | 47037500
S12787 | Statewide | Integrated Transportation Management System (ITMS) Software - stand in for S12748 | 0 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000
S12877 | Pioneer Valley | Pioneer Valley Transit Authority - REHAB/RENOVATE - MAINTENANCE FACILITY - Springfield O&M Facility at Cottage St. Electric Bus Chargers Expansion and Upgrades | 0 | 3791961 | 0 | 0 | 0 | 0 | 0 | 0 | 3791961
|  | Scheduled AC Conversions |  |  | 194022282 | 160353494 | 14206183 | 10309868 | 0 | 378891827 | 1150745441
AC'd Year: 2025
608095 | Merrimack Valley | NORTH ANDOVER- CORRIDOR IMPROVEMENTS ON ROUTE 114, BETWEEN WAVERLY ROAD & WILLOW/MILL STREET | 0 | 0 | 0 | 0 | 0 | 13572149 | 0 | 13572149 | 50460555.64
608744 | Cape Cod | PROVINCETOWN- CORRIDOR IMPROVEMENTS AND RELATED WORK ON SHANK PAINTER ROAD, FROM ROUTE 6 TO BRADFORD STREET | 0 | 0 | 470000 | 0 | 0 | 0 | 0 | 0 | 13391878.24
605304 | Merrimack Valley | HAVERHILL- BRIDGE REPLACEMENT, H-12-007 & H-12-025, BRIDGE STREET (SR 125) OVER THE MERRIMACK RIVER AND THE ABANDONED B&M RR (PROPOSED BIKEWAY) | 0 | 0 | 30900000 | 38105819 | 41900000 | 18494181 | 26600000 | 98500000 | 156000000
608436 | Boston Region | ASHLAND- REHABILITATION AND RAIL CROSSING IMPROVEMENTS ON CHERRY STREET | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 1222315.12
|  | Scheduled AC Conversions |  |  |  | 38105819 | 41900000 | 32066330 | 26600000 | 112072149 | 221074749
AC'd Year: 2026
605983 | Franklin Region | WHATELY- REHABILITATION OF HAYDENVILLE ROAD, FROM CONWAY ROAD TO THE WILLIAMSBURG T.L. (1.7 MILES) | 0 | 0 | 0 | 377828 | 190664 | 0 | 0 | 190664 | 13637966.76
S12633 | Statewide | 2026 Bridge Inspection & Data Control | 0 | 0 | 0 | 17900000 | 11047515 | 0 | 0 | 11047515 | 28947515
S12662 | Statewide | MassDOT Resiliency-focused Improvements (2026-2028 STIP) | 0 | 0 | 0 | 15000000 | 16500000 | 18000000 | 0 | 34500000 | 59524326
608819 | Cape Cod | BARNSTABLE- RESURFACING AND RELATED WORK ON ROUTE 6 | 0 | 0 | 0 | 16658015 | 21904341 | 8633644 | 0 | 30537985 | 47196000
|  | Scheduled AC Conversions |  |  |  |  | 49642520 | 26633644 | 0 | 76276164 | 149305807.76
AC'd Year: 2027
606728 | Boston Region | BOSTON- BRIDGE REPLACEMENT B-16-365, STORROW DRIVE OVER BOWKER RAMPS | 0 | 0 | 0 | 0 | 10477205 | 40075975 | 61502820 | 40075975 | 112056000
607329 | Boston Region | WAKEFIELD- LYNNFIELD- RAIL TRAIL EXTENSION, FROM THE GALVIN MIDDLE SCHOOL TO LYNNFIELD/PEABODY T.L. | 0 | 0 | 0 | 0 | 10600000 | 13943047 | 0 | 13943047 | 24543047.2
S12782 | Statewide | Place holder for core funded systematic bridge maintenance. | 0 | 0 | 0 | 0 | 29000000 | 60000000 | 9533879 | 60000000 | 98533879
|  | Scheduled AC Conversions | [5 empty] | 114019022 | 71036699 | 114019022 | 235132926.2
AC'd Year: 2028
608787 | Pioneer Valley | WILLIAMSBURG- CONSTRUCTION OF THE "MILL RIVER GREENWAY" SHARED USE PATH | 0 | 0 | 0 | 0 | 0 | 20658059 | 23352341 | 0 | 44010400
S12759 | Statewide | 2028 Bridge Inspection & Data Control | 0 | 0 | 0 | 0 | 0 | 17900000 | 11481728 | 0 | 29381728
608396 | Boston Region | LYNN- REVERE- BRIDGE RECONSTRUCTION, L-18-015=R-05-008, ROUTE 1A OVER SAUGUS RIVER | 0 | 0 | 0 | 0 | 0 | 54185724 | 51374276 | 0 | 105560000
|  | Scheduled AC Conversions | [6 empty] | 86208345 | 0 | 178952128
|  | Non-Federal Aid* |  | 88357060 | 277742192 | 265090893 | 124511983 | 183028864 | 183845044 | 938730992 | 2314376640.96