## Fiscal Data
Disability Employment Initiative Project - Round V- Financial Data
Quarter |  | QTR 1 | QTR 2 | QTR 3 | QTR 4 | QTR 5 | QTR 6 |  | QTR 7 |  | QTR 8 |  | QTR 9 |  | QTR 10 |  | QTR 11 | QTR 12 | QTR13 | QTR14
| Total | Oct-Dec 2014 | Jan-Mar 2015 | Apr-Jun 2015 | Jul-Sep 2015 | Oct-Dec 2015 | Jan-Mar 2016 | % of the plan need to be at 100% in order for the grant to succeed | Apr-Jun 2016 | % of the plan need to be at 100% in order for the grant to succeed | Jul-Sep 2016 | % of the plan need to be at 100% in order for the grant to succeed | Oct-Dec 2016 | % of the plan need to be at 100% in order for the grant to succeed | Jan-Mar 2017 | % of the plan need to be at 100% in order for the grant to succeed | Apr-Jun 2017 | Jul-Sep 2017 | Oct-Dec 2017 | Jan-Mar 2018 | TOTAL | AWARD
Planned | 2500000 | 178571.44 | 357142.88 | 535714.29 | 714285.72 | 892857.15 | 1071428.56 |  | 1250000 |  | 1428571.44 |  | 1607142.85 |  | 1785714.29 |  | 1964285.71 | 2142857.15 | 2321428.59 | 2500000 | 2500000
Actual |  | 0 | 55892 | 188481 | 272207.5 | 398782.62 | 573555.17 | 23% | 807129.14 | 32% | 1274321.81 | 51% | 1469271 | 59% | 1605648.17 | 64% | 0 | 0 |  |  | 6645290.7
Difference |  | 178571.44 | 301250.88 | 347233.29 | 442078.22 | 494074.53 | 676444.83 |  | 442870.86 |  | 154249.63 |  | 137871.85 |  | 180066.12 |  | 1964285.71 | 2142857.15 | 2321428.59 | 2500000 | -4145290.7
Central Mass WIB | 431000
Planned | 500000 | 35714.29 | 71428.57 | 107142.86 | 142857.15 | 178571.43 | 214285.71 |  | 250000 |  | 285714.29 |  | 321428.57 |  | 357142.86 |  | 392857.14 | 428571.43 | 464285.71 | 500000 | 500000
Actual |  | 0 | 2135 | 2735 | 19297 | 39018 | 84479 | 17% | 128679 | 26% | 173404 | 35% | 232859 | 54% | 295454 | 69% |  |  |  |  | 978062.01
|  |  | (3/31/2015) | (6/30/2015) | (9/30/2015) | (12/31/2015) | (3/31/2016) |  | (6/30/2016) |  | (9/30/2016) |  | (12/31/2016) |  | (3/31/2017) | [5 empty] | -478062.01
Metro North WIB
Planned | 530167 | 37869.07 | 75738.14 | 113607.21 | 151476.29 | 189345.36 | 227214.43 |  | 265083.5 |  | 302952.57 |  | 340821.64 |  | 378690.71 |  | 416559.79 | 454428.86 | 492297.93 | 530167 | 530167
Actual |  | 0 | 4291 | 8162 | 43664 | 76863 | 94753 | 18% | 168284 | 32% | 464015 | 88% | 487104 | 92% | 495493 | 93% |  |  |  |  | 1842632.23
|  |  | (3/31/2015) | (6/30/2015) | (9/30/2015) | (12/31/2015) | (3/31/2016) |  | (6/30/2016) |  | (9/30/2016) |  | (12/31/2016) |  | (3/31/2017) | [5 empty] | -1312465.23
North Central WIB | 709000
Planned | 640000 | 45714.29 | 91428.57 | 137142.86 | 182857.14 | 228571.43 | 274285.71 |  | 320000 |  | 365714.29 |  | 411428.57 |  | 457142.86 |  | 502857.14 | 548571.43 | 594285.71 | 640000 | 640000
Actual |  | 0 | 49466 | 177584 | 208837 | 246510 | 329697 | 52% | 361265 | 56% | 430624 | 67% | 462717 | 65% | 494941 | 70% |  |  |  |  | 2761644.1
| WBA/Central |  | (3/31/2015) | (6/30/2015) | (9/30/2015) | (12/31/2015) | (3/31/2016) |  | (6/30/2016) |  | (9/30/2016) |  | (12/31/2016) |  | (3/31/2017) | [5 empty] | -2121644.1
UMass WWL
Planned | 175000 | 12500 | 250000 | 37500 | 50000 | 62500 | 75000 |  | 87500 |  | 100000 |  | 112500 |  | 125000 |  | 137500 | 150000 | 162500 | 175000 | 175000
Actual |  | 0 | 0 |  |  | 20586.7 | 24730.22 | 14% | 55305 | 32% | 78140.67 | 45% | 100153.43 | 57% | 115881.9 | 66% |  |  |  |  | 394800.06
|  | Disability Employment Initiative Project - Round V- Financial Data QTR 5: (12/31/2015); Disability Employment Initiative Project - Round V- Financial Data QTR 6: (3/31/2016) |  | (6/30/2016) |  | (9/30/2016) |  | (12/31/2016) |  | (3/31/2017)
UMass ICI
Planned | 507000 | 36214.29 | 72428.57 | 108642.86 | 144857.14 | 181071.43 | 217285.71 |  | 253500 |  | 289714.29 |  | 325928.57 |  | 362142.86 |  | 398357.14 | 434571.43 | 470785.71 | 507000 | 507000
Actual |  | 0 | 0 |  | 409.5 | 15804.92 | 39895.95 | 7.9% | 50149.14 | 10% | 74920.14 | 15% | 114940.19 | 22% | 132790.27 | 26% |  |  |  |  | 428910.919
|  | Disability Employment Initiative Project - Round V- Financial Data QTR 4: (9/30/2015); Disability Employment Initiative Project - Round V- Financial Data QTR 5: (12/31/2015); Disability Employment Initiative Project - Round V- Financial Data QTR 6: (3/31/2016) |  | (6/30/2016) |  | (9/30/2016) |  | (12/31/2016) |  | (1/31/2017) | [5 empty] | 78089.081
DCS
Planned | 147833 | 10559.5 | 21119 | 31678.5 | 42238 | 52797.5 | 63357 |  | 73916.5 |  | 84476 |  | 95035.5 |  | 105595 |  | 116154.5 | 126714 | 137273.5 | 147833 | 147833 | Estimate
Actual |  | Disability Employment Initiative Project - Round V- Financial Data QTR 1: 0; Disability Employment Initiative Project - Round V- Financial Data QTR 2: 0 |  | 43447 | 29% | 53218 | 36% | 71498 | 48% | 71498 | [5 empty] | 239662.13
[9 empty] | (6/30/2016) |  | (9/30/2016) |  | (12/31/2016) |  | (12/31/2016) | [5 empty] | -91829.13
DEI V Fiscal Information
|  | 7% | 14% | 21% | 28% | 35% | 42% |  | 50% |  | 57% |  | 64% |  | 71% |  | 78% | 85% | 92% | 100%
| 2500000 | 178571.44 | 357142.88 | 535714.29 | 714285.72 | 892857.15 | 1071428.56 |  | 1250000 |  | 1428571.44 |  | 1607142.85 |  | 1785714.29 |  | 1964285.71 | 2142857.15 | 2321429.48 | 2500001
Central Mass - Heather Mahall
Metro North - Michael Hatfield | [8 empty] | 128679 |  | 173404 |  | 232859 |  | 295454
North Central MA - Mary Chase |  |  | 2135 | 2735 | 19297 | 39018 | 84479 |  | 168284 |  | 464015 |  | 487104 |  | 494531
|  |  | 4291 | 8162 | 43664 | 76863 | 94753 |  | 361265 |  | 430624 |  | 462717 |  | 495493
|  |  | 49466 | 177584 | 208837 | 246510 | 329697 |  | 55305 |  | 78140.67 |  | 100153.43 |  | 115881.9
|  | 28%: 409.5; 35%: 20586.7; 42%: 24730.22 |  | 50149.14 |  | 74920.14 |  | 114940.19 |  | 132790.27
|  |  | 55892 | 188481 |  | 15804.92 | 39895.95 |  | 43447 |  | 53218 |  | 71498 |  | 71498
272207.5
|  | 35%: 398782.62; 42%: 573555.17 |  | 807129.14 |  | 1274321.81 |  | 1469271.62 |  | 1605648.17

## Participant Data
Quarter | Goal - 3 years |  |  |  | QTR 2 Jan - March 2015 |  |  |  | QTR 3 Apri - June 2015 |  |  |  | QTR 4 July - Sept 2015 |  |  |  | QTR 5 Oct - Dec 2015 |  |  |  |  | QTR 6 Jan - Mar 2016 |  |  |  | QTR 7 Apr - June 2016 |  |  |  | QTR 8 July - Sept 2016 |  |  |  | QTR 9 Oct - Dec 2016 |  |  |  | QTR 10 Jan - Mar 2017 |  |  |  | QTR 11 Apr - June 2017 |  |  |  | QTR 12 July - September 2017 |  |  |  | Total |  |  |  | QTR 8 July - Sep 2016 |  |  |  | QTR 9 Sep 2016 - Dec 2016 |  |  |  | QTR 10 Jan 2017 - March 2017
| Participants Entering Career Pathways | Completed Training | Attained Creditals | Entered employmnet | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment | Enrollment | Completed Training | Attained Creditials | Entered Employment
[18 empty] | 2015-11-30 |  |  |  | 2016-01-20 |  |  |  | 2016-07-14
Central Mass WIB | 45 | 30 | 27 | 31.5 | [13 empty] | 19 | 1 | 1 | 2 | 22 | 1 | 1 | 4 | 37 | 16 | 16 | 7 | [24 empty] | 61 | 29 | 21 | 14 | 91 | 7 | 29 | 27 | 108 | 52 | 53 | 37
Metro North WIB | 100 | 85 | 75 | 70 | [13 empty] | 4 | 1 | 1 | 0 | 20 | 16 | 14 | 8 | 50 | 44 | 36 | 15 | [24 empty] | 79 | 58 | 71 | 28 | 84 | 71 | 73 | 41 | 85 | 71 | 92 | 48
North Central WIB | 45 | 36 | 29 | 31.5 | [13 empty] | 17 | 13 | 10 | 5 | 12 | 2 | 1 | 2 | 18 | 3 | 3 | 1 | [24 empty] | 21 | 14 | 23 | 2 | 22 | 7 | 11 | 2 | 22 | 12 | 10 | 5
Total | 190 | 151 | 131 | 133 | [13 empty] | 40 | 15 | 12 | 7 | 54 | 19 | 16 | 14 | 105 | 63 | 55 | 23 | [24 empty] | 161 | 101 | 115 | 44 | 197 | 85 | 113 | 70 | 215 | 135 | 155 | 90
Percentage | [21 empty] | 28.4% | 12.5% | 12.2% | 10.5% | 55.2% | 41.7% | 41.9% | 17.2% | [24 empty] | 84.7% | 66.8% | 87.7% | 33% | 103% | 56% | 86.25% | 53% | 113% | 89% | 118% | 68%
MA DEI V Implementation Schedule
Total
Participants Entering Career Pathways Programs | 165
Participants who completed training in career pathways program | 140
Participants who attained credentials | 123
Entered Employment Rate | 70%
Employment Retention Rate | 75%

## Sheet1
Disability Employment Initiative - Enrollement Numbers
| Career Centers | 3 Year Goal | 2013-09-30 | 2013-12-31 | 2014-03-19 | 2014-03-27
MOSES
1 | Franklin Hampshire C.C | 22 | 11 | 17 | 30 | 30
2 | Hampden C.C. | 175
| Career Point C.C | 88 | 12 | 18 | 26 | 28
| Future Workers C.C. | 87 | 12 | 18 | 23 | 23
3 | Lowell C.C. | 44 | 29 | 26 | 60 | 58
4 | North Shore C.C. | 79 | 4 | 10 | 17 | 14
| Total | 495 | 68 | 89 | 156 | 153